## DB (hidden)
MODON - Weekly Progress Report - Construction Projects
| Contract General Information | [7 empty] | Key Dates | [10 empty] | Cost Summary (SR) | [8 empty] | Performance Summary | [11 empty] | Shop Drawings |  |  |  | Material Approval |  |  | Procurement Summary | [6 empty] | Quality Reports | [15 empty] | Key Submittals Approval Status | [9 empty] | Invoices Summary | [13 empty] | Resources at Site | [6 empty] | Safety Statistics | [63 empty] | Primavera P6 Schedule Status | [7 empty] | Weekly Prgoress Photos
Data Date | Project Name | Project ID | Contractor | Consultant | Stage | Status | Modon PM | Project Scope | Contract Award | Contract Sign | Site Handover | Original Completion | Contract Award (Hijri) | Contract Sign (Hijri) | Site Handover (Hijri) | Original Completion (Hijri) | Revised Completion | Committed Completion | Forecast Completion | Original Contract Value | Revised Contract Value | Estimate At Completion Value | Potential Changes | O&M Value (if any) | Submitted Invoices (Gross Value) | Penalities | FIR Value (Todate) | Original Plan Value | Plan Value | Earn Value | Phys. Plan Value | Phys. Earn Value | Quality Score | Safety Score | Weekly PV (SAR) | Weekly EV (SAR) | Weekly PV % | Weekly PV % | Weekly Phys PV% | Weekly Phys PV% | Total SD Planned | SD Remaining | SD Pending | Total SD Submittals | Planned Materials Approv | Material Pending Approval | Materila Total Submittals | Total Materials | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Material on Site | Remaining Materials | Material Delivery Completion (Date) | NCR Issued | NCR Closed | NCR Pending | NCR Avg. Closing (Days) | SIR Issued | SIR Closed | SIR Pending | SIR Avg. Closing (Days) | MIR Issued | MIR Closed | MIR Pending | MIR Avg. Closing (Days) | FIR Issued | FIR Closed | FIR Pending | FIR Avg. Closing (Days) | 1 Quality Plan Approval | 2 Quality Plan Last Up | 3 Safety Plan Approval | 4 Safety Plan Last Up | 5 Construction Plan Approval | 6 Baseline Approval | 7 No of Approved Version of Schedule | 8 Last Approved Schedule | 9 BOQ Approval Date | 10 No of Approved Version of BOQ | Total Submitted Invoices | PM Approved Invoices | No of Paid Invoices | No of Pending Invoices | Advance Payment % | Retention % | Deduction / Penalties % | Submitted Invoices (SAR) | PM Approved Invoices (SAR) | Paid Invoices (SAR) | Last Submitted Period | Advance Payment (SAR) | Retention (SAR) | Deduction / Penalties (SAR) | Planned Head Count | Actual Head Count | Saudi Staff | Labor Planned | Labor Actual | Equipment Planned | Equipment Actual | This Week Total Hours Worked | This Week Safe Hours Worked | This Week LTI | This Week MTC (Healed w/o Disability) | This Week MTC (Healed w/ Disability) | This Week Near Miss | This Week First Aid Cases | This Week Fatality | This Week Fire Incident Cases | This Week Vehicle Incident | This Week Property Damages | This Week Induction Training | This Week No.of Internal Training | This Week No.of Internal Audit | This Week No. of Toolbox Talks | This Week Safety Awards/Incentives | This Month Total Hours Worked | This Month Safe Hours Worked | This Month LTI | This Month MTC (Healed w/o Disability) | This Month MTC (Healed w/ Disability) | This Month Near Miss | This Month First Aid Cases | This Month Fatality | This Month Fire Incident Cases | This Month Vehicle Incident | This Month Property Damages | This Month Induction Training | This Month No.of Internal Training | This Month No.of Internal Audit | This Month No. of Toolbox Talks | This Month Safety Awards/Incentives | YTD Total Hours Worked | YTD Safe Hours Worked | YTD LTI | YTD MTC (Healed w/o Disability) | YTD MTC (Healed w/ Disability) | YTD Near Miss | YTD First Aid Cases | YTD Fatality | YTD Fire Incident Cases | YTD Vehicle Incident | YTD Property Damages | YTD Induction Training | YTD No.of Internal Training | YTD No.of Internal Audit | YTD No. of Toolbox Talks | YTD Safety Awards/Incentives | Cum Total Hours Worked | Cum Safe Hours Worked | Cum LTI | Cum MTC (Healed w/o Disability) | Cum MTC (Healed w/ Disability) | Cum Near Miss | Cum First Aid Cases | Cum Fatality | Cum Fire Incident Cases | Cum Vehicle Incident | Cum Property Damages | Cum Induction Training | Cum No.of Internal Training | Cum No.of Internal Audit | Cum No. of Toolbox Talks | Cum Safety Awards/Incentives | Total Act. | Not Started | In Progress | Completed | Critical Path Act.Last Week | Critical Path Act.This Week | Failed start Last Week | Failed start This Week | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-06 | Construction of Industrial Units for Artisans in Najran | NJR1-05-005 | Labenat Al Bena | EGIS | Construction | Active | Eng. Ahmed Kotbi | The project scope covers the construction of the Low Process RBF Unit, Outside Mosque, Pump Shed, and GRP Water Tank, including site preparation works (demolition, excavation, and backfilling), concrete and masonry works, thermal and waterproofing systems, installation of doors and windows, finishing works, and specialties. It also includes pre-engineered structures, mechanical systems (sanitary, water supply, HVAC, and firefighting), and electrical systems such as substations, distribution networks, lighting, power, telecom, fire alarm, and solar power. | 2026-01-25 | 2026-02-12 | 2026-03-03 | 2027-01-02 | 2026-01-25 | 2026-02-12 | 2026-03-03 | 2027-01-02 | 2027-01-02 | 2026-10-15 | 2026-10-15 | 9554134 | 9554134 | 9554134 | 0 | 0 | 6505001 | -20000 | 8999964.68 | 100% | 71.19% | 94.66% | 75.51% | 95.73% | 0.88776 | 0.83 | 283058 | 98305.66 | 2.963% | 1.029% | 3.47% | 0.523% | 93 | 0 | 0 | 93 | 95 | 0 | 95 | 95 | 95 | 95 | 0 | 95 | 0 | 2026-09-09 | 17 | 17 | 0 | 3 | 18 | 18 | 0 | 3 | 64 | 64 | 0 | 3 | 407 | 407 | 0 | 3 | 2026-04-22 | 2026-04-22 | 2026-04-18 | 2026-04-18 | 2026-04-02 | 2026-04-01 | 0 | 2026-04-01 | N/A | 0 | 5 | 5 | 4 | 1 | 0 | 0 | 0.0020933 | 6505001 | 6505001 | 4460610 | 2026-08-31 | 0 | 0 | -20000 | 13 | 14 | 0 | 119 | 21 | 34 | 8 | 2040 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2040 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 80246 | 80246 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 48 | 4 | 1 | 26 | 2 | 80246 | 80246 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 48 | 4 | 1 | 26 | 2 | 1462 | 26 | 27 | 1409 | 0 | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0

## Weekly Progress Report
MODON - Weekly Progress Report - Construction Projects | [30 empty] | Data Date | 2026-10-06
Contract General Information | [5 empty] | Key Dates | [5 empty] | Cost Summary (SR) | [7 empty] | Performance Summary | [5 empty] | Project Scope
Project Name | Construction of Industrial Units for Artisans in Najran |  |  |  |  | Contract Award | 2026-01-25 | Contract Award (Hijri) | 2026-01-25 | Revised Completion | 2027-01-02 | Original Contract Value |  | 9554134 |  | O&M Value (if any) |  | 0 | EAC | Plan Value | 71.19% | Phys. Plan Value | 75.51% | Quality Score | 88.78% | The project scope covers the construction of the Low Process RBF Unit, Outside Mosque, Pump Shed, and GRP Water Tank, including site preparation works (demolition, excavation, and backfilling), concrete and masonry works, thermal and waterproofing systems, installation of doors and windows, finishing works, and specialties. It also includes pre-engineered structures, mechanical systems (sanitary, water supply, HVAC, and firefighting), and electrical systems such as substations, distribution networks, lighting, power, telecom, fire alarm, and solar power.
Project ID | NJR1-05-005 |  | Stage | Construction |  | Contract Sign | 2026-02-12 | Contract Sign (Hijri) | 2026-02-12 | Committed Completion | 2026-10-15 | Revised Contract Value |  | 9554134 | EAC | Submitted Invoices (Gross Value) |  | 6505001 |  | Earn Value | 94.66% | Phys. Earn Value | 95.73% |  | ¢¢¢¢¢ ¢¢¢££
Contractor | Labenat Al Bena |  | Status | Active |  | Site Handover | 2026-03-03 | Site Handover (Hijri) | 2026-03-03 | Forecast Completion | 2026-10-15 | Estimate At Completion Value |  | 9554134 | #REF! | Penalities |  | -20000 |  | Variance | 23.47% | Variance | 20.22% | Safety Score | 83%
Consultant | EGIS |  | Modon PM | Eng. Ahmed Kotbi |  | Original Completion | 2027-01-02 | Original Completion (Hijri) | 2027-01-02 | Variance | 79 | Potential Changes |  | 0 |  | FIR Value (Todate) |  | 8999964.68 |  | SPI | 1.3297 | SPI | 1.2678 |  | ¢¢¢¢¢ ¢¢¢££
Progress Overview
Earned Value Progress (SAR) | [13 empty] | Physical Progress (Effort) | [11 empty] | Earned Value Progress (%)
WBS |  | BOQ Value (SAR) | % Wt. | Weekly (SAR) |  | To Date (SAR) | [7 empty] | Budgeted | % Wt. | Weekly Physical Progress |  |  |  | To Date Physical Progress
|  |  |  | Planned | Earned | Crushed Planned | Original Plan | Earned | Crushed Plan % | Original Plan % | Earned % | Variance | SPI | (Manhours) |  | Planned | Earned | Plan % | Earned % | Planned | Earned | Plan % | Earned % | Variance | SPI
MOBILIZATION |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 8972.8 | 4% | 0 | 0 | 0% | 0% | 8972.8 | 8972.8 | 100% | 100% | 0% | 1
ENGINEERING |  | 281825.22 | 2.95% | 0 | 0 | 281825 | 281825 | 281825 | 100% | 100% | 100% | 0% | 1 | 8972.8 | 4% | 0 | 0 | 0% | 0% | 8972.8 | 8972.8 | 100% | 100% | 0% | 1
PROCUREMENT |  | 2536426.98 | 26.55% | 70374 | 11340 | 2536427 | 2305241 | 2536427 | 100% | 90.89% | 100% | 9.115% | 1.1003 | 26918.4 | 12% | 550.88 | 43.62 | 2.046% | 0.162% | 26167.62 | 26918.4 | 97.21% | 100% | 2.789% | 1.0287
Site Works |  | 682299 | 7.141% | 17649 | 0 | 682299 | 140617 | 682299 | 100% | 20.61% | 100% | 79.39% | 4.8522 | 10600 | 4.725% | 704 | 0 | 6.642% | 0% | 3976 | 10600 | 37.51% | 100% | 62.49% | 2.666
Concrete |  | 508590 | 5.323% | 990 | 0 | 508590 | 508590 | 508590 | 100% | 100% | 100% | 0% | 1 | 38936 | 17.36% | 456 | 0 | 1.171% | 0% | 38936 | 38936 | 100% | 100% | 0% | 1 | [8 empty] | 0
Masonry Work |  | 25032 | 0.262% | 3093 | 0 | 25032 | 24333 | 25032 | 100% | 97.21% | 100% | 2.792% | 1.0287 | 4992 | 2.225% | 896 | 0 | 17.95% | 0% | 4608 | 4992 | 92.31% | 100% | 7.692% | 1.0833 | [8 empty] | 0
Metal Works |  | 43560 | 0.4559% | 2160 | 0 | 43560 | 6480 | 43560 | 100% | 14.88% | 100% | 85.12% | 6.7222 | 1288 | 0.5742% | 96 | 0 | 7.453% | 0% | 288 | 1288 | 22.36% | 100% | 77.64% | 4.4722
Thermal & Moisture Protection |  | 114132 | 1.195% | 3792 | 0 | 114132 | 101351 | 114132 | 100% | 88.8% | 100% | 11.2% | 1.1261 | 5984 | 2.668% | 776 | 0 | 12.97% | 0% | 4320 | 5984 | 72.19% | 100% | 27.81% | 1.3852
Doors and Windows |  | 198780 | 2.081% | 86400 | 0 | 198780 | 86400 | 198780 | 100% | 43.47% | 100% | 56.53% | 2.3007 | 8048 | 3.588% | 1152 | 0 | 14.31% | 0% | 1152 | 8048 | 14.31% | 100% | 85.69% | 6.9861
Finishes |  | 173460 | 1.816% | 2700 | 11286.66 | 173460 | 10436 | 173460 | 100% | 6.016% | 100% | 93.98% | 16.6213 | 11200 | 4.993% | 672 | 368 | 6% | 3.286% | 2080 | 11200 | 18.57% | 100% | 81.43% | 5.3846
Specialties |  | 27450 | 0.2873% | 0 | 10050 | 27450 | 0 | 27450 | 100% | 0% | 100% | 100% |  | 1392 | 0.6205% | 0 | 416 | 0% | 29.89% | 0 | 1392 | 0% | 100% | 100%
Pre Engineered Structure |  | 1223640 | 12.81% | 0 | 0 | 1223640 | 1223640 | 1188960 | 100% | 97.17% | 97.17% | 0% | 1 | 18224 | 8.124% | 0 | 0 | 0% | 0% | 18224 | 16640 | 100% | 91.31% | -8.692% | 0.91308
Mechanical Work |  | 1175904 | 12.31% | 10728 | 50400 | 1175904 | 1093804 | 974304 | 100% | 82.86% | 82.86% | 0% | 1 | 29328 | 13.07% | 768 | 288 | 2.619% | 0.982% | 24224 | 28176 | 82.6% | 96.07% | 13.48% | 1.1631
Electrical Work |  | 1607621.4 | 16.83% | 85172 | 0 | 1607621 | 1018777 | 1565728 | 100% | 97.39% | 97.39% | 0% | 1 | 41144 | 18.34% | 1712 | 0 | 4.161% | 0% | 27464 | 39552.96 | 66.75% | 96.13% | 29.38% | 1.4402
Close-Out |  | 955413.4 | 10% | 0 | 15229 | 955413 | 0 | 723343 | 100% | 75.71% | 75.71% | 0% | 1 | 8320 | 3.709% | 0 | 57.6 | 0% | 0.6923% | 0 | 3072 | 0% | 36.92% | 36.92%
| Total | 9554134 | 100% | 283058 | 98305.66 | 9554133 | 6801494 | 9043890 | 100% | 71.19% | 94.66% | 23.47% | 1.3297 | 224320 | 100% | 7782.88 | 1173.22 | 3.47% | 0.523% | 169385.22 | 214744.96 | 75.51% | 95.73% | 20.22% | 1.2678
Construction Milestones
[26 empty] | Item No. | Milestones |  | Original (Baseline) | Latest Plan | Forecast | Status | Days Change
[26 empty] | 1 | Award Date |  | 2026-01-25 | 2026-01-25 | 2026-01-25 | A | 0
[26 empty] | 2 | Contract Sign Date |  | 2026-02-12 | 2026-02-12 | 2026-02-12 | A | 0
[26 empty] | 3 | Site Handover Date |  | 2026-03-03 | 2026-03-03 | 2026-03-03 | A | 0
[26 empty] | 4 | Complete Mobilization |  | 2025-03-31 | 2025-03-31 | 2025-03-31 | A | 0
[26 empty] | 5 | Complete existing condition survey, submission of Final Reports |  | 2025-03-31 | 2025-03-31 | 2025-03-31 | A | 0
[26 empty] | 6 | Completion of Long Lead Procurement and Material Delivery |  | 2026-10-27 | 2026-10-27 | 2026-09-02 | F | 55
[26 empty] | 7 | Completion of Short Lead Procurement and Material Delivery |  | 2026-10-29 | 2026-10-29 | 2026-08-18 | F | 72
[26 empty] | 8 | Complete All Warehouse |  | 2026-11-29 | 2026-11-29 | 2026-09-30 | F | 60
[26 empty] | 9 | Complete All Outside Mosque (Prayer Room) |  | 2026-12-05 | 2026-12-05 | 2026-09-30 | F | 66
Performance overview
Submittals Status | [10 empty] | Quality | [10 empty] | Safety
Shop Drawings | [10 empty] | Quality Reports | [10 empty] | Safety Statistics | [7 empty] | Proactive Vs Reactive Actions Taken
Item Per WBS |  | Total | Total Submitted Drawings |  |  |  |  | Remaining | Pending | Total Submittals | Quality Reports |  | Issued | Closed | Pending | Avg. Closing (Days) | Pending |  |  |  |  | Category | Item |  | This Week |  | This Month | Year to Date | Cumulative
|  |  | A | B | C | D | Processed | [9 empty] | 0-10 Days | 11-20 Days | 21-30 Days | 31-60 Days | > 60 Days
Structural |  | 19 | 19 | 0 | 0 |  | 19 | 0 | 0 | 19 | [11 empty] | General | Total Hours Worked |  | 2040 |  | 2040 | 80246 | 80246 |  |  | Proactive | 0
Architectural |  | 15 | 15 | 0 | 0 |  | 15 | 0 | 0 | 15 | Non Conformance (NCR) |  | 17 | 17 | 0 | 3 | 0 | 0 | 0 | 0 | 0 |  | Safe Hours Worked |  | 2040 |  | 2040 | 80246 | 80246 |  |  | Reactive | 4
Mechanical, Electrical , & External Infra |  | 47 | 47 | 0 | 0 |  | 47 | 0 | 0 | 47 | Site Instruction (SIR) |  | 18 | 18 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | Reactive | LTI |  | 0 |  | 0 | 0 | 0
Road |  | 12 | 12 | 0 | 0 |  | 12 | 0 | 0 | 12 | Material Inspection (MIR) |  | 64 | 64 | 0 | 3 | 0 | 0 | 0 | 0 | 0 |  | MTC (Healed w/o Disability) |  | 0 |  | 0 | 0 | 0
[11 empty] | Field Inspection (FIR) |  | 407 | 407 | 0 | 3 | 0 | 0 | 0 | 0 | 0 |  | MTC (Healed w/ Disability) |  | 0 |  | 0 | 0 | 0
TOTAL |  | 93 | 93 | 0 | 0 | 0 | 93 | 0 | 0 | 93 | Key Submittals Approval Status | [11 empty] | Near Miss |  | 0 |  | 0 | 2 | 2
Material Approval | [10 empty] | 1 Quality Plan Approval |  |  | 2026-04-22 |  | 6 Baseline Approval |  |  |  | 2026-04-01 |  |  | First Aid Cases |  | 0 |  | 0 | 1 | 1 | Total Hours Worked Vs Safe Hours Worked
Item Per WBS |  | Total | Total Submitted Material |  |  |  |  | Remaining to approve | Pending | Total Submittals | 2 Quality Plan Last Up |  |  | 2026-04-22 |  | 7 No of Approved Version of Schedule |  |  |  | 0 |  |  | Fatality |  | 0 |  | 0 | 0 | 0
|  |  | A | B | C | D | Processed | with Designer |  |  | 3 Safety Plan Approval |  |  | 2026-04-18 |  | 8 Last Approved Schedule |  |  |  | 2026-04-01 |  |  | Fire Incident Cases |  | 0 |  | 0 | 1 | 1
Earthworks |  | 8 | 8 | 0 |  |  | 8 | 0 | 0 | 8 | 4 Safety Plan Last Up |  |  | 2026-04-18 |  | 9 BOQ Approval Date |  |  |  | N/A |  |  | Vehicle Incident |  | 0 |  | 0 | 0 | 0
Structural |  | 14 | 14 | 0 |  |  | 14 | 0 | 0 | 14 | 5 Construction Plan Approval |  |  | 2026-04-02 |  | 10 No of Approved Version of BOQ |  |  |  | 0 |  |  | Property Damages |  | 0 |  | 0 | 0 | 0
Architectural |  | 23 | 23 | 0 |  |  | 23 | 0 | 0 | 23 | Invoices Summary | [10 empty] | Proactive | Induction Training |  | 0 |  | 0 | 48 | 48
Mechanical |  | 28 | 28 | 0 |  |  | 28 | 0 | 0 | 28 | Total Submitted Invoices |  | 5 | Submitted Invoices (SAR) |  |  | 6505001 |  | Contract Value (SR) | 9554134 |  |  | No.of Internal Training |  | 0 |  | 0 | 4 | 4
Electrical |  | 22 | 22 | 0 |  |  | 22 | 0 | 0 | 22 | PM Approved Invoices |  | 5 | PM Approved Invoices (SAR) |  |  | 6505001 |  | Planned Value (SR) | 6801494 |  |  | No.of Internal Audit |  | 0 |  | 0 | 1 | 1
TOTAL |  | 95 | 95 | 0 | 0 | 0 | 95 | 0 | 0 | 95 | No of Paid Invoices |  | 4 | Paid Invoices (SAR) |  |  | 4460610 |  | Earned Value (SR) | 9043890 |  |  | No. of Toolbox Talks |  | 1 |  | 1 | 26 | 26
Procurement Summary | [10 empty] | No of Pending Invoices |  | 1 | Last Submitted Period |  |  | 2026-08-31 |  | Submitted (SAR) | 6505001 |  |  | Safety Awards/Incentives |  | 0 |  | 0 | 2 | 2
Item Per WBS |  | Total Materials | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Material on Site | Remaining Materials | Material Delivery Completion (Date) |  |  | Advance Payment % |  | 0% | Advance Payment (SAR) |  |  | 0 |  | PM Approved (SAR) | 6505001 |  | Latest Contract Change Order Log
|  |  | A | B | C | D | Processed |  |  |  | Retention % |  | 0% | Retention (SAR) |  |  | 0 |  | Total Paid (SAR) | 4460610
Earthworks |  | 8 | 8 | 8 | 0 | 8 | 0 | 2026-09-05 |  |  | Deduction / Penalties % |  | 0.2093% | Deduction / Penalties (SAR) |  |  | -20000 |  |  |  |  | CCO No. | Date Added | Description of Change |  |  |  |  | Status | Cost | Sch Impact (Months) | Date Approved | Duration
Structural |  | 14 | 14 | 14 | 0 | 14 | 0 | 2026-07-25 |  |  | Resources at Site
Architectural |  | 23 | 23 | 23 | 0 | 23 | 0 | 2026-09-05 |  |  | Head Count - Non Manual |  |  |  | Head Count - Manual |  |  |  | Total Head Count |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
Mechanical |  | 28 | 28 | 28 | 0 | 28 | 0 | 2026-09-09 |  |  | Planned | Actual | Next Month Forecast | Saudi Staff | Planned | Actual | Next Month Forecast | Saudi Staff | Total Plan | Total Actual | Variance
Electrical |  | 22 | 22 | 22 | 0 | 22 | 0 | 2026-07-30 |  |  | 13 | 14 | 13 | 0 | 119 | 21 | 56 | 0 | 132 | 35 | -97 |  | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
TOTAL |  | 95 | 95 | 95 | 0 | 95 | 0 | 2026-09-09 |  |  | Manpower Breakdown by Trade | [6 empty] | Major Equipment
Primavera P6 Schedule Status | [10 empty] | Key Trade | Planned | Actual |  |  |  |  | Type | Planned | Actual | Idle |  | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
Project Activities Overview | [10 empty] | General Labor | 10 | 5 |  |  |  |  | Excavator | 2 | 0 | 0
Schedule Statistics |  |  |  |  | Active Schedule Activities | [5 empty] | Carpenter | 4 | 0 |  |  |  |  | Grader | 0 | 0 | 0 | Major Quantity Trackers
Total Act. | Not Started | In Progress | Completed | % | Active | Ahead | On | Behind | Flag | 0 | Steel Fixer | 5 | 0 |  |  |  |  | Loader | 1 | 1 | 0 | BOQ N0. | Item Description |  |  |  |  | Total Qty | Measu Unit | Plan to Date | Act to Date | Remaining | Variance
1462 | 26 | 27 | 1409 | 96.37% | 27 | 0 | 27 | 0 | 27 |  | Concreting Labor | 2 | 0 |  |  |  |  | Skid Loader | 4 | 1 | 0 | 2.1.6 | Backfill Material |  |  |  |  | 2615 | m3 | 2615 | 2615 | 0 | 0
Critical Path Activities |  |  | Free Float Management (Total) |  |  |  | Failed Start Activities |  |  |  | Mason | 6 | 0 |  |  |  |  | Dump Truck | 3 | 0 | 0 | 2.2.1 | Bituminous wearing course asphalt layer |  |  |  |  | 217 | m3 | 0 | 217 | 0 | 217
|  |  | Greater Than 14 Days |  | Less Than 14 Days | [5 empty] | Operator | 15 | 3 |  |  |  |  | Water Tank Truck | 2 | 1 | 0 | 2.2.2 | Bituminous base course asphalt layer |  |  |  |  | 304 | m3 | 0 | 304 | 0 | 304
Last Week | This Week | Diff | Last Week | This Week | Last Week | This Week | Last Week | This Week | Flag | 0 | Others | 77 | 13 |  |  |  |  | Other | 22 | 5 | 0 | 2.2.3 | Base course layer |  |  |  |  | 867 | m3 | 0 | 867 | 0 | 867
0 | 0 | 0 | 3 | 2 | 2 | 2 | 13 | 13 | 0 |  | Total | 119 | 21 |  |  |  |  | Total | 34 | 8 | 0 | 2.2.4 | Subgrade material |  |  |  |  | 1300 | m3 | 606.71 | 1300 | 0 | 693.29
Weekly Prgoress Photos | [15 empty] | Top Issues and Risks
Refer to the Weekly Photo Sheet | [15 empty] | Issue No | Date Identified | Issue Description |  |  |  | Responsible | Action Taken |  |  | Mitigation |  |  |  |  | Current Status | Expected/Actual Closure | Duration Elapsed
[16 empty] | 1 | [16 empty] | 46301
[16 empty] | 2 | [16 empty] | 46301
[16 empty] | 3 | [16 empty] | 46301
[16 empty] | 4 | [16 empty] | 46301
[16 empty] | 5 | [16 empty] | 46301
Formulas:
Earned = MAX(I77:[Earned, row above])
1,301,000

## General Information
Weekly Progress Report - Construction Projects |  |  |  | Data Date | 2026-10-06
Contract General Information
Project Name | Construction of Industrial Units for Artisans in Najran
Project ID | NJR1-05-005
Contractor | Labenat Al Bena
Consultant | EGIS
Stage | Construction
Status | Active
Modon PM | Eng. Ahmed Kotbi
Key Dates
Contract Award Date | 2026-01-25
Contract Sign Date | 2026-02-12
Site Handover Date | 2026-03-03
Original Completion | 2027-01-02
Contract Award Date (Hijri) | 2026-01-25
Contract Sign Date (Hijri) | 2026-02-12
Site Handover Date (Hijri) | 2026-03-03
Original Completion (Hijri) | 2027-01-02
Revised Completion Date | 2027-01-02
Committed Completion Date | 2026-10-15
Forecast Completion | 2026-10-15
Variance | 79
Key Project Submittals | Submission Date | Days taken to approve orginal plan from site handover date
Quality Plan submission | 2026-04-16 | 44
Quality Plan approval | 2026-04-22
Quality Plan Last Update | 2026-04-22
Safety Plan submission | 2026-04-05 | 33
Safety Plan approval | 2026-04-18
Safety Plan Last Update | 2026-04-18
Risk Management Plan submission | 2026-05-13 | 71
Risk Management Plan approval | 2026-05-25
Risk Management Plan Last Update | 2026-05-25
Baseline Schedule submission | 2026-04-01 | 29
Baseline Schedule approval | 2026-04-01
No of Schedule Versions | 0
Last Recovery Schedule Approval Date | 2026-04-01
BOQ submission | 2026-03-03 | -305
BOQ approval | N/A |  | There is one revision of BOQ submitted
No of Approved Version of BOQ | 0
Construction Plan submission | 2026-04-02 | 30
Construction Plan Approval | 2026-04-02
Note on D25: AlNuaim, Abdulaziz: As per contract requirments submission of Plans should be 30 days after site handover

## PV-PH (hidden)
|  |  | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday
 | time axis 2024-01-09 to 2024-12-31
Activity ID | Budgeted Units | Spreadsheet Field | time axis 2024-01-09 to 2024-12-31
Project: HAL1-05-1 Civil Defense Fire Station in Hail Industrial City | 220460.02 | Budgeted Units | 255.34 | 533.36 | 831.16 | 2077.87 | 2245.69 | 1087.72 | 1210.9 | 888.95 | 1077.11 | 1173.43 | 1412.23 | 1580.18 | 2002.79 | 1307.97 | 1001.25 | 1763.77 | 1958.81 | 3815.2 | 4709.73 | 4188.35 | 4412.21 | 5224.69 | 5084.21 | 1917.88 | 7320.24 | 3942.95 | 4863.32 | 5293.56 | 8463.07 | 17579.75 | 19090.84 | 10307.51 | 5116.89 | 3622.87 | 2019.54 | 3577.07 | 4415.85 | 5145.74 | 8951.54 | 7055.71 | 3913.11 | 8551.62 | 6784.78 | 9307.43 | 4387.83 | 7117.5 | 825 | 257.5 | 493.2 | 485.6 | 1054.54 | 4056.33
Project: HAL1-05-1 Civil Defense Fire Station in Hail Industrial City | 220460.02 | Cum Budgeted Units | 255.34 | 788.7 | 1619.86 | 3697.73 | 5943.42 | 7031.14 | 8242.04 | 9130.99 | 10208.1 | 11381.53 | 12793.76 | 14373.94 | 16376.73 | 17684.7 | 18685.95 | 20449.72 | 22408.53 | 26223.73 | 30933.46 | 35121.81 | 39534.02 | 44758.71 | 49842.92 | 51760.8 | 59081.04 | 63023.99 | 67887.31 | 73180.87 | 81643.94 | 99223.69 | 118314.53 | 128622.04 | 133738.93 | 137361.8 | 139381.34 | 142958.41 | 147374.26 | 152520 | 161471.54 | 168527.25 | 172440.36 | 180991.98 | 187776.76 | 197084.19 | 201472.02 | 208589.52 | 209414.52 | 209672.02 | 210165.22 | 210650.82 | 211705.36 | 215761.69
WBS: HAL1-05-1.2 MOBILIZATION | 3445.8 | Budgeted Units | 147.78 | 295.56 | 511.56 | 1259.34 | 1231.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS: HAL1-05-1.2 MOBILIZATION | 3445.8 | Cum Budgeted Units | 147.78 | 443.34 | 954.9 | 2214.24 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8 | 3445.8
WBS: HAL1-05-1.7 SITE | 66611.78 | Budgeted Units | 22.08 | 46.22 | 55.61 | 163.79 | 240.88 | 350.73 | 366.06 | 157.13 | 268.48 | 207.96 | 53.23 | 3.78 | 140.84 | 95.31 | 112.46 | 273.46 | 533.01 | 1315.91 | 1885.85 | 2054.26 | 1636.18 | 1292.52 | 949.28 | 327.9 | 1128.49 | 1314.71 | 1438.17 | 1350.91 | 1268.86 | 9044.71 | 9515.05 | 3822.82 | 500.26 | 756.68 | 693.02 | 927.66 | 947.01 | 445.05 | 812.96 | 649.09 | 729.4 | 2536.28 | 1357.29 | 4476.26 | 3023.17 | 5791 | 0 | 120 | 493.2 | 485.6 | 431.2 | 0
WBS: HAL1-05-1.7 SITE | 66611.78 | Cum Budgeted Units | 22.08 | 68.3 | 123.91 | 287.7 | 528.58 | 879.31 | 1245.37 | 1402.5 | 1670.98 | 1878.94 | 1932.17 | 1935.95 | 2076.79 | 2172.1 | 2284.56 | 2558.02 | 3091.03 | 4406.94 | 6292.79 | 8347.05 | 9983.23 | 11275.75 | 12225.03 | 12552.93 | 13681.42 | 14996.13 | 16434.3 | 17785.21 | 19054.07 | 28098.78 | 37613.83 | 41436.65 | 41936.91 | 42693.59 | 43386.61 | 44314.27 | 45261.28 | 45706.33 | 46519.29 | 47168.38 | 47897.78 | 50434.06 | 51791.35 | 56267.61 | 59290.78 | 65081.78 | 65081.78 | 65201.78 | 65694.98 | 66180.58 | 66611.78 | 66611.78
WBS: HAL1-05-1.7.1 Engineering | 1607.2 | Budgeted Units | 22.08 | 46.22 | 55.61 | 163.79 | 240.88 | 229.01 | 244.35 | 116.56 | 241.48 | 180.97 | 41.71 | 0 | 10.22 | 8.18 | 3.68 | 2.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS: HAL1-05-1.7.1 Engineering | 1607.2 | Cum Budgeted Units | 22.08 | 68.3 | 123.91 | 287.7 | 528.58 | 757.59 | 1001.94 | 1118.5 | 1359.98 | 1540.95 | 1582.66 | 1582.66 | 1592.88 | 1601.06 | 1604.74 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2 | 1607.2
WBS: HAL1-05-1.7.2 Procurement | 7653.58 | Budgeted Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 26.99 | 11.52 | 3.78 | 130.62 | 87.13 | 35.44 | 51.01 | 36.34 | 49.91 | 68.19 | 131.25 | 44.52 | 74.19 | 46.78 | 26.73 | 126.99 | 199.41 | 130.75 | 141.24 | 262.19 | 65.52 | 16.8 | 635.82 | 6.26 | 20.01 | 40.02 | 15.66 | 107.01 | 13.05 | 332.96 | 169.09 | 9.4 | 1768.29 | 214.28 | 2527.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS: HAL1-05-1.7.2 Procurement | 7653.58 | Cum Budgeted Units | [8 empty] | 27 | 53.99 | 65.51 | 69.29 | 199.91 | 287.04 | 322.48 | 373.49 | 409.83 | 459.74 | 527.93 | 659.18 | 703.7 | 777.89 | 824.67 | 851.4 | 978.39 | 1177.8 | 1308.55 | 1449.79 | 1711.98 | 1777.5 | 1794.3 | 2430.12 | 2436.38 | 2456.39 | 2496.41 | 2512.07 | 2619.08 | 2632.13 | 2965.09 | 3134.18 | 3143.58 | 4911.87 | 5126.15 | 7653.58 | 7653.58 | 7653.58 | 7653.58 | 7653.58 | 7653.58 | 7653.58 | 7653.58 | 7653.58
WBS: HAL1-05-1.7.3 Construction | 57351 | Budgeted Units | 0 | 0 | 0 | 0 | 0 | 121.71 | 121.72 | 40.57 | 0 | 0 | 0 | 0 | 0 | 0 | 73.33 | 220 | 496.67 | 1266 | 1817.67 | 1923 | 1591.66 | 1218.34 | 902.5 | 301.16 | 1001.5 | 1115.3 | 1307.43 | 1209.66 | 1006.67 | 8979.19 | 9498.25 | 3187 | 494 | 736.67 | 653 | 912 | 840 | 432 | 480 | 480 | 720 | 768 | 1143 | 1948.83 | 3023.17 | 5791 | 0 | 120 | 493.2 | 485.6 | 431.2 | 0
WBS: HAL1-05-1.7.3 Construction | 57351 | Cum Budgeted Units | [5 empty] | 121.71 | 243.43 | 284 | 284 | 284 | 284 | 284 | 284 | 284 | 357.33 | 577.33 | 1074 | 2340 | 4157.67 | 6080.67 | 7672.33 | 8890.67 | 9793.17 | 10094.33 | 11095.83 | 12211.13 | 13518.56 | 14728.22 | 15734.89 | 24714.08 | 34212.33 | 37399.33 | 37893.33 | 38630 | 39283 | 40195 | 41035 | 41467 | 41947 | 42427 | 43147 | 43915 | 45058 | 47006.83 | 50030 | 55821 | 55821 | 55941 | 56434.2 | 56919.8 | 57351 | 57351
WBS: HAL1-05-1.8 MAIN BUILDING | 86348.45 | Budgeted Units | 43.76 | 106.12 | 162.97 | 403.24 | 538.92 | 523.51 | 627.47 | 570.49 | 708.78 | 696.53 | 528.39 | 432.05 | 332.45 | 356.59 | 276.19 | 350.84 | 583.17 | 1243.93 | 754.16 | 833.72 | 1537.3 | 2423.41 | 2311.2 | 686.71 | 2410.13 | 810.4 | 1066.39 | 1539.28 | 4773.4 | 6431.69 | 4988.55 | 4808.13 | 1364.58 | 1073.94 | 1253.9 | 2338.32 | 2078.99 | 2747.05 | 7366.2 | 5833.55 | 2603.71 | 3487.34 | 4856.16 | 3831.17 | 1364.67 | 1326.5 | 825 | 137.5 | 0 | 0 | 0 | 0
WBS: HAL1-05-1.8 MAIN BUILDING | 86348.45 | Cum Budgeted Units | 43.76 | 149.88 | 312.85 | 716.09 | 1255.01 | 1778.52 | 2405.99 | 2976.48 | 3685.26 | 4381.79 | 4910.18 | 5342.23 | 5674.68 | 6031.27 | 6307.46 | 6658.3 | 7241.47 | 8485.4 | 9239.56 | 10073.28 | 11610.58 | 14033.99 | 16345.19 | 17031.9 | 19442.03 | 20252.43 | 21318.82 | 22858.1 | 27631.5 | 34063.19 | 39051.74 | 43859.87 | 45224.45 | 46298.39 | 47552.29 | 49890.61 | 51969.6 | 54716.65 | 62082.85 | 67916.4 | 70520.11 | 74007.45 | 78863.61 | 82694.78 | 84059.45 | 85385.95 | 86210.95 | 86348.45 | 86348.45 | 86348.45 | 86348.45 | 86348.45
WBS: HAL1-05-1.8.1 Engineering | 3103.98 | Budgeted Units | 43.76 | 106.12 | 162.97 | 376.24 | 474.59 | 456.81 | 535.94 | 358.45 | 235.35 | 128.82 | 43.96 | 65.44 | 62.36 | 40.9 | 7.36 | 4.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS: HAL1-05-1.8.1 Engineering | 3103.98 | Cum Budgeted Units | 43.76 | 149.88 | 312.85 | 689.09 | 1163.68 | 1620.49 | 2156.43 | 2514.88 | 2750.23 | 2879.05 | 2923.01 | 2988.45 | 3050.81 | 3091.71 | 3099.07 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98 | 3103.98
WBS: HAL1-05-1.8.2 Procurement | 11205.47 | Budgeted Units | 0 | 0 | 0 | 27 | 64.32 | 66.71 | 91.53 | 20.04 | 9.43 | 27.7 | 9.44 | 21.61 | 88.37 | 89.41 | 66.83 | 81.93 | 74.9 | 271.14 | 277.23 | 326.71 | 310.3 | 403.41 | 291.21 | 104.2 | 662.63 | 319.6 | 547.2 | 771.28 | 331.4 | 421.68 | 345.81 | 1030.68 | 334.1 | 400.62 | 449.9 | 1406.81 | 595.49 | 864.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS: HAL1-05-1.8.2 Procurement | 11205.47 | Cum Budgeted Units |  |  |  | 27 | 91.32 | 158.03 | 249.56 | 269.6 | 279.03 | 306.73 | 316.17 | 337.78 | 426.15 | 515.56 | 582.39 | 664.32 | 739.22 | 1010.36 | 1287.59 | 1614.3 | 1924.6 | 2328.01 | 2619.22 | 2723.42 | 3386.05 | 3705.65 | 4252.85 | 5024.13 | 5355.53 | 5777.21 | 6123.02 | 7153.7 | 7487.8 | 7888.42 | 8338.32 | 9745.13 | 10340.62 | 11205.47 | 11205.47 | 11205.47 | 11205.47 | 11205.47 | 11205.47 | 11205.47 | 11205.47 | 11205.47 | 11205.47 | 11205.47 | 11205.47 | 11205.47 | 11205.47 | 11205.47
WBS: HAL1-05-1.8.3 Construction | 72039 | Budgeted Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192 | 464 | 540 | 475 | 345 | 181.71 | 226.29 | 202 | 264 | 508.27 | 972.8 | 476.93 | 507 | 1227 | 2020 | 2020 | 582.5 | 1747.5 | 490.8 | 519.2 | 768 | 4442 | 6010 | 4642.74 | 3777.45 | 1030.48 | 673.33 | 804 | 931.5 | 1483.5 | 1882.2 | 7366.2 | 5833.55 | 2603.72 | 3487.33 | 4856.17 | 3831.16 | 1364.67 | 1326.5 | 825 | 137.5 | 0 | 0 | 0 | 0
WBS: HAL1-05-1.8.3 Construction | 72039 | Cum Budgeted Units | [7 empty] | 192 | 656 | 1196 | 1671 | 2016 | 2197.71 | 2424 | 2626 | 2890 | 3398.27 | 4371.07 | 4848 | 5355 | 6582 | 8602 | 10622 | 11204.5 | 12952 | 13442.8 | 13962 | 14730 | 19172 | 25182 | 29824.74 | 33602.19 | 34632.67 | 35306 | 36110 | 37041.5 | 38525 | 40407.2 | 47773.4 | 53606.95 | 56210.67 | 59698 | 64554.17 | 68385.33 | 69750 | 71076.5 | 71901.5 | 72039 | 72039 | 72039 | 72039 | 72039
WBS: HAL1-05-1.9 SERVICE BUILDING | 19120.97 | Budgeted Units | 29.44 | 60.94 | 70.34 | 158.67 | 149.48 | 116.96 | 123.3 | 69.93 | 33.13 | 140.08 | 324 | 192 | 299.74 | 286.48 | 142.57 | 335.14 | 323.56 | 258.29 | 348.49 | 290.49 | 712.74 | 369.65 | 568 | 179.58 | 1101.08 | 70.19 | 941.07 | 1241.03 | 1562.46 | 1292.99 | 2010.95 | 1311.2 | 1287.46 | 902.04 | 28.18 | 28.19 | 467.13 | 1294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS: HAL1-05-1.9 SERVICE BUILDING | 19120.97 | Cum Budgeted Units | 29.44 | 90.38 | 160.72 | 319.39 | 468.87 | 585.83 | 709.13 | 779.06 | 812.19 | 952.27 | 1276.27 | 1468.27 | 1768.01 | 2054.49 | 2197.06 | 2532.2 | 2855.76 | 3114.05 | 3462.54 | 3753.03 | 4465.77 | 4835.42 | 5403.42 | 5583 | 6684.08 | 6754.27 | 7695.34 | 8936.37 | 10498.83 | 11791.82 | 13802.77 | 15113.97 | 16401.43 | 17303.47 | 17331.65 | 17359.84 | 17826.97 | 19120.97 | 19120.97 | 19120.97 | 19120.97 | 19120.97 | 19120.97 | 19120.97 | 19120.97 | 19120.97 | 19120.97 | 19120.97 | 19120.97 | 19120.97 | 19120.97 | 19120.97
WBS: HAL1-05-1.9.1 Engineering | 834.27 | Budgeted Units | 29.44 | 60.94 | 70.34 | 158.67 | 149.48 | 116.96 | 123.3 | 69.93 | 33.13 | 22.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS: HAL1-05-1.9.1 Engineering | 834.27 | Cum Budgeted Units | 29.44 | 90.38 | 160.72 | 319.39 | 468.87 | 585.83 | 709.13 | 779.06 | 812.19 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27 | 834.27
WBS: HAL1-05-1.9.2 Procurement | 2520.7 | Budgeted Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.99 | 26.03 | 24.37 | 62.87 | 55.03 | 85.49 | 85.49 | 79.49 | 76.49 | 92.15 | 141.75 | 27.58 | 249.08 | 70.19 | 173.07 | 425.03 | 202.46 | 44.99 | 314.95 | 0 | 0 | 4.7 | 28.18 | 28.19 | 169.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS: HAL1-05-1.9.2 Procurement | 2520.7 | Cum Budgeted Units | [12 empty] | 53.99 | 80.02 | 104.39 | 167.26 | 222.29 | 307.78 | 393.27 | 472.76 | 549.25 | 641.4 | 783.15 | 810.73 | 1059.81 | 1130 | 1303.07 | 1728.1 | 1930.56 | 1975.55 | 2290.5 | 2290.5 | 2290.5 | 2295.2 | 2323.38 | 2351.57 | 2520.7 | 2520.7 | 2520.7 | 2520.7 | 2520.7 | 2520.7 | 2520.7 | 2520.7 | 2520.7 | 2520.7 | 2520.7 | 2520.7 | 2520.7 | 2520.7 | 2520.7 | 2520.7
WBS: HAL1-05-1.9.3 Construction | 15766 | Budgeted Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 324 | 192 | 245.75 | 260.45 | 118.2 | 272.27 | 268.53 | 172.8 | 263 | 211 | 636.25 | 277.5 | 426.25 | 152 | 852 | 0 | 768 | 816 | 1360 | 1248 | 1696 | 1311.2 | 1287.47 | 897.33 | 0 | 0 | 298 | 1294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS: HAL1-05-1.9.3 Construction | 15766 | Cum Budgeted Units | [9 empty] | 118 | 442 | 634 | 879.75 | 1140.2 | 1258.4 | 1530.67 | 1799.2 | 1972 | 2235 | 2446 | 3082.25 | 3359.75 | 3786 | 3938 | 4790 | 4790 | 5558 | 6374 | 7734 | 8982 | 10678 | 11989.2 | 13276.67 | 14174 | 14174 | 14174 | 14472 | 15766 | 15766 | 15766 | 15766 | 15766 | 15766 | 15766 | 15766 | 15766 | 15766 | 15766 | 15766 | 15766 | 15766 | 15766
WBS: HAL1-05-1.10 GUARD ROOM 1 | 9829.32 | Budgeted Units | 6.13 | 12.27 | 12.27 | 28.22 | 28.22 | 46.62 | 44.98 | 54.4 | 29.44 | 47.63 | 188 | 376 | 421 | 159 | 144 | 192 | 215.5 | 436.49 | 639.32 | 306.65 | 247.47 | 370.47 | 432.31 | 161.66 | 614.98 | 326.97 | 326.98 | 374.97 | 206.98 | 182.97 | 1288.93 | 153.98 | 1123.88 | 372.18 | 25.06 | 25.05 | 198.34 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS: HAL1-05-1.10 GUARD ROOM 1 | 9829.32 | Cum Budgeted Units | 6.13 | 18.4 | 30.67 | 58.89 | 87.11 | 133.73 | 178.71 | 233.11 | 262.55 | 310.18 | 498.18 | 874.18 | 1295.18 | 1454.18 | 1598.18 | 1790.18 | 2005.68 | 2442.17 | 3081.49 | 3388.14 | 3635.61 | 4006.08 | 4438.39 | 4600.05 | 5215.03 | 5542 | 5868.98 | 6243.95 | 6450.93 | 6633.9 | 7922.83 | 8076.81 | 9200.69 | 9572.87 | 9597.93 | 9622.98 | 9821.32 | 9829.32 | 9829.32 | 9829.32 | 9829.32 | 9829.32 | 9829.32 | 9829.32 | 9829.32 | 9829.32 | 9829.32 | 9829.32 | 9829.32 | 9829.32 | 9829.32 | 9829.32
WBS: HAL1-05-1.10.1 Engineering | 282.18 | Budgeted Units | 6.13 | 12.27 | 12.27 | 28.22 | 28.22 | 46.62 | 44.98 | 54.4 | 29.44 | 19.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS: HAL1-05-1.10.1 Engineering | 282.18 | Cum Budgeted Units | 6.13 | 18.4 | 30.67 | 58.89 | 87.11 | 133.73 | 178.71 | 233.11 | 262.55 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18 | 282.18
WBS: HAL1-05-1.10.2 Procurement | 2877.14 | Budgeted Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.99 | 53.99 | 119.98 | 152.97 | 146.97 | 134.98 | 44.99 | 134.98 | 134.97 | 134.98 | 134.97 | 134.98 | 134.97 | 404.93 | 89.98 | 659.89 | 4.17 | 25.06 | 25.05 | 150.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS: HAL1-05-1.10.2 Procurement | 2877.14 | Cum Budgeted Units | [17 empty] | 53.99 | 107.98 | 227.96 | 380.93 | 527.9 | 662.88 | 707.87 | 842.85 | 977.82 | 1112.8 | 1247.77 | 1382.75 | 1517.72 | 1922.65 | 2012.63 | 2672.52 | 2676.69 | 2701.75 | 2726.8 | 2877.14 | 2877.14 | 2877.14 | 2877.14 | 2877.14 | 2877.14 | 2877.14 | 2877.14 | 2877.14 | 2877.14 | 2877.14 | 2877.14 | 2877.14 | 2877.14 | 2877.14 | 2877.14
WBS: HAL1-05-1.10.3 Construction | 6670 | Budgeted Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 188 | 376 | 421 | 159 | 144 | 192 | 215.5 | 382.5 | 585.33 | 186.67 | 94.5 | 223.5 | 297.33 | 116.67 | 480 | 192 | 192 | 240 | 72 | 48 | 884 | 64 | 464 | 368 | 0 | 0 | 48 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS: HAL1-05-1.10.3 Construction | 6670 | Cum Budgeted Units | [9 empty] | 28 | 216 | 592 | 1013 | 1172 | 1316 | 1508 | 1723.5 | 2106 | 2691.33 | 2878 | 2972.5 | 3196 | 3493.33 | 3610 | 4090 | 4282 | 4474 | 4714 | 4786 | 4834 | 5718 | 5782 | 6246 | 6614 | 6614 | 6614 | 6662 | 6670 | 6670 | 6670 | 6670 | 6670 | 6670 | 6670 | 6670 | 6670 | 6670 | 6670 | 6670 | 6670 | 6670 | 6670
WBS: HAL1-05-1.11 GUARD ROOM 2 | 6730.54 | Budgeted Units | 2.45 | 4.91 | 4.91 | 7.36 | 4.91 | 0 | 0 | 0 | 0 | 46 | 206 | 376 | 421 | 159 | 144 | 192 | 215.5 | 382.5 | 585.33 | 186.67 | 94.5 | 223.5 | 297.33 | 116.67 | 480 | 192 | 192 | 208 | 104 | 48 | 884 | 64 | 464 | 368 | 0 | 0 | 48 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS: HAL1-05-1.11 GUARD ROOM 2 | 6730.54 | Cum Budgeted Units | 2.45 | 7.36 | 12.27 | 19.63 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 70.54 | 276.54 | 652.54 | 1073.54 | 1232.54 | 1376.54 | 1568.54 | 1784.04 | 2166.54 | 2751.87 | 2938.54 | 3033.04 | 3256.54 | 3553.87 | 3670.54 | 4150.54 | 4342.54 | 4534.54 | 4742.54 | 4846.54 | 4894.54 | 5778.54 | 5842.54 | 6306.54 | 6674.54 | 6674.54 | 6674.54 | 6722.54 | 6730.54 | 6730.54 | 6730.54 | 6730.54 | 6730.54 | 6730.54 | 6730.54 | 6730.54 | 6730.54 | 6730.54 | 6730.54 | 6730.54 | 6730.54 | 6730.54 | 6730.54
WBS: HAL1-05-1.11.1 Engineering | 24.54 | Budgeted Units | 2.45 | 4.91 | 4.91 | 7.36 | 4.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS: HAL1-05-1.11.1 Engineering | 24.54 | Cum Budgeted Units | 2.45 | 7.36 | 12.27 | 19.63 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54 | 24.54
WBS: HAL1-05-1.11.3 Construction | 6706 | Budgeted Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 206 | 376 | 421 | 159 | 144 | 192 | 215.5 | 382.5 | 585.33 | 186.67 | 94.5 | 223.5 | 297.33 | 116.67 | 480 | 192 | 192 | 208 | 104 | 48 | 884 | 64 | 464 | 368 | 0 | 0 | 48 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS: HAL1-05-1.11.3 Construction | 6706 | Cum Budgeted Units | [9 empty] | 46 | 252 | 628 | 1049 | 1208 | 1352 | 1544 | 1759.5 | 2142 | 2727.33 | 2914 | 3008.5 | 3232 | 3529.33 | 3646 | 4126 | 4318 | 4510 | 4718 | 4822 | 4870 | 5754 | 5818 | 6282 | 6650 | 6650 | 6650 | 6698 | 6706 | 6706 | 6706 | 6706 | 6706 | 6706 | 6706 | 6706 | 6706 | 6706 | 6706 | 6706 | 6706 | 6706 | 6706
WBS: HAL1-05-1.12 PUMP ROOM | 18995.17 | Budgeted Units | 3.68 | 7.36 | 13.5 | 57.25 | 51.73 | 49.9 | 49.08 | 37.01 | 37.28 | 35.23 | 112.6 | 200.36 | 387.76 | 251.58 | 182.04 | 420.32 | 88.08 | 178.07 | 496.57 | 516.58 | 184 | 545.15 | 526.08 | 445.38 | 1585.56 | 1228.67 | 898.7 | 579.38 | 547.37 | 579.38 | 403.37 | 147.38 | 376.7 | 150.05 | 19.37 | 257.85 | 676.38 | 643.64 | 772.38 | 573.07 | 580 | 2528 | 571.33 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS: HAL1-05-1.12 PUMP ROOM | 18995.17 | Cum Budgeted Units | 3.68 | 11.04 | 24.54 | 81.79 | 133.52 | 183.42 | 232.5 | 269.51 | 306.79 | 342.02 | 454.62 | 654.98 | 1042.74 | 1294.32 | 1476.36 | 1896.68 | 1984.76 | 2162.83 | 2659.4 | 3175.98 | 3359.98 | 3905.13 | 4431.21 | 4876.59 | 6462.15 | 7690.82 | 8589.52 | 9168.9 | 9716.27 | 10295.65 | 10699.02 | 10846.4 | 11223.1 | 11373.15 | 11392.52 | 11650.37 | 12326.75 | 12970.39 | 13742.77 | 14315.84 | 14895.84 | 17423.84 | 17995.17 | 18995.17 | 18995.17 | 18995.17 | 18995.17 | 18995.17 | 18995.17 | 18995.17 | 18995.17 | 18995.17
WBS: HAL1-05-1.12.1 Engineering | 220.84 | Budgeted Units | 3.68 | 7.36 | 13.5 | 57.25 | 51.73 | 36.4 | 22.08 | 14.52 | 8.18 | 6.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS: HAL1-05-1.12.1 Engineering | 220.84 | Cum Budgeted Units | 3.68 | 11.04 | 24.54 | 81.79 | 133.52 | 169.92 | 192 | 206.52 | 214.7 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84 | 220.84
WBS: HAL1-05-1.12.2 Procurement | 2197.34 | Budgeted Units | 0 | 0 | 0 | 0 | 0 | 13.5 | 26.99 | 22.5 | 29.09 | 29.1 | 84.6 | 112.36 | 84.76 | 29.58 | 14.79 | 29.58 | 29.57 | 56.58 | 56.57 | 48.57 | 44.58 | 44.57 | 48.75 | 222.71 | 445.56 | 58 | 19.38 | 19.37 | 19.38 | 19.37 | 19.38 | 19.37 | 19.37 | 19.38 | 19.37 | 161.85 | 4.38 | 3.65 | 4.37 | 316.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS: HAL1-05-1.12.2 Procurement | 2197.34 | Cum Budgeted Units | [5 empty] | 13.5 | 40.49 | 62.99 | 92.08 | 121.18 | 205.78 | 318.14 | 402.9 | 432.48 | 447.27 | 476.85 | 506.42 | 563 | 619.57 | 668.14 | 712.72 | 757.29 | 806.04 | 1028.75 | 1474.31 | 1532.31 | 1551.69 | 1571.06 | 1590.44 | 1609.81 | 1629.19 | 1648.56 | 1667.93 | 1687.31 | 1706.68 | 1868.53 | 1872.91 | 1876.56 | 1880.93 | 2197.34 | 2197.34 | 2197.34 | 2197.34 | 2197.34 | 2197.34 | 2197.34 | 2197.34 | 2197.34 | 2197.34 | 2197.34 | 2197.34 | 2197.34
WBS: HAL1-05-1.12.3 Construction | 16577 | Budgeted Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 88 | 303 | 222 | 167.25 | 390.75 | 58.5 | 121.5 | 440 | 468 | 139.43 | 500.57 | 477.33 | 222.67 | 1140 | 1170.67 | 879.33 | 560 | 528 | 560 | 384 | 128 | 357.33 | 130.67 | 0 | 96 | 672 | 640 | 768 | 256.67 | 580 | 2528 | 571.33 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS: HAL1-05-1.12.3 Construction | 16577 | Cum Budgeted Units | [10 empty] | 28 | 116 | 419 | 641 | 808.25 | 1199 | 1257.5 | 1379 | 1819 | 2287 | 2426.43 | 2927 | 3404.33 | 3627 | 4767 | 5937.67 | 6817 | 7377 | 7905 | 8465 | 8849 | 8977 | 9334.33 | 9465 | 9465 | 9561 | 10233 | 10873 | 11641 | 11897.67 | 12477.67 | 15005.67 | 15577 | 16577 | 16577 | 16577 | 16577 | 16577 | 16577 | 16577 | 16577 | 16577
WBS: HAL1-05-1.6 CLOSEOUT | 9378 | Budgeted Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 623.33 | 4056.34
WBS: HAL1-05-1.6 CLOSEOUT | 9378 | Cum Budgeted Units | 2024-12-24: 623.33; 2024-12-31: 4679.67

## PV (hidden)
[5 empty] | 33 | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday | Tuesday
[5 empty] | 33 | 2024-01-16 | 2024-01-23 | 2024-01-30 | 2024-02-06 | 2024-02-13 | 2024-02-20 | 2024-02-27 | 2024-03-05 | 2024-03-12 | 2024-03-19 | 2024-03-26 | 2024-04-02 | 2024-04-09 | 2024-04-16 | 2024-04-23 | 2024-04-30 | 2024-05-07 | 2024-05-14 | 2024-05-21 | 2024-05-28 | 2024-06-04 | 2024-06-11 | 2024-06-18 | 2024-06-25 | 2024-07-02 | 2024-07-09 | 2024-07-16 | 2024-07-23 | 2024-07-30 | 2024-08-06 | 2024-08-13 | 2024-08-20 | 2024-08-27 | 2024-09-03 | 2024-09-10 | 2024-09-17 | 2024-09-24 | 2024-10-01 | 2024-10-08 | 2024-10-15 | 2024-10-22 | 2024-10-29 | 2024-11-05 | 2024-11-12 | 2024-11-19 | 2024-11-26 | 2024-12-03 | 2024-12-10 | 2024-12-17 | 2024-12-24 | 2024-12-31
Activity ID | Budgeted Total Cost | Budgeted Labor Units | Start | Finish | Spreadsheet Field | time axis 2024-01-16 to 2024-12-31
Civil Defense Fire Station in Hail Industrial City | 11141855 | 220460.02 | 2024-01-07 | 2025-01-06 | Planned Value Cost | 15390 | 1485 | 11831.4 | 22422.42 | 28755.46 | 18674.21 | 13885.71 | 13329 | 62496 | 58581 | 43470 | 25781.27 | 20954.29 | 30834.9 | 77837.7 | 110028.69 | 130521.15 | 108631.2 | 160604.55 | 305749.19 | 248632.89 | 265832.95 | 85935.93 | 249269.05 | 253696.94 | 351361.65 | 566591.4 | 633363.42 | 509956.68 | 458763.89 | 549854.62 | 557625.57 | 282234.77 | 138246.66 | 116546.37 | 286301.29 | 296323.16 | 374979.71 | 430088.13 | 462351.93 | 489355.71 | 397504.79 | 155793.08 | 224377.12 | 160616.79 | 111592.08 | 46723.68 | 18802.8 | 17203.68 | 119328.41 | 557092.75
Civil Defense Fire Station in Hail Industrial City | 11141855 | 220460.02 | 2024-01-07 | 2025-01-06 | Cum Planned Value Cost | 15390 | 16875 | 28706.4 | 51128.82 | 79884.28 | 98558.49 | 112444.2 | 125773.2 | 188269.2 | 246850.2 | 290320.2 | 316101.47 | 337055.76 | 367890.66 | 445728.36 | 555757.05 | 686278.2 | 794909.4 | 955513.95 | 1261263.14 | 1509896.03 | 1775728.98 | 1861664.91 | 2110933.96 | 2364630.9 | 2715992.55 | 3282583.95 | 3915947.37 | 4425904.05 | 4884667.94 | 5434522.56 | 5992148.13 | 6274382.9 | 6412629.56 | 6529175.93 | 6815477.22 | 7111800.38 | 7486780.09 | 7916868.22 | 8379220.15 | 8868575.86 | 9266080.65 | 9421873.73 | 9646250.85 | 9806867.64 | 9918459.72 | 9965183.4 | 9983986.2 | 10001189.88 | 10120518.29 | 10677611.04
PROJECT MILESTONES | 0 | 0 | 2024-01-07 | 2025-01-06 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT MILESTONES | 0 | 0 | 2024-01-07 | 2025-01-06 | Cum Planned Value Cost
MOBILIZATION | 0 | 3445.8 | 2024-01-07 | 2024-02-06 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MOBILIZATION | 0 | 3445.8 | 2024-01-07 | 2024-02-06 | Cum Planned Value Cost
SITE | 2802577.5 | 66611.78 | 2024-01-07 | 2024-12-23 | Planned Value Cost | 0 | 1485 | 8910 | 4894.02 | 19991.26 | 18674.21 | 5785.71 | 0 | 0 | 0 | 0 | 0 | 0 | 3636.9 | 10910.7 | 56656.35 | 56608.65 | 62913 | 72895.2 | 62832.75 | 104323.35 | 88359.33 | 12258.93 | 39071.8 | 151592.54 | 176194.05 | 167254.2 | 140418 | 98538.15 | 29703.6 | 61967.85 | 145612.35 | 127809 | 79098.3 | 34221.6 | 44313.75 | 15091.15 | 14957.4 | 14957.4 | 131682.22 | 155027.19 | 122641.17 | 89666.25 | 193565.47 | 87447.6 | 0 | 28125 | 18802.8 | 17203.68 | 26479.62 | 0
SITE | 2802577.5 | 66611.78 | 2024-01-07 | 2024-12-23 | Cum Planned Value Cost |  | 1485 | 10395 | 15289.02 | 35280.28 | 53954.49 | 59740.2 | 59740.2 | 59740.2 | 59740.2 | 59740.2 | 59740.2 | 59740.2 | 63377.1 | 74287.8 | 130944.15 | 187552.8 | 250465.8 | 323361 | 386193.75 | 490517.1 | 578876.43 | 591135.36 | 630207.16 | 781799.7 | 957993.75 | 1125247.95 | 1265665.95 | 1364204.1 | 1393907.7 | 1455875.55 | 1601487.9 | 1729296.9 | 1808395.2 | 1842616.8 | 1886930.55 | 1902021.7 | 1916979.1 | 1931936.5 | 2063618.72 | 2218645.91 | 2341287.08 | 2430953.33 | 2624518.8 | 2711966.4 | 2711966.4 | 2740091.4 | 2758894.2 | 2776097.88 | 2802577.5 | 2802577.5
Engineering | 19240.2 | 1607.2 | 2024-01-07 | 2024-04-18 | Planned Value Cost | 0 | 1485 | 8910 | 4894.02 | 2634.12 | 1317.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineering | 19240.2 | 1607.2 | 2024-01-07 | 2024-04-18 | Cum Planned Value Cost |  | 1485 | 10395 | 15289.02 | 17923.14 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2 | 19240.2
Procurement | 128268 | 7653.58 | 2024-02-28 | 2024-11-04 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99000 | 0 | 0 | 29268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement | 128268 | 7653.58 | 2024-02-28 | 2024-11-04 | Cum Planned Value Cost | 2024-07-02: 99000; 2024-07-09: 99000; 2024-07-16: 99000; 2024-07-23: 128268; 2024-07-30: 128268; 2024-08-06: 128268; 2024-08-13: 128268; 2024-08-20: 128268; 2024-08-27: 128268; 2024-09-03: 128268; 2024-09-10: 128268; 2024-09-17: 128268; 2024-09-24: 128268; 2024-10-01: 128268; 2024-10-08: 128268; 2024-10-15: 128268; 2024-10-22: 128268; 2024-10-29: 128268; 2024-11-05: 128268; 2024-11-12: 128268; 2024-11-19: 128268; 2024-11-26: 128268; 2024-12-03: 128268; 2024-12-10: 128268; 2024-12-17: 128268; 2024-12-24: 128268; 2024-12-31: 128268
Construction | 2655069.3 | 57351 | 2024-02-07 | 2024-12-23 | Planned Value Cost | 0 | 0 | 0 | 0 | 17357.14 | 17357.15 | 5785.71 | 0 | 0 | 0 | 0 | 0 | 0 | 3636.9 | 10910.7 | 56656.35 | 56608.65 | 62913 | 72895.2 | 62832.75 | 104323.35 | 88359.33 | 12258.93 | 39071.8 | 52592.54 | 176194.05 | 167254.2 | 111150 | 98538.15 | 29703.6 | 61967.85 | 145612.35 | 127809 | 79098.3 | 34221.6 | 44313.75 | 15091.15 | 14957.4 | 14957.4 | 131682.22 | 155027.19 | 122641.17 | 89666.25 | 193565.47 | 87447.6 | 0 | 28125 | 18802.8 | 17203.68 | 26479.62 | 0
Construction | 2655069.3 | 57351 | 2024-02-07 | 2024-12-23 | Cum Planned Value Cost |  |  |  |  | 17357.14 | 34714.29 | 40500 | 40500 | 40500 | 40500 | 40500 | 40500 | 40500 | 44136.9 | 55047.6 | 111703.95 | 168312.6 | 231225.6 | 304120.8 | 366953.55 | 471276.9 | 559636.23 | 571895.16 | 610966.96 | 663559.5 | 839753.55 | 1007007.75 | 1118157.75 | 1216695.9 | 1246399.5 | 1308367.35 | 1453979.7 | 1581788.7 | 1660887 | 1695108.6 | 1739422.35 | 1754513.5 | 1769470.9 | 1784428.3 | 1916110.52 | 2071137.71 | 2193778.88 | 2283445.13 | 2477010.6 | 2564458.2 | 2564458.2 | 2592583.2 | 2611386 | 2628589.68 | 2655069.3 | 2655069.3
MAIN BUILDING | 4439875.5 | 86348.45 | 2024-01-07 | 2024-11-27 | Planned Value Cost | 15390 | 0 | 0 | 0 | 0 | 0 | 8100 | 13329 | 57375 | 41512.5 | 9787.5 | 9567 | 6633 | 19170 | 51030 | 36762.6 | 58245.3 | 24682.2 | 69920.55 | 196531.65 | 110925 | 110925 | 3262.5 | 9787.5 | 37557 | 35106.3 | 228564.9 | 297377.52 | 299462.58 | 248835.14 | 272429.77 | 82964.67 | 34648.82 | 59148.36 | 76128.27 | 187789.09 | 226620.46 | 336406.31 | 262470.73 | 213369.71 | 209864.52 | 182945.63 | 61077.82 | 30811.65 | 73169.19 | 111592.08 | 18598.68 | 0 | 0 | 0 | 0
MAIN BUILDING | 4439875.5 | 86348.45 | 2024-01-07 | 2024-11-27 | Cum Planned Value Cost | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 23490 | 36819 | 94194 | 135706.5 | 145494 | 155061 | 161694 | 180864 | 231894 | 268656.6 | 326901.9 | 351584.1 | 421504.65 | 618036.3 | 728961.3 | 839886.3 | 843148.8 | 852936.3 | 890493.3 | 925599.6 | 1154164.5 | 1451542.02 | 1751004.6 | 1999839.74 | 2272269.51 | 2355234.18 | 2389883 | 2449031.36 | 2525159.63 | 2712948.72 | 2939569.18 | 3275975.49 | 3538446.22 | 3751815.93 | 3961680.45 | 4144626.08 | 4205703.9 | 4236515.55 | 4309684.74 | 4421276.82 | 4439875.5 | 4439875.5 | 4439875.5 | 4439875.5 | 4439875.5
Engineering | 15390 | 3103.98 | 2024-01-07 | 2024-04-18 | Planned Value Cost | 15390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineering | 15390 | 3103.98 | 2024-01-07 | 2024-04-18 | Cum Planned Value Cost | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390 | 15390
Procurement | 138510 | 11205.47 | 2024-01-28 | 2024-09-24 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement | 138510 | 11205.47 | 2024-01-28 | 2024-09-24 | Cum Planned Value Cost | 2024-07-16: 138510; 2024-07-23: 138510; 2024-07-30: 138510; 2024-08-06: 138510; 2024-08-13: 138510; 2024-08-20: 138510; 2024-08-27: 138510; 2024-09-03: 138510; 2024-09-10: 138510; 2024-09-17: 138510; 2024-09-24: 138510; 2024-10-01: 138510; 2024-10-08: 138510; 2024-10-15: 138510; 2024-10-22: 138510; 2024-10-29: 138510; 2024-11-05: 138510; 2024-11-12: 138510; 2024-11-19: 138510; 2024-11-26: 138510; 2024-12-03: 138510; 2024-12-10: 138510; 2024-12-17: 138510; 2024-12-24: 138510; 2024-12-31: 138510
Construction | 4285975.5 | 72039 | 2024-02-25 | 2024-11-27 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 8100 | 13329 | 57375 | 41512.5 | 9787.5 | 9567 | 6633 | 19170 | 51030 | 36762.6 | 58245.3 | 24682.2 | 69920.55 | 196531.65 | 110925 | 110925 | 3262.5 | 9787.5 | 37557 | 35106.3 | 90054.9 | 297377.52 | 299462.58 | 248835.14 | 272429.77 | 82964.67 | 34648.82 | 59148.36 | 76128.27 | 187789.09 | 226620.46 | 336406.31 | 262470.73 | 213369.71 | 209864.52 | 182945.63 | 61077.82 | 30811.65 | 73169.19 | 111592.08 | 18598.68 | 0 | 0 | 0 | 0
Construction | 4285975.5 | 72039 | 2024-02-25 | 2024-11-27 | Cum Planned Value Cost | [6 empty] | 8100 | 21429 | 78804 | 120316.5 | 130104 | 139671 | 146304 | 165474 | 216504 | 253266.6 | 311511.9 | 336194.1 | 406114.65 | 602646.3 | 713571.3 | 824496.3 | 827758.8 | 837546.3 | 875103.3 | 910209.6 | 1000264.5 | 1297642.02 | 1597104.6 | 1845939.74 | 2118369.51 | 2201334.18 | 2235983 | 2295131.36 | 2371259.63 | 2559048.72 | 2785669.18 | 3122075.49 | 3384546.22 | 3597915.93 | 3807780.45 | 3990726.08 | 4051803.9 | 4082615.55 | 4155784.74 | 4267376.82 | 4285975.5 | 4285975.5 | 4285975.5 | 4285975.5 | 4285975.5
SERVICE BUILDING | 1307801.7 | 19120.97 | 2024-01-07 | 2024-09-24 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4824 | 15052.5 | 23625 | 8015.63 | 6748.87 | 3510 | 6138 | 8478 | 9477 | 5629.5 | 8476.8 | 38170.87 | 14681.26 | 33440.62 | 12397.5 | 35583.75 | 0 | 45819 | 38248.8 | 107524.5 | 79061.55 | 143875.05 | 208999.2 | 281907 | 91602 | 0 | 0 | 30362.85 | 46152.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SERVICE BUILDING | 1307801.7 | 19120.97 | 2024-01-07 | 2024-09-24 | Cum Planned Value Cost | [8 empty] | 4824 | 19876.5 | 43501.5 | 51517.13 | 58266 | 61776 | 67914 | 76392 | 85869 | 91498.5 | 99975.3 | 138146.17 | 152827.43 | 186268.05 | 198665.55 | 234249.3 | 234249.3 | 280068.3 | 318317.1 | 425841.6 | 504903.15 | 648778.2 | 857777.4 | 1139684.4 | 1231286.4 | 1231286.4 | 1231286.4 | 1261649.25 | 1307801.7 | 1307801.7 | 1307801.7 | 1307801.7 | 1307801.7 | 1307801.7 | 1307801.7 | 1307801.7 | 1307801.7 | 1307801.7 | 1307801.7 | 1307801.7 | 1307801.7 | 1307801.7 | 1307801.7
Engineering | 0 | 834.27 | 2024-01-07 | 2024-03-10 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineering | 0 | 834.27 | 2024-01-07 | 2024-03-10 | Cum Planned Value Cost
Procurement | 0 | 2520.7 | 2024-03-27 | 2024-09-15 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement | 0 | 2520.7 | 2024-03-27 | 2024-09-15 | Cum Planned Value Cost
Construction | 1307801.7 | 15766 | 2024-03-06 | 2024-09-24 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4824 | 15052.5 | 23625 | 8015.63 | 6748.87 | 3510 | 6138 | 8478 | 9477 | 5629.5 | 8476.8 | 38170.87 | 14681.26 | 33440.62 | 12397.5 | 35583.75 | 0 | 45819 | 38248.8 | 107524.5 | 79061.55 | 143875.05 | 208999.2 | 281907 | 91602 | 0 | 0 | 30362.85 | 46152.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction | 1307801.7 | 15766 | 2024-03-06 | 2024-09-24 | Cum Planned Value Cost | [8 empty] | 4824 | 19876.5 | 43501.5 | 51517.13 | 58266 | 61776 | 67914 | 76392 | 85869 | 91498.5 | 99975.3 | 138146.17 | 152827.43 | 186268.05 | 198665.55 | 234249.3 | 234249.3 | 280068.3 | 318317.1 | 425841.6 | 504903.15 | 648778.2 | 857777.4 | 1139684.4 | 1231286.4 | 1231286.4 | 1231286.4 | 1261649.25 | 1307801.7 | 1307801.7 | 1307801.7 | 1307801.7 | 1307801.7 | 1307801.7 | 1307801.7 | 1307801.7 | 1307801.7 | 1307801.7 | 1307801.7 | 1307801.7 | 1307801.7 | 1307801.7 | 1307801.7
GUARD ROOM 1 | 127414.8 | 9829.32 | 2024-01-07 | 2024-09-18 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148.5 | 783 | 4500 | 1601.82 | 411.21 | 1370.25 | 4114.2 | 4117.02 | 2700 | 5338.5 | 1740 | 3580.2 | 4773.6 | 10500.6 | 3093 | 14886 | 5533.2 | 2435.4 | 6428.7 | 418.5 | 640.2 | 13696.8 | 1622.4 | 14043.45 | 11043.45 | 0 | 0 | 7206.3 | 688.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GUARD ROOM 1 | 127414.8 | 9829.32 | 2024-01-07 | 2024-09-18 | Cum Planned Value Cost | [8 empty] | 148.5 | 931.5 | 5431.5 | 7033.32 | 7444.53 | 8814.78 | 12928.98 | 17046 | 19746 | 25084.5 | 26824.5 | 30404.7 | 35178.3 | 45678.9 | 48771.9 | 63657.9 | 69191.1 | 71626.5 | 78055.2 | 78473.7 | 79113.9 | 92810.7 | 94433.1 | 108476.55 | 119520 | 119520 | 119520 | 126726.3 | 127414.8 | 127414.8 | 127414.8 | 127414.8 | 127414.8 | 127414.8 | 127414.8 | 127414.8 | 127414.8 | 127414.8 | 127414.8 | 127414.8 | 127414.8 | 127414.8 | 127414.8
Engineering | 0 | 282.18 | 2024-01-07 | 2024-03-10 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineering | 0 | 282.18 | 2024-01-07 | 2024-03-10 | Cum Planned Value Cost
Procurement | 0 | 2877.14 | 2024-05-01 | 2024-09-15 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement | 0 | 2877.14 | 2024-05-01 | 2024-09-15 | Cum Planned Value Cost
Construction | 127414.8 | 6670 | 2024-03-11 | 2024-09-18 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148.5 | 783 | 4500 | 1601.82 | 411.21 | 1370.25 | 4114.2 | 4117.02 | 2700 | 5338.5 | 1740 | 3580.2 | 4773.6 | 10500.6 | 3093 | 14886 | 5533.2 | 2435.4 | 6428.7 | 418.5 | 640.2 | 13696.8 | 1622.4 | 14043.45 | 11043.45 | 0 | 0 | 7206.3 | 688.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction | 127414.8 | 6670 | 2024-03-11 | 2024-09-18 | Cum Planned Value Cost | [8 empty] | 148.5 | 931.5 | 5431.5 | 7033.32 | 7444.53 | 8814.78 | 12928.98 | 17046 | 19746 | 25084.5 | 26824.5 | 30404.7 | 35178.3 | 45678.9 | 48771.9 | 63657.9 | 69191.1 | 71626.5 | 78055.2 | 78473.7 | 79113.9 | 92810.7 | 94433.1 | 108476.55 | 119520 | 119520 | 119520 | 126726.3 | 127414.8 | 127414.8 | 127414.8 | 127414.8 | 127414.8 | 127414.8 | 127414.8 | 127414.8 | 127414.8 | 127414.8 | 127414.8 | 127414.8 | 127414.8 | 127414.8 | 127414.8
GUARD ROOM 2 | 135848.7 | 6730.54 | 2024-01-07 | 2024-09-18 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148.5 | 783 | 4500 | 1601.82 | 411.21 | 1370.25 | 3687.3 | 3263.22 | 2821.5 | 5460 | 1740 | 3580.2 | 9455.4 | 9836.4 | 3174 | 14886 | 5614.2 | 2363.4 | 5209.8 | 602.4 | 673.2 | 11643.3 | 3275.4 | 18834.9 | 12834.9 | 0 | 0 | 7435.8 | 642.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GUARD ROOM 2 | 135848.7 | 6730.54 | 2024-01-07 | 2024-09-18 | Cum Planned Value Cost | [8 empty] | 148.5 | 931.5 | 5431.5 | 7033.32 | 7444.53 | 8814.78 | 12502.08 | 15765.3 | 18586.8 | 24046.8 | 25786.8 | 29367 | 38822.4 | 48658.8 | 51832.8 | 66718.8 | 72333 | 74696.4 | 79906.2 | 80508.6 | 81181.8 | 92825.1 | 96100.5 | 114935.4 | 127770.3 | 127770.3 | 127770.3 | 135206.1 | 135848.7 | 135848.7 | 135848.7 | 135848.7 | 135848.7 | 135848.7 | 135848.7 | 135848.7 | 135848.7 | 135848.7 | 135848.7 | 135848.7 | 135848.7 | 135848.7 | 135848.7
Engineering | 0 | 24.54 | 2024-01-07 | 2024-02-04 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineering | 0 | 24.54 | 2024-01-07 | 2024-02-04 | Cum Planned Value Cost
Construction | 135848.7 | 6706 | 2024-03-11 | 2024-09-18 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148.5 | 783 | 4500 | 1601.82 | 411.21 | 1370.25 | 3687.3 | 3263.22 | 2821.5 | 5460 | 1740 | 3580.2 | 9455.4 | 9836.4 | 3174 | 14886 | 5614.2 | 2363.4 | 5209.8 | 602.4 | 673.2 | 11643.3 | 3275.4 | 18834.9 | 12834.9 | 0 | 0 | 7435.8 | 642.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction | 135848.7 | 6706 | 2024-03-11 | 2024-09-18 | Cum Planned Value Cost | [8 empty] | 148.5 | 931.5 | 5431.5 | 7033.32 | 7444.53 | 8814.78 | 12502.08 | 15765.3 | 18586.8 | 24046.8 | 25786.8 | 29367 | 38822.4 | 48658.8 | 51832.8 | 66718.8 | 72333 | 74696.4 | 79906.2 | 80508.6 | 81181.8 | 92825.1 | 96100.5 | 114935.4 | 127770.3 | 127770.3 | 127770.3 | 135206.1 | 135848.7 | 135848.7 | 135848.7 | 135848.7 | 135848.7 | 135848.7 | 135848.7 | 135848.7 | 135848.7 | 135848.7 | 135848.7 | 135848.7 | 135848.7 | 135848.7 | 135848.7
PUMP ROOM | 1214151.3 | 18995.17 | 2024-01-07 | 2024-11-04 | Planned Value Cost | 0 | 0 | 2921.4 | 17528.4 | 8764.2 | 0 | 0 | 0 | 0 | 450 | 1057.5 | 4995 | 6750 | 1777.5 | 1957.5 | 751.5 | 668.7 | 4608 | 5832 | 1053.51 | 4474.29 | 12771 | 51750 | 135054 | 53400 | 89443.5 | 120885 | 87022.5 | 31581 | 11010 | 1560 | 14263.2 | 4296.6 | 0 | 6196.5 | 9193.5 | 7128 | 23616 | 152660 | 117300 | 124464 | 91918 | 5049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PUMP ROOM | 1214151.3 | 18995.17 | 2024-01-07 | 2024-11-04 | Cum Planned Value Cost |  |  | 2921.4 | 20449.8 | 29214 | 29214 | 29214 | 29214 | 29214 | 29664 | 30721.5 | 35716.5 | 42466.5 | 44244 | 46201.5 | 46953 | 47621.7 | 52229.7 | 58061.7 | 59115.21 | 63589.5 | 76360.5 | 128110.5 | 263164.5 | 316564.5 | 406008 | 526893 | 613915.5 | 645496.5 | 656506.5 | 658066.5 | 672329.7 | 676626.3 | 676626.3 | 682822.8 | 692016.3 | 699144.3 | 722760.3 | 875420.3 | 992720.3 | 1117184.3 | 1209102.3 | 1214151.3 | 1214151.3 | 1214151.3 | 1214151.3 | 1214151.3 | 1214151.3 | 1214151.3 | 1214151.3 | 1214151.3
Engineering | 29214 | 220.84 | 2024-01-07 | 2024-03-11 | Planned Value Cost | 0 | 0 | 2921.4 | 17528.4 | 8764.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineering | 29214 | 220.84 | 2024-01-07 | 2024-03-11 | Cum Planned Value Cost |  |  | 2921.4 | 20449.8 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214 | 29214
Procurement | 262926 | 2197.34 | 2024-02-11 | 2024-10-07 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45522 | 91044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement | 262926 | 2197.34 | 2024-02-11 | 2024-10-07 | Cum Planned Value Cost | 2024-06-18: 45522; 2024-06-25: 136566; 2024-07-02: 136566; 2024-07-09: 136566; 2024-07-16: 136566; 2024-07-23: 136566; 2024-07-30: 136566; 2024-08-06: 136566; 2024-08-13: 136566; 2024-08-20: 136566; 2024-08-27: 136566; 2024-09-03: 136566; 2024-09-10: 136566; 2024-09-17: 136566; 2024-09-24: 136566; 2024-10-01: 136566; 2024-10-08: 262926; 2024-10-15: 262926; 2024-10-22: 262926; 2024-10-29: 262926; 2024-11-05: 262926; 2024-11-12: 262926; 2024-11-19: 262926; 2024-11-26: 262926; 2024-12-03: 262926; 2024-12-10: 262926; 2024-12-17: 262926; 2024-12-24: 262926; 2024-12-31: 262926
Construction | 922011.3 | 16577 | 2024-03-18 | 2024-11-04 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 1057.5 | 4995 | 6750 | 1777.5 | 1957.5 | 751.5 | 668.7 | 4608 | 5832 | 1053.51 | 4474.29 | 12771 | 6228 | 44010 | 53400 | 89443.5 | 120885 | 87022.5 | 31581 | 11010 | 1560 | 14263.2 | 4296.6 | 0 | 6196.5 | 9193.5 | 7128 | 23616 | 26300 | 117300 | 124464 | 91918 | 5049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction | 922011.3 | 16577 | 2024-03-18 | 2024-11-04 | Cum Planned Value Cost | [9 empty] | 450 | 1507.5 | 6502.5 | 13252.5 | 15030 | 16987.5 | 17739 | 18407.7 | 23015.7 | 28847.7 | 29901.21 | 34375.5 | 47146.5 | 53374.5 | 97384.5 | 150784.5 | 240228 | 361113 | 448135.5 | 479716.5 | 490726.5 | 492286.5 | 506549.7 | 510846.3 | 510846.3 | 517042.8 | 526236.3 | 533364.3 | 556980.3 | 583280.3 | 700580.3 | 825044.3 | 916962.3 | 922011.3 | 922011.3 | 922011.3 | 922011.3 | 922011.3 | 922011.3 | 922011.3 | 922011.3 | 922011.3
CLOSEOUT | 1114185.5 | 9378 | 2024-12-24 | 2025-01-06 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92848.79 | 557092.75
CLOSEOUT | 1114185.5 | 9378 | 2024-12-24 | 2025-01-06 | Cum Planned Value Cost | 2024-12-24: 92848.79; 2024-12-31: 649941.54
Testing & Commissioning | 1114185.5 | 7480 | 2024-12-24 | 2025-01-06 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92848.79 | 557092.75
Testing & Commissioning | 1114185.5 | 7480 | 2024-12-24 | 2025-01-06 | Cum Planned Value Cost | 2024-12-24: 92848.79; 2024-12-31: 649941.54
Site Work | 311397.5 | 800 | 2024-12-24 | 2025-01-06 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25949.79 | 155698.75
Site Work | 311397.5 | 800 | 2024-12-24 | 2025-01-06 | Cum Planned Value Cost | 2024-12-24: 25949.79; 2024-12-31: 181648.54
Main Building | 493319.5 | 2200 | 2024-12-24 | 2025-01-06 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41109.96 | 246659.75
Main Building | 493319.5 | 2200 | 2024-12-24 | 2025-01-06 | Cum Planned Value Cost | 2024-12-24: 41109.96; 2024-12-31: 287769.71
Service Building | 145311.3 | 1800 | 2024-12-24 | 2025-01-06 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12109.28 | 72655.65
Service Building | 145311.3 | 1800 | 2024-12-24 | 2025-01-06 | Cum Planned Value Cost | 2024-12-24: 12109.28; 2024-12-31: 84764.93
Guard Room 1 | 14157.2 | 940.5 | 2024-12-24 | 2025-01-06 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1179.77 | 7078.6
Guard Room 1 | 14157.2 | 940.5 | 2024-12-24 | 2025-01-06 | Cum Planned Value Cost | 2024-12-24: 1179.77; 2024-12-31: 8258.37
Guard Room 2 | 15094.3 | 939.5 | 2024-12-24 | 2025-01-06 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1257.86 | 7547.15
Guard Room 2 | 15094.3 | 939.5 | 2024-12-24 | 2025-01-06 | Cum Planned Value Cost | 2024-12-24: 1257.86; 2024-12-31: 8805.01
Pump Room | 134905.7 | 800 | 2024-12-24 | 2025-01-06 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11242.14 | 67452.85
Pump Room | 134905.7 | 800 | 2024-12-24 | 2025-01-06 | Cum Planned Value Cost | 2024-12-24: 11242.14; 2024-12-31: 78694.99
Engineering | 0 | 0 | 2024-12-24 | 2024-12-30 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineering | 0 | 0 | 2024-12-24 | 2024-12-30 | Cum Planned Value Cost
Demobilization | 0 | 1898 | 2024-12-31 | 2025-01-06 | Planned Value Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Demobilization | 0 | 1898 | 2024-12-31 | 2025-01-06 | Cum Planned Value Cost
[9 empty] | #REF! | 0 | 0 | 0
[9 empty] | #REF! | 0 | 0 | 0
[9 empty] | #REF! | 0 | 0 | 0
[9 empty] | #REF! | 0 | 0 | 0
[9 empty] | #REF! | 0 | 0 | 0

## Progress
Project Scope Statement | The project scope covers the construction of the Low Process RBF Unit, Outside Mosque, Pump Shed, and GRP Water Tank, including site preparation works (demolition, excavation, and backfilling), concrete and masonry works, thermal and waterproofing systems, installation of doors and windows, finishing works, and specialties. It also includes pre-engineered structures, mechanical systems (sanitary, water supply, HVAC, and firefighting), and electrical systems such as substations, distribution networks, lighting, power, telecom, fire alarm, and solar power. | [13 empty] | Data Date | 2026-10-06
Earned Value Progress (SAR) | [8 empty] | Physical Progress (Effort)
WBS |  | BOQ Value (SAR) | % Wt. | Weekly (SAR) |  | To Date (SAR) |  |  | Budgeted | % Wt. | Weekly Physical Progress |  | To Date Physical Progress
|  |  |  | Planned | Earned | Crushed | Planned | Earned | (Manhours) |  | Planned | Earned | Planned | Earned
MOBILIZATION |  |  |  | 0 | 0 |  |  |  | 8972.8 | 4% | 0 | 0 | 8972.8 | 8972.8
ENGINEERING |  | 281825.22 | 2.95% | 0 | 0 | 281825 | 281825 | 281825 | 8972.8 | 4% | 0 | 0 | 8972.8 | 8972.8
PROCUREMENT |  | 2536426.98 | 26.55% | 70374 | 11340 | 2536427 | 2305241 | 2536427 | 26918.4 | 12% | 550.88 | 43.62 | 26167.62 | 26918.4
CONSTRUCTION |  | 5780468.4 | 60.5% | 212684 | 71736.66 | 5780468 | 4214428 | 5502295 | 171136 | 76.29% | 10203.2 | 12191.44 | 125272 | 166808.96
Site Works |  | 682299 | 7.141% | 17649 | 0 | 682299 | 140617 | 682299 | 10600 | 4.725% | 704 | 0 | 3976 | 10600
Concrete |  | 508590 | 5.323% | 990 | 0 | 508590 | 508590 | 508590 | 38936 | 17.36% | 456 | 0 | 38936 | 38936
Masonry Work |  | 25032 | 0.262% | 3093 | 0 | 25032 | 24333 | 25032 | 4992 | 2.225% | 896 | 0 | 4608 | 4992
Metal Works |  | 43560 | 0.4559% | 2160 | 0 | 43560 | 6480 | 43560 | 1288 | 0.5742% | 96 | 0 | 288 | 1288
Thermal & Moisture Protection |  | 114132 | 1.195% | 3792 | 0 | 114132 | 101351 | 114132 | 5984 | 2.668% | 776 | 0 | 4320 | 5984
Doors and Windows |  | 198780 | 2.081% | 86400 | 0 | 198780 | 86400 | 198780 | 8048 | 3.588% | 1152 | 0 | 1152 | 8048
Finishes |  | 173460 | 1.816% | 2700 | 11286.66 | 173460 | 10436 | 173460 | 11200 | 4.993% | 672 | 368 | 2080 | 11200
Specialties |  | 27450 | 0.2873% | 0 | 10050 | 27450 | 0 | 27450 | 1392 | 0.6205% | 0 | 416 | 0 | 1392
Pre Engineered Structure |  | 1223640 | 12.81% | 0 | 0 | 1223640 | 1223640 | 1188960 | 18224 | 8.124% | 0 | 0 | 18224 | 16640
Mechanical Work |  | 1175904 | 12.31% | 10728 | 50400 | 1175904 | 1093804 | 974304 | 29328 | 13.07% | 768 | 288 | 24224 | 28176
Electrical Work |  | 1607621.4 | 16.83% | 85172 | 0 | 1607621 | 1018777 | 1565728 | 41144 | 18.34% | 1712 | 0 | 27464 | 39552.96
Close-Out |  | 955413.4 | 10% | 0 | 15229 | 955413 | 0 | 723343 | 8320 | 3.709% | 0 | 0 | 0 | 3072
Close-Out |  | 955413.4 | 10% | 0 | 15229 | 955413 | 0 | 723343 | 8320 | 3.709% | 0 | 57.6 | 0 | 3072
| Total | 9554134 | 100% | 283058 | 98305.66 | 9554133 | 6801494 | 9043890 | 224320 | 100% | 10754.08 | 12235.06 | 169385.22 | 214744.96
|  |  |  | 2.963% | 1.029% | 100% | 71.19% | 94.66% |  |  | 4.794% | 5.454% | 75.51% | 95.73%
[17 empty] | 623.33 | 1246.67 | 1870 | 1870 | 2493.33 | 3116.67 | 3740 | 4363.33 | 4986.67 | 5610 | 5610 | 6233.33 | 6856.67 | 7480
[24 empty] | 316.33 | 316.33 | 316.33 |  | 316.33 | 316.33 | 316.33
[24 empty] | 316.33 | 632.67 | 949 | 949 | 1265.33 | 1581.67 | 1898

## Weekly Photos
Date | 2026-10-06
Fire Pump System Works
Fire Pump System Works
Landscaping Works
8

## FIR Summary
Project Name |  | Construction Of Industrial Units For Artisans In Najran
Project ID |  | cv |  | Project Budget | 9554134 |  |  | 122510
Date Pariod |  | Start Date | 2026-09-28 | To | Data Date | 2026-10-04
BOQ Item # | BOQ Description | FIR # | Date | FIR Description | Unit Rate | Current Period Quantity | Total (SR) | Comments
10.2.1.1 | Supply and install internal and external signs; comprising directional, identification, label, information signs, logos | NJR1-05-005-LBC-TS9-1-ARC-FIR-0060-00 | 2026-09-30 | Identification sign for toilets & prayer room | 250 | 3 | 750
10.3.1 | Supply and install MODON logo on the entrance including fixing and fittings | NJR1-05-005-LBC-TS9-1-ARC-FIR-0061-00 | 2026-09-30 | Inspection of Installation of MODON logo. | 5000 | 4 | 20000
16.10.2 | Supply, install, test, and comission of Lighting Fixtures complete including but not limited to wires & cables for lighting fixtures & their switches, plus conduits, supports and all the required accessories | NJR1-05-005-LBC-TS9-1-ELE-FIR--0031-00 | 2026-09-29 | Surface mounted LED lighting | 400 | 54 | 21600
16.10.3 | Supply, install, test, and comission of Lighting Fixtures complete including but not limited to wires & cables for lighting fixtures & their switches, plus conduits, supports and all the required accessories | NJR1-05-005-LBC-TS9-1-ELE-FIR--0031-00 | 2026-09-29 | Wall mounted LED Emergency lighting | 640 | 14 | 8960
16.10.4 | Supply, install, test, and comission of Lighting Fixtures complete including but not limited to wires & cables for lighting fixtures & their switches, plus conduits, supports and all the required accessories | NJR1-05-005-LBC-TS9-1-ELE-FIR--0031-00 | 2026-09-29 | Exits LED lighting | 480 | 14 | 6720
16.10.5 | Supply, install, test, and comission of Lighting Fixtures complete including but not limited to wires & cables for lighting fixtures & their switches, plus conduits, supports and all the required accessories | NJR1-05-005-LBC-TS9-1-ELE-FIR--0031-00 | 2026-09-29 | Outdoor wall mounted LED lighting | 360 | 42 | 15120
16.10.6 | Supply, install, test, and comission of Lighting Fixtures complete including but not limited to wires & cables for lighting fixtures & their switches, plus conduits, supports and all the required accessories | NJR1-05-005-LBC-TS9-1-ELE-FIR--0031-00 | 2026-09-29 | Outdoor wall mounted LED Flood lighting | 496 | 24 | 11904
16.10.7 | Supply, install, test, and comission of Lighting Fixtures complete including but not limited to wires & cables for lighting fixtures & their switches, plus conduits, supports and all the required accessories | NJR1-05-005-LBC-TS9-1-ELE-FIR--0031-00 | 2026-09-29 | Lighting Outlet | 160 | 12 | 1920
16.10.8 | Supply, install, test, and comission of Lighting Fixtures complete including but not limited to wires & cables for lighting fixtures & their switches, plus conduits, supports and all the required accessories | NJR1-05-005-LBC-TS9-1-ELE-FIR--0031-00 | 2026-09-29 | 2 Gang switch, one way | 256 | 26 | 6656
16.10.9 | Supply, install, test, and comission of Lighting Fixtures complete including but not limited to wires & cables for lighting fixtures & their switches, plus conduits, supports and all the required accessories | NJR1-05-005-LBC-TS9-1-ELE-FIR--0031-00 | 2026-09-29 | One Gang switch, one way | 240 | 7 | 1680
16.12.1 | Installation and Inspection Testing for all KHM'S | NJR1-05-005-LBC-TS9-1-ELE-FIR--0033-00 | 2026-10-01 | Grounding for all KWHM's | 1600 | 17 | 27200
0
0
Total Period Amount | [6 empty] | 122510
Previous weekly reports amount | [6 empty] | 8877454.68
Accomulative Amount | [6 empty] | 8999964.68

## Quality
QC OBSERVATIONS CHECKLIST
Project No. |  |  | NJR1-05-005 |  |  | OBS No. |  |  |  | 28 |  |  | Inspection Day: |  | 2026-10-06 | [17 empty] | 218
Project |  |  | Construction of Industrial Units for Artisans in Najran | [6 empty] | Contractor: Consultant: |  |  | LABENAT AL BENA EGIS
4 |  | Excellent |  | Quality Management System is being practiced and applies to MODON System | [11 empty] | 90 - 100 |  | QC Overall Score | 88.78% |  |  |  |  | 0% | 100 | 0.22883
3 |  | Good |  | Evidence of compliance with plans and procedures. | [11 empty] | 80 - 89 | [7 empty] | 0 | 89 | 0.20366
2 |  | Average |  | Indication level of compliance with standards but there is room for improvement | [11 empty] | 70 - 79 | [8 empty] | 79 | 0.18078
1 |  | Improve |  | Quality and Control is NOT being managed effectively. Needs Improvement | [11 empty] | ≤ 69 | [8 empty] | 69 | 0.15789
0 |  | N/A |  | Item was not applicable or this item was not reviewed during the inspection. | [11 empty] | Zero | [8 empty] | 100 | 0.22883
No. | Topic |  |  |  |  | E (4) | G (3) | A (2) | I (1) | N/A (0) | No. | Topic |  |  |  | E (4) | G (3) | A (2) | I (1) | N/A (0) |  |  |  |  | 437
[6 empty] | 100% | 89% | 79% | 69% | 100% | [5 empty] | 100% | 89% | 79% | 69% | 100% | 88.78%
1 | Control of Access to Site/Office | [5 empty] | 1 | 0 | 0 |  | 30 | QC of Excavation |  |  |  | 0 | 1 |  |  |  | 0.89 | 0.89 | [6 empty] | Item Count | Score | Distributtion
2 | Document Control Administration | [5 empty] | 0 | 1 |  |  | 31 | QC of Roads/Round about | [7 empty] | 1 | 0.79 | 1 | [8 empty] | Overall | Relevant
3 | Project Documents and Progress | [5 empty] | 1 |  |  |  | 32 | QC of Interlock & Curbstone | [7 empty] | 1 | 0.89 | 1 | 4 | 58 | counts |  | 4 | Excellent | 0 | 0 | 0% | 0%
4 | Contractor's Quality Plan/CM (Updated and Reviewed) | [5 empty] | 1 |  |  |  | 33 | Layers/Backfilling Sampling |  |  |  | 0 | 1 | 0 | 0 |  | 0.89 | 0.89 | 3 | 58 | counts |  | 3 | Good | 28 | 84 | 48.28% | 68.29%
5 | MS Log and Paperwork | [5 empty] | 1 |  |  |  | 34 | Pump Stations Units | [5 empty] | 1 |  | 0 | 0.89 | 0.79 | 2 | 58 | counts |  | 2 | Average | 6 | 12 | 10.34% | 14.63% | NB: Insert 1, or 0 in the required cell only.
6 | RFI, FIR, & MIR Procedure | [5 empty] | 1 |  |  |  | 35 | Quality of Form Work |  |  |  |  | 1 | 0 | 0 | 0 | 0.89 | 0.89 | 1 | 58 | counts |  | 1 | Improve | 7 | 7 | 12.07% | 17.07%
7 | RFI, FIR, & MIR Inventory system | [5 empty] | 1 |  |  |  | 36 | Design Change List | [7 empty] | 1 | 0.89 | 1 | 0 | 58 | counts |  | 0 | N/A | 17 | 0 | 29.31% | -
8 | NCRs Control & Procedure | [5 empty] | 1 |  |  |  | 37 | Quality of Concrete Placing |  |  |  |  | 1 | 0 |  | 0 | 0.89 | 0.89 | [5 empty] | Total | 58 | 103 | 100% | 100%
9 | NCR Log | [5 empty] | 1 |  |  |  | 38 | Concrete Surface Finishing | [5 empty] | 1 |  | 0 | 0.89 | 0.79
10 | MODON Standard* | [5 empty] | 1 | 0 |  |  | 39 | Pedestals/Columns/Beams Alignment |  |  |  |  | 1 |  |  | 0 | 0.89 | 0.89 | [6 empty] | Maz Score Available: | 164 | <- Excludes N/A items
11 | Project Risk Plan/Management* | [5 empty] | 1 | 0 | 0 |  | 40 | Siporex Lifting & Unloading | [7 empty] | 1 | 0.89 | 1
12 | Monthly Quality Reports* | [5 empty] | 1 | 0 |  | 0 | 41 | Siporex Quality Pre-installation | [7 empty] | 1 | 0.89 | 1
13 | ITP | [5 empty] | 1 | 0 |  |  | 42 | Siporex Finishing Quality | [7 empty] | 1 | 0.89 | 1 | [5 empty] | Total Score |  | Percentage (%)
14 | MODON Weekly Report | [5 empty] | 1 |  |  |  | 43 | Roads / Parking Markings | [7 empty] | 1 | 0.89 | 1 |  | 58 |  |  |  | 103 |  | 62.8049 |  | %
15 | Design Change Official Paperwork* | [5 empty] | 0 |  |  | 1 | 44 | QC of Finishing Outdoors | [7 empty] | 1 | 1 | 1 | [5 empty] | Max Score Available | [5 empty] | 31
16 | Design Change was Applied* | [5 empty] | 0 |  |  | 1 | 45 | Quality of Finishing Indoors | [7 empty] | 1 | 1 | 1 | [5 empty] | 164 | [5 empty] | 32
17 | Material List | [5 empty] | 0 | 1 |  |  | 46 | Stairs Quality | [7 empty] | 1 | 0.79 | 1 | [11 empty] | 33
18 | Pending Material Status | [5 empty] | 1 |  |  |  | 47 | Tanks Method Statement Work | [6 empty] | 1 | 0 | 0.89 | 0.69 | [11 empty] | 34
19 | Lifting Plan* | [5 empty] | 1 |  |  |  | 48 | Electric Rooms | [7 empty] | 1 | 0.89 | 1 | [11 empty] | 35
20 | DWG Log | [5 empty] | 1 |  |  |  | 49 | QC of MCC/ATS Plant Units | [7 empty] | 1 | 0.89 | 1 | [11 empty] | 36
21 | Invoice Status | [5 empty] | 1 |  |  | 0 | 50 | Qualified Subcontractor |  |  |  |  | 0 |  | 1 |  | 0.89 | 0.69 | [11 empty] | 37
22 | Site Handover Letter | [5 empty] | 0 |  |  | 1 | 51 | Scaffold/Ladders/Slope/Bridge Compliance | [6 empty] | 1 | 0 | 1 | 0.69 | [11 empty] | 38
23 | Material Testing Results & Certification | [5 empty] | 0 | 1 | 0 |  | 52 | Protection Applied to Completed Work |  |  |  | 0 | 0 | 1 |  |  | 0.79 | 0.79
24 | As Build Drawings Status* | [8 empty] | 1 | 53 | Storage Management in/out Control |  |  |  | 0 | 1 |  |  |  | 1 | 0.89
25 | Calibrated Lab Tools & Equipment | [5 empty] | 0 |  | 1 |  | 54 | Material Control |  |  |  |  | 1 | 0 |  |  | 0.69 | 0.89
26 | Storage Inventory System | [5 empty] | 0 |  | 1 | 0 | 55 | Manholes Storing and Quality | [7 empty] | 1 | 0.69 | 1
27 | Logistics Plan | [5 empty] | 0 |  | 1 |  | 56 | Reinforced Steel Quality |  |  |  |  | 1 |  |  | 0 | 0.69 | 0.89
28 | Project Progress Planview | [5 empty] | 1 |  |  |  | 57 | Safety Overview |  |  |  | 0 | 1 | 0 |  |  | 0.89 | 0.89
29 | Sufficient Number of QC Inspectors | [5 empty] | 0 |  | 1 |  | 58 | Waste Management Control |  |  |  | 0 | 1 | 0 |  |  | 0.69 | 0.89
0
Score
[8 empty] | *QC % |  |  | 88.78%
Prepared by: | [10 empty] | Issued to PM: |  |  | Eng. Ahmed Kotbi
*QC Observations refer only to the practices and documentation observed at time of inspection. The responsibility of the CM and Contractor is to ensure that aspects of Quality are suitably managed. *Scores are a reflection of the general site conditions based upon the findings at the time of the walk through *If Applicable

## Quality-Stat
Quality Reports
Item |  | Issued | Closed | Pending | Avg. Closing (Days) | Pending
[6 empty] | 0-10 Days | 11-20 Days | 21-30 Days | 31-60 Days | > 60 Days
Non Conforomance Report (NCR) |  | 17 | 17 | 0 | 3 | 0 | 0 | 0 | 0 | 0
Site Instruction (SI) |  | 18 | 18 | 0 | 3 | 0 | 0 | 0 | 0 | 0
Material Inspection Report (MIR) |  | 64 | 64 | 0 | 3 | 0 | 0 | 0 | 0 | 0
Field Inspection Report (FIR) |  | 407 | 407 | 0 | 3 | 0 | 0 | 0 | 0 | 0
Shop Drawings
Item Per WBS |  |  | Total Planned | Total Drawings Submitted |  |  |  |  | Remaining Drawings | Pending | Total Submittals
|  |  |  | A | B | C | D | Approved | with Designer | Submittals With Consultant
Structural |  |  | 19 | 19 | 0 | 0 |  | 19 | 0 | 0 | 19
Architectural |  |  | 15 | 15 | 0 | 0 |  | 15 | 0 | 0 | 15
Mechanical, Electrical , & External Infra |  |  | 47 | 47 | 0 | 0 |  | 47 | 0 | 0 | 47
Road |  |  | 12 | 12 | 0 | 0 |  | 12 | 0 | 0 | 12
TOTAL |  |  | 93 | 93 | 0 | 0 | 0 | 93 | 0 | 0 | 93
Material Approval
Item Per WBS |  |  | Total Planned | Total Materials Submitted |  |  |  |  | Remaining to approve | Pending | Total Submittals
|  |  |  | A | B | C | D | Approved | with Designer | Submittals With Consultant
Earthworks |  |  | 8 | 8 | 0 |  |  | 8 | 0 | 0 | 8
Structural |  |  | 14 | 14 | 0 |  |  | 14 | 0 | 0 | 14
Architectural |  |  | 23 | 23 | 0 |  |  | 23 | 0 | 0 | 23
Mechanical |  |  | 28 | 28 | 0 |  |  | 28 | 0 | 0 | 28
Electrical |  |  | 22 | 22 | 0 |  |  | 22 | 0 | 0 | 22
TOTAL |  |  | 95 | 95 | 0 | 0 | 0 | 95 | 0 | 0 | 95
Procurement Summary
Item Per WBS |  |  | Total Materials Planned | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Actual Material on Site | Remaining Materials | Material Delivery Completion (Date)
|  |  |  | A | B | C | D | Processed
Earthworks |  |  | 8 | 8 | 8 | 0 | 8 | 0 | 2026-09-05
Structural |  |  | 14 | 14 | 14 | 0 | 14 | 0 | 2026-07-25
Architectural |  |  | 23 | 23 | 23 | 0 | 23 | 0 | 2026-09-05
Mechanical |  |  | 28 | 28 | 28 | 0 | 28 | 0 | 2026-09-09
Electrical |  |  | 22 | 22 | 22 | 0 | 22 | 0 | 2026-07-30
TOTAL |  |  | 95 | 95 | 95 | 0 | 95 | 0 | 2026-09-09
Consultant Quality Inspections / Observations (Weekly Basis) | [7 empty] | Overall Average | 88.78% |  | Average Closing | 1
Week Number | Date of Audit | Date Issued | Numbers Of Comments | Quality Score | Date Closed | Closure Duration |  | This Week Score | 88.78% |  | Average Number of Comments Per Audit | 0
Week-1 | 2026-04-06 | 2026-04-06 | 0 | 88.78% | 2026-04-07 | 1
Week-2 | 2026-04-13 | 2026-04-13 | 0 | 88.78% | 2026-04-14 | 1
Week-3 | 2026-04-20 | 2026-04-20 | 0 | 88.78% | 2026-04-21 | 1
Week-4 | 2026-04-27 | 2026-04-27 | 0 | 88.78% | 2026-04-28 | 1
Week-5 | 2026-05-04 | 2026-05-04 | 0 | 88.78% | 2026-05-05 | 1
Week-6 | 2026-05-11 | 2026-05-11 | 0 | 88.78% | 2026-05-12 | 1
Week-7 | 2026-05-18 | 2026-05-18 | 0 | 88.78% | 2026-05-19 | 1
Week-8 | 2026-05-24 | 2026-05-24 | 0 | 88.78% | 2026-05-25 | 1
Week-9 | 2026-06-01 | 2026-06-01 | 0 | 88.78% | 2026-06-02 | 1
Week-10 | 2026-06-08 | 2026-06-08 | 0 | 88.78% | 2026-06-09 | 1
Week-11 | 2026-06-15 | 2026-06-15 | 0 | 88.78% | 2026-06-16 | 1
Week-12 | 2026-06-22 | 2026-06-22 | 0 | 88.78% | 2026-06-23 | 1
Week-13 | 2026-06-29 | 2026-06-29 | 0 | 88.78% | 2026-06-30 | 1
Week-14 | 2026-07-06 | 2026-07-06 | 0 | 88.78% | 2026-07-07 | 1
Week-15 | 2026-07-13 | 2026-07-13 | 0 | 88.78% | 2026-07-14 | 1
Week-16 | 2026-07-20 | 2026-07-20 | 0 | 88.78% | 2026-07-21 | 1
Week-17 | 2026-07-27 | 2026-07-27 | 0 | 88.78% | 2026-07-28 | 1
Week-18 | 2026-08-03 | 2026-08-03 | 0 | 88.78% | 2026-08-04 | 1
Week-19 | 2026-08-10 | 2026-08-10 | 0 | 88.78% | 2026-08-11 | 1
Week-20 | 2026-08-17 | 2026-08-17 | 0 | 88.78% | 2026-08-18 | 1
Week-21 | 2026-08-24 | 2026-08-24 | 0 | 88.78% | 2026-08-25 | 1
Week-22 | 2026-08-31 | 2026-08-31 | 0 | 88.78% | 2026-09-01 | 1
Week-23 | 2026-09-07 | 2026-09-07 | 0 | 88.78% | 2026-09-08 | 1
Week-24 | 2026-09-14 | 2026-09-14 | 0 | 88.78% | 2026-09-15 | 1
Week-25 | 2026-09-21 | 2026-09-21 | 0 | 88.78% | 2026-09-22 | 1
Week-26 | 2026-09-28 | 2026-09-28 | 0 | 88.78% | 2026-09-29 | 1
Week-27 | 2026-10-05 | 2026-10-05 | 0 | 88.78% | 2026-10-06 | 1
Week-28
Week-29
Week-30
Week-31
Week-32
Week-33
Week-34
Week-35
Week-36
Week-37
Week-38
Week-39
Week-40
Week-41
Week-42
Week-43
Week-44
Week-45
Week-46
Week-47
Week-48
Week-49
Week-50
Week-51
Week-52
Week-53
Week-54
Week-55
Week-56
Week-57
Week-58
Week-59
Week-60
Week-61
Week-62
Week-63
Week-64
Week-65
Week-66
Week-67
Week-68
Week-69
Week-70
Week-71
Week-72
Week-73
Week-74
Week-75
Formulas:
Remaining Drawings = MAX(J35:[Remaining Drawings, row above])
Avg. Closing (Days) = [Issued]+1

## HSE
MODON HSE Site Inspection Report
Date |  |  | 2026-10-05 |  |  |  |  | Inspected By:
Project ID. |  |  | NJR1-05-005 |  |  |  |  | Report No. | 28 |  |  |  |  | MODON PM Name |  | Eng. Ahmed Kotbi
Project Name: |  |  | Construction of Industrial Units for Artisans in Najran |  |  |  |  | Contractor: |  | Labenat Al Bena |  |  |  |  | Safety Performance |  | 2 |  |  | 83%
Inspections are a snapshot in time and refer only to the practices and documentation observed at the time of the Inspection. It remains the responsibility of the Consultant and Contractor to ensure that all aspects of Health & Safety are suitably managed.
1 |  | Good Practice |  |  | 2 | Need Improvement | [5 empty] | 3 | Fail (Life Threatening Activity) / Comliance with Plan & Procedures |  | N/A | Atcitty Not Applicable for this Site Inspection Report
No. | Topic | [5 empty] | Wt. | HSE Compliance |  |  | No. | Topic | [5 empty] | Wt. | HSE Compliance
1 | Access and Egress - (General access to site, segregated from vehicles, / Overhead protection, while entering into the building /Adequate lighting provided when dark or overnight work) | [5 empty] | 5% | 1 |  |  | 14 | Work at Height - (PPE/Fall Protection(Same level, above and blow) / Training / Fall restraint / competency /Safe access & egress to and from work at height / Ladders / Openings (floor/shafts/Provision of emergency rescue) | [5 empty] | 5% | 2 |  |  |  | 1 | 100 | 1
2 | Traffic Management - (Loading/unloading/sheeting/temp. routes/speed/parking/competence) | [5 empty] | 3% | 1 |  |  | 15 | Scaffolding - (Temp. Scaffolding Work-platform (All types) - qualified scaffolder / Inspection / Tagged / Safe Access/egress / PTW/Falsework & Formwork) | [5 empty] | 4% | N/A |  |  |  | 2 | 75 | 2
3 | Site Signage - (Project Notice Board & General Signage) | [5 empty] | 2% | 1 |  |  | 16 | Mobile Elevated Work platform (MEWP) - (PTW/competence requirements/conditions/inspections/tagged/training/Full-body harness) | [5 empty] | 4% | N/A |  |  |  | 3 | 0 | 3
4 | PPE Compliance - (Use, storage, stock, handling & checks - Head, Foot, Eye, Hearing) | [5 empty] | 5% | 2 |  |  | 17 | Excavation & Trenches - (PTW/Edge protection/buffer zone/Slope/Benching/Shoring/Geo-tech report/Atmospheric hazards/Acess&egress/Emergency management / MS&RA/H.E) | [5 empty] | 3% | 2 | [5 empty] | N/A
5 | Housekeeping - (Material correctly stored/Rubbish cleaned & removed daily/slips & trips hazards) | [5 empty] | 3% | 2 |  |  | 18 | Confined Space - (PTW/Training/competence/Emergency Management/MS & RA/Safe access/egress) | [5 empty] | 5% | 2
6 | Storage of Materials - (Transporting, storage, training and use - Combustible / Flammable / Hazardous substances (COSHH) | [6 empty] | 2 |  |  | 19 | Fire Protection - (Flammable/Oxy. LPG /Combustible separated/FE's/Flashback arrestor/Sparks & slags/Smoking area/PTW/Generators/MS & RA/Emergency Management) | [6 empty] | 1 |  | Red | Serious injury or death (immediately)
7 | Site Waste Management - (Hazardous waste /Combustible waste / Human waste / Construction waste - asphalt, cable, timber, paving roof sheeting tiles, plastic & bricks) | [6 empty] | 2 |  |  | 20 | Health & Welfare - (Adequate drinking water/shaded - eating & rest area/washing & sanitary facilities/Certified FA/FA Box & Stock/adequate toilets/Ambulance) | [6 empty] | 2 |  | Yellow | Minor or near miss (3 days to comply)
8 | Health Surveillance - (Expose to excessive noise/vibration/dust/silica/CO/cement/radiation/extreme weather condition) | [5 empty] | 3% | 1 |  |  | 21 | Environmental Incident Measures - (Spill/ Leakage / Concrete wash / vehicle & eqpts. wash / waste disposal/Sewers and drains/emissions/Emergency Management/Training/site run-off water) | [5 empty] | 5% | 1 |  | Green | No issues
9 | Electrical Safety - (Electrical qualified /RCD/GFCI/Industrial Cocket/LOTO/Cable-overhung or buried/Cords in good condition/current inspection tag) | [5 empty] | 5% | 2 |  |  | 22 | HSE Communications & Meetings - (Schedule HSE Meetings/Safety Committee meetings/Alerts / Lesson learned/Safety Bulletin contains latest HSE KPI) | [5 empty] | 5% | 2
10 | Tools & Equipment - (Includes, powered, hydraulic & pneumatic/Guards in place/Properly stored/RCD Protection/Earthed/Good condition & tagged) | [5 empty] | 3% | 2 |  |  | 23 | HSE Plan & Associated Procedures - (Approved updated HSE Plan/ CEMP/HAZComm/Procedures/Standards/Project Safety Risk Register) | [5 empty] | 3% | 2 |  | 26 points > 4 minors then is it’s a serious issue
11 | Manual Handling - (Lifting/loading/pulling/pushing/twisting/awkward posture/repetitive task/frequent and prolong physical effort/Reasonable practicable use of mechanical aid) | [5 empty] | 3% | 2 |  |  | 24 | Health, Safety & Environment Incident reporting - (Review of HSE Statistics, Reporting of Unsafe Act & Conditions/ Reporting of Near Miss incident/Reporting of FA cases/Record MT cases) | [5 empty] | 3% | 2
12 | Vehicle and mobile equipment / Plant - (dumpers; excavators, cranes, piling rigs, grader, roller, loaders/condition/KSA License/certification) | [5 empty] | 5% | 2 |  |  | 25 | HSE Awareness, Training & Competence - (Policy /Objective & targets/Information, training/Climatic condition awareness/Reponses in emergency situation/ Safety Behavior Observation) | [5 empty] | 4% | 1
13 | Lifting Operations & Rigging - (Lifting Plan/Lifting devices & gears/PTW/Condition/3rd party certification/bank-man/rigger/slingers/man-basket/inspection record/tagged) | [6 empty] | N/A |  |  | 26 | Project Leadership Site Tours - (Provide evidence of proactive safety performance/Deficient discovered discussed/Positive feedback/Workers resolving safety issues) | [6 empty] | 1
Prepared by: |  |  |  | 0 | [6 empty] | Sent to MODON PM: |  |  |  | Eng. Ahmed Kotbi
Safety Results
1 |  | 8 |  |  |  | 2 |  | 15 |  |  |  |  | 3 | 0
Note on C13: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Safe access / egress for people to their work area 2 - Safe access / egress for construction vehicles 3 - Access properly restricted-site fencing provided and maintained 4 - Access proper and not blocked 5 - Safe access is available for rescue operation 6 - Storage access / exit are clearly marked and unobstructed 8 - Access and egress is in good condition, hand holds, ladder etc. are sound and in place 9 - Ensure unauthorized public access is prevented 11 - Site assembled ladders or make-shift tables for access are forbidden on site. 13 - Use proper bridges, walkways or gangways to access or cross trenches or an excavation area 14 - Surrounding areas are cleared and barricaded and access restricted to all unauthorized trades while crane in operation 15 - To ensure early access to accredited medical / rehabilitation services 16 - Parking vehicles on site access roads causing obstruction 17 - All personnel will be instructed that access to firefighting equipment must remain clear at all times 18 - Access control gates to be locked out of hours 19 - Site access gates to be designed and located to, where possible, avoid clashes with external hazards / activities
Note on T13: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Personal Fall Arrest System; 1 - Is the suitable harness harnesses is provided 2 - Are shock absorbing lanyard with 2 locking snap hooks. 3 - Is anchorage point strong enough and can support 5,000 Ibs. 4 - Do inspection checklist is being implemented before use. 5 - Is the emergency plan for rescue in place Personal Fall Restraint System; 1 - The fall restraint equipment should be set and adjusted so there is no free fall over the edge. 2 - A harness or body belt may be used 3 - The anchorage point must support 4 times the intended load. Positioning System; 1 - Is a suitable harness or body belt provided 2 - Is there a not more than 2' free fall maintained 3 - Is the anchorage point capable of supporting 2 times the intended load or 3.000 Ibs, whichever is greater 4 - Is 100% tie-off (protection from falls at all times, even when moving from point to point) provided while using personal fall protection with two lanyards Fall Protection System; 1 - Suitable edge protection and work platforms are to be provided to prevent a fall occurring 2 - Where the provision of edge protection or adequate platforms cannot be provided safety nets or other soft-landing systems such as inflatable bags are to be used to minimize the consequences of a fall. 3 - If nets are used, they must be installed by a competent rigger and fitted as close under the work surface as possible. 4 - Areas below roof works are to be cordoned off and properly signed to prevent personnel being injured from falling materials 5 - If access onto the roof cannot be avoided, edge protection is to be installed 6 - Floor and wall openings are to be protected using covers of adequate strength to withstand the expected load that will be imposed and securely fixed. 7 - Penetrations in walls such as those provided for lift shafts, door openings, etc. are to be closed with suitable strength material or have fixed protective barriers around the penetration with a sign warning personnel of the danger of falling.
Note on C14: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are arrival and departure of vehicles and delivery accompany by security department? 2 - Are proper loading, unloading and securing loads, being properly controlled? 3 - Is the proper sheeting & coupling in place when transporting and disposing material to and from site? 4 - Is the parking to the designated parking lot and in reverse order? 5 - Is the designated speed limit adhered on workplace? 6 - Provision of ramps, traffic signs, cones, barriers, demarcation posts and tape, flashing lights and any other traffic control devices. 7 - Do visiting drivers are being inducted at the workplace, prior to enter on the workplace? 8 - Are visiting drivers restricted to dangerous areas, e.g. moving to and from they vehicles to washrooms, lavatory & offices etc.? 9 - Do drivers observe site rules and procedures, for delivery, loading and unloading? 10 - Are the areas wide enough for the safe movement of large vehicles (including visiting vehicles)? 11 - Does drivers are competent, hold valid local driving license and competent training? 12 - Ensure the vehicle and trailers have their brakes applied and all stabilizers properly positioned before beginning loading or unloading?
Note on T14: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Base soundness, load adequately spread (base plate jacks, base plate on firm ground). 2 - Line of standard (vertical) and ledger (horizontal) secure and plumb. 3 - Spacing of transoms on platforms, support for Scaff boards, boards are not over protruded and boards are secured. 4 - Staggering of joints vertical and horizontal. 5 - Guardrail / fall protection. (Top rail – Min.1mtr, Mid rail – 470mm from floor and Toe boards – Minimum150mm) 6 - Longitude and bracing on standards and ledgers. 7 - If close to structure, ties must be on lift below to top working platform and every 3m, load bearing couplers used or tie with certified anchor bolts (eye bolts). 8 - Clamps and tubes used are of correct fittings, size and free from defects. 9 - Tubes & fittings free from defects / deformation. 10 - Safe and proper access available to the working platform. 11 - Scaff tags signed, displayed and up to date. 12 - If close to slab edge/opening scaffold tied and secured to structure correctly.
Note on C15: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a Project Notice Board - (showing HSE Statistics / Safety alerts / lesson learned)? 2 - Is there prominent safety boards that are depicting the mandatory PPE on the workplace? 3 - Are other safety required signs are prominently installed on the workplace in relevant to their work-task, as following: > Hazardous Substances - e.g. respiratory protection Sign > Working at Height - e.g. Full body Harness Sign > Working UG - e.g. Full body Harness, SCBA, Ventilation, PTW Signage etc. > Working with Electrical - e.g. Leather Gloves, Goggles, Face shield, Electric shock proof helmet & shoes > Working with Chemicals - Signage = e.g. Impermeable gloves/clothing's, long sleeves, Goggles 4 - General Site Safety Signs: > Prohibition Sign = (e.g., ‘no access for unauthorized persons’). > Warning Signs = (e.g., ‘danger: electricity’) > Mandatory Signs = e.g., ‘eye protection must be worn’) > Emergency Escape or First Aid Sign = e.g., ‘emergency exit/escape route’) > Safety Color Signs = (e.g., yellow means ‘be careful’ or ‘take precautions’) > Illuminated Signs = (e.g., many emergency exit signs) > Acoustic Signals =( e.g., fire alarm) > Fire safety sign > Supplementary Signs = "This way"
Note on T15: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Man-Lift operators are to be competent and trained to operate the specific Man-Lift by examination and hold a current approved certificate / license from an approved and internationally recognized source (TUV, SGS etc. 1 - All Man-Lifts shall be inspected by a 3rd party on an annual basis. 2 - All Man-Lifts shall display a sticker corresponding to the 3rd party inspection certificate. 3 - The manufacturer's instruction manual must be on site for each and every type of Man-Lift in use. 4- A pre-start daily operator inspection of the equipment will be performed and documented on a daily basis as per the manufacturer's instructions. The user is responsible for ensuring this has occurred. 5 - The use of a Man-Lift as, or in lieu of, a Crane is strictly prohibited. Man-Lifts are to be used only for lifting personnel and small tools within the designed Safe Working Load. 6 - The platform is not to be loaded in excess of the designed working load; the safe working load of the platform is to be clearly displayed on both the platform, and body of the equipment. 7 - All persons inside work platforms shall wear a full-body harness attached to the designated anchor point. Personnel must stand on the floor of the working platform; standing on the handrails is strictly prohibited. Harnesses must not be attached to other structures outside of the working platform. 8 - Personnel must stay inside the working platform at all times; the platform must not be used as an access to structures. The use of staging or ladders to extend height is strictly forbidden. 9 - Securing the boom or work platform to any structure is strictly prohibited. The boom or working platform must not be rested upon on any structure, nor is the Man-Lift to be used as a jack/ prop or tie to support other structures. 10 - All Man-Lifts must be equipped with a 5kg (10lb) fire extinguisher. 11 - No man-lifts are to be operated that have had safety devices removed or disabled. Daily operator inspections are to include the testing of these devices (limit switches, alarms and hazard flashing beacons). 12 - Specific Man-Lifts are fitted with outriggers and/or stabilizers which must be used as per manufacturer's instructions. 13 - The work area surrounding the man-lift is to be cordoned off using barricades and signage if the area is used by other workers or vehicles. A full traffic management plan is required for all works involving man-lifts when working on highways. Under no circumstances is any part of a man-lift to extend or swing into a line of traffic.
Note on C16: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Does required mandatory PPE (refer specification BS, EN & ANSI) is provided, as following? > Safety helmet (see below for color scheme) > Safety glasses (shaded for outdoor work and clear inside structures and during non-daylight hours) > Safety boots (safety shoes are prohibited) > Orange hi-visibility vest 2 - Additional PPE shall be provided to a specific task 3 - Do specific PPE is provided according to their job requirement? > To work at height - Full Body harness / Fall arrest Devices / Fall Restraint Devices / V & H Lifeline etc. > To work in the confined space - Full Bodyarness, Tripod with retractable lifeline, SCBA, Masks etc. > 4 - Are the PPE stored appropriately to prevent deformation or distortion? 5 - Has self assessment being carried out for in according to the work requirements? 6 - EYEWEAR (Glasses/Goggles/Face Shields) > Eyewear cleaning supplies available. > Safety glasses in good condition and lenses free of scratches. > Goggles adjustment strap not cracked or frayed, not deformed, or lenses not > Face shields in good condition, including adjustment band, and free of scratches or 7 - HEAD PROTECTION > Hard hat bill and suspension attached as allowed by manufacturer. > is pliable, free of dents, cracks, nicks, or any damage due to impact. > Suspension maintained at 1.25 inches from inside of shell. > Suspension free of cuts or fraying, torn headband, adjustment strap workable. > Electrical hard hat matched to hazard classification. > Dated to determine whether within manufacturer’s allowable 5-year use time period. 8 - HAND PROTECTION > Available in sizes matched to employee. > Gloves free of rips tears, abrasions, or holes. > Matched to manufacturer’s specification for chemicals used onsite. > Electrical gloves matched to hazard and periodically inspected for insulating rating. > Maintained in a clean and sanitary condition, decontaminated or disposed properly. 9 - BODY PROTECTION > Available in sizes matched to employee. > Maintained in a clean and sanitary condition, decontaminated or disposed properly. > Vapor-tight fully encapsulated suits tested at required periodic intervals. > Flame-resistant clothing matched to electrical hazard and arc flash rating. > Welding gear matched to degree of hazard and free of cuts, tears or burn holes. > Flotation gear available for work near or on water and in good condition. 10 - HOT AND COLD BODY PROTECTION > Cooling gear available based on degree of heat stress hazard. > Cooling gear in operable, clean, and sanitary condition. > Cold-weather gear provided based on needs assessment. > Cold-weather gear available in sizes to match employees. > Cold-weather gear is in free of tears, rips, or holes and in maintained in a clean condition. 11 - TRAINING > Initial PPE training completed by employees. > Training conducted when new types or styles of PPE are issued. > PPE selection, use, and maintenance reviewed at daily safety briefings. 12 - Provision of impermeable clothing appropriate for the work being performed? 13 - Wearing of shorts, sleeveless shirts, loose clothing are prohibited across the MODON Projects. 14 - Clothing contaminated with grease, oils, fuels and other hazardous substances is not to be worn.
Note on T16: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a valid Excavation PTW in place? 2 - Are spoils, materials, and equipment set back at least 1.5 meters from the edge of the excavation? 3 - Are walkways and bridges over excavations structurally sound, minimum 0.5 meter in width and equipped with standard guard rails and toe boards? 4 - Are warning systems established and used when mobile equipment is operating near the edge of an excavation? 5 - Are employees prohibited from working on the faces of sloped or benched excavations above other employees? 6 - Are the exact locations of Utilities (piping, electrical, etc.) clearly marked? 7 - Are underground installations protected, supported, or removed when an excavation is open? 8 - Are ladders or other means of access and egress in place as per the PTW requirements? 9 - Are all workers within 7.6 meters of a means of access and egress to a trench? 10 - Are ALL ramps constructed of materials of uniform thickness, cleated together, equipped with no-slip surfaces? 11 - Are employees protected from cave-ins when entering or exiting excavation? 12 - Are precautions taken to protect employees from water accumulation and dewatering is being carried out? 13 - Is surface water or runoff diverted after every rainstorm or other hazard-increasing occurrence? 14 - Is the excavation classified as a confined space? If so, is their a valid confined space PTW and is the atmosphere being tested when there is a reasonable possibility of an oxygen-deficient, oxygen-enriched, combustible, toxic, or other harmful contaminant? 15 - Have materials and/or equipment chosen for shoring been based upon soils analysis, trench depth and expected loads (as per Excavation PTW)? 16 - Are shoring materials and equipment that are used for protective systems inspected and in good condition? 17 - Are damaged shoring materials and equipment immediately removed from service? 18 - Are damaged shoring materials and equipment inspected by a Registered Professional Engineer after repairs are made and before being placed back in service? 19 - Are protective systems installed without exposing employees to hazards of cave-ins, collapses, or threat of being struck by materials or equipment? 20 - Are ALL members of support systems securely fastened together to prevent failure? 21 - Are support systems provided to insure stability of adjacent structures, buildings, roadways, sidewalks, etc.? 22 - Are excavations below the level of the base or footing supported, and approved by a Registered Professional Engineer? 23 - Does back-filling progress with the removal of the support system? 24 - Is a shield system installed to prevent lateral movement? 25 - Are employees prohibited from remaining in a shield system during vertical movement?
Note on C17: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Sites are to be kept clean and tidy and free from slip, trip and fall hazards. 2 - Do all personnel trained in the importance of good housekeeping, managers, supervisors undertake regular monitoring and inspection of the workplace? 3 - Workplace are to be left clean and tidy at the end of each shift and where there is an accumulation of materials throughout the shift, at regular intervals as required to maintain a clean and safe site. 4 - Buildings under construction and nearing completion must ensure that all combustible and flammable materials are removed at the end of each shift. 5 - Nails are to be removed from timber as soon as possible, where this is not practical they are to be flattened and placed in a safe area (barrier and signs) until nails can be removed at a later time. 6 - Materials are to be stored so as they do not pose a risk to personnel stacking, removing or walking by (further guidance is given in the materials storage and handling section). 7 - All spills are to be cleaned up immediately using absorbent material. 8 - Cables/hoses/other trailing leads are to be protected, buried or secured above head height to avoid a slip trip, fall hazard. 9 - Waste is to be placed in designated containers and covered to protect against high winds, pests or risk of fire. Waste containers are to be emptied on a regular basis to prevent a build-up of material. 10 - Loose or light materials that are stored on roofs or open spaces are to be secured to prevent them from inclement weather. Location: 1 - Receptacles located inside buildings shall be kept at least 18 inches away from combustible walls and partitions. 2 - Receptacles for combustible trash that are located outside of buildings shall be placed at least 15 feet from the building or combustible material. Use: 1 - Cigarettes, cigar butts, matches, and similar potential ignition sources should never be placed in a trash receptacle. Proper receptacles for such items should be provided in areas designated for smoking. 2 - Broken glass, empty jars, scrap metal, and similar construction material should never be placed in office trash containers. A roll-off bin or other appropriate container should be used to hold construction debris. Environmental: 1 - Container storage areas shall be kept clean and free of trash. Improper disposal of food waste can attract pests and vermin. Prevention methods that do not involve the use of toxic chemicals is the preferred method of pest control. 2 - Outdoor containers should be kept covered when not in use so as to avoid attracting pests and to prevent the entry of water. Dripping or leaking trash containers may violate local storm water quality discharge regulations. 3 - Promote recycling by contracting with a waste removal company that provides reuse as part of the waste processing or by providing segregated bins for the collection of office paper, aluminum cans, plastic bottles, and toner cartridges. Rinse empty cans and bottles of sugar-based soda so as not to attract ants and other pests. 4 - Proper lighting (indoor) or during Night Shift are provided. Accurately installed. No impairement or poor visibilty is generated. No shadow due to installation of lights are presents.
Note on T17: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Permit is taken for confined space entry and all recommended precautions are in place. 2 - Operatives are trained and fit for the specified job. 3 - Confined space is well ventilated by means of mechanical ventilation. (Exhaust fan, blowers, low velocity air hose etc.). 4 - Rescue system (Tripod with hoisting device, Rescue Harness etc.) in place and sufficient trained persons are available for the rescue operation. 5 - Safe access is available for rescue operation. (Manhole size - Min. 450 mm X 407 mm or 457 mm Dia.) 6 - Atmospheric monitoring conducted and confined space is safe to enter. Percentage of gas concentration will be monitored and recorded every 4 hrs. A. Oxygen percentage. (Permissible limit – 19.5% to 23.5%) B. Flammable gas or vapors.(Permissible limit - <10% of LFL) C. Carbon Monoxide. (Permissible limit - <50ppm) D. Hydrogen sulfide.(Permissible limit - <10ppm) E. Any other toxic gas or vapors. _______________________________ 7 - Minimum two persons shall be assigned to work in the confined space. One person will remain in the entrance at all times to monitor the work 8 - All persons shall wear safety harness, which should be connected to safety line from outside at all times. 9 - All electrical equipment & leads are free from damage and guards in place. 10 - All electrical tools & equipment are connected through ELCB. 11 - Compressed gas cylinders are kept outside the confined space. 12 - supervisor / Foreman will be available at all time to monitor the work and for the rescue operation. 13 - Tool box talk conducted for the entire team and they are well aware of the risks. 14 - Proper communication system is available in between persons inside and standby person. 15 - Trained First aider with first aid kit will be available when working in the confined space. 16 - Confined space entry register is available and shift records will be maintained. -
Note on C18: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Combustible: 1 - Ensure oily rags, combustible material and other flammable substances which may ignite are not accumulated and that they are removed without delay to the designated disposal / storage area. 2 - Combustible materials shall not be stored within 20 feet (6.1 meters) of compressed gas cylinders. 3 - Safety cans used for dispensing combustible liquids shall be kept at a point of use 4 - Storage rooms for combustible liquids must have explosion-proof light fixtures 5 - No flames - hot work or smoking is be permitted in combustible liquid storage areas. Flammable: 1 - Adequate training in the use and storage of flammable liquids is in place. 2 - Storage of Flammable liquids in accordance with NFPA approved flammable storage lockers or in low value structures at least 50 feet from any other structure. 3 - Do not store other combustible materials near flammable storage areas 4 - Bulk drums of flammable liquids must be grounded and bonded to containers during dispensing 5 - Portable containers of gasoline or diesel are not to exceed 5 gallons 6 - Safety cans used for dispensing flammable liquids shall be kept at a point of use 7 - Appropriate fire extinguishers are to be mounted within 75 feet of outside areas containing flammable liquids, and within 10 feet of any inside storage area for such materials. 8 - Storage rooms for flammable liquids must have explosion-proof light fixtures 9 - No flames - hot work or smoking is be permitted in flammable or combustible liquid storage areas. 10 - Flammable liquid transfer areas are to be separated from other operations by distance or by construction having proper fire resistance. 11 - When not in use flammable liquids shall be kept in covered containers. 12 - Flammable materials are considered hazardous and as such, material safety data sheets and appropriate hazard communication training for affected employees is required 13 - Maintain high levels of housekeeping, particularly with relations to flammable materials. 14 - Where flammable materials are handled in the course of work, safe work procedures must be prepared and documented with reference made to the Material Safety Data Sheets (MSDS‘s) for the materials concerned. 15 - All people handling, working with or in control of flammable substances must be properly trained and supervised (documentation to be maintained). 16 - Lead, dust, fumes and vapor constitute a major health hazard to workers. Hazardous Substances COSHH 1 - Under COSHH the risk presented by any hazardous substance assessed using hierarchy of control, stored, transported, created or disposed and usage at the workplace; > Very toxic or toxic: Substances that, in low quantities, cause death or acute or chronic damage to health when inhaled, swallowed or absorbed via the skin > Harmful: Substances that may cause death or acute or chronic damage to health when inhaled, swallowed or absorbed via the skin > Corrosive: Substances that may, on contact with living tissues, destroy them > inhalation into the lungs, when the substance is in the form of a gas, vapor, fume, mist, aerosol or dust > absorption through the skin or eyes by contact with a substance that can penetrate unbroken skin, or is absorbed through unprotected cuts or grazes > injection by contact with contaminated sharp objects or high-pressure equipment, e.g. water jetting > ingestion by swallowing particles of a hazardous substance resulting from hand-to- mouth transfer
Note on T18: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are regular and frequent fire safety inspections carried out? 2 - Have a sufficient number of fire marshals/evacuation officers been appointed? 3 - Are water supplies adequate? 4 - Does the building or site have a written fire procedure? 5 - Is there an effective permit to work system in operation for all hot work and other fire related work? 6 - Do all doors from areas from which a large number of people may have to escape open in the direction of travel? 7 - Do all emergency exit doors (i.e. doors not in normal use) have clear instructions displayed on how to open? 8 - Are all escape routes clear and unobstructed? 9 - Are all fire exit doors correctly signed? 10 - Is all fire fighting equipment immediately visible or correctly signed? 11 - Are all flammable and explosive substances adequately signed to indicate their presence and danger? 12 - Where necessary, is there a sufficient number of emergency lights to adequately illuminate all internal escape routes, exit doors and signs? 13 - Where automatic fire detection is deemed to be necessary is there an adequate number of detectors in the critical areas? 14 - Where the means of raising the alarm is by hand-operated devices, can the operation of one device be heard throughout the entire building or site? 15 - Is there an adequate number of fire extinguishers in the building? 16 - Is there firefighting equipment other than extinguishers in the building? 17 - Are all electrical circuits and fixed electrical installations examined and tested at an acceptable frequency? 18 - Is housekeeping to an acceptable standard? 19 - Have all staff been trained in fire procedures in the last twelve months? 20 - Are all fire drills adequately recorded?
Note on C19: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - General construction waste streams generated including; > Asphalt, cable, timber, paving, roof sheeting, tiles, plastic sheeting and brickwork. > Excess concrete, spoil material from excavations. > General waste, such as putrescible food scraps and packaging from workers. > General (food) waste, construction/concrete waste, hazardous waste, paper/cardboard and waste water/sewage. 2 - Are hazardous waste identified with hazardous Waste label. 3 - Containers are properly labeled in according to their contents. 4 - Container inspections are documented in writing using the Container Inspection Checklist. 5 - Weekly inspections logged into book using the Accumulation Area Inspection Log Sheet. “NO SMOKING OR OPEN FLAME” sign posted. 6 Disposal facilities identified, evaluated using the procedures. 7 - Disposal facility accepted waste and issue approval letter. 8 - Waste transfer/dispose tracked using Waste Tracking Form. 9 - Waste streams, such as asphalt and concrete, to be recycled should be segregated and separately stored. 10 - Spill Release Contingency: 1 - Prior to beginning operations, ensure that on-site spill response capabilities (containment and personal protective equipment) are consistent with task requirements described in job hazard analysis.
Note on T19: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: HHE is required at all locations where chemical hazards exist, such as; storing, transferring and handling facilities, under routine conditions. The HHE scope shall include the physical, chemical, radiological, and biological health hazards. Physical health hazards include elevated noise and vibration exposures, repetitive motion work operations, ionizing and non-ionizing radiation exposures heat and cold stress and biological hazards include infectious disease agents. HHE shall be performed before the site mobilization; 1 - Is the adequate eating or mess area is provided and sufficient for number of workers? 2 - Are sufficient tables and Chair are provide and Kept Clean? 3 - Are FEs, signs, pest control being implemented? 4 - Is washing Area sufficient and Kept Clean? 5- Cooking Area Kept Clean? 6 - L.P.G. Cylinder stored outside, secured & upright 7 - Sufficient drinking water provided. Filters changed (as per manufacturer recommendation)? 8 - Sufficient toilets, washbasins, cleaned/disinfectant provided? 9 - Provision of First Aider 10 - Provision of Nurse 11 - Provision of First Aid Kit 12 - Provision of site clinic with required first aid equipment and items. 13 - Provision of shaded area on the workplace 14 - Provision of Ambulance or an equal arrangement in place" 15 - Smoking area is Prohibited other than designated smoking areas, clear of flammable and combustible materials? 16 - All toilets, washing, rest and eating facilities to be kept clean, hygienic and be well maintained at all times? 17 - Waste Management - Covered bins, emptied daily, close proximity, color coded etc.? 18 - Are the monitoring, including integrated air sampling, noise dosimetry and other exposure assessments, being carried out? 19 - Are the Physical, chemical, and biological stresses, being identified, results are taken with action level to prevent sickness, impaired health, significant discomfort, or inefficiency in workers? 20 - Are WEL, LEL, OEL PEL & TLV linked to control workers airborne exposure to a chemical in a concentration above which is likely to cause death or immediate or delayed permanent adverse health effects or prevent escape from such an environment, if bening implemented?
Note on C20: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Is the hierarchy of Control is beng carried out on the following and recorded; 1 - Exposure to Chemical; e.g. - Dust, Gas, Mist, Vapor 2 - Exposure to Radiation; e.g. - Pipe radiography etc. 3 - Exposure to Biological Hazard; e.g. - Bloodborne pathogens / Legionella / Leptospirosis 4 - Exposure to noise; e.g. Loss of hearing / Physical damage to hearing mechanism 5 - Heat and cold stress work; e.g. - Heat-stroke, Heat stress / Frostbite / 6 - Repetitive Motion Work; e.g. - Musculoskeletal disorder, awkward position etc. 7 - Is the risk assessment carried out on the hazardous material and covering the following; > Allowable exposure limits, > Exposure monitoring requirements, > Methods of compliance for potential over exposure conditions, > Medical surveillance program, > Hazard communication, employee training requirements, 8- Is the IH Surveillance Plan should being implemented and have rocored on the following; > Which exposure groups require IH monitoring and medical surveillance > Specific substances or agents to be monitored, > The OELs to be used to evaluate results > The statistical basis to continue or cease monitoring > Specific medical testing/protocol to be implemented 9 - Do we've program on identifies work conditions such as the following, the exposure must first be mitigated or work shall not be performed. > Oxygen concentrations less than 19.5% or greater than 23.5%, or > Atmospheres greater than 1% of the Lower Explosive Limit, or > Atmospheres that are >50% of Immediately Dangerous to Life or Health (IDLH) concentrations, or > Work with sensitizers or known human carcinogens, mutagens, or teratogens without process isolation or fully encapsulating personal protection, or > Work with highly infectious biological agents without process isolation
Note on T20: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are all dispensing areas diked or properly graded to control drainage of spilled fuel? 2 - are all workers and operatives are trained to use spill response kit? 3 - Is the procedure in place for collecting and/or containing, and disposing of spilled materials? 4 - All tanks & vessels areas are diked to contain accidental spills?. 5 - Do measures taken to prevent an accidental contaminated runoff from construction , operation, maintenance, plant and storage areas? 6 - Do measures taken to control on deposits of oils, greases and fuels, from site plant and vehicle operations, mechanical failures, spillages and discharges to ground or drains and the dispersion of unattended spills by plant / vehicle movements?. 7 - Do measures taken to control on fuels, oils and other hazardous chemicals spilled on site during re-fueling, storage or transport operations?. 8 - Do we have an Emergency Response Procedure will be followed in the event of environmental emergency such as an oil or chemical spill? 9 - Is there a procedure for concrete wash, clean and dispose to prevent ground contamination, such as; Concrete wash pits with leak proof sedimentation tanks will be provided for washing concrete mixer trucks. The design and location of such wash pits shall be agreed with the Project Manager prior to its construction on site. Concrete dumping or spillages of any kind shall not be allowed in any other location on site? 10 - Is there a procedure to used in the situation of a major spills that will have an impact on the surrounding environment will be promptly reported to the Fire Brigade? 11 - Are there a procedure of disposing off any damage/leakage drums or containers shall be removed in accordance with the local requirements? 12 - Are there a procedure of dealing with spilled contaminated soils, resulted and remediated, accordingly? 13 - Are all personnel trained in the use of spill procedure and response and the adequate spill kits are available on site?
Note on C21: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - All electrical extension cords are equipped with nonconductive plugs 2 - Cords must not be spliced or draped over nails, metal objects 3 - The use of extension cords by means of multiple outlet plugs from single outlets is prohibited 4 - All electrical service removals, alterations and equipment installations are performed by an authorized electrician 5 - Faulty electrical installation 6 - Electrical supply disruption 7 - Exposed cables 8 - Trip / fall hazards from installed cables 9 - Fire hazard Electrical overload 10 - electrocution 11 - Electrical (short circuit) - Contact with exposed conductors or a device that is incorrectly or inadvertently grounded, such as when a metal ladder comes into contact with power lines 12 - Electrical - (static discharge) 13 - Electrical Fire - Use of electrical power that results in electrical overheating or arcing to the point of combustion or ignition of flammables, or electrical component damage 14 - Improper grounding 15 - Damaged insulation 16 - Exposed electrical parts 17 - Overloaded circuits 18 - Inadequate wiring 19 - Wet conditions 20 - Overhead power lines 21 - Damaged tools and equipment
Note on T21: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a meaningful and an effective consultation and communication on health and safety matters being implemented through out the project? 2 - Is the Consultation and communication on health and safety matters in place through the following mechanisms: > Project specific induction - (prior to commencement of contracted work) > Work activity Induction (in SWMS or equivalent) - (prior to commencement any construction work) > Toolbox Meetings - (Monthly intervals or generally when there is the introduction of a new process (SWMS) or when discussing OHS issues/topics). > Subcontractor Meetings - (weekly) > Project team meetings - (weekly) > HSE Committee Meeting - (as agreed with the HSE Committee) > OHS Report - (monthly) > Project Notice Board and general signage - (as required) 3 - Is there a method of communication is to be established in the work procedures to allow constant monitoring of those persons working in the confined space? 4 - Is there a material safety data sheets and appropriate hazard communication training for affected employees is in place? 5 - Are all environmental aspects and impacts been communicated to employees? 6 - Dose the notice
Note on C22: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1- Check that all the workers are using safe hand tools/power tools and instruct them to operate and maintain the same in safe manner 2 - Ensure power tools and hand tools are checked prior to issue 3 - Damaged tools and equipment 4 - Electrical tools or electrical equipment are not to be issued for use until inspected. 5 - Electrical tools or electrical equipment are not to be issued for use until inspected. 6 - "Defective" electrical tools and equipment are to be tagged and removed from service until repaired and inspected 7 - The frequency for inspection of construction electrical tools and electrical equipment shall be monthly and inspection indicated by attached color-coded tape or color- coded tie wraps and a color coded inspection tag with Contractor‘s name, the supervisor, the inspection date, equipment number and signature of competent inspector displayed on the tag. 8 - Checking the cords for worn or cracked insulation. 9 - Checking the cords entry to plug and tool housing for frayed or worn insulation and strain relief. 10 - Checking the plug prongs for damage. 11 - Checking the plug for exposed connectors 12 - Checking the equipment housing for damage. 13 - Checking trigger locks to ensure they have been removed 14 - Checking the leads for signs of wear, poor connections at probes, etc. 15 - Checking the housing and the readout window for cracks, loose screws, etc. 16 - Check all Ground Fault Circuit Interrupters (GFCI) during the monthly inspections. 17 - Machines are free from any defects / damage. 18 - Pressure switch and safety guards in place where applicable. 19 - Leads are fitted with correct plugs & sockets and free from damages. 20 - Leads wires are free from joints, cuts and other defects. 21 - Leads are suitably rated for the electric current. 22 - Machines / Tools are equipped with properly functioning dead man switch. 23 - Tools issue and maintenance record is properly maintained. 24 - Tools are correctly stored. 25 - Discarded Tools / cords are marked and stored separately.
Note on T22: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is the Project HSE Plan presents actions, responsibilities, protocol, conformance, verification and containment activities to be undertaken by project staff and sub-contractors at all times during the construction phase of the project. 2 - Is the implementation of the HSE plan is being monitored, evaluated for accuracy and any changes made communicated to all relevant personnel. 3 - Is the HSE Plan, CEMP, Security Plan, HAZcomm., standards & procedures are updated, signed, approved and distributed, acknowledged to the construction team's responsible individuals? 4 -Is the project overall safety risk register developed, approved and being implemented?
Note on C23: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Immediate Postural and Load Factor; 1- Is the body position stable? 2 - Is the trunk of the body straight (not twisted)? 3 - Is the operation carried out by one person? 4 - Is the load kept close to the body? 5 - Can the handler avoid stretching upwards? 6 - Can the handler avoid a prolonged period in one posture? 7 - Can the handler perform the task without overreaching? 8 - Are both hands used for grasping? 9 - Are the hands less than a shoulder width apart? 10 - Is the load positioned centrally in front of the body? 11 - Is the load reasonably symmetrical? 12 - Is the load stable and easy to grasp? 13 - Can handlers move and position themselves freely? Environmental Risk Factor; 1 - Too hot? 2 - Too cold? 3 - Too bright? 4 - Too dark? 5 - Too noisy to allow effective communication? 6 - Too wet? 7 - Slippery underfoot? 8 - Does any personal protective equipment interfere with the task? Carrying; 1 - Is the load carried at knuckle height? 2 - Is the load carried at arm's length from the body? 3 - Is the load carried for more than 10 meters? Seated Work; 1 - Is the load lifted from below thigh height? 2 - Is the load lifted to above shoulder height? 3 - Is the load lifted at arm's length from the body? 4 - Does the handler have to twist significantly to the side? 5 - Is the load heavier than 5kg? Pushing and Pulling; 1 - Does the pushing and pulling take place below knuckle height? 2 - Does the pushing and pulling take place above shoulder height? 3 - Is the initial or maximum force required to push or pull the load more than 25kg? 4 - Is the continuous force required to keep the load in motion more than 10kg?
Note on T23: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a system of proper HSE reporting in place, such as; all work-related incidents including near misses, injuries, illnesses, property damage, environmental incidents, security events and motor vehicle incidents, using proper protocol followed? 2 - Is the HSE incidents, accident, near misses, unsafe acts/conditions and dangerous occurrences are being reporting in timely manner and in the approved company format? 3 - Are the workers informed, trained in reporting all near misses, unsafe acts/conditions to the appropriate authority or line of manager? 4 - Is the Weekly / Monthly HSE Statistics data, including (leading & lagging) indicators, reviewed by the senior management?
Note on C24: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: CHECKS; 1 - Plant guarding is in place and in good condition to prevent injury from parts disintegrating or failing 2 - Access and egress is in good condition, hand holds, ladder etc. are sound and in place 3 - Operator's seat and controls are in good condition and all safety devices (limiters and indicators) are labelled and fully operational. 4 - Operator's manual / instructions supplied by the manufacturer of the plant are available in the plant. 5 - Hazards with the use of the plant are identified, i.e. Safe working limits on batters, operator safety instructions etc., are displayed clearly in the cabin of the plant for operator reference. I.E. PLANT SPECIFIC RISK ASSESSMENT. 6 - Hazard controls, i.e. seat belts must be worn and hearing protection must be worn, caution/danger signs (counter weight slewing area, excavators and cranes) etc. are displayed in the cabin or on the plant in a position relevant to the hazard. 7 - Operator cabin/work platform access is clean and free of debris, loose tools, equipment, grease oil and is in an orderly condition. 8 - Plant is clean and free from oil leaks and oil build up. 9 - Plant Pre Start inspection is complete and a record of the inspection will be provided at commencement on the site. 10 - Certification of operator / proof of competency. 11 - Operational Noise Level - Statement of conforming emission level. 12 - Plant has no areas of excessive wear or damage. Mobile plant required to have; 1 - Plant is fitted with a Roll Over Protection Structure (R.O.P.S.) and operator restraint. 2 - Plant is fitted with a front horn and reversing beeper. 3 - Plant is fitted with a rotating or flashing amber beacon. Plant used to lift Material and equipment; Backhoes, excavators, cranes and loaders used as crane from designed lifting points. The Safe Working Load of the plant item is displayed on the plant as: EITHER; A Crane Chart supplied by the manufacturer specific to the plant item in the cabin of the plant for operator reference OR; The Safe Working Load of the equipment on the boom of the loader bucket and of the dipper arm of excavators - a combination of both is required for backhoes e.g. SWL 1.2ton. Personal Lifting Equipment - (Cherry Pickers, boom lift and elevated platform) 1 - Safety Working Load is displayed on work bucket / platform. 2 - Fully body harnesses and lanyards are to be provided for personnel using the equipment. 3 - Safety Instruction for the operation of the equipment is clearly displayed in the work bucket / platform. 4 - The supplier have provided training for personnel using the platform in the safe use of the equipment
Note on T24: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Do all personnel have the correct information, instruction and training according to their role and responsibilities? 2 - Is the contractor promoting awareness of company standards and regulations among their employees on a regular basis, or when it is necessary? 3 - Do all personnel have completed basic relevant awareness training, such as; Fire Awareness Training, Heat Stress awareness Training, Safety Signs and Color Code awareness Training, Environmental Awareness Training, Using Fire Extinguisher Awareness Training, Emergency reporting Awareness Training, Unsafe Act/Conditions reporting awareness training, Evacuation Procedure Awareness Training?
Note on C25: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Crane Inspected 2 - Operator certified 3 - Lift Plan approved 4 - PTW obtained 5 - lifting equipment is suitable for the use it is being put to, marked with safe working load, properly maintained and inspected, and receives a periodic thorough examination. 6 - Are all members of the lifting operations team including the Appointed Person, Crane Drivers and Slingers / Signalers / Banksmen will be competent and have such practical and theoretical knowledge and experience as is necessary to carry out their duties. 7 - Bank man is available and certified 8 - The crane operator have a practical and theoretical knowledge of lifting operations 9 - Lifting operations will be undertaken by a minimum of three competent people the crane operator, slinger / signaler (slinger and signaler can be one person) / banks man / flagman (banks man and flagmen can be one person) and Supervisor 10 - Certification of Lifting Equipment / Lifting Gear / Lifting Devices 11 - Lifting plan prepared/approved/communicated 12 - Lifting gear (Chain sling, shackle, webbing sling, lifting clamps etc.) / devices (Chain block, Winch, Monorail etc.) are checked, inspected & tagged - ( size, length, dia, width, SWL,Condition & defects. 13 - All lifting equipment / gears have valid test certificates and are in good condition.
Note on T25: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there process of SBO for leadership to identify and reinforce safe work practices/behaviors? 2 - Is there process of SBO for leadership to identify and improve on at-risk practices? 3 - Is there process of SBO for leadership to identify and improve on practices, conditions, controls, and compliance that eliminate or reduce hazards? 4 - Is there a process of SBO for leadership to make positive, corrective, cooperative, collaborative feedback/recommendations? 5 - Is there a training program for BBST, that how to identify critical safety behavior and how to provide feedback and the number of personnel trained. 6 - Is there a program for the leadership to carry out SBO once a month or twice (depends project scope of work), and record available?

## HSE-Stat
Safety Statistics
Category | Item |  | This Week | This Month | Year to Date | Cumulative
Category | Total Hours Worked |  | 2040 | 2040 | 80246 | 80246
| Safe Hours Worked |  | 2040 | 2040 | 80246 | 80246
Reactive | LTI |  | 0 | 0 | 0 | 0
| MTC (Healed w/o Disability) |  | 0 | 0 | 0 | 0
| MTC (Healed w/ Disability) |  | 0 | 0 | 0 | 0
| Near Miss |  | 0 | 0 | 9 | 0
| First Aid Cases |  | 0 | 2 | 2 | 2
| Fatality |  | 0 | 0 | 0 | 0
| Fire Incident Cases |  | 0 | 0 | 0 | 0
| Vehicle Incident |  | 0 | 0 | 0 | 0
| Property Damages |  | 0 | 0 | 0 | 0
Proactive | Induction Training |  | 0 | 0 | 48 | 48
| No.of Internal Training |  | 0 | 0 | 4 | 4
| No.of Internal Audit |  | 0 | 0 | 1 | 1
| No. of Toolbox Talks |  | 1 | 1 | 26 | 26
| Safety Awards/Incentives |  | 0 | 0 | 2 | 2
[7 empty] | Category | Item | This Week | This Month | Year to Date | Cumulative
Consultant Safety Inspection (Weekly Basis) | [6 empty] | Overall Average | 82%
Week Number | Date of Audit | Date Issued | Numbers Of Comments | Overall Score | Date Closed | Closure Duration | This Week Score | 83%
Week-1 | 2026-04-06 | 2026-04-06 | 0 | 84.09% | 2026-04-07 | 1
Week-2 | 2026-04-13 | 2026-04-13 | 0 | 84.09% | 2026-04-14 | 1
Week-3 | 2026-04-20 | 2026-04-20 | 0 | 84.09% | 2026-04-21 | 1
Week-4 | 2026-04-27 | 2026-04-27 | 0 | 84.09% | 2026-04-28 | 1
Week-5 | 2026-05-04 | 2026-05-04 | 0 | 84.09% | 2026-05-05 | 1
Week-6 | 2026-05-11 | 2026-05-11 | 0 | 84.09% | 2026-05-12 | 1
Week-7 | 2026-05-18 | 2026-05-18 | 0 | 84.09% | 2026-05-19 | 1
Week-8 | 2026-05-24 | 2026-05-24 | 0 | 84.09% | 2026-05-25 | 1
Week-9 | 2026-06-01 | 2026-06-01 | 0 | 84.09% | 2026-06-02 | 1
Week-10 | 2026-06-08 | 2026-06-08 | 0 | 84.09% | 2026-06-09 | 1
Week-11 | 2026-06-15 | 2026-06-15 | 0 | 84.09% | 2026-06-16 | 1
Week-12 | 2026-06-22 | 2026-06-22 | 0 | 84.09% | 2026-06-23 | 1
Week-13 | 2026-06-29 | 2026-06-29 | 0 | 84.09% | 2026-06-30 | 1
Week-14 | 2026-07-06 | 2026-07-06 | 0 | 84.09% | 2026-07-07 | 1
Week-15 | 2026-07-13 | 2026-07-13 | 0 | 82% | 2026-07-13 | 1
Week-16 | 2026-07-20 | 2026-07-20 | 0 | 83% | 2026-07-21 | 1
Week-17 | 2026-07-27 | 2026-07-27 | 0 | 83% | 2026-07-28 | 1
Week-18 | 2026-08-03 | 2026-08-03 | 0 | 83% | 2026-08-04 | 1
Week-19 | 2026-08-10 | 2026-08-10 | 0 | 83% | 2026-08-11 | 1
Week-20 | 2026-08-17 | 2026-08-17 | 0 | 83% | 2026-08-18 | 1
Week-21 | 2026-08-24 | 2026-08-24 | 0 | 83% | 2026-08-25 | 1
Week-22 | 2026-08-31 | 2026-08-31 | 0 | 83% | 2026-09-01 | 1
Week-23 | 2026-09-07 | 2026-09-07 | 0 | 83% | 2026-09-08 | 1
Week-24 | 2026-09-14 | 2026-09-14 | 0 | 83% | 2026-09-15 | 1
Week-25 | 2026-09-21 | 2026-09-21 | 0 | 83% | 2026-09-22 | 1
Week-26 | 2026-09-28 | 2026-09-28 | 0 | 83% | 2026-09-29 | 1
Week-27 | 2026-10-05 | 2026-10-05 | 0 | 83% | 2026-10-06 | 1
Week-28
Week-29
Week-30
Week-31
Week-32
Week-33
Week-34
Week-35
Week-36
Week-37
Week-38
Week-39
Week-40
Week-41
Week-42
Week-43
Week-44
Week-45
Week-46
Week-47
Week-48
Week-49
Week-50
Week-51
Week-52
Week-53
Week-54
Week-55
Week-56
Week-57
Week-58
Week-59
Week-60
Week-61
Week-62
Week-63
Week-64
Week-65
Week-66
Week-67
Week-68
Week-69
Week-70
Week-71
Week-72
Week-73
Week-74
Week-75
Formulas:
Date Issued = [Item]
Year to Date = [Date Issued]+1

## Major Quantities
BOQ Number | Description of Item | Total Quantity | Unit of Measurement | Plan To Date | Actual To Date | Remaining Total | Variance
2.1.6 | Backfill Material | 2615 | m3 | 2615 | 2615 | 0 | 0
2.2.1 | Bituminous wearing course asphalt layer | 217 | m3 |  | 217 | 0 | 217
2.2.2 | Bituminous base course asphalt layer | 304 | m3 |  | 304 | 0 | 304
2.2.3 | Base course layer | 867 | m3 | 0 | 867 | 0 | 867
2.2.4 | Subgrade material | 1300 | m3 | 606.71 | 1300 | 0 | 693.29
2.2.7.1 | Interlocking block pavers | 1326 | m2 |  | 1326 | 0 | 1326
2.3.8 | Precast concrete curbstone | 1294 | Lm | 0 | 1294 | 0 | 1294
3.2 | Reinforced concrete | 449 | m3 | 449 | 449 | 0 | 0
3.3 | 150 mm thk concrete floor slab on grade | 307 | m3 | 307 | 307 | 0 | 0
3.4 | Autoclaved aerated panel for slabs, external and internal walls and parapet | 55 | m2 | 55 | 55 | 0 | 0
4.1 | Concrete Masonry Unit | 444 | m2 | 431.6124 | 444 | 0 | 12.3876
15.1.2.1 | 200 mm Ø HDPE Fire Fighting | 48 | Lm | 48 | 48 | 0 | 0
15.1.2.2 | 150 mm Ø HDPE Fire Fighting | 200 | Lm | 200 | 200 | 0 | 0
15.2.2.1 | 100 mm Ø HDPE Water Supply | 20 | Lm | 20 | 20 | 0 | 0
15.2.2.2 | 90 mm Ø HDPE Water Supply | 235 | Lm | 235 | 235 | 0 | 0
15.2.2.3 | 63 mm Ø HDPE Water Supply | 8 | Lm | 8 | 8 | 0 | 0
15.2.2.4 | 50 mm Ø HDPE Water Supply | 40 | Lm | 40 | 40 | 0 | 0
15.3.2.1 | 110 mm Pipe sewer upvc pipe | 105 | Lm | 105 | 105 | 0 | 0
15.3.2.2 | 160 mm Pipe sewer upvc pipe | 75 | Lm | 75 | 75 | 0 | 0
15.4.1.1 | 8" Ø Fire Fighting HDPE Pipes | 15 | Lm | 15 | 15 | 0 | 0
15.5.1.1 | 63 mm Ø HDPE pipes Water Supply | 40 | Lm | 40 | 40 | 0 | 0
15.6.1.1 | Ø 4" uPVC Pipe Sewer & Drainage | 168 | Lm | 168 | 168 | 0 | 0
15.6.1.2 | Ø 3" uPVC Pipe Sewer & Drainage | 30 | Lm | 30 | 30 | 0 | 0
15.6.1.3 | Ø 2" uPVC Pipe Sewer & Drainage | 132 | Lm | 132 | 132 | 0 | 0
15.6.1.4 | Ø 1" uPVC Pipe Sewer & Drainage | 180 | Lm | 180 | 180 | 0 | 0
16.6.1 | 4C x 185 mm2 +1C x 95mm2 Low voltage cables | 120 | Lm | 80.004 | 120 | 0 | 39.996
16.6.2 | 4C x 120 mm2 +1C x 70mm2 Low voltage cables | 75 | Lm | 50.0025 | 75 | 0 | 24.9975

## Risk Register
Department: | [8 empty] | Status Date: | 2026-10-06
Program
Project: |  |  | Construction of Industrial Units for Artisans in Najran
Project No.: |  |  | NJR1-05-005
Project Location: |  |  | Najran, Saudi Arabia
[16 empty] | Before Treatment | [10 empty] | Post Treatment
Risk Data | [5 empty] | Category |  |  | Risk Description |  |  | Risk Control Dates |  | Risk Manageability | Risk Proximity | Most Likely |  |  | Risk Owner | Risk Response & Treatment Action |  |  |  | Treatment Control Dates |  |  | Most Likely |  |  | Treatment Status
Risk ID | Region | Section / Group | City | Project ID | Risk Status | T/O/I | Internal / External Level1 | Category | Cause / Source | Risk | Consequence / Effect | Identified | Closed |  |  | Liklihood | Impact | Risk Score |  | Risk Response Strategy | Treatment Action | Treatment Action Description | Treatment Action Owner | Start | Due | Closed | Liklihood | Impact | Risk Score
NOTES:
Risk Status: 1.Open, 2.Closed, or 3.Realized
T/O/I: 1.Threat, 2.Opportunity, or 3.Issue
Category (select 1):
1. Political
2. Legal, Regulatory, Compliance
3. Funding, Finance, Budget
4. Management, Governance, Policies, KPI, Performance
5. Human Resources
6. Stakeholders, Authorities, Approvals, Permits
7. Requirements, Specifications, Scope, Procurement, Contract
8. Process, Tools, Technique, Technology
9. Design, Engineering
10. Construction, Execution
11. Testing, Commissioning, Handover
12. Operation, Maintenance
Risk Description (add all 3):
1. Source/Cause
2. Event = Threat, Opportunity, or Issue
3. Consequence/Effect
Risk Response Strategy for Threats: 1.Terminate, 2.Tolerate, 3.Transfer, or 4.Treat
Risk Response Strategy for Opportunities: 1.Ignore, 2.Share, or 3.Enhance/Exploit
Treatment Action: 1.Mitigate, 2.Control, or 3.Fall Back
Treatment Status: 1.Unapproved, 2.Active, or 3.Closed
Risk Level/Score: Likelihood x Highest Impact (Safety, Cost, Schedule, Environment, Quality, or Reputation. See Risk Scoring Matrix tab)

## EV-Chart Data
| 9554134 |  |  | 9554134 | [5 empty] | 0.85
| Baseline Plan (Original Plan) |  |  | Baseline Plan (Crushed) |  |  | Earned Value |  |  | Gross Paid Value |  |  | Forecast |  |  | Actual/Fcst vs Plan
Month | Monthly | Cum | % | Monthly | Cum | % | Monthly | Cum | % | Monthly | Cum | % | Monthly | C um |  | Month | Cum
2026-03-03 | 134128.43 | 134128.43 | 0% | 152202 | 152202 | 0% |  | 0 | 0% | 0 | 0 | 0% |  |  |  | -152202 | -152202 | Actuals thru previous month
2026-04-30 | 638522.06 | 772650.49 | 8.087% | 692767 | 844969 | 8.844% | 771218 | 771218 | 8.072% | 0 | 0 | 0% |  |  |  | 78451 | -73751
2026-05-31 | 488657.03 | 1261307.52 | 13.2% | 727104 | 1572073 | 16.45% | 652117 | 1423335 | 14.9% | 0 | 0 | 0% |  |  |  | -74987 | -148738 | Forecast current and future months
2026-06-30 | 1356793.23 | 2618100.75 | 27.4% | 1870539 | 3442612 | 36.03% | 2117547 | 3540882 | 37.06% | 180835 | 180835 | 1.893% |  |  |  | -1870539 | -2019277
2026-07-31 | 2212825.16 | 4830925.91 | 50.56% | 2737145 | 6179757 | 64.68% | 2201031 | 5741913 | 60.1% | 1725541 | 1906376 | 19.95% |  |  |  | -2737145 | -4756422
2026-08-31 | 1046425.78 | 5877351.69 | 61.52% | 2128922 | 8308679 | 86.96% | 1921737.56 | 7663650.56 | 80.21% | 2554234 | 4460610 | 46.69% |  |  |  | -2128922 | -6885344
2026-09-30 | 675374.23 | 6552725.92 | 68.59% | 1245455 | 9554134 | 100% | 1281933.78 | 8945584.34 | 93.63% | 0 | 4460610 | 46.69% |  |  |  | -1245455 | -8130799
2026-10-31 | 1305544.57 | 7858270.49 | 82.25% |  |  |  | 98305.66 | 9043890 | 94.66% |  |  |  | 510244 | 9554134 | 100% | 510244 | -7620555 |  | Extended Duration
2026-11-30 | 714502.65 | 8572773.14 | 89.73%
2026-12-31 | 981360.86 | 9554134 | 100%
2027-01-31 | [13 empty] | 0
2027-02-28
2027-03-31
2027-04-30
2027-05-31
UPDATE ONLY YELLOW PORTION FROM PRIMAVERA EXPORT, IF NEEDED, EXTEND YELLOW PORTION BASED ON SCHEDULE.
Formulas:
Month = EOMONTH([Month, row above],1)

## Physical-Chart Data
| 224320 |  |  | 241519.85
| Baseline Plan (Original Plan) |  |  | Baseline Plan (Crushed) |  |  | Earned Effort % |  |  | Forecast |  |  | Achieved/Fcst vs Plan
Week | Monthly Effort | Cum Effort | Plan Wt.% | Weekly Effort | Cum Effort | Plan Wt.% | Weekly Wt. | Cum Wt. | Achieved Wt.% | Monthly Wt. | Cum Wt. | Wt.% | Weekly Wt. | Cum Wt.
2026-03-03 | 14673.48 | 14673.48 | 0 | 16022.45 | 16022.45 | 0% |  | 0 | 0% |  |  |  | -16022.45 | -16022.45 | Actuals thru previous month
2026-04-30 | 10034.32 | 24707.8 | 11.01% | 12975.86 | 28998.31 | 12.01% | 26134.04 | 26134.04 | 10.82% |  |  |  | 13158.18 | -2864.27
2026-05-31 | 17663.63 | 42371.43 | 18.89% | 26862.13 | 55860.44 | 23.13% | 23650.35 | 49784.39 | 20.61% |  |  |  | -3211.78 | -6076.05 | Forecast current and future months
2026-06-30 | 19366.49 | 61737.92 | 27.52% | 44046.04 | 99906.48 | 41.37% | 51190.05 | 100974.44 | 41.81% |  |  |  | -44046.04 | -50122.09
2026-07-31 | 46535.41 | 108273.33 | 48.27% | 64090.97 | 163997.45 | 67.9% | 49570.01 | 150544.45 | 62.33% |  |  |  | -64090.97 | -114213.06
2026-08-31 | 28434.85 | 136708.18 | 60.94% | 64388.65 | 228386.1 | 94.56% | 42830.35 | 193374.8 | 80.07% |  |  |  | -64388.65 | -178601.71
2026-09-30 | 26122.93 | 162831.11 | 72.59% | 13133.75 | 241519.85 | 100% | 20196.94 | 213571.74 | 88.43% |  |  |  | -13133.75 | -191735.46
2026-10-31 | 32096.85 | 194927.96 | 86.9% |  |  |  | 1173.22 | 214744.96 | 88.91% | 26774.89 | 241519.85 | 100% | 26774.89 | -164960.57 |  | Extended Duration
2026-11-30 | 19376 | 214303.96 | 95.53%
2026-12-31 | 10016.04 | 224320 | 100%
2027-01-31
2027-02-28
2027-03-31
2027-04-30
2027-05-31
2027-06-30
2027-07-31
2027-08-31
2027-09-30
2027-10-31
2027-11-30
2027-12-31
2028-01-31
2028-02-29
2028-03-31
2028-04-30
2028-05-31
2028-06-30
2028-07-31
2028-08-31
2028-09-30
2028-10-31
UPDATE ONLY YELLOW PORTION FROM PRIMAVERA EXPORT, IF NEEDED, EXTEND YELLOW PORTION BASED ON SCHEDULE.
Formulas:
Week = EOMONTH([Week, row above],1)

## Invoice Log
Weekly Progress Report - Invoice Log | [31 empty] | Y
Project Value | [8 empty] | Payment Status | [7 empty] | Invoices Summary | [9 empty] | Average Invoices durations |  |  |  |  | N
Original Contract Value |  |  | 9554134 |  | O&M Value |  | 0 | EAC | Advance Payment % |  | 0% |  | Advance Payment (SAR) |  | 0 |  | No of Submitted Invoices |  | 5 |  | Submitted Invoices (SAR) |  | 6505001 |  | Submiited Invoice Peroid | 2026-08-31 | CM / PgM Average Approval duration |  | 0 | Average Invoice Value | 1301000.2
Revised Contract Value |  | 21100000 | 9554134 |  | Revised O&M Value |  | 0 | #REF! | Retention % |  | 0% |  | Retention (SAR) |  | 0 |  | No of Approved Invoices (CM) |  | 5 |  | Approved Invoices (CM) (SAR) |  | 6505001 |  |  |  | MODON PM & Accounts Average Approval duration |  | 0
Estimate At Completion Value |  | 20900000 | 9554134 | #REF! | Submitted Invoices (Gross Value) |  | 6505001 |  | Penalties and deduction % |  | 0.2093% |  | AP Recovery (SAR) |  | 0 |  | No of Approved Invoices (PM) |  | 5 |  | Approved Invoices (PM) (SAR) |  | 6505001 |  | Invoice Submitted Compared to Contract Value | 68.09% | Payments Average Duration |  | 26.75
Potential Changes |  | 200000 | 0 |  | Total Deduction |  | -20000 |  | Penalties and deduction (SAR) |  | -20000 |  | Retention Cumulative (SAR) |  | 0 |  | No of Paid Invoices |  | 4 |  | Paid Invoices (SAR) |  | 4460610 |  |  |  | Invoices Average total Duration |  | 26.75
Invoice Reference |  |  |  | Invoice Value |  |  |  |  | Period Covered |  | CM / PgM Approval Timeline |  |  |  | Modon PM & Accounts Approval | [6 empty] | Payment Status |  |  |  |  | Total Invoice Duration | Remarks
# | Invoice No. | Doc Control reference | Submittal Rev. # | Gross Value | AP Recovery | Retention | Deduction / Penalties | Amount (net) + VAT 15% | Start Date | End Date | Date to CM / PgM | CM / PgM Approval (Yes/No) | CM / PgM Reply Date | Days Elapsed | Date to PM | PM Approval (Yes/No) | PM Reply Date | Date to Accounts | Accounts Approval (Yes/No) | Accounts Approval Date | Days Elapsed | Date Paid | Amount Paid | Paid % | Payment Period (d) | Amount Pending
1 | 1 | NJR1-01-007-LBC-TS9-1-PRW-IPC-0001-00 |  | 180835 | 0 | 0 | 0 | 207960.25 | 2026-03-03 | 2026-04-30 | 2026-05-04 | Y | 2026-05-04 | 0 | 2026-05-04 | Y | 2026-05-04 | 2026-05-04 | Y | 2026-05-04 | 0 | 2026-06-04 | 180835 | 0% | 31 | 0 | 31 |  |  |  | format if no, make shaded
2 | 2 | NJR1-05-005-LBC-TS9-1-PRW-IPC-0002-00 |  | 318233 | 0 | 0 | 0 | 365967.95 | 2026-05-01 | 2026-05-31 | 2026-06-06 | Y | 2026-06-06 | 0 | 2026-06-06 | Y | 2026-06-06 | 2026-06-06 | Y | 2026-06-06 | 0 | 2026-07-07 | 318233 | 0% | 31 | 0 | 31
3 | 3 | NJR1-05-005-LBC-TS9-1-PRW-IPC-0003-00 |  | 1407308 | 0 | 0 | 0 | 1618405.2 | 2026-06-01 | 2026-06-30 | 2026-06-30 | Y | 2026-06-30 | 0 | 2026-06-30 | Y | 2026-06-30 | 2026-06-30 | Y | 2026-06-30 | 0 | 2026-07-22 | 1407308 | 0% | 22 | 0 | 22
4 | 4 | NJR1-05-005-LBC-TS9-1-PRW-IPC-0004-00 |  | 2554234 | 0 | 0 | 0 | 2937370.1 | 2026-07-01 | 2026-07-31 | 2026-08-01 | Y | 2026-08-01 | 0 | 2026-08-01 | Y | 2026-08-01 | 2026-08-01 | Y | 2026-08-01 | 0 | 2026-08-24 | 2554234 | 0% | 23 | 0 | 23
5 | 5 | NJR1-05-005-LBC-TS9-1-PRW-IPC-0005-00 |  | 2044391 | 0 | 0 | -20000 | 2331048.65 | 2026-08-01 | 2026-08-31 | 2026-09-01 | Y | 2026-09-01 | 0 | 2026-09-01 | Y | 2026-09-01 | 2026-09-01 | Y | 2026-09-01 | 0 |  | 0 | 0% |  | 2044391
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
|  |  | TOTAL | 6505001 | 0 | 0 | -20000 | 7460752.15 | [14 empty] | 4460610 |  |  | 2044391
Formulas:
CM / PgM Reply Date = [CM / PgM Approval Timeline]
Modon PM & Accounts Approval = [CM / PgM Reply Date]
Invoices Summary = [Modon PM & Accounts Approval]
Date to Accounts = [Invoices Summary]
Accounts Approval Date = [Date to Accounts]
Note on I3: Without O&M Cost
Note on D4: Without O&M Cost
Note on E4: Without O&M Cost

## Procurement
MATERIALS DELIVERY
Project Name : Construction of Industrial Units for Artisans in Najran
| Project ID : NJR1-05-005 |  |  |  | Date : | [6 empty] | Date as of : | 2026-06-20 | [9 empty] | 2026-07-26
Sr. NO. | Project ID | ACT # in P6 | Item Description | Discipline | (Long \Short) Lead Items | BOQ. No. | Unit | Quantity | Proc. Qty | Required P.O Date | Date of Pur. Order Issued | Purchase Order No. | Supplier | Supplier Phone | Method of Shipping | Required on Job | E.D.A. to Site | A.D.A. to Site | Lead Time | Approval Status | The Impact (BOQ Cost) | Completion Rate | Remarks
1 | NJR1-05-005 | NJR1-MS-LL-CO-PS-100 | Autoclaved aerated panel (ACC Blocks) | Concrete Work | Long Lead | 3.4 | m2 | 55 | 55 | 2026-05-16 | 2026-06-10 | Najran Workshop - - Modon / 37 /2026 | Siporex | + 966 11 498 1800 | Land | 2026-08-27 | 2026-08-24 | 2026-07-22 | 42 | Approved | 16500 | 100% | Delivered | 1 | Structural
2 | NJR1-05-005 | NJR1-MS-LL-DW-PS-100 | Roll up shutter door | Doors & Windows Work | Long Lead | 8.1.1 | Nos. | 12 | 12 | 2026-05-16 | 2026-03-30 | Najran Workshop - - Modon / 9 /2026 | Randa Automatic Doors Factory | + 966 11 474 8881 | Land | 2026-10-02 | 2026-09-29 | 2026-07-14 | 106 | Approved | 240000 | 100% | Delivered | 1 | Architectural
3 | NJR1-05-005 | NJR1-MS-LL-DW-PS-110 | Steel door | Doors & Windows Work | Long Lead | 8.1.2 | Sets | 12 | 12 | 2026-05-16 | 2026-05-17 | Najran Workshop - - Modon / 28 /2026 | Architectural Doors | +966 1 499 0113 | Land | 2026-09-19 | 2026-09-16 | 2026-07-04 | 48 | Approved | 36000 | 100% | Delivered | 1 | Architectural | to date delivred
4 | NJR1-05-005 | NJR1-MS-LL-DW-PS-120 | Galvanized steel door | Doors & Windows Work | Long Lead | 8.1.3 | Sets | 2 | 2 | 2026-05-16 | 2026-05-17 | Najran Workshop - - Modon / 28 /2026 | Architectural Doors | +966 1 499 0113 | Land | 2026-09-19 | 2026-09-16 | 2026-07-04 | 48 | Approved | 6000 | 100% | Delivered | 1 | Architectural
5 | NJR1-05-005 | NJR1-MS-LL-DW-PS-130 | Solid wood door | Doors & Windows Work | Long Lead | 8.1.4 | Sets | 2 | 2 | 2026-05-16 | 2026-05-17 | Najran Workshop - - Modon / 28 /2026 | Architectural Doors | +966 1 499 0113 | Land | 2026-10-02 | 2026-09-29 | 2026-07-04 | 48 | Approved | 7000 | 100% | Delivered |  | Architectural
6 | NJR1-05-005 | NJR1-MS-LL-DW-PS-140 | Aluminum framed double glazed windows | Doors & Windows Work | Long Lead | 8.2.1 | Nos. | 14 | 14 | 2026-05-16 | 2026-04-27 | Issued | Labenat Albena Company | +966 53 269 4871 | Land | 2026-10-02 | 2026-09-29 | 2026-08-01 | 96 | Approved | 19200 | 100% | Delivered |  | Architectural
7 | NJR1-05-005 | NJR1-MS-LL-DW-PS-150 | Glass and aluminum door | Doors & Windows Work | Long Lead | 8.3.1 | Nos. | 1 | 1 | 2026-05-16 | 2026-04-27 | Issued | Labenat Albena Company | +966 53 269 4871 | Land | 2026-10-02 | 2026-09-29 | 2026-08-01 | 96 | Approved | 7500 | 100% | Delivered |  | Architectural
8 | NJR1-05-005 | NJR1-MS-LL-PR-PS-100 | RBF Steel Structure | Pre Engineered Structure Work | Long Lead | 11.1.1 | Nos. | 1 | 1 | 2026-04-06 | 2026-03-26 | by Contract | Arabian International Company(aic) | +966 92 000 3343 | Land | 2026-06-13 | 2026-06-10 | 2026-06-14 | 80 | Approved | 1700000 | 100% | Delivered | 1 | Structural
9 | NJR1-05-005 | NJR1-MS-LL-PR-PS-110 | Sandwich Panel | Pre Engineered Structure Work | Long Lead | 11.1.1 | Nos. | 1 | 1 | 2026-04-06 | 2026-04-15 | Najran Workshop - - Modon /10 /2026 | BCOMS | +966 13 812 4571 | Land | 2026-06-13 | 2026-06-10 | 2026-07-15 | 91 | Approved | 1700000 | 100% | Delivered | 1 | Structural
10 | NJR1-05-005 | NJR1-MS-LL-PR-PS-120 | Pump Shed | Pre Engineered Structure Work | Long Lead | 11.1.5 | Item | 1 | 1 | 2026-04-06 | 2026-03-26 | by Contract | Arabian International Company(aic) | +966 92 000 3343 | Land | 2026-06-13 | 2026-06-10 | 2026-06-02 | 68 | Approved | 35000 | 100% | Delivered | 1 | Structural
11 | NJR1-05-005 | NJR1-MS-LL-FF-PS-100 | Fire Pump system | Mechanical Works | Long Lead | 15.1.1 | Item | 1 | 1 | 2026-04-09 | 2026-05-06 | Najran Workshop - - Modon /19 /2026 | Saudi Mechanical Industries Co. | +966 11 265 1979 | Land | 2026-07-04 | 2026-07-01 | 2026-10-03 | 150 | Approved | 420000 | 100% | Delivered |  | Mechanical
12 | NJR1-05-005 | NJR1-MS-LL-WS-PS-100 | Facility water storage tanks (GRP Tank) | Mechanical Works | Long Lead | 15.2.8.1 | Nos. | 1 | 1 | 2026-04-09 | 2026-04-20 | Najran Workshop - - Modon /12 /2026 | Pipeco | +966 54 734 5295 | Land | 2026-07-04 | 2026-07-01 | 2026-08-08 | 110 | Approved | 500000 | 100% | Delivered |  | Mechanical
13 | NJR1-05-005 | NJR1-MS-LL-EE-PS-100 | Street lighting network | Electrical Works | Long Lead | 16.3 | Ls | 1 | 1 | 2026-04-16 | 2026-05-14 | Najran Workshop - - Modon /26 /2026 | Pan Light Factory | +966 53 269 4871 | Land | 2026-08-09 | 2026-08-06 | 2026-07-19 | 66 | Approved | 211600 | 100% | Delivered | 1 | Electrical
14 | NJR1-05-005 | NJR1-MS-LL-EE-PS-110 | Lighting, Power Panelboards, and Control | Electrical Works | Long Lead | 16.8 | Nos. | 54 | 54 | 2026-04-15 | 2026-03-29 | Najran Workshop - - Modon /4 /2026 | Technomake Group Company | +966 5455 55 468 | Land | 2026-09-24 | 2026-09-21 | 2026-07-29 | 122 | Approved | 273600 | 100% | Delivered | 1 | Electrical
15 | NJR1-05-005 | NJR1-MS-LL-EE-PS-120 | Lighting Fixtures + Switches | Electrical Works | Long Lead | 16.10 | Ls | 1 | 1 | 2026-04-15 | 2026-05-14 | Najran Workshop - - Modon /26 /2026 | Pan Light Factory | +966 53 269 4871 | Land | 2026-10-07 | 2026-10-04 | 2026-07-19 | 66 | Approved | 190640 | 100% | Delivered | 1 | Electrical
16 | NJR1-05-005 | NJR1-MS-LL-EE-PS-130 | Fire Alarm System | Electrical Works | Long Lead | 16.14 | Ls | 1 | 1 | 2026-04-15 | 2026-05-20 | Najran Workshop - - Modon /30 /2026 | Masdar Hardware Trading Company | +966 112418624 | Land | 2026-10-30 | 2026-10-27 | 2026-06-14 | 25 | Approved | 106280 | 100% | Delivered | 1 | Electrical
17 | NJR1-05-005 | NJR1-MS-LL-EE-PS-140 | Solar Power Plant | Electrical Works | Long Lead | 16.16.1 | Set | 12 | 12 | 2026-04-15 | 2026-03-29 | Najran Workshop - - Modon /2 /2026 | Al-Rabeh International Trading Co. Ltd. | +966 12 698 2183 | Land | 2026-08-20 | 2026-08-17 | 2026-05-20 | 52 | Approved | 441600 | 100% | Delivered | 1 | Electrical
18 | NJR1-05-005 | NJR1-MS-LL-EE-PS-150 | Skylight Fixtures | Electrical Works | Long Lead | 16.17.1 | Nos. | 24 | 24 | 2026-04-15 | 2026-03-25 | Najran Workshop - - Modon /3 /2026 | Green Watt Co. for Energy | +966 13 887 7577 | Land | 2026-08-20 | 2026-08-17 | 2026-07-29 | 126 | Approved | 63360 | 100% | Delivered | 1 | Electrical
19 | NJR1-05-005 | NJR1-MS-SL-EA-PS-100 | Backfill Material | Earth Work | Short Lead | 2.1.6 | m3 | 2615 | 2615 | 2026-05-18 |  | Issued |  |  | Land | 2026-05-24 | 2026-05-21 | 2026-05-10 |  | Approved | 94140 | 100% | Delivered | 1 | Earthworks
20 | NJR1-05-005 | NJR1-MS-SL-EA-PS-110 | Bituminous wearing course asphalt layer | Earth Work | Short Lead | 2.2.1 | m3 | 217 |  | 2026-09-08 | [5 empty] | 2026-10-18 | 2026-10-15 |  |  |  | 208320 |  | Ready for delivery |  | Earthworks
21 | NJR1-05-005 | NJR1-MS-SL-EA-PS-120 | Bituminous base course asphalt layer | Earth Work | Short Lead | 2.2.2 | m3 | 304 |  | 2026-08-16 | [5 empty] | 2026-10-15 | 2026-10-12 |  |  |  | 291840 |  | Ready for delivery |  | Earthworks
22 | NJR1-05-005 | NJR1-MS-SL-EA-PS-130 | Base course layer | Earth Work | Short Lead | 2.2.3 | m3 | 867 |  | 2026-07-23 |  | Issued |  |  | Land | 2026-07-30 | 2026-07-27 | 2026-07-12 |  | Approved | 43350 | 100% | Delivered | 1 | Earthworks
23 | NJR1-05-005 | NJR1-MS-SL-EA-PS-140 | Subgrade material | Earth Work | Short Lead | 2.2.4 | m3 | 1300 |  | 2026-06-30 |  | Issued |  |  | Land | 2026-07-07 | 2026-07-04 | 2026-06-30 |  | Approved | 52000 | 100% | Delivered | 1 | Earthworks
24 | NJR1-05-005 | NJR1-MS-SL-EA-PS-150 | Road Paints | Earth Work | Short Lead | 2.2.5 | Item | 1 |  | 2026-10-03 | [5 empty] | 2026-10-09 | 2026-10-06 |  |  |  | 12000 |  | Ready for delivery |  | Earthworks
25 | NJR1-05-005 | NJR1-MS-SL-EA-PS-160 | Concrete parking bumper | Earth Work | Short Lead | 2.2.7 | Nos. | 42 |  | 2026-08-16 |  |  |  |  | Land | 2026-08-22 | 2026-08-19 | 2026-07-25 |  | Approved | 9660 | 100% | Delivered | 1 | Earthworks
26 | NJR1-05-005 | NJR1-MS-SL-EA-PS-170 | Interlocking block pavers | Earth Work | Short Lead | 2.2.7.1 | m2 | 1326 |  | 2026-08-16 |  |  |  |  | Land | 2026-08-22 | 2026-08-19 | 2026-07-20 |  | Approved | 145860 | 100% | Delivered | 1 | Earthworks
27 | NJR1-05-005 | NJR1-MS-SL-EA-PS-180 | Precast concrete curbstone | Earth Work | Short Lead | 2.3.8 | Lm | 1294 |  | 2026-08-16 |  |  |  |  | Land | 2026-08-22 | 2026-08-19 | 2026-07-18 |  | Approved | 122930 | 100% | Delivered | 1 | Earthworks
28 | NJR1-05-005 | NJR1-MS-SL-EA-PS-190 | Traffic signs | Earth Work | Short Lead | 2.4 | Nos. | 25 |  | 2026-10-26 |  |  |  |  | Land | 2026-11-01 | 2026-10-29 | 2026-07-13 |  | Approved | 30000 | 100% | Delivered | 1 | Earthworks
29 | NJR1-05-005 | NJR1-MS-SL-CO-PS-100 | Concrete Mix Design | Concrete Work | Short Lead | 3 | Ls | 1 | 0.25 | 2026-04-21 |  | Issued |  |  | Land | 2026-04-28 | 2026-04-25 | 2026-04-18 |  | Approved | 831150 | 100% | Delivered | 1 | Structural
30 | NJR1-05-005 | NJR1-MS-SL-CO-PS-110 | Reinforcing Steel Bars | Concrete Work | Short Lead | 3 | Ls | 1 | 19 ton | 2026-04-21 | 2026-04-16 | Najran Workshop - - Modon /11 /2026 | Building Materials Orbit, Building Materials Madar |  | Land | 2026-04-28 | 2026-04-25 | 2026-04-18 |  | Approved | 0 | 100% | Delivered | 1 | Structural
31 | NJR1-05-005 | NJR1-MS-SL-MA-PS-100 | Concrete Masonry Unit | Masonry Work | Short Lead | 4.1 | m2 | 444 |  | 2026-09-06 |  | Issued |  |  | Land | 2026-09-12 | 2026-09-09 | 2026-04-28 |  | Approved | 41720 | 100% | Delivered | 1 | Architectural
32 | NJR1-05-005 | NJR1-MS-SL-MW-PS-100 | Steel ladder with safety cage | Metals Work | Short Lead | 5.1 | Nos. | 1 |  | 2026-06-21 |  |  |  |  | Land | 2026-06-27 | 2026-06-24 |  |  | Approved | 9000 | 100% | Delivered | 1 | Architectural
33 | NJR1-05-005 | NJR1-MS-SL-MW-PS-110 | Steel bollards | Metals Work | Short Lead | 5.2 | Nos. | 24 |  | 2026-10-14 |  |  |  |  | Land | 2026-10-21 | 2026-10-18 | 2026-07-15 | 46218 | Approved | 16800 | 100% | Delivered | 1 | Architectural | to date delivred
34 | NJR1-05-005 | NJR1-MS-SL-MW-PS-120 | Galvanised steel gratings | Metals Work | Short Lead | 5.3 | Nos. | 12 |  | 2026-09-06 |  |  |  |  | Land | 2026-09-12 | 2026-09-09 |  |  | Approved | 36000 | 100% | Delivered | 1 | Architectural
35 | NJR1-05-005 | NJR1-MS-SL-MW-PS-130 | Overflow galvanized steel roof scupper | Metals Work | Short Lead | 5.4 | Nos. | 12 |  | 2026-09-22 |  | Issued |  |  | Land | 2026-09-30 | 2026-09-27 | 2026-06-27 |  | Approved | 10800 | 100% | Delivered | 1 | Architectural
36 | NJR1-05-005 | NJR1-MS-SL-TH-PS-100 | Bitumen waterproofing paint | Thermal & Moisture Protection | Short Lead | 7.1 | m2 | 1972 | 1972 | 2026-04-21 | 2026-04-09 | Najran Workshop - - Modon / 7 /2026 | Bagnid Trading Company |  | Land | 2026-04-28 | 2026-04-25 | 2026-04-22 |  | Approved | 29580 | 100% | Delivered | 1 | Architectural
37 | NJR1-05-005 | NJR1-MS-SL-TH-PS-110 | Polyethylene sheet | Thermal & Moisture Protection | Short Lead | 7.2 | m2 | 2148 | 2148 | 2026-04-21 |  | Issued |  |  | Land | 2026-04-28 | 2026-04-25 | 2026-05-19 |  | Approved | 21480 | 100% | Delivered | 1 | Architectural
38 | NJR1-05-005 | NJR1-MS-SL-TH-PS-120 | Anti termite control | Thermal & Moisture Protection | Short Lead | 7.3 | m2 | 2186 | 2186 | 2026-04-18 |  | Issued |  |  | Land | 2026-04-24 | 2026-04-21 | 2026-05-19 |  | Approved | 17488 | 100% | Delivered | 1 | Architectural
39 | NJR1-05-005 | NJR1-MS-SL-TH-PS-130 | Liquid applied waterproofing membrane | Thermal & Moisture Protection | Short Lead | 7.4.1 | m2 | 80 |  | 2026-09-06 | [5 empty] | 2026-09-12 | 2026-09-09 |  |  |  | 8000 | 100% | Delivered | 1 | Architectural
40 | NJR1-05-005 | NJR1-MS-SL-TH-PS-140 | Geotextile sheet | Thermal & Moisture Protection | Short Lead | 7.4.2 | m2 | 80 |  | 2026-09-06 | [5 empty] | 2026-09-12 | 2026-09-09 |  |  |  | 1280 | 100% | Delivered | 1 | Architectural
41 | NJR1-05-005 | NJR1-MS-SL-TH-PS-150 | Polyurethane waterpoof coating | Thermal & Moisture Protection | Short Lead | 7.4.3 | m2 | 19 |  | 2026-09-06 | [5 empty] | 2026-09-12 | 2026-09-09 |  |  |  | 2280 |  | n/a |  | Architectural
42 | NJR1-05-005 | NJR1-MS-SL-TH-PS-160 | Roofdeck waterproofing system | Thermal & Moisture Protection | Short Lead | 7.4 | Ls | 1 |  | 2026-09-06 | [5 empty] | 2026-09-12 | 2026-09-09 |  |  |  | 46672 |  | On-Going Delivery | 1 | Architectural
43 | NJR1-05-005 | NJR1-MS-SL-TH-PS-170 | Aluminium cladding | Thermal & Moisture Protection | Short Lead | 7.5 | m2 | 250 |  | 2026-09-06 | [5 empty] | 2026-09-12 | 2026-09-09 |  |  |  | 75000 |  | 15/08/2026 | 1 | Architectural
44 | NJR1-05-005 | NJR1-MS-SL-FW-PS-100 | Ceramic tiles | Finishes Work | Short Lead | 9.1.1 | m2 | 75 |  | 2026-05-16 |  | Issued |  |  | Land | 2026-10-16 | 2026-10-13 | 2026-07-07 |  | Approved | 111000 | 100% | Delivered | 1 | Architectural
45 | NJR1-05-005 | NJR1-MS-SL-FW-PS-110 | Carpet rolls | Finishes Work | Short Lead | 9.1.2 | m2 | 56 |  | 2026-05-16 | [5 empty] | 2026-05-22 | 2026-05-19 |  |  |  | 18480 |  | Locally Available |  | Architectural
46 | NJR1-05-005 | NJR1-MS-SL-FW-PS-120 | Epoxy paint | Finishes Work | Short Lead | 9.1.3 | m2 | 1850 |  | 2026-10-10 |  | Issued |  |  |  | 2026-10-16 | 2026-10-13 | 2026-08-03 |  | Approved | 111000 | 100% | Delivered | 1 | Architectural
47 | NJR1-05-005 | NJR1-MS-SL-FW-PS-130 | Granite tiles | Finishes Work | Short Lead | 9.1.4 | m2 | 35 |  | 2026-05-16 | [5 empty] | 2026-05-22 | 2026-05-19 |  |  |  | 8750 |  | Ready for delivery |  | Architectural
48 | NJR1-05-005 | NJR1-MS-SL-FW-PS-140 | Marble strip | Finishes Work | Short Lead | 9.1.5 | Lm | 3 |  | 2026-05-16 | [5 empty] | 2026-05-22 | 2026-05-19 |  |  |  | 750 |  | Ready for delivery |  | Architectural
49 | NJR1-05-005 | NJR1-MS-SL-FW-PS-150 | Wood skirt | Finishes Work | Short Lead | 9.1.6 | Lm | 43 |  | 2026-05-16 | [5 empty] | 2026-05-22 | 2026-05-19 |  |  |  | 1505 |  | Ready for delivery |  | Architectural
50 | NJR1-05-005 | NJR1-MS-SL-FW-PS-160 | Acrylic paint | Finishes Work | Short Lead | 9.2.3 | m2 | 316 |  | 2026-05-16 |  |  |  |  | Land | 2026-05-22 | 2026-05-19 | 2026-07-25 |  | Approved | 9480 | 100% | Delivered | 1 | Architectural
51 | NJR1-05-005 | NJR1-MS-SL-FW-PS-170 | Marble chips | Finishes Work | Short Lead | 9.2.5 | m2 | 75 |  | 2026-05-16 | [5 empty] | 2026-05-22 | 2026-05-19 |  |  |  | 4500 |  | Contractor ready |  | Architectural
52 | NJR1-05-005 | NJR1-MS-SL-FW-PS-180 | GRC panels | Finishes Work | Short Lead | 9.2.6 | m2 | 11 |  | 2026-05-16 | [5 empty] | 2026-08-27 | 2026-08-24 | 2026-07-28 |  |  | 4400 | 100% | Delivered | 1 | Architectural
53 | NJR1-05-005 | NJR1-MS-SL-FW-PS-190 | Phenolic partitions | Finishes Work | Short Lead | 9.2.8 | m2 | 75 |  | 2026-05-16 | [5 empty] | 2026-05-22 | 2026-05-19 |  |  |  | 45000 |  | Contractor ready |  | Architectural
54 | NJR1-05-005 | NJR1-MS-SL-FW-PS-200 | Moisture resistant gypsum board | Finishes Work | Short Lead | 9.3.1 | m2 | 75 |  | 2026-05-16 |  |  |  |  | Land | 2026-05-22 | 2026-05-19 | 2026-07-18 |  | Approved | 11250 | 100% | Delivered | 1 | Architectural
55 | NJR1-05-005 | NJR1-MS-SL-SP-PS-100 | Toilet Fittings | Specialties Work | Short Lead | 10.1 | Nos. | 40 |  | 2026-05-16 | [5 empty] | 2026-05-22 | 2026-05-19 | 2026-07-18 |  | Approved | 25000 | 100% | Delivered | 1 | Architectural
56 | NJR1-05-005 | NJR1-MS-SL-SP-PS-110 | Signage (Toilet & Mosque) | Specialties Work | Short Lead | 10.2 | Nos. | 3 |  | 2026-06-04 | [5 empty] | 2026-06-11 | 2026-06-08 |  |  |  | 750 |  | - |  | Architectural
57 | NJR1-05-005 | NJR1-MS-SL-SP-PS-120 | MODON Logo | Specialties Work | Short Lead | 10.3 | Nos. | 4 |  | 2026-06-04 | [5 empty] | 2026-06-14 | 2026-06-11 |  |  |  | 20000 |  | - |  | Architectural
58 | NJR1-05-005 | NJR1-MS-SL-PR-PS-100 | Intumescent paint | Pre Engineered Structure Work | Short Leads | 11.1.2 | Item | 1 | 1 | 2026-06-23 | 2026-05-13 | by Contract |  |  | Land | 2026-06-30 | 2026-06-27 | 2026-06-29 | 47 | Approved | 220000 | 100% | Delivered | 1 | Structural
59 | NJR1-05-005 | NJR1-MS-SL-PR-PS-110 | Galvanized steel fence | Pre Engineered Structure Work | Short Lead | 11.1.3 | Lm | 36 |  | 2026-05-16 | [5 empty] | 2026-05-22 | 2026-05-19 |  |  |  | 50400 |  | 15/08/2026 |  | Structural
60 | NJR1-05-005 | NJR1-MS-SL-PR-PS-120 | Steel fence gate | Pre Engineered Structure Work | Short Lead | 11.1.4 | Ls | 1 |  | 2026-06-04 | [5 empty] | 2026-06-14 | 2026-06-11 |  |  |  | 69000 |  | 15/08/2026 |  | Structural
61 | NJR1-05-005 | NJR1-MS-SL-FF-PS-100 | HDPE pipes | Mechanical Works | Short Lead | 15.1.2 | Lm | 248 |  | 2026-04-18 |  |  |  |  | Land | 2026-04-24 | 2026-04-21 | 2026-05-14 |  | Approved | 58000 | 100% | Delivered | 1 | Mechanical
62 | NJR1-05-005 | NJR1-MS-SL-FF-PS-110 | Directly Buried Gate valve | Mechanical Works | Short Lead | 15.1.3 | Nos. | 2 |  | 2026-05-04 |  | Issued |  |  | Land | 2026-05-10 | 2026-05-07 | 2026-06-24 |  | Approved | 9500 | 100% | Delivered | 1 | Mechanical
63 | NJR1-05-005 | NJR1-MS-SL-WS-PS-100 | HDPE pipes | Mechanical Works | Short Lead | 15.2.1 | Lm | 303 | 303 | 2026-04-18 |  | delivered |  |  | Land | 2026-04-24 | 2026-04-21 | 2026-05-14 |  | Approved | 53180 | 100% | Delivered | 1 | Mechanical
64 | NJR1-05-005 | NJR1-MS-SL-WS-PS-110 | Directly Buried Gate valve | Mechanical Works | Short Lead | 15.2.2 | Nos. | 16 |  | 2026-05-04 |  | Issued |  |  | Land | 2026-05-10 | 2026-05-07 | 2026-06-24 |  | Approved | 16000 | 100% | Delivered | 1 | Mechanical
65 | NJR1-05-005 | NJR1-MS-SL-WS-PS-120 | Air Valve | Mechanical Works | Short Lead | 15.2.6.1 | Nos. | 1 |  | 2026-05-20 |  | Issued |  |  | Land | 2026-05-27 | 2026-05-24 | 2026-06-24 |  | Approved | 7500 | 100% | Delivered | 1 | Mechanical
66 | NJR1-05-005 | NJR1-MS-SL-WS-PS-130 | Washout Valve | Mechanical Works | Short Lead | 15.2.6.2 | Nos. | 1 |  | 2026-06-09 |  | Issued |  |  | Land | 2026-06-16 | 2026-06-13 | 2026-06-24 |  | Approved | 9500 | 100% | Delivered | 1 | Mechanical
67 | NJR1-05-005 | NJR1-MS-SL-WS-PS-140 | Valve Chamber Cover | Mechanical Works | Short Lead |  | 0 | 0 |  | 2026-06-09 |  | Issued |  |  | Land | 2026-06-16 | 2026-06-13 | 2026-07-11 |  | Approved | 0 | 100% | Delivered | 1 | Mechanical
68 | NJR1-05-005 | NJR1-MS-SL-SW-PS-100 | Sewage tank Cover | Mechanical Works | Short Lead | 15.3.1 | No | 1 |  | 2026-06-25 |  | Issued |  |  | Land | 2026-07-02 | 2026-06-29 | 2026-07-11 |  | Approved | 110000 | 100% | Delivered | 1 | Mechanical
69 | NJR1-05-005 | NJR1-MS-SL-SW-PS-110 | UPVC pipes | Mechanical Works | Short Lead | 15.3.2 | Lm | 550 | 550 | 2026-04-18 |  | Issued |  |  | Land | 2026-04-24 | 2026-04-21 | 2026-05-14 |  | Approved | 48750 | 100% | Delivered | 1 | Mechanical
70 | NJR1-05-005 | NJR1-MS-SL-SW-PS-120 | Sewer manholes cover | Mechanical Works | Short Lead | 15.3.3 | Nos. | 11 |  | 2026-04-18 |  | Issued |  |  | Land | 2026-04-24 | 2026-04-21 | 2026-07-11 |  | Approved | 110000 | 100% | Delivered | 1 | Mechanical
71 | NJR1-05-005 | NJR1-MS-SL-SW-PS-130 | Gully traps | Mechanical Works | Short Lead | 15.3.4 | Nos. | 8 | 8 | 2026-05-04 |  | Issued |  |  | Land | 2026-05-10 | 2026-05-07 | 2026-06-09 |  | Approved | 10400 | 100% | Delivered | 1 | Mechanical
72 | NJR1-05-005 | NJR1-MS-SL-FF-PS-120 | HDPE pipes | Mechanical Works | Short Lead | 15.4.1 | Lm | 15 | 15 | 2026-04-18 |  | Issued |  |  | Land | 2026-04-24 | 2026-04-21 | 2026-05-14 |  | Approved | 6000 | 100% | Delivered | 1 | Mechanical
73 | NJR1-05-005 | NJR1-MS-SL-FF-PS-130 | Seamless black steel pipes & fittings | Mechanical Works | Short Lead | 15.4.2 | Lm | 1083 |  | 2026-04-18 |  |  |  |  | Land | 2026-04-24 | 2026-04-21 | 2026-07-09 |  | Approved | 232750 | 100% | Delivered | 1 | Mechanical
74 | NJR1-05-005 | NJR1-MS-SL-FF-PS-140 | Water sprinklers | Mechanical Works | Short Lead | 15.4.3 | Nos. | 195 |  | 2026-04-18 | [5 empty] | 2026-04-24 | 2026-04-21 |  |  |  | 12810 |  | - |  | Mechanical
75 | NJR1-05-005 | NJR1-MS-SL-FF-PS-150 | Fire hose cabinet | Mechanical Works | Short Lead | 15.4.4 | Nos. | 6 | 6 | 2026-05-04 |  | Issued |  |  | Land | 2026-05-10 | 2026-05-07 | 2026-06-09 |  | Approved | 18000 | 100% | Delivered | 1 | Mechanical
76 | NJR1-05-005 | NJR1-MS-SL-FF-PS-160 | OS&Y Gate valve | Mechanical Works | Short Lead | 15.4.5 | Nos. | 17 |  | 2026-05-04 |  |  |  |  | Land | 2026-05-10 | 2026-05-07 | 2026-07-09 |  | Approved | 23800 | 100% | Delivered | 1 | Mechanical
77 | NJR1-05-005 | NJR1-MS-SL-FF-PS-170 | Fire Alarm Check Valve (ACV) | Mechanical Works | Short Lead | 15.4.6 | Nos. | 1 |  | 2026-05-04 |  |  |  |  | Land | 2026-05-10 | 2026-05-07 | 2026-07-09 |  | Approved | 5500 | 100% | Delivered | 1 | Mechanical
78 | NJR1-05-005 | NJR1-MS-SL-FF-PS-180 | Fire Department Connection (FDC) | Mechanical Works | Short Lead | 15.4.7 | Set | 1 |  | 2026-05-04 |  |  |  |  | Land | 2026-05-10 | 2026-05-07 | 2026-07-09 |  | Approved | 3000 | 100% | Delivered | 1 | Mechanical
79 | NJR1-05-005 | NJR1-MS-SL-FF-PS-190 | Automatic air release valve | Mechanical Works | Short Lead | 15.4.8 | Nos. | 1 |  | 2026-05-04 |  |  |  |  | Land | 2026-05-10 | 2026-05-07 | 2026-07-09 |  | Approved | 1000 | 100% | Delivered | 1 | Mechanical
80 | NJR1-05-005 | NJR1-MS-SL-WS-PS-150 | HDPE pipes | Mechanical Works | Short Lead | 15.5.1 | Lm | 40 |  | 2026-05-04 |  | Issued |  |  | Land | 2026-05-10 | 2026-05-07 | 2026-05-14 |  | Approved | 8000 | 100% | Delivered | 1 | Mechanical
81 | NJR1-05-005 | NJR1-MS-SL-WS-PS-160 | PPR pipe | Mechanical Works | Short Lead | 15.5.2 | Lm | 79 |  | 2026-05-04 |  |  |  |  | Land | 2026-05-10 | 2026-05-07 | 2026-07-09 |  | Approved | 11620 | 100% | Delivered | 1 | Mechanical
82 | NJR1-05-005 | NJR1-MS-SL-WS-PS-170 | Ball Valve | Mechanical Works | Short Lead | 15.5.3 | Nos. | 6 |  | 2026-05-20 |  |  |  |  | Land | 2026-05-27 | 2026-05-24 | 2026-07-09 |  | Approved | 2560 | 100% | Delivered | 1 | Mechanical
83 | NJR1-05-005 | NJR1-MS-SL-WS-PS-180 | Valve box | Mechanical Works | Short Lead | 15.5.5 | Nos. | 14 |  | 2026-05-20 |  | Issued |  |  | Land | 2026-05-27 | 2026-05-24 | 2026-07-09 |  | Approved | 28400 | 100% | Delivered | 1 | Mechanical
84 | NJR1-05-005 | NJR1-MS-SL-SW-PS-140 | uPVC pipes | Mechanical Works | Short Lead | 15.6.1 | Lm | 510 | 510 | 2026-05-04 |  | Issued |  |  | Land | 2026-05-14 | 2026-05-11 | 2026-05-14 |  | Approved | 81420 | 100% | Delivered | 1 | Mechanical
85 | NJR1-05-005 | NJR1-MS-SL-SW-PS-150 | Roof Vent Caps | Mechanical Works | Short Lead | 15.6.2 | Nos. | 2 |  | 2026-09-22 |  |  |  |  | Land | 2026-09-30 | 2026-09-27 | 2026-05-14 |  | Approved | 1000 | 100% | Delivered | 1 | Mechanical
86 | NJR1-05-005 | NJR1-MS-SL-SW-PS-160 | Floor drain | Mechanical Works | Short Lead | 15.6.3 | Nos. | 22 |  | 2026-09-22 |  |  |  |  | Land | 2026-09-30 | 2026-09-27 | 2026-07-18 |  | Approved | 8800 | 100% | Delivered | 1 | Mechanical
87 | NJR1-05-005 | NJR1-MS-SL-SW-PS-170 | Gully Traps cover | Mechanical Works | Short Lead | 15.6.4 | Nos. | 8 |  | 2026-09-22 |  | Issued |  |  | Land | 2026-09-30 | 2026-09-27 | 2026-06-09 |  | Approved | 11600 | 100% | Delivered | 1 | Mechanical
88 | NJR1-05-005 | NJR1-MS-SL-SW-PS-180 | Inspection chamber cover | Mechanical Works | Short Lead | 15.6.5 | Nos. | 3 |  | 2026-09-22 |  | Issued |  |  | Land | 2026-09-30 | 2026-09-27 | 2026-07-11 |  | Approved | 13500 | 100% | Delivered | 1 | Mechanical
89 | NJR1-05-005 | NJR1-MS-SL-SW-PS-190 | Electric water heater | Mechanical Works | Short Lead | 15.6.6.1 | Nos. | 2 | 2 | 2026-05-16 |  | delivered |  |  | Land | 2026-06-03 | 2026-05-31 | 2026-07-25 |  | Approved | 2400 | 100% | Delivered | 1 | Mechanical
90 | NJR1-05-005 | NJR1-MS-SL-SW-PS-200 | Western water closet | Mechanical Works | Short Lead | 15.6.6.2 | Nos. | 8 | 8 | 2026-05-16 |  | delivered |  |  | Land | 2026-06-03 | 2026-05-31 | 2026-06-09 |  | Approved | 14400 | 100% | Delivered | 1 | Mechanical
91 | NJR1-05-005 | NJR1-MS-SL-SW-PS-210 | Bib tap with Perenial Hose | Mechanical Works | Short Lead | 15.6.6.4 | Nos. | 10 |  | 2026-05-16 | [5 empty] | 2026-06-03 | 2026-05-31 |  |  |  | 5500 |  | Delivered | 1 | Mechanical
92 | NJR1-05-005 | NJR1-MS-SL-SW-PS-220 | Wash Basin | Mechanical Works | Short Lead | 15.6.6.5 | Nos. | 2 |  | 2026-05-16 |  |  |  |  | Land | 2026-06-03 | 2026-05-31 |  |  | Approved | 20000 | 100% | Delivered | 1 | Mechanical
93 | NJR1-05-005 | NJR1-MS-SL-SW-PS-230 | Corian Marble Countertop | Mechanical Works | Short Lead | 15.6.6.5 | Nos. | 2 |  | 2026-05-16 | [5 empty] | 2026-06-03 | 2026-05-31 |  |  |  | 20000 |  | - |  | Mechanical
94 | NJR1-05-005 | NJR1-MS-SL-HV-PS-100 | Inline exhaust fans/make-up air fans | Mechanical Works | Short Lead | 15.7.1 | Nos. | 4 |  | 2026-05-16 | [5 empty] | 2026-06-03 | 2026-05-31 |  |  |  | 10400 |  | Contractor ready |  | Mechanical
95 | NJR1-05-005 | NJR1-MS-SL-HV-PS-110 | Indoor ductwork | Mechanical Works | Short Lead | 15.7.3 | K G | 60 |  | 2026-05-16 | [5 empty] | 2026-06-03 | 2026-05-31 |  |  |  | 7800 |  | Contractor ready |  | Mechanical
96 | NJR1-05-005 | NJR1-MS-SL-HV-PS-120 | Square exhaust diffuser | Mechanical Works | Short Lead | 15.7.4 | Nos. | 10 |  | 2026-05-16 | [5 empty] | 2026-06-03 | 2026-05-31 |  |  |  | 2500 |  | Contractor ready |  | Mechanical
97 | NJR1-05-005 | NJR1-MS-SL-HV-PS-130 | Exhaust grills | Mechanical Works | Short Lead | 15.7.5 | Nos. | 2 |  | 2026-05-16 | [5 empty] | 2026-06-03 | 2026-05-31 |  |  |  | 600 |  | Contractor ready |  | Mechanical
98 | NJR1-05-005 | NJR1-MS-SL-HV-PS-140 | Condensate drain pipe | Mechanical Works | Short Lead | 15.7.7 | Item | 38 | 38 | 2026-06-23 |  | delivered |  |  | Land | 2026-06-30 | 2026-06-27 | 2026-05-14 |  | Approved | 34200 | 100% | Delivered | 1 | Mechanical
99 | NJR1-05-005 | NJR1-MS-SL-EE-PS-100 | Electrical manhole cover | Electrical Works | Short Lead | 16.2 | Nos. | 58 |  | 2026-06-25 |  |  |  |  | Land | 2026-07-02 | 2026-06-29 | 2026-07-21 |  | Approved | 188840 | 100% | Delivered | 1 | Electrical
100 | NJR1-05-005 | NJR1-MS-SL-EE-PS-110 | All pump room electrical items | Electrical Works | Short Lead | 16.4 | Ls | 1 |  | 2026-06-25 | [5 empty] | 2026-07-02 | 2026-06-29 |  |  |  | 67280 |  | Delivered |  | Electrical
101 | NJR1-05-005 | NJR1-MS-SL-EE-PS-120 | Grounding system | Electrical Works | Short Lead | 16.5 | Sets | 31 | 31 | 2026-07-12 |  | Issued |  |  | Land | 2026-07-18 | 2026-07-15 | 2026-06-24 |  | Approved | 34000 | 100% | Delivered | 1 | Electrical
102 | NJR1-05-005 | NJR1-MS-SL-EE-PS-130 | Low Voltage Copper Cables & Wires | Electrical Works | Short Leads | 16.6 | Lm | 195 | 195 | 2026-07-12 | 2026-07-25 | Instock | Jeddah Cabels Bahara Alriyadh Cabels | 126360770 | Land | 2026-07-18 | 2026-07-15 | 2026-08-06 | 12 | Approved | 89070 | 100% | Delivered | 1 | Electrical
103 | NJR1-05-005 | NJR1-MS-SL-EE-PS-140 | Cable Trays | Electrical Works | Short Lead | 16.7 | Lm | 500 |  | 2026-07-28 |  |  |  |  | Land | 2026-08-22 | 2026-08-19 |  |  | Approved | 128000 | 100% | Delivered | 1 | Electrical
104 | NJR1-05-005 | NJR1-MS-SL-EE-PS-150 | Safety Disconnect Switches | Electrical Works | Short Leads | 16.9 | Nos. | 132 | 132 | 2026-08-13 | 2026-06-06 | Issued | General Electric (GE) |  | Land | 2026-08-20 | 2026-08-17 | 2026-07-04 | 28 | Approved | 52032 | 100% | Delivered | 1 | Electrical
105 | NJR1-05-005 | NJR1-MS-SL-EE-PS-160 | Telecom & Data System | Electrical Works | Short Lead | 16.11 | Ls | 1 |  | 2026-08-13 | 2026-06-06 | Issued |  |  | Land | 2026-08-20 | 2026-08-17 | 2026-07-04 | 28 | Approved | 198400 | 100% | Delivered | 1 | Electrical
106 | NJR1-05-005 | NJR1-MS-SL-EE-PS-170 | Grounding System | Electrical Works | Short Lead | 16.12 | Ls | 1 | 1 | 2026-07-12 |  | Issued |  |  | Land | 2026-08-20 | 2026-08-17 | 2026-06-24 |  | Approved | 52800 | 100% | Delivered | 1 | Electrical
107 | NJR1-05-005 | NJR1-MS-SL-EE-PS-180 | Lightning Protection System | Electrical Works | Short Lead | 16.13 | Set | 2 |  | 2026-10-05 |  |  |  |  | Land | 2026-10-11 | 2026-10-08 | 2026-06-24 |  | Approved | 40000 | 100% | Delivered | 1 | Electrical
108 | NJR1-05-005 | NJR1-MS-SL-EE-PS-190 | Sockets + outlets + wiring devices | Electrical Works | Short Lead | 16.15 | Ls | 1 |  | 2026-10-05 |  |  |  |  | Land | 2026-10-11 | 2026-10-08 | 2026-07-25 |  | Approved | 98007 | 100% | Delivered | 1 | Electrical
Formulas:
Required on Job = [E.D.A. to Site]+3

## CCO
CONTRACT CHANGE ORDER (CCO)
CCO No. | Date Added | Description of Change | Status | SR | Sch Impact (Months) | Date Approved | Duration (days)
0
0
0
0
0
0

## Issues
[8 empty] | 2026-10-06 | Status | Responsibility
[9 empty] | Open | Contractor
[9 empty] | Closed | Consultant
Modon
Third Party
Other
Issue Log
Issue No | Date Identified | Issue Description | Responsibility | Action Taken | Current Status | Expected/Actual Closure | Duration Elapsed
1 | [6 empty] | 46301
2 | [6 empty] | 46301
3 | [6 empty] | 46301
4 | [6 empty] | 46301
5 | [6 empty] | 46301
6 | [6 empty] | 46301
7 | [6 empty] | 46301
8 | [6 empty] | 46301
9 | [6 empty] | 46301
10 | [6 empty] | 46301
11 | [6 empty] | 46301
12 | [6 empty] | 46301
13 | [6 empty] | 46301
14 | [6 empty] | 46301
15 | [6 empty] | 46301
16 | [6 empty] | 46301
17 | [6 empty] | 46301
18 | [6 empty] | 46301
19 | [6 empty] | 46301
20 | [6 empty] | 46301
21 | [6 empty] | 46301
22 | [6 empty] | 46301
23 | [6 empty] | 46301
24 | [6 empty] | 46301
25 | [6 empty] | 46301
26 | [6 empty] | 46301
27 | [6 empty] | 46301
28 | [6 empty] | 46301
29 | [6 empty] | 46301
30 | [6 empty] | 46301
31 | [6 empty] | 46301
32 | [6 empty] | 46301
33 | [6 empty] | 46301
34 | [6 empty] | 46301
35 | [6 empty] | 46301
36 | [6 empty] | 46301
37 | [6 empty] | 46301
38 | [6 empty] | 46301
39 | [6 empty] | 46301
40 | [6 empty] | 46301
41 | [6 empty] | 46301
42 | [6 empty] | 46301
43 | [6 empty] | 46301
44 | [6 empty] | 46301
45 | [6 empty] | 46301
46 | [6 empty] | 46301
47 | [6 empty] | 46301
48 | [6 empty] | 46301
49 | [6 empty] | 46301
50 | [6 empty] | 46301

## Milestones
Construction of Industrial Units for Artisans in Najran
Item No. | Milestones | Original (Baseline) | Latest | Forecast |  | Days Change
| Contract Duration Current Contract Weeks : 31 of 44 | 43.5714 | 43.5714 | 32.2857 |  | 79 | 31 | 43.5714
1 | Award Date | 2026-01-25 | 2026-01-25 | 2026-01-25 | A | 0
2 | Contract Sign Date | 2026-02-12 | 2026-02-12 | 2026-02-12 | A | 0
3 | Site Handover Date | 2026-03-03 | 2026-03-03 | 2026-03-03 | A | 0
4 | Complete Mobilization | 2025-03-31 | 2025-03-31 | 2025-03-31 | A | 0
5 | Complete existing condition survey, submission of Final Reports | 2025-03-31 | 2025-03-31 | 2025-03-31 | A | 0
6 | Completion of Long Lead Procurement and Material Delivery | 2026-10-27 | 2026-10-27 | 2026-09-02 | F | 55
7 | Completion of Short Lead Procurement and Material Delivery | 2026-10-29 | 2026-10-29 | 2026-08-18 | F | 72
8 | Complete All Warehouse | 2026-11-29 | 2026-11-29 | 2026-09-30 | F | 60
9 | Complete All Outside Mosque (Prayer Room) | 2026-12-05 | 2026-12-05 | 2026-09-30 | F | 66
10 | Complete All GRP Watertank and Pumpshed | 2026-08-24 | 2026-08-24 | 2026-08-24 | F | 0
11 | Complete All External Works | 2026-11-25 | 2026-11-25 | 2026-09-30 | F | 56
12 | Complete all Works including Testing & Commissioning, Cleanup, Closeout Documentation and Ready for Initial Handover | 2027-01-02 | 2027-01-02 | 2026-10-15 | F | 79
13 | Complete Demobilization | 2027-01-02 | 2027-01-02 | 2026-10-15 | F | 79

## Manpower
Head-Count ( Non Manual)
MONTHS | 2026-03-03 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31 | 2028-01-31 | 2028-02-29 | 2028-03-31 | 2028-04-30 | 2028-05-31 | 2028-06-30 | 2028-07-31 | 2028-08-31 | 2028-09-30 | 2028-10-31 | 2028-11-30 | 2028-12-31 | 2029-01-31 | 2029-02-28 | 2029-03-31 | 2029-04-30 | 2029-05-31
Plan - Monthly | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
Planned - Cumulative | 13 | 26 | 39 | 52 | 65 | 78 | 91 | 104 | 117 | 130
Actual - Monthly | 0 | 14 | 16 | 17 | 16 | 16 | 13 | 13
Actual Cumulative | 0 | 14 | 30 | 47 | 63 | 79 | 92 | 105
Forecast - Monthly |  |  | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
Saudi Monthly - Actual |  |  | 1 | 1 | 0 | 0 | 0
Head-Count (Manual)
MONTHS | 2026-03-03 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31 | 2028-01-31 | 2028-02-29 | 2028-03-31 | 2028-04-30 | 2028-05-31 | 2028-06-30 | 2028-07-31 | 2028-08-31 | 2028-09-30 | 2028-10-31 | 2028-11-30 | 2028-12-31 | 2029-01-31 | 2029-02-28 | 2029-03-31 | 2029-04-30 | 2029-05-31
Plan - Monthly | 37 | 42 | 93 | 42 | 137 | 100 | 93 | 119 | 105 | 86
Planned - Cumulative | 37 | 79 | 172 | 214 | 351 | 451 | 544 | 663 | 768 | 854
Actual - Monthly |  | 38 | 45 | 49 | 58 | 55 | 26 | 21
Actual Cumulative |  | 38 | 83 | 132 | 190 | 245 | 271 | 292
Forecast - Monthly |  |  | 93 | 42 | 137 | 100 | 93 | 119 | 105 | 86
Saudi - Actual
Head-Count (Non-Manual) | [31 empty] | Month |  | 2026-10-31 |  |  |  | 2026-11-30
Planned | Actual |  | Variance |  | Forecast Next Month |  | Saudi Staff
13 | 16 |  | 3 |  | 13 |  | 0
Head-Count (Manual) | [10 empty] | Man Power by Trade
Planned | Actual |  | Variance |  | Forecast Next Month |  | Saudi Staff |  |  |  | Key Trade |  | General Labor |  | Carpenter |  | Steel Fixer |  | Concreting Labor |  | Mason |  | Operator |  | Others |  | Total
119 | 21 |  | -98 |  | 105 |  | 0 |  |  |  | Plan |  | 10 |  | 4 |  | 5 |  | 2 |  | 6 |  | 15 |  | 77 |  | 119
[11 empty] | Actual |  | 5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 3 |  | 13 |  | 21
Equipment
MONTHS | 2026-03-03 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31 | 2028-01-31 | 2028-02-29 | 2028-03-31 | 2028-04-30 | 2028-05-31 | 2028-06-30 | 2028-07-31 | 2028-08-31 | 2028-09-30 | 2028-10-31 | 2028-11-30 | 2028-12-31 | 2029-01-31 | 2029-02-28 | 2029-03-31 | 2029-04-30 | 2029-05-31
Plan - Monthly | 15 | 13 | 16 | 16 | 32 | 14 | 19 | 34 | 21 | 10
Planned - Cumulative | 15 | 28 | 44 | 60 | 92 | 106 | 125 | 159 | 180 | 190
Actual - Monthly |  | 10 | 13 | 16 | 16 | 12 | 12 | 8
Actual Cumulative |  | 10 | 23 | 39 | 55 | 67 | 79 | 87
Forecast - Monthly |  |  | 16 | 16 | 32 | 14 | 19 | 34 | 21 | 10
Equipment Count
Planned | Actual |  | Idle |  | Variance |  | Forecast Next Month
34 | 8 |  |  |  | -26 |  | 21
Type | Excavator | Fork lift | Grader | Dumper | Loader | Grader | Skid Loader |  | Dump Truck |  | Water Tank Truck |  | Other |  | Total
Plan | 2 |  | 0 |  | 1 |  | 4 |  | 3 |  | 2 |  | 22 |  | 34
Actual | 0 |  | 0 |  | 1 |  | 1 |  | 0 |  | 1 |  | 5 |  | 8
Idle | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0

## Schedule
Primavera P6 Schedule Status | [9 empty] | Data Date | 2026-10-06
Project Activities Overview
Schedule Statistics |  |  |  |  | Active Schedule Activities
Total Act. | Not Started | In Progress | Completed | % | Active | Ahead | On | Behind | Flag
1462 | 26 | 27 | 1409 | 96.37% | 27 | 0 | 27 | 0 | 27
Critical Path Activities |  |  | Free Float Management (Total) |  |  |  | Failed Start Activities
|  |  | Greater Than 14 Days |  | Less Than 14 Days
Last Week | This Week | Diff | Last Week | This Week | Last Week | This Week | Last Week | This Week | Flag
0 | 0 | 0 | 3 | 2 | 2 | 2 | 13 | 13 | 0

## Testing
Testing and Commissioning
Item | Planned Start Date | Planned Finish Date | Forecast Start Date | Forecast Finish Date | Actual Start Date | Actual Finish Date | % Completed | Open Comments | Closed Comments
Test & Commission Site Works | 2026-12-09 | 2026-12-19 | 2026-12-09 | 2026-12-19
Test & Commission Concrete Works | 2026-12-09 | 2026-12-19 | 2026-12-09 | 2026-12-19
Test & Commission Masonry Works | 2026-12-09 | 2026-12-19 | 2026-12-09 | 2026-12-19
Test & Commission Metal Works | 2026-12-09 | 2026-12-19 | 2026-12-09 | 2026-12-19
Test & Commission Thermal & Moisture Protection | 2026-12-09 | 2026-12-19 | 2026-12-09 | 2026-12-19
Test & Commission Door and Windows | 2026-12-09 | 2026-12-19 | 2026-12-09 | 2026-12-19
Test & Commission Finishes | 2026-12-09 | 2026-12-19 | 2026-12-09 | 2026-12-19
Test & Commission Specialties | 2026-12-09 | 2026-12-19 | 2026-12-09 | 2026-12-19
Test & Commission Pre Engineered Structure | 2026-12-09 | 2026-12-19 | 2026-12-09 | 2026-12-19
Test & Commission Mechanical Works | 2026-12-09 | 2026-12-19 | 2026-12-09 | 2026-12-19
Test & Commission Electrical Works | 2026-12-09 | 2026-12-19 | 2026-12-09 | 2026-12-19
Total | 2026-12-09 | 2026-12-19 | 2026-12-09 | 2026-12-19 | 0 | 0 | #DIV/0! | 0 | 0
Formulas:
Forecast Start Date = [Planned Start Date]
Forecast Finish Date = [Planned Finish Date]

## Lookahead
مستهدف الربع الثاني
# | القطاع | المبادرة | Project ID | اسم المشروع | مدير المشروع | المقاول | بداية المشروع | نهاية المشروع التعاقدية | مدة المشروع (أشهر) | نهاية المشروع المتوقعة/ الالتزام | قيمة المشروع | المخطط /الفعلي | Mobilization المخطط | Mobilization المنفذ | Procurement (Long Lead Items) توريد المواد طويلة الأجل (المخطط) | Procurement (Long Lead Items) توريد المواد طويلة الأجل (المنفذ) | Civil Work الأعمال المدنيه (المخطط) | Civil Work الأعمال المدنيه (المنفذ) | Mechnical Work أعمال الميكانيكل (المخطط) | Mechnical Work أعمال الميكانيكل (المنفذ) | Electrical Work أعمال الكهرباء (المخطط) | Electrical Work أعمال الكهرباء (المنفذ) | تأثير التأخير (إن وجد) على المبادرات في الربع | نسبة الانجاز المستهدفة بنهاية الربع | نسبة الانجاز المحققة بنهاية الربع | مجموع المبالغ المفوترة المستهدفة بنهاية الربع | مجموع المبالغ المفوترة المحققة بنهاية الربع | نهاية المشروع المتوقعة
1 |  |  | NJR1-01-007 | Construction of Industrial Units for Artisans in Najran | Mohammed Alharbi | Labenat Al Bena Company | 2026-03-03 | 2027-01-02 | 10 | 2027-01-02 | 9554134 | 1.3297 | Completed | Completed | Completed | Completed | Install galvanized steel fence Install Sandwich Panels Install steel fence gate Install swing gate for fence with similar design with opening of 3m. Interlocking block pavers Waterproofing System Install Doors - Warehouse WF - Internal & External plastering outside mosque WF - Internal & External Paint Retroreflective Thermoplastic White & Yellow Traffic lines FF - Install Carpet Roll @ Mosque | Install Sandwich Panels = 100% Interlocking block pavers = 100% Waterproofing System = 100% Install Doors - Warehouse = 100% Install Windows - Warehouse = 100% Base Course Asphalt Paving = 100% WF - Internal & External plastering outside mosque = 100% WF - Internal & External Paint = 100% Retroreflective Thermoplastic White & Yellow Traffic lines = 100% Epoxy Paint = 100% Install Phenolic Partition & Doors = 100% Install Aluminum Cladding = 100% Wearing Course Asphalt Paving = 100% FF - Install Carpet Roll @ Mosque = 100% | Hot Press GRP Sectional Panel Water Tanks (10x8x4m) Install fire pump system Install Seamless black steel pipes & fittings Water sprinklers Fire house cabinet Install OS&Y Gate valve Condensate drain piping | Sewer & Drainage Pipes = 100% Water Supply Pipes = 100% Install Seamless black steel pipes & fittings = 100% Condensate drain piping = 100% Install OS&Y Gate valve = 100% HVAC Duct = 100% GRP Tank = 100% Sprinkler System = 100% Plumbing Fixtures = 100% Fire Pump Set = 20% | Electrical substation - Foundation Street lighting feeder pillar Street lighting poles with LED lighting fixtures Concrete wall for KWHM for street lighting feeder pillar Feeder pillars Grounding System Lighting Fixtures and Their Switches Fire Alarm System Lightning Protection System Solar Power Plant Skylight Fixtures All Pumproom Works | Electrical substation - Foundation = 100% Street lighting poles with LED lighting fixtures = 100% Lighting Fixtures and Their Switches = 90% Panel Board Installation = 100% Fire Alarm System = 100% Data & Telephone = 100% Skylight Fixtures = 100% Solar Panels = 100% |  | 89.73% | 94.66% | 68.09% | 6505001 | 2027-01-02
Formulas:
نهاية المشروع المتوقعة = [نهاية المشروع المتوقعة/ الالتزام]

## Project Summary
تم إحراز تقدم في بناء الوحدات الصناعية للحرفيين في نجران.
معلومات المشروع |  |  |  | نطاق المشروع |  |  |  |  | موقع المشروع
المقاول | Labenat Al Bena Company | الاستشاري | Egis | البند | الكمية الكلية (م.ط) | الكمية المنفذة (م.ط) | الكمية المتبقية (م.ط) | نسبة المنفذ
تاريخ استلام الموقع | 2026-03-03 | مدة التنفيذ | 10 Months | Excavation Work | 1148 | 1148 | 0 | 100%
بداية العقد | بداية العقد | قيمة العقد (شامل ضريبة القيمة المضافة) | 10987254.1 | Backfill Work | 2615 | 2615 | 0 | 100%
نسبة الإنجاز المخطط له | 71.19% | نسبة الإنجاز الفعلي | 94.66% | Reinforced concrete | 449 | 449 | 0 | 100%
|  |  |  | 150 mm thk concrete floor slab on grade | 307 | 307 | 0 | 100%
ملخص جدول الكميات |  |  |  | Autoclaved aerated panel for slabs, external and internal walls and parapet | 55 | 55 | 0 | 100%
مكونات المشروع |  | التكلفة (غير شامل ضريبة القيمة المضافة) | النسبة الاجمالية | 110 mm Pipe sewer upvc pipe | 105 | 105 | 0 | 100%
Site Works |  | 1067430 | 11.17% | 160 mm Pipe sewer upvc pipe | 75 | 75 | 0 | 100%
Concrete |  | 847650 | 8.872%
Masonry Work |  | 41720 | 0.4367% | ملخص التوريدات |  |  |  |  | تقدم أعمال layout
Metal Works |  | 72600 | 0.7599% | البند | الكمية الكلية (م.ط) | الكمية المورده (م.ط) | الكمية المتبقية (م.ط) | نسبة التوريد
Thermal & Moisture Protection |  | 190220 | 1.991% | Excavation Work | 1148 | 1148 | 0 | 100%
Doors and Windows |  | 331300 | 3.468% | Backfill Work | 2615 | 2615 | 0 | 100%
Finishes |  | 279905 | 2.93% | Reinforced concrete | 449 | 449 | 0 | 100%
Specialties |  | 45750 | 0.4789% | 150 mm thk concrete floor slab on grade | 307 | 307 | 0 | 100%
Pre Engineered Structure |  | 2039400 | 21.35% | Autoclaved aerated panel for slabs, external and internal walls and parapet | 55 | 55 | 0 | 100%
Mechanical Work |  | 1958790 | 20.5% | 110 mm Pipe sewer upvc pipe | 105 | 105 | 0 | 100%
Electrical Work |  | 2679369 | 28.04% | 160 mm Pipe sewer upvc pipe | 75 | 75 | 0 | 100%
9554134
معالم البرنامج الزمني
البند |  | التاريخ حسب الجدول الزمني | ملاحظة
Mobilization |  | 2026-04-28 | Completed
Submittal of Shop Drawing |  | 2026-04-29 | Completed | التحديات والعوائق
Submittal of Materials |  | 2026-05-02 | Completed | 1-
Excavation Works |  | 2026-11-01 | Completed | 2-
Concrete Works |  | 2026-10-08 | Completed | 3-
Masonry Work |  | 2026-10-10 | Completed | 4-
Metal Works |  | 2026-08-01 | Completed | 5-
Thermal & Moisture Protection |  | 2026-08-12 | Completed | 6-
Pre Engineered Structure |  | 2026-08-24 | Completed | 7-

## Codes (hidden)
Status List
| Approved |  | Y
| Pending |  | N | [5 empty] | (Manhours)
| Potential | [7 empty] | (Mandays)
| Phase | Stage |  | Stage |  | Status |  | Score
[8 empty] | Low | Contractor | Active
| Launch | LOA |  | LOA |  | Active |  | Medium | CM | Expired
| Launch | Kick-off Meeting |  | Kick-off Meeting |  | On Hold |  | High | PgM | Occurred
| Launch | Site Handover |  |  |  | Terminated |  |  | Modon | Pending
| Launch | Mobilization |  | Mobilization | Initial staff and equipment in place, ready to start production | Terminated, Closed |  |  | Other
| Execution | Construction |  | Execution | Tender Documents Issued | Substantial Complete | Initial Handover done at site
| Execution | T&C |  |  | Responses to the OCS completed | Complete | Initial Handover Signed
| Execution | Initial Handover |  | Closeout | Design close-out process complete | Closed | Final Handover done at Site
Warranty Period
Final Handover
Project Status Score
Elements |  |  | Max | Score | Planned | Actual | Remarks
SPI (Physical Effort) |  |  | 100% | 126.8% | No Entry Required
SPI (Cost) |  |  | 100% | 133% | No Entry Required
On Schedule -Active |  |  | 100% | 100% | No Entry Required |  |  |  | 0.6
Manpower Availability |  |  | 100% | 17.65% | No Entry Required
Major Equipment Availability |  |  | 100% | 23.53% | No Entry Required
Billing % Compared to Planned |  |  | 100% | 68.57% | No Entry Required
Safety Score |  |  | 100% | #REF! | No Entry Required
Quality Score |  |  | 100% | 88.78% | No Entry Required