## Dashboard (hidden)
MODON Design Department — Risk & Issue Dashboard
Open Risks | High | Medium | Low |  |  | Open Issues | Critical | High | Normal
236 | 0 | 0 | 0 |  |  | 123 | 0 | 0 | 0
Risks by category × rating | [5 empty] | Issues by category × priority
Category | High | Medium | Low | Total | Exposure (SAR M) | Category | Critical | High | Normal | Total | Exposure (SAR M)
Contractor Performance | 0 | 0 | 0 | 0 | 0 | Contractor Performance | 0 | 0 | 0 | 0 | 0
Contractual | 0 | 0 | 0 | 0 | 0 | Contractual | 0 | 0 | 0 | 0 | 0
Cost | 0 | 0 | 0 | 0 | 0 | Cost | 0 | 0 | 0 | 0 | 0
Financial | 0 | 0 | 0 | 0 | 0 | Design/Technical | 0 | 0 | 0 | 0 | 0
Reporting | 0 | 0 | 0 | 0 | 0 | Financial | 0 | 0 | 0 | 0 | 0
Resources | 0 | 0 | 0 | 0 | 0 | Interface/Utilities | 0 | 0 | 0 | 0 | 0
Schedule | 0 | 0 | 0 | 0 | 0 | Permits/Stakeholder | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | Quality/HSE | 0 | 0 | 0 | 0 | 0
[6 empty] | Schedule | 0 | 0 | 0 | 0 | 0
[6 empty] | Scope | 0 | 0 | 0 | 0 | 0
[6 empty] | Site/Technical | 0 | 0 | 0 | 0 | 0
[6 empty] | Total | 0 | 0 | 0 | 0 | 0
Risks by fund source | [5 empty] | Issues by fund source
Category | High | Medium | Low | Total |  | Category | Critical | High | Normal | Total
MODON | 0 | 0 | 0 | 0 |  | MODON | 0 | 0 | 0 | 0
MOF | 0 | 0 | 0 | 0 |  | MOF | 0 | 0 | 0 | 0
MTLS | 0 | 0 | 0 | 0 |  | MTLS | 0 | 0 | 0 | 0
Modon | 0 | 0 | 0 | 0 |  | Modon | 0 | 0 | 0 | 0
NIDLP | 0 | 0 | 0 | 0 |  | NIDLP | 0 | 0 | 0 | 0
NIS | 0 | 0 | 0 | 0 |  | NIS | 0 | 0 | 0 | 0
Other | 0 | 0 | 0 | 0 |  | Other | 0 | 0 | 0 | 0
WAS | 0 | 0 | 0 | 0 |  | WAS | 0 | 0 | 0 | 0
التجمعات الصناعية | 0 | 0 | 0 | 0 |  | التجمعات الصناعية | 0 | 0 | 0 | 0
الصندوق الصناعي | 0 | 0 | 0 | 0 |  | الصندوق الصناعي | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 |  | Total | 0 | 0 | 0 | 0
Scoring: Risk Score = Probability × Impact → High ≥15, Medium 8–14, Low <8. Issue Priority = Severity × Urgency → Critical ≥15, High 8–14, Normal <8. Impact from value: ≥100M=5, 50–100M=4, 20–50M=3, 5–20M=2, <5M=1. Counts exclude entries with Status = Closed.

## Risk Log
Risk Log
Risk ID | Parent Project ID | Contract / Project ID | Project Name | City | Region | Fund Source | Phase | PM / Owner | Contractor / Designer | Current Status | Value (SAR) | Category | Risk Title | Description | Evidence / Data | Probability (1-5) | Impact (1-5) | Score | Rating | Response | Mitigation Plan | Date Identified | Status | Target Date | Notes / Updates | Source
CEN-TAB1-02-RI-001 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | owner |  | DIVERT THE CABLE TO BE AWAY FROM THE POND |  | Schedule | ELECTRICAL CABLE IN POND | ACCIDENTAL DAMAGE OR CUTTING OF THE ELECTRICAL CABLE DURING EXCAVATION |  | 1 | 1 | H25 |  | Transfer |  | 2025-09-06 | Closed | 2026-04-20
CEN-TAB1-02-RI-002 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | owner |  | THE RFI HAS BEEN RAISED REGRARDING NETWORK DAMAGE DUE TO INTERFERENCE WITH THE FACTORIES |  | Cost | INDUSTRIAL FACILITIES ENCROACHING ON ROAD LOCAL1- 2-3-4-5-COLLECTOR 3-UPGRADE 39-21 | IMPLEMENTATION UNDER THE CURRENT CONDITIONS WILL NOT MEET TRAFIC SAFETY STANDARDS |  | 1 | 2 | M12 |  | Avoid |  | 2026-02-10 | Closed | 2026-04-29
CEN-TAB1-02-RI-003 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | owner |  | THE DRAWING ARE BEING SUBMITTED FOR APPROVAL |  | Scope | TELECOMMUNICATIONS NETWORK INTEGRATION & UNDERSIZED SERVER ROOM IN THE ADMINISTRATION BUILDING | TELECOMMUNICATIONS NETWORK INTEGRATION & UNDERSIZED SERVER ROOM IN THE ADMINISTRATION BUILDING |  | 1 | 3 | M9 |  | Avoid |  | 2026-02-11 | Closed | 2026-06-06
CEN-TAB1-02-RI-004 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | pm |  | MATERIAL DELIVERY HAS STARTED |  | Schedule | DELAY IN PROCUREMENT FOR MV | DELAY IN PROCUREMENT FOR MV |  | 1 | 1 | H16 |  | Mitigate |  | 2026-05-06 | Closed | 2026-06-15
CEN-TAB1-02-RI-005 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | pm |  | PROCUREMENT ACTIVITIES WILL BE INITIATED |  | Schedule | DELAY IN PROCUREMENT DELIVERY OF MATERIALS INCLUDING CATCHBASIN - SLEEVES PIPES FOR UPVC & GRP | DELAY IN PROCUREMENT DELIVERY OF MATERIALS INCLUDING CATCHBASIN -WARNING TAPE - SLEEVES PIPES |  | 1 | 2 | H16 |  | Mitigate |  | 2026-04-27 | Closed | 2026-06-22
CEN-TAB1-02-RI-006 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | owner |  | THE REPLY HAS BEEN RECEIVED AND THE DRAWINGS ARE BEING SUBMITTED FOR UPGRADING TO CODE A |  | Schedule | NEW JERSEY BARRIES DETAILS (LENGTH & DIMENSIONS) | NEW JERSEY BARRIES DETAILS (LENGTH & DIMENSIONS) |  | 1 | 3 | M9 |  | Mitigate |  | 2026-05-04 | Closed | 2026-06-06
CEN-TAB1-02-RI-007 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | pm |  | DRAWING ARE BEING SUBMITTED |  | Schedule | UPGRADING SHOP DRAWING TO CODE A | UPGRADING SHOP DRAWING TO CODE A |  | 1 | 1 | H16 |  | Mitigate |  | 2026-06-29 | Open | 2026-10-19
CEN-TAB1-02-RI-008 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | owner |  | approval & potable water and tse have been submitted for approval |  | Schedule | THERE ARE CHANGES TO THE VAVE CHAMBER DRAWINGS AND THE UPDATED DRAWINGS ARE AWAITING APPROVAL (RFI 29) | UPDATED DRAWINGS ARE AWAITING APPROVAL |  | 1 | 2 | H16 |  | Mitigate |  | 2026-06-29 | Closed | 2026-07-14
CEN-TAB1-02-RI-009 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | pm |  | THE RESPONSE FROM STATION WILL BE RECEIVED TOMORROW |  | Schedule | START OF THE MV NETWORK CONNECTION FOR THE STATION | START OF THE MV NETWORK CONNECTION FOR THE STATION |  | 1 | 2 | M9 |  | Mitigate |  | 2026-06-15 | Open | 2026-10-19
CEN-TAB1-02-RI-010 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | owner |  | email has been sent to the consultant for review and further action |  | Schedule | THERE IS SHINKO FENCE IS OBSTRUCTING THE ELECTRICAL WORKS AND PREVENTING PROGRESS | THERE IS SHINKO FENCE IS OBSTRUCTING THE ELECTRICAL WORKS AND PREVENTING PROGRESS |  | 1 | 3 | M9 |  | Mitigate |  | 2026-07-06 | Open | 2026-10-19
CEN-TAB1-02-RI-011 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | pm |  | SUBMITTAL GELENTY HAS BEEN RESUBMITTED - AL BABTAIN APPROVAL IS CURRENTLY Done |  | Schedule | DELAY IN PROCUREMENT DELIVERY OF MATERIALS INCLUDING LV-STREET LIGHTING -HDPE TELE & DELAY PO FOR STREET LIGHTING | DELAY IN PROCUREMENT DELIVERY OF MATERIALS INCLUDING LV-STREET LIGHTING -HDPE TELE & DELAY PO FOR STREET LIGHTING |  | 1 | 3 | H16 |  | Mitigate |  | 2026-08-31 | Closed | 2026-09-07
CEN-TAB1-02-RI-012 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | owner |  | FIR has been sent to the consultant for review and further action |  | Schedule | PROPOSED MODIFICATION TO THE STORMWATER NETWORK LOCAL 1 | PROPOSED MODIFICATION TO THE STORMWATER NETWORK LOCAL 1 |  | 1 | 2 | M9 |  | Mitigate |  | 2026-07-06 | Closed | 2026-09-12
CEN-TAB1-02-RI-013 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | pm |  | IT WILL BE DELIVERED TODAY |  | Schedule | PROCUREMENT DELIVERY OF MATERIALS INCLUDING LV-STREET | PROCUREMENT DELIVERY OF MATERIALS INCLUDING LV-STREET |  | 1 | 3 | M9 |  | Mitigate |  | 2026-09-14 | Closed | 2026-09-17
CEN-TAB1-02-RI-014 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK | [5 empty] | PROVDING PROTECTIVE BARRIES AND WARNING SIGNS AND KEEPING EQUIPMENT AWAY FROM EXCAVATION EDGES |  | SAFETY | DEEP EXCAVATION - COLLAPSE OF EXCAVATION SIDES | DEEP EXCAVATION - COLLAPSE OF EXCAVATION SIDES |  | 1 | 1 | H16 |  | Mitigate |  | 2025-09-04 | Open

## Issue Log
Issue Log
Issue ID | Parent Project ID | Contract / Project ID | Project Name | City | Region | Fund Source | Phase | PM / Owner | Contractor / Designer | Current Status | Value (SAR) | Category | Issue Title | Description | Evidence / Data | Severity (1-5) | Urgency (1-5) | Priority Score | Priority | Action Required | Date Raised | Status | Target Date | Resolution / Updates | Source
CEN-TAB1-02-RI-001 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | owner |  | DIVERT THE CABLE TO BE AWAY FROM THE POND |  | Schedule | ELECTRICAL CABLE IN POND | ACCIDENTAL DAMAGE OR CUTTING OF THE ELECTRICAL CABLE DURING EXCAVATION |  | 1 | 1 | 1 |  | DIVERT THE CABLE TO BE AWAY FROM THE POND | 2025-09-06 | Closed | 2026-04-20
CEN-TAB1-02-RI-002 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | owner |  | THE RFI HAS BEEN RAISED REGRARDING NETWORK DAMAGE DUE TO INTERFERENCE WITH THE FACTORIES |  | Schedule | INDUSTRIAL FACILITIES ENCROACHING ON ROAD LOCAL1- 2-3-4-5-COLLECTOR 3-UPGRADE 39-21 | IMPLEMENTATION UNDER THE CURRENT CONDITIONS WILL NOT MEET TRAFIC SAFETY STANDARDS |  | 2 | 2 | 1 |  | THE RFI HAS BEEN RAISED REGRARDING NETWORK DAMAGE DUE TO INTERFERENCE WITH THE FACTORIES | 2026-02-10 | Closed | 2026-04-29
CEN-TAB1-02-RI-003 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | owner |  | THE DRAWING ARE BEING SUBMITTED FOR APPROVAL |  | Scope | TELECOMMUNICATIONS NETWORK INTEGRATION & UNDERSIZED SERVER ROOM IN THE ADMINISTRATION BUILDING | TELECOMMUNICATIONS NETWORK INTEGRATION & UNDERSIZED SERVER ROOM IN THE ADMINISTRATION BUILDING |  | 3 | 2 | 1 |  | THE DRAWING ARE BEING SUBMITTED FOR APPROVAL | 2026-02-11 | Closed | 2026-06-06
CEN-TAB1-02-RI-004 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | pm |  | MATERIAL DELIVERY HAS STARTED |  | Schedule | DELAY IN PROCUREMENT FOR MV | DELAY IN PROCUREMENT FOR MV |  | 1 | 1 | 1 |  | MATERIAL DELIVERY HAS STARTED | 2026-05-06 | Closed | 2026-06-15
CEN-TAB1-02-RI-005 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | pm |  | PROCUREMENT ACTIVITIES WILL BE INITIATED |  | Schedule | DELAY IN PROCUREMENT DELIVERY OF MATERIALS INCLUDING CATCHBASIN - SLEEVES PIPES FOR UPVC & GRP | DELAY IN PROCUREMENT DELIVERY OF MATERIALS INCLUDING CATCHBASIN -WARNING TAPE - SLEEVES PIPES |  | 1 | 1 | 1 |  | PROCUREMENT ACTIVITIES WILL BE INITIATED | 2026-04-27 | Closed | 2026-06-22
CEN-TAB1-02-RI-006 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | owner |  | THE REPLY HAS BEEN RECEIVED AND THE DRAWINGS ARE BEING SUBMITTED FOR UPGRADING TO CODE A |  | Schedule | NEW JERSEY BARRIES DETAILS (LENGTH & DIMENSIONS) | NEW JERSEY BARRIES DETAILS (LENGTH & DIMENSIONS) |  | 3 | 1 | 1 |  | THE REPLY HAS BEEN RECEIVED AND THE DRAWINGS ARE BEING SUBMITTED FOR UPGRADING TO CODE A | 2026-05-04 | Closed | 2026-06-06
CEN-TAB1-02-RI-007 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | pm |  | DRAWING ARE BEING SUBMITTED |  | Schedule | UPGRADING SHOP DRAWING TO CODE A | UPGRADING SHOP DRAWING TO CODE A |  | 2 | 1 | 1 |  | DRAWING ARE BEING SUBMITTED | 2026-06-29 | Open | 2026-10-30
CEN-TAB1-02-RI-008 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | owner |  | approval & potable water and tse have been submitted for approval |  | Schedule | THERE ARE CHANGES TO THE VAVE CHAMBER DRAWINGS AND THE UPDATED DRAWINGS ARE AWAITING APPROVAL (RFI 29) | UPDATED DRAWINGS ARE AWAITING APPROVAL |  | 2 | 1 | 1 |  | approval & potable water and tse have been submitted for approval | 2026-06-29 | Closed | 2026-07-14
CEN-TAB1-02-RI-009 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | pm |  | THE RESPONSE FROM STATION WILL BE RECEIVED TOMORROW |  | Schedule | START OF THE MV NETWORK CONNECTION FOR THE STATION | START OF THE MV NETWORK CONNECTION FOR THE STATION |  | 2 | 2 | 1 |  | THE RESPONSE FROM STATION WILL BE RECEIVED TOMORROW | 2026-06-15 | Open | 2026-10-30
CEN-TAB1-02-RI-010 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | owner |  | email has been sent to the consultant for review and further action |  | Schedule | THERE IS SHINKO FENCE IS OBSTRUCTING THE ELECTRICAL WORKS AND PREVENTING PROGRESS | THERE IS SHINKO FENCE IS OBSTRUCTING THE ELECTRICAL WORKS AND PREVENTING PROGRESS |  | 1 | 1 | 1 |  | email has been sent to the consultant for review and further action | 2026-07-06 | Open | 2026-10-26
CEN-TAB1-02-RI-011 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | pm |  | SUBMITTAL GELENTY HAS BEEN RESUBMITTED - AL BABTAIN APPROVAL IS CURRENTLY IN PROGRESS |  | Schedule | DELAY IN PROCUREMENT PO DELIVERY OF MATERIALS INCLUDING LV-STREET LIGHTING -HDPE TELE & DELAY PO FOR STREET LIGHTING | DELAY IN PROCUREMENT DELIVERY OF MATERIALS INCLUDING LV-STREET LIGHTING -HDPE TELE & DELAY PO FOR STREET LIGHTING |  | 1 | 1 | 1 |  | SUBMITTAL GELENTY HAS BEEN RESUBMITTED - AL BABTAIN APPROVAL IS CURRENTLY IN PROGRESS | 2026-08-31 | Closed | 2026-09-07
CEN-TAB1-02-RI-012 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | owner |  | FIR has been sent to the consultant for review and further action |  | Schedule | PROPOSED MODIFICATION TO THE STORMWATER NETWORK LOCAL 1 | PROPOSED MODIFICATION TO THE STORMWATER NETWORK LOCAL 1 |  | 2 | 1 | 1 |  | FIR has been sent to the consultant for review and further action | 2026-07-06 | Closed | 2026-09-12
CEN-TAB1-02-RI-013 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | pm |  | IT WILL BE DELIVERED TODAY |  | Schedule | PROCUREMENT DELIVERY OF MATERIALS INCLUDING LV-STREET | PROCUREMENT DELIVERY OF MATERIALS INCLUDING LV-STREET |  | 3 | 2 | 1 |  | IT WILL BE DELIVERED TODAY | 2026-09-14 | Closed | 2026-09-17
CEN-TAB1-02-RI-014 | TAB1-02-003 | 3066 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TABOUK |  |  |  | pm |  | WAITING SHOP DRAWING |  | Cost | INCREASE IN THE NUMBER OF MANHOLES FOR THE TELECOMMUNICATIONS NETWORK | INCREASE IN THE NUMBER OF MANHOLES FOR THE TELECOMMUNICATIONS NETWORK |  | 3 | 3 | 1 |  |  | 28-9-2026 | Open | 2026-10-26

## Lists (hidden)
Status | Response | Scale | RiskCategory
Open | Avoid | 1 | Schedule
In Progress | Mitigate | 2 | Cost
Monitoring | Transfer | 3 | Financial
Closed | Accept | 4 | Scope
|  | 5 | Contractual
Resources
Contractor Performance
Reporting
Design/Technical
Permits/Stakeholder
Interface/Utilities
Quality/HSE
Site/Technical

## Rules (hidden)
Detection rules & methodology
Each entry in the logs was generated by one of these rules. Adjust thresholds here for reference; logs are static once generated.
Log | Rule | Condition (source field) | Default score | Suggested response
Issue | Schedule slippage beyond tolerance | CWAR Schedule Variance < −10% (Severity 5 if < −25%) | Sev 4–5 × Urg 4 | Recovery plan, EOT/penalty assessment
Issue | Contract flagged as delayed | CWAR "Delayed?" = 1 | Sev 4 × Urg 4 | Delay notice, revised finish
Issue | Extension of time granted | CWAR Approved Extension Of Time > 0 | Sev 3 × Urg 2 | Track vs revised finish
Issue | Contract on hold | CWAR Current Status = Hold | Sev 5 × Urg 5 | Escalate, resumption plan
Issue | Invoices pending payment | CWAR Invoices Pending Payment > 0 | Sev 3 × Urg 3 | Finance follow-up
Issue | Contract value exceeds approved budget | CWAR Current Approved Contract Value > Approved Budget | Sev 4 × Urg 3 | Budget re-approval
Issue | EAC exceeds contract value | CWAR EAC > Current Approved Contract Value | Sev 4 × Urg 3 | Validate EAC, variation
Issue | Approved change orders | CWAR Approved Change Orders (Nos.) > 0 | Sev 2 × Urg 2 | Update baseline
Issue | Guarantee / insurance expired | CWAR "Expired or Expiring in 3 Months" = منتهي الصلاحية, or Insurance Expiry < Data Date | Sev 4 × Urg 5 | Immediate renewal
Issue | Quality / Safety NCRs | CWAR NCRs Issued > 0 | Sev 3 × Urg 3 | Corrective action
Issue | Site / interface / permit / design / contractor issue | CWAR "Remarks on Schedule Status" non-empty (keyword-classified into category) | Sev 3–4 × Urg 3 | PM action owner
Issue | Ongoing project without full approval | All Projects: Status = Ongoing and حالة الاعتماد ∈ {غير معتمد, اعتماد جزئي} | Sev 3–4 × Urg 4 | Expedite approval
Risk | Progress trending behind plan | CWAR Schedule Variance between −5% and −10% | Prob 3 | Mitigate
Risk | Guarantee / insurance expiring ≤ 3 months | CWAR "Expired or Expiring" = تنتهي في ثلاثة أشهر, or Insurance Expiry within 90 days | Prob 4 | Mitigate
Risk | Insufficient time to complete | CWAR Remaining Duration < 90 days and Actual < 85% (Active) | Prob 4 | Mitigate
Risk | Manpower below plan | CWAR Actual Manpower < 70% of Plan Manpower | Prob 3 | Mitigate
Risk | Potential change orders | CWAR Potential Changes (Active) > 0 | Prob 3 | Mitigate
Risk | Baseline not approved / works suspended | CWAR "Delays by Modon or Contractor" contains baseline / stoppage keywords | Prob 3–4 | Mitigate
Risk | Mobilisation / start-up delay | CWAR Status ∈ {LOA, Open} or Actual = 0% more than 60 days after contract start | Prob 3 | Mitigate
Risk | Contractor delayed on multiple contracts | Same contractor with ≥2 active contracts at SV < −10% | Prob 4 | Mitigate
Risk | Budget not approved for next phase | All Projects: Status ∈ {Design completed, Tendered, Future} and حالة الاعتماد ∈ {غير معتمد, اعتماد جزئي} | Prob 3–4 | Mitigate
Risk | No approved budget baseline | All Projects: Status ∈ {Design completed, Future, Under design} and Approved Budget blank/0 | Prob 3 | Mitigate
Risk | Completed design awaiting tender | All Projects: Status = Design completed and no Contractor | Prob 2 | Accept / monitor
Risk | No active CWAR record | All Projects: Status = Ongoing and Parent Project ID not found in active CWAR rows | Prob 3 | Mitigate
Both | Impact scale (from value incl. VAT) | ≥100M = 5 · 50–100M = 4 · 20–50M = 3 · 5–20M = 2 · <5M = 1
Both | Scope | Active CWAR = Current Status ∈ {Active, Substantial Complete, LOA, Hold, Open}. Portfolio excludes Completed, Closed, Merged, Terminated.