## Dashboard (hidden)
MODON Design Department — Risk & Issue Dashboard
Open Risks | High | Medium | Low |  |  | Open Issues | Critical | High | Normal
240 | 0 | 0 | 0 |  |  | 133 | 0 | 0 | 0
Risks by category × rating | [5 empty] | Issues by category × priority
Category | High | Medium | Low | Total | Exposure (SAR M) | Category | Critical | High | Normal | Total | Exposure (SAR M)
Contractor Performance | 0 | 0 | 0 | 0 | 0 | Contractor Performance | 0 | 0 | 0 | 0 | 0
Contractual | 0 | 0 | 0 | 0 | 0 | Contractual | 0 | 0 | 0 | 0 | 0
Cost | 0 | 0 | 0 | 0 | 0 | Cost | 0 | 0 | 0 | 0 | 0
Financial | 0 | 0 | 0 | 0 | 0 | Design/Technical | 0 | 0 | 0 | 0 | 0
Reporting | 0 | 0 | 0 | 0 | 0 | Financial | 0 | 0 | 0 | 0 | 0
Resources | 0 | 0 | 0 | 0 | 0 | Interface/Utilities | 0 | 0 | 0 | 0 | 0
Schedule | 0 | 0 | 0 | 0 | 0 | Permits/Stakeholder | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | Quality/HSE | 0 | 0 | 0 | 0 | 0
[6 empty] | Schedule | 0 | 0 | 0 | 0 | 0
[6 empty] | Scope | 0 | 0 | 0 | 0 | 0
[6 empty] | Site/Technical | 0 | 0 | 0 | 0 | 0
[6 empty] | Total | 0 | 0 | 0 | 0 | 0
Risks by fund source | [5 empty] | Issues by fund source
Category | High | Medium | Low | Total |  | Category | Critical | High | Normal | Total
MODON | 0 | 0 | 0 | 0 |  | MODON | 0 | 0 | 0 | 0
MOF | 0 | 0 | 0 | 0 |  | MOF | 0 | 0 | 0 | 0
MTLS | 0 | 0 | 0 | 0 |  | MTLS | 0 | 0 | 0 | 0
Modon | 0 | 0 | 0 | 0 |  | Modon | 0 | 0 | 0 | 0
NIDLP | 0 | 0 | 0 | 0 |  | NIDLP | 0 | 0 | 0 | 0
NIS | 0 | 0 | 0 | 0 |  | NIS | 0 | 0 | 0 | 0
Other | 0 | 0 | 0 | 0 |  | Other | 0 | 0 | 0 | 0
WAS | 0 | 0 | 0 | 0 |  | WAS | 0 | 0 | 0 | 0
التجمعات الصناعية | 0 | 0 | 0 | 0 |  | التجمعات الصناعية | 0 | 0 | 0 | 0
الصندوق الصناعي | 0 | 0 | 0 | 0 |  | الصندوق الصناعي | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 |  | Total | 0 | 0 | 0 | 0
Scoring: Risk Score = Probability × Impact → High ≥15, Medium 8–14, Low <8. Issue Priority = Severity × Urgency → Critical ≥15, High 8–14, Normal <8. Impact from value: ≥100M=5, 50–100M=4, 20–50M=3, 5–20M=2, <5M=1. Counts exclude entries with Status = Closed.

## Risk Log
Risk Log
Risk ID | Parent Project ID | Contract / Project ID | Project Name | City | Region | Fund Source | Phase | PM / Owner | Contractor / Designer | Current Status | Value (SAR) | Category | Risk Title | Description | Evidence / Data | Probability (1-5) | Impact (1-5) | Score | Rating | Response | Mitigation Plan | Date Identified | Status | Target Date | Notes / Updates | Source
MKH2-02-003-00 |  | MKH2-02-003 | Completion of Infrastructure Works in The Second Industrial City in Makkah Al-Mukarramah | Makkah | Western | MODON | MODON-MIC Phase II | Engr. Abdallah Aljulaifi | Al Enjaz Trading & Contracting Co. | In Progress | 52025516 | Design/Technical | Design revision for Open Channel 3A issued by MODON | Design revision for Open Channel 3A issued by MODON |  | 3 | 4 |  |  | Mitigate | Make Design Revision closely with the Engineer and get approval | 2026-04-07 | Closed
MKH2-02-003-01 |  | MKH2-02-003 | Completion of Infrastructure Works in The Second Industrial City in Makkah Al-Mukarramah | Makkah | Western | MODON | MODON-MIC Phase II | Engr. Abdallah Aljulaifi | Al Enjaz Trading & Contracting Co. | In Progress | 52025516 | Design/Technical | Construction of additional culvert, Number 3, at the Northern Entrance of the Al-Badad | Construction of additional culvert, Number 3, at the Northern Entrance of the Al-Badad |  | 3 | 4 |  |  | Mitigate | Make Design and Drawings closely with the Engineer and get approval | 2026-04-07 | Closed
MKH2-02-003-02 |  | MKH2-02-003 | Completion of Infrastructure Works in The Second Industrial City in Makkah Al-Mukarramah | Makkah | Western | MODON | MODON-MIC Phase II | Engr. Abdallah Aljulaifi | Al Enjaz Trading & Contracting Co. | In Progress | 52025516 | Permits/Stakeholder | Delay in Receiving perrmit for work in Makkah I Hajj Period | Delay in Receiving perrmit for work in Makkah I Hajj Period |  | 3 | 4 |  |  | Mitigate | Make necessary arrangements with the relevent Authorities | 2026-04-14 | Closed
MKH2-02-003-03 |  | MKH2-02-003 | Completion of Infrastructure Works in The Second Industrial City in Makkah Al-Mukarramah | Makkah | Western | MODON | MODON-MIC Phase II | Engr. Abdallah Aljulaifi | Al Enjaz Trading & Contracting Co. | In Progress | 52025516 | Permits/Stakeholder | No permission for Non-Muslim workers to work in Hajj Period | No permission for Non-Muslim workers to work in Hajj Period |  | 4 | 4 |  |  | Mitigate | Make arrangemets for replacement of Non Muslim works durung Hujj period | 2026-04-14 | Closed
MKH2-02-003-04 |  | MKH2-02-003 | Completion of Infrastructure Works in The Second Industrial City in Makkah Al-Mukarramah | Makkah | Western | MODON | MODON-MIC Phase II | Engr. Abdallah Aljulaifi | Al Enjaz Trading & Contracting Co. | In Progress | 52025516 | Design/Technical | Construction of additional culvert, Number 4, at the RAMP2-IN | Construction of additional culvert, Number 4, at the RAMP2-IN |  | 4 | 3 |  |  | Mitigate | Make Design and Drawings closely with the Engineer and get approval | 2026-06-20 | Closed
MKH2-02-003-05 |  | MKH2-02-003 | Completion of Infrastructure Works in The Second Industrial City in Makkah Al-Mukarramah | Makkah | Western | MODON | MODON-MIC Phase II | Engr. Abdallah Aljulaifi | Al Enjaz Trading & Contracting Co. | In Progress | 52025516 | Scope | Delay in Construction Works | Addition works in Collector 9 |  | 3 | 3 |  |  | Mitigate | Make arrangements deploy required resources to complete works within the target date | 2026-06-23 | Open | 2026-11-14
MKH2-02-003-06 |  | MKH2-02-003 | Completion of Infrastructure Works in The Second Industrial City in Makkah Al-Mukarramah | Makkah | Western | MODON | MODON-MIC Phase II | Engr. Abdallah Aljulaifi | Al Enjaz Trading & Contracting Co. | In Progress | 52025516 | Scope | Delay in Construction Works | Construction of Road 52 |  | 3 | 3 |  |  | Mitigate | Make arrangements deploy required resources to complete works within the target date | 2026-06-23 | Open | 2026-12-28
MKH2-02-003-07 |  | MKH2-02-003 | Completion of Infrastructure Works in The Second Industrial City in Makkah Al-Mukarramah | Makkah | Western | MODON | MODON-MIC Phase II | Engr. Abdallah Aljulaifi | Al Enjaz Trading & Contracting Co. | In Progress | 52025516 | Scope | Delay in Construction Works | Construction of Al Gloud Road |  | 3 | 3 |  |  | Mitigate | Make arrangements deploy required resources to complete works within the target date | 2026-06-23 | Closed | 2026-12-01

## Issue Log
Issue Log
Issue ID | Parent Project ID | Contract / Project ID | Project Name | City | Region | Fund Source | Phase | PM / Owner | Contractor / Designer | Current Status | Value (SAR) | Category | Issue Title | Description | Evidence / Data | Severity (1-5) | Urgency (1-5) | Priority Score | Priority | Action Required | Date Raised | Status | Target Date | Resolution / Updates | Source

## Lists (hidden)
Status | Response | Scale | RiskCategory
Open | Avoid | 1 | Schedule
In Progress | Mitigate | 2 | Cost
Monitoring | Transfer | 3 | Financial
Closed | Accept | 4 | Scope
|  | 5 | Contractual
Resources
Contractor Performance
Reporting
Design/Technical
Permits/Stakeholder
Interface/Utilities
Quality/HSE
Site/Technical

## Rules (hidden)
Detection rules & methodology
Each entry in the logs was generated by one of these rules. Adjust thresholds here for reference; logs are static once generated.
Log | Rule | Condition (source field) | Default score | Suggested response
Issue | Schedule slippage beyond tolerance | CWAR Schedule Variance < −10% (Severity 5 if < −25%) | Sev 4–5 × Urg 4 | Recovery plan, EOT/penalty assessment
Issue | Contract flagged as delayed | CWAR "Delayed?" = 1 | Sev 4 × Urg 4 | Delay notice, revised finish
Issue | Extension of time granted | CWAR Approved Extension Of Time > 0 | Sev 3 × Urg 2 | Track vs revised finish
Issue | Contract on hold | CWAR Current Status = Hold | Sev 5 × Urg 5 | Escalate, resumption plan
Issue | Invoices pending payment | CWAR Invoices Pending Payment > 0 | Sev 3 × Urg 3 | Finance follow-up
Issue | Contract value exceeds approved budget | CWAR Current Approved Contract Value > Approved Budget | Sev 4 × Urg 3 | Budget re-approval
Issue | EAC exceeds contract value | CWAR EAC > Current Approved Contract Value | Sev 4 × Urg 3 | Validate EAC, variation
Issue | Approved change orders | CWAR Approved Change Orders (Nos.) > 0 | Sev 2 × Urg 2 | Update baseline
Issue | Guarantee / insurance expired | CWAR "Expired or Expiring in 3 Months" = منتهي الصلاحية, or Insurance Expiry < Data Date | Sev 4 × Urg 5 | Immediate renewal
Issue | Quality / Safety NCRs | CWAR NCRs Issued > 0 | Sev 3 × Urg 3 | Corrective action
Issue | Site / interface / permit / design / contractor issue | CWAR "Remarks on Schedule Status" non-empty (keyword-classified into category) | Sev 3–4 × Urg 3 | PM action owner
Issue | Ongoing project without full approval | All Projects: Status = Ongoing and حالة الاعتماد ∈ {غير معتمد, اعتماد جزئي} | Sev 3–4 × Urg 4 | Expedite approval
Risk | Progress trending behind plan | CWAR Schedule Variance between −5% and −10% | Prob 3 | Mitigate
Risk | Guarantee / insurance expiring ≤ 3 months | CWAR "Expired or Expiring" = تنتهي في ثلاثة أشهر, or Insurance Expiry within 90 days | Prob 4 | Mitigate
Risk | Insufficient time to complete | CWAR Remaining Duration < 90 days and Actual < 85% (Active) | Prob 4 | Mitigate
Risk | Manpower below plan | CWAR Actual Manpower < 70% of Plan Manpower | Prob 3 | Mitigate
Risk | Potential change orders | CWAR Potential Changes (Active) > 0 | Prob 3 | Mitigate
Risk | Baseline not approved / works suspended | CWAR "Delays by Modon or Contractor" contains baseline / stoppage keywords | Prob 3–4 | Mitigate
Risk | Mobilisation / start-up delay | CWAR Status ∈ {LOA, Open} or Actual = 0% more than 60 days after contract start | Prob 3 | Mitigate
Risk | Contractor delayed on multiple contracts | Same contractor with ≥2 active contracts at SV < −10% | Prob 4 | Mitigate
Risk | Budget not approved for next phase | All Projects: Status ∈ {Design completed, Tendered, Future} and حالة الاعتماد ∈ {غير معتمد, اعتماد جزئي} | Prob 3–4 | Mitigate
Risk | No approved budget baseline | All Projects: Status ∈ {Design completed, Future, Under design} and Approved Budget blank/0 | Prob 3 | Mitigate
Risk | Completed design awaiting tender | All Projects: Status = Design completed and no Contractor | Prob 2 | Accept / monitor
Risk | No active CWAR record | All Projects: Status = Ongoing and Parent Project ID not found in active CWAR rows | Prob 3 | Mitigate
Both | Impact scale (from value incl. VAT) | ≥100M = 5 · 50–100M = 4 · 20–50M = 3 · 5–20M = 2 · <5M = 1
Both | Scope | Active CWAR = Current Status ∈ {Active, Substantial Complete, LOA, Hold, Open}. Portfolio excludes Completed, Closed, Merged, Terminated.