## Procurement
[10 empty] | Plan | [5 empty] | Plan | Forcast | Actual
Sr. NO. | Project ID | ACT#inP6 | Item Description | Discipline | (Long \Short) Lead Items | BOQ. No. | Unit | Quantity | Proc. Qty | Required P.O Date | Date of Pur. Order Issued | Purchase Order No. | Supplier | Supplier Phone | Method of Shipping | Required on Job | E.D.A. to Site | A.D.A. to Site | Lead Time | Approval Status | Completion Rate | The Impact (BOQ Cost) | Remarks
1 | MLTX-02-004 | ______________ | AAC panels | Architectural | Long Lead | 3.4 | m² | 680.43 | 748.473 |  | 2026-04-27 | HQ01-PO-26-0015 | ESPAC | 592880434 | Local | 2026-04-20 |  |  | Long Lead | Approved |  |  | Delivered Of Site |  |  | 1
2 | MLTX-02-004 | _____________ | Structural Glass | Architectural | short Lead | 8.2.1 | Sets | 3 | 3 |  | 2026-04-28 | HQ01-PO-26-0221 | Dreametal | 538882626 | Local | 2026-07-05 |  |  | short Lead | Approved |  |  | PO Issued |  |  | 1
3 | MLTX-02-004 | _____________ | Frosted glass partition + door ( 12 mm thk. ) | Architectural | short Lead | 9.2.9 | m² | 18.72 | 20.592 |  | 2026-04-28 | HQ01-PO-26-0221 | Dreametal | 538882626 | Local | 2026-07-05 |  |  | short Lead | Approved |  |  | PO Issued |  |  | 1
4 | MLTX-02-004 | _____________ | CNC aluminum cladding plates ( 3mm thk. ) | Architectural | short Lead | 9.2.7 | item | 1 | 1 |  | 2026-04-28 | HQ01-PO-26-0221 | Dreametal | 538882626 | Local | 2026-07-05 |  |  | short Lead | Approved |  |  | PO Issued |  |  | 1
5 | MLTX-02-004 | _____________ | Anti slip ceramic ( floor 60*60 & 30*30 ) | Architectural | short Lead | 9.1.1.1 9.1.1.2 | m² | 178.77 | 196.647 |  | 2026-04-19 | PR. 4 | Saudi Ceramics | +966 2 001 1124 | Local | 2026-06-29 |  |  | short Lead |  |  |  | Delivered Of Site |  |  | 1
6 | MLTX-02-004 | _____________ | Anti slip ceramic ( wall 30*30 ) | Architectural | short Lead | 9.2.1 | m² | 355.68 | 391.248 |  | 2026-04-19 | PR. 4 | Saudi Ceramics | +966 2 001 1124 | Local | 2026-06-29 |  |  | short Lead | [6 empty] | 1
7 | MLTX-02-004 | _____________ | Anti slip ceramic ( skirting 60*100*10 ) | Architectural | short Lead | 9.1.2.1 | L.M | 27.72 | 30.492 |  | 2026-04-19 | PR. 4 | Saudi Ceramics | +966 2 001 1124 | Local | 2026-06-29 |  |  | short Lead |  |  |  | Delivered Of Site |  |  | 1
8 | MLTX-02-004 | _____________ | Artificial Marble (Corian) | Architectural | short Lead | 15.3.8.5 | Nos. | 3 | 3.3 |  |  |  | AFIFI |  | Local | 2026-06-29 |  |  | short Lead |  |  |  |  | Delay |  | 1
9 | MLTX-02-004 | _____________ | Granite ( floor , treshold , coping ) | Architectural | short Lead | 9.1.1.3 9.2.10 | m² | 121.8 | 133.98 |  | 2026-04-19 | PR. 4 | Saudi Ceramics | +966 2 001 1124 | Local | 2026-06-29 |  |  | short Lead |  |  |  | Delivered Of Site |  |  | 1
10 | MLTX-02-004 | _____________ | Acrylic paint (walls , ceilings , elevations) | Architectural | short Lead | 9.2.3 9.2.4 9.3.3 | m² | 685 | 753.5 |  | 2026-04-16 | PR. 2 | Jazeera Paints | +966 2 000 0085 | Local | 2026-07-12 |  |  | short Lead | Approved | [5 empty] | 1
11 | MLTX-02-004 | _____________ | Decorative profile paint | Architectural | short Lead | 9.2.6 | item | 3 | 3 |  | 2026-04-16 | PR. 2 | Jazeera Paints | +966 2 000 0085 | Local | 2026-07-12 |  |  | short Lead | Approved |  |  | PO Issued |  |  | 1
12 | MLTX-02-004 | _____________ | Epoxy paint { (sport flooring (pike & walking paths )} | Architectural | short Lead | 9.1.1.4 | m² | 16.56 | 18.216 |  | 2026-05-10 | HQ01-SCC-CND-0027 | First Roshin | 966539293693 | Local | 2026-07-12 |  |  | short Lead | Approved | [5 empty] | 1
13 | MLTX-02-004 | _____________ | Stone cladding 300*600 | Architectural | short Lead | 9.2.5 | m² | 140 | 168 | [5 empty] | Local | 2026-07-25 |  |  | short Lead |  |  |  | PO Issued | Delay |  | 1
14 | MLTX-02-004 | Suspend Ceiling | Gypsum board ( RG. & MR. ) 12.5 LL THK. | Architectural | short Lead | 9.3.1 9.3.2 | m² | 164.4 | 180.84 |  | 2026-04-15 | PR. 1 | MADA | +966 4 325 2411 | Local | 2026-07-12 |  |  | short Lead |  |  |  | PO Issued |  |  | 1
15 | MLTX-02-004 | _____________ | PHENOLIC TOILETS PARTITION & PHENOLIC LOCKER | Architectural | short Lead | 9.2.8 10.1.2.1 10.1.2.2 | m² | 120.96 + 3 Item | 139.104 + 3Item |  | 10-May-26 | HQ01-SCC-CND-0030 | Perfect Doors | 550840114 | Local | 2026-06-29 |  |  | short Lead |  |  |  | Delivered Of Site |  | تحويل عتد م.اسلام عبدالسميع | 1
16 | MLTX-02-004 | Grass/Trees | Trees (Cassia Glauca+Plumeria Alba+Neem) | Architectural | Long Lead | 2.3.4.1 | Nos. | 850 | 850 |  | 17-May-26 | HQ01-SCC-CND-26-0027 | Sana Al-Andalus | +966 56 006 6003 | Local | 2026-09-18 |  |  | Long Lead | [6 empty] | 1
17 | MLTX-02-004 | _____________ | Ground Covers -Lawn | Architectural | short Lead | 2.3.4.2.1 | m2 | 13600 | 14000 |  | 17-May-26 | HQ01-SCC-CND-26-0027 | Sana Al-Andalus | +966 56 006 6003 | Local | 2026-06-07 |  |  | short Lead | [6 empty] | 1
18 | MLTX-02-004 | Padel Glass | padel playground fence - Glass | Architectural | Long Lead | 2.3.7 | Item | 3 | 3 |  | 2026-05-10 | HQ01-SCC-CND-0027 | First Roshin | 966539293693 | Local | 2026-05-08 |  |  | Long Lead | Approved |  |  | PO Issued |  |  | 1
19 | MLTX-02-004 | _________________ | Damproofinig paint | Architectural | Short Lead | 7.3 | m² | 146.7 | 150 |  | 2026-04-30 | PR.15 | Awazel | +966 2 660 1740 | Local | 2026-05-25 |  |  | Short Lead |  |  |  | PO Issued |  |  | 1
20 | MLTX-02-004 | _________________ | 4mm thick layer APP modified bituminous membrane | Architectural | Short Lead | 7.5 | m² | 236.16 | 300 |  | 2026-04-30 | PR.15 | Awazel | +966 2 660 1740 | Local | 2026-05-12 |  |  | Short Lead | Approved | 30% |  |  |  |  | 1
21 | MLTX-02-004 | _____________ | Geotextile sheet | Architectural | Short Lead | _______ | _____ | _____ | _____ |  | 2026-04-30 | PR.15 | Awazel | +966 2 660 1740 | Local | 2026-05-12 |  |  | Short Lead |  |  |  | PO Issued |  | تحويل عتد م.اسلام عبدالسميع | 1
22 | MLTX-02-004 | _____________ | 50 mm thk rigid insulation (extruded polystyrene XPS) Density 35 kg/m3 | Architectural | Short Lead | 7.4.4 | m² | 211.41 | 232.551 |  | 2026-04-30 | PR.15 | Awazel | +966 2 660 1740 | Local | 2026-05-12 |  |  | Short Lead | [6 empty] | 1
23 | MLTX-02-004 | _____________ | Water proofing system | Architectural | Short Lead | 7.4.1 7.4.2 7.4.5 7.4.6 | m² | 211.41 | 232.551 |  | 2026-04-30 | PR.15 | Awazel | +966 2 660 1740 | Local | 2026-05-12 |  |  | Short Lead |  |  |  | PO Issued |  | تحويل عتد م.اسلام عبدالسميع | 1
24 | MLTX-02-004 | _____________ | epoxy 2 coating | Architectural | Short Lead | 7.6 | m² | 172 | 200 |  | 2026-04-30 | PR.15 | Awazel | +966 2 660 1740 | Local | 2026-05-12 |  |  | Short Lead | [5 empty] | تحويل عتد م.اسلام عبدالسميع | 1
25 | MLTX-02-004 | _____________ | Precast conc. Seats ( rect. & circle ) | Architectural | Long Lead | 2.3.10.1 2.3.10.2 2.3.10.3 | Nos. | 201 | 241.2 |  | 2026-04-23 | PR.8 | Al-Hasaniah |  | Local | 2026-07-03 |  |  | Long Lead |  |  |  | PO Issued |  | تحويل عتد م.اسلام عبدالسميع | 1
26 | MLTX-02-004 | _____________ | Precast connc. Trash pin | Architectural | Long Lead | 2.3.10.4 | Nos. | 38 | 38 |  | 2026-04-23 | PR.8 | Al-Hasaniah |  | Local | 2026-07-03 |  |  | Long Lead |  |  |  | Delivered Of Site |  | تحويل عتد م.اسلام عبدالسميع | 1
27 | MLTX-02-004 | _____________ | Air dome ( Full system )2 | Architectural | Long Lead | 2.3.9 | Item | 3 | 3 |  |  |  | Global Sport Gate | 551707700 | Local | 2026-06-23 |  |  | Long Lead |  |  |  | Delivered Of Site | Delay | تحويل عتد م.اسلام عبدالسميع | 1
28 | MLTX-02-004 | Interlocking Block Pavers | Curbstone & Interlock -01 | Architectural | Short Lead | 2.2.1 2.3.1.1 2.3.2 | m² L.M | 1994.57 17350.00 | 2194 19085 |  | 29-4-2026 | HQ01-PO-26-010 | 33564116.5 | 598283830 | Local | 2026-07-02 |  |  | Short Lead | Approved |  |  | Delivered Of Site |  | تحويل عتد م.اسلام عبدالسميع | 1
29 | MLTX-02-004 | Interlocking Block Pavers | Curbstone & Interlock -02 | Architectural | Short Lead | 2.2.1 2.3.1.1 2.3.2 | m² L.M | 1994.57 17350.00 | 2194 19085 |  | 22-4-2026 | HQ01-PO-CND-9-26-04-20 | AL_taj | 555103330 | Local | 2026-07-02 |  |  | Short Lead | Approved |  |  | PO Issued |  |  | 1
30 | MLTX-02-004 | Interlocking Block Pavers | Curbstone & Interlock -03 | Architectural | Short Lead | 2.2.1 2.3.1.1 2.3.2 | m² L.M | 1994.57 17350.00 | 2194 19085 |  | 22-4-2026 | HQ01-PO-CND-11-26-04-20 | Bin OTOT | 507738308 | Local | 2026-06-14 |  |  | Short Lead | Approved | [5 empty] | 1
31 | MLTX-02-004 | _____________ | galvanized block ladder mesh | Civil | Short Lead | 4.1.1 | Item | 3 | 3 |  | 2026-05-02 | PR. 19 | Unitech | +966 2 627 8222 | Local | 2026-04-29 |  |  | Short Lead |  |  |  | Delivered Of Site |  |  | 1
32 | MLTX-02-004 | _____________ | galvanized block angle | Civil | Short Lead | 4.1.1 | Item | 3 | 3 |  | 2026-05-02 | PR. 19 | Unitech | +966 2 627 8222 | Local | 2026-04-29 |  |  | Short Lead |  |  |  | Delivered Of Site |  |  | 1
33 | MLTX-02-004 | _____________ | Plastering Accessories | Civil | Short Lead | 9.2.2 | Item | 3 | 3 |  | 2026-05-02 | PR. 19 | Unitech | +966 2 627 8222 | Local | 2026-04-29 |  |  | Short Lead |  |  |  | PO Issued |  |  | 1
34 | MLTX-02-004 | _____________ | Metal doors | Civil | Short Lead | 8 | Nos. | 3 | 3 |  |  |  | Anfal | 545969350 | Local | 2026-05-31 |  |  | Short Lead |  |  |  | PO Issued | Delay |  | 1
35 | MLTX-02-004 | Aggregate Base Course | CRUSHERS ( backfilling materials )1 | Civil | short Lead | 2.1.2 | m³ | 3068.6667 | 3375.5333 |  | 26-4-2026 | HQ01-PO-26-001 | Alazm uniited company |  | Local | 2026-05-31 |  |  | short Lead | Approved | [5 empty] | 1
36 | MLTX-02-004 | Aggregate Base Course | CRUSHERS ( backfilling materials )2 | Civil | short Lead | 2.1.2 | m³ | 3068.6667 | 3375.5333 |  | 22-4-2026 | HQ7-PO01-26-04-20 | EEAC |  | Local | 2026-05-31 |  |  | short Lead | Approved |  |  | Delivered Of Site |  |  | 1
37 | MLTX-02-004 | Aggregate Base Course | CRUSHERS ( backfilling materials )3 | Civil | short Lead | 2.1.2 | m³ | 3068.6667 | 3375.5333 |  | 22-4-2026 | HQ10-26-04-20CND-PO01- | Star Towers Contracting Company |  | Local | 2026-05-31 |  |  | short Lead | Approved | [5 empty] | 1
38 | MLTX-02-004 | _____________ | polyethylene sheet | Civil | Short Lead | 7.1 7.4.3 | m² | 499.29 | 500 |  | 29-4-2026 | PR. 14 | Unitech | +966 2 627 8222 | Local | 2026-07-12 | 2026-06-02 | 2026-06-02 | Short Lead | Approved | 100% |  | Delivered Of Site |  | تحويل عند م اسلام عبدالسميع | 1
39 | MLTX-02-004 | _____________ | Anti termite | Civil | Short Lead | 7.2 | m² | 287.88 | 300 |  | 27-4-2026 | PR.12 | Trap kill | +966 56 657 7862 | Local | 2026-05-15 | 2026-06-03 | 2026-06-03 | Short Lead | Approved | 30% |  |  |  |  | 1
40 | MLTX-02-004 | Concrete Blocks | 01- Concrete & Masonry block for walls 10 cm | Civil | Short Lead | 3 4.1.1 | m3 m² | 843.37 176.53 | 900 180 |  | 19-4-2026 | HQ01-PO-CND 4 -26-04-18 | Rhino | 597224822 | Local | 2026-04-23 |  |  | Short Lead | Approved |  |  | Delivered Of Site |  |  | 1
41 | MLTX-02-004 | Concrete Blocks | 02 -Concrete & Masonry block for walls 10 cm | Civil | Short Lead | 3 4.1.1 | m3 m² | 843.37 176.53 | 900 180 |  | 22-4-2026 | HQ01-PO-CND-9-26-04-20 | Al Taj | 555103330 | Local | 2026-04-23 |  |  | Short Lead | Approved | [5 empty] | 1
42 | MLTX-02-004 | Concrete Blocks | 03- Concrete & Masonry block for walls 10 cm | Civil | Short Lead | 3 4.1.1 | m3 m² | 843.37 176.53 | 900 180 |  | 24-4-2026 | HQ01-PO-CND-11-26-04-20 | Bin OTOT | 507738308 | Local | 2026-04-23 |  |  | Short Lead | Approved |  |  | Delivered Ongoing |  |  | 1
43 | MLTX-02-004 | Steel Reincement | Reinforcement Steel 1 | Civil | Short Lead | 43.5 | Ton | 30 | 22.5 |  | 2026-04-20 | PR.5 | ALRAJHI | 542264279 | Local | 2026-05-12 | 25-05-2026 | 25-05-2026 | Short Lead | Approved | 75% |  | Delivered Ongoing |  |  | 1
44 | MLTX-02-004 | Steel Reincement | Reinforcement Steel 2 | Civil | Short Lead | 43.5 | Ton | __ | __ |  |  |  | AL-ITTEFAQ |  | Local | 2026-05-12 |  |  | Short Lead |  |  |  |  | Delay |  | 1
45 | MLTX-02-004 | Pavement Markings | Road markings | Civil | Short Lead | 2.2.5 | Lot | 3 |  |  |  |  | SHAWAHID | 541767351 | Local | 2026-06-21 |  |  | Short Lead | [6 empty] | 1
46 | MLTX-02-004 | Traffic Signs | Aluminum traffic breakaway signs | Civil | Short Lead | 2.3.3.1 | Nos. | 6 |  |  |  |  | SHAWAHID | 541767351 | Local | 2026-09-24 |  |  | Short Lead | [6 empty] | 1
47 | MLTX-02-004 | Track Surface Artificial TURF | Tartan floors system (EPDM Granules + Polyurethane ) & Playground Flooring & Asphalt | Civil | Short Lead | 2.3.1.2 2.3.1.3 2.3.1.5 2.3.1.6 2.3.5 | m2 | 11874.26 |  |  | 2026-05-10 | HQ01-SCC-CND-0027 | First Roshin | 966539293693 | Local | 2026-06-07 |  |  | Short Lead | Approved |  |  | PO Issued |  |  | 1
48 | MLTX-02-004 | _____________ | Steel ladder with safety cage | Civil | Short Lead | 5.1 | Nos. | 3 |  |  |  |  | Judff |  | Local | 2026-07-31 |  |  | Short Lead | [6 empty] | 1
49 | MLTX-02-004 |  | Low Voltage Cable -Wiring | Electrical | Long Lead | 16.9 | _____ | _____ |  |  |  |  | Bahra Electric | 920011127 | Local |  |  |  | Long Lead | [6 empty] | 1
50 | MLTX-02-004 | Cables - Landscape | Low Voltage Cable -600/1000volt | Electrical | Long Lead | _______ | _____ | _____ |  |  |  |  | Jeddah Cable Company | +966 055 289 3405 | Local | 2026-07-31 |  |  | Long Lead | [6 empty] | 1
51 | MLTX-02-004 | _____________ | BACK & JUNCTION BOXES | Electrical | Short Lead | _______ | _____ | _____ | _____ |  | 24-05-2026 | PO-Ele-01 | ALFANAR | 800-124-1333 | Local | 2026-07-01 | 2026-06-08 | 2026-06-08 | Short Lead | Approved | 40% |  | Delivered Ongoing |  |  | 1
52 | MLTX-02-004 | _____________ | CONDUITS & FITTINGS & Accessories for PVC | Electrical | Short Lead | _______ | _____ | _____ |  |  | 24-05-2026 | PR-Ele-01 | Khereiji Showrooms Company (MK ) | +966 56 686 6706 | Local | 2026-07-01 | 2026-06-08 | 2026-06-21 | Short Lead | Approved | 10% |  | Delivered Ongoing |  |  | 1
53 | MLTX-02-004 | _____________ | EMT/RSC CONDUITS – LIQUDTIGHT FLEXIBLE CONDUIT- METAL FLEXIBLE CONDUIT | Electrical | Short Lead | _______ | _____ | _____ |  |  | 24-05-2026 | PO-Ele-01 | ITCC | +966 12 288 9198 | Local | 2026-07-01 | 2026-06-08 | 2026-06-08 | Short Lead | Approved | 10% |  | Delivered Ongoing |  |  | 1
54 | MLTX-02-004 | Earthing System | GROUNDING/ LIGHTNING PROTECTION SYSTEM | Electrical | Short Lead | 16.6 16.7 | Nos. | 12 | 6 |  | 24-05-2026 | PO-Ele-01 | Jeddah Cable Company | +966 56 686 6706 | Local | 2026-05-12 | 2026-06-08 | 2026-06-08 | Short Lead | Approved | 25% |  | Delivered Ongoing |  |  | 1
55 | MLTX-02-004 | Switches/Sockets - Toilet wer Outlets/Switches - Playground | WIRING DEVICES | Electrical | Short Lead | 16.9 | Nos. | 66 |  |  |  |  | Khereiji Showrooms Company (MK) | +966 56 686 6706 | Local |  |  |  | Short Lead |  |  |  |  | Delay |  | 1
56 | MLTX-02-004 | ____________ | Disconnect switch | Electrical | Short Lead | 16.9.10 | Nos. | 3 |  |  |  |  | ABB | +966 92 001 0301 | Local | 2026-07-31 |  |  | Short Lead |  |  |  |  | Delay | Material Submite 2-10-2025 | 1
57 | MLTX-02-004 | Distribution Panels - Toilet Distribution Boards - Playground | LV PANEL BOARDS | Electrical | Short Lead | 16.1 | Nos. | 8 |  |  |  |  | Al-Babtain Power | +966 11 250 6900 | Local |  |  |  | Short Lead |  |  |  |  | Delay | Material Submite 2-10-2025 | 1
58 | MLTX-02-004 | Light Fixtures - playground | Roadway/ street lights – Lighting Poles | Electrical | Short Lead | 16.2 | Nos. | 322 | 322 |  | 2026-06-03 | PO2026-283 | Al-Babtain Power | +966 11 250 6900 | Local | 2026-07-07 |  |  | Short Lead |  |  |  | Delivered Of Site |  |  | 1
59 | MLTX-02-004 | Lighting Fixtures- toilet | Interior Lighting | Electrical | Short Lead | 16.3 | Nos. | 144 |  |  |  |  | Nassli led Lights | +966 59 406 6470 | Local | 2026-06-25 |  |  | Short Lead |  |  |  |  | Delay |  | 1
60 | MLTX-02-004 | _____________ | Fire Alarm System | Electrical | Short Lead | 16.8 | Nos. | 45 |  |  |  |  | Gent | 966112650555 | Local | 2026-08-20 |  |  | Short Lead |  |  |  |  | Delay |  | 1
61 | MLTX-02-004 | _____________ | Telecommunications & Data System | Electrical | Short Lead | 16.4 | Nos. | 27 |  |  |  |  | Mesc | 96611434711 | Local | 2026-08-20 |  |  | Short Lead |  |  |  |  | Delay |  | 1
62 | MLTX-02-004 | CCTV | Security and Access Control System - CCTV | Electrical | Short Lead | 16.5 | Nos. | 42 | [6 empty] | Local | 2026-07-12 |  |  | Short Lead |  |  |  |  | Delay |  | 1
63 | MLTX-02-004 | Sewage/Drainage Pipes | UPVC Pipes | Mechanical | Short Lead | 15.3.1 15.3.7 | Lm | 454 | 460 |  | 21-05-2026 | PR 26 | AL MUNIF | +966 2 000 0357 | Local | 2026-04-16 | 2026-06-05 | 2026-06-05 | Short Lead | Approved | 100% |  | Delivered Of Site |  |  | 1
64 | MLTX-02-004 | AC Split - Toilet | Split Type Air Conditioner | Mechanical | Short Lead | 15.4.5 | Nos. | 3 | 3 |  | 2026-04-06 | Profast-PO2026-286 | ZAMIL | +966 2 234 3630 | Local | 2026-06-19 |  |  | Short Lead |  |  |  | PO Issued |  |  | 1
65 | MLTX-02-004 | _____________ | Fire Extinguisher | Mechanical | Short Lead | 15.1 | Nos. | 6 |  |  | 2026-06-28 | PR 31 | SFFECO | +966 12 670 6009 | Local | 2026-08-18 |  |  | Short Lead |  |  |  | PO Issued |  |  | 1
66 | MLTX-02-004 | Sanitary Fixtures | Sanitary Fixtures ( water heater , soap dispenser , tissue holder , mirrors , grap bar , mixer & tissue dispenser , WC , lav. ….. ) | Mechanical | Short Lead | 15.3.3 15.3.4 15.3.8 | Nos. | 3 | 3 |  | 2026-06-07 | PR 26 | Saudi Ceramics | +966 2 001 1124 | Local | 2026-06-13 |  |  | Short Lead |  |  |  | PO Issued |  |  | 1
67 | MLTX-02-004 | Irrigation Pipes/Sprinkles | Land scape & i irrigation system materials (main and sub-main irrigation pipelines, fittings, valve boxes and sprinklers) | Mechanical | Long Lead | 15.4.1.9 15.5.3 | Item | 3 | 3 |  | 17-05-2026 | HQ01-SCC-CND-26-0027 | Sana Al-Andalus | +966 56 006 6003 | Local | 2026-07-31 |  |  | Long Lead |  |  |  | PO Issued |  |  | 1
68 | MLTX-02-004 | Exhaust Fans | Inline Exhaust Fans | Mechanical | Short Lead | 15.4.1 | Nos. | 18 | 20 |  | 18-05-2026 | PR 27 | Saudi Fan | +966 2 283 2295 | Local | 2026-06-19 |  |  | Short Lead |  |  |  | PO Issued |  |  | 1
69 | MLTX-02-004 | _____________ | HDPE PIPES & FITTINGS | Mechanical | Short Lead | 15.2.2 | m | 300 | 300 |  | 28-06-2026 | PR 33 | AL MUNIF | +966 2 000 0357 | Local | 2026-08-18 |  |  | Short Lead |  |  |  | PO Issued |  |  | 1
70 | MLTX-02-004 | Water Supply Pipes | PPR PIPES & FITTINGS | Mechanical | Short Lead | 15.2.1 | Lm | 256.5 | 285 |  | 2026-09-06 | PR 30 | AL MUNIF | +966 2 000 0357 | Local | 2026-06-04 | 13-06-2026 | 13-06-2026 | Short Lead | Approved | 100% |  | Delivered Of Site |  |  | 1
71 | MLTX-02-004 | Exhaust Fans | Square Exhaust Diffuser | Mechanical | Short Lead | 14.4.2.1 | Nos. | 18 |  |  | 2026-06-03 | Profast-PO2026-280 | Rabie Al Takyeef | +966 59 255 5240 | Local | 2026-06-19 |  |  | Short Lead | [6 empty] | 1
72 | MLTX-02-004 | _____________ | Copper Pipe for AC | Mechanical | Short Lead | _______ | Nos. | 3 |  |  |  |  | Al-Sayed Center A/C | +966 2 261 6246 | Local | 2026-06-19 |  |  | Short Lead |  |  |  |  | Delay |  | 1
73 | MLTX-02-004 | _____________ | Copper Pipe Insulation | Mechanical | Short Lead | _______ | Nos. | 3 |  |  |  |  | KIMMCO-ISOVER | +966 3 847 1450 | Local | 2026-06-19 |  |  | Short Lead |  |  |  |  | Delay |  | 1
74 | MLTX-02-004 | _____________ | Valves, check valves strainers and air vent | Mechanical | Long Lead | _______ | Nos. | 43 | 43 |  | 2026-06-30 | PR 37 | ZAMIL | +966 2 234 3630 | Local | 2026-09-18 |  |  | Long Lead |  |  |  | PO Issued |  |  | 1
75 | MLTX-02-004 | _____________ | Afico Insulation | Mechanical | Short Lead | _______ | Nos. | 3 |  |  |  |  | Afico | +966 3 331 3333 | Local | 2026-06-23 |  |  | Short Lead |  |  |  |  | Delay |  | 1
76 | MLTX-02-004 | _____________ | Water Supply Booster Pumps | Mechanical | Long Lead | 15.2.3 | Set | 2 | 2 |  | 17-05-2026 | HQ01-SCC-CND-26-0027 | KSB | +966 1 227 7060 | Local | 2026-08-18 |  |  | Long Lead |  |  |  | PO Issued |  |  | 1
77 | MLTX-02-004 | _____________ | Roof Drain & Steel roof scupper | Mechanical | Short Lead | 5.2 | Nos. | 3 | 3 |  | 4/25/2026 6/28/2026 | PR.10 PR.31 | Saudi Cast | +966 1 448 0107 | Local | 2026-07-31 |  |  | Short Lead |  |  |  | PO Issued |  |  | 1
78 | MLTX-02-004 | _____________ | Hot Press GRP Sectional Panel Water Tanks | Mechanical | Long Lead | 15.2.4.1 | Set | 2 | 2 |  | 2026-07-05 | PROFAST-PO-2026-277 | AL-MUHAIDEB | +966 92 002 8545 | Local | 2026-06-23 |  |  | Long Lead |  |  |  | PO Issued |  |  | 1
79 | MLTX-02-004 | Galvanized Duct | ductwork as per SMACNA Standards | Mechanical | Short Lead | 15.4.3 | K G | 183 |  |  |  |  | Rabie Al Takyeef | +966 59 255 5240 | Local | 2026-06-23 |  |  | Short Lead | [6 empty] | 1
80 | MLTX-02-004 | _____________ | Manhole Cover | Mechanical | Short Lead | 15.3.5 15.3.6 | Nos. | 6 | 6 |  | 2026-06-28 | PR.43 | Judff |  | Local | 2026-08-18 |  |  | Short Lead |  |  |  | PO Issued
Y

## Sheet1
Sr. NO. | Location | Submittal Reference | Submission Date | Approval Date | Status | Item Description | Discipline | (Long \Short) Lead Items | Quantity | Proc. Qty | Date of Pur. Order Issued | Purchase Order No. | Supplier | Supplier | Remarks
|  |  | (Last Revision) | [10 empty] | Phone
1 | All Sites | MLTX-02-004-PRO-TS9-1-ARC-MAC-0001-00 | 2026-04-15 | 2026-04-15 | B | AAC panels | Architectural | Long Lead | 680.43 | 748.47 | 2026-04-27 | HQ01-PO-26-0015 | ESPAC | 592880434 | Delivered Of Site
2 | All Sites | MLTX-02-004-PRO-TS9-1-ARC-MAC-0002-00 | 2026-04-26 | 2026-04-26 | A | Structural Glass | Architectural | short Lead | 3 | 3 | 2026-04-28 | HQ01-PO-26-0221 | Alutal | 538882626 | PO Issued
3 | All Sites | MLTX-02-004-PRO-TS9-1-ARC-MAC-0002-00 | 2026-04-26 | 2026-04-26 | A | Frosted glass partition + door ( 12 mm thk. ) | Architectural | short Lead | 18.72 | 20.59 | 2026-04-28 | HQ01-PO-26-0221 | Alutal | 538882626 | PO Issued
4 | Jeddah | MLTX-02-004-PRO-TS9-1-ARC-MAC-0002-00 | 2026-04-26 | 2026-04-26 | A | CNC aluminum cladding plates ( 3mm thk. ) | Architectural | short Lead | 1 | 1 | 2026-04-28 | HQ01-PO-26-0221 | Alutal | 538882626 | PO Issued
5 | All Sites | MLTX-02-004-PRO-TS9-1-ARC-MAC-0005-01 | 2026-06-16 | 29-Jul-26 | B | Anti slip ceramic ( floor 60*60 & 30*30 ) | Architectural | short Lead | 178.77 | 196.65 | 2026-04-19 | PR. 4 | Saudi Ceramics | +966 2 001 1124 | Delivered Of Site
6 | All Sites | MLTX-02-004-PRO-TS9-1-ARC-MAC-0005-01 | 2026-06-16 | 29-Jul-26 | B | Anti slip ceramic ( wall 30*30 ) | Architectural | short Lead | 355.68 | 391.25 | 2026-04-19 | PR. 4 | Saudi Ceramics | +966 2 001 1124 | Delivered Of Site
7 | All Sites | MLTX-02-004-PRO-TS9-1-ARC-MAC-0005-01 | 2026-06-16 | 29-Jul-26 | B | Anti slip ceramic ( skirting 60*100*10 ) | Architectural | short Lead | 27.72 | 30.49 | 2026-04-19 | PR. 4 | Saudi Ceramics | +966 2 001 1124 | Delivered Of Site
8 | All Sites | MLTX-02-004-PRO-TS9-1-ARC-MAC-0008-00 | 2026-04-26 | 2026-04-26 | B | Artificial Marble (Corian) | Architectural | short Lead | 3 | 3.3 |  |  | Forst elfan | 0594306000 | PO Issued
9 | All Sites | MLTX-02-004-PRO-TS9-1-ARC-MAC-0005-01 | 2026-06-16 |  | B | Granite ( floor , treshold , coping ) | Architectural | short Lead | 121.8 | 133.98 | 2026-04-19 | PR. 4 | Saudi Ceramics | +966 2 001 1124
10 | All Sites | MLTX-02-004-PRO-TS9-1-ARC-MAC-0006-00 | 2026-04-18 | 2026-04-19 | B | Acrylic paint (walls , ceilings , elevations) | Architectural | short Lead | 685 | 753.5 | 2026-04-16 | PR. 2 | Jazeera Paints | +966 2 000 0085 | PO Issued
11 | All Sites | MLTX-02-004-PRO-TS9-1-ARC-MAC-0006-00 | 2026-04-18 | 2026-04-19 | B | Decorative profile paint | Architectural | short Lead | 3 | 3 | 2026-04-16 | PR. 2 | Jazeera Paints | +966 2 000 0085 | PO Issued
12 | All Sites | MLTX-02-004-PRO-TS9-1-CVL-MAC-0009-01 | 2026-06-13 | 2026-06-30 | B | Epoxy paint { (sport flooring (pike & walking paths )} | Architectural | short Lead | 16.56 | 18.22 | 2026-05-10 | HQ01-SCC-CND-0027 | First Roshin | 966539293693 | Delivered Of Site
13 | All Sites |  |  |  |  | Stone cladding 300*600 | Architectural | short Lead | 140 | 168
14 | All Sites | MLTX-02-004-PRO-TS9-1-ARC-MAC-0003-01 | 2026-04-19 | 2026-04-20 | B | Gypsum board ( RG. & MR. ) 12.5 LL THK. | Architectural | short Lead | 164.4 | 180.84 | 2026-04-15 | PR. 1 | MADA | +966 4 325 2411 | PO Issued
15 | All Sites | MLTX-02-004-PRO-TS9-1-ARC-MAC-0007-00 | 2026-04-19 | 2026-04-20 | B | PHENOLIC TOILETS PARTITION & PHENOLIC LOCKER | Architectural | short Lead | 120.96 | 139.104 | 10-May-26 | HQ01-SCC-CND-0030 | Perfect Doors | 550840114 | PO Issued
[9 empty] | + 3 Item | + 3Item
16 | All Sites | MLTX-02-004-PRO-TS9-1-MEC-MAC-0005-00 | 2026-04-18 | 2026-06-06 | B | Trees | Architectural | Long Lead | 850 | 850 | 17-May-26 | HQ01-SCC-CND-26-0027 | Sana Al-Andalus | +966 56 006 6003 | PO Issued
(Cassia Glauca+Plumeria Alba+Neem)
17 | All Sites | MLTX-02-004-PRO-TS9-1-MEC-MAC-0005-00 | 2026-04-18 | 2026-06-06 | B | Ground Covers -Lawn | Architectural | short Lead | 13600 | 14000 | 17-May-26 | HQ01-SCC-CND-26-0027 | Sana Al-Andalus | +966 56 006 6003 | PO Issued
18 | All Sites | MLTX-02-004-PRO-TS9-1-CVL-MAC-0009-01 | 2026-06-13 | 2026-06-30 | B | padel playground fence - Glass | Architectural | Long Lead | 3 | 3 | 2026-05-10 | HQ01-SCC-CND-0027 | First Roshin | 966539293693 | PO Issued
19 | All Sites | MLTX-02-004-PRO-TS9-1-ARC-MAC-0004-00 | 2026-04-18 | 2026-04-18 | B | Dam proofinig paint | Architectural | Short Lead | 146.7 | 150 | 2026-04-30 | PR.15 | Awazel | +966 2 660 1740 | Delivered Of Site
20 | All Sites | MLTX-02-004-PRO-TS9-1-ARC-MAC-0004-00 | 2026-04-18 | 2026-04-18 | B | 4mm thick layer APP modified bituminous membrane | Architectural | Short Lead | 236.16 | 300 | 2026-04-30 | PR.15 | Awazel | +966 2 660 1740 | Delivered Of Site
21 | All Sites | MLTX-02-004-PRO-TS9-1-ARC-MAC-0004-00 | 2026-04-18 | 2026-04-18 | B | Geotextile sheet | Architectural | Short Lead | _____ | _____ | 2026-04-30 | PR.15 | Awazel | +966 2 660 1740 | Delivered Of Site
22 | All Sites | MLTX-02-004-PRO-TS9-1-ARC-MAC-0004-00 | 2026-04-18 | 2026-04-18 | B | 50 mm thk rigid insulation (extruded polystyrene XPS) | Architectural | Short Lead | 211.41 | 232.55 | 2026-04-30 | PR.15 | Awazel | +966 2 660 1740 | PO Issued
Density 35 kg/m3
23 | All Sites | MLTX-02-004-PRO-TS9-1-ARC-MAC-0004-00 | 2026-04-18 | 2026-04-18 | B | Water proofing system | Architectural | Short Lead | 211.41 | 232.55 | 2026-04-30 | PR.15 | Awazel | +966 2 660 1740 | Delivered Of Site
24 | All Sites | MLTX-02-004-PRO-TS9-1-ARC-MAC-0004-00 | 2026-04-18 | 2026-04-18 | B | epoxy 2 coating | Architectural | Short Lead | 172 | 200 | 2026-04-30 | PR.15 | Awazel | +966 2 660 1740 | Delivered Of Site
25 | All Sites | MLTX-02-004-PRO-TS9-1-CVL-MAC-0015-00 | 2026-05-14 | 2026-05-16 | B | Precast conc. Seats ( rect. & circle ) | Architectural | Long Lead | 201 | 241.2 | 2026-04-23 | PR.8 | Al-Hasaniah |  | PO Issued
26 | All Sites | MLTX-02-004-PRO-TS9-1-CVL-MAC-0015-00 | 2026-05-14 | 2026-05-16 | B | Precast connc. Trash pin | Architectural | Long Lead | 38 | 38 | 2026-04-23 | PR.8 | Al-Hasaniah |  | PO Issued
27 | All Sites | MLTX-02-004-PRO-TS9-1-CVL-PQA-0015-00 | 2026-04-13 | 2026-04-15 | A | Air dome ( Full system )2 | Architectural | Long Lead | 3 | 3 |  |  | Global Sport Gate | 551707700
28 | jeddah | MLTX-02-004-PRO-TS9-1-ARC-PQA-0007-00 | 2026-04-13 | 2026-04-15 | A | Curbstone & Interlock -01 | Architectural | Short Lead | 1994.57 | 2194 | 2026-04-29 | HQ01-PO-26-010 | 33564116.5 | 598283830 | Delivered Of Site
[9 empty] | 17350 | 19085
29 | jazan | MLTX-02-004-PRO-TS9-1-ARC-PQA-0008-00 | 2026-04-15 | 2026-04-15 | A | Curbstone & Interlock -02 | Architectural | Short Lead | 1994.57 | 2194 | 2026-04-22 | HQ01-PO-CND-9-26-04-20 | AL_taj | 555103330 | Delivered Of Site
[9 empty] | 17350 | 19085
30 | Asir | MLTX-02-004-PRO-TS9-1-ARC-PQA-0009-00 | 2026-04-16 | 2026-04-16 | A | Curbstone & Interlock -03 | Architectural | Short Lead | 1994.57 | 2194 | 2026-04-22 | HQ01-PO-CND-11-26-04-20 | Bin OTOT | 507738308 | Delivered Of Site
[9 empty] | 17350 | 19085

## Sheet2
Sr. NO. | Location | Submittal Reference | Submission Date | Approval Date | Status | Item Description | Discipline | (Long \Short) Lead Items | Quantity | Proc. Qty | Date of Pur. Order Issued | Purchase Order No. | Supplier | Supplier | Remarks
|  |  | (Last Revision) | [10 empty] | Phone
31 | All Sites | MLTX-02-004-PRO-TS9-1-CVL-MAR-0001-00 | 2026-04-14 | 2026-04-15 | B | galvanized block ladder mesh | Civil | Short Lead | 3 | 3 | 2026-05-02 | PR. 19 | Unitech | +966 2 627 8222 | Delivered Of Site
32 | All Sites | MLTX-02-004-PRO-TS9-1-CVL-MAR-0001-00 | 2026-04-14 | 2026-04-15 | B | galvanized block angle | Civil | Short Lead | 3 | 3 | 2026-05-02 | PR. 19 | Unitech | +966 2 627 8222 | Delivered Of Site
33 | All Sites | MLTX-02-004-PRO-TS9-1-CVL-MAR-0001-00 | 2026-04-14 | 2026-04-15 | B | Plastering Accessories | Civil | Short Lead | 3 | 3 | 2026-05-02 | PR. 19 | Unitech | +966 2 627 8222 | Delivered Of Site
34 | All Sites | MLTX-02-004-PRO-TS9-1-ARC-MAC-0009-00 | 2026-05-14 | 2026-05-16 | B | Metal doors | Civil | Short Lead | 3 | 3 |  |  | Anfal | 545969350 | PO Issued
35 | Jeddah | MLTX-02-004-PRO-TS9-1-CVL-PQA-0011-00 | 2026-04-13 | 2026-04-15 | B | CRUSHERS ( backfilling materials )1 | Civil | short Lead | 3068.67 | 3375.53 | 2026-04-26 | HQ01-PO-26-001 | Alazm uniited company |  | Delivered Of Site
36 | Jazan | MLTX-02-004-PRO-TS9-1-CVL-PQA-0011-00 | 2026-04-18 | 2026-04-20 | B | CRUSHERS ( backfilling materials )2 | Civil | short Lead | 3068.67 | 3375.53 | 2026-04-22 | HQ7-PO01-26-04-20 | EEAC |  | Delivered Of Site
37 | Asir | MLTX-02-004-PRO-TS9-1-CVL-PQA-0011-00 | 2026-04-15 | 2026-04-15 | B | CRUSHERS ( backfilling materials )3 | Civil | short Lead | 3068.67 | 3375.53 | 2026-04-22 | HQ10-26-04-20CND-PO01- | Star Towers Contracting Company |  | Delivered Of Site
38 | All Sites | MLTX-02-004-PRO-TS9-1-CVL-MAC-0001-00 | 2026-04-15 | 2026-04-26 | B | polyethylene sheet | Civil | Short Lead | 499.29 | 500 | 2026-04-29 | PR. 14 | Unitech | +966 2 627 8222 | Delivered Of Site
39 | All Sites | MLTX-02-004-PRO-TS9-1-CVL-MAC-0002-00 | 2026-04-16 | 2026-04-18 | A | Anti termite | Civil | Short Lead | 287.88 | 300 | 2026-04-27 | PR.12 | Trap kill | +966 56 657 7862 | Delivered Of Site
40 | Jeddah | MLTX-02-004-PRO-TS9-1-CVL-PQA-003-00 | 2026-04-11 | 2026-04-12 | B | 01- Concrete & Masonry block for walls 10 cm | Civil | Short Lead | 843.37 | 900 | 2026-04-19 | HQ01-PO-CND 4 -26-04-18 | Rhino | 597224822 | Delivered Of Site
[9 empty] | 176.53 | 180
41 | Jazan | MLTX-02-004-PRO-TS9-1-CVL-PQA-003-00 | 2026-04-15 | 2026-04-20 | B | 02 -Concrete & Masonry block for walls 10 cm | Civil | Short Lead | 843.37 | 900 | 2026-04-22 | HQ01-PO-CND-9-26-04-20 | Al Taj | 555103330 | Delivered Of Site
[9 empty] | 176.53 | 180
42 | Asir | MLTX-02-004-PRO-TS9-1-CVL-PQA-003-00 | 2026-04-12 | 2026-04-23 | B | 03- Concrete & Masonry block for walls 10 cm | Civil | Short Lead | 843.37 | 900 | 2026-04-24 | HQ01-PO-CND-11-26-04-20 | Bin OTOT | 507738308 | Delivered Of Site
[9 empty] | 176.53 | 180
43 | All Sites | MLTX-02-004-PRO-TS9-1-CVL-PQA-0004-00 | 2026-04-12 | 2026-04-13 | B | Reinforcement Steel 1 | Civil | Short Lead | 30 | 22.5 | 2026-04-20 | PR.5 | ALRAJHI | 542264279 | Delivered Of Site
44 | All Sites | MLTX-02-004-PRO-TS9-1-CVL-PQA-0008-00 | 2026-04-12 | 2026-04-12 | B | Reinforcement Steel 2 | Civil | Short Lead | __ | __ |  |  | AL-ITTEFAQ |  | Delivered Of Site
45 | All Sites | MLTX-02-004-PRO-TS9-1-CVL-MAC-0014-00 | 2026-05-14 | 2026-05-19 | B | Road markings | Civil | Short Lead | 3 |  |  |  | SHAWAHID | 541767351 | PO Issued
46 | All Sites | MLTX-02-004-PRO-TS9-1-CVL-MAC-0014-00 | 2026-05-14 | 2026-05-19 | B | Aluminum traffic breakaway signs | Civil | Short Lead | 6 |  |  |  | SHAWAHID | 541767351 | PO Issued
47 | All Sites | MLTX-02-004-PRO-TS9-1-CVL-MAC-0009-01 | 2026-06-13 | 2026-06-30 | B | Tartan floors system (EPDM Granules + Polyurethane ) & Playground Flooring & Asphalt | Civil | Short Lead | 11874.26 |  | 2026-05-10 | HQ01-SCC-CND-0027 | First Roshin | 966539293693 | PO Issued
48 | All Sites | MLTX-02-004-PRO-TS9-1-MEC-PQA-0016-00 | 2026-04-15 | 2026-04-19 | B | Steel ladder with safety cage | Civil | Short Lead | 3 |  |  |  | Judff |  | PO Issued

## Sheet3
Sr. NO. | Location | Submittal Reference | Submission Date | Approval Date | Status | Item Description | Discipline | (Long \Short) Lead Items | Quantity | Proc. Qty | Date of Pur. Order Issued | Purchase Order No. | Supplier | Supplier | Remarks
|  |  | (Last Revision) | [10 empty] | Phone
49 | All Sites | MLTX-02-004-PRO-TS9-1-ELE-MAC-0016-00 | 2026-06-07 | 2026-06-14 | B | Low Voltage Cable -Wiring | Electrical | Long Lead | _____ |  |  |  | Bahra Electric | 920011127 | PO ISSUED
50 | All Sites | MLTX-02-004-PRO-TS9-1-ELE-MAC-0001-00 | 2026-04-18 | 2026-04-20 | B | Low Voltage Cable -600/1000volt | Electrical | Long Lead | _____ |  |  |  | Jeddah Cable Company | +966 055 289 3405 | PO ISSUED
51 | All Sites | MLTX-02-004-PRO-TS9-1-ELE-MAC-0002-00 | 2026-04-18 | 2026-04-20 | B | BACK & JUNCTION BOXES | Electrical | Short Lead | _____ | _____ | 2026-05-24 | PO-Ele-01 | ALFANAR | 800-124-1333 | Delivered Ongoing
52 | All Sites | MLTX-02-004-PRO-TS9-1-ELE-MAC-0003-00 | 2026-04-18 | 2026-04-20 | B | CONDUITS & FITTINGS & Accessories for PVC | Electrical | Short Lead | _____ |  | 2026-05-24 | PR-Ele-01 | Khereiji Showrooms Company (MK ) | +966 56 686 6706 | Delivered Ongoing
53 | All Sites | MLTX-02-004-PRO-TS9-1-ELE-MAC-0004-00 | 2026-04-18 | 2026-04-20 | B | EMT/RSC CONDUITS – LIQUDTIGHT FLEXIBLE CONDUIT- METAL FLEXIBLE CONDUIT | Electrical | Short Lead | _____ |  | 2026-05-24 | PO-Ele-01 | ITCC | +966 12 288 9198 | Delivered Ongoing
54 | All Sites | MLTX-02-004-PRO-TS9-1-ELE-MAC-0005-00 | 2026-04-18 | 2026-04-20 | B | GROUNDING/ LIGHTNING PROTECTION SYSTEM | Electrical | Short Lead | 12 | 6 | 2026-05-24 | PO-Ele-01 | Jeddah Cable Company | +966 56 686 6706 | Delivered Ongoing
55 | All Sites | MLTX-02-004-PRO-TS9-1-ELE-MAC-0006-00 | 2026-04-19 | 2026-04-25 | B | WIRING DEVICES | Electrical | Short Lead | 66 |  |  |  | Khereiji Showrooms Company (MK) | +966 56 686 6706 | PO ISSUED
56 | All Sites | MLTX-02-004-PRO-TS9-1-ELE-MAC-0007-00 | 2026-04-19 | 2026-04-25 | B | Disconnect switch | Electrical | Short Lead | 3 |  |  |  | ABB | +966 92 001 0301 | PO ISSUED
57 | All Sites | MLTX-02-004-PRO-TS9-1-ELE-MAC-0008-00 | 2026-04-19 | 2026-04-25 | B | LV PANEL BOARDS | Electrical | Short Lead | 8 |  |  |  | Al-Babtain Power | +966 11 250 6900 | Delivered Of Site
58 | All Sites | MLTX-02-004-PRO-TS9-1-ELE-MAC-0009-00 | 2026-04-20 | 2026-04-25 | B | Roadway/ street lights – Lighting Poles | Electrical | Short Lead | 322 | 322 | 2026-06-03 | PO2026-283 | Al-Babtain Power | +966 11 250 6900 | PO ISSUED
59 | All Sites | MLTX-02-004-PRO-TS9-1-ELE-MAC-0010-00 | 2026-04-20 | 2026-04-25 | B | Interior Lighting | Electrical | Short Lead | 144 |  |  |  | Nassli led Lights | +966 59 406 6470 | PO ISSUED
60 | All Sites | MLTX-02-004-PRO-TS9-1-ELE-MAC-0022-00 | 2026-06-21 | 2026-06-24 | B | Fire Alarm System | Electrical | Short Lead | 45 |  |  |  | Gent | 966112650555 | PO ISSUED
61 | All Sites | MLTX-02-004-PRO-TS9-1-ELE-MAC-0021-00 | 2026-06-17 | 21-Jun-26 | B | Telecommunications & Data System | Electrical | Short Lead | 27 |  |  |  | Mesc | 96611434711 | PO ISSUED
62 | All Sites | MLTX-02-004-PRO-TS9-1-ELE-MAC-0023-00 | 2026-06-27 | 2026-07-05 | B | Security and Access Control System - CCTV | Electrical | Short Lead | 42 | [5 empty] | PO ISSUED

## Sheet4
Sr. NO. | Location | Submittal Reference | Submission Date | Approval Date | Status | Item Description | Discipline | (Long \Short) Lead Items | Quantity | Proc. Qty | Date of Pur. Order Issued | Purchase Order No. | Supplier | Supplier | Remarks
|  |  | (Last Revision) | [10 empty] | Phone
63 | All Sites | MLTX-02-004-PRO-TS9-1-MEC-MAC-0001-00 | 2026-04-15 | 2026-04-16 | B | UPVC Pipes | Mechanical | Short Lead | 454 | 460 | 2026-05-21 | PR 26 | AL MUNIF | +966 2 000 0357 | Delivered Of Site
64 | All Sites | MLTX-02-004-PRO-TS9-1-MEC-MAC-0002-01 | 2026-04-20 | 2026-04-21 | B | Split Type Air Conditioner | Mechanical | Short Lead | 3 | 3 | 2026-04-06 | Profast-PO2026-286 | ZAMIL | +966 2 234 3630 | Delivered Of Site
65 | All Sites | MLTX-02-004-PRO-TS9-1-MEC-MAC-0003-00 | 2026-04-16 | 2026-04-18 | B | Fire Extinguisher | Mechanical | Short Lead | 6 |  | 2026-06-28 | PR 31 | SFFECO | +966 12 670 6009 | PO Issued
66 | All Sites | MLTX-02-004-PRO-TS9-1-MEC-MAC-0004-01 | 2026-04-21 | 2026-04-30 | B | Sanitary Fixtures ( water heater , soap dispenser , tissue holder , mirrors , grap bar , mixer & tissue dispenser , WC , lav. ….. ) | Mechanical | Short Lead | 3 | 3 | 2026-06-07 | PR 26 | Saudi Ceramics | +966 2 001 1124 | Delivered Of Site
67 | All Sites | MLTX-02-004-PRO-TS9-1-MEC-MAC-0005-00 | 2026-04-18 | 2026-06-06 | B | Land scape & i irrigation system materials (main and sub-main irrigation pipelines, fittings, valve boxes and sprinklers) | Mechanical | Long Lead | 3 | 3 | 2026-05-17 | HQ01-SCC-CND-26-0027 | Sana Al-Andalus | +966 56 006 6003 | Delivered Of Site
68 | All Sites | MLTX-02-004-PRO-TS9-1-MEC-MAC-0006-00 | 2026-04-18 | 2026-05-05 | B | Inline Exhaust Fans | Mechanical | Short Lead | 18 | 20 | 2026-05-18 | PR 27 | Saudi Fan | +966 2 283 2295 | Delivered Of Site
69 | All Sites | MLTX-02-004-PRO-TS9-1-MEC-MAC-0007-00 | 2026-04-18 | 2026-05-05 | B | HDPE PIPES & FITTINGS | Mechanical | Short Lead | 300 | 300 | 2026-06-28 | PR 33 | AL MUNIF | +966 2 000 0357 | Delivered Of Site
70 | All Sites | MLTX-02-004-PRO-TS9-1-MEC-MAC-0008-00 | 2026-04-18 | 2026-05-05 | B | PPR PIPES & FITTINGS | Mechanical | Short Lead | 256.5 | 285 | 2026-09-06 | PR 30 | AL MUNIF | +966 2 000 0357 | Delivered Of Site
71 | All Sites | MLTX-02-004-PRO-TS9-1-MEC-MAC-0009-00 | 2026-04-22 | 2026-05-05 | B | Square Exhaust Diffuser | Mechanical | Short Lead | 18 |  | 2026-06-03 | Profast-PO2026-280 | Rabie Al Takyeef | +966 59 255 5240 | Delivered Of Site
72 | All Sites | MLTX-02-004-PRO-TS9-1-MEC-MAC-0010-00 | 2026-04-22 | 2026-04-23 | B | Copper Pipe for AC | Mechanical | Short Lead | 3 |  |  |  | Al-Sayed Center A/C | +966 2 261 6246 | Delivered Of Site
73 | All Sites | MLTX-02-004-PRO-TS9-1-MEC-MAC-0011-00 | 2026-04-22 | 2026-04-23 | B | Copper Pipe Insulation | Mechanical | Short Lead | 3 |  |  |  | KIMMCO-ISOVER | +966 3 847 1450 | Delivered Of Site
74 | All Sites | MLTX-02-004-PRO-TS9-1-MEC-MAC-0012-00 | 2026-04-22 | 2026-04-23 | B | Valves, check valves strainers and air vent | Mechanical | Long Lead | 43 | 43 | 2026-06-30 | PR 37 | ZAMIL | +966 2 234 3630 | Delivered Of Site
75 | All Sites | MLTX-02-004-PRO-TS9-1-MEC-MAC-0013-00 | 2026-04-23 | 2026-04-23 | B | Afico Insulation | Mechanical | Short Lead | 3 |  |  |  | Afico | +966 3 331 3333 | Delivered Of Site
76 | All Sites | MLTX-02-004-PRO-TS9-1-MEC-MAC-0014-00 | 2026-04-25 | 2026-04-27 | B | Water Supply Booster Pumps | Mechanical | Long Lead | 2 | 2 | 2026-05-17 | HQ01-SCC-CND-26-0027 | KSB | +966 1 227 7060 | PO Issued
77 | All Sites | MLTX-02-004-PRO-TS9-1-MEC-MAC-0021-00 | 2026-06-10 | 2026-06-11 | B | Roof Drain & Steel roof scupper | Mechanical | Short Lead | 3 | 3 | 4/25/2026 | PR.10 | Saudi Cast | +966 1 448 0107 | Delivered Of Site
[11 empty] | 6/28/2026 | PR.31
78 | All Sites | MLTX-02-004-PRO-TS9-1-MEC-MAC-0016-03 | 2026-06-30 | 2026-07-02 | B | Hot Press GRP Sectional Panel Water Tanks | Mechanical | Long Lead | 2 | 2 | 2026-07-05 | PROFAST-PO-2026-277 | AL-MUHAIDEB | +966 92 002 8545 | PO Issued
79 | All Sites | MLTX-02-004-PRO-TS9-1-MEC-MAC-0022-00 | 2026-06-11 | 2026-06-17 | B | ductwork as per SMACNA Standards | Mechanical | Short Lead | 183 |  |  |  | Rabie Al Takyeef | +966 59 255 5240 | Delivered Of Site
80 | All Sites | MLTX-02-004-PRO-TS9-1-MEC-MAC-0018-00 | 2026-05-20 | 2026-05-25 | B | Manhole Cover | Mechanical | Short Lead | 6 | 6 | 2026-06-28 | PR.43 | Judff |  | PO Issued