## Material Montoring
PROCUREMENT FOR INFRASTRUCTURE DEVELOPMENT FOR INDUSTRIAL CITY 1 IN JEDDAH
Material | Unit | Original BOQ Qty | Revised BOQ Qty | Delivered Qty | Remainning | Delivery % | Installed QTY
Road and Civil
Steel Reinforcement | ton | 126 | 126 | 126 | 0 | 100% | 126
Ready Mixed Concrete | m³ | 4835 | 4835 | 4835 | 0 | 100% | 4835
Backfilling Materials | m³ | 234480 | 234480 | 234480 | 0 | 100% | 234480
Aggregate Base Course | m³ | 24870 | 24870 | 24870 | 0 | 100% | 24870
Precast Concrete Kerb | m | 59990 | 59990 | 59990 | 0 | 100% | 47992
Interlocking Block Pavers | m2 | 57905 | 57905 | 57905 | 0 | 100% | 44586.85
Water Proofing | m2 | 19530 | 19530 | 19530 | 0 | 100% | 16600.5
Pavement Markings | m2 | 3780 | 3780 |  | 3780 | 0%
Bituminous Base Course | m3 | 8290 | 8290 | 8290 | 0 | 100% | 8290
Bituminous Wearing Course | m3 | 5920 | 5920 | 1723 | 4197 | 29.1% | 1723
Traffic Signs | Nos | 261 | 261 | 261 | 0 | 100% | 160
Metal Fence | m | 3356 | 2295 | 2295 | 0 | 100% | 1905
Gates | Nos | 6 | 0 |  | 0 | 0%
Paint On Cement Plaster | m2 | 4062 | 4062 |  | 4062 | 0% | 1225
MECHANICAL
GRP Pipes for Sewer network | m | 6737 | 6244 | 6244 | 0 | 100% | 6244
Fiberglass Manholes for Sewer network | m | 122 | 116 | 116 | 0 | 100% | 116
HDPE Pipe (PN 16) for TSE | m | 9424 | 8502 | 8722 | -220 | 102.6% | 8772
Valves for TSE | Nos | 142 | 142 | 142 | 0 | 100% | 142
Fire Hydrant | Nos | 89 | 79 | 79 | 0 | 100% | 79
GRP Pipes for Storm network | m | 5939 | 5650 | 5650 | 0 | 100% | 5650
UPVC Pipes | m | 3127 | 4159 | 4159 | 0 | 100% | 4159
Inlet Manholes for Storm network | Nos | 130 | 127 | 127 | 0 | 100% | 127
Concrete chambers | Nos | 180 | 189 | 189 | 0 | 100% | 189
HDPE Pipe (PN 16) for Ptable Water | m | 10852 | 12075 | 12075 | 0 | 100% | 12045
Valves for Ptable Water | Nos | 108 | 108 | 108 | 0 | 100% | 108
ELECTRICAL
Pipe for Duct | m | 700 | 700 | 700 | 0 | 100% | 700
Low Voltage Cables | m | 17223 | 17223 | 17223 | 0 | 100% | 12065
Manhole | Nos | 77 | 71 | 71 | 0 | 100% | 60
Pipe for Duct | m | 500 | 500 | 500 | 0 | 100% | 500 | 0.21
Cable Termination & Joints | Nos | 64 | 64 |  | 64 | 0%
Earthing System | Nos | 70 | 70 | 70 | 0 | 100% | 33
Medium Voltage Cable | m | 14500 | 14500 |  | 14500 | 0%
Street Lighting Sub-station | Nos | 4 | 4 |  | 4 | 0%
Low Voltage Cables | m | 6115 | 6115 | 6115 | 0 | 100% | 1444
Ring Main Unit | Nos | 4 | 4 |  | 4 | 0%
Lighting poles | Nos | 443 | 404 | 404 | 0 | 100% | 344
Lighting panels | Nos | 4 | 4 | 4 | 0 | 100% | 4
Street Lighting Luminaire | Nos | 443 | 404 | 404 | 0 | 100% | 344
KWHM | Nos | 4 | 4 |  | 4 | 0%
Feeder Piller | Nos | 10 | 10 | 10 | 0 | 100% | 10
Street Lighting Panels | Nos | 4 | 4 | 4 | 0 | 100% | 4
LED Screen 43" (24/7 operation) with Ethernet decoders | Nos | 4 | 4 | 4 | 0 | 100%
Network Video Recorder 4k 64 Channel | Nos | 1 | 1 | 1 | 0 | 100%
Keypad | Nos | 1 | 1 | 1 | 0 | 100%
Fiber Optic Patch Panel 12 port | Nos | 2 | 2 | 2 | 0 | 100% | 2
Modular Industrial Switches for main pole | Nos | 1 | 1 | 1 | 0 | 100% | 1
8POE ports Industrial Switches for remote poles | Nos | 6 | 6 | 6 | 0 | 100% | 6
Core Switch | Nos | 2 | 2 | 2 | 0 | 100% | 2
Access Switch 48 port | Nos | 2 | 2 | 2 | 0 | 100% | 2
Server | Nos | 3 | 3 | 3 | 0 | 100% | 3
Stand rack 42U- 19" | Nos | 2 | 2 | 2 | 0 | 100% | 2
IP Outdoor CCTV POE Camera,5 MP, Metal Housing | Nos | 28 | 28 | 28 | 0 | 100% | 28