## DB (hidden)
MODON - Weekly Progress Report - Construction Projects
| Contract General Information | [7 empty] | Key Dates | [10 empty] | Cost Summary (SR) | [8 empty] | Performance Summary | [11 empty] | Shop Drawings |  |  |  | Material Approval |  |  | Procurement Summary | [6 empty] | Quality Reports | [15 empty] | Key Submittals Approval Status | [9 empty] | Invoices Summary | [13 empty] | Resources at Site | [6 empty] | Safety Statistics | [63 empty] | Primavera P6 Schedule Status | [7 empty] | Weekly Prgoress Photos
Data Date | Project Name | Project ID | Contractor | Consultant | Stage | Status | Modon PM | Project Scope | Contract Award | Contract Sign | Site Handover | Original Completion | Contract Award (Hijri) | Contract Sign (Hijri) | Site Handover (Hijri) | Original Completion (Hijri) | Revised Completion | Committed Completion | Forecast Completion | Original Contract Value | Revised Contract Value | Estimate At Completion Value | Potential Changes | O&M Value (if any) | Submitted Invoices (Gross Value) | Penalities | FIR Value (THIS WEEK) | Original Plan Value | Plan Value | Earn Value | Phys. Plan Value | Phys. Earn Value | Quality Score | Safety Score | Weekly PV (SAR) | Weekly EV (SAR) | Weekly PV % | Weekly PV % | Weekly Phys PV% | Weekly Phys PV% | Total SD Planned | SD Remaining | SD Pending | Total SD Submittals | Planned Materials Approv | Material Pending Approval | Materila Total Submittals | Total Materials | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Material on Site | Remaining Materials | Material Delivery Completion (Date) | NCR Issued | NCR Closed | NCR Pending | NCR Avg. Closing (Days) | SIR Issued | SIR Closed | SIR Pending | SIR Avg. Closing (Days) | MIR Issued | MIR Closed | MIR Pending | MIR Avg. Closing (Days) | FIR Issued | FIR Closed | FIR Pending | FIR Avg. Closing (Days) | 1 Quality Plan Approval | 2 Quality Plan Last Up | 3 Safety Plan Approval | 4 Safety Plan Last Up | 5 Construction Plan Approval | 6 Baseline Approval | 7 No of Approved Version of Schedule | 8 Last Approved Schedule | 9 BOQ Approval Date | 10 No of Approved Version of BOQ | Total Submitted Invoices | PM Approved Invoices | No of Paid Invoices | No of Pending Invoices | Advance Payment % | Retention % | Deduction / Penalties % | Submitted Invoices (SAR) | PM Approved Invoices (SAR) | Paid Invoices (SAR) | Last Submitted Period | Advance Payment (SAR) | Retention (SAR) | Deduction / Penalties (SAR) | Planned Head Count | Actual Head Count | Saudi Staff | Labor Planned | Labor Actual | Equipment Planned | Equipment Actual | This Week Total Hours Worked | This Week Safe Hours Worked | This Week LTI | This Week MTC (Healed w/o Disability) | This Week MTC (Healed w/ Disability) | This Week Near Miss | This Week First Aid Cases | This Week Fatality | This Week Fire Incident Cases | This Week Vehicle Incident | This Week Property Damages | This Week Induction Training | This Week No.of Internal Training | This Week No.of Internal Audit | This Week No. of Toolbox Talks | This Week Safety Awards/Incentives | This Month Total Hours Worked | This Month Safe Hours Worked | This Month LTI | This Month MTC (Healed w/o Disability) | This Month MTC (Healed w/ Disability) | This Month Near Miss | This Month First Aid Cases | This Month Fatality | This Month Fire Incident Cases | This Month Vehicle Incident | This Month Property Damages | This Month Induction Training | This Month No.of Internal Training | This Month No.of Internal Audit | This Month No. of Toolbox Talks | This Month Safety Awards/Incentives | YTD Total Hours Worked | YTD Safe Hours Worked | YTD LTI | YTD MTC (Healed w/o Disability) | YTD MTC (Healed w/ Disability) | YTD Near Miss | YTD First Aid Cases | YTD Fatality | YTD Fire Incident Cases | YTD Vehicle Incident | YTD Property Damages | YTD Induction Training | YTD No.of Internal Training | YTD No.of Internal Audit | YTD No. of Toolbox Talks | YTD Safety Awards/Incentives | Cum Total Hours Worked | Cum Safe Hours Worked | Cum LTI | Cum MTC (Healed w/o Disability) | Cum MTC (Healed w/ Disability) | Cum Near Miss | Cum First Aid Cases | Cum Fatality | Cum Fire Incident Cases | Cum Vehicle Incident | Cum Property Damages | Cum Induction Training | Cum No.of Internal Training | Cum No.of Internal Audit | Cum No. of Toolbox Talks | Cum Safety Awards/Incentives | Total Act. | Not Started | In Progress | Completed | Critical Path Act.Last Week | Critical Path Act.This Week | Failed start Last Week | Failed start This Week | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-05 | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | TAB1-02-003 | ASAS for Developing & Operating Industrial Cities | EGIS | INFRASTRUCTURE & UTILITIES | Active | ENG/ YAZEED ALRAGABAH | The project consists of roads works and the POND A which works as a downstream for the storm water wet utility piping network including manholes and catch basins, continued project wet utilities also sewerage GRP piping network with manholes, potable water and firefighting compound HDPE piping network including the installation of valves and fire hydrants and the irrigation water (TSE) network with all valves and the flow meter, dry utility represented in electrical road lighting network - the installation of poles and the LV cables which is connected to the panel board and the 13.8/0.4 K V unit substation. | 2025-08-13 | 2025-08-31 | 2025-09-04 | 2027-09-03 | 2025-08-13 | 2025-08-31 | 2025-09-04 | 2027-09-03 | 2027-09-03 | 2027-09-03 | 2027-10-02 | 140467862 | 140467862 | 140467862 | 0 | 0 | 43497867.43 | 58000 | 49536099.6895 | 61.95% | 36.95% | 46.89% | 34.02% | 48.55% | 0.92983 | 0.94565 | 572175.95 | 600872.91 | 0.4073% | 0.4278% | 0.648% | 0.8238% | 300 | 0 | 0 | 428 | 0 | 1 | 52 | 29 | 29 | 27 | 2 | 45142 | 12907 | 0 | 11 | 11 | 0 | 5 | 20 | 20 | 0 | 5 | 220 | 219 | 1 | 2 | 6434 | 6334 | 100 | 2 | 2025-11-02 | 2025-11-02 | 2025-10-20 | 2025-10-20 | #REF! | 2025-11-03 | 2 | 2025-11-03 | 0 | 0 | 13 | 9 | 9 | 0 | 0.1 | 0 | 0.00041291 | 43497867.43 | 29853856.43 | 34389934.8945 | 2026-09-30 | 14046786.2 | 0 | 58000 | 28 | 32 | 4 | 141 | 398 | 38 | 57 | 10980 | 6360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 10980 | 10980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 361964 | 361964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 18 | 0 | 35 | 0 | 361964 | 361964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 18 | 0 | 35 | 0 | 1492 | 729 | 199 | 564 | 117 | 188 | 22 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0

## Procurement (2) (hidden)
|  | TAB1-02-003 |  | Procurement Log- Long Lead Items | [18 empty] | 2026-10-05
Sr. NO. | Project ID | ACT#inP6 | Item Description | Discipline | (Long \Short) Lead Items | BOQ. No. | Unit | Quantity | Proc. Qty | Required P.O Date | Date of Pur. Order Issued | Purchase Order No. | Supplier | Supplier Phone | Method of Shipping | Required on Job | E.D.A. to Site | A.D.A. to Site | Lead Time | Approval Status | Completion Rate | The Impact (BOQ Cost) | Remarks
SHORT-LEAD
1 |  | ROADS | ROADS |  | Short
1 | TAB1-01-009 | TAPQDVRD0001 | ABC | ROADS | LONG |  | m3 | 48485 | 48485 | 2025-11-01 | 2026-03-24 | SL103026 | شركة خبير المستقبل للاسفلت |  | Local | 2026-04-09 | 2026-03-21 | 2026-03-21 |  | Accepted As Material | 32% |  | po issued
2 | TAB1-01-009 | TAPQDVRD0002 | BBC Base Course | ROADS | LONG |  | m3 | 24510 | 24510 | 2025-11-01 | 2026-03-24 | SL103026 | شركة خبير المستقبل للاسفلت |  | Local | 2026-03-29 | 2026-03-29 | 2026-03-29 |  | Accepted As Material | 16% |  | DELIVERY ONGOING
3 | TAB1-01-009 | TAPQDVRD0003 | BWC Asphalt Wearing Course | ROADS | LONG |  | m3 | 14195 | 14195 | 2025-11-01 | 2026-03-24 | SL103027 | شركة خبير المستقبل للاسفلت |  | Local | 2027-07-14 |  |  |  | Accepted As Material |  |  | po issued
4 | TAB1-01-009 | TAPQDVRD0004 | Precast Concrete Curbstone | ROADS | LONG |  | m | 74370 | 74370 | 2025-11-01 | 2026-07-05 | PO-02156 | جسور المستقبل |  | Local | 2026-04-07 | 2026-04-12 | 2026-04-12 |  | Accepted As Material | 5% |  | DELIVERY ONGOING
5 | TAB1-01-009 | TAPQDVRD0005 | Precast Concrete Interlocking | ROADS | LONG |  | m2 | 62075 | 62075 | 2025-11-01 | 2026-07-05 | PO-02156 | جسور المستقبل |  | Local | 2027-07-18 |  |  |  | Accepted As Material |  |  | po issued
6 | TAB1-01-009 | TAPQDVRD0008 | Marking for Road | ROADS | LONG |  |  |  |  | 2025-11-01 | 2026-04-19 | SL1942026 | شركة أضواء طي الشمال |  | Local | 2026-04-22 | 2026-04-26 | 2026-04-26 |  | Accepted As Material | 19% |  | DELIVERY ONGOING
7 | TAB1-01-009 | TAPQDVRD0009 | Trafic Sinage | ROADS | LONG |  | Unit | 246 | 246 | 2025-11-01 |  |  |  |  | Local | 2026-04-28 |  |  |  | Accepted As Material | 2% |  | DELIVERY ONGOING
2 |  | ELECTRICAL | ELECTRICAL
8 | TAB1-01-009 | TAPQDVEL0001 | Pipes ,Fittings | ELECTRICAL | LONG |  | m | 2145 | 2145 | 2026-04-23 | 2026-04-22 | SL2242026 | الشركة العربية لصناعة البلاستك |  | Local | 2026-04-29 | 2026-04-29 | 2026-04-29 |  | Accepted As Material | 70% |  | DELIVERY ONGOING | 26.81%
9 |  |  | cables (LV ) | [6 empty] | 2026-04-23 | 2026-07-02 | PO-02162 | بحرة |  |  | 2026-08-20 | [6 empty] | po issued
10 | TAB1-01-009 | TAPQDVEL0002 | SCOPE MV | ELECTRICAL | LONG |  | m | 115400 | 115400 | 2026-04-23 | 2026-04-14 | PO-014255 | شركة ايتيا |  | Local | 2026-08-20 | 2026-06-10 | 2026-06-10 |  | Accepted As Material | 12% |  | DELIVERY ONGOING
11 | TAB1-01-009 | TAPQDVEL0003 | Poles & Luminares | ELECTRICAL | LONG |  | Unit | 957 | 957 | 2026-04-23 | 2026-06-09 | PO-012069 | شركة جلنتي |  | Local | 2026-10-29 |  |  |  | Accepted As Material |  |  | po issued
13 | TAB1-01-009 | TAPQDVEL0004 | Substations ,ets.. | ELECTRICAL | LONG |  | Unit | 5 | 5 | 2026-04-23 | 2026-04-14 | PO-014255 | شركة ايتيا |  | Local | 2027-01-07 |  |  |  | Accepted As Material |  |  | po issued
14 | TAB1-01-009 | TAPQDVEL0004 | RMU ,ets.. | ELECTRICAL | LONG |  | Unit | 5 | 5 | 2026-04-23 | 2026-04-14 | PO-014255 | شركة ايتيا |  | Local | 2027-01-07 |  |  |  | Accepted As Material |  |  | po issued
16 |  |  | Pole Foundation | [6 empty] | 2026-04-23 | [5 empty] | 2027-01-14 | [6 empty] | po not issued
3 |  | TELECOMMUNICATION | TELECOMMUNICATION
17 | TAB1-01-009 | TAPQDVTC0001 | Telecommunication Material (Pipes,,ets) | TELECOMMUNICATION | LONG |  | m | 16522 | 16522 | 2026-06-03 |  |  |  |  | Local | 2026-07-16 |  |  |  | Accepted As Material | 1% |  | po not issued
4 |  | CCTV NETWORK | CCTV NETWORK
18 | TAB1-01-009 | TAPQDVCC0001 | CCTV NETWORK | CCTV NETWORK | LONG |  | m | 24430 | 24430 | 2026-06-29 | 2026-07-06 |  |  |  | Local | 2026-09-24 |  |  |  | Accepted As Material |  |  | po issued
5 |  | POTABLE WATER | POTABLE WATER
19 | TAB1-01-009 | TAPQDVPT0001 | PE Pipes | POTABLE WATER | LONG |  | m | 13221 | 13221 | 2026-01-03 | 2025-12-30 | PO-01613 | UNION PIPES |  | Local | 2026-01-18 | 2026-01-21 | 2026-01-21 |  | Accepted As Material | 89% |  | DELIVERY ONGOING
20 | TAB1-01-009 | TAPQDVPT0002 | Valves | POTABLE WATER | LONG |  | Nr | 146 | 146 | 2026-01-03 | 2025-12-25 | PO-01520 | SPC |  | Local | 2026-02-10 | 2026-02-10 | 2026-02-10 |  | Accepted As Material | 78% |  | DELIVERY ONGOING
21 | TAB1-01-009 | TAPQDVPT0003 | Fire Hydrent | POTABLE WATER | LONG |  | Nr | 152 | 152 | 2026-01-03 | 2025-12-25 | PO-1520 | SPC |  | Local | 2026-02-20 | 2026-02-20 | 2026-02-20 |  | Accepted As Material | 68% |  | DELIVERY ONGOING
6 |  | TSE NETWORK | TSE NETWORK
22 | TAB1-01-009 | TAPQDVTS0001 | PE Pipes | TSE NETWORK | LONG |  | m | 12223 | 12223 | 2026-01-03 | 2025-12-30 | PO-01613 | UNION PIPES |  | Local | 2026-01-22 | 2026-01-21 | 2026-01-21 |  | Accepted As Material | 89% |  | DELIVERY ONGOING
23 | TAB1-01-009 | TAPQDVTS0002 | Valves | TSE NETWORK | LONG |  | Nr | 141 | 141 | 2026-01-03 | 2025-12-25 | PO-01520 | SPC |  | Local | 2026-02-20 | 2026-02-10 | 2026-02-10 |  | Accepted As Material | 78% |  | DELIVERY ONGOING
7 |  | SEWERAGE NETWORK | SEWERAGE NETWORK
24 | TAB1-01-009 | TAPQDVSW0001 | GRP Pipes | SEWERAGE NETWORK | LONG |  | m | 8370 | 8370 | 2025-11-19 | 2025-11-24 | PO-01437 | TAREQ NAQADI | 533365029 | Local | 2025-12-09 | 2025-12-09 | 2025-12-09 |  | Accepted As Material | 84% |  | DELIVERY ONGOING
25 | TAB1-01-009 | TAPQDVSW0002 | Fiberglass Manholes,ets) | SEWERAGE NETWORK | LONG |  | Nr | 142 | 142 | 2025-11-19 | 2026-01-18 | PO-1662 | TAREQ NAQADI |  | Local | 2026-01-29 | 2026-02-02 | 2026-02-02 |  | Accepted As Material | 100% |  | DONE
8 |  | STORM NETWORK | STORM NETWORK
26 | TAB1-01-009 | TAPQDVST0001 | UPVC Pipes with Fittings | STORM NETWORK | LONG |  | m | 6621 | 6621 | 2026-12-03 | 2025-12-28 | PO-01580 | الخام الوطني للصناعات |  | Local | 2026-01-18 | 2026-01-21 | 2026-01-21 |  | Accepted As Material | 100% |  | DONE
27 | TAB1-01-009 | TAPQDVST0002 | GRP Pipes with Fittings | STORM NETWORK | LONG |  | m | 9017 | 9017 | 2025-11-21 | 2025-11-24 | PO-01437 | TAREQ NAQADI | 533365029 | Local | 2025-12-09 | 2025-12-09 | 2025-12-09 |  | Accepted As Material | 88% |  | DELIVERY ONGOING
28 | TAB1-01-009 | TAPQDVST0005 | Box Culvert | STORM NETWORK | LONG |  | m3 | 4100 | 4100 | 2025-11-21 | 2026-02-01 | PO-01183 | TAREQ NAQADI |  | Local | 2026-03-04 | 2026-03-05 | 2026-03-05 |  | Accepted As Material | 98% |  | DELIVERY ONGOING
29 | TAB1-01-009 | TAPQDVST0006 | Manholes,ets | STORM NETWORK | LONG |  | Nr | 155 | 155 | 2025-11-21 | 2026-01-21 | PO -01700 | JOSOR ELMOSTAKBEL |  | Local | 2026-02-07 | 2026-03-05 | 2026-03-05 |  | Accepted As Material | 99% |  | DELIVERY ONGOING
30 |  |  | CATCH BASIN | STORM NETWORK | [7 empty] | PO-01886 | TAREQ NAQADI |  |  | 2026-06-15 | 2026-04-22 | 2026-04-22 |  | Accepted As Material | 68% |  | DELIVERY ONGOING
31 | TAB1-01-009 | TAPQDVST0007 | RIprab for Ponds | STORM NETWORK | LONG |  | m2 | 15345 | 15345 | 2025-11-21 | 2026-04-21 | SL1942027 | SALALEM ELYAMAMAH |  | Local | 2026-04-22 | 2026-04-22 | 2026-04-22 |  | Accepted As Material | 30% |  | DELIVERY ONGOING
32 | TAB1-01-009 | TAPQDVST0010 | Riprab for Dike | STORM NETWORK | LONG |  | m2 | 1570 | 1570 | 2025-11-21 | 2026-04-21 | SL1942027 | SALALEM ELYAMAMAH |  | Local | 2026-04-22 | 2026-04-22 | 2026-04-22 |  | Accepted As Material | 90% |  | DELIVERY ONGOING
CCTV Swiches Lighting panels
Street Lighting panels 1- 63A MCCB Circuit Breaker 2- 6X32 MCB Circuit Breakers 3- 1X63A contactors 4- Photocell & Timer 5- ON/OFF Push Button 6- Indication Lamps 7- Copper Bus Bars 8- Panel Body from Galavanized Steel anti-corrosion (IP65) And includes everything necessary to operate the panels according to the technical specifications or instructions of the supervising engineer.
Feeder pillars 1- 100A MCCB Circuit Breaker 2- 5X63A MCCB Circuit Breakers 3- Indication Lamps 4- Copper Bus Bars 5- Panel Body from Galavanized Steel anti-corrosion (IP65) And includes everything necessary for operation according to the technical specifications or instructions of the supervising engineer.
#REF!

## Weekly Progress Report
MODON - Weekly Progress Report - Construction Projects | [30 empty] | Data Date | 2026-10-05
Contract General Information | [5 empty] | Key Dates | [5 empty] | Cost Summary (SR) | [7 empty] | Performance Summary | [5 empty] | Project Scope
Project Name | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY |  |  |  |  | Contract Award | 2025-08-13 | Contract Award (Hijri) | 2025-08-13 | Revised Completion | 2027-09-03 | Original Contract Value |  | 140467862 |  | O&M Value (if any) |  | 0 | EAC | Plan Value | 36.95% | Phys. Plan Value | 34.02% | Quality Score | 92.98% | The project consists of roads works and the POND A which works as a downstream for the storm water wet utility piping network including manholes and catch basins, continued project wet utilities also sewerage GRP piping network with manholes, potable water and firefighting compound HDPE piping network including the installation of valves and fire hydrants and the irrigation water (TSE) network with all valves and the flow meter, dry utility represented in electrical road lighting network - the installation of poles and the LV cables which is connected to the panel board and the 13.8/0.4 K V unit substation.
Project ID | TAB1-02-003 |  | Stage | INFRASTRUCTURE & UTILITIES |  | Contract Sign | 2025-08-31 | Contract Sign (Hijri) | 2025-08-31 | Committed Completion | 2027-09-03 | Revised Contract Value |  | 140467862 | EAC | Submitted Invoices (Gross Value) |  | 43497867.43 |  | Earn Value | 46.89% | Phys. Earn Value | 48.55% |  | ¢¢¢¢¢ ¢¢¢¢£
Contractor | ASAS for Developing & Operating Industrial Cities |  | Status | Active |  | Site Handover | 2025-09-04 | Site Handover (Hijri) | 2025-09-04 | Forecast Completion | 2027-10-02 | Estimate At Completion Value |  | 140467862 | #REF! | Penalities |  | 58000 |  | Variance | 9.943% | Variance | 14.53% | Safety Score | 94.57%
Consultant | EGIS |  | Modon PM | ENG/ YAZEED ALRAGABAH |  | Original Completion | 2027-09-03 | Original Completion (Hijri) | 2027-09-03 | Variance | -29 | Potential Changes |  | 0 |  | FIR Value (THIS WEEK) |  | 49536099.6895 |  | FIR % | 35.27% | Invoiced % | 30.97% |  | ¢¢¢¢¢ ¢¢¢¢£
Progress Overview
Earned Value Progress (SAR) | [13 empty] | Physical Progress (Effort) | [11 empty] | Earned Value Progress (%)
WBS |  | BOQ Value (SAR) | % Wt. | Weekly (SAR) |  | To Date (SAR) | [7 empty] | Budgeted | % Wt. | Weekly Physical Progress |  |  |  | To Date Physical Progress
|  |  |  | Planned | Earned | Original Plan | Revised Planned | Earned | Original Plan % | Revised Planned % | Earned % | Variance | SPI | (Manhours) |  | Planned | Earned | Plan % | Earned % | Planned | Earned | Plan % | Earned % | Variance | SPI
MILESTONS |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | 0% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
MOBILIZATION |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 1600 | 0.4515% | 0 | 0 | 0% | 0% | 1600 | 1600 | 100% | 100% | 0% | 1
ENGINEERING |  | 4214035 | 3% | 0 | 0 | 4214035 | 4214035 | 4214035.86 | 100% | 100% | 100% | 2.041e-05% | 1 | 0 | 0% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
PROCUREMENT |  | 28093571.94 | 20% | 199021.62 | 0 | 21353231.77 | 14863212.17 | 17030315.65 | 76.01% | 52.91% | 60.62% | 7.714% | 1.1458 | 0 | 0% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
CONSTRUCTION WORKS |  | 94113468.86 | 67% | 373154.33 | 600872.91 | 57322787.15 | 32825234.38 | 44625184.51 | 60.91% | 34.88% | 47.42% | 12.54% | 1.3595 | 347187 | 97.98% | 2296 | 2919 | 0.6613% | 0.8408% | 118954 | 170422 | 34.26% | 49.09% | 14.82% | 1.4327
ZONE 01 |  | 18023708.09 | 12.83% | 84426.05 | 110171.62 | 15946487.31 | 10061529.48 | 11756509.92 | 88.48% | 55.82% | 65.23% | 9.404% | 1.1685 | 74705 | 21.08% | 714 | 1080 | 0.9558% | 1.446% | 28223 | 41425 | 37.78% | 55.45% | 17.67% | 1.4678
ZONE 02 |  | 24418267.82 | 17.38% | 99957.83 | 200481.63 | 16454735.19 | 9237285.45 | 14479525.74 | 67.39% | 37.83% | 59.3% | 21.47% | 1.5675 | 89699 | 25.31% | 586 | 411 | 0.6533% | 0.4582% | 39539 | 61620 | 44.08% | 68.7% | 24.62% | 1.5585
ZONE 03 |  | 51671492.95 | 36.79% | 188770.45 | 290219.65 | 24921564.64 | 13526419.45 | 18389148.85 | 48.23% | 26.18% | 35.59% | 9.411% | 1.3595 | 182783 | 51.58% | 997 | 1428 | 0.5455% | 0.7813% | 51193 | 67377 | 28.01% | 36.86% | 8.854% | 1.3161
CLOSE OUT |  | 14046786.2 | 10% | 0 |  | 4136347.57 | 0 | 0 | 29.45% | 0% | 0% | 0% |  | 5552 | 1.567% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
0
| Total | 140467862 | 100% | 572175.95 | 600872.91 | 87026401.49 | 51902481.55 | 65869536.02 | 61.95% | 36.95% | 46.89% | 9.943% | 1.2691 | 354339 | 100% | 2296 | 2919 | 0.648% | 0.8238% | 120554 | 172022 | 34.02% | 48.55% | 14.53% | 1.4269
Construction Milestones
[26 empty] | Item No. | Milestones |  | Original (Baseline) | Latest Plan | Forecast | Status | Days Change
[26 empty] | 1 | Award Date |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | A | 0
[26 empty] | 2 | Contract Sign Date |  | 2025-08-31 | 2025-08-31 | 2025-08-31 | A | 0
[26 empty] | 3 | Site Handover Date |  | 2025-09-04 | 2025-09-04 | 2025-09-04 | A | 0
[26 empty] | 4 | Complete Mobilization |  | 2027-08-10 | 2027-08-23 | 2027-08-30 | F | -7
[26 empty] | 7 | Complete ZONE 1 |  | 2027-02-09 | 2027-09-30 | 2027-10-02 | F | -2
[26 empty] | 8 | Complete ZONE 2 |  | 2027-08-02 | 2027-08-09 | 2027-08-16 | F | -7
[26 empty] | 9 | Complete ZONE 3 |  | 2027-08-02 | 2027-09-26 | 2027-09-27 | F | -1
[26 empty] | 10 | Complete all Works including Testing & Commissioning, Cleanup, Closeout Documentation and Ready for Initial Handover |  | 2027-08-10 | 2027-09-12 | 2027-09-13 | F | -1
[26 empty] | 11 | Complete Demobilization |  | 2027-09-03 | 2027-09-30 | 2027-10-02 | F | -2
[26 empty] | 12 | Project Handover |  | 2027-09-03 | 2027-09-30 | 2027-10-02 | F | -2
Performance overview
Submittals Status | [10 empty] | Quality | [10 empty] | Safety
Shop Drawings | [10 empty] | Quality Reports | [10 empty] | Safety Statistics | [7 empty] | Proactive Vs Reactive Actions Taken
Item Per WBS |  | Total | Total Submitted Drawings |  |  |  |  | Remaining | Pending | Total Submittals | Quality Reports |  | Issued | Closed | Pending | Avg. Closing (Days) | Pending |  |  |  |  | Category | Item |  | This Week |  | This Month | Year to Date | Cumulative
|  |  | A | B | C | D | Processed | [9 empty] | 0-10 Days | 11-20 Days | 21-30 Days | 31-60 Days | > 60 Days
Electrical Network - Road Lighting |  | 102 | 33 | 69 | 0 | 0 | 102 |  |  | 102 | [11 empty] | General | Total Hours Worked |  | 10980 |  | 10980 | 361964 | 361964 |  |  | Proactive | 61
Potable Water Network |  | 53 | 50 | 3 | 0 | 0 | 53 |  |  | 53 | Non Conformance (NCR) |  | 11 | 11 | 0 | 5 | 0 | 0 | 0 | 0 | 0 |  | Safe Hours Worked |  | 6360 |  | 10980 | 361964 | 361964 |  |  | Reactive | 0
TSE Network |  | 50 | 0 | 50 | 0 | 0 | 50 | 0 |  | 50 | Site Instruction (SIR) |  | 20 | 20 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | Reactive | LTI |  | 0 |  | 0 | 0 | 0
Sewerage Network |  | 25 | 25 | 0 | 0 | 0 | 25 | 0 |  | 27 | Material Inspection (MIR) |  | 220 | 219 | 1 | 2 | 1 | 0 | 0 | 0 | 0 |  | MTC (Healed w/o Disability) |  | 0 |  | 0 | 0 | 0
Storm Water Network |  | 25 | 41 | 33 | 2 | 0 | 25 | 0 |  | 35
ROAD |  | 45 | 37 | 122 | 2 | 0 | 45 |  |  | 161 | Field Inspection (FIR) |  | 6434 | 6334 | 100 | 2 | 1 | 0 | 0 | 0 | 0 |  | MTC (Healed w/ Disability) |  | 0 |  | 0 | 0 | 0
TOTAL |  | 300 | 186 | 277 | 4 | 0 | 300 | 0 | 0 | 428 | Key Submittals Approval Status | [11 empty] | Near Miss |  | 0 |  | 0 | 0 | 0
Material Approval | [10 empty] | 1 Quality Plan Approval |  |  | 2025-11-02 |  | 6 Baseline Approval |  |  |  | 2025-11-03 |  |  | First Aid Cases |  | 0 |  | 0 | 0 | 0 | Total Hours Worked Vs Safe Hours Worked
Item Per WBS |  | Total | Total Submitted Material |  |  |  |  | Remaining to approve | Pending | Total Submittals | 2 Quality Plan Last Up |  |  | 2025-11-02 |  | 7 No of Approved Version of Schedule |  |  |  | 2 |  |  | Fatality |  | 0 |  | 0 | 0 | 0
|  |  | A | B | C | D | Processed | with Designer |  |  | 3 Safety Plan Approval |  |  | 2025-10-20 |  | 8 Last Approved Schedule |  |  |  | 2025-11-03 |  |  | Fire Incident Cases |  | 0 |  | 0 | 0 | 0
Electrical Network - Road Lighting |  |  | 0 | 26 | 0 | 0 | 25 | 0 | 0 | 26 | 4 Safety Plan Last Up |  |  | 2025-10-20 |  | 9 BOQ Approval Date |  |  |  | 0 |  |  | Vehicle Incident |  | 0 |  | 0 | 0 | 0
Potable Water Network |  | 0 | 0 | 6 | 0 | 0 | 5 | 0 | 1 | 6 | 5 Construction Plan Approval |  |  | #REF! |  | 10 No of Approved Version of BOQ |  |  |  | 0 |  |  | Property Damages |  | 0 |  | 0 | 0 | 0
TSE Network |  | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | Invoices Summary | [10 empty] | Proactive | Induction Training |  | 0 |  | 0 | 7 | 8
Sewerage Network |  | 0 | 0 | 7 | 0 | 0 | 6 | 0 | 0 | 7 | Total Submitted Invoices |  | 13 | Submitted Invoices (SAR) |  |  | 43497867.43 |  | Contract Value (SR) | 140467862 |  |  | No.of Internal Training |  | 1 |  | 1 | 18 | 18
Storm Water Network |  | 0 | 0 | 7 | 0 | 0 | 6 | 0 | 0 | 7 | PM Approved Invoices |  | 9 | PM Approved Invoices (SAR) |  |  | 29853856.43 |  | Planned Value (SR) | 51902481.55 |  |  | No.of Internal Audit |  | 0 |  | 0 | 0 | 0
TOTAL |  | 0 | 0 | 52 | 0 | 0 | 48 | 0 | 1 | 52 | No of Paid Invoices |  | 9 | Paid Invoices (SAR) |  |  | 34389934.8945 |  | Earned Value (SR) | 65869536.02 |  |  | No. of Toolbox Talks |  | 1 |  | 1 | 35 | 35
Procurement Summary | [10 empty] | No of Pending Invoices |  | 0 | Last Submitted Period |  |  | 2026-09-30 |  | Submitted (SAR) | 43497867.43 |  |  | Safety Awards/Incentives |  | 0 |  | 0 | 0 | 0
Item Per WBS |  | Total Materials | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Material on Site | Remaining Materials | Material Delivery Completion (Date) |  |  | Advance Payment % |  | 10% | Advance Payment (SAR) |  |  | 14046786.2 |  | PM Approved (SAR) | 29853856.43 |  | Latest Contract Change Order Log
|  |  | A | B | C | D | Processed |  |  |  | Retention % |  | 0% | Retention (SAR) |  |  | 0 |  | Total Paid (SAR) | 34389934.8945
Electrical Network - Road Lighting |  | 9 | 9 | 7 | 2 | 8000 | 0 |  |  |  | Deduction / Penalties % |  | 0.04129% | Deduction / Penalties (SAR) |  |  | 58000 |  |  |  |  | CCO No. | Date Added | Description of Change |  |  |  |  | Status | Cost | Sch Impact (Months) | Date Approved | Duration
Potable Water Network |  | 3 | 3 | 3 | 0 | 6474 | 6248 |  |  |  | Resources at Site
TSE Network |  | 2 | 2 | 2 | 0 | 6474 | 6248 |  |  |  | Head Count - Non Manual |  |  |  | Head Count - Manual |  |  |  | Total Head Count |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
Sewerage Network |  | 2 | 2 | 2 | 0 | 7045 | 275 |  |  |  | Planned | Actual | Next Month Forecast | Saudi Staff | Planned | Actual | Next Month Forecast | Saudi Staff | Total Plan | Total Actual | Variance
Storm Water Network |  | 6 | 6 | 6 | 0 | 16049 | 136 |  |  |  | 28 | 32 | 28 | 4 | 141 | 398 | 63 | 0 | 169 | 430 | 261
TOTAL |  | 29 | 29 | 27 | 2 | 45142 | 12907 |  |  |  | Manpower Breakdown by Trade | [6 empty] | Major Equipment
Primavera P6 Schedule Status | [10 empty] | Key Trade | Planned | Actual |  |  |  |  | Type | Planned | Actual | Idle
Project Activities Overview | [10 empty] | General Labor | 13 | 79 |  |  |  |  | Excavator | 15 | 24 | 0
Schedule Statistics |  |  |  |  | Active Schedule Activities | [5 empty] | Carpenter | 0 | 18 |  |  |  |  | Loader | 1 | 3 | 0 | Major Quantity Trackers
Total Act. | Not Started | In Progress | Completed | % | Active | Ahead | On | Behind | Flag | 0 | Plumber | 5 | 11 |  |  |  |  | Dozer | 1 | 1 | 0 | BOQ N0. | Item Description |  |  |  |  | Total Qty | Measu Unit | Plan to Date | Act to Date | Remaining | Variance
1492 | 729 | 199 | 564 | 37.8% | 199 | 183 | 16 | 0 | 199 |  | OPERATOR | 19 | 45 |  |  |  |  | Dump truck | 16 | 10 | 0 | 31 22 00 05 | POND Excavation |  |  |  |  | 321070 | M3 | 296255 | 296255 | 24815 | 0
Critical Path Activities |  |  | Free Float Management (Total) |  |  |  | Failed Start Activities |  |  |  | Steel Fixer | 0 | 10 |  |  |  |  | Water tanker | 2 | 3 | 0 | 31 22 00 01 | ROAD Excavation |  |  |  |  | 99925 | M3 | 99925 | 93475 | 6450 | -6450
|  |  | Greater Than 14 Days |  | Less Than 14 Days | [5 empty] | Driver | 18 | 16 |  |  |  |  | Grader | 1 | 2 | 0 | 31 22 00 02 | ROAD BACKFILL |  |  |  |  | 107100 | M3 | 107100 | 81600 | 25500 | -25500
[11 empty] | Milling | 1 | 1 |  |  |  |  | MILLING MACHINE | 1 | 1 | 0 | 32 22 00 03 | ROAD SUPGRADE |  |  |  |  | 72730 | M3 | 72730 | 53900 | 18830 | -18830
Last Week | This Week | Diff | Last Week | This Week | Last Week | This Week | Last Week | This Week | Flag | 0 | Total | 85 | 218 |  |  |  |  | Roller | 1 | 9 | 0 | 33 31 00 | SEWAGE network |  |  |  |  | 8370 | M | 0 | 6815 | 1555 | 6815
117 | 188 | -71 | 0 | 0 | 0 | 0 | 22 | 24 | -2 | [8 empty] | Desil tanker | 0 | 1 | 0 | 33 31 00 | STORM network |  |  |  |  | 15638 | M | 0 | 12964 | 2674 | 12964
[18 empty] | PAVER BASE COURSE | 0 | 1 | 1 |  | BACKFILLING DIKE |  |  |  |  | 3865 | M3 | 0 | 3865 | 0 | 3865
[18 empty] | SCREEN | 0 | 2 | 0 |  | TSE network |  |  |  |  | 12223 | M | 0 | 8078 | 4145 | 8078
[11 empty] | Total | 141 | 398 |  |  |  |  | Total | 38 | 57 | 1 |  | POTABLE WATER network |  |  |  |  | 13221 | M | 0 | 8992 | 4229 | 8992
Weekly Prgoress Photos | [15 empty] | Top Issues and Risks
VALVE CHAMBER |  |  |  |  | MC1 | [5 empty] | CATCH BASIN |  |  |  |  | Top 5 Issues
[16 empty] | Issue No | Date Identified | Issue Description |  |  |  | Responsible | Action Taken |  |  | Mitigation |  |  |  |  | Current Status | Expected/Actual Closure | Duration Elapsed
[16 empty] | 1 | 2025-09-06 | ELECTRICAL CABLE IN POND |  |  |  | E | DIVERT THE CABLE TO BE AWAY FROM THE POND | [7 empty] | Close | 2026-04-20 | 226
[16 empty] | 2 | 2026-03-30 | INDUSTRIAL FACILITIES ENCROACHING ON ROAD LOCAL1- 2-3-4-5-COLLECTOR 3-UPGRADE 39-21 |  |  |  | Consultant | THE RFI HAS BEEN RAISED REGRARDING NETWORK DAMAGE DUE TO INTERFERENCE WITH THE FACTORIES | [7 empty] | Closed | 2026-04-29 | 30
[16 empty] | 3 | 2026-02-11 | TELECOMMUNICATIONS NETWORK INTEGRATION & UNDERSIZED SERVER ROOM IN THE ADMINISTRATION BUILDING |  |  |  | Contractor | THE DRAWING ARE BEING SUBMITTED FOR APPROVAL | [7 empty] | Closed | 2026-06-06 | 115
[16 empty] | 4 | 2026-05-06 | DELAY IN PROCUREMENT FOR MV |  |  |  | Contractor | MATERIAL DELIVERY HAS STARTED | [7 empty] | Closed | 2026-06-15 | 40
[16 empty] | 5 | 2026-04-27 | DELAY IN PROCUREMENT DELIVERY OF MATERIALS INCLUDING CATCHBASIN - SLEEVES PIPES FOR UPVC & GRP |  |  |  | Contractor | PROCUREMENT ACTIVITIES WILL BE INITIATED | [7 empty] | Closed | 2026-06-22 | 56
3,345,990

## General Information
Weekly Progress Report - Construction Projects |  |  | Data Date | 2026-10-05
Contract General Information
Project Name | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY
Project ID | TAB1-02-003
Contractor | ASAS for Developing & Operating Industrial Cities
Consultant | EGIS
Stage | INFRASTRUCTURE & UTILITIES
Status | Active
Modon PM | ENG/ YAZEED ALRAGABAH
Key Dates
Contract Award Date | 2025-08-13
Contract Sign Date | 2025-08-31
Site Handover Date | 2025-09-04
Original Completion | 2027-09-03
Contract Award Date (Hijri) | 2025-08-13
Contract Sign Date (Hijri) | 2025-08-31
Site Handover Date (Hijri) | 2025-09-04
Original Completion (Hijri) | 2027-09-03
Revised Completion Date | 2027-09-03
Committed Completion Date | 2027-09-03
Forecast Completion | 2027-10-02
Variance | -29
Key Project Submittals | Submission Date | Days taken to approve orginal plan from site handover date
Quality Plan submission | 2025-10-01 | 27
Quality Plan approval | 2025-11-02
Quality Plan Last Update | 2025-11-02
NO OF REVESION | 3
Safety Plan submission | 2025-10-04 | 30
Safety Plan approval | 2025-10-20
Safety Plan Last Update | 2025-10-20
NO OF REVESION | 1
Risk Management Plan submission
Risk Management Plan approval
Risk Management Plan Last Update
Baseline Schedule submission | 2025-10-14 | 40
Baseline Schedule approval | 2025-11-03
No of Schedule Versions | 2
Last Recovery Schedule Approval Date | 2025-11-03
BOQ submission
BOQ approval
No of Approved Version of BOQ
Note on D25: AlNuaim, Abdulaziz: As per contract requirments submission of Plans should be 30 days after site handover

## Weekly Photos
Date | 2026-10-05
CATCH BASIN |  | SUGRADE
VALVE CHAMBER |  | MC1

## Progress
Project Scope Statement | The project consists of roads works and the POND A which works as a downstream for the storm water wet utility piping network including manholes and catch basins, continued project wet utilities also sewerage GRP piping network with manholes, potable water and firefighting compound HDPE piping network including the installation of valves and fire hydrants and the irrigation water (TSE) network with all valves and the flow meter, dry utility represented in electrical road lighting network - the installation of poles and the LV cables which is connected to the panel board and the 13.8/0.4 K V unit substation. | [15 empty] | Data Date | 2026-10-05
Earned Value Progress (SAR) | [8 empty] | Physical Progress (Effort)
WBS |  | BOQ Value (SAR) | % Wt. | Weekly (SAR) |  |  | To Date (SAR) |  | Budgeted | % Wt. | Weekly Physical Progress |  | To Date Physical Progress
|  |  |  | Planned | Earned | Original Plan | Planned | Earned | (Manhours) |  | Planned | Earned | Planned | Earned
MILESTONS |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0
MOBILIZATION |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 1600 | 0.4515% | 0 | 0 | 1600 | 1600
ENGINEERING |  | 4214035 | 3% | 0 | 0 | 4214035 | 4214035 | 4214035.86 | 0 | 0% | 0 | 0 | 0 | 0
PROCUREMENT |  | 28093571.94 | 20% | 199021.62 | 0 | 21353231.77 | 14863212.17 | 17030315.65 | 0 | 0% | 0 | 0 | 0 | 0
CONSTRUCTION WORKS |  | 94113468.86 | 67% | 373154.33 | 600872.91 | 57322787.15 | 32825234.38 | 44625184.51 | 347187 | 97.98% | 2296 | 2919 | 118954 | 170422
ZONE 01 |  | 18023708.09 | 12.83% | 84426.05 | 110171.62 | 15946487.31 | 10061529.48 | 11756509.92 | 74705 | 21.08% | 714 | 1080 | 28223 | 41425
ZONE 02 |  | 24418267.82 | 17.38% | 99957.83 | 200481.63 | 16454735.19 | 9237285.45 | 14479525.74 | 89699 | 25.31% | 586 | 411 | 39539 | 61620
ZONE 03 |  | 51671492.95 | 36.79% | 188770.45 | 290219.65 | 24921564.64 | 13526419.45 | 18389148.85 | 182783 | 51.58% | 997 | 1428 | 51193 | 67377
CLOSE OUT |  | 14046786.2 | 10% | 0 | 0 | 4136347.57 | 0 | 0 | 5552 | 1.567% |  | 0 | 0 | 0
| Total | 140467862 | 100% | 572175.95 | 600872.91 | 87026401.49 | 51902481.55 | 65869536.02 | 354339 | 100% | 2296 | 2919 | 120554 | 172022
|  |  |  | 0.4073% | 0.4278% | 61.95% | 36.95% | 46.89% |  |  | 0.648% | 0.8238% | 34.02% | 48.55%
18023708.09 | 12.83% |  | THIS WEEK |  | TO DATE |  |  | LAST WEEK |  |  | `
24418267.82 | 17.38% | EARNED | PLANNED |  | EARNED | PLANNED | EARNED | PLANNED
51671492.95 | 36.79% | 0 | 0 |  | 4214035.86 | 4214035 | 4214035.86 | 4214035
|  | 0 | 199021.62 |  | 17030315.65 | 14863212.17 | 17030315.65 | 14664190.55 |  | 3034784.22
|  |  | -32825234.38 |  |  |  | 44024311.6 | 32452080.05 | Activity ID | Activity Name | Budgeted Total Cost | Planned Value Cost | Earned Value Cost | Budgeted Labor Units | Planned Value Labor Units | Earned Value Labor Units |  | Activity ID | Activity Name | Budgeted Total Cost | Planned Value Cost | Earned Value Cost | Budgeted Labor Units | Planned Value Labor Units | Earned Value Labor Units
|  |  | 0 |  |  |  | 4214035.86 | 4214035 | Mobilization |  | 0 | 0 | 0 | 73264 | 24824 | 24818.56 |  | Mobilization |  | 0 | 0 | 0 | 73264 | 24152 | 24146.63
|  |  | 0 |  |  |  | 17030315.65 | 14664190.55 | POND A |  | 8470654 | 3058845 | 3921635.66 | 21368 | 14428 | 13070.16 |  | POND A |  | 8470654 | 3015000 | 3921635.66 | 21368 | 14080 | 12590.16
|  |  | 0 |  |  |  | 44024311.6 | 32452080.05 | Engineering |  | 0 | 0 | 0 | 720 | 720 | 720 |  | Engineering |  | 0 | 0 | 0 | 720 | 720 | 528
|  |  | 0 |  |  |  | 4214035.86 | 4214035 | Procurement |  | 0 | 0 | 0 | 3472 | 1872 | 1008 |  | Procurement |  | 0 | 0 | 0 | 3472 | 1824 | 720
|  |  | 0 |  |  |  | 17030315.65 | 14664190.55 | Construction |  | 8470654 | 3058845 | 3921635.66 | 17176 | 11836 | 11342.16 |  | Construction |  | 8470654 | 3015000 | 3921635.66 | 17176 | 11536 | 11342.16
|  |  | 0 |  |  |  | 44024311.6 | 32452080.05 | Storm Network |  | 18712041 | 4045715.84 | 7526224.98 | 172856 | 45912 | 66478.76 |  | Storm Network |  | 18712041 | 3609053.88 | 7382744.22 | 172856 | 41216 | 64478.11
|  |  | 0 |  |  |  | 4214035.86 | 4214035 | Engineering |  | 477625.95 | 477625.95 | 477625.95 | 528 | 528 | 528 |  | Engineering |  | 477625.95 | 477625.95 | 477625.95 | 528 | 528 | 528
|  |  | 0 |  |  |  | 17030315.65 | 14664190.55 | Procurement |  | 3184173 | 1758490.02 | 2649528.75 | 11800 | 6520 | 8391.81 |  | Procurement |  | 3184173 | 1644425.81 | 2620191.92 | 11800 | 6136 | 8194.12
|  |  | 0 |  |  |  | 44024311.6 | 32452080.05 | Construction |  | 12167339.55 | 1809599.87 | 4399070.28 | 159952 | 38864 | 57558.95 |  | Construction |  | 12167339.55 | 1487002.12 | 4284926.36 | 159952 | 34552 | 55755.99
|  |  | 0 |  |  |  | 4214035.86 | 4214035 | Testing & Commissioning |  | 2882902.5 | 0 | 0 | 576 | 0 | 0 |  | Testing & Commissioning |  | 2882902.5 | 0 | 0 | 576 | 0 | 0
|  |  | 0 |  |  |  | 17030315.65 | 14664190.55 | Sewerage Network |  | 5198775 | 137774.25 | 2756946.48 | 89168 | 1280 | 43406.4 |  | Sewerage Network |  | 5198775 | 137774.25 | 2484242.95 | 89168 | 1280 | 39988.27
|  |  | 0 |  |  |  | 44024311.6 | 32452080.05 | Engineering |  | 137774.25 | 137774.25 | 137774.25 | 440 | 440 | 440 |  | Engineering |  | 137774.25 | 137774.25 | 137774.25 | 440 | 440 | 440
|  |  | 0 |  |  |  | 4214035.86 | 4214035 | Procurement |  | 918495 | 0 | 739138.75 | 6600 | 840 | 5010.28 |  | Procurement |  | 918495 | 0 | 728737.79 | 6600 | 840 | 4916.64
|  |  | 0 |  |  |  | 17030315.65 | 14664190.55 | Construction |  | 3683258.25 | 0 | 1880033.48 | 81488 | 0 | 37956.12 |  | Construction |  | 3683258.25 | 0 | 1617730.91 | 81488 | 0 | 34631.63
|  |  | 0 |  |  |  | 44024311.6 | 32452080.05 | Testing & Commissioning |  | 459247.5 | 0 | 0 | 640 | 0 | 0 |  | Testing & Commissioning |  | 459247.5 | 0 | 0 | 640 | 0 | 0
|  |  | 0 |  |  |  | 4214035.86 | 4214035 | Potable Network |  | 4220565 | 115789.35 | 134067.15 | 53248 | 2016 | 2167.99 |  | Potable Network |  | 4220565 | 115789.35 | 115789.35 | 53248 | 2016 | 1848
|  |  | 0 |  |  |  | 17030315.65 | 14664190.55 | Engineering |  | 115789.35 | 115789.35 | 115789.35 | 432 | 432 | 432 |  | Engineering |  | 115789.35 | 115789.35 | 115789.35 | 432 | 432 | 432
|  |  | 0 |  |  |  | 44024311.6 | 32452080.05 | Procurement |  | 771929 | 0 | 0 | 11984 | 1584 | 1416 |  | Procurement |  | 771929 | 0 | 0 | 11984 | 1584 | 1416
|  |  | 0 |  |  |  | 4214035.86 | 4214035 | Construction |  | 2946882.15 | 0 | 18277.8 | 40256 | 0 | 319.99 |  | Construction |  | 2946882.15 | 0 | 0 | 40256 | 0 | 0
|  |  | 0 |  |  |  | 17030315.65 | 14664190.55 | Testing & Commissioning |  | 385964.5 | 0 | 0 | 576 | 0 | 0 |  | Testing & Commissioning |  | 385964.5 | 0 | 0 | 576 | 0 | 0
|  |  | 0 |  |  |  | 44024311.6 | 32452080.05 | TSE Network |  | 2343660 | 62735.4 | 65496.71 | 56400 | 1640 | 1676 |  | TSE Network |  | 2343660 | 62735.4 | 62735.4 | 56400 | 1640 | 1640
|  |  | 0 |  |  |  | 4214035.86 | 4214035 | Engineering |  | 62735.4 | 62735.4 | 62735.4 | 344 | 344 | 344 |  | Engineering |  | 62735.4 | 62735.4 | 62735.4 | 344 | 344 | 344
|  |  | 0 |  |  |  | 17030315.65 | 14664190.55 | Procurement |  | 418236 | 0 | 0 | 6736 | 1296 | 1296 |  | Procurement |  | 418236 | 0 | 0 | 6736 | 1296 | 1296
|  |  | 0 |  |  |  | 44024311.6 | 32452080.05 | Construction |  | 1653570.6 | 0 | 2761.31 | 48744 | 0 | 36 |  | Construction |  | 1653570.6 | 0 | 0 | 48744 | 0 | 0
|  |  | 0 |  |  |  | 4214035.86 | 4214035 | Testing & Commissioning |  | 209118 | 0 | 0 | 576 | 0 | 0 |  | Testing & Commissioning |  | 209118 | 0 | 0 | 576 | 0 | 0
|  |  | 0 |  |  |  | 17030315.65 | 14664190.55 | Electrical Works - Road Lighting |  | 6147980 | 171640.5 | 157900.5 | 54144 | 7728 | 4040 |  | Electrical Works - Road Lighting |  | 6147980 | 171640.5 | 155440.5 | 54144 | 7728 | 3608
|  |  | -51902481.55 |  |  |  | 44024311.6 | 32452080.05 | Engineering |  | 171640.5 | 171640.5 | 157900.5 | 1128 | 1128 | 536 |  | Engineering |  | 171640.5 | 171640.5 | 155440.5 | 1128 | 1128 | 440
|  |  | -0.3695 |  |  |  | 4214035.86 | 4214035 | Procurement |  | 1144270 | 0 | 0 | 19960 | 6600 | 3504 |  | Procurement |  | 1144270 | 0 | 0 | 19960 | 6600 | 3168
|  |  | 0 |  |  |  | 17030315.65 | 14664190.55 | Construction |  | 4259934.5 | 0 | 0 | 32496 | 0 | 0 |  | Construction |  | 4259934.5 | 0 | 0 | 32496 | 0 | 0
|  |  | 0 |  |  |  | 44024311.6 | 32452080.05 | Testing & Commissioning |  | 572135 | 0 | 0 | 560 | 0 | 0 |  | Testing & Commissioning |  | 572135 | 0 | 0 | 560 | 0 | 0
|  |  | 0 |  |  |  | 4214035.86 | 4214035 | Close Out |  | 0 | 0 | 0 | 1200 | 0 | 0 |  | Close Out |  | 0 | 0 | 0 | 1200 | 0 | 0
|  |  | 0 |  |  |  | 17030315.65 | 14664190.55
|  |  | #VALUE! |  |  |  | 44024311.6 | 32452080.05
|  |  | -4214035.86 |  |  |  | 4214035.86 | 4214035
|  |  | -17030315.65 |  |  |  | 17030315.65 | 14664190.55
|  | 600872.91 | 373154.33 |  | 44625184.51 | 32825234.38 | 44024311.6 | 32452080.05
|  | 0 | 0 |  | 0 | 0 |  | 0
|  | 600872.91 | 572175.95 |  | 65869536.02 | 51902481.55 | 65268663.11 | 51330305.6
|  | THIS WEEK |  |  | TO DATE |  | LAST WEEK
|  | EARNED | PLANNED |  | EARNED | PLANNED | EARNED | PLANNED
|  | 0 | 0 |  |  | 0 | 0 | 0
|  | 0 | 0 |  | 1600 | 1600 | 1600 | 1600 | 1152 | 1571
|  | 0 | 0 |  |  | 0 | 0 | 0 | 14379 | 16255
|  | 0 | 0 |  |  | 0 | 0 | 0
|  | 2919 | 2296 |  | 170422 | 118954 | 167503 | 116658
|  | 0 | 0 |  |  | 0 |  | 0
|  | 2919 | 2296 |  | 172022 | 120554 | 169103 | 118258
|  | 110171.62 | 84426.05 |  | 11756509.92 | 10061529.48 | 11646338.3 | 9977103.43
|  | 200481.63 | 99957.83 |  | 14479525.74 | 9237285.45 | 14279044.11 | 9137327.62
|  | 290219.65 | 188770.45 |  | 18389148.85 | 13526419.45 | 18098929.2 | 13337649
[5 empty] | 44625184.51 | 32825234.38 | 44024311.61 | 32452080.05
|  | 1080 | 714 |  | 41425 | 28223 | 40345 | 27509
|  | 411 | 586 |  | 61620 | 39539 | 61209 | 38953
|  | 1428 | 997 |  | 67377 | 51193 | 65949 | 50196

## FIR Summary
Project Name |  | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY
Project ID |  | Project Budget | 140467862 | Total FIR Amount | 49536099.6895
Date Pariod |  | Start Date | 2026-09-29 | To | 2026-10-05
SL. | date of FIR | TOTAL AMOUNT |  | Total Amount % (as per FIR)
1 | 2025-12-18 | 5481497.57 |  | 3.902% |  |  | 694495.374
2 | 2025-12-27 | 6294267.27 |  | 4.481% |  |  | 29085.9975
3 | 2026-01-04 | 6611589.6844 |  | 4.707% |  |  | 1649842.2638
4 | 2026-01-18 | 6870205.81 |  | 4.891% |  |  | 53438.985
5 | 2026-01-12 | 7315951.38 |  | 5.208% |  |  | 63638.2254
6 | 2026-01-26 | 7625043.81 |  | 5.428% |  |  | 1228633.9388
7 | 2026-02-01 | 9927796.8908 |  | 7.068% |  |  | 1223854.4934
8 | 2026-02-08 | 10171734.3811 |  | 7.241% |  |  | 538913.14
9 | 2026-02-15 | 11230039.2344 |  | 7.995% |  |  | 78456.8862
10 | 2026-02-22 | 12001213.295 |  | 8.544% |  |  | 7020520
11 | 2026-03-01 | 12646729.9722 |  | 9.003% |  |  | 439316.205
12 | 2026-03-10 | 13096417.7611 |  | 9.323% |  |  | 76222.252
13 | 2026-03-16 | 13670634.98 |  | 9.732% |  |  | 13096417.7611
14 | 2026-03-24 | 13948403.98 |  | 9.93% |  |  | 26192835.5221
15 | 2026-03-29 | 14265278.58 |  | 10.16%
16 | 2026-04-06 | 16655783.37 |  | 11.86%
16 | 2026-04-13 | 17041466.4098 |  | 12.13% |  |  | 23307506.6141
17 | 2026-04-19 | 18406573.6 |  | 13.1%
19 | 2026-04-26 | 20233592.7829 |  | 14.4%
20 | 2026-05-03 | 22462434.9354 |  | 15.99%
21 | 2026-05-09 | 23307506.6141 |  | 16.59%
22 | 2026-05-17 | 24118465.2022 |  | 17.17% |  | 24118465.2022
23 | 2026-05-23 | 25053976.2737 |  | 17.84% |  |  | 23307506.6141
24 | 2026-05-31 | 25482985.1472 |  | 18.14% |  | 29620391.3761
25 | 2026-06-07 | 26822182.7827 |  | 19.09% |  |  | 25482985.1472
26 | 2026-06-14 | 27449997.6589 |  | 19.54%
27 | 2026-06-22 | 29620391.3761 |  | 21.09% |  | 34438964.0694
28 | 2026-06-28 | 32264053.868 |  | 22.97%
29 | 2026-06-06 | 33487382.1956 |  | 23.84% |  | 32264053.868
30 | 2026-07-13 | 34438964.0694 |  | 24.52%
31 | 2026-07-20 | 36225039.4 |  | 25.79% |  | 33487382.1956
32 | 2026-07-27 | 38555752.8153 |  | 27.45% |  | 40536512.7317
| 2026-08-03 | 39610512.7317 |  | 28.2% |  | 41463220.2738
| 2026-08-10 | 41463220.27 |  | 29.52% |  | 44854868.8104
| 2026-08-17 | 44202407.4552 |  | 31.47%
| 2026-08-23 | 44854868.8104 |  | 31.93%
| 2026-08-30 | 46432145.9087 |  | 33.06% |  | 48524583.3371
| 2026-09-07 | 46753754.2742 |  | 33.28%
| 2026-09-14 | 48118249.4214 |  | 34.26% |  | 49536099.6895
| 2026-09-20 | 48524583.3371 |  | 34.54%
| 2026-09-27 | 49536099.6895 |  | 35.27% |  | 50191338.0405
| 2026-10-05 | 50191338.0405 |  | 35.73%

## Quality
QC OBSERVATIONS CHECKLIST
2024-03-26
Project No. |  |  | TAB1-02-003 |  |  | OBS No. | [6 empty] | Inspection Day: |  | 2026-10-05
Project |  |  | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY | [6 empty] | Contractor: Consultant: |  |  | ASAS for Developing & Operating Industrial CITIES EGIS
4 |  | Excellent |  | Quality Management System is being practiced and applies to MODON System | [11 empty] | 90 - 100 |  | QC Overall Score | 92.98% |  |  |  |  | 0% | 100 | 0.22883
3 |  | Good |  | Evidence of compliance with plans and procedures. | [11 empty] | 80 - 89 | [7 empty] | 0 | 89 | 0.20366
2 |  | Average |  | Indication level of compliance with standards but there is room for improvement | [11 empty] | 70 - 79 | [8 empty] | 79 | 0.18078
1 |  | Improve |  | Quality and Control is NOT being managed effectively. Needs Improvement | [11 empty] | ≤ 69 | [8 empty] | 69 | 0.15789
0 |  | N/A |  | Item was not applicable or this item was not reviewed during the inspection. | [11 empty] | Zero | [8 empty] | 100 | 0.22883
No. | Topic |  |  |  |  | E (4) | G (3) | A (2) | I (1) | N/A (0) | No. | Topic |  |  |  | E (4) | G (3) | A (2) | I (1) | N/A (0) |  |  |  |  | 437
[6 empty] | 100% | 89% | 79% | 69% | 100% | [5 empty] | 100% | 89% | 79% | 69% | 100% | 92.98%
1 | Control of Access to Site/Office |  |  |  |  | 0 | 1 |  |  |  | 30 | QC of Excavation |  |  |  | 0 | 1 |  |  |  | 0.89 | 0.89 | [6 empty] | Item Count | Score | Distributtion
2 | Document Control Administration |  |  |  |  | 0 | 0 | 1 |  |  | 31 | QC of Roads/Round about |  |  |  | 0 | 1 |  |  |  | 0.79 | 0.89 | [8 empty] | Overall | Relevant
3 | Project Documents and Progress | [5 empty] | 1 | 0 |  |  | 32 | QC of Interlock & Curbstone |  |  |  | 1 |  |  |  | 0 | 0.89 | 1 | 4 | 58 | counts |  | 4 | Excellent | 14 | 56 | 24.14% | 34.15%
4 | Contractor's Quality Plan/CM (Updated and Reviewed) |  |  |  |  | 0 | 1 |  |  |  | 33 | Layers/Backfilling Sampling |  |  |  |  | 0 | 1 | 0 |  | 0.89 | 0.79 | 3 | 58 | counts |  | 3 | Good | 18 | 54 | 31.03% | 43.9%
5 | MS Log and Paperwork |  |  |  |  | 1 | 0 | 0 |  |  | 34 | Pump Stations Units | [6 empty] | 0 | 1 | 1 | 1 | 2 | 58 | counts |  | 2 | Average | 7 | 14 | 12.07% | 17.07% |  | NB: Insert 1, or 0 in the required cell only.
6 | RFI, FIR, & MIR Procedure |  |  |  |  | 1 | 0 |  |  |  | 35 | Quality of Form Work |  |  |  |  | 1 | 0 |  | 0 | 1 | 0.89 | 1 | 58 | counts |  | 1 | Improve | 2 | 2 | 3.448% | 4.878%
7 | RFI, FIR, & MIR Inventory system |  |  |  |  | 0 | 1 |  |  |  | 36 | Design Change List | [6 empty] | 0 | 1 | 0.89 | 1 | 0 | 58 | counts |  | 0 | N/A | 17 | 0 | 29.31% | -
8 | NCRs Control & Procedure |  |  |  |  | 0 | 1 | 0 |  | 0 | 37 | Quality of Concrete Placing |  |  |  |  | 1 |  |  | 0 | 0.89 | 0.89 | [5 empty] | Total | 58 | 126 | 100% | 100%
9 | NCR Log |  |  |  |  | 1 | 0 |  |  |  | 38 | Concrete Surface Finishing |  |  |  | 0 | 1 |  |  | 0 | 1 | 0.89
10 | MODON Standard* |  |  |  |  | 0 | 0 |  | 1 |  | 39 | Pedestals/Columns/Beams Alignment | [7 empty] | 1 | 0.69 | 1 | [6 empty] | Maz Score Available: | 164 | <- Excludes N/A items
11 | Project Risk Plan/Management* |  |  |  |  | 0 |  | 0 |  | 1 | 40 | Siporex Lifting & Unloading | [7 empty] | 1 | 1 | 1
12 | Monthly Quality Reports* |  |  |  |  | 0 | 1 | 0 |  |  | 41 | Siporex Quality Pre-installation | [7 empty] | 1 | 0.89 | 1
13 | ITP |  |  |  |  | 1 | 0 | 0 |  |  | 42 | Siporex Finishing Quality | [7 empty] | 1 | 1 | 1 | [5 empty] | Total Score |  | Percentage (%)
14 | MODON Weekly Report |  |  |  |  | 1 | 0 | 0 |  |  | 43 | Roads / Parking Markings | [7 empty] | 1 | 1 | 1 |  | 58 |  |  |  | 126 |  | 76.8293 |  | %
15 | Design Change Official Paperwork* |  |  |  |  | 0 |  |  |  | 1 | 44 | QC of Finishing Outdoors | [7 empty] | 1 | 1 | 1 | [5 empty] | Max Score Available | [6 empty] | 31
16 | Design Change was Applied* |  |  |  |  | 0 |  |  |  | 1 | 45 | Quality of Finishing Indoors | [7 empty] | 1 | 1 | 1 | [5 empty] | 164 | [6 empty] | 32
17 | Material List |  |  |  |  | 1 | 0 | 0 |  |  | 46 | Stairs Quality | [7 empty] | 1 | 1 | 1 | [12 empty] | 33
18 | Pending Material Status |  |  |  |  | 1 | 0 |  |  | 0 | 47 | Tanks Method Statement Work | [7 empty] | 1 | 1 | 1 | [12 empty] | 34
19 | Lifting Plan* | [8 empty] | 1 | 48 | Electric Rooms | [7 empty] | 1 | 1 | 1 | [12 empty] | 35
20 | DWG Log |  |  |  |  | 0 | 1 | 0 |  | 0 | 49 | QC of MCC/ATS Plant Units | [7 empty] | 1 | 0.89 | 1 | [12 empty] | 36
21 | Invoice Status |  |  |  |  | 1 | 0 |  |  | 0 | 50 | Qualified Subcontractor |  |  |  | 0 | 1 | 0 |  | 0 | 1 | 0.89 | [12 empty] | 37
22 | Site Handover Letter |  |  |  |  | 1 | 0 |  |  |  | 51 | Scaffold/Ladders/Slope/Bridge Compliance | [6 empty] | 1 | 0 | 1 | 0.69 | [12 empty] | 38
23 | Material Testing Results & Certification |  |  |  |  | 1 | 0 | 0 | 0 |  | 52 | Protection Applied to Completed Work | [5 empty] | 1 | 0 | 0 | 1 | 0.79
24 | As Build Drawings Status* | [5 empty] | 1 | 0 |  | 0 | 53 | Storage Management in/out Control |  |  |  |  | 1 | 0 |  | 0 | 0.89 | 0.89
25 | Calibrated Lab Tools & Equipment |  |  |  |  | 1 | 0 |  | 0 |  | 54 | Material Control |  |  |  |  | 1 | 0 |  | 0 | 1 | 0.89
26 | Storage Inventory System | [5 empty] | 0 | 1 | 0 |  | 55 | Manholes Storing and Quality |  |  |  | 0 | 1 | 0 |  | 0 | 0.79 | 0.89
27 | Logistics Plan | [5 empty] | 0 | 1 |  |  | 56 | Reinforced Steel Quality |  |  |  | 1 | 0 | 0 |  | 0 | 0.79 | 1
28 | Project Progress Planview |  |  |  |  | 1 |  | 0 | 0 |  | 57 | Safety Overview |  |  |  | 0 | 0 | 1 | 0 | 0 | 1 | 0.79
29 | Sufficient Number of QC Inspectors |  |  |  |  | 0 | 1 | 0 | 0 |  | 58 | Waste Management Control |  |  |  |  | 0 | 1 | 0 | 0 | 0.89 | 0.79
0
Score
[8 empty] | *QC % |  |  | 92.98%
Prepared by: |  |  |  | ENG / AHMED SAMIR | [6 empty] | Issued to PM: |  |  | ENG/ YAZEED ALRAGABAH
*QC Observations refer only to the practices and documentation observed at time of inspection. The responsibility of the CM and Contractor is to ensure that aspects of Quality are suitably managed. *Scores are a reflection of the general site conditions based upon the findings at the time of the walk through *If Applicable

## Quality-Stat
Quality Reports
Item |  | Issued | Closed | Pending | Avg. Closing (Days) | Pending
[6 empty] | 0-10 Days | 11-20 Days | 21-30 Days | 31-60 Days | > 60 Days
[13 empty] | 299 | 618 | 917
Non Conforomance Report (NCR) |  | 11 | 11 | 0 | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 1
Site Instruction (SI) |  | 20 | 20 |  | 5 | 2 | 0 | 0 | 0 | 0 |  |  | 286 | 583 | 869
Material Inspection Report (MIR) |  | 220 | 219 | 1 | 2 | 1 | 0 | 0 | 0 | 0
Field Inspection Report (FIR) |  | 6434 | 6334 | 100 | 2 | 1 | 0 | 0 | 0 | 0
[13 empty] | 694 | 7 | 701
Shop Drawings | [12 empty] | 5401 | 87 | 5488
Item Per WBS |  |  | Total Planned | Total Drawings Submitted |  |  |  |  | Remaining Drawings | Pending | Total Submittals |  | 239 | 6 | 245
|  |  |  | A | B | C | D | Approved | with Designer | Submittals With Consultant
Electrical Network - Road Lighting |  |  | 102 | 33 | 69 | 0 | 0 | 102 |  |  | 102
Potable Water Network |  |  | 53 | 50 | 3 | 0 | 0 | 53 |  |  | 53
TSE Network |  |  | 50 | 0 | 50 | 0 | 0 | 50 | 0 |  | 50
Sewerage Network |  |  | 25 | 25 | 0 | 0 | 0 | 25 | 0 |  | 27
Storm Water Network |  |  | 45 | 41 | 33 | 2 | 0 | 45 | 0 |  | 35 |  | 121
ROAD |  |  | 153 | 37 | 122 | 2 | 0 | 153 |  |  | 161
TOTAL |  |  | 428 | 186 | 277 | 4 | 0 | 428 | 0 | 0 | 428
Material Approval
Item Per WBS |  |  | Total Planned | Total Materials Submitted |  |  |  |  | Remaining to approve | Pending | Total Submittals
|  |  |  | A | B | C | D | Approved | with Designer | Submittals With Consultant
Electrical Network - Road Lighting |  |  |  | 0 | 26 | 0 | 0 | 25 | 0 | 0 | 26
Potable Water Network |  |  | 0 | 0 | 6 | 0 | 0 | 5 | 0 | 1 | 6
TSE Network |  |  | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 |  |  | 30
Sewerage Network |  |  | 0 | 0 | 7 | 0 | 0 | 6 | 0 | 0 | 7
Storm Water Network |  |  | 0 | 0 | 7 | 0 | 0 | 6 | 0 | 0 | 7
TOTAL |  |  | 0 | 0 | 52 | 0 | 0 | 48 | 0 | 1 | 52
Procurement Summary
Item Per WBS |  |  | Total Materials Planned | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Actual Material on Site | Remaining Materials | Material Delivery Completion (Date)
|  |  |  | A | B | C | D | Processed
Electrical Network - Road Lighting |  |  | 9 | 9 | 7 | 2 | 8000 | 0
Potable Water Network |  |  | 3 | 3 | 3 | 0 | 6474 | 6248
TSE Network |  |  | 2 | 2 | 2 | 0 | 6474 | 6248 |  |  |  |  | 12496 | 6248
Sewerage Network |  |  | 2 | 2 | 2 | 0 | 7045 | 275
Storm Water Network |  |  | 6 | 6 | 6 | 0 | 16049 | 136
Roads |  |  | 7 | 7 | 7 | 0 | 1100
TOTAL |  |  | 29 | 29 | 27 | 2 | 45142 | 12907
Consultant Quality Inspections / Observations (Weekly Basis) | [7 empty] | Overall Average | 92.86% |  | Average Closing | 1.5614
Week Number | Date of Audit | Date Issued | Numbers Of Comments | Quality Score | Date Closed | Closure Duration |  | This Week Score | 92.98% |  | Average Number of Comments Per Audit | 2.5636
Week-1 | 2025-09-04 | 2025-09-04 | 5 | 92.03% | 2025-09-05 | 1
Week-2 | 2025-09-11 | 2025-09-11 | 5 | 91.21% | 2025-09-12 | 1
Week-3 | 2025-09-18 | 2025-09-18 | 4 | 94.83% | 2025-09-19 | 1
Week-4 | 2025-09-25 | 2025-09-25 | 3 | 92.98% | 2025-09-26 | 1
Week-5 | 2025-10-02 | 2025-10-02 | 1 | 92% | 2025-10-03 | 1
Week-6 | 2025-10-09 | 2025-10-09 | 1 | 94.83% | 2025-10-10 | 1
Week-7 | 2025-10-16 | 2025-10-16 | 1 | 92.98% | 2025-10-17 | 1
Week-8 | 2025-10-23 | 2025-10-23 | 1 | 94.83% | 2025-10-24 | 1
Week-9 | 2025-10-30 | 2025-10-30 | 1 | 93.74% | 2025-10-31 | 1
Week-10 | 2025-11-06 | 2025-11-06 | 2 | 93.74% | 2025-11-07 | 1
Week-11 | 2025-11-13 | 2025-11-13 | 2 | 90.88% | 2025-11-14 | 1
Week-12 | 2025-11-20 | 2025-11-20 | 4 | 90.88% | 2025-11-21 | 1
Week-13 | 2025-11-27 | 2025-11-27 | 5 | 90.88% | 2025-11-28 | 1
Week-14 | 2025-12-04 | 2025-12-04 | 6 | 90.88% | 2025-12-16 | 12
Week-15 | 2025-12-11 | 2025-12-11 | 3 | 90% | 2025-12-12 | 1
Week-16 | 2025-12-19 | 2025-12-19 | 2 | 90.5% | 2025-12-20 | 1
Week-17 | 2025-12-25 | 2025-12-25 | 5 | 93% | 2025-12-26 | 1
Week-18 | 2026-01-01 | 2026-01-01 | 4 | 94% | 2026-01-02 | 1
Week-19 | 2026-01-08 | 2026-01-08 | 3 | 92% | 2026-01-09 | 1
Week-20 | 2026-01-15 | 2026-01-15 | 2 | 93% | 2026-01-16 | 1
Week-21 | 2026-01-22 | 2026-01-22 | 1 | 90% | 2026-01-23 | 1
Week-22 | 2026-01-29 | 2026-01-29 | 2 | 93% | 2026-01-30 | 1
Week-23 | 2026-02-05 | 2026-02-05 | 8 | 88% | 2026-02-06 | 1
Week-24 | 2026-02-12 | 2026-02-12 | 4 | 89% | 2026-02-13 | 1
Week-25 | 2026-02-19 | 2026-02-19 | 6 | 89% | 2026-02-20 | 1
Week-26 | 2026-02-26 | 2026-02-26 | 4 | 90% | 2026-02-27 | 1
Week-27 | 2026-03-05 | 2026-03-05 | 2 | 91% | 2026-03-06 | 1
Week-28 | 2026-03-12 | 2026-03-12 | 3 | 90% | 2026-03-13 | 1
Week-29 | 2026-03-19 | 2026-03-19 | 5 | 89% | 2026-03-20 | 1
Week-30 | 2026-03-26 | 2026-03-26 | 6 | 88% | 2026-03-27 | 1
Week-31 | 2026-04-02 | 2026-04-02 | 1 | 94% | 2026-04-03 | 1
Week-32 | 2026-04-09 | 2026-04-09 | 1 | 94% | 2026-04-10 | 1
Week-33 | 2026-04-16 | 2026-04-16 | 1 | 90% | 2026-04-17 | 1
Week-34 | 2026-04-20 | 2026-04-20 | 1 | 95% | 2026-04-20 | 0
Week-35 | 2026-04-25 | 2026-04-25 | 1 | 95% | 2026-04-26 | 1
Week-36 | 2026-05-01 | 2026-05-02 | 1 | 95% | 2026-05-02 | 1
Week-37 | 2026-05-09 | 2026-05-09 | 3 | 95% | 2026-05-11 | 2
Week-38 | 2026-05-15 | 2026-05-17 | 1 | 93% | 2026-05-18 | 3
Week-39 | 2026-05-20 | 2026-05-21 | 1 | 93% | 2026-05-24 | 4
Week-40 | 2026-05-31 | 2026-05-31 | 0 | 90% | 2026-05-31 | 0
Week-41 | 2026-06-11 | 2026-06-11 | 1 | 95% | 2026-06-14 | 2
Week-42 | 2026-06-20 | 2026-06-20 | 1 | 95% | 2026-06-21 | 3
Week-43 | 2026-06-27 | 2026-06-27 | 1 | 95% | 2026-06-28 | 1
Week-44 | 2026-07-01 | 2026-07-01 | 5 | 95% | 2026-07-06 | 5
Week-45 | 2026-07-09 | 2026-07-09 | 5 | 80% | 2026-07-14 | 6
Week-46 | 2026-07-18 | 2026-07-18 | 4 | 95% | 2026-07-19 | 1
Week-47 | 2026-07-25 | 2026-07-25 | 1 | 97% | 2026-07-26 | 1
Week-48 | 2026-08-01 | 2026-08-01 | 1 | 96% | 2026-08-02 | 1
Week-49 | 46239 | 46239 | 1 | 0.95 | 46240 | 1
Week-50 | 2026-08-15 | 2026-08-15 | 3 | 96% | 2026-08-16 | 2
Week-51 | 2026-08-22 | 2026-08-22 | 3 | 95% | 2026-08-23 | 3
Week-52 | 2026-08-29 | 2026-08-29 | 1 | 97% | 2026-08-30 | 1
Week-53 | 2026-09-05 | 2026-09-05 |  | 94% | 2026-09-06 | 2
Week-54 | 2026-09-12 | 2026-09-12 | 1 | 98% | 2026-09-13 | 1
Week-55 | 2026-09-19 | 2026-09-19 | 2 | 96% | 2026-09-20 | 2
Week-56 | 2026-09-26 | 2026-09-26 | 1 | 97% | 2026-09-27 | 1
Week-57 | 2026-10-03 | 2026-10-03 | 3 | 96% | 2026-10-04 | 1
Week-58
Week-59
Week-60
Week-61
Week-62
Week-63
Week-64
Week-65
Week-66
Week-67
Week-68
Week-69
Week-70
Week-71
Week-72
Week-73
Week-74
Week-75
Formulas:
Avg. Closing (Days) = [Issued]+1
Avg. Closing (Days) = [Issued]
Note on A43: Malik, Muhammad: This refers to quality observation sheet

## HSE
MODON HSE Site Inspection Report
Date |  |  | 2026-10-05 |  |  |  |  | Inspected By:
Project ID. |  |  | TAB1-02-003 |  |  |  |  | Report No. | 0 |  |  |  |  | MODON PM Name |  | ENG/ YAZEED ALRAGABAH
Project Name: |  |  | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY |  |  |  |  | Contractor: |  | ASAS for Developing & Operating Industrial Cities |  |  |  |  | Safety Performance |  | 2 |  |  | 94.57%
Inspections are a snapshot in time and refer only to the practices and documentation observed at the time of the Inspection. It remains the responsibility of the Consultant and Contractor to ensure that all aspects of Health & Safety are suitably managed.
1 |  | Good Practice |  |  | 2 | Need Improvement | [5 empty] | 3 | Fail (Life Threatening Activity) / Comliance with Plan & Procedures |  | N/A | Atcitty Not Applicable for this Site Inspection Report
No. | Topic | [5 empty] | Wt. | HSE Compliance |  |  | No. | Topic | [5 empty] | Wt. | HSE Compliance
1 | Access and Egress - (General access to site, segregated from vehicles, / Overhead protection, while entering into the building /Adequate lighting provided when dark or overnight work) | [5 empty] | 5% | 2 |  |  | 14 | Work at Height - (PPE/Fall Protection(Same level, above and blow) / Training / Fall restraint / competency /Safe access & egress to and from work at height / Ladders / Openings (floor/shafts/Provision of emergency rescue) | [5 empty] | 5% | N/A |  |  |  | 1 | 100 | 1
2 | Traffic Management - (Loading/unloading/sheeting/temp. routes/speed/parking/competence) | [5 empty] | 3% | 1 |  |  | 15 | Scaffolding - (Temp. Scaffolding Work-platform (All types) - qualified scaffolder / Inspection / Tagged / Safe Access/egress / PTW/Falsework & Formwork) | [5 empty] | 4% | N/A |  |  |  | 2 | 75 | 2
3 | Site Signage - (Project Notice Board & General Signage) | [5 empty] | 2% | 1 |  |  | 16 | Mobile Elevated Work platform (MEWP) - (PTW/competence requirements/conditions/inspections/tagged/training/Full-body harness) | [5 empty] | 4% | N/A |  |  |  | 3 | 0 | 3
4 | PPE Compliance - (Use, storage, stock, handling & checks - Head, Foot, Eye, Hearing) | [5 empty] | 5% | 2 |  |  | 17 | Excavation & Trenches - (PTW/Edge protection/buffer zone/Slope/Benching/Shoring/Geo-tech report/Atmospheric hazards/Acess&egress/Emergency management / MS&RA/H.E) | [5 empty] | 3% | 2 | [5 empty] | N/A
5 | Housekeeping - (Material correctly stored/Rubbish cleaned & removed daily/slips & trips hazards) | [5 empty] | 3% | 1 |  |  | 18 | Confined Space - (PTW/Training/competence/Emergency Management/MS & RA/Safe access/egress) | [5 empty] | 5% | 1
6 | Storage of Materials - (Transporting, storage, training and use - Combustible / Flammable / Hazardous substances (COSHH) | [6 empty] | 1 |  |  | 19 | Fire Protection - (Flammable/Oxy. LPG /Combustible separated/FE's/Flashback arrestor/Sparks & slags/Smoking area/PTW/Generators/MS & RA/Emergency Management) | [6 empty] | 1 |  | Red | Serious injury or death (immediately)
7 | Site Waste Management - (Hazardous waste /Combustible waste / Human waste / Construction waste - asphalt, cable, timber, paving roof sheeting tiles, plastic & bricks) | [6 empty] | 1 |  |  | 20 | Health & Welfare - (Adequate drinking water/shaded - eating & rest area/washing & sanitary facilities/Certified FA/FA Box & Stock/adequate toilets/Ambulance) | [6 empty] | 1 |  | Yellow | Minor or near miss (3 days to comply)
8 | Health Surveillance - (Expose to excessive noise/vibration/dust/silica/CO/cement/radiation/extreme weather condition) | [5 empty] | 3% | 2 |  |  | 21 | Environmental Incident Measures - (Spill/ Leakage / Concrete wash / vehicle & eqpts. wash / waste disposal/Sewers and drains/emissions/Emergency Management/Training/site run-off water) | [5 empty] | 5% | 1 |  | Green | No issues
9 | Electrical Safety - (Electrical qualified /RCD/GFCI/Industrial Cocket/LOTO/Cable-overhung or buried/Cords in good condition/current inspection tag) | [5 empty] | 5% | 1 |  |  | 22 | HSE Communications & Meetings - (Schedule HSE Meetings/Safety Committee meetings/Alerts / Lesson learned/Safety Bulletin contains latest HSE KPI) | [5 empty] | 5% | 1
10 | Tools & Equipment - (Includes, powered, hydraulic & pneumatic/Guards in place/Properly stored/RCD Protection/Earthed/Good condition & tagged) | [5 empty] | 3% | 1 |  |  | 23 | HSE Plan & Associated Procedures - (Approved updated HSE Plan/ CEMP/HAZComm/Procedures/Standards/Project Safety Risk Register) | [5 empty] | 3% | 1 |  | 26 points > 4 minors then is it’s a serious issue
11 | Manual Handling - (Lifting/loading/pulling/pushing/twisting/awkward posture/repetitive task/frequent and prolong physical effort/Reasonable practicable use of mechanical aid) | [5 empty] | 3% | 1 |  |  | 24 | Health, Safety & Environment Incident reporting - (Review of HSE Statistics, Reporting of Unsafe Act & Conditions/ Reporting of Near Miss incident/Reporting of FA cases/Record MT cases) | [5 empty] | 3% | 1
12 | Vehicle and mobile equipment / Plant - (dumpers; excavators, cranes, piling rigs, grader, roller, loaders/condition/KSA License/certification) | [5 empty] | 5% | 1 |  |  | 25 | HSE Awareness, Training & Competence - (Policy /Objective & targets/Information, training/Climatic condition awareness/Reponses in emergency situation/ Safety Behavior Observation) | [5 empty] | 4% | 1
13 | Lifting Operations & Rigging - (Lifting Plan/Lifting devices & gears/PTW/Condition/3rd party certification/bank-man/rigger/slingers/man-basket/inspection record/tagged) | [6 empty] | 2 |  |  | 26 | Project Leadership Site Tours - (Provide evidence of proactive safety performance/Deficient discovered discussed/Positive feedback/Workers resolving safety issues) | [6 empty] | 1
Prepared by: |  |  |  | ENG/MOHAMED FAIZAN | [6 empty] | Sent to MODON PM: |  |  |  | ENG/ YAZEED ALRAGABAH
Safety Results
1 |  | 18 |  |  |  | 2 |  | 5 |  |  |  |  | 3 | 0
Note on C13: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Safe access / egress for people to their work area 2 - Safe access / egress for construction vehicles 3 - Access properly restricted-site fencing provided and maintained 4 - Access proper and not blocked 5 - Safe access is available for rescue operation 6 - Storage access / exit are clearly marked and unobstructed 8 - Access and egress is in good condition, hand holds, ladder etc. are sound and in place 9 - Ensure unauthorized public access is prevented 11 - Site assembled ladders or make-shift tables for access are forbidden on site. 13 - Use proper bridges, walkways or gangways to access or cross trenches or an excavation area 14 - Surrounding areas are cleared and barricaded and access restricted to all unauthorized trades while crane in operation 15 - To ensure early access to accredited medical / rehabilitation services 16 - Parking vehicles on site access roads causing obstruction 17 - All personnel will be instructed that access to firefighting equipment must remain clear at all times 18 - Access control gates to be locked out of hours 19 - Site access gates to be designed and located to, where possible, avoid clashes with external hazards / activities
Note on T13: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Personal Fall Arrest System; 1 - Is the suitable harness harnesses is provided 2 - Are shock absorbing lanyard with 2 locking snap hooks. 3 - Is anchorage point strong enough and can support 5,000 Ibs. 4 - Do inspection checklist is being implemented before use. 5 - Is the emergency plan for rescue in place Personal Fall Restraint System; 1 - The fall restraint equipment should be set and adjusted so there is no free fall over the edge. 2 - A harness or body belt may be used 3 - The anchorage point must support 4 times the intended load. Positioning System; 1 - Is a suitable harness or body belt provided 2 - Is there a not more than 2' free fall maintained 3 - Is the anchorage point capable of supporting 2 times the intended load or 3.000 Ibs, whichever is greater 4 - Is 100% tie-off (protection from falls at all times, even when moving from point to point) provided while using personal fall protection with two lanyards Fall Protection System; 1 - Suitable edge protection and work platforms are to be provided to prevent a fall occurring 2 - Where the provision of edge protection or adequate platforms cannot be provided safety nets or other soft-landing systems such as inflatable bags are to be used to minimize the consequences of a fall. 3 - If nets are used, they must be installed by a competent rigger and fitted as close under the work surface as possible. 4 - Areas below roof works are to be cordoned off and properly signed to prevent personnel being injured from falling materials 5 - If access onto the roof cannot be avoided, edge protection is to be installed 6 - Floor and wall openings are to be protected using covers of adequate strength to withstand the expected load that will be imposed and securely fixed. 7 - Penetrations in walls such as those provided for lift shafts, door openings, etc. are to be closed with suitable strength material or have fixed protective barriers around the penetration with a sign warning personnel of the danger of falling.
Note on C14: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are arrival and departure of vehicles and delivery accompany by security department? 2 - Are proper loading, unloading and securing loads, being properly controlled? 3 - Is the proper sheeting & coupling in place when transporting and disposing material to and from site? 4 - Is the parking to the designated parking lot and in reverse order? 5 - Is the designated speed limit adhered on workplace? 6 - Provision of ramps, traffic signs, cones, barriers, demarcation posts and tape, flashing lights and any other traffic control devices. 7 - Do visiting drivers are being inducted at the workplace, prior to enter on the workplace? 8 - Are visiting drivers restricted to dangerous areas, e.g. moving to and from they vehicles to washrooms, lavatory & offices etc.? 9 - Do drivers observe site rules and procedures, for delivery, loading and unloading? 10 - Are the areas wide enough for the safe movement of large vehicles (including visiting vehicles)? 11 - Does drivers are competent, hold valid local driving license and competent training? 12 - Ensure the vehicle and trailers have their brakes applied and all stabilizers properly positioned before beginning loading or unloading?
Note on T14: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Base soundness, load adequately spread (base plate jacks, base plate on firm ground). 2 - Line of standard (vertical) and ledger (horizontal) secure and plumb. 3 - Spacing of transoms on platforms, support for Scaff boards, boards are not over protruded and boards are secured. 4 - Staggering of joints vertical and horizontal. 5 - Guardrail / fall protection. (Top rail – Min.1mtr, Mid rail – 470mm from floor and Toe boards – Minimum150mm) 6 - Longitude and bracing on standards and ledgers. 7 - If close to structure, ties must be on lift below to top working platform and every 3m, load bearing couplers used or tie with certified anchor bolts (eye bolts). 8 - Clamps and tubes used are of correct fittings, size and free from defects. 9 - Tubes & fittings free from defects / deformation. 10 - Safe and proper access available to the working platform. 11 - Scaff tags signed, displayed and up to date. 12 - If close to slab edge/opening scaffold tied and secured to structure correctly.
Note on C15: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a Project Notice Board - (showing HSE Statistics / Safety alerts / lesson learned)? 2 - Is there prominent safety boards that are depicting the mandatory PPE on the workplace? 3 - Are other safety required signs are prominently installed on the workplace in relevant to their work-task, as following: > Hazardous Substances - e.g. respiratory protection Sign > Working at Height - e.g. Full body Harness Sign > Working UG - e.g. Full body Harness, SCBA, Ventilation, PTW Signage etc. > Working with Electrical - e.g. Leather Gloves, Goggles, Face shield, Electric shock proof helmet & shoes > Working with Chemicals - Signage = e.g. Impermeable gloves/clothing's, long sleeves, Goggles 4 - General Site Safety Signs: > Prohibition Sign = (e.g., ‘no access for unauthorized persons’). > Warning Signs = (e.g., ‘danger: electricity’) > Mandatory Signs = e.g., ‘eye protection must be worn’) > Emergency Escape or First Aid Sign = e.g., ‘emergency exit/escape route’) > Safety Color Signs = (e.g., yellow means ‘be careful’ or ‘take precautions’) > Illuminated Signs = (e.g., many emergency exit signs) > Acoustic Signals =( e.g., fire alarm) > Fire safety sign > Supplementary Signs = "This way"
Note on T15: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Man-Lift operators are to be competent and trained to operate the specific Man-Lift by examination and hold a current approved certificate / license from an approved and internationally recognized source (TUV, SGS etc. 1 - All Man-Lifts shall be inspected by a 3rd party on an annual basis. 2 - All Man-Lifts shall display a sticker corresponding to the 3rd party inspection certificate. 3 - The manufacturer's instruction manual must be on site for each and every type of Man-Lift in use. 4- A pre-start daily operator inspection of the equipment will be performed and documented on a daily basis as per the manufacturer's instructions. The user is responsible for ensuring this has occurred. 5 - The use of a Man-Lift as, or in lieu of, a Crane is strictly prohibited. Man-Lifts are to be used only for lifting personnel and small tools within the designed Safe Working Load. 6 - The platform is not to be loaded in excess of the designed working load; the safe working load of the platform is to be clearly displayed on both the platform, and body of the equipment. 7 - All persons inside work platforms shall wear a full-body harness attached to the designated anchor point. Personnel must stand on the floor of the working platform; standing on the handrails is strictly prohibited. Harnesses must not be attached to other structures outside of the working platform. 8 - Personnel must stay inside the working platform at all times; the platform must not be used as an access to structures. The use of staging or ladders to extend height is strictly forbidden. 9 - Securing the boom or work platform to any structure is strictly prohibited. The boom or working platform must not be rested upon on any structure, nor is the Man-Lift to be used as a jack/ prop or tie to support other structures. 10 - All Man-Lifts must be equipped with a 5kg (10lb) fire extinguisher. 11 - No man-lifts are to be operated that have had safety devices removed or disabled. Daily operator inspections are to include the testing of these devices (limit switches, alarms and hazard flashing beacons). 12 - Specific Man-Lifts are fitted with outriggers and/or stabilizers which must be used as per manufacturer's instructions. 13 - The work area surrounding the man-lift is to be cordoned off using barricades and signage if the area is used by other workers or vehicles. A full traffic management plan is required for all works involving man-lifts when working on highways. Under no circumstances is any part of a man-lift to extend or swing into a line of traffic.
Note on C16: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Does required mandatory PPE (refer specification BS, EN & ANSI) is provided, as following? > Safety helmet (see below for color scheme) > Safety glasses (shaded for outdoor work and clear inside structures and during non-daylight hours) > Safety boots (safety shoes are prohibited) > Orange hi-visibility vest 2 - Additional PPE shall be provided to a specific task 3 - Do specific PPE is provided according to their job requirement? > To work at height - Full Body harness / Fall arrest Devices / Fall Restraint Devices / V & H Lifeline etc. > To work in the confined space - Full Bodyarness, Tripod with retractable lifeline, SCBA, Masks etc. > 4 - Are the PPE stored appropriately to prevent deformation or distortion? 5 - Has self assessment being carried out for in according to the work requirements? 6 - EYEWEAR (Glasses/Goggles/Face Shields) > Eyewear cleaning supplies available. > Safety glasses in good condition and lenses free of scratches. > Goggles adjustment strap not cracked or frayed, not deformed, or lenses not > Face shields in good condition, including adjustment band, and free of scratches or 7 - HEAD PROTECTION > Hard hat bill and suspension attached as allowed by manufacturer. > is pliable, free of dents, cracks, nicks, or any damage due to impact. > Suspension maintained at 1.25 inches from inside of shell. > Suspension free of cuts or fraying, torn headband, adjustment strap workable. > Electrical hard hat matched to hazard classification. > Dated to determine whether within manufacturer’s allowable 5-year use time period. 8 - HAND PROTECTION > Available in sizes matched to employee. > Gloves free of rips tears, abrasions, or holes. > Matched to manufacturer’s specification for chemicals used onsite. > Electrical gloves matched to hazard and periodically inspected for insulating rating. > Maintained in a clean and sanitary condition, decontaminated or disposed properly. 9 - BODY PROTECTION > Available in sizes matched to employee. > Maintained in a clean and sanitary condition, decontaminated or disposed properly. > Vapor-tight fully encapsulated suits tested at required periodic intervals. > Flame-resistant clothing matched to electrical hazard and arc flash rating. > Welding gear matched to degree of hazard and free of cuts, tears or burn holes. > Flotation gear available for work near or on water and in good condition. 10 - HOT AND COLD BODY PROTECTION > Cooling gear available based on degree of heat stress hazard. > Cooling gear in operable, clean, and sanitary condition. > Cold-weather gear provided based on needs assessment. > Cold-weather gear available in sizes to match employees. > Cold-weather gear is in free of tears, rips, or holes and in maintained in a clean condition. 11 - TRAINING > Initial PPE training completed by employees. > Training conducted when new types or styles of PPE are issued. > PPE selection, use, and maintenance reviewed at daily safety briefings. 12 - Provision of impermeable clothing appropriate for the work being performed? 13 - Wearing of shorts, sleeveless shirts, loose clothing are prohibited across the MODON Projects. 14 - Clothing contaminated with grease, oils, fuels and other hazardous substances is not to be worn.
Note on T16: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a valid Excavation PTW in place? 2 - Are spoils, materials, and equipment set back at least 1.5 meters from the edge of the excavation? 3 - Are walkways and bridges over excavations structurally sound, minimum 0.5 meter in width and equipped with standard guard rails and toe boards? 4 - Are warning systems established and used when mobile equipment is operating near the edge of an excavation? 5 - Are employees prohibited from working on the faces of sloped or benched excavations above other employees? 6 - Are the exact locations of Utilities (piping, electrical, etc.) clearly marked? 7 - Are underground installations protected, supported, or removed when an excavation is open? 8 - Are ladders or other means of access and egress in place as per the PTW requirements? 9 - Are all workers within 7.6 meters of a means of access and egress to a trench? 10 - Are ALL ramps constructed of materials of uniform thickness, cleated together, equipped with no-slip surfaces? 11 - Are employees protected from cave-ins when entering or exiting excavation? 12 - Are precautions taken to protect employees from water accumulation and dewatering is being carried out? 13 - Is surface water or runoff diverted after every rainstorm or other hazard-increasing occurrence? 14 - Is the excavation classified as a confined space? If so, is their a valid confined space PTW and is the atmosphere being tested when there is a reasonable possibility of an oxygen-deficient, oxygen-enriched, combustible, toxic, or other harmful contaminant? 15 - Have materials and/or equipment chosen for shoring been based upon soils analysis, trench depth and expected loads (as per Excavation PTW)? 16 - Are shoring materials and equipment that are used for protective systems inspected and in good condition? 17 - Are damaged shoring materials and equipment immediately removed from service? 18 - Are damaged shoring materials and equipment inspected by a Registered Professional Engineer after repairs are made and before being placed back in service? 19 - Are protective systems installed without exposing employees to hazards of cave-ins, collapses, or threat of being struck by materials or equipment? 20 - Are ALL members of support systems securely fastened together to prevent failure? 21 - Are support systems provided to insure stability of adjacent structures, buildings, roadways, sidewalks, etc.? 22 - Are excavations below the level of the base or footing supported, and approved by a Registered Professional Engineer? 23 - Does back-filling progress with the removal of the support system? 24 - Is a shield system installed to prevent lateral movement? 25 - Are employees prohibited from remaining in a shield system during vertical movement?
Note on C17: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Sites are to be kept clean and tidy and free from slip, trip and fall hazards. 2 - Do all personnel trained in the importance of good housekeeping, managers, supervisors undertake regular monitoring and inspection of the workplace? 3 - Workplace are to be left clean and tidy at the end of each shift and where there is an accumulation of materials throughout the shift, at regular intervals as required to maintain a clean and safe site. 4 - Buildings under construction and nearing completion must ensure that all combustible and flammable materials are removed at the end of each shift. 5 - Nails are to be removed from timber as soon as possible, where this is not practical they are to be flattened and placed in a safe area (barrier and signs) until nails can be removed at a later time. 6 - Materials are to be stored so as they do not pose a risk to personnel stacking, removing or walking by (further guidance is given in the materials storage and handling section). 7 - All spills are to be cleaned up immediately using absorbent material. 8 - Cables/hoses/other trailing leads are to be protected, buried or secured above head height to avoid a slip trip, fall hazard. 9 - Waste is to be placed in designated containers and covered to protect against high winds, pests or risk of fire. Waste containers are to be emptied on a regular basis to prevent a build-up of material. 10 - Loose or light materials that are stored on roofs or open spaces are to be secured to prevent them from inclement weather. Location: 1 - Receptacles located inside buildings shall be kept at least 18 inches away from combustible walls and partitions. 2 - Receptacles for combustible trash that are located outside of buildings shall be placed at least 15 feet from the building or combustible material. Use: 1 - Cigarettes, cigar butts, matches, and similar potential ignition sources should never be placed in a trash receptacle. Proper receptacles for such items should be provided in areas designated for smoking. 2 - Broken glass, empty jars, scrap metal, and similar construction material should never be placed in office trash containers. A roll-off bin or other appropriate container should be used to hold construction debris. Environmental: 1 - Container storage areas shall be kept clean and free of trash. Improper disposal of food waste can attract pests and vermin. Prevention methods that do not involve the use of toxic chemicals is the preferred method of pest control. 2 - Outdoor containers should be kept covered when not in use so as to avoid attracting pests and to prevent the entry of water. Dripping or leaking trash containers may violate local storm water quality discharge regulations. 3 - Promote recycling by contracting with a waste removal company that provides reuse as part of the waste processing or by providing segregated bins for the collection of office paper, aluminum cans, plastic bottles, and toner cartridges. Rinse empty cans and bottles of sugar-based soda so as not to attract ants and other pests. 4 - Proper lighting (indoor) or during Night Shift are provided. Accurately installed. No impairement or poor visibilty is generated. No shadow due to installation of lights are presents.
Note on T17: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Permit is taken for confined space entry and all recommended precautions are in place. 2 - Operatives are trained and fit for the specified job. 3 - Confined space is well ventilated by means of mechanical ventilation. (Exhaust fan, blowers, low velocity air hose etc.). 4 - Rescue system (Tripod with hoisting device, Rescue Harness etc.) in place and sufficient trained persons are available for the rescue operation. 5 - Safe access is available for rescue operation. (Manhole size - Min. 450 mm X 407 mm or 457 mm Dia.) 6 - Atmospheric monitoring conducted and confined space is safe to enter. Percentage of gas concentration will be monitored and recorded every 4 hrs. A. Oxygen percentage. (Permissible limit – 19.5% to 23.5%) B. Flammable gas or vapors.(Permissible limit - <10% of LFL) C. Carbon Monoxide. (Permissible limit - <50ppm) D. Hydrogen sulfide.(Permissible limit - <10ppm) E. Any other toxic gas or vapors. _______________________________ 7 - Minimum two persons shall be assigned to work in the confined space. One person will remain in the entrance at all times to monitor the work 8 - All persons shall wear safety harness, which should be connected to safety line from outside at all times. 9 - All electrical equipment & leads are free from damage and guards in place. 10 - All electrical tools & equipment are connected through ELCB. 11 - Compressed gas cylinders are kept outside the confined space. 12 - supervisor / Foreman will be available at all time to monitor the work and for the rescue operation. 13 - Tool box talk conducted for the entire team and they are well aware of the risks. 14 - Proper communication system is available in between persons inside and standby person. 15 - Trained First aider with first aid kit will be available when working in the confined space. 16 - Confined space entry register is available and shift records will be maintained. -
Note on C18: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Combustible: 1 - Ensure oily rags, combustible material and other flammable substances which may ignite are not accumulated and that they are removed without delay to the designated disposal / storage area. 2 - Combustible materials shall not be stored within 20 feet (6.1 meters) of compressed gas cylinders. 3 - Safety cans used for dispensing combustible liquids shall be kept at a point of use 4 - Storage rooms for combustible liquids must have explosion-proof light fixtures 5 - No flames - hot work or smoking is be permitted in combustible liquid storage areas. Flammable: 1 - Adequate training in the use and storage of flammable liquids is in place. 2 - Storage of Flammable liquids in accordance with NFPA approved flammable storage lockers or in low value structures at least 50 feet from any other structure. 3 - Do not store other combustible materials near flammable storage areas 4 - Bulk drums of flammable liquids must be grounded and bonded to containers during dispensing 5 - Portable containers of gasoline or diesel are not to exceed 5 gallons 6 - Safety cans used for dispensing flammable liquids shall be kept at a point of use 7 - Appropriate fire extinguishers are to be mounted within 75 feet of outside areas containing flammable liquids, and within 10 feet of any inside storage area for such materials. 8 - Storage rooms for flammable liquids must have explosion-proof light fixtures 9 - No flames - hot work or smoking is be permitted in flammable or combustible liquid storage areas. 10 - Flammable liquid transfer areas are to be separated from other operations by distance or by construction having proper fire resistance. 11 - When not in use flammable liquids shall be kept in covered containers. 12 - Flammable materials are considered hazardous and as such, material safety data sheets and appropriate hazard communication training for affected employees is required 13 - Maintain high levels of housekeeping, particularly with relations to flammable materials. 14 - Where flammable materials are handled in the course of work, safe work procedures must be prepared and documented with reference made to the Material Safety Data Sheets (MSDS‘s) for the materials concerned. 15 - All people handling, working with or in control of flammable substances must be properly trained and supervised (documentation to be maintained). 16 - Lead, dust, fumes and vapor constitute a major health hazard to workers. Hazardous Substances COSHH 1 - Under COSHH the risk presented by any hazardous substance assessed using hierarchy of control, stored, transported, created or disposed and usage at the workplace; > Very toxic or toxic: Substances that, in low quantities, cause death or acute or chronic damage to health when inhaled, swallowed or absorbed via the skin > Harmful: Substances that may cause death or acute or chronic damage to health when inhaled, swallowed or absorbed via the skin > Corrosive: Substances that may, on contact with living tissues, destroy them > inhalation into the lungs, when the substance is in the form of a gas, vapor, fume, mist, aerosol or dust > absorption through the skin or eyes by contact with a substance that can penetrate unbroken skin, or is absorbed through unprotected cuts or grazes > injection by contact with contaminated sharp objects or high-pressure equipment, e.g. water jetting > ingestion by swallowing particles of a hazardous substance resulting from hand-to- mouth transfer
Note on T18: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are regular and frequent fire safety inspections carried out? 2 - Have a sufficient number of fire marshals/evacuation officers been appointed? 3 - Are water supplies adequate? 4 - Does the building or site have a written fire procedure? 5 - Is there an effective permit to work system in operation for all hot work and other fire related work? 6 - Do all doors from areas from which a large number of people may have to escape open in the direction of travel? 7 - Do all emergency exit doors (i.e. doors not in normal use) have clear instructions displayed on how to open? 8 - Are all escape routes clear and unobstructed? 9 - Are all fire exit doors correctly signed? 10 - Is all fire fighting equipment immediately visible or correctly signed? 11 - Are all flammable and explosive substances adequately signed to indicate their presence and danger? 12 - Where necessary, is there a sufficient number of emergency lights to adequately illuminate all internal escape routes, exit doors and signs? 13 - Where automatic fire detection is deemed to be necessary is there an adequate number of detectors in the critical areas? 14 - Where the means of raising the alarm is by hand-operated devices, can the operation of one device be heard throughout the entire building or site? 15 - Is there an adequate number of fire extinguishers in the building? 16 - Is there firefighting equipment other than extinguishers in the building? 17 - Are all electrical circuits and fixed electrical installations examined and tested at an acceptable frequency? 18 - Is housekeeping to an acceptable standard? 19 - Have all staff been trained in fire procedures in the last twelve months? 20 - Are all fire drills adequately recorded?
Note on C19: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - General construction waste streams generated including; > Asphalt, cable, timber, paving, roof sheeting, tiles, plastic sheeting and brickwork. > Excess concrete, spoil material from excavations. > General waste, such as putrescible food scraps and packaging from workers. > General (food) waste, construction/concrete waste, hazardous waste, paper/cardboard and waste water/sewage. 2 - Are hazardous waste identified with hazardous Waste label. 3 - Containers are properly labeled in according to their contents. 4 - Container inspections are documented in writing using the Container Inspection Checklist. 5 - Weekly inspections logged into book using the Accumulation Area Inspection Log Sheet. “NO SMOKING OR OPEN FLAME” sign posted. 6 Disposal facilities identified, evaluated using the procedures. 7 - Disposal facility accepted waste and issue approval letter. 8 - Waste transfer/dispose tracked using Waste Tracking Form. 9 - Waste streams, such as asphalt and concrete, to be recycled should be segregated and separately stored. 10 - Spill Release Contingency: 1 - Prior to beginning operations, ensure that on-site spill response capabilities (containment and personal protective equipment) are consistent with task requirements described in job hazard analysis.
Note on T19: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: HHE is required at all locations where chemical hazards exist, such as; storing, transferring and handling facilities, under routine conditions. The HHE scope shall include the physical, chemical, radiological, and biological health hazards. Physical health hazards include elevated noise and vibration exposures, repetitive motion work operations, ionizing and non-ionizing radiation exposures heat and cold stress and biological hazards include infectious disease agents. HHE shall be performed before the site mobilization; 1 - Is the adequate eating or mess area is provided and sufficient for number of workers? 2 - Are sufficient tables and Chair are provide and Kept Clean? 3 - Are FEs, signs, pest control being implemented? 4 - Is washing Area sufficient and Kept Clean? 5- Cooking Area Kept Clean? 6 - L.P.G. Cylinder stored outside, secured & upright 7 - Sufficient drinking water provided. Filters changed (as per manufacturer recommendation)? 8 - Sufficient toilets, washbasins, cleaned/disinfectant provided? 9 - Provision of First Aider 10 - Provision of Nurse 11 - Provision of First Aid Kit 12 - Provision of site clinic with required first aid equipment and items. 13 - Provision of shaded area on the workplace 14 - Provision of Ambulance or an equal arrangement in place" 15 - Smoking area is Prohibited other than designated smoking areas, clear of flammable and combustible materials? 16 - All toilets, washing, rest and eating facilities to be kept clean, hygienic and be well maintained at all times? 17 - Waste Management - Covered bins, emptied daily, close proximity, color coded etc.? 18 - Are the monitoring, including integrated air sampling, noise dosimetry and other exposure assessments, being carried out? 19 - Are the Physical, chemical, and biological stresses, being identified, results are taken with action level to prevent sickness, impaired health, significant discomfort, or inefficiency in workers? 20 - Are WEL, LEL, OEL PEL & TLV linked to control workers airborne exposure to a chemical in a concentration above which is likely to cause death or immediate or delayed permanent adverse health effects or prevent escape from such an environment, if bening implemented?
Note on C20: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Is the hierarchy of Control is beng carried out on the following and recorded; 1 - Exposure to Chemical; e.g. - Dust, Gas, Mist, Vapor 2 - Exposure to Radiation; e.g. - Pipe radiography etc. 3 - Exposure to Biological Hazard; e.g. - Bloodborne pathogens / Legionella / Leptospirosis 4 - Exposure to noise; e.g. Loss of hearing / Physical damage to hearing mechanism 5 - Heat and cold stress work; e.g. - Heat-stroke, Heat stress / Frostbite / 6 - Repetitive Motion Work; e.g. - Musculoskeletal disorder, awkward position etc. 7 - Is the risk assessment carried out on the hazardous material and covering the following; > Allowable exposure limits, > Exposure monitoring requirements, > Methods of compliance for potential over exposure conditions, > Medical surveillance program, > Hazard communication, employee training requirements, 8- Is the IH Surveillance Plan should being implemented and have rocored on the following; > Which exposure groups require IH monitoring and medical surveillance > Specific substances or agents to be monitored, > The OELs to be used to evaluate results > The statistical basis to continue or cease monitoring > Specific medical testing/protocol to be implemented 9 - Do we've program on identifies work conditions such as the following, the exposure must first be mitigated or work shall not be performed. > Oxygen concentrations less than 19.5% or greater than 23.5%, or > Atmospheres greater than 1% of the Lower Explosive Limit, or > Atmospheres that are >50% of Immediately Dangerous to Life or Health (IDLH) concentrations, or > Work with sensitizers or known human carcinogens, mutagens, or teratogens without process isolation or fully encapsulating personal protection, or > Work with highly infectious biological agents without process isolation
Note on T20: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are all dispensing areas diked or properly graded to control drainage of spilled fuel? 2 - are all workers and operatives are trained to use spill response kit? 3 - Is the procedure in place for collecting and/or containing, and disposing of spilled materials? 4 - All tanks & vessels areas are diked to contain accidental spills?. 5 - Do measures taken to prevent an accidental contaminated runoff from construction , operation, maintenance, plant and storage areas? 6 - Do measures taken to control on deposits of oils, greases and fuels, from site plant and vehicle operations, mechanical failures, spillages and discharges to ground or drains and the dispersion of unattended spills by plant / vehicle movements?. 7 - Do measures taken to control on fuels, oils and other hazardous chemicals spilled on site during re-fueling, storage or transport operations?. 8 - Do we have an Emergency Response Procedure will be followed in the event of environmental emergency such as an oil or chemical spill? 9 - Is there a procedure for concrete wash, clean and dispose to prevent ground contamination, such as; Concrete wash pits with leak proof sedimentation tanks will be provided for washing concrete mixer trucks. The design and location of such wash pits shall be agreed with the Project Manager prior to its construction on site. Concrete dumping or spillages of any kind shall not be allowed in any other location on site? 10 - Is there a procedure to used in the situation of a major spills that will have an impact on the surrounding environment will be promptly reported to the Fire Brigade? 11 - Are there a procedure of disposing off any damage/leakage drums or containers shall be removed in accordance with the local requirements? 12 - Are there a procedure of dealing with spilled contaminated soils, resulted and remediated, accordingly? 13 - Are all personnel trained in the use of spill procedure and response and the adequate spill kits are available on site?
Note on C21: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - All electrical extension cords are equipped with nonconductive plugs 2 - Cords must not be spliced or draped over nails, metal objects 3 - The use of extension cords by means of multiple outlet plugs from single outlets is prohibited 4 - All electrical service removals, alterations and equipment installations are performed by an authorized electrician 5 - Faulty electrical installation 6 - Electrical supply disruption 7 - Exposed cables 8 - Trip / fall hazards from installed cables 9 - Fire hazard Electrical overload 10 - electrocution 11 - Electrical (short circuit) - Contact with exposed conductors or a device that is incorrectly or inadvertently grounded, such as when a metal ladder comes into contact with power lines 12 - Electrical - (static discharge) 13 - Electrical Fire - Use of electrical power that results in electrical overheating or arcing to the point of combustion or ignition of flammables, or electrical component damage 14 - Improper grounding 15 - Damaged insulation 16 - Exposed electrical parts 17 - Overloaded circuits 18 - Inadequate wiring 19 - Wet conditions 20 - Overhead power lines 21 - Damaged tools and equipment
Note on T21: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a meaningful and an effective consultation and communication on health and safety matters being implemented through out the project? 2 - Is the Consultation and communication on health and safety matters in place through the following mechanisms: > Project specific induction - (prior to commencement of contracted work) > Work activity Induction (in SWMS or equivalent) - (prior to commencement any construction work) > Toolbox Meetings - (Monthly intervals or generally when there is the introduction of a new process (SWMS) or when discussing OHS issues/topics). > Subcontractor Meetings - (weekly) > Project team meetings - (weekly) > HSE Committee Meeting - (as agreed with the HSE Committee) > OHS Report - (monthly) > Project Notice Board and general signage - (as required) 3 - Is there a method of communication is to be established in the work procedures to allow constant monitoring of those persons working in the confined space? 4 - Is there a material safety data sheets and appropriate hazard communication training for affected employees is in place? 5 - Are all environmental aspects and impacts been communicated to employees? 6 - Dose the notice
Note on C22: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1- Check that all the workers are using safe hand tools/power tools and instruct them to operate and maintain the same in safe manner 2 - Ensure power tools and hand tools are checked prior to issue 3 - Damaged tools and equipment 4 - Electrical tools or electrical equipment are not to be issued for use until inspected. 5 - Electrical tools or electrical equipment are not to be issued for use until inspected. 6 - "Defective" electrical tools and equipment are to be tagged and removed from service until repaired and inspected 7 - The frequency for inspection of construction electrical tools and electrical equipment shall be monthly and inspection indicated by attached color-coded tape or color- coded tie wraps and a color coded inspection tag with Contractor‘s name, the supervisor, the inspection date, equipment number and signature of competent inspector displayed on the tag. 8 - Checking the cords for worn or cracked insulation. 9 - Checking the cords entry to plug and tool housing for frayed or worn insulation and strain relief. 10 - Checking the plug prongs for damage. 11 - Checking the plug for exposed connectors 12 - Checking the equipment housing for damage. 13 - Checking trigger locks to ensure they have been removed 14 - Checking the leads for signs of wear, poor connections at probes, etc. 15 - Checking the housing and the readout window for cracks, loose screws, etc. 16 - Check all Ground Fault Circuit Interrupters (GFCI) during the monthly inspections. 17 - Machines are free from any defects / damage. 18 - Pressure switch and safety guards in place where applicable. 19 - Leads are fitted with correct plugs & sockets and free from damages. 20 - Leads wires are free from joints, cuts and other defects. 21 - Leads are suitably rated for the electric current. 22 - Machines / Tools are equipped with properly functioning dead man switch. 23 - Tools issue and maintenance record is properly maintained. 24 - Tools are correctly stored. 25 - Discarded Tools / cords are marked and stored separately.
Note on T22: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is the Project HSE Plan presents actions, responsibilities, protocol, conformance, verification and containment activities to be undertaken by project staff and sub-contractors at all times during the construction phase of the project. 2 - Is the implementation of the HSE plan is being monitored, evaluated for accuracy and any changes made communicated to all relevant personnel. 3 - Is the HSE Plan, CEMP, Security Plan, HAZcomm., standards & procedures are updated, signed, approved and distributed, acknowledged to the construction team's responsible individuals? 4 -Is the project overall safety risk register developed, approved and being implemented?
Note on C23: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Immediate Postural and Load Factor; 1- Is the body position stable? 2 - Is the trunk of the body straight (not twisted)? 3 - Is the operation carried out by one person? 4 - Is the load kept close to the body? 5 - Can the handler avoid stretching upwards? 6 - Can the handler avoid a prolonged period in one posture? 7 - Can the handler perform the task without overreaching? 8 - Are both hands used for grasping? 9 - Are the hands less than a shoulder width apart? 10 - Is the load positioned centrally in front of the body? 11 - Is the load reasonably symmetrical? 12 - Is the load stable and easy to grasp? 13 - Can handlers move and position themselves freely? Environmental Risk Factor; 1 - Too hot? 2 - Too cold? 3 - Too bright? 4 - Too dark? 5 - Too noisy to allow effective communication? 6 - Too wet? 7 - Slippery underfoot? 8 - Does any personal protective equipment interfere with the task? Carrying; 1 - Is the load carried at knuckle height? 2 - Is the load carried at arm's length from the body? 3 - Is the load carried for more than 10 meters? Seated Work; 1 - Is the load lifted from below thigh height? 2 - Is the load lifted to above shoulder height? 3 - Is the load lifted at arm's length from the body? 4 - Does the handler have to twist significantly to the side? 5 - Is the load heavier than 5kg? Pushing and Pulling; 1 - Does the pushing and pulling take place below knuckle height? 2 - Does the pushing and pulling take place above shoulder height? 3 - Is the initial or maximum force required to push or pull the load more than 25kg? 4 - Is the continuous force required to keep the load in motion more than 10kg?
Note on T23: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a system of proper HSE reporting in place, such as; all work-related incidents including near misses, injuries, illnesses, property damage, environmental incidents, security events and motor vehicle incidents, using proper protocol followed? 2 - Is the HSE incidents, accident, near misses, unsafe acts/conditions and dangerous occurrences are being reporting in timely manner and in the approved company format? 3 - Are the workers informed, trained in reporting all near misses, unsafe acts/conditions to the appropriate authority or line of manager? 4 - Is the Weekly / Monthly HSE Statistics data, including (leading & lagging) indicators, reviewed by the senior management?
Note on C24: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: CHECKS; 1 - Plant guarding is in place and in good condition to prevent injury from parts disintegrating or failing 2 - Access and egress is in good condition, hand holds, ladder etc. are sound and in place 3 - Operator's seat and controls are in good condition and all safety devices (limiters and indicators) are labelled and fully operational. 4 - Operator's manual / instructions supplied by the manufacturer of the plant are available in the plant. 5 - Hazards with the use of the plant are identified, i.e. Safe working limits on batters, operator safety instructions etc., are displayed clearly in the cabin of the plant for operator reference. I.E. PLANT SPECIFIC RISK ASSESSMENT. 6 - Hazard controls, i.e. seat belts must be worn and hearing protection must be worn, caution/danger signs (counter weight slewing area, excavators and cranes) etc. are displayed in the cabin or on the plant in a position relevant to the hazard. 7 - Operator cabin/work platform access is clean and free of debris, loose tools, equipment, grease oil and is in an orderly condition. 8 - Plant is clean and free from oil leaks and oil build up. 9 - Plant Pre Start inspection is complete and a record of the inspection will be provided at commencement on the site. 10 - Certification of operator / proof of competency. 11 - Operational Noise Level - Statement of conforming emission level. 12 - Plant has no areas of excessive wear or damage. Mobile plant required to have; 1 - Plant is fitted with a Roll Over Protection Structure (R.O.P.S.) and operator restraint. 2 - Plant is fitted with a front horn and reversing beeper. 3 - Plant is fitted with a rotating or flashing amber beacon. Plant used to lift Material and equipment; Backhoes, excavators, cranes and loaders used as crane from designed lifting points. The Safe Working Load of the plant item is displayed on the plant as: EITHER; A Crane Chart supplied by the manufacturer specific to the plant item in the cabin of the plant for operator reference OR; The Safe Working Load of the equipment on the boom of the loader bucket and of the dipper arm of excavators - a combination of both is required for backhoes e.g. SWL 1.2ton. Personal Lifting Equipment - (Cherry Pickers, boom lift and elevated platform) 1 - Safety Working Load is displayed on work bucket / platform. 2 - Fully body harnesses and lanyards are to be provided for personnel using the equipment. 3 - Safety Instruction for the operation of the equipment is clearly displayed in the work bucket / platform. 4 - The supplier have provided training for personnel using the platform in the safe use of the equipment
Note on T24: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Do all personnel have the correct information, instruction and training according to their role and responsibilities? 2 - Is the contractor promoting awareness of company standards and regulations among their employees on a regular basis, or when it is necessary? 3 - Do all personnel have completed basic relevant awareness training, such as; Fire Awareness Training, Heat Stress awareness Training, Safety Signs and Color Code awareness Training, Environmental Awareness Training, Using Fire Extinguisher Awareness Training, Emergency reporting Awareness Training, Unsafe Act/Conditions reporting awareness training, Evacuation Procedure Awareness Training?
Note on C25: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Crane Inspected 2 - Operator certified 3 - Lift Plan approved 4 - PTW obtained 5 - lifting equipment is suitable for the use it is being put to, marked with safe working load, properly maintained and inspected, and receives a periodic thorough examination. 6 - Are all members of the lifting operations team including the Appointed Person, Crane Drivers and Slingers / Signalers / Banksmen will be competent and have such practical and theoretical knowledge and experience as is necessary to carry out their duties. 7 - Bank man is available and certified 8 - The crane operator have a practical and theoretical knowledge of lifting operations 9 - Lifting operations will be undertaken by a minimum of three competent people the crane operator, slinger / signaler (slinger and signaler can be one person) / banks man / flagman (banks man and flagmen can be one person) and Supervisor 10 - Certification of Lifting Equipment / Lifting Gear / Lifting Devices 11 - Lifting plan prepared/approved/communicated 12 - Lifting gear (Chain sling, shackle, webbing sling, lifting clamps etc.) / devices (Chain block, Winch, Monorail etc.) are checked, inspected & tagged - ( size, length, dia, width, SWL,Condition & defects. 13 - All lifting equipment / gears have valid test certificates and are in good condition.
Note on T25: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there process of SBO for leadership to identify and reinforce safe work practices/behaviors? 2 - Is there process of SBO for leadership to identify and improve on at-risk practices? 3 - Is there process of SBO for leadership to identify and improve on practices, conditions, controls, and compliance that eliminate or reduce hazards? 4 - Is there a process of SBO for leadership to make positive, corrective, cooperative, collaborative feedback/recommendations? 5 - Is there a training program for BBST, that how to identify critical safety behavior and how to provide feedback and the number of personnel trained. 6 - Is there a program for the leadership to carry out SBO once a month or twice (depends project scope of work), and record available?

## HSE-Stat
Safety Statistics
Category | Item |  | This Week | This Month | Year to Date | Cumulative
Category | Total Hours Worked |  | 10980 | 10980 | 361964 | 361964 |  |  | 64 | 64
| Safe Hours Worked |  | 10980 | 10980 | 361964 | 361964 |  |  |  | 0
Reactive | LTI |  | 0 | 0 | 0 | 0
| MTC (Healed w/o Disability) |  | 0 | 0 | 0 | 0 |  |  |  |  | 6420
| MTC (Healed w/ Disability) |  | 0 | 0 | 0 | 0
| Near Miss |  | 0 | 0 | 0 | 0 |  | 4500
| First Aid Cases |  | 0 | 0 | 0 | 0
| Fatality |  | 0 | 0 | 0 | 0 |  |  |  | 6060
| Fire Incident Cases |  | 0 | 0 | 0 | 0
| Vehicle Incident |  | 0 | 0 | 0 | 0 | [6 empty] | 6180
| Property Damages |  | 0 | 0 | 0 | 0
Proactive | Induction Training |  | 0 | 0 | 7 | 8
| No.of Internal Training |  | 1 | 1 | 18 | 18
| No.of Internal Audit |  | 0 | 0 | 0 | 0
| No. of Toolbox Talks |  | 1 | 1 | 35 | 35
| Safety Awards/Incentives |  | 0 | 0 | 0 | 0
[7 empty] | Category | Item |  | This Week | This Month | Year to Date | Cumulative
Consultant Safety Inspection (Weekly Basis) | [6 empty] | Overall Average | 86.71%
Week Number | Date of Audit | Date Issued | Numbers Of Comments | Overall Score | Date Closed | Closure Duration | This Week Score | 94.57%
Week-1 | 2025-09-04 | 2025-09-04 | 7 | 75% | 2025-09-05 | 1
Week-2 | 2025-09-11 | 2025-09-11 | 1 | 81.82% | 2025-09-12 | 1
Week-3 | 2025-09-18 | 2025-09-18 | 2 | 82% | 2025-09-19 | 1
Week-4 | 2025-09-25 | 2025-09-25 | 2 | 81.82% | 2025-09-26 | 1
Week-5 | 2025-10-02 | 2025-10-02 | 6 | 73% | 2025-10-03 | 1
Week-6 | 2025-10-09 | 2025-10-09 | 6 | 79.55% | 2025-10-10 | 1
Week-7 | 2025-10-16 | 2025-10-16 | 5 | 79.55% | 2025-10-17 | 1
Week-8 | 2025-10-23 | 2025-10-23 | 5 | 79.55% | 2025-10-24 | 1
Week-9 | 2025-10-30 | 2025-10-30 | 1 | 81.82% | 2025-10-31 | 1
Week-10 | 2025-11-06 | 2025-11-06 | 5 | 89% | 2025-11-07 | 1
Week-11 | 2025-11-13 | 2025-11-13 | 2 | 87.5% | 2025-11-14 | 1
Week-12 | 2025-11-20 | 2025-11-20 | 2 | 87.5% | 2025-11-22 | 2
Week-13 | 2025-11-27 | 2025-11-27 | 2 | 89% | 2025-11-29 | 2
Week-14 | 2025-12-04 | 2025-12-04 | 1 | 89% | 2025-12-06 | 2
Week-15 | 2025-12-11 | 2025-12-11 | 2 | 45% | 2025-12-15 | 4
Week-16 | 2025-12-19 | 2025-12-19 | 2 | 90% | 2025-12-20 | 1
Week-17 | 2025-12-25 | 2025-12-25 | 6 | 79.55% | 2025-12-27 | 2
Week-18 | 2026-01-01 | 2026-01-01 | 5 | 79.55% | 2026-01-03 | 2
Week-19 | 2026-01-08 | 2026-01-08 | 5 | 79.55% | 2026-01-09 | 1
Week-20 | 2026-01-15 | 2026-01-15 | 1 | 81.82% | 2026-01-16 | 1
Week-21 | 2026-01-22 | 2026-01-22 | 5 | 89% | 2026-01-25 | 3
Week-22 | 2026-01-29 | 2026-01-29 | 2 | 87.5% | 2026-01-31 | 2
Week-23 | 2026-02-05 | 2026-02-05 | 2 | 87.5% | 2026-02-06 | 1
Week-24 | 2026-02-12 | 2026-02-12 | 2 | 89% | 2026-02-13 | 1
Week-25 | 2026-02-19 | 2026-02-19 | 1 | 89% | 2026-02-20 | 1
Week-26 | 2026-02-26 | 2026-02-26 | 2 | 79.55% | 2026-02-27 | 1
Week-27 | 2026-03-05 | 2026-03-05 | 2 | 79.55% | 2026-03-06 | 1
Week-28 | 2026-03-12 | 2026-03-12 | 5 | 79.55% | 2026-03-14 | 2
Week-29 | 2026-03-19 | 2026-03-19 | 2 | 81.82% | 2026-03-20 | 1
Week-30 | 2026-03-26 | 2026-03-26 | 2 | 89% | 2026-03-28 | 2
Week-31 | 2026-04-02 | 2026-04-02 | 5 | 87.5% | 2026-04-04 | 2
Week-32 | 2026-04-09 | 2026-04-09 | 18 | 60% | 2026-04-15 | 6
Week-33 | 2026-04-16 | 2026-04-16 | 1 | 87% | 2026-04-16 | 0
Week-34 | 2026-04-20 | 2026-04-20 | 2 | 86% | 2026-04-20 | 1
Week-35 | 2026-04-23 | 2026-04-23 | 2 | 88% | 2026-04-24 | 1
Week-36 | 2026-05-02 | 2026-05-02 | 1 | 93% | 2026-05-02 | 1
Week-37 | 2026-05-10 | 2026-05-10 | 2 | 95% | 2026-05-11 | 1
Week-38 | 2026-05-17 | 2026-05-17 | 1 | 93% | 2026-05-18 | 1
Week-39 | 2026-05-21 | 2026-05-21 | 2 | 95% | 2026-05-22 | 1
Week-40 | 2026-05-31 | 2026-05-31 | 0 | 95% | 2026-05-31 | 0
Week-41 | 2026-06-13 | 2026-06-13 | 1 | 95% | 2026-06-14 | 2
Week-42 | 2026-06-20 | 2026-06-20 | 1 | 95% | 2026-06-21 | 1
Week-43 | 2026-06-27 | 2026-06-27 | 1 | 95% | 2026-06-28 | 1
Week-44 | 2026-07-05 | 2026-07-05 | 2 | 95% | 2026-07-06 | 1
Week-45 | 2026-07-09 | 2026-07-09 | 12 | 0.8 | 46217 | 6
Week-46 | 2026-07-18 | 2026-07-18 | 1 | 95% | 2026-07-19 | 1
Week-47 | 2026-07-25 | 2026-07-25 | 1 | 95% | 2026-07-26 | 1
Week-48 | 2026-08-01 | 2026-08-01 | 1 | 95% | 2026-08-02 | 1
Week-49 | 2026-08-05 | 2026-08-05 | 1 | 95% | 2026-08-06 | 1
Week-50 | 2026-08-15 | 2026-08-15 | 1 | 95% | 2026-08-16 | 1
Week-51 | 2026-08-23 | 2026-08-23 | 1 | 95% | 2026-08-24 | 1
Week-52 | 2026-08-29 | 2026-08-29 | 1 | 95% | 2026-08-30 | 1
Week-53 | 2026-09-06 | 2026-09-06 | 1 | 0.95 | 46272 | 1
Week-54 | 2026-09-12 | 2026-09-12 | 2 | 95% | 2026-09-13 | 1
Week-55 | 2026-09-19 | 2026-09-19 | 1 | 95% | 2026-09-20 | 1
Week-56 | 2026-09-27 | 2026-09-27 | 1 | 95% | 2026-09-28 | 1
Week-57 | 2026-10-03 | 2026-10-03 | 2 | 95% | 2026-10-04 | 2
Week-58
Week-59
Week-60
Week-61
Week-62
Week-63
Week-64
Week-65
Week-66
Week-67
Week-68
Week-69
Week-70
Week-71
Week-72
Week-73
Week-74
Week-75
Formulas:
Year to Date = (C40+[Cumulative])

## Major Quantities
BOQ Number | Description of Item | Total Quantity | Unit of Measurement | Plan To Date | Actual To Date | Remaining Total | Variance | Variance % | Notices |  | Perf. %
31 22 00 05 | POND Excavation | 321070 | M3 | 296255 | 296255 | 24815 | 0 | 0% |  |  | 92.27%
31 22 00 01 | ROAD Excavation | 99925 | M3 | 99925 | 93475 | 6450 | -6450 | -6.455% |  |  | 93.55%
31 22 00 02 | ROAD BACKFILL | 107100 | M3 | 107100 | 81600 | 25500 | -25500 | -23.81% |  |  | 76.19%
32 22 00 03 | ROAD SUPGRADE | 72730 | M3 | 72730 | 53900 | 18830 | -18830 | -25.89% |  |  | 74.11%
33 31 00 | SEWAGE network | 8370 | M |  | 6815 | 1555 | 6815 | 81.42% |  |  | 81.42%
33 31 00 | STORM network | 15638 | M |  | 12964 | 2674 | 12964 | 82.9% |  |  | 82.9%
31 22 00 07 | BACKFILLING DIKE | 3865 | M3 |  | 3865 | 0 | 3865 | 100% |  |  | 100%
| TSE network | 12223 | M |  | 8078 | 4145 | 8078 | 66.09% |  |  | 66.09%
| POTABLE WATER network | 13221 | M |  | 8992 | 4229 | 8992 | 68.01% |  | 81600 | 68.01%
| ELECTRICAL MV | 23700 | M |  | 4998 | 18702 | 4998 | 21.09% |  |  | 21.09%
| BBC | 27310 | M3 |  | 7270 | 20040 | 7270 | 26.62% |  |  | 26.62%
| ABC | 48485 | M3 |  | 18078 | 30407 | 18078 | 37.29% |  |  | 37.29%
[6 empty] | 0 | 0 |  |  |  | #DIV/0!
[6 empty] | 0 | 0 |  |  |  | #DIV/0!
[6 empty] | 0 | 0 |  |  |  | #DIV/0!
[6 empty] | 0 | 0 |  |  |  | #DIV/0!
[6 empty] | 0 | 0 |  |  |  | #DIV/0!
[6 empty] | 0 | 0 |  |  |  | #DIV/0!
[6 empty] | 0 | 0 |  |  |  | #DIV/0!
Activity ID | Activity Name | Resource Name | Price / Unit | Budgeted Units | Actual Units | Budgeted Cost |  | Actual | 2024-01-28 | 2024-01-29 | 2024-01-30 | 2024-01-31 | 2024-02-01 | 2024-02-02 | 2024-02-03 | 2024-02-04 | 2024-02-05 | 2024-02-06 | 2024-02-07 | 2024-02-08 | 2024-02-09 | 2024-02-10 | 2024-02-11 | 2024-02-12 | 2024-02-13 | 2024-02-14 | 2024-02-15 | 2024-02-16 | 2024-02-17 | 2024-02-18 | 2024-02-19 | 2024-02-20 | 2024-02-21 | 2024-02-22 | 2024-02-23 | 2024-02-24 | 2024-02-25 | 2024-02-26 | 2024-02-27 | 2024-02-28 | 2024-02-29 | 2024-03-01 | 2024-03-02 | 2024-03-03 | 2024-03-04 | 2024-03-05 | 2024-03-06 | 2024-03-07 | 2024-03-08 | 2024-03-09 | 2024-03-10 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-17 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-23 | 2024-03-24 | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-23 | 2024-04-24 | 2024-04-25 | 2024-04-26 | 2024-04-27 | 2024-04-28 | 2024-04-29 | 2024-04-30 | 2024-05-01 | 2024-05-02 | 2024-05-03 | 2024-05-04 | 2024-05-05 | 2024-05-06 | 2024-05-07 | 2024-05-08 | 2024-05-09 | 2024-05-10 | 2024-05-11 | 2024-05-12 | 2024-05-13 | 2024-05-14 | 2024-05-15 | 2024-05-16 | 2024-05-17 | 2024-05-18 | 2024-05-19 | 2024-05-20 | 2024-05-21 | 2024-05-22 | 2024-05-23 | 2024-05-24 | 2024-05-25 | 2024-05-26 | 2024-05-27 | 2024-05-28 | 2024-05-29 | 2024-05-30 | 2024-05-31 | 2024-06-01 | 2024-06-02 | 2024-06-03 | 2024-06-04 | 2024-06-05 | 2024-06-06 | 2024-06-07 | 2024-06-08 | 2024-06-09 | 2024-06-10 | 2024-06-11 | 2024-06-12 | 2024-06-13 | 2024-06-14 | 2024-06-15 | 2024-06-16 | 2024-06-17 | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | 2024-06-22 | 2024-06-23 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-06-27 | 2024-06-28 | 2024-06-29 | 2024-06-30 | 2024-07-01 | 2024-07-02 | 2024-07-03 | 2024-07-04 | 2024-07-05 | 2024-07-06 | 2024-07-07 | 2024-07-08 | 2024-07-09 | 2024-07-10 | 2024-07-11 | 2024-07-12 | 2024-07-13 | 2024-07-14 | 2024-07-15 | 2024-07-16 | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-20 | 2024-07-21 | 2024-07-22 | 2024-07-23 | 2024-07-24 | 2024-07-25 | 2024-07-26 | 2024-07-27 | 2024-07-28 | 2024-07-29 | 2024-07-30 | 2024-07-31 | 2024-08-01 | 2024-08-02 | 2024-08-03 | 2024-08-04 | 2024-08-05 | 2024-08-06 | 2024-08-07 | 2024-08-08 | 2024-08-09 | 2024-08-10 | 2024-08-11 | 2024-08-12 | 2024-08-13 | 2024-08-14 | 2024-08-15 | 2024-08-16 | 2024-08-17 | 2024-08-18 | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-24 | 2024-08-25 | 2024-08-26 | 2024-08-27 | 2024-08-28 | 2024-08-29 | 2024-08-30 | 2024-08-31 | 2024-09-01 | 2024-09-02 | 2024-09-03 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-07 | 2024-09-08 | 2024-09-09 | 2024-09-10 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-15 | 2024-09-16 | 2024-09-17 | 2024-09-18 | 2024-09-19 | 2024-09-20 | 2024-09-21 | 2024-09-22 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27 | 2024-09-28 | 2024-09-29 | 2024-09-30 | 2024-10-01 | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-05 | 2024-10-06 | 2024-10-07 | 2024-10-08 | 2024-10-09 | 2024-10-10 | 2024-10-11 | 2024-10-12 | 2024-10-13 | 2024-10-14 | 2024-10-15 | 2024-10-16 | 2024-10-17 | 2024-10-18 | 2024-10-19 | 2024-10-20 | 2024-10-21 | 2024-10-22 | 2024-10-23 | 2024-10-24 | 2024-10-25 | 2024-10-26 | 2024-10-27 | 2024-10-28 | 2024-10-29 | 2024-10-30 | 2024-10-31 | 2024-11-01 | 2024-11-02 | 2024-11-03 | 2024-11-04 | 2024-11-05 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 2024-11-11 | 2024-11-12 | 2024-11-13 | 2024-11-14 | 2024-11-15 | 2024-11-16 | 2024-11-17 | 2024-11-18 | 2024-11-19 | 2024-11-20 | 2024-11-21 | 2024-11-22 | 2024-11-23 | 2024-11-24 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 2024-11-30 | 2024-12-01 | 2024-12-02 | 2024-12-03 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-07 | 2024-12-08 | 2024-12-09 | 2024-12-10 | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-14 | 2024-12-15 | 2024-12-16 | 2024-12-17 | 2024-12-18 | 2024-12-19 | 2024-12-20 | 2024-12-21 | 2024-12-22 | 2024-12-23 | 2024-12-24 | 2024-12-25 | 2024-12-26 | 2024-12-27 | 2024-12-28 | 2024-12-29 | 2024-12-30 | 2024-12-31 | 2025-01-01 | 2025-01-02 | 2025-01-03 | 2025-01-04 | 2025-01-05 | 2025-01-06 | 2025-01-07 | 2025-01-08 | 2025-01-09 | 2025-01-10 | 2025-01-11 | 2025-01-12 | 2025-01-13 | 2025-01-14 | 2025-01-15 | 2025-01-16 | 2025-01-17 | 2025-01-18 | 2025-01-19 | 2025-01-20 | 2025-01-21 | 2025-01-22 | 2025-01-23 | 2025-01-24 | 2025-01-25 | 2025-01-26 | 2025-01-27 | 2025-01-28 | 2025-01-29 | 2025-01-30 | 2025-01-31 | 2025-02-01 | 2025-02-02 | 2025-02-03 | 2025-02-04 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-08 | 2025-02-09 | 2025-02-10 | 2025-02-11 | 2025-02-12 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-16 | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-05 | 2025-07-06 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 45998 | 45999 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18
Total |  |  |  | 102031 | 44934.91 | 45093675 |  | 44934.91 | 21.55 | 21.55 | 21.55 | 21.55 | 21.55 |  | 21.83 | 21.83 | 21.83 | 0.27 | 0.27 | 1.46 |  | 1.46 | 1.46 | 70.33 | 70.33 | 70.33 | 112.19 |  | 112.19 | 112.19 | 59.21 | 59.21 | 59.21 |  |  | 35.32 | 35.32 | 16.44 | 16.85 | 16.85 | 0.87 |  | 0.27 | 0.27 | 0 | 0 | 0 | 189.2 |  | 189.2 | 189.2 | 141.9 | 141.9 | 141.9 | 141.9 |  | 141.9 | 141.9 | 141.9 | 141.9 | 141.9 | 141.9 |  | 141.9 | 141.9 | 141.9 | 141.9 | 141.9 | 141.9 |  | 141.9 | 141.9 | 141.9 | 141.9 | 127.2 | 126.6 |  | 126.6 | 126.6 | 126.6 | 126.6 | [5 empty] | 168.8 | 168.8 | 168.8 | 168.8 |  | 168.8 | 168.8 | 168.8 | 168.8 | 168.8 | 168.8 |  | 168.8 | 168.8 | 168.8 | 176.59 | 184.37 | 184.37 |  | 184.37 | 184.37 | 184.37 | 184.37 | 184.48 | 184.59 |  | 184.59 | 184.59 | 184.59 | 188.22 | 191.86 | 191.87 |  | 192.51 | 193.15 | 189.52 | 173.9 | 161.91 | 162.5 |  | 164.88 | 167.11 | 167.57 | 167.58 | 166.99 | 168.41 |  | 169.07 | 168.89 | 170.07 | 170.1 | 168.12 | 166.1 |  | 173.18 | 181.19 | 182.12 | 182.19 | 182.26 | 715.97 |  | 1253.81 | 1257.95 | [5 empty] | 1259.46 | 1260.97 | 1261.4 | 1257.71 | 1256.27 | 1258.96 |  | 1258.8 | 1259.08 | 1257.81 | 1253.41 | 1250.72 | 1250.72 |  | 1256.66 | 1261.05 | 1261.24 | 1262.99 | 1262.99 | 1396.73 |  | 1526.57 | 1521.77 | 1520.73 | 1520.58 | 1520.58 | 1518.2 |  | 1516.6 | 1522.61 | 1531.64 | 1535.45 | 785.51 | 35.59 |  | 28.78 | 21.94 | 21.94 | 23.84 | 25.12 | 24.42 |  | 24.2 | 36.24 | 48.4 | 52.11 | 55.84 | 55.69 |  | 42.55 | 28.38 | 33.58 | 40.48 | 41.01 | 41.81 |  | 72.51 | 274.38 | 459.01 | 471.56 | 471.46 | 467.45 |  | 464.26 | 452.44 | 444.04 | 448.3 | 448.19 | 445.73 |  | 444.97 | 442.3 | 438.04 | 260.54 | 83.03 | 78.29 |  | 43.88 | 13.3 | 197.77 | 383.29 | 383.45 | 381.68 |  | 380 | 194.34 | 8.59 | 8.59 | 8.77 | 8.69 |  | 8.43 | 8.44 |  | 8.28 | 8.96 | 9.8 |  | 9.74 | 11.69 | 13.68 | 14.81 | 15.72 | 15.51 |  | 14.14 | 15.53 | 19.42 | 22.57 | 24.53 | 27.69 |  | 35.94 | 41.52 | 42.66 | 42.76 | 53.47 | 69.64 |  | 62.96 | 58.15 | 72.8 | 112.27 | 142.58 | 129.26 |  | 127.31 | 144.73 | 105.34 | 57.11 | 64.4 | 64.56 |  | 46.25 | 41.41 | 50.63 | 54.8 | 49.72 | 44.52 |  | 47.52 | 50.57 | 39.97 | 29.71 | 37.26 | 44.53 |  | 39.58 | 33.69 | 51.95 | 91.66 | 108.72 | 106.4 |  | 107.85 | 99.66 | 92.65 | 83.03 | 72.46 | 60.56 |  | 48.38 | 45.24 | 44.94 | 57.38 | 66.43 | 97.63 |  | 122.69 | 88.44 | 64.32 | 139.59 | 214.39 | 219.2 |  | 217.1 | 215.73 | 224.41 | 153.08 | 75.72 | 77.28 |  | 77.93 | 79.36 | 76.9 | 73.16 | 71.12 | 78.67 |  | 87.82 | 87.1 | 77.2 | 62.8 | 63.13 | 66.81 |  | 64.95 | 63.67 | 51.03 | 37.85 | 33.5 | 29.9 |  | 29.85 | 28.91 | 27.97 | 23.83 | 38.57 | 58.66 |  | 38.82 | 17.75 | 17.73 | 16.56 | 15.49 | 15.6 |  | 15.6 | 15.6 | 15.59 | 15.58 | 15.59 | 14.44 |  | 18.24 | 23.21 | 23.26 | 23.31 | 23.31 | 23.31 |  | 32.13 | 40.95 | 40.95 | 44.56 | 44.66 | 41.15 |  | 41.15 | 37.19 | 33.23 | 40.64 | 48.13 | 48.21 |  |  | 49.78 | 51.42 | 51.48 | 55.47 | 49.97 |  | 30.38 | 30.4 | 42.94 | 42.94 | 42.62 | 41.99 |  | 39.52 | 39.62 | 38.85 | 37.2 | 41.88 | 39.29 |  | 38 | 38 | 36.57 | 34.12 | 32.89 | 32.89 |  | 38.78 | 34.91 | 33.02 | 33.11 | 33.11 | 33.11 |  | 33.11 |  |  |  |  | 44.87 |  | 41.58 | 25.17 | 25.17 | 24.87 | 23.97 | 21.96 |  | 26.95 | 59.98 | 59.98 | 57.9 | 51.64 | 51.68 |  | 67.07 | 112.2 | 110.21 | 105.83 | 105.85 | 93.69 |  | 57.03 | 57.06 | 60.03 | 73 | 85.47 | 84.59 |  | 84.59 | 83.47 | 74.96 | 65.16 | 87.05 | 96.26 |  | 81.82 | 88.54 | 92.61 | 92.47 | 92.47 | 88.12 |  | 93.15 | 80.89 | 77.48 | 77.44 | 71.49 | 77.95 |  | 109.23 | 94.06 | 48.46 | 57.19 | 82.65 | 70.88 |  | 33.17 | 23.85 | 26.07 | 23.38 | 15.24 | 15.09 | [5 empty] | 15.39 | 15.14 |  | 14.41 | 15.11 | 18.47 | 23.22 | 23.21 | 23.18 |  | 31.08 | 54.77 | 54.77 | 54.77 | 58.18 | 75.04 |  | 95.06 | 128.25 | 226.95 | 228.05 | 188.29 | 69 |  | 67.01 | 57.64 | 47.52 | 46.01 | 42.06 | 43.71 |  | 43.57 | 43.5 | 43.11 | 43.31 | 43.29 | 41.84 |  | 32.36 | 16.67 | 15.57 | 18.25 | 27.31 | 29.33 |  | 29.03 | 31.79 | 29.01 | 73.54 | 71.55 | 35.98 |  | 36.5 | 38.47 | 41.74 | 49.19 | 69.2 | 126.69 |  | 100.17 | 39.12 | 41.31 | 52.36 | 55.87 | 32.83 |  | 32.65 | 32.1 | 32.1 | 33.15 | 36.26 | 36.38 |  | 36.5 | 33.19 | 23.46 | 24.23 | 23.62 | 20.59 |  | 20.57 | 31.85 | 67.01 | 82.05 | 118.49 | 121.05 |  | 117.22 | 148.48 | 243.82 | 243.97 | 242.68 | 242.22 |  | 230.75 | 238.39 | 352.51 | 355.95 | 362.35 | 359.99 |  | 359.75 | 365.12 | 378.86 |  | 321.98 | 172.61 |  | 172.81 | 173.28 | 176.82 | 182.75 | 182.4 | 190.28 |  | 207.41 | 208.55 | 188.07 | 150.81 | 207.66 | 171.87 |  | 72.23 | 98.64 | 176.75 | 173.92 | 164.68 | 135.94 |  | 135.06 | 135.74 | 134.42 | 170 | 300.86 | 333.41 |  | 335.99 | 379.73 | 335.5 | 202 | 200.23 | 241.61 |  | 366.26 | 364.93 | 373.75 | 440.86 | 526.67 | 526.62 |  | 527.57 | 500.4 | 404.75 | 388.18 | 388.38 | 351.31 |  | 231.37 | 217.45 | 244.64 | 247.28 | 254.64 | 235.11 |  | 181.35 | 181.02 | 166.1 | 123.29 | 123.29 | 121.71 |  | 108.76 | 84.11 | 83.53 | 82.26 | 82.26 | 82.26 |  | 82.26 | 96.75 | 140.23 | 140.23 | 140.23 | 140.23 |  | 140.23 | 140.23 | 140.23 | 140.23 | 140.23 | 105.17
2 Way PVC |  |  |  | 90 | 0 | 42300 |  | 0 | [584 empty] | 1.23 | 3.68 |  |  | 0.73 | 2.94 | 2.94 | 2.94 | 2.94 |  | 2.51 | 1.23 | 1.23 | 1.23 | 0.92 | [21 empty] | 0.21 |  | 0.85 | 0.85 | 0.85 | 0.85 | 2.5 | 7.45 |  | 7.59 | 8.02 | 6.87 | 3.41 | 4.07 | 5.34 |  | 3.21 | 3.21 | 3.21 | 2.64 | 0.92 | 0.92 |  | 0.92 | 0.92 | 0.69
3-outlet Fire Hydrant (2 x 2.5 inch and 1 x 4 inch) |  |  |  | 60 | 1.8 | 1043400 |  | 1.8 | [30 empty] | 0.6 | 0.6 | 0.6 | [360 empty] | 0.07 | 0.13 | 0.13 | 0.13 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.1 |  |  |  |  | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.23 | 0.5 | 0.5 |  | 0.5 | 0.56 | 0.75 | 1.09 | 2.1 | 2.19 |  | 2.44 | 2.44 | 2.44 | 2.1 | 1.09 | 1.09 | [5 empty] | 1.09 | 1.03 |  | 0.84 | 0.74 | 0.38 | 0.13 | 0.2 | 0.39 |  | 0.39 | 0.39 | 0.39 | 0.39 | 0.36 | 0.26 |  | 0.26 | 0.42 | 0.9 | 0.9 | 0.9 | 0.9 |  | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 |  | 0.9 | 0.75 | 0.29 | 0.29 | 0.29 | 0.29 |  | 0.29 | 0.29 | 0.29 | 0.22 | [14 empty] | 0.05 | 0.2 |  | 0.25 | 0.4 | 0.43 | 0.51 | 0.44 | 0.23 |  | 0.23 | 0.23 | 0.18 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.02 | [83 empty] | 0.19 | 0.75 | 0.75 |  | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.56
300 mm diameter pipe |  |  |  | 925 | 0 | 342250 |  | 0 | [202 empty] | 12.68 | 25.37 | 25.37 | 25.37 | 25.37 | 25.37 |  | 25.37 | 25.37 | 25.37 | 25.37 | 25.37 | 25.37 |  | 25.37 | 25.37 | 25.37 | 25.37 | 25.37 | 25.37 |  | 12.68 | [21 empty] | 0.57 | 1.14 | 1.14 | 1.14 | 1.14 |  | 0.57 | [16 empty] | 9.58 | 19.16 | 19.16 |  | 19.16 | 20.97 | 13.21 | 3.63 | 3.63 | 1.81 | [18 empty] | 6.5 | 13 | 13 |  | 13 | 6.5 | [10 empty] | 7.54 |  | 15.09 | 7.54 |  | 18.02 | 36.04 | 36.04 |  | 36.04 | 36.04 | 36.04 | 18.02 | [28 empty] | 10.13 | 20.25 |  | 10.13 | [20 empty] | 1.69 | 3.38 | 3.38 | 3.38 | 1.69
4 Way PVC |  |  |  | 102 | 0 | 95880 |  | 0 | [632 empty] | 0.85 | 3.4 | 3.4 |  | 6.12 | 14.28 | 14.28 | 14.28 | 14.28 | 12.41 |  | 6.8 | 6.8 | 5.1
400 mm diameter pipe |  |  |  | 1231 | 0 | 689360 |  | 0 | [202 empty] | 14.86 | 29.73 | 29.73 | 29.73 | 29.73 | 29.73 |  | 29.73 | 29.73 | 29.73 | 29.73 | 29.73 | 29.73 |  | 29.73 | 29.73 | 29.73 | 29.73 | 29.73 | 29.73 |  | 14.86 | [21 empty] | 0.67 | 1.34 | 1.34 | 1.34 | 1.34 |  | 0.67 | [16 empty] | 12.29 | 24.58 | 24.58 |  | 24.58 | 26.9 | 16.94 | 4.65 | 4.65 | 2.33 | [18 empty] | 11.8 | 23.6 | 23.6 |  | 23.6 | 11.8 | [10 empty] | 12.63 |  | 25.26 | 12.63 |  | 30.17 | 60.33 | 60.33 |  | 60.33 | 60.33 | 60.33 | 30.17 | [28 empty] | 7.65 | 15.3 |  | 7.65 | [20 empty] | 1.27 | 2.55 | 2.55 | 2.55 | 1.27
500 mm diameter pipe |  |  |  | 625 | 0 | 468750 |  | 0 | [202 empty] | 2.98 | 5.96 | 5.96 | 5.96 | 5.96 | 5.96 |  | 5.96 | 5.96 | 5.96 | 5.96 | 5.96 | 5.96 |  | 5.96 | 5.96 | 5.96 | 5.96 | 5.96 | 5.96 |  | 2.98 | [21 empty] | 0.13 | 0.27 | 0.27 | 0.27 | 0.27 |  | 0.13 | [16 empty] | 15.53 | 31.05 | 31.05 |  | 31.05 | 34 | 21.41 | 5.88 | 5.88 | 2.94 | [18 empty] | 3.05 | 6.1 | 6.1 |  | 6.1 | 3.05 | [10 empty] | 9.04 |  | 18.09 | 9.04 |  | 21.6 | 43.2 | 43.2 |  | 43.2 | 43.2 | 43.2 | 21.6 | [28 empty] | 3.34 | 6.68 |  | 3.34 | [20 empty] | 0.56 | 1.11 | 1.11 | 1.11 | 0.56
Acess Entrace Ramp |  |  |  | 2 | 0 | 70500 |  | 0 | [219 empty] | 0.2 | 0.4 | 0.4 |  | 0.4 | 0.4 | 0.2
Air V CH On pipes Dia. 160 mm |  |  |  | 3 | 0 | 28680 |  | 0 | [452 empty] | 0.02 |  | 0.08 | 0.08 | 0.08 | 0.09 | 0.15 | 0.15 |  | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.14 |  | 0.1 | 0.1 | 0.18 | 0.4 | 0.4 | 0.3
Air V CH On pipes Dia. 250 mm |  |  |  | 3 | 0 | 28680 |  | 0 | [477 empty] | 0.01 | 0.03 | 0.03 | 0.05 |  | 0.1 | 0.1 | 0.1 | 0.09 | 0.05 | 0.1 |  | 0.25 | 0.23 | 0.15 | 0.16 | 0.2 | 0.18 | [5 empty] | 0.13 | 0.12 |  | 0.11 | 0.23 | 0.23 | 0.2 | 0.15
Air V CH On pipes Dia. 315 mm |  |  |  | 1 | 0 | 9560 |  | 0 | [536 empty] | 0.01 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.03 | 0.07 |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.06 | 0.03 |  | 0.03 | 0.06 | 0.13 | 0.13 | 0.1
Air valve chamber; on 160 mm dia pipeline Depth 1.5- 3 m |  |  |  | 7 | 0 | 66990 |  | 0 | [539 empty] | 0.03 | 0.1 | 0.1 | 0.11 | 0.15 |  | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 |  | 0.13 | 0.08 | 0.08 | 0.08 | 0.13 | 0.3 |  | 0.3 | 0.3 | 0.22 | [9 empty] | 0.01 |  | 0.05 | 0.05 | 0.05 | 0.06 | 0.08 | 0.08 |  | 0.08 | 0.08 | 0.08 | 0.07 | 0.07 | 0.07 |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 |  | 0.07 | 0.09 | 0.16 | 0.16 | 0.17 | 0.2 |  | 0.2 | 0.17 | 0.07 |  | 0.07 | 0.07 |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.06 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.06 | 0.16 | 0.16 |  | 0.16 | 0.16 | 0.12
Chain link fence |  |  |  | 650 | 0 | 113750 |  | 0 | [644 empty] | 4.88 | 19.5 | 19.5 | 19.5 | 19.5 |  | 20.43 | 23.21 | 23.21 | 23.21 | 23.21 | 23.21 |  | 23.21 | 31.34 | 55.71 | 55.71 | 55.71 | 55.71 |  | 55.71 | 55.71 | 41.79
Conc. lining, incl PC & Expansion Joints |  |  |  | 3000 | 1043.41 | 4935000 |  | 1043.41 | [618 empty] | 27.69 | 110.77 | 83.07 |  |  | 27.69 | 110.77 | 110.77 | 99.69 | 66.46 |  | 66.46 | 66.46 | 66.46 | 105.23 | 221.53 | 221.53 |  | 221.53 | 221.53 | 177.22 | 44.31 | 44.31 | 68.83 |  | 142.39 | 131.32 | 98.09 | 98.09 | 98.09 | 98.09 |  | 98.09 | 73.56
Double Catch basin |  |  |  | 20 | 2.43 | 483000 |  | 2.43 | [11 empty] | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | [48 empty] | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | [5 empty] | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | [5 empty] | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.03 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.05 | 0.05 |  | 0.05 | 0.05 |  | 0.08 | 0.1 | 0.1 |  | 0.1 | 0.06 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.08 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.16 |  | 0.19 | 0.19 | 0.19 | 0.31 | 0.44 | 0.44 |  | 0.44 | 0.23 | 0.02 | 0.02 | 0.02 | 0.04 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.04 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.01 |  |  |  | 0.27 | 0.54 |  | 0.54 | 0.67 | 0.8 | 1.41 | 2.01 | 1 |  |  | 0.1 | 0.2 | 0.2 | 0.2 | 0.1 | [40 empty] | 0.02 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.06 | 0.07 |  | 0.07 | 0.07 | 0.12 | 0.17 | 0.17 | 0.17 |  | 0.08 |  |  |  | 0.01 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.01 | [251 empty] | 0.06 |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  | 0.25 | 0.19
Double swing main entrance gate |  |  |  | 2 | 0 | 117500 |  | 0 | [666 empty] | 0.17 | 0.67 | 0.67 | 0.5
Drawpit incl. cover |  |  |  | 23 | 0 | 135700 |  | 0 | [581 empty] | 0.05 | 0.2 | 0.2 | 0.24 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.39 | 0.45 | 0.45 | 0.45 | 0.42 | 0.27 |  | 0.12 | 0.2 | 0.45 |  | 0.42 | 0.3 |  | 0.2 | 0.2 | 0.17 | 0.07 | 0.07 | 0.05 |  |  | 0.28 | 0.83 |  |  | 0.46 |  | 1.93 | 2.13 | 1.65 | 1.1 | 1.1 | 0.92 |  | 0.45 | 0.7 | 0.61 | 0.33 | 0.33 | 0.33 |  | 0.32 | 0.3 | 0.3 | 0.3 | 0.25 | 0.08 |  | 0.08 | 0.08 | 0.08 | 0.06
Earthing |  |  |  | 13 | 0 | 152750 |  | 0 | [654 empty] | 0.33 | 0.98 |  |  | 0.76 | 3.03 | 3.03 | 2.49 | 0.87 |  | 0.87 | 0.65
Excavation |  |  |  | 37125 | 36754.04 | 2227500 |  | 36754.04 | [39 empty] | 189.2 |  | 189.2 | 189.2 | 141.9 | 141.9 | 141.9 | 141.9 |  | 141.9 | 141.9 | 141.9 | 141.9 | 141.9 | 141.9 |  | 141.9 | 141.9 | 141.9 | 141.9 | 141.9 | 141.9 |  | 141.9 | 141.9 | 141.9 | 141.9 | 120.97 | 120.97 |  | 120.97 | 120.97 | 120.97 | 120.97 | [5 empty] | 161.29 | 161.29 | 161.29 | 161.29 |  | 161.29 | 161.29 | 161.29 | 161.29 | 161.29 | 161.29 |  | 161.29 | 161.29 | 161.29 | 168.11 | 174.92 | 174.92 |  | 174.92 | 174.92 | 174.92 | 174.92 | 174.92 | 174.92 |  | 174.92 | 174.92 | 174.92 | 174.92 | 174.92 | 174.92 |  | 174.92 | 174.92 | 174.92 | 162.89 | 150.86 | 150.86 |  | 150.86 | 150.86 | 150.86 | 150.86 | 150.86 | 150.86 |  | 150.86 | 150.86 | 150.86 | 150.86 | 150.86 | 150.86 |  | 150.86 | 150.86 | 150.86 | 150.86 | 150.86 | 691.69 |  | 1232.52 | 1232.52 | [5 empty] | 1232.52 | 1232.52 | 1232.52 | 1232.52 | 1232.52 | 1232.52 |  | 1232.52 | 1232.52 | 1232.52 | 1232.52 | 1232.52 | 1232.52 |  | 1232.52 | 1232.52 | 1232.52 | 1232.52 | 1232.52 | 616.26
Filling |  |  |  | 16500 | 0 | 825000 |  | 0 | [165 empty] | 750 |  | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 |  | 1500 | 1500 | 1500 | 1500 | 750
Filling with imported Material |  |  |  | 1856 | 0 | 129920 |  | 0 | [225 empty] | 185.6 | 371.2 | 371.2 | 371.2 |  | 371.2 | 185.6
Flow meter chamber on 630 mm dia pipeline Depth 0- 1.5 m |  |  |  | 1 | 0.03 | 9570 |  | 0.03 | [27 empty] | 0.01 | 0.01 | 0.01 | [586 empty] | 0.01 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.02 | 0.02 |  | 0.02 | 0.04 | 0.12 | 0.12 | 0.12 | 0.09 | [27 empty] | 0 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01
LED Lumin 110 W |  |  |  | 193 | 5.79 | 675500 |  | 5.79 | [18 empty] | 0.97 |  | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | [492 empty] | 0.14 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.41 | [13 empty] | 1.27 | 5.06 |  | 6.07 | 9.08 | 9.08 | 9.08 | 8.08 | 5.9 |  | 8.41 | 7.15 | 2.51 | [19 empty] | 1.82 | 7.27 | 7.27 | 7.27 | 7.27 |  | 7.27 | 7.27 | 5.45 | [9 empty] | 0.56 |  | 2.23 | 2.23 | 1.68 | [12 empty] | 0.48 | 1.93 | 1.93 | 1.93 | 1.93 |  | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.45
Outfall 1000 |  |  |  | 1 | 0 | 18800 |  | 0 | [185 empty] | 0.03 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.18 | 0.3 | 0.16 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.01
Outfall 1400 |  |  |  | 1 | 0 | 23500 |  | 0 | [179 empty] | 0.03 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.18 | 0.3 |  | 0.16 | 0.02 | 0.02 | 0.02 | 0.02 | 0.01
Pipe encasement dia 200mm |  |  |  | 215 | 0 | 202100 |  | 0 | [316 empty] | 1.89 | 3.77 | 3.77 | 3.77 |  | 3.77 | 3.77 | 8.17 | 12.57 | 12.57 | 7.79 |  | 3.02 | 3.02 | 3.02 | 3.02 | 5 | 6.98 |  | 6.98 | 6.98 | 6.98 | 6.98 | 9.31 | 11.63 |  | 11.63 | 11.63 | 11.63 | 11.63 | 8.14 | 4.65 |  | 4.65 | 4.65 | 4.65 | 4.65 | 2.33
Pipe encasement dia 250mm |  |  |  | 215 | 0 | 202100 |  | 0 | [288 empty] | 0.64 | 1.29 | 1.29 | 1.29 |  | 1.29 | 1.29 | 1.29 | 1.29 | 1.29 | 2.02 |  | 2.76 | 2.76 | 2.76 | 2.76 | 2.76 | 2.76 |  | 1.86 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 |  | 0.97 | 0.97 | 0.48 | [6 empty] | 3.61 | 7.21 | 7.21 | 7.21 |  | 7.21 | 7.21 | 9.62 | 12.02 | 12.02 | 12.02 |  | 12.02 | 12.02 | 8.42 | 4.81 | 4.81 | 4.81 |  | 4.81 | 4.81 | 2.4 | [51 empty] | 0.97 |  | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 |  | 6.03 | 6.03 | 4.42 | 1.21 | 1.21 | 1.21 |  | 1.21 | 1.21
Pipe encasement dia 315mm |  |  |  | 215 | 0 | 202100 |  | 0 | [324 empty] | 1.08 | 2.17 | 2.17 |  | 2.17 | 2.17 | 2.17 | 4.7 | 7.22 | 7.22 |  | 4.48 | 1.73 | 1.73 | 1.73 | 1.73 | 0.87 | [44 empty] | 3.22 | 6.44 | 6.44 | 6.44 | 6.44 |  |  | 6.44 | 6.44 | 6.44 | 10.37 | 14.31 |  | 10.73 | 10.73 | 10.73 | 10.73 | 10.73 | 10.73 |  | 3.68 | 3.68 | 3.68 | 3.68 | 3.68 | 3.68 |  | 3.68 | 3.68 | 3.68 | 1.23
Pot Air V on pipes with dia(160) mm. |  |  |  | 4 | 0.12 | 11280 |  | 0.12 | [22 empty] | 0.02 | 0.02 | 0.02 |  |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | [336 empty] | 0 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 |  |  |  |  | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.02 |  | 0.07 | 0.07 | 0.07 | 0.09 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.13 |  | 0.09 | 0.09 | 0.16 | 0.37 | 0.37 | 0.28 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | [5 empty] | 0.01 | 0.01 |  | 0.01 | [156 empty] | 0.01 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.04
Pot Air V on pipes with dia(250) mm. |  |  |  | 2 | 0.06 | 5640 |  | 0.06 | [22 empty] | 0.01 | 0.01 | 0.01 |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | [336 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.01 | 0.02 | 0.02 | 0.03 |  | 0.05 | 0.05 | 0.05 | 0.04 | 0.03 | 0.05 |  | 0.12 | 0.1 | 0.07 | 0.08 | 0.09 | 0.09 | [5 empty] | 0.06 | 0.06 |  | 0.05 | 0.1 | 0.1 | 0.09 | 0.07 | [152 empty] | 0.01 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.02
Pot Air V on pipes with dia(315) mm. |  |  |  | 1 | 0.03 | 2820 |  | 0.03 | [22 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [336 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | [32 empty] | 0.01 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.03 | 0.04 |  | 0.04 | 0.06 | 0.09 | 0.09 | 0.07 | [103 empty] | 0 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
Pot Butterfly Valves Dia. 315 mm |  |  |  | 1 | 0.03 | 13630 |  | 0.03 | [22 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [336 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0.02 | 0.05 | 0.01 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.04 |  | 0.04 | 0.06 | 0.14 | 0.1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | [156 empty] | 0 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
Pot Gate Valves Dia. 160 mm |  |  |  | 12 | 0.36 | 36720 |  | 0.36 | [22 empty] | 0.05 | 0.05 | 0.05 |  |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | [336 empty] | 0.01 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 |  |  |  |  | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.26 | 0.96 | 0.96 |  | 0.96 | 0.79 | 0.26 | 0.26 | 0.26 | 0.2 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.16 |  | 0.56 | 0.46 | 0.16 | 0.12 | 0.02 | 0.02 |  | 0.06 | 0.16 | 0.16 | 0.16 | 0.13 | 0.06 |  | 0.06 | 0.06 | 0.05 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | [5 empty] | 0.02 | 0.02 |  | 0.02 | [45 empty] | 0.09 | 0.36 |  | 0.36 | 0.29 | 0.09 | 0.09 | 0.07 | [103 empty] | 0.04 | 0.15 | 0.15 |  | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.11
Pot Gate Valves Dia. 200 mm |  |  |  | 2 | 0.06 | 8460 |  | 0.06 | [22 empty] | 0.01 | 0.01 | 0.01 |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | [336 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0.07 | 0.27 |  | 0.27 | 0.27 | 0.22 | 0.07 | 0.07 | 0.07 |  | 0.05 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | [156 empty] | 0.01 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.02
Pot Gate Valves Dia. 225 mm |  |  |  | 3 | 0.09 | 18330 |  | 0.09 | [22 empty] | 0.01 | 0.01 | 0.01 |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | [336 empty] | 0 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.14 | 0.54 | 0.44 | 0.14 | 0.11 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | [5 empty] | 0.01 | 0.01 |  | 0 | [21 empty] | 0.03 | 0.13 | 0.13 | 0.13 | 0.11 |  | 0.03 | 0.03 | 0.03 | 0.03 | [125 empty] | 0.01 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.03
Pot Gate Valves Dia. 250 mm |  |  |  | 3 | 0.09 | 21150 |  | 0.09 | [22 empty] | 0.01 | 0.01 | 0.01 |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | [336 empty] | 0 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.07 | 0.27 | 0.22 |  | 0.07 | 0.06 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.07 | 0.27 | 0.27 | 0.27 |  | 0.22 | 0.07 | 0.07 | 0.07 | 0.06 | 0.01 | [5 empty] | 0.01 | 0.01 |  | 0 | [156 empty] | 0.01 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.03
Pot Gate Valves Dia. 280 mm |  |  |  | 1 | 0.03 | 8225 |  | 0.03 | [22 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [336 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.04 | 0.14 | 0.14 | 0.14 | 0.11 | 0.04 | [5 empty] | 0.04 | 0.04 |  | 0.03 | [156 empty] | 0 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
Pot HDPE 160mm 0.0 to 1.5m |  |  |  | 300 | 9 | 96000 |  | 9 | [18 empty] | 1.13 |  | 1.13 | 1.13 | 1.13 | 1.13 | 1.13 |  |  | 1.13 | 1.13 | [341 empty] | 0.33 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 |  | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 |  | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 |  |  | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 |  |  |  |  | 0.67 |  | 0.67 | 0.67 | 0.67 | 1.76 | 5.04 | 5.04 |  | 4.68 | 3.59 | 3.59 | 5.04 | 9.42 | 9.42 |  | 9.42 | 9.42 | 7.96 | 3.59 | 3.59 | 3.51 |  | 3.29 | 3.29 | 3.29 | 7.55 | 15.4 | 0.67 |  | 0.67 | 2.08 | 6.34 | 12.01 | 29.03 | 23.36 |  | 6.34 | 7.05 | 9.17 | 7.05 | 0.67 | 0.67 |  | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 |  | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.5 | [172 empty] | 0.94 | 3.75 | 3.75 |  | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 2.81
Pot HDPE 160mm 1.5 to 3.0m |  |  |  | 2300 | 99.73 | 1081000 |  | 99.73 | [18 empty] | 8.63 |  | 8.63 | 8.63 | 8.63 | 8.63 | 8.63 |  |  | 8.63 | 8.63 | [341 empty] | 2.56 | 5.11 | 5.11 | 5.11 | 5.11 | 5.11 |  | 5.11 | 5.11 | 5.11 | 5.11 | 5.11 | 5.11 |  | 5.11 | 5.11 | 5.11 | 5.11 | 5.11 | 5.11 |  |  | 5.11 | 5.11 | 5.11 | 5.11 | 5.11 |  | 3.83 | 3.83 | 3.83 | 3.83 | 3.83 | 3.83 |  | 3.83 | 3.83 | 3.83 | 3.83 | 3.83 | 3.83 |  | 3.83 | 3.83 | 3.83 | 3.83 | 3.83 | 3.83 |  | 3.83 | 3.83 | 3.83 | 3.83 | 3.83 | 3.83 |  | 3.83 |  |  |  |  | 5.11 |  | 5.11 | 5.11 | 5.11 | 5.11 | 5.11 | 5.11 |  | 16.49 | 50.61 | 50.61 | 46.82 | 35.45 | 35.45 |  | 50.62 | 96.12 | 96.12 | 96.12 | 96.12 | 84.03 |  | 47.76 | 47.76 | 47 | 44.73 | 49.34 | 63.19 |  | 63.19 | 56.36 | 31.27 | 17.43 | 16.19 | 12.5 |  | 12.5 | 12.5 | 12.5 | 10.65 | 5.11 | 5.11 |  | 5.11 | 5.11 | 5.11 | 5.11 | 5.11 | 5.11 |  | 5.11 | 5.11 | 5.11 | 5.11 | 5.11 | 3.83 | [17 empty] | 1.54 | 6.16 | 6.16 | 6.16 |  | 5.65 | 4.11 | 4.11 | 4.11 | 6.51 | 13.69 |  | 13.69 | 13.69 | 13.69 | 13.69 | 11.3 | 4.11 |  | 4.11 | 4.11 | 4.11 | 4.11 | 4.11 | 4.11 |  | 4.11 | 4.11 | 3.08 | [7 empty] | 2.75 | 11.02 | 11.02 |  | 13.77 | 16.53 | 13.77 | 55.09 | 43.15 | 7.35 |  | 7.35 | 7.58 | 8.26 | 8.26 | 8.26 | 6.2 | [102 empty] | 7.19 | 28.75 | 28.75 |  | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 21.56
Pot HDPE 200mm 1.5 to 3.0m |  |  |  | 750 | 22.5 | 412500 |  | 22.5 | [18 empty] | 2.81 |  | 2.81 | 2.81 | 2.81 | 2.81 | 2.81 |  |  | 2.81 | 2.81 | [341 empty] | 0.83 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 |  | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 |  | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 |  |  | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 |  | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 |  | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 |  | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 |  | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 |  | 1.25 |  |  |  |  | 1.67 |  | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 |  | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 |  | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 |  | 1.67 | 1.67 | 5.33 | 16.31 | 16.31 | 16.31 |  | 16.31 | 17.26 | 19.56 | 17.94 | 24.04 | 42.52 |  | 43.06 | 43.78 | 45.94 | 45.22 | 36.96 | 18.75 |  | 19.02 | 17.73 | 13.87 | 13.87 | 13.87 | 13.87 |  | 13.87 | 10.82 | 1.67 | 1.67 | 1.67 | 1.25 | [172 empty] | 2.34 | 9.38 | 9.38 |  | 9.38 | 9.38 | 9.38 | 9.38 | 9.38 | 7.03
Pot HDPE 225mm 1.5 to 3.0m |  |  |  | 550 | 16.5 | 324501.3 |  | 16.5 | [18 empty] | 2.06 |  | 2.06 | 2.06 | 2.06 | 2.06 | 2.06 |  |  | 2.06 | 2.06 | [341 empty] | 0.61 | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 |  | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 |  | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 |  |  | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 |  | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 |  | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 |  | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 |  | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 |  | 0.92 |  |  |  |  | 1.22 |  | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 |  | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 |  | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 |  | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 |  | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 |  | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 | 4.22 |  | 13.2 | 13.2 | 13.2 | 14.19 | 17.19 | 33.15 |  | 81.05 | 65.08 | 17.19 | 19.18 | 25.17 | 18.88 | [22 empty] | 0.46 | 1.84 | 1.84 | 1.84 | 1.79 | 1.64 |  | 1.64 | 2.46 | 4.92 | 4.92 | 4.92 | 4.92 |  | 4.1 | 1.64 | 1.64 | 1.6 | 1.48 | 1.48 |  | 1.48 | 1.48 | 1.11 | [126 empty] | 1.72 | 6.88 | 6.88 |  | 6.88 | 6.88 | 6.88 | 6.88 | 6.88 | 5.16
Pot HDPE 250mm 1.5 to 3.0m |  |  |  | 850 | 25.5 | 552498.7 |  | 25.5 | [18 empty] | 3.19 |  | 3.19 | 3.19 | 3.19 | 3.19 | 3.19 |  |  | 3.19 | 3.19 | [341 empty] | 0.94 | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 |  | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 |  | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 |  |  | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 |  | 1.42 | 1.42 | 1.42 | 1.42 | 1.42 | 1.42 |  | 1.42 | 1.42 | 1.42 | 1.42 | 1.42 | 1.42 |  | 1.42 | 1.42 | 1.42 | 1.42 | 1.42 | 1.42 |  | 1.42 | 1.42 | 1.42 | 1.42 | 1.42 | 1.42 |  | 1.42 |  |  |  |  | 1.89 |  | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 |  | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 |  | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 |  | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 |  | 1.89 | 5.23 | 15.25 | 15.25 | 15.25 | 15.25 |  | 15.62 | 16.74 | 16.74 | 22.3 | 39.01 | 39.01 |  | 39.01 | 39.01 | 39.01 | 36.46 | 28.81 | 23.25 |  | 6.54 | 10.27 | 21.46 | 27.66 | 46.27 | 39.6 |  | 16.23 | 6.98 | 9.31 | 6.98 | [167 empty] | 2.66 | 10.63 | 10.63 |  | 10.63 | 10.63 | 10.63 | 10.63 | 10.63 | 7.97
Pot HDPE 280mm 1.5 to 3.0m |  |  |  | 110 | 8.62 | 79200 |  | 8.62 | [18 empty] | 0.41 |  | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 |  |  | 0.41 | 0.41 | [341 empty] | 0.12 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 |  | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 |  | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 |  | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 |  | 0.18 |  |  |  |  | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 1.63 | 5.77 | 5.31 | 3.93 | 7.61 | 18.67 |  | 14.98 | 3.93 | 4.39 | 5.77 | 4.39 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.18 | [172 empty] | 0.34 | 1.38 | 1.38 |  | 1.38 | 1.38 | 1.38 | 1.38 | 1.38 | 1.03
Pot HDPE 315mm 0.0 to 1.5m |  |  |  | 175 | 5.25 | 112000 |  | 5.25 | [18 empty] | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  |  | 0.66 | 0.66 | [341 empty] | 0.19 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 |  | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 |  | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 |  |  | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 |  | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 |  | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 |  | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 |  | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 |  | 0.29 |  |  |  |  | 0.39 |  | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 |  | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 |  | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 |  | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 |  | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 |  | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 |  | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 |  | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.29 | [26 empty] | 1.1 | 4.4 |  | 4.4 | 4.4 | 4.76 | 5.86 | 9.28 | 19.54 |  | 19.54 | 16.12 | 5.86 | 4.4 | [5 empty] | 1.47 | 5.86 | 5.86 | 4.4 | [123 empty] | 0.55 | 2.19 | 2.19 |  | 2.19 | 2.19 | 2.19 | 2.19 | 2.19 | 1.64
Pot Wash out valve with dia (160) mm |  |  |  | 2 | 0.06 | 6200 |  | 0.06 | [22 empty] | 0.01 | 0.01 | 0.01 |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | [336 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0.04 |  | 0.1 | 0 | 0 | 0 | 0 | 0.02 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.04 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.05 |  | 0.14 | 0.14 | 0.14 | 0.1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | [156 empty] | 0.01 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.02
Pot Wash out valve with dia (200) mm |  |  |  | 1 | 0.03 | 4580 |  | 0.03 | [22 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [336 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0.01 | 0.04 |  | 0.04 | 0.07 | 0.07 | 0.07 | 0.06 | 0.04 |  | 0.04 | 0.07 | 0.07 | 0.07 | 0.05 | 0 | [5 empty] | 0 | 0 |  | 0 | [156 empty] | 0 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
Pot Wash out valve with dia (250) mm |  |  |  | 3 | 0.09 | 21510 |  | 0.09 | [22 empty] | 0.01 | 0.01 | 0.01 |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | [336 empty] | 0 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.03 | 0.03 | 0.04 | 0.07 | 0.07 | 0.07 |  | 0.07 | 0.07 | 0.09 | 0.17 | 0.13 | 0.06 |  | 0.14 | 0.14 | 0.14 | 0.12 | 0.07 | 0.12 | [5 empty] | 0.27 | 0.21 |  | 0 | [156 empty] | 0.01 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.03
Riprap |  |  |  | 5000 | 0 | 1300000 |  | 0 | [203 empty] | 178.57 | 357.14 | 357.14 | 357.14 | 357.14 |  | 357.14 | 357.14 | 357.14 | 357.14 | 357.14 | 357.14 |  | 357.14 | 357.14 | 357.14 | 178.57
Sewer Dia 200 mm; Depth : 1.5m - 2.5m |  |  |  | 600 | 409.75 | 282000 |  | 409.75 | [22 empty] | 2.25 | 2.25 | 2.25 |  |  | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | [233 empty] | 0.67 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 |  | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 |  | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 |  | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 |  | 1.33 | 1.33 | 1.93 | 2.54 | 2.54 | 2.54 |  | 2.54 | 2.54 | 2.23 | 1.93 | 1.93 | 1.93 |  | 1.93 | 1.93 | 2.83 | 3.74 | 3.74 | 3.74 |  | 3.74 | 3.74 | 2.53 | 1.33 | 1.33 | 1.33 |  | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 |  | 1.33 | 1.63 | 1.93 | 1.93 | 1.93 | 1.93 |  | 1.93 | 2.23 | 2.54 | 2.54 | 2.54 | 2.54 |  | 2.54 | 1.93 | 1.33 | 1.33 | 1.33 | 1.33 |  | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 |  | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 |  | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 |  | 4.73 | 8.13 | 8.13 | 8.13 | 8.13 | 8.13 |  | 8.13 | 8.13 | 8.13 | 7.12 | 6.1 | 6.1 |  | 6.1 | 6.1 | 6.1 | 13.51 | 20.91 | 20.91 |  |  | 20.91 | 20.91 | 20.91 | 20.91 | 10.46 | [12 empty] | 4.58 | 4.58 |  | 4.58 | 4.58 | 4.58 | 4.58 | 4.58 | 4.58 |  | 7.84 | 7.84 | 7.84 | 7.84 | 7.84 | 7.84 |  | 7.84 |  |  |  |  | 10.46 |  | 7.84 | [217 empty] | 1.88 | 7.5 | 7.5 | 7.5 | 7.5 |  | 7.5 | 7.5 | 7.5 | 5.63
Sewer Dia 250 mm; Depth : 1.5m - 2.5m |  |  |  | 715 | 460.09 | 357500 |  | 460.09 | [22 empty] | 2.68 | 2.68 | 2.68 |  |  | 2.68 | 2.68 | 2.68 | 2.68 | 2.68 | [233 empty] | 0.79 | 1.59 | 1.59 | 1.59 | 1.59 | 1.59 |  | 1.59 | 1.59 | 1.59 | 1.59 | 1.59 | 1.59 |  | 1.59 | 1.59 | 1.59 | 1.59 | 1.59 | 1.59 |  | 1.59 | 1.59 | 1.59 | 1.59 | 1.59 | 1.59 |  | 1.59 | 1.59 | 1.59 | 1.59 | 1.59 | 1.59 |  | 1.59 | 1.59 | 1.59 | 1.59 | 1.59 | 1.59 |  | 1.59 | 1.59 | 1.59 | 2.69 | 3.79 | 3.79 |  | 3.79 | 3.79 | 3.79 | 3.36 | 2.93 | 2.93 |  | 2.93 | 2.93 | 4.17 | 5.41 | 5.41 | 5.41 |  | 5.41 | 5.41 | 5.41 | 3.5 | 1.59 | 1.59 |  | 1.59 | 1.59 | 1.59 | 1.59 | 2.07 | 2.54 |  | 2.54 | 2.54 | 2.54 | 2.54 | 2.54 | 2.07 |  | 1.59 | 1.59 | 1.59 | 2.69 | 3.79 | 3.79 |  | 3.79 | 3.79 | 3.79 | 2.69 | 1.59 | 1.59 |  | 1.59 | 1.59 | 1.59 | 1.59 | 1.59 | 1.59 |  | 0.79 | [9 empty] | 4.59 | 9.17 | 9.17 |  | 9.17 | 9.17 | 9.17 | 9.17 | 9.17 | 9.17 |  |  | 8.02 | 6.87 | 6.87 | 6.87 | 6.87 |  | 5.15 | 5.15 | 17.69 | 17.69 | 17.69 | 17.69 |  | 17.69 | 17.69 | 17.69 | 17.69 | 17.69 | 10.02 |  | 6.18 | 6.18 | 6.18 | 6.18 | 6.18 | 6.18 |  | 8.84 | 8.84 | 8.84 | 8.84 | 8.84 | 8.84 |  | 8.84 |  |  |  |  | 11.79 |  | 8.84 | [217 empty] | 2.23 | 8.94 | 8.94 | 8.94 | 8.94 |  | 8.94 | 8.94 | 8.94 | 6.7
Sewer Dia 315 mm; Depth : 2.5m - 3.5m |  |  |  | 950 | 606.95 | 631750 |  | 606.95 | [22 empty] | 3.56 | 3.56 | 3.56 |  |  | 3.56 | 3.56 | 3.56 | 3.56 | 3.56 | [224 empty] | 1.9 |  | 3.81 | 3.81 | 3.81 | 3.81 | 3.81 | 3.81 |  | 4.86 | 5.92 | 5.92 | 5.92 | 5.18 | 4.44 |  | 4.44 | 4.44 | 4.44 | 4.44 | 4.44 | 4.44 |  | 4.44 | 9.25 | 14.07 | 14.07 | 14.07 | 14.07 |  | 14.07 | 14.07 | 8.09 | 2.11 | 2.11 | 2.11 |  | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 |  | 2.11 | 2.11 | 4.2 | 6.3 | 6.3 | 6.3 |  | 6.3 | 6.3 | 7.46 | 7.75 | 6.88 | 6.88 |  | 6.88 | 6.88 | 6.88 | 11.44 | 16 | 16.74 |  | 17.48 | 17.48 | 17.48 | 12.59 | 7.34 | 6.96 |  | 6.96 | 6.96 | 6.96 | 6.96 | 6.63 | 6.3 |  | 6.3 | 6.3 | 7.52 | 8.74 | 6.65 | 4.55 |  | 4.55 | 4.55 | 5.42 | 6.3 | 6.3 | 6.3 |  | 6.3 | 6.3 | 6.3 | 4.2 | 2.63 | 3.16 |  | 3.16 | 3.16 | 3.16 | 3.16 | 3.53 | 3.91 |  | 3.91 | 3.91 | 3.91 | 3.91 | 3.91 | 3.01 |  | 1.06 | [21 empty] | 2.72 | 5.45 | 5.45 | 5.45 | 5.45 |  | 4.09 | 4.09 | 4.09 | 4.09 | 3.81 | 3.27 |  | 3.27 | 3.27 | 3.27 | 3.27 | 3.27 | 8.35 |  | 10.9 | 10.9 | 10.9 | 10.9 | 10.9 | 10.9 |  | 10.9 | 5.81 | 3.27 | 3.27 | 3.27 | 3.27 |  | 3.27 |  |  |  |  | 5.08 |  | 7.27 | 7.27 | 7.27 | 7.27 | 7.27 | 5.45 | [212 empty] | 2.97 | 11.88 | 11.88 | 11.88 | 11.88 |  | 11.88 | 11.88 | 11.88 | 8.91
Sewer Dia 315 mm; Depth : 3.5m - 4.5m |  |  |  | 1150 | 866.07 | 920000 |  | 866.07 | [22 empty] | 4.31 | 4.31 | 4.31 |  |  | 4.31 | 4.31 | 4.31 | 4.31 | 4.31 | [233 empty] | 1.28 | 2.56 | 2.56 | 2.56 | 8.06 | 13.56 |  | 13.56 | 13.56 | 13.56 | 13.56 | 13.56 | 13.56 |  | 13.56 | 13.56 | 13.56 | 13.56 | 13.56 | 13.56 |  | 12.87 | 12.19 | 12.19 | 12.19 | 12.19 | 12.19 |  | 12.19 | 12.19 | 24.49 | 36.8 | 36.8 | 36.8 |  | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | 19.68 |  | 2.56 | 2.56 | 6.84 | 11.12 | 11.12 | 11.12 |  | 11.12 | 11.12 | 11.12 | 11.12 | 11.12 | 13.84 |  | 16.56 | 16.56 | 16.56 | 16.56 | 16.56 | 16.56 |  | 16.56 | 16.56 | 16.56 | 16.56 | 9.56 | 2.56 |  | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 |  | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 |  | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 |  | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 |  | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 |  | 1.28 | [280 empty] | 3.59 | 14.38 | 14.38 | 14.38 | 14.38 |  | 14.38 | 14.38 | 14.38 | 10.78
Sewer Dia 315 mm; Depth : 4.5m - 5.5m |  |  |  | 15 | 6.4 | 13725 |  | 6.4 | [22 empty] | 0.06 | 0.06 | 0.06 |  |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | [233 empty] | 0.02 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.16 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.24 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.37 | 0.54 | 0.54 | 0.54 |  | 0.54 | 0.54 | 0.54 | 0.54 | 0.36 | 0.18 |  | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.25 |  | 0.32 | 0.32 | 0.32 | 0.32 | 0.32 | 0.32 |  | 0.18 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.02 | [280 empty] | 0.05 | 0.19 | 0.19 | 0.19 | 0.19 |  | 0.19 | 0.19 | 0.19 | 0.14
Sewer Dia 400 mm; Depth : 3.5m - 4.5m |  |  |  | 420 | 293.04 | 390600 |  | 293.04 | [22 empty] | 1.58 | 1.58 | 1.58 |  |  | 1.58 | 1.58 | 1.58 | 1.58 | 1.58 | [233 empty] | 0.47 | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 |  | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 |  | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 |  | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 |  | 0.93 | 0.93 | 3.28 | 5.62 | 5.62 | 5.62 |  | 5.62 | 5.62 | 5.62 | 5.62 | 5.62 | 5.62 |  | 5.62 | 5.62 | 5.62 | 5.62 | 5.62 | 5.62 |  | 5.62 | 5.62 | 11.32 | 17.01 | 17.01 | 17.01 |  | 17.01 | 17.01 | 17.01 | 10.73 | 4.45 | 4.45 |  | 4.45 | 4.45 | 4.45 | 4.45 | 4.45 | 5.82 |  | 7.19 | 7.19 | 7.19 | 7.19 | 7.19 | 7.19 |  | 7.19 | 7.19 | 4.06 | 0.93 | 0.93 | 0.93 |  | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 |  | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 |  | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 |  | 0.47 | [280 empty] | 1.31 | 5.25 | 5.25 | 5.25 | 5.25 |  | 5.25 | 5.25 | 5.25 | 3.94
Sewer Dia 400 mm; Depth : 4.5m - 5.5m |  |  |  | 375 | 208.6 | 397500 |  | 208.6 | [22 empty] | 1.41 | 1.41 | 1.41 |  |  | 1.41 | 1.41 | 1.41 | 1.41 | 1.41 | [233 empty] | 0.42 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 |  | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 |  | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 |  | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 |  | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 |  | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 |  | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 |  | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 |  | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 |  | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 |  | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 |  | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 |  | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 2.93 |  | 5.02 | 5.02 | 5.02 | 5.02 | 5.02 | 5.02 |  | 5.02 | 5.02 | 5.02 | 5.02 | 5.02 | 4.72 |  | 4.01 | 3.59 | 3.59 | 3.59 | 3.59 | 3.59 |  | 8.97 | 14.36 | 14.36 | 14.36 | 14.36 | 14.36 |  | 14.36 | 7.18 | [21 empty] | 0.79 | 2.36 | 2.36 | 2.36 |  | 2.36 | 2.36 | 2.36 | 2.36 | 2.36 | 2.36 |  | 2.36 | 3.58 | 4.19 | 4.19 | 4.19 | 4.19 |  | 4.19 |  |  |  |  | 5.58 |  | 5.58 | 5.58 | 5.58 | 4.19 | [214 empty] | 1.17 | 4.69 | 4.69 | 4.69 | 4.69 |  | 4.69 | 4.69 | 4.69 | 3.52
Sewer Manhole Dia 1200 mm, Depth: 1.5 - 2.5m |  |  |  | 22 | 11.52 | 325600 |  | 11.52 | [27 empty] | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 |  | 0.08 | 0.08 | [243 empty] | 0.11 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 |  | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 |  | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 |  | 0.35 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.32 | 0.16 | 0.16 |  | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 |  | 0.15 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.09 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.12 | 0.19 |  |  | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 |  | 0.16 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 |  | 0.19 | 0.29 | 0.34 | 0.34 | 0.3 | 0.3 |  | 0.3 | 0.3 | 0.08 | 0.08 | 0.08 | 0.08 |  | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 |  | 0.08 |  |  |  |  | 0.1 |  | 0.08 | [217 empty] | 0.07 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.21
Sewer Manhole Dia 1200 mm, Depth: 2.5 - 3.5m |  |  |  | 27 | 15.08 | 617760 |  | 15.08 | [27 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 | [253 empty] | 0.04 | 0.09 | 0.09 |  | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 |  | 0.12 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 |  | 0.16 | 0.16 | 0.22 | 0.3 | 0.32 | 0.32 |  | 0.32 | 0.32 | 0.32 | 0.25 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.23 | 0.26 | 0.26 |  | 0.26 | 0.26 | 0.22 | 0.18 | 0.21 | 0.23 |  | 0.2 | 0.17 | 0.17 | 0.17 | 0.14 | 0.1 |  | 0.09 | 0.09 | 0.09 | 0.08 | 0.08 | 0.08 |  | 0.08 | 0.08 | 0.08 | 0.07 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.22 | 0.22 |  | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 |  | 0.22 | 0.22 | 0.26 | 0.35 | 0.35 | 0.35 |  | 0.35 |  |  |  |  | 0.47 |  | 0.58 | 0.93 | 0.93 | 0.93 | 0.93 | 0.74 |  | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 |  | 0.18 | 0.23 | 0.23 | 0.23 | 0.23 | 0.17 | [198 empty] | 0.08 | 0.34 | 0.34 | 0.34 | 0.34 |  | 0.34 | 0.34 | 0.34 | 0.25
Sewer Manhole Dia 1200 mm, Depth: 3.5 - 4.5m |  |  |  | 7 | 2.62 | 226800 |  | 2.62 | [27 empty] | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | [264 empty] | 0.06 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.2 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.18 | 0.08 | 0.08 | 0.08 | 0.08 |  | 0.08 | 0.08 | 0.08 | 0.07 | 0.07 | 0.07 |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.04 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | [242 empty] | 0.02 | 0.09 | 0.09 | 0.09 | 0.09 |  | 0.09 | 0.09 | 0.09 | 0.07
Sewer Manhole Dia 1200 mm, Depth: 4.5 - 5.5m |  |  |  | 6 | 1.8 | 237600 |  | 1.8 | [27 empty] | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | [264 empty] | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.05 | 0.08 | 0.08 |  | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 |  | 0.08 | 0.08 | 0.08 | 0.08 | 0.1 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.16 | 0.22 | 0.22 |  | 0.22 | 0.22 | 0.22 | 0.22 | 0.16 | 0.13 |  | 0.17 | 0.17 | 0.13 | 0.09 | 0.09 | 0.07 |  | 0.05 | 0.05 | 0.05 | 0.06 | 0.07 | 0.07 |  | 0.07 | 0.05 | 0.02 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | [242 empty] | 0.02 | 0.08 | 0.08 | 0.08 | 0.08 |  | 0.08 | 0.08 | 0.08 | 0.06
Sewer Manhole Dia 1200 mm, Depth: 5.5 - 6.5m |  |  |  | 2 | 0.24 | 93400 |  | 0.24 | [27 empty] | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | [264 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.02 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.07 | 0.09 |  | 0.09 | 0.09 | 0.09 | 0.09 | 0.06 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.02 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [242 empty] | 0.01 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.02
Sewer Manhole Dia 1200 mm; Depth < 1.5m |  |  |  | 8 | 4.4 | 98240 |  | 4.4 | [27 empty] | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | [233 empty] | 0.03 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.1 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.09 | 0.03 | 0.03 |  | 0.04 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.03 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.06 | 0.1 | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.12 | 0.14 |  |  | 0.14 | 0.14 | 0.14 | 0.19 | 0.25 |  | 0.19 | 0.19 | 0.19 | 0.19 | 0.15 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | [233 empty] | 0.03 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.08
Single Catch basin |  |  |  | 217 | 26.39 | 1944320 |  | 26.39 | [11 empty] | 1.09 |  | 1.09 | 1.09 | 1.09 | 1.09 | 1.09 | [48 empty] | 0.17 | 0.17 |  | 0.17 | 0.17 | 0.17 | 0.17 | [5 empty] | 0.23 | 0.23 | 0.23 | 0.23 |  | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 |  | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 |  | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 |  | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 |  | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 |  | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 |  | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 |  | 0.23 | 0.61 | 0.99 | 0.99 | 0.99 | 0.99 |  | 0.99 | 0.99 | [5 empty] | 0.99 | 0.99 | 0.99 | 0.99 | 0.99 | 0.99 |  | 0.99 | 0.89 | 0.79 | 0.79 | 0.79 | 0.79 |  | 0.79 | 0.79 | 0.79 | 0.79 | 0.79 | 0.79 |  | 0.79 | 0.79 | 0.79 | 0.79 | 0.79 | 0.79 |  | 0.79 | 0.79 | 1.12 | 1.45 | 1.45 | 1.45 |  | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 |  | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 |  | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 |  | 0.84 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 |  | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 |  | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 |  | 0.42 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 |  | 0.42 | 0.23 | 0.23 |  | 0.23 | 0.23 | 0.23 | 0.23 | 0.54 | 0.86 |  | 0.86 | 0.86 | 0.86 | 0.86 | 0.86 | 0.99 |  | 1.11 | 1.11 | 1.11 | 1.11 | 1.78 | 2.44 |  | 2.44 | 2.44 | 2.44 | 1.33 | 0.23 | 0.23 |  | 0.23 | 0.23 | 0.45 | 0.67 | 0.67 | 0.67 |  | 0.67 | 0.45 | 0.23 | 0.36 | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.63 | 0.76 | 0.76 |  | 1.17 | 1.57 | 2.29 | 2.34 | 1.67 | 1.67 |  | 1.55 | 1.52 | 1.6 | 1.6 | 2.03 | 2.47 |  | 2.39 | 2.3 | 2.3 | 3.55 | 4.8 | 4.8 |  | 4.8 | 4.8 | 4.8 | 2.4 | [6 empty] | 0.36 | 0.72 | 0.72 |  | 0.72 | 0.72 | 0.72 | 0.72 | 0.72 | 0.36 | [9 empty] | 0.1 | 0.2 | 0.2 | 0.2 | 0.3 |  | 0.4 | 0.54 | 0.67 | 0.67 | 0.34 |  |  | 0.07 | 0.13 | 0.13 | 0.07 | [281 empty] | 0.68 |  | 2.71 | 2.71 | 2.71 | 2.71 | 2.71 | 2.71 |  | 2.71 | 2.03
SL Pole 12 M |  |  |  | 193 | 5.79 | 2354600 |  | 5.79 | [15 empty] | 0.97 | 0.97 | 0.97 | 0.97 |  | 0.97 | 0.97 | [483 empty] | 0.14 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.74 | 1.31 |  | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 |  | 1.31 | 1.25 | 1.08 | 1.08 | 1.08 | 1.08 |  | 0.94 | 0.53 | 0.53 | 0.53 | 0.53 | 0.53 |  | 0.53 | 0.73 | 1.68 | 2.73 | 2.61 | 2.23 |  | 2.23 | 2.23 | 2.23 |  | 2.23 | 2.23 |  | 2.23 | 2.6 | 4.07 | 4.83 | 3.21 | 2.17 |  | 2.92 | 1.59 | 1.93 | 2.93 | 3.08 | 3.08 |  | 1.61 | 1.52 | 1.89 | 1.6 | 1.6 | 1.6 |  | 1.6 | 1.6 | 1.6 | 1.55 | 1.97 | 3.73 |  | 3.58 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 |  | 3.11 | 2.33 |  | 0.05 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.41 | 1.05 | 1.05 | 1.05 |  | 1.05 | 1.23 | 1.77 | 1.77 | 1.77 | 1.33 |  |  |  | 0.05 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.15 | [6 empty] | 0.48 | 1.93 | 1.93 | 1.93 | 1.93 |  | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.45
Stand. Arm. 1C 10MM2 |  |  |  | 5900 | 177 | 737500 |  | 177 | [15 empty] | 29.5 | 29.5 | 29.5 | 29.5 |  | 29.5 | 29.5 | [559 empty] | 4.92 | 19.67 | 19.67 | 19.67 | 19.67 |  | 19.67 | 34.75 | 80.01 | 80.01 | 80.01 | 80.01 |  | 80.01 | 98.87 | 155.44 | 155.44 | 155.44 | 155.44 |  | 155.44 | 158.73 | 168.59 |  | 143.7 | 69.03 |  | 69.03 | 69.03 | 74.19 | 89.69 | 89.69 | 89.69 |  | 89.69 | 89.69 | 80.64 | 45.03 | 19.67 | 21.31 |  | 26.24 | 26.24 | 26.24 | 26.24 | 26.24 | 26.24 |  | 26.24 | 26.24 | 26.24 | 26.24 | 31.71 | 46.47 |  | 44.13 | 51.9 | 51.9 | 51.9 | 51.9 | 51.9 |  | 51.9 | 61.2 | 89.08 | 95.24 | 113.71 | 113.71 |  | 113.71 | 113.71 | 112.51 | 108.91 | 108.91 | 89.29 |  | 30.81 | 31.95 | 31.95 | 31.95 | 31.95 | 28.07 |  | 16.4 | 22.77 | 41.89 | 41.89 | 41.89 | 41.89 |  | 37.79 | 25.49 | 22.09 | 11.9 | 11.9 | 11.9 |  | 11.9 | 23.67 | 59 | 59 | 59 | 59 |  | 59 | 59 | 59 | 59 | 59 | 44.25
Stand. Arm. 1C 16MM2 |  |  |  | 910 | 27.3 | 118300 |  | 27.3 | [15 empty] | 4.55 | 4.55 | 4.55 | 4.55 |  | 4.55 | 4.55 | [559 empty] | 0.76 | 3.03 | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 |  | 6.42 | 16.58 | 16.58 | 16.58 | 16.58 | 16.58 |  | 16.58 | 16.58 | 16.58 | 24.63 | 48.76 | 48.76 |  | 48.76 | 48.76 | 48 | 45.73 | 45.73 | 39.38 |  | 20.32 | 20.32 | 20.32 | 20.32 | 20.32 | 15.24 | [16 empty] | 2.28 | 9.1 | 9.1 | 9.1 | 9.1 |  | 9.1 | 9.1 | 9.1 | 9.1 | 9.1 | 6.83
Stand. Arm. 4C 16MM2 |  |  |  | 5900 | 177 | 1091500 |  | 177 | [15 empty] | 29.5 | 29.5 | 29.5 | 29.5 |  | 29.5 | 29.5 | [559 empty] | 4.92 | 19.67 | 19.67 | 19.67 | 19.67 |  | 19.67 | 34.75 | 80.01 | 80.01 | 80.01 | 80.01 |  | 80.01 | 98.87 | 155.44 | 155.44 | 155.44 | 155.44 |  | 155.44 | 158.73 | 168.6 |  | 143.7 | 69.03 |  | 69.03 | 69.03 | 65.74 | 55.87 | 55.87 | 65.74 |  | 95.33 | 95.33 | 86.28 | 59.12 | 59.12 | 50.9 |  | 26.24 | 26.24 | 26.24 | 26.24 | 26.24 | 26.24 |  | 26.24 | 26.24 | 26.24 | 26.24 | 31.71 | 46.47 |  | 44.13 | 51.9 | 51.9 | 51.9 | 51.9 | 51.9 |  | 51.9 | 46.44 | 44.8 | 95.23 | 113.7 | 113.7 |  | 113.7 | 113.7 | 112.51 | 108.91 | 108.91 | 104.05 |  | 81.46 | 57.45 | 57.45 | 57.45 | 57.45 | 53.56 |  | 41.89 | 35.52 | 16.4 | 16.4 | 16.4 | 16.4 |  | 12.3 |  | 2.97 | 11.9 | 11.9 | 11.9 |  | 11.9 | 23.67 | 59 | 59 | 59 | 59 |  | 59 | 59 | 59 | 59 | 59 | 44.25
Stand. Arm. 4C 25MM2 |  |  |  | 910 | 27.3 | 200200 |  | 27.3 | [15 empty] | 4.55 | 4.55 | 4.55 | 4.55 |  | 4.55 | 4.55 | [559 empty] | 0.76 | 3.03 | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 |  | 6.42 | 16.58 | 16.58 | 16.58 | 16.58 | 16.58 |  | 16.58 | 16.58 | 16.58 | 24.63 | 48.76 | 48.76 |  | 48.76 | 48.76 | 48 | 45.73 | 45.73 | 39.38 |  | 20.32 | 20.32 | 20.32 | 20.32 | 20.32 | 15.24 | [16 empty] | 2.28 | 9.1 | 9.1 | 9.1 | 9.1 |  | 9.1 | 9.1 | 9.1 | 9.1 | 9.1 | 6.83
Stand. Arm. 4C 35MM2 |  |  |  | 15 | 0.45 | 3750 |  | 0.45 | [15 empty] | 0.08 | 0.08 | 0.08 | 0.08 |  | 0.08 | 0.08 | [559 empty] | 0.01 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.11 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 |  | 0.27 | 0.27 | 0.27 | 0.43 | 0.91 | 0.91 |  | 0.91 | 0.91 | 0.9 | 0.86 | 0.65 | 0.08 |  | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.25 | [16 empty] | 0.04 | 0.15 | 0.15 | 0.15 | 0.15 |  | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.11
Storm 1000 mm depth: 1.5 - 2.5m |  |  |  | 485 | 370.63 | 1100950 |  | 370.63 | 1.82 | 1.82 | 1.82 | 1.82 | 1.82 |  | 1.82 | 1.82 | 1.82 | [57 empty] | 0.45 | 0.45 |  | 0.45 | 0.45 | 0.45 | 0.45 | [5 empty] | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | [5 empty] | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 4.09 | 7.57 | 7.57 | 7.57 |  | 7.57 | 7.57 | 7.57 | 8.15 | 8.73 | 8.73 |  | 8.73 | 20.92 | 33.1 | 33.1 | 33.1 | 33.1 |  | 20.1 | 7.11 | 7.11 | 7.11 | 7.11 | 7.92 |  | 8.73 | 8.73 | 8.73 | 8.73 | 8.73 | 4.67 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.3 | [375 empty] | 1.52 |  | 6.06 | 6.06 | 6.06 | 6.06 | 6.06 | 6.06 |  | 6.06 | 4.55
Storm 1000 mm depth: 2.5 - 3.5m |  |  |  | 410 | 310.75 | 1016800 |  | 310.75 | 1.54 | 1.54 | 1.54 | 1.54 | 1.54 |  | 1.54 | 1.54 | 1.54 | [57 empty] | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | [5 empty] | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | [5 empty] | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 2.57 | 4.63 | 4.63 |  | 4.63 | 4.63 | 4.63 | 4.22 | 3.81 | 3.81 |  | 3.81 | 3.81 | 10.4 | 16.98 | 16.98 | 16.98 |  | 16.98 | 10.4 | 3.81 | 3.81 | 3.81 | 3.81 |  | 4.63 | 5.45 | 5.45 | 5.45 | 5.45 | 2.98 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.26 | [37 empty] | 2.06 | 4.12 | 4.12 |  | 4.12 | 4.81 | 5.5 | 11.91 | 18.33 | 18.33 |  | 11.91 | 5.5 | 5.5 | 5.5 | 5.5 | 2.75 | [321 empty] | 1.28 |  | 5.13 | 5.13 | 5.13 | 5.13 | 5.13 | 5.13 |  | 5.13 | 3.84
Storm 1000 mm depth: 3.5 - 4.5m |  |  |  | 35 | 27.02 | 93800 |  | 27.02 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | [57 empty] | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | [5 empty] | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | [5 empty] | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.02 | [42 empty] | 0.29 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 2.25 |  | 3.91 | 3.91 | 2.25 | 0.59 | 0.59 | 0.59 |  | 0.73 | 0.88 | 0.88 | 0.88 | 0.44 | [308 empty] | 0.11 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.33
Storm 1100 mm depth: 1.5 - 2.5m |  |  |  | 50 | 11.3 | 130000 |  | 11.3 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 |  | 0.19 | 0.19 | 0.19 | [57 empty] | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | [5 empty] | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | [5 empty] | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.03 | [56 empty] | 0.84 | 1.68 | 1.68 | 1.68 | 1.68 |  | 3.63 | 5.58 | 5.58 | 3.35 | 1.12 | 1.12 |  | 1.19 | 1.26 | 1.26 | 1.26 | 0.63 | [301 empty] | 0.16 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.47
Storm 1100 mm depth: 2.5 - 3.5m |  |  |  | 472 | 360.1 | 1331040 |  | 360.1 | 1.77 | 1.77 | 1.77 | 1.77 | 1.77 |  | 1.77 | 1.77 | 1.77 | [57 empty] | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | [5 empty] | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | [5 empty] | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 4.54 | 8.5 | 8.5 |  | 8.5 | 8.5 | 8.5 | 7.71 | 6.91 | 6.91 |  | 6.91 | 6.91 | 19.56 | 32.21 | 32.21 | 32.21 |  | 32.21 | 19.56 | 6.91 | 6.91 | 6.91 | 6.91 |  | 8.5 | 10.08 | 10.08 | 10.08 | 10.08 | 5.33 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.29 | [375 empty] | 1.48 |  | 5.9 | 5.9 | 5.9 | 5.9 | 5.9 | 5.9 |  | 5.9 | 4.43
Storm 1100 mm depth: 3.5 - 4.5m |  |  |  | 300 | 229 | 912000 |  | 229 | 1.13 | 1.13 | 1.13 | 1.13 | 1.13 |  | 1.13 | 1.13 | 1.13 | [57 empty] | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | [5 empty] | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | [5 empty] | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 1.7 | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 | 2.77 | 2.5 | 2.5 |  | 2.5 | 2.5 | 6.76 | 11.01 | 11.01 | 11.01 |  | 11.01 | 6.76 | 2.5 | 2.5 | 2.5 | 2.5 |  | 3.03 | 3.57 | 3.57 | 3.57 | 3.57 | 1.97 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.19 | [49 empty] | 1.18 | 2.37 | 2.37 | 2.37 | 2.37 |  | 2.37 | 2.37 | 2.37 | 2.37 | 2.37 | 9.07 |  | 15.77 | 15.77 | 9.07 | 2.37 | 2.37 | 2.37 |  | 2.96 | 3.55 | 3.55 | 3.55 | 1.77 | [301 empty] | 0.94 |  | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 |  | 3.75 | 2.81
Storm 1200 mm depth: 2.5 - 3.5m |  |  |  | 50 | 11.3 | 144000 |  | 11.3 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 |  | 0.19 | 0.19 | 0.19 | [57 empty] | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | [5 empty] | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | [5 empty] | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.03 | [59 empty] | 0.84 | 1.68 |  | 1.68 | 1.68 | 1.68 | 3.63 | 5.58 | 5.58 |  | 3.35 | 1.12 | 1.12 | 1.4 | 1.68 | 1.68 |  | 0.84 | [298 empty] | 0.16 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.47
Storm 1200 mm depth: 3.5 - 4.5m |  |  |  | 220 | 73.71 | 682000 |  | 73.71 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 |  | 0.83 | 0.83 | 0.82 | [57 empty] | 0.21 | 0.21 |  | 0.21 | 0.21 | 0.21 | 0.21 | [5 empty] | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | [5 empty] | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.44 | 0.6 | 0.6 |  | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.65 |  | 0.71 | 0.71 | 0.71 | 1.57 | 2.44 | 2.44 |  | 2.44 | 1.53 | 0.62 | 0.62 | 0.62 | 0.62 |  | 0.71 | 0.79 | 0.79 | 0.79 | 0.79 | 0.53 |  | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.14 | [56 empty] | 1.63 | 3.25 | 3.25 | 3.25 | 3.25 |  | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 12.47 |  | 21.68 | 21.68 | 12.47 | 3.25 | 3.25 | 3.25 |  | 2.51 | 1.77 | 1.77 | 1.77 | 1.77 | 1.77 |  | 1.77 | 1.77 | 1.77 | 1.77 | 1.77 | 0.89 | [286 empty] | 0.69 |  | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 |  | 2.75 | 2.06
Storm 1200 mm depth: 4.5 - 5.5m |  |  |  | 35 | 9.46 | 116900 |  | 9.46 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | [57 empty] | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | [5 empty] | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | [5 empty] | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.08 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.26 | 0.4 | 0.4 |  | 0.4 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.08 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.3 | 0.56 | 0.56 |  | 0.54 | 0.52 | 0.52 | 0.6 | 0.69 | 0.69 |  | 2.06 | 3.44 | 3.44 | 1.98 | 0.52 | 0.52 |  | 0.52 | 0.64 | 0.77 | 0.77 | 0.77 | 0.39 | [356 empty] | 0.11 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.33
Storm 1400 mm depth: 2.5 - 3.5m |  |  |  | 100 | 22.6 | 362000 |  | 22.6 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | [57 empty] | 0.09 | 0.09 |  | 0.09 | 0.09 | 0.09 | 0.09 | [5 empty] | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | [5 empty] | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.06 | [63 empty] | 1.68 | 3.35 | 3.35 | 3.35 | 3.35 |  | 7.26 | 11.17 | 11.17 | 6.7 | 2.23 | 2.23 |  | 2.79 | 3.35 | 3.35 | 1.68 | [295 empty] | 0.31 |  | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 |  | 1.25 | 0.94
Storm 1400 mm depth: 3.5 - 4.5m |  |  |  | 250 | 56.5 | 970000 |  | 56.5 | 0.94 | 0.94 | 0.94 | 0.94 | 0.94 |  | 0.94 | 0.94 | 0.94 | [57 empty] | 0.23 | 0.23 |  | 0.23 | 0.23 | 0.23 | 0.23 | [5 empty] | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | [5 empty] | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.16 | [66 empty] | 3.14 | 6.28 |  | 6.28 | 6.28 | 7.33 | 8.38 | 14.66 | 20.94 |  | 20.94 | 20.94 | 13.26 | 5.58 | 5.58 | 5.93 |  | 6.28 | 6.28 | 6.28 | 3.14 | [288 empty] | 0.78 |  | 3.13 | 3.13 | 3.13 | 3.13 | 3.13 | 3.13 |  | 3.13 | 2.34
Storm 1400 mm depth: 4.5 - 5.5m |  |  |  | 35 | 7.91 | 249550 |  | 7.91 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | [57 empty] | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | [5 empty] | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | [5 empty] | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.02 | [71 empty] | 0.35 | 0.7 | 0.7 | 0.7 |  | 0.7 | 0.94 | 1.17 | 2.05 | 2.93 | 2.93 |  | 2.93 | 1.86 | 0.78 | 0.78 | 0.68 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.29 | [280 empty] | 0.11 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.33
Storm 400 mm depth: 1.5 - 2.5m |  |  |  | 355 | 273.12 | 237850 |  | 273.12 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 |  | 1.33 | 1.33 | 1.33 | [57 empty] | 0.33 | 0.33 |  | 0.33 | 0.33 | 0.33 | 0.33 | [5 empty] | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 1.42 | 2.39 | 2.39 |  | 2.39 | 2.39 | 2.39 | 2.39 | 2.32 | 2.26 |  | 2.26 | 2.26 | 2.26 | 5.89 | 9.51 | 9.51 |  | 9.51 | 9.51 | 5.89 | 2.26 | 2.26 | 2.26 |  | 2.26 | 2.71 | 3.16 | 3.16 | 3.16 | 3.16 |  | 1.8 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | [5 empty] | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 4.12 |  | 7.8 | 7.8 | 7.8 | 7.8 | 22.52 | 37.23 |  | 22.29 | 7.36 | 9.2 | 11.04 | 5.52 | [371 empty] | 1.11 |  | 4.44 | 4.44 | 4.44 | 4.44 | 4.44 | 4.44 |  | 4.44 | 3.33
Storm 400 mm depth: 2.5 - 3.5m |  |  |  | 95 | 21.47 | 78375 |  | 21.47 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 |  | 0.36 | 0.36 | 0.36 | [57 empty] | 0.09 | 0.09 |  | 0.09 | 0.09 | 0.09 | 0.09 | [5 empty] | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.26 | 0.4 |  | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 |  | 0.41 | 0.42 | 0.42 | 0.42 | 0.42 | 1.01 |  | 1.6 | 1.6 | 1.6 | 1.6 | 1.01 | 0.42 |  | 0.42 | 0.42 | 0.42 | 0.45 | 0.49 | 0.49 |  | 0.49 | 0.49 | 0.49 | 0.3 | 0.12 | 0.12 |  | 0.12 | 0.12 | [5 empty] | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.28 | 0.43 |  | 0.43 | 0.43 |  | 0.43 | 0.45 | 0.47 |  | 0.47 | 1.17 | 1.86 | 1.86 | 1.3 | 0.73 |  | 0.73 | 0.73 | 0.6 | 0.49 | 0.51 | 0.71 |  | 1.68 | 2.47 | 2.96 | 2.44 | 1.41 | 1.41 |  | 1.52 | 1.7 | 4.44 | 7.1 | 4.44 | 1.55 |  | 1.67 | 2 | 1 | [366 empty] | 0.3 |  | 1.19 | 1.19 | 1.19 | 1.19 | 1.19 | 1.19 |  | 1.19 | 0.89
Storm 500 mm depth: 1.5 - 2.5m |  |  |  | 380 | 252.66 | 357200 |  | 252.66 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 |  | 1.43 | 1.43 | 1.43 | [57 empty] | 0.36 | 0.36 |  | 0.36 | 0.36 | 0.36 | 0.36 | [5 empty] | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 1.11 | 1.74 | 1.74 | 1.74 | 1.74 | 1.74 |  | 1.61 | 1.48 | 1.48 | 1.48 | 1.48 | 3.5 |  | 5.52 | 5.52 | 5.52 | 5.52 | 3.5 | 1.48 |  | 1.48 | 1.48 | 1.48 | 1.74 | 1.99 | 1.99 |  | 1.99 | 1.99 | [5 empty] | 1.23 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 |  | 0.48 | 1.29 | 2.1 |  | 2.1 | 2.1 | 2.1 | 1.97 | 1.83 | 1.83 |  | 1.83 | 4.55 | 7.26 | 7.26 | 7.26 | 4.55 |  | 1.83 | 1.83 | 1.83 | 2.17 | 2.51 | 2.51 |  | 4.06 | 4.6 | 3.58 | 3.58 | 4.18 | 4.77 |  | 14.32 | 23.87 | 14.32 | 4.77 | 5.97 | 7.16 |  | 3.58 | [27 empty] | 1.36 | 2.72 | 2.72 | 2.72 | 2.72 | 5.88 |  | 9.05 | 9.05 | 5.43 | 1.81 | 1.81 | 2.26 |  | 2.72 | 2.72 | 1.36 | [317 empty] | 1.19 |  | 4.75 | 4.75 | 4.75 | 4.75 | 4.75 | 4.75 |  | 4.75 | 3.56
Storm 500 mm depth: 2.5 - 3.5m |  |  |  | 110 | 79.67 | 118800 |  | 79.67 | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 |  | 0.41 | 0.41 | 0.41 | [57 empty] | 0.1 | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.1 | [5 empty] | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | [5 empty] | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.07 |  |  |  | 1.38 | 2.76 |  | 2.76 | 2.76 | 3.22 | 3.69 | 11.06 | 18.43 |  | 11.06 | 3.69 | 4.61 | 5.53 | 2.76 | [357 empty] | 0.34 |  | 1.38 | 1.38 | 1.38 | 1.38 | 1.38 | 1.38 |  | 1.38 | 1.03
Storm 500 mm depth: 3.5 - 4.5m |  |  |  | 50 | 11.3 | 61250 |  | 11.3 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 |  | 0.19 | 0.19 | 0.19 | [57 empty] | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | [5 empty] | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | [5 empty] | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.03 | [8 empty] | 0.63 | 1.26 | 1.26 | 1.26 |  | 1.47 | 1.68 | 5.03 | 8.38 | 5.03 | 1.68 |  | 2.09 | 2.51 | 1.26 | [352 empty] | 0.16 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.47
Storm 600 mm depth: 1.5 - 2.5m |  |  |  | 465 | 374.24 | 492900 |  | 374.24 | 1.74 | 1.74 | 1.74 | 1.74 | 1.74 |  | 1.74 | 1.74 | 1.74 | [57 empty] | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | [5 empty] | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 2.49 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 |  | 4.4 | 4.27 | 4.14 | 4.14 | 4.14 | 4.14 |  | 11.26 | 18.38 | 18.38 | 18.38 | 18.38 | 11.26 |  | 4.14 | 4.14 | [5 empty] | 4.14 | 4.14 | 4.59 | 5.03 | 5.03 | 5.03 |  | 5.03 | 5.03 | 2.81 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 1.84 | 3.1 | 3.1 |  | 3.1 | 3.1 | 2.89 | 2.68 | 2.68 | 2.68 |  | 6.89 | 11.09 | 11.09 | 11.09 | 6.89 | 2.68 |  | 2.39 | 2.1 | 2.63 | 3.15 | 3.15 | 3.15 |  | 1.58 | [6 empty] | 0.93 | 1.85 | 1.85 | 1.85 | 2.16 | 2.47 |  | 7.42 | 12.36 | 7.42 | 2.47 | 2.47 | 2.47 |  | 2.47 | 1.24 | [346 empty] | 1.45 |  | 5.81 | 5.81 | 5.81 | 5.81 | 5.81 | 5.81 |  | 5.81 | 4.36
Storm 600 mm depth: 2.5 - 3.5m |  |  |  | 110 | 86.86 | 24200 |  | 86.86 | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 |  | 0.41 | 0.41 | 0.41 | [57 empty] | 0.1 | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.1 | [5 empty] | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | [5 empty] | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.07 | [17 empty] | 1.38 | 2.76 |  | 2.76 | 2.76 | 3.22 | 3.69 | 11.06 | 18.43 |  | 11.06 | 3.69 | 3.69 | 3.69 | 3.69 | 1.84 | [342 empty] | 0.34 |  | 1.38 | 1.38 | 1.38 | 1.38 | 1.38 | 1.38 |  | 1.38 | 1.03
Storm 600 mm depth: 3.5 - 4.5m |  |  |  | 50 | 11.3 | 68500 |  | 11.3 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 |  | 0.19 | 0.19 | 0.19 | [57 empty] | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | [5 empty] | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | [5 empty] | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.03 | [22 empty] | 0.63 | 1.26 | 1.26 | 1.26 |  | 1.47 | 1.68 | 5.03 | 8.38 | 5.03 | 1.68 |  | 1.68 | 1.68 | 1.68 | 0.84 | [337 empty] | 0.16 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.47
Storm 700 mm depth: 1.5 - 2.5m |  |  |  | 300 | 226.57 | 420000 |  | 226.57 | 1.13 | 1.13 | 1.13 | 1.13 | 1.13 |  | 1.13 | 1.13 | 1.13 | [57 empty] | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | [5 empty] | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 1.67 | 2.96 | 2.96 | 2.96 | 2.96 |  | 2.96 | 2.7 | 2.44 | 2.44 | 2.44 | 2.44 |  | 6.57 | 10.71 | [5 empty] | 10.71 | 10.71 | 10.71 | 6.57 | 2.44 | 2.44 |  | 2.44 | 2.44 | 2.96 | 3.47 | 3.47 | 3.47 |  | 3.47 | 1.92 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 1.84 | 3.31 | 3.31 | 3.31 |  | 3.31 | 3.06 | 2.82 | 2.82 | 2.82 | 7.7 |  | 12.4 | 12.21 | 12.21 | 7.33 | 2.44 | 2.44 |  | 2.44 | 3.05 | 3.66 | 3.66 | 3.66 | 1.83 | [363 empty] | 0.94 |  | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 |  | 3.75 | 2.81
Storm 700 mm depth: 2.5 - 3.5m |  |  |  | 530 | 266.34 | 832100 |  | 266.34 | 1.99 | 1.99 | 1.99 | 1.99 | 1.99 |  | 1.99 | 1.99 | 1.99 | [57 empty] | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | [5 empty] | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 1.43 | 2.2 | 2.2 | 2.2 | 2.2 |  | 2.2 | 2.2 | [5 empty] | 2.33 | 2.46 | 2.46 | 2.46 | 5.15 | 7.85 |  | 7.85 | 7.85 | 7.85 | 5.15 | 2.46 | 2.46 |  | 2.46 | 2.46 | 2.46 | 2.46 | 2.46 | 2.46 |  | 2.46 | 1.56 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 2.61 | 4.56 | 4.56 |  | 4.56 | 4.56 | 4.56 | 4.56 | 4.56 | 4.56 |  | 4.23 | 11.69 | 19.49 | 19.49 | 19.49 | 11.04 |  | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.97 |  | 3.34 | 3.34 | 3.34 | 3.34 | 3.34 | 3.34 |  | 1.67 | [6 empty] | 1.91 | 3.82 | 3.82 | 3.82 | 3.82 | 5.09 |  | 6.37 | 19.11 | 31.84 | 19.11 | 6.37 | 6.37 |  | 6.37 | 6.37 | 3.18 | [331 empty] | 1.66 |  | 6.63 | 6.63 | 6.63 | 6.63 | 6.63 | 6.63 |  | 6.63 | 4.97
Storm 700 mm depth: 3.5 - 4.5m |  |  |  | 50 | 11.3 | 87000 |  | 11.3 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 |  | 0.19 | 0.19 | 0.19 | [57 empty] | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | [5 empty] | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | [5 empty] | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.03 | [44 empty] | 0.84 | 1.68 | 1.68 |  | 1.68 | 1.68 | 3.63 | 5.58 | 5.58 | 3.35 |  | 1.12 | 1.12 | 1.4 | 1.68 | 1.68 | 0.84 | [314 empty] | 0.16 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.47
Storm 800 mm depth: 1.5 - 2.5m |  |  |  | 280 | 91.14 | 459200 |  | 91.14 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |  | 1.05 | 1.05 | 1.05 | [57 empty] | 0.26 | 0.26 |  | 0.26 | 0.26 | 0.26 | 0.26 | [5 empty] | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | [5 empty] | 2.36 | 4.37 | 4.37 | 4.37 | 4.37 | 4.37 |  | 4.37 | 4.24 | 4.1 | 4.1 | 4.1 | 4.1 |  | 10.04 | 15.98 | 15.98 | 15.98 | 15.98 | 15.98 |  | 9.73 | 3.48 | 3.48 | 3.48 | 3.48 | 3.48 |  | 4.26 | 5.04 | 5.04 | 5.04 | 5.04 | 5.04 |  | 2.7 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.17 | [375 empty] | 0.88 |  | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 |  | 3.5 | 2.63
Storm 800 mm depth: 2.5 - 3.5m |  |  |  | 160 | 118.78 | 291200 |  | 118.78 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 |  | 0.6 | 0.6 | 0.6 | [57 empty] | 0.15 | 0.15 |  | 0.15 | 0.15 | 0.15 | 0.15 | [5 empty] | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | [5 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.88 | 1.56 | 1.56 | 1.56 | 1.56 |  | 1.56 | 1.56 | 1.67 | 1.79 | 1.79 | 1.79 |  | 4.17 | 6.55 | 6.55 | 6.55 | 6.55 | 4.17 |  | 1.79 | 1.79 | 1.79 | 1.79 | 1.79 | 1.79 |  | 1.79 | 1.79 | 1.79 | 0.99 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 1.02 | 1.84 | 1.84 | 1.84 | 1.75 |  | 1.56 | 1.46 | 4.37 | 7.28 | 7.28 | 4.08 |  | 0.87 | 0.87 | 0.87 | 0.87 | 0.98 | 1.09 |  | 1.09 | 1.09 | 1.09 | 1.09 | 0.55 | [357 empty] | 0.5 |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 1.5
Storm 800 mm depth: 3.5 - 4.5m |  |  |  | 50 | 11.3 | 100000 |  | 11.3 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 |  | 0.19 | 0.19 | 0.19 | [57 empty] | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | [5 empty] | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | [5 empty] | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.03 | [48 empty] | 1.26 | 2.51 | 2.09 | 1.68 | 5.03 | 8.38 |  | 4.75 | 1.12 | 1.12 | 1.4 | 1.68 | 1.68 |  | 0.84 | [312 empty] | 0.16 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.47
Storm 900 mm depth: 1.5 - 2.5m |  |  |  | 195 | 44.07 | 390000 |  | 44.07 | 0.73 | 0.73 | 0.73 | 0.73 | 0.73 |  | 0.73 | 0.73 | 0.73 | [57 empty] | 0.18 | 0.18 |  | 0.18 | 0.18 | 0.18 | 0.18 | [5 empty] | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | [5 empty] | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 1.88 | 3.51 | 3.51 | 3.51 |  | 3.51 | 3.51 | 3.18 | 2.86 | 2.86 | 2.86 |  | 2.86 | 8.08 | 13.31 | 13.31 | 13.31 | 13.31 |  | 8.08 | 2.86 | 2.86 | 2.86 | 2.86 | 2.78 |  | 2.69 | 2.69 | 2.69 | 2.69 | 2.69 | 2.69 |  | 2.69 | 1.47 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.12 | [375 empty] | 0.61 |  | 2.44 | 2.44 | 2.44 | 2.44 | 2.44 | 2.44 |  | 2.44 | 1.83
Storm 900 mm depth: 2.5 - 3.5m |  |  |  | 90 | 56.76 | 198000 |  | 56.76 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 |  | 0.34 | 0.34 | 0.34 | [57 empty] | 0.08 | 0.08 |  | 0.08 | 0.08 | 0.08 | 0.08 | [5 empty] | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | [5 empty] | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.3 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 1.21 | 1.95 | 1.95 | 1.95 | 1.18 | 0.41 |  | 0.41 | 0.41 | 0.41 | 0.48 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.33 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.06 | [32 empty] | 0.86 |  | 1.71 | 1.71 | 1.71 | 2 | 2.28 | 6.84 |  | 11.41 | 6.84 | 2.28 | 2.28 | 2.28 | 2.28 |  | 1.14 | [326 empty] | 0.28 |  | 1.13 | 1.13 | 1.13 | 1.13 | 1.13 | 1.13 |  | 1.13 | 0.84
Storm 900 mm depth: 3.5 - 4.5m |  |  |  | 35 | 7.91 | 84000 |  | 7.91 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | [57 empty] | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | [5 empty] | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | [5 empty] | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.02 | [53 empty] | 0.88 |  | 1.76 | 1.47 | 1.17 | 2.54 | 3.91 | 3.91 |  | 2.34 | 0.78 | 0.78 | 0.98 | 1.17 | 1.17 |  | 0.59 | [305 empty] | 0.11 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.33
Storm Manhole Dia 1200 mm, Depth: 1.5 - 2.5m |  |  |  | 9 | 4.17 | 133200 |  | 4.17 | [6 empty] | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | [51 empty] | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | [5 empty] | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.04 | 0.08 |  | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.09 |  | 0.09 | 0.09 | 0.09 | 0.13 | 0.17 | 0.17 |  | 0.17 | 0.17 | 0.11 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.03 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | [5 empty] | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 |  | 0.01 | 0.03 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.08 | 0.1 |  | 0.1 | 0.14 | 0.19 | 0.19 | 0.12 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.13 |  | 0.2 | 0.19 | 0.17 | 0.14 | 0.14 | 0.14 |  | 0.34 | 0.55 | 0.34 | 0.14 | 0.14 | 0.14 |  | 0.08 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0 | [340 empty] | 0.03 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.08
Storm Manhole Dia 1200 mm, Depth: 2.5 - 3.5m |  |  |  | 3 | 1.56 | 68640 |  | 1.56 | [6 empty] | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | [51 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0.01 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.04 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.04 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | [5 empty] | 0.02 | 0.02 | 0.01 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0.02 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.04 | 0.05 | 0.05 |  | 0.07 | 0.09 | 0.09 | 0.06 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.04 | 0.05 | 0.05 | 0.05 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.09 | 0.14 |  | 0.09 | 0.04 | 0.04 | 0.04 | 0.02 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [340 empty] | 0.01 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.03
Storm Manhole Dia 1200 mm; Depth < 1.5m |  |  |  | 1 | 0.12 | 12280 |  | 0.12 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [51 empty] | 0.2 | [193 empty] | 0.02 | 0.04 | 0.04 | 0.04 |  | 0.03 | 0.03 | 0.03 | 0.08 | 0.13 | 0.08 |  | 0.03 | 0.03 | 0.03 | 0.02 | [365 empty] | 0 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01
Storm Manhole Dia 1500 mm, Depth: 1.5 - 2.5m |  |  |  | 18 | 8.78 | 290700 |  | 8.78 | [6 empty] | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 |  | 0.07 | 0.07 | [51 empty] | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | [5 empty] | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.08 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.18 | 0.21 | 0.21 | 0.21 | 0.21 |  | 0.21 | 0.21 | [5 empty] | 0.34 | 0.47 | 0.47 | 0.47 | 0.47 | 0.47 |  | 0.3 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.07 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.07 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.16 | 0.2 | 0.2 | 0.29 |  | 0.38 | 0.38 | 0.23 | 0.09 | 0.09 | 0.09 |  | 0.18 | 0.26 | 0.26 | 0.24 | 0.19 | 0.15 |  | 0.15 | 0.35 | 0.55 | 0.35 | 0.15 | 0.15 |  | 0.15 | 0.09 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.01 | [340 empty] | 0.06 |  | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 |  | 0.23 | 0.17
Storm Manhole Dia 1500 mm, Depth: 2.5 - 3.5m |  |  |  | 9 | 3.28 | 178200 |  | 3.28 | [6 empty] | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | [51 empty] | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | [5 empty] | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | [5 empty] | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.04 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.09 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.17 | 0.22 | 0.22 |  | 0.22 | 0.22 | 0.14 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.04 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.02 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.05 | 0.05 | 0.08 | 0.12 | 0.14 |  | 0.14 | 0.11 | 0.07 | 0.13 | 0.18 | 0.18 |  | 0.22 | 0.26 | 0.26 | 0.19 | 0.12 | 0.22 |  | 0.32 | 0.21 | 0.11 | 0.11 | 0.11 | 0.06 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0 | [340 empty] | 0.03 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.08
Storm Manhole Dia 1500 mm, Depth: 3.5 - 4.5m |  |  |  | 1 | 0.12 | 29400 |  | 0.12 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [51 empty] | 0.2 | [213 empty] | 0.02 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.08 | 0.13 | 0.08 |  | 0.03 | 0.03 | 0.03 | 0.02 | [344 empty] | 0 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01
Storm Manhole Dia 2000 mm, Depth > 5.5m |  |  |  | 1 | 0.12 | 65750 |  | 0.12 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [51 empty] | 0.2 | [147 empty] | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.03 | 0.04 |  | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.03 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0 | [381 empty] | 0 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01
Storm Manhole Dia 2000 mm, Depth: 1.5 - 2.5m |  |  |  | 4 | 1.5 | 104400 |  | 1.5 | [6 empty] | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | [51 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0.03 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.08 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.17 | 0.22 | 0.22 | 0.22 | 0.22 |  | 0.14 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.03 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [340 empty] | 0.01 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.04
Storm Manhole Dia 2000 mm, Depth: 2.5 - 3.5m |  |  |  | 8 | 3.26 | 274240 |  | 3.26 | [6 empty] | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | [51 empty] | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | [5 empty] | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | [5 empty] | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.04 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.09 | 0.12 | 0.12 | 0.12 | 0.12 | 0.17 |  | 0.22 | 0.22 | 0.22 | 0.22 | 0.14 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.04 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.08 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.34 | 0.54 | 0.34 | 0.14 | 0.14 |  | 0.14 | 0.07 | [339 empty] | 0.03 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.08
Storm Manhole Dia 2000 mm, Depth: 3.5 - 4.5m |  |  |  | 15 | 5.55 | 702000 |  | 5.55 | [6 empty] | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | [51 empty] | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | [5 empty] | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | [5 empty] | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.06 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.14 |  | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 |  | 0.31 | 0.44 | 0.44 | 0.44 | 0.44 | 0.27 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 |  | 0.06 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.11 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.23 | 0.25 | 0.25 | 0.25 |  | 0.59 | 0.94 | 0.59 | 0.23 | 0.2 | 0.16 |  | 0.16 | 0.08 | [332 empty] | 0.05 |  | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 |  | 0.19 | 0.14
Storm Manhole Dia 2000 mm, Depth: 4.5 - 5.5m |  |  |  | 4 | 1.48 | 225120 |  | 1.48 | [6 empty] | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | [51 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0.05 | 0.09 | 0.09 |  | 0.09 | 0.09 | 0.09 | 0.14 | 0.18 | 0.18 |  | 0.27 | 0.36 | 0.36 | 0.22 | 0.07 | 0.07 |  | 0.07 | 0.06 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.02 | [339 empty] | 0.01 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.04
Street Lighting Panels |  |  |  | 1 | 0.03 | 82000 |  | 0.03 | [31 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [542 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0.02 | 0.05 |  |  | 0.01 | 0.04 | 0.04 | 0.07 | 0.16 | 0.16 |  | 0.12 | [21 empty] | 0 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
TSE Air V Dia (50) mm on pipes with dia(160) mm. |  |  |  | 9 | 0.27 | 27495 |  | 0.27 | [22 empty] | 0.05 | 0.05 | 0.05 |  |  | 0.05 | 0.05 | 0.05 | [421 empty] | 0.01 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | [5 empty] | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.04 | 0.09 | 0.09 | 0.1 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.11 | 0.07 | 0.07 | 0.07 | 0.11 | 0.22 |  | 0.22 | 0.22 | 0.17 | [9 empty] | 0.01 |  | 0.05 | 0.05 | 0.05 | 0.06 | 0.08 | 0.08 |  | 0.08 | 0.08 | 0.08 | 0.07 | 0.07 | 0.07 |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 |  | 0.07 | 0.09 | 0.16 | 0.16 | 0.17 | 0.2 |  | 0.2 | 0.17 | 0.07 |  | 0.07 | 0.07 |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.06 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.06 | 0.16 | 0.16 |  | 0.16 | 0.16 | 0.12 | [37 empty] | 0.03 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.08
TSE Gate valves dia (160) mm |  |  |  | 7 | 0.21 | 22190 |  | 0.21 | [22 empty] | 0.04 | 0.04 | 0.04 |  |  | 0.04 | 0.04 | 0.04 | [421 empty] | 0 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | [5 empty] | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 |  | 0.07 | 0.07 | 0.07 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.06 | 0.1 | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.09 | 0.1 | 0.12 |  | 0.1 | 0.03 | 0.04 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.02 | 0.02 | 0.03 | 0.04 | 0.04 |  | 0.06 | 0.12 | 0.12 | 0.11 | 0.13 | 0.1 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.03 | 0.04 |  | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.05 |  | 0.1 | 0.11 | 0.1 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.03 | 0.09 | 0.09 | 0.07 | [41 empty] | 0.02 |  | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 |  | 0.09 | 0.07
TSE Gate valves dia (200) mm |  |  |  | 1 | 0.03 | 4465 |  | 0.03 | [22 empty] | 0.01 | 0.01 | 0.01 |  |  | 0.01 | 0.01 | 0 | [421 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [35 empty] | 0 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.03 |  | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.02 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.02 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.03 | [42 empty] | 0 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01
TSE Gate valves dia (90) mm |  |  |  | 16 | 0.48 | 37600 |  | 0.48 | [22 empty] | 0.08 | 0.08 | 0.08 |  |  | 0.08 | 0.08 | 0.08 | [421 empty] | 0.01 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | [5 empty] | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.07 | 0.19 |  | 0.19 | 0.18 | 0.15 | 0.15 | 0.15 | 0.15 |  | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 |  | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.14 |  | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 |  | 0.09 | 0.12 | 0.21 | 0.21 | 0.21 | 0.21 |  | 0.24 | 0.31 | 0.2 | 0.17 | 0.18 | 0.22 |  | 0.18 | 0.05 | 0.05 | 0.05 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.06 | 0.09 | 0.07 | 0.07 |  | 0.07 | 0.07 | 0.1 | 0.19 | 0.23 | 0.23 |  | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.13 | 0.13 | 0.13 | 0.14 | 0.16 | 0.15 |  | 0.11 | 0.11 | 0.1 |  | 0.1 | 0.1 |  | 0.1 | 0.11 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.15 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.15 | [45 empty] | 0.05 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.15
TSE HDPE 160mm 0.0 to 1.5m |  |  |  | 220 | 6.6 | 66000 |  | 6.6 | [18 empty] | 1.1 |  | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | [462 empty] | 0.16 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | [5 empty] | 0.63 | 0.63 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.47 | [7 empty] | 1.11 | 4.42 | 4.42 | 4.42 |  | 4.42 | 4.05 | 2.95 | 2.95 | 2.95 | 2.95 |  | 4.84 | 10.53 | 10.53 | 10.53 | 10.53 | 10.53 |  | 10.53 | 8.63 | 2.95 |  | 2.95 | 2.95 |  | 2.95 | 3 | 3.16 | 3.16 | 3.16 | 3.16 |  | 3.16 | 3.16 | 2.37 | [51 empty] | 0.69 |  | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 |  | 2.75 | 2.06
TSE HDPE 160mm 1.5 to 3.0m |  |  |  | 4100 | 129.14 | 1845000 |  | 129.14 | [18 empty] | 20.5 |  | 20.5 | 20.5 | 20.5 | 20.5 | 20.5 | [462 empty] | 2.93 |  | 11.71 | 11.71 | 11.71 | 11.71 | 11.71 | 11.71 | [5 empty] | 11.71 | 11.71 |  | 11.71 | 11.71 | 11.71 | 11.71 | 11.71 | 11.71 |  | 19.89 | 44.42 | 44.42 | 44.42 | 44.42 | 49.87 |  | 66.22 | 98.02 | 193.41 | 193.41 | 152.53 | 29.88 |  | 29.88 | 29.88 | 29.88 | 29.88 | 30.45 | 32.16 |  | 32.16 | 32.16 | 32.16 | 32.16 | 32.16 | 32.16 |  | 27.04 | 11.71 | 11.71 | 11.71 | 11.71 | 11.71 |  | 11.71 | 11.71 | 11.71 | 14.78 | 23.99 | 23.99 |  | 23.99 | 23.99 | 26.03 | 32.17 | 52.62 | 113.98 |  | 93.53 | 32.17 | 34.73 | 46.22 | 50.03 | 27.02 |  | 27.02 | 27.02 | 27.02 | 27.02 | 27.02 | 27.02 |  | 27.02 | 24.09 | 15.48 | 16.03 | 16.03 | 16.03 |  | 16.03 | 16.03 | 16.03 | 27.61 | 62.34 | 62.34 |  | 62.34 | 63.52 | 67.05 | 67.05 | 67.05 | 66.66 |  | 53.9 | 19.17 | 19.17 | 21.52 | 28.59 | 28.59 |  | 28.59 | 29.25 | 28.9 |  | 21.84 | 21.84 |  | 21.84 | 21.84 | 21.84 | 21.84 | 21.84 | 17.17 |  | 3.14 | 2.35 | [52 empty] | 12.81 |  | 51.25 | 51.25 | 51.25 | 51.25 | 51.25 | 51.25 |  | 51.25 | 38.44
TSE HDPE 90mm 0.0 to 1.5m |  |  |  | 320 | 9.6 | 70400 |  | 9.6 | [18 empty] | 1.6 |  | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | [462 empty] | 0.23 |  | 0.91 | 0.91 | 0.91 | 0.91 | 0.91 | 0.91 | [5 empty] | 0.91 | 0.91 |  | 0.91 | 1.6 | 3.66 | 3.66 | 3.66 | 3.66 |  | 3.43 | 2.74 | 2.74 | 2.74 | 2.74 | 3.92 |  | 7.45 | 7.45 | 7.45 | 7.45 | 7.45 | 7.45 |  | 6.27 | 2.74 | 2.74 | 2.74 | 2.74 | 2.71 |  | 2.63 | 2.63 | 2.63 | 2.63 | 2.63 | 2.63 |  | 2.63 | 2.2 | 0.91 | 0.91 | 1.89 | 3.85 |  | 0.91 | 0.91 | 0.91 | 1.13 | 1.79 | 1.79 |  | 2.38 | 4.18 | 4.6 | 5.86 | 5.15 | 3.03 |  | 3.03 | 3.03 | 3.03 | 2.94 | 2.71 | 2.87 |  | 2.87 | 2.87 | 2.87 | 3.95 | 7 | 6.51 |  | 6.51 | 6.29 | 5.6 | 5.74 | 5.14 | 2.12 |  | 2.12 | 2.12 | 2.06 | 1.97 | 2.27 | 2.27 |  | 2.27 | 2.27 | 2.48 | 2.62 | 1.15 | 1.15 |  | 1.15 | 1.15 | 1.15 | 1.15 | 0.94 | 0.31 |  | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.32 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.26 | [52 empty] | 1 |  | 4 | 4 | 4 | 4 | 4 | 4 |  | 4 | 3
TSE Washout Dia (100) mm on pipes with dia (160) mm |  |  |  | 3 | 0.09 | 8460 |  | 0.09 | [22 empty] | 0.02 | 0.02 | 0.02 |  |  | 0.02 | 0.02 | 0.02 | [421 empty] | 0 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | [5 empty] | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.05 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.05 | 0.1 |  | 0.1 | 0.1 | 0.09 | 0.09 | 0.07 |  |  |  |  | 0.02 | 0.05 |  | 0.01 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.03 | 0.07 | 0.07 |  | 0.07 | 0.05 | [73 empty] | 0.01 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.03
Unit Substation 13.8/0.4 KV |  |  |  | 1 | 0 | 458000 |  | 0 | [20 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [462 empty] | 0 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [11 empty] | 0.02 | 0.05 |  |  | 0.01 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.06 | 0.16 | 0.16 |  | 0.12 | [14 empty] | 0 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
V Ch On pipes Dia. 160 mm |  |  |  | 16 | 0 | 24480 |  | 0 | [525 empty] | 0.03 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.11 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.12 | 0.07 | 0.07 | 0.07 |  | 0.07 | 0.07 | 0.07 | 0.11 | 0.22 | 0.22 |  | 0.22 | 0.22 | 0.22 | 0.22 | 0.24 | 0.3 |  | 0.24 | 0.08 | 0.09 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.1 | 0.05 | 0.05 | 0.07 | 0.11 | 0.11 |  | 0.16 | 0.3 | 0.28 | 0.26 | 0.33 | 0.27 |  | 0.09 | 0.09 | 0.09 | 0.09 | 0.11 | 0.2 |  | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.28 |  | 0.5 | 0.54 | 0.55 | 0.25 | 0.25 | 0.24 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.18 | 0.13 |  | 0.13 | 0.13 | 0.26 | 0.67 | 0.67 | 0.5
V Ch On pipes Dia. 200 mm |  |  |  | 1 | 0 | 1530 |  | 0 | [597 empty] | 0.01 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.05 |  | 0.05 | 0.05 |  | 0.05 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.03 | 0.07 |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.05
V Ch On pipes Dia. 90 mm |  |  |  | 16 | 0 | 24480 |  | 0 | [521 empty] | 0.06 | 0.23 |  | 0.23 | 0.22 | 0.18 | 0.18 | 0.18 | 0.18 |  | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 |  | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.15 |  | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 |  | 0.09 | 0.13 | 0.25 | 0.25 | 0.25 | 0.25 |  | 0.3 | 0.4 | 0.25 | 0.25 | 0.27 | 0.33 |  | 0.27 | 0.08 | 0.08 | 0.08 | 0.07 | 0.07 |  | 0.07 | 0.07 | 0.08 | 0.13 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.15 | 0.29 | 0.34 | 0.34 |  | 0.29 | 0.14 | 0.14 | 0.14 | 0.14 | 0.16 |  | 0.19 | 0.19 | 0.19 | 0.21 | 0.24 | 0.22 |  | 0.17 | 0.17 | 0.15 |  | 0.15 | 0.15 |  | 0.15 | 0.16 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.23 | 0.3 | 0.3 | 0.3 | 0.3 |  | 0.3 | 0.23
Wash out chamber; on 160 mm dia pipeline |  |  |  | 3 | 0 | 135000 |  | 0 | [531 empty] | 0.01 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.04 | 0.08 | 0.08 | 0.08 | 0.08 |  | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.07 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.06 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.1 |  |  |  |  | 0.03 | 0.08 |  | 0.01 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.04 | 0.1 | 0.1 |  | 0.1 | 0.08
Washout Chambers on pipes Dia. 160 mm |  |  |  | 3 | 0 | 147000 |  | 0 | [445 empty] | 0.05 |  | 0.15 |  |  |  |  | 0.02 |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.06 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.07 |  | 0.2 | 0.2 | 0.2 | 0.15 | 0.01 | 0.05 |  | 0.06 | 0.1 | 0.1 | 0.1 | 0.09 | 0.05 |  | 0.06 | 0.1 | 0.1 | 0.1 | 0.08
Washout Chambers on pipes Dia. 250 mm |  |  |  | 3 | 0 | 147000 |  | 0 | [473 empty] | 0.01 |  | 0.03 | 0.03 | 0.05 | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.09 | 0.13 | 0.24 | 0.19 | 0.08 |  | 0.2 | 0.2 | 0.2 | 0.18 | 0.1 | 0.18 | [5 empty] | 0.4 | 0.3

## Risk Register
Department: | [8 empty] | Status Date:
Program | [8 empty] | 2026-10-05
Project: |  |  | ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY
Project No.: |  |  | TAB1-02-003
Project Location: |  |  | TABOUK Industrial City
[16 empty] | Before Treatment | [10 empty] | Post Treatment
Risk Data | [5 empty] | Category |  |  | Risk Description |  |  | Risk Control Dates |  | Risk Manageability | Risk Proximity | Most Likely |  |  | Risk Owner | Risk Response & Treatment Action |  |  |  | Treatment Control Dates |  |  | Most Likely |  |  | Treatment Status
Risk ID | Region | Section / Group | City | Project ID | Risk Status | T/O/I | Internal/External | Category | Cause / Source | Risk | Consequence / Effect | Identified | Closed |  |  | Liklihood | Impact | Risk Score |  | Risk Response Strategy | Treatment Action | Treatment Acton Description | Treatment Action Owner | Start | Due | Closed | Liklihood | Impact | Risk Score
CEN-TAB1-02-RI-001 | Central | Central | TABOUK | TAB1-02-005 | Open | Issue | Internal | Construction / Obstacle | ELECTRICAL CABLE IN POND | ACCIDENTAL DAMAGE OR CUTTING OF THE ELECTRICAL CABLE DURING EXCAVATION | POWER OUTAGE IN THE SURROUNDING AREA - WORKS INJURY OR SERIOUS ELECTRICAL INCIDENT - DELAY IN THE PROJECT SCHEDULE | 2025-09-06 | 2026-04-20 | Ease | Overdue | Very High | Very High | H25 | ENG/ YAZEED ALRAGABAH | Treat | Control | DIVERT THE CABLE TO BE AWAY FROM THE POND | ELECTRICITY COMPANY | 2025-09-06 | 2026-04-20 | 2026-04-20 |  |  |  | Close
CEN-TAB1-02-RI-002 | Central | Central | TABOUK | TAB1-02-005 | Open | Issue | Internal | Construction / Obstacle | INDUSTRIAL FACILITIES ENCROACHING ON ROAD LOCAL1- 2-3-4-5-COLLECTOR 3-UPGRADE 39-21 | IMPLEMENTATION UNDER THE CURRENT CONDITIONS WILL NOT MEET TRAFIC SAFETY STANDARDS | FAILURE TO COMPLETE THE INTERSECTION WORKS | 2026-02-10 | 2026-04-29 | Ease | Med Term | Medium | High | M12 | ENG/ YAZEED ALRAGABAH | Treat | Control | THE RFI HAS BEEN RAISED REGRARDING NETWORK DAMAGE DUE TO INTERFERENCE WITH THE FACTORIES | CONSULTANT | 2026-03-30 | 2026-04-29 | 2026-04-29 |  |  |  | Close
CEN-TAB1-02-RI-003 | Central | Central | TABOUK | TAB1-02-005 | Open | Issue | Internal | Construction / Obstacle | TELECOMMUNICATIONS NETWORK INTEGRATION & UNDERSIZED SERVER ROOM IN THE ADMINISTRATION BUILDING | TELECOMMUNICATIONS NETWORK INTEGRATION & UNDERSIZED SERVER ROOM IN THE ADMINISTRATION BUILDING | FAILURE TO FINALIZE THE CCTV SHOP DRAWINGS | 2026-02-11 |  | Moderate | Med Term | Medium | Medium | M9 | ENG/ YAZEED ALRAGABAH | Treat | Control | THE DRAWING ARE BEING SUBMITTED FOR APPROVAL | CONTRACTOR | 2026-02-11 | 2026-06-05 | 2026-06-06 |  |  |  | Close
CEN-TAB1-02-RI-004 | Central | Central | TABOUK | TAB1-02-005 | Open | Issue | Internal | Construction / Obstacle | DELAY IN PROCUREMENT FOR MV | DELAY IN PROCUREMENT FOR MV | UNDER PROGRESS | 2026-05-06 |  | Moderate | Med Term | High | High | H16 | ENG/ YAZEED ALRAGABAH | Treat | Control | MATERIAL DELIVERY HAS STARTED | CONTRACTOR | 2026-05-06 | 2026-06-15 | 2026-06-15 |  |  |  | Close
CEN-TAB1-02-RI-005 | Central | Central | TABOUK | TAB1-02-006 | Open | Issue | Internal | Construction / Obstacle | DELAY IN PROCUREMENT DELIVERY OF MATERIALS INCLUDING CATCHBASIN - SLEEVES PIPES FOR UPVC & GRP | DELAY IN PROCUREMENT DELIVERY OF MATERIALS INCLUDING CATCHBASIN -WARNING TAPE - SLEEVES PIPES | IMPACTS THE COMPLETION OF UTILITIES BACKFILLING WORKS & CONSEQUENTLY DELAYS THE START OF UPVC INSTALLATION WORKS |  |  | Moderate | Med Term | High | High | H16 | ENG/ YAZEED ALRAGABAH | Treat | Control | PROCUREMENT ACTIVITIES WILL BE INITIATED | CONTRACTOR | 2026-04-27 | 2026-06-22 | 2026-06-22 |  |  |  | Close
CEN-TAB1-02-RI-006 | Central | Central | TABOUK | TAB1-02-007 | Open | Issue | Internal | Construction / Obstacle | NEW JERSEY BARRIES DETAILS (LENGTH & DIMENSIONS) | NEW JERSEY BARRIES DETAILS (LENGTH & DIMENSIONS) | RFI HAS BEEN SIBMITTED |  |  | Moderate | Med Term | Medium | Medium | M9 | ENG/ YAZEED ALRAGABAH | Treat | Control | THE REPLY HAS BEEN RECEIVED AND THE DRAWINGS ARE BEING SUBMITTED FOR UPGRADING TO CODE A | CONTRACTOR | 2026-05-04 | 2026-05-17 | 2026-06-06 |  |  |  | Close
CEN-TAB1-02-RI-007 | Central | Central | TABOUK | TAB1-02-007 | Open | Issue | Internal | Construction / Obstacle | UPGRADING SHOP DRAWING TO CODE A | UPGRADING SHOP DRAWING TO CODE A | DRAWING ARE BEING SUBMITTED |  |  | Moderate | Med Term | High | High | H16 | ENG/ YAZEED ALRAGABAH | Treat | Control | DRAWING ARE BEING SUBMITTED | CONTRACTOR | 2026-06-29 | 2026-09-28 |  |  |  |  | Open
CEN-TAB1-02-RI-008 | Central | Central | TABOUK | TAB1-02-007 | Open | Issue | Internal | Construction / Obstacle | THERE ARE CHANGES TO THE VAVE CHAMBER DRAWINGS AND THE UPDATED DRAWINGS ARE AWAITING APPROVAL (RFI 29) | UPDATED DRAWINGS ARE AWAITING APPROVAL | UNDERREVIEW |  |  | Moderate | Med Term | High | High | H16 | ENG/ YAZEED ALRAGABAH | Treat | Control | approval & potable water and tse have been submitted for approval | CONTRACTOR | 2026-06-29 | 2026-07-13 | 2026-07-14 |  |  |  | Close
CEN-TAB1-02-RI-009 | Central | Central | TABOUK | TAB1-02-007 | Open | Issue | Internal | Construction / Obstacle | START OF THE MV NETWORK CONNECTION FOR THE STATION | START OF THE MV NETWORK CONNECTION FOR THE STATION | the substation is currently under testing and commissioning. All testing activities are expected to be completed by August 2026. |  |  | Moderate | Med Term | Medium | Medium | M9 | ENG/ YAZEED ALRAGABAH | Treat | Control | THE RESPONSE FROM STATION WILL BE RECEIVED TOMORROW | MODON | 2026-06-15 | 2026-10-05 |  |  |  |  | Open
CEN-TAB1-02-RI-010 | Central | Central | TABOUK | TAB1-02-007 | Open | Issue | Internal | Construction / Obstacle | THERE IS SHINKO FENCE IS OBSTRUCTING THE ELECTRICAL WORKS AND PREVENTING PROGRESS | THERE IS SHINKO FENCE IS OBSTRUCTING THE ELECTRICAL WORKS AND PREVENTING PROGRESS |  |  |  | Moderate | Med Term | Medium | Medium | M9 | ENG/ YAZEED ALRAGABAH | Treat | Control | email has been sent to the consultant for review and further action | MODON | 2026-07-06 | 2026-10-05 |  |  |  |  | Open
CEN-TAB1-02-RI-011 | Central | Central | TABOUK | TAB1-02-007 | Open | Issue | Internal | Construction / Obstacle | DELAY IN PROCUREMENT DELIVERY OF MATERIALS INCLUDING LV-STREET LIGHTING -HDPE TELE & DELAY PO FOR STREET LIGHTING | DELAY IN PROCUREMENT DELIVERY OF MATERIALS INCLUDING LV-STREET LIGHTING -HDPE TELE & DELAY PO FOR STREET LIGHTING |  |  |  | Moderate | Med Term | High | High | H16 | ENG/ YAZEED ALRAGABAH | Treat | Control | SUBMITTAL GELENTY HAS BEEN RESUBMITTED - AL BABTAIN APPROVAL IS CURRENTLY IN PROGRESS | MODON | 2026-08-31 | 2026-09-07 | 2026-09-07 |  |  |  | Close
CEN-TAB1-02-RI-012 | Central | Central | TABOUK | TAB1-02-007 | Open | Issue | Internal | Construction / Obstacle | PROPOSED MODIFICATION TO THE STORMWATER NETWORK LOCAL 1 | PROPOSED MODIFICATION TO THE STORMWATER NETWORK LOCAL 1 |  |  |  | Moderate | Med Term | Medium | Medium | M9 | ENG/ YAZEED ALRAGABAH | Treat | Control | FIR has been sent to the consultant for review and further action | MODON | 2026-07-06 | 2026-09-14 | 2026-09-12 |  |  |  | Close
CEN-TAB1-02-RI-013 | Central | Central | TABOUK | TAB1-02-007 | Open | Issue | Internal | Construction / Obstacle | DELAY IN PROCUREMENT DELIVERY OF MATERIALS INCLUDING LV-STREET | DELAY IN PROCUREMENT DELIVERY OF MATERIALS INCLUDING LV-STREET |  |  |  | Moderate | Med Term | Medium | Medium | M9 | ENG/ YAZEED ALRAGABAH | Treat | Control | IT WILL BE DELIVERED TODAY | MODON | 2026-09-14 | 2026-09-15 | 2026-09-17 |  |  |  | Close
CEN-TAB1-02-RI-014 | Central | Central | TABOUK | TAB1-02-008 | Open | Issue | Internal | Construction / Obstacle | INCREASE IN THE NUMBER OF MANHOLES FOR THE TELECOMMUNICATIONS NETWORK | INCREASE IN THE NUMBER OF MANHOLES FOR THE TELECOMMUNICATIONS NETWORK |  |  |  | Moderate | Med Term | Medium | Medium | M9 | ENG/ YAZEED ALRAGABAH | Treat | Control | WAITING A RESPONSE | CONTRACTOR | 2026-10-05 | 2026-09-15 |  |  |  |  | Open
NOTES: | [10 empty] | All testing activities are expected to be completed by August 2026.
Risk Status: 1.Open, 2.Closed, or 3.Realized
T/O/I: 1.Threat, 2.Opportunity, or 3.Issue
Category (select 1):
1. Political
2. Legal, Regulatory, Compliance
3. Funding, Finance, Budget
4. Management, Governance, Policies, KPI, Performance
5. Human Resources | [21 empty] | `
6. Stakeholders, Authorities, Approvals, Permits
7. Requirements, Specifications, Scope, Procurement, Contract
8. Process, Tools, Technique, Technology
9. Design, Engineering
10. Construction, Execution
11. Testing, Commissioning, Handover
12. Operation, Maintenance
Risk Description (add all 3):
1. Source/Cause
2. Event = Threat, Opportunity, or Issue
3. Consequence/Effect
Risk Response Strategy for Threats: 1.Terminate, 2.Tolerate, 3.Transfer, or 4.Treat
Risk Response Strategy for Opportunities: 1.Ignore, 2.Share, or 3.Enhance/Exploit
Treatment Action: 1.Mitigate, 2.Control, or 3.Fall Back
Treatment Status: 1.Unapproved, 2.Active, or 3.Closed
Risk Level/Score: Likelihood x Highest Impact (Safety, Cost, Schedule, Environment, Quality, or Reputation. See Risk Scoring Matrix tab)
Formulas:
Closed = [Closed]
Closed = [Due]
Treatment Control Dates = [Risk Control Dates]
Risk Control Dates = [Treatment Control Dates]

## CCO
CONTRACT CHANGE ORDER (CCO)
CCO No. | Date Added | Description of Change | Status | SR | Sch Impact (Months) | Date Approved | Duration (days)

## Invoice Log
Weekly Progress Report - Invoice Log | [31 empty] | Y
Project Value | [8 empty] | Payment Status | [7 empty] | Invoices Summary | [9 empty] | Average Invoices durations |  |  |  |  | N
Original Contract Value |  |  | 140467862 |  | O&M Value |  | 0 | EAC | Advance Payment % |  | 10% |  | Advance Payment (SAR) |  | 14046786.2 |  | No of Submitted Invoices |  | 13 |  | Submitted Invoices (SAR) |  | 43497867.43 |  | Submiited Invoice Peroid | 2026-09-30 | CM / PgM Average Approval duration |  | 0.076923 | Average Invoice Value | 3345989.8023
Revised Contract Value |  | 21100000 | 140467862 | EAC | Revised O&M Value |  | 0 | #REF! | Retention % |  | 0% |  | Retention (SAR) |  | 0 |  | No of Approved Invoices (CM) |  | 13 |  | Approved Invoices (CM) (SAR) |  | 43497867.43 |  |  |  | MODON PM & Accounts Average Approval duration |  | 17.2222
Estimate At Completion Value |  | 20900000 | 140467862 | #REF! | Submitted Invoices (Gross Value) |  | 43497867.43 |  | Penalties and deduction % |  | 0.04129% |  | AP Recovery (SAR) |  | 0 |  | No of Approved Invoices (PM) |  | 9 |  | Approved Invoices (PM) (SAR) |  | 29853856.43 |  | Invoice Submitted Compared to Contract Value | 30.97% | Payments Average Duration |  | 13.6667
Potential Changes |  | 200000 | 0 |  | Total Deduction |  | 58000 |  | Penalties and deduction (SAR) |  | 58000 |  | Retention Cumulative (SAR) |  | 0 |  | No of Paid Invoices |  | 9 |  | Paid Invoices (SAR) |  | 34389934.8945 |  |  |  | Invoices Average total Duration |  | 34.3333
Invoice Reference |  |  |  | Invoice Value |  |  |  |  | Period Covered |  | CM / PgM Approval Timeline |  |  |  | Modon PM & Accounts Approval | [6 empty] | Payment Status |  |  |  |  | Total Invoice Duration | Remarks
# | Invoice No. | Doc Control reference | Submittal Rev. # | Gross Value | AP Recovery | Retention | Deduction / Penalties | Amount (net) + VAT 15% | Start Date | End Date | Date to CM / PgM | CM / PgM Approval (Yes/No) | CM / PgM Reply Date | Days Elapsed | Date to PM | PM Approval (Yes/No) | PM Reply Date | Date to Accounts | Accounts Approval (Yes/No) | Accounts Approval Date | Days Elapsed | Date Paid | Amount Paid | Paid % | Payment Period (d) | Amount Pending
1 | 1 | INVOICE 01 | 0 | 2814914.75 |  | 0 |  | 3237151.9625 | 2025-09-04 | 2025-10-30 | 2025-10-30 | Y | 2025-10-30 | 0 | 2025-10-30 | Y | 2025-10-30 | 2025-10-30 | Y | 2025-10-30 | 0 | 2025-11-01 | 3237151.9625 | 100% | 2 | 0 | 2
2 | 2 | INVOICE 02 | 0 | 1250224.29 |  | 0 |  | 1437757.9335 | 2025-10-30 | 2025-12-01 | 2025-12-01 | Y | 2025-12-01 | 0 | 2025-12-01 | Y | 2025-12-01 | 2025-12-01 | Y | 2025-12-01 | 0 | 2025-12-01 | 1437757.9335 | 100% | 0 | 0 | 0
3 | 3 | INVOICE 03 | 0 | 1853260 |  | 0 |  | 2131249 | 2026-01-25 | 2026-01-26 | 2026-01-26 | Y | 2026-01-26 | 0 | 2026-01-26 | Y | 2026-01-30 | 2026-01-29 | Y | 2026-01-29 | 3 | 2026-01-31 | 2131249 | 100% | 2 | 0 | 5
4 | 4 | INVOICE 04 | 0 | 2906476 |  | 0 |  | 3342447.4 | 2026-02-01 | 2026-02-02 | 2026-02-02 | Y | 2026-02-02 | 0 | 2026-02-02 | Y | 2026-02-02 | 2026-02-02 | Y | 2026-02-02 | 0 | 2026-02-03 | 3342447.4 | 100% | 1 | 0 | 1
5 | 5 | INVOICE 05 | 0 | 2508482 |  | 0 | 32000 | 2916754.3 | 2/29/2026 | 2026-03-01 | 2026-03-01 | Y | 2026-03-02 | 1 | 2026-03-02 | Y | 2026-03-03 | 2026-03-03 | Y | 2026-03-03 | 1 | 2026-06-01 | 2916754.3 | 100% | 90 |  | 92
6 | 6 | INVOICE 06 | 0 | 3628041.39 |  | 0 |  | 4172247.5985 | 2026-03-01 | 2026-03-31 | 2026-04-09 | Y | 2026-04-09 | 0 | 2026-04-09 | Y | 2026-05-18 | 2026-05-18 | Y | 2026-05-18 | 39 | 2026-06-01 | 4172247.5985 | 100% | 14 | 0 | 53
7 | 7 | INVOICE 07 | 0 | 5980688 |  | 0 | 10000 | 6887791.2 | 2026-04-01 | 2026-04-01 | 2026-04-01 | Y | 2026-04-01 | 0 | 2026-05-01 | Y | 2026-05-18 | 2026-05-18 | Y | 2026-05-18 | 17 | 2026-06-01 | 6887791.2 | 100% | 14 | 0 | 61
8 | 8 | INVOICE 08 | 0 | 2989995 |  | 0 | 10000 | 3448494.25 | 2026-05-01 | 2026-06-08 | 2026-06-08 | Y | 2026-06-08 | 0 | 2026-06-08 | Y | 2026-07-19 | 2026-07-19 | Y | 2026-07-19 | 41 | 2026-07-19 | 3448494.25 | 100% | 0 | 0 | 41
9 | 9 | INVOICE 09 | 0 | 5921775 |  | 0 | 6000 | 6816041.25 | 2026-07-06 | 2026-07-06 | 2026-07-06 | Y | 2026-07-06 | 0 | 2026-07-06 | Y | 2026-08-29 | 2026-07-06 | Y | 2026-08-29 | 54 | 2026-08-29 | 6816041.25 | 100% | 0 | 0 | 54
10 | 10 | INVOICE 10 | 0 | 4968932 |  | 0 |  | 5714271.8 | 2026-08-03 | 2026-08-03 | 2026-08-03 | Y | 2026-08-03 | 0 | 2026-08-03
11 | 11 | INVOICE 11 | 0 | 3091936 |  | 0 |  | 3555726.4 | 2026-08-15 | 2026-08-15 | 2026-08-15 | Y | 2026-08-15 | 0 | 2026-08-15
12 | 12 | INVOICE 12 | 0 | 2678671 |  | 0 |  | 3080471.65 | 2026-08-15 | 2026-08-31 | 2026-08-31 | Y | 2026-08-31 | 0 | 2026-08-31
13 | 13 | INVOICE 13 | 0 | 2904472 |  | 0 |  | 3340142.8 | 2026-09-01 | 2026-09-30 | 2026-10-04 | Y | 2026-10-04 | 0 | 2026-10-04
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
|  |  | TOTAL | 43497867.43 |  | 0 | 58000 | 50080547.5445 | [17 empty] | 0
Formulas:
CM / PgM Approval Timeline = [End Date]
Modon PM & Accounts Approval = [CM / PgM Reply Date]
Date to Accounts = [Invoices Summary]
Accounts Approval Date = [Date to Accounts]
Note on I3: Without O&M Cost
Note on D4: Without O&M Cost
Note on E4: Without O&M Cost

## Procurement
|  | TAB1-02-003 |  | Procurement Log- Long Lead Items | [18 empty] | 2026-10-05
Sr. NO. | Project ID | ACT#inP6 | Item Description | Discipline | (Long \Short) Lead Items | BOQ. No. | Unit | Quantity | Proc. Qty | Required P.O Date | Date of Pur. Order Issued | Purchase Order No. | Supplier | Supplier Phone | Method of Shipping | Required on Job | E.D.A. to Site | A.D.A. to Site | Lead Time | Approval Status | Completion Rate | The Impact (BOQ Cost) | Remarks
SHORT-LEAD
1 |  | ROADS | ROADS |  | Short
1 | TAB1-02-003 | TAPQDVRD0001 | ABC | ROADS | LONG |  | m3 | 48485 | 48485 | 2026-01-10 | 2026-03-24 | SL103026 | شركة خبير المستقبل للاسفلت |  | Local | 2026-01-19 | 2026-03-21 | 2026-03-21 |  | Accepted As Material | 49% |  | DELIVERY ONGOING
2 | TAB1-02-003 | TAPQDVRD0002 | BBC Base Course | ROADS | LONG |  | m3 | 24510 | 24510 | 2026-01-10 | 2026-03-24 | SL103026 | شركة خبير المستقبل للاسفلت |  | Local | 2026-12-30 | 2026-03-29 | 2026-03-29 |  | Accepted As Material | 27% |  | DELIVERY ONGOING
3 | TAB1-02-003 | TAPQDVRD0003 | BWC Asphalt Wearing Course | ROADS | LONG |  | m3 | 14195 | 14195 | 2026-01-10 | 2026-03-24 | SL103027 | شركة خبير المستقبل للاسفلت |  | Local | 2027-06-01 |  |  |  | Accepted As Material |  |  | po issued
4 | TAB1-02-003 | TAPQDVRD0004 | Precast Concrete Curbstone | ROADS | LONG |  | m | 74370 | 74370 | 2026-01-10 | 2026-07-21 | PO-02240 | جسور المستقبل |  | Local | 2026-03-18 | 2026-04-12 | 2026-04-12 |  | Accepted As Material | 9% |  | DELIVERY ONGOING
5 | TAB1-02-003 | TAPQDVRD0005 | Precast Concrete Interlocking | ROADS | LONG |  | m2 | 62075 | 62075 | 2026-01-10 | 2026-07-05 | PO-02156 | جسور المستقبل |  | Local | 2026-03-26 |  |  |  | Accepted As Material |  |  | po issued
6 | TAB1-02-003 | TAPQDVRD0008 | Marking for Road | ROADS | LONG |  |  |  |  | 2026-01-10 | 2026-04-19 | SL1942026 | شركة أضواء طي الشمال |  | Local | 2027-07-22 | 2026-04-26 | 2026-04-26 |  | Accepted As Material | 19% |  | DELIVERY ONGOING
7 | TAB1-02-003 | TAPQDVRD0009 | Trafic Sinage | ROADS | LONG |  | Unit | 246 | 246 | 2026-01-10 |  |  |  |  | Local | 2027-07-24 |  |  |  | Accepted As Material | 2% |  | DELIVERY ONGOING
2 |  | ELECTRICAL | ELECTRICAL
8 | TAB1-02-003 | TAPQDVEL0001 | Pipes ,Fittings | ELECTRICAL | LONG |  | m | 2145 | 2145 | 2026-03-04 | 2026-04-22 | SL2242026 | الشركة العربية لصناعة البلاستك |  | Local | 2026-05-13 | 2026-04-29 | 2026-04-29 |  | Accepted As Material | 89% |  | DELIVERY ONGOING | 26.81%
9 | TAB1-02-003 |  | cables (LV ) | [6 empty] | 2026-03-04 | 2026-07-02 | PO-02162 | بحرة |  |  | 2026-05-21 | 2026-09-14 | 2026-09-17 |  |  | 55% |  | DELIVERY ONGOING
10 | TAB1-02-003 | TAPQDVEL0002 | SCOPE MV | ELECTRICAL | LONG |  | m | 115400 | 115400 | 2026-03-04 | 2026-04-14 | PO-014255 | شركة ايتيا |  | Local | 2026-05-21 | 2026-06-10 | 2026-06-10 |  | Accepted As Material | 71.7% |  | DELIVERY ONGOING
11 | TAB1-02-003 | TAPQDVEL0003 | Poles & Luminares | ELECTRICAL | LONG |  | Unit | 957 | 957 | 2026-03-04 | 2026-09-08 | PO-012069 | شركة البابطين |  | Local | 2026-05-21 |  |  |  | Accepted As Material |  |  | po issued
13 | TAB1-02-003 | TAPQDVEL0004 | Substations ,ets.. | ELECTRICAL | LONG |  | Unit | 5 | 5 | 2026-03-04 | 2026-04-14 | PO-014255 | شركة ايتيا |  | Local | 2026-09-03 | 2026-08-01 | 2026-08-01 |  | Accepted As Material | 100% |  | DONE
14 | TAB1-02-003 | TAPQDVEL0004 | RMU ,ets.. | ELECTRICAL | LONG |  | Unit | 5 | 5 | 2026-03-04 | 2026-04-14 | PO-014255 | شركة ايتيا |  | Local | 2026-09-03 | 2026-08-01 | 2026-08-01 |  | Accepted As Material | 100% |  | DONE
16 | TAB1-02-003 |  | Pole Foundation | [6 empty] | 2026-03-04 | 2026-08-24 |  | جسور المستقبل | [9 empty] | po issued
3 |  | TELECOMMUNICATION | TELECOMMUNICATION
17 | TAB1-02-003 | TAPQDVTC0001 | Telecommunication Material (Pipes,,ets) | TELECOMMUNICATION | LONG |  | m | 16522 | 16522 | 2026-03-12 | 22-5-2026 | PO-2185 | شركة الاتحاد |  | Local | 2026-05-10 |  |  |  | Accepted As Material | 92% |  | DELIVERY ONGOING
4 |  | CCTV NETWORK | CCTV NETWORK
18 | TAB1-02-003 | TAPQDVCC0001 | CCTV NETWORK (cable fiber) | CCTV NETWORK | LONG |  | m | 24430 | 24430 | 2026-03-22 | 2026-07-06 | PO-1040726 | شركة فضاء الاعمال |  | Local | 2026-07-19 | 2026-09-19 | 2026-09-19 |  | Accepted As Material | 100% |  | DONE
18 |  |  | CCTV NETWORK (camera - devices) | [6 empty] | 2026-03-22 | 2026-07-06 | PO-1040726 | شركة فضاء الاعمال |  | Local | 2026-07-19 | [6 empty] | po issued
5 |  | POTABLE WATER | POTABLE WATER
19 | TAB1-02-003 | TAPQDVPT0001 | PE Pipes | POTABLE WATER | LONG |  | m | 13221 | 13221 | 2026-01-11 | 2025-12-30 | PO-01613 | UNION PIPES |  | Local | 2026-03-16 | 2026-01-21 | 2026-01-21 |  | Accepted As Material | 100% |  | DONE
20 | TAB1-02-003 | TAPQDVPT0002 | Valves | POTABLE WATER | LONG |  | Nr | 146 | 146 | 2026-01-11 | 2025-12-25 | PO-01520 | SPC |  | Local | 2026-04-14 | 2026-02-10 | 2026-02-10 |  | Accepted As Material | 100% |  | DONE
21 | TAB1-02-003 | TAPQDVPT0003 | Fire Hydrent | POTABLE WATER | LONG |  | Nr | 152 | 152 | 2026-01-11 | 2025-12-25 | PO-1520 | SPC |  | Local | 2026-04-14 | 2026-02-20 | 2026-02-20 |  | Accepted As Material | 100% |  | DONE
6 |  | TSE NETWORK | TSE NETWORK
22 | TAB1-02-003 | TAPQDVTS0001 | PE Pipes | TSE NETWORK | LONG |  | m | 12223 | 12223 | 2026-01-11 | 2025-12-30 | PO-01613 | UNION PIPES |  | Local | 2026-03-16 | 2026-01-21 | 2026-01-21 |  | Accepted As Material | 100% |  | DONE
23 | TAB1-02-003 | TAPQDVTS0002 | Valves | TSE NETWORK | LONG |  | Nr | 141 | 141 | 2026-01-11 | 2025-12-25 | PO-01520 | SPC |  | Local | 2026-03-16 | 2026-02-10 | 2026-02-10 |  | Accepted As Material | 100% |  | DONE
7 |  | SEWERAGE NETWORK | SEWERAGE NETWORK
24 | TAB1-02-003 | TAPQDVSW0001 | GRP Pipes | SEWERAGE NETWORK | LONG |  | m | 8370 | 8370 | 2025-12-07 | 2025-11-24 | PO-01437 | TAREQ NAQADI | 533365029 | Local | 2025-12-30 | 2025-12-09 | 2025-12-09 |  | Accepted As Material | 97% |  | DELIVERY ONGOING
25 | TAB1-02-003 | TAPQDVSW0002 | Fiberglass Manholes,ets) | SEWERAGE NETWORK | LONG |  | Nr | 142 | 142 | 2025-12-07 | 2026-01-18 | PO-1662 | TAREQ NAQADI |  | Local | 2026-01-17 | 2026-02-02 | 2026-02-02 |  | Accepted As Material | 100% |  | DONE
8 |  | STORM NETWORK | STORM NETWORK
26 | TAB1-02-003 | TAPQDVST0001 | UPVC Pipes with Fittings | STORM NETWORK | LONG |  | m | 6621 | 6621 | 2025-11-21 | 2025-12-28 | PO-01580 | الخام الوطني للصناعات |  | Local | 2025-11-27 | 2026-01-21 | 2026-01-21 |  | Accepted As Material | 100% |  | DONE
27 | TAB1-02-003 | TAPQDVST0002 | GRP Pipes with Fittings | STORM NETWORK | LONG |  | m | 9017 | 9017 | 2025-11-21 | 2025-11-24 | PO-01437 | TAREQ NAQADI | 533365029 | Local | 2025-11-29 | 2025-12-09 | 2025-12-09 |  | Accepted As Material | 99% |  | DELIVERY ONGOING
28 | TAB1-02-003 | TAPQDVST0005 | Box Culvert | STORM NETWORK | LONG |  | m3 | 4100 | 4100 | 2025-11-21 | 2026-02-01 | PO-01183 | TAREQ NAQADI |  | Local | 2025-12-22 | 2026-03-05 | 2026-03-05 |  | Accepted As Material | 98% |  | DELIVERY ONGOING
29 | TAB1-02-003 | TAPQDVST0006 | Manholes,ets | STORM NETWORK | LONG |  | Nr | 155 | 155 | 2025-11-21 | 2026-01-21 | PO -01700 | JOSOR ELMOSTAKBEL |  | Local | 2025-12-22 | 2026-03-05 | 2026-03-05 |  | Accepted As Material | 99% |  | DELIVERY ONGOING
30 | TAB1-02-003 |  | CATCH BASIN | STORM NETWORK | [7 empty] | PO-01886 | TAREQ NAQADI |  |  |  | 2026-04-22 | 2026-04-22 |  | Accepted As Material | 81% |  | DELIVERY ONGOING
31 | TAB1-02-003 | TAPQDVST0007 | RIprab for Ponds | STORM NETWORK | LONG |  | m2 | 15345 | 15345 | 2025-11-21 | 2026-04-21 | SL1942027 | SALALEM ELYAMAMAH |  | Local | 2026-06-27 | 2026-04-22 | 2026-04-22 |  | Accepted As Material | 90% |  | DELIVERY ONGOING
32 | TAB1-02-003 | TAPQDVST0010 | Riprab for Dike | STORM NETWORK | LONG |  | m2 | 1570 | 1570 | 2025-11-21 | 2026-04-21 | SL1942027 | SALALEM ELYAMAMAH |  | Local | 2026-01-13 | 2026-04-22 | 2026-04-22 |  | Accepted As Material | 100% |  | DONE
CCTV Swiches Lighting panels
Street Lighting panels 1- 63A MCCB Circuit Breaker 2- 6X32 MCB Circuit Breakers 3- 1X63A contactors 4- Photocell & Timer 5- ON/OFF Push Button 6- Indication Lamps 7- Copper Bus Bars 8- Panel Body from Galavanized Steel anti-corrosion (IP65) And includes everything necessary to operate the panels according to the technical specifications or instructions of the supervising engineer.
Feeder pillars 1- 100A MCCB Circuit Breaker 2- 5X63A MCCB Circuit Breakers 3- Indication Lamps 4- Copper Bus Bars 5- Panel Body from Galavanized Steel anti-corrosion (IP65) And includes everything necessary for operation according to the technical specifications or instructions of the supervising engineer.
#REF!

## Issues
[8 empty] | 2026-10-05 | Status | Responsibility
[9 empty] | Open | Contractor
[9 empty] | Closed | Consultant
Modon
Third Party
Other
Issue Log
Issue No | Date Identified | Issue Description | Responsibility | Action Taken | Current Status | Expected/Actual Closure | Duration Elapsed
1 | 2025-09-06 | ELECTRICAL CABLE IN POND | Other | DIVERT THE CABLE TO BE AWAY FROM THE POND | Close | 2026-04-20 | 226
2 | 2026-03-30 | INDUSTRIAL FACILITIES ENCROACHING ON ROAD LOCAL1- 2-3-4-5-COLLECTOR 3-UPGRADE 39-21 | Consultant | THE RFI HAS BEEN RAISED REGRARDING NETWORK DAMAGE DUE TO INTERFERENCE WITH THE FACTORIES | Closed | 2026-04-29 | 30
3 | 2026-02-11 | TELECOMMUNICATIONS NETWORK INTEGRATION & UNDERSIZED SERVER ROOM IN THE ADMINISTRATION BUILDING | Contractor | THE DRAWING ARE BEING SUBMITTED FOR APPROVAL | Closed | 2026-06-06 | 115
4 | 2026-05-06 | DELAY IN PROCUREMENT FOR MV | Contractor | MATERIAL DELIVERY HAS STARTED | Closed | 2026-06-15 | 40
5 | 2026-04-27 | DELAY IN PROCUREMENT DELIVERY OF MATERIALS INCLUDING CATCHBASIN - SLEEVES PIPES FOR UPVC & GRP | Contractor | PROCUREMENT ACTIVITIES WILL BE INITIATED | Closed | 2026-06-22 | 56
6 | 2026-05-04 | NEW JERSEY BARRIES DETAILS (LENGTH & DIMENSIONS) | Contractor | THE REPLY HAS BEEN RECEIVED AND THE DRAWINGS ARE BEING SUBMITTED FOR UPGRADING TO CODE A | Closed | 2026-06-06 | 33
7 | 2026-06-29 | UPGRADING SHOP DRAWING TO CODE A | Contractor | DRAWING ARE BEING SUBMITTED | Open
8 | 2026-06-29 | THERE ARE CHANGES TO THE VAVE CHAMBER DRAWINGS AND THE UPDATED DRAWINGS ARE AWAITING APPROVAL (RFI 29) | Contractor | approval & potable water and tse have been submitted for approval | Closed | 2026-07-14 | 15
9 | 2026-06-15 | START OF THE MV NETWORK CONNECTION FOR THE STATION | Other | THE RESPONSE FROM STATION WILL BE RECEIVED TOMORROW | Open
10 | 2026-07-06 | THERE IS SHINKO FENCE IS OBSTRUCTING THE ELECTRICAL WORKS AND PREVENTING PROGRESS | Other | email has been sent to the consultant for review and further action | Open
11 | 2026-08-31 | DELAY IN PROCUREMENT DELIVERY OF MATERIALS INCLUDING LV-STREET LIGHTING -HDPE TELE & DELAY PO FOR STREET LIGHTING | Contractor | SUBMITTAL GELENTY HAS BEEN RESUBMITTED - AL BABTAIN APPROVAL IS CURRENTLY IN PROGRESS | Closed | 2026-09-07 | 7
12 | 2026-07-06 | PROPOSED MODIFICATION TO THE STORMWATER NETWORK LOCAL 1 | Other | FIR has been sent to the consultant for review and further action | Closed | 2026-09-12 | 68
13 | 2026-09-14 | DELAY IN PROCUREMENT DELIVERY OF MATERIALS INCLUDING LV-STREET | Other | IT WILL BE DELIVERED TODAY | Closed | 2026-09-17 | 3
14 | 2026-10-05 | INCREASE IN THE NUMBER OF MANHOLES FOR THE TELECOMMUNICATIONS NETWORK | Contractor | WAITING A RESPONSE | Open
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Manpower
Head-Count ( Non Manual)
MONTHS | 2025-09-04 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30
Plan - Monthly | 12 | 15 | 23 | 24 | 26 | 27 | 27 | 27 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 26 | 25 | 25 | 24 | 21 | 20 | 21
Planned - Cumulative | 12 | 27 | 50 | 74 | 100 | 127 | 154 | 181 | 209 | 237 | 265 | 293 | 321 | 349 | 377 | 405 | 433 | 461 | 487 | 512 | 537 | 561 | 582 | 602 | 623
Actual - Monthly | 10 | 9 | 11 | 20 | 21 | 20 | 24 | 24 | 24 | 31 | 31 | 32 | 33 | 35
Actual Cumulative | 10 | 19 | 30 | 50 | 71 | 91 | 115 | 139 | 163 | 194 | 225 | 257 | 290 | 325
Forecast - Monthly | [14 empty] | 28 | 28 | 28 | 28 | 26 | 25 | 25 | 24 | 21 | 20 | 21
Saudi Monthly - Actual |  |  | 1
Head-Count (Manual)
MONTHS | 2025-09-04 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30
Plan - Monthly | 18 | 27 | 36 | 37 | 50 | 60 | 47 | 136 | 89 | 34 | 9 | 24 | 57 | 69 | 63 | 76 | 102 | 121 | 203 | 197 | 169 | 134 | 108 | 40 | 32
Planned - Cumulative | 18 | 45 | 81 | 118 | 168 | 228 | 275 | 411 | 500 | 534 | 543 | 567 | 624 | 693 | 756 | 832 | 934 | 1055 | 1258 | 1455 | 1624 | 1758 | 1866 | 1906 | 1938
Actual - Monthly | 26 | 37 | 41 | 63 | 83 | 83 | 85 | 92 | 100 | 172 | 176 | 188 | 192 | 183
Actual Cumulative | 26 | 63 | 104 | 167 | 250 | 333 | 418 | 510 | 610 | 782 | 958 | 1146 | 1338 | 1521
Forecast - Monthly | [14 empty] | 63 | 76 | 102 | 121 | 203 | 197 | 169 | 134 | 108 | 40 | 32
Saudi - Actual
Head-Count (Non-Manual) | [29 empty] | Month | 2026-10-31 | 2026-11-30
Planned | Actual |  | Variance |  | Forecast Next Month |  | Saudi Staff
28 | 32 |  | 4 |  | 28 |  | 1
Head-Count (Manual) | [10 empty] | Man Power by Trade
Planned | Actual |  | Variance |  | Forecast Next Month |  | Saudi Staff |  |  |  | Key Trade |  | General Labor |  | Milling |  | Carpenter |  | Plumber |  | OPERATOR |  | Steel Fixer |  | Driver | MASON | ELECTRICAN | Others | Total
57 | 192 |  | 135 |  | 63 |  | 0 |  |  |  | Plan |  | 13 |  | 1 |  |  |  | 5 |  | 19 |  |  |  | 18 |  | 1 | 28 | 85 |  | 110
[11 empty] | Actual |  | 79 |  | 1 |  | 18 |  | 11 |  | 45 |  | 10 |  | 16 | 0 | 3 | 35 | 218
Equipment
MONTHS | 2025-09-04 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30
Plan - Monthly | 16 | 24 | 31 | 27 | 39 | 49 | 31 | 71 | 43 | 22 | 8 | 17 | 38 | 32 | 29 | 45 | 57 | 68 | 94 | 71 | 46 | 36 | 32 | 15 | 5
Planned - Cumulative | 16 | 40 | 71 | 98 | 137 | 186 | 217 | 288 | 331 | 353 | 361 | 378 | 416 | 448 | 477 | 522 | 579 | 647 | 741 | 812 | 858 | 894 | 926 | 941 | 946
Actual - Monthly | 27 | 31 | 35 | 53 | 63 | 60 | 59 | 59 | 58 | 73 | 75 | 75 | 70 | 62
Actual Cumulative | 27 | 58 | 93 | 146 | 209 | 269 | 269 | 269 | 269 | 269 | 269 | 269 | 269 | 269
Forecast - Monthly | [14 empty] | 29 | 45 | 57 | 68 | 94 | 71 | 46 | 36 | 32 | 15 | 5
Equipment Count
Planned | Actual |  | Idle |  | Variance |  | Forecast Next Month
38 | 70 |  | 5 |  | 32 |  | 29
Type | Excavator | Fork lift | Loader | Dumper | Dozer | Grader | Dump truck |  | Water tanker |  | SCREEN |  | TRAILLER |  | MILLING MACHINE |  | Grader |  | PAVER BASE COURSE |  | Desil tanker |  | BOBCAT |  | PAVER ASPHALT | JCP | Roller | MC DRIVER | Total
Plan | 15 |  | 1 |  | 1 |  | 16 |  | 2 |  | 0 |  | 0 |  | 1 |  | 1 |  | 0 |  | 0 |  |  |  | 0 |  | 1 | 0 | 38
Actual | 24 |  | 3 |  | 1 |  | 10 |  | 3 |  | 2 |  | 2 |  | 1 |  | 2 |  | 1 |  | 1 |  | 1 |  | 0 | 3 | 9 | 0 | 63
Idle |  |  |  |  | 0 | [13 empty] | 1 | [5 empty] | 0 |  |  |  | 1

## Milestones
Milestones for Ready Built Facroties in XYZ
Item No. | Milestones | Original (Baseline) | Latest | Forecast |  | Days Change
| Contract Duration Current Contract Weeks : 57 of 108 | 104.1429 | 108 | 108.2857 |  | -2 |  | 57 |  |  | 108
1 | Award Date | 2025-08-13 | 2025-08-13 | 2025-08-13 | A | 0
2 | Contract Sign Date | 2025-08-31 | 2025-08-31 | 2025-08-31 | A | 0
3 | Site Handover Date | 2025-09-04 | 2025-09-04 | 2025-09-04 | A | 0
4 | Complete Mobilization | 2027-08-10 | 2027-08-23 | 2027-08-30 | F | -7
5 | Complete Preliminary Submittals | 2025-12-06 | 2026-10-27 | 2026-11-03 | F | -7
6 | Complete delivery of all equipment and materials | 2027-08-03 | 2027-09-28 | 2027-09-29 | F | -1
7 | Complete ZONE 1 | 2027-02-09 | 2027-09-30 | 2027-10-02 | F | -2
8 | Complete ZONE 2 | 2027-08-02 | 2027-08-09 | 2027-08-16 | F | -7
9 | Complete ZONE 3 | 2027-08-02 | 2027-09-26 | 2027-09-27 | F | -1
10 | Complete all Works including Testing & Commissioning, Cleanup, Closeout Documentation and Ready for Initial Handover | 2027-08-10 | 2027-09-12 | 2027-09-13 | F | -1
11 | Complete Demobilization | 2027-09-03 | 2027-09-30 | 2027-10-02 | F | -2
12 | Project Handover | 2027-09-03 | 2027-09-30 | 2027-10-02 | F | -2
Activity ID | Activity Name | Original Duration | Activity Count | BL Project Start | BL Project Finish | Start | Finish | Budgeted Total Cost | Schedule % Complete | Performance % Complete | Planned Value Cost | Actual Total Cost | Earned Value Cost | Activity % Complete | Units % Complete | Labor Units % Complete | Physical % Complete | Duration % Complete | Budgeted Labor Units | Planned Value Labor Units | Performance % Complete - Labor Units | Actual Labor Units | Earned Value Labor Units
B6.31 22 00.93 | Excavation in Central Area | 20 | 1 | 2024-06-13 | 2024-07-11 | 28-Feb-24 A | 2024-10-03 | 1479028.2 | 100% | 99% | 147902820% | 146423792% | 146423792% | 99% | 99% | 0.99 | 99% | 99% | 2240 | 2240 | 99% | 2217.6 | 2217.6
0.1.4 | Mobilization Finish | 0 | 1 |  | 2024-02-27 |  | 2024-06-20 | 0 | 100% | 100% | 0% | 0% | 0% | 100% | 0% | 0 | 100% | 100% | 0 | 0 | 0% | 0 | 0
Proc.26 11 161.19 | Units Substations - Manufacturing, Shipment & Delivery | 120 | 1 | 2025-06-03 | 2025-10-27 | 2025-07-12 | 2025-11-30 | 91600 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 960 | 0 | 0% | 0 | 0
Proc.26 11 161.16 | LV Cables Material - Shipping & Delivery | 60 | 1 | 2025-08-31 | 2025-11-10 | 2025-10-05 | 2025-12-14 | 430250 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2400 | 0 | 0% | 0 | 0
0.1.10 | Wet Networks Finish | 0 | 1 |  | 2025-10-30 |  | 2025-12-03 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0% | 0 | 0
0.1.9 | Zone 02 Finish | 0 | 1 |  | 2025-12-07 |  | 2026-01-10 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0% | 0 | 0
Clsout.13.2.1.4 | Desnagging | 3 | 1 | 2025-12-23 | 2025-12-27 | 2026-01-26 | 2026-01-29 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 48 | 0 | 0% | 0 | 0
Clsout.13.2.1.10 | Restoration Of Ground Surfaces | 3 | 1 | 2025-12-31 | 2026-01-04 | 2026-02-03 | 2026-02-07 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 120 | 0 | 0% | 0 | 0
Clsout.13.2.1.11 | Project Handing Over | 2 | 1 | 2026-01-04 | 2026-01-06 | 2026-02-07 | 2026-02-09 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0% | 0 | 0

## Schedule
Primavera P6 Schedule Status | [11 empty] | Data Date | 2026-10-05
Project Activities Overview
Schedule Statistics |  |  |  |  | Active Schedule Activities
Total Act. | Not Started | In Progress | Completed | % | Active | Ahead | On | Behind | Flag
1492 | 729 | 199 | 564 | 37.8% | 199 | 183 | 16 | 0 | 199
Critical Path Activities |  |  | Free Float Management (Total) |  |  |  | Failed Start Activities
|  |  | Greater Than 14 Days |  | Less Than 14 Days
Last Week | This Week | Diff | Last Week | This Week | Last Week | This Week | Last Week | This Week | Flag
117 | 188 | -71 | 0 | 0 | 0 | 0 | 22 | 24 | -2
117
71
172
[5 empty] | 183 |  |  |  | 96
155
123
59

## EV-Chart Data
| 140467862 |  |  | 140467862
| Baseline Plan |  |  | Revised / Recovery Plan |  |  | Earned Value |  |  | Gross Paid Value |  |  | Forecast |  |  | Actual/Fcst vs Plan
Month | Monthly | Cum | % | Monthly | Cum | % | Monthly | Cum | % | Monthly | Cum | % | Monthly | C um |  | Month | Cum
2025-09-04 | 2910173.9 | 2910173.9 | 2.072% | 996820 | 996820 | 0.7096% | 996820 | 996820 | 0.7096% | [6 empty] | -1913353.9 | -1913353.9
2025-10-31 | 3779585.5 | 6689759.4 | 4.762% | 2141562.59 | 3138382.59 | 2.234% | 1997250.94 | 2994070.94 | 2.131% | 2814914.75 | 2814914.75 | 2.004% |  |  |  | -1782334.56 | -3695688.46
2025-11-30 | 3745314.4 | 10435073.8 | 7.429% | 4227812.16 | 7366194.75 | 5.244% | 4032907.05 | 7026977.99 | 5.003% | 1250224.29 | 4065139.04 | 2.894% |  |  |  | 287592.65 | -3408095.81
2025-12-31 | 5261151.93 | 15696225.73 | 11.17% | 5200351.12 | 12566545.87 | 8.946% | 4918593.94 | 11945571.93 | 8.504% | 1853260 | 5918399.04 | 4.213% |  |  |  | -342557.99 | -3750653.8
2026-01-31 | 5622637.98 | 21318863.71 | 15.18% | 6005500.35 | 18572046.22 | 13.22% | 4765965.91 | 16711537.84 | 11.9% | 2906476 | 8824875.04 | 6.282%
2026-02-28 | 6629407.24 | 27948270.95 | 19.9% | 6038765.24 | 24610811.46 | 17.52% | 4138995.83 | 20850533.67 | 14.84% | 2508482 | 11333357.04 | 8.068%
2026-03-31 | 7446555.39 | 35394826.34 | 25.2% | 5220523.88 | 29831335.34 | 21.24% | 4132964.7 | 24983498.37 | 17.79% | 3628041.39 | 14961398.43 | 10.65%
2026-04-30 | 8900333.55 | 44295159.89 | 31.53% | 9997129.75 | 39828465.09 | 28.35% | 7260451.39 | 32243949.76 | 22.95% | 5980688 | 20942086.43 | 14.91%
2026-05-31 | 8217943.56 | 52513103.45 | 37.38% | 4458685.11 | 44287150.2 | 31.53% | 8146276.83 | 40390226.59 | 28.75% | 2989995 | 23932081.43 | 17.04%
2026-06-30 | 8302980.41 | 60816083.86 | 43.3% | 1168636.83 | 45455787.03 | 32.36% | 8951577.95 | 49341804.54 | 35.13% | 5921775 | 29853856.43 | 21.25%
2026-07-31 | 8438547.75 | 69254631.61 | 49.3% | 1205402.37 | 46661189.4 | 33.22% | 6080108.82 | 55421913.36 | 39.46% | 4968932 | 34822788.43 | 24.79%
2026-08-31 | 7804506.57 | 77059138.18 | 54.86% | 2071148.97 | 48732338.37 | 34.69% | 5736891.52 | 61158804.88 | 43.54% | 5770607 | 40593395.43 | 28.9%
2026-09-30 | 8679548.29 | 85738686.47 | 61.04% | 2898013.45 | 51630351.82 | 36.76% | 4109858.23 | 65268663.11 | 46.47% | 2904472 | 43497867.43 | 30.97% | [5 empty] | 62911800.19
2026-10-31 | 8229860.05 | 93968546.52 | 66.9% | 2953197.61 | 54583549.43 | 38.86% | 600872.91 | 65869536.02 | 46.89% |  |  |  |  | 65869536.02 | 46.89% |  |  | 65605422.09
2026-11-30 | 7237872.23 | 101206418.75 | 72.05% | 2947915.12 | 57531464.55 | 40.96% | [6 empty] | 3700544.59 | 69570080.61 | 49.53% |  |  | 69570080.61
2026-12-31 | 6668333.1 | 107874751.85 | 76.8% | 3438503.91 | 60969968.46 | 43.4% | [6 empty] | 2656224.48 | 72226305.09 | 51.42% |  |  | 72226305.09
2027-01-31 | 7099837.44 | 114974589.29 | 81.85% | 4989302.94 | 65959271.4 | 46.96% | [6 empty] | 3297496.09 | 75523801.18 | 53.77% |  |  | 75523801.18
2027-02-28 | 5748809.77 | 120723399.06 | 85.94% | 5413458.51 | 71372729.91 | 50.81% | [6 empty] | 6407741.82 | 81931543 | 58.33% |  |  | 81931543
2027-03-31 | 4721884.76 | 125445283.82 | 89.31% | 10363409.39 | 81736139.3 | 58.19% | [6 empty] | 5927874.37 | 87859417.37 | 62.55% |  |  | 87859417.37
2027-04-30 | 3479952.27 | 128925236.09 | 91.78% | 14796557.21 | 96532696.51 | 68.72% | [6 empty] | 12301052.58 | 100160469.95 | 71.3% |  |  | 100160469.95
2027-05-31 | 3524295.6 | 132449531.69 | 94.29% | 14332914.46 | 110865610.97 | 78.93% | [6 empty] | 11800441.14 | 111960911.09 | 79.71% |  |  | 111960911.09
2027-06-30 | 3817162.16 | 136266693.85 | 97.01% | 11368746.48 | 122234357.45 | 87.02% | [6 empty] | 13096865.53 | 125057776.62 | 89.03% |  |  | 125057776.62
2027-07-31 | 3015094.75 | 139281788.6 | 99.16% | 10343849.95 | 132578207.4 | 94.38% | [6 empty] | 7178023.88 | 132235800.5 | 94.14% |  |  | 132235800.5
2027-08-31 | 1186073.4 | 140467862 | 100% | 7544216.89 | 140122424.29 | 99.75% | [6 empty] | 6122911.2 | 138358711.7 | 98.5% |  |  | 138358711.7
2027-09-30 | 0 | 140467862 | 100% | 345437.71 | 140467862 | 100% | [6 empty] | 2109150.3 | 140467862 | 100% |  |  | 140467862
2027-10-31
2027-11-30
2027-12-31
2028-01-31
2028-02-29
2028-03-31
2028-04-30
UPDATE ONLY YELLOW PORTION FROM PRIMAVERA EXPORT, IF NEEDED, EXTEND YELLOW PORTION BASED ON SCHEDULE.
140467862
|  | Activity ID | Activity Name | Activity Count | Start | Finish | Duration % Complete | Performance % Complete | Schedule % Complete | Planned Value Cost | Earned Value Cost | Budgeted Total Cost | Total Float | Spreadsheet Field | 45901 | 45931 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01
|  | 3066 ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY |  | 1492 | 04-Sep-25 A | 2027-09-05 | 0.4479 | 0.3907 | 33.06% | 46432808.09 | 54885787.44 | 140467862 | -200% | BL Project Labor Units | 3108 | 5586 | 7269 | 7553 | 9750 | 10940 | 9115 | 27258 | 18071 | 4513 | 1453 | 4305 | 10708 | 13793 | 11983 | 15803 | 19483 | 19317 | 43168 | 40929 | 34255 | 27822 | 21016 | 6453 | 316
|  | 3066 ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY |  | 1492 | 04-Sep-25 A | 2027-09-05 | 0.4479 | 0.3907 | 33.06% | 46432808.09 | 54885787.44 | 140467862 | -200% | Cum BL Project Labor Units | 3108 | 8695 | 15964 | 23516 | 33266 | 44206 | 53321 | 80578 | 98650 | 103163 | 104616 | 108921 | 119628 | 133421 | 145404 | 161207 | 180689 | 200006 | 243175 | 284104 | 318359 | 346181 | 367197 | 373650 | 373966
|  | 3066 ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY |  | 1492 | 04-Sep-25 A | 2027-09-05 | 0.4479 | 0.3907 | 33.06% | 46432808.09 | 54885787.44 | 140467862 | -2 | At Completion Labor Units | 3108 | 5586 | 7269 | 7553 | 9750 | 10940 | 9115 | 27258 | 18071 | 21411 | 16703 | 8120 | 14223 | 16934 | 11896 | 13740 | 13616 | 15736 | 37071 | 28642 | 33137 | 28910 | 12667 | 2151 | 360
|  | 3066 ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY |  | 1492 | 04-Sep-25 A | 2027-09-05 | 0.4479 | 0.3907 | 33.06% | 46432808.09 | 54885787.44 | 140467862 | -2 | Cum At Completion Total Cost | 996820 | 3138382.59 | 7366194.75 | 12566545.87 | 18535551.69 | 24501327.87 | 29666521.35 | 39816692.66 | 44287150.2 | 48537539.49 | 55091179.77 | 56611812.75 | 59768228.19 | 64272533.47 | 66726621.57 | 70332770.89 | 74545442.13 | 78450114.14 | 91923578.29 | 104551803.69 | 121058013.35 | 131103735.02 | 137455761.18 | 140420611.35 | 140467862
|  | 3066 ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY |  | 1492 | 04-Sep-25 A | 2027-09-05 | 0.4479 | 0.3907 | 33.06% | 46432808.09 | 54885787.44 | 140467862 | -2 | Cum At Completion Labor Units | 3108 | 8695 | 15964 | 23516 | 33266 | 44206 | 53321 | 80578 | 98650 | 120061 | 136764 | 144884 | 159107 | 176041 | 187937 | 201677 | 215293 | 231029 | 268100 | 296742 | 329879 | 358789 | 371456 | 373606 | 373966
0
[14 empty] | Activity ID | Activity Name | Activity Count | Start | Finish | Duration % Complete | BL Project Completed Activities | BL Project In-Progress Activities | Performance % Complete | Schedule % Complete | Planned Value Cost | Earned Value Cost | Budgeted Total Cost | Total Float | Spreadsheet Field | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01
[14 empty] | 3066 ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY |  | 1492 | 04-Sep-25 A | 2027-09-21 | 48.13% | 423 | 13 | 43.54% | 34.64% | 48662607.27 | 61158804.87 | 140467862 | -16 | Cum At Completion Total Cost | 996820 | 3138382.59 | 7366194.75 | 12566545.87 | 18535551.69 | 24501327.87 | 29666521.35 | 39816692.66 | 44287150.2 | 47789064.06 | 53029683.94 | 61206898.28 | 62911800.19 | 65605422.09 | 69570080.61 | 72226305.09 | 75523801.18 | 81931543 | 87859417.37 | 100160469.95 | 111960911.09 | 125057776.62 | 132235800.5 | 138358711.7 | 140467862
[8 empty] | Activity ID | Activity Name | Activity Count | Start | Finish | Performance % Complete | Schedule % Complete | Planned Value Cost | Earned Value Cost | Planned Value Labor Units | Earned Value Labor Units | Total Float | Spreadsheet Field | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01
[8 empty] | 3066 ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY |  | 1492 | 04-Sep-25 A | 2027-09-08 | 34.27% | 32.13% | 45127358.15 | 48140194.66 | 102507 | 116383 | -5 | Planned Total Cost | 996820 | 2141562.59 | 4227812.16 | 5200351.12 | 6005500.35 | 6038765.24 | 5220523.88 | 9997129.75 | 4458685.11 | 571845.44 | 1249900.24 | 2482632.81 | 3672923.94 | 2665102.97 | 4315865.33 | 5118795.85 | 5072650.88 | 5041293.53 | 8376969.55 | 14033719.38 | 17114222.16 | 12819884.86 | 7010366.16 | 5595098.73 | 1039439.97
[8 empty] | 3066 ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY |  | 1492 | 04-Sep-25 A | 2027-09-08 | 34.27% | 32.13% | 45127358.15 | 48140194.66 | 102507 | 116383 | -5 | Cum Earned Value Cost | 996820 | 3138382.59 | 7366194.75 | 12566545.87 | 18535551.69 | 24501327.87 | 29666521.35 | 39816692.66 | 44287150.2 | 48140194.66 | 48140194.66 | 48140194.66 | 48140194.66 | 48140194.66 | 48140194.66 | 48140194.66 | 48140194.66 | 48140194.66 | 48140194.66 | 48140194.66 | 48140194.66 | 48140194.66 | 48140194.66 | 48140194.66 | 48140194.66
[8 empty] | 3066 ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY |  | 1492 | 04-Sep-25 A | 2027-09-08 | 34.27% | 32.13% | 45127358.15 | 48140194.66 | 102507 | 116383 | -5 | Cum Remaining Total Cost | [9 empty] | 306674.41 | 1519170.27 | 3447686.02 | 6044950.34 | 8103374.39 | 11628363.01 | 16900364.13 | 21835299.32 | 26662918.61 | 35093983.72 | 49309080.49 | 66400741.59 | 79220633.71 | 85741980.16 | 91288227.36 | 92327667.33
[8 empty] | 3066 ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY |  | 1492 | 04-Sep-25 A | 2027-09-08 | 34.27% | 32.13% | 45127358.15 | 48140194.66 | 102507 | 116383 | -5 | At Completion Total Cost | 996820 | 2141562.59 | 4227812.16 | 5200351.12 | 5969005.82 | 5965776.19 | 5165193.47 | 10150171.32 | 4470457.54 | 4159718.88 | 1212495.86 | 1928515.75 | 2597264.32 | 2058424.06 | 3524988.62 | 5272001.12 | 4934935.19 | 4827619.29 | 8431065.12 | 14215096.76 | 17091661.1 | 12819892.13 | 6521346.45 | 5546247.2 | 1039439.97
[8 empty] | 3066 ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY |  | 1492 | 04-Sep-25 A | 2027-09-08 | 34.27% | 32.13% | 45127358.15 | 48140194.66 | 102507 | 116383 | -5 | Cum At Completion Total Cost | 996820 | 3138382.59 | 7366194.75 | 12566545.87 | 18535551.69 | 24501327.87 | 29666521.35 | 39816692.66 | 44287150.2 | 48446869.08 | 49659364.93 | 51587880.69 | 54185145 | 56243569.06 | 59768557.67 | 65040558.79 | 69975493.98 | 74803113.27 | 83234178.39 | 97449275.15 | 114540936.25 | 127360828.38 | 133882174.83 | 139428422.03 | 140467862
[8 empty] | Activity ID | Activity Name | Activity Count | BL Project Completed Activities | BL Project In-Progress Activities | Start | Finish | Performance % Complete | Schedule % Complete | Planned Value Labor Units | Earned Value Labor Units | Planned Value Cost | Earned Value Cost | Budgeted Total Cost | Total Float | Spreadsheet Field | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01
[8 empty] | 3066 ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY |  | 1492 | 395 | 11 | 04-Sep-25 A | 2027-09-15 | 35.13% | 32.31% | 103063 | 123184 | 45385512.58 | 49341804.54 | 140467862 | -10 | At Completion Total Cost | 996820 | 2141562.59 | 4227812.16 | 5200351.12 | 5969005.82 | 5965776.19 | 5165193.47 | 10150171.32 | 4470457.54 | 5127877.21 | 1155223.09 | 1751774.69 | 2496067.52 | 2677632.74 | 3640285.39 | 5438278.46 | 4787187.69 | 4000346.19 | 9642499.42 | 13768392.52 | 17329430.66 | 11307503.69 | 6295949 | 5109247.59 | 1653015.93
[8 empty] | 3066 ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY |  | 1492 | 395 | 11 | 04-Sep-25 A | 2027-09-15 | 35.13% | 32.31% | 103063 | 123184 | 45385512.58 | 49341804.54 | 140467862 | -10 | Cum At Completion Total Cost | 996820 | 3138382.59 | 7366194.75 | 12566545.87 | 18535551.69 | 24501327.87 | 29666521.35 | 39816692.66 | 44287150.2 | 49415027.41 | 50570250.5 | 52322025.19 | 54818092.71 | 57495725.45 | 61136010.84 | 66574289.3 | 71361476.99 | 75361823.19 | 85004322.61 | 98772715.13 | 116102145.79 | 127409649.48 | 133705598.48 | 138814846.07 | 140467862
Formulas:
Month = EOMONTH([Month, row above],1)

## Physical-Chart Data
| 354336 | 373967 |  | 373967
| Baseline Plan |  |  | Revised / Recovery Plan |  |  | Earned Effort % |  |  | Forecast |  |  | Achieved/Fcst vs Plan
Week | Monthly Effort | Cum Effort | Plan Wt.% | Monthly Effort | Cum Effort | Plan Wt.% | MONTHLY Wt. | Cum Wt. | Achieved Wt.% | Monthly Wt. | Cum Wt. | Wt.% | Weekly Wt. | Cum Wt.
2025-09-04 | 2784 | 2784 | 0.7857% | 3108 | 3108 | 0.8311% | 3111 | 3108 | 0.8771% |  |  |  | 327 | 327
2025-10-31 | 5200 | 7984 | 2.253% | 5586 | 8694 | 2.325% | 5250 | 8311 | 2.346% |  |  |  | 50 | 377
2025-11-30 | 5588 | 13572 | 3.83% | 7269 | 15963 | 4.269% | 6628 | 14203 | 4.008% |  |  |  | 1040 | 1417
2025-12-31 | 11033 | 24605 | 6.944% | 7553 | 23516 | 6.288% | 6321 | 20524 | 5.792% |  |  |  | -4712 | -3295
2026-01-31 | 13269 | 37874 | 10.69% | 9750 | 33266 | 8.895% | 5887 | 26411 | 7.454% |  |  |  | -7382
2026-02-28 | 14179 | 52053 | 14.69% | 10940 | 44206 | 11.82% | 8072 | 34483 | 9.732% |  |  |  | -6107
2026-03-31 | 16420 | 68473 | 19.32% | 9115 | 53321 | 14.26% | 7742 | 42225 | 11.92%
2026-04-30 | 16474 | 84947 | 23.97% | 27258 | 80579 | 21.55% | 16360 | 58585 | 16.53%
2026-05-31 | 18540 | 103487 | 29.21% | 18071 | 98650 | 26.38% | 24333 | 82918 | 23.4% | [5 empty] | 1360
2026-06-30 | 18618 | 122105 | 34.46% | 4513 | 103163 | 27.59% | 40266 | 123184 | 34.76%
2026-07-31 | 21113 | 143218 | 40.42% | 1453 | 104616 | 27.97% | 10425 | 133609 | 35.73%
2026-08-31 | 26729 | 169947 | 47.96% | 4305 | 108921 | 29.13% | 21664 | 155273 | 41.52%
2026-09-30 | 28808 | 198755 | 56.09% | 10708 | 119629 | 31.99% | 13830 | 169103 | 45.22%
2026-10-31 | 28585 | 227340 | 64.16% | 13793 | 133422 | 35.68% | 2919 | 172022 | 46% |  | 172022 | 46%
2026-11-30 | 25254 | 252594 | 71.29% | 11983 | 145405 | 38.88% |  |  |  | 20860 | 187937 | 50.25% |  |  | 55423
2026-12-31 | 23535 | 276129 | 77.93% | 15803 | 161208 | 43.11% |  |  |  | 14219 | 201677 | 53.93%
2027-01-31 | 16377 | 292506 | 82.55% | 19483 | 180691 | 48.32% |  |  |  | 18226 | 215239 | 57.56%
2027-02-28 | 12069 | 304575 | 85.96% | 19317 | 200008 | 53.48% |  |  |  | 14571 | 231029 | 61.78%
2027-03-31 | 11749 | 316324 | 89.27% | 43168 | 243176 | 65.03% |  |  |  | 35701 | 268100 | 71.69%
2027-04-30 | 10620 | 326944 | 92.27% | 40929 | 284105 | 75.97% |  |  |  | 33158 | 296742 | 79.35%
2027-05-31 | 11209 | 338153 | 95.43% | 34255 | 318360 | 85.13% |  |  |  | 33169 | 329879 | 88.21%
2027-06-30 | 10093 | 348246 | 98.28% | 27822 | 346182 | 92.57% |  |  |  | 26133 | 358789 | 95.94%
2027-07-31 | 5247 | 353493 | 99.76% | 21016 | 367198 | 98.19% |  |  |  | 17575 | 371456 | 99.33%
2027-08-31 | 703 | 354196 | 99.96% | 6453 | 373651 | 99.92% |  |  |  | 5993 | 373606 | 99.9%
2027-09-30 | 140 | 354336 | 100% | 316 | 373967 | 100% |  |  |  | 791 | 373967 | 100%
2027-10-31
2027-11-30
2027-12-31
2028-01-31
2028-02-29
2028-03-31
2028-04-30
UPDATE ONLY YELLOW PORTION FROM PRIMAVERA EXPORT, IF NEEDED, EXTEND YELLOW PORTION BASED ON SCHEDULE.
Activity ID | Activity Name | Original Duration | Activity Count | BL Project Start | BL Project Finish | Start | Finish | Budgeted Total Cost | Schedule % Complete | Performance % Complete | Planned Value Cost | Earned Value Cost | Spreadsheet Field | 2024-01-07 | 2024-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-31 | 2024-06-30 | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28
Total |  | 623.25 | 1116 | 2024-01-07 | 46028 | 07-Jan-24 A | 46062 | 45093675 | 2.35% | 0.0414 | 105921808% | 186653732% | Estimate At Completion Cost |  | 30538.52 | 1081338.05 | 1181886.84 | 3852422.27 | 2825164.68 | 5589699.62 | 164037.04 | 1457350.04 | 2023101.31 | 2985685.95 | 2676580.28 | 2382653.65 | 1638258.93 | 399461.15 | 853330.59 | 673208.04 | 847493.51 | 1128976.22 | 758032.28 | 519891.8 | 1698067.5 | 3666808.7 | 5859916.21 | 804803.46
Total |  | 623.25 | 1116 | 2024-01-07 | 46028 | 07-Jan-24 A | 46062 | 45093675 | 2.35% | 0.0414 | 105921808% | 186653732% | Cum Estimate At Completion Cost |  | 30538.52 | 1111876.57 | 2293763.41 | 6146185.67 | 8971350.35 | 14561049.97 | 14725087 | 16182437.05 | 18205538.36 | 21191224.3 | 23867804.58 | 26250458.24 | 27888717.17 | 28288178.32 | 29141508.91 | 29814716.95 | 30662210.45 | 31791186.68 | 32549218.96 | 33069110.76 | 34767178.27 | 38433986.97 | 44293903.18 | 45098706.64 | 45098706.64
Total |  | 623.25 | 1116 | 2024-01-07 | 46028 | 07-Jan-24 A | 46062 | 45093675 | 2.35% | 0.0414 | 105921808% | 186653732% | Estimate At Completion - Labor Units | 4258.46 | 5074.51 | 8105.89 | 19746.36 | 28683.22 | 22788.05 | 115528.27 | 24471.59 | 23083.07 | 26804.15 | 16374.77 | 43019.93 | 31912.42 | 13734.26 | 6745.33 | 11525.08 | 10816.73 | 12606.27 | 13153.86 | 15583.13 | 13855.6 | 30008.2 | 24989.16 | 15344.27 | 2832.93 | 276.87
Total |  | 623.25 | 1116 | 2024-01-07 | 46028 | 07-Jan-24 A | 46062 | 45093675 | 2.35% | 0.0414 | 105921808% | 186653732% | Cum Estimate At Completion - Labor Units | 4258.46 | 9332.97 | 17438.86 | 37185.22 | 65868.44 | 88656.49 | 204184.75 | 208656.34 | 231739.41 | 258543.56 | 274918.32 | 317938.26 | 349850.68 | 363584.94 | 370330.28 | 381855.36 | 392672.09 | 405278.36 | 418432.22 | 434015.35 | 447870.95 | 477879.15 | 502868.31 | 518212.58 | 521045.51 | 521322.38
Total |  | 623.25 | 1116 | 2024-01-07 | 2026-01-06 | 07-Jan-24 A | 2026-02-09 | 45093675 | 2.35% | 0.0414 | 105921808% | 186653732% | Budgeted Nonlabor Units | 1020.07 | 683.2 | 1827.82 | 8222.03 | 9599.27 | 8008.4 | 22624.35 | 8359.75 | 8710.96 | 9488.56 | 4750.34 | 14612.18 | 14065.27 | 4938.49 | 2034.98 | 3281.5 | 2695.75 | 3107.56 | 3844.99 | 4489.05 | 4347.6 | 7437.25 | 7013.87 | 4975.96 | 617 | 156.87
354336
[6 empty] | Activity ID | Activity Name | Activity Count | Start | Finish | Performance % Complete | Schedule % Complete | Planned Value Cost | 2024-01-07: Earned Value Cost; 2024-02-29: Planned Value Labor Units; 2024-03-31: Earned Value Labor Units; 2024-04-30: Total Float; 2024-05-31: Spreadsheet Field; 2024-06-30: 2025-09-01
[6 empty] | 3066 ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY |  | 1492 | 04-Sep-25 A | 2027-09-08 | 34.27% | 32.13% | 45127358.15 | 2024-01-07: 48140194.66; 2024-02-29: 102507; 2024-03-31: 116383; 2024-04-30: -5; 2024-05-31: BL Project Labor Units; 2024-06-30: 3108
[6 empty] | 3066 ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY |  | 1492 | 04-Sep-25 A | 2027-09-08 | 34.27% | 32.13% | 45127358.15 | 2024-01-07: 48140194.66; 2024-02-29: 102507; 2024-03-31: 116383; 2024-04-30: -5; 2024-05-31: Cum BL Project Labor Units; 2024-06-30: 3108
[6 empty] | Activity ID | Activity Name | Activity Count | Start | Finish | Performance % Complete | Schedule % Complete | Planned Value Cost | Earned Value Cost | Planned Value Labor Units | Earned Value Labor Units | Total Float | Spreadsheet Field | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01
[6 empty] | 3066 ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY |  | 1492 | 04-Sep-25 A | 2027-09-08 | 34.27% | 32.13% | 45127358.15 | 48140194.66 | 102507 | 116383 | -5 | BL Project Labor Units | 3108 | 5586 | 7269 | 7553 | 9750 | 10940 | 9115 | 27258 | 18071 | 4513 | 1453 | 4305 | 10708 | 13793 | 11983 | 15803 | 19483 | 19317 | 43168 | 40929 | 34255 | 27822 | 21016 | 6453 | 316
[6 empty] | 3066 ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY |  | 1492 | 04-Sep-25 A | 2027-09-08 | 34.27% | 32.13% | 45127358.15 | 48140194.66 | 102507 | 116383 | -5 | Cum BL Project Labor Units | 3108 | 8695 | 15964 | 23516 | 33266 | 44206 | 53321 | 80578 | 98650 | 103163 | 104616 | 108921 | 119628 | 133421 | 145404 | 161207 | 180689 | 200006 | 243175 | 284104 | 318359 | 346181 | 367197 | 373650 | 373966
[6 empty] | Activity ID | Activity Name | Activity Count | Start | Finish | Performance % Complete | Schedule % Complete | Planned Value Cost | Earned Value Cost | Planned Value Labor Units | Earned Value Labor Units | Total Float | Spreadsheet Field | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01
[6 empty] | 3066 ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY |  | 1492 | 04-Sep-25 A | 2027-09-08 | 34.27% | 32.13% | 45127358.15 | 48140194.66 | 102507 | 116383 | -5 | BL Project Labor Units | 3108 | 5586 | 7269 | 7553 | 9750 | 10940 | 9115 | 27258 | 18071 | 4513 | 1453 | 4305 | 10708 | 13793 | 11983 | 15803 | 19483 | 19317 | 43168 | 40929 | 34255 | 27822 | 21016 | 6453 | 316
[6 empty] | 3066 ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY |  | 1492 | 04-Sep-25 A | 2027-09-08 | 34.27% | 32.13% | 45127358.15 | 48140194.66 | 102507 | 116383 | -5 | Cum BL Project Labor Units | 3108 | 8695 | 15964 | 23516 | 33266 | 44206 | 53321 | 80578 | 98650 | 103163 | 104616 | 108921 | 119628 | 133421 | 145404 | 161207 | 180689 | 200006 | 243175 | 284104 | 318359 | 346181 | 367197 | 373650 | 373966
[6 empty] | 3066 ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY |  | 1492 | 04-Sep-25 A | 2027-09-08 | 34.27% | 32.13% | 45127358.15 | 48140194.66 | 102507 | 116383 | -5 | At Completion Labor Units | 3108 | 5586 | 7269 | 7553 | 9750 | 10940 | 9115 | 27258 | 18071 | 19762 | 1833 | 6185 | 9498 | 7755 | 18284 | 19093 | 17743 | 18146 | 37275 | 36295 | 33507 | 27214 | 17527 | 4612 | 591
[6 empty] | 3066 ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY |  | 1492 | 04-Sep-25 A | 2027-09-08 | 34.27% | 32.13% | 45127358.15 | 48140194.66 | 102507 | 116383 | -5 | Cum At Completion Labor Units | 3108 | 8695 | 15964 | 23516 | 33266 | 44206 | 53321 | 80578 | 98650 | 118411 | 120244 | 126429 | 135926 | 143682 | 161966 | 181059 | 198802 | 216948 | 254222 | 290517 | 324024 | 351238 | 368765 | 373377 | 373967
[6 empty] | Activity ID | Activity Name | Activity Count | BL Project Completed Activities | BL Project In-Progress Activities | Start | Finish | Performance % Complete | Schedule % Complete | Planned Value Labor Units | Earned Value Labor Units | Planned Value Cost | Earned Value Cost | Budgeted Total Cost | Total Float | Spreadsheet Field | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01
[6 empty] | 3066 ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY |  | 1492 | 395 | 11 | 04-Sep-25 A | 2027-09-15 | 35.13% | 32.31% | 103063 | 123184 | 45385512.58 | 49341804.54 | 140467862 | -10 | At Completion Labor Units | 3108 | 5586 | 7269 | 7553 | 9750 | 10940 | 9115 | 27258 | 18071 | 25130 | 2701 | 6573 | 9003 | 11514 | 20860 | 14219 | 18226 | 14571 | 35701 | 33158 | 33169 | 26133 | 17575 | 5993 | 791
[6 empty] | 3066 ADDITIONAL DEVELOPMENT IN TABOUK INDUSTRIAL CITY |  | 1492 | 395 | 11 | 04-Sep-25 A | 2027-09-15 | 35.13% | 32.31% | 103063 | 123184 | 45385512.58 | 49341804.54 | 140467862 | -10 | Cum At Completion Labor Units | 3108 | 8695 | 15964 | 23516 | 33266 | 44206 | 53321 | 80578 | 98650 | 123780 | 126480 | 133053 | 142056 | 153570 | 174430 | 188649 | 206876 | 221446 | 257147 | 290305 | 323474 | 349607 | 367182 | 373176 | 373967
Formulas:
Week = EOMONTH([Week, row above],1)

## Testing
Testing and Commissioning
Item | Planned Start Date | Planned Finish Date | Forecast Start Date | Forecast Finish Date | Actual Start Date | Actual Finish Date | % Completed | Open Comments | Closed Comments
ZONE 1 | 2027-05-01 | 2027-06-28 | 2027-05-01 | 2027-06-21
ROAD WORKS | 2027-06-09 | 2027-06-13 | 2027-06-16 | 2027-06-21
ELECTRICAL NETWORKS | 2027-06-01 | 2027-06-08 | 2027-06-08 | 2027-06-16
TELECOMMUNICATIONS NETWORKS | 2027-05-01 | 2027-05-04 | 2027-05-08 | 2027-05-12
CCTV NETWORKS | 2027-05-12 | 2027-05-19 | 2027-05-17 | 2027-05-25
POTABLE WATER NETWORKS | 2027-06-20 | 2027-06-23 | 2027-05-13 | 2027-05-18
TSE NETWORKS | 2027-06-24 | 2027-06-28 | 2027-05-20 | 2027-05-25
SEWERAGE NETWORKS | 2027-06-08 | 2027-06-14 | 2027-05-01 | 2027-05-08
STORM NETWORKS | 2027-06-12 | 2027-06-19 | 2027-05-04 | 2027-05-12
ZONE 2 | 2027-04-17 | 2027-08-24 | 2027-04-05 | 2027-08-30
ROAD WORKS | 2027-07-26 | 2027-08-02 | 2027-07-31 | 2027-08-08
ELECTRICAL NETWORKS | 2027-04-26 | 2027-05-03 | 2027-05-03 | 2027-05-11
TELECOMMUNICATIONS NETWORKS | 2027-06-07 | 2027-06-14 | 2027-06-07 | 2027-06-15
CCTV NETWORKS | 2027-08-17 | 2027-08-24 | 2027-08-22 | 2027-08-30
POTABLE WATER NETWORKS | 2027-07-08 | 2027-07-12 | 2027-06-03 | 2027-06-08
TSE NETWORKS | 2027-07-13 | 2027-07-17 | 2027-06-08 | 2027-06-13
SEWERAGE NETWORKS | 2027-04-17 | 2027-04-22 | 2027-04-05 | 2027-04-12
STORM NETWORKS | 2027-06-26 | 2027-07-03 | 2027-05-22 | 2027-05-30
ZONE 3 | 2027-07-04 | 2027-09-03 | 2027-05-19 | 2027-09-08
ROAD WORKS | 2027-08-03 | 2027-08-05 | 2027-08-08 | 2027-08-11
ELECTRICAL NETWORKS | 2027-08-02 | 2027-08-09 | 2027-07-27 | 2027-08-04
TELECOMMUNICATIONS NETWORKS | 2027-08-01 | 2027-08-08 | 2027-08-01 | 2027-08-09 | [5 empty] | Performance % Complete | Planned Value Cost | Actual Total Cost | Earned Value Cost | Activity % Complete | Units % Complete | Labor Units % Complete | Physical % Complete | Duration % Complete | Budgeted Labor Units | Planned Value Labor Units | Performance % Complete - Labor Units | Actual Labor Units | Earned Value Labor Units
CCTV NETWORKS | 2027-08-25 | 2027-09-03 | 2027-08-30 | 2027-09-08 | [5 empty] | 0% | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 576 | 0% | 0% | 0 | 0
POTABLE WATER NETWORKS | 2027-08-16 | 2027-08-21 | 2027-07-13 | 2027-07-19 | [5 empty] | 0% | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 640 | 0% | 0% | 0 | 0
TSE NETWORKS | 2027-07-19 | 2027-07-21 | 2027-06-17 | 2027-06-21 | [5 empty] | 0% | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 576 | 0% | 0% | 0 | 0
SEWERAGE NETWORKS | 2027-07-28 | 2027-08-02 | 2027-05-19 | 2027-05-25 | [5 empty] | 0% | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 576 | 0% | 0% | 0 | 0
STORM NETWORKS | 2027-07-04 | 2027-07-11 | 2027-06-10 | 2027-06-19 | [5 empty] | 0% | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 560 | 0% | 0% | 0 | 0
ROAD WORKS | 2027-07-01 | 2027-07-05 | 2027-07-05 | 2027-07-08
ELECTRICAL NETWORKS | 2027-08-02 | 2027-08-09 | 2027-07-27 | 2027-08-04
TELECOMMUNICATIONS NETWORKS | 2027-08-01 | 2027-08-08 | 2027-08-01 | 2027-08-09
CCTV NETWORKS | 2027-08-25 | 2027-09-03 | 2027-08-30 | 2027-09-08
POTABLE WATER NETWORKS | 2027-08-16 | 2027-08-21 | 2027-07-13 | 2027-07-19
TSE NETWORKS | 2027-07-19 | 2027-07-21 | 2027-06-17 | 2027-06-21
SEWERAGE NETWORKS | 2027-07-28 | 2027-08-02 | 2027-05-19 | 2027-05-25
STORM NETWORKS | 2027-07-04 | 2027-07-11 | 2027-06-10 | 2027-06-19
| Activity ID | Activity Name | Activity Count | BL Project Start | BL Project Finish | Start | Finish | Performance % Complete | Schedule % Complete | Planned Value Cost | Earned Value Cost | Planned Value Labor Units | Earned Value Labor Units | Total Float
| 3066.22.3.1 Final Test & commisionning Zone 1 |  | 8 | 2027-05-01 | 2027-06-28 | 2027-05-01 | 2027-06-21 | 0% | 0% | 0 | 0 | 0 | 0 | 55
| TACOFTFT0001 | Road Works | 1 | 2027-06-09 | 2027-06-13 | 2027-06-16 | 2027-06-21 | 0% | 0% | 0 | 0 | 0 | 0 | 30
| TACOFTFT0002 | Electrical NetWorks | 1 | 2027-06-01 | 2027-06-08 | 2027-06-08 | 2027-06-16 | 0% | 0% | 0 | 0 | 0 | 0 | 53
| TACOFTFT0003 | Telecommunications Networks | 1 | 2027-05-01 | 2027-05-04 | 2027-05-08 | 2027-05-12 | 0% | 0% | 0 | 0 | 0 | 0 | 83
| TACOFTFT0004 | CCTV Networks | 1 | 2027-05-12 | 2027-05-19 | 2027-05-17 | 2027-05-25 | 0% | 0% | 0 | 0 | 0 | 0 | 78
| TACOFTFT0005 | Potable Water Networks | 1 | 2027-06-20 | 2027-06-23 | 2027-05-13 | 2027-05-18 | 0% | 0% | 0 | 0 | 0 | 0 | 84
| TACOFTFT0006 | TSE Networks | 1 | 2027-06-24 | 2027-06-28 | 2027-05-20 | 2027-05-25 | 0% | 0% | 0 | 0 | 0 | 0 | 78
| TACOFTFT0007 | Sewerage Networks | 1 | 2027-06-08 | 2027-06-14 | 2027-05-01 | 2027-05-08 | 0% | 0% | 0 | 0 | 0 | 0 | 92
| TACOFTFT0008 | Storm Water Drainage Networks | 1 | 2027-06-12 | 2027-06-19 | 2027-05-04 | 2027-05-12 | 0% | 0% | 0 | 0 | 0 | 0 | 84
| 3066.22.3.2 Final Test & commisionning Zone 2 |  | 8 | 2027-04-17 | 2027-08-24 | 2027-04-05 | 2027-08-30 | 0% | 0% | 0 | 0 | 0 | 0 | 2
| TACOFTFT0009 | Road Works | 1 | 2027-07-26 | 2027-08-02 | 2027-07-31 | 2027-08-08 | 0% | 0% | 0 | 0 | 0 | 0 | -5
| TACOFTFT0010 | Electrical NetWorks | 1 | 2027-04-26 | 2027-05-03 | 2027-05-03 | 2027-05-11 | 0% | 0% | 0 | 0 | 0 | 0 | 71
| TACOFTFT0011 | Telecommunications Networks | 1 | 2027-06-07 | 2027-06-14 | 2027-06-07 | 2027-06-15 | 0% | 0% | 0 | 0 | 0 | 0 | 39
| TACOFTFT0012 | CCTV Networks | 1 | 2027-08-17 | 2027-08-24 | 2027-08-22 | 2027-08-30 | 0% | 0% | 0 | 0 | 0 | 0 | -4
| TACOFTFT0013 | Potable Water Networks | 1 | 2027-07-08 | 2027-07-12 | 2027-06-03 | 2027-06-08 | 0% | 0% | 0 | 0 | 0 | 0 | 71
| TACOFTFT0014 | TSE Networks | 1 | 2027-07-13 | 2027-07-17 | 2027-06-08 | 2027-06-13 | 0% | 0% | 0 | 0 | 0 | 0 | 69
| TACOFTFT0015 | Sewerage Networks | 1 | 2027-04-17 | 2027-04-22 | 2027-04-05 | 2027-04-12 | 0% | 0% | 0 | 0 | 0 | 0 | 93
| TACOFTFT0016 | Storm Water Drainage Networks | 1 | 2027-06-26 | 2027-07-03 | 2027-05-22 | 2027-05-30 | 0% | 0% | 0 | 0 | 0 | 0 | 65
| 3066.22.3.3 Final Test & commisionning Zone 3 |  | 8 | 2027-07-04 | 2027-09-03 | 2027-05-19 | 2027-09-08 | 0% | 0% | 0 | 0 | 0 | 0 | -4
| TACOFTFT0017 | Road Works | 1 | 2027-08-03 | 2027-08-05 | 2027-08-08 | 2027-08-11 | 0% | 0% | 0 | 0 | 0 | 0 | -5
| TACOFTFT0018 | Electrical NetWorks | 1 | 2027-08-02 | 2027-08-09 | 2027-07-27 | 2027-08-04 | 0% | 0% | 0 | 0 | 0 | 0 | 5
| TACOFTFT0019 | Telecommunications Networks | 1 | 2027-08-01 | 2027-08-08 | 2027-08-01 | 2027-08-09 | 0% | 0% | 0 | 0 | 0 | 0 | -1
| TACOFTFT0020 | CCTV Networks | 1 | 2027-08-25 | 2027-09-03 | 2027-08-30 | 2027-09-08 | 0% | 0% | 0 | 0 | 0 | 0 | -4
| TACOFTFT0021 | Potable Water Networks | 1 | 2027-08-16 | 2027-08-21 | 2027-07-13 | 2027-07-19 | 0% | 0% | 0 | 0 | 0 | 0 | 40
| TACOFTFT0022 | TSE Networks | 1 | 2027-07-19 | 2027-07-21 | 2027-06-17 | 2027-06-21 | 0% | 0% | 0 | 0 | 0 | 0 | 65
| TACOFTFT0023 | Sewerage Networks | 1 | 2027-07-28 | 2027-08-02 | 2027-05-19 | 2027-05-25 | 0% | 0% | 0 | 0 | 0 | 0 | 61
| TACOFTFT0024 | Storm Water Drainage Networks | 1 | 2027-07-04 | 2027-07-11 | 2027-06-10 | 2027-06-19 | 0% | 0% | 0 | 0 | 0 | 0 | 54

## CONCULUSTION
تطوير اضافي في المدينة الصناعية بتبوك
معلومات المشروع |  |  |  | نطاق المشروع
المقاول | شركة أساس لتطوير و تشغيل المدن الصناعية | الاستشاري | شركة ايجيس السعودية للاستشارات | البند | الكمية الكلية | الكمية المنفذة | الكمية المتبقية | نسبة المنفذ
تاريخ استلام الموقع | 2025-09-04 | مدة التنفيذ | 24 شهرًا ميلاديًا | ZONE 1 | 100% | 65.23% | 34.77% | 65.23%
بداية العقد | 2025-08-31 | قيمة العقد (غير شامل ضريبة القيمة المضافة ) | 140467862 | ZONE 2 | 100% | 59.3% | 40.7% | 59.3%
نسبة الإنجاز المخطط له | 36.95% | نسبة الإنجاز الفعلي | 46.89% | ZONE 3 | 100% | 35.59% | 64.41% | 35.59%
ملخص جدول الكميات
مكونات المشروع |  | التكلفة (غير شامل ضريبة القيمة المضافة) | النسبة الاجمالية
ROADS |  | 55700828 | 39.65%
ELECTRICAL |  | 21956853 | 15.63%
POTABLE WATER NETWORK |  | 7176559 | 5.109%
TSE NETWORK |  | 6656378 | 4.739% | ملخص التوريدات
SEWERAGE NETWORK |  | 6435003 | 4.581% | البند | الكمية الكلية | الكمية المورده | الكمية المتبقية | نسبة التوريد
STORM WATER NETWORK |  | 42542241 | 30.29% | GRP PIPES FOR SEWERAGE | 8370 | 8095 | 275 | 96.71%
|  |  |  | GRP PIPES FOR STORM | 9153 | 9017 | 136 | 98.51%
|  |  |  | UPVC FOR STORM | 7032 | 7032 | 0 | 100%
معالم البرنامج الزمني |  |  |  | VALVES | 287 | 287 | 0 | 100%
البند |  | التاريخ حسب الجدول الزمني | ملاحظة | PE Pipes | 26080 | 26080 | 0 | 100%
END PROJECT |  | 2027-09-03 |  | Fiberglass Manholes,ets | 142 | 142 | 0 | 100%
START PROJECT |  | 2025-09-04 | تم البدء | Manholes,ets | 123 | 123 | 0 | 100%
FINISH ZONE1 |  | 2027-02-09 | جاري التنفيذ | Fire Hydrent | 152 | 152 | 0 | 100%
FINISH ZONE2 |  | 2027-08-02 | جاري التنفيذ | BOX CULVERT | 471 | 461 | 10 | 97.88%
FINISH ZONE3 |  | 2027-08-02 | جاري التنفيذ | التحديات والعوائق
ترقية المخططات لكود A
ربط شبكة الكهرباء مع المحطة
معوقات اعمال الكهرباء
1

## LOOK AHEAD
# | القطاع | المبادرة | Project ID | اسم المشروع | مدير المشروع | المقاول | بداية المشروع | نهاية المشروع التعاقدية | مدة المشروع (أشهر) | نهاية المشروع المتوقعة/ الالتزام | قيمة المشروع | المخطط /الفعلي | Mobilization المخطط | Mobilization المنفذ | Procurement (Long Lead Items) توريد المواد طويلة الأجل (المخطط) | Procurement (Long Lead Items) توريد المواد طويلة الأجل (المنفذ) | Civil Work الأعمال المدنيه (المخطط) | Civil Work الأعمال المدنيه (المنفذ) | Mechnical Work أعمال الميكانيكا (المخطط) | Mechnical Work أعمال الميكانيكا (المنفذ) | Mechnical Work أعمال الكهرباء (المخطط) | Mechnical Work أعمال الكهرباء (المنفذ) | تأثير التأخير (إن وجد) على المبادرات في الربع | نسبة الانجاز المستهدفة بنهاية الربع | نسبة الانجاز المحققة بنهاية الربع | مجموع المبالغ المفوترة المستهدفة بنهاية الربع | مجموع المبالغ المفوترة المحققة بنهاية الربع | نهاية المشروع المتوقعة
1 | TABOUK | - | TAB1-02-003 | تطوير اضافي في المدينة الصناعية بتبوك | م.يزيد | Asas for Developing and Operating | 2025-09-04 | 2027-09-03 | 24 | 2027-09-03 | 140467862 | 100% | 100% | 100% | UPVC -GRP PIPES -MANHOLES - BOX CUILVERT-VALVES FOR TSE-FIRE HYDRENT-HDPE-RIPRAP FOR DIKE-ABC - CERBSTONE-INTERLOOK | تم توريد UPVS - MANHOLES متبقي الملحقات جاري توريد - GRP - HDPE - -BOX CULVERT - FIPERGLASS-BBC-VALVES-CERBSTONE-FIRE HYDRENT-CATCHBASIN-UPVC ELECTRIC-ABC-HDPE ELECTRICAL-CABLE MV--RMU | اعمال حفر LOCAL 4-6-8 / اعمال ردم COLLECTOR 1-2 - LOCAL 3-4-6-8 / SUBGRADE COLLECTOR 1 -LOCAL1- 3-4-5-6-8-10+POND اعمال-UP21-28-29 ABC&BBC COLLECTOR1-2- 3-LOCAL2-3-4-5-9 اعمال طريق المحلي 2 abc اعمال الطريق المحلي subgrade 5 | تم الانتهاء من حفر COLLECTOR1- 2 و4-2-1- LOCAL 3-5-9-10-6-7 وجاري اعمال حفر LOCAL 8 تم الانتهاء من ردم COLLECTOR 3-1 - LOCAL2- 5-9-10-1-7-3-4 وجاري ردم LOCAL 8-6 جاري حفر POND -تم الانتهاء من اعمال 1-3-4-5 -SUBGRADE collector 03- LOCAL 9-2-7 - جاري اعمالSUPGRADE COLLECTOR 1-2-LOCAL -6-8 AMANAH ROAD asphalt +m c1تم الانتهاء و اعمال البردورة و عمل العلامات الارضية تم الانتهاء من ردم الجسر تم الانتهاء من اعمال رش وطبقة الاساس الاسفلتية للطريق المجمع 3والمحلي 2-5 تم اعمال تركيب الربراب للبركة وااسد - تم طريق المحلي -3-2-4- BBC-5 تم الانتهاءاعمالABC طريق-1-3 وجاري 2 BBC مدخل المدينة الصناعية تم الانتهاء من البردورة طريق مجمع 3وجاري طريق -4-5-2 ABC COLLECTOR 2 | اعمال شبكات الصرف COLLECTOR 1-2-UPGRADE21-20-32-33 -LOCAL 4-5-3-10/ اعمال شبكات المطر COLLECTOR 1-2-3-UPGRADE 21-39-20-32-33-LOCAL 2-3-4-5-10 اعمال شبكة المياه COLLECTOR 1-2-3-LOCAL10-UP21-28 اعمال شبكة الري COLLECTOR 2- 3- | LOCAL 1-COLLECTOR 1 شبكة الصرف الصحي حفر تم الانتهاء من اعمال ردم شبكة الصرف الصحي LOCAL3 -4-6-10-5 جاري ردم شبكة الصرف الصحي LOCAL1-8 جاري اعمال حفر شبكات المطر COLLECTOR 1-LOCAL 3-1-8-9-UPGRADE 39-21 وجاري اعمال تمديد مواسيرCOLLECTOR 1- 2-LOCAL-7-8 -UPGRADE 21-39 جاري تركيب مناهيل COLLECTOR 2-1-LOCAL -7-8-9-10-1UPGRADE 21-39 صرف صحي ومطر جاري اعمال BOX CULVERT COLLECTOR 1-LOCAL1 جاري اعمال ردم شبكة المطر collector 2-1 - local-3-7--1-8 جاري اعمال شبكة الري3--COLLECTOR 2 -LOCAL1-7-9 جاري اعمال شبكة المياه 3--COLLECTOR 2-1-LOCAL -7-9-1 تم الانتهاء من تركيب طفايا الحريق والمحابس وردم شبكة المياه و المطر ل-LOCAL 2-5-4 -COLLECTOR 3 , تم الانتهاء من اعمال المطر ومصائد الامطار وشبكة الري والمياه للطريق المجمع-2-4-5 3 جارري اعمال الاختبارات لشبكة الصرف والمطر الطريق المجمع 2 والمحلي 5 تم الانتهاء من اعمال شبكة الصرف الطريق المحلي 5- 3-4 تم الانتهاء من شبكة الري والمياه الطريق المحلي -4-5-2والطريق المجمع 3 تم الانتهاء يالمحابس والغرف لطريق المحلي 5-2-4 تم البدء باعمال شبكة المياه والري الطريق المحلي 1-3 اعمال مصائد الامطار طريق مجمع 2 اعمال حفر شبكة المياه - الري طريق 29 تم الانتهاء مصائد الامطار للطريق المحلي5 -2-4-1 تم البدء باعمال حفر الصرف الصحي+المياه IPGRADE 21 اعمال طريق 33 صرف صحي تركيب مصائد الامطار طريق مجمع 2 | اعمال شبكة الاتصالات COLLECTOR 2-3 | تم الانتهاء من حفر وردم وتمديد التقاطع شبكة الكهرباء COLLECTOR 3 تم الانتهاء من حفر طريق 2 -5-4و الردم والتغليف وجاري اعمال حفر وتمديد الطريق -20 12-26-14-8 mv | لا يوجد | 43.4% | 46.89% | 60969968.46 | 43497867.43 | 2027-10-02

## Codes (hidden)
Status List
| Approved |  | Y
| Pending |  | N | [5 empty] | (Manhours)
| Potential | [7 empty] | (Mandays)
| Phase | Stage |  | Stage |  | Status |  | Score
[8 empty] | Low | Contractor | Active
| Launch | LOA |  | LOA |  | Active |  | Medium | CM | Expired
| Launch | Kick-off Meeting |  | Kick-off Meeting |  | On Hold |  | High | PgM | Occurred
| Launch | Site Handover |  |  |  | Terminated |  |  | Modon | Pending
| Launch | Mobilization |  | Mobilization | Initial staff and equipment in place, ready to start production | Terminated, Closed |  |  | Other
| Execution | Construction |  | Execution | Tender Documents Issued | Substantial Complete | Initial Handover done at site
| Execution | T&C |  |  | Responses to the OCS completed | Complete | Initial Handover Signed
| Execution | Initial Handover |  | Closeout | Design close-out process complete | Closed | Final Handover done at Site
Warranty Period
Final Handover
Project Status Score
Elements |  |  | Max | Score | Planned | Actual | Remarks
SPI (Physical Effort) |  |  | 100% | 142.7% | No Entry Required
SPI (Cost) |  |  | 100% | 126.9% | No Entry Required
On Schedule -Active |  |  | 100% | 100% | No Entry Required |  |  |  | 0.6
Manpower Availability |  |  | 100% | 282.3% | No Entry Required
Major Equipment Availability |  |  | 100% | 150% | No Entry Required
Billing % Compared to Planned |  |  | 100% | 79.06% | No Entry Required
Safety Score |  |  | 100% | 86.71% | No Entry Required
Quality Score |  |  | 100% | #REF! | No Entry Required