## Dashboard (hidden)
MODON Design Department — Risk & Issue Dashboard
Open Risks | High | Medium | Low |  |  | Open Issues | Critical | High | Normal
9 | 6 | 2 | 1 |  |  | 1 | 0 | 0 | 0
Risks by category × rating | [5 empty] | Issues by category × priority
Category | High | Medium | Low | Total | Exposure (SAR M) | Category | Critical | High | Normal | Total | Exposure (SAR M)
Contractor Performance | 1 | 0 | 0 | 1 | 0 | Contractor Performance | 0 | 0 | 0 | 0 | 0
Contractual | 0 | 0 | 0 | 0 | 0 | Contractual | 0 | 0 | 0 | 0 | 0
Cost | 0 | 0 | 0 | 0 | 0 | Cost | 0 | 0 | 0 | 0 | 0
Financial | 0 | 0 | 0 | 0 | 0 | Design/Technical | 0 | 0 | 0 | 0 | 0
Reporting | 0 | 0 | 0 | 0 | 0 | Financial | 0 | 0 | 0 | 0 | 0
Resources | 1 | 0 | 0 | 1 | 0 | Interface/Utilities | 0 | 0 | 0 | 0 | 0
Schedule | 0 | 0 | 0 | 0 | 0 | Permits/Stakeholder | 0 | 0 | 0 | 0 | 0
Total | 2 | 0 | 0 | 2 | 0 | Quality/HSE | 0 | 0 | 0 | 0 | 0
[6 empty] | Schedule | 0 | 0 | 0 | 0 | 0
[6 empty] | Scope | 0 | 0 | 0 | 0 | 0
[6 empty] | Site/Technical | 0 | 0 | 0 | 0 | 0
[6 empty] | Total | 0 | 0 | 0 | 0 | 0
Risks by fund source | [5 empty] | Issues by fund source
Category | High | Medium | Low | Total |  | Category | Critical | High | Normal | Total
MODON | 0 | 0 | 0 | 0 |  | MODON | 0 | 0 | 0 | 0
MOF | 0 | 0 | 0 | 0 |  | MOF | 0 | 0 | 0 | 0
MTLS | 0 | 0 | 0 | 0 |  | MTLS | 0 | 0 | 0 | 0
Modon | 0 | 0 | 0 | 0 |  | Modon | 0 | 0 | 0 | 0
NIDLP | 0 | 0 | 0 | 0 |  | NIDLP | 0 | 0 | 0 | 0
NIS | 0 | 0 | 0 | 0 |  | NIS | 0 | 0 | 0 | 0
Other | 0 | 0 | 0 | 0 |  | Other | 0 | 0 | 0 | 0
WAS | 0 | 0 | 0 | 0 |  | WAS | 0 | 0 | 0 | 0
التجمعات الصناعية | 0 | 0 | 0 | 0 |  | التجمعات الصناعية | 0 | 0 | 0 | 0
الصندوق الصناعي | 0 | 0 | 0 | 0 |  | الصندوق الصناعي | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 |  | Total | 0 | 0 | 0 | 0
Scoring: Risk Score = Probability × Impact → High ≥15, Medium 8–14, Low <8. Issue Priority = Severity × Urgency → Critical ≥15, High 8–14, Normal <8. Impact from value: ≥100M=5, 50–100M=4, 20–50M=3, 5–20M=2, <5M=1. Counts exclude entries with Status = Closed.

## Risk Log
Risk Log
Risk ID | Parent Project ID | Contract / Project ID | Project Name | City | Region | Fund Source | Phase | PM / Owner | Contractor / Designer | Current Status | Value (SAR) | Category | Risk Title | Description | Evidence / Data | Probability (1-5) | Impact (1-5) | Score | Rating | Response | Mitigation Plan | Date Identified | Status | Target Date | Notes / Updates | Source
MLTX-02-004-01 | MLTX-02-004 | MLTX-02-004 | Playground Initiative for Western Region (Asir - Jazan - Jeddah) | Asir / Jazan / Jeddah | Western |  |  | Contractor | Contractor |  |  | Resources | Delay of Material Delivery of Air Dome | Cause/Source: Delay of Material Delivery for Long Lead Item ¦ Consequence/Effect: Delay In Construction Works |  | 4 | 5 | 20 | High | Mitigate | Continous follow up with MODON Representative to expedite the approval process of AIR Dome Design | 2026-04-30 | Open | 2026-11-15 | Original Risk Response Strategy: Treat; Treatment Action: Mitigate; Treatment Owner: Contractor; Treatment Start: 2026-04-30; Post-Treatment Likelihood/Impact: High/High (Score H16); Treatment Status: Open | Migrated from legacy Risk Register (Western Region)
MLTX-02-004-02 | MLTX-02-004 | MLTX-02-004 | Playground Initiative for Western Region (Asir - Jazan - Jeddah) | Asir / Jazan / Jeddah | Western |  |  | Contractor | Contractor |  |  | Quality/HSE | Unauthorized entry to site | Cause/Source: General site workers ¦ Consequence/Effect: Injury to 3rd party / Unauthorized access / Breach of Perimeter fence / Access of non-inducted persons to Site / Trip hazards Visitors access |  | 3 | 4 | 12 | Medium | Mitigate | Implement a comprehensive security framework that combines physical barriers, electronic surveillance, and strict access protocols to prevent, detect, and respond to unauthorized entry. | 2026-03-11 | Open | 2027-01-25 | Original Risk Response Strategy: Treat; Treatment Action: Control; Treatment Owner: Contractor; Treatment Start: 2026-03-12; Post-Treatment Likelihood/Impact: Medium/High (Score M12); Treatment Status: Open | Migrated from legacy Risk Register (Western Region)
MLTX-02-004-03 | MLTX-02-004 | MLTX-02-004 | Playground Initiative for Western Region (Asir - Jazan - Jeddah) | Asir / Jazan / Jeddah | Western |  |  | Contractor | Contractor |  |  | Quality/HSE | Failure to test and monitor air quality in confined spaces | Cause/Source: General site workers / General site staff / Site visitors ¦ Consequence/Effect: Fire leading to fatality / property damage |  | 4 | 5 | 20 | High | Mitigate | Establish a mandatory atmospheric testing protocol requiring pre-entry gas detection, continuous real-time monitoring, and mechanical ventilation under a strict permit-to-work system to ensure a safe, breathable environment. | 2026-03-11 | Open | 2027-01-25 | Original Risk Response Strategy: Treat; Treatment Action: Control; Treatment Owner: Contractor; Treatment Start: 2026-03-12; Post-Treatment Likelihood/Impact: High/Very High (Score H20); Treatment Status: Open | Migrated from legacy Risk Register (Western Region)
MLTX-02-004-04 | MLTX-02-004 | MLTX-02-004 | Playground Initiative for Western Region (Asir - Jazan - Jeddah) | Asir / Jazan / Jeddah | Western |  |  | Contractor | Contractor |  |  | Quality/HSE | Unsafe storage of materials | Cause/Source: General site workers / General site staff / Site visitors ¦ Consequence/Effect: Fire / Overloading and collapse of racking ,shelving / Chemical spills / Tipping & collapse of stacked materials / Unsafe movement of large diameter pipes |  | 3 | 4 | 12 | Medium | Mitigate | Implement a structured material management plan that enforces proper stacking heights, secondary containment for hazardous liquids, and clear segregation of incompatible substances within designated, well-labeled storage zones. | 2026-03-11 | Open | 2027-01-25 | Original Risk Response Strategy: Treat; Treatment Action: Mitigate; Treatment Owner: Contractor; Treatment Start: 2026-03-12; Post-Treatment Likelihood/Impact: Medium/High (Score M12); Treatment Status: Open | Migrated from legacy Risk Register (Western Region)
MLTX-02-004-05 | MLTX-02-004 | MLTX-02-004 | Playground Initiative for Western Region (Asir - Jazan - Jeddah) | Asir / Jazan / Jeddah | Western |  |  | Contractor | Contractor |  |  | Contractor Performance | Lack of equipment maintenance & certification | Cause/Source: General site workers / General site staff / Site visitors ¦ Consequence/Effect: Financial and production loss due to damage or quarantine of plant / vehicle |  | 4 | 5 | 20 | High | Mitigate | Establish a rigorous maintenance management system that mandates scheduled preventive inspections, real-time tracking of certification validity, and a "tag-out" policy for any equipment that does not meet current regulatory safety standards | 2026-03-11 | Open | 2027-01-25 | Original Risk Response Strategy: Treat; Treatment Action: Mitigate; Treatment Owner: Contractor; Treatment Start: 2026-03-12; Post-Treatment Likelihood/Impact: High/Very High (Score H20); Treatment Status: Open | Migrated from legacy Risk Register (Western Region)
MLTX-02-004-06 | MLTX-02-004 | MLTX-02-004 | Playground Initiative for Western Region (Asir - Jazan - Jeddah) | Asir / Jazan / Jeddah | Western |  |  | Contractor | Contractor |  |  | Site/Technical | Lack of, or use of, substandard fall arrest / fall restraint equipment or installation by incompetent persons | Cause/Source: General site workers ¦ Consequence/Effect: Personal injury due to falls and impact of falling objects / Damage due to falling objects leading to financial and production loss |  | 4 | 5 | 20 | High | Mitigate | Enforce a strict fall-protection program that mandates the use of certified, high-quality equipment installed and inspected exclusively by qualified persons in accordance with manufacturer specifications and safety regulations | 2026-03-11 | Open | 2027-01-25 | Original Risk Response Strategy: Treat; Treatment Action: Control; Treatment Owner: Contractor; Treatment Start: 2026-03-12; Post-Treatment Likelihood/Impact: High/Very High (Score H20); Treatment Status: Open | Migrated from legacy Risk Register (Western Region)
MLTX-02-004-07 | MLTX-02-004 | MLTX-02-004 | Playground Initiative for Western Region (Asir - Jazan - Jeddah) | Asir / Jazan / Jeddah | Western |  |  | Contractor | Contractor |  |  | Quality/HSE | Defective Tools / Equipment | Cause/Source: General site staff / Site visitors ¦ Consequence/Effect: Physical injuries, Property damage |  | 2 | 3 | 6 | Low | Mitigate | Required PPE is being used | 2026-03-11 | Open | 2027-01-25 | Original Risk Response Strategy: Treat; Treatment Action: Control; Treatment Owner: Contractor; Treatment Start: 2026-03-12; Post-Treatment Likelihood/Impact: Low/Medium (Score M6); Treatment Status: Open | Migrated from legacy Risk Register (Western Region)
MLTX-02-004-08 | MLTX-02-004 | MLTX-02-004 | Playground Initiative for Western Region (Asir - Jazan - Jeddah) | Asir / Jazan / Jeddah | Western |  |  | Contractor | Contractor |  |  | Site/Technical | Failure to consider weather / climate | Cause/Source: General site workers / General site staff / Site visitors ¦ Consequence/Effect: Illness due to temperature extremes e.g. dehydration, heat stress/ Irrational and / or violent behavior |  | 4 | 4 | 16 | High | Accept | Install and maintain heating / air conditioning / dehumidifying systems / Implement control measures in line with the project heat stress management plan. / Implement counter measures such as drinking programs, use of electrolytes etc. Counter measures shall be medically proven and shall be appropriate to the location | 2026-03-11 | Open | 2027-01-25 | Original Risk Response Strategy: Accept; Treatment Action: Control; Treatment Owner: Contractor; Treatment Start: 2026-03-12; Post-Treatment Likelihood/Impact: High/High (Score H16); Treatment Status: Open | Migrated from legacy Risk Register (Western Region)
MLTX-02-004-09 | MLTX-02-004 | MLTX-02-004 | Playground Initiative for Western Region (Asir - Jazan - Jeddah) | Asir / Jazan / Jeddah | Western |  |  | Contractor | Contractor |  |  | Interface/Utilities | Failure to designate and separate external traffic / pedestrian routes | Cause/Source: General site workers General site staff Site visitors Neighbors General public ¦ Consequence/Effect: Traffic accident – fatality / damage / lost production |  | 3 | 5 | 15 | High | Mitigate | Traffic management shall be in line with the requirements of THABAT Traffic Management Plan / Site access / egress shall be in line with the requirements of THABAT HSE Plan – Access / Egress A site logistics plan shall be prepared. This shall detail the site boundary, pedestrian and vehicle access and site roads / Barriers shall be installed to separate pedestrians from vehicle traffic. Pedestrian routes shall be clearly marked and illuminated where necessary. Signage should be in a language understood by the majority of the labour | 2026-03-11 | Open | 2027-01-25 | Original Risk Response Strategy: Treat; Treatment Action: Control; Treatment Owner: Contractor; Treatment Start: 2026-03-12; Post-Treatment Likelihood/Impact: Medium/Very High (Score H15); Treatment Status: Open | Migrated from legacy Risk Register (Western Region)

## Issue Log
Issue Log
Issue ID | Parent Project ID | Contract / Project ID | Project Name | City | Region | Fund Source | Phase | PM / Owner | Contractor / Designer | Current Status | Value (SAR) | Category | Issue Title | Description | Evidence / Data | Severity (1-5) | Urgency (1-5) | Priority Score | Priority | Action Required | Date Raised | Status | Target Date | Resolution / Updates | Source
MLTX-02-004-ISS-01 | MLTX-02-004 | MLTX-02-004 | Playground Initiative for Western Region (Asir - Jazan - Jeddah) | Jeddah | Western |  |  | Contractor | Owner |  |  | Site/Technical | Connection of the project to the drainage channel on the... | Connection of the project to the drainage channel on the eastern side.(Jeddah) | [5 empty] | Coordination between the Municipality (City Management) and the infrastructure contractor. |  | Closed | 2026-05-21 | Follow-up owner noted in legacy log: Owner; Completed on 2026-05-21; Severity/Urgency ratings were not present in the legacy log — needs PM input to score priority. | Migrated from legacy Issue Log (Western Region)
MLTX-02-004-ISS-02 | MLTX-02-004 | MLTX-02-004 | Playground Initiative for Western Region (Asir - Jazan - Jeddah) | Jeddah | Western |  |  | Owner | Contractor |  |  | Site/Technical | drainage pipe was encountered during site excavation.(Jeddah) | drainage pipe was encountered during site excavation.(Jeddah) | [5 empty] | The required calculations and slope analysis have been completed. |  | Closed | 2026-05-21 | Follow-up owner noted in legacy log: Contractor; Completed on 2026-05-21; Severity/Urgency ratings were not present in the legacy log — needs PM input to score priority. | Migrated from legacy Issue Log (Western Region)
MLTX-02-004-ISS-03 | MLTX-02-004 | MLTX-02-004 | Playground Initiative for Western Region (Asir - Jazan - Jeddah) | Jeddah | Western |  |  | Owner | Consultant |  |  | Site/Technical | Based on the visit by Modon management, it was noted... | Based on the visit by Modon management, it was noted that the project level can be raised to match the external road level in front of the parking area.(Jeddah) | [5 empty] | The required filling quantity was estimated at 59,000 m³ | 2026-05-05 | Closed | 2026-05-21 | Follow-up owner noted in legacy log: Consultant; Legacy log override note: closed; Completed on 2026-05-21; Severity/Urgency ratings were not present in the legacy log — needs PM input to score priority. | Migrated from legacy Issue Log (Western Region)
MLTX-02-004-ISS-04 | MLTX-02-004 | MLTX-02-004 | Playground Initiative for Western Region (Asir - Jazan - Jeddah) | Asir | Western |  |  | Contractor |  |  |  | Design/Technical | Increase the sewage tank capacity for the Asir project to... | Increase the sewage tank capacity for the Asir project to serve the administration building and playgrounds. | [5 empty] | Waiting for clarification of the project savings/cost reductions. |  | Closed | 2026-05-10 | Completed on 2026-05-10; Severity/Urgency ratings were not present in the legacy log — needs PM input to score priority. | Migrated from legacy Issue Log (Western Region)
MLTX-02-004-ISS-05 | MLTX-02-004 | MLTX-02-004 | Playground Initiative for Western Region (Asir - Jazan - Jeddah) | Jazan | Western |  |  | Consultant |  |  |  | Site/Technical | Difficulty accessing the parking area due to a level difference-... | Difficulty accessing the parking area due to a level difference- Jazan | [5 empty] | Relocating the parking area to the far left side. | 2026-05-21 | Closed | 2026-05-16 | Completed on 2026-05-16; Severity/Urgency ratings were not present in the legacy log — needs PM input to score priority. | Migrated from legacy Issue Log (Western Region)
MLTX-02-004-ISS-06 | MLTX-02-004 | MLTX-02-004 | Playground Initiative for Western Region (Asir - Jazan - Jeddah) | Jeddah | Western |  |  | Consultant |  |  |  | Site/Technical | Road shoulder overlap at the Jeddah site | Road shoulder overlap at the Jeddah site | [5 empty] | A proposal has been submitted to the consultant. | 2026-05-13 | Closed | 2026-10-01 | Severity/Urgency ratings were not present in the legacy log — needs PM input to score priority. | Migrated from legacy Issue Log (Western Region)
MLTX-02-004-ISS-07 | MLTX-02-004 | MLTX-02-004 | Playground Initiative for Western Region (Asir - Jazan - Jeddah) | Asir | Western |  |  | Owner |  |  |  | Permits/Stakeholder | Trees located within Asir site. | Trees located within Asir site. | [5 empty] | Waiting for tree removal by the landscaping contractor. | 2026-02-06 | Closed | 2026-05-16 | Completed on 2026-05-16; Severity/Urgency ratings were not present in the legacy log — needs PM input to score priority. | Migrated from legacy Issue Log (Western Region)
MLTX-02-004-ISS-07 | MLTX-02-004 | MLTX-02-004 | Playground Initiative for Western Region (Asir - Jazan - Jeddah) | Jazan | Western |  |  | Owner |  |  |  | Site/Technical | Medium voltage cables on excavation way | Medium voltage cables on excavation way | [5 empty] | Waiting for owner permission | 2026-10-10 | Open |  | Medium voltage cables are conflicting with the excavation route. Assessment and coordination with relevant stakeholders are ongoing to determine the required mitigation actions. Risk remains open. | Excavation Works

## Lists (hidden)
Status | Response | Scale | RiskCategory
Open | Avoid | 1 | Schedule
In Progress | Mitigate | 2 | Cost
Monitoring | Transfer | 3 | Financial
Closed | Accept | 4 | Scope
|  | 5 | Contractual
Resources
Contractor Performance
Reporting
Design/Technical
Permits/Stakeholder
Interface/Utilities
Quality/HSE
Site/Technical

## Rules (hidden)
Detection rules & methodology
Each entry in the logs was generated by one of these rules. Adjust thresholds here for reference; logs are static once generated.
Log | Rule | Condition (source field) | Default score | Suggested response
Issue | Schedule slippage beyond tolerance | CWAR Schedule Variance < −10% (Severity 5 if < −25%) | Sev 4–5 × Urg 4 | Recovery plan, EOT/penalty assessment
Issue | Contract flagged as delayed | CWAR "Delayed?" = 1 | Sev 4 × Urg 4 | Delay notice, revised finish
Issue | Extension of time granted | CWAR Approved Extension Of Time > 0 | Sev 3 × Urg 2 | Track vs revised finish
Issue | Contract on hold | CWAR Current Status = Hold | Sev 5 × Urg 5 | Escalate, resumption plan
Issue | Invoices pending payment | CWAR Invoices Pending Payment > 0 | Sev 3 × Urg 3 | Finance follow-up
Issue | Contract value exceeds approved budget | CWAR Current Approved Contract Value > Approved Budget | Sev 4 × Urg 3 | Budget re-approval
Issue | EAC exceeds contract value | CWAR EAC > Current Approved Contract Value | Sev 4 × Urg 3 | Validate EAC, variation
Issue | Approved change orders | CWAR Approved Change Orders (Nos.) > 0 | Sev 2 × Urg 2 | Update baseline
Issue | Guarantee / insurance expired | CWAR "Expired or Expiring in 3 Months" = منتهي الصلاحية, or Insurance Expiry < Data Date | Sev 4 × Urg 5 | Immediate renewal
Issue | Quality / Safety NCRs | CWAR NCRs Issued > 0 | Sev 3 × Urg 3 | Corrective action
Issue | Site / interface / permit / design / contractor issue | CWAR "Remarks on Schedule Status" non-empty (keyword-classified into category) | Sev 3–4 × Urg 3 | PM action owner
Issue | Ongoing project without full approval | All Projects: Status = Ongoing and حالة الاعتماد ∈ {غير معتمد, اعتماد جزئي} | Sev 3–4 × Urg 4 | Expedite approval
Risk | Progress trending behind plan | CWAR Schedule Variance between −5% and −10% | Prob 3 | Mitigate
Risk | Guarantee / insurance expiring ≤ 3 months | CWAR "Expired or Expiring" = تنتهي في ثلاثة أشهر, or Insurance Expiry within 90 days | Prob 4 | Mitigate
Risk | Insufficient time to complete | CWAR Remaining Duration < 90 days and Actual < 85% (Active) | Prob 4 | Mitigate
Risk | Manpower below plan | CWAR Actual Manpower < 70% of Plan Manpower | Prob 3 | Mitigate
Risk | Potential change orders | CWAR Potential Changes (Active) > 0 | Prob 3 | Mitigate
Risk | Baseline not approved / works suspended | CWAR "Delays by Modon or Contractor" contains baseline / stoppage keywords | Prob 3–4 | Mitigate
Risk | Mobilisation / start-up delay | CWAR Status ∈ {LOA, Open} or Actual = 0% more than 60 days after contract start | Prob 3 | Mitigate
Risk | Contractor delayed on multiple contracts | Same contractor with ≥2 active contracts at SV < −10% | Prob 4 | Mitigate
Risk | Budget not approved for next phase | All Projects: Status ∈ {Design completed, Tendered, Future} and حالة الاعتماد ∈ {غير معتمد, اعتماد جزئي} | Prob 3–4 | Mitigate
Risk | No approved budget baseline | All Projects: Status ∈ {Design completed, Future, Under design} and Approved Budget blank/0 | Prob 3 | Mitigate
Risk | Completed design awaiting tender | All Projects: Status = Design completed and no Contractor | Prob 2 | Accept / monitor
Risk | No active CWAR record | All Projects: Status = Ongoing and Parent Project ID not found in active CWAR rows | Prob 3 | Mitigate
Both | Impact scale (from value incl. VAT) | ≥100M = 5 · 50–100M = 4 · 20–50M = 3 · 5–20M = 2 · <5M = 1
Both | Scope | Active CWAR = Current Status ∈ {Active, Substantial Complete, LOA, Hold, Open}. Portfolio excludes Completed, Closed, Merged, Terminated.