## Slide 1: Weekly Progress Report – Construction Projects
Projects Department

## Slide 2: Disclaimer
This report is not all inclusive, nor it is intended to address the entirety of construction progress. It is concerned primarily with construction progress and is intended to provide near term management information. The report itself serves as the Agenda for the weekly/Biweekly/Monthly or as required progress meetings.

## Slide 3: Introduction

## Slide 4: Weekly Progress Report Dashboard

## Slide 5
مجموعة اﻳﺠﺲ لإدارة المشاريع | إستشاري المشروع | الانشاء المتقدم للمقاولات | مقاول المشروع
16-Dec-2026 | تاريخ نهاية المشروع التعاقدية | 17-Feb-2026 | تاريخ بداية المشروع
69.00% | نسبة الانجاز الفعلى بالمشروع | 80.32% | النسبة المستهدفة (طبقا للبرنامج الزمنى التعاقدي)
Progress Overview
Chart: 
| elapsed | remaining
time elapsed | 243 | 59
Project Progress | Planned % | Actual %
 | 80.32 % | 69.00 %

## Slide 6: Weekly Progress Report Attachment
Weekly Progress Report Attachement
Contractor/Consultant should ensure that the weekly progress report are supported with required attachment.
Those attachment should include the following as a minimum requirement:
Approved Primavera P6 Schedule in .xer format.
3-5 latest progress photographs in JPG format
Updated Primavera P6 schedule in .xer format & PDF Format Three weeks look ahead in PDF format. (as per plf link)
Remaining Works in PDF format.
Any other supporting document required per the development of the project.

## Slide 7: Weekly Report Areas / Sections

## Slide 8: Weekly Report Areas / Sections
Contract General Information
Key Dates
Progress Overview
Construction Milestones
Submittals Status
Material Approval Status
HSE
Invoices
Shop Drawing Status
Resources at Site
Primavera P6 Schedule Status
Contract Change Order Log
Major Quantity Trackers
Testing And Commissioning
Top Issues
Quality

## Slide 9: Weekly Report Areas / General Information
Contract General Information

## Slide 10: Weekly Report Areas / Dates
Key Dates

## Slide 11: Weekly Report Areas / Dates
Key Dates

## Slide 12: Weekly Report Areas / Progress
Progress Overview

## Slide 13: Weekly Report Areas / Progress
Progress Overview

## Slide 14: Weekly Report Areas / Progress
Progress Overview

## Slide 15: Weekly Report Areas / Progress
Progress Overview

## Slide 16: Weekly Report Areas / Milestones
Construction Milestones

## Slide 17: Weekly Report Areas / Shop Drawings
Shop Drawings

## Slide 18: Weekly Report Areas / Material Approval
Material Approval

## Slide 19: Weekly Report Areas / Quality Reports
Quality Reports

## Slide 20: Weekly Report Areas / Invoices Summary
Invoices Summary

## Slide 21: Weekly Report Areas / Quality
Quality Audit

## Slide 22: Weekly Report Areas / HSE
Health, Safety & Environmental (HSE)

## Slide 23: Weekly Report Areas / HSE
Health, Safety & Environmental (HSE) Audits

## Slide 24: Weekly Report Areas / Invoices
Invoice Log

## Slide 25: Weekly Report Areas / Invoices
Invoice Summary

## Slide 26: Weekly Report Areas / CCOs
Contract Change Orders (CCOs)

## Slide 27: Weekly Report Areas / Resources
Resources

## Slide 28: Weekly Report Areas / Schedule Status
Primavera P6 Schedule Status

## Slide 29: Weekly Report Areas / Testing and Commissioning
Testing And Commissioning

## Slide 30: Weekly Report Areas / Issues
Active Issues

## Slide 31: شكراً