## DB (hidden)
MODON - Weekly Progress Report - Construction Projects
| Contract General Information | [7 empty] | Key Dates | [10 empty] | Cost Summary (SR) | [8 empty] | Performance Summary | [11 empty] | Shop Drawings |  |  |  | Material Approval |  |  | Procurement Summary | [6 empty] | Quality Reports | [15 empty] | Key Submittals Approval Status | [9 empty] | Invoices Summary | [13 empty] | Resources at Site | [6 empty] | Safety Statistics | [63 empty] | Primavera P6 Schedule Status | [7 empty] | Weekly Prgoress Photos
Data Date | Project Name | Project ID | Contractor | Consultant | Stage | Status | Modon PM | Project Scope | Contract Award | Contract Sign | Site Handover | Original Completion | Contract Award (Hijri) | Contract Sign (Hijri) | Site Handover (Hijri) | Original Completion (Hijri) | Revised Completion | Committed Completion | Forecast Completion | Original Contract Value | Revised Contract Value | Estimate At Completion Value | Potential Changes | O&M Value (if any) | Submitted Invoices (Gross Value) | Penalities | FIR Value (Todate) | Original Plan Value | Plan Value | Earn Value | Phys. Plan Value | Phys. Earn Value | Quality Score | Safety Score | Weekly PV (SAR) | Weekly EV (SAR) | Weekly PV % | Weekly PV % | Weekly Phys PV% | Weekly Phys PV% | Total SD Planned | SD Remaining | SD Pending | Total SD Submittals | Planned Materials Approv | Material Pending Approval | Materila Total Submittals | Total Materials | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Material on Site | Remaining Materials | Material Delivery Completion (Date) | NCR Issued | NCR Closed | NCR Pending | NCR Avg. Closing (Days) | SIR Issued | SIR Closed | SIR Pending | SIR Avg. Closing (Days) | MIR Issued | MIR Closed | MIR Pending | MIR Avg. Closing (Days) | FIR Issued | FIR Closed | FIR Pending | FIR Avg. Closing (Days) | 1 Quality Plan Approval | 2 Quality Plan Last Up | 3 Safety Plan Approval | 4 Safety Plan Last Up | 5 Construction Plan Approval | 6 Baseline Approval | 7 No of Approved Version of Schedule | 8 Last Approved Schedule | 9 BOQ Approval Date | 10 No of Approved Version of BOQ | Total Submitted Invoices | PM Approved Invoices | No of Paid Invoices | No of Pending Invoices | Advance Payment % | Retention % | Deduction / Penalties % | Submitted Invoices (SAR) | PM Approved Invoices (SAR) | Paid Invoices (SAR) | Last Submitted Period | Advance Payment (SAR) | Retention (SAR) | Deduction / Penalties (SAR) | Planned Head Count | Actual Head Count | Saudi Staff | Labor Planned | Labor Actual | Equipment Planned | Equipment Actual | This Week Total Hours Worked | This Week Safe Hours Worked | This Week LTI | This Week MTC (Healed w/o Disability) | This Week MTC (Healed w/ Disability) | This Week Near Miss | This Week First Aid Cases | This Week Fatality | This Week Fire Incident Cases | This Week Vehicle Incident | This Week Property Damages | This Week Induction Training | This Week No.of Internal Training | This Week No.of Internal Audit | This Week No. of Toolbox Talks | This Week Safety Awards/Incentives | This Month Total Hours Worked | This Month Safe Hours Worked | This Month LTI | This Month MTC (Healed w/o Disability) | This Month MTC (Healed w/ Disability) | This Month Near Miss | This Month First Aid Cases | This Month Fatality | This Month Fire Incident Cases | This Month Vehicle Incident | This Month Property Damages | This Month Induction Training | This Month No.of Internal Training | This Month No.of Internal Audit | This Month No. of Toolbox Talks | This Month Safety Awards/Incentives | YTD Total Hours Worked | YTD Safe Hours Worked | YTD LTI | YTD MTC (Healed w/o Disability) | YTD MTC (Healed w/ Disability) | YTD Near Miss | YTD First Aid Cases | YTD Fatality | YTD Fire Incident Cases | YTD Vehicle Incident | YTD Property Damages | YTD Induction Training | YTD No.of Internal Training | YTD No.of Internal Audit | YTD No. of Toolbox Talks | YTD Safety Awards/Incentives | Cum Total Hours Worked | Cum Safe Hours Worked | Cum LTI | Cum MTC (Healed w/o Disability) | Cum MTC (Healed w/ Disability) | Cum Near Miss | Cum First Aid Cases | Cum Fatality | Cum Fire Incident Cases | Cum Vehicle Incident | Cum Property Damages | Cum Induction Training | Cum No.of Internal Training | Cum No.of Internal Audit | Cum No. of Toolbox Talks | Cum Safety Awards/Incentives | Total Act. | Not Started | In Progress | Completed | Critical Path Act.Last Week | Critical Path Act.This Week | Failed start Last Week | Failed start This Week | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2024-07-30 | Hail - Developing of Infrastructure Hail industrial city PHASE II - Eastern side Project | HAL1-02-005 | Shibh Aljazira Contracting Company | JASARA Program Managemant Company | Construction | Active | Abdulaziz M. Al-Musallam | The project consists of the POND A which works as a downstream for the storm water wet utility piping network including manholes and catch basins, continued project wet utilities also sewerage GRP piping network with manholes, potable water and firefighting compound HDPE piping network including the installation of valves and fire hydrants and the irrigation water (TSE) network with all valves and the flow meter, dry utility represented in electrical road lighting network - the installation of poles and the LV cables which is connected to the panel board and the 13.8/0.4 K V unit substation. | 2023-09-17 | 2023-12-20 | 2024-01-07 | 2026-01-06 | 2023-09-17 | 2023-12-20 | 2024-01-07 | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-29 | 45093675 | 45093675 | 45093675 | 0 | 0 | 5707774.55 | -579777.455 | 450291.6 | 16.84% | 16.84% | 32.29% | 18.75% | 29.84% | 0.90879 | 0.875 | 480506.96 | 439683.4 | 1.066% | 0.975% | 1.096% | 1.411% | 85 | 6 | 0 | 79 | 102 | 1 | 39 | 31 | 28 | 5 | 23 | 4 | 27 | 2024-08-29 | 3 | 3 | 0 | 0 | 3 | 3 | 0 | 0 | 30 | 29 | 1 | 0 | 489 | 460 | 29 | 0 | 2024-02-24 | 2024-02-24 | 2024-02-28 | 2024-02-28 | 2024-02-26 | 2024-03-10 | 1 | 2024-03-10 | 0 | 1 | 4 | 0 | 0 | 0 | 0.1 | 0 | 0.00019958 | 5707774.55 | 0 | 0 | 2024-06-30 | 4509367.5 | 0 | -9000 | 30 | 26 | 4 | 86 | 90 | 37 | 45 | 5568 | 5568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1(50) | 0 | 26288 | 26288 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 22(28) | 1 (4) | 0 | 3(122) | 0 | 86904 | 86904 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 43(106) | 8(56) | 3 | 17(592) | 4 | 86904 | 86904 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 43(106) | 8(56) | 3 | 17(592) | 4 | 1116 | 750 | 167 | 199 | 170 | 149 | 27 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0

## Sheet3 (hidden)
MODON - Weekly Progress Report - Construction Projects
Contract General Information
Data Date | Project Name | Project ID | Contractor | Consultant | Stage | Status | Modon PM | Project Scope | Contract Award | Contract Sign | Site Handover | Original Completion | Contract Award (Hijri) | Contract Sign (Hijri) | Site Handover (Hijri) | Original Completion (Hijri) | Revised Completion | Committed Completion | Forecast Completion | Original Contract Value | Revised Contract Value | Estimate At Completion Value | Potential Changes | O&M Value (if any) | Submitted Invoices (Gross Value) | Penalities | FIR Value (Todate) | Original Plan Value | Plan Value | Earn Value | Phys. Plan Value | Phys. Earn Value | Quality Score | Safety Score | Weekly PV (SAR) | Weekly EV (SAR) | Weekly PV % | Weekly PV % | Weekly Phys PV% | Weekly Phys PV% | Total SD Planned | SD Remaining | SD Pending | Total SD Submittals | Planned Materials Approv | Material Pending Approval | Materila Total Submittals | Total Materials | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Material on Site | Remaining Materials | Material Delivery Completion (Date) | NCR Issued | NCR Closed | NCR Pending | NCR Avg. Closing (Days) | SIR Issued | SIR Closed | SIR Pending | SIR Avg. Closing (Days) | MIR Issued | MIR Closed | MIR Pending | MIR Avg. Closing (Days) | FIR Issued | FIR Closed | FIR Pending | FIR Avg. Closing (Days) | 1 Quality Plan Approval | 2 Quality Plan Last Up | 3 Safety Plan Approval | 4 Safety Plan Last Up | 5 Construction Plan Approval | 6 Baseline Approval | 7 No of Approved Version of Schedule | 8 Last Approved Schedule | 9 BOQ Approval Date | 10 No of Approved Version of BOQ | Total Submitted Invoices | PM Approved Invoices | No of Paid Invoices | No of Pending Invoices | Advance Payment % | Retention % | Deduction / Penalties % | Submitted Invoices (SAR) | PM Approved Invoices (SAR) | Paid Invoices (SAR) | Last Submitted Period | Advance Payment (SAR) | Retention (SAR) | Deduction / Penalties (SAR) | Planned Head Count | Actual Head Count | Saudi Staff | Labor Planned | Labor Actual | Equipment Planned | Equipment Actual | This Week Total Hours Worked | This Week Safe Hours Worked | This Week LTI | This Week MTC (Healed w/o Disability) | This Week MTC (Healed w/ Disability) | This Week Near Miss | This Week First Aid Cases | This Week Fatality | This Week Fire Incident Cases | This Week Vehicle Incident | This Week Property Damages | This Week Induction Training | This Week No.of Internal Training | This Week No.of Internal Audit | This Week No. of Toolbox Talks | This Week Safety Awards/Incentives | This Month Total Hours Worked | This Month Safe Hours Worked | This Month LTI | This Month MTC (Healed w/o Disability) | This Month MTC (Healed w/ Disability) | This Month Near Miss | This Month First Aid Cases | This Month Fatality | This Month Fire Incident Cases | This Month Vehicle Incident | This Month Property Damages | This Month Induction Training | This Month No.of Internal Training | This Month No.of Internal Audit | This Month No. of Toolbox Talks | This Month Safety Awards/Incentives | YTD Total Hours Worked | YTD Safe Hours Worked | YTD LTI | YTD MTC (Healed w/o Disability) | YTD MTC (Healed w/ Disability) | YTD Near Miss | YTD First Aid Cases | YTD Fatality | YTD Fire Incident Cases | YTD Vehicle Incident | YTD Property Damages | YTD Induction Training | YTD No.of Internal Training | YTD No.of Internal Audit | YTD No. of Toolbox Talks | YTD Safety Awards/Incentives | Cum Total Hours Worked | Cum Safe Hours Worked | Cum LTI | Cum MTC (Healed w/o Disability) | Cum MTC (Healed w/ Disability) | Cum Near Miss | Cum First Aid Cases | Cum Fatality | Cum Fire Incident Cases | Cum Vehicle Incident | Cum Property Damages | Cum Induction Training | Cum No.of Internal Training | Cum No.of Internal Audit | Cum No. of Toolbox Talks | Cum Safety Awards/Incentives | Total Act. | Not Started | In Progress | Completed | Critical Path Act.Last Week | Critical Path Act.This Week | Failed start Last Week | Failed start This Week | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-18 | Playgrounds Initiative - Qassim, Hail & Tabuk | MLTX-02-003 | Advanced Construction & Contracting Company | Egis | Construction | Active | Bader Alrowaidan | Construction of Playgrounds Initiatives at 03 Location(Qassim, Hail, Tabuk). The project includes civil, architectural, electrical, mechanical and landscape works, as well as general site works, according to the plans and technical specifications. | 2026-01-06 | 2026-02-17 | 2026-02-17 | 2026-12-16 | 2026-01-06 | 2026-02-17 | 2026-02-17 | 2026-12-16 | 2026-12-16 | 2026-12-16 | 2027-02-07 | 35709993 | 35709993 | 35709993 | 0 | 0 | 2317493.31 | -250749.331 | 3298582.8807 | 80.32% | 80.32% | 69% | 80.25% | 74.79% | 91.31% | 91.3% | 28512896.32 | 24528612.98 | 79.85% | 68.69% | 71.95% | 66.95% | 393 | 0 | 44 | 393 | 141 | 12 | 141 | 57 | 57 | 33 | 25 | 8 | 0 |  | 3 | 3 | 0 | 0 | 3 | 3 | 0 | 0 | 30 | 29 | 1 | 0 | 489 | 460 | 29 | 0 | 2024-02-24 | 2024-02-24 | 2024-02-28 | 2024-02-28 | 2024-02-26 | 2024-03-10 | 1 | 2024-03-10 | 0 | 1 | 4 | 0 | 0 | 0 | 0.1 | 0 | 0.00019958 | 5707774.55 | 0 | 0 | 2024-06-30 | 4509367.5 | 0 | -9000 | 30 | 26 | 4 | 86 | 90 | 37 | 45 | 5568 | 5568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1(50) | 0 | 26288 | 26288 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 22(28) | 1 (4) | 0 | 3(122) | 0 | 86904 | 86904 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 43(106) | 8(56) | 3 | 17(592) | 4 | 86904 | 86904 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 43(106) | 8(56) | 3 | 17(592) | 4 | 1116 | 750 | 167 | 199 | 170 | 149 | 27 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0

## Weekly Progress Report
MODON - Weekly Progress Report - Construction Projects | [30 empty] | Data Date | 2026-10-18
Contract General Information | [5 empty] | Key Dates | [5 empty] | Cost Summary (SR) | [7 empty] | Performance Summary | [5 empty] | Project Scope
Project Name | Playgrounds Initiative - Qassim, Hail & Tabuk |  |  |  |  | Contract Award | 2026-01-06 | Contract Award (Hijri) | 2026-01-06 | Revised Completion | 2026-12-16 | Original Contract Value |  | 35709993 |  | O&M Value (if any) |  | 0 | EAC | Plan Value | 80.32% | Phys. Plan Value | 80.25% | Quality Score | 91.31% | Construction of Playgrounds Initiatives at 03 Location(Qassim, Hail, Tabuk). The project includes civil, architectural, electrical, mechanical and landscape works, as well as general site works, according to the plans and technical specifications.
Project ID | MLTX-02-003 |  | Stage | Construction |  | Contract Sign | 2026-02-17 | Contract Sign (Hijri) | 2026-02-17 | Committed Completion | 2026-12-16 | Revised Contract Value |  | 35709993 |  | Submitted Invoices (Gross Value) |  | 2317493.31 | EAC | Earn Value | 69% | Phys. Earn Value | 74.79% |  | ¢¢¢¢¢ ¢¢¢¢£
Contractor | Advanced Construction & Contracting Company |  | Status | Active |  | Site Handover | 2026-02-17 | Site Handover (Hijri) | 2026-02-17 | Forecast Completion | 2027-02-07 | Estimate At Completion Value |  | 35709993 |  | Penalities |  | -250749.331 | EAC | Variance | -11.32% | Variance | -5.459% | Safety Score | 91.3%
Consultant | Egis |  | Modon PM | Bader Alrowaidan |  | Original Completion | 2026-12-16 | Original Completion (Hijri) | 2026-12-16 | Variance | -53 | Potential Changes |  | 0 |  | FIR Value (Todate) |  | 3298582.8807 |  | FIR % | 9.237% | Invoiced % | 6.49% |  | ¢¢¢¢¢ ¢¢¢¢£
Progress Overview
Earned Value Progress (SAR) | [13 empty] | Physical Progress (Effort) | [11 empty] | Earned Value Progress (%)
WBS |  | BOQ Value (SAR) | % Wt. | Weekly (SAR) |  | To Date (SAR) | [7 empty] | Budgeted | % Wt. | Weekly Physical Progress |  |  |  | To Date Physical Progress
|  |  |  | Planned | Earned | Original Plan | Revised Planned | Earned | Original Plan % | Revised Planned % | Earned % | Variance | SPI | (Manhours) |  | Planned | Earned | Plan % | Earned % | Planned | Earned | Plan % | Earned % | Variance | SPI
PROJECT MILESTONE |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 10000 | 29.99% | 227 | 885 | 2.27% | 8.85% | 7927 | 7935 | 79.27% | 79.35% | 0.08% | 1.001
MOBILIZATION |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | 0% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
ENGINEERING |  | 1071299.79 | 3% | 1090347.18 | 1090347.18 | 1071299.79 | 1071299.79 | 1071299.79 | 100% | 100% | 100% | 0% | 1 | 0 | 0% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
PROCUREMENT |  | 9641698.11 | 27% | 9813124.62 | 8945474.82 | 9641698.11 | 9641698.11 | 8769229.7 | 100% | 100% | 90.95% | -9.049% | 0.90951 | 0 | 0% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
CONSTRUCTION |  | 21425995.8 | 60% | 17500389.8 | 13921267.06 | 17861236.65 | 17861236.65 | 14189804.91 | 83.36% | 83.36% | 66.23% | -17.14% | 0.79445 | 22188 | 66.55% | 23717 | 21229 | 106.9% | 95.68% | 18795 | 16835 | 84.71% | 75.87% | -8.834% | 0.89572
CLOSEOUT |  | 3570999.3 | 10% | 109034.72 | 571523.92 | 107129.98 | 107129.98 | 610206.45 | 3% | 3% | 17.09% | 14.09% | 5.6959 | 1152 | 3.455% | 44 | 206 | 3.819% | 17.88% | 33 | 165 | 2.865% | 14.32% | 11.46% | 5
| Total | 35709993 | 100% | 28512896.32 | 24528612.98 | 28681364.53 | 28681364.53 | 24640540.85 | 80.32% | 80.32% | 69% | -11.32% | 0.85911 | 33340 | 100% | 23988 | 22320 | 71.95% | 66.95% | 26755 | 24935 | 80.25% | 74.79% | -5.459% | 0.93198
Construction Milestones
[26 empty] | Item No. | Milestones |  | Original (Baseline) | Latest Plan | Forecast | Status | Days Change
[26 empty] | 1 | Award Date |  | 2026-01-06 | 2026-01-06 | 2026-01-06 | A | 0
[26 empty] | 2 | Contract Sign Date |  | 2026-02-17 | 2026-02-17 | 2026-02-17 | A | 0
[26 empty] | 3 | Site Handover Date |  | 2026-02-17 | 2026-02-17 | 2026-02-17 | A | 0
[26 empty] | 4 | Complete Mobilization |  | 2026-03-18 | 2026-03-18 | 2026-04-14 | A | 0
[26 empty] | 7 | Complete Construction |  | 2026-12-14 | 2026-12-14 | 2027-01-23 | F | -40
[26 empty] | 8 | Complete all Works including Testing & Commissioning, Cleanup, Closeout Documentation and Ready for Initial Handover |  | 2026-12-16 | 2026-12-16 | 2027-02-02 | F | -48
[26 empty] | 9 | Complete Demobilization |  | 2026-12-16 | 2026-12-16 | 2027-02-06 | F | -52
[26 empty] | 10 | Project Handover |  | 2026-12-16 | 2026-12-16 | 2027-02-07 | F | -53
Performance overview
Submittals Status | [10 empty] | Quality | [10 empty] | Safety
Shop Drawings | [10 empty] | Quality Reports | [10 empty] | Safety Statistics | [7 empty] | Proactive Vs Reactive Actions Taken
Item Per WBS |  | Total | Total Submitted Drawings |  |  |  |  | Remaining | Pending | Total Submittals | Quality Reports |  | Issued | Closed | Pending | Avg. Closing (Days) | Pending |  |  |  |  | Category | Item |  | This Week |  | This Month | Year to Date | Cumulative
|  |  | A | B | C | D | Processed | [9 empty] | 0-10 Days | 11-20 Days | 21-30 Days | 31-60 Days | > 60 Days
Architectural |  | 58 | 6 | 33 | 2 |  | 39 |  | 17 | 58 | [11 empty] | General | Total Hours Worked |  | 8160 |  | 15240 | 97870 | 97870 |  |  | Proactive | 531
Civil / Structural |  | 84 |  | 66 |  | 12 | 66 |  | 6 | 84 | Non Conformance (NCR) |  | 17 | 7 | 10 |  | 8 | 2 |  |  |  |  | Safe Hours Worked |  | 8160 |  | 15240 | 97870 | 97870 |  |  | Reactive | 212
Mechanical |  | 42 | 16 | 22 | 2 |  | 38 |  | 2 | 42 | Site Instruction (SIR) |  | 7 | 6 | 1 |  |  |  | 1 |  |  | Reactive | LTI |  | 0 |  | 0 | 0 | 0
Electrical |  | 98 | 4 | 43 | 12 | 22 | 47 |  | 17 | 98 | Material Inspection (MIR) |  | 76 | 53 | 23 |  | 20 | 3 |  |  |  |  | MTC (Healed w/o Disability) |  | 0 |  | 0 | 0 | 0
Landscape |  | 69 | 4 | 59 | 1 | 3 | 63 |  | 2 | 69 | Field Inspection (FIR) |  | 658 | 488 | 170 |  | 140 | 15 | 15 |  |  |  | MTC (Healed w/ Disability) |  | 0 |  | 0 | 0 | 0
General |  | 42 | 6 | 36 |  |  | 42 |  |  | 42 | TOTAL |  | 758 | 554 | 204 |  | 168 | 20 | 16 | 0 |  |  | Near Miss |  | 0 |  | 0 | 0 | 0
TOTAL |  | 393 | 36 | 259 | 17 | 37 | 295 | 0 | 44 | 393 | Key Submittals Approval Status | [11 empty] | First Aid Cases |  | 0 |  | 0 | 0 | 0
Material Approval | [10 empty] | 1 Quality Plan Approval |  |  | 0 |  | 6 Baseline Approval |  |  |  | 2026-03-05 |  |  | Fatality |  | 0 |  | 0 | 0 | 0 | Total Hours Worked Vs Safe Hours Worked
Item Per WBS |  | Total | Total Submitted Material |  |  |  |  | Remaining to approve | Pending | Total Submittals | 2 Quality Plan Last Up |  |  | 2026-03-12 |  | 7 No of Approved Version of Schedule |  |  |  | 2 |  |  | Fire Incident Cases |  | 0 |  | 0 | 0 | 0
|  |  | A | B | C | D | Processed | with Designer |  |  | 3 Safety Plan Approval |  |  | 0 |  | 8 Last Approved Schedule |  |  |  | 2026-07-08 |  |  | Vehicle Incident |  | 0 |  | 0 | 0 | 0
Architectural |  | 41 | 4 | 35 | 1 |  | 39 |  | 1 | 41 | 4 Safety Plan Last Up |  |  | 0 |  | 9 BOQ Approval Date | [6 empty] | Property Damages |  | 0 |  | 0 | 0 | 0
Civil / Structural |  | 51 | 1 | 41 | 4 |  | 42 |  | 5 | 51 | 5 Construction Plan Approval |  |  |  |  | 10 No of Approved Version of BOQ | [5 empty] | Proactive | Induction Training |  | 40 |  | 63 | 212 | 212
Mechanical |  | 19 |  | 14 | 1 |  | 14 |  | 4 | 19 | Invoices Summary | [11 empty] | No.of Internal Training |  | 0 |  | 1 | 1 | 1
Electrical |  | 28 |  | 26 | 2 |  | 26 |  |  | 28 | Total Submitted Invoices |  | 0 | Submitted Invoices (SAR) |  |  | 2317493.31 |  | Contract Value (SR) | 35709993 |  |  | No.of Internal Audit |  | 0 |  | 0 | 0 | 0
Landscape |  | 2 | [6 empty] | 2 | 2 | PM Approved Invoices |  | 0 | PM Approved Invoices (SAR) |  |  | 0 |  | Planned Value (SR) | 28681364.53 |  |  | No. of Toolbox Talks |  | 46 |  | 87 | 530 | 530
General | [22 empty] | Safety Awards/Incentives |  | 0 |  | 0 | 0 | 0
TOTAL |  | 141 | 5 | 116 | 8 | 0 | 121 | 0 | 12 | 141 | No of Paid Invoices |  | 0 | Paid Invoices (SAR) |  |  | 2379605.58 |  | Earned Value (SR) | 24640540.85
Procurement Summary | [10 empty] | No of Pending Invoices |  | 0 | Last Submitted Period |  |  | 29/09/2026 |  | Submitted (SAR) | 2317493.31
Item Per WBS |  | Total Materials | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Material on Site | Remaining Materials | Material Delivery Completion (Date) |  |  | Advance Payment % |  | 0% | Advance Payment (SAR) |  |  | 0 |  | PM Approved (SAR) | 0 |  | Latest Contract Change Order Log
|  |  | A | B | C | D | Processed |  |  |  | Retention % |  | 0% | Retention (SAR) |  |  | 0 |  | Total Paid (SAR) | 2379605.58
Architectural |  | 11 | 11 | 7 | 4 | 3 |  |  |  |  | Deduction / Penalties % |  | 0.05321% | Deduction / Penalties (SAR) |  |  | -19000 |  |  |  |  | CCO No. | Date Added | Description of Change |  |  |  |  | Status | Cost | Sch Impact (Months) | Date Approved | Duration
Civil / Structural |  | 19 | 19 | 15 | 4 | 3 |  |  |  |  | Resources at Site
Mechanical |  | 20 | 20 | 8 | 13 | 1 |  |  |  |  | Head Count - Non Manual |  |  |  | Head Count - Manual |  |  |  | Total Head Count
Electrical |  | 7 | 7 | 3 | 4 | 1 |  |  |  |  | Planned | Actual | Next Month Forecast | Saudi Staff | Planned | Actual | Next Month Forecast | Saudi Staff | Total Plan | Total Actual | Variance
General | [10 empty] | 8 | 16 | 8 | 2 | 32 | 77 | 20 | 0 | 40 | 93 | 53
TOTAL |  | 57 | 57 | 33 | 25 | 8 | 0 |  |  |  | Manpower Breakdown by Trade | [6 empty] | Major Equipment
Primavera P6 Schedule Status | [10 empty] | Key Trade | Planned | Actual |  |  |  |  | Type | Planned | Actual | Idle
Project Activities Overview | [10 empty] | Site Engineer | 1 | 3 |  |  |  |  | Spray Machine | 1 | -
Schedule Statistics |  |  |  |  | Active Schedule Activities | [5 empty] | Mason | 1 | 4 |  |  |  |  | Excavator | 1 | 2 |  | Major Quantity Trackers
Total Act. | Not Started | In Progress | Completed | % | Active | Ahead | On | Behind | Flag | 0 | Labor / Helper | 8 | 16 |  |  |  |  | Paving Machine | 1 | - |  | BOQ N0. | Item Description |  |  |  |  | Total Qty | Measu Unit | Plan to Date | Act to Date | Remaining | Variance
1929 | 86 | 223 | 1620 | 83.98% | 223 | 43 | 51 | 215 | -121 |  | Plumber | 1 | 4 |  |  |  |  | Crane | 1 | - |  | 2.1.1 | Excavation |  |  |  |  | 29400 | m3 | 29400 | 29400 | 0 | 0
Critical Path Activities |  |  | Free Float Management (Total) |  |  |  | Failed Start Activities |  |  |  | Electrician | 2 | 4 |  |  |  |  | Dump Truck | 1 | 2 |  | 2.1.2 | Backfilling with selected fill material |  |  |  |  | 29400 | m3 | 29400 | 29400 | 0 | 0
|  |  | Greater Than 14 Days |  | Less Than 14 Days | [5 empty] | HVAC Technician | 1 | - |  |  |  |  | Compactor | - | 2 |  | 2.2.1 | Interlock Tiles for parking |  |  |  |  | 7140 | m² | 5901.21 | 6640.2 | 499.8 | 738.99
Last Week | This Week | Diff | Last Week | This Week | Last Week | This Week | Last Week | This Week | Flag | 0 | Tile Fixer | 1 | 2 |  |  |  |  | Roller Compactor | - | 2 |  | 2.3.1.2 | Stamped Concrete Floor |  |  |  |  | 7800 | m² | 7033.26 | 6630 | 1170 | -403.26
205 | 174 | 31 | 54 | 39 | 284 | 270 | 77 | 42 | 35 |  | Applicator | 2 | - |  |  |  |  | Grader | - | 1 |  | 2.3.1.3 | Tartan Floor |  |  |  |  | 10950 | m² | 9920.7 | 8000 | 2950 | -1920.7
[11 empty] | ELV Technician | 2 | - |  |  |  |  | Boom Truck | - | 1 |  | 2.3.1.4 | Compacted Natural Ground Soil |  |  |  |  | 33300 | m² | 33300 | 33300 | 0 | 0
[11 empty] | Facade Technician | 1 | - |  |  |  |  | Pickup Car | - | 3 |  | 2.3.2.3 | Kerb type K4 |  |  |  |  | 27100 | L.m | 27100 | 27100 | 0 | 0
[11 empty] | Crane Operator | 1 | - |  |  |  |  | Wheel Loader | - | 2 |  | 2.3.4.2.1 | Lawn |  |  |  |  | 19100 | m² | 12539.15 | 0 | 19100 | -12539.15
[11 empty] | Mechanical Technician | 1 | - |  |  |  |  | Water Tanker | - | 1 |  | 2.3.5.1 | Football Playground |  |  |  |  | 7350 | m² | 7350 | 4400 | 2950 | -2950
[11 empty] | Painter | 1 | - |  |  |  |  | Forklift | - | 2 |  | 15.5.1.5 | Pipe line O.D 25mm PN 10, in depth 0 to 1.5m |  |  |  |  | 11100 | m | 10545 | 1811.52 | 9288.48 | -8733.48
[11 empty] | Surveyor | 1 | 1 |  |  |  |  | Backhoe | - | 2
[11 empty] | Glass Installer | 1 | - |  |  |  |  | Total | 5 | 20
[11 empty] | Excavator Operator | 1 | 2
[11 empty] | Dump Truck Driver | 1 | 2
[11 empty] | Safety Officer | 1 | 3
[11 empty] | Paving Machine Operator | 1 | -
[11 empty] | Concrete Mason | 1 | -
[11 empty] | Carpenter | 1 | 2
[11 empty] | Gardener | 1 | -
[11 empty] | Backhoe Operator | - | 2
[11 empty] | Wheel loader Operator | - | 2
[11 empty] | Store keeper | - | 2
[11 empty] | Security Guard | - | 3
[11 empty] | Boom Truck Operator | - | 1
[11 empty] | Foreman | - | 4
[11 empty] | Pickup Driver | - | 3
[11 empty] | Steel Fixer | - | 3
[11 empty] | Curbstone Installer | - | 8
[11 empty] | Compactor Operator | - | 2
[11 empty] | Roller Compactor Operator | - | 2
[11 empty] | Forklift Operator | - | 2
[11 empty] | Total | 32 | 77
Weekly Prgoress Photos | [15 empty] | Top Issues and Risks
Excavation, Bitumen Coat, Concrete Pouring, Base Course Installation, Asphalt Work, Curbstone Installation, Compaction & Levelling | [15 empty] | Top 5 Issues
[16 empty] | Issue No | Date Identified | Issue Description |  |  |  | Responsible | Action Taken |  |  | Mitigation |  |  |  |  | Current Status | Expected/Actual Closure | Duration Elapsed
[16 empty] | 1 | 2026-04-11 | Delay in starting work at Hail site project due to not getting the aoorved work permit |  |  |  | Other | Submit request to BALADI Platform for approval the work permit request | [7 empty] | Closed | 2026-04-19
2
3
4
5
-

## Codes (hidden)
Status List
| Approved |  | Y
| Pending |  | N | [5 empty] | (Manhours)
| Potential | [7 empty] | (Mandays)
| Phase | Stage |  | Stage |  | Status |  | Score
[8 empty] | Low | Contractor | Active
| Launch | LOA |  | LOA |  | Active |  | Medium | CM | Expired
| Launch | Kick-off Meeting |  | Kick-off Meeting |  | On Hold |  | High | PgM | Occurred
| Launch | Site Handover |  |  |  | Terminated |  |  | Modon | Pending
| Launch | Mobilization |  | Mobilization | Initial staff and equipment in place, ready to start production | Terminated, Closed |  |  | Other
| Execution | Construction |  | Execution | Tender Documents Issued | Substantial Complete | Initial Handover done at site
| Execution | T&C |  |  | Responses to the OCS completed | Complete | Initial Handover Signed
| Execution | Initial Handover |  | Closeout | Design close-out process complete | Closed | Final Handover done at Site
Warranty Period
Final Handover
#DIV/0!
Project Status Score
Elements |  |  | Max | Score | Planned | Actual | Remarks
SPI (Physical Effort) |  |  | 100% | 93.2% | No Entry Required
SPI (Cost) |  |  | 100% | 85.91% | No Entry Required
On Schedule -Active |  |  | 100% | 42.15% | No Entry Required |  |  |  | 0.6
Manpower Availability |  |  | 100% | 100% | No Entry Required
Major Equipment Availability |  |  | 100% | 400% | No Entry Required
Billing % Compared to Planned |  |  | 100% | 102.7% | No Entry Required
Safety Score |  |  | 100% | 91.3% | No Entry Required
Quality Score |  |  | 100% | 91.31% | No Entry Required

## General Information
Weekly Progress Report - Construction Projects |  |  | Data Date | 2026-10-18
Contract General Information
Project Name | Playgrounds Initiative - Qassim, Hail & Tabuk
Project ID | MLTX-02-003
Contractor | Advanced Construction & Contracting Company
Consultant | Egis
Stage | Construction
Status | Active
Modon PM | Bader Alrowaidan
Key Dates
Contract Award Date | 2026-01-06
Contract Sign Date | 2026-02-17
Site Handover Date | 2026-02-17
Original Completion | 2026-12-16
Contract Award Date (Hijri) | 2026-01-06
Contract Sign Date (Hijri) | 2026-02-17
Site Handover Date (Hijri) | 2026-02-17
Original Completion (Hijri) | 2026-12-16
Revised Completion Date | 2026-12-16
Committed Completion Date | 2026-12-16
Forecast Completion | 2027-02-07
Variance | -53
Key Project Submittals | Submission Date | Days taken to approve orginal plan from site handover date
Quality Plan submission | 2026-02-17 | 0
Quality Plan approval
Quality Plan Last Update | 2026-03-12
Safety Plan submission | 2026-02-17 | 0
Safety Plan approval
Safety Plan Last Update
Risk Management Plan submission | 2026-02-17 | 0
Risk Management Plan approval
Risk Management Plan Last Update
Baseline Schedule submission | 2026-02-28 | 11
Baseline Schedule approval | 2026-03-05
No of Schedule Versions | 2
Last Recovery Schedule Approval Date | 2026-07-08
BOQ submission | 2026-02-17 | 0
BOQ approval
No of Approved Version of BOQ
Construction Plan submission | 2026-02-17 | 0
Construction Plan Approval
Note on E25: AlNuaim, Abdulaziz: As per contract requirments submission of Plans should be 30 days after site handover

## Progress
Project Scope | Construction of Playgrounds Initiatives at 03 Location(Qassim, Hail, Tabuk). The project includes civil, architectural, electrical, mechanical and landscape works, as well as general site works, according to the plans and technical specifications.
Work Progress (SAR) | [7 empty] | Manpower Status
WBS | BOQ Value (SAR) | % Wt. | Weekly Progress |  |  | To Date Progress |  | Budgeted Manhours | % Wt. | Weekly Manhours |  | To Date Manhours
|  |  | Planned | Earned | Original Plan | Planned | Earned | Budgeted Manhours | % Wt. | Planned | Earned | Planned | Earned
PROJECT MILESTONE | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 10000 | 29.99% | 227 | 885 | 7927 | 7935
MOBILIZATION | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0
ENGINEERING | 1071299.79 | 3% | 1090347.18 | 1090347.18 | 1071299.79 | 1071299.79 | 1071299.79 | 0 | 0% | 0 | 0 | 0 | 0
QASSIM | 526126.2 | 1.473% | 0 | 0 | 526126.2 | 526126.2 | 526126.2 | 0 | 0% | 0 | 0 | 0 | 0
SHOP DRAWINGS SUBMITTAL | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0
MATERIAL SUBMITTAL | 526126.2 | 1.473% | 0 | 0 | 526126.2 | 526126.2 | 526126.2 | 0 | 0% | 0 | 0 | 0 | 0
HAIL | 204439.56 | 0.5725% | 0 | 0 | 204439.56 | 204439.56 | 204439.56 | 0 |  | 0 | 0 | 0 | 0
SHOP DRAWINGS SUBMITTAL | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0
MATERIAL SUBMITTAL | 204439.56 | 0.5725% | 0 | 0 | 204439.56 | 204439.56 | 204439.56 | 0 | 0% | 0 | 0 | 0 | 0
TABUK | 340734.03 | 0.9542% | 0 | 0 | 340734.03 | 340734.03 | 340734.03 | 0 |  | 0 | 0 | 0 | 0
SHOP DRAWINGS SUBMITTAL | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0
MATERIAL SUBMITTAL | 340734.03 | 0.9542% | 0 | 0 | 340734.03 | 340734.03 | 340734.03 | 0 | 0% | 0 | 0 | 0 | 0
PROCUREMENT | 9641698.11 | 27% | 9813124.62 | 8945474.82 | 9641698.11 | 9641698.11 | 8769229.7 | 0 | 0% | 0 | 0 | 0 | 0
QASSIM | 4735135.8 | 13.26% | 0 | 393630.22 | 4735135.8 | 4735135.8 | 4290343.42 | 0 |  | 0 | 0 | 0 | 0
LONG LEAD ITEMS | 3229967.34 | 9.045% | 0 | 377836.78 | 3229967.34 | 3229967.34 | 2815918.75 | 0 | 0% | 0 | 0 | 0 | 0
SHORT LEAD ITEMS | 1505168.46 | 4.215% | 0 | 15793.44 | 1505168.46 | 1505168.46 | 1474424.67 | 0 | 0% | 0 | 0 | 0 | 0
HAIL | 1839956.04 | 5.152% | 0 | 28384.23 | 1839956.04 | 1839956.04 | 1816202.83 | 0 |  | 0 | 0 | 0 | 0
LONG LEAD ITEMS | 999589.41 | 2.799% | 0 | 19306.16 | 999589.41 | 999589.41 | 981462.29 | 0 | 0% | 0 | 0 | 0 | 0
SHORT LEAD ITEMS | 840366.63 | 2.353% | 0 | 9078.05 | 840366.63 | 840366.63 | 834740.53 | 0 | 0% | 0 | 0 | 0 | 0
TABUK | 3066606.27 | 8.588% | 0 | 377543.73 | 3066606.27 | 3066606.27 | 2662683.45 | 0 |  | 0 | 0 | 0 | 0
LONG LEAD ITEMS | 2561939.82 | 7.174% | 0 | 376757.42 | 2561939.82 | 2561939.82 | 2161684.91 | 0 | 0% | 0 | 0 | 0 | 0
SHORT LEAD ITEMS | 504666.45 | 1.413% | 0 | 786.32 | 504666.45 | 504666.45 | 500998.54 | 0 | 0% | 0 | 0 | 0 | 0
CONSTRUCTION | 21425995.8 | 60% | 17500389.8 | 13921267.06 | 17861236.65 | 17861236.65 | 14189804.91 | 22188 | 66.55% | 23717 | 21229 | 18795 | 16835
QASSIM | 10522524 | 29.47% | 516953.07 | 275629.64 | 8948881.52 | 8948881.52 | 7197982.38 | 8112 | 24.33% | 409 | 467 | 6809 | 6065
PLAYGROUND AND LANDSCAPING WORK | 6019638.42 | 16.86% | 269950.21 | 269791.79 | 5378139.13 | 5378139.13 | 5433056.07 | 5288 | 15.86% | 243 | 422 | 4345 | 4048
AIR DOME CONSTRUCTION | 4178041.2 | 11.7% | 184703.48 | 0 | 3260143.02 | 3260143.02 | 1461181.68 | 1116 | 3.347% | 41 | 0 | 865 | 446
TOILET BUILDING WORKS | 324844.38 | 0.9097% | 62299.36 | 5837.86 | 310599.36 | 310599.36 | 303744.63 | 1708 | 5.123% | 124 | 45 | 1599 | 1571
HAIL | 4088791.2 | 11.45% | 335606.94 | 234285.44 | 3836982.53 | 3836982.53 | 3434319.44 | 5964 | 17.89% | 211 | 407 | 5398 | 4553
PLAYGROUND AND LANDSCAPING WORK | 3760297.62 | 10.53% | 325613.23 | 221795.36 | 3508488.95 | 3508488.95 | 3160875.18 | 4256 | 12.77% | 198 | 390 | 3690 | 3096
TOILET BUILDING WORKS | 328493.58 | 0.9199% | 9993.71 | 12490.08 | 328493.58 | 328493.58 | 273444.26 | 1708 | 5.123% | 13 | 18 | 1708 | 1458
TABUK | 6814680.6 | 19.08% | 505666.59 | 103722.2 | 5075372.6 | 5075372.6 | 3557503.09 | 8112 | 24.33% | 453 | 371 | 6588 | 6217
PLAYGROUND AND LANDSCAPING WORK | 2311795.02 | 6.474% | 91455.92 | 96732.13 | 1913311.43 | 1913311.43 | 2041669.63 | 5288 | 15.86% | 186 | 346 | 4288 | 4204
AIR DOME CONSTRUCTION | 4178041.2 | 11.7% | 307146.35 | 0 | 2880615.31 | 2880615.31 | 1210693.39 | 1116 | 3.347% | 58 | 0 | 784 | 392
TOILET BUILDING WORKS | 324844.38 | 0.9097% | 107064.32 | 6990.07 | 281445.86 | 281445.86 | 305140.07 | 1708 | 5.123% | 16 | 0 | 16 | 0
CLOSEOUT | 3570999.3 | 10% | 109034.72 | 571523.92 | 107129.98 | 107129.98 | 610206.45 | 1152 | 3.455% | 44 | 206 | 33 | 165
QASSIM | 1753754 | 4.911% | 0 | 0 | 52612.62 | 52612.62 | 324444.49 | 384 | 1.152% | 0 | 0 | 11 | 62
HAIL | 681465.2 | 1.908% | 0 | 0 | 20443.96 | 20443.96 | 75642.64 | 384 | 1.152% | 0 | 0 | 11 | 41
TABUK | 1135780.1 | 3.181% | 0 | 0 | 34073.4 | 34073.4 | 210119.32 | 0 | 0% | 0 | 0 | 11 | 62
TOTAL | 35709993 | 100% | 28512896.32 | 24528612.98 | 28681364.53 | 28681364.53 | 24640540.85 | 33340 | 100% | 23988 | 22320 | 26755 | 24935

## Current Week
Activity ID | Activity Name | BL Project Duration | BL Project Start | BL Project Finish | Actual Start | Actual Finish | Planned Value Cost | Earned Value Cost | Budgeted Total Cost | Schedule % Complete | Performance % Complete | Budgeted Labor Units | Planned Value Labor Units | Earned Value Labor Units | Critical | Activity Count | Actual Completed Activities | Actual In-Progress Activities | Actual Not-Started Activities
PLAYGROUNDS INITIATIVE - QASSIM, HAIL & TABUK - 18-Oct-2026 |  | 250 | 2026-02-17 | 2026-12-16 | 2026-02-17 |  | 28681364.53 | 24640540.86 | 35709993 | 80.32% | 69% | 33340 | 26756 | 24935 |  | 1929 | 1620 | 223 | 86
MILESTONES |  | 250 | 2026-02-17 | 2026-12-16 | 2026-02-17 |  | 0 | 0 | 0 | 0% | 0% | 10000 | 7927 | 7935 |  | 10 | 4 | 1 | 5
GENERAL MILESTONES |  | 250 | 2026-02-17 | 2026-12-16 | 2026-02-17 |  | 0 | 0 | 0 | 0% | 0% | 10000 | 7927 | 7935 |  | 4 | 2 | 1 | 1
PG-GN-MS-10 | Project Commencement Date | 0 | 2026-02-17 |  | 2026-02-17 |  | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-GN-MS-30 | Project Durations(Completed) | 101 | 2026-02-17 | 2026-06-24 | 2026-02-17 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 4100 | 4100 | 4100 | No | 1 | 1 | 0 | 0
PG-GN-MS-30_R | Project Durations(Remaining) | 148 | 2026-06-25 | 2026-12-15 | 2026-07-01 |  | 0 | 0 | 0 | 64.86% | 65% | 5900 | 3827 | 3835 | No | 1 | 0 | 1 | 0
PG-GN-MS-20 | Project Completion Date | 0 |  | 2026-12-16 |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | Yes | 1 | 0 | 0 | 1
CONTRACUAL MILESTONES |  | 188 | 2026-05-05 | 2026-12-16 | 2026-05-05 |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 6 | 2 | 0 | 4
PG-IN-MS-20 | Completion of Earthworks (Cut and fill) For Site Layout | 0 |  | 2026-05-05 |  | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-IN-MS-10 | Site Preparation, Work Plans, Schedule ,Drawings Submittals | 0 |  | 2026-08-04 |  | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-IN-MS-30 | Completion of Toilet Building | 0 |  | 2026-10-28 |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | No | 1 | 0 | 0 | 1
PG-IN-MS-50 | Completion of Playground Works | 0 |  | 2026-12-07 |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | No | 1 | 0 | 0 | 1
PG-IN-MS-40 | Completion of Landscape Works | 0 |  | 2026-12-16 |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-IN-MS-60 | Substantial Completion - All Works | 0 |  | 2026-12-16 |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | Yes | 1 | 0 | 0 | 1
QASSIM |  | 250 | 2026-02-17 | 2026-12-16 | 2026-02-17 |  | 14262756.14 | 12338896.49 | 17537540 | 81.33% | 70.36% | 8496 | 6820 | 6127 |  | 667 | 554 | 86 | 27
MOBILIZATION |  | 29 | 2026-02-17 | 2026-03-29 | 2026-02-17 | 2026-03-28 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 9 | 9 | 0 | 0
TEMPORARY CAMP |  | 28 | 2026-02-17 | 2026-03-28 | 2026-02-17 | 2026-03-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-MOB-CAM-10 | Temporary Underground Utilities works | 28 | 2026-02-17 | 2026-03-28 | 2026-02-17 | 2026-03-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-MOB-CAM-20 | Temporary Porta-Cabins | 21 | 2026-02-26 | 2026-03-28 | 2026-02-26 | 2026-03-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-MOB-CAM-30 | Temporary Toilets | 21 | 2026-02-26 | 2026-03-28 | 2026-02-26 | 2026-03-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-MOB-CAM-40 | Temporary Mosque | 13 | 2026-03-08 | 2026-03-28 | 2026-03-08 | 2026-03-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SITE OFFICES |  | 29 | 2026-02-17 | 2026-03-29 | 2026-02-17 | 2026-03-28 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-Q-MOB-SO-10 | Temporary Underground Utilities works | 29 | 2026-02-17 | 2026-03-29 | 2026-02-17 | 2026-03-28 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-MOB-SO-20 | Temporary Porta-Cabins | 22 | 2026-02-26 | 2026-03-29 | 2026-02-26 | 2026-03-28 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-MOB-SO-30 | Temporary Toilets | 22 | 2026-02-26 | 2026-03-29 | 2026-02-26 | 2026-03-28 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-MOB-SO-40 | Temporary Mosque | 16 | 2026-03-05 | 2026-03-29 | 2026-03-05 | 2026-03-28 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-MOB-SO-50 | Car Parking Area | 10 | 2026-03-12 | 2026-03-29 | 2026-03-12 | 2026-03-28 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
GENERAL REQUIEREMENTS |  | 57 | 2026-02-17 | 2026-04-30 | 2026-02-17 | 2026-04-29 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-GEN-20 | HSSE Submission Plan | 57 | 2026-02-17 | 2026-04-30 | 2026-02-17 | 2026-04-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-GEN-30 | Surveying report Submission Plan | 57 | 2026-02-17 | 2026-04-30 | 2026-02-17 | 2026-04-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-GEN-40 | Baseline Submission | 6 | 2026-02-28 | 2026-03-07 | 2026-02-28 | 2026-03-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-GEN-10 | QA/QC Submission Plan | 16 | 2026-03-12 | 2026-04-04 | 2026-03-12 | 2026-04-04 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ENGINEERING |  | 146 | 2026-02-17 | 2026-08-16 | 2026-02-17 |  | 526126.2 | 526126.2 | 526126.2 | 100% | 100% | 0 | 0 | 0 |  | 262 | 258 | 4 | 0
SHOP DRAWINGS SUBMITTALS |  | 136 | 2026-02-17 | 2026-08-04 | 2026-02-17 |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 62 | 58 | 4 | 0
STRUCTURAL DRAWINGS |  | 111 | 2026-02-17 | 2026-07-06 | 2026-02-17 | 2026-07-11 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PROJECT FENCE |  | 19 | 2026-04-29 | 2026-05-21 | 2026-04-29 | 2026-05-20 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ST-SD-SB-10 | Excavation Drawings | 19 | 2026-04-29 | 2026-05-21 | 2026-04-29 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ST-SD-SB-20 | Foundation Drawings | 19 | 2026-04-29 | 2026-05-21 | 2026-04-29 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PADEL PLAYGROUND FENCE |  | 19 | 2026-04-29 | 2026-05-21 | 2026-04-29 | 2026-05-20 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ST-SD-SB-30 | Excavation Drawings | 19 | 2026-04-29 | 2026-05-21 | 2026-04-29 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ST-SD-SB-40 | Foundation Drawings | 19 | 2026-04-29 | 2026-05-21 | 2026-04-29 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 10 | 2026-06-25 | 2026-07-06 | 2026-07-01 | 2026-07-11 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ST-SD-SB-50 | Excavation Drawings | 8 | 2026-06-25 | 2026-07-04 | 2026-07-01 | 2026-07-02 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ST-SD-SB-60 | Foundation Drawings | 10 | 2026-06-25 | 2026-07-06 | 2026-07-07 | 2026-07-11 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
TOILET BUILDING |  | 43 | 2026-02-17 | 2026-04-14 | 2026-02-17 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ST-SD-SB-70 | Excavation Drawings | 43 | 2026-02-17 | 2026-04-14 | 2026-02-17 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ST-SD-SB-80 | Foundation Drawings | 41 | 2026-02-19 | 2026-04-14 | 2026-02-19 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
WATER STORAGE TANK |  | 41 | 2026-02-19 | 2026-04-14 | 2026-02-19 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ST-SD-SB-90 | Excavation Drawings | 41 | 2026-02-19 | 2026-04-14 | 2026-02-19 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ST-SD-SB-100 | Foundation Drawings | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SEPTIC TANK |  | 13 | 2026-04-28 | 2026-05-13 | 2026-04-28 | 2026-05-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ST-SD-SB-110 | Reinforcement Detail Drawings | 13 | 2026-04-28 | 2026-05-13 | 2026-04-28 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ST-SD-SB-120 | Concrete Detail Drawings | 13 | 2026-04-28 | 2026-05-13 | 2026-04-28 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL DRAWINGS |  | 124 | 2026-02-19 | 2026-07-23 | 2026-02-19 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 13 | 13 | 0 | 0
TOILET BUILDING |  | 42 | 2026-02-19 | 2026-04-15 | 2026-02-19 | 2026-04-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 10 | 0 | 0
PG-Q-EN-AR-SD-SB-10 | Ground Floor Plan | 40 | 2026-02-19 | 2026-04-13 | 2026-02-19 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-SB-20 | Roof Floor Plan | 37 | 2026-02-25 | 2026-04-14 | 2026-02-25 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-SB-50 | Floor Finish Layout | 36 | 2026-02-25 | 2026-04-13 | 2026-02-25 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-SB-60 | Reflected Ceiling Layout | 37 | 2026-02-25 | 2026-04-13 | 2026-02-25 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-SB-70 | Enlarged Toilets Layout | 38 | 2026-02-25 | 2026-04-15 | 2026-02-25 | 2026-04-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-SB-30 | Elevations | 34 | 2026-03-01 | 2026-04-14 | 2026-03-01 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-SB-80 | Doors & Windows Schedule | 35 | 2026-03-01 | 2026-04-15 | 2026-03-01 | 2026-04-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-SB-90 | Aluminum Work | 35 | 2026-03-01 | 2026-04-15 | 2026-03-01 | 2026-04-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-SB-100 | Cladding Details | 34 | 2026-03-01 | 2026-04-14 | 2026-03-01 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-SB-40 | Sections | 32 | 2026-03-03 | 2026-04-13 | 2026-03-03 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 15 | 2026-07-07 | 2026-07-23 | 2026-08-14 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-EN-AR-SD-SB-110 | Membrane & Insulation Details | 15 | 2026-07-07 | 2026-07-23 | 2026-08-14 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-SB-120 | Steel Cable System | 15 | 2026-07-07 | 2026-07-23 | 2026-08-14 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-SB-130 | Doors & Access Sytem Drawings | 15 | 2026-07-07 | 2026-07-23 | 2026-08-14 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
LANDSCAPE DRAWINGS |  | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 13 | 13 | 0 | 0
PG-Q-EN-LS-SD-SB-10 | Hardscape Layout Plan | 36 | 2026-02-23 | 2026-04-11 | 2026-02-23 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-SB-20 | Interlock Tile Details | 36 | 2026-02-23 | 2026-04-11 | 2026-02-23 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-SB-30 | Stamped Concrete Pattern & Section | 36 | 2026-02-23 | 2026-04-11 | 2026-02-23 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-SB-40 | Tartan Flooring Layout & Details | 36 | 2026-02-23 | 2026-04-11 | 2026-02-23 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-SB-50 | Bike Path Layout & Details | 36 | 2026-02-23 | 2026-04-11 | 2026-02-23 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-SB-60 | Walking Path layout & Details | 36 | 2026-02-23 | 2026-04-11 | 2026-02-23 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-SB-70 | Tree Planting Plan & Details | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-SB-80 | Traffic Sign Location & Details | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-SB-90 | Football Playground Layout | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-SB-100 | Padel Playground Layout | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-SB-110 | Basketball Playground Layout | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-SB-120 | Playground Details | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-SB-130 | Padel Fence Elevation & Details | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MECHANICAL DRAWINGS |  | 111 | 2026-02-28 | 2026-07-15 | 2026-02-28 |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 9 | 1 | 0
WATER SUPPLY SYSTEM |  | 32 | 2026-02-28 | 2026-04-11 | 2026-02-28 | 2026-04-09 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-EN-ME-SD-SB-20 | Pump Room Layout | 32 | 2026-02-28 | 2026-04-11 | 2026-02-28 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ME-SD-SB-10 | Cold & Hot Water Piping Layout | 28 | 2026-03-04 | 2026-04-11 | 2026-03-04 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ME-SD-SB-30 | Booster Pump Details | 28 | 2026-03-04 | 2026-04-11 | 2026-03-04 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ME-SD-SB-40 | GRP Water Tank Details | 24 | 2026-03-09 | 2026-04-11 | 2026-03-09 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SEWER AND DRAINAGE SYSTEM |  | 28 | 2026-03-04 | 2026-04-11 | 2026-03-04 | 2026-04-09 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-EN-ME-SD-SB-50 | Drainage Layout | 28 | 2026-03-04 | 2026-04-11 | 2026-03-04 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ME-SD-SB-60 | Floor Drains & Cleanouts Details | 24 | 2026-03-09 | 2026-04-11 | 2026-03-09 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ME-SD-SB-70 | Inspection Chamber Details | 21 | 2026-03-12 | 2026-04-11 | 2026-03-12 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION SYSTEM |  | 24 | 2026-03-09 | 2026-04-11 | 2026-03-09 | 2026-04-09 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ME-SD-SB-80 | HDPE Pipe Routing | 24 | 2026-03-09 | 2026-04-11 | 2026-03-09 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ME-SD-SB-90 | Irrigation Network Layout | 21 | 2026-03-12 | 2026-04-11 | 2026-03-12 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 18 | 2026-06-25 | 2026-07-15 | 2026-07-30 |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 0 | 1 | 0
PG-Q-EN-ME-SD-SB-100 | Air Package and HVAC System Drawings | 18 | 2026-06-25 | 2026-07-15 | 2026-07-30 |  | 0 | 0 | 0 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
ELECTRICAL DRAWINGS |  | 70 | 2026-05-11 | 2026-08-04 | 2026-05-11 |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 14 | 11 | 3 | 0
POWER AND LIGHTING SYSTEM |  | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-EN-EL-SD-SB-10 | Main Distribution Board (MDB) Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-SB-20 | Pump Room Power Panel | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-SB-30 | Street Lighting Power Panel | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-SB-40 | Site Lighting Pole Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELV SYSTEM |  | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-EN-EL-SD-SB-50 | Telecom & Data Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-SB-60 | CCTV Camera Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-SB-70 | Access Control Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-SB-80 | AV System Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE ALARM SYSTEM |  | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-EN-EL-SD-SB-90 | Fire Alarm Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-SB-100 | Detector & Manual Call Point Details | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-SB-110 | Control Panel Wiring Diagram | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 17 | 2026-07-16 | 2026-08-04 | 2026-07-30 |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 0 | 3 | 0
PG-Q-EN-EL-SD-SB-120 | Power & Lighting System Drawings | 10 | 2026-07-16 | 2026-07-27 | 2026-07-30 |  | 0 | 0 | 0 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-Q-EN-EL-SD-SB-130 | Generators Details | 15 | 2026-07-16 | 2026-08-02 | 2026-07-30 |  | 0 | 0 | 0 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-Q-EN-EL-SD-SB-140 | Smart Dome System Drawings | 17 | 2026-07-16 | 2026-08-04 | 2026-07-30 |  | 0 | 0 | 0 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
SHOP DRAWINGS APPROVALS |  | 144 | 2026-02-19 | 2026-08-16 | 2026-02-19 | 2026-09-21 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 62 | 62 | 0 | 0
STRUCTURAL DRAWINGS |  | 116 | 2026-02-19 | 2026-07-14 | 2026-02-19 | 2026-07-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PROJECT FENCE |  | 7 | 2026-05-13 | 2026-05-21 | 2026-05-13 | 2026-05-20 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ST-SD-AP-10 | Excavation Drawings | 7 | 2026-05-13 | 2026-05-21 | 2026-05-13 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ST-SD-AP-20 | Foundation Drawings | 7 | 2026-05-13 | 2026-05-21 | 2026-05-13 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PADEL PLAYGROUND FENCE |  | 9 | 2026-05-11 | 2026-05-21 | 2026-05-11 | 2026-05-20 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ST-SD-AP-30 | Excavation Drawings | 9 | 2026-05-11 | 2026-05-21 | 2026-05-11 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ST-SD-AP-40 | Foundation Drawings | 9 | 2026-05-11 | 2026-05-21 | 2026-05-11 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 9 | 2026-07-05 | 2026-07-14 | 2026-07-06 | 2026-07-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ST-SD-AP-50 | Excavation Drawings | 4 | 2026-07-05 | 2026-07-08 | 2026-07-06 | 2026-07-07 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ST-SD-AP-60 | Foundation Drawings | 7 | 2026-07-07 | 2026-07-14 | 2026-07-08 | 2026-07-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
TOILET BUILDING |  | 44 | 2026-02-19 | 2026-04-18 | 2026-02-19 | 2026-04-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ST-SD-AP-70 | Excavation Drawings | 44 | 2026-02-19 | 2026-04-18 | 2026-02-19 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ST-SD-AP-80 | Foundation Drawings | 36 | 2026-03-02 | 2026-04-18 | 2026-03-02 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
WATER STORAGE TANK |  | 42 | 2026-02-23 | 2026-04-18 | 2026-02-23 | 2026-04-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ST-SD-AP-90 | Excavation Drawings | 42 | 2026-02-23 | 2026-04-18 | 2026-02-23 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ST-SD-AP-100 | Foundation Drawings | 34 | 2026-03-04 | 2026-04-18 | 2026-03-04 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SEPTIC TANK |  | 3 | 2026-05-11 | 2026-05-14 | 2026-05-11 | 2026-05-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ST-SD-AP-110 | Reinforcement Detail Drawings | 3 | 2026-05-11 | 2026-05-14 | 2026-05-11 | 2026-05-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ST-SD-AP-120 | Concrete Detail Drawings | 3 | 2026-05-11 | 2026-05-14 | 2026-05-11 | 2026-05-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL DRAWINGS |  | 127 | 2026-02-25 | 2026-08-01 | 2026-02-25 | 2026-09-21 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 13 | 13 | 0 | 0
TOILET BUILDING |  | 40 | 2026-02-25 | 2026-04-18 | 2026-02-25 | 2026-04-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 10 | 0 | 0
PG-Q-EN-AR-SD-AP-10 | Ground Floor Plan | 40 | 2026-02-25 | 2026-04-18 | 2026-02-25 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-AP-20 | Roof Floor Plan | 37 | 2026-03-01 | 2026-04-18 | 2026-03-01 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-AP-50 | Floor Finish Layout | 35 | 2026-03-03 | 2026-04-18 | 2026-03-03 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-AP-60 | Reflected Ceiling Layout | 35 | 2026-03-03 | 2026-04-18 | 2026-03-03 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-AP-70 | Enlarged Toilets Layout | 35 | 2026-03-03 | 2026-04-18 | 2026-03-03 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-AP-30 | Elevations | 34 | 2026-03-04 | 2026-04-18 | 2026-03-04 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-AP-80 | Doors & Windows Schedule | 34 | 2026-03-04 | 2026-04-18 | 2026-03-04 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-AP-90 | Aluminum Work | 33 | 2026-03-05 | 2026-04-18 | 2026-03-05 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-AP-100 | Cladding Details | 33 | 2026-03-05 | 2026-04-18 | 2026-03-05 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-AP-40 | Sections | 31 | 2026-03-08 | 2026-04-18 | 2026-03-08 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 7 | 2026-07-25 | 2026-08-01 | 2026-08-20 | 2026-09-21 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-EN-AR-SD-AP-110 | Membrane & Insulation Details | 7 | 2026-07-25 | 2026-08-01 | 2026-08-20 | 2026-09-21 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-AP-120 | Steel Cable System | 7 | 2026-07-25 | 2026-08-01 | 2026-08-20 | 2026-09-21 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-AP-130 | Doors & Access Sytem Drawings | 7 | 2026-07-25 | 2026-08-01 | 2026-08-20 | 2026-09-21 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
LANDSCAPE DRAWINGS |  | 39 | 2026-02-26 | 2026-04-18 | 2026-02-26 | 2026-04-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 13 | 13 | 0 | 0
PG-Q-EN-LS-SD-AP-50 | Bike Path Layout & Details | 39 | 2026-02-26 | 2026-04-18 | 2026-02-26 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-AP-60 | Walking Path layout & Details | 39 | 2026-02-26 | 2026-04-18 | 2026-02-26 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-AP-80 | Traffic Sign Location & Details | 39 | 2026-02-26 | 2026-04-18 | 2026-02-26 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-AP-130 | Padel Fence Elevation & Details | 39 | 2026-02-26 | 2026-04-18 | 2026-02-26 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-AP-10 | Hardscape Layout Plan | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-AP-40 | Tartan Flooring Layout & Details | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-AP-70 | Tree Planting Plan & Details | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-AP-90 | Football Playground Layout | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-AP-100 | Padel Playground Layout | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-AP-110 | Basketball Playground Layout | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-AP-120 | Playground Details | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-AP-20 | Interlock Tile Details | 28 | 2026-03-11 | 2026-04-18 | 2026-03-11 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-AP-30 | Stamped Concrete Pattern & Section | 18 | 2026-03-28 | 2026-04-18 | 2026-03-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MECHANICAL DRAWINGS |  | 113 | 2026-03-09 | 2026-07-27 | 2026-03-09 | 2026-09-21 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 10 | 0 | 0
WATER SUPPLY SYSTEM |  | 27 | 2026-03-09 | 2026-04-14 | 2026-03-09 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-EN-ME-SD-AP-10 | Cold & Hot Water Piping Layout | 27 | 2026-03-09 | 2026-04-14 | 2026-03-09 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ME-SD-AP-30 | Booster Pump Details | 26 | 2026-03-10 | 2026-04-14 | 2026-03-10 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ME-SD-AP-40 | GRP Water Tank Details | 22 | 2026-03-14 | 2026-04-13 | 2026-03-14 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ME-SD-AP-20 | Pump Room Layout | 21 | 2026-03-16 | 2026-04-14 | 2026-03-16 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SEWER AND DRAINAGE SYSTEM |  | 27 | 2026-03-09 | 2026-04-14 | 2026-03-09 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-EN-ME-SD-AP-50 | Drainage Layout | 27 | 2026-03-09 | 2026-04-14 | 2026-03-09 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ME-SD-AP-60 | Floor Drains & Cleanouts Details | 21 | 2026-03-16 | 2026-04-14 | 2026-03-16 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ME-SD-AP-70 | Inspection Chamber Details | 21 | 2026-03-16 | 2026-04-14 | 2026-03-16 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION SYSTEM |  | 24 | 2026-03-12 | 2026-04-14 | 2026-03-12 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ME-SD-AP-80 | HDPE Pipe Routing | 24 | 2026-03-12 | 2026-04-14 | 2026-03-12 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ME-SD-AP-90 | Irrigation Network Layout | 20 | 2026-03-17 | 2026-04-14 | 2026-03-17 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 10 | 2026-07-16 | 2026-07-27 | 2026-08-20 | 2026-09-21 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-Q-EN-ME-SD-AP-100 | Air Package and HVAC System Drawings | 10 | 2026-07-16 | 2026-07-27 | 2026-08-20 | 2026-09-21 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL DRAWINGS |  | 72 | 2026-05-20 | 2026-08-16 | 2026-05-20 | 2026-09-21 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 14 | 14 | 0 | 0
POWER AND LIGHTING SYSTEM |  | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-EN-EL-SD-AP-10 | Main Distribution Board (MDB) Layout | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-AP-20 | Pump Room Power Panel | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-AP-30 | Street Lighting Power Panel | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-AP-40 | Site Lighting Pole Layout | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELV SYSTEM |  | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-EN-EL-SD-AP-50 | Telecom & Data Layout | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-AP-60 | CCTV Camera Layout | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-AP-70 | Access Control Layout | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-AP-80 | AV System Layout | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE ALARM SYSTEM |  | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-EN-EL-SD-AP-90 | Fire Alarm Layout | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-AP-100 | Detector & Manual Call Point Details | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-AP-110 | Control Panel Wiring Diagram | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 17 | 2026-07-28 | 2026-08-16 | 2026-08-20 | 2026-09-21 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-EN-EL-SD-AP-120 | Power & Lighting System Drawings | 17 | 2026-07-28 | 2026-08-16 | 2026-08-20 | 2026-09-21 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-AP-130 | Generators Details | 8 | 2026-08-03 | 2026-08-11 | 2026-08-20 | 2026-09-21 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-AP-140 | Smart Dome System Drawings | 6 | 2026-08-05 | 2026-08-11 | 2026-08-20 | 2026-09-21 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MATERIAL SUBMITTALS |  | 120 | 2026-02-17 | 2026-07-16 | 2026-02-17 | 2026-08-20 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 63 | 63 | 0 | 0
LONG LEAD ITEMS |  | 120 | 2026-02-17 | 2026-07-16 | 2026-02-17 | 2026-08-20 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 24 | 24 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 56 | 2026-02-25 | 2026-05-06 | 2026-02-25 | 2026-05-05 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-PR-LL-LS-MS-20 | Benches, Seats (Rectangular & Circular) | 56 | 2026-02-25 | 2026-05-06 | 2026-02-25 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-MS-30 | Fence, gates and accessories | 49 | 2026-03-05 | 2026-05-06 | 2026-03-05 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-MS-10 | Bike and Walk Path Materials | 49 | 2026-03-05 | 2026-05-06 | 2026-03-05 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 120 | 2026-02-17 | 2026-07-16 | 2026-02-17 | 2026-08-20 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 6 | 6 | 0 | 0
PG-Q-PR-LL-SP-MS-50 | Air Dome Materials(Completed) | 101 | 2026-02-17 | 2026-06-25 | 2026-02-17 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MS-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc) | 48 | 2026-03-07 | 2026-05-06 | 2026-03-07 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MS-20 | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc) | 48 | 2026-03-07 | 2026-05-06 | 2026-03-07 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MS-30 | Padel Playgound Materials (Flooring, fence, tempered glass, etc) | 48 | 2026-03-07 | 2026-05-06 | 2026-03-07 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MS-40 | Tartan Floor | 48 | 2026-03-07 | 2026-05-06 | 2026-03-07 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MS-50_R | Air Dome Materials(Remaining) | 19 | 2026-06-25 | 2026-07-16 | 2026-06-30 | 2026-08-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 43 | 2026-03-04 | 2026-04-28 | 2026-03-04 | 2026-04-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-Q-PR-LL-CO-MS-10 | Autoclaved Aerated Panel | 43 | 2026-03-04 | 2026-04-28 | 2026-03-04 | 2026-04-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 47 | 2026-03-09 | 2026-05-07 | 2026-03-09 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-PR-LL-MT-MS-10 | Metal Doors | 47 | 2026-03-09 | 2026-05-07 | 2026-03-09 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-MT-MS-20 | Curtain Wall | 47 | 2026-03-09 | 2026-05-07 | 2026-03-09 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 46 | 2026-03-10 | 2026-05-07 | 2026-03-10 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-PR-LL-PB-MS-10 | Booster Pump | 46 | 2026-03-10 | 2026-05-07 | 2026-03-10 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-PB-MS-20 | GRP Sectional Panel Water Tanks (4x3x3m) | 42 | 2026-03-15 | 2026-05-07 | 2026-03-15 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 50 | 2026-03-05 | 2026-05-07 | 2026-03-05 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-PR-LL-IR-MS-10 | HDPE Pipes | 50 | 2026-03-05 | 2026-05-07 | 2026-03-05 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-IR-MS-20 | Irrigation Control System | 50 | 2026-03-05 | 2026-05-07 | 2026-03-05 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 26 | 2026-05-12 | 2026-06-16 | 2026-05-12 | 2026-06-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 8 | 8 | 0 | 0
PG-Q-PR-LL-EL-MS-10 | Main Distribution Board | 26 | 2026-05-12 | 2026-06-16 | 2026-05-12 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MS-20 | Power Panels (Pump, Street Light) | 26 | 2026-05-12 | 2026-06-16 | 2026-05-12 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MS-30 | Site Lighting Poles | 26 | 2026-05-12 | 2026-06-16 | 2026-05-12 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MS-40 | Lighting Fixtures | 26 | 2026-05-12 | 2026-06-16 | 2026-05-12 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MS-50 | Grounding System Materials (Earth pit rod, LPS, etc) | 26 | 2026-05-12 | 2026-06-16 | 2026-05-12 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MS-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc) | 26 | 2026-05-12 | 2026-06-16 | 2026-05-12 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MS-70 | Security and Access Control System Materials | 26 | 2026-05-12 | 2026-06-16 | 2026-05-12 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MS-80 | Fire Alarm System Materials | 26 | 2026-05-12 | 2026-06-16 | 2026-05-12 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SHORT LEAD ITEMS |  | 28 | 2026-02-17 | 2026-03-28 | 2026-02-17 | 2026-03-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 39 | 39 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 23 | 2026-02-17 | 2026-03-17 | 2026-02-17 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 8 | 8 | 0 | 0
PG-Q-PR-SL-LS-MS-10 | Backfilling Materials | 23 | 2026-02-17 | 2026-03-17 | 2026-02-17 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MS-30 | Compacted Natural Ground Soil | 20 | 2026-02-21 | 2026-03-17 | 2026-02-21 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MS-20 | Interlock tiles | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MS-40 | Curb Stone | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MS-50 | Thermoplastic pavement road marking | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MS-60 | Traffic Signages | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MS-70 | Trees | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MS-80 | Lawn | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 28 | 2026-02-17 | 2026-03-28 | 2026-02-17 | 2026-03-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-Q-PR-SL-CO-MS-10 | Steel Rebar | 17 | 2026-02-17 | 2026-03-10 | 2026-02-17 | 2026-03-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-MS-20 | Concrete | 13 | 2026-02-23 | 2026-03-10 | 2026-02-23 | 2026-03-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-MS-40 | CMU Block | 19 | 2026-03-01 | 2026-03-28 | 2026-03-01 | 2026-03-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-MS-50 | Concrete Repair & Protection Materials | 19 | 2026-03-01 | 2026-03-28 | 2026-03-01 | 2026-03-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-MS-30 | Screed | 9 | 2026-03-12 | 2026-03-28 | 2026-03-12 | 2026-03-26 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL & FINISHES WORK |  | 18 | 2026-02-21 | 2026-03-15 | 2026-02-21 | 2026-03-14 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PG-Q-PR-SL-AR-MS-40 | Cement Plaster | 18 | 2026-02-21 | 2026-03-15 | 2026-02-21 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MS-50 | Acrylic Paint | 15 | 2026-02-25 | 2026-03-15 | 2026-02-25 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MS-80 | Phenolic Partition | 10 | 2026-03-03 | 2026-03-15 | 2026-03-03 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MS-90 | Glass Partition | 10 | 2026-03-03 | 2026-03-15 | 2026-03-03 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MS-10 | Ceramic tiles | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MS-20 | Anti-slip Granite tiles | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MS-30 | Epoxy Paint | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MS-60 | Stone Cladding | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MS-70 | Aluminum Plates | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MS-100 | Gypsum Boards | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MS-110 | Specialities Materials (Toilet accessories, lockers, logo, etc) | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MS-120 | Waterproofing System Materials | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 11 | 2026-03-04 | 2026-03-17 | 2026-03-04 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-PR-SL-MT-MS-20 | Galvanized Steel Roof Scupper | 11 | 2026-03-04 | 2026-03-17 | 2026-03-04 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-MT-MS-30 | Galvanized Steel Cover with frame | 11 | 2026-03-04 | 2026-03-17 | 2026-03-04 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-MT-MS-10 | Galvanized Steel Ladder | 8 | 2026-03-08 | 2026-03-17 | 2026-03-08 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
HVAC WORK |  | 19 | 2026-02-23 | 2026-03-17 | 2026-02-23 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-PR-SL-AC-MS-10 | Split Air Conditioning Unit | 19 | 2026-02-23 | 2026-03-17 | 2026-02-23 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-MS-20 | Air Duct | 15 | 2026-02-28 | 2026-03-17 | 2026-02-28 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-MS-30 | Diffusers and Grills | 11 | 2026-03-04 | 2026-03-17 | 2026-03-04 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-MS-40 | Exhaust fans | 11 | 2026-03-04 | 2026-03-17 | 2026-03-04 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-PR-SL-PB-MS-10 | PPR Pipes & Valves | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-PB-MS-20 | UPCV Pipes | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-PB-MS-30 | Sanitary Drainage Fixtures | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 17 | 2026-02-25 | 2026-03-17 | 2026-02-25 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-PR-SL-IR-MS-10 | Gate Valve including valve box | 17 | 2026-02-25 | 2026-03-17 | 2026-02-25 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-IR-MS-20 | Bulbblers and Spreyers | 12 | 2026-03-03 | 2026-03-17 | 2026-03-03 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-Q-PR-SL-EL-MS-10 | Wiring Devices Materials | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE FIGHTING WORK |  | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-Q-PR-SL-FF-MS-10 | Fire Extinguishers | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MATERIAL APPROVALS |  | 118 | 2026-02-21 | 2026-07-18 | 2026-02-21 | 2026-10-01 | 526126.2 | 526126.2 | 526126.2 | 100% | 100% | 0 | 0 | 0 |  | 75 | 75 | 0 | 0
LONG LEAD ITEMS |  | 111 | 2026-03-02 | 2026-07-18 | 2026-03-02 | 2026-10-01 | 358885.26 | 358885.26 | 358885.26 | 100% | 100% | 0 | 0 | 0 |  | 36 | 36 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 2 | 2026-05-11 | 2026-05-12 | 2026-05-11 | 2026-05-12 | 19812.18 | 19812.18 | 19812.18 | 100% | 100% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-PR-LL-LS-MA-20 | Benches, Seats (Rectangular & Circular) | 2 | 2026-05-11 | 2026-05-12 | 2026-05-11 | 2026-05-12 | 4007.97 | 4007.97 | 4007.97 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-MA-30 | Fence, gates and accessories | 2 | 2026-05-11 | 2026-05-12 | 2026-05-11 | 2026-05-12 | 2529.21 | 2529.21 | 2529.21 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-MA-10 | Bike and Walk Path Materials | 2 | 2026-05-11 | 2026-05-12 | 2026-05-11 | 2026-05-12 | 13275 | 13275 | 13275 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 96 | 2026-03-02 | 2026-06-30 | 2026-03-02 | 2026-09-19 | 273522.54 | 273522.54 | 273522.54 | 100% | 100% | 0 | 0 | 0 |  | 6 | 6 | 0 | 0
PG-Q-PR-LL-SP-MA-50 | Air Dome Materials(Completed) | 91 | 2026-03-02 | 2026-06-24 | 2026-03-02 | 2026-06-24 | 62622.07 | 62622.07 | 62622.07 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MA-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc) | 8 | 2026-05-12 | 2026-05-20 | 2026-05-12 | 2026-05-20 | 13051.5 | 13051.5 | 13051.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MA-20 | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc) | 8 | 2026-05-12 | 2026-05-20 | 2026-05-12 | 2026-05-20 | 2256 | 2256 | 2256 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MA-30 | Padel Playgound Materials (Flooring, fence, tempered glass, etc) | 8 | 2026-05-12 | 2026-05-20 | 2026-05-12 | 2026-05-20 | 5950.8 | 5950.8 | 5950.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MA-40 | Tartan Floor | 8 | 2026-05-12 | 2026-05-20 | 2026-05-12 | 2026-05-20 | 43524 | 43524 | 43524 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MA-50_R | Air Dome Materials(Remaining) | 5 | 2026-06-25 | 2026-06-30 | 2026-07-02 | 2026-09-19 | 146118.17 | 146118.17 | 146118.17 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 40 | 2026-03-09 | 2026-04-28 | 2026-03-09 | 2026-04-28 | 1417.5 | 1417.5 | 1417.5 | 100% | 100% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-Q-PR-LL-CO-MA-10 | Autoclaved Aerated Panel | 40 | 2026-03-09 | 2026-04-28 | 2026-03-09 | 2026-04-28 | 1417.5 | 1417.5 | 1417.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 34 | 2026-06-09 | 2026-07-18 | 2026-06-09 | 2026-10-01 | 1902-06-07 05:31 | 889.23 | 1902-06-07 05:31 | 100% | 100% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-PR-LL-MT-MA-10 | Metal Doors(Completed) | 14 | 2026-06-09 | 2026-06-24 | 2026-06-09 | 2026-06-24 | 1900-03-16 12:29 | 76.52 | 76.52 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-MT-MA-20 | Curtain Wall(Completed) | 14 | 2026-06-09 | 2026-06-24 | 2026-06-09 | 2026-06-24 | 1901-04-01 00:29 | 1901-04-01 00:29 | 1901-04-01 00:29 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-MT-MA-10_R | Metal Doors(Remaining) | 15 | 2026-06-25 | 2026-07-12 | 2026-09-16 | 2026-10-01 | 1900-02-19 00:14 | 51.01 | 51.01 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-MT-MA-20_R | Curtain Wall(Remaining) | 20 | 2026-06-25 | 2026-07-18 | 2026-09-16 | 2026-10-01 | 1900-10-30 16:19 | 1900-10-30 16:19 | 1900-10-30 16:19 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 34 | 2026-06-09 | 2026-07-18 | 2026-05-20 | 2026-06-24 | 3553.95 | 3553.95 | 3553.95 | 100% | 100% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-PR-LL-PB-MA-10 | Booster Pump(Completed) | 14 | 2026-06-09 | 2026-06-24 | 2026-06-09 | 2026-06-24 | 1090.98 | 1090.98 | 1090.98 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-PB-MA-20 | GRP Sectional Panel Water Tanks (4x3x3m)(Completed) | 14 | 2026-06-09 | 2026-06-24 | 2026-06-09 | 2026-06-24 | 1041.39 | 1041.39 | 1041.39 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-PB-MA-10_R | Booster Pump(Remaining) | 20 | 2026-06-25 | 2026-07-18 | 2026-05-20 | 2026-05-21 | 727.32 | 727.32 | 727.32 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-PB-MA-20_R | GRP Sectional Panel Water Tanks (4x3x3m)(Remaining) | 15 | 2026-06-25 | 2026-07-12 | 2026-06-03 | 2026-06-06 | 694.26 | 694.26 | 694.26 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 45 | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-06 | 24486.75 | 24486.75 | 24486.75 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-PR-LL-IR-MA-10 | HDPE Pipes | 45 | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-06 | 19941 | 19941 | 19941 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-IR-MA-20 | Irrigation Control System | 45 | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-06 | 4545.75 | 4545.75 | 4545.75 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 41 | 2026-05-12 | 2026-07-02 | 2026-05-12 | 2026-09-16 | 35203.11 | 35203.11 | 35203.11 | 100% | 100% | 0 | 0 | 0 |  | 16 | 16 | 0 | 0
PG-Q-PR-LL-EL-MA-10 | Main Distribution Board(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 1900-10-23 12:58 | 297.54 | 297.54 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-20 | Power Panels (Pump, Street Light)(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 1900-08-25 00:43 | 238.03 | 1900-08-25 00:43 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-30 | Site Lighting Poles(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 1947-08-26 06:43 | 17405.28 | 17405.28 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-40 | Lighting Fixtures(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 1902-02-07 16:48 | 769.7 | 1902-02-07 16:48 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 602.51 | 602.51 | 602.51 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 587.63 | 587.63 | 587.63 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-70 | Security and Access Control System Materials(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 743.94 | 743.94 | 743.94 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-80 | Fire Alarm System Materials(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 1901-04-21 05:31 | 477.23 | 477.23 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-10_R | Main Distribution Board(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-30 | 2026-09-16 | 1900-07-16 08:38 | 198.36 | 198.36 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-20_R | Power Panels (Pump, Street Light)(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-30 | 2026-09-16 | 1900-06-06 16:34 | 158.69 | 1900-06-06 16:34 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-30_R | Site Lighting Poles(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-30 | 2026-09-16 | 1931-10-07 12:29 | 11603.52 | 11603.52 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-40_R | Lighting Fixtures(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-12 | 2026-07-23 | 513.13 | 513.13 | 513.13 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-30 | 2026-09-16 | 1901-02-04 16:19 | 401.68 | 401.68 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-30 | 2026-09-16 | 391.75 | 1901-01-25 18:00 | 391.75 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-70_R | Security and Access Control System Materials(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-27 | 2026-09-16 | 1901-05-09 23:02 | 495.96 | 495.96 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-80_R | Fire Alarm System Materials(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-27 | 2026-09-16 | 1900-11-13 03:50 | 1900-11-13 03:50 | 1900-11-13 03:50 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SHORT LEAD ITEMS |  | 25 | 2026-02-21 | 2026-03-26 | 2026-02-21 | 2026-03-26 | 167240.94 | 167240.94 | 167240.94 | 100% | 100% | 0 | 0 | 0 |  | 39 | 39 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 25 | 2026-02-21 | 2026-03-26 | 2026-02-21 | 2026-03-26 | 139867.29 | 139867.29 | 139867.29 | 100% | 100% | 0 | 0 | 0 |  | 8 | 8 | 0 | 0
PG-Q-PR-SL-LS-MA-10 | Backfilling Materials | 25 | 2026-02-21 | 2026-03-26 | 2026-02-21 | 2026-03-26 | 36450 | 36450 | 36450 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MA-30 | Compacted Natural Ground Soil | 22 | 2026-02-25 | 2026-03-26 | 2026-02-25 | 2026-03-26 | 8580 | 8580 | 8580 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MA-20 | Interlock tiles | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 29832 | 29832 | 29832 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MA-40 | Curb Stone | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 43185 | 43185 | 43185 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MA-50 | Thermoplastic pavement road marking | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 525.63 | 525.63 | 525.63 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MA-60 | Traffic Signages | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 198.36 | 198.36 | 198.36 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MA-70 | Trees | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 9546.3 | 9546.3 | 9546.3 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MA-80 | Lawn | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 11550 | 11550 | 11550 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 24 | 2026-02-23 | 2026-03-26 | 2026-02-23 | 2026-03-26 | 1609.47 | 1609.47 | 1609.47 | 100% | 100% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-Q-PR-SL-CO-MA-10 | Steel Rebar | 14 | 2026-02-23 | 2026-03-10 | 2026-02-23 | 2026-03-10 | 1901-04-20 19:41 | 476.82 | 476.82 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-MA-20 | Concrete | 9 | 2026-03-01 | 2026-03-10 | 2026-03-01 | 2026-03-10 | 1901-06-01 20:24 | 518.85 | 518.85 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-MA-40 | CMU Block | 15 | 2026-03-05 | 2026-03-26 | 2026-03-05 | 2026-03-26 | 1900-05-03 04:48 | 124.2 | 124.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-MA-50 | Concrete Repair & Protection Materials | 15 | 2026-03-05 | 2026-03-26 | 2026-03-05 | 2026-03-26 | 1901-01-06 | 372 | 372 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-MA-30 | Screed | 1 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 1900-04-26 14:24 | 117.6 | 117.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL & FINISHES WORK |  | 17 | 2026-02-25 | 2026-03-16 | 2026-02-25 | 2026-03-16 | 7931.55 | 7931.55 | 7931.55 | 100% | 100% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PG-Q-PR-SL-AR-MA-40 | Cement Plaster | 17 | 2026-02-25 | 2026-03-16 | 2026-02-25 | 2026-03-16 | 1900-08-08 08:53 | 221.37 | 221.37 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MA-50 | Acrylic Paint | 14 | 2026-03-01 | 2026-03-16 | 2026-03-01 | 2026-03-16 | 147.9 | 147.9 | 147.9 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MA-10 | Ceramic tiles | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 571.95 | 571.95 | 571.95 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MA-20 | Anti-slip Granite tiles | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1901-06-18 12:00 | 535.5 | 535.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MA-30 | Epoxy Paint | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 111.18 | 111.18 | 111.18 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MA-60 | Stone Cladding | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1905-01-25 04:48 | 1852.2 | 1852.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MA-70 | Aluminum Plates | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MA-80 | Phenolic Partition | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1903-09-01 09:36 | 1340.4 | 1340.4 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MA-90 | Glass Partition | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 155.4 | 155.4 | 155.4 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MA-100 | Gypsum Boards | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1900-07-06 13:55 | 188.58 | 188.58 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MA-110 | Specialities Materials (Toilet accessories, lockers, logo, etc) | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 2262.87 | 2262.87 | 2262.87 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MA-120 | Waterproofing System Materials | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1901-06-27 04:48 | 544.2 | 544.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 12 | 2026-03-09 | 2026-03-26 | 2026-03-09 | 2026-03-26 | 1901-04-22 21:22 | 478.89 | 478.89 | 100% | 100% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-PR-SL-MT-MA-20 | Galvanized Steel Roof Scupper | 12 | 2026-03-09 | 2026-03-26 | 2026-03-09 | 2026-03-26 | 1900-01-30 07:41 | 31.32 | 31.32 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-MT-MA-30 | Galvanized Steel Cover with frame | 12 | 2026-03-09 | 2026-03-26 | 2026-03-09 | 2026-03-26 | 1900-03-25 17:02 | 85.71 | 85.71 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-MT-MA-10 | Galvanized Steel Ladder | 9 | 2026-03-12 | 2026-03-26 | 2026-03-12 | 2026-03-26 | 1900-12-26 20:38 | 361.86 | 361.86 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
HVAC WORK |  | 20 | 2026-02-28 | 2026-03-26 | 2026-02-28 | 2026-03-26 | 1901-08-28 08:38 | 606.36 | 606.36 | 100% | 100% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-PR-SL-AC-MA-10 | Split Air Conditioning Unit | 20 | 2026-02-28 | 2026-03-26 | 2026-02-28 | 2026-03-26 | 1900-11-04 22:19 | 309.93 | 309.93 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-MA-20 | Air Duct | 16 | 2026-03-04 | 2026-03-26 | 2026-03-04 | 2026-03-26 | 1900-06-04 | 156 | 156 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-MA-30 | Diffusers and Grills | 11 | 2026-03-10 | 2026-03-26 | 2026-03-10 | 2026-03-26 | 1900-03-14 07:26 | 74.31 | 74.31 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-MA-40 | Exhaust fans | 11 | 2026-03-10 | 2026-03-26 | 2026-03-10 | 2026-03-26 | 1900-03-06 02:53 | 66.12 | 66.12 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 3147.03 | 3147.03 | 3147.03 | 100% | 100% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-PR-SL-PB-MA-10 | PPR Pipes & Valves | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 265.2 | 265.2 | 265.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-PB-MA-20 | UPCV Pipes | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1900-11-30 04:34 | 335.19 | 335.19 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-PB-MA-30 | Sanitary Drainage Fixtures | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2546.64 | 2546.64 | 2546.64 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 17 | 2026-03-03 | 2026-03-26 | 2026-03-03 | 2026-03-26 | 13170.12 | 13170.12 | 13170.12 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-PR-SL-IR-MA-10 | Gate Valve including valve box | 17 | 2026-03-03 | 2026-03-26 | 2026-03-03 | 2026-03-26 | 1330.74 | 1330.74 | 1330.74 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-IR-MA-20 | Bulbblers and Spreyers | 12 | 2026-03-09 | 2026-03-26 | 2026-03-09 | 2026-03-26 | 11839.38 | 11839.38 | 11839.38 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1901-02-10 12:29 | 407.52 | 407.52 | 100% | 100% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-Q-PR-SL-EL-MA-10 | Wiring Devices Materials | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1901-02-10 12:29 | 407.52 | 407.52 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE FIGHTING WORK |  | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1900-01-21 17:02 | 22.71 | 22.71 | 100% | 100% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-Q-PR-SL-FF-MA-10 | Fire Extinguishers | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1900-01-21 17:02 | 22.71 | 22.71 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PROCUREMENT |  | 145 | 2026-03-03 | 2026-08-27 | 2026-03-03 |  | 4735135.8 | 4290343.42 | 4735135.8 | 100% | 90.61% | 0 | 0 | 0 |  | 214 | 187 | 27 | 0
LONG LEAD ITEMS |  | 132 | 2026-03-18 | 2026-08-27 | 2026-03-18 |  | 3229967.34 | 2815918.75 | 3229967.34 | 100% | 87.18% | 0 | 0 | 0 |  | 121 | 105 | 16 | 0
PURCHASE ORDER |  | 92 | 2026-03-18 | 2026-07-12 | 2026-03-18 | 2026-09-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 31 | 31 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 5 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-11 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-PR-LL-LS-PO-20 | Benches, Seats (Rectangular & Circular) | 5 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-11 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-PO-30 | Fence, gates and accessories | 5 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-11 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-PO-10 | Bike and Walk Path Materials | 5 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-11 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 87 | 2026-03-26 | 2026-07-09 | 2026-03-26 | 2026-07-09 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-Q-PR-LL-SP-PO-40 | Tartan Floor | 36 | 2026-03-26 | 2026-05-07 | 2026-03-26 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-PO-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc) | 35 | 2026-03-28 | 2026-05-07 | 2026-03-28 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-PO-20 | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc) | 35 | 2026-03-28 | 2026-05-07 | 2026-03-28 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-PO-30 | Padel Playgound Materials (Flooring, fence, tempered glass, etc) | 35 | 2026-03-28 | 2026-05-07 | 2026-03-28 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-PO-50 | Air Dome Materials | 8 | 2026-07-01 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 39 | 2026-03-18 | 2026-05-07 | 2026-03-18 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-Q-PR-LL-CO-PO-10 | Autoclaved Aerated Panel | 39 | 2026-03-18 | 2026-05-07 | 2026-03-18 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 36 | 2026-03-26 | 2026-05-07 | 2026-03-26 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-PR-LL-MT-PO-10 | Metal Doors | 36 | 2026-03-26 | 2026-05-07 | 2026-03-26 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-MT-PO-20 | Curtain Wall | 36 | 2026-03-26 | 2026-05-07 | 2026-03-26 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 34 | 2026-03-29 | 2026-05-07 | 2026-03-29 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-PR-LL-PB-PO-10 | Booster Pump | 34 | 2026-03-29 | 2026-05-07 | 2026-03-29 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-PB-PO-20 | GRP Sectional Panel Water Tanks (4x3x3m) | 30 | 2026-04-02 | 2026-05-07 | 2026-04-02 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 37 | 2026-03-25 | 2026-05-07 | 2026-03-25 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-PR-LL-IR-PO-10 | HDPE Pipes | 37 | 2026-03-25 | 2026-05-07 | 2026-03-25 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-IR-PO-20 | Irrigation Control System | 37 | 2026-03-25 | 2026-05-07 | 2026-03-25 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 48 | 2026-05-13 | 2026-07-12 | 2026-05-13 | 2026-09-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 16 | 16 | 0 | 0
PG-Q-PR-LL-EL-PO-10 | Main Distribution Board(Completed) | 33 | 2026-05-13 | 2026-06-25 | 2026-05-13 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-20 | Power Panels (Pump, Street Light)(Completed) | 33 | 2026-05-13 | 2026-06-25 | 2026-05-13 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-30 | Site Lighting Poles(Completed) | 33 | 2026-05-13 | 2026-06-25 | 2026-05-13 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-40 | Lighting Fixtures(Completed) | 33 | 2026-05-13 | 2026-06-25 | 2026-05-13 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 33 | 2026-05-13 | 2026-06-25 | 2026-05-13 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 33 | 2026-05-13 | 2026-06-25 | 2026-05-13 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-70 | Security and Access Control System Materials(Completed) | 33 | 2026-05-13 | 2026-06-25 | 2026-05-13 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-80 | Fire Alarm System Materials(Completed) | 33 | 2026-05-13 | 2026-06-25 | 2026-05-13 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-10_R | Main Distribution Board(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-08-14 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-20_R | Power Panels (Pump, Street Light)(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-08-14 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-30_R | Site Lighting Poles(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-08-14 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-40_R | Lighting Fixtures(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-07-23 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-08-27 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-08-27 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-70_R | Security and Access Control System Materials(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-08-27 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-80_R | Fire Alarm System Materials(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-08-27 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MANUFACTURE / FABRICATION |  | 81 | 2026-05-05 | 2026-08-11 | 2026-05-05 | 2026-10-04 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 45 | 45 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 65 | 2026-05-05 | 2026-07-23 | 2026-05-05 | 2026-09-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 6 | 6 | 0 | 0
PG-Q-PR-LL-LS-MF-20 | Benches, Seats (Rectangular & Circular)(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-MF-30 | Fence, gates and accessories(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-MF-10 | Bike and Walk Path Materials(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-MF-20_R | Benches, Seats (Rectangular & Circular)(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-07-30 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-MF-30_R | Fence, gates and accessories(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-14 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-MF-10_R | Bike and Walk Path Materials(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-30 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 81 | 2026-05-05 | 2026-08-11 | 2026-05-05 | 2026-09-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 9 | 9 | 0 | 0
PG-Q-PR-LL-SP-MF-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc)(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MF-20 | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc)(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MF-30 | Padel Playgound Materials (Flooring, fence, tempered glass, etc)(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MF-40 | Tartan Floor(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MF-10_R | Football Playground Materials (Flooring, goal post, nets, paints, etc)(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-07-30 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MF-20_R | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc)(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-14 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MF-30_R | Padel Playgound Materials (Flooring, fence, tempered glass, etc)(Remaining) | 15 | 2026-06-25 | 2026-07-12 | 2026-07-30 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MF-40_R | Tartan Floor(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-07-22 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MF-50 | Air Dome Materials | 28 | 2026-07-11 | 2026-08-11 | 2026-08-27 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 55 | 2026-05-05 | 2026-07-12 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-PR-LL-CO-MF-10 | Autoclaved Aerated Panel(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-CO-MF-10_R | Autoclaved Aerated Panel(Remaining) | 15 | 2026-06-25 | 2026-07-12 | 2026-06-01 | 2026-06-04 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 65 | 2026-05-05 | 2026-07-23 | 2026-05-05 | 2026-10-04 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-PR-LL-MT-MF-10 | Metal Doors(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-MT-MF-20 | Curtain Wall(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-MT-MF-10_R | Metal Doors(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-09-06 | 2026-10-02 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-MT-MF-20_R | Curtain Wall(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-09-17 | 2026-10-04 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 65 | 2026-05-05 | 2026-07-23 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-PR-LL-PB-MF-10 | Booster Pump(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-PB-MF-20 | GRP Sectional Panel Water Tanks (4x3x3m)(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-PB-MF-10_R | Booster Pump(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-06-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-PB-MF-20_R | GRP Sectional Panel Water Tanks (4x3x3m)(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-06-06 | 2026-06-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 50 | 2026-05-05 | 2026-07-06 | 2026-05-05 | 2026-09-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-PR-LL-IR-MF-10 | HDPE Pipes(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-IR-MF-20 | Irrigation Control System(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-IR-MF-10_R | HDPE Pipes(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-06-02 | 2026-06-04 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-IR-MF-20_R | Irrigation Control System(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-30 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 74 | 2026-05-12 | 2026-08-10 | 2026-05-12 | 2026-09-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 16 | 16 | 0 | 0
PG-Q-PR-LL-EL-MF-10 | Main Distribution Board(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-20 | Power Panels (Pump, Street Light)(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-30 | Site Lighting Poles(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-40 | Lighting Fixtures(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-70 | Security and Access Control System Materials(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-80 | Fire Alarm System Materials(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-10_R | Main Distribution Board(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-08-14 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-20_R | Power Panels (Pump, Street Light)(Remaining) | 15 | 2026-07-13 | 2026-07-29 | 2026-08-14 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-30_R | Site Lighting Poles(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-08-14 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-40_R | Lighting Fixtures(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-08-14 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-08-27 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-08-27 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-70_R | Security and Access Control System Materials(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-08-27 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-80_R | Fire Alarm System Materials(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-08-27 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
DELIVERY TO SITE |  | 94 | 2026-05-06 | 2026-08-27 | 2026-05-06 |  | 3229967.34 | 2815918.75 | 3229967.34 | 100% | 87.18% | 0 | 0 | 0 |  | 45 | 29 | 16 | 0
EXTERNAL / LANDSCAPE WORK |  | 79 | 2026-05-06 | 2026-08-10 | 2026-05-06 |  | 178309.62 | 176866.75 | 178309.62 | 100% | 99.19% | 0 | 0 | 0 |  | 6 | 5 | 1 | 0
PG-Q-PR-LL-LS-DL-20 | Benches, Seats (Rectangular & Circular)(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 21643.04 | 21643.04 | 21643.04 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-DL-30 | Fence, gates and accessories(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 11381.45 | 11381.45 | 11381.45 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-DL-10 | Bike and Walk Path Materials(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 71685 | 71685 | 71685 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-DL-10_R | Bike and Walk Path Materials(Remaining) | 9 | 2026-07-07 | 2026-07-16 | 2026-08-14 | 2026-09-26 | 47790 | 47790 | 47790 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-DL-20_R | Benches, Seats (Rectangular & Circular)(Remaining) | 15 | 2026-07-25 | 2026-08-10 | 2026-08-14 |  | 14428.69 | 12985.82 | 14428.69 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-LL-LS-DL-30_R | Fence, gates and accessories(Remaining) | 15 | 2026-07-25 | 2026-08-10 | 2026-08-14 | 2026-09-30 | 11381.45 | 11381.45 | 11381.45 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 90 | 2026-05-06 | 2026-08-23 | 2026-05-06 |  | 2461702.86 | 2073940.31 | 2461702.86 | 100% | 84.25% | 0 | 0 | 0 |  | 9 | 4 | 5 | 0
PG-Q-PR-LL-SP-DL-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc)(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 70478.1 | 70478.1 | 70478.1 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-DL-20 | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc)(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 10152 | 10152 | 10152 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-DL-30 | Padel Playgound Materials (Fence, tempered glass, etc)(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 26778.6 | 26778.6 | 26778.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-DL-40 | Tartan Floor(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 235029.6 | 235029.6 | 235029.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-DL-30_R | Padel Playgound Materials (Fence, tempered glass, etc)(Remaining) | 15 | 2026-07-13 | 2026-07-29 | 2026-08-14 |  | 26778.6 | 25439.67 | 26778.6 | 100% | 95% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-LL-SP-DL-10_R | Football Playground Materials (Flooring, goal post, nets, paints, etc)(Remaining) | 15 | 2026-07-25 | 2026-08-10 | 2026-08-14 |  | 46985.4 | 44636.13 | 46985.4 | 100% | 95% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-LL-SP-DL-20_R | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc)(Remaining) | 15 | 2026-07-25 | 2026-08-10 | 2026-08-14 |  | 10152 | 9644.4 | 10152 | 100% | 95% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-LL-SP-DL-40_R | Tartan Floor(Remaining) | 15 | 2026-07-25 | 2026-08-10 | 2026-08-14 |  | 156686.4 | 148852.08 | 156686.4 | 100% | 95% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-LL-SP-DL-50 | Air Dome Materials | 10 | 2026-08-12 | 2026-08-23 | 2026-10-18 |  | 1878662.16 | 1502929.73 | 1878662.16 | 100% | 80% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
CONCRETE WORK |  | 64 | 2026-05-06 | 2026-07-23 | 2026-05-06 | 2026-07-05 | 12757.5 | 12757.5 | 12757.5 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-PR-LL-CO-DL-10 | Autoclaved Aerated Panel(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 7654.5 | 7654.5 | 7654.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-CO-DL-10_R | Autoclaved Aerated Panel(Remaining) | 10 | 2026-07-13 | 2026-07-23 | 2026-07-04 | 2026-07-05 | 5103 | 5103 | 5103 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 79 | 2026-05-06 | 2026-08-10 | 2026-05-06 |  | 8003.07 | 6289.25 | 8003.07 | 100% | 78.59% | 0 | 0 | 0 |  | 4 | 3 | 1 | 0
PG-Q-PR-LL-MT-DL-10 | Metal Doors(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 573.89 | 573.89 | 573.89 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-MT-DL-20 | Curtain Wall(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 1909-05-19 15:36 | 1909-05-19 15:36 | 1909-05-19 15:36 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-MT-DL-10_R | Metal Doors(Remaining) | 15 | 2026-07-25 | 2026-08-10 | 2026-08-27 | 2026-10-02 | 573.89 | 573.89 | 573.89 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-MT-DL-20_R | Curtain Wall(Remaining) | 15 | 2026-07-25 | 2026-08-10 | 2026-10-05 |  | 1909-05-19 15:36 | 1904-09-08 19:55 | 3427.65 | 100% | 50% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PLUMBING WORK |  | 79 | 2026-05-06 | 2026-08-10 | 2026-05-06 | 2026-10-13 | 31985.55 | 31985.55 | 31985.55 | 100% | 100% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-PR-LL-PB-DL-10 | Booster Pump(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 8182.35 | 8182.35 | 8182.35 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-PB-DL-20 | GRP Sectional Panel Water Tanks (4x3x3m)(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 7810.43 | 7810.43 | 7810.43 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-PB-DL-10_R | Booster Pump(Remaining) | 15 | 2026-07-25 | 2026-08-10 | 2026-08-20 | 2026-09-30 | 8182.35 | 8182.35 | 8182.35 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-PB-DL-20_R | GRP Sectional Panel Water Tanks (4x3x3m)(Remaining) | 15 | 2026-07-25 | 2026-08-10 | 2026-08-14 | 2026-10-13 | 7810.43 | 7810.43 | 7810.43 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 57 | 2026-05-06 | 2026-07-15 | 2026-05-06 |  | 220380.75 | 219357.96 | 220380.75 | 100% | 99.54% | 0 | 0 | 0 |  | 4 | 3 | 1 | 0
PG-Q-PR-LL-IR-DL-10 | HDPE Pipes(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 89734.5 | 89734.5 | 89734.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-IR-DL-20 | Irrigation Control System(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 20455.88 | 20455.88 | 20455.88 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-IR-DL-10_R | HDPE Pipes(Remaining) | 7 | 2026-07-07 | 2026-07-14 | 2026-08-14 | 2026-08-27 | 89734.5 | 89734.5 | 89734.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-IR-DL-20_R | Irrigation Control System(Remaining) | 8 | 2026-07-07 | 2026-07-15 | 2026-08-20 |  | 20455.88 | 19433.08 | 20455.88 | 100% | 95% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
ELECTRICAL WORK |  | 88 | 2026-05-13 | 2026-08-27 | 2026-05-13 |  | 316827.99 | 294721.44 | 316827.99 | 100% | 93.02% | 0 | 0 | 0 |  | 16 | 8 | 8 | 0
PG-Q-PR-LL-EL-DL-10 | Main Distribution Board(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 1338.93 | 1338.93 | 1338.93 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-DL-20 | Power Panels (Pump, Street Light)(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 1785.24 | 1785.24 | 1785.24 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-DL-30 | Site Lighting Poles(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 78323.76 | 78323.76 | 78323.76 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-DL-40 | Lighting Fixtures(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 3463.64 | 3463.64 | 3463.64 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-DL-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 2711.31 | 2711.31 | 2711.31 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-DL-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 2644.33 | 2644.33 | 2644.33 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-DL-70 | Security and Access Control System Materials(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 3347.73 | 3347.73 | 3347.73 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-DL-80 | Fire Alarm System Materials(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 2147.55 | 2147.55 | 2147.55 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-DL-20_R | Power Panels (Pump, Street Light)(Remaining) | 10 | 2026-07-30 | 2026-08-10 | 2026-08-14 |  | 1785.24 | 1606.72 | 1785.24 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-LL-EL-DL-10_R | Main Distribution Board(Remaining) | 15 | 2026-08-11 | 2026-08-27 | 2026-08-14 |  | 3124.17 | 2811.75 | 3124.17 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-LL-EL-DL-30_R | Site Lighting Poles(Remaining) | 15 | 2026-08-11 | 2026-08-27 | 2026-08-14 |  | 182755.44 | 164479.9 | 182755.44 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-LL-EL-DL-40_R | Lighting Fixtures(Remaining) | 15 | 2026-08-11 | 2026-08-27 | 2026-08-14 |  | 1922-02-14 19:55 | 1919-11-29 15:36 | 8081.83 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-LL-EL-DL-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 15 | 2026-08-11 | 2026-08-27 | 2026-08-27 |  | 6326.4 | 5693.76 | 6326.4 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-LL-EL-DL-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 15 | 2026-08-11 | 2026-08-27 | 2026-08-27 |  | 6170.09 | 1915-03-15 01:55 | 6170.09 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-LL-EL-DL-70_R | Security and Access Control System Materials(Remaining) | 15 | 2026-08-11 | 2026-08-27 | 2026-08-27 |  | 7811.37 | 7030.23 | 7811.37 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-LL-EL-DL-80_R | Fire Alarm System Materials(Remaining) | 15 | 2026-08-11 | 2026-08-27 | 2026-08-27 |  | 5010.96 | 1912-05-05 20:38 | 5010.96 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
SHORT LEAD ITEMS |  | 105 | 2026-03-03 | 2026-07-12 | 2026-03-03 |  | 1505168.46 | 1474424.67 | 1505168.46 | 100% | 97.96% | 0 | 0 | 0 |  | 93 | 82 | 11 | 0
MATERIAL SUBMITTALS |  | 0 |  |  |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
PURCHASE ORDER |  | 64 | 2026-03-03 | 2026-05-21 | 2026-03-03 | 2026-05-20 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 39 | 39 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 57 | 2026-03-03 | 2026-05-13 | 2026-03-03 | 2026-05-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 8 | 8 | 0 | 0
PG-Q-PR-SL-LS-PO-10 | Backfilling Materials | 40 | 2026-03-03 | 2026-04-23 | 2026-03-03 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-PO-30 | Compacted Natural Ground Soil | 37 | 2026-03-07 | 2026-04-23 | 2026-03-07 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-PO-40 | Curb Stone | 28 | 2026-03-29 | 2026-04-30 | 2026-03-29 | 2026-04-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-PO-20 | Interlock tiles | 25 | 2026-04-01 | 2026-04-30 | 2026-04-01 | 2026-04-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-PO-50 | Thermoplastic pavement road marking | 2 | 2026-05-11 | 2026-05-13 | 2026-05-11 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-PO-60 | Traffic Signages | 2 | 2026-05-11 | 2026-05-13 | 2026-05-11 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-PO-70 | Trees | 2 | 2026-05-11 | 2026-05-13 | 2026-05-11 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-PO-80 | Lawn | 2 | 2026-05-11 | 2026-05-13 | 2026-05-11 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 39 | 2026-03-04 | 2026-04-23 | 2026-03-04 | 2026-04-22 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-Q-PR-SL-CO-PO-10 | Steel Rebar | 39 | 2026-03-04 | 2026-04-23 | 2026-03-04 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-PO-20 | Concrete | 34 | 2026-03-10 | 2026-04-23 | 2026-03-10 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-PO-40 | CMU Block | 30 | 2026-03-15 | 2026-04-23 | 2026-03-15 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-PO-50 | Concrete Repair & Protection Materials | 30 | 2026-03-15 | 2026-04-23 | 2026-03-15 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-PO-30 | Screed | 19 | 2026-04-01 | 2026-04-23 | 2026-04-01 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL & FINISHES WORK |  | 48 | 2026-03-07 | 2026-05-06 | 2026-03-07 | 2026-05-05 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PG-Q-PR-SL-AR-PO-40 | Cement Plaster | 48 | 2026-03-07 | 2026-05-06 | 2026-03-07 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-PO-50 | Acrylic Paint | 45 | 2026-03-10 | 2026-05-06 | 2026-03-10 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-PO-80 | Phenolic Partition | 40 | 2026-03-16 | 2026-05-06 | 2026-03-16 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-PO-90 | Glass Partition | 40 | 2026-03-16 | 2026-05-06 | 2026-03-16 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-PO-10 | Ceramic tiles | 32 | 2026-03-30 | 2026-05-06 | 2026-03-30 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-PO-20 | Anti-slip Granite tiles | 32 | 2026-03-30 | 2026-05-06 | 2026-03-30 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-PO-30 | Epoxy Paint | 32 | 2026-03-30 | 2026-05-06 | 2026-03-30 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-PO-100 | Gypsum Boards | 32 | 2026-03-30 | 2026-05-06 | 2026-03-30 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-PO-110 | Specialities Materials (Toilet accessories, lockers, logo, etc) | 32 | 2026-03-30 | 2026-05-06 | 2026-03-30 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-PO-120 | Waterproofing System Materials | 32 | 2026-03-30 | 2026-05-06 | 2026-03-30 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-PO-60 | Stone Cladding | 30 | 2026-04-01 | 2026-05-06 | 2026-04-01 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-PO-70 | Aluminum Plates | 30 | 2026-04-01 | 2026-05-06 | 2026-04-01 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 36 | 2026-03-25 | 2026-05-06 | 2026-03-25 | 2026-05-05 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-PR-SL-MT-PO-10 | Galvanized Steel Ladder | 36 | 2026-03-25 | 2026-05-06 | 2026-03-25 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-MT-PO-20 | Galvanized Steel Roof Scupper | 2 | 2026-05-04 | 2026-05-06 | 2026-05-04 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-MT-PO-30 | Galvanized Steel Cover with frame | 2 | 2026-05-04 | 2026-05-06 | 2026-05-04 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
HVAC WORK |  | 46 | 2026-03-09 | 2026-05-06 | 2026-03-09 | 2026-05-05 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-PR-SL-AC-PO-10 | Split Air Conditioning Unit | 46 | 2026-03-09 | 2026-05-06 | 2026-03-09 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-PO-20 | Air Duct | 42 | 2026-03-14 | 2026-05-06 | 2026-03-14 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-PO-30 | Diffusers and Grills | 34 | 2026-03-28 | 2026-05-06 | 2026-03-28 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-PO-40 | Exhaust fans | 27 | 2026-04-05 | 2026-05-06 | 2026-04-05 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 33 | 2026-03-29 | 2026-05-06 | 2026-03-29 | 2026-05-05 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-PR-SL-PB-PO-10 | PPR Pipes & Valves | 33 | 2026-03-29 | 2026-05-06 | 2026-03-29 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-PB-PO-20 | UPCV Pipes | 33 | 2026-03-29 | 2026-05-06 | 2026-03-29 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-PB-PO-30 | Sanitary Drainage Fixtures | 33 | 2026-03-29 | 2026-05-06 | 2026-03-29 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 43 | 2026-03-12 | 2026-05-06 | 2026-03-12 | 2026-05-05 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-PR-SL-IR-PO-10 | Gate Valve including valve box | 43 | 2026-03-12 | 2026-05-06 | 2026-03-12 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-IR-PO-20 | Bulbblers and Spreyers | 38 | 2026-03-18 | 2026-05-06 | 2026-03-18 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 8 | 2026-05-12 | 2026-05-21 | 2026-05-12 | 2026-05-20 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-Q-PR-SL-EL-PO-10 | Wiring Devices Materials | 8 | 2026-05-12 | 2026-05-21 | 2026-05-12 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE FIGHTING WORK |  | 30 | 2026-04-01 | 2026-05-06 | 2026-04-01 | 2026-05-05 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-Q-PR-SL-FF-PO-10 | Fire Extinguishers | 30 | 2026-04-01 | 2026-05-06 | 2026-04-01 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
DELIVERY TO SITE |  | 103 | 2026-03-05 | 2026-07-12 | 2026-03-05 |  | 1505168.46 | 1474424.67 | 1505168.46 | 100% | 97.96% | 0 | 0 | 0 |  | 54 | 43 | 11 | 0
EXTERNAL / LANDSCAPE WORK |  | 100 | 2026-03-05 | 2026-07-08 | 2026-03-05 |  | 1258805.61 | 1243095 | 1258805.61 | 100% | 98.75% | 0 | 0 | 0 |  | 12 | 8 | 4 | 0
PG-Q-PR-SL-LS-DL-10 | Backfilling Materials | 39 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-04-24 | 328050 | 328050 | 328050 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-DL-30 | Compacted Natural Ground Soil | 12 | 2026-04-30 | 2026-05-13 | 2026-04-30 | 2026-05-13 | 77220 | 77220 | 77220 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-DL-20 | Interlock tiles | 12 | 2026-04-30 | 2026-05-13 | 2026-04-30 | 2026-05-13 | 268488 | 268488 | 268488 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-DL-40 | Curb Stone | 12 | 2026-04-30 | 2026-05-13 | 2026-04-30 | 2026-05-13 | 388665 | 388665 | 388665 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-DL-50 | Thermoplastic pavement road marking(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 2838.4 | 2838.4 | 2838.4 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-DL-60 | Traffic Signages(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 1071.14 | 1071.14 | 1071.14 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-DL-70 | Trees(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 51550.02 | 51550.02 | 51550.02 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-DL-80 | Lawn(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 62370 | 62370 | 62370 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-DL-50_R | Thermoplastic pavement road marking(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-08-27 |  | 1892.27 | 1904-02-21 19:26 | 1892.27 | 100% | 80% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-SL-LS-DL-60_R | Traffic Signages(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-08-27 |  | 714.1 | 571.28 | 714.1 | 100% | 80% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-SL-LS-DL-70_R | Trees(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-08-27 |  | 34366.68 | 1975-04-09 08:10 | 34366.68 | 100% | 80% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-SL-LS-DL-80_R | Lawn(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-08-27 |  | 41580 | 33264 | 41580 | 100% | 80% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
CONCRETE WORK |  | 50 | 2026-03-12 | 2026-05-13 | 2026-03-12 | 2026-05-13 | 14485.23 | 14485.23 | 14485.23 | 100% | 100% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-Q-PR-SL-CO-DL-20 | Concrete | 50 | 2026-03-12 | 2026-05-13 | 2026-03-12 | 2026-05-13 | 4669.65 | 4669.65 | 4669.65 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-DL-10 | Steel Rebar | 18 | 2026-04-23 | 2026-05-13 | 2026-04-23 | 2026-05-13 | 4291.38 | 4291.38 | 4291.38 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-DL-30 | Screed | 18 | 2026-04-23 | 2026-05-13 | 2026-04-23 | 2026-05-13 | 1058.4 | 1058.4 | 1058.4 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-DL-40 | CMU Block | 18 | 2026-04-23 | 2026-05-13 | 2026-04-23 | 2026-05-13 | 1117.8 | 1117.8 | 1117.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-DL-50 | Concrete Repair & Protection Materials | 18 | 2026-04-23 | 2026-05-13 | 2026-04-23 | 2026-05-13 | 3348 | 3348 | 3348 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL & FINISHES WORK |  | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 71383.95 | 71383.95 | 71383.95 | 100% | 100% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PG-Q-PR-SL-AR-DL-10 | Ceramic tiles | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 5147.55 | 5147.55 | 5147.55 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-DL-20 | Anti-slip Granite tiles | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 4819.5 | 4819.5 | 4819.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-DL-30 | Epoxy Paint | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 1000.62 | 1000.62 | 1000.62 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-DL-40 | Cement Plaster | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 1992.33 | 1992.33 | 1992.33 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-DL-50 | Acrylic Paint | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 1331.1 | 1331.1 | 1331.1 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-DL-60 | Stone Cladding | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 16669.8 | 16669.8 | 16669.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-DL-70 | Aluminum Plates | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-DL-80 | Phenolic Partition | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 12063.6 | 12063.6 | 12063.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-DL-90 | Glass Partition | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 1398.6 | 1398.6 | 1398.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-DL-100 | Gypsum Boards | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 1697.22 | 1697.22 | 1697.22 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-DL-110 | Specialities Materials (Toilet accessories, lockers, logo, etc) | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 20365.83 | 20365.83 | 20365.83 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-DL-120 | Waterproofing System Materials | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 4897.8 | 4897.8 | 4897.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 51 | 2026-05-06 | 2026-07-08 | 2026-05-06 |  | 4310.01 | 3965.21 | 4310.01 | 100% | 92% | 0 | 0 | 0 |  | 6 | 3 | 3 | 0
PG-Q-PR-SL-MT-DL-10 | Galvanized Steel Ladder(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 1905-05-07 00:58 | 1905-05-07 00:58 | 1954.04 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-MT-DL-20 | Galvanized Steel Roof Scupper(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 1900-06-17 03:07 | 169.13 | 169.13 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-MT-DL-30 | Galvanized Steel Cover with frame(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 462.83 | 462.83 | 462.83 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-MT-DL-10_R | Galvanized Steel Ladder(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-09-26 |  | 1903-07-25 16:48 | 1042.16 | 1302.7 | 100% | 80% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-SL-MT-DL-20_R | Galvanized Steel Roof Scupper(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-09-26 |  | 1900-04-21 18:00 | 1900-03-30 04:48 | 1900-04-21 18:00 | 100% | 80% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-SL-MT-DL-30_R | Galvanized Steel Cover with frame(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-09-26 |  | 308.56 | 246.84 | 308.56 | 100% | 80% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
HVAC WORK |  | 51 | 2026-05-06 | 2026-07-08 | 2026-05-06 | 2026-10-02 | 5457.24 | 5457.24 | 5457.24 | 100% | 100% | 0 | 0 | 0 |  | 8 | 8 | 0 | 0
PG-Q-PR-SL-AC-DL-10 | Split Air Conditioning Unit(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 1904-07-30 14:53 | 1904-07-30 14:53 | 1673.62 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-DL-20 | Air Duct(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 1902-04-21 09:36 | 842.4 | 842.4 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-DL-30 | Diffusers and Grills(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 1901-02-04 06:29 | 1901-02-04 06:29 | 1901-02-04 06:29 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-DL-40 | Exhaust fans(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 357.05 | 357.05 | 357.05 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-DL-10_R | Split Air Conditioning Unit(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-08-27 | 2026-10-02 | 1903-01-19 18:00 | 1903-01-19 18:00 | 1903-01-19 18:00 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-DL-20_R | Air Duct(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-08-27 | 2026-10-02 | 1901-07-14 14:24 | 561.6 | 561.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-DL-30_R | Diffusers and Grills(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-08-27 | 2026-10-02 | 1900-09-23 12:29 | 1900-09-23 12:29 | 1900-09-23 12:29 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-DL-40_R | Exhaust fans(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-08-27 | 2026-10-02 | 238.03 | 238.03 | 238.03 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 28323.27 | 28323.27 | 28323.27 | 100% | 100% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-PR-SL-PB-DL-10 | PPR Pipes & Valves | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 2386.8 | 2386.8 | 2386.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-PB-DL-20 | UPCV Pipes | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 3016.71 | 3016.71 | 3016.71 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-PB-DL-30 | Sanitary Drainage Fixtures | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 22919.76 | 22919.76 | 22919.76 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 51 | 2026-05-06 | 2026-07-08 | 2026-05-06 |  | 118531.08 | 104307.35 | 118531.08 | 100% | 88% | 0 | 0 | 0 |  | 4 | 2 | 2 | 0
PG-Q-PR-SL-IR-DL-10 | Gate Valve including valve box(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 4790.66 | 4790.66 | 4790.66 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-IR-DL-20 | Bulbblers and Spreyers(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 42621.77 | 42621.77 | 42621.77 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-IR-DL-10_R | Gate Valve including valve box(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-08-14 |  | 7186 | 5748.8 | 7186 | 100% | 80% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-Q-PR-SL-IR-DL-20_R | Bulbblers and Spreyers(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-08-20 |  | 63932.65 | 51146.12 | 63932.65 | 100% | 80% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
ELECTRICAL WORK |  | 50 | 2026-05-11 | 2026-07-12 | 2026-05-11 |  | 3667.68 | 3227.56 | 3667.68 | 100% | 88% | 0 | 0 | 0 |  | 2 | 1 | 1 | 0
PG-Q-PR-SL-EL-DL-10 | Wiring Devices Materials(Completed) | 35 | 2026-05-11 | 2026-06-24 | 2026-05-11 | 2026-06-24 | 1467.07 | 1467.07 | 1467.07 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-EL-DL-10_R | Wiring Devices Materials(Remaining) | 15 | 2026-06-25 | 2026-07-12 | 2026-09-26 |  | 2200.61 | 1760.49 | 2200.61 | 100% | 80% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
FIRE FIGHTING WORK |  | 51 | 2026-05-06 | 2026-07-08 | 2026-05-06 |  | 1900-07-22 09:22 | 179.86 | 204.39 | 100% | 88% | 0 | 0 | 0 |  | 2 | 1 | 1 | 0
PG-Q-PR-SL-FF-DL-10 | Fire Extinguishers(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 1900-03-21 18:14 | 1900-03-21 18:14 | 1900-03-21 18:14 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-FF-DL-10_R | Fire Extinguishers(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-09-26 |  | 122.63 | 98.11 | 122.63 | 100% | 80% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
CONSTRUCTION STAGE |  | 225 | 2026-03-24 | 2026-12-16 | 2026-03-24 |  | 8948881.52 | 7197982.38 | 10522524 | 85.05% | 68.41% | 8112 | 6809 | 6065 |  | 171 | 95 | 53 | 23
PLAYGROUND AND LANDSCAPING WORKS |  | 225 | 2026-03-24 | 2026-12-16 | 2026-03-24 |  | 5378139.13 | 5433056.07 | 6019638.42 | 89.34% | 90.26% | 5288 | 4345 | 4048 |  | 112 | 58 | 43 | 11
CUT AND FILL |  | 38 | 2026-03-24 | 2026-05-06 | 2026-03-24 | 2026-05-06 | 900600 | 900600 | 900600 | 100% | 100% | 376 | 376 | 376 |  | 3 | 3 | 0 | 0
PG-Q-CON-EX-CF-10 | Existing Soil Excavation Works | 36 | 2026-03-24 | 2026-05-04 | 2026-03-24 | 2026-05-04 | 233280 | 233280 | 233280 | 100% | 100% | 172 | 172 | 172 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-CF-20 | Soil Replacement Works | 27 | 2026-04-05 | 2026-05-05 | 2026-04-05 | 2026-05-05 | 171600 | 171600 | 171600 | 100% | 100% | 100 | 100 | 100 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-CF-30 | Levelling & Backfilling Works | 18 | 2026-04-16 | 2026-05-06 | 2026-04-16 | 2026-05-06 | 495720 | 495720 | 495720 | 100% | 100% | 104 | 104 | 104 | No | 1 | 1 | 0 | 0
PLAYGROUND WORKS |  | 189 | 2026-04-21 | 2026-12-02 | 2026-04-21 |  | 1158012.41 | 1224704.75 | 1318471.2 | 87.83% | 92.89% | 1896 | 1636 | 1605 |  | 35 | 20 | 12 | 3
FOOTBALL PLAYGROUND WORKS |  | 176 | 2026-04-21 | 2026-11-17 | 2026-04-21 |  | 578454.9 | 572933.63 | 611282.16 | 94.63% | 93.73% | 864 | 737 | 750 |  | 13 | 8 | 4 | 1
PG-Q-CON-EX-FB-10 | Subgrade Preparation and Compaction | 14 | 2026-04-21 | 2026-05-06 | 2026-04-21 | 2026-05-06 | 23667 | 23667 | 23667 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-FB-20 | Sub-Base Laying and Compaction | 10 | 2026-04-26 | 2026-05-06 | 2026-04-26 | 2026-05-06 | 23667 | 23667 | 23667 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-FB-30 | Base Course Laying and Compaction | 33 | 2026-05-06 | 2026-06-17 | 2026-05-06 | 2026-06-17 | 23667 | 23667 | 23667 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-FB-40 | Tartan flooring(Completed) | 7 | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 104457.6 | 104457.6 | 104457.6 | 100% | 100% | 19 | 19 | 19 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-FB-80 | Fine Grading & Leveling | 10 | 2026-06-25 | 2026-07-06 | 2026-07-09 | 2026-07-11 | 23667 | 23667 | 23667 | 100% | 100% | 76 | 76 | 76 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-FB-70 | Topsoil Placement | 12 | 2026-07-07 | 2026-07-20 | 2026-07-12 | 2026-08-14 | 23667 | 23667 | 23667 | 100% | 100% | 84 | 84 | 84 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-FB-50 | Goal Post Foundation | 25 | 2026-07-21 | 2026-08-18 | 2026-08-06 | 2026-08-27 | 35500.5 | 35500.5 | 35500.5 | 100% | 100% | 100 | 100 | 100 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-FB-120 | Installation of Lighting System | 12 | 2026-08-19 | 2026-09-01 | 2026-08-20 |  | 24360 | 21924 | 24360 | 100% | 90% | 32 | 32 | 29 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-FB-90 | Turfing / Seeding Works | 10 | 2026-09-02 | 2026-09-13 | 2026-08-14 |  | 1964-10-17 | 18933.6 | 23667 | 100% | 80% | 48 | 48 | 38 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-FB-40_R | Tartan flooring(Remaining) | 15 | 2026-09-14 | 2026-10-01 | 2026-07-12 | 2026-08-14 | 243734.4 | 243734.4 | 243734.4 | 100% | 100% | 45 | 45 | 45 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-FB-60 | Goal Post Installation & Alignment | 15 | 2026-10-03 | 2026-10-19 | 2026-08-27 |  | 28400.4 | 28400.4 | 35500.5 | 80% | 80% | 56 | 45 | 45 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-FB-110 | Install Playground Benches | 17 | 2026-10-20 | 2026-11-08 | 2026-08-27 |  | 0 | 1648.13 | 2060.16 | 0% | 80% | 32 | 0 | 26 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-FB-100 | Markings and Signages | 8 | 2026-11-09 | 2026-11-17 |  |  | 0 | 0 | 23667 | 0% | 0% | 84 | 0 | 0 | No | 1 | 0 | 0 | 1
BASKETBALL PLAYGROUND WORKS |  | 168 | 2026-04-30 | 2026-11-17 | 2026-04-30 |  | 372458.96 | 372910.46 | 381705.12 | 97.58% | 97.7% | 608 | 552 | 574 |  | 11 | 7 | 4 | 0
PG-Q-CON-EX-BB-10 | Subgrade Preparation and Compaction | 6 | 2026-04-30 | 2026-05-06 | 2026-04-30 | 2026-05-06 | 15472.08 | 15472.08 | 15472.08 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-BB-20 | Sub-Base Laying and Compaction | 1 | 2026-05-05 | 2026-05-06 | 2026-05-05 | 2026-05-06 | 15472.08 | 15472.08 | 15472.08 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-BB-30 | Base Course Laying and Compaction | 33 | 2026-05-06 | 2026-06-17 | 2026-05-06 | 2026-06-17 | 15472.08 | 15472.08 | 15472.08 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-BB-70 | Floor Surface Curing(Completed) | 7 | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 4641.62 | 4641.62 | 4641.62 | 100% | 100% | 7 | 7 | 7 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-BB-50 | Basketball Pole Foundation | 25 | 2026-06-25 | 2026-07-23 | 2026-08-06 | 2026-08-13 | 15472.08 | 15472.08 | 15472.08 | 100% | 100% | 100 | 100 | 100 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-BB-70_R | Floor Surface Curing(Remaining) | 15 | 2026-07-25 | 2026-08-10 | 2026-08-06 | 2026-08-14 | 10830.46 | 10830.46 | 10830.46 | 100% | 100% | 17 | 17 | 17 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-BB-40 | Tartan flooring | 17 | 2026-08-11 | 2026-08-30 | 2026-07-30 | 2026-08-14 | 261144 | 261144 | 261144 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-BB-80 | Court Line Marking | 15 | 2026-08-31 | 2026-09-16 | 2026-08-20 |  | 1935-11-03 18:14 | 10473.41 | 13091.76 | 100% | 80% | 28 | 28 | 22 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-BB-60 | Basketball Pole Installation & Alignment | 17 | 2026-09-17 | 2026-10-07 | 2026-08-20 |  | 1942-05-11 01:55 | 12377.66 | 15472.08 | 100% | 80% | 56 | 56 | 45 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-BB-90 | Backboard & Hoop Installation | 17 | 2026-10-08 | 2026-10-27 | 2026-10-01 |  | 1914-10-03 17:17 | 1928-09-02 09:50 | 13091.76 | 41.18% | 80% | 40 | 16 | 32 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-BB-100 | Install Playground Benches | 18 | 2026-10-28 | 2026-11-17 | 2026-09-27 |  | 0 | 1081.58 | 1545.12 | 0% | 70% | 32 | 0 | 22 | No | 1 | 0 | 1 | 0
PADEL PLAYGROUND WORKS |  | 176 | 2026-05-06 | 2026-12-02 | 2026-05-06 |  | 207098.55 | 278860.66 | 325483.92 | 63.63% | 85.68% | 424 | 346 | 282 |  | 11 | 5 | 4 | 2
PG-Q-CON-EX-PD-10 | Excavation For Fence Footing(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 16243.2 | 16243.2 | 16243.2 | 100% | 100% | 54 | 54 | 54 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-PD-20 | RC Foundations For Fence(Completed) | 27 | 2026-05-20 | 2026-06-24 | 2026-05-20 | 2026-06-24 | 1767.48 | 1767.48 | 1767.48 | 100% | 100% | 24 | 24 | 24 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-PD-30 | Tartan Flooring Layers(Completed) | 7 | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 130572 | 130572 | 130572 | 100% | 100% | 20 | 20 | 20 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-PD-10_R | Excavation For Fence Footing(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-06 | 2026-08-14 | 1804.8 | 1804.8 | 1804.8 | 100% | 100% | 6 | 6 | 6 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-PD-20_R | RC Foundations For Fence(Remaining) | 20 | 2026-07-04 | 2026-07-26 | 2026-08-07 | 2026-08-27 | 1767.48 | 1767.48 | 1767.48 | 100% | 100% | 24 | 24 | 24 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-PD-40 | Steel Structure & Fence Supports Installation | 18 | 2026-08-11 | 2026-08-31 | 2026-08-20 |  | 3534.96 | 2827.97 | 3534.96 | 100% | 80% | 56 | 56 | 45 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-PD-60 | Chain Link Fence & Gates Installation | 16 | 2026-09-01 | 2026-09-19 | 2026-08-20 |  | 1914-07-07 10:34 | 1911-08-11 22:48 | 5302.44 | 100% | 80% | 72 | 72 | 58 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-PD-50 | Tempered Glass Installation | 17 | 2026-09-20 | 2026-10-10 | 2026-10-12 |  | 1914-07-07 10:34 | 2120.98 | 5302.44 | 100% | 40% | 84 | 84 | 34 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-PD-30_R | Tartan Flooring Layers(Remaining) | 16 | 2026-10-11 | 2026-10-28 | 2026-08-06 |  | 2011-09-17 18:00 | 2221-09-27 19:12 | 130572 | 31.25% | 90% | 20 | 6 | 18 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-PD-70 | Court Accessories Installation | 15 | 2026-10-29 | 2026-11-15 |  |  | 0 | 0 | 27072 | 0% | 0% | 32 | 0 | 0 | No | 1 | 0 | 0 | 1
PG-Q-CON-EX-PD-80 | Install Playground Benches | 15 | 2026-11-16 | 2026-12-02 |  |  | 0 | 0 | 1545.12 | 0% | 0% | 32 | 0 | 0 | No | 1 | 0 | 0 | 1
GENERAL SITE WORKS |  | 205 | 2026-04-16 | 2026-12-16 | 2026-04-16 |  | 1503676.62 | 1381839.58 | 1617941.82 | 92.94% | 85.41% | 1996 | 1498 | 1201 |  | 48 | 15 | 26 | 7
FENCE WORKS |  | 125 | 2026-04-16 | 2026-09-13 | 2026-04-16 |  | 32909.4 | 25998.43 | 32909.4 | 100% | 79% | 336 | 336 | 270 |  | 5 | 2 | 3 | 0
PG-Q-CON-EX-GN-FN-10 | Excavation for fence foundation | 3 | 2026-04-16 | 2026-04-19 | 2026-04-16 | 2026-04-19 | 6581.88 | 6581.88 | 6581.88 | 100% | 100% | 92 | 92 | 92 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-FN-20 | Concrete Foundations for Fence | 10 | 2026-07-21 | 2026-08-01 | 2026-08-13 | 2026-08-20 | 1918-01-06 21:07 | 6581.88 | 6581.88 | 100% | 100% | 68 | 68 | 68 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-FN-30 | Installation of Galvanized Steel Posts & Framing | 12 | 2026-08-02 | 2026-08-15 | 2026-08-20 |  | 1918-01-06 21:07 | 1915-04-25 14:24 | 6581.88 | 100% | 85% | 56 | 56 | 48 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-FN-40 | Fixing of Chain Link Mesh, Tensioning & Bracing | 15 | 2026-08-16 | 2026-09-01 | 2026-09-27 |  | 6581.88 | 1912-08-11 07:41 | 6581.88 | 100% | 70% | 48 | 48 | 34 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-FN-50 | Installation of Gates | 10 | 2026-09-02 | 2026-09-13 | 2026-10-14 |  | 6581.88 | 2632.75 | 6581.88 | 100% | 40% | 72 | 72 | 29 | No | 1 | 0 | 1 | 0
MECHANICAL WORK |  | 81 | 2026-05-12 | 2026-08-18 | 2026-05-12 |  | 780707.34 | 707170.08 | 780707.34 | 100% | 90.58% | 476 | 476 | 328 |  | 14 | 6 | 4 | 4
STORM WATER AND UTILITY WORK |  | 79 | 2026-05-12 | 2026-08-16 | 2026-05-12 |  | 27252 | 19573.2 | 27252 | 100% | 71.82% | 300 | 300 | 197 |  | 9 | 4 | 2 | 3
PG-Q-CON-EX-GN-M-10 | Excavation | 2 | 2026-05-12 | 2026-05-13 | 2026-05-12 | 2026-05-13 | 3096 | 3096 | 3096 | 100% | 100% | 92 | 92 | 92 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-M-20 | Bedding preparation & level control(Completed) | 27 | 2026-05-20 | 2026-06-24 | 2026-05-20 | 2026-06-24 | 1651.2 | 1651.2 | 1651.2 | 100% | 100% | 26 | 26 | 26 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-M-30 | Manhole Installation(Completed) | 7 | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 1032 | 1032 | 1032 | 100% | 100% | 10 | 10 | 10 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-M-20_R | Bedding preparation & level control(Remaining) | 8 | 2026-06-25 | 2026-07-04 | 2026-08-07 | 2026-08-27 | 412.8 | 412.8 | 412.8 | 100% | 100% | 6 | 6 | 6 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-M-30_R | Manhole Installation(Remaining) | 6 | 2026-07-05 | 2026-07-11 | 2026-08-20 |  | 4128 | 3715.2 | 4128 | 100% | 90% | 38 | 38 | 35 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-M-40 | 150 mm uPVC pipe laying & jointing | 6 | 2026-07-12 | 2026-07-18 | 2026-08-20 |  | 10740 | 1926-06-18 | 10740 | 100% | 90% | 32 | 32 | 29 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-M-50 | Concrete Encasement | 7 | 2026-07-19 | 2026-07-26 |  |  | 2064 | 0 | 2064 | 100% | 0% | 24 | 24 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-GN-M-60 | Backfilling & Compaction | 6 | 2026-07-27 | 2026-08-02 |  |  | 2064 | 0 | 2064 | 100% | 0% | 48 | 48 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-GN-M-70 | Surface Reinstatement & Civil Works | 6 | 2026-08-10 | 2026-08-16 |  |  | 2064 | 0 | 2064 | 100% | 0% | 24 | 24 | 0 | Yes | 1 | 0 | 0 | 1
IRRIGATION SYSTEM WORKS |  | 46 | 2026-06-17 | 2026-08-09 | 2026-06-17 |  | 753137.4 | 687596.88 | 753137.4 | 100% | 91.3% | 144 | 144 | 131 |  | 4 | 2 | 2 | 0
PG-Q-CON-EX-GN-M-80 | Installation of HDPE Irrigation Pipe Network with Gate Valve and Box(Completed) | 7 | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 148902.18 | 148902.18 | 148902.18 | 100% | 100% | 28 | 28 | 28 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-M-80_R | Installation of HDPE Irrigation Pipe Network with Gate Valve and Box(Remaining) | 3 | 2026-07-30 | 2026-08-02 | 2026-08-06 | 2026-10-01 | 276532.62 | 276532.62 | 276532.62 | 100% | 100% | 52 | 52 | 52 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-M-90 | Installation of Irrigation Control System | 3 | 2026-08-03 | 2026-08-05 | 2026-08-20 |  | 90915 | 72732 | 90915 | 100% | 80% | 32 | 32 | 26 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-M-100 | Installation of Bubblers and Sprinklers | 3 | 2026-08-06 | 2026-08-09 | 2026-08-27 |  | 236787.6 | 2418-08-21 01:55 | 236787.6 | 100% | 80% | 32 | 32 | 26 | Yes | 1 | 0 | 1 | 0
FIRE PROTECTION SYSTEM |  | 2 | 2026-08-17 | 2026-08-18 |  |  | 1900-11-12 22:34 | 0 | 1900-11-12 22:34 | 100% | 0% | 32 | 32 | 0 |  | 1 | 0 | 0 | 1
PG-Q-CON-EX-GN-M-110 | Fire Extinguisher Installation | 2 | 2026-08-17 | 2026-08-18 |  |  | 317.94 | 0 | 317.94 | 100% | 0% | 32 | 32 | 0 | Yes | 1 | 0 | 0 | 1
ELECTRICAL WORK |  | 137 | 2026-05-20 | 2026-11-01 | 2026-05-20 |  | 670160.88 | 555990.28 | 693965.28 | 96.57% | 80.12% | 784 | 664 | 388 |  | 21 | 3 | 18 | 0
POWER, LIGHTING & GROUNDING |  | 102 | 2026-05-20 | 2026-09-20 | 2026-05-20 |  | 636895.08 | 538869.22 | 636895.08 | 100% | 84.61% | 376 | 376 | 266 |  | 10 | 3 | 7 | 0
PG-Q-CON-EX-GN-E-10 | Excavation(Completed) | 27 | 2026-05-20 | 2026-06-24 | 2026-05-20 | 2026-06-24 | 121836.96 | 121836.96 | 121836.96 | 100% | 100% | 64 | 64 | 64 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-E-20 | Foundation Work for Site Lighting Poles(Completed) | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 69621.12 | 69621.12 | 69621.12 | 100% | 100% | 20 | 20 | 20 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-E-10_R | Excavation(Remaining) | 3 | 2026-08-13 | 2026-08-16 | 2026-07-16 | 2026-08-27 | 52215.84 | 52215.84 | 52215.84 | 100% | 100% | 28 | 28 | 28 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-E-20_R | Foundation Work for Site Lighting Poles(Remaining) | 4 | 2026-08-13 | 2026-08-17 | 2026-08-20 |  | 162449.28 | 2255-10-24 10:05 | 162449.28 | 100% | 80% | 48 | 48 | 38 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-E-30 | Lightning Protection System (LPS) | 3 | 2026-08-29 | 2026-08-31 | 2026-08-27 |  | 1922-08-17 | 1918-02-06 | 8265 | 100% | 80% | 32 | 32 | 26 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-E-40 | KWH Meter and MDB Installation | 2 | 2026-09-01 | 2026-09-02 | 2026-10-13 |  | 1912-07-21 16:48 | 1905-01-07 16:19 | 4586.7 | 100% | 40% | 32 | 32 | 13 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-E-50 | Power Panels and Distribution Boards | 5 | 2026-09-03 | 2026-09-08 | 2026-10-14 |  | 1947-08-18 21:36 | 6959.16 | 17397.9 | 100% | 40% | 40 | 40 | 16 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-E-60 | Site Lighting Poles Installation | 3 | 2026-09-09 | 2026-09-12 | 2026-08-20 |  | 2376-07-14 19:12 | 2281-03-24 05:46 | 174052.8 | 100% | 80% | 40 | 40 | 32 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-E-70 | Wiring Works | 3 | 2026-09-13 | 2026-09-15 | 2026-10-10 |  | 1911-07-25 | 1904-08-15 14:24 | 4224 | 100% | 40% | 32 | 32 | 13 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-E-80 | Lighting Fixtures with outlets Installation | 4 | 2026-09-16 | 2026-09-20 | 2026-10-12 |  | 1960-11-25 11:31 | 1924-05-11 04:34 | 22245.48 | 100% | 40% | 40 | 40 | 16 | Yes | 1 | 0 | 1 | 0
ELV SYSTEMS (TELECOM, DATA, AV & CCTV) |  | 25 | 2026-09-21 | 2026-10-20 | 2026-10-07 |  | 1972-11-10 | 1935-06-08 19:12 | 43146 | 61.68% | 30% | 272 | 222 | 82 |  | 7 | 0 | 7 | 0
PG-Q-CON-EX-GN-E-90 | ELV Containment & Cabling Works | 3 | 2026-09-21 | 2026-09-24 | 2026-10-07 |  | 1901-09-10 19:12 | 1900-07-03 22:34 | 619.8 | 100% | 30% | 40 | 40 | 12 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-E-100 | Fiber Optic Pull Box Installation | 3 | 2026-09-26 | 2026-09-28 | 2026-10-10 |  | 1901-09-10 19:12 | 1900-07-03 22:34 | 619.8 | 100% | 30% | 32 | 32 | 10 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-E-110 | Telephone and Data Outlet Installation | 4 | 2026-09-29 | 2026-10-03 | 2026-10-10 |  | 1910-03-06 19:12 | 1903-01-19 15:22 | 3718.8 | 100% | 30% | 40 | 40 | 12 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-E-120 | Telecom Equipment and AV HDMI Installation | 4 | 2026-10-04 | 2026-10-07 | 2026-10-12 |  | 1941-09-30 02:53 | 1912-07-09 17:46 | 15249.12 | 100% | 30% | 40 | 40 | 12 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-E-130 | CCTV Rack / Cabinet Installation | 4 | 2026-10-08 | 2026-10-12 | 2026-10-11 |  | 1903-12-16 11:31 | 1901-03-08 22:34 | 1446.48 | 100% | 30% | 40 | 40 | 12 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-E-140 | NVR and CCTV Monitor Installation | 4 | 2026-10-13 | 2026-10-17 | 2026-10-13 |  | 1913-07-29 | 1905-06-05 14:24 | 1918-02-06 | 75% | 30% | 40 | 30 | 12 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-E-150 | IP Camera Installation | 3 | 2026-10-18 | 2026-10-20 | 2026-10-14 |  | 0 | 1912-03-21 | 14880 | 0% | 30% | 40 | 0 | 12 | Yes | 1 | 0 | 1 | 0
FIRE ALARM SYSTEM |  | 32 | 2026-09-26 | 2026-11-01 | 2026-10-11 |  | 1918-03-18 19:12 | 1911-06-08 06:14 | 13924.2 | 47.78% | 30% | 136 | 66 | 41 |  | 4 | 0 | 4 | 0
PG-Q-CON-EX-GN-E-160 | Fire Alarm Containment & Cabling | 8 | 2026-09-26 | 2026-10-04 | 2026-10-11 |  | 1905-06-05 14:24 | 1901-08-17 01:55 | 1983.6 | 100% | 30% | 32 | 32 | 10 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-E-170 | Fire Alarm Control Panel (FACP) Installation | 8 | 2026-10-05 | 2026-10-13 | 2026-10-12 |  | 1907-03-28 19:12 | 1902-03-03 10:34 | 2644.8 | 100% | 30% | 24 | 24 | 7 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-E-180 | Initiating Devices (Detectors & Manual Pull Station) | 8 | 2026-10-14 | 2026-10-22 | 2026-10-13 |  | 1905-07-16 09:36 | 1906-08-25 06:43 | 8097.6 | 25% | 30% | 40 | 10 | 12 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-E-190 | Notification Appliances (Strobe with Sounder) | 8 | 2026-10-24 | 2026-11-01 | 2026-10-15 |  | 0 | 359.46 | 1198.2 | 0% | 30% | 40 | 0 | 12 | Yes | 1 | 0 | 1 | 0
PARKING WORK |  | 124 | 2026-06-17 | 2026-11-09 | 2026-06-17 |  | 19899 | 88440 | 102919.8 | 19.33% | 85.93% | 164 | 22 | 80 |  | 4 | 3 | 0 | 1
PG-Q-CON-EX-GN-PR-20 | Interlock tiles(Completed) | 7 | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 19899 | 19899 | 19899 | 100% | 100% | 22 | 22 | 22 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-PR-10 | Installlation of Parking Accessories | 5 | 2026-10-29 | 2026-11-03 | 2026-08-20 | 2026-10-01 | 0 | 44220 | 44220 | 0% | 100% | 32 | 0 | 32 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-PR-20_R | Interlock tiles(Remaining) | 3 | 2026-11-01 | 2026-11-03 | 2026-07-06 | 2026-07-10 | 0 | 1966-08-02 | 24321 | 0% | 100% | 26 | 0 | 26 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-PR-30 | Marking & Signages | 5 | 2026-11-04 | 2026-11-09 |  |  | 0 | 0 | 14479.8 | 0% | 0% | 84 | 0 | 0 | Yes | 1 | 0 | 0 | 1
SERVICE CONNECTION |  | 32 | 2026-11-10 | 2026-12-16 | 2026-07-12 |  | 0 | 4240.8 | 7440 | 0% | 57% | 236 | 0 | 135 |  | 4 | 1 | 1 | 2
PG-Q-CON-EX-GN-SC-10 | Excavation & Trench Preparation | 8 | 2026-11-10 | 2026-11-18 | 2026-07-12 | 2026-08-20 | 0 | 2232 | 2232 | 0% | 100% | 92 | 0 | 92 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-SC-20 | HDPE Pipe Laying & Valve Installation | 8 | 2026-11-19 | 2026-11-28 | 2026-08-14 |  | 0 | 1905-06-30 19:12 | 2232 | 0% | 90% | 48 | 0 | 43 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-SC-30 | Connection to City Network | 8 | 2026-11-29 | 2026-12-07 |  |  | 0 | 0 | 1488 | 0% | 0% | 48 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-GN-SC-40 | Backfilling | 8 | 2026-12-08 | 2026-12-16 |  |  | 0 | 0 | 1488 | 0% | 0% | 48 | 0 | 0 | Yes | 1 | 0 | 0 | 1
LANDSCAPING WORKS |  | 169 | 2026-05-31 | 2026-12-14 | 2026-05-30 |  | 1767559.7 | 1898449.14 | 2134335 | 82.82% | 88.95% | 392 | 208 | 269 |  | 14 | 9 | 4 | 1
HARDSCAPE WORK |  | 169 | 2026-05-31 | 2026-12-14 | 2026-05-30 |  | 1644359.7 | 1690549.14 | 1712409 | 96.03% | 98.72% | 224 | 163 | 193 |  | 11 | 8 | 3 | 0
PG-Q-CON-EX-LS-HS-10 | Curbstone Installation(Completed) | 22 | 2026-05-31 | 2026-06-24 | 2026-05-30 | 2026-06-24 | 604590 | 604590 | 604590 | 100% | 100% | 22 | 22 | 22 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-LS-HS-20 | Interlock Tiles Grey Scale with Black Marble Chips(Completed) | 22 | 2026-05-31 | 2026-06-24 | 2026-05-30 | 2026-06-24 | 36960 | 36960 | 36960 | 100% | 100% | 19 | 19 | 19 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-LS-HS-40 | Bike Path and Walking Path Construction(Completed) | 22 | 2026-05-31 | 2026-06-24 | 2026-05-30 | 2026-06-24 | 146025 | 146025 | 146025 | 100% | 100% | 26 | 26 | 26 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-LS-HS-30 | Stamped Concrete Floor(Completed) | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 207900 | 207900 | 207900 | 100% | 100% | 16 | 16 | 16 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-LS-HS-50 | Install Recycled Precast Concrete Seats(Completed) | 7 | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 6959.7 | 6959.7 | 6959.7 | 100% | 100% | 3 | 3 | 3 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-LS-HS-40_R | Bike Path and Walking Path Construction(Remaining) | 17 | 2026-07-18 | 2026-08-05 | 2026-07-08 | 2026-08-14 | 119475 | 119475 | 119475 | 100% | 100% | 22 | 22 | 22 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-LS-HS-10_R | Curbstone Installation(Remaining) | 10 | 2026-09-02 | 2026-09-13 | 2026-07-07 | 2026-08-14 | 259110 | 259110 | 259110 | 100% | 100% | 10 | 10 | 10 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-LS-HS-30_R | Stamped Concrete Floor(Remaining) | 13 | 2026-09-14 | 2026-09-29 | 2026-07-31 | 2026-08-27 | 207900 | 207900 | 207900 | 100% | 100% | 16 | 16 | 16 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-LS-HS-20_R | Interlock Tiles Grey Scale with Black Marble Chips(Remaining) | 13 | 2026-09-30 | 2026-10-14 | 2026-08-27 |  | 2051-10-14 | 49896 | 55440 | 100% | 90% | 29 | 29 | 26 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-LS-HS-50_R | Install Recycled Precast Concrete Seats(Remaining) | 10 | 2026-11-22 | 2026-12-02 | 2026-08-20 |  | 0 | 2037-03-10 20:10 | 62637.3 | 0% | 80% | 29 | 0 | 23 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-LS-HS-60 | Install Recycled Precast Concrete Trash Bins | 10 | 2026-12-03 | 2026-12-14 | 2026-10-12 |  | 0 | 1623.6 | 5412 | 0% | 30% | 32 | 0 | 10 | No | 1 | 0 | 1 | 0
SOFTSCAPE WORK |  | 140 | 2026-06-10 | 2026-11-21 | 2026-06-10 |  | 123200 | 207900 | 421926 | 29.2% | 49.27% | 168 | 45 | 76 |  | 3 | 1 | 1 | 1
PG-Q-CON-EX-LS-SS-20 | Lawn Area Preparation & Planting / Turfing(Completed) | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 115500 | 115500 | 115500 | 100% | 100% | 42 | 42 | 42 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-LS-SS-20_R | Lawn Area Preparation & Planting / Turfing(Remaining) | 15 | 2026-10-15 | 2026-11-01 | 2026-08-27 |  | 1921-01-29 | 2152-12-23 | 115500 | 6.67% | 80% | 42 | 3 | 34 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-LS-SS-10 | Planting Trees | 17 | 2026-11-02 | 2026-11-21 |  |  | 0 | 0 | 190926 | 0% | 0% | 84 | 0 | 0 | No | 1 | 0 | 0 | 1
TANK WORKS |  | 81 | 2026-05-13 | 2026-08-19 | 2026-05-13 |  | 48290.4 | 27462.6 | 48290.4 | 100% | 56.87% | 628 | 628 | 597 |  | 12 | 11 | 1 | 0
SEPTIC TANK |  | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 7475.22 | 7475.22 | 7475.22 | 100% | 100% | 364 | 364 | 364 |  | 7 | 7 | 0 | 0
PG-Q-CON-EX-TW-ST-10 | Excavation | 29 | 2026-05-13 | 2026-06-20 | 2026-05-13 | 2026-06-20 | 1900-09-08 04:19 | 252.18 | 252.18 | 100% | 100% | 92 | 92 | 92 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-TW-ST-20 | PCC / Lean Concrete laying | 24 | 2026-05-20 | 2026-06-21 | 2026-05-20 | 2026-06-21 | 168.12 | 168.12 | 168.12 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-TW-ST-40 | RCC Wall | 4 | 2026-06-20 | 2026-06-23 | 2026-06-20 | 2026-06-23 | 2757.6 | 2757.6 | 2757.6 | 100% | 100% | 56 | 56 | 56 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-TW-ST-30 | RCC Foundation | 2 | 2026-06-21 | 2026-06-22 | 2026-06-21 | 2026-06-22 | 1277.64 | 1277.64 | 1277.64 | 100% | 100% | 56 | 56 | 56 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-TW-ST-50 | RCC Slab | 4 | 2026-06-21 | 2026-06-24 | 2026-06-21 | 2026-06-24 | 2599.38 | 2599.38 | 2599.38 | 100% | 100% | 56 | 56 | 56 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-TW-ST-60 | Finishing Work | 3 | 2026-06-22 | 2026-06-24 | 2026-06-22 | 2026-06-24 | 1900-09-08 04:19 | 252.18 | 252.18 | 100% | 100% | 24 | 24 | 24 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-TW-ST-70 | Backfilling | 2 | 2026-06-23 | 2026-06-24 | 2026-06-23 | 2026-06-24 | 1900-06-16 02:53 | 168.12 | 168.12 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
WATER STORAGE TANK |  | 81 | 2026-05-13 | 2026-08-19 | 2026-05-13 |  | 40815.18 | 19987.38 | 40815.18 | 100% | 48.97% | 264 | 264 | 233 |  | 5 | 4 | 1 | 0
PG-Q-CON-EX-TW-IR-10 | Excavation(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 1902-02-04 13:55 | 766.58 | 766.58 | 100% | 100% | 83 | 83 | 83 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-TW-IR-10_R | Excavation(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-07 | 2026-07-08 | 1900-03-25 04:19 | 85.18 | 85.18 | 100% | 100% | 9 | 9 | 9 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-TW-IR-20 | RCC Foundation | 15 | 2026-07-04 | 2026-07-20 | 2026-07-09 | 2026-08-26 | 4136.4 | 4136.4 | 4136.4 | 100% | 100% | 72 | 72 | 72 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-TW-IR-30 | Backfilling | 7 | 2026-07-21 | 2026-07-28 | 2026-08-20 | 2026-08-27 | 1114.02 | 1903-01-18 00:29 | 1114.02 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-TW-IR-40 | GRP Water Tank Installation | 8 | 2026-08-11 | 2026-08-19 | 2026-10-14 |  | 34713 | 13885.2 | 34713 | 100% | 40% | 52 | 52 | 21 | No | 1 | 0 | 1 | 0
AIR DOME CONSTRUCTION |  | 165 | 2026-05-13 | 2026-11-26 | 2026-05-13 |  | 3260143.02 | 1461181.68 | 4178041.2 | 78.03% | 34.97% | 1116 | 865 | 446 |  | 21 | 7 | 2 | 12
CIVIL WORK |  | 100 | 2026-05-13 | 2026-09-10 | 2026-05-13 |  | 1711669.97 | 1210693.39 | 1711669.97 | 100% | 70.73% | 536 | 536 | 392 |  | 9 | 7 | 0 | 2
PG-Q-CON-EX-AD-CL-10 | Excavation For Footing(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 25048.83 | 25048.83 | 25048.83 | 100% | 100% | 10 | 10 | 10 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-AD-CL-10_R | Excavation For Footing(Remaining) | 6 | 2026-07-09 | 2026-07-15 | 2026-07-09 | 2026-07-10 | 225439.46 | 225439.46 | 225439.46 | 100% | 100% | 90 | 90 | 90 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-AD-CL-20 | Anti-Termite Treatment | 2 | 2026-07-16 | 2026-07-18 | 2026-07-11 | 2026-07-12 | 83496.1 | 83496.1 | 83496.1 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-AD-CL-30 | PCC / Blinding Concrete | 3 | 2026-07-19 | 2026-07-21 | 2026-07-23 | 2026-08-06 | 125244.14 | 125244.14 | 125244.14 | 100% | 100% | 64 | 64 | 64 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-AD-CL-40 | RCC Foundation Works | 12 | 2026-07-22 | 2026-08-04 | 2026-07-31 | 2026-08-13 | 250488.29 | 250488.29 | 250488.29 | 100% | 100% | 88 | 88 | 88 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-AD-CL-50 | Backfilling with Compaction | 6 | 2026-08-05 | 2026-08-11 | 2026-08-06 | 2026-08-14 | 250488.29 | 250488.29 | 250488.29 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-AD-CL-60 | Installation of Anchorage System | 8 | 2026-08-12 | 2026-08-20 | 2026-08-27 | 2026-09-29 | 250488.29 | 250488.29 | 250488.29 | 100% | 100% | 60 | 60 | 60 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-AD-CL-70 | Installation of Steel Cable Structural System | 10 | 2026-08-22 | 2026-09-01 |  |  | 250488.29 | 0 | 250488.29 | 100% | 0% | 76 | 76 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-AD-CL-80 | Installation of Membrane System | 8 | 2026-09-02 | 2026-09-10 |  |  | 250488.29 | 0 | 250488.29 | 100% | 0% | 68 | 68 | 0 | Yes | 1 | 0 | 0 | 1
ARCHITECTURAL WORK |  | 27 | 2026-10-27 | 2026-11-26 | 2026-08-27 |  | 0 | 2242-11-26 03:22 | 712953.22 | 0% | 17.57% | 212 | 0 | 30 |  | 4 | 0 | 1 | 3
PG-Q-CON-EX-AD-AR-10 | Installation of Thermal Insulation System | 8 | 2026-10-27 | 2026-11-04 | 2026-08-27 |  | 0 | 2242-11-26 03:22 | 250488.29 | 0% | 50% | 60 | 0 | 30 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-AD-AR-40 | Final Fixing of Accessories & Finishes | 8 | 2026-11-05 | 2026-11-14 |  |  | 0 | 0 | 208740.24 | 0% | 0% | 56 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-AD-AR-20 | Installation of Doors & Access Systems | 6 | 2026-11-15 | 2026-11-21 |  |  | 0 | 0 | 250488.29 | 0% | 0% | 56 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-AD-AR-30 | Installation of Logo | 5 | 2026-11-22 | 2026-11-26 |  |  | 0 | 0 | 3236.4 | 0% | 0% | 40 | 0 | 0 | Yes | 1 | 0 | 0 | 1
MECHANICAL WORK |  | 16 | 2026-09-12 | 2026-09-30 |  |  | 667968.77 | 0 | 667968.77 | 100% | 0% | 160 | 160 | 0 |  | 3 | 0 | 0 | 3
PG-Q-CON-EX-AD-ME-10 | Installation of Main Air Package Units | 5 | 2026-09-12 | 2026-09-16 |  |  | 250488.29 | 0 | 250488.29 | 100% | 0% | 56 | 56 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-AD-ME-20 | Installation of Backup Air Package Unit | 5 | 2026-09-17 | 2026-09-22 |  |  | 208740.24 | 0 | 208740.24 | 100% | 0% | 56 | 56 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-AD-ME-30 | Installation of Complete HVAC System | 6 | 2026-09-24 | 2026-09-30 |  |  | 208740.24 | 0 | 208740.24 | 100% | 0% | 48 | 48 | 0 | Yes | 1 | 0 | 0 | 1
ELECTRICAL WORK |  | 60 | 2026-08-17 | 2026-10-26 | 2026-08-27 |  | 880504.29 | 2242-11-26 03:22 | 1085449.25 | 81.12% | 11.54% | 208 | 169 | 24 |  | 5 | 0 | 1 | 4
PG-Q-CON-EX-AD-EL-10 | Installation of Electrical Boxes & MDBs | 12 | 2026-08-17 | 2026-08-30 | 2026-08-27 |  | 208740.24 | 2242-11-26 03:22 | 208740.24 | 100% | 60% | 40 | 40 | 24 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-AD-EL-20 | Installation of Lighting System | 12 | 2026-08-31 | 2026-09-13 |  |  | 208740.24 | 0 | 208740.24 | 100% | 0% | 32 | 32 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-AD-EL-30 | Electrical Connections to Main Power Source (Excluding kWh Meter) | 5 | 2026-10-01 | 2026-10-06 |  |  | 208740.24 | 0 | 208740.24 | 100% | 0% | 40 | 40 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-AD-EL-40 | Installation of Backup Generator | 6 | 2026-10-07 | 2026-10-13 |  |  | 208740.24 | 0 | 208740.24 | 100% | 0% | 48 | 48 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-AD-EL-50 | Installation of Smart Dome System | 11 | 2026-10-14 | 2026-10-26 |  |  | 45543.33 | 0 | 250488.29 | 18.18% | 0% | 48 | 9 | 0 | Yes | 1 | 0 | 0 | 1
TOILET BUILDING WORKS |  | 139 | 2026-05-06 | 2026-10-20 | 2026-05-06 |  | 310599.36 | 303744.63 | 324844.38 | 95.61% | 93.5% | 1708 | 1599 | 1571 |  | 38 | 30 | 8 | 0
CIVIL WORK |  | 138 | 2026-05-06 | 2026-10-19 | 2026-05-06 |  | 213008.82 | 211541.22 | 227117.58 | 93.79% | 93.14% | 1100 | 1023 | 1027 |  | 24 | 19 | 5 | 0
STRUCTURAL WORK |  | 74 | 2026-05-06 | 2026-08-04 | 2026-05-06 | 2026-07-10 | 37980 | 37980 | 37980 | 100% | 100% | 372 | 372 | 372 |  | 7 | 7 | 0 | 0
PG-Q-CON-B-STR-10 | Excavation up to bottom of footing | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 1900.8 | 1900.8 | 1900.8 | 100% | 100% | 92 | 92 | 92 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-STR-20 | Anti-termite treatment and Polyethene Sheet | 2 | 2026-05-12 | 2026-05-13 | 2026-05-12 | 2026-05-13 | 3294 | 3294 | 3294 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-STR-30 | Backfilling with selected fill material (under footing) | 1 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 1900.8 | 1900.8 | 1900.8 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-STR-40 | Raft Foundation Work | 21 | 2026-05-13 | 2026-06-10 | 2026-05-13 | 2026-06-10 | 2534.4 | 2534.4 | 2534.4 | 100% | 100% | 64 | 64 | 64 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-STR-50 | Autoclaved aerated panel (walls) | 4 | 2026-07-25 | 2026-07-28 | 2026-07-08 | 2026-07-09 | 11340 | 11340 | 11340 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-STR-60 | Autoclaved aerated panel (ceiling) | 3 | 2026-07-29 | 2026-08-01 | 2026-07-09 | 2026-07-10 | 8505 | 8505 | 8505 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-STR-70 | Autoclaved aerated panel (parapet) | 3 | 2026-08-02 | 2026-08-04 | 2026-07-09 | 2026-07-10 | 8505 | 8505 | 8505 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
ARCHITECTURAL WORK |  | 64 | 2026-08-05 | 2026-10-19 | 2026-07-12 |  | 175028.82 | 173561.22 | 189137.58 | 92.54% | 91.76% | 728 | 651 | 655 |  | 17 | 12 | 5 | 0
GENERAL FINISHES |  | 64 | 2026-08-05 | 2026-10-19 | 2026-07-12 |  | 79589.04 | 77872.38 | 84120 | 94.61% | 92.57% | 376 | 347 | 352 |  | 8 | 6 | 2 | 0
PG-Q-CON-B-AR-GF-10 | Block Works | 6 | 2026-08-05 | 2026-08-11 | 2026-07-12 | 2026-07-16 | 2484 | 2484 | 2484 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-AR-GF-20 | Plaster | 7 | 2026-08-12 | 2026-08-19 | 2026-07-22 | 2026-08-05 | 4427.4 | 4427.4 | 4427.4 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-AR-GF-30 | False Ceiling Installation & Finishing | 7 | 2026-08-20 | 2026-08-27 | 2026-08-20 | 2026-09-10 | 1902-05-22 14:24 | 873.6 | 873.6 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-AR-GF-40 | Wall Paint | 12 | 2026-09-16 | 2026-09-30 | 2026-08-20 | 2026-09-06 | 1908-02-05 | 2958 | 2958 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-AR-GF-50 | Epoxy Flooring | 6 | 2026-10-01 | 2026-10-07 | 2026-08-20 | 2026-09-23 | 1900-09-29 14:24 | 1900-09-29 14:24 | 273.6 | 100% | 100% | 56 | 56 | 56 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-AR-GF-80 | Facade Finishing Work | 8 | 2026-10-01 | 2026-10-10 | 2026-08-20 | 2026-09-10 | 2043-02-16 | 2043-02-16 | 52278 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-AR-GF-60 | Install Doors & Windows | 5 | 2026-10-08 | 2026-10-13 | 2026-08-27 |  | 1936-05-03 19:12 | 9291.66 | 13273.8 | 100% | 70% | 32 | 32 | 22 | No | 1 | 0 | 1 | 0
PG-Q-CON-B-AR-GF-70 | Lockers and Furniture Installation | 5 | 2026-10-14 | 2026-10-19 | 2026-09-19 |  | 1908-04-07 15:22 | 5286.12 | 7551.6 | 40% | 70% | 48 | 19 | 34 | No | 1 | 0 | 1 | 0
WET AREA FINISHES |  | 47 | 2026-08-20 | 2026-10-14 | 2026-08-06 |  | 2122-02-07 18:43 | 79515.3 | 81123.78 | 100% | 98.02% | 216 | 216 | 206 |  | 6 | 5 | 1 | 0
PG-Q-CON-B-AR-WF-10 | False Ceiling Installation & Finishing | 7 | 2026-08-20 | 2026-08-27 | 2026-08-27 | 2026-09-04 | 1907-12-07 | 2898 | 2898 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-AR-WF-20 | Wall Tiles and Partition Work | 6 | 2026-09-16 | 2026-09-22 | 2026-08-06 | 2026-08-14 | 1958-04-08 04:48 | 21283.2 | 21283.2 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-AR-WF-30 | Waterproofing on Floor | 6 | 2026-09-24 | 2026-09-30 | 2026-08-14 | 2026-09-07 | 1915-11-01 | 5784 | 5784 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-AR-WF-40 | Floor Tiles Works | 6 | 2026-10-01 | 2026-10-07 | 2026-08-14 | 2026-09-07 | 1917-10-06 | 1917-10-06 | 6489 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-AR-WF-50 | Toliet accessories Installation Works | 6 | 2026-10-08 | 2026-10-14 | 2026-08-27 | 2026-09-10 | 2007-08-13 23:31 | 2007-08-13 23:31 | 39307.98 | 100% | 100% | 24 | 24 | 24 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-AR-WF-60 | Install Doors | 5 | 2026-10-08 | 2026-10-13 | 2026-10-01 |  | 1914-09-04 14:24 | 3753.12 | 5361.6 | 100% | 70% | 32 | 32 | 22 | No | 1 | 0 | 1 | 0
ROOF FINISHES |  | 16 | 2026-10-01 | 2026-10-19 | 2026-08-20 |  | 1939-03-12 | 16173.54 | 23893.8 | 59.92% | 67.69% | 136 | 88 | 97 |  | 3 | 1 | 2 | 0
PG-Q-CON-B-AR-RF-10 | Waterproofing on Floor | 4 | 2026-10-01 | 2026-10-05 | 2026-08-20 | 2026-09-08 | 1911-05-20 | 4158 | 4158 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-AR-RF-20 | Epoxy Flooring and Finishes | 6 | 2026-10-06 | 2026-10-12 | 2026-08-20 |  | 1927-10-23 | 1925-01-10 04:48 | 10158 | 100% | 90% | 56 | 56 | 50 | No | 1 | 0 | 1 | 0
PG-Q-CON-B-AR-RF-30 | Steel ladder and Steel roof scupper Installation | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 |  | 0 | 2873.34 | 9577.8 | 0% | 30% | 48 | 0 | 14 | No | 1 | 0 | 1 | 0
MEP WORK |  | 108 | 2026-06-16 | 2026-10-20 | 2026-06-16 |  | 97590.54 | 92203.41 | 97726.8 | 99.86% | 94.35% | 608 | 576 | 544 |  | 14 | 11 | 3 | 0
MECANICAL WORKS |  | 108 | 2026-06-16 | 2026-10-20 | 2026-06-16 |  | 79343.22 | 73956.09 | 79479.48 | 99.83% | 93.05% | 400 | 368 | 336 |  | 9 | 6 | 3 | 0
FIRE FIGHTING SYSTEM |  | 1 | 2026-10-20 | 2026-10-20 | 2026-10-01 |  | 0 | 1900-03-08 03:07 | 1900-05-15 06:14 | 0% | 50% | 32 | 0 | 16 |  | 1 | 0 | 1 | 0
PG-Q-CON-B-GF-FF-10 | Fire Extinguisher Installation | 1 | 2026-10-20 | 2026-10-20 | 2026-10-01 |  | 0 | 68.13 | 136.26 | 0% | 50% | 32 | 0 | 16 | No | 1 | 0 | 1 | 0
SEWER AND DRAINAGE SYSTEM |  | 68 | 2026-06-16 | 2026-09-02 | 2026-06-16 |  | 11290.02 | 9677.16 | 11290.02 | 100% | 85.71% | 144 | 144 | 120 |  | 3 | 2 | 1 | 0
PG-Q-CON-B-GF-DR-10 | Sewer and Drainge System Main Lines Installation | 2 | 2026-06-16 | 2026-06-17 | 2026-06-16 | 2026-06-17 | 3225.72 | 3225.72 | 3225.72 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-GF-DR-20 | Sewer and Drainge System Pipes and fittings Installation | 2 | 2026-06-16 | 2026-06-17 | 2026-06-16 | 2026-06-17 | 4838.58 | 4838.58 | 4838.58 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-GF-DR-30 | Sanitaryware Installation (Final Fix) | 2 | 2026-09-01 | 2026-09-02 | 2026-10-01 |  | 1908-10-29 17:17 | 1612.86 | 3225.72 | 100% | 50% | 48 | 48 | 24 | No | 1 | 0 | 1 | 0
HVAC SYSTEM |  | 10 | 2026-08-12 | 2026-08-23 | 2026-08-13 |  | 12127.2 | 8284.8 | 12127.2 | 100% | 68.32% | 96 | 96 | 72 |  | 2 | 1 | 1 | 0
PG-Q-CON-B-GF-AC-10 | Duct Work and Exhaust Fan Installation | 7 | 2026-08-12 | 2026-08-19 | 2026-08-13 | 2026-08-20 | 1912-02-28 09:36 | 1912-02-28 09:36 | 4442.4 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-GF-AC-20 | Split AC, Grills & Diffuser Installation | 3 | 2026-08-20 | 2026-08-23 | 2026-10-01 |  | 7684.8 | 3842.4 | 7684.8 | 100% | 50% | 48 | 48 | 24 | No | 1 | 0 | 1 | 0
WATER SUPPLY SYSTEM |  | 66 | 2026-06-16 | 2026-08-31 | 2026-06-16 | 2026-09-07 | 55926 | 55926 | 55926 | 100% | 100% | 128 | 128 | 128 |  | 3 | 3 | 0 | 0
PG-Q-CON-B-GF-WS-10 | Water Supply Main Lines Installation | 2 | 2026-06-16 | 2026-06-17 | 2026-06-16 | 2026-06-17 | 5702.4 | 5702.4 | 5702.4 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-GF-WS-20 | Water Supply Pipes Installation (Cold and Hot Water) | 2 | 2026-08-24 | 2026-08-25 | 2026-07-22 | 2026-07-31 | 1937-12-08 14:24 | 13857.6 | 13857.6 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-GF-WS-30 | Water Supply Accesories and Booster pump Installation | 3 | 2026-08-29 | 2026-08-31 | 2026-08-20 | 2026-09-07 | 1999-07-25 | 36366 | 36366 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
ELECTRICAL WORKS |  | 56 | 2026-07-13 | 2026-09-15 | 2026-07-22 | 2026-09-08 | 18247.32 | 18247.32 | 18247.32 | 100% | 100% | 208 | 208 | 208 |  | 5 | 5 | 0 | 0
PG-Q-CON-B-GF-EL-10 | Pipes & Conduits Installation | 8 | 2026-07-13 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 1983.6 | 1983.6 | 1983.6 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-GF-EL-50 | Electrical Light Fixtures Installation | 2 | 2026-09-03 | 2026-09-05 | 2026-08-20 | 2026-09-08 | 1920-02-01 12:29 | 7337.52 | 7337.52 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-GF-EL-30 | Fire Alarm Devices Installation | 3 | 2026-09-06 | 2026-09-08 | 2026-08-20 | 2026-09-08 | 1905-06-05 14:24 | 1983.6 | 1983.6 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-GF-EL-40 | Telecom & CCTV Devices Installation | 3 | 2026-09-09 | 2026-09-12 | 2026-08-20 | 2026-09-08 | 1913-07-29 | 4959 | 4959 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-GF-EL-20 | Electrical & ELV Wiring Works | 3 | 2026-09-13 | 2026-09-15 | 2026-08-20 | 2026-09-08 | 1983.6 | 1983.6 | 1983.6 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PROJECT CLOSOUT |  | 174 | 2026-05-23 | 2026-12-16 | 2026-05-22 |  | 52612.62 | 324444.49 | 1753754 | 3% | 18.5% | 384 | 11 | 62 |  | 7 | 1 | 2 | 4
PG-Q-PCL-10 | Testing, Commessioning for All Systems(Completed) | 25 | 2026-05-23 | 2026-06-24 | 2026-05-22 | 2026-06-24 | 52612.62 | 52612.62 | 52612.62 | 100% | 100% | 11 | 11 | 11 | No | 1 | 1 | 0 | 0
PG-Q-PCL-20 | As-Built Drawings | 15 | 2026-11-16 | 2026-12-02 | 2026-09-23 |  | 0 | 35075.08 | 175375.4 | 0% | 20% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-Q-PCL-10_R | Testing, Commessioning for All Systems(Remaining) | 10 | 2026-11-16 | 2026-11-26 | 2026-08-06 |  | 0 | 236756.79 | 473513.58 | 0% | 50% | 101 | 0 | 50 | Yes | 1 | 0 | 1 | 0
PG-Q-PCL-30 | Snag list Submission | 3 | 2026-11-28 | 2026-11-30 |  |  | 0 | 0 | 350750.8 | 0% | 0% | 136 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-PCL-40 | Snag list Closeout | 10 | 2026-12-01 | 2026-12-12 |  |  | 0 | 0 | 350750.8 | 0% | 0% | 136 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-PCL-50 | Issuing Approvals | 3 | 2026-12-13 | 2026-12-15 |  |  | 0 | 0 | 175375.4 | 0% | 0% | 0 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-PCL-60 | Handing Over | 1 | 2026-12-16 | 2026-12-16 |  |  | 0 | 0 | 175375.4 | 0% | 0% | 0 | 0 | 0 | Yes | 1 | 0 | 0 | 1
HAIL |  | 249 | 2026-02-17 | 2026-12-15 | 2026-02-17 |  | 5901822.09 | 5530604.47 | 6814652 | 86.6% | 81.16% | 6348 | 5409 | 4595 |  | 581 | 496 | 66 | 19
MOBILIZATION |  | 29 | 2026-02-17 | 2026-03-29 | 2026-02-17 | 2026-03-28 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 9 | 9 | 0 | 0
TEMPORARY CAMP |  | 28 | 2026-02-17 | 2026-03-28 | 2026-02-17 | 2026-03-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-MOB-CAM-10 | Temporary Underground Utilities works | 28 | 2026-02-17 | 2026-03-28 | 2026-02-17 | 2026-03-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-MOB-CAM-20 | Temporary Porta-Cabins | 21 | 2026-02-26 | 2026-03-28 | 2026-02-26 | 2026-03-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-MOB-CAM-30 | Temporary Toilets | 21 | 2026-02-26 | 2026-03-28 | 2026-02-26 | 2026-03-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-MOB-CAM-40 | Temporary Mosque | 13 | 2026-03-08 | 2026-03-28 | 2026-03-08 | 2026-03-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SITE OFFICES |  | 29 | 2026-02-17 | 2026-03-29 | 2026-02-17 | 2026-03-28 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-H-MOB-SO-10 | Temporary Underground Utilities works | 29 | 2026-02-17 | 2026-03-29 | 2026-02-17 | 2026-03-28 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-MOB-SO-20 | Temporary Porta-Cabins | 23 | 2026-02-25 | 2026-03-29 | 2026-02-25 | 2026-03-28 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-MOB-SO-30 | Temporary Toilets | 23 | 2026-02-25 | 2026-03-29 | 2026-02-25 | 2026-03-28 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-MOB-SO-40 | Temporary Mosque | 17 | 2026-03-04 | 2026-03-29 | 2026-03-04 | 2026-03-28 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-MOB-SO-50 | Car Parking Area | 10 | 2026-03-12 | 2026-03-29 | 2026-03-12 | 2026-03-28 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
GENERAL REQUIEREMENTS |  | 51 | 2026-02-17 | 2026-04-23 | 2026-02-17 | 2026-04-22 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-GEN-20 | HSSE Submission Plan | 51 | 2026-02-17 | 2026-04-23 | 2026-02-17 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-GEN-30 | Surveying report Submission Plan | 51 | 2026-02-17 | 2026-04-23 | 2026-02-17 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-GEN-40 | Baseline Submission | 6 | 2026-02-28 | 2026-03-07 | 2026-02-28 | 2026-03-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-GEN-10 | QA/QC Submission Plan | 16 | 2026-03-12 | 2026-04-05 | 2026-03-12 | 2026-04-04 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ENGINEERING |  | 118 | 2026-02-17 | 2026-07-14 | 2026-02-17 | 2026-09-17 | 204439.56 | 204439.56 | 204439.56 | 100% | 100% | 0 | 0 | 0 |  | 230 | 230 | 0 | 0
SHOP DRAWINGS SUBMITTALS |  | 93 | 2026-02-17 | 2026-06-16 | 2026-02-17 | 2026-06-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 48 | 48 | 0 | 0
STRUCTURAL DRAWINGS |  | 61 | 2026-02-17 | 2026-05-05 | 2026-02-17 | 2026-05-04 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 8 | 8 | 0 | 0
PROJECT FENCE |  | 57 | 2026-02-17 | 2026-04-30 | 2026-02-17 | 2026-04-29 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-EN-ST-SD-SB-10 | Excavation Drawings | 57 | 2026-02-17 | 2026-04-30 | 2026-02-17 | 2026-04-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ST-SD-SB-20 | Foundation Drawings | 55 | 2026-02-19 | 2026-04-30 | 2026-02-19 | 2026-04-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
TOILET BUILDING |  | 41 | 2026-02-19 | 2026-04-14 | 2026-02-19 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-EN-ST-SD-SB-30 | Excavation Drawings | 41 | 2026-02-19 | 2026-04-14 | 2026-02-19 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ST-SD-SB-40 | Foundation Drawings | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
WATER STORAGE TANK |  | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-EN-ST-SD-SB-60 | Excavation Drawings | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ST-SD-SB-50 | Foundation Drawings | 37 | 2026-02-25 | 2026-04-14 | 2026-02-25 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SEPTIC TANK |  | 55 | 2026-02-25 | 2026-05-05 | 2026-02-25 | 2026-05-04 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-EN-ST-SD-SB-70 | Reinforcement Detail Drawings | 55 | 2026-02-25 | 2026-05-05 | 2026-02-25 | 2026-05-04 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ST-SD-SB-80 | Concrete Detail Drawings | 52 | 2026-03-01 | 2026-05-05 | 2026-03-01 | 2026-05-04 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL DRAWINGS |  | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 10 | 0 | 0
TOILET BUILDING |  | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 10 | 0 | 0
PG-H-EN-AR-SD-SB-10 | Ground Floor Plan | 36 | 2026-02-23 | 2026-04-11 | 2026-02-23 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-SB-20 | Roof Floor Plan | 35 | 2026-02-28 | 2026-04-14 | 2026-02-28 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-SB-50 | Floor Finish Layout | 32 | 2026-02-28 | 2026-04-09 | 2026-02-28 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-SB-60 | Reflected Ceiling Layout | 32 | 2026-02-28 | 2026-04-11 | 2026-02-28 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-SB-70 | Enlarged Toilets Layout | 35 | 2026-02-28 | 2026-04-14 | 2026-02-28 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-SB-30 | Elevations | 29 | 2026-03-03 | 2026-04-11 | 2026-03-03 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-SB-80 | Doors & Windows Schedule | 32 | 2026-03-03 | 2026-04-14 | 2026-03-03 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-SB-90 | Aluminum Work | 32 | 2026-03-03 | 2026-04-14 | 2026-03-03 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-SB-100 | Cladding Details | 32 | 2026-03-03 | 2026-04-14 | 2026-03-03 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-SB-40 | Sections | 27 | 2026-03-05 | 2026-04-11 | 2026-03-05 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
LANDSCAPE DRAWINGS |  | 38 | 2026-02-24 | 2026-04-14 | 2026-02-24 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 10 | 0 | 0
PG-H-EN-LS-SD-SB-10 | Hardscape Layout Plan | 38 | 2026-02-24 | 2026-04-14 | 2026-02-24 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-SB-20 | Interlock Tile Details | 35 | 2026-02-24 | 2026-04-11 | 2026-02-24 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-SB-30 | Stamped Concrete Pattern & Section | 38 | 2026-02-24 | 2026-04-14 | 2026-02-24 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-SB-40 | Tartan Flooring Layout & Details | 38 | 2026-02-24 | 2026-04-14 | 2026-02-24 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-SB-50 | Bike Path Layout & Details | 35 | 2026-02-24 | 2026-04-11 | 2026-02-24 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-SB-60 | Walking Path layout & Details | 35 | 2026-02-24 | 2026-04-11 | 2026-02-24 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-SB-70 | Tree Planting Plan & Details | 35 | 2026-02-24 | 2026-04-11 | 2026-02-24 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-SB-80 | Traffic Sign Location & Details | 38 | 2026-02-24 | 2026-04-14 | 2026-02-24 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-SB-90 | Football Playground Layout | 38 | 2026-02-24 | 2026-04-14 | 2026-02-24 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-SB-100 | Playground Details | 35 | 2026-02-24 | 2026-04-11 | 2026-02-24 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MECHANICAL DRAWINGS |  | 52 | 2026-03-01 | 2026-05-05 | 2026-03-01 | 2026-05-04 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 9 | 9 | 0 | 0
WATER SUPPLY SYSTEM |  | 31 | 2026-03-01 | 2026-04-11 | 2026-03-01 | 2026-04-09 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-EN-ME-SD-SB-20 | Pump Room Layout | 31 | 2026-03-01 | 2026-04-11 | 2026-03-01 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ME-SD-SB-10 | Cold & Hot Water Piping Layout | 27 | 2026-03-05 | 2026-04-11 | 2026-03-05 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ME-SD-SB-30 | Booster Pump Details | 27 | 2026-03-05 | 2026-04-11 | 2026-03-05 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ME-SD-SB-40 | GRP Water Tank Details | 23 | 2026-03-10 | 2026-04-11 | 2026-03-10 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SEWER AND DRAINAGE SYSTEM |  | 27 | 2026-03-05 | 2026-04-11 | 2026-03-05 | 2026-04-09 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-EN-ME-SD-SB-50 | Drainage Layout | 27 | 2026-03-05 | 2026-04-11 | 2026-03-05 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ME-SD-SB-60 | Floor Drains & Cleanouts Details | 23 | 2026-03-10 | 2026-04-11 | 2026-03-10 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ME-SD-SB-70 | Inspection Chamber Details | 20 | 2026-03-14 | 2026-04-11 | 2026-03-14 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION SYSTEM |  | 44 | 2026-03-10 | 2026-05-05 | 2026-03-10 | 2026-05-04 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-EN-ME-SD-SB-80 | HDPE Pipe Routing | 44 | 2026-03-10 | 2026-05-05 | 2026-03-10 | 2026-05-04 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ME-SD-SB-90 | Irrigation Network Layout | 41 | 2026-03-14 | 2026-05-05 | 2026-03-14 | 2026-05-04 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL DRAWINGS |  | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 11 | 11 | 0 | 0
POWER AND LIGHTING SYSTEM |  | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-EN-EL-SD-SB-10 | Main Distribution Board (MDB) Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-SB-20 | Pump Room Power Panel | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-SB-30 | Street Lighting Power Panel | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-SB-40 | Site Lighting Pole Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELV SYSTEM |  | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-EN-EL-SD-SB-50 | Telecom & Data Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-SB-60 | CCTV Camera Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-SB-70 | Access Control Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-SB-80 | AV System Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE ALARM SYSTEM |  | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-EN-EL-SD-SB-90 | Fire Alarm Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-SB-100 | Detector & Manual Call Point Details | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-SB-110 | Control Panel Wiring Diagram | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SHOP DRAWINGS APPROVALS |  | 92 | 2026-02-19 | 2026-06-17 | 2026-02-19 | 2026-06-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 48 | 48 | 0 | 0
STRUCTURAL DRAWINGS |  | 61 | 2026-02-19 | 2026-05-07 | 2026-02-19 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 8 | 8 | 0 | 0
PROJECT FENCE |  | 55 | 2026-02-19 | 2026-04-30 | 2026-02-19 | 2026-04-29 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-EN-ST-SD-AP-10 | Excavation Drawings | 55 | 2026-02-19 | 2026-04-30 | 2026-02-19 | 2026-04-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ST-SD-AP-20 | Foundation Drawings | 52 | 2026-02-24 | 2026-04-30 | 2026-02-24 | 2026-04-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
TOILET BUILDING |  | 42 | 2026-02-23 | 2026-04-18 | 2026-02-23 | 2026-04-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-EN-ST-SD-AP-30 | Excavation Drawings | 42 | 2026-02-23 | 2026-04-18 | 2026-02-23 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ST-SD-AP-40 | Foundation Drawings | 39 | 2026-02-26 | 2026-04-18 | 2026-02-26 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
WATER STORAGE TANK |  | 40 | 2026-02-25 | 2026-04-18 | 2026-02-25 | 2026-04-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-EN-ST-SD-AP-50 | Excavation Drawings | 40 | 2026-02-25 | 2026-04-18 | 2026-02-25 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ST-SD-AP-60 | Foundation Drawings | 37 | 2026-03-01 | 2026-04-18 | 2026-03-01 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SEPTIC TANK |  | 54 | 2026-03-01 | 2026-05-07 | 2026-03-01 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-EN-ST-SD-AP-70 | Reinforcement Detail Drawings | 54 | 2026-03-01 | 2026-05-07 | 2026-03-01 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ST-SD-AP-80 | Concrete Detail Drawings | 51 | 2026-03-04 | 2026-05-07 | 2026-03-04 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL DRAWINGS |  | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 10 | 0 | 0
TOILET BUILDING |  | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 10 | 0 | 0
PG-H-EN-AR-SD-AP-10 | Ground Floor Plan | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-AP-20 | Roof Floor Plan | 35 | 2026-03-03 | 2026-04-18 | 2026-03-03 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-AP-50 | Floor Finish Layout | 33 | 2026-03-05 | 2026-04-18 | 2026-03-05 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-AP-60 | Reflected Ceiling Layout | 33 | 2026-03-05 | 2026-04-18 | 2026-03-05 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-AP-70 | Enlarged Toilets Layout | 33 | 2026-03-05 | 2026-04-18 | 2026-03-05 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-AP-30 | Elevations | 32 | 2026-03-07 | 2026-04-18 | 2026-03-07 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-AP-80 | Doors & Windows Schedule | 32 | 2026-03-07 | 2026-04-18 | 2026-03-07 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-AP-90 | Aluminum Work | 31 | 2026-03-08 | 2026-04-18 | 2026-03-08 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-AP-100 | Cladding Details | 31 | 2026-03-08 | 2026-04-18 | 2026-03-08 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-AP-40 | Sections | 29 | 2026-03-10 | 2026-04-18 | 2026-03-10 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
LANDSCAPE DRAWINGS |  | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 10 | 0 | 0
PG-H-EN-LS-SD-AP-50 | Bike Path Layout & Details | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-AP-60 | Walking Path layout & Details | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-AP-80 | Traffic Sign Location & Details | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-AP-10 | Hardscape Layout Plan | 37 | 2026-03-01 | 2026-04-18 | 2026-03-01 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-AP-40 | Tartan Flooring Layout & Details | 37 | 2026-03-01 | 2026-04-18 | 2026-03-01 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-AP-70 | Tree Planting Plan & Details | 37 | 2026-03-01 | 2026-04-18 | 2026-03-01 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-AP-90 | Football Playground Layout | 37 | 2026-03-01 | 2026-04-18 | 2026-03-01 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-AP-100 | Playground Details | 37 | 2026-03-01 | 2026-04-18 | 2026-03-01 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-AP-20 | Interlock Tile Details | 29 | 2026-03-10 | 2026-04-18 | 2026-03-10 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-AP-30 | Stamped Concrete Pattern & Section | 23 | 2026-03-17 | 2026-04-18 | 2026-03-17 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MECHANICAL DRAWINGS |  | 46 | 2026-03-10 | 2026-05-07 | 2026-03-10 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 9 | 9 | 0 | 0
WATER SUPPLY SYSTEM |  | 26 | 2026-03-10 | 2026-04-14 | 2026-03-10 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-EN-ME-SD-AP-10 | Cold & Hot Water Piping Layout | 26 | 2026-03-10 | 2026-04-14 | 2026-03-10 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ME-SD-AP-30 | Booster Pump Details | 25 | 2026-03-11 | 2026-04-14 | 2026-03-11 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ME-SD-AP-40 | GRP Water Tank Details | 22 | 2026-03-15 | 2026-04-14 | 2026-03-15 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ME-SD-AP-20 | Pump Room Layout | 20 | 2026-03-17 | 2026-04-14 | 2026-03-17 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SEWER AND DRAINAGE SYSTEM |  | 26 | 2026-03-10 | 2026-04-14 | 2026-03-10 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-EN-ME-SD-AP-50 | Drainage Layout | 26 | 2026-03-10 | 2026-04-14 | 2026-03-10 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ME-SD-AP-60 | Floor Drains & Cleanouts Details | 20 | 2026-03-17 | 2026-04-14 | 2026-03-17 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ME-SD-AP-70 | Inspection Chamber Details | 20 | 2026-03-17 | 2026-04-14 | 2026-03-17 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION SYSTEM |  | 43 | 2026-03-14 | 2026-05-07 | 2026-03-14 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-EN-ME-SD-AP-80 | HDPE Pipe Routing | 43 | 2026-03-14 | 2026-05-07 | 2026-03-14 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ME-SD-AP-90 | Irrigation Network Layout | 39 | 2026-03-18 | 2026-05-07 | 2026-03-18 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL DRAWINGS |  | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 11 | 11 | 0 | 0
POWER AND LIGHTING SYSTEM |  | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-EN-EL-SD-AP-10 | Main Distribution Board (MDB) Layout | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-AP-20 | Pump Room Power Panel | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-AP-30 | Street Lighting Power Panel | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-AP-40 | Site Lighting Pole Layout | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELV SYSTEM |  | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-EN-EL-SD-AP-50 | Telecom & Data Layout | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-AP-60 | CCTV Camera Layout | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-AP-70 | Access Control Layout | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-AP-80 | AV System Layout | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE ALARM SYSTEM |  | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-EN-EL-SD-AP-90 | Fire Alarm Layout | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-AP-100 | Detector & Manual Call Point Details | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-AP-110 | Control Panel Wiring Diagram | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MATERIAL SUBMITTALS |  | 111 | 2026-02-17 | 2026-07-06 | 2026-02-17 | 2026-09-01 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 67 | 67 | 0 | 0
LONG LEAD ITEMS |  | 108 | 2026-02-21 | 2026-07-06 | 2026-02-21 | 2026-09-01 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 28 | 28 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 56 | 2026-02-25 | 2026-05-06 | 2026-02-25 | 2026-05-05 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-PR-LL-LS-MS-20 | Benches, Seats (Rectangular & Circular) | 56 | 2026-02-25 | 2026-05-06 | 2026-02-25 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-MS-30 | Fence, gates and accessories | 56 | 2026-02-25 | 2026-05-06 | 2026-02-25 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-MS-10 | Bike and Walk Path Materials | 48 | 2026-03-07 | 2026-05-06 | 2026-03-07 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 47 | 2026-03-08 | 2026-05-06 | 2026-03-08 | 2026-05-05 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-SP-MS-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc) | 47 | 2026-03-08 | 2026-05-06 | 2026-03-08 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-SP-MS-20 | Tartan Floor | 47 | 2026-03-08 | 2026-05-06 | 2026-03-08 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 41 | 2026-03-07 | 2026-04-28 | 2026-03-07 | 2026-04-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-H-PR-LL-CO-MS-10 | Autoclaved Aerated Panel | 41 | 2026-03-07 | 2026-04-28 | 2026-03-07 | 2026-04-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 44 | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-05 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-MT-MS-10 | Metal Doors | 44 | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-MT-MS-20 | Curtain Wall | 44 | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 44 | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-05 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-PB-MS-10 | Booster Pump | 44 | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-PB-MS-20 | GRP Sectional Panel Water Tanks (4x3x3m) | 40 | 2026-03-16 | 2026-05-06 | 2026-03-16 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 60 | 2026-02-21 | 2026-05-07 | 2026-02-21 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-IR-MS-10 | HDPE Pipes | 60 | 2026-02-21 | 2026-05-07 | 2026-02-21 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-IR-MS-20 | Irrigation Control System | 60 | 2026-02-21 | 2026-05-07 | 2026-02-21 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 44 | 2026-05-12 | 2026-07-06 | 2026-05-12 | 2026-09-01 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 16 | 16 | 0 | 0
PG-H-PR-LL-EL-MS-10 | Main Distribution Board(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-20 | Power Panels (Pump, Street Light)(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-30 | Site Lighting Poles(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-40 | Lighting Fixtures(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-70 | Security and Access Control System Materials(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-80 | Fire Alarm System Materials(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-10_R | Main Distribution Board(Remaining) | 8 | 2026-06-25 | 2026-07-04 | 2026-07-11 | 2026-08-03 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-20_R | Power Panels (Pump, Street Light)(Remaining) | 8 | 2026-06-25 | 2026-07-04 | 2026-07-11 | 2026-08-03 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-30_R | Site Lighting Poles(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-11 | 2026-08-03 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-40_R | Lighting Fixtures(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-11 | 2026-07-23 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-11 | 2026-09-01 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-11 | 2026-09-01 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-70_R | Security and Access Control System Materials(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-11 | 2026-09-01 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-80_R | Fire Alarm System Materials(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-08-27 | 2026-09-01 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SHORT LEAD ITEMS |  | 28 | 2026-02-17 | 2026-03-28 | 2026-02-17 | 2026-03-26 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 39 | 39 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 23 | 2026-02-17 | 2026-03-17 | 2026-02-17 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 8 | 8 | 0 | 0
PG-H-PR-SL-LS-MS-10 | Backfilling Materials | 23 | 2026-02-17 | 2026-03-17 | 2026-02-17 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MS-30 | Compacted Natural Ground Soil | 20 | 2026-02-21 | 2026-03-17 | 2026-02-21 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MS-60 | Traffic Signages | 8 | 2026-03-08 | 2026-03-17 | 2026-03-08 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MS-20 | Interlock tiles | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MS-40 | Curb Stone | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MS-50 | Thermoplastic pavement road marking | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MS-70 | Trees | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MS-80 | Lawn | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 28 | 2026-02-17 | 2026-03-28 | 2026-02-17 | 2026-03-26 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-H-PR-SL-CO-MS-10 | Steel Rebar | 17 | 2026-02-17 | 2026-03-10 | 2026-02-17 | 2026-03-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-MS-20 | Concrete | 13 | 2026-02-23 | 2026-03-10 | 2026-02-23 | 2026-03-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-MS-40 | CMU Block | 19 | 2026-03-01 | 2026-03-28 | 2026-03-01 | 2026-03-26 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-MS-50 | Concrete Repair & Protection Materials | 19 | 2026-03-01 | 2026-03-28 | 2026-03-01 | 2026-03-26 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-MS-30 | Screed | 10 | 2026-03-11 | 2026-03-28 | 2026-03-11 | 2026-03-26 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL & FINISHES WORK |  | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PG-H-PR-SL-AR-MS-10 | Ceramic tiles | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MS-20 | Anti-slip Granite tiles | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MS-30 | Epoxy Paint | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MS-40 | Cement Plaster | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MS-50 | Acrylic Paint | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MS-60 | Stone Cladding | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MS-70 | Aluminum Plates | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MS-80 | Phenolic Partition | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MS-90 | Glass Partition | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MS-100 | Gypsum Boards | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MS-110 | Specialities Materials (Toilet accessories, lockers, logo, etc) | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MS-120 | Waterproofing System Materials | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 9 | 2026-03-07 | 2026-03-17 | 2026-03-07 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-PR-SL-MT-MS-20 | Galvanized Steel Roof Scupper | 9 | 2026-03-07 | 2026-03-17 | 2026-03-07 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-MT-MS-30 | Galvanized Steel Cover with frame | 9 | 2026-03-07 | 2026-03-17 | 2026-03-07 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-MT-MS-10 | Galvanized Steel Ladder | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
HVAC WORK |  | 19 | 2026-02-23 | 2026-03-17 | 2026-02-23 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-PR-SL-AC-MS-10 | Split Air Conditioning Unit | 19 | 2026-02-23 | 2026-03-17 | 2026-02-23 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AC-MS-20 | Air Duct | 15 | 2026-02-28 | 2026-03-17 | 2026-02-28 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AC-MS-30 | Diffusers and Grills | 11 | 2026-03-04 | 2026-03-17 | 2026-03-04 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AC-MS-40 | Exhaust fans | 11 | 2026-03-04 | 2026-03-17 | 2026-03-04 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-PR-SL-PB-MS-10 | PPR Pipes & Valves | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-PB-MS-20 | UPCV Pipes | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-PB-MS-30 | Sanitary Drainage Fixtures | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-SL-IR-MS-10 | Gate Valve including valve box | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-IR-MS-20 | Bulbblers and Spreyers | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-H-PR-SL-EL-MS-10 | Wiring Devices Materials | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE FIGHTING WORK |  | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-H-PR-SL-FF-MS-10 | Fire Extinguishers | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MATERIAL APPROVALS |  | 115 | 2026-02-21 | 2026-07-14 | 2026-02-21 | 2026-09-17 | 204439.56 | 204439.56 | 204439.56 | 100% | 100% | 0 | 0 | 0 |  | 67 | 67 | 0 | 0
LONG LEAD ITEMS |  | 112 | 2026-02-25 | 2026-07-14 | 2026-02-25 | 2026-09-17 | 111065.49 | 111065.49 | 111065.49 | 100% | 100% | 0 | 0 | 0 |  | 28 | 28 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 57 | 2026-02-25 | 2026-05-06 | 2026-02-25 | 2026-05-06 | 26079.63 | 26079.63 | 26079.63 | 100% | 100% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-PR-LL-LS-MA-20 | Benches, Seats (Rectangular & Circular) | 57 | 2026-02-25 | 2026-05-06 | 2026-02-25 | 2026-05-06 | 6327.69 | 6327.69 | 6327.69 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-MA-30 | Fence, gates and accessories | 51 | 2026-03-04 | 2026-05-06 | 2026-03-04 | 2026-05-06 | 3290.94 | 3290.94 | 3290.94 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-MA-10 | Bike and Walk Path Materials | 41 | 2026-03-16 | 2026-05-06 | 2026-03-16 | 2026-05-06 | 16461 | 16461 | 16461 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 43 | 2026-03-14 | 2026-05-06 | 2026-03-14 | 2026-05-06 | 38839.5 | 38839.5 | 38839.5 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-SP-MA-20 | Tartan Floor | 43 | 2026-03-14 | 2026-05-06 | 2026-03-14 | 2026-05-06 | 24570 | 24570 | 24570 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-SP-MA-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc) | 42 | 2026-03-15 | 2026-05-06 | 2026-03-15 | 2026-05-06 | 14269.5 | 14269.5 | 14269.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 45 | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-06 | 1417.5 | 1417.5 | 1417.5 | 100% | 100% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-H-PR-LL-CO-MA-10 | Autoclaved Aerated Panel | 45 | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-06 | 1417.5 | 1417.5 | 1417.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 42 | 2026-03-15 | 2026-05-06 | 2026-03-15 | 2026-05-06 | 1902-06-07 05:31 | 889.23 | 889.23 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-MT-MA-10 | Metal Doors | 42 | 2026-03-15 | 2026-05-06 | 2026-03-15 | 2026-05-06 | 1900-05-06 12:43 | 127.53 | 127.53 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-MT-MA-20 | Curtain Wall | 42 | 2026-03-15 | 2026-05-06 | 2026-03-15 | 2026-05-06 | 761.7 | 761.7 | 761.7 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 41 | 2026-03-16 | 2026-05-06 | 2026-03-16 | 2026-05-06 | 3553.95 | 3553.95 | 3553.95 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-PB-MA-10 | Booster Pump | 41 | 2026-03-16 | 2026-05-06 | 2026-03-16 | 2026-05-06 | 1818.3 | 1818.3 | 1818.3 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-PB-MA-20 | GRP Sectional Panel Water Tanks (4x3x3m) | 38 | 2026-03-24 | 2026-05-06 | 2026-03-24 | 2026-05-06 | 1735.65 | 1735.65 | 1735.65 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 55 | 2026-02-28 | 2026-05-06 | 2026-02-28 | 2026-05-06 | 12818.25 | 12818.25 | 12818.25 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-IR-MA-10 | HDPE Pipes | 55 | 2026-02-28 | 2026-05-06 | 2026-02-28 | 2026-05-06 | 8272.5 | 8272.5 | 8272.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-IR-MA-20 | Irrigation Control System | 55 | 2026-02-28 | 2026-05-06 | 2026-02-28 | 2026-05-06 | 4545.75 | 4545.75 | 4545.75 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 51 | 2026-05-12 | 2026-07-14 | 2026-05-12 | 2026-09-17 | 27467.43 | 27467.43 | 27467.43 | 100% | 100% | 0 | 0 | 0 |  | 16 | 16 | 0 | 0
PG-H-PR-LL-EL-MA-10 | Main Distribution Board(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 1900-12-12 03:07 | 347.13 | 1900-12-12 03:07 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-20 | Power Panels (Pump, Street Light)(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 1900-10-03 16:48 | 277.7 | 277.7 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-30 | Site Lighting Poles(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 1940-10-07 04:19 | 14891.18 | 1940-10-07 04:19 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-40 | Lighting Fixtures(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 897.98 | 897.98 | 897.98 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 702.93 | 702.93 | 702.93 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 685.57 | 685.57 | 685.57 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-70 | Security and Access Control System Materials(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 867.93 | 867.93 | 867.93 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-80 | Fire Alarm System Materials(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 1901-07-09 18:29 | 556.77 | 556.77 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-10_R | Main Distribution Board(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-30 | 2026-09-17 | 1900-05-27 18:29 | 1900-05-27 18:29 | 1900-05-27 18:29 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-20_R | Power Panels (Pump, Street Light)(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-30 | 2026-09-17 | 119.02 | 119.02 | 119.02 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-30_R | Site Lighting Poles(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-30 | 2026-09-17 | 1917-06-20 22:34 | 1917-06-20 22:34 | 1917-06-20 22:34 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-40_R | Lighting Fixtures(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-23 | 2026-07-23 | 1901-01-18 20:24 | 384.85 | 384.85 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-08-27 | 2026-09-17 | 1900-10-19 19:26 | 1900-10-19 19:26 | 1900-10-19 19:26 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-70_R | Security and Access Control System Materials(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-08-27 | 2026-09-17 | 371.97 | 371.97 | 371.97 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-80_R | Fire Alarm System Materials(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-08-27 | 2026-09-17 | 1900-08-25 14:53 | 1900-08-25 14:53 | 1900-08-25 14:53 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 10 | 2026-07-04 | 2026-07-14 | 2026-08-27 | 2026-09-17 | 301.26 | 301.26 | 301.26 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SHORT LEAD ITEMS |  | 25 | 2026-02-21 | 2026-03-26 | 2026-02-21 | 2026-03-26 | 93374.07 | 93374.07 | 93374.07 | 100% | 100% | 0 | 0 | 0 |  | 39 | 39 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 25 | 2026-02-21 | 2026-03-26 | 2026-02-21 | 2026-03-26 | 72133.44 | 72133.44 | 72133.44 | 100% | 100% | 0 | 0 | 0 |  | 8 | 8 | 0 | 0
PG-H-PR-SL-LS-MA-10 | Backfilling Materials | 25 | 2026-02-21 | 2026-03-26 | 2026-02-21 | 2026-03-26 | 19575 | 19575 | 19575 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MA-30 | Compacted Natural Ground Soil | 22 | 2026-02-25 | 2026-03-26 | 2026-02-25 | 2026-03-26 | 3120 | 3120 | 3120 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MA-60 | Traffic Signages | 10 | 2026-03-11 | 2026-03-26 | 2026-03-11 | 2026-03-26 | 198.36 | 198.36 | 198.36 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MA-70 | Trees | 7 | 2026-03-15 | 2026-03-26 | 2026-03-15 | 2026-03-26 | 1913-03-23 22:48 | 4831.95 | 4831.95 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MA-80 | Lawn | 7 | 2026-03-15 | 2026-03-26 | 2026-03-15 | 2026-03-26 | 5460 | 5460 | 5460 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MA-20 | Interlock tiles | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 17494.5 | 17494.5 | 17494.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MA-40 | Curb Stone | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 20928 | 20928 | 20928 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MA-50 | Thermoplastic pavement road marking | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 525.63 | 525.63 | 525.63 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 24 | 2026-02-23 | 2026-03-26 | 2026-02-23 | 2026-03-26 | 1609.47 | 1609.47 | 1609.47 | 100% | 100% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-H-PR-SL-CO-MA-10 | Steel Rebar | 14 | 2026-02-23 | 2026-03-10 | 2026-02-23 | 2026-03-10 | 1901-04-20 19:41 | 476.82 | 476.82 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-MA-20 | Concrete | 9 | 2026-03-01 | 2026-03-10 | 2026-03-01 | 2026-03-10 | 1901-06-01 20:24 | 518.85 | 518.85 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-MA-40 | CMU Block | 15 | 2026-03-05 | 2026-03-26 | 2026-03-05 | 2026-03-26 | 1900-05-03 04:48 | 124.2 | 124.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-MA-50 | Concrete Repair & Protection Materials | 15 | 2026-03-05 | 2026-03-26 | 2026-03-05 | 2026-03-26 | 1901-01-06 | 372 | 372 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-MA-30 | Screed | 1 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 117.6 | 117.6 | 117.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL & FINISHES WORK |  | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 8114.01 | 8114.01 | 8114.01 | 100% | 100% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PG-H-PR-SL-AR-MA-10 | Ceramic tiles | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1901-07-24 22:48 | 571.95 | 571.95 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MA-20 | Anti-slip Granite tiles | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 535.5 | 535.5 | 535.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MA-30 | Epoxy Paint | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1900-04-20 04:19 | 111.18 | 111.18 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MA-40 | Cement Plaster | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1900-08-08 08:53 | 221.37 | 221.37 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MA-50 | Acrylic Paint | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 147.9 | 147.9 | 147.9 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MA-60 | Stone Cladding | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1905-01-25 04:48 | 1852.2 | 1852.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MA-70 | Aluminum Plates | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 182.46 | 182.46 | 182.46 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MA-80 | Phenolic Partition | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1340.4 | 1340.4 | 1340.4 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MA-90 | Glass Partition | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1900-06-03 09:36 | 155.4 | 155.4 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MA-100 | Gypsum Boards | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 188.58 | 188.58 | 188.58 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MA-110 | Specialities Materials (Toilet accessories, lockers, logo, etc) | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1906-03-11 20:53 | 2262.87 | 2262.87 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MA-120 | Waterproofing System Materials | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1901-06-27 04:48 | 544.2 | 544.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 10 | 2026-03-11 | 2026-03-26 | 2026-03-11 | 2026-03-26 | 1901-04-22 21:22 | 478.89 | 478.89 | 100% | 100% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-PR-SL-MT-MA-20 | Galvanized Steel Roof Scupper | 10 | 2026-03-11 | 2026-03-26 | 2026-03-11 | 2026-03-26 | 1900-01-30 07:41 | 31.32 | 31.32 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-MT-MA-30 | Galvanized Steel Cover with frame | 10 | 2026-03-11 | 2026-03-26 | 2026-03-11 | 2026-03-26 | 1900-03-25 17:02 | 85.71 | 85.71 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-MT-MA-10 | Galvanized Steel Ladder | 7 | 2026-03-15 | 2026-03-26 | 2026-03-15 | 2026-03-26 | 1900-12-26 20:38 | 361.86 | 361.86 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
HVAC WORK |  | 20 | 2026-02-28 | 2026-03-26 | 2026-02-28 | 2026-03-26 | 1901-08-28 08:38 | 606.36 | 606.36 | 100% | 100% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-PR-SL-AC-MA-10 | Split Air Conditioning Unit | 20 | 2026-02-28 | 2026-03-26 | 2026-02-28 | 2026-03-26 | 1900-11-04 22:19 | 309.93 | 309.93 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AC-MA-20 | Air Duct | 16 | 2026-03-04 | 2026-03-26 | 2026-03-04 | 2026-03-26 | 1900-06-04 | 156 | 156 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AC-MA-30 | Diffusers and Grills | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1900-03-14 07:26 | 74.31 | 74.31 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AC-MA-40 | Exhaust fans | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 66.12 | 66.12 | 66.12 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 3147.03 | 3147.03 | 3147.03 | 100% | 100% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-PR-SL-PB-MA-10 | PPR Pipes & Valves | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 265.2 | 265.2 | 265.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-PB-MA-20 | UPCV Pipes | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 335.19 | 335.19 | 335.19 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-PB-MA-30 | Sanitary Drainage Fixtures | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2546.64 | 2546.64 | 2546.64 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 6854.64 | 6854.64 | 6854.64 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-SL-IR-MA-10 | Gate Valve including valve box | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 756.3 | 756.3 | 756.3 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-IR-MA-20 | Bulbblers and Spreyers | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1916-09-10 08:10 | 6098.34 | 6098.34 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1901-02-10 12:29 | 407.52 | 407.52 | 100% | 100% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-H-PR-SL-EL-MA-10 | Wiring Devices Materials | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1901-02-10 12:29 | 407.52 | 407.52 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE FIGHTING WORK |  | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1900-01-21 17:02 | 22.71 | 22.71 | 100% | 100% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-H-PR-SL-FF-MA-10 | Fire Extinguishers | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 22.71 | 22.71 | 22.71 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PROCUREMENT |  | 148 | 2026-02-26 | 2026-08-26 | 2026-02-26 |  | 1839956.04 | 1816202.83 | 1839956.04 | 100% | 98.71% | 0 | 0 | 0 |  | 202 | 190 | 12 | 0
LONG LEAD ITEMS |  | 142 | 2026-03-05 | 2026-08-26 | 2026-03-05 |  | 999589.41 | 981462.29 | 999589.41 | 100% | 98.19% | 0 | 0 | 0 |  | 108 | 99 | 9 | 0
PURCHASE ORDER |  | 112 | 2026-03-05 | 2026-07-22 | 2026-03-05 | 2026-09-08 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 28 | 28 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 49 | 2026-03-07 | 2026-05-07 | 2026-03-07 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-PR-LL-LS-PO-20 | Benches, Seats (Rectangular & Circular) | 49 | 2026-03-07 | 2026-05-07 | 2026-03-07 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-PO-30 | Fence, gates and accessories | 43 | 2026-03-14 | 2026-05-07 | 2026-03-14 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-PO-10 | Bike and Walk Path Materials | 33 | 2026-03-30 | 2026-05-07 | 2026-03-30 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 35 | 2026-03-28 | 2026-05-07 | 2026-03-28 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-SP-PO-20 | Tartan Floor | 35 | 2026-03-28 | 2026-05-07 | 2026-03-28 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-SP-PO-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc) | 34 | 2026-03-29 | 2026-05-07 | 2026-03-29 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 39 | 2026-03-18 | 2026-05-07 | 2026-03-18 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-H-PR-LL-CO-PO-10 | Autoclaved Aerated Panel | 39 | 2026-03-18 | 2026-05-07 | 2026-03-18 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 38 | 2026-03-24 | 2026-05-07 | 2026-03-24 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-MT-PO-10 | Metal Doors | 38 | 2026-03-24 | 2026-05-07 | 2026-03-24 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-MT-PO-20 | Curtain Wall | 38 | 2026-03-24 | 2026-05-07 | 2026-03-24 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 34 | 2026-03-29 | 2026-05-07 | 2026-03-29 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-PB-PO-10 | Booster Pump | 34 | 2026-03-29 | 2026-05-07 | 2026-03-29 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-PB-PO-20 | GRP Sectional Panel Water Tanks (4x3x3m) | 33 | 2026-03-30 | 2026-05-07 | 2026-03-30 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 50 | 2026-03-05 | 2026-05-07 | 2026-03-05 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-IR-PO-20 | Irrigation Control System | 50 | 2026-03-05 | 2026-05-07 | 2026-03-05 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-IR-PO-10 | HDPE Pipes | 49 | 2026-03-07 | 2026-05-07 | 2026-03-07 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 59 | 2026-05-11 | 2026-07-22 | 2026-05-11 | 2026-09-08 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 16 | 16 | 0 | 0
PG-H-PR-LL-EL-PO-10 | Main Distribution Board(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-20 | Power Panels (Pump, Street Light)(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-30 | Site Lighting Poles(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-40 | Lighting Fixtures(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-70 | Security and Access Control System Materials(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-80 | Fire Alarm System Materials(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-10_R | Main Distribution Board(Remaining) | 7 | 2026-07-07 | 2026-07-14 | 2026-08-05 | 2026-09-08 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-20_R | Power Panels (Pump, Street Light)(Remaining) | 7 | 2026-07-07 | 2026-07-14 | 2026-08-05 | 2026-09-08 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-30_R | Site Lighting Poles(Remaining) | 7 | 2026-07-07 | 2026-07-14 | 2026-08-05 | 2026-09-08 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-40_R | Lighting Fixtures(Remaining) | 7 | 2026-07-07 | 2026-07-14 | 2026-07-23 | 2026-07-23 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 7 | 2026-07-07 | 2026-07-14 | 2026-08-27 | 2026-09-08 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-70_R | Security and Access Control System Materials(Remaining) | 7 | 2026-07-07 | 2026-07-14 | 2026-08-27 | 2026-09-08 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-80_R | Fire Alarm System Materials(Remaining) | 7 | 2026-07-07 | 2026-07-14 | 2026-08-27 | 2026-09-08 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 7 | 2026-07-15 | 2026-07-22 | 2026-08-27 | 2026-09-08 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MANUFACTURE / FABRICATION |  | 111 | 2026-04-01 | 2026-08-12 | 2026-04-01 | 2026-10-02 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 40 | 40 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 65 | 2026-05-05 | 2026-07-23 | 2026-05-05 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 6 | 6 | 0 | 0
PG-H-PR-LL-LS-MF-20 | Benches, Seats (Rectangular & Circular)(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-MF-30 | Fence, gates and accessories(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-MF-10 | Bike and Walk Path Materials(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-MF-20_R | Benches, Seats (Rectangular & Circular)(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-05 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-MF-30_R | Fence, gates and accessories(Remaining) | 5 | 2026-06-25 | 2026-06-30 | 2026-07-23 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-MF-10_R | Bike and Walk Path Materials(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-07-30 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 65 | 2026-05-05 | 2026-07-23 | 2026-05-05 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-PR-LL-SP-MF-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc)(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-SP-MF-20 | Tartan Floor(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-SP-MF-10_R | Football Playground Materials (Flooring, goal post, nets, paints, etc)(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-07-30 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-SP-MF-20_R | Tartan Floor(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-07-30 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 79 | 2026-04-01 | 2026-07-06 | 2026-04-01 | 2026-06-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-CO-MF-10 | Autoclaved Aerated Panel(Completed) | 69 | 2026-04-01 | 2026-06-25 | 2026-04-01 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-CO-MF-10_R | Autoclaved Aerated Panel(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-06-24 | 2026-06-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 65 | 2026-05-05 | 2026-07-23 | 2026-05-05 | 2026-10-02 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-PR-LL-MT-MF-10 | Metal Doors(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-MT-MF-20 | Curtain Wall(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-MT-MF-10_R | Metal Doors(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-09-26 | 2026-10-02 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-MT-MF-20_R | Curtain Wall(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-17 | 2026-08-26 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 65 | 2026-05-05 | 2026-07-23 | 2026-05-05 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-PR-LL-PB-MF-10 | Booster Pump(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-PB-MF-20 | GRP Sectional Panel Water Tanks (4x3x3m)(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-PB-MF-10_R | Booster Pump(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-27 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-PB-MF-20_R | GRP Sectional Panel Water Tanks (4x3x3m)(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-27 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 52 | 2026-05-05 | 2026-07-08 | 2026-05-05 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-PR-LL-IR-MF-10 | HDPE Pipes(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-IR-MF-20 | Irrigation Control System(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-IR-MF-10_R | HDPE Pipes(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-08-27 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-IR-MF-20_R | Irrigation Control System(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-08-27 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 76 | 2026-05-12 | 2026-08-12 | 2026-05-12 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 16 | 16 | 0 | 0
PG-H-PR-LL-EL-MF-10 | Main Distribution Board(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-20 | Power Panels (Pump, Street Light)(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-30 | Site Lighting Poles(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-40 | Lighting Fixtures(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-70 | Security and Access Control System Materials(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-80 | Fire Alarm System Materials(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-10_R | Main Distribution Board(Remaining) | 13 | 2026-07-15 | 2026-07-29 | 2026-07-30 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-20_R | Power Panels (Pump, Street Light)(Remaining) | 13 | 2026-07-15 | 2026-07-29 | 2026-07-30 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-30_R | Site Lighting Poles(Remaining) | 25 | 2026-07-15 | 2026-08-12 | 2026-07-30 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-40_R | Lighting Fixtures(Remaining) | 25 | 2026-07-15 | 2026-08-12 | 2026-07-30 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 25 | 2026-07-15 | 2026-08-12 | 2026-08-27 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-70_R | Security and Access Control System Materials(Remaining) | 25 | 2026-07-15 | 2026-08-12 | 2026-08-27 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-80_R | Fire Alarm System Materials(Remaining) | 25 | 2026-07-15 | 2026-08-12 | 2026-08-27 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 13 | 2026-07-23 | 2026-08-06 | 2026-08-27 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
DELIVERY TO SITE |  | 92 | 2026-05-07 | 2026-08-26 | 2026-05-06 |  | 999589.41 | 981462.29 | 999589.41 | 100% | 98.19% | 0 | 0 | 0 |  | 40 | 31 | 9 | 0
EXTERNAL / LANDSCAPE WORK |  | 75 | 2026-05-07 | 2026-08-06 | 2026-05-06 | 2026-10-15 | 234716.67 | 234716.67 | 234716.67 | 100% | 100% | 0 | 0 | 0 |  | 6 | 6 | 0 | 0
PG-H-PR-LL-LS-DL-20 | Benches, Seats (Rectangular & Circular)(Completed) | 38 | 2026-05-07 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 28474.61 | 28474.61 | 28474.61 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-DL-30 | Fence, gates and accessories(Completed) | 38 | 2026-05-07 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 11847.38 | 11847.38 | 11847.38 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-DL-10 | Bike and Walk Path Materials(Completed) | 38 | 2026-05-07 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 103704.3 | 103704.3 | 103704.3 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-DL-30_R | Fence, gates and accessories(Remaining) | 5 | 2026-07-01 | 2026-07-06 | 2026-07-22 | 2026-09-19 | 17771.08 | 17771.08 | 17771.08 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-DL-20_R | Benches, Seats (Rectangular & Circular)(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-20 | 2026-10-15 | 28474.61 | 28474.61 | 28474.61 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-DL-10_R | Bike and Walk Path Materials(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-06 | 2026-10-13 | 44444.7 | 44444.7 | 44444.7 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 75 | 2026-05-07 | 2026-08-06 | 2026-05-06 | 2026-10-15 | 349555.5 | 349555.5 | 349555.5 | 100% | 100% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-PR-LL-SP-DL-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc)(Completed) | 38 | 2026-05-07 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 64212.75 | 64212.75 | 64212.75 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-SP-DL-20 | Tartan Floor(Completed) | 38 | 2026-05-07 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 121621.5 | 121621.5 | 121621.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-SP-DL-10_R | Football Playground Materials (Flooring, goal post, nets, paints, etc)(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-06 | 2026-10-15 | 64212.75 | 64212.75 | 64212.75 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-SP-DL-20_R | Tartan Floor(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-06 | 2026-10-15 | 99508.5 | 99508.5 | 99508.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 53 | 2026-05-07 | 2026-07-12 | 2026-05-06 | 2026-07-07 | 12757.5 | 12757.5 | 12757.5 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-CO-DL-10 | Autoclaved Aerated Panel(Completed) | 38 | 2026-05-07 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 7654.5 | 7654.5 | 7654.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-CO-DL-10_R | Autoclaved Aerated Panel(Remaining) | 5 | 2026-07-07 | 2026-07-12 | 2026-07-06 | 2026-07-07 | 5103 | 5103 | 5103 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 75 | 2026-05-07 | 2026-08-06 | 2026-05-06 |  | 8003.07 | 7180.43 | 8003.07 | 100% | 89.72% | 0 | 0 | 0 |  | 4 | 3 | 1 | 0
PG-H-PR-LL-MT-DL-10 | Metal Doors(Completed) | 38 | 2026-05-07 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 459.11 | 459.11 | 459.11 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-MT-DL-20 | Curtain Wall(Completed) | 38 | 2026-05-07 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 2742.12 | 2742.12 | 2742.12 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-MT-DL-10_R | Metal Doors(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-27 | 2026-10-15 | 688.66 | 1901-11-18 15:50 | 688.66 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-MT-DL-20_R | Curtain Wall(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-27 |  | 4113.18 | 3290.54 | 4113.18 | 100% | 80% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PLUMBING WORK |  | 75 | 2026-05-07 | 2026-08-06 | 2026-05-06 | 2026-10-15 | 31985.55 | 31985.55 | 31985.55 | 100% | 100% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-PR-LL-PB-DL-10 | Booster Pump(Completed) | 38 | 2026-05-07 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 6545.88 | 6545.88 | 6545.88 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-PB-DL-20 | GRP Sectional Panel Water Tanks (4x3x3m)(Completed) | 38 | 2026-05-07 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 6248.34 | 6248.34 | 6248.34 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-PB-DL-10_R | Booster Pump(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-27 | 2026-09-21 | 9818.82 | 1926-11-17 19:41 | 9818.82 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-PB-DL-20_R | GRP Sectional Panel Water Tanks (4x3x3m)(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-27 | 2026-10-15 | 9372.51 | 9372.51 | 9372.51 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 58 | 2026-05-07 | 2026-07-18 | 2026-05-06 | 2026-09-04 | 115364.25 | 115364.25 | 115364.25 | 100% | 100% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-PR-LL-IR-DL-10 | HDPE Pipes(Completed) | 38 | 2026-05-07 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 37226.25 | 37226.25 | 37226.25 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-IR-DL-20 | Irrigation Control System(Completed) | 38 | 2026-05-07 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 16364.7 | 16364.7 | 16364.7 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-IR-DL-10_R | HDPE Pipes(Remaining) | 8 | 2026-07-09 | 2026-07-18 | 2026-08-20 | 2026-08-27 | 37226.25 | 37226.25 | 37226.25 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-IR-DL-20_R | Irrigation Control System(Remaining) | 8 | 2026-07-09 | 2026-07-18 | 2026-08-20 | 2026-09-04 | 24547.05 | 24547.05 | 24547.05 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 87 | 2026-05-13 | 2026-08-26 | 2026-05-13 |  | 247206.87 | 229902.39 | 247206.87 | 100% | 93% | 0 | 0 | 0 |  | 16 | 8 | 8 | 0
PG-H-PR-LL-EL-DL-10 | Main Distribution Board(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 1338.93 | 1338.93 | 1338.93 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-DL-20 | Power Panels (Pump, Street Light)(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 1071.14 | 1071.14 | 1071.14 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-DL-30 | Site Lighting Poles(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 57437.42 | 57437.42 | 57437.42 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-DL-40 | Lighting Fixtures(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 3463.64 | 3463.64 | 3463.64 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-DL-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 2711.31 | 2711.31 | 2711.31 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-DL-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 2644.33 | 2644.33 | 2644.33 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-DL-70 | Security and Access Control System Materials(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 3347.73 | 3347.73 | 3347.73 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-DL-80 | Fire Alarm System Materials(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 2147.55 | 2147.55 | 2147.55 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-DL-10_R | Main Distribution Board(Remaining) | 8 | 2026-07-30 | 2026-08-08 | 2026-08-27 |  | 1908-07-20 04:05 | 1907-09-11 18:00 | 3124.17 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-H-PR-LL-EL-DL-20_R | Power Panels (Pump, Street Light)(Remaining) | 8 | 2026-07-30 | 2026-08-08 | 2026-08-27 |  | 2499.34 | 2249.4 | 2499.34 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-H-PR-LL-EL-DL-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 8 | 2026-08-08 | 2026-08-16 | 2026-08-27 |  | 6326.4 | 1915-08-02 18:14 | 6326.4 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-H-PR-LL-EL-DL-30_R | Site Lighting Poles(Remaining) | 12 | 2026-08-13 | 2026-08-26 | 2026-08-20 |  | 134020.66 | 120618.59 | 134020.66 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-H-PR-LL-EL-DL-40_R | Lighting Fixtures(Remaining) | 12 | 2026-08-13 | 2026-08-26 | 2026-08-20 |  | 8081.83 | 1919-11-29 15:36 | 8081.83 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-H-PR-LL-EL-DL-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 12 | 2026-08-13 | 2026-08-26 | 2026-08-27 |  | 6170.09 | 5553.08 | 6170.09 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-H-PR-LL-EL-DL-70_R | Security and Access Control System Materials(Remaining) | 12 | 2026-08-13 | 2026-08-26 | 2026-08-27 |  | 7811.37 | 1919-03-31 05:31 | 7811.37 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-H-PR-LL-EL-DL-80_R | Fire Alarm System Materials(Remaining) | 12 | 2026-08-13 | 2026-08-26 | 2026-08-27 |  | 5010.96 | 4509.86 | 5010.96 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
SHORT LEAD ITEMS |  | 113 | 2026-02-26 | 2026-07-16 | 2026-02-26 |  | 840366.63 | 834740.53 | 840366.63 | 100% | 99.33% | 0 | 0 | 0 |  | 94 | 91 | 3 | 0
MATERIAL SUBMITTALS |  | 0 |  |  |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
PURCHASE ORDER |  | 101 | 2026-02-26 | 2026-07-02 | 2026-02-26 | 2026-08-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 47 | 47 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 101 | 2026-02-26 | 2026-07-02 | 2026-02-26 | 2026-08-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PG-H-PR-SL-LS-PO-10 | Backfilling Materials | 44 | 2026-02-26 | 2026-04-23 | 2026-02-26 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-PO-30 | Compacted Natural Ground Soil | 42 | 2026-03-01 | 2026-04-23 | 2026-03-01 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-PO-20 | Interlock tiles | 27 | 2026-03-30 | 2026-04-30 | 2026-03-30 | 2026-04-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-PO-40 | Curb Stone | 22 | 2026-04-05 | 2026-04-30 | 2026-04-05 | 2026-04-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-PO-50 | Thermoplastic pavement road marking(Completed) | 36 | 2026-05-10 | 2026-06-25 | 2026-05-10 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-PO-60 | Traffic Signages(Completed) | 36 | 2026-05-10 | 2026-06-25 | 2026-05-10 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-PO-70 | Trees(Completed) | 36 | 2026-05-10 | 2026-06-25 | 2026-05-10 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-PO-80 | Lawn(Completed) | 36 | 2026-05-10 | 2026-06-25 | 2026-05-10 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-PO-50_R | Thermoplastic pavement road marking(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-20 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-PO-60_R | Traffic Signages(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-20 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-PO-70_R | Trees(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-20 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-PO-80_R | Lawn(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-20 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 41 | 2026-03-02 | 2026-04-23 | 2026-03-02 | 2026-04-22 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-H-PR-SL-CO-PO-10 | Steel Rebar | 41 | 2026-03-02 | 2026-04-23 | 2026-03-02 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-PO-20 | Concrete | 36 | 2026-03-08 | 2026-04-23 | 2026-03-08 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-PO-40 | CMU Block | 33 | 2026-03-11 | 2026-04-23 | 2026-03-11 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-PO-50 | Concrete Repair & Protection Materials | 32 | 2026-03-12 | 2026-04-23 | 2026-03-12 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-PO-30 | Screed | 23 | 2026-03-28 | 2026-04-23 | 2026-03-28 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL & FINISHES WORK |  | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PG-H-PR-SL-AR-PO-10 | Ceramic tiles | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-PO-20 | Anti-slip Granite tiles | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-PO-30 | Epoxy Paint | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-PO-40 | Cement Plaster | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-PO-50 | Acrylic Paint | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-PO-60 | Stone Cladding | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-PO-70 | Aluminum Plates | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-PO-80 | Phenolic Partition | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-PO-90 | Glass Partition | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-PO-100 | Gypsum Boards | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-PO-110 | Specialities Materials (Toilet accessories, lockers, logo, etc) | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-PO-120 | Waterproofing System Materials | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-PR-SL-MT-PO-10 | Galvanized Steel Ladder | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-MT-PO-20 | Galvanized Steel Roof Scupper | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-MT-PO-30 | Galvanized Steel Cover with frame | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
HVAC WORK |  | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-PR-SL-AC-PO-10 | Split Air Conditioning Unit | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AC-PO-20 | Air Duct | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AC-PO-30 | Diffusers and Grills | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AC-PO-40 | Exhaust fans | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-PR-SL-PB-PO-10 | PPR Pipes & Valves | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-PB-PO-20 | UPCV Pipes | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-PB-PO-30 | Sanitary Drainage Fixtures | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 47 | 2026-05-05 | 2026-07-02 | 2026-05-05 | 2026-08-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-PR-SL-IR-PO-10 | Gate Valve including valve box(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-IR-PO-20 | Bulbblers and Spreyers(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-IR-PO-10_R | Gate Valve including valve box(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-20 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-IR-PO-20_R | Bulbblers and Spreyers(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-20 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 41 | 2026-05-12 | 2026-07-02 | 2026-05-12 | 2026-08-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-SL-EL-PO-10 | Wiring Devices Materials(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-EL-PO-10_R | Wiring Devices Materials(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-27 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE FIGHTING WORK |  | 41 | 2026-05-12 | 2026-07-02 | 2026-05-12 | 2026-08-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-SL-FF-PO-10 | Fire Extinguishers(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-FF-PO-10_R | Fire Extinguishers(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-20 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
DELIVERY TO SITE |  | 111 | 2026-03-01 | 2026-07-16 | 2026-03-01 |  | 840366.63 | 834740.53 | 840366.63 | 100% | 99.33% | 0 | 0 | 0 |  | 47 | 44 | 3 | 0
EXTERNAL / LANDSCAPE WORK |  | 111 | 2026-03-01 | 2026-07-16 | 2026-03-01 |  | 649200.96 | 643574.86 | 649200.96 | 100% | 99.13% | 0 | 0 | 0 |  | 12 | 9 | 3 | 0
PG-H-PR-SL-LS-DL-10 | Backfilling Materials | 43 | 2026-03-01 | 2026-04-23 | 2026-03-01 | 2026-04-24 | 176175 | 176175 | 176175 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-DL-30 | Compacted Natural Ground Soil | 41 | 2026-03-03 | 2026-04-23 | 2026-03-03 | 2026-04-24 | 28080 | 28080 | 28080 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-DL-20 | Interlock tiles | 12 | 2026-04-30 | 2026-05-13 | 2026-04-30 | 2026-05-13 | 157450.5 | 157450.5 | 157450.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-DL-40 | Curb Stone | 12 | 2026-04-30 | 2026-05-13 | 2026-04-30 | 2026-05-13 | 188352 | 188352 | 188352 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-DL-50 | Thermoplastic pavement road marking(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 1419.2 | 1419.2 | 1419.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-DL-60 | Traffic Signages(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 535.57 | 535.57 | 535.57 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-DL-70 | Trees(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 13046.27 | 13046.27 | 13046.27 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-DL-80 | Lawn(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 24570 | 24570 | 24570 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-DL-50_R | Thermoplastic pavement road marking(Remaining) | 12 | 2026-07-04 | 2026-07-16 | 2026-08-27 | 2026-09-19 | 3311.47 | 3311.47 | 3311.47 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-DL-60_R | Traffic Signages(Remaining) | 12 | 2026-07-04 | 2026-07-16 | 2026-08-27 |  | 1249.67 | 1903-01-28 16:48 | 1249.67 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-H-PR-SL-LS-DL-70_R | Trees(Remaining) | 12 | 2026-07-04 | 2026-07-16 | 2026-08-27 |  | 30441.29 | 27397.16 | 30441.29 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-H-PR-SL-LS-DL-80_R | Lawn(Remaining) | 12 | 2026-07-04 | 2026-07-16 | 2026-08-27 |  | 24570 | 22113 | 24570 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
CONCRETE WORK |  | 52 | 2026-03-10 | 2026-05-13 | 2026-03-10 | 2026-05-13 | 14485.23 | 14485.23 | 14485.23 | 100% | 100% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-H-PR-SL-CO-DL-20 | Concrete | 35 | 2026-03-10 | 2026-04-23 | 2026-03-10 | 2026-04-24 | 4669.65 | 4669.65 | 4669.65 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-DL-10 | Steel Rebar | 12 | 2026-04-23 | 2026-05-06 | 2026-04-23 | 2026-05-06 | 4291.38 | 4291.38 | 4291.38 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-DL-30 | Screed | 18 | 2026-04-23 | 2026-05-13 | 2026-04-23 | 2026-05-13 | 1058.4 | 1058.4 | 1058.4 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-DL-40 | CMU Block | 18 | 2026-04-23 | 2026-05-13 | 2026-04-23 | 2026-05-13 | 1117.8 | 1117.8 | 1117.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-DL-50 | Concrete Repair & Protection Materials | 18 | 2026-04-23 | 2026-05-13 | 2026-04-23 | 2026-05-13 | 3348 | 3348 | 3348 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL & FINISHES WORK |  | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 73026.09 | 73026.09 | 73026.09 | 100% | 100% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PG-H-PR-SL-AR-DL-10 | Ceramic tiles | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 5147.55 | 5147.55 | 5147.55 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-DL-20 | Anti-slip Granite tiles | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 4819.5 | 4819.5 | 4819.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-DL-30 | Epoxy Paint | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 1000.62 | 1000.62 | 1000.62 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-DL-40 | Cement Plaster | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 1992.33 | 1992.33 | 1992.33 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-DL-50 | Acrylic Paint | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 1331.1 | 1331.1 | 1331.1 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-DL-60 | Stone Cladding | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 16669.8 | 16669.8 | 16669.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-DL-70 | Aluminum Plates | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 1642.14 | 1642.14 | 1642.14 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-DL-80 | Phenolic Partition | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 12063.6 | 12063.6 | 12063.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-DL-90 | Glass Partition | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 1398.6 | 1398.6 | 1398.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-DL-100 | Gypsum Boards | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 1697.22 | 1697.22 | 1697.22 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-DL-110 | Specialities Materials (Toilet accessories, lockers, logo, etc) | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 20365.83 | 20365.83 | 20365.83 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-DL-120 | Waterproofing System Materials | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 4897.8 | 4897.8 | 4897.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 4310.01 | 4310.01 | 4310.01 | 100% | 100% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-PR-SL-MT-DL-10 | Galvanized Steel Ladder | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 1908-11-29 17:46 | 3256.74 | 3256.74 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-MT-DL-20 | Galvanized Steel Roof Scupper | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 281.88 | 281.88 | 281.88 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-MT-DL-30 | Galvanized Steel Cover with frame | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 771.39 | 771.39 | 771.39 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
HVAC WORK |  | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 5457.24 | 5457.24 | 5457.24 | 100% | 100% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-PR-SL-AC-DL-10 | Split Air Conditioning Unit | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 1907-08-20 08:53 | 2789.37 | 2789.37 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AC-DL-20 | Air Duct | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 1903-11-04 | 1404 | 1404 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AC-DL-30 | Diffusers and Grills | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 668.79 | 668.79 | 668.79 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AC-DL-40 | Exhaust fans | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 595.08 | 595.08 | 595.08 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 28323.27 | 28323.27 | 28323.27 | 100% | 100% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-PR-SL-PB-DL-10 | PPR Pipes & Valves | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 2386.8 | 2386.8 | 2386.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-PB-DL-20 | UPCV Pipes | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 3016.71 | 3016.71 | 3016.71 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-PB-DL-30 | Sanitary Drainage Fixtures | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 22919.76 | 22919.76 | 22919.76 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 58 | 2026-05-06 | 2026-07-16 | 2026-05-06 | 2026-10-15 | 61691.76 | 61691.76 | 61691.76 | 100% | 100% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-PR-SL-IR-DL-10 | Gate Valve including valve box(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 3403.35 | 3403.35 | 3403.35 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-IR-DL-20 | Bulbblers and Spreyers(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 27442.53 | 27442.53 | 27442.53 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-IR-DL-10_R | Gate Valve including valve box(Remaining) | 12 | 2026-07-04 | 2026-07-16 | 2026-08-20 | 2026-10-15 | 3403.35 | 3403.35 | 3403.35 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-IR-DL-20_R | Bulbblers and Spreyers(Remaining) | 12 | 2026-07-04 | 2026-07-16 | 2026-08-27 | 2026-10-15 | 27442.53 | 27442.53 | 27442.53 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 46 | 2026-05-20 | 2026-07-16 | 2026-05-20 | 2026-10-15 | 3667.68 | 3667.68 | 3667.68 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-SL-EL-DL-10 | Wiring Devices Materials(Completed) | 27 | 2026-05-20 | 2026-06-24 | 2026-05-20 | 2026-06-24 | 1100.3 | 1100.3 | 1100.3 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-EL-DL-10_R | Wiring Devices Materials(Remaining) | 12 | 2026-07-04 | 2026-07-16 | 2026-09-26 | 2026-10-15 | 2567.38 | 2567.38 | 2567.38 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE FIGHTING WORK |  | 46 | 2026-05-20 | 2026-07-16 | 2026-05-20 | 2026-10-15 | 1900-07-22 09:22 | 1900-07-22 09:22 | 1900-07-22 09:22 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-SL-FF-DL-10 | Fire Extinguishers(Completed) | 27 | 2026-05-20 | 2026-06-24 | 2026-05-20 | 2026-06-24 | 61.32 | 61.32 | 61.32 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-FF-DL-10_R | Fire Extinguishers(Remaining) | 12 | 2026-07-04 | 2026-07-16 | 2026-10-03 | 2026-10-15 | 143.07 | 143.07 | 143.07 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONSTRUCTION STAGE |  | 198 | 2026-04-05 | 2026-11-26 | 2026-04-05 |  | 3836982.53 | 3434319.44 | 4088791.2 | 93.84% | 83.99% | 5964 | 5398 | 4553 |  | 129 | 62 | 53 | 14
PLAYGROUND AND LANDSCAPING WORKS |  | 198 | 2026-04-05 | 2026-11-26 | 2026-04-05 |  | 3508488.95 | 3160875.18 | 3760297.62 | 93.3% | 84.06% | 4256 | 3690 | 3096 |  | 91 | 41 | 39 | 11
CUT AND FILL |  | 28 | 2026-04-05 | 2026-05-06 | 2026-04-05 | 2026-05-06 | 453900 | 453900 | 453900 | 100% | 100% | 376 | 376 | 376 |  | 3 | 3 | 0 | 0
PG-H-CON-EX-CF-10 | Existing Soil Excavation Works | 26 | 2026-04-05 | 2026-05-04 | 2026-04-05 | 2026-05-04 | 125280 | 125280 | 125280 | 100% | 100% | 172 | 172 | 172 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-CF-20 | Soil Replacement Works | 21 | 2026-04-12 | 2026-05-05 | 2026-04-12 | 2026-05-05 | 62400 | 62400 | 62400 | 100% | 100% | 100 | 100 | 100 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-CF-30 | Levelling & Backfilling Works | 18 | 2026-04-16 | 2026-05-06 | 2026-04-16 | 2026-05-06 | 266220 | 266220 | 266220 | 100% | 100% | 104 | 104 | 104 | No | 1 | 1 | 0 | 0
PLAYGROUND WORKS |  | 178 | 2026-04-19 | 2026-11-17 | 2026-04-19 |  | 744930.58 | 701267.82 | 781940.4 | 95.27% | 89.68% | 864 | 735 | 742 |  | 14 | 8 | 5 | 1
FOOTBALL PLAYGROUND WORKS |  | 178 | 2026-04-19 | 2026-11-17 | 2026-04-19 |  | 744930.58 | 701267.82 | 781940.4 | 95.27% | 89.68% | 864 | 735 | 742 |  | 14 | 8 | 5 | 1
PG-H-CON-EX-FB-10 | Subgrade Preparation and Compaction | 16 | 2026-04-19 | 2026-05-06 | 2026-04-19 | 2026-05-06 | 23667 | 23667 | 23667 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-FB-20 | Sub-Base Laying and Compaction | 12 | 2026-04-23 | 2026-05-06 | 2026-04-23 | 2026-05-06 | 23667 | 23667 | 23667 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-FB-30 | Base Course Laying and Compaction | 33 | 2026-05-06 | 2026-06-17 | 2026-05-06 | 2026-06-17 | 23667 | 23667 | 23667 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-FB-70 | Topsoil Placement(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 7100.1 | 7100.1 | 7100.1 | 100% | 100% | 25 | 25 | 25 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-FB-40 | Tartan flooring(Completed) | 7 | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 147420 | 147420 | 147420 | 100% | 100% | 19 | 19 | 19 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-FB-80 | Fine Grading & Leveling | 15 | 2026-06-25 | 2026-07-12 | 2026-07-12 | 2026-08-14 | 23667 | 23667 | 23667 | 100% | 100% | 76 | 76 | 76 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-FB-70_R | Topsoil Placement(Remaining) | 14 | 2026-07-13 | 2026-07-28 | 2026-07-30 | 2026-08-14 | 16566.9 | 16566.9 | 16566.9 | 100% | 100% | 59 | 59 | 59 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-FB-50 | Goal Post Foundation | 17 | 2026-07-29 | 2026-08-17 | 2026-08-20 | 2026-10-15 | 35500.5 | 35500.5 | 35500.5 | 100% | 100% | 100 | 100 | 100 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-FB-120 | Installation of Lighting System | 13 | 2026-08-18 | 2026-09-01 | 2026-08-27 |  | 48720 | 38976 | 48720 | 100% | 80% | 32 | 32 | 26 | No | 1 | 0 | 1 | 0
PG-H-CON-EX-FB-90 | Turfing / Seeding Works | 12 | 2026-09-02 | 2026-09-15 | 2026-08-14 |  | 1964-10-17 | 18933.6 | 23667 | 100% | 80% | 48 | 48 | 38 | No | 1 | 0 | 1 | 0
PG-H-CON-EX-FB-40_R | Tartan flooring(Remaining) | 15 | 2026-09-16 | 2026-10-04 | 2026-08-06 |  | 343980 | 309582 | 343980 | 100% | 90% | 45 | 45 | 40 | No | 1 | 0 | 1 | 0
PG-H-CON-EX-FB-60 | Goal Post Installation & Alignment | 13 | 2026-10-05 | 2026-10-19 | 2026-08-20 |  | 27308.08 | 28400.4 | 35500.5 | 76.92% | 80% | 56 | 43 | 45 | No | 1 | 0 | 1 | 0
PG-H-CON-EX-FB-110 | Install Playground Benches | 15 | 2026-10-20 | 2026-11-05 | 2026-08-27 |  | 0 | 4120.32 | 5150.4 | 0% | 80% | 32 | 0 | 26 | No | 1 | 0 | 1 | 0
PG-H-CON-EX-FB-100 | Markings and Signages | 10 | 2026-11-07 | 2026-11-17 |  |  | 0 | 0 | 23667 | 0% | 0% | 84 | 0 | 0 | No | 1 | 0 | 0 | 1
GENERAL SITE WORKS |  | 188 | 2026-04-16 | 2026-11-26 | 2026-04-16 |  | 1201902.36 | 907871.66 | 1224114.42 | 98.19% | 74.17% | 1996 | 1673 | 1226 |  | 47 | 14 | 28 | 5
FENCE WORKS |  | 101 | 2026-04-16 | 2026-08-16 | 2026-04-16 | 2026-10-15 | 65818.8 | 65818.8 | 65818.8 | 100% | 100% | 336 | 336 | 336 |  | 5 | 5 | 0 | 0
PG-H-CON-EX-GN-FN-10 | Excavation for fence foundation | 3 | 2026-04-16 | 2026-04-19 | 2026-04-16 | 2026-04-19 | 13163.76 | 13163.76 | 13163.76 | 100% | 100% | 92 | 92 | 92 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-GN-FN-20 | Concrete Foundations for Fence | 9 | 2026-07-13 | 2026-07-22 | 2026-08-13 | 2026-08-20 | 13163.76 | 1936-01-14 18:14 | 13163.76 | 100% | 100% | 68 | 68 | 68 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-GN-FN-30 | Installation of Galvanized Steel Posts & Framing | 9 | 2026-07-23 | 2026-08-02 | 2026-08-27 | 2026-10-14 | 13163.76 | 1936-01-14 18:14 | 13163.76 | 100% | 100% | 56 | 56 | 56 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-GN-FN-40 | Fixing of Chain Link Mesh, Tensioning & Bracing | 8 | 2026-08-03 | 2026-08-11 | 2026-09-27 | 2026-10-15 | 13163.76 | 13163.76 | 13163.76 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-GN-FN-50 | Installation of Gates | 4 | 2026-08-12 | 2026-08-16 | 2026-10-05 | 2026-10-15 | 13163.76 | 13163.76 | 13163.76 | 100% | 100% | 72 | 72 | 72 | No | 1 | 1 | 0 | 0
MECHANICAL WORK |  | 71 | 2026-05-12 | 2026-08-06 | 2026-05-12 |  | 421027.74 | 335030.68 | 421027.74 | 100% | 79.57% | 476 | 476 | 318 |  | 13 | 3 | 7 | 3
STORM WATER AND UTILITY WORK |  | 69 | 2026-05-12 | 2026-08-04 | 2026-05-12 |  | 27252 | 16144.8 | 27252 | 100% | 59.24% | 300 | 300 | 185 |  | 8 | 2 | 3 | 3
PG-H-CON-EX-GN-M-10 | Excavation | 2 | 2026-05-12 | 2026-05-13 | 2026-05-12 | 2026-05-13 | 3096 | 3096 | 3096 | 100% | 100% | 92 | 92 | 92 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-GN-M-20 | Bedding preparation & level control(Completed) | 27 | 2026-05-20 | 2026-06-24 | 2026-05-20 | 2026-06-24 | 1032 | 1032 | 1032 | 100% | 100% | 16 | 16 | 16 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-GN-M-20_R | Bedding preparation & level control(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-08-14 |  | 1032 | 1902-07-16 19:12 | 1032 | 100% | 90% | 16 | 16 | 14 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-M-30 | Manhole Installation | 5 | 2026-07-07 | 2026-07-12 | 2026-08-27 |  | 5160 | 1912-09-17 | 5160 | 100% | 90% | 48 | 48 | 43 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-M-40 | 150 mm uPVC pipe laying & jointing | 4 | 2026-07-13 | 2026-07-16 | 2026-10-13 |  | 10740 | 1917-08-22 | 10740 | 100% | 60% | 32 | 32 | 19 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-M-50 | Concrete Encasement | 3 | 2026-07-18 | 2026-07-20 |  |  | 2064 | 0 | 2064 | 100% | 0% | 24 | 24 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-CON-EX-GN-M-60 | Backfilling & Compaction | 3 | 2026-07-21 | 2026-07-23 |  |  | 2064 | 0 | 2064 | 100% | 0% | 48 | 48 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-CON-EX-GN-M-70 | Surface Reinstatement & Civil Works | 4 | 2026-08-01 | 2026-08-04 |  |  | 2064 | 0 | 2064 | 100% | 0% | 24 | 24 | 0 | Yes | 1 | 0 | 0 | 1
IRRIGATION SYSTEM WORKS |  | 51 | 2026-06-02 | 2026-07-30 | 2026-06-02 |  | 393457.8 | 318758.7 | 393457.8 | 100% | 81.01% | 144 | 144 | 120 |  | 4 | 1 | 3 | 0
PG-H-CON-EX-GN-M-80 | Installation of HDPE Irrigation Pipe Network with Gate Valve and Box(Completed) | 20 | 2026-06-02 | 2026-06-24 | 2026-06-02 | 2026-06-24 | 72230.4 | 72230.4 | 72230.4 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-GN-M-80_R | Installation of HDPE Irrigation Pipe Network with Gate Valve and Box(Remaining) | 3 | 2026-07-21 | 2026-07-23 | 2026-08-14 |  | 108345.6 | 97511.04 | 108345.6 | 100% | 90% | 48 | 48 | 43 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-M-90 | Installation of Irrigation Control System | 3 | 2026-07-25 | 2026-07-27 | 2026-08-26 |  | 90915 | 2074-03-27 12:00 | 90915 | 100% | 70% | 32 | 32 | 22 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-M-100 | Installation of Bubblers and Sprinklers | 3 | 2026-07-28 | 2026-07-30 | 2026-10-10 |  | 121966.8 | 2133-09-30 18:14 | 121966.8 | 100% | 70% | 32 | 32 | 22 | Yes | 1 | 0 | 1 | 0
FIRE PROTECTION SYSTEM |  | 2 | 2026-08-05 | 2026-08-06 | 2026-10-11 |  | 317.94 | 127.18 | 317.94 | 100% | 40% | 32 | 32 | 13 |  | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-M-110 | Fire Extinguisher Installation | 2 | 2026-08-05 | 2026-08-06 | 2026-10-11 |  | 317.94 | 127.18 | 317.94 | 100% | 40% | 32 | 32 | 13 | Yes | 1 | 0 | 1 | 0
ELECTRICAL WORK |  | 127 | 2026-05-20 | 2026-10-20 | 2026-05-20 |  | 538652.58 | 346426.19 | 539251.68 | 99.89% | 64.24% | 784 | 764 | 338 |  | 21 | 3 | 18 | 0
POWER, LIGHTING & GROUNDING |  | 92 | 2026-05-20 | 2026-09-08 | 2026-05-20 |  | 482181.48 | 329305.13 | 482181.48 | 100% | 68.29% | 376 | 376 | 215 |  | 10 | 3 | 7 | 0
PG-H-CON-EX-GN-E-10 | Excavation(Completed) | 27 | 2026-05-20 | 2026-06-24 | 2026-05-20 | 2026-06-24 | 63819.36 | 63819.36 | 63819.36 | 100% | 100% | 46 | 46 | 46 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-GN-E-20 | Foundation Work for Site Lighting Poles(Completed) | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 51055.49 | 51055.49 | 51055.49 | 100% | 100% | 20 | 20 | 20 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-GN-E-10_R | Excavation(Remaining) | 1 | 2026-08-04 | 2026-08-04 | 2026-07-16 | 2026-08-27 | 63819.36 | 63819.36 | 63819.36 | 100% | 100% | 46 | 46 | 46 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-GN-E-20_R | Foundation Work for Site Lighting Poles(Remaining) | 4 | 2026-08-05 | 2026-08-09 | 2026-08-20 |  | 119129.47 | 2160-12-04 13:55 | 119129.47 | 100% | 80% | 48 | 48 | 38 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-E-30 | Lightning Protection System (LPS) | 3 | 2026-08-17 | 2026-08-19 | 2026-10-10 |  | 1922-08-17 | 1906-10-14 12:00 | 8265 | 100% | 30% | 32 | 32 | 10 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-E-40 | KWH Meter and MDB Installation | 2 | 2026-08-20 | 2026-08-22 | 2026-10-11 |  | 1912-07-21 16:48 | 1903-10-07 00:14 | 4586.7 | 100% | 30% | 32 | 32 | 10 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-E-50 | Power Panels and Distribution Boards | 5 | 2026-08-23 | 2026-08-27 | 2026-10-11 |  | 1947-08-18 21:36 | 1914-04-15 08:53 | 17397.9 | 100% | 30% | 40 | 40 | 12 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-E-60 | Site Lighting Poles Installation | 3 | 2026-08-29 | 2026-08-31 | 2026-10-12 |  | 2249-06-16 17:17 | 2004-10-31 14:53 | 127638.72 | 100% | 30% | 40 | 40 | 12 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-E-70 | Wiring Works | 3 | 2026-09-01 | 2026-09-03 | 2026-10-10 |  | 1911-07-25 | 1903-06-20 04:48 | 4224 | 100% | 30% | 32 | 32 | 10 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-E-80 | Lighting Fixtures with outlets Installation | 4 | 2026-09-05 | 2026-09-08 | 2026-10-13 |  | 1960-11-25 11:31 | 1918-04-08 15:22 | 22245.48 | 100% | 30% | 40 | 40 | 12 | Yes | 1 | 0 | 1 | 0
ELV SYSTEMS (TELECOM, DATA, AV & CCTV) |  | 25 | 2026-09-09 | 2026-10-08 | 2026-10-10 |  | 2018-02-15 | 1935-06-08 19:12 | 43146 | 100% | 30% | 272 | 272 | 82 |  | 7 | 0 | 7 | 0
PG-H-CON-EX-GN-E-90 | ELV Containment & Cabling Works | 3 | 2026-09-09 | 2026-09-12 | 2026-10-11 |  | 1901-09-10 19:12 | 1900-07-03 22:34 | 619.8 | 100% | 30% | 40 | 40 | 12 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-E-100 | Fiber Optic Pull Box Installation | 3 | 2026-09-13 | 2026-09-15 | 2026-10-12 |  | 1901-09-10 19:12 | 1900-07-03 22:34 | 619.8 | 100% | 30% | 32 | 32 | 10 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-E-110 | Telephone and Data Outlet Installation | 4 | 2026-09-16 | 2026-09-20 | 2026-10-12 |  | 1910-03-06 19:12 | 1903-01-19 15:22 | 3718.8 | 100% | 30% | 40 | 40 | 12 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-E-120 | Telecom Equipment and AV HDMI Installation | 4 | 2026-09-21 | 2026-09-26 | 2026-10-13 |  | 1941-09-30 02:53 | 1912-07-09 17:46 | 15249.12 | 100% | 30% | 40 | 40 | 12 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-E-130 | CCTV Rack / Cabinet Installation | 4 | 2026-09-27 | 2026-09-30 | 2026-10-10 |  | 1903-12-16 11:31 | 1901-03-08 22:34 | 1446.48 | 100% | 30% | 40 | 40 | 12 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-E-140 | NVR and CCTV Monitor Installation | 4 | 2026-10-01 | 2026-10-05 | 2026-10-10 |  | 1918-02-06 | 1905-06-05 14:24 | 6612 | 100% | 30% | 40 | 40 | 12 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-E-150 | IP Camera Installation | 3 | 2026-10-06 | 2026-10-08 | 2026-10-10 |  | 1940-09-26 | 1912-03-21 | 14880 | 100% | 30% | 40 | 40 | 12 | Yes | 1 | 0 | 1 | 0
FIRE ALARM SYSTEM |  | 32 | 2026-09-13 | 2026-10-20 | 2026-10-10 |  | 1936-06-24 02:24 | 1911-06-08 06:14 | 13924.2 | 95.7% | 30% | 136 | 116 | 41 |  | 4 | 0 | 4 | 0
PG-H-CON-EX-GN-E-160 | Fire Alarm Containment & Cabling | 8 | 2026-09-13 | 2026-09-21 | 2026-10-10 |  | 1905-06-05 14:24 | 1901-08-17 01:55 | 1983.6 | 100% | 30% | 32 | 32 | 10 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-E-170 | Fire Alarm Control Panel (FACP) Installation | 8 | 2026-09-22 | 2026-10-01 | 2026-10-10 |  | 1907-03-28 19:12 | 1902-03-03 10:34 | 2644.8 | 100% | 30% | 24 | 24 | 7 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-E-180 | Initiating Devices (Detectors & Manual Pull Station) | 8 | 2026-10-03 | 2026-10-11 | 2026-10-10 |  | 8097.6 | 2429.28 | 8097.6 | 100% | 30% | 40 | 40 | 12 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-E-190 | Notification Appliances (Strobe with Sounder) | 8 | 2026-10-12 | 2026-10-20 | 2026-10-10 |  | 1901-08-21 02:24 | 359.46 | 1198.2 | 50% | 30% | 40 | 20 | 12 | Yes | 1 | 0 | 1 | 0
PARKING WORK |  | 107 | 2026-06-17 | 2026-10-20 | 2026-06-17 |  | 176403.24 | 155574 | 190576.2 | 92.56% | 81.63% | 164 | 97 | 74 |  | 4 | 2 | 1 | 1
PG-H-CON-EX-GN-PR-20 | Interlock tiles(Completed) | 7 | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 38893.5 | 38893.5 | 38893.5 | 100% | 100% | 22 | 22 | 22 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-GN-PR-10 | Installlation of Parking Accessories | 5 | 2026-10-10 | 2026-10-14 | 2026-08-20 |  | 86430 | 69144 | 86430 | 100% | 80% | 32 | 32 | 26 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-PR-20_R | Interlock tiles(Remaining) | 3 | 2026-10-12 | 2026-10-14 | 2026-07-11 | 2026-07-30 | 2030-02-22 12:00 | 47536.5 | 47536.5 | 100% | 100% | 26 | 26 | 26 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-GN-PR-30 | Marking & Signages | 5 | 2026-10-15 | 2026-10-20 |  |  | 1909-09-12 05:46 | 0 | 17716.2 | 20% | 0% | 84 | 17 | 0 | Yes | 1 | 0 | 0 | 1
SERVICE CONNECTION |  | 32 | 2026-10-21 | 2026-11-26 | 2026-07-30 |  | 0 | 5022 | 7440 | 0% | 67.5% | 236 | 0 | 162 |  | 4 | 1 | 2 | 1
PG-H-CON-EX-GN-SC-10 | Excavation & Trench Preparation | 8 | 2026-10-21 | 2026-10-29 | 2026-07-30 | 2026-08-27 | 0 | 2232 | 2232 | 0% | 100% | 92 | 0 | 92 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-GN-SC-20 | HDPE Pipe Laying & Valve Installation | 8 | 2026-10-31 | 2026-11-08 | 2026-08-20 |  | 0 | 1905-03-11 04:48 | 2232 | 0% | 85% | 48 | 0 | 41 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-SC-30 | Connection to City Network | 8 | 2026-11-09 | 2026-11-17 |  |  | 0 | 0 | 1488 | 0% | 0% | 48 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-CON-EX-GN-SC-40 | Backfilling | 8 | 2026-11-18 | 2026-11-26 | 2026-08-27 |  | 0 | 892.8 | 1488 | 0% | 60% | 48 | 0 | 29 | Yes | 1 | 0 | 1 | 0
LANDSCAPING WORKS |  | 139 | 2026-05-31 | 2026-11-09 | 2026-05-30 |  | 1059465.62 | 1085198.47 | 1252052.4 | 84.62% | 86.67% | 392 | 278 | 251 |  | 14 | 7 | 5 | 2
HARDSCAPE WORK |  | 139 | 2026-05-31 | 2026-11-09 | 2026-05-30 |  | 917890.52 | 986918.47 | 1046213.4 | 87.73% | 94.33% | 224 | 161 | 175 |  | 11 | 6 | 4 | 1
PG-H-CON-EX-LS-HS-10 | Curbstone Installation(Completed) | 22 | 2026-05-31 | 2026-06-24 | 2026-05-30 | 2026-06-24 | 251136 | 251136 | 251136 | 100% | 100% | 19 | 19 | 19 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-LS-HS-20 | Interlock Tiles Grey Scale with Black Marble Chips(Completed) | 22 | 2026-05-31 | 2026-06-24 | 2026-05-30 | 2026-06-24 | 36036 | 36036 | 36036 | 100% | 100% | 19 | 19 | 19 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-LS-HS-40 | Bike Path and Walking Path Construction(Completed) | 22 | 2026-05-31 | 2026-06-24 | 2026-05-30 | 2026-06-24 | 181071 | 181071 | 181071 | 100% | 100% | 26 | 26 | 26 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-LS-HS-50 | Install Recycled Precast Concrete Seats(Completed) | 22 | 2026-05-31 | 2026-06-24 | 2026-05-30 | 2026-06-24 | 11599.14 | 11599.14 | 11599.14 | 100% | 100% | 3 | 3 | 3 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-LS-HS-30 | Stamped Concrete Floor(Completed) | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 43470 | 43470 | 43470 | 100% | 100% | 16 | 16 | 16 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-LS-HS-10_R | Curbstone Installation(Remaining) | 8 | 2026-09-10 | 2026-09-19 | 2026-07-22 | 2026-08-27 | 2358-05-22 | 167424 | 167424 | 100% | 100% | 13 | 13 | 13 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-LS-HS-20_R | Interlock Tiles Grey Scale with Black Marble Chips(Remaining) | 13 | 2026-09-20 | 2026-10-05 | 2026-08-27 |  | 54054 | 43243.2 | 54054 | 100% | 80% | 29 | 29 | 23 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-LS-HS-30_R | Stamped Concrete Floor(Remaining) | 15 | 2026-09-20 | 2026-10-07 | 2026-07-30 |  | 2019-01-05 | 39123 | 43470 | 100% | 90% | 16 | 16 | 14 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-LS-HS-40_R | Bike Path and Walking Path Construction(Remaining) | 8 | 2026-10-08 | 2026-10-17 | 2026-07-09 |  | 2254-11-29 09:07 | 140741.55 | 148149 | 87.5% | 95% | 22 | 19 | 21 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-LS-HS-50_R | Install Recycled Precast Concrete Seats(Remaining) | 10 | 2026-10-18 | 2026-10-28 | 2026-07-30 |  | 0 | 73074.58 | 104392.26 | 0% | 70% | 29 | 0 | 20 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-LS-HS-60 | Install Recycled Precast Concrete Trash Bins | 10 | 2026-10-29 | 2026-11-09 |  |  | 0 | 0 | 5412 | 0% | 0% | 32 | 0 | 0 | Yes | 1 | 0 | 0 | 1
SOFTSCAPE WORK |  | 136 | 2026-06-03 | 2026-11-09 | 2026-06-03 |  | 141575.1 | 98280 | 205839 | 68.78% | 47.75% | 168 | 118 | 76 |  | 3 | 1 | 1 | 1
PG-H-CON-EX-LS-SS-20 | Lawn Area Preparation & Planting / Turfing(Completed) | 19 | 2026-06-03 | 2026-06-24 | 2026-06-03 | 2026-06-24 | 54600 | 54600 | 54600 | 100% | 100% | 42 | 42 | 42 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-LS-SS-10 | Planting Trees | 10 | 2026-10-06 | 2026-10-17 |  |  | 86975.1 | 0 | 96639 | 90% | 0% | 84 | 76 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-CON-EX-LS-SS-20_R | Lawn Area Preparation & Planting / Turfing(Remaining) | 7 | 2026-11-02 | 2026-11-09 | 2026-08-27 |  | 0 | 43680 | 54600 | 0% | 80% | 42 | 0 | 34 | Yes | 1 | 0 | 1 | 0
TANK WORKS |  | 107 | 2026-05-13 | 2026-09-19 | 2026-05-13 |  | 48290.4 | 12637.22 | 48290.4 | 100% | 26.17% | 628 | 628 | 501 |  | 13 | 9 | 1 | 3
SEPTIC TANK |  | 91 | 2026-05-13 | 2026-08-31 | 2026-05-13 |  | 7475.22 | 6535.04 | 7475.22 | 100% | 87.42% | 364 | 364 | 289 |  | 8 | 5 | 1 | 2
PG-H-CON-EX-TW-ST-10 | Excavation | 32 | 2026-05-13 | 2026-06-23 | 2026-05-13 | 2026-06-23 | 1900-09-08 04:19 | 252.18 | 252.18 | 100% | 100% | 92 | 92 | 92 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-TW-ST-20 | PCC / Lean Concrete laying | 27 | 2026-05-20 | 2026-06-24 | 2026-05-20 | 2026-06-24 | 1900-06-16 02:53 | 168.12 | 1900-06-16 02:53 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-TW-ST-30 | RCC Foundation(Completed) | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 1902-02-04 13:55 | 766.58 | 766.58 | 100% | 100% | 34 | 34 | 34 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-TW-ST-30_R | RCC Foundation(Remaining) | 6 | 2026-06-25 | 2026-07-01 | 2026-07-30 | 2026-08-27 | 1901-05-25 01:26 | 1901-05-25 01:26 | 511.06 | 100% | 100% | 22 | 22 | 22 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-TW-ST-40 | RCC Wall | 7 | 2026-07-02 | 2026-07-09 | 2026-08-14 | 2026-10-15 | 2757.6 | 1907-07-19 14:24 | 2757.6 | 100% | 100% | 56 | 56 | 56 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-TW-ST-50 | RCC Slab | 7 | 2026-07-11 | 2026-07-18 | 2026-08-27 |  | 1907-02-11 09:07 | 1905-09-09 12:00 | 1907-02-11 09:07 | 100% | 80% | 56 | 56 | 45 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-TW-ST-60 | Finishing Work | 7 | 2026-08-17 | 2026-08-24 |  |  | 252.18 | 0 | 252.18 | 100% | 0% | 24 | 24 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-CON-EX-TW-ST-70 | Backfilling | 6 | 2026-08-25 | 2026-08-31 |  |  | 168.12 | 0 | 168.12 | 100% | 0% | 40 | 40 | 0 | Yes | 1 | 0 | 0 | 1
WATER STORAGE TANK |  | 107 | 2026-05-13 | 2026-09-19 | 2026-05-13 |  | 2011-09-29 04:19 | 6102.18 | 40815.18 | 100% | 14.95% | 264 | 264 | 212 |  | 5 | 4 | 0 | 1
PG-H-CON-EX-TW-IR-10 | Excavation(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 1902-02-04 13:55 | 766.58 | 766.58 | 100% | 100% | 83 | 83 | 83 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-TW-IR-10_R | Excavation(Remaining) | 3 | 2026-08-29 | 2026-08-31 | 2026-07-08 | 2026-07-09 | 1900-03-25 04:19 | 85.18 | 85.18 | 100% | 100% | 9 | 9 | 9 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-TW-IR-20 | RCC Foundation | 6 | 2026-09-01 | 2026-09-07 | 2026-07-23 | 2026-08-27 | 1911-04-28 09:36 | 4136.4 | 4136.4 | 100% | 100% | 72 | 72 | 72 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-TW-IR-30 | Backfilling | 5 | 2026-09-08 | 2026-09-13 | 2026-08-14 | 2026-08-27 | 1114.02 | 1114.02 | 1114.02 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-TW-IR-40 | GRP Water Tank Installation | 5 | 2026-09-14 | 2026-09-19 |  |  | 34713 | 0 | 34713 | 100% | 0% | 52 | 52 | 0 | Yes | 1 | 0 | 0 | 1
TOILET BUILDING WORKS |  | 127 | 2026-05-12 | 2026-10-12 | 2026-05-12 |  | 328493.58 | 273444.26 | 328493.58 | 100% | 83.24% | 1708 | 1708 | 1458 |  | 38 | 21 | 14 | 3
CIVIL WORK |  | 127 | 2026-05-12 | 2026-10-12 | 2026-05-12 |  | 230766.78 | 191581.5 | 230766.78 | 100% | 83.02% | 1100 | 1100 | 982 |  | 24 | 16 | 7 | 1
STRUCTURAL WORK |  | 58 | 2026-05-12 | 2026-07-22 | 2026-05-12 | 2026-07-23 | 37980 | 37980 | 37980 | 100% | 100% | 372 | 372 | 372 |  | 7 | 7 | 0 | 0
PG-H-CON-B-STR-10 | Excavation up to bottom of footing | 2 | 2026-05-12 | 2026-05-13 | 2026-05-12 | 2026-05-13 | 1900.8 | 1900.8 | 1900.8 | 100% | 100% | 92 | 92 | 92 | No | 1 | 1 | 0 | 0
PG-H-CON-B-STR-20 | Anti-termite treatment and Polyethene Sheet | 2 | 2026-05-12 | 2026-05-13 | 2026-05-12 | 2026-05-13 | 3294 | 3294 | 3294 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-H-CON-B-STR-30 | Backfilling with selected fill material (under footing) | 1 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 1900.8 | 1900.8 | 1900.8 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
PG-H-CON-B-STR-40 | Raft Foundation Work | 27 | 2026-05-13 | 2026-06-17 | 2026-05-13 | 2026-06-17 | 2534.4 | 2534.4 | 2534.4 | 100% | 100% | 64 | 64 | 64 | No | 1 | 1 | 0 | 0
PG-H-CON-B-STR-50 | Autoclaved aerated panel (walls) | 4 | 2026-07-13 | 2026-07-16 | 2026-07-11 | 2026-07-12 | 11340 | 11340 | 11340 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-B-STR-60 | Autoclaved aerated panel (ceiling) | 3 | 2026-07-18 | 2026-07-20 | 2026-07-12 | 2026-07-16 | 8505 | 8505 | 8505 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-B-STR-70 | Autoclaved aerated panel (parapet) | 2 | 2026-07-21 | 2026-07-22 | 2026-07-12 | 2026-07-23 | 8505 | 8505 | 8505 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
ARCHITECTURAL WORK |  | 69 | 2026-07-23 | 2026-10-12 | 2026-07-31 |  | 192786.78 | 153601.5 | 192786.78 | 100% | 79.67% | 728 | 728 | 610 |  | 17 | 9 | 7 | 1
GENERAL FINISHES |  | 69 | 2026-07-23 | 2026-10-12 | 2026-07-31 |  | 87769.2 | 62097.24 | 87769.2 | 100% | 70.75% | 376 | 376 | 330 |  | 8 | 4 | 4 | 0
PG-H-CON-B-AR-GF-10 | Block Works | 4 | 2026-07-23 | 2026-07-27 | 2026-07-31 | 2026-08-05 | 2484 | 2484 | 2484 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-B-AR-GF-20 | Plaster | 4 | 2026-08-08 | 2026-08-11 | 2026-08-06 | 2026-08-07 | 4427.4 | 4427.4 | 4427.4 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-B-AR-GF-30 | False Ceiling Installation & Finishing | 8 | 2026-08-20 | 2026-08-29 | 2026-08-20 | 2026-09-15 | 1902-05-22 14:24 | 873.6 | 873.6 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-B-AR-GF-40 | Wall Paint | 3 | 2026-09-09 | 2026-09-12 | 2026-08-20 |  | 1908-02-05 | 1906-06-23 09:36 | 2958 | 100% | 80% | 48 | 48 | 38 | No | 1 | 0 | 1 | 0
PG-H-CON-B-AR-GF-50 | Epoxy Flooring | 7 | 2026-09-13 | 2026-09-20 | 2026-08-20 |  | 1900-09-29 14:24 | 218.88 | 273.6 | 100% | 80% | 56 | 56 | 45 | No | 1 | 0 | 1 | 0
PG-H-CON-B-AR-GF-60 | Install Doors & Windows | 5 | 2026-09-21 | 2026-09-27 | 2026-08-27 |  | 1936-05-03 19:12 | 1929-01-26 00:58 | 13273.8 | 100% | 80% | 32 | 32 | 26 | No | 1 | 0 | 1 | 0
PG-H-CON-B-AR-GF-70 | Facade Finishing Work | 18 | 2026-09-21 | 2026-10-12 | 2026-08-20 | 2026-09-16 | 1920-09-02 14:24 | 7551.6 | 7551.6 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-B-AR-GF-80 | Lockers and Furniture Installation | 7 | 2026-09-28 | 2026-10-05 | 2026-10-04 |  | 55927.2 | 33556.32 | 55927.2 | 100% | 60% | 48 | 48 | 29 | No | 1 | 0 | 1 | 0
WET AREA FINISHES |  | 51 | 2026-08-12 | 2026-10-11 | 2026-08-07 |  | 81123.78 | 80051.46 | 81123.78 | 100% | 98.68% | 216 | 216 | 210 |  | 6 | 5 | 1 | 0
PG-H-CON-B-AR-WF-10 | False Ceiling Installation & Finishing | 4 | 2026-08-12 | 2026-08-16 | 2026-08-20 | 2026-09-16 | 1907-12-07 | 2898 | 2898 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-B-AR-WF-20 | Wall Tiles and Partition Work | 3 | 2026-09-13 | 2026-09-15 | 2026-08-07 | 2026-08-14 | 1958-04-08 04:48 | 21283.2 | 21283.2 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-B-AR-WF-30 | Waterproofing on Floor | 2 | 2026-09-16 | 2026-09-17 | 2026-08-14 | 2026-09-16 | 1915-11-01 | 5784 | 5784 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-H-CON-B-AR-WF-40 | Floor Tiles Works | 10 | 2026-09-19 | 2026-09-30 | 2026-08-14 | 2026-09-16 | 1917-10-06 | 1917-10-06 | 6489 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-H-CON-B-AR-WF-50 | Toliet accessories Installation Works | 9 | 2026-10-01 | 2026-10-11 | 2026-08-27 | 2026-09-16 | 2007-08-13 23:31 | 39307.98 | 39307.98 | 100% | 100% | 24 | 24 | 24 | No | 1 | 1 | 0 | 0
PG-H-CON-B-AR-WF-60 | Install Doors | 4 | 2026-10-01 | 2026-10-05 | 2026-08-27 |  | 5361.6 | 4289.28 | 5361.6 | 100% | 80% | 32 | 32 | 26 | No | 1 | 0 | 1 | 0
ROOF FINISHES |  | 14 | 2026-09-19 | 2026-10-05 | 2026-08-20 |  | 1965-05-31 19:12 | 1931-05-09 19:12 | 23893.8 | 100% | 47.93% | 136 | 136 | 70 |  | 3 | 0 | 2 | 1
PG-H-CON-B-AR-RF-10 | Waterproofing on Floor | 4 | 2026-09-19 | 2026-09-22 | 2026-08-20 |  | 1911-05-20 | 1909-02-07 09:36 | 4158 | 100% | 80% | 32 | 32 | 26 | No | 1 | 0 | 1 | 0
PG-H-CON-B-AR-RF-20 | Epoxy Flooring and Finishes | 2 | 2026-09-24 | 2026-09-26 | 2026-08-27 |  | 1927-10-23 | 8126.4 | 10158 | 100% | 80% | 56 | 56 | 45 | No | 1 | 0 | 1 | 0
PG-H-CON-B-AR-RF-30 | Steel ladder and Steel roof scupper Installation | 2 | 2026-10-04 | 2026-10-05 |  |  | 1926-03-21 19:12 | 0 | 9577.8 | 100% | 0% | 48 | 48 | 0 | No | 1 | 0 | 0 | 1
MEP WORK |  | 60 | 2026-07-28 | 2026-10-06 | 2026-07-22 |  | 97726.8 | 81862.76 | 97726.8 | 100% | 83.77% | 608 | 608 | 476 |  | 14 | 5 | 7 | 2
MECANICAL WORKS |  | 60 | 2026-07-28 | 2026-10-06 | 2026-07-22 |  | 79479.48 | 66055 | 79479.48 | 100% | 83.11% | 400 | 400 | 292 |  | 9 | 4 | 3 | 2
FIRE FIGHTING SYSTEM |  | 1 | 2026-10-06 | 2026-10-06 |  |  | 1900-05-15 06:14 | 0 | 136.26 | 100% | 0% | 32 | 32 | 0 |  | 1 | 0 | 0 | 1
PG-H-CON-B-GF-FF-10 | Fire Extinguisher Installation | 1 | 2026-10-06 | 2026-10-06 |  |  | 1900-05-15 06:14 | 0 | 136.26 | 100% | 0% | 32 | 32 | 0 | No | 1 | 0 | 0 | 1
SEWER AND DRAINAGE SYSTEM |  | 18 | 2026-08-03 | 2026-08-23 | 2026-07-22 |  | 11290.02 | 7580.44 | 11290.02 | 100% | 67.14% | 144 | 144 | 89 |  | 3 | 1 | 1 | 1
PG-H-CON-B-GF-DR-10 | Sewer and Drainge System Main Lines Installation | 2 | 2026-08-03 | 2026-08-04 | 2026-07-30 |  | 1908-10-29 17:17 | 2741.86 | 3225.72 | 100% | 85% | 48 | 48 | 41 | No | 1 | 0 | 1 | 0
PG-H-CON-B-GF-DR-20 | Sewer and Drainge System Pipes and fittings Installation | 2 | 2026-08-18 | 2026-08-19 | 2026-07-22 | 2026-08-05 | 4838.58 | 4838.58 | 4838.58 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-B-GF-DR-30 | Sanitaryware Installation (Final Fix) | 2 | 2026-08-22 | 2026-08-23 |  |  | 1908-10-29 17:17 | 0 | 3225.72 | 100% | 0% | 48 | 48 | 0 | No | 1 | 0 | 0 | 1
HVAC SYSTEM |  | 16 | 2026-07-28 | 2026-08-15 | 2026-08-13 |  | 12127.2 | 1926-11-20 18:14 | 12127.2 | 100% | 80.99% | 96 | 96 | 82 |  | 2 | 1 | 1 | 0
PG-H-CON-B-GF-AC-10 | Duct Work and Exhaust Fan Installation | 3 | 2026-07-28 | 2026-07-30 | 2026-08-13 | 2026-08-20 | 4442.4 | 4442.4 | 4442.4 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-B-GF-AC-20 | Split AC, Grills & Diffuser Installation | 3 | 2026-08-12 | 2026-08-15 | 2026-09-26 |  | 7684.8 | 5379.36 | 7684.8 | 100% | 70% | 48 | 48 | 34 | No | 1 | 0 | 1 | 0
WATER SUPPLY SYSTEM |  | 18 | 2026-08-01 | 2026-08-20 | 2026-07-30 |  | 55926 | 48652.8 | 55926 | 100% | 86.99% | 128 | 128 | 122 |  | 3 | 2 | 1 | 0
PG-H-CON-B-GF-WS-10 | Water Supply Main Lines Installation | 2 | 2026-08-01 | 2026-08-02 | 2026-07-30 | 2026-07-31 | 5702.4 | 5702.4 | 5702.4 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-B-GF-WS-20 | Water Supply Pipes Installation (Cold and Hot Water) | 2 | 2026-08-16 | 2026-08-17 | 2026-07-30 | 2026-08-06 | 1937-12-08 14:24 | 13857.6 | 13857.6 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-B-GF-WS-30 | Water Supply Accesories and Booster pump Installation | 3 | 2026-08-18 | 2026-08-20 | 2026-08-27 |  | 1999-07-25 | 29092.8 | 36366 | 100% | 80% | 32 | 32 | 26 | No | 1 | 0 | 1 | 0
ELECTRICAL WORKS |  | 30 | 2026-08-05 | 2026-09-08 | 2026-08-12 |  | 18247.32 | 15807.76 | 18247.32 | 100% | 86.63% | 208 | 208 | 184 |  | 5 | 1 | 4 | 0
PG-H-CON-B-GF-EL-10 | Pipes & Conduits Installation | 2 | 2026-08-05 | 2026-08-06 | 2026-08-12 | 2026-08-14 | 1983.6 | 1983.6 | 1983.6 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-B-GF-EL-20 | Electrical Light Fixtures Installation | 2 | 2026-08-27 | 2026-08-29 | 2026-08-20 |  | 1905-06-05 14:24 | 1686.06 | 1983.6 | 100% | 85% | 48 | 48 | 41 | No | 1 | 0 | 1 | 0
PG-H-CON-B-GF-EL-30 | Fire Alarm Devices Installation | 3 | 2026-08-30 | 2026-09-01 | 2026-08-20 |  | 1905-06-05 14:24 | 1686.06 | 1983.6 | 100% | 85% | 32 | 32 | 27 | No | 1 | 0 | 1 | 0
PG-H-CON-B-GF-EL-40 | Telecom & CCTV Devices Installation | 3 | 2026-09-02 | 2026-09-05 | 2026-08-20 |  | 4959 | 4215.15 | 4959 | 100% | 85% | 40 | 40 | 34 | No | 1 | 0 | 1 | 0
PG-H-CON-B-GF-EL-50 | Electrical & ELV Wiring Works | 3 | 2026-09-06 | 2026-09-08 | 2026-08-20 |  | 7337.52 | 6236.89 | 7337.52 | 100% | 85% | 40 | 40 | 34 | No | 1 | 0 | 1 | 0
PROJECT CLOSOUT |  | 171 | 2026-05-25 | 2026-12-15 | 2026-05-25 |  | 20443.96 | 75642.64 | 681465.2 | 3% | 11.1% | 384 | 11 | 41 |  | 7 | 1 | 1 | 5
PG-H-PCL-10 | Testing, Commessioning for All Systems(Completed) | 23 | 2026-05-25 | 2026-06-24 | 2026-05-25 | 2026-06-24 | 20443.96 | 20443.96 | 20443.96 | 100% | 100% | 11 | 11 | 11 | No | 1 | 1 | 0 | 0
PG-H-PCL-10_R | Testing, Commessioning for All Systems(Remaining) | 10 | 2026-11-02 | 2026-11-12 | 2026-08-06 |  | 0 | 55198.68 | 183995.6 | 0% | 30% | 101 | 0 | 30 | Yes | 1 | 0 | 1 | 0
PG-H-PCL-20 | As-Built Drawings | 18 | 2026-11-14 | 2026-12-03 |  |  | 0 | 0 | 68146.52 | 0% | 0% | 0 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-PCL-30 | Snag list Submission | 8 | 2026-11-14 | 2026-11-22 |  |  | 0 | 0 | 136293.04 | 0% | 0% | 136 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-PCL-40 | Snag list Closeout | 14 | 2026-11-23 | 2026-12-08 |  |  | 0 | 0 | 136293.04 | 0% | 0% | 136 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-PCL-50 | Issuing Approvals | 3 | 2026-12-09 | 2026-12-12 |  |  | 0 | 0 | 68146.52 | 0% | 0% | 0 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-PCL-60 | Handing Over | 3 | 2026-12-13 | 2026-12-15 |  |  | 0 | 0 | 68146.52 | 0% | 0% | 0 | 0 | 0 | Yes | 1 | 0 | 0 | 1
TABUK |  | 250 | 2026-02-17 | 2026-12-16 | 2026-02-17 |  | 8516786.3 | 6771039.9 | 11357801 | 74.99% | 59.62% | 8496 | 6599 | 6279 |  | 671 | 566 | 70 | 35
MOBILIZATION |  | 44 | 2026-02-17 | 2026-04-15 | 2026-02-17 | 2026-04-14 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 9 | 9 | 0 | 0
TEMPORARY CAMP |  | 43 | 2026-02-17 | 2026-04-14 | 2026-02-17 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-MOB-CAM-10 | Temporary Underground Utilities works | 43 | 2026-02-17 | 2026-04-14 | 2026-02-17 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-MOB-CAM-20 | Temporary Porta-Cabins | 36 | 2026-02-26 | 2026-04-14 | 2026-02-26 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-MOB-CAM-30 | Temporary Toilets | 36 | 2026-02-26 | 2026-04-14 | 2026-02-26 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-MOB-CAM-40 | Temporary Mosque | 28 | 2026-03-08 | 2026-04-14 | 2026-03-08 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SITE OFFICES |  | 44 | 2026-02-17 | 2026-04-15 | 2026-02-17 | 2026-04-14 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-T-MOB-SO-10 | Temporary Underground Utilities works | 44 | 2026-02-17 | 2026-04-15 | 2026-02-17 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-MOB-SO-20 | Temporary Porta-Cabins | 38 | 2026-02-25 | 2026-04-15 | 2026-02-25 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-MOB-SO-30 | Temporary Toilets | 38 | 2026-02-25 | 2026-04-15 | 2026-02-25 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-MOB-SO-40 | Temporary Mosque | 32 | 2026-03-04 | 2026-04-15 | 2026-03-04 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-MOB-SO-50 | Car Parking Area | 25 | 2026-03-12 | 2026-04-15 | 2026-03-12 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
GENERAL REQUIEREMENTS |  | 44 | 2026-02-17 | 2026-04-15 | 2026-02-17 | 2026-04-14 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-GEN-20 | HSSE Submission Plan | 35 | 2026-02-17 | 2026-04-05 | 2026-02-17 | 2026-04-04 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-GEN-30 | Surveying report Submission Plan | 44 | 2026-02-17 | 2026-04-15 | 2026-02-17 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-GEN-40 | Baseline Submission | 6 | 2026-02-28 | 2026-03-07 | 2026-02-28 | 2026-03-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-GEN-10 | QA/QC Submission Plan | 16 | 2026-03-12 | 2026-04-05 | 2026-03-12 | 2026-04-04 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ENGINEERING |  | 143 | 2026-02-17 | 2026-08-12 | 2026-02-17 | 2026-09-17 | 340734.03 | 340734.03 | 340734.03 | 100% | 100% | 0 | 0 | 0 |  | 264 | 264 | 0 | 0
SHOP DRAWINGS SUBMITTALS |  | 136 | 2026-02-17 | 2026-08-04 | 2026-02-17 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 62 | 62 | 0 | 0
STRUCTURAL DRAWINGS |  | 121 | 2026-02-17 | 2026-07-18 | 2026-02-17 | 2026-07-03 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PROJECT FENCE |  | 63 | 2026-02-17 | 2026-05-07 | 2026-02-17 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ST-SD-SB-10 | Excavation Drawings | 63 | 2026-02-17 | 2026-05-07 | 2026-02-17 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ST-SD-SB-20 | Foundation Drawings | 61 | 2026-02-19 | 2026-05-07 | 2026-02-19 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PADEL PLAYGROUND FENCE |  | 63 | 2026-02-17 | 2026-05-07 | 2026-02-17 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ST-SD-SB-30 | Excavation Drawings | 63 | 2026-02-17 | 2026-05-07 | 2026-02-17 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ST-SD-SB-40 | Foundation Drawings | 61 | 2026-02-19 | 2026-05-07 | 2026-02-19 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 20 | 2026-06-25 | 2026-07-18 | 2026-07-01 | 2026-07-03 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ST-SD-SB-50 | Excavation Drawings | 10 | 2026-06-25 | 2026-07-06 | 2026-07-01 | 2026-07-03 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ST-SD-SB-60 | Foundation Drawings | 10 | 2026-07-07 | 2026-07-18 | 2026-07-01 | 2026-07-03 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
TOILET BUILDING |  | 41 | 2026-02-19 | 2026-04-14 | 2026-02-19 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ST-SD-SB-70 | Excavation Drawings | 41 | 2026-02-19 | 2026-04-14 | 2026-02-19 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ST-SD-SB-80 | Foundation Drawings | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
WATER STORAGE TANK |  | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ST-SD-SB-90 | Excavation Drawings | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ST-SD-SB-100 | Foundation Drawings | 37 | 2026-02-25 | 2026-04-14 | 2026-02-25 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SEPTIC TANK |  | 57 | 2026-02-25 | 2026-05-07 | 2026-02-25 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ST-SD-SB-110 | Reinforcement Detail Drawings | 57 | 2026-02-25 | 2026-05-07 | 2026-02-25 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ST-SD-SB-120 | Concrete Detail Drawings | 54 | 2026-03-01 | 2026-05-07 | 2026-03-01 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL DRAWINGS |  | 132 | 2026-02-23 | 2026-08-04 | 2026-02-23 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 13 | 13 | 0 | 0
TOILET BUILDING |  | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 10 | 0 | 0
PG-T-EN-AR-SD-SB-10 | Ground Floor Plan | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-SB-20 | Roof Floor Plan | 35 | 2026-02-28 | 2026-04-14 | 2026-02-28 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-SB-50 | Floor Finish Layout | 36 | 2026-02-28 | 2026-04-14 | 2026-02-28 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-SB-60 | Reflected Ceiling Layout | 36 | 2026-02-28 | 2026-04-15 | 2026-02-28 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-SB-70 | Enlarged Toilets Layout | 36 | 2026-02-28 | 2026-04-15 | 2026-02-28 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-SB-30 | Elevations | 33 | 2026-03-03 | 2026-04-15 | 2026-03-03 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-SB-80 | Doors & Windows Schedule | 33 | 2026-03-03 | 2026-04-15 | 2026-03-03 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-SB-90 | Aluminum Work | 33 | 2026-03-03 | 2026-04-15 | 2026-03-03 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-SB-100 | Cladding Details | 32 | 2026-03-03 | 2026-04-14 | 2026-03-03 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-SB-40 | Sections | 31 | 2026-03-05 | 2026-04-15 | 2026-03-05 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 15 | 2026-07-19 | 2026-08-04 | 2026-08-05 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-EN-AR-SD-SB-110 | Membrane & Insulation Details | 15 | 2026-07-19 | 2026-08-04 | 2026-08-05 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-SB-120 | Steel Cable System | 15 | 2026-07-19 | 2026-08-04 | 2026-08-05 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-SB-130 | Doors & Access Sytem Drawings | 15 | 2026-07-19 | 2026-08-04 | 2026-08-05 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
LANDSCAPE DRAWINGS |  | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 13 | 13 | 0 | 0
PG-T-EN-LS-SD-SB-10 | Hardscape Layout Plan | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-SB-20 | Interlock Tile Details | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-SB-30 | Stamped Concrete Pattern & Section | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-SB-40 | Tartan Flooring Layout & Details | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-SB-50 | Bike Path Layout & Details | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-SB-60 | Walking Path layout & Details | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-SB-70 | Tree Planting Plan & Details | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-SB-80 | Traffic Sign Location & Details | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-SB-90 | Football Playground Layout | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-SB-100 | Padel Playground Layout | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-SB-110 | Basketball Playground Layout | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-SB-120 | Playground Details | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-SB-130 | Padel Fence Elevation & Details | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MECHANICAL DRAWINGS |  | 108 | 2026-02-28 | 2026-07-12 | 2026-02-28 | 2026-07-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 10 | 0 | 0
WATER SUPPLY SYSTEM |  | 32 | 2026-02-28 | 2026-04-11 | 2026-02-28 | 2026-04-09 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-EN-ME-SD-SB-20 | Pump Room Layout | 32 | 2026-02-28 | 2026-04-11 | 2026-02-28 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-SB-10 | Cold & Hot Water Piping Layout | 28 | 2026-03-04 | 2026-04-11 | 2026-03-04 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-SB-30 | Booster Pump Details | 28 | 2026-03-04 | 2026-04-11 | 2026-03-04 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-SB-40 | GRP Water Tank Details | 24 | 2026-03-09 | 2026-04-11 | 2026-03-09 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SEWER AND DRAINAGE SYSTEM |  | 28 | 2026-03-04 | 2026-04-11 | 2026-03-04 | 2026-04-09 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-EN-ME-SD-SB-50 | Drainage Layout | 28 | 2026-03-04 | 2026-04-11 | 2026-03-04 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-SB-60 | Floor Drains & Cleanouts Details | 24 | 2026-03-09 | 2026-04-11 | 2026-03-09 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-SB-70 | Inspection Chamber Details | 21 | 2026-03-12 | 2026-04-11 | 2026-03-12 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION SYSTEM |  | 47 | 2026-03-09 | 2026-05-07 | 2026-03-09 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ME-SD-SB-80 | HDPE Pipe Routing | 47 | 2026-03-09 | 2026-05-07 | 2026-03-09 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-SB-90 | Irrigation Network Layout | 44 | 2026-03-12 | 2026-05-07 | 2026-03-12 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 15 | 2026-06-25 | 2026-07-12 | 2026-07-02 | 2026-07-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-SB-100 | Air Package and HVAC System Drawings | 15 | 2026-06-25 | 2026-07-12 | 2026-07-02 | 2026-07-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL DRAWINGS |  | 66 | 2026-05-10 | 2026-07-29 | 2026-05-10 | 2026-07-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 14 | 14 | 0 | 0
POWER AND LIGHTING SYSTEM |  | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-EN-EL-SD-SB-10 | Main Distribution Board (MDB) Layout | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-SB-20 | Pump Room Power Panel | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-SB-30 | Street Lighting Power Panel | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-SB-40 | Site Lighting Pole Layout | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELV SYSTEM |  | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-EN-EL-SD-SB-50 | Telecom & Data Layout | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-SB-60 | CCTV Camera Layout | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-SB-70 | Access Control Layout | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-SB-80 | AV System Layout | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE ALARM SYSTEM |  | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-EN-EL-SD-SB-90 | Fire Alarm Layout | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-SB-100 | Detector & Manual Call Point Details | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-SB-110 | Control Panel Wiring Diagram | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 30 | 2026-06-25 | 2026-07-29 | 2026-07-08 | 2026-07-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-EN-EL-SD-SB-130 | Generators Details | 15 | 2026-06-25 | 2026-07-12 | 2026-07-08 | 2026-07-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-SB-120 | Power & Lighting System Drawings | 15 | 2026-07-13 | 2026-07-29 | 2026-07-08 | 2026-07-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-SB-140 | Smart Dome System Drawings | 15 | 2026-07-13 | 2026-07-29 | 2026-07-08 | 2026-07-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SHOP DRAWINGS APPROVALS |  | 141 | 2026-02-19 | 2026-08-12 | 2026-02-19 | 2026-09-02 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 62 | 62 | 0 | 0
STRUCTURAL DRAWINGS |  | 124 | 2026-02-19 | 2026-07-23 | 2026-02-19 | 2026-07-11 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PROJECT FENCE |  | 61 | 2026-02-19 | 2026-05-07 | 2026-02-19 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ST-SD-AP-10 | Excavation Drawings | 61 | 2026-02-19 | 2026-05-07 | 2026-02-19 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ST-SD-AP-20 | Foundation Drawings | 58 | 2026-02-24 | 2026-05-07 | 2026-02-24 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PADEL PLAYGROUND FENCE |  | 61 | 2026-02-19 | 2026-05-07 | 2026-02-19 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ST-SD-AP-30 | Excavation Drawings | 61 | 2026-02-19 | 2026-05-07 | 2026-02-19 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ST-SD-AP-40 | Foundation Drawings | 58 | 2026-02-24 | 2026-05-07 | 2026-02-24 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 15 | 2026-07-07 | 2026-07-23 | 2026-07-05 | 2026-07-11 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ST-SD-AP-50 | Excavation Drawings | 5 | 2026-07-07 | 2026-07-12 | 2026-07-08 | 2026-07-11 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ST-SD-AP-60 | Foundation Drawings | 5 | 2026-07-19 | 2026-07-23 | 2026-07-05 | 2026-07-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
TOILET BUILDING |  | 42 | 2026-02-23 | 2026-04-18 | 2026-02-23 | 2026-04-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ST-SD-AP-70 | Excavation Drawings | 42 | 2026-02-23 | 2026-04-18 | 2026-02-23 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ST-SD-AP-80 | Foundation Drawings | 39 | 2026-02-26 | 2026-04-18 | 2026-02-26 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
WATER STORAGE TANK |  | 40 | 2026-02-25 | 2026-04-18 | 2026-02-25 | 2026-04-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ST-SD-AP-90 | Excavation Drawings | 40 | 2026-02-25 | 2026-04-18 | 2026-02-25 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ST-SD-AP-100 | Foundation Drawings | 37 | 2026-03-01 | 2026-04-18 | 2026-03-01 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SEPTIC TANK |  | 54 | 2026-03-01 | 2026-05-07 | 2026-03-01 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ST-SD-AP-110 | Reinforcement Detail Drawings | 54 | 2026-03-01 | 2026-05-07 | 2026-03-01 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ST-SD-AP-120 | Concrete Detail Drawings | 51 | 2026-03-04 | 2026-05-07 | 2026-03-04 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL DRAWINGS |  | 135 | 2026-02-28 | 2026-08-12 | 2026-02-28 | 2026-09-02 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 13 | 13 | 0 | 0
TOILET BUILDING |  | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 10 | 0 | 0
PG-T-EN-AR-SD-AP-10 | Ground Floor Plan | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-AP-20 | Roof Floor Plan | 35 | 2026-03-03 | 2026-04-18 | 2026-03-03 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-AP-50 | Floor Finish Layout | 33 | 2026-03-05 | 2026-04-18 | 2026-03-05 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-AP-60 | Reflected Ceiling Layout | 33 | 2026-03-05 | 2026-04-18 | 2026-03-05 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-AP-70 | Enlarged Toilets Layout | 33 | 2026-03-05 | 2026-04-18 | 2026-03-05 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-AP-30 | Elevations | 32 | 2026-03-07 | 2026-04-18 | 2026-03-07 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-AP-80 | Doors & Windows Schedule | 32 | 2026-03-07 | 2026-04-18 | 2026-03-07 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-AP-90 | Aluminum Work | 31 | 2026-03-08 | 2026-04-18 | 2026-03-08 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-AP-100 | Cladding Details | 31 | 2026-03-08 | 2026-04-18 | 2026-03-08 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-AP-40 | Sections | 29 | 2026-03-10 | 2026-04-18 | 2026-03-10 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 7 | 2026-08-05 | 2026-08-12 | 2026-08-06 | 2026-09-02 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-EN-AR-SD-AP-110 | Membrane & Insulation Details | 7 | 2026-08-05 | 2026-08-12 | 2026-08-06 | 2026-09-02 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-AP-120 | Steel Cable System | 7 | 2026-08-05 | 2026-08-12 | 2026-08-06 | 2026-09-02 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-AP-130 | Doors & Access Sytem Drawings | 7 | 2026-08-05 | 2026-08-12 | 2026-08-06 | 2026-09-02 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
LANDSCAPE DRAWINGS |  | 39 | 2026-02-26 | 2026-04-18 | 2026-02-26 | 2026-04-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 13 | 13 | 0 | 0
PG-T-EN-LS-SD-AP-50 | Bike Path Layout & Details | 39 | 2026-02-26 | 2026-04-18 | 2026-02-26 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-AP-60 | Walking Path layout & Details | 39 | 2026-02-26 | 2026-04-18 | 2026-02-26 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-AP-80 | Traffic Sign Location & Details | 39 | 2026-02-26 | 2026-04-18 | 2026-02-26 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-AP-130 | Padel Fence Elevation & Details | 39 | 2026-02-26 | 2026-04-18 | 2026-02-26 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-AP-10 | Hardscape Layout Plan | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-AP-40 | Tartan Flooring Layout & Details | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-AP-70 | Tree Planting Plan & Details | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-AP-90 | Football Playground Layout | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-AP-100 | Padel Playground Layout | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-AP-110 | Basketball Playground Layout | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-AP-120 | Playground Details | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-AP-20 | Interlock Tile Details | 30 | 2026-03-09 | 2026-04-18 | 2026-03-09 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-AP-30 | Stamped Concrete Pattern & Section | 24 | 2026-03-16 | 2026-04-18 | 2026-03-16 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MECHANICAL DRAWINGS |  | 110 | 2026-03-09 | 2026-07-23 | 2026-03-09 | 2026-07-18 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 10 | 0 | 0
WATER SUPPLY SYSTEM |  | 27 | 2026-03-09 | 2026-04-14 | 2026-03-09 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-EN-ME-SD-AP-10 | Cold & Hot Water Piping Layout | 27 | 2026-03-09 | 2026-04-14 | 2026-03-09 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-AP-30 | Booster Pump Details | 26 | 2026-03-10 | 2026-04-14 | 2026-03-10 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-AP-40 | GRP Water Tank Details | 23 | 2026-03-14 | 2026-04-14 | 2026-03-14 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-AP-20 | Pump Room Layout | 21 | 2026-03-16 | 2026-04-14 | 2026-03-16 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SEWER AND DRAINAGE SYSTEM |  | 27 | 2026-03-09 | 2026-04-14 | 2026-03-09 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-EN-ME-SD-AP-50 | Drainage Layout | 27 | 2026-03-09 | 2026-04-14 | 2026-03-09 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-AP-60 | Floor Drains & Cleanouts Details | 21 | 2026-03-16 | 2026-04-14 | 2026-03-16 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-AP-70 | Inspection Chamber Details | 21 | 2026-03-16 | 2026-04-14 | 2026-03-16 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION SYSTEM |  | 44 | 2026-03-12 | 2026-05-07 | 2026-03-12 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ME-SD-AP-80 | HDPE Pipe Routing | 44 | 2026-03-12 | 2026-05-07 | 2026-03-12 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-AP-90 | Irrigation Network Layout | 40 | 2026-03-17 | 2026-05-07 | 2026-03-17 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 10 | 2026-07-13 | 2026-07-23 | 2026-07-13 | 2026-07-18 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-AP-100 | Air Package and HVAC System Drawings | 10 | 2026-07-13 | 2026-07-23 | 2026-07-13 | 2026-07-18 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL DRAWINGS |  | 73 | 2026-05-11 | 2026-08-08 | 2026-05-11 | 2026-07-19 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 14 | 14 | 0 | 0
POWER AND LIGHTING SYSTEM |  | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-EN-EL-SD-AP-10 | Main Distribution Board (MDB) Layout | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-AP-20 | Pump Room Power Panel | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-AP-30 | Street Lighting Power Panel | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-AP-40 | Site Lighting Pole Layout | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELV SYSTEM |  | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-EN-EL-SD-AP-50 | Telecom & Data Layout | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-AP-60 | CCTV Camera Layout | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-AP-70 | Access Control Layout | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-AP-80 | AV System Layout | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE ALARM SYSTEM |  | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-EN-EL-SD-AP-90 | Fire Alarm Layout | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-AP-100 | Detector & Manual Call Point Details | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-AP-110 | Control Panel Wiring Diagram | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 23 | 2026-07-13 | 2026-08-08 | 2026-07-13 | 2026-07-19 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-EN-EL-SD-AP-130 | Generators Details | 8 | 2026-07-13 | 2026-07-21 | 2026-07-13 | 2026-07-19 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-AP-120 | Power & Lighting System Drawings | 8 | 2026-07-30 | 2026-08-08 | 2026-07-13 | 2026-07-19 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-AP-140 | Smart Dome System Drawings | 8 | 2026-07-30 | 2026-08-08 | 2026-07-13 | 2026-07-19 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MATERIAL SUBMITTALS |  | 115 | 2026-02-17 | 2026-07-11 | 2026-02-17 | 2026-09-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 70 | 70 | 0 | 0
LONG LEAD ITEMS |  | 115 | 2026-02-17 | 2026-07-11 | 2026-02-17 | 2026-09-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 32 | 32 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 57 | 2026-02-25 | 2026-05-07 | 2026-02-25 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-PR-LL-LS-MS-20 | Benches, Seats (Rectangular & Circular) | 57 | 2026-02-25 | 2026-05-07 | 2026-02-25 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-MS-30 | Fence, gates and accessories | 50 | 2026-03-05 | 2026-05-07 | 2026-03-05 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-MS-10 | Bike and Walk Path Materials | 50 | 2026-03-05 | 2026-05-07 | 2026-03-05 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 110 | 2026-02-17 | 2026-07-05 | 2026-02-17 | 2026-09-02 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 6 | 6 | 0 | 0
PG-T-PR-LL-SP-MS-50 | Air Dome Materials(Completed) | 101 | 2026-02-17 | 2026-06-25 | 2026-02-17 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MS-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc) | 49 | 2026-03-07 | 2026-05-07 | 2026-03-07 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MS-20 | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc) | 49 | 2026-03-07 | 2026-05-07 | 2026-03-07 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MS-30 | Padel Playgound Materials (Flooring, fence, tempered glass, etc) | 49 | 2026-03-07 | 2026-05-07 | 2026-03-07 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MS-40 | Tartan Floor | 49 | 2026-03-07 | 2026-05-07 | 2026-03-07 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MS-50_R | Air Dome Materials(Remaining) | 9 | 2026-06-25 | 2026-07-05 | 2026-07-07 | 2026-09-02 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 41 | 2026-03-07 | 2026-04-28 | 2026-03-07 | 2026-04-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-T-PR-LL-CO-MS-10 | Autoclaved Aerated Panel | 41 | 2026-03-07 | 2026-04-28 | 2026-03-07 | 2026-04-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 45 | 2026-03-11 | 2026-05-07 | 2026-03-11 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-LL-MT-MS-10 | Metal Doors | 45 | 2026-03-11 | 2026-05-07 | 2026-03-11 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-MT-MS-20 | Curtain Wall | 45 | 2026-03-11 | 2026-05-07 | 2026-03-11 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 46 | 2026-03-10 | 2026-05-07 | 2026-03-10 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-LL-PB-MS-10 | Booster Pump | 46 | 2026-03-10 | 2026-05-07 | 2026-03-10 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-PB-MS-20 | GRP Sectional Panel Water Tanks (4x3x3m) | 42 | 2026-03-15 | 2026-05-07 | 2026-03-15 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 50 | 2026-03-05 | 2026-05-07 | 2026-03-05 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-LL-IR-MS-10 | HDPE Pipes | 50 | 2026-03-05 | 2026-05-07 | 2026-03-05 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-IR-MS-20 | Irrigation Control System | 50 | 2026-03-05 | 2026-05-07 | 2026-03-05 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 49 | 2026-05-11 | 2026-07-11 | 2026-05-11 | 2026-09-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 16 | 16 | 0 | 0
PG-T-PR-LL-EL-MS-10 | Main Distribution Board(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-20 | Power Panels (Pump, Street Light)(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-30 | Site Lighting Poles(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-40 | Lighting Fixtures(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-70 | Security and Access Control System Materials(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-80 | Fire Alarm System Materials(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-10_R | Main Distribution Board(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-16 | 2026-08-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-20_R | Power Panels (Pump, Street Light)(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-16 | 2026-08-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-30_R | Site Lighting Poles(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-16 | 2026-08-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-40_R | Lighting Fixtures(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-16 | 2026-07-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-16 | 2026-09-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-70_R | Security and Access Control System Materials(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-16 | 2026-09-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-80_R | Fire Alarm System Materials(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-08-27 | 2026-09-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 5 | 2026-07-06 | 2026-07-11 | 2026-07-16 | 2026-07-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SHORT LEAD ITEMS |  | 28 | 2026-02-17 | 2026-03-28 | 2026-02-17 | 2026-03-26 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 38 | 38 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 23 | 2026-02-17 | 2026-03-17 | 2026-02-17 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 8 | 8 | 0 | 0
PG-T-PR-SL-LS-MS-10 | Backfilling Materials | 23 | 2026-02-17 | 2026-03-17 | 2026-02-17 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MS-30 | Compacted Natural Ground Soil | 20 | 2026-02-21 | 2026-03-17 | 2026-02-21 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MS-60 | Traffic Signages | 9 | 2026-03-07 | 2026-03-17 | 2026-03-07 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MS-40 | Curb Stone | 7 | 2026-03-09 | 2026-03-17 | 2026-03-09 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MS-20 | Interlock tiles | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MS-50 | Thermoplastic pavement road marking | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MS-70 | Trees | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MS-80 | Lawn | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 28 | 2026-02-17 | 2026-03-28 | 2026-02-17 | 2026-03-26 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-T-PR-SL-CO-MS-10 | Steel Rebar | 17 | 2026-02-17 | 2026-03-10 | 2026-02-17 | 2026-03-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-MS-20 | Concrete | 13 | 2026-02-23 | 2026-03-10 | 2026-02-23 | 2026-03-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-MS-40 | CMU Block | 19 | 2026-03-01 | 2026-03-28 | 2026-03-01 | 2026-03-26 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-MS-50 | Concrete Repair & Protection Materials | 19 | 2026-03-01 | 2026-03-28 | 2026-03-01 | 2026-03-26 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-MS-30 | Screed | 10 | 2026-03-11 | 2026-03-28 | 2026-03-11 | 2026-03-26 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL & FINISHES WORK |  | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 11 | 11 | 0 | 0
PG-T-PR-SL-AR-MS-10 | Ceramic tiles | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MS-20 | Anti-slip Granite tiles | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MS-30 | Epoxy Paint | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MS-40 | Cement Plaster | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MS-50 | Acrylic Paint | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MS-60 | Stone Cladding | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MS-70 | Phenolic Partition | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MS-80 | Glass Partition | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MS-90 | Gypsum Boards | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MS-100 | Specialities Materials (Toilet accessories, lockers, logo, etc) | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MS-110 | Waterproofing System Materials | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 9 | 2026-03-07 | 2026-03-17 | 2026-03-07 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-PR-SL-MT-MS-20 | Galvanized Steel Roof Scupper | 9 | 2026-03-07 | 2026-03-17 | 2026-03-07 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-MT-MS-30 | Galvanized Steel Cover with frame | 9 | 2026-03-07 | 2026-03-17 | 2026-03-07 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-MT-MS-10 | Galvanized Steel Ladder | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
HVAC WORK |  | 19 | 2026-02-23 | 2026-03-17 | 2026-02-23 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-PR-SL-AC-MS-10 | Split Air Conditioning Unit | 19 | 2026-02-23 | 2026-03-17 | 2026-02-23 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AC-MS-20 | Air Duct | 15 | 2026-02-28 | 2026-03-17 | 2026-02-28 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AC-MS-30 | Diffusers and Grills | 11 | 2026-03-04 | 2026-03-17 | 2026-03-04 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AC-MS-40 | Exhaust fans | 11 | 2026-03-04 | 2026-03-17 | 2026-03-04 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-PR-SL-PB-MS-10 | PPR Pipes & Valves | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-PB-MS-20 | UPCV Pipes | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-PB-MS-30 | Sanitary Drainage Fixtures | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-SL-IR-MS-10 | Gate Valve including valve box | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-IR-MS-20 | Bulbblers and Spreyers | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-T-PR-SL-EL-MS-10 | Wiring Devices Materials | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE FIGHTING WORK |  | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-T-PR-SL-FF-MS-10 | Fire Extinguishers | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MATERIAL APPROVALS |  | 114 | 2026-02-21 | 2026-07-13 | 2026-02-21 | 2026-09-17 | 340734.03 | 340734.03 | 340734.03 | 100% | 100% | 0 | 0 | 0 |  | 70 | 70 | 0 | 0
LONG LEAD ITEMS |  | 111 | 2026-02-25 | 2026-07-13 | 2026-02-25 | 2026-09-17 | 284659.98 | 284659.98 | 284659.98 | 100% | 100% | 0 | 0 | 0 |  | 32 | 32 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 56 | 2026-02-25 | 2026-05-05 | 2026-02-25 | 2026-05-05 | 15425.28 | 15425.28 | 15425.28 | 100% | 100% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-PR-LL-LS-MA-20 | Benches, Seats (Rectangular & Circular) | 56 | 2026-02-25 | 2026-05-05 | 2026-02-25 | 2026-05-05 | 3869.07 | 3869.07 | 3869.07 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-MA-30 | Fence, gates and accessories | 43 | 2026-03-12 | 2026-05-05 | 2026-03-12 | 2026-05-05 | 2529.21 | 2529.21 | 2529.21 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-MA-10 | Bike and Walk Path Materials | 41 | 2026-03-15 | 2026-05-05 | 2026-03-15 | 2026-05-05 | 9027 | 9027 | 9027 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 105 | 2026-03-02 | 2026-07-11 | 2026-03-02 | 2026-09-03 | 238773.54 | 238773.54 | 238773.54 | 100% | 100% | 0 | 0 | 0 |  | 6 | 6 | 0 | 0
PG-T-PR-LL-SP-MA-50 | Air Dome Materials(Completed) | 91 | 2026-03-02 | 2026-06-24 | 2026-03-02 | 2026-06-24 | 62622.07 | 62622.07 | 62622.07 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MA-40 | Tartan Floor | 43 | 2026-03-12 | 2026-05-05 | 2026-03-12 | 2026-05-05 | 8775 | 8775 | 8775 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MA-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc) | 42 | 2026-03-14 | 2026-05-05 | 2026-03-14 | 2026-05-05 | 13051.5 | 13051.5 | 13051.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MA-20 | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc) | 42 | 2026-03-14 | 2026-05-05 | 2026-03-14 | 2026-05-05 | 2256 | 2256 | 2256 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MA-30 | Padel Playgound Materials (Flooring, fence, tempered glass, etc) | 42 | 2026-03-14 | 2026-05-05 | 2026-03-14 | 2026-05-05 | 5950.8 | 5950.8 | 5950.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MA-50_R | Air Dome Materials(Remaining) | 5 | 2026-07-06 | 2026-07-11 | 2026-07-09 | 2026-09-03 | 146118.17 | 146118.17 | 146118.17 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 38 | 2026-03-11 | 2026-04-28 | 2026-03-11 | 2026-04-28 | 1417.5 | 1417.5 | 1417.5 | 100% | 100% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-T-PR-LL-CO-MA-10 | Autoclaved Aerated Panel | 38 | 2026-03-11 | 2026-04-28 | 2026-03-11 | 2026-04-28 | 1417.5 | 1417.5 | 1417.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 42 | 2026-03-15 | 2026-05-06 | 2026-03-15 | 2026-05-06 | 1902-06-07 05:31 | 889.23 | 889.23 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-LL-MT-MA-10 | Metal Doors | 42 | 2026-03-15 | 2026-05-06 | 2026-03-15 | 2026-05-06 | 127.53 | 127.53 | 127.53 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-MT-MA-20 | Curtain Wall | 42 | 2026-03-15 | 2026-05-06 | 2026-03-15 | 2026-05-06 | 761.7 | 761.7 | 761.7 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 42 | 2026-03-15 | 2026-05-06 | 2026-03-15 | 2026-05-06 | 3553.95 | 3553.95 | 3553.95 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-LL-PB-MA-10 | Booster Pump | 42 | 2026-03-15 | 2026-05-06 | 2026-03-15 | 2026-05-06 | 1818.3 | 1818.3 | 1818.3 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-PB-MA-20 | GRP Sectional Panel Water Tanks (4x3x3m) | 38 | 2026-03-24 | 2026-05-06 | 2026-03-24 | 2026-05-06 | 1735.65 | 1735.65 | 1735.65 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 45 | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-06 | 6802.65 | 6802.65 | 6802.65 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-LL-IR-MA-10 | HDPE Pipes | 45 | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-06 | 2256.9 | 2256.9 | 2256.9 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-IR-MA-20 | Irrigation Control System | 45 | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-06 | 4545.75 | 4545.75 | 4545.75 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 50 | 2026-05-12 | 2026-07-13 | 2026-05-12 | 2026-09-17 | 17797.83 | 17797.83 | 17797.83 | 100% | 100% | 0 | 0 | 0 |  | 16 | 16 | 0 | 0
PG-T-PR-LL-EL-MA-10 | Main Distribution Board(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 1900-10-23 12:58 | 297.54 | 297.54 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-20 | Power Panels (Pump, Street Light)(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 1900-08-25 00:43 | 238.03 | 238.03 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-30 | Site Lighting Poles(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 6962.11 | 6962.11 | 6962.11 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-40 | Lighting Fixtures(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 769.7 | 769.7 | 769.7 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 1901-08-24 12:14 | 602.51 | 602.51 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 587.63 | 587.63 | 587.63 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-70 | Security and Access Control System Materials(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 743.94 | 743.94 | 743.94 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-80 | Fire Alarm System Materials(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 477.23 | 477.23 | 477.23 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-10_R | Main Distribution Board(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-17 | 2026-08-06 | 1900-07-16 08:38 | 198.36 | 198.36 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-20_R | Power Panels (Pump, Street Light)(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-17 | 2026-08-06 | 1900-06-06 16:34 | 158.69 | 1900-06-06 16:34 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-30_R | Site Lighting Poles(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-17 | 2026-08-06 | 4641.41 | 4641.41 | 4641.41 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-40_R | Lighting Fixtures(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-17 | 2026-07-23 | 1901-05-27 03:07 | 513.13 | 1901-05-27 03:07 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-17 | 2026-09-17 | 391.75 | 391.75 | 391.75 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-70_R | Security and Access Control System Materials(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-17 | 2026-09-17 | 495.96 | 1901-05-09 23:02 | 495.96 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-80_R | Fire Alarm System Materials(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-27 | 2026-09-17 | 318.16 | 318.16 | 318.16 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 2 | 2026-07-12 | 2026-07-13 | 2026-07-22 | 2026-07-28 | 401.68 | 401.68 | 401.68 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SHORT LEAD ITEMS |  | 25 | 2026-02-21 | 2026-03-26 | 2026-02-21 | 2026-03-26 | 56074.05 | 56074.05 | 56074.05 | 100% | 100% | 0 | 0 | 0 |  | 38 | 38 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 25 | 2026-02-21 | 2026-03-26 | 2026-02-21 | 2026-03-26 | 38542.29 | 38542.29 | 38542.29 | 100% | 100% | 0 | 0 | 0 |  | 8 | 8 | 0 | 0
PG-T-PR-SL-LS-MA-10 | Backfilling Materials | 25 | 2026-02-21 | 2026-03-26 | 2026-02-21 | 2026-03-26 | 10125 | 10125 | 10125 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MA-30 | Compacted Natural Ground Soil | 22 | 2026-02-25 | 2026-03-26 | 2026-02-25 | 2026-03-26 | 1287 | 1287 | 1287 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MA-60 | Traffic Signages | 11 | 2026-03-10 | 2026-03-26 | 2026-03-10 | 2026-03-26 | 1900-07-16 08:38 | 198.36 | 198.36 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MA-70 | Trees | 8 | 2026-03-14 | 2026-03-26 | 2026-03-14 | 2026-03-26 | 1906-04-24 02:24 | 2306.1 | 2306.1 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MA-80 | Lawn | 8 | 2026-03-14 | 2026-03-26 | 2026-03-14 | 2026-03-26 | 3045 | 3045 | 3045 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MA-50 | Thermoplastic pavement road marking | 6 | 2026-03-16 | 2026-03-26 | 2026-03-16 | 2026-03-26 | 525.63 | 525.63 | 525.63 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MA-20 | Interlock tiles | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 10715.4 | 10715.4 | 10715.4 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MA-40 | Curb Stone | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 10339.8 | 10339.8 | 10339.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 24 | 2026-02-23 | 2026-03-26 | 2026-02-23 | 2026-03-26 | 1609.47 | 1609.47 | 1609.47 | 100% | 100% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-T-PR-SL-CO-MA-10 | Steel Rebar | 14 | 2026-02-23 | 2026-03-10 | 2026-02-23 | 2026-03-10 | 1901-04-20 19:41 | 476.82 | 476.82 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-MA-20 | Concrete | 9 | 2026-03-01 | 2026-03-10 | 2026-03-01 | 2026-03-10 | 1901-06-01 20:24 | 518.85 | 518.85 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-MA-40 | CMU Block | 15 | 2026-03-05 | 2026-03-26 | 2026-03-05 | 2026-03-26 | 1900-05-03 04:48 | 124.2 | 124.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-MA-50 | Concrete Repair & Protection Materials | 15 | 2026-03-05 | 2026-03-26 | 2026-03-05 | 2026-03-26 | 372 | 372 | 372 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-MA-30 | Screed | 1 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 1900-04-26 14:24 | 117.6 | 117.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL & FINISHES WORK |  | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 7931.55 | 7931.55 | 7931.55 | 100% | 100% | 0 | 0 | 0 |  | 11 | 11 | 0 | 0
PG-T-PR-SL-AR-MA-10 | Ceramic tiles | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1901-07-24 22:48 | 571.95 | 571.95 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MA-20 | Anti-slip Granite tiles | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 535.5 | 535.5 | 535.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MA-30 | Epoxy Paint | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1900-04-20 04:19 | 111.18 | 111.18 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MA-40 | Cement Plaster | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1900-08-08 08:53 | 221.37 | 221.37 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MA-50 | Acrylic Paint | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 147.9 | 147.9 | 147.9 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MA-60 | Stone Cladding | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1852.2 | 1852.2 | 1852.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MA-70 | Phenolic Partition | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1340.4 | 1340.4 | 1340.4 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MA-80 | Glass Partition | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1900-06-03 09:36 | 155.4 | 155.4 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MA-90 | Gypsum Boards | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1900-07-06 13:55 | 188.58 | 188.58 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MA-100 | Specialities Materials (Toilet accessories, lockers, logo, etc) | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1906-03-11 20:53 | 2262.87 | 2262.87 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MA-110 | Waterproofing System Materials | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1901-06-27 04:48 | 544.2 | 544.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 10 | 2026-03-11 | 2026-03-26 | 2026-03-11 | 2026-03-26 | 1901-04-22 21:22 | 478.89 | 478.89 | 100% | 100% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-PR-SL-MT-MA-20 | Galvanized Steel Roof Scupper | 10 | 2026-03-11 | 2026-03-26 | 2026-03-11 | 2026-03-26 | 1900-01-30 07:41 | 31.32 | 31.32 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-MT-MA-30 | Galvanized Steel Cover with frame | 10 | 2026-03-11 | 2026-03-26 | 2026-03-11 | 2026-03-26 | 1900-03-25 17:02 | 85.71 | 85.71 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-MT-MA-10 | Galvanized Steel Ladder | 7 | 2026-03-15 | 2026-03-26 | 2026-03-15 | 2026-03-26 | 1900-12-26 20:38 | 361.86 | 361.86 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
HVAC WORK |  | 20 | 2026-02-28 | 2026-03-26 | 2026-02-28 | 2026-03-26 | 1901-08-28 08:38 | 606.36 | 606.36 | 100% | 100% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-PR-SL-AC-MA-10 | Split Air Conditioning Unit | 20 | 2026-02-28 | 2026-03-26 | 2026-02-28 | 2026-03-26 | 1900-11-04 22:19 | 309.93 | 309.93 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AC-MA-20 | Air Duct | 16 | 2026-03-04 | 2026-03-26 | 2026-03-04 | 2026-03-26 | 1900-06-04 | 156 | 156 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AC-MA-30 | Diffusers and Grills | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 74.31 | 74.31 | 74.31 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AC-MA-40 | Exhaust fans | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1900-03-06 02:53 | 66.12 | 66.12 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 3147.03 | 3147.03 | 3147.03 | 100% | 100% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-PR-SL-PB-MA-10 | PPR Pipes & Valves | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 265.2 | 265.2 | 265.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-PB-MA-20 | UPCV Pipes | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 335.19 | 335.19 | 335.19 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-PB-MA-30 | Sanitary Drainage Fixtures | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1906-12-20 15:22 | 2546.64 | 2546.64 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 3328.23 | 3328.23 | 3328.23 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-SL-IR-MA-10 | Gate Valve including valve box | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 413.28 | 413.28 | 413.28 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-IR-MA-20 | Bulbblers and Spreyers | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1907-12-23 22:48 | 2914.95 | 2914.95 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1901-02-10 12:29 | 407.52 | 407.52 | 100% | 100% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-T-PR-SL-EL-MA-10 | Wiring Devices Materials | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1901-02-10 12:29 | 407.52 | 407.52 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE FIGHTING WORK |  | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 22.71 | 22.71 | 22.71 | 100% | 100% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-T-PR-SL-FF-MA-10 | Fire Extinguishers | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 22.71 | 22.71 | 22.71 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PROCUREMENT |  | 149 | 2026-02-26 | 2026-08-27 | 2026-02-26 |  | 3066606.27 | 2662683.45 | 3066606.27 | 100% | 86.83% | 0 | 0 | 0 |  | 213 | 189 | 24 | 0
LONG LEAD ITEMS |  | 142 | 2026-03-07 | 2026-08-27 | 2026-03-07 |  | 2561939.82 | 2161684.91 | 2561939.82 | 100% | 84.38% | 0 | 0 | 0 |  | 121 | 105 | 16 | 0
PURCHASE ORDER |  | 106 | 2026-03-07 | 2026-07-16 | 2026-03-07 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 31 | 31 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 49 | 2026-03-07 | 2026-05-07 | 2026-03-07 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-PR-LL-LS-PO-20 | Benches, Seats (Rectangular & Circular) | 49 | 2026-03-07 | 2026-05-07 | 2026-03-07 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-PO-30 | Fence, gates and accessories | 36 | 2026-03-26 | 2026-05-07 | 2026-03-26 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-PO-10 | Bike and Walk Path Materials | 34 | 2026-03-29 | 2026-05-07 | 2026-03-29 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 93 | 2026-03-26 | 2026-07-16 | 2026-03-26 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-T-PR-LL-SP-PO-40 | Tartan Floor | 36 | 2026-03-26 | 2026-05-07 | 2026-03-26 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-PO-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc) | 35 | 2026-03-28 | 2026-05-07 | 2026-03-28 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-PO-20 | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc) | 35 | 2026-03-28 | 2026-05-07 | 2026-03-28 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-PO-30 | Padel Playgound Materials (Flooring, fence, tempered glass, etc) | 35 | 2026-03-28 | 2026-05-07 | 2026-03-28 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-PO-50 | Air Dome Materials | 5 | 2026-07-12 | 2026-07-16 | 2026-08-06 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 39 | 2026-03-18 | 2026-05-07 | 2026-03-18 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-T-PR-LL-CO-PO-10 | Autoclaved Aerated Panel | 39 | 2026-03-18 | 2026-05-07 | 2026-03-18 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 38 | 2026-03-24 | 2026-05-07 | 2026-03-24 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-LL-MT-PO-10 | Metal Doors | 38 | 2026-03-24 | 2026-05-07 | 2026-03-24 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-MT-PO-20 | Curtain Wall | 38 | 2026-03-24 | 2026-05-07 | 2026-03-24 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 35 | 2026-03-28 | 2026-05-07 | 2026-03-28 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-LL-PB-PO-10 | Booster Pump | 35 | 2026-03-28 | 2026-05-07 | 2026-03-28 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-PB-PO-20 | GRP Sectional Panel Water Tanks (4x3x3m) | 33 | 2026-03-30 | 2026-05-07 | 2026-03-30 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 40 | 2026-03-17 | 2026-05-07 | 2026-03-17 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-LL-IR-PO-20 | Irrigation Control System | 40 | 2026-03-17 | 2026-05-07 | 2026-03-17 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-IR-PO-10 | HDPE Pipes | 39 | 2026-03-18 | 2026-05-07 | 2026-03-18 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 54 | 2026-05-11 | 2026-07-16 | 2026-05-11 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 16 | 16 | 0 | 0
PG-T-PR-LL-EL-PO-10 | Main Distribution Board(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-20 | Power Panels (Pump, Street Light)(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-30 | Site Lighting Poles(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-40 | Lighting Fixtures(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-70 | Security and Access Control System Materials(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-80 | Fire Alarm System Materials(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-10_R | Main Distribution Board(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-07-26 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-20_R | Power Panels (Pump, Street Light)(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-07-26 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-30_R | Site Lighting Poles(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-07-26 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-40_R | Lighting Fixtures(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-07-23 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-08-27 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-70_R | Security and Access Control System Materials(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-08-27 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-80_R | Fire Alarm System Materials(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-08-27 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 3 | 2026-07-14 | 2026-07-16 | 2026-07-26 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MANUFACTURE / FABRICATION |  | 90 | 2026-04-29 | 2026-08-16 | 2026-04-29 | 2026-10-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 45 | 45 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 64 | 2026-05-06 | 2026-07-23 | 2026-05-06 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 6 | 6 | 0 | 0
PG-T-PR-LL-LS-MF-20 | Benches, Seats (Rectangular & Circular)(Completed) | 39 | 2026-05-06 | 2026-06-25 | 2026-05-06 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-MF-30 | Fence, gates and accessories(Completed) | 39 | 2026-05-06 | 2026-06-25 | 2026-05-06 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-MF-10 | Bike and Walk Path Materials(Completed) | 39 | 2026-05-06 | 2026-06-25 | 2026-05-06 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-MF-20_R | Benches, Seats (Rectangular & Circular)(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-05 | 2026-09-07 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-MF-30_R | Fence, gates and accessories(Remaining) | 6 | 2026-06-25 | 2026-07-01 | 2026-07-22 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-MF-10_R | Bike and Walk Path Materials(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-05 | 2026-09-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 84 | 2026-05-06 | 2026-08-16 | 2026-05-06 | 2026-10-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 9 | 9 | 0 | 0
PG-T-PR-LL-SP-MF-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc)(Completed) | 39 | 2026-05-06 | 2026-06-25 | 2026-05-06 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MF-20 | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc)(Completed) | 39 | 2026-05-06 | 2026-06-25 | 2026-05-06 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MF-30 | Padel Playgound Materials (Flooring, fence, tempered glass, etc)(Completed) | 39 | 2026-05-06 | 2026-06-25 | 2026-05-06 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MF-40 | Tartan Floor(Completed) | 39 | 2026-05-06 | 2026-06-25 | 2026-05-06 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MF-10_R | Football Playground Materials (Flooring, goal post, nets, paints, etc)(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-05 | 2026-09-02 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MF-20_R | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc)(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-05 | 2026-09-04 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MF-30_R | Padel Playgound Materials (Flooring, fence, tempered glass, etc)(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-05 | 2026-09-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MF-40_R | Tartan Floor(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-05 | 2026-09-19 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MF-50 | Air Dome Materials | 26 | 2026-07-18 | 2026-08-16 | 2026-08-27 | 2026-10-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 50 | 2026-04-29 | 2026-06-30 | 2026-04-29 | 2026-07-02 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-LL-CO-MF-10 | Autoclaved Aerated Panel(Completed) | 45 | 2026-04-29 | 2026-06-25 | 2026-04-29 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-CO-MF-10_R | Autoclaved Aerated Panel(Remaining) | 5 | 2026-06-25 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 64 | 2026-05-06 | 2026-07-23 | 2026-05-06 | 2026-09-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-PR-LL-MT-MF-10 | Metal Doors(Completed) | 39 | 2026-05-06 | 2026-06-25 | 2026-05-06 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-MT-MF-20 | Curtain Wall(Completed) | 39 | 2026-05-06 | 2026-06-25 | 2026-05-06 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-MT-MF-10_R | Metal Doors(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-27 | 2026-09-17 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-MT-MF-20_R | Curtain Wall(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-27 | 2026-09-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 64 | 2026-05-06 | 2026-07-23 | 2026-05-06 | 2026-09-14 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-PR-LL-PB-MF-10 | Booster Pump(Completed) | 39 | 2026-05-06 | 2026-06-25 | 2026-05-06 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-PB-MF-20 | GRP Sectional Panel Water Tanks (4x3x3m)(Completed) | 39 | 2026-05-06 | 2026-06-25 | 2026-05-06 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-PB-MF-10_R | Booster Pump(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-06-25 | 2026-07-02 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-PB-MF-20_R | GRP Sectional Panel Water Tanks (4x3x3m)(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-05 | 2026-09-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 44 | 2026-05-06 | 2026-06-30 | 2026-05-06 | 2026-09-21 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-PR-LL-IR-MF-10 | HDPE Pipes(Completed) | 39 | 2026-05-06 | 2026-06-25 | 2026-05-06 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-IR-MF-20 | Irrigation Control System(Completed) | 39 | 2026-05-06 | 2026-06-25 | 2026-05-06 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-IR-MF-10_R | HDPE Pipes(Remaining) | 5 | 2026-06-25 | 2026-06-30 | 2026-08-14 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-IR-MF-20_R | Irrigation Control System(Remaining) | 5 | 2026-06-25 | 2026-06-30 | 2026-08-27 | 2026-09-21 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 74 | 2026-05-12 | 2026-08-10 | 2026-05-12 | 2026-09-30 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 16 | 16 | 0 | 0
PG-T-PR-LL-EL-MF-10 | Main Distribution Board(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-20 | Power Panels (Pump, Street Light)(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-30 | Site Lighting Poles(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-40 | Lighting Fixtures(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-70 | Security and Access Control System Materials(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-80 | Fire Alarm System Materials(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-10_R | Main Distribution Board(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-08-06 | 2026-09-28 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-20_R | Power Panels (Pump, Street Light)(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-08-06 | 2026-09-26 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-30_R | Site Lighting Poles(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-08-06 | 2026-09-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-40_R | Lighting Fixtures(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-07-23 | 2026-09-30 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-08-27 | 2026-09-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-70_R | Security and Access Control System Materials(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-08-27 | 2026-09-30 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-80_R | Fire Alarm System Materials(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-08-27 | 2026-09-30 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 6 | 2026-07-18 | 2026-07-23 | 2026-08-27 | 2026-09-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
DELIVERY TO SITE |  | 94 | 2026-05-06 | 2026-08-27 | 2026-05-06 |  | 2561939.82 | 2161684.91 | 2561939.82 | 100% | 84.38% | 0 | 0 | 0 |  | 45 | 29 | 16 | 0
EXTERNAL / LANDSCAPE WORK |  | 76 | 2026-05-06 | 2026-08-06 | 2026-05-06 |  | 138827.52 | 137434.65 | 138827.52 | 100% | 99% | 0 | 0 | 0 |  | 6 | 5 | 1 | 0
PG-T-PR-LL-LS-DL-20 | Benches, Seats (Rectangular & Circular)(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 20892.98 | 20892.98 | 20892.98 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-DL-30 | Fence, gates and accessories(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 11381.45 | 11381.45 | 11381.45 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-DL-10 | Bike and Walk Path Materials(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 56870.1 | 56870.1 | 56870.1 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-DL-30_R | Fence, gates and accessories(Remaining) | 5 | 2026-07-02 | 2026-07-07 | 2026-07-23 | 2026-09-19 | 11381.45 | 11381.45 | 11381.45 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-DL-20_R | Benches, Seats (Rectangular & Circular)(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-14 |  | 13928.65 | 12535.79 | 13928.65 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-T-PR-LL-LS-DL-10_R | Bike and Walk Path Materials(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-06 | 2026-09-28 | 24372.9 | 24372.9 | 24372.9 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 94 | 2026-05-06 | 2026-08-27 | 2026-05-06 |  | 2148961.86 | 1759714.44 | 2148961.86 | 100% | 81.89% | 0 | 0 | 0 |  | 9 | 4 | 5 | 0
PG-T-PR-LL-SP-DL-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc)(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 58731.75 | 58731.75 | 58731.75 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-DL-20 | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc)(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 10152 | 10152 | 10152 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-DL-30 | Padel Playgound Materials (Fence, tempered glass, etc)(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 26778.6 | 26778.6 | 26778.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-DL-40 | Tartan Floor(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 39487.5 | 39487.5 | 39487.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-DL-10_R | Football Playground Materials (Flooring, goal post, nets, paints, etc)(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-14 |  | 58731.75 | 52858.58 | 58731.75 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-T-PR-LL-SP-DL-20_R | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc)(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-14 |  | 10152 | 9136.8 | 10152 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-T-PR-LL-SP-DL-30_R | Padel Playgound Materials (Fence, tempered glass, etc)(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-14 |  | 26778.6 | 24100.74 | 26778.6 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-T-PR-LL-SP-DL-40_R | Tartan Floor(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-06 |  | 39487.5 | 35538.75 | 39487.5 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-T-PR-LL-SP-DL-50 | Air Dome Materials | 10 | 2026-08-17 | 2026-08-27 | 2026-10-18 |  | 1878662.16 | 1502929.73 | 1878662.16 | 100% | 80% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
CONCRETE WORK |  | 49 | 2026-05-06 | 2026-07-06 | 2026-05-06 | 2026-07-05 | 12757.5 | 12757.5 | 12757.5 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-LL-CO-DL-10 | Autoclaved Aerated Panel(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 8930.25 | 8930.25 | 8930.25 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-CO-DL-10_R | Autoclaved Aerated Panel(Remaining) | 5 | 2026-07-01 | 2026-07-06 | 2026-07-04 | 2026-07-05 | 3827.25 | 3827.25 | 3827.25 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 76 | 2026-05-06 | 2026-08-06 | 2026-05-06 |  | 8003.07 | 6974.78 | 8003.07 | 100% | 87.15% | 0 | 0 | 0 |  | 4 | 3 | 1 | 0
PG-T-PR-LL-MT-DL-10 | Metal Doors(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 573.89 | 573.89 | 573.89 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-MT-DL-20 | Curtain Wall(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 1909-05-19 15:36 | 1909-05-19 15:36 | 3427.65 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-MT-DL-10_R | Metal Doors(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-27 | 2026-10-15 | 573.89 | 573.89 | 573.89 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-MT-DL-20_R | Curtain Wall(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-27 |  | 3427.65 | 2399.36 | 3427.65 | 100% | 70% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PLUMBING WORK |  | 76 | 2026-05-06 | 2026-08-06 | 2026-05-06 | 2026-10-15 | 31985.55 | 31985.55 | 31985.55 | 100% | 100% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-PR-LL-PB-DL-10 | Booster Pump(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 9818.82 | 9818.82 | 9818.82 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-PB-DL-20 | GRP Sectional Panel Water Tanks (4x3x3m)(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 9372.51 | 9372.51 | 9372.51 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-PB-DL-10_R | Booster Pump(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-27 | 2026-09-26 | 6545.88 | 6545.88 | 6545.88 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-PB-DL-20_R | GRP Sectional Panel Water Tanks (4x3x3m)(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-14 | 2026-10-15 | 6248.34 | 6248.34 | 6248.34 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 48 | 2026-05-06 | 2026-07-05 | 2026-05-06 |  | 61223.85 | 59587.38 | 61223.85 | 100% | 97.33% | 0 | 0 | 0 |  | 4 | 3 | 1 | 0
PG-T-PR-LL-IR-DL-10 | HDPE Pipes(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 12187.26 | 12187.26 | 12187.26 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-IR-DL-20 | Irrigation Control System(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 24547.05 | 24547.05 | 24547.05 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-IR-DL-10_R | HDPE Pipes(Remaining) | 4 | 2026-07-01 | 2026-07-05 | 2026-08-07 | 2026-09-22 | 8124.84 | 8124.84 | 8124.84 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-IR-DL-20_R | Irrigation Control System(Remaining) | 4 | 2026-07-01 | 2026-07-05 | 2026-08-20 |  | 16364.7 | 14728.23 | 16364.7 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
ELECTRICAL WORK |  | 85 | 2026-05-13 | 2026-08-24 | 2026-05-13 |  | 160180.47 | 153230.61 | 160180.47 | 100% | 95.66% | 0 | 0 | 0 |  | 16 | 8 | 8 | 0
PG-T-PR-LL-EL-DL-10 | Main Distribution Board(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 2677.86 | 2677.86 | 2677.86 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-DL-20 | Power Panels (Pump, Street Light)(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 2142.29 | 2142.29 | 2142.29 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-DL-30 | Site Lighting Poles(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 62659.01 | 62659.01 | 62659.01 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-DL-40 | Lighting Fixtures(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 6927.28 | 6927.28 | 6927.28 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-DL-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 5422.63 | 5422.63 | 5422.63 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-DL-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 5288.65 | 5288.65 | 5288.65 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-DL-70 | Security and Access Control System Materials(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 6695.46 | 6695.46 | 6695.46 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-DL-80 | Fire Alarm System Materials(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 4295.11 | 4295.11 | 4295.11 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-DL-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 4 | 2026-07-25 | 2026-07-28 | 2026-08-14 |  | 3615.08 | 3253.58 | 3615.08 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-T-PR-LL-EL-DL-10_R | Main Distribution Board(Remaining) | 12 | 2026-08-11 | 2026-08-24 | 2026-08-14 |  | 1785.24 | 1904-05-24 17:17 | 1785.24 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-T-PR-LL-EL-DL-20_R | Power Panels (Pump, Street Light)(Remaining) | 12 | 2026-08-11 | 2026-08-24 | 2026-08-14 |  | 1428.19 | 1285.37 | 1428.19 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-T-PR-LL-EL-DL-30_R | Site Lighting Poles(Remaining) | 12 | 2026-08-11 | 2026-08-24 | 2026-08-14 |  | 41772.67 | 2002-12-05 09:36 | 41772.67 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-T-PR-LL-EL-DL-40_R | Lighting Fixtures(Remaining) | 12 | 2026-08-11 | 2026-08-24 | 2026-08-14 |  | 4618.19 | 4156.37 | 4618.19 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-T-PR-LL-EL-DL-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 12 | 2026-08-11 | 2026-08-24 | 2026-08-27 |  | 1909-08-25 18:29 | 1908-03-14 21:36 | 3525.77 | 100% | 85% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-T-PR-LL-EL-DL-70_R | Security and Access Control System Materials(Remaining) | 12 | 2026-08-11 | 2026-08-24 | 2026-08-27 |  | 4463.64 | 3794.09 | 4463.64 | 100% | 85% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-T-PR-LL-EL-DL-80_R | Fire Alarm System Materials(Remaining) | 12 | 2026-08-11 | 2026-08-24 | 2026-08-27 |  | 2863.4 | 2433.89 | 2863.4 | 100% | 85% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
SHORT LEAD ITEMS |  | 118 | 2026-02-26 | 2026-07-22 | 2026-02-26 |  | 504666.45 | 500998.54 | 504666.45 | 100% | 99.27% | 0 | 0 | 0 |  | 92 | 84 | 8 | 0
MATERIAL SUBMITTALS |  | 0 |  |  |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
PURCHASE ORDER |  | 108 | 2026-02-26 | 2026-07-11 | 2026-02-26 | 2026-08-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 44 | 44 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 108 | 2026-02-26 | 2026-07-11 | 2026-02-26 | 2026-08-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PG-T-PR-SL-LS-PO-10 | Backfilling Materials | 44 | 2026-02-26 | 2026-04-23 | 2026-02-26 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-PO-30 | Compacted Natural Ground Soil | 42 | 2026-03-01 | 2026-04-23 | 2026-03-01 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-PO-20 | Interlock tiles | 28 | 2026-03-29 | 2026-04-30 | 2026-03-29 | 2026-04-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-PO-40 | Curb Stone | 23 | 2026-04-04 | 2026-04-30 | 2026-04-04 | 2026-04-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-PO-50 | Thermoplastic pavement road marking(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-PO-60 | Traffic Signages(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-PO-70 | Trees(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-PO-80 | Lawn(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-PO-50_R | Thermoplastic pavement road marking(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-20 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-PO-70_R | Trees(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-20 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-PO-80_R | Lawn(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-20 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-PO-60_R | Traffic Signages(Remaining) | 7 | 2026-07-04 | 2026-07-11 | 2026-08-20 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 41 | 2026-03-02 | 2026-04-23 | 2026-03-02 | 2026-04-22 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-T-PR-SL-CO-PO-10 | Steel Rebar | 41 | 2026-03-02 | 2026-04-23 | 2026-03-02 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-PO-20 | Concrete | 36 | 2026-03-08 | 2026-04-23 | 2026-03-08 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-PO-40 | CMU Block | 33 | 2026-03-11 | 2026-04-23 | 2026-03-11 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-PO-50 | Concrete Repair & Protection Materials | 32 | 2026-03-12 | 2026-04-23 | 2026-03-12 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-PO-30 | Screed | 23 | 2026-03-28 | 2026-04-23 | 2026-03-28 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL & FINISHES WORK |  | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 11 | 11 | 0 | 0
PG-T-PR-SL-AR-PO-10 | Ceramic tiles | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-PO-20 | Anti-slip Granite tiles | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-PO-30 | Epoxy Paint | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-PO-40 | Cement Plaster | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-PO-50 | Acrylic Paint | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-PO-60 | Stone Cladding | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-PO-70 | Phenolic Partition | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-PO-80 | Glass Partition | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-PO-90 | Gypsum Boards | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-PO-100 | Specialities Materials (Toilet accessories, lockers, logo, etc) | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-PO-110 | Waterproofing System Materials | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-PR-SL-MT-PO-10 | Galvanized Steel Ladder | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-MT-PO-20 | Galvanized Steel Roof Scupper | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-MT-PO-30 | Galvanized Steel Cover with frame | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
HVAC WORK |  | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-PR-SL-AC-PO-10 | Split Air Conditioning Unit | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AC-PO-20 | Air Duct | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AC-PO-30 | Diffusers and Grills | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AC-PO-40 | Exhaust fans | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-PR-SL-PB-PO-10 | PPR Pipes & Valves | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-PB-PO-20 | UPCV Pipes | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-PB-PO-30 | Sanitary Drainage Fixtures | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-SL-IR-PO-10 | Gate Valve including valve box | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-IR-PO-20 | Bulbblers and Spreyers | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 42 | 2026-05-11 | 2026-07-02 | 2026-05-11 | 2026-08-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-SL-EL-PO-10 | Wiring Devices Materials(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-EL-PO-10_R | Wiring Devices Materials(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-20 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE FIGHTING WORK |  | 39 | 2026-05-11 | 2026-06-29 | 2026-05-11 | 2026-08-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-SL-FF-PO-10 | Fire Extinguishers(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-FF-PO-10_R | Fire Extinguishers(Remaining) | 4 | 2026-06-25 | 2026-06-29 | 2026-08-20 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
DELIVERY TO SITE |  | 116 | 2026-03-01 | 2026-07-22 | 2026-03-01 |  | 504666.45 | 500998.54 | 504666.45 | 100% | 99.27% | 0 | 0 | 0 |  | 48 | 40 | 8 | 0
EXTERNAL / LANDSCAPE WORK |  | 116 | 2026-03-01 | 2026-07-22 | 2026-03-01 |  | 346880.61 | 344882.8 | 346880.61 | 100% | 99.42% | 0 | 0 | 0 |  | 11 | 8 | 3 | 0
PG-T-PR-SL-LS-DL-10 | Backfilling Materials | 43 | 2026-03-01 | 2026-04-23 | 2026-03-01 | 2026-04-24 | 91125 | 91125 | 91125 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-DL-30 | Compacted Natural Ground Soil | 41 | 2026-03-03 | 2026-04-23 | 2026-03-03 | 2026-04-24 | 11583 | 11583 | 11583 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-DL-20 | Interlock tiles | 13 | 2026-04-29 | 2026-05-13 | 2026-04-29 | 2026-05-13 | 96438.6 | 96438.6 | 96438.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-DL-40 | Curb Stone | 13 | 2026-04-29 | 2026-05-13 | 2026-04-29 | 2026-05-13 | 93058.2 | 93058.2 | 93058.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-DL-50 | Thermoplastic pavement road marking | 1 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 4730.67 | 4730.67 | 4730.67 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-DL-60 | Traffic Signages(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 1071.14 | 1071.14 | 1071.14 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-DL-70 | Trees(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 12452.94 | 12452.94 | 12452.94 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-DL-80 | Lawn(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 16443 | 16443 | 16443 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-DL-60_R | Traffic Signages(Remaining) | 10 | 2026-07-12 | 2026-07-22 | 2026-08-27 |  | 714.1 | 642.69 | 714.1 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-T-PR-SL-LS-DL-70_R | Trees(Remaining) | 10 | 2026-07-12 | 2026-07-22 | 2026-08-27 |  | 8301.96 | 7471.76 | 8301.96 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-T-PR-SL-LS-DL-80_R | Lawn(Remaining) | 10 | 2026-07-12 | 2026-07-22 | 2026-08-27 |  | 10962 | 9865.8 | 10962 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
CONCRETE WORK |  | 52 | 2026-03-10 | 2026-05-13 | 2026-03-10 | 2026-05-13 | 14485.23 | 14485.23 | 14485.23 | 100% | 100% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-T-PR-SL-CO-DL-20 | Concrete | 35 | 2026-03-10 | 2026-04-23 | 2026-03-10 | 2026-04-24 | 4669.65 | 4669.65 | 4669.65 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-DL-10 | Steel Rebar | 18 | 2026-04-23 | 2026-05-13 | 2026-04-23 | 2026-05-13 | 4291.38 | 4291.38 | 4291.38 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-DL-30 | Screed | 18 | 2026-04-23 | 2026-05-13 | 2026-04-23 | 2026-05-13 | 1058.4 | 1058.4 | 1058.4 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-DL-40 | CMU Block | 18 | 2026-04-23 | 2026-05-13 | 2026-04-23 | 2026-05-13 | 1117.8 | 1117.8 | 1117.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-DL-50 | Concrete Repair & Protection Materials | 18 | 2026-04-23 | 2026-05-13 | 2026-04-23 | 2026-05-13 | 3348 | 3348 | 3348 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL & FINISHES WORK |  | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 71383.95 | 71383.95 | 71383.95 | 100% | 100% | 0 | 0 | 0 |  | 11 | 11 | 0 | 0
PG-T-PR-SL-AR-DL-10 | Ceramic tiles | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 5147.55 | 5147.55 | 5147.55 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-DL-20 | Anti-slip Granite tiles | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 4819.5 | 4819.5 | 4819.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-DL-30 | Epoxy Paint | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 1000.62 | 1000.62 | 1000.62 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-DL-40 | Cement Plaster | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 1992.33 | 1992.33 | 1992.33 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-DL-50 | Acrylic Paint | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 1331.1 | 1331.1 | 1331.1 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-DL-60 | Stone Cladding | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 16669.8 | 16669.8 | 16669.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-DL-70 | Phenolic Partition | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 12063.6 | 12063.6 | 12063.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-DL-80 | Glass Partition | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 1398.6 | 1398.6 | 1398.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-DL-90 | Gypsum Boards | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 1697.22 | 1697.22 | 1697.22 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-DL-100 | Specialities Materials (Toilet accessories, lockers, logo, etc) | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 20365.83 | 20365.83 | 20365.83 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-DL-110 | Waterproofing System Materials | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 4897.8 | 4897.8 | 4897.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 51 | 2026-05-06 | 2026-07-08 | 2026-05-06 |  | 4310.01 | 4137.61 | 4310.01 | 100% | 96% | 0 | 0 | 0 |  | 6 | 3 | 3 | 0
PG-T-PR-SL-MT-DL-10 | Galvanized Steel Ladder(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 1905-05-07 00:58 | 1905-05-07 00:58 | 1905-05-07 00:58 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-MT-DL-20 | Galvanized Steel Roof Scupper(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 1900-06-17 03:07 | 169.13 | 169.13 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-MT-DL-30 | Galvanized Steel Cover with frame(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 462.83 | 462.83 | 462.83 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-MT-DL-10_R | Galvanized Steel Ladder(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-09-23 |  | 1302.7 | 1172.43 | 1302.7 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-T-PR-SL-MT-DL-20_R | Galvanized Steel Roof Scupper(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-09-24 |  | 112.75 | 101.48 | 112.75 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-T-PR-SL-MT-DL-30_R | Galvanized Steel Cover with frame(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-09-24 |  | 308.56 | 277.7 | 308.56 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
HVAC WORK |  | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 5457.24 | 5457.24 | 5457.24 | 100% | 100% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-PR-SL-AC-DL-10 | Split Air Conditioning Unit | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 1907-08-20 08:53 | 2789.37 | 2789.37 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AC-DL-20 | Air Duct | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 1404 | 1404 | 1404 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AC-DL-30 | Diffusers and Grills | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 668.79 | 668.79 | 668.79 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AC-DL-40 | Exhaust fans | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 595.08 | 595.08 | 595.08 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 28323.27 | 28323.27 | 28323.27 | 100% | 100% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-PR-SL-PB-DL-10 | PPR Pipes & Valves | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 2386.8 | 2386.8 | 2386.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-PB-DL-20 | UPCV Pipes | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 3016.71 | 3016.71 | 3016.71 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-PB-DL-30 | Sanitary Drainage Fixtures | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 22919.76 | 22919.76 | 22919.76 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 48 | 2026-05-06 | 2026-07-05 | 2026-05-06 |  | 29954.07 | 28456.37 | 29954.07 | 100% | 95% | 0 | 0 | 0 |  | 4 | 2 | 2 | 0
PG-T-PR-SL-IR-DL-10 | Gate Valve including valve box(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 1859.76 | 1859.76 | 1859.76 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-IR-DL-20 | Bulbblers and Spreyers(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 13117.28 | 13117.28 | 13117.28 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-IR-DL-10_R | Gate Valve including valve box(Remaining) | 9 | 2026-06-25 | 2026-07-05 | 2026-08-07 |  | 1859.76 | 1673.78 | 1859.76 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-T-PR-SL-IR-DL-20_R | Bulbblers and Spreyers(Remaining) | 9 | 2026-06-25 | 2026-07-05 | 2026-08-20 |  | 13117.28 | 1932-04-26 13:12 | 13117.28 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
ELECTRICAL WORK |  | 52 | 2026-05-13 | 2026-07-16 | 2026-05-13 | 2026-10-15 | 3667.68 | 3667.68 | 3667.68 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-SL-EL-DL-10 | Wiring Devices Materials(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 1467.07 | 1467.07 | 1467.07 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-EL-DL-10_R | Wiring Devices Materials(Remaining) | 12 | 2026-07-04 | 2026-07-16 | 2026-09-19 | 2026-10-15 | 2200.61 | 1906-01-08 14:38 | 2200.61 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE FIGHTING WORK |  | 46 | 2026-05-13 | 2026-07-09 | 2026-05-13 | 2026-10-15 | 204.39 | 204.39 | 204.39 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-SL-FF-DL-10 | Fire Extinguishers(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 81.76 | 81.76 | 81.76 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-FF-DL-10_R | Fire Extinguishers(Remaining) | 9 | 2026-06-30 | 2026-07-09 | 2026-09-27 | 2026-10-15 | 122.63 | 122.63 | 122.63 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONSTRUCTION STAGE |  | 223 | 2026-03-24 | 2026-12-14 | 2026-03-24 |  | 5075372.6 | 3557503.09 | 6814680.6 | 74.48% | 52.2% | 8112 | 6588 | 6217 |  | 174 | 99 | 44 | 31
PLAYGROUND AND LANDSCAPING WORKS |  | 223 | 2026-03-24 | 2026-12-14 | 2026-03-24 |  | 1913311.43 | 2041669.63 | 2311795.02 | 82.76% | 88.32% | 5288 | 4288 | 4204 |  | 113 | 58 | 38 | 17
CUT AND FILL |  | 38 | 2026-03-24 | 2026-05-06 | 2026-03-24 | 2026-05-06 | 228240 | 228240 | 228240 | 100% | 100% | 376 | 376 | 376 |  | 3 | 3 | 0 | 0
PG-T-CON-EX-CF-10 | Existing Soil Excavation Works | 22 | 2026-03-24 | 2026-04-18 | 2026-03-24 | 2026-04-18 | 64800 | 64800 | 64800 | 100% | 100% | 172 | 172 | 172 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-CF-20 | Soil Replacement Works | 18 | 2026-04-07 | 2026-04-27 | 2026-04-07 | 2026-04-27 | 25740 | 25740 | 25740 | 100% | 100% | 100 | 100 | 100 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-CF-30 | Levelling & Backfilling Works | 17 | 2026-04-18 | 2026-05-06 | 2026-04-18 | 2026-05-06 | 137700 | 137700 | 137700 | 100% | 100% | 104 | 104 | 104 | No | 1 | 1 | 0 | 0
PLAYGROUND WORKS |  | 191 | 2026-04-23 | 2026-12-07 | 2026-04-23 |  | 522480.95 | 535284.26 | 623491.2 | 83.8% | 85.85% | 1896 | 1617 | 1599 |  | 35 | 20 | 11 | 4
FOOTBALL PLAYGROUND WORKS |  | 174 | 2026-04-23 | 2026-11-17 | 2026-04-23 |  | 293362.8 | 297308.33 | 333290.16 | 88.02% | 89.2% | 864 | 726 | 754 |  | 13 | 8 | 4 | 1
PG-T-CON-EX-FB-10 | Subgrade Preparation and Compaction | 12 | 2026-04-23 | 2026-05-06 | 2026-04-23 | 2026-05-06 | 23667 | 23667 | 23667 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-FB-20 | Sub-Base Laying and Compaction | 8 | 2026-04-28 | 2026-05-06 | 2026-04-28 | 2026-05-06 | 23667 | 23667 | 23667 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-FB-30 | Base Course Laying and Compaction | 33 | 2026-05-06 | 2026-06-17 | 2026-05-06 | 2026-06-17 | 23667 | 23667 | 23667 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-FB-70 | Topsoil Placement(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 9466.8 | 9466.8 | 9466.8 | 100% | 100% | 34 | 34 | 34 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-FB-80 | Fine Grading & Leveling | 15 | 2026-06-25 | 2026-07-12 | 2026-07-07 | 2026-07-12 | 23667 | 23667 | 23667 | 100% | 100% | 76 | 76 | 76 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-FB-70_R | Topsoil Placement(Remaining) | 15 | 2026-07-13 | 2026-07-29 | 2026-07-09 | 2026-07-12 | 14200.2 | 14200.2 | 14200.2 | 100% | 100% | 50 | 50 | 50 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-FB-50 | Goal Post Foundation | 17 | 2026-07-30 | 2026-08-18 | 2026-07-23 | 2026-08-14 | 35500.5 | 35500.5 | 35500.5 | 100% | 100% | 100 | 100 | 100 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-FB-120 | Installation of Lighting System | 13 | 2026-08-19 | 2026-09-02 | 2026-08-20 |  | 24360 | 21924 | 24360 | 100% | 90% | 32 | 32 | 29 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-FB-90 | Turfing / Seeding Works | 12 | 2026-09-03 | 2026-09-16 | 2026-08-14 |  | 23667 | 21300.3 | 23667 | 100% | 90% | 48 | 48 | 43 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-FB-40 | Tartan flooring | 15 | 2026-09-17 | 2026-10-05 | 2026-08-14 | 2026-08-14 | 2092-03-12 | 70200 | 70200 | 100% | 100% | 64 | 64 | 64 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-FB-60 | Goal Post Installation & Alignment | 15 | 2026-10-06 | 2026-10-22 | 2026-08-20 |  | 21300.3 | 28400.4 | 35500.5 | 60% | 80% | 56 | 34 | 45 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-FB-110 | Install Playground Benches | 12 | 2026-10-24 | 2026-11-05 | 2026-08-27 |  | 0 | 1648.13 | 2060.16 | 0% | 80% | 32 | 0 | 26 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-FB-100 | Markings and Signages | 10 | 2026-11-07 | 2026-11-17 |  |  | 0 | 0 | 23667 | 0% | 0% | 84 | 0 | 0 | No | 1 | 0 | 0 | 1
BASKETBALL PLAYGROUND WORKS |  | 163 | 2026-05-06 | 2026-11-17 | 2026-05-06 |  | 162424.76 | 157108.46 | 173211.12 | 93.77% | 90.7% | 608 | 548 | 556 |  | 11 | 7 | 3 | 1
PG-T-CON-EX-BB-10 | Subgrade Preparation and Compaction | 1 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 15472.08 | 15472.08 | 15472.08 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-BB-20 | Sub-Base Laying and Compaction | 1 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 15472.08 | 15472.08 | 15472.08 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-BB-30 | Base Course Laying and Compaction | 33 | 2026-05-06 | 2026-06-17 | 2026-05-06 | 2026-06-17 | 15472.08 | 15472.08 | 15472.08 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-BB-70 | Floor Surface Curing(Completed) | 7 | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 7736.04 | 7736.04 | 7736.04 | 100% | 100% | 12 | 12 | 12 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-BB-50 | Basketball Pole Foundation | 25 | 2026-06-25 | 2026-07-23 | 2026-08-06 | 2026-08-14 | 15472.08 | 15472.08 | 15472.08 | 100% | 100% | 100 | 100 | 100 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-BB-70_R | Floor Surface Curing(Remaining) | 15 | 2026-07-25 | 2026-08-10 | 2026-07-09 | 2026-07-12 | 7736.04 | 7736.04 | 7736.04 | 100% | 100% | 12 | 12 | 12 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-BB-40 | Tartan flooring | 17 | 2026-08-11 | 2026-08-30 | 2026-07-12 | 2026-08-14 | 52650 | 52650 | 52650 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-BB-80 | Court Line Marking | 16 | 2026-08-31 | 2026-09-17 | 2026-08-20 |  | 1935-11-03 18:14 | 1932-04-03 13:55 | 13091.76 | 100% | 90% | 28 | 28 | 25 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-BB-60 | Basketball Pole Installation & Alignment | 18 | 2026-09-19 | 2026-10-10 | 2026-08-20 |  | 15472.08 | 13924.87 | 15472.08 | 100% | 90% | 56 | 56 | 50 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-BB-90 | Backboard & Hoop Installation | 17 | 2026-10-11 | 2026-10-29 |  |  | 3850.52 | 0 | 13091.76 | 29.41% | 0% | 40 | 12 | 0 | No | 1 | 0 | 0 | 1
PG-T-CON-EX-BB-100 | Install Playground Benches | 16 | 2026-10-31 | 2026-11-17 | 2026-08-27 |  | 0 | 1390.61 | 1545.12 | 0% | 90% | 32 | 0 | 29 | No | 1 | 0 | 1 | 0
PADEL PLAYGROUND WORKS |  | 180 | 2026-05-06 | 2026-12-07 | 2026-05-06 |  | 66693.39 | 80867.47 | 116989.92 | 57.01% | 69.12% | 424 | 344 | 288 |  | 11 | 5 | 4 | 2
PG-T-CON-EX-PD-10 | Excavation For Fence Footing(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 16243.2 | 16243.2 | 16243.2 | 100% | 100% | 54 | 54 | 54 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-PD-20 | RC Foundations For Fence(Completed) | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 1767.48 | 1767.48 | 1767.48 | 100% | 100% | 24 | 24 | 24 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-PD-30 | Tartan Flooring Layers(Completed) | 7 | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 26325 | 26325 | 26325 | 100% | 100% | 20 | 20 | 20 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-PD-10_R | Excavation For Fence Footing(Remaining) | 8 | 2026-06-25 | 2026-07-04 | 2026-08-06 | 2026-08-14 | 1804.8 | 1804.8 | 1804.8 | 100% | 100% | 6 | 6 | 6 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-PD-20_R | RC Foundations For Fence(Remaining) | 20 | 2026-07-05 | 2026-07-27 | 2026-08-14 | 2026-08-27 | 1767.48 | 1904-11-01 11:31 | 1767.48 | 100% | 100% | 24 | 24 | 24 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-PD-40 | Steel Structure & Fence Supports Installation | 20 | 2026-08-08 | 2026-08-30 | 2026-08-20 |  | 3534.96 | 3181.46 | 3534.96 | 100% | 90% | 56 | 56 | 50 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-PD-60 | Chain Link Fence & Gates Installation | 18 | 2026-08-31 | 2026-09-20 | 2026-08-20 |  | 1914-07-07 10:34 | 1913-01-23 04:48 | 5302.44 | 100% | 90% | 72 | 72 | 65 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-PD-50 | Tempered Glass Installation | 18 | 2026-09-21 | 2026-10-12 |  |  | 1914-07-07 10:34 | 0 | 5302.44 | 100% | 0% | 84 | 84 | 0 | No | 1 | 0 | 0 | 1
PG-T-CON-EX-PD-30_R | Tartan Flooring Layers(Remaining) | 17 | 2026-10-13 | 2026-11-01 | 2026-08-20 |  | 4645.59 | 23692.5 | 26325 | 17.65% | 90% | 20 | 4 | 18 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-PD-70 | Court Accessories Installation | 16 | 2026-11-02 | 2026-11-19 |  |  | 0 | 0 | 27072 | 0% | 0% | 32 | 0 | 0 | No | 1 | 0 | 0 | 1
PG-T-CON-EX-PD-80 | Install Playground Benches | 15 | 2026-11-21 | 2026-12-07 | 2026-08-27 |  | 0 | 1313.35 | 1545.12 | 0% | 85% | 32 | 0 | 27 | No | 1 | 0 | 1 | 0
GENERAL SITE WORKS |  | 203 | 2026-04-16 | 2026-12-14 | 2026-04-16 |  | 582912.18 | 515172.26 | 656604.42 | 88.78% | 78.46% | 1996 | 1456 | 1284 |  | 47 | 15 | 20 | 12
FENCE WORKS |  | 102 | 2026-04-16 | 2026-08-17 | 2026-04-16 | 2026-10-15 | 32909.4 | 32909.4 | 32909.4 | 100% | 100% | 336 | 336 | 336 |  | 5 | 5 | 0 | 0
PG-T-CON-EX-GN-FN-10 | Excavation for fence foundation | 3 | 2026-04-16 | 2026-04-19 | 2026-04-16 | 2026-04-19 | 6581.88 | 6581.88 | 6581.88 | 100% | 100% | 92 | 92 | 92 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-GN-FN-20 | Concrete Foundations for Fence | 12 | 2026-07-13 | 2026-07-26 | 2026-08-13 | 2026-10-14 | 6581.88 | 1918-01-06 21:07 | 6581.88 | 100% | 100% | 68 | 68 | 68 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-GN-FN-30 | Installation of Galvanized Steel Posts & Framing | 7 | 2026-07-27 | 2026-08-03 | 2026-08-20 | 2026-10-15 | 6581.88 | 6581.88 | 6581.88 | 100% | 100% | 56 | 56 | 56 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-GN-FN-40 | Fixing of Chain Link Mesh, Tensioning & Bracing | 6 | 2026-08-04 | 2026-08-10 | 2026-09-20 | 2026-10-15 | 6581.88 | 6581.88 | 6581.88 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-GN-FN-50 | Installation of Gates | 6 | 2026-08-11 | 2026-08-17 | 2026-10-11 | 2026-10-15 | 6581.88 | 6581.88 | 6581.88 | 100% | 100% | 72 | 72 | 72 | No | 1 | 1 | 0 | 0
MECHANICAL WORK |  | 74 | 2026-05-12 | 2026-08-10 | 2026-05-12 |  | 230187.54 | 201030.97 | 230187.54 | 100% | 87.33% | 476 | 476 | 317 |  | 13 | 4 | 5 | 4
STORM WATER AND UTILITY WORK |  | 69 | 2026-05-12 | 2026-08-04 | 2026-05-12 |  | 27252 | 16806 | 27252 | 100% | 61.67% | 300 | 300 | 185 |  | 8 | 3 | 2 | 3
PG-T-CON-EX-GN-M-10 | Excavation | 2 | 2026-05-12 | 2026-05-13 | 2026-05-12 | 2026-05-13 | 3096 | 3096 | 3096 | 100% | 100% | 92 | 92 | 92 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-GN-M-20 | Bedding preparation & level control(Completed) | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 1548 | 1548 | 1548 | 100% | 100% | 24 | 24 | 24 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-GN-M-20_R | Bedding preparation & level control(Remaining) | 5 | 2026-06-25 | 2026-06-30 | 2026-07-12 | 2026-08-27 | 1901-05-30 | 1901-05-30 | 516 | 100% | 100% | 8 | 8 | 8 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-GN-M-30 | Manhole Installation | 5 | 2026-07-01 | 2026-07-06 | 2026-08-20 |  | 5160 | 1911-04-20 | 5160 | 100% | 80% | 48 | 48 | 38 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-M-40 | 150 mm uPVC pipe laying & jointing | 4 | 2026-07-07 | 2026-07-11 | 2026-09-20 |  | 10740 | 1920-07-31 | 10740 | 100% | 70% | 32 | 32 | 22 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-M-50 | Concrete Encasement | 3 | 2026-07-12 | 2026-07-14 |  |  | 2064 | 0 | 2064 | 100% | 0% | 24 | 24 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-GN-M-60 | Backfilling & Compaction | 3 | 2026-07-15 | 2026-07-18 |  |  | 2064 | 0 | 2064 | 100% | 0% | 48 | 48 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-GN-M-70 | Surface Reinstatement & Civil Works | 4 | 2026-08-01 | 2026-08-04 |  |  | 2064 | 0 | 2064 | 100% | 0% | 24 | 24 | 0 | Yes | 1 | 0 | 0 | 1
IRRIGATION SYSTEM WORKS |  | 51 | 2026-06-02 | 2026-07-30 | 2026-06-02 |  | 202617.6 | 184224.97 | 202617.6 | 100% | 90.92% | 144 | 144 | 132 |  | 4 | 1 | 3 | 0
PG-T-CON-EX-GN-M-80 | Installation of HDPE Irrigation Pipe Network with Gate Valve and Box(Completed) | 20 | 2026-06-02 | 2026-06-24 | 2026-06-02 | 2026-06-24 | 18691.26 | 18691.26 | 18691.26 | 100% | 100% | 28 | 28 | 28 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-GN-M-80_R | Installation of HDPE Irrigation Pipe Network with Gate Valve and Box(Remaining) | 4 | 2026-07-14 | 2026-07-18 | 2026-07-12 |  | 34712.34 | 31241.11 | 34712.34 | 100% | 90% | 52 | 52 | 47 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-M-90 | Installation of Irrigation Control System | 6 | 2026-07-19 | 2026-07-25 | 2026-08-20 |  | 90915 | 2124-01-08 12:00 | 90915 | 100% | 90% | 32 | 32 | 29 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-M-100 | Installation of Bubblers and Sprinklers | 5 | 2026-07-26 | 2026-07-30 | 2026-08-20 |  | 58299 | 52469.1 | 58299 | 100% | 90% | 32 | 32 | 29 | Yes | 1 | 0 | 1 | 0
FIRE PROTECTION SYSTEM |  | 5 | 2026-08-05 | 2026-08-10 |  |  | 317.94 | 0 | 317.94 | 100% | 0% | 32 | 32 | 0 |  | 1 | 0 | 0 | 1
PG-T-CON-EX-GN-M-110 | Fire Extinguisher Installation | 5 | 2026-08-05 | 2026-08-10 |  |  | 317.94 | 0 | 317.94 | 100% | 0% | 32 | 32 | 0 | Yes | 1 | 0 | 0 | 1
ELECTRICAL WORK |  | 130 | 2026-06-08 | 2026-11-07 | 2026-06-08 |  | 313356.84 | 252549.49 | 345859.68 | 90.6% | 73.02% | 784 | 595 | 418 |  | 20 | 2 | 13 | 5
POWER, LIGHTING & GROUNDING |  | 95 | 2026-06-08 | 2026-09-27 | 2026-06-08 |  | 288789.48 | 230976.49 | 288789.48 | 100% | 79.98% | 376 | 376 | 282 |  | 9 | 2 | 6 | 1
PG-T-CON-EX-GN-E-10 | Excavation | 3 | 2026-06-08 | 2026-06-10 | 2026-06-08 | 2026-06-10 | 69621.12 | 69621.12 | 69621.12 | 100% | 100% | 92 | 92 | 92 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-GN-E-20 | Foundation Work for Site Lighting Poles(Completed) | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 37131.26 | 37131.26 | 37131.26 | 100% | 100% | 27 | 27 | 27 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-GN-E-20_R | Foundation Work for Site Lighting Poles(Remaining) | 21 | 2026-06-25 | 2026-07-19 | 2026-08-20 |  | 55696.9 | 2037-03-28 05:02 | 55696.9 | 100% | 90% | 41 | 41 | 37 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-E-30 | Lightning Protection System (LPS) | 8 | 2026-08-11 | 2026-08-19 | 2026-08-20 |  | 1922-08-17 | 1920-05-12 12:00 | 8265 | 100% | 90% | 32 | 32 | 29 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-E-40 | KWH Meter and MDB Installation | 5 | 2026-08-25 | 2026-08-30 | 2026-09-17 |  | 1912-07-21 16:48 | 1908-10-14 16:34 | 4586.7 | 100% | 70% | 32 | 32 | 22 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-E-50 | Power Panels and Distribution Boards | 7 | 2026-08-31 | 2026-09-07 | 2026-09-17 |  | 1947-08-18 21:36 | 1933-05-04 12:43 | 17397.9 | 100% | 70% | 40 | 40 | 28 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-E-60 | Site Lighting Poles Installation | 6 | 2026-09-08 | 2026-09-14 | 2026-09-17 |  | 2090-08-11 02:53 | 2033-06-04 18:43 | 69621.12 | 100% | 70% | 40 | 40 | 28 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-E-70 | Wiring Works | 4 | 2026-09-15 | 2026-09-19 | 2026-10-04 |  | 1911-07-25 | 1906-12-08 09:36 | 4224 | 100% | 60% | 32 | 32 | 19 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-E-80 | Lighting Fixtures with outlets Installation | 6 | 2026-09-20 | 2026-09-27 |  |  | 22245.48 | 0 | 22245.48 | 100% | 0% | 40 | 40 | 0 | Yes | 1 | 0 | 0 | 1
ELV SYSTEMS (TELECOM, DATA, AV & CCTV) |  | 25 | 2026-09-28 | 2026-10-26 | 2026-09-22 |  | 1957-04-20 18:14 | 1959-01-23 | 43146 | 48.51% | 50% | 272 | 172 | 136 |  | 7 | 0 | 7 | 0
PG-T-CON-EX-GN-E-90 | ELV Containment & Cabling Works | 3 | 2026-09-28 | 2026-09-30 | 2026-09-22 |  | 1901-09-10 19:12 | 1900-11-04 21:36 | 619.8 | 100% | 50% | 40 | 40 | 20 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-E-100 | Fiber Optic Pull Box Installation | 3 | 2026-10-01 | 2026-10-04 | 2026-09-22 |  | 1901-09-10 19:12 | 1900-11-04 21:36 | 619.8 | 100% | 50% | 32 | 32 | 16 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-E-110 | Telephone and Data Outlet Installation | 4 | 2026-10-05 | 2026-10-08 | 2026-09-22 |  | 1910-03-06 19:12 | 1905-02-01 09:36 | 3718.8 | 100% | 50% | 40 | 40 | 20 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-E-120 | Telecom Equipment and AV HDMI Installation | 4 | 2026-10-10 | 2026-10-13 | 2026-09-22 |  | 1941-09-30 02:53 | 1920-11-14 13:26 | 15249.12 | 100% | 50% | 40 | 40 | 20 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-E-130 | CCTV Rack / Cabinet Installation | 4 | 2026-10-14 | 2026-10-18 | 2026-09-22 |  | 1901-12-23 05:46 | 1901-12-23 05:46 | 1446.48 | 50% | 50% | 40 | 20 | 20 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-E-140 | NVR and CCTV Monitor Installation | 4 | 2026-10-19 | 2026-10-22 | 2026-09-22 |  | 0 | 1909-01-18 | 6612 | 0% | 50% | 40 | 0 | 20 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-E-150 | IP Camera Installation | 3 | 2026-10-24 | 2026-10-26 | 2026-09-22 |  | 0 | 1920-05-14 | 14880 | 0% | 50% | 40 | 0 | 20 | Yes | 1 | 0 | 1 | 0
FIRE ALARM SYSTEM |  | 32 | 2026-10-01 | 2026-11-07 |  |  | 1909-12-14 14:24 | 0 | 13924.2 | 26.12% | 0% | 136 | 47 | 0 |  | 4 | 0 | 0 | 4
PG-T-CON-EX-GN-E-160 | Fire Alarm Containment & Cabling | 8 | 2026-10-01 | 2026-10-10 |  |  | 1905-06-05 14:24 | 0 | 1983.6 | 100% | 0% | 32 | 32 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-GN-E-170 | Fire Alarm Control Panel (FACP) Installation | 8 | 2026-10-11 | 2026-10-19 |  |  | 1653 | 0 | 2644.8 | 62.5% | 0% | 24 | 15 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-GN-E-180 | Initiating Devices (Detectors & Manual Pull Station) | 8 | 2026-10-20 | 2026-10-28 |  |  | 0 | 0 | 8097.6 | 0% | 0% | 40 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-GN-E-190 | Notification Appliances (Strobe with Sounder) | 8 | 2026-10-29 | 2026-11-07 |  |  | 0 | 0 | 1198.2 | 0% | 0% | 40 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PARKING WORK |  | 126 | 2026-06-17 | 2026-11-11 | 2026-06-17 |  | 5788.8 | 24441.6 | 40207.8 | 14.4% | 60.79% | 164 | 22 | 77 |  | 4 | 2 | 1 | 1
PG-T-CON-EX-GN-PR-20 | Interlock tiles(Completed) | 7 | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 5788.8 | 5788.8 | 5788.8 | 100% | 100% | 22 | 22 | 22 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-GN-PR-10 | Installlation of Parking Accessories | 7 | 2026-10-27 | 2026-11-03 | 2026-08-20 |  | 0 | 11577.6 | 12864 | 0% | 90% | 32 | 0 | 29 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-PR-20_R | Interlock tiles(Remaining) | 7 | 2026-10-27 | 2026-11-03 | 2026-07-12 | 2026-08-27 | 0 | 7075.2 | 7075.2 | 0% | 100% | 26 | 0 | 26 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-GN-PR-30 | Marking & Signages | 7 | 2026-11-04 | 2026-11-11 |  |  | 0 | 0 | 14479.8 | 0% | 0% | 84 | 0 | 0 | Yes | 1 | 0 | 0 | 1
SERVICE CONNECTION |  | 160 | 2026-06-10 | 2026-12-14 | 2026-06-10 |  | 1901-10-30 14:24 | 4240.8 | 7440 | 9% | 57% | 236 | 28 | 135 |  | 5 | 2 | 1 | 2
PG-T-CON-EX-GN-SC-10 | Excavation & Trench Preparation(Completed) | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 1901-10-30 14:24 | 669.6 | 669.6 | 100% | 100% | 28 | 28 | 28 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-GN-SC-10_R | Excavation & Trench Preparation(Remaining) | 7 | 2026-11-04 | 2026-11-11 | 2026-07-12 | 2026-07-23 | 0 | 1562.4 | 1562.4 | 0% | 100% | 64 | 0 | 64 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-GN-SC-20 | HDPE Pipe Laying & Valve Installation | 10 | 2026-11-12 | 2026-11-23 | 2026-08-14 |  | 0 | 2008.8 | 2232 | 0% | 90% | 48 | 0 | 43 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-SC-30 | Connection to City Network | 10 | 2026-11-24 | 2026-12-05 |  |  | 0 | 0 | 1488 | 0% | 0% | 48 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-GN-SC-40 | Backfilling | 8 | 2026-12-06 | 2026-12-14 |  |  | 0 | 0 | 1488 | 0% | 0% | 48 | 0 | 0 | Yes | 1 | 0 | 0 | 1
LANDSCAPING WORKS |  | 150 | 2026-05-31 | 2026-11-22 | 2026-05-30 |  | 531387.9 | 728820.09 | 755169 | 70.37% | 96.51% | 392 | 211 | 362 |  | 14 | 8 | 6 | 0
HARDSCAPE WORK |  | 150 | 2026-05-31 | 2026-11-22 | 2026-05-30 |  | 483966.9 | 630064.29 | 648147 | 74.67% | 97.21% | 224 | 135 | 207 |  | 11 | 7 | 4 | 0
PG-T-CON-EX-LS-HS-10 | Curbstone Installation(Completed) | 22 | 2026-05-31 | 2026-06-24 | 2026-05-30 | 2026-06-24 | 124077.6 | 124077.6 | 124077.6 | 100% | 100% | 19 | 19 | 19 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-LS-HS-20 | Interlock Tiles Grey Scale with Black Marble Chips(Completed) | 22 | 2026-05-31 | 2026-06-24 | 2026-05-30 | 2026-06-24 | 40656 | 40656 | 40656 | 100% | 100% | 19 | 19 | 19 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-LS-HS-40 | Bike Path and Walking Path Construction(Completed) | 22 | 2026-05-31 | 2026-06-24 | 2026-05-30 | 2026-06-24 | 99297 | 99297 | 99297 | 100% | 100% | 26 | 26 | 26 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-LS-HS-50 | Install Recycled Precast Concrete Seats(Completed) | 22 | 2026-05-31 | 2026-06-24 | 2026-05-30 | 2026-06-24 | 6681.9 | 6681.9 | 6681.9 | 100% | 100% | 3 | 3 | 3 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-LS-HS-30 | Stamped Concrete Floor(Completed) | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 43470 | 43470 | 43470 | 100% | 100% | 16 | 16 | 16 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-LS-HS-10_R | Curbstone Installation(Remaining) | 8 | 2026-09-17 | 2026-09-27 | 2026-07-12 | 2026-08-27 | 82718.4 | 82718.4 | 82718.4 | 100% | 100% | 13 | 13 | 13 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-LS-HS-20_R | Interlock Tiles Grey Scale with Black Marble Chips(Remaining) | 10 | 2026-09-28 | 2026-10-08 | 2026-08-27 |  | 2066-12-18 | 54885.6 | 60984 | 100% | 90% | 29 | 29 | 26 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-LS-HS-30_R | Stamped Concrete Floor(Remaining) | 10 | 2026-10-10 | 2026-10-20 | 2026-07-30 |  | 1971-05-29 | 39123 | 43470 | 60% | 90% | 16 | 10 | 14 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-LS-HS-40_R | Bike Path and Walking Path Construction(Remaining) | 8 | 2026-10-21 | 2026-10-29 | 2026-07-23 | 2026-08-27 | 0 | 81243 | 81243 | 0% | 100% | 22 | 0 | 22 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-LS-HS-50_R | Install Recycled Precast Concrete Seats(Remaining) | 10 | 2026-10-31 | 2026-11-10 | 2026-07-30 |  | 0 | 2048-03-06 09:22 | 60137.1 | 0% | 90% | 29 | 0 | 26 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-LS-HS-60 | Install Recycled Precast Concrete Trash Bins | 10 | 2026-11-11 | 2026-11-22 | 2026-09-23 |  | 0 | 3788.4 | 5412 | 0% | 70% | 32 | 0 | 22 | No | 1 | 0 | 1 | 0
SOFTSCAPE WORK |  | 141 | 2026-06-10 | 2026-11-22 | 2026-06-10 |  | 47421 | 98755.8 | 107022 | 44.31% | 92.28% | 168 | 76 | 155 |  | 3 | 1 | 2 | 0
PG-T-CON-EX-LS-SS-20 | Lawn Area Preparation & Planting / Turfing(Completed) | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 24360 | 24360 | 24360 | 100% | 100% | 34 | 34 | 34 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-LS-SS-10 | Planting Trees | 12 | 2026-10-10 | 2026-10-22 | 2026-09-22 |  | 23061 | 41509.8 | 46122 | 50% | 90% | 84 | 42 | 76 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-LS-SS-20_R | Lawn Area Preparation & Planting / Turfing(Remaining) | 6 | 2026-11-16 | 2026-11-22 | 2026-07-12 |  | 0 | 32886 | 36540 | 0% | 90% | 50 | 0 | 45 | No | 1 | 0 | 1 | 0
TANK WORKS |  | 113 | 2026-05-13 | 2026-09-27 | 2026-05-13 |  | 48290.4 | 34153.02 | 48290.4 | 100% | 70.72% | 628 | 628 | 583 |  | 14 | 12 | 1 | 1
SEPTIC TANK |  | 94 | 2026-05-13 | 2026-09-03 | 2026-05-13 |  | 7475.22 | 7223.04 | 7475.22 | 100% | 96.63% | 364 | 364 | 340 |  | 8 | 7 | 0 | 1
PG-T-CON-EX-TW-ST-10 | Excavation | 21 | 2026-05-13 | 2026-06-10 | 2026-05-13 | 2026-06-10 | 1900-09-08 04:19 | 252.18 | 1900-09-08 04:19 | 100% | 100% | 92 | 92 | 92 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-TW-ST-20 | PCC / Lean Concrete laying | 27 | 2026-05-20 | 2026-06-24 | 2026-05-20 | 2026-06-24 | 1900-06-16 02:53 | 168.12 | 168.12 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-TW-ST-30 | RCC Foundation(Completed) | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 1902-06-12 08:24 | 894.35 | 894.35 | 100% | 100% | 39 | 39 | 39 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-TW-ST-30_R | RCC Foundation(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-12 | 2026-08-27 | 1901-01-17 06:58 | 1901-01-17 06:58 | 1901-01-17 06:58 | 100% | 100% | 17 | 17 | 17 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-TW-ST-40 | RCC Wall | 9 | 2026-07-07 | 2026-07-16 | 2026-08-14 | 2026-10-12 | 2757.6 | 1907-07-19 14:24 | 2757.6 | 100% | 100% | 56 | 56 | 56 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-TW-ST-50 | RCC Slab | 13 | 2026-07-18 | 2026-08-01 | 2026-10-13 | 2026-10-15 | 2599.38 | 2599.38 | 2599.38 | 100% | 100% | 56 | 56 | 56 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-TW-ST-60 | Finishing Work | 8 | 2026-08-18 | 2026-08-26 |  |  | 252.18 | 0 | 252.18 | 100% | 0% | 24 | 24 | 0 | No | 1 | 0 | 0 | 1
PG-T-CON-EX-TW-ST-70 | Backfilling | 7 | 2026-08-27 | 2026-09-03 | 2026-08-20 | 2026-08-24 | 168.12 | 168.12 | 168.12 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
WATER STORAGE TANK |  | 113 | 2026-05-13 | 2026-09-27 | 2026-05-13 |  | 40815.18 | 26929.98 | 40815.18 | 100% | 65.98% | 264 | 264 | 243 |  | 6 | 5 | 1 | 0
PG-T-CON-EX-TW-IR-10 | Excavation(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 1902-02-04 13:55 | 766.58 | 766.58 | 100% | 100% | 83 | 83 | 83 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-TW-IR-20 | RCC Foundation(Completed) | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 1654.56 | 1654.56 | 1654.56 | 100% | 100% | 29 | 29 | 29 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-TW-IR-10_R | Excavation(Remaining) | 6 | 2026-08-29 | 2026-09-03 | 2026-07-08 | 2026-07-09 | 1900-03-25 04:19 | 1900-03-25 04:19 | 85.18 | 100% | 100% | 9 | 9 | 9 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-TW-IR-20_R | RCC Foundation(Remaining) | 8 | 2026-09-05 | 2026-09-13 | 2026-07-16 | 2026-08-27 | 2481.84 | 2481.84 | 2481.84 | 100% | 100% | 43 | 43 | 43 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-TW-IR-30 | Backfilling | 6 | 2026-09-14 | 2026-09-20 | 2026-08-14 | 2026-08-25 | 1114.02 | 1114.02 | 1114.02 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-TW-IR-40 | GRP Water Tank Installation | 5 | 2026-09-21 | 2026-09-27 | 2026-10-13 |  | 34713 | 20827.8 | 34713 | 100% | 60% | 52 | 52 | 31 | No | 1 | 0 | 1 | 0
AIR DOME CONSTRUCTION |  | 171 | 2026-05-13 | 2026-12-03 | 2026-05-13 |  | 2880615.31 | 1210693.39 | 4178041.2 | 68.95% | 28.98% | 1116 | 784 | 392 |  | 21 | 7 | 0 | 14
CIVIL WORK |  | 103 | 2026-05-13 | 2026-09-14 | 2026-05-13 |  | 1711669.97 | 1210693.39 | 1711669.97 | 100% | 70.73% | 536 | 536 | 392 |  | 9 | 7 | 0 | 2
PG-T-CON-EX-AD-CL-10 | Excavation For Footing(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 25048.83 | 25048.83 | 25048.83 | 100% | 100% | 10 | 10 | 10 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-AD-CL-10_R | Excavation For Footing(Remaining) | 7 | 2026-07-05 | 2026-07-12 | 2026-07-08 | 2026-07-10 | 225439.46 | 225439.46 | 225439.46 | 100% | 100% | 90 | 90 | 90 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-AD-CL-20 | Anti-Termite Treatment | 1 | 2026-07-13 | 2026-07-13 | 2026-07-10 | 2026-07-10 | 83496.1 | 83496.1 | 83496.1 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-AD-CL-30 | PCC / Blinding Concrete | 3 | 2026-07-25 | 2026-07-27 | 2026-07-22 | 2026-07-23 | 125244.14 | 125244.14 | 125244.14 | 100% | 100% | 64 | 64 | 64 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-AD-CL-40 | RCC Foundation Works | 9 | 2026-07-28 | 2026-08-06 | 2026-07-23 | 2026-08-13 | 250488.29 | 250488.29 | 250488.29 | 100% | 100% | 88 | 88 | 88 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-AD-CL-50 | Backfilling with Compaction | 8 | 2026-08-08 | 2026-08-16 | 2026-08-07 | 2026-08-14 | 250488.29 | 250488.29 | 250488.29 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-AD-CL-60 | Installation of Anchorage System | 8 | 2026-08-17 | 2026-08-25 | 2026-08-27 | 2026-09-23 | 250488.29 | 250488.29 | 250488.29 | 100% | 100% | 60 | 60 | 60 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-AD-CL-70 | Installation of Steel Cable Structural System | 9 | 2026-08-26 | 2026-09-05 |  |  | 250488.29 | 0 | 250488.29 | 100% | 0% | 76 | 76 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-AD-CL-80 | Installation of Membrane System | 8 | 2026-09-06 | 2026-09-14 |  |  | 250488.29 | 0 | 250488.29 | 100% | 0% | 68 | 68 | 0 | Yes | 1 | 0 | 0 | 1
ARCHITECTURAL WORK |  | 25 | 2026-11-05 | 2026-12-03 |  |  | 0 | 0 | 712953.22 | 0% | 0% | 212 | 0 | 0 |  | 4 | 0 | 0 | 4
PG-T-CON-EX-AD-AR-10 | Installation of Thermal Insulation System | 7 | 2026-11-05 | 2026-11-12 |  |  | 0 | 0 | 250488.29 | 0% | 0% | 60 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-AD-AR-40 | Final Fixing of Accessories & Finishes | 7 | 2026-11-14 | 2026-11-21 |  |  | 0 | 0 | 208740.24 | 0% | 0% | 56 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-AD-AR-20 | Installation of Doors & Access Systems | 6 | 2026-11-22 | 2026-11-28 |  |  | 0 | 0 | 250488.29 | 0% | 0% | 56 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-AD-AR-30 | Installation of Logo | 5 | 2026-11-29 | 2026-12-03 |  |  | 0 | 0 | 3236.4 | 0% | 0% | 40 | 0 | 0 | Yes | 1 | 0 | 0 | 1
MECHANICAL WORK |  | 23 | 2026-09-15 | 2026-10-12 |  |  | 667968.77 | 0 | 667968.77 | 100% | 0% | 160 | 160 | 0 |  | 3 | 0 | 0 | 3
PG-T-CON-EX-AD-ME-10 | Installation of Main Air Package Units | 5 | 2026-09-15 | 2026-09-20 |  |  | 250488.29 | 0 | 250488.29 | 100% | 0% | 56 | 56 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-AD-ME-20 | Installation of Backup Air Package Unit | 5 | 2026-09-21 | 2026-09-27 |  |  | 208740.24 | 0 | 208740.24 | 100% | 0% | 56 | 56 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-AD-ME-30 | Installation of Complete HVAC System | 6 | 2026-10-06 | 2026-10-12 |  |  | 208740.24 | 0 | 208740.24 | 100% | 0% | 48 | 48 | 0 | Yes | 1 | 0 | 0 | 1
ELECTRICAL WORK |  | 33 | 2026-09-28 | 2026-11-04 |  |  | 500976.58 | 0 | 1085449.25 | 46.15% | 0% | 208 | 88 | 0 |  | 5 | 0 | 0 | 5
PG-T-CON-EX-AD-EL-10 | Installation of Electrical Boxes & MDBs | 7 | 2026-09-28 | 2026-10-05 |  |  | 208740.24 | 0 | 208740.24 | 100% | 0% | 40 | 40 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-AD-EL-20 | Installation of Lighting System | 7 | 2026-10-06 | 2026-10-13 |  |  | 208740.24 | 0 | 208740.24 | 100% | 0% | 32 | 32 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-AD-EL-30 | Electrical Connections to Main Power Source (Excluding kWh Meter) | 5 | 2026-10-14 | 2026-10-19 |  |  | 83496.1 | 0 | 208740.24 | 40% | 0% | 40 | 16 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-AD-EL-40 | Installation of Backup Generator | 6 | 2026-10-20 | 2026-10-26 |  |  | 0 | 0 | 208740.24 | 0% | 0% | 48 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-AD-EL-50 | Installation of Smart Dome System | 8 | 2026-10-27 | 2026-11-04 |  |  | 0 | 0 | 250488.29 | 0% | 0% | 48 | 0 | 0 | Yes | 1 | 0 | 0 | 1
TOILET BUILDING WORKS |  | 141 | 2026-05-12 | 2026-10-28 | 2026-05-12 |  | 281445.86 | 305140.07 | 324844.38 | 86.64% | 93.93% | 1708 | 1516 | 1622 |  | 40 | 34 | 6 | 0
CIVIL WORK |  | 139 | 2026-05-12 | 2026-10-26 | 2026-05-12 |  | 183855.32 | 221677.98 | 227117.58 | 80.95% | 97.6% | 1100 | 940 | 1071 |  | 24 | 22 | 2 | 0
STRUCTURAL WORK |  | 66 | 2026-05-12 | 2026-08-01 | 2026-05-12 | 2026-08-12 | 37980 | 37980 | 37980 | 100% | 100% | 372 | 372 | 372 |  | 7 | 7 | 0 | 0
PG-T-CON-B-STR-10 | Excavation up to bottom of footing | 2 | 2026-05-12 | 2026-05-13 | 2026-05-12 | 2026-05-13 | 1900.8 | 1900.8 | 1900.8 | 100% | 100% | 92 | 92 | 92 | No | 1 | 1 | 0 | 0
PG-T-CON-B-STR-20 | Anti-termite treatment and Polyethene Sheet | 2 | 2026-05-12 | 2026-05-13 | 2026-05-12 | 2026-05-13 | 3294 | 3294 | 3294 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-T-CON-B-STR-30 | Backfilling with selected fill material (under footing) | 1 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 1900.8 | 1900.8 | 1900.8 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
PG-T-CON-B-STR-40 | Raft Foundation Work | 27 | 2026-05-13 | 2026-06-17 | 2026-05-13 | 2026-06-17 | 2534.4 | 2534.4 | 2534.4 | 100% | 100% | 64 | 64 | 64 | No | 1 | 1 | 0 | 0
PG-T-CON-B-STR-50 | Autoclaved aerated panel (walls) | 9 | 2026-07-07 | 2026-07-16 | 2026-07-07 | 2026-07-09 | 11340 | 11340 | 11340 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-B-STR-60 | Autoclaved aerated panel (ceiling) | 9 | 2026-07-18 | 2026-07-27 | 2026-07-09 | 2026-07-31 | 8505 | 8505 | 8505 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-B-STR-70 | Autoclaved aerated panel (parapet) | 4 | 2026-07-28 | 2026-08-01 | 2026-07-11 | 2026-08-12 | 8505 | 8505 | 8505 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
ARCHITECTURAL WORK |  | 73 | 2026-08-02 | 2026-10-26 | 2026-08-01 |  | 145875.32 | 183697.98 | 189137.58 | 77.13% | 97.12% | 728 | 568 | 699 |  | 17 | 15 | 2 | 0
GENERAL FINISHES |  | 69 | 2026-08-02 | 2026-10-21 | 2026-08-01 | 2026-09-07 | 59142.4 | 84120 | 84120 | 70.31% | 100% | 376 | 312 | 376 |  | 8 | 8 | 0 | 0
PG-T-CON-B-AR-GF-10 | Block Works | 6 | 2026-08-02 | 2026-08-08 | 2026-08-01 | 2026-08-06 | 1906-10-19 | 2484 | 2484 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-GF-20 | Plaster | 7 | 2026-08-18 | 2026-08-25 | 2026-08-06 | 2026-08-07 | 4427.4 | 4427.4 | 4427.4 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-GF-30 | False Ceiling Installation & Finishing | 8 | 2026-08-26 | 2026-09-03 | 2026-08-20 | 2026-09-07 | 1902-05-22 14:24 | 1902-05-22 14:24 | 873.6 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-GF-40 | Wall Paint | 10 | 2026-09-19 | 2026-09-30 | 2026-08-20 | 2026-09-07 | 1908-02-05 | 1908-02-05 | 2958 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-GF-50 | Epoxy Flooring | 7 | 2026-10-01 | 2026-10-08 | 2026-08-20 | 2026-09-07 | 1900-09-29 14:24 | 273.6 | 273.6 | 100% | 100% | 56 | 56 | 56 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-GF-60 | Install Doors & Windows | 4 | 2026-10-10 | 2026-10-13 | 2026-08-27 | 2026-09-07 | 1936-05-03 19:12 | 13273.8 | 13273.8 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-GF-80 | Facade Finishing Work | 9 | 2026-10-10 | 2026-10-19 | 2026-08-20 | 2026-09-07 | 1995-06-02 | 52278 | 52278 | 66.67% | 100% | 48 | 32 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-GF-70 | Lockers and Furniture Installation | 2 | 2026-10-20 | 2026-10-21 | 2026-08-27 | 2026-09-07 | 0 | 7551.6 | 7551.6 | 0% | 100% | 48 | 0 | 48 | No | 1 | 1 | 0 | 0
WET AREA FINISHES |  | 41 | 2026-08-26 | 2026-10-13 | 2026-08-06 |  | 2122-02-07 18:43 | 79515.3 | 81123.78 | 100% | 98.02% | 216 | 216 | 206 |  | 6 | 5 | 1 | 0
PG-T-CON-B-AR-WF-10 | False Ceiling Installation & Finishing | 4 | 2026-08-26 | 2026-08-30 | 2026-08-20 | 2026-09-10 | 1907-12-07 | 2898 | 2898 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-WF-20 | Wall Tiles and Partition Work | 3 | 2026-10-01 | 2026-10-04 | 2026-08-06 | 2026-08-14 | 1958-04-08 04:48 | 21283.2 | 21283.2 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-WF-30 | Waterproofing on Floor | 2 | 2026-10-05 | 2026-10-06 | 2026-08-14 | 2026-09-10 | 1915-11-01 | 5784 | 5784 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-WF-40 | Floor Tiles Works | 3 | 2026-10-07 | 2026-10-10 | 2026-08-14 | 2026-09-10 | 1917-10-06 | 6489 | 6489 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-WF-50 | Toliet accessories Installation Works | 3 | 2026-10-11 | 2026-10-13 | 2026-08-20 | 2026-09-10 | 2007-08-13 23:31 | 39307.98 | 39307.98 | 100% | 100% | 24 | 24 | 24 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-WF-60 | Install Doors | 2 | 2026-10-11 | 2026-10-12 | 2026-09-23 |  | 1914-09-04 14:24 | 3753.12 | 5361.6 | 100% | 70% | 32 | 32 | 22 | No | 1 | 0 | 1 | 0
ROOF FINISHES |  | 17 | 2026-10-07 | 2026-10-26 | 2026-08-14 |  | 1915-05-10 03:22 | 20062.68 | 23893.8 | 23.48% | 83.97% | 136 | 40 | 117 |  | 3 | 2 | 1 | 0
PG-T-CON-B-AR-RF-10 | Waterproofing on Floor | 7 | 2026-10-07 | 2026-10-14 | 2026-08-14 | 2026-09-12 | 4158 | 4158 | 4158 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-RF-20 | Epoxy Flooring and Finishes | 7 | 2026-10-15 | 2026-10-22 | 2026-08-20 | 2026-09-12 | 1451.14 | 10158 | 10158 | 14.29% | 100% | 56 | 8 | 56 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-RF-30 | Steel ladder and Steel roof scupper Installation | 3 | 2026-10-24 | 2026-10-26 | 2026-09-19 |  | 0 | 1915-09-24 16:19 | 9577.8 | 0% | 60% | 48 | 0 | 29 | No | 1 | 0 | 1 | 0
MEP WORK |  | 115 | 2026-06-16 | 2026-10-28 | 2026-06-16 |  | 97590.54 | 83462.09 | 97726.8 | 99.86% | 85.4% | 608 | 576 | 550 |  | 16 | 12 | 4 | 0
MECANICAL WORKS |  | 115 | 2026-06-16 | 2026-10-28 | 2026-06-16 |  | 79343.22 | 65214.77 | 79479.48 | 99.83% | 82.05% | 400 | 368 | 342 |  | 11 | 7 | 4 | 0
FIRE FIGHTING SYSTEM |  | 2 | 2026-10-27 | 2026-10-28 | 2026-09-23 |  | 0 | 54.5 | 136.26 | 0% | 40% | 32 | 0 | 13 |  | 1 | 0 | 1 | 0
PG-T-CON-B-GF-FF-10 | Fire Extinguisher Installation | 2 | 2026-10-27 | 2026-10-28 | 2026-09-23 |  | 0 | 54.5 | 136.26 | 0% | 40% | 32 | 0 | 13 | No | 1 | 0 | 1 | 0
SEWER AND DRAINAGE SYSTEM |  | 70 | 2026-06-16 | 2026-09-05 | 2026-06-16 |  | 11290.02 | 10322.3 | 11290.02 | 100% | 91.43% | 144 | 144 | 130 |  | 5 | 4 | 1 | 0
PG-T-CON-B-GF-DR-10 | Sewer and Drainge System Main Lines Installation(Completed) | 8 | 2026-06-16 | 2026-06-24 | 2026-06-16 | 2026-06-24 | 967.72 | 967.72 | 967.72 | 100% | 100% | 14 | 14 | 14 | No | 1 | 1 | 0 | 0
PG-T-CON-B-GF-DR-20 | Sewer and Drainge System Pipes and fittings Installation(Completed) | 8 | 2026-06-16 | 2026-06-24 | 2026-06-16 | 2026-06-24 | 1451.57 | 1451.57 | 1451.57 | 100% | 100% | 14 | 14 | 14 | No | 1 | 1 | 0 | 0
PG-T-CON-B-GF-DR-10_R | Sewer and Drainge System Main Lines Installation(Remaining) | 2 | 2026-08-12 | 2026-08-13 | 2026-07-23 | 2026-09-10 | 1906-03-07 | 2258 | 2258 | 100% | 100% | 34 | 34 | 34 | No | 1 | 1 | 0 | 0
PG-T-CON-B-GF-DR-20_R | Sewer and Drainge System Pipes and fittings Installation(Remaining) | 2 | 2026-08-15 | 2026-08-16 | 2026-07-23 | 2026-07-31 | 3387.01 | 3387.01 | 3387.01 | 100% | 100% | 34 | 34 | 34 | No | 1 | 1 | 0 | 0
PG-T-CON-B-GF-DR-30 | Sanitaryware Installation (Final Fix) | 2 | 2026-09-03 | 2026-09-05 | 2026-09-23 |  | 1908-10-29 17:17 | 1906-03-07 | 3225.72 | 100% | 70% | 48 | 48 | 34 | No | 1 | 0 | 1 | 0
HVAC SYSTEM |  | 55 | 2026-08-09 | 2026-10-12 | 2026-08-13 |  | 12127.2 | 9821.76 | 12127.2 | 100% | 80.99% | 96 | 96 | 82 |  | 2 | 1 | 1 | 0
PG-T-CON-B-GF-AC-10 | Duct Work and Exhaust Fan Installation | 3 | 2026-08-09 | 2026-08-11 | 2026-08-13 | 2026-08-20 | 1912-02-28 09:36 | 4442.4 | 4442.4 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-B-GF-AC-20 | Split AC, Grills & Diffuser Installation | 2 | 2026-10-11 | 2026-10-12 | 2026-09-20 |  | 7684.8 | 5379.36 | 7684.8 | 100% | 70% | 48 | 48 | 34 | No | 1 | 0 | 1 | 0
WATER SUPPLY SYSTEM |  | 19 | 2026-08-12 | 2026-09-02 | 2026-07-22 |  | 55926 | 45016.2 | 55926 | 100% | 80.49% | 128 | 128 | 118 |  | 3 | 2 | 1 | 0
PG-T-CON-B-GF-WS-10 | Water Supply Main Lines Installation | 2 | 2026-08-12 | 2026-08-13 | 2026-07-22 | 2026-09-10 | 5702.4 | 5702.4 | 5702.4 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-B-GF-WS-20 | Water Supply Pipes Installation (Cold and Hot Water) | 2 | 2026-08-15 | 2026-08-16 | 2026-07-23 | 2026-07-30 | 13857.6 | 13857.6 | 13857.6 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-B-GF-WS-30 | Water Supply Accesories and Booster pump Installation | 3 | 2026-08-31 | 2026-09-02 | 2026-09-23 |  | 1999-07-25 | 25456.2 | 36366 | 100% | 70% | 32 | 32 | 22 | No | 1 | 0 | 1 | 0
ELECTRICAL WORKS |  | 30 | 2026-08-15 | 2026-09-17 | 2026-07-22 | 2026-09-16 | 1949-12-15 07:41 | 18247.32 | 18247.32 | 100% | 100% | 208 | 208 | 208 |  | 5 | 5 | 0 | 0
PG-T-CON-B-GF-EL-10 | Pipes & Conduits Installation | 3 | 2026-08-15 | 2026-08-17 | 2026-07-22 | 2026-07-23 | 1905-06-05 14:24 | 1983.6 | 1983.6 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-B-GF-EL-50 | Electrical Light Fixtures Installation | 2 | 2026-09-06 | 2026-09-07 | 2026-08-20 | 2026-09-16 | 1920-02-01 12:29 | 7337.52 | 7337.52 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
PG-T-CON-B-GF-EL-30 | Fire Alarm Devices Installation | 3 | 2026-09-08 | 2026-09-10 | 2026-08-20 | 2026-09-16 | 1983.6 | 1983.6 | 1983.6 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-T-CON-B-GF-EL-40 | Telecom & CCTV Devices Installation | 3 | 2026-09-12 | 2026-09-14 | 2026-08-20 | 2026-09-16 | 4959 | 4959 | 4959 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
PG-T-CON-B-GF-EL-20 | Electrical & ELV Wiring Works | 3 | 2026-09-15 | 2026-09-17 | 2026-08-20 | 2026-09-16 | 1905-06-05 14:24 | 1983.6 | 1983.6 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PROJECT CLOSOUT |  | 172 | 2026-05-25 | 2026-12-16 | 2026-05-25 |  | 34073.4 | 210119.32 | 1135780.1 | 3% | 18.5% | 384 | 11 | 62 |  | 7 | 1 | 2 | 4
PG-T-PCL-10 | Testing, Commessioning for All Systems(Completed) | 23 | 2026-05-25 | 2026-06-24 | 2026-05-25 | 2026-06-24 | 34073.4 | 34073.4 | 34073.4 | 100% | 100% | 11 | 11 | 11 | No | 1 | 1 | 0 | 0
PG-T-PCL-20 | As-Built Drawings | 15 | 2026-11-22 | 2026-12-08 | 2026-09-23 |  | 0 | 22715.6 | 113578.01 | 0% | 20% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-T-PCL-10_R | Testing, Commessioning for All Systems(Remaining) | 11 | 2026-11-22 | 2026-12-03 | 2026-08-06 |  | 0 | 2319-10-20 07:26 | 306660.63 | 0% | 50% | 101 | 0 | 50 | Yes | 1 | 0 | 1 | 0
PG-T-PCL-30 | Snag list Submission | 2 | 2026-12-05 | 2026-12-06 |  |  | 0 | 0 | 227156.02 | 0% | 0% | 136 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-PCL-40 | Snag list Closeout | 7 | 2026-12-07 | 2026-12-14 |  |  | 0 | 0 | 227156.02 | 0% | 0% | 136 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-PCL-50 | Issuing Approvals | 1 | 2026-12-15 | 2026-12-15 |  |  | 0 | 0 | 113578.01 | 0% | 0% | 0 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-PCL-60 | Handing Over | 1 | 2026-12-16 | 2026-12-16 |  |  | 0 | 0 | 113578.01 | 0% | 0% | 0 | 0 | 0 | Yes | 1 | 0 | 0 | 1

## Previous Week
Activity ID | Activity Name | BL Project Duration | BL Project Start | BL Project Finish | Actual Start | Actual Finish | Planned Value Cost | Earned Value Cost | Budgeted Total Cost | Schedule % Complete | Performance % Complete | Budgeted Labor Units | Planned Value Labor Units | Earned Value Labor Units | Critical | Activity Count | Actual Completed Activities | Actual In-Progress Activities | Actual Not-Started Activities
PLAYGROUNDS INITIATIVE - QASSIM, HAIL & TABUK - 11-Oct-2026 |  | 250 | 2026-02-17 | 2026-12-16 | 2026-02-17 |  | 27323137.93 | 23227345.38 | 35709993 | 76.88% | 65.36% | 33340 | 25456 | 22804 |  | 1929 | 1591 | 205 | 133
MILESTONES |  | 250 | 2026-02-17 | 2026-12-16 | 2026-02-17 |  | 0 | 0 | 0 | 0% | 0% | 10000 | 7700 | 7050 |  | 10 | 4 | 1 | 5
GENERAL MILESTONES |  | 250 | 2026-02-17 | 2026-12-16 | 2026-02-17 |  | 0 | 0 | 0 | 0% | 0% | 10000 | 7700 | 7050 |  | 4 | 2 | 1 | 1
PG-GN-MS-10 | Project Commencement Date | 0 | 2026-02-17 |  | 2026-02-17 |  | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-GN-MS-30 | Project Durations(Completed) | 101 | 2026-02-17 | 4619700% | 2026-02-17 | 46197 | 0 | 0 | 0 | 100% | 100% | 4100 | 4100 | 4100 | No | 1 | 1 | 0 | 0
PG-GN-MS-30_R | Project Durations(Remaining) | 148 | 2026-06-25 | 2026-12-15 | 2026-07-01 |  | 0 | 0 | 0 | 61.02% | 50% | 5900 | 3600 | 2950 | Yes | 1 | 0 | 1 | 0
PG-GN-MS-20 | Project Completion Date | 0 |  | 2026-12-16 |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | Yes | 1 | 0 | 0 | 1
CONTRACUAL MILESTONES |  | 188 | 2026-05-05 | 2026-12-16 | 2026-05-05 |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 6 | 2 | 0 | 4
PG-IN-MS-20 | Completion of Earthworks (Cut and fill) For Site Layout | 0 |  | 2026-05-05 |  | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-IN-MS-10 | Site Preparation, Work Plans, Schedule ,Drawings Submittals | 0 |  | 2026-08-04 |  | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-IN-MS-30 | Completion of Toilet Building | 0 |  | 2026-10-28 |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-IN-MS-50 | Completion of Playground Works | 0 |  | 2026-12-07 |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | No | 1 | 0 | 0 | 1
PG-IN-MS-40 | Completion of Landscape Works | 0 |  | 2026-12-16 |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-IN-MS-60 | Substantial Completion - All Works | 0 |  | 2026-12-16 |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | Yes | 1 | 0 | 0 | 1
QASSIM |  | 250 | 2026-02-17 | 2026-12-16 | 2026-02-17 |  | 13745803.07 | 11669636.63 | 17537540 | 79.15% | 67.2% | 8496 | 6412 | 5660 |  | 667 | 552 | 66 | 49
MOBILIZATION |  | 29 | 2026-02-17 | 2026-03-29 | 2026-02-17 | 2026-03-28 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 9 | 9 | 0 | 0
TEMPORARY CAMP |  | 28 | 2026-02-17 | 2026-03-28 | 2026-02-17 | 2026-03-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-MOB-CAM-10 | Temporary Underground Utilities works | 28 | 2026-02-17 | 2026-03-28 | 2026-02-17 | 2026-03-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-MOB-CAM-20 | Temporary Porta-Cabins | 21 | 2026-02-26 | 2026-03-28 | 2026-02-26 | 2026-03-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-MOB-CAM-30 | Temporary Toilets | 21 | 2026-02-26 | 2026-03-28 | 2026-02-26 | 2026-03-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-MOB-CAM-40 | Temporary Mosque | 13 | 2026-03-08 | 2026-03-28 | 2026-03-08 | 2026-03-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SITE OFFICES |  | 29 | 2026-02-17 | 2026-03-29 | 2026-02-17 | 2026-03-28 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-Q-MOB-SO-10 | Temporary Underground Utilities works | 29 | 2026-02-17 | 2026-03-29 | 2026-02-17 | 2026-03-28 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-MOB-SO-20 | Temporary Porta-Cabins | 22 | 2026-02-26 | 2026-03-29 | 2026-02-26 | 2026-03-28 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-MOB-SO-30 | Temporary Toilets | 22 | 2026-02-26 | 2026-03-29 | 2026-02-26 | 2026-03-28 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-MOB-SO-40 | Temporary Mosque | 16 | 2026-03-05 | 2026-03-29 | 2026-03-05 | 2026-03-28 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-MOB-SO-50 | Car Parking Area | 10 | 2026-03-12 | 2026-03-29 | 2026-03-12 | 2026-03-28 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
GENERAL REQUIEREMENTS |  | 57 | 2026-02-17 | 2026-04-30 | 2026-02-17 | 2026-04-29 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-GEN-20 | HSSE Submission Plan | 57 | 2026-02-17 | 2026-04-30 | 2026-02-17 | 2026-04-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-GEN-30 | Surveying report Submission Plan | 57 | 2026-02-17 | 2026-04-30 | 2026-02-17 | 2026-04-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-GEN-40 | Baseline Submission | 6 | 2026-02-28 | 2026-03-07 | 2026-02-28 | 2026-03-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-GEN-10 | QA/QC Submission Plan | 16 | 2026-03-12 | 2026-04-04 | 2026-03-12 | 2026-04-04 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ENGINEERING |  | 146 | 2026-02-17 | 2026-08-16 | 2026-02-17 |  | 526126.2 | 526126.2 | 526126.2 | 100% | 100% | 0 | 0 | 0 |  | 262 | 258 | 4 | 0
SHOP DRAWINGS SUBMITTALS |  | 136 | 2026-02-17 | 2026-08-04 | 2026-02-17 |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 62 | 58 | 4 | 0
STRUCTURAL DRAWINGS |  | 111 | 2026-02-17 | 2026-07-06 | 2026-02-17 | 2026-07-11 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PROJECT FENCE |  | 19 | 2026-04-29 | 2026-05-21 | 2026-04-29 | 2026-05-20 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ST-SD-SB-10 | Excavation Drawings | 19 | 2026-04-29 | 2026-05-21 | 2026-04-29 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ST-SD-SB-20 | Foundation Drawings | 19 | 2026-04-29 | 2026-05-21 | 2026-04-29 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PADEL PLAYGROUND FENCE |  | 19 | 2026-04-29 | 2026-05-21 | 2026-04-29 | 2026-05-20 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ST-SD-SB-30 | Excavation Drawings | 19 | 2026-04-29 | 2026-05-21 | 2026-04-29 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ST-SD-SB-40 | Foundation Drawings | 19 | 2026-04-29 | 2026-05-21 | 2026-04-29 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 10 | 2026-06-25 | 2026-07-06 | 2026-07-01 | 2026-07-11 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ST-SD-SB-50 | Excavation Drawings | 8 | 2026-06-25 | 2026-07-04 | 2026-07-01 | 2026-07-02 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ST-SD-SB-60 | Foundation Drawings | 10 | 2026-06-25 | 2026-07-06 | 2026-07-07 | 2026-07-11 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
TOILET BUILDING |  | 43 | 2026-02-17 | 2026-04-14 | 2026-02-17 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ST-SD-SB-70 | Excavation Drawings | 43 | 2026-02-17 | 2026-04-14 | 2026-02-17 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ST-SD-SB-80 | Foundation Drawings | 41 | 2026-02-19 | 2026-04-14 | 2026-02-19 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
WATER STORAGE TANK |  | 41 | 2026-02-19 | 2026-04-14 | 2026-02-19 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ST-SD-SB-90 | Excavation Drawings | 41 | 2026-02-19 | 2026-04-14 | 2026-02-19 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ST-SD-SB-100 | Foundation Drawings | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SEPTIC TANK |  | 13 | 2026-04-28 | 2026-05-13 | 2026-04-28 | 2026-05-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ST-SD-SB-110 | Reinforcement Detail Drawings | 13 | 2026-04-28 | 2026-05-13 | 2026-04-28 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ST-SD-SB-120 | Concrete Detail Drawings | 13 | 2026-04-28 | 2026-05-13 | 2026-04-28 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL DRAWINGS |  | 124 | 2026-02-19 | 2026-07-23 | 2026-02-19 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 13 | 13 | 0 | 0
TOILET BUILDING |  | 42 | 2026-02-19 | 2026-04-15 | 2026-02-19 | 2026-04-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 10 | 0 | 0
PG-Q-EN-AR-SD-SB-10 | Ground Floor Plan | 40 | 2026-02-19 | 2026-04-13 | 2026-02-19 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-SB-20 | Roof Floor Plan | 37 | 2026-02-25 | 2026-04-14 | 2026-02-25 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-SB-50 | Floor Finish Layout | 36 | 2026-02-25 | 2026-04-13 | 2026-02-25 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-SB-60 | Reflected Ceiling Layout | 37 | 2026-02-25 | 2026-04-13 | 2026-02-25 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-SB-70 | Enlarged Toilets Layout | 38 | 2026-02-25 | 2026-04-15 | 2026-02-25 | 2026-04-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-SB-30 | Elevations | 34 | 2026-03-01 | 2026-04-14 | 2026-03-01 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-SB-80 | Doors & Windows Schedule | 35 | 2026-03-01 | 2026-04-15 | 2026-03-01 | 2026-04-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-SB-90 | Aluminum Work | 35 | 2026-03-01 | 2026-04-15 | 2026-03-01 | 2026-04-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-SB-100 | Cladding Details | 34 | 2026-03-01 | 2026-04-14 | 2026-03-01 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-SB-40 | Sections | 32 | 2026-03-03 | 2026-04-13 | 2026-03-03 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 15 | 2026-07-07 | 2026-07-23 | 2026-08-14 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-EN-AR-SD-SB-110 | Membrane & Insulation Details | 15 | 2026-07-07 | 2026-07-23 | 2026-08-14 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-SB-120 | Steel Cable System | 15 | 2026-07-07 | 2026-07-23 | 2026-08-14 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-SB-130 | Doors & Access Sytem Drawings | 15 | 2026-07-07 | 2026-07-23 | 2026-08-14 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
LANDSCAPE DRAWINGS |  | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 13 | 13 | 0 | 0
PG-Q-EN-LS-SD-SB-10 | Hardscape Layout Plan | 36 | 2026-02-23 | 2026-04-11 | 2026-02-23 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-SB-20 | Interlock Tile Details | 36 | 2026-02-23 | 2026-04-11 | 2026-02-23 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-SB-30 | Stamped Concrete Pattern & Section | 36 | 2026-02-23 | 2026-04-11 | 2026-02-23 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-SB-40 | Tartan Flooring Layout & Details | 36 | 2026-02-23 | 2026-04-11 | 2026-02-23 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-SB-50 | Bike Path Layout & Details | 36 | 2026-02-23 | 2026-04-11 | 2026-02-23 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-SB-60 | Walking Path layout & Details | 36 | 2026-02-23 | 2026-04-11 | 2026-02-23 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-SB-70 | Tree Planting Plan & Details | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-SB-80 | Traffic Sign Location & Details | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-SB-90 | Football Playground Layout | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-SB-100 | Padel Playground Layout | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-SB-110 | Basketball Playground Layout | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-SB-120 | Playground Details | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-SB-130 | Padel Fence Elevation & Details | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MECHANICAL DRAWINGS |  | 111 | 2026-02-28 | 2026-07-15 | 2026-02-28 |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 9 | 1 | 0
WATER SUPPLY SYSTEM |  | 32 | 2026-02-28 | 2026-04-11 | 2026-02-28 | 2026-04-09 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-EN-ME-SD-SB-20 | Pump Room Layout | 32 | 2026-02-28 | 2026-04-11 | 2026-02-28 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ME-SD-SB-10 | Cold & Hot Water Piping Layout | 28 | 2026-03-04 | 2026-04-11 | 2026-03-04 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ME-SD-SB-30 | Booster Pump Details | 28 | 2026-03-04 | 2026-04-11 | 2026-03-04 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ME-SD-SB-40 | GRP Water Tank Details | 24 | 2026-03-09 | 2026-04-11 | 2026-03-09 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SEWER AND DRAINAGE SYSTEM |  | 28 | 2026-03-04 | 2026-04-11 | 2026-03-04 | 2026-04-09 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-EN-ME-SD-SB-50 | Drainage Layout | 28 | 2026-03-04 | 2026-04-11 | 2026-03-04 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ME-SD-SB-60 | Floor Drains & Cleanouts Details | 24 | 2026-03-09 | 2026-04-11 | 2026-03-09 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ME-SD-SB-70 | Inspection Chamber Details | 21 | 2026-03-12 | 2026-04-11 | 2026-03-12 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION SYSTEM |  | 24 | 2026-03-09 | 2026-04-11 | 2026-03-09 | 2026-04-09 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ME-SD-SB-80 | HDPE Pipe Routing | 24 | 2026-03-09 | 2026-04-11 | 2026-03-09 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ME-SD-SB-90 | Irrigation Network Layout | 21 | 2026-03-12 | 2026-04-11 | 2026-03-12 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 18 | 2026-06-25 | 2026-07-15 | 2026-07-30 |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 0 | 1 | 0
PG-Q-EN-ME-SD-SB-100 | Air Package and HVAC System Drawings | 18 | 2026-06-25 | 2026-07-15 | 2026-07-30 |  | 0 | 0 | 0 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
ELECTRICAL DRAWINGS |  | 70 | 2026-05-11 | 2026-08-04 | 2026-05-11 |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 14 | 11 | 3 | 0
POWER AND LIGHTING SYSTEM |  | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-EN-EL-SD-SB-10 | Main Distribution Board (MDB) Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-SB-20 | Pump Room Power Panel | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-SB-30 | Street Lighting Power Panel | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-SB-40 | Site Lighting Pole Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELV SYSTEM |  | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-EN-EL-SD-SB-50 | Telecom & Data Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-SB-60 | CCTV Camera Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-SB-70 | Access Control Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-SB-80 | AV System Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE ALARM SYSTEM |  | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-EN-EL-SD-SB-90 | Fire Alarm Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-SB-100 | Detector & Manual Call Point Details | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-SB-110 | Control Panel Wiring Diagram | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 17 | 2026-07-16 | 2026-08-04 | 2026-07-30 |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 0 | 3 | 0
PG-Q-EN-EL-SD-SB-120 | Power & Lighting System Drawings | 10 | 2026-07-16 | 2026-07-27 | 2026-07-30 |  | 0 | 0 | 0 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-Q-EN-EL-SD-SB-130 | Generators Details | 15 | 2026-07-16 | 2026-08-02 | 2026-07-30 |  | 0 | 0 | 0 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-Q-EN-EL-SD-SB-140 | Smart Dome System Drawings | 17 | 2026-07-16 | 2026-08-04 | 2026-07-30 |  | 0 | 0 | 0 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
SHOP DRAWINGS APPROVALS |  | 144 | 2026-02-19 | 2026-08-16 | 2026-02-19 | 2026-09-21 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 62 | 62 | 0 | 0
STRUCTURAL DRAWINGS |  | 116 | 2026-02-19 | 2026-07-14 | 2026-02-19 | 2026-07-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PROJECT FENCE |  | 7 | 2026-05-13 | 2026-05-21 | 2026-05-13 | 2026-05-20 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ST-SD-AP-10 | Excavation Drawings | 7 | 2026-05-13 | 2026-05-21 | 2026-05-13 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ST-SD-AP-20 | Foundation Drawings | 7 | 2026-05-13 | 2026-05-21 | 2026-05-13 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PADEL PLAYGROUND FENCE |  | 9 | 2026-05-11 | 2026-05-21 | 2026-05-11 | 2026-05-20 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ST-SD-AP-30 | Excavation Drawings | 9 | 2026-05-11 | 2026-05-21 | 2026-05-11 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ST-SD-AP-40 | Foundation Drawings | 9 | 2026-05-11 | 2026-05-21 | 2026-05-11 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 9 | 2026-07-05 | 2026-07-14 | 2026-07-06 | 2026-07-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ST-SD-AP-50 | Excavation Drawings | 4 | 2026-07-05 | 2026-07-08 | 2026-07-06 | 2026-07-07 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ST-SD-AP-60 | Foundation Drawings | 7 | 2026-07-07 | 2026-07-14 | 2026-07-08 | 2026-07-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
TOILET BUILDING |  | 44 | 2026-02-19 | 2026-04-18 | 2026-02-19 | 2026-04-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ST-SD-AP-70 | Excavation Drawings | 44 | 2026-02-19 | 2026-04-18 | 2026-02-19 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ST-SD-AP-80 | Foundation Drawings | 36 | 2026-03-02 | 2026-04-18 | 2026-03-02 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
WATER STORAGE TANK |  | 42 | 2026-02-23 | 2026-04-18 | 2026-02-23 | 2026-04-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ST-SD-AP-90 | Excavation Drawings | 42 | 2026-02-23 | 2026-04-18 | 2026-02-23 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ST-SD-AP-100 | Foundation Drawings | 34 | 2026-03-04 | 2026-04-18 | 2026-03-04 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SEPTIC TANK |  | 3 | 2026-05-11 | 2026-05-14 | 2026-05-11 | 2026-05-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ST-SD-AP-110 | Reinforcement Detail Drawings | 3 | 2026-05-11 | 2026-05-14 | 2026-05-11 | 2026-05-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ST-SD-AP-120 | Concrete Detail Drawings | 3 | 2026-05-11 | 2026-05-14 | 2026-05-11 | 2026-05-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL DRAWINGS |  | 127 | 2026-02-25 | 2026-08-01 | 2026-02-25 | 2026-09-21 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 13 | 13 | 0 | 0
TOILET BUILDING |  | 40 | 2026-02-25 | 2026-04-18 | 2026-02-25 | 2026-04-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 10 | 0 | 0
PG-Q-EN-AR-SD-AP-10 | Ground Floor Plan | 40 | 2026-02-25 | 2026-04-18 | 2026-02-25 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-AP-20 | Roof Floor Plan | 37 | 2026-03-01 | 2026-04-18 | 2026-03-01 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-AP-50 | Floor Finish Layout | 35 | 2026-03-03 | 2026-04-18 | 2026-03-03 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-AP-60 | Reflected Ceiling Layout | 35 | 2026-03-03 | 2026-04-18 | 2026-03-03 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-AP-70 | Enlarged Toilets Layout | 35 | 2026-03-03 | 2026-04-18 | 2026-03-03 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-AP-30 | Elevations | 34 | 2026-03-04 | 2026-04-18 | 2026-03-04 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-AP-80 | Doors & Windows Schedule | 34 | 2026-03-04 | 2026-04-18 | 2026-03-04 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-AP-90 | Aluminum Work | 33 | 2026-03-05 | 2026-04-18 | 2026-03-05 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-AP-100 | Cladding Details | 33 | 2026-03-05 | 2026-04-18 | 2026-03-05 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-AP-40 | Sections | 31 | 2026-03-08 | 2026-04-18 | 2026-03-08 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 7 | 2026-07-25 | 2026-08-01 | 2026-08-20 | 2026-09-21 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-EN-AR-SD-AP-110 | Membrane & Insulation Details | 7 | 2026-07-25 | 2026-08-01 | 2026-08-20 | 2026-09-21 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-AP-120 | Steel Cable System | 7 | 2026-07-25 | 2026-08-01 | 2026-08-20 | 2026-09-21 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-AR-SD-AP-130 | Doors & Access Sytem Drawings | 7 | 2026-07-25 | 2026-08-01 | 2026-08-20 | 2026-09-21 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
LANDSCAPE DRAWINGS |  | 39 | 2026-02-26 | 2026-04-18 | 2026-02-26 | 2026-04-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 13 | 13 | 0 | 0
PG-Q-EN-LS-SD-AP-50 | Bike Path Layout & Details | 39 | 2026-02-26 | 2026-04-18 | 2026-02-26 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-AP-60 | Walking Path layout & Details | 39 | 2026-02-26 | 2026-04-18 | 2026-02-26 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-AP-80 | Traffic Sign Location & Details | 39 | 2026-02-26 | 2026-04-18 | 2026-02-26 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-AP-130 | Padel Fence Elevation & Details | 39 | 2026-02-26 | 2026-04-18 | 2026-02-26 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-AP-10 | Hardscape Layout Plan | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-AP-40 | Tartan Flooring Layout & Details | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-AP-70 | Tree Planting Plan & Details | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-AP-90 | Football Playground Layout | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-AP-100 | Padel Playground Layout | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-AP-110 | Basketball Playground Layout | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-AP-120 | Playground Details | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-AP-20 | Interlock Tile Details | 28 | 2026-03-11 | 2026-04-18 | 2026-03-11 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-LS-SD-AP-30 | Stamped Concrete Pattern & Section | 18 | 2026-03-28 | 2026-04-18 | 2026-03-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MECHANICAL DRAWINGS |  | 113 | 2026-03-09 | 2026-07-27 | 2026-03-09 | 2026-09-21 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 10 | 0 | 0
WATER SUPPLY SYSTEM |  | 27 | 2026-03-09 | 2026-04-14 | 2026-03-09 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-EN-ME-SD-AP-10 | Cold & Hot Water Piping Layout | 27 | 2026-03-09 | 2026-04-14 | 2026-03-09 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ME-SD-AP-30 | Booster Pump Details | 26 | 2026-03-10 | 2026-04-14 | 2026-03-10 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ME-SD-AP-40 | GRP Water Tank Details | 22 | 2026-03-14 | 2026-04-13 | 2026-03-14 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ME-SD-AP-20 | Pump Room Layout | 21 | 2026-03-16 | 2026-04-14 | 2026-03-16 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SEWER AND DRAINAGE SYSTEM |  | 27 | 2026-03-09 | 2026-04-14 | 2026-03-09 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-EN-ME-SD-AP-50 | Drainage Layout | 27 | 2026-03-09 | 2026-04-14 | 2026-03-09 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ME-SD-AP-60 | Floor Drains & Cleanouts Details | 21 | 2026-03-16 | 2026-04-14 | 2026-03-16 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ME-SD-AP-70 | Inspection Chamber Details | 21 | 2026-03-16 | 2026-04-14 | 2026-03-16 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION SYSTEM |  | 24 | 2026-03-12 | 2026-04-14 | 2026-03-12 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-EN-ME-SD-AP-80 | HDPE Pipe Routing | 24 | 2026-03-12 | 2026-04-14 | 2026-03-12 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-ME-SD-AP-90 | Irrigation Network Layout | 20 | 2026-03-17 | 2026-04-14 | 2026-03-17 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 10 | 2026-07-16 | 2026-07-27 | 2026-08-20 | 2026-09-21 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-Q-EN-ME-SD-AP-100 | Air Package and HVAC System Drawings | 10 | 2026-07-16 | 2026-07-27 | 2026-08-20 | 2026-09-21 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL DRAWINGS |  | 72 | 2026-05-20 | 2026-08-16 | 2026-05-20 | 2026-09-21 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 14 | 14 | 0 | 0
POWER AND LIGHTING SYSTEM |  | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-EN-EL-SD-AP-10 | Main Distribution Board (MDB) Layout | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-AP-20 | Pump Room Power Panel | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-AP-30 | Street Lighting Power Panel | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-AP-40 | Site Lighting Pole Layout | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELV SYSTEM |  | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-EN-EL-SD-AP-50 | Telecom & Data Layout | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-AP-60 | CCTV Camera Layout | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-AP-70 | Access Control Layout | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-AP-80 | AV System Layout | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE ALARM SYSTEM |  | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-EN-EL-SD-AP-90 | Fire Alarm Layout | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-AP-100 | Detector & Manual Call Point Details | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-AP-110 | Control Panel Wiring Diagram | 20 | 2026-05-20 | 2026-06-17 | 2026-05-20 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 17 | 2026-07-28 | 2026-08-16 | 2026-08-20 | 2026-09-21 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-EN-EL-SD-AP-120 | Power & Lighting System Drawings | 17 | 2026-07-28 | 2026-08-16 | 2026-08-20 | 2026-09-21 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-AP-130 | Generators Details | 8 | 2026-08-03 | 2026-08-11 | 2026-08-20 | 2026-09-21 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-EN-EL-SD-AP-140 | Smart Dome System Drawings | 6 | 2026-08-05 | 2026-08-11 | 2026-08-20 | 2026-09-21 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MATERIAL SUBMITTALS |  | 120 | 2026-02-17 | 2026-07-16 | 2026-02-17 | 2026-08-20 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 63 | 63 | 0 | 0
LONG LEAD ITEMS |  | 120 | 2026-02-17 | 2026-07-16 | 2026-02-17 | 2026-08-20 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 24 | 24 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 56 | 2026-02-25 | 2026-05-06 | 2026-02-25 | 2026-05-05 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-PR-LL-LS-MS-20 | Benches, Seats (Rectangular & Circular) | 56 | 2026-02-25 | 2026-05-06 | 2026-02-25 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-MS-30 | Fence, gates and accessories | 49 | 2026-03-05 | 2026-05-06 | 2026-03-05 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-MS-10 | Bike and Walk Path Materials | 49 | 2026-03-05 | 2026-05-06 | 2026-03-05 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 120 | 2026-02-17 | 2026-07-16 | 2026-02-17 | 2026-08-20 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 6 | 6 | 0 | 0
PG-Q-PR-LL-SP-MS-50 | Air Dome Materials(Completed) | 101 | 2026-02-17 | 2026-06-25 | 2026-02-17 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MS-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc) | 48 | 2026-03-07 | 2026-05-06 | 2026-03-07 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MS-20 | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc) | 48 | 2026-03-07 | 2026-05-06 | 2026-03-07 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MS-30 | Padel Playgound Materials (Flooring, fence, tempered glass, etc) | 48 | 2026-03-07 | 2026-05-06 | 2026-03-07 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MS-40 | Tartan Floor | 48 | 2026-03-07 | 2026-05-06 | 2026-03-07 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MS-50_R | Air Dome Materials(Remaining) | 19 | 2026-06-25 | 2026-07-16 | 2026-06-30 | 2026-08-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 43 | 2026-03-04 | 2026-04-28 | 2026-03-04 | 2026-04-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-Q-PR-LL-CO-MS-10 | Autoclaved Aerated Panel | 43 | 2026-03-04 | 2026-04-28 | 2026-03-04 | 2026-04-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 47 | 2026-03-09 | 2026-05-07 | 2026-03-09 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-PR-LL-MT-MS-10 | Metal Doors | 47 | 2026-03-09 | 2026-05-07 | 2026-03-09 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-MT-MS-20 | Curtain Wall | 47 | 2026-03-09 | 2026-05-07 | 2026-03-09 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 46 | 2026-03-10 | 2026-05-07 | 2026-03-10 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-PR-LL-PB-MS-10 | Booster Pump | 46 | 2026-03-10 | 2026-05-07 | 2026-03-10 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-PB-MS-20 | GRP Sectional Panel Water Tanks (4x3x3m) | 42 | 2026-03-15 | 2026-05-07 | 2026-03-15 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 50 | 2026-03-05 | 2026-05-07 | 2026-03-05 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-PR-LL-IR-MS-10 | HDPE Pipes | 50 | 2026-03-05 | 2026-05-07 | 2026-03-05 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-IR-MS-20 | Irrigation Control System | 50 | 2026-03-05 | 2026-05-07 | 2026-03-05 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 26 | 2026-05-12 | 2026-06-16 | 2026-05-12 | 2026-06-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 8 | 8 | 0 | 0
PG-Q-PR-LL-EL-MS-10 | Main Distribution Board | 26 | 2026-05-12 | 2026-06-16 | 2026-05-12 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MS-20 | Power Panels (Pump, Street Light) | 26 | 2026-05-12 | 2026-06-16 | 2026-05-12 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MS-30 | Site Lighting Poles | 26 | 2026-05-12 | 2026-06-16 | 2026-05-12 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MS-40 | Lighting Fixtures | 26 | 2026-05-12 | 2026-06-16 | 2026-05-12 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MS-50 | Grounding System Materials (Earth pit rod, LPS, etc) | 26 | 2026-05-12 | 2026-06-16 | 2026-05-12 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MS-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc) | 26 | 2026-05-12 | 2026-06-16 | 2026-05-12 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MS-70 | Security and Access Control System Materials | 26 | 2026-05-12 | 2026-06-16 | 2026-05-12 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MS-80 | Fire Alarm System Materials | 26 | 2026-05-12 | 2026-06-16 | 2026-05-12 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SHORT LEAD ITEMS |  | 28 | 2026-02-17 | 2026-03-28 | 2026-02-17 | 2026-03-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 39 | 39 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 23 | 2026-02-17 | 2026-03-17 | 2026-02-17 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 8 | 8 | 0 | 0
PG-Q-PR-SL-LS-MS-10 | Backfilling Materials | 23 | 2026-02-17 | 2026-03-17 | 2026-02-17 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MS-30 | Compacted Natural Ground Soil | 20 | 2026-02-21 | 2026-03-17 | 2026-02-21 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MS-20 | Interlock tiles | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MS-40 | Curb Stone | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MS-50 | Thermoplastic pavement road marking | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MS-60 | Traffic Signages | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MS-70 | Trees | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MS-80 | Lawn | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 28 | 2026-02-17 | 2026-03-28 | 2026-02-17 | 2026-03-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-Q-PR-SL-CO-MS-10 | Steel Rebar | 17 | 2026-02-17 | 2026-03-10 | 2026-02-17 | 2026-03-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-MS-20 | Concrete | 13 | 2026-02-23 | 2026-03-10 | 2026-02-23 | 2026-03-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-MS-40 | CMU Block | 19 | 2026-03-01 | 2026-03-28 | 2026-03-01 | 2026-03-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-MS-50 | Concrete Repair & Protection Materials | 19 | 2026-03-01 | 2026-03-28 | 2026-03-01 | 2026-03-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-MS-30 | Screed | 9 | 2026-03-12 | 2026-03-28 | 2026-03-12 | 2026-03-26 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL & FINISHES WORK |  | 18 | 2026-02-21 | 2026-03-15 | 2026-02-21 | 2026-03-14 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PG-Q-PR-SL-AR-MS-40 | Cement Plaster | 18 | 2026-02-21 | 2026-03-15 | 2026-02-21 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MS-50 | Acrylic Paint | 15 | 2026-02-25 | 2026-03-15 | 2026-02-25 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MS-80 | Phenolic Partition | 10 | 2026-03-03 | 2026-03-15 | 2026-03-03 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MS-90 | Glass Partition | 10 | 2026-03-03 | 2026-03-15 | 2026-03-03 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MS-10 | Ceramic tiles | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MS-20 | Anti-slip Granite tiles | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MS-30 | Epoxy Paint | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MS-60 | Stone Cladding | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MS-70 | Aluminum Plates | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MS-100 | Gypsum Boards | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MS-110 | Specialities Materials (Toilet accessories, lockers, logo, etc) | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MS-120 | Waterproofing System Materials | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 11 | 2026-03-04 | 2026-03-17 | 2026-03-04 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-PR-SL-MT-MS-20 | Galvanized Steel Roof Scupper | 11 | 2026-03-04 | 2026-03-17 | 2026-03-04 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-MT-MS-30 | Galvanized Steel Cover with frame | 11 | 2026-03-04 | 2026-03-17 | 2026-03-04 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-MT-MS-10 | Galvanized Steel Ladder | 8 | 2026-03-08 | 2026-03-17 | 2026-03-08 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
HVAC WORK |  | 19 | 2026-02-23 | 2026-03-17 | 2026-02-23 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-PR-SL-AC-MS-10 | Split Air Conditioning Unit | 19 | 2026-02-23 | 2026-03-17 | 2026-02-23 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-MS-20 | Air Duct | 15 | 2026-02-28 | 2026-03-17 | 2026-02-28 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-MS-30 | Diffusers and Grills | 11 | 2026-03-04 | 2026-03-17 | 2026-03-04 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-MS-40 | Exhaust fans | 11 | 2026-03-04 | 2026-03-17 | 2026-03-04 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-PR-SL-PB-MS-10 | PPR Pipes & Valves | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-PB-MS-20 | UPCV Pipes | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-PB-MS-30 | Sanitary Drainage Fixtures | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 17 | 2026-02-25 | 2026-03-17 | 2026-02-25 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-PR-SL-IR-MS-10 | Gate Valve including valve box | 17 | 2026-02-25 | 2026-03-17 | 2026-02-25 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-IR-MS-20 | Bulbblers and Spreyers | 12 | 2026-03-03 | 2026-03-17 | 2026-03-03 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-Q-PR-SL-EL-MS-10 | Wiring Devices Materials | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE FIGHTING WORK |  | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-Q-PR-SL-FF-MS-10 | Fire Extinguishers | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MATERIAL APPROVALS |  | 118 | 2026-02-21 | 2026-07-18 | 2026-02-21 | 2026-10-01 | 526126.2 | 526126.2 | 526126.2 | 100% | 100% | 0 | 0 | 0 |  | 75 | 75 | 0 | 0
LONG LEAD ITEMS |  | 111 | 2026-03-02 | 2026-07-18 | 2026-03-02 | 2026-10-01 | 358885.26 | 358885.26 | 358885.26 | 100% | 100% | 0 | 0 | 0 |  | 36 | 36 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 2 | 2026-05-11 | 2026-05-12 | 2026-05-11 | 2026-05-12 | 19812.18 | 19812.18 | 19812.18 | 100% | 100% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-PR-LL-LS-MA-20 | Benches, Seats (Rectangular & Circular) | 2 | 2026-05-11 | 2026-05-12 | 2026-05-11 | 2026-05-12 | 4007.97 | 4007.97 | 4007.97 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-MA-30 | Fence, gates and accessories | 2 | 2026-05-11 | 2026-05-12 | 2026-05-11 | 2026-05-12 | 2529.21 | 2529.21 | 2529.21 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-MA-10 | Bike and Walk Path Materials | 2 | 2026-05-11 | 2026-05-12 | 2026-05-11 | 2026-05-12 | 13275 | 13275 | 13275 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 96 | 2026-03-02 | 2026-06-30 | 2026-03-02 | 2026-09-19 | 273522.54 | 273522.54 | 273522.54 | 100% | 100% | 0 | 0 | 0 |  | 6 | 6 | 0 | 0
PG-Q-PR-LL-SP-MA-50 | Air Dome Materials(Completed) | 91 | 2026-03-02 | 2026-06-24 | 2026-03-02 | 2026-06-24 | 62622.07 | 62622.07 | 62622.07 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MA-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc) | 8 | 2026-05-12 | 2026-05-20 | 2026-05-12 | 2026-05-20 | 13051.5 | 13051.5 | 13051.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MA-20 | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc) | 8 | 2026-05-12 | 2026-05-20 | 2026-05-12 | 2026-05-20 | 2256 | 2256 | 2256 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MA-30 | Padel Playgound Materials (Flooring, fence, tempered glass, etc) | 8 | 2026-05-12 | 2026-05-20 | 2026-05-12 | 2026-05-20 | 5950.8 | 5950.8 | 5950.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MA-40 | Tartan Floor | 8 | 2026-05-12 | 2026-05-20 | 2026-05-12 | 2026-05-20 | 43524 | 43524 | 43524 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MA-50_R | Air Dome Materials(Remaining) | 5 | 2026-06-25 | 2026-06-30 | 2026-07-02 | 2026-09-19 | 146118.17 | 146118.17 | 146118.17 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 40 | 2026-03-09 | 2026-04-28 | 2026-03-09 | 2026-04-28 | 1417.5 | 1417.5 | 1417.5 | 100% | 100% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-Q-PR-LL-CO-MA-10 | Autoclaved Aerated Panel | 40 | 2026-03-09 | 2026-04-28 | 2026-03-09 | 2026-04-28 | 1417.5 | 1417.5 | 1417.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 34 | 2026-06-09 | 2026-07-18 | 2026-06-09 | 2026-10-01 | 1902-06-07 05:31 | 889.23 | 1902-06-07 05:31 | 100% | 100% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-PR-LL-MT-MA-10 | Metal Doors(Completed) | 14 | 2026-06-09 | 2026-06-24 | 2026-06-09 | 2026-06-24 | 1900-03-16 12:29 | 76.52 | 76.52 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-MT-MA-20 | Curtain Wall(Completed) | 14 | 2026-06-09 | 2026-06-24 | 2026-06-09 | 2026-06-24 | 1901-04-01 00:29 | 1901-04-01 00:29 | 1901-04-01 00:29 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-MT-MA-10_R | Metal Doors(Remaining) | 15 | 2026-06-25 | 2026-07-12 | 2026-09-16 | 2026-10-01 | 1900-02-19 00:14 | 51.01 | 51.01 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-MT-MA-20_R | Curtain Wall(Remaining) | 20 | 2026-06-25 | 2026-07-18 | 46281 | 2026-10-01 | 1900-10-30 16:19 | 1900-10-30 16:19 | 1900-10-30 16:19 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 34 | 2026-06-09 | 2026-07-18 | 2026-05-20 | 2026-06-24 | 3553.95 | 3553.95 | 3553.95 | 100% | 100% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-PR-LL-PB-MA-10 | Booster Pump(Completed) | 14 | 2026-06-09 | 2026-06-24 | 2026-06-09 | 2026-06-24 | 1090.98 | 1090.98 | 1090.98 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-PB-MA-20 | GRP Sectional Panel Water Tanks (4x3x3m)(Completed) | 14 | 2026-06-09 | 2026-06-24 | 2026-06-09 | 2026-06-24 | 1041.39 | 1041.39 | 1041.39 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-PB-MA-10_R | Booster Pump(Remaining) | 20 | 2026-06-25 | 2026-07-18 | 2026-05-20 | 2026-05-21 | 727.32 | 727.32 | 727.32 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-PB-MA-20_R | GRP Sectional Panel Water Tanks (4x3x3m)(Remaining) | 15 | 2026-06-25 | 2026-07-12 | 2026-06-03 | 2026-06-06 | 694.26 | 694.26 | 694.26 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 45 | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-06 | 24486.75 | 24486.75 | 24486.75 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-PR-LL-IR-MA-10 | HDPE Pipes | 45 | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-06 | 19941 | 19941 | 19941 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-IR-MA-20 | Irrigation Control System | 45 | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-06 | 4545.75 | 4545.75 | 4545.75 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 41 | 2026-05-12 | 2026-07-02 | 2026-05-12 | 2026-09-16 | 35203.11 | 35203.11 | 35203.11 | 100% | 100% | 0 | 0 | 0 |  | 16 | 16 | 0 | 0
PG-Q-PR-LL-EL-MA-10 | Main Distribution Board(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 1900-10-23 12:58 | 297.54 | 297.54 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-20 | Power Panels (Pump, Street Light)(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 1900-08-25 00:43 | 238.03 | 1900-08-25 00:43 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-30 | Site Lighting Poles(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 1947-08-26 06:43 | 17405.28 | 17405.28 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-40 | Lighting Fixtures(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 1902-02-07 16:48 | 769.7 | 1902-02-07 16:48 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 602.51 | 602.51 | 602.51 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 587.63 | 587.63 | 587.63 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-70 | Security and Access Control System Materials(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 743.94 | 743.94 | 743.94 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-80 | Fire Alarm System Materials(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 1901-04-21 05:31 | 477.23 | 477.23 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-10_R | Main Distribution Board(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-30 | 2026-09-16 | 1900-07-16 08:38 | 198.36 | 198.36 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-20_R | Power Panels (Pump, Street Light)(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-30 | 2026-09-16 | 1900-06-06 16:34 | 158.69 | 1900-06-06 16:34 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-30_R | Site Lighting Poles(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-30 | 2026-09-16 | 1931-10-07 12:29 | 11603.52 | 11603.52 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-40_R | Lighting Fixtures(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-12 | 2026-07-23 | 513.13 | 513.13 | 513.13 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-30 | 2026-09-16 | 1901-02-04 16:19 | 401.68 | 401.68 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-30 | 2026-09-16 | 391.75 | 1901-01-25 18:00 | 391.75 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-70_R | Security and Access Control System Materials(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-27 | 2026-09-16 | 1901-05-09 23:02 | 495.96 | 495.96 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MA-80_R | Fire Alarm System Materials(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-27 | 2026-09-16 | 1900-11-13 03:50 | 1900-11-13 03:50 | 1900-11-13 03:50 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SHORT LEAD ITEMS |  | 25 | 2026-02-21 | 2026-03-26 | 2026-02-21 | 2026-03-26 | 167240.94 | 167240.94 | 167240.94 | 100% | 100% | 0 | 0 | 0 |  | 39 | 39 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 25 | 2026-02-21 | 2026-03-26 | 2026-02-21 | 2026-03-26 | 139867.29 | 139867.29 | 139867.29 | 100% | 100% | 0 | 0 | 0 |  | 8 | 8 | 0 | 0
PG-Q-PR-SL-LS-MA-10 | Backfilling Materials | 25 | 2026-02-21 | 2026-03-26 | 2026-02-21 | 2026-03-26 | 36450 | 36450 | 36450 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MA-30 | Compacted Natural Ground Soil | 22 | 2026-02-25 | 2026-03-26 | 2026-02-25 | 2026-03-26 | 8580 | 8580 | 8580 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MA-20 | Interlock tiles | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 29832 | 29832 | 29832 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MA-40 | Curb Stone | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 43185 | 43185 | 43185 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MA-50 | Thermoplastic pavement road marking | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 525.63 | 525.63 | 525.63 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MA-60 | Traffic Signages | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 198.36 | 198.36 | 198.36 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MA-70 | Trees | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 9546.3 | 9546.3 | 9546.3 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-MA-80 | Lawn | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 11550 | 11550 | 11550 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 24 | 2026-02-23 | 2026-03-26 | 2026-02-23 | 2026-03-26 | 1609.47 | 1609.47 | 1609.47 | 100% | 100% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-Q-PR-SL-CO-MA-10 | Steel Rebar | 14 | 2026-02-23 | 2026-03-10 | 2026-02-23 | 2026-03-10 | 1901-04-20 19:41 | 476.82 | 476.82 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-MA-20 | Concrete | 9 | 2026-03-01 | 2026-03-10 | 2026-03-01 | 2026-03-10 | 1901-06-01 20:24 | 518.85 | 518.85 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-MA-40 | CMU Block | 15 | 2026-03-05 | 2026-03-26 | 2026-03-05 | 2026-03-26 | 1900-05-03 04:48 | 124.2 | 124.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-MA-50 | Concrete Repair & Protection Materials | 15 | 2026-03-05 | 2026-03-26 | 2026-03-05 | 2026-03-26 | 1901-01-06 | 372 | 372 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-MA-30 | Screed | 1 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 1900-04-26 14:24 | 117.6 | 117.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL & FINISHES WORK |  | 17 | 2026-02-25 | 2026-03-16 | 2026-02-25 | 2026-03-16 | 7931.55 | 7931.55 | 7931.55 | 100% | 100% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PG-Q-PR-SL-AR-MA-40 | Cement Plaster | 17 | 2026-02-25 | 2026-03-16 | 2026-02-25 | 2026-03-16 | 1900-08-08 08:53 | 221.37 | 221.37 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MA-50 | Acrylic Paint | 14 | 2026-03-01 | 2026-03-16 | 2026-03-01 | 2026-03-16 | 147.9 | 147.9 | 147.9 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MA-10 | Ceramic tiles | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 571.95 | 571.95 | 571.95 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MA-20 | Anti-slip Granite tiles | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1901-06-18 12:00 | 535.5 | 535.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MA-30 | Epoxy Paint | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 111.18 | 111.18 | 111.18 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MA-60 | Stone Cladding | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1905-01-25 04:48 | 1852.2 | 1852.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MA-70 | Aluminum Plates | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MA-80 | Phenolic Partition | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1903-09-01 09:36 | 1340.4 | 1340.4 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MA-90 | Glass Partition | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 155.4 | 155.4 | 155.4 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MA-100 | Gypsum Boards | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1900-07-06 13:55 | 188.58 | 188.58 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MA-110 | Specialities Materials (Toilet accessories, lockers, logo, etc) | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 2262.87 | 2262.87 | 2262.87 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-MA-120 | Waterproofing System Materials | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1901-06-27 04:48 | 544.2 | 544.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 12 | 2026-03-09 | 2026-03-26 | 2026-03-09 | 2026-03-26 | 1901-04-22 21:22 | 478.89 | 478.89 | 100% | 100% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-PR-SL-MT-MA-20 | Galvanized Steel Roof Scupper | 12 | 2026-03-09 | 2026-03-26 | 2026-03-09 | 2026-03-26 | 1900-01-30 07:41 | 31.32 | 31.32 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-MT-MA-30 | Galvanized Steel Cover with frame | 12 | 2026-03-09 | 2026-03-26 | 2026-03-09 | 2026-03-26 | 1900-03-25 17:02 | 85.71 | 85.71 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-MT-MA-10 | Galvanized Steel Ladder | 9 | 2026-03-12 | 2026-03-26 | 2026-03-12 | 2026-03-26 | 1900-12-26 20:38 | 361.86 | 361.86 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
HVAC WORK |  | 20 | 2026-02-28 | 2026-03-26 | 2026-02-28 | 2026-03-26 | 1901-08-28 08:38 | 606.36 | 606.36 | 100% | 100% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-PR-SL-AC-MA-10 | Split Air Conditioning Unit | 20 | 2026-02-28 | 2026-03-26 | 2026-02-28 | 2026-03-26 | 1900-11-04 22:19 | 309.93 | 309.93 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-MA-20 | Air Duct | 16 | 2026-03-04 | 2026-03-26 | 2026-03-04 | 2026-03-26 | 1900-06-04 | 156 | 156 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-MA-30 | Diffusers and Grills | 11 | 2026-03-10 | 2026-03-26 | 2026-03-10 | 2026-03-26 | 1900-03-14 07:26 | 74.31 | 74.31 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-MA-40 | Exhaust fans | 11 | 2026-03-10 | 2026-03-26 | 2026-03-10 | 2026-03-26 | 1900-03-06 02:53 | 66.12 | 66.12 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 3147.03 | 3147.03 | 3147.03 | 100% | 100% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-PR-SL-PB-MA-10 | PPR Pipes & Valves | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 265.2 | 265.2 | 265.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-PB-MA-20 | UPCV Pipes | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1900-11-30 04:34 | 335.19 | 335.19 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-PB-MA-30 | Sanitary Drainage Fixtures | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2546.64 | 2546.64 | 2546.64 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 17 | 2026-03-03 | 2026-03-26 | 2026-03-03 | 2026-03-26 | 13170.12 | 13170.12 | 13170.12 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-PR-SL-IR-MA-10 | Gate Valve including valve box | 17 | 2026-03-03 | 2026-03-26 | 2026-03-03 | 2026-03-26 | 1330.74 | 1330.74 | 1330.74 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-IR-MA-20 | Bulbblers and Spreyers | 12 | 2026-03-09 | 2026-03-26 | 2026-03-09 | 2026-03-26 | 11839.38 | 11839.38 | 11839.38 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1901-02-10 12:29 | 407.52 | 407.52 | 100% | 100% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-Q-PR-SL-EL-MA-10 | Wiring Devices Materials | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1901-02-10 12:29 | 407.52 | 407.52 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE FIGHTING WORK |  | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1900-01-21 17:02 | 22.71 | 22.71 | 100% | 100% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-Q-PR-SL-FF-MA-10 | Fire Extinguishers | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1900-01-21 17:02 | 22.71 | 22.71 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PROCUREMENT |  | 145 | 2026-03-03 | 2026-08-27 | 2026-03-03 |  | 4735135.8 | 3896713.2 | 4735135.8 | 100% | 82.29% | 0 | 0 | 0 |  | 214 | 185 | 27 | 2
LONG LEAD ITEMS |  | 132 | 2026-03-18 | 2026-08-27 | 2026-03-18 |  | 3229967.34 | 2438081.97 | 3229967.34 | 100% | 75.48% | 0 | 0 | 0 |  | 121 | 103 | 16 | 2
PURCHASE ORDER |  | 92 | 2026-03-18 | 2026-07-12 | 2026-03-18 | 2026-09-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 31 | 31 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 5 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-11 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-PR-LL-LS-PO-20 | Benches, Seats (Rectangular & Circular) | 5 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-11 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-PO-30 | Fence, gates and accessories | 5 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-11 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-PO-10 | Bike and Walk Path Materials | 5 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-11 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 87 | 2026-03-26 | 2026-07-09 | 2026-03-26 | 2026-07-09 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-Q-PR-LL-SP-PO-40 | Tartan Floor | 36 | 2026-03-26 | 2026-05-07 | 2026-03-26 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-PO-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc) | 35 | 2026-03-28 | 2026-05-07 | 2026-03-28 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-PO-20 | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc) | 35 | 2026-03-28 | 2026-05-07 | 2026-03-28 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-PO-30 | Padel Playgound Materials (Flooring, fence, tempered glass, etc) | 35 | 2026-03-28 | 2026-05-07 | 2026-03-28 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-PO-50 | Air Dome Materials | 8 | 2026-07-01 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 39 | 2026-03-18 | 2026-05-07 | 2026-03-18 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-Q-PR-LL-CO-PO-10 | Autoclaved Aerated Panel | 39 | 2026-03-18 | 2026-05-07 | 2026-03-18 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 36 | 2026-03-26 | 2026-05-07 | 2026-03-26 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-PR-LL-MT-PO-10 | Metal Doors | 36 | 2026-03-26 | 2026-05-07 | 2026-03-26 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-MT-PO-20 | Curtain Wall | 36 | 2026-03-26 | 2026-05-07 | 2026-03-26 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 34 | 2026-03-29 | 2026-05-07 | 2026-03-29 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-PR-LL-PB-PO-10 | Booster Pump | 34 | 2026-03-29 | 2026-05-07 | 2026-03-29 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-PB-PO-20 | GRP Sectional Panel Water Tanks (4x3x3m) | 30 | 2026-04-02 | 2026-05-07 | 2026-04-02 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 37 | 2026-03-25 | 2026-05-07 | 2026-03-25 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-PR-LL-IR-PO-10 | HDPE Pipes | 37 | 2026-03-25 | 2026-05-07 | 2026-03-25 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-IR-PO-20 | Irrigation Control System | 37 | 2026-03-25 | 2026-05-07 | 2026-03-25 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 48 | 2026-05-13 | 2026-07-12 | 2026-05-13 | 2026-09-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 16 | 16 | 0 | 0
PG-Q-PR-LL-EL-PO-10 | Main Distribution Board(Completed) | 33 | 2026-05-13 | 2026-06-25 | 2026-05-13 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-20 | Power Panels (Pump, Street Light)(Completed) | 33 | 2026-05-13 | 2026-06-25 | 2026-05-13 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-30 | Site Lighting Poles(Completed) | 33 | 2026-05-13 | 2026-06-25 | 2026-05-13 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-40 | Lighting Fixtures(Completed) | 33 | 2026-05-13 | 2026-06-25 | 2026-05-13 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 33 | 2026-05-13 | 2026-06-25 | 2026-05-13 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 33 | 2026-05-13 | 2026-06-25 | 2026-05-13 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-70 | Security and Access Control System Materials(Completed) | 33 | 2026-05-13 | 2026-06-25 | 2026-05-13 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-80 | Fire Alarm System Materials(Completed) | 33 | 2026-05-13 | 2026-06-25 | 2026-05-13 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-10_R | Main Distribution Board(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-08-14 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-20_R | Power Panels (Pump, Street Light)(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-08-14 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-30_R | Site Lighting Poles(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-08-14 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-40_R | Lighting Fixtures(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-07-23 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-08-27 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-08-27 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-70_R | Security and Access Control System Materials(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-08-27 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-PO-80_R | Fire Alarm System Materials(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-08-27 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MANUFACTURE / FABRICATION |  | 81 | 2026-05-05 | 2026-08-11 | 2026-05-05 |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 45 | 44 | 0 | 1
EXTERNAL / LANDSCAPE WORK |  | 65 | 2026-05-05 | 2026-07-23 | 2026-05-05 | 2026-09-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 6 | 6 | 0 | 0
PG-Q-PR-LL-LS-MF-20 | Benches, Seats (Rectangular & Circular)(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-MF-30 | Fence, gates and accessories(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-MF-10 | Bike and Walk Path Materials(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-MF-20_R | Benches, Seats (Rectangular & Circular)(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-07-30 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-MF-30_R | Fence, gates and accessories(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-14 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-MF-10_R | Bike and Walk Path Materials(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-30 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 81 | 2026-05-05 | 2026-08-11 | 2026-05-05 | 2026-09-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 9 | 9 | 0 | 0
PG-Q-PR-LL-SP-MF-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc)(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MF-20 | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc)(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MF-30 | Padel Playgound Materials (Flooring, fence, tempered glass, etc)(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MF-40 | Tartan Floor(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MF-10_R | Football Playground Materials (Flooring, goal post, nets, paints, etc)(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-07-30 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MF-20_R | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc)(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-14 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MF-30_R | Padel Playgound Materials (Flooring, fence, tempered glass, etc)(Remaining) | 15 | 2026-06-25 | 2026-07-12 | 2026-07-30 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MF-40_R | Tartan Floor(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-07-22 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-MF-50 | Air Dome Materials | 28 | 2026-07-11 | 2026-08-11 | 2026-08-27 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 55 | 2026-05-05 | 2026-07-12 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-PR-LL-CO-MF-10 | Autoclaved Aerated Panel(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-CO-MF-10_R | Autoclaved Aerated Panel(Remaining) | 15 | 2026-06-25 | 2026-07-12 | 2026-06-01 | 2026-06-04 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 65 | 2026-05-05 | 2026-07-23 | 2026-05-05 |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 3 | 0 | 1
PG-Q-PR-LL-MT-MF-10 | Metal Doors(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-MT-MF-20 | Curtain Wall(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-MT-MF-10_R | Metal Doors(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-09-06 | 2026-10-02 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-MT-MF-20_R | Curtain Wall(Remaining) | 25 | 2026-06-25 | 2026-07-23 |  |  | 0 | 0 | 0 | 100% | 0% | 0 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PLUMBING WORK |  | 65 | 2026-05-05 | 2026-07-23 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-PR-LL-PB-MF-10 | Booster Pump(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-PB-MF-20 | GRP Sectional Panel Water Tanks (4x3x3m)(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-PB-MF-10_R | Booster Pump(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-06-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-PB-MF-20_R | GRP Sectional Panel Water Tanks (4x3x3m)(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-06-06 | 2026-06-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 50 | 2026-05-05 | 2026-07-06 | 2026-05-05 | 2026-09-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-PR-LL-IR-MF-10 | HDPE Pipes(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-IR-MF-20 | Irrigation Control System(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-IR-MF-10_R | HDPE Pipes(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-06-02 | 2026-06-04 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-IR-MF-20_R | Irrigation Control System(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-30 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 74 | 2026-05-12 | 2026-08-10 | 2026-05-12 | 2026-09-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 16 | 16 | 0 | 0
PG-Q-PR-LL-EL-MF-10 | Main Distribution Board(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-20 | Power Panels (Pump, Street Light)(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-30 | Site Lighting Poles(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-40 | Lighting Fixtures(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-70 | Security and Access Control System Materials(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-80 | Fire Alarm System Materials(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-10_R | Main Distribution Board(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-08-14 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-20_R | Power Panels (Pump, Street Light)(Remaining) | 15 | 2026-07-13 | 2026-07-29 | 2026-08-14 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-30_R | Site Lighting Poles(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-08-14 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-40_R | Lighting Fixtures(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-08-14 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-08-27 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-08-27 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-70_R | Security and Access Control System Materials(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-08-27 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-MF-80_R | Fire Alarm System Materials(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-08-27 | 2026-09-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
DELIVERY TO SITE |  | 94 | 2026-05-06 | 2026-08-27 | 2026-05-06 |  | 3229967.34 | 2438081.97 | 3229967.34 | 100% | 75.48% | 0 | 0 | 0 |  | 45 | 28 | 16 | 1
EXTERNAL / LANDSCAPE WORK |  | 79 | 2026-05-06 | 2026-08-10 | 2026-05-06 |  | 178309.62 | 176866.75 | 178309.62 | 100% | 99.19% | 0 | 0 | 0 |  | 6 | 5 | 1 | 0
PG-Q-PR-LL-LS-DL-20 | Benches, Seats (Rectangular & Circular)(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 21643.04 | 21643.04 | 21643.04 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-DL-30 | Fence, gates and accessories(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 11381.45 | 11381.45 | 11381.45 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-DL-10 | Bike and Walk Path Materials(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 71685 | 71685 | 71685 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-DL-10_R | Bike and Walk Path Materials(Remaining) | 9 | 2026-07-07 | 2026-07-16 | 2026-08-14 | 2026-09-26 | 47790 | 47790 | 47790 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-LS-DL-20_R | Benches, Seats (Rectangular & Circular)(Remaining) | 15 | 2026-07-25 | 2026-08-10 | 2026-08-14 |  | 14428.69 | 12985.82 | 14428.69 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-LL-LS-DL-30_R | Fence, gates and accessories(Remaining) | 15 | 2026-07-25 | 2026-08-10 | 2026-08-14 | 2026-09-30 | 11381.45 | 11381.45 | 11381.45 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 90 | 2026-05-06 | 2026-08-23 | 2026-05-06 |  | 2461702.86 | 1698207.88 | 2461702.86 | 100% | 68.99% | 0 | 0 | 0 |  | 9 | 4 | 5 | 0
PG-Q-PR-LL-SP-DL-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc)(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 70478.1 | 70478.1 | 70478.1 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-DL-20 | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc)(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 10152 | 10152 | 10152 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-DL-30 | Padel Playgound Materials (Fence, tempered glass, etc)(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 26778.6 | 26778.6 | 26778.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-DL-40 | Tartan Floor(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 235029.6 | 235029.6 | 235029.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-SP-DL-30_R | Padel Playgound Materials (Fence, tempered glass, etc)(Remaining) | 15 | 2026-07-13 | 2026-07-29 | 2026-08-14 |  | 26778.6 | 25439.67 | 26778.6 | 100% | 95% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-LL-SP-DL-10_R | Football Playground Materials (Flooring, goal post, nets, paints, etc)(Remaining) | 15 | 2026-07-25 | 2026-08-10 | 2026-08-14 |  | 46985.4 | 44636.13 | 46985.4 | 100% | 95% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-LL-SP-DL-20_R | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc)(Remaining) | 15 | 2026-07-25 | 2026-08-10 | 2026-08-14 |  | 10152 | 9644.4 | 10152 | 100% | 95% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-LL-SP-DL-40_R | Tartan Floor(Remaining) | 15 | 2026-07-25 | 2026-08-10 | 2026-08-14 |  | 156686.4 | 148852.08 | 156686.4 | 100% | 95% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-LL-SP-DL-50 | Air Dome Materials | 10 | 2026-08-12 | 2026-08-23 | 2026-08-25 |  | 1878662.16 | 1127197.3 | 1878662.16 | 100% | 60% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
CONCRETE WORK |  | 64 | 2026-05-06 | 2026-07-23 | 2026-05-06 | 2026-07-05 | 12757.5 | 12757.5 | 12757.5 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-PR-LL-CO-DL-10 | Autoclaved Aerated Panel(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 7654.5 | 7654.5 | 7654.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-CO-DL-10_R | Autoclaved Aerated Panel(Remaining) | 10 | 2026-07-13 | 2026-07-23 | 2026-07-04 | 2026-07-05 | 5103 | 5103 | 5103 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 79 | 2026-05-06 | 2026-08-10 | 2026-05-06 |  | 8003.07 | 4575.42 | 8003.07 | 100% | 57.17% | 0 | 0 | 0 |  | 4 | 3 | 0 | 1
PG-Q-PR-LL-MT-DL-10 | Metal Doors(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 573.89 | 573.89 | 573.89 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-MT-DL-20 | Curtain Wall(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 1909-05-19 15:36 | 1909-05-19 15:36 | 1909-05-19 15:36 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-MT-DL-10_R | Metal Doors(Remaining) | 15 | 2026-07-25 | 2026-08-10 | 2026-08-27 | 2026-10-02 | 573.89 | 573.89 | 573.89 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-MT-DL-20_R | Curtain Wall(Remaining) | 15 | 2026-07-25 | 2026-08-10 |  |  | 1909-05-19 15:36 | 0 | 3427.65 | 100% | 0% | 0 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PLUMBING WORK |  | 79 | 2026-05-06 | 2026-08-10 | 2026-05-06 |  | 31985.55 | 31595.03 | 31985.55 | 100% | 98.78% | 0 | 0 | 0 |  | 4 | 3 | 1 | 0
PG-Q-PR-LL-PB-DL-10 | Booster Pump(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 8182.35 | 8182.35 | 8182.35 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-PB-DL-20 | GRP Sectional Panel Water Tanks (4x3x3m)(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 7810.43 | 7810.43 | 7810.43 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-PB-DL-10_R | Booster Pump(Remaining) | 15 | 2026-07-25 | 2026-08-10 | 2026-08-20 | 2026-09-30 | 8182.35 | 8182.35 | 8182.35 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-PB-DL-20_R | GRP Sectional Panel Water Tanks (4x3x3m)(Remaining) | 15 | 2026-07-25 | 2026-08-10 | 2026-08-14 |  | 7810.43 | 7419.9 | 7810.43 | 100% | 95% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
IRRIGATION WORK |  | 57 | 2026-05-06 | 2026-07-15 | 2026-05-06 |  | 220380.75 | 219357.96 | 220380.75 | 100% | 99.54% | 0 | 0 | 0 |  | 4 | 3 | 1 | 0
PG-Q-PR-LL-IR-DL-10 | HDPE Pipes(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 89734.5 | 89734.5 | 89734.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-IR-DL-20 | Irrigation Control System(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 20455.88 | 20455.88 | 20455.88 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-IR-DL-10_R | HDPE Pipes(Remaining) | 7 | 2026-07-07 | 2026-07-14 | 2026-08-14 | 2026-08-27 | 89734.5 | 89734.5 | 89734.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-IR-DL-20_R | Irrigation Control System(Remaining) | 8 | 2026-07-07 | 2026-07-15 | 2026-08-20 |  | 20455.88 | 19433.08 | 20455.88 | 100% | 95% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
ELECTRICAL WORK |  | 88 | 2026-05-13 | 2026-08-27 | 2026-05-13 |  | 316827.99 | 294721.44 | 316827.99 | 100% | 93.02% | 0 | 0 | 0 |  | 16 | 8 | 8 | 0
PG-Q-PR-LL-EL-DL-10 | Main Distribution Board(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 1338.93 | 1338.93 | 1338.93 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-DL-20 | Power Panels (Pump, Street Light)(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 1785.24 | 1785.24 | 1785.24 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-DL-30 | Site Lighting Poles(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 78323.76 | 78323.76 | 78323.76 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-DL-40 | Lighting Fixtures(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 3463.64 | 3463.64 | 3463.64 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-DL-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 2711.31 | 2711.31 | 2711.31 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-DL-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 2644.33 | 2644.33 | 2644.33 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-DL-70 | Security and Access Control System Materials(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 3347.73 | 3347.73 | 3347.73 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-DL-80 | Fire Alarm System Materials(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 2147.55 | 2147.55 | 2147.55 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-LL-EL-DL-20_R | Power Panels (Pump, Street Light)(Remaining) | 10 | 2026-07-30 | 2026-08-10 | 2026-08-14 |  | 1785.24 | 1606.72 | 1785.24 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-Q-PR-LL-EL-DL-10_R | Main Distribution Board(Remaining) | 15 | 2026-08-11 | 2026-08-27 | 2026-08-14 |  | 3124.17 | 2811.75 | 3124.17 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-Q-PR-LL-EL-DL-30_R | Site Lighting Poles(Remaining) | 15 | 2026-08-11 | 2026-08-27 | 2026-08-14 |  | 182755.44 | 164479.9 | 182755.44 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-Q-PR-LL-EL-DL-40_R | Lighting Fixtures(Remaining) | 15 | 2026-08-11 | 2026-08-27 | 2026-08-14 |  | 1922-02-14 19:55 | 1919-11-29 15:36 | 8081.83 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-LL-EL-DL-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 15 | 2026-08-11 | 2026-08-27 | 2026-08-27 |  | 6326.4 | 5693.76 | 6326.4 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-Q-PR-LL-EL-DL-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 15 | 2026-08-11 | 2026-08-27 | 2026-08-27 |  | 6170.09 | 1915-03-15 01:55 | 6170.09 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-LL-EL-DL-70_R | Security and Access Control System Materials(Remaining) | 15 | 2026-08-11 | 2026-08-27 | 2026-08-27 |  | 7811.37 | 7030.23 | 7811.37 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-LL-EL-DL-80_R | Fire Alarm System Materials(Remaining) | 15 | 2026-08-11 | 2026-08-27 | 2026-08-27 |  | 5010.96 | 1912-05-05 20:38 | 5010.96 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
SHORT LEAD ITEMS |  | 105 | 2026-03-03 | 2026-07-12 | 2026-03-03 |  | 1505168.46 | 1458631.23 | 1505168.46 | 100% | 96.91% | 0 | 0 | 0 |  | 93 | 82 | 11 | 0
MATERIAL SUBMITTALS |  | 0 |  |  |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
PURCHASE ORDER |  | 64 | 2026-03-03 | 2026-05-21 | 2026-03-03 | 2026-05-20 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 39 | 39 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 57 | 2026-03-03 | 2026-05-13 | 2026-03-03 | 2026-05-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 8 | 8 | 0 | 0
PG-Q-PR-SL-LS-PO-10 | Backfilling Materials | 40 | 2026-03-03 | 2026-04-23 | 2026-03-03 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-PO-30 | Compacted Natural Ground Soil | 37 | 2026-03-07 | 2026-04-23 | 2026-03-07 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-PO-40 | Curb Stone | 28 | 2026-03-29 | 2026-04-30 | 2026-03-29 | 2026-04-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-PO-20 | Interlock tiles | 25 | 2026-04-01 | 2026-04-30 | 2026-04-01 | 2026-04-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-PO-50 | Thermoplastic pavement road marking | 2 | 2026-05-11 | 2026-05-13 | 2026-05-11 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-PO-60 | Traffic Signages | 2 | 2026-05-11 | 2026-05-13 | 2026-05-11 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-PO-70 | Trees | 2 | 2026-05-11 | 2026-05-13 | 2026-05-11 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-PO-80 | Lawn | 2 | 2026-05-11 | 2026-05-13 | 2026-05-11 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 39 | 2026-03-04 | 2026-04-23 | 2026-03-04 | 2026-04-22 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-Q-PR-SL-CO-PO-10 | Steel Rebar | 39 | 2026-03-04 | 2026-04-23 | 2026-03-04 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-PO-20 | Concrete | 34 | 2026-03-10 | 2026-04-23 | 2026-03-10 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-PO-40 | CMU Block | 30 | 2026-03-15 | 2026-04-23 | 2026-03-15 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-PO-50 | Concrete Repair & Protection Materials | 30 | 2026-03-15 | 2026-04-23 | 2026-03-15 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-PO-30 | Screed | 19 | 2026-04-01 | 2026-04-23 | 2026-04-01 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL & FINISHES WORK |  | 48 | 2026-03-07 | 2026-05-06 | 2026-03-07 | 2026-05-05 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PG-Q-PR-SL-AR-PO-40 | Cement Plaster | 48 | 2026-03-07 | 2026-05-06 | 2026-03-07 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-PO-50 | Acrylic Paint | 45 | 2026-03-10 | 2026-05-06 | 2026-03-10 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-PO-80 | Phenolic Partition | 40 | 2026-03-16 | 2026-05-06 | 2026-03-16 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-PO-90 | Glass Partition | 40 | 2026-03-16 | 2026-05-06 | 2026-03-16 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-PO-10 | Ceramic tiles | 32 | 2026-03-30 | 2026-05-06 | 2026-03-30 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-PO-20 | Anti-slip Granite tiles | 32 | 2026-03-30 | 2026-05-06 | 2026-03-30 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-PO-30 | Epoxy Paint | 32 | 2026-03-30 | 2026-05-06 | 2026-03-30 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-PO-100 | Gypsum Boards | 32 | 2026-03-30 | 2026-05-06 | 2026-03-30 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-PO-110 | Specialities Materials (Toilet accessories, lockers, logo, etc) | 32 | 2026-03-30 | 2026-05-06 | 2026-03-30 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-PO-120 | Waterproofing System Materials | 32 | 2026-03-30 | 2026-05-06 | 2026-03-30 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-PO-60 | Stone Cladding | 30 | 2026-04-01 | 2026-05-06 | 2026-04-01 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-PO-70 | Aluminum Plates | 30 | 2026-04-01 | 2026-05-06 | 2026-04-01 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 36 | 2026-03-25 | 2026-05-06 | 2026-03-25 | 2026-05-05 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-PR-SL-MT-PO-10 | Galvanized Steel Ladder | 36 | 2026-03-25 | 2026-05-06 | 2026-03-25 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-MT-PO-20 | Galvanized Steel Roof Scupper | 2 | 2026-05-04 | 2026-05-06 | 2026-05-04 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-MT-PO-30 | Galvanized Steel Cover with frame | 2 | 2026-05-04 | 2026-05-06 | 2026-05-04 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
HVAC WORK |  | 46 | 2026-03-09 | 2026-05-06 | 2026-03-09 | 2026-05-05 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-Q-PR-SL-AC-PO-10 | Split Air Conditioning Unit | 46 | 2026-03-09 | 2026-05-06 | 2026-03-09 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-PO-20 | Air Duct | 42 | 2026-03-14 | 2026-05-06 | 2026-03-14 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-PO-30 | Diffusers and Grills | 34 | 2026-03-28 | 2026-05-06 | 2026-03-28 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-PO-40 | Exhaust fans | 27 | 2026-04-05 | 2026-05-06 | 2026-04-05 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 33 | 2026-03-29 | 2026-05-06 | 2026-03-29 | 2026-05-05 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-PR-SL-PB-PO-10 | PPR Pipes & Valves | 33 | 2026-03-29 | 2026-05-06 | 2026-03-29 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-PB-PO-20 | UPCV Pipes | 33 | 2026-03-29 | 2026-05-06 | 2026-03-29 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-PB-PO-30 | Sanitary Drainage Fixtures | 33 | 2026-03-29 | 2026-05-06 | 2026-03-29 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 43 | 2026-03-12 | 2026-05-06 | 2026-03-12 | 2026-05-05 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-Q-PR-SL-IR-PO-10 | Gate Valve including valve box | 43 | 2026-03-12 | 2026-05-06 | 2026-03-12 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-IR-PO-20 | Bulbblers and Spreyers | 38 | 2026-03-18 | 2026-05-06 | 2026-03-18 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 8 | 2026-05-12 | 2026-05-21 | 2026-05-12 | 2026-05-20 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-Q-PR-SL-EL-PO-10 | Wiring Devices Materials | 8 | 2026-05-12 | 2026-05-21 | 2026-05-12 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE FIGHTING WORK |  | 30 | 2026-04-01 | 2026-05-06 | 2026-04-01 | 2026-05-05 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-Q-PR-SL-FF-PO-10 | Fire Extinguishers | 30 | 2026-04-01 | 2026-05-06 | 2026-04-01 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
DELIVERY TO SITE |  | 103 | 2026-03-05 | 2026-07-12 | 2026-03-05 |  | 1505168.46 | 1458631.23 | 1505168.46 | 100% | 96.91% | 0 | 0 | 0 |  | 54 | 43 | 11 | 0
EXTERNAL / LANDSCAPE WORK |  | 100 | 2026-03-05 | 2026-07-08 | 2026-03-05 |  | 1258805.61 | 1235050.47 | 1258805.61 | 100% | 98.11% | 0 | 0 | 0 |  | 12 | 8 | 4 | 0
PG-Q-PR-SL-LS-DL-10 | Backfilling Materials | 39 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-04-24 | 328050 | 328050 | 328050 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-DL-30 | Compacted Natural Ground Soil | 12 | 2026-04-30 | 2026-05-13 | 2026-04-30 | 2026-05-13 | 77220 | 77220 | 77220 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-DL-20 | Interlock tiles | 12 | 2026-04-30 | 2026-05-13 | 2026-04-30 | 2026-05-13 | 268488 | 268488 | 268488 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-DL-40 | Curb Stone | 12 | 2026-04-30 | 2026-05-13 | 2026-04-30 | 2026-05-13 | 388665 | 388665 | 388665 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-DL-50 | Thermoplastic pavement road marking(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 2838.4 | 2838.4 | 2838.4 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-DL-60 | Traffic Signages(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 1071.14 | 1071.14 | 1071.14 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-DL-70 | Trees(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 51550.02 | 51550.02 | 51550.02 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-DL-80 | Lawn(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 62370 | 62370 | 62370 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-LS-DL-50_R | Thermoplastic pavement road marking(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-08-27 |  | 1892.27 | 1903-02-08 08:38 | 1892.27 | 100% | 60% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-SL-LS-DL-60_R | Traffic Signages(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-08-27 |  | 714.1 | 499.87 | 714.1 | 100% | 70% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-SL-LS-DL-70_R | Trees(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-08-27 |  | 34366.68 | 1965-11-10 16:19 | 34366.68 | 100% | 70% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-SL-LS-DL-80_R | Lawn(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-08-27 |  | 41580 | 29106 | 41580 | 100% | 70% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
CONCRETE WORK |  | 50 | 2026-03-12 | 2026-05-13 | 2026-03-12 | 2026-05-13 | 14485.23 | 14485.23 | 14485.23 | 100% | 100% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-Q-PR-SL-CO-DL-20 | Concrete | 50 | 2026-03-12 | 2026-05-13 | 2026-03-12 | 2026-05-13 | 4669.65 | 4669.65 | 4669.65 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-DL-10 | Steel Rebar | 18 | 2026-04-23 | 2026-05-13 | 2026-04-23 | 2026-05-13 | 4291.38 | 4291.38 | 4291.38 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-DL-30 | Screed | 18 | 2026-04-23 | 2026-05-13 | 2026-04-23 | 2026-05-13 | 1058.4 | 1058.4 | 1058.4 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-DL-40 | CMU Block | 18 | 2026-04-23 | 2026-05-13 | 2026-04-23 | 2026-05-13 | 1117.8 | 1117.8 | 1117.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-CO-DL-50 | Concrete Repair & Protection Materials | 18 | 2026-04-23 | 2026-05-13 | 2026-04-23 | 2026-05-13 | 3348 | 3348 | 3348 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL & FINISHES WORK |  | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 71383.95 | 71383.95 | 71383.95 | 100% | 100% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PG-Q-PR-SL-AR-DL-10 | Ceramic tiles | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 5147.55 | 5147.55 | 5147.55 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-DL-20 | Anti-slip Granite tiles | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 4819.5 | 4819.5 | 4819.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-DL-30 | Epoxy Paint | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 1000.62 | 1000.62 | 1000.62 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-DL-40 | Cement Plaster | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 1992.33 | 1992.33 | 1992.33 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-DL-50 | Acrylic Paint | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 1331.1 | 1331.1 | 1331.1 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-DL-60 | Stone Cladding | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 16669.8 | 16669.8 | 16669.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-DL-70 | Aluminum Plates | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-DL-80 | Phenolic Partition | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 12063.6 | 12063.6 | 12063.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-DL-90 | Glass Partition | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 1398.6 | 1398.6 | 1398.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-DL-100 | Gypsum Boards | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 1697.22 | 1697.22 | 1697.22 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-DL-110 | Specialities Materials (Toilet accessories, lockers, logo, etc) | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 20365.83 | 20365.83 | 20365.83 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AR-DL-120 | Waterproofing System Materials | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 4897.8 | 4897.8 | 4897.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 51 | 2026-05-06 | 2026-07-08 | 2026-05-06 |  | 4310.01 | 3792.81 | 4310.01 | 100% | 88% | 0 | 0 | 0 |  | 6 | 3 | 3 | 0
PG-Q-PR-SL-MT-DL-10 | Galvanized Steel Ladder(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 1905-05-07 00:58 | 1905-05-07 00:58 | 1954.04 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-MT-DL-20 | Galvanized Steel Roof Scupper(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 1900-06-17 03:07 | 169.13 | 169.13 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-MT-DL-30 | Galvanized Steel Cover with frame(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 462.83 | 462.83 | 462.83 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-MT-DL-10_R | Galvanized Steel Ladder(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-09-26 |  | 1903-07-25 16:48 | 911.89 | 1302.7 | 100% | 70% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-SL-MT-DL-20_R | Galvanized Steel Roof Scupper(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 46291 |  | 1900-04-21 18:00 | 1900-03-18 22:19 | 1900-04-21 18:00 | 100% | 70% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-Q-PR-SL-MT-DL-30_R | Galvanized Steel Cover with frame(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-09-26 |  | 308.56 | 215.99 | 308.56 | 100% | 70% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
HVAC WORK |  | 51 | 2026-05-06 | 2026-07-08 | 2026-05-06 | 2026-10-02 | 5457.24 | 5457.24 | 5457.24 | 100% | 100% | 0 | 0 | 0 |  | 8 | 8 | 0 | 0
PG-Q-PR-SL-AC-DL-10 | Split Air Conditioning Unit(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 1904-07-30 14:53 | 1904-07-30 14:53 | 1673.62 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-DL-20 | Air Duct(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 1902-04-21 09:36 | 842.4 | 842.4 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-DL-30 | Diffusers and Grills(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 1901-02-04 06:29 | 1901-02-04 06:29 | 1901-02-04 06:29 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-DL-40 | Exhaust fans(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 357.05 | 357.05 | 357.05 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-DL-10_R | Split Air Conditioning Unit(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-08-27 | 2026-10-02 | 1903-01-19 18:00 | 1903-01-19 18:00 | 1903-01-19 18:00 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-DL-20_R | Air Duct(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-08-27 | 2026-10-02 | 1901-07-14 14:24 | 561.6 | 561.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-DL-30_R | Diffusers and Grills(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-08-27 | 2026-10-02 | 1900-09-23 12:29 | 1900-09-23 12:29 | 1900-09-23 12:29 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-AC-DL-40_R | Exhaust fans(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-08-27 | 2026-10-02 | 238.03 | 238.03 | 238.03 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 28323.27 | 28323.27 | 28323.27 | 100% | 100% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-Q-PR-SL-PB-DL-10 | PPR Pipes & Valves | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 2386.8 | 2386.8 | 2386.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-PB-DL-20 | UPCV Pipes | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 3016.71 | 3016.71 | 3016.71 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-PB-DL-30 | Sanitary Drainage Fixtures | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 22919.76 | 22919.76 | 22919.76 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 51 | 2026-05-06 | 2026-07-08 | 2026-05-06 |  | 118531.08 | 97195.49 | 118531.08 | 100% | 82% | 0 | 0 | 0 |  | 4 | 2 | 2 | 0
PG-Q-PR-SL-IR-DL-10 | Gate Valve including valve box(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 4790.66 | 4790.66 | 4790.66 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-IR-DL-20 | Bulbblers and Spreyers(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 42621.77 | 42621.77 | 42621.77 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-IR-DL-10_R | Gate Valve including valve box(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-08-14 |  | 7186 | 5030.2 | 7186 | 100% | 70% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-Q-PR-SL-IR-DL-20_R | Bulbblers and Spreyers(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-08-20 |  | 63932.65 | 44752.86 | 63932.65 | 100% | 70% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
ELECTRICAL WORK |  | 50 | 2026-05-11 | 2026-07-12 | 2026-05-11 |  | 3667.68 | 2787.44 | 3667.68 | 100% | 76% | 0 | 0 | 0 |  | 2 | 1 | 1 | 0
PG-Q-PR-SL-EL-DL-10 | Wiring Devices Materials(Completed) | 35 | 2026-05-11 | 2026-06-24 | 2026-05-11 | 2026-06-24 | 1467.07 | 1467.07 | 1467.07 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-EL-DL-10_R | Wiring Devices Materials(Remaining) | 15 | 2026-06-25 | 2026-07-12 | 2026-09-26 |  | 2200.61 | 1320.36 | 2200.61 | 100% | 60% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
FIRE FIGHTING WORK |  | 51 | 2026-05-06 | 2026-07-08 | 2026-05-06 |  | 1900-07-22 09:22 | 155.34 | 204.39 | 100% | 76% | 0 | 0 | 0 |  | 2 | 1 | 1 | 0
PG-Q-PR-SL-FF-DL-10 | Fire Extinguishers(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 1900-03-21 18:14 | 1900-03-21 18:14 | 1900-03-21 18:14 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-Q-PR-SL-FF-DL-10_R | Fire Extinguishers(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-09-26 |  | 122.63 | 73.58 | 122.63 | 100% | 60% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
CONSTRUCTION STAGE |  | 225 | 2026-03-24 | 2026-12-16 | 2026-03-24 |  | 8431928.45 | 6922352.74 | 10522524 | 81.46% | 66.88% | 8112 | 6400 | 5598 |  | 171 | 95 | 33 | 43
PLAYGROUND AND LANDSCAPING WORKS |  | 225 | 2026-03-24 | 2026-12-16 | 2026-03-24 |  | 5108188.92 | 5163264.28 | 6019638.42 | 87.35% | 88.29% | 5288 | 4102 | 3626 |  | 112 | 58 | 24 | 30
CUT AND FILL |  | 38 | 2026-03-24 | 2026-05-06 | 2026-03-24 | 2026-05-06 | 729000 | 729000 | 900600 | 100% | 100% | 376 | 276 | 276 |  | 3 | 3 | 0 | 0
PG-Q-CON-EX-CF-10 | Existing Soil Excavation Works | 36 | 2026-03-24 | 2026-05-04 | 2026-03-24 | 2026-05-04 | 233280 | 233280 | 233280 | 100% | 100% | 172 | 172 | 172 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-CF-30 | Levelling & Backfilling Works | 18 | 2026-04-16 | 2026-05-06 | 2026-04-16 | 2026-05-06 | 495720 | 495720 | 495720 | 100% | 100% | 104 | 104 | 104 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-CF-39 | Soil Replacement Works | 0 |  |  | 2026-04-05 | 2026-05-05 | 0 | 0 | 171600 | 0% | 100% | 100 | 0 | 0 | No | 1 | 1 | 0 | 0
PLAYGROUND WORKS |  | 189 | 2026-04-21 | 2026-12-02 | 2026-04-21 |  | 1098075.94 | 1220136.71 | 1318471.2 | 83.28% | 92.54% | 1896 | 1588 | 1548 |  | 35 | 20 | 11 | 4
FOOTBALL PLAYGROUND WORKS |  | 176 | 2026-04-21 | 2026-11-17 | 2026-04-21 |  | 564254.7 | 571303.6 | 611282.16 | 92.31% | 93.46% | 864 | 714 | 742 |  | 13 | 8 | 4 | 1
PG-Q-CON-EX-FB-10 | Subgrade Preparation and Compaction | 14 | 2026-04-21 | 2026-05-06 | 2026-04-21 | 2026-05-06 | 23667 | 23667 | 23667 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-FB-20 | Sub-Base Laying and Compaction | 10 | 2026-04-26 | 2026-05-06 | 2026-04-26 | 2026-05-06 | 23667 | 23667 | 23667 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-FB-30 | Base Course Laying and Compaction | 33 | 2026-05-06 | 2026-06-17 | 2026-05-06 | 2026-06-17 | 23667 | 23667 | 23667 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-FB-40 | Tartan flooring(Completed) | 7 | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 104457.6 | 104457.6 | 104457.6 | 100% | 100% | 19 | 19 | 19 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-FB-80 | Fine Grading & Leveling | 10 | 2026-06-25 | 2026-07-06 | 2026-07-09 | 2026-07-11 | 23667 | 23667 | 23667 | 100% | 100% | 76 | 76 | 76 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-FB-70 | Topsoil Placement | 12 | 2026-07-07 | 2026-07-20 | 2026-07-12 | 2026-08-14 | 23667 | 23667 | 23667 | 100% | 100% | 84 | 84 | 84 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-FB-50 | Goal Post Foundation | 25 | 2026-07-21 | 2026-08-18 | 2026-08-06 | 2026-08-27 | 35500.5 | 35500.5 | 35500.5 | 100% | 100% | 100 | 100 | 100 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-FB-120 | Installation of Lighting System | 12 | 2026-08-19 | 2026-09-01 | 2026-08-20 |  | 24360 | 20706 | 24360 | 100% | 85% | 32 | 32 | 27 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-FB-90 | Turfing / Seeding Works | 10 | 2026-09-02 | 2026-09-13 | 2026-08-14 |  | 1964-10-17 | 18933.6 | 23667 | 100% | 80% | 48 | 48 | 38 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-FB-40_R | Tartan flooring(Remaining) | 15 | 2026-09-14 | 2026-10-01 | 2026-07-12 | 2026-08-14 | 243734.4 | 243734.4 | 243734.4 | 100% | 100% | 45 | 45 | 45 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-FB-60 | Goal Post Installation & Alignment | 15 | 2026-10-03 | 2026-10-19 | 2026-08-27 |  | 14200.2 | 28400.4 | 35500.5 | 40% | 80% | 56 | 22 | 45 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-FB-110 | Install Playground Benches | 17 | 2026-10-20 | 2026-11-08 | 2026-08-27 |  | 0 | 1236.1 | 2060.16 | 0% | 60% | 32 | 0 | 19 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-FB-100 | Markings and Signages | 8 | 2026-11-09 | 2026-11-17 |  |  | 0 | 0 | 23667 | 0% | 0% | 84 | 0 | 0 | No | 1 | 0 | 0 | 1
BASKETBALL PLAYGROUND WORKS |  | 168 | 2026-04-30 | 2026-11-17 | 2026-04-30 |  | 367838.34 | 372446.93 | 381705.12 | 96.37% | 97.57% | 608 | 538 | 564 |  | 11 | 7 | 4 | 0
PG-Q-CON-EX-BB-10 | Subgrade Preparation and Compaction | 6 | 2026-04-30 | 2026-05-06 | 2026-04-30 | 2026-05-06 | 15472.08 | 15472.08 | 15472.08 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-BB-20 | Sub-Base Laying and Compaction | 1 | 2026-05-05 | 2026-05-06 | 2026-05-05 | 2026-05-06 | 15472.08 | 15472.08 | 15472.08 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-BB-30 | Base Course Laying and Compaction | 33 | 2026-05-06 | 2026-06-17 | 2026-05-06 | 2026-06-17 | 15472.08 | 15472.08 | 15472.08 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-BB-70 | Floor Surface Curing(Completed) | 7 | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 4641.62 | 4641.62 | 4641.62 | 100% | 100% | 7 | 7 | 7 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-BB-50 | Basketball Pole Foundation | 25 | 2026-06-25 | 2026-07-23 | 2026-08-06 | 2026-08-13 | 15472.08 | 15472.08 | 15472.08 | 100% | 100% | 100 | 100 | 100 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-BB-70_R | Floor Surface Curing(Remaining) | 15 | 2026-07-25 | 2026-08-10 | 2026-08-06 | 2026-08-14 | 10830.46 | 10830.46 | 10830.46 | 100% | 100% | 17 | 17 | 17 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-BB-40 | Tartan flooring | 17 | 2026-08-11 | 2026-08-30 | 2026-07-30 | 2026-08-14 | 261144 | 261144 | 261144 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-BB-80 | Court Line Marking | 15 | 2026-08-31 | 2026-09-16 | 2026-08-20 |  | 1935-11-03 18:14 | 10473.41 | 13091.76 | 100% | 80% | 28 | 28 | 22 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-BB-60 | Basketball Pole Installation & Alignment | 17 | 2026-09-17 | 2026-10-07 | 2026-08-20 |  | 1942-05-11 01:55 | 12377.66 | 15472.08 | 100% | 80% | 56 | 56 | 45 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-BB-90 | Backboard & Hoop Installation | 17 | 2026-10-08 | 2026-10-27 | 46296 |  | 1902-02-08 02:24 | 1928-09-02 09:50 | 13091.76 | 5.88% | 80% | 40 | 2 | 32 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-BB-100 | Install Playground Benches | 18 | 2026-10-28 | 2026-11-17 | 2026-09-27 |  | 0 | 618.05 | 1545.12 | 0% | 40% | 32 | 0 | 13 | No | 1 | 0 | 1 | 0
PADEL PLAYGROUND WORKS |  | 176 | 2026-05-06 | 2026-12-02 | 2026-05-06 |  | 165982.89 | 276386.18 | 325483.92 | 51% | 84.92% | 424 | 335 | 243 |  | 11 | 5 | 3 | 3
PG-Q-CON-EX-PD-10 | Excavation For Fence Footing(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 16243.2 | 16243.2 | 16243.2 | 100% | 100% | 54 | 54 | 54 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-PD-20 | RC Foundations For Fence(Completed) | 27 | 2026-05-20 | 2026-06-24 | 2026-05-20 | 2026-06-24 | 1767.48 | 1767.48 | 1767.48 | 100% | 100% | 24 | 24 | 24 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-PD-30 | Tartan Flooring Layers(Completed) | 7 | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 130572 | 130572 | 130572 | 100% | 100% | 20 | 20 | 20 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-PD-10_R | Excavation For Fence Footing(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-06 | 2026-08-14 | 1804.8 | 1804.8 | 1804.8 | 100% | 100% | 6 | 6 | 6 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-PD-20_R | RC Foundations For Fence(Remaining) | 20 | 2026-07-04 | 2026-07-26 | 2026-08-07 | 2026-08-27 | 1767.48 | 1767.48 | 1767.48 | 100% | 100% | 24 | 24 | 24 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-PD-40 | Steel Structure & Fence Supports Installation | 18 | 2026-08-11 | 2026-08-31 | 2026-08-20 |  | 3534.96 | 2474.47 | 3534.96 | 100% | 70% | 56 | 56 | 39 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-PD-60 | Chain Link Fence & Gates Installation | 16 | 2026-09-01 | 2026-09-19 | 2026-08-20 |  | 1914-07-07 10:34 | 1911-08-11 22:48 | 5302.44 | 100% | 80% | 72 | 72 | 58 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-PD-50 | Tempered Glass Installation | 17 | 2026-09-20 | 2026-10-10 |  |  | 1913-08-29 12:43 | 0 | 5302.44 | 94.12% | 0% | 84 | 79 | 0 | No | 1 | 0 | 0 | 1
PG-Q-CON-EX-PD-30_R | Tartan Flooring Layers(Remaining) | 16 | 2026-10-11 | 2026-10-28 | 46240 |  | 0 | 2221-09-27 19:12 | 130572 | 0% | 90% | 20 | 0 | 18 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-PD-70 | Court Accessories Installation | 15 | 2026-10-29 | 2026-11-15 |  |  | 0 | 0 | 27072 | 0% | 0% | 32 | 0 | 0 | No | 1 | 0 | 0 | 1
PG-Q-CON-EX-PD-80 | Install Playground Benches | 15 | 2026-11-16 | 2026-12-02 |  |  | 0 | 0 | 1545.12 | 0% | 0% | 32 | 0 | 0 | No | 1 | 0 | 0 | 1
GENERAL SITE WORKS |  | 205 | 2026-04-16 | 2026-12-16 | 2026-04-16 |  | 1494285.96 | 1303724.63 | 1617941.82 | 92.36% | 80.58% | 1996 | 1416 | 966 |  | 48 | 15 | 10 | 23
FENCE WORKS |  | 125 | 2026-04-16 | 2026-09-13 | 2026-04-16 |  | 32909.4 | 21391.11 | 32909.4 | 100% | 65% | 336 | 336 | 227 |  | 5 | 2 | 2 | 1
PG-Q-CON-EX-GN-FN-10 | Excavation for fence foundation | 3 | 2026-04-16 | 2026-04-19 | 2026-04-16 | 2026-04-19 | 6581.88 | 6581.88 | 6581.88 | 100% | 100% | 92 | 92 | 92 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-FN-20 | Concrete Foundations for Fence | 10 | 2026-07-21 | 2026-08-01 | 2026-08-13 | 2026-08-20 | 1918-01-06 21:07 | 6581.88 | 6581.88 | 100% | 100% | 68 | 68 | 68 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-FN-30 | Installation of Galvanized Steel Posts & Framing | 12 | 2026-08-02 | 2026-08-15 | 2026-08-20 |  | 1918-01-06 21:07 | 1915-04-25 14:24 | 6581.88 | 100% | 85% | 56 | 56 | 48 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-FN-40 | Fixing of Chain Link Mesh, Tensioning & Bracing | 15 | 2026-08-16 | 2026-09-01 | 46292 |  | 6581.88 | 1907-03-16 18:00 | 6581.88 | 100% | 40% | 48 | 48 | 19 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-FN-50 | Installation of Gates | 10 | 2026-09-02 | 2026-09-13 |  |  | 6581.88 | 0 | 6581.88 | 100% | 0% | 72 | 72 | 0 | No | 1 | 0 | 0 | 1
MECHANICAL WORK |  | 81 | 2026-05-12 | 2026-08-18 | 2026-05-12 |  | 780707.34 | 670165.14 | 780707.34 | 100% | 85.84% | 476 | 476 | 316 |  | 14 | 6 | 4 | 4
STORM WATER AND UTILITY WORK |  | 79 | 2026-05-12 | 2026-08-16 | 2026-05-12 |  | 27252 | 18086.4 | 27252 | 100% | 66.37% | 300 | 300 | 190 |  | 9 | 4 | 2 | 3
PG-Q-CON-EX-GN-M-10 | Excavation | 2 | 2026-05-12 | 2026-05-13 | 2026-05-12 | 2026-05-13 | 3096 | 3096 | 3096 | 100% | 100% | 92 | 92 | 92 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-M-20 | Bedding preparation & level control(Completed) | 27 | 2026-05-20 | 2026-06-24 | 2026-05-20 | 2026-06-24 | 1651.2 | 1651.2 | 1651.2 | 100% | 100% | 26 | 26 | 26 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-M-30 | Manhole Installation(Completed) | 7 | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 1032 | 1032 | 1032 | 100% | 100% | 10 | 10 | 10 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-M-20_R | Bedding preparation & level control(Remaining) | 8 | 2026-06-25 | 2026-07-04 | 2026-08-07 | 2026-08-27 | 412.8 | 412.8 | 412.8 | 100% | 100% | 6 | 6 | 6 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-M-30_R | Manhole Installation(Remaining) | 6 | 2026-07-05 | 2026-07-11 | 2026-08-20 |  | 4128 | 3302.4 | 4128 | 100% | 80% | 38 | 38 | 31 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-M-40 | 150 mm uPVC pipe laying & jointing | 6 | 2026-07-12 | 2026-07-18 | 2026-08-20 |  | 10740 | 1923-07-10 | 10740 | 100% | 80% | 32 | 32 | 26 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-M-50 | Concrete Encasement | 7 | 2026-07-19 | 2026-07-26 |  |  | 2064 | 0 | 2064 | 100% | 0% | 24 | 24 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-GN-M-60 | Backfilling & Compaction | 6 | 2026-07-27 | 2026-08-02 |  |  | 2064 | 0 | 2064 | 100% | 0% | 48 | 48 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-GN-M-70 | Surface Reinstatement & Civil Works | 6 | 2026-08-10 | 2026-08-16 |  |  | 2064 | 0 | 2064 | 100% | 0% | 24 | 24 | 0 | Yes | 1 | 0 | 0 | 1
IRRIGATION SYSTEM WORKS |  | 46 | 2026-06-17 | 2026-08-09 | 2026-06-17 |  | 753137.4 | 652078.74 | 753137.4 | 100% | 86.58% | 144 | 144 | 126 |  | 4 | 2 | 2 | 0
PG-Q-CON-EX-GN-M-80 | Installation of HDPE Irrigation Pipe Network with Gate Valve and Box(Completed) | 7 | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 148902.18 | 148902.18 | 148902.18 | 100% | 100% | 28 | 28 | 28 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-M-80_R | Installation of HDPE Irrigation Pipe Network with Gate Valve and Box(Remaining) | 3 | 2026-07-30 | 2026-08-02 | 2026-08-06 | 2026-10-01 | 276532.62 | 276532.62 | 276532.62 | 100% | 100% | 52 | 52 | 52 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-M-90 | Installation of Irrigation Control System | 3 | 2026-08-03 | 2026-08-05 | 2026-08-20 |  | 90915 | 72732 | 90915 | 100% | 80% | 32 | 32 | 26 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-M-100 | Installation of Bubblers and Sprinklers | 3 | 2026-08-06 | 2026-08-09 | 2026-08-27 |  | 236787.6 | 2321-05-23 22:34 | 236787.6 | 100% | 65% | 32 | 32 | 21 | Yes | 1 | 0 | 1 | 0
FIRE PROTECTION SYSTEM |  | 2 | 2026-08-17 | 2026-08-18 |  |  | 1900-11-12 22:34 | 0 | 1900-11-12 22:34 | 100% | 0% | 32 | 32 | 0 |  | 1 | 0 | 0 | 1
PG-Q-CON-EX-GN-M-110 | Fire Extinguisher Installation | 2 | 2026-08-17 | 2026-08-18 |  |  | 317.94 | 0 | 317.94 | 100% | 0% | 32 | 32 | 0 | Yes | 1 | 0 | 0 | 1
ELECTRICAL WORK |  | 137 | 2026-05-20 | 2026-11-01 | 2026-05-20 |  | 660770.22 | 519487.58 | 693965.28 | 95.22% | 74.86% | 784 | 582 | 208 |  | 21 | 3 | 3 | 15
POWER, LIGHTING & GROUNDING |  | 102 | 2026-05-20 | 2026-09-20 | 2026-05-20 |  | 636895.08 | 519487.58 | 636895.08 | 100% | 81.57% | 376 | 376 | 208 |  | 10 | 3 | 3 | 4
PG-Q-CON-EX-GN-E-10 | Excavation(Completed) | 27 | 2026-05-20 | 2026-06-24 | 2026-05-20 | 2026-06-24 | 121836.96 | 121836.96 | 121836.96 | 100% | 100% | 64 | 64 | 64 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-E-20 | Foundation Work for Site Lighting Poles(Completed) | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 69621.12 | 69621.12 | 69621.12 | 100% | 100% | 20 | 20 | 20 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-E-10_R | Excavation(Remaining) | 3 | 2026-08-13 | 2026-08-16 | 2026-07-16 | 2026-08-27 | 52215.84 | 52215.84 | 52215.84 | 100% | 100% | 28 | 28 | 28 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-E-20_R | Foundation Work for Site Lighting Poles(Remaining) | 4 | 2026-08-13 | 2026-08-17 | 2026-08-20 |  | 162449.28 | 2255-10-24 10:05 | 162449.28 | 100% | 80% | 48 | 48 | 38 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-E-30 | Lightning Protection System (LPS) | 3 | 2026-08-29 | 2026-08-31 | 2026-08-27 |  | 1922-08-17 | 1918-02-06 | 8265 | 100% | 80% | 32 | 32 | 26 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-E-40 | KWH Meter and MDB Installation | 2 | 2026-09-01 | 2026-09-02 |  |  | 1912-07-21 16:48 | 0 | 4586.7 | 100% | 0% | 32 | 32 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-GN-E-50 | Power Panels and Distribution Boards | 5 | 2026-09-03 | 2026-09-08 |  |  | 1947-08-18 21:36 | 0 | 17397.9 | 100% | 0% | 40 | 40 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-GN-E-60 | Site Lighting Poles Installation | 3 | 2026-09-09 | 2026-09-12 | 46254 |  | 2376-07-14 19:12 | 2281-03-24 05:46 | 174052.8 | 100% | 80% | 40 | 40 | 32 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-E-70 | Wiring Works | 3 | 2026-09-13 | 2026-09-15 |  |  | 1911-07-25 | 0 | 4224 | 100% | 0% | 32 | 32 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-GN-E-80 | Lighting Fixtures with outlets Installation | 4 | 2026-09-16 | 2026-09-20 |  |  | 1960-11-25 11:31 | 0 | 22245.48 | 100% | 0% | 40 | 40 | 0 | Yes | 1 | 0 | 0 | 1
ELV SYSTEMS (TELECOM, DATA, AV & CCTV) |  | 25 | 2026-09-21 | 2026-10-20 |  |  | 1956-04-24 03:22 | 0 | 43146 | 47.67% | 0% | 272 | 162 | 0 |  | 7 | 0 | 0 | 7
PG-Q-CON-EX-GN-E-90 | ELV Containment & Cabling Works | 3 | 2026-09-21 | 2026-09-24 |  |  | 1901-09-10 19:12 | 0 | 619.8 | 100% | 0% | 40 | 40 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-GN-E-100 | Fiber Optic Pull Box Installation | 3 | 2026-09-26 | 2026-09-28 |  |  | 1901-09-10 19:12 | 0 | 619.8 | 100% | 0% | 32 | 32 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-GN-E-110 | Telephone and Data Outlet Installation | 4 | 2026-09-29 | 2026-10-03 |  |  | 1910-03-06 19:12 | 0 | 3718.8 | 100% | 0% | 40 | 40 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-GN-E-120 | Telecom Equipment and AV HDMI Installation | 4 | 2026-10-04 | 2026-10-07 |  |  | 1941-09-30 02:53 | 0 | 15249.12 | 100% | 0% | 40 | 40 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-GN-E-130 | CCTV Rack / Cabinet Installation | 4 | 2026-10-08 | 2026-10-12 |  |  | 1900-12-26 14:53 | 0 | 1446.48 | 25% | 0% | 40 | 10 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-GN-E-140 | NVR and CCTV Monitor Installation | 4 | 2026-10-13 | 2026-10-17 |  |  | 0 | 0 | 1918-02-06 | 0% | 0% | 40 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-GN-E-150 | IP Camera Installation | 3 | 2026-10-18 | 2026-10-20 |  |  | 0 | 0 | 14880 | 0% | 0% | 40 | 0 | 0 | Yes | 1 | 0 | 0 | 1
FIRE ALARM SYSTEM |  | 32 | 2026-09-26 | 2026-11-01 |  |  | 1909-01-18 | 0 | 13924.2 | 23.74% | 0% | 136 | 44 | 0 |  | 4 | 0 | 0 | 4
PG-Q-CON-EX-GN-E-160 | Fire Alarm Containment & Cabling | 8 | 2026-09-26 | 2026-10-04 |  |  | 1905-06-05 14:24 | 0 | 1983.6 | 100% | 0% | 32 | 32 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-GN-E-170 | Fire Alarm Control Panel (FACP) Installation | 8 | 2026-10-05 | 2026-10-13 |  |  | 1903-08-14 09:36 | 0 | 2644.8 | 50% | 0% | 24 | 12 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-GN-E-180 | Initiating Devices (Detectors & Manual Pull Station) | 8 | 2026-10-14 | 2026-10-22 |  |  | 0 | 0 | 8097.6 | 0% | 0% | 40 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-GN-E-190 | Notification Appliances (Strobe with Sounder) | 8 | 2026-10-24 | 2026-11-01 |  |  | 0 | 0 | 1198.2 | 0% | 0% | 40 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PARKING WORK |  | 124 | 2026-06-17 | 2026-11-09 | 2026-06-17 |  | 19899 | 88440 | 102919.8 | 19.33% | 85.93% | 164 | 22 | 80 |  | 4 | 3 | 0 | 1
PG-Q-CON-EX-GN-PR-20 | Interlock tiles(Completed) | 7 | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 19899 | 19899 | 19899 | 100% | 100% | 22 | 22 | 22 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-PR-10 | Installlation of Parking Accessories | 5 | 2026-10-29 | 2026-11-03 | 2026-08-20 | 2026-10-01 | 0 | 44220 | 44220 | 0% | 100% | 32 | 0 | 32 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-PR-20_R | Interlock tiles(Remaining) | 3 | 2026-11-01 | 2026-11-03 | 2026-07-06 | 2026-07-10 | 0 | 1966-08-02 | 24321 | 0% | 100% | 26 | 0 | 26 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-PR-30 | Marking & Signages | 5 | 2026-11-04 | 2026-11-09 |  |  | 0 | 0 | 14479.8 | 0% | 0% | 84 | 0 | 0 | Yes | 1 | 0 | 0 | 1
SERVICE CONNECTION |  | 32 | 2026-11-10 | 2026-12-16 | 2026-07-12 |  | 0 | 4240.8 | 7440 | 0% | 57% | 236 | 0 | 135 |  | 4 | 1 | 1 | 2
PG-Q-CON-EX-GN-SC-10 | Excavation & Trench Preparation | 8 | 2026-11-10 | 2026-11-18 | 2026-07-12 | 2026-08-20 | 0 | 2232 | 2232 | 0% | 100% | 92 | 0 | 92 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-GN-SC-20 | HDPE Pipe Laying & Valve Installation | 8 | 2026-11-19 | 2026-11-28 | 2026-08-14 |  | 0 | 1905-06-30 19:12 | 2232 | 0% | 90% | 48 | 0 | 43 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-GN-SC-30 | Connection to City Network | 8 | 2026-11-29 | 2026-12-07 |  |  | 0 | 0 | 1488 | 0% | 0% | 48 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-GN-SC-40 | Backfilling | 8 | 2026-12-08 | 2026-12-16 |  |  | 0 | 0 | 1488 | 0% | 0% | 48 | 0 | 0 | Yes | 1 | 0 | 0 | 1
LANDSCAPING WORKS |  | 169 | 2026-05-31 | 2026-12-14 | 2026-05-30 |  | 1738536.62 | 1896825.54 | 2134335 | 81.46% | 88.87% | 392 | 194 | 259 |  | 14 | 9 | 3 | 2
HARDSCAPE WORK |  | 169 | 2026-05-31 | 2026-12-14 | 2026-05-30 |  | 1623036.62 | 1688925.54 | 1712409 | 94.78% | 98.63% | 224 | 152 | 183 |  | 11 | 8 | 2 | 1
PG-Q-CON-EX-LS-HS-10 | Curbstone Installation(Completed) | 22 | 2026-05-31 | 2026-06-24 | 2026-05-30 | 2026-06-24 | 604590 | 604590 | 604590 | 100% | 100% | 22 | 22 | 22 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-LS-HS-20 | Interlock Tiles Grey Scale with Black Marble Chips(Completed) | 22 | 2026-05-31 | 2026-06-24 | 2026-05-30 | 2026-06-24 | 36960 | 36960 | 36960 | 100% | 100% | 19 | 19 | 19 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-LS-HS-40 | Bike Path and Walking Path Construction(Completed) | 22 | 2026-05-31 | 2026-06-24 | 2026-05-30 | 2026-06-24 | 146025 | 146025 | 146025 | 100% | 100% | 26 | 26 | 26 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-LS-HS-30 | Stamped Concrete Floor(Completed) | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 207900 | 207900 | 207900 | 100% | 100% | 16 | 16 | 16 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-LS-HS-50 | Install Recycled Precast Concrete Seats(Completed) | 7 | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 6959.7 | 6959.7 | 6959.7 | 100% | 100% | 3 | 3 | 3 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-LS-HS-40_R | Bike Path and Walking Path Construction(Remaining) | 17 | 2026-07-18 | 2026-08-05 | 2026-07-08 | 2026-08-14 | 119475 | 119475 | 119475 | 100% | 100% | 22 | 22 | 22 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-LS-HS-10_R | Curbstone Installation(Remaining) | 10 | 2026-09-02 | 2026-09-13 | 2026-07-07 | 2026-08-14 | 259110 | 259110 | 259110 | 100% | 100% | 10 | 10 | 10 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-LS-HS-30_R | Stamped Concrete Floor(Remaining) | 13 | 2026-09-14 | 2026-09-29 | 2026-07-31 | 2026-08-27 | 207900 | 207900 | 207900 | 100% | 100% | 16 | 16 | 16 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-LS-HS-20_R | Interlock Tiles Grey Scale with Black Marble Chips(Remaining) | 13 | 2026-09-30 | 2026-10-14 | 2026-08-27 |  | 1993-05-27 22:05 | 49896 | 55440 | 61.54% | 90% | 29 | 18 | 26 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-LS-HS-50_R | Install Recycled Precast Concrete Seats(Remaining) | 10 | 2026-11-22 | 2026-12-02 | 2026-08-20 |  | 0 | 2037-03-10 20:10 | 62637.3 | 0% | 80% | 29 | 0 | 23 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-LS-HS-60 | Install Recycled Precast Concrete Trash Bins | 10 | 2026-12-03 | 2026-12-14 |  |  | 0 | 0 | 5412 | 0% | 0% | 32 | 0 | 0 | No | 1 | 0 | 0 | 1
SOFTSCAPE WORK |  | 140 | 2026-06-10 | 2026-11-21 | 2026-06-10 |  | 115500 | 207900 | 421926 | 27.37% | 49.27% | 168 | 42 | 76 |  | 3 | 1 | 1 | 1
PG-Q-CON-EX-LS-SS-20 | Lawn Area Preparation & Planting / Turfing(Completed) | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 115500 | 115500 | 115500 | 100% | 100% | 42 | 42 | 42 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-LS-SS-20_R | Lawn Area Preparation & Planting / Turfing(Remaining) | 15 | 2026-10-15 | 2026-11-01 | 2026-08-27 |  | 0 | 2152-12-23 | 115500 | 0% | 80% | 42 | 0 | 34 | No | 1 | 0 | 1 | 0
PG-Q-CON-EX-LS-SS-10 | Planting Trees | 17 | 2026-11-02 | 2026-11-21 |  |  | 0 | 0 | 190926 | 0% | 0% | 84 | 0 | 0 | No | 1 | 0 | 0 | 1
TANK WORKS |  | 81 | 2026-05-13 | 2026-08-19 | 2026-05-13 |  | 48290.4 | 13577.4 | 48290.4 | 100% | 28.12% | 628 | 628 | 576 |  | 12 | 11 | 0 | 1
SEPTIC TANK |  | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 7475.22 | 7475.22 | 7475.22 | 100% | 100% | 364 | 364 | 364 |  | 7 | 7 | 0 | 0
PG-Q-CON-EX-TW-ST-10 | Excavation | 29 | 2026-05-13 | 2026-06-20 | 2026-05-13 | 2026-06-20 | 1900-09-08 04:19 | 252.18 | 252.18 | 100% | 100% | 92 | 92 | 92 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-TW-ST-20 | PCC / Lean Concrete laying | 24 | 2026-05-20 | 2026-06-21 | 2026-05-20 | 2026-06-21 | 168.12 | 168.12 | 168.12 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-TW-ST-40 | RCC Wall | 4 | 2026-06-20 | 2026-06-23 | 2026-06-20 | 2026-06-23 | 2757.6 | 2757.6 | 2757.6 | 100% | 100% | 56 | 56 | 56 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-TW-ST-30 | RCC Foundation | 2 | 2026-06-21 | 2026-06-22 | 2026-06-21 | 2026-06-22 | 1277.64 | 1277.64 | 1277.64 | 100% | 100% | 56 | 56 | 56 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-TW-ST-50 | RCC Slab | 4 | 2026-06-21 | 2026-06-24 | 2026-06-21 | 2026-06-24 | 2599.38 | 2599.38 | 2599.38 | 100% | 100% | 56 | 56 | 56 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-TW-ST-60 | Finishing Work | 3 | 2026-06-22 | 2026-06-24 | 2026-06-22 | 2026-06-24 | 1900-09-08 04:19 | 252.18 | 252.18 | 100% | 100% | 24 | 24 | 24 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-TW-ST-70 | Backfilling | 2 | 2026-06-23 | 2026-06-24 | 2026-06-23 | 2026-06-24 | 1900-06-16 02:53 | 168.12 | 168.12 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
WATER STORAGE TANK |  | 81 | 2026-05-13 | 2026-08-19 | 2026-05-13 |  | 40815.18 | 6102.18 | 40815.18 | 100% | 14.95% | 264 | 264 | 212 |  | 5 | 4 | 0 | 1
PG-Q-CON-EX-TW-IR-10 | Excavation(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 1902-02-04 13:55 | 766.58 | 766.58 | 100% | 100% | 83 | 83 | 83 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-TW-IR-10_R | Excavation(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-07 | 2026-07-08 | 1900-03-25 04:19 | 85.18 | 85.18 | 100% | 100% | 9 | 9 | 9 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-TW-IR-20 | RCC Foundation | 15 | 2026-07-04 | 2026-07-20 | 2026-07-09 | 2026-08-26 | 4136.4 | 4136.4 | 4136.4 | 100% | 100% | 72 | 72 | 72 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-TW-IR-30 | Backfilling | 7 | 2026-07-21 | 2026-07-28 | 2026-08-20 | 2026-08-27 | 1114.02 | 1903-01-18 00:29 | 1114.02 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-TW-IR-40 | GRP Water Tank Installation | 8 | 2026-08-11 | 2026-08-19 |  |  | 34713 | 0 | 34713 | 100% | 0% | 52 | 52 | 0 | No | 1 | 0 | 0 | 1
AIR DOME CONSTRUCTION |  | 165 | 2026-05-13 | 2026-11-26 | 2026-05-13 |  | 3075439.54 | 1461181.68 | 4178041.2 | 73.61% | 34.97% | 1116 | 824 | 446 |  | 21 | 7 | 2 | 12
CIVIL WORK |  | 100 | 2026-05-13 | 2026-09-10 | 2026-05-13 |  | 1711669.97 | 1210693.39 | 1711669.97 | 100% | 70.73% | 536 | 536 | 392 |  | 9 | 7 | 0 | 2
PG-Q-CON-EX-AD-CL-10 | Excavation For Footing(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 25048.83 | 25048.83 | 25048.83 | 100% | 100% | 10 | 10 | 10 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-AD-CL-10_R | Excavation For Footing(Remaining) | 6 | 2026-07-09 | 2026-07-15 | 2026-07-09 | 2026-07-10 | 225439.46 | 225439.46 | 225439.46 | 100% | 100% | 90 | 90 | 90 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-AD-CL-20 | Anti-Termite Treatment | 2 | 2026-07-16 | 2026-07-18 | 2026-07-11 | 2026-07-12 | 83496.1 | 83496.1 | 83496.1 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-AD-CL-30 | PCC / Blinding Concrete | 3 | 2026-07-19 | 2026-07-21 | 2026-07-23 | 2026-08-06 | 125244.14 | 125244.14 | 125244.14 | 100% | 100% | 64 | 64 | 64 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-AD-CL-40 | RCC Foundation Works | 12 | 2026-07-22 | 2026-08-04 | 2026-07-31 | 2026-08-13 | 250488.29 | 250488.29 | 250488.29 | 100% | 100% | 88 | 88 | 88 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-AD-CL-50 | Backfilling with Compaction | 6 | 2026-08-05 | 2026-08-11 | 2026-08-06 | 2026-08-14 | 250488.29 | 250488.29 | 250488.29 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-AD-CL-60 | Installation of Anchorage System | 8 | 2026-08-12 | 2026-08-20 | 2026-08-27 | 2026-09-29 | 250488.29 | 250488.29 | 250488.29 | 100% | 100% | 60 | 60 | 60 | No | 1 | 1 | 0 | 0
PG-Q-CON-EX-AD-CL-70 | Installation of Steel Cable Structural System | 10 | 2026-08-22 | 2026-09-01 |  |  | 250488.29 | 0 | 250488.29 | 100% | 0% | 76 | 76 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-AD-CL-80 | Installation of Membrane System | 8 | 2026-09-02 | 2026-09-10 |  |  | 250488.29 | 0 | 250488.29 | 100% | 0% | 68 | 68 | 0 | Yes | 1 | 0 | 0 | 1
ARCHITECTURAL WORK |  | 27 | 2026-10-27 | 2026-11-26 | 2026-08-27 |  | 0 | 2242-11-26 03:22 | 712953.22 | 0% | 17.57% | 212 | 0 | 30 |  | 4 | 0 | 1 | 3
PG-Q-CON-EX-AD-AR-10 | Installation of Thermal Insulation System | 8 | 2026-10-27 | 2026-11-04 | 2026-08-27 |  | 0 | 2242-11-26 03:22 | 250488.29 | 0% | 50% | 60 | 0 | 30 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-AD-AR-40 | Final Fixing of Accessories & Finishes | 8 | 2026-11-05 | 2026-11-14 |  |  | 0 | 0 | 208740.24 | 0% | 0% | 56 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-AD-AR-20 | Installation of Doors & Access Systems | 6 | 2026-11-15 | 2026-11-21 |  |  | 0 | 0 | 250488.29 | 0% | 0% | 56 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-AD-AR-30 | Installation of Logo | 5 | 2026-11-22 | 2026-11-26 |  |  | 0 | 0 | 3236.4 | 0% | 0% | 40 | 0 | 0 | Yes | 1 | 0 | 0 | 1
MECHANICAL WORK |  | 16 | 2026-09-12 | 2026-09-30 |  |  | 667968.77 | 0 | 667968.77 | 100% | 0% | 160 | 160 | 0 |  | 3 | 0 | 0 | 3
PG-Q-CON-EX-AD-ME-10 | Installation of Main Air Package Units | 5 | 2026-09-12 | 2026-09-16 |  |  | 250488.29 | 0 | 250488.29 | 100% | 0% | 56 | 56 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-AD-ME-20 | Installation of Backup Air Package Unit | 5 | 2026-09-17 | 2026-09-22 |  |  | 208740.24 | 0 | 208740.24 | 100% | 0% | 56 | 56 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-AD-ME-30 | Installation of Complete HVAC System | 6 | 2026-09-24 | 2026-09-30 |  |  | 208740.24 | 0 | 208740.24 | 100% | 0% | 48 | 48 | 0 | Yes | 1 | 0 | 0 | 1
ELECTRICAL WORK |  | 60 | 2026-08-17 | 2026-10-26 | 2026-08-27 |  | 695800.8 | 2242-11-26 03:22 | 1085449.25 | 64.1% | 11.54% | 208 | 128 | 24 |  | 5 | 0 | 1 | 4
PG-Q-CON-EX-AD-EL-10 | Installation of Electrical Boxes & MDBs | 12 | 2026-08-17 | 2026-08-30 | 2026-08-27 |  | 208740.24 | 2242-11-26 03:22 | 208740.24 | 100% | 60% | 40 | 40 | 24 | Yes | 1 | 0 | 1 | 0
PG-Q-CON-EX-AD-EL-20 | Installation of Lighting System | 12 | 2026-08-31 | 2026-09-13 |  |  | 208740.24 | 0 | 208740.24 | 100% | 0% | 32 | 32 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-AD-EL-30 | Electrical Connections to Main Power Source (Excluding kWh Meter) | 5 | 2026-10-01 | 2026-10-06 |  |  | 208740.24 | 0 | 208740.24 | 100% | 0% | 40 | 40 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-AD-EL-40 | Installation of Backup Generator | 6 | 2026-10-07 | 2026-10-13 |  |  | 2090-07-01 01:55 | 0 | 208740.24 | 33.33% | 0% | 48 | 16 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-CON-EX-AD-EL-50 | Installation of Smart Dome System | 11 | 2026-10-14 | 2026-10-26 |  |  | 0 | 0 | 250488.29 | 0% | 0% | 48 | 0 | 0 | Yes | 1 | 0 | 0 | 1
TOILET BUILDING WORKS |  | 139 | 2026-05-06 | 2026-10-20 | 2026-05-06 |  | 248300 | 297906.77 | 324844.38 | 76.44% | 91.71% | 1708 | 1475 | 1526 |  | 38 | 30 | 7 | 1
CIVIL WORK |  | 138 | 2026-05-06 | 2026-10-19 | 2026-05-06 |  | 150709.46 | 207912.72 | 227117.58 | 66.36% | 91.54% | 1100 | 899 | 1008 |  | 24 | 19 | 4 | 1
STRUCTURAL WORK |  | 74 | 2026-05-06 | 2026-08-04 | 2026-05-06 | 2026-07-10 | 37980 | 37980 | 37980 | 100% | 100% | 372 | 372 | 372 |  | 7 | 7 | 0 | 0
PG-Q-CON-B-STR-10 | Excavation up to bottom of footing | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 1900.8 | 1900.8 | 1900.8 | 100% | 100% | 92 | 92 | 92 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-STR-20 | Anti-termite treatment and Polyethene Sheet | 2 | 2026-05-12 | 2026-05-13 | 2026-05-12 | 2026-05-13 | 3294 | 3294 | 3294 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-STR-30 | Backfilling with selected fill material (under footing) | 1 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 1900.8 | 1900.8 | 1900.8 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-STR-40 | Raft Foundation Work | 21 | 2026-05-13 | 2026-06-10 | 2026-05-13 | 2026-06-10 | 2534.4 | 2534.4 | 2534.4 | 100% | 100% | 64 | 64 | 64 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-STR-50 | Autoclaved aerated panel (walls) | 4 | 2026-07-25 | 2026-07-28 | 2026-07-08 | 2026-07-09 | 11340 | 11340 | 11340 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-STR-60 | Autoclaved aerated panel (ceiling) | 3 | 2026-07-29 | 2026-08-01 | 2026-07-09 | 2026-07-10 | 8505 | 8505 | 8505 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-STR-70 | Autoclaved aerated panel (parapet) | 3 | 2026-08-02 | 2026-08-04 | 2026-07-09 | 2026-07-10 | 8505 | 8505 | 8505 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
ARCHITECTURAL WORK |  | 64 | 2026-08-05 | 2026-10-19 | 2026-07-12 |  | 112729.46 | 169932.72 | 189137.58 | 59.6% | 89.85% | 728 | 527 | 636 |  | 17 | 12 | 4 | 1
GENERAL FINISHES |  | 64 | 2026-08-05 | 2026-10-19 | 2026-07-12 |  | 59414.61 | 77117.22 | 84120 | 70.63% | 91.68% | 376 | 296 | 347 |  | 8 | 6 | 2 | 0
PG-Q-CON-B-AR-GF-10 | Block Works | 6 | 2026-08-05 | 2026-08-11 | 2026-07-12 | 2026-07-16 | 2484 | 2484 | 2484 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-AR-GF-20 | Plaster | 7 | 2026-08-12 | 2026-08-19 | 2026-07-22 | 2026-08-05 | 4427.4 | 4427.4 | 4427.4 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-AR-GF-30 | False Ceiling Installation & Finishing | 7 | 2026-08-20 | 2026-08-27 | 2026-08-20 | 2026-09-10 | 1902-05-22 14:24 | 873.6 | 873.6 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-AR-GF-40 | Wall Paint | 12 | 2026-09-16 | 2026-09-30 | 2026-08-20 | 2026-09-06 | 1908-02-05 | 2958 | 2958 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-AR-GF-50 | Epoxy Flooring | 6 | 2026-10-01 | 2026-10-07 | 2026-08-20 | 2026-09-23 | 1900-09-29 14:24 | 1900-09-29 14:24 | 273.6 | 100% | 100% | 56 | 56 | 56 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-AR-GF-80 | Facade Finishing Work | 8 | 2026-10-01 | 2026-10-10 | 2026-08-20 | 2026-09-10 | 2025-03-27 06:00 | 2043-02-16 | 52278 | 87.5% | 100% | 48 | 42 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-AR-GF-60 | Install Doors & Windows | 5 | 2026-10-08 | 2026-10-13 | 2026-08-27 |  | 1907-04-07 18:14 | 9291.66 | 13273.8 | 20% | 70% | 32 | 6 | 22 | No | 1 | 0 | 1 | 0
PG-Q-CON-B-AR-GF-70 | Lockers and Furniture Installation | 5 | 2026-10-14 | 2026-10-19 | 46284 |  | 0 | 4530.96 | 7551.6 | 0% | 60% | 48 | 0 | 29 | Yes | 1 | 0 | 1 | 0
WET AREA FINISHES |  | 47 | 2026-08-20 | 2026-10-14 | 2026-08-06 |  | 2020-09-03 20:24 | 79515.3 | 81123.78 | 54.33% | 98.02% | 216 | 170 | 206 |  | 6 | 5 | 1 | 0
PG-Q-CON-B-AR-WF-10 | False Ceiling Installation & Finishing | 7 | 2026-08-20 | 2026-08-27 | 2026-08-27 | 2026-09-04 | 1907-12-07 | 2898 | 2898 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-AR-WF-20 | Wall Tiles and Partition Work | 6 | 2026-09-16 | 2026-09-22 | 2026-08-06 | 2026-08-14 | 1958-04-08 04:48 | 21283.2 | 21283.2 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-AR-WF-30 | Waterproofing on Floor | 6 | 2026-09-24 | 2026-09-30 | 2026-08-14 | 2026-09-07 | 1915-11-01 | 5784 | 5784 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-AR-WF-40 | Floor Tiles Works | 6 | 2026-10-01 | 2026-10-07 | 2026-08-14 | 2026-09-07 | 1917-10-06 | 1917-10-06 | 6489 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-AR-WF-50 | Toliet accessories Installation Works | 6 | 2026-10-08 | 2026-10-14 | 2026-08-27 | 2026-09-10 | 1917-12-07 07:55 | 2007-08-13 23:31 | 39307.98 | 16.67% | 100% | 24 | 4 | 24 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-AR-WF-60 | Install Doors | 5 | 2026-10-08 | 2026-10-13 | 46296 |  | 1902-12-07 07:41 | 3753.12 | 5361.6 | 20% | 70% | 32 | 6 | 22 | No | 1 | 0 | 1 | 0
ROOF FINISHES |  | 16 | 2026-10-01 | 2026-10-19 | 2026-08-20 |  | 1925-04-15 | 13300.2 | 23893.8 | 38.66% | 55.66% | 136 | 60 | 82 |  | 3 | 1 | 1 | 1
PG-Q-CON-B-AR-RF-10 | Waterproofing on Floor | 4 | 2026-10-01 | 2026-10-05 | 2026-08-20 | 2026-09-08 | 1911-05-20 | 4158 | 4158 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-AR-RF-20 | Epoxy Flooring and Finishes | 6 | 2026-10-06 | 2026-10-12 | 2026-08-20 |  | 1913-11-26 | 1925-01-10 04:48 | 10158 | 50% | 90% | 56 | 28 | 50 | No | 1 | 0 | 1 | 0
PG-Q-CON-B-AR-RF-30 | Steel ladder and Steel roof scupper Installation | 1 | 2026-10-19 | 2026-10-19 |  |  | 0 | 0 | 9577.8 | 0% | 0% | 48 | 0 | 0 | Yes | 1 | 0 | 0 | 1
MEP WORK |  | 108 | 2026-06-16 | 2026-10-20 | 2026-06-16 |  | 97590.54 | 89994.05 | 97726.8 | 99.86% | 92.09% | 608 | 576 | 518 |  | 14 | 11 | 3 | 0
MECANICAL WORKS |  | 108 | 2026-06-16 | 2026-10-20 | 2026-06-16 |  | 79343.22 | 71746.73 | 79479.48 | 99.83% | 90.27% | 400 | 368 | 310 |  | 9 | 6 | 3 | 0
FIRE FIGHTING SYSTEM |  | 1 | 2026-10-20 | 2026-10-20 | 46296 |  | 0 | 1900-02-08 21:07 | 1900-05-15 06:14 | 0% | 30% | 32 | 0 | 10 |  | 1 | 0 | 1 | 0
PG-Q-CON-B-GF-FF-10 | Fire Extinguisher Installation | 1 | 2026-10-20 | 2026-10-20 | 2026-10-01 |  | 0 | 40.88 | 136.26 | 0% | 30% | 32 | 0 | 10 | Yes | 1 | 0 | 1 | 0
SEWER AND DRAINAGE SYSTEM |  | 68 | 2026-06-16 | 2026-09-02 | 2026-06-16 |  | 11290.02 | 9032.02 | 11290.02 | 100% | 80% | 144 | 144 | 110 |  | 3 | 2 | 1 | 0
PG-Q-CON-B-GF-DR-10 | Sewer and Drainge System Main Lines Installation | 2 | 2026-06-16 | 2026-06-17 | 2026-06-16 | 2026-06-17 | 3225.72 | 3225.72 | 3225.72 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-GF-DR-20 | Sewer and Drainge System Pipes and fittings Installation | 2 | 2026-06-16 | 2026-06-17 | 2026-06-16 | 2026-06-17 | 4838.58 | 4838.58 | 4838.58 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-GF-DR-30 | Sanitaryware Installation (Final Fix) | 2 | 2026-09-01 | 2026-09-02 | 46296 |  | 1908-10-29 17:17 | 967.72 | 3225.72 | 100% | 30% | 48 | 48 | 14 | No | 1 | 0 | 1 | 0
HVAC SYSTEM |  | 10 | 2026-08-12 | 2026-08-23 | 2026-08-13 |  | 12127.2 | 6747.84 | 12127.2 | 100% | 55.64% | 96 | 96 | 62 |  | 2 | 1 | 1 | 0
PG-Q-CON-B-GF-AC-10 | Duct Work and Exhaust Fan Installation | 7 | 2026-08-12 | 2026-08-19 | 2026-08-13 | 2026-08-20 | 1912-02-28 09:36 | 1912-02-28 09:36 | 4442.4 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-GF-AC-20 | Split AC, Grills & Diffuser Installation | 3 | 2026-08-20 | 2026-08-23 | 2026-10-01 |  | 7684.8 | 2305.44 | 7684.8 | 100% | 30% | 48 | 48 | 14 | No | 1 | 0 | 1 | 0
WATER SUPPLY SYSTEM |  | 66 | 2026-06-16 | 2026-08-31 | 2026-06-16 | 2026-09-07 | 55926 | 55926 | 55926 | 100% | 100% | 128 | 128 | 128 |  | 3 | 3 | 0 | 0
PG-Q-CON-B-GF-WS-10 | Water Supply Main Lines Installation | 2 | 2026-06-16 | 2026-06-17 | 2026-06-16 | 2026-06-17 | 5702.4 | 5702.4 | 5702.4 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-GF-WS-20 | Water Supply Pipes Installation (Cold and Hot Water) | 2 | 2026-08-24 | 2026-08-25 | 2026-07-22 | 2026-07-31 | 1937-12-08 14:24 | 13857.6 | 13857.6 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-GF-WS-30 | Water Supply Accesories and Booster pump Installation | 3 | 2026-08-29 | 2026-08-31 | 2026-08-20 | 2026-09-07 | 1999-07-25 | 36366 | 36366 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
ELECTRICAL WORKS |  | 56 | 2026-07-13 | 2026-09-15 | 2026-07-22 | 2026-09-08 | 18247.32 | 18247.32 | 18247.32 | 100% | 100% | 208 | 208 | 208 |  | 5 | 5 | 0 | 0
PG-Q-CON-B-GF-EL-10 | Pipes & Conduits Installation | 8 | 2026-07-13 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 1983.6 | 1983.6 | 1983.6 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-GF-EL-50 | Electrical Light Fixtures Installation | 2 | 2026-09-03 | 2026-09-05 | 2026-08-20 | 2026-09-08 | 1920-02-01 12:29 | 7337.52 | 7337.52 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-GF-EL-30 | Fire Alarm Devices Installation | 3 | 2026-09-06 | 2026-09-08 | 2026-08-20 | 2026-09-08 | 1905-06-05 14:24 | 1983.6 | 1983.6 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-GF-EL-40 | Telecom & CCTV Devices Installation | 3 | 2026-09-09 | 2026-09-12 | 2026-08-20 | 2026-09-08 | 1913-07-29 | 4959 | 4959 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
PG-Q-CON-B-GF-EL-20 | Electrical & ELV Wiring Works | 3 | 2026-09-13 | 2026-09-15 | 2026-08-20 | 2026-09-08 | 1983.6 | 1983.6 | 1983.6 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PROJECT CLOSOUT |  | 174 | 2026-05-23 | 2026-12-16 | 2026-05-22 |  | 52612.62 | 324444.49 | 1753754 | 3% | 18.5% | 384 | 11 | 62 |  | 7 | 1 | 2 | 4
PG-Q-PCL-10 | Testing, Commessioning for All Systems(Completed) | 25 | 2026-05-23 | 2026-06-24 | 2026-05-22 | 2026-06-24 | 52612.62 | 52612.62 | 52612.62 | 100% | 100% | 11 | 11 | 11 | No | 1 | 1 | 0 | 0
PG-Q-PCL-20 | As-Built Drawings | 15 | 2026-11-15 | 2026-12-02 | 2026-09-23 |  | 0 | 35075.08 | 175375.4 | 0% | 20% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-Q-PCL-10_R | Testing, Commessioning for All Systems(Remaining) | 11 | 2026-11-15 | 2026-11-26 | 46240 |  | 0 | 236756.79 | 473513.58 | 0% | 50% | 101 | 0 | 50 | Yes | 1 | 0 | 1 | 0
PG-Q-PCL-30 | Snag list Submission | 3 | 2026-11-28 | 2026-11-30 |  |  | 0 | 0 | 350750.8 | 0% | 0% | 136 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-PCL-40 | Snag list Closeout | 10 | 2026-12-01 | 2026-12-12 |  |  | 0 | 0 | 350750.8 | 0% | 0% | 136 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-PCL-50 | Issuing Approvals | 3 | 2026-12-13 | 2026-12-15 |  |  | 0 | 0 | 175375.4 | 0% | 0% | 0 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-Q-PCL-60 | Handing Over | 1 | 2026-12-16 | 2026-12-16 |  |  | 0 | 0 | 175375.4 | 0% | 0% | 0 | 0 | 0 | Yes | 1 | 0 | 0 | 1
HAIL |  | 249 | 2026-02-17 | 2026-12-16 | 2026-02-17 |  | 5566215.15 | 5267934.8 | 6814652 | 81.68% | 77.3% | 6348 | 5198 | 4187 |  | 581 | 479 | 61 | 41
MOBILIZATION |  | 29 | 2026-02-17 | 2026-03-29 | 2026-02-17 | 2026-03-28 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 9 | 9 | 0 | 0
TEMPORARY CAMP |  | 28 | 2026-02-17 | 2026-03-28 | 2026-02-17 | 2026-03-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-MOB-CAM-10 | Temporary Underground Utilities works | 28 | 2026-02-17 | 2026-03-28 | 2026-02-17 | 2026-03-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-MOB-CAM-20 | Temporary Porta-Cabins | 21 | 2026-02-26 | 2026-03-28 | 2026-02-26 | 2026-03-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-MOB-CAM-30 | Temporary Toilets | 21 | 2026-02-26 | 2026-03-28 | 2026-02-26 | 2026-03-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-MOB-CAM-40 | Temporary Mosque | 13 | 2026-03-08 | 2026-03-28 | 2026-03-08 | 2026-03-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SITE OFFICES |  | 29 | 2026-02-17 | 2026-03-29 | 2026-02-17 | 2026-03-28 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-H-MOB-SO-10 | Temporary Underground Utilities works | 29 | 2026-02-17 | 2026-03-29 | 2026-02-17 | 2026-03-28 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-MOB-SO-20 | Temporary Porta-Cabins | 23 | 2026-02-25 | 2026-03-29 | 2026-02-25 | 2026-03-28 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-MOB-SO-30 | Temporary Toilets | 23 | 2026-02-25 | 2026-03-29 | 2026-02-25 | 2026-03-28 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-MOB-SO-40 | Temporary Mosque | 17 | 2026-03-04 | 2026-03-29 | 2026-03-04 | 2026-03-28 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-MOB-SO-50 | Car Parking Area | 10 | 2026-03-12 | 2026-03-29 | 2026-03-12 | 2026-03-28 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
GENERAL REQUIEREMENTS |  | 51 | 2026-02-17 | 2026-04-23 | 2026-02-17 | 2026-04-22 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-GEN-20 | HSSE Submission Plan | 51 | 2026-02-17 | 2026-04-23 | 2026-02-17 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-GEN-30 | Surveying report Submission Plan | 51 | 2026-02-17 | 2026-04-23 | 2026-02-17 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-GEN-40 | Baseline Submission | 6 | 2026-02-28 | 2026-03-07 | 2026-02-28 | 2026-03-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-GEN-10 | QA/QC Submission Plan | 16 | 2026-03-12 | 2026-04-05 | 2026-03-12 | 2026-04-04 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ENGINEERING |  | 118 | 2026-02-17 | 2026-07-14 | 2026-02-17 | 2026-09-17 | 204439.56 | 204439.56 | 204439.56 | 100% | 100% | 0 | 0 | 0 |  | 230 | 230 | 0 | 0
SHOP DRAWINGS SUBMITTALS |  | 93 | 2026-02-17 | 2026-06-16 | 2026-02-17 | 2026-06-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 48 | 48 | 0 | 0
STRUCTURAL DRAWINGS |  | 61 | 2026-02-17 | 2026-05-05 | 2026-02-17 | 2026-05-04 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 8 | 8 | 0 | 0
PROJECT FENCE |  | 57 | 2026-02-17 | 2026-04-30 | 2026-02-17 | 2026-04-29 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-EN-ST-SD-SB-10 | Excavation Drawings | 57 | 2026-02-17 | 2026-04-30 | 2026-02-17 | 2026-04-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ST-SD-SB-20 | Foundation Drawings | 55 | 2026-02-19 | 2026-04-30 | 2026-02-19 | 2026-04-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
TOILET BUILDING |  | 41 | 2026-02-19 | 2026-04-14 | 2026-02-19 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-EN-ST-SD-SB-30 | Excavation Drawings | 41 | 2026-02-19 | 2026-04-14 | 2026-02-19 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ST-SD-SB-40 | Foundation Drawings | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
WATER STORAGE TANK |  | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-EN-ST-SD-SB-60 | Excavation Drawings | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ST-SD-SB-50 | Foundation Drawings | 37 | 2026-02-25 | 2026-04-14 | 2026-02-25 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SEPTIC TANK |  | 55 | 2026-02-25 | 2026-05-05 | 2026-02-25 | 2026-05-04 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-EN-ST-SD-SB-70 | Reinforcement Detail Drawings | 55 | 2026-02-25 | 2026-05-05 | 2026-02-25 | 2026-05-04 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ST-SD-SB-80 | Concrete Detail Drawings | 52 | 2026-03-01 | 2026-05-05 | 2026-03-01 | 2026-05-04 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL DRAWINGS |  | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 10 | 0 | 0
TOILET BUILDING |  | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 10 | 0 | 0
PG-H-EN-AR-SD-SB-10 | Ground Floor Plan | 36 | 2026-02-23 | 2026-04-11 | 2026-02-23 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-SB-20 | Roof Floor Plan | 35 | 2026-02-28 | 2026-04-14 | 2026-02-28 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-SB-50 | Floor Finish Layout | 32 | 2026-02-28 | 2026-04-09 | 2026-02-28 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-SB-60 | Reflected Ceiling Layout | 32 | 2026-02-28 | 2026-04-11 | 2026-02-28 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-SB-70 | Enlarged Toilets Layout | 35 | 2026-02-28 | 2026-04-14 | 2026-02-28 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-SB-30 | Elevations | 29 | 2026-03-03 | 2026-04-11 | 2026-03-03 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-SB-80 | Doors & Windows Schedule | 32 | 2026-03-03 | 2026-04-14 | 2026-03-03 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-SB-90 | Aluminum Work | 32 | 2026-03-03 | 2026-04-14 | 2026-03-03 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-SB-100 | Cladding Details | 32 | 2026-03-03 | 2026-04-14 | 2026-03-03 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-SB-40 | Sections | 27 | 2026-03-05 | 2026-04-11 | 2026-03-05 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
LANDSCAPE DRAWINGS |  | 38 | 2026-02-24 | 2026-04-14 | 2026-02-24 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 10 | 0 | 0
PG-H-EN-LS-SD-SB-10 | Hardscape Layout Plan | 38 | 2026-02-24 | 2026-04-14 | 2026-02-24 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-SB-20 | Interlock Tile Details | 35 | 2026-02-24 | 2026-04-11 | 2026-02-24 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-SB-30 | Stamped Concrete Pattern & Section | 38 | 2026-02-24 | 2026-04-14 | 2026-02-24 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-SB-40 | Tartan Flooring Layout & Details | 38 | 2026-02-24 | 2026-04-14 | 2026-02-24 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-SB-50 | Bike Path Layout & Details | 35 | 2026-02-24 | 2026-04-11 | 2026-02-24 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-SB-60 | Walking Path layout & Details | 35 | 2026-02-24 | 2026-04-11 | 2026-02-24 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-SB-70 | Tree Planting Plan & Details | 35 | 2026-02-24 | 2026-04-11 | 2026-02-24 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-SB-80 | Traffic Sign Location & Details | 38 | 2026-02-24 | 2026-04-14 | 2026-02-24 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-SB-90 | Football Playground Layout | 38 | 2026-02-24 | 2026-04-14 | 2026-02-24 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-SB-100 | Playground Details | 35 | 2026-02-24 | 2026-04-11 | 2026-02-24 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MECHANICAL DRAWINGS |  | 52 | 2026-03-01 | 2026-05-05 | 2026-03-01 | 2026-05-04 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 9 | 9 | 0 | 0
WATER SUPPLY SYSTEM |  | 31 | 2026-03-01 | 2026-04-11 | 2026-03-01 | 2026-04-09 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-EN-ME-SD-SB-20 | Pump Room Layout | 31 | 2026-03-01 | 2026-04-11 | 2026-03-01 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ME-SD-SB-10 | Cold & Hot Water Piping Layout | 27 | 2026-03-05 | 2026-04-11 | 2026-03-05 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ME-SD-SB-30 | Booster Pump Details | 27 | 2026-03-05 | 2026-04-11 | 2026-03-05 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ME-SD-SB-40 | GRP Water Tank Details | 23 | 2026-03-10 | 2026-04-11 | 2026-03-10 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SEWER AND DRAINAGE SYSTEM |  | 27 | 2026-03-05 | 2026-04-11 | 2026-03-05 | 2026-04-09 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-EN-ME-SD-SB-50 | Drainage Layout | 27 | 2026-03-05 | 2026-04-11 | 2026-03-05 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ME-SD-SB-60 | Floor Drains & Cleanouts Details | 23 | 2026-03-10 | 2026-04-11 | 2026-03-10 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ME-SD-SB-70 | Inspection Chamber Details | 20 | 2026-03-14 | 2026-04-11 | 2026-03-14 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION SYSTEM |  | 44 | 2026-03-10 | 2026-05-05 | 2026-03-10 | 2026-05-04 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-EN-ME-SD-SB-80 | HDPE Pipe Routing | 44 | 2026-03-10 | 2026-05-05 | 2026-03-10 | 2026-05-04 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ME-SD-SB-90 | Irrigation Network Layout | 41 | 2026-03-14 | 2026-05-05 | 2026-03-14 | 2026-05-04 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL DRAWINGS |  | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 11 | 11 | 0 | 0
POWER AND LIGHTING SYSTEM |  | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-EN-EL-SD-SB-10 | Main Distribution Board (MDB) Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-SB-20 | Pump Room Power Panel | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-SB-30 | Street Lighting Power Panel | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-SB-40 | Site Lighting Pole Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELV SYSTEM |  | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-EN-EL-SD-SB-50 | Telecom & Data Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-SB-60 | CCTV Camera Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-SB-70 | Access Control Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-SB-80 | AV System Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE ALARM SYSTEM |  | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-EN-EL-SD-SB-90 | Fire Alarm Layout | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-SB-100 | Detector & Manual Call Point Details | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-SB-110 | Control Panel Wiring Diagram | 27 | 2026-05-11 | 2026-06-16 | 2026-05-11 | 2026-06-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SHOP DRAWINGS APPROVALS |  | 92 | 2026-02-19 | 2026-06-17 | 2026-02-19 | 2026-06-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 48 | 48 | 0 | 0
STRUCTURAL DRAWINGS |  | 61 | 2026-02-19 | 2026-05-07 | 2026-02-19 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 8 | 8 | 0 | 0
PROJECT FENCE |  | 55 | 2026-02-19 | 2026-04-30 | 2026-02-19 | 2026-04-29 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-EN-ST-SD-AP-10 | Excavation Drawings | 55 | 2026-02-19 | 2026-04-30 | 2026-02-19 | 2026-04-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ST-SD-AP-20 | Foundation Drawings | 52 | 2026-02-24 | 2026-04-30 | 2026-02-24 | 2026-04-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
TOILET BUILDING |  | 42 | 2026-02-23 | 2026-04-18 | 2026-02-23 | 2026-04-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-EN-ST-SD-AP-30 | Excavation Drawings | 42 | 2026-02-23 | 2026-04-18 | 2026-02-23 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ST-SD-AP-40 | Foundation Drawings | 39 | 2026-02-26 | 2026-04-18 | 2026-02-26 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
WATER STORAGE TANK |  | 40 | 2026-02-25 | 2026-04-18 | 2026-02-25 | 2026-04-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-EN-ST-SD-AP-50 | Excavation Drawings | 40 | 2026-02-25 | 2026-04-18 | 2026-02-25 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ST-SD-AP-60 | Foundation Drawings | 37 | 2026-03-01 | 2026-04-18 | 2026-03-01 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SEPTIC TANK |  | 54 | 2026-03-01 | 2026-05-07 | 2026-03-01 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-EN-ST-SD-AP-70 | Reinforcement Detail Drawings | 54 | 2026-03-01 | 2026-05-07 | 2026-03-01 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ST-SD-AP-80 | Concrete Detail Drawings | 51 | 2026-03-04 | 2026-05-07 | 2026-03-04 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL DRAWINGS |  | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 10 | 0 | 0
TOILET BUILDING |  | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 10 | 0 | 0
PG-H-EN-AR-SD-AP-10 | Ground Floor Plan | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-AP-20 | Roof Floor Plan | 35 | 2026-03-03 | 2026-04-18 | 2026-03-03 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-AP-50 | Floor Finish Layout | 33 | 2026-03-05 | 2026-04-18 | 2026-03-05 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-AP-60 | Reflected Ceiling Layout | 33 | 2026-03-05 | 2026-04-18 | 2026-03-05 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-AP-70 | Enlarged Toilets Layout | 33 | 2026-03-05 | 2026-04-18 | 2026-03-05 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-AP-30 | Elevations | 32 | 2026-03-07 | 2026-04-18 | 2026-03-07 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-AP-80 | Doors & Windows Schedule | 32 | 2026-03-07 | 2026-04-18 | 2026-03-07 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-AP-90 | Aluminum Work | 31 | 2026-03-08 | 2026-04-18 | 2026-03-08 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-AP-100 | Cladding Details | 31 | 2026-03-08 | 2026-04-18 | 2026-03-08 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-AR-SD-AP-40 | Sections | 29 | 2026-03-10 | 2026-04-18 | 2026-03-10 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
LANDSCAPE DRAWINGS |  | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 10 | 0 | 0
PG-H-EN-LS-SD-AP-50 | Bike Path Layout & Details | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-AP-60 | Walking Path layout & Details | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-AP-80 | Traffic Sign Location & Details | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-AP-10 | Hardscape Layout Plan | 37 | 2026-03-01 | 2026-04-18 | 2026-03-01 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-AP-40 | Tartan Flooring Layout & Details | 37 | 2026-03-01 | 2026-04-18 | 2026-03-01 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-AP-70 | Tree Planting Plan & Details | 37 | 2026-03-01 | 2026-04-18 | 2026-03-01 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-AP-90 | Football Playground Layout | 37 | 2026-03-01 | 2026-04-18 | 2026-03-01 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-AP-100 | Playground Details | 37 | 2026-03-01 | 2026-04-18 | 2026-03-01 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-AP-20 | Interlock Tile Details | 29 | 2026-03-10 | 2026-04-18 | 2026-03-10 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-LS-SD-AP-30 | Stamped Concrete Pattern & Section | 23 | 2026-03-17 | 2026-04-18 | 2026-03-17 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MECHANICAL DRAWINGS |  | 46 | 2026-03-10 | 2026-05-07 | 2026-03-10 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 9 | 9 | 0 | 0
WATER SUPPLY SYSTEM |  | 26 | 2026-03-10 | 2026-04-14 | 2026-03-10 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-EN-ME-SD-AP-10 | Cold & Hot Water Piping Layout | 26 | 2026-03-10 | 2026-04-14 | 2026-03-10 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ME-SD-AP-30 | Booster Pump Details | 25 | 2026-03-11 | 2026-04-14 | 2026-03-11 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ME-SD-AP-40 | GRP Water Tank Details | 22 | 2026-03-15 | 2026-04-14 | 2026-03-15 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ME-SD-AP-20 | Pump Room Layout | 20 | 2026-03-17 | 2026-04-14 | 2026-03-17 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SEWER AND DRAINAGE SYSTEM |  | 26 | 2026-03-10 | 2026-04-14 | 2026-03-10 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-EN-ME-SD-AP-50 | Drainage Layout | 26 | 2026-03-10 | 2026-04-14 | 2026-03-10 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ME-SD-AP-60 | Floor Drains & Cleanouts Details | 20 | 2026-03-17 | 2026-04-14 | 2026-03-17 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ME-SD-AP-70 | Inspection Chamber Details | 20 | 2026-03-17 | 2026-04-14 | 2026-03-17 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION SYSTEM |  | 43 | 2026-03-14 | 2026-05-07 | 2026-03-14 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-EN-ME-SD-AP-80 | HDPE Pipe Routing | 43 | 2026-03-14 | 2026-05-07 | 2026-03-14 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-ME-SD-AP-90 | Irrigation Network Layout | 39 | 2026-03-18 | 2026-05-07 | 2026-03-18 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL DRAWINGS |  | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 11 | 11 | 0 | 0
POWER AND LIGHTING SYSTEM |  | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-EN-EL-SD-AP-10 | Main Distribution Board (MDB) Layout | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-AP-20 | Pump Room Power Panel | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-AP-30 | Street Lighting Power Panel | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-AP-40 | Site Lighting Pole Layout | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELV SYSTEM |  | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-EN-EL-SD-AP-50 | Telecom & Data Layout | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-AP-60 | CCTV Camera Layout | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-AP-70 | Access Control Layout | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-AP-80 | AV System Layout | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE ALARM SYSTEM |  | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-EN-EL-SD-AP-90 | Fire Alarm Layout | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-AP-100 | Detector & Manual Call Point Details | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-EN-EL-SD-AP-110 | Control Panel Wiring Diagram | 27 | 2026-05-12 | 2026-06-17 | 2026-05-12 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MATERIAL SUBMITTALS |  | 111 | 2026-02-17 | 2026-07-06 | 2026-02-17 | 2026-09-01 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 67 | 67 | 0 | 0
LONG LEAD ITEMS |  | 108 | 2026-02-21 | 2026-07-06 | 2026-02-21 | 2026-09-01 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 28 | 28 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 56 | 2026-02-25 | 2026-05-06 | 2026-02-25 | 2026-05-05 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-PR-LL-LS-MS-20 | Benches, Seats (Rectangular & Circular) | 56 | 2026-02-25 | 2026-05-06 | 2026-02-25 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-MS-30 | Fence, gates and accessories | 56 | 2026-02-25 | 2026-05-06 | 2026-02-25 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-MS-10 | Bike and Walk Path Materials | 48 | 2026-03-07 | 2026-05-06 | 2026-03-07 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 47 | 2026-03-08 | 2026-05-06 | 2026-03-08 | 2026-05-05 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-SP-MS-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc) | 47 | 2026-03-08 | 2026-05-06 | 2026-03-08 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-SP-MS-20 | Tartan Floor | 47 | 2026-03-08 | 2026-05-06 | 2026-03-08 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 41 | 2026-03-07 | 2026-04-28 | 2026-03-07 | 2026-04-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-H-PR-LL-CO-MS-10 | Autoclaved Aerated Panel | 41 | 2026-03-07 | 2026-04-28 | 2026-03-07 | 2026-04-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 44 | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-05 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-MT-MS-10 | Metal Doors | 44 | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-MT-MS-20 | Curtain Wall | 44 | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 44 | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-05 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-PB-MS-10 | Booster Pump | 44 | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-PB-MS-20 | GRP Sectional Panel Water Tanks (4x3x3m) | 40 | 2026-03-16 | 2026-05-06 | 2026-03-16 | 2026-05-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 60 | 2026-02-21 | 2026-05-07 | 2026-02-21 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-IR-MS-10 | HDPE Pipes | 60 | 2026-02-21 | 2026-05-07 | 2026-02-21 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-IR-MS-20 | Irrigation Control System | 60 | 2026-02-21 | 2026-05-07 | 2026-02-21 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 44 | 2026-05-12 | 2026-07-06 | 2026-05-12 | 2026-09-01 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 16 | 16 | 0 | 0
PG-H-PR-LL-EL-MS-10 | Main Distribution Board(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-20 | Power Panels (Pump, Street Light)(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-30 | Site Lighting Poles(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-40 | Lighting Fixtures(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-70 | Security and Access Control System Materials(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-80 | Fire Alarm System Materials(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-10_R | Main Distribution Board(Remaining) | 8 | 2026-06-25 | 2026-07-04 | 2026-07-11 | 2026-08-03 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-20_R | Power Panels (Pump, Street Light)(Remaining) | 8 | 2026-06-25 | 2026-07-04 | 2026-07-11 | 2026-08-03 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-30_R | Site Lighting Poles(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-11 | 2026-08-03 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-40_R | Lighting Fixtures(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-11 | 2026-07-23 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-11 | 2026-09-01 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-11 | 2026-09-01 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-70_R | Security and Access Control System Materials(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-11 | 2026-09-01 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MS-80_R | Fire Alarm System Materials(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-08-27 | 2026-09-01 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SHORT LEAD ITEMS |  | 28 | 2026-02-17 | 2026-03-28 | 2026-02-17 | 2026-03-26 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 39 | 39 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 23 | 2026-02-17 | 2026-03-17 | 2026-02-17 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 8 | 8 | 0 | 0
PG-H-PR-SL-LS-MS-10 | Backfilling Materials | 23 | 2026-02-17 | 2026-03-17 | 2026-02-17 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MS-30 | Compacted Natural Ground Soil | 20 | 2026-02-21 | 2026-03-17 | 2026-02-21 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MS-60 | Traffic Signages | 8 | 2026-03-08 | 2026-03-17 | 2026-03-08 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MS-20 | Interlock tiles | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MS-40 | Curb Stone | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MS-50 | Thermoplastic pavement road marking | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MS-70 | Trees | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MS-80 | Lawn | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 28 | 2026-02-17 | 2026-03-28 | 2026-02-17 | 2026-03-26 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-H-PR-SL-CO-MS-10 | Steel Rebar | 17 | 2026-02-17 | 2026-03-10 | 2026-02-17 | 2026-03-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-MS-20 | Concrete | 13 | 2026-02-23 | 2026-03-10 | 2026-02-23 | 2026-03-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-MS-40 | CMU Block | 19 | 2026-03-01 | 2026-03-28 | 2026-03-01 | 2026-03-26 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-MS-50 | Concrete Repair & Protection Materials | 19 | 2026-03-01 | 2026-03-28 | 2026-03-01 | 2026-03-26 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-MS-30 | Screed | 10 | 2026-03-11 | 2026-03-28 | 2026-03-11 | 2026-03-26 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL & FINISHES WORK |  | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PG-H-PR-SL-AR-MS-10 | Ceramic tiles | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MS-20 | Anti-slip Granite tiles | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MS-30 | Epoxy Paint | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MS-40 | Cement Plaster | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MS-50 | Acrylic Paint | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MS-60 | Stone Cladding | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MS-70 | Aluminum Plates | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MS-80 | Phenolic Partition | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MS-90 | Glass Partition | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MS-100 | Gypsum Boards | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MS-110 | Specialities Materials (Toilet accessories, lockers, logo, etc) | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MS-120 | Waterproofing System Materials | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 9 | 2026-03-07 | 2026-03-17 | 2026-03-07 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-PR-SL-MT-MS-20 | Galvanized Steel Roof Scupper | 9 | 2026-03-07 | 2026-03-17 | 2026-03-07 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-MT-MS-30 | Galvanized Steel Cover with frame | 9 | 2026-03-07 | 2026-03-17 | 2026-03-07 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-MT-MS-10 | Galvanized Steel Ladder | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
HVAC WORK |  | 19 | 2026-02-23 | 2026-03-17 | 2026-02-23 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-PR-SL-AC-MS-10 | Split Air Conditioning Unit | 19 | 2026-02-23 | 2026-03-17 | 2026-02-23 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AC-MS-20 | Air Duct | 15 | 2026-02-28 | 2026-03-17 | 2026-02-28 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AC-MS-30 | Diffusers and Grills | 11 | 2026-03-04 | 2026-03-17 | 2026-03-04 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AC-MS-40 | Exhaust fans | 11 | 2026-03-04 | 2026-03-17 | 2026-03-04 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-PR-SL-PB-MS-10 | PPR Pipes & Valves | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-PB-MS-20 | UPCV Pipes | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-PB-MS-30 | Sanitary Drainage Fixtures | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-SL-IR-MS-10 | Gate Valve including valve box | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-IR-MS-20 | Bulbblers and Spreyers | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-H-PR-SL-EL-MS-10 | Wiring Devices Materials | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE FIGHTING WORK |  | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-H-PR-SL-FF-MS-10 | Fire Extinguishers | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MATERIAL APPROVALS |  | 115 | 2026-02-21 | 2026-07-14 | 2026-02-21 | 2026-09-17 | 204439.56 | 204439.56 | 204439.56 | 100% | 100% | 0 | 0 | 0 |  | 67 | 67 | 0 | 0
LONG LEAD ITEMS |  | 112 | 2026-02-25 | 2026-07-14 | 2026-02-25 | 2026-09-17 | 111065.49 | 111065.49 | 111065.49 | 100% | 100% | 0 | 0 | 0 |  | 28 | 28 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 57 | 2026-02-25 | 2026-05-06 | 2026-02-25 | 2026-05-06 | 26079.63 | 26079.63 | 26079.63 | 100% | 100% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-PR-LL-LS-MA-20 | Benches, Seats (Rectangular & Circular) | 57 | 2026-02-25 | 2026-05-06 | 2026-02-25 | 2026-05-06 | 6327.69 | 6327.69 | 6327.69 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-MA-30 | Fence, gates and accessories | 51 | 2026-03-04 | 2026-05-06 | 2026-03-04 | 2026-05-06 | 3290.94 | 3290.94 | 3290.94 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-MA-10 | Bike and Walk Path Materials | 41 | 2026-03-16 | 2026-05-06 | 2026-03-16 | 2026-05-06 | 16461 | 16461 | 16461 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 43 | 2026-03-14 | 2026-05-06 | 2026-03-14 | 2026-05-06 | 38839.5 | 38839.5 | 38839.5 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-SP-MA-20 | Tartan Floor | 43 | 2026-03-14 | 2026-05-06 | 2026-03-14 | 2026-05-06 | 24570 | 24570 | 24570 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-SP-MA-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc) | 42 | 2026-03-15 | 2026-05-06 | 2026-03-15 | 2026-05-06 | 14269.5 | 14269.5 | 14269.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 45 | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-06 | 1417.5 | 1417.5 | 1417.5 | 100% | 100% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-H-PR-LL-CO-MA-10 | Autoclaved Aerated Panel | 45 | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-06 | 1417.5 | 1417.5 | 1417.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 42 | 2026-03-15 | 2026-05-06 | 2026-03-15 | 2026-05-06 | 1902-06-07 05:31 | 889.23 | 889.23 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-MT-MA-10 | Metal Doors | 42 | 2026-03-15 | 2026-05-06 | 2026-03-15 | 2026-05-06 | 1900-05-06 12:43 | 127.53 | 127.53 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-MT-MA-20 | Curtain Wall | 42 | 2026-03-15 | 2026-05-06 | 2026-03-15 | 2026-05-06 | 761.7 | 761.7 | 761.7 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 41 | 2026-03-16 | 2026-05-06 | 2026-03-16 | 2026-05-06 | 3553.95 | 3553.95 | 3553.95 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-PB-MA-10 | Booster Pump | 41 | 2026-03-16 | 2026-05-06 | 2026-03-16 | 2026-05-06 | 1818.3 | 1818.3 | 1818.3 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-PB-MA-20 | GRP Sectional Panel Water Tanks (4x3x3m) | 38 | 2026-03-24 | 2026-05-06 | 2026-03-24 | 2026-05-06 | 1735.65 | 1735.65 | 1735.65 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 55 | 2026-02-28 | 2026-05-06 | 2026-02-28 | 2026-05-06 | 12818.25 | 12818.25 | 12818.25 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-IR-MA-10 | HDPE Pipes | 55 | 2026-02-28 | 2026-05-06 | 2026-02-28 | 2026-05-06 | 8272.5 | 8272.5 | 8272.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-IR-MA-20 | Irrigation Control System | 55 | 2026-02-28 | 2026-05-06 | 2026-02-28 | 2026-05-06 | 4545.75 | 4545.75 | 4545.75 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 51 | 2026-05-12 | 2026-07-14 | 2026-05-12 | 2026-09-17 | 27467.43 | 27467.43 | 27467.43 | 100% | 100% | 0 | 0 | 0 |  | 16 | 16 | 0 | 0
PG-H-PR-LL-EL-MA-10 | Main Distribution Board(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 1900-12-12 03:07 | 347.13 | 1900-12-12 03:07 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-20 | Power Panels (Pump, Street Light)(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 1900-10-03 16:48 | 277.7 | 277.7 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-30 | Site Lighting Poles(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 1940-10-07 04:19 | 14891.18 | 1940-10-07 04:19 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-40 | Lighting Fixtures(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 897.98 | 897.98 | 897.98 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 702.93 | 702.93 | 702.93 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 685.57 | 685.57 | 685.57 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-70 | Security and Access Control System Materials(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 867.93 | 867.93 | 867.93 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-80 | Fire Alarm System Materials(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 1901-07-09 18:29 | 556.77 | 556.77 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-10_R | Main Distribution Board(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-30 | 2026-09-17 | 1900-05-27 18:29 | 1900-05-27 18:29 | 1900-05-27 18:29 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-20_R | Power Panels (Pump, Street Light)(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-30 | 2026-09-17 | 119.02 | 119.02 | 119.02 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-30_R | Site Lighting Poles(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-30 | 2026-09-17 | 1917-06-20 22:34 | 1917-06-20 22:34 | 1917-06-20 22:34 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-40_R | Lighting Fixtures(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-23 | 2026-07-23 | 1901-01-18 20:24 | 384.85 | 384.85 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-08-27 | 2026-09-17 | 1900-10-19 19:26 | 1900-10-19 19:26 | 1900-10-19 19:26 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-70_R | Security and Access Control System Materials(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-08-27 | 2026-09-17 | 371.97 | 371.97 | 371.97 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-80_R | Fire Alarm System Materials(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-08-27 | 2026-09-17 | 1900-08-25 14:53 | 1900-08-25 14:53 | 1900-08-25 14:53 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MA-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 10 | 2026-07-04 | 2026-07-14 | 2026-08-27 | 2026-09-17 | 301.26 | 301.26 | 301.26 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SHORT LEAD ITEMS |  | 25 | 2026-02-21 | 2026-03-26 | 2026-02-21 | 2026-03-26 | 93374.07 | 93374.07 | 93374.07 | 100% | 100% | 0 | 0 | 0 |  | 39 | 39 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 25 | 2026-02-21 | 2026-03-26 | 2026-02-21 | 2026-03-26 | 72133.44 | 72133.44 | 72133.44 | 100% | 100% | 0 | 0 | 0 |  | 8 | 8 | 0 | 0
PG-H-PR-SL-LS-MA-10 | Backfilling Materials | 25 | 2026-02-21 | 2026-03-26 | 2026-02-21 | 2026-03-26 | 19575 | 19575 | 19575 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MA-30 | Compacted Natural Ground Soil | 22 | 2026-02-25 | 2026-03-26 | 2026-02-25 | 2026-03-26 | 3120 | 3120 | 3120 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MA-60 | Traffic Signages | 10 | 2026-03-11 | 2026-03-26 | 2026-03-11 | 2026-03-26 | 198.36 | 198.36 | 198.36 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MA-70 | Trees | 7 | 2026-03-15 | 2026-03-26 | 2026-03-15 | 2026-03-26 | 1913-03-23 22:48 | 4831.95 | 4831.95 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MA-80 | Lawn | 7 | 2026-03-15 | 2026-03-26 | 2026-03-15 | 2026-03-26 | 5460 | 5460 | 5460 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MA-20 | Interlock tiles | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 17494.5 | 17494.5 | 17494.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MA-40 | Curb Stone | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 20928 | 20928 | 20928 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-MA-50 | Thermoplastic pavement road marking | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 525.63 | 525.63 | 525.63 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 24 | 2026-02-23 | 2026-03-26 | 2026-02-23 | 2026-03-26 | 1609.47 | 1609.47 | 1609.47 | 100% | 100% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-H-PR-SL-CO-MA-10 | Steel Rebar | 14 | 2026-02-23 | 2026-03-10 | 2026-02-23 | 2026-03-10 | 1901-04-20 19:41 | 476.82 | 476.82 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-MA-20 | Concrete | 9 | 2026-03-01 | 2026-03-10 | 2026-03-01 | 2026-03-10 | 1901-06-01 20:24 | 518.85 | 518.85 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-MA-40 | CMU Block | 15 | 2026-03-05 | 2026-03-26 | 2026-03-05 | 2026-03-26 | 1900-05-03 04:48 | 124.2 | 124.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-MA-50 | Concrete Repair & Protection Materials | 15 | 2026-03-05 | 2026-03-26 | 2026-03-05 | 2026-03-26 | 1901-01-06 | 372 | 372 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-MA-30 | Screed | 1 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 117.6 | 117.6 | 117.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL & FINISHES WORK |  | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 8114.01 | 8114.01 | 8114.01 | 100% | 100% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PG-H-PR-SL-AR-MA-10 | Ceramic tiles | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1901-07-24 22:48 | 571.95 | 571.95 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MA-20 | Anti-slip Granite tiles | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 535.5 | 535.5 | 535.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MA-30 | Epoxy Paint | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1900-04-20 04:19 | 111.18 | 111.18 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MA-40 | Cement Plaster | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1900-08-08 08:53 | 221.37 | 221.37 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MA-50 | Acrylic Paint | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 147.9 | 147.9 | 147.9 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MA-60 | Stone Cladding | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1905-01-25 04:48 | 1852.2 | 1852.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MA-70 | Aluminum Plates | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 182.46 | 182.46 | 182.46 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MA-80 | Phenolic Partition | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1340.4 | 1340.4 | 1340.4 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MA-90 | Glass Partition | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1900-06-03 09:36 | 155.4 | 155.4 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MA-100 | Gypsum Boards | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 188.58 | 188.58 | 188.58 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MA-110 | Specialities Materials (Toilet accessories, lockers, logo, etc) | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1906-03-11 20:53 | 2262.87 | 2262.87 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-MA-120 | Waterproofing System Materials | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1901-06-27 04:48 | 544.2 | 544.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 10 | 2026-03-11 | 2026-03-26 | 2026-03-11 | 2026-03-26 | 1901-04-22 21:22 | 478.89 | 478.89 | 100% | 100% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-PR-SL-MT-MA-20 | Galvanized Steel Roof Scupper | 10 | 2026-03-11 | 2026-03-26 | 2026-03-11 | 2026-03-26 | 1900-01-30 07:41 | 31.32 | 31.32 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-MT-MA-30 | Galvanized Steel Cover with frame | 10 | 2026-03-11 | 2026-03-26 | 2026-03-11 | 2026-03-26 | 1900-03-25 17:02 | 85.71 | 85.71 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-MT-MA-10 | Galvanized Steel Ladder | 7 | 2026-03-15 | 2026-03-26 | 2026-03-15 | 2026-03-26 | 1900-12-26 20:38 | 361.86 | 361.86 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
HVAC WORK |  | 20 | 2026-02-28 | 2026-03-26 | 2026-02-28 | 2026-03-26 | 1901-08-28 08:38 | 606.36 | 606.36 | 100% | 100% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-PR-SL-AC-MA-10 | Split Air Conditioning Unit | 20 | 2026-02-28 | 2026-03-26 | 2026-02-28 | 2026-03-26 | 1900-11-04 22:19 | 309.93 | 309.93 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AC-MA-20 | Air Duct | 16 | 2026-03-04 | 2026-03-26 | 2026-03-04 | 2026-03-26 | 1900-06-04 | 156 | 156 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AC-MA-30 | Diffusers and Grills | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1900-03-14 07:26 | 74.31 | 74.31 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AC-MA-40 | Exhaust fans | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 66.12 | 66.12 | 66.12 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 3147.03 | 3147.03 | 3147.03 | 100% | 100% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-PR-SL-PB-MA-10 | PPR Pipes & Valves | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 265.2 | 265.2 | 265.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-PB-MA-20 | UPCV Pipes | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 335.19 | 335.19 | 335.19 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-PB-MA-30 | Sanitary Drainage Fixtures | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2546.64 | 2546.64 | 2546.64 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 6854.64 | 6854.64 | 6854.64 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-SL-IR-MA-10 | Gate Valve including valve box | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 756.3 | 756.3 | 756.3 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-IR-MA-20 | Bulbblers and Spreyers | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1916-09-10 08:10 | 6098.34 | 6098.34 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1901-02-10 12:29 | 407.52 | 407.52 | 100% | 100% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-H-PR-SL-EL-MA-10 | Wiring Devices Materials | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1901-02-10 12:29 | 407.52 | 407.52 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE FIGHTING WORK |  | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1900-01-21 17:02 | 22.71 | 22.71 | 100% | 100% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-H-PR-SL-FF-MA-10 | Fire Extinguishers | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 22.71 | 22.71 | 22.71 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PROCUREMENT |  | 148 | 2026-02-26 | 2026-08-26 | 2026-02-26 |  | 1839956.04 | 1787818.6 | 1839956.04 | 100% | 97.17% | 0 | 0 | 0 |  | 202 | 178 | 23 | 1
LONG LEAD ITEMS |  | 142 | 2026-03-05 | 2026-08-26 | 2026-03-05 |  | 999589.41 | 962156.13 | 999589.41 | 100% | 96.26% | 0 | 0 | 0 |  | 108 | 92 | 15 | 1
PURCHASE ORDER |  | 112 | 2026-03-05 | 2026-07-22 | 2026-03-05 | 2026-09-08 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 28 | 28 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 49 | 2026-03-07 | 2026-05-07 | 2026-03-07 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-PR-LL-LS-PO-20 | Benches, Seats (Rectangular & Circular) | 49 | 2026-03-07 | 2026-05-07 | 2026-03-07 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-PO-30 | Fence, gates and accessories | 43 | 2026-03-14 | 2026-05-07 | 2026-03-14 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-PO-10 | Bike and Walk Path Materials | 33 | 2026-03-30 | 2026-05-07 | 2026-03-30 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 35 | 2026-03-28 | 2026-05-07 | 2026-03-28 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-SP-PO-20 | Tartan Floor | 35 | 2026-03-28 | 2026-05-07 | 2026-03-28 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-SP-PO-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc) | 34 | 2026-03-29 | 2026-05-07 | 2026-03-29 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 39 | 2026-03-18 | 2026-05-07 | 2026-03-18 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-H-PR-LL-CO-PO-10 | Autoclaved Aerated Panel | 39 | 2026-03-18 | 2026-05-07 | 2026-03-18 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 38 | 2026-03-24 | 2026-05-07 | 2026-03-24 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-MT-PO-10 | Metal Doors | 38 | 2026-03-24 | 2026-05-07 | 2026-03-24 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-MT-PO-20 | Curtain Wall | 38 | 2026-03-24 | 2026-05-07 | 2026-03-24 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 34 | 2026-03-29 | 2026-05-07 | 2026-03-29 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-PB-PO-10 | Booster Pump | 34 | 2026-03-29 | 2026-05-07 | 2026-03-29 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-PB-PO-20 | GRP Sectional Panel Water Tanks (4x3x3m) | 33 | 2026-03-30 | 2026-05-07 | 2026-03-30 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 50 | 2026-03-05 | 2026-05-07 | 2026-03-05 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-IR-PO-20 | Irrigation Control System | 50 | 2026-03-05 | 2026-05-07 | 2026-03-05 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-IR-PO-10 | HDPE Pipes | 49 | 2026-03-07 | 2026-05-07 | 2026-03-07 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 59 | 2026-05-11 | 2026-07-22 | 2026-05-11 | 2026-09-08 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 16 | 16 | 0 | 0
PG-H-PR-LL-EL-PO-10 | Main Distribution Board(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-20 | Power Panels (Pump, Street Light)(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-30 | Site Lighting Poles(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-40 | Lighting Fixtures(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-70 | Security and Access Control System Materials(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-80 | Fire Alarm System Materials(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-10_R | Main Distribution Board(Remaining) | 7 | 2026-07-07 | 2026-07-14 | 2026-08-05 | 2026-09-08 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-20_R | Power Panels (Pump, Street Light)(Remaining) | 7 | 2026-07-07 | 2026-07-14 | 2026-08-05 | 2026-09-08 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-30_R | Site Lighting Poles(Remaining) | 7 | 2026-07-07 | 2026-07-14 | 2026-08-05 | 2026-09-08 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-40_R | Lighting Fixtures(Remaining) | 7 | 2026-07-07 | 2026-07-14 | 2026-07-23 | 2026-07-23 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 7 | 2026-07-07 | 2026-07-14 | 2026-08-27 | 2026-09-08 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-70_R | Security and Access Control System Materials(Remaining) | 7 | 2026-07-07 | 2026-07-14 | 2026-08-27 | 2026-09-08 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-80_R | Fire Alarm System Materials(Remaining) | 7 | 2026-07-07 | 2026-07-14 | 2026-08-27 | 2026-09-08 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-PO-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 7 | 2026-07-15 | 2026-07-22 | 2026-08-27 | 2026-09-08 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MANUFACTURE / FABRICATION |  | 111 | 2026-04-01 | 2026-08-12 | 2026-04-01 |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 40 | 39 | 0 | 1
EXTERNAL / LANDSCAPE WORK |  | 65 | 2026-05-05 | 2026-07-23 | 2026-05-05 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 6 | 6 | 0 | 0
PG-H-PR-LL-LS-MF-20 | Benches, Seats (Rectangular & Circular)(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-MF-30 | Fence, gates and accessories(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-MF-10 | Bike and Walk Path Materials(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-MF-20_R | Benches, Seats (Rectangular & Circular)(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-05 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-MF-30_R | Fence, gates and accessories(Remaining) | 5 | 2026-06-25 | 2026-06-30 | 2026-07-23 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-MF-10_R | Bike and Walk Path Materials(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-07-30 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 65 | 2026-05-05 | 2026-07-23 | 2026-05-05 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-PR-LL-SP-MF-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc)(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-SP-MF-20 | Tartan Floor(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-SP-MF-10_R | Football Playground Materials (Flooring, goal post, nets, paints, etc)(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-07-30 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-SP-MF-20_R | Tartan Floor(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-07-30 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 79 | 2026-04-01 | 2026-07-06 | 2026-04-01 | 2026-06-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-CO-MF-10 | Autoclaved Aerated Panel(Completed) | 69 | 2026-04-01 | 2026-06-25 | 2026-04-01 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-CO-MF-10_R | Autoclaved Aerated Panel(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-06-24 | 2026-06-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 65 | 2026-05-05 | 2026-07-23 | 2026-05-05 |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 3 | 0 | 1
PG-H-PR-LL-MT-MF-10 | Metal Doors(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-MT-MF-20 | Curtain Wall(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-MT-MF-10_R | Metal Doors(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 46291 | 2026-10-02 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-MT-MF-20_R | Curtain Wall(Remaining) | 25 | 2026-06-25 | 2026-07-23 |  |  | 0 | 0 | 0 | 100% | 0% | 0 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PLUMBING WORK |  | 65 | 2026-05-05 | 2026-07-23 | 2026-05-05 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-PR-LL-PB-MF-10 | Booster Pump(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-PB-MF-20 | GRP Sectional Panel Water Tanks (4x3x3m)(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-PB-MF-10_R | Booster Pump(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-27 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-PB-MF-20_R | GRP Sectional Panel Water Tanks (4x3x3m)(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-27 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 52 | 2026-05-05 | 2026-07-08 | 2026-05-05 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-PR-LL-IR-MF-10 | HDPE Pipes(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-IR-MF-20 | Irrigation Control System(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-IR-MF-10_R | HDPE Pipes(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-08-27 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-IR-MF-20_R | Irrigation Control System(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-08-27 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 76 | 2026-05-12 | 2026-08-12 | 2026-05-12 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 16 | 16 | 0 | 0
PG-H-PR-LL-EL-MF-10 | Main Distribution Board(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-20 | Power Panels (Pump, Street Light)(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-30 | Site Lighting Poles(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-40 | Lighting Fixtures(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-70 | Security and Access Control System Materials(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-80 | Fire Alarm System Materials(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-10_R | Main Distribution Board(Remaining) | 13 | 2026-07-15 | 2026-07-29 | 2026-07-30 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-20_R | Power Panels (Pump, Street Light)(Remaining) | 13 | 2026-07-15 | 2026-07-29 | 2026-07-30 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-30_R | Site Lighting Poles(Remaining) | 25 | 2026-07-15 | 2026-08-12 | 2026-07-30 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-40_R | Lighting Fixtures(Remaining) | 25 | 2026-07-15 | 2026-08-12 | 2026-07-30 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 25 | 2026-07-15 | 2026-08-12 | 2026-08-27 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-70_R | Security and Access Control System Materials(Remaining) | 25 | 2026-07-15 | 2026-08-12 | 2026-08-27 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-80_R | Fire Alarm System Materials(Remaining) | 25 | 2026-07-15 | 2026-08-12 | 2026-08-27 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-MF-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 13 | 2026-07-23 | 2026-08-06 | 2026-08-27 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
DELIVERY TO SITE |  | 92 | 2026-05-07 | 2026-08-26 | 2026-05-06 |  | 999589.41 | 962156.13 | 999589.41 | 100% | 96.26% | 0 | 0 | 0 |  | 40 | 25 | 15 | 0
EXTERNAL / LANDSCAPE WORK |  | 75 | 2026-05-07 | 2026-08-06 | 2026-05-06 |  | 234716.67 | 229646.97 | 234716.67 | 100% | 97.84% | 0 | 0 | 0 |  | 6 | 4 | 2 | 0
PG-H-PR-LL-LS-DL-20 | Benches, Seats (Rectangular & Circular)(Completed) | 38 | 2026-05-07 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 28474.61 | 28474.61 | 28474.61 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-DL-30 | Fence, gates and accessories(Completed) | 38 | 2026-05-07 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 11847.38 | 11847.38 | 11847.38 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-DL-10 | Bike and Walk Path Materials(Completed) | 38 | 2026-05-07 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 103704.3 | 103704.3 | 103704.3 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-DL-30_R | Fence, gates and accessories(Remaining) | 5 | 2026-07-01 | 2026-07-06 | 2026-07-22 | 2026-09-19 | 17771.08 | 17771.08 | 17771.08 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-LS-DL-20_R | Benches, Seats (Rectangular & Circular)(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-20 |  | 28474.61 | 25627.14 | 28474.61 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-H-PR-LL-LS-DL-10_R | Bike and Walk Path Materials(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-06 |  | 44444.7 | 42222.46 | 44444.7 | 100% | 95% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 75 | 2026-05-07 | 2026-08-06 | 2026-05-06 |  | 349555.5 | 336394.01 | 349555.5 | 100% | 96.23% | 0 | 0 | 0 |  | 4 | 2 | 2 | 0
PG-H-PR-LL-SP-DL-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc)(Completed) | 38 | 2026-05-07 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 64212.75 | 64212.75 | 64212.75 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-SP-DL-20 | Tartan Floor(Completed) | 38 | 2026-05-07 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 121621.5 | 121621.5 | 121621.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-SP-DL-10_R | Football Playground Materials (Flooring, goal post, nets, paints, etc)(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-06 |  | 64212.75 | 61002.11 | 64212.75 | 100% | 95% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-H-PR-LL-SP-DL-20_R | Tartan Floor(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-06 |  | 99508.5 | 89557.65 | 99508.5 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
CONCRETE WORK |  | 53 | 2026-05-07 | 2026-07-12 | 2026-05-06 | 2026-07-07 | 12757.5 | 12757.5 | 12757.5 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-LL-CO-DL-10 | Autoclaved Aerated Panel(Completed) | 38 | 2026-05-07 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 7654.5 | 7654.5 | 7654.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-CO-DL-10_R | Autoclaved Aerated Panel(Remaining) | 5 | 2026-07-07 | 2026-07-12 | 2026-07-06 | 2026-07-07 | 5103 | 5103 | 5103 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 75 | 2026-05-07 | 2026-08-06 | 2026-05-06 |  | 8003.07 | 7042.7 | 8003.07 | 100% | 88% | 0 | 0 | 0 |  | 4 | 2 | 2 | 0
PG-H-PR-LL-MT-DL-10 | Metal Doors(Completed) | 38 | 2026-05-07 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 459.11 | 459.11 | 459.11 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-MT-DL-20 | Curtain Wall(Completed) | 38 | 2026-05-07 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 2742.12 | 2742.12 | 2742.12 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-MT-DL-10_R | Metal Doors(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-27 |  | 688.66 | 1901-07-03 22:19 | 688.66 | 100% | 80% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-H-PR-LL-MT-DL-20_R | Curtain Wall(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-27 |  | 4113.18 | 3290.54 | 4113.18 | 100% | 80% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PLUMBING WORK |  | 75 | 2026-05-07 | 2026-08-06 | 2026-05-06 |  | 31985.55 | 31048.3 | 31985.55 | 100% | 97.07% | 0 | 0 | 0 |  | 4 | 3 | 1 | 0
PG-H-PR-LL-PB-DL-10 | Booster Pump(Completed) | 38 | 2026-05-07 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 6545.88 | 6545.88 | 6545.88 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-PB-DL-20 | GRP Sectional Panel Water Tanks (4x3x3m)(Completed) | 38 | 2026-05-07 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 6248.34 | 6248.34 | 6248.34 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-PB-DL-10_R | Booster Pump(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-27 | 2026-09-21 | 9818.82 | 1926-11-17 19:41 | 9818.82 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-PB-DL-20_R | GRP Sectional Panel Water Tanks (4x3x3m)(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-27 |  | 9372.51 | 8435.26 | 9372.51 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
IRRIGATION WORK |  | 58 | 2026-05-07 | 2026-07-18 | 2026-05-06 | 2026-09-04 | 115364.25 | 115364.25 | 115364.25 | 100% | 100% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-PR-LL-IR-DL-10 | HDPE Pipes(Completed) | 38 | 2026-05-07 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 37226.25 | 37226.25 | 37226.25 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-IR-DL-20 | Irrigation Control System(Completed) | 38 | 2026-05-07 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 16364.7 | 16364.7 | 16364.7 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-IR-DL-10_R | HDPE Pipes(Remaining) | 8 | 2026-07-09 | 2026-07-18 | 2026-08-20 | 2026-08-27 | 37226.25 | 37226.25 | 37226.25 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-IR-DL-20_R | Irrigation Control System(Remaining) | 8 | 2026-07-09 | 2026-07-18 | 2026-08-20 | 2026-09-04 | 24547.05 | 24547.05 | 24547.05 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 87 | 2026-05-13 | 2026-08-26 | 2026-05-13 |  | 247206.87 | 229902.39 | 247206.87 | 100% | 93% | 0 | 0 | 0 |  | 16 | 8 | 8 | 0
PG-H-PR-LL-EL-DL-10 | Main Distribution Board(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 1338.93 | 1338.93 | 1338.93 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-DL-20 | Power Panels (Pump, Street Light)(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 1071.14 | 1071.14 | 1071.14 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-DL-30 | Site Lighting Poles(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 57437.42 | 57437.42 | 57437.42 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-DL-40 | Lighting Fixtures(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 3463.64 | 3463.64 | 3463.64 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-DL-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 2711.31 | 2711.31 | 2711.31 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-DL-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 2644.33 | 2644.33 | 2644.33 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-DL-70 | Security and Access Control System Materials(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 3347.73 | 3347.73 | 3347.73 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-DL-80 | Fire Alarm System Materials(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 2147.55 | 2147.55 | 2147.55 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-LL-EL-DL-10_R | Main Distribution Board(Remaining) | 8 | 2026-07-30 | 2026-08-08 | 2026-08-27 |  | 1908-07-20 04:05 | 1907-09-11 18:00 | 3124.17 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-H-PR-LL-EL-DL-20_R | Power Panels (Pump, Street Light)(Remaining) | 8 | 2026-07-30 | 2026-08-08 | 2026-08-27 |  | 2499.34 | 2249.4 | 2499.34 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-H-PR-LL-EL-DL-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 8 | 2026-08-08 | 2026-08-16 | 2026-08-27 |  | 6326.4 | 1915-08-02 18:14 | 6326.4 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-H-PR-LL-EL-DL-30_R | Site Lighting Poles(Remaining) | 12 | 2026-08-13 | 2026-08-26 | 2026-08-20 |  | 134020.66 | 120618.59 | 134020.66 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-H-PR-LL-EL-DL-40_R | Lighting Fixtures(Remaining) | 12 | 2026-08-13 | 2026-08-26 | 2026-08-20 |  | 8081.83 | 1919-11-29 15:36 | 8081.83 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-H-PR-LL-EL-DL-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 12 | 2026-08-13 | 2026-08-26 | 2026-08-27 |  | 6170.09 | 5553.08 | 6170.09 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-H-PR-LL-EL-DL-70_R | Security and Access Control System Materials(Remaining) | 12 | 2026-08-13 | 2026-08-26 | 2026-08-27 |  | 7811.37 | 1919-03-31 05:31 | 7811.37 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-H-PR-LL-EL-DL-80_R | Fire Alarm System Materials(Remaining) | 12 | 2026-08-13 | 2026-08-26 | 2026-08-27 |  | 5010.96 | 4509.86 | 5010.96 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
SHORT LEAD ITEMS |  | 113 | 2026-02-26 | 2026-07-16 | 2026-02-26 |  | 840366.63 | 825662.48 | 840366.63 | 100% | 98.25% | 0 | 0 | 0 |  | 94 | 86 | 8 | 0
MATERIAL SUBMITTALS |  | 0 |  |  |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
PURCHASE ORDER |  | 101 | 2026-02-26 | 2026-07-02 | 2026-02-26 | 2026-08-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 47 | 47 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 101 | 2026-02-26 | 2026-07-02 | 2026-02-26 | 2026-08-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PG-H-PR-SL-LS-PO-10 | Backfilling Materials | 44 | 2026-02-26 | 2026-04-23 | 2026-02-26 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-PO-30 | Compacted Natural Ground Soil | 42 | 2026-03-01 | 2026-04-23 | 2026-03-01 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-PO-20 | Interlock tiles | 27 | 2026-03-30 | 2026-04-30 | 2026-03-30 | 2026-04-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-PO-40 | Curb Stone | 22 | 2026-04-05 | 2026-04-30 | 2026-04-05 | 2026-04-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-PO-50 | Thermoplastic pavement road marking(Completed) | 36 | 2026-05-10 | 2026-06-25 | 2026-05-10 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-PO-60 | Traffic Signages(Completed) | 36 | 2026-05-10 | 2026-06-25 | 2026-05-10 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-PO-70 | Trees(Completed) | 36 | 2026-05-10 | 2026-06-25 | 2026-05-10 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-PO-80 | Lawn(Completed) | 36 | 2026-05-10 | 2026-06-25 | 2026-05-10 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-PO-50_R | Thermoplastic pavement road marking(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-20 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-PO-60_R | Traffic Signages(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-20 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-PO-70_R | Trees(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-20 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-PO-80_R | Lawn(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-20 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 41 | 2026-03-02 | 2026-04-23 | 2026-03-02 | 2026-04-22 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-H-PR-SL-CO-PO-10 | Steel Rebar | 41 | 2026-03-02 | 2026-04-23 | 2026-03-02 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-PO-20 | Concrete | 36 | 2026-03-08 | 2026-04-23 | 2026-03-08 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-PO-40 | CMU Block | 33 | 2026-03-11 | 2026-04-23 | 2026-03-11 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-PO-50 | Concrete Repair & Protection Materials | 32 | 2026-03-12 | 2026-04-23 | 2026-03-12 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-PO-30 | Screed | 23 | 2026-03-28 | 2026-04-23 | 2026-03-28 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL & FINISHES WORK |  | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PG-H-PR-SL-AR-PO-10 | Ceramic tiles | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-PO-20 | Anti-slip Granite tiles | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-PO-30 | Epoxy Paint | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-PO-40 | Cement Plaster | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-PO-50 | Acrylic Paint | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-PO-60 | Stone Cladding | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-PO-70 | Aluminum Plates | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-PO-80 | Phenolic Partition | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-PO-90 | Glass Partition | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-PO-100 | Gypsum Boards | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-PO-110 | Specialities Materials (Toilet accessories, lockers, logo, etc) | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-PO-120 | Waterproofing System Materials | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-PR-SL-MT-PO-10 | Galvanized Steel Ladder | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-MT-PO-20 | Galvanized Steel Roof Scupper | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-MT-PO-30 | Galvanized Steel Cover with frame | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
HVAC WORK |  | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-PR-SL-AC-PO-10 | Split Air Conditioning Unit | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AC-PO-20 | Air Duct | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AC-PO-30 | Diffusers and Grills | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AC-PO-40 | Exhaust fans | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-PR-SL-PB-PO-10 | PPR Pipes & Valves | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-PB-PO-20 | UPCV Pipes | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-PB-PO-30 | Sanitary Drainage Fixtures | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 47 | 2026-05-05 | 2026-07-02 | 2026-05-05 | 2026-08-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-PR-SL-IR-PO-10 | Gate Valve including valve box(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-IR-PO-20 | Bulbblers and Spreyers(Completed) | 40 | 2026-05-05 | 2026-06-25 | 2026-05-05 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-IR-PO-10_R | Gate Valve including valve box(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-20 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-IR-PO-20_R | Bulbblers and Spreyers(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-20 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 41 | 2026-05-12 | 2026-07-02 | 2026-05-12 | 2026-08-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-SL-EL-PO-10 | Wiring Devices Materials(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-EL-PO-10_R | Wiring Devices Materials(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-27 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE FIGHTING WORK |  | 41 | 2026-05-12 | 2026-07-02 | 2026-05-12 | 2026-08-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-H-PR-SL-FF-PO-10 | Fire Extinguishers(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-FF-PO-10_R | Fire Extinguishers(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-20 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
DELIVERY TO SITE |  | 111 | 2026-03-01 | 2026-07-16 | 2026-03-01 |  | 840366.63 | 825662.48 | 840366.63 | 100% | 98.25% | 0 | 0 | 0 |  | 47 | 39 | 8 | 0
EXTERNAL / LANDSCAPE WORK |  | 111 | 2026-03-01 | 2026-07-16 | 2026-03-01 |  | 649200.96 | 640265.1 | 649200.96 | 100% | 98.62% | 0 | 0 | 0 |  | 12 | 8 | 4 | 0
PG-H-PR-SL-LS-DL-10 | Backfilling Materials | 43 | 2026-03-01 | 2026-04-23 | 2026-03-01 | 2026-04-24 | 176175 | 176175 | 176175 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-DL-30 | Compacted Natural Ground Soil | 41 | 2026-03-03 | 2026-04-23 | 2026-03-03 | 2026-04-24 | 28080 | 28080 | 28080 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-DL-20 | Interlock tiles | 12 | 2026-04-30 | 2026-05-13 | 2026-04-30 | 2026-05-13 | 157450.5 | 157450.5 | 157450.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-DL-40 | Curb Stone | 12 | 2026-04-30 | 2026-05-13 | 2026-04-30 | 2026-05-13 | 188352 | 188352 | 188352 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-DL-50 | Thermoplastic pavement road marking(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 1419.2 | 1419.2 | 1419.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-DL-60 | Traffic Signages(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 535.57 | 535.57 | 535.57 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-DL-70 | Trees(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 13046.27 | 13046.27 | 13046.27 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-DL-80 | Lawn(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 24570 | 24570 | 24570 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-LS-DL-50_R | Thermoplastic pavement road marking(Remaining) | 12 | 2026-07-04 | 2026-07-16 | 2026-08-27 |  | 3311.47 | 2814.75 | 3311.47 | 100% | 85% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-H-PR-SL-LS-DL-60_R | Traffic Signages(Remaining) | 12 | 2026-07-04 | 2026-07-16 | 2026-08-27 |  | 1249.67 | 1902-11-27 05:17 | 1249.67 | 100% | 85% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-H-PR-SL-LS-DL-70_R | Trees(Remaining) | 12 | 2026-07-04 | 2026-07-16 | 2026-08-27 |  | 30441.29 | 25875.09 | 30441.29 | 100% | 85% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-H-PR-SL-LS-DL-80_R | Lawn(Remaining) | 12 | 2026-07-04 | 2026-07-16 | 2026-08-27 |  | 24570 | 20884.5 | 24570 | 100% | 85% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
CONCRETE WORK |  | 52 | 2026-03-10 | 2026-05-13 | 2026-03-10 | 2026-05-13 | 14485.23 | 14485.23 | 14485.23 | 100% | 100% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-H-PR-SL-CO-DL-20 | Concrete | 35 | 2026-03-10 | 2026-04-23 | 2026-03-10 | 2026-04-24 | 4669.65 | 4669.65 | 4669.65 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-DL-10 | Steel Rebar | 12 | 2026-04-23 | 2026-05-06 | 2026-04-23 | 2026-05-06 | 4291.38 | 4291.38 | 4291.38 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-DL-30 | Screed | 18 | 2026-04-23 | 2026-05-13 | 2026-04-23 | 2026-05-13 | 1058.4 | 1058.4 | 1058.4 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-DL-40 | CMU Block | 18 | 2026-04-23 | 2026-05-13 | 2026-04-23 | 2026-05-13 | 1117.8 | 1117.8 | 1117.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-CO-DL-50 | Concrete Repair & Protection Materials | 18 | 2026-04-23 | 2026-05-13 | 2026-04-23 | 2026-05-13 | 3348 | 3348 | 3348 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL & FINISHES WORK |  | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 73026.09 | 73026.09 | 73026.09 | 100% | 100% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PG-H-PR-SL-AR-DL-10 | Ceramic tiles | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 5147.55 | 5147.55 | 5147.55 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-DL-20 | Anti-slip Granite tiles | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 4819.5 | 4819.5 | 4819.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-DL-30 | Epoxy Paint | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 1000.62 | 1000.62 | 1000.62 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-DL-40 | Cement Plaster | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 1992.33 | 1992.33 | 1992.33 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-DL-50 | Acrylic Paint | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 1331.1 | 1331.1 | 1331.1 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-DL-60 | Stone Cladding | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 16669.8 | 16669.8 | 16669.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-DL-70 | Aluminum Plates | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 1642.14 | 1642.14 | 1642.14 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-DL-80 | Phenolic Partition | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 12063.6 | 12063.6 | 12063.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-DL-90 | Glass Partition | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 1398.6 | 1398.6 | 1398.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-DL-100 | Gypsum Boards | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 1697.22 | 1697.22 | 1697.22 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-DL-110 | Specialities Materials (Toilet accessories, lockers, logo, etc) | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 20365.83 | 20365.83 | 20365.83 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AR-DL-120 | Waterproofing System Materials | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 4897.8 | 4897.8 | 4897.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 4310.01 | 4310.01 | 4310.01 | 100% | 100% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-PR-SL-MT-DL-10 | Galvanized Steel Ladder | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 1908-11-29 17:46 | 3256.74 | 3256.74 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-MT-DL-20 | Galvanized Steel Roof Scupper | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 281.88 | 281.88 | 281.88 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-MT-DL-30 | Galvanized Steel Cover with frame | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 771.39 | 771.39 | 771.39 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
HVAC WORK |  | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 5457.24 | 5457.24 | 5457.24 | 100% | 100% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-H-PR-SL-AC-DL-10 | Split Air Conditioning Unit | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 1907-08-20 08:53 | 2789.37 | 2789.37 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AC-DL-20 | Air Duct | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 1903-11-04 | 1404 | 1404 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AC-DL-30 | Diffusers and Grills | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 668.79 | 668.79 | 668.79 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-AC-DL-40 | Exhaust fans | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 595.08 | 595.08 | 595.08 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 28323.27 | 28323.27 | 28323.27 | 100% | 100% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-H-PR-SL-PB-DL-10 | PPR Pipes & Valves | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 2386.8 | 2386.8 | 2386.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-PB-DL-20 | UPCV Pipes | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 3016.71 | 3016.71 | 3016.71 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-PB-DL-30 | Sanitary Drainage Fixtures | 6 | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 22919.76 | 22919.76 | 22919.76 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 58 | 2026-05-06 | 2026-07-16 | 2026-05-06 |  | 61691.76 | 57064.88 | 61691.76 | 100% | 92.5% | 0 | 0 | 0 |  | 4 | 2 | 2 | 0
PG-H-PR-SL-IR-DL-10 | Gate Valve including valve box(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 3403.35 | 3403.35 | 3403.35 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-IR-DL-20 | Bulbblers and Spreyers(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 27442.53 | 27442.53 | 27442.53 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-IR-DL-10_R | Gate Valve including valve box(Remaining) | 12 | 2026-07-04 | 2026-07-16 | 2026-08-20 |  | 3403.35 | 2892.85 | 3403.35 | 100% | 85% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-H-PR-SL-IR-DL-20_R | Bulbblers and Spreyers(Remaining) | 12 | 2026-07-04 | 2026-07-16 | 2026-08-27 |  | 27442.53 | 23326.15 | 27442.53 | 100% | 85% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
ELECTRICAL WORK |  | 46 | 2026-05-20 | 2026-07-16 | 2026-05-20 |  | 3667.68 | 2640.73 | 3667.68 | 100% | 72% | 0 | 0 | 0 |  | 2 | 1 | 1 | 0
PG-H-PR-SL-EL-DL-10 | Wiring Devices Materials(Completed) | 27 | 2026-05-20 | 2026-06-24 | 2026-05-20 | 2026-06-24 | 1100.3 | 1100.3 | 1100.3 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-EL-DL-10_R | Wiring Devices Materials(Remaining) | 12 | 2026-07-04 | 2026-07-16 | 2026-09-26 |  | 2567.38 | 1540.43 | 2567.38 | 100% | 60% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
FIRE FIGHTING WORK |  | 46 | 2026-05-20 | 2026-07-16 | 2026-05-20 |  | 1900-07-22 09:22 | 1900-03-29 22:19 | 1900-07-22 09:22 | 100% | 44% | 0 | 0 | 0 |  | 2 | 1 | 1 | 0
PG-H-PR-SL-FF-DL-10 | Fire Extinguishers(Completed) | 27 | 2026-05-20 | 2026-06-24 | 2026-05-20 | 2026-06-24 | 61.32 | 61.32 | 61.32 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-H-PR-SL-FF-DL-10_R | Fire Extinguishers(Remaining) | 12 | 2026-07-04 | 2026-07-16 | 2026-10-03 |  | 143.07 | 28.61 | 143.07 | 100% | 20% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
CONSTRUCTION STAGE |  | 198 | 2026-04-05 | 2026-11-26 | 2026-04-05 |  | 3501375.59 | 3200034 | 4088791.2 | 85.63% | 78.26% | 5964 | 5187 | 4146 |  | 129 | 57 | 37 | 35
PLAYGROUND AND LANDSCAPING WORKS |  | 198 | 2026-04-05 | 2026-11-26 | 2026-04-05 |  | 3182875.72 | 2939079.82 | 3760297.62 | 84.64% | 78.16% | 4256 | 3492 | 2706 |  | 91 | 36 | 23 | 32
CUT AND FILL |  | 28 | 2026-04-05 | 2026-05-06 | 2026-04-05 | 2026-05-06 | 453900 | 453900 | 453900 | 100% | 100% | 376 | 376 | 376 |  | 3 | 3 | 0 | 0
PG-H-CON-EX-CF-10 | Existing Soil Excavation Works | 26 | 2026-04-05 | 2026-05-04 | 2026-04-05 | 2026-05-04 | 125280 | 125280 | 125280 | 100% | 100% | 172 | 172 | 172 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-CF-20 | Soil Replacement Works | 21 | 2026-04-12 | 2026-05-05 | 2026-04-12 | 2026-05-05 | 62400 | 62400 | 62400 | 100% | 100% | 100 | 100 | 100 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-CF-30 | Levelling & Backfilling Works | 18 | 2026-04-16 | 2026-05-06 | 2026-04-16 | 2026-05-06 | 266220 | 266220 | 266220 | 100% | 100% | 104 | 104 | 104 | No | 1 | 1 | 0 | 0
PLAYGROUND WORKS |  | 178 | 2026-04-19 | 2026-11-17 | 2026-04-19 |  | 728545.73 | 687924.15 | 781940.4 | 93.17% | 87.98% | 864 | 709 | 713 |  | 14 | 7 | 6 | 1
FOOTBALL PLAYGROUND WORKS |  | 178 | 2026-04-19 | 2026-11-17 | 2026-04-19 |  | 728545.73 | 687924.15 | 781940.4 | 93.17% | 87.98% | 864 | 709 | 713 |  | 14 | 7 | 6 | 1
PG-H-CON-EX-FB-10 | Subgrade Preparation and Compaction | 16 | 2026-04-19 | 2026-05-06 | 2026-04-19 | 2026-05-06 | 23667 | 23667 | 23667 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-FB-20 | Sub-Base Laying and Compaction | 12 | 2026-04-23 | 2026-05-06 | 2026-04-23 | 2026-05-06 | 23667 | 23667 | 23667 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-FB-30 | Base Course Laying and Compaction | 33 | 2026-05-06 | 2026-06-17 | 2026-05-06 | 2026-06-17 | 23667 | 23667 | 23667 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-FB-70 | Topsoil Placement(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 7100.1 | 7100.1 | 7100.1 | 100% | 100% | 25 | 25 | 25 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-FB-40 | Tartan flooring(Completed) | 7 | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 147420 | 147420 | 147420 | 100% | 100% | 19 | 19 | 19 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-FB-80 | Fine Grading & Leveling | 15 | 2026-06-25 | 2026-07-12 | 2026-07-12 | 2026-08-14 | 23667 | 23667 | 23667 | 100% | 100% | 76 | 76 | 76 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-FB-70_R | Topsoil Placement(Remaining) | 14 | 2026-07-13 | 2026-07-28 | 2026-07-30 | 2026-08-14 | 16566.9 | 16566.9 | 16566.9 | 100% | 100% | 59 | 59 | 59 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-FB-50 | Goal Post Foundation | 17 | 2026-07-29 | 2026-08-17 | 2026-08-20 |  | 35500.5 | 28400.4 | 35500.5 | 100% | 80% | 100 | 100 | 80 | No | 1 | 0 | 1 | 0
PG-H-CON-EX-FB-120 | Installation of Lighting System | 13 | 2026-08-18 | 2026-09-01 | 2026-08-27 |  | 48720 | 36540 | 48720 | 100% | 75% | 32 | 32 | 24 | No | 1 | 0 | 1 | 0
PG-H-CON-EX-FB-90 | Turfing / Seeding Works | 12 | 2026-09-02 | 2026-09-15 | 2026-08-14 |  | 1964-10-17 | 18933.6 | 23667 | 100% | 80% | 48 | 48 | 38 | No | 1 | 0 | 1 | 0
PG-H-CON-EX-FB-40_R | Tartan flooring(Remaining) | 15 | 2026-09-16 | 2026-10-04 | 2026-08-06 |  | 343980 | 309582 | 343980 | 100% | 90% | 45 | 45 | 40 | No | 1 | 0 | 1 | 0
PG-H-CON-EX-FB-60 | Goal Post Installation & Alignment | 13 | 2026-10-05 | 2026-10-19 | 2026-08-20 |  | 10923.23 | 24850.35 | 35500.5 | 30.77% | 70% | 56 | 17 | 39 | No | 1 | 0 | 1 | 0
PG-H-CON-EX-FB-110 | Install Playground Benches | 15 | 2026-10-20 | 2026-11-05 | 2026-08-27 |  | 0 | 3862.8 | 5150.4 | 0% | 75% | 32 | 0 | 24 | No | 1 | 0 | 1 | 0
PG-H-CON-EX-FB-100 | Markings and Signages | 10 | 2026-11-07 | 2026-11-17 |  |  | 0 | 0 | 23667 | 0% | 0% | 84 | 0 | 0 | No | 1 | 0 | 0 | 1
GENERAL SITE WORKS |  | 188 | 2026-04-16 | 2026-11-26 | 2026-04-16 |  | 1061769.12 | 716076.06 | 1224114.42 | 86.74% | 58.5% | 1996 | 1568 | 888 |  | 47 | 11 | 10 | 26
FENCE WORKS |  | 101 | 2026-04-16 | 2026-08-16 | 2026-04-16 |  | 65818.8 | 48705.91 | 65818.8 | 100% | 74% | 336 | 336 | 249 |  | 5 | 2 | 2 | 1
PG-H-CON-EX-GN-FN-10 | Excavation for fence foundation | 3 | 2026-04-16 | 2026-04-19 | 2026-04-16 | 2026-04-19 | 13163.76 | 13163.76 | 13163.76 | 100% | 100% | 92 | 92 | 92 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-GN-FN-20 | Concrete Foundations for Fence | 9 | 2026-07-13 | 2026-07-22 | 2026-08-13 | 2026-08-20 | 13163.76 | 1936-01-14 18:14 | 13163.76 | 100% | 100% | 68 | 68 | 68 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-GN-FN-30 | Installation of Galvanized Steel Posts & Framing | 9 | 2026-07-23 | 2026-08-02 | 2026-08-27 |  | 13163.76 | 1932-06-07 09:07 | 13163.76 | 100% | 90% | 56 | 56 | 50 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-FN-40 | Fixing of Chain Link Mesh, Tensioning & Bracing | 8 | 2026-08-03 | 2026-08-11 | 2026-09-27 |  | 13163.76 | 10531.01 | 13163.76 | 100% | 80% | 48 | 48 | 38 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-FN-50 | Installation of Gates | 4 | 2026-08-12 | 2026-08-16 |  |  | 13163.76 | 0 | 13163.76 | 100% | 0% | 72 | 72 | 0 | Yes | 1 | 0 | 0 | 1
MECHANICAL WORK |  | 71 | 2026-05-12 | 2026-08-06 | 2026-05-12 |  | 421027.74 | 237097.86 | 421027.74 | 100% | 56.31% | 476 | 476 | 255 |  | 13 | 3 | 4 | 6
STORM WATER AND UTILITY WORK |  | 69 | 2026-05-12 | 2026-08-04 | 2026-05-12 |  | 27252 | 9133.2 | 27252 | 100% | 33.51% | 300 | 300 | 160 |  | 8 | 2 | 2 | 4
PG-H-CON-EX-GN-M-10 | Excavation | 2 | 2026-05-12 | 2026-05-13 | 2026-05-12 | 2026-05-13 | 3096 | 3096 | 3096 | 100% | 100% | 92 | 92 | 92 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-GN-M-20 | Bedding preparation & level control(Completed) | 27 | 2026-05-20 | 2026-06-24 | 2026-05-20 | 2026-06-24 | 1032 | 1032 | 1032 | 100% | 100% | 16 | 16 | 16 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-GN-M-20_R | Bedding preparation & level control(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-08-14 |  | 1032 | 1902-05-26 04:48 | 1032 | 100% | 85% | 16 | 16 | 14 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-M-30 | Manhole Installation | 5 | 2026-07-07 | 2026-07-12 | 2026-08-27 |  | 5160 | 1911-04-20 | 5160 | 100% | 80% | 48 | 48 | 38 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-M-40 | 150 mm uPVC pipe laying & jointing | 4 | 2026-07-13 | 2026-07-16 |  |  | 10740 | 0 | 10740 | 100% | 0% | 32 | 32 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-CON-EX-GN-M-50 | Concrete Encasement | 3 | 2026-07-18 | 2026-07-20 |  |  | 2064 | 0 | 2064 | 100% | 0% | 24 | 24 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-CON-EX-GN-M-60 | Backfilling & Compaction | 3 | 2026-07-21 | 2026-07-23 |  |  | 2064 | 0 | 2064 | 100% | 0% | 48 | 48 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-CON-EX-GN-M-70 | Surface Reinstatement & Civil Works | 4 | 2026-08-01 | 2026-08-04 |  |  | 2064 | 0 | 2064 | 100% | 0% | 24 | 24 | 0 | Yes | 1 | 0 | 0 | 1
IRRIGATION SYSTEM WORKS |  | 51 | 2026-06-02 | 2026-07-30 | 2026-06-02 |  | 393457.8 | 227964.66 | 393457.8 | 100% | 57.94% | 144 | 144 | 95 |  | 4 | 1 | 2 | 1
PG-H-CON-EX-GN-M-80 | Installation of HDPE Irrigation Pipe Network with Gate Valve and Box(Completed) | 20 | 2026-06-02 | 2026-06-24 | 2026-06-02 | 2026-06-24 | 72230.4 | 72230.4 | 72230.4 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-GN-M-80_R | Installation of HDPE Irrigation Pipe Network with Gate Valve and Box(Remaining) | 2 | 2026-07-21 | 2026-07-23 | 2026-08-14 |  | 108345.6 | 92093.76 | 108345.6 | 100% | 85% | 48 | 48 | 41 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-M-90 | Installation of Irrigation Control System | 3 | 2026-07-25 | 2026-07-27 | 2026-08-26 |  | 90915 | 2074-03-27 12:00 | 90915 | 100% | 70% | 32 | 32 | 22 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-M-100 | Installation of Bubblers and Sprinklers | 3 | 2026-07-28 | 2026-07-30 |  |  | 121966.8 | 0 | 121966.8 | 100% | 0% | 32 | 32 | 0 | Yes | 1 | 0 | 0 | 1
FIRE PROTECTION SYSTEM |  | 2 | 2026-08-05 | 2026-08-06 |  |  | 317.94 | 0 | 317.94 | 100% | 0% | 32 | 32 | 0 |  | 1 | 0 | 0 | 1
PG-H-CON-EX-GN-M-110 | Fire Extinguisher Installation | 2 | 2026-08-05 | 2026-08-06 |  |  | 317.94 | 0 | 317.94 | 100% | 0% | 32 | 32 | 0 | Yes | 1 | 0 | 0 | 1
ELECTRICAL WORK |  | 127 | 2026-05-20 | 2026-10-20 | 2026-05-20 |  | 536029.08 | 273997.79 | 539251.68 | 99.4% | 50.81% | 784 | 734 | 150 |  | 21 | 3 | 1 | 17
POWER, LIGHTING & GROUNDING |  | 92 | 2026-05-20 | 2026-09-08 | 2026-05-20 |  | 482181.48 | 273997.79 | 482181.48 | 100% | 56.82% | 376 | 376 | 150 |  | 10 | 3 | 1 | 6
PG-H-CON-EX-GN-E-10 | Excavation(Completed) | 27 | 2026-05-20 | 2026-06-24 | 2026-05-20 | 2026-06-24 | 63819.36 | 63819.36 | 63819.36 | 100% | 100% | 46 | 46 | 46 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-GN-E-20 | Foundation Work for Site Lighting Poles(Completed) | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 51055.49 | 51055.49 | 51055.49 | 100% | 100% | 20 | 20 | 20 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-GN-E-10_R | Excavation(Remaining) | 1 | 2026-08-04 | 2026-08-04 | 2026-07-16 | 2026-08-27 | 63819.36 | 63819.36 | 63819.36 | 100% | 100% | 46 | 46 | 46 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-GN-E-20_R | Foundation Work for Site Lighting Poles(Remaining) | 4 | 2026-08-05 | 2026-08-09 | 2026-08-20 |  | 119129.47 | 2160-12-04 13:55 | 119129.47 | 100% | 80% | 48 | 48 | 38 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-E-30 | Lightning Protection System (LPS) | 3 | 2026-08-17 | 2026-08-19 |  |  | 1922-08-17 | 0 | 8265 | 100% | 0% | 32 | 32 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-CON-EX-GN-E-40 | KWH Meter and MDB Installation | 2 | 2026-08-20 | 2026-08-22 |  |  | 1912-07-21 16:48 | 0 | 4586.7 | 100% | 0% | 32 | 32 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-CON-EX-GN-E-50 | Power Panels and Distribution Boards | 5 | 2026-08-23 | 2026-08-27 |  |  | 1947-08-18 21:36 | 0 | 17397.9 | 100% | 0% | 40 | 40 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-CON-EX-GN-E-60 | Site Lighting Poles Installation | 3 | 2026-08-29 | 2026-08-31 |  |  | 2249-06-16 17:17 | 0 | 127638.72 | 100% | 0% | 40 | 40 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-CON-EX-GN-E-70 | Wiring Works | 3 | 2026-09-01 | 2026-09-03 |  |  | 1911-07-25 | 0 | 4224 | 100% | 0% | 32 | 32 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-CON-EX-GN-E-80 | Lighting Fixtures with outlets Installation | 4 | 2026-09-05 | 2026-09-08 |  |  | 1960-11-25 11:31 | 0 | 22245.48 | 100% | 0% | 40 | 40 | 0 | Yes | 1 | 0 | 0 | 1
ELV SYSTEMS (TELECOM, DATA, AV & CCTV) |  | 25 | 2026-09-09 | 2026-10-08 |  |  | 2018-02-15 | 0 | 43146 | 100% | 0% | 272 | 272 | 0 |  | 7 | 0 | 0 | 7
PG-H-CON-EX-GN-E-90 | ELV Containment & Cabling Works | 3 | 2026-09-09 | 2026-09-12 |  |  | 1901-09-10 19:12 | 0 | 619.8 | 100% | 0% | 40 | 40 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-CON-EX-GN-E-100 | Fiber Optic Pull Box Installation | 3 | 2026-09-13 | 2026-09-15 |  |  | 1901-09-10 19:12 | 0 | 619.8 | 100% | 0% | 32 | 32 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-CON-EX-GN-E-110 | Telephone and Data Outlet Installation | 4 | 2026-09-16 | 2026-09-20 |  |  | 1910-03-06 19:12 | 0 | 3718.8 | 100% | 0% | 40 | 40 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-CON-EX-GN-E-120 | Telecom Equipment and AV HDMI Installation | 4 | 2026-09-21 | 2026-09-26 |  |  | 1941-09-30 02:53 | 0 | 15249.12 | 100% | 0% | 40 | 40 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-CON-EX-GN-E-130 | CCTV Rack / Cabinet Installation | 4 | 2026-09-27 | 2026-09-30 |  |  | 1903-12-16 11:31 | 0 | 1446.48 | 100% | 0% | 40 | 40 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-CON-EX-GN-E-140 | NVR and CCTV Monitor Installation | 4 | 2026-10-01 | 2026-10-05 |  |  | 1918-02-06 | 0 | 6612 | 100% | 0% | 40 | 40 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-CON-EX-GN-E-150 | IP Camera Installation | 3 | 2026-10-06 | 2026-10-08 |  |  | 1940-09-26 | 0 | 14880 | 100% | 0% | 40 | 40 | 0 | Yes | 1 | 0 | 0 | 1
FIRE ALARM SYSTEM |  | 32 | 2026-09-13 | 2026-10-20 |  |  | 1929-04-18 14:24 | 0 | 13924.2 | 76.86% | 0% | 136 | 86 | 0 |  | 4 | 0 | 0 | 4
PG-H-CON-EX-GN-E-160 | Fire Alarm Containment & Cabling | 8 | 2026-09-13 | 2026-09-21 |  |  | 1905-06-05 14:24 | 0 | 1983.6 | 100% | 0% | 32 | 32 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-CON-EX-GN-E-170 | Fire Alarm Control Panel (FACP) Installation | 8 | 2026-09-22 | 2026-10-01 |  |  | 1907-03-28 19:12 | 0 | 2644.8 | 100% | 0% | 24 | 24 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-CON-EX-GN-E-180 | Initiating Devices (Detectors & Manual Pull Station) | 8 | 2026-10-03 | 2026-10-11 |  |  | 6073.2 | 0 | 8097.6 | 75% | 0% | 40 | 30 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-CON-EX-GN-E-190 | Notification Appliances (Strobe with Sounder) | 8 | 2026-10-12 | 2026-10-20 |  |  | 0 | 0 | 1198.2 | 0% | 0% | 40 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PARKING WORK |  | 107 | 2026-06-17 | 2026-10-20 | 2026-06-17 |  | 38893.5 | 151252.5 | 190576.2 | 20.41% | 79.37% | 164 | 22 | 72 |  | 4 | 2 | 1 | 1
PG-H-CON-EX-GN-PR-20 | Interlock tiles(Completed) | 7 | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 38893.5 | 38893.5 | 38893.5 | 100% | 100% | 22 | 22 | 22 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-GN-PR-10 | Installlation of Parking Accessories | 5 | 2026-10-10 | 2026-10-14 | 2026-08-20 |  | 0 | 64822.5 | 86430 | 0% | 75% | 32 | 0 | 24 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-PR-20_R | Interlock tiles(Remaining) | 3 | 2026-10-12 | 2026-10-14 | 2026-07-11 | 2026-07-30 | 0 | 47536.5 | 47536.5 | 0% | 100% | 26 | 0 | 26 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-GN-PR-30 | Marking & Signages | 5 | 2026-10-15 | 2026-10-20 |  |  | 0 | 0 | 17716.2 | 0% | 0% | 84 | 0 | 0 | Yes | 1 | 0 | 0 | 1
SERVICE CONNECTION |  | 32 | 2026-10-21 | 2026-11-26 | 2026-07-30 |  | 0 | 5022 | 7440 | 0% | 67.5% | 236 | 0 | 162 |  | 4 | 1 | 2 | 1
PG-H-CON-EX-GN-SC-10 | Excavation & Trench Preparation | 8 | 2026-10-21 | 2026-10-29 | 2026-07-30 | 2026-08-27 | 0 | 2232 | 2232 | 0% | 100% | 92 | 0 | 92 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-GN-SC-20 | HDPE Pipe Laying & Valve Installation | 8 | 2026-10-31 | 2026-11-08 | 2026-08-20 |  | 0 | 1905-03-11 04:48 | 2232 | 0% | 85% | 48 | 0 | 41 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-GN-SC-30 | Connection to City Network | 8 | 2026-11-09 | 2026-11-17 |  |  | 0 | 0 | 1488 | 0% | 0% | 48 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-CON-EX-GN-SC-40 | Backfilling | 8 | 2026-11-18 | 2026-11-26 | 2026-08-27 |  | 0 | 892.8 | 1488 | 0% | 60% | 48 | 0 | 29 | Yes | 1 | 0 | 1 | 0
LANDSCAPING WORKS |  | 139 | 2026-05-31 | 2026-11-09 | 2026-05-30 |  | 890370.47 | 1069353.85 | 1252052.4 | 71.11% | 85.41% | 392 | 212 | 245 |  | 14 | 7 | 5 | 2
HARDSCAPE WORK |  | 139 | 2026-05-31 | 2026-11-09 | 2026-05-30 |  | 806778.77 | 971073.85 | 1046213.4 | 77.11% | 92.82% | 224 | 144 | 169 |  | 11 | 6 | 4 | 1
PG-H-CON-EX-LS-HS-10 | Curbstone Installation(Completed) | 22 | 2026-05-31 | 2026-06-24 | 2026-05-30 | 2026-06-24 | 251136 | 251136 | 251136 | 100% | 100% | 19 | 19 | 19 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-LS-HS-20 | Interlock Tiles Grey Scale with Black Marble Chips(Completed) | 22 | 2026-05-31 | 2026-06-24 | 2026-05-30 | 2026-06-24 | 36036 | 36036 | 36036 | 100% | 100% | 19 | 19 | 19 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-LS-HS-40 | Bike Path and Walking Path Construction(Completed) | 22 | 2026-05-31 | 2026-06-24 | 2026-05-30 | 2026-06-24 | 181071 | 181071 | 181071 | 100% | 100% | 26 | 26 | 26 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-LS-HS-50 | Install Recycled Precast Concrete Seats(Completed) | 22 | 2026-05-31 | 2026-06-24 | 2026-05-30 | 2026-06-24 | 11599.14 | 11599.14 | 11599.14 | 100% | 100% | 3 | 3 | 3 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-LS-HS-30 | Stamped Concrete Floor(Completed) | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 43470 | 43470 | 43470 | 100% | 100% | 16 | 16 | 16 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-LS-HS-10_R | Curbstone Installation(Remaining) | 8 | 2026-09-10 | 2026-09-19 | 2026-07-22 | 2026-08-27 | 2358-05-22 | 167424 | 167424 | 100% | 100% | 13 | 13 | 13 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-LS-HS-20_R | Interlock Tiles Grey Scale with Black Marble Chips(Remaining) | 13 | 2026-09-20 | 2026-10-05 | 2026-08-27 |  | 54054 | 37837.8 | 54054 | 100% | 70% | 29 | 29 | 20 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-LS-HS-30_R | Stamped Concrete Floor(Remaining) | 15 | 2026-09-20 | 2026-10-07 | 2026-07-30 |  | 2019-01-05 | 39123 | 43470 | 100% | 90% | 16 | 16 | 14 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-LS-HS-40_R | Bike Path and Walking Path Construction(Remaining) | 8 | 2026-10-08 | 2026-10-17 | 2026-07-09 |  | 1950-09-12 15:07 | 140741.55 | 148149 | 12.5% | 95% | 22 | 3 | 21 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-LS-HS-50_R | Install Recycled Precast Concrete Seats(Remaining) | 10 | 2026-10-18 | 2026-10-28 | 2026-07-30 |  | 0 | 62635.36 | 104392.26 | 0% | 60% | 29 | 0 | 17 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-LS-HS-60 | Install Recycled Precast Concrete Trash Bins | 10 | 2026-10-29 | 2026-11-09 |  |  | 0 | 0 | 5412 | 0% | 0% | 32 | 0 | 0 | Yes | 1 | 0 | 0 | 1
SOFTSCAPE WORK |  | 136 | 2026-06-03 | 2026-11-09 | 2026-06-03 |  | 83591.7 | 98280 | 205839 | 40.61% | 47.75% | 168 | 67 | 76 |  | 3 | 1 | 1 | 1
PG-H-CON-EX-LS-SS-20 | Lawn Area Preparation & Planting / Turfing(Completed) | 19 | 2026-06-03 | 2026-06-24 | 2026-06-03 | 2026-06-24 | 54600 | 54600 | 54600 | 100% | 100% | 42 | 42 | 42 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-LS-SS-10 | Planting Trees | 10 | 2026-10-06 | 2026-10-17 |  |  | 28991.7 | 0 | 96639 | 30% | 0% | 84 | 25 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-CON-EX-LS-SS-20_R | Lawn Area Preparation & Planting / Turfing(Remaining) | 7 | 2026-11-02 | 2026-11-09 | 2026-08-27 |  | 0 | 43680 | 54600 | 0% | 80% | 42 | 0 | 34 | Yes | 1 | 0 | 1 | 0
TANK WORKS |  | 107 | 2026-05-13 | 2026-09-19 | 2026-05-13 |  | 48290.4 | 11825.77 | 48290.4 | 100% | 24.49% | 628 | 628 | 484 |  | 13 | 8 | 2 | 3
SEPTIC TANK |  | 91 | 2026-05-13 | 2026-08-31 | 2026-05-13 |  | 7475.22 | 5723.59 | 7475.22 | 100% | 76.57% | 364 | 364 | 272 |  | 8 | 4 | 2 | 2
PG-H-CON-EX-TW-ST-10 | Excavation | 32 | 2026-05-13 | 2026-06-23 | 2026-05-13 | 2026-06-23 | 1900-09-08 04:19 | 252.18 | 252.18 | 100% | 100% | 92 | 92 | 92 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-TW-ST-20 | PCC / Lean Concrete laying | 27 | 2026-05-20 | 2026-06-24 | 2026-05-20 | 2026-06-24 | 1900-06-16 02:53 | 168.12 | 1900-06-16 02:53 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-TW-ST-30 | RCC Foundation(Completed) | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 1902-02-04 13:55 | 766.58 | 766.58 | 100% | 100% | 34 | 34 | 34 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-TW-ST-30_R | RCC Foundation(Remaining) | 6 | 2026-06-25 | 2026-07-01 | 2026-07-30 | 2026-08-27 | 1901-05-25 01:26 | 1901-05-25 01:26 | 511.06 | 100% | 100% | 22 | 22 | 22 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-TW-ST-40 | RCC Wall | 7 | 2026-07-02 | 2026-07-09 | 2026-08-14 |  | 2757.6 | 1906-01-14 01:55 | 2757.6 | 100% | 80% | 56 | 56 | 45 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-TW-ST-50 | RCC Slab | 7 | 2026-07-11 | 2026-07-18 | 2026-08-27 |  | 1907-02-11 09:07 | 1904-12-23 13:41 | 1907-02-11 09:07 | 100% | 70% | 56 | 56 | 39 | Yes | 1 | 0 | 1 | 0
PG-H-CON-EX-TW-ST-60 | Finishing Work | 7 | 2026-08-17 | 2026-08-24 |  |  | 252.18 | 0 | 252.18 | 100% | 0% | 24 | 24 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-CON-EX-TW-ST-70 | Backfilling | 6 | 2026-08-25 | 2026-08-31 |  |  | 168.12 | 0 | 168.12 | 100% | 0% | 40 | 40 | 0 | Yes | 1 | 0 | 0 | 1
WATER STORAGE TANK |  | 107 | 2026-05-13 | 2026-09-19 | 2026-05-13 |  | 2011-09-29 04:19 | 6102.18 | 40815.18 | 100% | 14.95% | 264 | 264 | 212 |  | 5 | 4 | 0 | 1
PG-H-CON-EX-TW-IR-10 | Excavation(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 1902-02-04 13:55 | 766.58 | 766.58 | 100% | 100% | 83 | 83 | 83 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-TW-IR-10_R | Excavation(Remaining) | 3 | 2026-08-29 | 2026-08-31 | 2026-07-08 | 2026-07-09 | 1900-03-25 04:19 | 85.18 | 85.18 | 100% | 100% | 9 | 9 | 9 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-TW-IR-20 | RCC Foundation | 6 | 2026-09-01 | 2026-09-07 | 2026-07-23 | 2026-08-27 | 1911-04-28 09:36 | 4136.4 | 4136.4 | 100% | 100% | 72 | 72 | 72 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-TW-IR-30 | Backfilling | 5 | 2026-09-08 | 2026-09-13 | 2026-08-14 | 2026-08-27 | 1114.02 | 1114.02 | 1114.02 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-EX-TW-IR-40 | GRP Water Tank Installation | 5 | 2026-09-14 | 2026-09-19 |  |  | 34713 | 0 | 34713 | 100% | 0% | 52 | 52 | 0 | Yes | 1 | 0 | 0 | 1
TOILET BUILDING WORKS |  | 127 | 2026-05-12 | 2026-10-12 | 2026-05-12 |  | 318499.87 | 260954.18 | 328493.58 | 96.96% | 79.44% | 1708 | 1695 | 1440 |  | 38 | 21 | 14 | 3
CIVIL WORK |  | 127 | 2026-05-12 | 2026-10-12 | 2026-05-12 |  | 220773.07 | 179859.9 | 230766.78 | 95.67% | 77.94% | 1100 | 1087 | 969 |  | 24 | 16 | 7 | 1
STRUCTURAL WORK |  | 58 | 2026-05-12 | 2026-07-22 | 2026-05-12 | 2026-07-23 | 37980 | 37980 | 37980 | 100% | 100% | 372 | 372 | 372 |  | 7 | 7 | 0 | 0
PG-H-CON-B-STR-10 | Excavation up to bottom of footing | 2 | 2026-05-12 | 2026-05-13 | 2026-05-12 | 2026-05-13 | 1900.8 | 1900.8 | 1900.8 | 100% | 100% | 92 | 92 | 92 | No | 1 | 1 | 0 | 0
PG-H-CON-B-STR-20 | Anti-termite treatment and Polyethene Sheet | 2 | 2026-05-12 | 2026-05-13 | 2026-05-12 | 2026-05-13 | 3294 | 3294 | 3294 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-H-CON-B-STR-30 | Backfilling with selected fill material (under footing) | 1 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 1900.8 | 1900.8 | 1900.8 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
PG-H-CON-B-STR-40 | Raft Foundation Work | 27 | 2026-05-13 | 2026-06-17 | 2026-05-13 | 2026-06-17 | 2534.4 | 2534.4 | 2534.4 | 100% | 100% | 64 | 64 | 64 | No | 1 | 1 | 0 | 0
PG-H-CON-B-STR-50 | Autoclaved aerated panel (walls) | 4 | 2026-07-13 | 2026-07-16 | 2026-07-11 | 2026-07-12 | 11340 | 11340 | 11340 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-B-STR-60 | Autoclaved aerated panel (ceiling) | 3 | 2026-07-18 | 2026-07-20 | 2026-07-12 | 2026-07-16 | 8505 | 8505 | 8505 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-B-STR-70 | Autoclaved aerated panel (parapet) | 2 | 2026-07-21 | 2026-07-22 | 2026-07-12 | 2026-07-23 | 8505 | 8505 | 8505 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
ARCHITECTURAL WORK |  | 69 | 2026-07-23 | 2026-10-12 | 2026-07-31 |  | 182793.07 | 141879.9 | 192786.78 | 94.82% | 73.59% | 728 | 715 | 597 |  | 17 | 9 | 7 | 1
GENERAL FINISHES |  | 69 | 2026-07-23 | 2026-10-12 | 2026-07-31 |  | 86510.6 | 50911.8 | 87769.2 | 98.57% | 58.01% | 376 | 368 | 320 |  | 8 | 4 | 4 | 0
PG-H-CON-B-AR-GF-10 | Block Works | 4 | 2026-07-23 | 2026-07-27 | 2026-07-31 | 2026-08-05 | 2484 | 2484 | 2484 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-B-AR-GF-20 | Plaster | 4 | 2026-08-08 | 2026-08-11 | 2026-08-06 | 2026-08-07 | 4427.4 | 4427.4 | 4427.4 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-B-AR-GF-30 | False Ceiling Installation & Finishing | 8 | 2026-08-20 | 2026-08-29 | 2026-08-20 | 2026-09-15 | 1902-05-22 14:24 | 873.6 | 873.6 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-B-AR-GF-40 | Wall Paint | 3 | 2026-09-09 | 2026-09-12 | 2026-08-20 |  | 1908-02-05 | 1906-06-23 09:36 | 2958 | 100% | 80% | 48 | 48 | 38 | No | 1 | 0 | 1 | 0
PG-H-CON-B-AR-GF-50 | Epoxy Flooring | 7 | 2026-09-13 | 2026-09-20 | 2026-08-20 |  | 1900-09-29 14:24 | 218.88 | 273.6 | 100% | 80% | 56 | 56 | 45 | No | 1 | 0 | 1 | 0
PG-H-CON-B-AR-GF-60 | Install Doors & Windows | 5 | 2026-09-21 | 2026-09-27 | 2026-08-27 |  | 1936-05-03 19:12 | 1929-01-26 00:58 | 13273.8 | 100% | 80% | 32 | 32 | 26 | No | 1 | 0 | 1 | 0
PG-H-CON-B-AR-GF-70 | Facade Finishing Work | 18 | 2026-09-21 | 2026-10-12 | 2026-08-20 | 2026-09-16 | 1917-03-24 | 7551.6 | 7551.6 | 83.33% | 100% | 48 | 40 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-B-AR-GF-80 | Lockers and Furniture Installation | 7 | 2026-09-28 | 2026-10-05 | 46299 |  | 55927.2 | 22370.88 | 55927.2 | 100% | 40% | 48 | 48 | 19 | Yes | 1 | 0 | 1 | 0
WET AREA FINISHES |  | 51 | 2026-08-12 | 2026-10-11 | 2026-08-07 |  | 72388.67 | 79515.3 | 81123.78 | 89.23% | 98.02% | 216 | 211 | 206 |  | 6 | 5 | 1 | 0
PG-H-CON-B-AR-WF-10 | False Ceiling Installation & Finishing | 4 | 2026-08-12 | 2026-08-16 | 2026-08-20 | 2026-09-16 | 1907-12-07 | 2898 | 2898 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-B-AR-WF-20 | Wall Tiles and Partition Work | 3 | 2026-09-13 | 2026-09-15 | 2026-08-07 | 2026-08-14 | 1958-04-08 04:48 | 21283.2 | 21283.2 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-B-AR-WF-30 | Waterproofing on Floor | 2 | 2026-09-16 | 2026-09-17 | 2026-08-14 | 2026-09-16 | 1915-11-01 | 5784 | 5784 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-H-CON-B-AR-WF-40 | Floor Tiles Works | 10 | 2026-09-19 | 2026-09-30 | 2026-08-14 | 2026-09-16 | 1917-10-06 | 1917-10-06 | 6489 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-H-CON-B-AR-WF-50 | Toliet accessories Installation Works | 9 | 2026-10-01 | 2026-10-11 | 2026-08-27 | 2026-09-16 | 1983-09-13 20:53 | 39307.98 | 39307.98 | 77.78% | 100% | 24 | 19 | 24 | No | 1 | 1 | 0 | 0
PG-H-CON-B-AR-WF-60 | Install Doors | 4 | 2026-10-01 | 2026-10-05 | 2026-08-27 |  | 5361.6 | 3753.12 | 5361.6 | 100% | 70% | 32 | 32 | 22 | No | 1 | 0 | 1 | 0
ROOF FINISHES |  | 14 | 2026-09-19 | 2026-10-05 | 2026-08-20 |  | 1965-05-31 19:12 | 1931-05-09 19:12 | 23893.8 | 100% | 47.93% | 136 | 136 | 70 |  | 3 | 0 | 2 | 1
PG-H-CON-B-AR-RF-10 | Waterproofing on Floor | 4 | 2026-09-19 | 2026-09-22 | 2026-08-20 |  | 1911-05-20 | 1909-02-07 09:36 | 4158 | 100% | 80% | 32 | 32 | 26 | No | 1 | 0 | 1 | 0
PG-H-CON-B-AR-RF-20 | Epoxy Flooring and Finishes | 2 | 2026-09-24 | 2026-09-26 | 2026-08-27 |  | 1927-10-23 | 8126.4 | 10158 | 100% | 80% | 56 | 56 | 45 | No | 1 | 0 | 1 | 0
PG-H-CON-B-AR-RF-30 | Steel ladder and Steel roof scupper Installation | 2 | 2026-10-04 | 2026-10-05 |  |  | 1926-03-21 19:12 | 0 | 9577.8 | 100% | 0% | 48 | 48 | 0 | Yes | 1 | 0 | 0 | 1
MEP WORK |  | 60 | 2026-07-28 | 2026-10-06 | 2026-07-22 |  | 97726.8 | 81094.28 | 97726.8 | 100% | 82.98% | 608 | 608 | 471 |  | 14 | 5 | 7 | 2
MECANICAL WORKS |  | 60 | 2026-07-28 | 2026-10-06 | 2026-07-22 |  | 79479.48 | 65286.52 | 79479.48 | 100% | 82.14% | 400 | 400 | 287 |  | 9 | 4 | 3 | 2
FIRE FIGHTING SYSTEM |  | 1 | 2026-10-06 | 2026-10-06 |  |  | 1900-05-15 06:14 | 0 | 136.26 | 100% | 0% | 32 | 32 | 0 |  | 1 | 0 | 0 | 1
PG-H-CON-B-GF-FF-10 | Fire Extinguisher Installation | 1 | 2026-10-06 | 2026-10-06 |  |  | 1900-05-15 06:14 | 0 | 136.26 | 100% | 0% | 32 | 32 | 0 | Yes | 1 | 0 | 0 | 1
SEWER AND DRAINAGE SYSTEM |  | 18 | 2026-08-03 | 2026-08-23 | 2026-07-22 |  | 11290.02 | 7580.44 | 11290.02 | 100% | 67.14% | 144 | 144 | 89 |  | 3 | 1 | 1 | 1
PG-H-CON-B-GF-DR-10 | Sewer and Drainge System Main Lines Installation | 2 | 2026-08-03 | 2026-08-04 | 2026-07-30 |  | 1908-10-29 17:17 | 2741.86 | 3225.72 | 100% | 85% | 48 | 48 | 41 | No | 1 | 0 | 1 | 0
PG-H-CON-B-GF-DR-20 | Sewer and Drainge System Pipes and fittings Installation | 2 | 2026-08-18 | 2026-08-19 | 2026-07-22 | 2026-08-05 | 4838.58 | 4838.58 | 4838.58 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-B-GF-DR-30 | Sanitaryware Installation (Final Fix) | 2 | 2026-08-22 | 2026-08-23 |  |  | 1908-10-29 17:17 | 0 | 3225.72 | 100% | 0% | 48 | 48 | 0 | No | 1 | 0 | 0 | 1
HVAC SYSTEM |  | 16 | 2026-07-28 | 2026-08-15 | 2026-08-13 |  | 12127.2 | 1924-10-13 06:43 | 12127.2 | 100% | 74.65% | 96 | 96 | 77 |  | 2 | 1 | 1 | 0
PG-H-CON-B-GF-AC-10 | Duct Work and Exhaust Fan Installation | 3 | 2026-07-28 | 2026-07-30 | 2026-08-13 | 2026-08-20 | 4442.4 | 4442.4 | 4442.4 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-B-GF-AC-20 | Split AC, Grills & Diffuser Installation | 3 | 2026-08-12 | 2026-08-15 | 46291 |  | 7684.8 | 4610.88 | 7684.8 | 100% | 60% | 48 | 48 | 29 | No | 1 | 0 | 1 | 0
WATER SUPPLY SYSTEM |  | 18 | 2026-08-01 | 2026-08-20 | 2026-07-30 |  | 55926 | 48652.8 | 55926 | 100% | 86.99% | 128 | 128 | 122 |  | 3 | 2 | 1 | 0
PG-H-CON-B-GF-WS-10 | Water Supply Main Lines Installation | 2 | 2026-08-01 | 2026-08-02 | 2026-07-30 | 2026-07-31 | 5702.4 | 5702.4 | 5702.4 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-B-GF-WS-20 | Water Supply Pipes Installation (Cold and Hot Water) | 2 | 2026-08-16 | 2026-08-17 | 2026-07-30 | 2026-08-06 | 1937-12-08 14:24 | 13857.6 | 13857.6 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-B-GF-WS-30 | Water Supply Accesories and Booster pump Installation | 3 | 2026-08-18 | 2026-08-20 | 2026-08-27 |  | 1999-07-25 | 29092.8 | 36366 | 100% | 80% | 32 | 32 | 26 | No | 1 | 0 | 1 | 0
ELECTRICAL WORKS |  | 30 | 2026-08-05 | 2026-09-08 | 2026-08-12 |  | 18247.32 | 15807.76 | 18247.32 | 100% | 86.63% | 208 | 208 | 184 |  | 5 | 1 | 4 | 0
PG-H-CON-B-GF-EL-10 | Pipes & Conduits Installation | 2 | 2026-08-05 | 2026-08-06 | 2026-08-12 | 2026-08-14 | 1983.6 | 1983.6 | 1983.6 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-H-CON-B-GF-EL-20 | Electrical Light Fixtures Installation | 2 | 2026-08-27 | 2026-08-29 | 2026-08-20 |  | 1905-06-05 14:24 | 1686.06 | 1983.6 | 100% | 85% | 48 | 48 | 41 | No | 1 | 0 | 1 | 0
PG-H-CON-B-GF-EL-30 | Fire Alarm Devices Installation | 3 | 2026-08-30 | 2026-09-01 | 2026-08-20 |  | 1905-06-05 14:24 | 1686.06 | 1983.6 | 100% | 85% | 32 | 32 | 27 | No | 1 | 0 | 1 | 0
PG-H-CON-B-GF-EL-40 | Telecom & CCTV Devices Installation | 3 | 2026-09-02 | 2026-09-05 | 2026-08-20 |  | 4959 | 4215.15 | 4959 | 100% | 85% | 40 | 40 | 34 | No | 1 | 0 | 1 | 0
PG-H-CON-B-GF-EL-50 | Electrical & ELV Wiring Works | 3 | 2026-09-06 | 2026-09-08 | 2026-08-20 |  | 7337.52 | 6236.89 | 7337.52 | 100% | 85% | 40 | 40 | 34 | No | 1 | 0 | 1 | 0
PROJECT CLOSOUT |  | 171 | 2026-05-25 | 2026-12-16 | 2026-05-25 |  | 20443.96 | 75642.64 | 681465.2 | 3% | 11.1% | 384 | 11 | 41 |  | 7 | 1 | 1 | 5
PG-H-PCL-10 | Testing, Commessioning for All Systems(Completed) | 23 | 2026-05-25 | 2026-06-24 | 2026-05-25 | 2026-06-24 | 20443.96 | 20443.96 | 20443.96 | 100% | 100% | 11 | 11 | 11 | No | 1 | 1 | 0 | 0
PG-H-PCL-10_R | Testing, Commessioning for All Systems(Remaining) | 10 | 2026-11-02 | 2026-11-14 | 2026-08-06 |  | 0 | 55198.68 | 183995.6 | 0% | 30% | 101 | 0 | 30 | Yes | 1 | 0 | 1 | 0
PG-H-PCL-20 | As-Built Drawings | 18 | 2026-11-14 | 2026-12-05 |  |  | 0 | 0 | 68146.52 | 0% | 0% | 0 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-PCL-30 | Snag list Submission | 8 | 2026-11-14 | 2026-11-23 |  |  | 0 | 0 | 136293.04 | 0% | 0% | 136 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-PCL-40 | Snag list Closeout | 14 | 2026-11-23 | 2026-12-09 |  |  | 0 | 0 | 136293.04 | 0% | 0% | 136 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-PCL-50 | Issuing Approvals | 3 | 2026-12-09 | 2026-12-13 |  |  | 0 | 0 | 68146.52 | 0% | 0% | 0 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-H-PCL-60 | Handing Over | 3 | 2026-12-13 | 2026-12-16 |  |  | 0 | 0 | 68146.52 | 0% | 0% | 0 | 0 | 0 | Yes | 1 | 0 | 0 | 1
TABUK |  | 250 | 2026-02-17 | 2026-12-16 | 2026-02-17 |  | 8011119.71 | 6289773.95 | 11357801 | 70.53% | 55.38% | 8496 | 6146 | 5907 |  | 671 | 556 | 77 | 38
MOBILIZATION |  | 44 | 2026-02-17 | 2026-04-15 | 2026-02-17 | 2026-04-14 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 9 | 9 | 0 | 0
TEMPORARY CAMP |  | 43 | 2026-02-17 | 2026-04-14 | 2026-02-17 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-MOB-CAM-10 | Temporary Underground Utilities works | 43 | 2026-02-17 | 2026-04-14 | 2026-02-17 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-MOB-CAM-20 | Temporary Porta-Cabins | 36 | 2026-02-26 | 2026-04-14 | 2026-02-26 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-MOB-CAM-30 | Temporary Toilets | 36 | 2026-02-26 | 2026-04-14 | 2026-02-26 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-MOB-CAM-40 | Temporary Mosque | 28 | 2026-03-08 | 2026-04-14 | 2026-03-08 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SITE OFFICES |  | 44 | 2026-02-17 | 2026-04-15 | 2026-02-17 | 2026-04-14 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-T-MOB-SO-10 | Temporary Underground Utilities works | 44 | 2026-02-17 | 2026-04-15 | 2026-02-17 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-MOB-SO-20 | Temporary Porta-Cabins | 38 | 2026-02-25 | 2026-04-15 | 2026-02-25 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-MOB-SO-30 | Temporary Toilets | 38 | 2026-02-25 | 2026-04-15 | 2026-02-25 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-MOB-SO-40 | Temporary Mosque | 32 | 2026-03-04 | 2026-04-15 | 2026-03-04 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-MOB-SO-50 | Car Parking Area | 25 | 2026-03-12 | 2026-04-15 | 2026-03-12 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
GENERAL REQUIEREMENTS |  | 44 | 2026-02-17 | 2026-04-15 | 2026-02-17 | 2026-04-14 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-GEN-20 | HSSE Submission Plan | 35 | 2026-02-17 | 2026-04-05 | 2026-02-17 | 2026-04-04 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-GEN-30 | Surveying report Submission Plan | 44 | 2026-02-17 | 2026-04-15 | 2026-02-17 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-GEN-40 | Baseline Submission | 6 | 2026-02-28 | 2026-03-07 | 2026-02-28 | 2026-03-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-GEN-10 | QA/QC Submission Plan | 16 | 2026-03-12 | 2026-04-05 | 2026-03-12 | 2026-04-04 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ENGINEERING |  | 143 | 2026-02-17 | 2026-08-12 | 2026-02-17 | 2026-09-17 | 340734.03 | 340734.03 | 340734.03 | 100% | 100% | 0 | 0 | 0 |  | 264 | 264 | 0 | 0
SHOP DRAWINGS SUBMITTALS |  | 136 | 2026-02-17 | 2026-08-04 | 2026-02-17 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 62 | 62 | 0 | 0
STRUCTURAL DRAWINGS |  | 121 | 2026-02-17 | 2026-07-18 | 2026-02-17 | 2026-07-03 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PROJECT FENCE |  | 63 | 2026-02-17 | 2026-05-07 | 2026-02-17 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ST-SD-SB-10 | Excavation Drawings | 63 | 2026-02-17 | 2026-05-07 | 2026-02-17 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ST-SD-SB-20 | Foundation Drawings | 61 | 2026-02-19 | 2026-05-07 | 2026-02-19 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PADEL PLAYGROUND FENCE |  | 63 | 2026-02-17 | 2026-05-07 | 2026-02-17 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ST-SD-SB-30 | Excavation Drawings | 63 | 2026-02-17 | 2026-05-07 | 2026-02-17 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ST-SD-SB-40 | Foundation Drawings | 61 | 2026-02-19 | 2026-05-07 | 2026-02-19 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 20 | 2026-06-25 | 2026-07-18 | 2026-07-01 | 2026-07-03 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ST-SD-SB-50 | Excavation Drawings | 10 | 2026-06-25 | 2026-07-06 | 2026-07-01 | 2026-07-03 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ST-SD-SB-60 | Foundation Drawings | 10 | 2026-07-07 | 2026-07-18 | 2026-07-01 | 2026-07-03 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
TOILET BUILDING |  | 41 | 2026-02-19 | 2026-04-14 | 2026-02-19 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ST-SD-SB-70 | Excavation Drawings | 41 | 2026-02-19 | 2026-04-14 | 2026-02-19 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ST-SD-SB-80 | Foundation Drawings | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
WATER STORAGE TANK |  | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ST-SD-SB-90 | Excavation Drawings | 39 | 2026-02-23 | 2026-04-14 | 2026-02-23 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ST-SD-SB-100 | Foundation Drawings | 37 | 2026-02-25 | 2026-04-14 | 2026-02-25 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SEPTIC TANK |  | 57 | 2026-02-25 | 2026-05-07 | 2026-02-25 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ST-SD-SB-110 | Reinforcement Detail Drawings | 57 | 2026-02-25 | 2026-05-07 | 2026-02-25 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ST-SD-SB-120 | Concrete Detail Drawings | 54 | 2026-03-01 | 2026-05-07 | 2026-03-01 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL DRAWINGS |  | 132 | 2026-02-23 | 2026-08-04 | 2026-02-23 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 13 | 13 | 0 | 0
TOILET BUILDING |  | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 10 | 0 | 0
PG-T-EN-AR-SD-SB-10 | Ground Floor Plan | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-SB-20 | Roof Floor Plan | 35 | 2026-02-28 | 2026-04-14 | 2026-02-28 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-SB-50 | Floor Finish Layout | 36 | 2026-02-28 | 2026-04-14 | 2026-02-28 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-SB-60 | Reflected Ceiling Layout | 36 | 2026-02-28 | 2026-04-15 | 2026-02-28 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-SB-70 | Enlarged Toilets Layout | 36 | 2026-02-28 | 2026-04-15 | 2026-02-28 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-SB-30 | Elevations | 33 | 2026-03-03 | 2026-04-15 | 2026-03-03 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-SB-80 | Doors & Windows Schedule | 33 | 2026-03-03 | 2026-04-15 | 2026-03-03 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-SB-90 | Aluminum Work | 33 | 2026-03-03 | 2026-04-15 | 2026-03-03 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-SB-100 | Cladding Details | 32 | 2026-03-03 | 2026-04-14 | 2026-03-03 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-SB-40 | Sections | 31 | 2026-03-05 | 2026-04-15 | 2026-03-05 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 15 | 2026-07-19 | 2026-08-04 | 2026-08-05 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-EN-AR-SD-SB-110 | Membrane & Insulation Details | 15 | 2026-07-19 | 2026-08-04 | 2026-08-05 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-SB-120 | Steel Cable System | 15 | 2026-07-19 | 2026-08-04 | 2026-08-05 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-SB-130 | Doors & Access Sytem Drawings | 15 | 2026-07-19 | 2026-08-04 | 2026-08-05 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
LANDSCAPE DRAWINGS |  | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 13 | 13 | 0 | 0
PG-T-EN-LS-SD-SB-10 | Hardscape Layout Plan | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-SB-20 | Interlock Tile Details | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-SB-30 | Stamped Concrete Pattern & Section | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-SB-40 | Tartan Flooring Layout & Details | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-SB-50 | Bike Path Layout & Details | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-SB-60 | Walking Path layout & Details | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-SB-70 | Tree Planting Plan & Details | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-SB-80 | Traffic Sign Location & Details | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-SB-90 | Football Playground Layout | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-SB-100 | Padel Playground Layout | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-SB-110 | Basketball Playground Layout | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-SB-120 | Playground Details | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-SB-130 | Padel Fence Elevation & Details | 40 | 2026-02-23 | 2026-04-15 | 2026-02-23 | 2026-04-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MECHANICAL DRAWINGS |  | 108 | 2026-02-28 | 2026-07-12 | 2026-02-28 | 2026-07-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 10 | 0 | 0
WATER SUPPLY SYSTEM |  | 32 | 2026-02-28 | 2026-04-11 | 2026-02-28 | 2026-04-09 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-EN-ME-SD-SB-20 | Pump Room Layout | 32 | 2026-02-28 | 2026-04-11 | 2026-02-28 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-SB-10 | Cold & Hot Water Piping Layout | 28 | 2026-03-04 | 2026-04-11 | 2026-03-04 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-SB-30 | Booster Pump Details | 28 | 2026-03-04 | 2026-04-11 | 2026-03-04 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-SB-40 | GRP Water Tank Details | 24 | 2026-03-09 | 2026-04-11 | 2026-03-09 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SEWER AND DRAINAGE SYSTEM |  | 28 | 2026-03-04 | 2026-04-11 | 2026-03-04 | 2026-04-09 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-EN-ME-SD-SB-50 | Drainage Layout | 28 | 2026-03-04 | 2026-04-11 | 2026-03-04 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-SB-60 | Floor Drains & Cleanouts Details | 24 | 2026-03-09 | 2026-04-11 | 2026-03-09 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-SB-70 | Inspection Chamber Details | 21 | 2026-03-12 | 2026-04-11 | 2026-03-12 | 2026-04-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION SYSTEM |  | 47 | 2026-03-09 | 2026-05-07 | 2026-03-09 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ME-SD-SB-80 | HDPE Pipe Routing | 47 | 2026-03-09 | 2026-05-07 | 2026-03-09 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-SB-90 | Irrigation Network Layout | 44 | 2026-03-12 | 2026-05-07 | 2026-03-12 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 15 | 2026-06-25 | 2026-07-12 | 2026-07-02 | 2026-07-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-SB-100 | Air Package and HVAC System Drawings | 15 | 2026-06-25 | 2026-07-12 | 2026-07-02 | 2026-07-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL DRAWINGS |  | 66 | 2026-05-10 | 2026-07-29 | 2026-05-10 | 2026-07-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 14 | 14 | 0 | 0
POWER AND LIGHTING SYSTEM |  | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-EN-EL-SD-SB-10 | Main Distribution Board (MDB) Layout | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-SB-20 | Pump Room Power Panel | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-SB-30 | Street Lighting Power Panel | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-SB-40 | Site Lighting Pole Layout | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELV SYSTEM |  | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-EN-EL-SD-SB-50 | Telecom & Data Layout | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-SB-60 | CCTV Camera Layout | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-SB-70 | Access Control Layout | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-SB-80 | AV System Layout | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE ALARM SYSTEM |  | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-EN-EL-SD-SB-90 | Fire Alarm Layout | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-SB-100 | Detector & Manual Call Point Details | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-SB-110 | Control Panel Wiring Diagram | 10 | 2026-05-10 | 2026-05-21 | 2026-05-10 | 2026-05-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 30 | 2026-06-25 | 2026-07-29 | 2026-07-08 | 2026-07-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-EN-EL-SD-SB-130 | Generators Details | 15 | 2026-06-25 | 2026-07-12 | 2026-07-08 | 2026-07-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-SB-120 | Power & Lighting System Drawings | 15 | 2026-07-13 | 2026-07-29 | 2026-07-08 | 2026-07-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-SB-140 | Smart Dome System Drawings | 15 | 2026-07-13 | 2026-07-29 | 2026-07-08 | 2026-07-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SHOP DRAWINGS APPROVALS |  | 141 | 2026-02-19 | 2026-08-12 | 2026-02-19 | 2026-09-02 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 62 | 62 | 0 | 0
STRUCTURAL DRAWINGS |  | 124 | 2026-02-19 | 2026-07-23 | 2026-02-19 | 2026-07-11 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PROJECT FENCE |  | 61 | 2026-02-19 | 2026-05-07 | 2026-02-19 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ST-SD-AP-10 | Excavation Drawings | 61 | 2026-02-19 | 2026-05-07 | 2026-02-19 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ST-SD-AP-20 | Foundation Drawings | 58 | 2026-02-24 | 2026-05-07 | 2026-02-24 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PADEL PLAYGROUND FENCE |  | 61 | 2026-02-19 | 2026-05-07 | 2026-02-19 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ST-SD-AP-30 | Excavation Drawings | 61 | 2026-02-19 | 2026-05-07 | 2026-02-19 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ST-SD-AP-40 | Foundation Drawings | 58 | 2026-02-24 | 2026-05-07 | 2026-02-24 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 15 | 2026-07-07 | 2026-07-23 | 2026-07-05 | 2026-07-11 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ST-SD-AP-50 | Excavation Drawings | 5 | 2026-07-07 | 2026-07-12 | 2026-07-08 | 2026-07-11 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ST-SD-AP-60 | Foundation Drawings | 5 | 2026-07-19 | 2026-07-23 | 2026-07-05 | 2026-07-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
TOILET BUILDING |  | 42 | 2026-02-23 | 2026-04-18 | 2026-02-23 | 2026-04-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ST-SD-AP-70 | Excavation Drawings | 42 | 2026-02-23 | 2026-04-18 | 2026-02-23 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ST-SD-AP-80 | Foundation Drawings | 39 | 2026-02-26 | 2026-04-18 | 2026-02-26 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
WATER STORAGE TANK |  | 40 | 2026-02-25 | 2026-04-18 | 2026-02-25 | 2026-04-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ST-SD-AP-90 | Excavation Drawings | 40 | 2026-02-25 | 2026-04-18 | 2026-02-25 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ST-SD-AP-100 | Foundation Drawings | 37 | 2026-03-01 | 2026-04-18 | 2026-03-01 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SEPTIC TANK |  | 54 | 2026-03-01 | 2026-05-07 | 2026-03-01 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ST-SD-AP-110 | Reinforcement Detail Drawings | 54 | 2026-03-01 | 2026-05-07 | 2026-03-01 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ST-SD-AP-120 | Concrete Detail Drawings | 51 | 2026-03-04 | 2026-05-07 | 2026-03-04 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL DRAWINGS |  | 135 | 2026-02-28 | 2026-08-12 | 2026-02-28 | 2026-09-02 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 13 | 13 | 0 | 0
TOILET BUILDING |  | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 10 | 0 | 0
PG-T-EN-AR-SD-AP-10 | Ground Floor Plan | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-AP-20 | Roof Floor Plan | 35 | 2026-03-03 | 2026-04-18 | 2026-03-03 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-AP-50 | Floor Finish Layout | 33 | 2026-03-05 | 2026-04-18 | 2026-03-05 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-AP-60 | Reflected Ceiling Layout | 33 | 2026-03-05 | 2026-04-18 | 2026-03-05 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-AP-70 | Enlarged Toilets Layout | 33 | 2026-03-05 | 2026-04-18 | 2026-03-05 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-AP-30 | Elevations | 32 | 2026-03-07 | 2026-04-18 | 2026-03-07 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-AP-80 | Doors & Windows Schedule | 32 | 2026-03-07 | 2026-04-18 | 2026-03-07 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-AP-90 | Aluminum Work | 31 | 2026-03-08 | 2026-04-18 | 2026-03-08 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-AP-100 | Cladding Details | 31 | 2026-03-08 | 2026-04-18 | 2026-03-08 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-AP-40 | Sections | 29 | 2026-03-10 | 2026-04-18 | 2026-03-10 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 7 | 2026-08-05 | 2026-08-12 | 2026-08-06 | 2026-09-02 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-EN-AR-SD-AP-110 | Membrane & Insulation Details | 7 | 2026-08-05 | 2026-08-12 | 2026-08-06 | 2026-09-02 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-AP-120 | Steel Cable System | 7 | 2026-08-05 | 2026-08-12 | 2026-08-06 | 2026-09-02 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-AR-SD-AP-130 | Doors & Access Sytem Drawings | 7 | 2026-08-05 | 2026-08-12 | 2026-08-06 | 2026-09-02 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
LANDSCAPE DRAWINGS |  | 39 | 2026-02-26 | 2026-04-18 | 2026-02-26 | 2026-04-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 13 | 13 | 0 | 0
PG-T-EN-LS-SD-AP-50 | Bike Path Layout & Details | 39 | 2026-02-26 | 2026-04-18 | 2026-02-26 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-AP-60 | Walking Path layout & Details | 39 | 2026-02-26 | 2026-04-18 | 2026-02-26 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-AP-80 | Traffic Sign Location & Details | 39 | 2026-02-26 | 2026-04-18 | 2026-02-26 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-AP-130 | Padel Fence Elevation & Details | 39 | 2026-02-26 | 2026-04-18 | 2026-02-26 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-AP-10 | Hardscape Layout Plan | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-AP-40 | Tartan Flooring Layout & Details | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-AP-70 | Tree Planting Plan & Details | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-AP-90 | Football Playground Layout | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-AP-100 | Padel Playground Layout | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-AP-110 | Basketball Playground Layout | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-AP-120 | Playground Details | 38 | 2026-02-28 | 2026-04-18 | 2026-02-28 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-AP-20 | Interlock Tile Details | 30 | 2026-03-09 | 2026-04-18 | 2026-03-09 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-LS-SD-AP-30 | Stamped Concrete Pattern & Section | 24 | 2026-03-16 | 2026-04-18 | 2026-03-16 | 2026-04-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MECHANICAL DRAWINGS |  | 110 | 2026-03-09 | 2026-07-23 | 2026-03-09 | 2026-07-18 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 10 | 10 | 0 | 0
WATER SUPPLY SYSTEM |  | 27 | 2026-03-09 | 2026-04-14 | 2026-03-09 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-EN-ME-SD-AP-10 | Cold & Hot Water Piping Layout | 27 | 2026-03-09 | 2026-04-14 | 2026-03-09 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-AP-30 | Booster Pump Details | 26 | 2026-03-10 | 2026-04-14 | 2026-03-10 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-AP-40 | GRP Water Tank Details | 23 | 2026-03-14 | 2026-04-14 | 2026-03-14 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-AP-20 | Pump Room Layout | 21 | 2026-03-16 | 2026-04-14 | 2026-03-16 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SEWER AND DRAINAGE SYSTEM |  | 27 | 2026-03-09 | 2026-04-14 | 2026-03-09 | 2026-04-13 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-EN-ME-SD-AP-50 | Drainage Layout | 27 | 2026-03-09 | 2026-04-14 | 2026-03-09 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-AP-60 | Floor Drains & Cleanouts Details | 21 | 2026-03-16 | 2026-04-14 | 2026-03-16 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-AP-70 | Inspection Chamber Details | 21 | 2026-03-16 | 2026-04-14 | 2026-03-16 | 2026-04-13 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION SYSTEM |  | 44 | 2026-03-12 | 2026-05-07 | 2026-03-12 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-EN-ME-SD-AP-80 | HDPE Pipe Routing | 44 | 2026-03-12 | 2026-05-07 | 2026-03-12 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-AP-90 | Irrigation Network Layout | 40 | 2026-03-17 | 2026-05-07 | 2026-03-17 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 10 | 2026-07-13 | 2026-07-23 | 2026-07-13 | 2026-07-18 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-T-EN-ME-SD-AP-100 | Air Package and HVAC System Drawings | 10 | 2026-07-13 | 2026-07-23 | 2026-07-13 | 2026-07-18 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL DRAWINGS |  | 73 | 2026-05-11 | 2026-08-08 | 2026-05-11 | 2026-07-19 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 14 | 14 | 0 | 0
POWER AND LIGHTING SYSTEM |  | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-EN-EL-SD-AP-10 | Main Distribution Board (MDB) Layout | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-AP-20 | Pump Room Power Panel | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-AP-30 | Street Lighting Power Panel | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-AP-40 | Site Lighting Pole Layout | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELV SYSTEM |  | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-EN-EL-SD-AP-50 | Telecom & Data Layout | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-AP-60 | CCTV Camera Layout | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-AP-70 | Access Control Layout | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-AP-80 | AV System Layout | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE ALARM SYSTEM |  | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-EN-EL-SD-AP-90 | Fire Alarm Layout | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-AP-100 | Detector & Manual Call Point Details | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-AP-110 | Control Panel Wiring Diagram | 28 | 2026-05-11 | 2026-06-17 | 2026-05-11 | 2026-06-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
AIR DOME |  | 23 | 2026-07-13 | 2026-08-08 | 2026-07-13 | 2026-07-19 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-EN-EL-SD-AP-130 | Generators Details | 8 | 2026-07-13 | 2026-07-21 | 2026-07-13 | 2026-07-19 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-AP-120 | Power & Lighting System Drawings | 8 | 2026-07-30 | 2026-08-08 | 2026-07-13 | 2026-07-19 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-EN-EL-SD-AP-140 | Smart Dome System Drawings | 8 | 2026-07-30 | 2026-08-08 | 2026-07-13 | 2026-07-19 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MATERIAL SUBMITTALS |  | 115 | 2026-02-17 | 2026-07-11 | 2026-02-17 | 2026-09-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 70 | 70 | 0 | 0
LONG LEAD ITEMS |  | 115 | 2026-02-17 | 2026-07-11 | 2026-02-17 | 2026-09-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 32 | 32 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 57 | 2026-02-25 | 2026-05-07 | 2026-02-25 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-PR-LL-LS-MS-20 | Benches, Seats (Rectangular & Circular) | 57 | 2026-02-25 | 2026-05-07 | 2026-02-25 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-MS-30 | Fence, gates and accessories | 50 | 2026-03-05 | 2026-05-07 | 2026-03-05 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-MS-10 | Bike and Walk Path Materials | 50 | 2026-03-05 | 2026-05-07 | 2026-03-05 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 110 | 2026-02-17 | 2026-07-05 | 2026-02-17 | 2026-09-02 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 6 | 6 | 0 | 0
PG-T-PR-LL-SP-MS-50 | Air Dome Materials(Completed) | 101 | 2026-02-17 | 2026-06-25 | 2026-02-17 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MS-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc) | 49 | 2026-03-07 | 2026-05-07 | 2026-03-07 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MS-20 | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc) | 49 | 2026-03-07 | 2026-05-07 | 2026-03-07 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MS-30 | Padel Playgound Materials (Flooring, fence, tempered glass, etc) | 49 | 2026-03-07 | 2026-05-07 | 2026-03-07 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MS-40 | Tartan Floor | 49 | 2026-03-07 | 2026-05-07 | 2026-03-07 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MS-50_R | Air Dome Materials(Remaining) | 9 | 2026-06-25 | 2026-07-05 | 2026-07-07 | 2026-09-02 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 41 | 2026-03-07 | 2026-04-28 | 2026-03-07 | 2026-04-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-T-PR-LL-CO-MS-10 | Autoclaved Aerated Panel | 41 | 2026-03-07 | 2026-04-28 | 2026-03-07 | 2026-04-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 45 | 2026-03-11 | 2026-05-07 | 2026-03-11 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-LL-MT-MS-10 | Metal Doors | 45 | 2026-03-11 | 2026-05-07 | 2026-03-11 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-MT-MS-20 | Curtain Wall | 45 | 2026-03-11 | 2026-05-07 | 2026-03-11 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 46 | 2026-03-10 | 2026-05-07 | 2026-03-10 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-LL-PB-MS-10 | Booster Pump | 46 | 2026-03-10 | 2026-05-07 | 2026-03-10 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-PB-MS-20 | GRP Sectional Panel Water Tanks (4x3x3m) | 42 | 2026-03-15 | 2026-05-07 | 2026-03-15 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 50 | 2026-03-05 | 2026-05-07 | 2026-03-05 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-LL-IR-MS-10 | HDPE Pipes | 50 | 2026-03-05 | 2026-05-07 | 2026-03-05 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-IR-MS-20 | Irrigation Control System | 50 | 2026-03-05 | 2026-05-07 | 2026-03-05 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 49 | 2026-05-11 | 2026-07-11 | 2026-05-11 | 2026-09-15 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 16 | 16 | 0 | 0
PG-T-PR-LL-EL-MS-10 | Main Distribution Board(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-20 | Power Panels (Pump, Street Light)(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-30 | Site Lighting Poles(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-40 | Lighting Fixtures(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-70 | Security and Access Control System Materials(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-80 | Fire Alarm System Materials(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-10_R | Main Distribution Board(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-16 | 2026-08-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-20_R | Power Panels (Pump, Street Light)(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-16 | 2026-08-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-30_R | Site Lighting Poles(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-16 | 2026-08-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-40_R | Lighting Fixtures(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-16 | 2026-07-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-16 | 2026-09-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-70_R | Security and Access Control System Materials(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-16 | 2026-09-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-80_R | Fire Alarm System Materials(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-08-27 | 2026-09-15 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MS-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 5 | 2026-07-06 | 2026-07-11 | 2026-07-16 | 2026-07-20 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SHORT LEAD ITEMS |  | 28 | 2026-02-17 | 2026-03-28 | 2026-02-17 | 2026-03-26 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 38 | 38 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 23 | 2026-02-17 | 2026-03-17 | 2026-02-17 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 8 | 8 | 0 | 0
PG-T-PR-SL-LS-MS-10 | Backfilling Materials | 23 | 2026-02-17 | 2026-03-17 | 2026-02-17 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MS-30 | Compacted Natural Ground Soil | 20 | 2026-02-21 | 2026-03-17 | 2026-02-21 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MS-60 | Traffic Signages | 9 | 2026-03-07 | 2026-03-17 | 2026-03-07 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MS-40 | Curb Stone | 7 | 2026-03-09 | 2026-03-17 | 2026-03-09 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MS-20 | Interlock tiles | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MS-50 | Thermoplastic pavement road marking | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MS-70 | Trees | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MS-80 | Lawn | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 28 | 2026-02-17 | 2026-03-28 | 2026-02-17 | 2026-03-26 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-T-PR-SL-CO-MS-10 | Steel Rebar | 17 | 2026-02-17 | 2026-03-10 | 2026-02-17 | 2026-03-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-MS-20 | Concrete | 13 | 2026-02-23 | 2026-03-10 | 2026-02-23 | 2026-03-09 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-MS-40 | CMU Block | 19 | 2026-03-01 | 2026-03-28 | 2026-03-01 | 2026-03-26 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-MS-50 | Concrete Repair & Protection Materials | 19 | 2026-03-01 | 2026-03-28 | 2026-03-01 | 2026-03-26 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-MS-30 | Screed | 10 | 2026-03-11 | 2026-03-28 | 2026-03-11 | 2026-03-26 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL & FINISHES WORK |  | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 11 | 11 | 0 | 0
PG-T-PR-SL-AR-MS-10 | Ceramic tiles | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MS-20 | Anti-slip Granite tiles | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MS-30 | Epoxy Paint | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MS-40 | Cement Plaster | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MS-50 | Acrylic Paint | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MS-60 | Stone Cladding | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MS-70 | Phenolic Partition | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MS-80 | Glass Partition | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MS-90 | Gypsum Boards | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MS-100 | Specialities Materials (Toilet accessories, lockers, logo, etc) | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MS-110 | Waterproofing System Materials | 4 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 9 | 2026-03-07 | 2026-03-17 | 2026-03-07 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-PR-SL-MT-MS-20 | Galvanized Steel Roof Scupper | 9 | 2026-03-07 | 2026-03-17 | 2026-03-07 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-MT-MS-30 | Galvanized Steel Cover with frame | 9 | 2026-03-07 | 2026-03-17 | 2026-03-07 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-MT-MS-10 | Galvanized Steel Ladder | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
HVAC WORK |  | 19 | 2026-02-23 | 2026-03-17 | 2026-02-23 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-PR-SL-AC-MS-10 | Split Air Conditioning Unit | 19 | 2026-02-23 | 2026-03-17 | 2026-02-23 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AC-MS-20 | Air Duct | 15 | 2026-02-28 | 2026-03-17 | 2026-02-28 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AC-MS-30 | Diffusers and Grills | 11 | 2026-03-04 | 2026-03-17 | 2026-03-04 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AC-MS-40 | Exhaust fans | 11 | 2026-03-04 | 2026-03-17 | 2026-03-04 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-PR-SL-PB-MS-10 | PPR Pipes & Valves | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-PB-MS-20 | UPCV Pipes | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-PB-MS-30 | Sanitary Drainage Fixtures | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-SL-IR-MS-10 | Gate Valve including valve box | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-IR-MS-20 | Bulbblers and Spreyers | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-T-PR-SL-EL-MS-10 | Wiring Devices Materials | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE FIGHTING WORK |  | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-T-PR-SL-FF-MS-10 | Fire Extinguishers | 4 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-16 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MATERIAL APPROVALS |  | 114 | 2026-02-21 | 2026-07-13 | 2026-02-21 | 2026-09-17 | 340734.03 | 340734.03 | 340734.03 | 100% | 100% | 0 | 0 | 0 |  | 70 | 70 | 0 | 0
LONG LEAD ITEMS |  | 111 | 2026-02-25 | 2026-07-13 | 2026-02-25 | 2026-09-17 | 284659.98 | 284659.98 | 284659.98 | 100% | 100% | 0 | 0 | 0 |  | 32 | 32 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 56 | 2026-02-25 | 2026-05-05 | 2026-02-25 | 2026-05-05 | 15425.28 | 15425.28 | 15425.28 | 100% | 100% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-PR-LL-LS-MA-20 | Benches, Seats (Rectangular & Circular) | 56 | 2026-02-25 | 2026-05-05 | 2026-02-25 | 2026-05-05 | 3869.07 | 3869.07 | 3869.07 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-MA-30 | Fence, gates and accessories | 43 | 2026-03-12 | 2026-05-05 | 2026-03-12 | 2026-05-05 | 2529.21 | 2529.21 | 2529.21 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-MA-10 | Bike and Walk Path Materials | 41 | 2026-03-15 | 2026-05-05 | 2026-03-15 | 2026-05-05 | 9027 | 9027 | 9027 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 105 | 2026-03-02 | 2026-07-11 | 2026-03-02 | 2026-09-03 | 238773.54 | 238773.54 | 238773.54 | 100% | 100% | 0 | 0 | 0 |  | 6 | 6 | 0 | 0
PG-T-PR-LL-SP-MA-50 | Air Dome Materials(Completed) | 91 | 2026-03-02 | 2026-06-24 | 2026-03-02 | 2026-06-24 | 62622.07 | 62622.07 | 62622.07 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MA-40 | Tartan Floor | 43 | 2026-03-12 | 2026-05-05 | 2026-03-12 | 2026-05-05 | 8775 | 8775 | 8775 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MA-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc) | 42 | 2026-03-14 | 2026-05-05 | 2026-03-14 | 2026-05-05 | 13051.5 | 13051.5 | 13051.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MA-20 | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc) | 42 | 2026-03-14 | 2026-05-05 | 2026-03-14 | 2026-05-05 | 2256 | 2256 | 2256 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MA-30 | Padel Playgound Materials (Flooring, fence, tempered glass, etc) | 42 | 2026-03-14 | 2026-05-05 | 2026-03-14 | 2026-05-05 | 5950.8 | 5950.8 | 5950.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MA-50_R | Air Dome Materials(Remaining) | 5 | 2026-07-06 | 2026-07-11 | 2026-07-09 | 2026-09-03 | 146118.17 | 146118.17 | 146118.17 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 38 | 2026-03-11 | 2026-04-28 | 2026-03-11 | 2026-04-28 | 1417.5 | 1417.5 | 1417.5 | 100% | 100% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-T-PR-LL-CO-MA-10 | Autoclaved Aerated Panel | 38 | 2026-03-11 | 2026-04-28 | 2026-03-11 | 2026-04-28 | 1417.5 | 1417.5 | 1417.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 42 | 2026-03-15 | 2026-05-06 | 2026-03-15 | 2026-05-06 | 1902-06-07 05:31 | 889.23 | 889.23 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-LL-MT-MA-10 | Metal Doors | 42 | 2026-03-15 | 2026-05-06 | 2026-03-15 | 2026-05-06 | 127.53 | 127.53 | 127.53 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-MT-MA-20 | Curtain Wall | 42 | 2026-03-15 | 2026-05-06 | 2026-03-15 | 2026-05-06 | 761.7 | 761.7 | 761.7 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 42 | 2026-03-15 | 2026-05-06 | 2026-03-15 | 2026-05-06 | 3553.95 | 3553.95 | 3553.95 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-LL-PB-MA-10 | Booster Pump | 42 | 2026-03-15 | 2026-05-06 | 2026-03-15 | 2026-05-06 | 1818.3 | 1818.3 | 1818.3 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-PB-MA-20 | GRP Sectional Panel Water Tanks (4x3x3m) | 38 | 2026-03-24 | 2026-05-06 | 2026-03-24 | 2026-05-06 | 1735.65 | 1735.65 | 1735.65 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 45 | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-06 | 6802.65 | 6802.65 | 6802.65 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-LL-IR-MA-10 | HDPE Pipes | 45 | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-06 | 2256.9 | 2256.9 | 2256.9 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-IR-MA-20 | Irrigation Control System | 45 | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-06 | 4545.75 | 4545.75 | 4545.75 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 50 | 2026-05-12 | 2026-07-13 | 2026-05-12 | 2026-09-17 | 17797.83 | 17797.83 | 17797.83 | 100% | 100% | 0 | 0 | 0 |  | 16 | 16 | 0 | 0
PG-T-PR-LL-EL-MA-10 | Main Distribution Board(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 1900-10-23 12:58 | 297.54 | 297.54 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-20 | Power Panels (Pump, Street Light)(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 1900-08-25 00:43 | 238.03 | 238.03 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-30 | Site Lighting Poles(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 6962.11 | 6962.11 | 6962.11 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-40 | Lighting Fixtures(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 769.7 | 769.7 | 769.7 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 1901-08-24 12:14 | 602.51 | 602.51 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 587.63 | 587.63 | 587.63 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-70 | Security and Access Control System Materials(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 743.94 | 743.94 | 743.94 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-80 | Fire Alarm System Materials(Completed) | 34 | 2026-05-12 | 2026-06-24 | 2026-05-12 | 2026-06-24 | 477.23 | 477.23 | 477.23 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-10_R | Main Distribution Board(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-17 | 2026-08-06 | 1900-07-16 08:38 | 198.36 | 198.36 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-20_R | Power Panels (Pump, Street Light)(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-17 | 2026-08-06 | 1900-06-06 16:34 | 158.69 | 1900-06-06 16:34 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-30_R | Site Lighting Poles(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-17 | 2026-08-06 | 4641.41 | 4641.41 | 4641.41 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-40_R | Lighting Fixtures(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-17 | 2026-07-23 | 1901-05-27 03:07 | 513.13 | 1901-05-27 03:07 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-17 | 2026-09-17 | 391.75 | 391.75 | 391.75 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-70_R | Security and Access Control System Materials(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-07-17 | 2026-09-17 | 495.96 | 1901-05-09 23:02 | 495.96 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-80_R | Fire Alarm System Materials(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-27 | 2026-09-17 | 318.16 | 318.16 | 318.16 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MA-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 2 | 2026-07-12 | 2026-07-13 | 2026-07-22 | 2026-07-28 | 401.68 | 401.68 | 401.68 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SHORT LEAD ITEMS |  | 25 | 2026-02-21 | 2026-03-26 | 2026-02-21 | 2026-03-26 | 56074.05 | 56074.05 | 56074.05 | 100% | 100% | 0 | 0 | 0 |  | 38 | 38 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 25 | 2026-02-21 | 2026-03-26 | 2026-02-21 | 2026-03-26 | 38542.29 | 38542.29 | 38542.29 | 100% | 100% | 0 | 0 | 0 |  | 8 | 8 | 0 | 0
PG-T-PR-SL-LS-MA-10 | Backfilling Materials | 25 | 2026-02-21 | 2026-03-26 | 2026-02-21 | 2026-03-26 | 10125 | 10125 | 10125 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MA-30 | Compacted Natural Ground Soil | 22 | 2026-02-25 | 2026-03-26 | 2026-02-25 | 2026-03-26 | 1287 | 1287 | 1287 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MA-60 | Traffic Signages | 11 | 2026-03-10 | 2026-03-26 | 2026-03-10 | 2026-03-26 | 1900-07-16 08:38 | 198.36 | 198.36 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MA-70 | Trees | 8 | 2026-03-14 | 2026-03-26 | 2026-03-14 | 2026-03-26 | 1906-04-24 02:24 | 2306.1 | 2306.1 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MA-80 | Lawn | 8 | 2026-03-14 | 2026-03-26 | 2026-03-14 | 2026-03-26 | 3045 | 3045 | 3045 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MA-50 | Thermoplastic pavement road marking | 6 | 2026-03-16 | 2026-03-26 | 2026-03-16 | 2026-03-26 | 525.63 | 525.63 | 525.63 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MA-20 | Interlock tiles | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 10715.4 | 10715.4 | 10715.4 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-MA-40 | Curb Stone | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 10339.8 | 10339.8 | 10339.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 24 | 2026-02-23 | 2026-03-26 | 2026-02-23 | 2026-03-26 | 1609.47 | 1609.47 | 1609.47 | 100% | 100% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-T-PR-SL-CO-MA-10 | Steel Rebar | 14 | 2026-02-23 | 2026-03-10 | 2026-02-23 | 2026-03-10 | 1901-04-20 19:41 | 476.82 | 476.82 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-MA-20 | Concrete | 9 | 2026-03-01 | 2026-03-10 | 2026-03-01 | 2026-03-10 | 1901-06-01 20:24 | 518.85 | 518.85 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-MA-40 | CMU Block | 15 | 2026-03-05 | 2026-03-26 | 2026-03-05 | 2026-03-26 | 1900-05-03 04:48 | 124.2 | 124.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-MA-50 | Concrete Repair & Protection Materials | 15 | 2026-03-05 | 2026-03-26 | 2026-03-05 | 2026-03-26 | 372 | 372 | 372 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-MA-30 | Screed | 1 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 1900-04-26 14:24 | 117.6 | 117.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL & FINISHES WORK |  | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 7931.55 | 7931.55 | 7931.55 | 100% | 100% | 0 | 0 | 0 |  | 11 | 11 | 0 | 0
PG-T-PR-SL-AR-MA-10 | Ceramic tiles | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1901-07-24 22:48 | 571.95 | 571.95 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MA-20 | Anti-slip Granite tiles | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 535.5 | 535.5 | 535.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MA-30 | Epoxy Paint | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1900-04-20 04:19 | 111.18 | 111.18 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MA-40 | Cement Plaster | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1900-08-08 08:53 | 221.37 | 221.37 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MA-50 | Acrylic Paint | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 147.9 | 147.9 | 147.9 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MA-60 | Stone Cladding | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1852.2 | 1852.2 | 1852.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MA-70 | Phenolic Partition | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1340.4 | 1340.4 | 1340.4 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MA-80 | Glass Partition | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1900-06-03 09:36 | 155.4 | 155.4 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MA-90 | Gypsum Boards | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1900-07-06 13:55 | 188.58 | 188.58 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MA-100 | Specialities Materials (Toilet accessories, lockers, logo, etc) | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1906-03-11 20:53 | 2262.87 | 2262.87 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-MA-110 | Waterproofing System Materials | 2 | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 1901-06-27 04:48 | 544.2 | 544.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 10 | 2026-03-11 | 2026-03-26 | 2026-03-11 | 2026-03-26 | 1901-04-22 21:22 | 478.89 | 478.89 | 100% | 100% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-PR-SL-MT-MA-20 | Galvanized Steel Roof Scupper | 10 | 2026-03-11 | 2026-03-26 | 2026-03-11 | 2026-03-26 | 1900-01-30 07:41 | 31.32 | 31.32 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-MT-MA-30 | Galvanized Steel Cover with frame | 10 | 2026-03-11 | 2026-03-26 | 2026-03-11 | 2026-03-26 | 1900-03-25 17:02 | 85.71 | 85.71 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-MT-MA-10 | Galvanized Steel Ladder | 7 | 2026-03-15 | 2026-03-26 | 2026-03-15 | 2026-03-26 | 1900-12-26 20:38 | 361.86 | 361.86 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
HVAC WORK |  | 20 | 2026-02-28 | 2026-03-26 | 2026-02-28 | 2026-03-26 | 1901-08-28 08:38 | 606.36 | 606.36 | 100% | 100% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-PR-SL-AC-MA-10 | Split Air Conditioning Unit | 20 | 2026-02-28 | 2026-03-26 | 2026-02-28 | 2026-03-26 | 1900-11-04 22:19 | 309.93 | 309.93 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AC-MA-20 | Air Duct | 16 | 2026-03-04 | 2026-03-26 | 2026-03-04 | 2026-03-26 | 1900-06-04 | 156 | 156 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AC-MA-30 | Diffusers and Grills | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 74.31 | 74.31 | 74.31 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AC-MA-40 | Exhaust fans | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1900-03-06 02:53 | 66.12 | 66.12 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 3147.03 | 3147.03 | 3147.03 | 100% | 100% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-PR-SL-PB-MA-10 | PPR Pipes & Valves | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 265.2 | 265.2 | 265.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-PB-MA-20 | UPCV Pipes | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 335.19 | 335.19 | 335.19 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-PB-MA-30 | Sanitary Drainage Fixtures | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1906-12-20 15:22 | 2546.64 | 2546.64 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 3328.23 | 3328.23 | 3328.23 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-SL-IR-MA-10 | Gate Valve including valve box | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 413.28 | 413.28 | 413.28 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-IR-MA-20 | Bulbblers and Spreyers | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1907-12-23 22:48 | 2914.95 | 2914.95 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1901-02-10 12:29 | 407.52 | 407.52 | 100% | 100% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-T-PR-SL-EL-MA-10 | Wiring Devices Materials | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 1901-02-10 12:29 | 407.52 | 407.52 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE FIGHTING WORK |  | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 22.71 | 22.71 | 22.71 | 100% | 100% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-T-PR-SL-FF-MA-10 | Fire Extinguishers | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 22.71 | 22.71 | 22.71 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PROCUREMENT |  | 149 | 2026-02-26 | 2026-08-27 | 2026-02-26 |  | 3066606.27 | 2285139.72 | 3066606.27 | 100% | 74.52% | 0 | 0 | 0 |  | 213 | 184 | 29 | 0
LONG LEAD ITEMS |  | 142 | 2026-03-07 | 2026-08-27 | 2026-03-07 |  | 2561939.82 | 1784927.49 | 2561939.82 | 100% | 69.67% | 0 | 0 | 0 |  | 121 | 102 | 19 | 0
PURCHASE ORDER |  | 106 | 2026-03-07 | 2026-07-16 | 2026-03-07 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 31 | 31 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 49 | 2026-03-07 | 2026-05-07 | 2026-03-07 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-PR-LL-LS-PO-20 | Benches, Seats (Rectangular & Circular) | 49 | 2026-03-07 | 2026-05-07 | 2026-03-07 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-PO-30 | Fence, gates and accessories | 36 | 2026-03-26 | 2026-05-07 | 2026-03-26 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-PO-10 | Bike and Walk Path Materials | 34 | 2026-03-29 | 2026-05-07 | 2026-03-29 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 93 | 2026-03-26 | 2026-07-16 | 2026-03-26 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-T-PR-LL-SP-PO-40 | Tartan Floor | 36 | 2026-03-26 | 2026-05-07 | 2026-03-26 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-PO-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc) | 35 | 2026-03-28 | 2026-05-07 | 2026-03-28 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-PO-20 | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc) | 35 | 2026-03-28 | 2026-05-07 | 2026-03-28 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-PO-30 | Padel Playgound Materials (Flooring, fence, tempered glass, etc) | 35 | 2026-03-28 | 2026-05-07 | 2026-03-28 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-PO-50 | Air Dome Materials | 5 | 2026-07-12 | 2026-07-16 | 2026-08-06 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 39 | 2026-03-18 | 2026-05-07 | 2026-03-18 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 1 | 1 | 0 | 0
PG-T-PR-LL-CO-PO-10 | Autoclaved Aerated Panel | 39 | 2026-03-18 | 2026-05-07 | 2026-03-18 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 38 | 2026-03-24 | 2026-05-07 | 2026-03-24 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-LL-MT-PO-10 | Metal Doors | 38 | 2026-03-24 | 2026-05-07 | 2026-03-24 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-MT-PO-20 | Curtain Wall | 38 | 2026-03-24 | 2026-05-07 | 2026-03-24 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 35 | 2026-03-28 | 2026-05-07 | 2026-03-28 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-LL-PB-PO-10 | Booster Pump | 35 | 2026-03-28 | 2026-05-07 | 2026-03-28 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-PB-PO-20 | GRP Sectional Panel Water Tanks (4x3x3m) | 33 | 2026-03-30 | 2026-05-07 | 2026-03-30 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 40 | 2026-03-17 | 2026-05-07 | 2026-03-17 | 2026-05-06 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-LL-IR-PO-20 | Irrigation Control System | 40 | 2026-03-17 | 2026-05-07 | 2026-03-17 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-IR-PO-10 | HDPE Pipes | 39 | 2026-03-18 | 2026-05-07 | 2026-03-18 | 2026-05-06 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 54 | 2026-05-11 | 2026-07-16 | 2026-05-11 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 16 | 16 | 0 | 0
PG-T-PR-LL-EL-PO-10 | Main Distribution Board(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-20 | Power Panels (Pump, Street Light)(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-30 | Site Lighting Poles(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-40 | Lighting Fixtures(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-70 | Security and Access Control System Materials(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-80 | Fire Alarm System Materials(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-10_R | Main Distribution Board(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-07-26 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-20_R | Power Panels (Pump, Street Light)(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-07-26 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-30_R | Site Lighting Poles(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-07-26 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-40_R | Lighting Fixtures(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-07-23 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-08-27 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-70_R | Security and Access Control System Materials(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-08-27 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-80_R | Fire Alarm System Materials(Remaining) | 8 | 2026-07-04 | 2026-07-12 | 2026-08-27 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-PO-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 3 | 2026-07-14 | 2026-07-16 | 2026-07-26 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
MANUFACTURE / FABRICATION |  | 90 | 2026-04-29 | 2026-08-16 | 2026-04-29 |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 45 | 44 | 1 | 0
EXTERNAL / LANDSCAPE WORK |  | 64 | 2026-05-06 | 2026-07-23 | 2026-05-06 | 2026-09-10 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 6 | 6 | 0 | 0
PG-T-PR-LL-LS-MF-20 | Benches, Seats (Rectangular & Circular)(Completed) | 39 | 2026-05-06 | 2026-06-25 | 2026-05-06 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-MF-30 | Fence, gates and accessories(Completed) | 39 | 2026-05-06 | 2026-06-25 | 2026-05-06 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-MF-10 | Bike and Walk Path Materials(Completed) | 39 | 2026-05-06 | 2026-06-25 | 2026-05-06 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-MF-20_R | Benches, Seats (Rectangular & Circular)(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-05 | 2026-09-07 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-MF-30_R | Fence, gates and accessories(Remaining) | 6 | 2026-06-25 | 2026-07-01 | 2026-07-22 | 2026-09-10 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-MF-10_R | Bike and Walk Path Materials(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-05 | 2026-09-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 84 | 2026-05-06 | 2026-08-16 | 2026-05-06 |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 9 | 8 | 1 | 0
PG-T-PR-LL-SP-MF-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc)(Completed) | 39 | 2026-05-06 | 2026-06-25 | 2026-05-06 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MF-20 | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc)(Completed) | 39 | 2026-05-06 | 2026-06-25 | 2026-05-06 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MF-30 | Padel Playgound Materials (Flooring, fence, tempered glass, etc)(Completed) | 39 | 2026-05-06 | 2026-06-25 | 2026-05-06 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MF-40 | Tartan Floor(Completed) | 39 | 2026-05-06 | 2026-06-25 | 2026-05-06 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MF-10_R | Football Playground Materials (Flooring, goal post, nets, paints, etc)(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-05 | 2026-09-02 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MF-20_R | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc)(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-05 | 2026-09-04 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MF-30_R | Padel Playgound Materials (Flooring, fence, tempered glass, etc)(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-05 | 2026-09-05 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MF-40_R | Tartan Floor(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-05 | 2026-09-19 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-MF-50 | Air Dome Materials | 26 | 2026-07-18 | 2026-08-16 | 2026-08-27 |  | 0 | 0 | 0 | 100% | 60% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
CONCRETE WORK |  | 50 | 2026-04-29 | 2026-06-30 | 2026-04-29 | 2026-07-02 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-LL-CO-MF-10 | Autoclaved Aerated Panel(Completed) | 45 | 2026-04-29 | 2026-06-25 | 2026-04-29 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-CO-MF-10_R | Autoclaved Aerated Panel(Remaining) | 5 | 2026-06-25 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 64 | 2026-05-06 | 2026-07-23 | 2026-05-06 | 2026-09-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-PR-LL-MT-MF-10 | Metal Doors(Completed) | 39 | 2026-05-06 | 2026-06-25 | 2026-05-06 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-MT-MF-20 | Curtain Wall(Completed) | 39 | 2026-05-06 | 2026-06-25 | 2026-05-06 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-MT-MF-10_R | Metal Doors(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-27 | 2026-09-17 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-MT-MF-20_R | Curtain Wall(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-27 | 2026-09-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 64 | 2026-05-06 | 2026-07-23 | 2026-05-06 | 2026-09-14 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-PR-LL-PB-MF-10 | Booster Pump(Completed) | 39 | 2026-05-06 | 2026-06-25 | 2026-05-06 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-PB-MF-20 | GRP Sectional Panel Water Tanks (4x3x3m)(Completed) | 39 | 2026-05-06 | 2026-06-25 | 2026-05-06 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-PB-MF-10_R | Booster Pump(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-06-25 | 2026-07-02 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-PB-MF-20_R | GRP Sectional Panel Water Tanks (4x3x3m)(Remaining) | 25 | 2026-06-25 | 2026-07-23 | 2026-08-05 | 2026-09-14 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 44 | 2026-05-06 | 2026-07-01 | 2026-05-06 | 2026-09-21 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-PR-LL-IR-MF-10 | HDPE Pipes(Completed) | 39 | 2026-05-06 | 2026-06-25 | 2026-05-06 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-IR-MF-20 | Irrigation Control System(Completed) | 39 | 2026-05-06 | 2026-06-25 | 2026-05-06 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-IR-MF-10_R | HDPE Pipes(Remaining) | 5 | 2026-06-25 | 2026-07-01 | 2026-08-14 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-IR-MF-20_R | Irrigation Control System(Remaining) | 5 | 2026-06-25 | 2026-07-01 | 2026-08-27 | 2026-09-21 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 74 | 2026-05-12 | 2026-08-10 | 2026-05-12 | 2026-09-30 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 16 | 16 | 0 | 0
PG-T-PR-LL-EL-MF-10 | Main Distribution Board(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-20 | Power Panels (Pump, Street Light)(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-30 | Site Lighting Poles(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-40 | Lighting Fixtures(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-70 | Security and Access Control System Materials(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-80 | Fire Alarm System Materials(Completed) | 34 | 2026-05-12 | 2026-06-25 | 2026-05-12 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-10_R | Main Distribution Board(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-08-06 | 2026-09-28 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-20_R | Power Panels (Pump, Street Light)(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-08-06 | 2026-09-26 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-30_R | Site Lighting Poles(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-08-06 | 2026-09-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-40_R | Lighting Fixtures(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-07-23 | 2026-09-30 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-08-27 | 2026-09-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-70_R | Security and Access Control System Materials(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-08-27 | 2026-09-30 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-80_R | Fire Alarm System Materials(Remaining) | 25 | 2026-07-13 | 2026-08-10 | 2026-08-27 | 2026-09-30 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-MF-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 6 | 2026-07-18 | 2026-07-23 | 2026-08-27 | 2026-09-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
DELIVERY TO SITE |  | 94 | 2026-05-06 | 2026-08-27 | 2026-05-06 |  | 2561939.82 | 1784927.49 | 2561939.82 | 100% | 69.67% | 0 | 0 | 0 |  | 45 | 27 | 18 | 0
EXTERNAL / LANDSCAPE WORK |  | 76 | 2026-05-06 | 2026-08-06 | 2026-05-06 |  | 138827.52 | 137434.65 | 138827.52 | 100% | 99% | 0 | 0 | 0 |  | 6 | 5 | 1 | 0
PG-T-PR-LL-LS-DL-20 | Benches, Seats (Rectangular & Circular)(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 20892.98 | 20892.98 | 20892.98 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-DL-30 | Fence, gates and accessories(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 11381.45 | 11381.45 | 11381.45 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-DL-10 | Bike and Walk Path Materials(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 56870.1 | 56870.1 | 56870.1 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-DL-30_R | Fence, gates and accessories(Remaining) | 5 | 2026-07-02 | 2026-07-07 | 2026-07-23 | 2026-09-19 | 11381.45 | 11381.45 | 11381.45 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-LS-DL-20_R | Benches, Seats (Rectangular & Circular)(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-14 |  | 13928.65 | 12535.79 | 13928.65 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-T-PR-LL-LS-DL-10_R | Bike and Walk Path Materials(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-06 | 2026-09-28 | 24372.9 | 24372.9 | 24372.9 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
SPORTS & RECREATIONAL FACILITIES WORK |  | 94 | 2026-05-06 | 2026-08-27 | 2026-05-06 |  | 2148961.86 | 1383982.01 | 2148961.86 | 100% | 64.4% | 0 | 0 | 0 |  | 9 | 4 | 5 | 0
PG-T-PR-LL-SP-DL-10 | Football Playground Materials (Flooring, goal post, nets, paints, etc)(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 58731.75 | 58731.75 | 58731.75 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-DL-20 | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc)(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 10152 | 10152 | 10152 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-DL-30 | Padel Playgound Materials (Fence, tempered glass, etc)(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 26778.6 | 26778.6 | 26778.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-DL-40 | Tartan Floor(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 39487.5 | 39487.5 | 39487.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-SP-DL-10_R | Football Playground Materials (Flooring, goal post, nets, paints, etc)(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-14 |  | 58731.75 | 52858.58 | 58731.75 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-T-PR-LL-SP-DL-20_R | Basketball Playground Materials (Flooring, basketball poll, nets, paints, etc)(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-14 |  | 10152 | 9136.8 | 10152 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-T-PR-LL-SP-DL-30_R | Padel Playgound Materials (Fence, tempered glass, etc)(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-14 |  | 26778.6 | 24100.74 | 26778.6 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-T-PR-LL-SP-DL-40_R | Tartan Floor(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-06 |  | 39487.5 | 35538.75 | 39487.5 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-T-PR-LL-SP-DL-50 | Air Dome Materials | 10 | 2026-08-17 | 2026-08-27 | 2026-08-20 |  | 1878662.16 | 1127197.3 | 1878662.16 | 100% | 60% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
CONCRETE WORK |  | 49 | 2026-05-06 | 2026-07-06 | 2026-05-06 | 2026-07-05 | 12757.5 | 12757.5 | 12757.5 | 100% | 100% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-LL-CO-DL-10 | Autoclaved Aerated Panel(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 8930.25 | 8930.25 | 8930.25 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-CO-DL-10_R | Autoclaved Aerated Panel(Remaining) | 5 | 2026-07-01 | 2026-07-06 | 2026-07-04 | 2026-07-05 | 3827.25 | 3827.25 | 3827.25 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 76 | 2026-05-06 | 2026-08-06 | 2026-05-06 |  | 8003.07 | 6574.62 | 8003.07 | 100% | 82.15% | 0 | 0 | 0 |  | 4 | 2 | 2 | 0
PG-T-PR-LL-MT-DL-10 | Metal Doors(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 573.89 | 573.89 | 573.89 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-MT-DL-20 | Curtain Wall(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 1909-05-19 15:36 | 1909-05-19 15:36 | 3427.65 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-MT-DL-10_R | Metal Doors(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-27 |  | 573.89 | 516.5 | 573.89 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-T-PR-LL-MT-DL-20_R | Curtain Wall(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-27 |  | 3427.65 | 2056.59 | 3427.65 | 100% | 60% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PLUMBING WORK |  | 76 | 2026-05-06 | 2026-08-06 | 2026-05-06 |  | 31985.55 | 31360.72 | 31985.55 | 100% | 98.05% | 0 | 0 | 0 |  | 4 | 3 | 1 | 0
PG-T-PR-LL-PB-DL-10 | Booster Pump(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 9818.82 | 9818.82 | 9818.82 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-PB-DL-20 | GRP Sectional Panel Water Tanks (4x3x3m)(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 9372.51 | 9372.51 | 9372.51 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-PB-DL-10_R | Booster Pump(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-27 | 2026-09-26 | 6545.88 | 6545.88 | 6545.88 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-PB-DL-20_R | GRP Sectional Panel Water Tanks (4x3x3m)(Remaining) | 12 | 2026-07-25 | 2026-08-06 | 2026-08-14 |  | 6248.34 | 5623.51 | 6248.34 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
IRRIGATION WORK |  | 48 | 2026-05-06 | 2026-07-06 | 2026-05-06 |  | 61223.85 | 59587.38 | 61223.85 | 100% | 97.33% | 0 | 0 | 0 |  | 4 | 3 | 1 | 0
PG-T-PR-LL-IR-DL-10 | HDPE Pipes(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 12187.26 | 12187.26 | 12187.26 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-IR-DL-20 | Irrigation Control System(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 24547.05 | 24547.05 | 24547.05 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-IR-DL-10_R | HDPE Pipes(Remaining) | 4 | 2026-07-01 | 2026-07-06 | 2026-08-07 | 2026-09-22 | 8124.84 | 8124.84 | 8124.84 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-IR-DL-20_R | Irrigation Control System(Remaining) | 4 | 2026-07-01 | 2026-07-06 | 2026-08-20 |  | 16364.7 | 14728.23 | 16364.7 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
ELECTRICAL WORK |  | 85 | 2026-05-13 | 2026-08-24 | 2026-05-13 |  | 160180.47 | 153230.61 | 160180.47 | 100% | 95.66% | 0 | 0 | 0 |  | 16 | 8 | 8 | 0
PG-T-PR-LL-EL-DL-10 | Main Distribution Board(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 2677.86 | 2677.86 | 2677.86 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-DL-20 | Power Panels (Pump, Street Light)(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 2142.29 | 2142.29 | 2142.29 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-DL-30 | Site Lighting Poles(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 62659.01 | 62659.01 | 62659.01 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-DL-40 | Lighting Fixtures(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 6927.28 | 6927.28 | 6927.28 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-DL-50 | Grounding System Materials (Earth pit rod, LPS, etc)(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 5422.63 | 5422.63 | 5422.63 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-DL-60 | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 5288.65 | 5288.65 | 5288.65 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-DL-70 | Security and Access Control System Materials(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 6695.46 | 6695.46 | 6695.46 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-DL-80 | Fire Alarm System Materials(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 4295.11 | 4295.11 | 4295.11 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-LL-EL-DL-50_R | Grounding System Materials (Earth pit rod, LPS, etc)(Remaining) | 4 | 2026-07-25 | 2026-07-28 | 2026-08-14 |  | 3615.08 | 3253.58 | 3615.08 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-T-PR-LL-EL-DL-10_R | Main Distribution Board(Remaining) | 12 | 2026-08-11 | 2026-08-24 | 2026-08-14 |  | 1785.24 | 1904-05-24 17:17 | 1785.24 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-T-PR-LL-EL-DL-20_R | Power Panels (Pump, Street Light)(Remaining) | 12 | 2026-08-11 | 2026-08-24 | 2026-08-14 |  | 1428.19 | 1285.37 | 1428.19 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-T-PR-LL-EL-DL-30_R | Site Lighting Poles(Remaining) | 12 | 2026-08-11 | 2026-08-24 | 2026-08-14 |  | 41772.67 | 2002-12-05 09:36 | 41772.67 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-T-PR-LL-EL-DL-40_R | Lighting Fixtures(Remaining) | 12 | 2026-08-11 | 2026-08-24 | 2026-08-14 |  | 4618.19 | 4156.37 | 4618.19 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-T-PR-LL-EL-DL-60_R | Telecommunications & Data System Materials (Telephone outlet, CCTV, etc)(Remaining) | 12 | 2026-08-11 | 2026-08-24 | 2026-08-27 |  | 1909-08-25 18:29 | 1908-03-14 21:36 | 3525.77 | 100% | 85% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-T-PR-LL-EL-DL-70_R | Security and Access Control System Materials(Remaining) | 12 | 2026-08-11 | 2026-08-24 | 2026-08-27 |  | 4463.64 | 3794.09 | 4463.64 | 100% | 85% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-T-PR-LL-EL-DL-80_R | Fire Alarm System Materials(Remaining) | 12 | 2026-08-11 | 2026-08-24 | 2026-08-27 |  | 2863.4 | 2433.89 | 2863.4 | 100% | 85% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
SHORT LEAD ITEMS |  | 118 | 2026-02-26 | 2026-07-22 | 2026-02-26 |  | 504666.45 | 500212.22 | 504666.45 | 100% | 99.12% | 0 | 0 | 0 |  | 92 | 82 | 10 | 0
MATERIAL SUBMITTALS |  | 0 |  |  |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
PURCHASE ORDER |  | 108 | 2026-02-26 | 2026-07-11 | 2026-02-26 | 2026-08-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 44 | 44 | 0 | 0
EXTERNAL / LANDSCAPE WORK |  | 108 | 2026-02-26 | 2026-07-11 | 2026-02-26 | 2026-08-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 12 | 12 | 0 | 0
PG-T-PR-SL-LS-PO-10 | Backfilling Materials | 44 | 2026-02-26 | 2026-04-23 | 2026-02-26 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-PO-30 | Compacted Natural Ground Soil | 42 | 2026-03-01 | 2026-04-23 | 2026-03-01 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-PO-20 | Interlock tiles | 28 | 2026-03-29 | 2026-04-30 | 2026-03-29 | 2026-04-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-PO-40 | Curb Stone | 23 | 2026-04-04 | 2026-04-30 | 2026-04-04 | 2026-04-29 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-PO-50 | Thermoplastic pavement road marking(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-PO-60 | Traffic Signages(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-PO-70 | Trees(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-PO-80 | Lawn(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-PO-50_R | Thermoplastic pavement road marking(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-20 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-PO-70_R | Trees(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-20 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-PO-80_R | Lawn(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-20 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-PO-60_R | Traffic Signages(Remaining) | 7 | 2026-07-04 | 2026-07-11 | 2026-08-20 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
CONCRETE WORK |  | 41 | 2026-03-02 | 2026-04-23 | 2026-03-02 | 2026-04-22 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-T-PR-SL-CO-PO-10 | Steel Rebar | 41 | 2026-03-02 | 2026-04-23 | 2026-03-02 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-PO-20 | Concrete | 36 | 2026-03-08 | 2026-04-23 | 2026-03-08 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-PO-40 | CMU Block | 33 | 2026-03-11 | 2026-04-23 | 2026-03-11 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-PO-50 | Concrete Repair & Protection Materials | 32 | 2026-03-12 | 2026-04-23 | 2026-03-12 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-PO-30 | Screed | 23 | 2026-03-28 | 2026-04-23 | 2026-03-28 | 2026-04-22 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL & FINISHES WORK |  | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 11 | 11 | 0 | 0
PG-T-PR-SL-AR-PO-10 | Ceramic tiles | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-PO-20 | Anti-slip Granite tiles | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-PO-30 | Epoxy Paint | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-PO-40 | Cement Plaster | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-PO-50 | Acrylic Paint | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-PO-60 | Stone Cladding | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-PO-70 | Phenolic Partition | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-PO-80 | Glass Partition | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-PO-90 | Gypsum Boards | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-PO-100 | Specialities Materials (Toilet accessories, lockers, logo, etc) | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-PO-110 | Waterproofing System Materials | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-PR-SL-MT-PO-10 | Galvanized Steel Ladder | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-MT-PO-20 | Galvanized Steel Roof Scupper | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-MT-PO-30 | Galvanized Steel Cover with frame | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
HVAC WORK |  | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-PR-SL-AC-PO-10 | Split Air Conditioning Unit | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AC-PO-20 | Air Duct | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AC-PO-30 | Diffusers and Grills | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AC-PO-40 | Exhaust fans | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-PR-SL-PB-PO-10 | PPR Pipes & Valves | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-PB-PO-20 | UPCV Pipes | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-PB-PO-30 | Sanitary Drainage Fixtures | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-SL-IR-PO-10 | Gate Valve including valve box | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-IR-PO-20 | Bulbblers and Spreyers | 7 | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-12 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ELECTRICAL WORK |  | 42 | 2026-05-11 | 2026-07-02 | 2026-05-11 | 2026-08-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-SL-EL-PO-10 | Wiring Devices Materials(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-EL-PO-10_R | Wiring Devices Materials(Remaining) | 7 | 2026-06-25 | 2026-07-02 | 2026-08-20 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
FIRE FIGHTING WORK |  | 39 | 2026-05-11 | 2026-06-29 | 2026-05-11 | 2026-08-27 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
PG-T-PR-SL-FF-PO-10 | Fire Extinguishers(Completed) | 35 | 2026-05-11 | 2026-06-25 | 2026-05-11 | 2026-06-24 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-FF-PO-10_R | Fire Extinguishers(Remaining) | 4 | 2026-06-25 | 2026-06-29 | 2026-08-20 | 2026-08-27 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
DELIVERY TO SITE |  | 116 | 2026-03-01 | 2026-07-22 | 2026-03-01 |  | 504666.45 | 500212.22 | 504666.45 | 100% | 99.12% | 0 | 0 | 0 |  | 48 | 38 | 10 | 0
EXTERNAL / LANDSCAPE WORK |  | 116 | 2026-03-01 | 2026-07-22 | 2026-03-01 |  | 346880.61 | 344882.8 | 346880.61 | 100% | 99.42% | 0 | 0 | 0 |  | 11 | 8 | 3 | 0
PG-T-PR-SL-LS-DL-10 | Backfilling Materials | 43 | 2026-03-01 | 2026-04-23 | 2026-03-01 | 2026-04-24 | 91125 | 91125 | 91125 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-DL-30 | Compacted Natural Ground Soil | 41 | 2026-03-03 | 2026-04-23 | 2026-03-03 | 2026-04-24 | 11583 | 11583 | 11583 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-DL-20 | Interlock tiles | 13 | 2026-04-29 | 2026-05-13 | 2026-04-29 | 2026-05-13 | 96438.6 | 96438.6 | 96438.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-DL-40 | Curb Stone | 13 | 2026-04-29 | 2026-05-13 | 2026-04-29 | 2026-05-13 | 93058.2 | 93058.2 | 93058.2 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-DL-50 | Thermoplastic pavement road marking | 1 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 4730.67 | 4730.67 | 4730.67 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-DL-60 | Traffic Signages(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 1071.14 | 1071.14 | 1071.14 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-DL-70 | Trees(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 12452.94 | 12452.94 | 12452.94 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-DL-80 | Lawn(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 16443 | 16443 | 16443 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-LS-DL-60_R | Traffic Signages(Remaining) | 10 | 2026-07-12 | 2026-07-22 | 2026-08-27 |  | 714.1 | 642.69 | 714.1 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-T-PR-SL-LS-DL-70_R | Trees(Remaining) | 10 | 2026-07-12 | 2026-07-22 | 2026-08-27 |  | 8301.96 | 7471.76 | 8301.96 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-T-PR-SL-LS-DL-80_R | Lawn(Remaining) | 10 | 2026-07-12 | 2026-07-22 | 2026-08-27 |  | 10962 | 9865.8 | 10962 | 100% | 90% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
CONCRETE WORK |  | 52 | 2026-03-10 | 2026-05-13 | 2026-03-10 | 2026-05-13 | 14485.23 | 14485.23 | 14485.23 | 100% | 100% | 0 | 0 | 0 |  | 5 | 5 | 0 | 0
PG-T-PR-SL-CO-DL-20 | Concrete | 35 | 2026-03-10 | 2026-04-23 | 2026-03-10 | 2026-04-24 | 4669.65 | 4669.65 | 4669.65 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-DL-10 | Steel Rebar | 18 | 2026-04-23 | 2026-05-13 | 2026-04-23 | 2026-05-13 | 4291.38 | 4291.38 | 4291.38 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-DL-30 | Screed | 18 | 2026-04-23 | 2026-05-13 | 2026-04-23 | 2026-05-13 | 1058.4 | 1058.4 | 1058.4 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-DL-40 | CMU Block | 18 | 2026-04-23 | 2026-05-13 | 2026-04-23 | 2026-05-13 | 1117.8 | 1117.8 | 1117.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-CO-DL-50 | Concrete Repair & Protection Materials | 18 | 2026-04-23 | 2026-05-13 | 2026-04-23 | 2026-05-13 | 3348 | 3348 | 3348 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
ARCHITECTURAL & FINISHES WORK |  | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 71383.95 | 71383.95 | 71383.95 | 100% | 100% | 0 | 0 | 0 |  | 11 | 11 | 0 | 0
PG-T-PR-SL-AR-DL-10 | Ceramic tiles | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 5147.55 | 5147.55 | 5147.55 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-DL-20 | Anti-slip Granite tiles | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 4819.5 | 4819.5 | 4819.5 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-DL-30 | Epoxy Paint | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 1000.62 | 1000.62 | 1000.62 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-DL-40 | Cement Plaster | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 1992.33 | 1992.33 | 1992.33 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-DL-50 | Acrylic Paint | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 1331.1 | 1331.1 | 1331.1 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-DL-60 | Stone Cladding | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 16669.8 | 16669.8 | 16669.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-DL-70 | Phenolic Partition | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 12063.6 | 12063.6 | 12063.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-DL-80 | Glass Partition | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 1398.6 | 1398.6 | 1398.6 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-DL-90 | Gypsum Boards | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 1697.22 | 1697.22 | 1697.22 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-DL-100 | Specialities Materials (Toilet accessories, lockers, logo, etc) | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 20365.83 | 20365.83 | 20365.83 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AR-DL-110 | Waterproofing System Materials | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 4897.8 | 4897.8 | 4897.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
METAL WORK |  | 51 | 2026-05-06 | 2026-07-08 | 2026-05-06 |  | 4310.01 | 3620.41 | 4310.01 | 100% | 84% | 0 | 0 | 0 |  | 6 | 3 | 3 | 0
PG-T-PR-SL-MT-DL-10 | Galvanized Steel Ladder(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 1905-05-07 00:58 | 1905-05-07 00:58 | 1905-05-07 00:58 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-MT-DL-20 | Galvanized Steel Roof Scupper(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 1900-06-17 03:07 | 169.13 | 169.13 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-MT-DL-30 | Galvanized Steel Cover with frame(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 462.83 | 462.83 | 462.83 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-MT-DL-10_R | Galvanized Steel Ladder(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-09-23 |  | 1302.7 | 781.62 | 1302.7 | 100% | 60% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-T-PR-SL-MT-DL-20_R | Galvanized Steel Roof Scupper(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-09-24 |  | 112.75 | 67.65 | 112.75 | 100% | 60% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
PG-T-PR-SL-MT-DL-30_R | Galvanized Steel Cover with frame(Remaining) | 12 | 2026-06-25 | 2026-07-08 | 2026-09-24 |  | 308.56 | 185.13 | 308.56 | 100% | 60% | 0 | 0 | 0 | No | 1 | 0 | 1 | 0
HVAC WORK |  | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 5457.24 | 5457.24 | 5457.24 | 100% | 100% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0
PG-T-PR-SL-AC-DL-10 | Split Air Conditioning Unit | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 1907-08-20 08:53 | 2789.37 | 2789.37 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AC-DL-20 | Air Duct | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 1404 | 1404 | 1404 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AC-DL-30 | Diffusers and Grills | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 668.79 | 668.79 | 668.79 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-AC-DL-40 | Exhaust fans | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 595.08 | 595.08 | 595.08 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PLUMBING WORK |  | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 28323.27 | 28323.27 | 28323.27 | 100% | 100% | 0 | 0 | 0 |  | 3 | 3 | 0 | 0
PG-T-PR-SL-PB-DL-10 | PPR Pipes & Valves | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 2386.8 | 2386.8 | 2386.8 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-PB-DL-20 | UPCV Pipes | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 3016.71 | 3016.71 | 3016.71 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-PB-DL-30 | Sanitary Drainage Fixtures | 7 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 22919.76 | 22919.76 | 22919.76 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
IRRIGATION WORK |  | 48 | 2026-05-06 | 2026-07-05 | 2026-05-06 |  | 29954.07 | 28456.37 | 29954.07 | 100% | 95% | 0 | 0 | 0 |  | 4 | 2 | 2 | 0
PG-T-PR-SL-IR-DL-10 | Gate Valve including valve box(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 1859.76 | 1859.76 | 1859.76 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-IR-DL-20 | Bulbblers and Spreyers(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 13117.28 | 13117.28 | 13117.28 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-IR-DL-10_R | Gate Valve including valve box(Remaining) | 9 | 2026-06-25 | 2026-07-05 | 2026-08-07 |  | 1859.76 | 1673.78 | 1859.76 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-T-PR-SL-IR-DL-20_R | Bulbblers and Spreyers(Remaining) | 9 | 2026-06-25 | 2026-07-05 | 2026-08-20 |  | 13117.28 | 1932-04-26 13:12 | 13117.28 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
ELECTRICAL WORK |  | 52 | 2026-05-13 | 2026-07-16 | 2026-05-13 |  | 3667.68 | 3447.62 | 3667.68 | 100% | 94% | 0 | 0 | 0 |  | 2 | 1 | 1 | 0
PG-T-PR-SL-EL-DL-10 | Wiring Devices Materials(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 1467.07 | 1467.07 | 1467.07 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-EL-DL-10_R | Wiring Devices Materials(Remaining) | 12 | 2026-07-04 | 2026-07-16 | 46284 |  | 2200.61 | 1905-06-02 13:12 | 2200.61 | 100% | 90% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
FIRE FIGHTING WORK |  | 46 | 2026-05-13 | 2026-07-09 | 2026-05-13 |  | 204.39 | 155.34 | 204.39 | 100% | 76% | 0 | 0 | 0 |  | 2 | 1 | 1 | 0
PG-T-PR-SL-FF-DL-10 | Fire Extinguishers(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 81.76 | 81.76 | 81.76 | 100% | 100% | 0 | 0 | 0 | No | 1 | 1 | 0 | 0
PG-T-PR-SL-FF-DL-10_R | Fire Extinguishers(Remaining) | 9 | 2026-06-30 | 2026-07-09 | 2026-09-27 |  | 122.63 | 73.58 | 122.63 | 100% | 60% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
CONSTRUCTION STAGE |  | 223 | 2026-03-24 | 2026-12-14 | 2026-03-24 |  | 4569706.01 | 3453780.89 | 6814680.6 | 67.06% | 50.68% | 8112 | 6135 | 5846 |  | 174 | 94 | 46 | 34
PLAYGROUND AND LANDSCAPING WORKS |  | 223 | 2026-03-24 | 2026-12-14 | 2026-03-24 |  | 1821855.51 | 1944937.5 | 2311795.02 | 78.81% | 84.13% | 5288 | 4102 | 3858 |  | 113 | 53 | 40 | 20
CUT AND FILL |  | 38 | 2026-03-24 | 2026-05-06 | 2026-03-24 | 2026-05-06 | 228240 | 228240 | 228240 | 100% | 100% | 376 | 376 | 376 |  | 3 | 3 | 0 | 0
PG-T-CON-EX-CF-10 | Existing Soil Excavation Works | 22 | 2026-03-24 | 2026-04-18 | 2026-03-24 | 2026-04-18 | 64800 | 64800 | 64800 | 100% | 100% | 172 | 172 | 172 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-CF-20 | Soil Replacement Works | 18 | 2026-04-07 | 2026-04-27 | 2026-04-07 | 2026-04-27 | 25740 | 25740 | 25740 | 100% | 100% | 100 | 100 | 100 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-CF-30 | Levelling & Backfilling Works | 17 | 2026-04-18 | 2026-05-06 | 2026-04-18 | 2026-05-06 | 137700 | 137700 | 137700 | 100% | 100% | 104 | 104 | 104 | No | 1 | 1 | 0 | 0
PLAYGROUND WORKS |  | 191 | 2026-04-23 | 2026-12-07 | 2026-04-23 |  | 498041.34 | 531610.46 | 623491.2 | 79.88% | 85.26% | 1896 | 1562 | 1586 |  | 35 | 20 | 11 | 4
FOOTBALL PLAYGROUND WORKS |  | 174 | 2026-04-23 | 2026-11-17 | 2026-04-23 |  | 279162.6 | 296090.33 | 333290.16 | 83.76% | 88.84% | 864 | 703 | 753 |  | 13 | 8 | 4 | 1
PG-T-CON-EX-FB-10 | Subgrade Preparation and Compaction | 12 | 2026-04-23 | 2026-05-06 | 2026-04-23 | 2026-05-06 | 23667 | 23667 | 23667 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-FB-20 | Sub-Base Laying and Compaction | 8 | 2026-04-28 | 2026-05-06 | 2026-04-28 | 2026-05-06 | 23667 | 23667 | 23667 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-FB-30 | Base Course Laying and Compaction | 33 | 2026-05-06 | 2026-06-17 | 2026-05-06 | 2026-06-17 | 23667 | 23667 | 23667 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-FB-70 | Topsoil Placement(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 9466.8 | 9466.8 | 9466.8 | 100% | 100% | 34 | 34 | 34 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-FB-80 | Fine Grading & Leveling | 15 | 2026-06-25 | 2026-07-12 | 2026-07-07 | 2026-07-12 | 23667 | 23667 | 23667 | 100% | 100% | 76 | 76 | 76 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-FB-70_R | Topsoil Placement(Remaining) | 15 | 2026-07-13 | 2026-07-29 | 2026-07-09 | 2026-07-12 | 14200.2 | 14200.2 | 14200.2 | 100% | 100% | 50 | 50 | 50 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-FB-50 | Goal Post Foundation | 17 | 2026-07-30 | 2026-08-18 | 2026-07-23 | 2026-08-14 | 35500.5 | 35500.5 | 35500.5 | 100% | 100% | 100 | 100 | 100 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-FB-120 | Installation of Lighting System | 13 | 2026-08-19 | 2026-09-02 | 2026-08-20 |  | 24360 | 20706 | 24360 | 100% | 85% | 32 | 32 | 27 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-FB-90 | Turfing / Seeding Works | 12 | 2026-09-03 | 2026-09-16 | 2026-08-14 |  | 23667 | 21300.3 | 23667 | 100% | 90% | 48 | 48 | 43 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-FB-40 | Tartan flooring | 15 | 2026-09-17 | 2026-10-05 | 2026-08-14 | 2026-08-14 | 2092-03-12 | 70200 | 70200 | 100% | 100% | 64 | 64 | 64 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-FB-60 | Goal Post Installation & Alignment | 15 | 2026-10-06 | 2026-10-22 | 2026-08-20 |  | 7100.1 | 28400.4 | 35500.5 | 20% | 80% | 56 | 11 | 45 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-FB-110 | Install Playground Benches | 12 | 2026-10-24 | 2026-11-05 | 2026-08-27 |  | 0 | 1648.13 | 2060.16 | 0% | 80% | 32 | 0 | 26 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-FB-100 | Markings and Signages | 10 | 2026-11-07 | 2026-11-17 |  |  | 0 | 0 | 23667 | 0% | 0% | 84 | 0 | 0 | No | 1 | 0 | 0 | 1
BASKETBALL PLAYGROUND WORKS |  | 163 | 2026-05-06 | 2026-11-17 | 2026-05-06 |  | 157714.68 | 154829.41 | 173211.12 | 91.05% | 89.39% | 608 | 533 | 548 |  | 11 | 7 | 3 | 1
PG-T-CON-EX-BB-10 | Subgrade Preparation and Compaction | 1 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 15472.08 | 15472.08 | 15472.08 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-BB-20 | Sub-Base Laying and Compaction | 1 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 15472.08 | 15472.08 | 15472.08 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-BB-30 | Base Course Laying and Compaction | 33 | 2026-05-06 | 2026-06-17 | 2026-05-06 | 2026-06-17 | 15472.08 | 15472.08 | 15472.08 | 100% | 100% | 96 | 96 | 96 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-BB-70 | Floor Surface Curing(Completed) | 7 | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 7736.04 | 7736.04 | 7736.04 | 100% | 100% | 12 | 12 | 12 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-BB-50 | Basketball Pole Foundation | 25 | 2026-06-25 | 2026-07-23 | 2026-08-06 | 2026-08-14 | 15472.08 | 15472.08 | 15472.08 | 100% | 100% | 100 | 100 | 100 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-BB-70_R | Floor Surface Curing(Remaining) | 15 | 2026-07-25 | 2026-08-10 | 2026-07-09 | 2026-07-12 | 7736.04 | 7736.04 | 7736.04 | 100% | 100% | 12 | 12 | 12 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-BB-40 | Tartan flooring | 17 | 2026-08-11 | 2026-08-30 | 2026-07-12 | 2026-08-14 | 52650 | 52650 | 52650 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-BB-80 | Court Line Marking | 16 | 2026-08-31 | 2026-09-17 | 2026-08-20 |  | 1935-11-03 18:14 | 1930-06-19 | 13091.76 | 100% | 85% | 28 | 28 | 24 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-BB-60 | Basketball Pole Installation & Alignment | 18 | 2026-09-19 | 2026-10-10 | 2026-08-20 |  | 14612.52 | 12377.66 | 15472.08 | 94.44% | 80% | 56 | 53 | 45 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-BB-90 | Backboard & Hoop Installation | 17 | 2026-10-11 | 2026-10-29 |  |  | 0 | 0 | 13091.76 | 0% | 0% | 40 | 0 | 0 | No | 1 | 0 | 0 | 1
PG-T-CON-EX-BB-100 | Install Playground Benches | 16 | 2026-10-31 | 2026-11-17 | 46261 |  | 0 | 1313.35 | 1545.12 | 0% | 85% | 32 | 0 | 27 | No | 1 | 0 | 1 | 0
PADEL PLAYGROUND WORKS |  | 180 | 2026-05-06 | 2026-12-07 | 2026-05-06 |  | 61164.06 | 80690.72 | 116989.92 | 52.28% | 68.97% | 424 | 326 | 286 |  | 11 | 5 | 4 | 2
PG-T-CON-EX-PD-10 | Excavation For Fence Footing(Completed) | 39 | 2026-05-06 | 2026-06-24 | 2026-05-06 | 2026-06-24 | 16243.2 | 16243.2 | 16243.2 | 100% | 100% | 54 | 54 | 54 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-PD-20 | RC Foundations For Fence(Completed) | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 1767.48 | 1767.48 | 1767.48 | 100% | 100% | 24 | 24 | 24 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-PD-30 | Tartan Flooring Layers(Completed) | 7 | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 26325 | 26325 | 26325 | 100% | 100% | 20 | 20 | 20 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-PD-10_R | Excavation For Fence Footing(Remaining) | 8 | 2026-06-25 | 2026-07-04 | 2026-08-06 | 2026-08-14 | 1804.8 | 1804.8 | 1804.8 | 100% | 100% | 6 | 6 | 6 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-PD-20_R | RC Foundations For Fence(Remaining) | 20 | 2026-07-05 | 2026-07-27 | 2026-08-14 | 2026-08-27 | 1767.48 | 1904-11-01 11:31 | 1767.48 | 100% | 100% | 24 | 24 | 24 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-PD-40 | Steel Structure & Fence Supports Installation | 20 | 2026-08-08 | 2026-08-30 | 2026-08-20 |  | 3534.96 | 3004.72 | 3534.96 | 100% | 85% | 56 | 56 | 48 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-PD-60 | Chain Link Fence & Gates Installation | 18 | 2026-08-31 | 2026-09-20 | 2026-08-20 |  | 1914-07-07 10:34 | 1913-01-23 04:48 | 5302.44 | 100% | 90% | 72 | 72 | 65 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-PD-50 | Tempered Glass Installation | 18 | 2026-09-21 | 2026-10-12 |  |  | 1912-02-04 16:48 | 0 | 5302.44 | 83.33% | 0% | 84 | 70 | 0 | No | 1 | 0 | 0 | 1
PG-T-CON-EX-PD-30_R | Tartan Flooring Layers(Remaining) | 17 | 2026-10-13 | 2026-11-01 | 2026-08-20 |  | 0 | 23692.5 | 26325 | 0% | 90% | 20 | 0 | 18 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-PD-70 | Court Accessories Installation | 16 | 2026-11-02 | 2026-11-19 |  |  | 0 | 0 | 27072 | 0% | 0% | 32 | 0 | 0 | No | 1 | 0 | 0 | 1
PG-T-CON-EX-PD-80 | Install Playground Benches | 15 | 2026-11-21 | 2026-12-07 | 2026-08-27 |  | 0 | 1313.35 | 1545.12 | 0% | 85% | 32 | 0 | 27 | No | 1 | 0 | 1 | 0
GENERAL SITE WORKS |  | 203 | 2026-04-16 | 2026-12-14 | 2026-04-16 |  | 565038.87 | 470510.34 | 656604.42 | 86.05% | 71.66% | 1996 | 1377 | 1101 |  | 47 | 12 | 22 | 13
FENCE WORKS |  | 102 | 2026-04-16 | 2026-08-17 | 2026-04-16 |  | 32909.4 | 24352.96 | 32909.4 | 100% | 74% | 336 | 336 | 249 |  | 5 | 2 | 2 | 1
PG-T-CON-EX-GN-FN-10 | Excavation for fence foundation | 3 | 2026-04-16 | 2026-04-19 | 2026-04-16 | 2026-04-19 | 6581.88 | 6581.88 | 6581.88 | 100% | 100% | 92 | 92 | 92 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-GN-FN-20 | Concrete Foundations for Fence | 12 | 2026-07-13 | 2026-07-26 | 2026-08-13 | 2026-08-20 | 6581.88 | 1918-01-06 21:07 | 6581.88 | 100% | 100% | 68 | 68 | 68 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-GN-FN-30 | Installation of Galvanized Steel Posts & Framing | 7 | 2026-07-27 | 2026-08-03 | 2026-08-20 |  | 6581.88 | 5923.69 | 6581.88 | 100% | 90% | 56 | 56 | 50 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-FN-40 | Fixing of Chain Link Mesh, Tensioning & Bracing | 6 | 2026-08-04 | 2026-08-10 | 2026-09-20 |  | 6581.88 | 5265.5 | 6581.88 | 100% | 80% | 48 | 48 | 38 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-FN-50 | Installation of Gates | 6 | 2026-08-11 | 2026-08-17 |  |  | 6581.88 | 0 | 6581.88 | 100% | 0% | 72 | 72 | 0 | No | 1 | 0 | 0 | 1
MECHANICAL WORK |  | 74 | 2026-05-12 | 2026-08-10 | 2026-05-12 |  | 230187.54 | 192496.27 | 230187.54 | 100% | 83.63% | 476 | 476 | 311 |  | 13 | 4 | 5 | 4
STORM WATER AND UTILITY WORK |  | 69 | 2026-05-12 | 2026-08-04 | 2026-05-12 |  | 27252 | 15732 | 27252 | 100% | 57.73% | 300 | 300 | 182 |  | 8 | 3 | 2 | 3
PG-T-CON-EX-GN-M-10 | Excavation | 2 | 2026-05-12 | 2026-05-13 | 2026-05-12 | 2026-05-13 | 3096 | 3096 | 3096 | 100% | 100% | 92 | 92 | 92 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-GN-M-20 | Bedding preparation & level control(Completed) | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 1548 | 1548 | 1548 | 100% | 100% | 24 | 24 | 24 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-GN-M-20_R | Bedding preparation & level control(Remaining) | 5 | 2026-06-25 | 2026-06-30 | 2026-07-12 | 2026-08-27 | 1901-05-30 | 1901-05-30 | 516 | 100% | 100% | 8 | 8 | 8 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-GN-M-30 | Manhole Installation | 5 | 2026-07-01 | 2026-07-06 | 2026-08-20 |  | 5160 | 1911-04-20 | 5160 | 100% | 80% | 48 | 48 | 38 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-M-40 | 150 mm uPVC pipe laying & jointing | 4 | 2026-07-07 | 2026-07-11 | 46285 |  | 10740 | 1917-08-22 | 10740 | 100% | 60% | 32 | 32 | 19 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-M-50 | Concrete Encasement | 3 | 2026-07-12 | 2026-07-14 |  |  | 2064 | 0 | 2064 | 100% | 0% | 24 | 24 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-GN-M-60 | Backfilling & Compaction | 3 | 2026-07-15 | 2026-07-18 |  |  | 2064 | 0 | 2064 | 100% | 0% | 48 | 48 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-GN-M-70 | Surface Reinstatement & Civil Works | 4 | 2026-08-01 | 2026-08-04 |  |  | 2064 | 0 | 2064 | 100% | 0% | 24 | 24 | 0 | Yes | 1 | 0 | 0 | 1
IRRIGATION SYSTEM WORKS |  | 51 | 2026-06-02 | 2026-07-30 | 2026-06-02 |  | 202617.6 | 176764.27 | 202617.6 | 100% | 87.24% | 144 | 144 | 129 |  | 4 | 1 | 3 | 0
PG-T-CON-EX-GN-M-80 | Installation of HDPE Irrigation Pipe Network with Gate Valve and Box(Completed) | 20 | 2026-06-02 | 2026-06-24 | 2026-06-02 | 2026-06-24 | 18691.26 | 18691.26 | 18691.26 | 100% | 100% | 28 | 28 | 28 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-GN-M-80_R | Installation of HDPE Irrigation Pipe Network with Gate Valve and Box(Remaining) | 4 | 2026-07-14 | 2026-07-18 | 2026-07-12 |  | 34712.34 | 31241.11 | 34712.34 | 100% | 90% | 52 | 52 | 47 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-M-90 | Installation of Irrigation Control System | 6 | 2026-07-19 | 2026-07-25 | 2026-08-20 |  | 90915 | 2111-07-29 18:00 | 90915 | 100% | 85% | 32 | 32 | 27 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-M-100 | Installation of Bubblers and Sprinklers | 5 | 2026-07-26 | 2026-07-30 | 2026-08-20 |  | 58299 | 49554.15 | 58299 | 100% | 85% | 32 | 32 | 27 | Yes | 1 | 0 | 1 | 0
FIRE PROTECTION SYSTEM |  | 5 | 2026-08-05 | 2026-08-10 |  |  | 317.94 | 0 | 317.94 | 100% | 0% | 32 | 32 | 0 |  | 1 | 0 | 0 | 1
PG-T-CON-EX-GN-M-110 | Fire Extinguisher Installation | 5 | 2026-08-05 | 2026-08-10 |  |  | 317.94 | 0 | 317.94 | 100% | 0% | 32 | 32 | 0 | Yes | 1 | 0 | 0 | 1
ELECTRICAL WORK |  | 130 | 2026-06-08 | 2026-11-07 | 2026-06-08 |  | 295483.53 | 225733.52 | 345859.68 | 85.43% | 65.27% | 784 | 516 | 333 |  | 20 | 2 | 13 | 5
POWER, LIGHTING & GROUNDING |  | 95 | 2026-06-08 | 2026-09-27 | 2026-06-08 |  | 288789.48 | 212789.72 | 288789.48 | 100% | 73.68% | 376 | 376 | 252 |  | 9 | 2 | 6 | 1
PG-T-CON-EX-GN-E-10 | Excavation | 3 | 2026-06-08 | 2026-06-10 | 2026-06-08 | 2026-06-10 | 69621.12 | 69621.12 | 69621.12 | 100% | 100% | 92 | 92 | 92 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-GN-E-20 | Foundation Work for Site Lighting Poles(Completed) | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 37131.26 | 37131.26 | 37131.26 | 100% | 100% | 27 | 27 | 27 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-GN-E-20_R | Foundation Work for Site Lighting Poles(Remaining) | 21 | 2026-06-25 | 2026-07-19 | 2026-08-20 |  | 55696.9 | 2021-12-27 12:29 | 55696.9 | 100% | 80% | 41 | 41 | 33 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-E-30 | Lightning Protection System (LPS) | 8 | 2026-08-11 | 2026-08-19 | 2026-08-20 |  | 1922-08-17 | 1919-03-26 06:00 | 8265 | 100% | 85% | 32 | 32 | 27 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-E-40 | KWH Meter and MDB Installation | 5 | 2026-08-25 | 2026-08-30 | 46282 |  | 1912-07-21 16:48 | 1906-04-11 08:24 | 4586.7 | 100% | 50% | 32 | 32 | 16 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-E-50 | Power Panels and Distribution Boards | 7 | 2026-08-31 | 2026-09-07 | 46282 |  | 1947-08-18 21:36 | 1923-10-24 22:48 | 17397.9 | 100% | 50% | 40 | 40 | 20 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-E-60 | Site Lighting Poles Installation | 6 | 2026-09-08 | 2026-09-14 | 46282 |  | 2090-08-11 02:53 | 2014-05-13 16:05 | 69621.12 | 100% | 60% | 40 | 40 | 24 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-E-70 | Wiring Works | 4 | 2026-09-15 | 2026-09-19 | 46299 |  | 1911-07-25 | 1904-08-15 14:24 | 4224 | 100% | 40% | 32 | 32 | 13 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-E-80 | Lighting Fixtures with outlets Installation | 6 | 2026-09-20 | 2026-09-27 |  |  | 22245.48 | 0 | 22245.48 | 100% | 0% | 40 | 40 | 0 | Yes | 1 | 0 | 0 | 1
ELV SYSTEMS (TELECOM, DATA, AV & CCTV) |  | 25 | 2026-09-28 | 2026-10-26 | 46287 |  | 1913-07-28 09:36 | 1935-06-08 19:12 | 43146 | 11.49% | 30% | 272 | 112 | 82 |  | 7 | 0 | 7 | 0
PG-T-CON-EX-GN-E-90 | ELV Containment & Cabling Works | 3 | 2026-09-28 | 2026-09-30 | 46287 |  | 1901-09-10 19:12 | 1900-07-03 22:34 | 619.8 | 100% | 30% | 40 | 40 | 12 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-E-100 | Fiber Optic Pull Box Installation | 3 | 2026-10-01 | 2026-10-04 | 46287 |  | 1901-09-10 19:12 | 1900-07-03 22:34 | 619.8 | 100% | 30% | 32 | 32 | 10 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-E-110 | Telephone and Data Outlet Installation | 4 | 2026-10-05 | 2026-10-08 | 46287 |  | 1910-03-06 19:12 | 1903-01-19 15:22 | 3718.8 | 100% | 30% | 40 | 40 | 12 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-E-120 | Telecom Equipment and AV HDMI Installation | 4 | 2026-10-10 | 2026-10-13 | 46287 |  | 0 | 1912-07-09 17:46 | 15249.12 | 0% | 30% | 40 | 0 | 12 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-E-130 | CCTV Rack / Cabinet Installation | 4 | 2026-10-14 | 2026-10-18 | 46287 |  | 0 | 1901-03-08 22:34 | 1446.48 | 0% | 30% | 40 | 0 | 12 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-E-140 | NVR and CCTV Monitor Installation | 4 | 2026-10-19 | 2026-10-22 | 46287 |  | 0 | 1905-06-05 14:24 | 6612 | 0% | 30% | 40 | 0 | 12 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-E-150 | IP Camera Installation | 3 | 2026-10-24 | 2026-10-26 | 46287 |  | 0 | 1912-03-21 | 14880 | 0% | 30% | 40 | 0 | 12 | Yes | 1 | 0 | 1 | 0
FIRE ALARM SYSTEM |  | 32 | 2026-10-01 | 2026-11-07 |  |  | 1904-09-30 15:36 | 0 | 13924.2 | 12.46% | 0% | 136 | 28 | 0 |  | 4 | 0 | 0 | 4
PG-T-CON-EX-GN-E-160 | Fire Alarm Containment & Cabling | 8 | 2026-10-01 | 2026-10-10 |  |  | 1904-09-30 15:36 | 0 | 1983.6 | 87.5% | 0% | 32 | 28 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-GN-E-170 | Fire Alarm Control Panel (FACP) Installation | 8 | 2026-10-11 | 2026-10-19 |  |  | 0 | 0 | 2644.8 | 0% | 0% | 24 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-GN-E-180 | Initiating Devices (Detectors & Manual Pull Station) | 8 | 2026-10-20 | 2026-10-28 |  |  | 0 | 0 | 8097.6 | 0% | 0% | 40 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-GN-E-190 | Notification Appliances (Strobe with Sounder) | 8 | 2026-10-29 | 2026-11-07 |  |  | 0 | 0 | 1198.2 | 0% | 0% | 40 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PARKING WORK |  | 126 | 2026-06-17 | 2026-11-11 | 2026-06-17 |  | 5788.8 | 23798.4 | 40207.8 | 14.4% | 59.19% | 164 | 22 | 75 |  | 4 | 2 | 1 | 1
PG-T-CON-EX-GN-PR-20 | Interlock tiles(Completed) | 7 | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 5788.8 | 5788.8 | 5788.8 | 100% | 100% | 22 | 22 | 22 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-GN-PR-10 | Installlation of Parking Accessories | 7 | 2026-10-27 | 2026-11-03 | 2026-08-20 |  | 0 | 10934.4 | 12864 | 0% | 85% | 32 | 0 | 27 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-PR-20_R | Interlock tiles(Remaining) | 7 | 2026-10-27 | 2026-11-03 | 2026-07-12 | 2026-08-27 | 0 | 7075.2 | 7075.2 | 0% | 100% | 26 | 0 | 26 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-GN-PR-30 | Marking & Signages | 7 | 2026-11-04 | 2026-11-11 |  |  | 0 | 0 | 14479.8 | 0% | 0% | 84 | 0 | 0 | Yes | 1 | 0 | 0 | 1
SERVICE CONNECTION |  | 160 | 2026-06-10 | 2026-12-14 | 2026-06-10 |  | 1901-10-30 14:24 | 4129.2 | 7440 | 9% | 55.5% | 236 | 28 | 133 |  | 5 | 2 | 1 | 2
PG-T-CON-EX-GN-SC-10 | Excavation & Trench Preparation(Completed) | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 1901-10-30 14:24 | 669.6 | 669.6 | 100% | 100% | 28 | 28 | 28 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-GN-SC-10_R | Excavation & Trench Preparation(Remaining) | 7 | 2026-11-04 | 2026-11-11 | 2026-07-12 | 2026-07-23 | 0 | 1562.4 | 1562.4 | 0% | 100% | 64 | 0 | 64 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-GN-SC-20 | HDPE Pipe Laying & Valve Installation | 10 | 2026-11-12 | 2026-11-23 | 2026-08-14 |  | 0 | 1897.2 | 2232 | 0% | 85% | 48 | 0 | 41 | Yes | 1 | 0 | 1 | 0
PG-T-CON-EX-GN-SC-30 | Connection to City Network | 10 | 2026-11-24 | 2026-12-05 |  |  | 0 | 0 | 1488 | 0% | 0% | 48 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-GN-SC-40 | Backfilling | 8 | 2026-12-06 | 2026-12-14 |  |  | 0 | 0 | 1488 | 0% | 0% | 48 | 0 | 0 | Yes | 1 | 0 | 0 | 1
LANDSCAPING WORKS |  | 150 | 2026-05-31 | 2026-11-22 | 2026-05-30 |  | 482244.9 | 704953.89 | 755169 | 63.86% | 93.35% | 392 | 159 | 321 |  | 14 | 8 | 6 | 0
HARDSCAPE WORK |  | 150 | 2026-05-31 | 2026-11-22 | 2026-05-30 |  | 457884.9 | 626473.89 | 648147 | 70.65% | 96.66% | 224 | 126 | 202 |  | 11 | 7 | 4 | 0
PG-T-CON-EX-LS-HS-10 | Curbstone Installation(Completed) | 22 | 2026-05-31 | 2026-06-24 | 2026-05-30 | 2026-06-24 | 124077.6 | 124077.6 | 124077.6 | 100% | 100% | 19 | 19 | 19 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-LS-HS-20 | Interlock Tiles Grey Scale with Black Marble Chips(Completed) | 22 | 2026-05-31 | 2026-06-24 | 2026-05-30 | 2026-06-24 | 40656 | 40656 | 40656 | 100% | 100% | 19 | 19 | 19 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-LS-HS-40 | Bike Path and Walking Path Construction(Completed) | 22 | 2026-05-31 | 2026-06-24 | 2026-05-30 | 2026-06-24 | 99297 | 99297 | 99297 | 100% | 100% | 26 | 26 | 26 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-LS-HS-50 | Install Recycled Precast Concrete Seats(Completed) | 22 | 2026-05-31 | 2026-06-24 | 2026-05-30 | 2026-06-24 | 6681.9 | 6681.9 | 6681.9 | 100% | 100% | 3 | 3 | 3 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-LS-HS-30 | Stamped Concrete Floor(Completed) | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 43470 | 43470 | 43470 | 100% | 100% | 16 | 16 | 16 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-LS-HS-10_R | Curbstone Installation(Remaining) | 8 | 2026-09-17 | 2026-09-27 | 2026-07-12 | 2026-08-27 | 82718.4 | 82718.4 | 82718.4 | 100% | 100% | 13 | 13 | 13 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-LS-HS-20_R | Interlock Tiles Grey Scale with Black Marble Chips(Remaining) | 10 | 2026-09-28 | 2026-10-08 | 2026-08-27 |  | 2066-12-18 | 51836.4 | 60984 | 100% | 85% | 29 | 29 | 24 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-LS-HS-30_R | Stamped Concrete Floor(Remaining) | 10 | 2026-10-10 | 2026-10-20 | 2026-07-30 |  | 0 | 39123 | 43470 | 0% | 90% | 16 | 0 | 14 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-LS-HS-40_R | Bike Path and Walking Path Construction(Remaining) | 8 | 2026-10-21 | 2026-10-29 | 2026-07-23 | 2026-08-27 | 0 | 81243 | 81243 | 0% | 100% | 22 | 0 | 22 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-LS-HS-50_R | Install Recycled Precast Concrete Seats(Remaining) | 10 | 2026-10-31 | 2026-11-10 | 2026-07-30 |  | 0 | 2048-03-06 09:22 | 60137.1 | 0% | 90% | 29 | 0 | 26 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-LS-HS-60 | Install Recycled Precast Concrete Trash Bins | 10 | 2026-11-11 | 2026-11-22 | 2026-09-23 |  | 0 | 3247.2 | 5412 | 0% | 60% | 32 | 0 | 19 | No | 1 | 0 | 1 | 0
SOFTSCAPE WORK |  | 141 | 2026-06-10 | 2026-11-22 | 2026-06-10 |  | 24360 | 78480 | 107022 | 22.76% | 73.33% | 168 | 34 | 118 |  | 3 | 1 | 2 | 0
PG-T-CON-EX-LS-SS-20 | Lawn Area Preparation & Planting / Turfing(Completed) | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 24360 | 24360 | 24360 | 100% | 100% | 34 | 34 | 34 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-LS-SS-10 | Planting Trees | 12 | 2026-10-10 | 2026-10-22 | 2026-09-22 |  | 0 | 23061 | 46122 | 0% | 50% | 84 | 0 | 42 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-LS-SS-20_R | Lawn Area Preparation & Planting / Turfing(Remaining) | 6 | 2026-11-16 | 2026-11-22 | 2026-07-12 |  | 0 | 31059 | 36540 | 0% | 85% | 50 | 0 | 43 | No | 1 | 0 | 1 | 0
TANK WORKS |  | 113 | 2026-05-13 | 2026-09-27 | 2026-05-13 |  | 48290.4 | 9622.8 | 48290.4 | 100% | 19.93% | 628 | 628 | 474 |  | 14 | 10 | 1 | 3
SEPTIC TANK |  | 94 | 2026-05-13 | 2026-09-03 | 2026-05-13 |  | 7475.22 | 3520.62 | 7475.22 | 100% | 47.1% | 364 | 364 | 262 |  | 8 | 5 | 1 | 2
PG-T-CON-EX-TW-ST-10 | Excavation | 21 | 2026-05-13 | 2026-06-10 | 2026-05-13 | 2026-06-10 | 1900-09-08 04:19 | 252.18 | 1900-09-08 04:19 | 100% | 100% | 92 | 92 | 92 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-TW-ST-20 | PCC / Lean Concrete laying | 27 | 2026-05-20 | 2026-06-24 | 2026-05-20 | 2026-06-24 | 1900-06-16 02:53 | 168.12 | 168.12 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-TW-ST-30 | RCC Foundation(Completed) | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 1902-06-12 08:24 | 894.35 | 894.35 | 100% | 100% | 39 | 39 | 39 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-TW-ST-30_R | RCC Foundation(Remaining) | 10 | 2026-06-25 | 2026-07-06 | 2026-07-12 | 2026-08-27 | 1901-01-17 06:58 | 1901-01-17 06:58 | 1901-01-17 06:58 | 100% | 100% | 17 | 17 | 17 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-TW-ST-40 | RCC Wall | 9 | 2026-07-07 | 2026-07-16 | 2026-08-14 |  | 2757.6 | 1904-07-11 13:26 | 2757.6 | 100% | 60% | 56 | 56 | 34 | No | 1 | 0 | 1 | 0
PG-T-CON-EX-TW-ST-50 | RCC Slab | 13 | 2026-07-18 | 2026-08-01 |  |  | 2599.38 | 0 | 2599.38 | 100% | 0% | 56 | 56 | 0 | No | 1 | 0 | 0 | 1
PG-T-CON-EX-TW-ST-60 | Finishing Work | 8 | 2026-08-18 | 2026-08-26 |  |  | 252.18 | 0 | 252.18 | 100% | 0% | 24 | 24 | 0 | No | 1 | 0 | 0 | 1
PG-T-CON-EX-TW-ST-70 | Backfilling | 7 | 2026-08-27 | 2026-09-03 | 46254 | 2026-08-24 | 168.12 | 168.12 | 168.12 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
WATER STORAGE TANK |  | 113 | 2026-05-13 | 2026-09-27 | 2026-05-13 |  | 40815.18 | 6102.18 | 40815.18 | 100% | 14.95% | 264 | 264 | 212 |  | 6 | 5 | 0 | 1
PG-T-CON-EX-TW-IR-10 | Excavation(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 1902-02-04 13:55 | 766.58 | 766.58 | 100% | 100% | 83 | 83 | 83 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-TW-IR-20 | RCC Foundation(Completed) | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 1654.56 | 1654.56 | 1654.56 | 100% | 100% | 29 | 29 | 29 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-TW-IR-10_R | Excavation(Remaining) | 6 | 2026-08-29 | 2026-09-03 | 2026-07-08 | 2026-07-09 | 1900-03-25 04:19 | 1900-03-25 04:19 | 85.18 | 100% | 100% | 9 | 9 | 9 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-TW-IR-20_R | RCC Foundation(Remaining) | 8 | 2026-09-05 | 2026-09-13 | 2026-07-16 | 2026-08-27 | 2481.84 | 2481.84 | 2481.84 | 100% | 100% | 43 | 43 | 43 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-TW-IR-30 | Backfilling | 6 | 2026-09-14 | 2026-09-20 | 2026-08-14 | 2026-08-25 | 1114.02 | 1114.02 | 1114.02 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-TW-IR-40 | GRP Water Tank Installation | 5 | 2026-09-21 | 2026-09-27 |  |  | 34713 | 0 | 34713 | 100% | 0% | 52 | 52 | 0 | No | 1 | 0 | 0 | 1
AIR DOME CONSTRUCTION |  | 171 | 2026-05-13 | 2026-12-03 | 2026-05-13 |  | 2573468.96 | 1210693.39 | 4178041.2 | 61.6% | 28.98% | 1116 | 726 | 392 |  | 21 | 7 | 0 | 14
CIVIL WORK |  | 103 | 2026-05-13 | 2026-09-14 | 2026-05-13 |  | 1711669.97 | 1210693.39 | 1711669.97 | 100% | 70.73% | 536 | 536 | 392 |  | 9 | 7 | 0 | 2
PG-T-CON-EX-AD-CL-10 | Excavation For Footing(Completed) | 33 | 2026-05-13 | 2026-06-24 | 2026-05-13 | 2026-06-24 | 25048.83 | 25048.83 | 25048.83 | 100% | 100% | 10 | 10 | 10 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-AD-CL-10_R | Excavation For Footing(Remaining) | 7 | 2026-07-05 | 2026-07-12 | 2026-07-08 | 2026-07-10 | 225439.46 | 225439.46 | 225439.46 | 100% | 100% | 90 | 90 | 90 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-AD-CL-20 | Anti-Termite Treatment | 1 | 2026-07-13 | 2026-07-13 | 2026-07-10 | 2026-07-10 | 83496.1 | 83496.1 | 83496.1 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-AD-CL-30 | PCC / Blinding Concrete | 3 | 2026-07-25 | 2026-07-27 | 2026-07-22 | 2026-07-23 | 125244.14 | 125244.14 | 125244.14 | 100% | 100% | 64 | 64 | 64 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-AD-CL-40 | RCC Foundation Works | 9 | 2026-07-28 | 2026-08-06 | 2026-07-23 | 2026-08-13 | 250488.29 | 250488.29 | 250488.29 | 100% | 100% | 88 | 88 | 88 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-AD-CL-50 | Backfilling with Compaction | 8 | 2026-08-08 | 2026-08-16 | 2026-08-07 | 2026-08-14 | 250488.29 | 250488.29 | 250488.29 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-AD-CL-60 | Installation of Anchorage System | 8 | 2026-08-17 | 2026-08-25 | 2026-08-27 | 2026-09-23 | 250488.29 | 250488.29 | 250488.29 | 100% | 100% | 60 | 60 | 60 | No | 1 | 1 | 0 | 0
PG-T-CON-EX-AD-CL-70 | Installation of Steel Cable Structural System | 9 | 2026-08-26 | 2026-09-05 |  |  | 250488.29 | 0 | 250488.29 | 100% | 0% | 76 | 76 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-AD-CL-80 | Installation of Membrane System | 8 | 2026-09-06 | 2026-09-14 |  |  | 250488.29 | 0 | 250488.29 | 100% | 0% | 68 | 68 | 0 | Yes | 1 | 0 | 0 | 1
ARCHITECTURAL WORK |  | 25 | 2026-11-05 | 2026-12-03 |  |  | 0 | 0 | 712953.22 | 0% | 0% | 212 | 0 | 0 |  | 4 | 0 | 0 | 4
PG-T-CON-EX-AD-AR-10 | Installation of Thermal Insulation System | 7 | 2026-11-05 | 2026-11-12 |  |  | 0 | 0 | 250488.29 | 0% | 0% | 60 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-AD-AR-40 | Final Fixing of Accessories & Finishes | 7 | 2026-11-14 | 2026-11-21 |  |  | 0 | 0 | 208740.24 | 0% | 0% | 56 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-AD-AR-20 | Installation of Doors & Access Systems | 6 | 2026-11-22 | 2026-11-28 |  |  | 0 | 0 | 250488.29 | 0% | 0% | 56 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-AD-AR-30 | Installation of Logo | 5 | 2026-11-29 | 2026-12-03 |  |  | 0 | 0 | 3236.4 | 0% | 0% | 40 | 0 | 0 | Yes | 1 | 0 | 0 | 1
MECHANICAL WORK |  | 23 | 2026-09-15 | 2026-10-12 |  |  | 563598.65 | 0 | 667968.77 | 84.38% | 0% | 160 | 136 | 0 |  | 3 | 0 | 0 | 3
PG-T-CON-EX-AD-ME-10 | Installation of Main Air Package Units | 5 | 2026-09-15 | 2026-09-20 |  |  | 250488.29 | 0 | 250488.29 | 100% | 0% | 56 | 56 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-AD-ME-20 | Installation of Backup Air Package Unit | 5 | 2026-09-21 | 2026-09-27 |  |  | 208740.24 | 0 | 208740.24 | 100% | 0% | 56 | 56 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-AD-ME-30 | Installation of Complete HVAC System | 6 | 2026-10-06 | 2026-10-12 |  |  | 2185-10-01 02:53 | 0 | 208740.24 | 50% | 0% | 48 | 24 | 0 | Yes | 1 | 0 | 0 | 1
ELECTRICAL WORK |  | 33 | 2026-09-28 | 2026-11-04 |  |  | 298200.34 | 0 | 1085449.25 | 27.47% | 0% | 208 | 54 | 0 |  | 5 | 0 | 0 | 5
PG-T-CON-EX-AD-EL-10 | Installation of Electrical Boxes & MDBs | 7 | 2026-09-28 | 2026-10-05 |  |  | 208740.24 | 0 | 208740.24 | 100% | 0% | 40 | 40 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-AD-EL-20 | Installation of Lighting System | 7 | 2026-10-06 | 2026-10-13 |  |  | 2144-12-05 02:24 | 0 | 208740.24 | 42.86% | 0% | 32 | 14 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-AD-EL-30 | Electrical Connections to Main Power Source (Excluding kWh Meter) | 5 | 2026-10-14 | 2026-10-19 |  |  | 0 | 0 | 208740.24 | 0% | 0% | 40 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-AD-EL-40 | Installation of Backup Generator | 6 | 2026-10-20 | 2026-10-26 |  |  | 0 | 0 | 208740.24 | 0% | 0% | 48 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-CON-EX-AD-EL-50 | Installation of Smart Dome System | 8 | 2026-10-27 | 2026-11-04 |  |  | 0 | 0 | 250488.29 | 0% | 0% | 48 | 0 | 0 | Yes | 1 | 0 | 0 | 1
TOILET BUILDING WORKS |  | 141 | 2026-05-12 | 2026-10-28 | 2026-05-12 |  | 174381.54 | 298150 | 324844.38 | 53.68% | 91.78% | 1708 | 1306 | 1596 |  | 40 | 34 | 6 | 0
CIVIL WORK |  | 139 | 2026-05-12 | 2026-10-26 | 2026-05-12 |  | 84475.8 | 220184.04 | 227117.58 | 37.19% | 96.95% | 1100 | 778 | 1063 |  | 24 | 22 | 2 | 0
STRUCTURAL WORK |  | 66 | 2026-05-12 | 2026-08-01 | 2026-05-12 | 2026-08-12 | 37980 | 37980 | 37980 | 100% | 100% | 372 | 372 | 372 |  | 7 | 7 | 0 | 0
PG-T-CON-B-STR-10 | Excavation up to bottom of footing | 2 | 2026-05-12 | 2026-05-13 | 2026-05-12 | 2026-05-13 | 1900.8 | 1900.8 | 1900.8 | 100% | 100% | 92 | 92 | 92 | No | 1 | 1 | 0 | 0
PG-T-CON-B-STR-20 | Anti-termite treatment and Polyethene Sheet | 2 | 2026-05-12 | 2026-05-13 | 2026-05-12 | 2026-05-13 | 3294 | 3294 | 3294 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-T-CON-B-STR-30 | Backfilling with selected fill material (under footing) | 1 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 1900.8 | 1900.8 | 1900.8 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
PG-T-CON-B-STR-40 | Raft Foundation Work | 27 | 2026-05-13 | 2026-06-17 | 2026-05-13 | 2026-06-17 | 2534.4 | 2534.4 | 2534.4 | 100% | 100% | 64 | 64 | 64 | No | 1 | 1 | 0 | 0
PG-T-CON-B-STR-50 | Autoclaved aerated panel (walls) | 9 | 2026-07-07 | 2026-07-16 | 2026-07-07 | 2026-07-09 | 11340 | 11340 | 11340 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-B-STR-60 | Autoclaved aerated panel (ceiling) | 9 | 2026-07-18 | 2026-07-27 | 2026-07-09 | 2026-07-31 | 8505 | 8505 | 8505 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-B-STR-70 | Autoclaved aerated panel (parapet) | 4 | 2026-07-28 | 2026-08-01 | 2026-07-11 | 2026-08-12 | 8505 | 8505 | 8505 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
ARCHITECTURAL WORK |  | 73 | 2026-08-02 | 2026-10-26 | 2026-08-01 |  | 46495.8 | 182204.04 | 189137.58 | 24.58% | 96.33% | 728 | 406 | 691 |  | 17 | 15 | 2 | 0
GENERAL FINISHES |  | 69 | 2026-08-02 | 2026-10-21 | 2026-08-01 | 2026-09-07 | 11016.6 | 84120 | 84120 | 13.1% | 100% | 376 | 248 | 376 |  | 8 | 8 | 0 | 0
PG-T-CON-B-AR-GF-10 | Block Works | 6 | 2026-08-02 | 2026-08-08 | 2026-08-01 | 2026-08-06 | 1906-10-19 | 2484 | 2484 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-GF-20 | Plaster | 7 | 2026-08-18 | 2026-08-25 | 2026-08-06 | 2026-08-07 | 4427.4 | 4427.4 | 4427.4 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-GF-30 | False Ceiling Installation & Finishing | 8 | 2026-08-26 | 2026-09-03 | 2026-08-20 | 2026-09-07 | 1902-05-22 14:24 | 1902-05-22 14:24 | 873.6 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-GF-40 | Wall Paint | 10 | 2026-09-19 | 2026-09-30 | 2026-08-20 | 2026-09-07 | 1908-02-05 | 1908-02-05 | 2958 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-GF-50 | Epoxy Flooring | 7 | 2026-10-01 | 2026-10-08 | 2026-08-20 | 2026-09-07 | 1900-09-29 14:24 | 273.6 | 273.6 | 100% | 100% | 56 | 56 | 56 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-GF-60 | Install Doors & Windows | 4 | 2026-10-10 | 2026-10-13 | 2026-08-27 | 2026-09-07 | 0 | 13273.8 | 13273.8 | 0% | 100% | 32 | 0 | 32 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-GF-80 | Facade Finishing Work | 9 | 2026-10-10 | 2026-10-19 | 2026-08-20 | 2026-09-07 | 0 | 52278 | 52278 | 0% | 100% | 48 | 0 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-GF-70 | Lockers and Furniture Installation | 2 | 2026-10-20 | 2026-10-21 | 2026-08-27 | 2026-09-07 | 0 | 7551.6 | 7551.6 | 0% | 100% | 48 | 0 | 48 | No | 1 | 1 | 0 | 0
WET AREA FINISHES |  | 41 | 2026-08-26 | 2026-10-13 | 2026-08-06 |  | 1993-11-18 04:48 | 78979.14 | 81123.78 | 42.27% | 97.36% | 216 | 149 | 203 |  | 6 | 5 | 1 | 0
PG-T-CON-B-AR-WF-10 | False Ceiling Installation & Finishing | 4 | 2026-08-26 | 2026-08-30 | 2026-08-20 | 2026-09-10 | 1907-12-07 | 2898 | 2898 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-WF-20 | Wall Tiles and Partition Work | 3 | 2026-10-01 | 2026-10-04 | 2026-08-06 | 2026-08-14 | 1958-04-08 04:48 | 21283.2 | 21283.2 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-WF-30 | Waterproofing on Floor | 2 | 2026-10-05 | 2026-10-06 | 2026-08-14 | 2026-09-10 | 1915-11-01 | 5784 | 5784 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-WF-40 | Floor Tiles Works | 3 | 2026-10-07 | 2026-10-10 | 2026-08-14 | 2026-09-10 | 1911-11-04 | 6489 | 6489 | 66.67% | 100% | 32 | 21 | 32 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-WF-50 | Toliet accessories Installation Works | 3 | 2026-10-11 | 2026-10-13 | 2026-08-20 | 2026-09-10 | 0 | 39307.98 | 39307.98 | 0% | 100% | 24 | 0 | 24 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-WF-60 | Install Doors | 2 | 2026-10-11 | 2026-10-12 | 46288 |  | 0 | 3216.96 | 5361.6 | 0% | 60% | 32 | 0 | 19 | No | 1 | 0 | 1 | 0
ROOF FINISHES |  | 17 | 2026-10-07 | 2026-10-26 | 2026-08-14 |  | 1903-04-02 | 19104.9 | 23893.8 | 4.97% | 79.96% | 136 | 9 | 112 |  | 3 | 2 | 1 | 0
PG-T-CON-B-AR-RF-10 | Waterproofing on Floor | 7 | 2026-10-07 | 2026-10-14 | 2026-08-14 | 2026-09-12 | 1188 | 4158 | 4158 | 28.57% | 100% | 32 | 9 | 32 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-RF-20 | Epoxy Flooring and Finishes | 7 | 2026-10-15 | 2026-10-22 | 2026-08-20 | 2026-09-12 | 0 | 10158 | 10158 | 0% | 100% | 56 | 0 | 56 | No | 1 | 1 | 0 | 0
PG-T-CON-B-AR-RF-30 | Steel ladder and Steel roof scupper Installation | 3 | 2026-10-24 | 2026-10-26 | 46284 |  | 0 | 1913-02-08 21:36 | 9577.8 | 0% | 50% | 48 | 0 | 24 | No | 1 | 0 | 1 | 0
MEP WORK |  | 115 | 2026-06-16 | 2026-10-28 | 2026-06-16 |  | 89905.74 | 77965.96 | 97726.8 | 92% | 79.78% | 608 | 528 | 533 |  | 16 | 12 | 4 | 0
MECANICAL WORKS |  | 115 | 2026-06-16 | 2026-10-28 | 2026-06-16 |  | 71658.42 | 59718.64 | 79479.48 | 90.16% | 75.14% | 400 | 320 | 325 |  | 11 | 7 | 4 | 0
FIRE FIGHTING SYSTEM |  | 2 | 2026-10-27 | 2026-10-28 | 2026-09-23 |  | 0 | 54.5 | 136.26 | 0% | 40% | 32 | 0 | 13 |  | 1 | 0 | 1 | 0
PG-T-CON-B-GF-FF-10 | Fire Extinguisher Installation | 2 | 2026-10-27 | 2026-10-28 | 46288 |  | 0 | 54.5 | 136.26 | 0% | 40% | 32 | 0 | 13 | No | 1 | 0 | 1 | 0
SEWER AND DRAINAGE SYSTEM |  | 70 | 2026-06-16 | 2026-09-05 | 2026-06-16 |  | 11290.02 | 9999.73 | 11290.02 | 100% | 88.57% | 144 | 144 | 125 |  | 5 | 4 | 1 | 0
PG-T-CON-B-GF-DR-10 | Sewer and Drainge System Main Lines Installation(Completed) | 8 | 2026-06-16 | 2026-06-24 | 2026-06-16 | 2026-06-24 | 967.72 | 967.72 | 967.72 | 100% | 100% | 14 | 14 | 14 | No | 1 | 1 | 0 | 0
PG-T-CON-B-GF-DR-20 | Sewer and Drainge System Pipes and fittings Installation(Completed) | 8 | 2026-06-16 | 2026-06-24 | 2026-06-16 | 2026-06-24 | 1451.57 | 1451.57 | 1451.57 | 100% | 100% | 14 | 14 | 14 | No | 1 | 1 | 0 | 0
PG-T-CON-B-GF-DR-10_R | Sewer and Drainge System Main Lines Installation(Remaining) | 1 | 2026-08-12 | 2026-08-13 | 2026-07-23 | 2026-09-10 | 1906-03-07 | 2258 | 2258 | 100% | 100% | 34 | 34 | 34 | No | 1 | 1 | 0 | 0
PG-T-CON-B-GF-DR-20_R | Sewer and Drainge System Pipes and fittings Installation(Remaining) | 1 | 2026-08-15 | 2026-08-16 | 2026-07-23 | 2026-07-31 | 3387.01 | 3387.01 | 3387.01 | 100% | 100% | 34 | 34 | 34 | No | 1 | 1 | 0 | 0
PG-T-CON-B-GF-DR-30 | Sanitaryware Installation (Final Fix) | 2 | 2026-09-03 | 2026-09-05 | 46288 |  | 1908-10-29 17:17 | 1905-04-18 10:19 | 3225.72 | 100% | 60% | 48 | 48 | 29 | No | 1 | 0 | 1 | 0
HVAC SYSTEM |  | 55 | 2026-08-09 | 2026-10-12 | 2026-08-13 |  | 4442.4 | 8284.8 | 12127.2 | 36.63% | 68.32% | 96 | 48 | 72 |  | 2 | 1 | 1 | 0
PG-T-CON-B-GF-AC-10 | Duct Work and Exhaust Fan Installation | 3 | 2026-08-09 | 2026-08-11 | 2026-08-13 | 2026-08-20 | 1912-02-28 09:36 | 4442.4 | 4442.4 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-B-GF-AC-20 | Split AC, Grills & Diffuser Installation | 2 | 2026-10-11 | 2026-10-12 | 46285 |  | 0 | 3842.4 | 7684.8 | 0% | 50% | 48 | 0 | 24 | No | 1 | 0 | 1 | 0
WATER SUPPLY SYSTEM |  | 19 | 2026-08-12 | 2026-09-02 | 2026-07-22 |  | 55926 | 41379.6 | 55926 | 100% | 73.99% | 128 | 128 | 115 |  | 3 | 2 | 1 | 0
PG-T-CON-B-GF-WS-10 | Water Supply Main Lines Installation | 2 | 2026-08-12 | 2026-08-13 | 2026-07-22 | 2026-09-10 | 5702.4 | 5702.4 | 5702.4 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-B-GF-WS-20 | Water Supply Pipes Installation (Cold and Hot Water) | 2 | 2026-08-15 | 2026-08-16 | 2026-07-23 | 2026-07-30 | 13857.6 | 13857.6 | 13857.6 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-B-GF-WS-30 | Water Supply Accesories and Booster pump Installation | 3 | 2026-08-31 | 2026-09-02 | 46288 |  | 1999-07-25 | 21819.6 | 36366 | 100% | 60% | 32 | 32 | 19 | No | 1 | 0 | 1 | 0
ELECTRICAL WORKS |  | 30 | 2026-08-15 | 2026-09-17 | 2026-07-22 | 2026-09-16 | 1949-12-15 07:41 | 18247.32 | 18247.32 | 100% | 100% | 208 | 208 | 208 |  | 5 | 5 | 0 | 0
PG-T-CON-B-GF-EL-10 | Pipes & Conduits Installation | 3 | 2026-08-15 | 2026-08-17 | 2026-07-22 | 2026-07-23 | 1905-06-05 14:24 | 1983.6 | 1983.6 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PG-T-CON-B-GF-EL-50 | Electrical Light Fixtures Installation | 2 | 2026-09-06 | 2026-09-07 | 2026-08-20 | 2026-09-16 | 1920-02-01 12:29 | 7337.52 | 7337.52 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
PG-T-CON-B-GF-EL-30 | Fire Alarm Devices Installation | 3 | 2026-09-08 | 2026-09-10 | 2026-08-20 | 2026-09-16 | 1983.6 | 1983.6 | 1983.6 | 100% | 100% | 32 | 32 | 32 | No | 1 | 1 | 0 | 0
PG-T-CON-B-GF-EL-40 | Telecom & CCTV Devices Installation | 3 | 2026-09-12 | 2026-09-14 | 2026-08-20 | 2026-09-16 | 4959 | 4959 | 4959 | 100% | 100% | 40 | 40 | 40 | No | 1 | 1 | 0 | 0
PG-T-CON-B-GF-EL-20 | Electrical & ELV Wiring Works | 3 | 2026-09-15 | 2026-09-17 | 2026-08-20 | 2026-09-16 | 1905-06-05 14:24 | 1983.6 | 1983.6 | 100% | 100% | 48 | 48 | 48 | No | 1 | 1 | 0 | 0
PROJECT CLOSOUT |  | 172 | 2026-05-25 | 2026-12-16 | 2026-05-25 |  | 34073.4 | 210119.32 | 1135780.1 | 3% | 18.5% | 384 | 11 | 62 |  | 7 | 1 | 2 | 4
PG-T-PCL-10 | Testing, Commessioning for All Systems(Completed) | 23 | 2026-05-25 | 2026-06-24 | 2026-05-25 | 2026-06-24 | 34073.4 | 34073.4 | 34073.4 | 100% | 100% | 11 | 11 | 11 | No | 1 | 1 | 0 | 0
PG-T-PCL-20 | As-Built Drawings | 15 | 2026-11-22 | 2026-12-09 | 2026-09-23 |  | 0 | 22715.6 | 113578.01 | 0% | 20% | 0 | 0 | 0 | Yes | 1 | 0 | 1 | 0
PG-T-PCL-10_R | Testing, Commessioning for All Systems(Remaining) | 11 | 2026-11-22 | 2026-12-03 | 46240 |  | 0 | 2319-10-20 07:26 | 306660.63 | 0% | 50% | 101 | 0 | 50 | Yes | 1 | 0 | 1 | 0
PG-T-PCL-30 | Snag list Submission | 2 | 2026-12-05 | 2026-12-06 |  |  | 0 | 0 | 227156.02 | 0% | 0% | 136 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-PCL-40 | Snag list Closeout | 7 | 2026-12-07 | 2026-12-14 |  |  | 0 | 0 | 227156.02 | 0% | 0% | 136 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-PCL-50 | Issuing Approvals | 1 | 2026-12-15 | 2026-12-15 |  |  | 0 | 0 | 113578.01 | 0% | 0% | 0 | 0 | 0 | Yes | 1 | 0 | 0 | 1
PG-T-PCL-60 | Handing Over | 1 | 2026-12-16 | 2026-12-16 |  |  | 0 | 0 | 113578.01 | 0% | 0% | 0 | 0 | 0 | Yes | 1 | 0 | 0 | 1

## Weekly Photos
Date | 2026-10-18
Excavation, Bitumen Coat, Concrete Pouring, Base Course Installation, Asphalt Work, Curbstone Installation, Compaction & Levelling

## FIR Summary
Project Name |  | Playground Initiative ( QASSIM , HAIL & TABUK) | [5 empty] | Total FIR Amount
Project ID |  | MLTX-02-003 |  | Project Budget | 35709993 |  |  | 3298582.8807
Date Pariod |  | Start Date | 2025-01-12 | To | Data Date | 22/12/2025
BOQ Item # | BOQ Description | FIR # | Date | FIR Description | Unit Rate | Current Pariod Quantity | Total (SR) | Comments
0
0
| Description | [5 empty] | 3294127.7187 |  | 7.305%
IPA-01
2.1.1 | Excavation | MLTX-02-003-ADV-TS9-1-CVL-FIR-0310-00 | 2026-09-03 | Verification of Excavation Quantities for = 1. Court 1- Football court 2. Court 1- Basketball court 3. Court 1- Padel court 4. Court 1- Interlock 5. Court 1- Stamped concrete 6. Court 2- Football court 7. Court 2- Interlock 8. Court 2- Stamped concrete 9. Parking 10. Tartan 1, 2, 3, 4 11. Tartan 1-4- Stamped 12. Tartan 11, 12 As shown in the approved drawings. | 24 | 2549.66 | 61191.84
2.1.2 | Backfilling with selected fill material free of debris and boulders, in layers. Price also includes testing each layer by a specialized laboratory. The works shall satisfy the project specification and soil report requirements and shall be accepted and approved by the Engineer. | MLTX-02-003-ADV-TS9-1-CVL-FIR-0053-00 | 2026-04-23 | under Shower and locker building | 51 | 1310.95 | 66858.45
2.2.1 | interlock tiles for parking 8cm | MLTX-02-003-ADV-TS9-1-CVL-FIR-0426-00 | 2026-09-26 | Subgrade Layer (300 mm) | 67 | 437.07 | 29283.69
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0427-00 | 2026-09-26 | Base Course Layer(200 mm) | 67 | 437.07 | 29283.69
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0435-00 | 2026-09-27 | Base Course Layer(200 mm) | 67 | 144.1 | 9654.7
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0434-00 | 2026-09-27 | Subgrade Layer (300 mm) | 67 | 144.1 | 9654.7
2.3.1.1 | Interlock tiles grey scale with black marble chips 600*300*60mm zero joint | MLTX-02-003-ADV-TS9-1-CVL-FIR-0444-00 | 2026-09-27 | Sub grade backfilling Quantities under interlock tiles as highlighted in the drawings (location 1 &location 2) | 77 | 474.57 | 36541.89
2.3.1.3 | Tartan floor | MLTX-02-003-ADV-TS9-1-CVL-FIR-0415-00 | 2026-09-26 | (Tartan: 1 +3+11+12) Subbase | 234 | 276.63 | 64731.42
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0416-00 | 2026-09-26 | (Tartan: 2+4) Subbase | 234 | 29.8 | 6973.2
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0418-00 | 2026-09-26 | (Tartan: 2+4+11+12) Concrete Layer | 234 | 296.55 | 69392.7
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0438-00 | 2026-09-27 | (Tartan: 1+2+3+4+9) Subbase | 234 | 162.06 | 37922.04
2.3.2.1 | Kerb type K1A | MLTX-02-003-ADV-TS9-1-CVL-FIR-0190-00 | 2026-09-27 | Qassim Parking Area | 78 | 177.38 | 13835.64
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0375-00 | 2026-09-12 | Cycle Track | 78 | 86.01 | 6708.78
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0306-02 | 2026-08-30 | for walkway as shown in the attached shop drawing. | 78 | 386.16 | 30120.48
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0441-00 | 2026-09-24 | for Walking path (Cycle Track) as shown in the attached drawings | 78 | 184.01 | 14352.78
2.3.2.3 | Kerb type K4 | MLTX-02-003-ADV-TS9-1-CVL-FIR-0178-00 | 2026-07-23 | Curb stones for TARTAN AREA 1,2,3,4 as shown in the attached drawings. | 79 | 211.01 | 16669.79
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0150-00 | 2026-07-23 | Parking Area | 79 | 297 | 23463
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0177-01 | 2026-07-25 | Football Court 2 as per highlight DWG | 79 | 146.09 | 11541.11
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0217-01 | 2026-07-30 | Curb Stones for TARTAN AREA 11, 12 | 79 | 319.64 | 25251.56
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0288-00 | 2026-08-17 | (K4) for Walking path (Cycle Track) as shown in the attached drawings. | 79 | 96.04 | 7587.16
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0374-00 | 2026-09-28 | Cycle Track | 79 | 70.89 | 5600.31
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0307-01 | 2026-08-29 | (K4) for walkway as shown in the attached shop drawing. | 79 | 380.21 | 30036.59
2.3.5.1 | Football playground | MLTX-02-003-ADV-TS9-1-CVL-FIR-0417-00 | 2026-09-22 | Court 1 Backfilling works | 161 | 84.76 | 13646.36
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0420-00 | 2026-09-26 | Court 2 Backfilling works | 161 | 84.76 | 13646.36
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0436-00 | 2026-09-27 | Court 1 Backfilling works | 161 | 84.76 | 13646.36
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0437-00 | 2026-09-27 | Court 2 Backfilling works | 161 | 84.76 | 13646.36
2.3.5.2 | Padel playgound | MLTX-02-003-ADV-TS9-1-CVL-FIR-0425-00 | 2026-09-26 | Padel playgound Backfilling works | 376 | 29.35 | 11035.6
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0440-00 | 2026-09-27 | Padel playgound Backfilling works | 376 | 29.35 | 11035.6
2.3.5.3 | Basketball playground | MLTX-02-003-ADV-TS9-1-CVL-FIR-0422-00 | 2026-09-26 | Basketball playground Backfilling works | 348 | 91.88 | 31974.24
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0423-00 | 2026-09-26 | Basketball playground Concrete Layer (140 mm) | 348 | 214.38 | 74604.24
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0439-00 | 2026-09-27 | Basketball playground Backfilling works | 348 | 91.88 | 31974.24
2.3.9 | air dome | MLTX-02-003-ADV-TS9-1-CVL-FIR-0421-00 | 2026-09-26 | Strip footing and Raft foundation | 6958008 | 0.08 | 556640.64
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0457-00 | 2026-09-27 | Upstand | 6958008 | 0.02 | 139160.16
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0428-00 | 2026-09-27 | Strip footing and Raft foundation | 6958008 | 0.1 | 695800.8
3.1.1 | lean concrete under foundation | MLTX-02-003-ADV-TS9-1-CVL-FIR-0068-02 | 2026-06-16 | under Shower and locker building | 467 | 3.59 | 1676.53
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0303-00 | 2026-08-23 | under GRP Tank | 467 | 0.87 | 406.29
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0091-00 | 2026-06-23 | under Shower and locker building | 467 | 3.64 | 1699.88
100244.13
IPA-02
2.2.1 | interlock tiles for parking 8cm | MLTX-02-003-ADV-TS9-1-CVL-FIR-0185-01 | 2026-10-04 | FIR for installation of Interlock Pavers in the Parking Area, as shown in the attached drawing. | 67 | 874.134 | 58566.978
2.3.1.2 | Stamped concrete floor | MLTX-02-003-ADV-TS9-1-CVL-FIR-0517-00 | 2026-10-07 | FIR for Concrete Pouring for Stamped Concrete (Court 2) as shown in highlighted drawing. | 126 | 324.738 | 40916.988
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0486-00 | 2026-10-04 | stamped concrete in (Tartan 1 & 3) Area | 126 | 218.394 | 27517.644
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0470-00 | 2026-10-03 | FIR For Concrete Pouring for Stamped Concrete at the Location Tartan (5&7) as Shown In the as shown in highlighted drawing. | 126 | 242.478 | 30552.228
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0572-00 | 2026-10-12 | FIR for Concrete Pouring For Stamped Concrete (Tartan 2 & 4) as shown in highlighted drawing. | 126 | 121.806 | 15347.556
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0573-00 | 2026-10-12 | FIR for Concrete Pouring For Stamped Concrete (COURT-2 AREA) as shown in highlighted drawing. | 126 | 324.738 | 40916.988
2.3.1.3 | Tartan floor | MLTX-02-003-ADV-TS9-1-CVL-FIR-0489-00 | 2026-10-11 | FIR for concrete pouring (35 Mpa) for Grade Slab (Tartan 9) as shown in highlighted drawing. | 234 | 144.261 | 33757.074
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0490-00 | 2026-10-11 | Field inspection request for Concrete pouring (c35) Grade Slab at Tartan 1–3, as highlighted in the attached drawing. | 234 | 23.382 | 5471.388
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0539-00 | 2026-10-10 | FIR for Concrete Pouring for Tartan 1 & 3 as shown in highlighted drawing. | 234 | 163.107 | 38167.038
[5 empty] | 234 |  | 0
2.3.2.3 | Kerb type K4 | MLTX-02-003-ADV-TS9-1-CVL-FIR-0474-00 | 2026-10-04 | Curb stones (K4) for Court 2 | 79 | 225.387 | 17805.573
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0308-01 | 2026-10-13 | Curb stones (K4) for Court 2 | 79 | 138.3525 | 10929.8475
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0546-00 | 2026-10-14 | Field inspection request for the installation of curbstone at TARTAN-9 area, as highlighted in the attached shop drawing. | 79 | 79.362 | 6269.598
2.3.5.1 | Football playground | MLTX-02-003-ADV-TS9-1-CVL-FIR-0528-00 | 2026-10-07 | Court 2 Asphalt Base Course (50 mm) | 161 | 169.524 | 27293.364
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0563-00 | 2026-10-14 | Court 1 Asphalt Base Course (50 mm) | 161 | 169.524 | 27293.364
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0564-00 | 2026-10-14 | Asphalt Wearing Course on Football Court 1, | 161 | 169.524 | 27293.364
2.3.9 | air dome | MLTX-02-003-ADV-TS9-1-CVL-FIR-0523-00 | 2026-10-12 | FIR for RCC concrete pouring (35 Mpa) for Air Dome Raft Footing as shown in highlighted drawing. | 6958008 | 0.0369 | 256750.4952
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0591-00 | 2026-10-12 | FIR for pouring of concrete (RCC) for curtain wall area Raft foundation as attached highlighted shop drawings | 6958008 | 0.036 | 250488.288
3.4 | The autoclaved aerated panel for slabs | MLTX-02-003-ADV-TS9-1-CVL-FIR-0508-00 | 2026-10-04 | FIR for Installation of Autoclaved Aerated Panels for Parapet wall, Shower and locker building as shown in the attached shop drawing. | 189 | 27.864 | 5266.296
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0242-01 | 2026-10-12 | FIR for installation of Autoclave Aerated Panels for walls, Lintels, Slab And Parapet Wall for Shower and locker building (Toilet) as shown in the attached shop drawing. | 189 | 201.7044 | 38122.1316
|  | MLTX-02-003-ADV-TS9-1-CVL-FIR-0554-00 | 2026-10-10 | FIR for installation of Autoclaved Aerated Panels for Slab, Shower and locker building as shown in the attached shop drawing. | 189 | 65.0736 | 12298.9104
7.3 | Supply and install liquid applied waterproofing membrane for toilets according to drawings and specifications. | MLTX-02-003-ADV-TS9-1-CVL-FIR-0583-00 | 2026-10-13 | FIR for installation of 2 layers of Waterproofing Membrane in Toilets floor area as highlighted in the drawings | 34 | 33.75 | 1147.5
7.5 | 2 layers of waterproofing membrane 4mm including layer protection board for RC footings and RC walls in contact with soil according to the drawings and specification | MLTX-02-003-ADV-TS9-1-CVL-FIR-0562-00 | 2026-10-11 | FIR for application of Waterproofing Membrane below the septic tank foundation and RCC Walls as highlighted in the drawings | 73 | 44.46 | 3245.58
9.1.1.1 | Anti-slip glazed grey ceramic tiles, 600*600 mm | MLTX-02-003-ADV-TS9-1-CVL-FIR-0445-00 | 2026-09-26 | Ceramic Tiles on Floor – in location The (Shower and locker building) as | 105 | 11.583 | 1216.215
9.1.1.2 | Light grey Ceramic tiles, 300*300 mm | MLTX-02-003-ADV-TS9-1-CVL-FIR-0443-00 | 2026-09-26 | Ceramic Tiles on Floor – in location The (Shower and locker building) | 103 | 43.254 | 4455.162
Total Period Amount | [6 empty] | 3298582.8807

## Quality
QC OBSERVATIONS CHECKLIST
2024-03-26
Project No. |  |  | MLTX-02-003 |  |  | OBS No. |  |  |  | 105.7143 |  |  | Inspection Day: |  | 2026-04-12
Project |  |  | Playgrounds Initiative (Qassim Oasis, Hail and Tabuk Industrial City) | [6 empty] | Contractor: Consultant: |  |  | Advanced Construction & Contracting Company Egis
4 |  | Excellent |  | Quality Management System is being practiced and applies to MODON System | [11 empty] | 90 - 100 |  | QC Overall Score | 91.31% |  |  |  |  | 0% | 100 | 0.22883
3 |  | Good |  | Evidence of compliance with plans and procedures. | [11 empty] | 80 - 89 | [7 empty] | 0 | 89 | 0.20366
2 |  | Average |  | Indication level of compliance with standards but there is room for improvement | [11 empty] | 70 - 79 | [8 empty] | 79 | 0.18078
1 |  | Improve |  | Quality and Control is NOT being managed effectively. Needs Improvement | [11 empty] | ≤ 69 | [8 empty] | 69 | 0.15789
0 |  | N/A |  | Item was not applicable or this item was not reviewed during the inspection. | [11 empty] | Zero | [8 empty] | 100 | 0.22883
No. | Topic |  |  |  |  | E (4) | G (3) | A (2) | I (1) | N/A (0) | No. | Topic |  |  |  | E (4) | G (3) | A (2) | I (1) | N/A (0) |  |  |  |  | 437
[6 empty] | 100% | 89% | 79% | 69% | 100% | [5 empty] | 100% | 89% | 79% | 69% | 100% | 91.31%
1 | Control of Access to Site/Office | [5 empty] | 1 |  |  |  | 30 | QC of Excavation |  |  |  | 0 | 1 |  |  |  | 0.89 | 0.89 | [6 empty] | Item Count | Score | Distributtion
2 | Document Control Administration | [5 empty] | 1 |  |  |  | 31 | QC of Roads/Round about |  |  |  | 0 | 1 |  |  |  | 0.89 | 0.89 | [8 empty] | Overall | Relevant
3 | Project Documents and Progress | [5 empty] | 1 | 0 |  |  | 32 | QC of Interlock & Curbstone |  |  |  | 0 | 1 |  |  | 0 | 0.89 | 0.89 | 4 | 58 | counts |  | 4 | Excellent | 5 | 20 | 8.621% | 12.82%
4 | Contractor's Quality Plan/CM (Updated and Reviewed) | [5 empty] | 1 |  |  |  | 33 | Layers/Backfilling Sampling |  |  |  | 0 | 1 | 0 | 0 | 0 | 0.89 | 0.89 | 3 | 58 | counts |  | 3 | Good | 24 | 72 | 41.38% | 61.54%
5 | MS Log and Paperwork | [5 empty] | 1 | 0 |  |  | 34 | Pump Stations Units |  |  |  | 0 | 1 | 0 |  | 0 | 0.89 | 0.89 | 2 | 58 | counts |  | 2 | Average | 7 | 14 | 12.07% | 17.95% |  | NB: Insert 1, or 0 in the required cell only.
6 | RFI, FIR, & MIR Procedure | [5 empty] | 1 |  |  |  | 35 | Quality of Form Work |  |  |  | 0 | 1 |  |  | 0 | 0.89 | 0.89 | 1 | 58 | counts |  | 1 | Improve | 3 | 3 | 5.172% | 7.692%
7 | RFI, FIR, & MIR Inventory system | [5 empty] | 1 |  |  |  | 36 | Design Change List | [6 empty] | 0 | 1 | 0.89 | 1 | 0 | 58 | counts |  | 0 | N/A | 19 | 0 | 32.76% | -
8 | NCRs Control & Procedure | [5 empty] | 1 |  |  |  | 37 | Quality of Concrete Placing |  |  |  |  | 1 |  | 0 | 0 | 0.89 | 0.89 | [5 empty] | Total | 58 | 109 | 100% | 100%
9 | NCR Log |  |  |  |  | 0 | 1 |  |  |  | 38 | Concrete Surface Finishing |  |  |  | 0 | 1 |  |  | 0 | 0.89 | 0.89
10 | MODON Standard* |  |  |  |  | 0 | 1 |  |  |  | 39 | Pedestals/Columns/Beams Alignment |  |  |  | 0 |  |  |  | 1 | 0.89 | 1 | [6 empty] | Maz Score Available: | 156 | <- Excludes N/A items
11 | Project Risk Plan/Management* |  |  |  |  | 1 |  |  |  |  | 40 | Siporex Lifting & Unloading | [5 empty] | 0 |  | 1 | 1 | 1
12 | Monthly Quality Reports* |  |  |  |  | 0 | 1 | 0 |  |  | 41 | Siporex Quality Pre-installation | [5 empty] | 0 |  | 1 | 0.89 | 1
13 | ITP |  |  |  |  | 0 | 1 | 0 |  |  | 42 | Siporex Finishing Quality |  |  |  | 0 |  |  |  | 1 | 0.89 | 1 | [5 empty] | Total Score |  | Percentage (%)
14 | MODON Weekly Report |  |  |  |  | 0 | 1 | 0 |  |  | 43 | Roads / Parking Markings |  |  |  | 0 | 0 |  |  | 1 | 0.89 | 1 |  | 58 |  |  |  | 109 |  | 69.8718 |  | %
15 | Design Change Official Paperwork* |  |  |  |  | 0 |  | 1 |  | 0 | 44 | QC of Finishing Outdoors |  |  |  | 0 | 0 |  |  | 1 | 0.79 | 1 | [5 empty] | Max Score Available | [6 empty] | 31
16 | Design Change was Applied* |  |  |  |  | 0 |  | 1 |  | 0 | 45 | Quality of Finishing Indoors |  |  |  | 0 |  |  |  | 1 | 0.79 | 1 | [5 empty] | 156 | [6 empty] | 32
17 | Material List |  |  |  |  | 0 | 1 | 0 |  |  | 46 | Stairs Quality |  |  |  | 0 |  |  |  | 1 | 0.89 | 1 | [12 empty] | 33
18 | Pending Material Status |  |  |  |  | 0 | 1 |  |  | 0 | 47 | Tanks Method Statement Work |  |  |  | 0 |  |  |  | 1 | 0.89 | 1 | [12 empty] | 34
19 | Lifting Plan* | [8 empty] | 1 | 48 | Electric Rooms |  |  |  | 0 |  |  |  | 1 | 1 | 1 | [12 empty] | 35
20 | DWG Log | [6 empty] | 1 |  | 0 | 49 | QC of MCC/ATS Plant Units |  |  |  | 0 |  |  |  | 1 | 0.79 | 1 | [12 empty] | 36
21 | Invoice Status |  |  |  |  | 1 | 0 |  |  | 0 | 50 | Qualified Subcontractor |  |  |  | 0 |  |  |  | 1 | 1 | 1 | [12 empty] | 37
22 | Site Handover Letter |  |  |  |  | 1 | 0 |  |  |  | 51 | Scaffold/Ladders/Slope/Bridge Compliance |  |  |  | 0 |  |  |  | 1 | 1 | 1 | [12 empty] | 38
23 | Material Testing Results & Certification |  |  |  |  | 0 | 1 | 0 | 0 |  | 52 | Protection Applied to Completed Work | [6 empty] | 0 | 1 | 0.89 | 1
24 | As Build Drawings Status* | [5 empty] | 0 |  |  | 1 | 53 | Storage Management in/out Control |  |  |  |  | 0 |  | 1 |  | 1 | 0.69
25 | Calibrated Lab Tools & Equipment |  |  |  |  | 1 | 0 |  | 0 |  | 54 | Material Control |  |  |  |  | 0 |  | 0 | 1 | 1 | 1
26 | Storage Inventory System | [5 empty] | 0 |  | 1 |  | 55 | Manholes Storing and Quality |  |  |  |  | 0 |  | 1 | 0 | 0.69 | 0.69
27 | Logistics Plan | [6 empty] | 1 |  |  | 56 | Reinforced Steel Quality |  |  |  |  | 0 |  |  | 1 | 0.79 | 1
28 | Project Progress Planview |  |  |  |  | 1 |  | 0 | 0 |  | 57 | Safety Overview |  |  |  | 0 |  | 1 |  |  | 1 | 0.79
29 | Sufficient Number of QC Inspectors |  |  |  |  | 0 |  | 1 | 0 |  | 58 | Waste Management Control |  |  |  | 0 |  | 1 |  |  | 0.79 | 0.79
0
Score
[8 empty] | *QC % |  |  | 91.31%
Prepared by: |  |  |  | Abdelmutalb Eldukhri | [6 empty] | Issued to PM: |  |  | Abdulaziz M. Al-Musallam
*QC Observations refer only to the practices and documentation observed at time of inspection. The responsibility of the CM and Contractor is to ensure that aspects of Quality are suitably managed. *Scores are a reflection of the general site conditions based upon the findings at the time of the walk through *If Applicable

## Quality-Stat
Quality Reports
Item |  | Issued | Closed | Pending | Avg. Closing (Days) | Pending
[6 empty] | 0-10 Days | 11-20 Days | 21-30 Days | 31-60 Days | > 60 Days
Non Conforomance Report (NCR) |  | 17 | 7 | 10 | 0 | 8 | 2 | 0 | 0 | 0
Site Instruction (SI) |  | 7 | 6 | 1 | 0 | 0 | 0 | 1 | 0 | 0
Material Inspection Report (MIR) |  | 76 | 53 | 23 | 0 | 20 | 3 | 0 | 0 | 0
Field Inspection Report (FIR) |  | 658 | 488 | 170 | 0 | 140 | 15 | 15 | 0 | 0
Shop Drawings
Item |  |  | Total Planned | Total Drawings Submitted |  |  |  |  | Remaining Drawings | Pending | Total Submittals
|  |  |  | A | B | C | D | Approved | with Designer | Submittals With Consultant
Architectural |  |  | 58 | 6 | 33 | 2 | 0 | 39 | 0 | 17 | 58
Civil / Structural |  |  | 84 | 0 | 66 | 0 | 12 | 66 | 0 | 6 | 84
Mechanical |  |  | 42 | 16 | 22 | 2 | 0 | 38 | 0 | 2 | 42
Electrical |  |  | 98 | 4 | 43 | 12 | 22 | 47 | 0 | 17 | 98
Landscape |  |  | 69 | 4 | 59 | 1 | 3 | 63 | 0 | 2 | 69
General |  |  | 42 | 6 | 36 | 0 | 0 | 42 | 0 | 0 | 42
TOTAL |  |  | 259 | 36 | 259 | 17 | 37 | 295 | 0 | 44 | 393
Material Approval
Item |  |  | Total Planned | Total Materials Submitted |  |  |  |  | Remaining to approve | Pending | Total Submittals
|  |  |  | A | B | C | D | Approved | with Designer | Submittals With Consultant
Architectural |  |  | 41 | 4 | 35 | 1 | 0 | 39 |  | 1 | 41
Civil / Structural |  |  | 51 | 1 | 41 | 4 | 0 | 42 |  | 5 | 51
Mechanical |  |  | 19 | 0 | 14 | 1 | 0 | 14 |  | 4 | 19
Electrical |  |  | 28 | 0 | 26 | 2 | 0 | 26 |  | 0 | 28
Landscape |  |  | 2 |  | 0 | 0 |  | 0 |  | 2 | 2
General
TOTAL |  |  | 141 | 5 | 116 | 8 | 0 | 121 | 0 | 12 | 141
Procurement Summary
Item |  |  | Total Materials Planned | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Actual Material on Site | Remaining Materials | Material Delivery Completion (Date)
|  |  |  | A | B | C | D | Processed
Architectural |  |  | 11 | 11 | 7 | 4 | 3
Civil / Structural |  |  | 19 | 19 | 15 | 4 | 3
Mechanical |  |  | 20 | 20 | 8 | 13 | 1
Electrical |  |  | 7 | 7 | 3 | 4 | 1
General
TOTAL |  |  | 57 | 57 | 33 | 25 | 8 | 0 | 0
Consultant Quality Inspections / Observations (Weekly Basis) | [7 empty] | Overall Average | #DIV/0! |  | Average Closing | #DIV/0!
Week Number | Date of Audit | Date Issued | Numbers Of Comments | Quality Score | Date Closed | Closure Duration |  | This Week Score | 90.88% |  | Average Number of Comments Per Audit | #DIV/0!
Week-1
Week-2
Week-3
Week-4
Week-5
Week-6
Week-7
Week-8
Week-9
Week-10
Week-11
Week-12
Week-13
Week-14
Week-15
Week-16
Week-17
Week-18
Week-19
Week-20
Week-21
Week-22
Week-23
Week-24
Week-25
Week-26
Week-27
Week-28
Week-29
Week-30
Week-31
Week-32
Week-33
Week-34
Week-35
Week-36
Week-37
Week-38
Week-39
Week-40
Week-41
Week-42
Week-43
Week-44
Week-45
Week-46
Week-47
Week-48
Week-49
Week-50
Week-51
Week-52
Week-53
Week-54
Week-55
Week-56
Week-57
Week-58
Week-59
Week-60
Week-61
Week-62
Week-63
Week-64
Week-65
Week-66
Week-67
Week-68
Week-69
Week-70
Week-71
Week-72
Week-73
Week-74
Week-75
Formulas:
Remaining Drawings = MAX(J36:[Remaining Drawings, row above])

## HSE
MODON HSE Site Inspection Report
Date |  |  | 2026-10-15 |  |  |  |  | Inspected By: |  |  |  |  | Saud Al Shammari
Project ID. |  |  | MLTX-02-003 |  |  |  |  | Report No. | 28 |  |  |  |  | MODON PM Name |  | Bader K. Alrowaidan
Project Name: |  |  | Central Region Playground Initiative Project (Hail, Qassim & Tabuk) |  |  |  |  | Contractor: |  | Advanced Construction & Contracting Company |  |  |  |  | Safety Performance |  | 3 |  |  | 91.3% | Date: | [5 empty] | 10 to 15
Inspections are a snapshot in time and refer only to the practices and documentation observed at the time of the Inspection. It remains the responsibility of the Consultant and Contractor to ensure that all aspects of Health & Safety are suitably managed.
1 |  | Good Practice |  |  | 2 | Need Improvement | [5 empty] | 3 | Fail (Life Threatening Activity) / Comliance with Plan & Procedures |  | N/A | Activity Not Applicable for this Site Inspection Report
No. | Topic | [5 empty] | Wt. | HSE Compliance |  |  | No. | Topic | [5 empty] | Wt. | HSE Compliance
1 | Access and Egress - (General access to site, segregated from vehicles, / Overhead protection, while entering into the building /Adequate lighting provided when dark or overnight work) | [5 empty] | 5% | 1 |  |  | 14 | Work at Height - (PPE/Fall Protection(Same level, above and below) / Training / Fall restraint / competency /Safe access & egress to and from work at height / Ladders / Openings (floor/shafts/Provision of emergency rescue) | [5 empty] | 5% | 2 |  |  |  |  | 1 | 100 | 1
2 | Traffic Management - (Loading/unloading/sheeting/temp. routes/speed/parking/competence) | [5 empty] | 3% | 1 |  |  | 15 | Scaffolding - (Temp. Scaffolding Work-platform (All types) - qualified scaffolder / Inspection / Tagged / Safe Access/egress / PTW/Falsework & Formwork) | [5 empty] | 4% | 2 |  |  |  |  | 2 | 75 | 2
3 | Site Signage - (Project Notice Board & General Signage) | [5 empty] | 2% | 1 |  |  | 16 | Mobile Elevated Work platform (MEWP) - (PTW/competence requirements/conditions/inspections/tagged/training/Full-body harness) | [5 empty] | 4% | N/A |  |  |  |  | 3 | 0 | 3
4 | PPE Compliance - (Use, storage, stock, handling & checks - Head, Foot, Eye, Hearing) | [5 empty] | 5% | 1 |  |  | 17 | Excavation & Trenches - (PTW/Edge protection/buffer zone/Slope/Benching/Shoring/Geo-tech report/Atmospheric hazards/Acess&egress/Emergency management / MS&RA/H.E) | [5 empty] | 3% | 2 | [6 empty] | N/A
5 | Housekeeping - (Material correctly stored / Rubbish cleaned & removed daily/slips & trips hazards) | [5 empty] | 3% | 2 |  |  | 18 | Confined Space - (PTW/Training/competence/Emergency Management/MS & RA/Safe access/egress) | [5 empty] | 5% | N/A
6 | Storage of Materials - (Transporting, storage, training and use - Combustible / Flammable / Hazardous substances (COSHH) | [6 empty] | 2 |  |  | 19 | Fire Protection - (Flammable/Oxy. LPG /Combustible separated/FE's/Flashback arrestor/Sparks & slags/Smoking area/PTW/Generators/MS & RA/Emergency Management) | [6 empty] | 1 |  |  | Red | Serious injury or death (immediately)
7 | Site Waste Management - (Hazardous waste /Combustible waste / Human waste / Construction waste - asphalt, cable, timber, paving roof sheeting tiles, plastic & bricks) | [6 empty] | 2 |  |  | 20 | Health & Welfare - (Adequate drinking water/shaded - eating & rest area/washing & sanitary facilities/Certified FA/FA Box & Stock/adequate toilets/Ambulance) | [6 empty] | 1 |  |  | Yellow | Minor or near miss (3 days to comply)
8 | Health Surveillance - (Expose to excessive noise/vibration/dust/silica/CO/cement/radiation/extreme weather condition) | [5 empty] | 3% | 1 |  |  | 21 | Environmental Incident Measures - (Spill/ Leakage / Concrete wash / vehicle & eqpts. wash / waste disposal/Sewers and drains/emissions/Emergency Management/Training/site run-off water) | [5 empty] | 5% | 2 |  |  | Green | No issues
9 | Electrical Safety - (Electrical qualified /RCD/GFCI/Industrial Socket/LOTO/Cable-overhung or buried/Cords in good condition/current inspection tag) | [5 empty] | 5% | 1 |  |  | 22 | HSE Communications & Meetings - (Schedule HSE Meetings/Safety Committee meetings/Alerts / Lesson learned/Safety Bulletin contains latest HSE KPI) | [5 empty] | 5% | 1
10 | Tools & Equipment - (Includes, powered, hydraulic & pneumatic/Guards in place/Properly stored/RCD Protection/Earthed/Good condition & tagged) | [5 empty] | 3% | 1 |  |  | 23 | HSE Plan & Associated Procedures - (Approved updated HSE Plan/ CEMP/HAZComm/Procedures/Standards/Project Safety Risk Register) | [5 empty] | 3% | 1 |  |  | 26 points > 4 minors then is it’s a serious issue
11 | Manual Handling - (Lifting/loading/pulling/pushing/twisting/awkward posture/repetitive task/frequent and prolong physical effort/Reasonable practicable use of mechanical aid) | [5 empty] | 3% | 1 |  |  | 24 | Health, Safety & Environment Incident reporting - (Review of HSE Statistics, Reporting of Unsafe Act & Conditions/ Reporting of Near Miss incident/Reporting of FA cases/Record MT cases) | [5 empty] | 3% | 1
12 | Vehicle and mobile equipment / Plant - (dumpers; excavators, cranes, piling rigs, grader, roller, loaders/condition/KSA License/certification) | [5 empty] | 5% | 2 |  |  | 25 | HSE Awareness, Training & Competence - (Policy /Objective & targets/Information, training/Climatic condition awareness/Reponses in emergency situation/ Safety Behavior Observation) | [5 empty] | 4% | 1
13 | Lifting Operations & Rigging - (Lifting Plan/Lifting devices & gears/PTW/Condition/3rd party certification/bank-man/rigger/slingers/man-basket/inspection record/tagged) | [6 empty] | N/A |  |  | 26 | Project Leadership Site Tours - (Provide evidence of proactive safety performance/Deficient discovered discussed/Positive feedback/Workers resolving safety issues) | [6 empty] | 1
Prepared by: |  |  |  | Saud Al Shammari | [6 empty] | Sent to MODON PM: |  |  |  | Bader K. Alrowaidan
Safety Results
1 |  | 15 |  |  |  | 2 |  | 8 |  |  |  |  | 3 | 0
Note on C13: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Safe access / egress for people to their work area 2 - Safe access / egress for construction vehicles 3 - Access properly restricted-site fencing provided and maintained 4 - Access proper and not blocked 5 - Safe access is available for rescue operation 6 - Storage access / exit are clearly marked and unobstructed 8 - Access and egress is in good condition, hand holds, ladder etc. are sound and in place 9 - Ensure unauthorized public access is prevented 11 - Site assembled ladders or make-shift tables for access are forbidden on site. 13 - Use proper bridges, walkways or gangways to access or cross trenches or an excavation area 14 - Surrounding areas are cleared and barricaded and access restricted to all unauthorized trades while crane in operation 15 - To ensure early access to accredited medical / rehabilitation services 16 - Parking vehicles on site access roads causing obstruction 17 - All personnel will be instructed that access to firefighting equipment must remain clear at all times 18 - Access control gates to be locked out of hours 19 - Site access gates to be designed and located to, where possible, avoid clashes with external hazards / activities
Note on T13: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Personal Fall Arrest System; 1 - Is the suitable harness harnesses is provided 2 - Are shock absorbing lanyard with 2 locking snap hooks. 3 - Is anchorage point strong enough and can support 5,000 Ibs. 4 - Do inspection checklist is being implemented before use. 5 - Is the emergency plan for rescue in place Personal Fall Restraint System; 1 - The fall restraint equipment should be set and adjusted so there is no free fall over the edge. 2 - A harness or body belt may be used 3 - The anchorage point must support 4 times the intended load. Positioning System; 1 - Is a suitable harness or body belt provided 2 - Is there a not more than 2' free fall maintained 3 - Is the anchorage point capable of supporting 2 times the intended load or 3.000 Ibs, whichever is greater 4 - Is 100% tie-off (protection from falls at all times, even when moving from point to point) provided while using personal fall protection with two lanyards Fall Protection System; 1 - Suitable edge protection and work platforms are to be provided to prevent a fall occurring 2 - Where the provision of edge protection or adequate platforms cannot be provided safety nets or other soft-landing systems such as inflatable bags are to be used to minimize the consequences of a fall. 3 - If nets are used, they must be installed by a competent rigger and fitted as close under the work surface as possible. 4 - Areas below roof works are to be cordoned off and properly signed to prevent personnel being injured from falling materials 5 - If access onto the roof cannot be avoided, edge protection is to be installed 6 - Floor and wall openings are to be protected using covers of adequate strength to withstand the expected load that will be imposed and securely fixed. 7 - Penetrations in walls such as those provided for lift shafts, door openings, etc. are to be closed with suitable strength material or have fixed protective barriers around the penetration with a sign warning personnel of the danger of falling.
Note on C14: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are arrival and departure of vehicles and delivery accompany by security department? 2 - Are proper loading, unloading and securing loads, being properly controlled? 3 - Is the proper sheeting & coupling in place when transporting and disposing material to and from site? 4 - Is the parking to the designated parking lot and in reverse order? 5 - Is the designated speed limit adhered on workplace? 6 - Provision of ramps, traffic signs, cones, barriers, demarcation posts and tape, flashing lights and any other traffic control devices. 7 - Do visiting drivers are being inducted at the workplace, prior to enter on the workplace? 8 - Are visiting drivers restricted to dangerous areas, e.g. moving to and from they vehicles to washrooms, lavatory & offices etc.? 9 - Do drivers observe site rules and procedures, for delivery, loading and unloading? 10 - Are the areas wide enough for the safe movement of large vehicles (including visiting vehicles)? 11 - Does drivers are competent, hold valid local driving license and competent training? 12 - Ensure the vehicle and trailers have their brakes applied and all stabilizers properly positioned before beginning loading or unloading?
Note on T14: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Base soundness, load adequately spread (base plate jacks, base plate on firm ground). 2 - Line of standard (vertical) and ledger (horizontal) secure and plumb. 3 - Spacing of transoms on platforms, support for Scaff boards, boards are not over protruded and boards are secured. 4 - Staggering of joints vertical and horizontal. 5 - Guardrail / fall protection. (Top rail – Min.1mtr, Mid rail – 470mm from floor and Toe boards – Minimum150mm) 6 - Longitude and bracing on standards and ledgers. 7 - If close to structure, ties must be on lift below to top working platform and every 3m, load bearing couplers used or tie with certified anchor bolts (eye bolts). 8 - Clamps and tubes used are of correct fittings, size and free from defects. 9 - Tubes & fittings free from defects / deformation. 10 - Safe and proper access available to the working platform. 11 - Scaff tags signed, displayed and up to date. 12 - If close to slab edge/opening scaffold tied and secured to structure correctly.
Note on C15: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a Project Notice Board - (showing HSE Statistics / Safety alerts / lesson learned)? 2 - Is there prominent safety boards that are depicting the mandatory PPE on the workplace? 3 - Are other safety required signs are prominently installed on the workplace in relevant to their work-task, as following: > Hazardous Substances - e.g. respiratory protection Sign > Working at Height - e.g. Full body Harness Sign > Working UG - e.g. Full body Harness, SCBA, Ventilation, PTW Signage etc. > Working with Electrical - e.g. Leather Gloves, Goggles, Face shield, Electric shock proof helmet & shoes > Working with Chemicals - Signage = e.g. Impermeable gloves/clothing's, long sleeves, Goggles 4 - General Site Safety Signs: > Prohibition Sign = (e.g., ‘no access for unauthorized persons’). > Warning Signs = (e.g., ‘danger: electricity’) > Mandatory Signs = e.g., ‘eye protection must be worn’) > Emergency Escape or First Aid Sign = e.g., ‘emergency exit/escape route’) > Safety Color Signs = (e.g., yellow means ‘be careful’ or ‘take precautions’) > Illuminated Signs = (e.g., many emergency exit signs) > Acoustic Signals =( e.g., fire alarm) > Fire safety sign > Supplementary Signs = "This way"
Note on T15: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Man-Lift operators are to be competent and trained to operate the specific Man-Lift by examination and hold a current approved certificate / license from an approved and internationally recognized source (TUV, SGS etc. 1 - All Man-Lifts shall be inspected by a 3rd party on an annual basis. 2 - All Man-Lifts shall display a sticker corresponding to the 3rd party inspection certificate. 3 - The manufacturer's instruction manual must be on site for each and every type of Man-Lift in use. 4- A pre-start daily operator inspection of the equipment will be performed and documented on a daily basis as per the manufacturer's instructions. The user is responsible for ensuring this has occurred. 5 - The use of a Man-Lift as, or in lieu of, a Crane is strictly prohibited. Man-Lifts are to be used only for lifting personnel and small tools within the designed Safe Working Load. 6 - The platform is not to be loaded in excess of the designed working load; the safe working load of the platform is to be clearly displayed on both the platform, and body of the equipment. 7 - All persons inside work platforms shall wear a full-body harness attached to the designated anchor point. Personnel must stand on the floor of the working platform; standing on the handrails is strictly prohibited. Harnesses must not be attached to other structures outside of the working platform. 8 - Personnel must stay inside the working platform at all times; the platform must not be used as an access to structures. The use of staging or ladders to extend height is strictly forbidden. 9 - Securing the boom or work platform to any structure is strictly prohibited. The boom or working platform must not be rested upon on any structure, nor is the Man-Lift to be used as a jack/ prop or tie to support other structures. 10 - All Man-Lifts must be equipped with a 5kg (10lb) fire extinguisher. 11 - No man-lifts are to be operated that have had safety devices removed or disabled. Daily operator inspections are to include the testing of these devices (limit switches, alarms and hazard flashing beacons). 12 - Specific Man-Lifts are fitted with outriggers and/or stabilizers which must be used as per manufacturer's instructions. 13 - The work area surrounding the man-lift is to be cordoned off using barricades and signage if the area is used by other workers or vehicles. A full traffic management plan is required for all works involving man-lifts when working on highways. Under no circumstances is any part of a man-lift to extend or swing into a line of traffic.
Note on C16: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Does required mandatory PPE (refer specification BS, EN & ANSI) is provided, as following? > Safety helmet (see below for color scheme) > Safety glasses (shaded for outdoor work and clear inside structures and during non-daylight hours) > Safety boots (safety shoes are prohibited) > Orange hi-visibility vest 2 - Additional PPE shall be provided to a specific task 3 - Do specific PPE is provided according to their job requirement? > To work at height - Full Body harness / Fall arrest Devices / Fall Restraint Devices / V & H Lifeline etc. > To work in the confined space - Full Bodyarness, Tripod with retractable lifeline, SCBA, Masks etc. > 4 - Are the PPE stored appropriately to prevent deformation or distortion? 5 - Has self assessment being carried out for in according to the work requirements? 6 - EYEWEAR (Glasses/Goggles/Face Shields) > Eyewear cleaning supplies available. > Safety glasses in good condition and lenses free of scratches. > Goggles adjustment strap not cracked or frayed, not deformed, or lenses not > Face shields in good condition, including adjustment band, and free of scratches or 7 - HEAD PROTECTION > Hard hat bill and suspension attached as allowed by manufacturer. > is pliable, free of dents, cracks, nicks, or any damage due to impact. > Suspension maintained at 1.25 inches from inside of shell. > Suspension free of cuts or fraying, torn headband, adjustment strap workable. > Electrical hard hat matched to hazard classification. > Dated to determine whether within manufacturer’s allowable 5-year use time period. 8 - HAND PROTECTION > Available in sizes matched to employee. > Gloves free of rips tears, abrasions, or holes. > Matched to manufacturer’s specification for chemicals used onsite. > Electrical gloves matched to hazard and periodically inspected for insulating rating. > Maintained in a clean and sanitary condition, decontaminated or disposed properly. 9 - BODY PROTECTION > Available in sizes matched to employee. > Maintained in a clean and sanitary condition, decontaminated or disposed properly. > Vapor-tight fully encapsulated suits tested at required periodic intervals. > Flame-resistant clothing matched to electrical hazard and arc flash rating. > Welding gear matched to degree of hazard and free of cuts, tears or burn holes. > Flotation gear available for work near or on water and in good condition. 10 - HOT AND COLD BODY PROTECTION > Cooling gear available based on degree of heat stress hazard. > Cooling gear in operable, clean, and sanitary condition. > Cold-weather gear provided based on needs assessment. > Cold-weather gear available in sizes to match employees. > Cold-weather gear is in free of tears, rips, or holes and in maintained in a clean condition. 11 - TRAINING > Initial PPE training completed by employees. > Training conducted when new types or styles of PPE are issued. > PPE selection, use, and maintenance reviewed at daily safety briefings. 12 - Provision of impermeable clothing appropriate for the work being performed? 13 - Wearing of shorts, sleeveless shirts, loose clothing are prohibited across the MODON Projects. 14 - Clothing contaminated with grease, oils, fuels and other hazardous substances is not to be worn.
Note on T16: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a valid Excavation PTW in place? 2 - Are spoils, materials, and equipment set back at least 1.5 meters from the edge of the excavation? 3 - Are walkways and bridges over excavations structurally sound, minimum 0.5 meter in width and equipped with standard guard rails and toe boards? 4 - Are warning systems established and used when mobile equipment is operating near the edge of an excavation? 5 - Are employees prohibited from working on the faces of sloped or benched excavations above other employees? 6 - Are the exact locations of Utilities (piping, electrical, etc.) clearly marked? 7 - Are underground installations protected, supported, or removed when an excavation is open? 8 - Are ladders or other means of access and egress in place as per the PTW requirements? 9 - Are all workers within 7.6 meters of a means of access and egress to a trench? 10 - Are ALL ramps constructed of materials of uniform thickness, cleated together, equipped with no-slip surfaces? 11 - Are employees protected from cave-ins when entering or exiting excavation? 12 - Are precautions taken to protect employees from water accumulation and dewatering is being carried out? 13 - Is surface water or runoff diverted after every rainstorm or other hazard-increasing occurrence? 14 - Is the excavation classified as a confined space? If so, is their a valid confined space PTW and is the atmosphere being tested when there is a reasonable possibility of an oxygen-deficient, oxygen-enriched, combustible, toxic, or other harmful contaminant? 15 - Have materials and/or equipment chosen for shoring been based upon soils analysis, trench depth and expected loads (as per Excavation PTW)? 16 - Are shoring materials and equipment that are used for protective systems inspected and in good condition? 17 - Are damaged shoring materials and equipment immediately removed from service? 18 - Are damaged shoring materials and equipment inspected by a Registered Professional Engineer after repairs are made and before being placed back in service? 19 - Are protective systems installed without exposing employees to hazards of cave-ins, collapses, or threat of being struck by materials or equipment? 20 - Are ALL members of support systems securely fastened together to prevent failure? 21 - Are support systems provided to insure stability of adjacent structures, buildings, roadways, sidewalks, etc.? 22 - Are excavations below the level of the base or footing supported, and approved by a Registered Professional Engineer? 23 - Does back-filling progress with the removal of the support system? 24 - Is a shield system installed to prevent lateral movement? 25 - Are employees prohibited from remaining in a shield system during vertical movement?
Note on C17: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Sites are to be kept clean and tidy and free from slip, trip and fall hazards. 2 - Do all personnel trained in the importance of good housekeeping, managers, supervisors undertake regular monitoring and inspection of the workplace? 3 - Workplace are to be left clean and tidy at the end of each shift and where there is an accumulation of materials throughout the shift, at regular intervals as required to maintain a clean and safe site. 4 - Buildings under construction and nearing completion must ensure that all combustible and flammable materials are removed at the end of each shift. 5 - Nails are to be removed from timber as soon as possible, where this is not practical they are to be flattened and placed in a safe area (barrier and signs) until nails can be removed at a later time. 6 - Materials are to be stored so as they do not pose a risk to personnel stacking, removing or walking by (further guidance is given in the materials storage and handling section). 7 - All spills are to be cleaned up immediately using absorbent material. 8 - Cables/hoses/other trailing leads are to be protected, buried or secured above head height to avoid a slip trip, fall hazard. 9 - Waste is to be placed in designated containers and covered to protect against high winds, pests or risk of fire. Waste containers are to be emptied on a regular basis to prevent a build-up of material. 10 - Loose or light materials that are stored on roofs or open spaces are to be secured to prevent them from inclement weather. Location: 1 - Receptacles located inside buildings shall be kept at least 18 inches away from combustible walls and partitions. 2 - Receptacles for combustible trash that are located outside of buildings shall be placed at least 15 feet from the building or combustible material. Use: 1 - Cigarettes, cigar butts, matches, and similar potential ignition sources should never be placed in a trash receptacle. Proper receptacles for such items should be provided in areas designated for smoking. 2 - Broken glass, empty jars, scrap metal, and similar construction material should never be placed in office trash containers. A roll-off bin or other appropriate container should be used to hold construction debris. Environmental: 1 - Container storage areas shall be kept clean and free of trash. Improper disposal of food waste can attract pests and vermin. Prevention methods that do not involve the use of toxic chemicals is the preferred method of pest control. 2 - Outdoor containers should be kept covered when not in use so as to avoid attracting pests and to prevent the entry of water. Dripping or leaking trash containers may violate local storm water quality discharge regulations. 3 - Promote recycling by contracting with a waste removal company that provides reuse as part of the waste processing or by providing segregated bins for the collection of office paper, aluminum cans, plastic bottles, and toner cartridges. Rinse empty cans and bottles of sugar-based soda so as not to attract ants and other pests. 4 - Proper lighting (indoor) or during Night Shift are provided. Accurately installed. No impairement or poor visibilty is generated. No shadow due to installation of lights are presents.
Note on T17: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Permit is taken for confined space entry and all recommended precautions are in place. 2 - Operatives are trained and fit for the specified job. 3 - Confined space is well ventilated by means of mechanical ventilation. (Exhaust fan, blowers, low velocity air hose etc.). 4 - Rescue system (Tripod with hoisting device, Rescue Harness etc.) in place and sufficient trained persons are available for the rescue operation. 5 - Safe access is available for rescue operation. (Manhole size - Min. 450 mm X 407 mm or 457 mm Dia.) 6 - Atmospheric monitoring conducted and confined space is safe to enter. Percentage of gas concentration will be monitored and recorded every 4 hrs. A. Oxygen percentage. (Permissible limit – 19.5% to 23.5%) B. Flammable gas or vapors.(Permissible limit - <10% of LFL) C. Carbon Monoxide. (Permissible limit - <50ppm) D. Hydrogen sulfide.(Permissible limit - <10ppm) E. Any other toxic gas or vapors. _______________________________ 7 - Minimum two persons shall be assigned to work in the confined space. One person will remain in the entrance at all times to monitor the work 8 - All persons shall wear safety harness, which should be connected to safety line from outside at all times. 9 - All electrical equipment & leads are free from damage and guards in place. 10 - All electrical tools & equipment are connected through ELCB. 11 - Compressed gas cylinders are kept outside the confined space. 12 - supervisor / Foreman will be available at all time to monitor the work and for the rescue operation. 13 - Tool box talk conducted for the entire team and they are well aware of the risks. 14 - Proper communication system is available in between persons inside and standby person. 15 - Trained First aider with first aid kit will be available when working in the confined space. 16 - Confined space entry register is available and shift records will be maintained. -
Note on C18: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Combustible: 1 - Ensure oily rags, combustible material and other flammable substances which may ignite are not accumulated and that they are removed without delay to the designated disposal / storage area. 2 - Combustible materials shall not be stored within 20 feet (6.1 meters) of compressed gas cylinders. 3 - Safety cans used for dispensing combustible liquids shall be kept at a point of use 4 - Storage rooms for combustible liquids must have explosion-proof light fixtures 5 - No flames - hot work or smoking is be permitted in combustible liquid storage areas. Flammable: 1 - Adequate training in the use and storage of flammable liquids is in place. 2 - Storage of Flammable liquids in accordance with NFPA approved flammable storage lockers or in low value structures at least 50 feet from any other structure. 3 - Do not store other combustible materials near flammable storage areas 4 - Bulk drums of flammable liquids must be grounded and bonded to containers during dispensing 5 - Portable containers of gasoline or diesel are not to exceed 5 gallons 6 - Safety cans used for dispensing flammable liquids shall be kept at a point of use 7 - Appropriate fire extinguishers are to be mounted within 75 feet of outside areas containing flammable liquids, and within 10 feet of any inside storage area for such materials. 8 - Storage rooms for flammable liquids must have explosion-proof light fixtures 9 - No flames - hot work or smoking is be permitted in flammable or combustible liquid storage areas. 10 - Flammable liquid transfer areas are to be separated from other operations by distance or by construction having proper fire resistance. 11 - When not in use flammable liquids shall be kept in covered containers. 12 - Flammable materials are considered hazardous and as such, material safety data sheets and appropriate hazard communication training for affected employees is required 13 - Maintain high levels of housekeeping, particularly with relations to flammable materials. 14 - Where flammable materials are handled in the course of work, safe work procedures must be prepared and documented with reference made to the Material Safety Data Sheets (MSDS‘s) for the materials concerned. 15 - All people handling, working with or in control of flammable substances must be properly trained and supervised (documentation to be maintained). 16 - Lead, dust, fumes and vapor constitute a major health hazard to workers. Hazardous Substances COSHH 1 - Under COSHH the risk presented by any hazardous substance assessed using hierarchy of control, stored, transported, created or disposed and usage at the workplace; > Very toxic or toxic: Substances that, in low quantities, cause death or acute or chronic damage to health when inhaled, swallowed or absorbed via the skin > Harmful: Substances that may cause death or acute or chronic damage to health when inhaled, swallowed or absorbed via the skin > Corrosive: Substances that may, on contact with living tissues, destroy them > inhalation into the lungs, when the substance is in the form of a gas, vapor, fume, mist, aerosol or dust > absorption through the skin or eyes by contact with a substance that can penetrate unbroken skin, or is absorbed through unprotected cuts or grazes > injection by contact with contaminated sharp objects or high-pressure equipment, e.g. water jetting > ingestion by swallowing particles of a hazardous substance resulting from hand-to- mouth transfer
Note on T18: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are regular and frequent fire safety inspections carried out? 2 - Have a sufficient number of fire marshals/evacuation officers been appointed? 3 - Are water supplies adequate? 4 - Does the building or site have a written fire procedure? 5 - Is there an effective permit to work system in operation for all hot work and other fire related work? 6 - Do all doors from areas from which a large number of people may have to escape open in the direction of travel? 7 - Do all emergency exit doors (i.e. doors not in normal use) have clear instructions displayed on how to open? 8 - Are all escape routes clear and unobstructed? 9 - Are all fire exit doors correctly signed? 10 - Is all fire fighting equipment immediately visible or correctly signed? 11 - Are all flammable and explosive substances adequately signed to indicate their presence and danger? 12 - Where necessary, is there a sufficient number of emergency lights to adequately illuminate all internal escape routes, exit doors and signs? 13 - Where automatic fire detection is deemed to be necessary is there an adequate number of detectors in the critical areas? 14 - Where the means of raising the alarm is by hand-operated devices, can the operation of one device be heard throughout the entire building or site? 15 - Is there an adequate number of fire extinguishers in the building? 16 - Is there firefighting equipment other than extinguishers in the building? 17 - Are all electrical circuits and fixed electrical installations examined and tested at an acceptable frequency? 18 - Is housekeeping to an acceptable standard? 19 - Have all staff been trained in fire procedures in the last twelve months? 20 - Are all fire drills adequately recorded?
Note on C19: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - General construction waste streams generated including; > Asphalt, cable, timber, paving, roof sheeting, tiles, plastic sheeting and brickwork. > Excess concrete, spoil material from excavations. > General waste, such as putrescible food scraps and packaging from workers. > General (food) waste, construction/concrete waste, hazardous waste, paper/cardboard and waste water/sewage. 2 - Are hazardous waste identified with hazardous Waste label. 3 - Containers are properly labeled in according to their contents. 4 - Container inspections are documented in writing using the Container Inspection Checklist. 5 - Weekly inspections logged into book using the Accumulation Area Inspection Log Sheet. “NO SMOKING OR OPEN FLAME” sign posted. 6 Disposal facilities identified, evaluated using the procedures. 7 - Disposal facility accepted waste and issue approval letter. 8 - Waste transfer/dispose tracked using Waste Tracking Form. 9 - Waste streams, such as asphalt and concrete, to be recycled should be segregated and separately stored. 10 - Spill Release Contingency: 1 - Prior to beginning operations, ensure that on-site spill response capabilities (containment and personal protective equipment) are consistent with task requirements described in job hazard analysis.
Note on T19: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: HHE is required at all locations where chemical hazards exist, such as; storing, transferring and handling facilities, under routine conditions. The HHE scope shall include the physical, chemical, radiological, and biological health hazards. Physical health hazards include elevated noise and vibration exposures, repetitive motion work operations, ionizing and non-ionizing radiation exposures heat and cold stress and biological hazards include infectious disease agents. HHE shall be performed before the site mobilization; 1 - Is the adequate eating or mess area is provided and sufficient for number of workers? 2 - Are sufficient tables and Chair are provide and Kept Clean? 3 - Are FEs, signs, pest control being implemented? 4 - Is washing Area sufficient and Kept Clean? 5- Cooking Area Kept Clean? 6 - L.P.G. Cylinder stored outside, secured & upright 7 - Sufficient drinking water provided. Filters changed (as per manufacturer recommendation)? 8 - Sufficient toilets, washbasins, cleaned/disinfectant provided? 9 - Provision of First Aider 10 - Provision of Nurse 11 - Provision of First Aid Kit 12 - Provision of site clinic with required first aid equipment and items. 13 - Provision of shaded area on the workplace 14 - Provision of Ambulance or an equal arrangement in place" 15 - Smoking area is Prohibited other than designated smoking areas, clear of flammable and combustible materials? 16 - All toilets, washing, rest and eating facilities to be kept clean, hygienic and be well maintained at all times? 17 - Waste Management - Covered bins, emptied daily, close proximity, color coded etc.? 18 - Are the monitoring, including integrated air sampling, noise dosimetry and other exposure assessments, being carried out? 19 - Are the Physical, chemical, and biological stresses, being identified, results are taken with action level to prevent sickness, impaired health, significant discomfort, or inefficiency in workers? 20 - Are WEL, LEL, OEL PEL & TLV linked to control workers airborne exposure to a chemical in a concentration above which is likely to cause death or immediate or delayed permanent adverse health effects or prevent escape from such an environment, if bening implemented?
Note on C20: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Is the hierarchy of Control is beng carried out on the following and recorded; 1 - Exposure to Chemical; e.g. - Dust, Gas, Mist, Vapor 2 - Exposure to Radiation; e.g. - Pipe radiography etc. 3 - Exposure to Biological Hazard; e.g. - Bloodborne pathogens / Legionella / Leptospirosis 4 - Exposure to noise; e.g. Loss of hearing / Physical damage to hearing mechanism 5 - Heat and cold stress work; e.g. - Heat-stroke, Heat stress / Frostbite / 6 - Repetitive Motion Work; e.g. - Musculoskeletal disorder, awkward position etc. 7 - Is the risk assessment carried out on the hazardous material and covering the following; > Allowable exposure limits, > Exposure monitoring requirements, > Methods of compliance for potential over exposure conditions, > Medical surveillance program, > Hazard communication, employee training requirements, 8- Is the IH Surveillance Plan should being implemented and have rocored on the following; > Which exposure groups require IH monitoring and medical surveillance > Specific substances or agents to be monitored, > The OELs to be used to evaluate results > The statistical basis to continue or cease monitoring > Specific medical testing/protocol to be implemented 9 - Do we've program on identifies work conditions such as the following, the exposure must first be mitigated or work shall not be performed. > Oxygen concentrations less than 19.5% or greater than 23.5%, or > Atmospheres greater than 1% of the Lower Explosive Limit, or > Atmospheres that are >50% of Immediately Dangerous to Life or Health (IDLH) concentrations, or > Work with sensitizers or known human carcinogens, mutagens, or teratogens without process isolation or fully encapsulating personal protection, or > Work with highly infectious biological agents without process isolation
Note on T20: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are all dispensing areas diked or properly graded to control drainage of spilled fuel? 2 - are all workers and operatives are trained to use spill response kit? 3 - Is the procedure in place for collecting and/or containing, and disposing of spilled materials? 4 - All tanks & vessels areas are diked to contain accidental spills?. 5 - Do measures taken to prevent an accidental contaminated runoff from construction , operation, maintenance, plant and storage areas? 6 - Do measures taken to control on deposits of oils, greases and fuels, from site plant and vehicle operations, mechanical failures, spillages and discharges to ground or drains and the dispersion of unattended spills by plant / vehicle movements?. 7 - Do measures taken to control on fuels, oils and other hazardous chemicals spilled on site during re-fueling, storage or transport operations?. 8 - Do we have an Emergency Response Procedure will be followed in the event of environmental emergency such as an oil or chemical spill? 9 - Is there a procedure for concrete wash, clean and dispose to prevent ground contamination, such as; Concrete wash pits with leak proof sedimentation tanks will be provided for washing concrete mixer trucks. The design and location of such wash pits shall be agreed with the Project Manager prior to its construction on site. Concrete dumping or spillages of any kind shall not be allowed in any other location on site? 10 - Is there a procedure to used in the situation of a major spills that will have an impact on the surrounding environment will be promptly reported to the Fire Brigade? 11 - Are there a procedure of disposing off any damage/leakage drums or containers shall be removed in accordance with the local requirements? 12 - Are there a procedure of dealing with spilled contaminated soils, resulted and remediated, accordingly? 13 - Are all personnel trained in the use of spill procedure and response and the adequate spill kits are available on site?
Note on C21: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - All electrical extension cords are equipped with nonconductive plugs 2 - Cords must not be spliced or draped over nails, metal objects 3 - The use of extension cords by means of multiple outlet plugs from single outlets is prohibited 4 - All electrical service removals, alterations and equipment installations are performed by an authorized electrician 5 - Faulty electrical installation 6 - Electrical supply disruption 7 - Exposed cables 8 - Trip / fall hazards from installed cables 9 - Fire hazard Electrical overload 10 - electrocution 11 - Electrical (short circuit) - Contact with exposed conductors or a device that is incorrectly or inadvertently grounded, such as when a metal ladder comes into contact with power lines 12 - Electrical - (static discharge) 13 - Electrical Fire - Use of electrical power that results in electrical overheating or arcing to the point of combustion or ignition of flammables, or electrical component damage 14 - Improper grounding 15 - Damaged insulation 16 - Exposed electrical parts 17 - Overloaded circuits 18 - Inadequate wiring 19 - Wet conditions 20 - Overhead power lines 21 - Damaged tools and equipment
Note on T21: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a meaningful and an effective consultation and communication on health and safety matters being implemented through out the project? 2 - Is the Consultation and communication on health and safety matters in place through the following mechanisms: > Project specific induction - (prior to commencement of contracted work) > Work activity Induction (in SWMS or equivalent) - (prior to commencement any construction work) > Toolbox Meetings - (Monthly intervals or generally when there is the introduction of a new process (SWMS) or when discussing OHS issues/topics). > Subcontractor Meetings - (weekly) > Project team meetings - (weekly) > HSE Committee Meeting - (as agreed with the HSE Committee) > OHS Report - (monthly) > Project Notice Board and general signage - (as required) 3 - Is there a method of communication is to be established in the work procedures to allow constant monitoring of those persons working in the confined space? 4 - Is there a material safety data sheets and appropriate hazard communication training for affected employees is in place? 5 - Are all environmental aspects and impacts been communicated to employees? 6 - Dose the notice
Note on C22: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1- Check that all the workers are using safe hand tools/power tools and instruct them to operate and maintain the same in safe manner 2 - Ensure power tools and hand tools are checked prior to issue 3 - Damaged tools and equipment 4 - Electrical tools or electrical equipment are not to be issued for use until inspected. 5 - Electrical tools or electrical equipment are not to be issued for use until inspected. 6 - "Defective" electrical tools and equipment are to be tagged and removed from service until repaired and inspected 7 - The frequency for inspection of construction electrical tools and electrical equipment shall be monthly and inspection indicated by attached color-coded tape or color- coded tie wraps and a color coded inspection tag with Contractor‘s name, the supervisor, the inspection date, equipment number and signature of competent inspector displayed on the tag. 8 - Checking the cords for worn or cracked insulation. 9 - Checking the cords entry to plug and tool housing for frayed or worn insulation and strain relief. 10 - Checking the plug prongs for damage. 11 - Checking the plug for exposed connectors 12 - Checking the equipment housing for damage. 13 - Checking trigger locks to ensure they have been removed 14 - Checking the leads for signs of wear, poor connections at probes, etc. 15 - Checking the housing and the readout window for cracks, loose screws, etc. 16 - Check all Ground Fault Circuit Interrupters (GFCI) during the monthly inspections. 17 - Machines are free from any defects / damage. 18 - Pressure switch and safety guards in place where applicable. 19 - Leads are fitted with correct plugs & sockets and free from damages. 20 - Leads wires are free from joints, cuts and other defects. 21 - Leads are suitably rated for the electric current. 22 - Machines / Tools are equipped with properly functioning dead man switch. 23 - Tools issue and maintenance record is properly maintained. 24 - Tools are correctly stored. 25 - Discarded Tools / cords are marked and stored separately.
Note on T22: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is the Project HSE Plan presents actions, responsibilities, protocol, conformance, verification and containment activities to be undertaken by project staff and sub-contractors at all times during the construction phase of the project. 2 - Is the implementation of the HSE plan is being monitored, evaluated for accuracy and any changes made communicated to all relevant personnel. 3 - Is the HSE Plan, CEMP, Security Plan, HAZcomm., standards & procedures are updated, signed, approved and distributed, acknowledged to the construction team's responsible individuals? 4 -Is the project overall safety risk register developed, approved and being implemented?
Note on C23: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Immediate Postural and Load Factor; 1- Is the body position stable? 2 - Is the trunk of the body straight (not twisted)? 3 - Is the operation carried out by one person? 4 - Is the load kept close to the body? 5 - Can the handler avoid stretching upwards? 6 - Can the handler avoid a prolonged period in one posture? 7 - Can the handler perform the task without overreaching? 8 - Are both hands used for grasping? 9 - Are the hands less than a shoulder width apart? 10 - Is the load positioned centrally in front of the body? 11 - Is the load reasonably symmetrical? 12 - Is the load stable and easy to grasp? 13 - Can handlers move and position themselves freely? Environmental Risk Factor; 1 - Too hot? 2 - Too cold? 3 - Too bright? 4 - Too dark? 5 - Too noisy to allow effective communication? 6 - Too wet? 7 - Slippery underfoot? 8 - Does any personal protective equipment interfere with the task? Carrying; 1 - Is the load carried at knuckle height? 2 - Is the load carried at arm's length from the body? 3 - Is the load carried for more than 10 meters? Seated Work; 1 - Is the load lifted from below thigh height? 2 - Is the load lifted to above shoulder height? 3 - Is the load lifted at arm's length from the body? 4 - Does the handler have to twist significantly to the side? 5 - Is the load heavier than 5kg? Pushing and Pulling; 1 - Does the pushing and pulling take place below knuckle height? 2 - Does the pushing and pulling take place above shoulder height? 3 - Is the initial or maximum force required to push or pull the load more than 25kg? 4 - Is the continuous force required to keep the load in motion more than 10kg?
Note on T23: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a system of proper HSE reporting in place, such as; all work-related incidents including near misses, injuries, illnesses, property damage, environmental incidents, security events and motor vehicle incidents, using proper protocol followed? 2 - Is the HSE incidents, accident, near misses, unsafe acts/conditions and dangerous occurrences are being reporting in timely manner and in the approved company format? 3 - Are the workers informed, trained in reporting all near misses, unsafe acts/conditions to the appropriate authority or line of manager? 4 - Is the Weekly / Monthly HSE Statistics data, including (leading & lagging) indicators, reviewed by the senior management?
Note on C24: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: CHECKS; 1 - Plant guarding is in place and in good condition to prevent injury from parts disintegrating or failing 2 - Access and egress is in good condition, hand holds, ladder etc. are sound and in place 3 - Operator's seat and controls are in good condition and all safety devices (limiters and indicators) are labelled and fully operational. 4 - Operator's manual / instructions supplied by the manufacturer of the plant are available in the plant. 5 - Hazards with the use of the plant are identified, i.e. Safe working limits on batters, operator safety instructions etc., are displayed clearly in the cabin of the plant for operator reference. I.E. PLANT SPECIFIC RISK ASSESSMENT. 6 - Hazard controls, i.e. seat belts must be worn and hearing protection must be worn, caution/danger signs (counter weight slewing area, excavators and cranes) etc. are displayed in the cabin or on the plant in a position relevant to the hazard. 7 - Operator cabin/work platform access is clean and free of debris, loose tools, equipment, grease oil and is in an orderly condition. 8 - Plant is clean and free from oil leaks and oil build up. 9 - Plant Pre Start inspection is complete and a record of the inspection will be provided at commencement on the site. 10 - Certification of operator / proof of competency. 11 - Operational Noise Level - Statement of conforming emission level. 12 - Plant has no areas of excessive wear or damage. Mobile plant required to have; 1 - Plant is fitted with a Roll Over Protection Structure (R.O.P.S.) and operator restraint. 2 - Plant is fitted with a front horn and reversing beeper. 3 - Plant is fitted with a rotating or flashing amber beacon. Plant used to lift Material and equipment; Backhoes, excavators, cranes and loaders used as crane from designed lifting points. The Safe Working Load of the plant item is displayed on the plant as: EITHER; A Crane Chart supplied by the manufacturer specific to the plant item in the cabin of the plant for operator reference OR; The Safe Working Load of the equipment on the boom of the loader bucket and of the dipper arm of excavators - a combination of both is required for backhoes e.g. SWL 1.2ton. Personal Lifting Equipment - (Cherry Pickers, boom lift and elevated platform) 1 - Safety Working Load is displayed on work bucket / platform. 2 - Fully body harnesses and lanyards are to be provided for personnel using the equipment. 3 - Safety Instruction for the operation of the equipment is clearly displayed in the work bucket / platform. 4 - The supplier have provided training for personnel using the platform in the safe use of the equipment
Note on T24: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Do all personnel have the correct information, instruction and training according to their role and responsibilities? 2 - Is the contractor promoting awareness of company standards and regulations among their employees on a regular basis, or when it is necessary? 3 - Do all personnel have completed basic relevant awareness training, such as; Fire Awareness Training, Heat Stress awareness Training, Safety Signs and Color Code awareness Training, Environmental Awareness Training, Using Fire Extinguisher Awareness Training, Emergency reporting Awareness Training, Unsafe Act/Conditions reporting awareness training, Evacuation Procedure Awareness Training?
Note on C25: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Crane Inspected 2 - Operator certified 3 - Lift Plan approved 4 - PTW obtained 5 - lifting equipment is suitable for the use it is being put to, marked with safe working load, properly maintained and inspected, and receives a periodic thorough examination. 6 - Are all members of the lifting operations team including the Appointed Person, Crane Drivers and Slingers / Signalers / Banksmen will be competent and have such practical and theoretical knowledge and experience as is necessary to carry out their duties. 7 - Bank man is available and certified 8 - The crane operator have a practical and theoretical knowledge of lifting operations 9 - Lifting operations will be undertaken by a minimum of three competent people the crane operator, slinger / signaler (slinger and signaler can be one person) / banks man / flagman (banks man and flagmen can be one person) and Supervisor 10 - Certification of Lifting Equipment / Lifting Gear / Lifting Devices 11 - Lifting plan prepared/approved/communicated 12 - Lifting gear (Chain sling, shackle, webbing sling, lifting clamps etc.) / devices (Chain block, Winch, Monorail etc.) are checked, inspected & tagged - ( size, length, dia, width, SWL,Condition & defects. 13 - All lifting equipment / gears have valid test certificates and are in good condition.
Note on T25: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there process of SBO for leadership to identify and reinforce safe work practices/behaviors? 2 - Is there process of SBO for leadership to identify and improve on at-risk practices? 3 - Is there process of SBO for leadership to identify and improve on practices, conditions, controls, and compliance that eliminate or reduce hazards? 4 - Is there a process of SBO for leadership to make positive, corrective, cooperative, collaborative feedback/recommendations? 5 - Is there a training program for BBST, that how to identify critical safety behavior and how to provide feedback and the number of personnel trained. 6 - Is there a program for the leadership to carry out SBO once a month or twice (depends project scope of work), and record available?

## HSE-Stat
Safety Statistics
[13 empty] | Working Days: | 148
Category | Item |  | This Week | This Month | Year to Date | Cumulative | [6 empty] | Working Hours /Day: | 10
Category | Total Hours Worked |  | 8160 | 15240 | 97870 | 97870
| Safe Hours Worked |  | 8160 | 15240 | 97870 | 97870
Reactive | LTI |  | 0 | 0 | 0 | 0
| MTC (Healed w/o Disability) |  | 0 | 0 | 0 | 0
| MTC (Healed w/ Disability) |  | 0 | 0 | 0 | 0
| Near Miss |  | 0 | 0 | 0 | 0
| First Aid Cases |  | 0 | 0 | 0 | 0
| Fatality |  | 0 | 0 | 0 | 0
| Fire Incident Cases |  | 0 | 0 | 0 | 0
| Vehicle Incident |  | 0 | 0 | 0 | 0
| Property Damages |  | 0 | 0 | 0 | 0
Proactive | Induction Training |  | 40 | 63 | 212 | 212
| No.of Internal Training |  | 0 | 1 | 1 | 1
| No.of Internal Audit |  | 0 | 0 | 0 | 0
| No. of Toolbox Talks |  | 46 | 87 | 530 | 530
| Safety Awards/Incentives |  | 0 | 0 | 0 | 0
[7 empty] | Category | Item | This Week | This Month | Year to Date | Cumulative
Consultant Safety Inspection (Weekly Basis) | [6 empty] | Overall Average | 90.57%
Week Number | Date of Audit | Date Issued | Numbers Of Comments | Overall Score | Date Closed | Closure Duration | This Week Score | 91.3%
Week-1 |  |  |  | 90%
Week-2 |  |  |  | 92%
Week-3 |  |  |  | 87%
Week-4 |  |  |  | 90%
Week-5 |  |  |  | 82%
Week-6 |  |  |  | 86%
Week-7 |  |  |  | 92%
Week-8 |  |  |  | 89%
Week-9 |  |  |  | 90%
Week-10 |  |  |  | 89%
Week-11 |  |  |  | 90%
Week-12 |  |  |  | 93%
Week-13 |  |  |  | 94%
Week-14 |  |  |  | 88%
Week-15 |  |  |  | 94%
Week-16 |  |  |  | 89%
Week-17 |  |  |  | 90%
Week-18 |  |  |  | 93%
Week-19 |  |  |  | 93%
Week-20 |  |  |  | 92%
Week-21 |  |  |  | 90%
Week-22 |  |  |  | 92%
Week-23 |  |  |  | 93%
Week-24 |  |  |  | 89%
Week-25 |  |  |  | 93%
Week-26 |  |  |  | 93%
Week-27 |  |  |  | 92%
Week-28 |  |  |  | 91%
Week-29
Week-30
Week-31
Week-32
Week-33
Week-34
Week-35
Week-36
Week-37
Week-38
Week-39
Week-40
Week-41
Week-42
Week-43
Week-44
Week-45
Week-46
Week-47
Week-48
Week-49
Week-50
Week-51
Week-52
Week-53
Week-54
Week-55
Week-56
Week-57
Week-58
Week-59
Week-60
Week-61
Week-62
Week-63
Week-64
Week-65
Week-66
Week-67
Week-68
Week-69
Week-70
Week-71
Week-72
Week-73
Week-74
Week-75

## Major Quantities (hidden)
BOQ Number | Description of Item | Total Quantity | Unit of Measurement | Plan To Date | Actual To Date | Remaining Total | Variance | Variance % | Notices |  | Perf. %
2.1.1 | Excavation | 29400 | m3 | 29400 | 29400 | 0 | 0 | 0% |  | 30.56% | 100%
2.1.2 | Backfilling with selected fill material | 29400 | m3 | 29400 | 29400 | 0 | 0 | 0% |  | 8984.64 | 100%
2.2.1 | Interlock Tiles for parking | 7140 | m² | 5901.21 | 6640.2 | 499.8 | 738.99 | 10.35% |  |  | 93%
2.3.1.2 | Stamped Concrete Floor | 7800 | m² | 7033.26 | 6630 | 1170 | -403.26 | -5.17% |  |  | 85%
2.3.1.3 | Tartan Floor | 10950 | m² | 9920.7 | 8000 | 2950 | -1920.7 | -17.54% |  |  | 73.06%
2.3.1.4 | Compacted Natural Ground Soil | 33300 | m² | 33300 | 33300 | 0 | 0 | 0% |  |  | 100%
2.3.2.3 | Kerb type K4 | 27100 | L.m | 27100 | 27100 | 0 | 0 | 0% |  |  | 100%
2.3.4.2.1 | Lawn | 19100 | m² | 12539.15 | 0 | 19100 | -12539.15 | -65.65% |  |  | 0%
2.3.5.1 | Football Playground | 7350 | m² | 7350 | 4400 | 2950 | -2950 | -40.14% |  |  | 59.86%
15.5.1.5 | Pipe line O.D 25mm PN 10, in depth 0 to 1.5m | 11100 | m | 10545 | 1811.52 | 9288.48 | -8733.48 | -78.68% |  |  | 16.32%
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!

## Risk Register
Department: | [8 empty] | Status Date:
Program | [8 empty] | 2026-04-12
Project: |  |  | Playground Initiative (Qassim, Hail, Tabuk)
Project No.: |  |  | P030
Project Location: |  |  | Qassim & Hail & Tabuk
[16 empty] | Before Treatment | [10 empty] | Post Treatment
Risk Data | [5 empty] | Category |  |  | Risk Description |  |  | Risk Control Dates |  | Risk Manageability | Risk Proximity | Most Likely |  |  | Risk Owner | Risk Response & Treatment Action |  |  |  | Treatment Control Dates |  |  | Most Likely |  |  | Treatment Status
Risk ID | Region | Section / Group | City | Project ID | Risk Status | T/O/I | Internal/External | Category | Cause / Source | Risk | Consequence / Effect | Identified | Closed |  |  | Liklihood | Impact | Risk Score |  | Risk Response Strategy | Treatment Action | Treatment Acton Description | Treatment Action Owner | Start | Due | Closed | Liklihood | Impact | Risk Score
| Central | Central | Tabuk | MLTX-02-003 | Open | Issue | Issue | Design, Engineering | Delay in obtaining borehole (soil investigation) test results from the laboratory, which requires 7–10 days to issue the final report. | Potential delay in starting excavation activities due to the unavailability of approved soil data, which may impact the overall project schedule. | Excavation works at Tabuk site are on hold until receiving and reviewing the soil test results, leading to a delay in site progress. | 2026-04-08 |  | Moderate | Overdue | Medium | Low | M6 | Contractor | Mitigate | Expedite soil test results and adjust work sequence | Follow up continuously with the laboratory to expedite the issuance of borehole test results. | Site Engineer | 2026-04-09 | 2026-04-19 | 2026-05-02 | Medium | Medium | M9 | Close
NOTES:
Risk Status: 1.Open, 2.Closed, or 3.Realized
T/O/I: 1.Threat, 2.Opportunity, or 3.Issue
Category (select 1):
1. Political
2. Legal, Regulatory, Compliance
3. Funding, Finance, Budget
4. Management, Governance, Policies, KPI, Performance
5. Human Resources | [21 empty] | `
6. Stakeholders, Authorities, Approvals, Permits
7. Requirements, Specifications, Scope, Procurement, Contract
8. Process, Tools, Technique, Technology
9. Design, Engineering
10. Construction, Execution
11. Testing, Commissioning, Handover
12. Operation, Maintenance
Risk Description (add all 3):
1. Source/Cause
2. Event = Threat, Opportunity, or Issue
3. Consequence/Effect
Risk Response Strategy for Threats: 1.Terminate, 2.Tolerate, 3.Transfer, or 4.Treat
Risk Response Strategy for Opportunities: 1.Ignore, 2.Share, or 3.Enhance/Exploit
Treatment Action: 1.Mitigate, 2.Control, or 3.Fall Back
Treatment Status: 1.Unapproved, 2.Active, or 3.Closed
Risk Level/Score: Likelihood x Highest Impact (Safety, Cost, Schedule, Environment, Quality, or Reputation. See Risk Scoring Matrix tab)

## CCO
CONTRACT CHANGE ORDER (CCO)
CCO No. | Date Added | Description of Change | Status | SR | Sch Impact (Months) | Date Approved | Duration (days)

## Invoice Log
Weekly Progress Report - Invoice Log | [32 empty] | Y
Project Value | [8 empty] | Payment Status | [7 empty] | Invoices Summary | [9 empty] | Average Invoices durations | [5 empty] | N
Original Contract Value |  |  | 35709993 |  | O&M Value |  | 0 | EAC | Advance Payment % |  | 0% |  | Advance Payment (SAR) |  | 0 |  | No of Submitted Invoices |  | 0 |  | Submitted Invoices (SAR) |  | 2317493.31 |  | Submiited Invoice Peroid | 29/09/2026 | CM / PgM Average Approval duration |  | 0 | Average Invoice Value | 2317493.31
Revised Contract Value |  | 21100000 | 35709993 | EAC | Revised O&M Value |  | 0 | #REF! | Retention % |  | 0% |  | Retention (SAR) |  | 0 |  | No of Approved Invoices (CM) |  | 1 |  | Approved Invoices (CM) (SAR) |  | 2317493.31 |  |  |  | MODON PM & Accounts Average Approval duration |  | #DIV/0!
Estimate At Completion Value |  | 20900000 | 35709993 | #REF! | Submitted Invoices (Gross Value) |  | 2317493.31 |  | Penalties and deduction % |  | 0.05321% |  | AP Recovery (SAR) |  | -231749.331 |  | No of Approved Invoices (PM) |  | 0 |  | Approved Invoices (PM) (SAR) |  | 0 |  | Invoice Submitted Compared to Contract Value | 6.49% | Payments Average Duration |  | #DIV/0!
Potential Changes |  | 200000 | 0 |  | Total Deduction |  | -250749.331 |  | Penalties and deduction (SAR) |  | -19000 |  | Retention Cumulative (SAR) |  | 0 |  | No of Paid Invoices |  | 0 |  | Paid Invoices (SAR) |  | 2379605.58 |  |  |  | Invoices Average total Duration
Invoice Reference |  |  |  | Invoice Value |  |  |  |  | Period Covered |  | CM / PgM Approval Timeline |  |  |  | Modon PM & Accounts Approval | [6 empty] | Payment Status |  |  |  |  | Total Invoice Duration | Remarks
# | Invoice No. | Doc Control reference | Submittal Rev. # | Gross Value | AP Recovery | Retention | Deduction / Penalties | Amount (net) + VAT 15% | Start Date | End Date | Date to CM / PgM | CM / PgM Approval (Yes/No) | CM / PgM Reply Date | Days Elapsed | Date to PM | PM Approval (Yes/No) | PM Reply Date | Date to Accounts | Accounts Approval (Yes/No) | Accounts Approval Date | Days Elapsed | Date Paid | Amount Paid | Paid % | Payment Period (d) | Amount Pending
1 | IPC-01 | MLTX-02-003-ADV-TS9-1PRM-INV-0175-00 | 0 | 2317493.31 | -231749.331 | 0 | -19000 | 2379605.58 | 17/02/2026 | 29/09/2026 | 29/09/2026 | Y | 29/09/2026 | 0 | [8 empty] | 2379605.58 | 100% |  | 0 |  |  |  | #VALUE!
2
3
4
5
6
7
8
9 | [29 empty] | 14/09/2025 | 30/11/2025
10 | [29 empty] | 2025-01-12 | 22/12/2025
11
12
13 | [29 empty] | 2025-09-14 | 2025-11-30 | 77
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
|  |  | TOTAL | 2317493.31 | -231749.331 | 0 | -19000 | 2379605.58 | [17 empty] | 0
Note on I3: Without O&M Cost
Note on B4: Without O&M Cost
Note on E4: Without O&M Cost

## Milestones
Milestones for Playgrounds Initiative-Qaseem, Hail & Tabuk Project
Item No. | Milestones | Original (Baseline) | Latest | Forecast |  | Days Change
| Contract Duration Current Contract Weeks : 0 of 0 | 43.1429 | 43 | 50.5714 |  | -53
1 | Award Date | 2026-01-06 | 2026-01-06 | 2026-01-06 | A | 0
2 | Contract Sign Date | 2026-02-17 | 2026-02-17 | 2026-02-17 | A | 0
3 | Site Handover Date | 2026-02-17 | 2026-02-17 | 2026-02-17 | A | 0
4 | Complete Mobilization | 2026-03-18 | 2026-03-18 | 2026-04-14 | A | 0
5 | Complete Engineering | 2026-08-16 | 2026-08-16 | 2026-10-19 | F | -64
6 | Complete Procurement | 2026-08-27 | 2026-08-27 | 2026-10-25 | F | -59
7 | Complete Construction | 2026-12-14 | 2026-12-14 | 2027-01-23 | F | -40
8 | Complete all Works including Testing & Commissioning, Cleanup, Closeout Documentation and Ready for Initial Handover | 2026-12-16 | 2026-12-16 | 2027-02-02 | F | -48
9 | Complete Demobilization | 2026-12-16 | 2026-12-16 | 2027-02-06 | F | -52
10 | Project Handover | 2026-12-16 | 2026-12-16 | 2027-02-07 | F | -53
Formulas:
Latest = [Original (Baseline)]
Days Change = IF([Forecast]<TODAY(),0,[Latest]-[Forecast])

## Procurement
|  | MLTX-05-047 |  | Procurement Log- Long Lead Items | [16 empty] | 2025-09-22
Sr. NO. | ACT # in P6 | Item Description | (Long\Short) Lead Items | BOQ. No. | Unit | Quantity | Proc. Qty | Required P.O Date | Date of Pur. Order Issued | Purchase Order No. | Supplier | Supplier Phone | Method of Shipping | Required on Job | E.D.A. to Site | A.D.A. to Site | Lead Time | Approval Status | The Impact (BOQ Cost) | Completion Rate | Remarks
1 |  | Air Dome | Long Lead Items |  | Nos. | 2 | 2 |  | Under Process | Approved | Global Sport Gate |  | Local and extrnal Transportation to site |  |  |  | 150 | under review
2 |  | Autoclaved aerated panel | Long Lead Items | 3.4 | m² | 110 | 110 |  | Under Process | Approved | Espac |  | Local Transportation to site |  |  |  | 60 | Approved
3 |  | Landscaping | Long Lead Items |  | Nos. |  |  |  | Under Process | Under Process | Arab Farm |  | Local Transportation to site |  |  |  | 60
4 |  | Sport Flooring | Long Lead Items |  | m2 |  |  |  | Under Process | Approved | Rawaee ALBasateen |  | Local Transportation to site |  |  |  | 45d
5 |  | Steel Door | Long Lead Items | 8.1.2 | Sets | 24 | 24 |  | Under Process | Approved | MANASHY |  | Local Transportation to site |  |  |  | 60
6 |  | Aliminum Framed Window | Long Lead Items | 8.2.1.1 | Nos. | 24 | 24 |  | Under Process | Under Process | Sada AlTatweer |  | Local Transportation to site |  |  |  | 90
7 |  | Lighting And Power Type Panelboards | Long Lead Items | 16.11.1 | Nos. | 4 | 4 |  | Under Process | Under Process | Under Process |  | Local Transportation to site |  |  |  | 120
8 |  | Lighting Fixtures | Long Lead Items | 16.5.1 | Nos. | 2 | 2 |  | Under Process | Under Process | Under Process |  | Local Transportation to site |  |  |  | 120
9 |  | Fire Alarm System | Long Lead Items | 16.17.1 | Nos. | 288 | 288 |  | Under Process | Under Process | Under Process |  | Local Transportation to site |  |  |  | 120
10 |  | Facility water storage tanks | Long Lead Items | 15.2.8.1 | Nos. | 1 | 1 |  | Under Process | Approved | AlMuheedib |  | Local Transportation to site |  |  |  | 120
11 |  | Domestic-water packaged booster pump | Long Lead Items | 15.2.7.1 | Set | 1 | 1 |  | Under Process | Approved | Grandfos |  | Local Transportation to site |  |  |  | 120
#REF!

## Issues
[9 empty] | 2025-09-22 | Status | Responsibility
[10 empty] | Open | Contractor
[10 empty] | Closed | Consultant
Modon
Third Party
Other
Issue Log
Issue No | Date Identified | Issue Description | Responsibility | Action Taken | Current Status | Expected/Actual Closure | Duration Elapsed | #NAME?
1 | 2026-04-11 | Delay in starting work at Hail site project due to not getting the aoorved work permit | Other | Submit request to BALADI Platform for approval the work permit request | Closed | 2026-04-19
2
3
4
5
6
7

## Manpower
Head-Count ( Non Manual)
MONTHS | 2026-02-17 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | [15 empty] | 25
Plan - Monthly | 5 | 6 | 7 | 8 | 8 | 9 | 8 | 8 | 8 | 8 | 8
Planned - Cumulative | 5 | 11 | 18 | 26 | 34 | 43 | 51 | 59 | 67 | 75 | 83 |  |  |  | Key Trade | Site Engineer | Mason | Labor / Helper | Plumber | Electrician | HVAC Technician | Tile Fixer | Applicator | ELV Technician | Facade Technician | Crane Operator | Mechanical Technician | Painter | Surveyor | Glass Installer | Excavator Operator | Dump Truck Driver | Safety Officer | Paving Machine Operator | Concrete Mason | Carpenter | Gardener | Backhoe Operator | Wheel loader Operator | Store keeper | Security Guard | Boom Truck Operator | Foreman | Pickup Driver | Steel Fixer | Curbstone Installer | Compactor Operator | Roller Compactor Operator | Forklift Operator
Actual - Monthly | 6 | 7 | 10 | 17 | 15 | 16 | 17 | 17 | 16 | [5 empty] | Planned | 1 | 1 | 8 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | - | - | - | - | - | - | - | - | - | - | - | -
Actual Cumulative | 6 | 13 | 23 | 40 | 55 | 71 | 88 | 105 | 121 | 121 | 121 |  |  |  | Actual | 3 | 4 | 16 | 4 | 4 | - | 2 | - | - | - | - | - | - | 1 | - | 2 | 2 | 3 | - | - | 2 | - | 2 | 2 | 2 | 3 | 1 | 4 | 3 | 3 | 8 | 2 | 2 | 2
Forecast - Monthly | [9 empty] | 8 | 8
Saudi Monthly - Actual | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Head-Count (Manual)
MONTHS | 2026-02-17 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31
Plan - Monthly | 0 | 15 | 25 | 30 | 32 | 45 | 38 | 30 | 25 | 20 | 15
Planned - Cumulative | 0 | 15 | 40 | 70 | 102 | 147 | 185 | 215 | 240 | 260 | 275
Actual - Monthly | 3 | 5 | 30 | 35 | 48 | 76 | 72 | 75 | 73
Actual Cumulative | 3 | 8 | 38 | 73 | 121 | 197 | 269 | 344 | 417 | 417 | 417
Forecast - Monthly | [9 empty] | 20 | 15
Saudi - Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Head-Count (Non-Manual) | [11 empty] | Month | 2026-10-31 | 2026-11-30
Planned | Actual |  | Variance |  | Forecast Next Month |  | Saudi Staff
8 | 16 |  | 8 |  | 8 |  | 2
Head-Count (Manual)
Planned | Actual |  | Variance |  | Forecast Next Month |  | Saudi Staff
25 | 73 |  | 48 |  | 20 |  | 0
Equipment
MONTHS | 2026-02-17 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31
Plan - Monthly | 2 | 3 | 7 | 12 | 15 | 15 | 15 | 12 | 8 | 3 | 2
Planned - Cumulative | 2 | 5 | 12 | 24 | 39 | 54 | 69 | 81 | 89 | 92 | 94 |  |  |  | Type | Spray Machine | Excavator | Paving Machine | Crane | Dump Truck | Compactor | Roller Compactor | Grader | Boom Truck | Pickup Car | Wheel Loader | Water Tanker | Forklift | Backhoe
Actual - Monthly | 3 | 5 | 8 | 20 | 28 | 32 | 36 | 35 | 30 | [5 empty] | Planned | 1 | 1 | 1 | 1 | 1 | - | - | - | - | - | - | - | - | -
Actual Cumulative | 3 | 8 | 16 | 36 | 64 | 96 | 132 | 167 | 197 | 197 | 197 |  |  |  | Actual | - | 2 | - | - | 2 | 2 | 2 | 1 | 1 | 3 | 2 | 1 | 2 | 2
Forecast - Monthly | [9 empty] | 3 | 2 |  |  |  | Idle
Equipment Count
Planned | Actual |  | Idle |  | Variance |  | Forecast Next Month
8 | 30 |  |  |  | 22 |  | 3

## EV-Chart Data
| 35709993 |  |  | 0 | [5 empty] | 0.85
| Baseline Plan |  |  | Revised / Recovery Plan |  |  | Earned Value |  |  | Gross Paid Value |  |  | Forecast |  |  | Actual/Fcst vs Plan
Month | Monthly | Cum | % | Monthly | Cum | % | Monthly | Cum | % | Monthly | Cum | % | Monthly | C um |  | Month | Cum
2026-02-28 | 19016.75 | 19016.75 | 0% |  |  |  | 19016.75 | 19016.75 | 0.05325% | 2317493.31 | 2317493.31 | 6.49% | 19016.75 | 19017 | 0.05325% | 0 | 0 | Actuals thru previous month
2026-03-31 | 773633.22 | 792649.97 | 2.22% |  |  |  | 773633.22 | 792649.97 | 2.22% | 0 | 2317493.31 | 6.49% | 773633.22 | 792650 | 2.22% | 0 | 0
2026-04-30 | 1887846.29 | 2680496.26 | 7.506% |  |  |  | 1887846.29 | 2680496.26 | 7.506% | 0 | 2317493.31 | 6.49% | 1887846.29 | 2680496 | 7.506% | 0 | 0
2026-05-31 | 3153854.91 | 5834351.17 | 16.34% |  |  |  | 3153854.91 | 5834351.17 | 16.34% | 0 | 2317493.31 | 6.49% | 3153854.91 | 5834351 | 16.34% | 0 | 0
2026-06-30 | 4690129.86 | 10524481.03 | 29.47% |  |  |  | 4690129.86 | 10524481.03 | 29.47% | 0 | 2317493.31 | 6.49% | 4690129.86 | 10524481 | 29.47% | 0 | 0 | Forecast current and future months
2026-07-31 | 3183343.63 | 13707824.66 | 38.39% |  |  |  | 2150305.64 | 12674786.67 | 35.49% | 0 | 2317493.31 | 6.49% | 2150305.64 | 12674787 | 35.49% | -1033038 | -1033038
2026-08-31 | 8430690.11 | 22138514.77 | 62% |  |  |  | 5880471.86 | 18555258.53 | 51.96% | 0 | 2317493.31 | 6.49% | 5880471.86 | 18555259 | 51.96% | -2550218 | -3583256
2026-09-30 | 4219313.21 | 26357827.98 | 73.81% |  |  |  | 3860180.03 | 22415438.56 | 62.77% | 0 | 2317493.31 | 6.49% | 3860180.03 | 22415439 | 62.77% | -359133 | -3942389
2026-10-31 | 3799829.35 | 30157657.33 | 84.45% |  |  |  | 2225102.3 | 24640540.86 | 69% | 0 | 2317493.31 | 6.49% | 4392271 | 26807710 | 75.07% | -1574727 | -5517116
2026-11-30 | 3769036.68 | 33926694.01 | 95.01% |  |  |  |  | 24640540.86 | 69% | 0 | 2317493.31 | 6.49% | 3186473 | 29994183 | 83.99% | -3769037 | -9286153
2026-12-31 | 1783298.99 | 35709993 | 100% |  |  |  |  | 24640540.86 | 69% | 0 | 2317493.31 | 6.49% | 2362934 | 32357117 | 90.61% | -1783299 | -11069452
2027-01-31 | [7 empty] | 24640540.86 | 69% | 0 | 2317493.31 | 6.49% | 2646932 | 35004049 | 98.02% | 0 | -11069452
2027-02-28 | [7 empty] | 24640540.86 | 69% |  |  |  | 705944 | 35709993 | 100% |  |  |  | Extended Duration
705944
UPDATE ONLY YELLOW PORTION FROM PRIMAVERA EXPORT, IF NEEDED, EXTEND YELLOW PORTION BASED ON SCHEDULE.

## Physical-Chart Data
| 33340.01 |  |  | 0
| Baseline Plan |  |  | Revised / Recovery Plan |  |  | Earned Effort % |  |  | Forecast |  |  | Achieved/Fcst vs Plan
Week | Monthly Effort | Cum Effort | Plan Wt.% | Monthly Effort | Cum Effort | Plan Wt.% | Monthly Wt. | Cum Wt. | Achieved Wt.% | Monthly Wt. | Cum Wt. | Wt.% | Monthly Wt. | Cum Wt.
2026-02-28 | 365.35 | 365.35 | 1.096% |  |  |  | 0 | 365.35 | 1.096% | 0 | 0 | 0% | -365 | -365 |  | Actuals thru previous month
2026-03-31 | 1021.84 | 1387.19 | 4.161% |  |  |  | 1021.84 | 1387.19 | 4.161% | 1021.84 | 1021.84 | 3.065% | 0 | -365
2026-04-30 | 2555.3 | 3942.49 | 11.83% |  |  |  | 2555.3 | 3942.49 | 11.83% | 2555.3 | 3577.14 | 10.73% | 0 | -365
2026-05-31 | 3166.11 | 7108.6 | 21.32% |  |  |  | 3166.11 | 7108.6 | 21.32% | 3166.11 | 6743.25 | 20.23% | 0 | -365
2026-06-30 | 3611.07 | 10719.67 | 32.15% |  |  |  | 3611.07 | 10719.67 | 32.15% | 3611 | 10354.25 | 31.06% | 0 | -365 |  | Forecast current and future months
2026-07-31 | 3964.01 | 14683.68 | 44.04% |  |  |  | 2719.89 | 13439.56 | 40.31% | 2720 | 13074.25 | 39.21% | -1244 | -1609
2026-08-31 | 4829.56 | 19513.24 | 58.53% |  |  |  | 5621.12 | 19060.68 | 57.17% | 5621 | 18695.25 | 56.07% | 791 | -818
2026-09-30 | 4518.95 | 24032.19 | 72.08% |  |  |  | 3247.32 | 22308 | 66.91% | 3247.32 | 21942.57 | 65.81% | -1272 | -2090
2026-10-31 | 4581.12 | 28613.31 | 85.82% |  |  |  | 2627 | 24935 | 74.79% | 5122.44 | 27065.01 | 81.18% | 541 | -1549
2026-11-30 | 3488.79 | 32102.1 | 96.29% |  |  |  |  | 24935 | 74.79% | 2998 | 30063.01 | 90.17% | -491 | -2040
2026-12-31 | 1237.91 | 33340.01 | 100% |  |  |  |  | 24935 | 74.79% | 2194 | 32257.01 | 96.75% | 956 | -1084
2027-01-31 | [7 empty] | 24935 | 74.79% | 1020 | 33277.01 | 99.81%
2027-02-28 | [7 empty] | 24935 | 74.79% | 63 | 33340.01 | 100%
33340.01
Extended Duration
"
63
UPDATE ONLY YELLOW PORTION FROM PRIMAVERA EXPORT, IF NEEDED, EXTEND YELLOW PORTION BASED ON SCHEDULE.
Activity ID | Activity Name | Original Duration | Activity Count | BL Project Start | BL Project Finish | Start | Finish | Budgeted Total Cost | Schedule % Complete | Performance % Complete | Planned Value Cost | Earned Value Cost | Spreadsheet Field | 2024-01-07 | 2024-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-31 | 2024-06-30 | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28
Total |  | 623.25 | 1116 | 2024-01-07 | 46028 | 07-Jan-24 A | 46062 | 45093675 | 2.35% | 0.0414 | 105921808% | 186653732% | Estimate At Completion Cost |  | 30538.52 | 1081338.05 | 1181886.84 | 3852422.27 | 2825164.68 | 5589699.62 | 164037.04 | 1457350.04 | 2023101.31 | 2985685.95 | 2676580.28 | 2382653.65 | 1638258.93 | 399461.15 | 853330.59 | 673208.04 | 847493.51 | 1128976.22 | 758032.28 | 519891.8 | 1698067.5 | 3666808.7 | 5859916.21 | 804803.46
Total |  | 623.25 | 1116 | 2024-01-07 | 46028 | 07-Jan-24 A | 46062 | 45093675 | 2.35% | 0.0414 | 105921808% | 186653732% | Cum Estimate At Completion Cost |  | 30538.52 | 1111876.57 | 2293763.41 | 6146185.67 | 8971350.35 | 14561049.97 | 14725087 | 16182437.05 | 18205538.36 | 21191224.3 | 23867804.58 | 26250458.24 | 27888717.17 | 28288178.32 | 29141508.91 | 29814716.95 | 30662210.45 | 31791186.68 | 32549218.96 | 33069110.76 | 34767178.27 | 38433986.97 | 44293903.18 | 45098706.64 | 45098706.64
Total |  | 623.25 | 1116 | 2024-01-07 | 46028 | 07-Jan-24 A | 46062 | 45093675 | 2.35% | 0.0414 | 105921808% | 186653732% | Estimate At Completion - Labor Units | 4258.46 | 5074.51 | 8105.89 | 19746.36 | 28683.22 | 22788.05 | 115528.27 | 24471.59 | 23083.07 | 26804.15 | 16374.77 | 43019.93 | 31912.42 | 13734.26 | 6745.33 | 11525.08 | 10816.73 | 12606.27 | 13153.86 | 15583.13 | 13855.6 | 30008.2 | 24989.16 | 15344.27 | 2832.93 | 276.87
Total |  | 623.25 | 1116 | 2024-01-07 | 46028 | 07-Jan-24 A | 46062 | 45093675 | 2.35% | 0.0414 | 105921808% | 186653732% | Cum Estimate At Completion - Labor Units | 4258.46 | 9332.97 | 17438.86 | 37185.22 | 65868.44 | 88656.49 | 204184.75 | 208656.34 | 231739.41 | 258543.56 | 274918.32 | 317938.26 | 349850.68 | 363584.94 | 370330.28 | 381855.36 | 392672.09 | 405278.36 | 418432.22 | 434015.35 | 447870.95 | 477879.15 | 502868.31 | 518212.58 | 521045.51 | 521322.38
Total |  | 623.25 | 1116 | 2024-01-07 | 2026-01-06 | 07-Jan-24 A | 2026-02-09 | 45093675 | 2.35% | 0.0414 | 105921808% | 186653732% | Budgeted Nonlabor Units | 1020.07 | 683.2 | 1827.82 | 8222.03 | 9599.27 | 8008.4 | 22624.35 | 8359.75 | 8710.96 | 9488.56 | 4750.34 | 14612.18 | 14065.27 | 4938.49 | 2034.98 | 3281.5 | 2695.75 | 3107.56 | 3844.99 | 4489.05 | 4347.6 | 7437.25 | 7013.87 | 4975.96 | 617 | 156.87
0

## Schedule
Primavera P6 Schedule Status | [9 empty] | Data Date | 2026-10-18
Project Activities Overview
Schedule Statistics |  |  |  |  | Active Schedule Activities
Total Act. | Not Started | In Progress | Completed | % | Active | Ahead | On | Behind | Flag
1929 | 86 | 223 | 1620 | 83.98% | 223 | 43 | 51 | 215 | -121
Critical Path Activities |  |  | Free Float Management (Total) |  |  |  | Failed Start Activities
|  |  | Greater Than 14 Days |  | Less Than 14 Days
Last Week | This Week | Diff | Last Week | This Week | Last Week | This Week | Last Week | This Week | Flag
205 | 174 | 31 | 54 | 39 | 284 | 270 | 77 | 42 | 35

## Testing
Testing and Commissioning
Location | Planned Start Date | Planned Finish Date | Forecast Start Date | Forecast Finish Date | Actual Start Date | Actual Finish Date | % Completed | Open Comments | Closed Comments
QASSIM | 2026-11-15 | 2026-12-12 |  | 2027-01-18 | 2026-05-22
HAIL | 2026-11-02 | 2026-12-03 |  | 2026-12-07 | 2026-05-25
TABUK | 2026-11-22 | 2027-01-02 |  | 2027-01-23 | 2026-05-25
Total | 2026-11-02 | 2027-01-02 |  | 2027-01-23 | 2026-05-22
Formulas:
Planned Start Date = MIN(C4:[Planned Start Date, row above])
Planned Finish Date = MAX(D4:[Planned Finish Date, row above])
Forecast Finish Date = MAX(F4:[Forecast Finish Date, row above])
Actual Start Date = IF(MIN(G4:[Actual Start Date, row above]),MIN(G4:[Actual Start Date, row above]),"")

## Progress Tracking sheet
Playgrounds Initiative - Qassim, Hail & Tabuk |  |  |  |  | Progress Tracking Sheet | [11 empty] | Date : | 2026-10-18
Block | Activities
| Cut and Fill | Football Playground works | Basketball Playground works | Padel Playground works | Fence Works | Mechanical Works | Electrical Works | Park Works | Septic Tank Works | Water Storage Tank Works | Civil Works Air dome | Architectural Works | Mechanical Works | Electrical Works | Civil Works Toilet Bld | MEP Works Toilet Bld | Hardscape Works | Softscape Works
[15 empty] | Beams | Beams
Playground & General Site Works (Qassim) | 100% | 80% | 80% | 60% | 90% | 20% |  | 50% | 100% | 100% | 30%
Air Dome Works (Qassim)
Toilet Building Works (Qassim) | [14 empty] | 80% | 40%
Landscaping Works (Qassim)
Playground & General Site Works (Hail) | 100% | 80% |  |  | 80% | 20% |  | 50% | 80% | 80%
Toilet Building Works (Hail) | [14 empty] | 70% | 40%
Landscaping Works (Hail)
Playground & General Site Works (Tabuk) | 100% | 80% | 80% | 60% | 90% | 20% |  | 50% | 80% | 80% | 30%
Air Dome Works (Tabuk)
Toilet Building Works (Tabuk) | [14 empty] | 80% | 40%
Landscaping Works (Tabuk)

## BOQ Summary
اسم المشروع | مبادرة الملاعب بالمنطقة الوسطى
رقم العقد | P030
رقم المشروع | MLTX-02-003
قيمة المشروع (غير شامل ضريبة القيمة المضافة) | 35709992
ملخص جدول الكميات
الحفریات و الردم | 2205000 | 6.175%
أعمال الطـــرق والمواقف | 530943 | 1.487%
تنسیق المواقع | 25537253 | 71.51%
إشارات الطـــرق | 19836 | 0.05555%
اعمال الخرسانة | 241317 | 0.6758% | 1622404 | 1641789
اعمال المباني | 12420 | 0.03478% | 82232 | 82232
الأعمال المعدنیة | 47889 | 0.1341% | 129676 | 129676
اعمال العزل المائى والحرارى | 75930 | 0.2126% | 342656 | 342656
اعمال الابواب والشبابیك | 88923 | 0.249% | 957942 | 957942
أعمال التشطیبات | 508780 | 1.425% | 539460 | 539460
الأعمال الخاصة | 226287 | 0.6337% | 287656 | 287656
الأثاث | 473491 | 1.326% | 4081341 | 4153389
الأعمال المیكانیكیة | 3018893 | 8.454% | 2917872 | 2928158
الأعمال الكھربائیة | 2723031 | 7.625% | 5235491 | 4588560