## Weekly Progress Report
MODON - Weekly Progress Report - Construction Projects | [30 empty] | Data Date |  | 2026-10-12
Contract General Information | [5 empty] | Key Dates | [5 empty] | Cost Summary (SR) | [7 empty] | Performance Summary | [5 empty] | Project Scope
Project Name | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two |  |  |  |  | Contract Award | 2025-12-07 | Contract Award (Hijri) | 16/6/1447 | Revised Completion | 0 | Original Contract Value |  | 168629520 |  | O&M Value |  | 0 | EAC | Plan Value | 37.9% | Phys. Plan Value | 39.1% | Quality Score | 81.34% | The scope of work of the project includes the implementation of the entire works subject to the contract, including the following: Road and paving works, Potable Water Network Works, Treatment Water Network Works, Sewer network works, Rainwater drainage network works, Irrigation and landscaping network works, Electrical network works including (medium voltage, communications, road lighting), Camera surveillance work
Project ID | SUD1-02-011 |  | Stage | Construction |  | Contract Sign | 2025-12-29 | Contract Sign (Hijri) | 9/7/1447 | Committed Completion | 2027-07-05 | Revised Contract Value |  | 0 | EAC | Revised O&M Value |  | 0 | #REF! | Earn Value | 46.3% | Phys. Earn Value | 42.8% |  | ¢¢¢¢¢ ¢¢¢££
Contractor | Technical Dvelopment Co. "TDC" |  | Status | Active |  | Site Handover | 2026-01-06 | Site Handover (Hijri) | 17/7/1447 | Forecast Completion | 2027-07-05 | Estimate At Completion Value |  | 168629520 | #REF! | Submitted Invoices (Gross Value) |  | 24575402.47 |  | Variance | 8.393% | Variance | 3.697% | Safety Score | 81.82%
Consultant | Saudi Arabia Consulting Engineering Company "EGIS" |  | Modon PM | Engr.Zyad Al Shabat |  | Original Completion | 2027-07-05 | Original Completion (Hijri) | 30/1/1449 | Variance | 0 | Potential Changes |  | 0 |  | Total Deduction |  | -2491540.247 |  | SPI | 1.2214 | SPI | 1.0945 |  | ¢¢¢¢¢ ¢¢¢££
Progress Overview
Earned Value Progress (SAR) | [13 empty] | Physical Progress (Effort) | [11 empty] | Earned Value Progress (%)
WBS |  | BOQ Value (SAR) | % Wt. | Weekly (SAR) |  | To Date (SAR) | [7 empty] | Budgeted | % Wt. | Weekly Physical Progress |  |  |  | To Date Physical Progress
|  |  |  | Planned | Earned | Original Plan | Planned | Earned | Original Plan % | Cum. Planned % | Cum.Earned % | Variance | SPI | (Manhours) |  | Planned | Earned | Plan % | Earned % | Planned | Earned | Plan % | Earned % | Variance | SPI
|  | 0 | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0% |  |  |  | 0% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
Mobilization |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 34177 | 3% | 0 | 0 | 0% | 0% | 34177 | 34177 | 100% | 100% | 0% | 1
Engineering |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 56962 | 5% | 0 | 0 | 0% | 0% | 56962 | 53211 | 100% | 93.41% | -6.585% | 0.93415
Procurement |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 148102 | 13% | 1217 | 17580 | 0.8217% | 11.87% | 146212 | 65998 | 98.72% | 44.56% | -54.16% | 0.45139
Construction |  | 168629520.27 | 100% | 5429626.78 | 2109267.84 | 0 | 63916569.57 | 78069977.79 | 0% | 37.9% | 46.3% | 8.393% | 1.2214 | 854433 | 75% | 18811 | 12969 | 2.202% | 1.518% | 208117 | 334200 | 24.36% | 39.11% | 14.76% | 1.6058
ROAD WORKS |  | 87969996.94 | 52.17% | 3927465.91 | 753424.85 | 0 | 52825114.99 | 55876252.92 | 0% | 60.05% | 63.52% | 3.468% | 1.0578 | 186393 | 16.36% | 6915 | 1275 | 3.71% | 0.684% | 129463 | 144870 | 69.46% | 77.72% | 8.266% | 1.119
ZONE A |  | 54469012.74 | 32.3% | 3473855.41 | 574125.23 | 0 | 30294037.65 | 30553312.26 | 0% | 55.62% | 56.09% | 0.476% | 1.0086 | 121795 | 10.69% | 3996 | 943 | 3.281% | 0.7743% | 82886 | 93033 | 68.05% | 76.38% | 8.331% | 1.1224
ZONE G |  | 33500984.21 | 19.87% | 453610.49 | 179299.62 | 0 | 22531077.33 | 25322940.66 | 0% | 67.25% | 75.59% | 8.334% | 1.1239 | 64598 | 5.67% | 2918 | 334 | 4.517% | 0.517% | 46576 | 51838 | 72.1% | 80.25% | 8.146% | 1.113
Storm Water Drainage Network |  | 25407829.28 | 15.07% | 366060.85 | 949166.11 | 0 | 6330005.15 | 10306197.27 | 0% | 24.91% | 40.56% | 15.65% | 1.6281 | 187421 | 16.45% | 3342 | 5382 | 1.783% | 2.872% | 36171 | 80702 | 19.3% | 43.06% | 23.76% | 2.2311
ZONE A |  | 22856155.07 | 13.55% | 334539.67 | 949166.11 | 0 | 349473.37 | 7772621.72 | 0% | 1.529% | 34.01% | 32.48% | 22.241 | 131130 | 11.51% | 2389 | 5382 | 1.822% | 4.104% | 25551 | 25084 | 19.49% | 19.13% | -0.3561% | 0.98172
ZONE G |  | 2551674.21 | 1.513% | 0 | 0 | 0 | 349473.37 | 2533575.54 | 0% | 13.7% | 99.29% | 85.59% | 7.2497 | 56291 | 4.941% | 0 | 0 | 0% | 0% | 10620 | 55618 | 18.87% | 98.8% | 79.94% | 5.2371
Sewerage Network |  | 7071026.79 | 4.193% | 0 | 198690.12 | 0 | 140851.15 | 5555678.93 | [5 empty] | 62221 | 5.462% | 1127 | 725 | 1.811% | 1.165% | 1907 | 45169 | 3.065% | 72.59% | 69.53% | 23.6859
ZONE A |  | 4499744.21 | 2.668% |  | 198690.11 | 0 | 91222.91 | 3111180.86 | [5 empty] | 40161 | 3.525% | 725 | 726 | 1.805% | 1.808% | 1097 | 24182 | 2.732% | 60.21% | 57.48% | 22.0438
ZONE G |  | 2571282.59 | 1.525% |  | 0 | 0 | 49628.24 | 2444498.06 | [5 empty] | 22061 | 1.936% | 0 | 0 | 0% | 0% | 810 | 20987 | 3.672% | 95.13% | 91.46% | 25.9099
TSE Network |  | 4147696.13 | 2.46% |  | 114868.09 | 0 |  | 785149.68 | [5 empty] | 87808 | 7.708% | 0 | 1471 | 0% | 1.675% | 0 | 5356 | 0% | 6.1% | 6.1%
ZONE A |  | 3158469.43 | 1.873% | 0 | 114868.08 | 0 | 179295.3 | 721661.92 | 0% | 22.85% | 22.85% | 0% | 1 | 64717 | 5.681% | 0 | 0 | 0% | 0% | 1614 | 4104 | 2.494% | 6.341% | 3.848% | 2.5428
ZONE G |  | 989226.71 | 0.5866% |  | 0 | 0 |  | 63487.76 | [5 empty] | 23091 | 2.027% | 0 | 0 | 0% | 0% | 0 | 1252 | 0% | 5.422% | 5.422%
Portable Water |  | 7780467.63 | 4.614% |  | 63323.42 | 0 | 0 | 1697785.81 | 0% | 0% | 21.82% | 21.82% |  | 139722 | 12.26% | 0 | 3617 | 0% | 2.589% | 0 | 19877 | 0% | 14.23% | 14.23%
ZONE A |  | 4936252.63 | 2.927% |  | 63323.42 | 0 |  | 476047.8 | [5 empty] | 99650 | 8.747% | 0 | 3617 | 0% | 3.63% | 0 | 9191 | 0% | 9.223% | 9.223%
ZONE G |  | 2844215 | 1.687% |  | 0 | 0 | 0 | 1221738.01 | 0% | 0% | 42.96% | 42.96% |  | 40072 | 3.517% | 0 | 0 | 0% | 0% | 0 | 10686 | 0% | 26.67% | 26.67%
Electrical Works |  | 20111193.29 | 11.93% |  | 29795.25 | 0 | [7 empty] | 99033 | 8.693%
ZONE A |  | 13562632.1 | 8.043% |  |  | 0 | [7 empty] | 63660 | 5.588%
ZONE G |  | 6548561.19 | 3.883% |  |  | 0 | [7 empty] | 35373 | 3.105%
Landscape & Irrigation Works |  | 6835460.57 | 4.054% |  |  | 0 | [7 empty] | 77656 | 6.816%
ZONE A |  | 3801841.66 | 2.255% |  |  | 0 | [7 empty] | 65750 | 5.771%
ZONE G |  | 3033618.91 | 1.799% |  |  | 0 | [7 empty] | 11907 | 1.045%
CCTV Works |  | 9305849.64 | 5.519% |  |  | 0 | [7 empty] | 14178 | 1.245%
ZONE A |  | 46056 | 3.863% |  |  | 0 | [7 empty] | 7062 | 0.6199%
ZONE G |  | 2 | 1.656% |  |  | 0 | [7 empty] | 7116 | 0.6246%
Testing and commissioning |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 22785 | 2% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
Close out |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 22785 | 2% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
| Total | 168629520.27 | 100% | 5429626.78 | 2109267.84 | 0 | 63916569.57 | 78069977.79 | 0% | 37.9% | 46.3% | 8.393% | 1.2214 | 1139244 | 100% | 20028 | 30549 | 1.758% | 2.682% | 445468 | 487586 | 39.1% | 42.8% | 3.697% | 1.0945
Construction Milestones
[26 empty] | Item No. | Milestones |  | Original (Baseline) | Latest Plan | Forecast |  | Status | Days Change
[7 empty] | #VALUE! | [18 empty] | 1 | Project Start Milstone |  | 2026-01-06 | 2026-01-06 | 2026-01-06 |  | Finish | 0
[25 empty] | #REF! | 2 | Mobilization Finish Milestone |  | 2026-02-05 | 2026-02-05 | 2026-02-05 |  | Finish | 0
[25 empty] | #REF! | 3 | Baseline Submission Finish Milestone |  | 2026-02-05 | 2026-04-06 | 2026-04-06 |  | Finish | -60
[25 empty] | #REF! | 4 | Technical Submittals Finish Milestone |  | 2026-03-05 | 2026-08-16 | 2026-08-16 |  | UP | -164
[25 empty] | #REF! | 5 | Quality Lap Finish Milestone |  | 2026-02-05 | 2026-02-16 | 2026-02-16 |  | Finish | -11
[25 empty] | #REF! | 6 | RBF Finish Milestone |  | 2026-02-05 | 2026-02-16 | 2026-02-16 |  | Finish | -11
[6 empty] | 20000000 | 505886 | 463892 | [5 empty] | 34555 | 34555 | [9 empty] | #REF! | 7 | All Works Finish Milestone |  | 2027-07-05 | 2027-07-05 | 2027-07-05 |  | UP | 0
[7 empty] | 86640 | 605533 | [16 empty] | #REF! | 8 | Engineering Phase Finish Milestone |  | 2026-03-05 | 2026-09-28 | 2026-09-28 |  | UP | -207
[7 empty] | 926799 | [6 empty] | 57592 | 50223 | [9 empty] | #REF! | 9 | Procurment Phase Finish Milestone |  | 2027-01-23 | 2027-01-17 | 2027-01-17 |  | UP | 6
[7 empty] | 921566 | [6 empty] | 9755 | 11013
[7 empty] | 479000 | 504900 | [5 empty] | 4073
[7 empty] | 442566 | 1116058 | [5 empty] | 3975 | 8164
[7 empty] | 5233 | 186144 | [5 empty] | 2008 | 2454
[7 empty] | 5233 | 186144 | [5 empty] | 1967 | 5710
[14 empty] | 97 | 635
[14 empty] | 97 | 635
Performance overview
Submittals Status | [10 empty] | Quality | [10 empty] | Safety
Shop Drawings | [10 empty] | Quality Reports | [10 empty] | Safety Statistics | [7 empty] | Proactive Vs Reactive Actions Taken
Item Per WBS |  | Total | Total Submitted Drawings |  |  |  |  | Remaining | Pending | Total Submittals | Quality Reports |  | Issued | Closed | Pending | Avg. Closing (Days) | Pending |  |  |  |  | Category | Item |  | This Week |  | This Month | Year to Date | Cumulative
|  |  | A | B | C | D | Processed | [9 empty] | 0-10 Days | 11-20 Days | 21-30 Days | 31-60 Days | > 60 Days
Road work |  | 130 | 28 | 102 | 0 | 0 | 130 | 0 | 0 | 130 | [11 empty] | General | Total Hours Worked |  | 37020 |  | 61360 | 863816 | 863816 |  |  |  | Proactive | 94
wet network(sewer,storm,potable,irrigation) |  | 140 | 26 | 109 | 0 | 0 | 135 | 5 | 0 | 135 | Non Conformance (NCR) |  | 17 | 16 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | Safe Hours Worked |  | 37020 |  | 61360 | 863816 | 863816 |  |  |  | Reactive | 0
Electrical,Telecom,Street light |  | 107 | 35 | 0 | 0 | 44 | 35 | 28 | 0 | 79 | Site Instruction (SIR) |  | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Reactive | 0 |  | 0 |  | 0 | 54 | 0
Landscape |  | 22 | 3 | 4 | 15 | 0 | 7 | 0 | 0 | 22 | Material Inspection (MIR) |  | 230 | 229 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
CCTV |  | 12 | 0 | 11 | 0 | 1 | 11 | 0 | 0 | 12 | Field Inspection (FIR) |  | 3616 | 3558 | 58 | 0 | 58 | 0 | - | 0 | 0 |  | 0 |  | 0 |  | 0 | 40 | 0
TOTAL |  | 411 | 92 | 226 | 15 | 45 | 318 | 33 | 0 | 378 | Key Submittals Approval Status | [11 empty] | 0 |  | 0 |  | 0 | 0 | 0
Material Approval | [10 empty] | 1 Quality Plan Approval |  |  | 2026-03-31 |  | 6 Baseline Approval |  |  |  | 2026-04-08 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | Total Hours Worked Vs Safe Hours Worked
Item Per WBS |  | Total | Total Submitted Material |  |  |  |  | Remaining to approve | Pending | Total Submittals | 2 Quality Plan Last Up |  |  | 2026-03-31 |  | 7 No of Approved Version of Schedule |  |  |  | 1 |  |  | 0 |  | 0 |  | 0 | 0 | 0
|  |  | A | B | C | D | Processed | with Designer |  |  | 3 Safety Plan Approval |  |  | 2026-01-27 |  | 8 Last Approved Schedule |  |  |  | - |  |  | 0 |  | 0 |  | 0 | 0 | 0
Civil /Structural /Architectural |  | 25 | 0 | 22 | 0 | 1 | 23 | 2 | 0 | 23 | 4 Safety Plan Last Up |  |  | 2026-01-27 |  | 9 BOQ Approval Date |  |  |  | - |  |  | 0 |  | 0 |  | 0 | 0 | 0
Mechanical |  | 14 | 0 | 14 | 0 | 0 | 14 | 0 | - | 14 | 5 Construction Plan Approval |  |  | 2026-02-10 |  | 10 No of Approved Version of BOQ |  |  |  | - |  |  | 0 |  | 0 |  | 0 | 46088 | 0
Electrical |  | 21 | 1 | 17 | 0 | 3 | 18 | 0 | 0 | 18 | Invoices Summary | [10 empty] | Proactive | 0 |  | 0 |  | 0 | 46095 | 0
[11 empty] | Total Submitted Invoices |  | 4 | Submitted Invoices (SAR) |  |  | 24575402.47 |  | Contract Value (SR) | 0 |  |  | No.of Internal Training |  | 1 |  | 2 | 54 | 54
[11 empty] | PM Approved Invoices |  | 0 | PM Approved Invoices (SAR) |  |  | 0 |  | Planned Value (SR) | 63916569.57 |  |  | No.of Internal Audit |  | 0 |  | 0 | 0 | 0
TOTAL |  | 60 | 1 | 53 | 0 | 4 | 55 | 2 | 0 | 55 | No of Paid Invoices |  | 0 | Paid Invoices (SAR) |  |  | 0 |  | Earned Value (SR) | 78069977.79 |  |  | No. of Toolbox Talks |  | 1 |  | 2 | 40 | 40
Procurement Summary | [10 empty] | No of Pending Invoices |  | 4 | Last Submitted Period |  |  | 0 |  | Submitted (SAR) | 24575402.47 |  |  | Safety Awards/Incentives |  | 0 |  | 0 | 0 | 0
Item Per WBS |  | Total Materials | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Material on Site | Remaining Materials | Material Delivery Completion (Date) |  |  | Advance Payment % |  | 10% | Advance Payment (SAR) |  |  | 16862952 |  | PM Approved (SAR) | 0 |  | Latest Contract Change Order Log
|  |  | A | B | C | D | Processed |  |  |  | Retention % |  | 0% | Retention (SAR) |  |  | 0 |  | Total Paid (SAR) | 0
Civil /Structural /Architectural |  | 16 | 16 | 10 | 6 | 7 | 9 | - | 0 | 0 | Deduction / Penalties % |  | -1.478% | Deduction / Penalties (SAR) |  |  | -34000 |  |  |  |  | CCO No. | Date Added | Description of Change |  |  |  |  | Status | Cost | Sch Impact (Months) |  | Date Approved | Duration
Mechanical |  | 75 | 59 | 59 | 17 | 23 | 52 | - | 0 | 0 | Resources at Site
Electrical |  | 20 | 14 | 14 | 6 | 4 | 16 | - | 0 | 0 | Head Count - Manual |  |  |  | Head Count - Non Manual |  |  |  | Total Head Count |  |  | - | - | - |  |  |  |  | - | - | - |  | - | -
[11 empty] | Planned | Actual | Next Month Forecast | Saudi Staff | Planned | Actual | Next Month Forecast | Saudi Staff | Total Plan | Total Actual | Variance
[11 empty] | 300 | 558 | 0 | 6 | 35 | 58 | 0 | 4 | 335 | 616 | 281
TOTAL |  | 111 | 89 | 83 | 29 | 34 | 77 | 0 |  |  | Manpower Breakdown by Trade | [6 empty] | Major Equipment
Primavera P6 Schedule Status | [10 empty] | Key Trade | Planned | Actual |  |  |  |  | Type | Planned | Actual | Idle
Project Activities Overview | [10 empty] | Engineer | 15 | 18 |  |  |  |  | PICK UP/Car | 7 | 12 | 0
Schedule Statistics |  |  |  |  | Active Schedule Activities | [5 empty] | Doc. Controller | 2 | 3 |  |  |  |  | Bus | 4 | 6 | 0 | Major Quantity Trackers
Total Act. | Not Started | In Progress | Completed | % | Active | Ahead | On | Behind | Flag | 0 | Proc. Team | 3 | 3 |  |  |  |  | Dump Truck | 70 | 158 | 0 | BOQ N0. | Item Description |  |  |  |  | Total Qty | Measu Unit | Plan to Date | Actual To Date Delivered | Excecuted on site | Remaining Total Delivery | Variance
2115 | 1052 | 144 | 711 | 33.62% | 26 | 5 | 0 | 17 | -12 |  | Foreman | 9 | 19 |  |  |  |  | Boom Truck | 2 | 5 | 0 | 33 31 00 | GRP Pipes |  |  |  |  | 18337 | m | 16000 | 17437 | 16000 | 900 | 900
Critical Path Activities |  |  | Free Float Management (Total) |  |  |  | Failed Start Activities |  |  |  | Draftman | 2 | 2 |  |  |  |  | Generator + Tower Light | 4 | 5 | 0 | 33 05 39 | Manholes |  |  |  |  | 251 | m | 150 | 221 | 210 | 30 | 30
|  |  | Greater Than 14 Days |  | Less Than 14 Days | [5 empty] | Driver | 135 | 321 |  |  |  |  | JCB | 4 | 9 | 0 | 33 42.1 | UPVC Pipes |  |  |  |  | 4716 | m | 5500 | 4716 | 1000 | 0 | 0
Last Week | This Week | Diff | Last Week | This Week | Last Week | This Week | Last Week | This Week | Flag | 0 | UnSkilled Labor | 41 | 90 |  |  |  |  | Water Tank | 13 | 15 | 0 | 33 42.1 | Fire Hydrants |  |  |  |  | 90 | Unit | 20 | 90 | 1 | 0 | 0
34 | 0 | 34 | 193 | 180 | 1209 | 1186 | 17 | 33 | -16 |  | Total | 300 | 611 |  |  |  |  | Total | 104 | 210 | 0 | 33 05 39 | Catch Basins |  |  |  |  | 295 | Unit | 150 | 295 | 116 | 0 | 0
Weekly Prgoress Photos | [15 empty] | Top Issues and Risks
Grading for base course layer works at MC20 Zone A |  |  |  |  | Compaction for base course layer works at MC20 Zone A | [5 empty] | Spraying MC1 for base course works at MCD0, Zone G. |  |  |  |  | Top 5 Issues
[16 empty] | Issue No | Date Identified | Issue Description |  |  |  | Responsible | Action Taken |  |  | Mitigation |  |  |  |  | Current Status |  | Expected/Actual Closure | Duration Elapsed
[16 empty] | 3120 - 7 | 2026-09-28 |  | #REF! | #REF! | #REF! | Contractor | An Awareness session was conducted with operators working in utilties contained areas | [7 empty] | CLOSED |  | 2 | 1
[16 empty] | 3120 - 8 | 2026-10-01 | observe excavation without proper sloping or benching | #REF! | #REF! | #REF! | Contractor | Provide sloping, benching and shoring with edge protection | [7 empty] | CLOSED |  | 2 | 1
[16 empty] | 3120 - 9 | 2026-10-01 | Found Equipment Operator unaware of MEPI and Equipment Safety Training | #REF! | #REF! | #REF! | Contractor | An Awareness session was conducted with operators and inspection of equipment was insured | [7 empty] | CLOSED |  | 2 | 1
[16 empty] | 3120 - 10 | 2026-10-11 | observe excavation not backfilled for long time with improper sloping | #REF! | #REF! | #REF! | Contractor | Backfilling of excavated tenches and provide sloping, benching and shoring with edge protection | [7 empty] | CLOSED |  | 2 | 1
[16 empty] | 3120 - 11 | 2026-10-11 | Observe unleved roads with no dust control | #REF! | #REF! | #REF! | Contractor | Level the roads with regular grading and water spraying of vehicles routes. | [7 empty] | CLOSED |  | 2 | 1
0

## General Information
Weekly Progress Report - Construction Projects |  |  |  |  | Data Date | 2026-10-12
Contract General Information
Project Name | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two
Project ID | SUD1-02-011
Contractor | Technical Dvelopment Co. "TDC"
Consultant | Saudi Arabia Consulting Engineering Company "EGIS"
Stage | Construction
Status | Active
Modon PM | Engr.Zyad Al Shabat
|  |  | 0 | 0
Key Dates |  |  | 0 | 0
Contract Award Date | 2025-12-07
Contract Sign Date | 2025-12-29
Site Handover Date | 2026-01-06
Original Completion | 2027-07-05
Contract Award Date (Hijri) | 16/6/1447
Contract Sign Date (Hijri) | 9/7/1447
Site Handover Date (Hijri) | 17/7/1447
Original Completion (Hijri) | 30/1/1449
Revised Completion Date | 0
Committed Completion Date | 2027-07-05
Forecast Completion | 2027-07-05
Variance | 0
Key Project Submittals | Submission Date | Days taken to approve orginal plan from site handover date
Quality Plan submission | 2026-02-04 | 29
Quality Plan approval | 2026-03-31
Quality Plan Last Update | 2026-03-31
Safety Plan submission | 2026-01-22 | 16
Safety Plan approval | 2026-01-27
Safety Plan Last Update | 2026-01-27
Risk Management Plan submission | 2026-01-28 | 22
Risk Management Plan approval | 2026-02-03
Risk Management Plan Last Update | 2026-02-03
Baseline Schedule submission | 2026-01-31 | 25
Baseline Schedule approval | 2026-04-08
No of Schedule Versions | 1
Last Revised Schedule Approval Date | -
BOQ submission | - | -
BOQ approval | -
No of Approved Version of BOQ | -
Execution Plan submission | 2026-02-07 | 32
Execution Plan Approval | 2026-02-10
Note on D25: AlNuaim, Abdulaziz: As per contract requirments submission of Plans should be 30 days after site handover

## Progress
Project Scope Statement | The scope of work of the project includes the implementation of the entire works subject to the contract, including the following: Road and paving works, Potable Water Network Works, Treatment Water Network Works, Sewer network works, Rainwater drainage network works, Irrigation and landscaping network works, Electrical network works including (medium voltage, communications, road lighting), Camera surveillance work
Earned Value Progress (SAR) | [8 empty] | Physical Progress (Effort)
WBS |  | BOQ Value (SAR) | % Wt. | Weekly (SAR) |  |  | To Date (SAR) |  | Budgeted | % Wt. | Weekly Physical Progress |  | To Date Physical Progress
|  |  |  | Planned | Earned | Original Plan | Planned | Earned | (Manhours) |  | Planned | Earned | Planned | Earned
Milestones |  | 0 |  |  |  |  | 0 | 0 | 0 | 0% |  |  | 0 | 0
Mobilization |  | 0 |  |  |  |  | 0 | 0 | 34177 | 3% | 0 | 0 | 34177 | 34177
Engineering |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 56962 | 5% | 0 | 0 | 56962 | 53211
Procurement |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 148102 | 13% | 1217 | 17580 | 146212 | 65998
Construction |  | 168629520.27 | 100% | 5429626.78 | 2109267.84 | 0 | 63916569.57 | 78069977.79 | 854433 | 75% | 18811 | 12969 | 208117 | 334200
ROAD WORKS |  | 87969996.94 | 52.17% | 3927465.91 | 753424.85 | 0 | 52825114.99 | 55876252.92 | 186393 | 16.36% | 6915 | 1275 | 129463 | 144870
ZONE A |  | 54469012.74 | 32.3% | 3473855.41 | 574125.23 | 0 | 30294037.65 | 30553312.26 | 121795 | 10.69% | 3996 | 943 | 82886 | 93033
ZONE G |  | 33500984.21 | 19.87% | 453610.49 | 179299.62 | 0 | 22531077.33 | 25322940.66 | 64598 | 5.67% | 2918 | 334 | 46576 | 51838
Storm Water Drainage Network |  | 25407829.28 | 15.07% | 366060.85 | 949166.11 | 0 | 6330005.15 | 10306197.27 | 187421 | 16.45% | 3342 | 5382 | 36171 | 80702
ZONE A |  | 22856155.07 | 13.55% | 334539.67 | 949166.11 | 0 | 5980531.77 | 7772621.72 | 131130 | 11.51% | 2389 | 5382 | 25551 | 25084
ZONE G |  | 2551674.21 | 1.513% |  | 0 | 0 | 349473.37 | 2533575.54 | 56291 | 4.941% |  | 0 | 10620 | 55618
Sewerage Network |  | 7071026.79 | 4.193% | 82872.07 | 198690.12 | 0 | 140851.15 | 5555678.93 | 62221 | 5.462% | 1127 | 725 | 1907 | 45169
ZONE A |  | 4499744.21 | 2.668% | 58057.95 | 198690.11 | 0 | 91222.91 | 3111180.86 | 40161 | 3.525% | 725 | 726 | 1097 | 24182
ZONE G |  | 2571282.59 | 1.525% | 24814.12 | 0 | 0 | 49628.24 | 2444498.06 | 22061 | 1.936% |  | 0 | 810 | 20987
TSE Network |  | 4147696.13 | 2.46% | 0 | 114868.09 | 0 | 0 | 785149.68 | 87808 | 7.708% | 0 | 1471 | 0 | 5356
ZONE A |  | 3158469.43 | 1.873% | 0 | 114868.08 | 0 | 0 | 721661.92 | 64717 | 5.681% | 0 | 1471 | 0 | 4104
ZONE G |  | 989226.71 | 0.5866% | 0 | 0 | 0 | 0 | 63487.76 | 23091 | 2.027% | 0 | 0 | 0 | 1252
Portable Water |  | 7780467.63 | 4.614% | 0 | 63323.42 | 0 | 0 | 1697785.81 | 139722 | 12.26% | 0 | 3617 | 0 | 19877
ZONE A |  | 4936252.63 | 2.927% | 0 | 63323.42 | 0 | 0 | 476047.8 | 99650 | 8.747% | 0 | 3617 | 0 | 9191
ZONE G |  | 2844215 | 1.687% | 0 | 0 | 0 | 0 | 1221738.01 | 40072 | 3.517% | 0 | 0 | 0 | 10686
Electrical Works |  | 20111193.29 | 11.93% | 828245.36 | 29795.25 | 0 | 4075211.12 | 3324385.38 | 99033 | 8.693% | 6855 | 498 | 36171 | 32863
ZONE A |  | 13562632.1 | 8.043% | 527678.88 | 19666.98 | 0 | 2892908.57 | 2028708.9 | 63660 | 5.588% | 4197 | 323 | 26974 | 18788
ZONE G |  | 6548561.19 | 3.883% | 300566.48 | 10128.27 | 0 | 1182302.55 | 1295676.48 | 35373 | 3.105% | 2659 | 175 | 9198 | 14075
Landscape & Irrigation Works |  | 6835460.57 | 4.054% | 0 | 0 | 0 | 0 | 87510.77 | 77656 | 6.816% | 0 | 0 | 0 | 3637
ZONE A |  | 3801841.66 | 2.255% | 0 | 0 | 0 | 0 | 87510.77 | 65750 | 5.771% | 0 | 0 | 0 | 3637
ZONE G |  | 3033618.91 | 1.799% | 0 | 0 | 0 | 0 | 0 | 11907 | 1.045% | 0 | 0 | 0 | 0
CCTV Works |  | 9305849.64 | 5.519% | 224982.58 | 0 | 0 | 545387.16 | 437017.03 | 14178 | 1.245% | 570 | 0 | 4404 | 1726
ZONE A |  | 6513995.54 | 3.863% | 169352.2 | 0 | 0 | 366091.86 | 341142.34 | 7062 | 0.6199% | 334 | 0 | 2790 | 996
ZONE G |  | 2791854.1 | 1.656% | 55630.39 | 0 | 0 | 179295.3 | 95874.69 | 7116 | 0.6246% | 237 | 0 | 1614 | 730
Testing and commissioning |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 22785 | 2% | 0 | 0 | 0 | 0
Close out |  | 0 | 0% | 0 | 0 |  | 0 | 0 | 22785 | 2% | 0 | 0 | 0 | 0
0
0
0
0
| Total | 168629520.27 | 100% | 5429626.78 | 2109267.84 | 0 | 63916569.57 | 78069977.79 | 1139244 | 100% | 20028 | 30549 | 445468 | 487586
[6 empty] | 0% | 37.9% | 46.3% |  |  |  |  | 39.1% | 42.8%
[13 empty] | PW Planned | PW Actuals
[7 empty] | PW Planned | PW Actuals |  |  | Mobilization |  | 34177 | 34177
[6 empty] | Engineering | 0 | 0 |  |  | Engineering |  | 56962 | 53211
[6 empty] | Procurement | 0 | 0 |  |  | Procurement |  | 144995 | 48418
[6 empty] | Construction | 58486942.79 | 75960709.95 |  |  | Construction |  | 189306 | 321231
[6 empty] | ROAD WORKS | 48897649.08 | 55122828.07 |  |  | ROAD WORKS |  | 122548 | 143595
[6 empty] | ZONE A | 26820182.24 | 29979187.03 |  |  | ZONE A |  | 78890 | 92090
[6 empty] | ZONE G | 22077466.84 | 25143641.04 |  |  | ZONE G |  | 43658 | 51504
[6 empty] | Storm Water Drainage Network | 5963944.3 | 9357031.16 |  |  | Storm Water Drainage Network |  | 32829 | 75320
[6 empty] | ZONE A | 5645992.1 | 6823455.61 |  |  | ZONE A |  | 23162 | 19702
[6 empty] | ZONE G | 317952.2 | 2533575.54 |  |  | ZONE G |  | 9667 | 55618
[6 empty] | Sewerage Network | 57979.08 | 5356988.81 |  |  | Sewerage Network |  | 780 | 44444
[6 empty] | ZONE A | 33164.96 | 2912490.75 |  |  | ZONE A |  | 372 | 23456
[6 empty] | ZONE G | 24814.12 | 2444498.06 |  |  | ZONE G |  | 408 | 20987
[6 empty] | TSE Network | 0 | 670281.59 |  |  | TSE Network |  | 0 | 3885
[6 empty] | ZONE A | 0 | 606793.84 |  |  | ZONE A |  | 0 | 2633
[6 empty] | ZONE G | 0 | 63487.76 |  |  | ZONE G |  | 0 | 1252
[6 empty] | Portable Water | 0 | 1634462.39 |  |  | Portable Water |  | 0 | 16260
[6 empty] | ZONE A | 0 | 412724.38 |  |  | ZONE A |  | 0 | 5574
[6 empty] | ZONE G | 0 | 1221738.01 |  |  | ZONE G |  | 0 | 10686
[6 empty] | Electrical Works | 3246965.76 | 3294590.13 |  |  | Electrical Works |  | 29316 | 32365
[6 empty] | ZONE A | 2365229.69 | 2009041.92 |  |  | ZONE A |  | 22777 | 18465
[6 empty] | ZONE G | 881736.07 | 1285548.21 |  |  | ZONE G |  | 6539 | 13900
[6 empty] | Landscape & Irrigation Works | 0 | 87510.77 |  |  | Landscape & Irrigation Works |  | 0 | 3637
[6 empty] | ZONE A | 0 | 87510.77 |  |  | ZONE A |  | 0 | 3637
[6 empty] | ZONE G | 0 | 0 |  |  | ZONE G |  | 0 | 0
[6 empty] | CCTV Works | 320404.58 | 437017.03 |  |  | CCTV Works |  | 3834 | 1726
[6 empty] | ZONE A | 196739.66 | 341142.34 |  |  | ZONE A |  | 2456 | 996
[6 empty] | ZONE G | 123664.91 | 95874.69 |  |  | ZONE G |  | 1377 | 730
[6 empty] | Testing and commissioning | 0 | 0 |  |  | Testing and commissioning |  | 0 | 0
[6 empty] | Close out | 0 | 0 |  |  | Close out |  | 0 | 0
[7 empty] | 0 | 0

## Weekly Photos
WEEKLY PROGRESS PHOTOS |  | Data Date | 2026-10-12
Grading for base course layer works at MC20 Zone A | Compaction for base course layer works at MC20 Zone A
Spraying MC1 for base course works at MCD0, Zone G. | Compaction of base course layer works at MCD0, Zone G.
Concrete pouring for curbstone works at MCG0, Zone G. | Preparing for pouring concrete for curbstone works at MCG0, Zone G.
V

## Quality.
QC OBSERVATIONS CHECKLIST
2024-03-26
Project No. |  |  | SUD1-02-011 |  |  | OBS No. | [7 empty] | Inspection Day: |  | 2026-10-12
Project |  |  | Infrastructure Networks Development Project in Sudir City for Industry and Business Phase II – Part II | [6 empty] | 0 |  |  |  | Technical Development Company Egis Engineering cunsultancy
4 |  | Excellent |  | Quality Management System is being practiced and applies to MODON System | [12 empty] | 90 - 100 |  | QC Overall Score | 81.34% |  |  |  |  | 0% | 100 | 0.22883
3 |  | Good |  | Evidence of compliance with plans and procedures. | [12 empty] | 80 - 89 | [7 empty] | 0 | 89 | 0.20366
2 |  | Average |  | Indication level of compliance with standards but there is room for improvement | [12 empty] | 70 - 79 | [8 empty] | 79 | 0.18078
1 |  | Improve |  | Quality and Control is NOT being managed effectively. Needs Improvement | [12 empty] | ≤ 69 | [8 empty] | 69 | 0.15789
0 |  | N/A |  | Item was not applicable or this item was not reviewed during the inspection. | [12 empty] | Zero | [8 empty] | 100 | 0.22883
No. | Topic |  |  |  |  | E (4) | G (3) | A (2) | I (1) | N/A (0) | 0 | No. | Topic |  |  |  | E (4) | G (3) | A (2) | I (1) | N/A (0) |  |  |  |  | 437
[6 empty] | 100% | 89% | 79% | 69% | 0% | [6 empty] | 100% | 89% | 79% | 69% | 100% | 81.34%
1 | Control of Access to Site/Office | [5 empty] | 1 |  |  |  |  | 30 | QC of Excavation |  |  |  | 0 |  | 1 | 0 | 0 | 0.89 | 0.79 | [6 empty] | Item Count | Score | Distributtion
2 | Document Control Administration |  |  |  |  | 1 |  | 0 |  |  |  | 31 | QC of Roads/Round about | [5 empty] | 1 | 0 |  | 1 | 0.79 | [8 empty] | Overall | Relevant
3 | Project Documents and Progress |  |  |  |  | 1 | [5 empty] | 32 | QC of Interlock & Curbstone | [5 empty] | 0 | 0 | 1 | 1 | 1 | 4 | 58 | counts |  | 4 | Excellent | 3 | 12 | 5.263% | 8.571%
4 | Contractor's Quality Plan/CM (Updated and Reviewed) |  |  |  |  | 0 |  | 1 |  |  |  | 33 | Layers/Backfilling Sampling |  |  |  | 0 | 1 | 0 | 0 | 0 | 0.79 | 0.89 | 3 | 58 | counts |  | 3 | Good | 12 | 36 | 21.05% | 34.29%
5 | MS Log and Paperwork | [5 empty] | 1 |  |  |  |  | 34 | Pump Stations Units | [7 empty] | 1 | 0.89 | 1 | 2 | 58 | counts |  | 2 | Average | 17 | 34 | 29.82% | 48.57%
6 | RFI, FIR, & MIR Procedure | [6 empty] | 1 |  |  |  | 35 | Quality of Form Work |  |  |  |  | 0 | 1 | 0 | 0 | 0.79 | 0.79 | 1 | 58 | counts |  | 1 | Improve | 3 | 3 | 5.263% | 8.571%
7 | RFI, FIR, & MIR Inventory system | [5 empty] | 1 |  |  |  |  | 36 | Design Change List | [7 empty] | 1 | 0.89 | 1 | 0 | 58 | counts |  | 0 | N/A | 22 | 0 | 38.6% | -
8 | NCRs Control & Procedure | [5 empty] | 1 | 0 | 0 |  |  | 37 | Quality of Concrete Placing |  |  |  |  | 0 | 0 | 0 | 1 | 0.89 | 1 | [5 empty] | Total | 57 | 85 | 100% | 100%
9 | NCR Log | [6 empty] | 1 |  |  |  | 38 | Concrete Surface Finishing |  |  |  |  | 0 | 0 | 0 | 1 | 0.79 | 1
10 | MODON Standard* |  |  |  |  | 0 | 1 |  |  |  |  | 39 | Pedestals/Columns/Beams Alignment |  |  |  |  | 0 |  |  | 1 | 0.89 | 1 | [6 empty] | Maz Score Available: | 140 | <- Excludes N/A items
11 | Project Risk Plan/Management* | [6 empty] | 1 |  |  |  | 40 | Siporex Lifting & Unloading | [7 empty] | 1 | 0.79 | 1
12 | Monthly Quality Reports* | [5 empty] | 0 | 1 |  | 0 |  | 41 | Siporex Quality Pre-installation | [7 empty] | 1 | 0.79 | 1
13 | ITP | [5 empty] | 1 |  |  | 0 |  | 42 | Siporex Finishing Quality | [7 empty] | 1 | 0.89 | 1 | [5 empty] | Total Score |  | Percentage (%)
14 | MODON Weekly Report | [6 empty] | 1 | 0 |  |  | 43 | Roads / Parking Markings | [6 empty] | 0 | 1 | 0.79 | 1 |  | 58 |  |  |  | 85 |  | 60.7143 |  | %
15 | Design Change Official Paperwork* | [8 empty] | 1 |  | 44 | QC of Finishing Outdoors | [6 empty] | 0 | 1 | 0 | 1 | [5 empty] | Max Score Available | [5 empty] | 31
16 | Design Change was Applied* | [8 empty] | 1 |  | 45 | Quality of Finishing Indoors | [7 empty] | 1 | 0 | 1 | [5 empty] | 140 | [5 empty] | 32
17 | Material List |  |  |  |  | 0 | 1 |  |  | 0 |  | 46 | Stairs Quality | [7 empty] | 1 | 0.89 | 1 | [11 empty] | 33
18 | Pending Material Status | [5 empty] | 0 | 0 | 1 | 0 |  | 47 | Tanks Method Statement Work | [5 empty] | 0 | 0 | 1 | 0.69 | 1 | [11 empty] | 34
19 | Lifting Plan* |  |  |  |  | 0 | 0 | 1 |  | 0 |  | 48 | Electric Rooms | [7 empty] | 1 | 0.79 | 1 | [11 empty] | 35
20 | DWG Log | [5 empty] | 1 |  |  |  |  | 49 | QC of MCC/ATS Plant Units | [7 empty] | 1 | 0.89 | 1 | [11 empty] | 36
21 | Invoice Status |  |  |  |  | 0 | 0 |  |  | 1 |  | 50 | Qualified Subcontractor | [5 empty] | 1 |  | 0 | 0 | 0.79 | [11 empty] | 37
22 | Site Handover Letter |  |  |  |  | 1 |  |  |  | 0 |  | 51 | Scaffold/Ladders/Slope/Bridge Compliance | [7 empty] | 1 | 1 | 1 | [11 empty] | 38
23 | Material Testing Results & Certification | [5 empty] | 1 |  | 0 |  |  | 52 | Protection Applied to Completed Work |  |  |  |  | 0 | 1 | 0 | 0 | 0.89 | 0.79
24 | As Build Drawings Status* | [7 empty] | 0 | 1 |  | 53 | Storage Management in/out Control |  |  |  |  | 1 |  | 0 |  | 0 | 0.89
25 | Calibrated Lab Tools & Equipment | [5 empty] | 1 | 0 | 0 | 0 |  | 54 | Material Control | [6 empty] | 0 | 0 | 0.89 | 0
26 | Storage Inventory System | [5 empty] | 0 |  | 1 | 0 |  | 55 | Manholes Storing and Quality | [5 empty] | 1 |  |  | 0.69 | 0.79
27 | Logistics Plan | [6 empty] | 1 |  | 0 |  | 56 | Reinforced Steel Quality | [5 empty] | 0 | 0 | 1 | 0.79 | 1
28 | Project Progress Planview | [6 empty] | 1 | 0 | 0 |  | 57 | Safety Overview |  |  |  | 0 | 0 | 1 | 0 |  | 0.79 | 0.79
29 | Sufficient Number of QC Inspectors | [5 empty] | 0 |  | 1 | 0 |  | 58 | Waste Management Control |  |  |  | 0 |  | 1 |  | 0 | 0.69 | 0.79
0
Score
[8 empty] | *QC % |  |  |  | 81.34%
Prepared by: |  |  |  | Sarvar Ahmad | [7 empty] | Issued to PM: |  |  | Engr.Zyad Al Shabat
*QC Observations refer only to the practices and documentation observed at time of inspection. The responsibility of the CM and Contractor is to ensure that aspects of Quality are suitably managed. *Scores are a reflection of the general site conditions based upon the findings at the time of the walk through *If Applicable

## Quality-Stat
Quality -Stat
Quality Reports
Item |  | Issued | Closed | Pending | Avg. Closing (Days) | Pending
[6 empty] | 0-10 Days | 11-20 Days | 21-30 Days | 31-60 Days | > 60 Days
Non Conforomance Report (NCR) |  | 17 | 16 | 1 |  | 1 | [8 empty] | 34
Site Instruction (SI) |  | 6 | 5 | 1 |  | 0 | 0
Material Inspection Report (MIR) |  | 230 | 229 | 1 |  | 1
Field Inspection Request (FIR) |  | 3616 | 3558 | 58 |  | 58 | 0 | -
Shop Drawings
Item Per WBS |  |  | Total Drawings | Total Drawings Submitted |  |  | 0 | 0 | Remaining Drawings | Pending | Total Submittals
|  |  |  | A | B | C | D | Processed | with Designer | Submittals With Consultant
Road work/Structural |  |  | 130 | 28 | 102 | 0 | 0 | 130 | 0 | 0 | 130
wet network(sewer,storm,potable,irrigation) |  |  | 140 | 26 | 109 | 0 | 0 | 135 | 5 | 0 | 135
Telecom,Street light |  |  | 107 | 35 | 0 | 0 | 44 | 35 | 28 | 0 | 79
Landscape |  | Mechanical | 22 | 3 | 4 | 15 | 0 | 7 | 0 | 0 | 22
CCTV |  | Electrical | 12 | 0 | 11 | 0 | 1 | 11 | 0 | 0 | 12
TOTAL |  |  | 411 | 92 | 226 | 15 | 45 | 318 | 33 | 0 | 378
Material Approval
Item Per WBS |  |  | Total | Total Materials Submitted |  |  |  |  | Remaining to approve | Pending | Total Submittals
|  |  |  | A | B | C | D | Processed | with Designer | Submittals With Consultant
Civil /Structural /Architectural |  |  | 25 | 0 | 22 | 0 | 1 | 23 | 2 | 0 | 23 |  | 34162 | 32453.9
Mechanical |  | Mechanical | 14 | 0 | 14 | 0 | 0 | 14 | 0 | - | 14 |  | 22140 | 21033
Electrical |  | Electrical | 21 | 1 | 17 | 0 | 3 | 18 | 0 | 0 | 18 | 21 | 4500 | 4275
TOTAL |  |  | 60 | 1 | 53 | 0 | 4 | 55 | 2 | 0 | 55 |  | 51500 | 48925
Procurement Summary
Item Per WBS |  |  | Total Materials | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Actual Material on Site | Remaining Materials | Material Delivery Completion (Date)
|  |  |  | A | B | C | D | Processed
Civil /Structural /Architectural |  |  | 16 | 16 | 10 | 6 | 7 | 9 | -
Mechanical |  | Mechanical | 75 | 59 | 59 | 17 | 23 | 52 | -
Electrical |  | Electrical | 20 | 14 | 14 | 6 | 4 | 16 | -
TOTAL |  |  | 111 | 89 | 83 | 29 | 34 | 77
Consultant Quality Inspections / Observations (Weekly Basis) | [7 empty] | Overall Average | - |  | Average Closing | -
Week Number | Date of Audit | 2026-02-03 | Numbers Of Comments | Quality Score | Date Closed | Closure Duration |  | This Week Score | - |  | Average Number of Comments Per Audit | -
Note on A38: Malik, Muhammad: This refers to quality observation sheet

## HSE-Stat
Safety Statistics
Category | Item |  | This Week | This Month | Year to Date | Cumulative
Category | Total Hours Worked |  | 37020 | 61360 | 863816 | 863816
| Safe Hours Worked |  | 37020 | 61360 | 863816 | 863816
| No.of Internal Training |  | 1 | 2 | 54 | 54
No.of Internal Audit
| No. of Toolbox Talks |  | 1 | 2 | 40 | 40
Safety Awards/Incentives
[7 empty] | Category | Item | This Week | This Month | Year to Date | Cumulative
Consultant Safety Inspection (Weekly Basis) | [6 empty] | Overall Average | 80.7%
Week Number | Date of Audit | Date Issued | Numbers Of Comments | Overall Score | Date Closed | Closure Duration | This Week Score | 80.7%
Week-1 | 2026-03-03 | 2026-03-03 | 6 | 78% | 2026-03-07 | 4
Week-2 | 2026-03-10 | 2026-03-10 | 5 | 78% | 2026-03-14 | 4
Week-3 | 2026-03-17 | 2026-03-17 | 5 | 80% | 2026-03-20 | 3
Week-4 | 2026-03-24 | 2026-03-24 | 7 | 80% | 2026-03-26 | 2
Week-5 | 2026-03-31 | 2026-03-31 | 5 | 80% | 2026-04-02 | 2
Week-6 | 2026-04-07 | 2026-04-07 | 5 | 80% | 2026-04-09 | 2
Week-7 | 2026-04-14 | 2026-04-14 | 6 | 80% | 2026-04-16 | 0
Week-8 | 2026-04-21 | 2026-04-21 | 6 | 80% | 2026-04-24 | 0
Week-9 | 2026-04-21 | 2026-04-28 | 0 | 80.7% | 2026-05-02 | 0
Week-10 | 2026-06-01 | 2026-06-06 | 0 | 80.7% | 2026-06-06 | 0
Week-11 | 2026-06-09 | 2026-06-09 | 0 | 80.7% | 2026-06-09 | 0
Week-12 | 2026-06-15 | 2026-06-15 | 0 | 80.7% | 2026-06-15 | 0
Week-13 | 2026-06-22 | 2026-06-22 | 0 | 80.7% | 2026-06-22 | 0
Week-14 | 2026-06-29 | 2026-06-29 | 0 | 80.7% | 2026-06-29 | 0
Week-15 | 2026-07-06 | 2026-07-06 | 0 | 80.7% | 2026-07-06 | 0
Week-16 | 2026-07-13 | 2026-07-13 | 0 | 80.7% | 2026-07-13 | 0
Week-17 | 2026-07-20 | 2026-07-20 | 0 | 80.7% | 2026-07-20 | 0
Week-18 | 2026-07-27 | 2026-07-27 | 0 | 80.7% | 2026-07-27 | 0
Week-19 | 2026-08-03 | 2026-08-03 | 0 | 80.7% | 2026-08-03 | 0
Week-20 | 2026-08-10 | 2026-08-10 | 0 | 80.7% | 2026-08-10 | 0
Week-21 | 2026-08-17 | 2026-08-17 | 0 | 80.7% | 2026-08-17 | 0
Week-22 | 2026-08-24 | 2026-08-24 | 0 | 80.7% | 2026-08-24 | 0
Week-23 | 2026-08-31 | 2026-08-31 | 0 | 80.7% | 2026-08-31 | 0
Week-24 | 2026-09-07 | 2026-09-07 | 0 | 80.7% | 2026-09-07 | 0
Week-25 | 2026-09-14 | 2026-09-14 | 0 | 80.7% | 2026-09-14 | 0
Week-26 | 2026-09-21 | 2026-09-21 | 0 | 80.7% | 2026-09-21 | 0
Week-27 | 2026-09-28 | 2026-09-28 | 0 | 80.7% | 2026-09-28 | 0
Week-28 | 2026-10-05 | 2026-10-05 | 0 | 80.7% | 2026-10-05 | 0
Week-29 | 2026-10-12 | 2026-10-12 | 0 | 80.7% | 2026-10-12 | 0

## HSE.
MODON HSE Site Inspection Report
Date |  |  | 2026-10-12 |  |  |  |  | Inspected By: |  |  | Engr Ayman Sabry
Project ID. |  |  | SUD1-02-011 |  |  |  |  | Report No. |  |  |  |  | MODON PM Name |  | Engr.Ziyad Al Shabbat
Project Name: |  |  | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two |  |  |  |  | Contractor: | TECHNICAL DEVELOPMENT CONTRACTING CO. |  |  |  |  | Safety Performance |  | 2 |  |  | 81.82%
Inspections are a snapshot in time and refer only to the practices and documentation observed at the time of the Inspection. It remains the responsibility of the Consultant and Contractor to ensure that all aspects of Health & Safety are suitably managed.
1 |  | Good Practice |  |  | 2 | Need Improvement |  |  |  |  | 3 | Fail (Life Threatening Activity) / Comliance with Plan & Procedures |  | N/A | Atcitty Not Applicable for this Site Inspection Report
No. | Topic | [5 empty] | Wt. | HSE Compliance |  | No. | Topic | [5 empty] | Wt. | HSE Compliance
1 | Access and Egress - (General access to site, segregated from vehicles, / Overhead protection, while entering into the building /Adequate lighting provided when dark or overnight work) | [5 empty] | 5% | 2 |  | 14 | Work at Height - (PPE/Fall Protection(Same level, above and blow) / Training / Fall restraint / competency /Safe access & egress to and from work at height / Ladders / Openings (floor/shafts/Provision of emergency rescue) | [5 empty] | 5% | N/A |  |  |  | 1 | 100 | 1
2 | Traffic Management - (Loading/unloading/sheeting/temp. routes/speed/parking/competence) | [5 empty] | 3% | 2 |  | 15 | Scaffolding - (Temp. Scaffolding Work-platform (All types) - qualified scaffolder / Inspection / Tagged / Safe Access/egress / PTW/Falsework & Formwork) | [5 empty] | 4% | N/A |  |  |  | 2 | 75 | 2
3 | Site Signage - (Project Notice Board & General Signage) | [5 empty] | 2% | 2 |  | 16 | Mobile Elevated Work platform (MEWP) - (PTW/competence requirements/conditions/inspections/tagged/training/Full-body harness) | [5 empty] | 4% | N/A |  |  |  | 3 | 0 | 3
4 | PPE Compliance - (Use, storage, stock, handling & checks - Head, Foot, Eye, Hearing) | [5 empty] | 5% | 2 |  | 17 | Excavation & Trenches - (PTW/Edge protection/buffer zone/Slope/Benching/Shoring/Geo-tech report/Atmospheric hazards/Acess&egress/Emergency management / MS&RA/H.E) | [5 empty] | 3% | 2 | [5 empty] | N/A
5 | Housekeeping - (Material correctly stored/Rubbish cleaned & removed daily/slips & trips hazards) | [5 empty] | 3% | 2 |  | 18 | Confined Space - (PTW/Training/competence/Emergency Management/MS & RA/Safe access/egress) | [5 empty] | 5% | 2
6 | Storage of Materials - (Transporting, storage, training and use - Combustible / Flammable / Hazardous substances (COSHH) | [6 empty] | 1 |  | 19 | Fire Protection - (Flammable/Oxy. LPG /Combustible separated/FE's/Flashback arrestor/Sparks & slags/Smoking area/PTW/Generators/MS & RA/Emergency Management) | [6 empty] | 2 |  | Red | Serious injury or death (immediately)
7 | Site Waste Management - (Hazardous waste /Combustible waste / Human waste / Construction waste - asphalt, cable, timber, paving roof sheeting tiles, plastic & bricks) | [6 empty] | 1 |  | 20 | Health & Welfare - (Adequate drinking water/shaded - eating & rest area/washing & sanitary facilities/Certified FA/FA Box & Stock/adequate toilets/Ambulance) | [6 empty] | 2 |  | Yellow | Minor or near miss (3 days to comply)
8 | Health Surveillance - (Expose to excessive noise/vibration/dust/silica/CO/cement/radiation/extreme weather condition) | [5 empty] | 3% | 1 |  | 21 | Environmental Incident Measures - (Spill/ Leakage / Concrete wash / vehicle & eqpts. wash / waste disposal/Sewers and drains/emissions/Emergency Management/Training/site run-off water) | [5 empty] | 5% | 2 |  | Green | No issues
9 | Electrical Safety - (Electrical qualified /RCD/GFCI/Industrial Cocket/LOTO/Cable-overhung or buried/Cords in good condition/current inspection tag) | [5 empty] | 5% | 1 |  | 22 | HSE Communications & Meetings - (Schedule HSE Meetings/Safety Committee meetings/Alerts / Lesson learned/Safety Bulletin contains latest HSE KPI) | [5 empty] | 5% | 2
10 | Tools & Equipment - (Includes, powered, hydraulic & pneumatic/Guards in place/Properly stored/RCD Protection/Earthed/Good condition & tagged) | [5 empty] | 3% | 1 |  | 23 | HSE Plan & Associated Procedures - (Approved updated HSE Plan/ CEMP/HAZComm/Procedures/Standards/Project Safety Risk Register) | [5 empty] | 3% | 2 |  | 26 points > 4 minors then is it’s a serious issue
11 | Manual Handling - (Lifting/loading/pulling/pushing/twisting/awkward posture/repetitive task/frequent and prolong physical effort/Reasonable practicable use of mechanical aid) | [5 empty] | 3% | 1 |  | 24 | Health, Safety & Environment Incident reporting - (Review of HSE Statistics, Reporting of Unsafe Act & Conditions/ Reporting of Near Miss incident/Reporting of FA cases/Record MT cases) | [5 empty] | 3% | 2
12 | Vehicle and mobile equipment / Plant - (dumpers; excavators, cranes, piling rigs, grader, roller, loaders/condition/KSA License/certification) | [5 empty] | 5% | 2 |  | 25 | HSE Awareness, Training & Competence - (Policy /Objective & targets/Information, training/Climatic condition awareness/Reponses in emergency situation/ Safety Behavior Observation) | [5 empty] | 4% | 2
13 | Lifting Operations & Rigging - (Lifting Plan/Lifting devices & gears/PTW/Condition/3rd party certification/bank-man/rigger/slingers/man-basket/inspection record/tagged) | [6 empty] | N/A |  | 26 | Project Leadership Site Tours - (Provide evidence of proactive safety performance/Deficient discovered discussed/Positive feedback/Workers resolving safety issues) | [6 empty] | 2
Prepared by: |  |  |  | Abdul kalim | [5 empty] | Sent to MODON PM: |  |  |  | Engr.Ziyad Al Shabbat
Safety Results
1 |  | 6 |  |  |  | 2 |  | 16 |  |  |  | 3 | 0
Note on C13: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Safe access / egress for people to their work area 2 - Safe access / egress for construction vehicles 3 - Access properly restricted-site fencing provided and maintained 4 - Access proper and not blocked 5 - Safe access is available for rescue operation 6 - Storage access / exit are clearly marked and unobstructed 8 - Access and egress is in good condition, hand holds, ladder etc. are sound and in place 9 - Ensure unauthorized public access is prevented 11 - Site assembled ladders or make-shift tables for access are forbidden on site. 13 - Use proper bridges, walkways or gangways to access or cross trenches or an excavation area 14 - Surrounding areas are cleared and barricaded and access restricted to all unauthorized trades while crane in operation 15 - To ensure early access to accredited medical / rehabilitation services 16 - Parking vehicles on site access roads causing obstruction 17 - All personnel will be instructed that access to firefighting equipment must remain clear at all times 18 - Access control gates to be locked out of hours 19 - Site access gates to be designed and located to, where possible, avoid clashes with external hazards / activities
Note on T13: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Personal Fall Arrest System; 1 - Is the suitable harness harnesses is provided 2 - Are shock absorbing lanyard with 2 locking snap hooks. 3 - Is anchorage point strong enough and can support 5,000 Ibs. 4 - Do inspection checklist is being implemented before use. 5 - Is the emergency plan for rescue in place Personal Fall Restraint System; 1 - The fall restraint equipment should be set and adjusted so there is no free fall over the edge. 2 - A harness or body belt may be used 3 - The anchorage point must support 4 times the intended load. Positioning System; 1 - Is a suitable harness or body belt provided 2 - Is there a not more than 2' free fall maintained 3 - Is the anchorage point capable of supporting 2 times the intended load or 3.000 Ibs, whichever is greater 4 - Is 100% tie-off (protection from falls at all times, even when moving from point to point) provided while using personal fall protection with two lanyards Fall Protection System; 1 - Suitable edge protection and work platforms are to be provided to prevent a fall occurring 2 - Where the provision of edge protection or adequate platforms cannot be provided safety nets or other soft-landing systems such as inflatable bags are to be used to minimize the consequences of a fall. 3 - If nets are used, they must be installed by a competent rigger and fitted as close under the work surface as possible. 4 - Areas below roof works are to be cordoned off and properly signed to prevent personnel being injured from falling materials 5 - If access onto the roof cannot be avoided, edge protection is to be installed 6 - Floor and wall openings are to be protected using covers of adequate strength to withstand the expected load that will be imposed and securely fixed. 7 - Penetrations in walls such as those provided for lift shafts, door openings, etc. are to be closed with suitable strength material or have fixed protective barriers around the penetration with a sign warning personnel of the danger of falling.
Note on C14: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are arrival and departure of vehicles and delivery accompany by security department? 2 - Are proper loading, unloading and securing loads, being properly controlled? 3 - Is the proper sheeting & coupling in place when transporting and disposing material to and from site? 4 - Is the parking to the designated parking lot and in reverse order? 5 - Is the designated speed limit adhered on workplace? 6 - Provision of ramps, traffic signs, cones, barriers, demarcation posts and tape, flashing lights and any other traffic control devices. 7 - Do visiting drivers are being inducted at the workplace, prior to enter on the workplace? 8 - Are visiting drivers restricted to dangerous areas, e.g. moving to and from they vehicles to washrooms, lavatory & offices etc.? 9 - Do drivers observe site rules and procedures, for delivery, loading and unloading? 10 - Are the areas wide enough for the safe movement of large vehicles (including visiting vehicles)? 11 - Does drivers are competent, hold valid local driving license and competent training? 12 - Ensure the vehicle and trailers have their brakes applied and all stabilizers properly positioned before beginning loading or unloading?
Note on T14: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Base soundness, load adequately spread (base plate jacks, base plate on firm ground). 2 - Line of standard (vertical) and ledger (horizontal) secure and plumb. 3 - Spacing of transoms on platforms, support for Scaff boards, boards are not over protruded and boards are secured. 4 - Staggering of joints vertical and horizontal. 5 - Guardrail / fall protection. (Top rail – Min.1mtr, Mid rail – 470mm from floor and Toe boards – Minimum150mm) 6 - Longitude and bracing on standards and ledgers. 7 - If close to structure, ties must be on lift below to top working platform and every 3m, load bearing couplers used or tie with certified anchor bolts (eye bolts). 8 - Clamps and tubes used are of correct fittings, size and free from defects. 9 - Tubes & fittings free from defects / deformation. 10 - Safe and proper access available to the working platform. 11 - Scaff tags signed, displayed and up to date. 12 - If close to slab edge/opening scaffold tied and secured to structure correctly.
Note on C15: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a Project Notice Board - (showing HSE Statistics / Safety alerts / lesson learned)? 2 - Is there prominent safety boards that are depicting the mandatory PPE on the workplace? 3 - Are other safety required signs are prominently installed on the workplace in relevant to their work-task, as following: > Hazardous Substances - e.g. respiratory protection Sign > Working at Height - e.g. Full body Harness Sign > Working UG - e.g. Full body Harness, SCBA, Ventilation, PTW Signage etc. > Working with Electrical - e.g. Leather Gloves, Goggles, Face shield, Electric shock proof helmet & shoes > Working with Chemicals - Signage = e.g. Impermeable gloves/clothing's, long sleeves, Goggles 4 - General Site Safety Signs: > Prohibition Sign = (e.g., ‘no access for unauthorized persons’). > Warning Signs = (e.g., ‘danger: electricity’) > Mandatory Signs = e.g., ‘eye protection must be worn’) > Emergency Escape or First Aid Sign = e.g., ‘emergency exit/escape route’) > Safety Color Signs = (e.g., yellow means ‘be careful’ or ‘take precautions’) > Illuminated Signs = (e.g., many emergency exit signs) > Acoustic Signals =( e.g., fire alarm) > Fire safety sign > Supplementary Signs = "This way"
Note on T15: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Man-Lift operators are to be competent and trained to operate the specific Man-Lift by examination and hold a current approved certificate / license from an approved and internationally recognized source (TUV, SGS etc. 1 - All Man-Lifts shall be inspected by a 3rd party on an annual basis. 2 - All Man-Lifts shall display a sticker corresponding to the 3rd party inspection certificate. 3 - The manufacturer's instruction manual must be on site for each and every type of Man-Lift in use. 4- A pre-start daily operator inspection of the equipment will be performed and documented on a daily basis as per the manufacturer's instructions. The user is responsible for ensuring this has occurred. 5 - The use of a Man-Lift as, or in lieu of, a Crane is strictly prohibited. Man-Lifts are to be used only for lifting personnel and small tools within the designed Safe Working Load. 6 - The platform is not to be loaded in excess of the designed working load; the safe working load of the platform is to be clearly displayed on both the platform, and body of the equipment. 7 - All persons inside work platforms shall wear a full-body harness attached to the designated anchor point. Personnel must stand on the floor of the working platform; standing on the handrails is strictly prohibited. Harnesses must not be attached to other structures outside of the working platform. 8 - Personnel must stay inside the working platform at all times; the platform must not be used as an access to structures. The use of staging or ladders to extend height is strictly forbidden. 9 - Securing the boom or work platform to any structure is strictly prohibited. The boom or working platform must not be rested upon on any structure, nor is the Man-Lift to be used as a jack/ prop or tie to support other structures. 10 - All Man-Lifts must be equipped with a 5kg (10lb) fire extinguisher. 11 - No man-lifts are to be operated that have had safety devices removed or disabled. Daily operator inspections are to include the testing of these devices (limit switches, alarms and hazard flashing beacons). 12 - Specific Man-Lifts are fitted with outriggers and/or stabilizers which must be used as per manufacturer's instructions. 13 - The work area surrounding the man-lift is to be cordoned off using barricades and signage if the area is used by other workers or vehicles. A full traffic management plan is required for all works involving man-lifts when working on highways. Under no circumstances is any part of a man-lift to extend or swing into a line of traffic.
Note on C16: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Does required mandatory PPE (refer specification BS, EN & ANSI) is provided, as following? > Safety helmet (see below for color scheme) > Safety glasses (shaded for outdoor work and clear inside structures and during non-daylight hours) > Safety boots (safety shoes are prohibited) > Orange hi-visibility vest 2 - Additional PPE shall be provided to a specific task 3 - Do specific PPE is provided according to their job requirement? > To work at height - Full Body harness / Fall arrest Devices / Fall Restraint Devices / V & H Lifeline etc. > To work in the confined space - Full Bodyarness, Tripod with retractable lifeline, SCBA, Masks etc. > 4 - Are the PPE stored appropriately to prevent deformation or distortion? 5 - Has self assessment being carried out for in according to the work requirements? 6 - EYEWEAR (Glasses/Goggles/Face Shields) > Eyewear cleaning supplies available. > Safety glasses in good condition and lenses free of scratches. > Goggles adjustment strap not cracked or frayed, not deformed, or lenses not > Face shields in good condition, including adjustment band, and free of scratches or 7 - HEAD PROTECTION > Hard hat bill and suspension attached as allowed by manufacturer. > is pliable, free of dents, cracks, nicks, or any damage due to impact. > Suspension maintained at 1.25 inches from inside of shell. > Suspension free of cuts or fraying, torn headband, adjustment strap workable. > Electrical hard hat matched to hazard classification. > Dated to determine whether within manufacturer’s allowable 5-year use time period. 8 - HAND PROTECTION > Available in sizes matched to employee. > Gloves free of rips tears, abrasions, or holes. > Matched to manufacturer’s specification for chemicals used onsite. > Electrical gloves matched to hazard and periodically inspected for insulating rating. > Maintained in a clean and sanitary condition, decontaminated or disposed properly. 9 - BODY PROTECTION > Available in sizes matched to employee. > Maintained in a clean and sanitary condition, decontaminated or disposed properly. > Vapor-tight fully encapsulated suits tested at required periodic intervals. > Flame-resistant clothing matched to electrical hazard and arc flash rating. > Welding gear matched to degree of hazard and free of cuts, tears or burn holes. > Flotation gear available for work near or on water and in good condition. 10 - HOT AND COLD BODY PROTECTION > Cooling gear available based on degree of heat stress hazard. > Cooling gear in operable, clean, and sanitary condition. > Cold-weather gear provided based on needs assessment. > Cold-weather gear available in sizes to match employees. > Cold-weather gear is in free of tears, rips, or holes and in maintained in a clean condition. 11 - TRAINING > Initial PPE training completed by employees. > Training conducted when new types or styles of PPE are issued. > PPE selection, use, and maintenance reviewed at daily safety briefings. 12 - Provision of impermeable clothing appropriate for the work being performed? 13 - Wearing of shorts, sleeveless shirts, loose clothing are prohibited across the MODON Projects. 14 - Clothing contaminated with grease, oils, fuels and other hazardous substances is not to be worn.
Note on T16: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a valid Excavation PTW in place? 2 - Are spoils, materials, and equipment set back at least 1.5 meters from the edge of the excavation? 3 - Are walkways and bridges over excavations structurally sound, minimum 0.5 meter in width and equipped with standard guard rails and toe boards? 4 - Are warning systems established and used when mobile equipment is operating near the edge of an excavation? 5 - Are employees prohibited from working on the faces of sloped or benched excavations above other employees? 6 - Are the exact locations of Utilities (piping, electrical, etc.) clearly marked? 7 - Are underground installations protected, supported, or removed when an excavation is open? 8 - Are ladders or other means of access and egress in place as per the PTW requirements? 9 - Are all workers within 7.6 meters of a means of access and egress to a trench? 10 - Are ALL ramps constructed of materials of uniform thickness, cleated together, equipped with no-slip surfaces? 11 - Are employees protected from cave-ins when entering or exiting excavation? 12 - Are precautions taken to protect employees from water accumulation and dewatering is being carried out? 13 - Is surface water or runoff diverted after every rainstorm or other hazard-increasing occurrence? 14 - Is the excavation classified as a confined space? If so, is their a valid confined space PTW and is the atmosphere being tested when there is a reasonable possibility of an oxygen-deficient, oxygen-enriched, combustible, toxic, or other harmful contaminant? 15 - Have materials and/or equipment chosen for shoring been based upon soils analysis, trench depth and expected loads (as per Excavation PTW)? 16 - Are shoring materials and equipment that are used for protective systems inspected and in good condition? 17 - Are damaged shoring materials and equipment immediately removed from service? 18 - Are damaged shoring materials and equipment inspected by a Registered Professional Engineer after repairs are made and before being placed back in service? 19 - Are protective systems installed without exposing employees to hazards of cave-ins, collapses, or threat of being struck by materials or equipment? 20 - Are ALL members of support systems securely fastened together to prevent failure? 21 - Are support systems provided to insure stability of adjacent structures, buildings, roadways, sidewalks, etc.? 22 - Are excavations below the level of the base or footing supported, and approved by a Registered Professional Engineer? 23 - Does back-filling progress with the removal of the support system? 24 - Is a shield system installed to prevent lateral movement? 25 - Are employees prohibited from remaining in a shield system during vertical movement?
Note on C17: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Sites are to be kept clean and tidy and free from slip, trip and fall hazards. 2 - Do all personnel trained in the importance of good housekeeping, managers, supervisors undertake regular monitoring and inspection of the workplace? 3 - Workplace are to be left clean and tidy at the end of each shift and where there is an accumulation of materials throughout the shift, at regular intervals as required to maintain a clean and safe site. 4 - Buildings under construction and nearing completion must ensure that all combustible and flammable materials are removed at the end of each shift. 5 - Nails are to be removed from timber as soon as possible, where this is not practical they are to be flattened and placed in a safe area (barrier and signs) until nails can be removed at a later time. 6 - Materials are to be stored so as they do not pose a risk to personnel stacking, removing or walking by (further guidance is given in the materials storage and handling section). 7 - All spills are to be cleaned up immediately using absorbent material. 8 - Cables/hoses/other trailing leads are to be protected, buried or secured above head height to avoid a slip trip, fall hazard. 9 - Waste is to be placed in designated containers and covered to protect against high winds, pests or risk of fire. Waste containers are to be emptied on a regular basis to prevent a build-up of material. 10 - Loose or light materials that are stored on roofs or open spaces are to be secured to prevent them from inclement weather. Location: 1 - Receptacles located inside buildings shall be kept at least 18 inches away from combustible walls and partitions. 2 - Receptacles for combustible trash that are located outside of buildings shall be placed at least 15 feet from the building or combustible material. Use: 1 - Cigarettes, cigar butts, matches, and similar potential ignition sources should never be placed in a trash receptacle. Proper receptacles for such items should be provided in areas designated for smoking. 2 - Broken glass, empty jars, scrap metal, and similar construction material should never be placed in office trash containers. A roll-off bin or other appropriate container should be used to hold construction debris. Environmental: 1 - Container storage areas shall be kept clean and free of trash. Improper disposal of food waste can attract pests and vermin. Prevention methods that do not involve the use of toxic chemicals is the preferred method of pest control. 2 - Outdoor containers should be kept covered when not in use so as to avoid attracting pests and to prevent the entry of water. Dripping or leaking trash containers may violate local storm water quality discharge regulations. 3 - Promote recycling by contracting with a waste removal company that provides reuse as part of the waste processing or by providing segregated bins for the collection of office paper, aluminum cans, plastic bottles, and toner cartridges. Rinse empty cans and bottles of sugar-based soda so as not to attract ants and other pests. 4 - Proper lighting (indoor) or during Night Shift are provided. Accurately installed. No impairement or poor visibilty is generated. No shadow due to installation of lights are presents.
Note on T17: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Permit is taken for confined space entry and all recommended precautions are in place. 2 - Operatives are trained and fit for the specified job. 3 - Confined space is well ventilated by means of mechanical ventilation. (Exhaust fan, blowers, low velocity air hose etc.). 4 - Rescue system (Tripod with hoisting device, Rescue Harness etc.) in place and sufficient trained persons are available for the rescue operation. 5 - Safe access is available for rescue operation. (Manhole size - Min. 450 mm X 407 mm or 457 mm Dia.) 6 - Atmospheric monitoring conducted and confined space is safe to enter. Percentage of gas concentration will be monitored and recorded every 4 hrs. A. Oxygen percentage. (Permissible limit – 19.5% to 23.5%) B. Flammable gas or vapors.(Permissible limit - <10% of LFL) C. Carbon Monoxide. (Permissible limit - <50ppm) D. Hydrogen sulfide.(Permissible limit - <10ppm) E. Any other toxic gas or vapors. _______________________________ 7 - Minimum two persons shall be assigned to work in the confined space. One person will remain in the entrance at all times to monitor the work 8 - All persons shall wear safety harness, which should be connected to safety line from outside at all times. 9 - All electrical equipment & leads are free from damage and guards in place. 10 - All electrical tools & equipment are connected through ELCB. 11 - Compressed gas cylinders are kept outside the confined space. 12 - supervisor / Foreman will be available at all time to monitor the work and for the rescue operation. 13 - Tool box talk conducted for the entire team and they are well aware of the risks. 14 - Proper communication system is available in between persons inside and standby person. 15 - Trained First aider with first aid kit will be available when working in the confined space. 16 - Confined space entry register is available and shift records will be maintained. -
Note on C18: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Combustible: 1 - Ensure oily rags, combustible material and other flammable substances which may ignite are not accumulated and that they are removed without delay to the designated disposal / storage area. 2 - Combustible materials shall not be stored within 20 feet (6.1 meters) of compressed gas cylinders. 3 - Safety cans used for dispensing combustible liquids shall be kept at a point of use 4 - Storage rooms for combustible liquids must have explosion-proof light fixtures 5 - No flames - hot work or smoking is be permitted in combustible liquid storage areas. Flammable: 1 - Adequate training in the use and storage of flammable liquids is in place. 2 - Storage of Flammable liquids in accordance with NFPA approved flammable storage lockers or in low value structures at least 50 feet from any other structure. 3 - Do not store other combustible materials near flammable storage areas 4 - Bulk drums of flammable liquids must be grounded and bonded to containers during dispensing 5 - Portable containers of gasoline or diesel are not to exceed 5 gallons 6 - Safety cans used for dispensing flammable liquids shall be kept at a point of use 7 - Appropriate fire extinguishers are to be mounted within 75 feet of outside areas containing flammable liquids, and within 10 feet of any inside storage area for such materials. 8 - Storage rooms for flammable liquids must have explosion-proof light fixtures 9 - No flames - hot work or smoking is be permitted in flammable or combustible liquid storage areas. 10 - Flammable liquid transfer areas are to be separated from other operations by distance or by construction having proper fire resistance. 11 - When not in use flammable liquids shall be kept in covered containers. 12 - Flammable materials are considered hazardous and as such, material safety data sheets and appropriate hazard communication training for affected employees is required 13 - Maintain high levels of housekeeping, particularly with relations to flammable materials. 14 - Where flammable materials are handled in the course of work, safe work procedures must be prepared and documented with reference made to the Material Safety Data Sheets (MSDS‘s) for the materials concerned. 15 - All people handling, working with or in control of flammable substances must be properly trained and supervised (documentation to be maintained). 16 - Lead, dust, fumes and vapor constitute a major health hazard to workers. Hazardous Substances COSHH 1 - Under COSHH the risk presented by any hazardous substance assessed using hierarchy of control, stored, transported, created or disposed and usage at the workplace; > Very toxic or toxic: Substances that, in low quantities, cause death or acute or chronic damage to health when inhaled, swallowed or absorbed via the skin > Harmful: Substances that may cause death or acute or chronic damage to health when inhaled, swallowed or absorbed via the skin > Corrosive: Substances that may, on contact with living tissues, destroy them > inhalation into the lungs, when the substance is in the form of a gas, vapor, fume, mist, aerosol or dust > absorption through the skin or eyes by contact with a substance that can penetrate unbroken skin, or is absorbed through unprotected cuts or grazes > injection by contact with contaminated sharp objects or high-pressure equipment, e.g. water jetting > ingestion by swallowing particles of a hazardous substance resulting from hand-to- mouth transfer
Note on T18: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are regular and frequent fire safety inspections carried out? 2 - Have a sufficient number of fire marshals/evacuation officers been appointed? 3 - Are water supplies adequate? 4 - Does the building or site have a written fire procedure? 5 - Is there an effective permit to work system in operation for all hot work and other fire related work? 6 - Do all doors from areas from which a large number of people may have to escape open in the direction of travel? 7 - Do all emergency exit doors (i.e. doors not in normal use) have clear instructions displayed on how to open? 8 - Are all escape routes clear and unobstructed? 9 - Are all fire exit doors correctly signed? 10 - Is all fire fighting equipment immediately visible or correctly signed? 11 - Are all flammable and explosive substances adequately signed to indicate their presence and danger? 12 - Where necessary, is there a sufficient number of emergency lights to adequately illuminate all internal escape routes, exit doors and signs? 13 - Where automatic fire detection is deemed to be necessary is there an adequate number of detectors in the critical areas? 14 - Where the means of raising the alarm is by hand-operated devices, can the operation of one device be heard throughout the entire building or site? 15 - Is there an adequate number of fire extinguishers in the building? 16 - Is there firefighting equipment other than extinguishers in the building? 17 - Are all electrical circuits and fixed electrical installations examined and tested at an acceptable frequency? 18 - Is housekeeping to an acceptable standard? 19 - Have all staff been trained in fire procedures in the last twelve months? 20 - Are all fire drills adequately recorded?
Note on C19: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - General construction waste streams generated including; > Asphalt, cable, timber, paving, roof sheeting, tiles, plastic sheeting and brickwork. > Excess concrete, spoil material from excavations. > General waste, such as putrescible food scraps and packaging from workers. > General (food) waste, construction/concrete waste, hazardous waste, paper/cardboard and waste water/sewage. 2 - Are hazardous waste identified with hazardous Waste label. 3 - Containers are properly labeled in according to their contents. 4 - Container inspections are documented in writing using the Container Inspection Checklist. 5 - Weekly inspections logged into book using the Accumulation Area Inspection Log Sheet. “NO SMOKING OR OPEN FLAME” sign posted. 6 Disposal facilities identified, evaluated using the procedures. 7 - Disposal facility accepted waste and issue approval letter. 8 - Waste transfer/dispose tracked using Waste Tracking Form. 9 - Waste streams, such as asphalt and concrete, to be recycled should be segregated and separately stored. 10 - Spill Release Contingency: 1 - Prior to beginning operations, ensure that on-site spill response capabilities (containment and personal protective equipment) are consistent with task requirements described in job hazard analysis.
Note on T19: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: HHE is required at all locations where chemical hazards exist, such as; storing, transferring and handling facilities, under routine conditions. The HHE scope shall include the physical, chemical, radiological, and biological health hazards. Physical health hazards include elevated noise and vibration exposures, repetitive motion work operations, ionizing and non-ionizing radiation exposures heat and cold stress and biological hazards include infectious disease agents. HHE shall be performed before the site mobilization; 1 - Is the adequate eating or mess area is provided and sufficient for number of workers? 2 - Are sufficient tables and Chair are provide and Kept Clean? 3 - Are FEs, signs, pest control being implemented? 4 - Is washing Area sufficient and Kept Clean? 5- Cooking Area Kept Clean? 6 - L.P.G. Cylinder stored outside, secured & upright 7 - Sufficient drinking water provided. Filters changed (as per manufacturer recommendation)? 8 - Sufficient toilets, washbasins, cleaned/disinfectant provided? 9 - Provision of First Aider 10 - Provision of Nurse 11 - Provision of First Aid Kit 12 - Provision of site clinic with required first aid equipment and items. 13 - Provision of shaded area on the workplace 14 - Provision of Ambulance or an equal arrangement in place" 15 - Smoking area is Prohibited other than designated smoking areas, clear of flammable and combustible materials? 16 - All toilets, washing, rest and eating facilities to be kept clean, hygienic and be well maintained at all times? 17 - Waste Management - Covered bins, emptied daily, close proximity, color coded etc.? 18 - Are the monitoring, including integrated air sampling, noise dosimetry and other exposure assessments, being carried out? 19 - Are the Physical, chemical, and biological stresses, being identified, results are taken with action level to prevent sickness, impaired health, significant discomfort, or inefficiency in workers? 20 - Are WEL, LEL, OEL PEL & TLV linked to control workers airborne exposure to a chemical in a concentration above which is likely to cause death or immediate or delayed permanent adverse health effects or prevent escape from such an environment, if bening implemented?
Note on C20: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Is the hierarchy of Control is beng carried out on the following and recorded; 1 - Exposure to Chemical; e.g. - Dust, Gas, Mist, Vapor 2 - Exposure to Radiation; e.g. - Pipe radiography etc. 3 - Exposure to Biological Hazard; e.g. - Bloodborne pathogens / Legionella / Leptospirosis 4 - Exposure to noise; e.g. Loss of hearing / Physical damage to hearing mechanism 5 - Heat and cold stress work; e.g. - Heat-stroke, Heat stress / Frostbite / 6 - Repetitive Motion Work; e.g. - Musculoskeletal disorder, awkward position etc. 7 - Is the risk assessment carried out on the hazardous material and covering the following; > Allowable exposure limits, > Exposure monitoring requirements, > Methods of compliance for potential over exposure conditions, > Medical surveillance program, > Hazard communication, employee training requirements, 8- Is the IH Surveillance Plan should being implemented and have rocored on the following; > Which exposure groups require IH monitoring and medical surveillance > Specific substances or agents to be monitored, > The OELs to be used to evaluate results > The statistical basis to continue or cease monitoring > Specific medical testing/protocol to be implemented 9 - Do we've program on identifies work conditions such as the following, the exposure must first be mitigated or work shall not be performed. > Oxygen concentrations less than 19.5% or greater than 23.5%, or > Atmospheres greater than 1% of the Lower Explosive Limit, or > Atmospheres that are >50% of Immediately Dangerous to Life or Health (IDLH) concentrations, or > Work with sensitizers or known human carcinogens, mutagens, or teratogens without process isolation or fully encapsulating personal protection, or > Work with highly infectious biological agents without process isolation
Note on T20: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are all dispensing areas diked or properly graded to control drainage of spilled fuel? 2 - are all workers and operatives are trained to use spill response kit? 3 - Is the procedure in place for collecting and/or containing, and disposing of spilled materials? 4 - All tanks & vessels areas are diked to contain accidental spills?. 5 - Do measures taken to prevent an accidental contaminated runoff from construction , operation, maintenance, plant and storage areas? 6 - Do measures taken to control on deposits of oils, greases and fuels, from site plant and vehicle operations, mechanical failures, spillages and discharges to ground or drains and the dispersion of unattended spills by plant / vehicle movements?. 7 - Do measures taken to control on fuels, oils and other hazardous chemicals spilled on site during re-fueling, storage or transport operations?. 8 - Do we have an Emergency Response Procedure will be followed in the event of environmental emergency such as an oil or chemical spill? 9 - Is there a procedure for concrete wash, clean and dispose to prevent ground contamination, such as; Concrete wash pits with leak proof sedimentation tanks will be provided for washing concrete mixer trucks. The design and location of such wash pits shall be agreed with the Project Manager prior to its construction on site. Concrete dumping or spillages of any kind shall not be allowed in any other location on site? 10 - Is there a procedure to used in the situation of a major spills that will have an impact on the surrounding environment will be promptly reported to the Fire Brigade? 11 - Are there a procedure of disposing off any damage/leakage drums or containers shall be removed in accordance with the local requirements? 12 - Are there a procedure of dealing with spilled contaminated soils, resulted and remediated, accordingly? 13 - Are all personnel trained in the use of spill procedure and response and the adequate spill kits are available on site?
Note on C21: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - All electrical extension cords are equipped with nonconductive plugs 2 - Cords must not be spliced or draped over nails, metal objects 3 - The use of extension cords by means of multiple outlet plugs from single outlets is prohibited 4 - All electrical service removals, alterations and equipment installations are performed by an authorized electrician 5 - Faulty electrical installation 6 - Electrical supply disruption 7 - Exposed cables 8 - Trip / fall hazards from installed cables 9 - Fire hazard Electrical overload 10 - electrocution 11 - Electrical (short circuit) - Contact with exposed conductors or a device that is incorrectly or inadvertently grounded, such as when a metal ladder comes into contact with power lines 12 - Electrical - (static discharge) 13 - Electrical Fire - Use of electrical power that results in electrical overheating or arcing to the point of combustion or ignition of flammables, or electrical component damage 14 - Improper grounding 15 - Damaged insulation 16 - Exposed electrical parts 17 - Overloaded circuits 18 - Inadequate wiring 19 - Wet conditions 20 - Overhead power lines 21 - Damaged tools and equipment
Note on T21: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a meaningful and an effective consultation and communication on health and safety matters being implemented through out the project? 2 - Is the Consultation and communication on health and safety matters in place through the following mechanisms: > Project specific induction - (prior to commencement of contracted work) > Work activity Induction (in SWMS or equivalent) - (prior to commencement any construction work) > Toolbox Meetings - (Monthly intervals or generally when there is the introduction of a new process (SWMS) or when discussing OHS issues/topics). > Subcontractor Meetings - (weekly) > Project team meetings - (weekly) > HSE Committee Meeting - (as agreed with the HSE Committee) > OHS Report - (monthly) > Project Notice Board and general signage - (as required) 3 - Is there a method of communication is to be established in the work procedures to allow constant monitoring of those persons working in the confined space? 4 - Is there a material safety data sheets and appropriate hazard communication training for affected employees is in place? 5 - Are all environmental aspects and impacts been communicated to employees? 6 - Dose the notice
Note on C22: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1- Check that all the workers are using safe hand tools/power tools and instruct them to operate and maintain the same in safe manner 2 - Ensure power tools and hand tools are checked prior to issue 3 - Damaged tools and equipment 4 - Electrical tools or electrical equipment are not to be issued for use until inspected. 5 - Electrical tools or electrical equipment are not to be issued for use until inspected. 6 - "Defective" electrical tools and equipment are to be tagged and removed from service until repaired and inspected 7 - The frequency for inspection of construction electrical tools and electrical equipment shall be monthly and inspection indicated by attached color-coded tape or color- coded tie wraps and a color coded inspection tag with Contractor‘s name, the supervisor, the inspection date, equipment number and signature of competent inspector displayed on the tag. 8 - Checking the cords for worn or cracked insulation. 9 - Checking the cords entry to plug and tool housing for frayed or worn insulation and strain relief. 10 - Checking the plug prongs for damage. 11 - Checking the plug for exposed connectors 12 - Checking the equipment housing for damage. 13 - Checking trigger locks to ensure they have been removed 14 - Checking the leads for signs of wear, poor connections at probes, etc. 15 - Checking the housing and the readout window for cracks, loose screws, etc. 16 - Check all Ground Fault Circuit Interrupters (GFCI) during the monthly inspections. 17 - Machines are free from any defects / damage. 18 - Pressure switch and safety guards in place where applicable. 19 - Leads are fitted with correct plugs & sockets and free from damages. 20 - Leads wires are free from joints, cuts and other defects. 21 - Leads are suitably rated for the electric current. 22 - Machines / Tools are equipped with properly functioning dead man switch. 23 - Tools issue and maintenance record is properly maintained. 24 - Tools are correctly stored. 25 - Discarded Tools / cords are marked and stored separately.
Note on T22: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is the Project HSE Plan presents actions, responsibilities, protocol, conformance, verification and containment activities to be undertaken by project staff and sub-contractors at all times during the construction phase of the project. 2 - Is the implementation of the HSE plan is being monitored, evaluated for accuracy and any changes made communicated to all relevant personnel. 3 - Is the HSE Plan, CEMP, Security Plan, HAZcomm., standards & procedures are updated, signed, approved and distributed, acknowledged to the construction team's responsible individuals? 4 -Is the project overall safety risk register developed, approved and being implemented?
Note on C23: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Immediate Postural and Load Factor; 1- Is the body position stable? 2 - Is the trunk of the body straight (not twisted)? 3 - Is the operation carried out by one person? 4 - Is the load kept close to the body? 5 - Can the handler avoid stretching upwards? 6 - Can the handler avoid a prolonged period in one posture? 7 - Can the handler perform the task without overreaching? 8 - Are both hands used for grasping? 9 - Are the hands less than a shoulder width apart? 10 - Is the load positioned centrally in front of the body? 11 - Is the load reasonably symmetrical? 12 - Is the load stable and easy to grasp? 13 - Can handlers move and position themselves freely? Environmental Risk Factor; 1 - Too hot? 2 - Too cold? 3 - Too bright? 4 - Too dark? 5 - Too noisy to allow effective communication? 6 - Too wet? 7 - Slippery underfoot? 8 - Does any personal protective equipment interfere with the task? Carrying; 1 - Is the load carried at knuckle height? 2 - Is the load carried at arm's length from the body? 3 - Is the load carried for more than 10 meters? Seated Work; 1 - Is the load lifted from below thigh height? 2 - Is the load lifted to above shoulder height? 3 - Is the load lifted at arm's length from the body? 4 - Does the handler have to twist significantly to the side? 5 - Is the load heavier than 5kg? Pushing and Pulling; 1 - Does the pushing and pulling take place below knuckle height? 2 - Does the pushing and pulling take place above shoulder height? 3 - Is the initial or maximum force required to push or pull the load more than 25kg? 4 - Is the continuous force required to keep the load in motion more than 10kg?
Note on T23: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a system of proper HSE reporting in place, such as; all work-related incidents including near misses, injuries, illnesses, property damage, environmental incidents, security events and motor vehicle incidents, using proper protocol followed? 2 - Is the HSE incidents, accident, near misses, unsafe acts/conditions and dangerous occurrences are being reporting in timely manner and in the approved company format? 3 - Are the workers informed, trained in reporting all near misses, unsafe acts/conditions to the appropriate authority or line of manager? 4 - Is the Weekly / Monthly HSE Statistics data, including (leading & lagging) indicators, reviewed by the senior management?
Note on C24: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: CHECKS; 1 - Plant guarding is in place and in good condition to prevent injury from parts disintegrating or failing 2 - Access and egress is in good condition, hand holds, ladder etc. are sound and in place 3 - Operator's seat and controls are in good condition and all safety devices (limiters and indicators) are labelled and fully operational. 4 - Operator's manual / instructions supplied by the manufacturer of the plant are available in the plant. 5 - Hazards with the use of the plant are identified, i.e. Safe working limits on batters, operator safety instructions etc., are displayed clearly in the cabin of the plant for operator reference. I.E. PLANT SPECIFIC RISK ASSESSMENT. 6 - Hazard controls, i.e. seat belts must be worn and hearing protection must be worn, caution/danger signs (counter weight slewing area, excavators and cranes) etc. are displayed in the cabin or on the plant in a position relevant to the hazard. 7 - Operator cabin/work platform access is clean and free of debris, loose tools, equipment, grease oil and is in an orderly condition. 8 - Plant is clean and free from oil leaks and oil build up. 9 - Plant Pre Start inspection is complete and a record of the inspection will be provided at commencement on the site. 10 - Certification of operator / proof of competency. 11 - Operational Noise Level - Statement of conforming emission level. 12 - Plant has no areas of excessive wear or damage. Mobile plant required to have; 1 - Plant is fitted with a Roll Over Protection Structure (R.O.P.S.) and operator restraint. 2 - Plant is fitted with a front horn and reversing beeper. 3 - Plant is fitted with a rotating or flashing amber beacon. Plant used to lift Material and equipment; Backhoes, excavators, cranes and loaders used as crane from designed lifting points. The Safe Working Load of the plant item is displayed on the plant as: EITHER; A Crane Chart supplied by the manufacturer specific to the plant item in the cabin of the plant for operator reference OR; The Safe Working Load of the equipment on the boom of the loader bucket and of the dipper arm of excavators - a combination of both is required for backhoes e.g. SWL 1.2ton. Personal Lifting Equipment - (Cherry Pickers, boom lift and elevated platform) 1 - Safety Working Load is displayed on work bucket / platform. 2 - Fully body harnesses and lanyards are to be provided for personnel using the equipment. 3 - Safety Instruction for the operation of the equipment is clearly displayed in the work bucket / platform. 4 - The supplier have provided training for personnel using the platform in the safe use of the equipment
Note on T24: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Do all personnel have the correct information, instruction and training according to their role and responsibilities? 2 - Is the contractor promoting awareness of company standards and regulations among their employees on a regular basis, or when it is necessary? 3 - Do all personnel have completed basic relevant awareness training, such as; Fire Awareness Training, Heat Stress awareness Training, Safety Signs and Color Code awareness Training, Environmental Awareness Training, Using Fire Extinguisher Awareness Training, Emergency reporting Awareness Training, Unsafe Act/Conditions reporting awareness training, Evacuation Procedure Awareness Training?
Note on C25: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Crane Inspected 2 - Operator certified 3 - Lift Plan approved 4 - PTW obtained 5 - lifting equipment is suitable for the use it is being put to, marked with safe working load, properly maintained and inspected, and receives a periodic thorough examination. 6 - Are all members of the lifting operations team including the Appointed Person, Crane Drivers and Slingers / Signalers / Banksmen will be competent and have such practical and theoretical knowledge and experience as is necessary to carry out their duties. 7 - Bank man is available and certified 8 - The crane operator have a practical and theoretical knowledge of lifting operations 9 - Lifting operations will be undertaken by a minimum of three competent people the crane operator, slinger / signaler (slinger and signaler can be one person) / banks man / flagman (banks man and flagmen can be one person) and Supervisor 10 - Certification of Lifting Equipment / Lifting Gear / Lifting Devices 11 - Lifting plan prepared/approved/communicated 12 - Lifting gear (Chain sling, shackle, webbing sling, lifting clamps etc.) / devices (Chain block, Winch, Monorail etc.) are checked, inspected & tagged - ( size, length, dia, width, SWL,Condition & defects. 13 - All lifting equipment / gears have valid test certificates and are in good condition.
Note on T25: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there process of SBO for leadership to identify and reinforce safe work practices/behaviors? 2 - Is there process of SBO for leadership to identify and improve on at-risk practices? 3 - Is there process of SBO for leadership to identify and improve on practices, conditions, controls, and compliance that eliminate or reduce hazards? 4 - Is there a process of SBO for leadership to make positive, corrective, cooperative, collaborative feedback/recommendations? 5 - Is there a training program for BBST, that how to identify critical safety behavior and how to provide feedback and the number of personnel trained. 6 - Is there a program for the leadership to carry out SBO once a month or twice (depends project scope of work), and record available?

## Major Quantities
MAJOR QUANTITIES Delivered
BOQ Number | Description of Item | Total Quantity | Unit of Measurement | Plan To Date | Actual To Date Delivered | Excecuted on site | Remaining Total Delivery | Variance
33 31 00 | GRP Pipes | 18337 | m | 16000 | 17437 | 16000 | 900 | 900 | 95.09% | 2337
33 05 39 | Manholes | 251 | m | 150 | 221 | 210 | 30 | 30 | 88.05% | 41
33 42.1 | UPVC Pipes | 4716 | m | 5500 | 4716 | 1000 | 0 | 0 | 100%
33 42.1 | Fire Hydrants | 90 | Unit | 20 | 90 | 1 | 0 | 0 | 100%
33 05 39 | Catch Basins | 295 | Unit | 150 | 295 | 116 | 0 | 0 | 100%
33 42.1 | HDPE Pipes | 28557 | m | 26000 | 28557 | 5500 | 0 | 0 | 100%
26 05 13.16 | Medium Voltage Cables | 51500 | m | 0 | 0 | 0 | 51500 | 51500 | 0%
26 56 19 | Street Lighting Poles | 592 | Unit | 0 | 1 | 0 | 591 | 591 | 0.1689%
26 05 19 | Low Voltage Cables | 68400 | m | 5000 | 68400 | 0 | 0 | 0 | 100%
26 11 16 | Unit Substation | 5 | Unit | 0 | 0 | 0 | 5 | 5 | 0%
26 24 16 | Street Lighting Panels | 52 | Unit | 0 | 0 | 0 | 52 | 52 | 0%
33 14 19 | Valves | 218 | Unit | 100 | 215 | 10 | 3 | 3 | 98.62%
26 11 16.02 | RMU ( Ring main unit ) | 11 | Unit | 5 | 6 | 0 | 5 | 5 | 54.55%
26 13 00.01 | NOP | 6 | Unit | 6 | 6 | 0 | 0 | 0 | 100%
23521

## CCO
CONTRACT CHANGE ORDER (CCO)
CCO No. | Date Added | Description of Change | Status | SR | Sch Impact (Months) | Date Approved | Duration (days)
- | - | - | - | - | - | - | -
8%

## Invoice Log
Weekly Progress Report - Invoice Log | [32 empty] | Y
Project Value | [9 empty] | Payment Status | [7 empty] | Invoices Summary | [9 empty] | Average Invoices durations |  |  |  |  | N
Original Contract Value |  |  |  | 168629520 |  | O&M Value |  | 0 |  | Advance Payment % |  | 10% |  | Advance Payment (SAR) |  | 16862952 |  | No of Submitted Invoices |  | 4 |  | Submitted Invoices (SAR) |  | 24575402.47 |  | Submiited Invoice Peroid |  | CM / PgM Average Approval duration |  | 0 | Average Invoice Value | 0
Revised Contract Value |  |  |  | 0 |  | Revised O&M Value |  | 0 |  | Retention % |  | 0% |  | Retention (SAR) |  | 0 |  | No of Approved Invoices (CM) |  | 0 |  | Approved Invoices (CM) (SAR) |  | 0 |  |  |  | MODON PM & Accounts Average Approval duration |  | 0
Estimate At Completion Value |  |  |  | 168629520 |  | Submitted Invoices (Gross Value) |  | 24575402.47 |  | Penalties and deduction % |  | -1.478% |  | AP Recovery (SAR) |  | -2457540.247 |  | No of Approved Invoices (PM) |  | 0 |  | Approved Invoices (PM) (SAR) |  | 0 |  | Invoice Submitted Compared to Contract Value | #DIV/0! | Payments Average Duration |  | 0
Potential Changes |  |  |  | 0 |  | Total Deduction |  | -2491540.247 |  | Penalties and deduction (SAR) |  | -34000 |  | Retention Cumulative (SAR) |  | 0 |  | No of Paid Invoices |  | 0 |  | Paid Invoices (SAR) |  | 0 |  |  |  | Invoices Average total Duration
Invoice Reference |  |  |  | Invoice Value |  |  |  |  | Period Covered |  |  | CM / PgM Approval Timeline |  |  |  | Modon PM & Accounts Approval | [6 empty] | Payment Status |  |  |  |  | Total Invoice Duration | Remarks
# | Invoice No. | Doc Control reference | Submittal Rev. # | Gross Value | AP Recovery | Retention | VAT 5%/15% | Deduction / Penalties | Amount (net) | Start Date | End Date | Date to CM / PgM | CM / PgM Approval (Yes/No) | CM / PgM Reply Date | Days Elapsed | Date to PM | PM Approval (Yes/No) | PM Reply Date | Date to Accounts | Accounts Approval (Yes/No) | Accounts Approval Date | Days Elapsed | Date Paid | Amount Paid | Paid % | Payment Period (d) | Amount Pending
1 | 1 | SUD1-02-011-TDC-TS9-1-IPC-0001-00 |  | 6935961.18 | -693596.118 |  | 936354.76 | -27000 | 7151719.822 | 2026-01-06 | 2026-06-28
2 | 2 | SUD1-02-011-TDC-TS9-1-IPC-0002-00 |  | 5943128.46 | -594312.846 |  | 802322.34 | 0 | 6151137.954 | 2026-06-29 | 2026-07-29
3 | 3 | SUD1-02-011-TDC-TS9-1-IPC-0003-00 |  | 3894723.74 | -389472.374 |  | 525787.71 | -1000 | 4030039.076 | 2026-06-30 | 2026-08-31
4 | 4 | SUD1-02-011-TDC-TS9-1-IPC-0004-00 |  | 7801589.09 | -780158.909 |  | 1053214.53 | -6000 | 8068644.711 | 2026-09-01 | 2026-09-30
5
6
7
8
9
10 | [20 empty] | 0.08 | 0.08 |  |  |  | -0.08
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
|  |  | TOTAL | 24575402.47 | -2457540.247 | 0 |  | -34000 | 25401541.563 | [14 empty] | 0 |  |  | 0
Note on J3: Without O&M Cost

## Issues
[12 empty] | 2026-10-12 | Status | Responsibility
[13 empty] | Open | Contractor
[13 empty] | Closed | Consultant
Modon
Third Party
Other
Issue Log
Issue ID | Parent Project ID | Contract / Project ID | Project Name | City | Region | Fund Source | Phase | PM / Owner | Contractor / Designer | Current Status | Value (SAR) | Category | Issue Title | Description | Evidence / Data | Severity (1-5) | Urgency (1-5) | Priority Score | Priority | Action Required | Date Raised | Status | Expected/Actual Closure | Duration Elapsed | Target Date | Resolution / Updates | Source | Column1
3120 - 1 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Finishing | Egis / MODON | Technical Development Company for Contracting | Closed |  |  |  | Soil is presently scattered on the road surface. | [5 empty] | Install temporary physical hard barricades, warning tape, and clear hazard signage. | 2026-09-08 | Closed | 2 | 1 | 2026-09-08
3120 - 2 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Finishing | Egis / MODON | Technical Development Company for Contracting | Closed |  |  |  | Collected unused barriers on-site and placed them around the existing excavation. | [5 empty] | Bobcat sweeper was deployed to remove fine soil from the road surface to eliminate dust and skid hazards. | 2026-09-09 | Closed | 2 | 1 | 2026-09-09
3120 - 3 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Finishing | Egis / MODON | Technical Development Company for Contracting | Closed |  |  |  | Observed workers non complaince with site mandatory PPE | [5 empty] | GOOD PRACTICE | 2026-09-09 | Closed | 2 | 1 | 2026-09-09
3120 - 4 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Finishing | Egis / MODON | Technical Development Company for Contracting | Closed |  |  |  | Found conrete pouring activities in night without sufficient lighting. | [5 empty] | PPE provided and conduct awareness session | 2026-09-17 | Closed | 2 | 1 | 2026-09-17
3120 - 5 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Finishing | Egis / MODON | Technical Development Company for Contracting | Closed |  |  |  | Discovered an excavation without the required signage. | [5 empty] | Tower lights has been provided and engineer has been informed of the requirements | 2026-09-18 | Closed | 2 | 1 | 2026-09-18
3120 - 6 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Finishing | Egis / MODON | Technical Development Company for Contracting | Closed |  |  |  | observe excavation existing utilities without proper supervision | [5 empty] | Provide supervison to the excavation team to continous evaluate the working conditions and guide the team of control measures | 2026-09-27 | Closed | 2 | 1 | 2026-09-27
3120 - 7 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Finishing | Egis / MODON | Technical Development Company for Contracting | Closed |  |  |  | Found operators unaware of the risk of underground utilities | [5 empty] | An Awareness session was conducted with operators working in utilties contained areas | 2026-09-28 | Closed | 2 | 1 | 2026-09-28
3120 - 8 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Finishing | Egis / MODON | Technical Development Company for Contracting | Closed |  |  |  | observe excavation without proper sloping or benching | [5 empty] | Provide sloping, benching and shoring with edge protection | 2026-10-01 | Closed | 2 | 1 | 2026-10-01
3120 - 9 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Finishing | Egis / MODON | Technical Development Company for Contracting | Closed |  |  |  | Found Equipment Operator unaware of MEPI and Equipment Safety Training | [5 empty] | An Awareness session was conducted with operators and inspection of equipment was insured | 2026-10-01 | Closed | 2 | 1 | 2026-10-01
3120 - 10 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Finishing | Egis / MODON | Technical Development Company for Contracting | Closed |  |  |  | observe excavation not backfilled for long time with improper sloping | [5 empty] | Backfilling of excavated tenches and provide sloping, benching and shoring with edge protection | 2026-10-11 | Closed | 2 | 1 | 2026-10-11
3120 - 11 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Finishing | Egis / MODON | Technical Development Company for Contracting | Closed |  |  |  | Observe unleved roads with no dust control | [5 empty] | Level the roads with regular grading and water spraying of vehicles routes. | 2026-10-11 | Closed | 2 | 1 | 2026-10-11

## Risk Register
Risk Log
Risk ID | Parent Project ID | Contract / Project ID | Project Name | City | Region | Fund Source | Phase | PM / Owner | Contractor / Designer | Current Status | Value (SAR) | Category | Risk Title | Description | Evidence / Data | Probability (1-5) | Impact (1-5) | Score | Rating | Response | Mitigation Plan | Date Identified | Status | Target Date | Notes / Updates | Source
3120 - 1 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Testing & Commissioning | Egis / MODON | Technical Development Company for Contracting | Close |  | Authorities / Permits | MV System | There is no electricity service delivery agreement between the Modon and the electricity company | TDC Wont be able to suubmit any sort of documents for material approval |  |  |  | H16 | Client/ Contractor |  | 2026-03-30 | Close | 2026-03-31 | Coordination between all stakholders (Client / Electricity Company and Contractor ) so we can execute our process
3120 - 2 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Finishing | Egis / MODON | Technical Development Company for Contracting | Close |  | Interface / Communication | International Issue (War and Conflicts) | Affecting time and cost | The ongoing Conflict during this peiord is affecting the deilvery of the material like GRP which is risking time and cost |  |  |  | M12 | Contractor |  | 2026-04-01 | Close | 2026-04-02 | Should find alternative solution to this serious issue
3120 - 3 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Finishing | Egis / MODON | Technical Development Company for Contracting | Close |  | Safety / Quality | Found an excavation area that requires immediate barricading. | Accidental falls, unauthorized entry, and structural collapse. | Serious injuries or death |  |  |  | H16 | Contractor |  | 2026-08-01 | Close | 2026-08-03 | Isolating the hazard zone, installing rigid physical barriers, and displaying clear warning signage
3120 - 4 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Finishing | Egis / MODON | Technical Development Company for Contracting | Close |  | Safety / Quality | Found soil debris on the road from dump trucks. | Soil and debris spilled from dump trucks onto public roads create severe driving hazards, including sudden loss of traction, cracked windshields from flying rocks, and dangerous swerving maneuvers. | Vehicle damage, and environmental risks |  |  |  | L4 | Contractor |  | 2026-08-01 | Close | 2026-08-01 | When soil debris from construction dump trucks falls onto public roads, authorities Enforce immediate site cleanup, issue warning letter to drivers, and mandate preventive transport controls
3120 - 5 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Finishing | Egis / MODON | Technical Development Company for Contracting | Close |  | Safety / Quality | Observed an excavation in the area without the required barricade. | Accidental falls, equipment rollovers, and site fatalities. | Fatal falls, structural collapses, and heavy legal penalties. |  |  |  | H16 | HSE team/Construction Team |  | 2026-09-08 | Close | 2026-09-08 | Stop any nearby hazardous work and immediately secure the area with hard barricades and warning signs to prevent falls and unauthorized entry.
3120 - 6 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Finishing | Egis / MODON | Technical Development Company for Contracting | Close |  | Safety / Quality | An oil leak was observed from the equipment. | Serious risks to worker safety, environmental health, and machine performance | Severe safety hazards, environmental damage, equipment failure, and costly operational downtime. |  |  |  | H16 | Operator/Maintenance team/HSE team |  | 2026-09-07 | Close | 2026-09-07 | Initiate a swift and structured Spill Response and Corrective Maintenance Procedure.
3120 - 7 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Finishing | Egis / MODON | Technical Development Company for Contracting | Close |  | Safety / Quality | Observed workers non complaince with site mandatory PPE | Non complaince with site mandatory requirements and physical injuries to workers, low visibility and reputational damage | Body injuries, penalties |  |  |  | M12 | HSE team |  | 2026-09-17 | Close | 2026-09-17 | Stop any workers with non complaince and provide PPE and replace the damage PPE.
3120 - 8 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Finishing | Egis / MODON | Technical Development Company for Contracting | Close |  | Safety / Quality | Found conrete pouring activities in night without sufficient lighting. | Serious risks to worker safety and quality of work | Risk to get personal injuries of workers due low visibility and low quality of work due poor illumination. |  |  |  | H16 | Construction team/HSE team |  | 2026-09-18 | Close | 2026-09-07 | Provide sufficient lighting inform lighting tower during night shift activities.
3120 - 9 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Testing & Commissioning | Egis / MODON | Technical Development Company for Contracting | Open – Confirmation Pending | 6835460.61 | Interface/Utilities | Pending Substation Location Confirmation Affecting MV Cable Design and Energization | The final substation location is currently pending confirmation between the Client and SEC. The Contractor has already raised an RFI regarding the MV cable size, and the response was received following SEC approval of the MV drawing. Although the cable-size issue has been addressed and the MV cables have been procured, final confirmation of the substation location and associated power-generation interface is still required to complete the MV system coordination and enable energization. Any continued delay may affect testing, energization and ultimately the planned handover milestone. | RFI Ref. SUD1-02-011-TDC-TS9-1-ELE-RFI-0004-00, submitted 04-Feb-2026 and approval/response received 09-Feb-2026 following SEC approval of the MV Drawing. MV cables have been procured. Contractor is proactively progressing road-crossing ducts for MV cables at its own risk. Final substation location and power-generation interface remain pending. | 5 | 5 | #REF! | H16 | Mitigate | Expedite formal confirmation of the final substation location between Client and SEC. Continue close interface coordination with Client/SEC and obtain formal confirmation to avoid further design changes. Proceed with preparatory works such as MV cable road-crossing ducts where technically feasible and authorized. Maintain readiness for immediate submission of any revised/final MV cable drawings following location confirmation. Coordinate testing, power-generation interface and energization requirements in advance to minimize downstream impact. Closely monitor the remaining activities against the handover milestone and develop a recovery/acceleration plan if required. |  | Monitoring | Required date for substation location confirmation | Project is currently ahead of schedule. Contractor has already addressed the MV cable-size clarification through RFI Ref. SUD1-02-011-TDC-TS9-1-ELE-RFI-0004-00, submitted on 04-Feb-2026 and responded/approved on 09-Feb-2026 following SEC approval. MV cables have been procured and road-crossing duct works are being progressed at Contractor's own risk. However, final substation location and power-generation/energization requirements remain subject to confirmation between Client and SEC. Continued delay may consume available float and potentially impact energization and handover. | RFI Ref. SUD1-02-011-TDC-TS9-1-ELE-RFI-0004-00; SEC-approved MV Drawing; Client/SEC correspondence; MV Cable Procurement Records; Site Progress Records; Interface Meeting Minutes; Project Schedule
3120 - 10 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Finishing | Egis / MODON | Technical Development Company for Contracting | Open – Approval Pending | 10128939.86 | Design/Technical | Delay in Landscape Proposal / Shop Drawing Approval Affecting Procurement and Installation | The landscape proposal has been submitted by the Contractor and is currently awaiting Client approval. The approval is required to proceed with finalization of the landscape shop drawings and related material procurement. Any delay in approval may affect subsequent procurement, installation and finishing activities and could consume the available schedule float | SUD1-02-011-TDC-TS9-1-ROD-RFI-0036-00 / 23-Aug-2026 | 3 | 4 | #REF! | M12 | Mitigate | Expedite Client/Consultant review and approval of the landscape proposal. Maintain regular follow-up until approval is obtained. Prepare shop drawing details in parallel where possible to minimize turnaround time. Identify long-lead materials and prepare procurement actions in advance. Upon approval, prioritize shop drawing submission, material procurement and installation to avoid consuming available float. |  | Monitoring | Required approval date | Project is currently ahead of schedule. However, prolonged approval of the landscape proposal may affect shop drawing finalization, material procurement and installation activities and may consume available float. | Landscape Proposal Submission / Shop Drawing Register / Procurement Log / Project Schedule
3120 - 11 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Finishing | Egis / MODON | Technical Development Company for Contracting | Close |  | Safety / Quality | observe excavation existing utilities without proper supervision | Non complaince with continous supervision by working near utilities could expose the utilities struck by the equipement and utilities could be damage and services could be interupted. | property damages, services interuption and penalties |  |  |  | H16 | Site Team/HSE Team | Provide supervison to the excavation team to continous evaluate the working conditions and guide the team of control measures | 2026-09-27 | Close | 2026-09-27 | Provide supervison to the excavation team to continous evaluate the working conditions and guide the team of control measures
3120 - 12 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Finishing | Egis / MODON | Technical Development Company for Contracting | Close |  | Safety / Quality | Found operators unaware of the risk of underground utilities | Serious risks to worker of being electrocuted and could damage the utilities | Risk to get personal injuries of workers due low visibility and low quality of work due poor illumination. |  |  |  | H16 | Site Team/HSE Team | An Awareness session was conducted with operators working in utilties contained areas | 2026-09-27 | Close | 2026-09-27 | An Awareness session was conducted with operators working in utilties contained areas
3120 - 13 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Finishing | Egis / MODON | Technical Development Company for Contracting | Close |  | Safety / Quality | observe excavation without proper sloping or benching | The critical risk of excavation collapse due loose soil condition, viberation and equipmen movement. | Severe Injuries and Fatalities to workers inside the trenches |  |  |  | H16 | Site ConstructionTeam/HSE Team | Provide sloping, benching and shoring with edge protection | 0/10/2026 | Close | 0/10/2026 | Provide sloping, benching and shoring with edge protection
3120 - 14 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Finishing | Egis / MODON | Technical Development Company for Contracting | Close |  | Safety / Quality | Found Equipment Operator unaware of MEPI and Equipment Safety Training | Risk of struck and hit by equipment, equipment collision and failures. | serious injuries to workers on ground, fatalities and property damages |  |  |  | H16 | Site ConstructionTeam/HSE Team | An Awareness session was conducted with operators and inspection of equipment was insured | 2026-10-01 | Close | 2026-10-01 | An Awareness session was conducted with operators and inspection of equipment was insured
3120 - 15 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Finishing | Egis / MODON | Technical Development Company for Contracting | Close |  | Safety / Quality | observe excavation not backfilled for long time with improper sloping | The critical risk of excavation collapse due deterioration of loose soil, viberation and equipmen movement. | Severe Injuries and Fatalities to workers inside the trenches |  |  |  | H16 | Site ConstructionTeam/HSE Team | Backfilling of excavated tenches and provide sloping, benching and shoring with edge protection | 2026-10-01 | Close | 2026-10-02 | Backfilling of excavated tenches and provide sloping, benching and shoring with edge protection
3120 - 16 | 3120 | SUD1-02-011 | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two | Sudair | Riyadh Region | Government Funded | Construction / Finishing | Egis / MODON | Technical Development Company for Contracting | Close |  | Safety / Quality | Observe unleved roads with no dust control | Risk of vehicles damages and workers exposures to the site dust. | Property damage and Respiratory issues to the workers. |  |  |  | H16 | Site ConstructionTeam/HSE Team | Level the roads with regular grading and water spraying of vehicles routes. | 2026-10-01 | Close | 2026-10-02 | Level the roads with regular grading and water spraying of vehicles routes.

## Invoice Amount FIR
INVOICE AMOUNT FIR |  |  |  | 168629520
SL. | date of FIR | TOTAL AMOUNT | Total Amount % (as per FIR)
1 | 2026-06-28 | 6935961.18 | 4.113%
2 | 2026-07-29 | 5943128.46 | 3.524%
3 | 2026-08-31 | 3894723.74 | 2.31%
4 | 2026-09-30 | 7801589.09 | 4.626%
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19

## Manpower
Head-Count ( Non Manual)
MONTHS | 2026-01-06 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31
Plan - Monthly | 0 | 25 | 24 | 26 | 29 | 30 | 28 | 32 | 24 | 28 | 26 | 22 | 18 | 21 | 20 | 19 | 21 | 18 | 15
Planned - Cumulative | 0 | 25 | 49 | 75 | 104 | 134 | 162 | 194 | 218 | 246 | 272 | 294 | 312 | 333 | 353 | 372 | 393 | 411 | 426
Actual - Monthly | 11 | 29 | 28 | 42 | 53 | 56 | 57 | 61 | 53 | 58
Actual Cumulative | 11 | 40 | 68 | 110 | 163 | 219 | 276 | 337 | 390 | 448
Forecast - Monthly
Saudi Monthly - Actual
Head-Count (Manual)
MONTHS | 2026-01-06 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31
Plan - Monthly | 99.3038 | 169.35 | 75.3308 | 94.2192 | 159.8654 | 267 | 261.6308 | 286.7846 | 340.7462 | 326.7154 | 365.4962 | 279.1923 | 241.2346 | 214.7115 | 216.3692 | 102.6692 | 122.7962 | 292.7269 | 12.8923
Planned - Cumulative | 99.3038 | 268.6538 | 343.9846 | 438.2038 | 598.0692 | 865.0692 | 1126.7 | 1413.4846 | 1754.2308 | 2080.9462 | 2446.4423 | 2725.6346 | 2966.8692 | 3181.5808 | 3397.95 | 3500.6192 | 3623.4154 | 3916.1423 | 3929.0346
Actual - Monthly | 32 | 148 | 199 | 321 | 405 | 400 | 395 | 377 | 547 | 558
Actual Cumulative | 32 | 180 | 379 | 700 | 1105 | 1505 | 1900 | 2277 | 2824 | 3382
Forecast - Monthly
Saudi - Actual
Head-Count (Non-Manual) | [25 empty] | Month |  | 2026-10-31 | 2026-11-30
Planned | Actual |  | Variance |  | Forecast Next Month |  | Saudi Staff
35 | 58 |  | 23 |  | 0 |  | 4
Head-Count (Manual) | [10 empty] | Man Power by Trade
Planned | Actual |  | Variance |  | Forecast Next Month |  | Saudi Staff |  |  |  | Key Trade |  | Engineer |  | Doc. Controller |  | Proc. Team |  | Foreman | Draftman | Driver | UnSkilled Labor | Skiled labour | Others | Total
300 | 558 |  | 258 |  | 0 |  | 6 |  |  |  | Plan |  | 15 |  | 2 |  | 3 |  | 9 | 2 | 135 | 41 | 42 | 51 | 300
[11 empty] | Actual |  | 18 |  | 3 |  | 3 |  | 19 | 2 | 321 | 90 | 92 | 63 | 611
Equipment
MONTHS | 2026-01-06 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31
Plan - Monthly | 0 | 20 | 44 | 50 | 65.0854 | 228 | 220 | 205 | 190 | 150 | 110 | 80.4462 | 57.8731 | 18.9577 | 10.4962 | 4.9231 | 11.1231 | 27.2721 | 0.59712
Planned - Cumulative | 0 | 20 | 64 | 114 | 179.0854 | 407.0854 | 627.0854 | 832.0854 | 1022.0854 | 1172.0854 | 1282.0854 | 1362.5316 | 1420.4047 | 1439.3623 | 1449.8585 | 1454.7816 | 1465.9047 | 1493.1768 | 1493.7739
Actual - Monthly | 0 | 35 | 111 | 241 | 260 | 320 | 326 | 225 | 326 | 326
Actual Cumulative | 0 | 35 | 146 | 387 | 647 | 967 | 1293 | 1518 | 1844 | 2170
Forecast - Monthly
Equipment Count
Planned | Actual |  | Idle |  | Variance |  | Forecast Next Month
200 | 326 | 150 | 0 |  | 126 |  | 0
Type | PICK UP/Car | Fork lift | Bus | Dumper | Dump Truck | Grader | Boom Truck |  | Generator + Tower Light |  | JCB |  | Water Tank |  | CRANE |  | Showel |  | Tyre ROLLER | Excavator/Poclain | Lowbed Trailer | Forklift | BOBCAT | Bulldozer | Diesel Tank | Dyna | Grader | Total
Plan | 7 |  | 4 |  | 70 |  | 2 |  | 4 |  | 4 |  | 13 |  | 2 |  | 17 |  | 17 | 19 | 1 | 1 | 2 | 15 | 4 | 1 | 17 | 200
Actual | 12 |  | 6 |  | 158 |  | 5 |  | 5 |  | 9 |  | 15 |  | 1 |  | 20 |  | 20 | 20 | 1 | 3 | 6 | 20 | 3 | 2 | 20 | 326
Idle

## FIR Summary
| Project Name |  | Infrastructure Network Development Project in Sudair City for Industry and Business - Phase Two - Part Two
| Project ID |  | SUD1-02-011 |  | Project Budget | 168629520
| Date Pariod |  | Start Date | 2026-01-06 | To | Data Date | 2026-10-12
SL No | BOQ Item # | BOQ Description | Date | FIR # | FIR Description | Unit Rate as per BOQ | Current Pariod Quantity | % Claim | Unit Rate as per claim | Total (SR)
|  | Description | [7 empty] | 29518302.4886
1 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-01 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0008-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Road # MCE0, STA: 0+500 to STA: 0+610 | 22.31 | 721.03 | 100% | 22.31 | 16086.1793
2 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-02 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0009-01 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Road # MCG0, STA: 0+580 to STA: 0+740 | 22.31 | 1448.15 | 100% | 22.31 | 32308.2265
3 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-07 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0011-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Road # MCE0, STA: 0+710 to STA: 0+860 | 22.31 | 1500.26 | 100% | 22.31 | 33470.8006
4 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-09 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0013-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Road # MCE0, STA: 0+500 to STA: 0+600 | 22.31 | 836.86 | 100% | 22.31 | 18670.3466
5 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-09 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0014-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Road # MCG0, STA: 0+380 to STA: 0+480 | 22.31 | 2433.38 | 100% | 22.31 | 54288.7078
6 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-11 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0015-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Road # MCE0, STA: 0+600 to STA: 0+710 | 22.31 | 1362.19 | 100% | 22.31 | 30390.4589
7 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-13 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0016-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Road # MCF0, STA: 0+230 to STA: 0+350 | 22.31 | 1995.27 | 100% | 22.31 | 44514.4737
8 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-16 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0018-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Road # MCE0, STA: 0+700 to STA: 0+860 | 22.31 | 1615.11 | 100% | 22.31 | 36033.1041
9 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-16 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0019-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Road # MCE0, STA: 0+620 to STA: 0+700 | 22.31 | 879.49 | 100% | 22.31 | 19621.4219
10 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-18 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0023-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Road # MCD0, STA: 0+50 to STA: 0+180 | 22.31 | 932.1 | 100% | 22.31 | 20795.151
11 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-18 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0026-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Road # MCZ0, STA: 0+080.00 to STA: 0+310.00 | 22.31 | 1958.41 | 100% | 22.31 | 43692.1271
12 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-18 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0027-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Road # MCE0, STA: 0+500 to STA: 0+620 | 22.31 | 1257.28 | 100% | 22.31 | 28049.9168
13 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-19 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0029-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Road # MCF0, STA: 0+230 to STA: 0+350 | 22.31 | 1477.14 | 100% | 22.31 | 32954.9934
14 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-19 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0030-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at Road # MCE0, STA: 0+620 to STA: 0+830 | 22.31 | 2394.09 | 100% | 22.31 | 53412.1479
15 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-19 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0031-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Road # MCF0, STA: 0+350 to STA: 0+410 | 22.31 | 1521.95 | 100% | 22.31 | 33954.7045
16 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-20 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0032-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Road # MCZ0, STA: 0+310 to STA: 0+447.25 | 22.31 | 1476.28 | 100% | 22.31 | 32935.8068
17 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-20 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0033-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Road # MCG0, STA: 0+380 to STA: 0+480 | 22.31 | 1612.73 | 100% | 22.31 | 35980.0063
18 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-20 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0034-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at Road # MCE0, STA: 0+500 to STA: 0+620 | 22.31 | 1161.27 | 100% | 22.31 | 25907.9337
19 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-21 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0035-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Road # MCZ0, STA: 0+80 to STA: 0+170 | 22.31 | 812.15 | 100% | 22.31 | 18119.0665
20 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-21 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0036-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Road # MCG0, STA: 0+260 to STA: 0+380 | 22.31 | 2166.97 | 100% | 22.31 | 48345.1007
21 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-21 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0039-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Road # MCZ0, STA: 0+170 to STA: 0+310 | 22.31 | 2073.37 | 100% | 22.31 | 46256.8847
22 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-21 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0041-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Road # MCG0, STA: 0+224 to STA: 0+260 | 22.31 | 599.64 | 100% | 22.31 | 13377.9684
23 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-21 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0042-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Road # MCF0, STA: 0+224 to STA: 0+230 | 22.31 | 77.86 | 100% | 22.31 | 1737.0566
24 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-22 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0045-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Road # MCG0, STA: 0+380 to STA: 0+490 | 22.31 | 1657.98 | 100% | 22.31 | 36989.5338
25 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-27 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0053-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer at Road # MCE0, STA: 0+620 to STA: 0+810 | 22.31 | 2071.48 | 100% | 22.31 | 46214.7188
26 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-27 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0054-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer at Road # MCE0, STA: 0+500 to STA: 0+620 | 22.31 | 1127.4 | 100% | 22.31 | 25152.294
27 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-27 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0055-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Road # MCF0, STA: 0+230 to STA: 0+350 | 22.31 | 1574.1 | 100% | 22.31 | 35118.171
28 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-27 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0056-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Road # MCD0, STA: 0+50 to STA: 0+180 | 22.31 | 2410.85 | 100% | 22.31 | 53786.0635
29 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-02 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0058-02 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at Road # MCG0, STA: 0+490 to STA: 0+610 | 22.31 | 1475.11 | 100% | 22.31 | 32909.7041
30 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-29 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0059-01 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Road # MCZ0, STA: 0+80 to STA: 0+170 | 22.31 | 673.43 | 100% | 22.31 | 15024.2233
31 | B1.31 22 00.03 | Embankments to the ROW | 2026-04-29 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0060-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Road # MCG0, STA: 0+224 to STA: 0+260 | 22.31 | 911.61 | 100% | 22.31 | 20338.0191
32 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-02 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0061-01 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at Road # MCG0, STA: 0+380 to STA: 0+490 | 22.31 | 1602.98 | 100% | 22.31 | 35762.4838
33 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-02 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0062-01 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Road # MCZ0, STA: 0+170 to STA: 0+310 | 22.31 | 1990.8 | 100% | 22.31 | 44414.748
34 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-02 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0064-00 | Check Coordinates level and Compaction F.D.T for Embankment 6th layer at Road # MCE0, STA: 0+620 to STA: 0+720 | 22.31 | 1051.75 | 100% | 22.31 | 23464.5425
35 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-02 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0065-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Road # MCF0, STA: 0+460 to STA: 0+560 | 22.31 | 638.47 | 100% | 22.31 | 14244.2657
36 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-03 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0066-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Road # MCZ0, STA: 0+310 to STA: 0+447.25 | 22.31 | 1766.75 | 100% | 22.31 | 39416.1925
37 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-03 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0067-00 | Check Coordinates level and Compaction F.D.T for Embankment 6th layer at Road # MCE0, STA: 0+500 to STA: 0+620 | 22.31 | 1162.2 | 100% | 22.31 | 25928.682
38 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-03 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0068-00 | Check Coordinates level and Compaction F.D.T for Embankment 6th layer at Road # MCE0, STA: 0+720 to STA: 0+800 | 22.31 | 848.88 | 100% | 22.31 | 18938.5128
39 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-06 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0069-01 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Road# MCF0, STA: 0+350 to STA: 0+410 | 22.31 | 647.12 | 100% | 22.31 | 14437.2472
40 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-04 | SUD1-02-011-TDC-TS9-1-ROD­FIR-0070-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Road# MCG0, STA: 0+224 to STA: 0+380 | 22.31 | 3115.32 | 100% | 22.31 | 69502.7892
41 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-04 | SUD1-02-011-TDC-TS9-1-ROD­FIR-0071-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at Road# MCZ0, STA: 0+80 to STA: 0+170 | 22.31 | 724.95 | 100% | 22.31 | 16173.6345
42 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-04 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0074-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Road connection point MCZ0 to MCE0, STA: 0+000.00 to STA: 0+144.25 | 22.31 | 2089.09 | 100% | 22.31 | 46607.5979
43 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-04 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0075-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Road # MCF0, STA: 0+560 to STA: 0+730 | 22.31 | 1375.6 | 100% | 22.31 | 30689.636
44 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-04 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0077-00 | Check Coordinates level and Compaction F.D.T for Embankment 7th layer at Road # MCE0, STA: 0+500 to STA: 0+640 and STA : 0+730 to 0+ 740 | 22.31 | 1408.75 | 100% | 22.31 | 31429.2125
45 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-06 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0078-00 | Check Coordinates level and Compaction F.D.T for Embankment 8th layer at Road # MCE0, STA: 0+500 to STA: 0+610 | 22.31 | 1132.33 | 100% | 22.31 | 25262.2823
46 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-06 | SUD1-02-011-TDC-TS9-1-ROD­FIR-0079-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer at Road# MCGO, STA: 0+380 to STA: 0+560 | 22.31 | 2401.99 | 100% | 22.31 | 53588.3969
47 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-05 | SUD1-02-011-TDC-TS9-1-ROD­FIR-0080-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at Road# MCF0, STA: 0+230 to STA: 0+350 | 22.31 | 1560.48 | 100% | 22.31 | 34814.3088
48 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-06 | SUD1-02-011-TDC-TS9-1-ROD­FIR-0081-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Road# MCFO, STA: 0+224 to STA: 0+230 | 22.31 | 141.91 | 100% | 22.31 | 3166.0121
49 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-06 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0082-01 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at Road # MCZ0, STA: 0+170 to STA: 0+310 | 22.31 | 1989.77 | 100% | 22.31 | 44391.7687
50 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-06 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0083-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Road # MCZ0, STA: 0+310 to STA: 0+447.25 | 22.31 | 1953.26 | 100% | 22.31 | 43577.2306
51 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-07 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0087-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Road # MCF0, STA: 0+560 to STA: 0+680 | 22.31 | 1136.97 | 100% | 22.31 | 25365.8007
52 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-07 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0089-00 | Check Coordinates level and Compaction F.D.T for Embankment 9th layer at Road # MCE0, STA: 0+500 to STA: 0+600 | 22.31 | 1040.91 | 100% | 22.31 | 23222.7021
53 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-07 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0090-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer at Road # MCZ0, STA: 0+80 to STA: 0+170 | 22.31 | 743.01 | 100% | 22.31 | 16576.5531
54 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-09 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0093-00 | Check Coordinates level and Compaction F.D.T for Embankment 6th layer at Road # MCD0, STA: 0+50 to STA: 0+180 | 22.31 | 2209.38 | 100% | 22.31 | 49291.2678
55 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-10 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0094-00 | Check Coordinates level and Compaction F.D.T for Embankment 6th layer at Road # MCG0, STA: 0+380 to STA: 0+540 | 22.31 | 2067.09 | 100% | 22.31 | 46116.7779
56 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-11 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0095-01 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Road connection point MCZ0 to MCE0, STA: 0+000.00 to STA: 0+144.25 | 22.31 | 2206.72 | 100% | 22.31 | 49231.9232
57 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-11 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0096-01 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer at Road # MCF0, STA: 0+230 to STA: 0+350 | 22.31 | 1579.04 | 100% | 22.31 | 35228.3824
58 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-11 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0097-01 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Road # MCF0, STA: 0+350 to STA: 0+410 | 22.31 | 662.88 | 100% | 22.31 | 14788.8528
59 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-11 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0098-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer at Road # MCZ0, STA: 0+170 to STA: 0+310 | 22.31 | 1945.12 | 100% | 22.31 | 43395.6272
60 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-11 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0099-00 | Check Coordinates level and Compaction F.D.T for Embankment 10th layer at Road # MCE0, STA: 0+500 to STA: 0+580 | 22.31 | 888.44 | 100% | 22.31 | 19821.0964
61 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-10 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0100-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Road # MCF0, STA: 0+224 to STA: 0+230 | 22.31 | 142.04 | 100% | 22.31 | 3168.9124
62 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-11 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0102-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer at Road # MCG0, STA: 0+224 to STA: 0+380 | 22.31 | 2945.18 | 100% | 22.31 | 65706.9658
63 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-11 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0103-00 | Check Coordinates level and Compaction F.D.T for Embankment 7th layer at Road # MCD0, STA: 0+40 to STA: 0+180 | 22.31 | 2975.57 | 100% | 22.31 | 66384.9667
64 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-12 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0104-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at Road # MCZ0, STA: 0+310 to STA: 0+447.25 | 22.31 | 1910.55 | 100% | 22.31 | 42624.3705
65 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-14 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0105-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at Road connection point MCZ0 to MCE0, STA: 0+000.00 to STA: 0+144.25 | 22.31 | 2272.85 | 100% | 22.31 | 50707.2835
66 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-05-12 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0107-00 | Check Coordinates level and Excavation width Bottom level for sewerage pipe line trench from Existing Manhole# MH-39-26 to Manhole# MH-51-1, at Road MCE0 | 221.14 | 98.8 | 5% | 11.057 | 1092.4316
67 | B5 33.05.13.05 | Sewerage Network:GRP Pipes 200 mm (Depth 2.51m to 3.5m) | 2026-05-17 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0108-02 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH-51-1, at Road MCE0 | 15848.43 | 1 | 5% | 792.4215 | 792.4215
68 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-12 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0109-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at Road # MCF0, STA: 0+224 to STA: 0+230 | 22.31 | 142.32 | 100% | 22.31 | 3175.1592
69 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-12 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0110-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at Road # MCF0, STA: 0+350 to STA: 0+410 | 22.31 | 666.36 | 100% | 22.31 | 14866.4916
70 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-12 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0111-00 | Check Coordinates level and Compaction F.D.T for Embankment 6th layer at Road # MCZ0, STA: 0+80 to STA: 0+170 | 22.31 | 770.95 | 100% | 22.31 | 17199.8945
71 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-13 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0112-01 | Check Coordinates level and Compaction F.D.T for Embankment 11th layer at Road # MCE0, STA: 0+500 to STA: 0+530 | 22.31 | 127.02 | 100% | 22.31 | 2833.8162
72 | B5 33.05.13.05 | Sewerage Network:GRP Pipes 200 mm (Depth 2.51m to 3.5m) | 2026-05-14 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0113-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 51-2 & MH-51-3 at Road MCE0 | 15848.43 | 2 | 5% | 792.4215 | 1584.843
73 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-05-14 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0114-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-51-1 – MH-51-2 – MH-51-3 at Road MCE0 | 221.14 | 197.6 | 5% | 11.057 | 2184.8632
74 | B5 33.31.00.04 | Sewerage Network:GRP Pipes 200 mm (Depth 3.51m to 4.5m) | 2026-06-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0115-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Existing Manhole # MH 39-27 - MH 49-1 at Road MCE0 | 14852.32 | 98.8 | 5% | 742.616 | 73370.4608
75 | B5.33 05 13.07 | Sewerage Network:GRP Pipes 1000 mm (Depth 3.51m to 4.5m) | 2026-05-23 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0116-03 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 49-1,49-2,49-3 at Road MCE0 | 19319.76 | 3 | 5% | 965.988 | 2897.964
76 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-14 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0117-00 | Check Coordinates level and Compaction F.D.T for Embankment 7th layer at Road # MCG0, STA: 0+380 to STA: 0+520 | 22.31 | 1658.21 | 100% | 22.31 | 36994.6651
77 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-14 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0118-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Road # MCF0, STA: 0+410 to STA: 0+460 | 22.31 | 493.13 | 100% | 22.31 | 11001.7303
78 | B5 33.31.00.03 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-05-20 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0119-02 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH 49-2 TO MH – 49-1 at Road MCE0 | 329.77 | 98.8 | 5% | 16.4885 | 1629.0638
79 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-14 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0121-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer at Road # MCF0, STA: 0+224 to STA: 0+230 | 22.31 | 142.74 | 100% | 22.31 | 3184.5294
80 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-14 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0122-00 | Check Coordinates level and Compaction F.D.T for Embankment 8th layer at Road # MCD0, STA: 0+40 to STA: 0+180 | 22.31 | 2297.58 | 100% | 22.31 | 51259.0098
81 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-16 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0123-00 | Check Coordinates level and Compaction F.D.T for Embankment 6th layer at Road # MCZ0, STA: 0+170 to STA: 0+310 | 22.31 | 1900.52 | 100% | 22.31 | 42400.6012
82 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-16 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0126-00 | Check Coordinates level and Compaction F.D.T for Embankment 6th layer at Road # MCF0, STA: 0+224 to STA: 0+230 | 22.31 | 143.08 | 100% | 22.31 | 3192.1148
83 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-17 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0127-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer at Road # MCF0, STA: 0+350 to STA: 0+410 | 22.31 | 670.18 | 100% | 22.31 | 14951.7158
84 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-17 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0128-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Road # MCF0, STA: 0+410 to STA: 0+460 | 22.31 | 472.69 | 100% | 22.31 | 10545.7139
85 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-17 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0129-00 | Check Coordinates level and Compaction F.D.T for Embankment 7th layer at Road # MCZ0, STA: 0+80 to STA: 0+170 | 22.31 | 803.74 | 100% | 22.31 | 17931.4394
86 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-17 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0130-00 | Check Coordinates level and Compaction F.D.T for Embankment 8th layer at Road # MCG0, STA: 0+380 to STA: 0+490 | 22.31 | 1268.91 | 100% | 22.31 | 28309.3821
87 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-17 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0131-00 | Check Coordinates level and Compaction F.D.T for Embankment 9th layer at Road # MCD0, STA: 0+40 to STA: 0+180 | 22.31 | 2238.92 | 100% | 22.31 | 49950.3052
88 | B1.31 22 00.01 | EARTHWORKS AND SITE GRADING Roadway Excavation for cuttings | 2026-05-17 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0132-00 | Check Coordinates and bottom level Road Excavation/cutting upto bottom of Sub-Grade at Road # MCG0, STA: 0+730 to STA: 0+807.40 | 13.58 | 405.011 | 100% | 13.58 | 5500.0494
89 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-05-17 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0133-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from # MH 51-3 - MH 51-4 at Road MCE0 | 221.14 | 98.8 | 5% | 11.057 | 1092.4316
90 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-05-19 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0134-01 | Check Coordinates level, Excavation width Bottom level and compaction for sewerage Manhole pit MH- 51-4 at Road MCE0 | 12377.1 | 1 | 5% | 618.855 | 618.855
91 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-19 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0135-01 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at Road # MCF0, STA: 0+0460 to STA: 0+580 | 22.31 | 1302.03 | 100% | 22.31 | 29048.2893
92 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-19 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0136-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer at Road connection point MCZ0 to MCE0, STA: 0+000.00 to STA: 0+144.25 | 22.31 | 2326.43 | 100% | 22.31 | 51902.6533
93 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-19 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0137-00 | Check Coordinates level and Compaction F.D.T for Embankment 7th layer at Road # MCG0, STA: 0+224 to STA: 0+380 | 22.31 | 2791.98 | 100% | 22.31 | 62289.0738
94 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-23 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0138-01 | Check Coordinates level and Compaction F.D.T for Embankment 10th layer at Road # MCD0, STA: 0+40 to STA: 0+180 | 22.31 | 1938.17 | 100% | 22.31 | 43240.5727
95 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0139-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from existing manhole # MH-39-22 to MH-53-1 at Road MCF0 | 221.14 | 98.8 | 5% | 11.057 | 1092.4316
96 | B5 33.05.13.05 | Sewerage Network:GRP Pipes 200 mm (Depth 2.51m to 3.5m) int dia 1200 mm | 2026-05-23 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0140-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 53-1 at Road MCF0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
97 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0141-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Existing Manhole # MH 39-23 to MH 52-1 at Road MCF0 | 221.14 | 98.8 | 5% | 11.057 | 1092.4316
98 | B5 33.05.13.05 | Sewerage Network:GRP Pipes 200 mm (Depth 2.51m to 3.5m) int dia 1200 mm | 2026-05-23 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0142-01 | Check Coordinates level, Excavation width Bottom level and compaction for Sewerage Manhole pit MH- 52-1 at Road MCF0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
99 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-14 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0143-02 | Check Sand bedding and GRP pipe installation for sewerage line from Existing Manholes # MH 39-26 to MH 51-1 at Road MCE0 | 221.14 | 98.8 | 45% | 99.513 | 9831.8844
100 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-05-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0144-01 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-51-1 to MH-51-2 at Road MCE0 | 221.14 | 98.8 | 45% | 99.513 | 9831.8844
101 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-20 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0148-00 | Check Coordinates level and Compaction F.D.T for Embankment 6th layer at Road # MCZ0, STA: 0+310 to STA: 0+447.25 | 22.31 | 1824.42 | 100% | 22.31 | 40702.8102
102 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-20 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0149-00 | Check Coordinates level and Compaction F.D.T for Embankment 9th layer at Road # MCG0, STA: 0+380 to STA: 0+460 | 22.31 | 867.28 | 100% | 22.31 | 19349.0168
103 | B5 33.31.00.03 | Sewerage Network:GRP Pipes 200 mm (Depth 2.51m to 3.5m) | 2026-05-20 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0150-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH 49-3 TO MH – 49-2 at Road MCE0 | 329.77 | 98.8 | 5% | 16.4885 | 1629.0638
104 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-21 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0151-00 | Check Coordinates level and Compaction F.D.T for Embankment 7th layer at Road # MCZ0, STA: 0+170 to STA: 0+310 | 22.31 | 1855.89 | 100% | 22.31 | 41404.9059
105 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-23 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0152-01 | Check Coordinates level and Compaction F.D.T for Embankment 8th layer at Road # MCG0, STA: 0+224 to STA: 0+380 | 22.31 | 2713.98 | 100% | 22.31 | 60548.8938
106 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-05-23 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0153-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH 51-4 TO MH – 51-5 at Road MCE0 | 221.14 | 58.8 | 5% | 11.057 | 650.1516
107 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-05-23 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0154-00 | Check Coordinates level, Excavation width Bottom level and compaction for Sewerage Manhole pit MH- 51-5 at Road MCE0 | 12377.1 | 1 | 5% | 618.855 | 618.855
108 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-23 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0155-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Road # MCG0, STA: 0+050 to STA: 0+360 | 22.31 | 1544.49 | 100% | 22.31 | 34457.5719
109 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-23 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0156-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Road # MC20, STA: 5+020 to STA: 5+230 | 22.31 | 1932.77 | 100% | 22.31 | 43120.0987
110 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-23 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0157-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Road # MCG0, STA: 0+050 to STA: 0+290 | 22.31 | 2400 | 100% | 22.31 | 53544
111 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-23 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0159-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Road # MCG0, STA: 0+190 to STA: 0+220 | 22.31 | 300 | 100% | 22.31 | 6693
112 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-23 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0160-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Road # MCE0, STA: 0+50 to STA: 0+350 | 22.31 | 1490.57 | 100% | 22.31 | 33254.6167
113 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-21 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0161-00 | Check Coordinates level and Compaction F.D.T 1st layer at Road # MCF0, STA: 0+50 to STA: 0+370 | 22.31 | 1901.95 | 100% | 22.31 | 42432.5045
114 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-24 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0162-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right & Left side)1st layer at Road # MC20, STA: 4+710 to STA: 5+020 | 22.31 | 2099.32 | 100% | 22.31 | 46835.8292
115 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-24 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0163-00 | Check Coordinates level and Compaction F.D.T for Embankment 8th layer at Road # MCZ0, STA: 0+80 to STA: 0+170 | 22.31 | 839.24 | 100% | 22.31 | 18723.4444
116 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-24 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0164-00 | Check Coordinates level and Compaction F.D.T for Embankment 6th layer at Road # MCF0, STA: 0+350 to STA: 0+410 | 22.31 | 671.8 | 100% | 22.31 | 14987.858
117 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-24 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0165-00 | Check Coordinates level and Compaction F.D.T for Embankment 11th layer at Road # MCD0, STA: 0+40 to STA: 0+180 | 22.31 | 1759.61 | 100% | 22.31 | 39256.8991
118 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-21 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0166-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Road # MCH0, STA: 0+60 to STA: 0+360 | 22.31 | 1455.73 | 100% | 22.31 | 32477.3363
119 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-23 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0167-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Road # MCH0, STA: 0+60 to STA: 0+320 | 22.31 | 2610 | 100% | 22.31 | 58229.1
120 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-23 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0168-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Road # MCF0, STA: 0+50 to STA: 0+290 | 22.31 | 2402 | 100% | 22.31 | 53588.62
121 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-24 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0169-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Road # MCF0, STA: 0+160 to STA: 0+230 | 22.31 | 700 | 100% | 22.31 | 15617
122 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-21 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0170-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Road # MCA0, STA: 0+720 to STA: 0+800 | 22.31 | 458.61 | 100% | 22.31 | 10231.5891
123 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-24 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0171-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Road # MCA0, STA: 0+910 to STA: 0+950 | 22.31 | 233.68 | 100% | 22.31 | 5213.4008
124 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-21 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0172-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Road # MCA0, STA: 0+590 to STA: 0+640 | 22.31 | 216.81 | 100% | 22.31 | 4837.0311
125 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-24 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0173-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right & Left side)1st layer at Road # MC20, STA: 5+230 to STA: 5+280 | 22.31 | 434.65 | 100% | 22.31 | 9697.0415
126 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-24 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0174-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right & Left side)1st layer at Road # MC20, STA: 5+420 to STA: 5+500 | 22.31 | 485.5 | 100% | 22.31 | 10831.505
127 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-24 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0175-00 | Check Coordinates level and Compaction F.D.T for Embankment 6th layer at Road connection point MCZ0 to MCE0, STA: 0+000.00 to STA: 0+144.25 | 22.31 | 2376.02 | 100% | 22.31 | 53009.0062
128 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-25 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0177-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right & Left side)2nd layer at Road # MC20, STA: 4+820 to STA: 5+230 | 22.31 | 4305.81 | 100% | 22.31 | 96062.6211
129 | B1.31 22 00.03 | Embankments to the Plot | 2026-05-25 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0179-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Road # MCG0, STA: 0+050 to STA: 0+190 | 22.31 | 1400 | 100% | 22.31 | 31234
130 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-24 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0180-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at Road # MCF0, STA: 0+580 to STA: 0+610 | 22.31 | 304.71 | 100% | 22.31 | 6798.0801
131 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-25 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0181-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Road # MCG0, STA: 0+290 to STA: 0+320 | 22.31 | 114.37 | 100% | 22.31 | 2551.5947
132 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-25 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0182-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Road # MCG0, STA: 0+220 to STA: 0+290 | 22.31 | 229.32 | 100% | 22.31 | 5116.1292
133 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-31 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0183-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right & Left side)3rd layer at Road # MC20, STA: 5+020 to STA: 5+230 | 22.31 | 1855.91 | 100% | 22.31 | 41405.3521
134 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-25 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0184-00 | Check Coordinates level and Compaction F.D.T for Embankment 7th layer at Road # MCZ0, STA: 0+310 to STA: 0+447.25 | 22.31 | 1785.12 | 100% | 22.31 | 39826.0272
135 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-31 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0185-01 | Check Coordinates level and Compaction F.D.T for Embankment 7th layer at Road # MCF0, STA: 0+224 to STA: 0+410 | 22.31 | 2421.5 | 100% | 22.31 | 54023.665
136 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-31 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0186-01 | Check Coordinates level and Compaction F.D.T for Embankment 9th layer at Road # MCG0, STA: 0+224 to STA: 0+380 | 22.31 | 2639.16 | 100% | 22.31 | 58879.6596
137 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-31 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0187-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right & Left side)3rd layer at Road # MCH0, STA: 0+060 to STA: 0+320 | 22.31 | 1326 | 100% | 22.31 | 29583.06
138 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-24 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0191-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right & Left side)3rd layer at Road # MCG0, STA: 0+220 to STA: 0+290 | 22.31 | 381.28 | 100% | 22.31 | 8506.3568
139 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-25 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0192-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right & Left side) 2nd layer at Road # MCG0, STA: 0+290 to STA: 0+320 | 22.31 | 223.38 | 100% | 22.31 | 4983.6078
140 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-31 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0193-00 | Check Coordinates level and Compaction F.D.T for Embankment of 4th layer at Road # MCG0, STA: 0+190 to STA: 0+220 | 22.31 | 117.01 | 100% | 22.31 | 2610.4931
141 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-31 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0194-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right & Left side) 4th layer at Road # MCG0, STA: 0+190 to STA: 0+220 | 22.31 | 152.49 | 100% | 22.31 | 3402.0519
142 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-01 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0195-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right & Left side) 4th layer at Road # MCH0, STA: 0+060 to STA: 0+300 | 22.31 | 1210.5 | 100% | 22.31 | 27006.255
143 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-01 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0196-00 | Check Coordinates level and Compaction F.D.T for Embankment 9th layer at Road # MCZ0, STA: 0+80 to STA: 0+170 | 22.31 | 869.81 | 100% | 22.31 | 19405.4611
144 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-01 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0197-00 | Check Coordinates level and Compaction F.D.T for Embankment 8th layer at Road # MCZ0, STA: 0+170 to STA: 0+310 | 22.31 | 1810.44 | 100% | 22.31 | 40390.9164
145 | B5 33.31.00.03 | Sewerage Network:GRP Pipes 200 mm (Depth 2.51 m to 3.5m) | 2026-06-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0198-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH – 49-3 to MH – 49-4 at Road MCE0 | 329.77 | 101.33 | 5% | 16.4885 | 1670.7797
146 | B5.33 05 13.07 | Sewerage Network:GRP Pipes 1000 mm (Depth 3.51m to 4.5m) | 2026-06-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0199-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 49-4 at Road MCE0 | 19319.76 | 01 | 5% | 965.988 | 965.988
147 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-01 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0203-00 | Check Coordinates level and Compaction F.D.T for Embankment 7th layer at Road connection point MCZ0 to MCE0, STA: 0+000.00 to STA: 0+144.25 | 22.31 | 2430.8 | 100% | 22.31 | 54231.148
148 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-01 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0204-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right & Left side) 3rd layer at Road # MCF0, STA: 0+050 to STA: 0+160 | 22.31 | 520.41 | 100% | 22.31 | 11610.3471
149 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-01 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0205-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Road # MCF0, STA: 0+50 to STA: 0+160 | 22.31 | 178.46 | 100% | 22.31 | 3981.4426
150 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-01 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0206-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right & Left side) 4th layer at Road # MCF0, STA: 0+160 to STA: 0+250 | 22.31 | 382.5 | 100% | 22.31 | 8533.575
151 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-01 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0207-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at Road # MCF0, STA: 0+160 to STA: 0+250 | 22.31 | 177.38 | 100% | 22.31 | 3957.3478
152 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-09 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0208-01 | Check Coordinates level and Compaction F.D.T for Shoulder (Right & Left side) Embankments 1st layer at Road # MC20, STA: 4+530 to STA: 4+710 | 22.31 | 1043.32 | 100% | 22.31 | 23276.4692
153 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-09 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0209-01 | Check Coordinates level and Compaction F.D.T for Shoulder (Right & Left side) 2nd layer at Road # MC20, STA: 5+420 to STA: 5+500 | 22.31 | 765.73 | 100% | 22.31 | 17083.4363
154 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-17 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0210-01 | Check Coordinates level and Compaction F.D.T for Shoulder (Right & Left side) Embankment 1st layer at Road # MCI0, STA: 0+020 to STA: 0+150 | 22.31 | 763.3 | 100% | 22.31 | 17029.223
155 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-17 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0211-01 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Road # MCI0, STA: 0+020 to STA: 0+150 | 22.31 | 144.78 | 100% | 22.31 | 3230.0418
156 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-01 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0212-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Road # MCF0, STA: 0+250 to STA: 0+290 | 22.31 | 56.84 | 100% | 22.31 | 1268.1004
157 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-01 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0213-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Road # MCF0, STA: 0+290 to STA: 0+370 | 22.31 | 101.92 | 100% | 22.31 | 2273.8352
158 | B6.33 42 11.22 | Storm Water Network : Manhole for GRP Pipes 1000mm (Depth: 1.51m -2.51m) | 2026-06-02 | SUD1-02-011-TDC-TS9-1-STR-FIR-0215-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Existing Manhole # FIMH – G2/6 to MH – G2/6/1 at Road MCG0 | 884.56 | 92.65 | 5% | 44.228 | 4097.7242
159 | B6.33 05 39.8 | Storm Water Network : Manhole 2000mm (Depth: 1.51m -2.51m) | 2026-06-02 | SUD1-02-011-TDC-TS9-1-STR-FIR-0216-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water manhole pit MH- G2/6/1at Road MCG0 | 30133.35 | 01 | 5% | 1506.6675 | 1506.6675
160 | B6.33 42 11.22 | Storm Water Network : Manhole for GRP Pipes 1000mm (Depth: 1.51m -2.51m) | 2026-06-02 | SUD1-02-011-TDC-TS9-1-STR-FIR-0217-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # MH – G2/6/1 to MH – G2/6/2 at Road MCG0 | 884.56 | 89 | 5% | 44.228 | 3936.292
161 | B6.33 05 39.8 | Storm Water Network : Manhole 2000mm (Depth: 1.51m -2.51m) | 2026-06-02 | SUD1-02-011-TDC-TS9-1-STR-FIR-0218-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water manhole pit MH- G2/6/2 at Road MCG0 | 30133.35 | 01 | 5% | 1506.6675 | 1506.6675
162 | B6.33 42 11.19 | Storm Water Network : Manhole for GRP Pipes 900mm (Depth: 1.51m -2.51m) | 2026-06-02 | SUD1-02-011-TDC-TS9-1-STR-FIR-0219-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # MH – G2/6/2 to MH – G2/6/3 at Road MCG0 | 743.93 | 89.25 | 5% | 37.1965 | 3319.7876
163 | B6.33 05 39.5 | Storm Water Network : Manhole 1500mm (Depth: 1.51m -2.51m) | 2026-06-02 | SUD1-02-011-TDC-TS9-1-STR-FIR-0220-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water manhole pit MH- G2/6/3 at Road MCG0 | 15295.58 | 01 | 5% | 764.779 | 764.779
164 | B6.33 42 11.15 | Storm Water Network : Manhole for GRP Pipes 800mm (Depth: 0.00 -1.50 m) | 2026-06-02 | SUD1-02-011-TDC-TS9-1-STR-FIR-0221-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # MH – G2/6/3 to MH – G2/6/4 at Road MCG0 | 623.66 | 89.5 | 5% | 31.183 | 2790.8785
165 | B6.33 05 39.5 | Storm Water Network : Manhole 1500mm (Depth: 1.51m -2.51m) | 2026-06-02 | SUD1-02-011-TDC-TS9-1-STR-FIR-0222-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water manhole pit MH- G2/6/4 at Road MCG0 | 15295.58 | 01 | 5% | 764.779 | 764.779
166 | B1.31 22 00.04 | Embankments to the Plot | 2026-06-02 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0223-00 | Check Coordinates level and Compaction F.D.T for Embankment 1ST layer at PLOT (5), STA: 0+360 to STA: 0+570 | 22.31 | 4985.91 | 100% | 22.31 | 111235.6521
167 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-02 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0224-00 | Check Coordinates level and Compaction F.D.T for Embankment 10th layer at Road # MCG0, STA: 0+224 to STA: 0+380 | 22.31 | 2561.16 | 100% | 22.31 | 57139.4796
168 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-02 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0225-00 | Check Coordinates level and Compaction F.D.T for Embankment 8th layer at Road # MCZ0, STA: 0+310 to STA: 0+447.25 | 22.31 | 1742.06 | 100% | 22.31 | 38865.3586
169 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-07 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0226-01 | Check Coordinates level and Compaction F.D.T for Embankment 12th layer at Road # MCD0, STA: 0+30 to STA: 0+180 (Bottom Subgrade) | 22.31 | 1221.13 | 100% | 22.31 | 27243.4103
170 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-02 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0228-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Road # MCF0, STA: 0+410 to STA: 0+430 | 22.31 | 220.54 | 100% | 22.31 | 4920.2474
171 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-02 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0230-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Road # MCH0, STA: 0+70 to STA: 0+310 | 22.31 | 217.56 | 100% | 22.31 | 4853.7636
172 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-02 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0236-00 | Check Coordinates level and Compaction F.D.T for Embankments of 3rd layer at Road # MCG0, STA: 0+290 to STA: 0+320 | 22.31 | 111.72 | 100% | 22.31 | 2492.4732
173 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-02 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0237-00 | Check Coordinates level and Compaction F.D.T for Embankments of 4th layer at Road # MCG0, STA: 0+220 to STA: 0+290 | 22.31 | 249.9 | 100% | 22.31 | 5575.269
174 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-02 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0238-00 | Check Coordinates level and Compaction F.D.T for Embankments of 5th layer at Road # MCG0, STA: 0+190 to STA: 0+220 | 22.31 | 103.88 | 100% | 22.31 | 2317.5628
175 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-03 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0239-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Plot (5) STA: 0+350 to STA: 0+467 | 22.31 | 3821.64 | 100% | 22.31 | 85260.7884
176 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-04 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0240-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right & Left side) 1st layer at Road # MC20, STA: 5+500 to STA: 5+620 | 22.31 | 849.49 | 100% | 22.31 | 18952.1219
177 | B1.31 22 00.04 | Embankments to the Plot | 2026-07-15 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0246-00 | Check Coordinates level, Compaction F.D.T for Embankment 1st Layer STA: 0+360 to 0+467 at Plot. No: - 04 | 22.31 | 6931.74 | 100% | 22.31 | 154647.1194
178 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-04 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0247-00 | Check Coordinates level and Compaction F.D.T for Embankment 8th layer at Road connection point MCZ0 to MCE0, STA: 0+000.00 to STA: 0+144.25 | 22.31 | 2489.56 | 100% | 22.31 | 55542.0836
179 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-04 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0248-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at Road # MCF0, STA: 0+410 to STA: 0+430 | 22.31 | 220.93 | 100% | 22.31 | 4928.9483
180 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-04 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0249-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right side) 3rd layer at Road # MCG0, STA: 0+290 to STA: 0+320 | 22.31 | 76.14 | 100% | 22.31 | 1698.6834
181 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-04 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0250-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right side)4th layer at Road # MCG0, STA: 0+220 to STA: 0+290 | 22.31 | 178.5 | 100% | 22.31 | 3982.335
182 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-04 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0251-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right side) 5th layer at Road # MCG0, STA: 0+190 to STA: 0+220 | 22.31 | 85.49 | 100% | 22.31 | 1907.2819
183 | B1.31 22 00.04 | Embankments to the Plot | 2026-06-09 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0252-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at PLOT (3), STA: 0+060 to STA: 0+150 | 22.31 | 1,392.73 | 100% | 22.31 | 31071.8063
184 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-08 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0255-02 | Check Coordinates level and Compaction F.D.T for Embankment 11th layer at Road # MCG0, STA: 0+240 to STA: 0+360 | 22.31 | 1766.28 | 100% | 22.31 | 39405.7068
185 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-06 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0256-00 | Check Coordinates level and Compaction F.D.T for Embankment 9th layer at Road # MCZ0, STA: 0+170 to STA: 0+310 | 22.31 | 1766.14 | 100% | 22.31 | 39402.5834
186 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-06 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0257-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer at Road # MCF0, STA: 0+410 to STA: 0+430 | 22.31 | 221.39 | 100% | 22.31 | 4939.2109
187 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-08 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0258-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Road # MCF0, STA: 0+430 to STA: 0+460 | 22.31 | 258.04 | 100% | 22.31 | 5756.8724
188 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-07 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0260-00 | Check Coordinates and bottom level Road Excavation/cutting upto bottom of Sub-Grade at Road # MCD0, STA: 0+30 to STA: 0+40 | 22.31 | 49.190 | 100% | 22.31 | 1097.4289
189 | B1.31 22 00.03 | Embankments to the ROW | 2026-05-25 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0261-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Road # MCF0, STA: 0+230 to STA: 0+250 | 22.31 | 150.00 | 100% | 22.31 | 3346.5
190 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-07 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0262-00 | Check Coordinates and bottom level Road Excavation/cutting and compaction test upto bottom of Sub-Grade at Road # MC20, STA: 4+530 to STA: 4+710 | 22.31 | 799.67 | 100% | 22.31 | 17840.6377
191 | B1.31 22 00.04 | Embankments to the Plot | 2026-06-11 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0263-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Plot (5) STA: 0+020 to STA: 0+150 Area (3) | 22.31 | 4339.03 | 100% | 22.31 | 96803.7593
192 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-07 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0264-00 | Check Coordinates level and Compaction F.D.T for Embankment 10th layer at Road # MCZ0, STA: 0+80 to STA: 0+170 | 22.31 | 911.91 | 100% | 22.31 | 20344.7121
193 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0266-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from existing manhole # MH-52-2 to MH-52-3 at Road MCF0 | 221.14 | 98.80 | 5% | 11.057 | 1092.4316
194 | B5 33.05.13.05 | Sewerage Network:GRP Pipes 200 mm (Depth 2.51m to 3.5m) | 2026-06-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0267-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 52-2 at Road MCF0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
195 | B5 33.05.13.05 | Sewerage Network:GRP Pipes 200 mm (Depth 2.51m to 3.5m) | 2026-06-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0268-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 52-3 at Road MCF0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
196 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0269-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from existing manhole # MH-53-2 to MH-53-3 at Road MCF0 | 221.14 | 98.80 | 5% | 11.057 | 1092.4316
197 | B5 33.05.13.05 | Sewerage Network:GRP Pipes 200 mm (Depth 2.51m to 3.5m) | 2026-06-07 | UD1-02-011-TDC-TS9-1-SEW-FIR-0270-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 53-2 at Road MCF0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
198 | B5 33.05.13.05 | Sewerage Network: (Depth 2.51m to 3.5m) | 2026-06-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0271-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 53-3 at Road MCF0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
199 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-14 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0272-01 | Check Coordinates level and Compaction F.D.T for Embankment 10th layer at Road # MCF0, STA: 0+224 to STA: 0+410 | 22.31 | 2,460.39 | 100% | 22.31 | 54891.3009
200 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0273-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from manhole # MH-12-26 to MH-12-25 at Road MCB0 | 212.41 | 73.80 | 5% | 10.6205 | 783.7929
201 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-06-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0274-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 12-26 at Road MCB0 | 12377.1 | 01 | 5% | 618.855 | 618.855
202 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0275-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from manhole # MH-12-25 to MH-12-24 at Road MCB0 | 212.41 | 73.80 | 5% | 10.6205 | 783.7929
203 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-06-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0276-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 12-25 at Road MCB0 | 12377.1 | 01 | 5% | 618.855 | 618.855
204 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-06-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0277-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 12-24 at Road MCB0 | 12377.1 | 01 | 5% | 618.855 | 618.855
205 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-07 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0278-00 | Check Coordinates level and Compaction F.D.T for Embankment 9th layer at Road # MCZ0, STA: 0+310 to STA: 0+447.25 | 22.31 | 1699.67 | 100% | 22.31 | 37919.6377
206 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-08 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0283-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH – 52-1 to MH – 52-2 at Road MCF0 | 221.14 | 98.80 | 5% | 11.057 | 1092.4316
207 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-08 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0284 -00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH – 53-1 to MH – 53-2 at Road MCF0 | 221.14 | 98.80 | 5% | 11.057 | 1092.4316
208 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-10 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0285-01 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Road # MCE0, STA: 0+50 to STA: 0+160 | 22.31 | 1100 | 100% | 22.31 | 24541
209 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-08 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0286-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Road # MCE0, STA: 0+160 to STA: 0+200 | 22.31 | 120.54 | 100% | 22.31 | 2689.2474
210 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-08 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0287-00 | Check Coordinates level and Compaction F.D.T T for Shoulder (Right & Left side) 2nd layer at Road # MCE0, STA: 0+160 to STA: 0+200 | 22.31 | 204 | 100% | 22.31 | 4551.24
211 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-08 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0288-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from existing manhole # MH-49-4 to MH-49-5 at Road MCD0 | 221.14 | 41.12 | 5% | 11.057 | 454.6638
212 | B5.33 05 13.07 | Sewerage Network:GRP Pipes 1000 mm (Depth 3.51m to 4.5m) | 2026-06-08 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0289-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole Pit MH- 49-5 at Road MCD0 | 19319.76 | 01 | 5% | 965.988 | 965.988
213 | B5 33.05.13.06 | Sewerage Network: Manhole Depth 2.51m to 3.5m) internal dia 1200 mm with backdrop | 2026-06-08 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0290-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole Pit MH- 49-6 at Road MCD0 | 19018.11 | 01 | 5% | 950.9055 | 950.9055
214 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-06-08 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0291-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole Pit MH- 50-1 at Road MCD0 | 12377.1 | 01 | 5% | 618.855 | 618.855
215 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-08 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0292-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from existing manhole # MH-49-6 to MH-50-1 at Road MCD0 | 221.14 | 67.70 | 5% | 11.057 | 748.5589
216 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-09 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0295-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Road # MCF0, STA: 0+370 to STA: 0+390 | 22.31 | 31.11 | 100% | 22.31 | 694.0641
217 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-09 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0296-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at Road # MCG0, STA: 0+050 to STA: 0+190 | 22.31 | 1400.00 | 100% | 22.31 | 31234
218 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-09 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0297-00 | Check Coordinates level and Compaction F.D.T for Embankment 10th layer at Road # MCZ0, STA: 0+170 to STA: 0+310 | 22.31 | 1719.89 | 100% | 22.31 | 38370.7459
219 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-06-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0301-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 53-4 at Road MCF0 | 12377.1 | 01 | 5% | 618.855 | 618.855
220 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-06-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0302-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 53-5 at Road MCF0 | 12377.1 | 01 | 5% | 618.855 | 618.855
221 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-06-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0303-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 53-6 at Road MCF0 | 12377.1 | 01 | 5% | 618.855 | 618.855
222 | B5 33.05.13.05 | Sewerage Network: Manhole Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-06-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0304-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 52-4 at Road MCF0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
223 | B5 33.05.13.05 | Sewerage Network: Manhole Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-06-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0305-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 52-5 at Road MCF0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
224 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-06-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0306-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 52-6 at Road MCF0 | 12377.1 | 01 | 5% | 618.855 | 618.855
225 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0307-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from manhole # MH-12-24 to MH-12-23 at Road MCB0 | 221.14 | 98.80 | 5% | 11.057 | 1092.4316
226 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0308-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Existing manhole # MH-12-23 to MH-12-22 at Road MCB0 | 212.41 | 98.80 | 5% | 10.6205 | 1049.3054
227 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0309-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Existing manhole # MH-12-22 to MH-12-21 at Road MCB0 | 212.41 | 95.92 | 5% | 10.6205 | 1018.7184
228 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-06-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0310-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 12-23 at Road MCB0 | 12377.1 | 01 | 5% | 618.855 | 618.855
229 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-06-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0311-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 12-22 at Road MCB0 | 12377.1 | 01 | 5% | 618.855 | 618.855
230 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-06-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0312-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 12-21 at Road MCB0 | 12377.1 | 01 | 5% | 618.855 | 618.855
231 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-18 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0313-01 | Check Coordinates and level and compaction F.D.T for Embankment 4th layer at Road # MCH0, STA: 0+070 to STA: 0+300 ( bottom Sub-Grade) | 22.31 | 917.28 | 100% | 22.31 | 20464.5168
232 | B1.31 22 00.01 | Roadway Excavation for cuttings | 2026-06-11 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0314-00 | Check Coordinates and bottom level Road Excavation/cutting and compaction test of bottom Sub-Grade at Road # MCA0, STA: 0+950 to STA: 1+340 | 13.58 | 437.61 | 100% | 13.58 | 5942.7438
233 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-17 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0315-00 | Check Coordinates level Road and compaction F.D.T for Embankment bottom Sub-Grade layer at Road # MCF0, STA: 0+050 to STA: 0+390 | 22.31 | 1041.41 | 100% | 22.31 | 23233.8571
234 | B1.31 22 00.01 | Roadway Excavation for cuttings | 2026-06-10 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0316-00 | Check Coordinates and bottom level Road cutting and compaction test of bottom Sub-Grade at Road # MC20, STA: 4+710 to STA: 4+900 | 13.58 | 339.96 | 100% | 13.58 | 4616.6568
235 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-14 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0317-01 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-51-2 to MH-51-3 at Road MCE0 | 221.14 | 98.80 | 45% | 99.513 | 9831.8844
236 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0318-02 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-51-3 to MH-51-4 at Road MCE0 | 221.14 | 98.80 | 45% | 99.513 | 9831.8844
237 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-16 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0325-02 | Check Coordinates and compaction F.D.T for Embankment 1st layer at Road # MC20, STA: 4+710 to STA: 4+900 (bottom Sub-Grade) | 22.31 | 86.62 | 100% | 22.31 | 1932.4922
238 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-10 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0326-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Road # MCA0, STA: 0+590 to STA: 0+640 | 22.31 | 352.00 | 100% | 22.31 | 7853.12
239 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-10 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0327-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right side) Embankments 2nd layer at Road # MCF0, STA: 0+290 to STA: 0+350 | 22.31 | 153.00 | 100% | 22.31 | 3413.43
240 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-10 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0328-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right side) Embankments 3rd layer at Road # MCF0, STA: 0+250 to STA: 0+290 | 22.31 | 79.56 | 100% | 22.31 | 1774.9836
241 | B1.31 22 00.04 | Embankments to the Plot | 2026-06-13 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0329-00 | Check Coordinates level, Compaction F.D.T for Embankment 1st Layer STA: 0+250 to 0+360 (Left Side) at Plot. No: - 04 | 22.31 | 2208.54 | 100% | 22.31 | 49272.5274
242 | B1.31 22 00.01 | Roadway Excavation for cuttings | 2026-06-11 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0330-00 | Check Coordinates and bottom level Road cutting and compaction test of bottom Sub-Grade at Road layer 1st STA: 0 +850 to STA: 0+890 at Road # MCA0 | 13.58 | 61.19 | 100% | 13.58 | 830.9602
243 | B1.31 22 00.03 | Earth works & Site Grading | 2026-06-14 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0331-01 | Check Coordinates and bottom level Road Filling and compaction test of bottom Sub-Grade 1st layer at Road # MCA0, STA: 0+800 to STA: 0+890 |  | 514.13
244 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-06-11 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0332-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH – 49-6 to MH – 49-7 at Road MCE0 | 212.41 | 40.42 | 5% | 10.6205 | 429.2806
245 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-06-11 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0333-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH – 49-7 to MH – 49-8 at Road MCE0 | 212.41 | 48.80 | 5% | 10.6205 | 518.2804
246 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-06-11 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0334-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH – 51-5 to MH – 51-6 at Road MCE0 | 212.41 | 58.80 | 5% | 10.6205 | 624.4854
247 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-06-11 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0335-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 49-7 at Road MCE0 | 12377.1 | 01 | 5% | 618.855 | 618.855
248 | B5 33.05.13.05 | Sewerage Network: Manhole Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-06-11 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0336-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 49-8 at Road MCE0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
249 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-06-11 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0337-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 51-6 at Road MCE0 | 12377.1 | 01 | 5% | 618.855 | 618.855
250 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-16 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0344-02 | Check Coordinates and bottom level Road Filling and compaction test of bottom Sub-Grade at Road # MCA0, STA: 0+950 to STA: 1+340 | 22.31 | 1909.79 | 100% | 22.31 | 42607.4149
251 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0346-01 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from Existing manhole # MH-39-23 to MH-52-1 at Road MCF0 | 221.14 | 98.80 | 45% | 99.513 | 9831.8844
252 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0347-02 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-52-1 to MH-52-2 at Road MCF0 | 221.14 | 98.80 | 45% | 99.513 | 9831.8844
253 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0348-02 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-52-2 to MH-52-3 at Road MCF0 | 221.14 | 98.80 | 45% | 99.513 | 9831.8844
254 | B1.31 22 00.04 | Embankments to the Plot | 2026-06-13 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0349-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at PLOT (3), STA: 0+060 to STA: 0+150 | 22.31 | 2690.67 | 100% | 22.31 | 60028.8477
255 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-15 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0350-01 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at, STA: 0+360 to STA: 0+370 & 2nd layer at, STA: 0+320 to STA: 0+370 at Road # MCG0 | 22.31 | 88.98 | 100% | 22.31 | 1985.1438
256 | B1.31.22.00.04 | Embankments to the Plot | 2026-06-21 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0351-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Plot (3) STA: 0+0250 to STA: 0+460 | 22.31 | 6,860.47 | 100% | 22.31 | 153057.0857
257 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-14 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0352-01 | Check Coordinates level and Compaction F.D.T for Embankment 12th layer at Road # MCG0, STA: 0+240 to STA: 0+360 | 22.31 | 1,556.63 | 100% | 22.31 | 34728.4153
258 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-13 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0353-00 | Check Coordinates level and Compaction F.D.T for Embankment 11th layer at Road # MCZ0, STA: 0+80 to STA: 0+170 | 22.31 | 866.81 | 100% | 22.31 | 19338.5311
259 | B6.33 42 11.13 | Storm Water Network : GRP Pipes 700 mm (Depth: 1.51m -2.51m) | 2026-06-16 | SUD1-02-011-TDC-TS9-1-STR-FIR-0355-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water pipeline trench from Manhole # MH – G2/6/4 to FMH – A2/9/20-398 at Road MCG0 | 544.12 | 43.96 | 5% | 27.206 | 1195.9758
260 | B6.33 42 11.10 | Storm Water Network : GRP Pipes 600 mm (Depth: 1.51m -2.51m) | 2026-06-16 | SUD1-02-011-TDC-TS9-1-STR-FIR-0356-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water pipeline trench from Manhole # FMH – A2/9/20-398 MH – G2/6/5 to at Road MCG0 | 461.68 | 44.19 | 5% | 23.084 | 1020.082
261 | B6.33 42 11.7 | Storm Water Network : GRP Pipes 600 mm (Depth: 1.51m -2.51m) | 2026-06-16 | SUD1-02-011-TDC-TS9-1-STR-FIR-0357-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water pipeline trench from Manhole # MH – G2/6/5 to FMH – A2/9/20-396 at Road MCG0 | 379.24 | 44.24 | 5% | 18.962 | 838.8789
262 | B6.33 42 11.3 | Storm Water Network : GRP Pipes 400 mm (Depth: 0m -1.5m) | 2026-06-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-0358-01 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water pipeline trench from Manhole # FMH – A2/9/20-396 to MH – G2/6/6 to at Road MCG0 | 544.12 | 39.34 | 5% | 27.206 | 1070.284
263 | B6.33 05 39.5 | Storm Water Network : Manhole 1500mm (Depth: 1.51m -2.51m) | 2026-06-16 | SUD1-02-011-TDC-TS9-1-STR-FIR-0359-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit FMH-A2/9/20-398 at Road MCG0 | 15295.58 | 01 | 5% | 764.779 | 764.779
264 | B6.33 05 39.2 | Storm Water Network : Manhole 1200mm (Depth: 1.51m -2.51m) | 2026-06-16 | SUD1-02-011-TDC-TS9-1-STR-FIR-0360-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit MH- G2/6/5 at Road MCG0 | 12376.13 | 01 | 5% | 618.8065 | 618.8065
265 | B6.33 05 39.2 | Storm Water Network : Manhole 1200mm (Depth: 1.51m -2.51m) | 2026-06-16 | SUD1-02-011-TDC-TS9-1-STR-FIR-0361-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit FMH- A2/9/20-396 at Road MCG0 | 12376.13 | 01 | 5% | 618.8065 | 618.8065
266 | B6.33 05 39.2 | Storm Water Network : Manhole 1200mm (Depth: 1.51m -2.51m) | 2026-06-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-0362-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole Pit MH- G2/6/6 at Road MCG0 | 12376.13 | 01 | 5% | 618.8065 | 618.8065
267 | B5.33 05 13.07 | Sewerage Network:GRP Pipes 1000 mm (Depth 3.51m to 4.5m) | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0363-00 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 49-1 at Road MCE0 | 19319.76 | 01 | 55% | 10625.868 | 10625.868
268 | B5.33 05 13.07 | Sewerage Network:GRP Pipes 1000 mm (Depth 3.51m to 4.5m) | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0364-00 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 49-2 at Road MCE0 | 19319.76 | 01 | 55% | 10625.868 | 10625.868
269 | B5.33 05 13.07 | Sewerage Network:GRP Pipes 1000 mm (Depth 3.51m to 4.5m) | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0365-00 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 49-3 at Road MCE0 | 19319.76 | 01 | 55% | 10625.868 | 10625.868
270 | B5.33 05 13.07 | Sewerage Network:GRP Pipes 1000 mm (Depth 3.51m to 4.5m) | 2026-06-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0366-01 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 49-4 at Road MCE0 | 19319.76 | 01 | 55% | 10625.868 | 10625.868
271 | B5 33.05.13.05 | Sewerage Network: Manhole Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0367-00 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 51-1 at Road MCE0 | 15848.43 | 01 | 55% | 8716.6365 | 8716.6365
272 | B5 33.05.13.05 | Sewerage Network: Manhole Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0368-00 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 51-2 at Road MCE0 | 15848.43 | 01 | 55%
273 | B5 33.05.13.05 | Sewerage Network: Manhole Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0369-00 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 51-3 at Road MCE0 | 15848.43 | 01 | 55% | 8716.6365 | 8716.6365
274 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0370-00 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 51-4 at Road MCE0 | 12377.1 | 01 | 55% | 6807.405 | 6807.405
275 | B5 33.05.13.05 | Sewerage Network: Manhole Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0371-00 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 52-1 at Road MCF0 | 15848.43 | 01 | 55% | 8716.6365 | 8716.6365
276 | B5 33.05.13.05 | Sewerage Network: Manhole Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0372-00 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 52-2 at Road MCF0 | 15848.43 | 01 | 55% | 8716.6365 | 8716.6365
277 | B5 33.05.13.05 | Sewerage Network: Manhole Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0373-00 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 52-3 at Road MCF0 | 15848.43 | 01 | 55% | 8716.6365 | 8716.6365
278 | B5 33.05.13.05 | Sewerage Network: Manhole Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0374-00 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 53-1 at Road MCF0 | 15848.43 | 01 | 55% | 8716.6365 | 8716.6365
279 | B5 33.05.13.05 | Sewerage Network: Manhole Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0375-00 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 53-2 at Road MCF0 | 15848.43 | 01 | 55% | 8716.6365 | 8716.6365
280 | B5 33.05.13.05 | Sewerage Network: Manhole Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0376-00 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 53-3 at Road MCF0 | 15848.43 | 01 | 55% | 8716.6365 | 8716.6365
281 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-14 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0380-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-51-1 – MH-51-2 at Road MCE0 | 221.14 | 98.80 | 45% | 99.513 | 9831.8844
282 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-15 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0381-00 | Check Coordinates level and Compaction F.D.T for Embankment 6th layer at Road # MCF0, STA: 0+410 to STA: 0+430 | 22.31 | 88.20 | 100% | 22.31 | 1967.742
283 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-15 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0382-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at Road # MCF0, STA: 0+430 to STA: 0+460 | 22.31 | 137.20 | 100% | 22.31 | 3060.932
284 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.0m to 1.5m) |  | SUD1-02-011-TDC-TS9-1-SEW-FIR-0383-02 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from manhole # MH-12-21 to MH-12-20 at Road MCB0 | 212.41 | 100.57 | 5% | 10.6205 | 1068.1037
285 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.0m to 1.5m) | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0384-02 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-20 to MH-12-19 at Road MCB0 | 212.41 | 94.83 | 5% | 10.6205 | 1007.142
286 | B5 33.05.13.04 | Sewerage Network:Manhole (Depth 1.51m to 2.5m) int dia with backdrop | 2026-06-14 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0385-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 12-20 at Road MCB0 | 14852.32 | 01 | 5% | 742.616 | 742.616
287 | B5 33.05.13.04 | Sewerage Network:Manhole (Depth 1.51m to 2.5m) int dia with backdrop | 2026-06-14 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0386-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 12-19 at Road MCB0 | 14852.32 | 01 | 5% | 742.616 | 742.616
288 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-15 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0387-00 | Check Coordinates level and Compaction F.D.T for Embankment 13th layer at Road # MCG0, STA: 0+240 to STA: 0+360 | 22.31 | 562.00 | 100% | 22.31 | 12538.22
289 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-15 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0388-00 | Check Coordinates level and Compaction F.D.T for Embankment 11th layer at Road # MCZ0, STA: 0+170 to STA: 0+310 | 22.31 | 1,566.56 | 100% | 22.31 | 34949.9536
290 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-15 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0389-00 | Check Coordinates level and Compaction F.D.T for Embankment 11th layer at Road # MCZ0, STA: 0+310 to STA: 0+447.25 | 22.31 | 1,344.16 | 100% | 22.31 | 29988.2096
291 | B1.31 22 00.04 | Embankments to the Plot | 2026-06-16 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0390-01 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at PLOT (3), STA: 0+060 to STA: 0+150 | 22.31 | 2,690.67 | 100% | 22.31 | 60028.8477
292 | B1.31 22 00.04 | Embankments to the Plot | 2026-06-16 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0391-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at PLOT (6), STA: 0+450 to STA: 0+700 | 22.31 | 2426.35 | 100% | 22.31 | 54131.8685
293 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0392-02 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH – 49-6 to MH – 49-5 at Road MCE0 | 221.14 | 33.69 | 5% | 11.057 | 372.5103
294 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-16 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0393-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH – 53-4 to MH – 53-3 at Road MCF0 | 221.14 | 98.80 | 5% | 11.057 | 1092.4316
295 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.0m to 1.5m) | 2026-06-16 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0394-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH – 53-5 to MH – 53-4 at Road MCF0 | 212.41 | 58.80 | 5% | 10.6205 | 624.4854
296 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.0m to 1.5m) | 2026-06-16 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0395-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH – 53-6 to MH – 53-5 at Road MCF0 | 212.41 | 58.80 | 5% | 10.6205 | 624.4854
297 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0396-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH – 52-4 to MH – 52-3 at Road MCF0 | 221.14 | 98.80 | 5% | 11.057 | 1092.4316
298 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0397-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH – 52-5 to MH – 52-4 at Road MCF0 | 221.14 | 58.80 | 5% | 11.057 | 650.1516
299 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-18 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0398-01 | Check Coordinates level and compaction F.D.T for Embankment 1st layer at Road # MC20, STA: 4+900 to STA: 5+060 (Bottom sub grade) | 22.31 | 783.14 | 100% | 22.31 | 17471.8534
300 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-16 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0399-00 | Check Coordinates level and compaction F.D.T for Embankment 1st layer at Road # MC20, STA: 5+060 to STA: 5+230 (Bottom sub grade) | 22.31 | 676.17 | 100% | 22.31 | 15085.3527
301 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0400-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-51-3 – MH-51-2 at Road MCE0 | 221.14 | 98.80 | 10% | 22.114 | 2184.8632
302 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-16 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0402-00 | Check Coordinates level and Compaction F.D.T for Embankment 12th layer at Road # MCZ0, STA: 0+80 to STA: 0+170 | 22.31 | 365.51 | 100% | 22.31 | 8154.5281
303 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-17 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0403-00 | Check Coordinates level and Compaction F.D.T for Embankment 9th layer at Road connection point MCZ0 to MCE0, STA: 0+000.00 to STA: 0+144.25 | 22.31 | 2544.23 | 100% | 22.31 | 56761.7713
304 | B1.31 22 00.04 | Embankments to the Plot | 2026-06-17 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0404-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at PLOT (5), STA: 0+360 to STA: 0+570 | 22.31 | 5,916.05 | 100% | 22.31 | 131987.0755
305 | B5 33.31.00.04 | Sewerage Network:GRP Pipes 200 mm (Depth 3.51m to 4.5m) | 2026-06-16 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0405-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-49-1 to MH-49-2 at Road MCE0 | 397.67 | 98.80 | 45% | 178.9515 | 17680.4082
306 | B5 33.31.00.04 | Sewerage Network:GRP Pipes 200 mm (Depth 3.51m to 4.5m) | 2026-06-16 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0406-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from Existing manhole # MH-39-27 to MH-49-1 at Road MCE0 | 397.67 | 98.80 | 45% | 178.9515 | 17680.4082
307 | B5 33.31.00.03 | Sewerage Network:GRP Pipes 200 mm (Depth 2.51m to 3.5m) | 2026-06-16 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0407-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-49-2 to MH-49-3 at Road MCE0 | 329.77 | 98.80 | 45% | 148.3965 | 14661.5742
308 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-17 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0409-00 | Check Coordinates level and compaction F.D.T for Embankment 1st layer at Road # MCG0, STA: 0+190 to STA: 0+370 (Bottom sub grade) | 22.31 | 595.64 | 100% | 22.31 | 13288.7284
309 | B1.31 22 00.01 | Earth Work & Site Grading (Roadway Excavation/cuttings) | 2026-06-17 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0410-00 | Check Coordinates and bottom level Road Excavation/cutting upto bottom of Sub-Grade STA: 0+020 to STA: 0+150 at Road # MCI0 | 13.58 | 117.805 | 100% | 13.58 | 1599.7919
310 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.0m to 1.5m) | 2026-06-18 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0411-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-19 to MH-12-18 at Road MCB0 | 212.41 | 101.75 | 5% | 10.6205 | 1080.6359
311 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-06-18 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0412-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 12-18 at Road MCB0 | 12377.1 | 01 | 5% | 618.855 | 618.855
312 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-17 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0413-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-51-4 – MH-51-3 at Road MCE0 | 221.14 | 98.80 | 10% | 22.114 | 2184.8632
313 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-18 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0414-00 | Check Coordinates level and Compaction F.D.T for Embankment 11th layer at Road # MCF0, STA: 0+224 to STA: 0+410 | 22.31 | 1,401.71 | 100% | 22.31 | 31272.1501
314 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-18 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0415-00 | Check Coordinates level and Compaction F.D.T for Embankment 7th layer at Road # MCF0, STA: 0+410 to STA: 0+460 | 22.31 | 220.50 | 100% | 22.31 | 4919.355
315 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-18 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0417-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH – 52-5 to MH – 52-6 at Road MCF0 | 221.14 | 58.80 | 5% | 11.057 | 650.1516
316 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-20 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0418-01 | Check Coordinates level and Compaction F.D.T for Embankment 12th layer at Road # MCZ0, STA: 0+170 to STA: 0+310 | 22.31 | 964.81 | 100% | 22.31 | 21524.9111
317 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-20 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0419-00 | Check Coordinates level and Compaction F.D.T for Embankment 12th layer at Road # MCZ0, STA: 0+310 to STA: 0+447.25 | 22.31 | 525.19 | 100% | 22.31 | 11716.9889
318 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-20 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0420-01 | Check Coordinates level and Compaction F.D.T for Embankment 14th layer at Road # MCG0, STA: 0+240 to STA: 0+360 | 22.31 | 308.61 | 100% | 22.31 | 6885.0891
319 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-18 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0425-00 | Inspection Gravity and Leakage test pipeline from Existing Manhole # MH-39-26 to MH-51-1 at Road MCE0 | 221.14 | 98.80 | 10% | 22.114 | 2184.8632
320 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-22 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0426-01 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer at Road and right side shoulder # MCG0, STA: 0+050 to STA: 0+190 | 22.31 | 439.00 | 100% | 22.31 | 9794.09
321 | B1.31 22 00.04 | Embankments to the Plot | 2026-06-23 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0427-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Plot (9), STA: 0+050 to STA: 0+200 | 22.31 | 3144.16 | 100% | 22.31 | 70146.2096
322 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-20 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0429-00 | Check Coordinates,bottom level,Road Filling and compaction test and Embankment 1st layer at bottom Sub-Grade at Road # MC20, STA: 5+390 to STA: 5+530 | 22.31 | 145.00 | 100% | 22.31 | 3234.95
323 | B1.31 22 00.01 | Earth Work & Site Grading (Roadway Excavation/cuttings) | 2026-06-22 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0430-01 | Check Coordinates level and Compaction F.D.T for Embankment 13th layer Bottom subgrade at Road # MCZ0, STA: 0+80 to STA: 0+170 | 13.58 | 848.23 | 100% | 13.58 | 11518.9634
324 | B1.31 22 00.04 | Embankments to the Plot | 2026-06-21 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0432-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at PLOT (3), STA: 0+060 to STA: 0+160 | 22.31 | 2,341.43 | 100% | 22.31 | 52237.3033
325 | B1.31 22 00.01 | Earth Work & Site Grading (Roadway Excavation/cuttings) | 2026-06-20 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0433-00 | Check Coordinates and bottom level Road Excavation/cutting upto bottom of Sub-Grade STA: 5+390to STA: 5+530 at Road # MC20 | 13.58 | 45.35 | 100% | 13.58 | 615.853
326 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-22 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0434-01 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer (Left side) Shoulder at Road # MCG0, STA: 0+050 to STA: 0+190 | 22.31 | 356.49 | 100% | 22.31 | 7953.2919
327 | B6.33 42 11.22 | Embankments to the Plot | 2026-07-23 | SUD1-02-011-TDC-TS9-1-STR-FIR-0437-02 | Check Sand Bedding and GRP Pipe Installation for Storm water line from Existing Manhole # FIMH-G2/6 to MH-G2/6/1at Road MCG0 | 884.56 | 92.65 | 45% | 398.052 | 36879.5178
328 | B6.33 42 11.22 | Storm Water Network : Manhole for GRP Pipes 1000mm (Depth: 1.51m -2.51m) | 2026-07-02 | SUD1-02-011-TDC-TS9-1-STR-FIR-0438-02 | Check Sand Bedding and GRP Pipe Installation for Storm water line from Manhole # MH-G2/6/1 to MH-G2/6/2 at Road MCG0 | 884.56 | 89.00 | 45% | 398.052 | 35426.628
329 | B6.33 42 11.19 | Storm Water Network:GRP Pipes 900mm dia (Depth 1.51m to 2.5m) | 2026-07-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-0439-02 | Check Sand Bedding and GRP Pipe Installation for Storm water line from Manhole # MH-G2/6/2 to MH-G2/6/3 at Road MCG0 | 743.93 | 89.25 | 45% | 334.7685 | 29878.0886
330 | B6.33 42 11.16 | Storm Water Network:Catch Basin ( Double) | 2026-07-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-0440-02 | Check Sand Bedding and GRP Pipe Installation for Storm water line from Manhole # MH-G2/6/3 to MH-G2/6/4 at Road MCG0 | 366.63 | 89.50 | 45% | 164.9835 | 14766.0233
331 | B5.33 05 13.07 | Sewerage Network:GRP Pipes 1000 mm (Depth 3.51m to 4.5m) | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0441-00 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 49-5 at Road MCD0 | 19319.76 | 1 | 55% | 10625.868 | 10625.868
332 | B5 33.05.13.06 | Sewerage Network: Manhole Depth 2.51m to 3.5m) internal dia 1200 mm with backdrop | 2026-06-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0442-01 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 49-6 at Road MCD0 | 19018.11 | 1 | 55% | 10459.9605 | 10459.9605
333 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0443-00 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 49-7 at Road MCE0 | 12377.1 | 1 | 55% | 6807.405 | 6807.405
334 | B5 33.05.13.05 | Sewerage Network: Manhole Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0444-00 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 49-8 at Road MCE0 | 15848.43 | 1 | 55% | 8716.6365 | 8716.6365
335 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0445-00 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 50-1 at Road MCD0 | 12377.1 | 1 | 55% | 6807.405 | 6807.405
336 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0446-00 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 51-5 at Road MCE0 | 12377.1 | 1 | 55% | 6807.405 | 6807.405
337 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0447-00 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 51-6 at Road MCE0 | 12377.1 | 1 | 55% | 6807.405 | 6807.405
338 | B5 33.05.13.05 | Sewerage Network: Manhole Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0448-00 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 52-4 at Road MCF0 | 15848.43 | 1 | 55% | 8716.6365 | 8716.6365
339 | B5 33.05.13.05 | Sewerage Network: Manhole Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0449-00 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 52-5 at Road MCF0 | 15848.43 | 1 | 55% | 8716.6365 | 8716.6365
340 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0450-00 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 52-6 at Road MCF0 | 12377.1 | 1 | 55% | 6807.405 | 6807.405
341 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0451-00 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 53-4 at Road MCF0 | 12377.1 | 1 | 55% | 6807.405 | 6807.405
342 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0452-00 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 53-5 at Road MCF0 | 12377.1 | 1 | 55% | 6807.405 | 6807.405
343 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0453-00 | Check Installation of Manhole Base including Rings and Flatslab of Manhole MH- 53-6 at Road MCF0 | 12377.1 | 1 | 55% | 6807.405 | 6807.405
344 | B1.31 22 00.01 | Earth Work & Site Grading (Roadway Excavation/cuttings) | 2026-06-22 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0454-00 | Check Coordinates and bottom level Road Excavation/cutting upto bottom of Sub-Grade STA: 5+530 to STA: 5+800 at Road # MC20 | 13.58 | 1,667.78 | 100% | 13.58 | 22648.4524
345 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-22 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0455-01 | Check Coordinates level and Compaction F.D.T for Embankment 12th layer at Road # MCF0, STA: 0+240 to STA: 0+410 | 22.31 | 1,124.30 | 100% | 22.31 | 25083.133
346 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-21 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0456-00 | Check Coordinates level and Compaction F.D.T for Embankment 10th layer at Road connection point MCZ0 to MCE0, STA: 0+000.00 to STA: 0+144.25 | 22.31 | 2,510.73 | 100% | 22.31 | 56014.3863
347 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0457-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-52-3 to MH-52-4 at Road MCF0 | 221.14 | 98.80 | 45% | 99.513 | 9831.8844
348 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0458-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-52-4 to MH-52-5 at Road MCF0 | 221.14 | 58.80 | 45% | 99.513 | 5851.3644
349 | B1.31 22 00.04 | Embankments to the Plot | 2026-06-21 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0459-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at PLOT (5), STA: 0+360 to STA: 0+570 | 22.31 | 6,423.27 | 100% | 22.31 | 143303.1537
350 | B5 33.31.00.04 | Sewerage Network:GRP Pipes 200 mm (Depth 3.51m to 4.5m) | 2026-06-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0460-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH 39-27 - MH 49-1 at Road MCE0 | 397.67 | 98.80 | 100% | 397.67 | 39289.796
351 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-22 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0461-00 | Check Coordinates level and compaction F.D.T for Embankment 1st layer of half road right side at Road # MCB0, STA: 0+580 to STA: 0+660 | 22.31 | 233.09 | 100% | 22.31 | 5200.2379
352 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-22 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0462-00 | Check Coordinates and bottom level Road Filling and compaction test of bottom Sub-Grade at Road # MC20, STA: 5+530 to STA: 5+800 | 22.31 | 11.41 | 100% | 22.31 | 254.5571
353 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-23 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0467-00 | Check Coordinates level and Compaction F.D.T for Embankment 8th layer at Road # MCF0, STA: 0+410 to STA: 0+460 | 22.31 | 220.50 | 100% | 22.31 | 4919.355
354 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-22 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0468-00 | Check Coordinates level and Compaction F.D.T for Embankment 15th layer at Road # MCG0, STA: 0+290 to STA: 0+320 | 22.31 | 63.07 | 100% | 22.31 | 1407.0917
355 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-23 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0469-01 | Check Coordinates level and Compaction F.D.T for Embankment 13th layer Right side at Road # MCZ0, STA: 0+230 to STA: 0+310 | 22.31 | 285.21 | 100% | 22.31 | 6363.0351
356 | B1.31 22 00.04 | Embankments to the Plot | 2026-06-23 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0470-00 | Check Coordinates level and Compaction F.D.T for Embankment 1ST layer at PLOT (5), STA: 0+250 to STA: 0+360 | 22.31 | 7363 | 100% | 22.31 | 164268.53
357 | B6.33 42 11.22 | Storm Water Network:GRP Pipes 1000 mm dia (Depth 1.51m to 2.5m) | 2026-06-22 | SUD1-02-011-TDC-TS9-1-STR-FIR-0471-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # MH – G2/16/3 to MH – G2/16/4 at Road MCE0 | 884.56 | 87.00 | 5% | 44.228 | 3847.836
358 | B6.33 42 11.19 | Storm Water Network:GRP Pipes 900mm dia (Depth 1.51m to 2.5m) | 2026-06-22 | SUD1-02-011-TDC-TS9-1-STR-FIR-0472-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # MH – G2/16/4 to MH – G2/16/5 at Road MCE0 | 743.93 | 87.25 | 5% | 37.1965 | 3245.3946
359 | B6.33 05 39.9 | Storm Water Network: Manhole 2000mm dia (Depth > 2.5m) | 2026-06-22 | SUD1-02-011-TDC-TS9-1-STR-FIR-0473-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit MH- G2/16/3 at Road MCE0 | 30133.35 | 01 | 5% | 1506.6675 | 1506.6675
360 | B6.33 05 39.9 | Storm Water Network: Manhole 2000mm dia (Depth > 2.5m) | 2026-06-22 | SUD1-02-011-TDC-TS9-1-STR-FIR-0474-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit MH- G2/16/4 at Road MCE0 | 30133.35 | 01 | 5% | 1506.6675 | 1506.6675
361 | B6.33 05 39.6 | Storm Water Network: Manhole 1500mm dia (Depth > 2.5m) | 2026-06-22 | SUD1-02-011-TDC-TS9-1-STR-FIR-0475-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit MH- G2/16/5 at Road MCE0 | 19537.02 | 01 | 5% | 976.851 | 976.851
362 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0 to 1.5m) | 2026-06-23 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0476-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-17 to MH-12-18 at Road MCB0 | 212.41 | 42.24 | 5% | 10.6205 | 448.6099
363 | B5 33.05.13.05 | Sewerage Network: Manhole (Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-06-23 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0477-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 12-17 at Road MCB0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
364 | B5 33.05.13.01 | Sewerage Network: Manhole (Depth 0 m to 1.5m) internal dia 1200 mm | 2026-06-23 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0478-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH-1-91-1 at Road MCA0 | 8820.42 | 01 | 5% | 441.021 | 441.021
365 | B5 33.05.13.01 | Sewerage Network: Manhole (Depth 0 m to 1.5m) internal dia 1200 mm | 2026-06-23 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0479-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 1-91-2 at Road MCA0 | 8820.42 | 01 | 5% | 441.021 | 441.021
366 | B1.31 22 00.04 | Embankments to the Plot | 2026-06-27 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0480-01 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at PLOT (2), STA: 0+570 to STA: 0+720 | 22.31 | 2657.64 | 100% | 22.31 | 59291.9484
367 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0 to 1.5m) | 2026-06-23 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0481-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-91-1to MH-1-91-2 at Road MCA0 | 212.41 | 78.80 | 5% | 10.6205 | 836.8954
368 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0 to 1.5m) | 2026-06-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0483-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-51-5 to MH-51-6 at Road MCE0 | 212.41 | 58.80 | 45% | 95.5845 | 5620.3686
369 | B5 33.31.00.03 | Sewerage Network:GRP Pipes 200 mm (Depth 2.51 m to 3.5m) | 2026-06-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0484-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-49-3 to MH-49-4 at Road MCE0 | 329.77 | 101.33 | 45% | 148.3965 | 15037.0173
370 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0 to 1.5m) | 2026-06-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0485-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-51-4 to MH-51-5 at Road MCE0 | 212.41 | 58.80 | 45% | 95.5845 | 5620.3686
371 | B1.31 22 00.01 | Roadway Excavation for cuttings | 2026-06-23 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0486-00 | Check Coordinates and bottom level Road Excavation/cutting upto bottom of Sub-Grade STA: 0+660 to STA: 0+850 at Road # MCB0 | 13.58 | 1116.65 | 100% | 13.58 | 15164.107
372 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-24 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0489-00 | Check Coordinates level and Compaction F.D.T for Embankment 13th layer at Road # MCF0, STA: 0+240 to STA: 0+410 | 22.31 | 804.36 | 100% | 22.31 | 17945.2716
373 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-24 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0490-00 | Check Coordinates level and Compaction F.D.T for Embankment 9th layer at Road # MCF0, STA: 0+410 to STA: 0+460 | 22.31 | 219.52 | 100% | 22.31 | 4897.4912
374 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-04 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0491-00 | Check Coordinates level and Compaction F.D.T for Embankment 13th layer at Road/carriageway # MCZ0, STA: 0+310 to STA: 0+447.25 | 22.31 | 1,352.35 | 100% | 22.31 | 30170.9285
375 | B5 33.31.00.03 | Sewerage Network:GRP Pipes 200 mm (Depth 2.51 m to 3.5m) | 2026-06-23 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0492-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH 49-1 to MH 49-2 at Road MCE0 | 329.77 | 98.80 | 15% | 49.4655 | 4887.1914
376 | B6.33 42 11.7 | Storm Water Network:GRP Pipes 500 mm dia (Depth 1.51m to 2.5m) | 2026-06-23 | SUD1-02-011-TDC-TS9-1-STR-FIR-0493-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from Manhole # MH-G2/6/5 to FMH-A2/9/20-396 at Road MCG0 | 379.24 | 44.24 | 45% | 170.658 | 7549.9099
377 | B1.31 22 00.04 | Embankments to the Plot | 2026-06-23 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0494-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Plot (5) STA: 0+350 to STA: 0+467 | 22.31 | 2893.13 | 100% | 22.31 | 64545.7303
378 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0 to 1.5m) | 2026-06-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0495-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-91 to MH-1-91-1 at Road MCA0 | 212.41 | 78.20 | 5% | 10.6205 | 830.5231
379 | B5 33.31.00.06 | Sewerage Network:Manhole (Depth 2.51 to 3.5m) Int dia 1200 mm with backdrop | 2026-06-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0496-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-91 at Road MCA0 | 19018.11 | 01 | 5% | 950.9055 | 950.9055
380 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51 m to 2.5m) | 2026-06-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0497-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-89 to MH-1-90 at Road MCA0 | 221.14 | 101.80 | 5% | 11.057 | 1125.6026
381 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51 m to 2.5m) | 2026-06-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0498-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-90 to MH-1-91 at Road MCA0 | 221.14 | 101.30 | 5% | 11.057 | 1120.0741
382 | B5 33.05.13.05 | Sewerage Network: Manhole Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-06-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0499-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-89 at Road MCA0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
383 | B5 33.05.13.05 | Sewerage Network: Manhole Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-06-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0500-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-90 at Road MCA0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
384 | B1.31 22 00.04 | Embankments to the Plot | 2026-06-24 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0501-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at PLOT (5), STA: 0+360 to STA: 0+570 | 22.31 | 6,562.05 | 100% | 22.31 | 146399.3355
385 | B1.31 22 00.04 | Embankments to the Plot | 2026-06-24 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0502-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer at PLOT (3), STA: 0+060 to STA: 0+160 | 22.31 | 2,810.00 | 100% | 22.31 | 62691.1
386 | B1.31 22 00.03 | Embankments to the ROW | 2026-06-24 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0503-00 | Check Coordinates level and Compaction F.D.T for Embankment 11th layer at Road connection point MCZ0 to MCE0, STA: 0+000.00 to STA: 0+144.25 | 22.31 | 1,698.41 | 100% | 22.31 | 37891.5271
387 | B5 33.31.00.03 | Sewerage Network:GRP Pipes 200 mm (Depth 2.51 m to 3.5m) | 2026-06-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0504-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH 49-2 to MH 49-3 at Road MCE0 | 329.77 | 98.80 | 10% | 32.977 | 3258.1276
388 | B5 33.05.13.06 | Sewerage Network: Manhole Depth 2.51m to 3.5m) internal dia 1200 mm with backdrop | 2026-06-24 | SUD1-02-011-TDC-TS9-1-STR-FIR-0505-00 | Check Installation of Manhole Base including Rings and Flat slab of manhole FMH – A2/9/20-396 at Road MCG0 | 19018.11 | 01 | 55% | 10459.9605 | 10459.9605
389 | B6.33 05 39.2 | Storm Water Network : Manhole Dia 1200 mm (Depth:1.51m -2.51m) | 2026-06-24 | SUD1-02-011-TDC-TS9-1-STR-FIR-0506-00 | Check Installation of Manhole Base including Rings and Flat slab of manhole MH –G2/6/5 at Road MCG0 | 12376.13 | 01 | 55% | 6806.8715 | 6806.8715
390 | B6.33 05 39.2 | Storm Water Network : Manhole Dia 1200 mm (Depth:1.51m -2.51m) | 2026-06-24 | SUD1-02-011-TDC-TS9-1-STR-FIR-0507-00 | Check Installation of Manhole Base including Rings and Flat slab of manhole MH –G2/6/6 at Road MCG0 | 12376.13 | 01 | 55% | 6806.8715 | 6806.8715
391 | B6.33 42 11.3 | Storm Water Network:GRP Pipes 400 mm dia (Depth 0 m to 1.5m) | 2026-06-25 | SUD1-02-011-TDC-TS9-1-STR-FIR-0508-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from Manhole # FMH-A2/9/20-396 to MH-G2/6/6 at Road MCG0 | 300.67 | 39.34 | 45% | 135.3015 | 5322.761
392 | B1.31.22.00.04 | Embankments to the Plot | 2026-06-28 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0509-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at PLOT (6), STA: 0+224 to STA: 0+450 | 22.31 | 1,761.91 | 100% | 22.31 | 39308.2121
393 | B1.31 22 00.01 | Earth Work & Site Grading (Roadway Excavation/cuttings) | 2026-06-27 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0518-00 | Check Coordinates and bottom level Road Excavation/cutting upto bottom of Sub-Grade STA: 0+850 to STA: 1+100 at Road # MCB0 | 13.58 | 1,593.43 | 100% | 13.58 | 21638.7794
394 | B1.31.22.00.04 | Embankments to the Plot | 2026-06-27 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0521-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at PLOT (5), STA: 0+250 to STA: 0+360 | 22.31 | 3,141.91 | 100% | 22.31 | 70096.0121
395 | B6.34 42 16.2 | Storm Water Network ( Box Culvert) | 2026-06-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-0525-00 | Check Coordinates level and Excavation width Bottom level and compaction Test of Box Culvert from Existing Manhole # FIMH – G2/16 to MH – G2/16/1 at Road MCE0 | 17.46 | 496.65 | 5% | 0.873 | 433.5755
396 | B1.31.22.00.04 | Embankments to the Plot | 2026-06-28 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0526-00 | Check Coordinates level and Compaction F.D.T for Embankment of PLOT (3), from STA: 0+080 to STA: 0+130 (Left side slope) from Road # MCE0 | 22.31 | 1476.69 | 100% | 22.31 | 32944.9539
397 | B1.31.22.00.04 | Embankments to the Plot | 2026-06-28 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0527-00 | Check Coordinates level and Compaction F.D.T for Embankment of PLOT (3), from STA: 0+040 to STA: 0+180 (Right side slope) from Road # MCD0 | 22.31 | 3,189.23 | 100% | 22.31 | 71151.7213
398 | B6.31 22 00 | Drainage Work for Pond amd Open Canals | 2026-07-23 | SUD1-02-011-TDC-TS9-1-STR-FIR-0528-01 | Check Coordinates level, protection side slope, Bottom level Excavation and Compaction F.D.T for Pond A | 17.46 | 16516.30 | 100% | 17.46 | 288374.598
399 | B1.31.22.00.04 | Embankments to the Plot | 2026-06-28 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0529-00 | Check Coordinates level and Compaction F.D.T for Embankment of PLOT (2), from STA: 0+040 to STA: 0+180 (Left side slope) from Road # MCD0 | 22.31 | 3,370.29 | 100% | 22.31 | 75191.1699
400 | B1.31.22.00.04 | Embankments to the Plot | 2026-06-28 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0530-00 | Check Coordinates level and Compaction F.D.T for Embankment of PLOT (2), from STA: 0+590 to STA: 0+960 (Left side slope) from Road # MCE0 | 22.31 | 3,338.06 | 100% | 22.31 | 74472.1186
401 | B1.31.22.00.04 | Embankments to the Plot | 2026-06-28 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0531-00 | Check Coordinates level and Compaction F.D.T for Embankment of PLOT (5), from STA: 0+224 to STA: 0+720 (Right side slope) from Road # MCF0 | 22.31 | 9,225.78 | 100% | 22.31 | 205827.1518
402 | B1.31.22.00.04 | Embankments to the Plot | 2026-06-28 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0532-00 | Check Coordinates level and Compaction F.D.T for Embankment of PLOT (5), from STA: 0+224 to STA: 0+720 (Left side slope) from Road # MCG0 | 22.31 | 10,022.68 | 100% | 22.31 | 223605.9908
403 | B1.31.22.00.04 | Embankments to the Plot | 2026-06-28 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0533-00 | Check Coordinates level and Compaction F.D.T for Embankment of PLOT (5), from STA: 0+270 to STA: 0+340 (Left side slope) from Road # MCZ0 | 22.31 | 1,869.09 | 100% | 22.31 | 41699.3979
404 | B1.31.22.00.04 | Embankments to the Plot | 2026-06-28 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0534-00 | Check Coordinates level and Compaction F.D.T for Embankment of PLOT (6), from STA: 0+224 to STA: 0+720 (Right side slope) from Road # MCG0 | 22.31 | 8079.45 | 100% | 22.31 | 180252.5295
405 | B1.31.22.00.03 | Embankments to the ROW | 2026-06-30 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0535-01 | Check Coordinates level and Compaction F.D.T for Embankment upto bottom of sub-grade of Road/carriageway at # MCF0, STA: 0+240 to STA: 0+460 | 22.31 | 1080.24 | 100% | 22.31 | 24100.1544
406 | B1.31 22 00.01 | Earth Work & Site Grading (Roadway Excavation/cuttings) | 2026-06-29 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0536-00 | Check Coordinates and bottom level Road/Carriageway Excavation/cutting upto bottom of Sub-Grade STA: 1+100 to STA: 1+200 at Road # MCB0 | 13.58 | 770.34 | 100% | 13.58 | 10461.2172
407 | B1.31.22.00.04 | Embankments to the Plot | 2026-06-29 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0537-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at PLOT (2), STA: 0+570 to STA: 0+720 | 22.31 | 3,417.05 | 100% | 22.31 | 76234.3855
408 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-06-28 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0538-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-49-6 to MH-49-7 at Road MCE0 | 212.41 | 40.42 | 45% | 95.5845 | 3863.5255
409 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0539-03 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-49-5 to MH-49-6 at Road MCD0 | 221.14 | 33.69 | 45% | 99.513 | 3352.593
410 | B5 33.31.00.03 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-28 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0540-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-49-4 to MH-49-5 at Road MCD0 | 329.77 | 41.12 | 45% | 148.3965 | 6102.0641
411 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-28 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0541-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-52-5 to MH-52-6 at Road MCF0 | 221.14 | 58.80 | 5% | 11.057 | 650.1516
412 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-12 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0542-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-93-4 to MH-1-93-3 at Road MCC0 | 212.41 | 78.87 | 5% | 10.6205 | 837.6388
413 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-12 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0543-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-93-2 to MH-1-93-3 at Road MCC0 | 212.41 | 98.86 | 5% | 10.6205 | 1049.9426
414 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-06-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0544-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-93-2 to MH-1-93-1 at Road MCC0 | 212.41 | 98.74 | 5% | 10.6205 | 1048.6682
415 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-12 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0545-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-93-1 to MH-1-93 at Road MCC0 | 221.14 | 97.01 | 5% | 11.057 | 1072.6396
416 | B1.31.22.00.03 | Embankments to the ROW | 2026-06-28 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0549-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Road/carriageway # MCE0, STA: 0+50 to STA: 0+200 | 22.31 | 454.00 | 100% | 22.31 | 10128.74
417 | B1.31.22.00.03 | Embankments to the ROW | 2026-06-28 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0550-00 | Check Coordinates level and compaction F.D.T for Embankment 2nd layer of Road/carriageway at # MCB0, STA: 0+580 to STA: 0+660 | 22.31 | 141.61 | 100% | 22.31 | 3159.3191
418 | B5 33.05.13.01 | Sewerage Network: Manhole (Depth 0 m to 1.5m) internal dia 1200 mm | 2026-06-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0553-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-93-4 at Road MCC0 | 8820.42 | 01 | 5% | 441.021 | 441.021
419 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-06-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0554-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-93-3 at Road MCC0 | 12377.1 | 01 | 5% | 618.855 | 618.855
420 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-06-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0555-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-93-2 at Road MCC0 | 12377.1 | 01 | 5% | 618.855 | 618.855
421 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-06-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0556-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-93-1 at Road MCC0 | 12377.1 | 01 | 5% | 618.855 | 618.855
422 | B5 33.05.13.05 | Sewerage Network: Manhole Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-06-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0557-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-93 at Road MCC0 | 12377.1 | 01 | 5% | 618.855 | 618.855
423 | B6.34 42 16.3 | Storm Water Network ( Box Culvert) | 2026-06-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-0558-00 | Check Formwork, Lean concrete pouring,concrete surface finishing and level of Box culvert from Existing Manhole FIMH – G2/16 to MH-G2/16/1 at Road MCE0 | 367.6 | 19.25 | 15% | 55.14 | 1061.445
424 | B6.33 42 11.22 | Storm Water Network:GRP Pipes 1000 mm dia (Depth 1.51m to 2.5m) | 2026-06-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-0560-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Existing Manhole # FIMH – G2/11 to MH – G2/11/1 at Road MCF0 | 884.56 | 92.96 | 5% | 44.228 | 4111.4349
425 | B6.33 42 11.23 | Storm Water Network : Manhole for GRP Pipes 1000mm (Depth: 2.51m -3.5m) | 2026-06-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-0561-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # MH – G2/11/1 to MH – G2/11/2 at Road MCF0 | 1017.44 | 89.00 | 5% | 50.872 | 4527.608
426 | B6.33 42 11.20 | Storm Water Network : Manhole for GRP Pipes 900mm (Depth: 2.51m -3.5m) | 2026-06-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-0562-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # MH – G2/11/2 to MH – G2/11/3 at Road MCF0 | 875.83 | 89.25 | 5% | 43.7915 | 3908.3914
427 | B6.33 05 39.9 | Storm Water Network: Manhole 2000mm dia (Depth > 2.5m) | 2026-06-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-0563-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit MH- G2/11/1 at Road MCF0 | 30133.35 | 01 | 5% | 1506.6675 | 1506.6675
428 | B6.33 05 39.9 | Storm Water Network: Manhole 2000mm dia (Depth > 2.5m) | 2026-06-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-0564-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit MH- G2/11/2 at Road MCF0 | 30133.35 | 01 | 5% | 1506.6675 | 1506.6675
429 | B6.33 05 39.6 | Storm Water Network: Manhole 1500mm dia (Depth > 2.5m) | 2026-06-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-0565-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit MH- G2/11/3 at Road MCF0 | 19537.02 | 01 | 5% | 976.851 | 976.851
430 | B1.31 22 00.01 | Earth Work & Site Grading (Roadway Excavation/cuttings) | 2026-06-29 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0566-00 | Check Coordinates and bottom level Road/Carriageway cutting and compaction test of bottom Sub-Grade at Road # MC10 STA: 2+720 to STA: 2+920 | 13.58 | 2,762.43 | 100% | 13.58 | 37513.7994
431 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0567-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH 52-2 to MH 52-3 at Road MCF0 | 221.14 | 98.80 | 10% | 22.114 | 2184.8632
432 | B5 33.31.00.03 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0568-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH 49-3 to MH 49-4 at Road MCE0 | 329.77 | 101.33 | 10% | 32.977 | 3341.5594
433 | B1.31.22.00.04 | Embankments to the Plot | 2026-06-30 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0569-00 | Check Coordinates level and Compaction F.D.T for Embankment 6th layer at PLOT (3), STA: 0+060 to STA: 0+160 | 22.31 | 2,812.18 | 100% | 22.31 | 62739.7358
434 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0570-00 | Inspection Gravity and Leakage test pipeline from Existing Manhole # MH 39-23 to MH 52-1 at Road MCF0 | 221.14 | 98.80 | 10% | 22.114 | 2184.8632
435 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0571-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH 52-1 to MH 52-2 at Road MCF0 | 221.14 | 98.80 | 10% | 22.114 | 2184.8632
436 | B1.31.22.00.03 | Embankments to the ROW | 2026-06-29 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0573-00 | Check Coordinates level and Compaction F.D.T for Embankment 6th layer at Road/Carriageway and Right Side Shoulder # MCG0, STA: 0+050 to STA: 0+190 | 22.31 | 846.16 | 100% | 22.31 | 18877.8296
437 | B1.31.22.00.03 | Embankments to the ROW | 2026-06-29 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0574-00 | Check Coordinates level and Compaction F.D.T for Embankment 6th layer(Left Shoulder) at Road # MCG0, STA: 0+050 to STA: 0+190 | 22.31 | 253.98 | 100% | 22.31 | 5666.2938
438 | B1.31.22.00.03 | Embankments to the ROW | 2026-06-30 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0575-00 | Check Coordinates level and Compaction F.D.T for Embankment 13th layer at Road connection point MCZ0 to MCE0, STA: 0+000.00 to STA: 0+144.25 (bottom subgrade) | 22.31 | 3,100.71 | 100% | 22.31 | 69176.8401
439 | B1.31 22 00.01 | Earth Work & Site Grading (Roadway Excavation/cuttings) | 2026-07-01 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0576-01 | Check Coordinates and bottom level Road/Carriageway Excavation/cutting upto bottom of Sub-Grade STA: 1+350 to STA: 1+560 at Road # MCA0 | 13.58 | 2329.31 | 10% | 1.358 | 3163.203
440 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-05 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0577-01 | Check Coordinates level and Compaction F.D.T for Embankment 1ST layer at PLOT (5), STA: 0+570 to STA: 0+730 | 22.31 | 3383.72 | 100% | 22.31 | 75490.7932
441 | B1.31.22.00.04 | Embankments to the Plot | 2026-06-30 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0578-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at PLOT (6), STA: 0+450 to STA: 0+700 | 22.31 | 3282.31 | 100% | 22.31 | 73228.3361
442 | B1.31.22.00.04 | Embankments to the Plot | 2026-06-30 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0579-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at PLOT (6), STA: 0+700 to STA: 0+750 | 22.31 | 516.33 | 100% | 22.31 | 11519.3223
443 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0580-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-98 to MH-1-97 at Road MCC0 | 212.41 | 78.87 | 5% | 10.6205 | 837.6388
444 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0581-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-97 to MH-1-96 at Road MCC0 | 212.41 | 98.86 | 5% | 10.6205 | 1049.9426
445 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0582-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-96 to MH-1-95 at Road MCC0 | 221.14 | 98.74 | 5% | 11.057 | 1091.7682
446 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0583-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-95 to MH-1-94 at Road MCC0 | 221.14 | 96.90 | 5% | 11.057 | 1071.4233
447 | B5 33.05.13.01 | Sewerage Network: Manhole (Depth 0 m to 1.5m) internal dia 1200 mm | 2026-07-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0584-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-98 at Road MCC0 | 8820.42 | 01 | 5% | 441.021 | 441.021
448 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0585-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-97 at Road MCC0 | 12377.1 | 01 | 5% | 618.855 | 618.855
449 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0586-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-96 at Road MCC0 | 12377.1 | 01 | 5% | 618.855 | 618.855
450 | B5 33.05.13.05 | Sewerage Network: Manhole (Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-07-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0587-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-95 at Road MCC0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
451 | B5 33.05.13.05 | Sewerage Network: Manhole (Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-07-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0588-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-94 at Road MCC0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
452 | B6.33 05 39.9 | Storm Water Network: Manhole 2000mm dia (Depth > 2.5m) | 2026-06-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-0596-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit MH- G2/16/1 at Road MCE0 | 30133.35 | 01 | 5% | 1506.6675 | 1506.6675
453 | B6.33 05 39.9 | Storm Water Network: Manhole 2000mm dia (Depth > 2.5m) | 2026-06-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-0597-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit MH- G2/16/2 at Road MCE0 | 30133.35 | 01 | 5% | 1506.6675 | 1506.6675
454 | B6.33 42 11.22 | Storm Water Network:GRP Pipes 1000 mm dia (Depth 1.51m to 2.5m) | 2026-06-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-0598-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # MH – G2/16/1 to MH – G2/16/2 at Road MCE0 | 884.56 | 87.00 | 5% | 44.228 | 3847.836
455 | B6.33 42 11.22 | Storm Water Network:GRP Pipes 1000 mm dia (Depth 1.51m to 2.5m) | 2026-06-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-0599-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # MH – G2/16/2 to MH – G2/16/3 at Road MCE0 | 884.56 | 87.00 | 5% | 44.228 | 3847.836
456 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-06-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0603-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH 51-4 to MH 51-5 at Road MCE0 | 212.41 | 58.80 | 10% | 21.241 | 1248.9708
457 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0604-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH 52-5 to MH 52-6 at Road MCF0 | 221.14 | 58.80 | 10% | 22.114 | 1300.3032
458 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0605-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH 52-3 to MH 52-4 at Road MCF0 | 221.14 | 98.80 | 10% | 22.114 | 2184.8632
459 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-06-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0606-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH 52-4 to MH 52-5 at Road MCF0 | 221.14 | 58.80 | 10% | 22.114 | 1300.3032
460 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-01 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0607-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at PLOT (5), STA: 0+250 to STA: 0+360 | 22.31 | 3098.42 | 100% | 22.31 | 69125.7502
461 | B1.31 22 00.01 | Earth Work & Site Grading (Roadway Excavation/cuttings) | 2026-07-01 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0613-00 | Check Coordinates and bottom level Road/Carriageway cutting and compaction test of bottom Sub-Grade at Road # MC10 STA: 2+920 to STA: 3+120 | 13.58 | 2,661.89 | 100% | 13.58 | 36148.4662
462 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-07 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0624-01 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Plot (3) STA: 0+0310 to STA: 0+467 | 22.31 | 5,484.66 | 100% | 22.31 | 122362.7646
463 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0625-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH 51-5 to MH 51-6 at Road MCE0 | 212.41 | 58.80 | 10% | 21.241 | 1248.9708
464 | B5 33.31.00.03 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0626-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH 49-4 to MH 49-5 at Road MCD0 | 329.77 | 41.12 | 10% | 32.977 | 1356.0142
465 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0627-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH 49-6 to MH 49-7 at Road MCE0 | 212.41 | 40.42 | 10% | 21.241 | 858.5612
466 | B1.31 22 00.01 | Earth Work & Site Grading (Roadway Excavation/cuttings) | 2026-07-01 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0628-00 | Check Coordinates and bottom level Road/carriageway Excavation/cutting upto bottom of Sub-Grade STA: 5+800 to STA: 6+030 at Road # MC20 | 13.58 | 6,658.16 | 100% | 13.58 | 90417.8128
467 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-02 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0636-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer at PLOT (5), STA: 0+360 to STA: 0+570 | 22.31 | 7,157.04 | 100% | 22.31 | 159673.5624
468 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-04 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0637-00 | Check Coordinates level and Compaction F.D.T for Embankment 14th layer at Road/Carriageway # MCZ0, STA: 0+170 to STA: 0+310 (Bottom Subgrade) | 22.31 | 1,275.05 | 100% | 22.31 | 28446.3655
469 | B6.33 05 39.9 | Storm Water Network: Manhole 2000mm dia (Depth > 2.5m) | 2026-07-02 | SUD1-02-011-TDC-TS9-1-STR-FIR-0638-00 | Check Installation of Manhole Base (Rings not required) MH – G2/6/2 at Road MCG0 | 30133.35 | 01 | 25% | 7533.3375 | 7533.3375
470 | B6.33 05 39.9 | Storm Water Network: Manhole 2000mm dia (Depth > 2.5m) | 2026-07-02 | SUD1-02-011-TDC-TS9-1-STR-FIR-0639-00 | Check Installation of Manhole Base (Rings not required) MH –G2/6/1at Road MCG0 | 30133.35 | 01 | 25% | 7533.3375 | 7533.3375
471 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-02 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0640-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Left side) Embankment 2nd layer at Road # MC20, STA: 4+530 to STA: 4+820 | 22.31 | 668.12 | 100% | 22.31 | 14905.7572
472 | B1.31 22 00.01 | Earth Work & Site Grading (Roadway Excavation/cuttings) | 2026-07-04 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0648-00 | Check Coordinates and bottom level Road/Carriageway Excavation/cutting upto bottom of Sub-Grade STA: 1+200 to STA: 1+430 at Road # MCB0 | 13.58 | 2,978.19 | 100% | 13.58 | 40443.8202
473 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0650-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-49-6 to MH-50-1 at Road MCD0 | 212.41 | 67.70 | 45% | 95.5845 | 6471.0707
474 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0651-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-49-7 to MH-49-8 at Road MCE0 | 221.14 | 48.80 | 45% | 99.513 | 4856.2344
475 | B5 33.05.13.01 | Sewerage Network: Manhole (Depth 0 m to 1.5m) internal dia 1200 mm | 2026-07-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0652-00 | Check Installation of Manhole Base(Rings not required) MH- 1-91-1 at Road MCA0 | 8820.42 | 01 | 25% | 2205.105 | 2205.105
476 | B5 33.05.13.05 | Sewerage Network: Manhole (Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-07-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0653-00 | Check Installation of Manhole Base MH- 1-89 at Road MCA0 | 15848.43 | 01 | 25% | 3962.1075 | 3962.1075
477 | B5 33.05.13.05 | Sewerage Network: Manhole (Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-07-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0654-00 | Check Installation of Manhole Base MH- 1-90 at Road MCA0 | 15848.43 | 01 | 25% | 3962.1075 | 3962.1075
478 | B5 33.05.13.01 | Sewerage Network: Manhole (Depth 0 m to 1.5m) internal dia 1200 mm | 2026-07-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0655-00 | Check Installation of Manhole Base(Rings not required) MH- 1-91-2 at Road MCA0 | 8820.42 | 01 | 25% | 2205.105 | 2205.105
479 | B5 33.05.13.06 | Sewerage Network: Manhole Depth 2.51m to 3.5m) internal dia 1200 mm with backdrop | 2026-07-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0656-00 | Check Installation of Manhole Base MH- 1-91 at Road MCA0 | 19018.11 | 01 | 5% | 950.9055 | 950.9055
480 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-12 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0657-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-21-2 to MH-12-21-3 at Road MCD0 | 212.41 | 78.85 | 100% | 212.41 | 16748.5285
481 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0658-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-88-4 to MH-1-88-5 at Road MCD0 | 212.41 | 98.74 | 5% | 10.6205 | 1048.6682
482 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0659-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-88-3 to MH-1-88-4 at Road MCD0 | 221.14 | 96.68 | 5% | 11.057 | 1068.9908
483 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0660-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-21-1 to MH-12-21-1-1 at Road MCD0 | 221.14 | 78.87 | 5% | 11.057 | 872.0656
484 | B5 33.05.13.01 | Sewerage Network: Manhole (Depth 0 m to 1.5m) internal dia 1200 mm | 2026-07-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0661-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 12-21-3 at Road MCD0 | 8820.42 | 01 | 5% | 441.021 | 441.021
485 | B5 33.05.13.01 | Sewerage Network: Manhole (Depth 0 m to 1.5m) internal dia 1200 mm | 2026-07-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0662-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 12-21-2 at Road MCD0 | 8820.42 | 01 | 5% | 441.021 | 441.021
486 | B5 33.05.13.01 | Sewerage Network: Manhole (Depth 0 m to 1.5m) internal dia 1200 mm | 2026-07-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0663-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-88-5 at Road MCD0 | 8820.42 | 01 | 5% | 441.021 | 441.021
487 | B5 33.05.13.01 | Sewerage Network: Manhole (Depth 0 m to 1.5m) internal dia 1200 mm | 2026-07-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0664-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-88-4 at Road MCD0 | 8820.42 | 01 | 5% | 441.021 | 441.021
488 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0665-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-88-3 at Road MCD0 | 12377.1 | 01 | 5% | 618.855 | 618.855
489 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0666-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 12-21-1 at Road MCD0 | 12377.1 | 01 | 5% | 618.855 | 618.855
490 | B5 33.05.13.01 | Sewerage Network: Manhole (Depth 0 m to 1.5m) internal dia 1200 mm | 2026-07-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0667-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 12-21-1-1 at Road MCD0 | 8820.42 | 01 | 5% | 441.021 | 441.021
491 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-04 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0672-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at PLOT (5), STA: 0+240 to STA: 0+360 | 22.31 | 3,536.89 | 100% | 22.31 | 78908.0159
492 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-05 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0680-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-1-91-2 to MH-1-91-1 at Road MCA0 | 212.41 | 78.80 | 45% | 95.5845 | 7532.0586
493 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-07 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0681-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at PLOT (2), STA: 0+570 to STA: 0+720 | 22.31 | 4,220.29 | 100% | 22.31 | 94154.6699
494 | B5 33.05.13.01 | Sewerage Network: Manhole (Depth 0 m to 1.5m) internal dia 1200 mm | 2026-07-05 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0682-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-88-2-2 at Road MCD0 | 8820.42 | 01 | 5% | 441.021 | 441.021
495 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-05 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0683-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-88-2-1 at Road MCD0 | 12377.1 | 01 | 5% | 618.855 | 618.855
496 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-05 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0684-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-88-2 at Road MCD0 | 12377.1 | 01 | 5% | 618.855 | 618.855
497 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-05 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0685-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-88-1 at Road MCD0 | 12377.1 | 01 | 5% | 618.855 | 618.855
498 | B5 33.05.13.05 | Sewerage Network: Manhole (Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-07-05 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0686-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-92 at Road MCC0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
499 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-05 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0687-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-88-2-2 to MH-1-88-2-1 at Road MCD0 | 212.41 | 98.74 | 5% | 10.6205 | 1048.6682
500 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-05 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0688-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-88-2-1 to MH-1-88-2 at Road MCD0 | 212.41 | 97.13 | 5% | 10.6205 | 1031.5692
501 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-05 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0689-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-88-2 to MH-1-88-1 at Road MCD0 | 212.41 | 42.49 | 5% | 10.6205 | 451.265
502 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-05 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0690-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-93 to MH-1-92 at Road MCC0 | 221.14 | 42.50 | 5% | 11.057 | 469.9225
503 | B6.33 05 39.6 | Storm Water Network: Manhole 1500mm dia (Depth > 2.5m) | 2026-07-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-0691-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit MH- G2/16/6 at Road MCE0 | 19537.02 | 01 | 5% | 976.851 | 976.851
504 | B6.33 05 39.3 | Storm Water Network: Manhole 1200mm dia (Depth > 2.5m) | 2026-07-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-0692-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit MH- G2/16/7 at Road MCE0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
505 | B6.33 05 39.6 | Storm Water Network: Manhole 1500mm dia (Depth > 2.5m) | 2026-07-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-0693-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit MH- G2/11/4 at Road MCF0 | 19537.02 | 01 | 5% | 976.851 | 976.851
506 | B6.33 05 39.6 | Storm Water Network: Manhole 1500mm dia (Depth > 2.5m) | 2026-07-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-0694-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit FMH- A2/9/20-399 at Road MCF0 | 19537.02 | 01 | 5% | 976.851 | 976.851
507 | B6.33 05 39.2 | Storm Water Network : Manhole Dia 1200 mm (Depth:1.51m -2.51m) | 2026-07-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-0695-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit MH-G2/6/7 at Road MCG0 | 12376.13 | 01 | 5% | 618.8065 | 618.8065
508 | B6.33 42 11.13 | Storm Water Network : GRP Pipes 700 mm (Depth: 1.51m -2.51m) | 2026-07-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-0696-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # MH – G2/16/6 to MH – G2/16/5 at Road MCE0 | 544.12 | 69.12 | 5% | 27.206 | 1880.4787
509 | B6.33 42 11.10 | Storm Water Network : GRP Pipes 600 mm (Depth: 1.51m -2.51m) | 2026-07-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-0697-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # MH – G2/16/7 to MH – G2/16/6 at Road MCE0 | 461.68 | 73.07 | 5% | 23.084 | 1686.7479
510 | B6.33 42 11.16 | Storm Water Network : GRP Pipes 800 mm (Depth: 1.51m -2.51m) | 2026-07-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-0698-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # MH – G2/11/4 to MH – G2/11/3 at Road MCF0 | 639.17 | 89.50 | 5% | 31.9585 | 2860.2858
511 | B6.33 42 11.13 | Storm Water Network : GRP Pipes 700 mm (Depth: 1.51m -2.51m) | 2026-07-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-0699-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # FIMH – A2/9/20-399 to MH – G2/11/4 at Road MCF0 | 544.12 | 44.00 | 5% | 27.206 | 1197.064
512 | B6.33 42 11.3 | Storm Water Network : GRP Pipes 400 mm (Depth: 0m -1.5m) | 2026-07-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-0700-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # MH –G2/6/7 to MH – G2/6/6 at Road MCG0 | 300.67 | 44.79 | 5% | 15.0335 | 673.3505
513 | B1.31 22 00.01 | Earth Work & Site Grading (Roadway Excavation/cuttings) | 2026-07-05 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0701-00 | Check Coordinates and bottom level Road/Carriageway cutting and compaction test of bottom Sub-Grade at Road # MC10 STA: 3+120 to STA: 3+350 | 13.58 | 3733.30 | 100% | 13.58 | 50698.214
514 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0705-01 | Check Coordinates level and compaction F.D.T for Trench Backfilling 1st layer Between Manholes # MH 52-3 to MH 52-4 at Road MCF0 | 221.14 | 98.80 | 15% | 33.171 | 3277.2948
515 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0706-01 | Check Coordinates level and compaction F.D.T for Trench Backfilling 1st layer Between Manholes # MH 52-4 to MH 52-5 at Road MCF0 | 221.14 | 58.8 | 15% | 33.171 | 1950.4548
516 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-05 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0707-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling 1st layer Between Manholes # MH 52-5 to MH 52-6 at Road MCF0 | 221.14 | 58.80 | 15% | 33.171 | 1950.4548
517 | B1.31 22 00.01 | Earth Work & Site Grading (Roadway Excavation/cuttings) | 2026-07-07 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0708-01 | Check Coordinates and bottom level Road/Carriageway Excavation/cutting upto bottom of Sub-Grade STA: 0+300 to STA: 0+440 at Road # MCH0 | 13.58 | 404.42 | 100% | 13.58 | 5492.0236
518 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-05 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0709-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Left side)Embankment 3rd layer at Road # MC20, STA: 4+820 to STA: 5+010 | 22.31 | 392.99 | 100% | 22.31 | 8767.6069
519 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-05 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0710-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at PLOT (5), STA: 0+570 to STA: 0+690 | 22.31 | 4,321.52 | 100% | 22.31 | 96413.1112
520 | B5 33.05.13.05 | Sewerage Network: Manhole (Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-07-06 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0711-00 | Check Installation of Manhole Base MH-1-93 at Road MCC0 | 15848.43 | 01 | 25% | 3962.1075 | 3962.1075
521 | B5 33.05.13.05 | Sewerage Network: Manhole (Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-07-06 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0712-00 | Check Installation of Manhole Base MH-1-94 at Road MCC0 | 15848.43 | 01 | 25% | 3962.1075 | 3962.1075
522 | B5 33.05.13.05 | Sewerage Network: Manhole (Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-07-06 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0713-00 | Check Installation of Manhole Base MH-1-95 at Road MCC0 | 15848.43 | 01 | 25% | 3962.1075 | 3962.1075
523 | B5 33.05.13.05 | Sewerage Network: Manhole (Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-07-06 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0714-00 | Check Installation of Manhole Base MH-1-96 at Road MCC0 | 15848.43 | 01 | 25% | 3962.1075 | 3962.1075
524 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-06 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0715-00 | Check Installation of Manhole Base (Rings not required) MH-1-97 at Road MCC0 | 12377.1 | 01 | 25% | 3094.275 | 3094.275
525 | B6.33 05 39.3 | Storm Water Network: Manhole 1200mm dia (Depth > 2.5m) | 2026-07-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-0716-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit MH- G2/11/5 at Road MCF0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
526 | B6.33 05 39.3 | Storm Water Network: Manhole 1200mm dia (Depth > 2.5m) | 2026-07-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-0717-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit FMH- A2/9/20-397 at Road MCF0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
527 | B6.33 05 39.2 | Storm Water Network : Manhole Dia 1200 mm (Depth:1.51m -2.51m) | 2026-07-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-0718-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit MH- G2/11/6 at Road MCF0 | 12376.13 | 01 | 5% | 618.8065 | 618.8065
528 | B6.33 05 39.2 | Storm Water Network : Manhole Dia 1200 mm (Depth:1.51m -2.51m) | 2026-07-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-0719-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit MH- G2/11/7 at Road MCF0 | 12376.13 | 01 | 5% | 618.8065 | 618.8065
529 | B6.33 42 11.10 | Storm Water Network : GRP Pipes 600 mm (Depth: 1.51m -2.51m) | 2026-07-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-0720-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # FMH – A2/9/20-399 to MH – G2/11/5 at Road MCF0 | 461.68 | 44.16 | 5% | 23.084 | 1019.3894
530 | B6.33 42 11.7 | Storm Water Network:GRP Pipes 500 mm dia (Depth 1.51m to 2.5m) | 2026-07-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-0721-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # MH – G2/11/5 to FMH – A2/9/20-397 at Road MCF0 | 379.24 | 44.27 | 5% | 18.962 | 839.4477
531 | B6.33 42 11.4 | Storm Water Network:GRP Pipes 400 mm dia (Depth 1.51m to 2.5m) | 2026-07-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-0722-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # FMH – A2/9/20-397 to MH – G2/11/6 at Road MCF0 | 312.31 | 40.30 | 5% | 15.6155 | 629.3047
532 | B6.33 42 11.4 | Storm Water Network:GRP Pipes 400 mm dia (Depth 1.51m to 2.5m) | 2026-07-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-0723-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # MH – G2/11/6 to MH – G2/11/7 at Road MCF0 | 312.31 | 43.80 | 5% | 15.6155 | 683.9589
533 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-06 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0733-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Left side) Embankment 4th layer at Road # MC20, STA: 5+010 to STA: 5+230 | 22.31 | 507.97 | 100% | 22.31 | 11332.8107
534 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-06 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0740-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH 49-6 to MH 50-1 at Road MCD0 | 212.41 | 67.70 | 10% | 21.241 | 1438.0157
535 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-06 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0741-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH 49-7 to MH 49-8 at Road MCE0 | 221.14 | 48.80 | 10% | 22.114 | 1079.1632
536 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-06 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0742-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right side) Embankments 2nd layer at Road # MC20, STA: 4+530 to STA: 4+820 | 22.31 | 551.07 | 100% | 22.31 | 12294.3717
537 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-07 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0743-00 | Check Coordinates level and Compaction F.D.T for Embankment at (Road & Shoulders) 4th layer at Road # MCE0, STA: 0+50 to STA: 0+200 (Bottom Subgrade) | 22.31 | 1,476.00 | 100% | 22.31 | 32929.56
538 | B6.33 05 39.6 | Storm Water Network: Manhole 1500mm dia (Depth > 2.5m) | 2026-07-07 | SUD1-02-011-TDC-TS9-1-STR-FIR-0751-00 | Check Installation of Manhole Base(Rings not required) MH–G2/6/3 at Road MCG0 | 19537.02 | 01 | 30% | 5861.106 | 5861.106
539 | B6.33 05 39.9 | Storm Water Network: Manhole 2000mm dia (Depth > 2.5m) | 2026-07-07 | SUD1-02-011-TDC-TS9-1-STR-FIR-0752-00 | Check Installation of Manhole Base MH –G2/11/1 at Road MCF0 | 30133.35 | 01 | 30% | 9040.005 | 9040.005
540 | B6.33 05 39.9 | Storm Water Network: Manhole 2000mm dia (Depth > 2.5m) | 2026-07-07 | SUD1-02-011-TDC-TS9-1-STR-FIR-0753-00 | Check Installation of Manhole Base MH –G2/16/1 at Road MCE0 | 30133.35 | 01 | 30% | 9040.005 | 9040.005
541 | B6.33 05 39.9 | Storm Water Network: Manhole 2000mm dia (Depth > 2.5m) | 2026-07-07 | SUD1-02-011-TDC-TS9-1-STR-FIR-0754-00 | Check Installation of Manhole Base MH –G2/16/4 at Road MCE0 | 30133.35 | 01 | 30% | 9040.005 | 9040.005
542 | B6.33 05 39.9 | Storm Water Network: Manhole 2000mm dia (Depth > 2.5m) | 2026-07-07 | SUD1-02-011-TDC-TS9-1-STR-FIR-0755-00 | Check Installation of Manhole Base MH –G2/16/3 at Road MCE0 | 30133.35 | 01 | 30% | 9040.005 | 9040.005
543 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-07 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0756-00 | Check Coordinates level and Compaction F.D.T for Embankment 7th layer at PLOT (3), STA: 0+060 to STA: 0+160 | 22.31 | 2,804.08 | 100% | 22.31 | 62559.0248
544 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-07 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0757-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer at PLOT (5), STA: 0+240 to STA: 0+360 | 22.31 | 3,758.59 | 100% | 22.31 | 83854.1429
545 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-07 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0758-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right side) Embankment 1st layer at Road # MCB0, STA: 0+580 to STA: 0+660 | 22.31 | 142.20 | 100% | 22.31 | 3172.482
546 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-07 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0759-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right side) Embankment 3rd layer at Road # MC20, STA: 4+820 to STA: 5+010 | 22.3 | 326.32 | 100% | 22.3 | 7276.936
547 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-08 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0760-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right side) Embankment 4th layer at Road # MC20, STA: 5+010 to STA: 5+230 | 22.31 | 475.95 | 100% | 22.31 | 10618.4445
548 | B6.33 42 11.3 | Storm Water Network:GRP Pipes 400 mm dia (Depth 0m to 1.5m) | 2026-07-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-0763-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/6/6 to FMH-A2/9/20-396 at Road MCG0 | 300.68 | 39.34 | 10% | 30.068 | 1182.8751
549 | B5 33.05.13.06 | Sewerage Network: Manhole Depth 2.51m to 3.5m) internal dia 1200 mm with backdrop | 2026-07-08 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0764-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 1-88 at Road MCA0 at Road MCA0 | 19018.11 | 01 | 5% | 950.9055 | 950.9055
550 | B5 33.05.13.05 | Sewerage Network: Manhole (Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-07-08 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0765-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-87 at Road MCA0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
551 | B5 33.05.13.06 | Sewerage Network: Manhole Depth 2.51m to 3.5m) internal dia 1200 mm with backdrop | 2026-07-08 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0766-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-86 at Road MCA0 | 19018.11 | 01 | 5% | 950.9055 | 950.9055
552 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-08 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0767-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-89 to MH-1-88 at Road MCA0 | 221.14 | 99.63 | 5% | 11.057 | 1101.6089
553 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-08 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0768-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-88 to MH-1-87 at Road MCA0 | 221.14 | 100.98 | 5% | 11.057 | 1116.5359
554 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-08 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0769-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-87 to MH-1-86 at Road MCA0 | 221.14 | 100.44 | 5% | 11.057 | 1110.5651
555 | B6.33 42 11.10 | Storm Water Network : GRP Pipes 600 mm (Depth: 1.51m -2.51m) | 2026-07-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-0770-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from Manhole # FMH-A2/9/20-398 to MH-G2/6/5 at Road MCG0 | 461.68 | 44.19 | 5% | 23.084 | 1020.082
556 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-08 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0771-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right & Left side) Embankment 2nd layer at Road # MC20, STA: 5+230 to STA: 5+280 | 22.31 | 336.33 | 100% | 22.31 | 7503.5223
557 | B6.33 05 39.3 | Storm Water Network: Manhole 1200mm dia (Depth > 2.5m) | 2026-07-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-0772-00 | Check Installation of Manhole Base(Rings not required) MH –G2/16/7 at Road MCE0 | 15848.43 | 01 | 25% | 3962.1075 | 3962.1075
558 | B6.33 05 39.6 | Storm Water Network: Manhole 1500mm dia (Depth > 2.5m) | 2026-07-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-0773-00 | Check Installation of Manhole Base MH –G2/16/6 at Road MCE0 | 19537.02 | 01 | 25% | 4884.255 | 4884.255
559 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-08 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0774-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right side) Embankment 1st layer at Road # MCB0, STA: 0+760 to STA: 1+000 | 22.31 | 342.71 | 100% | 22.31 | 7645.8601
560 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-11 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0776-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling 5th and last layer Between Manholes # MH 51-3 to MH 51-4 at Road MCE0 | 221.14 | 98.80 | 5% | 11.057 | 1092.4316
561 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-11 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0777-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling 5th and layer Between Manholes # MH 51-2 to MH 51-3 at Road MCE0 | 221.14 | 98.80 | 5% | 11.057 | 1092.4316
562 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-11 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0779-01 | Check Coordinates level and Compaction F.D.T for Embankment 6th layer at PLOT (5), STA: 0+360 to STA: 0+570 | 22.31 | 7,078.53 | 100% | 22.31 | 157922.0043
563 | B6.33 05 39.9 | Storm Water Network: Manhole 2000mm dia (Depth > 2.5m) | 2026-07-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-0785-00 | Check Installation of Manhole Base MH –G2/16/2 at Road MCE0 | 30133.35 | 1 | 25% | 7533.3375 | 7533.3375
564 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-07-08 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0786-00 | Inspection Gravity and Leakage test pipline from Manhole # MH-1-91-2 to MH-1-91-1 at Road MCA0 | 212.41 | 78.80 | 10% | 21.241 | 1673.7908
565 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-08 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0787-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-53-1 to MH-53-2 at Road MCF0 | 221.14 | 98.80 | 45% | 99.513 | 9831.8844
566 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-08 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0788-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-53-2 to MH-53-3 at Road MCF0 | 221.14 | 98.80 | 45% | 99.513 | 9831.8844
567 | B6.33 42 11.22 | Storm Water Network : Manhole for GRP Pipes 1000mm (Depth: 1.51m -2.51m) | 2026-07-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-0790-01 | Inspection Gravity and Leakage test pipeline from Manhole # MH G2/6/1 to MHG2/6/2 at Road MCG0 | 884.56 | 89.00 | 10% | 88.456 | 7872.584
568 | B1.31 22 00.04 | Embankments to the Plot | 2026-07-14 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0798-01 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at PLOT (5), STA: 0+570 to STA: 0+660 | 22.31 | 3,196.21 | 100% | 22.31 | 71307.4451
569 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-09 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0799-00 | Check Coordinates level and Compaction F.D.T for Embankment 7th layer at Road/Carriageway and Right Side Shoulder # MCG0, STA: 0+060 to STA: 0+150 | 22.31 | 254.00 | 100% | 58.8 | 14935.2
570 | B5 33.05.13.05 | Sewerage Network: Manhole (Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-07-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0800-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-85 at Road MCA0 | 15848.43 | 01 | 5% | 58.8 | 58.8
571 | B5 33.05.13.06 | Sewerage Network: Manhole Depth 2.51m to 3.5m) internal dia 1200 mm with backdrop | 2026-07-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0801-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-84 at Road MCA0 | 19018.11 | 01 | 5% | 950.9055 | 950.9055
572 | B5 33.05.13.05 | Sewerage Network: Manhole (Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-07-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0802-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-83 at Road MCA0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
573 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0803-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-82 at Road MCA0 | 12377.1 | 01 | 5% | 618.855 | 618.855
574 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0804-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-81 at Road MCA0 | 12377.1 | 01 | 5% | 618.855 | 618.855
575 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0805-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-80 at Road MCA0 | 12377.1 | 01 | 5% | 618.855 | 618.855
576 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0806-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-85 to MH-1-86 at Road MCA0 | 221.14 | 82.15 | 5% | 11.057 | 908.3326
577 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0807-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-84 to MH-1-85 at Road MCA0 | 221.14 | 83.80 | 5% | 11.057 | 926.5766
578 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0808-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-83 to MH-1-84 at Road MCA0 | 221.14 | 83.80 | 5% | 11.057 | 926.5766
579 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0809-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-82 to MH-1-83 at Road MCA0 | 221.14 | 83.76 | 5% | 11.057 | 926.1343
580 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0810-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-81 to MH-1-82 at Road MCA0 | 212.41 | 98.84 | 5% | 10.6205 | 1049.7302
581 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0811-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-80 to MH-1-81 at Road MCA0 | 212.41 | 98.80 | 5% | 10.6205 | 1049.3054
582 | B6.33 42 11.13 | Storm Water Network : GRP Pipes 700 mm (Depth: 1.51m -2.51m) | 2026-07-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-0812-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from Manhole # MH-G2/6/4 to FMH-A2/9/20-398 at Road MCG0 | 544.12 | 43.96 | 5% | 27.206 | 1195.9758
583 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0816-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-1-89 to MH-1-90 at Road MCA0 | 221.14 | 101.80 | 45% | 99.513 | 10130.4234
584 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-08-26 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0817-02 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-1-91-1 to MH-1-91 at Road MCA0 | 212.41 | 78.20 | 0% | 0 | 0
585 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0818-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-1-90 to MH-1-91 at Road MCA0 | 221.14 | 101.30 | 45% | 99.513 | 10080.6669
586 | B6.33 42 11.7 | Storm Water Network:GRP Pipes 500 mm dia (Depth 1.51m to 2.5m) | 2026-07-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-0819-00 | Inspection Gravity and Leakage test pipeline from Manhole # FMH-A2/9/20-396 to MH-G2/6/5 at Road MCG0 | 379.24 | 44.24 | 10% | 37.924 | 1677.7578
587 | B6.31 22 00 | Drainage Work for Pond amd Open Canals | 2026-07-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-0820-00 | Check Coordinates level, protection side slope, Bottom level Excavation and Compaction F.D.T for Pond B | 17.46 | 29646.88 | 100% | 17.46 | 517634.5248
588 | B6.33 05 39.15 | Storm Water Network:Catch Basin ( Single) | 2026-07-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-0821-02 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/6 (S) at Road MCG0 | 5124.07 | 1 | 5% | 256.2035 | 256.2035
589 | B6.33 05 39.15 | Storm Water Network:Catch Basin ( Single) | 2026-07-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-0822-01 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/6/1 A(S) at Road MCG0 | 5124.07 | 1 | 5% | 256.2035 | 256.2035
590 | B6.33 05 39.16 | Storm Water Network:Catch Basin ( Double) | 2026-07-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-0823-01 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/6/1 (D) at Road MCG0 | 12444.99 | 1 | 5% | 622.2495 | 622.2495
591 | B6.33 05 39.15 | Storm Water Network:Catch Basin ( Single) | 2026-07-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-0824-01 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/6/1 B(S) at Road MCG0 | 5124.07 | 1 | 5% | 256.2035 | 256.2035
592 | B6.33 05 39.15 | Storm Water Network:Catch Basin ( Single) | 2026-07-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-0825-01 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/6/2 A(S) at Road MCG0 | 5124.07 | 1 | 5% | 256.2035 | 256.2035
593 | B6.33 05 39.16 | Storm Water Network:Catch Basin ( Double) | 2026-07-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-0826-01 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/6/2 (D) at Road MCG0 | 12444.99 | 1 | 5% | 622.2495 | 622.2495
594 | B6.33 05 39.15 | Storm Water Network:Catch Basin ( Single) | 2026-07-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-0827-01 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/6/2 B(S)at Road MCG0 | 5124.07 | 1 | 5% | 256.2035 | 256.2035
595 | B6.33 05 39.15 | Storm Water Network:Catch Basin ( Single) | 2026-07-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-0828-01 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/6/3 A(S) at Road MCG0 | 5124.07 | 1 | 5% | 256.2035 | 256.2035
596 | B6.33 05 39.16 | Storm Water Network:Catch Basin ( Double) | 2026-07-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-0829-01 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/6/3 (D) at Road MCG0 | 12444.99 | 1 | 5% | 622.2495 | 622.2495
597 | B6.33 05 39.15 | Storm Water Network:Catch Basin ( Single) | 2026-07-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-0830-01 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/6/3 B(S)at Road MCG0 | 5124.07 | 1 | 5% | 256.2035 | 256.2035
598 | B6.33 05 39.15 | Storm Water Network:Catch Basin ( Single) | 2026-07-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-0831-01 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/6/4 A(S) at Road MCG0 | 5124.07 | 1 | 5% | 256.2035 | 256.2035
599 | B6.33 05 39.16 | Storm Water Network:Catch Basin ( Double) | 2026-07-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-0832-01 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/6/4 (D) at Road MCG0 | 12444.99 | 1 | 5% | 622.2495 | 622.2495
600 | B6.33 05 39.15 | Storm Water Network:Catch Basin ( Single) | 2026-07-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-0835-01 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/6/4 B(S) at Road MCG0 | 5124.07 | 1 | 5% | 256.2035 | 256.2035
601 | B6.33 05 39.15 | Storm Water Network:Catch Basin ( Single) | 2026-07-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-0836-01 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-A2/9/20-398 (S) at Road MCG0 | 5124.07 | 1 | 5% | 256.2035 | 256.2035
602 | B6.33 05 39.15 | Storm Water Network:Catch Basin ( Single) | 2026-07-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-0837-01 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/6/5 A (S) at Road MCG0 | 5124.07 | 1 | 5% | 256.2035 | 256.2035
603 | B6.33 05 39.15 | Storm Water Network:Catch Basin ( Single) | 2026-07-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-0838-01 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-A2/9/20-396 (S) at Road MCG0 | 5124.07 | 1 | 5% | 256.2035 | 256.2035
604 | B6.33 05 39.15 | Storm Water Network:Catch Basin ( Single) | 2026-07-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-0839-01 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/6/5 B(S) at Road MCG0 | 5124.07 | 1 | 5% | 256.2035 | 256.2035
605 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-12 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0840-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-79 to MH-1-79-1 at Road MCA0 | 212.41 | 96.31 | 5% | 10.6205 | 1022.8604
606 | B5 33.05.13.01 | Sewerage Network: Manhole (Depth 0 m to 1.5m) internal dia 1200 mm | 2026-07-12 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0841-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-79-1 at Road MCA0 | 8820.42 | 01 | 5% | 441.021 | 441.021
607 | B5 33.05.13.01 | Sewerage Network: Manhole (Depth 0 m to 1.5m) internal dia 1200 mm | 2026-07-12 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0842-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 1-79 at Road MCA0 | 8820.42 | 01 | 5% | 441.021 | 441.021
608 | B6.33 05 39.15 | Storm Water Network:Catch Basin ( Single) | 2026-07-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-0843-01 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/6/6 A(S) at Road MCG0 | 5124.07 | 1.00 | 5% | 256.2035 | 256.2035
609 | B6.33 05 39.15 | Storm Water Network:Catch Basin ( Single) | 2026-07-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-0844-01 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/6/6 B(S) at Road MCG0 | 5124.07 | 1.00 | 5% | 256.2035 | 256.2035
610 | B6.33 05 39.15 | Storm Water Network:Catch Basin ( Single) | 2026-07-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-0845-01 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/6/6 C(S) at Road MCG0 | 5124.07 | 1.00 | 5% | 256.2035 | 256.2035
611 | B6.33 05 39.15 | Storm Water Network:Catch Basin ( Single) | 2026-07-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-0846-01 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/6/7 (S) at Road MCG0 | 5124.07 | 1.00 | 5% | 256.2035 | 256.2035
612 | B6.33 42 11.10 | Storm Water Network : GRP Pipes 600 mm (Depth: 1.51m -2.51m) | 2026-07-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-0847-00 | Inspection Gravity and Leakage test pipeline from Manhole # FMH-A2/9/20-398 to MH-G2/6/5 at Road MCG0 | 461.68 | 44.19 | 10% | 46.168 | 2040.1639
613 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-11 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0848-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH 53-1 to MH 53-2 at Road MCF0 | 221.14 | 98.80 | 10% | 22.114 | 2184.8632
614 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-11 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0849-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH 53-2 to MH 53-3 at Road MCF0 | 221.14 | 98.80 | 10% | 22.114 | 2184.8632
615 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-11 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0850-00 | Check Coordinates level and Compaction F.D.T for Embankment 6th layer at PLOT (5), STA: 0+240 to STA: 0+360 | 22.31 | 3,845.54 | 100% | 22.31 | 85793.9974
616 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-11 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0851-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right & Left side) Embankment 3rd layer at Road # MC20, STA: 5+420 to STA: 5+500 | 22.31 | 309.84 | 100% | 22.31 | 6912.5304
617 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-11 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0852-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right & Left side) Embankment 2nd layer at Road # MC20, STA: 5+500 to STA: 5+620 | 22.31 | 894.70 | 100% | 22.31 | 19960.757
618 | B6.33 42 11.16 | Storm Water Network : GRP Pipes 800 mm (Depth: 1.51m -2.51m) | 2026-07-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-0853-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from Manhole # MH-G2/11/3 to MH-G2/11/4 at Road MCF0 | 639.17 | 89.50 | 45% | 287.6265 | 25742.5717
619 | B6.33 42 11.3 | Storm Water Network : GRP Pipes 700 mm (Depth: 1.51m -2.51m) | 2026-07-25 | SUD1-02-011-TDC-TS9-1-STR-FIR-0854-03 | Check Sand Bedding and GRP Pipe Installation for Storm water line from Manhole # MH-G2/6/6 to MH-G2/6/7 at Road MCG0 | 544.12 | 44.79 | 45% | 244.854 | 10967.0107
620 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-14 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0858-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 12-11-2 at Road MCG0 | 12377.1 | 01 | 5% | 618.855 | 618.855
621 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-12 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0859-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 12-11-3 at Road MCG0 | 12377.1 | 01 | 5% | 618.855 | 618.855
622 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-14 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0860-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 12-11-4 at Road MCG0 | 12377.1 | 01 | 5% | 618.855 | 618.855
623 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-14 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0861-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 12-11-1 at Road MCG0 | 12377.1 | 01 | 5% | 618.855 | 618.855
624 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-12 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0862-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 12-11-1-1 at Road MCG0 | 12377.1 | 01 | 5% | 618.855 | 618.855
625 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-14 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0863-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 12-11-1-2 at Road MCG0 | 12377.1 | 01 | 5% | 618.855 | 618.855
626 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-12 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0864-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-11-3 to MH-12-11-2 at Road MCG0 | 212.41 | 78.84 | 5% | 10.6205 | 837.3202
627 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-12 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0865-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-11-4 to MH-12-11-3 at Road MCG0 | 212.41 | 98.86 | 5% | 10.6205 | 1049.9426
628 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-12 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0866-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-11-1 to MH-12-11-1-1 at Road MCG0 | 212.41 | 78.87 | 5% | 10.6205 | 837.6388
629 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-12 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0867-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-11-1-1 to MH-12-11-1-2 at Road MCG0 | 212.41 | 98.86 | 5% | 10.6205 | 1049.9426
630 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-12 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0875-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-53-3 to MH-53-4 at Road MCF0 | 221.14 | 98.80 | 45% | 99.513 | 9831.8844
631 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-12 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0876-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from Existing manhole # MH-39-22 to MH-53-1 at Road MCF0 | 221.14 | 98.80 | 45% | 99.513 | 9831.8844
632 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-15 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0877-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right side) Embankments 3rd layer at Road # MC20, STA: 4+530 to STA: 4+820 | 22.31 | 608.13 | 100% | 22.31 | 13567.3803
633 | B6.33 42 11.7 | Storm Water Network:GRP Pipes 500 mm dia (Depth 1.51m to 2.5m) | 2026-07-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-0884-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from Manhole # MH-G2/11/5 to FMH-A2/9/20-397 at Road MCF0 | 379.24 | 44.27 | 45% | 170.658 | 7555.0297
634 | B6.33 42 11.4 | Storm Water Network:GRP Pipes 400 mm dia (Depth 1.51m to 2.5m) | 2026-07-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-0885-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from Manhole # MH-G2/11/6 to MH-G2/11/7 at Road MCF0 | 312.31 | 43.80 | 45% | 140.5395 | 6155.6301
635 | B6.33 05 39.6 | Storm Water Network: Manhole 1500mm dia (Depth > 2.5m) | 2026-07-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-0886-00 | Check Installation of Manhole Base FMH-A2/9/20-399 at Road MCF0 | 19537.02 | 01 | 25% | 4884.255 | 4884.255
636 | B6.33 05 39.3 | Storm Water Network: Manhole 1200mm dia (Depth > 2.5m) | 2026-07-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-0887-00 | Check Installation of Manhole Base (Rings not required) FMH-A2/9/20-397 at Road MCF0 | 15848.43 | 01 | 25% | 3962.1075 | 3962.1075
637 | B6.33 05 39.6 | Storm Water Network: Manhole 1500mm dia (Depth > 2.5m) | 2026-07-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-0888-00 | Check Installation of Manhole Base MH-G2/11/4 at Road MCF0 | 19537.02 | 01 | 25% | 4884.255 | 4884.255
638 | B6.33 05 39.6 | Storm Water Network: Manhole 1500mm dia (Depth > 2.5m) | 2026-07-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-0889-00 | Check Installation of Manhole Base MH-G2/11/3 at Road MCF0 | 19537.02 | 01 | 25% | 4884.255 | 4884.255
639 | B6.33 05 39.2 | Storm Water Network : Manhole Dia 1200 mm (Depth:1.51m -2.51m) | 2026-07-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-0890-00 | Check Installation of Manhole Base (Rings not required) MH-G2/11/7 at Road MCF0 | 12376.13 | 01 | 25% | 3094.0325 | 3094.0325
640 | B6.33 05 39.2 | Storm Water Network : Manhole Dia 1200 mm (Depth:1.51m -2.51m) | 2026-07-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-0891-00 | Check Installation of Manhole Base (Rings not required) MH-G2/11/6 at Road MCF0 | 12376.13 | 01 | 25% | 3094.0325 | 3094.0325
641 | B6.33 05 39.9 | Storm Water Network: Manhole 2000mm dia (Depth > 2.5m) | 2026-07-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-0892-00 | Check Installation of Manhole Base MH-G2/11/2 at Road MCF0 | 30133.35 | 01 | 25% | 7533.3375 | 7533.3375
642 | B6.33 05 39.6 | Storm Water Network: Manhole 1500mm dia (Depth > 2.5m) | 2026-07-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-0893-00 | Check Installation of Manhole Base MH-G2/16/5 at Road MCE0 | 19537.02 | 01 | 25% | 4884.255 | 4884.255
643 | B6.33 05 39.2 | Storm Water Network : Manhole Dia 1200 mm (Depth:1.51m -2.51m) | 2026-07-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-0894-00 | Check Installation of Manhole Base(Rings not required) MH-G2/6/7 at Road MCG0 | 12376.13 | 01 | 25% | 3094.0325 | 3094.0325
644 | B6.33 05 39.3 | Storm Water Network: Manhole 1200mm dia (Depth > 2.5m) | 2026-07-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-0895-00 | Check Installation of Manhole Base (Rings not required) MH-G2/11/5 at Road MCF0 | 15848.43 | 01 | 25% | 3962.1075 | 3962.1075
645 | B6.33 05 39.6 | Storm Water Network: Manhole 1500mm dia (Depth > 2.5m) | 2026-07-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-0896-00 | Check Installation of Manhole Base MH-G2/6/4(Rings not required) at Road MCG0 | 19537.02 | 01 | 25% | 4884.255 | 4884.255
646 | B6.33 42 11.10 | Storm Water Network : GRP Pipes 600 mm (Depth: 1.51m -2.51m) | 2026-07-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-0897-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from Manhole # FMH-A2/9/20-399 to MH-G2/11/5 at Road MCF0 | 461.68 | 44.16 | 45% | 207.756 | 9174.505
647 | B6.33 42 11.4 | Storm Water Network:GRP Pipes 400 mm dia (Depth 1.51m to 2.5m) | 2026-07-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-0898-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from Manhole # FMH-A2/9/20-397 to MH-G2/11/6 at Road MCF0 | 312.31 | 40.30 | 45% | 140.5395 | 5663.7418
648 | B6.33 42 11.13 | Storm Water Network : GRP Pipes 700 mm (Depth: 1.51m -2.51m) | 2026-07-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-0899-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from Manhole # MH-G2/11/4 to FMH-A2/9/20-399 at Road MCF0 | 544.12 | 44.00 | 45% | 244.854 | 10773.576
649 | B5 33.05.13.05 | Sewerage Network: Manhole (Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-07-13 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0900-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 12-16 at Road MCI0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
650 | B5 33.05.13.05 | Sewerage Network: Manhole (Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-07-13 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0901-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 12-15 at Road MCB0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
651 | B5 33.05.13.05 | Sewerage Network: Manhole (Depth 2.51m to 3.5m) internal dia 1200 mm | 2026-07-13 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0902-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 12-14 at Road MCB0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
652 | B5 33.05.13.06 | Sewerage Network: Manhole Depth 2.51m to 3.5m) internal dia 1200 mm with backdrop | 2026-07-13 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0903-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 12-13 at Road MCB0 | 19018.11 | 01 | 5% | 950.9055 | 950.9055
653 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-13 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0904-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-17 to MH-12-16 at Road MCI0 | 221.14 | 39.80 | 5% | 11.057 | 440.0686
654 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-13 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0905-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-16 to MH-12-15 at Road MCB0 | 221.14 | 41.62 | 5% | 11.057 | 460.1923
655 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-13 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0906-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-15 to MH-12-14 at Road MCB0 | 221.14 | 74.30 | 5% | 11.057 | 821.5351
656 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-13 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0907-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-14 to MH-12-13 at Road MCB0 | 221.14 | 58.85 | 5% | 11.057 | 650.7045
657 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-14 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0921-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at PLOT (2), STA: 0+570 to STA: 0+720 | 22.31 | 4,696.39 | 100% | 22.31 | 104776.4609
658 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-13 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0924-00 | Inspection Gravity and Leakage test pipeline from Existing Manhole # MH-39-22 to MH-53-1 at Road MCF0 | 221.14 | 98.80 | 10% | 22.114 | 2184.8632
659 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-13 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0925-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-53-4 to MH-53-3 at Road MCF0 | 221.14 | 98.80 | 10% | 22.114 | 2184.8632
660 | B5 33.05.13.04 | Sewerage Network:Manhole (Depth 1.51m to 2.5m) int dia with backdrop | 2026-07-14 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0926-00 | Check Installation of Manhole Base (Rings not required) MH-12-19 at Road MCB0 | 14852.32 | 01 | 25% | 3713.08 | 3713.08
661 | B5 33.05.13.04 | Sewerage Network:Manhole (Depth 1.51m to 2.5m) int dia with backdrop | 2026-07-26 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0927-01 | Check Installation of Manhole Base (Rings not required) MH-12-20 at Road MCB0 | 14852.32 | 1 | 25% | 3713.08 | 3713.08
662 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-14 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0928-00 | Check Installation of Manhole Base (Rings not required) MH-12-24 at Road MCB0 | 12377.1 | 01 | 25% | 3094.275 | 3094.275
663 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-14 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0929-00 | Check Installation of Manhole Base (Rings not required) MH-12-25 at Road MCB0 | 12377.1 | 01 | 25% | 3094.275 | 3094.275
664 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-14 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0930-00 | Check Installation of Manhole Base (Rings not required) MH-12-26 at Road MCB0 | 12377.1 | 01 | 25% | 3094.275 | 3094.275
665 | B5 33.05.13.01 | Sewerage Network: Manhole (Depth 0 m to 1.5m) internal dia 1200 mm | 2026-07-14 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0931-00 | Check Installation of Manhole Base (Rings not required) MH-1-98 at Road MCC0 | 8820.42 | 01 | 25% | 2205.105 | 2205.105
666 | B2.33 71 19.02 | Road Crossing ducts, 4 ways ( 4 x 150 mm PVC) | 2026-07-14 | SUD1-02-011-TDC-TS9-1-LIT-FIR-0936-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (4X160mm) from Manhole 19 To Manhole 20 for Street Lighting Duct Bank in road MCG0 | 617.84 | 16.45 | 25% | 154.46 | 2540.867
667 | B2.33 71 19.01 | Road Crossing ducts, 2 ways ( 2 x 150 mm PVC) | 2026-07-14 | SUD1-02-011-TDC-TS9-1-LIT-FIR-0937-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (2X160mm) from Manhole 21 To Manhole 22 for Street Lighting Duct Bank in road MCG0 | 308.43 | 15.20 | 10% | 30.843 | 468.8136
668 | B6.33 42 11.19 | Storm Water Network : Manhole for GRP Pipes 900mm (Depth: 1.51m -2.51m) | 2026-07-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-0949-00 | Inspection Gravity and Leakage test pipeline from Manhole MH-G2/6/3 to MH-G2/6/2. at Road MCG0 | 743.93 | 89.25 | 10% | 74.393 | 6639.5752
669 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-14 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0950-00 | Check Coordinates level and Compaction F.D.T for Embankment 7th layer at PLOT (5), STA: 0+360 to STA: 0+560 | 22.31 | 6,586.78 | 100% | 22.31 | 146951.0618
670 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-14 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0953-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Left side) Embankment 3rd layer at Road # MC20, STA: 4+530 to STA: 4+820 | 22.31 | 609.37 | 100% | 22.31 | 13595.0447
671 | B6.33 05 39.5 | Storm Water Network : Manhole Dia 1500 mm (Depth:1.51m -2.51m) | 2026-07-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-0965-00 | Check Installation of Manhole Base (Rings not required) FMH – A2/9/20-398 at Road MCG0 | 15295.58 | 01 | 25% | 3823.895 | 3823.895
672 | B6.33 42 11.13 | Storm Water Network : GRP Pipes 700 mm (Depth: 1.51m -2.51m) | 2026-07-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-0966-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from Manhole MH-G2/16/5 to MH-G2/16/6 at Road MCE0 | 544.12 | 69.12 | 45% | 244.854 | 16924.3085
673 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0967-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-12-7-1 at Road MCH0 | 12377.1 | 01 | 5% | 618.855 | 618.855
674 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0968-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-12-7-2 at Road MCH0 | 12377.1 | 01 | 5% | 618.855 | 618.855
675 | B5 33.05.13.01 | Sewerage Network: Manhole (Depth 0 m to 1.5m) internal dia 1200 mm | 2026-07-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0969-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-12-7-3 at Road MCH0 | 8820.42 | 01 | 5% | 441.021 | 441.021
676 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0978-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-7-1 to MH-12-7-2 at Road MCH0 | 212.41 | 86.38 | 5% | 10.6205 | 917.3988
677 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0979-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-7-2 to MH-12-7-3 at Road MCH0 | 212.41 | 98.86 | 100% | 212.41 | 20998.8526
678 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-16 | SUD1-02-011-TDC-TS9-1-ROD-FIR-0980-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right side) Embankment 2nd layer at Road # MCB0, STA: 0+580 to STA: 0+660 | 22.31 | 173.91 | 100% | 22.31 | 3879.9321
679 | B6.33 42 11.10 | Storm Water Network : GRP Pipes 600 mm (Depth: 1.51m -2.51m) | 2026-07-25 | SUD1-02-011-TDC-TS9-1-STR-FIR-0981-01 | Check Sand Bedding and GRP Pipe Installation for Storm water line from Manhole # MH-G2/16/6 to MH-G2/16/7 at Road MCE0 | 461.68 | 73.07 | 45% | 207.756 | 15180.7309
680 | B6.33 42 11.20 | Storm Water Network :GRP Pipes 900mm (Depth: 2.51m -3.5m) | 2026-07-16 | SUD1-02-011-TDC-TS9-1-STR-FIR-0982-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from Manhole # MH-G2/11/2 to MH-G2/11/3 at Road MCF0 | 875.83 | 89.25 | 45% | 394.1235 | 35175.5224
681 | B5 33.31.00.03 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-16 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0983-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling 6th and Last layer Between Existing Manholes # MH 39-26 to MH 51-1 at Road MCE0 | 329.77 | 98.80 | 5% | 16.4885 | 1629.0638
682 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-16 | SUD1-02-011-TDC-TS9-1-SEW-FIR-0984-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling 6th and last layer Between Manholes # MH 51-1 to MH 51-2 at Road MCE0 | 221.14 | 98.80 | 5% | 11.057 | 1092.4316
683 | B6.33 42 11.3 | Storm Water Network : GRP Pipes 700 mm (Depth: 1.51m -2.51m) |  | SUD1-02-011-TDC-TS9-1-STR-FIR-0997-01 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/6/6 to MH-G2/6/7 at Road MCG0 | 544.12 | 44.79 | 10% | 54.412 | 2437.1135
684 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-18 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1002-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-53-5 to MH-53-6 at Road MCF0 | 212.41 | 58.80 | 45% | 95.5845 | 5620.3686
685 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-18 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1003-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from Existing manhole # MH-53-4 to MH-53-5 at Road MCF0 | 212.41 | 58.80 | 45% | 95.5845 | 5620.3686
686 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-16 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1004-00 | Check Coordinates level and Compaction F.D.T for Embankment 7th layer at PLOT (5), STA: 0+240 to STA: 0+360 | 22.31 | 3,908.83 | 100% | 22.31 | 87205.9973
687 | B6.34 42 16.5 | STORM WATER NETWORK: (BOX CULVERT) | 2026-06-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-1005-00 | Check Steel Reinforcement for Precast box culverts at SACEP (Manufacturer/Supplier) production plant | 4529.51 | 22.93 | 30% | 1358.853 | 31158.4993
688 | B6.34 42 16.4 | STORM WATER NETWORK: (BOX CULVERT) | 2026-08-02 | SUD1-02-011-TDC-TS9-1-STR-FIR-1006-00 | Check precast box culvert installation from Existing Manhole # FIMH – G2/16 to MH –G2/16/1 at Road MCE0 | 792.42 | 150.94 | 30% | 237.726 | 35882.3624
689 | B6.33 42 11.16 | Storm Water Network : GRP Pipes 800 mm (Depth: 1.51m -2.51m) | 2026-07-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-1007-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/6/4 to MH-G2/6/5 at Road MCG0 | 639.17 | 89.50 | 10% | 63.917 | 5720.5715
690 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-18 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1008-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right side) Embankment 2nd layer at Road # MCB0, STA: 0+760 to STA: 1+000 | 22.31 | 604.81 | 100% | 22.31 | 13493.3111
691 | B2.33 71 19.01 | Road Crossing ducts, 2 ways ( 2 x 150 mm PVC) | 2026-07-18 | SUD1-02-011-TDC-TS9-1-LIT-FIR-1009-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (2X160mm) from Manhole 07 To Manhole 08 for Street Lighting Duct Bank in road MCE0 | 308.43 | 15.2 | 30% | 92.529 | 1406.4408
692 | B2.33 71 19.02 | Road Crossing ducts, 4 ways ( 4 x 150 mm PVC) | 2026-07-18 | SUD1-02-011-TDC-TS9-1-LIT-FIR-1010-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (4X160mm) from Manhole 09 To Manhole 10 for Street Lighting Duct Bank in road MCE0 | 617.84 | 20.24 | 30% | 185.352 | 3751.5245
693 | B2.33 71 19.01 | Road Crossing ducts, 2 ways ( 2 x 150 mm PVC) | 2026-07-18 | SUD1-02-011-TDC-TS9-1-LIT-FIR-1011-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (2X160mm) from Manhole 03 To Manhole 06 for Street Lighting Duct Bank in road MCD0 | 308.43 | 24.58 | 30% | 92.529 | 2274.3628
694 | B2.33 71 19.02 | Road Crossing ducts, 4 ways ( 4 x 150 mm PVC) | 2026-07-18 | SUD1-02-011-TDC-TS9-1-LIT-FIR-1012-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (4X160mm) from Manhole 13 To Manhole 14 for Street Lighting Duct Bank in road MCF0 | 617.84 | 16.41 | 30% | 185.352 | 3041.6263
695 | B6.33 42 11.23 | Storm Water Network :GRP Pipes 1000mm (Depth: 2.51m -3.5m) | 2026-07-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-1013-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from Manhole # MH-G2/11/1 toMH-G2/11/2 at Road MCF0 | 1017.44 | 89.00 | 45% | 457.848 | 40748.472
696 | B6.33 42 11.22 | Storm Water Network : Manhole for GRP Pipes 1000mm (Depth: 1.51m -2.51m) | 2026-07-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-1014-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from Manhole # MH-G2/16/1 to MH-G2/16/2 at Road MCE0 | 884.56 | 87.00 | 45% | 398.052 | 34630.524
697 | B6.33 42 11.13 | Storm Water Network : GRP Pipes 700 mm (Depth: 1.51m -2.51m) | 2026-07-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-1016-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/11/4 to FMH-A2/9/20-399 at Road MCF0 | 544.12 | 44.00 | 10% | 54.412 | 2394.128
698 | B6.33 42 11.10 | Storm Water Network : GRP Pipes 600 mm (Depth: 1.51m -2.51m) | 2026-07-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-1017-00 | Inspection Gravity and Leakage test pipeline from Manhole # FMH-A2/9/20-399 to MH-G2/11/5 at Road MCF0 | 461.68 | 44.16 | 10% | 46.168 | 2038.7789
699 | B6.33 42 11.7 | Storm Water Network:GRP Pipes 500 mm dia (Depth 1.51m to 2.5m) | 2026-07-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-1018-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/11/5 to FMH-A20/9/20-397 at Road MCF0 | 379.24 | 44.27 | 10% | 37.924 | 1678.8955
700 | B6.33 42 11.4 | STORM WATER NETWORK: GRP Pipes 400mm (Depth 1.51 to 2.50 m) | 2026-07-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-1019-00 | Inspection Gravity and Leakage test pipeline from Manhole # FMH-A20/9/20-397 to MH-G2/11/6 at Road MCF0 | 312.31 | 40.30 | 10% | 31.231 | 1258.6093
701 | B6.33 42 11.4 | STORM WATER NETWORK: GRP Pipes 400mm (Depth 1.51 to 2.50 m) | 2026-07-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-1020-01 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/11/6 to MH-G2/11/7 at Road MCF0 | 312.31 | 43.80 | 10% | 31.231 | 1367.9178
702 | B5.33 31 00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-19 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1021-00 | Check Sand around GRP pipe for sewerage line up to Bottom Subgrade from Manholes # MH 53-4 to MH 53-5 at Road MCF0 | 212.41 | 58.80 | 45% | 95.5845 | 5620.3686
703 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-18 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1027-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling 3rd and last layer Between Manholes # MH 49-6 to MH 50-1 at Road MCD0 | 212.41 | 67.70 | 5% | 10.6205 | 719.0078
704 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-18 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1028-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling 3rd and last layer Between Manholes # MH 49-6 to MH 49-7 at Road MCE0 | 212.41 | 40.42 | 5% | 10.6205 | 429.2806
705 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-18 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1029-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling 4th and layer Between Manholes # MH 51-4 to MH 51-5 at Road MCE0 | 212.41 | 58.80 | 5% | 10.6205 | 624.4854
706 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-18 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1030-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling 3rd and last layer Between Manholes # MH 51-5 to MH 51-6 at Road MCE0 | 212.41 | 58.80 | 5% | 10.6205 | 624.4854
707 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-18 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1034-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at PLOT (5), STA: 0+570 to STA: 0+630 | 22.31 | 2030.10 | 100% | 22.31 | 45291.531
708 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-18 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1040-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Plot (3) STA: 0+0250 to STA: 0+310 | 22.31 | 2,529.26 | 100% | 22.31 | 56427.7906
709 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-18 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1041-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Plot (3) STA: 0+0310 to STA: 0+467 | 22.31 | 4,225.27 | 100% | 22.31 | 94265.7737
710 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-07-19 | SUD1-02-011-TDC-TS9-1-TEL-FIR-1055-00 | Check Installation HDPE Pipe 3(2X50mm) From Manhole 010 To 011 for TELECOMMUNICATIONS Works in road MCE0 | 617.84 | 26.71 | 30% | 185.352 | 4950.7519
711 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-19 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1057-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right side) Embankment 3rd layer at Road # MCB0, STA: 0+580 to STA: 0+660 | 22.31 | 205.53 | 100% | 22.31 | 4585.3743
712 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-19 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1058-00 | Check Coordinates level, Compaction F.D.T for Embankment 1st Layer at STA: 0+250 to 0+360 (Right Side) at Plot. No: - 04 | 22.31 | 3,843.39 | 100% | 22.31 | 85746.0309
713 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-19 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1059-00 | Check Coordinates level and Compaction F.D.T for Embankment 8th layer at PLOT (5), STA: 0+240 to STA: 0+360 | 22.31 | 3,980.00 | 100% | 22.31 | 88793.8
714 | B5.33 31 00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-19 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1060-00 | Check Sand around GRP pipe for sewerage line up to Bottom Subgrade from Manholes # MH 53-5 to MH 53-6 at Road MCF0 | 212.41 | 58.80 | 10% | 21.241 | 1248.9708
715 | B6.33 42 11.20 | Storm Water Network :GRP Pipes 900mm (Depth: 2.51m -3.5m) | 2026-07-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-1061-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/11/2 to MH-G2/11/3 at Road MCF0 | 875.83 | 89.25 | 10% | 87.583 | 7816.7828
716 | B6.33 42 11.16 | Storm Water Network : GRP Pipes 800 mm (Depth: 1.51m -2.51m) | 2026-07-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-1062-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/11/3 to MH-G2/11/4 at Road MCF0 | 639.17 | 89.50 | 10% | 63.917 | 5720.5715
717 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-19 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1063-00 | Check Coordinates level, Compaction F.D.T for Embankment 2nd Layer (Right side) at STA: 0+360 to 0+467 at Plot. No: - 04 | 22.31 | 4,267.36 | 100% | 22.31 | 95204.8016
718 | B6.33 42 11.22 | Storm Water Network : Manhole for GRP Pipes 1000mm (Depth: 1.51m -2.51m) | 2026-07-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-1064-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from Manhole # MH-G2/16/3 to MH-G2/16/4 at Road MCE0 | 884.56 | 87.00 | 45% | 398.052 | 34630.524
719 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-20 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1065-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer at PLOT (5), STA: 0+570 to STA: 0+590 | 22.31 | 572.21 | 100% | 22.31 | 12766.0051
720 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-20 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1066-00 | Check Coordinates level and Compaction F.D.T for Embankment 8th layer at Road/Carriageway and Shoulders # MCG0, STA: 0+050 to STA: 0+190 Bottom subgrade | 22.31 | 1,664.00 | 100% | 22.31 | 37123.84
721 | B1.31 22 00.01 | EARTHWORKS AND SITE GRADING Roadway Excavation for cuttings | 2026-07-22 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1067-00 | Check Coordinates and bottom level Road cutting and compaction test of bottom Sub-Grade Shoulders (left and right side) at Road # MC10 STA: 2+770 to STA: 2+870 | 13.58 | 618.56 | 100% | 13.58 | 8400.0448
722 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-22 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1068-00 | Check Coordinates and bottom level Road Filling and compaction test of bottom Sub-Grade of shoulders (left and right side) at Road # MC10, STA: 2+770 to STA: 2+870 | 22.31 | 398.26 | 100% | 22.31 | 8885.1806
723 | B5 33.31.00.02 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-20 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1072-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling 2nd layer Between Manhole # MH 53-3 to MH 53-4 at Road MCF0 | 221.14 | 98.80 | 10% | 22.114 | 2184.8632
724 | B6.33 42 11.13 | Storm Water Network : GRP Pipes 700 mm (Depth: 1.51m -2.51m) | 2026-07-22 | SUD1-02-011-TDC-TS9-1-STR-FIR-1073-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/16/5 to MH-G2/16/6 at Road MCE0 | 544.12 | 69.12 | 10% | 54.412 | 3760.9574
725 | B6.33 42 11.22 | Storm Water Network : Manhole for GRP Pipes 1000mm (Depth: 1.51m -2.51m) | 2026-07-22 | SUD1-02-011-TDC-TS9-1-STR-FIR-1074-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/16/3 to MH-G2/16/4 at Road MCE0 | 884.56 | 87.00 | 10% | 88.456 | 7695.672
726 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-20 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1075-00 | Check Coordinates level and Compaction F.D.T for Shoulders (Left & Right side) Embankment 4th layer at Road # MC20, STA: 4+820 to STA: 5+010 | 22.31 | 982.28 | 100% | 22.31 | 21914.6668
727 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1076-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-13-2 to MH-12-13-3 at Road MCF0 | 212.41 | 78.87 | 5% | 10.6205 | 837.6388
728 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1077-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-13-3 to MH-12-13-4 at Road MCF0 | 212.41 | 98.86 | 5% | 10.6205 | 1049.9426
729 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1078-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-13-4 to MH-12-13-5 at Road MCF0 | 212.41 | 98.71 | 5% | 10.6205 | 1048.3496
730 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1079-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-13-1 to MH-12-13-1-1 at Road MCF0 | 212.41 | 78.87 | 5% | 10.6205 | 837.6388
731 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1080-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-13-1-1 to MH-12-13-1-2 at Road MCF0 | 212.41 | 98.86 | 5% | 10.6205 | 1049.9426
732 | B5 33.31.00.01 | Sewerage Network:GRP Pipes 200 mm (Depth 0.00 m to 1.5m) | 2026-07-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1081-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-13-1-2 to MH-12-13-1-3 at Road MCF0 | 212.41 | 98.74 | 5% | 10.6205 | 1048.6682
733 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1084-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 12-13-2 at Road MCF0 | 12377.1 | 01 | 5% | 618.855 | 618.855
734 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1085-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 12-13-3 at Road MCF0 | 12377.1 | 01 | 5% | 618.855 | 618.855
735 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1086-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 12-13-4 at Road MCF0 | 12377.1 | 01 | 5% | 618.855 | 618.855
736 | B5 33.05.13.01 | Sewerage Network: Manhole (Depth 0 m to 1.5m) internal dia 1200 mm | 2026-07-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1087-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 12-13-5 at Road MCF0 | 8820.42 | 01 | 5% | 441.021 | 441.021
737 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1088-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 12-13-1 at Road MCF0 | 12377.1 | 01 | 5% | 618.855 | 618.855
738 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1089-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 12-13-1-1 at Road MCF0 | 12377.1 | 01 | 5% | 618.855 | 618.855
739 | B5 33.05.13.03 | Sewerage Network: Manhole (Depth 1.51m to 2.5m) Int dia 1200 mm | 2026-07-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1090-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 12-13-1-2 at Road MCF0 | 12377.1 | 01 | 5% | 618.855 | 618.855
740 | B5 33.05.13.01 | Sewerage Network: Manhole (Depth 0 m to 1.5m) internal dia 1200 mm | 2026-07-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1091-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 12-13-1-3 at Road MCF0 | 8820.42 | 01 | 5% | 441.021 | 441.021
741 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-20 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1092-00 | Check Coordinates level, Compaction F.D.T for Embankment 2nd Layer at STA: 0+250 to 0+360 (left Side) at Plot. No: - 04 | 22.31 | 2,915.56 | 1 | 22.31 | 65046.1436
742 | B6.33 42 11.23 | Storm Water Network :GRP Pipes 1000mm (Depth: 2.51m -3.5m) | 2026-07-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-1093-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/11/1 to MH-G2/11/2 at Road MCF0 | 1017.44 | 89.00 | 0.1 | 101.744 | 9055.216
743 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-21 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1094-00 | Check Coordinates level and Compaction F.D.T for Shoulders (Left and Right side) Embankment 5th layer at Road # MC20, STA: 5+010 to STA: 5+230 | 22.31 | 934.02 | 100% | 22.31 | 20837.9862
744 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-21 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1101-00 | Check Coordinates level and Compaction F.D.T for Embankment 8th layer at PLOT (5), STA: 0+360 to STA: 0+540 | 22.31 | 5570.38 | 100% | 22.31 | 124275.1778
745 | B6.33 42 11.22 | Storm Water Network : Manhole for GRP Pipes 1000mm (Depth: 1.51m -2.51m) | 2026-07-21 | SUD1-02-011-TDC-TS9-1-STR-FIR-1102-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from Existing Manhole # FIMH-G2/11 to MH-G2/11/1 at Road MCF0 | 884.56 | 92.96 | 45% | 398.052 | 37002.9139
746 | B6.33 42 11.22 | Storm Water Network : Manhole for GRP Pipes 1000mm (Depth: 1.51m -2.51m) | 2026-07-21 | SUD1-02-011-TDC-TS9-1-STR-FIR-1103-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/16/1 to MH-G2/16/2 at Road MCE0 | 884.56 | 87.00 | 10% | 88.456 | 7695.672
747 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-07-22 | SUD1-02-011-TDC-TS9-1-TEL-FIR-1110-00 | Check Coordinates and level for Excavation of TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 066 To 067 in road MCF0 | 617.84 | 26.71 | 5% | 30.892 | 825.1253
748 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-07-22 | SUD1-02-011-TDC-TS9-1-TEL-FIR-1111-00 | Check Coordinates and level for Excavation of TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 030 To 031 in road ART- MC10 | 617.84 | 60.80 | 5% | 30.892 | 1878.2336
749 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-07-22 | SUD1-02-011-TDC-TS9-1-TEL-FIR-1112-00 | Check Coordinates and level for Excavation of TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 032 To 033 in road ART- MC10 | 617.84 | 60.80 | 5% | 30.892 | 1878.2336
750 | B5 33.31.00.03 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1113-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-1-89 to MH-1-90 at Road MCA0 | 329.77 | 101.80 | 0.1 | 32.977 | 3357.0586
751 | B5 33.31.00.03 | Sewerage Network:GRP Pipes 200 mm (Depth 1.51m to 2.5m) | 2026-07-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1114-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-1-90 to MH-1-91 at Road MCA0 | 329.77 | 101.30 | 10% | 32.977 | 3340.5701
752 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-22 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1130-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right & Left side) Embankment 4th layer at Road # MC20, STA: 5+230 to STA: 5+280 (last layer) | 22.31 | 253.13 | 100% | 22.31 | 5647.3303
753 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-07-26 | SUD1-02-011-TDC-TS9-1-TEL-FIR-1131-01 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 008 To 009 in road MCE0 | 617.84 | 26.69 | 25% | 154.46 | 4122.5374
754 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-07-26 | SUD1-02-011-TDC-TS9-1-TEL-FIR-1132-01 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 010 To 011 in road MCE0 | 617.84 | 26.71 | 25% | 154.46 | 4125.6266
755 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-07-26 | SUD1-02-011-TDC-TS9-1-TEL-FIR-1133-01 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 017 To 018 in road MCF0 | 617.84 | 26.69 | 25% | 154.46 | 4122.5374
756 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-07-26 | SUD1-02-011-TDC-TS9-1-TEL-FIR-1134-01 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 019 To 020 in road MCF0 | 617.84 | 26.69 | 25% | 154.46 | 4122.5374
757 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-07-26 | SUD1-02-011-TDC-TS9-1-TEL-FIR-1135-01 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 012 To 013 in road MCD0 | 617.84 | 33.14 | 25% | 154.46 | 5118.8044
758 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-07-26 | SUD1-02-011-TDC-TS9-1-TEL-FIR-1136-01 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 024 To 025 in road MCG0 | 617.84 | 26.69 | 25% | 154.46 | 4122.5374
759 | B6.33 05 39.5 | STORM WATER NETWORK: Manhole Diameter :-1500mm (Depth: 1.51 to 2.50m ) | 2026-07-26 | SUD1-02-011-TDC-TS9-1-STR-FIR-1137-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/39 at Road MCB0 | 15295.58 | 01 | 5% | 764.779 | 764.779
760 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51 to 2.50m ) | 2026-07-26 | SUD1-02-011-TDC-TS9-1-STR-FIR-1138-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/40 at Road MCB0 | 12376.13 | 01 | 5% | 618.8065 | 618.8065
761 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51 to 2.50m ) | 2026-07-26 | SUD1-02-011-TDC-TS9-1-STR-FIR-1139-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/41 at Road MCB0 | 12376.13 | 01 | 5% | 618.8065 | 618.8065
762 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51 to 2.50m ) | 2026-07-26 | SUD1-02-011-TDC-TS9-1-STR-FIR-1140-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/42 at Road MCB0 | 12376.13 | 01 | 5% | 618.8065 | 618.8065
763 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51 to 2.50m ) | 2026-07-26 | SUD1-02-011-TDC-TS9-1-STR-FIR-1141-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/43 at Road MCB0 | 12376.13 | 01 | 5% | 618.8065 | 618.8065
764 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51 to 2.50m ) | 2026-07-26 | SUD1-02-011-TDC-TS9-1-STR-FIR-1142-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/44 at Road MCB0 | 12376.13 | 01 | 5% | 618.8065 | 618.8065
765 | B6.33 42 11.9 | STORM WATER NETWORK: GRP Pipes 600mm (Depth: 1.51m - 2.5m) | 2026-07-26 | SUD1-02-011-TDC-TS9-1-STR-FIR-1143-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/39 to STA-A1/40 at Road MCB0 | 448.1 | 44.09 | 5% | 22.405 | 987.8365
766 | B6.33 42 11.9 | STORM WATER NETWORK: GRP Pipes 600mm (Depth: 1.51m - 2.5m) | 2026-07-26 | SUD1-02-011-TDC-TS9-1-STR-FIR-1144-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/40 to STA-A1/41 at Road MCB0 | 448.1 | 88.83 | 5% | 22.405 | 1990.2361
767 | B6.33 42 11.9 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51m - 2.5m) | 2026-07-22 | SUD1-02-011-TDC-TS9-1-STR-FIR-1145-00 | Check Installation of Flat slab at Manhole FMH – A2/9/20-396 at Road MCG0 | 448.1 | 01 | 0% | 0 | 0
768 | B6.33 42 11.9 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51m - 2.5m) | 2026-07-22 | SUD1-02-011-TDC-TS9-1-STR-FIR-1146-00 | Check Installation of Flat slab at Manhole MH –G2/6/5 at Road MCG0 | 448.1 | 01 | 0% | 0 | 0
769 | B6.33 42 11.9 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51m - 2.5m) | 2026-07-22 | SUD1-02-011-TDC-TS9-1-STR-FIR-1147-00 | Check Installation of Flat slab at Manhole MH –G2/6/6 at Road MCG0 | 448.1 | 01 | 0% | 0 | 0
770 | B6.33 42 11.9 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51m - 2.5m) | 2026-07-22 | SUD1-02-011-TDC-TS9-1-STR-FIR-1148-00 | Check Installation of Flat slab at manhole MH – G2/6/2 at Road MCG0 | 448.1 | 01 | 0% | 0 | 0
771 | B6.33 42 11.9 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51m - 2.5m) | 2026-07-22 | SUD1-02-011-TDC-TS9-1-STR-FIR-1149-00 | Check Installation of Flat slab at Manhole MH –G2/6/1at Road MCG0 | 448.1 | 01 | 0% | 0 | 0
772 | B6.33 42 11.9 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51m - 2.5m) | 2026-07-22 | SUD1-02-011-TDC-TS9-1-STR-FIR-1150-00 | Check Installation of Flat slab at Manhole MH –G2/6/3 at Road MCG0 | 448.1 | 01 | 0% | 0 | 0
773 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: > 2.5m) | 2026-07-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-1151-01 | Check Installation of Rings and Flat slab at Manhole MH –G2/11/1 at Road MCF0 | 30133.35 | 01 | 25% | 7533.3375 | 7533.3375
774 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: > 2.5m) | 2026-07-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-1152-01 | Check Installation of Rings and Flat slab at manhole MH –G2/16/1 at Road MCE0 | 30133.35 | 01 | 0% | 0 | 0
775 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: > 2.5m) | 2026-08-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-1153-02 | Check Installation of Rings and Flat slab at manhole MH –G2/16/4 at Road MCE0 | 30133.35 | 01 | 0% | 0 | 0
776 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: > 2.5m) | 2026-08-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-1154-02 | Check Installation of Rings and Flat slab at manhole MH –G2/16/3 at Road MCE0 | 30133.35 | 01 | 0% | 0 | 0
777 | B6.33 05 39.3 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: > 2.5m) | 2026-08-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-1155-01 | Check Installation of Flat slab at Manhole MH –G2/16/7 at Road MCE0 | 448.1 | 01 | 0% | 0 | 0
778 | B6.33 05 39.6 | STORM WATER NETWORK: Manhole Diameter :-1500mm (Depth: > 2.5m) | 2026-08-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-1156-02 | Check Installation of Rings and Flat slab at Manhole MH –G2/16/6 at Road MCE0 | 448.1 | 01 | 0% | 0 | 0
779 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: > 2.5m) | 2026-08-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-1157-02 | Check Installation of Rings and Flat slab at Manhole MH –G2/16/2 at Road MCE0 | 30133.35 | 01 | 0% | 0 | 0
780 | B6.33 05 39.6 | Storm Water Network: Manhole 1500mm dia (Depth > 2.5m) | 2026-07-22 | SUD1-02-011-TDC-TS9-1-STR-FIR-1158-00 | Check Installation of Rings and flat slab at Manhole Base MH – FMH-A2/9/20-399 at Road MCF0 | 19537.02 | 01 | 55% | 10745.361 | 10745.361
781 | B6.33 05 39.3 | Storm Water Network: Manhole 1200mm dia (Depth > 2.5m) | 2026-07-22 | SUD1-02-011-TDC-TS9-1-STR-FIR-1159-00 | Check Installation of Flat Slab at Manhole Base MH – FMH-A2/9/20-397 at Road MCF0 | 15848.43 | 01 | 25% | 3962.1075 | 3962.1075
782 | B6.33 05 39.6 | STORM WATER NETWORK: Manhole Diameter :-1500mm (Depth: > 2.5m) | 2026-08-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-1160-02 | Check Installation of Rings and Flat Slab at Manhole Base MH – MH-G2/11/4 at Road MCF0 | 19537.02 | 01 | 25% | 4884.255 | 4884.255
783 | B6.33 05 39.6 | STORM WATER NETWORK: Manhole Diameter :-1500mm (Depth: > 2.5m) | 2026-08-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-1161-01 | Check Installation of Rings and Flat Slab at Manhole MH-G2/11/3 at Road MCF0 | 19537.02 | 01 | 25% | 4884.255 | 4884.255
784 | B6.33 05 39.2 | Storm Water Network : Manhole Dia 1200 mm (Depth:1.51m -2.51m) | 2026-07-23 | SUD1-02-011-TDC-TS9-1-STR-FIR-1162-00 | Check Installation of Flat Slab at Manhole Base MH –G2/11/7 at Road MCF0 | 12376.13 | 01 | 25% | 3094.0325 | 3094.0325
785 | B6.33 05 39.2 | Storm Water Network : Manhole Dia 1200 mm (Depth:1.51m -2.51m) | 2026-07-23 | SUD1-02-011-TDC-TS9-1-STR-FIR-1163-00 | Check Installation of Flat Slab at Manhole MH-G2/11/6 at Road MCF0 | 12376.13 | 01 | 25% | 3094.0325 | 3094.0325
786 | B6.33 05 39.9 | Storm Water Network: Manhole 2000mm dia (Depth > 2.5m) | 2026-08-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-1164-01 | Check Installation of Rings and Flat Slab at Manhole MH-G2/11/2 at Road MCF0 | 30133.35 | 01 | 25% | 7533.3375 | 7533.3375
787 | B6.33 05 39.6 | STORM WATER NETWORK: Manhole Diameter :-1500mm (Depth: > 2.5m) | 2026-08-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-1165-01 | Check Installation of Rings and Flat Slab at Manhole MH-G2/16/5 at Road MCE0 | 448.1 | 01 | 0% | 0 | 0
788 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-07-23 | SUD1-02-011-TDC-TS9-1-STR-FIR-1166-00 | Check Installation of Flat Slab at Manhole MH-G2/6/7 at Road MCG0 | 12376.13 | 01 | 30% | 3712.839 | 3712.839
789 | B6.33 05 39.3 | 1.51m - 2.5m) | 2026-07-23 | SUD1-02-011-TDC-TS9-1-STR-FIR-1167-00 | Check Installation of Flat Slab at Manhole MH-G2/11/5 at Road MCF0 | 15848.43 | 01 | 25% | 3962.1075 | 3962.1075
790 | B6.33 05 39.6 | STORM WATER NETWORK: Manhole Diameter :-1500mm (Depth: > 2.5m) | 2026-07-23 | SUD1-02-011-TDC-TS9-1-STR-FIR-1168-00 | Check Installation of Flat Slab at Manhole MH-G2/6/4 at Road MCG0 | 448.1 | 01 | 0% | 0 | 0
791 | B6.33 05 39.5 | STORM WATER NETWORK: Manhole Diameter :-1500mm (Depth: 1.51m - 2.5m) | 2026-08-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-1169-01 | Check Installation of Flat Slab at Manhole FMH – A2/9/20-398 at Road MCG0 | 15295.58 | 01 | 25% | 3823.895 | 3823.895
792 | B6.33 42 11.9 | STORM WATER NETWORK: GRP Pipes 600mm (Depth: 1.51m - 2.5m) | 2026-07-26 | SUD1-02-011-TDC-TS9-1-STR-FIR-1177-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/41 to STR-A1/42 at Road MCB0 | 448.1 | 59.16 | 5% | 22.405 | 1325.4798
793 | B6.33 42 11.6 | STORM WATER NETWORK: GRP Pipes 500mm (Depth: 1.51m - 2.5m) | 2026-07-26 | SUD1-02-011-TDC-TS9-1-STR-FIR-1178-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/42 to STR-A1/43 at Road MCB0 | 366.63 | 59.33 | 5% | 18.3315 | 1087.6079
794 | B6.33 42 11.3 | Storm Water Network : GRP Pipes 400 mm (Depth: 0m -1.5m) | 2026-07-26 | SUD1-02-011-TDC-TS9-1-STR-FIR-1179-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/43 to STR-A1/44 at Road MCB0 | 544.12 | 22.55 | 5% | 27.206 | 613.4953
795 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-23 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1181-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Plot (5) STA: 0+350 to STA: 0+467 | 22.31 | 1782.06 | 100% | 22.31 | 39757.7586
796 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-23 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1182-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right & Left side) Embankment 4th layer at Road # MC20, STA: 5+420 to STA: 5+500 | 22.31 | 530.21 | 100% | 22.31 | 11828.9851
797 | B5 33.31.00.04 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 3.51 m to 4.5m) | 2026-07-23 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1195-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling 9th layer Between Existing Manholes # MH 39-27 to MH 49-1 at Road MCE0 (bottom sub grade) | 397.67 | 98.80 | 10% | 39.767 | 3928.9796
798 | B5 33.31.00.03 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 2.51 m to 3.5m) | 2026-07-23 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1196-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling 9th layer Between Manholes # MH 49-1 to MH 49-2 at Road MCE0 (Bottom sub grade) | 329.77 | 98.80 | 10% | 32.977 | 3258.1276
799 | B5 33.31.00.03 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 2.51 m to 3.5m) | 2026-07-23 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1197-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling 9th layer Between Manholes # MH 49-2 to MH 49-3 at Road MCE0 (Bottom sub grade) | 329.77 | 98.80 | 10% | 32.977 | 3258.1276
800 | B5 33.31.00.03 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 2.51 m to 3.5m) | 2026-07-23 | SUD1-02-011-TDC-TS9-1-SEW-FIR-01198-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling 7th layer Between Manholes # MH 49-3 to MH 49-4 at Road MCE0 (Bottom sub grade) | 329.77 | 101.33 | 10% | 32.977 | 3341.5594
801 | B5 33.31.00.03 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 2.51 m to 3.5m) | 2026-07-23 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1199-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling 7th layer Between Manholes # MH 49-4 to MH 49-5 at Road MCE0 (bottom sub grade) | 329.77 | 41.12 | 10% | 32.977 | 1356.0142
802 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 0.0 to 1.5m) | 2026-07-26 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1200-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-2-1 to MH-12-3 at Road MCH0 | 212.41 | 91.96 | 5% | 10.6205 | 976.6612
803 | B5.33 05 13.06 | SEWERAGE NETWORK: Manhole (Depth 2.51 to 3.5m) Internal Diameter (1200mm) With Backdrop | 2026-07-26 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1202-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-12-3 at Road MCH0 | 19018.11 | 01 | 5% | 950.9055 | 950.9055
804 | B5 33.05.13.03 | SEWERAGE NETWORK: Manhole (Depth 1.51 to 2.5m) Internal Diameter (1200mm) | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1203-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-12-19-3 at Road MCE0 | 12377.1 | 01 | 5% | 618.855 | 618.855
805 | B5 33.05.13.03 | SEWERAGE NETWORK: Manhole (Depth 1.51 to 2.5m) Internal Diameter (1200mm) | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1204-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-12-19-4 at Road MCE0 | 12377.1 | 01 | 5% | 618.855 | 618.855
806 | B5 33.05.13.03 | SEWERAGE NETWORK: Manhole (Depth 1.51 to 2.5m) Internal Diameter (1200mm) | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1205-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-12-19-2 at Road MCE0 | 12377.1 | 01 | 5% | 618.855 | 618.855
807 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 0.0 m to 1.5m) | 2026-07-26 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1206-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-19-2 to MH-12-19-3 at Road MCE0 | 212.41 | 78.87 | 5% | 10.6205 | 837.6388
808 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 0.0 to 1.5m) | 2026-07-26 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1207-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-19-3 to MH-12-19-4 at Road MCE0 | 212.41 | 98.86 | 5% | 10.6205 | 1049.9426
809 | B5 33.05.13.03 | SEWERAGE NETWORK: Manhole (Depth 1.51 to 2.5m) Internal Diameter (1200mm) | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1208-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-12-19-1 at Road MCE0 | 12377.1 | 01 | 5% | 618.855 | 618.855
810 | B5 33.05.13.03 | SEWERAGE NETWORK: Manhole (Depth 1.51 to 2.5m) Internal Diameter (1200mm) | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1209-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-12-19-1-1 at Road MCE0 | 12377.1 | 01 | 5% | 618.855 | 618.855
811 | B5 33.05.13.03 | SEWERAGE NETWORK: Manhole (Depth 1.51 to 2.5m) Internal Diameter (1200mm) | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1210-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-12-19-1-2 at Road MCE0 | 12377.1 | 01 | 5% | 618.855 | 618.855
812 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 0.0 to 1.5m) | 2026-07-26 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1211-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-19-1 to MH-12-19-1-1 at Road MCE0 | 212.41 | 78.87 | 5% | 10.6205 | 837.6388
813 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 0.0 to 1.5m) | 2026-07-26 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1212-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-19-1-1 to MH-12-19-1-2 at Road MCE0 | 212.41 | 98.86 | 5% | 10.6205 | 1049.9426
814 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 1.51m to 2.5m) | 2026-07-23 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1214-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling 5th layer Between Existing Manhole # MH 39-22 to MH 53-1 at Road MCF0 (bottom sub grade) | 221.14 | 98.80 | 10% | 22.114 | 2184.8632
815 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 1.51m to 2.5m) | 2026-07-23 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1215-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling 5th layer Between Manhole # MH 53-1 to MH 53-2 at Road MCF0 (bottom sub grade) | 221.14 | 98.80 | 10% | 22.114 | 2184.8632
816 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 1.51m to 2.5m) | 2026-07-23 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1216-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling 5th layer Between Manhole # MH 53-2 to MH 53-3 at Road MCF0 (Bottom sub grade) | 221.14 | 98.80 | 10% | 22.114 | 2184.8632
817 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-23 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1233-00 | Check Coordinates level and Compaction F.D.T for Embankment 9th layer at PLOT (5), STA: 0+240 to STA: 0+360 | 22.31 | 4038.66 | 100% | 22.31 | 90102.5046
818 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-25 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1234-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer at PLOT (2), STA: 0+570 to STA: 0+720 | 22.31 | 4,846.94 | 100% | 22.31 | 108135.2314
819 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-07-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1235-01 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from Manhole # MH-1-95 to MH-1-96 at Road MCC0 | 221.14 | 98.74 | 45% | 99.513 | 9825.9136
820 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-25 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1236-00 | Check Coordinates and bottom level Road/Carriageway cutting and compaction test of bottom Sub-Grade at Road # MC10 STA: 3+340 to STA: 3+467 | 13.58 | 4397.97 | 100% | 13.58 | 59724.4326
821 | B5 33.05.13.01 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 0m- 1.50m) | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1237-00 | Check Installation of Manhole Base (Rings not required) MH-1-93-4 at Road MCC0 | 8820.42 | 01 | 30% | 2646.126 | 2646.126
822 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1238-00 | Check Installation of Manhole Base (Rings not required) MH-1-93-3 at Road MCC0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
823 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1239-00 | Check Installation of Manhole Base (Rings not required) MH-1-93-2 at Road MCC0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
824 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1240-00 | Check Installation of Manhole Base MH-1-93-1 at Road MCC0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
825 | B5 33.05.13.05 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm | 2026-08-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1241-01 | Check Installation of Rings and Flat Slab # MH-1-93 at Road MCC0 | 15848.43 | 01 | 30% | 4754.529 | 4754.529
826 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1242-00 | Check Installation of Manhole Base (Rings not required) MH-1-88-3 at Road MCD0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
827 | B5 33.05.13.01 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 0m- 1.50m) | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1243-00 | Check Installation of Manhole Base (Rings not required) MH-1-88-4 at Road MCD0 | 8820.42 | 01 | 30% | 2646.126 | 2646.126
828 | B5 33.05.13.01 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 0m- 1.50m) | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1244-00 | Check Installation of Manhole Base (Rings not required) MH-1-88-5 at Road MCD0 | 8820.42 | 01 | 30% | 2646.126 | 2646.126
829 | B5 33.05.13.01 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 0m- 1.50m) | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1245-00 | Check Installation of Manhole Base (Rings not required) MH-12-21-3 at Road MCD0 | 8820.42 | 01 | 30% | 2646.126 | 2646.126
830 | B5 33.05.13.01 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 0m- 1.50m) | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1246-00 | Check Installation of Manhole Base (Rings not required) MH-12-21-2 at Road MCD0 | 8820.42 | 01 | 30% | 2646.126 | 2646.126
831 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1247-00 | Check Installation of Manhole Base (Rings not required) MH-12-21-1 at Road MCD0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
832 | B5 33.05.13.01 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 0m- 1.50m) | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1248-00 | Check Installation of Manhole Base (Rings not required) MH-1-88-2-2 at Road MCD0 | 8820.42 | 01 | 30% | 2646.126 | 2646.126
833 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1249-00 | Check Installation of Manhole Base (Rings not required) MH-1-88-2-1 at Road MCD0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
834 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1250-00 | Check Installation of Manhole Base MH-1-88-1 at Road MCA0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
835 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1251-00 | Check Installation of Manhole Base MH-1-81 at Road MCA0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
836 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1252-00 | Check Installation of Manhole Base (Rings not required) MH-1-80 at Road MCA0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
837 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-07-26 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1253-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 12-2-1 at Road MCH0 | 12377.1 | 01 | 5% | 618.855 | 618.855
838 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-07-26 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1254-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 109 at Road MCA0 | 12377.1 | 01 | 5% | 618.855 | 618.855
839 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1255-00 | Check Installation of Manhole Base (Rings not required) MH-12-22 at Road MCB0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
840 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-07-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1256-00 | Check Installation of Manhole Base (Rings not required) MH-12-23 at Road MCB0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
841 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-07-26 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1257-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH- 108 at Road MCA0 | 12377.1 | 01 | 5% | 618.855 | 618.855
842 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-07-26 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1258-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-1-80-1 at Road MCA0 | 12377.1 | 01 | 5% | 618.855 | 618.855
843 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-26 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1259-01 | Check Coordinates level and Compaction F.D.T for Shoulder (Right side) Embankment 4th layer at Road # MCB0, STA: 0+580 to STA: 0+660 | 22.31 | 209.61 | 100% | 22.31 | 4676.3991
844 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-25 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1260-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right & Left side) Embankment 1st layer at Road # MC20, STA: 5+620 to STA: 5+730 | 22.31 | 794.57 | 100% | 22.31 | 17726.8567
845 | B2.33 71 19.02 | Road crossing ducts, 4 ways (4 x 150mm PVC) | 2026-07-25 | SUD1-02-011-TDC-TS9-1-LIT-FIR-1265-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (4X160mm) from Manhole 15 To Manhole 16 for Street Lighting Duct Bank in road MCF0 | 617.84 | 15.21 | 25% | 154.46 | 2349.3366
846 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-27 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1266-01 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Plot (5) STA: 0+020 to STA: 0+110 | 22.31 | 3100.54 | 100% | 22.31 | 69173.0474
847 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-26 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1267-00 | Check Coordinates level and Compaction F.D.T for Embankment 9th layer at PLOT (5), STA: 0+360 to STA: 0+530 | 22.31 | 3969.13 | 100% | 22.31 | 88551.2903
848 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-26 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1268-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Left side) Embankment 1st layer at Road # MC20, STA: 5+730 to STA: 5+910 (Bottom Subgrade) | 22.31 | 99.62 | 100% | 22.31 | 2222.5222
849 | B1.31 22 00.01 | EARTHWORKS AND SITE GRADING Roadway Excavation for cuttings | 2026-07-26 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1269-00 | Check Coordinates and bottom level Road Excavation/cutting and compaction test of bottom Sub-Grade Left side shoulder at Road # MC20, STA: 5+730 to STA: 5+910 (Bottom Subgrade) | 13.58 | 717.51 | 100% | 13.58 | 9743.7858
850 | B6.33 42 11.22 | STORM WATER NETWORK: GRP Pipes 1000mm Diameter (Depth: 1.51 to 2.50m) | 2026-07-26 | SUD1-02-011-TDC-TS9-1-STR-FIR-1271-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/6/1 to MH-G2/6 at Road MCG0 | 884.56 | 92.65 | 10% | 88.456 | 8195.4484
851 | B6.33 42 11.22 | STORM WATER NETWORK: GRP Pipes 1000mm Diameter (Depth: 1.51 to 2.50m) | 2026-07-26 | SUD1-02-011-TDC-TS9-1-STR-FIR-1272-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/11/1 to FMH-G2/11 at Road MCF0 | 884.56 | 92.96 | 10% | 88.456 | 8222.8698
852 | B5 33.05.13.05 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm | 2026-07-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1273-00 | Check Installation of Manhole Base Manhole MH-1-85 at Road MCA0 | 15848.43 | 01 | 30% | 4754.529 | 4754.529
853 | B5 33.05.13.06 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm With Backdrop | 2026-07-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1274-00 | Check Installation of Manhole Base Manhole MH-1-88 at Road MCA0 | 19018.11 | 01 | 30% | 5705.433 | 5705.433
854 | B5 33.05.13.05 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm | 2026-07-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1275-00 | Check Installation of Manhole Base Manhole MH-1-87 at Road MCA0 | 15848.43 | 01 | 30% | 4754.529 | 4754.529
855 | B5 33.05.13.06 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm With Backdrop | 2026-07-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1276-00 | Check Installation of Manhole Base Manhole MH-1-86 at Road MCA0 | 19018.11 | 01 | 30% | 5705.433 | 5705.433
856 | B5 33.05.13.05 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm | 2026-07-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1277-00 | Check Installation of Manhole Base Manhole MH-1-83 at Road MCA0 | 15848.43 | 01 | 30% | 4754.529 | 4754.529
857 | B5 33.05.13.06 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm With Backdrop | 2026-07-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1278-00 | Check Installation of Manhole Base Manhole MH-1-84 at Road MCA0 | 19018.11 | 01 | 30% | 5705.433 | 5705.433
858 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-07-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1279-00 | Check Installation of Manhole Base (Rings not required) Manhole MH-12-21 at Road MCB0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
859 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-27 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1281-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right side) Embankment 3rd layer at Road # MC20, STA: 5+500 to STA: 5+620 | 22.31 | 171.88 | 100% | 22.31 | 3834.6428
860 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-27 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1282-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Left side) Embankment 3rd layer at Road # MC20, STA: 5+500 to STA: 5+620 (last layer) | 22.31 | 390.58 | 100% | 22.31 | 8713.8398
861 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-07-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1283-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from Manhole # MH-1-84 to MH-1-85 at Road MCA0 | 221.14 | 83.80 | 45% | 99.513 | 8339.1894
862 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-07-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1284-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from Manhole # MH-1-85 to MH-1-86 at Road MCA0 | 221.14 | 82.15 | 45% | 99.513 | 8174.9929
863 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-07-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1285-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from Manhole # MH-12-20 to MH-12-19 at Road MCB0 | 212.41 | 94.83 | 45% | 95.5845 | 9064.2781
864 | B3.33 14 13.3 | POT ABLE WATER NETWORK: HOPE Pipes 225 Diameter (Depth 0 to 1.50m) | 2026-07-27 | SUD1-02-011-TDC-TS9-1-PW-FIR-1290-00 | Check Coordinates level and Excavation width Bottom level and compaction for potable water pipeline (255mm) Diameter from Station ST: +625.00 to ST: +000.00 Road MCG0 | 179.43 | 625.00 | 5% | 8.9715 | 5607.1875
865 | B6.33 42 11.1 | POTABLE WATER NETWORK: HOPE Pipes 160mm Diameter (Depth O.Om to 1.50m) | 2026-07-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-1291-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-G2/6/2 A (S) to CB-G2/6/2 (D) at Road MCG0 | 377.3 | 24.10 | 10% | 37.73 | 909.293
866 | B6.33 42 11.2 | POTABLE WATER NETWORK: HOPE Pipes 160mm Diameter (Depth O.Om to 1.50m) | 2026-07-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-1292-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-G2/6/2 (D) to MH-G2/6/2 at Road MCG0 | 602.32 | 11.47 | 10% | 60.232 | 690.861
867 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-07-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-1293-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-G2/6/2 B (S) to MH-CB-G2/6/2 at Road MCG0 | 377.3 | 16.47 | 10% | 37.73 | 621.4131
868 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-07-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-1294-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-G2/6/3 A (S) to CB-G2/6/3 (D) at Road MCG0 | 377.3 | 28.80 | 10% | 37.73 | 1086.624
869 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes with DIA 400mm for Catch Basin | 2026-07-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-1295-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-G2/6/3 (D) to MH-CB-G2/6/3 at Road MCG0 | 602.32 | 12.67 | 10% | 60.232 | 763.1394
870 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-07-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-1296-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-G2/6/3 B (S) to MH-CB-G2/6/3 at Road MCG0 | 377.3 | 15.75 | 10% | 37.73 | 594.2475
871 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-07-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-1297-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-G2/6/4 A (S) to CB-G2/6/4 (D) at Road MCG0 | 377.3 | 28.80 | 10% | 37.73 | 1086.624
872 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes with DIA 400mm for Catch Basin | 2026-07-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-1298-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-G2/6/4 (D) to MH-CB-G2/6/4 at Road MCG0 | 602.32 | 13.63 | 10% | 60.232 | 820.9622
873 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-07-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-1299-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-G2/6/4 B (S) to MH-CB-G2/6/4 at Road MCG0 | 377.3 | 14.77 | 10% | 37.73 | 557.2721
874 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-07-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-1300-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-A2/9/20-398 (S) to FMH-A2/9/20-398 at Road MCG0 | 377.3 | 2.90 | 10% | 37.73 | 109.417
875 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-07-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-1301-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-G2/6/5 A (S) to MH-G2/6/5 at Road MCG0 | 377.3 | 15.28 | 10% | 37.73 | 576.5144
876 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-07-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-1302-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-G2/6/5 B (S) to MH-G2/6/5 at Road MCG0 | 377.3 | 13.97 | 10% | 37.73 | 527.0881
877 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: |  | SUD1-02-011-TDC-TS9-1-STR-FIR-1322-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit AST-A1/40/1 at Road MCD0 | 12376.13 | 01 | 10% | 1237.613 | 1237.613
878 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-07-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1308-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from Manhole # MH-12-21 to MH-12-22 at Road MCB0 | 212.41 | 95.92 | 45% | 95.5845 | 9168.4652
879 | B2.33 71 19.02 | Road crossing ducts, 4 ways (4 x 150mm PVC) | 2026-07-27 | SUD1-02-011-TDC-TS9-1-LIT-FIR-1307-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (4X160mm) from Manhole 67 To Manhole 68 for Street Lighting Duct Bank in road MCH0 | 617.84 | 15.62 | 25% | 154.46 | 2412.6652
880 | B2.33 71 19.02 | Road crossing ducts, 4 ways (4 x 150mm PVC) | 2026-07-27 | SUD1-02-011-TDC-TS9-1-LIT-FIR-1309-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (4X160mm) from Manhole 69 To Manhole 70 for Street Lighting Duct Bank in road MCG0 | 617.84 | 15.62 | 25% | 154.46 | 2412.6652
881 | B3.33 14 13.1 | POTABLE WATER NETWORK: HOPE Pipes 160mm Diameter (Depth O.Om to 1.50m) | 2026-07-28 | SUD1-02-011-TDC-TS9-1-PW-FIR-1310-00 | Check Coordinates level and Excavation width Bottom level and compaction for Road crossing potable water HDPE pipelines (Diameter 160mm) at Road MCG0 | 101.84 | 54.66 | 5% | 5.092 | 278.3287
882 | B5 33.05.13.05 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm | 2026-07-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1311-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-1-73 at Road MCA0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
883 | B5 33.05.13.07 | SEWERAGE NETWORK: Manhole (Depth 3.51 to 4.5m) Internal Diameter (1200mm) | 2026-07-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1312-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-1-74 at Road MCA0 | 19319.76 | 01 | 5% | 965.988 | 965.988
884 | B5 33.05.13.05 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm | 2026-07-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1313-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-1-75 at Road MCA0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
885 | B5 33.05.13.05 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm | 2026-07-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1314-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-1-76 at Road MCA0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
886 | B5 33.05.13.05 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm | 2026-07-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1315-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-1-77 at Road MCA0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
887 | B5 33.05.13.06 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm With Backdrop | 2026-07-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1316-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-1-78 at Road MCA0 | 19018.11 | 01 | 5% | 950.9055 | 950.9055
888 | B5 33.31.00.03 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 2.51 m to 3.5m) | 2026-07-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1317-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-73 to MH-1-74 at Road MCA0 | 329.77 | 43.43 | 5% | 16.4885 | 716.0956
889 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-07-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1318-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-74 to MH-1-75 at Road MCA0 | 221.14 | 26.34 | 5% | 11.057 | 291.2414
890 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-07-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1319-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-75 to MH-1-76 at Road MCA0 | 221.14 | 26.43 | 5% | 11.057 | 292.2365
891 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-07-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1320-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-76 to MH-1-77 at Road MCA0 | 221.14 | 19.44 | 5% | 11.057 | 214.9481
892 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-07-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1321-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-77 to MH-1-78 at Road MCA0 | 221.14 | 52.85 | 5% | 11.057 | 584.3625
893 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-07-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-1323-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/40/2 at Road MCD0 | 12376.13 | 01 | 10% | 1237.613 | 1237.613
894 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-07-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-1324-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A2/24/4 at Road MCD0 | 12376.13 | 01 | 10% | 1237.613 | 1237.613
895 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-07-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-1325-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A2/24/3 at Road MCD0 | 12376.13 | 01 | 10% | 1237.613 | 1237.613
896 | B6.33 42 11.3 | STORM WATER NETWORK: GRP Pipes 400mm (Depth: 0m - 1.5m) | 2026-07-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-1326-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole #STA-A1/40/1 to STA-A1/40/2 at Road MCD0 | 300.67 | 64.34 | 10% | 30.067 | 1934.5108
897 | B6.33 42 11.4 | STORM WATER NETWORK: GRP Pipes 400mm (Depth: 1.51m - 2.5m) | 2026-07-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-1327-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole #STA-A1/40/2 to STA-A2/24/4 at Road MCD0 | 312.31 | 63.85 | 10% | 31.231 | 1994.0994
898 | B6.33 42 11.3 | STORM WATER NETWORK: GRP Pipes 400mm (Depth: 0m - 1.5m) | 2026-07-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-1328-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole #STA-A2/24/4 TO STA-A2/24/3 at Road MCD0 | 300.67 | 63.80 | 10% | 30.067 | 1918.2746
899 | B6.33 42 11.10 | STORM WATER NETWORK: GRP Pipes 600mm Diameter (Depth: 1.51 to 2.50m) | 2026-07-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-1329-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/16/6 to MH-G2/16/7 at Road MCE0 | 461.68 | 73.07 | 10% | 46.168 | 3373.4958
900 | B1.31 22 00.01 | EARTHWORKS AND SITE GRADING Roadway Excavation for cuttings | 2026-07-27 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1330-00 | Check Coordinates and bottom level Road/carriageway Excavation/cutting upto bottom of Sub-Grade STA: 6+030 to STA: 6+121.40 at Road # MC20 | 13.58 | 1468.20 | 100% | 13.58 | 19938.156
901 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-08-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1332-00 | Check Installation of Manhole Base (Rings not required) Manhole MH-12-19-2 at Road MCE0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
902 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-08-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1333-00 | Check Installation of Manhole Base (Rings not required) Manhole MH-1-80-1 at Road MCA0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
903 | B5 33.05.13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51-2.5m) Internal Diameter :-1200mm | 2026-08-10 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1334-01 | Check Installation of Manhole Base (Rings not required) Manhole MH-108 at Road MCA0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
904 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-07-28 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1335-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-19-4 to MH-12-19-5 at Road MCE0 | 212.41 | 98.74 | 5% | 10.6205 | 1048.6682
905 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-07-28 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1336-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-19-1-2 to MH-12-19-1-3 at Road MCE0 | 212.41 | 98.74 | 5% | 10.6205 | 1048.6682
906 | B5 33.05.13.01 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 0m- 1.50m) | 2026-07-28 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1337-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-12-19-5 at Road MCE0 | 8820.42 | 01 | 5% | 441.021 | 441.021
907 | B5 33.05.13.01 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 0m- 1.50m) | 2026-07-28 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1338-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-12-19-1-3 at Road MCE0 | 8820.42 | 01 | 5% | 441.021 | 441.021
908 | B6.33 42 11.22 | STORM WATER NETWORK: GRP Pipes 1000mm (Depth: 1.51m - 2.5m) | 2026-07-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-1339-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A2/23 to STA-A2/22 at Road MCA0 | 884.56 | 48.90 | 10% | 88.456 | 4325.4984
909 | B6.33 42 11.28 | STORM WATER NETWORK: GRP Pipes 1200mm (Depth: 1.51m - 2.5m) | 2026-07-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-1340-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A2/22 to STA-A2/21 at Road MCA0 | 1287.08 | 48.64 | 10% | 128.708 | 6260.3571
910 | B6.33 42 11.28 | STORM WATER NETWORK: GRP Pipes 1200mm (Depth: 1.51m - 2.5m) | 2026-07-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-1341-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A2/21 to STA-A2/20 at Road MCA0 | 1287.08 | 46.75 | 10% | 128.708 | 6017.099
911 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-07-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-1342-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit STA-A2/24/2 at Road MCD0 | 12376.13 | 01 | 10% | 1237.613 | 1237.613
912 | B6.33 05 39.5 | STORM WATER NETWORK: Manhole diameter :- 1500mm (Depth: 1.51m - 2.5m) | 2026-07-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-1343-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit STA-A2/24/1 at Road MCD0 | 15295.58 | 01 | 10% | 1529.558 | 1529.558
913 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: > 2.5m) | 2026-08-24 | SUD1-02-011-TDC-TS9-1-STR-FIR-1344-02 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit STA-A2/23 at Road MCD0 | 30133.35 | 01 | 0% | 0 | 0
914 | B6.33 42 11.10 | STORM WATER NETWORK: GRP Pipes 600mm Diameter (Depth: 1.51 to 2.50m) | 2026-07-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-1345-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # STA-A2/24/2 to STA-A2/24/1 at Road MCD0 | 461.68 | 63.65 | 10% | 46.168 | 2938.5932
915 | B6.33 42 11.13 | STORM WATER NETWORK: GRP Pipes 700mm Diameter (Depth:1.51 to 2.50m) | 2026-08-24 | SUD1-02-011-TDC-TS9-1-STR-FIR-1346-03 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # STA-A2/24/1 to STA-A2/23 at Road MCD0 | 544.12 | 66.93 | 0% | 0 | 0
916 | B6.33 42 11.7 | STORM WATER NETWORK: Manhole FOR GRP Pipes 500mm (Depth: 1.51 to 2.50m) | 2026-07-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-1347-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # STA-A2/24/3 to STA-A2/24/2 at Road MCD0 | 379.24 | 63.80 | 5% | 18.962 | 1209.7756
917 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: > 2.5m) | 2026-07-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-1348-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit STA-A2/22 at Road MCA0 | 30133.35 | 01 | 10% | 3013.335 | 3013.335
918 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: > 2.5m) | 2026-07-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-1349-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit STA-A2/21 at Road MCA0 | 30133.35 | 01 | 10% | 3013.335 | 3013.335
919 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: > 2.5m) | 2026-07-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-1350-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit (STA) MH-A2/20 at Road MCA0 | 30133.35 | 01 | 10% | 3013.335 | 3013.335
920 | B1.31.22.00.03 | Embankments to the ROW | 2026-08-03 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1351-00 | Check Coordinates and bottom level Road cutting and compaction test of bottom Sub-Grade Shoulder (left side) at Road # MC10 STA: 2+870 to STA: 3+040 | 22.31 | 836.82 | 100% | 22.31 | 18669.4542
921 | B1.31.22.00.03 | Embankments to the ROW | 2026-08-03 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1352-00 | Check Coordinates and bottom level Road Filling and compaction test of bottom Sub-Grade of shoulders (Leftt side) at Road # MC10, STA: 2+870 to STA: 3+040 | 22.31 | 215.07 | 100% | 22.31 | 4798.2117
922 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-08-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1353-00 | Check Installation of Manhole Base (Rings not required) MH-12-13-3 at Road MCF0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
923 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-08-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1354-00 | Check Installation of Manhole Base (Rings not required) MH-12-13-4 at Road MCF0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
924 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-08-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1355-01 | Check sand bedding and GRP pipe installation for Sewerage line from manhole # MH-1-95 to MH-1-94at Road MCC0 | 221.14 | 96.90 | 45% | 99.513 | 9642.8097
925 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-07-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1356-00 | Check sand bedding and GRP pipe installation for Sewerage line from manhole # MH-1-97 to MH-1-96 at Road MCC0 | 212.41 | 98.86 | 45% | 95.5845 | 9449.4837
926 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-08-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1357-01 | Check sand bedding and GRP pipe installation for Sewerage line from manhole # MH-1-98 to MH-1-97at Road MCC0 | 212.41 | 78.87 | 45% | 95.5845 | 7538.7495
927 | B5 33.05.13.01 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 0m- 1.50m) | 2026-08-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1358-00 | Check Installation of Manhole Base (Rings not required) MH-12-13-5 at Road MCF0 | 8820.42 | 01 | 30% | 2646.126 | 2646.126
928 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-08-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1359-00 | Check Installation of Manhole Base (Rings not required) MH-12-13-2 at Road MCF0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
929 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-28 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1360-00 | Check Coordinates level and Compaction F.D.T for Embankment 10th layer at PLOT (5), STA: 0+240 to STA: 0+360 | 22.31 | 4067.81 | 100% | 22.31 | 90752.8411
930 | B6.33 42 11.28 | STORM WATER NETWORK: GRP Pipes 1200mm (Depth: 1.51m - 2.5m) | 2026-07-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-1361-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A2/19 to STA-A2/20 at Road MCA0 | 1287.08 | 53.78 | 10% | 128.708 | 6921.9162
931 | B6.33 42 11.6 | STORM WATER NETWORK: GRP Pipes 500mm (Depth: 0.0m - 1.5m) | 2026-07-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-1362-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A2/19/1 to STA-A2/19 at Road MCE0 | 366.63 | 59.02 | 5% | 18.3315 | 1081.9251
932 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: > 2.5m) | 2026-07-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-1363-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A2/19 at Road MCA0 | 30133.35 | 01 | 10% | 3013.335 | 3013.335
933 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-07-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-1364-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A2/19/1 at Road MCE0 | 12376.13 | 01 | 10% | 1237.613 | 1237.613
934 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-07-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1365-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-26 to MH-12-25 at Road MCB0 | 212.41 | 73.80 | 45% | 95.5845 | 7054.1361
935 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-07-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1366-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-25 to MH-12-24 at Road MCB0 | 212.41 | 73.80 | 45% | 95.5845 | 7054.1361
936 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-07-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1367-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-24 to MH-12-23 at Road MCB0 | 212.41 | 98.80 | 45% | 95.5845 | 9443.7486
937 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-07-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1368-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-23 to MH-12-22 at Road MCB0 | 212.41 | 98.80 | 45% | 95.5845 | 9443.7486
938 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-07-28 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1369-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-1-84 to MH-1-83 at Road MCA0 | 221.14 | 83.80 | 45% | 99.513 | 8339.1894
939 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-07-28 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1370-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-1-83 to MH-1-82 at Road MCA0 | 221.14 | 83.76 | 45% | 99.513 | 8335.2089
940 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-07-28 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1371-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-1-81 to MH-1-80 at Road MCA0 | 212.41 | 98.80 | 45% | 95.5845 | 9443.7486
941 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-07-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-1372-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-G2/6/1 A (S) to CB-G2/6/1 (D) at Road MCG0 | 377.3 | 28.80 | 10% | 37.73 | 1086.624
942 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes with DIA 400mm for Catch Basin | 2026-07-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-1373-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-G2/6/1 (D) to MH-G2/6/1 at Road MCG0 | 602.32 | 10.53 | 10% | 60.232 | 634.243
943 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-07-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-1374-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-G2/6/1 B (S) to MH-G2/6/1at Road MCG0 | 377.3 | 17.45 | 10% | 37.73 | 658.3885
944 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1375-01 | Check Installation of catch basin CB-G2/6/1 A (S) include the connecting pipe opening at Road MCG0 | 5124.07 | 01 | 30% | 1537.221 | 1537.221
945 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-07-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-1376-00 | Check Installation of catch basin CB-G2/6/1 B (S) include the connecting pipe opening at Road MCG0 | 5124.07 | 01 | 30% | 1537.221 | 1537.221
946 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-07-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-1377-00 | Check Installation of catch basin CB-G2/6/2 A (S) include the connecting pipe opening at Road MCG0 | 5124.07 | 01 | 30% | 1537.221 | 1537.221
947 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-07-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-1378-00 | Check Installation of catch basin CB-G2/6/2 B (S) include the connecting pipe opening at Road MCG0 | 5124.07 | 01 | 30% | 1537.221 | 1537.221
948 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-07-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-1379-00 | Check Installation of catch basin CB-G2/6/3 A (S) include the connecting pipe opening at Road MCG0 | 5124.07 | 01 | 30% | 1537.221 | 1537.221
949 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-07-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-1380-00 | Check Installation of catch basin CB-G2/6/3 B (S) include the connecting pipe opening at Road MCG0 | 5124.07 | 01 | 30% | 1537.221 | 1537.221
950 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-07-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-1381-00 | Check Installation of catch basin CB-G2/6/4 A (S) include the connecting pipe opening at Road MCG0 | 5124.07 | 01 | 30% | 1537.221 | 1537.221
951 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-07-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-1382-00 | Check Installation of catch basin CB-G2/6/4 B (S) include the connecting pipe opening at Road MCG0 | 5124.07 | 01 | 30% | 1537.221 | 1537.221
952 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1383-01 | Check Installation of catch basin CB-A2/9/20-398 (S) include the connecting pipe opening at Road MCG0 | 5124.07 | 01 | 30% | 1537.221 | 1537.221
953 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1384-01 | Check Installation of catch basin CB-G2/6/5 A (S) include the connecting pipe opening at Road MCG0 | 5124.07 | 01 | 30% | 1537.221 | 1537.221
954 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-07-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-1385-00 | Check Installation of catch basin CB-G2/6/5 B (S) include the connecting pipe opening at Road MCG0 | 5124.07 | 01 | 30% | 1537.221 | 1537.221
955 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-07-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-1386-00 | Check Installation of catch basin CB-A2/9/20-396 (S) include the connecting pipe opening at Road MCG0 | 5124.07 | 01 | 30% | 1537.221 | 1537.221
956 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-07-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-1387-00 | Check Installation of catch basin CB-G2/6/6 A (S) include the connecting pipe opening at Road MCG0 | 5124.07 | 01 | 30% | 1537.221 | 1537.221
957 | B1.31.22.00.04 | Embankments to the Plot | 2026-07-29 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1399-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Plot (5) STA: 0+270 to STA: 0+350 | 22.31 | 2273.24 | 100% | 22.31 | 50715.9844
958 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-30 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1400-00 | Check Coordinates and bottom level Road cutting and compaction test of bottom Sub-Grade Shoulder (Right side) at Road # MC10 STA: 2+870 to STA: 3+040 | 22.31 | 190.70 | 100% | 22.31 | 4254.517
959 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-30 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1401-00 | Check Coordinates and bottom level Road Filling and compaction test of bottom Sub-Grade of shoulders (Right side) at Road # MC10, STA: 2+870 to STA: 3+040 | 22.31 | 594.47 | 100% | 22.31 | 13262.6257
960 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-07-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1402-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-26 to MH-12-25 at Road MCB0 | 212.41 | 73.80 | 10% | 21.241 | 1567.5858
961 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-07-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1403-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-25 to MH-12-24 at Road MCB0 | 212.41 | 73.80 | 10% | 21.241 | 1567.5858
962 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-07-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1404-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-24 to MH-12-23 at Road MCB0 | 212.41 | 98.80 | 10% | 21.241 | 2098.6108
963 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-07-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1405-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-23 to MH-12-22 at Road MCB0 | 212.41 | 98.80 | 10% | 21.241 | 2098.6108
964 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-08-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1409-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-15 to MH-12-16 at Road MCB0 | 221.14 | 41.62 | 45% | 99.513 | 4141.7311
965 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-08-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1410-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-16 to MH-12-17 at Road MCI0 | 221.14 | 39.80 | 45% | 99.513 | 3960.6174
966 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-08-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1411-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-17 to MH-12-18 at Road MCB0 | 212.41 | 42.24 | 45% | 95.5845 | 4037.4893
967 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-07-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1413-00 | Check Installation of Manhole Base MH-1-82 at Road MCA0. | 12377.1 | 01 | 30% | 3713.13 | 3713.13
968 | B5 33.05.13.01 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 0m- 1.50m) | 2026-07-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1415-00 | Check Installation of Manhole Base (Rings not required) MH-1-79 at Road MCA0. | 8820.42 | 01 | 30% | 2646.126 | 2646.126
969 | B5.33 05 13.03 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 1.51-2.5 ) | 2026-08-10 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1417-01 | Check Installation of Manhole Base (Rings not required) MH-109 at Road MCA0. | 12377.1 | 01 | 30% | 3713.13 | 3713.13
970 | B5.33 05 13.06 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 2.51- 3.5/BD m ) With backdrop | 2026-08-10 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1418-01 | Check Installation of Manhole Base MH-12-3 at Road MCH0. | 19018.11 | 01 | 30% | 5705.433 | 5705.433
971 | B5 33.05.13.05 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm | 2026-07-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1419-00 | Check Installation of Manhole Base MH-12-17 at Road MCB0. | 15848.43 | 01 | 30% | 4754.529 | 4754.529
972 | B5 33.05.13.05 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm | 2026-07-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1420-00 | Check Installation of Manhole Base MH-12-15 at Road MCB0. | 15848.43 | 01 | 30% | 4754.529 | 4754.529
973 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-07-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1421-00 | Check Installation of Manhole Base MH-12-19-1 at Road MCE0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
974 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-07-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1422-00 | Check Installation of Manhole Base (Rings not required) MH-12-19-1-1 at Road MCE0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
975 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-08-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1423-00 | Check Installation of Manhole Base (Rings not required) MH-12-19-1-2 at Road MCE0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
976 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-08-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1424-00 | Check Installation of Manhole Base (Rings not required) MH-12-19-3 at Road MCE0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
977 | B5 33.05.13.01 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 0m- 1.50m) | 2026-08-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1425-00 | Check Installation of Manhole Base (Rings not required) MH-12-21-1-1 at Road MCD0. | 8820.42 | 01 | 30% | 2646.126 | 2646.126
978 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-08-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1426-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-18 to MH-12-19 at Road MCB0 | 212.41 | 101.75 | 45% | 95.5845 | 9725.7229
979 | B5.33 05 13.03 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 1.51-2.5) | 2026-08-10 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1427-01 | Check Installation of Manhole Base MH-12-11-1 at Road MCG0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
980 | B5.33 05 13.03 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 1.51-2.5) | 2026-08-10 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1428-01 | Check Installation of Manhole Base MH-12-11-1-1 at Road MCG0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
981 | B5 33.05.13.05 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm | 2026-07-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1429-00 | Check Installation of Manhole Base MH-12-14 at Road MCB0 | 15848.43 | 01 | 30% | 4754.529 | 4754.529
982 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-07-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-1430-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/11 (S) at Road MCF0 | 5124.07 | 1.00 | 10% | 512.407 | 512.407
983 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-07-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-1431-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/11/1 A(S) at Road MCF0 | 5124.07 | 1.00 | 10% | 512.407 | 512.407
984 | B6.33 05 39.16 | STORM WATER NETWORK: Catch Basin (Double) | 2026-07-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-1432-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/11/1 (D) at Road MCF0 | 12444.99 | 1.00 | 10% | 1244.499 | 1244.499
985 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-07-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-1433-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/11/1 B(S) at Road MCF0 | 5124.07 | 1.00 | 10% | 512.407 | 512.407
986 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-07-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-1434-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/11/2 A (S) at Road MCF0 | 5124.07 | 1.00 | 10% | 512.407 | 512.407
987 | B6.33 05 39.16 | STORM WATER NETWORK: Catch Basin (Double) | 2026-07-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-1435-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/11/2 (D) at Road MCF0 | 12444.99 | 1.00 | 10% | 1244.499 | 1244.499
988 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-07-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-1436-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # FMH-A2/9/20-396 to CB-A2/9/20-396 (S) at Road MCG0 | 377.3 | 3.24 | 10% | 37.73 | 122.2452
989 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-07-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-1437-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/6/6 to CB-G2/6/6 A (S) at Road MCG0 | 377.3 | 11.17 | 10% | 37.73 | 421.4441
990 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-07-23 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1441-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-53-5 to MH-53-4 at Road MCF0 | 212.41 | 58.80 | 10% | 21.241 | 1248.9708
991 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-07-23 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1442-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-53-6 to MH-53-5 at Road MCF0 | 212.41 | 58.80 | 10% | 21.241 | 1248.9708
992 | B2.33 71 19.02 | Road crossing ducts, 4 ways (4 x 150mm PVC) | 2026-07-30 | SUD1-02-011-TDC-TS9-1-LIT-FIR-1443-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (4X160mm) from Manhole 59 To Manhole 60 for Street Lighting Duct Bank in road MCE0 | 617.84 | 17.14 | 25% | 154.46 | 2647.4444
993 | B2.33 71 19.02 | Road crossing ducts, 4 ways (4 x 150mm PVC) | 2026-07-30 | SUD1-02-011-TDC-TS9-1-LIT-FIR-1446-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (4X160mm) from Manhole 47 To Manhole 48 for Street Lighting Duct Bank in road MC20 | 617.84 | 9.10 | 25% | 154.46 | 1405.586
994 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-30 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1447-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right side) Embankment 5th layer at Road # MCB0, STA: 0+580 to STA: 0+660 | 22.31 | 179.49 | 100% | 22.31 | 4004.4219
995 | B1.31.22.00.03 | Embankments to the ROW | 2026-07-30 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1448-00 | Check Coordinates level and compaction F.D.T for Embankment 5th layer of Road/carriageway at # MCB0, STA: 0+580 to STA: 0+660 (Bottom Subgrade) | 22.31 | 556.64 | 100% | 22.31 | 12418.6384
996 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: > 2.5m) | 2026-08-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-1449-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A2/18 at Road MCA0 | 30133.35 | 01 | 10% | 3013.335 | 3013.335
997 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: > 2.5m) | 2026-08-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-1450-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A2/17 at Road MCA0 | 30133.35 | 01 | 10% | 3013.335 | 3013.335
998 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: > 2.5m) | 2026-08-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-1451-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A2/16 at Road MCA0 | 30133.35 | 01 | 10% | 3013.335 | 3013.335
999 | B6.33 42 11.31 | STORM WATER NETWORK: GRP Pipes 1300mm (Depth: 1.51m - 2.5m) | 2026-08-26 | SUD1-02-011-TDC-TS9-1-STR-FIR-1453-03 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A2/18 to STA-A2/17 at Road MCA0 | 1591.63 | 53.78 | 10% | 159.163 | 8559.7861
1000 | B6.33 42 11.31 | STORM WATER NETWORK: GRP Pipes 1300mm (Depth: 1.51m - 2.5m) | 2026-08-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-1454-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A2/17 to STA-A2/16 at Road MCA0 | 1591.63 | 48.42 | 10% | 159.163 | 7706.6725
1001 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-08-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1456-00 | Check Installation of Manhole Base (Rings not required) MH-12-13-1-1 at Road MCF0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
1002 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-08-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1457-00 | Check Installation of Manhole Base (Rings not required) MH-12-13-1-2 at Road MCF0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
1003 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-07-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1458-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from Manhole # MH-1-81 to MH-1-82 at Road MCA0 | 212.41 | 98.84 | 45% | 95.5845 | 9447.572
1004 | B5 33.05.13.01 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 0m- 1.50m) | 2026-08-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1459-00 | Check Installation of Manhole Base (Rings not required) MH-12-13-1-3 at Road MCF0 | 8820.42 | 01 | 30% | 2646.126 | 2646.126
1005 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-07-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1460-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from Manhole # MH-12-21 to MH-12-20 at Road MCB0 | 212.41 | 100.57 | 45% | 95.5845 | 9612.9332
1006 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-07-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-1461-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/11/2 B(S) at Road MCF0 | 5124.07 | 1.00 | 10% | 512.407 | 512.407
1007 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-07-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-1462-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/11/3 A(S) at Road MCF0 | 5124.07 | 1.00 | 10% | 512.407 | 512.407
1008 | B6.33 05 39.16 | STORM WATER NETWORK: Catch Basin (Double) | 2026-07-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-1463-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/11/3 (D) at Road MCF0 | 12444.99 | 1.00 | 10% | 1244.499 | 1244.499
1009 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-07-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-1464-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/11/3 B(S) at Road MCF0 | 5124.07 | 1.00 | 10% | 512.407 | 512.407
1010 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-07-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-1465-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/11/4 A(S) at Road MCF0 | 5124.07 | 1.00 | 10% | 512.407 | 512.407
1011 | B6.33 05 39.16 | STORM WATER NETWORK: Catch Basin (Double) | 2026-07-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-1466-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/11/4 (D) at Road MCF0 | 12444.99 | 1.00 | 10% | 1244.499 | 1244.499
1012 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-07-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-1467-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/6/6 to CB-G2/6/6 C (S) at Road MCG0 | 377.3 | 17.83 | 10% | 37.73 | 672.7259
1013 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-07-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-1468-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/6/7 to CB-G2/6/7 (S) at Road MCG0 | 377.3 | 27.43 | 10% | 37.73 | 1034.9339
1014 | B1.31.22.00.03 | Embankments to the ROW | 2026-08-01 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1478-00 | Check Coordinates level and Compaction F.D.T for Embankment 10th layer at PLOT (5), STA: 0+360 to STA: 0+480 | 22.31 | 2908.88 | 100% | 22.31 | 64897.1128
1015 | B5 33.05.13.11 | SEWERAGE NETWORK: Manhole (Depth 4.51m to 5.5m) Internal Diameter (1200mm) With Backdrop | 2026-08-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1479-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-12-2 at Road MCH0 | 25162.53 | 01 | 5% | 1258.1265 | 1258.1265
1016 | B5 33.05.13.09 | SEWERAGE NETWORK: Manhole (Depth 4.51m to 5.5m) Internal Diameter (1200mm) | 2026-08-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1480-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-12-4 at Road MCH0 | 22875.47 | 01 | 5% | 1143.7735 | 1143.7735
1017 | B5 33.31.00.03 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 2.51m m to 3.5m) | 2026-08-23 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1481-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-78 to MH-12-2 at Road MCH0 | 329.77 | 48.59 | 5% | 16.4885 | 801.1762
1018 | B5 33.31.00.04 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 3.51m m to 4.5m) | 2026-08-23 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1482-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-2 to MH-12-4 at Road MCH0 | 397.67 | 91.93 | 5% | 19.8835 | 1827.8902
1019 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-08-01 | SUD1-02-011-TDC-TS9-1-TEL-FIR-1483-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 106 To 107 in road MC20 | 617.84 | 35.89 | 25% | 154.46 | 5543.5694
1020 | B1.31 22 00.01 | 6-ways ducts, 50mm diameter | 2026-08-01 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1499-00 | Check Coordinates and bottom level Road/Carriageway Excavation/cutting upto bottom of Sub-Grade STA: 0+440 to STA: 0+656.75 at Road # MCH0 | 13.58 | 4002.93 | 100% | 13.58 | 54359.7894
1021 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-1500-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/11/4 B (S) at Road MCF0 | 5124.07 | 1.00 | 10% | 512.407 | 512.407
1022 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-1501-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-A2/9/20-399 (S) at Road MCF0 | 5124.07 | 1.00 | 10% | 512.407 | 512.407
1023 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-1502-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/11/5 A (S) at Road MCF0 | 5124.07 | 1.00 | 10% | 512.407 | 512.407
1024 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-1503-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/11/5 B (S) at Road MCF0 | 5124.07 | 1.00 | 10% | 512.407 | 512.407
1025 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-1504-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-A2/9/20-397 (S) at Road MCF0 | 5124.07 | 1.00 | 10% | 512.407 | 512.407
1026 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-1505-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/11/6 A (S) at Road MCF0 | 5124.07 | 1.00 | 10% | 512.407 | 512.407
1027 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-1506-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/11/6 B (S) at Road MCF0 | 5124.07 | 1.00 | 10% | 512.407 | 512.407
1028 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-1507-01 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/11/6 C (S) at Road MCF0 | 5124.07 | 1.00 | 10% | 512.407 | 512.407
1029 | B1.31.22.00.03 | 6-ways ducts, 50mm diameter | 2026-08-01 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1509-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right side) Embankment 4th layer at Road # MC20, STA: 5+500 to STA: 5+620 | 22.31 | 239.94 | 100% | 22.31 | 5353.0614
1030 | B1.31.22.00.03 | 6-ways ducts, 50mm diameter | 2026-08-01 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1510-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right & Left side) Embankment 2nd layer at Road # MC20, STA: 5+620 to STA: 5+730 | 22.31 | 432.17 | 100% | 22.31 | 9641.7127
1031 | B5.33 05 13.06 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 2.51-3.5m) With backdrop | 2026-08-10 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1511-01 | Check Installation of Manhole Base MH-1-78 at Road MCA0. | 19018.11 | 01 | 30% | 5705.433 | 5705.433
1032 | B5.33 05 13.06 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 2.51-3.5m) With backdrop | 2026-08-10 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1512-01 | Check Installation of Manhole Base MH-1-77 at Road MCA0. | 19018.11 | 01 | 30% | 5705.433 | 5705.433
1033 | B5.33 05 13.06 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 2.51-3.5m) With backdrop | 2026-08-10 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1513-01 | Check Installation of Manhole Base MH-1-76 at Road MCA0. | 19018.11 | 01 | 30% | 5705.433 | 5705.433
1034 | B5.33 05 13.06 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 2.51-3.5m) With backdrop | 2026-08-10 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1514-01 | Check Installation of Manhole Base MH-1-75 at Road MCA0. | 19018.11 | 01 | 30% | 5705.433 | 5705.433
1035 | B5.33 05 13.06 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 2.51-3.5m) With backdrop | 2026-08-10 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1515-01 | Check Installation of Manhole Base MH-1-74 at Road MCA0. | 19018.11 | 01 | 30% | 5705.433 | 5705.433
1036 | B1.31.22.00.04 | 6-ways ducts, 50mm diameter | 2026-08-02 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1516-00 | Check Coordinates level and Compaction F.D.T for Embankment 11th layer at PLOT (5), STA: 0+240 to STA: 0+360 | 22.31 | 3881.14 | 100% | 22.31 | 86588.2334
1037 | B6.33 42 11.13 | STORM WATER NETWORK: GRP Pipes 700mm Diameter (Depth:1.51 to 2.50m) | 2026-08-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-1517-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/6/4 to FMH-A2/9/20-398 at Road MCG0 | 544.12 | 43.96 | 10% | 54.412 | 2391.9515
1038 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-08-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1518-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-1-96 to MH-1-95 at Road MCC0 | 221.14 | 98.74 | 10% | 22.114 | 2183.5364
1039 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-08-02 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1519-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-22 to MH-12-21 at Road MCB0 | 212.41 | 95.92 | 10% | 21.241 | 2037.4367
1040 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-08-02 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1520-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-21 to MH-12-20 at Road MCB0 | 212.41 | 100.57 | 10% | 21.241 | 2136.2074
1041 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-08-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1521-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-1-97 to MH-1-96 at Road MCC0 | 212.41 | 98.86 | 10% | 21.241 | 2099.8853
1042 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Depth 0-1.50m) | 2026-08-05 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1522-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-19 to MH-12-18 at Road MCB0 | 212.41 | 101.75 | 10% | 21.241 | 2161.2717
1043 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-08-02 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1523-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-20 to MH-12-19 at Road MCB0 | 212.41 | 94.83 | 10% | 21.241 | 2014.284
1044 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-08-02 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1524-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-1-85 to MH-1-84 at Road MCA0 | 221.14 | 83.8 | 10% | 22.114 | 1853.1532
1045 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-08-02 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1525-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-1-84 to MH-1-83 at Road MCA0 | 221.14 | 83.8 | 10% | 22.114 | 1853.1532
1046 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-08-02 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1526-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-1-83 to MH-1-82 at Road MCA0 | 221.14 | 83.76 | 10% | 22.114 | 1852.2686
1047 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-08-02 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1527-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-1-82 to MH-1-81 at Road MCA0 | 212.41 | 98.84 | 10% | 21.241 | 2099.4604
1048 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-08-02 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1528-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-1-86 to MH-1-85 at Road MCA0 | 221.14 | 82.15 | 10% | 22.114 | 1816.6651
1049 | B5 33.31.00.02 |  | 2026-08-02 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1543-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-1-87 to MH-1-88 at Road MCA0 |  | 97.31 | 45% | 0 | 0
1050 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-08-02 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1544-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-1-86 to MH-1-87 at Road MCA0 | 221.14 | 100.44 | 45% | 99.513 | 9995.0857
1051 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-08-02 | SUD1-02-011-TDC-TS9-1-TEL-FIR-1546-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 101 To 102 in road MC20 | 617.84 | 35.88 | 25% | 154.46 | 5542.0248
1052 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-08-02 | SUD1-02-011-TDC-TS9-1-TEL-FIR-1547-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 104 To 105 in road MC20 | 617.84 | 35.88 | 25% | 154.46 | 5542.0248
1053 | B2.33 71 19.01 | Road crossing ducts, 2 ways (2 x 150mm PVC) | 2026-08-02 | SUD1-02-011-TDC-TS9-1-LIT-FIR-1548-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (2X160mm) from Manhole 45 To Manhole 46 for Street Lighting Duct Bank in road MC20 | 188 | 9.10 | 25% | 47 | 427.7
1054 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-08-02 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1549-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-1-87 to MH-1-86 at Road MCA0 | 221.14 | 100.44 | 10% | 22.114 | 2221.1302
1055 | B4.33 14 13.3 | TSE NETWORK: 225mm Diameter (Depth: 0.0m - 1.5m) | 2026-08-03 | SUD1-02-011-TDC-TS9-1-IRR-FIR-1564-00 | Check Excavation for Road crossing 125mm O.D HDPE Pipes at Road MCG0 (Attached three Locations) | 179.43 | 98.39 | 5% | 8.9715 | 882.7059
1056 | B4.33 14 13.5 | TSE NETWORK: 225mm Diameter (Depth: 0.0m - 1.5m) | 2026-08-03 | SUD1-02-011-TDC-TS9-1-IRR-FIR-1565-00 | Check Excavation for Road crossing 225mm O.D HDPE Pipes at Road MCG0 | 290.97 | 26.88 | 5% | 14.5485 | 391.0637
1057 | B5 33.05.13.09 | SEWERAGE NETWORK: Manhole (Depth 4.51m to 5.5m) Internal Diameter (1200mm) | 2026-08-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1566-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-12-5 at Road MCH0 | 290.97 | 01 | 5% | 14.5485 | 14.5485
1058 | B5 33.05.13.09 | SEWERAGE NETWORK: Manhole (Depth 4.51m to 5.5m) Internal Diameter (1200mm) | 2026-08-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1567-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-12-6 at Road MCH0 | 179.43 | 01 | 5% | 8.9715 | 8.9715
1059 | B5 33.05.13.08 | SEWERAGE NETWORK: Manhole (Depth 3.51m to 4.5m) Internal Diameter (1200mm) With Backdrop | 2026-08-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1568-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-12-7 at Road MCH0 | 21251.83 | 01 | 5% | 1062.5915 | 1062.5915
1060 | B5 33.31.00.04 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 3.51m to 4.5m) | 2026-08-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1569-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-4 to MH-12-5 at Road MCH0 | 397.67 | 98.74 | 5% | 19.8835 | 1963.2968
1061 | B5 33.31.00.04 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 3.51m to 4.5m) | 2026-08-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1570-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-5 to MH-12-6 at Road MCH0 | 397.67 | 98.86 | 5% | 19.8835 | 1965.6828
1062 | B5 33.31.00.03 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 2.51 m to 3.5m) | 2026-08-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1571-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-6 to MH-12-7 at Road MCH0 | 329.77 | 86.36 | 5% | 16.4885 | 1423.9469
1063 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-1572-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/36/5 at Road MCE0 | 12376.13 | 01 | 10% | 1237.613 | 1237.613
1064 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-1573-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/36/4 at Road MCE0 | 12376.13 | 01 | 10% | 1237.613 | 1237.613
1065 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-1574-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/36/3 at Road MCE0 | 12376.13 | 01 | 10% | 1237.613 | 1237.613
1066 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-1575-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/36/2 at Road MCE0 | 12376.13 | 01 | 10% | 1237.613 | 1237.613
1067 | B6.33 05 39.6 | STORM WATER NETWORK: Manhole Diameter :-1500mm (Depth: > 2.5m) | 2026-08-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-1576-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/36/1 at Road MCE0 | 19537.02 | 01 | 10% | 1953.702 | 1953.702
1068 | B6.33 42 11.6 | STORM WATER NETWORK: GRP Pipes 500mm (Depth: 0.0m - 1.5m) | 2026-08-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-1577-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/36/5 to STA-A1/36/4 at Road MCE0 | 366.63 | 63.80 | 5% | 18.3315 | 1169.5497
1069 | B6.33 42 11.9 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51m - 2.5m) | 2026-08-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-1578-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/36/4 to STA-A1/36/3 at Road MCE0 | 448.1 | 63.80 | 5% | 22.405 | 1429.439
1070 | B6.33 42 11.10 | STORM WATER NETWORK: GRP Pipes 600mm Diameter (Depth: 1.51 to 2.50m) | 2026-08-24 | SUD1-02-011-TDC-TS9-1-STR-FIR-1579-01 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/36/3 TO STA-A1/36/2 at Road MCE0 | 461.68 | 63.80 | 10% | 46.168 | 2945.5184
1071 | B6.33 42 11.10 | STORM WATER NETWORK: GRP Pipes 600mm Diameter (Depth: 1.51 to 2.50m) | 2026-09-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-1580-02 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/36/2 to STA-A1/36/1 at Road MCE0 | 461.68 | 64.25 | 10% | 46.168 | 2966.294
1072 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-1587-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from Manhole # MH-G2/6/4 to CB-G2/6/4 B (S) at Road MCG0 | 377.3 | 14.77 | 45% | 169.785 | 2507.7244
1073 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-1588-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from Manhole # FMH-A2/9/20-398 to CB-A2/9/20-398 (S) at Road MCG0 | 377.3 | 2.90 | 45% | 169.785 | 492.3765
1074 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-1589-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from Manhole # MH-G2/6/5 to CB-G2/6/5 A (S) at Road MCG0 | 377.3 | 15.28 | 45% | 169.785 | 2594.3148
1075 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-1590-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from Manhole # MH-G2/6/5 to CB-G2/6/5 B (S) at Road MCG0 | 377.3 | 13.97 | 45% | 169.785 | 2371.8965
1076 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-1591-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from Manhole # FMH-A2/9/20-396 to CB-A2/9/20-396 (S) at Road MCG0 | 377.3 | 3.24 | 45% | 169.785 | 550.1034
1077 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-1592-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from Manhole # MH-G2/6/6 to CB-G2/6/6 A (S) at Road MCG0 | 377.3 | 11.17 | 45% | 169.785 | 1896.4985
1078 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-1593-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from Manhole # MH-G2/6/6 to CB-G2/6/6 C (S) at Road MCG0 | 377.3 | 17.83 | 45% | 169.785 | 3027.2665
1079 | B6.33 42 11.22 | STORM WATER NETWORK: GRP Pipes 1000mm (Depth: 1.51m - 2.5m) | 2026-08-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-1597-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling (Bottom Sub grade)Between Existing Manhole # FIMH G2/6 to MH-G2/6/1 at Road MCG0 | 884.56 | 92.65 | 10% | 88.456 | 8195.4484
1080 | B6.33 42 11.22 | STORM WATER NETWORK: GRP Pipes 1000mm (Depth: 1.51m - 2.5m) | 2026-08-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-1598-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling (Bottom sub grade) Between Manhole # MH G2/6/1 to MH-G2/6/2 at Road MCG0 | 884.56 | 89.00 | 10% | 88.456 | 7872.584
1081 | B6.33 42 11.19 | STORM WATER NETWORK: GRP 900m Pipes (Depth 1.51 - 2.50m) | 2026-08-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-1599-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling (Bottom sub grade) Between Manhole # MH G2/6/2 to MH-G2/6/3 at Road MCG0 | 743.93 | 89.25 | 10% | 74.393 | 6639.5752
1082 | B6.33 42 11.16 | STORM WATER NETWORK: GRP 800m Pipes (Depth 1.51 - 2.50m) | 2026-08-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-1600-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling (Bottom sub grade) Between Manhole # MH G2/6/3 to MH-G2/6/4 at Road MCG0 | 639.17 | 89.50 | 10% | 63.917 | 5720.5715
1083 | B6.33 42 11.13 | STORM WATER NETWORK: GRP Pipes 700mm Diameter (Depth:1.51 to 2.50m) | 2026-08-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-1601-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling (Bottom sub grade) Between Manhole # MH G2/6/4 to FMH-A2/9/20-398 at Road MCG0 | 544.12 | 43.96 | 10% | 54.412 | 2391.9515
1084 | B6.33 42 11.10 | STORM WATER NETWORK: GRP Pipes 600mm Diameter (Depth: 1.51 to 2.50m) | 2026-08-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-1602-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling (Bottom sub grade) Between Manhole # FMH- A2/9/20-398 to MH G2/6/5 at Road MCG0 | 461.68 | 44.19 | 10% | 46.168 | 2040.1639
1085 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-08-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1603-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-1-88-3 to MH-1-88-4 at Road MCD0 | 212.41 | 96.68 | 45% | 95.5845 | 9241.1095
1086 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-08-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1604-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-1-88-5 to MH-1-88-4 at Road MCD0 | 212.41 | 98.74 | 45% | 95.5845 | 9438.0135
1087 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0m to 1.5m) | 2026-08-12 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1605-01 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-21-3 to MH-12-21-2 at Road MCD0 | 212.41 | 78.85 | 30% | 63.723 | 5024.5585
1088 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes with DIA 400mm for Catch Basin | 2026-08-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-1606-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from Manhole # MH-G2/6/1 to CB-G2/6/1 (D) at Road MCG0 | 602.32 | 10.53 | 10% | 60.232 | 634.243
1089 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-1607-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from Manhole # MH-G2/6/1 to CB-G2/6/1 B (S) at Road MCG0 | 377.3 | 17.45 | 45% | 169.785 | 2962.7482
1090 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0m to 1.5m) | 2026-08-12 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1608-01 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-1-93-4 to MH-1-93-3 at Road MCC0 | 212.41 | 78.87 | 30% | 63.723 | 5025.833
1091 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-1619-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from Manhole # CB-G2/6/1(D) to CB-G2/6/1 A (S) at Road MCG0 | 377.3 | 28.80 | 45% | 169.785 | 4889.808
1092 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-04 | SUD1-02-011-TDC-TS9-1-STR-FIR-1620-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Existing Manhole # FIMH-G2/6 to CB-G2/6 (S) at Road MCG0 | 377.3 | 22.78 | 45% | 169.785 | 3867.7023
1093 | B2.33 71 19.01 | Road crossing ducts, 2 ways (2 x 150mm PVC) | 2026-08-04 | SUD1-02-011-TDC-TS9-1-LIT-FIR-1623-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (2X160mm) from Manhole 41 To Manhole 42 for Street Lighting Duct Bank in road MC20 | 188 | 9.10 | 25% | 47 | 427.7
1094 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-08-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1633-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-8 to MH-12-7-1-2 at Road MCH0 | 212.41 | 97.70 | 5% | 10.6205 | 1037.6228
1095 | B5 33.05.13.08 | SEWERAGE NETWORK: Manhole (Depth 3.51m to 4.5m) Internal Diameter (1200mm) With Backdrop | 2026-08-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1634-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-12-8 at Road MCH0 | 21251.83 | 01 | 5% | 1062.5915 | 1062.5915
1096 | B5 33.05.13.01 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 0m- 1.50m) | 2026-08-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1635-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-12-7-1-2 at Road MCH0 | 8820.42 | 1 | 5% | 441.021 | 441.021
1097 | B5 33.31.00.03 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 2.51 m to 3.5m) | 2026-08-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1637-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-8 to MH-12-7 at Road MCH0 | 329.77 | 67.36 | 5% | 16.4885 | 1110.6654
1098 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-04 | SUD1-02-011-TDC-TS9-1-STR-FIR-1640-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from Manhole # CB-G2/6/2 (D) to CB-G2/6/2 A (S) at Road MCG0 | 377.3 | 24.10 | 45% | 169.785 | 4091.8185
1099 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes with DIA 400mm for Catch Basin | 2026-08-04 | SUD1-02-011-TDC-TS9-1-STR-FIR-1641-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from Manhole # MH-G2/6/2 to CB-G2/6/2 (D) at Road MCG0 | 602.32 | 11.47 | 10% | 60.232 | 690.861
1100 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-04 | SUD1-02-011-TDC-TS9-1-STR-FIR-1642-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from Manhole # MH-G2/6/2 to CB-G2/6/2 B (S) at Road MCG0 | 377.3 | 16.47 | 45% | 169.785 | 2796.3589
1101 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-04 | SUD1-02-011-TDC-TS9-1-STR-FIR-1643-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from Manhole # CB-G2/6/3 (D) to CB-G2/6/3 A (S) at Road MCG0 | 377.3 | 28.80 | 45% | 169.785 | 4889.808
1102 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes with DIA 400mm for Catch Basin | 2026-08-04 | SUD1-02-011-TDC-TS9-1-STR-FIR-1644-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from Manhole # MH-G2/6/3 to CB-G2/6/3(D) at Road MCG0 | 602.32 | 12.67 | 10% | 60.232 | 763.1394
1103 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-04 | SUD1-02-011-TDC-TS9-1-STR-FIR-1645-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from Manhole # MH-G2/6/3 to CB-G2/6/3 B (S) at Road MCG0 | 377.3 | 15.75 | 45% | 169.785 | 2674.1137
1104 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-04 | SUD1-02-011-TDC-TS9-1-STR-FIR-1646-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from Manhole # CB-G2/6/4 (D) to CB-G2/6/4 A (S)at Road MCG0 | 377.3 | 28.80 | 45% | 169.785 | 4889.808
1105 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-04 | SUD1-02-011-TDC-TS9-1-STR-FIR-1647-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from Manhole # MH-G2/6/7 to CB-G2/6/7 (S) at Road MCG0 | 377.3 | 27.43 | 45% | 169.785 | 4657.2025
1106 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-04 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1648-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Plot (5) STA: 0+020 to STA: 0+110 | 22.31 | 2274.03 | 100% | 22.31 | 50733.6093
1107 | B1.31 22 00.01 | Earth works & Site Grading (Road Excavation/cutting) | 2026-08-04 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1649-00 | Check Coordinates and bottom level Road/carriageway Excavation/cutting upto bottom of Sub-Grade STA: 5+230 to STA: 5+390 at Road # MC20 | 13.58 | 208.81 | 10% | 1.358 | 283.564
1108 | B1.31 22 00.03 | Earth works & Site Grading | 2026-08-04 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1650-00 | Check Coordinates and bottom level Road Filling and compaction test of bottom Sub-Grade of Road # MC20, STA: 5+230 to STA: 5+390 | 22.31 | 430.02 | 10% | 2.231 | 959.3746
1109 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-08-04 | SUD1-02-011-TDC-TS9-1-TEL-FIR-1651-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 094 To 095 in road MC20 | 617.84 | 47.79 | 25% | 154.46 | 7381.6434
1110 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-08-04 | SUD1-02-011-TDC-TS9-1-TEL-FIR-1652-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 092 To 093 in road MC20 | 617.84 | 35.88 | 25% | 154.46 | 5542.0248
1111 | B3.33 14 13.1 | POTABLE WATER NETWORK: HOPE Pipes 160mm Diameter (Depth O.Om to 1.50m) | 2026-08-04 | SUD1-02-011-TDC-TS9-1-PW-FIR-1653-00 | Check Sand bedding and pipe installation of Road crossing potable water HDPE Pipes (Diameter 160mm) at STA: +204.25 & ST: +450.99, Road MCG0 | 101.84 | 54.66 | 45% | 45.828 | 2504.9585
1112 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-08-05 | SUD1-02-011-TDC-TS9-1-TEL-FIR-1657-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 026 To 027 in road MCG0 | 123 | 26.69 | 60% | 73.8 | 1969.722
1113 | B4.33 14 13.5 | TSE NETWORK: 225mm Diameter (Depth: 0.0m - 1.5m) | 2026-08-04 | SUD1-02-011-TDC-TS9-1-IRR-FIR-1655-00 | Check Sand bedding and pipe installation of Road crossing Irrigation water HDPE Pipes (Diameter 225mm) at ST: +685.57 & ST: +538.51 at Road MCG0 | 290.97 | 25.69 | 45% | 130.9365 | 3363.7587
1114 | B4.33 14 13.3 | TSE NETWORK: 225mm Diameter (Depth: 0.0m - 1.5m) | 2026-08-04 | SUD1-02-011-TDC-TS9-1-IRR-FIR-1656-00 | Check Sand bedding and pipe installation of Road crossing Irrigation water HDPE Pipes (Diameter 125mm) at ST: +460.28 ,ST: +156.39 & ST: +00.00 at Road MCG0 & MCZ0 | 179.43 | 98.39 | 45% | 80.7435 | 7944.353
1115 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-08-05 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1659-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling 5th layer Between Existing Manhole # MH 39-23 to MH 52-1 at Road MCF0 (Bottom Sub grade) | 221.14 | 98.80 | 5% | 11.057 | 1092.4316
1116 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-08-05 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1660-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling 5th layer Between Manhole # MH 52-1 to MH 52-2 at Road MCF0 (Bottom Subgrade) | 221.14 | 98.80 | 5% | 11.057 | 1092.4316
1117 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-08-05 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1661-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling 5th layer Between Manhole # MH 52-2 to MH 52-3 at Road MCF0(Bottom Sub grade) | 221.14 | 98.80 | 5% | 11.057 | 1092.4316
1118 | B6.33 42 11.22 | STORM WATER NETWORK: GRP Pipes 1000mm (Depth: 1.51m - 2.5m) | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1662-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling 3rd layer Between Existing Manhole # FIMH G2/11 to MH-G2/11/1 at Road MCF0 (Bottom Subgrade) | 884.56 | 92.96 | 10% | 88.456 | 8222.8698
1119 | B6.33 42 11.23 | STORM WATER NETWORK: GRP 1000m Pipes (Depth 2.51 - 3.50m) | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1663-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling 3rd layer Between Manhole # MH G2/11/1 to MH-G2/11/2 at Road MCF0 (Bottom Subgrade) | 1017.44 | 89.00 | 10% | 101.744 | 9055.216
1120 | B6.33 42 11.20 | STORM WATER NETWORK: GRP 900m Pipes (Depth 2.51 - 3.50m) | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1664-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling 3rd layer Between Manhole # MH G2/11/2 to MH-G2/11/3 at Road MCF0 (Bottom Subgrade) | 875.83 | 89.25 | 10% | 87.583 | 7816.7828
1121 | B1.31.22.00.04 | Embankments to the Plot | 2026-08-05 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1665-00 | Check Coordinates level and Compaction F.D.T for Embankment 11th layer at PLOT (5), STA: 0+360 to STA: 0+440 | 22.31 | 2669.67 | 100% | 22.31 | 59560.3377
1122 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1667-00 | Inspection Gravity and Leakage test pipeline from # MH-G2/6/7 to CB-G2/6/7(S) at Road MCG0 | 377.3 | 27.43 | 10% | 37.73 | 1034.9339
1123 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1668-00 | Inspection Gravity and Leakage test pipeline from # MH-G2/6/6 to CB-G2/6/6C(S) at Road MCG0 | 377.3 | 17.83 | 10% | 37.73 | 672.7259
1124 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1669-00 | Inspection Gravity and Leakage test pipeline from # MH-G2/6/6 to CB-G2/6/6 A (S) at Road MCG0 | 377.3 | 11.17 | 10% | 37.73 | 421.4441
1125 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1670-00 | Inspection Gravity and Leakage test pipeline from # FMH-A2/9/20-396 to CB­A2/9/20-396 (S) at Road MCGO | 377.3 | 3.24 | 10% | 37.73 | 122.2452
1126 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1671-00 | Inspection Gravity and Leakage test pipeline from # MH-G2/6/5 to CB-G2/6/5 A (S) at Road MCG0 | 377.3 | 15.28 | 10% | 37.73 | 576.5144
1127 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1672-00 | Inspection Gravity and Leakage test pipeline from # MH-G2/6/5 to CB-G2/6/5 B (S) at Road MCG0 | 377.3 | 13.97 | 10% | 37.73 | 527.0881
1128 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1673-00 | Inspection Gravity and Leakage test pipeline from # FMH-A2/9/20-398 to CB­A2/9/20-398 (S) at Road MCGO | 377.3 | 2.90 | 10% | 37.73 | 109.417
1129 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1674-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from Manhole # FIMH-G2/6 to CB-G2/6 (S) at Road MCG0 | 377.3 | 22.78 | 45% | 169.785 | 3867.7023
1130 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1676-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # FIMH-G2/11 to CB-G2/11 (S) at Road MCF0 | 377.3 | 23.25 | 5% | 18.865 | 438.6113
1131 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1677-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/11/1 to CB-G2/11/1 B (S) at Road MCF0 | 377.3 | 17.45 | 5% | 18.865 | 329.1943
1132 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400mm | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1678-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/11/1 to CB-G2/11/1 (D) at Road MCF0 | 602.32 | 10.53 | 5% | 30.116 | 317.1215
1133 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1679-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin #CB-G2/11/1(D) to CB-G2/11/1 A(S) at RoadMCF0 | 377.3 | 28.80 | 5% | 18.865 | 543.312
1134 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1680-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/11/2 to CB-G2/11/2 B (S) at Road MCF0 | 377.3 | 16.47 | 5% | 18.865 | 310.7065
1135 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400mm | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1681-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/11/2 to CB-G2/11/2 (D) at Road MCF0 | 602.32 | 11.47 | 5% | 30.116 | 345.4305
1136 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1682-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-G2/11/2 (D) to CB-G2/11/2 A(S)at Road MCF0 | 377.3 | 23.73 | 5% | 18.865 | 447.6665
1137 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1683-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/11/3 to CB-G2/11/3 B (S) at Road MCF0 | 377.3 | 15.75 | 5% | 18.865 | 297.1238
1138 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400mm | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1684-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/11/3 to CB-G2/11/3 (D) at Road MCF0 | 602.32 | 12.67 | 5% | 30.116 | 381.5697
1139 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1685-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-G2/11/3 (D) to CB-G2/11/3 A(S) at Road MCF0 | 377.3 | 28.80 | 10% | 37.73 | 1086.624
1140 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1686-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/11/4 to CB-G2/11/4 B (S) at Road MCF0 | 377.3 | 14.78 | 5% | 18.865 | 278.8247
1141 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400mm | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1687-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/11/4 to CB-G2/11/4 (D) at Road MCF0 | 602.32 | 13.63 | 5% | 30.116 | 410.4811
1142 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1688-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-G2/11/4 (D) to CB-G2/11/4 A (S) at Road MCF0 | 377.3 | 28.80 | 5% | 18.865 | 543.312
1143 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1689-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # FMH-A2/9/20-399 to CB-A2/9/20-399 (S) at Road MCF0 | 377.3 | 2.90 | 5% | 18.865 | 54.7085
1144 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1690-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/11/5 to CB-G2/11/5 B(S) at Road MCF0 | 377.3 | 13.97 | 5% | 18.865 | 263.5441
1145 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1691-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/11/5 to CB-G2/11/5 A (S) at Road MCF0 | 377.3 | 15.28 | 5% | 18.865 | 288.2572
1146 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1692-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # FMH-A2/9/20-397 to CB-A2/9/20-397 (S) at Road MCF0 | 377.3 | 3.23 | 5% | 18.865 | 60.934
1147 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1693-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin #From MH-G2/11/6 to CB-G2/11/6 A (S) atRoad MCF0 | 377.3 | 12.03 | 5% | 18.865 | 226.946
1148 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-10 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1694-00 | Check Coordinates level and Compaction F.D.T for Embankment 12th layer at PLOT (5), STA: 0+360 to STA: 0+430 | 22.31 | 2443.85 | 100% | 22.31 | 54522.2935
1149 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1695-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/11/6 to CB-G2/11/6 C (S) at Road MCF0 | 377.3 | 26.29 | 5% | 18.865 | 495.9609
1150 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1696-00 | Check Installation of catch basin CB-G2/11 (S) include the connecting pipe opening at Road MCF0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1151 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1697-00 | Check Installation of catch basin CB-G2/11/1 A (S) include the connecting pipe opening at Road MCF0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1152 | B6.33 05 39.16 | STORM WATER NETWORK: - Catch Basin Double | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1698-00 | Check Installation of catch basin CB-G2/11/1 (D) include the connecting pipe opening at Road MCF0 | 12444.99 | 01 | 35% | 4355.7465 | 4355.7465
1153 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1699-00 | Check Installation of catch basin CB-G2/11/1 B (S) include the connecting pipe opening at Road MCF0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1154 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1700-00 | Check Installation of catch basin CB-G2/11/2 A(S) include the connecting pipe opening at Road MCF0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1155 | B6.33 05 39.16 | STORM WATER NETWORK: - Catch Basin Double | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1701-00 | Check Installation of catch basin CB-G2-11/2 (D) include the connecting pipe opening at Road MCF0 | 12444.99 | 01 | 35% | 4355.7465 | 4355.7465
1156 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1702-00 | Check Installation of catch basin CB-G2/11/2 B (S) include the connecting pipe opening at Road MCF0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1157 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1703-00 | Check Installation of catch basin CB-G2/11/3 A (S) include the connecting pipe opening at Road MCF0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1158 | B6.33 05 39.16 | STORM WATER NETWORK: - Catch Basin Double | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1704-00 | Check Installation of catch basin CB-G2/11/3 (D) include the connecting pipe opening at Road MCF0 | 12444.99 | 01 | 35% | 4355.7465 | 4355.7465
1159 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1705-00 | Check Installation of catch basin CB-G2/11/3 B (S) include the connecting pipe opening at Road MCF0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1160 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-05 | SUD1-02-011-TDC-TS9-1-STR-FIR-1706-00 | Check Installation of catch basin CB-G2/11/4 A (S) include the connecting pipe opening at Road MCF0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1161 | B6.33 05 39.16 | STORM WATER NETWORK: - Catch Basin Double | 2026-08-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-1707-00 | Check Installation of catch basin CB-G2/11/4 (D) include the connecting pipe opening at Road MCF0 | 12444.99 | 01 | 35% | 4355.7465 | 4355.7465
1162 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-1708-00 | Check Installation of catch basin CB-G2/11/4 B (S) include the connecting pipe opening at Road MCF0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1163 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-1709-00 | Check Installation of catch basin CB-A2/9/20-399 (S) include the connecting pipe opening at Road MCF0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1164 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-1710-00 | Check Installation of catch basin CB-G2/11/5 A (S) Include the connecting pipe opening at Road MCF0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1165 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-1711-00 | Check Installation of catch basin CB-G2/11/5 B (S) Include the connecting pipe opening at Road MCF0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1166 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-1712-00 | Check Installation of catch basin CB-A2/9/20-397 (S) Include the connecting pipe opening at Road MCF0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1167 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-1713-00 | Check Installation of catch basin CB-G2/11/6 A (S) Include the connecting pipe opening at Road MCF0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1168 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-1714-00 | Check Installation of catch basin CB-G2/11/6 B (S) Include the connecting pipe opening at Road MCF0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1169 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-1715-00 | Check Installation of catch basinCB-G2/11/6 C (S) Include the connecting pipe opening at Road MCF0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1170 | B1.31 22 00.03 | Earth works & Site Grading | 2026-08-06 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1727-00 | Check Coordinates level and Compaction F.D.T for (Right Side Shoulder) Embankment 2nd layer at Road # MCB0, STA: 1+110 to STA: 1+200 | 22.31 | 303.74 | 100% | 22.31 | 6776.4394
1171 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0m - 1.5m) | 2026-08-12 | SUD1-02-011-TDC-TS9-1-IRR-FIR-1728-00 | Check Sand bedding and pipe installation of Road crossing Irrigation water HDPE Pipes (Diameter 125mm) ST:+212.21 & ST:+265.15 at Road MCE0 | 82.44 | 27.36 | 45% | 37.098 | 1015.0013
1172 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-1730-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/16 (S) at Road MCE0 | 5124.07 | 1.00 | 15% | 768.6105 | 768.6105
1173 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-1731-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/16/1 A (S) at Road MCE0 | 5124.07 | 1.00 | 15% | 768.6105 | 768.6105
1174 | B6.33 05 39.16 | STORM WATER NETWORK: - Catch Basin Double | 2026-08-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-1732-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/16/1 (D) at Road MCE0 | 12444.99 | 1.00 | 15% | 1866.7485 | 1866.7485
1175 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-1733-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/16/1 B (S) at Road MCE0 | 5124.07 | 1.00 | 15% | 768.6105 | 768.6105
1176 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-1734-02 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/16/2 A (S) at Road MCE0 | 5124.07 | 1.00 | 15% | 768.6105 | 768.6105
1177 | B6.33 05 39.16 | STORM WATER NETWORK: - Catch Basin Double | 2026-08-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-1735-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/16/2 (D) at Road MCE0 | 12444.99 | 1.00 | 15% | 1866.7485 | 1866.7485
1178 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0.0m - 1.5m) | 2026-08-08 | SUD1-02-011-TDC-TS9-1-IRR-FIR-1736-00 | Check Excavation for Road crossing 125mm O.D HDPE Pipes at Road MCE0 (Attached three Locations) | 82.44 | 94.48 | 5% | 4.122 | 389.4466
1179 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400mm for Catch Basin | 2026-08-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-1737-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from Manhole # MH-G2/6/4 to CB-G2/6/4 (D)at Road MCG0 | 602.32 | 13.63 | 45% | 271.044 | 3694.3297
1180 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0.0m - 1.5m) | 2026-08-08 | SUD1-02-011-TDC-TS9-1-IRR-FIR-1738-00 | Check Excavation for Road crossing 125mm O.D HDPE Pipes at Road MCF0 (Attached Three Locations) | 82.44 | 67.09 | 5% | 4.122 | 276.545
1181 | B3.33 14 13.1 | POTABLE WATER NETWORK: HDPE Pipes 160mm Diameter (Depth 0.0m to 1.50m) | 2026-08-08 | SUD1-02-011-TDC-TS9-1-PW-FIR-1739-00 | Check Coordinates level and Excavation width Bottom level and compaction for Road crossing potable water HDPE pipelines (Diameter 160mm) at Road MCE0 | 101.84 | 68.06 | 5% | 5.092 | 346.5615
1182 | B3.33 14 13.1 | POTABLE WATER NETWORK: HDPE Pipes 160mm Diameter (Depth 0.0m to 1.50m) | 2026-08-08 | SUD1-02-011-TDC-TS9-1-PW-FIR-1740-00 | Check Coordinates level and Excavation width Bottom level and compaction for Road crossing potable water HDPE pipelines (Diameter 160mm) at Road MCF0 | 101.84 | 110.58 | 5% | 5.092 | 563.0734
1183 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-1741-00 | Check Installation of catch basin CB-G2/6 (S) include the connecting pipe opening at Road MCG0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1184 | B6.33 05 39.16 | STORM WATER NETWORK: - Catch Basin Double | 2026-08-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-1742-00 | Check Installation of catch basin CB-G2/6/1 (D) include the connecting pipe opening at Road MCG0 | 12444.99 | 01 | 35% | 4355.7465 | 4355.7465
1185 | B6.33 05 39.16 | STORM WATER NETWORK: - Catch Basin Double | 2026-08-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-1743-00 | Check Installation of catch basin CB-G2/6/2 (D) include the connecting pipe opening at Road MCG0 | 12444.99 | 01 | 35% | 4355.7465 | 4355.7465
1186 | B6.33 05 39.16 | STORM WATER NETWORK: - Catch Basin Double | 2026-08-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-1744-00 | Check Installation of catch basin CB-G2/6/3 (D) include the connecting pipe opening at Road MCG0 | 12444.99 | 01 | 35% | 4355.7465 | 4355.7465
1187 | B6.33 05 39.16 | STORM WATER NETWORK: - Catch Basin Double | 2026-08-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-1745-00 | Check Installation of catch basin CB-G2/6/4 (D) include the connecting pipe opening at Road MCG0 | 12444.99 | 01 | 35% | 4355.7465 | 4355.7465
1188 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-1746-00 | Check Installation of catch basin CB-G2/6/6 B (S) include the connecting pipe opening at Road MCG0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1189 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-1747-00 | Check Installation of catch basin CB-G2/6/6 C (S) include the connecting pipe opening at Road MCG0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1190 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-1748-00 | Check Installation of catch basin CB-G2/6/7 (S) include the connecting pipe opening at Road MCG0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1191 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-08-12 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1760-01 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-1-93-1 to MH-1-93-2 at Road MCC0 | 212.41 | 98.74 | 30% | 63.723 | 6292.009
1192 | B3.33 14 13.5 | POTABLE WATER NETWORK: HDPE Pipes 315 Diameter (Depth 0 to 1.50m) | 2026-08-06 | SUD1-02-011-TDC-TS9-1-PW-FIR-1761-00 | Check Coordinates level and Excavation width Bottom level and compaction for potable water pipeline from Station ST: 1+750 to ST: 2+169.08 Road MCZ0 | 290.97 | 419.08 | 5% | 14.5485 | 6096.9854
1193 | B3.33 14 13.6 | POTABLE WATER NETWORK: HDPE Pipes 315 Diameter (Depth 1.51m to 2.50m) | 2026-08-06 | SUD1-02-011-TDC-TS9-1-PW-FIR-1762-00 | Check Coordinates level and Excavation width Bottom level and compaction for potable water pipeline from Station ST: 1+625.00 to ST: 1+750.00 Road MCZ0 | 301.64 | 125.00 | 5% | 15.082 | 1885.25
1194 | B3.33 14 13.7 | POTABLE WATER NETWORK: HDPE Pipes 315 Diameter (Depth 2.51m to 3.50m) | 2026-08-06 | SUD1-02-011-TDC-TS9-1-PW-FIR-1763-00 | Check Coordinates level and Excavation width Bottom level and compaction for potable water pipeline from Station ST: 1+575.00 to ST: 1+625.00 Road MCZ0 | 412.21 | 50.00 | 5% | 20.6105 | 1030.525
1195 | B3.33 14 13.8 | POTABLE WATER NETWORK: HDPE Pipes 315 Diameter (Depth 3.51m to 4.50m) | 2026-08-06 | SUD1-02-011-TDC-TS9-1-PW-FIR-1764-00 | Check Coordinates level and Excavation width Bottom level and compaction for potable water pipeline from Station ST: 1+538.50 to ST: 1+575.00 MCZ0 | 481.08 | 36.48 | 5% | 24.054 | 877.4899
1196 | B1.31 22 00.01 | Earth works & Site Grading (Road Excavation/cutting) | 2026-08-10 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1770-01 | Check Coordinates and bottom level Road cutting and compaction test of bottom Sub-Grade Shoulder (left side) at Road # MC10 STA: 3+040 to STA: 3+250 | 13.58 | 1755.99 | 5% | 0.679 | 1192.3172
1197 | B1.31 22 00.03 | Earth works & Site Grading | 2026-08-10 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1771-01 | Check Coordinates and bottom level Road Filling and compaction test of bottom Sub-Grade of shoulders (Left side) at Road # MC10, STA: 3+040 to STA: 3+250 | 22.31 | 144.94 | 5% | 1.1155 | 161.6806
1198 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-08 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1773-00 | Check Coordinates level and Compaction F.D.T for Embankment 12th layer at PLOT (5), STA: 0+240 to STA: 0+360 | 22.31 | 4022.53 | 100% | 22.31 | 89742.6443
1199 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-1774-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/16/2 B (S) at Road MCE0 | 5124.07 | 1.00 | 5% | 256.2035 | 256.2035
1200 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-1775-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/16/3 A (S) at Road MCE0 | 5124.07 | 1.00 | 5% | 256.2035 | 256.2035
1201 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0.0m - 1.5m) | 2026-08-08 | SUD1-02-011-TDC-TS9-1-IRR-FIR-1776-00 | Check Excavation for Road crossing 125mm O.D HDPE Pipes at Road MCD0 | 82.44 | 22.57 | 25% | 20.61 | 465.1677
1202 | B4.33 14 13.4 | TSE NETWORK: 125mm Diameter (Depth: >1.5m) | 2026-08-08 | SUD1-02-011-TDC-TS9-1-IRR-FIR-1777-00 | Check Excavation for Road crossing 125mm O.D HDPE Pipes at Road MCF0 | 86.32 | 30.57 | 25% | 21.58 | 659.7006
1203 | B4.33 14 13.5 | TSE NETWORK: 225mm Diameter (Depth: 0.0m to 1.5m) | 2026-08-08 | SUD1-02-011-TDC-TS9-1-IRR-FIR-1778-00 | Check Excavation for Road crossing 225mm O.D HDPE Pipes at Road MCF0 | 179.43 | 27.23 | 25% | 44.8575 | 1221.4697
1204 | B4.33 14 13.5 | TSE NETWORK: 225mm Diameter (Depth: 0.0m to 1.5m) | 2026-08-08 | SUD1-02-011-TDC-TS9-1-IRR-FIR-1779-00 | Check Excavation for Road crossing 225mm O.D HDPE Pipes at Road MCE0 | 179.43 | 24.64 | 25% | 44.8575 | 1105.2888
1205 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-08-08 | SUD1-02-011-TDC-TS9-1-TEL-FIR-1780-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 035 To 036 in road MC20 | 617.84 | 34.24 | 25% | 154.46 | 5288.7104
1206 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-08-08 | SUD1-02-011-TDC-TS9-1-TEL-FIR-1781-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 037 To 038 in road MC20 | 617.84 | 40.47 | 25% | 154.46 | 6250.9962
1207 | B2.33 71 19.03 | Road crossing ducts, 6 ways (6 x 150mm PVC) | 2026-08-08 | SUD1-02-011-TDC-TS9-1-LIT-FIR-1782-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (6X160mm) from Manhole 33 To Manhole 34 for Street Lighting Duct Bank in road MC20 | 926.27 | 9.10 | 25% | 231.5675 | 2107.2642
1208 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-08 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1783-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at Plot (5) STA: 0+350 to STA: 0+467 | 22.31 | 1288.83 | 100% | 22.31 | 28753.7973
1209 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-09 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1784-00 | Check Coordinates level and Compaction F.D.T for Embankment 6th layer at PLOT (2), STA: 0+570 to STA: 0+720 | 22.31 | 4,916.22 | 100% | 22.31 | 109680.8682
1210 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-1785-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole # MH-G2/6/4 to CB-G2/6/4 B(S) at Road MCG0 (Last Layer) | 461.68 | 14.77 | 5% | 23.084 | 340.9507
1211 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-1786-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole # CB-A2/9/20-398 (s) to FMH-A2/9/20-398 at Road MCG0 (Last Layer) | 461.68 | 2.90 | 5% | 23.084 | 66.9436
1212 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-1787-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole CB-G2/6/5 A (s) to MH-G2/6/5 at Road MCG0 (Last Layer) | 461.68 | 15.28 | 5% | 23.084 | 352.7235
1213 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-1788-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole # CB-G2/6/5 B (s) to MH-G2/6/5 at Road MCG0 (Last Layer) | 461.68 | 13.97 | 5% | 23.084 | 322.4835
1214 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-1789-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole # CB-A2/9/20-396 (s} to FMH-A2/9/20-396 at Road MCG0 (Last Layer) | 461.68 | 3.24 | 5% | 23.084 | 74.7922
1215 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-1790-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole CB-G2/6/6 A (s) to MH-G2/6/6 at Road MCG0 (Last Layer) | 461.68 | 11.17 | 5% | 23.084 | 257.8483
1216 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-1791-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole # CB-G2/6/6 C (s) to MH-G2/6/6 at Road MCG0 (Last Layer) | 461.68 | 17.83 | 5% | 23.084 | 411.5877
1217 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-1792-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole # MH-G2/6/1 to CB-G2/6/1 (D) at Road MCG0 (Last Layer) | 461.68 | 10.53 | 5% | 23.084 | 243.0745
1218 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-1793-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole # MH-G2/6/1 to CB-G2/6/1 B(S) at Road MCG0 (Last Layer) | 461.68 | 17.45 | 5% | 23.084 | 402.8158
1219 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-1794-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole # CB-G2/6/1 (D) to CB-G2/6/1 A (S) at Road MCG0 (Last Layer) | 461.68 | 28.80 | 5% | 23.084 | 664.8192
1220 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1795-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole # MH-G2/6/2 (D) to CB-G2/6/2 A(S) at Road MCG0 (Last Layer) | 461.68 | 24.10 | 5% | 23.084 | 556.3244
1221 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1796-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole # MH-G2/6/2 to CB-G2/6/2(D) at Road MCG0 (Last Layer) | 461.68 | 11.47 | 5% | 23.084 | 264.7735
1222 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1797-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole # MH-G2/6/2 to CB-G2/6/2 B(S) at Road MCG0 (Last Layer) | 461.68 | 16.47 | 5% | 23.084 | 380.1935
1223 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-1798-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between # CB-G2/6/3 (D) to CB-G2/6/3 A(S) at Road MCG0 (Last Layer) | 461.68 | 28.80 | 5% | 23.084 | 664.8192
1224 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-1799-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between # MH-G2/6/3 to CB-G2/6/3 D at Road MCG0 (Last Layer) | 461.68 | 12.67 | 5% | 23.084 | 292.4743
1225 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-1800-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between # MH-G2/6/3 to CB-G2/6/3 B(S) at Road MCG0 (Last Layer) | 461.68 | 15.75 | 5% | 23.084 | 363.573
1226 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1801-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between # CB-G2/6/4 (D) to CB-G2/6/4 A(S) at Road MCG0 (Last Layer) | 461.68 | 28.80 | 5% | 23.084 | 664.8192
1227 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1802-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between # MH-G2/6/7 to CB-G2/6/7(s) at Road MCG0 (Last Layer) | 461.68 | 27.43 | 5% | 23.084 | 633.1941
1228 | B5.33 31 00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Depth 1.51-2.50) | 2026-08-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1806-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-1-95 to MH-1-94 at Road MCC0 | 221.14 | 96.90 | 10% | 22.114 | 2142.8466
1229 | B5.33 31 00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Depth 0 -1.50) | 2026-08-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1807-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-1-98 to MH-1-97 at Road MCC0 | 212.41 | 78.87 | 10% | 21.241 | 1675.2777
1230 | B6.33 05 39.16 | STORM WATER NETWORK: - Catch Basin Double | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1808-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/16/3 (D) at Road MCE0 | 12444.99 | 1.00 | 5% | 622.2495 | 622.2495
1231 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1809-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/16/3 B (S) at Road MCE0 | 5124.07 | 1.00 | 5% | 256.2035 | 256.2035
1232 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1810-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/16/4 A (S) at Road MCE0 | 5124.07 | 1.00 | 5% | 256.2035 | 256.2035
1233 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300 mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1812-00 | Inspection Gravity and Leakage test pipeline from # CB-G2/6 (S) to FIMH-G2/6 at Road MCG0 | 461.68 | 22.78 | 10% | 46.168 | 1051.707
1234 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300 mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1813-00 | Inspection Gravity and Leakage test pipeline from # CB-G2/6/1 A (S) CB-G2/6/1 (D) at Road MCG0 | 461.68 | 28.80 | 10% | 46.168 | 1329.6384
1235 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400 mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1814-00 | Inspection Gravity and Leakage test pipeline from #MH-G2/6/1 to CB-G2/6/1 (D) at Road MCG0 | 875.83 | 10.53 | 10% | 87.583 | 922.249
1236 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300 mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1815-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # CB-G2/11/1 A (S) to CB-G2/11/1 (D) at Road MCF0 | 461.68 | 28.80 | 45% | 207.756 | 5983.3728
1237 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400 mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1816-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # CB-G2/11/1 (D) TO MH-G2/11/1 at Road MCF0 | 875.83 | 10.53 | 45% | 394.1235 | 4150.1205
1238 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300 mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1817-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # CB-G2/11/1 B (S) to MH-G2/11/1 at Road MCF0 | 461.68 | 17.45 | 45% | 207.756 | 3625.3422
1239 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300 mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1818-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # CB-G2/11/3 A (S) to CB-G2/11/3 (D) at Road MCF0 | 461.68 | 28.80 | 45% | 207.756 | 5983.3728
1240 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400 mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1819-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # CB-G2/11/3 (D) MH-G2/11/3 at Road MCF0 | 875.83 | 12.67 | 45% | 394.1235 | 4993.5447
1241 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300 mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1820-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # MH-G2/11/3 to CB-G2/11/3 B (S) at Road MCF0 | 461.68 | 15.75 | 45% | 207.756 | 3272.157
1242 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300 mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1821-00 | Inspection Gravity and Leakage test pipeline from #MH-G2/6/3 to CB-G2/6/3 B (S) at Road MCG0 | 461.68 | 15.75 | 10% | 46.168 | 727.146
1243 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0.0m - 1.5m) | 2026-08-09 | SUD1-02-011-TDC-TS9-1-IRR-FIR-1822-00 | Check Coordinates level and compaction F.D.T for Backfilling Road crossing ST: +460.28 ,ST: +156.39 & ST: +00.00 125mm O.D HDPE Pipes at Road MCG0 (Attached three Locations) (Last layer) | 82.44 | 98.39 | 5% | 4.122 | 405.5636
1244 | B2.33 71 19.02 | Road crossing ducts, 4 ways (4 x 150mm PVC) | 2026-08-09 | SUD1-02-011-TDC-TS9-1-LIT-FIR-1823-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (4X160mm) from Manhole 35 To Manhole 36 for Street Lighting Duct Bank in road MC20 | 75.65 | 9.10 | 25% | 18.9125 | 172.1038
1245 | B4.33 14 13.5 | TSE NETWORK: 225mm Diameter (Depth: 0.0m - 1.5m) | 2026-08-09 | SUD1-02-011-TDC-TS9-1-IRR-FIR-1824-00 | Check Coordinates level and compaction F.D.T for Backfilling Road crossing 225mm O.D HDPE Pipes at ST: +685.57 & ST: +538.51 at Road MCG0 (last layer) | 179.43 | 25.69 | 5% | 8.9715 | 230.4778
1246 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300 mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1825-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # CB-G2/11 (S) to FIMH-G2/11 at Road MCF0 | 377.3 | 23.25 | 45% | 169.785 | 3947.5012
1247 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300 mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1826-00 | Inspection Gravity and Leakage test pipeline from # MH-G2/6/1 to CB-G2/6/1 B (S) at Road MCG0 | 377.3 | 17.45 | 10% | 37.73 | 658.3885
1248 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300 mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1827-00 | Inspection Gravity and Leakage test pipeline from # CB-G2/6/2 A (S) to CB-G2/6/2 (D) at Road MCG0 | 377.3 | 24.10 | 10% | 37.73 | 909.293
1249 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400 mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1828-00 | Inspection Gravity and Leakage test pipeline from # CB-G2/6/2 (D) To MH-G2/6/2at Road MCG0 | 602.32 | 11.47 | 10% | 60.232 | 690.861
1250 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300 mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1829-00 | Inspection Gravity and Leakage test pipeline from # CB-G2/6/2 B (S) to MH-G2/6/2 at Road MCG0 | 377.3 | 16.47 | 10% | 37.73 | 621.4131
1251 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300 mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1830-00 | Inspection Gravity and Leakage test pipeline from # CB-G2/6/3 (D) to CB-G2/6/3 A (S) at Road MCG0 | 377.3 | 28.80 | 10% | 37.73 | 1086.624
1252 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400 mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1831-00 | Inspection Gravity and Leakage test pipeline from # MH-G2/6/3 to CB-G2/6/3 (D) at Road MCG0 | 602.32 | 12.67 | 10% | 60.232 | 763.1394
1253 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 0m to 1.5m) | 2026-08-13 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1832-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-11-4 to MH-12-11-5 at Road MCG0 | 212.41 | 98.71 | 5% | 10.6205 | 1048.3496
1254 | B3.33 14 13.1 | POTABLE WATER NETWORK: HDPE Pipes 160mm Diameter (Depth 0.0m to 1.50m) | 2026-08-09 | SUD1-02-011-TDC-TS9-1-PW-FIR-1833-00 | Check Coordinates level and compaction F.D.T for Backfilling Road crossing potable water HDPE pipelines at ST: +204.25 & ST:+450.99 (Diameter 160mm) at Road MCG0 (Last layer) | 392.82 | 54.66 | 5% | 19.641 | 1073.5771
1255 | B6.33 42 11.3 | STORM WATER NETWORK: GRP Pipes 400mm (Depth: 0- 1.5m) | 2026-08-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-1836-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/15/9 to STA-A1/15/10 at Road MCF0 | 300.67 | 59.15 | 5% | 15.0335 | 889.2315
1256 | B6.33 42 11.13 | STORM WATER NETWORK: GRP Pipes 700mm (Depth: 1.51-2.50) | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-1837-01 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/30/2 to STA-A1/30/1 at Road MCF0 | 300.67 | 63.82 | 5% | 15.0335 | 959.438
1257 | B6.33 42 11.12 | STORM WATER NETWORK: GRP Pipes 700mm (Depth: 0- 1.50) | 2026-08-24 | SUD1-02-011-TDC-TS9-1-STR-FIR-1838-01 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/30/3 to STA-A1/30/2 at Road MCF0 | 529.57 | 63.50 | 10% | 52.957 | 3362.7695
1258 | B6.33 42 11.9 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51m - 2.5m) | 2026-08-24 | SUD1-02-011-TDC-TS9-1-STR-FIR-1839-01 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/30/4 to STA-A1/30/3 at Road MCF0 | 448.1 | 63.65 | 5% | 22.405 | 1426.0783
1259 | B6.33 42 11.6 | STORM WATER NETWORK: GRP Pipes 500mm (Depth: 0- 1.50) | 2026-08-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-1840-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/30/5 to STA-A1/30/4 at Road MCF0 | 366.63 | 63.80 | 5% | 18.3315 | 1169.5497
1260 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300 mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1841-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # CB-G2/11/2 (D) to CB-G2/11/2 A(S) at Road MCF0 | 377.3 | 23.73 | 45% | 169.785 | 4028.9981
1261 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400 mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1842-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # MH-G2/11/2 to CB-G2/11/2 (D)at Road MCF0 | 602.32 | 11.47 | 45% | 271.044 | 3108.8747
1262 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300 mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1843-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # MH-G2/11/2 to CB-G2/11/2 B (S) at Road MCF0 | 377.3 | 16.47 | 45% | 169.785 | 2796.3589
1263 | B6.33 05 39.16 | STORM WATER NETWORK: Catch Basin (Double) | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1845-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/16/4 D at Road MCE0 | 12444.99 | 1.00 | 5% | 622.2495 | 622.2495
1264 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin (Single) | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1846-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/16/4 B(S) at Road MCE0 | 5124.07 | 1.00 | 5% | 256.2035 | 256.2035
1265 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin (Single) | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1847-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/16/5 A(S) at Road MCE0 | 5124.07 | 1.00 | 5% | 256.2035 | 256.2035
1266 | B6.33 05 39.16 | STORM WATER NETWORK: Catch Basin (Double) | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1848-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/16/5 D at Road MCE0 | 12444.99 | 1.00 | 5% | 622.2495 | 622.2495
1267 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin (Single) | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1849-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/16/5 B (S) at Road MCE0 | 5124.07 | 1.00 | 5% | 256.2035 | 256.2035
1268 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin (Single) | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1850-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/16/6 A (S) at Road MCE0 | 5124.07 | 1.00 | 5% | 256.2035 | 256.2035
1269 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin (Single) | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1851-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/16/6 B (S) at Road MCE0 | 5124.07 | 1.00 | 5% | 256.2035 | 256.2035
1270 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin (Single) | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1852-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-G2/16/7 B (S) at Road MCE0 | 5124.07 | 1.00 | 5% | 256.2035 | 256.2035
1271 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0m - 1.5m) | 2026-08-09 | SUD1-02-011-TDC-TS9-1-IRR-FIR-1853-00 | Check Excavation for Road crossing 125mm O.D HDPE Pipes at Road MCZ0 | 82.44 | 33.49 | 30% | 24.732 | 828.2747
1272 | B1.31 22 00.01 | Earth works & Site Grading (Road Excavation/cutting) | 2026-08-09 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1854-00 | Check Coordinates and bottom level Road Excavation/cutting of Shoulder (Left side) STA: 5+910 to STA: 6+040 at Road # MC20 (Last Layer) | 13.58 | 1398.67 | 5% | 0.679 | 949.6969
1273 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51-2.50 m ) | 2026-08-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-1855-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/15/9 at Road MCF0 | 12376.13 | 01 | 5% | 618.8065 | 618.8065
1274 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51-2.50 m ) | 2026-08-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-1856-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/15/10 at Road MCF0 | 12376.13 | 01 | 5% | 618.8065 | 618.8065
1275 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51-2.50 m ) | 2026-08-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-1857-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/30/5 at Road MCF0 | 12376.13 | 01 | 5% | 618.8065 | 618.8065
1276 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51-2.50 m ) | 2026-08-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-1858-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/30/4 at Road MCF0 | 12376.13 | 01 | 5% | 618.8065 | 618.8065
1277 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300 mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1859-00 | Inspection Gravity and Leakage test pipeline from # CB-G2/6/4 (D) to CB-G2/6/4 A (S) at Road MCG0 | 377.3 | 28.80 | 10% | 37.73 | 1086.624
1278 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400 mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1860-00 | Inspection Gravity and Leakage test pipeline from # MH-G2/6/4 to CB-G2/6/4 (D) at Road MCG0 | 884.56 | 13.63 | 10% | 88.456 | 1205.6553
1279 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300 mm for Catch Basin | 2026-08-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-1861-00 | Inspection Gravity and Leakage test pipeline from # MH-G2/6/4 to CB-G2/6/4 B (S) at Road MCG0 | 377.3 | 14.77 | 10% | 37.73 | 557.2721
1280 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-10 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1862-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at PLOT (1), STA: 0+610 to STA: 0+857.5 | 22.31 | 7740.89 | 100% | 22.31 | 172699.2559
1281 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300 mm for Catch Basin | 2026-08-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-1864-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # MH-G2/11/4 to CB-G2/11/4 B (S) at Road MCF0 | 377.3 | 14.78 | 45% | 169.785 | 2509.4223
1282 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400 mm for Catch Basin | 2026-08-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-1865-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # MH-G2/11/4 to CB-G2/11/4 (D) at Road MCF0 | 884.56 | 13.63 | 45% | 398.052 | 5425.4488
1283 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300 mm for Catch Basin | 2026-08-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-1866-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # CB-G2/11/4 (D) to CB-G2/11/4 A (S) at Road MCF0 | 377.3 | 28.80 | 45% | 169.785 | 4889.808
1284 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300 mm for Catch Basin | 2026-08-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-1868-00 | Inspection Gravity and Leakage test pipeline from # CB-G2/11 (S) to FIMH-G2/11 at Road MCF0 | 377.3 | 23.25 | 10% | 37.73 | 877.2225
1285 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300 mm for Catch Basin | 2026-08-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-1869-00 | Inspection Gravity and Leakage test pipeline from # CB-G2/11/1 A (S) to CB-G2/11/1 (D) at Road MCF0 | 377.3 | 28.80 | 10% | 37.73 | 1086.624
1286 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400 mm for Catch Basin | 2026-08-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-1870-00 | Inspection Gravity and Leakage test pipeline from # CB-G2/11/1 (D) TO MH-G2/11/1 at Road MCF0 | 884.56 | 10.53 | 10% | 88.456 | 931.4417
1287 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300 mm for Catch Basin | 2026-08-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-1871-00 | Inspection Gravity and Leakage test pipeline from # CB-G2/11/1 B (S) to MH-G2/11/1 at Road MCF0 | 377.3 | 17.45 | 10% | 37.73 | 658.3885
1288 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300 mm for Catch Basin | 2026-08-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-1872-00 | Inspection Gravity and Leakage test pipeline from # CB-G2/11/3 A (S) to CB-G2/11/3 (D) at Road MCF0 | 377.3 | 28.80 | 10% | 37.73 | 1086.624
1289 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400 mm for Catch Basin | 2026-08-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-1873-00 | Inspection Gravity and Leakage test pipeline from # CB-G2/11/3 (D) MH-G2/11/3 at Road MCF0 | 884.56 | 12.67 | 10% | 88.456 | 1120.7375
1290 | B6.33 05 39.5 | STORM WATER NETWORK: Manhole Diameter :- 1500mm (Depth: 1.51-2.50m) | 2026-08-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-1875-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/30/3 at Road MCF0 | 15295.58 | 01 | 5% | 764.779 | 764.779
1291 | B6.33 05 39.5 | STORM WATER NETWORK: Manhole Diameter :- 1500mm (Depth: 1.51-2.50m) | 2026-08-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-1876-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/30/2 at Road MCF0 | 15295.58 | 01 | 5% | 764.779 | 764.779
1292 | B6.33 05 39.6 | STORM WATER NETWORK: Manhole Diameter :- 1500mm (Depth: Greater 2.50m) | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-1877-01 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/30/1 at Road MCF0 | 19537.02 | 01 | 5% | 976.851 | 976.851
1293 | B1.31 22 00.01 | Earth works & Site Grading (Road Excavation/cutting) | 2026-08-10 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1878-00 | Check Coordinates and bottom level Road cutting and compaction test of bottom Sub-Grade Shoulder (Right side) at Road # MC10 STA: 3+040 to STA: 3+250 | 13.58 | 517.65 | 5% | 0.679 | 351.4844
1294 | B1.31 22 00.03 | Earth works & Site Grading | 2026-08-10 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1879-00 | Check Coordinates and bottom level Road Filling and compaction test of bottom Sub-Grade of shoulders (Right side) at Road # MC10, STA: 3+040 to STA: 3+250 | 22.31 | 562.38 | 5% | 1.1155 | 627.3349
1295 | B2.33 71 19.01 | Road crossing ducts, 2 ways (2 x 150mm PVC) | 2026-08-15 | SUD1-02-011-TDC-TS9-1-LIT-FIR-1882-01 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (2X160mm) from Manhole 37 To Manhole 38 for Street Lighting Duct Bank in road ART- MC10 | 308.43 | 10.08 | 25% | 77.1075 | 777.2436
1296 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-08-15 | SUD1-02-011-TDC-TS9-1-TEL-FIR-1883-01 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 032 To 033 in road ART-MC10 | 75.65 | 60.80 | 25% | 18.9125 | 1149.88
1297 | B4.33 14 13.5 | TSE NETWORK: 225mm Diameter (Depth: 0.0m - 1.5m) | 2026-08-10 | SUD1-02-011-TDC-TS9-1-IRR-FIR-1884-00 | Check Sand bedding and pipe installation of Road crossing Irrigation water HDPE Pipes (Diameter 225mm) at ST: +242.09& ST: +512.88 at Road MCE0 | 179.43 | 24.64 | 45% | 80.7435 | 1989.5198
1298 | B4.33 14 13.5 | TSE NETWORK: 225mm Diameter (Depth: 0.0m - 1.5m) | 2026-08-10 | SUD1-02-011-TDC-TS9-1-IRR-FIR-1885-00 | Check Sand bedding and pipe installation of Road crossing Irrigation water HDPE Pipes (Diameter 225mm) at ST: +461.88 & ST: +536.87 at Road MCF0 | 179.43 | 27.23 | 45% | 80.7435 | 2198.6455
1299 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0.0m - 1.5m) | 2026-08-10 | SUD1-02-011-TDC-TS9-1-IRR-FIR-1891-00 | Check Sand bedding and pipe installation of Road crossing Irrigation water HDPE Pipes (Diameter 125mm) ST: +360.81& ST: +081.13,ST :+114.70 at Road MCE0 | 82.44 | 67.12 | 45% | 37.098 | 2490.0178
1300 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300 mm for Catch Basin | 2026-08-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-1892-00 | Inspection Gravity and Leakage test pipeline from # MH-G2/11/3 to CB-G2/11/3 B (S) at Road MCF0 | 377.3 | 15.75 | 10% | 37.73 | 594.2475
1301 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0.0m - 1.5m) | 2026-08-10 | SUD1-02-011-TDC-TS9-1-IRR-FIR-1893-00 | Check Sand bedding and pipe installation of Road crossing Irrigation water HDPE Pipes (Diameter 125mm) ST: +389.75& ST: +143.63 at Road MCF0 | 82.44 | 67.09 | 45% | 37.098 | 2488.9048
1302 | B4.33 14 13.4 | TSE NETWORK: 125mm Diameter (Depth: >1.5m) | 2026-08-10 | SUD1-02-011-TDC-TS9-1-IRR-FIR-1894-00 | Check Sand bedding and pipe installation of Road crossing Irrigation water HDPE Pipes (Diameter 125mm) ST: +0.00 & ST:+432.1 at Road MCF0 | 86.32 | 30.57 | 45% | 38.844 | 1187.4611
1303 | B3.33 14 13.1 | POTABLE WATER NETWORK: HDPE Pipes 160mm Diameter (Depth 0.0m to 1.50m) | 2026-08-10 | SUD1-02-011-TDC-TS9-1-PW-FIR-1895-00 | Check Sand bedding and pipe installation of Road crossing potable water HDPE Pipes (Diameter 160mm) at STA: ST: +309.99&ST: +056.73, Road MCE0 | 392.82 | 68.06 | 45% | 176.769 | 12030.8981
1304 | B3.33 14 13.1 | POTABLE WATER NETWORK: HDPE Pipes 160mm Diameter (Depth 0.0m to 1.50m) | 2026-08-10 | SUD1-02-011-TDC-TS9-1-PW-FIR-1896-00 | Check Sand bedding and pipe installation of Road crossing potable water HDPE Pipes (Diameter 160mm) at ST: +449.02 ST: +195.75, Road MCF0 | 392.82 | 67.98 | 45% | 176.769 | 12016.7566
1305 | B1.31 22 00.01 | Earth works & Site Grading (Road Excavation/cutting) | 2026-08-10 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1897-00 | Check Coordinates and bottom level of Road Excavation/cutting upto bottom of Sub-Grade shoulders (Right side) STA: 5+770 to STA: 5+900 at Road # MC20 | 13.58 | 141.15 | 5% | 0.679 | 95.8409
1306 | B1.31 22 00.03 | Earth works & Site Grading | 2026-08-10 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1898-00 | Check Coordinates and bottom level Road Filling and compaction test of bottom Sub-Grade of shoulder (Right side) Road # MC20, STA: 5+770 to STA: 5+900 | 22.31 | 57.77 | 5% | 1.1155 | 64.4424
1307 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-1899-00 | Check Installation of catch basin CB-G2/16 (S) include the connecting pipe opening at Road MCE0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1308 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-1900-00 | Check Installation of catch basin CB-G2/16/1 A (S) include the connecting pipe opening at Road MCE0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1309 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-1901-00 | Check Installation of catch basin CB-G2/16/1 B (S) include the connecting pipe opening at Road MCE0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1310 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-1902-00 | Check Installation of catch basin CB-G2/16/2 B (S) include the connecting pipe opening at Road MCE0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1311 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-1903-00 | Check Installation of catch basin CB-G2/16/3 A (S) include the connecting pipe opening at Road MCE0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1312 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-1904-00 | Check Installation of catch basin CB-G2/16/3 B (S) include the connecting pipe opening at Road MCE0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1313 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-1907-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # FMH-A2/9/20-399 to CB-A2/9/20-399 (S) at Road MCF0 | 377.3 | 2.90 | 45% | 169.785 | 492.3765
1314 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-1908-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # MH-G2/11/5 to CB-G2/11/5 A (S) at Road MCF0 | 377.3 | 15.28 | 45% | 169.785 | 2594.3148
1315 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-1909-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from MH-G2/11/5 to CB-G2/11/5 B (S) at Road MCF0 | 377.3 | 13.97 | 45% | 169.785 | 2371.8965
1316 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-1910-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from FMH-A2/9/20-397 to CB-A2/9/20-397 (S) at Road MCF0 | 377.3 | 3.23 | 45% | 169.785 | 548.4055
1317 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-1911-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from MH-G2/11/6 to CB-G2/11/6 A (S) at Road MCF0 | 377.3 | 12.03 | 45% | 169.785 | 2042.5135
1318 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-1912-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from MH-G2/11/6 to CB-G2/11/6 C (S) at Road MCF0 | 377.3 | 26.29 | 45% | 169.785 | 4463.6476
1319 | B2.33 71 19.01 | Road crossing ducts, 2 ways (2 x 150mm PVC) | 2026-08-11 | SUD1-02-011-TDC-TS9-1-CCTV-FIR-1920-00 | Check levels, laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (2X160mm) for CCTV Duct Bank in road MCG0 as per Attached Highlighted Drawing | 308.43 | 13.05 | 25% | 77.1075 | 1006.2529
1320 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-1923-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between #FIMH-G2/6 to CB-G2/6(s) at Road MCG0 (Last Layer) | 377.3 | 22.78 | 5% | 18.865 | 429.7447
1321 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-11 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1924-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Plot (5) STA: 0+270 to STA: 0+350 | 22.31 | 1356.88 | 100% | 22.31 | 30271.9928
1322 | B5.33 05 13.03 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 1.51-2.50m) | 2026-08-11 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1925-00 | Check Installation of Manhole Base (Rings not required) MH-12-11-1-2 at Road MCG0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
1323 | B5.33 05 13.09 | SEWER NETWORK: Manhole Diameter: -1200mm (Depth: 4.51- 5.5M) | 2026-08-11 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1926-00 | Check Installation of Manhole Base MH-12-4 at Road MCH0 | 22875.47 | 01 | 30% | 6862.641 | 6862.641
1324 | B5.33 05 13.09 | SEWER NETWORK: Manhole Diameter: -1200mm (Depth: 4.51- 5.5M) | 2026-08-11 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1927-00 | Check Installation of Manhole Base MH-12-5 at Road MCH0 | 22875.47 | 01 | 30% | 6862.641 | 6862.641
1325 | B5.33 05 13.11 | SEWER NETWORK: Manhole Diameter: -1200mm (Depth: 4.51- 5.5/BD M) With Backdrop | 2026-08-11 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1928-00 | Check Installation of Manhole Base MH-12-2 at Road MCH0 | 25162.53 | 01 | 30% | 7548.759 | 7548.759
1326 | B5.33 05 13.01 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 0-1.50m) | 2026-08-11 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1929-00 | Check Installation of Manhole Base (Rings not required) MH-12-7-3 at Road MCH0 | 8820.42 | 01 | 30% | 2646.126 | 2646.126
1327 | B5.33 05 13.03 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 1.51-2.50m) | 2026-08-11 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1930-00 | Check Installation of Manhole Base (Rings not required) MH-12-7-2 at Road MCH0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
1328 | B6.33 42 11.22 | STORM WATER NETWORK: GRP Pipes 1000mm Diameter (Depth: 1.51 m - 2.50m) | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-1933-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole # MH G2/16/1 to MH-G2/16/2 at Road MCE0 (Bottom subgrade) | 884.56 | 87.00 | 5% | 44.228 | 3847.836
1329 | B6.33 42 11.22 | STORM WATER NETWORK: GRP Pipes 1000mm Diameter (Depth: 1.51 m - 2.50m) | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-1934-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole # MH-G2/16/3 to MH-G2/16/4 at Road MCE0 (Bottom subgrade) | 884.56 | 87.00 | 5% | 44.228 | 3847.836
1330 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-1945-00 | Inspection Gravity and Leakage test pipeline from # FMH-CB-A2/9/20-399 (S) FMH-A2/9/20-399 at Road MCF0 | 377.3 | 2.90 | 10% | 37.73 | 109.417
1331 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-1946-00 | Inspection Gravity and Leakage test pipeline from # CB-G2/11/4 A (S) to CB-G2/11/4 (D) at Road MCF0 | 377.3 | 28.80 | 10% | 37.73 | 1086.624
1332 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400 mm for Catch Basin | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-1947-00 | Inspection Gravity and Leakage test pipeline from # CB-G2/11/4 (D) to MH-G2/11/4 at Road MCF0 | 884.56 | 13.63 | 10% | 88.456 | 1205.6553
1333 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-1948-00 | Inspection Gravity and Leakage test pipeline from # CB-G2/11/4 B (S) to MH-G2/11/4 at Road MCF0 | 377.3 | 14.78 | 10% | 37.73 | 557.6494
1334 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-1949-00 | Inspection Gravity and Leakage test pipeline from # CB-G2/11 /2 A(S) to CB-G2-11/2 (D) at Road MCF0 t | 377.3 | 23.73 | 10% | 37.73 | 895.3329
1335 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400 mm for Catch Basin | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-1950-00 | Inspection Gravity and Leakage test pipeline from # CB-G2-11/2 (D) to MH-G2/11/2 at Road MCF0 | 884.56 | 11.47 | 10% | 88.456 | 1014.5903
1336 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-1951-00 | Inspection Gravity and Leakage test pipeline from # CB-G2/11/2 B (S) MH-G2/11/2 at Road MCF0 | 377.3 | 16.47 | 10% | 37.73 | 621.4131
1337 | B6.34 42 16.4 | STORM WATER NETWORK: (BOX CULVERT) | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-1952-00 | Check Internal Finishing,External Finishing & Isolation of Box culvert at # Road MCE0 | 792.42 | 150.94 | 100% | 792.42 | 119607.8748
1338 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-11 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1953-00 | Check Coordinates level and Compaction F.D.T for Embankment 13th layer at PLOT (5), STA: 0+360 to STA: 0+430 | 22.31 | 2211.57 | 100% | 22.31 | 49340.1267
1339 | B2.33 71 19.01 | Road crossing ducts, 2 ways (2 x 150mm PVC) | 2026-08-11 | SUD1-02-011-TDC-TS9-1-LIT-FIR-1955-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (2X160mm) from Manhole 29 To Manhole 30 for Street Lighting Duct Bank in road ART- MC10 | 308.43 | 9.10 | 25% | 77.1075 | 701.6782
1340 | B2.33 71 19.01 | Road crossing ducts, 2 ways (2 x 150mm PVC) | 2026-08-11 | SUD1-02-011-TDC-TS9-1-LIT-FIR-1956-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (2X160mm) from Manhole 31 To Manhole 32 for Street Lighting Duct Bank in road ART- MC10 | 308.43 | 9.31 | 25% | 77.1075 | 717.8708
1341 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-1963-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Existing Manhole # FIMH-G2/5 to CB03-22 (S) at Road MCG0 | 377.3 | 26.29 | 5% | 18.865 | 495.9609
1342 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-1964-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Existing Manhole # FIMH-G2/8 to CB03-21 (S) at Road MCG0 | 377.3 | 27.69 | 5% | 18.865 | 522.3719
1343 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin (Single) | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-1965-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB03-21(S) at Road MCG0 | 5124.07 | 1.00 | 10% | 512.407 | 512.407
1344 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin (Single) | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-1966-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB03-22(S) at Road MCG0 | 5124.07 | 1.00 | 10% | 512.407 | 512.407
1345 | B1.31 22 00.01 | Earth works & Site Grading (Road Excavation/cutting) | 2026-08-11 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1967-00 | Check Coordinates and bottom level Road cutting and compaction test of bottom Sub-Grade Shoulder (Left & Right side) at Road # MC10 STA: 3+250 to STA: 3+350 | 13.58 | 2487.96 | 10% | 1.358 | 3378.6497
1346 | B1.31 22 00.03 | Earth works & Site Grading | 2026-08-11 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1968-00 | Check Coordinates and bottom level Road Filling and compaction test of bottom Sub-Grade of shoulders (Right & Left side) at Road # MC10, STA: 3+250 to STA: 3+350 | 22.31 | 61.67 | 5% | 1.1155 | 68.7929
1347 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-11 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1969-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at PLOT (1), STA: 0+030 to STA: 0+200 | 22.31 | 3513.23 | 100% | 22.31 | 78380.1613
1348 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0.00 - 1.5m) | 2026-08-11 | SUD1-02-011-TDC-TS9-1-IRR-FIR-1971-00 | Check Sand bedding and pipe installation of Road crossing Irrigation water HDPE Pipes (Diameter 125mm) ST: +0.00 & ST +022.57at Road MCD0 | 82.44 | 22.57 | 45% | 37.098 | 837.3019
1349 | B5.33 31 00.02 | SEWER NETWORK: GRP Pipes 200mm (Manhole Depth: 1.51-2.50) | 2026-08-11 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1972-00 | Check sand bedding and GRP pipe installation for Sewerage line from manhole # MH-1-93-1 to MH-1-93 at Road MCC0 . | 221.14 | 97.01 | 45% | 99.513 | 9653.7561
1350 | B5.33 31 00.02 | SEWER NETWORK: GRP Pipes 200mm (Manhole Depth: 1.51-2.50) | 2026-08-11 | SUD1-02-011-TDC-TS9-1-SEW-FIR-1973-00 | Check sand bedding and GRP pipe installation for Sewerage line from manhole # MH-1-93-3 to MH-1-93-2 at Road MCC0 . | 221.14 | 98.86 | 45% | 99.513 | 9837.8552
1351 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin (Single) | 2026-08-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-1974-00 | Check Installation of catch basin CB-G2/16/4 A (S) include the connecting pipe opening at Road MCE0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1352 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin (Single) | 2026-08-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-1975-00 | Check Installation of catch basin CB-G2/16/4 B (S) include the connecting pipe opening at Road MCE0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1353 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin (Single) | 2026-08-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-1976-00 | Check Installation of catch basin CB-G2/16/5 A (S) include the connecting pipe opening at Road MCE0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1354 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin (Single) | 2026-08-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-1977-00 | Check Installation of catch basin CB-G2/16/5 B (S) include the connecting pipe opening at Road MCE0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1355 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin (Single) | 2026-08-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-1978-00 | Check Installation of catch basin CB-G2/16/6 A (S) include the connecting pipe opening at Road MCE0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1356 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin (Single) | 2026-08-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-1979-00 | Check Installation of catch basin CB-G2/16/6 B (S) include the connecting pipe opening at Road MCE0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1357 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin (Single) | 2026-08-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-1980-00 | Check Installation of catch basin CB-G2/16/7 B (S) include the connecting pipe opening at Road MCE0 | 5124.07 | 01 | 35% | 1793.4245 | 1793.4245
1358 | B1.31 22 00.03 | Earth works & Site Grading | 2026-08-16 | SUD1-02-011-TDC-TS9-1-ROD-FIR-1989-01 | Check Coordinates level and Compaction F.D.T for Shoulder (Right side) Embankment 2nd layer at Road # MC20, STA: 5+730 to STA: 5+770 | 22.31 | 225.79 | 100% | 22.31 | 5037.3749
1359 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0.00 - 1.5m) | 2026-08-12 | SUD1-02-011-TDC-TS9-1-IRR-FIR-1990-00 | Check Sand bedding and pipe installation of Road crossing Irrigation water HDPE Pipes (Diameter 125mm) ST: +566.47 at Road MCZ0 | 82.44 | 33.49 | 45% | 37.098 | 1242.412
1360 | B6.33 42 11.13 | STORM WATER NETWORK: GRP Pipes 700mm Diameter (Depth: 1.51 m - 2.50m) | 2026-08-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-1991-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole # MH G2/16/6 to MH-G2/16/5 at Road MCE0 (Bottom subgrade) | 544.12 | 69.12 | 5% | 27.206 | 1880.4787
1361 | B6.33 42 11.10 | STORM WATER NETWORK: GRP Pipes 600mm Diameter (Depth: 1.51 to 2.50m) | 2026-08-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-1992-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole # MH G2/16/6 to MH-G2/16/7 at Road MCE0 (Bottom subgrade) | 461.68 | 73.07 | 10% | 46.168 | 3373.4958
1362 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-1993-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/16/1 to CB-G2/16/1 B (S) at Road MCE0 | 377.3 | 22.38 | 5% | 18.865 | 422.1987
1363 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400mm | 2026-08-24 | SUD1-02-011-TDC-TS9-1-STR-FIR-1994-01 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/16/1 to CB-G2/16/1 (D) at Road MCE0 | 602.32 | 5.86 | 5% | 30.116 | 176.4798
1364 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-1995-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-G2/16/1 (D) to CB-G2-16/1 A (S) at Road MCE0 | 377.3 | 28.80 | 5% | 18.865 | 543.312
1365 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-24 | SUD1-02-011-TDC-TS9-1-STR-FIR-1996-01 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/16/2 to CB-G2/16/2 B (S) at Road MCE0 | 377.3 | 23.36 | 5% | 18.865 | 440.6864
1366 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400mm | 2026-08-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-1997-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/16/2 to CB-G2/16/2 (D) at Road MCE0 | 602.32 | 5.04 | 5% | 30.116 | 151.7846
1367 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-1998-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-G2/16/2 (D) to CB-G2/16/2 A (S) at Road MCE0 | 377.3 | 24.14 | 5% | 18.865 | 455.4011
1368 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-1999-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/16/3 to CB-G2/16/3 B (S) at Road MCE0 | 377.3 | 24.34 | 5% | 18.865 | 459.1741
1369 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400mm | 2026-08-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-2000-01 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/16/3 to CB-G2/16/3 (D) at Road MCE0 | 602.32 | 4.25 | 5% | 30.116 | 127.993
1370 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-2001-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-G2/16/3 (D) to CB-G2/16/3 A (S) at Road MCE0 | 377.3 | 28.85 | 5% | 18.865 | 544.2553
1371 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-2002-01 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/16/4 to CB-G2/16/4 B (S) at Road MCE0 | 377.3 | 25.34 | 5% | 18.865 | 478.0391
1372 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400mm | 2026-08-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-2003-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/16/4 to CB-G2/16/4 (D) at Road MCE0 | 602.32 | 3.63 | 5% | 30.116 | 109.3211
1373 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-2004-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/16/5 to CB-G2/16/5 B (S) at Road MCE0 | 377.3 | 26.49 | 5% | 18.865 | 499.7339
1374 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400mm | 2026-08-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-2005-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/16/5 to CB-G2/16/5 (D) at Road MCE0 | 602.32 | 3.56 | 5% | 30.116 | 107.213
1375 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-2006-01 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-G2/16/5 (D) to CB-G2/16/5 A (S) at Road MCE0 | 377.3 | 28.80 | 5% | 18.865 | 543.312
1376 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-2007-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/16/6 to CB-G2/16/6 B (S) at Road MCE0 | 377.3 | 24.49 | 5% | 18.865 | 462.0038
1377 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-2008-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/16/6 to CB-G2/16/6 A (S) at Road MCE0 | 377.3 | 12.71 | 5% | 18.865 | 239.7742
1378 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-2009-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/16/7 to CB-G2/16/7 B (S) at Road MCE0 | 377.3 | 41.88 | 5% | 18.865 | 790.0662
1379 | B5.33 05 13.08 | SEWER NETWORK: Manhole Diameter: -1200mm (Depth: 3.51- 4.5/BD M) With Backdrop | 2026-08-13 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2010-00 | Check Installation of Manhole Base MH-12-7 at Road MCH0 | 21251.83 | 01 | 30% | 6375.549 | 6375.549
1380 | B5.33 05 13.06 | SEWER NETWORK: Manhole Diameter: -1200mm (Depth: 2.51- 3.50/BD M) With Backdrop | 2026-08-13 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2011-00 | Check Installation of Manhole Base MH-12-13 at Road MCB0. | 19018.11 | 01 | 30% | 5705.433 | 5705.433
1381 | B5.33 05 13.09 | SEWER NETWORK: Manhole Diameter: -1200mm (Depth: 4.51-5.5 M) | 2026-08-13 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2012-00 | Check Installation of Manhole Base MH-12-6 at Road MCH0 | 22875.47 | 01 | 30% | 6862.641 | 6862.641
1382 | B5 33.05.13.01 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 0m- 1.50m) | 2026-08-13 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2013-00 | Check Installation of Manhole Base (Rings not required) MH-1-79-1 at Road MCA0 | 8820.42 | 01 | 0% | 0 | 0
1383 | B5 33.05.13.05 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm | 2026-08-13 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2014-00 | Check Installation of Manhole Base MH-1-73 at Road MCA0 | 15848.43 | 01 | 0% | 0 | 0
1384 | B5.33 05 13.03 | SEWER NETWORK: Manhole Diameter: -1200mm (Depth: 1.51- 2.5M) | 2026-08-13 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2015-00 | Check Installation of Manhole Base (Rings not required) MH-12-2-1 at Road MCH0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
1385 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin (Single) | 2026-08-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-2016-00 | Check Installation of catch basin CB-G2/16/2 A (S) include the connecting pipe opening at Road MCE0 | 5124.07 | 01 | 30% | 1537.221 | 1537.221
1386 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 0m to 1.5m) | 2026-08-13 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2017-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-11-1-2 to MH-12-11-1-3 at Road MCG0 | 212.41 | 98.74 | 10% | 21.241 | 2097.3363
1387 | B5 33.05.13.01 | SEWERAGE NETWORK: Manhole (Depth 0 to 1.5m) Internal Diameter (1200mm) | 2026-08-13 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2018-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-12-11-1-3 at Road MCG0 | 8820.42 | 1 | 10% | 882.042 | 882.042
1388 | B5 33.05.13.01 | SEWERAGE NETWORK: Manhole (Depth 0 to 1.5m) Internal Diameter (1200mm) | 2026-08-13 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2019-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage Manhole pit MH-12-11-5 at Road MCG0 | 8820.42 | 1 | 10% | 882.042 | 882.042
1389 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2020-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-G2/16/4 (D) to CB-G2/16/4 A (S) at Road MCE0 | 377.3 | 28.80 | 5% | 18.865 | 543.312
1390 | B6.33 42 11.19 | STORM WATER NETWORK: GRP Pipes 900mm Diameter (Depth: 1.51m - 2.50m) | 2026-08-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2021-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from Manhole MH-G2/16/4 to MH-G2/16/5 at Road MCE0 | 743.93 | 87.25 | 45% | 334.7685 | 29208.5516
1391 | B2.33 71 19.01 | Road crossing ducts, 2 ways (2 x 150mm PVC) | 2026-08-13 | SUD1-02-011-TDC-TS9-1-CCTV-FIR-2022-00 | Check levels, laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (2X160mm) for CCTV Duct Bank 2 Crossing in road MCF0 as per Attached Highlighted Drawing | 308.43 | 25.64 | 25% | 77.1075 | 1977.0363
1392 | B6.33 05 39.16 | STORM WATER NETWORK: - Catch Basin Double | 2026-08-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2023-00 | Check Installation of catch basin CB-G2/16/1 (D) include the connecting pipe opening at Road MCE0 | 12444.99 | 01 | 30% | 3733.497 | 3733.497
1393 | B6.33 05 39.16 | STORM WATER NETWORK: - Catch Basin Double | 2026-08-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2024-00 | Check Installation of catch basin CB-G2/16/2 (D) include the connecting pipe opening at Road MCE0 | 12444.99 | 01 | 30% | 3733.497 | 3733.497
1394 | B6.33 05 39.16 | STORM WATER NETWORK: - Catch Basin Double | 2026-08-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2025-00 | Check Installation of catch basin CB-G2/16/3 (D) include the connecting pipe opening at Road MCE0 | 12444.99 | 01 | 30% | 3733.497 | 3733.497
1395 | B6.33 05 39.16 | STORM WATER NETWORK: - Catch Basin Double | 2026-08-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2026-00 | Check Installation of catch basin CB-G2/16/4 (D) include the connecting pipe opening at Road MCE0 | 12444.99 | 01 | 30% | 3733.497 | 3733.497
1396 | B6.33 05 39.16 | STORM WATER NETWORK: - Catch Basin Double | 2026-08-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2027-00 | Check Installation of catch basin CB-G2/16/5 (D) include the connecting pipe opening at Road MCE0 | 12444.99 | 01 | 30% | 3733.497 | 3733.497
1397 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin (Single) | 2026-08-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2028-00 | Check Installation of catch basin CB03-21 (S) include the connecting pipe opening at Road MCG0 | 5124.07 | 01 | 30% | 1537.221 | 1537.221
1398 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin (Single) | 2026-08-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2029-00 | Check Installation of catch basin CB03-22 (S) include the connecting pipe opening at Road MCG0 | 5124.07 | 01 | 30% | 1537.221 | 1537.221
1399 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-13 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2031-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer at Plot (5) STA: 0+350 to STA: 0+467 | 22.31 | 620.88 | 100% | 22.31 | 13851.8328
1400 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin (Single) | 2026-08-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2034-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB01-19 at Road MCE0 | 5124.07 | 1.00 | 10% | 512.407 | 512.407
1401 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-2036-00 | Inspection Gravity and Leakage test pipeline from # CB-MH-G2/11/5 to CB-G2/11/5 A (S) at Road MCF0 | 377.3 | 15.28 | 10% | 37.73 | 576.5144
1402 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-2037-00 | Inspection Gravity and Leakage test pipeline from # MH-G2/11/5 to CB-G2/11/5 B (S) at Road MCF0 | 377.3 | 13.97 | 10% | 37.73 | 527.0881
1403 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-2038-00 | Inspection Gravity and Leakage test pipeline from # FMH-A2/9/20-397 to CB-A2/9/20-397 (S) at Road MCF0 | 377.3 | 3.23 | 10% | 37.73 | 121.8679
1404 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-2039-00 | Inspection Gravity and Leakage test pipeline from #MH-G2/11/6 to CB-G2/11/6 A (S)at Road MCF0 | 377.3 | 12.03 | 10% | 37.73 | 453.8919
1405 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-11 | SUD1-02-011-TDC-TS9-1-STR-FIR-2040-00 | Inspection Gravity and Leakage test pipeline from #MH-G2/11/6 to CB-G2/11/6 C (S) at Road MCF0 | 377.3 | 26.29 | 10% | 37.73 | 991.9217
1406 | B6.33 42 11.19 | STORM WATER NETWORK: GRP Pipes 900mm Diameter (Depth: 1.51 to 2.50m) | 2026-08-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-2041-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/16/4 to MH-G2/16/5 at Road MCE0 | 743.93 | 87.25 | 10% | 74.393 | 6490.7892
1407 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-08-04 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2042-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH 49-5 to MH 49-6 at Road MCD0 | 221.14 | 33.69 | 10% | 22.114 | 745.0207
1408 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0m to 1.5m) | 2026-08-23 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2044-01 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-19-1 to MH-12-19-1-1 at Road MCE0 | 212.41 | 78.87 | 45% | 95.5845 | 7538.7495
1409 | B5 33.31.00.03 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 2.51 to 3.5m) | 2026-08-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2045-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-1-93 to MH-1-92 at Road MCC0 | 329.77 | 41.87 | 45% | 148.3965 | 6213.3615
1410 | B5.33 31 00.02 | SEWER NETWORK: GRP Pipes 200mm (Manhole Depth: 1.51-2.50) | 2026-08-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2047-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-1-93-1 to MH-1-93 at Road MCC0 | 221.14 | 97.01 | 10% | 22.114 | 2145.2791
1411 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0m to 1.5m) | 2026-08-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2048-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-1-93-1 to MH-1-93-2 at Road MCC0 | 212.41 | 98.74 | 10% | 21.241 | 2097.3363
1412 | B5.33 31 00.02 | SEWER NETWORK: GRP Pipes 200mm (Manhole Depth: 1.51-2.50) | 2026-08-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2049-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-1-93-3 to MH-1-93-2 at Road MCC0 | 221.14 | 98.86 | 10% | 22.114 | 2186.19
1413 | B5 33.31.00.03 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 2.51 to 3.5m) | 2026-08-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2050-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-10 to MH-12-9 at Road MCB0 | 329.77 | 68.29 | 5% | 16.4885 | 1125.9997
1414 | B5 33.31.00.03 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 2.51 to 3.5m) | 2026-08-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2051-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-10 TO MH-12-11 at Road MCB0 | 329.77 | 68.95 | 5% | 16.4885 | 1136.8821
1415 | B5.33 31 00.02 | SEWER NETWORK: GRP Pipes 200mm (Manhole Depth: 1.51-2.50) | 2026-08-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2052-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-11 TO MH-12-12 at Road MCB0 | 221.14 | 98.44 | 5% | 11.057 | 1088.4511
1416 | B5.33 31 00.02 | SEWER NETWORK: GRP Pipes 200mm (Manhole Depth: 1.51-2.50) | 2026-08-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2053-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-12 TO MH-12-13 at Road MCB0 | 221.14 | 99.16 | 5% | 11.057 | 1096.4121
1417 | B5 33.05.13.05 | SEWERAGE NETWORK: Manhole (Depth 2.51m to 3.5m) Internal Diameter (1200mm) | 2026-08-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2054-01 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 12-9 at Road MCB0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
1418 | B5 33.05.13.05 | SEWERAGE NETWORK: Manhole (Depth 2.51m to 3.5m) Internal Diameter (1200mm) | 2026-08-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2055-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 12-10 at Road MCB0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
1419 | B5 33.05.13.06 | SEWERAGE NETWORK: Manhole (Depth 2.51m to 3.5m) Internal Diameter (1200mm) With Backdrop | 2026-08-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2056-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 12-11 at Road MCB0 | 19018.11 | 01 | 5% | 950.9055 | 950.9055
1420 | B5 33.05.13.05 | SEWERAGE NETWORK: Manhole (Depth 2.51m to 3.5m) Internal Diameter (1200mm) | 2026-08-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2057-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit MH- 12-12 at Road MCB0 | 15848.43 | 01 | 5% | 792.4215 | 792.4215
1421 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-15 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2058-00 | Check Coordinates and bottom level Road Filling and compaction test (bottom Sub-Grade) of Plot 5 STA: 0+270 to STA: 0+350 | 22.31 | 713.64 | 10% | 2.231 | 1592.1308
1422 | B6.33 42 11.13 | STORM WATER NETWORK: GRP Pipes 700mm (Depth: 1.51m - 2.5m) | 2026-08-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-2064-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/26/1 to STA-A1/26/2 at Road MCG0 | 544.12 | 63.59 | 5% | 27.206 | 1730.0295
1423 | B6.33 42 11.12 | STORM WATER NETWORK: GRP Pipes 700mm (Depth: 0m - 1.5m) | 2026-08-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-2065-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/26/2 to STA-A1/26/3 at Road MCG0 | 529.57 | 63.50 | 5% | 26.4785 | 1681.3848
1424 | B6.33 42 11.9 | STORM WATER NETWORK: GRP Pipes 600mm (Depth: 0m - 1.5m) | 2026-08-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-2066-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/26/3 to STA-A1/26/4 at Road MCG0 | 448.1 | 63.65 | 5% | 22.405 | 1426.0783
1425 | B6.33 42 11.9 | STORM WATER NETWORK: GRP Pipes 600mm (Depth: 0m - 1.5m) | 2026-08-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-2067-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/26/4 to STA-A1/26/5 at Road MCG0 | 448.1 | 63.80 | 5% | 22.405 | 1429.439
1426 | B6.33 42 11.3 | STORM WATER NETWORK: GRP Pipes 400mm (Depth: 0m - 1.5m) | 2026-08-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-2068-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/26/5 to STA-A1/26/6 at Road MCG0 | 300.67 | 64.54 | 5% | 15.0335 | 970.2621
1427 | B6.33 05 39.6 | STORM WATER NETWORK: Manhole Diameter :-1500mm (Depth: >2.50m) | 2026-08-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-2069-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/26/1 at Road MCG0 | 19537.02 | 01 | 5% | 976.851 | 976.851
1428 | B6.33 05 39.5 | STORM WATER NETWORK: Manhole Diameter :-1500mm (Depth: 1.51m to 2.5m) | 2026-08-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-2070-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/26/2 at Road MCG0 | 15295.58 | 01 | 5% | 764.779 | 764.779
1429 | B6.33 05 39.5 | STORM WATER NETWORK: Manhole Diameter :-1500mm (Depth: 1.51m to 2.5m) | 2026-08-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-2071-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/26/3 at Road MCG0 | 15295.58 | 01 | 5% | 764.779 | 764.779
1430 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51m to 2.5m) | 2026-08-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-2072-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/26/4 at Road MCG0 | 12376.13 | 01 | 5% | 618.8065 | 618.8065
1431 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51m to 2.5m) | 2026-08-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-2073-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/26/5 at Road MCG0 | 12376.13 | 01 | 5% | 618.8065 | 618.8065
1432 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51m to 2.5m) | 2026-08-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-2074-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/26/6 at Road MCG0 | 12376.13 | 01 | 5% | 618.8065 | 618.8065
1433 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-08-15 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2075-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 030 To 031 in Road ART-MC10 | 617.84 | 60.80 | 25% | 154.46 | 9391.168
1434 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-16 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2077-00 | Check Coordinates level and Compaction F.D.T for Embankment 14th layer at PLOT (5), STA: 0+360 to STA: 0+420 | 28.13 | 1872.94 | 100% | 28.13 | 52685.8022
1435 | B6.34 42 16.2 | STORM WATER NETWORK: BOX CULVERT | 2026-08-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-2076-00 | Check Coordinates level and compaction F.D.T for Backfilling bottom subgrade (Embankment material) from Existing manhole # FIMH-G2/16 to MH-G2/16/1 at Road MCE0 (Beside Box Culvert) | 17.46 | 225.40 | 10% | 1.746 | 393.5484
1436 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-16 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2078-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at Plot (3) STA: 0+0310 to STA: 0+467 | 28.13 | 4986.46 | 100% | 28.13 | 140269.1198
1437 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 0.0 m to 1.5m) | 2026-08-19 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2089-01 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-19-2 to MH-12-19-3 at Road MCE0 | 212.41 | 78.87 | 45% | 95.5845 | 7538.7495
1438 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 0.0 m to 1.5m) | 2026-08-16 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2090-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-1-88-2-1 to MH-1-88-2 at Road MCD0 | 212.41 | 97.13 | 45% | 95.5845 | 9284.1225
1439 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 0.0 m to 1.5m) | 2026-08-19 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2091-01 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole# MH-12-19-4 to MH-12-19-5 at Road MCE0 | 212.41 | 98.74 | 45% | 95.5845 | 9438.0135
1440 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 0.0 m to 1.5m) | 2026-08-19 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2092-01 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole# MH-12-19-3 to MH-12-19-4 at Road MCE0 | 212.41 | 98.86 | 45% | 95.5845 | 9449.4837
1441 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-16 | SUD1-02-011-TDC-TS9-1-STR-FIR-2093-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/6/6 to CB-G2/6/6 B (S) at Road MCG0 | 377.3 | 29.11 | 5% | 18.865 | 549.1602
1442 | B3.33 14 13.3 | POT ABLE WATER NETWORK: HDPE Pipes 225 Diameter (Depth 0 to 1.50m) | 2026-08-16 | SUD1-02-011-TDC-TS9-1-PW-FIR-2094-00 | Check Sand bedding and pipe installation of potable water HDPE Pipes(225mm) at ST: +625.00 to ST: +000.00 Road MCG0 | 179.43 | 625.00 | 45% | 80.7435 | 50464.6875
1443 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-16 | SUD1-02-011-TDC-TS9-1-STR-FIR-2097-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # CB-G2/16/1 (D) to CB-G2/16/1 A(S) at Road MCE0 | 377.3 | 28.80 | 45% | 169.785 | 4889.808
1444 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-16 | SUD1-02-011-TDC-TS9-1-STR-FIR-2098-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # CB-G2/16/1 B (S) to MH-G2/16/1 at Road MCE0 | 377.3 | 22.38 | 45% | 169.785 | 3799.7883
1445 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-16 | SUD1-02-011-TDC-TS9-1-STR-FIR-2099-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # CB-G2/16/2 A (S) to CB-G2/16/2 (D) at Road MCE0 | 377.3 | 24.14 | 45% | 169.785 | 4098.6099
1446 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-16 | SUD1-02-011-TDC-TS9-1-STR-FIR-2100-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # CB-G2/16/3 A (S) to CB-G2/16/3 (D) at Road MCE0 | 377.3 | 28.85 | 45% | 169.785 | 4898.2973
1447 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-16 | SUD1-02-011-TDC-TS9-1-STR-FIR-2101-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # CB-G2/16/3 B (S) to MH-G2/16/3 at Road MCE0 | 377.3 | 24.34 | 45% | 169.785 | 4132.5669
1448 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-16 | SUD1-02-011-TDC-TS9-1-STR-FIR-2102-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # CB-G2/16/4 A (S) to CB-G2/16/4 (D) at Road MCE0 | 377.3 | 28.80 | 45% | 169.785 | 4889.808
1449 | B3.33 14 13.3 | POTABLE WATER NETWORK: HDPE Pipes 225 Diameter (Depth 0 to 1.50m) | 2026-08-16 | SUD1-02-011-TDC-TS9-1-PW-FIR-2103-00 | Check Coordinates level and Excavation width Bottom level and compaction for potable water pipeline from Station ST: +625.00 to ST: +000.00 Road MCF0 | 179.43 | 625.00 | 5% | 8.9715 | 5607.1875
1450 | B2.33 71 19.02 | Road crossing ducts, 4 ways (4 x 150mm PVC) | 2026-08-16 | SUD1-02-011-TDC-TS9-1-LIT-FIR-2108-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (4X160mm) from Manhole 63 To Manhole 64 for Street Lighting Duct Bank in Road MCC0 | 617.84 | 17.14 | 25% | 154.46 | 2647.4444
1451 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-08-16 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2104-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-1-88-2-2 to MH-1-88-2-1 at Road MCD0 | 212.41 | 98.74 | 45% | 95.5845 | 9438.0135
1452 | B5 33.05.13.08 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 3.51-4.5/BD) with Backdrop | 2026-08-17 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2109-00 | Check Installation of Manhole Base MH-12-8 at Road MCH0. | 21251.83 | 01 | 30% | 6375.549 | 6375.549
1453 | B5 33.05.13.01 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 0-1.50m) | 2026-08-17 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2110-00 | Check Installation of Manhole Base (Rings not required) MH-12-11-1-3 at Road MCG0. | 8820.42 | 01 | 30% | 2646.126 | 2646.126
1454 | B5 33.05.13.01 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 0-1.50m) | 2026-08-17 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2111-00 | Check Installation of Manhole Base MH-12-11-5 at Road MCG0 | 8820.42 | 01 | 30% | 2646.126 | 2646.126
1455 | B5 33.05.13.01 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 0-1.50m) | 2026-08-17 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2112-00 | Check Installation of Manhole Base (Rings not required) MH-12-7-1-2 at Road MCH0 | 8820.42 | 01 | 30% | 2646.126 | 2646.126
1456 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-16 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2113-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Plot (3) STA: 0+0250 to STA: 0+310 | 22.31 | 1505.15 | 100% | 22.31 | 33579.8965
1457 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-17 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2114-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at PLOT (1), STA: 0+200 to STA: 0+400 | 22.31 | 5376.76 | 100% | 22.31 | 119955.5156
1458 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-17 | SUD1-02-011-TDC-TS9-1-STR-FIR-2115-00 | Check Coordinates level and compaction F.D.T for Backfilling of #CB-G2/6(S) at Road MCG0 (Bottom subgrade) | 5124.07 | 1 | 10% | 512.407 | 512.407
1459 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-17 | SUD1-02-011-TDC-TS9-1-STR-FIR-2116-00 | Check Coordinates level and compaction F.D.T for Backfilling of #CB-G2/6/1 B(S) at Road MCG0 (Bottom subgrade) | 5124.07 | 1 | 10% | 512.407 | 512.407
1460 | B1.31 22 00.01 | Earth works & Site Grading (Road Excavation/cutting) | 2026-08-17 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2117-00 | Check Coordinates and bottom level Road Excavation/cutting upto bottom of Sub-Grade Sholuder (Right side) STA: 5+970 to STA: 6+120 at Road # MC20 | 13.58 | 2617.51 | 10% | 1.358 | 3554.5786
1461 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-17 | SUD1-02-011-TDC-TS9-1-STR-FIR-2120-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # MH-G2/11/6 to CB-G2/11/6 B (S) at Road MCF0 | 377.3 | 25.44 | 5% | 18.865 | 479.9256
1462 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0.00 - 1.5m) | 2026-08-17 | SUD1-02-011-TDC-TS9-1-IRR-FIR-2121-00 | Check Coordinates level and compaction F.D.T for Backfilling Road crossing 125mm O.D HDPE Pipes for ST:+389.75,ST:+143.63 at Road MCF0 (Last layer) | 179.43 | 67.09 | 10%
1463 | B4.33 14 13.4 | TSE NETWORK: 125mm Diameter (Depth: >1.5m) | 2026-08-17 | SUD1-02-011-TDC-TS9-1-IRR-FIR-2122-00 | Check Coordinates level and compaction F.D.T for Backfilling Road crossing 125mm O.D HDPE Pipes for ST: +0.00,ST+432.1at Road MCF0 (Last layer) | 184.28 | 30.57 | 10%
1464 | B4.33 14 13.5 | TSE NETWORK: 225mm Diameter (Depth: 0.0m - 1.5m) | 2026-08-17 | SUD1-02-011-TDC-TS9-1-IRR-FIR-2125-00 | Check Coordinates level and compaction F.D.T for Backfilling Road crossing 225mm O.D HDPE Pipes for ST: +461.88 &ST: +536.87 at Road MCF0 (Last layer) | 290.97 | 27.23 | 10%
1465 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole diameter, 2000mm (Depth: >2.5m) | 2026-08-17 | SUD1-02-011-TDC-TS9-1-STR-FIR-2129-00 | Check Coordinates level and compaction F.D.T for Backfilling of Manhole #MH-G2/6/1 at Road MCG0 (Bottom subgrade) | 30133.35 | 01 | 10% | 3013.335 | 3013.335
1466 | B6.33 05 39.16 | STORM WATER NETWORK: - Catch Basin Double | 2026-08-17 | SUD1-02-011-TDC-TS9-1-STR-FIR-2130-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/6/2 (D) at Road MCG0 (Bottom subgrade) | 12444.99 | 01 | 10% | 1244.499 | 1244.499
1467 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth:> 2.5m) | 2026-08-17 | SUD1-02-011-TDC-TS9-1-STR-FIR-2131-00 | Check Coordinates level and compaction F.D.T for Backfilling of Manhole # MH - G2/6/2 at Road MCG0 (Bottom subgrade) | 30133.35 | 01 | 10% | 3013.335 | 3013.335
1468 | B6.33 05 39.6 | STORM WATER NETWORK: Manhole Diameter :-1500mm (Depth: 2.51 m - 3.5m) | 2026-08-17 | SUD1-02-011-TDC-TS9-1-STR-FIR-2132-00 | Check Coordinates level and compaction F.D.T for Backfilling of Manhole # MH - G2/6/4 at Road MCG0 (Bottom subgrade) | 19537.02 | 01 | 10% | 1953.702 | 1953.702
1469 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-17 | SUD1-02-011-TDC-TS9-1-STR-FIR-2133-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/6/4 B (S) at Road MCG0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1470 | B6.33 05 39.6 | STORM WATER NETWORK: Manhole Diameter :-1500mm (Depth: >2.5m) | 2026-08-17 | SUD1-02-011-TDC-TS9-1-STR-FIR-2134-00 | Check Coordinates level and compaction F.D.T for Backfilling of # MH-G2/6/3 at Road MCG0 (Bottom subgrade) | 19537.02 | 01 | 10% | 1953.702 | 1953.702
1471 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-17 | SUD1-02-011-TDC-TS9-1-STR-FIR-2135-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/6/3 B (S) at Road MCG0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1472 | B1.31 22 00.01 | Earth works & Site Grading/cutting | 2026-08-18 | SUD1-02-011-TDC-TS9-1-LSP-FIR-2136-00 | Check Coordinates level and Compaction F.D.T for cutting Grading level for bottom of replacement soil (MODON Landscape Area) From #STA: 0+320 to STA: 0+620 | 13.58 | 1391.27 | 10% | 1.358 | 1889.3447
1473 | B1.31 22 00.03 | Earth works & Site Grading/Filling | 2026-08-18 | SUD1-02-011-TDC-TS9-1-LSP-FIR-2137-00 | Check Coordinates level and Compaction F.D.T for Filling Grading level for bottom of replacement soil (MODON Landscape Area)# STA: 0+320 to STA: 0+620 | 22.31 | 168.56 | 10% | 2.231 | 376.0574
1474 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-18 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2139-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Plot (5) STA: 0+110 to STA: 0+150 | 22.31 | 1250.81 | 100% | 22.31 | 27905.5711
1475 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2140-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/11/3 B (S) at Road MCF0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1476 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2141-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole # CB-G2/11 (S) to FIMH-G2/11 at Road MCF0 (Last Layer) | 377.3 | 23.25 | 10% | 37.73 | 877.2225
1477 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2142-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole # CB-G2/11/1 A (S) to CB-G2/11/1 (D) at Road MCF0 (Last Layer) | 377.3 | 28.80 | 10% | 37.73 | 1086.624
1478 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400mm for Catch Basin | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2143-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole # CB-G2/11/1 (D) to MH-G2/11/1 at Road MCF0 (Last Layer) | 602.32 | 10.53 | 10% | 60.232 | 634.243
1479 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2144-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole # CB-G2/11/1 B (S) to MH-G2/11/1 at Road MCF0 (Last Layer) | 377.3 | 17.45 | 10% | 37.73 | 658.3885
1480 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2145-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole #CB-G2/11 /2 (D) to CB-G2/11/2 A(S) at Road MCF0 (Last Layer) | 377.3 | 23.73 | 10% | 37.73 | 895.3329
1481 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400mm for Catch Basin | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2146-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole #MH-G2/11/2 to CB-G2/11/2 (D) at Road MCF0 (Last Layer) | 602.32 | 11.47 | 10% | 60.232 | 690.861
1482 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2147-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole #MH-G2/11/2 to CB-G2/11/2 B (S) at Road MCF0 (Last Layer) | 377.3 | 16.47 | 10% | 37.73 | 621.4131
1483 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2148-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole # CB-G2/11 /3 A (S) to CB-G2/11 /3 (D) at Road MCF0 (Last Layer) | 377.3 | 28.80 | 10% | 37.73 | 1086.624
1484 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2149-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole CB-G2/11/3 B(S) MH-G2/11/3 at Road MCF0 (Last Layer) | 377.3 | 15.75 | 10% | 37.73 | 594.2475
1485 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400mm for Catch Basin | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2150-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole# CB-G2/11/3 (D) MH-G2/11/3 at Road MCF0 (Last Layer) | 602.32 | 12.67 | 10% | 60.232 | 763.1394
1486 | B6.33 05 39.5 | STORM WATER NETWORK: Manhole Diameter :- 1500 mm (Depth: 1.51 m- 2.5 m) | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2151-00 | Check Coordinates level and compaction F.D.T for Backfilling of # FMH -A2/9/20-398 at Road MCG0 (Bottom subgrade) | 15295.58 | 01 | 10% | 1529.558 | 1529.558
1487 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2152-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-A2/9/20-398 (S) at Road MCG0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1488 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200 mm (Depth: 1.51 m- 2.5 m) | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2153-00 | Check Coordinates level and compaction F.D.T for Backfilling of # MH -G2/6/5 at Road MCG0 (Bottom subgrade) | 12376.13 | 01 | 10% | 1237.613 | 1237.613
1489 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2154-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/6/5 A (S) at Road MCG0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1490 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2155-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/6/5 B (S) at Road MCG0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1491 | B6.33 05 39.2 | STORM WATER NETWORK: 1200mm (Depth: 1.51 m - 2.5m) | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2156-00 | Check Coordinates level and compaction F.D.T for Backfilling of # MH -G2/6/6 at Road MCG0 (Bottom subgrade) | 12376.13 | 01 | 10% | 1237.613 | 1237.613
1492 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2157-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/6/6 C (S) at Road MCG0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1493 | B6.33 05 39.2 | STORM WATER NETWORK: 1200mm (Depth: 1.51 m - 2.5m) | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2158-00 | Check Coordinates level and compaction F.D.T for Backfilling of # MH -G2/6/7 at Road MCG0 (Bottom subgrade) | 12376.13 | 01 | 10% | 1237.613 | 1237.613
1494 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2159-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/6/7 (S) at Road MCG0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1495 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51m - 2.5m) | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2160-00 | Check Coordinates level and compaction F.D.T for Backfilling of # FMH -A2/9/20-396 at Road MCG0 (Bottom subgrade) | 12376.13 | 01 | 10% | 1237.613 | 1237.613
1496 | B2.33 71 19.01 | Road crossing ducts, 2 ways (2 x 150mm PVC) | 2026-08-18 | SUD1-02-011-TDC-TS9-1-CCTV-FIR-2161-00 | Check levels, laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (2X160mm) for CCTV Duct Bank Near Pole (4) in Road MCE0 as per Attached Highlighted Drawing | 308.43 | 20.63 | 25% | 77.1075 | 1590.7277
1497 | B2.33 71 19.01 | Road crossing ducts, 2 ways (2 x 150mm PVC) | 2026-08-18 | SUD1-02-011-TDC-TS9-1-CCTV-FIR-2162-00 | Check levels, laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (2X160mm) for CCTV Duct Bank Near Pole (4) in Road MCD0 as per Attached Highlighted Drawing | 308.43 | 15.46 | 25% | 77.1075 | 1192.082
1498 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-22 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2163-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at PLOT (1), STA: 0+400 to STA: 0+610 | 22.31 | 8093.05 | 100% | 22.31 | 180555.9455
1499 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2164-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from CB03-22 (S) FMH-G2/5 at Road MCG0 | 377.3 | 26.29 | 45% | 169.785 | 4463.6476
1500 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2165-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from CB03-21 (S) to FMH-G2/8 at Road MCG0 | 377.3 | 27.69 | 45% | 169.785 | 4701.3467
1501 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2166-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from CB-G2/6/6 B (S) MH-G2/6/6 at Road MCG0 | 377.3 | 29.11 | 45% | 169.785 | 4942.4414
1502 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2169-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/11 (S) at Road MCF0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1503 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2170-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/11/1 (D) at Road MCF0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1504 | B3.33 14 13.1 | POTABLE WATER NETWORK: HOPE Pipes 160mm Diameter (Depth O.Om to 1.50m) | 2026-08-17 | SUD1-02-011-TDC-TS9-1-PW-FIR-2123-00 | Check Coordinates level and compaction F.D.T for Backfilling Road crossing potable water HDPE pipelines at ST: +449.02& ST: +195.75 (Diameter 160mm) at Road MCF0 (Last lyer) | 101.84 | 67.98 | 10% | 10.184 | 692.3083
1505 | B3.33 14 13.1 | POTABLE WATER NETWORK: HDPE Pipes 160mm Diameter (Depth 0m-1.50m) | 2026-08-18 | SUD1-02-011-TDC-TS9-1-PW-FIR-2172-00 | Check Coordinates level and Excavation width Bottom level and compaction for Road crossing potable water HDPE pipelines (Diameter 160mm) at Road MCZ0 | 101.84 | 26.80 | 5% | 5.092 | 136.4656
1506 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2173-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole CB-G2/11/4 (D) to CB-G2/11/4 A (S) at Road MCF0 (Last Layer) | 377.3 | 28.80 | 10% | 37.73 | 1086.624
1507 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400mm for Catch Basin | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2174-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole MH-G2/11/4 to CB-G2/11/4 (D) at Road MCF0 (Last Layer) | 602.32 | 13.63 | 10% | 60.232 | 820.9622
1508 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2175-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole MH-G2/11 /4 to CB-G2/11 /4 B (S) at Road MCF0 (Last Layer) | 377.3 | 14.78 | 10% | 37.73 | 557.6494
1509 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2176-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole FMH-A2/9/20-399 to CB-A2/9/20-399 (S) at Road MCF0 (Last Layer) | 377.3 | 2.90 | 10% | 37.73 | 109.417
1510 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2177-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/11/1 A (S) at Road MCF0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1511 | B6.33 05 39.9 | STORM WATER NETWORK: 2000mm (Depth:> 2.5m) | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2178-00 | Check Coordinates level and compaction F.D.T for Backfilling of # MH -G2/11/1 at Road MCF0 (Bottom subgrade) | 30133.35 | 01 | 10% | 3013.335 | 3013.335
1512 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2179-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/11/1 B (S) at Road MCF0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1513 | B6.33 05 39.16 | STORM WATER NETWORK: Catch Basin Double | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2180-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2-11/2 (D) at Road MCF0 (Bottom subgrade) | 12444.99 | 01 | 10% | 1244.499 | 1244.499
1514 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2181-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/11/2 A(S) at Road MCF0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1515 | B6.33 05 39.9 | STORM WATER NETWORK: 2000mm (Depth:> 2.5m) | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2182-00 | Check Coordinates level and compaction F.D.T for Backfilling of # MH-G2/11/2 at Road MCF0 (Bottom subgrade) | 30133.35 | 01 | 10% | 3013.335 | 3013.335
1516 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2183-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/11/2 B (S) at Road MCF0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1517 | B6.33 05 39.16 | STORM WATER NETWORK: Catch Basin Double | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2184-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/11/3 (D) at Road MCF0 (Bottom subgrade) | 12444.99 | 01 | 10% | 1244.499 | 1244.499
1518 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2185-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/11/3 A (S) at Road MCF0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1519 | B6.33 05 39.6 | STORM WATER NETWORK: Manhole Diameter :-1500mm (Depth: >2.5m) | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2186-00 | Check Coordinates level and compaction F.D.T for Backfilling of # MH-G2/11/3 at Road MCF0 (Bottom subgrade) | 19537.02 | 01 | 10% | 1953.702 | 1953.702
1520 | B6.33 05 39.16 | STORM WATER NETWORK: Catch Basin Double | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2187-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/11/4 (D) at Road MCF0 (Bottom subgrade) | 12444.99 | 01 | 10% | 1244.499 | 1244.499
1521 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2188-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/11/4 A (S) at Road MCF0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1522 | B6.33 05 39.6 | STORM WATER NETWORK: Manhole Diameter :-1500mm (Depth: >2.5m) | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2189-00 | Check Coordinates level and compaction F.D.T for Backfilling of # MH-G2/11/4 at Road MCF0 (Bottom subgrade) | 19537.02 | 01 | 10% | 1953.702 | 1953.702
1523 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2190-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/11/4 B (S) at Road MCF0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1524 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2191-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-A2/9/20-399 (S) at Road MCF0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1525 | B6.33 05 39.6 | STORM WATER NETWORK: Manhole Diameter :-1500mm (Depth: >2.5m) | 2026-08-18 | SUD1-02-011-TDC-TS9-1-STR-FIR-2192-00 | Check Coordinates level and compaction F.D.T for Backfilling of # FMH-A2/9/20-399 at Road MCF0 (Bottom subgrade) | 19537.02 | 01 | 10% | 1953.702 | 1953.702
1526 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-2193-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-A2/9/20-396(S) at Road MCG0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1527 | B6.33 05 39.16 | STORM WATER NETWORK: Catch Basin Double | 2026-08-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-2194-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/6/1 (D) at Road MCG0 (Bottom subgrade) | 12444.99 | 01 | 10% | 1244.499 | 1244.499
1528 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-2195-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/6/1 A (S) at Road MCG0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1529 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-2196-00 | Check compaction F.D.T for Backfilling of # CB-G2/6/2 A (S) at Road MCG0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1530 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-2197-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/6/2 B (S) at Road MCG0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1531 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-2198-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/6/3 A (S) at Road MCG0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1532 | B6.33 05 39.16 | STORM WATER NETWORK: Catch Basin Double | 2026-08-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-2199-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/6/3 (D) at Road MCG0 (Bottom subgrade) | 12444.99 | 01 | 10% | 1244.499 | 1244.499
1533 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-2200-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/6/4 A (S) at Road MCG0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1534 | B6.33 05 39.16 | STORM WATER NETWORK: Catch Basin Double | 2026-08-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-2201-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/6/4 (D) at Road MCG0 (Bottom subgrade) | 12444.99 | 01 | 10% | 1244.499 | 1244.499
1535 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-19 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2203-00 | Check Coordinates level and Compaction F.D.T for Embankment 13th layer at PLOT (5), STA: 0+230 to STA: 0+360 | 22.31 | 4658.47 | 100% | 22.31 | 103930.4657
1536 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 0 to 1.5m) | 2026-08-19 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2204-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-13-1 to MH-12-13-1-1 at Road MCF0 | 212.41 | 78.87 | 45% | 95.5845 | 7538.7495
1537 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 0 to 1.5m) | 2026-08-19 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2205-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-13-1-1 to MH-12-13-1-2 at Road MCF0 | 212.41 | 98.86 | 45% | 95.5845 | 9449.4837
1538 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 0 to 1.5m) | 2026-08-19 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2206-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-13-1-2 to MH-12-13-1-3 at Road MCF0 | 212.41 | 98.74 | 45% | 95.5845 | 9438.0135
1539 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-2202-00 | Check Coordinates level and compaction F.D.T for Backfilling of # CB-G2/6/6 A (S) at Road MCG0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1540 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-2207-00 | Inspection Gravity and Leakage test pipeline from Manhole # CB-G2/16/1 (D) to CB-G2/16/1 A(S) at Road MCE0 | 377.3 | 28.80 | 10% | 37.73 | 1086.624
1541 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-2208-00 | Inspection Gravity and Leakage test pipeline from Manhole # CB-G2/16/1 B (S) to MH-G2/16/1 at Road MCE0 | 377.3 | 22.38 | 10% | 37.73 | 844.3974
1542 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-2209-00 | Inspection Gravity and Leakage test pipeline from Manhole# CB-G2/16/2 A (S) to CB-G2/16/2 (D) at Road MCE0 | 377.3 | 24.14 | 10% | 37.73 | 910.8022
1543 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-2210-00 | Inspection Gravity and Leakage test pipeline from Manhole # CB-G2/16/3 A (S) to CB-G2/16/3 (D) at Road MCE0 | 377.3 | 28.85 | 10% | 37.73 | 1088.5105
1544 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-2211-00 | Inspection Gravity and Leakage test pipeline from Manhole # CB-G2/16/3 B (S) to MH-G2/16/3 at Road MCE0 | 377.3 | 24.34 | 10% | 37.73 | 918.3482
1545 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-2212-00 | Inspection Gravity and Leakage test pipeline from Manhole # CB-G2/16/4 A (S) to CB-G2/16/4 (D) at Road MCE0 | 377.3 | 28.80 | 10% | 37.73 | 1086.624
1546 | B6.33 42 11.22 | STORM WATER NETWORK: GRP Pipes1000mm Diameter (Depth: 1.51m – 2.50m) | 2026-08-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-2213-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from Manhole # MH-G2/16/2 TOMH-G2/16/3 at Road MCE0 | 884.56 | 87.00 | 45% | 398.052 | 34630.524
1547 | B6.33 05 39.6 | STORM WATER NETWORK: Manhole Diameter :- 1500mm (Depth: Greater 2.50m) | 2026-08-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-2214-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/38 at Road MCB0 | 19537.02 | 01 | 5% | 976.851 | 976.851
1548 | B6.33 05 39.6 | STORM WATER NETWORK: Manhole Diameter :- 1500mm (Depth: Greater 2.50m) | 2026-08-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-2215-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/37 at Road MCB0 | 19537.02 | 01 | 5% | 976.851 | 976.851
1549 | B6.33 05 39.6 | STORM WATER NETWORK: Manhole Diameter :- 1500mm (Depth: Greater 2.50m) | 2026-08-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-2216-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/36 at Road MCB0 | 19537.02 | 01 | 5% | 976.851 | 976.851
1550 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: Greater 2.50m) | 2026-08-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-2217-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/35 at Road MCB0 | 30133.35 | 01 | 5% | 1506.6675 | 1506.6675
1551 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: Greater 2.50m) | 2026-08-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-2218-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/34 at Road MCB0 | 30133.35 | 01 | 5% | 1506.6675 | 1506.6675
1552 | B6.33 42 11.16 | STORM WATER NETWORK: GRP Pipes 800mm (Depth: 1.51-2.50m) | 2026-08-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-2219-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/39 to STA-A1/38 at Road MCB0 | 639.17 | 66.41 | 5% | 31.9585 | 2122.364
1553 | B6.33 42 11.16 | STORM WATER NETWORK: GRP Pipes 800mm (Depth: 1.51-2.50m) | 2026-08-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-2220-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/38 to STA-A1/37 at Road MCB0 | 639.17 | 50.50 | 5% | 31.9585 | 1613.9043
1554 | B6.33 42 11.16 | STORM WATER NETWORK: GRP Pipes 800mm (Depth: 1.51-2.50m) | 2026-08-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-2221-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/37 to STA-A1/36at Road MCB0 | 639.17 | 53.90 | 5% | 31.9585 | 1722.5631
1555 | B6.33 42 11.20 | STORM WATER NETWORK: GRP Pipes 900mm (Depth: 2.51-3.50m) | 2026-08-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-2222-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/36 to STA-A1/35 at Road MCB0 | 875.83 | 60.77 | 5% | 43.7915 | 2661.2095
1556 | B6.33 42 11.23 | STORM WATER NETWORK: GRP Pipes 1000 mm (Depth: 2.51-3.50m) | 2026-08-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-2223-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/35 STA-A1/34 at Road MCB0 | 1017.44 | 50.00 | 5% | 50.872 | 2543.6
1557 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 1.51 to 2.5m) | 2026-08-19 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2224-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-1-93 to MH-1-92 at Road MCC0 | 221.14 | 41.87 | 10% | 22.114 | 925.9132
1558 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 0 to 1.5m) | 2026-08-19 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2225-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-1-88-2-2 to MH-1-88-2-1 at Road MCD0 | 212.41 | 98.74 | 10% | 21.241 | 2097.3363
1559 | B3.33 14 13.3 | POTABLE WATER NETWORK: HDPE Pipes 225 Diameter (Depth 0 to 1.50m) | 2026-08-25 | SUD1-02-011-TDC-TS9-1-PW-FIR-2226-00 | Check Coordinates level and Excavation width Bottom level and compaction for potable water pipeline from Station ST: +475.00 to ST: +000.00 Road MCE0 | 179.43 | 475.00 | 5% | 8.9715 | 4261.4625
1560 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-2227-00 | Inspection Gravity and Leakage test pipeline from Manhole # CB-G2/6/6 B (S) MH-G2/6/6 at Road MCG0 | 377.3 | 29.11 | 10% | 37.73 | 1098.3203
1561 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-2228-00 | Inspection Gravity and Leakage test pipeline from Manhole # CB03-22 (S) FMH-G2/5 at Road MCG0 | 377.3 | 26.29 | 10% | 37.73 | 991.9217
1562 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-2229-00 | Inspection Gravity and Leakage test pipeline from Manhole # CB03-21 (S) to FMH-G2/8 at Road MCG0 | 377.3 | 27.69 | 10% | 37.73 | 1044.7437
1563 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-20 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2234-00 | Check Coordinates level and Compaction F.D.T for Embankment 15th layer at PLOT (5), STA: 0+360 to STA: 0+420 | 22.31 | 1501.43 | 100% | 22.31 | 33496.9033
1564 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin (Single) | 2026-08-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-2235-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB02-22(S) at Road MCF0 | 5124.07 | 1.00 | 5% | 256.2035 | 256.2035
1565 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin (Single) | 2026-08-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-2236-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB02-23(S) at Road MCF0 | 5124.07 | 1.00 | 5% | 256.2035 | 256.2035
1566 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-2240-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Existing Manhole # FIMH-G2/13 to CB02-22 (S) at Road MCF0 | 377.3 | 26.53 | 5% | 18.865 | 500.4885
1567 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-2241-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Existing Manhole # FIMH-G2/10 to CB02-23 (S) at Road MCF0 | 377.3 | 26.79 | 5% | 18.865 | 505.3934
1568 | B5 33 05 13.05 | SEVVERAGE NETWORK: Manhole (Depth 2.51 m to 3.5m) Internal Diameter (1200mm) | 2026-08-20 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2247-00 | Check compaction F.D.T for Backfilling 4th layer of Manhole # MH-53-1 at Road MCF0(bottom subgrade) | 15848.43 | 1 | 10% | 1584.843 | 1584.843
1569 | B5 33 05 13.05 | SEVVERAGE NETWORK: Manhole (Depth 2.51 m to 3.5m) Internal Diameter (1200mm) | 2026-08-20 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2248-00 | Check compaction F.D.T for Backfilling 4th layer of Manhole # MH-53-2 at Road MCF0(Bottom subgrade) | 15848.43 | 01 | 10% | 1584.843 | 1584.843
1570 | B5 33 05 13.05 | SEVVERAGE NETWORK: Manhole (Depth 2.51 m to 3.5m) Internal Diameter (1200mm) | 2026-08-20 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2249-00 | Check compaction F.D.T for Backfilling 4th layer of Manhole # MH-53-3 at Road MCF0 (Bottom subgrade) | 15848.43 | 01 | 10% | 1584.843 | 1584.843
1571 | B5 33 05 13.03 | SEVVERAGE NETWORK: Manhole (Depth 1.51 m to 2.5m) Internal Diameter (1200mm) | 2026-08-20 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2250-00 | Check compaction F.D.T for Backfilling 4th layer of Manhole # MH-53-4 at Road MCF0 (Bottom subgrade) | 12377.1 | 01 | 10% | 1237.71 | 1237.71
1572 | B5 33 05 13.03 | SEVVERAGE NETWORK: Manhole (Depth 1.51 m to 2.5m) Internal Diameter (1200mm) | 2026-08-20 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2251-00 | Check compaction F.D.T for Backfilling 4th layer of Manhole # MH-53-5 at Road MCF0 (Bottom subgrade) | 12377.1 | 01 | 10% | 1237.71 | 1237.71
1573 | B5 33 05 13.03 | SEVVERAGE NETWORK: Manhole (Depth 1.51 m to 2.5m) Internal Diameter (1200mm) | 2026-08-20 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2252-00 | Check compaction F.D.T for Backfilling 4th layer of Manhole # MH-53-6 at Road MCF0 (Bottom subgrade) | 12377.1 | 01 | 10% | 1237.71 | 1237.71
1574 | B6.33 42 11.22 | STORM WATER NETWORK: GRP Pipes1000mm Diameter (Depth: 1.51m – 2.50m) | 2026-08-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-2253-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/16/2 TOMH-G2/16/3 at Road MCE0 | 884.56 | 87.00 | 10% | 88.456 | 7695.672
1575 | B5.33 31 00.01 | SEWER NETWORK: GRP Pipes 200mm (Manhole Depth: 0- 1.50m) | 2026-08-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2255-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-19-3 to MH-12-19-2 at Road MCE0 | 212.41 | 78.87 | 10% | 21.241 | 1675.2777
1576 | B5.33 31 00.01 | SEWER NETWORK: GRP Pipes 200mm (Manhole Depth: 0- 1.50m) | 2026-08-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2256-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-19-5 to MH-12-19-4 at Road MCE0 | 212.41 | 98.74 | 10% | 21.241 | 2097.3363
1577 | B1.31 22 00.03 | Earth works & Site Grading | 2026-08-20 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2259-00 | Check Coordinates and bottom level Road Filling and compaction test 1st Layer of shoulders (Right & Left side) at Road # MC10, STA: 2+660 to STA: 2+740 | 22.31 | 1204.67 | 10% | 2.231 | 2687.6188
1578 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-22 | SUD1-02-011-TDC-TS9-1-STR-FIR-2260-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from MH-G2/16/6 to CB-G2/16/6 B (S) at Road MCF0 | 377.3 | 24.49 | 45% | 169.785 | 4158.0346
1579 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-2261-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from MH-G2/16/4 to CB-G2/16/4 B (S) at Road MCE0 | 377.3 | 25.34 | 45% | 169.785 | 4302.3519
1580 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-2263-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # MH-G2/16/6 to CB-G2/16/6 A (S) at Road MCE0 | 377.3 | 12.71 | 45% | 169.785 | 2157.9673
1581 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-2264-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # MH-G2/11/6 to CB-G2/11/6 B (S) at Road MCF0 | 377.3 | 25.44 | 45% | 169.785 | 4319.3304
1582 | B5.33 31 00.01 | SEWER NETWORK: GRP Pipes 200mm (Manhole Depth: 0- 1.50m) | 2026-08-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2265-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-19-4 to MH-12-19-3 at Road MCE0 | 212.41 | 98.86 | 10% | 21.241 | 2099.8853
1583 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400mm | 2026-08-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-2266-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # MH-G2/16/4 to CB-G2/16/4 (D) at Road MCE0 | 602.32 | 3.63 | 45% | 271.044 | 983.8897
1584 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-2267-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # MH-G2/16/7 to CB-G2/16/7 B (S) at Road MCE0 | 377.3 | 41.88 | 45% | 169.785 | 7110.5958
1585 | B2.33 71 19.01 | Road crossing ducts, 2 ways (2 x 150mm PVC) | 2026-08-22 | SUD1-02-011-TDC-TS9-1-CCTV-FIR-2271-00 | Check levels, laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (2X160mm) for CCTV Duct Bank Near Pole (2) in road MCG0 as per Attached Highlighted Drawing | 308.43 | 11.28 | 25% | 77.1075 | 869.7726
1586 | B5.33 31 00.01 | SEWER NETWORK: GRP Pipes 200mm (Manhole Depth: 0- 1.50m) | 2026-08-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2273-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-1-88-2-1 to MH-1-88-2 at Road MCD0 | 212.41 | 97.13 | 10% | 21.241 | 2063.1383
1587 | B5.33 31 00.01 | SEWER NETWORK: GRP Pipes 200mm (Manhole Depth: 0- 1.50m) | 2026-08-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2274-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-19-1-3 to MH-12-19-1-2 at Road MCE0 | 212.41 | 98.74 | 45% | 95.5845 | 9438.0135
1588 | B1.31 22 00.03 | Earth works & Site Grading | 2026-08-22 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2275-00 | Check Coordinates, level and compaction test of bottom Sub-Grade of Road # MCG0, STA: 0+240 to STA: 0+410 | 22.31 | 1,177.73 | 10% | 2.231 | 2627.5156
1589 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-22 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2276-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Plot (5) STA: 0+110 to STA: 0+150 | 22.31 | 413.95 | 100% | 22.31 | 9235.2245
1590 | B5.33 31 00.01 | SEWER NETWORK: GRP Pipes 200mm (Manhole Depth: 0- 1.50m) | 2026-08-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2277-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-19-1-2 MH-12-19-1-1 at Road MCE0 | 212.41 | 98.86 | 0.45 | 95.5845 | 9449.4837
1591 | B6.33 05 39.15 | Storm Water Network:Catch Basin ( Single) | 2026-08-22 | SUD1-02-011-TDC-TS9-1-STR-FIR-2278-00 | Check compaction F.D.T for Backfilling of # CB-G2/11/5 A (S) at Road MCF0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1592 | B6.33 05 39.15 | Storm Water Network:Catch Basin ( Single) | 2026-08-22 | SUD1-02-011-TDC-TS9-1-STR-FIR-2279-00 | Check compaction F.D.T for Backfilling of # CB-G2/11/5 B (S) at Road MCF0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1593 | B6.33 05 39.3 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: >2.5m) | 2026-08-22 | SUD1-02-011-TDC-TS9-1-STR-FIR-2280-00 | Check compaction F.D.T for Backfilling of #MH-G2/11/5 at Road MCF0 (Bottom subgrade) | 15848.43 | 01 | 10% | 1584.843 | 1584.843
1594 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-22 | SUD1-02-011-TDC-TS9-1-STR-FIR-2281-00 | Check compaction F.D.T for Trench Backfilling Between Manhole MH-G2/11/5 to CB-G2/11/5 A (S) at Road MCF0 (Last Layer) | 377.3 | 15.28 | 10% | 37.73 | 576.5144
1595 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-22 | SUD1-02-011-TDC-TS9-1-STR-FIR-2282-00 | Check compaction F.D.T for Trench Backfilling Between Manhole MH-G2/11/5 to CB-G2/11/5 B (S) at Road MCF0 (Last Layer) | 377.3 | 13.97 | 10% | 37.73 | 527.0881
1596 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-22 | SUD1-02-011-TDC-TS9-1-STR-FIR-2284-00 | Inspection Gravity and Leakage test pipeline from # MH-G2/11/6 to CB-G2/11/6 B (S) at Road MCF0 | 377.3 | 25.44 | 10% | 37.73 | 959.8512
1597 | B1.31 22 00.01 | Earth works & Site Grading/cutting | 2026-08-22 | SUD1-02-011-TDC-TS9-1-LSP-FIR-2285-00 | Check Coordinates level and Compaction F.D.T for cutting Grading level for bottom of replacement soil From STA: 0+120 to STA: 0+320 (MODON Landscape Area) | 13.58 | 1608.36 | 10% | 1.358 | 2184.1529
1598 | B1.31 22 00.04 | Earth works & Site Grading/Filling | 2026-08-22 | SUD1-02-011-TDC-TS9-1-LSP-FIR-2286-00 | Check Coordinates level and Compaction F.D.T for Filling Grading level for bottom of replacement soil STA: 0+120 to STA: 0+320 (MODON Landscape Area) | 22.31 | 16.87 | 10% | 2.231 | 37.637
1599 | B1.31 22 00.05 | Earth works & Site Grading (Subgrade) | 2026-08-22 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2287-00 | Check Coordinates level and Compaction F.D.T for (Subgrade)2nd layer at Road /Carriageway# MCF0, STA: 0+600 to STA: 0+770 | 28.13 | 1,038.54 | 10% | 2.813 | 2921.413
1600 | B2.33 71 19.13.02 | Drawpit with medium duty steel cover, size 900x900x1200mm | 2026-08-23 | SUD1-02-011-TDC-TS9-1-LIT-FIR-2288-00 | Check Installation Drawpit MH-20 for Street Lighting in Road MCG0 | 3850.57 | 1 | 30% | 1155.171 | 1155.171
1601 | B2.33 71 19.13.01 | Drawpit with medium duty steel cover, size600x600x1000mm | 2026-08-23 | SUD1-02-011-TDC-TS9-1-LIT-FIR-2289-00 | Check Installation Drawpit MH-21 & MH-22 for Street Lighting in Road MCG0 | 2683.76 | 2 | 30% | 805.128 | 1610.256
1602 | B2.33.71.19.13.05 | Manhole Type 3 | 2026-08-23 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2290-00 | Check Installation Manhole MH-025 & MH-027 for TELECOMMUNICATIONS Works in Road MCG0 | 7057.11 | 2 | 30% | 2117.133 | 4234.266
1603 | B1.31 22 00.05 | Earth works & Site Grading (Subgrade) | 2026-08-23 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2297-00 | Check Coordinates level and Compaction F.D.T for (Subgrade) 2nd layer at Road /Carriageway# MCG0, STA: 0+650 to STA: 0+800 | 28.13 | 886.68 | 10% | 2.813 | 2494.2308
1604 | B6.34 42 16.1 | STORM WATER NETWORK: GRP Pipes 900mm Diameter (Depth: 1.51 to 2.50m) |  | SUD1-02-011-TDC-TS9-1-STR-FIR-2302-01 | Inspection Flow test pipeline for Box Culvert from Existing Manhole # FIMH – G2/16 to MH – G2/16/1 at Road MCE0 | 22.31 | 150.94 | 0% | 0 | 0
1605 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-24 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2305-00 | Check Coordinates level and Compaction F.D.T for Embankment 7th layer at PLOT (2), STA: 0+570 to STA: 0+720 | 22.31 | 5012.10 | 100% | 22.31 | 111819.951
1606 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-23 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2306-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at PLOT (1), STA: 0+610 to STA: 0+857.5 | 22.31 | 3946.26 | 100% | 22.31 | 88041.0606
1607 | B2.33 71 19.13.02 | Drawpit with medium duty steel cover, size 900x900x1200mm | 2026-08-24 | SUD1-02-011-TDC-TS9-1-LIT-FIR-2315-00 | Check Installation Drawpit MH-13 & MH-14 & MH-15 & MH-16 for Street Lighting in Road MCF0 | 3850.57 | 4 | 30% | 1155.171 | 4620.684
1608 | B2.33.71.19.13.05 | Manhole Type 3 | 2026-08-24 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2316-00 | Check Installation Manhole MH-018 & MH-020 for TELECOMMUNICATIONS Works in Road MCF0 | 7057.11 | 2 | 30% | 2117.133 | 4234.266
1609 | B3.33 14 13.1 | POTABLE WATER NETWORK: HDPE Pipes 160mm Diameter (Depth 0m-1.50m) | 2026-08-24 | SUD1-02-011-TDC-TS9-1-PW-FIR-2318-00 | Check Sand bedding and pipe installation of Road crossing potable water HDPE Pipes(160mm) at ST: 2+036.62 Road MCZ0 | 101.84 | 26.80 | 45% | 45.828 | 1228.1904
1610 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-24 | SUD1-02-011-TDC-TS9-1-STR-FIR-2320-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB01-19 to FIMH-G2/16 at Road MCE0 | 377.3 | 22.78 | 5% | 18.865 | 429.7447
1611 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-24 | SUD1-02-011-TDC-TS9-1-STR-FIR-2321-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-G2/16 (S) to FIMH-G2/16 at Road MCE0 | 377.3 | 22.91 | 5% | 18.865 | 432.1972
1612 | B5 33.05.13.05 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm | 2026-08-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2307-01 | Check Installation of Rings and Flat slab of Manhole # MH-1-94 at Road MCC0 | 15848.43 | 01 | 30% | 4754.529 | 4754.529
1613 | B5 33.05.13.05 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm | 2026-08-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2308-01 | Check Installation of Rings and Flat slab of Manhole # MH-1-95 at Road MCC0 | 15848.43 | 01 | 30% | 4754.529 | 4754.529
1614 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-08-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2309-01 | Check Installation of including Rings and Flat slab of Manhole MH-1-96 at Road MCC0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
1615 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-08-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2310-01 | Check Installation Flat slab of Manhole # MH-1-97 at Road MCC0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
1616 | B5 33.05.13.01 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 0m- 1.50m) | 2026-08-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2311-01 | Check Installation of Flat slab of Manhole # MH-1-98 at Road MCC0 | 8820.42 | 01 | 30% | 2646.126 | 2646.126
1617 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-08-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2313-01 | Check Installation of Rings and Flat slab MH-1-93-1 at Road MCC0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
1618 | B5 33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-08-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2314-01 | Check Installation of Flat slab # MH-1-93-2 at Road MCC0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
1619 | B5 33.05.13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-08-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2322-00 | Check Installation of Flat slab MH-1-93-3 at Road MCC0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
1620 | B5 33.05.13.01 | SEWERAGE NETWORK: - Manhole Depth (0m to 1.5m) Internal Diameter :-1200mm | 2026-08-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2323-00 | Check Installation of Flat slab MH-1-93-4 at Road MCC0 | 8820.42 | 01 | 30% | 2646.126 | 2646.126
1621 | B5 33.05.13.01 | SEWERAGE NETWORK: - Manhole Depth (0m to 1.5m) Internal Diameter :-1200mm | 2026-08-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2324-00 | Check Installation of Flat slab of Manhole MH- 1-91-2 at Road MCA0 | 8820.42 | 01 | 30% | 2646.126 | 2646.126
1622 | B5 33.05.13.01 | SEWERAGE NETWORK: - Manhole Depth (0m to 1.5m) Internal Diameter :-1200mm | 2026-08-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2325-00 | Check Installation of Rings and Flat slab of Manhole MH- 1-91-1 at Road MCA0 | 8820.42 | 01 | 30% | 2646.126 | 2646.126
1623 | B5 33.05.13.01 | SEWERAGE NETWORK: - Manhole Depth (0m to 1.5m) Internal Diameter :-1200mm | 2026-08-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2326-00 | Check Installation of Rings and Flat slab of Manhole MH- 1-91 at Road MCA0 | 8820.42 | 01 | 0% | 0 | 0
1624 | B5 33.05.13.05 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm | 2026-08-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2327-01 | Check Installation of Rings and Flat slab of Manhole MH-1-90 at Road MCA0 | 15848.43 | 01 | 30% | 4754.529 | 4754.529
1625 | B5 33.05.13.05 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm | 2026-08-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2328-01 | Check Installation of Rings and Flat slab of Manhole MH-1-89 at Road MCA0 | 15848.43 | 01 | 30% | 4754.529 | 4754.529
1626 | B5 33.05.13.06 |  | 2026-08-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2329-00 | Check Installation of Rings and Flat slab Manhole MH-1-88 at Road MCA0 |  | 01 | 0% | 0 | 0
1627 | B5 33.05.13.05 |  | 2026-08-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2330-01 | Check Installation of Rings and Flat slab Manhole MH-1-87 at Road MCA0 |  | 01 | 0% | 0 | 0
1628 | B5 33.05.13.06 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm With Backdrop | 2026-08-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2331-01 | Check Installation of Rings and Flat slab Manhole MH-1-86 at Road MCA0 | 19018.11 | 01 | 30% | 5705.433 | 5705.433
1629 | B5 33.05.13.05 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm | 2026-08-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2332-01 | Check Installation of Rings and Flat slab Manhole MH-1-85 at Road MCA0 | 15848.43 | 01 | 30% | 4754.529 | 4754.529
1630 | B5 33.05.13.06 |  | 2026-08-25 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2333-00 | Check Installation of Rings and Flat slab Manhole MH-1-84 at Road MCA0 |  | 01 | 0% | 0 | 0
1631 | B5 33.05.13.05 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm | 2026-08-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2334-01 | Check Installation of Rings and Flat slab for Manhole MH-1-83 at Road MCA0 | 15848.43 | 01 | 30% | 4754.529 | 4754.529
1632 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-24 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2336-00 | Check Coordinates level and Compaction F.D.T for Embankment 16th layer at PLOT (5), STA: 0+360 to STA: 0+410 | 22.31 | 920.10 | 100% | 22.31 | 20527.431
1633 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-24 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2337-00 | Check Coordinates level and Compaction F.D.T for Embankment 14th layer at PLOT (5), STA: 0+230 to STA: 0+360 | 22.31 | 3907.25 | 100% | 22.31 | 87170.7475
1634 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-24 | SUD1-02-011-TDC-TS9-1-STR-FIR-2340-00 | Inspection Gravity and Leakage test pipeline from Manhole # CB-G2/16/7 B (S) to MH-G2/16/7 at Road MCE0 | 377.3 | 41.88 | 10% | 37.73 | 1580.1324
1635 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-24 | SUD1-02-011-TDC-TS9-1-STR-FIR-2341-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/16/6 to CB-G2/16/6 A (S) at Road MCE0 | 377.3 | 12.71 | 10% | 37.73 | 479.5483
1636 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-24 | SUD1-02-011-TDC-TS9-1-STR-FIR-2342-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/16/6 to CB-G2/16/6 B (S) at Road MCE0 | 377.3 | 24.49 | 10% | 37.73 | 924.0077
1637 | B1.31 22 00.05 | Earth works & Site Grading (Subgrade) | 2026-08-24 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2344-00 | Check Coordinates level and Compaction F.D.T for (Subgrade) 2nd layer at Road /Carriageway# MCG0, STA: 0+410 to STA: 0+650 | 28.13 | 1476.00 | 10% | 2.813 | 4151.988
1638 | B3.33 14 13.5 | POT ABLE WATER NETWORK: HDPE Pipes 315 Diameter (Depth 0 to 1.50m) | 2026-08-24 | SUD1-02-011-TDC-TS9-1-PW-FIR-2345-00 | Check Sand bedding and pipe installation of potable water HDPE Pipes(315mm) from ST: 1+750 to ST: 2+169.08 at Road MCZ0 | 290.97 | 419.08 | 45% | 130.9365 | 54872.8684
1639 | B1.31 22 00.01 | Earth works & Site Grading/cutting | 2026-08-24 | SUD1-02-011-TDC-TS9-1-LSP-FIR-2346-00 | Check Coordinates level and Compaction F.D.T for cutting Grading level for bottom of replacement soil from STA: 0+ 620 to STA: 0+720 (MODON Landscape Area) | 13.58 | 519.42 | 10% | 1.358 | 705.3724
1640 | B1.31 22 00.04 | Earth works & Site Grading/Filling | 2026-08-24 | SUD1-02-011-TDC-TS9-1-LSP-FIR-2347-00 | Check Coordinates level and Compaction F.D.T for Filling Grading level for bottom of replacement soil STA: 0+620 to STA: 0+720 (MODON Landscape Area) | 22.31 | 4.78 | 10% | 2.231 | 10.6642
1641 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 0 to 1.5m) | 2026-08-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2348-01 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-13-3 to MH-12-13-4 at Road MCF0 | 212.41 | 98.86 | 45% | 95.5845 | 9449.4837
1642 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 0 to 1.5m) | 2026-08-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2349-01 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-13-2 to MH-12-13-3 at Road MCF0 | 212.41 | 78.87 | 45% | 95.5845 | 7538.7495
1643 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-25 | SUD1-02-011-TDC-TS9-1-STR-FIR-2354-00 | Check compaction F.D.T for Trench Backfilling Between Manhole FMH-A2/9/20-397 to CB-A2/9/20-397 (S) at Road MCF0 (Last Layer) | 377.3 | 3.23 | 10% | 37.73 | 121.8679
1644 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-25 | SUD1-02-011-TDC-TS9-1-STR-FIR-2355-00 | Check compaction F.D.T for Backfilling of #CB-A2/9/20-397 (S) at Road MCF0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1645 | B3.33 14 13.3 | POT ABLE WATER NETWORK: HOPE Pipes 225 Diameter (Depth 0 to 1.50m) | 2026-09-01 | SUD1-02-011-TDC-TS9-1-PW-FIR-2356-01 | Inspection Pressure test of potable water Pipeline HDPE Pipes(225mm) from ST: +625.00 to ST: +000.00 Road MCG0 | 179.43 | 625.00 | 25% | 44.8575 | 28035.9375
1646 | B3.33 14 13.1 | POTABLE WATER NETWORK: HOPE Pipes 160mm Diameter (Depth O.Om to 1.50m) | 2026-09-01 | SUD1-02-011-TDC-TS9-1-PW-FIR-2357-01 | Inspection Pressure test of Road crossing potable water Pipeline HDPE Pipes(160mm) from STA: +204.25 & ST: +450.99 Road MCG0 | 101.84 | 54.66 | 25% | 25.46 | 1391.6436
1647 | B1.31 22 00.03 | Earth works & Site Grading | 2026-08-25 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2358-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer shoulders (Left and right side) at Road # MCI0, STA: 0+130 to STA: 0+170 | 22.31 | 755.34 | 100% | 22.31 | 16851.6354
1648 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-25 | SUD1-02-011-TDC-TS9-1-STR-FIR-2361-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # FIMH-G2/13 to CB02-22 (S) at Road MCF0 | 377.3 | 26.53 | 45% | 169.785 | 4504.3961
1649 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-25 | SUD1-02-011-TDC-TS9-1-STR-FIR-2362-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # FIMH-G2/10 to CB02-23 (S) at Road MCF0 | 377.3 | 26.79 | 45% | 169.785 | 4548.5401
1650 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400mm | 2026-08-24 | SUD1-02-011-TDC-TS9-1-STR-FIR-2364-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/16/4 to CB-G2/16/4 (D) at Road MCE0 | 602.32 | 3.63 | 10% | 60.232 | 218.6422
1651 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-24 | SUD1-02-011-TDC-TS9-1-STR-FIR-2365-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/16/4 to CB-G2/16/4 B (S) at Road MCE0 | 377.3 | 25.34 | 10% | 37.73 | 956.0782
1652 | B1.31 22 00.05 | Earth works & Site Grading (Subgrade) | 2026-08-25 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2368-00 | Check Coordinates level and Compaction F.D.T for (Subgrade) 2nd layer at Road /Carriageway# # MCF0, STA: 0+400 to STA: 0+600 | 28.13 | 1230.00 | 10% | 2.813 | 3459.99
1653 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-25 | SUD1-02-011-TDC-TS9-1-STR-FIR-2369-00 | Check compaction F.D.T for Trench Backfilling Between Manhole # MH-G2/11/6 to CB-G2/11/6 B (S) at Road MCF0 (Last Layer) | 377.3 | 25.44 | 10% | 37.73 | 959.8512
1654 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-25 | SUD1-02-011-TDC-TS9-1-STR-FIR-2373-00 | Check compaction F.D.T for Trench Backfilling Between Manhole # MH-G2/11/6 to CB-G2/11/6 A (S) at Road MCF0 (Last Layer) | 377.3 | 12.03 | 10% | 37.73 | 453.8919
1655 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-25 | SUD1-02-011-TDC-TS9-1-STR-FIR-2374-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole # MH-G2/11/6 to CB-G2/11/6 C (S) at Road MCF0 (Last Layer) | 377.3 | 26.29 | 45% | 169.785 | 4463.6476
1656 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-25 | SUD1-02-011-TDC-TS9-1-STR-FIR-2375-00 | Check compaction F.D.T for Backfilling of Manhole #CB-G2/11/6 A(S) at Road MCF0 (Bottom subgrade) | 5124.07 | 1 | 10% | 512.407 | 512.407
1657 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-25 | SUD1-02-011-TDC-TS9-1-STR-FIR-2376-00 | Check compaction F.D.T for Backfilling of Manhole #CB-G2/11/6 B(S) at Road MCF0 (Bottom subgrade) | 5124.07 | 1 | 10% | 512.407 | 512.407
1658 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-25 | SUD1-02-011-TDC-TS9-1-STR-FIR-2377-00 | Check compaction F.D.T for Backfilling of Manhole #CB-G2/11/6 C(S) at Road MCF0 (Bottom subgrade) | 5124.07 | 1 | 10% | 512.407 | 512.407
1659 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51m to 2.5m) | 2026-08-25 | SUD1-02-011-TDC-TS9-1-STR-FIR-2378-00 | Check Compaction F.D.T for Backfilling of Manhole #MH-G2/11/6 at Road MCF0 (Bottom subgrade) | 12376.13 | 1 | 10% | 1237.613 | 1237.613
1660 | B2.33 71 19.13.02 | Drawpit with medium duty steel cover, size 900x900x1200mm | 2026-08-25 | SUD1-02-011-TDC-TS9-1-LIT-FIR-2379-00 | Check Installation Drawpit MH-09 & MH-10 for Street Lighting in Road MCE0 | 3850.57 | 2 | 30% | 1155.171 | 2310.342
1661 | B1.31 22 00.03 | Earth works & Site Grading | 2026-08-25 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2380-00 | Check Coordinates level and Compaction F.D.T for Shoulder (Right & Left side) Embankments 1st layer at Road # MC20, STA: 5+280 to STA: 5+420 |  | 1728.60 | 0% | 0 | 0
1662 | B2.33 71 19.13.01 | Drawpit with medium duty steel cover, size600x600x1000mm | 2026-08-25 | SUD1-02-011-TDC-TS9-1-LIT-FIR-2381-00 | Check Installation Drawpit MH-03 & MH-06 for Street Lighting in Road MCD0 | 2683.76 | 2 | 30% | 805.128 | 1610.256
1663 | B2.33.71.19.13.05 | Manhole Type 3 | 2026-08-25 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2382-00 | Check Installation Manhole MH-009 & MH-011 for TELECOMMUNICATIONS Works in Road MCE0 | 7057.11 | 2 | 30% | 2117.133 | 4234.266
1664 | B6.33 42 11.29 | STORM WATER NETWORK: GRP Pipes 1200mm (Depth: 2.51-3.50m) | 2026-08-26 | SUD1-02-011-TDC-TS9-1-STR-FIR-2383-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/31 to STA-A1/32 at Road MCB0 | 1423.84 | 54.00 | 10% | 142.384 | 7688.736
1665 | B6.33 42 11.29 | STORM WATER NETWORK: GRP Pipes 1200mm (Depth: 2.51-3.50m) | 2026-08-26 | SUD1-02-011-TDC-TS9-1-STR-FIR-2384-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/31 to STA-A1/30 at Road MCB0 | 1423.84 | 59.35 | 10% | 142.384 | 8450.4904
1666 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-26 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2388-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at PLOT (1), STA: 0+040 to STA: 0+200 | 22.31 | 3434.86 | 100% | 22.31 | 76631.7266
1667 | B6.33 42 11.33 | STORM WATER NETWORK: GRP Pipes 1300mm (Depth: Greater 3.50m) | 2026-08-26 | SUD1-02-011-TDC-TS9-1-STR-FIR-2389-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/30 to STA-A1/29 at Road MCB0 | 1890.37 | 38.65 | 10% | 189.037 | 7306.2801
1668 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: Greater 2.50m) | 2026-08-26 | SUD1-02-011-TDC-TS9-1-STR-FIR-2390-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/32 at Road MCB0 | 30133.35 | 01 | 5% | 1506.6675 | 1506.6675
1669 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: Greater 2.50m) | 2026-08-26 | SUD1-02-011-TDC-TS9-1-STR-FIR-2391-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/31 at Road MCB0 | 30133.35 | 01 | 5% | 1506.6675 | 1506.6675
1670 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: Greater 2.50m) | 2026-08-26 | SUD1-02-011-TDC-TS9-1-STR-FIR-2392-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/29 at Road MCB0 | 30133.35 | 01 | 5% | 1506.6675 | 1506.6675
1671 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-08-26 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2393-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 040 To 054 in Road MCH0 | 617.84 | 28.91 | 25% | 154.46 | 4465.4386
1672 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-08-26 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2394-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 041 To 042 in Road MCH0 | 617.84 | 25.40 | 25% | 154.46 | 3923.284
1673 | B3.33 14 13.1 | POTABLE WATER NETWORK: HDPE Pipes 160mm Diameter (Depth 0.0m to 1.50m) | 2026-08-26 | SUD1-02-011-TDC-TS9-1-PW-FIR-2396-00 | Check Coordinates level and Excavation width Bottom level and compaction for Road crossing potable water HDPE pipelines from 4+811.60 (R)to4+811.60 (L), 5+263.35 (R)to5+263.35 (L), 5+811.7 (R)to5+811.7 (L) at Road MC20 | 101.84 | 106.76 | 10% | 10.184 | 1087.2438
1674 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0.0m - 1.5m) | 2026-08-26 | SUD1-02-011-TDC-TS9-1-IRR-FIR-2397-00 | Check Excavation for Road crossing 125mm O.D HDPE Pipes at 4+905.5 (R) to 4+905.5 (L) Road MC20 | 82.44 | 41.39 | 10% | 8.244 | 341.2192
1675 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-26 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2401-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Plot (5) STA: 0+150 to STA: 0+270 | 22.31 | 1064.03 | 100% | 22.31 | 23738.5093
1676 | B1.31 22 00.05 | Earth works & Site Grading (Subgrade) | 2026-08-26 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2402-00 | Check Coordinates level and Compaction F.D.T for (Subgrade) 2nd layer at Road /Carriageway# # MCF0, STA: 0+300 to STA: 0+400 | 28.13 | 615.00 | 10% | 2.813 | 1729.995
1677 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: Greater 2.50m) | 2026-08-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-2404-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/30 at Road MCB0 | 30133.35 | 01 | 10% | 3013.335 | 3013.335
1678 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-08-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-2408-00 | Check compaction F.D.T for Backfilling of #CB-G2/6/6 B (S) at Road MCG0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1679 | B6.33 42 11.13 | STORM WATER NETWORK: GRP Pipes 700mm Diameter (Depth:1.51 to 2.50m) | 2026-08-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-2409-00 | Check compaction F.D.T for Trench Backfilling 1st layer Between Manhole # MH-G2/11/4 to FMH-A2/9/20-399 at Road MCF0 (Bottom Subgrade) | 544.12 | 44.00 | 10% | 54.412 | 2394.128
1680 | B6.33 42 11.16 | STORM WATER NETWORK: GRP 800m Pipes (Depth 1.51 - 2.50m) | 2026-08-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-2410-00 | Check compaction F.D.T for Trench Backfilling 1st layer Between Manhole MH-G2/11/3 to MH-G2/11/4 at Road MCF0 (Bottom Subgrade) | 639.17 | 89.50 | 10% | 63.917 | 5720.5715
1681 | B6.33 42 11.10 | STORM WATER NETWORK: GRP Pipes 600mm Diameter (Depth: 1.51 to 2.50m) | 2026-08-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-2411-00 | Check compaction F.D.T for Trench Backfilling 1st layer Between Manhole # FMH-A2/9/20-399 to MH-G2/11/5 at Road MCF0 (Bottom Subgrade) | 461.68 | 44.16 | 10% | 46.168 | 2038.7789
1682 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-2412-00 | Inspection Gravity and Leakage test pipeline from Manhole # CB02-23 (S) to CB/G2/10 at Road MCF0 | 377.3 | 26.79 | 10% | 37.73 | 1010.7867
1683 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-2413-00 | Inspection Gravity and Leakage test pipeline from Manhole # CB02-22 (S) to FIMH-G2/13 at Road MCF0 | 377.3 | 26.53 | 10% | 37.73 | 1000.9769
1684 | B6.33 42 11.7 | STORM WATER NETWORK: Manhole FOR GRP Pipes 500mm (Depth: 1.51 to 2.50m) | 2026-08-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-2414-00 | Check compaction F.D.T for Trench Backfilling 1st layer Between Manhole # MH-G2/11/5 to FMH-A20/9/20-397 at Road MCF0 (Bottom Subgrade) | 379.24 | 44.27 | 10% | 37.924 | 1678.8955
1685 | B6.33 42 11.4 | STORM WATER NETWORK: GRP Pipes 400mm (Depth: 1.51m - 2.5m) | 2026-08-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-2415-00 | Check compaction F.D.T for Trench Backfilling 1st layer Between Manhole # FMH-A20/9/20-397 to MH-G2/11/6 at Road MCF0 (Bottom Subgrade) | 312.31 | 44.27 | 10% | 31.231 | 1382.5964
1686 | B6.33 42 11.4 | STORM WATER NETWORK: GRP Pipes 400mm (Depth: 1.51m - 2.5m) | 2026-08-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-2416-00 | Check compaction F.D.T for Trench Backfilling 1st layer Between Manhole # MH-G2/11/6 to MH-G2/11/7 at Road MCF0 (Bottom Subgrade) | 312.31 | 40.30 | 10% | 31.231 | 1258.6093
1687 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-08-27 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2419-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 086 To 087 in Road MCC0 | 617.84 | 24.89 | 25% | 154.46 | 3844.5094
1688 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-08-31 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2420-01 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 088 To 089 in Road MCC0 | 617.84 | 25.85 | 25% | 154.46 | 3992.791
1689 | B2.33 71 19.01 | Road crossing ducts, 2 ways (2 x 150mm PVC) | 2026-08-31 | SUD1-02-011-TDC-TS9-1-LIT-FIR-2421-01 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (2X160mm) from Manhole 75 To Manhole 76 for Street Lighting Duct Bank in Road MCC0 | 308.43 | 15.62 | 25% | 77.1075 | 1204.4191
1690 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-2423-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # CB-G2/16 (S) to FIMH-G2/16 at Road MCE0 | 377.3 | 43.80 | 45% | 169.785 | 7436.583
1691 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400mm | 2026-08-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-2424-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # MH-G2/16/1 to CB-G2/16/1 (D) at Road MCE0 | 602.32 | 5.86 | 45% | 271.044 | 1588.3178
1692 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400mm | 2026-08-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-2425-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # MH-G2/16/2 to CB-G2/16/2 (D) at Road MCE0 | 602.32 | 5.04 | 45% | 271.044 | 1366.0618
1693 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-2426-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # MH-G2/16/2 to CB-G2/16/2 B (S) at Road MCE0 | 377.3 | 23.36 | 45% | 169.785 | 3966.1776
1694 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400mm | 2026-08-27 | SUD1-02-011-TDC-TS9-1-STR-FIR-2427-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # MH-G2/16/3 to CB-G2/16/3 (D) at Road MCE0 | 602.32 | 4.25 | 45% | 271.044 | 1151.937
1695 | B3.33 14 19.01 |  | 2026-08-29 | SUD1-02-011-TDC-TS9-1-PW-FIR-2429-00 | Check Coordinates level and installation of Buried Gate Valves diameter 150mm for potable water line at Road MCG0 | 7802.97 | 2 | 0% | 0 | 0
1696 | B3.33 14 19.02 | POTABLE WATER NETWORK: installation of Buried Gate Valves | 2026-08-29 | SUD1-02-011-TDC-TS9-1-PW-FIR-2430-00 | Check Coordinates level and installation of Buried Gate Valves diameter 200mm for potable water line at Road MCG0 | 10933.86 | 3 | 30% | 3280.158 | 9840.474
1697 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-29 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2435-00 | Check Coordinates level and Compaction F.D.T for Embankment 8th layer at PLOT (3), STA: 0+050 to STA: 0+160 | 22.31 | 4047.03 | 100% | 22.31 | 90289.2393
1698 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Depth 0m to 1.5m) | 2026-08-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2437-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-1-81 to MH-1-80 at Road MCA0 | 212.41 | 98.80 | 10% | 21.241 | 2098.6108
1699 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-2438-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # MH-G2/16/5 to CB-G2/16/5 B (S) at Road MCE0 | 377.3 | 26.49 | 45% | 169.785 | 4497.6046
1700 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Depth 0m to 1.5m) | 2026-08-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2445-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-13-5 to MH-12-13-4 at Road MCF0 | 212.41 | 98.71 | 45% | 95.5845 | 9435.146
1701 | B6.33 42 11.3 | STORM WATER NETWORK: GRP Pipes 400mm (Depth: 0m - 1.5m) | 2026-08-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-2446-00 | Check compaction F.D.T for Trench Backfilling Between # MH-G2/6/6 to MH-G2/6/7 at Road MCG0 (Last Layer) | 300.67 | 44.79 | 10% | 30.067 | 1346.7009
1702 | B6.33 42 11.7 | STORM WATER NETWORK: Manhole FOR GRP Pipes 500mm (Depth: 1.51 to 2.50m) | 2026-08-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-2447-00 | Check compaction F.D.T for Trench Backfilling Between # FMH-A2/9/20-396 to MH-G2/6/5 at Road MCG0 (Last Layer) | 379.24 | 44.24 | 10% | 37.924 | 1677.7578
1703 | B6.33 42 11.3 | STORM WATER NETWORK: GRP Pipes 400mm (Depth: 0m - 1.5m) | 2026-08-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-2448-00 | Check compaction F.D.T for Trench Backfilling Between # MH-G2/6/6 to FMH-A2/9/20-396 at Road MCG0 (Last Layer) | 300.67 | 39.24 | 10% | 30.067 | 1179.8291
1704 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-2449-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # CB01-19 to FIMH-G2/16 at Road MCE0 | 377.3 | 22.78 | 45% | 169.785 | 3867.7023
1705 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm | 2026-08-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-2450-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # CB-G2/16/5 (D) to CB-G2/16/5 A (S) at Road MCE0 | 377.3 | 28.80 | 45% | 169.785 | 4889.808
1706 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400mm | 2026-08-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-2451-00 | Check Sand Bedding and UPVC Pipe Installation for Storm water line from # MH-G2/16/5 to CB-G2/16/5 (D) at Road MCE0 | 602.32 | 3.56 | 45% | 271.044 | 964.9166
1707 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-2452-00 | Check compaction F.D.T for Backfilling of Manhole #MH-G2/11/7 at Road MCF0 (Bottom subgrade) | 12376.13 | 1 | 10% | 1237.613 | 1237.613
1708 | B6.33 05 39.3 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: > 2.5m) | 2026-08-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-2453-00 | Check compaction F.D.T for Backfilling of Manhole #FMH­A2/9/20-397at Road MCF0 (Bottom subgrade) | 15848.43 | 1 | 10% | 1584.843 | 1584.843
1709 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-31 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2454-00 | Check Coordinates level and Compaction F.D.T for Embankment 17th layer at PLOT (5), STA: 0+360 to STA: 0+400 | 22.31 | 331.79 | 100% | 22.31 | 7402.2349
1710 | B1.31 22 00.04 | Earth works & Site Grading | 2026-08-31 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2455-00 | Check Coordinates level and Compaction F.D.T for Embankment 15th layer at PLOT (5), STA: 0+224 to STA: 0+360 | 22.31 | 2030.75 | 100% | 22.31 | 45306.0325
1711 | B1.31 22 00.05 | Earth works & Site Grading (Subgrade) | 2026-08-30 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2456-00 | Check Coordinates level and Compaction F.D.T for (Subgrade) 2nd layer at Road /Carriageway# MCG0, STA: 0+240 to STA: 0+410 | 10 | 1003.83 | 10% | 1 | 1003.83
1712 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-31 | SUD1-02-011-TDC-TS9-1-STR-FIR-2457-00 | Inspection Gravity and Leakage test pipeline from Manhole # CB-G2/16 (S) to FIMH-G2/16 at Road MCE0 | 377.3 | 22.91 | 10% | 37.73 | 864.3943
1713 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes with DIA 400mm for Catch Basin | 2026-08-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-2458-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/16/1 to CB-G2/16/1 (D) at Road MCE0 | 602.32 | 5.86 | 10% | 60.232 | 352.9595
1714 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes with DIA 400mm for Catch Basin | 2026-08-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-2459-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/16/2 to CB-G2/16/2 (D) at Road MCE0 | 602.32 | 5.04 | 10% | 60.232 | 303.5693
1715 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-2460-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/16/2 to CB-G2/16/2 B (S) at Road MCE0 | 377.3 | 23.36 | 10% | 37.73 | 881.3728
1716 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes with DIA 400mm for Catch Basin | 2026-08-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-2461-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/16/3 to CB-G2/16/3 (D) at Road MCE0 | 602.32 | 4.25 | 10% | 60.232 | 255.986
1717 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-2462-00 | Inspection Gravity and Leakage test pipeline from Manhole # CB-G2/16/5 (D) to CB-G2/16/5 A (S) at Road MCE0 | 377.3 | 28.80 | 10% | 37.73 | 1086.624
1718 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes with DIA 400mm for Catch Basin | 2026-08-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-2463-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/16/5 to CB-G2/16/5 (D) at Road MCE0 | 602.32 | 3.56 | 10% | 60.232 | 214.4259
1719 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-08-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-2464-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-G2/16/5 to CB-G2/16/5 B (S) at Road MCE0 | 377.3 | 26.49 | 10% | 37.73 | 999.4677
1720 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Depth 0m to 1.5m) | 2026-08-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2465-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-19-1 to MH-12-19-1-1 at Road MCE0 | 212.41 | 78.87 | 10% | 21.241 | 1675.2777
1721 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-08-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2466-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-13-1-1 to MH-12-13-1-2 at Road MCF0 | 212.41 | 98.86 | 10% | 21.241 | 2099.8853
1722 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-08-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2467-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-13-1 to MH-12-13-1-1 at Road MCF0 | 212.41 | 78.87 | 10% | 21.241 | 1675.2777
1723 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-08-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2468-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-13-1-2 to MH-12-13-1-3 at Road MCF0 | 212.41 | 98.74 | 10% | 21.241 | 2097.3363
1724 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Depth 0m to 1.5m) | 2026-08-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2469-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-19-1-2 MH-12-19-1-1at Road MCE0 | 212.41 | 98.86 | 10% | 21.241 | 2099.8853
1725 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Depth 0m to 1.5m) | 2026-08-29 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2470-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-19-1-3 to MH-12-19-1-2 at Road MCE0 | 212.41 | 98.74 | 10% | 21.241 | 2097.3363
1726 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-2472-00 | Check compaction F.D.T for Backfilling of # CB-G2/6/6 B (S) MH-G2/6/6 at Road MCG0 (Last layer) | 377.3 | 29.11 | 10% | 37.73 | 1098.3203
1727 | B1.31 22 00.05 | Earth works & Site Grading (Subgrade) | 2026-08-31 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2473-00 | Check Coordinates level and Compaction F.D.T for (Subgrade) 2nd layer at Road /Carriageway# MCF0, STA: 0+224 to STA: 0+300 | 28.13 | 459.11 | 10% | 2.813 | 1291.4764
1728 | B2.33 71 19.02 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 043 To 044 in Road MCH0 | 2026-08-30 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2474-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 043 To 044 in Road MCH0 | 617.84 | 26.71 | 25% | 154.46 | 4125.6266
1729 | B2.33.71.19.13.04 | Check Installation Manhole MH-001 & MH-002 & MH-003 for TELECOMMUNICATIONS Works in Existing RD | 2026-08-30 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2475-00 | Check Installation Manhole MH-001 & MH-002 & MH-003 for TELECOMMUNICATIONS Works in Existing RD | 7042.56 | 3 | 30% | 2112.768 | 6338.304
1730 | B3.33 14 13.3 | POTABLE WATER NETWORK: HDPE Pipes 225 Diameter (Depth 0 to 1.50m) | 2026-08-30 | SUD1-02-011-TDC-TS9-1-PW-FIR-2477-00 | Check Sand bedding and pipe installation of potable water HDPE Pipes(225mm) at ST: +625.00 to ST: +000.00 Road MCF0 | 179.43 | 625.00 | 45% | 80.7435 | 50464.6875
1731 | B5.33 31 00.01 | SEWER NETWORK: GRP Pipes 200mm (Manhole Depth 0- 1.5m) | 2026-08-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2486-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-1-93-4 to MH-1-93-3 at Road MCC0 | 212.41 | 78.87 | 10% | 21.241 | 1675.2777
1732 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-31 | SUD1-02-011-TDC-TS9-1-STR-FIR-2487-00 | Inspection Gravity and Leakage test pipeline from Manhole # CB01-19 to FIMH-G2/16 at Road MCE0 | 377.3 | 22.78 | 10% | 37.73 | 859.4894
1733 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-31 | SUD1-02-011-TDC-TS9-1-STR-FIR-2501-00 | Check compaction F.D.T for Trench Backfilling 1st layer Between Manhole # CB-G2/16/1 B (S) to MH-G2/16/1 at Road MCE0 (Bottom Subgrade) | 377.3 | 22.38 | 10% | 37.73 | 844.3974
1734 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400mm for Catch Basin | 2026-09-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-2502-00 | Check compaction F.D.T for Trench Backfilling 1st layer Between Manhole # MH-G2/16/1 to CB-G2/16/1 (D) at Road MCE0 (Bottom Subgrade) | 602.32 | 5.86 | 10% | 60.232 | 352.9595
1735 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-31 | SUD1-02-011-TDC-TS9-1-STR-FIR-2503-00 | Check compaction F.D.T for Trench Backfilling 1st layer Between Manhole # CB-G2/16/1 (D) to CB-G2/16/1 A(S) at Road MCE0 (Bottom Subgrade) | 377.3 | 28.80 | 10% | 37.73 | 1086.624
1736 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-09-21 | SUD1-02-011-TDC-TS9-1-STR-FIR-2504-00 | Check compaction F.D.T for Trench Backfilling 1st layer Between Manhole # MH-G2/16/2 to CB-G2/16/2 B (S) at Road MCE0 (Bottom Subgrade) | 377.3 | 23.36 | 10% | 37.73 | 881.3728
1737 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400mm for Catch Basin | 2026-09-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-2505-00 | Check compaction F.D.T for Trench Backfilling 1st layer Between Manhole # MH-G2/16/2 to CB-G2/16/2 (D) at Road MCE0 (Bottom Subgrade) | 602.32 | 5.04 | 10% | 60.232 | 303.5693
1738 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-08-31 | SUD1-02-011-TDC-TS9-1-STR-FIR-2506-00 | Check compaction F.D.T for Trench Backfilling 1st layer Between Manhole # CB-G2/16/2 A (S) to CB-G2/16/2 (D)at Road MCE0 (Bottom Subgrade) | 377.3 | 24.14 | 10% | 37.73 | 910.8022
1739 | B6.33 05 39.9 | STORM WATER NETWORK: 2000mm Diameter (Depth:> 2.5m) | 2026-08-31 | SUD1-02-011-TDC-TS9-1-STR-FIR-2507-00 | Check compaction F.D.T for Backfilling 1st layer Manhole # MH -G2/16/1 at Road MCE0 (Bottom Subgrade) | 30133.35 | 01 | 10% | 3013.335 | 3013.335
1740 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-31 | SUD1-02-011-TDC-TS9-1-STR-FIR-2508-00 | Check compaction F.D.T for Backfilling 1st layer CB-G2/16/1 B (S) at Road MCE0 (Bottom Subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1741 | B6.33 05 39.16 | STORM WATER NETWORK: Catch Basin Double | 2026-08-31 | SUD1-02-011-TDC-TS9-1-STR-FIR-2509-00 | Check compaction F.D.T for Backfilling 1st layer # CB-G2/16/1 (D) at Road MCE0 (Bottom Subgrade) | 12444.99 | 01 | 10% | 1244.499 | 1244.499
1742 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-31 | SUD1-02-011-TDC-TS9-1-STR-FIR-2510-00 | Check compaction F.D.T for Backfilling 1st layer # CB-G2/16/1 A (S) at Road MCE0 (Bottom Subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1743 | B6.33 05 39.9 | STORM WATER NETWORK: 2000mm Diameter (Depth:> 2.5m) | 2026-08-31 | SUD1-02-011-TDC-TS9-1-STR-FIR-2511-00 | Check compaction F.D.T for Backfilling 1st layer # MH -G2/16/2 at Road MCE0 (Bottom Subgrade) | 30133.35 | 01 | 10% | 3013.335 | 3013.335
1744 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-31 | SUD1-02-011-TDC-TS9-1-STR-FIR-2512-00 | Check compaction F.D.T for Backfilling 1st layer # CB-G2/16/2 B (S) at Road MCE0 (Bottom Subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1745 | B6.33 05 39.16 | STORM WATER NETWORK: Catch Basin Double | 2026-08-31 | SUD1-02-011-TDC-TS9-1-STR-FIR-2513-00 | Check compaction F.D.T for Backfilling 1st layer # CB-G2/16/2 (D)at Road MCE0 (Bottom Subgrade) | 12444.99 | 01 | 10% | 1244.499 | 1244.499
1746 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-08-31 | SUD1-02-011-TDC-TS9-1-STR-FIR-2514-00 | Check compaction F.D.T for Backfilling 1st layer # CB-G2/16/2 A (S) at Road MCE0 (Bottom Subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1747 | B1.32 14 13.02 | Installation Curbstone L1 | 2026-09-01 | SUD1-02-011-TDC-TS9-1-LSP-FIR-2517-00 | Installation of Curbstone L1 including backing concrete STA 0+340 to 0+540 (MODON Landscape Area) | 425.18 | 425.18 | 30% | 127.554 | 54233.4097
1748 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-09-01 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2519-00 | Check Sand Bedding and Installation HDPE Pipe 3(2X50mm) From Manhole 001 To 002 for TELECOMMUNICATIONS Works in Existing RD | 617.84 | 119.30 | 45% | 278.028 | 33168.7404
1749 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0.00 - 1.5m) | 2026-08-31 | SUD1-02-011-TDC-TS9-1-IRR-FIR-2428-00 | Check Excavation for Road crossing 125mm O.D HDPE Pipes at 5+759 (R) to 5+759 (L) #Road MC20 | 179.43 | 41.39 | 10% | 17.943 | 742.6608
1750 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0.0m - 1.5m) | 2026-09-07 | SUD1-02-011-TDC-TS9-1-IRR-FIR-2523-00 | Check Compaction F.D.T for Backfilling 1st layer for Road crossing 125mm O.D HDPE Pipes at Road MCE0 (Attached three Locations) (Bottom Subgrade) | 82.44 | 94.48 | 10% | 8.244 | 778.8931
1751 | B3.33 14 13.1 | POTABLE WATER NETWORK: HDPE Pipes 160mm Diameter (Depth 0.0m to 1.50m) | 2026-09-07 | SUD1-02-011-TDC-TS9-1-PW-FIR-2524-00 | Check Compaction F.D.T for Backfilling 1st layer for Road 2 crossing potable water HDPE pipelines (Diameter 160mm) at Road MCE0 (Bottom Subgrade) | 101.84 | 68.06 | 10% | 10.184 | 693.123
1752 | B1.32 11 23.01 | AGGREGATE BASE COURSE | 2026-09-01 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2525-00 | Check Coordinates level and compaction F.D.T for (Aggregate base course) 2nd layer at Road /Carriageway# MCG0, STA: 0+650 to STA: 0+790 | 62.07 | 532.50 | 10% | 6.207 | 3305.2275
1753 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-01 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2526-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at PLOT (1), STA: 0+200 to STA: 0+400 | 22.31 | 5128.31 | 100% | 22.31 | 114412.5961
1754 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-01 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2527-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at PLOT (1), STA: 0+400 to STA: 0+610 | 22.31 | 5803.10 | 100% | 22.31 | 129467.161
1755 | B5 33.05.13.03 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 1.51-2.50m) | 2026-09-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2530-00 | Check Installation of Manhole Base (Rings not required) MH-1-88-2 at Road MCD0. | 12377.1 | 01 | 30% | 3713.13 | 3713.13
1756 | B5 33.05.13.03 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 1.51-2.50m) | 2026-09-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2531-00 | Check Installation of Manhole Base (Rings not required) MH-12-19-4 at Road MCE0. | 12377.1 | 01 | 30% | 3713.13 | 3713.13
1757 | B5 33.05.13.01 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 0-1.50m) | 2026-09-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2532-00 | Check Installation of Manhole Base (Rings not required) MH-12-19-5 at Road MCE0. | 8820.42 | 01 | 30% | 2646.126 | 2646.126
1758 | B1.31 22 00.01 | Earth works & Site Grading/cutting | 2026-09-01 | SUD1-02-011-TDC-TS9-1-LSP-FIR-2533-00 | Check Coordinates level and Compaction F.D.T for cutting Grading level for bottom of replacement soil (MODON Landscape Area) at # STA:0+000 to STA:0+120 | 13.58 | 1312.12 | 10% | 1.358 | 1781.859
1759 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-09-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-2534-00 | Check compaction F.D.T for Trench Backfilling Between Manhole #CB-G2/16/3 A (S) to CB-G2/16/3 (D) at Road MCE0 (Bottom subgrade) | 377.3 | 28.85 | 10% | 37.73 | 1088.5105
1760 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-09-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-2535-00 | Check compaction F.D.T for Backfilling of # CB-G2/16/3 A (S) at Road MCE0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1761 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Depth 0m to 1.5m) | 2026-09-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2537-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-21-3 to MH-12-21-2 at Road MCD0 | 212.41 | 78.85 | 10% | 21.241 | 1674.8528
1762 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Depth 0m to 1.5m) | 2026-09-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2538-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-1-88-5 to MH-1-88-4 at Road MCD0 | 212.41 | 98.74 | 10% | 21.241 | 2097.3363
1763 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Depth 0m to 1.5m) | 2026-09-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2539-00 | Inspection Gravity and Leakage test pipeline from Manhole # , MH-1-88-4 to MH-1-88-3 at Road MCD0 | 212.41 | 96.68 | 10% | 21.241 | 2053.5799
1764 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-09-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-2540-00 | Check compaction F.D.T for Trench Backfilling Between Manhole #CB-G2/16/3 B (S) to MH-G2/16/3 at Road MCE0 (Bottom subgrade) | 377.3 | 24.34 | 10% | 37.73 | 918.3482
1765 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400mm for Catch Basin | 2026-09-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-2541-00 | Check compaction F.D.T for Trench Backfilling Between Manhole # MH-G2/16/3 to CB-G2/16/3 (D)at Road MCE0 (Bottom subgrade) | 602.32 | 4.25 | 10% | 60.232 | 255.986
1766 | B6.33 05 39.16 | STORM WATER NETWORK: Catch Basin Double | 2026-09-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-2542-00 | Check compaction F.D.T for Backfilling of # CB-G2/16/3 (D) at Road MCE0 (Bottom subgrade) | 12444.99 | 01 | 10% | 1244.499 | 1244.499
1767 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: > 2.5m) | 2026-09-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-2543-00 | Check compaction F.D.T for Backfilling of # MH -G2/16/3 at Road MCE0 (Bottom subgrade) | 30133.35 | 01 | 10% | 3013.335 | 3013.335
1768 | B3.33 14 13.5 | POTABLE WATER NETWORK: HDPE Pipes 315 Diameter (Depth 0 to 1.50m) | 2026-09-02 | SUD1-02-011-TDC-TS9-1-PW-FIR-2545-00 | Check Coordinates level and Excavation width Bottom level and compaction for potable water pipeline from Station STA: 1+450 TO 1+650, STA:1+925 TO 2+650, at Road MC20 | 290.97 | 925 | 5% | 14.5485 | 13457.3625
1769 | B1.31 22 00.01 | Earth works & Site Grading (Road Excavation/cutting) | 2026-09-02 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2546-00 | Check Coordinates and bottom level Road Excavation/cutting upto bottom of Sub-Grade from STA: 0+807.40 to STA: 0 +826.77 at Road # MCG0 | 13.58 | 803.37 | 10% | 1.358 | 1090.9765
1770 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-08 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2547-00 | Check Coordinates level and Compaction F.D.T for Embankment 16th layer at PLOT (5), STA: 0+250 to STA: 0+330 | 0 | 577.94 | 0%
1771 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-09-02 | SUD1-02-011-TDC-TS9-1-STR-FIR-2548-00 | Check compaction F.D.T for Trench Backfilling Between Manhole # CB02-23 (S) to FIMH-G2/10 at Road MCF0 (Last Layer) | 377.3 | 26.79 | 10% | 37.73 | 1010.7867
1772 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-09-02 | SUD1-02-011-TDC-TS9-1-STR-FIR-2549-00 | Check compaction F.D.T for Trench Backfilling Between Manhole # CB02-22 (S) to FIMH-G2/13 at Road MCF0 (Last Layer) | 377.3 | 26.53 | 10% | 37.73 | 1000.9769
1773 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-09-02 | SUD1-02-011-TDC-TS9-1-STR-FIR-2552-00 | Check Installation of catch basin CB01-19 include the connecting pipe opening at Road MCE0 | 5124.07 | 1.00 | 30% | 1537.221 | 1537.221
1774 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-09-02 | SUD1-02-011-TDC-TS9-1-STR-FIR-2553-00 | Check Installation of catch basin CB02-22(S) include the connecting pipe opening at Road MCF0 | 5124.07 | 1.00 | 30% | 1537.221 | 1537.221
1775 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-09-02 | SUD1-02-011-TDC-TS9-1-STR-FIR-2554-00 | Check Installation of catch basin CB02-23(S) include the connecting pipe opening at Road MCF0 | 5124.07 | 1.00 | 30% | 1537.221 | 1537.221
1776 | B2.33 71 19.02 | Road crossing ducts, 4 ways (4 x 150mm PVC) | 2026-09-02 | SUD1-02-011-TDC-TS9-1-LIT-FIR-2555-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (4X160mm) from Manhole 73 To Manhole 74 for Street Lighting Duct Bank in Road MCA0 | 617.84 | 16.71 | 25% | 154.46 | 2581.0266
1777 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-09-02 | SUD1-02-011-TDC-TS9-1-STR-FIR-2558-00 | Check compaction F.D.T for Backfilling of # CB-G2/16/3 B (S) at Road MCE0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1778 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-08 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2559-01 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at Plot (3) STA: 0+0250 to STA: 0+310 | 22.31 | 686.51 | 100% | 22.31 | 15316.0381
1779 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-08 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2560-01 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer at Plot (3) STA: 0+0310 to STA: 0+467 | 0 | 2593.58 | 0% | 0 | 0
1780 | B1.31 22 00.01 | Earth works & Site Grading (Road Excavation/cutting) | 2026-09-02 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2561-00 | Check Coordinates and bottom level Road Excavation/cutting upto bottom of Sub-Grade STA: 0+770 to STA: 0+826.79 at Road # MCF0 | 13.58 | 1294.89 | 10% | 1.358 | 1758.4606
1781 | B5 33.05.13.03 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 1.51-2.50m) | 2026-09-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2565-00 | Check Installation of Manhole Base MH-12-18 at Road MCB0. | 12377.1 | 01 | 30% | 3713.13 | 3713.13
1782 | B3.33 14 13.1 | POTABLE WATER NETWORK: HDPE Pipes 160mm Diameter (Depth 0.0m to 1.50m) | 2026-09-02 | SUD1-02-011-TDC-TS9-1-PW-FIR-2567-00 | Check Coordinates level and Excavation width Bottom level and compaction for Road crossing potable water HDPE pipelines at Road MC10 #STA:2+952.5 (R) & STA 2+952.5 (L) | 101.84 | 52.00 | 10% | 10.184 | 529.568
1783 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0.0m - 1.5m) | 2026-09-10 | SUD1-02-011-TDC-TS9-1-IRR-FIR-2568-01 | Check Excavation for Road crossing 125mm O.D HDPE Pipes at 2+957.5 (R) to 2+957.5 (L) #Road MC10 | 82.44 | 54.00 | 5% | 4.122 | 222.588
1784 | B6.33 42 11.6 | STORM WATER NETWORK: GRP Pipes 500mm (Depth: 0.0m - 1.5m) | 2026-09-02 | SUD1-02-011-TDC-TS9-1-STR-FIR-2569-00 | Check Coordinates level and Excavation width Bottom level and compaction(Road Crossing) for Storm Water pipeline trench from Manhole # STA-SW/A1/8/8 to STA-T/A1/8/9 at Road MC20 | 366.63 | 109.24 | 0% | 0 | 0
1785 | B2.33 71 19.13.01 | Drawpit with medium duty steel cover, size600x600x1000mm | 2026-09-02 | SUD1-02-011-TDC-TS9-1-LIT-FIR-2572-00 | Check Installation Drawpit MH-08 for Street Lighting in Road MCE0 | 2683.76 | 1 | 30% | 805.128 | 805.128
1786 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-19 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2573-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-21-1 to MH-12-21-2 at Road MCD0 | 212.41 | 31.10 | 0% | 0 | 0
1787 | B5 33 05 13.05 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 2.51-3.50) | 2026-09-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2574-00 | Check Installation of Manhole Base MH-12-12 at Road MCB0 | 15848.43 | 01 | 30% | 4754.529 | 4754.529
1788 | B5 33 05 13.05 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 2.51-3.50) | 2026-09-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2575-00 | Check Installation of Manhole Base MH-12-16 at Road MCI0. | 15848.43 | 01 | 30% | 4754.529 | 4754.529
1789 | B5 33.05.13.06 | SEWERAGE NETWORK: Manhole (Depth 2.51m to 3.5m) Internal Diameter (1200mm) With Backdrop | 2026-09-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2576-00 | Check Installation of Manhole Base MH-12-11 at Road MCB0. | 19018.11 | 01 | 30% | 5705.433 | 5705.433
1790 | B1.32 11 23.01 | AGGREGATE BASE COURSE | 2026-09-03 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2577-00 | Check Coordinates level and compaction F.D.T for (Aggregate base course) 2nd layer at Road /Carriageway# MCG0, STA: 0+450 to STA: 0+650 | 62.07 | 790.00 | 10% | 6.207 | 4903.53
1791 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-09-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-2583-00 | Check compaction F.D.T for Trench Backfilling Between Manhole # CB-G2/16/4 A (S) to CB-G2/16/4 (D) at Road MCE0 (Bottom subgrade) | 377.3 | 28.80 | 10% | 37.73 | 1086.624
1792 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400mm for Catch Basin | 2026-09-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-2584-00 | Check compaction F.D.T for Trench Backfilling Between Manhole # MH-G2/16/4 to CB-G2/16/4 (D) at Road MCE0 (Bottom subgrade) | 602.32 | 3.63 | 25% | 150.58 | 546.6054
1793 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-09-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-2585-00 | Check compaction F.D.T for Backfilling of # CB-G2/16/4 A (S) at Road MCE0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1794 | B6.33 05 39.16 | STORM WATER NETWORK: Catch Basin Double | 2026-09-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-2586-00 | Check compaction F.D.T for Backfilling of # CB-G2/16/4 (D) at Road MCE0 (Bottom subgrade) | 12444.99 | 01 | 10% | 1244.499 | 1244.499
1795 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: > 2.5m) | 2026-09-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-2587-00 | Check compaction F.D.T for Backfilling of # MH -G2/16/4 at Road MCE0 (Bottom subgrade) | 30133.35 | 01 | 10% | 3013.335 | 3013.335
1796 | B6.33 42 11.22 | STORM WATER NETWORK: GRP Pipes1000mm Diameter (Depth: 1.51m - 2.50m) | 2026-09-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-2588-00 | Check compaction F.D.T for Trench Backfilling Between Manhole # MH-G2/16/2 to MH-G2/16/3 at Road MCE0 (Bottom subgrade) | 884.56 | 87.00 | 10% | 88.456 | 7695.672
1797 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0.0m - 1.5m) | 2026-09-03 | SUD1-02-011-TDC-TS9-1-IRR-FIR-2589-00 | Inspection Gravity and Leakage test of Road crossing Irrigation water HDPE pipes (Diameter 125mm) at ST: +460.28 & ST: +156.39 & +00.00 at Road MCG0 & MCZ0 | 82.44 | 98.39 | 10% | 8.244 | 811.1272
1798 | B1.31 22 00.03 | Earth works & Site Grading | 2026-09-03 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2591-00 | Check Coordinates level and compaction F.D.T for Road Embankment upto bottom of Sub-Grade STA: 0+224 to STA: 0+240 at Road # MCG0 | 22.31 | 151.60 | 100% | 22.31 | 3382.196
1799 | B6.33 42 11.7 | STORM WATER NETWORK: Manhole FOR GRP Pipes 500mm (Depth: 1.51 to 2.50m) | 2026-09-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-2594-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from # STA-A2/24/3 to STA-A2/24/2 at Road MCD0 | 379.24 | 63.80 | 45% | 170.658 | 10887.9804
1800 | B6.33 42 11.3 | STORM WATER NETWORK: GRP Pipes 400mm (Depth: 0m - 1.5m) | 2026-09-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-2595-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from # STA-A2/24/4 TO STA-A2/24/3 at Road MCD0 | 300.67 | 63.80 | 45% | 135.3015 | 8632.2357
1801 | B6.33 42 11.3 | STORM WATER NETWORK: GRP Pipes 400mm (Depth: 0m - 1.5m) | 2026-09-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-2596-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from # STA-A1/40/1 to STA-A1/40/2 at Road MCD0 | 300.67 | 64.34 | 45% | 135.3015 | 8705.2985
1802 | B6.33 42 11.4 | STORM WATER NETWORK: GRP Pipes 400mm (Depth: 1.51m - 2.5m) | 2026-09-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-2597-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from # STA-A1/40/2 to STA-A2/24/4 at Road MCD0 | 312.31 | 63.85 | 45% | 140.5395 | 8973.4471
1803 | B6.33 42 11.10 | STORM WATER NETWORK: Manhole FOR GRP Pipes 600mm (Depth: 1.51m - 2.5m) | 2026-09-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-2598-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from # STA-A2/24/2 to STA-A2/24/1 at Road MCD0 | 461.68 | 63.65 | 45% | 207.756 | 13223.6694
1804 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-09-03 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2599-00 | Check Sand Bedding and Installation HDPE Pipe 3(2X50mm) From Manhole TIE IN CONNECTION To 001 for TELECOMMUNICATIONSWorks in Existing RD | 617.84 | 98.88 | 45% | 278.028 | 27491.4086
1805 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-09-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-2600-00 | Check compaction F.D.T for Backfilling of # CB-G2/16/4 B (S) at Road MCE0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1806 | B5 33.05.13.03 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 1.51-2.50m) | 2026-09-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2601-00 | Check Installation of Manhole Base (Rings not required) MH-12-11-2 at Road MCG0. | 12377.1 | 01 | 30% | 3713.13 | 3713.13
1807 | B5 33.05.13.03 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 1.51-2.50m) | 2026-09-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2602-00 | Check Installation of Manhole Base (Rings not required) MH-12-11-3 at Road MCG0. | 12377.1 | 01 | 30% | 3713.13 | 3713.13
1808 | B5 33.05.13.03 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 1.51-2.50m) | 2026-09-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2603-00 | Check Installation of Manhole Base (Rings not required) MH-12-11-4 at Road MCG0. | 12377.1 | 01 | 30% | 3713.13 | 3713.13
1809 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-09-07 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2604-01 | Check Sand Bedding and Installation HDPE Pipe 3(2X50mm) From Manhole 003 To 004 for TELECOMMUNICATIONS Works in Road MCA0 | 10584.69 | 76.59 | 45% | 4763.1105 | 364806.6332
1810 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-09-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-2605-01 | Check compaction F.D.T for Trench Backfilling Between Manhole # CB03-21 (S) to FMH-G2/8 at Road MCG0 (Bottom subgrade) | 377.3 | 27.69 | 0% | 0 | 0
1811 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-09-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-2606-01 | Check compaction F.D.T for Trench Backfilling Between Manhole # CB03-22 (S) to FMH-G2/5 at Road MCG0 (Bottom subgrade) | 377.3 | 26.29 | 0% | 0 | 0
1812 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-09-07 | SUD1-02-011-TDC-TS9-1-STR-FIR-2607-01 | Check compaction F.D.T for Backfilling of # CB03-21 (S) at Road MCG0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1813 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-09-07 | SUD1-02-011-TDC-TS9-1-STR-FIR-2608-01 | Check compaction F.D.T for Backfilling of # CB03-22 (S) at Road MCG0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1814 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-09-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-2609-00 | Check compaction F.D.T for Backfilling of # CB02-22(S) at Road MCF0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1815 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-09-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-2610-00 | Check compaction F.D.T for Backfilling of # CB02-23(S) at Road MCF0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1816 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-05 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2613-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at PLOT (6), STA: 0+450 to STA: 0+630 | 22.31 | 2372.55 | 100% | 22.31 | 52931.5905
1817 | B2.33 71 19.01 | Road crossing ducts, 2 ways (2 x 150mm PVC) | 2026-09-05 | SUD1-02-011-TDC-TS9-1-LIT-FIR-2615-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (2X160mm) from Manhole 77 To Manhole 78 for Street Lighting Duct Bank in Road MCD0 | 308.43 | 15.62 | 25% | 77.1075 | 1204.4191
1818 | B2.33 71 19.02 | Road crossing ducts, 4 ways (4 x 150mm PVC) | 2026-09-05 | SUD1-02-011-TDC-TS9-1-LIT-FIR-2616-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (4X160mm) from Manhole 61 To Manhole 62 for Street Lighting Duct Bank in Road MCD0 | 617.84 | 17.14 | 25% | 154.46 | 2647.4444
1819 | B2.33 71 19.02 | Road crossing ducts, 4 ways (4 x 150mm PVC) | 2026-09-05 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2617-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 080 To 081 in Road MCD0 | 617.84 | 24.23 | 25% | 154.46 | 3742.5658
1820 | B3.33 14 13.3 | POTABLE WATER NETWORK: HDPE Pipes 160mm Diameter (Depth 0.0m to 1.50m) | 2026-09-13 | SUD1-02-011-TDC-TS9-1-PW-FIR-2623-00 | Check Sand bedding and pipe installation of potable water HDPE Pipes (Diameter 225mm) at STA: ST: +000.00 & ST: 475.00, Road MCE0 | 179.43 | 475.00 | 45% | 80.7435 | 38353.1625
1821 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-09-14 | SUD1-02-011-TDC-TS9-1-STR-FIR-2624-00 | Check compaction F.D.T for Trench Backfilling Between Manhole # CB-G2/16 (S) to FIMH-G2/16 at Road MCE0 (Last Layer) | 525.69 | 22.91 | 10% | 52.569 | 1204.3558
1822 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-05 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2625-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Plot. No:-(7) STA 0+350 to 0+467 | 22.31 | 2727.95 | 100% | 22.31 | 60860.5645
1823 | B4.33 14 13.4 | TSE NETWORK: 125mm Diameter (Depth: >1.5m) | 2026-09-05 | SUD1-02-011-TDC-TS9-1-IRR-FIR-2630-00 | Inspection Gravity and Leakage test of Road crossing Irrigation water HDPE pipe (Diameter 125mm) at ST: +0.00 & ST:+432.1 at Road MCF0 | 86.32 | 30.57 | 10% | 8.632 | 263.8802
1824 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0.0m - 1.5m) | 2026-09-05 | SUD1-02-011-TDC-TS9-1-IRR-FIR-2631-00 | Inspection Gravity and Leakage test of Road crossing Irrigation water HDPE pipe (Diameter 125mm) ST: +389.75& ST: +143.63 at Road MCF0 | 82.44 | 67.09 | 10% | 8.244 | 553.09
1825 | B5.33 31 00.01 | SEWER NETWORK: GRP Pipes 200mm (Manhole Depth: 0- 1.50m) | 2026-09-05 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2633-00 | Check Sand around GRP pipe for sewerage line from Manholes # MH-12-19-4 to MH-12-19-3 at Road MCE0 (Last layer) | 212.41 | 98.86 | 45% | 95.5845 | 9449.4837
1826 | B5.33 31 00.01 | SEWER NETWORK: GRP Pipes 200mm (Manhole Depth: 0- 1.50m) | 2026-09-05 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2634-00 | Check Sand around GRP pipe for sewerage line from Manholes # MH-12-19-5 to MH-12-19-4 at Road MCE0 | 212.41 | 98.74 | 45% | 95.5845 | 9438.0135
1827 | B5.33 31 00.01 | SEWER NETWORK: GRP Pipes 200mm (Manhole Depth: 0- 1.50m) | 2026-09-05 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2635-00 | Check Sand around GRP pipe for sewerage line from Manholes # MH-12-19-1 to MH-12-19-1-1 at Road MCE0 (last layer) | 212.41 | 78.87 | 45% | 95.5845 | 7538.7495
1828 | B5.33 31 00.01 | SEWER NETWORK: GRP Pipes 200mm (Manhole Depth: 0- 1.50m) | 2026-09-05 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2636-00 | Check Sand around GRP pipe for sewerage line from Manholes # MH-12-19-1-2 MH-12-19-1-1 at Road MCE0(last layer) | 212.41 | 98.86 | 45% | 95.5845 | 9449.4837
1829 | B5.33 31 00.01 | SEWER NETWORK: GRP Pipes 200mm (Manhole Depth: 0- 1.50m) | 2026-09-05 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2637-00 | Check Sand around GRP pipe for sewerage line from Manholes # MH-12-19-1-3 to MH-12-19-1-2 at Road MCE0(last layer) | 212.41 | 98.74 | 45% | 95.5845 | 9438.0135
1830 | B1.32 11 23.01 | AGGREGATE BASE COURSE | 2026-09-05 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2639-00 | Check Coordinates level and compaction F.D.T for (Aggregate base course) at Road /Carriageway# MCG0, STA: 0+250 to STA: 0+450 | 212.41 | 768.05 | 10% | 21.241 | 16314.15
1831 | B4.33 14 13.5 | TSE NETWORK: 225mm Diameter (Depth: 0.0m - 1.5m) | 2026-09-05 | SUD1-02-011-TDC-TS9-1-IRR-FIR-2640-00 | Inspection Gravity and Leakage test of Road crossing Irrigation water HDPE pipe (Diameter 125mm) at ST+242.09& ST: +512.88 at Road MCE0 | 179.43 | 24.64 | 10% | 17.943 | 442.1155
1832 | B4.33 14 13.5 | TSE NETWORK: 225mm Diameter (Depth: 0.0m - 1.5m) | 2026-09-05 | SUD1-02-011-TDC-TS9-1-IRR-FIR-2641-00 | Inspection Gravity and Leakage test of Road crossing Irrigation water HDPE pipe (Diameter 125mm) at ST: +461.88 & ST: +536.87 at Road MCF0 | 179.43 | 27.23 | 10% | 17.943 | 488.5879
1833 | B4.33 14 13.5 | TSE NETWORK: 225mm Diameter (Depth: 0.0m - 1.5m) | 2026-09-05 | SUD1-02-011-TDC-TS9-1-IRR-FIR-2642-00 | Inspection Gravity and Leakage test of Road crossing Irrigation water HDPE pipe (Diameter 125mm) at ST: +685.57 & ST: +538.51 at Road MCG0 | 179.43 | 25.69 | 10% | 17.943 | 460.9557
1834 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0.0m - 1.5m) | 2026-09-06 | SUD1-02-011-TDC-TS9-1-IRR-FIR-2646-00 | Check Sand bedding and pipe installation of Road crossing Irrigation water 125mm O.D HDPE Pipes at 4+905.5 (R) to 4+905.5 (L) Road MC20 | 82.44 | 41.39 | 45% | 37.098 | 1535.4862
1835 | B1.32 14 13.02 | Installation Curbstone L1 | 2026-09-06 | SUD1-02-011-TDC-TS9-1-LSP-FIR-2648-00 | Installation of Curbstone L1 including backing concrete STA 0+140 to 0+340 & STA 0+540 to 0+680 (MODON Landscape Area) | 51.41 | 730.64 | 30% | 15.423 | 11268.6607
1836 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-06 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2651-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at PLOT (1), STA: 0+040 to STA: 0+200 | 22.31 | 2679.93 | 100% | 22.31 | 59789.2383
1837 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-05 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2652-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at PLOT (7), STA: 0+240 to STA: 0+350 | 22.31 | 4726.08 | 100% | 22.31 | 105438.8448
1838 | B3.33 14 13.1 | POTABLE WATER NETWORK: HDPE Pipes 160mm Diameter (Depth 0.0m to 1.50m) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-PW-FIR-2653-01 | Check Sand bedding and pipe installation of Road crossing potable water HDPE pipelines (160mm) Diameter from 4+811.60 (R)to4+811.60 (L), 5+263.35 (R)to5+263.35 (L) at Road MC20 (Attaached two locations) | 101.84 | 71.18 | 45% | 45.828 | 3262.037
1839 | B5.33 31 00.01 | SEWER NETWORK: GRP Pipes 200mm (Manhole Depth: 0- 1.50m) | 2026-09-06 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2655-00 | Check Sand around GRP pipe for sewerage line from Manholes # MH-12-13-1-2 to MH-12-13-1-3 at Road MCF0 | 212.41 | 98.74 | 45% | 95.5845 | 9438.0135
1840 | B5.33 31 00.01 | SEWER NETWORK: GRP Pipes 200mm (Manhole Depth: 0- 1.50m) | 2026-09-06 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2656-00 | Check Sand around GRP pipe for sewerage line from Manholes # MH-12-13-1-1 to MH-12-13-1-2 at Road MCF0 | 212.41 | 98.86 | 45% | 95.5845 | 9449.4837
1841 | B5.33 31 00.01 | SEWER NETWORK: GRP Pipes 200mm (Manhole Depth: 0- 1.50m) | 2026-09-06 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2657-00 | Check Sand around GRP pipe for sewerage line from Manholes # MH-12-13-1 to MH-12-13-1-1 at Road MCF0 | 212.41 | 78.87 | 45% | 95.5845 | 7538.7495
1842 | 31 25 00 | Loose Riprap | 2026-09-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-2660-00 | Check inspection for Installation of stone at Pond A | 62.07 | 5139.62 | 30% | 18.621 | 95704.864
1843 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-06 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2661-00 | Check Coordinates level and Compaction F.D.T for Embankment 9th layer at PLOT (3), STA: 0+030 to STA: 0+170 | 22.31 | 3602.09 | 100% | 22.31 | 80362.6279
1844 | B3.33 14 13.1 | POTABLE WATER NETWORK: HDPE Pipes 160mm Diameter (Depth 0.0m to 1.50m) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-PW-FIR-2662-01 | Check Sand bedding and pipe installation of Road crossing potable water HDPE pipelines (160mm) Diameter from 5+811.7 (R)to5+811.7 (L) at Road MC20 | 101.84 | 35.59 | 45% | 45.828 | 1631.0185
1845 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0.0m - 1.5m) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-IRR-FIR-2663-01 | Check Sand bedding and pipe installation of Road crossing 125mm O.D HDPE Pipes at 5+759 (R) to 5+759 (L) #Road MC20 | 179.43 | 41.39 | 45% | 80.7435 | 3341.9735
1846 | B5 33.05.13.01 | SEWERAGE NETWORK: - Manhole Depth (0m to 1.5m) Internal Diameter :-1200mm | 2026-09-06 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2666-00 | Check Installation of Manhole base (Rings not required) MH- 12-19-1-3 at Road MCE0 | 8820.42 | 01 | 30% | 2646.126 | 2646.126
1847 | B1.31 22 00.05 | Earth works & Site Grading (Subgrade) | 2026-09-07 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2669-00 | Check Coordinates level and Compaction F.D.T for (Subgrade) 2nd layer at Road/Carriageway # MCE0, STA: 0+850 to STA: 0+960 | 28.13 | 676.50 | 10% | 2.813 | 1902.9945
1848 | B1.31 22 00.05 | Earth works & Site Grading (Subgrade) | 2026-09-07 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2670-00 | Check Coordinates level and Compaction F.D.T for (Subgrade) 2nd layer at Road/Carriageway # MCF0, STA: 0+770 to STA: 0+826.79 | 28.13 | 607.91 | 10% | 2.813 | 1710.0508
1849 | B5 33.05.13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-09-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2671-00 | Check Installation of Manhole base MH- 12-13-1 at Road MCF0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
1850 | B5 33.05.13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-09-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2672-00 | Check Installation of Flatslab# MH-1-88-3 at Road MCD0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
1851 | B5 33.05.13.01 | SEWERAGE NETWORK: - Manhole Depth ( 0 to 1.5m) Internal Diameter :-1200mm | 2026-09-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2673-00 | Check Installation of Flatslab # MH-1-88-4 at Road MCD0 | 8820.42 | 01 | 30% | 2646.126 | 2646.126
1852 | B5 33.05.13.01 | SEWERAGE NETWORK: - Manhole Depth ( 0 to 1.5m) Internal Diameter :-1200mm | 2026-09-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2674-00 | Check Installation of Flatslab# MH-1-88-5 at Road MCD0 | 8820.42 | 01 | 30% | 2646.126 | 2646.126
1853 | B5 33.05.13.01 | SEWERAGE NETWORK: - Manhole Depth ( 0 to 1.5m) Internal Diameter :-1200mm | 2026-09-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2675-00 | Check Installation of Flatslab # MH-12-21-3 at Road MCD0 | 8820.42 | 01 | 30% | 2646.126 | 2646.126
1854 | B6.33 05 39.9 | SEWERAGE NETWORK: - Manhole Depth ( 0 to 1.5m) Internal Diameter :-1200mm | 2026-09-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2676-00 | Check Installation of Flatslab # MH-12-21-2 at Road MCD0 | 8820.42 | 01 | 30% | 2646.126 | 2646.126
1855 | B6.33 05 39.9 | SEWERAGE NETWORK: - Manhole Depth ( 0 to 1.5m) Internal Diameter :-1200mm | 2026-09-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2677-00 | Check Installation of Flatslab# MH-12-21-1 at Road MCD0 | 8820.42 | 01 | 30% | 2646.126 | 2646.126
1856 | B5 33.05.13.01 | SEWERAGE NETWORK: - Manhole Depth ( 0 to 1.5m) Internal Diameter :-1200mm | 2026-09-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2678-00 | Check Installation of Flatslab# MH-1-88-2-2 at Road MCD0 | 8820.42 | 01 | 30% | 2646.126 | 2646.126
1857 | B5 33.05.13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-09-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2679-00 | Check Installation of Flatslab # MH-1-88-2-1 at Road MCD0 | 12377.1 | 01 | 30% | 3713.13 | 3713.13
1858 | B5.33 05 13.01 | SEWERAGE NETWORK: - Manhole Depth ( 0 to 1.5m) Internal Diameter :-1200mm | 2026-09-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2680-00 | Check Installation of Flatslab MH-12-21-1-1 at Road MCD0. | 8820.42 | 01 | 30% | 2646.126 | 2646.126
1859 | B5.33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-09-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2681-00 | Check Sand around Manhole #MH-12-19-3 at Road MCE0(last layer) | 12377.1 | 01 | 45% | 5569.695 | 5569.695
1860 | B5.33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-09-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2682-00 | Check Sand around Manhole #MH-12-19-4 at Road MCE0(Last layer) | 12377.1 | 01 | 45% | 5569.695 | 5569.695
1861 | B5.33 05 13.01 | SEWERAGE NETWORK: - Manhole Depth ( 0 to 1.5m) Internal Diameter :-1200mm | 2026-09-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2683-00 | Check Sand around Manhole # MH-12-19-5 at Road MCE0(Last layer) | 8820.42 | 01 | 45% | 3969.189 | 3969.189
1862 | B5.33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-09-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2684-00 | Check Sand around Manhole # MH-12-19-1 at Road MCE0 (Last layer) | 12377.1 | 01 | 45% | 5569.695 | 5569.695
1863 | B5.33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-09-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2685-00 | Check Sand around Manhole # MH-12-19-1-1 at Road MCE0 (Last layer) | 12377.1 | 01 | 45% | 5569.695 | 5569.695
1864 | B5.33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-09-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2686-00 | Check Sand around Manhole # MH-12-19-1-2 at Road MCE0 (Last layer) | 12377.1 | 01 | 45% | 5569.695 | 5569.695
1865 | B5.33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-09-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2687-00 | Check Sand around Manhole # MH-12-13-1-2 at Road MCF0 (Last layer) | 12377.1 | 01 | 45% | 5569.695 | 5569.695
1866 | B5.33 05 13.01 | SEWERAGE NETWORK: - Manhole Depth ( 0 to 1.5m) Internal Diameter :-1200mm | 2026-09-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2688-00 | Check Sand around Manhole # MH-12-13-1-3 at Road MCF0 (Last layer) | 8820.42 | 01 | 45% | 3969.189 | 3969.189
1867 | B5.33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m to 2.5m) Internal Diameter :-1200mm | 2026-09-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2689-00 | Check Sand around Manhole # MH-12-13-1-1 at Road MCF0 (Last layer) | 12377.1 | 01 | 45% | 5569.695 | 5569.695
1868 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-09-14 | SUD1-02-011-TDC-TS9-1-STR-FIR-2692-00 | Check compaction F.D.T for Backfilling of Manhole # CB-G2/16 (S) at Road MCE0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1869 | B6.33 42 11.6 | STORM WATER NETWORK: GRP Pipes 500mm (Depth: 0.0m - 1.5m) | 2026-09-07 | SUD1-02-011-TDC-TS9-1-STR-FIR-2694-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from # STA-A1/36/5 to STA-A1/36/4 at Road MCE0 | 366.63 | 63.80 | 45% | 164.9835 | 10525.9473
1870 | B6.33 42 11.9 | STORM WATER NETWORK: GRP Pipes 600mm (Depth: 0- 1.50m) | 2026-09-07 | SUD1-02-011-TDC-TS9-1-STR-FIR-2695-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from # STA-A1/36/4 to STA-A1/36/3 at Road MCE0 | 448.1 | 63.80 | 45% | 201.645 | 12864.951
1871 | B1.31 22 00.05 | Earth works & Site Grading (Subgrade) | 2026-09-07 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2696-00 | Check Coordinates level and compaction F.D.T for (Subgrade) 2nd layer at Road/Carriageway # MCG0, STA: 0+800 to STA: 0+826.77 | 28.13 | 438.51 | 10% | 2.813 | 1233.5286
1872 | B2.33.71.19.13.04 | Manhole Type 2 | 2026-09-07 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2697-00 | Check Installation Manhole MH-006 for TELECOMMUNICATIONS Works in Road MCA0 | 7042.56 | 1 | 30% | 2112.768 | 2112.768
1873 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-08 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2698-00 | Check Coordinates level and Compaction F.D.T for Embankment 8th layer at PLOT (2), STA: 0+570 to STA: 0+720 | 22.31 | 4821.87 | 100% | 22.31 | 107575.9197
1874 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-08 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2699-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at PLOT (6), STA: 0+224 to STA: 0+450 | 22.31 | 2606.42 | 100% | 22.31 | 58149.2302
1875 | B1.31 22 00.05 | Earth works & Site Grading (Subgrade) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2700-00 | Check Coordinates level and Compaction F.D.T for (Subgrade)2nd layer at Road/Carriageway # MCE0, STA: 0+750 to STA: 0+850 | 28.13 | 615.00 | 10% | 2.813 | 1729.995
1876 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2702-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-13-2 to MH-12-13-3 at Road MCF0 | 212.41 | 78.87 | 10% | 21.241 | 1675.2777
1877 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2703-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-13-3 to MH-12-13-4 at Road MCF0 | 212.41 | 98.86 | 10% | 21.241 | 2099.8853
1878 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2704-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-13-5 to MH-12-13-4 at Road MCF0 | 212.41 | 98.71 | 10% | 21.241 | 2096.6991
1879 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51 to 2.50m) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-2705-00 | Check Installation of Manhole Base of manhole (Rings not required) STA-A1/44 at Road MCB0 | 12376.13 | 01 | 30% | 3712.839 | 3712.839
1880 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51 to 2.50m) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-2706-00 | Check Installation of Manhole Base of manhole (Rings not required) STA-A1/43 at Road MCB0 | 12376.13 | 01 | 30% | 3712.839 | 3712.839
1881 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51 to 2.50m) | 2026-09-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2707-00 | Check Installation of Manhole Base of manhole (Rings not required) STA-A1/42 at Road MCB0 | 12376.13 | 01 | 30% | 3712.839 | 3712.839
1882 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51 to 2.50m) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-2708-00 | Check Installation of Manhole Base of manhole (Rings not required) STA-A1/41 at Road MCB0 | 12376.13 | 01 | 30% | 3712.839 | 3712.839
1883 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51 to 2.50m) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-2709-00 | Check Installation of Manhole Base of manhole (Rings not required) STA-A1/40 at Road MCB0 | 12376.13 | 01 | 30% | 3712.839 | 3712.839
1884 | B6.33 05 39.5 | STORM WATER NETWORK: Manhole Diameter :- 1500mm (Depth: 1.51 to 2.50m ) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-2710-00 | Check Installation of Manhole Base of manhole (Rings not required) STA-A1/39 at Road MCB0 | 15295.58 | 01 | 30% | 4588.674 | 4588.674
1885 | B6.33 05 39.6 | STORM WATER NETWORK: Manhole Diameter 1500mm (Depth: Greater 2.50m) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-2711-00 | Check Installation of Manhole Base of manhole (Rings not required) STA-A1/38 at Road MCB0 | 19537.02 | 01 | 30% | 5861.106 | 5861.106
1886 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51 to 2.50m) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-2712-00 | Check Installation of Manhole Base of manhole (Rings not required) SAT-A1/40/1 at Road MCD0 | 12376.13 | 01 | 30% | 3712.839 | 3712.839
1887 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51 to 2.50m) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-2713-00 | Check Installation of Manhole Base of manhole (Rings not required) SAT-A1/40/2 at Road MCD0 | 12376.13 | 01 | 30% | 3712.839 | 3712.839
1888 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51 to 2.50m) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-2714-00 | Check Installation of Manhole Base of manhole STA-A2/24/4 at Road MCD0 | 12376.13 | 01 | 30% | 3712.839 | 3712.839
1889 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51 to 2.50m) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-2715-00 | Check Installation of Manhole Base of manhole STA-A2/24/3 at Road MCD0 | 12376.13 | 01 | 30% | 3712.839 | 3712.839
1890 | 31 22 00 | Earth works & Site Grading/cutting | 2026-09-07 | SUD1-02-011-TDC-TS9-1-LSP-FIR-2716-00 | Check Coordinates level and Compaction F.D.T for cutting Grading level for bottom of replacement soil (MODON Landscape Area) at # STA:0+720 to STA:0+839.04 | 51.41 | 2915.75 | 10% | 5.141 | 14989.8708
1891 | B2.33 71 19.01 | MV Duct bank 2 way | 2026-09-08 | SUD1-02-011-TDC-TS9-1-ELE-FIR-2718-00 | Supply and installation of 160mm UPVC ducts (2-way) complete with spacers, including supply, placing, compaction, and curing of concrete encasement without reinforcement steel for duct bank size 0.60m (W) x 0.50m (T), as per SEC standards in Road MCF0 and MCE0 | 308.43 | 34 | 30% | 92.529 | 3145.986
1892 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-08 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2719-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Plot. No:-(7) STA 0+130 to 0+240 | 22.31 | 4370.09 | 10% | 2.231 | 9749.6708
1893 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51 to 2.50m) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-2720-00 | Check Installation of Manhole Base of manhole (Rings not required) STA-A2/24/2 at Road MCD0 | 12376.13 | 01 | 30% | 3712.839 | 3712.839
1894 | B6.33 05 39.5 | STORM WATER NETWORK: Manhole Diameter :- 1500mm (Depth: 1.51 to 2.50m ) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-2721-00 | Check Installation of Manhole Base of manhole STA-A2/24/1 at Road MCD0 | 15295.58 | 01 | 30% | 4588.674 | 4588.674
1895 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: > 2.5m) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-2722-00 | Check Installation of Manhole Base of manhole (Rings not required) STA-A2/23 at Road MCD0 | 30133.35 | 01 | 0% | 0 | 0
1896 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: > 2.5m) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-2723-00 | Check Installation of Manhole Base of STA-A2/22 at Road MCA0, | 30133.35 | 01 | 0% | 0 | 0
1897 | B6.33 05 39.6 | STORM WATER NETWORK: Manhole Diameter 1500mm (Depth: Greater 2.50m) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-2724-00 | Check Installation of Manhole Base of STA-A1/36/1 at Road MCE0, | 19537.02 | 01 | 30% | 5861.106 | 5861.106
1898 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51 to 2.50m) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-2725-00 | Check Installation of Manhole Base (Rings not required) of STA-A1/36/2 at Road MCE0, | 12376.13 | 01 | 30% | 3712.839 | 3712.839
1899 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51 to 2.50m) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-2726-00 | Check Installation of Manhole Base (Rings not required) of STA-A1/36/3 at Road MCE0, | 12376.13 | 01 | 30% | 3712.839 | 3712.839
1900 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51 to 2.50m) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-2727-00 | Check Installation of Manhole Base (Rings not required) of STA-A1/36/4 at Road MCE0, | 12376.13 | 01 | 30% | 3712.839 | 3712.839
1901 | B6.33 42 11.10 | STORM WATER NETWORK: GRP Pipes 600mm (Depth: 1.51-2.50m) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-2728-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from # STA-A1/36/3 TO STA-A1/36/2 at Road MCE0 | 461.68 | 63.80 | 45% | 207.756 | 13254.8328
1902 | B6.33 42 11.10 | STORM WATER NETWORK: GRP Pipes 600mm (Depth: 1.51-2.50m) | 2026-09-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-2729-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from #STA-A1/36/2 to STA-A1/36/1 at Road MCE0 | 461.68 | 64.25 | 45% | 207.756 | 13348.323
1903 | B1.32 11 23.01 | AGGREGATE BASE COURSE | 2026-09-08 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2730-00 | Check Coordinates level and compaction F.D.T for (Aggregate base course) at Road /Carriageway# MCF0, STA: 0+600 to STA: 0+760 | 62.07 | 632.00 | 10% | 6.207 | 3922.824
1904 | B1.31 22 00.05 | Earth works & Site Grading (Subgrade) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2731-00 | Check Coordinates level and Compaction F.D.T for (Subgrade) 2nd layer at Road/Carriageway # MCG0, STA: 0+224 to STA: 0+240 | 28.13 | 124.53 | 10% | 2.813 | 350.3029
1905 | B1.31 22 00.05 | Earth works & Site Grading (Subgrade) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2732-00 | Check Coordinates level and Compaction F.D.T for (Subgrade) 2nd layer at Road/Carriageway # MCZ0, STA: 0+250 to STA: 0+447.25 | 28.13 | 1,225.10 | 10% | 2.813 | 3446.2063
1906 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51 to 2.50m) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-2737-00 | Check Installation of Manhole Base of manhole (Rings not required) STA-A1/36/5 at Road MCE0 | 12376.13 | 01 | 30% | 3712.839 | 3712.839
1907 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-09-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-2738-00 | Check Installation of Manhole Base of manhole (Rings not required) STA-A2/19/1 at Road MCE0 | 12376.13 | 01 | 0% | 0 | 0
1908 | B6.33 05 39.6 | STORM WATER NETWORK: Manhole Diameter 1500mm (Depth: Greater 2.50m) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-2739-00 | Check Installation of Manhole Base of manhole (Rings not required) STA-A1/30/1 at Road MCF0 | 19537.02 | 01 | 30% | 5861.106 | 5861.106
1909 | B6.33 05 39.5 | STORM WATER NETWORK: Manhole Diameter :- 1500mm (Depth: 1.51 to 2.50m ) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-2740-00 | Check Installation of Manhole Base of manhole (Rings not required) STA-A1/30/2 at Road MCF0 | 15295.58 | 01 | 30% | 4588.674 | 4588.674
1910 | B6.33 05 39.5 | STORM WATER NETWORK: Manhole Diameter :- 1500mm (Depth: 1.51 to 2.50m ) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-2741-00 | Check Installation of Manhole Base of manhole (Rings not required) STA-A1/30/3 at Road MCF0 | 15295.58 | 01 | 30% | 4588.674 | 4588.674
1911 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51 to 2.50m) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-2742-00 | Check Installation of Manhole Base of manhole (Rings not required) STA-A1/30/4 at Road MCF0 | 12376.13 | 01 | 30% | 3712.839 | 3712.839
1912 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51 to 2.50m) | 2026-09-08 | SUD1-02-011-TDC-TS9-1-STR-FIR-2743-00 | Check Installation of Manhole Base of manhole (Rings not required) STA-A1/15/10 at Road MCF0 | 12376.13 | 01 | 30% | 3712.839 | 3712.839
1913 | B5.33 31 00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Depth 0m- 1.50m) | 2026-09-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2752-00 | Check compaction F.D.T for Trench Backfilling 1st layer Between Manhole # MH-1-93-3 to MH-1-93-4 at Road MCC0(last layer) | 212.41 | 78.87 | 10% | 21.241 | 1675.2777
1914 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-09-09 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2753-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 074 To 075 in Road MCE0 | 617.84 | 24.15 | 25% | 154.46 | 3730.209
1915 | B5 33.05.13.05 | SEWERAGE NETWORK: - Manhole (Depth 2.51 to 3.5m) Internal Diameter (1200mm) | 2026-09-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2755-00 | Check Installation of Manhole Base MH-1-92 at Road MCC0 | 15848.43 | 01 | 30% | 4754.529 | 4754.529
1916 | B5.33 31 00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Depth 0m- 1.50m) | 2026-09-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2756-00 | Check compaction F.D.T for Trench Backfilling Between Manhole # MH-12-19-2 to MH-12-19-3 at Road MCE0 (Bottom Subgrade) | 212.41 | 78.87 | 0% | 0 | 0
1917 | B1.32 14 13.02 | Installation Curb stone L1 | 2026-09-09 | SUD1-02-011-TDC-TS9-1-LSP-FIR-2757-00 | Installation of Curb stone L1 including backing concrete STA 0+000 to 0+140 | 51.41 | 344.28 | 30% | 15.423 | 5309.8304
1918 | B1.32 14 13.02 | Installation Curb stone L2 | 2026-09-09 | SUD1-02-011-TDC-TS9-1-LSP-FIR-2758-00 | Installation of Curb stone L1 including backing concrete # STA A1,A2,A6,A10,A14 | 51.41 | 342.22 | 30% | 15.423 | 5278.0591
1919 | B5 33.05.13.01 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 0m- 1.50m) | 2026-09-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2769-00 | Check compaction F.D.T for Manhole Backfilling 1st layer at # MH-1-93-4 at Road # MCC0(bottom subgrade) | 8820.42 | 01 | 10% | 882.042 | 882.042
1920 | B5 33.05.13.03 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 1.51m-2.50m) | 2026-09-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2770-00 | Check compaction F.D.T for Manhole Backfilling at # MH-12-19-2 at Road # MCE0(Bottom Subgrade) | 12377.1 | 01 | 0% | 0 | 0
1921 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole diameter :- 2000mm (Depth: Greater > 2.50m) | 2026-09-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-2771-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit STA-A1/28 at Road MCB0 | 30133.35 | 01 | 5% | 1506.6675 | 1506.6675
1922 | B6.33 42 11.9 | STORM WATER NETWORK: GRP Pipes 600mm (Depth: 0- 1.50) | 2026-09-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-2772-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from # STA-A1/30/4 to STA-A1/30/3 at Road MCF0 | 448.1 | 63.65 | 45% | 201.645 | 12834.7043
1923 | B5 33.05.13.01 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 0m- 1.50m) | 2026-09-09 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2773-00 | Check compaction F.D.T for Manhole Backfilling at # MH-12-19-1-3 at Road # MCE0(Bottom Subgrade) | 8820.42 | 01 | 0% | 0 | 0
1924 | B1.31 22 00.05 | Earth works & Site Grading (Subgrade) | 2026-09-09 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2774-00 | Check Coordinates level and Compaction F.D.T for (Subgrade) 2nd layer at Road/Carriageway # MCE0, STA: 0+590 to STA: 0+750 | 10.67 | 984.00 | 10% | 1.067 | 1049.928
1925 | B1.32 11 23.01 | AGGREGATE BASE COURSE | 2026-09-09 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2775-00 | Check Coordinates level and compaction F.D.T for (Aggregate base course) at Road /Carriageway# MCF0, STA: 0+450 to STA: 0+600 (Last layer) | 62.07 | 592.50 | 10% | 6.207 | 3677.6475
1926 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-09-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-2776-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole # MH-G2/16/5 to CB-G2/16/5 B (S) at Road MCE0 (Last Layer) | 377.3 | 26.49 | 10% | 37.73 | 999.4677
1927 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes With DIA 400mm for Catch Basin | 2026-09-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-2777-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole # MH-G2/16/5 to CB-G2/16/5 (D) at Road MCE0 (Last Layer) | 602.32 | 3.56 | 10% | 60.232 | 214.4259
1928 | B6.33 42 11.1 | STORM WATER NETWORK: UPVC Pipes With DIA 300mm for Catch Basin | 2026-09-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-2778-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole # CB-G2/16/5 (D) to CB-G2/16/5 A (S) at Road MCE0 (Last Layer) | 377.3 | 3.56 | 10% | 37.73 | 134.3188
1929 | B6.33 42 11.19 | STORM WATER NETWORK: GRP Pipes 900mm Diameter (Depth: 1.51 to 2.50m) | 2026-09-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-2779-00 | Check Coordinates level and compaction F.D.T for Trench Backfilling Between Manhole # MH-G2/16/4 to MH-G2/16/5 at Road MCE0 (Last Layer) | 743.93 | 87.25 | 10% | 74.393 | 6490.7892
1930 | B6.33 42 11.6 | STORM WATER NETWORK: GRP Pipes 500mm (Depth: 0- 1.50) | 2026-09-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-2780-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from # STA-A1/30/5 to STA-A1/30/4 at Road MCF0 | 366.63 | 63.80 | 45% | 164.9835 | 10525.9473
1931 | B6.33 05 39.6 | STORM WATER NETWORK: GRP Pipes 500mm (Depth: 0- 1.50) | 2026-09-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-2781-00 | Check compaction F.D.T for Backfilling of Manhole # MH -G2/16/5 at Road MCE0 (Bottom subgrade) | 19537.02 | 01 | 10% | 1953.702 | 1953.702
1932 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-09-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-2782-00 | Check compaction F.D.T for Backfilling of Manhole # CB-G2/16/5 B (S) at Road MCE0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1933 | B6.33 05 39.16 | STORM WATER NETWORK: Catch Basin Double | 2026-09-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-2783-00 | Check compaction F.D.T for Backfilling of Manhole # CB-G2/16/5 (D) at Road MCE0 (Bottom subgrade) | 12444.99 | 01 | 10% | 1244.499 | 1244.499
1934 | B6.33 05 39.15 | STORM WATER NETWORK: Catch Basin Single | 2026-09-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-2784-00 | Check compaction F.D.T for Backfilling of Manhole # CB-G2/16/5 A (S) at Road MCE0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
1935 | B1.31 22 00.05 | Earth works & Site Grading (Subgrade) | 2026-09-09 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2785-00 | Check Coordinates level and Compaction F.D.T for (Subgrade) 2nd layer at Road/Carriageway # MCZ0, STA: 0+080 to STA: 0+250 | 28.13 | 1029.05 | 10% | 2.813 | 2894.7177
1936 | B6.33 05 39.6 | STORM WATER NETWORK: GRP Pipes 500mm (Depth: 0- 1.50) | 2026-09-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-2786-00 | Check Installation of Manhole Base (Rings not required) Pit STA-A1/26/1 at Road MCG0 | 19537.02 | 01 | 30% | 5861.106 | 5861.106
1937 | B6.33 05 39.5 | STORM WATER NETWORK: Manhole Diameter :- 1500mm (Depth: 1.51 to 2.50m ) | 2026-09-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-2787-00 | Check Installation of Manhole Base of manhole Pit STA-1/26/2 at Road MCG0 | 15295.58 | 01 | 30% | 4588.674 | 4588.674
1938 | B6.33 05 39.5 | STORM WATER NETWORK: Manhole Diameter :- 1500mm (Depth: 1.51 to 2.50m ) | 2026-09-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-2788-00 | Check Installation of Manhole Base (Rings not required) Pit STA-A1/26/3 at Road MCG0 | 15295.58 | 01 | 30% | 4588.674 | 4588.674
1939 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51 to 2.50m) | 2026-09-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-2789-00 | Check Installation of Manhole Base (Rings not required) Pit STA-A1/26/4at Road MCG0 | 12376.13 | 01 | 30% | 3712.839 | 3712.839
1940 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51 to 2.50m) | 2026-09-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-2790-00 | Check Installation of Manhole Base (Rings not required) Pit STA-A1/26/5 at Road MCG0 | 12376.13 | 01 | 30% | 3712.839 | 3712.839
1941 | B6.33 42 11.3 | STORM WATER NETWORK: GRP Pipes 400mm (Depth: 0m - 1.5m) | 2026-09-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-2791-00 | Inspection Gravity and Leakage test pipeline from Manhole # STA-A1/40/1 to STA-A1/40/2 at Road MCD0 | 300.67 | 64.34 | 10% | 30.067 | 1934.5108
1942 | B6.33 42 11.3 | STORM WATER NETWORK: GRP Pipes 400mm (Depth: 0m - 1.5m) | 2026-09-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-2792-00 | Inspection Gravity and Leakage test pipeline from Manhole # STA-A2/24/4 to STA-A2/24/3 at Road MCD0 | 300.67 | 63.80 | 10% | 30.067 | 1918.2746
1943 | B6.33 42 11.7 | STORM WATER NETWORK: GRP Pipes 500mm (Depth: 1.51 to 2.50m) | 2026-09-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-2793-00 | Inspection Gravity and Leakage test pipeline from Manhole # STA-A2/24/3 to STA-A2/24/2 at Road MCD0 | 379.24 | 63.80 | 10% | 37.924 | 2419.5512
1944 | B6.33 42 11.10 | STORM WATER NETWORK: GRP Pipes 600mm (Depth: 1.51-2.50m) | 2026-09-09 | SUD1-02-011-TDC-TS9-1-STR-FIR-2794-00 | Inspection Gravity and Leakage test pipeline from Manhole # STA-A2/24/2 to STA-A2/24/1 at Road MCD0 | 461.68 | 63.65 | 10% | 46.168 | 2938.5932
1945 | B3.33 14 13.7 | POTABLE WATER NETWORK: HDPE Pipes 315 Diameter (Depth 2.51 to 3.50m) | 2026-09-09 | SUD1-02-011-TDC-TS9-1-PW-FIR-2795-00 | Check Coordinates level and Excavation width Bottom level and compaction for potable water pipeline from Existing STA: 1+475.0 to ST: +1+538.5 Road MCD0 | 412.21 | 63.50 | 5% | 20.6105 | 1308.7668
1946 | B3.33 14 13.7 | POTABLE WATER NETWORK: HDPE Pipes 315 Diameter (Depth 2.51 to 3.50m) | 2026-09-17 | SUD1-02-011-TDC-TS9-1-PW-FIR-2796-01 | Check Coordinates level and Excavation width Bottom level and compaction for Road crossing potable water HDPE pipelines (Diameter 315mm) from ST: 1+538.5 at Road MCD0 | 412.21 | 28.26 | 5% | 20.6105 | 582.4527
1947 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-09 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2797-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Plot. No:-(7) STA 0+020 to 0+130 | 22.31 | 3817.71 | 100% | 22.31 | 85173.1101
1948 | B2.33.71.19.13.05 | Manhole Type 3 | 2026-09-09 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2798-00 | Check Installation Manhole MH-101 & MH-102 & MH-104 & MH-106 for TELECOMMUNICATIONS Works in Road MC20 | 7057.11 | 4 | 30% | 2117.133 | 8468.532
1949 | B2.33 71 19.13.02 | Drawpit with medium duty steel cover, size 900x900x1200mm | 2026-09-09 | SUD1-02-011-TDC-TS9-1-LIT-FIR-2799-00 | Check Installation Drawpit MH-47 & MH-48 for Street Lighting in Road MC20 | 3850.57 | 2 | 30% | 1155.171 | 2310.342
1950 | B3.33 14 13.1 | POTABLE WATER NETWORK: HDPE Pipes 160mm Diameter (Depth 0.0m to 1.50m) | 2026-09-14 | SUD1-02-011-TDC-TS9-1-PW-FIR-2801-00 | Check Compaction F.D.T for Backfilling 1st layer for Road crossing potable water HDPE pipelines (Diameter 160mm) at ST: 2 +036.62 #Road MCZ0 (Bottom Subgrade) | 101.84 | 26.80 | 10% | 10.184 | 272.9312
1951 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0.0m - 1.5m) | 2026-09-09 | SUD1-02-011-TDC-TS9-1-IRR-FIR-2802-00 | Check Compaction F.D.T for Backfilling 1st layer for Road crossing 125mm O.D HDPE Pipes STA +566.47at Road MCZ0 (Bottom Subgrade) | 179.43 | 33.49 | 10% | 17.943 | 600.9111
1952 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-09 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2803-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at PLOT (1), STA: 0+200 to STA: 0+400 | 22.31 | 3820.52 | 100% | 22.31 | 85235.8012
1953 | B3.33 14 13.6 | POTABLE WATER NETWORK: HDPE Pipes 315 Diameter (Depth 1.51 to 2.50m) | 2026-09-13 | SUD1-02-011-TDC-TS9-1-PW-FIR-2804-01 | Check Coordinates level and Excavation width Bottom level and compaction for potable water pipeline from Existing STA: 1+431.3 to ST: 1+475.0 Road MCD0 | 301.64 | 43.68 | 5% | 15.082 | 658.7818
1954 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole diameter 2000m Depth: (Greater > 2.50m) | 2026-09-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-2805-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit STA-A1/27 at Road MCB0 | 30133.35 | 01 | 5% | 1506.6675 | 1506.6675
1955 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole diameter 2000m Depth: (Greater > 2.50m) | 2026-09-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-2806-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit STA-A1/26 at Road MCB0 | 30133.35 | 01 | 5% | 1506.6675 | 1506.6675
1956 | B6.33 42 11.33 | STORM WATER NETWORK: GRP Pipes 1300mm (Depth: Greater > 3.50m) | 2026-09-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-2807-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/29 to STA-A1/28 at Road MCB0 | 1890.37 | 50.00 | 5% | 94.5185 | 4725.925
1957 | B6.33 42 11.33 | STORM WATER NETWORK: GRP Pipes 1300mm (Depth: Greater > 3.50m) | 2026-09-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-2808-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/28 to STA-A1/27at Road MCB0 | 1890.37 | 50.00 | 5% | 94.5185 | 4725.925
1958 | B6.33 42 11.33 | STORM WATER NETWORK: GRP Pipes 1300mm (Depth: Greater > 3.50m) | 2026-09-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-2809-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/27 to STA-A1/26 Road MCB0 | 1890.37 | 54.00 | 5% | 94.5185 | 5103.999
1959 | B3.33 14 13.5 | POTABLE WATER NETWORK: HDPE Pipes 315 Diameter (Depth 0m to 1.50m) | 2026-09-13 | SUD1-02-011-TDC-TS9-1-PW-FIR-2810-01 | Check Coordinates level and Excavation width Bottom level and compaction for potable water pipeline (315mm) Diameter from Existing STA: 1+431.3 to Existing Network at Road MCD0 | 290.97 | 33.78 | 5% | 14.5485 | 491.4483
1960 | B2.33 71 19.02 | MV Duct bank 4 way | 2026-09-10 | SUD1-02-011-TDC-TS9-1-ELE-FIR-2811-00 | Supply and installation of 160mm UPVC ducts (4-way) complete with spacers, including supply, placing, compaction, and curing of concrete encasement without reinforcement steel for duct bank size 0.60m (W) x 0.50m (T), as per SEC standards in Road MCD0 | 617.84 | 22.14 | 30% | 185.352 | 4103.6933
1961 | B2.33 71 19.01 | MV Duct bank 2 way | 2026-09-10 | SUD1-02-011-TDC-TS9-1-ELE-FIR-2812-00 | Supply and installation of 160mm UPVC ducts (2-way) complete with spacers, including supply, placing, compaction, and curing of concrete encasement without reinforcement steel for duct bank size 0.60m (W) x 0.50m (T), as per SEC standards in Road MCG0 | 308.43 | 15.49 | 30% | 92.529 | 1433.2742
1962 | B2.33 71 19.01 | MV Duct bank 2 way | 2026-09-10 | SUD1-02-011-TDC-TS9-1-ELE-FIR-2813-00 | Supply and installation of 160mm UPVC ducts (2-way) complete with spacers, including supply, placing, compaction, and curing of concrete encasement without reinforcement steel for duct bank size 0.60m (W) x 0.50m (T), as per SEC standards in Road MCC0 | 308.43 | 15.74 | 30% | 92.529 | 1456.4065
1963 | B2.33 71 19.02 | MV Duct bank 4 way | 2026-09-10 | SUD1-02-011-TDC-TS9-1-ELE-FIR-2814-00 | Supply and installation of 160mm UPVC ducts (4-way) complete with spacers, including supply, placing, compaction, and curing of concrete encasement without reinforcement steel for duct bank size 0.60m (W) x 0.50m (T), as per SEC standards in Road MCH0 | 617.84 | 20.22 | 30% | 185.352 | 3747.8174
1964 | B2.33 71 19.01 | MV Duct bank 2 way | 2026-09-10 | SUD1-02-011-TDC-TS9-1-ELE-FIR-2815-00 | Supply and installation of 160mm UPVC ducts (2-way) complete with spacers, including supply, placing, compaction, and curing of concrete encasement without reinforcement steel for duct bank size 0.60m (W) x 0.50m (T), as per SEC standards in Road MCF0 Near Road MCA0 | 308.43 | 15.70 | 30% | 92.529 | 1452.7053
1965 | B2.33 71 19.01 | MV Duct bank 2 way | 2026-09-10 | SUD1-02-011-TDC-TS9-1-ELE-FIR-2816-00 | Supply and installation of 160mm UPVC ducts (2-way) complete with spacers, including supply, placing, compaction, and curing of concrete encasement without reinforcement steel for duct bank size 0.60m (W) x 0.50m (T), as per SEC standards in Road MCF0 Near Road MCB0 | 308.43 | 15.21 | 30% | 92.529 | 1407.3661
1966 | B2.33 71 19.02 | MV Duct bank 4 way | 2026-09-10 | SUD1-02-011-TDC-TS9-1-ELE-FIR-2817-00 | Supply and installation of 160mm UPVC ducts (4-way) complete with spacers, including supply, placing, compaction, and curing of concrete encasement without reinforcement steel for duct bank size 0.60m (W) x 0.50m (T), as per SEC standards in Road MC20 Near STL-SS-01 | 617.84 | 8.27 | 30% | 185.352 | 1532.861
1967 | B6.33 42 11.3 | STORM WATER NETWORK: GRP Pipes 400mm (Depth: 0m - 1.5m) | 2026-09-10 | SUD1-02-011-TDC-TS9-1-STR-FIR-2818-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from # STA-A1/15/9 To STA-A1/15/10 at Road MCF0 | 300.67 | 59.15 | 45% | 135.3015 | 8003.0837
1968 | B1.32 11 23.01 | AGGREGATE BASE COURSE | 2026-09-10 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2820-00 | Check Coordinates level and compaction F.D.T for (Aggregate base course) at Road /Carriageway# MCF0, STA: 0+280 to STA: 0+450 (Last layer) | 62.07 | 671.50 | 10% | 6.207 | 4168.0005
1969 | B6.33 42 11.10 | STORM WATER NETWORK: GRP Pipes 600mm (Depth: 1.51-2.50m) | 2026-09-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2830-00 | Inspection Gravity and Leakage test pipeline from Manhole # STA-A1/36/2 to STA-A1/36/1 at Road MCE0 | 461.68 | 64.25 | 10% | 46.168 | 2966.294
1970 | B6.33 42 11.10 | STORM WATER NETWORK: GRP Pipes 600mm (Depth: 1.51-2.50m) | 2026-09-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-2831-00 | Inspection Gravity and Leakage test pipeline from Manhole # STA-A1/36/3 TO STA-A1/36/2 at Road MCE0 | 461.68 | 63.80 | 10% | 46.168 | 2945.5184
1971 | B6.33 42 11.9 | STORM WATER NETWORK: GRP Pipes 600mm (Depth: 0- 1.50m) | 2026-09-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-2832-00 | Inspection Gravity and Leakage test pipeline from Manhole # STA-A1/36/4 to STA-A1/36/3 at Road MCE0 | 743.93 | 63.80 | 10% | 74.393 | 4746.2734
1972 | B6.33 42 11.6 | STORM WATER NETWORK: GRP Pipes 500mm (Depth: 0- 1.50m) | 2026-09-12 | SUD1-02-011-TDC-TS9-1-STR-FIR-2833-00 | Inspection Gravity and Leakage test pipeline from Manhole # STA-A1/36/5 to STA-A1/36/4 at Road MCE0 | 366.63 | 63.80 | 10% | 36.663 | 2339.0994
1973 | B2.33.71.19.13.05 | Manhole Type 3 | 2026-09-10 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2834-00 | Check Installation Manhole MH-037 & MH-092 & MH-093 & MH-094 for TELECOMMUNICATIONS Works in Road MC20 | 7057.11 | 4 | 30% | 2117.133 | 8468.532
1974 | B2.33 71 19.13.01 | Drawpit with medium duty steel cover, size600x600x1000mm | 2026-09-12 | SUD1-02-011-TDC-TS9-1-LIT-FIR-2835-00 | Check Installation Drawpit MH-41 & MH-42 & MH-45 & MH-46 for Street Lighting in Road MC20 | 2683.76 | 4 | 30% | 805.128 | 3220.512
1975 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-09-12 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2838-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from Manhole # MH-12-15 to MH-12-14 at Road MCB0 | 221.14 | 74.30 | 45% | 99.513 | 7393.8159
1976 | B2.33 71 19.02 | MV Duct bank 4 way | 2026-09-12 | SUD1-02-011-TDC-TS9-1-ELE-FIR-2839-00 | Supply and installation of 160mm UPVC ducts (4-way) complete with spacers, including supply, placing, compaction, and curing of concrete encasement without reinforcement steel for duct bank size 0.60m (W) x 0.50m (T), as per SEC standards in Road MC20 Near Road COL-MC10 | 617.84 | 8.27 | 30% | 185.352 | 1532.861
1977 | B2.33 71 19.02 | MV Duct bank 4 way | 2026-09-12 | SUD1-02-011-TDC-TS9-1-ELE-FIR-2840-00 | Supply and installation of 160mm UPVC ducts (4-way) complete with spacers, including supply, placing, compaction, and curing of concrete encasement without reinforcement steel for duct bank size 0.60m (W) x 0.50m (T), as per SEC standards in Road MC20 Near Road ART-MC10 | 617.84 | 8.27 | 30% | 185.352 | 1532.861
1978 | B2.33 71 19.02 | MV Duct bank 4 way | 2026-09-12 | SUD1-02-011-TDC-TS9-1-ELE-FIR-2841-00 | Supply and installation of 160mm UPVC ducts (4-way) complete with spacers, including supply, placing, compaction, and curing of concrete encasement without reinforcement steel for duct bank size 0.60m (W) x 0.50m (T), as per SEC standards in Road MC20 Near STL-SS-02 | 617.84 | 8.27 | 30% | 185.352 | 1532.861
1979 | B2.33 71 19.01 | MV Duct bank 2 way | 2026-09-12 | SUD1-02-011-TDC-TS9-1-ELE-FIR-2842-00 | Supply and installation of 160mm UPVC ducts (2-way) complete with spacers, including supply, placing, compaction, and curing of concrete encasement without reinforcement steel for duct bank size 0.60m (W) x 0.50m (T), as per SEC standards in Road MCI0 | 308.43 | 15.55 | 30% | 92.529 | 1438.8259
1980 | B2.33 71 19.01 | MV Duct bank 2 way | 2026-09-12 | SUD1-02-011-TDC-TS9-1-ELE-FIR-2843-00 | Supply and installation of 160mm UPVC ducts (2-way) complete with spacers, including supply, placing, compaction, and curing of concrete encasement without reinforcement steel for duct bank size 0.60m (W) x 0.50m (T), as per SEC standards in Road MCH0 | 308.43 | 15.84 | 30% | 92.529 | 1465.6594
1981 | B2.33 71 19.03 | MV Duct bank 6 way | 2026-09-12 | SUD1-02-011-TDC-TS9-1-ELE-FIR-2844-00 | Supply and installation of 160mm UPVC ducts (6-way) complete with spacers, including supply, placing, compaction, and curing of concrete encasement without reinforcement steel for duct bank size 0.60m (W) x 0.50m (T), as per SEC standards in Road MCH0 | 926.27 | 20.85 | 30% | 277.881 | 5793.8188
1982 | B2.33 71 19.01 | MV Duct bank 2 way | 2026-09-12 | SUD1-02-011-TDC-TS9-1-ELE-FIR-2845-00 | Supply and installation of 160mm UPVC ducts (2-way) complete with spacers, including supply, placing, compaction, and curing of concrete encasement without reinforcement steel for duct bank size 0.60m (W) x 0.50m (T), as per SEC standards in Road MCB0 Near Road COL-MC10 | 308.43 | 17.74 | 30% | 92.529 | 1641.4645
1983 | B2.33 71 19.02 | MV Duct bank 4 way | 2026-09-12 | SUD1-02-011-TDC-TS9-1-ELE-FIR-2846-00 | Supply and installation of 160mm UPVC ducts (4-way) complete with spacers, including supply, placing, compaction, and curing of concrete encasement without reinforcement steel for duct bank size 0.60m (W) x 0.50m (T), as per SEC standards in Road MCI0 | 617.84 | 15.37 | 30% | 185.352 | 2848.8602
1984 | B3.33 14 13.1 | POTABLE WATER NETWORK: HDPE Pipes 160mm Diameter (Depth 0.0m to 1.50m) | 2026-09-03 | SUD1-02-011-TDC-TS9-1-PW-FIR-2847-00 | Inspection Pressure test of potable water Pipeline HDPE Pipes(160mm) from ST: 2 +036.62 Road MCZ0 | 101.84 | 26.80 | 25% | 25.46 | 682.328
1985 | B3.33 14 13.1 | POTABLE WATER NETWORK: HDPE Pipes 160mm Diameter (Depth 0.0m to 1.50m) | 2026-08-12 | SUD1-02-011-TDC-TS9-1-PW-FIR-2848-00 | Inspection Pressure test of potable water Pipeline HDPE Pipes (160mm) from ST: +309.99&ST: +056.73 Road MCE0 | 101.84 | 68.06 | 25% | 25.46 | 1732.8076
1986 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0.0m - 1.5m) | 2026-08-13 | SUD1-02-011-TDC-TS9-1-IRR-FIR-2849-00 | Inspection Pressure test of irrigation water Pipeline HDPE Pipes(125mm) from ST: +566.47 Road MCZ0 | 179.43 | 33.49 | 10% | 17.943 | 600.9111
1987 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0.0m - 1.5m) | 2026-08-13 | SUD1-02-011-TDC-TS9-1-IRR-FIR-2850-00 | Inspection Pressure test of irrigation water Pipeline HDPE Pipes(125mm) from ST: +0:00 & ST +022:57 Road MCD0 | 179.43 | 22.57 | 10% | 17.943 | 404.9735
1988 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0.0m - 1.5m) | 2026-08-13 | SUD1-02-011-TDC-TS9-1-IRR-FIR-2851-00 | Inspection Pressure test of irrigation water Pipeline HDPE Pipes(125mm) from ST: +360.81& ST: +081.13,ST :+114.70 Road MCE0 | 179.43 | 67.12 | 10% | 17.943 | 1204.3342
1989 | B3.33 14 13.1 | POTABLE WATER NETWORK: HDPE Pipes 160mm Diameter (Depth 0.0m to 1.50m) | 2026-08-11 | SUD1-02-011-TDC-TS9-1-PW-FIR-2852-00 | Inspection Pressure test of potable water Pipeline HDPE Pipes(160mm) from ST: +449.02 & ST:+195.75 Road MCF0 | 101.84 | 67.98 | 25% | 25.46 | 1730.7708
1990 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0.0m - 1.5m) | 2026-08-15 | SUD1-02-011-TDC-TS9-1-IRR-FIR-2853-00 | Inspection Pressure test of irrigation pipeline HDPE Pipes(125mm) from ST: +212.21& ST: +265.15 Road MCE0 | 179.43 | 27.36 | 10% | 17.943 | 490.9205
1991 | B6.33 42 11.6 | STORM WATER NETWORK: GRP Pipes 500mm (Depth: 0.0m - 1.5m) | 2026-09-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2855-00 | Inspection Gravity and Leakage test pipeline from Manhole # STA-A1/30/5 to STA-A1/30/4 at Road MCF0 | 366.63 | 63.80 | 10% | 36.663 | 2339.0994
1992 | B6.33 42 11.3 | STORM WATER NETWORK: GRP Pipes 400mm (Depth: 0m - 1.5m) | 2026-09-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2856-00 | Inspection Gravity and Leakage test pipeline from Manhole # STA-A1/15/9 To STA-A1/15/10 at Road MCF0 | 300.67 | 59.15 | 10% | 30.067 | 1778.4631
1993 | B1.32 11 23.01 | AGGREGATE BASE COURSE | 2026-09-12 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2860-00 | Check Coordinates level and compaction F.D.T for (Aggregate base course) at Road /Carriageway# MCF0, STA: 0+224 to STA: 0+280 (Last layer) | 62.07 | 196.67 | 10% | 6.207 | 1220.7307
1994 | B2.33.71.19.13.04 | Manhole Type 2 | 2026-09-12 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2862-00 | Check Installation Manhole MH-015 & MH-022 & MH-023 for TELECOMMUNICATIONS Works in Road MCA0 & MCG0 | 7042.56 | 3 | 30% | 2112.768 | 6338.304
1995 | B2.33.71.19.13.05 | Manhole Type 3 | 2026-09-12 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2863-00 | Check Installation Manhole MH-021 & MH-024 & MH-026 for TELECOMMUNICATIONS Works in Road MCG0 & MCA0 | 7057.11 | 3 | 30% | 2117.133 | 6351.399
1996 | B5 33.31.00.01 | 6-ways ducts, 50mm diameter | 2026-09-12 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2864-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from Manhole MH-12-21-1 to MH-12-21-1-1 at Road MCD0 | 212.41 | 78.87 | 45% | 95.5845 | 7538.7495
1997 | B6.33 42 11.36 | 6-ways ducts, 50mm diameter | 2026-09-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2865-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/26 STA-A1/25 Road MCB0 | 2078.53 | 54.70 | 10% | 207.853 | 11369.5591
1998 | B6.33 42 11.35 | Manhole Type 2 | 2026-09-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2866-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/25 to STA-A1/24 Road MCB0 | 2036.82 | 54.00 | 10% | 203.682 | 10998.828
1999 | B6.33 42 11.35 | Manhole Type 3 | 2026-09-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2867-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/24 to STA-A1/23 Road MCB0 | 2036.82 | 47.80 | 10% | 203.682 | 9735.9996
2000 | B6.33 05 39.9 | 6-ways ducts, 50mm diameter | 2026-09-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2868-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit STA-A1/25 at Road MCB0 | 30133.35 | 01 | 10% | 3013.335 | 3013.335
2001 | B6.33 05 39.9 | 6-ways ducts, 50mm diameter | 2026-09-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2869-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit STA-A1/24 at Road MCB0 | 30133.35 | 01 | 10% | 3013.335 | 3013.335
2002 | B6.33 05 39.12 | 6-ways ducts, 50mm diameter | 2026-09-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2870-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage manhole pit STA-A1/23 at Road MCB0 | 36159.44 | 01 | 10% | 3615.944 | 3615.944
2003 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-09-12 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2871-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 082 To 083 in Road MCD0 | 617.84 | 26.71 | 25% | 154.46 | 4125.6266
2004 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-09-12 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2872-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 076 To 077 in Road MCE0 | 617.84 | 26.71 | 25% | 154.46 | 4125.6266
2005 | B1.32 11 26.01 | 6-ways ducts, 50mm diameter | 2026-09-13 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2875-01 | Check Coordinates, level, thickness,Compaction and Testing for Bituminous base course layer (70mm) on Road /Carriageway from # ST: 0+450 to ST: 0+780 at Road MCG0 | 519.88 | 450.65 | 15% | 77.982 | 35142.5883
2006 | B1.31 22 00.04 | Manhole Type 2 | 2026-09-15 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2876-01 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer for Plot. No:-(8) # STA:0+020 to STA:0+320 at Zone A | 22.31 | 10369.14 | 100% | 22.31 | 231335.5134
2007 | B2.33.71.19.13.04 | Manhole Type 2 | 2026-09-13 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2877-00 | Check Installation Manhole MH-0095 for TELECOMMUNICATIONS Works in Road MC20 | 7042.56 | 1 | 30% | 2112.768 | 2112.768
2008 | B1.31 22 00.05 | Earth works & Site Grading (Subgrade) | 2026-09-13 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2880-00 | Check Coordinates level and compaction F.D.T for (Subgrade)2nd layer at Road/Carriageway # MCE0, STA: 0+500 to STA: 0+590 | 7057.11 | 584.58 | 100% | 7057.11 | 4125445.3638
2009 | B2.33.71.19.13.05 | Manhole Type 3 | 2026-09-13 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2882-00 | Check Installation Manhole MH-105 & MH-107 for TELECOMMUNICATIONS Works in Road MC20 | 7057.11 | 2 | 30% | 2117.133 | 4234.266
2010 | B6.33 42 11.9 | 6-ways ducts, 50mm diameter | 2026-09-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2884-00 | Inspection Gravity and Leakage test pipeline from Manhole # STA-A1/30/4 to STA-A1/30/3 at Road MCF0 | 448.1 | 63.65 | 10% | 44.81 | 2852.1565
2011 | B1.31 22 00.04 | 6-ways ducts, 50mm diameter | 2026-09-13 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2885-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Plot. No:-(7) STA 0+240 to 0+350 | 22.31 | 4375.98 | 100% | 22.31 | 97628.1138
2012 | B1.31 22 00.04 | 6-ways ducts, 50mm diameter | 2026-09-13 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2891-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Plot (3) STA: 0+0170 to STA: 0+250 | 22.31 | 2522.96 | 100% | 22.31 | 56287.2376
2013 | B6.33 42 11.1 | 6-ways ducts, 50mm diameter | 2026-09-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2895-00 | Check compaction F.D.T for Trench Backfilling Between Manhole # MH-G2/16/6 to CB-G2/16/6 B (S) at Road MCE0 (Last Layer) | 377.3 | 24.49 | 10% | 37.73 | 924.0077
2014 | B6.33 42 11.1 | Manhole Type 3 | 2026-09-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2896-00 | Check compaction F.D.T for Trench Backfilling Between Manhole # MH-G2/16/6 to CB-G2/16/6 A (S) at Road MCE0 (Last Layer) | 377.3 | 12.71 | 10% | 37.73 | 479.5483
2015 | B6.33 42 11.1 | 6-ways ducts, 50mm diameter | 2026-09-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-2897-00 | Check compaction F.D.T for Trench Backfilling Between Manhole CB-G2/16/7 B (S) to MH-G2/16/7 at Road MCE0 (Last Layer) | 377.3 | 41.88 | 10% | 37.73 | 1580.1324
2016 | B6.33 05 39.6 | Manhole Type 2 | 2026-09-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2898-00 | Check compaction F.D.T for Backfilling of Manhole # MH -G2/16/6 at Road MCE0 (Bottom subgrade) | 19537.02 | 01 | 10% | 1953.702 | 1953.702
2017 | B6.33 05 39.3 | Manhole Type 3 | 2026-09-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2899-00 | Check compaction F.D.T for Backfilling of Manhole # MH -G2/16/7 at Road MCE0 (Bottom subgrade) | 15848.43 | 01 | 10% | 1584.843 | 1584.843
2018 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-09-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2900-00 | Check compaction F.D.T for Backfilling of CB-G2/16/6 B (S) at Road MCE0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
2019 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-09-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2901-00 | Check compaction F.D.T for Backfilling of CB-G2/16/6 A (S) at Road MCE0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
2020 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-09-13 | SUD1-02-011-TDC-TS9-1-STR-FIR-2902-00 | Check compaction F.D.T for Backfilling of CB-G2/16/7 B (S) at Road MCE0 (Bottom subgrade) | 5124.07 | 01 | 10% | 512.407 | 512.407
2021 | B1.32 14 13.02 | Installation Curb stone L 1 | 2026-09-13 | SUD1-02-011-TDC-TS9-1-LSP-FIR-2904-00 | Installation of Curb stone L1 including backing concrete STA 0+680 to 0+840 & A18 | 51.41 | 660.26 | 30% | 15.423 | 10183.19
2022 | B5 33.31.00.02 | LANDSCAPE WORKS: PLANTS (Tabopia) | 2026-09-14 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2906-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-16 to MH-12-17 at Road MCI0 | 1132.86 | 39.80 | 10% | 113.286 | 4508.7828
2023 | B5 33.31.00.01 | LANDSCAPE WORKS: PLANTS (Cassia glauca) | 2026-09-14 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2907-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-17 to MH-12-18 at Road MCB0 | 1132.86 | 42.24 | 10% | 113.286 | 4785.2006
2024 | B5 33.31.00.02 | LANDSCAPE WORKS: PLANTS (Cassia glauca) | 2026-09-14 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2908-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-15 to MH-12-16 at Road MCB0 | 1132.86 | 41.62 | 10% | 113.286 | 4714.9633
2025 | B5 33.31.00.02 | Installation Curb stone L 1 | 2026-09-14 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2909-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-15 to MH-12-14 at Road MCB0 | 51.41 | 74.30 | 10% | 5.141 | 381.9763
2026 | B2.33 71 19.13.01 | PIPEWORK-PIPES: pipe line O.D 75 mm PN 10, in depth Oto 1.5 m | 2026-09-14 | SUD1-02-011-TDC-TS9-1-LIT-FIR-2911-00 | Check Installation Drawpit MH-11 & MH-12 for Street Lighting in Road MCA0 | 52.38 | 2 | 30% | 15.714 | 31.428
2027 | B2.33 71 19.13.02 | PIPEWORK-PIPES: pipe line 0.0 63 mm PN 10, in depth Oto 1.5 m | 2026-09-14 | SUD1-02-011-TDC-TS9-1-LIT-FIR-2912-00 | Check Installation Drawpit MH-19 for Street Lighting in Road MCG0 | 45.59 | 1 | 30% | 13.677 | 13.677
2028 | B3.33 14 13.5 | PIPEWORK-PIPES: pipe line O.D 50 mm PN 10, in depth Oto 1.5 m | 2026-09-14 | SUD1-02-011-TDC-TS9-1-PW-FIR-2913-00 | Check Sand bedding and pipe installation of potable water HDPE pipelines (315mm) Diameter from STA:1+925 TO 2+650 at Road MC20 | 38.8 | 725 | 45% | 17.46 | 12658.5
2029 | 31 22 00 | PIPEWORK-PIPES: pipe line 0.0 32 mm PN 10, in depth Oto 1.5 m | 2026-09-14 | SUD1-02-011-TDC-TS9-1-STR-FIR-2914-00 | Check Coordinates,bottom level Road Excavation/cutting compaction for open channel trench(C1) from # STA :0+000 STA: 0+300 with Connecting Storm Manholes# STA-SW-A5/16 TO STA-SW-A5/19 # at Road MC10 | 31.04 | 991.53 | 10% | 3.104 | 3077.7091
2030 | B1.31 22 00.04 | PIPEWORK-PIPES: pipe line O.D 25 mm PN 10, in depth Oto 1.5 m | 2026-09-14 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2918-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at PLOT (1), STA: 0+400 to STA: 0+610 | 22.31 | 4740.29 | 100% | 22.31 | 105755.8699
2031 | B1.31 22 00.04 | LANDSCAPE WORKS: PLANTS (Albizia lebbeck) | 2026-09-14 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2919-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Plot. No:-(7) STA 0+130 to 0+240 | 22.31 | 4642.76 | 100% | 22.31 | 103579.9756
2032 | B6.33 42 11.3 | GROUND COVER | 2026-09-14 | SUD1-02-011-TDC-TS9-1-STR-FIR-2920-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from # STA-A1/43 To STA-A1/44 at Road MCB0 | 73.71 | 22.55 | 45% | 33.1695 | 747.9722
2033 | B6.33 42 11.6 | STORM WATER NETWORK: GRP Pipes 500mm (Depth: 0.0m - 1.5m) | 2026-09-14 | SUD1-02-011-TDC-TS9-1-STR-FIR-2921-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from # STA-A1/42 To STA-A1/43 at Road MCB0 | 366.63 | 59.33 | 45% | 164.9835 | 9788.4711
2034 | B6.33 42 11.9 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51m - 2.5m) | 2026-09-14 | SUD1-02-011-TDC-TS9-1-STR-FIR-2922-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from # STA-A1/41 To STA-A1/42 at Road MCB0 | 448.1 | 59.16 | 45% | 201.645 | 11929.3182
2035 | B3.33 14 13.5 | PIPEWORK-PIPES: pipe line O.D 50 mm PN 10, in depth Oto 1.5 m | 2026-09-14 | SUD1-02-011-TDC-TS9-1-PW-FIR-2923-00 | Check Coordinates level and Excavation width Bottom level and compaction for potable water pipeline (315mm) Diameter from Station STA: 1+300 TO 1+450, STA:1+650 TO 1+750, at Road MC20 | 290.97 | 250.00 | 5% | 14.5485 | 3637.125
2036 | B1.32 11 26.01 | BITUMINOUS BASE COURSE (70MM) | 2026-09-12 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2926-00 | Check Coordinates, level, thickness,Compaction and Testing for Bituminous base course layer (70mm) on Road /Carriageway from # ST: 0+300 to ST: 0+450 at Road MCG0 | 101.84 | 205.80 | 15% | 15.276 | 3143.8008
2037 | B6.33 42 11.4 | STORM WATER NETWORK: GRP Pipes 400mm (Depth: 1.51m - 2.5m) | 2026-09-14 | SUD1-02-011-TDC-TS9-1-STR-FIR-2927-00 | Inspection Gravity and Leakage test pipeline from Manhole # STA-A1/40/2 to STA-A2/24/4 at Road MCD0 | 312.31 | 63.85 | 10% | 31.231 | 1994.0994
2038 | B3.33 14 13.1 | POTABLE WATER NETWORK: HDPE Pipes 160mm Diameter (Depth 0.0m to 1.50m) | 2026-09-15 | SUD1-02-011-TDC-TS9-1-PW-FIR-2940-00 | Inspection Pressure test of potable water Pipeline (160mm) Diameter HDPE Pipes from 4+811.60 (R) to 4+811.60 (L), 5+263.35 (R)to5+263.35 (L) Road MC20 | 101.84 | 71.18 | 25% | 25.46 | 1812.2428
2039 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0.0m - 1.5m) | 2026-09-15 | SUD1-02-011-TDC-TS9-1-IRR-FIR-2941-00 | Inspection Pressure test of Road crossing Irrigation water HDPE pipe (125mm) Diameter at 4+905.5 (R) to 4+905.5 (L) Road MC20 | 179.43 | 41.39 | 10% | 17.943 | 742.6608
2040 | B6.33 42 11.10 | STORM WATER NETWORK: GRP Pipes 600mm Diameter (Depth: 1.51 to 2.50m) | 2026-09-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-2945-00 | Check Sand around GRP pipe for Storm water line from STA-STA-A1/36/2 to STA-A1/36/3 at Road MCE0(Last layer) | 461.68 | 63.80 | 45% | 207.756 | 13254.8328
2041 | B6.33 42 11.9 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51m - 2.5m) | 2026-09-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-2946-00 | Check Sand around GRP pipe for Storm water line from STA-STA-A1/36/3 to STA-A1/36/4 at Road MCE0(Last Layer) | 448.1 | 63.80 | 45% | 201.645 | 12864.951
2042 | B6.33 42 11.6 | STORM WATER NETWORK: GRP Pipes 500mm (Depth: 0.0m - 1.5m) | 2026-09-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-2947-00 | Check Sand around GRP pipe for Storm water line from STA-STA-A1/36/4 to STA-A1/36/5 at Road MCE0 (Last layer) | 366.63 | 63.80 | 45% | 164.9835 | 10525.9473
2043 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-15 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2948-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at PLOT (6), STA: 0+630 to STA: 0+680 | 22.31 | 377.24 | 100% | 22.31 | 8416.2244
2044 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-15 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2949-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at PLOT (6), STA: 0+450 to STA: 0+630 | 22.31 | 2386.18 | 100% | 22.31 | 53235.6758
2045 | B1.31 22 00.05 | Earth works & Site Grading (Subgrade) | 2026-09-16 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2950-00 | Check Coordinates level and Compaction F.D.T for (Subgrade) 2nd layer at Road/Carriageway # connection point MCZ0 to MCE0, STA: 0+000 to STA: 0+144.25 | 28.13 | 966.26 | 10% | 2.813 | 2718.0894
2046 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2951-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-21-1 to MH-12-21-1-1 at Road MCD0 | 212.41 | 78.87 | 10% | 21.241 | 1675.2777
2047 | B3.33 14 13.1 | POTABLE WATER NETWORK: HDPE Pipes 160mm Diameter (Depth 0.0m to 1.50m) | 2026-09-15 | SUD1-02-011-TDC-TS9-1-PW-FIR-2952-00 | Inspection Pressure test of potable water Pipeline HDPE Pipes (160mm) Diameter from 5+811.7 (R) to 5+811.7 (L) at Road MC20 | 101.84 | 35.59 | 25% | 25.46 | 906.1214
2048 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0.0m - 1.5m) | 2026-09-15 | SUD1-02-011-TDC-TS9-1-IRR-FIR-2953-00 | Inspection Pressure test of Road crossing Irrigation water HDPE pipe (125mm) Diameter 5+759 (R) to 5+759 (L) #Road MC20 | 179.43 | 41.39 | 10% | 17.943 | 742.6608
2049 | B6.33 42 11.20 | STORM WATER NETWORK: GRP 900m Pipes (Depth 2.51 - 3.50m) | 2026-09-21 | SUD1-02-011-TDC-TS9-1-STR-FIR-2954-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from # # STA-A1/36 to STA-A1/35 at Road MCB0 | 875.83 | 60.77 | 45% | 394.1235 | 23950.8851
2050 | B6.33 42 11.9 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51m - 2.5m) | 2026-09-21 | SUD1-02-011-TDC-TS9-1-STR-FIR-2955-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from # STA-A1/26/3 to STA-A1/26/4 at Road MCG0 | 448.1 | 63.65 | 45% | 201.645 | 12834.7043
2051 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-09-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-2956-00 | Check Sand around Storm Manhole #STA-A1/36/4 at Road MCE0(Last layer) | 12376.13 | 01 | 10% | 1237.613 | 1237.613
2052 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-09-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-2957-00 | Check Sand around Storm Manhole # STA-A1/36/3 at Road MCE0(Last layer) | 12376.13 | 01 | 10% | 1237.613 | 1237.613
2053 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-09-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-2958-00 | Check Sand around Storm Manhole # STA-A1/36/2 at Road MCE0(Last layer) | 12376.13 | 01 | 10% | 1237.613 | 1237.613
2054 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-09-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-2959-00 | Check Sand around Storm Manhole # STA-A1/36/5 at Road MCE0(Last layer) | 12376.13 | 01 | 10% | 1237.613 | 1237.613
2055 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2960-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-11-3 to MH-12-11-2 at Road MCG0 | 212.41 | 78.84 | 45% | 95.5845 | 7535.882
2056 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-15 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2961-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-11-4 to MH-12-11-3 at Road MCG0 | 212.41 | 98.86 | 45% | 95.5845 | 9449.4837
2057 | B6.33 42 11.9 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51m - 2.5m) | 2026-09-16 | SUD1-02-011-TDC-TS9-1-STR-FIR-2962-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from # STA-A1/39 to STA-A1/40 at Road MCB0 | 448.1 | 44.09 | 45% | 201.645 | 8890.5281
2058 | B6.33 42 11.9 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51m - 2.5m) | 2026-09-16 | SUD1-02-011-TDC-TS9-1-STR-FIR-2963-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from # STA-A1/40 to STA-A1/41 at Road MCB0 | 448.1 | 88.83 | 45% | 201.645 | 17912.1254
2059 | B6.33 42 11.16 | STORM WATER NETWORK: GRP 800m Pipes (Depth 1.51 - 2.50m) | 2026-09-16 | SUD1-02-011-TDC-TS9-1-STR-FIR-2964-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from # STA-A1/38 to STA-A1/37 at Road MCB0 | 639.17 | 50.50 | 45% | 287.6265 | 14525.1382
2060 | B6.33 42 11.15 | STORM WATER NETWORK: Pipes 800mm (Depth: 0m- 1.50m) | 2026-09-16 | SUD1-02-011-TDC-TS9-1-STR-FIR-2965-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from # STA-A1/39 to STA-A1/38 at Road MCB0 | 623.66 | 66.41 |  | 0 | 0
2061 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-16 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2966-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-11-4 to MH-12-11-5 at Road MCG0 | 212.41 | 98.71 | 45% | 95.5845 | 9435.146
2062 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-16 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2967-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Plot. No:-(7) STA 0+020 to 0+130 | 22.31 | 3602.18 | 100% | 22.31 | 80364.6358
2063 | 31 22 00 | STORM WATER NETWORK: Drainage works for ponds and open canals | 2026-09-15 | SUD1-02-011-TDC-TS9-1-STR-FIR-2968-00 | Check Coordinates, bottom level Road Excavation/cutting compaction for open channel trench (C5) from # STA :0 +983 STA: 1+183.51 with Connecting Storm Manholes # STA-SW-T/A1/8/22 TO STA-SW-T/A1/8/20 # at Road MC20 | 17.46 | 66.67 | 5% | 0.873 | 58.2029
2064 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-09-16 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2969-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 064 To 065 in Road MCF0 | 617.84 | 25.87 | 25% | 154.46 | 3995.8802
2065 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-09-16 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2970-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 066 To 067 in Road MCF0 | 617.84 | 26.71 | 25% | 154.46 | 4125.6266
2066 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-16 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2971-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer(Right side) at PLOT (1), STA: 0+030 to STA: 0+200 | 22.31 | 2066.37 | 100% | 22.31 | 46100.7147
2067 | B1.31 22 00.01 | Earth works & Site Grading (Road Excavation/cutting) | 2026-09-16 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2972-00 | Check Coordinates and bottom level Road Excavation/cutting upto bottom of Sub-Grade STA: 0+970 to STA: 1+025.65 at Road # MCE0 | 13.78 | 910.60 | 5% | 0.689 | 627.4034
2068 | B1.31 22 00.05 | Earth works & Site Grading (Subgrade) | 2026-09-24 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2973-01 | Check Coordinates level and Compaction F.D.T for (Subgrade) 2nd layer at Road/Carriageway# MC20, STA: 5+420 to STA: 5 +740 | 28.13 | 1885.44 | 10% | 2.813 | 5303.7427
2069 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-09-16 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2974-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 058 To 059 in Road MCG0 | 617.84 | 25.44 | 25% | 154.46 | 3929.4624
2070 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-09-16 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2975-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 060 To 061 in Road MCG0 | 617.84 | 26.71 | 25% | 154.46 | 4125.6266
2071 | B1.32 11 23.01 | AGGREGATE BASE COURSE | 2026-09-16 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2976-00 | Check Coordinates level and compaction F.D.T for (Aggregate base course) at Road /Carriageway# MCG0, STA: 0+224 to STA: 0+250 | 62.07 | 100.02 | 25% | 15.5175 | 1552.0603
2072 | B1.32 11 23.01 | AGGREGATE BASE COURSE | 2026-09-16 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2977-00 | Check Coordinates level and compaction F.D.T for (Aggregate base course) at Road /Carriageway# MCZ0, STA: 0+250 to STA: 0+447.25 | 62.07 | 780.73 | 25% | 15.5175 | 12114.9778
2073 | B1.32 11 26.01 | BITUMINOUS BASE COURSE (70MM) | 2026-09-16 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2979-00 | Check Coordinates, level, thickness,Compaction and Testing for Bituminous base course layer (70mm) on Road /Carriageway from # ST: 0+580 to ST: 0+750 at Road MCF0 | 519.88 | 233.24 | 15% | 77.982 | 18188.5217
2074 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-16 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2980-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer(Left side) at PLOT (1), STA: 0+200 to STA: 0+400 | 22.31 | 4286.59 | 100% | 22.31 | 95633.8229
2075 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-16 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2981-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-19-1 to MH-12-19-2 at Road MCE0 | 212.41 | 31.10 | 5% | 10.6205 | 330.2976
2076 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-16 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2982-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-13-1 to MH-12-13-2 at Road MCF0 | 212.41 | 31.10 | 5% | 10.6205 | 330.2976
2077 | B1.32 11 23.01 | AGGREGATE BASE COURSE | 2026-09-16 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2983-00 | Check Coordinates level and compaction F.D.T for (Aggregate base course) at Road /Carriageway# MCZ0, STA: 0+080 to STA: 0+250 | 62.07 | 662.01 | 25% | 15.5175 | 10272.7402
2078 | B3.33 14 13.5 | PIPEWORK-PIPES: pipe line O.D 50 mm PN 10, in depth Oto 1.5 m | 2026-09-21 | SUD1-02-011-TDC-TS9-1-PW-FIR-2984-00 | Check Coordinates level and Excavation width Bottom level and compaction for potable water HDPE pipelines(315mm) at Road MC10 #STA:0+925 to STA:0+975 | 101.84 | 50.00 | 5% | 5.092 | 254.6
2079 | B2.33 71 19.13.02 | Drawpit with medium duty steel cover, size 900x900x1200mm | 2026-09-16 | SUD1-02-011-TDC-TS9-1-LIT-FIR-2985-00 | Check Installation Drawpit MH-17 & MH-18 for Street Lighting in Road MCA0 | 3850.57 | 2 | 30% | 1155.171 | 2310.342
2080 | B1.32 11 26.01 | Street Lighting Cables, 4xC-16 mm2 + 1C/10 mm2 CU/XLPE/SWA/PVC | 2026-09-16 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2987-00 | Check Coordinates, level, thickness,Compaction and Testing for Bituminous base course layer (70mm) on Road /Carriageway from # ST: 0+430 to ST: 0+580 at Road MCF0 | 57.23 | 205.80 | 15% | 8.5845 | 1766.6901
2081 | B6.33 42 11.16 | Street Lighting Cables, 4xC-16 mm2 + 1C/10 mm2 CU/XLPE/SWA/PVC | 2026-09-17 | SUD1-02-011-TDC-TS9-1-STR-FIR-2988-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from # STA-A1/36 to STA-A1/37 at Road MCB0 | 57.23 | 53.90 | 45% | 25.7535 | 1388.1137
2082 | B1.31 22 00.04 | Street Lighting Cables, 4xC-16 mm2 + 1C/10 mm2 CU/XLPE/SWA/PVC | 2026-09-22 | SUD1-02-011-TDC-TS9-1-ROD-FIR-2992-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Plot. No:-(7) STA 0+350 to 0+420 | 57.23 | 1022.85 | 100% | 57.23 | 58537.7055
2083 | B2.33.71.19.13.05 | Manhole Type 3 | 2026-09-17 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2993-00 | Check Installation Manhole MH-088 & MH-089 for TELECOMMUNICATIONS Works in Road MCC0 | 7057.11 | 2 | 30% | 2117.133 | 4234.266
2084 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-09-17 | SUD1-02-011-TDC-TS9-1-TEL-FIR-2994-00 | Check Sand Bedding and Installation HDPE Pipe 3(2X50mm) From Manhole 022 To 023 for TELECOMMUNICATIONS Works in Road MCG0 | 617.84 | 39.81 | 45% | 278.028 | 11068.2947
2085 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-19 | SUD1-02-011-TDC-TS9-1-SEW-FIR-2997-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-12-11-1 to MH-12-11-2 at Road MCG0 | 212.41 | 31.10 | 5% | 10.6205 | 330.2976
2086 | B3.33 14 13.5 | PIPEWORK-PIPES: pipe line O.D 50 mm PN 10, in depth Oto 1.5 m | 2026-08-26 | SUD1-02-011-TDC-TS9-1-PW-FIR-2998-00 | Inspection Pressure test of potable water Pipeline HDPE Pipes from ST: 1+750 to ST: 2+169.08 at Road MCZ0 | 290.97 | 419.08 | 25% | 72.7425 | 30484.9269
2087 | B3.33 14 13.3 | POTABLE WATER NETWORK: HDPE Pipes 225 Diameter (Depth 0 to 1.50m) | 2026-09-02 | SUD1-02-011-TDC-TS9-1-PW-FIR-2999-00 | Inspection Pressure test of potable water Pipeline HDPE Pipes from ST: +625.00 to ST: +000.00 Road MCF0 | 179.43 | 625.00 | 25% | 44.8575 | 28035.9375
2088 | B1.31 22 00.05 | Earth works & Site Grading (Subgrade) | 2026-09-26 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3000-01 | Check Coordinates level and Compaction F.D.T for (Subgrade) 2nd layer at Road/Carriageway# MC20, STA: 5+820 to STA: 6+060 | 28.13 | 1,811.87 | 10% | 2.813 | 5096.7903
2089 | B1.32 11 26.01 | BITUMINOUS BASE COURSE (70MM) | 2026-09-21 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3006-00 | Check Coordinates, level, thickness,Compaction and Testing for Bituminous base course layer (70mm) on Road /Carriageway from # ST: 0+300 to ST: 0+430 at Road MCF0 | 519.88 | 178.36 | 15% | 77.982 | 13908.8695
2090 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-19 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3007-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at PLOT (6), STA: 0+224 to STA: 0+450 | 22.31 | 2651.25 | 100% | 22.31 | 59149.3875
2091 | B6.33 42 11.9 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51m - 2.5m) | 2026-09-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-3008-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from # STA-A1/26/4 to STA-A1/26/5 at Road MCG0 | 448.1 | 63.80 | 45% | 201.645 | 12864.951
2092 | B6.33 42 11.3 | STORM WATER NETWORK: GRP Pipes 400mm (Depth: 0m - 1.5m) | 2026-09-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-3009-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from # STA-A1/26/5 to STA-A1/26/6 at Road MCG0 | 300.67 | 64.54 | 45% | 135.3015 | 8732.3588
2093 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-19 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3010-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-11-1-1 to MH-12-11-1-2 at Road MCG0 | 212.41 | 98.86 | 45% | 95.5845 | 9449.4837
2094 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-19 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3011-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-11-1 to MH-12-11-1-1 at Road MCG0 | 212.41 | 78.87 | 45% | 95.5845 | 7538.7495
2095 | B3.33 14 13.1 | POTABLE WATER NETWORK: HDPE Pipes 160mm Diameter (Depth 0.0m to 1.50m) | 2026-09-19 | SUD1-02-011-TDC-TS9-1-PW-FIR-3012-00 | Check Compaction F.D.T for Backfilling 1st layer for Road crossing potable water HDPE pipelines (Diameter 160mm) at 4+811.60 (R) to 4+811.60 (L), 5+263.35 (R)to5+263.35 (L) #Road MC20 (Bottom Subgrade) | 101.84 | 71.18 | 10% | 10.184 | 724.8971
2096 | B3.33 14 13.1 | TSE NETWORK: 125mm Diameter (Depth: 0.0m - 1.5m) | 2026-09-19 | SUD1-02-011-TDC-TS9-1-IRR-FIR-3013-00 | Check Compaction F.D.T for Backfilling 1st layer for Road crossing 125mm O.D HDPE 4+905.5 (R) to 4+905.5 (L) at Road MC20 (Bottom Subgrade) | 101.84 | 41.39 | 10% | 10.184 | 421.5158
2097 | B6.33 42 11.3 | STORM WATER NETWORK: GRP Pipes 400mm (Depth: 0m - 1.5m) | 2026-09-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-3014-00 | Check Sand around GRP pipe for Storm water line from STA-A1/15/9 To STA-A1/15/10 at Road MCF0(Last layer) | 300.67 | 59.15 | 45% | 135.3015 | 8003.0837
2098 | B2.33.71.19.13.04 | Manhole Type 2 | 2026-09-19 | SUD1-02-011-TDC-TS9-1-TEL-FIR-3017-00 | Check Installation Manhole MH-086 for TELECOMMUNICATIONS Works in Road MCC0 | 7042.56 | 1 | 30% | 2112.768 | 2112.768
2099 | B2.33.71.19.13.05 | Manhole Type 3 | 2026-09-19 | SUD1-02-011-TDC-TS9-1-TEL-FIR-3018-00 | Check Installation Manhole MH-087 for TELECOMMUNICATIONS Works in Road MCC0 | 7057.11 | 1 | 30% | 2117.133 | 2117.133
2100 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-19 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3021-00 | Check Coordinates level and Compaction F.D.T for Embankment 9th layer at PLOT (2), STA: 0+570 to STA: 0+720 | 22.31 | 4190.59 | 100% | 22.31 | 93492.0629
2101 | B1.32 11 23.01 | AGGREGATE BASE COURSE | 2026-09-19 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3022-00 | Check Coordinates level and compaction F.D.T for (Aggregate base course) at Road /Carriageway# MCE0&MCZ0, STA: 0+00 to STA: 0+090 | 62.07 | 391.98 | 25% | 15.5175 | 6082.5496
2102 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0.0m - 1.5m) | 2026-09-21 | SUD1-02-011-TDC-TS9-1-IRR-FIR-3025-00 | Check Compaction F.D.T for Backfilling 1st layer for Road crossing 125mm O.D HDPE 5+ 759 (R) to 5+759 (L) at Road MC20 (Bottom Subgrade) | 179.43 | 41.39 | 10% | 17.943 | 742.6608
2103 | B3.33 14 13.5 | POTABLE WATER NETWORK: HOPE Pipes 315mm Diameter (Depth 0.0m to 1.50m) | 2026-09-20 | SUD1-02-011-TDC-TS9-1-PW-FIR-3026-00 | Check Sand bedding and pipe installation of potable water HDPE Pipes (315mm) from ST: [1+431.3 TO Existing] at Road MCD0 | 290.97 | 33.78 | 45% | 130.9365 | 4423.035
2104 | B3.33 14 13.6 | POT ABLE WATER NETWORK: HOPE Pipes 315 Diameter (Depth 1.51-2.5m) | 2026-09-20 | SUD1-02-011-TDC-TS9-1-PW-FIR-3027-00 | Check Sand bedding and pipe installation of potable water HDPE Pipes Diameter (315mm) from ST: [1+625.0 to 1+750.0] and at Road MCZ0 | 301.64 | 125.00 | 45% | 135.738 | 16967.25
2105 | B1.31 22 00.04 | POT ABLE WATER NETWORK: HOPE Pipes 315 Diameter (Depth 1.51-2.5m) | 2026-09-19 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3028-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at PLOT (1), STA: 0+400 to STA: 0+610 | 22.31 | 4758.26 | 100% | 22.31 | 106156.7806
2106 | B1.31 22 00.04 | POT ABLE WATER NETWORK: HDPE Pipes 315 Diameter (Depth 2.51-3.5m) | 2026-09-19 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3029-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Plot. No:-(7) STA 0+130 to 0+240 | 22.31 | 4243.79 | 100% | 22.31 | 94678.9549
2107 | B3.33 14 13.6 | POT ABLE WATER NETWORK: HDPE Pipes 315 Diameter (Depth 2.51-3.5m) | 2026-09-20 | SUD1-02-011-TDC-TS9-1-PW-FIR-3030-00 | Check Sand bedding and pipe installation of potable water HDPE Pipes Diameter (315mm) from ST: [1+431.3 to 1+475.0] at Road MCD0 | 301.64 | 43.68 | 45% | 135.738 | 5929.0358
2108 | B3.33 14 13.7 | POT ABLE WATER NETWORK: HOPE Pipes 315 Diameter (Depth 3.51m to 4.50m) | 2026-09-20 | SUD1-02-011-TDC-TS9-1-PW-FIR-3031-00 | Check Sand bedding and pipe installation of potable water HDPE Pipes Diameter (315mm) from ST: [1+575.0 to 1+625.0] at Road MCZ0 | 412.21 | 50.00 | 45% | 185.4945 | 9274.725
2109 | B1.31 22 00.04 | POT ABLE WATER NETWORK: HDPE Pipes 315 Diameter (Depth 2.51-3.5m) | 2026-09-20 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3032-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Plot. No:-(7) STA 0+040 to 0+130 | 22.31 | 3527.91 | 100% | 22.31 | 78707.6721
2110 | B6.33 42 11.9 | POTABLE WATER NETWORK: HOPE Pipes 160mm Diameter (Depth O.Om to 1.50m) | 2026-09-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-3015-00 | Check Sand around GRP pipe for Storm water line from STA-A1/30/4 to STA-A1/30/3 at Road MCF0 | 448.1 | 63.65 | 10% | 44.81 | 2852.1565
2111 | B6.33 42 11.6 | STORM WATER NETWORK: GRP Pipes 500mm (Depth: 0.0m - 1.5m) | 2026-09-19 | SUD1-02-011-TDC-TS9-1-STR-FIR-3016-00 | Check Sand around GRP pipe for Storm water line from STA-A1/30/5 to STA-A1/30/4 at Road MCF0 | 366.63 | 63.80 | 10% | 36.663 | 2339.0994
2112 | B6.33 05 39.2 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-09-21 | SUD1-02-011-TDC-TS9-1-STR-FIR-3033-00 | Check Sand around Storm Manhole # STA-A1/15/10 at Road MCF0(Last layer) | 12376.13 | 01 | 10% | 1237.613 | 1237.613
2113 | B3.33 14 13.7 | POT ABLE WATER NETWORK: HOPE Pipes 315 Diameter (Depth 3.51m to 4.50m) | 2026-09-20 | SUD1-02-011-TDC-TS9-1-PW-FIR-3034-00 | Check Sand bedding and pipe installation of potable water HDPE Pipes Diameter (315mm) from ST: [1+475.0 to 1+538.5] at Road MCD0 | 412.21 | 63.50 | 45% | 185.4945 | 11778.9007
2114 | B3.33 14 13.8 | POT ABLE WATER NETWORK: HOPE Pipes 315 Diameter (Depth 3.51m to 4.50m) | 2026-09-20 | SUD1-02-011-TDC-TS9-1-PW-FIR-3035-00 | Check Sand Bedding and Pipe installation of potable water HDPE Pipes Diameter (315mm) from ST: (1+538.50 to ST: 1+575.00) at Road MCZ0 | 481.08 | 36.48 | 45% | 216.486 | 7897.4093
2115 | B3.33 14 13.7 | POT ABLE WATER NETWORK: HOPE Pipes 315 Diameter (Depth 3.51m to 4.50m) | 2026-09-20 | SUD1-02-011-TDC-TS9-1-PW-FIR-3036-00 | Check Sand bedding and pipe installation of potable water HDPE Pipes Diameter (315mm) Crossing from ST: [0+000.0 to 1+538.5] at Road MCD0 | 412.21 | 28.26 | 45% | 185.4945 | 5242.0746
2116 | B3.33 14 13.1 | POTABLE WATER NETWORK: HDPE Pipes 160mm Diameter (Depth 0.0m to 1.50m) | 2026-09-21 | SUD1-02-011-TDC-TS9-1-PW-FIR-3039-00 | Check Compaction F.D.T for Backfilling 1st layer for Road crossing potable water HDPE pipelines (Diameter 160mm) at 5+81 1.7 (R) to 5+811 .7 (L) #Road MC20 (Bottom Subgrade) | 101.84 | 35.59 | 10% | 10.184 | 362.4486
2117 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-20 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3040-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-11-1-2 to MH-12-11-1-3 at Road MCG0 | 212.41 | 98.74 | 45% | 95.5845 | 9438.0135
2118 | B7.32 93 00.02 | LANDSCAPE WORKS: PLANTS (Tabopia) | 2026-09-21 | SUD1-02-011-TDC-TS9-1-LSP-FIR-3043-00 | Installation of landscape tree planting works as per approved drawings and specifications (Tabopia) | 1132.86 | 46.00 | 30% | 339.858 | 15633.468
2119 | B7.32 93 00.04 | LANDSCAPE WORKS: PLANTS (Cassia glauca) | 2026-09-21 | SUD1-02-011-TDC-TS9-1-LSP-FIR-3044-00 | Installation of landscape tree planting works as per approved drawings and specifications (Cassia glauca) | 1132.86 | 133.00 | 30% | 339.858 | 45201.114
2120 | B7.32 93 00.04 | LANDSCAPE WORKS: PLANTS (Cassia glauca) | 2026-09-20 | SUD1-02-011-TDC-TS9-1-LSP-FIR-3045-00 | Installation of landscape tree planting works as per approved drawings and specifications (Plumeria alba) | 1132.86 | 34.00 | 30% | 339.858 | 11555.172
2121 | 31 25 00 | Installation Curb stone L 1 | 2026-09-20 | SUD1-02-011-TDC-TS9-1-STR-FIR-3048-00 | Check inspection for Installation of stone at Pond B | 62.07 | 5572.92 | 30% | 18.621 | 103773.3433
2122 | B2.33.71.19.13.05 | Manhole Type 3 | 2026-09-20 | SUD1-02-011-TDC-TS9-1-TEL-FIR-3049-00 | Check Installation Manhole MH-116 & MH-117 & MH-118 & MH-119 for TELECOMMUNICATIONS Works in Road COL-MC10 | 7057.11 | 4 | 30% | 2117.133 | 8468.532
2123 | B1.32 11 26.01 | PIPEWORK-PIPES: pipe line 0.0 63 mm PN 10, in depth Oto 1.5 m | 2026-09-21 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3050-00 | Check Coordinates, level, thickness, Compaction and Testing for Bituminous base course layer (70mm) on Road /Carriageway from# ST: 0+224 to ST: 0+300 at Road MCF0 | 519.88 | 95.68 | 30% | 155.964 | 14922.6355
2124 | B1.32 11 26.01 | PIPEWORK-PIPES: pipe line O.D 50 mm PN 10, in depth Oto 1.5 m | 2026-09-21 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3051-00 | Check Coordinates, level, thickness,Compaction and Testing for Bituminous base course layer (70mm) on Road /Carriageway from# ST: 0+224 to ST: 0+300 at Road MCG0 | 519.88 | 95.68 | 15% | 77.982 | 7461.3178
2125 | B1.32 11 26.01 | PIPEWORK-PIPES: pipe line 0.0 32 mm PN 10, in depth Oto 1.5 m | 2026-09-21 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3052-00 | Check Coordinates, level, thickness,Compaction and Testing for Bituminous base course layer (70mm) on Road /Carriageway from# ST: 0+300 to ST: 0+447.25 at Road MCZ0 | 519.88 | 204.70 | 15% | 77.982 | 15962.9154
2126 | B1.31 22 00.04 | PIPEWORK-PIPES: pipe line O.D 25 mm PN 10, in depth Oto 1.5 m | 2026-09-22 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3053-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer at PLOT (1) (Right side), STA: 0+200 to STA: 0+400 | 22.31 | 2592.75 | 100% | 22.31 | 57844.2525
2127 | B5.33 31 00.01 | LANDSCAPE WORKS: PLANTS (Albizia lebbeck) | 2026-09-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3058-00 | Check compaction F.D.T for Trench Backfilling 2nd layer Between Manhole # MH-1-97 to MH-1-98 at Road MCC0(Bottom subgrade) | 212.41 | 78.87 | 10% | 21.241 | 1675.2777
2128 | B5.33 31 00.01 | GROUND COVER | 2026-09-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3062-00 | Check compaction F.D.T for Trench Backfilling 2nd layer Between Manhole # MH-1-93-2 to MH-1-93-3 at Road MCC0(Bottom subgrade) | 212.41 | 98.86 | 10% | 21.241 | 2099.8853
2129 | B5 33.05.13.01 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 0m- 1.50m) | 2026-09-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3063-00 | Check compaction F.D.T for Manhole Backfilling at # MH-1-88-5 at Road # MCD0(Bottom Subgrade) | 8820.42 | 01 | 10% | 882.042 | 882.042
2130 | B5 33.05.13.01 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 0m- 1.50m) | 2026-09-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3064-00 | Check compaction F.D.T for Manhole Backfilling at # MH-12-21-2 at Road # MCD0(Bottom Subgrade) | 8820.42 | 01 | 10% | 882.042 | 882.042
2131 | B5 33.05.13.01 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 0m- 1.50m) | 2026-09-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3065-00 | Check compaction F.D.T for Manhole Backfilling at # MH-12-21-3at Road # MCD0(Bottom Subgrade) | 8820.42 | 01 | 10% | 882.042 | 882.042
2132 | B5 33.05.13.03 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 1.51m-2.50m) | 2026-09-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3069-00 | Check compaction F.D.T for Manhole Backfilling 2nd layer at # MH-1-97 at Road # MCC0(Bottom subgrade) | 12377.1 | 01 | 10% | 1237.71 | 1237.71
2133 | B5 33.05.13.01 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 0m- 1.50m) | 2026-09-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3070-00 | Check compaction F.D.T for Manhole Backfilling 2nd layer at # MH-1-98 at Road # MCC0 | 8820.42 | 01 | 10% | 882.042 | 882.042
2134 | B5 33.05.13.03 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 1.51m-2.50m) | 2026-09-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3074-00 | Check compaction F.D.T for Manhole Backfilling 2nd layer at # MH-1-93-2 at Road # MCC0(Bottom subgrade) | 12377.1 | 01 | 10% | 1237.71 | 1237.71
2135 | B5 33.05.13.03 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 1.51m-2.50m) | 2026-09-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3075-00 | Check compaction F.D.T for Manhole Backfilling 2nd layer at # MH-1-93-3 at Road # MCC0(bottom subgrade) | 12377.1 | 01 | 10% | 1237.71 | 1237.71
2136 | B2.33.71.19.13.04 | Manhole Type 2 | 2026-09-21 | SUD1-02-011-TDC-TS9-1-TEL-FIR-3076-00 | Check Installation Manhole MH-052 & MH-053 & MH-090 & MH-091 & MH-120 & MH-121 for TELECOMMUNICATIONS Works in Road MCB0 & MCA0 & COL-MC10 | 7042.56 | 6 | 30% | 2112.768 | 12676.608
2137 | B5.33 31 00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Depth 0m- 1.50m) | 2026-09-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3078-00 | Check compaction F.D.T for Trench Backfilling 1st layer Between Manhole # MH-1-88-4 to MH-1-88-5 at Road MCD0(Bottomsubgrade) | 212.41 | 98.74 | 10% | 21.241 | 2097.3363
2138 | B5.33 31 00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Depth 0m- 1.50m) | 2026-09-21 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3080-00 | Check compaction F.D.T for Trench Backfilling 1st layer Between Manhole # MH-12-21-3 to MH-12-21-2 at Road MCD0(Bottom subgrade) | 212.41 | 78.85 | 10% | 21.241 | 1674.8528
2139 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-21 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3086-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer at PLOT (6), STA: 0+450 to STA: 0+610 | 22.31 | 2014.45 | 100% | 22.31 | 44942.3795
2140 | B6.33 42 11.16 | STORM WATER NETWORK: GRP 800m Pipes (Depth 1.51 - 2.50m) | 2026-09-21 | SUD1-02-011-TDC-TS9-1-STR-FIR-3087-00 | Inspection Gravity and Leakage test pipeline from Manhole # STA-A1/36 to STA-A1/37 at Road MCB0 | 639.17 | 53.90 | 10% | 63.917 | 3445.1263
2141 | B6.33 42 11.16 | STORM WATER NETWORK: GRP 800m Pipes (Depth 1.51 - 2.50m) | 2026-09-21 | SUD1-02-011-TDC-TS9-1-STR-FIR-3088-00 | Inspection Gravity and Leakage test pipeline from Manhole # STA-A1/38 to STA-A1/37 at Road MCB0 | 639.17 | 50.50 | 10% | 63.917 | 3227.8085
2142 | B6.33 42 11.15 | STORM WATER NETWORK: Pipes 800mm (Depth: 0m- 1.50m) | 2026-09-21 | SUD1-02-011-TDC-TS9-1-STR-FIR-3089-00 | Inspection Gravity and Leakage test pipeline from Manhole # STA-A1/39 to STA-A1/38 at Road MCB0 | 623.66 | 66.41 |  | 0 | 0
2143 | B6.33 42 11.9 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51m - 2.5m) | 2026-09-21 | SUD1-02-011-TDC-TS9-1-STR-FIR-3090-00 | Inspection Gravity and Leakage test pipeline from Manhole # STA-A1/40 to STA-A1/41 at Road MCB0 | 448.1 | 8.83 | 10% | 44.81 | 395.6723
2144 | B6.33 42 11.9 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51m - 2.5m) | 2026-09-21 | SUD1-02-011-TDC-TS9-1-STR-FIR-3091-00 | Inspection Gravity and Leakage test pipeline from Manhole # STA-A1/39 to STA-A1/40 at Road MCB0 | 448.1 | 44.09 | 10% | 44.81 | 1975.6729
2145 | B6.33 42 11.9 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: 1.51m - 2.5m) | 2026-09-21 | SUD1-02-011-TDC-TS9-1-STR-FIR-3092-00 | Inspection Gravity and Leakage test pipeline from Manhole # STA-A1/41 To STA-A1/42 at Road MCB0 | 448.1 | 59.16 | 10% | 44.81 | 2650.9596
2146 | B6.33 42 11.6 | STORM WATER NETWORK: GRP Pipes 500mm (Depth: 0.0m - 1.5m) | 2026-09-21 | SUD1-02-011-TDC-TS9-1-STR-FIR-3093-00 | Inspection Gravity and Leakage test pipeline from Manhole # STA-A1/42 To STA-A1/43 at Road MCB0 | 366.63 | 59.33 | 10% | 36.663 | 2175.2158
2147 | B6.33 42 11.3 | STORM WATER NETWORK: GRP Pipes 400mm (Depth: 0m - 1.5m) | 2026-09-21 | SUD1-02-011-TDC-TS9-1-STR-FIR-3094-00 | Inspection Gravity and Leakage test pipeline from Manhole # STA-A1/43 To STA-A1/44 at Road MCB0 | 300.67 | 22.55 | 10% | 30.067 | 678.0109
2148 | B6.33 42 11.23 | STORM WATER NETWORK: GRP 1000m Pipes (Depth 2.51 - 3.50m) | 2026-09-21 | SUD1-02-011-TDC-TS9-1-STR-FIR-3095-00 | Check Sand Bedding and GRP Pipe Installation for Storm water line from # STA-A1/35 to STA-A1/34at Road MCB0 | 1017.44 | 50.00 | 45% | 457.848 | 22892.4
2149 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3096-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-7-1 to MH-12-7-2 at Road MCH0 | 212.41 | 86.38 | 45% | 95.5845 | 8256.5891
2150 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3097-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-7-2 to MH-12-7-3 at Road MCH0 | 212.41 | 98.86 | 45% | 95.5845 | 9449.4837
2151 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-22 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3098-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer (Left side) at PLOT (1), STA: 0+030 to STA: 0+200 | 22.31 | 1796.23 | 100% | 22.31 | 40073.8913
2152 | B1.32 14 13.02 | Installation Curb stone L 1 | 2026-09-22 | SUD1-02-011-TDC-TS9-1-LSP-FIR-3102-00 | Installation of Curb stone L1 including backing concrete # STA A3 ,A4,A5,A7,A8, A9,A11,A12,A13,A15,A16,A17 | 51.41 | 1079.81 | 30% | 15.423 | 16653.9096
2153 | B3.33 14 13.5 | PIPEWORK-PIPES: pipe line O.D 75 mm PN 10, in depth Oto 1.5 m | 2026-09-22 | SUD1-02-011-TDC-TS9-1-PW-FIR-3103-00 | Inspection Pressure test of potable water Pipeline HDPE Pipes from ST: [1+431.3 TO Existing] at Road MCD0 | 290.97 | 33.78 | 25% | 72.7425 | 2457.2417
2154 | B3.33 14 13.6 | PIPEWORK-PIPES: pipe line 0.0 63 mm PN 10, in depth Oto 1.5 m | 2026-09-22 | SUD1-02-011-TDC-TS9-1-PW-FIR-3104-00 | Inspection Pressure test of potable water Pipeline HDPE Pipes from ST: [1+625.0 to 1+750.0] and at Road MCZ0 | 301.64 | 125.00 | 25% | 75.41 | 9426.25
2155 | B3.33 14 13.6 | PIPEWORK-PIPES: pipe line O.D 50 mm PN 10, in depth Oto 1.5 m | 2026-09-22 | SUD1-02-011-TDC-TS9-1-PW-FIR-3105-00 | Inspection Pressure test of potable water Pipeline HDPE Pipes from ST: [1+431.3 to 1+475.0] at Road MCD0 | 301.64 | 43.68 | 25% | 75.41 | 3293.9088
2156 | B3.33 14 13.7 | PIPEWORK-PIPES: pipe line 0.0 32 mm PN 10, in depth Oto 1.5 m | 2026-09-22 | SUD1-02-011-TDC-TS9-1-PW-FIR-3106-00 | Inspection Pressure test of potable water Pipeline HDPE Pipes from ST: [1+575.0 to 1+625.0] at Road MCZ0 | 412.21 | 50.00 | 25% | 103.0525 | 5152.625
2157 | B3.33 14 13.8 | PIPEWORK-PIPES: pipe line O.D 25 mm PN 10, in depth Oto 1.5 m | 2026-09-22 | SUD1-02-011-TDC-TS9-1-PW-FIR-3107-00 | Inspection Pressure test of potable water Pipeline HDPE Pipes from ST: [1+538.50 to ST: 1+575.00] at Road MCZ0 |  | 36.48 | 25% | 0 | 0
2158 | B3.33 14 13.7 | LANDSCAPE WORKS: PLANTS (Albizia lebbeck) | 2026-09-22 | SUD1-02-011-TDC-TS9-1-PW-FIR-3108-00 | Inspection Pressure test of potable water Pipeline HDPE Pipes from ST: [0+000.0 to 1+538.5] at Road MCD0 | 412.21 | 28.26 | 25% | 103.0525 | 2912.2636
2159 | B3.33 14 13.7 | POT ABLE WATER NETWORK: HOPE Pipes 315 Diameter (Depth 3.51m to 4.50m) | 2026-09-22 | SUD1-02-011-TDC-TS9-1-PW-FIR-3109-00 | Inspection Pressure test of potable water Pipeline HDPE Pipes from ST: [1+475.0 to 1+538.5] at Road MCD0 | 412.21 | 63.50 | 25% | 103.0525 | 6543.8337
2160 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3110-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-11-1 to MH-12-11-1-1 at Road MCG0 | 212.41 | 78.87 | 10% | 21.241 | 1675.2777
2161 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3111-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-11-3 to MH-12-11-2 at Road MCG0 | 212.41 | 78.84 | 10% | 21.241 | 1674.6404
2162 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3112-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-11-4 to MH-12-11-3 at Road MCG0 | 212.41 | 98.86 | 10% | 21.241 | 2099.8853
2163 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3113-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-11-4 to MH-12-11-5 at Road MCG0 | 212.41 | 98.71 | 10% | 21.241 | 2096.6991
2164 | B7.33.14.11.01 | PIPEWORK-PIPES: pipe line O.D 75 mm PN 10, in depth Oto 1.5 m | 2026-09-22 | SUD1-02-011-TDC-TS9-1-LSP-FIR-3114-00 | Check coordinate level, Excavation, Sand bedding, Pipe installation,Testing and Backfilling last layer of O.D 75 mm PN 10 pipe | 52.38 | 153.00 | 45% | 23.571 | 3606.363
2165 | B7.33.14.11.02 | PIPEWORK-PIPES: pipe line 0.0 63 mm PN 10, in depth Oto 1.5 m | 2026-09-22 | SUD1-02-011-TDC-TS9-1-LSP-FIR-3115-00 | Check coordinate level, Excavation, Sand bedding, Pipe installation, Testing and Backfilling last layer of O.D 63 mm PN 10 pipe | 45.59 | 114.00 | 45% | 20.5155 | 2338.767
2166 | B7.33.14.11.03 | PIPEWORK-PIPES: pipe line O.D 50 mm PN 10, in depth Oto 1.5 m | 2026-09-22 | SUD1-02-011-TDC-TS9-1-LSP-FIR-3116-00 | Check coordinate level, Excavation, Sand bedding, Pipe installation, Testing and Backfilling last layer of O.D 50 mm PN 10 pipe | 38.8 | 185.00 | 45% | 17.46 | 3230.1
2167 | B7.33.14.11.04 | PIPEWORK-PIPES: pipe line 0.0 32 mm PN 10, in depth Oto 1.5 m | 2026-09-22 | SUD1-02-011-TDC-TS9-1-LSP-FIR-3117-00 | Check coordinate level, Excavation, Sand bedding, Pipe installation, Testing and Backfilling last layer of O.D 32 mm PN 10 pipe | 31.04 | 189.00 | 45% | 13.968 | 2639.952
2168 | B7.33.14.11.05 | PIPEWORK-PIPES: pipe line O.D 25 mm PN 10, in depth Oto 1.5 m | 2026-09-22 | SUD1-02-011-TDC-TS9-1-LSP-FIR-3118-00 | Check coordinate level, Excavation, Sand bedding, Pipe installation, Testing and Backfilling last layer of O.D 25 mm PN 10 pipe | 29.1 | 1072.00 | 45% | 13.095 | 14037.84
2169 | B2.33.71.19.13.04 | Manhole Type 2 | 2026-09-22 | SUD1-02-011-TDC-TS9-1-TEL-FIR-3119-00 | Check Installation Manhole MH-080 & MH-085 for TELECOMMUNICATIONS Works in Road MCB0 & MCD0 | 7042.56 | 2 | 30% | 2112.768 | 4225.536
2170 | B2.33.71.19.13.05 | Manhole Type 3 | 2026-09-22 | SUD1-02-011-TDC-TS9-1-TEL-FIR-3120-00 | Check Installation Manhole MH-081 & MH-082 & MH-083 & MH-084 for TELECOMMUNICATIONS Works in Road MCD0 & MCB0 | 7057.11 | 4 | 30% | 2117.133 | 8468.532
2171 | B5.33.05.13.05 | SEWERAGE NETWORK: - Manhole Depth (2.51 to 3.5m) Internal Diameter :-1200mm | 2026-09-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3121-00 | Check internal Finishing, Benching, steps, cover and joint finishes work for Installed manhole # MH-51-1, at Road # MCE0 | 15848.43 | 01 | 0% | 0 | 0
2172 | B5 33.05.13.05 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm | 2026-09-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3122-00 | Check internal Finishing, Benching, steps, cover and joint finishes work for Installed manhole # MH-51-2 at Road MCE0 | 15848.43 | 01 | 0% | 0 | 0
2173 | B5 33.05.13.05 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm | 2026-09-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3123-00 | Check internal Finishing, Benching, steps, cover and joint finishes work for Installed manhole # MH-51-3 at Road MCE0 | 15848.43 | 01 | 0% | 0 | 0
2174 | B5 33.05.13.03 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 1.51m-2.50m) | 2026-09-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3124-00 | Check internal Finishing, Benching, steps, cover and joint finishes work for Installed manhole # MH-51-4 at Road MCE0 | 12377.1 | 01 | 0% | 0 | 0
2175 | B5 33.05.13.03 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 1.51m-2.50m) | 2026-09-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3125-00 | Check internal Finishing, Benching, steps, cover and joint finishes work for Installed manhole # MH-51-5 at Road MCE0 | 12377.1 | 01 | 0% | 0 | 0
2176 | B5 33.05.13.03 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 1.51m-2.50m) | 2026-09-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3126-00 | Check internal Finishing, Benching, steps, cover and joint finishes work for Installed manhole # MH-51-6 at Road MCE0 | 12377.1 | 01 | 0% | 0 | 0
2177 | B5 33.05.13.07 | SEWERAGE NETWORK: Manhole (Depth 3.51 to 4.5m) Internal Diameter (1200mm) | 2026-09-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3127-00 | Check internal Finishing, Benching, steps, cover and joint finishes work for Installed manhole # MH-49-1 at Road MCE0 | 19319.76 | 01 | 0% | 0 | 0
2178 | B1.32 11 23.01 | AGGREGATE BASE COURSE | 2026-09-22 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3132-00 | Check Coordinates level and compaction F.D.T for (Aggregate base course) at Road /Carriageway# MCE0, STA: 0+750 to STA: 0+950 | 62.07 | 789.00 | 10% | 6.207 | 4897.323
2179 | 31 22 00 | STORM WATER NETWORK: Drainage works for ponds and open canals | 2026-09-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-3133-00 | Check Coordinates level, protection side slope, Bottom level Excavation/cutting and Compaction F.D.T for Pond C | 17.46 | 36753.94 | 10% | 1.746 | 64172.3792
2180 | 31 22 00 | STORM WATER NETWORK: Drainage works for ponds and open canals | 2026-09-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-3134-00 | Check Coordinates level, protection side slope, Bottom level Filling and Compaction Test F.D.T for Pond C | 17.46 | 10709.05 | 0% | 0 | 0
2181 | B1.32 11 26.01 | BITUMINOUS BASE COURSE (70MM) | 2026-09-24 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3136-00 | Check Coordinates, level, thickness,Compaction and Testing for Bituminous base course layer (70mm) on Road /Carriageway from# ST: 0+080 to ST: 0+300 at Road MCZ0 | 519.88 | 297.30 | 15% | 77.982 | 23184.0486
2182 | B1.32 11 26.01 | BITUMINOUS BASE COURSE (70MM) | 2026-09-24 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3137-00 | Check Coordinates, level, thickness,Compaction and Testing for Bituminous base course layer (70mm) on Road /Carriageway from# ST: 0+000 to ST: 0+070 at Road MCE0&MCZ0 | 519.88 | 103.29 | 15% | 77.982 | 8054.7608
2183 | B5 33.05.13.07 | SEWERAGE NETWORK: Manhole (Depth 3.51 to 4.5m) Internal Diameter (1200mm) | 2026-09-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3138-00 | Check internal Finishing, Benching, steps, cover and joint finishes work for Installed manhole # MH-49-3 at Road MCE0 | 19319.76 | 01 | 0% | 0 | 0
2184 | B5 33.05.13.07 | SEWERAGE NETWORK: Manhole (Depth 3.51 to 4.5m) Internal Diameter (1200mm) | 2026-09-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3139-00 | Check internal Finishing, Benching, steps, cover and joint finishes work for Installed manhole # MH-49-2at Road MCE0 | 19319.76 | 01 | 0% | 0 | 0
2185 | B5 33.05.13.07 | SEWERAGE NETWORK: Manhole (Depth 3.51 to 4.5m) Internal Diameter (1200mm) | 2026-09-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3140-00 | Check internal Finishing, Benching, steps, cover and joint finishes work for Installed manhole # MH- 49-4 at Road MCE0 | 19319.76 | 01 | 0% | 0 | 0
2186 | B5 33.05.13.03 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 1.51m-2.50m) | 2026-09-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3141-00 | Check internal Finishing, Benching, steps, cover and joint finishes work for Installed manhole # MH- 49-7 at Road MCE0 | 12377.1 | 01 | 0% | 0 | 0
2187 | B5 33.05.13.05 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm | 2026-09-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3142-00 | Check internal Finishing, Benching, steps, cover and joint finishes work for Installed manhole # MH-49-8 at Road MCE0 | 15848.43 | 01 | 0% | 0 | 0
2188 | B5 33.05.13.07 | SEWERAGE NETWORK: Manhole (Depth 3.51 to 4.5m) Internal Diameter (1200mm) | 2026-09-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3143-00 | Check internal Finishing, Benching, steps, cover and joint finishes work for Installed manhole # MH-49-5 at Road MCD0 | 19319.76 | 01 | 0% | 0 | 0
2189 | B5 33.05.13.06 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm With Backdrop | 2026-09-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3144-00 | Check internal Finishing, Benching, steps, cover and joint finishes work for Installed manhole # MH-49-6 at Road MCD0 | 19018.11 | 01 | 0% | 0 | 0
2190 | B5.33.05.13.03 | SEWERAGE NETWORK: - Manhole (1.51-2.50m) Internal Diameter :-1200mm | 2026-09-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3145-00 | Check internal Finishing, Benching, steps, cover and joint finishes work for Installed manhole # MH- 50-1 at Road MCD0 | 12377.1 | 01 | 0% | 0 | 0
2191 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-09-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3146-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from Manhole # MH-12-13 to MH-12-14 at Road MCB0 | 221.14 | 58.85 | 45% | 99.513 | 5856.34
2192 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-09-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3147-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from Manhole # MH-12-12 to MH-12-13 at Road MCB0 | 221.14 | 99.16 | 45% | 99.513 | 9867.7091
2193 | B5 33.31.00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 1.51m to 2.5m) | 2026-09-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3148-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from Manhole # MH-12-12 to MH-12-11 at Road MCB0 | 221.14 | 98.44 | 45% | 99.513 | 9796.0597
2194 | B8.34.14.19.53 | Power Cable Works | 2026-09-24 | SUD1-02-011-TDC-TS9-1-CCTV-FIR-3149-00 | Check Restored Power to CCTV Poles included Installation Cables from the main DB to CCTV Poles NO. (5, 6, 11) in Road KING SALMAN As per Modon Email Attached and CCTV Report | 64.98 | 542 | 25% | 16.245 | 8804.79
2195 | B2.26 05 19.01 | Street Lighting Cables, 4xC-16 mm2 + 1C/10 mm2 CU/XLPE/SWA/PVC | 2026-09-24 | SUD1-02-011-TDC-TS9-1-LIT-FIR-3150-00 | Check Sand Bedding and Laying of U/G LV Cables (4Cx16+10E) for Street Lighting Network Between Poles NO. (SLP18-07-02Y, SLP18-07-03B, SLP18-07-04R, SLP18-07-05Y, SLP18-07-06B, SLP18-07-07R. SLP18-07-08Y, SLP18-07-09B, SLP18-07-10R, SLP18-07-11Y, SLP18-07-12B, SLP18-07-13R) in Road MCG0 | 57.23 | 418 | 45% | 25.7535 | 10764.963
2196 | B7.32 93 00.01 | LANDSCAPE WORKS: PLANTS (Albizia lebbeck) | 2026-09-24 | SUD1-02-011-TDC-TS9-1-LSP-FIR-3152-00 | Installation of landscape tree planting works as per approved drawings and specifications (Albizia lebbeck) | 73.71 | 16.00 | 30% | 22.113 | 353.808
2197 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3153-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-1-80-1 to MH-108 at Road MCA0 | 212.41 | 47.10 | 45% | 95.5845 | 4502.03
2198 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3155-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-109 to MH-12-3 at Road MCA0 | 212.41 | 50.10 | 5% | 10.6205 | 532.087
2199 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3156-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-108 to MH-109 at Road MCA0 | 212.41 | 48.60 | 5% | 10.6205 | 516.1563
2200 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-22 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3157-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-80-1 to MH-108 at Road MCA0 | 212.41 | 47.10 | 5% | 10.6205 | 500.2255
2201 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3158-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-109 to MH-12-3 at Road MCA0 | 212.41 | 50.10 | 45% | 95.5845 | 4788.7835
2202 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-24 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3159-01 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-108 to MH-109 at Road MCA0 | 212.41 | 48.60 | 0% | 0 | 0
2203 | B1.32 11 23.01 | AGGREGATE BASE COURSE | 2026-09-24 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3161-00 | Check Coordinates level and compaction F.D.T for (Aggregate base course) at Road /Carriageway# MCE0, STA: 0+590 to STA: 0+750 | 62.07 | 631.20 | 15% | 9.3105 | 5876.7876
2204 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-24 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3162-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at Plot. No:-(7) STA 0+130 to 0+240 | 22.31 | 4110.72 | 100% | 22.31 | 91710.1632
2205 | B2.26 05 19.01 | Street Lighting Cables, 4xC-16 mm2 + 1C/10 mm2 CU/XLPE/SWA/PVC | 2026-09-26 | SUD1-02-011-TDC-TS9-1-LIT-FIR-3171-00 | Check Sand Bedding and Laying of U/G LV Cables (4Cx16+10E) for Street Lighting Network Between Poles NO. (SLP18-01-12B, SLP18-01-13R, SLP18-01-14Y, SLP18-01-15B) in Road MCA0 | 57.23 | 114.62 | 45% | 25.7535 | 2951.8662
2206 | B1.31 22 00.05 | Earth works & Site Grading (Subgrade) | 2026-09-26 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3172-00 | Check Coordinates level and Compaction F.D.T for (Subgrade) 2nd layer at Road/Carriageway# MC20, STA: 5+740 to STA: 5+820 | 28.13 | 516.05 | 10% | 2.813 | 1451.6486
2207 | 31 22 00 | STORM WATER NETWORK: Drainage works for ponds and open canals | 2026-09-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-3173-00 | Check Coordinates,Bottom level Filling and Compaction F.D.T for Pond B(spillway) | 17.46 | 136.04 | 0% | 0 | 0
2208 | B2.33.71.19.13.04 | Manhole Type 2 | 2026-09-26 | SUD1-02-011-TDC-TS9-1-TEL-FIR-3174-00 | Check Installation Manhole MH-034 & MH-035 & MH-036 for TELECOMMUNICATIONS Works in Road ART-MC10 & MC20 | 7042.56 | 3 | 30% | 2112.768 | 6338.304
2209 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3176-01 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-2-1 to MH-12-3 at Road MCH0 | 212.41 | 91.96 | 0% | 0 | 0
2210 | B5.33 31 00.03 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 2.51m to 3.5m) | 2026-09-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3177-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-10 to MH-12-11 at Road MCB0 | 329.77 | 68.95 | 45% | 148.3965 | 10231.9387
2211 | B5 33.31.00.03 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 2.51 m to 3.5m) | 2026-09-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3178-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-12-10 to MH-12-9 at Road MCB0 | 329.77 | 68.29 | 45% | 148.3965 | 10133.997
2212 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-27 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3179-00 | Check Coordinates level and Compaction F.D.T for Embankment at PLOT (1), STA: 0+400 to STA: 0+560 (5th layer Right side), STA: 0+610 to STA: 0+650 (3rd layer), STA: 0+780 to STA: 0+830 (3rd layer Left side) | 22.31 | 1569.97 | 100% | 22.31 | 35026.0307
2213 | 31 22 00 | STORM WATER NETWORK: Drainage works for ponds and open canals | 31 22 00 | SUD1-02-011-TDC-TS9-1-STR-FIR-3180-00 | Check Coordinates, bottom level Road Excavation/cutting compaction for open channel trench (C5) from # STA :1+300 to STA: 1+600 with Connecting Storm Manholes # STA-SW-T/A1/8/23 TO STA-SW-T/A1/8/26 # at Road MC20 | 17.46 | 403.60 | 5% | 0.873 | 352.3428
2214 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-28 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3181-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at Plot. No:-(7) STA 0+040 to 0+130 | 22.31 | 3247.79 | 100% | 22.31 | 72458.1949
2215 | B1.32 14 13.13.01 | PRECAST INTERLOCKING BLOCK PAVERS |  | SUD1-02-011-TDC-TS9-1-ROD-FIR-3182-01 | Installation of Precast interlocking block pavers 60mm thick - Interlocking block pavers for sidewalk/footpath | 59.16 | 2802.51 | 30% | 17.748 | 49738.9475
2216 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3183-00 | Inspection Gravity and Leakage test pipeline from Manhole # SW-MH-12-11-1-1 to SW-MH-12-11-1-2 at Road MCG0 | 212.41 | 98.86 | 10% | 21.241 | 2099.8853
2217 | B5 33.31.00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Manhole Depth 0.0m to 1.5m) | 2026-09-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3184-00 | Inspection Gravity and Leakage test pipeline from Manhole # SW-MH-12-11-1-2 to SW-MH-12-11-1-3 at Road MCG0 | 212.41 | 98.74 | 10% | 21.241 | 2097.3363
2218 | B5.33 31 00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Depth 0m- 1.50m) | 2026-09-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3185-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-7-1 to MH-12-7-2 at Road MCH0 | 212.41 | 86.38 | 10% | 21.241 | 1834.7976
2219 | B5.33 31 00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Depth 0m- 1.50m) | 2026-09-27 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3186-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-7-2 to MH-12-7-3 at Road MCH0 | 212.41 | 98.86 | 10% | 21.241 | 2099.8853
2220 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: > 2.5m) | 2026-09-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-3188-00 | Check Installation of Manhole Base of STA-A1/24 at Road MCB0 | 30133.35 | 01 | 0% | 0 | 0
2221 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: > 2.5m) | 2026-09-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-3189-00 | Check Installation of Manhole Base of STA-A1/25 at Road MCB0 | 30133.35 | 01 | 0% | 0 | 0
2222 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: > 2.5m) | 2026-09-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-3190-00 | Check Installation of Manhole Base of STA-A1/26 at Road MCB0 | 30133.35 | 01 | 0% | 0 | 0
2223 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: > 2.5m) | 2026-09-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-3191-00 | Check Installation of Manhole Base of STA-A1/27 at Road MCB0 | 30133.35 | 01 | 0% | 0 | 0
2224 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: > 2.5m) | 2026-09-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-3192-00 | Check Installation of Manhole Base STA-A1/28 at Road MCB0 | 30133.35 | 01 | 0% | 0 | 0
2225 | B6.33 05 39.9 | STORM WATER NETWORK: Manhole Diameter :-2000mm (Depth: > 2.5m) | 2026-09-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-3193-00 | Check Installation of Manhole Base STA-A1/29 at Road MCB0 | 30133.35 | 01 | 0% | 0 | 0
2226 | B2.26 05 19.01 | Street Lighting Cables, 4xC-16 mm2 + 1C/10 mm2 CU/XLPE/SWA/PVC | 2026-09-28 | SUD1-02-011-TDC-TS9-1-LIT-FIR-3194-00 | Check Sand Bedding and Laying of U/G LV Cables (4Cx16+10E) for Street Lighting Network Between Poles NO. (SLP18-07-13R, SLP18-07-14Y, SLP18-07-15B, SLP18-07-16R, SLP18-05-19Y, SLP18-05-20B) in Road MCG0 | 57.23 | 152.35 | 45% | 25.7535 | 3923.5457
2227 | B1.32 11 26.01 | BITUMINOUS BASE COURSE (70MM) | 2026-09-23 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3195-00 | Check Coordinates, level, thickness,Compaction and Testing for Bituminous base course layer (70mm) on Road /Carriageway from# ST: 0+800 to ST: 0+950 at Road MCE0 | 519.88 | 205.80 | 15% | 77.982 | 16048.6956
2228 | B5.33 31 00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Depth 1.51 m to 2.5m) | 2026-09-28 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3196-00 | Check compaction F.D.T for Trench Backfilling 1st layer Between Manholes # MH 49-5 to MH 49-6 at Road MCD0(Bottom subgrade) | 221.14 | 33.69 | 10% | 22.114 | 745.0207
2229 | B3.33 14 13.7 |  | 2026-09-28 | SUD1-02-011-TDC-TS9-1-PW-FIR-3197-00 | Check Compaction F.D.T for Backfilling 1st layer for Road crossing potable water HDPE pipelines (Diameter 315mm)ST: (0+000.0 to 1+538.5] at Road MCD0 (Bottom Subgrade) |  | 28.26 | 0% | 0 | 0
2230 | B3.33 14 13.7 | POT ABLE WATER NETWORK: HOPE Pipes 315 Diameter (Depth 3.51m to 4.50m) | 2026-09-28 | SUD1-02-011-TDC-TS9-1-PW-FIR-3198-00 | Check Compaction F.D.T for Backfilling 1st layer for Road potable water HDPE pipeline (Diameter 315mm) ST: [1+475.0 to 1 +538.5] at Road MCD0 (Bottom Subgrade) | 412.21 | 63.50 | 10% | 41.221 | 2617.5335
2231 | B3.33 14 13.5 | PIPEWORK-PIPES: pipe line O.D 75 mm PN 10, in depth Oto 1.5 m | 2026-09-28 | SUD1-02-011-TDC-TS9-1-PW-FIR-3202-00 | Check Compaction F.D.T for Backfilling 1st layer for Road potable water HDPE pipeline (Diameter 315mm) ST: [1+431.3 TO Existing) at Road MCD0 (Bottom Subgrade) | 290.97 | 33.78 | 10% | 29.097 | 982.8967
2232 | B3.33 14 13.6 | PIPEWORK-PIPES: pipe line 0.0 63 mm PN 10, in depth Oto 1.5 m | 2026-09-28 | SUD1-02-011-TDC-TS9-1-PW-FIR-3203-00 | Check Compaction F.D.T for Backfilling 1st layer for Road potable water HDPE pipeline (Diameter 315mm) ST: (1 +431.3 to 1 +475.0]at Road MCD0 (Bottom Subgrade) | 301.64 | 43.68 | 10% | 30.164 | 1317.5635
2233 | B1.32 11 23.01 | AGGREGATE BASE COURSE | 2026-09-29 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3204-00 | Check Coordinates level and compaction F.D.T for (Aggregate base course) at Road /Carriageway# MCE0, STA: 0+500 to STA: 0+590 | 62.07 | 377.57 | 25% | 15.5175 | 5858.9425
2234 | B6.33 42 11.39 | STORM WATER NETWORK: GRP Pipes 1600mm (Depth: >3.50m) | 2026-09-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-3205-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/15 to STA-A1/16 at Road MCH0 | 2454.86 | 59.05 | 5% | 122.743 | 7247.9742
2235 | B6.33 42 11.39 | STORM WATER NETWORK: GRP Pipes 1600mm (Depth: >3.50m) | 2026-09-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-3206-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/16 to STA-A1/17 at Road MCH0 | 2454.86 | 63.49 | 0% | 0 | 0
2236 | B6.33 05 39.12 | STORM WATER NETWORK: Manhole diameter 2500mm Depth: (Greater > 2.50m) | 2026-09-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-3207-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/15 at Road MCH0 | 36159.44 | 01 | 0% | 0 | 0
2237 | B6.33 05 39.12 | STORM WATER NETWORK: Manhole diameter 2500mm Depth: (Greater > 2.50m) | 2026-09-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-3208-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/16 at Road MCH0 | 36159.44 | 01 | 0% | 0 | 0
2238 | B6.33 05 39.12 | STORM WATER NETWORK: Manhole diameter 2500mm Depth: (Greater > 2.50m) | 2026-09-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-3209-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/17 at Road MCH0 | 36159.44 | 01 | 0% | 0 | 0
2239 | 31 22 00 | STORM WATER NETWORK: Drainage works for ponds and open canals | 2026-09-28 | SUD1-02-011-TDC-TS9-1-STR-FIR-3216-00 | Check Coordinates,Bottom level Filling and Compaction F.D.T for Pond A(spillway) | 17.46 | 825.70 | 0% | 0 | 0
2240 | B5.33 05 13.05 | SEWERAGE NETWORK: - Manhole (Depth 2.51m to 3.5m) Internal Diameter (1200mm) | 2026-09-28 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3217-00 | Check internal Finishing, Benching, steps, cover and joint finishes work for Installed manhole # MH- 53-2 at Road MCF0 | 15848.43 | 01 | 0% | 0 | 0
2241 | B5.33 05 13.05 | SEWERAGE NETWORK: - Manhole (Depth 2.51m to 3.5m) Internal Diameter (1200mm) | 2026-09-28 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3218-00 | Check internal Finishing, Benching, steps, cover and joint finishes work for Installed manhole # MH- 53-3 at Road MCF0 | 15848.43 | 01 | 0% | 0 | 0
2242 | B5.33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m-2.50m) Internal Diameter :-1200mm | 2026-09-28 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3219-00 | Check internal Finishing, Benching, steps, cover and joint finishes work for Installed manhole # MH- 53-4 at Road MCF0 | 12377.1 | 01 | 0% | 0 | 0
2243 | B5.33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m-2.50m) Internal Diameter :-1200mm | 2026-09-28 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3220-00 | Check internal Finishing, Benching, steps, cover and joint finishes work for Installed manhole # MH- 53-5 at Road MCF0 | 12377.1 | 01 | 0% | 0 | 0
2244 | B5.33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m-2.50m) Internal Diameter :-1200mm | 2026-09-28 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3221-00 | Check internal Finishing, Benching, steps, cover and joint finishes work for Installed manhole # MH- 53-6 at Road MCF0 | 12377.1 | 01 | 0% | 0 | 0
2245 | B2.33.71.19.13.05 | Manhole Type 3 | 2026-09-29 | SUD1-02-011-TDC-TS9-1-TEL-FIR-3222-00 | Check Installation Manhole MH-008 & MH-017 & MH-019 for TELECOMMUNICATIONS Works in Road MCE0 & MCF0 | 7057.11 | 3 | 30% | 2117.133 | 6351.399
2246 | B2.33.71.19.13.04 | Manhole Type 2 | 2026-09-29 | SUD1-02-011-TDC-TS9-1-TEL-FIR-3223-00 | Check Installation Manhole MH-007 & MH-016 for TELECOMMUNICATIONS Works in Road MCE0 & MCF0 | 7042.56 | 2 | 30% | 2112.768 | 4225.536
2247 | B5 33.05.13.05 | SEWERAGE NETWORK: - Manhole Depth (2.51m to 3.5m) Internal Diameter :-1200mm | 2026-09-28 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3224-00 | Check internal Finishing, Benching, steps, cover and joint finishes work for Installed manhole # MH- 53-1 at Road MCF0 | 15848.43 | 01 | 0% | 0 | 0
2248 | B3.33 14 13.3 | POTABLE WATER NETWORK: HDPE Pipes 225 Diameter (Depth 0 to 1.50m) | 2026-09-28 | SUD1-02-011-TDC-TS9-1-PW-FIR-3225-00 | Inspection Pressure test of potable water Pipeline HDPE Pipes (225mm) from ST: +000.00 & ST: 475.00 Road MCE0 | 179.43 | 475.00 | 15% | 26.9145 | 12784.3875
2249 | B5 33.05.13.05 |  | 2026-10-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3226-00 | Check Installation of Rings and Flat slab MH-1-92 at Road MCC0 |  | 01 | 0% | 0 | 0
2250 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-29 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3227-00 | Check Coordinates level and Compaction F.D.T for Embankment 10th layer at PLOT (2), STA: 0+560 to STA: 0+700 | 22.31 | 2998.36 | 100% | 22.31 | 66893.4116
2251 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-29 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3230-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at PLOT (6), STA: 0+190 to STA: 0+290 | 22.31 | 9621.29 | 100% | 22.31 | 214650.9799
2252 | 31 22 00 | STORM WATER NETWORK: Drainage works for ponds and open canals | 2026-09-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-3233-00 | Check Coordinates level, protection side slope, Bottom level Filling and Compaction Test F.D.T for Pond C (RAMP) | 17.46 | 203.94 | 0% | 0 | 0
2253 | B1.31 22 00.05 | Earth works & Site Grading (Subgrade) | 2026-09-29 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3234-00 | Check Coordinates level and Compaction F.D.T for (Subgrade) 2nd layer at Road/Carriageway## MC20, STA: 5+000 to STA: 5+250 | 28.13 | 1473.00 | 10% | 2.813 | 4143.549
2254 | 31 22 00 | STORM WATER NETWORK: Drainage works for ponds and open canals | 2026-09-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-3235-00 | Check Coordinates level, protection side slope, Bottom level Filling and Compaction Test F.D.T for Pond A (RAMP) | 17.46 | 209.62 | 0% | 0 | 0
2255 | B6.33 05 39.16 | STORM WATER NETWORK: Catch Basin (Double) | 2026-09-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-3236-01 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-A1/36/1 (D) at Road MCE0 | 12444.99 | 1.00 | 0% | 0 | 0
2256 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-09-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-3237-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-A1/36/1 (S) at Road MCE0 | 5124.07 | 1.00 | 0% | 0 | 0
2257 | B6.33 05 39.16 | STORM WATER NETWORK: Catch Basin (Double) | 2026-09-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-3238-01 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-A1/36/2 (D) at Road MCE0 | 12444.99 | 1.00 | 0% | 0 | 0
2258 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-09-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-3239-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-A1/36/2 (S) at Road MCE0 | 5124.07 | 1.00 | 0% | 0 | 0
2259 | B6.33 05 39.16 | STORM WATER NETWORK: Catch Basin (Double) | 2026-09-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-3240-01 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-A1/36/3 (D) at Road MCE0 | 12444.99 | 1.00 | 0% | 0 | 0
2260 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-09-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-3241-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-A1/36/3 (S) at Road MCE0 | 5124.07 | 1.00 | 0% | 0 | 0
2261 | B6.33 05 39.16 | STORM WATER NETWORK: Catch Basin (Double) | 2026-09-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-3242-001 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-A1/36/4 (D) at Road MCE0 | 12444.99 | 1.00 | 0% | 0 | 0
2262 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-09-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-3243-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-A1/36/4 (S) at Road MCE0 | 5124.07 | 1.00 | 0% | 0 | 0
2263 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-09-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-3244-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-A1/36/5 (S) at Road MCE0 | 5124.07 | 1.00 | 0% | 0 | 0
2264 | B2.33.71.19.13.04 | Manhole Type 2 | 2026-09-29 | SUD1-02-011-TDC-TS9-1-TEL-FIR-3245-00 | Check Installation Manhole MH-115 for TELECOMMUNICATIONS Works in Road COL-MC10 | 7042.56 | 1.00 | 30% | 2112.768 | 2112.768
2265 | 31 22 00 | STORM WATER NETWORK: Drainage works for ponds and open canals | 2026-09-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-3247-00 | Check Coordinates level, protection side slope, Bottom level Filling and Compaction Test F.D.T for Pond B (RAMP) | 17.46 | 139.30 | 0% | 0 | 0
2266 | B7.32 92 00.01 | GROUND COVER | 2026-09-29 | SUD1-02-011-TDC-TS9-1-LSP-FIR-3248-00 | Installation of Grass From STA:0+00 to 0+170 | 73.71 | 3,476.97 | 30% | 22.113 | 76886.2376
2267 | B6.33 05 39.16 | STORM WATER NETWORK: Catch Basin (Double) | 2026-09-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-3252-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-A1/19/1 (D) at Road MCE0 | 12444.99 | 1.00 | 0% | 0 | 0
2268 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-09-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-3253-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-A1/19/1 (S) at Road MCE0 | 5124.07 | 1.00 | 0% | 0 | 0
2269 | B6.33 05 39.16 | STORM WATER NETWORK: Catch Basin (Double) | 2026-09-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-3254-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-A2/19/(D) at Road MCE0 | 12444.99 | 1.00 | 0% | 0 | 0
2270 | B6.33 05 39.15 | STORM WATER NETWORK: - Catch Basin Single | 2026-09-29 | SUD1-02-011-TDC-TS9-1-STR-FIR-3255-00 | Check Coordinates level and Excavation width Bottom level and compaction for catch Basin CB-A2/19 B (S) at Road MCE0 | 5124.07 | 1.00 | 0% | 0 | 0
2271 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-09-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-3256-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-A1/36/1 (S) to CB-A1/36/1 (D) at Road MCE0 | 377.3 | 31.43 | 0% | 0 | 0
2272 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-09-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-3257-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-A1/36/2 (S) to CB-A1/36/2(D) at Road MCE0 | 377.3 | 31.46 | 0% | 0 | 0
2273 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-09-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-3258-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-A1/36/3 (S) to CB-A1/36/3 (D)at Road MCE0 | 377.3 | 31.18 | 0% | 0 | 0
2274 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-09-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-3259-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-A1/36/4 (S) to CB-A1/36/4 (D) at Road MCE0 | 377.3 | 31.25 | 0% | 0 | 0
2275 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-09-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-3260-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-A1/19/1 (S) to CB-A1/19/1 (D) at Road MCE0 | 377.3 | 31.36 | 0% | 0 | 0
2276 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-09-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-3261-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Catch basin # CB-A2/19 A (S)to CB-A2/19 (D) at Road MCE0 | 377.3 | 28.54 | 0% | 0 | 0
2277 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes with DIA 400mm for Catch Basin | 2026-09-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-3262-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from MH # STA-A1/36/1 to CB-A1/36/1 (D) at Road MCE0 | 602.32 | 2.1 | 0% | 0 | 0
2278 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes with DIA 400mm for Catch Basin | 2026-09-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-3263-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from MH # STA-A1/36/2 to CB-A1/36/2 (D) at Road MCE0 | 602.32 | 2.49 | 0% | 0 | 0
2279 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes with DIA 400mm for Catch Basin | 2026-09-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-3264-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from MH # STA-A1/36/3 to CB-A1/36/3 (D)at Road MCE0 | 602.32 | 2.49 | 0% | 0 | 0
2280 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes with DIA 400mm for Catch Basin | 2026-09-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-3265-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from MH # STA-A1/36/4 to CB-A1/36/4 (D) at Road MCE0 | 602.32 | 2.49 | 0% | 0 | 0
2281 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-09-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-3266-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from MH # STA-A1/36/5 to CB-A1/36/5 (S) at Road MCE0 | 377.3 | 2.59 | 0% | 0 | 0
2282 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes with DIA 400mm for Catch Basin | 2026-09-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-3267-01 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from MH # STA-A2/19/1 to CB-A1/19/1 (D) at Road MCE0 | 602.32 | 2.29 | 0% | 0 | 0
2283 | B6.33 42 11.2 | STORM WATER NETWORK: UPVC Pipes with DIA 400mm for Catch Basin | 2026-09-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-3268-01 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from MH # STA-A2/19 to CB-A2/19 (D) at Road MCE0 | 602.32 | 2.58 | 0% | 0 | 0
2284 | B5.33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m-2.50m) Internal Diameter :-1200mm | 2026-09-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3269-00 | Check Installation of Flat slab # MH-12-19-4 at Road MCE0. | 12377.1 | 01 | 0% | 0 | 0
2285 | B5.33 05 13.01 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 0-1.50m) | 2026-09-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3270-00 | Check Installation of Flat Slab # MH-12-19-5 at Road MCE0. | 8820.42 | 01 | 0% | 0 | 0
2286 | B5.33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m-2.50m) Internal Diameter :-1200mm | 2026-09-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3271-00 | Check Installation of Flat Slab # MH-12-19-2 at Road MCE0 | 12377.1 | 01 | 0% | 0 | 0
2287 | B5.33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m-2.50m) Internal Diameter :-1200mm | 2026-09-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3272-00 | Check Installation of Flat Slab # MH-12-19-3 at Road MCE0. | 12377.1 | 01 | 0% | 0 | 0
2288 | B6.33 42 11.1 | STORM WATER NETWORK: Manhole Diameter :-1200mm (Depth: | 2026-09-30 | SUD1-02-011-TDC-TS9-1-STR-FIR-3273-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from MH # STA-A2/19 to CB-A2/19 B (S) at Road MCE0 | 377.3 | 29.13 | 0% | 0 | 0
2289 | B5.33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m-2.50m) Internal Diameter :-1200mm | 2026-09-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3275-00 | Check Installation of Flat Slab # MH-12-19-1-1 at Road MCE0. | 12377.1 | 01 | 0% | 0 | 0
2290 | B1.31 22 00.04 | Earth works & Site Grading | 2026-09-30 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3274-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Plot. No:-(7) STA 0+240 to 0+330 | 22.31 | 2664.37 | 100% | 22.31 | 59442.0947
2291 | B5.33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m-2.50m) Internal Diameter :-1200mm | 2026-09-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3276-00 | Check Installation of Flat Slab # MH-12-19-1-2 at Road MCE0. | 12377.1 | 01 | 0% | 0 | 0
2292 | B5 33.05.13.01 | SEWER NETWORK: Manhole Diameter 1200mm (Depth: 0m- 1.50m) | 2026-09-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3277-00 | Check Installation of Flat Slab # MH- 12-19-1-3 at Road MCE0 | 8820.42 | 01 | 0% | 0 | 0
2293 | B1.31 22 00.04 | Earth works & Site Grading | 2026-10-01 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3278-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer at Plot (9), STA: 0+040 to STA: 0+200 | 22.31 | 4945.26 | 100% | 22.31 | 110328.7506
2294 | B1.31 22 00.04 | Earth works & Site Grading | 2026-10-05 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3279-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer for Plot. No:-(8) # STA:0+160 to STA:0+320 at Zone A | 22.31 | 6643.69 | 100% | 22.31 | 148220.7239
2295 | B5.33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m-2.50m) Internal Diameter :-1200mm | 2026-09-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3297-00 | Check Installation of Flat Slab # MH-12-13-2 at Road MCF0. | 12377.1 | 01 | 0% | 0 | 0
2296 | B5.33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m-2.50m) Internal Diameter :-1200mm | 2026-09-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3298-00 | Check Installation of Flat Slab # MH-12-13-3 at Road MCF0 | 12377.1 | 01 | 0% | 0 | 0
2297 | B5.33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m-2.50m) Internal Diameter :-1200mm | 2026-09-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3299-00 | Check Installation of Flat Slab # MH-12-13-4 at Road MCF0. | 12377.1 | 01 | 0% | 0 | 0
2298 | B5.33 05 13.01 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 0-1.50m) | 2026-09-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3300-00 | Check Installation of Flat Slab # MH-12-13-5 at Road MCF0. | 8820.42 | 01 | 0% | 0 | 0
2299 | B5.33 05.13.03 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 1.51-2.50m) | 2026-09-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3301-00 | Check Installation of Flat Slab # MH-12-11-2 at Road MCG0. | 12377.1 | 01 | 0% | 0 | 0
2300 | B5 33.31.00.03 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 2.51 m to 3.5m) | 2026-09-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3302-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-10 to MH-12-9 at Road MCB0 | 329.77 | 68.29 | 10% | 32.977 | 2251.9993
2301 | B5 33.31.00.03 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (Depth 2.51 m to 3.5m) | 2026-09-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3303-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-10 to MH-12-11 at Road MCB0 | 329.77 | 68.95 | 10% | 32.977 | 2273.7641
2302 | B4.33 14 13.3 | TSE NETWORK: 125mm Diameter (Depth: 0.0m - 1.5m) | 2026-09-30 | SUD1-02-011-TDC-TS9-1-IRR-FIR-3305-00 | Check Sand bedding and pipe installation of Road crossing Irrigation water 125mm O.D HDPE Pipes at 2+952.5 (R) to 2+952.5 (L) Road MC10 | 179.43 | 54.00 | 45% | 80.7435 | 4360.149
2303 | B3.33 14 13.1 | POTABLE WATER NETWORK: HDPE Pipes 160mm Diameter (Depth 0.0m to 1.50m) | 2026-09-30 | SUD1-02-011-TDC-TS9-1-PW-FIR-3306-00 | Check Sand bedding and pipe installation of Road crossing potable water HDPE Pipes (Diameter 160mm) at ST: 2+952.5 (R) to ST:2+952.5(L), Road MC10 | 101.84 | 52.00 | 45% | 45.828 | 2383.056
2304 | B5 33 31 00.03 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (2.51 m to 3.5m) | 2026-09-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3307-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-1-73 to MH-1-74 at Road MCA0 | 329.77 | 43.43 | 0% | 0 | 0
2305 | B5 33 31 00.02 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (1.51 m to 2.5m) | 2026-09-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3308-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-1-74 to MH-1-75 at Road MCA0 | 221.14 | 26.34 | 0% | 0 | 0
2306 | B5 33 31 00.02 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (1.51 m to 2.5m) | 2026-09-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3309-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-1-75 to MH-1-76 at Road MCA0 | 221.14 | 26.43 | 0% | 0 | 0
2307 | B5 33 31 00.02 | SEWERAGE NETWORK: GRP Pipes 200mm Diameter (1.51 m to 2.5m) | 2026-09-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3310-00 | Check Sand Bedding and GRP Pipe Installation for Sewerage line from manhole # MH-1-76 to MH-1-77at Road MCA0 | 221.14 | 19.44 | 0% | 0 | 0
2308 | B1.31 22 00.05 | Earth works & Site Grading (Subgrade) | 2026-09-30 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3311-00 | Check Coordinates level and Compaction F.D.T for (Subgrade) 2nd layer at Road /Carriageway #MC20, STA: 4+860 to STA: 5+000 | 28.13 | 824.88 | 10% | 2.813 | 2320.3874
2309 | B5.33 31 00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Depth 1.51 m to 2.5m) | 2026-09-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3314-00 | Check compaction F.D.T for Trench Backfilling 2nd layer Between Manholes # MH 49-7 to MH 49-8 at Road MCE0(Bottom subgrade) | 221.14 | 48.80 | 10% | 22.114 | 1079.1632
2310 | B3.33 14 13.7 | POT ABLE WATER NETWORK: HOPE Pipes 315 Diameter (Depth 3.51m to 4.50m) | 2026-09-30 | SUD1-02-011-TDC-TS9-1-PW-FIR-3315-00 | Check Compaction F.D.T for Backfilling 2nd layer for Road potable water HDPE pipeline (Diameter 315mm) ST: [1 +575.0 to 1 +625.0] at Road MCZ0(Bottom subgrade) | 412.21 | 50.00 | 10% | 41.221 | 2061.05
2311 | B7.32 92 00.01 |  | 2026-10-03 | SUD1-02-011-TDC-TS9-1-LSP-FIR-3319-00 | Installation of Grass From STA:0+170 to 0+840 |  | 7,523.03 | 0% | 0 | 0
2312 | B1.31 22 00.04 | Earth works & Site Grading | 2026-10-01 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3320-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer at PLOT (6), STA: 0+224 to STA: 0+450 | 22.31 | 2730.67 | 100% | 22.31 | 60921.2477
2313 | B5.33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m-2.50m) Internal Diameter :-1200mm | 2026-10-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3321-00 | Check Installation of Flat Slab # MH-12-11-3 at Road MCG0. | 12377.1 | 01 | 0% | 0 | 0
2314 | B5.33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m-2.50m) Internal Diameter :-1200mm | 2026-10-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3322-00 | Check Installation of Flat Slab # MH-12-11-4 at Road MCG0. | 12377.1 | 01 | 0% | 0 | 0
2315 | B5.33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m-2.50m) Internal Diameter :-1200mm | 2026-10-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3323-00 | Check Installation of Flat Slab # MH-12-11-1-2 at Road MCG0. | 12377.1 | 01 | 0% | 0 | 0
2316 | B6.33 05 39.2 |  | 2026-10-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-3324-00 | Check Installation of Manhole Base of STA-A1/30/5 at Road MCF0 |  | 01 | 0% | 0 | 0
2317 | B5.33 05 13.03 |  | 2026-10-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-3325-00 | Check Installation of Manhole Base (Rings not required) of STA-A1/26/6 at Road MCG0, |  | 01 | 0% | 0 | 0
2318 | B6.33 05 39.9 |  | 2026-10-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-3326-00 | Check Installation of Manhole Base of STA-A1/32 at Road MCB0, |  | 01 | 0% | 0 | 0
2319 | B6.33 05 39.62 |  | 2026-10-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-3327-00 | Check Installation of Manhole Base # STA-A1/37 at Road MCB0, |  | 01 | 0% | 0 | 0
2320 | B1.31 22 00.05 | Earth works & Site Grading (Subgrade) | 2026-10-01 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3328-00 | Check Coordinates level and Compaction F.D.T for (Subgrade) 2nd layer at Road/Carriageway# MCD0, STA: 0+030 to STA: 0+180 | 28.13 | 869.37 | 10% | 2.813 | 2445.5378
2321 | B6.33 05 39.6 |  | 2026-10-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-3329-00 | Check Installation of Manhole Base # STA-A1/36 at Road MCB0, |  | 01 | 0% | 0 | 0
2322 | B6.33 05 39.9 |  | 2026-10-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-3330-00 | Check Installation of Manhole Base # STA-A1/35 at Road MCB0, |  | 01 | 0% | 0 | 0
2323 | B6.33 05 39.9 |  | 2026-10-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-3331-00 | Check Installation of Manhole Base # STA-A1/34 at Road MCB0, |  | 01 | 0% | 0 | 0
2324 | B6.33 05 39.9 |  | 2026-10-01 | SUD1-02-011-TDC-TS9-1-STR-FIR-3332-00 | Check Installation of Manhole Base # STA-A1/31 at Road MCB0, |  | 01 | 0% | 0 | 0
2325 | B5.33 05 13.05 |  | 2026-10-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3333-00 | Check Installation of Manhole Base MH-12-10 at Road MCB0. |  | 01 | 0% | 0 | 0
2326 | B6.33 05 39.1 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 0-1.50m) | 2026-10-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3334-00 | Check Installation of Flat Slab MH-12-11-1-3 at Road MCG0. | 8820.42 | 01 | 0%
2327 | B6.33 05 39.1 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 0-1.50m) | 2026-10-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3335-00 | Check Installation of Rings & Flat Slab MH-12-11-5 at Road MCG0. | 8820.42 | 01 | 0% | 0 | 0
2328 | B2.26 05 19.02 | Street Lighting Cables, 4xC-25 mm² + 1C/16 mm² CU/XLPE/SWA/PVC | 2026-09-30 | SUD1-02-011-TDC-TS9-1-LIT-FIR-3336-00 | Check Sand Bedding and Laying of U/G LV Cables (4Cx25+16E) for Bollard Lighting Network in landscape Area near Modon Office | 81.47 | 500 | 45% | 36.6615 | 18330.75
2329 | B6.33 05 39.2 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 1.51-2.5) | 2026-09-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3337-00 | Check Installation of Rings & Flat Slab MH-12-11-1 at Road MCG0. | 12376.13 | 01 | 0% | 0 | 0
2330 | B6.33 05 39.2 | SEWER NETWORK: Manhole Diameter:-1200mm (Depth: 1.51-2.5) | 2026-09-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3338-00 | Check Installation of Rings & Flat Slab MH-12-11-1-1 at Road MCG0. | 12376.13 | 01 | 0% | 0 | 0
2331 | B5.33 05 13.05 |  | 2026-10-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3339-00 | Check Installation of Manhole Base MH-12-9 at Road MCB0. |  | 01 | 0% | 0 | 0
2332 | B3.33 14 19.01 |  | 2026-08-11 | SUD1-02-011-TDC-TS9-1-PW-FIR-3346-00 | Check Coordinates level and installation of Buried Gate Valves diameter 150mm for potable water line at Road MCF0 |  | 2 | 0% | 0 | 0
2333 | B3.33 14 19.02 |  | 2026-08-29 | SUD1-02-011-TDC-TS9-1-PW-FIR-3347-00 | Check Coordinates level and installation of Buried Gate Valves diameter 200mm for potable water line at Road MCF0 |  | 3 | 0% | 0 | 0
2334 | B3.33 14 13.1 |  | 2026-10-04 | SUD1-02-011-TDC-TS9-1-PW-FIR-3348-00 | Inspection Pressure test of Road crossing potable water Pipeline HDPE Pipes(160mm) from ST:2+952.5(R) to ST:2+952.5(L) Road MC10 |  | 52 | 0% | 0 | 0
2335 | B4.33 14 13.3 |  | 2026-10-04 | SUD1-02-011-TDC-TS9-1-IRR-FIR-3349-00 | Inspection Pressure test of Road crossing Irrigation water HDPE pipe (Diameter 125mm) at ST: 2+952.5(R) to ST: 2+952.5(L) at Road MC10 |  | 54 | 0% | 0 | 0
2336 | B3.33 14 19.01 |  | 2026-08-11 | SUD1-02-011-TDC-TS9-1-PW-FIR-3350-00 | Check Coordinates level and installation of Buried Gate Valves diameter 150mm for potable water line at Road MCE0 |  | 2 | 0% | 0 | 0
2337 | B3.33 14 19.02 |  | 2026-08-29 | SUD1-02-011-TDC-TS9-1-PW-FIR-3351-00 | Check Coordinates level and installation of Buried Gate Valves diameter 200mm for potable water line at Road MCE0 |  | 3 | 0% | 0 | 0
2338 | B3.33 14 13.5 |  | 2026-10-05 | SUD1-02-011-TDC-TS9-1-PW-FIR-3353-00 | Check Sand bedding and pipe installation of potable water HDPE Pipes (Diameter 315mm) at STA:0+925 to STA:0+975, Road MC10 |  | 50.00 | 0% | 0 | 0
2339 | B3.33 14 19.01 |  | 2026-08-31 | SUD1-02-011-TDC-TS9-1-PW-FIR-3354-00 | Inspection Pressure Test of Buried Gate Valves diameter 150mm for potable water line at Road MCG0,MCF0,MCE0 |  | 6 | 0% | 0 | 0
2340 | B3.33 14 19.02 |  | 2026-08-31 | SUD1-02-011-TDC-TS9-1-PW-FIR-3355-00 | Inspection Pressure Test of Buried Gate Valves diameter 200mm for potable water line at Road MCG0,MCFO,MCEO |  | 9 | 0% | 0 | 0
2341 | B3.33 1413.5 |  | 2026-10-05 | SUD1-02-011-TDC-TS9-1-PW-FIR-3356-00 | Inspection Pressure test of potable water Pipeline HDPE Pipes (315mm) from STA:1+925 TO ST: 2+275.00 Road MC20 |  | 350 | 0% | 0 | 0
2342 | B5.33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m-2.50m) Internal Diameter :-1200mm | 2026-09-30 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3360-00 | Check Installation of Rings and Flat slab MH-12-19-1 at Road MCE0. | 12377.1 | 01 | 0% | 0 | 0
2343 | B5.33 31 00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Depth 1.51 m to 2.5m) | 2026-10-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3361-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-12 to MH-12-11 at Road MCB0 | 221.14 | 98.44 | 0% | 0 | 0
2344 | B5.33 31 00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Depth 1.51 m to 2.5m) | 2026-10-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3362-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-12 to MH-12-13 at Road MCB0 | 221.14 | 99.16 | 0% | 0 | 0
2345 | B5.33 31 00.02 | SEWERAGE NETWORK: GRP Pipes 200mm (Depth 1.51 m to 2.5m) | 2026-10-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3363-00 | Inspection Gravity and Leakage test pipeline from Manhole # MH-12-13 to MH-12-14 at Road MCB0 | 221.14 | 58.85 | 0% | 0 | 0
2346 | B5.33 05 13.07 | SEVVERAGE NETWORK: Manhole (Depth 3.51 m to 4.5m) Internal Diameter (1200mm) | 2026-10-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3364-00 | Check Coordinates level and compaction F.D.T for Backfilling 2nd layer of Manhole # MH 49-5 at Road MCE0 (Bottom subgrade) | 19319.76 | 01 | 0% | 0 | 0
2347 | B5.33 05 13.06 | SEVVERAGE NETWORK: Manhole (Depth 2.51 m to 3.5m) Internal Diameter (1200mm) With Back drop | 2026-10-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3365-00 | Check Coordinates level and compaction F.D.T for Backfilling 2nd layer of Manhole # MH-49-6 at Road MCD0(Bottom subgrade) | 19018.11 | 01 | 0% | 0 | 0
2348 | B5.33 05 13.03 | SEWERAGE NETWORK: - Manhole Depth (1.51m-2.50m) Internal Diameter :-1200mm | 2026-10-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3366-00 | Check Coordinates level and compaction F.D.T for Backfilling 3rd layer of Manhole # MH 49-7 at Road MCE0(Bottom subgrade) | 12377.1 | 01 | 0% | 0 | 0
2349 | B5.33 05 13.05 | SEWERAGE NETWORK: - Manhole (Depth 2.51m to 3.5m) Internal Diameter (1200mm) | 2026-10-01 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3367-00 | Check Coordinates level and compaction F.D.T for Backfilling 2st layer of Manhole # MH 49-8 at Road MCE0(Bottom subgrade) | 15848.43 | 01 | 0% | 0 | 0
2350 | B1.31 22 00.04 | Earth works & Site Grading | 2026-10-03 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3369-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer at Plot. No:-(7) STA 0+130 to 0+220 | 22.31 | 1944.32 | 0% | 0 | 0
2351 | B6.33 42 11.39 |  | 2026-10-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-3370-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/18 to STA-A1/17 at Road MCH0 |  | 63.50 | 0% | 0 | 0
2352 | B6.33 05 39.12 |  | 2026-10-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-3371-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm water Manhole Pit STA-A1/18 at Road MCH0 |  | 01 | 0% | 0 | 0
2353 | B5.33 31 00.01 | SEWERAGE NETWORK: GRP Pipes 200mm (Depth 0m- 1.50m) | 2026-10-03 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3372-00 | Check Coordinates level and Excavation width Bottom level and compaction for sewerage pipeline trench from Manhole # MH-1-80 to MH-1-79 at Road MCA0 | 212.41 | 98.80 | 0% | 0 | 0
2354 | B6.33 42 11.3 |  | 2026-10-06 | SUD1-02-011-TDC-TS9-1-STR-FIR-3376-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/23/3 to STA-A1/23/2 at Road MCH0 |  | 42.77 | 0% | 0 | 0
2355 | B1.31 22 00.04 | Earth works & Site Grading | 2026-10-03 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3377-00 | Check Coordinates level and Compaction F.D.T for Embankment 10th layer at PLOT (3), STA: 0+030 to STA: 0+170 | 22.31 | 3458.09 | 0% | 0 | 0
2356 | B4.33 14 13.11 |  | 2026-10-03 | SUD1-02-011-TDC-TS9-1-IRR-FIR-3378-00 | Check Coordinates level and Excavation width Bottom level and compaction for Irrigation water pipeline (450MM) Diameter from STA:1+900 to STA: 1+950 #Road MC10 |  | 50.00 | 0% | 0 | 0
2357 | B4.33 14 13.1 |  | 2026-10-03 | SUD1-02-011-TDC-TS9-1-IRR-FIR-3379-00 | Check Coordinates level and Excavation width Bottom level and compaction for Irrigation water pipeline (90mm) STA:0+000 to STA:0+375 Diameter #Road MCF0 |  | 375.00 | 0% | 0 | 0
2358 | B1.31 22 00.04 | Earth works & Site Grading | 2026-10-03 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3381-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer for Plot. No:-(8) # STA:0+30 to STA:0+160 at Zone A | 22.31 | 4487.74 | 0% | 0 | 0
2359 | B1.31 22 00.04 | Earth works & Site Grading | 2026-10-03 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3382-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer at Plot. No:-(7) STA 0+040 to 0+130 | 22.31 | 2126.78 | 0% | 0 | 0
2360 | B4.33 14 13.10 |  | 2026-10-03 | SUD1-02-011-TDC-TS9-1-IRR-FIR-3383-00 | Check Coordinates level and Excavation width Bottom level and compaction for Irrigation water pipeline (450MM) Diameter from STA:1+950 to STA: 2+000 #Road MC10 |  | 50.00 | 0% | 0 | 0
2361 | B4.33 14 13.9 |  | 2026-10-03 | SUD1-02-011-TDC-TS9-1-IRR-FIR-3384-00 | Check Coordinates level and Excavation width Bottom level and compaction for Irrigation water pipeline (450MM) Diameter from STA: 2+000 to STA: 2+550 #Road MC10 |  | 550.00 | 0% | 0 | 0
2362 | B1.31 22 00.05 |  | 2026-10-03 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3385-00 | Check Coordinates level and Compaction F.D.T for (Subgrade) 2nd layer at Road /Carriageway # MC20, STA: 4+580 to STA: 4+860 |  | 1,649.76 | 0% | 0 | 0
2363 | B1.32 11 23.01 |  | 2026-10-03 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3393-00 | Check Coordinates level and compaction F.D.T for (Aggregate base course) at Road /Carriageway# MCE0&MCZ0, STA: 0+090 to STA: 0+144.25 |  | 209.15 | 0% | 0 | 0
2364 | B6.33 42 11.2 |  | 2026-10-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-3394-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/15/9 to CB-A1/15/9 (D) at Road MCF0 |  | 5.17 | 0% | 0 | 0
2365 | B6.33 42 11.2 |  | 2026-10-03 | SUD1-02-011-TDC-TS9-1-STR-FIR-3399-00 | Check Coordinates level and Excavation width Bottom level and compaction for Storm Water pipeline trench from Manhole # STA-A1/30/4 to CB-A1/30/4 (D) at Road MCF0 |  | 2.51 | 0% | 0 | 0
2366 | B2.33 71 19.01 | Road crossing ducts, 2 ways (2 x 150mm PVC) | 2026-10-03 | SUD1-02-011-TDC-TS9-1-LIT-FIR-3402-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (2X160mm) from Manhole 27 To Manhole 28 for Street Lighting Duct Bank in Road ART-MC10 | 308.43 | 9.10 | 0% | 0 | 0
2367 | B2.33 71 19.02 | 6-ways ducts, 50mm diameter | 2026-10-03 | SUD1-02-011-TDC-TS9-1-TEL-FIR-3403-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 084 To 085 in Road MCB0 | 617.84 | 27.86 | 0% | 0 | 0
2368 | B7.32 92 00.01 |  | 2026-10-05 | SUD1-02-011-TDC-TS9-1-LSP-FIR-3430-00 | Installation of Grass From STA:0+130 to 0+730 |  | 7,069.03 | 0% | 0 | 0
2369 | B2.33.71.19.13.04 |  | 2026-10-05 | SUD1-02-011-TDC-TS9-1-TEL-FIR-3431-00 | Check Installation Manhole MH-096 for TELECOMMUNICATIONS Works in Road MCI0 |  | 1 | 0% | 0 | 0
2370 | B7.32 93 34.01 |  | 2026-10-05 | SUD1-02-011-TDC-TS9-1-LSP-FIR-3436-00 | Spreading and installation of Gravels |  | 3,187.48 | 0% | 0 | 0
2371 | B7.33.14.19.06 |  | 2026-10-05 | SUD1-02-011-TDC-TS9-1-LSP-FIR-3437-00 | Installation inspection for Pressure bubblers |  | 85.00 | 0% | 0 | 0
2372 | B1.31 22 00.04 |  | 2026-10-05 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3438-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer at Plot (9), STA: 0+200 to STA: 0+400 | 22.31 | 6435.65 | 100% | 22.31 | 143579.3515
2373 | B7.33.14.19.07 |  | 2026-10-05 | SUD1-02-011-TDC-TS9-1-LSP-FIR-3439-00 | Installation inspection for Pressure bubblers |  | 288.00 | 0% | 0 | 0
2374 | B1.31 22 00.04 |  | 1604.60 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3453-00 | Check Coordinates level and Compaction F.D.T for Embankment 11th layer at PLOT (2), STA: 0+560 to STA: 0+660 | 22.31 | 1604.60 | 100% | 22.31 | 35798.626
2375 | B2.33 71 19.02 |  | 2026-10-06 | SUD1-02-011-TDC-TS9-1-TEL-FIR-3477-00 | Check Sand Bedding and Installation HDPE Pipe 3(2X50mm) From Manhole 015 To 016 for TELECOMMUNICATIONS Works in Road MCF0 |  | 39.83 | 0% | 0 | 0
2376 | B1.32 11 23.01 |  | 514.10 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3480-00 | Check Coordinates level and compaction F.D.T for (Aggregate base course) at Road /Carriageway# MCD0, STA: 0+040 to STA: 0+180 |  | 514.10 | 0% | 0 | 0
2377 | B3.33 14 13.5 |  | 2026-10-06 | SUD1-02-011-TDC-TS9-1-PW-FIR-3466-00 | Inspection Pressure test of potable water Pipeline HDPE Pipes(315mm) from STA: 0+975 to ST: 0+925 Road MC10 |  | 50.00 | 0% | 0 | 0
2378 | B5 33.05.13.03 |  | 2026-10-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3489-00 | Check compaction F.D.T for Manhole Backfilling 1st layer at # MH-1-81 at Road MCA0 (Bottom subgrade) |  | 01 | 0% | 0 | 0
2379 | B5 33.05.13.03 |  | 2026-10-07 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3490-00 | Check compaction F.D.T for Manhole Backfilling 1st layer at # MH-1-82 at Road MCA0 (Bottom subgrade) |  | 01 | 0% | 0 | 0
2380 | B1.32 11 26.01 |  | 2026-10-05 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3498-00 | Check Coordinates, level, thickness,Compaction and Testing for Bituminous base course layer (70mm) on Road /Carriageway from# ST: 0+070 to ST: 0+144.25 at Road MCE0&MCZ0 |  | 105.85 | 0% | 0 | 0
2381 | B1.31 22 00.04 |  | 2026-10-07 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3499-00 | Check Coordinates level and Compaction F.D.T for Embankment 6th layer at Plot. No:-(7) STA 0+070 to 0+140 |  | 731.82 | 0% | 0 | 0
2382 | B3.33 14 13.1 |  | 2026-10-07 | SUD1-02-011-TDC-TS9-1-PW-FIR-3500-00 | Check Coordinates level and Excavation width Bottom level and compaction for potable water pipeline(160mm) from Station STA:0+25 to STA: 0+300 at Road MCF0 |  | 275.00 | 0% | 0 | 0
2383 | B3.33 1413.5 |  | 2026-10-05 | SUD1-02-011-TDC-TS9-1-PW-FIR-3508-00 | Inspection Pressure test of potable water Pipeline HDPE Pipes (315mm) from ST: 2+275.00 to ST: 2+650.00 Road MC20 |  | 375 | 0% | 0 | 0
2384 | B1.31 22 00.04 |  | 2026-10-08 | SUD1-02-011-TDC-TS9-1-ROD-FIR-3515-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer at Plot (9), STA: 0+040 to STA: 0+200 | 22.31 | 3814.94 | 100% | 22.31 | 85111.3114
2385 | B4.33 14 13.1 |  | 2026-10-08 | SUD1-02-011-TDC-TS9-1-IRR-FIR-3517-00 | Check Coordinates level and Excavation width Bottom level and compaction for Irrigation water pipeline (90mm) Diameter STA:0+050 to STA:0+403 #Road MCE0 |  | 353.23 | 0% | 0 | 0
2386 | B5.33 05 13.05 |  | 2026-10-08 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3541-00 | Check Installation of Rings and Flat Slab at Manhole MH-12-10 Road MCB0. |  | 01 | 0% | 0 | 0
2387 | B5.33 05 13.05 |  | 2026-10-08 | SUD1-02-011-TDC-TS9-1-SEW-FIR-3542-00 | Check Installation of Rings and Flat Slab at Manhole MH-12-9 Road MCB0. |  | 01 | 0% | 0 | 0
29518302.4886

## Schedule
Primavera P6 Schedule Status | [9 empty] | Data Date | 2026-10-12
Project Activities Overview
Schedule Statistics |  |  |  |  | Active Schedule Activities
Total Act. | Not Started | In Progress | Completed | % | Active | Ahead | On | Behind | Flag
2115 | 1052 | 352 | 711 | 33.62% | 26 | 5 | 0 | 17 | -12
Critical Path Activities |  |  | Free Float Management (Total) |  |  |  | Failed Start Activities
|  |  | Greater Than 14 Days |  | Less Than 14 Days
Last Week | This Week | Diff | Last Week | This Week | Last Week | This Week | Last Week | This Week | Flag
34 | 0 | 34 | 193 | 180 | 1209 | 1186 | 17 | 33 | -16

## Milestones
Project Name
Item No. | Milestones | Original (Baseline) | Latest | Forecast |  | Days Change
| Contract Duration Current Contract Weeks : 40 of 78 |  | 77.8571 | 77.8571 |  | 0 |  | 39.8571 | 77.8571
1 | Project Start Milstone | 2026-01-06 | 2026-01-06 | 2026-01-06 | Finish | 0
2 | Mobilization Finish Milestone | 2026-02-05 | 2026-02-05 | 2026-02-05 | Finish | 0
3 | Baseline Submission Finish Milestone | 2026-02-05 | 2026-02-05 | 2026-04-06 | Finish | -60
4 | Technical Submittals Finish Milestone | 2026-03-05 | 2026-03-05 | 2026-08-16 | UP | -164
5 | Quality Lap Finish Milestone | 2026-02-05 | 2026-02-05 | 2026-02-16 | Finish | -11
6 | RBF Finish Milestone | 2026-02-05 | 2026-02-05 | 2026-02-16 | Finish | -11 | 5058886 | 4463892
7 | All Works Finish Milestone | 2027-07-05 | 2027-07-05 | 2027-07-05 | UP | 0 | 0 | 0
8 | Engineering Phase Finish Milestone | 2026-03-05 | 2026-03-05 | 2026-09-28 | UP | -207 | 0 | 0
9 | Procurment Phase Finish Milestone | 2027-01-23 | 2027-01-23 | 2027-01-17 | UP | 6 | 0 | 0
10 | Construction Phase Finish Milestone | 2027-07-05 | 2027-07-05 | 2027-07-05 | UP | 0 | 0 | 0
11 | Project Finish Milstone | 2027-07-05 | 2027-07-05 | 2027-07-05 | - | 0 | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0

## Procurement
PROCUREMENT
Sr. NO. | Project ID | ACT#inP6 | Item Description | Discipline | (Long \Short) Lead Items | BOQ. No. | Unit | Quantity | Proc. Qty | Required P.O Date | Date of Pur. Order Issued | Purchase Order No. | Supplier | Supplier Phone | Method of Shipping | Required on Job | E.D.A. to Site | A.D.A. to Site | Lead Time | Approval Status | The Impact (BOQ Cost) | Completion Rate | Remarks
1 | SUD1-02-011 | SIC-ENG-M-SUC-1000 | Earth works material | Civil | Short Lead Items | 31 22 00 | m3 | 2437927 | 2437927 | 2026-02-19 | - | - | - |  | Local trancport |  | 2026-03-07 |  | 16 | Approved | - | 90% | Delivery Ongoing
2 | SUD1-02-011 | SIC-ENG-M-SUC-1010 | Ready mix concrete | Civil | Short Lead Items | 33 42 16 | m3 | 270 | 270 | 2026-02-19 | - | - | - |  | Local trancport |  | 2026-03-14 | 2026-06-11 | 23 | Approved | - | 100% | Delivered
3 | SUD1-02-011 | SIC-ENG-M-SUC-1020 | Asphalt Mix | Civil | Short Lead Items | 32 11 26 | m3 | 32179 | 32179 | 2026-02-19 | - | - | - |  | Local trancport |  | 2026-03-14 | 2026-06-11 | 23 | Approved | - | 15% | Delivery Ongoing
4 | SUD1-02-011 | SIC-ENG-M-SUC-1030 | Road Marking | Civil | Short Lead Items | 32 17 23 | m² | 11860 | 11860 | 2026-03-30 | - | - | - |  | Local trancport |  | 2026-04-12 |  | 13 | Not submitted | - | -
5 | SUD1-02-011 | SIC-ENG-M-SUC-1040 | Kerbstone | Civil | Short Lead Items | 32 14 13 | m | 117195 | 117195 | 2026-04-13 | - | - | - |  | Local trancport |  | 2026-04-27 |  | 14 | Approved | - | 3.371% | Delivery Ongoing
6 | SUD1-02-011 | SIC-ENG-M-SUC-1050 | Interlock Tiles | Civil | Short Lead Items | 32 14 13.13 | m² | 53000 | 53000 | 2026-04-13 | - | - | - |  | Local trancport |  | 2026-05-10 |  | 27 | Approved | - | 5.538% | Delivery Ongoing
7 | SUD1-02-011 | SIC-ENG-M-SUC-1060 | Traffic Signage | Civil | Short Lead Items | 10 14 53 | Unit | 64 | 64 | 2026-04-27 | - | - | - |  | Local trancport |  | 2026-03-17 |  | 32 | Approved | - | -
8 | SUD1-02-011 | SIC-ENG-M-SUC-1070 | Construction material | Civil | Short Lead Items | 32 11 23 / 31 22 00.05 | m3 | 102138 | 102138 | 2026-02-19 | - | - | - |  | Local trancport |  | 2026-05-31 | 2026-07-29 | 101 | Approved | - | 100% | Delivered
9 | SUD1-02-011 | SIC-ENG-M-SUC-1080 | Fence for Electrical works | Civil | Short Lead Items | 26.11.00 | Unit | 5 |  | 2026-04-27 | - | - | - |  | Local trancport |  | 2026-07-16 |  | 80 | Not submitted | - | -
10 | SUD1-02-011 | SIC-ENG-M-SUC-1090 | Protection Bollards for CCTV Pole | Civil | Short Lead Items | 33 14 19 | Unit | 86 |  | 2026-05-11 | - | - | - |  | Local trancport |  | 2026-05-23 |  | 19 | Approved | - | -
11 | SUD1-02-011 | SIC-ENG-M-SUC-1100 | Protection (Guard rail) for Fire hydrant | Mechanical | Short Lead Items | 33 14 19 | Unit | 90 |  | 2026-05-25 | - | - | - |  | Local trancport |  | 2026-06-28 |  | 34 | Approved | - | -
12 | SUD1-02-011 | SIC-ENG-M-SUE-1210 | Termination Kits & Joints | Electrical | Short Lead Items | 26 05 13.16 | unit | 144 |  | 2026-02-26 | - | - | - |  | Local trancport |  | 2026-12-05 |  | 282 | Approved | - | 100% | Delivered
13 | SUD1-02-011 | SIC-ENG-M-SUE-1220 | UPVC Ducts & HDPE Ducts for Telecom network | Electrical | Short Lead Items | 33 14 13 | m | 15200 | 15200 | 2026-05-14 |  |  |  |  | Local trancport |  | 2026-12-05 | 2026-06-18 | 205 | Approved | - | 100% | Delivered
14 | SUD1-02-011 | SIC-ENG-M-SUE-1230 | Grounding System | Electrical | Short Lead Items | 26 05 26 | Unit | 50 | 50 | 2026-06-16 | - | - | - |  | Local trancport |  | 2026-12-19 | 2026-07-08 | 186 | Approved | - | 100% | Delivered
15 | SUD1-02-011 | SIC-ENG-M-SUE-1240 | PECD Ducts for CCTV network | Electrical | Short Lead Items | 34 14 19 | Unit | 1 |  | 2026-07-30 | - | - | - |  | Local trancport |  | 2027-01-11 |  | 165 | Approved | - | -
16 | SUD1-02-011 | SIC-ENG-M-SUM-1000 | GRP & UPVC Pipes & Fittings | Mechanical | Long Lead Items | 33 31 00 / 33 42 11 | m | 22100 | 22100 | 2026-02-24 | 2026-03-09 | 10708 &10697 | AMIANTIT&Nationel marketing | 9668471500 | Local trancport |  | 2026-05-02 | 2026-06-19 | 67 | Approved | - | 100% | Delivered
17 | SUD1-02-011 | SIC-ENG-M-SUM-1010 | HDPE Pipes & Fittings | Mechanical | Long Lead Items | 33 14 13 / 11 | m | 63710 | 63710 | 2026-03-15 | 2026-03-09 | 10760 | Union pipes | 500632552 | Local trancport |  | 2026-05-10 | 2026-06-19 | 56 | Approved | - | 100% | Delivered
18 | SUD1-02-011 | SIC-ENG-M-SUM-1020 | Gate Valves | Mechanical | Long Lead Items | 33 14 19 | Unit | 198 | 198 | 2026-03-31 | - |  | AVK | 114006355 | Local trancport |  | 2026-05-18 |  | 48 | Approved | - | 100% | Delivered
18.1 | SUD1-02-011 | SIC-ENG-M-SUM-1020 | Butterfly valves | Mechanical | Long Lead Items | 34 14 19 | Unit | 24 | 24 | 2026-03-31 |  |  | AVK | 114006355 | Local trancport |  | 2026-05-18 |  | 48 | Approved |  | 91.67% | Delivery Ongoing
18.2 | SUD1-02-011 | SIC-ENG-M-SUM-1020 | Washout valves | Mechanical | Long Lead Items | 35 14 19 | Unit | 14 | 14 | 2026-03-31 |  |  | AVK | 114006355 | Local trancport |  | 2026-05-18 |  | 48 | Approved |  | 0% | Delivery Ongoing
18.3 | SUD1-02-011 | SIC-ENG-M-SUM-1020 | Airrelease valves | Mechanical | Long Lead Items | 36 14 19 | Unit | 23 | 23 | 2026-03-31 |  |  | AVK | 114006355 | Local trancport |  | 2026-05-18 |  | 48 | Approved |  | 0% | Delivery Ongoing
19 | SUD1-02-011 | SIC-ENG-M-SUM-1030 | Manhole | Civil | Long Lead Items | 33 05 13 | Unit | 251 | 251 | 2026-03-15 | - |  | Sacep contraction | 53431677 | Local trancport |  | 2026-06-17 | 2026-07-05 | 94 | Approved | - | 95% | Delivery Ongoing
20 | SUD1-02-011 | SIC-ENG-M-SUM-1040 | Catch Basin | Civil | Long Lead Items | 33 05 39 | Unit | 294 | 294 | 2026-04-14 | - |  | United Al kharj | 53431677 | Local trancport |  | 2026-06-21 |  | 68 | Approved | - | 100% | Delivered
21 | SUD1-02-011 | SIC-ENG-M-SUM-1050 | Manhole, Catch basin and Valve box Cover | Civil | Long Lead Items | 33 05 13 / 39 | Unit | 545 | 545 | 2026-04-28 | - |  | United Al kharj | 53431677 | Local trancport |  | 2026-07-23 | 2026-07-10 | 86 | Approved | - | 99.63% | Delivery Ongoing
22 | SUD1-02-011 | SIC-ENG-M-SUM-1060 | Fire Hydrant | Mechanical | Long Lead Items | 33 14 19 | Unit | 90 | 90 | 2026-05-12 | 2026-03-08 | 10699 | AVK | 114006355 | Local trancport |  | 2026-09-24 |  | 135 | Approved | - | 100% | Delivered
23 | SUD1-02-011 | SIC-ENG-M-SUM-1070 | Valve of Fire Hydrant | Mechanical | Long Lead Items | 33 14 19 | Unit | 90 | 90 | 2026-05-12 | - |  | AVK | 114006355 | Local trancport |  | 2026-09-24 |  | 135 | Approved | - | 100% | Delivered
24 | SUD1-02-011 | SIC-ENG-M-SUE-1000 | MV Cables | Electrical | Long Lead Items | 26 05 13.16 | m | 51500 | 51500 | 2026-02-26 | - |  |  |  | Local trancport |  | 2026-05-31 |  | 94 | Not submitted | - | 0%
25 | SUD1-02-011 | SIC-ENG-M-SUE-1010 | LV Cables | Electrical | Long Lead Items | 26.5.19 | m | 29700 | 29700 | 2026-03-17 | - |  | Hasham Esawady |  | Local trancport |  | 2026-05-16 |  | 60 | Approved | - | 84% | Delivery Ongoing
26 | SUD1-02-011 | SIC-ENG-M-SUE-1020 | Street Lighting Poles | Electrical | Long Lead Items | 26 56 19 | Unit | 590 | 590 | 2026-04-02 | - |  | Ababten co |  | Local trancport |  | 2026-06-10 |  | 69 | Approved | - | 10% | Delivery Ongoing
27 | SUD1-02-011 | SIC-ENG-M-SUE-1030 | Street Lighting Fixtures | Electrical | Long Lead Items | 26 56 19 | Unit | 678 | 678 | 2026-04-16 | - |  | Ababten co |  | Local trancport |  | 2026-06-24 |  | 69 | Approved | - | -
28 | SUD1-02-011 | SIC-ENG-M-SUE-1040 | DrawPits for Lighting | Electrical | Long Lead Items | 33 71 19.13 | Unit | 95 |  | 2026-04-30 | - |  | - |  | Local trancport |  | 2026-07-08 |  | 69 | Approved | - | 100% | Delivered
29 | SUD1-02-011 | SIC-ENG-M-SUE-1050 | Concrete Manholes & DrawPits for Telecom Network | Electrical | Long Lead Items | 33 71 19.13 | Unit | 122 |  | 2026-06-02 | - |  | - |  | Local trancport |  | 2026-06-22 |  | 20 | Approved | - | -
30 | SUD1-02-011 | SIC-ENG-M-SUE-1060 | Switchgears - (RMUs) | Electrical | Long Lead Items | 26.11.00 | Unit | 5 |  | 2026-06-30 | - |  |  |  | Local trancport |  | 2026-07-08 |  | 18 | Approved | - | 100% | Delivered
31 | SUD1-02-011 | SIC-ENG-M-SUE-1070 | Unit Substation | Electrical | Long Lead Items | 26.11.00 | Unit | 5 | 5 | 2026-07-02 | - |  |  |  | Local trancport |  | 2026-08-04 |  | 33 | Not submitted | - | -
32 | SUD1-02-011 | SIC-ENG-M-SUE-1080 | Lighting Panels | Electrical | Long Lead Items | 26 24 16 | Unit | 5 | 5 | 2026-07-16 | - |  | MEG manefacture |  | Local trancport |  | 2026-08-05 |  | 20 | Approved | - | -
33 | SUD1-02-011 | SIC-ENG-M-SUE-1090 | KWH Meter with mounting frame | Electrical | Long Lead Items | 26 24 16 | Unit | 5 |  | 2026-07-16 | - |  |  |  | Local trancport |  | 2026-09-01 |  | 47 | Not submitted | - | -
34 | SUD1-02-011 | SIC-ENG-M-SUE-1100 | Main Feeder Pillar | Electrical | Long Lead Items | 26 24 16 | Unit | 5 |  | 2026-07-16 | - |  |  |  | Local trancport |  | 2026-09-19 | 2026-06-11 | 65 | Approved | - | -
35 | SUD1-02-011 | SIC-ENG-M-SUE-1110 | CCTV Poles including all hardwares | Electrical | Long Lead Items | 34 14 19 | Unit | 35 |  | 2026-07-30 | - |  | - |  | Local trancport |  | 2026-09-17 |  | 49 | Approved | - | -
36 | SUD1-02-011 | SIC-ENG-M-SUE-1120 | CCTV Cables "Power" | Electrical | Long Lead Items | 34 14 19 | m | 7500 |  | 2026-08-06 | - |  | - |  | Local trancport |  | 2026-09-17 |  | 42 | Approved | - | -
37 | SUD1-02-011 | SIC-ENG-M-SUE-1130 | CCTV Cables "CAT6" | Electrical | Long Lead Items | 34 14 19 | Unit | 195 |  | 2026-08-06 | - |  | - |  | Local trancport |  | 2026-08-01 |  | 25 | Approved | - | -
38 | SUD1-02-011 | SIC-ENG-M-SUE-1140 | Racks and Patch panels | Electrical | Long Lead Items | 35 14 19 | Unit | 3 |  | 2026-08-20 | - |  | - |  | Local trancport |  | 2026-09-19 |  | 30 | Approved | - | 100% | Delivered
39 | SUD1-02-011 | SIC-ENG-M-SUE-1150 | CCTV System,Servers & WorkStations | Electrical | Long Lead Items | 36 14 19 | Unit | 6 |  | 2026-09-03 | - |  | - |  | Local trancport |  | 2026-10-01 |  | 28 | Approved | - | -
40 | SUD1-02-011 | SIC-ENG-M-SUE-1160 | Professional 55" Video wall at control room | Electrical | Long Lead Items | 37 14 19 | Unit | 6 |  | 2026-09-17 | - |  | - |  | Local trancport |  | 2026-10-08 |  | 21 | Approved | - | 100% | Delivered
41 | SUD1-02-011 | SIC-ENG-M-SUE-1170 | CCTV Switches | Electrical | Long Lead Items | 38 14 19 | Unit | 27 |  | 2026-10-04 | - |  | - |  | Local trancport |  | 2026-10-03 |  | 19 | Approved | - | 100% | Delivered
42 | SUD1-02-011 | SIC-ENG-M-SUE-1180 | CCTV Wireless P2P bridges | Electrical | Long Lead Items | 39 14 19 | Unit | 27 |  | 2026-10-04 | - |  | - |  | Local trancport |  | 2026-10-22 |  | 18 | Approved | - | 100% | Delivered
43 | SUD1-02-011 | SIC-ENG-M-SUE-1190 | CCTV UPS | Electrical | Long Lead Items | 34 14 19 | Unit | 1 |  | 2026-10-18 | - |  | - |  | Local trancport |  | 2026-11-05 |  | 18 | Approved | - | 100% | Delivered
44 | SUD1-02-011 | SIC-ENG-M-SUE-1200 | CCTV Solar System | Electrical | Long Lead Items | 33 14 19 | Unit | 2 |  | 2026-11-01 |  |  | - |  | Local trancport |  | 2026-11-21 |  | 20 | Approved | - | -
#REF!
Y

## EV-Chart Data
| Baseline Plan |  |  | Revised / Recovery Plan |  |  | Earned Value |  |  | Gross Paid Value |  |  | Forecast |  |  | Actual/Fcst vs Plan
Month | Monthly | Cum | % | Monthly | Cum | % | Monthly | Cum | % | Monthly | Cum | % | Monthly | C um |  | Month | Cum
2026-01-06 |  | 0 | 0% |  |  |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 |  | 0 | 0 | Actuals thru previous month
2026-02-06 | 5363766 | 5363766 | 3.181% |  |  |  | 1803473 | 1803473 | 1.069% | 0 | 0 | 0% | 1803473 | 1803473 |  | -3560293 | -3560293
2026-03-06 | 573441 | 5937207 | 3.521% |  |  |  | 4942335 | 6745808 | 4% | 0 | 0 | 0% | 4942335 | 6745808 |  | 4368894 | 808601
2026-04-06 | 657064 | 6594271 | 3.911% |  |  |  | 1294293 | 8040101 | 4.768% | 0 | 0 | 0% | 1294293 | 8040101 |  | 637229 | 1445830
2026-05-06 | 6765952 | 13360223 | 7.923% |  |  |  | 5023481 | 13063582 | 7.747% | 0 | 0 | 0% | 5023481 | 13063582 |  | -1742471 | -296641 | Forecast current and future months
2026-06-06 | 15078567 | 28438790 | 16.86% |  |  |  | 21674992 | 34738574 | 20.6% | 0 | 0 | 0% | 21674992 | 34738574 |  | 6596425 | 6299784
2026-07-06 | 13666374 | 42105164 | 24.97% |  |  |  | 11876148 | 46614722 | 27.64% | 0 | 0 | 0% | 11876148 | 46614722 |  | -1790226 | 4509558
2026-08-06 | 17215276 | 59320440 | 35.18% |  |  |  | 15462572.34 | 62077294.34 | 36.81% | 0 | 0 | 0% | 15462572.34 | 62077294.34 |  | -1752703.66 | 2756854.34
2026-09-06 | 18831769 | 78152209 | 46.35% |  |  |  | 11072026.5 | 73149320.84 | 43.38% | 0 | 0 | 0% | 11072026.5 | 73149320.84 |  | -7759742.5 | -5002888.16
2026-10-06 | 16883223 | 95035432 | 56.36% |  |  |  | 4920656.95 | 78069977.79 | 46.3% |  |  |  | 4920656.95 | 78069977.79 | 46.3% | -11962566.05 | -16965454.21
2026-11-06 | 21549951 | 116585383 | 69.14% |  |  |  | 0 | [5 empty] | 33512517.05 | 111582494.84 | 66.17% | 11962566.05 | -5002888.16
2026-12-06 | 14180877 | 130766260 | 77.55% |  |  |  | 0 | [5 empty] | 14180877 | 125763371.84 | 74.58% | 0 | -5002888.16
2027-01-06 | 7380570 | 138146830 | 81.92% |  |  |  | 0 | [5 empty] | 7380570 | 133143941.84 | 78.96% | 0 | -5002888.16
2027-02-06 | 5035339 | 143182169 | 84.91% |  |  |  | 0 | [5 empty] | 5035339 | 138179280.84 | 81.94% | 0 | -5002888.16
2027-03-06 | 2950780 | 146132949 | 86.66% |  |  |  | 0 | [5 empty] | 2950780 | 141130060.84 | 83.69% | 0 | -5002888.16
2027-04-06 | 12729609 | 158862558 | 94.21% |  |  |  | 0 | [5 empty] | 12729609 | 153859669.84 | 91.24% | 0 | -5002888.16
2027-05-06 | 4484392 | 163346950 | 96.87% |  |  |  | 0 | [5 empty] | 4484392 | 158344061.84 | 93.9% | 0 | -5002888.16
2027-06-06 | 4640187 | 167987137 | 99.62% |  |  |  | 0 | [5 empty] | 9643075.16 | 167987137 | 99.62% | 5002888.16 | 0
2027-07-06 | 642382 | 168629519 | 100% |  |  |  | 0 | [5 empty] | 642382 | 168629519 | 100% | 0 | 0 |  | Extended Duration
UPDATE ONLY YELLOW PORTION FROM PRIMAVERA EXPORT, IF NEEDED, EXTEND YELLOW PORTION BASED ON SCHEDULE.
[14 empty] | 0 | 79968099
|  |  |  | 46614722 | 330920.4 | [8 empty] | 11072026.5
11876148
0
[13 empty] | 9643075.16 | 79968099 | 79968099
[8 empty] | 0 |  |  | 33512517.05
[8 empty] | 1803473 |  | 21549951 |  |  |  | 0 |  | 22625723 | 216225
[8 empty] | 6745808 |  |  |  |  | 16883223 | 1803473
| 78069977.79 | 487586 | [5 empty] | 8040101 |  | 21549951 | 8193506.62 |  |  | 6745808
[8 empty] | 13063582 |  |  |  |  | 16883223 | 8040101
[8 empty] | 34738574 | [5 empty] | 13063582
[8 empty] | 46614722 | [5 empty] | 34738574
[8 empty] | 62077294.34 | [5 empty] | 46614722
[8 empty] | 73149320.84 |  |  | 9643075.16 |  |  | 62077294.34
73149320.84
90032543.84
111582494.84
125763371.84
[5 empty] | 0 | [8 empty] | 133143941.84
138179280.84
141130060.84
153859669.84
158344061.84
167987137
168629519

## Physical-Chart Data
| Baseline Plan |  |  | Revised / Recovery Plan |  |  | Earned Effort % |  |  | Forecast |  |  | Achieved/Fcst vs Plan
Week | Monthly Effort | Cum Effort | Plan Wt.% | MonthlyEffort | Cum Effort | Plan Wt.% | Monthly Wt. | Cum Wt. | Achieved Wt.% | Monthly Wt. | Cum Wt. | Wt.% | Monthly Wt. | Cum Wt.
2026-01-06 | 29295 | 29295 | 2.571% |  |  |  | 0 | 0 | 0% |  |  |  | -29295 | -29295 | Actuals thru previous month
2026-02-06 | 63408 | 92703 | 8.137% |  |  |  | 9176 | 9176 | 0.8054% | 9176 | 9176 |  | -54232 | -83527
2026-03-06 | 6723 | 99426 | 8.727% |  |  |  | 95495 | 104671 | 9.188% | 95495 | 104671 |  | 88772 | 5245
2026-04-06 | 22044 | 121470 | 10.66% |  |  |  | 5885 | 110556 | 9.704% | 5885 | 110556 |  | -16159 | -10914
2026-05-06 | 35051 | 156521 | 13.74% |  |  |  | 46824 | 157380 | 13.81% | 46824 | 157380 |  | 11773 | 859 | Forecast current and future months
2026-06-06 | 66568 | 223089 | 19.58% |  |  |  | 115472 | 272852 | 23.95% | 115472 | 272852 |  | 48904 | 49763
2026-07-06 | 58517 | 281606 | 24.72% |  |  |  | 58068.4 | 330920.4 | 29.05% | 58068.4 | 330920.4 |  | -448.6 | 49314.4
2026-08-06 | 63858 | 345464 | 30.32% |  |  |  | 59915 | 390835.4 | 34.31% | 59915 | 390835.4 |  | -3943 | 45371.4
2026-09-06 | 70181 | 415645 | 36.48% |  |  |  | 56123.6 | 446959 | 39.23% | 56123.6 | 446959 |  | -14057.4 | 31314
2026-10-06 | 87930 | 503575 | 44.2% |  |  |  | 40627 | 487586 | 42.8% | 40627 | 487586 | 42.8% | -47303 | -15989
2026-11-06 | 94267 | 597842 | 52.48% | [6 empty] | 110256 | 597842 | 52.48% | 15989 | 0
2026-12-06 | 90588 | 688430 | 60.43% | [6 empty] | 90588 | 688430 | 60.43% | 0 | 0
2027-01-06 | 86356 | 774786 | 68.01% | [6 empty] | 86356 | 774786 | 68.01% | 0 | 0
2027-02-06 | 86016 | 860802 | 75.56% | [6 empty] | 86016 | 860802 | 75.56% | 0 | 0
2027-03-06 | 80671 | 941473 | 82.64% | [6 empty] | 80671 | 941473 | 82.64% | 0 | 0
2027-04-06 | 71569 | 1013042 | 88.92% | [6 empty] | 71569 | 1013042 | 88.92% | 0 | 0
2027-05-06 | 71175 | 1084216 | 95.17% | [6 empty] | 71174 | 1084216 | 95.17% | -1 | -1
2027-06-06 | 38461 | 1122677 | 98.55% | [6 empty] | 38461 | 1122677 | 98.55% | 0 | -1
2027-07-06 | 16567 | 1139244 | 100% | [6 empty] | 16567 | 1139244 | 100% | 0 | -1 |  | Extended Duration
UPDATE ONLY YELLOW PORTION FROM PRIMAVERA EXPORT, IF NEEDED, EXTEND YELLOW PORTION BASED ON SCHEDULE.
[10 empty] | 0 | 0
330920.4
[11 empty] | 56123.6 | 434980.72 | 434980.72
364039.9
457037
|  |  | 9176 | [6 empty] | 40627
|  |  | 104671 |  |  | 487586 |  |  |  | 0
110556
157380
|  |  | 272852 | [5 empty] | 9176
|  |  | 330920.4 | [5 empty] | 104671
|  |  | 455835.4 | [5 empty] | 110556
|  |  | 485514 | [5 empty] | 157380
272852
330920.4
455835
485514
540160
608020
706653
793681
866330
948888
1023803
1100929
1136407
1151844

## Testing
Testing and Commissioning
Item | Planned Start Date | Planned Finish Date | Forecast Start Date | Forecast Finish Date | Actual Start Date | Actual Finish Date | % Completed | Open Comments | Closed Comments
Zone A | 2027-01-12 | 2027-07-01 | 2026-12-24 | 2027-07-05
Road works | 2027-04-18 | 2027-04-22 | 2027-06-01 | 2027-06-06 |  |  | 0% | 0 | 0
Network work | 2027-05-05 | 2027-05-24 | 2027-06-15 | 2027-06-29 |  |  | 0% | 0 | 0
Sewage Network | 2027-04-14 | 2027-04-28 | 2027-04-29 | 2027-05-13 |  |  | 0% | 0 | 0
TSE Network | 2027-05-13 | 2027-06-04 | 2027-06-10 | 2027-07-05 |  |  | 0% | 0 | 0
Potable Network | 2027-05-27 | 2027-06-11 | 2027-04-19 | 2027-05-04 |  |  | 0% | 0 | 0
Electrical Network | 2027-01-28 | 2027-02-10 | 2027-04-12 | 2027-04-22 |  |  | 0% | 0 | 0
Landscape & Irrigation Network | 2027-06-25 | 2027-07-01 | 2027-06-28 | 2027-07-05 |  |  | 0% | 0 | 0
CCTV Medium voltage works | 2027-01-12 | 2027-01-23 | 2026-12-24 | 2027-01-05 |  |  | 0% | 0 | 0
Zone G | 2027-01-12 | 2027-07-01 | 2026-12-24 | 2027-07-05
Road works | 2027-04-18 | 2027-04-22 | 2027-06-01 | 2027-06-06 |  |  | 0% | 0 | 0
Network work | 2027-05-05 | 2027-05-24 | 2027-06-15 | 2027-06-29 |  |  | 0% | 0 | 0
Sewage Network | 2027-04-14 | 2027-04-28 | 2027-04-29 | 2027-05-13 |  |  | 0% | 0 | 0
TSE Network | 2027-05-13 | 2027-06-04 | 2027-06-10 | 2027-07-05 |  |  | 0% | 0 | 0
Potable Network | 2027-05-27 | 2027-06-11 | 2027-04-19 | 2027-05-04 |  |  | 0% | 0 | 0
Electrical Network | 2027-01-28 | 2027-02-10 | 2027-04-12 | 2027-04-22 |  |  | 0% | 0 | 0
Landscape & Irrigation Network | 2027-06-25 | 2027-07-01 | 2027-06-28 | 2027-07-05 |  |  | 0% | 0 | 0
CCTV Medium voltage works | 2027-01-12 | 2027-01-23 | 2026-12-24 | 2027-01-05 |  |  | 0% | 0 | 0
Total | [6 empty] | 0% | 0% | 0%

## Conclusion (hidden)
تقدم سير مشروع تطوير شبكات البنية التحتية في مدينة سدير للصناعة والأعمال – المرحلة الثانية – الجزء الثاني
معلومات المشروع |  |  |  | نطاق المشروع |  |  |  |  | موقع المشروع
المقاول | شركة تطوير التقنية للمقاولات | الاستشاري | شركة ايجيس السعودية للاستشارات | البند | الكمية الكلية | الكمية المنفذة | الكمية المتبقية | نسبة المنفذ
تاريخ استلام الموقع | 06-01-2026 م | مدة التنفيذ | 18 شهرًا ميلاديًا | أعمال الطرق والرصف (ROD) | 18,252 م | 0 | 0 | -
بداية العقد | من تاريخ استلام الموقع | قيمة العقد (شامل ضريبة القيمة المضافة) | 193,923,948.00 ريال | أعمال شبكة مياة الشرب (WAT) | 18,021 م | 0 | 0 | -
نسبة الإنجاز المخطط له | 0% | نسبة الإنجاز الفعلي | 0.03% | أعمال شبكة المياه المعالجة (TSE) | 16,141 م | 0 | 0 | -
|  | 168629519.99 |  | أعمال شبكة الصرف الصحي (SEW) | 13,040 م | 0 | 0 | -
ملخص جدول الكميات |  |  |  | أعمال شبكة صرف مياه الأمطار (STR) | 13,600 م | 0 | 0 | -
مكونات المشروع |  | التكلفة (غير شامل ضريبة القيمة المضافة) | النسبة الاجمالية | أعمال شبكة الري والمناظر الطبيعية (IRR) | 29,570 م | 0 | 0 | -
أعمال الطرق |  | 88002863.2 | 52.19% | أعمال الشبكة الكهربائية (ELE) | 51,500 م | 0 | 0 | -
شبكة تصريف مياه الأمطار |  | 25408256.59 | 15.07% | أعمال المراقبة بالكاميرات (CCTV) | 125 كاميرا | 0 | 0 | -
شبكة الصرف الصحي |  | 7071026.55 | 4.193% | ملخص التوريدات |  |  |  |  | تقدم أعمال layout
شبكة المياه المعالجة (TSE) |  | 4148179.83 | 2.46% | البند | الكمية الكلية | الكمية المورده | الكمية المتبقية | نسبة التوريد
شبكة مياه الشرب |  | 7780464.9 | 4.614%
الأعمال الكهربائية |  | 20085705.4 | 11.91%
أعمال تنسيق الموقع والري |  | 6827173.87 | 4.049%
أعمال كاميرات المراقبة (CCTV) |  | 9305849.65 | 5.519%
معالم البرنامج الزمني
البند |  | التاريخ حسب الجدول الزمني | ملاحظة
Mobilization Finish Milestone |  | 2026-02-05 | Finish
Baseline Submission Finish Milestone |  | 2026-02-05 | UG | التحديات والعوائق
Technical Submittals Finish Milestone |  | 2026-03-05 | UG | 1-
Quality Lap Finish Milestone |  | 2026-02-05 | Finish | 2-
RBF Finish Milestone |  | 2026-02-05 | Finish | 3-
All Works Finish Milestone |  | 2027-07-05 | UG | 4-
5-
6-
7-

## Codes (hidden)
Status List
| Approved |  | Y
| Pending |  | N | [5 empty] | (Manhours)
| Potential | [7 empty] | (Mandays)
| Phase | Stage |  | Stage |  | Status |  | Score
[8 empty] | Low | Contractor | Active
| Launch | LOA |  | LOA |  | Active |  | Medium | CM | Expired
| Launch | Kick-off Meeting |  | Kick-off Meeting |  | On Hold |  | High | PgM | Occurred
| Launch | Site Handover |  |  |  | Terminated |  |  | Modon | Pending
| Launch | Mobilization |  | Mobilization | Initial staff and equipment in place, ready to start production | Terminated, Closed |  |  | Other
| Execution | Construction |  | Execution | Tender Documents Issued | Substantial Complete | Initial Handover done at site
| Execution | T&C |  |  | Responses to the OCS completed | Complete | Initial Handover Signed
| Execution | Initial Handover |  | Closeout | Design close-out process complete | Closed | Final Handover done at Site
Warranty Period
Final Handover
Project Status Score
Elements |  |  | Max | Score | Planned | Actual | Remarks
SPI (Physical Effort) |  |  | 100% | 109.5% | No Entry Required
SPI (Cost) |  |  | 100% | 122.1% | No Entry Required
On Schedule -Active |  |  | 100% | 19.23% | No Entry Required |  |  |  | 0.6
Manpower Availability |  |  | 100% | 203.7% | No Entry Required
Major Equipment Availability |  |  | 100% | 201.9% | No Entry Required
Billing % Compared to Planned |  |  | 100% | 0% | No Entry Required
Safety Score |  |  | 100% | #REF! | No Entry Required
Quality Score |  |  | 100% | 95.07% | No Entry Required