## DB
MODON - Weekly Progress Report - Construction Projects
| Contract General Information | [7 empty] | Key Dates | [10 empty] | Cost Summary (SR) | [8 empty] | Performance Summary | [11 empty] | Shop Drawings |  |  |  | Material Approval |  |  | Procurement Summary | [6 empty] | Quality Reports | [15 empty] | Key Submittals Approval Status | [9 empty] | Invoices Summary | [13 empty] | Resources at Site | [6 empty] | Safety Statistics | [63 empty] | Primavera P6 Schedule Status | [7 empty] | Testing And Commissioning
Data Date | Project Name | Project ID | Contractor | Consultant | Stage | Status | Modon PM | Project Scope | Contract Award | Contract Sign | Site Handover | Original Completion | Contract Award (Hijri) | Contract Sign (Hijri) | Site Handover (Hijri) | Original Completion (Hijri) | Revised Completion | Committed Completion | Forecast Completion | Original Contract Value | Revised Contract Value | Estimate At Completion Value | Potential Changes | O&M Value | Revised O&M Value | Submitted Invoices (Gross Value) | Total Deduction | Original Plan Value | Plan Value | Earn Value | Phys. Plan Value | Phys. Earn Value | Quality Score | Safety Score | Weekly PV (SAR) | Weekly EV (SAR) | Weekly PV % | Weekly PV % | Weekly Phys PV% | Weekly Phys PV% | Total SD Planned | SD Remaining | SD Pending | Total SD Submittals | Planned Materials Approv | Material Pending Approval | Materila Total Submittals | Total Materials Planned | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Actual Material on Site | Remaining Materials | Material Delivery Completion (Date) | NCR Issued | NCR Closed | NCR Pending | NCR Avg. Closing (Days) | SIR Issued | SIR Closed | SIR Pending | SIR Avg. Closing (Days) | MIR Issued | MIR Closed | MIR Pending | MIR Avg. Closing (Days) | FIR Issued | FIR Closed | FIR Pending | FIR Avg. Closing (Days) | 1 Quality Plan Approval | 2 Quality Plan Last Up | 3 Safety Plan Approval | 4 Safety Plan Last Up | 5 Construction Plan Approval | 6 Baseline Approval | 7 No of Approved Version of Schedule | 8 Last Approved Schedule | 9 BOQ Approval Date | 10 No of Approved Version of BOQ | Total Submitted Invoices | PM Approved Invoices | No of Paid Invoices | No of Pending Invoices | Advance Payment % | Retention % | Deduction / Penalties % | Submitted Invoices (SAR) | PM Approved Invoices (SAR) | Paid Invoices (SAR) | Last Submitted Period | Advance Payment (SAR) | Retention (SAR) | Deduction / Penalties (SAR) | Planned Head Count | Actual Head Count | Saudi Staff | Labor Planned | Labor Actual | Equipment Planned | Equipment Actual | This Week Total Hours Worked | This Week Safe Hours Worked | This Week LTI | This Week MTC (Healed w/o Disability) | This Week MTC (Healed w/ Disability) | This Week Near Miss | This Week First Aid Cases | This Week Fatality | This Week Fire Incident Cases | This Week Vehicle Incident | This Week Property Damages | This Week Induction Training | This Week No.of Internal Training | This Week No.of Internal Audit | This Week No. of Toolbox Talks | This Week Safety Awards/Incentives | This Month Total Hours Worked | This Month Safe Hours Worked | This Month LTI | This Month MTC (Healed w/o Disability) | This Month MTC (Healed w/ Disability) | This Month Near Miss | This Month First Aid Cases | This Month Fatality | This Month Fire Incident Cases | This Month Vehicle Incident | This Month Property Damages | This Month Induction Training | This Month No.of Internal Training | This Month No.of Internal Audit | This Month No. of Toolbox Talks | This Month Safety Awards/Incentives | YTD Total Hours Worked | YTD Safe Hours Worked | YTD LTI | YTD MTC (Healed w/o Disability) | YTD MTC (Healed w/ Disability) | YTD Near Miss | YTD First Aid Cases | YTD Fatality | YTD Fire Incident Cases | YTD Vehicle Incident | YTD Property Damages | YTD Induction Training | YTD No.of Internal Training | YTD No.of Internal Audit | YTD No. of Toolbox Talks | YTD Safety Awards/Incentives | Cum Total Hours Worked | Cum Safe Hours Worked | Cum LTI | Cum MTC (Healed w/o Disability) | Cum MTC (Healed w/ Disability) | Cum Near Miss | Cum First Aid Cases | Cum Fatality | Cum Fire Incident Cases | Cum Vehicle Incident | Cum Property Damages | Cum Induction Training | Cum No.of Internal Training | Cum No.of Internal Audit | Cum No. of Toolbox Talks | Cum Safety Awards/Incentives | Total Act. | Not Started | In Progress | Completed | Critical Path Act.Last Week | Critical Path Act.This Week | Failed start Last Week | Failed start This Week | Planned Start Date | Planned Finish Date | Forecast Start Date | Forecast Finish Date | Actual Start Date | Actual Finish Date | % Completed | Open Comments | Closed Comments
2026-10-12 | Playground Initiative for Western Region (Asir - Jazan - Jeddah) | MLTX-02-004 | Profast Company Ltd. | Saudi Arabia Consulting Engineering Company "EGIS" | Construction | Active | Engr.Yazeed Al Ragabh | The Scope of Works for the Playground Initiative for Western Region (ASIR - JAZAN – JEDDAH) according to the following contents. - Playground Area (Padel – Basketball – football) - Service & Toilet Building - Land Scape Works - Bike & Walking Paths - Parking | 2026-02-04 | 2026-03-04 | 2026-03-26 | 2027-01-25 | 2026-02-04 | 2026-03-04 | 2026-03-26 | 2027-01-25 | 2027-01-25 | 2027-01-25 | 2027-05-02 | 33997787 | 33793604.34 | 33997787 | -204182.66 | 0 | 0 | 4943710.6384 | 11000 | 10.54% | 34.25% | 32.96% | 46.97% | 38.99% | 0.85707 | 0.8375 | 2365481.37 | 1453507.9 | 7% | 4.301% | 3.621% | 1.703% | 144 | 6 | 4 | 142 | 142 | 1 | 144 | 141 | 76 | 35 | 41 | 22 | 54 | 0 | 19 | 19 | 0 | 0 | 25 | 24 | 1 | 0 | 96 | 93 | 3 | 0 | 605 | 580 | 24 | 0 | 2026-04-30 | - | 2026-06-11 | - | 2026-05-13 | 2026-04-28 | - | - | 2025-09-18 | 0 | 5 | 0 | 0 | 5 | 0 | 0 | 0.00032355 | 4943710.6384 | 0 | 0 | 2026-10-08 | 0 | 0 | 11000 | 175 | 70 | 0 | 19 | 30 | 9 | 5 | 6480 | 6480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 4 | 0 | 6480 | 6480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 04 Session | 0 | 4 Sessions | 0 | 132050 | 132050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 17 Session | 0 | 156 sessions | 0 | 132050 | 132050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 17 Session | 0 | 156 sessions | 0 | 2134 | 434 | 20 | 1680 | 367 | 373 | 255 | 266 | 2026-11-05 | 2026-11-30 | 2027-01-17 | 2027-02-10

## Weekly Progress Report
MODON - Weekly Progress Report - Construction Projects | [30 empty] | Data Date | 2026-10-12
Contract General Information | [5 empty] | Key Dates | [5 empty] | Cost Summary (SR) | [7 empty] | Performance Summary | [5 empty] | Project Scope
Project Name | Playground Initiative for Western Region (Asir - Jazan - Jeddah) |  |  |  |  | Contract Award | 2026-02-04 | Contract Award (Hijri) | 2026-02-04 | Revised Completion | 2027-01-25 | Original Contract Value |  | 33997787 |  | O&M Value |  | 0 | EAC | Plan Value | 34.25% | Phys. Plan Value | 46.97% | Quality Score | 85.71% | The Scope of Works for the Playground Initiative for Western Region (ASIR - JAZAN – JEDDAH) according to the following contents. - Playground Area (Padel – Basketball – football) - Service & Toilet Building - Land Scape Works - Bike & Walking Paths - Parking
Project ID | MLTX-02-004 |  | Stage | Construction |  | Contract Sign | 2026-03-04 | Contract Sign (Hijri) | 2026-03-04 | Committed Completion | 2027-01-25 | Revised Contract Value |  | 33793604.34 | EAC | Revised O&M Value |  | 0 | #REF! | Earn Value | 32.96% | Phys. Earn Value | 38.99% |  | ¢¢¢¢¢ ¢¢¢££
Contractor | Profast Company Ltd. |  | Status | Active |  | Site Handover | 2026-03-26 | Site Handover (Hijri) | 2026-03-26 | Forecast Completion | 2027-05-02 | Estimate At Completion Value |  | 33997787 | #REF! | Submitted Invoices (Gross Value) |  | 4943710.6384 |  | Variance | -1.291% | Variance | -7.976% | Safety Score | 83.75%
Consultant | Saudi Arabia Consulting Engineering Company "EGIS" |  | Modon PM | Engr.Yazeed Al Ragabh |  | Original Completion | 2027-01-25 | Original Completion (Hijri) | 2027-01-25 | Variance | -97 | Potential Changes |  | -204182.66 |  | Total Deduction |  | 11000 |  | SPI | 0.9623 | SPI | 0.83019 |  | ¢¢¢¢¢ ¢¢¢££
Progress Overview
Earned Value Progress (SAR) | [13 empty] | Physical Progress (Effort) | [11 empty] | Earned Value Progress (%)
WBS |  | BOQ Value (SAR) | % Wt. | Weekly (SAR) |  | To Date (SAR) | [7 empty] | Budgeted | % Wt. | Weekly Physical Progress |  |  |  | To Date Physical Progress
|  |  |  | Planned | Earned | Original Plan | Revised Planned | Earned | Original Plan % | Revised Planned % | Earned % | Variance | SPI | (Manhours) |  | Planned | Earned | Plan % | Earned % | Planned | Earned | Plan % | Earned % | Variance | SPI
|  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0%
Moblization |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 12659 | 3.116% | -0.4 | -0.4 | -0.00316% | -0.00316% | 12658.6 | 12658.6 | 100% | 100% | 0% | 1
Engineering |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 21299 | 5.243% | 0.5 | 0.2 | 0.002348% | 0.000939% | 21299.5 | 20929.2 | 100% | 98.26% | -1.739% | 0.98261
Procurment |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 51273 | 12.62% | 430.59 | 450.4 | 0.8398% | 0.8784% | 50435.59 | 26870.4 | 98.37% | 52.41% | -45.96% | 0.53277
Construction |  | 33793604.34 | 100% | 1182740.69 | 726753.95 | 3561002.22 | 11574034.12 | 11137727.29 | 10.54% | 34.25% | 32.96% | -1.291% | 0.9623 | 299660 | 73.76% | 14280.26 | 6467 | 4.765% | 2.158% | 106418.26 | 97952 | 35.51% | 32.69% | -2.825% | 0.92044
Jazan Region |  | 10680071.52 | 31.6% | 375287.25 | 181207.68 | 794325.94 | 3550245.27 | 2469126.02 | 7.437% | 33.24% | 23.12% | -10.12% | 0.69548 | 102280 | 25.18% | 6190.05 | 2015 | 6.052% | 1.97% | 40380.05 | 20350 | 39.48% | 19.9% | -19.58% | 0.50396
Asir Region |  | 10578073.08 | 31.3% | 166367.52 | 229316.88 | 1310370.14 | 2445845.81 | 3748970.85 | 12.39% | 23.12% | 35.44% | 12.32% | 1.5328 | 96810 | 23.83% | 3681.69 | 1606 | 3.803% | 1.659% | 33248.69 | 38422 | 34.34% | 39.69% | 5.344% | 1.1556
Jeddah Region |  | 12535459.74 | 37.09% | 641085.91 | 316229.39 | 1456306.14 | 5577943.03 | 4919630.42 | 11.62% | 44.5% | 39.25% | -5.252% | 0.88198 | 100570 | 24.76% | 4408.52 | 2846 | 4.384% | 2.83% | 32789.52 | 39180 | 32.6% | 38.96% | 6.354% | 1.1949
Testing & Commissioning |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 12818 | 3.155% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
Close-Out |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 8546 | 2.104% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
|  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | 0% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
|  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | 0% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
|  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | 0% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
|  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | 0% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
|  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | 0% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
|  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | 0% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
| Total | 33793604.34 | 100% | 2365481.37 | 1453507.9 | 3561002.22 | 11574034.11 | 11137727.29 | 10.54% | 34.25% | 32.96% | -1.291% | 0.9623 | 406255 | 100% | 14710.95 | 6917.2 | 3.621% | 1.703% | 190811.95 | 158410.2 | 46.97% | 38.99% | -7.976% | 0.83019
Construction Milestones
[26 empty] | Item No. | Milestones |  | Original (Baseline) | Latest Plan | Forecast | Status | Days Change
[26 empty] | 1 | Project Finish |  | 2027-01-25 | 2027-05-02 | 2027-05-02 | F | -97
[25 empty] | #REF! | 2 | Project Start |  | 2026-03-26 | 2026-03-26 | 2026-03-26 | A | 0
[25 empty] | #REF! | 3 | Baseline Programme Approval |  | 2026-06-02 | 2026-04-25 | 2026-04-25 | A | 38
[25 empty] | #REF! | 4 | Completion of Mobilization |  | 2027-01-25 | 2026-06-02 | 2026-06-02 | A | 237
[25 empty] | #REF! | 5 | Completion of Levelling Works |  | 2026-07-22 | 2026-10-13 | 2026-10-13 | F | -83
[25 empty] | #REF! | 6 | Completion of Engineering |  | 2027-01-19 | 2026-10-29 | 2026-10-29 | F | 82
[6 empty] | 20000000 | [18 empty] | #REF! | 7 | Completion of Toilet Building |  | 2026-08-09 | 2027-01-09 | 2027-01-09 | F | -153
[26 empty] | 8 | Completion of Natural Landscape Works |  | 2027-01-16 | 2027-03-03 | 2027-03-03 | F | -46
[26 empty] | 9 | Completion of Playground Area |  | 2026-11-30 | 2027-04-22 | 2027-04-22 | F | -143
[25 empty] | #REF! | 10 | Completion of Asir Works |  | 2026-12-13 | 2027-03-24 | 2027-03-24 | F | -101
#REF!
[25 empty] | #REF! | [6 empty] | This Week
#REF!
#REF!
[6 empty] | 20000000 | [18 empty] | #REF!
#REF!
#REF!
Performance overview
Submittals Status | [10 empty] | Quality | [10 empty] | Safety
Shop Drawings | [10 empty] | Quality Reports | [10 empty] | Safety Statistics | [7 empty] | Proactive Vs Reactive Actions Taken
Item Per WBS |  | Total | Total Submitted Drawings |  |  |  |  | Remaining | Pending | Total Submittals | Quality Reports |  | Issued | Closed | Pending | Avg. Closing (Days) | Pending |  |  |  |  | Category | Item |  |  |  | This Month | Year to Date | Cumulative
|  |  | A | B | C | D | Processed | [9 empty] | 0-10 Days | 11-20 Days | 21-30 Days | 31-60 Days | > 60 Days
Civil/Structure |  | 36 | 7 | 24 | 2 | 3 | 36 | 0 | 2 | 38 | [11 empty] | General | Total Hours Worked |  | 6480 |  | 6480 | 132050 | 132050 |  |  | Proactive | 160
Architecture |  | 20 | 3 | 14 | 2 | 0 | 19 | 1 | 0 | 19 | Non Conformance (NCR) |  | 19 | 19 | 0 | 0 | 2 | 0 | 0 | 0 | 0 |  | Safe Hours Worked |  | 6480 |  | 6480 | 132050 | 132050 |  |  | Reactive | 0
Mechanical |  | 25 | 0 | 19 | 4 | 0 | 23 | 2 | 2 | 25 | Site Instruction (SIR) |  | 25 | 24 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | Reactive | LTI |  | 0 |  | 0 | 0 | 0
Electrical |  | 38 | 0 | 34 | 0 | 3 | 37 | 1 | 0 | 37 | Material Inspection (MIR) |  | 96 | 93 | 3 | 0 | 11 | 0 | 0 | 0 | 0 |  | MTC (Healed w/o Disability) |  | 0 |  | 0 | 0 | 0
Landscape |  | 25 | 7 | 14 | 2 | 0 | 23 | 2 | 0 | 23 | Field Inspection (FIR) |  | 605 | 580 | 24 | 0 | 46 | 0 | 0 | 0 | 0 |  | MTC (Healed w/ Disability) |  | 0 |  | 0 | 0 | 0
[11 empty] | Key Submittals Approval Status | [11 empty] | Near Miss |  | 0 |  | 0 | 0 | 0
TOTAL |  | 144 | 17 | 105 | 10 | 6 | 138 | 6 | 4 | 142 | 1 Quality Plan Approval |  |  | 2026-04-30 |  | 6 Baseline Approval |  |  |  | 2026-04-28 |  |  | First Aid Cases |  | 0 |  | 0 | 0 | 0 | Total Hours Worked Vs Safe Hours Worked
Material Approval | [10 empty] | 2 Quality Plan Last Up |  |  | - |  | 7 No of Approved Version of Schedule |  |  |  | - |  |  | Fatality |  | 0 |  | 0 | 0 | 0
Item Per WBS |  | Total | Total Submitted Material |  |  |  |  | Remaining to approve | Pending | Total Submittals | 3 Safety Plan Approval |  |  | 2026-06-11 |  | 8 Last Approved Schedule |  |  |  | - |  |  | Fire Incident Cases |  | 0 |  | 0 | 0 | 0
|  |  | A | B | C | D | Processed | with Designer |  |  | 4 Safety Plan Last Up |  |  | - |  | 9 BOQ Approval Date |  |  |  | 2025-09-18 |  |  | Vehicle Incident |  | 0 |  | 0 | 0 | 0
Civil/Structure |  | 48 | 2 | 40 | 5 | 2 | 42 | 6 | 0 | 49 | 5 Construction Plan Approval |  |  | 2026-05-13 |  | 10 No of Approved Version of BOQ |  |  |  | 0 |  |  | Property Damages |  | 0 |  | 0 | 0 | 0
Architecture |  | 26 | 2 | 24 | 0 | 0 | 26 | 0 | 0 | 26 | Invoices Summary | [10 empty] | Proactive | Induction Training |  | 0 |  | 18 | 160 | 160
Mechanical |  | 32 | 0 | 30 | 2 | 0 | 30 | 2 | 0 | 32 | Total Submitted Invoices |  | 5 | Submitted Invoices (SAR) |  |  | 4943710.6384 |  | Contract Value (SR) | 33793604.34 |  |  | No.of Internal Training |  | 1 |  | 04 Session | 17 Session | 17 Session
Electrical |  | 36 | 0 | 31 | 4 | 1 | 31 | 5 | 1 | 37 | PM Approved Invoices |  | 0 | PM Approved Invoices (SAR) |  |  | 0 |  | Planned Value (SR) | 11574034.11 |  |  | No.of Internal Audit |  | 0 |  | 0 | 0 | 0
[11 empty] | No of Paid Invoices |  | 0 | Paid Invoices (SAR) |  |  | 0 |  | Earned Value (SR) | 11137727.29 |  |  | No. of Toolbox Talks |  | 4 |  | 4 Sessions | 156 sessions | 156 sessions
TOTAL |  | 142 | 4 | 125 | 11 | 3 | 129 | 13 | 1 | 144 | No of Pending Invoices |  | 5 | Last Submitted Period |  |  | 2026-10-08 |  | Submitted (SAR) | 4943710.6384 |  |  | Safety Awards/Incentives |  | 0 |  | 0 | 0 | 0
Procurement Summary | [10 empty] | Advance Payment % |  | 0% | Advance Payment (SAR) |  |  | 0 |  | PM Approved (SAR) | 0 |  | Latest Contract Change Order Log
Item Per WBS |  | Total Materials Planned | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Actual Material on Site | Remaining Materials | Material Delivery Completion (Date) |  |  | Retention % |  | 0% | Retention (SAR) |  |  | 0 |  | Total Paid (SAR) | 0
|  |  | A | B | C | D | Processed |  |  |  | Deduction / Penalties % |  | 0.03236% | Deduction / Penalties (SAR) |  |  | 11000 |  |  |  |  | CCO No. | Date Added | Description of Change |  |  |  |  | Status | Cost | Sch Impact (Months) | Date Approved | Duration
Civil/Structure |  | 48 | 27 | 5 | 22 | 5 | 22 | 0 | 0 | 0 | Resources at Site
Architecture |  | 25 | 18 | 14 | 4 | 7 | 11 | 0 | 0 | 0 | Head Count - Manual |  |  |  | Head Count - Non Manual |  |  |  | Total Head Count |  |  | - | - | - |  |  |  |  | - | - | - | - | -
Mechanical |  | 32 | 18 | 10 | 8 | 7 | 11 | 0 | 0 | 0 | Planned | Actual | Next Month Forecast | Saudi Staff | Planned | Actual | Next Month Forecast | Saudi Staff | Total Plan | Total Actual | Variance
Electrical |  | 36 | 13 | 6 | 7 | 3 | 10 | 0 | 0 | 0 | 175 | 70 | 140 | 0 | 19 | 30 | 25 | 0 | 194 | 100 | -94
[11 empty] | Manpower Breakdown by Trade | [6 empty] | Major Equipment
TOTAL |  | 141 | 76 | 35 | 41 | 22 | 54 | 0 |  |  | Key Trade | Planned | Actual |  |  |  |  | Type | Planned | Actual | Idle
Primavera P6 Schedule Status | [10 empty] | Labor | 65 | 15 |  |  |  |  | Excavator | 3 | 3 | 0
Project Activities Overview | [10 empty] | Skilled Labor | 25 | 10 |  |  |  |  | Bulldozer | 2 | 0 | 0 | Major Quantity Trackers
Schedule Statistics |  |  |  |  | Active Schedule Activities | [5 empty] | Driver / Operator | 27 | 12 |  |  |  |  | Grader | 3 | 0 | 0 | BOQ N0. | Item Description |  |  |  |  | Total Qty | Measu Unit | Plan to Date | Act to Date | Remaining | Variance
Total Act. | Not Started | In Progress | Completed | % | Active | Ahead | On | Behind | Flag | 0 | Carpenter | 0 | 6 |  |  |  |  | Road Roller | 1 | 0 | 0 | 2.3.1 | Supply and plant trees |  |  |  |  | 895 | Nos. | 0 | 0 | 30380 | 0
2134 | 434 | 20 | 1680 | 78.73% | 20 | 23 | 185 | 226 | -18 |  | Steel Fixer | 26 | 6 |  |  |  |  | Crane | 0 | 0 | 0 | 2.3.10 | Supply and cast Concrete |  |  |  |  | 145 | m³ | 0 | 0 | 248 | 0
Critical Path Activities |  |  | Free Float Management (Total) |  |  |  | Failed Start Activities |  |  |  | Mason | 0 | 0 |  |  |  |  | Bobcat | 0 | 2 | 0 | 9.1.1 | CEILING FINISHES |  |  |  |  | 207 | m² | 0 | 0 | 219 | 0
|  |  | Greater Than 14 Days |  | Less Than 14 Days | [5 empty] | Plumber | 0 | 3 |  |  |  |  | Other | 0 | 0 | 0 | 9.3 | WATER SUPPLY SYSTEM for cold and hot water supply piping |  |  |  |  | 138 | Lm | 0 | 0 | 207 | 0
Last Week | This Week | Diff | Last Week | This Week | Last Week | This Week | Last Week | This Week | Flag | 0 | Total | 175 | 70 |  |  |  |  | Total | 9 | 5 | 0 | 15.2.1 | SEWER AND DRAINAGE PIPE |  |  |  |  | 177 | Lm | 0 | 14 | 124 | 14
367 | 373 | -6 | 89 | 80 | 387 | 374 | 255 | 266 | -11
Testing And Commissioning | [14 empty] | Top Issues and Risks
Top 5 Issues
Item | Planned Start Date |  | Planned Finish Date |  | Forecast Start Date |  | Forecast Finish Date |  | Actual Start Date |  | Actual Finish Date | % Completed | Open Comments | Closed Comments | Issue No |  | Date Identified | Issue Description |  |  | Responsible |  | Action Taken |  |  |  |  | Mitigation |  |  | Current Status | Expected/Actual Closure | Duration Elapsed
Testing and Commissioning for MEP Works for Landscape Works - Jazan | 2026-12-27 |  | 2027-01-13 |  | 2027-04-21 |  | 2027-04-26 | [7 empty] | 1 |  |  | Connection of the project to the drainage channel on the eastern side.(Jeddah) |  |  | Contractor |  | Coordination between the Municipality (City Management) and the infrastructure contractor. | [7 empty] | Completed | 2026-05-21
Testing and Commissioning for MEP Works for Toilet/Service Building - Jazan | 2026-11-17 |  | 2026-12-15 |  | 2027-02-02 |  | 2027-03-03 | [7 empty] | 2 |  |  | drainage pipe was encountered during site excavation.(Jeddah) |  |  | Owner |  | The required calculations and slope analysis have been completed. | [7 empty] | Completed | 2026-05-21
Testing and Commissioning for MEP Works for Playground Area - Jazan | 2027-01-14 |  | 2027-01-19 |  | 2027-04-08 |  | 2027-04-26 | [7 empty] | 3 |  | 2026-05-05 | Based on the visit by Modon management, it was noted that the project level can be raised to match the external road level in front of the parking area.(Jeddah) |  |  | Owner |  | The required filling quantity was estimated at 59,000 m³ | [7 empty] | Completed | 2026-05-21
Testing and Commissioning for MEP Works for Landscape Works - Asir | 2027-01-02 |  | 2027-01-12 |  | 2027-03-20 |  | 2027-03-30 | [7 empty] | 4 |  |  | Increase the sewage tank capacity for the Asir project to serve the administration building and playgrounds. |  |  | Contractor |  | Waiting for clarification of the project savings/cost reductions. | [7 empty] | Completed | 2026-05-10
Testing and Commissioning for MEP Works for Toilet/Service Building - Asir | 2026-11-05 |  | 2026-11-30 |  | 2027-01-17 |  | 2027-02-10 | [7 empty] | 5 |  | 2026-05-21 | Difficulty accessing the parking area due to a level difference- Jazan |  |  | Consultant |  | Relocating the parking area to the far left side. | [7 empty] | Completed | 2026-05-16
Testing and Commissioning for MEP Works for Playground Area - Asir | 2026-12-01 |  | 2026-12-26 |  | 2027-02-11 |  | 2027-03-09 | [7 empty] | 6 |  | 13-05-2026 | Road shoulder overlap at the Jeddah site |  |  | Consultant |  | A proposal has been submitted to the consultant. | [7 empty] | Completed | 2026-10-01
Testing and Commissioning for MEP Works for Landscape Works - Jeddeh | 2027-01-05 |  | 2027-01-13 |  | 2027-04-14 |  | 2027-04-18 | [7 empty] | 7 |  | 2026-02-06 | Trees located within Asir site. |  |  | Owner |  | Waiting for tree removal by the landscaping contractor. | [7 empty] | Completed | 2026-05-16
Testing and Commissioning for MEP Works for Toilet/Service Building - Jeddeh | 2026-12-01 |  | 2026-12-17 |  | 2026-12-31 |  | 2027-01-17 | [9 empty] | 2026-10-10 | Medium voltage cables on excavation way |  |  | Owner |  | Medium voltage cables are conflicting with the excavation route. Assessment and coordination with relevant stakeholders are ongoing to determine the required mitigation actions. Risk remains open. | [7 empty] | Open
Testing and Commissioning for MEP Works for Playground Area - Jeddeh | 2027-01-14 |  | 2027-01-18 |  | 2027-03-31 |  | 2027-04-08
988,742

## General Information
Weekly Progress Report - Construction Projects |  |  | Data Date | 2026-10-12
Contract General Information
Project Name | Playground Initiative for Western Region (Asir - Jazan - Jeddah)
Project ID | MLTX-02-004
Contractor | Profast Company Ltd.
Consultant | Saudi Arabia Consulting Engineering Company "EGIS"
Stage | Construction
Status | Active
Modon PM | Engr.Yazeed Al Ragabh
Key Dates
Contract Award Date | 2026-02-04
Contract Sign Date | 2026-03-04
Site Handover Date | 2026-03-26
Original Completion | 2027-01-25
Contract Award Date (Hijri) | 2026-02-04
Contract Sign Date (Hijri) | 2026-03-04
Site Handover Date (Hijri) | 2026-03-26
Original Completion (Hijri) | 2027-01-25
Revised Completion Date | 2027-01-25
Committed Completion Date | 2027-01-25
Forecast Completion | 2027-05-02
Variance | -97
Key Project Submittals | Submission Date | Days taken to approve orginal plan from site handover date
Quality Plan submission | 2026-04-11 | 16
Quality Plan approval | 2026-04-30
Quality Plan Last Update | -
Safety Plan submission | 2026-04-11 | 16
Safety Plan approval | 2026-06-11
Safety Plan Last Update | -
Risk Management Plan submission | 2026-04-29 | 34
Risk Management Plan approval
Risk Management Plan Last Update | -
Baseline Schedule submission | 2026-04-28 | 33
Baseline Schedule approval | 2026-04-28
No of Schedule Versions | -
Last Revised Schedule Approval Date | -
BOQ submission | 2025-09-18 | -189
BOQ approval | 2025-09-18
No of Approved Version of BOQ
Execution Plan submission | 2026-04-30 | 35
Execution Plan Approval | 2026-05-13
Note on D25: AlNuaim, Abdulaziz: As per contract requirments submission of Plans should be 30 days after site handover

## Milestones
Project Name
Item No. | Milestones | Original (Baseline) | Latest | Forecast |  | Days Change
|  |  | 43.5714 | 57.4286 |  | -97
1 | Project Finish | 2027-01-25 | 2027-01-25 | 2027-05-02 | F | -97
2 | Project Start | 2026-03-26 | 2026-03-26 | 2026-03-26 | A | 0
3 | Baseline Programme Approval | 2026-06-02 | 2026-06-02 | 2026-04-25 | A | 38
4 | Completion of Mobilization | 2027-01-25 | 2027-01-25 | 2026-06-02 | A | 237
5 | Completion of Levelling Works | 2026-07-22 | 2026-07-22 | 2026-10-13 | F | -83
6 | Completion of Engineering | 2027-01-19 | 2027-01-19 | 2026-10-29 | F | 82
7 | Completion of Toilet Building | 2026-08-09 | 2026-08-09 | 2027-01-09 | F | -153 |  |  | 2026-04-29
8 | Completion of Natural Landscape Works | 2027-01-16 | 2027-01-16 | 2027-03-03 | F | -46
9 | Completion of Playground Area | 2026-11-30 | 2026-11-30 | 2027-04-22 | F | -143
10 | Completion of Asir Works | 2026-12-13 | 2026-12-13 | 2027-03-24 | F | -101
11 | Completion of Jazan Works | 2027-01-19 | 2027-01-19 | 2027-05-02 | F | -103
12 | Completion of Jeddah Works | 2027-01-25 | 2027-01-25 | 2027-04-06 | F | -71
13 | Completion of Testing & Commissioning | 2026-04-29 | 2026-04-29 | 2027-04-07 | F | -343
Activity ID | Activity Name | Activity Status | Original Duration | Duration % Complete | Schedule % Complete | Performance % Complete | Earned Value Cost | Planned Value Cost | Start | Finish | BL1 Start | BL1 Finish | Budgeted Total Cost
MLTX-02-004 - Playground Initiative for Western Region (Asir - Jazan - Jeddah) - Updating 02-06-2026 |  |  | 310 | 18.06% | 5.76% | 5.34% | 1816335.29 | 1958160.74 | 26-Mar-26 A | 2027-03-31 | 2026-03-26 | 2027-03-31 | 33997787
KEY MILESTONES |  |  | 310 | 21.29% | 0% | 0% | 0 | 0 | 26-Mar-26 A | 2027-03-31 | 2026-03-26 | 2027-03-31 | 0
GENERAL MILESTONES |  |  | 310 | 100% | 0% | 0% | 0 | 0 | 26-Mar-26 A | 2027-03-31 | 2026-03-26 | 2027-03-31 | 0
MLTX-02-004-MS-1010 | Project Commencement Date | Completed | 0 | 100% | 100% | 100% | 0 | 0 | 26-Mar-26 A |  | 2026-03-26 |  | 0
MLTX-02-004-MS-1030 | Project Completion | Not Started | 0 | 0% | 0% | 0% | 0 | 0 |  | 2027-03-31 |  | 2027-03-31 | 0
CONTRACTUAL MILESTONE |  |  | 271 | 13.28% | 0% | 0% | 0 | 0 | 29-Apr-26 A | 2027-03-21 | 2026-04-29 | 2027-03-21 | 0
MLTX-02-004-MS-1060 | Baseline Programme Approval | Completed | 0 | 100% | 100% | 100% | 0 | 0 |  | 29-Apr-26 A |  | 2026-04-29 | 0
MLTX-02-004-MS-1050 | Completion of Mobilization | Completed | 0 | 100% | 100% | 100% | 0 | 0 |  | 02-Jun-26 A |  | 2026-06-11 | 0
MLTX-02-004-MS-1120 | Completion of Levelling Works | Not Started | 0 | 0% | 100% | 0% | 0 | 0 |  | 2026-06-14 |  | 2026-06-14 | 0
MLTX-02-004-MS-1100 | Completion of Engineering | Not Started | 0 | 0% | 100% | 0% | 0 | 0 |  | 2026-06-29 |  | 2026-06-29 | 0
MLTX-02-004-MS-1130 | Completion of Toilet Building | Not Started | 0 | 0% | 0% | 0% | 0 | 0 |  | 2026-09-27 |  | 2026-09-27 | 0
MLTX-02-004-MS-1150 | Completion of Natural Landscape Works | Not Started | 0 | 0% | 0% | 0% | 0 | 0 |  | 2027-01-26 |  | 2027-01-26 | 0
MLTX-02-004-MS-1140 | Completion of Playground Area | Not Started | 0 | 0% | 0% | 0% | 0 | 0 |  | 2027-02-27 |  | 2027-02-27 | 0
MLTX-02-004-MS-1160 | Completion of Asir Works | Not Started | 0 | 0% | 0% | 0% | 0 | 0 |  | 2027-03-21 |  | 2027-03-21 | 0
MLTX-02-004-MS-1170 | Completion of Jazan Works | Not Started | 0 | 0% | 0% | 0% | 0 | 0 |  | 2027-03-21 |  | 2027-03-21 | 0
MLTX-02-004-MS-1180 | Completion of Jeddah Works | Not Started | 0 | 0% | 0% | 0% | 0 | 0 |  | 2027-03-21 |  | 2027-03-21 | 0
MLTX-02-004-MS-1070 | Completion of Testing & Commissioning | Not Started | 0 | 0% | 0% | 0% | 0 | 0 |  | 2027-03-21 |  | 2027-03-21 | 0
Formulas:
Forecast = [Latest]

## Progress
Project Scope Statement | Playground Initiative for Western Region (Asir - Jazan - Jeddah)
Earned Value Progress (SAR) | [10 empty] | Physical Progress (Effort)
WBS |  | BOQ Value (SAR) | % Wt. | Weekly (SAR) |  |  | To Date (SAR) |  | Actual % |  | Budgeted | % Wt. | Weekly Physical Progress |  | To Date Physical Progress |  |  |  | Last Week Cost (SAR) |  | Last Week Physical Progress
|  |  |  | Planned | Earned | Original Plan | Planned | Earned |  |  | (Manhours) |  | Planned | Earned | Planned | Earned |  |  | Planned | Earned | Planned | Earned
Moblization |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% |  | 12659 | 3.116% | -0.4 | -0.4 | 12658.6 | 12658.6 |  |  | 0 | 0 | 12659 | 12659
Engineering |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% |  | 21299 | 5.243% | 0.5 | 0.2 | 21299.5 | 20929.2 |  |  |  |  | 21299 | 20929
Procurment |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% |  | 51273 | 12.62% | 430.59 | 450.4 | 50435.59 | 26870.4 |  |  |  |  | 50005 | 26420 |  |  | -450.4
Construction |  | 33793604.34 | 100% | 1182740.69 | 726753.95 | 3561002.22 | 11574034.12 | 11137727.29 | 32.96% |  | 299660 | 73.76% | 14280.26 | 6467 | 106418.26 | 97952 |  |  | 10391293.43 | 10410973.34 | 92138 | 91485
Jazan Region |  | 10680071.52 | 31.6% | 375287.25 | 181207.68 | 794325.94 | 3550245.27 | 2469126.02 | 7.306% |  | 102280 | 25.18% | 6190.05 | 2015 | 40380.05 | 20350 |  |  | 3174958.02 | 2287918.34 | 34190 | 18335
Asir Region |  | 10578073.08 | 31.3% | 166367.52 | 229316.88 | 1310370.14 | 2445845.81 | 3748970.85 | 11.09% |  | 96810 | 23.83% | 3681.69 | 1606 | 33248.69 | 38422 |  |  | 2279478.29 | 3519653.97 | 29567 | 36816
Jeddah Region |  | 12535459.74 | 37.09% | 641085.91 | 316229.39 | 1456306.14 | 5577943.03 | 4919630.42 | 14.56% |  | 100570 | 24.76% | 4408.52 | 2846 | 32789.52 | 39180 |  |  | 4936857.12 | 4603401.03 | 28381 | 36334
Testing & Commissioning |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% |  | 12818 | 3.155% | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
Close-Out |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% |  | 8546 | 2.104% | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
[14 empty] | 0 | 0 | 0
0
0
0
0
0
|  |  |  | 0 | 0 | [7 empty] | 0 | 0
|  |  |  | 0 | 0 | [7 empty] | 0 | 0
|  |  |  | 0 | 0 | [7 empty] | 0 | 0
| Total | 33793604.34 | 100% | 1182740.68 | 726753.95 | 3561002.22 | 11574034.11 | 11137727.29 | 32.96% |  | 406255 | 100% | 14710.95 | 6917.2 | 190811.95 | 158410.2 |  |  | 10391293.43 | 10410973.34 | 176101 | 151493
[6 empty] | 10.54% | 34.25% | 32.96% | [6 empty] | 46.97% | 38.99%
1.291%
Activity ID | Activity Name | Activity Status | Activity % Complete | Duration % Complete | Physical % Complete | Units % Complete | Schedule % Complete | Performance % Complete | Actual Total Cost | Earned Value Cost | Planned Value Cost | Actual Labor Units | Earned Value Labor Units | Planned Value Labor Units | Original Duration | Start | Finish | BL Project Start | BL Project Finish | Budgeted Total Cost | Budgeted Labor Units | Remaining Duration | Actual Nonlabor Units | Remaining Nonlabor Units | Variance - BL Project Nonlabor Units | Variance - BL Project Labor Cost | Schedule Performance Index | Total Float | % Variance
Moblization |  |  |  | 100% |  | 100% | 0% | 0% | 0 | 0 | 0 | 12659 | 12659 | 12659 | 63 | 26-Mar-26 A | 10-Jun-26 A | 2026-03-26 | 2026-06-10 | 0 | 12659 | 0 | 0 | 0 | 0 | 0 | 0 |  | -405
Engineering |  |  |  | 75.6% |  | 98.26% | 0% | 0% | 0 | 0 | 0 | 20929 | 20929 | 21299 | 209 | 31-Mar-26 A | 2026-12-03 | 2026-03-31 | 2026-09-02 | 0 | 21299 | 51 | 0 | 0 | 0 | 0 | 0 | 45 | -43720
Procurment |  |  |  | 57.54% |  | 51.53% | 0% | 0% | 0 | 0 | 0 | 26420 | 26420 | 50005 | 252 | 06-May-26 A | 2027-02-07 | 2026-05-06 | 2026-12-07 | 0 | 51273 | 107 | 0 | 0 | 0 | 0 | 0 | -39 | -6715.38
Construction |  |  |  | 44.19% |  | 27.34% | 30.75% | 30.81% | 6676185.13 | 10410973.34 | 10391293.43 | 78820 | 91485 | 92138 | 310 | 25-Apr-26 A | 2027-04-29 | 2026-04-25 | 2027-01-25 | 33793604.34 | 299660 | 173 | 14900 | 28200 | 0 | 0 | 1 | -77 | -2645.55
Jazan Region |  |  |  | 43.09% |  | 14.49% | 29.73% | 21.42% | 1078119.75 | 2287918.34 | 3174958.02 | 14200 | 18335 | 34190 | 304 | 02-May-26 A | 2027-04-29 | 2026-05-02 | 2027-01-25 | 10680071.52 | 102280 | 173 | 2770 | 12060 | 0 | 0 | 0.72 | -77 | -959.18
Asir Region |  |  |  | 46.23% |  | 34.69% | 21.55% | 33.27% | 2376926.05 | 3519653.97 | 2279478.29 | 32200 | 36816 | 29567 | 292 | 27-Apr-26 A | 2027-04-11 | 2026-04-27 | 2027-01-24 | 10578073.08 | 96810 | 157 | 6200 | 7670 | 0 | 0 | 1.54 | -61 | -858.18
Jeddah Region |  |  |  | 48.41% |  | 33.36% | 39.38% | 36.72% | 3221139.32 | 4603401.03 | 4936857.12 | 32420 | 36334 | 28381 | 283 | 25-Apr-26 A | 2027-03-29 | 2026-04-25 | 2027-01-25 | 12535459.74 | 100570 | 146 | 5930 | 8470 | 0 | 0 | 0.93 | -50 | -828.18
Testing & Commissioning |  |  |  | 0% |  | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 2026-11-08 | 2027-04-24 | 2026-11-05 | 2027-01-19 | 0 | 12818 | 140 | 0 | 0 | 0 | 0 | 0 | -77 | 0
Close-Out |  |  |  | 0% |  | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 2027-03-02 | 2027-04-29 | 2027-01-14 | 2027-01-25 | 0 | 8546 | 48 | 0 | 360 | 0 | 0 | 0 | -77 | 0
No WBS-Project |  |  |  | 51.04% |  | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 335 | 26-Mar-26 A | 2027-04-29 | 2026-03-26 | 2027-01-25 | 0 | 0 | 164 | 0 | 0 | 0 | 0 | 0 | -77 | -200
Activity ID | Activity Name | Activity Status | Activity % Complete | Duration % Complete | Physical % Complete | Units % Complete | Schedule % Complete | Performance % Complete | Actual Total Cost | Earned Value Cost | Planned Value Cost | Actual Labor Units | Earned Value Labor Units | Planned Value Labor Units | Original Duration | Start | Finish | BL Project Start | BL Project Finish | Budgeted Total Cost | Budgeted Labor Units | Remaining Duration | Actual Nonlabor Units | Remaining Nonlabor Units | Variance - BL Project Nonlabor Units | Variance - BL Project Labor Cost | Schedule Performance Index | Total Float | % Variance
Moblization |  |  |  | 100% |  | 100% | 0% | 0% | 0 | 0 | 0 | 12658.6 | 12658.6 | 12658.6 | 63 | 26-Mar-26 A | 10-Jun-26 A | 2026-03-26 | 2026-06-10 | 0 | 12658.6 | 0 | 0 | 0 | 0 | 0 | 0 |  | -405
Engineering |  |  |  | 76.28% |  | 98.26% | 0% | 0% | 0 | 0 | 0 | 20929.2 | 20929.2 | 21299.5 | 215 | 31-Mar-26 A | 2026-12-10 | 2026-03-31 | 2026-09-02 | 0 | 21299.5 | 51 | 0 | 0 | 0 | 0 | 0 | 39 | -43720
Procurment |  |  |  | 57.54% |  | 52.41% | 0% | 0% | 0 | 0 | 0 | 26870.4 | 26870.4 | 50435.59 | 252 | 06-May-26 A | 2027-02-14 | 2026-05-06 | 2026-12-07 | 0 | 51273.3 | 107 | 0 | 0 | 0 | 0 | 0 | -43 | -6715.38
Construction |  |  |  | 45.83% |  | 29.59% | 34.25% | 32.96% | 7472734.75 | 11137727.29 | 11574034.12 | 85000 | 97952 | 106418.26 | 312 | 25-Apr-26 A | 2027-05-02 | 2026-04-25 | 2027-01-25 | 33793604.34 | 299659.7 | 169 | 16420 | 26680 | 0 | 0 | 0.96 | -79 | -2645.55
Jazan Region |  |  |  | 44.77% |  | 16.83% | 33.24% | 23.12% | 1364443.66 | 2469126.02 | 3550245.27 | 16500 | 20350 | 40380.05 | 306 | 02-May-26 A | 2027-05-02 | 2026-05-02 | 2027-01-25 | 10680071.52 | 102279.9 | 169 | 3210 | 11620 | 0 | 0 | 0.7 | -79 | -959.18
Asir Region |  |  |  | 49.3% |  | 36.22% | 23.12% | 35.44% | 2696845.87 | 3748970.85 | 2445845.81 | 33350 | 38422 | 33248.69 | 286 | 27-Apr-26 A | 2027-04-04 | 2026-04-27 | 2027-01-24 | 10578073.08 | 96809.9 | 145 | 6740 | 7130 | 0 | 0 | 1.53 | -55 | -858.18
Jeddah Region |  |  |  | 49.31% |  | 36.2% | 44.5% | 39.25% | 3411445.22 | 4919630.42 | 5577943.03 | 35150 | 39180 | 32789.52 | 290 | 25-Apr-26 A | 2027-04-06 | 2026-04-25 | 2027-01-25 | 12535459.74 | 100569.9 | 147 | 6470 | 7930 | 0 | 0 | 0.88 | -57 | -828.18
Testing & Commissioning |  |  |  | 0% |  | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 2026-12-13 | 2027-04-07 | 2026-11-05 | 2027-01-19 | 0 | 12818.4 | 96 | 0 | 0 | 0 | 0 | 0 | -63 | 0
Close-Out |  |  |  | 0% |  | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 2027-03-27 | 2027-04-19 | 2027-01-14 | 2027-01-25 | 0 | 8545.6 | 21 | 0 | 360 | 0 | 0 | 0 | -68 | 0
No WBS-Project |  |  |  | 49.85% |  | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 337 | 26-Mar-26 A | 2027-05-02 | 2026-03-26 | 2027-01-25 | 0 | 0 | 169 | 0 | 0 | 0 | 0 | 0 | -79 | -200
Activity ID | Activity Name | Activity Status | Activity % Complete | Duration % Complete | Physical % Complete | Units % Complete | Schedule % Complete | Performance % Complete | Actual Total Cost | Earned Value Cost | Planned Value Cost | Actual Labor Units | Earned Value Labor Units | Planned Value Labor Units | Original Duration | Start | Finish | BL Project Start | BL Project Finish | Budgeted Total Cost | Budgeted Labor Units | Remaining Duration | Actual Nonlabor Units | Remaining Nonlabor Units | Variance - BL Project Nonlabor Units | Variance - BL Project Labor Cost | Schedule Performance Index | Total Float | % Variance
Moblization |  |  |  | 100% |  | 100% | 0% | 0% | 0 | 0 | 0 | 12658.6 | 12658.6 | 12658.6 | 63 | 26-Mar-26 A | 10-Jun-26 A | 2026-03-26 | 2026-06-10 | 0 | 12658.6 | 0 | 0 | 0 | 0 | 0 | 0 |  | -405
Engineering |  |  |  | 76.28% |  | 98.26% | 0% | 0% | 0 | 0 | 0 | 20929.2 | 20929.2 | 21299.5 | 215 | 31-Mar-26 A | 2026-12-10 | 2026-03-31 | 2026-09-02 | 0 | 21299.5 | 51 | 0 | 0 | 0 | 0 | 0 | 39 | -43720
Procurment |  |  |  | 57.54% |  | 52.41% | 0% | 0% | 0 | 0 | 0 | 26870.4 | 26870.4 | 50435.59 | 252 | 06-May-26 A | 2027-02-14 | 2026-05-06 | 2026-12-07 | 0 | 51273.3 | 107 | 0 | 0 | 0 | 0 | 0 | -43 | -6715.38
Construction |  |  |  | 45.83% |  | 29.59% | 34.25% | 32.96% | 7472734.75 | 11137727.29 | 11574034.12 | 85000 | 97952 | 106418.26 | 312 | 25-Apr-26 A | 2027-05-02 | 2026-04-25 | 2027-01-25 | 33793604.34 | 299659.7 | 169 | 16420 | 26680 | 0 | 0 | 0.96 | -79 | -2645.55
Jazan Region |  |  |  | 44.77% |  | 16.83% | 33.24% | 23.12% | 1364443.66 | 2469126.02 | 3550245.27 | 16500 | 20350 | 40380.05 | 306 | 02-May-26 A | 2027-05-02 | 2026-05-02 | 2027-01-25 | 10680071.52 | 102279.9 | 169 | 3210 | 11620 | 0 | 0 | 0.7 | -79 | -959.18
Asir Region |  |  |  | 49.3% |  | 36.22% | 23.12% | 35.44% | 2696845.87 | 3748970.85 | 2445845.81 | 33350 | 38422 | 33248.69 | 286 | 27-Apr-26 A | 2027-04-04 | 2026-04-27 | 2027-01-24 | 10578073.08 | 96809.9 | 145 | 6740 | 7130 | 0 | 0 | 1.53 | -55 | -858.18
Jeddah Region |  |  |  | 49.31% |  | 36.2% | 44.5% | 39.25% | 3411445.22 | 4919630.42 | 5577943.03 | 35150 | 39180 | 32789.52 | 290 | 25-Apr-26 A | 2027-04-06 | 2026-04-25 | 2027-01-25 | 12535459.74 | 100569.9 | 147 | 6470 | 7930 | 0 | 0 | 0.88 | -57 | -828.18
Testing & Commissioning |  |  |  | 0% |  | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 2026-12-13 | 2027-04-07 | 2026-11-05 | 2027-01-19 | 0 | 12818.4 | 96 | 0 | 0 | 0 | 0 | 0 | -63 | 0
Close-Out |  |  |  | 0% |  | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 2027-03-27 | 2027-04-19 | 2027-01-14 | 2027-01-25 | 0 | 8545.6 | 21 | 0 | 360 | 0 | 0 | 0 | -68 | 0
No WBS-Project |  |  |  | 49.85% |  | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 337 | 26-Mar-26 A | 2027-05-02 | 2026-03-26 | 2027-01-25 | 0 | 0 | 169 | 0 | 0 | 0 | 0 | 0 | -79 | -200

## EV-Chart Data
| Baseline Plan |  |  | Revised / Recovery Plan |  |  | Earned Value |  |  | Gross Paid Value |  |  | Forecast |  | Actual/Fcst vs Plan
Month | Monthly | Cum | % | Monthly | Cum | % | Monthly | Cum | % | Monthly | Cum | % | Monthly | C um | Month | Cum |  |  |  | Done
2026-03-15 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% |  |  | 0 | 0 | Actuals thru previous month
2026-04-15 | 199694.67 | 199694.67 | 0.5874% | 205818.85 | 205818.85 | 0.609% | 205818.85 | 205818.85 | 0.609% | 0 | 0 | 0% |  |  | 0 | 0
2026-05-15 | 1723647.94 | 1923342.61 | 5.657% | 1267322.64 | 1473141.49 | 4.359% | 1252747.08 | 1458565.93 | 4.316% | 0 | 0 | 0% |  |  | -14575.56 | -14575.56 |  |  | 85712.66
2026-06-15 | 2762137.78 | 4685480.39 | 13.78% | 896200.52 | 2369342.01 | 7.011% | 910089.8 | 2368655.73 | 7.009% | 634329.39 | 634329.39 | 1.866% |  |  | 13889.28 | -686.28 |  |  | 1597179.44
2026-07-15 | 5604940.17 | 10290420.56 | 30.27% | 1308159.86 | 3677501.87 | 10.88% | 1106584.36 | 3475240.09 | 10.28% | 887817 | 1522146.39 | 4.477% |  |  | -201575.5 | -202261.78 | Forecast current and future months |  | 2973246.08
2026-08-15 | 6742263.27 | 17032683.83 | 50.1% | 924766.73 | 4602268.6 | 13.62% | 2749566.23 | 6224806.32 | 18.42% | [5 empty] | 1824799.5 | 1622537.72 |  |  | 4807121.98
2026-09-15 | 5043935.1 | 22076618.93 | 64.94% | 5023017.74 | 9625286.34 | 28.48% | 2886879.07 | 9111685.39 | 26.96% | [5 empty] | -2136138.67 | -513600.95 |  |  | 5879972.09
2026-10-15 | 4651952.77 | 26728571.7 | 78.62% | 6221852.58 | 15847138.92 | 46.89% | 2026041.61 | 11137727 | 32.96% | [5 empty] | -4195810.97 | -4709411.92 |  |  | 5517468.45
2026-11-15 | 3823943.18 | 30552514.88 | 89.87% | 7294516.72 | 23141655.64 | 68.48% | [8 empty] | -7294516.72 | -12003928.64 |  |  | 4787653.55
2026-12-15 | 2333735.31 | 32886250.19 | 96.73% | 8882697.83 | 32024353.47 | 94.76% | [8 empty] | -8882697.83 | -20886626.47 |  |  | 4115781.26
2027-01-15 | 1111536.82 | 33997787.01 | 100% | 1769250.87 | 33793604.34 | 100% | [8 empty] | -1769250.87 | -22655877.34 |  |  | 2188790.53
2027-02-15 | [14 empty] | 0 | -22655877.34 |  |  | 1764236.48
[19 empty] | 2138770.66 | 5614010.75 | 0.16613
[19 empty] | 2749566.23 | 6224806.32 | 0.1842
[19 empty] | 212768.9 | 6437575.22 | 0.1905
[19 empty] | 1149500.24 | 7374306.56 | 0.21822
[19 empty] | 2886879.07 | 9111685.39 | 0.26963
[19 empty] | 1299287.95 | 10410973.34 | 0.30808
Extended Duration
UPDATE ONLY YELLOW PORTION FROM PRIMAVERA EXPORT, IF NEEDED, EXTEND YELLOW PORTION BASED ON SCHEDULE.
Spreadsheet Field | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01
Earned Value Cost | 2026-04-01: 205818.85; 2026-05-01: 1252747.08; 2026-06-01: 910089.8; 2026-07-01: 1106584.36; 2026-08-01: 300732.48
Planned Value Cost |  | 205818.85 | 1267322.64 | 896200.52 | 1308159.86 | 924766.73 | 5023017.74 | 6221852.58 | 7294516.72 | 8882697.83 | 1769250.86
Remaining Total Cost | 2026-08-01: 2565414.68; 2026-09-01: 2407360.37; 2026-10-01: 5270138.99; 2026-11-01: 4429466.49; 2026-12-01: 9838447.69; 2027-01-01: 5002146.69; 2027-02-01: 504657.34
Budgeted Total Cost |  | 205818.85 | 1267322.64 | 896200.52 | 542878.66 | 2830241.47 | 2950222.49 | 5326201.49 | 4429466.49 | 9838447.69 | 5002146.69 | 504657.34
Actual Labor Units | 2026-03-01: 1526; 2026-04-01: 18717; 2026-05-01: 22356; 2026-06-01: 27882; 2026-07-01: 21077; 2026-08-01: 1966
Remaining Labor Units | 2026-08-01: 38935; 2026-09-01: 28718; 2026-10-01: 54537; 2026-11-01: 47465; 2026-12-01: 63925; 2027-01-01: 57143; 2027-02-01: 22009
Budgeted Labor Units | 1526 | 18717 | 22356 | 27882 | 14212 | 46384 | 30044 | 54593 | 47465 | 63925 | 57143 | 22009
Earned Value Cost
Planned Value Cost
Remaining Total Cost
Budgeted Total Cost
Actual Labor Units | 2026-03-01: 1377; 2026-04-01: 7487; 2026-05-01: 3417; 2026-06-01: 378
Remaining Labor Units
Budgeted Labor Units | 2026-03-01: 1377; 2026-04-01: 7487; 2026-05-01: 3417; 2026-06-01: 378

## Physical-Chart Data
| Baseline Plan |  |  | Revised / Recovery Plan |  |  | Earned Effort % |  |  | Forecast |  |  | Achieved/Fcst vs Plan
Week | Monthly Effort | Cum Effort | Plan Wt.% | MonthlyEffort | Cum Effort | Plan Wt.% | Monthly Wt. | Cum Wt. | Achieved Wt.% | Monthly Wt. | Cum Wt. | Wt.% | Monthly Wt. | Cum Wt.
2026-03-15 | 2126 | 2126 | 0.4978% | 1526 | 1526 | 0.3756% | 1526 | 1526 | 0.3756% |  |  |  | 0 | 0 | Actuals thru previous month
2026-04-15 | 38413 | 40539 | 9.491% | 18717 | 20243 | 4.983% | 18717 | 20243 | 4.983% |  |  |  | 0 | 0
2026-05-15 | 30926 | 71465 | 16.73% | 22356 | 42599 | 10.49% | 22356 | 42599 | 10.49% |  |  |  | 0 | 0 |  |  |  |  | Done
2026-06-15 | 60339 | 131804 | 30.86% | 27882 | 70481 | 17.35% | 27882 | 70481 | 17.35% |  |  |  | 0 | 0
2026-07-15 | 50656 | 182460 | 42.72% | 36166 | 106647 | 26.25% | 21077 | 91558 | 22.54% |  |  |  | -15089 | -15089 | Forecast current and future months
2026-08-15 | 39250 | 221710 | 51.91% | 28032 | 134679 | 33.15% | 38316 | 129874 | 31.97% |  |  |  | 10284 | -4805
2026-09-15 | 48023 | 269733 | 63.15% | 34666 | 169345 | 41.68% | 13807 | 143681 | 35.37% |  |  |  | -20859 | -25664
2026-10-15 | 51145 | 320878 | 75.13% | 65304 | 234649 | 57.76% | 14729.2 | 158410.2 | 38.99% |  |  |  | -50574.8 | -76238.8
2026-11-15 | 41901 | 362779 | 84.94% | 53879 | 288528 | 71.02% | [6 empty] | -53879 | -130117.8 |  |  | 37220 | 128778 | 0.31699
2026-12-15 | 39788 | 402567 | 94.25% | 77888 | 366416 | 90.19% | [6 empty] | -77888 | -208005.8 |  |  | 461 | 144781 | 0.35638
2027-01-15 | 24553 | 427120 | 100% | 39839 | 406255 | 100% | [6 empty] | -39839 | -247844.8 |  |  | 13807 | 143681 | 0.35367
2027-02-15 | [12 empty] | 0 | -247844.8 |  |  | 7812 | 151493 | 0.3729
2027-03-15
2027-04-15
Extended Duration
UPDATE ONLY YELLOW PORTION FROM PRIMAVERA EXPORT, IF NEEDED, EXTEND YELLOW PORTION BASED ON SCHEDULE.

## Weekly Photos
|  | Data Date | 2026-10-12
Ceramics works in toilet / services building Jazan | Backfilling & compaction for bike / walk path Jazan
celling works / services building (Jeddah) | backfilling & laying for lighting poles cables & foundation (Jeddah)
Compaction for interlock work ASIR | Steel Fixing for Air Dome Entrance Raft ASIR

## Procurement
[10 empty] | Plan | [5 empty] | Plan | Forcast | Actual
Sr. NO. | Project ID | ACT#inP6 | Item Description | Discipline | (Long \Short) Lead Items | BOQ. No. | Unit | Quantity | Proc. Qty | Required P.O Date | Date of Pur. Order Issued | Purchase Order No. | Supplier | Supplier Phone | Method of Shipping | Required on Job | E.D.A. to Site | A.D.A. to Site | Lead Time | Approval Status | Completion Rate | The Impact (BOQ Cost) | Remarks
1 | MLTX-02-004 | ______________ | AAC panels | Architectural | Long Lead | 3.4 | m² | 680.43 | 748.473 |  | 2026-04-27 | HQ01-PO-26-0015 | ESPAC | 592880434 | Local | 2026-04-20 |  |  | Long Lead | Approved |  |  | Delivered Of Site |  |  | 1
2 | MLTX-02-004 | _____________ | Structural Glass | Architectural | short Lead | 8.2.1 | Sets | 3 | 3 |  | 2026-04-28 | HQ01-PO-26-0221 | Dreametal | 538882626 | Local | 2026-07-05 |  |  | short Lead | Approved |  |  | PO Issued |  |  | 1
3 | MLTX-02-004 | _____________ | Frosted glass partition + door ( 12 mm thk. ) | Architectural | short Lead | 9.2.9 | m² | 18.72 | 20.592 |  | 2026-04-28 | HQ01-PO-26-0221 | Dreametal | 538882626 | Local | 2026-07-05 |  |  | short Lead | Approved |  |  | PO Issued |  |  | 1
4 | MLTX-02-004 | _____________ | CNC aluminum cladding plates ( 3mm thk. ) | Architectural | short Lead | 9.2.7 | item | 1 | 1 |  | 2026-04-28 | HQ01-PO-26-0221 | Dreametal | 538882626 | Local | 2026-07-05 |  |  | short Lead | Approved |  |  | PO Issued |  |  | 1
5 | MLTX-02-004 | _____________ | Anti slip ceramic ( floor 60*60 & 30*30 ) | Architectural | short Lead | 9.1.1.1 9.1.1.2 | m² | 178.77 | 196.647 |  | 2026-04-19 | PR. 4 | Saudi Ceramics | +966 2 001 1124 | Local | 2026-06-29 |  |  | short Lead | [6 empty] | 1
6 | MLTX-02-004 | _____________ | Anti slip ceramic ( wall 30*30 ) | Architectural | short Lead | 9.2.1 | m² | 355.68 | 391.248 |  | 2026-04-19 | PR. 4 | Saudi Ceramics | +966 2 001 1124 | Local | 2026-06-29 |  |  | short Lead | [6 empty] | 1
7 | MLTX-02-004 | _____________ | Anti slip ceramic ( skirting 60*100*10 ) | Architectural | short Lead | 9.1.2.1 | L.M | 27.72 | 30.492 |  | 2026-04-19 | PR. 4 | Saudi Ceramics | +966 2 001 1124 | Local | 2026-06-29 |  |  | short Lead | [6 empty] | 1
8 | MLTX-02-004 | _____________ | Artificial Marble (Corian) | Architectural | short Lead | 15.3.8.5 | Nos. | 3 | 3.3 |  |  |  | AFIFI |  | Local | 2026-06-29 |  |  | short Lead |  |  |  |  | Delay |  | 1
9 | MLTX-02-004 | _____________ | Granite ( floor , treshold , coping ) | Architectural | short Lead | 9.1.1.3 9.2.10 | m² | 121.8 | 133.98 |  | 2026-04-19 | PR. 4 | Saudi Ceramics | +966 2 001 1124 | Local | 2026-06-29 |  |  | short Lead | [6 empty] | 1
10 | MLTX-02-004 | _____________ | Acrylic paint (walls , ceilings , elevations) | Architectural | short Lead | 9.2.3 9.2.4 9.3.3 | m² | 685 | 753.5 |  | 2026-04-16 | PR. 2 | Jazeera Paints | +966 2 000 0085 | Local | 2026-07-12 |  |  | short Lead | Approved |  |  | PO Issued |  |  | 1
11 | MLTX-02-004 | _____________ | Decorative profile paint | Architectural | short Lead | 9.2.6 | item | 3 | 3 |  | 2026-04-16 | PR. 2 | Jazeera Paints | +966 2 000 0085 | Local | 2026-07-12 |  |  | short Lead | Approved |  |  | PO Issued |  |  | 1
12 | MLTX-02-004 | _____________ | Epoxy paint { (sport flooring (pike & walking paths )} | Architectural | short Lead | 9.1.1.4 | m² | 16.56 | 18.216 |  | 2026-05-10 | HQ01-SCC-CND-0027 | First Roshin | 966539293693 | Local | 2026-07-12 |  |  | short Lead | Approved |  |  | PO Issued |  |  | 1
13 | MLTX-02-004 | _____________ | Stone cladding 300*600 | Architectural | short Lead | 9.2.5 | m² | 140 | 168 | [5 empty] | Local | 2026-07-25 |  |  | short Lead |  |  |  |  | Delay |  | 1
14 | MLTX-02-004 | Suspend Ceiling | Gypsum board ( RG. & MR. ) 12.5 LL THK. | Architectural | short Lead | 9.3.1 9.3.2 | m² | 164.4 | 180.84 |  | 2026-04-15 | PR. 1 | MADA | +966 4 325 2411 | Local | 2026-07-12 |  |  | short Lead | [6 empty] | 1
15 | MLTX-02-004 | _____________ | PHENOLIC TOILETS PARTITION & PHENOLIC LOCKER | Architectural | short Lead | 9.2.8 10.1.2.1 10.1.2.2 | m² | 120.96 + 3 Item | 139.104 + 3Item |  | 10-May-26 | HQ01-SCC-CND-0030 | Perfect Doors | 550840114 | Local | 2026-06-29 |  |  | short Lead | [5 empty] | تحويل عتد م.اسلام عبدالسميع | 1
16 | MLTX-02-004 | Grass/Trees | Trees (Cassia Glauca+Plumeria Alba+Neem) | Architectural | Long Lead | 2.3.4.1 | Nos. | 850 | 850 |  | 17-May-26 | HQ01-SCC-CND-26-0027 | Sana Al-Andalus | +966 56 006 6003 | Local | 2026-09-18 |  |  | Long Lead | [6 empty] | 1
17 | MLTX-02-004 | _____________ | Ground Covers -Lawn | Architectural | short Lead | 2.3.4.2.1 | m2 | 13600 | 14000 |  | 17-May-26 | HQ01-SCC-CND-26-0027 | Sana Al-Andalus | +966 56 006 6003 | Local | 2026-06-07 |  |  | short Lead | [6 empty] | 1
18 | MLTX-02-004 | Padel Glass | padel playground fence - Glass | Architectural | Long Lead | 2.3.7 | Item | 3 | 3 |  | 2026-05-10 | HQ01-SCC-CND-0027 | First Roshin | 966539293693 | Local | 2026-05-08 |  |  | Long Lead | Approved |  |  | PO Issued |  |  | 1
19 | MLTX-02-004 | _________________ | Damproofinig paint | Architectural | Short Lead | 7.3 | m² | 146.7 | 150 |  | 2026-04-30 | PR.15 | Awazel | +966 2 660 1740 | Local | 2026-05-25 |  |  | Short Lead |  |  |  | PO Issued |  |  | 1
20 | MLTX-02-004 | _________________ | 4mm thick layer APP modified bituminous membrane | Architectural | Short Lead | 7.5 | m² | 236.16 | 300 |  | 2026-04-30 | PR.15 | Awazel | +966 2 660 1740 | Local | 2026-05-12 |  |  | Short Lead | Approved | 30% |  | Delivered Of Site |  |  | 1
21 | MLTX-02-004 | _____________ | Geotextile sheet | Architectural | Short Lead | _______ | _____ | _____ | _____ |  | 2026-04-30 | PR.15 | Awazel | +966 2 660 1740 | Local | 2026-05-12 |  |  | Short Lead |  |  |  | Delivered Of Site |  | تحويل عتد م.اسلام عبدالسميع | 1
22 | MLTX-02-004 | _____________ | 50 mm thk rigid insulation (extruded polystyrene XPS) Density 35 kg/m3 | Architectural | Short Lead | 7.4.4 | m² | 211.41 | 232.551 |  | 2026-04-30 | PR.15 | Awazel | +966 2 660 1740 | Local | 2026-05-12 |  |  | Short Lead |  |  |  | PO Issued |  |  | 1
23 | MLTX-02-004 | _____________ | Water proofing system | Architectural | Short Lead | 7.4.1 7.4.2 7.4.5 7.4.6 | m² | 211.41 | 232.551 |  | 2026-04-30 | PR.15 | Awazel | +966 2 660 1740 | Local | 2026-05-12 |  |  | Short Lead |  |  |  | Delivered Of Site |  | تحويل عتد م.اسلام عبدالسميع | 1
24 | MLTX-02-004 | _____________ | epoxy 2 coating | Architectural | Short Lead | 7.6 | m² | 172 | 200 |  | 2026-04-30 | PR.15 | Awazel | +966 2 660 1740 | Local | 2026-05-12 |  |  | Short Lead |  |  |  | Delivered Of Site |  | تحويل عتد م.اسلام عبدالسميع | 1
25 | MLTX-02-004 | _____________ | Precast conc. Seats ( rect. & circle ) | Architectural | Long Lead | 2.3.10.1 2.3.10.2 2.3.10.3 | Nos. | 201 | 241.2 |  | 2026-04-23 | PR.8 | Al-Hasaniah |  | Local | 2026-07-03 |  |  | Long Lead |  |  |  | PO Issued |  | تحويل عتد م.اسلام عبدالسميع | 1
26 | MLTX-02-004 | _____________ | Precast connc. Trash pin | Architectural | Long Lead | 2.3.10.4 | Nos. | 38 | 38 |  | 2026-04-23 | PR.8 | Al-Hasaniah |  | Local | 2026-07-03 |  |  | Long Lead |  |  |  | PO Issued |  | تحويل عتد م.اسلام عبدالسميع | 1
27 | MLTX-02-004 | _____________ | Air dome ( Full system )2 | Architectural | Long Lead | 2.3.9 | Item | 3 | 3 |  |  |  | Global Sport Gate | 551707700 | Local | 2026-06-23 |  |  | Long Lead |  |  |  |  | Delay | تحويل عتد م.اسلام عبدالسميع | 1
28 | MLTX-02-004 | Interlocking Block Pavers | Curbstone & Interlock -01 | Architectural | Short Lead | 2.2.1 2.3.1.1 2.3.2 | m² L.M | 1994.57 17350.00 | 2194 19085 |  | 29-4-2026 | HQ01-PO-26-010 | 33564116.5 | 598283830 | Local | 2026-07-02 |  |  | Short Lead | Approved |  |  | PO Issued |  | تحويل عتد م.اسلام عبدالسميع | 1
29 | MLTX-02-004 | Interlocking Block Pavers | Curbstone & Interlock -02 | Architectural | Short Lead | 2.2.1 2.3.1.1 2.3.2 | m² L.M | 1994.57 17350.00 | 2194 19085 |  | 22-4-2026 | HQ01-PO-CND-9-26-04-20 | AL_taj | 555103330 | Local | 2026-07-02 |  |  | Short Lead | Approved |  |  | PO Issued |  |  | 1
30 | MLTX-02-004 | Interlocking Block Pavers | Curbstone & Interlock -03 | Architectural | Short Lead | 2.2.1 2.3.1.1 2.3.2 | m² L.M | 1994.57 17350.00 | 2194 19085 |  | 22-4-2026 | HQ01-PO-CND-11-26-04-20 | Bin OTOT | 507738308 | Local | 2026-06-14 |  |  | Short Lead | Approved |  |  | PO Issued |  |  | 1
31 | MLTX-02-004 | _____________ | galvanized block ladder mesh | Civil | Short Lead | 4.1.1 | Item | 3 | 3 |  | 2026-05-02 | PR. 19 | Unitech | +966 2 627 8222 | Local | 2026-04-29 |  |  | Short Lead | [6 empty] | 1
32 | MLTX-02-004 | _____________ | galvanized block angle | Civil | Short Lead | 4.1.1 | Item | 3 | 3 |  | 2026-05-02 | PR. 19 | Unitech | +966 2 627 8222 | Local | 2026-04-29 |  |  | Short Lead | [6 empty] | 1
33 | MLTX-02-004 | _____________ | Plastering Accessories | Civil | Short Lead | 9.2.2 | Item | 3 | 3 |  | 2026-05-02 | PR. 19 | Unitech | +966 2 627 8222 | Local | 2026-04-29 |  |  | Short Lead | [6 empty] | 1
34 | MLTX-02-004 | _____________ | Metal doors | Civil | Short Lead | 8 | Nos. | 3 | 3 |  |  |  | Anfal | 545969350 | Local | 2026-05-31 |  |  | Short Lead |  |  |  |  | Delay |  | 1
35 | MLTX-02-004 | Aggregate Base Course | CRUSHERS ( backfilling materials )1 | Civil | short Lead | 2.1.2 | m³ | 3068.6667 | 3375.5333 |  | 26-4-2026 | HQ01-PO-26-001 | Alazm uniited company |  | Local | 2026-05-31 |  |  | short Lead | Approved |  |  | Delivered Of Site |  |  | 1
36 | MLTX-02-004 | Aggregate Base Course | CRUSHERS ( backfilling materials )2 | Civil | short Lead | 2.1.2 | m³ | 3068.6667 | 3375.5333 |  | 22-4-2026 | HQ7-PO01-26-04-20 | EEAC |  | Local | 2026-05-31 |  |  | short Lead | Approved |  |  | Delivered Of Site |  |  | 1
37 | MLTX-02-004 | Aggregate Base Course | CRUSHERS ( backfilling materials )3 | Civil | short Lead | 2.1.2 | m³ | 3068.6667 | 3375.5333 |  | 22-4-2026 | HQ10-26-04-20CND-PO01- | Star Towers Contracting Company |  | Local | 2026-05-31 |  |  | short Lead | Approved |  |  | Delivered Of Site |  |  | 1
38 | MLTX-02-004 | _____________ | polyethylene sheet | Civil | Short Lead | 7.1 7.4.3 | m² | 499.29 | 500 |  | 29-4-2026 | PR. 14 | Unitech | +966 2 627 8222 | Local | 2026-07-12 | 2026-06-02 | 2026-06-02 | Short Lead | Approved | 100% |  | Delivered Of Site |  | تحويل عند م اسلام عبدالسميع | 1
39 | MLTX-02-004 | _____________ | Anti termite | Civil | Short Lead | 7.2 | m² | 287.88 | 300 |  | 27-4-2026 | PR.12 | Trap kill | +966 56 657 7862 | Local | 2026-05-15 | 2026-06-03 | 2026-06-03 | Short Lead | Approved | 30% |  | Delivered Ongoing |  |  | 1
40 | MLTX-02-004 | Concrete Blocks | 01- Concrete & Masonry block for walls 10 cm | Civil | Short Lead | 3 4.1.1 | m3 m² | 843.37 176.53 | 900 180 |  | 19-4-2026 | HQ01-PO-CND 4 -26-04-18 | Rhino | 597224822 | Local | 2026-04-23 |  |  | Short Lead | Approved |  |  | PO Issued |  |  | 1
41 | MLTX-02-004 | Concrete Blocks | 02 -Concrete & Masonry block for walls 10 cm | Civil | Short Lead | 3 4.1.1 | m3 m² | 843.37 176.53 | 900 180 |  | 22-4-2026 | HQ01-PO-CND-9-26-04-20 | Al Taj | 555103330 | Local | 2026-04-23 |  |  | Short Lead | Approved |  |  | Delivered Ongoing |  |  | 1
42 | MLTX-02-004 | Concrete Blocks | 03- Concrete & Masonry block for walls 10 cm | Civil | Short Lead | 3 4.1.1 | m3 m² | 843.37 176.53 | 900 180 |  | 24-4-2026 | HQ01-PO-CND-11-26-04-20 | Bin OTOT | 507738308 | Local | 2026-04-23 |  |  | Short Lead | Approved |  |  | Delivered Ongoing |  |  | 1
43 | MLTX-02-004 | Steel Reincement | Reinforcement Steel 1 | Civil | Short Lead | 43.5 | Ton | 30 | 22.5 |  | 2026-04-20 | PR.5 | ALRAJHI | 542264279 | Local | 2026-05-12 | 25-05-2026 | 25-05-2026 | Short Lead | Approved | 75% |  | Delivered Ongoing |  |  | 1
44 | MLTX-02-004 | Steel Reincement | Reinforcement Steel 2 | Civil | Short Lead | 43.5 | Ton | __ | __ |  |  |  | AL-ITTEFAQ |  | Local | 2026-05-12 |  |  | Short Lead |  |  |  |  | Delay |  | 1
45 | MLTX-02-004 | Pavement Markings | Road markings | Civil | Short Lead | 2.2.5 | Lot | 3 |  |  |  |  | SHAWAHID | 541767351 | Local | 2026-06-21 |  |  | Short Lead | [6 empty] | 1
46 | MLTX-02-004 | Traffic Signs | Aluminum traffic breakaway signs | Civil | Short Lead | 2.3.3.1 | Nos. | 6 |  |  |  |  | SHAWAHID | 541767351 | Local | 2026-09-24 |  |  | Short Lead | [6 empty] | 1
47 | MLTX-02-004 | Track Surface Artificial TURF | Tartan floors system (EPDM Granules + Polyurethane ) & Playground Flooring & Asphalt | Civil | Short Lead | 2.3.1.2 2.3.1.3 2.3.1.5 2.3.1.6 2.3.5 | m2 | 11874.26 |  |  | 2026-05-10 | HQ01-SCC-CND-0027 | First Roshin | 966539293693 | Local | 2026-06-07 |  |  | Short Lead | Approved |  |  | PO Issued |  |  | 1
48 | MLTX-02-004 | _____________ | Steel ladder with safety cage | Civil | Short Lead | 5.1 | Nos. | 3 |  |  |  |  | Judff |  | Local | 2026-07-31 |  |  | Short Lead | [6 empty] | 1
49 | MLTX-02-004 |  | Low Voltage Cable -Wiring | Electrical | Long Lead | 16.9 | _____ | _____ |  |  |  |  | Bahra Electric | 920011127 | Local |  |  |  | Long Lead | [6 empty] | 1
50 | MLTX-02-004 | Cables - Landscape | Low Voltage Cable -600/1000volt | Electrical | Long Lead | _______ | _____ | _____ |  |  |  |  | Jeddah Cable Company | +966 055 289 3405 | Local | 2026-07-31 |  |  | Long Lead | [6 empty] | 1
51 | MLTX-02-004 | _____________ | BACK & JUNCTION BOXES | Electrical | Short Lead | _______ | _____ | _____ | _____ |  | 24-05-2026 | PO-Ele-01 | ALFANAR | 800-124-1333 | Local | 2026-07-01 | 2026-06-08 | 2026-06-08 | Short Lead | Approved | 40% |  | Delivered Ongoing |  |  | 1
52 | MLTX-02-004 | _____________ | CONDUITS & FITTINGS & Accessories for PVC | Electrical | Short Lead | _______ | _____ | _____ |  |  | 24-05-2026 | PR-Ele-01 | Khereiji Showrooms Company (MK ) | +966 56 686 6706 | Local | 2026-07-01 | 2026-06-08 | 2026-06-21 | Short Lead | Approved | 10% |  | Delivered Ongoing |  |  | 1
53 | MLTX-02-004 | _____________ | EMT/RSC CONDUITS – LIQUDTIGHT FLEXIBLE CONDUIT- METAL FLEXIBLE CONDUIT | Electrical | Short Lead | _______ | _____ | _____ |  |  | 24-05-2026 | PO-Ele-01 | ITCC | +966 12 288 9198 | Local | 2026-07-01 | 2026-06-08 | 2026-06-08 | Short Lead | Approved | 10% |  | Delivered Ongoing |  |  | 1
54 | MLTX-02-004 | Earthing System | GROUNDING/ LIGHTNING PROTECTION SYSTEM | Electrical | Short Lead | 16.6 16.7 | Nos. | 12 | 6 |  | 24-05-2026 | PO-Ele-01 | Jeddah Cable Company | +966 56 686 6706 | Local | 2026-05-12 | 2026-06-08 | 2026-06-08 | Short Lead | Approved | 25% |  | Delivered Ongoing |  |  | 1
55 | MLTX-02-004 | Switches/Sockets - Toilet wer Outlets/Switches - Playground | WIRING DEVICES | Electrical | Short Lead | 16.9 | Nos. | 66 |  |  |  |  | Khereiji Showrooms Company (MK) | +966 56 686 6706 | Local |  |  |  | Short Lead |  |  |  |  | Delay |  | 1
56 | MLTX-02-004 | ____________ | Disconnect switch | Electrical | Short Lead | 16.9.10 | Nos. | 3 |  |  |  |  | ABB | +966 92 001 0301 | Local | 2026-07-31 |  |  | Short Lead |  |  |  |  | Delay | Material Submite 2-10-2025 | 1
57 | MLTX-02-004 | Distribution Panels - Toilet Distribution Boards - Playground | LV PANEL BOARDS | Electrical | Short Lead | 16.1 | Nos. | 8 |  |  |  |  | Al-Babtain Power | +966 11 250 6900 | Local |  |  |  | Short Lead |  |  |  |  | Delay | Material Submite 2-10-2025 | 1
58 | MLTX-02-004 | Light Fixtures - playground | Roadway/ street lights – Lighting Poles | Electrical | Short Lead | 16.2 | Nos. | 322 | 322 |  | 2026-06-03 | PO2026-283 | Al-Babtain Power | +966 11 250 6900 | Local | 2026-07-07 |  |  | Short Lead |  |  |  | Delivered Of Site |  |  | 1
59 | MLTX-02-004 | Lighting Fixtures- toilet | Interior Lighting | Electrical | Short Lead | 16.3 | Nos. | 144 |  |  |  |  | Nassli led Lights | +966 59 406 6470 | Local | 2026-06-25 |  |  | Short Lead |  |  |  |  | Delay |  | 1
60 | MLTX-02-004 | _____________ | Fire Alarm System | Electrical | Short Lead | 16.8 | Nos. | 45 |  |  |  |  | Gent | 966112650555 | Local | 2026-08-20 |  |  | Short Lead |  |  |  |  | Delay |  | 1
61 | MLTX-02-004 | _____________ | Telecommunications & Data System | Electrical | Short Lead | 16.4 | Nos. | 27 |  |  |  |  | Mesc | 96611434711 | Local | 2026-08-20 |  |  | Short Lead |  |  |  |  | Delay |  | 1
62 | MLTX-02-004 | CCTV | Security and Access Control System - CCTV | Electrical | Short Lead | 16.5 | Nos. | 42 | [6 empty] | Local | 2026-07-12 |  |  | Short Lead |  |  |  |  | Delay |  | 1
63 | MLTX-02-004 | Sewage/Drainage Pipes | UPVC Pipes | Mechanical | Short Lead | 15.3.1 15.3.7 | Lm | 454 | 460 |  | 21-05-2026 | PR 26 | AL MUNIF | +966 2 000 0357 | Local | 2026-04-16 | 2026-06-05 | 2026-06-05 | Short Lead | Approved | 100% |  | Delivered Of Site |  |  | 1
64 | MLTX-02-004 | AC Split - Toilet | Split Type Air Conditioner | Mechanical | Short Lead | 15.4.5 | Nos. | 3 | 3 |  | 2026-04-06 | Profast-PO2026-286 | ZAMIL | +966 2 234 3630 | Local | 2026-06-19 |  |  | Short Lead |  |  |  | PO Issued |  |  | 1
65 | MLTX-02-004 | _____________ | Fire Extinguisher | Mechanical | Short Lead | 15.1 | Nos. | 6 |  |  | 2026-06-28 | PR 31 | SFFECO | +966 12 670 6009 | Local | 2026-08-18 |  |  | Short Lead |  |  |  | PO Issued |  |  | 1
66 | MLTX-02-004 | Sanitary Fixtures | Sanitary Fixtures ( water heater , soap dispenser , tissue holder , mirrors , grap bar , mixer & tissue dispenser , WC , lav. ….. ) | Mechanical | Short Lead | 15.3.3 15.3.4 15.3.8 | Nos. | 3 | 3 |  | 2026-06-07 | PR 26 | Saudi Ceramics | +966 2 001 1124 | Local | 2026-06-13 |  |  | Short Lead |  |  |  | PO Issued |  |  | 1
67 | MLTX-02-004 | Irrigation Pipes/Sprinkles | Land scape & i irrigation system materials (main and sub-main irrigation pipelines, fittings, valve boxes and sprinklers) | Mechanical | Long Lead | 15.4.1.9 15.5.3 | Item | 3 | 3 |  | 17-05-2026 | HQ01-SCC-CND-26-0027 | Sana Al-Andalus | +966 56 006 6003 | Local | 2026-07-31 |  |  | Long Lead |  |  |  | PO Issued |  |  | 1
68 | MLTX-02-004 | Exhaust Fans | Inline Exhaust Fans | Mechanical | Short Lead | 15.4.1 | Nos. | 18 | 20 |  | 18-05-2026 | PR 27 | Saudi Fan | +966 2 283 2295 | Local | 2026-06-19 |  |  | Short Lead |  |  |  | PO Issued |  |  | 1
69 | MLTX-02-004 | _____________ | HDPE PIPES & FITTINGS | Mechanical | Short Lead | 15.2.2 | m | 300 | 300 |  | 28-06-2026 | PR 33 | AL MUNIF | +966 2 000 0357 | Local | 2026-08-18 |  |  | Short Lead |  |  |  | PO Issued |  |  | 1
70 | MLTX-02-004 | Water Supply Pipes | PPR PIPES & FITTINGS | Mechanical | Short Lead | 15.2.1 | Lm | 256.5 | 285 |  | 2026-09-06 | PR 30 | AL MUNIF | +966 2 000 0357 | Local | 2026-06-04 | 13-06-2026 | 13-06-2026 | Short Lead | Approved | 100% |  | Delivered Of Site |  |  | 1
71 | MLTX-02-004 | Exhaust Fans | Square Exhaust Diffuser | Mechanical | Short Lead | 14.4.2.1 | Nos. | 18 |  |  | 2026-06-03 | Profast-PO2026-280 | Rabie Al Takyeef | +966 59 255 5240 | Local | 2026-06-19 |  |  | Short Lead | [6 empty] | 1
72 | MLTX-02-004 | _____________ | Copper Pipe for AC | Mechanical | Short Lead | _______ | Nos. | 3 |  |  |  |  | Al-Sayed Center A/C | +966 2 261 6246 | Local | 2026-06-19 |  |  | Short Lead |  |  |  |  | Delay |  | 1
73 | MLTX-02-004 | _____________ | Copper Pipe Insulation | Mechanical | Short Lead | _______ | Nos. | 3 |  |  |  |  | KIMMCO-ISOVER | +966 3 847 1450 | Local | 2026-06-19 |  |  | Short Lead |  |  |  |  | Delay |  | 1
74 | MLTX-02-004 | _____________ | Valves, check valves strainers and air vent | Mechanical | Long Lead | _______ | Nos. | 43 | 43 |  | 2026-06-30 | PR 37 | ZAMIL | +966 2 234 3630 | Local | 2026-09-18 |  |  | Long Lead |  |  |  | PO Issued |  |  | 1
75 | MLTX-02-004 | _____________ | Afico Insulation | Mechanical | Short Lead | _______ | Nos. | 3 |  |  |  |  | Afico | +966 3 331 3333 | Local | 2026-06-23 |  |  | Short Lead |  |  |  |  | Delay |  | 1
76 | MLTX-02-004 | _____________ | Water Supply Booster Pumps | Mechanical | Long Lead | 15.2.3 | Set | 2 | 2 |  | 17-05-2026 | HQ01-SCC-CND-26-0027 | KSB | +966 1 227 7060 | Local | 2026-08-18 |  |  | Long Lead |  |  |  | PO Issued |  |  | 1
77 | MLTX-02-004 | _____________ | Roof Drain & Steel roof scupper | Mechanical | Short Lead | 5.2 | Nos. | 3 | 3 |  | 4/25/2026 6/28/2026 | PR.10 PR.31 | Saudi Cast | +966 1 448 0107 | Local | 2026-07-31 |  |  | Short Lead |  |  |  | PO Issued |  |  | 1
78 | MLTX-02-004 | _____________ | Hot Press GRP Sectional Panel Water Tanks | Mechanical | Long Lead | 15.2.4.1 | Set | 2 | 2 |  | 2026-07-05 | PROFAST-PO-2026-277 | AL-MUHAIDEB | +966 92 002 8545 | Local | 2026-06-23 |  |  | Long Lead |  |  |  | PO Issued |  |  | 1
79 | MLTX-02-004 | Galvanized Duct | ductwork as per SMACNA Standards | Mechanical | Short Lead | 15.4.3 | K G | 183 |  |  |  |  | Rabie Al Takyeef | +966 59 255 5240 | Local | 2026-06-23 |  |  | Short Lead | [6 empty] | 1
80 | MLTX-02-004 | _____________ | Manhole Cover | Mechanical | Short Lead | 15.3.5 15.3.6 | Nos. | 6 | 6 |  | 2026-06-28 | PR.43 | Judff |  | Local | 2026-08-18 |  |  | Short Lead |  |  |  | PO Issued
Y

## Major Quantities
BOQ Number | Description of Item | Total Quantity | Unit of Measurement | Plan To Date | Actual To Date | Remaining Total | Variance
2.1 | EARTHWORK (Excavation & Backfilling) | 68051.54 | m³ | 57843.809 | 57000 | 11051.54 | -843.809
2.3.1 | Supply and install hardscape works | 30380 | m2 | 0 | 0 | 30380 | 0
2.3.4 | Supply and plant trees | 895 | Nos. | 0 | 0 | 895 | 0
2.3.9 | Design, supply, install, testing and commissioning of air dome | 3 | Item | 0 | 0 | 3 | 0
2.3.10 | Supply and install site furniture | 248 | Nos | 0 | 0 | 248 | 0
3 | Supply and cast Concrete | 145 | m³ | 145 | 145 | 0 | 0
9.1.1 | Supply and install tiles Ceramic tiles | 219 | m² | 0 | 0 | 219 | 0
9.3 | CEILING FINISHES | 207 | m² | 0 | 0 | 207 | 0
15.2.1 | WATER SUPPLY SYSTEM for cold and hot water supply piping | 138 | Lm | 0 | 14 | 124 | 14
15.3.1 | SEWER AND DRAINAGE PIPE | 177 | Lm | 177 | 55 | 122 | -122
15.3.7 | Supply and install 150 mm uPVC pipes | 300 | m | 150 | 50 | 250 | -100
15.5.1 | IRRIGATION SYSTEM HDPE Pipes | 7150 | m | 0 | 0 | 7150 | 0
16.3 | Lighting Fixtures | 129 | Nos. | 0 | 0 | 129 | 0
16.2 | Site Lighting Poles | 322 | Nos. | 0 | 0 | 322 | 0

## Invoice Log
Weekly Progress Report - Invoice Log | [32 empty] | Y
Project Value | [9 empty] | Payment Status | [7 empty] | Invoices Summary | [9 empty] | Average Invoices durations |  |  |  |  | N
Original Contract Value |  |  |  | 33997787 |  | O&M Value |  | 0 |  | Advance Payment % |  | 0% |  | Advance Payment (SAR) |  | 0 |  | No of Submitted Invoices |  | 5 |  | Submitted Invoices (SAR) |  | 4943710.6384 |  | Submiited Invoice Peroid | 2026-10-08 | CM / PgM Average Approval duration |  | 2.5 | Average Invoice Value | 988742.1277
Revised Contract Value |  |  |  | 33793604.34 |  | Revised O&M Value |  | 0 |  | Retention % |  | 0% |  | Retention (SAR) |  | 0 |  | No of Approved Invoices (CM) |  | 47 |  | Approved Invoices (CM) (SAR) |  | 5674267.2341 |  |  |  | MODON PM & Accounts Average Approval duration |  | 0
Estimate At Completion Value |  |  |  | 33997787 |  | Submitted Invoices (Gross Value) |  | 4943710.6384 |  | Penalties and deduction % |  | 0.03236% |  | AP Recovery (SAR) |  | 0 |  | No of Approved Invoices (PM) |  | 0 |  | Approved Invoices (PM) (SAR) |  | 0 |  | Invoice Submitted Compared to Contract Value | 14.63% | Payments Average Duration |  | 0
Potential Changes |  |  |  | -204182.66 |  | Total Deduction |  | 11000 |  | Penalties and deduction (SAR) |  | 11000 |  | Retention Cumulative (SAR) |  | 0 |  | No of Paid Invoices |  | 0 |  | Paid Invoices (SAR) |  | 0 |  |  |  | Invoices Average total Duration
Invoice Reference |  |  |  | Invoice Value |  |  |  |  | Period Covered |  |  | CM / PgM Approval Timeline |  |  |  | Modon PM & Accounts Approval | [6 empty] | Payment Status |  |  |  |  | Total Invoice Duration | Remarks
# | Invoice No. | Doc Control reference | Submittal Rev. # | Gross Value | AP Recovery | Retention | VAT /15% | Deduction / Penalties | Amount (net) | Start Date | End Date | Date to CM / PgM | CM / PgM Approval (Yes/No) | CM / PgM Reply Date | Days Elapsed | Date to PM | PM Approval (Yes/No) | PM Reply Date | Date to Accounts | Accounts Approval (Yes/No) | Accounts Approval Date | Days Elapsed | Date Paid | Amount Paid | Paid % | Payment Period (d) | Amount Pending |  |  |  | Done
1 | 1 | MLTX-02-004-PRO-TS9-1-DSF-GEN-0002-00 | 0 | 634329.39 | 0 | 0 | 95149.4085 | 11000 | 718478.7985 | 2026-03-26 | 2026-06-13 | 2026-06-13 | Y | 2026-06-16 | 3
2 | 2 | MLTX-02-004-PRO-TS9-1-DSF-GEN-0003-00 | 0 | 887817 | 0 | 0 | 133172.55 | 0 | 1020989.55 | 2026-06-14 | 2026-07-04 | 2026-07-04 | Y | 2026-07-05 | 1 | [16 empty] | format if no, make shaded
3 | 3 | MLTX-02-004-PRO-TS9-1-DSF-GEN-0005-01 | 1 | 1120100.03 | 0 | 0 | 168015.0045 | 0 | 1288115.0345 | 2026-07-05 | 2026-08-08 | 2026-08-08 | Y | 2026-08-11 | 3
4 | 4 | MLTX-02-004-PRO-TS9-1-GEN-IPC-0004-00 | 0 | 1024958.7684 | 0 | 0 | 153743.8153 | 0 | 1178702.5836 | 2026-08-09 | 2026-08-24 | 2026-08-24 | Y | 2026-08-27 | 3
5 | 5 | MLTX-02-004-PRO-TS9-1-GEN-IPC-00005-00 | 0 | 1276505.45 | 0 | 0 | 191475.8175 | 0 | 1467981.2675 | 2026-08-25 | 2026-10-08 | 2026-10-08 | Y
6 | [12 empty] | Y
7 | [12 empty] | Y
8 | [12 empty] | Y
9 | [12 empty] | Y
10 | [12 empty] | Y
11 | [12 empty] | Y
12 | [12 empty] | Y
13 | [12 empty] | Y
14 | [12 empty] | Y
15 | [12 empty] | Y
16 | [12 empty] | Y
17 | [12 empty] | Y
18 | [12 empty] | Y
19 | [12 empty] | Y
20 | [12 empty] | Y
21 | [12 empty] | Y
22 | [12 empty] | Y
23 | [12 empty] | Y
24 | [12 empty] | Y
25 | [12 empty] | Y
26 | [12 empty] | Y
27 | [12 empty] | Y
28 | [12 empty] | Y
29 | [12 empty] | Y
30 | [12 empty] | Y
31 | [12 empty] | Y
32 | [12 empty] | Y
33 | [12 empty] | Y
34 | [12 empty] | Y
35 | [12 empty] | Y
36 | [12 empty] | Y
37 | [12 empty] | Y
38 | [12 empty] | Y
39 | [12 empty] | Y
40 | [12 empty] | Y
41 | [12 empty] | Y
42 | [12 empty] | Y
43 | [12 empty] | Y
44 | [12 empty] | Y
45 | [12 empty] | Y
46 | [12 empty] | Y
47 | [12 empty] | Y
48
49
50
|  |  | TOTAL | 4943710.6384 | 0 | 0 |  | 11000 | 5674267.2341 | [14 empty] | 0 |  |  | 0
5493011.8204
0.16255
16.2546
Note on J3: Without O&M Cost

## CCO
CONTRACT CHANGE ORDER (CCO)
CCO No. | Date Added | Description of Change | Status | SR | Sch Impact (Months) | Date Approved | Duration (days)
- | - | - | - | - | - | - | -

## Schedule
Primavera P6 Schedule Status
Project Activities Overview
Schedule Statistics |  |  |  |  | Active Schedule Activities
Total Act. | Not Started | In Progress | Completed | % | Active | Ahead | On | Behind | Flag
2134 | 434 | 20 | 1680 | 78.73% | 20 | 23 | 185 | 226 | -18
Critical Path Activities |  |  | Free Float Management (Total) |  |  |  | Failed Start Activities |  |  | Done
|  |  | Greater Than 14 Days |  | Less Than 14 Days
Last Week | This Week | Diff | Last Week | This Week | Last Week | This Week | Last Week | This Week | Flag
367 | 373 | -6 | 89 | 80 | 387 | 374 | 255 | 266 | -11

## LOOK AHEAD
مستهدف الربع
# | القطاع | المبادرة | Project ID | اسم المشروع | مدير المشروع | المقاول | بداية المشروع | نهاية المشروع التعاقدية | مدة المشروع (أشهر) | نهاية المشروع المتوقعة/ الالتزام | قيمة المشروع | المخطط /الفعلي | Mobilization المخطط | Mobilization المنفذ | Procurement (Long Lead Items) توريد المواد طويلة الأجل (المخطط) | Procurement (Long Lead Items) توريد المواد طويلة الأجل (المنفذ) | Civil Work الأعمال المدنيه (المخطط) | Civil Work الأعمال المدنيه (المنفذ) | Mechnical Work أعمال الميكانيكا (المخطط) | Mechnical Work أعمال الميكانيكا (المنفذ) | Mechnical Work أعمال الكهرباء (المخطط) | Mechnical Work أعمال الكهرباء (المنفذ) | تأثير التأخير (إن وجد) على المبادرات في الربع | نسبة الانجاز المستهدفة بنهاية الربع | نسبة الانجاز المحققة بنهاية الربع | مجموع المبالغ المفوترة المستهدفة بنهاية الربع | مجموع المبالغ المفوترة المحققة بنهاية الربع | نهاية المشروع المتوقعة
1 | الغربي | - | MLTX-02-004 | Playground Initiative for Western Region (Asir - Jazan - Jeddah) | Eng.Yazeed Al Ragabh | Profast Company Ltd. | 2026-03-26 | 2027-01-25 | 10 | 2027-01-25 | 33793604.34 | المخطط=34.25% الفعلى =32.96% | 100% | 100% | 1- 100% Steel Tension Cables 2- 100% Emergency Doors 3- 100% Pressure Units 4- 100% Lock Doors | 1- 0% Steel Tension Cables 2- 0% Emergency Doors 3- 0% Pressure Units 4- 0% Lock Doors | 1- الانتهاء من اعمال القواعد للحمامات 100% 2-الانتهاء من أعمال خرسانات الخزانات الارضية 100% 3-الانتهاء من تركيب جدران واسقف الحمامات 100% 4-الانتهاء من أعمال العزل 100% 5- الانتهاء من أعمال تركيب الابواب والشبابيك 100% | 1- الانتهاء من اعمال القواعد للحمامات 100% 2-الانتهاء من أعمال قواعد الخزانات الارضية 100% 3-الانتهاء من تركيب جدران واسقف الحمامات 100% 4-الانتهاء من أعمال العزل 95% 5- الانتهاء من أعمال تركيب الابواب والشبابيك 10% | 1- الانتهاء من أعمال تمديدات الميكانيك للحمامات 100% | 1- الانتهاء من أعمال تمديدات الميكانيك للحمامات 75% | 1- الانتهاء من تركيبات وحدات الانارة (الحمامات) 100% 2- الانتهاء من تركيب الافياش والمفاتيح (الحمامات) 100% | 1- الانتهاء من تركيبات وحدات الانارة 0% 2- الانتهاء من تركيب الافياش والمفاتيح 50% |  | 45.96% | 32.96% | 15533188 | 5674267.2341 | 2027-01-25

## Conclusion
مبادرة الملاعب للمنطقة الغربية (عسير - جازان - جدة) MLTX-02-004
معلومات المشروع |  |  |  |  | نطاق المشروع |  |  |  |  | موقع المشروع ( جدة - عسير - جازان )
المقاول | شركة البروفاست المحدودة | الاستشاري | شركة ايجيس السعودية للاستشارات |  | البند | الكمية الكلية | الكمية المنفذة | الكمية المتبقية | نسبة المنفذ |  |  |  | Playground Initiative for Western Region (Asir - Jazan - Jeddah)
تاريخ استلام الموقع | 26/03/2026 | مدة التنفيذ | 10 شهرًا ميلاديًا |  | الاعمال الترابية | 100% | 90% | 10% | 90%
بداية العقد | من تاريخ استلام الموقع | قيمة العقد (شامل ضريبة القيمة المضافة) | 33997787 | #REF! | أعمال الخرسانات والبلوك | 100% | 90% | 10% | 90%
نسبة الإنجاز المخطط له | 34.25% | نسبة الإنجاز الفعلي | 32.96% |  | أعمال الملاعب | 100% | 25% | 75% | 25%
ملخص جدول الكميات |  |  |  |  | أعمال مناظر الطبيعية | 100% | 0% | 100% | 0%
مكونات المشروع |  | التكلفة (غير شامل ضريبة القيمة المضافة) | النسبة الاجمالية |  | أعمال توريد الاشجار | 100% | 0% | 100% | 0% |  |  | 39097455.05
الاعمال الترابية |  | 1906125 | 4.875% |  | أعمال القبة الهوائية | 100% | 12% | 88% | 12%
أعمال المواقف |  | 370012.5 | 0.9464% |  | اعمال مواسير الصرف الصحي | 100% | 50% | 50% | 50% |  | 20865877 | 20423520.4076
أعمال المناظر الطبيعية والملاعب |  | 28692664.1625 | 73.39% |  | اعمال مواسير التغذية | 100% | 50% | 50% | 50% |  | 10508920 | 10286130.896
أعمال الخرسانات والبلوك |  | 551991.95 | 1.412% |  | اعمال شبكة مياه الري | 100% | 5% | 95% | 5% |  | 23728460 | 23225416.648
الاعمال المعدنية |  | 47092.5 | 0.1204% |  | وحدات الانارة | 100% | 15% | 85% | 15% |  | 7970089 | 7801123.1132
أعمال نظام العزل |  | 155034.95 | 0.3965% |  | ملخص التوريدات | [5 empty] | 8842925 | 8655454.99
أعمال الابواب والشبابيك |  | 235462.5 | 0.6022% |  | البند | الكمية الكلية | الكمية المورده | الكمية المتبقية | نسبة التوريد
الاعمال الخاصة والتشطيبات |  | 742862.05 | 1.9% |  | الحوائط الخفيفة للحمامات | 753 | 753 | 0 | 100%
الاعمال الميكانيكية |  | 2664969.75 | 6.816% |  | حديد التسليح | 25 | 25 | 0 | 100%
الاعمال الكهربائية |  | 3731239.4 | 9.543% |  | توريد كابلات القبة السماوية | 3 | 0 | 3 | 0% |  |  |  | 5041
معالم البرنامج الزمني |  |  |  |  | توريد الوحدات الصحية للحمامات | 3 | 0.5 | 2.5 | 16.67% |  |  |  | 12075.28
البند |  | التاريخ حسب الجدول الزمني | ملاحظة |  | توريد الخرسانات | 100 | 90 | 10 | 90% |  |  |  | 8502
نهاية الشروع |  | 2026-01-25 |  |  | توريد الانترلوك | 6400 |  | 6400 | 0% |  |  |  | 5775.1
بداية المشروع |  | 2026-03-26 | تم الانتهاء |  | توريد البردورات | 17550 |  | 17550 | 0%
الانتهاء من تجهيزات الموقع. |  | 2026-04-25 | تم الانتهاء | [6 empty] | تقدم أعمال layout
تقديم خطة العمل والبرنامج الزمني |  | 2026-04-23 | تم الانتهاء
تقديم واعتماد المخططات والمواد |  | 2026-07-22 | جاري
الانتهاء من الاعمال الترابية |  | 2026-08-09 | جاري
الانتهاء من أعمال الحمامات |  | 2026-11-30 | جاري |  | التحديات والعوائق
الانتهاء من المناطق الخضراء |  | 2026-12-13 | جاري
الانتهاء من تنفيذ الملاعب |  | 2026-01-16 | جاري
الانتهاء من كامل الأعمال لموقع عسير |  | 2027-01-19 | لم يبدأ
الانتهاء من كامل الأعمال لموقع جازان |  | 2027-01-25 | لم يبدأ
الانتهاء من كامل الأعمال لموقع جدة |  | 2027-01-25 | لم يبدأ
الانتهاء من الاختبار والتشغيل |  | 2027-01-19 | لم يبدأ
1-التصريف السطحي على القناة المفتوحة بالجهة الشرقية بمشروع جدة 2-التصريف السطحي للطريق بالجهة الشرقية بمشروع عسير 3-وجود تربة صخرية أثناء الحفر بموقع عسير 4- تغيير اماكن مواقف انتظار سيارات بموقع جازان 5- اقتراح امكانية رفع منسوب مشروع موقع جدة
موقع المشروع
جدة
جازان
عسير
أعمال الاحلال (جدة , عسير , جازان)

## Issues
[9 empty] | 2026-10-12 | Status | Responsibility
[10 empty] | Open | Contractor
[10 empty] | Closed | Consultant
Modon
Third Party
Other
Issue Log
Issue No | Date Identified | Issue Description | Responsibility | Action Taken | Current Status | Expected/Actual Closure | Duration Elapsed
1 |  | Connection of the project to the drainage channel on the eastern side.(Jeddah) | Contractor | Coordination between the Municipality (City Management) and the infrastructure contractor. | Completed | 2026-05-21 |  | Owner
2 |  | drainage pipe was encountered during site excavation.(Jeddah) | Owner | The required calculations and slope analysis have been completed. | Completed | 2026-05-21 |  | Contractor
3 | 2026-05-05 | Based on the visit by Modon management, it was noted that the project level can be raised to match the external road level in front of the parking area.(Jeddah) | Owner | The required filling quantity was estimated at 59,000 m³ | Completed | 2026-05-21 |  | Consultant |  |  |  | closed
4 |  | Increase the sewage tank capacity for the Asir project to serve the administration building and playgrounds. | Contractor | Waiting for clarification of the project savings/cost reductions. | Completed | 2026-05-10
5 | 2026-05-21 | Difficulty accessing the parking area due to a level difference- Jazan | Consultant | Relocating the parking area to the far left side. | Completed | 2026-05-16
6 | 13-05-2026 | Road shoulder overlap at the Jeddah site | Consultant | A proposal has been submitted to the consultant. | Completed | 2026-10-01
7 | 2026-02-06 | Trees located within Asir site. | Owner | Waiting for tree removal by the landscaping contractor. | Completed | 2026-05-16
8 | 2026-10-10 | Medium voltage cables on excavation way | Owner | Medium voltage cables are conflicting with the excavation route. Assessment and coordination with relevant stakeholders are ongoing to determine the required mitigation actions. Risk remains open. | Open | 2026-10-17
9
10
48
49
50
13 |  | MV Network |  |  | Open

## Testing
Testing and Commissioning
Item | Planned Start Date | Planned Finish Date | Forecast Start Date | Forecast Finish Date | Actual Start Date | Actual Finish Date | % Completed | Open Comments | Closed Comments
Testing and Commissioning for MEP Works for Landscape Works - Jeddeh | 2027-01-05 | 2027-01-13 | 2027-04-14 | 2027-04-18
Testing and Commissioning for MEP Works for Toilet/Service Building - Jeddeh | 2026-12-01 | 2026-12-17 | 2026-12-31 | 2027-01-17
Testing and Commissioning for MEP Works for Playground Area - Jeddeh | 2027-01-14 | 2027-01-18 | 2027-03-31 | 2027-04-08
Testing and Commissioning for MEP Works for Landscape Works - Asir | 2027-01-02 | 2027-01-12 | 2027-03-20 | 2027-03-30
Testing and Commissioning for MEP Works for Toilet/Service Building - Asir | 2026-11-05 | 2026-11-30 | 2027-01-17 | 2027-02-10
Testing and Commissioning for MEP Works for Playground Area - Asir | 2026-12-01 | 2026-12-26 | 2027-02-11 | 2027-03-09
Testing and Commissioning for MEP Works for Landscape Works - Jazan | 2026-12-27 | 2027-01-13 | 2027-04-21 | 2027-04-26
Testing and Commissioning for MEP Works for Toilet/Service Building - Jazan | 2026-11-17 | 2026-12-15 | 2027-02-02 | 2027-03-03
Testing and Commissioning for MEP Works for Playground Area - Jazan | 2027-01-14 | 2027-01-19 | 2027-04-08 | 2027-04-26
|  |  | #REF! | #REF!

## Manpower
Head-Count ( Non Manual)
MONTHS | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | [14 empty] | non direct | [15 empty] | Jazan | [7 empty] | Asir | [7 empty] | Jeddah
Plan - Monthly | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | [27 empty] | CONTRACTOR STAFF | [5 empty] | CONTRACTOR LABOUR |  |  | CONTRACTOR STAFF | [5 empty] | CONTRACTOR LABOUR |  |  | CONTRACTOR STAFF |  |  |  |  | CONTRACTOR LABOUR
Planned - Cumulative | 19 | 38 | 57 | 76 | 95 | 114 | 133 | 152 | 171 | 190 | 209 | [27 empty] | POSITION |  | Expats |  | Saudi |  | TRADE | Expats | Saudi | POSITION |  |  | Expats | Saudi |  | TRADE | Expats | Saudi | POSITION |  | Expats | Saudi |  | TRADE | Expats | Saudi
Actual - Monthly | 10 | 15 | 22 | 32 | 31 | 30 | 30 | 30 | [17 empty] | daily report | [12 empty] | Project Manager | [5 empty] | General Labor / Helper | 2 |  | Project Manager | [5 empty] | General Labor / Helper | 4 |  | Project Manager |  | 2 |  |  | General Labor / Helper | 10
Actual Cumulative | 10 | 25 | 47 | 79 | 110 | 140 | 170 | 200 | [30 empty] | Civil Engineer |  | 2 |  |  |  | Carpenter |  |  | Civil Engineer |  |  | 2 |  |  | Carpenter |  |  | Civil Engineer |  | 4 |  |  | Carpenter
Forecast - Monthly | [6 empty] | 20 | 20 | 20 | 20 | 20 | [27 empty] | Technical office manager | [5 empty] | Steel Fixer |  |  | Technical office manager | [5 empty] | Steel Fixer | 6 |  | Technical office manager |  | 2 |  |  | Steel Fixer | 4
Saudi Monthly - Actual | [38 empty] | Quality Engineer | [5 empty] | Concreting Labor |  |  | Quality Engineer | [5 empty] | Concreting Labor | 4 |  | Quality Engineer |  |  |  |  | Concreting Labor | 4
Head-Count (Manual) | [25 empty] | direct | [12 empty] | HSE Engineer | [5 empty] | Plumber |  |  | HSE Engineer | [5 empty] | Plumber |  |  | HSE Engineer |  |  |  |  | Plumber
MONTHS | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | [27 empty] | Planning Engineer | [5 empty] | Electricial |  |  | Planning Engineer | [5 empty] | Electricial |  |  | Planning Engineer |  | 2 |  |  | Electricial
Plan - Monthly | 4 | 35 | 79 | 165 | 159 | 140 | 177 | 175 | 159 | 150 | 64 | [27 empty] | Surveyor Engineer |  | 2 |  |  |  | Equipment Operator |  |  | Surveyor Engineer | [5 empty] | Equipment Operator |  |  | Surveyor Engineer |  | 2 |  |  | Equipment Operator
Planned - Cumulative | 4 | 39 | 118 | 283 | 442 | 582 | 759 | 934 | 1093 | 1243 | 1307 | [27 empty] | Electrical Engineer | [5 empty] | Glass & aluminum technical |  |  | Electrical Engineer | [5 empty] | Glass & aluminum technical |  |  | Electrical Engineer |  |  |  |  | Glass & aluminum technical
Actual - Monthly | 4 | 30 | 74 | 123 | 63 | 72 | 64 | 70 | [17 empty] | daily report | 0 | [11 empty] | Mechanical Engineer | [5 empty] | OTHER |  |  | Mechanical Engineer | [5 empty] | OTHER |  |  | Mechanical Engineer |  |  |  |  | OTHER
Actual Cumulative | 4 | 34 | 108 | 231 | 294 | 366 | 430 | 500 | [30 empty] | Agriculture Engineer | [5 empty] | curbstone worker |  |  | Agriculture Engineer | [5 empty] | curbstone worker |  |  | Agriculture Engineer |  |  |  |  | curbstone worker
Forecast - Monthly | [7 empty] | 175 | 159 | 150 | 64 | [27 empty] | Quantity Surveyor Engineer | [5 empty] | Water proofing labor |  |  | Quantity Surveyor Engineer | [5 empty] | Water proofing labor |  |  | Quantity Surveyor Engineer |  |  |  |  | Water proofing labor
Saudi - Actual | [38 empty] | HSE Officer |  | 2 |  |  |  | PLASTER WORKER |  |  | HSE Officer |  |  | 2 |  |  | PLASTER WORKER |  |  | HSE Officer |  | 2 |  |  | PLASTER WORKER
[39 empty] | Surveyor | [5 empty] | SHUTERR DOOR WORKER |  |  | Surveyor |  |  | 2 |  |  | SHUTERR DOOR WORKER |  |  | Surveyor |  | 2 |  |  | SHUTERR DOOR WORKER
Head-Count (Non-Manual) | [10 empty] | 96 | [12 empty] | Month | 2026-10-31 | 2026-11-30 | [12 empty] | Document Controller | [5 empty] | steel stu worker |  |  | Document Controller | [5 empty] | steel stu worker |  |  | Document Controller |  | 2 |  |  | steel stu worker
Planned | Actual |  | Variance |  | Forecast Next Month |  | Saudi Staff | [31 empty] | Supervisor |  | 2 |  |  |  | epoxy worker |  |  | Supervisor |  |  | 4 |  |  | epoxy worker |  |  | Supervisor |  | 2 |  |  | epoxy worker
19 | 30 |  | 11 |  | 25 |  | 0 | [37 empty] | ASPHALT WORKER | [8 empty] | ASPHALT WORKER |  |  | Labor |  | 2 |  |  | ASPHALT WORKER
[45 empty] | paint workers | [8 empty] | paint workers | [7 empty] | paint workers
Head-Count (Manual) | [10 empty] | Man Power by Trade | [33 empty] | TANKS workers | [8 empty] | TANKS workers | [7 empty] | TANKS workers
Planned | Actual |  | Variance |  | Forecast Next Month |  | Saudi Staff |  |  |  | Key Trade |  | Labor |  | Skilled Labor | Driver / Operator | Carpenter | Steel Fixer | Mason | Plumber | Electrician | Others | Total |  |  |  |  | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | [6 empty] | fire worker | [8 empty] | fire worker | [7 empty] | fire worker
175 | 70 |  | -105 |  | 140 |  | 0 |  |  |  | Plan |  | 65 |  | 25 | 27 | 0 | 26 | 0 | 0 | 0 | 32 | 175 | [21 empty] | Celing worker | [8 empty] | Celing worker | [7 empty] | Celing worker
[11 empty] | Actual |  | 15 |  | 10 | 12 | 6 | 6 | 0 | 3 | 3 | 15 | 70 | [21 empty] | Air conditioning technician | [8 empty] | Air conditioning technician | [7 empty] | Air conditioning technician
[45 empty] | TOTAL | 2 | [7 empty] | TOTAL | 14 | [6 empty] | TOTAL | 18
[45 empty] | SUB-CONTRACTORS LABOURS | [8 empty] | SUB-CONTRACTORS LABOURS | [7 empty] | SUB-CONTRACTORS LABOURS
[45 empty] | DESCRIPTION | Expats | Saudi | [6 empty] | DESCRIPTION | Expats | Saudi | [5 empty] | DESCRIPTION | Expats | Saudi
[45 empty] | Carpenter | [8 empty] | Carpenter | [7 empty] | Carpenter
[45 empty] | Steel Fixers | [8 empty] | Steel Fixers | [7 empty] | Steel Fixers
Equipment | [44 empty] | Labors | [8 empty] | Labors | [7 empty] | Labors
MONTHS | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | [33 empty] | Drivers | [8 empty] | Drivers | [7 empty] | Drivers
Plan - Monthly | 0 | 10 | 25 | 29 | 25 | 24 | 19 | 27 | 16 | 20 | 12 | [33 empty] | TOTAL | 0 | [7 empty] | TOTAL | 0 | [6 empty] | TOTAL | 0
Planned - Cumulative | 0 | 10 | 35 | 64 | 89 | 113 | 132 | 159 | 175 | 195 | 207 | [27 empty] | TOTAL CONTRACTOR STAFF |  | 8 |  |  |  | TOTAL PLANNED DIRECT MANPOWER |  |  | TOTAL CONTRACTOR STAFF |  |  | 10 |  |  | TOTAL PLANNED DIRECT MANPOWER |  |  | TOTAL CONTRACTOR STAFF |  | 22 |  |  | TOTAL PLANNED DIRECT MANPOWER
Actual - Monthly | 0 | 10 | 25 | 44 | 44 | 36 | 30 | 21 | [36 empty] | TOTAL ACTUAL DIRECT MANPOWER |  | 2 | [6 empty] | TOTAL ACTUAL DIRECT MANPOWER |  | 14 | [5 empty] | TOTAL ACTUAL DIRECT MANPOWER |  | 18
Actual Cumulative | 0 | 10 | 35 | 79 | 123 | 159 | 189 | 210 | [30 empty] | CONSULTANT STAFF | [8 empty] | CONSULTANT STAFF | [8 empty] | CONSULTANT STAFF
Forecast - Monthly | [5 empty] | 30 | 19 | 27 | 16 | 20 | 12 | [27 empty] | POSITION |  | Expats |  | Saudi |  | EQUIPMENT AVAILABLE AT SITE TODAY |  |  | POSITION |  |  | Expats | Saudi |  | EQUIPMENT AVAILABLE AT SITE TODAY |  |  | POSITION |  | Expats | Saudi |  | EQUIPMENT AVAILABLE AT SITE TODAY
[39 empty] | Project Engineer |  | 0 |  |  |  | TYPE | Working | Idle | Project Engineer |  |  | 0 |  |  | TYPE | Working | Idle | Project Engineer |  | 2 |  |  | TYPE | Working | Idle
[39 empty] | Control / Schedule Engineer |  | 0 |  |  |  | Buldozer | 0 |  | Control / Schedule Engineer |  |  | 0 |  |  | Buldozer | 0 |  | Control / Schedule Engineer |  | 2 |  |  | Buldozer | 0
Equipment Count | [38 empty] | Quality Engineer |  | 0 |  |  |  | Grader Machine | 0 |  | Quality Engineer |  |  | 0 |  |  | Grader Machine | 0 |  | Quality Engineer |  | 2 |  |  | Grader Machine | 2
Planned | Actual |  | Idle |  | Variance |  | Forecast Next Month | [31 empty] | HSE Engineer |  | 0 |  |  |  | Roller Compactor | 0 |  | HSE Engineer |  |  | 0 |  |  | Roller Compactor | 0 |  | HSE Engineer |  | 2 |  |  | Roller Compactor | 0
27 | 21 |  | 0 |  | -6 |  | 20 | [31 empty] | Mechanical Engineer |  | 0 |  |  |  | Shevol Loader | 2 |  | Mechanical Engineer |  |  | 0 |  |  | Shevol Loader | 2 |  | Mechanical Engineer |  | 2 |  |  | Shevol Loader | 4
[39 empty] | Electrical Engineer |  | 0 |  |  |  | Water Tank | 0 |  | Electrical Engineer |  |  | 0 |  |  | Water Tank | 0 |  | Electrical Engineer |  | 2 |  |  | Water Tank | 0
[39 empty] | Planning Engineer |  | 0 |  |  |  | Dump Truck | 0 |  | Planning Engineer |  |  | 0 |  |  | Dump Truck | 10 |  | Planning Engineer |  | 2 |  |  | Dump Truck | 8
[39 empty] | Civil Engineer - Structure/Buildings |  | 0 |  |  |  | Poclain Excavator | 6 |  | Civil Engineer - Structure/Buildings |  |  | 0 |  |  | Poclain Excavator | 2 |  | Civil Engineer - Structure/Buildings |  | 2 |  |  | Poclain Excavator | 2
[39 empty] | Civil Engineer - Wet Utilities |  | 0 |  |  |  | Bobcat | 0 |  | Civil Engineer - Wet Utilities |  |  | 0 |  |  | Bobcat | 0 |  | Civil Engineer - Wet Utilities |  | 2 |  |  | Bobcat | 0
[39 empty] | Architect |  | 0 |  |  |  | Truck | 12 |  | Architect |  |  | 0 | [5 empty] | Architect |  | 2
Type | Excavator | Loader | Bulldozer | Water Tanker | Grader | Truck | Road Roller | Asphalt Paver | Crane | Bobcat | Bobcat | Compactor | Other | Total | [24 empty] | Surveyor |  | 2 |  |  |  | Crane | 0 |  | Surveyor |  |  | 0 | [5 empty] | Surveyor |  | 2
Plan | 3 | 5 | 2 | 5 | 3 | 5 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 27 | [24 empty] | Quality Engineer |  | 0 | [6 empty] | Quality Engineer |  |  | 0 | [5 empty] | Quality Engineer |  | 2
Actual | 3 | 3 | 0 | 4 | 0 | 3 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 21 | [24 empty] | Document Controller |  | 0 | [6 empty] | Document Controller |  |  | 2 | [5 empty] | Document Controller |  | 2
Idle | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [24 empty] | Office Boy |  | 0 | [6 empty] | Office Boy |  |  | 0 | [5 empty] | Office Boy |  | 2
[39 empty] | TOTAL CONSULTANT STAFF |  | 2 | [6 empty] | TOTAL CONSULTANT STAFF |  |  | 2 | [5 empty] | TOTAL CONSULTANT STAFF |  | 28
[39 empty] | TOTAL STAFF AT SITE |  | 10 | [6 empty] | ` |  |  | 12 | [5 empty] | TOTAL STAFF AT SITE |  | 50
[39 empty] | TOTAL IMMUNE STAFF | [8 empty] | TOTAL IMMUNE STAFF | [8 empty] | TOTAL IMMUNE STAFF
[39 empty] | MATERIAL RECEIVED AT SITE TODAY (MIR) | [8 empty] | MATERIAL RECEIVED AT SITE TODAY (MIR) | [8 empty] | MATERIAL RECEIVED AT SITE TODAY (MIR)
[39 empty] | BOQ No. | DESCRIPTION |  |  | QTY | UNIT |  |  |  | BOQ No. | DESCRIPTION |  |  | QTY | UNIT |  |  |  | BOQ No. | DESCRIPTION |  | QTY | UNIT
[40 empty] | - |  |  |  |  | TOTAL PLANNED |  |  |  | - |  |  |  |  | TOTAL PLANNED |  |  |  | - |  |  |  | TOTAL PLANNED
[40 empty] | - |  |  |  |  | TOTAL ACTUAL | 20 | 0 |  | - |  |  |  |  | TOTAL ACTUAL | 14 | 0 |  | - |  |  |  | TOTAL ACTUAL | 16 | 0
ALL Sites
[39 empty] | CONTRACTOR STAFF | [5 empty] | CONTRACTOR LABOUR
[39 empty] | POSITION |  | Expats |  | Saudi |  | TRADE | Expats | Saudi
[39 empty] | Project Manager | [5 empty] | General Labor / Helper | 8
[39 empty] | Civil Engineer |  | 4 |  |  |  | Carpenter | 0
[39 empty] | Technical office manager |  | 1 |  |  |  | Steel Fixer | 5
[39 empty] | Quality Engineer |  | 0 |  |  |  | Concreting Labor | 4
[39 empty] | HSE Engineer |  | 0 |  |  |  | Plumber | 0
[39 empty] | Planning Engineer |  | 1 |  |  |  | Electricial | 0
[39 empty] | Surveyor Engineer |  | 2 |  |  |  | Equipment Operator | 0
[39 empty] | Electrical Engineer |  | 0 |  |  |  | Glass & aluminum technical | 0
[39 empty] | Mechanical Engineer |  | 0 |  |  |  | OTHER | 0
[39 empty] | Agriculture Engineer |  | 0 |  |  |  | curbstone worker | 0
[39 empty] | Quantity Surveyor Engineer |  | 0 |  |  |  | Water proofing labor | 0
[39 empty] | HSE Officer |  | 3 |  |  |  | PLASTER WORKER | 0
[39 empty] | Surveyor |  | 2 |  |  |  | SHUTERR DOOR WORKER | 0
[39 empty] | Document Controller |  | 1 |  |  |  | steel stu worker | 0
[39 empty] | Supervisor |  | 4 |  |  |  | epoxy worker | 0
[45 empty] | ASPHALT WORKER | 0
[45 empty] | paint workers | 0
[45 empty] | TANKS workers | 0
[45 empty] | fire worker | 0
[45 empty] | Celing worker | 0
[45 empty] | Air conditioning technician | 0
[45 empty] | TOTAL | 17
SUB-CONTRACTORS LABOURS
[45 empty] | DESCRIPTION | Expats | Saudi
Carpenter
Steel Fixers
Labors
Drivers
[45 empty] | TOTAL | 0
[39 empty] | TOTAL CONTRACTOR STAFF |  | 18 |  |  |  | TOTAL PLANNED DIRECT MANPOWER
[45 empty] | TOTAL ACTUAL DIRECT MANPOWER |  | 17
CONSULTANT STAFF
[39 empty] | POSITION |  | Expats |  | Saudi |  | EQUIPMENT AVAILABLE AT SITE TODAY
[39 empty] | Project Engineer |  | 1 |  |  |  | TYPE | Working | Idle
[39 empty] | Control / Schedule Engineer |  | 1 |  |  |  | Buldozer | 0
[39 empty] | Quality Engineer |  | 1 |  |  |  | Grader Machine | 1
[39 empty] | HSE Engineer |  | 1 |  |  |  | Roller Compactor | 0
[39 empty] | Mechanical Engineer |  | 1 |  |  |  | Shevol Loader | 4
[39 empty] | Electrical Engineer |  | 1 |  |  |  | Water Tank | 0
[39 empty] | Planning Engineer |  | 1 |  |  |  | Dump Truck | 9
[39 empty] | Civil Engineer - Structure/Buildings |  | 1 |  |  |  | Poclain Excavator | 5
[39 empty] | Civil Engineer - Wet Utilities |  | 1 |  |  |  | Bobcat | 0
[39 empty] | Architect |  | 1 |  |  |  | Truck | 6
[39 empty] | Surveyor |  | 2 |  |  |  | Crane | 0
[39 empty] | Quality Engineer |  | 1
[39 empty] | Document Controller |  | 2
[39 empty] | Office Boy |  | 1
[39 empty] | TOTAL CONSULTANT STAFF |  | 16
[39 empty] | TOTAL STAFF AT SITE |  | 34
TOTAL IMMUNE STAFF
MATERIAL RECEIVED AT SITE TODAY (MIR)
[39 empty] | BOQ No. | DESCRIPTION |  |  | QTY | UNIT
[40 empty] | - |  |  |  |  | TOTAL PLANNED
[40 empty] | - |  |  |  |  | TOTAL ACTUAL | 25 | 0

## HSE-Stat
Safety Statistics (06-Oct-2026 to 13-October-2026)
Category | Item |  | This Week | This Month | Year to Date | Cumulative | [6 empty] | Item | This Week | This Month | Year to Date | Cumulative
Lagging Indicators | Total Hours Worked |  | 5220 | 11700 | 137270 | 137270 | [6 empty] | Total Hours Worked | 4620 | 14280 | 40050 | 40050
| Safe Hours Worked |  | 5220 | 11700 | 137270 | 137270 | [6 empty] | Safe Hours Worked | 4620 | 14280 | 40050 | 40050
| LTI |  | 0 | 0 | 0 | 0 | 5220 |  | 32 | 55 |  |  | LTI | 0 | 0 | 0 | 0
| MTC (Healed w/o Disability) |  | 0 | 0 | 0 | 0 |  |  |  | 87 |  |  | MTC (Healed w/o Disability) | 0 | 0 | 0 | 0
| MTC (Healed w/ Disability) |  | 0 | 0 | 0 | 0 |  |  | Indirect Contractor Staff | Final Direct Manpower |  |  | MTC (Healed w/ Disability) | 0 | 0 | 0 | 0
| Near Miss |  | 0 | 0 | 0 | 0 | [6 empty] | Near Miss | 0 | 0 | 0 | 0
| First Aid Cases |  | 0 | 0 | 0 | 0 | [6 empty] | First Aid Cases | 0 | 0 | 0 | 0
| Fatality |  | 0 | 0 | 0 | 0 | [6 empty] | Fatality | 0 | 0 | 0 | 0
| Fire Incident Cases |  | 0 | 0 | 0 | 0 | [6 empty] | Fire Incident Cases | 0 | 0 | 0 | 0
| Vehicle Incident |  | 0 | 0 | 0 | 0 | [6 empty] | Vehicle Incident | 0 | 0 | 0 | 0
| Property Damages |  | 0 | 0 | 0 | 0 | [6 empty] | Property Damages | 0 | 0 | 0 | 0
Proactive | Induction Training |  | 0 | 18 | 160 | 160 | [6 empty] | Induction Training | 5 | 115 | 115 | 115
| No.of Internal Training |  | 0 | 04 Session | 17 Session | 17 Session | [6 empty] | No.of Internal Training | 1 | 3 Session | 6 Session | 6 Session
| No.of Internal Audit |  | 0 | 0 | 0 | 0 | [6 empty] | No.of Internal Audit | 0 | 0 | 0 | 0
| No. of Toolbox Talks |  | 3 | 7 Sessions | 159 sessions | 159 sessions | [6 empty] | No. of Toolbox Talks | 3 | 6 sessions | 18 sessions | 18 sessions
| Safety Awards/Incentives |  | 0 | 0 | 0 | 0 | [6 empty] | Safety Awards/Incentives | 0 | 0 | 0 | 0
[7 empty] | Category | Item |  | This Week | This Month | Year to Date | Cumulative
Consultant Safety Inspection (Weekly Basis) | [6 empty] | Overall Average | 93.33%
Week Number | Date of Audit | Date Issued | Numbers Of Comments | Overall Score | Date Closed | Closure Duration | This Week Score | 77.63%
Week-1 | 2026-04-28 | 2026-04-28 | 9 | 80% | 2026-05-05 | 8
Week-2 | 2026-05-04 | 2026-05-13 | 10 | 80% | 2026-05-13 | 1
Week-3 | 2026-05-05 | 2026-05-05 | 2 | 100% | NA | NA
Week-4 | 2026-05-06 | 2026-05-06 | 10 | 100% | 2026-06-10 | 34
Week-5 | 2026-05-14 | 14-05-2026 | 11 | 100% | 2026-07-02 | NA
Week-6 | 2026-06-08 | 2026-06-08 | 10 | 100% | 2026-07-02 | NA
Week-7 | 20-06-2026 | 20-06-2026 | 7 | 100% | 2026-07-02 | NA
Week-8 | 2026-07-08 | 2026-07-08 | 7 | 80% | 21-08-2026 | NA
Week-9 | 27-07-2026 | 27-07-2026 | 17 | 100% | 21-08-2026 | NA
Week-10
Week-11
Week-12
Week-13
Week-14
Week-15
Week-16
Week-17
Week-18
Week-19
Week-20
Week-21
Week-22
Week-23
Week-24
Week-25
Week-26
Week-27
Week-28
Week-28
Week-29
Week-30
Week-31
Week-32
Week-32
Week-34
Week-35
week-36
week-37
week-38
week-39
week-40
week-41
week-42
week-43
week-44
week-45
week-46
week-47
week-48
week-49
week-50
week-51
week-52
week-53
week-54
week-55
week-56
week-57
week-58
week-59
week-60
week-61
week-62
week-63
week-64
week-65
week-66
week-67

## HSE
MODON HSE Site Inspection Report
Date |  |  | 2026-10-13 |  |  |  |  | Inspected By: |  |  |  | PMO
Project ID. |  |  | MLTX-02-004 |  |  |  |  | Report No. | 13 |  |  |  |  | MODON PM Name |  | Engr.Yazeed Al Ragabh
Project Name: |  |  | Playground Initiative Western Region |  |  |  |  | Contractor: |  | PROFAST |  |  |  |  | Safety Performance |  | 2 |  |  | 83.75%
Inspections are a snapshot in time and refer only to the practices and documentation observed at the time of the Inspection. It remains the responsibility of the Consultant and Contractor to ensure that all aspects of Health & Safety are suitably managed.
1 |  | Good Practice |  |  | 2 | Need Improvement | [5 empty] | 3 | Fail (Life Threatening Activity) / Comliance with Plan & Procedures |  | N/A | Atcitty Not Applicable for this Site Inspection Report
No. | Topic | [5 empty] | Wt. | HSE Compliance |  |  | No. | Topic | [5 empty] | Wt. | HSE Compliance
1 | Access and Egress - (General access to site, segregated from vehicles, / Overhead protection, while entering into the building /Adequate lighting provided when dark or overnight work) | [5 empty] | 5% | 2 |  |  | 14 | Work at Height - (PPE/Fall Protection(Same level, above and blow) / Training / Fall restraint / competency /Safe access & egress to and from work at height / Ladders / Openings (floor/shafts/Provision of emergency rescue) | [5 empty] | 5% | 2 |  |  |  | 1 | 100 | 1
2 | Traffic Management - (Loading/unloading/sheeting/temp. routes/speed/parking/competence) | [5 empty] | 3% | 2 |  |  | 15 | Scaffolding - (Temp. Scaffolding Work-platform (All types) - qualified scaffolder / Inspection / Tagged / Safe Access/egress / PTW/Falsework & Formwork) | [5 empty] | 4% | N/A |  |  |  | 2 | 75 | 2
3 | Site Signage - (Project Notice Board & General Signage) | [5 empty] | 2% | 1 |  |  | 16 | Mobile Elevated Work platform (MEWP) - (PTW/competence requirements/conditions/inspections/tagged/training/Full-body harness) | [5 empty] | 4% | N/A |  |  |  | 3 | 0 | 3
4 | PPE Compliance - (Use, storage, stock, handling & checks - Head, Foot, Eye, Hearing) | [5 empty] | 5% | 1 |  |  | 17 | Excavation & Trenches - (PTW/Edge protection/buffer zone/Slope/Benching/Shoring/Geo-tech report/Atmospheric hazards/Acess&egress/Emergency management / MS&RA/H.E) | [5 empty] | 3% | 1 | [5 empty] | N/A
5 | Housekeeping - (Material correctly stored/Rubbish cleaned & removed daily/slips & trips hazards) | [5 empty] | 3% | 2 |  |  | 18 | Confined Space - (PTW/Training/competence/Emergency Management/MS & RA/Safe access/egress) | [5 empty] | 5% | N/A
6 | Storage of Materials - (Transporting, storage, training and use - Combustible / Flammable / Hazardous substances (COSHH) | [6 empty] | N/A |  |  | 19 | Fire Protection - (Flammable/Oxy. LPG /Combustible separated/FE's/Flashback arrestor/Sparks & slags/Smoking area/PTW/Generators/MS & RA/Emergency Management) | [6 empty] | N/A |  | Red | Serious injury or death (immediately)
7 | Site Waste Management - (Hazardous waste /Combustible waste / Human waste / Construction waste - asphalt, cable, timber, paving roof sheeting tiles, plastic & bricks) | [6 empty] | 1 |  |  | 20 | Health & Welfare - (Adequate drinking water/shaded - eating & rest area/washing & sanitary facilities/Certified FA/FA Box & Stock/adequate toilets/Ambulance) | [6 empty] | 2 |  | Yellow | Minor or near miss (3 days to comply)
8 | Health Surveillance - (Expose to excessive noise/vibration/dust/silica/CO/cement/radiation/extreme weather condition) | [5 empty] | 3% | 2 |  |  | 21 | Environmental Incident Measures - (Spill/ Leakage / Concrete wash / vehicle & eqpts. wash / waste disposal/Sewers and drains/emissions/Emergency Management/Training/site run-off water) | [5 empty] | 5% | 2 |  | Green | No issues
9 | Electrical Safety - (Electrical qualified /RCD/GFCI/Industrial Cocket/LOTO/Cable-overhung or buried/Cords in good condition/current inspection tag) | [5 empty] | 5% | 1 |  |  | 22 | HSE Communications & Meetings - (Schedule HSE Meetings/Safety Committee meetings/Alerts / Lesson learned/Safety Bulletin contains latest HSE KPI) | [5 empty] | 5% | 1
10 | Tools & Equipment - (Includes, powered, hydraulic & pneumatic/Guards in place/Properly stored/RCD Protection/Earthed/Good condition & tagged) | [5 empty] | 3% | 2 |  |  | 23 | HSE Plan & Associated Procedures - (Approved updated HSE Plan/ CEMP/HAZComm/Procedures/Standards/Project Safety Risk Register) | [5 empty] | 3% | 2 |  | 26 points > 4 minors then is it’s a serious issue
11 | Manual Handling - (Lifting/loading/pulling/pushing/twisting/awkward posture/repetitive task/frequent and prolong physical effort/Reasonable practicable use of mechanical aid) | [5 empty] | 3% | 2 |  |  | 24 | Health, Safety & Environment Incident reporting - (Review of HSE Statistics, Reporting of Unsafe Act & Conditions/ Reporting of Near Miss incident/Reporting of FA cases/Record MT cases) | [5 empty] | 3% | 2
12 | Vehicle and mobile equipment / Plant - (dumpers; excavators, cranes, piling rigs, grader, roller, loaders/condition/KSA License/certification) | [5 empty] | 5% | 1 |  |  | 25 | HSE Awareness, Training & Competence - (Policy /Objective & targets/Information, training/Climatic condition awareness/Reponses in emergency situation/ Safety Behavior Observation) | [5 empty] | 4% | 2
13 | Lifting Operations & Rigging - (Lifting Plan/Lifting devices & gears/PTW/Condition/3rd party certification/bank-man/rigger/slingers/man-basket/inspection record/tagged) | [6 empty] | N/A |  |  | 26 | Project Leadership Site Tours - (Provide evidence of proactive safety performance/Deficient discovered discussed/Positive feedback/Workers resolving safety issues) | [6 empty] | 2
Prepared by: |  |  |  | Atish Aitaf | [6 empty] | Sent to MODON PM: |  |  |  | Engr.Yazeed Al Ragabh
Safety Results
1 |  | 7 |  |  |  | 2 |  | 13 |  |  |  |  | 3 | 0
Note on C13: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Safe access / egress for people to their work area 2 - Safe access / egress for construction vehicles 3 - Access properly restricted-site fencing provided and maintained 4 - Access proper and not blocked 5 - Safe access is available for rescue operation 6 - Storage access / exit are clearly marked and unobstructed 8 - Access and egress is in good condition, hand holds, ladder etc. are sound and in place 9 - Ensure unauthorized public access is prevented 11 - Site assembled ladders or make-shift tables for access are forbidden on site. 13 - Use proper bridges, walkways or gangways to access or cross trenches or an excavation area 14 - Surrounding areas are cleared and barricaded and access restricted to all unauthorized trades while crane in operation 15 - To ensure early access to accredited medical / rehabilitation services 16 - Parking vehicles on site access roads causing obstruction 17 - All personnel will be instructed that access to firefighting equipment must remain clear at all times 18 - Access control gates to be locked out of hours 19 - Site access gates to be designed and located to, where possible, avoid clashes with external hazards / activities
Note on T13: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Personal Fall Arrest System; 1 - Is the suitable harness harnesses is provided 2 - Are shock absorbing lanyard with 2 locking snap hooks. 3 - Is anchorage point strong enough and can support 5,000 Ibs. 4 - Do inspection checklist is being implemented before use. 5 - Is the emergency plan for rescue in place Personal Fall Restraint System; 1 - The fall restraint equipment should be set and adjusted so there is no free fall over the edge. 2 - A harness or body belt may be used 3 - The anchorage point must support 4 times the intended load. Positioning System; 1 - Is a suitable harness or body belt provided 2 - Is there a not more than 2' free fall maintained 3 - Is the anchorage point capable of supporting 2 times the intended load or 3.000 Ibs, whichever is greater 4 - Is 100% tie-off (protection from falls at all times, even when moving from point to point) provided while using personal fall protection with two lanyards Fall Protection System; 1 - Suitable edge protection and work platforms are to be provided to prevent a fall occurring 2 - Where the provision of edge protection or adequate platforms cannot be provided safety nets or other soft-landing systems such as inflatable bags are to be used to minimize the consequences of a fall. 3 - If nets are used, they must be installed by a competent rigger and fitted as close under the work surface as possible. 4 - Areas below roof works are to be cordoned off and properly signed to prevent personnel being injured from falling materials 5 - If access onto the roof cannot be avoided, edge protection is to be installed 6 - Floor and wall openings are to be protected using covers of adequate strength to withstand the expected load that will be imposed and securely fixed. 7 - Penetrations in walls such as those provided for lift shafts, door openings, etc. are to be closed with suitable strength material or have fixed protective barriers around the penetration with a sign warning personnel of the danger of falling.
Note on C14: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are arrival and departure of vehicles and delivery accompany by security department? 2 - Are proper loading, unloading and securing loads, being properly controlled? 3 - Is the proper sheeting & coupling in place when transporting and disposing material to and from site? 4 - Is the parking to the designated parking lot and in reverse order? 5 - Is the designated speed limit adhered on workplace? 6 - Provision of ramps, traffic signs, cones, barriers, demarcation posts and tape, flashing lights and any other traffic control devices. 7 - Do visiting drivers are being inducted at the workplace, prior to enter on the workplace? 8 - Are visiting drivers restricted to dangerous areas, e.g. moving to and from they vehicles to washrooms, lavatory & offices etc.? 9 - Do drivers observe site rules and procedures, for delivery, loading and unloading? 10 - Are the areas wide enough for the safe movement of large vehicles (including visiting vehicles)? 11 - Does drivers are competent, hold valid local driving license and competent training? 12 - Ensure the vehicle and trailers have their brakes applied and all stabilizers properly positioned before beginning loading or unloading?
Note on T14: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Base soundness, load adequately spread (base plate jacks, base plate on firm ground). 2 - Line of standard (vertical) and ledger (horizontal) secure and plumb. 3 - Spacing of transoms on platforms, support for Scaff boards, boards are not over protruded and boards are secured. 4 - Staggering of joints vertical and horizontal. 5 - Guardrail / fall protection. (Top rail – Min.1mtr, Mid rail – 470mm from floor and Toe boards – Minimum150mm) 6 - Longitude and bracing on standards and ledgers. 7 - If close to structure, ties must be on lift below to top working platform and every 3m, load bearing couplers used or tie with certified anchor bolts (eye bolts). 8 - Clamps and tubes used are of correct fittings, size and free from defects. 9 - Tubes & fittings free from defects / deformation. 10 - Safe and proper access available to the working platform. 11 - Scaff tags signed, displayed and up to date. 12 - If close to slab edge/opening scaffold tied and secured to structure correctly.
Note on C15: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a Project Notice Board - (showing HSE Statistics / Safety alerts / lesson learned)? 2 - Is there prominent safety boards that are depicting the mandatory PPE on the workplace? 3 - Are other safety required signs are prominently installed on the workplace in relevant to their work-task, as following: > Hazardous Substances - e.g. respiratory protection Sign > Working at Height - e.g. Full body Harness Sign > Working UG - e.g. Full body Harness, SCBA, Ventilation, PTW Signage etc. > Working with Electrical - e.g. Leather Gloves, Goggles, Face shield, Electric shock proof helmet & shoes > Working with Chemicals - Signage = e.g. Impermeable gloves/clothing's, long sleeves, Goggles 4 - General Site Safety Signs: > Prohibition Sign = (e.g., ‘no access for unauthorized persons’). > Warning Signs = (e.g., ‘danger: electricity’) > Mandatory Signs = e.g., ‘eye protection must be worn’) > Emergency Escape or First Aid Sign = e.g., ‘emergency exit/escape route’) > Safety Color Signs = (e.g., yellow means ‘be careful’ or ‘take precautions’) > Illuminated Signs = (e.g., many emergency exit signs) > Acoustic Signals =( e.g., fire alarm) > Fire safety sign > Supplementary Signs = "This way"
Note on T15: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Man-Lift operators are to be competent and trained to operate the specific Man-Lift by examination and hold a current approved certificate / license from an approved and internationally recognized source (TUV, SGS etc. 1 - All Man-Lifts shall be inspected by a 3rd party on an annual basis. 2 - All Man-Lifts shall display a sticker corresponding to the 3rd party inspection certificate. 3 - The manufacturer's instruction manual must be on site for each and every type of Man-Lift in use. 4- A pre-start daily operator inspection of the equipment will be performed and documented on a daily basis as per the manufacturer's instructions. The user is responsible for ensuring this has occurred. 5 - The use of a Man-Lift as, or in lieu of, a Crane is strictly prohibited. Man-Lifts are to be used only for lifting personnel and small tools within the designed Safe Working Load. 6 - The platform is not to be loaded in excess of the designed working load; the safe working load of the platform is to be clearly displayed on both the platform, and body of the equipment. 7 - All persons inside work platforms shall wear a full-body harness attached to the designated anchor point. Personnel must stand on the floor of the working platform; standing on the handrails is strictly prohibited. Harnesses must not be attached to other structures outside of the working platform. 8 - Personnel must stay inside the working platform at all times; the platform must not be used as an access to structures. The use of staging or ladders to extend height is strictly forbidden. 9 - Securing the boom or work platform to any structure is strictly prohibited. The boom or working platform must not be rested upon on any structure, nor is the Man-Lift to be used as a jack/ prop or tie to support other structures. 10 - All Man-Lifts must be equipped with a 5kg (10lb) fire extinguisher. 11 - No man-lifts are to be operated that have had safety devices removed or disabled. Daily operator inspections are to include the testing of these devices (limit switches, alarms and hazard flashing beacons). 12 - Specific Man-Lifts are fitted with outriggers and/or stabilizers which must be used as per manufacturer's instructions. 13 - The work area surrounding the man-lift is to be cordoned off using barricades and signage if the area is used by other workers or vehicles. A full traffic management plan is required for all works involving man-lifts when working on highways. Under no circumstances is any part of a man-lift to extend or swing into a line of traffic.
Note on C16: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Does required mandatory PPE (refer specification BS, EN & ANSI) is provided, as following? > Safety helmet (see below for color scheme) > Safety glasses (shaded for outdoor work and clear inside structures and during non-daylight hours) > Safety boots (safety shoes are prohibited) > Orange hi-visibility vest 2 - Additional PPE shall be provided to a specific task 3 - Do specific PPE is provided according to their job requirement? > To work at height - Full Body harness / Fall arrest Devices / Fall Restraint Devices / V & H Lifeline etc. > To work in the confined space - Full Bodyarness, Tripod with retractable lifeline, SCBA, Masks etc. > 4 - Are the PPE stored appropriately to prevent deformation or distortion? 5 - Has self assessment being carried out for in according to the work requirements? 6 - EYEWEAR (Glasses/Goggles/Face Shields) > Eyewear cleaning supplies available. > Safety glasses in good condition and lenses free of scratches. > Goggles adjustment strap not cracked or frayed, not deformed, or lenses not > Face shields in good condition, including adjustment band, and free of scratches or 7 - HEAD PROTECTION > Hard hat bill and suspension attached as allowed by manufacturer. > is pliable, free of dents, cracks, nicks, or any damage due to impact. > Suspension maintained at 1.25 inches from inside of shell. > Suspension free of cuts or fraying, torn headband, adjustment strap workable. > Electrical hard hat matched to hazard classification. > Dated to determine whether within manufacturer’s allowable 5-year use time period. 8 - HAND PROTECTION > Available in sizes matched to employee. > Gloves free of rips tears, abrasions, or holes. > Matched to manufacturer’s specification for chemicals used onsite. > Electrical gloves matched to hazard and periodically inspected for insulating rating. > Maintained in a clean and sanitary condition, decontaminated or disposed properly. 9 - BODY PROTECTION > Available in sizes matched to employee. > Maintained in a clean and sanitary condition, decontaminated or disposed properly. > Vapor-tight fully encapsulated suits tested at required periodic intervals. > Flame-resistant clothing matched to electrical hazard and arc flash rating. > Welding gear matched to degree of hazard and free of cuts, tears or burn holes. > Flotation gear available for work near or on water and in good condition. 10 - HOT AND COLD BODY PROTECTION > Cooling gear available based on degree of heat stress hazard. > Cooling gear in operable, clean, and sanitary condition. > Cold-weather gear provided based on needs assessment. > Cold-weather gear available in sizes to match employees. > Cold-weather gear is in free of tears, rips, or holes and in maintained in a clean condition. 11 - TRAINING > Initial PPE training completed by employees. > Training conducted when new types or styles of PPE are issued. > PPE selection, use, and maintenance reviewed at daily safety briefings. 12 - Provision of impermeable clothing appropriate for the work being performed? 13 - Wearing of shorts, sleeveless shirts, loose clothing are prohibited across the MODON Projects. 14 - Clothing contaminated with grease, oils, fuels and other hazardous substances is not to be worn.
Note on T16: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a valid Excavation PTW in place? 2 - Are spoils, materials, and equipment set back at least 1.5 meters from the edge of the excavation? 3 - Are walkways and bridges over excavations structurally sound, minimum 0.5 meter in width and equipped with standard guard rails and toe boards? 4 - Are warning systems established and used when mobile equipment is operating near the edge of an excavation? 5 - Are employees prohibited from working on the faces of sloped or benched excavations above other employees? 6 - Are the exact locations of Utilities (piping, electrical, etc.) clearly marked? 7 - Are underground installations protected, supported, or removed when an excavation is open? 8 - Are ladders or other means of access and egress in place as per the PTW requirements? 9 - Are all workers within 7.6 meters of a means of access and egress to a trench? 10 - Are ALL ramps constructed of materials of uniform thickness, cleated together, equipped with no-slip surfaces? 11 - Are employees protected from cave-ins when entering or exiting excavation? 12 - Are precautions taken to protect employees from water accumulation and dewatering is being carried out? 13 - Is surface water or runoff diverted after every rainstorm or other hazard-increasing occurrence? 14 - Is the excavation classified as a confined space? If so, is their a valid confined space PTW and is the atmosphere being tested when there is a reasonable possibility of an oxygen-deficient, oxygen-enriched, combustible, toxic, or other harmful contaminant? 15 - Have materials and/or equipment chosen for shoring been based upon soils analysis, trench depth and expected loads (as per Excavation PTW)? 16 - Are shoring materials and equipment that are used for protective systems inspected and in good condition? 17 - Are damaged shoring materials and equipment immediately removed from service? 18 - Are damaged shoring materials and equipment inspected by a Registered Professional Engineer after repairs are made and before being placed back in service? 19 - Are protective systems installed without exposing employees to hazards of cave-ins, collapses, or threat of being struck by materials or equipment? 20 - Are ALL members of support systems securely fastened together to prevent failure? 21 - Are support systems provided to insure stability of adjacent structures, buildings, roadways, sidewalks, etc.? 22 - Are excavations below the level of the base or footing supported, and approved by a Registered Professional Engineer? 23 - Does back-filling progress with the removal of the support system? 24 - Is a shield system installed to prevent lateral movement? 25 - Are employees prohibited from remaining in a shield system during vertical movement?
Note on C17: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Sites are to be kept clean and tidy and free from slip, trip and fall hazards. 2 - Do all personnel trained in the importance of good housekeeping, managers, supervisors undertake regular monitoring and inspection of the workplace? 3 - Workplace are to be left clean and tidy at the end of each shift and where there is an accumulation of materials throughout the shift, at regular intervals as required to maintain a clean and safe site. 4 - Buildings under construction and nearing completion must ensure that all combustible and flammable materials are removed at the end of each shift. 5 - Nails are to be removed from timber as soon as possible, where this is not practical they are to be flattened and placed in a safe area (barrier and signs) until nails can be removed at a later time. 6 - Materials are to be stored so as they do not pose a risk to personnel stacking, removing or walking by (further guidance is given in the materials storage and handling section). 7 - All spills are to be cleaned up immediately using absorbent material. 8 - Cables/hoses/other trailing leads are to be protected, buried or secured above head height to avoid a slip trip, fall hazard. 9 - Waste is to be placed in designated containers and covered to protect against high winds, pests or risk of fire. Waste containers are to be emptied on a regular basis to prevent a build-up of material. 10 - Loose or light materials that are stored on roofs or open spaces are to be secured to prevent them from inclement weather. Location: 1 - Receptacles located inside buildings shall be kept at least 18 inches away from combustible walls and partitions. 2 - Receptacles for combustible trash that are located outside of buildings shall be placed at least 15 feet from the building or combustible material. Use: 1 - Cigarettes, cigar butts, matches, and similar potential ignition sources should never be placed in a trash receptacle. Proper receptacles for such items should be provided in areas designated for smoking. 2 - Broken glass, empty jars, scrap metal, and similar construction material should never be placed in office trash containers. A roll-off bin or other appropriate container should be used to hold construction debris. Environmental: 1 - Container storage areas shall be kept clean and free of trash. Improper disposal of food waste can attract pests and vermin. Prevention methods that do not involve the use of toxic chemicals is the preferred method of pest control. 2 - Outdoor containers should be kept covered when not in use so as to avoid attracting pests and to prevent the entry of water. Dripping or leaking trash containers may violate local storm water quality discharge regulations. 3 - Promote recycling by contracting with a waste removal company that provides reuse as part of the waste processing or by providing segregated bins for the collection of office paper, aluminum cans, plastic bottles, and toner cartridges. Rinse empty cans and bottles of sugar-based soda so as not to attract ants and other pests. 4 - Proper lighting (indoor) or during Night Shift are provided. Accurately installed. No impairement or poor visibilty is generated. No shadow due to installation of lights are presents.
Note on T17: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Permit is taken for confined space entry and all recommended precautions are in place. 2 - Operatives are trained and fit for the specified job. 3 - Confined space is well ventilated by means of mechanical ventilation. (Exhaust fan, blowers, low velocity air hose etc.). 4 - Rescue system (Tripod with hoisting device, Rescue Harness etc.) in place and sufficient trained persons are available for the rescue operation. 5 - Safe access is available for rescue operation. (Manhole size - Min. 450 mm X 407 mm or 457 mm Dia.) 6 - Atmospheric monitoring conducted and confined space is safe to enter. Percentage of gas concentration will be monitored and recorded every 4 hrs. A. Oxygen percentage. (Permissible limit – 19.5% to 23.5%) B. Flammable gas or vapors.(Permissible limit - <10% of LFL) C. Carbon Monoxide. (Permissible limit - <50ppm) D. Hydrogen sulfide.(Permissible limit - <10ppm) E. Any other toxic gas or vapors. _______________________________ 7 - Minimum two persons shall be assigned to work in the confined space. One person will remain in the entrance at all times to monitor the work 8 - All persons shall wear safety harness, which should be connected to safety line from outside at all times. 9 - All electrical equipment & leads are free from damage and guards in place. 10 - All electrical tools & equipment are connected through ELCB. 11 - Compressed gas cylinders are kept outside the confined space. 12 - supervisor / Foreman will be available at all time to monitor the work and for the rescue operation. 13 - Tool box talk conducted for the entire team and they are well aware of the risks. 14 - Proper communication system is available in between persons inside and standby person. 15 - Trained First aider with first aid kit will be available when working in the confined space. 16 - Confined space entry register is available and shift records will be maintained. -
Note on C18: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Combustible: 1 - Ensure oily rags, combustible material and other flammable substances which may ignite are not accumulated and that they are removed without delay to the designated disposal / storage area. 2 - Combustible materials shall not be stored within 20 feet (6.1 meters) of compressed gas cylinders. 3 - Safety cans used for dispensing combustible liquids shall be kept at a point of use 4 - Storage rooms for combustible liquids must have explosion-proof light fixtures 5 - No flames - hot work or smoking is be permitted in combustible liquid storage areas. Flammable: 1 - Adequate training in the use and storage of flammable liquids is in place. 2 - Storage of Flammable liquids in accordance with NFPA approved flammable storage lockers or in low value structures at least 50 feet from any other structure. 3 - Do not store other combustible materials near flammable storage areas 4 - Bulk drums of flammable liquids must be grounded and bonded to containers during dispensing 5 - Portable containers of gasoline or diesel are not to exceed 5 gallons 6 - Safety cans used for dispensing flammable liquids shall be kept at a point of use 7 - Appropriate fire extinguishers are to be mounted within 75 feet of outside areas containing flammable liquids, and within 10 feet of any inside storage area for such materials. 8 - Storage rooms for flammable liquids must have explosion-proof light fixtures 9 - No flames - hot work or smoking is be permitted in flammable or combustible liquid storage areas. 10 - Flammable liquid transfer areas are to be separated from other operations by distance or by construction having proper fire resistance. 11 - When not in use flammable liquids shall be kept in covered containers. 12 - Flammable materials are considered hazardous and as such, material safety data sheets and appropriate hazard communication training for affected employees is required 13 - Maintain high levels of housekeeping, particularly with relations to flammable materials. 14 - Where flammable materials are handled in the course of work, safe work procedures must be prepared and documented with reference made to the Material Safety Data Sheets (MSDS‘s) for the materials concerned. 15 - All people handling, working with or in control of flammable substances must be properly trained and supervised (documentation to be maintained). 16 - Lead, dust, fumes and vapor constitute a major health hazard to workers. Hazardous Substances COSHH 1 - Under COSHH the risk presented by any hazardous substance assessed using hierarchy of control, stored, transported, created or disposed and usage at the workplace; > Very toxic or toxic: Substances that, in low quantities, cause death or acute or chronic damage to health when inhaled, swallowed or absorbed via the skin > Harmful: Substances that may cause death or acute or chronic damage to health when inhaled, swallowed or absorbed via the skin > Corrosive: Substances that may, on contact with living tissues, destroy them > inhalation into the lungs, when the substance is in the form of a gas, vapor, fume, mist, aerosol or dust > absorption through the skin or eyes by contact with a substance that can penetrate unbroken skin, or is absorbed through unprotected cuts or grazes > injection by contact with contaminated sharp objects or high-pressure equipment, e.g. water jetting > ingestion by swallowing particles of a hazardous substance resulting from hand-to- mouth transfer
Note on T18: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are regular and frequent fire safety inspections carried out? 2 - Have a sufficient number of fire marshals/evacuation officers been appointed? 3 - Are water supplies adequate? 4 - Does the building or site have a written fire procedure? 5 - Is there an effective permit to work system in operation for all hot work and other fire related work? 6 - Do all doors from areas from which a large number of people may have to escape open in the direction of travel? 7 - Do all emergency exit doors (i.e. doors not in normal use) have clear instructions displayed on how to open? 8 - Are all escape routes clear and unobstructed? 9 - Are all fire exit doors correctly signed? 10 - Is all fire fighting equipment immediately visible or correctly signed? 11 - Are all flammable and explosive substances adequately signed to indicate their presence and danger? 12 - Where necessary, is there a sufficient number of emergency lights to adequately illuminate all internal escape routes, exit doors and signs? 13 - Where automatic fire detection is deemed to be necessary is there an adequate number of detectors in the critical areas? 14 - Where the means of raising the alarm is by hand-operated devices, can the operation of one device be heard throughout the entire building or site? 15 - Is there an adequate number of fire extinguishers in the building? 16 - Is there firefighting equipment other than extinguishers in the building? 17 - Are all electrical circuits and fixed electrical installations examined and tested at an acceptable frequency? 18 - Is housekeeping to an acceptable standard? 19 - Have all staff been trained in fire procedures in the last twelve months? 20 - Are all fire drills adequately recorded?
Note on C19: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - General construction waste streams generated including; > Asphalt, cable, timber, paving, roof sheeting, tiles, plastic sheeting and brickwork. > Excess concrete, spoil material from excavations. > General waste, such as putrescible food scraps and packaging from workers. > General (food) waste, construction/concrete waste, hazardous waste, paper/cardboard and waste water/sewage. 2 - Are hazardous waste identified with hazardous Waste label. 3 - Containers are properly labeled in according to their contents. 4 - Container inspections are documented in writing using the Container Inspection Checklist. 5 - Weekly inspections logged into book using the Accumulation Area Inspection Log Sheet. “NO SMOKING OR OPEN FLAME” sign posted. 6 Disposal facilities identified, evaluated using the procedures. 7 - Disposal facility accepted waste and issue approval letter. 8 - Waste transfer/dispose tracked using Waste Tracking Form. 9 - Waste streams, such as asphalt and concrete, to be recycled should be segregated and separately stored. 10 - Spill Release Contingency: 1 - Prior to beginning operations, ensure that on-site spill response capabilities (containment and personal protective equipment) are consistent with task requirements described in job hazard analysis.
Note on T19: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: HHE is required at all locations where chemical hazards exist, such as; storing, transferring and handling facilities, under routine conditions. The HHE scope shall include the physical, chemical, radiological, and biological health hazards. Physical health hazards include elevated noise and vibration exposures, repetitive motion work operations, ionizing and non-ionizing radiation exposures heat and cold stress and biological hazards include infectious disease agents. HHE shall be performed before the site mobilization; 1 - Is the adequate eating or mess area is provided and sufficient for number of workers? 2 - Are sufficient tables and Chair are provide and Kept Clean? 3 - Are FEs, signs, pest control being implemented? 4 - Is washing Area sufficient and Kept Clean? 5- Cooking Area Kept Clean? 6 - L.P.G. Cylinder stored outside, secured & upright 7 - Sufficient drinking water provided. Filters changed (as per manufacturer recommendation)? 8 - Sufficient toilets, washbasins, cleaned/disinfectant provided? 9 - Provision of First Aider 10 - Provision of Nurse 11 - Provision of First Aid Kit 12 - Provision of site clinic with required first aid equipment and items. 13 - Provision of shaded area on the workplace 14 - Provision of Ambulance or an equal arrangement in place" 15 - Smoking area is Prohibited other than designated smoking areas, clear of flammable and combustible materials? 16 - All toilets, washing, rest and eating facilities to be kept clean, hygienic and be well maintained at all times? 17 - Waste Management - Covered bins, emptied daily, close proximity, color coded etc.? 18 - Are the monitoring, including integrated air sampling, noise dosimetry and other exposure assessments, being carried out? 19 - Are the Physical, chemical, and biological stresses, being identified, results are taken with action level to prevent sickness, impaired health, significant discomfort, or inefficiency in workers? 20 - Are WEL, LEL, OEL PEL & TLV linked to control workers airborne exposure to a chemical in a concentration above which is likely to cause death or immediate or delayed permanent adverse health effects or prevent escape from such an environment, if bening implemented?
Note on C20: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Is the hierarchy of Control is beng carried out on the following and recorded; 1 - Exposure to Chemical; e.g. - Dust, Gas, Mist, Vapor 2 - Exposure to Radiation; e.g. - Pipe radiography etc. 3 - Exposure to Biological Hazard; e.g. - Bloodborne pathogens / Legionella / Leptospirosis 4 - Exposure to noise; e.g. Loss of hearing / Physical damage to hearing mechanism 5 - Heat and cold stress work; e.g. - Heat-stroke, Heat stress / Frostbite / 6 - Repetitive Motion Work; e.g. - Musculoskeletal disorder, awkward position etc. 7 - Is the risk assessment carried out on the hazardous material and covering the following; > Allowable exposure limits, > Exposure monitoring requirements, > Methods of compliance for potential over exposure conditions, > Medical surveillance program, > Hazard communication, employee training requirements, 8- Is the IH Surveillance Plan should being implemented and have rocored on the following; > Which exposure groups require IH monitoring and medical surveillance > Specific substances or agents to be monitored, > The OELs to be used to evaluate results > The statistical basis to continue or cease monitoring > Specific medical testing/protocol to be implemented 9 - Do we've program on identifies work conditions such as the following, the exposure must first be mitigated or work shall not be performed. > Oxygen concentrations less than 19.5% or greater than 23.5%, or > Atmospheres greater than 1% of the Lower Explosive Limit, or > Atmospheres that are >50% of Immediately Dangerous to Life or Health (IDLH) concentrations, or > Work with sensitizers or known human carcinogens, mutagens, or teratogens without process isolation or fully encapsulating personal protection, or > Work with highly infectious biological agents without process isolation
Note on T20: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are all dispensing areas diked or properly graded to control drainage of spilled fuel? 2 - are all workers and operatives are trained to use spill response kit? 3 - Is the procedure in place for collecting and/or containing, and disposing of spilled materials? 4 - All tanks & vessels areas are diked to contain accidental spills?. 5 - Do measures taken to prevent an accidental contaminated runoff from construction , operation, maintenance, plant and storage areas? 6 - Do measures taken to control on deposits of oils, greases and fuels, from site plant and vehicle operations, mechanical failures, spillages and discharges to ground or drains and the dispersion of unattended spills by plant / vehicle movements?. 7 - Do measures taken to control on fuels, oils and other hazardous chemicals spilled on site during re-fueling, storage or transport operations?. 8 - Do we have an Emergency Response Procedure will be followed in the event of environmental emergency such as an oil or chemical spill? 9 - Is there a procedure for concrete wash, clean and dispose to prevent ground contamination, such as; Concrete wash pits with leak proof sedimentation tanks will be provided for washing concrete mixer trucks. The design and location of such wash pits shall be agreed with the Project Manager prior to its construction on site. Concrete dumping or spillages of any kind shall not be allowed in any other location on site? 10 - Is there a procedure to used in the situation of a major spills that will have an impact on the surrounding environment will be promptly reported to the Fire Brigade? 11 - Are there a procedure of disposing off any damage/leakage drums or containers shall be removed in accordance with the local requirements? 12 - Are there a procedure of dealing with spilled contaminated soils, resulted and remediated, accordingly? 13 - Are all personnel trained in the use of spill procedure and response and the adequate spill kits are available on site?
Note on C21: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - All electrical extension cords are equipped with nonconductive plugs 2 - Cords must not be spliced or draped over nails, metal objects 3 - The use of extension cords by means of multiple outlet plugs from single outlets is prohibited 4 - All electrical service removals, alterations and equipment installations are performed by an authorized electrician 5 - Faulty electrical installation 6 - Electrical supply disruption 7 - Exposed cables 8 - Trip / fall hazards from installed cables 9 - Fire hazard Electrical overload 10 - electrocution 11 - Electrical (short circuit) - Contact with exposed conductors or a device that is incorrectly or inadvertently grounded, such as when a metal ladder comes into contact with power lines 12 - Electrical - (static discharge) 13 - Electrical Fire - Use of electrical power that results in electrical overheating or arcing to the point of combustion or ignition of flammables, or electrical component damage 14 - Improper grounding 15 - Damaged insulation 16 - Exposed electrical parts 17 - Overloaded circuits 18 - Inadequate wiring 19 - Wet conditions 20 - Overhead power lines 21 - Damaged tools and equipment
Note on T21: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a meaningful and an effective consultation and communication on health and safety matters being implemented through out the project? 2 - Is the Consultation and communication on health and safety matters in place through the following mechanisms: > Project specific induction - (prior to commencement of contracted work) > Work activity Induction (in SWMS or equivalent) - (prior to commencement any construction work) > Toolbox Meetings - (Monthly intervals or generally when there is the introduction of a new process (SWMS) or when discussing OHS issues/topics). > Subcontractor Meetings - (weekly) > Project team meetings - (weekly) > HSE Committee Meeting - (as agreed with the HSE Committee) > OHS Report - (monthly) > Project Notice Board and general signage - (as required) 3 - Is there a method of communication is to be established in the work procedures to allow constant monitoring of those persons working in the confined space? 4 - Is there a material safety data sheets and appropriate hazard communication training for affected employees is in place? 5 - Are all environmental aspects and impacts been communicated to employees? 6 - Dose the notice
Note on C22: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1- Check that all the workers are using safe hand tools/power tools and instruct them to operate and maintain the same in safe manner 2 - Ensure power tools and hand tools are checked prior to issue 3 - Damaged tools and equipment 4 - Electrical tools or electrical equipment are not to be issued for use until inspected. 5 - Electrical tools or electrical equipment are not to be issued for use until inspected. 6 - "Defective" electrical tools and equipment are to be tagged and removed from service until repaired and inspected 7 - The frequency for inspection of construction electrical tools and electrical equipment shall be monthly and inspection indicated by attached color-coded tape or color- coded tie wraps and a color coded inspection tag with Contractor‘s name, the supervisor, the inspection date, equipment number and signature of competent inspector displayed on the tag. 8 - Checking the cords for worn or cracked insulation. 9 - Checking the cords entry to plug and tool housing for frayed or worn insulation and strain relief. 10 - Checking the plug prongs for damage. 11 - Checking the plug for exposed connectors 12 - Checking the equipment housing for damage. 13 - Checking trigger locks to ensure they have been removed 14 - Checking the leads for signs of wear, poor connections at probes, etc. 15 - Checking the housing and the readout window for cracks, loose screws, etc. 16 - Check all Ground Fault Circuit Interrupters (GFCI) during the monthly inspections. 17 - Machines are free from any defects / damage. 18 - Pressure switch and safety guards in place where applicable. 19 - Leads are fitted with correct plugs & sockets and free from damages. 20 - Leads wires are free from joints, cuts and other defects. 21 - Leads are suitably rated for the electric current. 22 - Machines / Tools are equipped with properly functioning dead man switch. 23 - Tools issue and maintenance record is properly maintained. 24 - Tools are correctly stored. 25 - Discarded Tools / cords are marked and stored separately.
Note on T22: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is the Project HSE Plan presents actions, responsibilities, protocol, conformance, verification and containment activities to be undertaken by project staff and sub-contractors at all times during the construction phase of the project. 2 - Is the implementation of the HSE plan is being monitored, evaluated for accuracy and any changes made communicated to all relevant personnel. 3 - Is the HSE Plan, CEMP, Security Plan, HAZcomm., standards & procedures are updated, signed, approved and distributed, acknowledged to the construction team's responsible individuals? 4 -Is the project overall safety risk register developed, approved and being implemented?
Note on C23: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Immediate Postural and Load Factor; 1- Is the body position stable? 2 - Is the trunk of the body straight (not twisted)? 3 - Is the operation carried out by one person? 4 - Is the load kept close to the body? 5 - Can the handler avoid stretching upwards? 6 - Can the handler avoid a prolonged period in one posture? 7 - Can the handler perform the task without overreaching? 8 - Are both hands used for grasping? 9 - Are the hands less than a shoulder width apart? 10 - Is the load positioned centrally in front of the body? 11 - Is the load reasonably symmetrical? 12 - Is the load stable and easy to grasp? 13 - Can handlers move and position themselves freely? Environmental Risk Factor; 1 - Too hot? 2 - Too cold? 3 - Too bright? 4 - Too dark? 5 - Too noisy to allow effective communication? 6 - Too wet? 7 - Slippery underfoot? 8 - Does any personal protective equipment interfere with the task? Carrying; 1 - Is the load carried at knuckle height? 2 - Is the load carried at arm's length from the body? 3 - Is the load carried for more than 10 meters? Seated Work; 1 - Is the load lifted from below thigh height? 2 - Is the load lifted to above shoulder height? 3 - Is the load lifted at arm's length from the body? 4 - Does the handler have to twist significantly to the side? 5 - Is the load heavier than 5kg? Pushing and Pulling; 1 - Does the pushing and pulling take place below knuckle height? 2 - Does the pushing and pulling take place above shoulder height? 3 - Is the initial or maximum force required to push or pull the load more than 25kg? 4 - Is the continuous force required to keep the load in motion more than 10kg?
Note on T23: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a system of proper HSE reporting in place, such as; all work-related incidents including near misses, injuries, illnesses, property damage, environmental incidents, security events and motor vehicle incidents, using proper protocol followed? 2 - Is the HSE incidents, accident, near misses, unsafe acts/conditions and dangerous occurrences are being reporting in timely manner and in the approved company format? 3 - Are the workers informed, trained in reporting all near misses, unsafe acts/conditions to the appropriate authority or line of manager? 4 - Is the Weekly / Monthly HSE Statistics data, including (leading & lagging) indicators, reviewed by the senior management?
Note on C24: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: CHECKS; 1 - Plant guarding is in place and in good condition to prevent injury from parts disintegrating or failing 2 - Access and egress is in good condition, hand holds, ladder etc. are sound and in place 3 - Operator's seat and controls are in good condition and all safety devices (limiters and indicators) are labelled and fully operational. 4 - Operator's manual / instructions supplied by the manufacturer of the plant are available in the plant. 5 - Hazards with the use of the plant are identified, i.e. Safe working limits on batters, operator safety instructions etc., are displayed clearly in the cabin of the plant for operator reference. I.E. PLANT SPECIFIC RISK ASSESSMENT. 6 - Hazard controls, i.e. seat belts must be worn and hearing protection must be worn, caution/danger signs (counter weight slewing area, excavators and cranes) etc. are displayed in the cabin or on the plant in a position relevant to the hazard. 7 - Operator cabin/work platform access is clean and free of debris, loose tools, equipment, grease oil and is in an orderly condition. 8 - Plant is clean and free from oil leaks and oil build up. 9 - Plant Pre Start inspection is complete and a record of the inspection will be provided at commencement on the site. 10 - Certification of operator / proof of competency. 11 - Operational Noise Level - Statement of conforming emission level. 12 - Plant has no areas of excessive wear or damage. Mobile plant required to have; 1 - Plant is fitted with a Roll Over Protection Structure (R.O.P.S.) and operator restraint. 2 - Plant is fitted with a front horn and reversing beeper. 3 - Plant is fitted with a rotating or flashing amber beacon. Plant used to lift Material and equipment; Backhoes, excavators, cranes and loaders used as crane from designed lifting points. The Safe Working Load of the plant item is displayed on the plant as: EITHER; A Crane Chart supplied by the manufacturer specific to the plant item in the cabin of the plant for operator reference OR; The Safe Working Load of the equipment on the boom of the loader bucket and of the dipper arm of excavators - a combination of both is required for backhoes e.g. SWL 1.2ton. Personal Lifting Equipment - (Cherry Pickers, boom lift and elevated platform) 1 - Safety Working Load is displayed on work bucket / platform. 2 - Fully body harnesses and lanyards are to be provided for personnel using the equipment. 3 - Safety Instruction for the operation of the equipment is clearly displayed in the work bucket / platform. 4 - The supplier have provided training for personnel using the platform in the safe use of the equipment
Note on T24: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Do all personnel have the correct information, instruction and training according to their role and responsibilities? 2 - Is the contractor promoting awareness of company standards and regulations among their employees on a regular basis, or when it is necessary? 3 - Do all personnel have completed basic relevant awareness training, such as; Fire Awareness Training, Heat Stress awareness Training, Safety Signs and Color Code awareness Training, Environmental Awareness Training, Using Fire Extinguisher Awareness Training, Emergency reporting Awareness Training, Unsafe Act/Conditions reporting awareness training, Evacuation Procedure Awareness Training?
Note on C25: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Crane Inspected 2 - Operator certified 3 - Lift Plan approved 4 - PTW obtained 5 - lifting equipment is suitable for the use it is being put to, marked with safe working load, properly maintained and inspected, and receives a periodic thorough examination. 6 - Are all members of the lifting operations team including the Appointed Person, Crane Drivers and Slingers / Signalers / Banksmen will be competent and have such practical and theoretical knowledge and experience as is necessary to carry out their duties. 7 - Bank man is available and certified 8 - The crane operator have a practical and theoretical knowledge of lifting operations 9 - Lifting operations will be undertaken by a minimum of three competent people the crane operator, slinger / signaler (slinger and signaler can be one person) / banks man / flagman (banks man and flagmen can be one person) and Supervisor 10 - Certification of Lifting Equipment / Lifting Gear / Lifting Devices 11 - Lifting plan prepared/approved/communicated 12 - Lifting gear (Chain sling, shackle, webbing sling, lifting clamps etc.) / devices (Chain block, Winch, Monorail etc.) are checked, inspected & tagged - ( size, length, dia, width, SWL,Condition & defects. 13 - All lifting equipment / gears have valid test certificates and are in good condition.
Note on T25: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there process of SBO for leadership to identify and reinforce safe work practices/behaviors? 2 - Is there process of SBO for leadership to identify and improve on at-risk practices? 3 - Is there process of SBO for leadership to identify and improve on practices, conditions, controls, and compliance that eliminate or reduce hazards? 4 - Is there a process of SBO for leadership to make positive, corrective, cooperative, collaborative feedback/recommendations? 5 - Is there a training program for BBST, that how to identify critical safety behavior and how to provide feedback and the number of personnel trained. 6 - Is there a program for the leadership to carry out SBO once a month or twice (depends project scope of work), and record available?

## Quality
QC OBSERVATIONS CHECKLIST
32
2026-03-03
Project No. |  |  | MLTX-02-004 |  |  | OBS No. |  |  |  | 24 |  |  | Inspection Day: |  | 2026-10-12
Project |  |  | Playground Initiative for Western Region (Jeddah-Asir-Jazan) ) | [6 empty] | Contractor: Consultant: |  |  | Profast Company Ltd. EGIS SAUDI ARABIA ENGINEERING COSULTANCY
4 |  | Excellent |  | Quality Management System is being practiced and applies to MODON System | [11 empty] | 90 - 100 |  | QC Overall Score | 85.71% |  |  |  |  | 0% | 100 | 0.22883
3 |  | Good |  | Evidence of compliance with plans and procedures. | [11 empty] | 80 - 89 | [7 empty] | 0 | 89 | 0.20366
2 |  | Average |  | Indication level of compliance with standards but there is room for improvement | [11 empty] | 70 - 79 | [8 empty] | 79 | 0.18078
1 |  | Improve |  | Quality and Control is NOT being managed effectively. Needs Improvement | [11 empty] | ≤ 69 | [8 empty] | 69 | 0.15789
0 |  | N/A |  | Item was not applicable or this item was not reviewed during the inspection. | [11 empty] | Zero | [8 empty] | 100 | 0.22883
No. | Topic |  |  |  |  | E (4) | G (3) | A (2) | I (1) | N/A (0) | No. | Topic |  |  |  | E (4) | G (3) | A (2) | I (1) | N/A (0) |  |  |  |  | 437
[6 empty] | 100% | 89% | 79% | 69% | 100% | [5 empty] | 100% | 89% | 79% | 69% | 100% | 85.71%
1 | Control of Access to Site/Office |  |  |  |  | 1 |  |  |  |  | 30 | QC of Excavation |  |  |  |  | 1 |  |  |  | 1 | 0.89 | [6 empty] | Item Count | Score | Distributtion
2 | Document Control Administration | [5 empty] | 1 |  |  |  | 31 | QC of Roads/Round about | [5 empty] | 1 |  |  | 0.89 | 0.79 | [8 empty] | Overall | Relevant
3 | Project Documents and Progress | [6 empty] | 1 |  |  | 32 | QC of Interlock & Curbstone | [5 empty] | 1 |  |  | 0.79 | 0.79 | 4 | 58 | counts |  | 4 | Excellent | 1 | 4 | 1.724% | 2%
4 | Contractor's Quality Plan/CM (Updated and Reviewed) | [5 empty] | 1 |  |  |  | 33 | Layers/Backfilling Sampling |  |  |  |  | 1 |  |  |  | 0.89 | 0.89 | 3 | 58 | counts |  | 3 | Good | 27 | 81 | 46.55% | 54%
5 | MS Log and Paperwork | [6 empty] | 1 |  |  | 34 | Pump Stations Units |  |  |  |  | 1 |  |  |  | 0.79 | 0.89 | 2 | 58 | counts |  | 2 | Average | 15 | 30 | 25.86% | 30% |  | NB: Insert 1, or 0 in the required cell only.
6 | RFI, FIR, & MIR Procedure | [5 empty] | 1 |  |  |  | 35 | Quality of Form Work |  |  |  |  | 1 |  |  |  | 0.89 | 0.89 | 1 | 58 | counts |  | 1 | Improve | 7 | 7 | 12.07% | 14%
7 | RFI, FIR, & MIR Inventory system | [5 empty] | 1 |  |  |  | 36 | Design Change List | [5 empty] | 1 |  |  | 0.89 | 0.79 | 0 | 58 | counts |  | 0 | N/A | 8 | 0 | 13.79% | -
8 | NCRs Control & Procedure | [5 empty] | 1 |  |  |  | 37 | Quality of Concrete Placing |  |  |  |  | 1 |  |  |  | 0.89 | 0.89 | [5 empty] | Total | 58 | 122 | 100% | 100%
9 | NCR Log | [5 empty] | 1 |  |  |  | 38 | Concrete Surface Finishing |  |  |  |  | 1 |  |  |  | 0.89 | 0.89
10 | MODON Standard* | [5 empty] | 1 |  |  |  | 39 | Pedestals/Columns/Beams Alignment |  |  |  |  | 1 |  |  |  | 0.89 | 0.89 | [6 empty] | Maz Score Available: | 200 | <- Excludes N/A items
11 | Project Risk Plan/Management* | [6 empty] | 1 |  |  | 40 | Siporex Lifting & Unloading |  |  |  |  | 1 |  |  |  | 0.79 | 0.89
12 | Monthly Quality Reports* | [5 empty] | 1 |  |  |  | 41 | Siporex Quality Pre-installation |  |  |  |  | 1 |  |  |  | 0.89 | 0.89
13 | ITP | [5 empty] | 1 |  |  |  | 42 | Siporex Finishing Quality |  |  |  |  | 1 |  |  |  | 0.89 | 0.89 | [5 empty] | Total Score |  | Percentage (%)
14 | MODON Weekly Report | [5 empty] | 1 |  |  |  | 43 | Roads / Parking Markings | [7 empty] | 1 | 0.89 | 1 |  | 58 |  |  |  | 122 |  | 61 |  | %
15 | Design Change Official Paperwork* | [6 empty] | 1 |  |  | 44 | QC of Finishing Outdoors | [7 empty] | 1 | 0.79 | 1 | [5 empty] | Max Score Available | [6 empty] | 31
16 | Design Change was Applied* | [7 empty] | 1 |  | 45 | Quality of Finishing Indoors |  |  |  |  | 1 |  |  |  | 0.69 | 0.89 | [5 empty] | 200 | [6 empty] | 32
17 | Material List | [5 empty] | 1 |  |  |  | 46 | Stairs Quality | [6 empty] | 1 |  | 0.89 | 0.69 | [12 empty] | 33
18 | Pending Material Status | [6 empty] | 1 |  |  | 47 | Tanks Method Statement Work | [5 empty] | 1 |  |  | 0.79 | 0.79 | [12 empty] | 34
19 | Lifting Plan* | [8 empty] | 1 | 48 | Electric Rooms | [7 empty] | 1 | 1 | 1 | [12 empty] | 35
20 | DWG Log | [6 empty] | 1 |  |  | 49 | QC of MCC/ATS Plant Units | [7 empty] | 1 | 0.79 | 1 | [12 empty] | 36
21 | Invoice Status | [6 empty] | 1 |  |  | 50 | Qualified Subcontractor | [6 empty] | 1 |  | 0.79 | 0.69 | [12 empty] | 37
22 | Site Handover Letter | [7 empty] | 1 |  | 51 | Scaffold/Ladders/Slope/Bridge Compliance | [7 empty] | 1 | 0.69 | 1 | [12 empty] | 38
23 | Material Testing Results & Certification | [5 empty] | 1 |  |  |  | 52 | Protection Applied to Completed Work | [7 empty] | 1 | 0.89 | 1
24 | As Build Drawings Status* | [7 empty] | 1 |  | 53 | Storage Management in/out Control | [6 empty] | 1 |  | 0.69 | 0.69
25 | Calibrated Lab Tools & Equipment | [6 empty] | 1 |  |  | 54 | Material Control |  |  |  |  | 1 |  |  |  | 0.79 | 0.89
26 | Storage Inventory System | [6 empty] | 1 |  |  | 55 | Manholes Storing and Quality | [7 empty] | 1 | 0.79 | 1
27 | Logistics Plan | [6 empty] | 1 |  |  | 56 | Reinforced Steel Quality |  |  |  |  | 1 |  |  |  | 0.79 | 0.89
28 | Project Progress Planview | [6 empty] | 1 |  |  | 57 | Safety Overview |  |  |  |  | 1 |  |  |  | 0.79 | 0.89
29 | Sufficient Number of QC Inspectors | [5 empty] | 1 |  |  |  | 58 | Waste Management Control | [6 empty] | 1 |  | 0.89 | 0.69
Score
[8 empty] | *QC % |  |  | 85.71%
Prepared by: |  |  |  | Eng: Mahfouz Zaki | [6 empty] | Issued to PM: |  |  | Engr. Abdallah Aljulaifi
*QC Observations refer only to the practices and documentation observed at time of inspection. The responsibility of the CM and Contractor is to ensure that aspects of Quality are suitably managed. *Scores are a reflection of the general site conditions based upon the findings at the time of the walk through *If Applicable

## Quality-Stat
Quality Reports
Item |  |  | Issued | Closed | Pending | Avg. Closing (Days) | Pending
[7 empty] | 0-10 Days | 11-20 Days | 21-30 Days | 31-60 Days | > 60 Days
Non Conforomance Report (NCR) |  |  | 19 | 19 | 0 | 0 | 2 | 0 | 0 | 0 | 0
Site Instruction (SIR/SOR) |  |  | 25 | 24 | 1 | 0 |  | 3 | 0 | 0 | 0
Material Inspection Report (MRIR) |  |  | 96 | 93 | 3 | 0 | 11 | 0 | 0 | 0 | 0
Field Inspection Report (FIR) |  |  | 605 | 580 | 24 | 0 | 46 | 0 | 0 | 0 | 0
Shop Drawings
Item Per WBS |  |  | Total Planned | Total Drawings Submitted |  |  |  |  | Remaining Drawings | Pending | Total Submittals
|  |  |  | A | B | C | D | Processed | with Designer | Submittals With Consultant
Civil/Structure |  |  | 36 | 7 | 24 | 2 | 3 | 36 | 0 | 2 | 38 | 100% | 105.6% | 36 | 7 | 24 | 2 | 3 | 36 | 3 | 2
Architecture |  |  | 20 | 3 | 14 | 2 | 0 | 19 | 1 | 0 | 19 | 95% | 95% | 45 | 3 | 33 | 6 | 0 | 42 | 3 | 2
Mechanical |  |  | 25 | 0 | 19 | 4 | 0 | 23 | 2 | 2 | 25 | 92% |  | 38 | 0 | 34 | 0 | 3 | 37 | 1 | 0
Electrical |  |  | 38 | 0 | 34 | 0 | 3 | 37 | 1 | 0 | 37 | 97.37% | 97.37% | 25 | 7 | 14 | 2 | 0 | 23 | 2 | 0
Landscape |  |  | 25 | 7 | 14 | 2 | 0 | 23 | 2 | 0 | 23 | 92% | 92% | 142 | 4 | 125 | 11 | 3 | 129 | 13 | 1
TOTAL |  |  | 144 | 17 | 105 | 10 | 6 | 138 | 6 | 4 | 142 | 95.83% | 98.61%
Material Approval
Item Per WBS |  |  | Total Planned | Total Materials Submitted |  |  |  |  | Remaining | Pending | Total Submittals
|  |  |  | A | B | C | D | Approved | with Designer | Submittals With Consultant
Civil/Structure |  |  | 48 | 2 | 40 | 5 | 2 | 42 | 6 | 0 | 49
Architecture |  |  | 26 | 2 | 24 | 0 | 0 | 26 | 0 | 0 | 26
Mechanical |  |  | 32 | 0 | 30 | 2 |  | 30 | 2 | 0 | 32
Electrical |  |  | 36 | 0 | 31 | 4 | 1 | 31 | 5 | 1 | 37
|  |  | 0 |  |  |  |  | 0 | 0 |  | 0
TOTAL |  |  | 142 | 4 | 125 | 11 | 3 | 129 | 13 | 1 | 144 |  | 101.4%
Procurement Summary
Item Per WBS |  |  | Total Materials Planned | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Actual Material on Site | Remaining Materials | Material Delivery Completion (Date)
|  |  |  | A | B | C | D | Processed
Civil/Structure |  |  | 48 | 27 | 5 | 22 | 5 | 22
Architecture |  |  | 25 | 18 | 14 | 4 | 7 | 11
Mechanical |  |  | 32 | 18 | 10 | 8 | 7 | 11
Electrical |  |  | 36 | 13 | 6 | 7 | 3 | 10
|  |  |  | 0 | 0 | 0 | 0 | 0
TOTAL |  |  | 141 | 76 | 35 | 41 | 22 | 54 | 0
Consultant Quality Inspections / Observations (Weekly Basis) | [7 empty] | Overall Average | 85.84% |  | Average Closing | 0
Week Number | Date of Audit | Date Issued | Numbers Of Comments | Quality Score | Date Closed | Closure Duration |  | This Week Score | 85.71% |  | Average Number of Comments Per Audit | 0
Week-1 | 2026-06-07 | 2026-06-14 | 0 | 85.14% | 2026-06-15 | 0
Week-2 | 2026-06-14 | 2026-06-21 | 0 | 92.03% | 2026-06-21 | 0
Week-3 | 2026-06-21 | 2026-06-29 | 0 | 85.12% | 2026-06-29 | 0
Week-4 | 2026-06-29 | 2026-07-06 | 0 | 83.93% | 2026-07-06 | 0
Week-5 | 2026-07-06 | 2026-07-13 | 0 | 85.36% | 2026-07-13 | 0
Week-6 | 2026-07-13 | 2026-07-20 | 0 | 85.36% | 2026-07-20 | 0
Week-7 | 2026-07-20 | 2026-07-27 | 0 | 85.36% | 2026-07-27 | 0
Week-8 | 2026-07-27 | 2026-08-03 | 0 | 85.53% | 2026-08-03 | 0
Week-9 | 2026-08-03 | 2026-08-10 | 0 | 85.71% | 2026-08-10 | 0
Week-10 | 2026-08-10 | 2026-08-17 | 0 | 85.71% | 2026-08-17 | 0
Week-11 | 2026-08-17 | 2026-08-24 | 0 | 85.71% | 2026-08-24 | 0
Week-12 | 2026-08-24 | 2026-08-30 | 0 | 85.71% | 2026-08-30 | 0
Week-13 | 2026-08-31 | 2026-09-07 | 0 | 85.71% | 2026-09-07 | 0
Week-14 | 2026-09-07 | 2026-09-14 | 0 | 85.71% | 2026-09-14 | 0
Week-15 | 2026-09-14 | 2026-09-21 | 0 | 85.71% | 2026-09-21 | 0
Week-16 | 2026-09-21 | 2026-09-28 | 0 | 85.71% | 2026-09-28 | 0
Week-17 | 2026-09-28 | 2026-10-05 | 0 | 85.71% | 2026-10-05 | 0
Week-18
Week-19
Week-20
Week-21
Week-22
Week-23
Week-24
Week-25
Week-26
Week-27
Week-28
Week-29
Week-30
Week-31
Week-32
Week-33
Week-34
Week-35
Week-36
Week-37
Week-38
Week-39
Week-40
Week-41
Week-42
Week-43
Week-44
Week-45
Week-46
Week-47
Week-48
Week-49
Week-50
Week-51
Week-52
Week-53
Week-54
Week-55
Week-56
Week-57
Week-58
Week-59
Week-60
Week-61
Week-62
Week-63
Week-64
Week-65
Week-66
Week-67
Week-68
Week-69
Week-70
Week-71
Week-72
Week-73
Week-74
Week-75
Formulas:
Remaining Drawings = MAX(J33:[Remaining Drawings, row above])
Note on A40: Malik, Muhammad: This refers to quality observation sheet

## Invoice Ammount FIR
33997786.875
SL. | date of FIR | TOTAL AMOUNT | Cum. TOTAL AMOUNT | Total Amount % (as per FIR) | Cum. Total Amount % (as per FIR) |  | التاريخ | رقم البند | الكمية | السعر
1 | 2026-05-11 | 526329.375 | 526329.375 | 1.548% | 1.548% |  |  |  | 8305 | 63.375 | حفر موقع جدة | 1
2 | 2026-05-18 | 332465.25 | 858794.625 | 0.9779% | 2.526% |  |  |  | 5246 | 63.375 | حفر موقع عسير | 2
3 | 2026-06-06 | 1887.1125 | 860681.7375 | 0.005551% | 2.532% |  |  |  | 38.71 | 48.75 | Anti termite Asir | 3
4 | 2026-06-06 | 1513.2 | 862194.9375 | 0.004451% | 2.536% |  |  |  | 1.94 | 780 | Lean Concrete Asir | 4
5 | 2026-06-06 | 943.5562 | 863138.4938 | 0.002775% | 2.539% |  |  |  | 38.71 | 24.375 | Polyethylene Asir | 5
6 | 2026-06-07 | 6205.6312 | 869344.125 | 0.01825% | 2.557% |  |  |  | 181.85 | 34.125 | ردم موقع عسير | 6
7 | 2026-06-07 | 659.9775 | 870004.1025 | 0.001941% | 2.559% |  |  |  | 19.34 | 34.125 | ردم موقع عسير | 7
8 | 2026-06-08 | 2720.1037 | 872724.2063 | 0.008001% | 2.567% |  |  |  | 79.71 | 34.125 | ردم موقع عسير | 8
9 | 2026-06-08 | 24084.7425 | 896808.9488 | 0.07084% | 2.638% |  |  |  | 705.78 | 34.125 | ردم موقع عسير | 9
10 | 2026-06-10 | 792.0412 | 897600.99 | 0.00233% | 2.64% |  |  |  | 23.21 | 34.125 | ردم موقع جازان | 10
11 | 2026-06-10 | 202.7025 | 897803.6925 | 0.0005962% | 2.641% |  |  |  | 5.94 | 34.125 | ردم موقع جازان | 11
12 | 2026-06-11 | 923.7637 | 898727.4563 | 0.002717% | 2.643% |  |  |  | 27.07 | 34.125 | ردم موقع جازن | 12
13 | 2026-06-11 | 792.0412 | 899519.4975 | 0.00233% | 2.646% |  |  |  | 23.21 | 34.125 | ردم موقع جازن | 13
14 | 2026-06-13 | 208452.3187 | 1107971.8163 | 0.6131% | 3.259% |  |  |  | 8551.89 | 24.375 | ردم موقع جدة | 14
15 | 2026-06-07 | 659.9775 | 1108631.7938 | 0.001941% | 3.261% |  |  |  | 19.34 | 34.125 | ردم موقع عسير | 15
16 | 13/6/2026 | 159.3638 | 1108791.1575 | 0.0004687% | 3.261% |  |  | 2-1-2 | 4.67 | 34.125 | ردم موقع عسير | 16
17 | 16/6/2026 | 35439.3 | 1144230.4575 | 0.1042% | 3.366% |  |  | 3-2-1 | 13.98 | 2535 | خرسانه مسلحة موقع عسير | 17
18 | 17/6/2026 | 57657.6 | 1201888.0575 | 0.1696% | 3.535% |  |  | 3-3 | 26.88 | 2145 | خرسانه مسلحة موقع عسير | 18
19 | 18/6/2026 | 1323 | 1203211.0575 | 0.003891% | 3.539% |  |  | 15-3-1-1 | 21 | 63 | upvc موقع عسير | 19
20 | 18/6/2026 | 507 | 1203718.0575 | 0.001491% | 3.541% |  |  | 15-3-1-2 | 13 | 39 | upvc موقع عسير | 20
21 | 20/6/2026 | 840 | 1204558.0575 | 0.002471% | 3.543% |  |  | 15-3-1-3 | 14 | 60 | upvc موقع عسير | 21
22 | 20/6/2026 | 38001.6 | 1242559.6575 | 0.1118% | 3.655% |  |  | 3-2-2 | 13.92 | 2730 | حدادة موقع عسير | 22
23 | 21/6/2026 | 127.6275 | 1242687.285 | 0.0003754% | 3.655% |  |  | 2-1-2 | 3.74 | 34.125 | ردم موقع عسير | 23
24 | 22/6/2026 | 10857.6 | 1253544.885 | 0.03194% | 3.687% |  |  |  | 13.92 | 780 | خرسانه مسلحة موقع عسير | 24
25 | 22/6/2026 | 1419.6 | 1254964.485 | 0.004176% | 3.691% |  |  | 3-1-1 | 1.82 | 780 | خرسانه عادية موقع عسير | 25
26 | 22/6/2026 | 889.2 | 1255853.685 | 0.002615% | 3.694% |  |  | 7-2 | 18.24 | 48.75 | Anti termite Asir | 26
27 | 22/6/2026 | 1158.3 | 1257011.985 | 0.003407% | 3.697% |  |  | 7-5 | 23.76 | 48.75 | jazan membrane | 27
28 | 22/6/2026 | 444.6 | 1257456.585 | 0.001308% | 3.699% |  |  | 7-1 | 18.24 | 24.375 | Polyethylene Asir | 28
29 | 23/6/2026 | 1323 | 1258779.585 | 0.003891% | 3.703% |  |  | 15-3-1-1 | 21 | 63 | Ø4 upvc موقع جازان | 29
30 | 23/6/2026 | 507 | 1259286.585 | 0.001491% | 3.704% |  |  | 15-3-1-2 | 13 | 39 | Ø3 upvc موقع جازان | 30
31 | 23/6/2026 | 840 | 1260126.585 | 0.002471% | 3.706% |  |  | 15-3-1-3 | 14 | 60 | Ø2 upvc موقع جازان | 31
32 |  | 3930.1762 | 1264056.7613 | 0.01156% | 3.718% |  |  | 2-1-2 | 115.17 | 34.125 | ردم موقع جازان | 32
33 |  | 20966.4 | 1285023.1613 | 0.06167% | 3.78% |  |  | 3-3 | 26.88 | 780 | خرسانة مسلحة قواعد حمامات عسير | 33
34 |  | 265902 | 1550925.1613 | 0.7821% | 4.562% |  |  | 2-1-2 | 15584 | 17.0625 | ردم صخري موقع جدة | 34
35 |  | 8891.61 | 1559816.7713 | 0.02615% | 4.588% |  |  | 2-1-2 | 260.56 | 34.125 | ردم موقع جازان | 35
36 |  | 18074.55 | 1577891.3213 | 0.05316% | 4.641% |  |  | 3-2-1 | 7.13 | 2535 | خرسانة مسلحة SEPTIC TANK جازن | 36
37 |  | 57657.6 | 1635548.9213 | 0.1696% | 4.811% |  |  | 3-3 | 26.88 | 2145 | خرسانه مسلحه قواعد حمامات جازان | 37
38 |  | 1419.6 | 1636968.5213 | 0.004176% | 4.815% |  |  | 3.1.1 | 1.82 | 780 | خرسانة عادية grp asir | 38
39 | 24-6-2026 | 3930.1762 | 1640898.6975 | 0.01156% | 4.826% |  |  | 2.1.2 | 115.17 | 34.125 | ردم موقع جازان | 39
40 | 27-6-2026 | 30654 | 1671552.6975 | 0.09016% | 4.917% |  |  | 3.2.3 | 10.48 | 2925 | خرسانة مسلحة septic tank عسير | 40
41 | 28-6-2026 | 8891.61 | 1680444.3075 | 0.02615% | 4.943% |  |  | 2.1.2 | 260.56 | 34.125 | ردم موقع جازان | 41
42 | 28-6-2026 | 265902 | 1946346.3075 | 0.7821% | 5.725% |  |  | 2.1.2 | 15584 | 17.0625 | الردم الصخري موقع جدة | 42
43 | 30-6-2026 | 18074.55 | 1964420.8575 | 0.05316% | 5.778% |  |  | 3.2.1 | 7.13 | 2535 | خرسانة مسلحة خزان جازان | 43
44 | 2026-07-02 | 16781.7 | 1981202.5575 | 0.04936% | 5.827% |  |  | 3.2.1 | 6.62 | 2535 | خرسانة مسلحة grp tank موقع عسير | 44
45 | 2026-07-04 | 57657.6 | 2038860.1575 | 0.1696% | 5.997% |  |  | 3.3 | 26.88 | 2145 | خرسانة مسلحة مبني الحمامات جازان | 45
46 | 2026-07-05 | 101080.6388 | 2139940.7963 | 0.2973% | 6.294% |  |  | 2.1.2 | 2962.07 | 34.125 | ردم a1a موقع جدة | 46
47 | 2026-07-06 | 0 | 2139940.7963 | 0% | 6.294% |  |  | 2.3.9 | 1 |  | رش النمل موقع عسير | 47
48 | 2026-07-06 | 0 | 2139940.7963 | 0% | 6.294% |  |  | 2.3.9 | 1 |  | بولي اثلين شيت 250 ميكرون عسير | 48
49 | 2026-07-08 | 55342.2188 | 2195283.015 | 0.1628% | 6.457% |  |  | 2.1.1 | 873.25 | 63.375 | حفر اللممشي موقع عسر | 49
50 | 22-7-2026 | 14888.25 | 2210171.265 | 0.04379% | 6.501% |  |  | 7-6 | 101.8 | 146.25 | دهان ايبوكسي موقع عسير | 50
51 | 7-7-20026 | 31449.6 | 2241620.865 | 0.0925% | 6.593% |  |  | 3.2.2 | 11.52 | 2730 | صب حوائط الخزان جازان | 51
52 | 13-7-2026 | 14434.875 | 2256055.74 | 0.04246% | 6.636% |  |  | 2.1.2 | 423 | 34.125 | ردم a1a موقع جدة | 52
53 | 13-7-2026 | 799.2075 | 2256854.9475 | 0.002351% | 6.638% |  |  | 2.1.2 | 23.42 | 34.125 | ردم a1a موقع جدة | 53
54 | 14-7-2026 | 21469.5 | 2278324.4475 | 0.06315% | 6.701% |  |  | 3.2.3 | 7.34 | 2925 | صب خرسانة سقف الخزان جازان | 54
55 | 19-7-2026 | 3918.0375 | 2282242.485 | 0.01152% | 6.713% |  |  | 7.2 | 80.37 | 48.75 | رش النمل مبني الحمامات موقع جدة | 55
56 | 19-7-2026 | 1959.0188 | 2284201.5038 | 0.005762% | 6.719% |  |  | 7.1 | 80.37 | 24.375 | بولي اثيلين شيت مبني الحمامات جدة | 56
57 | 19-7-2026 | 3135.6 | 2287337.1038 | 0.009223% | 6.728% |  |  | 3.1.1 | 4.02 | 780 | خرسانة عادية مبني الحمامات جدة | 57
58 | 21-7-2026 | 20411.625 | 2307748.7288 | 0.06004% | 6.788% |  |  | 7-5 | 83.74 | 243.75 | ممبرين موقع جازان الخزان | 58
59 | 25-6-2026 | 0 | 2307748.7288 | 0% | 6.788% | [5 empty] | خرسان | 59
60 | 25-7-2026 | 74420.775 | 2382169.5038 | 0.2189% | 7.007% |  |  | 3-4 | 231.3 | 321.75 | السيبوركس aac panel عسير | 60
61 | 25-7-2026 | 35842.95 | 2418012.4538 | 0.1054% | 7.112% |  |  | 3.3 | 16.71 | 2145 | خرسانه مسلحه مبني الحمامات جدة | 61
62 | 25-7-2026 | 0 | 2418012.4538 | 0% | 7.112% | [6 empty] | 62
63 | 26-7-2026 | 5118.75 | 2423131.2038 | 0.01506% | 7.127% |  |  | 15.3.1.1 | 21 | 243.75 | Ø4 upvc مواسير موقع جدة | 63
64 | 26-7-2026 | 11029.2 | 2434160.4038 | 0.03244% | 7.16% |  |  | 4-1-1 | 40.4 | 273 | عسير cmu wall 10 mm | 64
65 | 26-7-2026 | 2408.25 | 2436568.6538 | 0.007084% | 7.167% |  |  | 15.3.1.2 | 13 | 185.25 | Ø3 upvc مواسير موقع جدة | 65
66 | 26-7-2026 | 1774.5 | 2438343.1538 | 0.005219% | 7.172% |  |  | 15.3.1.3 | 14 | 126.75 | Ø2 upvc مواسير موقع جدة | 66
67 | 27-7-2026 | 74420.775 | 2512763.9288 | 0.2189% | 7.391% |  |  | 3-4 | 231.3 | 321.75 | جازان - السيبوركس | 67
68 | 27-7-2026 | 31951.5787 | 2544715.5075 | 0.09398% | 7.485% |  |  | 2.1.2 | 936.31 | 34.125 | ردم موقع جدة a1a | 68
69 | 28-7-22026 | 72976.3125 | 2617691.82 | 0.2147% | 7.7% |  |  | 2.3.1.6 | 427.7 | 170.625 | backfilling a1a jeddah | 69
70 | 28-7-2026 | 72925.125 | 2690616.945 | 0.2145% | 7.914% |  |  | 2.1.2 | 2137 | 34.125 | ردم موقع جدة a1a | 70
71 | 2027-08-01 | 21482.0288 | 2712098.9738 | 0.06319% | 7.977% |  |  | 2.1.2 | 629.51 | 34.125 | ردم موقع جازان | 71
72 | 2026-08-01 | 20131.3612 | 2732230.335 | 0.05921% | 8.036% |  |  | 2.1.2 | 589.93 | 34.125 | ردم موقع جازان | 72
73 | 2026-08-02 | 74420.775 | 2806651.11 | 0.2189% | 8.255% |  |  | 3-4 | 231.3 | 321.75 | سيبوركس جده - acc panel | 73
74 | 2026-08-04 | 11029.2 | 2817680.31 | 0.03244% | 8.288% |  |  | 4.1.1 | 40.4 | 273 | مباني جازان cmu wall work | 74
75 | 2026-08-04 | 165.75 | 2817846.06 | 0.0004875% | 8.288% |  |  | 15.2.1.4 | 1 | 165.75 | asir cold ppr pipe Ø 32 mm | 75
76 | 2026-08-04 | 2028 | 2819874.06 | 0.005965% | 8.294% |  |  | 15.3.1.3 | 16 | 126.75 | asir upvc pipe Ø50mm | 76
77 | 2026-08-04 | 1267.5 | 2821141.56 | 0.003728% | 8.298% |  |  | 15.2.1.5 | 10 | 126.75 | asir ppr pipe Ø 25mm cold | 77
78 | 2026-08-04 | 741 | 2821882.56 | 0.00218% | 8.3% |  |  | 15.3.1.2 | 4 | 185.25 | asir upvc pipe Ø 75 mm | 78
79 | 2026-08-04 | 1009.125 | 2822891.685 | 0.002968% | 8.303% |  |  | 15.2.1.2 | 4.5 | 224.25 | cold asir ppr pipe Ø50mm | 79
80 | 2026-08-04 | 1218.75 | 2824110.435 | 0.003585% | 8.307% |  |  | 15.2.1.1. | 5 | 243.75 | cold asir ppr pipeØ 65 mm | 80
81 | 2026-08-04 | 2730 | 2826840.435 | 0.00803% | 8.315% |  |  | 15.3.1.4 | 8 | 341.25 | asir upvc pipe Ø 25mm | 81
82 | 2026-08-04 | 741 | 2827581.435 | 0.00218% | 8.317% |  |  | 15.2.1.3 | 4 | 185.25 | asir ppr pipe Ø4 mm | 82
83 | 2026-08-05 | 72976.3125 | 2900557.7475 | 0.2147% | 8.532% |  |  | 2.3.1.6 | 427.7 | 170.625 | backfilling a1a jeddah | 83
84 | 2026-08-05 | 8894.34 | 2909452.0875 | 0.02616% | 8.558% |  |  | 2.1.2 | 260.64 | 34.125 | backfilling a1a jeddah | 84
85 | 2026-08-05 | 72925.4663 | 2982377.5538 | 0.2145% | 8.772% |  |  | 2.1.2 | 2137.01 | 34.125 | backfilling a1a jeddah | 85
86 | 2026-08-05 | 24740.2837 | 3007117.8375 | 0.07277% | 8.845% |  |  | 2.1.2 | 724.99 | 34.125 | backfilling a1a jeddah | 86
87 | 2026-08-06 | 2730 | 3009847.8375 | 0.00803% | 8.853% |  |  | 15.3.1.4 | 8 | 341.25 | jazan upvc pipe Ø 25mm | 87
88 | 2026-08-06 | 165.75 | 3010013.5875 | 0.0004875% | 8.854% |  |  | 15.2.1.4 | 1 | 165.75 | cold jazan ppr pipeØ 32 mm | 88
89 | 2026-08-06 | 2028 | 3012041.5875 | 0.005965% | 8.86% |  |  | 15.3.1.3 | 16 | 126.75 | jzazan upvc pipe Ø50 | 89
90 | 2026-08-06 | 741 | 3012782.5875 | 0.00218% | 8.862% |  |  | 15.3.1.2 | 4 | 185.25 | jazan u pvc pipeØ 75mm | 90
91 | 2026-08-06 | 4436.25 | 3017218.8375 | 0.01305% | 8.875% |  |  | 15.2.1.7 | 35 | 126.75 | hot jazan ppr pipe Ø20 mm | 91
92 | 2026-08-06 | 4436.25 | 3021655.0875 | 0.01305% | 8.888% |  |  | 15.2.1.7 | 35 | 126.75 | cold jazan ppr pipe Ø20 mm | 92
93 | 2026-08-06 | 1218.75 | 3022873.8375 | 0.003585% | 8.891% |  |  | 15.2.1.1 | 5 | 243.75 | cold jazan ppr pipe Ø65mm | 93
94 | 2026-08-06 | 1009.125 | 3023882.9625 | 0.002968% | 8.894% |  |  | 15.2.1.2 | 4.5 | 224.25 | cold jazan ppr pipe Ø50mm | 94
95 | 2026-08-06 | 741 | 3024623.9625 | 0.00218% | 8.897% |  |  | 15.2.1.3 | 4 | 185.25 | cold jazan ppr pipe Ø40 mm | 95
96 | 2026-08-06 | 1267.5 | 3025891.4625 | 0.003728% | 8.9% |  |  | 15.2.1.5 | 10 | 126.75 | cold jazan ppr pipe Ø25mm | 96
97 | 2026-08-08 | 4436.25 | 3030327.7125 | 0.01305% | 8.913% |  |  | 15.2.1.7 | 35 | 126.75 | hot asir ppr pipe Ø20 mm | 97
98 | 2026-08-08 | 3753.75 | 3034081.4625 | 0.01104% | 8.924% |  |  | 15.2.1.6 | 35 | 107.25 | asir cold ppr pipe 20mmØ | 98
99 | 2026-08-12 | 72925.4663 | 3107006.9288 | 0.2145% | 9.139% |  |  | 2.1.2 | 2137.01 | 34.125 | jaddah Third Layer A1A Backfilling General Site Area, | 99
100 | 2026-08-12 | 14595.2625 | 3121602.1913 | 0.04293% | 9.182% |  |  | 2.1.2 | 427.7 | 34.125 | JADDAH A1A Backfilling, Bike & Walk Path.Compaction | 100
101 | 2026-08-12 | 14595.2625 | 3136197.4538 | 0.04293% | 9.225% |  |  | 2.1.2 | 427.7 | 34.125 | JADDAH A1A Backfilling, Bike & Walk Path.Compaction | 101
102 | 2026-08-12 | 14595.2625 | 3150792.7163 | 0.04293% | 9.268% |  |  | 2.1.2 | 427.7 | 34.125 | JEDDAH Third Layer A1A Bike & Walk Path Backfilling | 102
103 | 2026-08-15 | 33.7837 | 3150826.5 | 9.937e-05% | 9.268% |  |  | 2.1.2 | 0.99 | 34.125 | JEZZAN 1A Backfilling, Compaction, and Field Density Test (FDT) Works 1st LAYER GRP Tank | 103
104 | 2026-08-15 | 184.6163 | 3151011.1163 | 0.000543% | 9.268% |  |  | 2.1.2 | 5.41 | 34.125 | JEZZAN A1A Backfilling, Compaction, and Field Density Test (FDT) Works 2nd LAYER GRP Tank | 104
105 | 2026-08-15 | 221.13 | 3151232.2463 | 0.0006504% | 9.269% |  |  | 2.1.2 | 6.48 | 34.125 | JEZZAN A1A Backfilling, Compaction, and Field Density Test (FDT) Works 3rd LAYER GRP Tank, | 105
106 | 2026-08-15 | 221.13 | 3151453.3763 | 0.0006504% | 9.27% |  |  | 2.1.2 | 6.48 | 34.125 | A1A Backfilling, Compaction, and Field Density Test (FDT) Works 4th LAYER GRP Tank | 106
107 | 2026-08-15 | 221.13 | 3151674.5063 | 0.0006504% | 9.27% |  |  | 2.1.2 | 6.48 | 34.125 | JEZZAN A1A Backfilling, Compaction, and Field Density Test (FDT) Works 5th LAYER GRP Tank | 107
108 | 2026-08-15 | 221.13 | 3151895.6363 | 0.0006504% | 9.271% |  |  | 2.1.2 | 6.48 | 34.125 | JEZZAN A1A Backfilling, Compaction, and Field Density Test (FDT) Works 6th LAYER GRP Tank, | 108
109 | 2026-08-15 | 221.13 | 3152116.7663 | 0.0006504% | 9.272% |  |  | 2.1.2 | 6.48 | 34.125 | JEZZAN A1A Backfilling, Compaction, and Field Density Test (FDT) Works 7th LAYER GRP Tank, | 109
110 | 2026-08-23 | 1218.75 | 3153335.5163 | 0.003585% | 9.275% |  |  | 15.2.1.1 | 5 | 243.75 | Installation and test PPR Pipe with 65 mm Ø Cold water | 110
111 | 2026-08-23 | 1009.125 | 3154344.6413 | 0.002968% | 9.278% |  |  | 15.2.1.2 | 4.5 | 224.25 | Installation and test PPR Pipe with 50 mm Ø Cold JEDDAH water | 111
112 | 2026-08-23 | 741 | 3155085.6413 | 0.00218% | 9.28% |  |  | 15.2.1.3 | 4 | 185.25 | Installation and test PPR Pipe with 40 mm Ø Cold JEDDAH water | 112
113 | 2026-08-23 | 165.75 | 3155251.3913 | 0.0004875% | 9.281% |  |  | 15.2.1.4 | 1 | 165.75 | Installation and test PPR Pipe with 32 mm Ø Cold JEDDAH water | 113
114 | 2026-08-23 | 1267.5 | 3156518.8913 | 0.003728% | 9.284% |  |  | 15.2.1.5 | 10 | 126.75 | Installation and test PPR Pipe with 25 mm Ø Cold JEDDAH water | 114
115 | 2026-08-23 | 3753.75 | 3160272.6413 | 0.01104% | 9.296% |  |  | 15.2.1.6 | 35 | 107.25 | Installation and test PPR Pipe with 02 mm Ø Cold JEDDAH water | 115
116 | 2026-08-23 | 4436.25 | 3164708.8913 | 0.01305% | 9.309% |  |  | 15.2.1.7 | 35 | 126.75 | Installation and test PPR Pipe with 02 mm Ø Hot JEDDAH water | 116
117 | 2026-08-23 | 741 | 3165449.8913 | 0.00218% | 9.311% |  |  | 15.3.1.2 | 4 | 185.25 | Installation and leakage test U-PVC Pipe with Ø JEDDAH 3" (75mm) Inside the toilet building | 117
118 | 2026-08-23 | 2028 | 3167477.8913 | 0.005965% | 9.317% |  |  | 15.3.1.3 | 16 | 126.75 | Installation and leakage test U-PVC Pipe with Ø JEDDAH 2" (50mm) Inside the toilet building. | 118
119 | 2026-08-23 | 2730 | 3170207.8913 | 0.00803% | 9.325% |  |  | 15..3.1.4 | 8 | 341.25 | Installation and leakage test U-PVC Pipe with Ø JEDDAH 1" (25mm) Inside the toilet building. | 119
120 | 2026-08-30 | 241.605 | 3170449.4963 | 0.0007106% | 9.325% |  |  | 2.1.2 | 7.08 | 34.125 | Inspection for 1st Layer Backfilling – Around Septic Tank JAZAN Compacted Thickness: 30 cm | 120
121 | 2026-08-29 | 79.5113 | 3170529.0075 | 0.0002339% | 9.326% |  |  | 2.1.2 | 2.33 | 34.125 | Inspection for 1st Layer Backfilling – Around Septic Tank ASIR Compacted Thickness: 30 cm | 121
122 | 2026-08-29 | 204.0675 | 3170733.075 | 0.0006002% | 9.326% |  |  | 2.1.2 | 5.98 | 34.125 | Inspection for 3rd Layer Backfilling – Around Septic ASIR Tank Compacted Thickness: 30 cm | 122
123 | 2026-08-29 | 217.7175 | 3170950.7925 | 0.0006404% | 9.327% |  |  | 2.1.2 | 6.38 | 34.125 | Inspection for 4th Layer Backfilling – Around Septic ASIR Tank Compacted Thickness: 30 cm | 123
124 | 2026-09-09 | 2340 | 3173290.7925 | 0.006883% | 9.334% |  |  | 16.3.5 | 2 | 1170 | jedah waall mounted out door wall 17 watt | 124
125 | 2026-09-09 | 7800 | 3181090.7925 | 0.02294% | 9.357% |  |  | 16.5.5 | 4 | 1950 | jeddah outdor fixed cemera | 125
126 | 2026-09-09 | 1950 | 3183040.7925 | 0.005736% | 9.362% |  |  | 16.3.4 | 2 | 975 | jaddah led exit light fixtur 4.5 watt | 126
127 | 2026-09-09 | 4680 | 3187720.7925 | 0.01377% | 9.376% |  |  | 16.3.3 | 4 | 1170 | jaddah wall mounted emergancy led 230 v 60 hz | 127
128 | 2026-09-09 | 2600.325 | 3190321.1175 | 0.007649% | 9.384% |  |  | 16.9.11 | 1 | 2600.325 | jeddah outdoor disconnect switch exhaust fans | 128
129 | 2026-09-09 | 1170 | 3191491.1175 | 0.003441% | 9.387% |  |  | 16.3.2 | 1 | 1170 | jedah led flood light outdoor watt 96.4000k 12720lumen | 129
130 | 2026-09-09 | 7312.5 | 3198803.6175 | 0.02151% | 9.409% |  |  | 16.3.1 | 15 | 487.5 | jedah rescessed mounted led done light luminair 40 watt | 130
131 | 2026-09-09 | 1462.5 | 3200266.1175 | 0.004302% | 9.413% |  |  | 16.4.2 | 3 | 487.5 | jedah wall mounited data out let | 131
132 | 2026-09-09 | 1462.5 | 3201728.6175 | 0.004302% | 9.417% |  |  | 16.41 | 3 | 487.5 | jadah wall telephone outlet | 132
133 | 2026-09-09 | 536.25 | 3202264.8675 | 0.001577% | 9.419% |  |  | 16.8.3 | 1 | 536.25 | addresable manulal pull station | 133
134 | 2026-09-09 | 5898.75 | 3208163.6175 | 0.01735% | 9.436% |  |  | 16.8.2 | 11 | 536.25 | intelligent phto electric smoke and heat detector | 134
135 | 2026-09-09 | 1462.5 | 3209626.1175 | 0.004302% | 9.441% |  |  | 16.8.5 | 1 | 1462.5 | jeddah fir allarm storobe with sounder | 135
136 | 2026-09-09 | 1462.5 | 3211088.6175 | 0.004302% | 9.445% |  |  | 16.4.5 | 1 | 1462.5 | av wall out let | 136
137 | 2026-09-09 | 1950 | 3213038.6175 | 0.005736% | 9.451% |  |  | 16.5.6 | 1 | 1950 | pull box for fiber optic cable | 137
138 | 2026-09-09 | 2600.325 | 3215638.9425 | 0.007649% | 9.458% |  |  | 16.9.10 | 1 | 2600.325 | outdoor with conect switch for ac | 138
139 | 2026-09-09 | 1462.5 | 3217101.4425 | 0.004302% | 9.463% |  |  | 16.9.1 | 3 | 487.5 | 1 way . One gang switch | 139
140 | 2026-09-09 | 975 | 3218076.4425 | 0.002868% | 9.466% |  |  | 16.8.4 | 1 | 975 | addresable FIRE ALLLARM ASTROBE | 140
141 | 2026-09-09 | 1137.825 | 3219214.2675 | 0.003347% | 9.469% |  |  | 16.9.9 | 1 | 1137.825 | WATER HEATER SWTICH | 141
142 | 2026-09-09 | 1137.825 | 3220352.0925 | 0.003347% | 9.472% |  |  | 16.9.8 | 1 | 1137.825 | HAND DRYER SWITCH | 142
143 | 2026-09-09 | 5689.125 | 3226041.2175 | 0.01673% | 9.489% |  |  | 16.9.7 | 5 | 1137.825 | DUPLEX RECEPLTACLE | 143
144 | 2026-09-09 | 9360 | 3235401.2175 | 0.02753% | 9.517% |  |  | 16.5.4 | 6 | 1560 | INDOOR DOME CAMERA IP 20 | 144
145 | 2026-09-09 | 487.5 | 3235888.7175 | 0.001434% | 9.518% |  |  | 16.9.5 | 1 | 487.5 | INDOOR AC DP SWITCH | 145
146 | 2026-09-09 | 1950 | 3237838.7175 | 0.005736% | 9.524% |  |  | 16.4.4 | 1 | 1950 | AV FLOOR BOX | 146
147 | 2026-09-09 | 3248.7 | 3241087.4175 | 0.009556% | 9.533% |  |  | 16.9.6 | 4 | 812.175 | HIGH LEVEL SINGLE RECETPALE OUTLET | 147
148 | 2026-09-09 | 487.5 | 3241574.9175 | 0.001434% | 9.535% |  |  | 16.9.4 | 1 | 487.5 | EXAUST FAN DP WEATERPOOF | 148
149 | 2026-09-09 | 487.5 | 3242062.4175 | 0.001434% | 9.536% |  |  | 16.9.3 | 1 | 487.5 | 1 way . One gang switch | 149
150 | 2026-09-09 | 1950 | 3244012.4175 | 0.005736% | 9.542% |  |  | 16.9.2 | 4 | 487.5 | 1 way . TWO gang switch | 150
151 | 2026-09-09 | 10530.6337 | 3254543.0513 | 0.03097% | 9.573% |  |  | 2.12 | 308.59 | 34.125 | A1A BACKFILLING ASIR | 151
152 | 16/9/2026 | 25116.39 | 3279659.4413 | 0.07388% | 9.647% |  |  | 9.2.2 | 214.67 | 117 | INTERNAL AND EXTARNAL PLASTER WORKS JEDDAH | 152
153 | 14/9/2026 | 19150.56 | 3298810.0013 | 0.05633% | 9.703% |  |  | 9.2.2 | 163.68 | 117 | asir EXTERNAL PLASTERING WORK | 153
154 | 15/9/2026 | 12598.95 | 3311408.9513 | 0.03706% | 9.74% |  |  | 3.2.1 | 4.97 | 2535 | jazan FOUNDATION CASTING grp water tank | 154
155 | 14/9/2026 | 23100.9188 | 3334509.87 | 0.06795% | 9.808% |  |  | 2.1.2 | 676.95 | 34.125 | ASIR A1A BK GENRAL SITE | 155
156 | 15/9/2026 | 11843.0813 | 3346352.9513 | 0.03483% | 9.843% |  |  | 2.1.2 | 347.05 | 34.125 | ASIR A1A BK GENRAL SITE | 156
157 | 16/9/2026 | 7320.1537 | 3353673.105 | 0.02153% | 9.864% |  |  | 2.12 | 214.51 | 34.125 | ASIR A1A BK GENRAL SITE | 157
158 | 16/9/2026 | 2726.1 | 3356399.205 | 0.008018% | 9.872% |  |  | 9.2.5 | 13.98 | 195 | STONE CLADDING SHOWER LOCKER BULIDING | 158
159 | 2026-09-12 | 9743.7112 | 3366142.9163 | 0.02866% | 9.901% |  |  | 2.1.2 | 285.53 | 34.125 | ASIR A1A BK GENRAL SITE | 159
160 | 16/9/2026 | 2600.325 | 3368743.2413 | 0.007649% | 9.909% |  |  | 16.9.11 | 1 | 2600.325 | ASIR OUT DOOR DISCINNNECT SWITCH EXHAUT FAN | 160
161 | 2026-09-19 | 7312.5 | 3376055.7413 | 0.02151% | 9.93% |  |  | 16.3.1 | 15 | 487.5 | RECESSED MOUTED LEDIP 44 .230V .4000K 4200 LUMEN ASIR CRIASIR 80 LOW | 161
162 | 2026-09-19 | 1170 | 3377225.7413 | 0.003441% | 9.934% |  |  | 16.3.2 | 1 | 1170 | ASIR LED FLOOD LIGHT OUT DOOR TYPE 96 WATT .4000 K | 162
163 | 2026-09-19 | 1950 | 3379175.7413 | 0.005736% | 9.939% |  |  | 16.3.4 | 2 | 975 | asir LED EXIT LIGHT FIXTURE 4.5watt with bettery 3 hours | 163
164 | 2026-09-19 | 4680 | 3383855.7413 | 0.01377% | 9.953% |  |  | 16.3.3 | 4 | 1170 | asir wall mounted emergency led luminaire 230v .60hz 3 | 164
165 | 2026-09-19 | 1950 | 3385805.7413 | 0.005736% | 9.959% |  |  | 16.5.6 | 1 | 1950 | asir pull box for fiber optic cable | 165
166 | 2026-09-19 | 1462.5 | 3387268.2413 | 0.004302% | 9.963% |  |  | 16.4.2 | 3 | 487.5 | wall mounted data outlet | 166
167 | 2026-09-19 | 536.25 | 3387804.4913 | 0.001577% | 9.965% |  |  | 16.8.3 | 1 | 536.25 | addressable manual pull station wall | 167
168 | 2026-09-19 | 1950 | 3389754.4913 | 0.005736% | 9.971% |  |  | 16.4.4 | 1 | 1950 | av floorbox outlet | 168
169 | 2026-09-19 | 9360 | 3399114.4913 | 0.02753% | 9.998% |  |  | 16.5.4 | 6 | 1560 | INDOOR DOME CAMERA IP 20 | 169
170 | 24/9/2026 | 97500 | 3496614.4913 | 0.2868% | 10.28% |  |  | 15.2.2.1 | 40 | 2437.5 | water supply system | 170
171 | 2026-09-22 | 8531.25 | 3505145.7413 | 0.02509% | 10.31% |  |  | 15.3.7 | 10 | 853.125 | sewer and drainage system | 171
172 | 2026-09-22 | 4875 | 3510020.7413 | 0.01434% | 10.32% |  |  | 15.4.3 | 100 | 48.75 | duct supply install and testing and commission indoor | 172
173 | 2026-09-19 | 1462.5 | 3511483.2413 | 0.004302% | 10.33% |  |  | 16.9.1 | 3 | 487.5 | 1 way one gang switch | 173
174 | 2026-09-19 | 1462.5 | 3512945.7413 | 0.004302% | 10.33% |  |  | 16.4.5 | 1 | 1462.5 | av wall out let | 174
175 | 2026-09-14 | 23100.9188 | 3536046.66 | 0.06795% | 10.4% |  |  | 2.1.2 | 676.95 | 34.125 | A1A BACKFILLING ASIR | 175
176 | 2026-09-19 | 3777.15 | 3539823.81 | 0.01111% | 10.41% |  |  | 3.2.1 | 1.49 | 2535 | asir tank foundation concert | 176
177 | 2026-09-26 | 4121.6175 | 3543945.4275 | 0.01212% | 10.42% |  |  | 2.1.2 | 120.78 | 34.125 | backfilling a1a jezan | 177
178 | 2026-09-28 | 17485.7963 | 3561431.2238 | 0.05143% | 10.48% |  |  | 2.1.1 | 275.91 | 63.375 | excavation gazan | 178
179 | 2026-09-22 | 3887.52 | 3565318.7438 | 0.01143% | 10.49% |  |  | 2.1.2 | 113.92 | 34.125 | backfilling gazan | 179
180 | 2026-09-19 | 10804.95 | 3576123.6938 | 0.03178% | 10.52% |  |  | 7.6 | 73.88 | 146.25 | epoxy septic tank jazan | 180
181 | 2026-09-19 | 3777.15 | 3579900.8438 | 0.01111% | 10.53% |  |  | 3.2.1 | 1.49 | 2535 | grp jazan tank foundation concret reinforced | 181
182 | 2026-09-28 | 3916.8675 | 3583817.7113 | 0.01152% | 10.54% |  |  | 2.1.2 | 114.78 | 34.125 | backfillng layer jazan | 182
183 | 2026-09-28 | 5967 | 3589784.7113 | 0.01755% | 10.56% |  |  | 9.2.2 | 51 | 117 | internal jazaplastering to work | 183
184 | 2026-09-28 | 14945.385 | 3604730.0963 | 0.04396% | 10.6% |  |  | 9.2.1 | 109.49 | 136.5 | asir ceramic wall tile | 184
185 | 2026-09-28 | 2029.95 | 3606760.0463 | 0.005971% | 10.61% |  |  | 7.4.1 | 69.4 | 29.25 | concerte screed casting | 185
186 | 2026-10-01 | 17464.59 | 3624224.6363 | 0.05137% | 10.66% |  |  | 9.2.2 | 149.27 | 117 | external plastring work jazazn | 186
187 | 2026-09-21 | 3900 | 3628124.6363 | 0.01147% | 10.67% |  |  | 5.2 | 1 | 3900 | galvanized steel rooof scupper jazan | 187
188 | 2026-09-21 | 5850 | 3633974.6363 | 0.01721% | 10.69% |  |  | 5.1 | 1 | 5850 | galvanized steel rooofl ladder | 188
189 | 2026-09-21 | 3900 | 3637874.6363 | 0.01147% | 10.7% |  |  | 5.2 | 1 | 3900 | galvanized steel rooof scupperasir | 189
190 | 2026-09-19 | 1137.825 | 3639012.4613 | 0.003347% | 10.7% |  |  | 16.9.8 | 1 | 1137.825 | asir weaterproof HAND DRYER SWITCH | 190
191 | 2026-10-07 | 2018250 | 5657262.4613 | 5.936% | 16.64% |  |  | 2.3.9 | 0.36 | 5606250 | Air dome | 191
192 | 2026-10-08 | 125775 | 5783037.4613 | 0.37% | 17.01% |  |  | 16.2.1 | 20 | 6288.75 | Lighting Pole | 192 | 2026-08-10
193 | 2026-09-21 | 9487.4325 | 5792524.8938 | 0.02791% | 17.04% |  |  | 2.1.2 | 278.02 | 34.125 | Backfilling A1A | 193
194 | 2026-09-28 | 1315.1775 | 5793840.0713 | 0.003868% | 17.04% |  |  | 2.1.2 | 38.54 | 34.125 | Backfilling A1A | 194
195 | 2026-09-21 | 10191.7725 | 5804031.8438 | 0.02998% | 17.07% |  |  | 2.1.2 | 298.66 | 34.125 | Backfilling A1A | 195
196 | 2026-09-21 | 12783.9075 | 5816815.7513 | 0.0376% | 17.11% |  |  | 2.1.2 | 374.62 | 34.125 | Backfilling A1A | 196
197 | 2026-09-21 | 3200.5838 | 5820016.335 | 0.009414% | 17.12% |  |  | 2.1.2 | 93.79 | 34.125 | Backfilling A1A | 197
198 | 2026-09-30 | 2457 | 5822473.335 | 0.007227% | 17.13% |  |  | 2.1.2 | 72 | 34.125 | Backfilling A1A | 198
199 | 2026-09-30 | 204.75 | 5822678.085 | 0.0006022% | 17.13% |  |  | 2.1.2 | 6 | 34.125 | Backfilling A1A | 199
200 | 2026-09-29 | 1218.75 | 5823896.835 | 0.003585% | 17.13% |  |  | 15.3.1.1 | 5 | 243.75 | UPVC Pipe 4" | 200
201 | 2026-09-20 | 4875 | 5828771.835 | 0.01434% | 17.14% |  |  | 15.4.3 | 100 | 48.75 | duct supply install and testing and commission indoor | 201
202 | 2026-09-28 | 975 | 5829746.835 | 0.002868% | 17.15% |  |  | 15.4.1 | 1 | 975 | Inline Exhaust Fan | 202
203 | 2026-09-28 | 2029.95 | 5831776.785 | 0.005971% | 17.15% |  |  | 7.4.1 | 69.4 | 29.25 | Foam concrete screed | 203
204 | 2026-09-20 | 3900 | 5835676.785 | 0.01147% | 17.16% |  |  | 5.2 | 1 | 3900 | galvanized steel rooof scupper Jeddah | 204
205 | 2026-09-20 | 5850 | 5841526.785 | 0.01721% | 17.18% |  |  | 5.1 | 1 | 5850 | galvanized steel rooofl ladder | 205
206 | 2026-09-20 | 3900 | 5845426.785 | 0.01147% | 17.19% |  |  | 5.2 | 1 | 3900 | galvanized steel rooof scupper Asir | 206
207 | 2026-09-29 | 57182.7262 | 5902609.5113 | 0.1682% | 17.36% |  |  | 2.3.5.1 | 198.81 | 287.625 | Football Play Ground Backfilling and Excavation | 207
208 | 2026-09-29 | 64350 | 5966959.5113 | 0.1893% | 17.55% |  |  | 2.3.5.2 | 60 | 1072.5 | Padel Ground Backfilling and Excavation | 208
209 | 2026-09-29 | 89505 | 6056464.5113 | 0.2633% | 17.81% |  |  | 2.3.5.3 | 153 | 585 | Basket ball Backfilling and Excavation | 209
210 | 2026-10-03 | 8628.75 | 6065093.2613 | 0.02538% | 17.84% |  |  | 2.3.2.1 | 147.5 | 58.5 | Kerb Stone K1A Asir | 210

## Codes
Status List
| Approved |  | Y
| Pending |  | N | [5 empty] | (Manhours)
| Potential | [7 empty] | (Mandays)
| Phase | Stage |  | Stage |  | Status |  | Score
[8 empty] | Low | Contractor | Active
| Launch | LOA |  | LOA |  | Active |  | Medium | CM | Expired
| Launch | Kick-off Meeting |  | Kick-off Meeting |  | On Hold |  | High | PgM | Occurred
| Launch | Site Handover |  |  |  | Terminated |  |  | Modon | Pending
| Launch | Mobilization |  | Mobilization | Initial staff and equipment in place, ready to start production | Terminated, Closed |  |  | Other
| Execution | Construction |  | Execution | Tender Documents Issued | Substantial Complete | Initial Handover done at site
| Execution | T&C |  |  | Responses to the OCS completed | Complete | Initial Handover Signed
| Execution | Initial Handover |  | Closeout | Design close-out process complete | Closed | Final Handover done at Site
Warranty Period
Final Handover
Project Status Score
Elements |  |  | Max | Score | Planned | Actual | Remarks
SPI (Physical Effort) |  |  | 100% | 83.02% | No Entry Required
SPI (Cost) |  |  | 100% | 96.23% | No Entry Required
On Schedule -Active |  |  | 100% | 1040% | No Entry Required |  |  |  | 0.6
Manpower Availability |  |  | 100% | 40% | No Entry Required
Major Equipment Availability |  |  | 100% | 55.56% | No Entry Required
Billing % Compared to Planned |  |  | 100% | 0% | No Entry Required
Safety Score |  |  | 100% | #REF! | No Entry Required
Quality Score |  |  | 100% | #REF! | No Entry Required

## Kutools_Chart (hidden)
Pointer | Scale
#REF! | #REF!
1.5
#REF! | #REF!
Intermediate data of the speedometer chart (Please do not remove or modify the data, otherwise, error will occur to the speedometer chart)
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Current value: | #REF!
Pointer | Scale
#REF! | #REF!
1.5
#REF! | #REF!
Intermediate data of the speedometer chart (Please do not remove or modify the data, otherwise, error will occur to the speedometer chart)
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Current value: | #REF!
#REF! | #REF!
Pointer | Scale
#REF! | #REF!
1.5
#REF! | #REF!
Intermediate data of the speedometer chart (Please do not remove or modify the data, otherwise, error will occur to the speedometer chart)
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Current value: | #REF!