## الأعماال المنفذه خلال الاسبوع
# | القطاع | Project ID | اسم المشروع | مدير المشروع | المقاول | بداية المشروع | نهاية المشروع التعاقدية | نهاية المشروع المتوقعة/ الالتزام | قيمة المشروع | Planned (%) AS PER BASELINE حتى الاسبوع الحالي | Planned (%) AS PER Crashed Plan حتى الاسبوع الحالي | Actual (%) حتى الاسبوع السابق | Actual (%) حتى الاسبوع الحالي | Actual (%) خلال الاسبوع | الأعمال التي تمت خلال هذا الاسبوع | أسباب التأخير في حالة وجود تأخير | تحديات المشروع | استشاري المشروع | رقم استشاري المشروع | Email | مهندس تخطيط المشروع | رقم مهندس تخطيط المشروع | Email
1 | القطاع الأوسط | JHD4-02-007 | تطوير أراضي واحة جدة | عبد الله الشنيفي | شركة الانجاز للتجارة والمقاولات | 2025-11-24 | 2026-05-23 | 2026-11-23 | 57304347.86 | 61.39% | 86.21% | 93.31% | 95.17% | 1.86% | Road Marking Work at R8,R7S MCC Panel Work at Lift Station Diesl Pump Work at Lift Station Rockfilling Work for Plots 5 & 6 Sign Board Installation at R3 & R7S MV Termination Work SL Termination Work PLC Installation at Lift Station Panel Board Work at Lift Station TL MH Finishing Work Pump Installation Work at Lift Station RMU Termination Work Checker Plate Installation at Lift Station
3 | القطاع الأوسط
4 | القطاع الأوسط
5 | القطاع الأوسط | [16 empty] | باسم الطيب | 0542536776 | Bassem.Altayeb@jasarapmc.com