## Weekly Progress Report
MODON - Weekly Progress Report - Construction Projects | [11 empty] | Dashboard 20-Oct-2026 | [14 empty] | Report No. | 47.8571 |  |  | Data Date | 2026-10-20
Contract General Information | [5 empty] | Key Dates | [5 empty] | Cost Summary (SR) | [7 empty] | Performance Summary | [5 empty] | Project Scope
Project Name | INFRASTRUCTURE DEVELOPMENT FOR INDUSTRIAL CITY 1 IN JEDDAH |  |  |  |  | Contract Award | 2025-11-02 | Contract Award (Hijri) | 2025-11-02 | Revised Completion | 2027-11-18 | Original Contract Value |  | 86782345 |  | O&M Value (if any) |  | 0 | EAC | Plan Value | 53.18% | Phys. Plan Value | 46.99% | Quality Score | 85.21% | The Scope of Works for the INFRASTRUCTURE DEVELOPMENT FOR INDUSTRIAL CITY 1 IN JEDDAH. This construction works includes but not limited to the followings: (Road works - Storm network - Sewer Network - Potable water network - TSE network - Electrical works - Fence - Bridge - Landscape works)
Project ID | JDH1-02-003 |  | Stage | Construction |  | Contract Sign | 2025-11-13 | Contract Sign (Hijri) | 2025-11-13 | Committed Completion | 2027-11-18 | Revised Contract Value |  | 86782345 | EAC | Submitted Invoices (Gross Value) |  | 44851849.3625 |  | Earn Value | 78.72% | Phys. Earn Value | 72.61% |  | ¢¢¢¢¢ ¢¢¢££
Contractor | Al Enjaz Company for Trading and Contracting |  | Status | Active |  | Site Handover | 2025-11-19 | Site Handover (Hijri) | 2025-11-19 | Forecast Completion | 2028-05-20 | Estimate At Completion Value |  | 86782345 | #REF! | Penalities |  | 0 |  | Variance | 25.54% | Variance | 25.63% | Safety Score | 77.17%
Consultant | Saudi Arabia Consulting Engineering Company "EGIS" |  | Modon PM | Engr.Abdallah Aljulayfi |  | Original Completion | 2027-11-18 | Original Completion (Hijri) | 2027-11-18 | Variance | -184 | Potential Changes |  | 0 |  | FIR Value (Todate) |  | 57162746.82 |  | FIR % | 65.87% | Invoiced % | 51.68% |  | ¢¢¢¢¢ ¢¢£££
Progress Overview
Earned Value Progress (SAR) | [13 empty] | Physical Progress (Effort) | [11 empty] | Earned Value Progress (%)
WBS |  | BOQ Value (SAR) | % Wt. | Weekly (SAR) |  | To Date (SAR) | [7 empty] | Budgeted | % Wt. | Weekly Physical Progress |  |  |  | To Date Physical Progress
|  |  |  | Planned | Earned | Original Plan | Revised Planned | Earned | Original Plan % | Revised Planned % | Earned % | Variance | SPI | (Manhours) |  | Planned | Earned | Plan % | Earned % | Planned | Earned | Plan % | Earned % | Variance | SPI
|  | 0 | 0% | 88958.71 | 0 | 2119815.89 | 2208774.6 | 5352415.58 | 0% | 0% | 0% | 0%
Mobilization |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 20050 | 2.806% | 0 | 0 | 0% | 0% | 20050 | 20050 | 100% | 100% | 0% | 1
Engineering |  | 2601460.39 | 2.998% | 0 | 0 | 2601460.39 | 2601460.39 | 2579200.39 | 100% | 100% | 99.14% | -0.8557% | 0.99144 | 33415 | 4.676% | 0 | 0 | 0% | 0% | 33415 | 33009.2 | 100% | 98.79% | -1.214% | 0.98786
Procurement |  | 17355662.1 | 20% | 26504 | 208500 | 13492073.1 | 13518577.1 | 15737880.1 | 77.74% | 77.89% | 90.68% | 12.79% | 1.1642 | 82413.81 | 11.53% | 0 | 0 | 0% | 0% | 35843.52 | 65032.49 | 43.49% | 78.91% | 35.42% | 1.8143
Construction |  | 58147531.04 | 67% | 394580.51 | 190111.17 | 29638878.78 | 30033459.29 | 44572325.02 | 50.97% | 51.65% | 76.65% | 25% | 1.4841 | 545268.46 | 76.31% | 5590.01 | 1907.14 | 1.025% | 0.3498% | 246436.59 | 390120.29 | 45.2% | 71.55% | 26.35% | 1.583
Site Demolition |  | 279942.75 | 0.3226% | 0 | 0 | 279942.75 | 279942.75 | 279942.75 | 100% | 100% | 100% | 0% | 1 | 7350 | 1.029% | 0 | 0 | 0% | 0% | 7350 | 7350 | 100% | 100% | 0% | 1
Roads & Meduim Voltage |  | 11810038.74 | 13.61% | 0 | 0 | 11810038.74 | 11810038.74 | 8650438.79 | 100% | 100% | 73.25% | -26.75% | 0.73246 | 100175 | 14.02% | 0 | 0 | 0% | 0% | 100175 | 73591 | 100% | 73.46% | -26.54% | 0.73462
Deep Infrastructure network |  | 10009830.2 | 11.53% | 10082.82 | 7209.5 | 9958787.21 | 9968870.03 | 9750710.5 | 99.49% | 99.59% | 97.41% | -2.179% | 0.97812 | 54025 | 7.561% | 0 | 0 | 0% | 0% | 54025 | 51820.5 | 100% | 95.92% | -4.081% | 0.95919
Shallow infrastructure network |  | 12539076.3 | 14.45% | 209087.15 | 99253.79 | 2810927.82 | 3020014.97 | 10453768.19 | 22.42% | 24.08% | 83.37% | 59.28% | 3.4615 | 198577.38 | 27.79% | 4687.15 | 1717.15 | 2.36% | 0.8647% | 43207.03 | 154727.25 | 21.76% | 77.92% | 56.16% | 3.5811
Bridge |  | 2513306.98 | 2.896% | 15291.43 | 0 | 1320006.88 | 1335298.31 | 1830342.88 | 52.52% | 53.13% | 72.83% | 19.7% | 1.3707 | 14022.14 | 1.962% | 171.43 | 0 | 1.223% | 0% | 7721.43 | 12207.14 | 55.07% | 87.06% | 31.99% | 1.5809
Outside Boundary Area (Tie-in Lines) |  | 2681726.27 | 3.09% | 71160.39 | 0 | 1339359.49 | 1410519.88 | 2663147.17 | 49.94% | 52.6% | 99.31% | 46.71% | 1.8881 | 19949.2 | 2.792% | 681.43 | 0 | 3.416% | 0% | 9933.13 | 19885.03 | 49.79% | 99.68% | 49.89% | 2.0019
Roads Finishing |  | 8138565 | 9.378% | 0 | 83647.88 | 0 | 0 | 5591559.17 | 0% | 0% | 68.7% | 68.7% |  | 65951.79 | 9.23% | 0 | 190 | 0% | 0.2881% | 0 | 45112.37 | 0% | 68.4% | 68.4%
Fence and Gate |  | 8127691.9 | 9.366% | 88958.71 | 0 | 2119815.89 | 2208774.6 | 5352415.58 | 26.08% | 27.18% | 65.85% | 38.68% | 2.4233 | 43715 | 6.118% | 50 | 0 | 0.1144% | 0% | 24025 | 25427 | 54.96% | 58.17% | 3.207% | 1.0584
Roundabout & Landscape |  | 2047352.9 | 2.359% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 41502.94 | 5.808% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
Testing & Commissioning |  | 8677691.2 | 9.999% | 0 | 0 | 0 | 0 | 5426563.31 | 0% | 0% | 62.53% | 62.53% |  | 20050 | 2.806% | 0 | 0 | 0% | 0% | 0 | 10646.5 | 0% | 53.1% | 53.1%
Project Close-out |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 13364 | 1.87% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
| Total | 86782344.73 | 100% | 815665.01 | 505074.46 | 45732412.27 | 46153496.77 | 68315968.83 | 52.7% | 53.18% | 78.72% | 25.54% | 1.4802 | 714561.26 | 100% | 5590.01 | 1907.15 | 0.7823% | 0.2669% | 335745.11 | 518858.48 | 46.99% | 72.61% | 25.63% | 1.5454
Construction Milestones
[26 empty] | Item No. | Milestones |  | Original (Baseline) | Latest Plan | Forecast | Status | Days Change
[26 empty] | 1 | Project Finish |  | 2028-05-13 | 2028-05-20 | 2028-05-20 | F | -7
[25 empty] | #REF! | 2 | Project Start |  | 2025-11-19 | 2025-11-19 | 2025-11-19 | A | 0
[25 empty] | #REF! | 3 | Finish Mobilization |  | 2026-03-04 | 2026-03-04 | 2026-03-04 | A | 0
[25 empty] | #REF! | 4 | Finish Baseline Time Schedule |  | 2025-12-18 | 2025-12-18 | 2025-12-18 | A | 0
[25 empty] | #REF! | 5 | Finish Submission and Approval for Shop Drawings, Method of Statement, Prequalification and Materials |  | 2026-10-31 | 2026-11-07 | 2026-11-07 | F | -7
[25 empty] | #REF! | 6 | Finish PO for Short Lead Item & Long Lead Item |  | 2026-10-25 | 2026-11-01 | 2026-11-01 | F | -7
[6 empty] | 20000000 | [18 empty] | #REF! | 7 | Completion of Roads & Meduim Voltage |  | 2027-01-11 | 2027-01-18 | 2027-01-18 | F | -7
[26 empty] | 8 | Completion of Deep infrastructure network |  | 2027-06-12 | 2027-06-19 | 2027-06-19 | F | -7
[26 empty] | 9 | Completion of Shallow infrastructure network |  | 2027-09-26 | 2027-10-03 | 2027-10-03 | F | -7
[25 empty] | #REF! | 10 | Completion all Works |  | 2028-05-13 | 2028-05-20 | 2028-05-20 | F | -7
#REF!
#REF!
#REF!
#REF!
[6 empty] | 20000000 | [18 empty] | #REF!
#REF!
#REF!
Performance overview
Submittals Status | [10 empty] | Quality | [10 empty] | Safety
Shop Drawings | [10 empty] | Quality Reports | [10 empty] | Safety Statistics | [7 empty] | Proactive Vs Reactive Actions Taken
Item Per WBS |  | Total | Total Submitted Drawings |  |  |  |  | Remaining | Pending | Total Submittals | Quality Reports |  | Issued | Closed | Pending | Avg. Closing (Days) | Pending |  |  |  |  | Category | Item |  | This Week |  | This Month | Year to Date | Cumulative
|  |  | A | B | C | D | Processed | [9 empty] | 0-10 Days | 11-20 Days | 21-30 Days | 31-60 Days | > 60 Days
Roads |  | 268 | 2 | 266 | 0 | 0 | 268 | 0 | 0 | 268 | [11 empty] | General | Total Hours Worked |  | 9216 |  | 26112 | 438898 | 465010 |  |  | Proactive | 212
General |  | 11 | 0 | 11 | 0 | 0 | 11 | 0 | 0 | 11 | Non Conformance (NCR) |  | 16 | 16 | 0 | [7 empty] | Safe Hours Worked |  | 9216 |  | 26112 | 438898 | 465010 |  |  | Reactive | 0
Structural |  | 590 | 2 | 588 | 0 | 109 | 480 | 0 | 0 | 590 | Site Instruction (SIR) |  | 21 | 21 | 0 | [6 empty] | Reactive | LTI |  | 0 |  | 0 | 0 | 0
Architectural |  | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 2 | Material Inspection (MIR) |  | 100 | 100 | 0 | [7 empty] | MTC (Healed w/o Disability) |  | 0 |  | 0 | 0 | 0
Mechanical |  | 336 | 2 | 397 | 0 | 1 | 264 | 0 | 65 | 406 | Field Inspection (FIR) |  | 5477 | 5427 | 0 | [7 empty] | MTC (Healed w/ Disability) |  | 0 |  | 0 | 0 | 0
Electrical |  | 220 | 3 | 214 | 0 | 0 | 220 | 0 | 0 | 220 | Key Submittals Approval Status | [11 empty] | Near Miss |  | 0 |  | 0 | 0 | 0
TOTAL |  | 1427 | 9 | 1478 | 0 | 110 | 1245 | 0 | 65 | 1497 | 1 Quality Plan Approval |  |  | 2026-02-09 |  | 6 Baseline Approval |  |  |  | 2025-12-18 |  |  | First Aid Cases |  | 0 |  | 0 | 0 | 0 | Total Hours Worked Vs Safe Hours Worked
Material Approval | [10 empty] | 2 Quality Plan Last Up |  |  | - |  | 7 No of Approved Version of Schedule |  |  |  | 1 |  |  | Fatality |  | 0 |  | 0 | 0 | 0
Item Per WBS |  | Total | Total Submitted Material |  |  |  |  | Remaining to approve | Pending | Total Submittals | 3 Safety Plan Approval |  |  | 2026-02-03 |  | 8 Last Approved Schedule |  |  |  | - |  |  | Fire Incident Cases |  | 0 |  | 0 | 0 | 0
|  |  | A | B | C | D | Processed | with Designer |  |  | 4 Safety Plan Last Up |  |  | - |  | 9 BOQ Approval Date |  |  |  | 2025-11-19 |  |  | Vehicle Incident |  | 0 |  | 0 | 0 | 0
Civil /Structural /Architectural |  | 95 | 2 | 90 | 0 | 1 | 92 | 0 | 0 | 95 | 5 Construction Plan Approval |  |  | 2026-02-05 |  | 10 No of Approved Version of BOQ |  |  |  | 0 |  |  | Property Damages |  | 0 |  | 0 | 0 | 0
Mechanical |  | 33 | 2 | 33 | 0 | 0 | 33 | 0 | 0 | 33 | Invoices Summary | [10 empty] | Proactive | Induction Training |  | 0 session |  | 0 session | 63 | 63
Electrical |  | 22 | 0 | 16 | 0 | 6 | 16 | 0 | 0 | 22 | Total Submitted Invoices |  | 6 | Submitted Invoices (SAR) |  |  | 44851849.3625 |  | Contract Value (SR) | 86782345 |  |  | No.of Internal Training |  | 0session |  | 0 session | 61 | 61
[11 empty] | PM Approved Invoices |  | 7 | PM Approved Invoices (SAR) |  |  | 51579626.7669 |  | Planned Value (SR) | 46153496.77 |  |  | No.of Internal Audit |  | 0 |  | 0 | 0 | 0
[11 empty] | No of Paid Invoices |  | 6 | Paid Invoices (SAR) |  |  | 48055957.6059 |  | Earned Value (SR) | 68315968.83 |  |  | No. of Toolbox Talks |  | 0 sessions |  | 0 sessions | 88 | 88
TOTAL |  | 150 | 4 | 139 | 0 | 7 | 141 | 0 | 0 | 150 | No of Pending Invoices |  | 0 | Last Submitted Period |  |  | 2026-09-29 |  | Submitted (SAR) | 44851849.3625 |  |  | Safety Awards/Incentives |  | 0 |  | 0 | 0 | 0
Procurement Summary | [10 empty] | Advance Payment % |  | 0% | Advance Payment (SAR) |  |  | 0 |  | PM Approved (SAR) | 51579626.7669 |  | Latest Contract Change Order Log
Item Per WBS |  | Total Materials | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Material on Site | Remaining Materials | Material Delivery Completion (Date) |  |  | Retention % |  | 0% | Retention (SAR) |  |  | 0 |  | Total Paid (SAR) | 48055957.6059
|  |  | A | B | C | D | Processed |  |  |  | Deduction / Penalties % |  | 0% | Deduction / Penalties (SAR) |  |  | 0 |  |  |  |  | CCO No. | Date Added | Description of Change |  |  |  |  | Status | Cost | Sch Impact (Months) | Date Approved | Duration
Civil /Structural /Architectural |  | 31 | 31 | 31 | 0 | 28 | 3 | 2027-05-19 |  |  | Resources at Site
Mechanical |  | 19 | 19 | 19 | 0 | 19 | 0 | 2027-06-29 |  |  | Head Count - Manual |  |  |  | Head Count - Non Manual |  |  |  | Total Head Count |  |  | - | - | - |  |  |  |  | - | - | - | - | -
Electrical |  | 63 | 63 | 58 | 5 | 58 | 5 | 2027-03-11 |  |  | Planned | Actual | Next Month Forecast | Saudi Staff | Planned | Actual | Next Month Forecast | Saudi Staff | Total Plan | Total Actual | Variance
[11 empty] | 148 | 130 | 187 | 0 | 22 | 48 | 40 | 6 | 170 | 178 | 8
[11 empty] | Manpower Breakdown by Trade | [6 empty] | Major Equipment
TOTAL |  | 113 | 113 | 108 | 5 | 105 | 8 | 2027-06-29 |  |  | Key Trade | Planned | Actual |  |  |  |  | Type | Planned | Actual | Idle
Primavera P6 Schedule Status | [10 empty] | Labor | 40 | 17 |  |  |  |  | Excavator | 3 | 4 | 0
Project Activities Overview | [10 empty] | Skilled Labor | 26 | 30 |  |  |  |  | Bulldozer | 2 | 1 | 0 | Major Quantity Trackers
Schedule Statistics |  |  |  |  | Active Schedule Activities | [5 empty] | Driver / Operator | 60 | 48 |  |  |  |  | Grader | 4 | 1 | 0 | BOQ N0. | Item Description |  |  |  |  | Total Qty | Measu Unit | Plan to Date | Act to Date | Remaining | Variance
Total Act. | Not Started | In Progress | Completed | % | Active | Ahead | On | Behind | Flag | 0 | Carpenter | 5 | 6 |  |  |  |  | Road Roller | 3 | 3 | 0 | 31 22 00.02 | Parcrels Excavation for cuttings (all types of soil) |  |  |  |  | 123555 | m3 | 123555 | 123555 | 0 | 0
1905 | 423 | 204 | 1278 | 67.09% | 204 | 91 | 0 | 113 | -22 |  | Steel Fixer | 5 | 9 |  |  |  |  | Crane | 2 | 1 | 0 | 31 22 00.05 | Subgrade |  |  |  |  | 34693.65 | m3 | 34693.65 | 34693.65 | 0 | 0
Critical Path Activities |  |  | Free Float Management (Total) |  |  |  | Failed Start Activities |  |  |  | Mason | 2 | 0 |  |  |  |  | Aggregate paver | 0 | 0 | 0 | 32 11 26.01 | Bituminous base course (Grading I - Class A), including Prime Coat (MC1) according to drawings |  |  |  |  | 8290 | m3 | 8290 | 8290 | 0 | 0
|  |  | Greater Than 14 Days |  | Less Than 14 Days | [5 empty] | Plumber | 8 | 7 |  |  |  |  | Other | 28 | 10 | 0 | 32 12 16.01 | Bituminous concrete wearing course, (Grading I - Class A), including tack coat (RC2) according to drawings. |  |  |  |  | 5920 | m3 | 0 | 2074 | 3846 | 2074
Last Week | This Week | Diff | Last Week | This Week | Last Week | This Week | Last Week | This Week | Flag | 0 | Total | 148 | 130 |  |  |  |  | Total | 42 | 20 | 0 | 33 42 11 | GRP Pipes for Storm network |  |  |  |  | 5650 | m | 5650 | 5650 | 0 | 0
460 | 457 | 3 | 71 | 68 | 1834 | 1837 | 107 | 113 | -6 | [6 empty] | Top Issues and Risks
Testing And Commissioning
Top 5 Issues
Item | Planned Start Date |  | Planned Finish Date |  | Forecast Start Date |  | Forecast Finish Date |  | Actual Start Date |  | Actual Finish Date | % Completed | Open Comments | Closed Comments | Issue No |  | Date Identified | Issue Description |  |  | Responsible |  | Action Taken |  |  |  |  | Mitigation |  |  | Current Status | Expected/Actual Closure | Duration Elapsed
Test for Irrigation and Landscape | 2027-10-19 |  | 2027-10-26 |  | 2028-02-24 |  | 2028-03-02 | [7 empty] | 1 |  | 2025-12-15 | Update of Aggrement between MODON and SEC for Medium Voltage |  |  | Owner |  | 1. MODON contacted with SEC for getting Electric Source and it is under Process from SEC 2. Enjazco waiting for responding on Lettter No. (2818) 13.01.2026 | [7 empty] | Open | 2025-12-30
Test for Earthing System | 2027-10-20 |  | 2027-10-26 |  | 2027-12-15 |  | 2027-12-22 |  | 2026-08-01 |  |  | 30% |  |  | 2 |  | 2025-11-25 | Permits from (SEC - STC - NWC) for allowing Construction works for Tie-in Lines (Sewer Line - TSE Line - Potable Water Line) |  |  | Contractor |  | Coordination done with all Servse Providers (STC - NWC - SEC (HV)) | [7 empty] | closed | 2026-02-10
Test for CCTV feeding system and GSM | 2027-10-13 |  | 2027-10-19 |  | 2027-12-08 |  | 2027-12-15 |  | 2026-08-01 |  |  | 35% |  |  | 3 |  |  | Supplier Approval not included in Vendor List :: Pre-Qualification for Post Tension Works, Bearings and Expansion Joints Scope NOT IN VENDOR LIST Emirates Elite Trading Co. (ECO) Freyssinet Menard Saudi Arabia Ltd AL-BUNYAN EST. LT |  |  | Owner |  | PQD Submitted to Egis For Approval | [7 empty] | closed
Test for Telecommunications Work | 2027-10-06 |  | 2027-10-12 |  | 2027-12-01 |  | 2027-12-08 |  | 2026-08-01 |  |  | 30% |  |  | 4
Test for Road Lighting | 2027-09-29 |  | 2027-10-05 |  | 2027-11-24 |  | 2027-12-01 |  | 2026-08-01 |  |  | 30%
Test for Electrical Network | 2027-09-11 |  | 2027-09-19 |  | 2027-11-10 |  | 2027-11-20 |  | 2026-08-01 |  |  | 30%
Test for Road Works | 2027-08-04 |  | 2027-08-12 |  | 2027-10-16 |  | 2027-10-24 |  | 2026-08-01 |  |  | 70%
Test for Fence & Gate | 2027-10-19 |  | 2027-10-25 |  | 15-Jun-26 A |  | 2027-11-04 |  | 2026-06-15 |  |  | 60%
Test for Bridge Work | 2027-09-01 |  | 2027-09-09 |  | 15-Jun-26 A |  | 2027-11-10 |  | 2026-06-15 |  |  | 70%
Test for Stormwater Utilities | 2027-08-23 |  | 2027-08-31 |  | 15-Jun-26 A |  | 2027-11-04 |  | 2026-06-15 |  |  | 70%
Test for Sanitary Sewerage | 2027-08-14 |  | 2027-08-22 |  | 15-Jun-26 A |  | 2027-10-30 |  | 2026-06-15 |  |  | 75%
Test for TSE Network | 2027-09-20 |  | 2027-09-28 |  | 15-Jun-26 A |  | 2027-11-24 |  | 2026-06-15 |  |  | 75%
Test for Public Water Utility Distribution | 2027-08-14 |  | 2027-08-22 |  | 15-Jun-26 A |  | 2027-10-30 |  | 2026-06-15 |  |  | 75%
6,407,407

## General Information
Weekly Progress Report - Construction Projects |  |  | Data Date | 2026-10-20
Contract General Information |  |  | Week No. | 47.8571
Project Name | INFRASTRUCTURE DEVELOPMENT FOR INDUSTRIAL CITY 1 IN JEDDAH
Project ID | JDH1-02-003
Contractor | Al Enjaz Company for Trading and Contracting
Consultant | Saudi Arabia Consulting Engineering Company "EGIS"
Stage | Construction
Status | Active
Modon PM | Engr.Abdallah Aljulayfi
Key Dates
Contract Award Date | 2025-11-02
Contract Sign Date | 2025-11-13
Site Handover Date | 2025-11-19
Original Completion | 2027-11-18
Contract Award Date (Hijri) | 2025-11-02
Contract Sign Date (Hijri) | 2025-11-13
Site Handover Date (Hijri) | 2025-11-19
Original Completion (Hijri) | 2027-11-18
Revised Completion Date | 2027-11-18
Committed Completion Date | 2027-11-18
Forecast Completion | 2028-05-20
Variance | -184
Key Project Submittals | Submission Date | Days taken to approve orginal plan from site handover date
Quality Plan submission | 2025-11-25 | 6
Quality Plan approval | 2026-02-09
Quality Plan Last Update | -
Safety Plan submission | 2025-12-10 | 21
Safety Plan approval | 2026-02-03
Safety Plan Last Update | -
Risk Management Plan submission | 2025-12-15 | 26
Risk Management Plan approval | 2025-12-18
Risk Management Plan Last Update | -
Baseline Schedule submission | 2025-12-16 | 27
Baseline Schedule approval | 2025-12-18
No of Schedule Versions | 1
Last Revised Schedule Approval Date | -
BOQ submission | 2025-11-19 | 0
BOQ approval | 2025-11-19
No of Approved Version of BOQ
Execution Plan submission | 2025-11-25 | 6
Execution Plan Approval | 2026-02-05
Note on D25: AlNuaim, Abdulaziz: As per contract requirments submission of Plans should be 30 days after site handover

## Progress
Project Scope Statement
Earned Value Progress (SAR) | [10 empty] | Physical Progress (Effort)
WBS |  | BOQ Value (SAR) | % Wt. | Weekly (SAR) |  |  | To Date (SAR) |  | Actual % |  | Budgeted | % Wt. | Weekly Physical Progress |  | To Date Physical Progress |  |  |  | Last Week Cost (SAR) |  | Last Week Physical Progress
|  |  |  | Planned | Earned | Original Plan | Planned | Earned |  |  | (Manhours) |  | Planned | Earned | Planned | Earned |  | 5508011.04 | Planned | Earned | Planned | Earned
Mobilization |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% |  | 20050 | 2.806% | 0 | 0 | 20050 | 20050 |  | 0 | 0 | 0 | 20050 | 20050
Engineering |  | 2601460.39 | 2.998% | 0 | 0 | 2601460.39 | 2601460.39 | 2579200.39 | 2.972% |  | 33415 | 4.676% | 0 | 0 | 33415 | 33009.2 |  | 0 | 2601460.39 | 2579200.39 | 33415 | 33009.2
Procurement |  | 17355662.1 | 20% | 26504 | 208500 | 13492073.1 | 13518577.1 | 15737880.1 | 18.13% |  | 82413.81 | 11.53% | 0 | 0 | 35843.52 | 65032.49 |  | 188986338% | 13492073.1 | 15529380.1 | 35843.52 | 65032.49
Construction |  | 58147531.04 | 67% | 394580.51 | 190111.17 | 29638878.78 | 30033459.29 | 44572325.02 | 51.36% |  | 545268.46 | 76.31% | 5590.01 | 1907.14 | 246436.59 | 390120.29 |  | 152080744% | 29638878.78 | 44382213.85 | 240846.58 | 388213.15
Site Demolition |  | 279942.75 | 0.3226% | 0 | 0 | 279942.75 | 279942.75 | 279942.75 | 0.3226% |  | 7350 | 1.029% | 0 | 0 | 7350 | 7350 |  | 2097340.22 | 279942.75 | 279942.75 | 7350 | 7350
Roads & Meduim Voltage |  | 11810038.74 | 13.61% | 0 | 0 | 11810038.74 | 11810038.74 | 8650438.79 | 9.968% |  | 100175 | 14.02% | 0 | 0 | 100175 | 73591 |  | 957625.34 | 11810038.74 | 8650438.79 | 100175 | 73591
Deep Infrastructure network |  | 10009830.2 | 11.53% | 10082.82 | 7209.5 | 9958787.21 | 9968870.03 | 9750710.5 | 11.24% |  | 54025 | 7.561% | 0 | 0 | 54025 | 51820.5 |  | 583145.23 | 9958787.21 | 9743501 | 54025 | 51820.5
Shallow infrastructure network |  | 12539076.3 | 14.45% | 209087.15 | 99253.79 | 2810927.82 | 3020014.97 | 10453768.19 | 12.05% |  | 198577.38 | 27.79% | 4687.15 | 1717.15 | 43207.03 | 154727.25 |  | 55656964% | 2810927.82 | 10354514.4 | 38519.88 | 153010.1
Bridge |  | 2513306.98 | 2.896% | 15291.43 | 0 | 1320006.88 | 1335298.31 | 1830342.88 | 2.109% |  | 14022.14 | 1.962% | 171.43 | 0 | 7721.43 | 12207.14 |  | 0 | 1320006.88 | 1830342.88 | 7550 | 12207.14
Outside Boundary Area (Tie-in Lines) |  | 2681726.27 | 3.09% | 71160.39 | 0 | 1339359.49 | 1410519.88 | 2663147.17 | 3.069% |  | 19949.2 | 2.792% | 681.43 | 0 | 9933.13 | 19885.03 |  | 0 | 1339359.49 | 2663147.17 | 9251.7 | 19885.03
Roads Finishing |  | 8138565 | 9.378% | 0 | 83647.88 | 0 | 0 | 5591559.17 | 6.443% |  | 65951.79 | 9.23% | 0 | 190 | 0 | 45112.37 |  |  | 0 | 5507911.29 | 0 | 44922.37
Fence and Gate |  | 8127691.9 | 9.366% | 88958.71 | 0 | 2119815.89 | 2208774.6 | 5352415.58 | 6.168% |  | 43715 | 6.118% | 50 | 0 | 24025 | 25427 |  |  | 2119815.89 | 5352415.58 | 23975 | 25427
Roundabout & Landscape |  | 2047352.9 | 2.359% | 0 | 0 | 0 | 0 | 0 | 0% |  | 41502.94 | 5.808% | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Testing & Commissioning |  | 8677691.2 | 9.999% | 0 | 0 | 0 | 0 | 5426563.31 | 6.253% |  | 20050 | 2.806% | 0 | 0 | 0 | 10646.5 |  |  | 0 | 5426563.31 | 0 | 10646.5
Project Close-out |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% |  | 13364 | 1.87% | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | [7 empty] | 0 | 0
|  |  |  | 0 | 0 | [7 empty] | 0 | 0
|  |  |  | 0 | 0 | [7 empty] | 0 | 0
| Total | 86782344.73 | 100% | 421084.5 | 398611.17 | 45732412.27 | 46153496.77 | 68315968.83 | 78.72% |  | 714561.26 | 100% | 5590.01 | 1907.15 | 335745.11 | 518858.48 |  |  | 45732412.27 | 67917357.66 | 330155.1 | 516951.33
[6 empty] | 52.7% | 53.18% | 78.72% | [6 empty] | 46.99% | 72.61%
-25.54%
Activity ID | Activity Name | Original Duration | Budgeted Total Cost | Planned Value Cost | Earned Value Cost | Budgeted Labor Units | Planned Value Labor Units | Earned Value Labor Units
JDH1-02-003 - Infrastructure Development For Industrial City 1 In Jeddah - Update - 20.10.2026 |  | 763 | 86782344.73 | 46153496.78 | 68315968.81 | 714561.27 | 347982.15 | 528822.75 | 461520.15 | 67302.6
Milestones |  | 763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mobilization |  | 112 | 0 | 0 | 0 | 20050 | 20050 | 20050 | 20050 | 0
Engineering |  | 287 | 2601460.39 | 2601460.39 | 2579200.39 | 33415 | 33415 | 33009.2 | 33009.2 | 0
Procurement |  | 502 | 17355662.1 | 13518577.1 | 15737880.1 | 82413.81 | 48080.56 | 74996.76 | 65032.49 | 9964.27
Construction |  | 710 | 58147531.04 | 30033459.29 | 44572325.02 | 545268.46 | 246436.59 | 390120.29 | 339660.46 | 50459.83
Site Demolition |  | 93 | 279942.75 | 279942.75 | 279942.75 | 7350 | 7350 | 7350 | 7350 | 0
Roads & Meduim Voltage |  | 423 | 11810038.74 | 11810038.74 | 8650438.79 | 100175 | 100175 | 73591 | 72812.5 | 778.5
Deep Infrastructure network |  | 277 | 10009830.2 | 9968870.03 | 9750710.5 | 54025 | 54025 | 51820.5 | 51617.5 | 203
Shallow infrastructure network |  | 433 | 12539076.3 | 3020014.97 | 10453768.19 | 198577.38 | 43207.03 | 154727.25 | 126285.02 | 28442.23
Bridge |  | 452 | 2513306.98 | 1335298.31 | 1830342.88 | 14022.14 | 7721.43 | 12207.14 | 11391.07 | 816.07
Outside Boundary Area (Tie-in Lines) |  | 419 | 2681726.27 | 1410519.88 | 2663147.17 | 19949.2 | 9933.13 | 19885.03 | 17900.29 | 1984.74
Roads Finishing |  | 204 | 8138565 | 0 | 5591559.17 | 65951.79 | 0 | 45112.37 | 29496.58 | 15615.79
Fence and Gate |  | 558 | 8127691.9 | 2208774.6 | 5352415.58 | 43715 | 24025 | 25427 | 22807.5 | 2619.5
Roundabout & Landscape |  | 226 | 2047352.9 | 0 | 0 | 41502.94 | 0 | 0 | 0 | 0
Testing & Commissioning |  | 167 | 8677691.2 | 0 | 5426563.31 | 20050 | 0 | 10646.5 | 3768 | 6878.5
Project Close-out |  | 145 | 0 | 0 | 0 | 13364 | 0 | 0 | 0 | 0
[5 empty] | Activity ID | Activity Name | Original Duration | BL Project Start | BL Project Finish |  | Start | Finish | Planned Value Cost | Actual Total Cost | Earned Value Cost | Schedule % Complete | Performance % Complete | Budgeted Total Cost |  | Actual Labor Units | Earned Value Labor Units | Total Float
[5 empty] | Construction of 32 RBF's (900m2) in Jeddah 2 Industrial City |  | 359 | 2025-04-27 | 2026-06-25 |  | 26-Apr-25 A | 2026-07-01 | 26937516.67 | 26297180.31 | 26898066.69 | 38.27% | 38.21% | 70392244.33 |  | 19616 | 19774.6 | -5

## Weekly Photos
|  | Data Date | 2026-10-20
L01 - Installation of Telecom Pipes | Curbstone works
L01 - Backfilling of Telecom Pipes | Interlock works
Interlock works | Installation of street lights fuse box of local 1
Installation of Light Poles | Excavation of irrigation main pipes in plot no 10 for landscaping

## Major Quantities
BOQ Number | Description of Item | Total Quantity | Unit of Measurement | Plan To Date | Actual To Date | Remaining Total | Variance
31 22 00.01 | Excavation for Roadway, fences and bridge, cuttings including dump locations (all types of soil) | 116177.4 | m3 | 116177.4 | 116177.4 | 0 | 0
31 22 00.02 | Parcrels Excavation for cuttings (all types of soil) | 123555 | m3 | 123555 | 123555 | 0 | 0
31 22 00.03 | Embankments to the roads , fences and bridge. | 80919.7 | m3 | 80919.7 | 80919.7 | 0 | 0
31 22 00.04 | Embankments to the parcels | 94645 | m3 | 94645 | 94455.71 | 189.29 | -189.29
31 22 00.05 | Subgrade | 34693.65 | m3 | 34693.65 | 34693.65 | 0 | 0
32 11 23.01 | Aggregate base course | 23129.1 | m3 | 23129.1 | 23129.1 | 0 | 0
32 11 26.01 | Bituminous base course (Grading I - Class A), including Prime Coat (MC1) according to drawings | 8290 | m3 | 8290 | 8290 | 0 | 0
32 12 16.01 | Bituminous concrete wearing course, (Grading I - Class A), including tack coat (RC2) according to drawings. | 5920 | m3 | 0 | 2074 | 3846 | 2074
33 42 11 | GRP Pipes for Storm network | 5650 | m | 5650 | 5650 | 0 | 0 | 100%
33 14 13 | High Density Polyethylene pipes PE 100 SDR 11 (PN 16 Bars) | 12075.28 | m | 6979.5118 | 12075 | 0.28 | 5095.4882 | 100%
33 14 13 | High Density Polyethylene pipes PE 100 SDR 11 (PN 16 Bars) | 8722 | m | 6393.226 | 8700 | 22 | 2306.774 | 99.75%
33 31 00 | Glass Reinforced Plastic (GRP) for Sewer network | 6244 | m | 6244 | 6244 | 0 | 0 | 100%
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0

## Quality
QC OBSERVATIONS CHECKLIST
Project No. |  |  | JDH1-02-003 |  |  | OBS No. |  |  |  | 47.8571 |  |  | Inspection Day: |  | 2026-10-20
Project |  |  | INFRASTRUCTURE DEVELOPMENT FOR INDUSTRIAL CITY 1 IN JEDDAH | [6 empty] | Contractor: |  |  | Al Enjaz Company for Trading and Contracting
[10 empty] | Consultant: |  |  | EGIS Saudi ARABIA CONSULTANT ENGINEERING COMPANY
4 |  | Excellent |  | Quality Management System is being practiced and applies to MODON System | [11 empty] | 90 - 100 |  | QC Overall Score | 85.21% |  |  |  |  | 0% | 100 | 0.22883
3 |  | Good |  | Evidence of compliance with plans and procedures. | [11 empty] | 80 - 89 | [7 empty] | 0 | 89 | 0.20366
2 |  | Average |  | Indication level of compliance with standards but there is room for improvement | [11 empty] | 70 - 79 | [8 empty] | 79 | 0.18078
1 |  | Improve |  | Quality and Control is NOT being managed effectively. Needs Improvement | [11 empty] | ≤ 69 | [8 empty] | 69 | 0.15789
0 |  | N/A |  | Item was not applicable or this item was not reviewed during the inspection. | [11 empty] | Zero | [8 empty] | 100 | 0.22883
No. | Topic |  |  |  |  | E (4) | G (3) | A (2) | I (1) | N/A (0) | No. | Topic |  |  |  | E (4) | G (3) | A (2) | I (1) | N/A (0) |  |  |  |  | 437
[6 empty] | 100% | 89% | 79% | 69% | 100% | [5 empty] | 100% | 89% | 79% | 69% | 100% | 85.21%
1 | Control of Access to Site/Office | [5 empty] | 1 |  | 0 |  | 30 | QC of Excavation | [5 empty] | 1 | 0 | 0 | 0.89 | 0.79 | [6 empty] | Item Count | Score | Distributtion
2 | Document Control Administration | [5 empty] | 1 | 0 | 0 |  | 31 | QC of Roads/Round about | [5 empty] | 1 | 0 | 0 | 0.89 | 0.79 | [8 empty] | Overall | Relevant
3 | Project Documents and Progress | [5 empty] | 1 | 0 | 0 |  | 32 | QC of Interlock & Curbstone | [5 empty] | 1 |  |  | 0.89 | 0.79 | 4 | 58 | counts |  | 4 | Excellent | 0 | 0 | 0% | 0%
4 | Contractor's Quality Plan/CM (Updated and Reviewed) | [6 empty] | 1 |  |  | 33 | Layers/Backfilling Sampling | [5 empty] | 1 | 0 | 0 | 0.79 | 0.79 | 3 | 58 | counts |  | 3 | Good | 15 | 45 | 25.86% | 31.25%
5 | MS Log and Paperwork | [6 empty] | 1 |  |  | 34 | Pump Stations Units | [7 empty] | 1 | 0.79 | 1 | 2 | 58 | counts |  | 2 | Average | 33 | 66 | 56.9% | 68.75%
6 | RFI, FIR, & MIR Procedure | [6 empty] | 1 | 0 |  | 35 | Quality of Form Work | [5 empty] | 1 |  | 0 | 0.79 | 0.79 | 1 | 58 | counts |  | 1 | Improve | 0 | 0 | 0% | 0%
7 | RFI, FIR, & MIR Inventory system | [5 empty] | 1 | 0 | 0 |  | 36 | Design Change List | [7 empty] | 1 | 0.89 | 1 | 0 | 58 | counts |  | 0 | N/A | 10 | 0 | 17.24% | -
8 | NCRs Control & Procedure | [6 empty] | 1 | 0 |  | 37 | Quality of Concrete Placing | [5 empty] | 1 | 0 | 0 | 0.79 | 0.79 | [5 empty] | Total | 58 | 111 | 100% | 100%
9 | NCR Log | [5 empty] | 1 | 0 | 0 |  | 38 | Concrete Surface Finishing | [5 empty] | 1 |  | 0 | 0.89 | 0.79
10 | MODON Standard* | [6 empty] | 1 | 0 |  | 39 | Pedestals/Columns/Beams Alignment | [5 empty] | 1 |  | 0 | 0.79 | 0.79 | [6 empty] | Maz Score Available: | 192 | <- Excludes N/A items
11 | Project Risk Plan/Management* | [6 empty] | 1 | 0 |  | 40 | Siporex Lifting & Unloading | [7 empty] | 1 | 0.79 | 1
12 | Monthly Quality Reports* | [5 empty] | 1 | 0 | 0 | 0 | 41 | Siporex Quality Pre-installation | [7 empty] | 1 | 0.89 | 1
13 | ITP | [6 empty] | 1 |  |  | 42 | Siporex Finishing Quality | [7 empty] | 1 | 0.79 | 1 | [5 empty] | Total Score |  | Percentage (%)
14 | MODON Weekly Report | [5 empty] | 1 | 0 |  |  | 43 | Roads / Parking Markings | [5 empty] | 1 |  |  | 0.89 | 0.79 |  | 58 |  |  |  | 111 |  | 57.8125 |  | %
15 | Design Change Official Paperwork* | [5 empty] | 1 |  |  |  | 44 | QC of Finishing Outdoors | [5 empty] | 1 |  |  | 0.89 | 0.79 | [5 empty] | Max Score Available |  |  |  |  | 31
16 | Design Change was Applied* | [5 empty] | 1 |  |  |  | 45 | Quality of Finishing Indoors | [7 empty] | 1 | 0.89 | 1 | [5 empty] | 192 |  |  |  |  | 32
17 | Material List | [5 empty] | 1 | 0 |  | 0 | 46 | Stairs Quality | [7 empty] | 1 | 0.89 | 1 | [10 empty] | 33
18 | Pending Material Status | [5 empty] | 1 | 0 |  |  | 47 | Tanks Method Statement Work | [7 empty] | 1 | 0.89 | 1 | [10 empty] | 34
19 | Lifting Plan* | [6 empty] | 1 |  |  | 48 | Electric Rooms | [5 empty] | 1 |  |  | 0.79 | 0.79 | [10 empty] | 35
20 | DWG Log | [5 empty] | 1 |  |  |  | 49 | QC of MCC/ATS Plant Units | [5 empty] | 0 |  | 1 | 0.89 | 1 | [10 empty] | 36
21 | Invoice Status | [5 empty] | 1 |  |  |  | 50 | Qualified Subcontractor | [5 empty] | 1 |  | 0 | 0.89 | 0.79 | [10 empty] | 37
22 | Site Handover Letter | [8 empty] | 1 | 51 | Scaffold/Ladders/Slope/Bridge Compliance | [5 empty] | 1 |  |  | 1 | 0.79 | [10 empty] | 38
23 | Material Testing Results & Certification | [5 empty] | 1 | 0 |  |  | 52 | Protection Applied to Completed Work | [5 empty] | 1 |  | 0 | 0.89 | 0.79
24 | As Build Drawings Status* | [6 empty] | 1 |  |  | 53 | Storage Management in/out Control | [5 empty] | 1 | 0 |  | 0.79 | 0.79
25 | Calibrated Lab Tools & Equipment | [5 empty] | 1 | 0 |  | 0 | 54 | Material Control | [5 empty] | 1 | 0 | 0 | 0.89 | 0.79
26 | Storage Inventory System | [6 empty] | 1 |  |  | 55 | Manholes Storing and Quality | [5 empty] | 1 | 0 | 0 | 0.79 | 0.79
27 | Logistics Plan | [6 empty] | 1 |  |  | 56 | Reinforced Steel Quality | [5 empty] | 1 | 0 | 0 | 0.79 | 0.79
28 | Project Progress Planview | [6 empty] | 1 |  |  | 57 | Safety Overview | [5 empty] | 1 | 0 | 0 | 0.79 | 0.79
29 | Sufficient Number of QC Inspectors | [6 empty] | 1 |  |  | 58 | Waste Management Control | [5 empty] | 1 |  | 0 | 0.79 | 0.79
Score
[8 empty] | *QC % |  |  | 85.21%
Prepared by: |  |  |  | Imtiyaz Khan | [6 empty] | Issued to PM: |  |  | Engr.Abdallah Aljulayfi
*QC Observations refer only to the practices and documentation observed at time of inspection. The responsibility of the CM and Contractor is to ensure that aspects of Quality are suitably managed. *Scores are a reflection of the general site conditions based upon the findings at the time of the walk through *If Applicable

## Quality-Stat
Quality Reports
Item |  |  | Issued | A | B | C | D | Approved
[9 empty] | Remaining | Submittals With Consultant | Total Submittals
Non Conforomance Report (NCR) |  |  | 16 | 0 | 16 | 0 | 0 | 16 | 0 | 0 | 16
Site Instruction (SI) |  |  | 21 | 0 | 21 | 0 | 0 | 21 | 0 | 0 | 21
Material Inspection Report (MIR) |  |  | 100 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 100
Field Inspection Report (FIR) |  |  | 5477 | 905 | 4522 | 5 | 0 | 5427 | 0 | 45 | 5477
Shop Drawings
Item Per WBS |  |  | Total IFC | Total Drawings Submitted |  |  |  |  | Remaining Drawings | Pending | Total Submittals
|  |  |  | A | B | C | D | Processed | with Designer | Submittals With Consultant
Roads |  |  | 268 | 2 | 266 | 0 | 0 | 268 |  | 0 | 268
General |  |  | 11 | 0 | 11 | 0 | 0 | 11 |  | 0 | 11
Structural |  |  | 590 | 2 | 588 | 0 | 109 | 480 |  | 0 | 590
Architectural |  |  | 2 | 0 | 2 | 0 | 0 | 2 |  | 0 | 2
Mechanical |  | Mechanical | 336 | 2 | 397 | 0 | 1 | 264 |  | 65 | 406
Electrical |  | Electrical | 220 | 3 | 214 | 0 | 0 | 220 |  | 0 | 220
TOTAL |  |  | 1427 | 9 | 1478 | 0 | 110 | 1245 |  | 65 | 1497
Material Approval
Item Per WBS |  |  | Total | Total Materials Submitted |  |  |  |  | Remaining to approve | Pending | Total Submittals
|  |  |  | A | B | C | D | Processed | with Designer | Submittals With Consultant
Civil /Structural /Architectural |  |  | 95 | 2 | 90 | 0 | 1 | 92 |  | 0 | 95
Mechanical |  | Mechanical | 33 | 2 | 33 | 0 | 0 | 33 |  | 0 | 33
Electrical |  | Electrical | 22 | 0 | 16 | 0 | 6 | 16 |  | 0 | 22
TOTAL |  |  | 150 | 4 | 139 | 0 | 7 | 141 |  | 0 | 150
Procurement Summary
Item Per WBS |  |  | Total Materials | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Actual Material on Site | Remaining Materials | Material Delivery Completion (Date)
|  |  |  | A | B | C | D | Processed
Civil /Structural /Architectural |  |  | 31 | 31 | 31 | 0 | 28 | 3 | 2027-05-19
Mechanical |  | Mechanical | 19 | 19 | 19 | 0 | 19 | 0 | 2027-06-29
Electrical |  | Electrical | 63 | 63 | 58 | 5 | 58 | 5 | 2027-03-11
TOTAL |  |  | 113 | 113 | 108 | 5 | 105 | 8
Consultant Quality Inspections / Observations (Weekly Basis) | [7 empty] | Overall Average | 82.81% |  | Average Closing | 2.3415
Week Number | Date of Audit | Date Issued | Numbers Of Comments | Quality Score | Date Closed | Closure Duration |  | This Week Score | 85.21% |  | Average Number of Comments Per Audit | 3.0732
Week-1 | 2025-11-25
Week-2 | 2025-12-02
Week-3 | 2025-12-09
Week-4 | 2025-12-16
Week-5 | 2025-12-23
Week-6 | 2025-12-30 | 2025-12-27 | 3 | 80% | 2025-12-28 | 1
Week-7 | 2026-01-06 | 2026-01-02 | 2 | 70% | 2026-01-04 | 2
Week-8 | 2026-01-13 | 2026-01-09 | 4 | 72% | 2026-01-11 | 2
Week-9 | 2026-01-20 | 2026-01-15 | 6 | 75% | 2026-01-18 | 3
Week-10 | 2026-01-27 | 2026-01-21 | 4 | 75% | 2026-01-24 | 3
Week-11 | 2026-02-03 | 2026-01-31 | 2 | 80% | 2026-02-02 | 2
Week-12 | 2026-02-10 | 2026-02-06 | 5 | 75% | 2026-02-09 | 3
Week-13 | 2026-02-17 | 2026-02-12 | 4 | 80% | 2026-02-15 | 3
Week-14 | 2026-02-24 | 2026-02-21 | 3 | 81% | 2026-02-23 | 2
Week-15 | 2026-03-03 | 2026-02-26 | 4 | 72% | 2026-03-01 | 3
Week-16 | 2026-03-10 | 2026-03-07 | 3 | 80% | 2026-03-08 | 1
Week-17 | 2026-03-17 | 2026-03-12 | 4 | 80% | 2026-03-15 | 3
Week-18 | 2026-03-24
Week-19 | 2026-03-31 | 2026-03-29 | 1 | 85% | 2026-03-30 | 1
Week-20 | 2026-04-07 | 2026-04-04 | 2 | 85% | 2026-04-05 | 1
Week-21 | 2026-04-14 | 2026-04-11 | 1 | 85% | 2026-04-12 | 1
Week-22 | 2026-04-21 | 2026-04-17 | 3 | 88% | 2026-04-19 | 2
Week-23 | 2026-04-28 | 2026-04-24 | 3 | 80% | 2026-04-26 | 2
Week-24 | 2026-05-05 | 2026-05-02 | 3 | 86% | 2026-05-03 | 1
Week-25 | 2026-05-12 | 2026-05-09 | 2 | 86% | 2026-05-10 | 1
Week-26 | 2026-05-19 | 2026-05-16 | 2 | 86% | 2026-05-17 | 1
Week-27 | 2026-05-26
Week-28 | 2026-06-02 | 2026-05-30 | 1 | 86% | 2026-05-31 | 1
Week-29 | 2026-06-09 | 2026-06-05 | 1 | 86% | 2026-06-07 | 2
Week-30 | 2026-06-16 | 2026-06-14 | 3 | 86% | 2026-06-16 | 2
Week-31 | 2026-06-23 | 2026-06-20 | 4 | 84% | 2026-06-22 | 2
Week-32 | 2026-06-30 | 2026-06-27 | 3 | 85% | 2026-06-29 | 2
Week-33 | 2026-07-07 | 2026-07-02 | 4 | 84% | 2026-07-05 | 3
Week-34 | 2026-07-12 | 2026-07-11 | 3 | 85% | 2026-07-12 | 2
Week-35 | 2026-07-21 | 2026-07-18 | 4 | 84% | 2026-07-20 | 2
Week-36 | 2026-07-28 | 2026-07-23 | 5 | 84% | 2026-07-27 | 4
Week-37 | 2026-08-04 | 2026-07-30 | 4 | 85% | 2026-08-03 | 4
Week-38 | 2026-08-11 | 2026-08-06 | 3 | 86% | 2026-08-10 | 4
Week-39 | 2026-08-18 | 2026-08-15 | 3 | 86% | 2026-08-17 | 2
Week-40 | 2026-08-25 | 2026-08-20 | 4 | 85% | 2026-08-24 | 4
Week-41 | 2026-09-01 | 2026-08-29 | 3 | 86% | 2026-08-31 | 3
Week-42 | 2026-09-08 | 2026-09-03 | 3 | 86% | 2026-09-07 | 3
Week-43 | 2026-09-15 | 2026-09-10 | 3 | 86% | 2026-09-14 | 3
Week-44 | 2026-09-22 | 2026-09-17 | 4 | 85% | 2026-09-21 | 4
Week-45 | 2026-09-26 | 2026-09-20 | 1 | 85.24% | 2026-09-25 | 1
Week-46 | 2026-10-06 | 2026-09-29 | 3 | 86% | 2026-10-05 | 3
Week-47 | 2026-10-13 | 2026-10-08 | 3 | 87% | 2026-10-12 | 3
Week-48 | 2026-10-20 | 2026-10-15 | 3 | 87% | 2026-10-19 | 4
Note on A38: Malik, Muhammad: This refers to quality observation sheet

## HSE
MODON HSE Site Inspection Report
Date |  |  | 2026-10-20 |  |  |  |  | Inspected By: |  |  |  | Raef M. M.
Project ID. |  |  | JDH01-02-003 |  |  |  |  | Report No. | 47.8571 |  |  |  |  | MODON PM Name |  | Engr.Abdallah Aljulayfi
Project Name: |  |  | INFRASTRUCTURE DEVELOPMENT FOR INDUSTRIAL CITY 1 IN JEDDAH |  |  |  |  | Contractor: |  | Al Enjaz Company for Trading and Contracting |  |  |  |  | Safety Performance |  | 3 |  |  | 77.17%
Inspections are a snapshot in time and refer only to the practices and documentation observed at the time of the Inspection. It remains the responsibility of the Consultant and Contractor to ensure that all aspects of Health & Safety are suitably managed.
1 |  | Good Practice |  |  | 2 | Need Improvement | [5 empty] | 3 | Fail (Life Threatening Activity) / Comliance with Plan & Procedures |  | N/A | Atcitty Not Applicable for this Site Inspection Report
No. | Topic | [5 empty] | Wt. | HSE Compliance |  |  | No. | Topic | [5 empty] | Wt. | HSE Compliance
1 | Access and Egress - (General access to site, segregated from vehicles, / Overhead protection, while entering into the building /Adequate lighting provided when dark or overnight work) | [5 empty] | 5% | 1 |  |  | 14 | Work at Height - (PPE/Fall Protection(Same level, above and blow) / Training / Fall restraint / competency /Safe access & egress to and from work at height / Ladders / Openings (floor/shafts/Provision of emergency rescue) | [5 empty] | 5% | N/A |  |  |  | 1 | 100 | 1
2 | Traffic Management - (Loading/unloading/sheeting/temp. routes/speed/parking/competence) | [5 empty] | 3% | 1 |  |  | 15 | Scaffolding - (Temp. Scaffolding Work-platform (All types) - qualified scaffolder / Inspection / Tagged / Safe Access/egress / PTW/Falsework & Formwork) | [5 empty] | 4% | N/A |  |  |  | 2 | 75 | 2
3 | Site Signage - (Project Notice Board & General Signage) | [5 empty] | 2% | 1 |  |  | 16 | Mobile Elevated Work platform (MEWP) - (PTW/competence requirements/conditions/inspections/tagged/training/Full-body harness) | [5 empty] | 4% | N/A |  |  |  | 3 | 0 | 3
4 | PPE Compliance - (Use, storage, stock, handling & checks - Head, Foot, Eye, Hearing) | [5 empty] | 5% | 2 |  |  | 17 | Excavation & Trenches - (PTW/Edge protection/buffer zone/Slope/Benching/Shoring/Geo-tech report/Atmospheric hazards/Acess&egress/Emergency management / MS&RA/H.E) | [5 empty] | 3% | 2 | [5 empty] | N/A
5 | Housekeeping - (Material correctly stored/Rubbish cleaned & removed daily/slips & trips hazards) | [5 empty] | 3% | 2 |  |  | 18 | Confined Space - (PTW/Training/competence/Emergency Management/MS & RA/Safe access/egress) | [5 empty] | 5% | 2
6 | Storage of Materials - (Transporting, storage, training and use - Combustible / Flammable / Hazardous substances (COSHH) | [6 empty] | 2 |  |  | 19 | Fire Protection - (Flammable/Oxy. LPG /Combustible separated/FE's/Flashback arrestor/Sparks & slags/Smoking area/PTW/Generators/MS & RA/Emergency Management) | [6 empty] | 2 |  | Red | Serious injury or death (immediately)
7 | Site Waste Management - (Hazardous waste /Combustible waste / Human waste / Construction waste - asphalt, cable, timber, paving roof sheeting tiles, plastic & bricks) | [6 empty] | 2 |  |  | 20 | Health & Welfare - (Adequate drinking water/shaded - eating & rest area/washing & sanitary facilities/Certified FA/FA Box & Stock/adequate toilets/Ambulance) | [6 empty] | 1 |  | Yellow | Minor or near miss (3 days to comply)
8 | Health Surveillance - (Expose to excessive noise/vibration/dust/silica/CO/cement/radiation/extreme weather condition) | [5 empty] | 3% | 1 |  |  | 21 | Environmental Incident Measures - (Spill/ Leakage / Concrete wash / vehicle & eqpts. wash / waste disposal/Sewers and drains/emissions/Emergency Management/Training/site run-off water) | [5 empty] | 5% | 2 |  | Green | No issues
9 | Electrical Safety - (Electrical qualified /RCD/GFCI/Industrial Cocket/LOTO/Cable-overhung or buried/Cords in good condition/current inspection tag) | [5 empty] | 5% | 2 |  |  | 22 | HSE Communications & Meetings - (Schedule HSE Meetings/Safety Committee meetings/Alerts / Lesson learned/Safety Bulletin contains latest HSE KPI) | [5 empty] | 5% | 3
10 | Tools & Equipment - (Includes, powered, hydraulic & pneumatic/Guards in place/Properly stored/RCD Protection/Earthed/Good condition & tagged) | [5 empty] | 3% | 2 |  |  | 23 | HSE Plan & Associated Procedures - (Approved updated HSE Plan/ CEMP/HAZComm/Procedures/Standards/Project Safety Risk Register) | [5 empty] | 3% | 1 |  | 26 points > 4 minors then is it’s a serious issue
11 | Manual Handling - (Lifting/loading/pulling/pushing/twisting/awkward posture/repetitive task/frequent and prolong physical effort/Reasonable practicable use of mechanical aid) | [5 empty] | 3% | 2 |  |  | 24 | Health, Safety & Environment Incident reporting - (Review of HSE Statistics, Reporting of Unsafe Act & Conditions/ Reporting of Near Miss incident/Reporting of FA cases/Record MT cases) | [5 empty] | 3% | 1
12 | Vehicle and mobile equipment / Plant - (dumpers; excavators, cranes, piling rigs, grader, roller, loaders/condition/KSA License/certification) | [5 empty] | 5% | 2 |  |  | 25 | HSE Awareness, Training & Competence - (Policy /Objective & targets/Information, training/Climatic condition awareness/Reponses in emergency situation/ Safety Behavior Observation) | [5 empty] | 4% | 1
13 | Lifting Operations & Rigging - (Lifting Plan/Lifting devices & gears/PTW/Condition/3rd party certification/bank-man/rigger/slingers/man-basket/inspection record/tagged) | [6 empty] | 2 |  |  | 26 | Project Leadership Site Tours - (Provide evidence of proactive safety performance/Deficient discovered discussed/Positive feedback/Workers resolving safety issues) | [6 empty] | 3
Prepared by: |  |  |  | Raef M. M. | [6 empty] | Sent to MODON PM: |  |  |  | Engr.Abdallah Aljulayfi
Safety Results
1 |  | 8 |  |  |  | 2 |  | 13 |  |  |  |  | 3 | 2
Note on C13: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Safe access / egress for people to their work area 2 - Safe access / egress for construction vehicles 3 - Access properly restricted-site fencing provided and maintained 4 - Access proper and not blocked 5 - Safe access is available for rescue operation 6 - Storage access / exit are clearly marked and unobstructed 8 - Access and egress is in good condition, hand holds, ladder etc. are sound and in place 9 - Ensure unauthorized public access is prevented 11 - Site assembled ladders or make-shift tables for access are forbidden on site. 13 - Use proper bridges, walkways or gangways to access or cross trenches or an excavation area 14 - Surrounding areas are cleared and barricaded and access restricted to all unauthorized trades while crane in operation 15 - To ensure early access to accredited medical / rehabilitation services 16 - Parking vehicles on site access roads causing obstruction 17 - All personnel will be instructed that access to firefighting equipment must remain clear at all times 18 - Access control gates to be locked out of hours 19 - Site access gates to be designed and located to, where possible, avoid clashes with external hazards / activities
Note on T13: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Personal Fall Arrest System; 1 - Is the suitable harness harnesses is provided 2 - Are shock absorbing lanyard with 2 locking snap hooks. 3 - Is anchorage point strong enough and can support 5,000 Ibs. 4 - Do inspection checklist is being implemented before use. 5 - Is the emergency plan for rescue in place Personal Fall Restraint System; 1 - The fall restraint equipment should be set and adjusted so there is no free fall over the edge. 2 - A harness or body belt may be used 3 - The anchorage point must support 4 times the intended load. Positioning System; 1 - Is a suitable harness or body belt provided 2 - Is there a not more than 2' free fall maintained 3 - Is the anchorage point capable of supporting 2 times the intended load or 3.000 Ibs, whichever is greater 4 - Is 100% tie-off (protection from falls at all times, even when moving from point to point) provided while using personal fall protection with two lanyards Fall Protection System; 1 - Suitable edge protection and work platforms are to be provided to prevent a fall occurring 2 - Where the provision of edge protection or adequate platforms cannot be provided safety nets or other soft-landing systems such as inflatable bags are to be used to minimize the consequences of a fall. 3 - If nets are used, they must be installed by a competent rigger and fitted as close under the work surface as possible. 4 - Areas below roof works are to be cordoned off and properly signed to prevent personnel being injured from falling materials 5 - If access onto the roof cannot be avoided, edge protection is to be installed 6 - Floor and wall openings are to be protected using covers of adequate strength to withstand the expected load that will be imposed and securely fixed. 7 - Penetrations in walls such as those provided for lift shafts, door openings, etc. are to be closed with suitable strength material or have fixed protective barriers around the penetration with a sign warning personnel of the danger of falling.
Note on C14: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are arrival and departure of vehicles and delivery accompany by security department? 2 - Are proper loading, unloading and securing loads, being properly controlled? 3 - Is the proper sheeting & coupling in place when transporting and disposing material to and from site? 4 - Is the parking to the designated parking lot and in reverse order? 5 - Is the designated speed limit adhered on workplace? 6 - Provision of ramps, traffic signs, cones, barriers, demarcation posts and tape, flashing lights and any other traffic control devices. 7 - Do visiting drivers are being inducted at the workplace, prior to enter on the workplace? 8 - Are visiting drivers restricted to dangerous areas, e.g. moving to and from they vehicles to washrooms, lavatory & offices etc.? 9 - Do drivers observe site rules and procedures, for delivery, loading and unloading? 10 - Are the areas wide enough for the safe movement of large vehicles (including visiting vehicles)? 11 - Does drivers are competent, hold valid local driving license and competent training? 12 - Ensure the vehicle and trailers have their brakes applied and all stabilizers properly positioned before beginning loading or unloading?
Note on T14: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Base soundness, load adequately spread (base plate jacks, base plate on firm ground). 2 - Line of standard (vertical) and ledger (horizontal) secure and plumb. 3 - Spacing of transoms on platforms, support for Scaff boards, boards are not over protruded and boards are secured. 4 - Staggering of joints vertical and horizontal. 5 - Guardrail / fall protection. (Top rail – Min.1mtr, Mid rail – 470mm from floor and Toe boards – Minimum150mm) 6 - Longitude and bracing on standards and ledgers. 7 - If close to structure, ties must be on lift below to top working platform and every 3m, load bearing couplers used or tie with certified anchor bolts (eye bolts). 8 - Clamps and tubes used are of correct fittings, size and free from defects. 9 - Tubes & fittings free from defects / deformation. 10 - Safe and proper access available to the working platform. 11 - Scaff tags signed, displayed and up to date. 12 - If close to slab edge/opening scaffold tied and secured to structure correctly.
Note on C15: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a Project Notice Board - (showing HSE Statistics / Safety alerts / lesson learned)? 2 - Is there prominent safety boards that are depicting the mandatory PPE on the workplace? 3 - Are other safety required signs are prominently installed on the workplace in relevant to their work-task, as following: > Hazardous Substances - e.g. respiratory protection Sign > Working at Height - e.g. Full body Harness Sign > Working UG - e.g. Full body Harness, SCBA, Ventilation, PTW Signage etc. > Working with Electrical - e.g. Leather Gloves, Goggles, Face shield, Electric shock proof helmet & shoes > Working with Chemicals - Signage = e.g. Impermeable gloves/clothing's, long sleeves, Goggles 4 - General Site Safety Signs: > Prohibition Sign = (e.g., ‘no access for unauthorized persons’). > Warning Signs = (e.g., ‘danger: electricity’) > Mandatory Signs = e.g., ‘eye protection must be worn’) > Emergency Escape or First Aid Sign = e.g., ‘emergency exit/escape route’) > Safety Color Signs = (e.g., yellow means ‘be careful’ or ‘take precautions’) > Illuminated Signs = (e.g., many emergency exit signs) > Acoustic Signals =( e.g., fire alarm) > Fire safety sign > Supplementary Signs = "This way"
Note on T15: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Man-Lift operators are to be competent and trained to operate the specific Man-Lift by examination and hold a current approved certificate / license from an approved and internationally recognized source (TUV, SGS etc. 1 - All Man-Lifts shall be inspected by a 3rd party on an annual basis. 2 - All Man-Lifts shall display a sticker corresponding to the 3rd party inspection certificate. 3 - The manufacturer's instruction manual must be on site for each and every type of Man-Lift in use. 4- A pre-start daily operator inspection of the equipment will be performed and documented on a daily basis as per the manufacturer's instructions. The user is responsible for ensuring this has occurred. 5 - The use of a Man-Lift as, or in lieu of, a Crane is strictly prohibited. Man-Lifts are to be used only for lifting personnel and small tools within the designed Safe Working Load. 6 - The platform is not to be loaded in excess of the designed working load; the safe working load of the platform is to be clearly displayed on both the platform, and body of the equipment. 7 - All persons inside work platforms shall wear a full-body harness attached to the designated anchor point. Personnel must stand on the floor of the working platform; standing on the handrails is strictly prohibited. Harnesses must not be attached to other structures outside of the working platform. 8 - Personnel must stay inside the working platform at all times; the platform must not be used as an access to structures. The use of staging or ladders to extend height is strictly forbidden. 9 - Securing the boom or work platform to any structure is strictly prohibited. The boom or working platform must not be rested upon on any structure, nor is the Man-Lift to be used as a jack/ prop or tie to support other structures. 10 - All Man-Lifts must be equipped with a 5kg (10lb) fire extinguisher. 11 - No man-lifts are to be operated that have had safety devices removed or disabled. Daily operator inspections are to include the testing of these devices (limit switches, alarms and hazard flashing beacons). 12 - Specific Man-Lifts are fitted with outriggers and/or stabilizers which must be used as per manufacturer's instructions. 13 - The work area surrounding the man-lift is to be cordoned off using barricades and signage if the area is used by other workers or vehicles. A full traffic management plan is required for all works involving man-lifts when working on highways. Under no circumstances is any part of a man-lift to extend or swing into a line of traffic.
Note on C16: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Does required mandatory PPE (refer specification BS, EN & ANSI) is provided, as following? > Safety helmet (see below for color scheme) > Safety glasses (shaded for outdoor work and clear inside structures and during non-daylight hours) > Safety boots (safety shoes are prohibited) > Orange hi-visibility vest 2 - Additional PPE shall be provided to a specific task 3 - Do specific PPE is provided according to their job requirement? > To work at height - Full Body harness / Fall arrest Devices / Fall Restraint Devices / V & H Lifeline etc. > To work in the confined space - Full Bodyarness, Tripod with retractable lifeline, SCBA, Masks etc. > 4 - Are the PPE stored appropriately to prevent deformation or distortion? 5 - Has self assessment being carried out for in according to the work requirements? 6 - EYEWEAR (Glasses/Goggles/Face Shields) > Eyewear cleaning supplies available. > Safety glasses in good condition and lenses free of scratches. > Goggles adjustment strap not cracked or frayed, not deformed, or lenses not > Face shields in good condition, including adjustment band, and free of scratches or 7 - HEAD PROTECTION > Hard hat bill and suspension attached as allowed by manufacturer. > is pliable, free of dents, cracks, nicks, or any damage due to impact. > Suspension maintained at 1.25 inches from inside of shell. > Suspension free of cuts or fraying, torn headband, adjustment strap workable. > Electrical hard hat matched to hazard classification. > Dated to determine whether within manufacturer’s allowable 5-year use time period. 8 - HAND PROTECTION > Available in sizes matched to employee. > Gloves free of rips tears, abrasions, or holes. > Matched to manufacturer’s specification for chemicals used onsite. > Electrical gloves matched to hazard and periodically inspected for insulating rating. > Maintained in a clean and sanitary condition, decontaminated or disposed properly. 9 - BODY PROTECTION > Available in sizes matched to employee. > Maintained in a clean and sanitary condition, decontaminated or disposed properly. > Vapor-tight fully encapsulated suits tested at required periodic intervals. > Flame-resistant clothing matched to electrical hazard and arc flash rating. > Welding gear matched to degree of hazard and free of cuts, tears or burn holes. > Flotation gear available for work near or on water and in good condition. 10 - HOT AND COLD BODY PROTECTION > Cooling gear available based on degree of heat stress hazard. > Cooling gear in operable, clean, and sanitary condition. > Cold-weather gear provided based on needs assessment. > Cold-weather gear available in sizes to match employees. > Cold-weather gear is in free of tears, rips, or holes and in maintained in a clean condition. 11 - TRAINING > Initial PPE training completed by employees. > Training conducted when new types or styles of PPE are issued. > PPE selection, use, and maintenance reviewed at daily safety briefings. 12 - Provision of impermeable clothing appropriate for the work being performed? 13 - Wearing of shorts, sleeveless shirts, loose clothing are prohibited across the MODON Projects. 14 - Clothing contaminated with grease, oils, fuels and other hazardous substances is not to be worn.
Note on T16: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a valid Excavation PTW in place? 2 - Are spoils, materials, and equipment set back at least 1.5 meters from the edge of the excavation? 3 - Are walkways and bridges over excavations structurally sound, minimum 0.5 meter in width and equipped with standard guard rails and toe boards? 4 - Are warning systems established and used when mobile equipment is operating near the edge of an excavation? 5 - Are employees prohibited from working on the faces of sloped or benched excavations above other employees? 6 - Are the exact locations of Utilities (piping, electrical, etc.) clearly marked? 7 - Are underground installations protected, supported, or removed when an excavation is open? 8 - Are ladders or other means of access and egress in place as per the PTW requirements? 9 - Are all workers within 7.6 meters of a means of access and egress to a trench? 10 - Are ALL ramps constructed of materials of uniform thickness, cleated together, equipped with no-slip surfaces? 11 - Are employees protected from cave-ins when entering or exiting excavation? 12 - Are precautions taken to protect employees from water accumulation and dewatering is being carried out? 13 - Is surface water or runoff diverted after every rainstorm or other hazard-increasing occurrence? 14 - Is the excavation classified as a confined space? If so, is their a valid confined space PTW and is the atmosphere being tested when there is a reasonable possibility of an oxygen-deficient, oxygen-enriched, combustible, toxic, or other harmful contaminant? 15 - Have materials and/or equipment chosen for shoring been based upon soils analysis, trench depth and expected loads (as per Excavation PTW)? 16 - Are shoring materials and equipment that are used for protective systems inspected and in good condition? 17 - Are damaged shoring materials and equipment immediately removed from service? 18 - Are damaged shoring materials and equipment inspected by a Registered Professional Engineer after repairs are made and before being placed back in service? 19 - Are protective systems installed without exposing employees to hazards of cave-ins, collapses, or threat of being struck by materials or equipment? 20 - Are ALL members of support systems securely fastened together to prevent failure? 21 - Are support systems provided to insure stability of adjacent structures, buildings, roadways, sidewalks, etc.? 22 - Are excavations below the level of the base or footing supported, and approved by a Registered Professional Engineer? 23 - Does back-filling progress with the removal of the support system? 24 - Is a shield system installed to prevent lateral movement? 25 - Are employees prohibited from remaining in a shield system during vertical movement?
Note on C17: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Sites are to be kept clean and tidy and free from slip, trip and fall hazards. 2 - Do all personnel trained in the importance of good housekeeping, managers, supervisors undertake regular monitoring and inspection of the workplace? 3 - Workplace are to be left clean and tidy at the end of each shift and where there is an accumulation of materials throughout the shift, at regular intervals as required to maintain a clean and safe site. 4 - Buildings under construction and nearing completion must ensure that all combustible and flammable materials are removed at the end of each shift. 5 - Nails are to be removed from timber as soon as possible, where this is not practical they are to be flattened and placed in a safe area (barrier and signs) until nails can be removed at a later time. 6 - Materials are to be stored so as they do not pose a risk to personnel stacking, removing or walking by (further guidance is given in the materials storage and handling section). 7 - All spills are to be cleaned up immediately using absorbent material. 8 - Cables/hoses/other trailing leads are to be protected, buried or secured above head height to avoid a slip trip, fall hazard. 9 - Waste is to be placed in designated containers and covered to protect against high winds, pests or risk of fire. Waste containers are to be emptied on a regular basis to prevent a build-up of material. 10 - Loose or light materials that are stored on roofs or open spaces are to be secured to prevent them from inclement weather. Location: 1 - Receptacles located inside buildings shall be kept at least 18 inches away from combustible walls and partitions. 2 - Receptacles for combustible trash that are located outside of buildings shall be placed at least 15 feet from the building or combustible material. Use: 1 - Cigarettes, cigar butts, matches, and similar potential ignition sources should never be placed in a trash receptacle. Proper receptacles for such items should be provided in areas designated for smoking. 2 - Broken glass, empty jars, scrap metal, and similar construction material should never be placed in office trash containers. A roll-off bin or other appropriate container should be used to hold construction debris. Environmental: 1 - Container storage areas shall be kept clean and free of trash. Improper disposal of food waste can attract pests and vermin. Prevention methods that do not involve the use of toxic chemicals is the preferred method of pest control. 2 - Outdoor containers should be kept covered when not in use so as to avoid attracting pests and to prevent the entry of water. Dripping or leaking trash containers may violate local storm water quality discharge regulations. 3 - Promote recycling by contracting with a waste removal company that provides reuse as part of the waste processing or by providing segregated bins for the collection of office paper, aluminum cans, plastic bottles, and toner cartridges. Rinse empty cans and bottles of sugar-based soda so as not to attract ants and other pests. 4 - Proper lighting (indoor) or during Night Shift are provided. Accurately installed. No impairement or poor visibilty is generated. No shadow due to installation of lights are presents.
Note on T17: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Permit is taken for confined space entry and all recommended precautions are in place. 2 - Operatives are trained and fit for the specified job. 3 - Confined space is well ventilated by means of mechanical ventilation. (Exhaust fan, blowers, low velocity air hose etc.). 4 - Rescue system (Tripod with hoisting device, Rescue Harness etc.) in place and sufficient trained persons are available for the rescue operation. 5 - Safe access is available for rescue operation. (Manhole size - Min. 450 mm X 407 mm or 457 mm Dia.) 6 - Atmospheric monitoring conducted and confined space is safe to enter. Percentage of gas concentration will be monitored and recorded every 4 hrs. A. Oxygen percentage. (Permissible limit – 19.5% to 23.5%) B. Flammable gas or vapors.(Permissible limit - <10% of LFL) C. Carbon Monoxide. (Permissible limit - <50ppm) D. Hydrogen sulfide.(Permissible limit - <10ppm) E. Any other toxic gas or vapors. _______________________________ 7 - Minimum two persons shall be assigned to work in the confined space. One person will remain in the entrance at all times to monitor the work 8 - All persons shall wear safety harness, which should be connected to safety line from outside at all times. 9 - All electrical equipment & leads are free from damage and guards in place. 10 - All electrical tools & equipment are connected through ELCB. 11 - Compressed gas cylinders are kept outside the confined space. 12 - supervisor / Foreman will be available at all time to monitor the work and for the rescue operation. 13 - Tool box talk conducted for the entire team and they are well aware of the risks. 14 - Proper communication system is available in between persons inside and standby person. 15 - Trained First aider with first aid kit will be available when working in the confined space. 16 - Confined space entry register is available and shift records will be maintained. -
Note on C18: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Combustible: 1 - Ensure oily rags, combustible material and other flammable substances which may ignite are not accumulated and that they are removed without delay to the designated disposal / storage area. 2 - Combustible materials shall not be stored within 20 feet (6.1 meters) of compressed gas cylinders. 3 - Safety cans used for dispensing combustible liquids shall be kept at a point of use 4 - Storage rooms for combustible liquids must have explosion-proof light fixtures 5 - No flames - hot work or smoking is be permitted in combustible liquid storage areas. Flammable: 1 - Adequate training in the use and storage of flammable liquids is in place. 2 - Storage of Flammable liquids in accordance with NFPA approved flammable storage lockers or in low value structures at least 50 feet from any other structure. 3 - Do not store other combustible materials near flammable storage areas 4 - Bulk drums of flammable liquids must be grounded and bonded to containers during dispensing 5 - Portable containers of gasoline or diesel are not to exceed 5 gallons 6 - Safety cans used for dispensing flammable liquids shall be kept at a point of use 7 - Appropriate fire extinguishers are to be mounted within 75 feet of outside areas containing flammable liquids, and within 10 feet of any inside storage area for such materials. 8 - Storage rooms for flammable liquids must have explosion-proof light fixtures 9 - No flames - hot work or smoking is be permitted in flammable or combustible liquid storage areas. 10 - Flammable liquid transfer areas are to be separated from other operations by distance or by construction having proper fire resistance. 11 - When not in use flammable liquids shall be kept in covered containers. 12 - Flammable materials are considered hazardous and as such, material safety data sheets and appropriate hazard communication training for affected employees is required 13 - Maintain high levels of housekeeping, particularly with relations to flammable materials. 14 - Where flammable materials are handled in the course of work, safe work procedures must be prepared and documented with reference made to the Material Safety Data Sheets (MSDS‘s) for the materials concerned. 15 - All people handling, working with or in control of flammable substances must be properly trained and supervised (documentation to be maintained). 16 - Lead, dust, fumes and vapor constitute a major health hazard to workers. Hazardous Substances COSHH 1 - Under COSHH the risk presented by any hazardous substance assessed using hierarchy of control, stored, transported, created or disposed and usage at the workplace; > Very toxic or toxic: Substances that, in low quantities, cause death or acute or chronic damage to health when inhaled, swallowed or absorbed via the skin > Harmful: Substances that may cause death or acute or chronic damage to health when inhaled, swallowed or absorbed via the skin > Corrosive: Substances that may, on contact with living tissues, destroy them > inhalation into the lungs, when the substance is in the form of a gas, vapor, fume, mist, aerosol or dust > absorption through the skin or eyes by contact with a substance that can penetrate unbroken skin, or is absorbed through unprotected cuts or grazes > injection by contact with contaminated sharp objects or high-pressure equipment, e.g. water jetting > ingestion by swallowing particles of a hazardous substance resulting from hand-to- mouth transfer
Note on T18: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are regular and frequent fire safety inspections carried out? 2 - Have a sufficient number of fire marshals/evacuation officers been appointed? 3 - Are water supplies adequate? 4 - Does the building or site have a written fire procedure? 5 - Is there an effective permit to work system in operation for all hot work and other fire related work? 6 - Do all doors from areas from which a large number of people may have to escape open in the direction of travel? 7 - Do all emergency exit doors (i.e. doors not in normal use) have clear instructions displayed on how to open? 8 - Are all escape routes clear and unobstructed? 9 - Are all fire exit doors correctly signed? 10 - Is all fire fighting equipment immediately visible or correctly signed? 11 - Are all flammable and explosive substances adequately signed to indicate their presence and danger? 12 - Where necessary, is there a sufficient number of emergency lights to adequately illuminate all internal escape routes, exit doors and signs? 13 - Where automatic fire detection is deemed to be necessary is there an adequate number of detectors in the critical areas? 14 - Where the means of raising the alarm is by hand-operated devices, can the operation of one device be heard throughout the entire building or site? 15 - Is there an adequate number of fire extinguishers in the building? 16 - Is there firefighting equipment other than extinguishers in the building? 17 - Are all electrical circuits and fixed electrical installations examined and tested at an acceptable frequency? 18 - Is housekeeping to an acceptable standard? 19 - Have all staff been trained in fire procedures in the last twelve months? 20 - Are all fire drills adequately recorded?
Note on C19: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - General construction waste streams generated including; > Asphalt, cable, timber, paving, roof sheeting, tiles, plastic sheeting and brickwork. > Excess concrete, spoil material from excavations. > General waste, such as putrescible food scraps and packaging from workers. > General (food) waste, construction/concrete waste, hazardous waste, paper/cardboard and waste water/sewage. 2 - Are hazardous waste identified with hazardous Waste label. 3 - Containers are properly labeled in according to their contents. 4 - Container inspections are documented in writing using the Container Inspection Checklist. 5 - Weekly inspections logged into book using the Accumulation Area Inspection Log Sheet. “NO SMOKING OR OPEN FLAME” sign posted. 6 Disposal facilities identified, evaluated using the procedures. 7 - Disposal facility accepted waste and issue approval letter. 8 - Waste transfer/dispose tracked using Waste Tracking Form. 9 - Waste streams, such as asphalt and concrete, to be recycled should be segregated and separately stored. 10 - Spill Release Contingency: 1 - Prior to beginning operations, ensure that on-site spill response capabilities (containment and personal protective equipment) are consistent with task requirements described in job hazard analysis.
Note on T19: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: HHE is required at all locations where chemical hazards exist, such as; storing, transferring and handling facilities, under routine conditions. The HHE scope shall include the physical, chemical, radiological, and biological health hazards. Physical health hazards include elevated noise and vibration exposures, repetitive motion work operations, ionizing and non-ionizing radiation exposures heat and cold stress and biological hazards include infectious disease agents. HHE shall be performed before the site mobilization; 1 - Is the adequate eating or mess area is provided and sufficient for number of workers? 2 - Are sufficient tables and Chair are provide and Kept Clean? 3 - Are FEs, signs, pest control being implemented? 4 - Is washing Area sufficient and Kept Clean? 5- Cooking Area Kept Clean? 6 - L.P.G. Cylinder stored outside, secured & upright 7 - Sufficient drinking water provided. Filters changed (as per manufacturer recommendation)? 8 - Sufficient toilets, washbasins, cleaned/disinfectant provided? 9 - Provision of First Aider 10 - Provision of Nurse 11 - Provision of First Aid Kit 12 - Provision of site clinic with required first aid equipment and items. 13 - Provision of shaded area on the workplace 14 - Provision of Ambulance or an equal arrangement in place" 15 - Smoking area is Prohibited other than designated smoking areas, clear of flammable and combustible materials? 16 - All toilets, washing, rest and eating facilities to be kept clean, hygienic and be well maintained at all times? 17 - Waste Management - Covered bins, emptied daily, close proximity, color coded etc.? 18 - Are the monitoring, including integrated air sampling, noise dosimetry and other exposure assessments, being carried out? 19 - Are the Physical, chemical, and biological stresses, being identified, results are taken with action level to prevent sickness, impaired health, significant discomfort, or inefficiency in workers? 20 - Are WEL, LEL, OEL PEL & TLV linked to control workers airborne exposure to a chemical in a concentration above which is likely to cause death or immediate or delayed permanent adverse health effects or prevent escape from such an environment, if bening implemented?
Note on C20: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Is the hierarchy of Control is beng carried out on the following and recorded; 1 - Exposure to Chemical; e.g. - Dust, Gas, Mist, Vapor 2 - Exposure to Radiation; e.g. - Pipe radiography etc. 3 - Exposure to Biological Hazard; e.g. - Bloodborne pathogens / Legionella / Leptospirosis 4 - Exposure to noise; e.g. Loss of hearing / Physical damage to hearing mechanism 5 - Heat and cold stress work; e.g. - Heat-stroke, Heat stress / Frostbite / 6 - Repetitive Motion Work; e.g. - Musculoskeletal disorder, awkward position etc. 7 - Is the risk assessment carried out on the hazardous material and covering the following; > Allowable exposure limits, > Exposure monitoring requirements, > Methods of compliance for potential over exposure conditions, > Medical surveillance program, > Hazard communication, employee training requirements, 8- Is the IH Surveillance Plan should being implemented and have rocored on the following; > Which exposure groups require IH monitoring and medical surveillance > Specific substances or agents to be monitored, > The OELs to be used to evaluate results > The statistical basis to continue or cease monitoring > Specific medical testing/protocol to be implemented 9 - Do we've program on identifies work conditions such as the following, the exposure must first be mitigated or work shall not be performed. > Oxygen concentrations less than 19.5% or greater than 23.5%, or > Atmospheres greater than 1% of the Lower Explosive Limit, or > Atmospheres that are >50% of Immediately Dangerous to Life or Health (IDLH) concentrations, or > Work with sensitizers or known human carcinogens, mutagens, or teratogens without process isolation or fully encapsulating personal protection, or > Work with highly infectious biological agents without process isolation
Note on T20: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are all dispensing areas diked or properly graded to control drainage of spilled fuel? 2 - are all workers and operatives are trained to use spill response kit? 3 - Is the procedure in place for collecting and/or containing, and disposing of spilled materials? 4 - All tanks & vessels areas are diked to contain accidental spills?. 5 - Do measures taken to prevent an accidental contaminated runoff from construction , operation, maintenance, plant and storage areas? 6 - Do measures taken to control on deposits of oils, greases and fuels, from site plant and vehicle operations, mechanical failures, spillages and discharges to ground or drains and the dispersion of unattended spills by plant / vehicle movements?. 7 - Do measures taken to control on fuels, oils and other hazardous chemicals spilled on site during re-fueling, storage or transport operations?. 8 - Do we have an Emergency Response Procedure will be followed in the event of environmental emergency such as an oil or chemical spill? 9 - Is there a procedure for concrete wash, clean and dispose to prevent ground contamination, such as; Concrete wash pits with leak proof sedimentation tanks will be provided for washing concrete mixer trucks. The design and location of such wash pits shall be agreed with the Project Manager prior to its construction on site. Concrete dumping or spillages of any kind shall not be allowed in any other location on site? 10 - Is there a procedure to used in the situation of a major spills that will have an impact on the surrounding environment will be promptly reported to the Fire Brigade? 11 - Are there a procedure of disposing off any damage/leakage drums or containers shall be removed in accordance with the local requirements? 12 - Are there a procedure of dealing with spilled contaminated soils, resulted and remediated, accordingly? 13 - Are all personnel trained in the use of spill procedure and response and the adequate spill kits are available on site?
Note on C21: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - All electrical extension cords are equipped with nonconductive plugs 2 - Cords must not be spliced or draped over nails, metal objects 3 - The use of extension cords by means of multiple outlet plugs from single outlets is prohibited 4 - All electrical service removals, alterations and equipment installations are performed by an authorized electrician 5 - Faulty electrical installation 6 - Electrical supply disruption 7 - Exposed cables 8 - Trip / fall hazards from installed cables 9 - Fire hazard Electrical overload 10 - electrocution 11 - Electrical (short circuit) - Contact with exposed conductors or a device that is incorrectly or inadvertently grounded, such as when a metal ladder comes into contact with power lines 12 - Electrical - (static discharge) 13 - Electrical Fire - Use of electrical power that results in electrical overheating or arcing to the point of combustion or ignition of flammables, or electrical component damage 14 - Improper grounding 15 - Damaged insulation 16 - Exposed electrical parts 17 - Overloaded circuits 18 - Inadequate wiring 19 - Wet conditions 20 - Overhead power lines 21 - Damaged tools and equipment
Note on T21: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a meaningful and an effective consultation and communication on health and safety matters being implemented through out the project? 2 - Is the Consultation and communication on health and safety matters in place through the following mechanisms: > Project specific induction - (prior to commencement of contracted work) > Work activity Induction (in SWMS or equivalent) - (prior to commencement any construction work) > Toolbox Meetings - (Monthly intervals or generally when there is the introduction of a new process (SWMS) or when discussing OHS issues/topics). > Subcontractor Meetings - (weekly) > Project team meetings - (weekly) > HSE Committee Meeting - (as agreed with the HSE Committee) > OHS Report - (monthly) > Project Notice Board and general signage - (as required) 3 - Is there a method of communication is to be established in the work procedures to allow constant monitoring of those persons working in the confined space? 4 - Is there a material safety data sheets and appropriate hazard communication training for affected employees is in place? 5 - Are all environmental aspects and impacts been communicated to employees? 6 - Dose the notice
Note on C22: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1- Check that all the workers are using safe hand tools/power tools and instruct them to operate and maintain the same in safe manner 2 - Ensure power tools and hand tools are checked prior to issue 3 - Damaged tools and equipment 4 - Electrical tools or electrical equipment are not to be issued for use until inspected. 5 - Electrical tools or electrical equipment are not to be issued for use until inspected. 6 - "Defective" electrical tools and equipment are to be tagged and removed from service until repaired and inspected 7 - The frequency for inspection of construction electrical tools and electrical equipment shall be monthly and inspection indicated by attached color-coded tape or color- coded tie wraps and a color coded inspection tag with Contractor‘s name, the supervisor, the inspection date, equipment number and signature of competent inspector displayed on the tag. 8 - Checking the cords for worn or cracked insulation. 9 - Checking the cords entry to plug and tool housing for frayed or worn insulation and strain relief. 10 - Checking the plug prongs for damage. 11 - Checking the plug for exposed connectors 12 - Checking the equipment housing for damage. 13 - Checking trigger locks to ensure they have been removed 14 - Checking the leads for signs of wear, poor connections at probes, etc. 15 - Checking the housing and the readout window for cracks, loose screws, etc. 16 - Check all Ground Fault Circuit Interrupters (GFCI) during the monthly inspections. 17 - Machines are free from any defects / damage. 18 - Pressure switch and safety guards in place where applicable. 19 - Leads are fitted with correct plugs & sockets and free from damages. 20 - Leads wires are free from joints, cuts and other defects. 21 - Leads are suitably rated for the electric current. 22 - Machines / Tools are equipped with properly functioning dead man switch. 23 - Tools issue and maintenance record is properly maintained. 24 - Tools are correctly stored. 25 - Discarded Tools / cords are marked and stored separately.
Note on T22: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is the Project HSE Plan presents actions, responsibilities, protocol, conformance, verification and containment activities to be undertaken by project staff and sub-contractors at all times during the construction phase of the project. 2 - Is the implementation of the HSE plan is being monitored, evaluated for accuracy and any changes made communicated to all relevant personnel. 3 - Is the HSE Plan, CEMP, Security Plan, HAZcomm., standards & procedures are updated, signed, approved and distributed, acknowledged to the construction team's responsible individuals? 4 -Is the project overall safety risk register developed, approved and being implemented?
Note on C23: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Immediate Postural and Load Factor; 1- Is the body position stable? 2 - Is the trunk of the body straight (not twisted)? 3 - Is the operation carried out by one person? 4 - Is the load kept close to the body? 5 - Can the handler avoid stretching upwards? 6 - Can the handler avoid a prolonged period in one posture? 7 - Can the handler perform the task without overreaching? 8 - Are both hands used for grasping? 9 - Are the hands less than a shoulder width apart? 10 - Is the load positioned centrally in front of the body? 11 - Is the load reasonably symmetrical? 12 - Is the load stable and easy to grasp? 13 - Can handlers move and position themselves freely? Environmental Risk Factor; 1 - Too hot? 2 - Too cold? 3 - Too bright? 4 - Too dark? 5 - Too noisy to allow effective communication? 6 - Too wet? 7 - Slippery underfoot? 8 - Does any personal protective equipment interfere with the task? Carrying; 1 - Is the load carried at knuckle height? 2 - Is the load carried at arm's length from the body? 3 - Is the load carried for more than 10 meters? Seated Work; 1 - Is the load lifted from below thigh height? 2 - Is the load lifted to above shoulder height? 3 - Is the load lifted at arm's length from the body? 4 - Does the handler have to twist significantly to the side? 5 - Is the load heavier than 5kg? Pushing and Pulling; 1 - Does the pushing and pulling take place below knuckle height? 2 - Does the pushing and pulling take place above shoulder height? 3 - Is the initial or maximum force required to push or pull the load more than 25kg? 4 - Is the continuous force required to keep the load in motion more than 10kg?
Note on T23: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a system of proper HSE reporting in place, such as; all work-related incidents including near misses, injuries, illnesses, property damage, environmental incidents, security events and motor vehicle incidents, using proper protocol followed? 2 - Is the HSE incidents, accident, near misses, unsafe acts/conditions and dangerous occurrences are being reporting in timely manner and in the approved company format? 3 - Are the workers informed, trained in reporting all near misses, unsafe acts/conditions to the appropriate authority or line of manager? 4 - Is the Weekly / Monthly HSE Statistics data, including (leading & lagging) indicators, reviewed by the senior management?
Note on C24: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: CHECKS; 1 - Plant guarding is in place and in good condition to prevent injury from parts disintegrating or failing 2 - Access and egress is in good condition, hand holds, ladder etc. are sound and in place 3 - Operator's seat and controls are in good condition and all safety devices (limiters and indicators) are labelled and fully operational. 4 - Operator's manual / instructions supplied by the manufacturer of the plant are available in the plant. 5 - Hazards with the use of the plant are identified, i.e. Safe working limits on batters, operator safety instructions etc., are displayed clearly in the cabin of the plant for operator reference. I.E. PLANT SPECIFIC RISK ASSESSMENT. 6 - Hazard controls, i.e. seat belts must be worn and hearing protection must be worn, caution/danger signs (counter weight slewing area, excavators and cranes) etc. are displayed in the cabin or on the plant in a position relevant to the hazard. 7 - Operator cabin/work platform access is clean and free of debris, loose tools, equipment, grease oil and is in an orderly condition. 8 - Plant is clean and free from oil leaks and oil build up. 9 - Plant Pre Start inspection is complete and a record of the inspection will be provided at commencement on the site. 10 - Certification of operator / proof of competency. 11 - Operational Noise Level - Statement of conforming emission level. 12 - Plant has no areas of excessive wear or damage. Mobile plant required to have; 1 - Plant is fitted with a Roll Over Protection Structure (R.O.P.S.) and operator restraint. 2 - Plant is fitted with a front horn and reversing beeper. 3 - Plant is fitted with a rotating or flashing amber beacon. Plant used to lift Material and equipment; Backhoes, excavators, cranes and loaders used as crane from designed lifting points. The Safe Working Load of the plant item is displayed on the plant as: EITHER; A Crane Chart supplied by the manufacturer specific to the plant item in the cabin of the plant for operator reference OR; The Safe Working Load of the equipment on the boom of the loader bucket and of the dipper arm of excavators - a combination of both is required for backhoes e.g. SWL 1.2ton. Personal Lifting Equipment - (Cherry Pickers, boom lift and elevated platform) 1 - Safety Working Load is displayed on work bucket / platform. 2 - Fully body harnesses and lanyards are to be provided for personnel using the equipment. 3 - Safety Instruction for the operation of the equipment is clearly displayed in the work bucket / platform. 4 - The supplier have provided training for personnel using the platform in the safe use of the equipment
Note on T24: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Do all personnel have the correct information, instruction and training according to their role and responsibilities? 2 - Is the contractor promoting awareness of company standards and regulations among their employees on a regular basis, or when it is necessary? 3 - Do all personnel have completed basic relevant awareness training, such as; Fire Awareness Training, Heat Stress awareness Training, Safety Signs and Color Code awareness Training, Environmental Awareness Training, Using Fire Extinguisher Awareness Training, Emergency reporting Awareness Training, Unsafe Act/Conditions reporting awareness training, Evacuation Procedure Awareness Training?
Note on C25: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Crane Inspected 2 - Operator certified 3 - Lift Plan approved 4 - PTW obtained 5 - lifting equipment is suitable for the use it is being put to, marked with safe working load, properly maintained and inspected, and receives a periodic thorough examination. 6 - Are all members of the lifting operations team including the Appointed Person, Crane Drivers and Slingers / Signalers / Banksmen will be competent and have such practical and theoretical knowledge and experience as is necessary to carry out their duties. 7 - Bank man is available and certified 8 - The crane operator have a practical and theoretical knowledge of lifting operations 9 - Lifting operations will be undertaken by a minimum of three competent people the crane operator, slinger / signaler (slinger and signaler can be one person) / banks man / flagman (banks man and flagmen can be one person) and Supervisor 10 - Certification of Lifting Equipment / Lifting Gear / Lifting Devices 11 - Lifting plan prepared/approved/communicated 12 - Lifting gear (Chain sling, shackle, webbing sling, lifting clamps etc.) / devices (Chain block, Winch, Monorail etc.) are checked, inspected & tagged - ( size, length, dia, width, SWL,Condition & defects. 13 - All lifting equipment / gears have valid test certificates and are in good condition.
Note on T25: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there process of SBO for leadership to identify and reinforce safe work practices/behaviors? 2 - Is there process of SBO for leadership to identify and improve on at-risk practices? 3 - Is there process of SBO for leadership to identify and improve on practices, conditions, controls, and compliance that eliminate or reduce hazards? 4 - Is there a process of SBO for leadership to make positive, corrective, cooperative, collaborative feedback/recommendations? 5 - Is there a training program for BBST, that how to identify critical safety behavior and how to provide feedback and the number of personnel trained. 6 - Is there a program for the leadership to carry out SBO once a month or twice (depends project scope of work), and record available?

## HSE-Stat
Safety Statistics
Category | Item |  | This Week | This Month | Year to Date | Cumulative
Category | Total Hours Worked |  | 9216 | 26112 | 438898 | 465010
| Safe Hours Worked |  | 9216 | 26112 | 438898 | 465010
| LTI |  | 0 | 0 | 0 | 0
| MTC (Healed w/o Disability) |  | 0 | 0 | 0 | 0
| MTC (Healed w/ Disability) |  | 0 | 0 | 0 | 0
| Near Miss |  | 0 | 0 | 0 | 0
| First Aid Cases |  | 0 | 0 | 0 | 0
| Fatality |  | 0 | 0 | 0 | 0
| Fire Incident Cases |  | 0 | 0 | 0 | 0
| Vehicle Incident |  | 0 | 0 | 0 | 0
| Property Damages |  | 0 | 0 | 0 | 0
Proactive | Induction Training |  | 0 session | 0 session | 63 | 63
| No.of Internal Training |  | 0session | 0 session | 61 | 61
| No.of Internal Audit |  | 0 | 0 | 0 | 0
| No. of Toolbox Talks |  | 0 sessions | 0 sessions | 88 | 88
| Safety Awards/Incentives |  | 0 | 0 | 0 | 0
[7 empty] | Category | Item | This Week | This Month | Year to Date | Cumulative
Consultant Safety Inspection (Weekly Basis) | [6 empty] | Overall Average | 73.02%
Week Number | Date of Audit | Date Issued | Numbers Of Comments | Overall Score | Date Closed | Closure Duration | This Week Score | 77.17%
Week-1 | 2025-11-25
Week-2 | 2025-12-02
Week-3 | 2025-12-09
Week-4 | 2025-12-16
Week-5 | 2025-12-23
Week-6 | 2025-12-30 | 2025-12-27 | 2 | 80% | 2025-12-28 | 1
Week-7 | 2026-01-06 | 2026-01-02 | 2 | 48% | 2026-01-04 | 2
Week-8 | 2026-01-13 | 2026-01-09 | 2 | 48% | 2026-01-11 | 2
Week-9 | 2026-01-20 | 2026-01-15 | 1 | 60% | 2026-01-18 | 3
Week-10 | 2026-01-27 | 2026-01-21 | 2 | 60% | 2026-01-24 | 3
Week-11 | 2026-02-03 | 2026-01-31 | 1 | 60% | 2026-02-02 | 2
Week-12 | 2026-02-10 | 2026-02-06 | 1 | 72% | 2026-02-09 | 3
Week-13 | 2026-02-17 | 2026-02-12 | 1 | 72% | 2026-02-15 | 3
Week-14 | 2026-02-24 | 2026-02-21 | 2 | 72% | 2026-02-23 | 2
Week-15 | 2026-03-03 | 2026-02-26 | 1 | 72% | 2026-03-01 | 3
Week-16 | 2026-03-10 | 2026-03-07 | 2 | 72% | 2026-03-08 | 1
Week-17 | 2026-03-17 | 2026-03-12 | 2 | 72% | 2026-03-15 | 3
Week-18 | 2026-03-24
Week-19 | 2026-03-31 | 2026-03-29 | 2 | 72% | 2026-03-30 | 1
Week-20 | 2026-04-07 | 2026-04-04 | 2 | 73% | 2026-04-05 | 1
Week-21 | 2026-04-14 | 2026-04-11 | 2 | 73% | 2026-04-12 | 1
Week-22 | 2026-04-21 | 2026-04-17 | 1 | 73% | 2026-04-19 | 2
Week-23 | 2026-04-28 | 2026-04-24 | 3 | 73% | 2026-04-26 | 2
Week-24 | 2026-05-05 | 2026-05-02 | 2 | 75% | 2026-05-03 | 1
Week-25 | 2026-05-12 | 2026-05-09 | 1 | 75% | 2026-05-10 | 1
Week-26 | 2026-05-19 | 2026-05-16 | 2 | 73% | 2026-05-17 | 1
Week-27 | 2026-05-26
Week-28 | 2026-06-02 | 2026-05-30 | 3 | 73% | 2026-05-31 | 1
Week-29 | 2026-06-09 | 2026-06-05 | 1 | 76% | 2026-06-07 | 2
Week-30 | 2026-06-16 | 2026-06-14 | 2 | 76% | 2026-06-16 | 2
Week-31 | 2026-06-23 | 2026-06-21 | 4 | 64% | 2026-06-20 | 3
Week-32 | 2026-06-30 | 2026-06-28 | 3 | 64% | 2026-06-29 | 2
Week-33 | 2026-07-07 | 2026-07-05 | 2 | 70% | 2026-07-06 | 2
Week-34 | 2026-07-14 | 2026-07-12 | 3 | 75% | 2026-07-13 | 3
Week-35 | 2026-07-21 | 2026-07-19 | 3 | 75% | 2026-07-20 | 3
Week-36 | 2026-07-28 | 2026-07-26 | 2 | 69% | 2026-07-27 | 2
Week-37 | 2026-08-04 | 2026-08-02 | 3 | 69% | 2026-08-03 | 2
Week-38 | 2026-08-11 | 2026-08-09 | 2 | 72% | 2026-08-10 | 2
Week-39 | 2026-08-18 | 2026-08-16 | 2 | 84% | 2026-08-17 | 2
Week-40 | 2026-08-25 | 2026-08-23 | 2 | 84% | 2026-08-24 | 2
Week-41 | 2026-09-01 | 2026-08-30 | 3 | 84% | 2026-08-31 | 2
Week-42 | 2026-09-08 | 2026-09-06 | 2 | 86% | 2026-09-07 | 2
Week-43 | 2026-09-15 | 2026-09-13 | 2 | 86% | 2026-09-14 | 2
Week-44 | 2026-09-22 | 2026-09-21 | 2 | 86% | 2026-09-20 | 2
Week-45 | 2026-09-29 | 2026-09-28 | 3 | 86% | 2026-09-26 | 3
Week-46 | 2026-10-06 | 2026-10-05 | 2 | 86% | 2026-10-03 | 2
Week-47 | 2026-10-13 | 2026-10-11 | 3 | 77% | 2026-10-10 | 3
Week-48 | 2026-10-20 | 2026-10-18 | 2 | 77% | 2026-10-17 | 2
Week-49
Week-50
Week-51
Week-52
Week-53
Week-54
Week-55
Week-56
Week-57
Week-58
Week-59
Week-60
Week-61
Week-62
Week-63
Week-64
Week-65
Week-66
Week-67
Week-68
Week-69
Week-70
Week-71
Week-72
Week-73
Week-74
Week-75
Week-76
Week-77
Week-78
Week-79
Week-80
Week-81
Week-82
Week-83
Week-84
Week-85
Week-86
Formulas:
Item = [Item, row above]+7

## Invoice Log
Weekly Progress Report - Invoice Log | [31 empty] | Y
Project Value | [9 empty] | Payment Status | [7 empty] | Invoices Summary | [9 empty] | Average Invoices durations |  |  |  | N
Original Contract Value |  |  | 86782345 |  | O&M Value |  | 0 |  | Advance Payment % |  | 0% |  | Advance Payment (SAR) |  | 0 |  | No of Submitted Invoices |  | 6 |  | Submitted Invoices (SAR) |  | 44851849.3625 |  | Submiited Invoice Peroid | 2026-09-29 | CM / PgM Average Approval duration |  | 0.42857 | Average Invoice Value | 6407407.0518
Revised Contract Value |  |  | 86782345 |  | Revised O&M Value |  | 0 |  | Retention % |  | 0% |  | Retention (SAR) |  | 0 |  | No of Approved Invoices (CM) |  | 7 |  | Approved Invoices (CM) (SAR) |  | 51579626.7669 |  |  |  | MODON PM & Accounts Average Approval duration |  | 15.8333
Estimate At Completion Value |  |  | 86782345 |  | Submitted Invoices (Gross Value) |  | 44851849.3625 |  | Penalties and deduction % |  | 0% |  | AP Recovery (SAR) |  | 0 |  | No of Approved Invoices (PM) |  | 7 |  | Approved Invoices (PM) (SAR) |  | 51579626.7669 |  | Invoice Submitted Compared to Contract Value | 51.68% | Payments Average Duration |  | 36.8333
Potential Changes |  |  | 0 |  | Total Deduction |  | 0 |  | Penalties and deduction (SAR) |  | 0 |  | Retention Cumulative (SAR) |  | 0 |  | No of Paid Invoices |  | 6 |  | Paid Invoices (SAR) |  | 48055957.6059 |  |  |  | Invoices Average total Duration |  | 37.5
Invoice Reference |  |  |  | Invoice Value |  |  |  |  | Period Covered |  |  | CM / PgM Approval Timeline |  |  |  | Modon PM & Accounts Approval | [6 empty] | Payment Status |  |  |  |  | Total Invoice Duration | Remarks
# | Invoice No. | Doc Control reference | Submittal Rev. # | Gross Value | AP Recovery | Retention | Deduction / Penalties | Amount (net) | Start Date | End Date | Date to CM / PgM | CM / PgM Approval (Yes/No) | CM / PgM Reply Date | Days Elapsed | Date to PM | PM Approval (Yes/No) | PM Reply Date | Date to Accounts | Accounts Approval (Yes/No) | Accounts Approval Date | Days Elapsed | Date Paid | Amount Paid | Paid % | Payment Period (d) | Amount Pending
1 | 1 | JDH1-02-003-ENJ-TS9-1-COM-INV-0027-01 | 0 | 1992643.8425 | 0 | 0 | 0 | 2291540.4189 | 2025-11-19 | 2026-01-25 | 2026-01-28 | Y | 2026-01-28 | 0 | 2026-01-29 | Y | 2026-01-31 | 2026-02-10 | Y | 2026-02-10 | 12 | 2026-05-10 | 2291540.4189 | 100% | 89 | 0 | 40
2 | 2 | JDH1-02-003-ENJ-TS9-1-COM-INV-0043-01 | 0 | 5438489.97 | 0 | 0 | 0 | 6254263.4655 | 2026-01-26 | 2026-03-30 | 2026-03-31 | Y | 2026-04-01 | 1 | 2026-04-01 | Y | 2026-04-01 | 2026-04-04 | Y | 2026-04-05 | 4 | 2026-06-04 | 6254263.4655 | 100% | 60 | 0 | 29 |  |  |  | format if no, make shaded
3 | 3 | JDH1-02-003-ENJ-TS9-1-COM-INV-0055-00 | 0 | 6962016.37 | 0 | 0 | 0 | 8006318.8255 | 2026-03-31 | 2026-05-06 | 2026-05-06 | Y | 2026-05-07 | 1 | 2026-05-07 | Y | 2026-05-08 | 2026-05-08 | Y | 2026-06-30 | 54 | 2026-07-05 | 8006318.8255 | 100% | 5 | 0 | 60
4 | 4 | JDH1-02-003-ENJ-TS9-1-COM-INV-0068-00 | 0 | 12533257.53 | 0 | 0 | 0 | 14413246.1595 | 2026-05-07 | 2026-06-20 | 2026-06-29 | Y | 2026-06-29 | 0 | 2026-06-29 | Y | 2026-06-30 | 2026-07-05 | Y | 2026-07-07 | 8 | 2026-08-05 | 14413246.1595 | 100% | 29 | 0 | 37
5 | 5 | JDH1-02-003-ENJ-TS9-1-COM-INV-0078-00 | 0 | 9833283.9 | 0 | 0 | 0 | 11308276.485 | 2026-06-21 | 2026-07-30 | 2026-07-30 | Y | 2026-07-30 | 0 | 2026-08-01 | Y | 2026-08-02 | 2026-08-05 | Y | 2026-08-05 | 4 | 2026-08-30 | 11308276.485 | 100% | 25 | 0 | 31
6 | 6 | JDH1-02-003-ENJ-TS9-1-COM-INV-0088-00 | 0 | 5028097.61 | 0 | 0 | 0 | 5782312.2515 | 2026-07-31 | 2026-08-30 | 2026-08-30 | Y | 2026-08-30 | 0 | 2026-09-01 | Y | 2026-09-03 | 2026-09-05 | Y | 2026-09-14 | 13 | 2026-09-27 | 5782312.2515 | 100% | 13 | 0 | 28
7 |  | JDH1-02-003-ENJ-TS9-1-COM-INV-0098-00 | 0 | 3064060.14 | 0 | 0 | 0 | 3523669.161 | 2026-08-31 | 2026-09-29 | 2026-09-29 | Y | 2026-09-30 | 1 | 2026-10-03 | Y | 2026-10-03 | 2026-10-06
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
|  |  | TOTAL | 44851849.3625 | 0 | 0 | 0 | 51579626.7669 | [14 empty] | 48055957.6059 |  |  | 0
49835388.1806
Note on I3: Without O&M Cost

## Invoice Ammount FIR
86782344.73
SL. | date of FIR | TOTAL AMOUNT | Total Amount % (as per FIR)
1 | 2025-12-23 | 0 | 0%
2 | 2025-12-30 | 1342209.63 | 1.547% |  | weekly invoice
3 | 2026-01-04 | 1548711.48 | 1.785%
4 | 2026-01-11 | 2161553.57 | 2.491%
5 | 2026-01-18 | 2438279.81 | 2.81%
6 | 2026-01-25 | 3413204.4 | 3.933%
7 | 2026-02-02 | 4999723.11 | 5.761%
8 | 2026-02-08 | 6264074.7 | 7.218%
9 | 2026-02-15 | 7612053.39 | 8.771%
10 | 2026-02-24 | 8630947.81 | 9.946%
11 | 2026-03-03 | 9629665.62 | 11.1%
12 | 2026-03-09 | 10832959.66 | 12.48%
13 | 2026-03-16 | 12485173.28 | 14.39%
14 | 2026-03-24 | 13373011.86 | 15.41%
15 | 2026-03-30 | 13432568.08 | 15.48%
16 | 2026-04-05 | 13432568.08 | 15.48%
16 | 2026-04-13 | 17130141.67 | 19.74%
17 | 2026-04-20 | 19693513.34 | 22.69%
19 | 2026-04-26 | 21306727.54 | 24.55%
20 | 2026-05-03 | 22837643.33 | 26.32%
21 | 2026-05-10 | 26241135.36 | 30.24%
22 | 2026-05-17 | 27820904.43 | 32.06%
23 | 2026-05-24 | 27912388.35 | 32.16%
24 | 2026-05-31 | 30569920.27 | 35.23%
25 | 2026-06-07 | 32538463.28 | 37.49%
26 | 2026-06-15 | 33516783.14 | 38.62%
27 | 2026-06-22 | 34822475.39 | 40.13%
28 | 2026-06-29 | 36370093.43 | 41.91%
29 | 2026-07-07 | 39700000 | 45.75%
30 | 2026-07-14 | 41822116.04 | 48.19%
31 | 2026-07-21 | 43081772.97 | 49.64%
32 | 2026-07-28 | 45316047.09 | 52.22%
33 | 2026-08-04 | 47592246.12 | 54.84%
34 | 2026-08-11 | 49180855.71 | 56.67%
35 | 2026-08-18 | 50057107.63 | 57.68%
36 | 2026-08-25 | 50615678.63 | 58.32%
37 | 2026-09-01 | 51626734.59 | 59.49%
38 | 2026-09-08 | 52712815.16 | 60.74%
39 | 2026-09-15 | 53721283.73 | 61.9%
40 | 2026-09-22 | 54133552.58 | 62.38%
41 | 2026-09-29 | 54629505.81 | 62.95%
42 | 2026-10-06 | 55338219.12 | 63.77%
43 | 2026-10-13 | 56765678.34 | 65.41%
44 | 2026-10-20 | 57162746.82 | 65.87%

## CCO
CONTRACT CHANGE ORDER (CCO)
CCO No. | Date Added | Description of Change | Status | SR | Sch Impact (Months) | Date Approved | Duration (days)
- | - | - | - | - | - | - | -

## Procurement
Sr. NO. | Project ID | ACT#inP6 | Item Description | Discipline | (Long \Short) Lead Items | BOQ. No. | Unit | Quantity | Proc. Qty | Required P.O Date | Date of Pur. Order Issued | Purchase Order No. | Supplier | Supplier Phone | Method of Shipping | Required on Job | E.D.A. to Site | A.D.A. to Site | Lead Time | Approval Status | Completion Rate | The Impact (BOQ Cost) | Remarks
1
2 | JDH1-02-003 | Road - Civil |  | Road - Civil | Short
3 | JDH1-02-003 | CON-LEG101-PR-1390 | Steel Reinforcement | CIVIL | Short | 03 45 00.03 | ton | 126 | 126 | 2025-12-30 | 2025-12-15 | P116327 | BRC | 599556849 | Local | 2026-01-24 |  | 2025-12-16 | Short | Approved | 100% |  | Delivered Done |  |  | 1
4 | JDH1-02-003 | CON-LEG101-PR-1420 | Ready Mixed Concrete | CIVIL | Short | 03 30 00 | m³ | 4835 | 4835 | 2026-01-05 |  |  | Enjazco & Al Arabia Construction |  | Local | 2026-02-17 |  | 2025-12-21 | Short | Approved | 100% |  | Delivered Done | Delay |  | 1
5 | JDH1-02-003 | CON-LEG101-PR-3990 | Backfilling Materials | Roads | Short | 31 22 00 | m³ | 234480 | 234480 | 2026-01-08 |  |  | Enjazco |  | Local | 2026-02-26 |  | 2025-12-01 | Short | Approved | 100% |  | Delivered Done | Delay |  | 1
6 | JDH1-02-003 | CON-LEG101-PR-1470 | Aggregate Base Course | Roads | Short | 32 11 23.01 | m³ | 24870 | 224870 | 2026-01-11 | 2026-01-07 |  | Enjazco |  | Local | 2026-06-11 | 2026-02-15 | 2026-01-15 | Short | Approved | 100% |  | Delivered Done |  |  | 1
7 | JDH1-02-003 | CON-LEG101-PR-1520 | Precast Concrete Kerb | CIVIL | Short | 32 14 13 | m | 59990 | 59990 | 2026-01-15 |  |  | Enjazco |  | Local | 2026-12-12 | 2026-06-01 |  | Short | Approved | 100% |  | Delivered Done | Delay |  | 1
8 | JDH1-02-003 | CON-LEG101-PR-1550 | Interlocking Block Pavers | CIVIL | Short | 32 14 13.13 | m2 | 57905 |  | 2026-01-15 |  |  |  |  | Local | 2026-12-12 |  |  | Short | Approved | 100% |  | Delivered Done | Delay |  | 1
9 | JDH1-02-003 | CON-LEG101-PR-1440 | Water Proofing | CIVIL | Short | 07 00 00.01 | m2 | 19530 | 19530 | 2026-01-11 | 2026-01-03 | P117746 | Saleh Sunaid | 0506506735 | Local | 2026-03-15 | 2026-01-15 | 2026-01-05 | Short | Approved | 100% |  | Delivered Done |  |  | 1
10 | JDH1-02-003 | CON-LEG101-PR-1580 | Pavement Markings | Roads | Short | 32 17 23 | m2 | 3780 |  | 2026-01-17 |  |  |  |  | Local | 2027-04-04 |  |  | Short | Approved | 100% |  | Delivered Done | Delay |  | 1
11 | JDH1-02-003 | CON-LEG101-PR-1500 | Bituminous Base Course | Roads | Short | 32 11 26.01 | m3 | 8290 | 8290 | 2026-01-17 | 2026-01-01 |  | ENJAZCO |  | Local | 2026-07-06 | 2026-07-06 |  | Short | Approved | 100% |  | Delivered Done |  |  | 1
12 | JDH1-02-003 | CON-LEG101-PR-1500 | Bituminous Wearing Course | Roads | Short | 32 12 16.01 | m3 | 5920 | 5920 | 2026-01-17 | 2026-01-01 |  | ENJAZCO |  | Local | 2027-04-11 | 2026-11-15 | 2026-09-29 | Short | Approved | 100% |  | Delivered Done |  |  | 1
13 | JDH1-02-003 | CON-LEG101-PR-1610 | Traffic Signs | Roads | Long | 10 14 53 | Nos | 261 | 261 | 2026-01-17 | 2025-12-25 | P117196 | AL-HARAMAIN | 055 892 8861 | Local | 2026-12-29 | 2026-09-30 |  | Long | Approved | 100% |  | Delivered Done |  | تحويل عتد م.اسلام عبدالسميع | 1
14 | JDH1-02-003 | CON-LEG101-PR-2000 | Metal Fence | CIVIL | Long | 32 31 13.04 | m | 3356 | 1623 | 2026-01-06 | 2025-12-27 | P117265 | BRC | 0583880333 | Local | 2026-04-27 | 2026-04-27 |  | Long | Approved | 100% |  | Delivered Done |  |  | 1
15 | JDH1-02-003 | CON-LEG101-PR-2030 | Gates | CIVIL | Long | 32 31 13.01 | Nos | 6 | 6 | 2026-01-12 | 2025-12-27 | P117265 | BRC | 0583880333 | Local | 2026-08-09 | 2026-06-15 |  | Long | N/A | 0% |  | N/A |  |  | 1
16 | JDH1-02-003 | CON-LEG101-PR-2610 | Paint On Cement Plaster | CIVIL | Long | 09 91 00.01 | m2 | 4062 | 4062 | 2026-01-18 | 2026-01-13 | P118432 | DCP | 0507862088 | Local | 2026-05-26 | 2026-01-25 |  | Long | Approved | 100% |  | Delivered Done |  |  | 1
17 | JDH1-02-003 | CON-LEG101-PR-3000 | agricultural soil | CIVIL | Long | 32 90 00.01 | m2 | 9115 |  | 2026-01-18 |  |  |  |  | Local | 2027-09-02 |  |  | Long |  |  |  | PO ISSUED | Delay |  | 1
18 | JDH1-02-003 |  | SH-01, Golden daisy bush euryops pectinatus | CIVIL | Short | 32 90 00.01 | m2 | 9115 |  | 2026-01-18 |  |  |  |  | Local | 2027-09-14 |  |  | Short | Approved | 100% |  | Delivered Done | Delay |  | 1
19 | JDH1-02-003 | CON-LEG101-PR-2140 | Prestressing Strands | CIVIL | Long | 03 45 00.02 | ton | 24 | 24 | 2026-01-13 | 2026-02-12 |  |  |  | Local | 2026-05-04 |  |  | Long | Approved | 100% |  | Delivered Done |  | تحويل عتد م.اسلام عبدالسميع | 1
20 | JDH1-02-003 | CON-LEG101-PR-2200 | Bridge Bearings | CIVIL | Long | 14 70 00.01 | Nos | 14 | 14 | 2026-01-17 | 2026-02-12 | P121188 | AL-Bunyan | 533251336 | Local | 2026-06-18 | 2026-03-16 |  | Long | Approved | 100% |  | Delivered Done |  |  | 1
21 | JDH1-02-003 | CON-LEG101-PR-2390 | Bridge Gully (Scupper) drainage | CIVIL | Long | 33 44 00.01 | Nos | 3 |  | 2026-01-17 |  |  |  |  | Local | 2026-08-04 |  |  | Long |  | 100% |  | Delivered Done | Delay | تحويل عتد م.اسلام عبدالسميع | 1
22 | JDH1-02-003 | CON-LEG101-PR-2170 | New Jersey | CIVIL | Long | 13 14 32.01 | m | 96 |  | 2026-01-17 |  |  |  |  | Local | 2026-09-24 |  |  | Long | Approved | 100% |  | Delivered Done | Delay | تحويل عتد م.اسلام عبدالسميع | 1
23 | JDH1-02-003 | CON-LEG101-PR-2230 | Expansion Joints | CIVIL | Long | 07 95 13.01 | m | 28 | 28 | 2026-01-17 | 2026-02-12 |  | AL BUNYAN EST LTD |  | Local | 2026-12-27 |  |  | Long | Approved | 100% |  | Delivered Done |  | تحويل عتد م.اسلام عبدالسميع | 1
24 | JDH1-02-003 | CON-LEG101-PR-2280 | Guard Rail | CIVIL | Long | 05 50 00.01 | m | 80 |  | 2026-01-17 |  |  |  |  | Local | 2027-01-25 |  |  | Long | Approved |  |  | PO ISSUED | Delay | تحويل عتد م.اسلام عبدالسميع | 1
25 | JDH1-02-003 | CON-LEG101-PR-2360 | Logo MODON | CIVIL | Long | 10 14 23.01 | Nos | 2 | 2 | 2026-01-17 |  |  |  |  | Local | 2027-05-03 |  | 2026-09-10 | Long | Approved | 100% |  | Delivered Done | Delay | تحويل عتد م.اسلام عبدالسميع | 1
26 | JDH1-02-003 | CON-LEG101-PR-2320 | GRP Panel | CIVIL | Long | 06 64 00.01 | m2 | 235 |  | 2026-01-17 |  |  |  |  | Local | 2027-04-13 |  |  | Long |  |  |  | PO ISSUED | Delay | تحويل عتد م.اسلام عبدالسميع | 1
27 | JDH1-02-003 |  | Membrane waterproofing | CIVIL | Short | 07 13 26.01 | m2 | 644 | 644 | 2026-01-17 | 2026-01-03 | P117746 | Saleh Sunaid | 0506506735 | Local | 2027-01-25 | 2026-02-01 | 2025-12-25 | Short | Approved | 100% |  | Delivered Done |  |  | 1
28 | JDH1-02-003 |  | Protective Coating for Concrete Surfaces | CIVIL | Short | 09 96 00.01 | m2 | 1874 | 1874 | 2026-01-17 |  |  | ENJAZCO |  | Local | 2027-01-25 | 2026-09-01 |  | Short | Approved | 100% |  | Delivered Done | Delay |  | 1
29 | JDH1-02-003 | CON-LEG101-PR-3010 | Curbs and edging | CIVIL | Short | 32 14 13.05 | m | 340 | 340 | 2026-01-18 |  |  | ENJAZCO |  | Local | 2027-01-05 | 2026-09-01 |  | Short | Approved | 100% |  | Delivered Done | Delay |  | 1
30 | JDH1-02-003 | [24 empty] | 1
31 | JDH1-02-003 | MECHANICAL | [23 empty] | 1
32 | JDH1-02-003 | CON-LEG101-PR-1700 | GRP Pipes for Sewer network | MECHANICAL | Long | 33 31 00 | m | 6737 | 6737 | 2026-01-03 | 2025-12-17 | P117065 | Tarek Nagadi & Almunif | 0500195198 | Local | 2026-04-23 | 2025-12-28 | 2025-12-28 | Long | Approved | 100% |  | Delivered Done |  |  | 1
33 | JDH1-02-003 | CON-LEG101-PR-1730 | Fiberglass Manholes for Sewer network | MECHANICAL | Long | 33 05 76 | m | 122 | 122 | 2026-01-11 | 2026-12-29 | P117477 | Tarek Nagadi & Almunif | 0500195198 | Local | 2026-05-02 | 2026-01-10 | 2026-01-22 | Long | Approved | 100% |  | Delivered Done |  |  | 1
34 | JDH1-02-003 | CON-LEG101-PR-1670 | HDPE Pipe (PN 16) for TSE | MECHANICAL | Long | 33 14 13 | m | 9424 | 9424 | 2026-01-08 | 2026-01-01 | P117621 | Neproplast | 0557128534 | Local | 2026-05-23 | 2026-01-07 |  | Long | Approved | 100% |  | Delivered Done |  |  | 1
35 | JDH1-02-003 | CON-LEG101-PR-1360 | Valves for TSE | MECHANICAL | Long | 33 14 19 | Nos | 142 | 142 | 2026-01-19 | 2026-01-28 | P119667 | SPS | 0505275340 | Local | 2026-06-25 | 2026-02-15 | 2026-02-03 | Long | Approved | 100% |  | Delivered Done |  |  | 1
36 | JDH1-02-003 | CON-LEG101-PR-2440 | Fire Hydrant | MECHANICAL | Long | 33 14 19.15 | Nos | 89 | 89 | 2026-01-14 | 2026-01-28 | P119667 | SPS | 0505275340 | Local | 2026-08-18 | 2026-02-15 | 2026-02-03 | Long | Approved | 100% |  | Delivered Done |  |  | 1
36 | JDH1-02-003 | CON-LEG101-PR-1790 | GRP Pipes for Storm network | MECHANICAL | Long | 33 42 11 | m | 5939 | 5939 | 2026-01-03 | 2025-12-09 |  | Tarek Nagadi & Almunif | 0507779468 | Local | 2026-04-22 | 2025-12-16 | 2025-12-16 | Long | Approved | 100% |  | Delivered Done |  | تحويل عند م اسلام عبدالسميع | 1
37 | JDH1-02-003 | CON-LEG101-PR-1760 | UPVC Pipes | MECHANICAL | Long | 33 42 11 | m | 3127 | 3127 | 2026-01-03 | 2026-12-18 | P116662 | Al-Munif | 0507775269 | Local | 2026-04-23 | 2026-01-30 | 2026-01-31 | Long | Approved | 100% |  | Delivered Done |  |  | 1
37 | JDH1-02-003 | CON-LEG101-PR-1820 | Inlet Manholes for Storm network | MECHANICAL | Long | 33 05 13 | Nos | 130 | 130 | 2026-01-13 | 2025-12-22 | P116883 | Tarek Nagadi & Saudi Land | 0553455856 | Local | 2026-04-28 | 2025-12-28 | 2025-12-28 | Long | Approved | 100% |  | Delivered Done |  |  | 1
38 | JDH1-02-003 | CON-LEG101-PR-1850 | Concrete chambers | MECHANICAL | Long | 33 05 13.08 | Nos | 180 | 180 | 2026-01-19 | 2026-01-21 | P119137 | Tarek Nagadi | 0500195198 | Local | 2026-05-21 | 2026-02-15 | 2026-01-31 | Long | Approved | 100% |  | Delivered Done |  |  | 1
39 | JDH1-02-003 | CON-LEG101-PR-1640 | HDPE Pipe (PN 16) for Ptable Water | MECHANICAL | Long | 33 14 13 | m | 10852 | 10852 | 2026-01-10 | 2026-01-01 | P117621 | Neproplast | 0557128534 | Local | 2026-04-30 | 2026-01-04 | 2026-01-04 | Long | Approved | 100% |  | Delivered Done |  |  | 1
40 | JDH1-02-003 | CON-LEG101-PR-1330 | Valves for Ptable Water | MECHANICAL | Long | 33 14 19 | Nos | 108 | 108 | 2026-01-14 | 2026-01-28 | P119667 | SPS | 0505275340 | Local | 2026-07-25 | 2026-02-15 | 2026-02-03 | Long | Approved | 100% |  | Delivered Done |  |  | 1
41 | JDH1-02-003 | CON-LEG101-PR-2960 | Electrical Solenoid Valve | MECHANICAL | Long | 32 84 00.04 | Nos | 8 |  | 2026-01-18 |  |  |  |  | Local | 2027-01-17 |  | 2026-10-15 | Long | Approved | 100% |  | Delivered Done | Delay |  | 1
42 | JDH1-02-003 | CON-LEG101-PR-2970 | Quick coupler valve | MECHANICAL | Long | 32 84 00.06 | Nos | 8 |  | 2026-01-18 |  |  |  |  | Local | 2027-02-06 |  | 2026-10-15 | Long | Approved | 100% |  | Delivered Done |  |  | 1
43 | JDH1-02-003 | CON-LEG101-PR-3100 | Flush valve | MECHANICAL | Long | 32 84 00.07 | Nos | 50 |  | 2026-01-18 |  |  |  |  | Local | 2027-03-03 |  | 2026-10-15 | Long | Approved | 100% |  | Delivered Done |  |  | 1
44 | JDH1-02-003 | CON-LEG101-PR-2980 | Irrigation controller | MECHANICAL | Long | 32 84 00.09 | Nos | 1 |  | 2026-01-18 |  |  |  |  | Local | 2027-03-27 |  | 2026-10-15 | Long | Approved | 100% |  | Delivered Done |  |  | 1
45 | JDH1-02-003 | CON-LEG101-PR-3140 | Decoder for valve | MECHANICAL | Long | 32 84 00.10 | Nos | 8 |  | 2026-01-18 |  |  |  |  | Local | 2027-04-22 |  | 2026-10-15 | Long | Approved | 100% |  | Delivered Done |  |  | 1
46 | JDH1-02-003 | CON-LEG101-PR-2990 | Decoder Cables | MECHANICAL | Long | 32 84 00.11 | m | 3225 |  | 2026-01-18 |  |  |  |  | Local | 2027-01-17 |  | 2026-10-15 | Long | Approved | 100% |  | Delivered Done |  |  | 1
47 | JDH1-02-003 | CON-LEG101-PR-2820 | Single station decoder | MECHANICAL | Long | 32 84 00.10 | Nos | 8 |  | 2026-01-19 |  |  |  |  | Local | 2027-06-02 |  | 2026-10-15 | Long | Approved | 100% |  | Delivered Done |  |  | 1
48 | JDH1-02-003 | CON-LEG101-PR-2750 | Decoder cables 12 AWG | MECHANICAL | Long | 32 84 00.11 | m | 3225 |  | 2026-01-19 |  |  |  |  | Local | 2027-06-10 |  | 2026-10-15 | Long | Approved | 100% |  | Delivered Done |  |  | 1
49 | JDH1-02-003 | ELECTRICAL | [23 empty] | 1
50 | JDH1-02-003 | CON-LEG101-PR-3160 | Pipe for Duct | ELECTRICAL | Long | 33 71 19 | m | 700 |  | 2026-01-06 |  |  |  |  | Local | 2026-09-27 |  |  | Long | Approved | 100% |  | Delivered Done | Delay |  | 1
51 | JDH1-02-003 | CON-LEG101-PR-3190 | Low Voltage Cables | ELECTRICAL | Long | 26 05 19 | m | 39240 |  | 2026-01-15 |  |  |  |  | Local | 2026-10-29 |  |  | Long | Approved | 100% |  | Delivered Done | Delay |  | 1
52 | JDH1-02-003 | CON-LEG101-PR-3200 | Manhole | ELECTRICAL | Long | 33 71 19.13 | Nos | 77 |  | 2026-01-18 |  |  |  |  | Local | 2026-11-16 |  |  | Long | Approved | 100% |  | Delivered Done | Delay |  | 1
53 | JDH1-02-003 | CON-LEG101-PR-1260 | Pipe for Duct | ELECTRICAL | Long | 33 71 19 | m | 500 |  | 2026-01-06 |  |  |  |  | Local | 2026-05-18 |  |  | Long | Approved | 100% |  | Delivered Done | Delay |  | 1
54 | JDH1-02-003 | CON-LEG101-PR-1240 | Cable Termination & Joints | ELECTRICAL | Long | 26 05 13.16 | Nos | 64 |  | 2026-01-14 |  |  |  |  | Local | 2026-06-13 |  |  | Long | Approved |  |  | PO in Delay | Delay |  | 1
55 | JDH1-02-003 | CON-LEG101-PR-1250 | Earthing System | ELECTRICAL | Long | 26 05 26 | Nos | 70 |  | 2026-01-14 |  |  |  |  | Local | 2026-07-28 |  |  | Long | Approved | 100% |  | Delivered Done | Delay | Material Submite 2-10-2025 | 1
56 | JDH1-02-003 | CON-LEG101-PR-1000 | Medium Voltage Cable | ELECTRICAL | Long | 26 05 13.16.01 | m | 14500 |  | 2026-01-18 |  |  |  |  | Local | 2026-05-10 |  |  | Long | Approved |  |  | PO in Delay | Delay | Material Submite 2-10-2025 | 1
57 | JDH1-02-003 | CON-LEG101-PR-1010 | Street Lighting Sub-station | ELECTRICAL | Long | 26 11 16.01 | Nos | 4 |  | 2026-01-18 |  |  |  |  | Local | 2026-08-26 |  |  | Long | Approved |  |  | PO ISSUED | Delay |  | 1
58 | JDH1-02-003 | CON-LEG101-PR-1020 | Low Voltage Cables | ELECTRICAL | Long | 26 05 19 | m | 6115 |  | 2026-01-12 |  |  |  |  | Local | 2026-09-13 |  |  | Long | Approved | 100% |  | Delivered Done | Delay |  | 1
59 | JDH1-02-003 | CON-LEG101-PR-2480 | Ring Main Unit | ELECTRICAL | Long | 26 11 16.02 | Nos | 4 |  | 2026-01-18 |  |  |  |  | Local | 2026-10-20 |  |  | Long | Under Review |  |  | PO in Delay | Delay |  | 1
60 | JDH1-02-003 | CON-LEG101-PR-1030 | Lighting poles | ELECTRICAL | Long | 26 56 19.01 | Nos | 443 | 443 | 2026-01-17 | 2026-02-16 | P121189 | Al-Babtain | 564587728 | Local | 2026-08-27 | 2026-04-30 |  | Long | Approved | 100% |  | Delivered Done |  |  | 1
61 | JDH1-02-003 | CON-LEG101-PR-2520 | Lighting panels | ELECTRICAL | Long | 26 27 33 .01 | Nos | 4 |  | 2026-01-19 |  |  |  |  | Local | 2026-10-26 |  |  | Long | Approved | 100% |  | Delivered Done | Delay |  | 1
62 | JDH1-02-003 | CON-LEG101-PR-1040 | Street Lighting Luminaire | ELECTRICAL | Long | 26 56 19.02 | Nos | 443 | 443 | 2026-01-17 | 2026-02-16 | P121189 | Al-Babtain | 564587728 | Local | 2026-08-27 | 2026-04-30 |  | Long | Approved | 100% |  | Delivered Done |  |  | 1
62 | JDH1-02-003 | CON-LEG101-PR-1050 | KWHM | ELECTRICAL | Long | 04 20 00.01 | Nos | 4 |  | 2026-01-17 |  |  |  |  | Local | 2027-02-02 |  |  | Long | Approved | 100% |  | Delivered Done | Delay |  | 1
63 | JDH1-02-003 | CON-LEG101-PR-1060 | Feeder Piller | ELECTRICAL | Long | 26 24 16.01 | Nos | 10 |  | 2026-01-19 |  |  |  |  | Local | 2026-10-26 |  |  | Long | Approved | 100% |  | Delivered Done | Delay |  | 1
64 | JDH1-02-003 | CON-LEG101-PR-1070 | Street Lighting Panels | ELECTRICAL | Long | 26 24 16 | Nos | 4 |  | 2026-01-17 |  |  |  |  | Local | 2026-10-26 |  |  | Long | Approved | 100% |  | Delivered Done | Delay |  | 1
65 | JDH1-02-003 | CON-LEG101-PR-3270 | LED Screen 43" (24/7 operation) with Ethernet decoders | ELECTRICAL | Long | 28 20 00.04 | Nos | 4 |  | 2026-01-18 |  |  |  |  | Local | 2026-12-06 |  |  | Long | Approved | 100% |  | Delivered Done | Delay |  | 1
66 | JDH1-02-003 | CON-LEG101-PR-3740 | Network Video Recorder 4k 64 Channel | ELECTRICAL | Long | 28 20 00.05 | Nos | 1 |  | 2026-01-18 |  |  |  |  | Local | 2027-02-08 |  |  | Long | Approved | 100% |  | Delivered Done | Delay |  | 1
67 | JDH1-02-003 | CON-LEG101-PR-3770 | Keypad | ELECTRICAL | Long | 28 20 00.06 | Nos | 1 |  | 2026-01-18 |  |  |  |  | Local | 2027-02-15 |  |  | Long | Approved | 100% |  | Delivered Done | Delay |  | 1
68 | JDH1-02-003 | CON-LEG101-PR-3300 | Fiber Optic Patch Panel 12 port | ELECTRICAL | Long | 27 10 00.01 | Nos | 2 |  | 2026-01-15 |  |  |  |  | Local | 2026-10-14 |  |  | Long | Approved | 100% |  | Delivered Done | Delay |  | 1
69 | JDH1-02-003 | CON-LEG101-PR-3310 | Modular Industrial Switches for main pole | ELECTRICAL | Long | 27 20 00.01 | Nos | 1 |  | 2026-01-19 |  |  |  |  | Local | 2026-11-12 |  |  | Long | Approved | 100% |  | Delivered Done | Delay |  | 1
70 | JDH1-02-003 | CON-LEG101-PR-3380 | 8POE ports Industrial Switches for remote poles | ELECTRICAL | Long | 27 20 00.02 | Nos | 6 |  | 2026-01-18 |  |  |  |  | Local | 2026-10-11 |  |  | Long | Approved | 100% |  | Delivered Done | Delay |  | 1
71 | JDH1-02-003 | CON-LEG101-PR-3420 | Core Switch | ELECTRICAL | Long | 27 20 00.03 | Nos | 2 |  | 2026-01-18 |  |  |  |  | Local | 2026-12-17 |  |  | Long | Approved | 100% |  | Delivered Done | Delay |  | 1
72 | JDH1-02-003 | CON-LEG101-PR-3460 | Access Switch 48 port | ELECTRICAL | Long | 27 20 00.04 | Nos | 2 |  | 2026-01-18 |  |  |  |  | Local | 2026-12-26 |  |  | Long | Approved | 100% |  | Delivered Done | Delay |  | 1
73 | JDH1-02-003 | CON-LEG101-PR-3500 | Server | ELECTRICAL | Long | 27 42 00.01 | Nos | 3 |  | 2026-01-18 |  |  |  |  | Local | 2026-10-26 |  |  | Long | Approved | 100% |  | Delivered Done | Delay |  | 1
74 | JDH1-02-003 | CON-LEG101-PR-3540 | Stand rack 42U- 19" | ELECTRICAL | Long | 27 42 00.02 | Nos | 2 |  | 2026-01-19 |  |  |  |  | Local | 2027-01-21 |  |  | Long | Approved | 100% |  | Delivered Done | Delay |  | 1
75 | JDH1-02-003 | CON-LEG101-PR-3580 | IP Outdoor CCTV POE Camera,5 MP, Metal Housing | ELECTRICAL | Long | 28 20 00.01 | Nos | 28 |  | 2026-01-18 |  |  |  |  | Local | 2026-10-26 |  |  | Long | Approved | 100% |  | Delivered Done | Delay |  | 1
76 | JDH1-02-003 | CON-LEG101-PR-3640 | Outdoor PTZ with IR, HDTV 1080 and 31x optical, 12x digital | ELECTRICAL | Long | 28 20 00.02 | Nos | 7 |  | 2026-01-18 |  |  |  |  | Local | 2026-11-19 |  |  | Long | Approved | 100% |  | Delivered Done |  |  | 1
77 | JDH1-02-003 | CON-LEG101-PR-3680 | Security workstation with 1 x 19" LED screen | ELECTRICAL | Long | 28 20 00.03 | Nos | 1 |  | 2026-01-18 |  |  |  |  | Local | 2027-01-24 |  |  | Long | Approved | 100% |  | Delivered Done |  |  | 1
78 | JDH1-02-003 | CON-LEG101-PR-3720 | Horizontal Power Distribution Unit (min 8 outlets) | ELECTRICAL | Long | 28 20 00.04 | Nos | 4 |  | 2026-01-18 |  |  |  |  | Local | 2027-02-04 |  |  | Long | Approved | 100% |  | Delivered Done |  |  | 1
79 | JDH1-02-003 | CON-LEG101-PR-3820 | 35 Meters mono pole with Double Platform for Access Points | ELECTRICAL | Long | 26 33 54.01 | Nos | 1 |  | 2026-01-18 |  |  |  |  | Local | 2027-02-04 |  |  | Long | Approved | 100% |  | Delivered Done |  |  | 1
80 | JDH1-02-003 | CON-LEG101-PR-3860 | 25 Meters pole for CCTV Cameras | ELECTRICAL | Long | 26 33 54.02 | Nos | 6 |  | 2026-01-18 |  |  |  |  | Local | 2026-11-12 |  |  | Long | Approved | 100% |  | Delivered Done |  |  | 1
81 | JDH1-02-003 | CON-LEG101-PR-3900 | Short Range wireless point to point wireless bridge | ELECTRICAL | Long | 26 33 55.01 | Nos | 12 |  | 2026-01-18 |  |  |  |  | Local | 2026-11-12 |  |  | Long | Approved | 100% |  | Delivered Done |  |  | 1
#REF!
Y

## Issues
[9 empty] | 2026-10-20 | Status | Responsibility
[10 empty] | Open | Contractor
[10 empty] | Closed | Consultant
Modon
Third Party
Other
Issue Log
Issue No | Date Identified | Issue Description | Responsibility | Action Taken | Current Status | Expected/Actual Closure | Duration Elapsed
1 | 2025-12-15 | Update of Aggrement between MODON and SEC for Medium Voltage | Owner | 1. MODON contacted with SEC for getting Electric Source and it is under Process from SEC 2. Enjazco waiting for responding on Lettter No. (2818) 13.01.2026 | Open | 2025-12-30 |  | Owner
2 | 2025-11-25 | Permits from (SEC - STC - NWC) for allowing Construction works for Tie-in Lines (Sewer Line - TSE Line - Potable Water Line) | Contractor | Coordination done with all Servse Providers (STC - NWC - SEC (HV)) | closed | 2026-02-10 |  | Contractor
3 |  | Supplier Approval not included in Vendor List :: Pre-Qualification for Post Tension Works, Bearings and Expansion Joints Scope NOT IN VENDOR LIST Emirates Elite Trading Co. (ECO) Freyssinet Menard Saudi Arabia Ltd AL-BUNYAN EST. LT | Owner | PQD Submitted to Egis For Approval | closed |  |  | Consultant
4
5
6
7
8
9
10
48
49
50
13 |  | MV Network |  |  | Open

## Milestones
Project Name
Item No. | Milestones | Original (Baseline) | Latest | Forecast |  | Days Change
|  |  | 129.4286 | 130.4286 |  | -7
1 | Project Finish | 2027-11-18 | 2028-05-13 | 2028-05-20 | F | -7
2 | Project Start | 2025-11-19 | 2025-11-19 | 2025-11-19 | A | 0
3 | Finish Mobilization | 2025-11-11 | 2026-03-04 | 2026-03-04 | A | 0
4 | Finish Baseline Time Schedule | 2025-12-18 | 2025-12-18 | 2025-12-18 | A | 0
5 | Finish Submission and Approval for Shop Drawings, Method of Statement, Prequalification and Materials | 2026-01-19 | 2026-10-31 | 2026-11-07 | F | -7
6 | Finish PO for Short Lead Item & Long Lead Item | 2026-01-19 | 2026-10-25 | 2026-11-01 | F | -7
7 | Completion of Roads & Meduim Voltage | 2026-09-17 | 2027-01-11 | 2027-01-18 | F | -7
8 | Completion of Deep infrastructure network | 2026-11-18 | 2027-06-12 | 2027-06-19 | F | -7
9 | Completion of Shallow infrastructure network | 2027-03-18 | 2027-09-26 | 2027-10-03 | F | -7
10 | Completion all Works | 2027-11-18 | 2028-05-13 | 2028-05-20 | F | -7
| Activity ID | Activity Name | Original Duration | Activity Status | Activity % Complete | Physical % Complete | Duration % Complete | Units % Complete | Schedule % Complete | Performance % Complete | BL Project Start | BL Project Finish | Start | Finish | Budgeted Total Cost | Planned Value Cost | Earned Value Cost | Actual Total Cost | Budgeted Labor Units | Planned Value Labor Units | Earned Value Labor Units | Actual Labor Units | Total Float | Auto Compute Actuals
| JDH1-02-003 - Infrastructure Development For Industrial City 1 In Jeddah - Update - 20.10.2026 |  | 763 |  |  |  | 36.44% | 74.24% | 53.2% | 78.74% | 2025-11-19 | 2027-11-18 | 19-Nov-25 A | 2028-05-20 | 86782344.73 | 46153496.78 | 68315968.81 | 68315983.79 | 714561.27 | 347982.15 | 528822.75 | 531335.8 | -157
| Milestones |  | 763 |  |  |  | 37.64% | 0% | 0% | 0% | 2025-11-19 | 2027-11-18 | 19-Nov-25 A | 2028-05-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -157
| Key Milestones |  | 763 |  |  |  | 100% | 0% | 0% | 0% | 2025-11-19 | 2027-11-18 | 19-Nov-25 A | 2028-05-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -157
| CON-LEG101-MS-1090 | Project Commencement Date | 0 | Completed | 100% | 100% | 100% | 0% | 100% | 100% | 2025-11-19 |  | 19-Nov-25 A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | No
| CON-LEG101-MS-1000 | Project Completion Date | 0 | Not Started | 0% | 0% | 0% | 0% | 0% | 0% |  | 2027-11-18 |  | 2028-05-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -157 | No
| Contractual Milestone |  | 733 |  |  |  | 35.09% | 0% | 0% | 0% | 2025-12-18 | 2027-11-18 | 18-Dec-25 A | 2028-05-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -157
| Mobilization |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 2025-12-18 | 2025-12-18 | 04-Mar-26 A | 04-Mar-26 A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| CON-LEG101-MS-1070 | Finish Mobilization | 0 | Completed | 100% | 100% | 100% | 0% | 100% | 100% |  | 2025-12-18 |  | 2026-03-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | No
| Time Schedule |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 2025-12-18 | 2025-12-18 | 18-Dec-25 A | 2025-12-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| CON-LEG101-MS-1080 | Finish Baseline Time Schedule | 0 | Completed | 100% | 100% | 100% | 0% | 100% | 100% |  | 2025-12-18 |  | 2025-12-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | No
| Engineering |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 2026-01-19 | 2026-01-19 | 2026-11-07 | 2026-11-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -55
| CON-LEG101-MS-1060 | Finish Submission and Approval for Shop Drawings, Method of Statement, Prequalification and Materials | 0 | Not Started | 0% | 0% | 0% | 0% | 100% | 0% |  | 2026-01-19 |  | 2026-11-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -55 | No
| Procurement |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 2026-01-19 | 2026-01-19 | 2026-11-01 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -49
| CON-LEG101-MS-1100 | Finish PO for Short Lead Item & Long Lead Item | 0 | Not Started | 0% | 0% | 0% | 0% | 100% | 0% |  | 2026-01-19 |  | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -49 | No
| Construction |  | 408 |  |  |  | 0% | 0% | 0% | 0% | 2026-09-17 | 2027-11-18 | 2027-01-18 | 2028-05-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -157
| CON-LEG101-MS-1130 | Completion of Deep infrastructure network | 0 | Not Started | 0% | 0% | 0% | 0% | 0% | 0% |  | 2026-11-18 |  | 2027-01-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | No
| CON-LEG101-MS-1120 | Completion of Roads & Meduim Voltage | 0 | Not Started | 0% | 0% | 0% | 0% | 100% | 0% |  | 2026-09-17 |  | 2027-06-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -106 | No
| CON-LEG101-MS-1140 | Completion of Shallow infrastructure network | 0 | Not Started | 0% | 0% | 0% | 0% | 0% | 0% |  | 2027-03-18 |  | 2027-10-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -42 | No
| CON-LEG101-MS-1150 | Completion all Works | 0 | Not Started | 0% | 0% | 0% | 0% | 0% | 0% |  | 2027-11-18 |  | 2028-05-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -157 | No
| Monitoring and Control Milestone |  | 260 |  |  |  | 0% | 0% | 0% | 0% | 2027-05-04 | 2027-10-18 | 2027-06-20 | 2028-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -153
| Mobilization |  | 112 |  |  |  | 100% | 100% | 0% | 0% | 2025-11-19 | 2025-12-18 | 19-Nov-25 A | 04-Mar-26 A | 0 | 0 | 0 | 0 | 20050 | 20050 | 20050 | 20050
| Engineering |  | 287 |  |  |  | 94.77% | 98.79% | 100% | 99.14% | 2025-11-26 | 2026-01-19 | 01-Dec-25 A | 2026-11-07 | 2601460.39 | 2601460.39 | 2579200.39 | 2579202.39 | 33415 | 33415 | 33009.2 | 33009.2 | -55
| Procurement |  | 502 |  |  |  | 49.95% | 91% | 77.89% | 90.68% | 2025-12-28 | 2027-09-14 | 25-Nov-25 A | 2027-08-21 | 17355662.1 | 13518577.1 | 15737880.1 | 15737880.1 | 82413.81 | 48080.56 | 74996.76 | 74996.78 | 30
| Construction |  | 710 |  |  |  | 35.49% | 72.42% | 51.67% | 76.69% | 2025-12-20 | 2027-10-18 | 20-Nov-25 A | 2028-04-18 | 58147531.04 | 30033459.29 | 44572325.02 | 44572338 | 545268.46 | 246436.59 | 390120.29 | 392633.33 | -153
| Testing & Commissioning |  | 167 |  |  |  | 23.9% | 53.1% | 0% | 62.53% | 2027-08-04 | 2027-10-26 | 15-Jun-26 A | 2028-04-26 | 8677691.2 | 0 | 5426563.31 | 5426563.31 | 20050 | 0 | 10646.5 | 10646.5 | -157
| Project Close-out |  | 145 |  |  |  | 0% | 0% | 0% | 0% | 2027-08-14 | 2027-11-18 | 2027-12-04 | 2028-05-20 | 0 | 0 | 0 | 0 | 13364 | 0 | 0 | 0 | -157

## EV-Chart Data
| Baseline Plan |  |  | Revised / Recovery Plan |  |  | Earned Value |  |  | Gross Paid Value |  |  | Forecast |  |  | Actual/Fcst vs Plan
Month | Monthly | Cum | % | Monthly | Cum | % | Monthly | Cum | % | Monthly | Cum | % | Monthly | C um |  | Month | Cum
2025-11-30 |  | 0 | 0% |  |  |  | 204246.48 | 204246.48 | 0.2354% | 0 | 0 | 0% |  |  |  | 204246.48 | 204246.48 | Actuals thru previous month
2025-12-31 | 945885.87 | 945885.87 | 1.09% |  |  |  | 4365181.22 | 4569427.7 | 5.265% | 0 | 0 | 0% |  |  |  | 3419295.35 | 3623541.83
2026-01-28 | 2527898.36 | 3473784.23 | 4.003% |  |  |  | 7095979.17 | 11665406.87 | 13.44% | 0 | 0 | 0% |  |  |  | 4568080.81 | 8191622.64
2026-02-28 | 2865444.21 | 6339228.44 | 7.305% |  |  |  | 6859828.31 | 18525235.18 | 21.35% | 0 | 0 | 0% |  |  |  | 3994384.1 | 12186006.74
2026-03-31 | 778518.31 | 7117746.75 | 8.202% |  |  |  | 5417836.62 | 23943071.8 | 27.59% | 0 | 0 | 0% |  |  |  | 4639318.31 | 16825325.05 | Forecast current and future months
2026-04-30 | 6018470.75 | 13136217.5 | 15.14% |  |  |  | 9609746.11 | 33552817.91 | 38.66% | 0 | 0 | 0% |  |  |  | 3591275.36 | 20416600.41
2026-05-31 | 5115924.69 | 18252142.19 | 21.03% |  |  |  | 6579364.93 | 40132182.84 | 46.24% | 0 | 0 | 0% |  |  |  | 1463440.24 | 21880040.65
2026-06-30 | 6349563.3 | 24601705.49 | 28.35% |  |  |  | 6399095.81 | 46531278.65 | 53.62% | 0 | 0 | 0% |  |  |  | 49532.51 | 21929573.16
2026-07-31 | 5904651.32 | 30506356.81 | 35.15% |  |  |  | 7824666.75 | 54355945.4 | 62.63% | 0 | 0 | 0% |  |  |  | 1920015.43 | 23849588.59
2026-08-31 | 7367494.98 | 37873851.79 | 43.64% |  |  |  | 8165098.43 | 62521043.83 | 72.04% | 0 | 0 | 0% |  |  |  | 797603.45 | 24647192.04
2026-09-30 | 6675161.8 | 44549013.59 | 51.33% |  |  |  | 3874944.35 | 66395988.18 | 76.51% | 0 | 0 | 0% |  |  |  | -2800217.45 | 21846974.59
2026-10-31 | 2226357.71 | 46775371.3 | 53.9% |  |  |  | 1919980.63 | 68315968.81 | 78.72% |  | 0 | 0% | 381926.64 | 68697895.45 | 79.16% | 75549.56 | 21922524.15
2026-11-30 | 5664986.36 | 52440357.66 | 60.43% | [9 empty] | 803937.18 | 69501832.63 | 80.09%
2026-12-31 | 4709802.41 | 57150160.07 | 65.85% | [9 empty] | 650999.88 | 70152832.51 | 80.84%
2027-01-31 | 2450892.95 | 59601053.02 | 68.68% | [9 empty] | 1419963.84 | 71572796.35 | 82.47%
2027-02-28 | 2606967.71 | 62208020.73 | 71.68% | [9 empty] | 240430.02 | 71813226.37 | 82.75%
2027-03-31 | 3761453.27 | 65969474 | 76.02% | [9 empty] | 1206192.21 | 73019418.58 | 84.14%
2027-04-30 | 2318874.56 | 68288348.56 | 78.69% | [9 empty] | 1005171.07 | 74024589.65 | 85.3%
2027-05-31 | 2398376.07 | 70686724.63 | 81.45% | [9 empty] | 1460265.74 | 75484855.39 | 86.98% |  |  |  | Extended Duration
2027-06-30 | 3208784.16 | 73895508.79 | 85.15% | [9 empty] | 1135063.4 | 76619918.79 | 88.29%
2027-07-31 | 1687613.52 | 75583122.31 | 87.1% | [9 empty] | 1429215.9 | 78049134.69 | 89.94%
2027-08-31 | 5271091.44 | 80854213.75 | 93.17% | [9 empty] | 1091632.2 | 79140766.89 | 91.19%
2027-09-30 | 2475992.45 | 83330206.2 | 96.02% | [9 empty] | 1044925.57 | 80185692.46 | 92.4%
2027-10-31 | 3452138.54 | 86782344.74 | 100% | [9 empty] | 1438294.12 | 81623986.58 | 94.06%
2027-11-30 | [12 empty] | 2453576.34 | 84077562.92 | 96.88% |  |  |  |  | Spreadsheet Field | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01
2027-12-30 | [12 empty] | 1158901.42 | 85236464.34 | 98.22% |  |  |  |  | Cum BL1 Total Cost |  | 806595.32 | 1076993.67 | 1646314.32 | 4103352.07 | 11057031.87 | 26957436.31 | 35047131.01 | 43482279.99 | 49721626.48 | 55541495.19 | 58609252.97 | 59458608.49 | 62416851.82 | 70392954.05 | 70392954.05
2028-01-30 | [12 empty] | 437078.56 | 85673542.9 | 98.72% |  |  |  |  | Cum Actual Total Cost | 531360 | 1562095.14 | 4086192.63 | 6155575.82 | 8202527.2 | 15434172.62 | 25435681.32 | 28628682.18 | 28628682.18 | 28628682.18 | 28628682.18 | 28628682.18 | 28628682.18 | 28628682.18 | 28628682.18 | 28628682.18
2028-02-29 | [12 empty] | 156512.77 | 85830055.67 | 98.9% |  |  |  |  | BL1 Labor Units | 356 | 1721 | 872 | 1877 | 3382 | 4485 | 4819 | 7855 | 6939 | 5176 | 6559 | 5583 | 2552 | 2519 | 3446
2028-03-30 | [12 empty] | 568388.81 | 86398444.48 | 99.56% |  |  |  |  | Actual Labor Units | 2025-04-01: 1172.65; 2025-05-01: 3628.34; 2025-06-01: 1840.31; 2025-07-01: 3196.17; 2025-08-01: 3048.04; 2025-09-01: 3613.71; 2025-10-01: 2936.9; 2025-11-01: 961.48
2028-04-30 | [12 empty] | 383900.26 | 86782344.74 | 100% |  |  |  |  | BL1 Total Cost |  | 806595.32 | 270398.36 | 569320.64 | 2457037.75 | 6953679.8 | 15900404.44 | 8089694.7 | 8435148.98 | 6239346.49 | 5819868.71 | 3067757.77 | 849355.53 | 2958243.33 | 7976102.23
[20 empty] | Actual Total Cost | 2025-04-01: 531360; 2025-05-01: 1030735.14; 2025-06-01: 2524097.48; 2025-07-01: 2069383.2; 2025-08-01: 2046951.38; 2025-09-01: 7231645.42; 2025-10-01: 10001508.7; 2025-11-01: 3193000.86
[20 empty] | Cum BL1 Labor Units | 356 | 2077 | 2949 | 4826 | 8208 | 12693 | 17512 | 25367 | 32306 | 37482 | 44041 | 49624 | 52176 | 54695 | 58141 | 58141
[20 empty] | Cum Actual Labor Units | 1172.65 | 4800.99 | 6641.3 | 9837.47 | 12885.51 | 16499.22 | 19436.12 | 20397.6 | 20397.6 | 20397.6 | 20397.6 | 20397.6 | 20397.6 | 20397.6 | 20397.6 | 20397.6
[20 empty] | Remaining Labor Units | 2025-11-01: 6319.8; 2025-12-01: 7300.2; 2026-01-01: 7381.4; 2026-02-01: 5360; 2026-03-01: 3410; 2026-04-01: 1327; 2026-05-01: 1731; 2026-06-01: 4507; 2026-07-01: 369
[20 empty] | Remaining Total Cost | 2025-11-01: 20117547.23; 2025-12-01: 7464473.47; 2026-01-01: 8885194.98; 2026-02-01: 3858005.19; 2026-03-01: 1683332.28; 2026-04-01: 351955.75; 2026-05-01: 1819272.06; 2026-06-01: 8935913.56; 2026-07-01: 425432
UPDATE ONLY YELLOW PORTION FROM PRIMAVERA EXPORT, IF NEEDED, EXTEND YELLOW PORTION BASED ON SCHEDULE.
0
Formulas:
Month = [Month, row above]+31

## Physical-Chart Data
| Baseline Plan |  |  | Revised / Recovery Plan |  |  | Earned Effort % |  |  | Forecast |  |  | Achieved/Fcst vs Plan
Week | Monthly Effort | Cum Effort | Plan Wt.% | MonthlyEffort | Cum Effort | Plan Wt.% | Monthly Wt. | Cum Wt. | Achieved Wt.% | Monthly Wt. | Cum Wt. | Wt.% | Monthly Wt. | Cum Wt.
2025-11-30 | 5359.95 | 5359.95 | 0.7501% | 5359.95 | 5359.95 | 0.7501% | 11192.02 | 11192.02 | 1.566% |  |  |  | 5832.07 | 5832.07 | Actuals thru previous month
2025-12-31 | 29813.84 | 35173.79 | 4.922% | 29813.84 | 35173.79 | 4.922% | 48070.98 | 59263 | 8.294% |  |  |  | 18257.14 | 24089.21
2026-01-28 | 29643.7 | 64817.49 | 9.071% | 29643.7 | 64817.49 | 9.071% | 51804.67 | 111067.67 | 15.54% |  |  |  | 22160.97 | 46250.18
2026-02-28 | 24392.64 | 89210.13 | 12.48% | 24392.64 | 89210.13 | 12.48% | 42988.56 | 154056.23 | 21.56% |  |  |  | 18595.92 | 64846.1
2026-03-31 | 18781.31 | 107991.44 | 15.11% | 18781.31 | 107991.44 | 15.11% | 41993.23 | 196049.46 | 27.44% |  |  |  | 23211.92 | 88058.02 | Forecast current and future months
2026-04-30 | 29373.61 | 137365.05 | 19.22% | 29373.61 | 137365.05 | 19.22% | 64055.99 | 260105.45 | 36.4% |  |  |  | 34682.38 | 122740.4
2026-05-31 | 24568.1 | 161933.15 | 22.66% | 24568.1 | 161933.15 | 22.66% | 43582.96 | 303688.41 | 42.5% |  |  |  | 19014.86 | 141755.26
2026-06-30 | 33732.43 | 195665.58 | 27.38% | 33732.43 | 195665.58 | 27.38% | 43961.59 | 347650 | 48.65% |  |  |  | 10229.16 | 151984.42
2026-07-31 | 36781.76 | 232447.34 | 32.53% | 36781.76 | 232447.34 | 32.53% | 77155.64 | 424805.64 | 59.45% |  |  |  | 40373.88 | 192358.3
2026-08-31 | 47939.59 | 280386.93 | 39.24% | 47939.59 | 280386.93 | 39.24% | 62683.37 | 487489.01 | 68.22% |  |  |  | 14743.78 | 207102.08 |  |  | Spreadsheet Field | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01
2026-09-30 | 50083.47 | 330470.4 | 46.25% | 50083.47 | 330470.4 | 46.25% | 22015.45 | 509504.46 | 71.3% |  |  |  | -28068.02 | 179034.06 |  |  | Cum BL1 Total Cost |  | 806595.32 | 1076993.67 | 1646314.32 | 4103352.07 | 11057031.87 | 26957436.31 | 35047131.01 | 43482279.99 | 49721626.48 | 55541495.19 | 58609252.97 | 59458608.49 | 62416851.82 | 70392954.05 | 70392954.05
2026-10-31 | 31644.5 | 362114.9 | 50.68% | 31644.5 | 362114.9 | 50.68% | 19318.29 | 528822.75 | 74.01% | 7295.11 | 536117.86 | 75.03% | -5031.1 | 174002.96 |  |  | Cum Actual Total Cost | 531360 | 1562095.14 | 4086192.63 | 6155575.82 | 8206784.46 | 15457052.13 | 25654616.47 | 27792679.25 | 27792679.25 | 27792679.25 | 27792679.25 | 27792679.25 | 27792679.25 | 27792679.25 | 27792679.25 | 27792679.25
2026-11-30 | 39701.82 | 401816.72 | 56.23% | 39701.82 | 401816.72 | 56.23% |  |  |  | 7399.83 | 543517.69 | 76.06% |  |  |  |  | BL1 Labor Units | 356 | 1721 | 872 | 1877 | 3382 | 4485 | 4819 | 7855 | 6939 | 5176 | 6559 | 5583 | 2552 | 2519 | 3446
2026-12-31 | 46326.66 | 448143.38 | 62.72% | 46326.66 | 448143.38 | 62.72% |  |  |  | 7325.68 | 550843.37 | 77.09% |  |  |  |  | Actual Labor Units | 2025-04-01: 1172.65; 2025-05-01: 3628.34; 2025-06-01: 1840.31; 2025-07-01: 3196.17; 2025-08-01: 3049.07; 2025-09-01: 3618.81; 2025-10-01: 3018.25; 2025-11-01: 672.41
2027-01-31 | 41440.12 | 489583.5 | 68.52% | 41440.12 | 489583.5 | 68.52% |  |  |  | 7608.29 | 558451.66 | 78.15% |  |  |  |  | BL1 Total Cost |  | 806595.32 | 270398.36 | 569320.64 | 2457037.75 | 6953679.8 | 15900404.44 | 8089694.7 | 8435148.98 | 6239346.49 | 5819868.71 | 3067757.77 | 849355.53 | 2958243.33 | 7976102.23
2027-02-28 | 30567.53 | 520151.03 | 72.79% | 30567.53 | 520151.03 | 72.79% |  |  |  | 7456.81 | 565908.47 | 79.2% |  |  |  |  | Actual Total Cost | 2025-04-01: 531360; 2025-05-01: 1030735.14; 2025-06-01: 2524097.48; 2025-07-01: 2069383.2; 2025-08-01: 2051208.64; 2025-09-01: 7250267.67; 2025-10-01: 10197564.33; 2025-11-01: 2138062.78
2027-03-31 | 34520.87 | 554671.9 | 77.62% | 34520.87 | 554671.9 | 77.62% |  |  |  | 11660.64 | 577569.11 | 80.83% |  |  |  |  | Cum BL1 Labor Units | 356 | 2077 | 2949 | 4826 | 8208 | 12693 | 17512 | 25367 | 32306 | 37482 | 44041 | 49624 | 52176 | 54695 | 58141 | 58141
2027-04-30 | 21773.44 | 576445.34 | 80.67% | 21773.44 | 576445.34 | 80.67% |  |  |  | 7775.23 | 585344.34 | 81.92% |  |  |  |  | Cum Actual Labor Units | 1172.65 | 4800.99 | 6641.3 | 9837.47 | 12886.54 | 16505.35 | 19523.59 | 20196 | 20196 | 20196 | 20196 | 20196 | 20196 | 20196 | 20196 | 20196
2027-05-31 | 30753.45 | 607198.79 | 84.98% | 30753.45 | 607198.79 | 84.98% |  |  |  | 12741.9 | 598086.24 | 83.7% |  |  |  | Extended Duration | Remaining Labor Units | 2025-11-01: 7196.2; 2025-12-01: 7175.2; 2026-01-01: 7414.6; 2026-02-01: 5123; 2026-03-01: 3302; 2026-04-01: 1098; 2026-05-01: 2019; 2026-06-01: 4579
2027-06-30 | 28626.94 | 635825.73 | 88.98% | 28626.94 | 635825.73 | 88.98% |  |  |  | 15748.49 | 613834.73 | 85.9% |  |  |  |  | Remaining Total Cost | 2025-11-01: 21185773.51; 2025-12-01: 8002967.62; 2026-01-01: 8606824.19; 2026-02-01: 3474097.51; 2026-03-01: 1572072.15; 2026-04-01: 273706.67; 2026-05-01: 2370642.24; 2026-06-01: 8801345.56
2027-07-31 | 17130.27 | 652956 | 91.38% | 17130.27 | 652956 | 91.38% |  |  |  | 11432.82 | 625267.55 | 87.5%
2027-08-31 | 17971.29 | 670927.29 | 93.89% | 17971.29 | 670927.29 | 93.89% |  |  |  | 10852.09 | 636119.64 | 89.02%
2027-09-30 | 21052.53 | 691979.82 | 96.84% | 21052.53 | 691979.82 | 96.84% |  |  |  | 7628.93 | 643748.57 | 90.09%
2027-10-31 | 16945.56 | 708925.38 | 99.21% | 16945.56 | 708925.38 | 99.21% |  |  |  | 14085.45 | 657834.02 | 92.06%
2027-11-30 | 5635.87 | 714561.25 | 100% | 5635.87 | 714561.25 | 100% |  |  |  | 9976.84 | 667810.86 | 93.46%
2027-12-30 | [9 empty] | 20381.37 | 688192.23 | 96.31%
2028-01-30 | [9 empty] | 14328.06 | 702520.29 | 98.31%
2028-02-29 | [9 empty] | 3785.45 | 706305.74 | 98.84%
2028-03-30 | [9 empty] | 2961.8 | 709267.54 | 99.26%
2028-04-30 | [9 empty] | 5293.71 | 714561.25 | 100%
UPDATE ONLY YELLOW PORTION FROM PRIMAVERA EXPORT, IF NEEDED, EXTEND YELLOW PORTION BASED ON SCHEDULE.
0
Formulas:
Week = [Week, row above]+31

## LOOK AHEAD
مستهدف الربع
# | القطاع | المبادرة | Project ID | اسم المشروع | مدير المشروع | المقاول | بداية المشروع | نهاية المشروع التعاقدية | مدة المشروع (أشهر) | نهاية المشروع المتوقعة/ الالتزام | قيمة المشروع | المخطط /الفعلي | Mobilization المخطط | Mobilization المنفذ | Procurement (Long Lead Items) توريد المواد طويلة الأجل (المخطط) | Procurement (Long Lead Items) توريد المواد طويلة الأجل (المنفذ) | Civil Work الأعمال المدنيه (المخطط) | Civil Work الأعمال المدنيه (المنفذ) | Mechnical Work أعمال الميكانيكا (المخطط) | Mechnical Work أعمال الميكانيكا (المنفذ) | Mechnical Work أعمال الكهرباء (المخطط) | Mechnical Work أعمال الكهرباء (المنفذ) | تأثير التأخير (إن وجد) على المبادرات في الربع | نسبة الانجاز المستهدفة بنهاية الربع | نسبة الانجاز المحققة بنهاية الربع | مجموع المبالغ المفوترة المستهدفة بنهاية الربع | مجموع المبالغ المفوترة المحققة بنهاية الربع | نهاية المشروع المتوقعة
1 | الغربي | - | JDH1-02-003 | INFRASTRUCTURE DEVELOPMENT FOR INDUSTRIAL CITY 1 IN JEDDAH | م. رضا المنشاوي | Al Enjaz Company for Trading and Contracting | 2025-11-19 | 2027-11-18 | 24 | 2026-11-30 | 86782344.73 | المخطط=53.18% الفعلى =78.72% | 100% | 100% | 1. توريد مواسير شبكة السيول 100% 2. توريد مواسير شبكة الصرف الصحي 100% 3. توريد مواسير شبكة مياه الشرب 100% 4. توريد مواسير شبكة الري 100% 5. توريد مناهل السيول والصرف الصحي 100% 6. توريد مصايد الامطار 100% 7. توريد كابلات الجهد المنخفض 100% توريد أعمدة الانارة والكشافات 100 % 9. توريد مناهل الاتصالات 100% 10. توريد مواد شبكة الكاميرات والمراقبة 30% 11- توريد كابلات الجهد المتوسط 50% 12- توريد مواد الكوبري 100% 13. توريد حديد السور 100% | 1. جاري توريد مواسير شبكة السيول حيث تم توريد100 % 2- تم توريد مناهل السيول حيث تم وصول100% 3- تم توريد مواسير الصرف الصحي بنسبة 100% 4- تم توريد مواسير المياه حوالي 100% 5- تم توريد مواسير مياه شبكة الري بنسبة 100% 6- تم توريد مناهل الصرف الصحي بنسبة 100% 7- تم توريد مصايد السيول بنسبة 100% 8 - تم توريد محابس القفل والفراشة لشبكة المياه والري بنسبة 100% 9- توريد طفايات الحريق بنسبة100% 10 - تم توريد كابلات الجهد المنخفض 100% 11 - جاري توريد مناهل الاتصالات والكهرباء 12 - توريد حديد السور بنسبة 100% 13 - توريد اعمدة الانارة والكشافات بنسبة 100% | 1. انهاء اعمال إزالة المباني والاسوار 2. الانتهاء من اعمال قطع الاراضى 100% 3. الانتهاء من اعمال ردم الأراضي 100% 4. اعمال قطع الطرق 100% 5. اعمال ردم الطرق 100% 6. اعمال الحفر للسور 100% 7. اعمال خرسانات الاساسات للسور 80% 8. اعمال حفر الكوبري 100% 9. أعمال الخوازيق للكوبري 100% اعمال الانتهاء من خرسانات الكوبري 100% تركيب حديد للسور بنسبة 70% | 1. انهاء اعمال إزالة المباني والاسوار 100% 2. الانتهاء من اعمال قطع الاراضى 100% 3. الانتهاء من اعمال ردم الأراضي 99.8% 4. اعمال قطع الطرق 100% 5. اعمال ردم الطرق 100% 6. اعمال الحفر للسور100% 7. اعمال خرسانات الاساسات للسور 100% 8- اعمال Subgrade 100% 9- اعمال حفر وصب الخوازيق للكوبري بنسبة 100% 10- تم صب 100% من Abutment of Bridge - اعمال صب واعمال تسليجح لزوم جردرات الكوبري 100% - تركيب حديد السور بنسبة 83% - جاري اعمال الاسفلت الطبقة الاولى 100% - جاري اعمال البردورات 89% - اعمال الانترلوك بنسبة 79.82% - أعمال الاسفلت الطبقة السطحية بنسبة 43% | 1- تنفيذ شبكة السيول بنسبة 70% 2- تنفيذ شبكة الصرف الصحي بنسبة70% اعمال تنفيذ شبكة المياه 60% اعمال تنفيذ شبكة الري بنسبة 70% | 1- تم حفر وتركيب واختبار مواسير شبكة السيول56244 م.ط بنسبة 100% 2- انتهاء تركيب اعمال مواسير شبكة الصرف الصحي بطول 6244 م.ط 3. انتهاء اعمال حفر واعمال لحام مواسير شبكة مياه الشرب بطول 12075 م.ط 4- جاري اعمال حفر واعمال لحام مواسير شبكة الري بطول 8633 م.ط 5- تم الانتهاء من تركيب طفايات الحريق 100% 6- تم تركيب عدد 156 محبس لشبكة المياه والري 7- جاري اعمال والتشطيب لغرف شبكة المياه والري | 1- اعمال دكتات الكهرباء والاتصالات بنسبة 75% 2- اعمال مناهل الاتصالات بنسبة 40% اعمال شبكة الجهد المتوسط بنسبة 25% اعمال قواعد أعمدة الانارة 100% | 1- اعمال الدكتات بنسبة 100% 2- جاري اعمال حفر مناهل الاتصالات80% 3- تم اعمال صب قواعد أعمدة الانارة بنسبة100% 4- جاري تركيب أعمدة الانارة بعدد 370 عمود 5 - اعمال حفر وتمديد كابلات الجهد المنخفض بطول 13900 م 6- تركيب عدد 7 أعمدة لنظام CCTV | ضرورة انهاء اتفاقية شبكة الجهد المتوسط من قبل مدن مع شركة الكهرباء وذلك لتأخر بدء التوريد والعمل بالموقع | 75% | 78.72% | 65086758.75 | 44851849.32 | 2026-11-30

## Schedule
Primavera P6 Schedule Status | [9 empty] | Data Date | 2026-10-20
Project Activities Overview
Schedule Statistics |  |  |  |  | Active Schedule Activities
Total Act. | Not Started | In Progress | Completed | % | Active | Ahead | On | Behind | Flag
1905 | 423 | 204 | 1278 | 67.09% | 204 | 91 | 0 | 113 | -22
Critical Path Activities |  |  | Free Float Management (Total) |  |  |  | Failed Start Activities
|  |  | Greater Than 14 Days |  | Less Than 14 Days
Last Week | This Week | Diff | Last Week | This Week | Last Week | This Week | Last Week | This Week | Flag
460 | 457 | 3 | 71 | 68 | 1834 | 1837 | 107 | 113 | -6

## Manpower
Head-Count ( Non Manual)
MONTHS | 2025-11-30 | 2025-12-31 | 2026-01-28 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | [5 empty] | non direct
Plan - Monthly | 20 | 20 | 21 | 21 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 21 | 21 | 21 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 14
Planned - Cumulative | 20 | 40 | 61 | 82 | 104 | 126 | 148 | 170 | 192 | 214 | 236 | 258 | 279 | 300 | 321 | 341 | 361 | 381 | 401 | 421 | 441 | 461 | 481 | 501 | 515
Actual - Monthly | 30 | 40 | 54 | 54 | 52 | 52 | 52 | 52 | 52 | 52 | 47 | 48 | [18 empty] | daily report
Actual Cumulative | 30 | 70 | 124 | 178 | 230 | 282 | 334 | 386 | 438 | 490 | 537 | 585
Forecast - Monthly | [12 empty] | 40 | 35 | 21 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 14
Saudi Monthly - Actual
Head-Count (Manual) | [30 empty] | direct
MONTHS | 2025-11-30 | 2025-12-31 | 2026-01-28 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30
Plan - Monthly | 22.6819 | 102.0545 | 87.9966 | 117.2724 | 90.2948 | 139.4962 | 114.857 | 159.5615 | 177.3492 | 228.7163 | 239.4798 | 148.2502 | 186.5104 | 216.8592 | 196.8675 | 144.4988 | 168.551 | 109.7532 | 146.7325 | 136.7545 | 82.8618 | 52.5133 | 64.7185 | 17.5146 | 17.4279
Planned - Cumulative | 22.6819 | 124.7364 | 212.733 | 330.0053 | 420.3001 | 559.7962 | 674.6532 | 834.2147 | 1011.5639 | 1240.2803 | 1479.76 | 1628.0102 | 1814.5206 | 2031.3799 | 2228.2473 | 2372.7461 | 2541.2971 | 2651.0502 | 2797.7827 | 2934.5372 | 3017.399 | 3069.9123 | 3134.6308 | 3152.1454 | 3169.5733
Actual - Monthly | 35 | 93 | 148 | 140 | 134 | 155 | 192 | 196 | 194 | 196 | 135 | 130 | [18 empty] | daily report | 31
Actual Cumulative | 35 | 128 | 276 | 416 | 550 | 705 | 897 | 1093 | 1287 | 1483 | 1618 | 1748
Forecast - Monthly | [12 empty] | 186.5104 | 216.8592 | 196.8675 | 144.4988 | 168.551 | 109.7532 | 146.7325 | 136.7545 | 82.8618 | 52.5133 | 64.7185 | 17.5146 | 17.4279
Saudi - Actual
Head-Count (Non-Manual) | [28 empty] | Month | 2026-10-31 | 2026-11-30
Planned | Actual |  | Variance |  | Forecast Next Month |  | Saudi Staff
22 | 48 |  | 26 |  | 40 |  | 6
Head-Count (Manual) | [10 empty] | Man Power by Trade
Planned | Actual |  | Variance |  | Forecast Next Month |  | Saudi Staff |  |  |  | Key Trade |  | Labor |  | Skilled Labor |  | Driver / Operator |  | Carpenter |  | Steel Fixer |  | Mason |  | Plumber | Electrician | Others | Total
148 | 130 |  | -18 |  | 187 |  | 0 |  |  |  | Plan |  | 40 |  | 26 |  | 60 |  | 5 |  | 5 |  | 2 |  | 8 | 2 | 0 | 148
[11 empty] | Actual |  | 17 |  | 30 |  | 48 |  | 6 |  | 9 |  | 0 |  | 7 | 13 | 0 | 130
Equipment
MONTHS | 2025-11-30 | 2025-12-31 | 2026-01-28 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30
Plan - Monthly | 0 | 3.6264 | 11.8681 | 18.9495 | 14.194 | 29.7984 | 29.5907 | 53.2138 | 55.9268 | 77.1449 | 89.0682 | 59.69 | 55.8207 | 58.884 | 55.6918 | 43.8726 | 46.0436 | 19.9484 | 25.5747 | 19.3758 | 12.9544 | 17.6049 | 22.7611 | 4.853
Planned - Cumulative | 0 | 3.6264 | 15.4945 | 34.444 | 48.638 | 78.4363 | 108.0271 | 161.2408 | 217.1676 | 294.3125 | 383.3807 | 443.0708 | 498.8914 | 557.7755 | 613.4673 | 657.3399 | 703.3835 | 723.3319 | 748.9066 | 768.2824 | 781.2368 | 798.8417 | 821.6028 | 826.4558
Actual - Monthly | 20 | 52 | 83 | 75 | 69 | 69 | 94 | 98 | 96 | 98 | 54 | 48
Actual Cumulative | 20 | 72 | 155 | 230 | 299 | 368 | 462 | 560 | 564 | 564 | 564 | 564
Forecast - Monthly | [12 empty] | 55.8207 | 58.884 | 55.6918 | 43.8726 | 46.0436 | 19.9484 | 25.5747 | 19.3758 | 12.9544 | 17.6049 | 22.7611 | 4.853
Equipment Count
Planned | Actual |  | Idle |  | Variance |  | Forecast Next Month
60 | 48 |  | 0 |  | -12 |  | 56
Type | Excavator | Loader | Bulldozer | Water Tanker | Grader | Truck | Road Roller | Asphalt Paver | Crane | Bobcat | Aggregate paver | Compactor | Other | Total
Plan | 3 | 3 | 2 | 3 | 4 | 12 | 3 | 0 | 2 | 0 | 0 | 0 | 28 | 60
Actual | 4 | 3 | 1 | 6 | 1 | 9 | 3 | 2 | 1 | 5 | 0 | 3 | 10 | 48
Idle | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Conclusion
مشروع تطوير البنية التحتية بالمدينة الصناعية الاولى بجدة JDH1-02-003
معلومات المشروع |  |  |  |  | نطاق المشروع |  |  |  |  | موقع المشروع
المقاول | شركة الانجاز للتجارة والمقاولات | الاستشاري | شركة ايجيس السعودية للاستشارات |  | البند | الكمية الكلية | الكمية المنفذة | الكمية المتبقية | نسبة المنفذ
تاريخ استلام الموقع | 2025-11-19 | مدة التنفيذ | 24 شهرًا ميلاديًا |  | اعمال الازالة | 100% | 100% | 0% | 100%
بداية العقد | من تاريخ استلام الموقع | قيمة العقد (شامل ضريبة القيمة المضافة) | 86782345 | #REF! | الطرق و المواقف | 100% | 82.28% | 17.72% | 82.28%
نسبة الإنجاز المخطط له | 53.18% | نسبة الإنجاز الفعلي | 78.72% |  | الاعمال الكهربائية | 100% | 56.04% | 43.96% | 56.04%
[5 empty] | اعمال شبكة مياه الشرب | 100% | 94.72% | 5.28% | 94.72%
[5 empty] | اعمال شبكة مياه الري | 100% | 95.45% | 4.55% | 95.45%
ملخص جدول الكميات |  |  |  |  | اعمال شبكة السيول | 100% | 97.78% | 2.22% | 97.78%
مكونات المشروع |  | التكلفة (غير شامل ضريبة القيمة المضافة) | النسبة الاجمالية |  | اعمال شبكة الصرف الصحي | 100% | 97.04% | 2.96% | 97.04% |  | 20865877 | 20423520.4076
الطرق و المواقف |  | 21303539.3005 | 24.55% |  | اعمال الاسوار والبوابات | 100% | 65.85% | 34.15% | 65.85% | تقدم أعمال layout | 10508920 | 10286130.896
الاعمال الكهربائية |  | 15060435.99 | 17.35% |  | اعمال الكوبري | 100% | 72.83% | 27.17% | 72.83% |  | 23728460 | 23225416.648
اعمال شبكة مياه الشرب |  | 8476992.3706 | 9.768% |  | اعمال الاند سكيب | 100% | 0% | 100% | 0% |  | 7970089 | 7801123.1132
اعمال شبكة مياه الري |  | 7038125.4165 | 8.11% |  | ملخص التوريدات | [5 empty] | 8842925 | 8655454.99
اعمال شبكة السيول |  | 14055611.9367 | 16.2% |  | البند | الكمية الكلية | الكمية المورده | الكمية المتبقية | نسبة التوريد
اعمال شبكة الصرف الصحي |  | 6688000.6374 | 7.707% |  | Steel Reinforcement | 126 | 126 | 0 | 100%
اعمال الاسوار والبوابات |  | 7099976.21 | 8.181% |  | Precast Concrete Kerb | 59990 | 59990 | 0 | 100%
اعمال الكوبري |  | 3909548.3174 | 4.505% |  | Interlocking Block Pavers | 57905 | 57905 | 0 | 100% |  |  |  | 5041
اعمال الاند سكيب |  | 3150114.8119 | 3.63% |  | Metal Fence | 2295 | 2295 | 0 | 100% |  |  |  | 12075.28
الإجمالي للمشروع |  | 86782344.991 | 100% |  | GRP Pipes for Sewer network | 6244 | 6244 | 0 | 100% |  |  |  | 8502
معالم البرنامج الزمني |  |  |  |  | Fiberglass Manholes for Sewer network | 122 | 122 | 0 | 100% |  |  |  | 5775.1
البند |  | التاريخ حسب الجدول الزمني | ملاحظة |  | GRP Pipes for Storm network | 5650 | 5650 | 0 | 100%
نهاية الشروع |  | 2027-11-18 |  |  | Inlet Manholes for Storm network | 130 | 130 | 0 | 100%
بداية المشروع |  | 2025-11-19 | تم البدء |  | Concrete chambers | 189 | 189 | 0 | 100%
تجهيزات الموقع. |  | 2025-12-18 | تم الانتهاء |  | HDPE Pipe (PN 16) for Ptable Water | 12075 | 12075 | 0 | 100%
تقديم خطة العمل والبرنامج الزمني |  | 2025-12-18 | تم الانتهاء |  | HDPE Pipe (PN 16) for TSE | 8722 | 8722 | 0 | 100%
تقديم واعتماد المخططات والمواد |  | 2026-01-19 | جاري التنفيذ |  | التحديات والعوائق
الانتهاء من اصدار جميع أوامر الشراء |  | 2026-01-19 | جاري التنفيذ |  | في انتظار تحديث اتفاقية الكهرباء بين مدن والشركة السعودية للكهرباء بخصوص شبكة الجهد المتوسط
الانتهاء من نطاق أعمال الطرق والجهد المتوسط |  | 2026-09-17 | جاري التنفيذ
الانتهاء من نطاق أعمال الشبكات العميقة |  | 2026-11-18 | جاري التنفيذ
الانتهاء من نطاق جميع أعمال الشبكات |  | 2027-03-18 | جاري التنفيذ
الانتهاء من كامل الأعمال |  | 2027-11-18 | لم يبدأ
موقع المشروع

## Testing
Testing and Commissioning
Item | Planned Start Date | Planned Finish Date | Forecast Start Date | Forecast Finish Date | Actual Start Date | Actual Finish Date | % Completed | Open Comments | Closed Comments
Test for Irrigation and Landscape | 2027-10-19 | 2027-10-26 | 2028-02-24 | 2028-03-02
Test for Earthing System | 2027-10-20 | 2027-10-26 | 2027-12-15 | 2027-12-22 | 2026-08-01 |  | 30%
Test for CCTV feeding system and GSM | 2027-10-13 | 2027-10-19 | 2027-12-08 | 2027-12-15 | 2026-08-01 |  | 35%
Test for Telecommunications Work | 2027-10-06 | 2027-10-12 | 2027-12-01 | 2027-12-08 | 2026-08-01 |  | 30%
Test for Road Lighting | 2027-09-29 | 2027-10-05 | 2027-11-24 | 2027-12-01 | 2026-08-01 |  | 30%
Test for Electrical Network | 2027-09-11 | 2027-09-19 | 2027-11-10 | 2027-11-20 | 2026-08-01 |  | 30%
Test for Road Works | 2027-08-04 | 2027-08-12 | 2027-10-16 | 2027-10-24 | 2026-08-01 |  | 70%
Test for Fence & Gate | 2027-10-19 | 2027-10-25 | 15-Jun-26 A | 2027-11-04 | 2026-06-15 |  | 60%
Test for Bridge Work | 2027-09-01 | 2027-09-09 | 15-Jun-26 A | 2027-11-10 | 2026-06-15 |  | 70%
Test for Stormwater Utilities | 2027-08-23 | 2027-08-31 | 15-Jun-26 A | 2027-11-04 | 2026-06-15 |  | 70%
Test for Sanitary Sewerage | 2027-08-14 | 2027-08-22 | 15-Jun-26 A | 2027-10-30 | 2026-06-15 |  | 75%
Test for TSE Network | 2027-09-20 | 2027-09-28 | 15-Jun-26 A | 2027-11-24 | 2026-06-15 |  | 75%
Test for Public Water Utility Distribution | 2027-08-14 | 2027-08-22 | 15-Jun-26 A | 2027-10-30 | 2026-06-15 |  | 75%
Activity ID | Activity Name | Original Duration | Activity Status | Activity % Complete | Physical % Complete | Duration % Complete | Schedule % Complete | Units % Complete | Performance % Complete | BL Project Start | BL Project Finish | Start | Finish | Budgeted Total Cost | Planned Value Cost | Earned Value Cost | Actual Total Cost | Budgeted Labor Units | Planned Value Labor Units | Earned Value Labor Units | Actual Labor Units | Total Float | Auto Compute Actuals
CON-LEG101-TC-1090 | Test for Irrigation and Landscape | 7 | Not Started | 0% | 0 | 0 | 0 | 0 | 0% | 2027-10-19 | 2027-10-26 | 2028-02-24 | 2028-03-02 | 305575 | 0 | 0 | 0 | 1570 | 0 | 0 | 0 | -110 | No
CON-LEG101-TC-1120 | Test for Earthing System | 6 | Not Started | 0% | 0 | 0 | 0 | 0 | 0% | 2027-10-20 | 2027-10-26 | 2027-12-15 | 2027-12-22 | 16600 | 0 | 0 | 0 | 1570 | 0 | 0 | 0 | -49 | No
CON-LEG101-TC-1070 | Test for CCTV feeding system and GSM | 6 | Not Started | 0% | 0 | 0 | 0 | 0 | 0% | 2027-10-13 | 2027-10-19 | 2027-12-08 | 2027-12-15 | 249750 | 0 | 0 | 0 | 1570 | 0 | 0 | 0 | -49 | No
CON-LEG101-TC-1000 | Test for Telecommunications Work | 6 | Not Started | 0% | 0 | 0 | 0 | 0 | 0% | 2027-10-06 | 2027-10-12 | 2027-12-01 | 2027-12-08 | 341181 | 0 | 0 | 0 | 1210 | 0 | 0 | 0 | -49 | No
CON-LEG101-TC-1100 | Test for Road Lighting | 6 | Not Started | 0% | 0 | 0 | 0 | 0 | 0% | 2027-09-29 | 2027-10-05 | 2027-11-24 | 2027-12-01 | 477615 | 0 | 0 | 0 | 1570 | 0 | 0 | 0 | -49 | No
CON-LEG101-TC-1010 | Test for Electrical Network | 8 | Not Started | 0% | 0 | 0 | 0 | 0 | 0% | 2027-09-11 | 2027-09-19 | 2027-11-10 | 2027-11-20 | 418189 | 0 | 0 | 0 | 1570 | 0 | 0 | 0 | -49 | No
CON-LEG101-TC-1110 | Test for Road Works | 8 | Not Started | 0% | 0 | 0 | 0 | 0 | 0% | 2027-08-04 | 2027-08-12 | 2027-10-16 | 2027-10-24 | 2658716.5 | 0 | 0 | 0 | 1570 | 0 | 0 | 0 | -50 | No
CON-LEG101-TC-1080 | Test for Fence & Gate | 6 | In Progress | 40% | 0.4 | 0.4 | 0 | 0.4 | 40% | 2027-10-19 | 2027-10-25 | 15-Jun-26 A | 2027-11-04 | 1179417 | 0 | 471766.8 | 471766.8 | 1570 | 0 | 628 | 628 | -9 | No
CON-LEG101-TC-1060 | Test for Bridge Work | 8 | In Progress | 40% | 0.4 | 0.4 | 0 | 0.4 | 40% | 2027-09-01 | 2027-09-09 | 15-Jun-26 A | 2027-11-10 | 345044.7 | 0 | 138017.88 | 138017.88 | 1570 | 0 | 628 | 628 | -49 | No
CON-LEG101-TC-1050 | Test for Stormwater Utilities | 8 | In Progress | 40% | 0.4 | 0.4 | 0 | 0.4 | 40% | 2027-08-23 | 2027-08-31 | 15-Jun-26 A | 2027-11-04 | 1041566 | 0 | 416626.4 | 416626.4 | 1570 | 0 | 628 | 628 | -49 | No
CON-LEG101-TC-1040 | Test for Sanitary Sewerage | 8 | In Progress | 40% | 0.4 | 0.4 | 0 | 0.4 | 40% | 2027-08-14 | 2027-08-22 | 15-Jun-26 A | 2027-10-30 | 568550 | 0 | 227420 | 227420 | 1570 | 0 | 628 | 628 | -49 | No
CON-LEG101-TC-1030 | Test for TSE Network | 7 | In Progress | 40% | 0.4 | 0.4 | 0 | 0.4 | 40% | 2027-09-20 | 2027-09-28 | 15-Jun-26 A | 2027-11-24 | 581275 | 0 | 232510 | 232510 | 1570 | 0 | 628 | 628 | -49 | No
CON-LEG101-TC-1020 | Test for Public Water Utility Distribution | 8 | In Progress | 40% | 0.4 | 0.4 | 0 | 0.4 | 40% | 2027-08-14 | 2027-08-22 | 15-Jun-26 A | 2027-10-30 | 494212 | 0 | 197684.8 | 197684.8 | 1570 | 0 | 628 | 628 | -49 | No

## Codes
Status List
| Approved |  | Y
| Pending |  | N | [5 empty] | (Manhours)
| Potential | [7 empty] | (Mandays)
| Phase | Stage |  | Stage |  | Status |  | Score
[8 empty] | Low | Contractor | Active
| Launch | LOA |  | LOA |  | Active |  | Medium | CM | Expired
| Launch | Kick-off Meeting |  | Kick-off Meeting |  | On Hold |  | High | PgM | Occurred
| Launch | Site Handover |  |  |  | Terminated |  |  | Modon | Pending
| Launch | Mobilization |  | Mobilization | Initial staff and equipment in place, ready to start production | Terminated, Closed |  |  | Other
| Execution | Construction |  | Execution | Tender Documents Issued | Substantial Complete | Initial Handover done at site
| Execution | T&C |  |  | Responses to the OCS completed | Complete | Initial Handover Signed
| Execution | Initial Handover |  | Closeout | Design close-out process complete | Closed | Final Handover done at Site
Warranty Period
Final Handover
Project Status Score
Elements |  |  | Max | Score | Planned | Actual | Remarks
SPI (Physical Effort) |  |  | 100% | 154.5% | No Entry Required
SPI (Cost) |  |  | 100% | 148% | No Entry Required
On Schedule -Active |  |  | 100% | 44.61% | No Entry Required |  |  |  | 0.6
Manpower Availability |  |  | 100% | 87.84% | No Entry Required
Major Equipment Availability |  |  | 100% | 47.62% | No Entry Required
Billing % Compared to Planned |  |  | 100% | 107.1% | No Entry Required
Safety Score |  |  | 100% | #REF! | No Entry Required
Quality Score |  |  | 100% | #REF! | No Entry Required

## Kutools_Chart (hidden)
Pointer | Scale
#REF! | #REF!
1.5
#REF! | #REF!
Intermediate data of the speedometer chart (Please do not remove or modify the data, otherwise, error will occur to the speedometer chart)
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Current value: | #REF!
Pointer | Scale
#REF! | #REF!
1.5
#REF! | #REF!
Intermediate data of the speedometer chart (Please do not remove or modify the data, otherwise, error will occur to the speedometer chart)
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Current value: | #REF!
#REF! | #REF!
Pointer | Scale
#REF! | #REF!
1.5
#REF! | #REF!
Intermediate data of the speedometer chart (Please do not remove or modify the data, otherwise, error will occur to the speedometer chart)
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Current value: | #REF!