## Sheet1
Failed Start List
Project: LAND DEVELOPMENT OF JEDDAH OASIS
| 2026-10-06 | JHD4-02-007 | AL-ENJAZ TRADINGND CONTRACTING COMPANY
# | Activity ID | Activity Name | BL Project Start | Start | Activity Count | Remarks
1 | Total |  | 2026-03-23 | 2026-10-06 | 4 | Not required
2 | JDH4-02-007-MS-1050 | Completion of Earthworks & Site Grading For Plots |  |  | 1 | Not required
3 | JDH4-02-007-MS-1070 | Completion of Road Works |  |  | 1 | Not required
4 | JDH4-02-007-CN-2110 | Tack Coat (RC2) [Road 01 ] | 2026-09-24 | 2026-10-07 | 1 | Not required
5 | JDH4-02-007-CN-2160 | Bituminous concrete wearing course [Road 01 ] | 2026-10-06 | 2026-10-19 | 1 | Not required

## Sheet2 (hidden)
Activity ID | Activity Name | BL Project Start | Start | Activity Count
Total |  | 2026-02-03 | 2026-03-11 | 57
JDH4-02-007-CN-1080 | Removal of the existing asphalt layers (up to base course layer) [Demolition Works ] | 2026-02-09 | 2026-03-11 | 1
JDH4-02-007-CN-1590 | Pipe with diameter 250 mm pipe [Demolition Works ] | 2026-02-03 | 2026-03-11 | 1
JDH4-02-007-CN-1720 | Road excavation [Road 01 ] | 2026-02-03 | 2026-03-11 | 1
JDH4-02-007-PR-1180 | PO for Earthing System | 2026-02-25 | 2026-03-11 | 1
JDH4-02-007-PR-1240 | PO for Valves / Chambers | 2026-02-21 | 2026-03-11 | 1
JDH4-02-007-PR-1270 | PO for Valves / Chambers | 2026-02-15 | 2026-03-11 | 1
JDH4-02-007-PR-1350 | PO for Water Proofing | 2026-02-17 | 2026-03-11 | 1
JDH4-02-007-PR-1380 | PO for Aggregate Base Course | 2026-02-21 | 2026-03-11 | 1
JDH4-02-007-PR-1900 | PO for Risers | 2026-02-17 | 2026-03-11 | 1
JDH4-02-007-MA-1390 | Material Approval for Unit Sub Station By SEC | 2026-02-16 | 2026-03-11 | 1
JDH4-02-007-MA-1410 | Material Approval for Ring main Unit (RMU) By SEC | 2026-02-18 | 2026-03-11 | 1
JDH4-02-007-MA-1520 | Material Approval for Lighting panels/Feeder Pillers | 2026-02-28 | 2026-03-11 | 1
JDH4-02-007-MA-1870 | Material Approval for Main Distribution Board/MCC Panels | 2026-02-25 | 2026-03-11 | 1
JDH4-02-007-MA-1890 | Material Approval for Final Panel Boards | 2026-02-19 | 2026-03-11 | 1
JDH4-02-007-MA-2010 | Material Approval for Power Factor correction Capacitor Bank | 2026-02-19 | 2026-03-11 | 1
JDH4-02-007-PR-2290 | PO for Pipes | 2026-02-03 | 2026-03-11 | 1
JDH4-02-007-PR-2440 | PO for Fire Hydrant | 2026-02-21 | 2026-03-11 | 1
JDH4-02-007-PR-2780 | PO for Wiring Devices | 2026-03-02 | 2026-03-11 | 1
JDH4-02-007-PR-2790 | PO for Raceways for Electrical Systems | 2026-03-03 | 2026-03-11 | 1
JDH4-02-007-PR-3050 | PO for Process Control Wiring | 2026-02-26 | 2026-03-11 | 1
JDH4-02-007-PR-3120 | PO for Programmable Logic Controllers | 2026-03-09 | 2026-03-11 | 1
JDH4-02-007-PR-2026 | Material Fabrication for Pumps - Stage 1 | 2026-02-03 | 2026-03-11 | 1
JDH4-02-007-PR-2300 | Material Fabrication for Pipes | 2026-02-08 | 2026-03-16 | 1
JDH4-02-007-PR-1360 | Material Fabrication for Water Proofing | 2026-02-24 | 2026-03-17 | 1
JDH4-02-007-PR-1400 | PO for Bituminous Base & Wearing Cource | 2026-02-28 | 2026-03-17 | 1
JDH4-02-007-PR-1248 | Material Fabrication for Valves / Chambers - Stage 1 | 2026-02-28 | 2026-03-17 | 1
JDH4-02-007-PR-1277 | Material Fabrication for Valves / Chambers - Stage 1 | 2026-02-21 | 2026-03-17 | 1
JDH4-02-007-PR-1907 | Material Fabrication for Risers - Stage 1 | 2026-02-24 | 2026-03-17 | 1
JDH4-02-007-PR-2447 | Material Fabrication for Fire Hydrant - Stage 1 | 2026-02-28 | 2026-03-17 | 1
JDH4-02-007-PR-1010 | PO for Unit Sub-station | 2026-02-25 | 2026-03-23 | 1
JDH4-02-007-PR-1050 | PO for Lighting Panels/Feeder Pillers | 2026-03-08 | 2026-03-23 | 1
JDH4-02-007-PR-1200 | Material Fabrication for Earthing System | 2026-03-05 | 2026-03-23 | 1
JDH4-02-007-PR-1940 | PO for Ring Main Unit | 2026-02-28 | 2026-03-23 | 1
JDH4-02-007-MA-1910 | Material Approval for Local Control Panel / Monitoring Control Panel | 2026-03-01 | 2026-03-23 | 1
JDH4-02-007-PR-2530 | PO for Main Distribution Board / MCC panels | 2026-03-05 | 2026-03-23 | 1
JDH4-02-007-PR-2680 | PO for Final Panel Boards | 2026-03-01 | 2026-03-23 | 1
JDH4-02-007-PR-2760 | PO for Power Factor Correction Capacitor Bank | 2026-03-01 | 2026-03-23 | 1
JDH4-02-007-PR-2815 | Material Fabrication for Wiring Devices - Stage 1 | 2026-03-10 | 2026-03-23 | 1
JDH4-02-007-PR-1079 | Material Fabrication for Low Voltage Cables - Stage 2 | 2026-02-25 | 2026-03-23 | 1
JDH4-02-007-CN-1780 | Road backfilling [Road 01 ] | 2026-02-15 | 2026-03-26 | 1
JDH4-02-007-PR-1420 | PO for Precast Concrete Kerb | 2026-03-05 | 2026-03-26 | 1
JDH4-02-007-PR-1510 | PO for Traffic Signs | 2026-03-05 | 2026-03-26 | 1
JDH4-02-007-PR-3000 | PO for Instrumentation for Process Systems | 2026-03-10 | 2026-03-28 | 1
JDH4-02-007-PR-2567 | Material Fabrication for Main Distribution Board / MCC panels - Stage 1 | 2026-03-10 | 2026-03-28 | 1
JDH4-02-007-PR-1948 | Material Fabrication for Ring Main Unit - Stage 1 | 2026-03-05 | 2026-03-29 | 1
JDH4-02-007-PR-1278 | Material Fabrication for Valves / Chambers - Stage 2 | 2026-03-03 | 2026-03-30 | 1
JDH4-02-007-PR-2380 | PO for Air Conditioning and Ventilation | 2026-02-19 | 2026-03-31 | 1
JDH4-02-007-PR-2540 | PO for Local Control Panel/ Monitoring Control Panel | 2026-03-09 | 2026-03-31 | 1
JDH4-02-007-PR-2687 | Material Fabrication for Final Panel Boards - Stage 1 | 2026-03-09 | 2026-03-31 | 1
JDH4-02-007-CN-1110 | Milling of the existing asphalt layer [Demolition Works ] | 2026-03-01 | 2026-04-02 | 1
JDH4-02-007-CN-5340 | Excavation and Compaction (FDT) [Road 01 ] | 2026-02-24 | 2026-04-04 | 1
JDH4-02-007-PR-1908 | Material Fabrication for Risers - Stage 2 | 2026-03-10 | 2026-04-04 | 1
JDH4-02-007-PR-1870 | PO forFabrication for Fuel System | 2026-03-08 | 2026-04-05 | 1
JDH4-02-007-PR-2390 | Material Fabrication for Air Conditioning and Ventilation | 2026-02-25 | 2026-04-05 | 1
JDH4-02-007-CN-1850 | Plots backfilling Stage 4 [Plots ] | 2026-03-05 | 2026-04-05 | 1
JDH4-02-007-CN-4790 | Excavation & Compaction (FDT) [Road 01 ] | 2026-03-10 | 2026-04-18 | 1
JDH4-02-007-CN-5390 | Sand Bedding [Road 01 ] | 2026-03-10 | 2026-04-18 | 1