## الأعماال المنفذه خلال الاسبوع
# | القطاع | Project ID | اسم المشروع | مدير المشروع | المقاول | بداية المشروع | نهاية المشروع التعاقدية | نهاية المشروع المتوقعة/ الالتزام | قيمة المشروع | Planned (%) AS PER BASELINE حتى الاسبوع الحالي | Planned (%) AS PER Crashed Plan حتى الاسبوع الحالي | Actual (%) حتى الاسبوع السابق | Actual (%) حتى الاسبوع الحالي | Actual (%) خلال الاسبوع | الأعمال التي تمت خلال هذا الاسبوع | أسباب التأخير في حالة وجود تأخير | تحديات المشروع | استشاري المشروع | رقم استشاري المشروع | Email | مهندس تخطيط المشروع | رقم مهندس تخطيط المشروع | Email
1 | القطاع الأوسط | JHD4-02-007 | تطوير أراضي واحة جدة | عبد الله الشنيفي | شركة الانجاز للتجارة والمقاولات | 2025-11-24 | 2026-05-23 | 2026-11-23 | 57304347.86 | 58.61% | 86.21% | 88.41% | 91.11% | 2.7% | Road Marking Work at R4R, R4L, R5L, R7N & R8Road Marking Work at R4R, R4L, R5L, R7N & R8 CCTV Work at Lift Station Diesl Pump Work at Lift Station Rockfilling Work for Plots 4 & 6 Sign Board Installation at R7S & R5L ABC Work at Tent Road Earth work at Tent Kerbstone work at R1 MV Cable Laying at RS & Out Zone SL Work at R3 & R7S Handhole Installation at Lift Station Duct Work at Lift Station TL Work at R7S Pump Installation Work at Lift Station Relocation of Lightning Pole at R7S Checker Plate Installation at Lift Station
3 | القطاع الأوسط
4 | القطاع الأوسط
5 | القطاع الأوسط | [16 empty] | باسم الطيب | 0542536776 | Bassem.Altayeb@jasarapmc.com