## Failed Start Activities
Activity ID | Activity Name | Original Duration | Start | Finish | BL Project Start | BL Project Finish | Budgeted Total Cost | Total Float
Infrastructure Works of Area J -3rd Industrial City-Dammam-Phase 2 - Update 13-10-2026 |  | 304 | 2026-10-13 | 2027-10-13 | 2025-03-19 | 2026-11-11 | 18521051 | -226
Construction Works |  | 304 | 2026-10-13 | 2027-10-13 | 2025-03-19 | 2026-11-11 | 18521051 | -226
Infrastructure Networks |  | 304 | 2026-10-13 | 2027-10-13 | 2025-03-19 | 2026-10-26 | 14100199 | -226
Phase 2 Block "J" |  | 263 | 2026-10-13 | 2027-08-26 | 2025-03-19 | 2026-09-26 | 8029570 | -185
Rising Main Network |  | 17 | 2026-10-13 | 2026-11-01 | 2025-10-13 | 2025-11-01 | 226234 | 61
Valves Chamber |  | 17 | 2026-10-13 | 2026-11-01 | 2025-10-13 | 2025-11-01 | 226234 | 61
CO-RM-SW-410 | RC Slab Works for Valve Chambers and Washout chamber of Rising Main Network | 7 | 2026-10-13 | 2026-10-20 | 2025-10-13 | 2025-10-20 | 43273 | 61
CO-RM-SW-420 | Insulation Works for Valve Chambers and Washout chamber of Rising Main Network | 2 | 2026-10-21 | 2026-10-22 | 2025-10-21 | 2025-10-22 | 43273 | 61
CO-RM-SW-430 | Backfilling Works for Valve Chambers and Washout chamber of Rising Main Network | 5 | 2026-10-24 | 2026-10-28 | 2025-10-23 | 2025-10-28 | 53143 | 61
CO-RM-SW-440 | Testing and Covering Works for Valve Chambers and Washout chamber of Rising Main Network | 3 | 2026-10-29 | 2026-11-01 | 2025-10-29 | 2025-11-01 | 86545 | 61
Road 09 Local 2 ( 2278 LM ) |  | 263 | 2026-10-13 | 2027-08-26 | 2025-08-11 | 2026-08-25 | 3089265 | -227
SW_1 |  | 254 | 2026-10-13 | 2027-08-15 | 2025-08-11 | 2026-08-13 | 1209898 | -231
Sewage Network |  | 1 | 2026-10-13 | 2026-10-13 | 2025-08-11 | 2025-08-11 | 35494 | 22
Manholes |  | 1 | 2026-10-13 | 2026-10-13 | 2025-08-11 | 2025-08-11 | 35494 | 22
CO-R09.S01-SW-210 | Testing Works for Main Line Manholes of Sewage Network-[Road 09] -[SW-1] | 1 | 2026-10-13 | 2026-10-13 | 2025-08-11 | 2025-08-11 | 35494 | 22
Storm Drainage Network |  | 7 | 2026-10-21 | 2026-10-28 | 2025-10-30 | 2025-11-06 | 27719 | -160
Catch Basin Sections |  | 7 | 2026-10-21 | 2026-10-28 | 2025-10-30 | 2025-11-06 | 27719 | -160
CO-R09.S01-SD-160 | Testing Works for Catch Basins of Storm Drainage Network-[Road 09] -[SW-1] | 7 | 2026-10-21 | 2026-10-28 | 2025-10-30 | 2025-11-06 | 27719 | -160
Irrigation Network |  | 10 | 2026-10-21 | 2026-11-01 | 2025-12-17 | 2025-12-28 | 21307 | -201
Main Line Pipes |  | 10 | 2026-10-21 | 2026-11-01 | 2025-12-17 | 2025-12-28 | 21307 | -201
CO-R09.S01-IR-140 | Trench Backfilling and Compaction Works for Main Lines of Irrigation Network-[Road 09] -[SW-1] | 10 | 2026-10-21 | 2026-11-01 | 2025-12-17 | 2025-12-28 | 21307 | -201
Street Lighting Network |  | 237 | 2026-11-02 | 2027-08-15 | 2025-12-29 | 2026-08-13 | 273720 | -284
Lighting Poles Works |  | 68 | 2026-11-02 | 2027-01-19 | 2025-12-29 | 2026-04-30 | 140447 | -178
CO-R09.S01-SL-100 | Foundation Excavation Works for Lighting Poles of Street Lighting Network-[Road 09] -[SW-1] | 10 | 2026-11-02 | 2026-11-12 | 2025-12-29 | 2026-01-08 | 4664 | -201
CO-R09.S01-SL-110 | Installation Works for Lighting Poles Foundation of Street Lighting Network-[Road 09] -[SW-1] | 12 | 2026-11-14 | 2026-11-26 | 2026-01-10 | 2026-01-22 | 17827 | -201
CO-R09.S01-SL-120 | Installation Works for Lighting Poles of Street Lighting Network-[Road 09] -[SW-1] | 11 | 2026-12-19 | 2026-12-30 | 2026-02-14 | 2026-02-25 | 51299 | -201
CO-R09.S01-SL-210 | Backfilling Works for Lighting Poles of Street Lighting Network-[Road 09] -[SW-1] | 12 | 2026-12-31 | 2027-01-13 | 2026-04-12 | 2026-04-25 | 18654 | -201
CO-R09.S01-SL-130 | Installation Works for Lighting Fixtures With Drop Wire of Street Lighting Network-[Road 09] -[SW-1] | 12 | 2027-01-06 | 2027-01-19 | 2026-04-18 | 2026-04-30 | 29350 | -178
CO-R09.S01-SL-200 | Testing Works for Lighting Poles of Street Lighting Network-[Road 09] -[SW-1] | 5 | 2027-01-14 | 2027-01-19 | 2026-04-26 | 2026-04-30 | 18654 | -178
Cabling Works |  | 30 | 2026-11-14 | 2026-12-17 | 2026-01-10 | 2026-02-12 | 94452 | -201
CO-R09.S01-SL-140 | Trench Excavation and Bedding Works for Street Lighting Network-[Road 09] -[SW-1] | 10 | 2026-11-14 | 2026-11-24 | 2026-01-10 | 2026-01-20 | 0 | -201
CO-R09.S01-SL-150 | Cable Laying Works for Street Lighting Network-[Road 09] -[SW-1] | 10 | 2026-11-25 | 2026-12-06 | 2026-01-21 | 2026-02-01 | 87705 | -201
CO-R09.S01-SL-160 | Trench Backfilling and Compaction Works for Street Lighting Network-[Road 09] -[SW-1] | 10 | 2026-12-07 | 2026-12-17 | 2026-02-02 | 2026-02-12 | 6747 | -201
Distrubution Panel Boards |  | 39 | 2027-07-01 | 2027-08-15 | 2026-06-30 | 2026-08-13 | 38822 | -284
CO-R09.S01-SL-170 | Foundation Excavation Works For Panel Boards of Street Lighting Network-[Road 09] -[SW-1] | 15 | 2027-07-01 | 2027-07-18 | 2026-06-30 | 2026-07-16 | 0 | -284
CO-R09.S01-SL-180 | Installation Works for Panel Board Concrete Foundations of Street Lighting Network-[Road 09] -[SW-1] | 12 | 2027-07-19 | 2027-08-01 | 2026-07-18 | 2026-07-30 | 0 | -284
CO-R09.S01-SL-190 | Installation Works for Lighting Panel Boards of Street Lighting Network-[Road 09] -[SW-1] | 12 | 2027-08-02 | 2027-08-15 | 2026-08-01 | 2026-08-13 | 0 | -284
CO-R09.S01-SL-220 | A wall of concrete blocks to install the KWH meter of Street Lighting Network-[Road 09] -[SW-1] | 12 | 2027-08-02 | 2027-08-15 | 2026-08-01 | 2026-08-13 | 38822 | -284
Medium Voltage Network |  | 7 | 2026-12-20 | 2026-12-27 | 2026-02-24 | 2026-03-03 | 319548 | -200
Cabling Works |  | 7 | 2026-12-20 | 2026-12-27 | 2026-02-24 | 2026-03-03 | 319548 | -200
CO-R09.S01-MV-120 | Trench Backfilling and Compaction Works for Medium Voltage Network-[Road 09] -[SW-1] | 7 | 2026-12-20 | 2026-12-27 | 2026-02-24 | 2026-03-03 | 319548 | -200
Telecom Network |  | 38 | 2026-12-28 | 2027-02-09 | 2026-05-03 | 2026-06-20 | 166585 | -200
Ducts Works |  | 12 | 2026-12-28 | 2027-01-10 | 2026-05-03 | 2026-05-16 | 132124 | -186
CO-R09.S01-TE-100 | Trench Excavation and Bedding Works for Ducts of Telecom Network-[Road 09] -[SW-1] | 2 | 2026-12-28 | 2026-12-29 | 2026-05-03 | 2026-05-04 | 13266 | -200
CO-R09.S01-TE-110 | Pipes Laying Works for Ducts of Telecom Network-[Road 09] -[SW-1] | 4 | 2026-12-30 | 2027-01-03 | 2026-05-05 | 2026-05-09 | 79228 | -186
CO-R09.S01-TE-120 | Pouring Plain Concrete Above Ducts of Telecom Network-[Road 09] -[SW-1] | 2 | 2027-01-04 | 2027-01-05 | 2026-05-10 | 2026-05-11 | 13266 | -186
CO-R09.S01-TE-130 | Trench Backfilling and Compaction Works for Ducts of Telecom Network-[Road 09] -[SW-1] | 4 | 2027-01-06 | 2027-01-10 | 2026-05-12 | 2026-05-16 | 26365 | -186
Manholes Works |  | 36 | 2026-12-30 | 2027-02-09 | 2026-05-05 | 2026-06-20 | 34461 | -200
CO-R09.S01-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 09] -[SW-1] | 12 | 2026-12-30 | 2027-01-12 | 2026-05-05 | 2026-05-18 | 7515 | -200
CO-R09.S01-TE-150 | Installation Works for Manholes of Telecom Network-[Road 09] -[SW-1] | 12 | 2027-01-13 | 2027-01-26 | 2026-05-19 | 2026-06-06 | 19430 | -200
CO-R09.S01-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 09] -[SW-1] | 12 | 2027-01-27 | 2027-02-09 | 2026-06-07 | 2026-06-20 | 7515 | -200
Road Works |  | 21 | 2027-01-20 | 2027-02-13 | 2026-06-24 | 2026-07-18 | 365524 | -86
Pre-Bituminous Construction |  | 21 | 2027-01-20 | 2027-02-13 | 2026-06-24 | 2026-07-18 | 365524 | -86
CO-R09.S01-RD-P-110 | Aggregate Base Course Layer for Road Works-[Road 09] -[SW-1] | 21 | 2027-01-20 | 2027-02-13 | 2026-06-24 | 2026-07-18 | 365524 | -86
SW_2 |  | 263 | 2026-10-13 | 2027-08-26 | 2025-08-25 | 2026-08-25 | 1879368 | -227
Sewage Network |  | 1 | 2026-10-13 | 2026-10-13 | 2025-08-25 | 2025-08-25 | 5057 | -74
Manholes |  | 1 | 2026-10-13 | 2026-10-13 | 2025-08-25 | 2025-08-25 | 5057 | -74
CO-R09.S02-SW-210 | Testing Works for Main Line Manholes of Sewage Network-[Road 09]-[SW-2] | 1 | 2026-10-13 | 2026-10-13 | 2025-08-25 | 2025-08-25 | 5057 | -74
Storm Drainage Network |  | 11 | 2026-10-13 | 2026-10-25 | 2025-10-23 | 2025-12-11 | 66108 | 14
Manholes |  | 2 | 2026-10-13 | 2026-10-14 | 2025-10-23 | 2025-10-25 | 38389 | -78
CO-R09.S02-SD-210 | Testing Works for Manholes of Storm Drainage Network-[Road 09]-[SW-2] | 2 | 2026-10-13 | 2026-10-14 | 2025-10-23 | 2025-10-25 | 38389 | -78
Catch Basin Sections |  | 4 | 2026-10-21 | 2026-10-25 | 2025-12-08 | 2025-12-11 | 27719 | 14
CO-R09.S02-SD-160 | Testing Works for Catch Basins of Storm Drainage Network-[Road 09]-[SW-2] | 4 | 2026-10-21 | 2026-10-25 | 2025-12-08 | 2025-12-11 | 27719 | 14
Potable Water Network |  | 16 | 2026-10-21 | 2026-11-08 | 2025-11-11 | 2025-12-29 | 177551 | -171
Valve Chamber |  | 6 | 2026-10-21 | 2026-10-27 | 2025-11-11 | 2025-11-17 | 63935 | -161
CO-R09.S02-PW-210 | Installation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 09]-[SW-2] | 6 | 2026-10-21 | 2026-10-27 | 2025-11-11 | 2025-11-17 | 63935 | -161
Fire Hydrant |  | 16 | 2026-10-21 | 2026-11-08 | 2025-11-11 | 2025-12-29 | 113615 | -171
CO-R09.S02-PW-140 | Excavation Works for Fire Hydrants of Potable Water Network-[Road 09]-[SW-2] | 5 | 2026-10-21 | 2026-10-26 | 2025-11-11 | 2025-11-16 | 17042 | -171
CO-R09.S02-PW-150 | Installation Works for Fire Hydrant of Potable Water Network-[Road 09]-[SW-2] | 6 | 2026-10-27 | 2026-11-02 | 2025-12-17 | 2025-12-23 | 73850 | -171
CO-R09.S02-PW-160 | Trench Backfilling and Compaction Works for Fire Hydrants of Potable Water Network-[Road 09]-[SW-2] | 5 | 2026-11-03 | 2026-11-08 | 2025-12-24 | 2025-12-29 | 22723 | -171
Street Lighting Network |  | 130 | 2027-03-22 | 2027-08-26 | 2025-12-30 | 2026-08-25 | 573623 | -274
Lighting Poles Works |  | 58 | 2027-03-22 | 2027-06-02 | 2025-12-30 | 2026-06-01 | 140447 | -284
CO-R09.S02-SL-100 | Foundation Excavation Works for Lighting Poles of Street Lighting Network-[Road 09]-[SW-2] | 9 | 2027-03-22 | 2027-03-31 | 2025-12-30 | 2026-01-08 | 4664 | -281
CO-R09.S02-SL-110 | Installation Works for Lighting Poles Foundation of Street Lighting Network-[Road 09]-[SW-2] | 9 | 2027-04-01 | 2027-04-11 | 2026-01-10 | 2026-01-19 | 17827 | -281
CO-R09.S02-SL-120 | Installation Works for Lighting Poles of Street Lighting Network-[Road 09]-[SW-2] | 9 | 2027-04-12 | 2027-04-21 | 2026-02-08 | 2026-02-17 | 51299 | -281
CO-R09.S02-SL-210 | Backfilling Works for Lighting Poles of Street Lighting Network-[Road 09]-[SW-2] | 20 | 2027-04-22 | 2027-05-20 | 2026-04-26 | 2026-05-18 | 18654 | -281
CO-R09.S02-SL-130 | Installation Works for Lighting Fixtures With Drop Wire of Street Lighting Network-[Road 09]-[SW-2] | 17 | 2027-05-09 | 2027-06-02 | 2026-05-09 | 2026-06-01 | 29350 | -284
CO-R09.S02-SL-200 | Testing Works for Lighting Poles of Street Lighting Network-[Road 09]-[SW-2] | 8 | 2027-05-22 | 2027-05-30 | 2026-05-19 | 2026-06-01 | 18654 | -281
Cabling Works |  | 30 | 2027-04-22 | 2027-06-01 | 2026-02-18 | 2026-03-28 | 94452 | -259
CO-R09.S02-SL-140 | Trench Excavation and Bedding Works for Street Lighting Network-[Road 09]-[SW-2] | 10 | 2027-04-22 | 2027-05-03 | 2026-02-18 | 2026-03-01 | 0 | -259
CO-R09.S02-SL-150 | Cable Laying Works for Street Lighting Network-[Road 09]-[SW-2] | 10 | 2027-05-04 | 2027-05-20 | 2026-03-02 | 2026-03-12 | 87705 | -259
CO-R09.S02-SL-160 | Trench Backfilling and Compaction Works for Street Lighting Network-[Road 09]-[SW-2] | 10 | 2027-05-22 | 2027-06-01 | 2026-03-14 | 2026-03-28 | 6747 | -259
Distrubution Panel Boards |  | 48 | 2027-07-01 | 2027-08-26 | 2026-06-30 | 2026-08-25 | 338724 | -274
CO-R09.S02-SL-170 | Foundation Excavation Works For Panel Boards of Street Lighting Network-[Road 09]-[SW-2] | 10 | 2027-07-01 | 2027-07-12 | 2026-06-30 | 2026-07-11 | 43293 | -274
CO-R09.S02-SL-180 | Installation Works for Panel Board Concrete Foundations of Street Lighting Network-[Road 09]-[SW-2] | 10 | 2027-07-13 | 2027-07-24 | 2026-07-12 | 2026-07-22 | 48506 | -274
CO-R09.S02-SL-190 | Installation Works for Lighting Panel Boards of Street Lighting Network-[Road 09]-[SW-2] | 10 | 2027-07-25 | 2027-08-04 | 2026-07-23 | 2026-08-03 | 177856 | -274
CO-R09.S02-SL-220 | A wall of concrete blocks to install the KWH meter of Street Lighting Network-[Road 09]-[SW-2] | 18 | 2027-08-05 | 2027-08-26 | 2026-08-04 | 2026-08-25 | 69068 | -274
Telecom Network |  | 47 | 2027-01-11 | 2027-03-07 | 2026-05-17 | 2026-07-14 | 166742 | -200
Ducts Works |  | 24 | 2027-01-11 | 2027-02-07 | 2026-05-17 | 2026-06-17 | 132124 | -177
CO-R09.S02-TE-100 | Trench Excavation and Bedding Works for Ducts of Telecom Network-[Road 09]-[SW-2] | 3 | 2027-01-11 | 2027-01-13 | 2026-05-17 | 2026-05-19 | 13266 | -177
CO-R09.S02-TE-110 | Pipes Laying Works for Ducts of Telecom Network-[Road 09]-[SW-2] | 7 | 2027-01-14 | 2027-01-21 | 2026-05-20 | 2026-06-01 | 79228 | -177
CO-R09.S02-TE-120 | Pouring Plain Concrete Above Ducts of Telecom Network-[Road 09]-[SW-2] | 7 | 2027-01-23 | 2027-01-30 | 2026-06-02 | 2026-06-09 | 13266 | -177
CO-R09.S02-TE-130 | Trench Backfilling and Compaction Works for Ducts of Telecom Network-[Road 09]-[SW-2] | 7 | 2027-01-31 | 2027-02-07 | 2026-06-10 | 2026-06-17 | 26365 | -177
Manholes Works |  | 21 | 2027-02-10 | 2027-03-07 | 2026-06-21 | 2026-07-14 | 34618 | -200
CO-R09.S02-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 09]-[SW-2] | 7 | 2027-02-10 | 2027-02-17 | 2026-06-21 | 2026-06-28 | 6300 | -200
CO-R09.S02-TE-150 | Installation Works for Manholes of Telecom Network-[Road 09]-[SW-2] | 7 | 2027-02-18 | 2027-02-27 | 2026-06-29 | 2026-07-06 | 22017 | -200
CO-R09.S02-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 09]-[SW-2] | 7 | 2027-02-28 | 2027-03-07 | 2026-07-07 | 2026-07-14 | 6300 | -200
Road Works |  | 21 | 2027-05-25 | 2027-06-17 | 2026-07-15 | 2026-08-08 | 890287 | -168
Pre-Bituminous Construction |  | 21 | 2027-05-25 | 2027-06-17 | 2026-07-15 | 2026-08-08 | 890287 | -168
CO-R09.S02-RD-P-100 | Capping and Subgrade Layer for Road Works-[Road 09]-[SW-2] | 12 | 2027-05-25 | 2027-06-07 | 2026-07-15 | 2026-07-28 | 524764 | -259
CO-R09.S02-RD-P-110 | Aggregate Base Course Layer for Road Works-[Road 09]-[SW-2] | 18 | 2027-05-29 | 2027-06-17 | 2026-07-19 | 2026-08-08 | 365524 | -168
Road 10 Local 2 ( 2352 LM ) |  | 177 | 2026-10-13 | 2027-05-11 | 2025-07-23 | 2026-08-13 | 3671384 | -168
SW-3 |  | 172 | 2026-10-13 | 2027-05-05 | 2025-10-15 | 2026-08-13 | 1905867 | -166
SW_3-East |  | 172 | 2026-10-13 | 2027-05-05 | 2025-10-15 | 2026-06-29 | 1064519 | -166
Potable Water Network |  | 16 | 2026-10-13 | 2026-10-31 | 2025-10-15 | 2025-11-04 | 138829 | -68
Valve Chamber |  | 16 | 2026-10-13 | 2026-10-31 | 2025-10-15 | 2025-11-02 | 82021 | -68
CO-R10.S03-ES-PW-170 | Excavation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-3] | 1 | 2026-10-13 | 2026-10-13 | 2025-10-15 | 2025-10-15 | 1161 | -68
CO-R10.S03-ES-PW-180 | RC Footing Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-3] | 3 | 2026-10-14 | 2026-10-17 | 2025-10-16 | 2025-10-19 | 6529 | -68
CO-R10.S03-ES-PW-190 | RC Wall Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-3] | 6 | 2026-10-18 | 2026-10-24 | 2025-10-20 | 2025-10-26 | 15234 | -68
CO-R10.S03-ES-PW-200 | RC Slab Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-3] | 2 | 2026-10-25 | 2026-10-26 | 2025-10-27 | 2025-10-28 | 8705 | -68
CO-R10.S03-ES-PW-210 | Insulation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-3] | 1 | 2026-10-27 | 2026-10-27 | 2025-10-29 | 2025-10-29 | 41688 | -68
CO-R10.S03-ES-PW-220 | Backfilling Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-3] | 3 | 2026-10-28 | 2026-10-31 | 2025-10-30 | 2025-11-02 | 8705 | -68
Fire Hydrant |  | 15 | 2026-10-13 | 2026-10-29 | 2025-10-19 | 2025-11-04 | 56808 | -88
CO-R10.S03-ES-PW-140 | Excavation Works for Fire Hydrants of Potable Water Network-[Road 10]-[SW-3] | 6 | 2026-10-13 | 2026-10-19 | 2025-10-19 | 2025-10-25 | 8521 | -88
CO-R10.S03-ES-PW-150 | Installation Works for Fire Hydrant of Potable Water Network-[Road 10]-[SW-3] | 6 | 2026-10-20 | 2026-10-26 | 2025-10-26 | 2025-11-01 | 36925 | -88
CO-R10.S03-ES-PW-160 | Trench Backfilling and Compaction Works for Fire Hydrants of Potable Water Network-[Road 10]-[SW-3] | 6 | 2026-10-24 | 2026-10-29 | 2025-10-29 | 2025-11-04 | 11362 | -88
Street Lighting Network |  | 172 | 2026-10-13 | 2027-05-05 | 2025-12-02 | 2026-06-29 | 398748 | -245
Lighting Poles Works |  | 33 | 2026-10-13 | 2026-11-19 | 2025-12-02 | 2026-02-16 | 68790 | -151
CO-R10.S03-ES-SL-100 | Foundation Excavation Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2026-10-13 | 2026-10-26 | 2025-12-02 | 2025-12-15 | 2284 | -197
CO-R10.S03-ES-SL-110 | Installation Works for Lighting Poles Foundation of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2026-10-19 | 2026-11-01 | 2025-12-08 | 2025-12-21 | 8731 | -197
CO-R10.S03-ES-SL-120 | Installation Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-3] | 18 | 2026-10-25 | 2026-11-14 | 2025-12-14 | 2026-01-03 | 25126 | -197
CO-R10.S03-ES-SL-130 | Installation Works for Lighting Fixtures With Drop Wire of Street Lighting Network-[Road 10]-[SW-3] | 18 | 2026-10-31 | 2026-11-19 | 2026-01-26 | 2026-02-16 | 14376 | -151
CO-R10.S03-ES-SL-210 | Backfilling Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2026-11-01 | 2026-11-14 | 2026-01-27 | 2026-02-10 | 9137 | -176
CO-R10.S03-ES-SL-200 | Testing Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-3] | 5 | 2026-11-15 | 2026-11-19 | 2026-02-10 | 2026-02-16 | 9137 | -151
Cabling Works |  | 30 | 2026-11-15 | 2026-12-19 | 2026-01-04 | 2026-02-07 | 47398 | -197
CO-R10.S03-ES-SL-140 | Trench Excavation and Bedding Works for Street Lighting Network-[Road 10]-[SW-3] | 10 | 2026-11-15 | 2026-11-25 | 2026-01-04 | 2026-01-14 | 0 | -197
CO-R10.S03-ES-SL-150 | Cable Laying Works for Street Lighting Network-[Road 10]-[SW-3] | 10 | 2026-11-26 | 2026-12-07 | 2026-01-15 | 2026-01-26 | 44013 | -197
CO-R10.S03-ES-SL-160 | Trench Backfilling and Compaction Works for Street Lighting Network-[Road 10]-[SW-3] | 10 | 2026-12-08 | 2026-12-19 | 2026-01-27 | 2026-02-07 | 3386 | -197
Distrubution Panel Boards |  | 21 | 2027-04-12 | 2027-05-05 | 2026-06-06 | 2026-06-29 | 282560 | -245
CO-R10.S03-ES-SL-170 | Foundation Excavation Works For Panel Boards of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2027-04-12 | 2027-04-25 | 2026-06-06 | 2026-06-18 | 21647 | -245
CO-R10.S03-ES-SL-180 | Installation Works for Panel Board Concrete Foundations of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2027-04-19 | 2027-05-02 | 2026-06-13 | 2026-06-25 | 48506 | -245
CO-R10.S03-ES-SL-220 | A wall of concrete blocks to install the KWH meter of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2027-04-19 | 2027-05-02 | 2026-06-13 | 2026-06-25 | 34551 | -242
CO-R10.S03-ES-SL-190 | Installation Works for Lighting Panel Boards of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2027-04-22 | 2027-05-05 | 2026-06-16 | 2026-06-29 | 177856 | -245
Telecom Network |  | 28 | 2026-12-08 | 2027-01-09 | 2026-01-27 | 2026-02-28 | 80545 | -149
Ducts Works |  | 28 | 2026-12-08 | 2027-01-09 | 2026-01-27 | 2026-02-28 | 66431 | -149
CO-R10.S03-ES-TE-100 | Trench Excavation and Bedding Works for Ducts of Telecom Network-[Road 10]-[SW-3] | 7 | 2026-12-08 | 2026-12-15 | 2026-01-27 | 2026-02-03 | 6700 | -197
CO-R10.S03-ES-TE-110 | Pipes Laying Works for Ducts of Telecom Network-[Road 10]-[SW-3] | 7 | 2026-12-16 | 2026-12-23 | 2026-02-04 | 2026-02-11 | 39765 | -149
CO-R10.S03-ES-TE-120 | Pouring Plain Concrete Above Ducts of Telecom Network-[Road 10]-[SW-3] | 7 | 2026-12-24 | 2026-12-31 | 2026-02-12 | 2026-02-19 | 6700 | -149
CO-R10.S03-ES-TE-130 | Trench Backfilling and Compaction Works for Ducts of Telecom Network-[Road 10]-[SW-3] | 7 | 2027-01-02 | 2027-01-09 | 2026-02-21 | 2026-02-28 | 13266 | -149
Manholes Works |  | 21 | 2026-12-16 | 2027-01-09 | 2026-02-04 | 2026-02-28 | 14114 | -149
CO-R10.S03-ES-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 10]-[SW-3] | 7 | 2026-12-16 | 2026-12-23 | 2026-02-04 | 2026-02-11 | 2200 | -152
CO-R10.S03-ES-TE-150 | Installation Works for Manholes of Telecom Network-[Road 10]-[SW-3] | 7 | 2026-12-24 | 2026-12-31 | 2026-02-12 | 2026-02-19 | 9715 | -149
CO-R10.S03-ES-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 10]-[SW-3] | 7 | 2027-01-02 | 2027-01-09 | 2026-02-21 | 2026-02-28 | 2200 | -149
Road Works |  | 21 | 2027-01-10 | 2027-02-02 | 2026-03-07 | 2026-04-02 | 446397 | -91
Pre-Bituminous Construction |  | 21 | 2027-01-10 | 2027-02-02 | 2026-03-07 | 2026-04-02 | 446397 | -91
CO-R10.S03-ES-RD-100 | Capping and Subgrade Layer for Road Works-[Road 10]-[SW-3] | 18 | 2027-01-10 | 2027-01-30 | 2026-03-07 | 2026-03-30 | 263121 | -149
CO-R10.S03-ES-RD-110 | Aggregate Base Course Layer for Road Works-[Road 10]-[SW-3] | 18 | 2027-01-13 | 2027-02-02 | 2026-03-10 | 2026-04-02 | 183277 | -91
SW_3-West |  | 172 | 2026-10-13 | 2027-05-05 | 2026-01-05 | 2026-08-13 | 841348 | -166
Potable Water Network |  | 16 | 2026-10-13 | 2026-10-31 | 2026-01-05 | 2026-01-25 | 142020 | -68
Valve Chamber |  | 16 | 2026-10-13 | 2026-10-31 | 2026-01-05 | 2026-01-22 | 85213 | -68
CO-R10.S03-WE-PW-170 | Excavation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-3] | 1 | 2026-10-13 | 2026-10-13 | 2026-01-05 | 2026-01-05 | 4352 | -68
CO-R10.S03-WE-PW-180 | RC Footing Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-3] | 3 | 2026-10-14 | 2026-10-17 | 2026-01-06 | 2026-01-08 | 6529 | -68
CO-R10.S03-WE-PW-190 | RC Wall Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-3] | 6 | 2026-10-18 | 2026-10-24 | 2026-01-10 | 2026-01-15 | 15234 | -68
CO-R10.S03-WE-PW-200 | RC Slab Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-3] | 2 | 2026-10-25 | 2026-10-26 | 2026-01-17 | 2026-01-18 | 8705 | -68
CO-R10.S03-WE-PW-210 | Insulation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-3] | 1 | 2026-10-27 | 2026-10-27 | 2026-01-19 | 2026-01-19 | 41688 | -68
CO-R10.S03-WE-PW-220 | Backfilling Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-3] | 3 | 2026-10-28 | 2026-10-31 | 2026-01-20 | 2026-01-22 | 8705 | -68
Fire Hydrant |  | 15 | 2026-10-13 | 2026-10-29 | 2026-01-08 | 2026-01-25 | 56808 | -82
CO-R10.S03-WE-PW-140 | Excavation Works for Fire Hydrants of Potable Water Network-[Road 10]-[SW-3] | 6 | 2026-10-13 | 2026-10-19 | 2026-01-08 | 2026-01-14 | 8521 | -82
CO-R10.S03-WE-PW-150 | Installation Works for Fire Hydrant of Potable Water Network-[Road 10]-[SW-3] | 6 | 2026-10-20 | 2026-10-26 | 2026-01-15 | 2026-01-21 | 36925 | -82
CO-R10.S03-WE-PW-160 | Trench Backfilling and Compaction Works for Fire Hydrants of Potable Water Network-[Road 10]-[SW-3] | 6 | 2026-10-24 | 2026-10-29 | 2026-01-19 | 2026-01-25 | 11362 | -82
Street Lighting Network |  | 172 | 2026-10-13 | 2027-05-05 | 2026-02-22 | 2026-06-29 | 172386 | -245
Lighting Poles Works |  | 33 | 2026-10-13 | 2026-11-19 | 2026-02-22 | 2026-04-04 | 68790 | -151
CO-R10.S03-WE-SL-100 | Foundation Excavation Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2026-10-13 | 2026-10-26 | 2026-02-22 | 2026-03-07 | 2284 | -176
CO-R10.S03-WE-SL-110 | Installation Works for Lighting Poles Foundation of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2026-10-19 | 2026-11-01 | 2026-02-28 | 2026-03-12 | 8731 | -176
CO-R10.S03-WE-SL-120 | Installation Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-3] | 18 | 2026-10-25 | 2026-11-14 | 2026-03-05 | 2026-03-29 | 25126 | -176
CO-R10.S03-WE-SL-130 | Installation Works for Lighting Fixtures With Drop Wire of Street Lighting Network-[Road 10]-[SW-3] | 18 | 2026-10-31 | 2026-11-19 | 2026-03-11 | 2026-04-04 | 14376 | -151
CO-R10.S03-WE-SL-210 | Backfilling Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2026-11-01 | 2026-11-14 | 2026-03-12 | 2026-03-29 | 9137 | -151
CO-R10.S03-WE-SL-200 | Testing Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-3] | 5 | 2026-11-15 | 2026-11-19 | 2026-03-30 | 2026-04-04 | 9137 | -151
Cabling Works |  | 30 | 2026-11-15 | 2026-12-19 | 2026-03-30 | 2026-05-03 | 47398 | -176
CO-R10.S03-WE-SL-140 | Trench Excavation and Bedding Works for Street Lighting Network-[Road 10]-[SW-3] | 10 | 2026-11-15 | 2026-11-25 | 2026-03-30 | 2026-04-09 | 0 | -176
CO-R10.S03-WE-SL-150 | Cable Laying Works for Street Lighting Network-[Road 10]-[SW-3] | 10 | 2026-11-26 | 2026-12-07 | 2026-04-11 | 2026-04-21 | 44013 | -176
CO-R10.S03-WE-SL-160 | Trench Backfilling and Compaction Works for Street Lighting Network-[Road 10]-[SW-3] | 10 | 2026-12-08 | 2026-12-19 | 2026-04-22 | 2026-05-03 | 3386 | -176
Distrubution Panel Boards |  | 21 | 2027-04-12 | 2027-05-05 | 2026-06-06 | 2026-06-29 | 56197 | -245
CO-R10.S03-WE-SL-170 | Foundation Excavation Works For Panel Boards of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2027-04-12 | 2027-04-25 | 2026-06-06 | 2026-06-18 | 21647 | -245
CO-R10.S03-WE-SL-180 | Installation Works for Panel Board Concrete Foundations of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2027-04-19 | 2027-05-02 | 2026-06-13 | 2026-06-25 | 0 | -245
CO-R10.S03-WE-SL-220 | A wall of concrete blocks to install the KWH meter of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2027-04-19 | 2027-05-02 | 2026-06-13 | 2026-06-25 | 34551 | -242
CO-R10.S03-WE-SL-190 | Installation Works for Lighting Panel Boards of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2027-04-22 | 2027-05-05 | 2026-06-16 | 2026-06-29 | 0 | -245
Telecom Network |  | 24 | 2026-12-08 | 2027-01-04 | 2026-06-17 | 2026-07-14 | 80545 | -139
Ducts Works |  | 24 | 2026-12-08 | 2027-01-04 | 2026-06-17 | 2026-07-14 | 66431 | -139
CO-R10.S03-WE-TE-100 | Trench Excavation and Bedding Works for Ducts of Telecom Network-[Road 10]-[SW-3] | 3 | 2026-12-08 | 2026-12-10 | 2026-06-17 | 2026-06-20 | 6700 | -148
CO-R10.S03-WE-TE-110 | Pipes Laying Works for Ducts of Telecom Network-[Road 10]-[SW-3] | 7 | 2026-12-12 | 2026-12-19 | 2026-06-21 | 2026-06-28 | 39765 | -139
CO-R10.S03-WE-TE-120 | Pouring Plain Concrete Above Ducts of Telecom Network-[Road 10]-[SW-3] | 7 | 2026-12-20 | 2026-12-27 | 2026-06-29 | 2026-07-06 | 6700 | -139
CO-R10.S03-WE-TE-130 | Trench Backfilling and Compaction Works for Ducts of Telecom Network-[Road 10]-[SW-3] | 7 | 2026-12-28 | 2027-01-04 | 2026-07-07 | 2026-07-14 | 13266 | -139
Manholes Works |  | 21 | 2026-12-12 | 2027-01-04 | 2026-06-21 | 2026-07-14 | 14114 | -139
CO-R10.S03-WE-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 10]-[SW-3] | 7 | 2026-12-12 | 2026-12-19 | 2026-06-21 | 2026-06-28 | 2200 | -148
CO-R10.S03-WE-TE-150 | Installation Works for Manholes of Telecom Network-[Road 10]-[SW-3] | 7 | 2026-12-20 | 2026-12-27 | 2026-06-29 | 2026-07-06 | 9715 | -139
CO-R10.S03-WE-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 10]-[SW-3] | 7 | 2026-12-28 | 2027-01-04 | 2026-07-07 | 2026-07-14 | 2200 | -139
Road Works |  | 21 | 2027-01-05 | 2027-01-28 | 2026-07-21 | 2026-08-13 | 446397 | -87
Pre-Bituminous Construction |  | 21 | 2027-01-05 | 2027-01-28 | 2026-07-21 | 2026-08-13 | 446397 | -87
CO-R10.S03-WE-RD-100 | Capping and Subgrade Layer for Road Works-[Road 10]-[SW-3] | 12 | 2027-01-05 | 2027-01-18 | 2026-07-21 | 2026-08-03 | 263121 | -139
CO-R10.S03-WE-RD-110 | Aggregate Base Course Layer for Road Works-[Road 10]-[SW-3] | 18 | 2027-01-09 | 2027-01-28 | 2026-07-25 | 2026-08-13 | 183277 | -87
SW-4 |  | 177 | 2026-10-13 | 2027-05-11 | 2025-07-23 | 2026-08-11 | 1765518 | -168
SW_4-East |  | 139 | 2026-10-13 | 2027-03-28 | 2025-07-23 | 2026-08-11 | 837988 | -130
Sewage Network |  | 1 | 2026-10-13 | 2026-10-13 | 2025-07-23 | 2025-07-23 | 8813 | -70
Manholes |  | 1 | 2026-10-13 | 2026-10-13 | 2025-07-23 | 2025-07-23 | 8813 | -70
CO-R10.S04-ES-SW-210 | Testing Works for Main Line Manholes of Sewage Network-[Road 10]-[SW-4] | 1 | 2026-10-13 | 2026-10-13 | 2025-07-23 | 2025-07-23 | 8813 | -70
Storm Drainage Network |  | 10 | 2026-10-13 | 2026-10-24 | 2025-12-18 | 2026-01-22 | 34251 | -13
Manholes |  | 1 | 2026-10-13 | 2026-10-13 | 2025-12-18 | 2025-12-18 | 20352 | -70
CO-R10.S04-ES-SD-210 | Testing Works for Manholes of Storm Drainage Network-[Road 10]-[SW-4] | 1 | 2026-10-13 | 2026-10-13 | 2025-12-18 | 2025-12-18 | 20352 | -70
Catch Basin Sections |  | 10 | 2026-10-13 | 2026-10-24 | 2026-01-12 | 2026-01-22 | 13899 | -13
CO-R10.S04-ES-SD-160 | Testing Works for Catch Basins of Storm Drainage Network-[Road 10]-[SW-4] | 10 | 2026-10-13 | 2026-10-24 | 2026-01-12 | 2026-01-22 | 13899 | -13
Potable Water Network |  | 22 | 2026-10-13 | 2026-11-07 | 2026-01-15 | 2026-02-11 | 132366 | -91
Valve Chamber |  | 15 | 2026-10-13 | 2026-10-29 | 2026-01-15 | 2026-02-02 | 132366 | -84
CO-R10.S04-ES-PW-170 | Excavation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-4] | 1 | 2026-10-13 | 2026-10-13 | 2026-01-15 | 2026-01-15 | 16109 | -91
CO-R10.S04-ES-PW-180 | RC Footing Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-4] | 3 | 2026-10-14 | 2026-10-17 | 2026-01-17 | 2026-01-19 | 19376 | -84
CO-R10.S04-ES-PW-190 | RC Wall Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-4] | 6 | 2026-10-18 | 2026-10-24 | 2026-01-20 | 2026-01-26 | 45211 | -84
CO-R10.S04-ES-PW-200 | RC Slab Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-4] | 2 | 2026-10-25 | 2026-10-26 | 2026-01-27 | 2026-01-28 | 25835 | -84
CO-R10.S04-ES-PW-220 | Backfilling Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-4] | 3 | 2026-10-27 | 2026-10-29 | 2026-01-31 | 2026-02-02 | 25835 | -84
Fire Hydrant |  | 21 | 2026-10-14 | 2026-11-07 | 2026-01-19 | 2026-02-11 | 0 | -91
CO-R10.S04-ES-PW-140 | Excavation Works for Fire Hydrants of Potable Water Network-[Road 10]-[SW-4] | 7 | 2026-10-14 | 2026-10-21 | 2026-01-19 | 2026-01-26 | 0 | -91
CO-R10.S04-ES-PW-150 | Installation Works for Fire Hydrant of Potable Water Network-[Road 10]-[SW-4] | 7 | 2026-10-22 | 2026-10-29 | 2026-01-27 | 2026-02-03 | 0 | -91
CO-R10.S04-ES-PW-160 | Trench Backfilling and Compaction Works for Fire Hydrants of Potable Water Network-[Road 10]-[SW-4] | 7 | 2026-10-31 | 2026-11-07 | 2026-02-04 | 2026-02-11 | 0 | -91
Street Lighting Network |  | 139 | 2026-10-13 | 2027-03-28 | 2026-03-10 | 2026-06-15 | 135616 | -172
Lighting Poles Works |  | 139 | 2026-10-13 | 2027-03-28 | 2026-03-10 | 2026-04-20 | 68790 | -172
CO-R10.S04-ES-SL-100 | Foundation Excavation Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-4] | 7 | 2026-10-13 | 2026-10-20 | 2026-03-10 | 2026-03-17 | 2284 | -178
CO-R10.S04-ES-SL-110 | Installation Works for Lighting Poles Foundation of Street Lighting Network-[Road 10]-[SW-4] | 7 | 2026-10-19 | 2026-10-26 | 2026-03-16 | 2026-03-26 | 8731 | -178
CO-R10.S04-ES-SL-120 | Installation Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-4] | 7 | 2026-10-25 | 2026-11-01 | 2026-03-25 | 2026-04-01 | 25126 | -178
CO-R10.S04-ES-SL-210 | Backfilling Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-4] | 15 | 2026-11-15 | 2026-12-01 | 2026-03-25 | 2026-04-11 | 9137 | -176
CO-R10.S04-ES-SL-200 | Testing Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-4] | 7 | 2026-12-02 | 2026-12-09 | 2026-04-12 | 2026-04-19 | 9137 | -83
CO-R10.S04-ES-SL-130 | Installation Works for Lighting Fixtures With Drop Wire of Street Lighting Network-[Road 10]-[SW-4] | 18 | 2027-03-04 | 2027-03-28 | 2026-03-31 | 2026-04-20 | 14376 | -172
Cabling Works |  | 21 | 2026-11-02 | 2026-11-25 | 2026-04-02 | 2026-04-26 | 47398 | -178
CO-R10.S04-ES-SL-140 | Trench Excavation and Bedding Works for Street Lighting Network-[Road 10]-[SW-4] | 7 | 2026-11-02 | 2026-11-09 | 2026-04-02 | 2026-04-09 | 0 | -178
CO-R10.S04-ES-SL-150 | Cable Laying Works for Street Lighting Network-[Road 10]-[SW-4] | 7 | 2026-11-10 | 2026-11-17 | 2026-04-11 | 2026-04-18 | 44013 | -178
CO-R10.S04-ES-SL-160 | Trench Backfilling and Compaction Works for Street Lighting Network-[Road 10]-[SW-4] | 7 | 2026-11-18 | 2026-11-25 | 2026-04-19 | 2026-04-26 | 3386 | -178
Distrubution Panel Boards |  | 39 | 2026-11-26 | 2027-01-10 | 2026-04-27 | 2026-06-15 | 19427 | -150
CO-R10.S04-ES-SL-170 | Foundation Excavation Works For Panel Boards of Street Lighting Network-[Road 10]-[SW-4] | 18 | 2026-11-26 | 2026-12-16 | 2026-04-27 | 2026-05-17 | 0 | -159
CO-R10.S04-ES-SL-180 | Installation Works for Panel Board Concrete Foundations of Street Lighting Network-[Road 10]-[SW-4] | 12 | 2026-12-07 | 2026-12-20 | 2026-05-07 | 2026-05-20 | 0 | -150
CO-R10.S04-ES-SL-190 | Installation Works for Lighting Panel Boards of Street Lighting Network-[Road 10]-[SW-4] | 12 | 2026-12-21 | 2027-01-03 | 2026-05-21 | 2026-06-08 | 0 | -150
CO-R10.S04-ES-SL-220 | A wall of concrete blocks to install the KWH meter of Street Lighting Network-[Road 10]-[SW-4] | 18 | 2026-12-21 | 2027-01-10 | 2026-05-21 | 2026-06-15 | 19427 | -150
Telecom Network |  | 28 | 2026-12-16 | 2027-01-17 | 2026-04-25 | 2026-07-22 | 80545 | -152
Ducts Works |  | 28 | 2026-12-16 | 2027-01-17 | 2026-04-25 | 2026-05-31 | 66431 | -152
CO-R10.S04-ES-TE-100 | Trench Excavation and Bedding Works for Ducts of Telecom Network-[Road 10]-[SW-4] | 7 | 2026-12-16 | 2026-12-23 | 2026-04-25 | 2026-05-02 | 6700 | -197
CO-R10.S04-ES-TE-110 | Pipes Laying Works for Ducts of Telecom Network-[Road 10]-[SW-4] | 7 | 2026-12-24 | 2026-12-31 | 2026-05-03 | 2026-05-10 | 39765 | -152
CO-R10.S04-ES-TE-120 | Pouring Plain Concrete Above Ducts of Telecom Network-[Road 10]-[SW-4] | 7 | 2027-01-02 | 2027-01-09 | 2026-05-11 | 2026-05-18 | 6700 | -152
CO-R10.S04-ES-TE-130 | Trench Backfilling and Compaction Works for Ducts of Telecom Network-[Road 10]-[SW-4] | 7 | 2027-01-10 | 2027-01-17 | 2026-05-19 | 2026-05-31 | 13266 | -152
Manholes Works |  | 21 | 2026-12-24 | 2027-01-17 | 2026-06-29 | 2026-07-22 | 14114 | -152
CO-R10.S04-ES-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 10]-[SW-4] | 7 | 2026-12-24 | 2026-12-31 | 2026-06-29 | 2026-07-06 | 2200 | -152
CO-R10.S04-ES-TE-150 | Installation Works for Manholes of Telecom Network-[Road 10]-[SW-4] | 7 | 2027-01-02 | 2027-01-09 | 2026-07-07 | 2026-07-14 | 9715 | -152
CO-R10.S04-ES-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 10]-[SW-4] | 7 | 2027-01-10 | 2027-01-17 | 2026-07-15 | 2026-07-22 | 2200 | -152
Road Works |  | 17 | 2027-01-18 | 2027-02-06 | 2026-07-23 | 2026-08-11 | 446397 | -91
Pre-Bituminous Construction |  | 17 | 2027-01-18 | 2027-02-06 | 2026-07-23 | 2026-08-11 | 446397 | -91
CO-R10.S04-ES-RD-100 | Capping and Subgrade Layer for Road Works-[Road 10]-[SW-4] | 14 | 2027-01-18 | 2027-02-02 | 2026-07-23 | 2026-08-08 | 263121 | -152
CO-R10.S04-ES-RD-110 | Aggregate Base Course Layer for Road Works-[Road 10]-[SW-4] | 12 | 2027-01-24 | 2027-02-06 | 2026-07-29 | 2026-08-11 | 183277 | -91
SW_4-West |  | 177 | 2026-10-13 | 2027-05-11 | 2025-11-11 | 2026-08-09 | 927530 | -168
Sewage Network |  | 1 | 2026-10-13 | 2026-10-13 | 2025-11-11 | 2025-11-11 | 10264 | -68
Manholes |  | 1 | 2026-10-13 | 2026-10-13 | 2025-11-11 | 2025-11-11 | 10264 | -68
CO-R10.S04-WE-SW-210 | Testing Works for Main Line Manholes of Sewage Network-[Road 10]-[SW-4] | 1 | 2026-10-13 | 2026-10-13 | 2025-11-11 | 2025-11-11 | 10264 | -68
Storm Drainage Network |  | 7 | 2026-10-13 | 2026-10-20 | 2025-12-18 | 2026-01-26 | 49835 | -74
Manholes |  | 1 | 2026-10-13 | 2026-10-13 | 2025-12-18 | 2025-12-18 | 22038 | -68
CO-R10.S04-WE-SD-210 | Testing Works for Manholes of Storm Drainage Network-[Road 10]-[SW-4] | 1 | 2026-10-13 | 2026-10-13 | 2025-12-18 | 2025-12-18 | 22038 | -68
Catch Basin Sections |  | 7 | 2026-10-13 | 2026-10-20 | 2026-01-19 | 2026-01-26 | 27798 | -207
CO-R10.S04-WE-SD-170 | Trench Backfilling and Compaction Works for Catch Basins of Storm Drainage Network-[Road 10]-[SW-4] | 7 | 2026-10-13 | 2026-10-20 | 2026-01-19 | 2026-01-26 | 27798 | -207
Potable Water Network |  | 22 | 2026-10-13 | 2026-11-07 | 2026-01-15 | 2026-02-11 | 86792 | -89
Valve Chamber |  | 15 | 2026-10-13 | 2026-10-29 | 2026-01-15 | 2026-02-02 | 86792 | -82
CO-R10.S04-WE-PW-170 | Excavation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-4] | 1 | 2026-10-13 | 2026-10-13 | 2026-01-15 | 2026-01-15 | 8679 | -89
CO-R10.S04-WE-PW-180 | RC Footing Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-4] | 3 | 2026-10-14 | 2026-10-17 | 2026-01-17 | 2026-01-19 | 13019 | -82
CO-R10.S04-WE-PW-190 | RC Wall Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-4] | 6 | 2026-10-18 | 2026-10-24 | 2026-01-20 | 2026-01-26 | 30377 | -82
CO-R10.S04-WE-PW-200 | RC Slab Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-4] | 2 | 2026-10-25 | 2026-10-26 | 2026-01-27 | 2026-01-28 | 17358 | -82
CO-R10.S04-WE-PW-220 | Backfilling Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-4] | 3 | 2026-10-27 | 2026-10-29 | 2026-01-31 | 2026-02-02 | 17358 | -82
Fire Hydrant |  | 21 | 2026-10-14 | 2026-11-07 | 2026-01-19 | 2026-02-11 | 0 | -89
CO-R10.S04-WE-PW-140 | Excavation Works for Fire Hydrants of Potable Water Network-[Road 10]-[SW-4] | 7 | 2026-10-14 | 2026-10-21 | 2026-01-19 | 2026-01-26 | 0 | -89
CO-R10.S04-WE-PW-150 | Installation Works for Fire Hydrant of Potable Water Network-[Road 10]-[SW-4] | 7 | 2026-10-22 | 2026-10-29 | 2026-01-27 | 2026-02-03 | 0 | -89
CO-R10.S04-WE-PW-160 | Trench Backfilling and Compaction Works for Fire Hydrants of Potable Water Network-[Road 10]-[SW-4] | 7 | 2026-10-31 | 2026-11-07 | 2026-02-04 | 2026-02-11 | 0 | -89
Irrigation Network |  | 71 | 2026-10-21 | 2027-01-11 | 2026-02-12 | 2026-03-08 | 118080 | -257
Main Line Pipes |  | 71 | 2026-10-21 | 2027-01-11 | 2026-02-12 | 2026-03-08 | 118080 | -257
CO-R10.S04-WE-IR-100 | Trench Excavation and Bedding Works for Main Lines of Irrigation Network-[Road 10]-[SW-4] | 6 | 2026-10-21 | 2026-10-27 | 2026-02-12 | 2026-02-18 | 21368 | -207
CO-R10.S04-WE-IR-110 | Pipes Laying Works for Main Lines of Irrigation Network-[Road 10]-[SW-4] | 7 | 2026-10-28 | 2026-11-04 | 2026-02-19 | 2026-02-26 | 64103 | -207
CO-R10.S04-WE-IR-120 | Installation Works for Main Line Valves of Irrigation Network-[Road 10]-[SW-4] | 3 | 2027-01-03 | 2027-01-05 | 2026-02-28 | 2026-03-02 | 21926 | -257
CO-R10.S04-WE-IR-130 | Trench Backfilling and Compaction Works for Main Lines of Irrigation Network-[Road 10]-[SW-4] | 5 | 2027-01-06 | 2027-01-11 | 2026-03-03 | 2026-03-08 | 10684 | -257
Street Lighting Network |  | 97 | 2027-01-12 | 2027-05-09 | 2026-03-09 | 2026-07-07 | 135616 | -208
Lighting Poles Works |  | 61 | 2027-01-12 | 2027-03-28 | 2026-03-09 | 2026-04-23 | 68790 | -172
CO-R10.S04-WE-SL-100 | Foundation Excavation Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-4] | 10 | 2027-01-12 | 2027-01-23 | 2026-03-09 | 2026-03-19 | 2284 | -257
CO-R10.S04-WE-SL-110 | Installation Works for Lighting Poles Foundation of Street Lighting Network-[Road 10]-[SW-4] | 10 | 2027-01-18 | 2027-01-28 | 2026-03-15 | 2026-03-29 | 8731 | -257
CO-R10.S04-WE-SL-120 | Installation Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-4] | 18 | 2027-01-24 | 2027-02-13 | 2026-03-24 | 2026-04-13 | 25126 | -257
CO-R10.S04-WE-SL-210 | Backfilling Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-4] | 15 | 2027-01-27 | 2027-02-13 | 2026-03-30 | 2026-04-15 | 9137 | -146
CO-R10.S04-WE-SL-200 | Testing Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-4] | 7 | 2027-02-14 | 2027-02-21 | 2026-04-16 | 2026-04-23 | 9137 | -146
CO-R10.S04-WE-SL-130 | Installation Works for Lighting Fixtures With Drop Wire of Street Lighting Network-[Road 10]-[SW-4] | 18 | 2027-03-04 | 2027-03-28 | 2026-04-04 | 2026-04-23 | 14376 | -172
Cabling Works |  | 30 | 2027-02-14 | 2027-03-24 | 2026-04-14 | 2026-05-18 | 47398 | -257
CO-R10.S04-WE-SL-140 | Trench Excavation and Bedding Works for Street Lighting Network-[Road 10]-[SW-4] | 10 | 2027-02-14 | 2027-02-25 | 2026-04-14 | 2026-04-25 | 0 | -257
CO-R10.S04-WE-SL-150 | Cable Laying Works for Street Lighting Network-[Road 10]-[SW-4] | 10 | 2027-02-27 | 2027-03-13 | 2026-04-26 | 2026-05-06 | 44013 | -257
CO-R10.S04-WE-SL-160 | Trench Backfilling and Compaction Works for Street Lighting Network-[Road 10]-[SW-4] | 10 | 2027-03-14 | 2027-03-24 | 2026-05-07 | 2026-05-18 | 3386 | -257
Distrubution Panel Boards |  | 39 | 2027-03-25 | 2027-05-09 | 2026-05-19 | 2026-07-07 | 19427 | -248
CO-R10.S04-WE-SL-170 | Foundation Excavation Works For Panel Boards of Street Lighting Network-[Road 10]-[SW-4] | 18 | 2027-03-25 | 2027-04-14 | 2026-05-19 | 2026-06-13 | 0 | -257
CO-R10.S04-WE-SL-180 | Installation Works for Panel Board Concrete Foundations of Street Lighting Network-[Road 10]-[SW-4] | 12 | 2027-04-05 | 2027-04-18 | 2026-06-03 | 2026-06-16 | 0 | -248
CO-R10.S04-WE-SL-190 | Installation Works for Lighting Panel Boards of Street Lighting Network-[Road 10]-[SW-4] | 12 | 2027-04-19 | 2027-05-02 | 2026-06-17 | 2026-06-30 | 0 | -248
CO-R10.S04-WE-SL-220 | A wall of concrete blocks to install the KWH meter of Street Lighting Network-[Road 10]-[SW-4] | 18 | 2027-04-19 | 2027-05-09 | 2026-06-17 | 2026-07-07 | 19427 | -248
Telecom Network |  | 28 | 2027-03-23 | 2027-04-24 | 2026-06-21 | 2026-07-22 | 80545 | -229
Ducts Works |  | 28 | 2027-03-23 | 2027-04-24 | 2026-06-21 | 2026-07-22 | 66431 | -229
CO-R10.S04-WE-TE-100 | Trench Excavation and Bedding Works for Ducts of Telecom Network-[Road 10]-[SW-4] | 7 | 2027-03-23 | 2027-03-30 | 2026-06-21 | 2026-06-28 | 6700 | -229
CO-R10.S04-WE-TE-110 | Pipes Laying Works for Ducts of Telecom Network-[Road 10]-[SW-4] | 7 | 2027-03-31 | 2027-04-07 | 2026-06-29 | 2026-07-06 | 39765 | -229
CO-R10.S04-WE-TE-120 | Pouring Plain Concrete Above Ducts of Telecom Network-[Road 10]-[SW-4] | 7 | 2027-04-08 | 2027-04-15 | 2026-07-07 | 2026-07-14 | 6700 | -229
CO-R10.S04-WE-TE-130 | Trench Backfilling and Compaction Works for Ducts of Telecom Network-[Road 10]-[SW-4] | 7 | 2027-04-17 | 2027-04-24 | 2026-07-15 | 2026-07-22 | 13266 | -229
Manholes Works |  | 21 | 2027-03-31 | 2027-04-24 | 2026-06-29 | 2026-07-22 | 14114 | -229
CO-R10.S04-WE-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 10]-[SW-4] | 7 | 2027-03-31 | 2027-04-07 | 2026-06-29 | 2026-07-06 | 2200 | -229
CO-R10.S04-WE-TE-150 | Installation Works for Manholes of Telecom Network-[Road 10]-[SW-4] | 7 | 2027-04-08 | 2027-04-15 | 2026-07-07 | 2026-07-14 | 9715 | -229
CO-R10.S04-WE-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 10]-[SW-4] | 7 | 2027-04-17 | 2027-04-24 | 2026-07-15 | 2026-07-22 | 2200 | -229
Road Works |  | 15 | 2027-04-25 | 2027-05-11 | 2026-07-23 | 2026-08-09 | 446397 | -168
Pre-Bituminous Construction |  | 15 | 2027-04-25 | 2027-05-11 | 2026-07-23 | 2026-08-09 | 446397 | -168
CO-R10.S04-WE-RD-100 | Capping and Subgrade Layer for Road Works-[Road 10]-[SW-4] | 12 | 2027-04-25 | 2027-05-08 | 2026-07-23 | 2026-08-05 | 263121 | -229
CO-R10.S04-WE-RD-110 | Aggregate Base Course Layer for Road Works-[Road 10]-[SW-4] | 12 | 2027-04-28 | 2027-05-11 | 2026-07-27 | 2026-08-09 | 183277 | -168
Road 11 Local 1 ( 670 LM ) |  | 217 | 2026-10-13 | 2027-07-03 | 2025-10-14 | 2026-07-30 | 190284 | -232
SW_5 |  | 83 | 2026-10-13 | 2027-01-17 | 2026-01-11 | 2026-07-22 | 57986 | -119
Irrigation Network |  | 10 | 2026-10-13 | 2026-10-24 | 2026-01-11 | 2026-01-21 | 48585 | -46
Main Line Pipes |  | 10 | 2026-10-13 | 2026-10-24 | 2026-01-11 | 2026-01-21 | 48585 | -46
CO-R11.S05-IR-120 | Installation Works for Main Line Valves of Irrigation Network-[Road 11]-[SW-5] | 3 | 2026-10-13 | 2026-10-15 | 2026-01-11 | 2026-01-13 | 42350 | -46
CO-R11.S05-IR-130 | Trench Backfilling and Compaction Works for Main Lines of Irrigation Network-[Road 11]-[SW-5] | 7 | 2026-10-17 | 2026-10-24 | 2026-01-14 | 2026-01-21 | 6235 | -46
Telecom Network |  | 21 | 2026-12-24 | 2027-01-17 | 2026-06-29 | 2026-07-22 | 9401 | -124
Manholes Works |  | 21 | 2026-12-24 | 2027-01-17 | 2026-06-29 | 2026-07-22 | 9401 | -124
CO-R11.S05-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 11]-[SW-5] | 7 | 2026-12-24 | 2026-12-31 | 2026-06-29 | 2026-07-06 | 1257 | -131
CO-R11.S05-TE-150 | Installation Works for Manholes of Telecom Network-[Road 11]-[SW-5] | 7 | 2027-01-02 | 2027-01-09 | 2026-07-07 | 2026-07-14 | 6887 | -124
CO-R11.S05-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 11]-[SW-5] | 7 | 2027-01-10 | 2027-01-17 | 2026-07-15 | 2026-07-22 | 1257 | -124
SW_6 |  | 217 | 2026-10-13 | 2027-07-03 | 2025-10-14 | 2026-07-30 | 132298 | -232
Sewage Network |  | 1 | 2026-10-18 | 2026-10-18 | 2025-10-14 | 2025-10-14 | 9048 | -57
Manholes |  | 1 | 2026-10-18 | 2026-10-18 | 2025-10-14 | 2025-10-14 | 9048 | -57
CO-R11.S06-SW-210 | Testing Works for Main Line Manholes of Sewage Network-[Road 11]-[SW-6] | 1 | 2026-10-18 | 2026-10-18 | 2025-10-14 | 2025-10-14 | 9048 | -57
Potable Water Network |  | 177 | 2026-10-13 | 2027-05-11 | 2026-01-28 | 2026-02-28 | 53759 | -213
Valve Chamber |  | 6 | 2026-10-13 | 2026-10-19 | 2026-01-28 | 2026-02-03 | 15887 | -42
CO-R11.S06-PW-210 | Installation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 11]-[SW-6] | 6 | 2026-10-13 | 2026-10-19 | 2026-01-28 | 2026-02-03 | 15887 | -42
Fire Hydrant |  | 21 | 2027-04-18 | 2027-05-11 | 2026-02-04 | 2026-02-28 | 37872 | -213
CO-R11.S06-PW-140 | Excavation Works for Fire Hydrants of Potable Water Network-[Road 11]-[SW-6] | 7 | 2027-04-18 | 2027-04-25 | 2026-02-04 | 2026-02-11 | 5681 | -213
CO-R11.S06-PW-150 | Installation Works for Fire Hydrant of Potable Water Network-[Road 11]-[SW-6] | 7 | 2027-04-26 | 2027-05-03 | 2026-02-12 | 2026-02-19 | 24617 | -213
CO-R11.S06-PW-160 | Trench Backfilling and Compaction Works for Fire Hydrants of Potable Water Network-[Road 11]-[SW-6] | 7 | 2027-05-04 | 2027-05-11 | 2026-02-21 | 2026-02-28 | 7574 | -213
Street Lighting Network |  | 217 | 2026-10-13 | 2027-07-03 | 2026-05-19 | 2026-07-25 | 60090 | -232
Lighting Poles Works |  | 217 | 2026-10-13 | 2027-07-03 | 2026-06-24 | 2026-07-19 | 38090 | -232
CO-R11.S06-SL-210 | Backfilling Works for Lighting Poles of Street Lighting Network-[Road 11]-[SW-6] | 15 | 2026-10-13 | 2026-10-29 | 2026-06-24 | 2026-07-11 | 10659 | -37
CO-R11.S06-SL-200 | Testing Works for Lighting Poles of Street Lighting Network-[Road 11]-[SW-6] | 7 | 2026-10-31 | 2026-11-07 | 2026-07-12 | 2026-07-19 | 10659 | -37
CO-R11.S06-SL-130 | Installation Works for Lighting Fixtures With Drop Wire of Street Lighting Network-[Road 11]-[SW-6] | 18 | 2027-06-13 | 2027-07-03 | 2026-06-29 | 2026-07-19 | 16771 | -232
Cabling Works |  | 10 | 2026-10-13 | 2026-10-24 | 2026-05-19 | 2026-06-03 | 3989 | -72
CO-R11.S06-SL-160 | Trench Backfilling and Compaction Works for Street Lighting Network-[Road 11]-[SW-6] | 10 | 2026-10-13 | 2026-10-24 | 2026-05-19 | 2026-06-03 | 3989 | -72
Distrubution Panel Boards |  | 36 | 2027-04-15 | 2027-06-01 | 2026-06-14 | 2026-07-25 | 18011 | -251
CO-R11.S06-SL-170 | Foundation Excavation Works For Panel Boards of Street Lighting Network-[Road 11]-[SW-6] | 12 | 2027-04-15 | 2027-04-28 | 2026-06-14 | 2026-06-27 | 0 | -257
CO-R11.S06-SL-180 | Installation Works for Panel Board Concrete Foundations of Street Lighting Network-[Road 11]-[SW-6] | 12 | 2027-04-29 | 2027-05-12 | 2026-06-28 | 2026-07-11 | 0 | -257
CO-R11.S06-SL-190 | Installation Works for Lighting Panel Boards of Street Lighting Network-[Road 11]-[SW-6] | 12 | 2027-05-13 | 2027-06-01 | 2026-07-12 | 2026-07-25 | 0 | -257
CO-R11.S06-SL-220 | A wall of concrete blocks to install the KWH meter of Street Lighting Network-[Road 11]-[SW-6] | 12 | 2027-05-13 | 2027-06-01 | 2026-07-12 | 2026-07-25 | 18011 | -251
Telecom Network |  | 21 | 2027-04-08 | 2027-05-02 | 2026-07-07 | 2026-07-30 | 9401 | -210
Manholes Works |  | 21 | 2027-04-08 | 2027-05-02 | 2026-07-07 | 2026-07-30 | 9401 | -210
CO-R11.S06-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 11]-[SW-6] | 7 | 2027-04-08 | 2027-04-15 | 2026-07-07 | 2026-07-14 | 1257 | -210
CO-R11.S06-TE-150 | Installation Works for Manholes of Telecom Network-[Road 11]-[SW-6] | 7 | 2027-04-17 | 2027-04-24 | 2026-07-15 | 2026-07-22 | 6887 | -210
CO-R11.S06-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 11]-[SW-6] | 7 | 2027-04-25 | 2027-05-02 | 2026-07-23 | 2026-07-30 | 1257 | -210
Road 14 Local 1 ( 584 LM ) |  | 235 | 2026-10-13 | 2027-07-24 | 2025-08-02 | 2026-09-26 | 593791 | -208
SW_7 |  | 115 | 2026-10-13 | 2027-02-24 | 2025-08-02 | 2026-09-26 | 243091 | -91
Sewage Network |  | 1 | 2026-10-13 | 2026-10-13 | 2025-09-01 | 2025-09-01 | 6319 | -29
Manholes |  | 1 | 2026-10-13 | 2026-10-13 | 2025-09-01 | 2025-09-01 | 6319 | -29
CO-R14.S07-SW-210 | Testing Works for Main Line Manholes of Sewage Network-[Road 14]-[SW-7] | 1 | 2026-10-13 | 2026-10-13 | 2025-09-01 | 2025-09-01 | 6319 | -29
Street Lighting Network |  | 24 | 2026-10-13 | 2026-11-09 | 2025-08-02 | 2026-06-11 | 9399 | -69
Lighting Poles Works |  | 18 | 2026-10-13 | 2026-11-02 | 2026-05-18 | 2026-06-11 | 9399 | -63
CO-R14.S07-SL-130 | Installation Works for Lighting Fixtures With Drop Wire of Street Lighting Network-[Road 14]-[SW-7] | 18 | 2026-10-13 | 2026-11-02 | 2026-05-18 | 2026-06-11 | 7713 | -63
CO-R14.S07-SL-200 | Testing Works for Lighting Poles of Street Lighting Network-[Road 14]-[SW-7] | 5 | 2026-10-13 | 2026-10-18 | 2026-06-07 | 2026-06-11 | 1686 | -50
Distrubution Panel Boards |  | 24 | 2026-10-13 | 2026-11-09 | 2025-08-02 | 2025-08-28 | 0 | -73
CO-R14.S07-SL-170 | Foundation Excavation Works For Panel Boards of Street Lighting Network-[Road 14]-[SW-7] | 18 | 2026-10-13 | 2026-11-02 | 2025-08-02 | 2025-08-21 | 0 | -73
CO-R14.S07-SL-180 | Installation Works for Panel Board Concrete Foundations of Street Lighting Network-[Road 14]-[SW-7] | 18 | 2026-10-17 | 2026-11-05 | 2025-08-05 | 2025-08-25 | 0 | -73
CO-R14.S07-SL-220 | A wall of concrete blocks to install the KWH meter of Street Lighting Network-[Road 14]-[SW-7] | 18 | 2026-10-17 | 2026-11-05 | 2025-08-05 | 2025-08-25 | 0 | -70
CO-R14.S07-SL-190 | Installation Works for Lighting Panel Boards of Street Lighting Network-[Road 14]-[SW-7] | 18 | 2026-10-20 | 2026-11-09 | 2025-08-09 | 2025-08-28 | 0 | -73
Telecom Network |  | 24 | 2027-01-14 | 2027-02-10 | 2026-05-20 | 2026-07-30 | 69527 | -138
Ducts Works |  | 24 | 2027-01-14 | 2027-02-10 | 2026-05-20 | 2026-07-30 | 56984 | -138
CO-R14.S07-TE-100 | Trench Excavation and Bedding Works for Ducts of Telecom Network-[Road 14]-[SW-7] | 3 | 2027-01-14 | 2027-01-17 | 2026-05-20 | 2026-05-23 | 5595 | -145
CO-R14.S07-TE-110 | Pipes Laying Works for Ducts of Telecom Network-[Road 14]-[SW-7] | 7 | 2027-01-18 | 2027-01-25 | 2026-07-07 | 2026-07-14 | 34304 | -138
CO-R14.S07-TE-120 | Pouring Plain Concrete Above Ducts of Telecom Network-[Road 14]-[SW-7] | 7 | 2027-01-26 | 2027-02-02 | 2026-07-15 | 2026-07-22 | 5595 | -138
CO-R14.S07-TE-130 | Trench Backfilling and Compaction Works for Ducts of Telecom Network-[Road 14]-[SW-7] | 7 | 2027-02-03 | 2027-02-10 | 2026-07-23 | 2026-07-30 | 11491 | -138
Manholes Works |  | 21 | 2027-01-18 | 2027-02-10 | 2026-07-07 | 2026-07-30 | 12543 | -138
CO-R14.S07-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 14]-[SW-7] | 7 | 2027-01-18 | 2027-01-25 | 2026-07-07 | 2026-07-14 | 1885 | -145
CO-R14.S07-TE-150 | Installation Works for Manholes of Telecom Network-[Road 14]-[SW-7] | 7 | 2027-01-26 | 2027-02-02 | 2026-07-15 | 2026-07-22 | 8772 | -138
CO-R14.S07-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 14]-[SW-7] | 7 | 2027-02-03 | 2027-02-10 | 2026-07-23 | 2026-07-30 | 1885 | -138
Road Works |  | 18 | 2027-02-03 | 2027-02-24 | 2026-09-05 | 2026-09-26 | 157847 | -91
Pre-Bituminous Construction |  | 18 | 2027-02-03 | 2027-02-24 | 2026-09-05 | 2026-09-26 | 157847 | -91
CO-R14.S07-RD-P-110 | Aggregate Base Course Layer for Road Works-[Road 14]-[SW-7] | 18 | 2027-02-03 | 2027-02-24 | 2026-09-05 | 2026-09-26 | 157847 | -91
SW_8 |  | 235 | 2026-10-13 | 2027-07-24 | 2025-09-15 | 2026-09-22 | 350700 | -208
Sewage Network |  | 1 | 2026-10-13 | 2026-10-13 | 2025-09-15 | 2025-09-15 | 2342 | -41
Manholes |  | 1 | 2026-10-13 | 2026-10-13 | 2025-09-15 | 2025-09-15 | 2342 | -41
CO-R14.S08-SW-210 | Testing Works for Main Line Manholes of Sewage Network-[Road 14]-[SW-8] | 1 | 2026-10-13 | 2026-10-13 | 2025-09-15 | 2025-09-15 | 2342 | -41
Potable Water Network |  | 21 | 2026-10-13 | 2026-11-05 | 2026-02-26 | 2026-03-25 | 53020 | -12
Fire Hydrant |  | 21 | 2026-10-13 | 2026-11-05 | 2026-02-26 | 2026-03-25 | 53020 | -12
CO-R14.S08-PW-140 | Excavation Works for Fire Hydrants of Potable Water Network-[Road 14]-[SW-8] | 7 | 2026-10-13 | 2026-10-20 | 2026-02-26 | 2026-03-05 | 7953 | -12
CO-R14.S08-PW-150 | Installation Works for Fire Hydrant of Potable Water Network-[Road 14]-[SW-8] | 7 | 2026-10-21 | 2026-10-28 | 2026-03-07 | 2026-03-14 | 34463 | -12
CO-R14.S08-PW-160 | Trench Backfilling and Compaction Works for Fire Hydrants of Potable Water Network-[Road 14]-[SW-8] | 7 | 2026-10-29 | 2026-11-05 | 2026-03-15 | 2026-03-25 | 10604 | -12
Street Lighting Network |  | 235 | 2026-10-13 | 2027-07-24 | 2026-06-24 | 2026-08-15 | 67965 | -232
Lighting Poles Works |  | 235 | 2026-10-13 | 2027-07-24 | 2026-06-24 | 2026-08-09 | 41146 | -232
CO-R14.S08-SL-200 | Testing Works for Lighting Poles of Street Lighting Network-[Road 14]-[SW-8] | 7 | 2026-10-13 | 2026-10-20 | 2026-06-24 | 2026-07-01 | 15989 | -4
CO-R14.S08-SL-850 | Installation Works for Lighting Fixtures With Drop Wire of Street Lighting Network-[Road 14]-[SW-8] | 18 | 2027-07-04 | 2027-07-24 | 2026-07-20 | 2026-08-09 | 25157 | -232
Distrubution Panel Boards |  | 42 | 2027-04-29 | 2027-06-22 | 2026-06-28 | 2026-08-15 | 26818 | -257
CO-R14.S08-SL-DB-640 | Foundation Excavation Works For Panel Boards of Street Lighting Network-[Road 14]-[SW-8] | 18 | 2027-04-29 | 2027-05-25 | 2026-06-28 | 2026-07-18 | 0 | -243
CO-R14.S08-SL-DB-650 | Installation Works for Panel Board Concrete Foundations of Street Lighting Network-[Road 14]-[SW-8] | 18 | 2027-05-13 | 2027-06-08 | 2026-07-12 | 2026-08-01 | 0 | -252
CO-R14.S08-SL-220 | A wall of concrete blocks to install the KWH meter of Street Lighting Network-[Road 14]-[SW-8] | 25 | 2027-05-13 | 2027-06-16 | 2026-07-12 | 2026-08-09 | 26818 | -252
CO-R14.S08-SL-DB-660 | Installation Works for Lighting Panel Boards of Street Lighting Network-[Road 14]-[SW-8] | 18 | 2027-06-02 | 2027-06-22 | 2026-07-26 | 2026-08-15 | 0 | -257
Telecom Network |  | 93 | 2027-01-18 | 2027-05-10 | 2026-06-07 | 2026-08-08 | 69527 | -210
Ducts Works |  | 24 | 2027-01-18 | 2027-02-14 | 2026-06-07 | 2026-08-08 | 56984 | -141
CO-R14.S08-TE-100 | Trench Excavation and Bedding Works for Ducts of Telecom Network-[Road 14]-[SW-8] | 3 | 2027-01-18 | 2027-01-20 | 2026-06-07 | 2026-06-09 | 5595 | -141
CO-R14.S08-TE-110 | Pipes Laying Works for Ducts of Telecom Network-[Road 14]-[SW-8] | 7 | 2027-01-21 | 2027-01-28 | 2026-07-15 | 2026-07-22 | 34304 | -141
CO-R14.S08-TE-120 | Pouring Plain Concrete Above Ducts of Telecom Network-[Road 14]-[SW-8] | 7 | 2027-01-30 | 2027-02-06 | 2026-07-23 | 2026-07-30 | 5595 | -141
CO-R14.S08-TE-130 | Trench Backfilling and Compaction Works for Ducts of Telecom Network-[Road 14]-[SW-8] | 7 | 2027-02-07 | 2027-02-14 | 2026-08-01 | 2026-08-08 | 11491 | -141
Manholes Works |  | 21 | 2027-04-17 | 2027-05-10 | 2026-07-15 | 2026-08-08 | 12543 | -210
CO-R14.S08-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 14]-[SW-8] | 7 | 2027-04-17 | 2027-04-24 | 2026-07-15 | 2026-07-22 | 1885 | -210
CO-R14.S08-TE-150 | Installation Works for Manholes of Telecom Network-[Road 14]-[SW-8] | 7 | 2027-04-25 | 2027-05-02 | 2026-07-23 | 2026-07-30 | 8772 | -210
CO-R14.S08-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 14]-[SW-8] | 7 | 2027-05-03 | 2027-05-10 | 2026-08-01 | 2026-08-08 | 1885 | -210
Road Works |  | 18 | 2027-05-12 | 2027-06-07 | 2026-09-02 | 2026-09-22 | 157847 | -168
Pre-Bituminous Construction |  | 18 | 2027-05-12 | 2027-06-07 | 2026-09-02 | 2026-09-22 | 157847 | -168
CO-R14.S08-RD-P-110 | Aggregate Base Course Layer for Road Works-[Road 14]-[SW-8] | 18 | 2027-05-12 | 2027-06-07 | 2026-09-02 | 2026-09-22 | 157847 | -168
Road 15 Local 1 ( 556 LM ) |  | 113 | 2026-10-13 | 2027-02-21 | 2025-06-02 | 2026-03-31 | 74497 | -121
SW_10 |  | 113 | 2026-10-13 | 2027-02-21 | 2025-06-02 | 2026-03-31 | 74497 | -121
Sewage Network |  | 1 | 2026-10-13 | 2026-10-13 | 2025-07-05 | 2025-07-06 | 2883 | -27
Manholes |  | 1 | 2026-10-13 | 2026-10-13 | 2025-07-05 | 2025-07-06 | 2883 | -27
CO-R15.S10-SW-210 | Testing Works for Main Line Manholes of Sewage Network-[Road 15]-[SW-10] | 1 | 2026-10-13 | 2026-10-13 | 2025-07-05 | 2025-07-06 | 2883 | -27
Street Lighting Network |  | 113 | 2026-10-13 | 2027-02-21 | 2025-06-02 | 2026-02-02 | 41317 | -148
Lighting Poles Works |  | 113 | 2026-10-13 | 2027-02-21 | 2026-01-13 | 2026-02-02 | 24492 | -231
CO-R15.S10-SL-200 | Testing Works for Lighting Poles of Street Lighting Network-[Road 15]-[SW-10] | 5 | 2026-10-13 | 2026-10-18 | 2026-01-27 | 2026-02-02 | 9517 | -123
CO-R15.S10-SL-130 | Installation Works for Lighting Fixtures With Drop Wire of Street Lighting Network-[Road 15]-[SW-10] | 18 | 2027-02-01 | 2027-02-21 | 2026-01-13 | 2026-02-02 | 14975 | -231
Distrubution Panel Boards |  | 24 | 2026-10-13 | 2026-11-09 | 2025-06-02 | 2025-07-03 | 16825 | -59
CO-R15.S10-SL-170 | Foundation Excavation Works For Panel Boards of Street Lighting Network-[Road 15]-[SW-10] | 18 | 2026-10-13 | 2026-11-02 | 2025-06-02 | 2025-06-26 | 0 | -59
CO-R15.S10-SL-180 | Installation Works for Panel Board Concrete Foundations of Street Lighting Network-[Road 15]-[SW-10] | 18 | 2026-10-17 | 2026-11-05 | 2025-06-10 | 2025-06-30 | 0 | -59
CO-R15.S10-SL-220 | A wall of concrete blocks to install the KWH meter of Street Lighting Network-[Road 15]-[SW-10] | 18 | 2026-10-17 | 2026-11-05 | 2025-06-10 | 2025-06-30 | 16825 | -56
CO-R15.S10-SL-190 | Installation Works for Lighting Panel Boards of Street Lighting Network-[Road 15]-[SW-10] | 18 | 2026-10-20 | 2026-11-09 | 2025-06-14 | 2025-07-03 | 0 | -59
Potable Water Network |  | 18 | 2026-10-14 | 2026-11-03 | 2026-03-08 | 2026-03-31 | 30297 | -27
Fire Hydrant |  | 18 | 2026-10-14 | 2026-11-03 | 2026-03-08 | 2026-03-31 | 30297 | -27
CO-R15.S10-PW-140 | Excavation Works for Fire Hydrants of Potable Water Network-[Road 15]-[SW-10] | 6 | 2026-10-14 | 2026-10-20 | 2026-03-08 | 2026-03-14 | 4545 | -27
CO-R15.S10-PW-150 | Installation Works for Fire Hydrant of Potable Water Network-[Road 15]-[SW-10] | 6 | 2026-10-21 | 2026-10-27 | 2026-03-15 | 2026-03-24 | 19693 | -27
CO-R15.S10-PW-160 | Trench Backfilling and Compaction Works for Fire Hydrants of Potable Water Network-[Road 15]-[SW-10] | 6 | 2026-10-28 | 2026-11-03 | 2026-03-25 | 2026-03-31 | 6059 | -27
Road 16 Local 1 ( 527 LM ) |  | 25 | 2026-10-13 | 2026-11-10 | 2026-03-29 | 2026-04-18 | 30297 | -27
SW_12 |  | 25 | 2026-10-13 | 2026-11-10 | 2026-03-29 | 2026-04-18 | 30297 | -27
Potable Water Network |  | 25 | 2026-10-13 | 2026-11-10 | 2026-03-29 | 2026-04-18 | 30297 | -27
Fire Hydrant |  | 25 | 2026-10-13 | 2026-11-10 | 2026-03-29 | 2026-04-18 | 30297 | -27
CO-R16.S12-PW-140 | Excavation Works for Fire Hydrants of Potable Water Network-[Road 16]-[SW-12] | 6 | 2026-10-13 | 2026-10-19 | 2026-03-29 | 2026-04-04 | 4545 | -20
CO-R16.S12-PW-150 | Installation Works for Fire Hydrant of Potable Water Network-[Road 16]-[SW-12] | 6 | 2026-10-28 | 2026-11-03 | 2026-04-05 | 2026-04-11 | 19693 | -27
CO-R16.S12-PW-160 | Trench Backfilling and Compaction Works for Fire Hydrants of Potable Water Network-[Road 16]-[SW-12] | 6 | 2026-11-04 | 2026-11-10 | 2026-04-12 | 2026-04-18 | 6059 | -27
Road 17 Local 1 ( 500 LM ) |  | 61 | 2026-10-13 | 2026-12-22 | 2025-04-16 | 2026-09-01 | 102158 | -57
SW_14 |  | 61 | 2026-10-13 | 2026-12-22 | 2025-04-16 | 2026-09-01 | 102158 | -57
Sewage Network |  | 1 | 2026-10-13 | 2026-10-13 | 2025-05-21 | 2025-05-21 | 1518 | -15
Manholes |  | 1 | 2026-10-13 | 2026-10-13 | 2025-05-21 | 2025-05-21 | 1518 | -15
CO-R17.S14-SW-210 | Testing Works for Main Line Manholes of Sewage Network-[Road 17]-[SW-14] | 1 | 2026-10-13 | 2026-10-13 | 2025-05-21 | 2025-05-21 | 1518 | -15
Street Lighting Network |  | 61 | 2026-10-13 | 2026-12-22 | 2025-04-16 | 2025-12-14 | 71659 | -72
Lighting Poles Works |  | 61 | 2026-10-13 | 2026-12-22 | 2025-11-24 | 2025-12-14 | 44085 | -94
CO-R17.S14-SL-200 | Testing Works for Lighting Poles of Street Lighting Network-[Road 17]-[SW-14] | 5 | 2026-10-13 | 2026-10-18 | 2025-12-08 | 2025-12-14 | 17131 | -38
CO-R17.S14-SL-130 | Installation Works for Lighting Fixtures With Drop Wire of Street Lighting Network-[Road 17]-[SW-14] | 18 | 2026-12-02 | 2026-12-22 | 2025-11-24 | 2025-12-14 | 26954 | -94
Distrubution Panel Boards |  | 24 | 2026-10-13 | 2026-11-09 | 2025-04-16 | 2025-05-13 | 27573 | -35
CO-R17.S14-SL-170 | Foundation Excavation Works For Panel Boards of Street Lighting Network-[Road 17]-[SW-14] | 18 | 2026-10-13 | 2026-11-02 | 2025-04-16 | 2025-05-06 | 0 | -35
CO-R17.S14-SL-180 | Installation Works for Panel Board Concrete Foundations of Street Lighting Network-[Road 17]-[SW-14] | 18 | 2026-10-17 | 2026-11-05 | 2025-04-20 | 2025-05-10 | 0 | -35
CO-R17.S14-SL-220 | A wall of concrete blocks to install the KWH meter of Street Lighting Network-[Road 17]-[SW-14] | 18 | 2026-10-17 | 2026-11-05 | 2025-04-20 | 2025-05-10 | 27573 | -32
CO-R17.S14-SL-190 | Installation Works for Lighting Panel Boards of Street Lighting Network-[Road 17]-[SW-14] | 18 | 2026-10-20 | 2026-11-09 | 2025-04-23 | 2025-05-13 | 0 | -35
Potable Water Network |  | 30 | 2026-10-14 | 2026-11-17 | 2026-04-21 | 2026-05-11 | 22723 | -27
Fire Hydrant |  | 30 | 2026-10-14 | 2026-11-17 | 2026-04-21 | 2026-05-11 | 22723 | -27
CO-R17.S14-PW-140 | Excavation Works for Fire Hydrants of Potable Water Network-[Road 17]-[SW-14] | 6 | 2026-10-14 | 2026-10-20 | 2026-04-21 | 2026-04-27 | 3408 | -15
CO-R17.S14-PW-150 | Installation Works for Fire Hydrant of Potable Water Network-[Road 17]-[SW-14] | 6 | 2026-11-04 | 2026-11-10 | 2026-04-28 | 2026-05-04 | 14770 | -27
CO-R17.S14-PW-160 | Trench Backfilling and Compaction Works for Fire Hydrants of Potable Water Network-[Road 17]-[SW-14] | 6 | 2026-11-11 | 2026-11-17 | 2026-05-05 | 2026-05-11 | 4545 | -27
Telecom Network |  | 21 | 2026-10-13 | 2026-11-05 | 2026-08-09 | 2026-09-01 | 6258 | -55
Manholes Works |  | 21 | 2026-10-13 | 2026-11-05 | 2026-08-09 | 2026-09-01 | 6258 | -55
CO-R17.S14-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 17]-[SW-14] | 7 | 2026-10-13 | 2026-10-20 | 2026-08-09 | 2026-08-16 | 628 | -55
CO-R17.S14-TE-150 | Installation Works for Manholes of Telecom Network-[Road 17]-[SW-14] | 7 | 2026-10-21 | 2026-10-28 | 2026-08-17 | 2026-08-24 | 5002 | -55
CO-R17.S14-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 17]-[SW-14] | 7 | 2026-10-29 | 2026-11-05 | 2026-08-25 | 2026-09-01 | 628 | -55
Road 18 Local 1 ( 479 LM ) |  | 35 | 2026-10-13 | 2026-11-22 | 2025-03-19 | 2025-11-27 | 51658 | 31
SW_16 |  | 35 | 2026-10-13 | 2026-11-22 | 2025-03-19 | 2025-11-27 | 51658 | 31
Street Lighting Network |  | 35 | 2026-10-13 | 2026-11-22 | 2025-03-19 | 2025-11-27 | 36510 | -44
Lighting Poles Works |  | 35 | 2026-10-13 | 2026-11-22 | 2025-11-08 | 2025-11-27 | 20573 | -44
CO-R18.S16-SL-200 | Testing Works for Lighting Poles of Street Lighting Network-[Road 18]-[SW-16] | 5 | 2026-10-13 | 2026-10-18 | 2025-11-22 | 2025-11-27 | 7995 | -14
CO-R18.S16-SL-130 | Installation Works for Lighting Fixtures With Drop Wire of Street Lighting Network-[Road 18]-[SW-16] | 18 | 2026-11-02 | 2026-11-22 | 2025-11-08 | 2025-11-27 | 12579 | -44
Distrubution Panel Boards |  | 24 | 2026-10-13 | 2026-11-09 | 2025-03-19 | 2025-04-20 | 15936 | -35
CO-R18.S16-SL-170 | Foundation Excavation Works For Panel Boards of Street Lighting Network-[Road 18]-[SW-16] | 18 | 2026-10-13 | 2026-11-02 | 2025-03-19 | 2025-04-13 | 0 | -35
CO-R18.S16-SL-180 | Installation Works for Panel Board Concrete Foundations of Street Lighting Network-[Road 18]-[SW-16] | 18 | 2026-10-17 | 2026-11-05 | 2025-03-23 | 2025-04-16 | 0 | -35
CO-R18.S16-SL-220 | A wall of concrete blocks to install the KWH meter of Street Lighting Network-[Road 18]-[SW-16] | 18 | 2026-10-17 | 2026-11-05 | 2025-03-23 | 2025-04-16 | 15936 | -32
CO-R18.S16-SL-190 | Installation Works for Lighting Panel Boards of Street Lighting Network-[Road 18]-[SW-16] | 18 | 2026-10-20 | 2026-11-09 | 2025-03-26 | 2025-04-20 | 0 | -35
Potable Water Network |  | 18 | 2026-10-13 | 2026-11-02 | 2025-08-23 | 2025-09-11 | 15149 | 48
Fire Hydrant |  | 18 | 2026-10-13 | 2026-11-02 | 2025-08-23 | 2025-09-11 | 15149 | 48
CO-R18.S16-PW-250 | Excavation Works for Fire Hydrants of Potable Water Network-[Road 18]-[SW-16] | 6 | 2026-10-13 | 2026-10-19 | 2025-08-23 | 2025-08-28 | 2272 | 48
CO-R18.S16-PW-260 | Installation Works for Fire Hydrant of Potable Water Network-[Road 18]-[SW-16] | 6 | 2026-10-20 | 2026-10-26 | 2025-08-30 | 2025-09-04 | 9847 | 48
CO-R18.S16-PW-270 | Trench Backfilling and Compaction Works for Fire Hydrants of Potable Water Network-[Road 18]-[SW-16] | 6 | 2026-10-27 | 2026-11-02 | 2025-09-06 | 2025-09-11 | 3030 | 48
Finishes for Infrastructure Networks |  | 304 | 2026-10-13 | 2027-10-13 | 2026-05-04 | 2026-10-26 | 6070630 | -264
Phase 2 Block "J" |  | 304 | 2026-10-13 | 2027-10-13 | 2026-05-04 | 2026-10-26 | 6070630 | -264
Road 09 Local 2 ( 2278 LM ) |  | 201 | 2027-02-10 | 2027-10-13 | 2026-06-02 | 2026-10-26 | 2423500 | -283
Sewage Network |  | 15 | 2027-06-12 | 2027-06-28 | 2026-08-02 | 2026-08-18 | 81103 | -220
Testing and Finishes |  | 15 | 2027-06-12 | 2027-06-28 | 2026-08-02 | 2026-08-18 | 81103 | -220
CO-R09-SW-TF-110 | Install Manhole Cover Works for External Finishes of Sewage Network-[Road 09] | 12 | 2027-06-12 | 2027-06-24 | 2026-08-02 | 2026-08-15 | 40552 | -220
CO-R09-SW-TF-120 | Main Manhole Internal Finishes (Benching + Insulation) of Sewage Network-[Road 09] | 12 | 2027-06-15 | 2027-06-28 | 2026-08-05 | 2026-08-18 | 40552 | -220
Potable Water Network |  | 33 | 2027-06-17 | 2027-07-25 | 2026-08-02 | 2026-09-08 | 39232 | -243
Testing and Finishes |  | 33 | 2027-06-17 | 2027-07-25 | 2026-08-02 | 2026-09-08 | 39232 | -243
CO-R09-PW-TF-110 | Testing Work for Main Line of Potable Water Network-[Road 09] | 9 | 2027-06-17 | 2027-06-27 | 2026-08-02 | 2026-08-11 | 39232 | -264
CO-R09-PW-TF-100 | Final Finishes works and Covers for Valves and Valve Chambers of Potable Water Network-[Road 09] | 12 | 2027-06-28 | 2027-07-11 | 2026-08-12 | 2026-08-25 | 0 | -243
CO-R09-PW-TF-120 | Fire Hydrant Finishies (S.Box + Safety + Marker Post ) of Potable Water Network-[Road 09] | 12 | 2027-07-12 | 2027-07-25 | 2026-08-26 | 2026-09-08 | 0 | -243
Irrigation Network |  | 16 | 2027-06-08 | 2027-06-26 | 2026-07-29 | 2026-08-16 | 21307 | -218
Testing and Finishes |  | 16 | 2027-06-08 | 2027-06-26 | 2026-07-29 | 2026-08-16 | 21307 | -218
CO-R09-IR-TF-100 | Final Testing (pressure tests) of Irrigation Network-[Road 09] | 16 | 2027-06-08 | 2027-06-26 | 2026-07-29 | 2026-08-16 | 21307 | -218
Street Lighting Network |  | 86 | 2027-06-03 | 2027-09-11 | 2026-06-02 | 2026-09-09 | 189757 | -276
Termination and Testing Works |  | 84 | 2027-06-03 | 2027-09-08 | 2026-06-02 | 2026-09-07 | 177971 | -274
CO-R09-SL-TF-100 | Termination Works For Lighting Poles Cables of Street Lighting Network-[Road 09] | 12 | 2027-06-03 | 2027-06-16 | 2026-06-02 | 2026-06-15 | 80959 | -284
CO-R09-SL-TF-110 | Termination Works For Panel Board Cables of Street Lighting Network-[Road 09] | 11 | 2027-08-16 | 2027-08-28 | 2026-08-15 | 2026-08-26 | 64675 | -284
CO-R09-SL-TF-380 | Testing Works For Panel Board Cables of Street Lighting Network-[Road 09] | 10 | 2027-08-28 | 2027-09-08 | 2026-08-26 | 2026-09-07 | 32337 | -274
Earthing System Works |  | 74 | 2027-06-17 | 2027-09-11 | 2026-06-16 | 2026-09-09 | 11785 | -284
CO-R09-SL-ES-100 | Install Earthing System Works for Lighting Poles of Street Lighting Network-[Road 09] | 12 | 2027-06-17 | 2027-06-30 | 2026-06-16 | 2026-06-29 | 6125 | -284
CO-R09-SL-ES-110 | Install Earthing System Works for Lighting Panel Boards of Street Lighting Network-[Road 09] | 12 | 2027-08-28 | 2027-09-11 | 2026-08-26 | 2026-09-09 | 5660 | -284
Medium Voltage Network |  | 16 | 2027-02-10 | 2027-03-01 | 2026-06-21 | 2026-07-08 | 0 | -126
Termination and Testing Works |  | 16 | 2027-02-10 | 2027-03-01 | 2026-06-21 | 2026-07-08 | 0 | -126
CO-R09-MV-TF-100 | Termination Works of Medium Voltage Network-[Road 09] | 16 | 2027-02-10 | 2027-03-01 | 2026-06-21 | 2026-07-08 | 0 | -126
Road Works |  | 27 | 2027-09-11 | 2027-10-13 | 2026-09-24 | 2026-10-26 | 2092101 | -283
Bituminous Construction |  | 21 | 2027-09-11 | 2027-10-06 | 2026-09-24 | 2026-10-26 | 2058508 | -277
CO-R09-S1-RD-F-100 | Application of Prime Coat Layer for Road Works - S.W 01-[Road 09] | 12 | 2027-09-11 | 2027-09-26 | 2026-09-24 | 2026-10-08 | 576152 | -284
CO-R09-S2-RD-F-110 | Application of Prime Coat Layer for Road Works- S.W 02-[Road 09] | 18 | 2027-09-11 | 2027-10-03 | 2026-10-01 | 2026-10-22 | 576152 | -277
CO-R09-S1-RD-F-120 | Bituminous Base & Wearing Courses Layers for Road Works- S.W 01-[Road 09] | 12 | 2027-09-14 | 2027-09-29 | 2026-09-28 | 2026-10-12 | 453102 | -284
CO-R09-S2-RD-F-130 | Bituminous Base & Wearing Courses Layers for Road Works- S.W 02-[Road 09] | 18 | 2027-09-14 | 2027-10-06 | 2026-10-05 | 2026-10-26 | 453102 | -277
Traffic Signs Boards and Roads Marking |  | 12 | 2027-09-29 | 2027-10-13 | 2026-10-12 | 2026-10-26 | 33593 | -284
CO-R09-S1-RD-F-140 | Application of Road Marking Works For Road Works- S.W 01-[Road 09] | 12 | 2027-09-29 | 2027-10-13 | 2026-10-12 | 2026-10-26 | 33593 | -284
Road 10 Local 2 ( 2352 LM ) |  | 237 | 2026-10-13 | 2027-07-26 | 2026-05-04 | 2026-10-17 | 2808873 | -233
Sewage Network |  | 27 | 2027-04-28 | 2027-06-03 | 2026-07-29 | 2026-08-29 | 153798 | -229
Testing and Finishes |  | 27 | 2027-04-28 | 2027-06-03 | 2026-07-29 | 2026-08-29 | 153798 | -229
CO-R10-SW-TF-100 | Final Testing For Main Line of Sewage Network-[Road 10] | 12 | 2027-04-28 | 2027-05-11 | 2026-07-29 | 2026-08-11 | 115643 | -229
CO-R10-SW-TF-110 | Install Manhole Cover Works for External Finishes of Sewage Network-[Road 10] | 12 | 2027-05-12 | 2027-05-31 | 2026-08-12 | 2026-08-25 | 19078 | -229
CO-R10-SW-TF-130 | Main Manhole Internal Finishes (Benching + Insulation) of Sewage Network-[Road 10] | 12 | 2027-05-22 | 2027-06-03 | 2026-08-16 | 2026-08-29 | 19078 | -229
Potable Water Network |  | 97 | 2027-03-15 | 2027-07-11 | 2026-08-08 | 2026-09-03 | 299945 | -252
Testing and Finishes |  | 97 | 2027-03-15 | 2027-07-11 | 2026-08-08 | 2026-09-03 | 299945 | -252
CO-R10-PW-TF-100 | Final Finishes works and Covers for Valves and Valve Chambers of Potable Water Network-[Road 10] | 12 | 2027-03-15 | 2027-03-28 | 2026-08-08 | 2026-08-20 | 0 | -179
CO-R10-PW-TF-120 | Fire Hydrant Finishies (S.Box + Safety + Marker Post ) of Potable Water Network-[Road 10] | 12 | 2027-03-29 | 2027-04-11 | 2026-08-22 | 2026-09-03 | 0 | -179
CO-R10-PW-TF-110 | Testing Work for Main Line of Potable Water Network-[Road 10] | 12 | 2027-06-28 | 2027-07-11 | 2026-08-12 | 2026-08-25 | 299945 | -264
Irrigation Network |  | 10 | 2027-05-09 | 2027-05-25 | 2026-08-09 | 2026-08-19 | 100763 | -220
Testing and Finishes |  | 10 | 2027-05-09 | 2027-05-25 | 2026-08-09 | 2026-08-19 | 100763 | -220
CO-R10-IR-TF-120 | Final Testing (pressure tests) of Irrigation Network-[Road 10] | 10 | 2027-05-09 | 2027-05-25 | 2026-08-09 | 2026-08-19 | 100763 | -220
Street Lighting Network |  | 62 | 2027-03-15 | 2027-05-31 | 2026-05-04 | 2026-07-23 | 190052 | -228
Termination and Testing Works |  | 62 | 2027-03-15 | 2027-05-31 | 2026-05-04 | 2026-07-23 | 178267 | -228
CO-R10-SL-TF-140 | Termination Works For Lighting Poles Cables of Street Lighting Network-[Road 10] | 12 | 2027-03-15 | 2027-03-28 | 2026-05-04 | 2026-05-17 | 81254 | -245
CO-R10-SL-TF-150 | Termination Works For Panel Board Cables of Street Lighting Network-[Road 10] | 12 | 2027-05-10 | 2027-05-29 | 2026-07-08 | 2026-07-21 | 64675 | -248
CO-R10-SL-TF-380 | Testing Works For Panel Board Cables of Street Lighting Network-[Road 10] | 2 | 2027-05-30 | 2027-05-31 | 2026-07-22 | 2026-07-23 | 32337 | -228
Earthing System Works |  | 27 | 2027-03-29 | 2027-04-28 | 2026-05-18 | 2026-06-22 | 11785 | -245
CO-R10-SL-ES-140 | Install Earthing System Works for Lighting Poles of Street Lighting Network-[Road 10] | 12 | 2027-03-29 | 2027-04-11 | 2026-05-18 | 2026-06-04 | 6125 | -245
CO-R10-SL-ES-150 | Install Earthing System Works for Lighting Panel Boards of Street Lighting Network-[Road 10] | 12 | 2027-04-15 | 2027-04-28 | 2026-06-09 | 2026-06-22 | 5660 | -245
Medium Voltage Network |  | 7 | 2026-10-13 | 2026-10-20 | 2026-09-09 | 2026-09-16 | 0 | -28
Termination and Testing Works |  | 7 | 2026-10-13 | 2026-10-20 | 2026-09-09 | 2026-09-16 | 0 | -28
CO-R10-MV-TF-140 | Termination Works of Medium Voltage Network-[Road 10] | 7 | 2026-10-13 | 2026-10-20 | 2026-09-09 | 2026-09-16 | 0 | -28
Road Works |  | 13 | 2027-07-12 | 2027-07-26 | 2026-09-30 | 2026-10-17 | 2064315 | -233
Bituminous Construction |  | 13 | 2027-07-12 | 2027-07-26 | 2026-09-30 | 2026-10-17 | 2064315 | -233
CO-R10-S03-RD-F-110 | Application of Prime Coat Layer for Road Works- S.W 05-[Road 10] | 10 | 2027-07-12 | 2027-07-22 | 2026-09-30 | 2026-10-11 | 577777 | -235
CO-R10-S04-RD-F-140 | Application of Prime Coat Layer for Road Works- S.W 06-[Road 10] | 10 | 2027-07-12 | 2027-07-22 | 2026-10-03 | 2026-10-13 | 577777 | -233
CO-R10-S03-RD-F-120 | Bituminous Base & Wearing Courses Layers for Road Works- S.W 05-[Road 10] | 10 | 2027-07-15 | 2027-07-26 | 2026-10-04 | 2026-10-14 | 454381 | -235
CO-R10-S04-RD-F-150 | Bituminous Base & Wearing Courses Layers for Road Works- S.W 06-[Road 10] | 10 | 2027-07-15 | 2027-07-26 | 2026-10-06 | 2026-10-17 | 454381 | -233
Road 11 Local 1 ( 670 LM ) |  | 167 | 2027-01-12 | 2027-08-04 | 2026-05-18 | 2026-09-26 | 252027 | -259
Sewage Network |  | 27 | 2027-05-12 | 2027-06-17 | 2026-08-12 | 2026-09-12 | 210240 | -229
Testing and Finishes |  | 27 | 2027-05-12 | 2027-06-17 | 2026-08-12 | 2026-09-12 | 210240 | -229
CO-R11-SW-TF-100 | Final Testing For Main Line of Sewage Network-[Road 11] | 12 | 2027-05-12 | 2027-05-31 | 2026-08-12 | 2026-08-25 | 181391 | -229
CO-R11-SW-TF-110 | Install Manhole Cover Works for External Finishes of Sewage Network-[Road 11] | 12 | 2027-06-01 | 2027-06-14 | 2026-08-26 | 2026-09-08 | 14425 | -229
CO-R11-SW-TF-130 | Main Manhole Internal Finishes (Benching + Insulation) of Sewage Network-[Road 11] | 12 | 2027-06-05 | 2027-06-17 | 2026-08-30 | 2026-09-12 | 14425 | -229
Potable Water Network |  | 97 | 2027-03-29 | 2027-07-25 | 2026-08-26 | 2026-09-22 | 11619 | -252
Testing and Finishes |  | 97 | 2027-03-29 | 2027-07-25 | 2026-08-26 | 2026-09-22 | 11619 | -252
CO-R11-PW-TF-100 | Final Finishes works and Covers for Valves and Valve Chambers of Potable Water Network-[Road 11] | 12 | 2027-03-29 | 2027-04-11 | 2026-08-26 | 2026-09-08 | 0 | -179
CO-R11-PW-TF-120 | Fire Hydrant Finishies (S.Box + Safety + Marker Post ) of Potable Water Network-[Road 11] | 12 | 2027-04-12 | 2027-04-25 | 2026-09-09 | 2026-09-22 | 0 | -179
CO-R11-PW-TF-110 | Testing Work for Main Line of Potable Water Network-[Road 11] | 12 | 2027-07-12 | 2027-07-25 | 2026-08-26 | 2026-09-08 | 11619 | -264
Irrigation Network |  | 10 | 2027-05-26 | 2027-06-06 | 2026-08-23 | 2026-09-02 | 6235 | -220
Testing and Finishes |  | 10 | 2027-05-26 | 2027-06-06 | 2026-08-23 | 2026-09-02 | 6235 | -220
CO-R11-IR-TF-130 | Final Testing (pressure tests) of Irrigation Network-[Road 11] | 10 | 2027-05-26 | 2027-06-06 | 2026-08-23 | 2026-09-02 | 6235 | -220
Street Lighting Network |  | 40 | 2027-06-20 | 2027-08-04 | 2026-05-18 | 2026-08-10 | 23933 | -282
Termination and Testing Works |  | 40 | 2027-06-20 | 2027-08-04 | 2026-05-18 | 2026-08-10 | 23933 | -282
CO-R11-SL-TF-160 | Termination Works For Lighting Poles Cables of Street Lighting Network-[Road 11] | 12 | 2027-06-20 | 2027-07-03 | 2026-05-18 | 2026-06-04 | 23933 | -262
CO-R11-SL-TF-170 | Termination Works For Panel Board Cables of Street Lighting Network-[Road 11] | 12 | 2027-07-20 | 2027-08-02 | 2026-07-26 | 2026-08-08 | 0 | -292
CO-R11-SL-TF-380 | Testing Works For Panel Board Cables of Street Lighting Network-[Road 11] | 2 | 2027-08-03 | 2027-08-04 | 2026-08-09 | 2026-08-10 | 0 | -282
Medium Voltage Network |  | 7 | 2027-01-12 | 2027-01-19 | 2026-09-17 | 2026-09-26 | 0 | -99
Termination and Testing Works |  | 7 | 2027-01-12 | 2027-01-19 | 2026-09-17 | 2026-09-26 | 0 | -99
CO-R11-MV-TF-160 | Termination Works of Medium Voltage Network-[Road 11] | 7 | 2027-01-12 | 2027-01-19 | 2026-09-17 | 2026-09-26 | 0 | -99
Road 14 Local 1 ( 584 LM ) |  | 172 | 2027-01-20 | 2027-08-18 | 2026-06-13 | 2026-10-07 | 152149 | -261
Sewage Network |  | 27 | 2027-06-01 | 2027-07-01 | 2026-08-26 | 2026-09-27 | 48450 | -229
Testing and Finishes |  | 27 | 2027-06-01 | 2027-07-01 | 2026-08-26 | 2026-09-27 | 48450 | -229
CO-R14-SW-TF-100 | Final Testing For Main Line of Sewage Network-[Road 14] | 12 | 2027-06-01 | 2027-06-14 | 2026-08-26 | 2026-09-08 | 31128 | -229
CO-R14-SW-TF-110 | Install Manhole Cover Works for External Finishes of Sewage Network-[Road 14] | 12 | 2027-06-15 | 2027-06-28 | 2026-09-09 | 2026-09-22 | 8661 | -229
CO-R14-SW-TF-130 | Main Manhole Internal Finishes (Benching + Insulation) of Sewage Network-[Road 14] | 12 | 2027-06-19 | 2027-07-01 | 2026-09-13 | 2026-09-27 | 8661 | -229
Potable Water Network |  | 97 | 2027-04-12 | 2027-08-08 | 2026-09-09 | 2026-10-07 | 44448 | -252
Testing and Finishes |  | 97 | 2027-04-12 | 2027-08-08 | 2026-09-09 | 2026-10-07 | 44448 | -252
CO-R14-PW-TF-100 | Final Finishes works and Covers for Valves and Valve Chambers of Potable Water Network-[Road 14] | 12 | 2027-04-12 | 2027-04-25 | 2026-09-09 | 2026-09-22 | 0 | -179
CO-R14-PW-TF-120 | Fire Hydrant Finishies (S.Box + Safety + Marker Post ) of Potable Water Network-[Road 14] | 12 | 2027-04-26 | 2027-05-09 | 2026-09-24 | 2026-10-07 | 0 | -179
CO-R14-PW-TF-110 | Testing Work for Main Line of Potable Water Network-[Road 14] | 12 | 2027-07-26 | 2027-08-08 | 2026-09-09 | 2026-09-22 | 44448 | -264
Irrigation Network |  | 10 | 2027-06-07 | 2027-06-17 | 2026-09-03 | 2026-09-14 | 24385 | -220
Testing and Finishes |  | 10 | 2027-06-07 | 2027-06-17 | 2026-09-03 | 2026-09-14 | 24385 | -220
CO-R11-IR-TF-140 | Final Testing (pressure tests) of Irrigation Network-[Road 14] | 10 | 2027-06-07 | 2027-06-17 | 2026-09-03 | 2026-09-14 | 24385 | -220
Street Lighting Network |  | 40 | 2027-07-04 | 2027-08-18 | 2026-06-13 | 2026-08-31 | 34865 | -290
Termination and Testing Works |  | 40 | 2027-07-04 | 2027-08-18 | 2026-06-13 | 2026-08-31 | 34865 | -290
CO-R11-SL-TF-180 | Termination Works For Lighting Poles Cables of Street Lighting Network-[Road 14] | 12 | 2027-07-04 | 2027-07-17 | 2026-06-13 | 2026-06-25 | 34865 | -262
CO-R11-SL-TF-190 | Termination Works For Panel Board Cables of Street Lighting Network-[Road 14] | 12 | 2027-08-03 | 2027-08-16 | 2026-08-16 | 2026-08-29 | 0 | -292
CO-R14-SL-TF-380 | Testing Works For Panel Board Cables of Street Lighting Network-[Road 14] | 2 | 2027-08-17 | 2027-08-18 | 2026-08-30 | 2026-08-31 | 0 | -292
Medium Voltage Network |  | 7 | 2027-01-20 | 2027-01-27 | 2026-09-27 | 2026-10-04 | 0 | -99
Termination and Testing Works |  | 7 | 2027-01-20 | 2027-01-27 | 2026-09-27 | 2026-10-04 | 0 | -99
CO-R11-MV-TF-180 | Termination Works of Medium Voltage Network-[Road 14] | 7 | 2027-01-20 | 2027-01-27 | 2026-09-27 | 2026-10-04 | 0 | -99
Road 15 Local 1 ( 556 LM ) |  | 232 | 2026-12-14 | 2027-09-20 | 2026-06-27 | 2026-10-21 | 86925 | -277
Sewage Network |  | 27 | 2027-06-15 | 2027-07-15 | 2026-09-09 | 2026-10-11 | 44915 | -229
Testing and Finishes |  | 27 | 2027-06-15 | 2027-07-15 | 2026-09-09 | 2026-10-11 | 44915 | -229
CO-R15-SW-TF-100 | Final Testing For Main Line of Sewage Network-[Road 15] | 12 | 2027-06-15 | 2027-06-28 | 2026-09-09 | 2026-09-22 | 20768 | -229
CO-R15-SW-TF-110 | Install Manhole Cover Works for External Finishes of Sewage Network-[Road 15] | 12 | 2027-06-29 | 2027-07-12 | 2026-09-24 | 2026-10-07 | 12073 | -229
CO-R15-SW-TF-130 | Main Manhole Internal Finishes (Benching + Insulation) of Sewage Network-[Road 15] | 12 | 2027-07-03 | 2027-07-15 | 2026-09-28 | 2026-10-11 | 12073 | -229
Storm Drainage Network |  | 12 | 2026-12-14 | 2026-12-27 | 2026-09-20 | 2026-10-04 | 6827 | -57
Testing and Finishes |  | 12 | 2026-12-14 | 2026-12-27 | 2026-09-20 | 2026-10-04 | 6827 | -57
CO-R15-SD-TF-110 | Install Catch Basin Cover Works for External Finishes of Storm Drainage Network-[Road 15] | 12 | 2026-12-14 | 2026-12-27 | 2026-09-20 | 2026-10-04 | 6827 | -57
Potable Water Network |  | 97 | 2027-04-26 | 2027-08-22 | 2026-09-24 | 2026-10-21 | 9843 | -252
Testing and Finishes |  | 97 | 2027-04-26 | 2027-08-22 | 2026-09-24 | 2026-10-21 | 9843 | -252
CO-R15-PW-TF-100 | Final Finishes works and Covers for Valves and Valve Chambers of Potable Water Network-[Road 15] | 12 | 2027-04-26 | 2027-05-09 | 2026-09-24 | 2026-10-07 | 0 | -179
CO-R15-PW-TF-120 | Fire Hydrant Finishies (S.Box + Safety + Marker Post ) of Potable Water Network-[Road 15] | 12 | 2027-05-10 | 2027-05-29 | 2026-10-08 | 2026-10-21 | 0 | -179
CO-R15-PW-TF-110 | Testing Work for Main Line of Potable Water Network-[Road 15] | 12 | 2027-08-09 | 2027-08-22 | 2026-09-24 | 2026-10-07 | 9843 | -264
Irrigation Network |  | 10 | 2027-06-19 | 2027-06-29 | 2026-09-15 | 2026-09-27 | 5248 | -220
Testing and Finishes |  | 10 | 2027-06-19 | 2027-06-29 | 2026-09-15 | 2026-09-27 | 5248 | -220
CO-R15-IR-TF-150 | Final Testing (pressure tests) of Irrigation Network-[Road 15] | 10 | 2027-06-19 | 2027-06-29 | 2026-09-15 | 2026-09-27 | 5248 | -220
Street Lighting Network |  | 56 | 2027-07-18 | 2027-09-20 | 2026-06-27 | 2026-10-04 | 20092 | -286
Termination and Testing Works |  | 56 | 2027-07-18 | 2027-09-20 | 2026-06-27 | 2026-10-04 | 20092 | -286
CO-R15-SL-TF-200 | Termination Works For Lighting Poles Cables of Street Lighting Network-[Road 15] | 12 | 2027-07-18 | 2027-07-31 | 2026-06-27 | 2026-07-09 | 20092 | -262
CO-R15-SL-TF-210 | Termination Works For Panel Board Cables of Street Lighting Network-[Road 15] | 12 | 2027-08-19 | 2027-09-01 | 2026-09-01 | 2026-09-14 | 0 | -292
CO-R15-SL-TF-380 | Testing Works For Panel Board Cables of Street Lighting Network-[Road 15] | 16 | 2027-09-02 | 2027-09-20 | 2026-09-15 | 2026-10-04 | 0 | -286
Medium Voltage Network |  | 7 | 2027-01-28 | 2027-02-04 | 2026-10-05 | 2026-10-12 | 0 | -99
Termination and Testing Works |  | 7 | 2027-01-28 | 2027-02-04 | 2026-10-05 | 2026-10-12 | 0 | -99
CO-R15-MV-TF-200 | Termination Works of Medium Voltage Network-[Road 15] | 7 | 2027-01-28 | 2027-02-04 | 2026-10-05 | 2026-10-12 | 0 | -99
Road 16 Local 1 ( 527 LM ) |  | 264 | 2026-11-09 | 2027-09-22 | 2026-07-11 | 2026-10-25 | 134280 | -263
Sewage Network |  | 27 | 2027-06-29 | 2027-07-29 | 2026-09-24 | 2026-10-25 | 28933 | -229
Testing and Finishes |  | 27 | 2027-06-29 | 2027-07-29 | 2026-09-24 | 2026-10-25 | 28933 | -229
CO-R16-SW-TF-100 | Final Testing For Main Line of Sewage Network-[Road 16] | 12 | 2027-06-29 | 2027-07-12 | 2026-09-24 | 2026-10-07 | 14883 | -229
CO-R16-SW-TF-110 | Install Manhole Cover Works for External Finishes of Sewage Network-[Road 16] | 12 | 2027-07-13 | 2027-07-26 | 2026-10-08 | 2026-10-21 | 7025 | -229
CO-R16-SW-TF-130 | Main Manhole Internal Finishes (Benching + Insulation) of Sewage Network-[Road 16] | 12 | 2027-07-17 | 2027-07-29 | 2026-10-12 | 2026-10-25 | 7025 | -229
Storm Drainage Network |  | 54 | 2026-11-09 | 2027-01-10 | 2026-09-10 | 2026-10-18 | 71979 | -53
Testing and Finishes |  | 54 | 2026-11-09 | 2027-01-10 | 2026-09-10 | 2026-10-18 | 71979 | -53
CO-R16-SD-TF-100 | Testing Work for Pipes of Storm Drainage Network-[Road 16] | 16 | 2026-11-09 | 2026-11-26 | 2026-09-10 | 2026-09-29 | 65472 | -15
CO-R16-SD-TF-110 | Install Catch Basin Cover Works for External Finishes of Storm Drainage Network-[Road 16] | 12 | 2026-12-28 | 2027-01-10 | 2026-10-05 | 2026-10-18 | 6507 | -53
Potable Water Network |  | 97 | 2027-05-10 | 2027-09-05 | 2026-10-08 | 2026-10-21 | 9456 | -264
Testing and Finishes |  | 97 | 2027-05-10 | 2027-09-05 | 2026-10-08 | 2026-10-21 | 9456 | -264
CO-R16-PW-TF-100 | Final Finishes works and Covers for Valves and Valve Chambers of Potable Water Network-[Road 16] | 12 | 2027-05-10 | 2027-05-29 | 2026-10-08 | 2026-10-21 | 0 | -179
CO-R16-PW-TF-110 | Testing Work for Main Line of Potable Water Network-[Road 16] | 12 | 2027-08-23 | 2027-09-05 | 2026-10-08 | 2026-10-21 | 9456 | -264
Irrigation Network |  | 10 | 2027-06-30 | 2027-07-11 | 2026-09-28 | 2026-10-08 | 5002 | -220
Testing and Finishes |  | 10 | 2027-06-30 | 2027-07-11 | 2026-09-28 | 2026-10-08 | 5002 | -220
CO-R16-IR-TF-160 | Final Testing (pressure tests) of Irrigation Network-[Road 16] | 10 | 2027-06-30 | 2027-07-11 | 2026-09-28 | 2026-10-08 | 5002 | -220
Street Lighting Network |  | 46 | 2027-08-01 | 2027-09-22 | 2026-07-11 | 2026-10-06 | 18910 | -286
Termination and Testing Works |  | 46 | 2027-08-01 | 2027-09-22 | 2026-07-11 | 2026-10-06 | 18910 | -286
CO-R16-SL-TF-220 | Termination Works For Lighting Poles Cables of Street Lighting Network-[Road 16] | 12 | 2027-08-01 | 2027-08-14 | 2026-07-11 | 2026-07-23 | 18910 | -262
CO-R16-SL-TF-230 | Termination Works For Panel Board Cables of Street Lighting Network-[Road 16] | 12 | 2027-09-02 | 2027-09-15 | 2026-09-15 | 2026-09-29 | 0 | -292
CO-R16-SL-TF-380 | Testing Works For Panel Board Cables of Street Lighting Network-[Road 16] | 2 | 2027-09-21 | 2027-09-22 | 2026-10-05 | 2026-10-06 | 0 | -286
Road 17 Local 1 ( 500 LM ) |  | 254 | 2026-11-28 | 2027-09-30 | 2026-07-25 | 2026-10-21 | 85841 | -253
Sewage Network |  | 12 | 2027-07-13 | 2027-07-26 | 2026-10-08 | 2026-10-21 | 15595 | -229
Testing and Finishes |  | 12 | 2027-07-13 | 2027-07-26 | 2026-10-08 | 2026-10-21 | 15595 | -229
CO-R17-SW-TF-100 | Final Testing For Main Line of Sewage Network-[Road 17] | 12 | 2027-07-13 | 2027-07-26 | 2026-10-08 | 2026-10-21 | 15595 | -229
Storm Drainage Network |  | 16 | 2026-11-28 | 2026-12-15 | 2026-10-04 | 2026-10-21 | 52222 | -15
Testing and Finishes |  | 16 | 2026-11-28 | 2026-12-15 | 2026-10-04 | 2026-10-21 | 52222 | -15
CO-R17-SD-TF-100 | Testing Work for Pipes of Storm Drainage Network-[Road 17] | 16 | 2026-11-28 | 2026-12-15 | 2026-10-04 | 2026-10-21 | 52222 | -15
Street Lighting Network |  | 40 | 2027-08-15 | 2027-09-30 | 2026-07-25 | 2026-10-13 | 18024 | -290
Termination and Testing Works |  | 40 | 2027-08-15 | 2027-09-30 | 2026-07-25 | 2026-10-13 | 18024 | -290
CO-R17-SL-TF-240 | Termination Works For Lighting Poles Cables of Street Lighting Network-[Road 17] | 12 | 2027-08-15 | 2027-08-28 | 2026-07-25 | 2026-08-06 | 18024 | -262
CO-R17-SL-TF-250 | Termination Works For Panel Board Cables of Street Lighting Network-[Road 17] | 12 | 2027-09-16 | 2027-09-30 | 2026-09-30 | 2026-10-13 | 0 | -292
Road 18 Local 1 ( 479 LM ) |  | 160 | 2027-03-02 | 2027-09-13 | 2026-06-16 | 2026-10-21 | 127035 | -243
Sewage Network |  | 27 | 2027-06-12 | 2027-07-12 | 2026-08-20 | 2026-09-16 | 29759 | -202
Testing and Finishes |  | 27 | 2027-06-12 | 2027-07-12 | 2026-08-20 | 2026-09-16 | 29759 | -202
CO-R18-SW-TF-100 | Final Testing For Main Line of Sewage Network-[Road 18] | 12 | 2027-06-12 | 2027-06-24 | 2026-08-20 | 2026-09-02 | 12907 | -199
CO-R18-SW-TF-110 | Install Manhole Cover Works for External Finishes of Sewage Network-[Road 18] | 12 | 2027-06-26 | 2027-07-08 | 2026-09-03 | 2026-09-16 | 8426 | -199
CO-R18-SW-TF-130 | Main Manhole Internal Finishes (Benching + Insulation) of Sewage Network-[Road 18] | 12 | 2027-06-29 | 2027-07-12 | 2026-09-03 | 2026-09-16 | 8426 | -202
Storm Drainage Network |  | 71 | 2027-04-03 | 2027-06-29 | 2026-08-03 | 2026-10-21 | 75245 | -178
Testing and Finishes |  | 71 | 2027-04-03 | 2027-06-29 | 2026-08-03 | 2026-10-21 | 75245 | -178
CO-R18-SD-TF-110 | Install Catch Basin Cover Works for External Finishes of Storm Drainage Network-[Road 18] | 16 | 2027-04-03 | 2027-04-20 | 2026-08-03 | 2026-08-20 | 5983 | -123
CO-R18-SD-TF-100 | Testing Work for Pipes of Storm Drainage Network-[Road 18] | 16 | 2027-06-12 | 2027-06-29 | 2026-10-04 | 2026-10-21 | 69262 | -178
Potable Water Network |  | 24 | 2027-07-12 | 2027-08-08 | 2026-08-26 | 2026-09-22 | 0 | -216
Testing and Finishes |  | 24 | 2027-07-12 | 2027-08-08 | 2026-08-26 | 2026-09-22 | 0 | -216
CO-R18-PW-TF-100 | Final Finishes works and Covers for Valves and Valve Chambers of Potable Water Network-[Road 18] | 12 | 2027-07-12 | 2027-07-25 | 2026-08-26 | 2026-09-08 | 0 | -216
CO-R18-PW-TF-120 | Fire Hydrant Finishies (S.Box + Safety + Marker Post ) of Potable Water Network-[Road 18] | 12 | 2027-07-26 | 2027-08-08 | 2026-09-09 | 2026-09-22 | 0 | -216
Irrigation Network |  | 16 | 2027-06-27 | 2027-07-14 | 2026-08-17 | 2026-09-03 | 4599 | -213
Testing and Finishes |  | 16 | 2027-06-27 | 2027-07-14 | 2026-08-17 | 2026-09-03 | 4599 | -213
CO-R18-IR-TF-110 | Final Testing (pressure tests) of Irrigation Network-[Road 18] | 16 | 2027-06-27 | 2027-07-14 | 2026-08-17 | 2026-09-03 | 4599 | -213
Street Lighting Network |  | 76 | 2027-06-17 | 2027-09-13 | 2026-06-16 | 2026-09-12 | 17433 | -276
Termination and Testing Works |  | 76 | 2027-06-17 | 2027-09-13 | 2026-06-16 | 2026-09-12 | 17433 | -276
CO-R18-SL-TF-120 | Termination Works For Lighting Poles Cables of Street Lighting Network-[Road 18] | 12 | 2027-06-17 | 2027-07-01 | 2026-06-16 | 2026-06-30 | 17433 | -212
CO-R18-SL-TF-130 | Termination Works For Panel Board Cables of Street Lighting Network-[Road 18] | 12 | 2027-08-28 | 2027-09-11 | 2026-08-26 | 2026-09-09 | 0 | -276
CO-R18-SL-TF-380 | Testing Works For Panel Board Cables of Street Lighting Network-[Road 18] | 2 | 2027-09-11 | 2027-09-13 | 2026-09-09 | 2026-09-12 | 0 | -276
Medium Voltage Network |  | 16 | 2027-03-02 | 2027-03-23 | 2026-07-09 | 2026-07-27 | 0 | -121
Termination and Testing Works |  | 16 | 2027-03-02 | 2027-03-23 | 2026-07-09 | 2026-07-27 | 0 | -121
CO-R18-MV-TF-120 | Termination Works of Medium Voltage Network-[Road 18] | 16 | 2027-03-02 | 2027-03-23 | 2026-07-09 | 2026-07-27 | 0 | -121
Independent Works |  | 243 | 2026-10-13 | 2027-08-02 | 2026-02-15 | 2026-11-11 | 4420852 | -170
Tie In To Existing Networks |  | 12 | 2027-05-11 | 2027-05-30 | 2026-09-02 | 2026-09-15 | 0 | -115
Phase 2 Block "J" |  | 12 | 2027-05-11 | 2027-05-30 | 2026-09-02 | 2026-09-15 | 0 | -115
Road 18 Local 1 ( 479 LM ) |  | 12 | 2027-05-11 | 2027-05-30 | 2026-09-02 | 2026-09-15 | 0 | -115
Telecom Network |  | 12 | 2027-05-11 | 2027-05-30 | 2026-09-02 | 2026-09-15 | 0 | -115
TIE-R18-TE10 | TIE IN Existing Network For Telecom Network | 12 | 2027-05-11 | 2027-05-30 | 2026-09-02 | 2026-09-15 | 0 | -115
Sewage Pump Stations |  | 155 | 2026-11-17 | 2027-05-26 | 2026-05-10 | 2026-11-11 | 4105538 | -153
Sewage Pump Station ( PS 06 ) |  | 155 | 2026-11-17 | 2027-05-26 | 2026-05-10 | 2026-11-11 | 4105538 | -153
Pump Station Main Building |  | 120 | 2026-11-17 | 2027-04-10 | 2026-05-10 | 2026-10-06 | 1450260 | -118
CO-SW-PS7-MB-120 | Internal Finishes Works of Superstrucure | 30 | 2026-11-17 | 2026-12-21 | 2026-05-10 | 2026-06-17 | 19135 | -155
CO-SW-PS7-MB-130 | Internal Electrical Works | 30 | 2026-12-22 | 2027-01-25 | 2026-06-18 | 2026-07-22 | 697563 | -118
CO-SW-PS7-MB-140 | Internal Mechanical Works | 30 | 2027-01-26 | 2027-03-02 | 2026-07-23 | 2026-08-26 | 572621 | -118
CO-SW-PS7-MB-150 | Electromechanical Main Works | 30 | 2027-03-03 | 2027-04-10 | 2026-09-01 | 2026-10-06 | 160941 | -118
Generator With Umbrella Tank |  | 75 | 2026-12-22 | 2027-03-23 | 2026-06-18 | 2026-09-13 | 215257 | -155
CO-SW-PS7-GN-100 | Concrete Works of Base | 12 | 2026-12-22 | 2027-01-04 | 2026-06-18 | 2026-07-01 | 43051 | -155
CO-SW-PS7-GN-110 | Install Manually Operated Fuel Pump | 21 | 2027-01-05 | 2027-01-28 | 2026-07-02 | 2026-07-26 | 107628 | -155
CO-SW-PS7-GN-120 | Install Ground Fuel Tank | 21 | 2027-01-30 | 2027-02-23 | 2026-07-27 | 2026-08-19 | 43051 | -155
CO-SW-PS7-GN-130 | Fix Steel Structure for Umbrella | 21 | 2027-02-24 | 2027-03-23 | 2026-08-20 | 2026-09-13 | 21526 | -155
Motor Control Centre Building |  | 121 | 2026-11-17 | 2027-04-11 | 2026-05-10 | 2026-10-03 | 1971445 | -119
CO-SW-PS7-MCC-100 | Excavation Main Bulding | 16 | 2026-11-17 | 2026-12-05 | 2026-05-10 | 2026-06-01 | 96 | -119
CO-SW-PS7-MCC-110 | Concrete Works of Superstrucure | 21 | 2026-12-06 | 2026-12-29 | 2026-06-02 | 2026-06-25 | 108090 | -119
CO-SW-PS7-MCC-120 | Internal Finishes Works of Superstrucure | 21 | 2026-12-30 | 2027-01-23 | 2026-06-27 | 2026-07-20 | 65710 | -119
CO-SW-PS7-MCC-130 | Internal Electrical Works | 21 | 2027-01-24 | 2027-02-16 | 2026-07-21 | 2026-08-13 | 298746 | -119
CO-SW-PS7-MCC-140 | Internal Mechanical Works | 21 | 2027-02-17 | 2027-03-17 | 2026-08-15 | 2026-09-07 | 75272 | -119
CO-SW-PS7-MCC-150 | Electromechanical Main Works | 21 | 2027-03-18 | 2027-04-11 | 2026-09-08 | 2026-10-03 | 1423530 | -119
Simple Building Works |  | 50 | 2027-03-24 | 2027-05-26 | 2026-09-14 | 2026-11-11 | 468576 | -153
CO-SW-PS7-SBL-100 | Perimeter Fencing | 23 | 2027-03-24 | 2027-04-19 | 2026-09-14 | 2026-10-11 | 73149 | -155
CO-SW-PS7-SBL-110 | Outside Lighting | 27 | 2027-04-20 | 2027-05-26 | 2026-10-12 | 2026-11-11 | 16426 | -153
CO-SW-PS7-SBL-120 | Outside Duct Works | 23 | 2027-04-20 | 2027-05-22 | 2026-10-12 | 2026-11-07 | 9923 | -155
CO-SW-PS7-SBL-130 | Rectangular Wet Wells | 27 | 2027-04-20 | 2027-05-26 | 2026-10-12 | 2026-11-11 | 147819 | -153
CO-SW-PS7-SBL-140 | Round Wet Well Structure for basket screen | 27 | 2027-04-20 | 2027-05-26 | 2026-10-12 | 2026-11-11 | 67771 | -153
CO-SW-PS7-SBL-150 | Motorized basket screen | 27 | 2027-04-20 | 2027-05-26 | 2026-10-12 | 2026-11-11 | 153488 | -153
Storm Drainage Ponds |  | 243 | 2026-10-13 | 2027-08-02 | 2026-02-15 | 2026-08-24 | 315314 | -226
Storm Drainage Pond ( PO-J1) |  | 136 | 2026-10-13 | 2027-03-24 | 2026-02-15 | 2026-07-30 | 28703 | -147
CO-SD-PO-K1-110-P1 | Finished Grouted Riprap - PART 1 | 21 | 2026-10-13 | 2026-11-05 | 2026-02-15 | 2026-03-10 | 5741 | -147
CO-SD-PO-K1-110-P2 | Finished Grouted Riprap - PART 2 | 21 | 2026-11-07 | 2026-11-30 | 2026-03-11 | 2026-04-07 | 5741 | -147
CO-SD-PO-K1-110-P3 | Finished Grouted Riprap - PART 3 | 21 | 2026-12-01 | 2026-12-24 | 2026-04-08 | 2026-05-02 | 5741 | -147
CO-SD-PO-K1-110-P4 | Finished Grouted Riprap - PART 4 | 21 | 2026-12-26 | 2027-01-18 | 2026-05-03 | 2026-05-31 | 5741 | -147
CO-SD-PO-K1-120 | Outfall structure | 26 | 2027-01-19 | 2027-02-17 | 2026-06-01 | 2026-06-30 | 2870 | -147
CO-SD-PO-K1-130 | Acess Entrace Ramp | 26 | 2027-02-18 | 2027-03-24 | 2026-07-01 | 2026-07-30 | 2870 | -147
Storm Drainage Pond ( PO-J2) |  | 157 | 2027-01-21 | 2027-08-02 | 2026-02-15 | 2026-08-24 | 286611 | -226
CO-SD-PO-K2-100-P1 | Excavation & Filling Works - PART 1 | 21 | 2027-01-21 | 2027-02-14 | 2026-02-15 | 2026-03-10 | 68424 | -226
CO-SD-PO-K2-110-P1 | Finished Grouted Riprap - PART 1 | 21 | 2027-02-15 | 2027-03-15 | 2026-03-11 | 2026-04-07 | 2583 | -226
CO-SD-PO-K2-100-P2 | Excavation & Filling Works - PART 2 | 21 | 2027-02-15 | 2027-03-15 | 2026-03-11 | 2026-04-07 | 68424 | -226
CO-SD-PO-K2-110-P2 | Finished Grouted Riprap - PART 2 | 21 | 2027-03-16 | 2027-04-08 | 2026-04-08 | 2026-05-02 | 2583 | -226
CO-SD-PO-K2-100-P3 | Excavation & Filling Works - PART 3 | 21 | 2027-03-16 | 2027-04-08 | 2026-04-08 | 2026-05-02 | 68424 | -226
CO-SD-PO-K2-110-P3 | Finished Grouted Riprap - PART 3 | 21 | 2027-04-10 | 2027-05-03 | 2026-05-03 | 2026-05-31 | 2583 | -226
CO-SD-PO-K2-100-P4 | Excavation & Filling Works - PART 4 | 21 | 2027-04-10 | 2027-05-03 | 2026-05-03 | 2026-05-31 | 68424 | -226
CO-SD-PO-K2-110-P4 | Finished Grouted Riprap - PART 4 | 21 | 2027-05-04 | 2027-06-02 | 2026-06-01 | 2026-06-24 | 2583 | -226
CO-SD-PO-K2-120 | Outfall structure | 26 | 2027-06-03 | 2027-07-03 | 2026-06-25 | 2026-07-25 | 1292 | -226
CO-SD-PO-K2-130 | Acess Entrace Ramp | 26 | 2027-07-04 | 2027-08-02 | 2026-07-26 | 2026-08-24 | 1292 | -226

## Sheet1 (hidden)
Activity ID | Activity Name | Original Duration | Start | Finish | BL Project Start | BL Project Finish | Budgeted Total Cost | Total Float
Infrastructure Works of Area J -3rd Industrial City-Dammam-Phase 2 - Part 2 @06-May-25 |  | 624 | 12-Jan-25 A | 2027-01-30 | 2025-01-12 | 2027-01-11 | 113116847.71 | -16
Key Milestones |  | 624 | 12-Jan-25 A | 2027-01-30 | 2025-01-12 | 2027-01-11 | 0 | -16
Contractual Milestones |  | 624 | 12-Jan-25 A | 2027-01-30 | 2025-01-12 | 2027-01-11 | 0 | -16
MS-CS-PS | Project Commencement Date ( Site Handover ) | 0 | 12-Jan-25 A |  | 2025-01-12 |  | 0
MS-CF-MOB | Completion of Mobilization Works | 0 |  | 09-Mar-25 A |  | 2025-03-09 | 0
MS-CF-EBL | Completion of Work Plan and Baseline Schedule | 0 |  | 10-Mar-25 A |  | 2025-02-10 | 0
MS-CF-ENG | Completion of Submitting and Approval of Shopdrwing and Material | 0 |  | 01-Jun-25* |  | 2025-02-10 | 0 | -90
MS-CF-TE | Completion of Construction Works for Telecom Network | 0 |  | 20-Sep-26* |  | 2026-09-01 | 0 | -16
MS-CF-SL | Completion of Construction Works for Street Lighting Network | 0 |  | 03-Nov-26* |  | 2026-10-15 | 0 | -16
MS-CF-IR | Completion of Construction Works for Irrigation Network | 0 |  | 16-Nov-26* |  | 2026-10-28 | 0 | -16
MS-CF-MV | Completion of Construction Works for Medium Voltage Network | 0 |  | 16-Nov-26* |  | 2026-10-28 | 0 | -16
MS-CF-SW | Completion of Construction Works for Sewage Network | 0 |  | 26-Nov-26* |  | 2026-11-08 | 0 | -16
MS-CF-PW | Completion of Construction Works for Potable Water Network | 0 |  | 07-Dec-26* |  | 2026-11-18 | 0 | -16
MS-CF-SD | Completion of Construction Works for Storm Drainage Network | 0 |  | 30-Dec-26* |  | 2026-12-12 | 0 | -16
MS-CF-RD | Completion of Construction Works for Road Works | 0 |  | 2027-01-16 |  | 2026-12-28 | 0 | -16
MS-CF-PF | Project Completion Date | 0 |  | 2027-01-30 |  | 2027-01-11 | 0 | -16
Control Milestones |  | 333 | 2025-06-02 | 2026-07-09 | 2025-07-09 | 2026-06-21 | 0 | 23
MS-CS-SW | The Employer Approval NOC for Sewage Network | 0 | 2025-06-02 |  | 2025-07-09 |  | 0 | 63
MS-CS-SD | The Employer Approval NOC for Storm Drainage Network | 0 | 2025-09-28 |  | 2025-09-08 |  | 0 | 29
MS-CS-PW | The Employer Approval NOC for Potable Water Network | 0 | 2025-11-22 |  | 2025-11-03 |  | 0 | 96
MS-CS-IR | The Employer Approval NOC for Irrigation Network | 0 | 2025-12-08 |  | 2025-11-19 |  | 0 | 35
MS-CS-SL | The Employer Approval NOC for Street Lighting Network | 0 | 2026-02-17 |  | 2025-12-29 |  | 0 | 11
MS-CS-MV | The Employer Approval NOC for Medium Voltage Network | 0 | 2026-04-08 |  | 2026-02-14 |  | 0 | 9
MS-CS-TE | The Employer Approval NOC for Telecom Network | 0 | 2026-05-21 |  | 2026-05-03 |  | 0 | -6
MS-CS-RD | The Employer Approval NOC for Roads Works | 0 | 2026-07-09 |  | 2026-06-21 |  | 0 | 23
Intermediate Milestones |  | 107 | 2026-09-12 | 2027-01-16 | 2026-08-24 | 2026-12-28 | 0 | -13
MS-MO-20 | Completion of Storm Drainage Ponds | 0 |  | 2026-09-12 |  | 2026-08-24 | 0 | 84
MS-MO-10 | Completion of Sewage Pump Stations | 0 |  | 2026-12-24 |  | 2026-12-01 | 0 | -4
MS-MO-30 | Completion of Tie In To Existing Networks | 0 |  | 2027-01-16 |  | 2026-12-28 | 0 | -13
Preliminaries and Mobilization Works |  | 48 | 12-Jan-25 A | 12-Mar-25 A | 2025-01-12 | 2025-03-09 | 0
Mobilization Works |  | 48 | 12-Jan-25 A | 12-Mar-25 A | 2025-01-12 | 2025-03-09 | 0
MOB-10 | Clear and Grub for Offices and Access Roads | 24 | 12-Jan-25 A | 12-Mar-25 A | 2025-01-12 | 2025-02-08 | 0
MOB-20 | Project Site Layout Plan Approval | 24 | 12-Jan-25 A | 12-Mar-25 A | 2025-01-12 | 2025-02-08 | 0
MOB-30 | Supply & Install of Project Supervision Offices | 24 | 09-Feb-25 A | 12-Mar-25 A | 2025-02-09 | 2025-03-09 | 0
MOB-40 | Construction Project Store & Temporary Fence | 24 | 09-Feb-25 A | 12-Mar-25 A | 2025-02-09 | 2025-03-09 | 0
MOB-50 | Mobilization of Major Manpower | 24 | 09-Feb-25 A | 12-Mar-25 A | 2025-02-09 | 2025-03-09 | 0
MOB-60 | Mobilization of Major Equipments | 24 | 09-Feb-25 A | 12-Mar-25 A | 2025-02-09 | 2025-03-09 | 0
MOB-70 | Installation Project Sign Board | 24 | 09-Feb-25 A | 12-Mar-25 A | 2025-02-09 | 2025-03-09 | 0
MOB-80 | Construction Site Access Roads | 24 | 09-Feb-25 A | 12-Mar-25 A | 2025-02-09 | 2025-03-09 | 0
Project Documents Provision From The Employer |  | 0 | 12-Jan-25 A | 12-Feb-25 A | 2025-01-12 | 2025-01-12 | 0
PRE-EMP-MDC-10 | Receive of Approved Project Master Plans of works (IFC) From The Employer | 0 | 12-Jan-25 A |  | 2025-01-12 |  | 0
PRE-EMP-MDC-20 | Receive of Site Benchmark Coordinates (Original Point) From The Employer | 0 | 12-Feb-25 A |  | 2025-01-12 |  | 0
PRE-EMP-MDC-30 | Receive of Site Surveying Details From The Employer | 0 | 12-Feb-25 A |  | 2025-01-12 |  | 0
Project Main Documents From The Contractor |  | 26 | 12-Jan-25 A | 02-Mar-25 A | 2025-01-12 | 2025-02-10 | 0
PRE-CON-MDC-20 | Submission Project Baseline Schedule | 26 | 12-Jan-25 A | 01-Mar-25 A | 2025-01-12 | 2025-02-10 | 0
PRE-CON-MDC-30 | Submission Project Health & Safety Plan | 26 | 12-Jan-25 A | 02-Mar-25 A | 2025-01-12 | 2025-02-10 | 0
PRE-CON-MDC-40 | Submission Project Quality Control Plan | 26 | 12-Jan-25 A | 02-Mar-25 A | 2025-01-12 | 2025-02-10 | 0
PRE-CON-MDC-50 | Submission Project Surveying Report | 26 | 12-Jan-25 A | 02-Mar-25 A | 2025-01-12 | 2025-02-10 | 0
PRE-CON-MDC-60 | Submission Project Geotechnical Soil Report | 26 | 12-Jan-25 A | 02-Mar-25 A | 2025-01-12 | 2025-02-10 | 0
PRE-CON-MDC-70 | Submission Project Environmental Plan | 26 | 12-Jan-25 A | 02-Mar-25 A | 2025-01-12 | 2025-02-10 | 0
PRE-CON-MDC-80 | Submission Project Organization Chart and Communications Plan | 26 | 12-Jan-25 A | 02-Mar-25 A | 2025-01-12 | 2025-02-10 | 0
Engineering Works |  | 121 | 12-Jan-25 A | 2025-06-11 | 2025-01-12 | 2025-02-16 | 3015066.97 | 88
Design Reviews |  | 9 | 12-Jan-25 A | 21-Jan-25 A | 2025-01-12 | 2025-01-21 | 0
Infrastructure Networks |  | 9 | 12-Jan-25 A | 21-Jan-25 A | 2025-01-12 | 2025-01-21 | 0
Road Works |  | 9 | 12-Jan-25 A | 21-Jan-25 A | 2025-01-12 | 2025-01-21 | 0
ENG-DS-RD-S-100 | Receive of Design Drawing Package for Road Works from Modon | 6 | 12-Jan-25 A | 18-Jan-25 A | 2025-01-12 | 2025-01-18 | 0
ENG-DS-RD-A-110 | Review and Comment of Design Drawings for Road Works by Contractor | 6 | 15-Jan-25 A | 21-Jan-25 A | 2025-01-15 | 2025-01-21 | 0
Sewage Network |  | 9 | 12-Jan-25 A | 21-Jan-25 A | 2025-01-12 | 2025-01-21 | 0
ENG-DS-SW-S-100 | Receive of Design Drawing Package for Sewage Network from Modon | 6 | 12-Jan-25 A | 18-Jan-25 A | 2025-01-12 | 2025-01-18 | 0
ENG-DS-SW-A-110 | Review and Comment of Design Drawings for Sewage Network by Contractor | 6 | 15-Jan-25 A | 21-Jan-25 A | 2025-01-15 | 2025-01-21 | 0
Storm Drainage Network |  | 9 | 12-Jan-25 A | 21-Jan-25 A | 2025-01-12 | 2025-01-21 | 0
ENG-DS-SD-S-100 | Receive of Design Drawing Package for Storm Drainage Network from Modon | 6 | 12-Jan-25 A | 18-Jan-25 A | 2025-01-12 | 2025-01-18 | 0
ENG-DS-SD-A-110 | Review and Comment of Design Drawings for Storm Drainage Network by Contractor | 6 | 15-Jan-25 A | 21-Jan-25 A | 2025-01-15 | 2025-01-21 | 0
Potable Water Network |  | 9 | 12-Jan-25 A | 21-Jan-25 A | 2025-01-12 | 2025-01-21 | 0
ENG-DS-PW-S-100 | Receive of Design Drawing Package for Potable Water Network from Modon | 6 | 12-Jan-25 A | 18-Jan-25 A | 2025-01-12 | 2025-01-18 | 0
ENG-DS-PW-A-110 | Review and Comment of Design Drawings for Potable Water Network by Contractor | 6 | 15-Jan-25 A | 21-Jan-25 A | 2025-01-15 | 2025-01-21 | 0
Irrigation Network |  | 9 | 12-Jan-25 A | 21-Jan-25 A | 2025-01-12 | 2025-01-21 | 0
ENG-DS-IR-S-100 | Receive of Design Drawing Package for Irrigation Network from Modon | 6 | 12-Jan-25 A | 18-Jan-25 A | 2025-01-12 | 2025-01-18 | 0
ENG-DS-IR-A-110 | Review and Comment of Design Drawings for Irrigation Network by Contractor | 6 | 15-Jan-25 A | 21-Jan-25 A | 2025-01-15 | 2025-01-21 | 0
Medium Voltage Network |  | 9 | 12-Jan-25 A | 21-Jan-25 A | 2025-01-12 | 2025-01-21 | 0
ENG-DS-MV-S-100 | Receive of Design Drawing Package for Medium Voltage Network from Modon | 6 | 12-Jan-25 A | 18-Jan-25 A | 2025-01-12 | 2025-01-18 | 0
ENG-DS-MV-A-110 | Review and Comment of Design Drawings for Medium Voltage Network by Contractor | 6 | 15-Jan-25 A | 21-Jan-25 A | 2025-01-15 | 2025-01-21 | 0
Street Lighting Network |  | 9 | 12-Jan-25 A | 21-Jan-25 A | 2025-01-12 | 2025-01-21 | 0
ENG-DS-SL-S-100 | Receive of Design Drawing Package for Street Lighting Network from Modon | 6 | 12-Jan-25 A | 18-Jan-25 A | 2025-01-12 | 2025-01-18 | 0
ENG-DS-SL-A-110 | Review and Comment of Design Drawings for Street Lighting Network by Contractor | 6 | 15-Jan-25 A | 21-Jan-25 A | 2025-01-15 | 2025-01-21 | 0
Telecom Network |  | 9 | 12-Jan-25 A | 21-Jan-25 A | 2025-01-12 | 2025-01-21 | 0
ENG-DS-TE-S-100 | Receive of Design Drawing Package for Telecom Network from Modon | 6 | 12-Jan-25 A | 18-Jan-25 A | 2025-01-12 | 2025-01-18 | 0
ENG-DS-TE-A-110 | Review and Comment of Design Drawings for Telecom Network by Contractor | 6 | 15-Jan-25 A | 21-Jan-25 A | 2025-01-15 | 2025-01-21 | 0
Superstructure Works |  | 9 | 12-Jan-25 A | 21-Jan-25 A | 2025-01-12 | 2025-01-21 | 0
Sewage Pump Stations ( PS06 ) |  | 9 | 12-Jan-25 A | 21-Jan-25 A | 2025-01-12 | 2025-01-21 | 0
ENG-DS-SPS-S-100 | Receive of Design Drawing Package for Sewage Pump Stations from Modon | 6 | 12-Jan-25 A | 18-Jan-25 A | 2025-01-12 | 2025-01-18 | 0
ENG-DS-SPS-A-110 | Review and Comment of Design Drawings for Sewage Pump Stations by Contractor | 6 | 15-Jan-25 A | 21-Jan-25 A | 2025-01-15 | 2025-01-21 | 0
Storm Drainage Ponds ( PO-J1 , PO-J2 ) |  | 9 | 12-Jan-25 A | 21-Jan-25 A | 2025-01-12 | 2025-01-21 | 0
ENG-DS-DPO-S-100 | Receive of Design Drawing Package for Storm Drainage Ponds from Modon | 6 | 12-Jan-25 A | 18-Jan-25 A | 2025-01-12 | 2025-01-18 | 0
ENG-DS-DPO-A-110 | Review and Comment of Design Drawings for Storm Drainage Ponds by Contractor | 6 | 15-Jan-25 A | 21-Jan-25 A | 2025-01-15 | 2025-01-21 | 0
Shop Drawings |  | 17 | 22-Jan-25 A | 2025-05-13 | 2025-01-22 | 2025-02-10 | 0 | 31
Infrastructure Networks |  | 17 | 22-Jan-25 A | 2025-05-13 | 2025-01-22 | 2025-02-10 | 0 | -74
Road Works |  | 17 | 22-Jan-25 A | 2025-05-13 | 2025-01-22 | 2025-02-10 | 0 | -74
Road Pavement Works |  | 17 | 22-Jan-25 A | 2025-05-13 | 2025-01-22 | 2025-02-10 | 0 | -74
ENG-SH-RD-S-100 | Submission Shop Drawings for Plan and Profile of Road Works | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-SH-RD-S-110 | Submission Shop Drawings for Roads Typical Sections and Pavement Details | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-SH-RD-S-120 | Submission Shop Drawings of Extraover for Pedestrian ramps | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-SH-RD-S-130 | Submission Shop Drawings for Intersections of Road Works | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-SH-RD-A-100 | Approval Shop Drawings for Plan and Profile of Road Works | 8 | 29-Jan-25 A | 09-Feb-25 A | 2025-01-30 | 2025-02-08 | 0
ENG-SH-RD-A-110 | Approval Shop Drawings for Roads Typical Sections and Pavement Details | 10 | 30-Jan-25 A | 2025-05-13 | 2025-01-30 | 2025-02-10 | 0 | -74
ENG-SH-RD-A-120 | Approval Shop Drawings of Extraover for Pedestrian ramps | 10 | 30-Jan-25 A | 2025-05-13 | 2025-01-30 | 2025-02-10 | 0 | -74
ENG-SH-RD-A-130 | Approval Shop Drawings for Intersections of Road Works | 10 | 30-Jan-25 A | 2025-05-13 | 2025-01-30 | 2025-02-10 | 0 | -74
Pavement Works |  | 16 | 22-Jan-25 A | 2025-05-13 | 2025-01-22 | 2025-02-09 | 0 | -74
ENG-SH-HS-S-100 | Submission Shop Drawings for Hardscaping Works | 6 | 22-Jan-25 A | 28-Jan-25 A | 2025-01-22 | 2025-01-28 | 0
ENG-SH-HS-A-110 | Approval Shop Drawings for Hardscaping Works | 10 | 29-Jan-25 A | 2025-05-13 | 2025-01-29 | 2025-02-09 | 0 | -74
Traffic Sign Boards and Road Marking |  | 16 | 22-Jan-25 A | 2025-05-13 | 2025-01-22 | 2025-02-09 | 0 | -74
ENG-SH-TSB-S-100 | Submission Shop Drawings for Traffic Signs Boards | 6 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-28 | 0
ENG-SH-MRK-S-110 | Submission Shop Drawings for Roads Markings | 6 | 22-Jan-25 A | 28-Jan-25 A | 2025-01-22 | 2025-01-28 | 0
ENG-SH-TSB-A-100 | Approval Shop Drawings for Traffic Signs Boards | 10 | 29-Jan-25 A | 2025-05-13 | 2025-01-29 | 2025-02-09 | 0 | -74
ENG-SH-MRK-A-110 | Approval Shop Drawings for Roads Markings | 10 | 29-Jan-25 A | 2025-05-13 | 2025-01-29 | 2025-02-09 | 0 | -74
Sewage Network |  | 12 | 22-Jan-25 A | 28-Apr-25 A | 2025-01-22 | 2025-02-04 | 0
Main Line Sections |  | 12 | 22-Jan-25 A | 28-Apr-25 A | 2025-01-22 | 2025-02-04 | 0
ENG-SH-SW-ML-S-100 | Submission Shop Drawings for Main Line of Sewage Network | 5 | 22-Jan-25 A | 27-Jan-25 A | 2025-01-22 | 2025-01-27 | 0
ENG-SH-SW-ML-A-110 | Approval Shop Drawings for Main Line of Sewage Network | 7 | 28-Jan-25 A | 28-Apr-25 A | 2025-01-28 | 2025-02-04 | 0
Storm Drainage Network |  | 16 | 22-Jan-25 A | 09-Feb-25 A | 2025-01-22 | 2025-02-09 | 0
Main Line Sections |  | 16 | 22-Jan-25 A | 09-Feb-25 A | 2025-01-22 | 2025-02-09 | 0
ENG-SH-SD-ML-S-100 | Submission Shop Drawings for Main Line of Storm Drainage Network | 6 | 22-Jan-25 A | 28-Jan-25 A | 2025-01-22 | 2025-01-28 | 0
ENG-SH-SD-ML-A-110 | Approval Shop Drawings for Main Line of Storm Drainage Network | 10 | 29-Jan-25 A | 09-Feb-25 A | 2025-01-29 | 2025-02-09 | 0
Catch Basin Sections |  | 16 | 22-Jan-25 A | 09-Feb-25 A | 2025-01-22 | 2025-02-09 | 0
ENG-SH-SD-CB-S-100 | Submission Shop Drawings for Catch Basin of Storm Drainage Network | 6 | 22-Jan-25 A | 28-Jan-25 A | 2025-01-22 | 2025-01-28 | 0
ENG-SH-SD-CB-A-110 | Approval Shop Drawings for Catch Basin of Storm Drainage Network | 10 | 29-Jan-25 A | 09-Feb-25 A | 2025-01-29 | 2025-02-09 | 0
Potable Water Network |  | 15 | 22-Jan-25 A | 2025-05-13 | 2025-01-22 | 2025-02-08 | 0 | -74
Main Line Sections |  | 15 | 22-Jan-25 A | 2025-05-13 | 2025-01-22 | 2025-02-08 | 0 | -74
ENG-SH-PW-ML-S-100 | Submission Shop Drawings for Main Line of Potable Water Network | 5 | 22-Jan-25 A | 27-Jan-25 A | 2025-01-22 | 2025-01-27 | 0
ENG-SH-PW-ML-A-110 | Approval Shop Drawings for Main Line of Potable Water Network | 10 | 28-Jan-25 A | 2025-05-13 | 2025-01-28 | 2025-02-08 | 0 | -74
Fire Hydrant |  | 15 | 22-Jan-25 A | 2025-05-13 | 2025-01-22 | 2025-02-08 | 0 | -74
ENG-SH-PW-FH-S-100 | Submission Shop Drawings for Fire Hydrant Network | 5 | 22-Jan-25 A | 27-Jan-25 A | 2025-01-22 | 2025-01-27 | 0
ENG-SH-PW-FH-A-110 | Approval Shop Drawings for Fire Hydrant Network | 10 | 28-Jan-25 A | 2025-05-13 | 2025-01-28 | 2025-02-08 | 0 | -74
Irrigation Network |  | 16 | 22-Jan-25 A | 28-Apr-25 A | 2025-01-22 | 2025-02-09 | 0
Main Line Sections |  | 16 | 22-Jan-25 A | 27-Apr-25 A | 2025-01-22 | 2025-02-09 | 0
ENG-SH-IR-ML-S-100 | Submission Shop Drawings for Main Line of Irrigation Network | 6 | 22-Jan-25 A | 28-Jan-25 A | 2025-01-22 | 2025-01-28 | 0
ENG-SH-IR-ML-A-110 | Approval Shop Drawings for Main Line of Irrigation Network | 10 | 29-Jan-25 A | 27-Apr-25 A | 2025-01-29 | 2025-02-09 | 0
Lateral Line Sections |  | 16 | 22-Jan-25 A | 28-Apr-25 A | 2025-01-22 | 2025-02-09 | 0
ENG-SH-IR-LL-S-100 | Submission Shop Drawings for Lateral Line of Irrigation Network | 6 | 22-Jan-25 A | 28-Jan-25 A | 2025-01-22 | 2025-01-28 | 0
ENG-SH-IR-LL-A-110 | Approval Shop Drawings for Lateral Line of Irrigation Network | 10 | 29-Jan-25 A | 28-Apr-25 A | 2025-01-29 | 2025-02-09 | 0
Medium Voltage Network |  | 16 | 22-Jan-25 A | 09-Feb-25 A | 2025-01-22 | 2025-02-09 | 0
ENG-SH-MV-S-100 | Submission Shop Drawings for Medium Voltage Network | 6 | 22-Jan-25 A | 28-Jan-25 A | 2025-01-22 | 2025-01-28 | 0
ENG-SH-MV-A-110 | Approval Shop Drawings for Medium Voltage Network | 10 | 29-Jan-25 A | 09-Feb-25 A | 2025-01-29 | 2025-02-09 | 0
Street Lighting Network |  | 16 | 22-Jan-25 A | 09-Feb-25 A | 2025-01-22 | 2025-02-09 | 0
ENG-SH-SL-S-100 | Submission Shop Drawings for Street Lighting Network | 6 | 22-Jan-25 A | 28-Jan-25 A | 2025-01-22 | 2025-01-28 | 0
ENG-SH-SL-A-110 | Approval Shop Drawings for Street Lighting Network | 10 | 29-Jan-25 A | 09-Feb-25 A | 2025-01-29 | 2025-02-09 | 0
Telecom Network |  | 16 | 22-Jan-25 A | 09-Feb-25 A | 2025-01-22 | 2025-02-09 | 0
ENG-SH-CTV-S-100 | Submission Shop Drawings for CCTV Complete System | 6 | 22-Jan-25 A | 28-Jan-25 A | 2025-01-22 | 2025-01-28 | 0
ENG-SH-TE-S-100 | Submission Shop Drawings for Telecom Network | 6 | 22-Jan-25 A | 28-Jan-25 A | 2025-01-22 | 2025-01-28 | 0
ENG-SH-CTV-A-110 | Approval Shop Drawings for CCTV Complete System | 10 | 29-Jan-25 A | 09-Feb-25 A | 2025-01-29 | 2025-02-09 | 0
ENG-SH-TE-A-110 | Approval Shop Drawings for Telecom Network | 10 | 29-Jan-25 A | 09-Feb-25 A | 2025-01-29 | 2025-02-09 | 0
Superstructure Works |  | 17 | 22-Jan-25 A | 10-Feb-25 A | 2025-01-22 | 2025-02-10 | 0
Sewage Pump Stations ( PS 06 ) |  | 17 | 22-Jan-25 A | 10-Feb-25 A | 2025-01-22 | 2025-02-10 | 0
ENG-SH-SPS-S-110 | Submission Shop Drawings Package for Sewage Pump Stations | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-SH-SPS-A-110 | Approval Shop Drawings Package for Sewage Pump Stations | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 0
Storm Drainage Ponds ( PO-J1 , PO-J2 ) |  | 17 | 22-Jan-25 A | 10-Feb-25 A | 2025-01-22 | 2025-02-10 | 0
ENG-SH-DPO-S-100 | Submission Shop Drawings Package for Storm Drainage Ponds | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-SH-DPO-A-110 | Approval Shop Drawings Package for Storm Drainage Ponds | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 0
Method Statements |  | 17 | 22-Jan-25 A | 10-Feb-25 A | 2025-01-22 | 2025-02-10 | 0
Infrastructure Networks |  | 17 | 22-Jan-25 A | 10-Feb-25 A | 2025-01-22 | 2025-02-10 | 0
Road Works |  | 17 | 22-Jan-25 A | 10-Feb-25 A | 2025-01-22 | 2025-02-10 | 0
Road Pavement Works |  | 17 | 22-Jan-25 A | 10-Feb-25 A | 2025-01-22 | 2025-02-10 | 0
ENG-MS-RD-S-10 | Submission Method Statement for Plan and Profile of Road Works | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MS-RD-S-20 | Submission Method Statement for Roads Typical Sections and Pavement Details | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MS-RD-S-30 | Submission Method Statement of Extraover for Pedestrian ramps | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MS-RD-S-40 | Submission Method Statement for Intersections of Road Works | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MS-RD-A-10 | Approval Method Statement for Plan and Profile of Road Works | 8 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-08 | 0
ENG-MS-RD-A-20 | Approval Method Statement for Roads Typical Sections and Pavement Details | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 0
ENG-MS-RD-A-30 | Approval Method Statement of Extraover for Pedestrian ramps | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 0
ENG-MS-RD-A-40 | Approval Method Statement for Intersections of Road Works | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 0
Pavement Works |  | 17 | 22-Jan-25 A | 10-Feb-25 A | 2025-01-22 | 2025-02-10 | 0
ENG-MS-HS-S-10 | Submission Method Statement for Hardscaping Works | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MS-HS-A-10 | Approval Method Statement for Hardscaping Works | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 0
Traffic Sign Boards and Road Marking |  | 17 | 22-Jan-25 A | 10-Feb-25 A | 2025-01-22 | 2025-02-10 | 0
ENG-MS-TSB-S-10 | Submission Method Statement for Traffic Signs Boards | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MS-MRK-S-10 | Submission Method Statement for Roads Markings | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MS-TSB-A-10 | Approval Method Statement for Traffic Signs Boards | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 0
ENG-MS-MRK-A-10 | Approval Method Statement for Roads Markings | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 0
Sewage Network |  | 12 | 22-Jan-25 A | 08-Feb-25 A | 2025-01-22 | 2025-02-04 | 0
Main Line Sections |  | 12 | 22-Jan-25 A | 08-Feb-25 A | 2025-01-22 | 2025-02-04 | 0
ENG-MS-SW-ML-S-100 | Submission Method Statement for Main Line of Sewage Network | 5 | 22-Jan-25 A | 27-Jan-25 A | 2025-01-22 | 2025-01-27 | 0
ENG-MS-SW-ML-A-110 | Approval Method Statement for Main Line of Sewage Network | 7 | 28-Jan-25 A | 08-Feb-25 A | 2025-01-28 | 2025-02-04 | 0
Storm Drainage Network |  | 16 | 22-Jan-25 A | 09-Feb-25 A | 2025-01-22 | 2025-02-09 | 0
Main Line Sections |  | 16 | 22-Jan-25 A | 09-Feb-25 A | 2025-01-22 | 2025-02-09 | 0
ENG-MS-SD-ML-S-100 | Submission Method Statement for Main Line of Storm Drainage Network | 6 | 22-Jan-25 A | 28-Jan-25 A | 2025-01-22 | 2025-01-28 | 0
ENG-MS-SD-ML-A-110 | Approval Method Statement for Main Line of Storm Drainage Network | 10 | 29-Jan-25 A | 09-Feb-25 A | 2025-01-29 | 2025-02-09 | 0
Catch Basin Sections |  | 16 | 22-Jan-25 A | 09-Feb-25 A | 2025-01-22 | 2025-02-09 | 0
ENG-MS-SD-CB-S-100 | Submission Method Statement for Catch Basin of Storm Drainage Network | 6 | 22-Jan-25 A | 28-Jan-25 A | 2025-01-22 | 2025-01-28 | 0
ENG-MS-SD-CB-A-110 | Approval Method Statement for Catch Basin of Storm Drainage Network | 10 | 29-Jan-25 A | 09-Feb-25 A | 2025-01-29 | 2025-02-09 | 0
Potable Water Network |  | 15 | 22-Jan-25 A | 08-Feb-25 A | 2025-01-22 | 2025-02-08 | 0
Main Line Sections |  | 15 | 22-Jan-25 A | 08-Feb-25 A | 2025-01-22 | 2025-02-08 | 0
ENG-MS-PW-ML-S-100 | Submission Method Statement for Main Line of Potable Water Network | 5 | 22-Jan-25 A | 27-Jan-25 A | 2025-01-22 | 2025-01-27 | 0
ENG-MS-PW-ML-A-110 | Approval Method Statement for Main Line of Potable Water Network | 10 | 28-Jan-25 A | 08-Feb-25 A | 2025-01-28 | 2025-02-08 | 0
Irrigation Network |  | 16 | 22-Jan-25 A | 09-Feb-25 A | 2025-01-22 | 2025-02-09 | 0
Main Line Sections |  | 16 | 22-Jan-25 A | 09-Feb-25 A | 2025-01-22 | 2025-02-09 | 0
ENG-MS-IR-ML-S-100 | Submission Method Statement for Main Line of Irrigation Network | 6 | 22-Jan-25 A | 28-Jan-25 A | 2025-01-22 | 2025-01-28 | 0
ENG-MS-IR-ML-A-110 | Approval Method Statement for Main Line of Irrigation Network | 10 | 29-Jan-25 A | 09-Feb-25 A | 2025-01-29 | 2025-02-09 | 0
Lateral Line Sections |  | 16 | 22-Jan-25 A | 09-Feb-25 A | 2025-01-22 | 2025-02-09 | 0
ENG-MS-IR-LL-S-100 | Submission Method Statement for Lateral Line of Irrigation Network | 6 | 22-Jan-25 A | 28-Jan-25 A | 2025-01-22 | 2025-01-28 | 0
ENG-MS-IR-LL-A-110 | Approval Method Statement for Lateral Line of Irrigation Network | 10 | 29-Jan-25 A | 09-Feb-25 A | 2025-01-29 | 2025-02-09 | 0
Medium Voltage Network |  | 16 | 22-Jan-25 A | 09-Feb-25 A | 2025-01-22 | 2025-02-09 | 0
ENG-MS-MV-S-100 | Submission Method Statement for Medium Voltage Network | 6 | 22-Jan-25 A | 28-Jan-25 A | 2025-01-22 | 2025-01-28 | 0
ENG-MS-MV-A-110 | Approval Method Statement for Medium Voltage Network | 10 | 29-Jan-25 A | 09-Feb-25 A | 2025-01-29 | 2025-02-09 | 0
Street Lighting Network |  | 16 | 22-Jan-25 A | 09-Feb-25 A | 2025-01-22 | 2025-02-09 | 0
ENG-MS-SL-S-100 | Submission Method Statement for Street Lighting Network | 6 | 22-Jan-25 A | 28-Jan-25 A | 2025-01-22 | 2025-01-28 | 0
ENG-MS-SL-A-110 | Approval Method Statement for Street Lighting Network | 10 | 29-Jan-25 A | 09-Feb-25 A | 2025-01-29 | 2025-02-09 | 0
Telecom Network |  | 16 | 22-Jan-25 A | 09-Feb-25 A | 2025-01-22 | 2025-02-09 | 0
ENG-MS-CTV-S-100 | Submission Method Statement for CCTV Complete System | 6 | 22-Jan-25 A | 28-Jan-25 A | 2025-01-22 | 2025-01-28 | 0
ENG-MS-TE-S-100 | Submission Method Statement for Telecom Network | 6 | 22-Jan-25 A | 28-Jan-25 A | 2025-01-22 | 2025-01-28 | 0
ENG-MS-CTV-A-110 | Approval Method Statement for CCTV Complete System | 10 | 29-Jan-25 A | 09-Feb-25 A | 2025-01-29 | 2025-02-09 | 0
ENG-MS-TE-A-110 | Approval Method Statement for Telecom Network | 10 | 29-Jan-25 A | 09-Feb-25 A | 2025-01-29 | 2025-02-09 | 0
Superstructure Works |  | 17 | 22-Jan-25 A | 10-Feb-25 A | 2025-01-22 | 2025-02-10 | 0
Sewage Pump Stations ( PS 06 ) |  | 17 | 22-Jan-25 A | 10-Feb-25 A | 2025-01-22 | 2025-02-10 | 0
ENG-MS-SPS-S-100 | Submission Method Statement Package for Sewage Pump Stations | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MS-SPS-A-110 | Approval Method Statement Package for Sewage Pump Stations | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 0
Storm Drainage Ponds ( PO-J1 , PO-J2 ) |  | 17 | 22-Jan-25 A | 10-Feb-25 A | 2025-01-22 | 2025-02-10 | 0
ENG-MS-DPO-S-100 | Submission Method Statement Package for Storm Drainage Ponds | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MS-DPO-A-110 | Approval Method Statement Package for Storm Drainage Ponds | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 0
Material Submittals |  | 112 | 22-Jan-25 A | 2025-06-11 | 2025-01-22 | 2025-02-16 | 3015066.97 | 88
Short Lead Time Items |  | 112 | 22-Jan-25 A | 2025-06-11 | 2025-01-22 | 2025-02-16 | 2848900.57 | 88
Infrastructure Networks |  | 112 | 22-Jan-25 A | 2025-06-11 | 2025-01-22 | 2025-02-16 | 2736286.15 | 88
Road Works |  | 112 | 22-Jan-25 A | 2025-06-11 | 2025-01-22 | 2025-02-16 | 712379.13 | 88
Submission of Material |  | 102 | 22-Jan-25 A | 2025-05-27 | 2025-01-22 | 2025-02-04 | 0 | 88
Roads Works |  | 102 | 22-Jan-25 A | 26-May-25 A | 2025-01-22 | 2025-02-04 | 0
ENG-MT-RD-S-100 | Material Submittal for Subgrade of Road Works | 12 | 22-Jan-25 A | 04-Feb-25 A | 2025-01-22 | 2025-02-04 | 0
ENG-MT-RD-S-110 | Material Submittal for Aggregate Base Course of Road Works | 12 | 22-Jan-25 A | 04-Feb-25 A | 2025-01-22 | 2025-02-04 | 0
ENG-MT-RD-S-120 | Material Submittal for Prime Coat of Road Works | 12 | 13-May-25 A | 26-May-25 A | 2025-01-22 | 2025-02-04 | 0
ENG-MT-RD-S-130 | Material Submittal for Bituminous Base & Wearing Courses of Road Works | 12 | 13-May-25 A | 26-May-25 A | 2025-01-22 | 2025-02-04 | 0
Pavement Works |  | 102 | 27-Jan-25 A | 27-May-25 A | 2025-01-22 | 2025-02-04 | 0
ENG-MT-RD-S-140 | Material Submittal for Interlock Tiles of Landscaping | 12 | 27-Jan-25 A | 15-Mar-25 A | 2025-01-22 | 2025-02-04 | 0
ENG-MT-RD-S-150 | Material Submittal for Curbstones of Landscaping | 12 | 26-Apr-25 A | 27-May-25 A | 2025-01-22 | 2025-02-04 | 0
Traffic Signs Boards and Roads Marking |  | 12 | 13-May-25 A | 2025-05-26 | 2025-01-22 | 2025-02-04 | 0 | 88
ENG-MT-TS-S-100 | Material Submittal for Traffic Signs Boards of Road Works | 12 | 13-May-25 A | 26-May-25 A | 2025-01-22 | 2025-02-04 | 0
ENG-MT-TS-S-110 | Material Submittal for Road Markings of Road Works | 12 | 2025-05-13 | 2025-05-26 | 2025-01-22 | 2025-02-04 | 0 | 88
Approval of Material |  | 100 | 27-Jan-25 A | 2025-06-11 | 2025-02-05 | 2025-02-16 | 712379.13 | 88
Road Works |  | 95 | 05-Feb-25 A | 01-Jun-25 A | 2025-02-05 | 2025-02-10 | 529570.2
ENG-MT-RD-A-100 | Material Approval for Subgrade of Road Works | 5 | 05-Feb-25 A | 13-Mar-25 A | 2025-02-05 | 2025-02-10 | 73995
ENG-MT-RD-A-110 | Material Approval for Aggregate Base Course of Road Works | 5 | 05-Feb-25 A | 13-Mar-25 A | 2025-02-05 | 2025-02-10 | 83573.49
ENG-MT-RD-A-120 | Material Approval for Prime Coat of Road Works | 5 | 27-May-25 A | 01-Jun-25 A | 2025-02-05 | 2025-02-10 | 35817.21
ENG-MT-RD-A-130 | Material Approval for Bituminous Base & Wearing Courses of Road Works | 5 | 27-May-25 A | 01-Jun-25 A | 2025-02-05 | 2025-02-10 | 336184.5
Pavement Works |  | 17 | 27-Jan-25 A | 27-Apr-25 A | 2025-02-05 | 2025-02-16 | 167621.1
ENG-MT-RD-A-140 | Material Approval of Interlock Tiles for Landscaping | 10 | 27-Jan-25 A | 15-Mar-25 A | 2025-02-05 | 2025-02-16 | 69861.3
ENG-MT-RD-A-150 | Material Approval of Curbstones for Landscaping | 10 | 26-Apr-25 A | 27-Apr-25 A | 2025-02-05 | 2025-02-16 | 97759.8
Traffic Signs Boards and Roads Marking |  | 22 | 2025-05-13 | 2025-06-11 | 2025-02-05 | 2025-02-16 | 15187.83 | 88
ENG-MT-TS-A-100 | Material Approval for Traffic Signs Boards of Road Works | 10 | 2025-05-13 | 2025-05-24 | 2025-02-05 | 2025-02-16 | 4215.39 | 74
ENG-MT-TS-A-110 | Material Approval for Road Markings of Road Works | 10 | 2025-05-27 | 2025-06-11 | 2025-02-05 | 2025-02-16 | 10972.44 | 88
Sewage Network |  | 17 | 22-Jan-25 A | 15-May-25 A | 2025-01-22 | 2025-02-10 | 531962.88
Submission of Material |  | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
Main Line Sections |  | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-SW-ML-S-110 | Material Submittal for Main Line Pipes of Sewage Network | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-SW-ML-S-100 | Material Submittal for Manholes of Sewage Network | 5 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-27 | 0
Testing and Finishes |  | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-SW-TF-S-100 | Material Submittal for Manhole Covers of Sewage Network | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-SW-TF-S-120 | Material Submittal for Membrane Insulation of Sewage Network | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
Approval of Material |  | 12 | 30-Jan-25 A | 15-May-25 A | 2025-01-28 | 2025-02-10 | 531962.88
Main Line Sections |  | 12 | 30-Jan-25 A | 20-Apr-25 A | 2025-01-28 | 2025-02-10 | 506237.73
ENG-MT-SW-ML-A-110 | Material Approval for Main Line Pipes of Sewage Network | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 423387.75
ENG-MT-SW-ML-A-100 | Material Approval for Manholes of Sewage Network | 6 | 30-Jan-25 A | 20-Apr-25 A | 2025-01-28 | 2025-02-03 | 82849.98
Testing and Finishes |  | 10 | 05-Mar-25 A | 15-May-25 A | 2025-01-30 | 2025-02-10 | 25725.15
ENG-MT-SW-TF-A-100 | Material Approval for Manhole Covers of Sewage Network | 10 | 05-Mar-25 A | 15-May-25 A | 2025-01-30 | 2025-02-10 | 13078.44
ENG-MT-SW-TF-A-120 | Material Approval for Membrane Insulation of Sewage Network | 10 | 06-Mar-25 A | 15-Mar-25 A | 2025-01-30 | 2025-02-10 | 12646.71
Storm Drainage Network |  | 17 | 22-Jan-25 A | 2025-05-14 | 2025-01-22 | 2025-02-10 | 658054.11 | -75
Submission of Material |  | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
Main Line Sections |  | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-SD-ML-S-110 | Material Submittal for Main Line Pipes of Storm Drainage Network | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-SD-ML-S-100 | Material Submittal for Manholes of Storm Drainage Network | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
Catch Basin Sections |  | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-SD-CB-S-100 | Material Submittal for Catch Basins of Storm Drainage Network | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-SD-CB-S-110 | Material Submittal for Catch Basin Pipes of Storm Drainage Network | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
Testing and Finishes |  | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-SD-TF-S-100 | Material Submittal for Manhole Covers of Storm Drainage Network | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-SD-TF-S-110 | Material Submittal for Catch Basin Covers of Storm Drainage Network | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-SD-TF-S-120 | Material Submittal for Epoxy Insulation of Storm Drainage Network | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
Approval of Material |  | 10 | 30-Jan-25 A | 2025-05-14 | 2025-01-30 | 2025-02-10 | 658054.11 | -75
Main Line Sections |  | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 452922.8
ENG-MT-SD-ML-A-100 | Material Approval for Manholes of Storm Drainage Network | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 111361.25
ENG-MT-SD-ML-A-110 | Material Approval for Main Line Pipes of Storm Drainage Network | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 341561.55
Catch Basin Sections |  | 10 | 30-Jan-25 A | 2025-05-14 | 2025-01-30 | 2025-02-10 | 159940.8 | -75
ENG-MT-SD-CB-A-110 | Material Approval for Catch Basin Pipes of Storm Drainage Network | 10 | 30-Jan-25 A | 2025-05-14 | 2025-01-30 | 2025-02-10 | 90540 | -75
ENG-MT-SD-CB-A-100 | Material Approval for Catch Basins of Storm Drainage Network | 10 | 30-Jan-25 A | 2025-05-14 | 2025-01-30 | 2025-02-10 | 69400.8 | -75
Testing and Finishes |  | 10 | 30-Jan-25 A | 2025-05-14 | 2025-01-30 | 2025-02-10 | 45190.51 | -75
ENG-MT-SD-TF-A-100 | Material Approval for Manhole Covers of Storm Drainage Network | 10 | 30-Jan-25 A | 2025-05-14 | 2025-01-30 | 2025-02-10 | 13920.16 | -75
ENG-MT-SD-TF-A-110 | Material Approval for Catch Basin Covers of Storm Drainage Network | 10 | 30-Jan-25 A | 2025-05-14 | 2025-01-30 | 2025-02-10 | 8675.1 | -75
ENG-MT-SD-TF-A-120 | Material Approval for Epoxy Insulation of Storm Drainage Network | 10 | 30-Jan-25 A | 2025-05-14 | 2025-01-30 | 2025-02-10 | 22595.26 | -75
Potable Water Network |  | 17 | 22-Jan-25 A | 2025-05-15 | 2025-01-22 | 2025-02-10 | 273724.32 | -76
Submission of Material |  | 7 | 22-Jan-25 A | 2025-05-13 | 2025-01-22 | 2025-01-29 | 0 | -74
Main Line Sections |  | 7 | 22-Jan-25 A | 2025-05-13 | 2025-01-22 | 2025-01-29 | 0 | -74
ENG-MT-PW-ML-S-100 | Material Submittal for Main Line Pipes of Potable Water Network | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-PW-ML-S-110 | Material Submittal for Main Line Valves of Potable Water Network | 7 | 22-Jan-25 A | 2025-05-13 | 2025-01-22 | 2025-01-29 | 0 | -75
Fire Hydrant |  | 7 | 22-Jan-25 A | 2025-05-13 | 2025-01-22 | 2025-01-29 | 0 | -76
ENG-MT-PW-FH-S-100 | Material Submittal for Fire Hydrant of Potable Water Network | 7 | 22-Jan-25 A | 2025-05-13 | 2025-01-22 | 2025-01-29 | 0 | -76
Testing and Finishes |  | 7 | 22-Jan-25 A | 2025-05-13 | 2025-01-22 | 2025-01-29 | 0 | -74
ENG-MT-PW-TF-S-100 | Material Submittal for Surface Box of Potable Water Network | 7 | 22-Jan-25 A | 2025-05-13 | 2025-01-22 | 2025-01-29 | 0 | -74
Approval of Material |  | 10 | 30-Jan-25 A | 2025-05-15 | 2025-01-30 | 2025-02-10 | 273724.32 | -76
Main Line Sections |  | 10 | 30-Jan-25 A | 2025-05-14 | 2025-01-30 | 2025-02-10 | 246179.07 | -75
ENG-MT-PW-ML-A-100 | Material Approval for Main Line Pipes of Potable Water Network | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 194270.82
ENG-MT-PW-ML-A-110 | Material Approval for Valves of Potable Water Network | 10 | 30-Jan-25 A | 2025-05-14 | 2025-01-30 | 2025-02-10 | 51908.25 | -75
Fire Hydrant |  | 10 | 30-Jan-25 A | 2025-05-15 | 2025-01-30 | 2025-02-10 | 18653.25 | -76
ENG-MT-PW-FH-A-100 | Material Approval for Fire Hydrants of Potable Water Network | 10 | 30-Jan-25 A | 2025-05-15 | 2025-01-30 | 2025-02-10 | 18653.25 | -76
Testing and Finishes |  | 0 | 30-Jan-25 A | 2025-05-14 | 2025-01-30 | 2025-01-30 | 8892 | -74
ENG-MT-PW-TF-A-100 | Material Approval for Surface Box of Potable Water Network | 0 | 30-Jan-25 A | 2025-05-14 | 2025-01-30 | 2025-01-30 | 8892 | -74
Irrigation Network |  | 17 | 22-Jan-25 A | 2025-05-14 | 2025-01-22 | 2025-02-10 | 187247.64 | -75
Submission of Material |  | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
Main Line Pipes |  | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-IR-ML-S-100 | Material Submittal for Main Line Pipes of Irrigation Network | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-IR-ML-S-110 | Material Submittal for Main Line Valves of Irrigation Network | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
Approval of Material |  | 10 | 30-Jan-25 A | 2025-05-14 | 2025-01-30 | 2025-02-10 | 187247.64 | -75
Main Line Pipes |  | 10 | 30-Jan-25 A | 2025-05-14 | 2025-01-30 | 2025-02-10 | 187247.64 | -75
ENG-MT-IR-ML-A-100 | Material Approval for Main Line Pipes of Irrigation Network | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 147707.25
ENG-MT-IR-ML-A-110 | Material Approval for Valves of Irrigation Network | 10 | 30-Jan-25 A | 2025-05-14 | 2025-01-30 | 2025-02-10 | 39540.39 | -75
Medium Voltage Network |  | 17 | 22-Jan-25 A | 2025-05-21 | 2025-01-22 | 2025-02-10 | 168652.68 | -81
Submission of Material |  | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
Cabling Works |  | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-MV-ML-S-100 | Material Submittal for Medium Voltage Cables of Medium Voltage Network | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
RMU Concrete Works |  | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-MV-SS-S-100 | Material Submittal for RMU Concrete Foundations of Medium Voltage Network | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
Termination and Testing Works |  | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-MV-TF-S-100 | Material Submittal for Termination Kits of Medium Voltage Network | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
Approval of Material |  | 10 | 30-Jan-25 A | 2025-05-21 | 2025-01-30 | 2025-02-10 | 168652.68 | -81
Cabling Works |  | 10 | 30-Jan-25 A | 2025-05-13 | 2025-01-30 | 2025-02-10 | 165542.44 | -74
ENG-MT-MV-ML-A-100 | Material Approval for Medium Voltage Cables of Medium Voltage Network | 10 | 30-Jan-25 A | 2025-05-13 | 2025-01-30 | 2025-02-10 | 165542.44 | -74
RMU Concrete Works |  | 10 | 30-Jan-25 A | 2025-05-21 | 2025-01-30 | 2025-02-10 | 1600.8 | -81
ENG-MT-MV-SS-A-100 | Material Approval for RMU Concrete Foundations of Medium Voltage Network | 10 | 30-Jan-25 A | 2025-05-21 | 2025-01-30 | 2025-02-10 | 1600.8 | -81
Termination and Testing Works |  | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 1509.43
ENG-MT-MV-TF-A-100 | Material Approval for Termination and Joints Kits of Medium Voltage Network | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 1509.43
Street Lighting Network |  | 100 | 22-Jan-25 A | 2025-05-24 | 2025-01-22 | 2025-02-10 | 138710.56 | -83
Submission of Material |  | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
Cabling Works |  | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-SL-ML-S-100 | Material Submittal for Lighting Cables of Street Lighting Network | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
Lighting Poles Works |  | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-SL-S-100 | Material Submittal for Lighting Poles Concrete Foundations of Street Lighting Network | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-SL-S-110 | Material Submittal for Lighting Poles of Street Lighting Network | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-SL-S-120 | Material Submittal for Lighting Fixtures of Street Lighting Network | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
Distribution Panel Board |  | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-SL-DB-S-100 | Material Submittal for Lighting Distrubution Panel Boards of Street Lighting Network | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
Termination and Testing Works |  | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-SL-TF-S-100 | Material Submittal for Fuse Boxes of Street Lighting Network | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-SL-TF-S-110 | Material Submittal for Cable Lugs of Street Lighting Network | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
Earthing System Works |  | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-SL-ES-S-100 | Material Submittal for Lighting Earthing of Street Lighting Network | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
Approval of Material |  | 93 | 30-Jan-25 A | 2025-05-24 | 2025-01-30 | 2025-02-10 | 138710.56 | -83
Cabling Works |  | 10 | 30-Jan-25 A | 2025-05-14 | 2025-01-30 | 2025-02-10 | 46202.22 | -75
ENG-MT-SL-ML-A-100 | Material Approval for Lighting Cables of Street Lighting Network | 10 | 30-Jan-25 A | 2025-05-14 | 2025-01-30 | 2025-02-10 | 46202.22 | -75
Lighting Poles Works |  | 93 | 30-Jan-25 A | 2025-05-24 | 2025-01-30 | 2025-02-10 | 50225.64 | -83
ENG-MT-SL-A-100 | Material Approval for Lighting Poles Concrete Foundations of Street Lighting Network | 10 | 30-Jan-25 A | 2025-05-21 | 2025-01-30 | 2025-02-10 | 9725.13 | -81
ENG-MT-SL-A-110 | Material Approval for Lighting Poles of Street Lighting Network | 10 | 2025-05-13 | 2025-05-24 | 2025-01-30 | 2025-02-10 | 30634.05 | -83
ENG-MT-SL-A-120 | Material Approval for Lighting Fixtures of Street Lighting Network | 10 | 2025-05-13 | 2025-05-24 | 2025-01-30 | 2025-02-10 | 9866.46 | -83
Distribution Panel Board |  | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 28956.04
ENG-MT-SL-DB-A-100 | Material Approval for Distrubution Panel Boards of Street Lighting Network | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 28956.04
Termination and Testing Works |  | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 12271.26
ENG-MT-SL-TF-A-100 | Material Approval for Fuse Boxes of Street Lighting Network | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 4422.6
ENG-MT-SL-TF-A-110 | Material Approval for Cable Lugs of Street Lighting Network | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 7848.66
Earthing System Works |  | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 1055.4
ENG-MT-SL-ES-A-100 | Material Approval for Lighting Earthing of Street Lighting Network | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 1055.4
Telecom Network |  | 17 | 22-Jan-25 A | 2025-05-14 | 2025-01-22 | 2025-02-10 | 65554.83 | -75
Submission of Material |  | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
Ducts Works |  | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-TE-S-100 | Material Submittal for Ducts of Telecom Network | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
Manholes Works |  | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-TE-S-110 | Material Submittal for Manholes of Telecom Network | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
Approval of Material |  | 10 | 30-Jan-25 A | 2025-05-14 | 2025-01-30 | 2025-02-10 | 65554.83 | -75
Ducts Works |  | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 54182.7
ENG-MT-TE-A-100 | Material Approval for Ducts of Telecom Network | 10 | 30-Jan-25 A | 10-Feb-25 A | 2025-01-30 | 2025-02-10 | 54182.7
Manholes Works |  | 10 | 30-Jan-25 A | 2025-05-14 | 2025-01-30 | 2025-02-10 | 11372.13 | -75
ENG-MT-TE-A-110 | Material Approval for Manholes of Telecom Network | 10 | 30-Jan-25 A | 2025-05-14 | 2025-01-30 | 2025-02-10 | 11372.13 | -75
Superstructure Works |  | 17 | 22-Jan-25 A | 2025-05-14 | 2025-01-22 | 2025-02-10 | 112614.42 | -75
Sewage Pump Stations ( PS 06 ) |  | 17 | 22-Jan-25 A | 11-May-25 A | 2025-01-22 | 2025-02-10 | 23563.38
Submission of Material |  | 7 | 22-Jan-25 A | 11-May-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-SPS-CV-S-100 | Material Submittal for Civil Works for Sewage Pump Stations | 7 | 22-Jan-25 A | 11-May-25 A | 2025-01-22 | 2025-01-29 | 0
Approval of Material |  | 10 | 30-Jan-25 A | 11-May-25 A | 2025-01-30 | 2025-02-10 | 23563.38
ENG-MT-SPS-CV-A-110 | Material Approval for Civil Works for Sewage Pump Stations | 10 | 30-Jan-25 A | 11-May-25 A | 2025-01-30 | 2025-02-10 | 23563.38
Storm Drainage Ponds ( PO-J1 , PO-J2 ) |  | 17 | 22-Jan-25 A | 2025-05-14 | 2025-01-22 | 2025-02-10 | 89051.04 | -75
Submission of Material |  | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
ENG-MT-DPO-CV-S-100 | Material Submittal for Civil Works for Storm Drainage Ponds | 7 | 22-Jan-25 A | 29-Jan-25 A | 2025-01-22 | 2025-01-29 | 0
Approval of Material |  | 10 | 30-Jan-25 A | 2025-05-14 | 2025-01-30 | 2025-02-10 | 89051.04 | -75
ENG-MT-DPO-CV-A-110 | Material Approval for Civil Works for Storm Drainage Ponds | 10 | 30-Jan-25 A | 2025-05-14 | 2025-01-30 | 2025-02-10 | 89051.04 | -75
Long Lead Time Items |  | 17 | 11-May-25 A | 2025-06-01 | 2025-01-22 | 2025-02-10 | 166166.4 | -90
Infrastructure Networks |  | 7 | 2025-05-13 | 2025-05-21 | 2025-01-22 | 2025-01-30 | 10780.8 | -80
RMU Works of Medium Voltage Network |  | 7 | 2025-05-13 | 2025-05-21 | 2025-01-22 | 2025-01-30 | 10780.8 | -80
Submission of Material |  | 7 | 2025-05-13 | 2025-05-20 | 2025-01-22 | 2025-01-29 | 0 | -80
ENG-MT-MV-S-10 | Material Submittal for RMU of Medium Voltage Network | 7 | 2025-05-13 | 2025-05-20 | 2025-01-22 | 2025-01-29 | 0 | -80
Approval of Material |  | 0 | 2025-05-21 | 2025-05-21 | 2025-01-30 | 2025-01-30 | 10780.8 | -80
ENG-MT-MV-A-10 | Material Approval for RMU of Medium Voltage Network | 0 | 2025-05-21 | 2025-05-21 | 2025-01-30 | 2025-01-30 | 10780.8 | -80
Superstructure Works |  | 17 | 11-May-25 A | 2025-06-01 | 2025-01-22 | 2025-02-10 | 155385.6 | -90
Sewage Pump Stations ( PS 06 ) |  | 17 | 11-May-25 A | 2025-06-01 | 2025-01-22 | 2025-02-10 | 155385.6 | -90
Submission of Material |  | 7 | 11-May-25 A | 2025-05-20 | 2025-01-22 | 2025-01-29 | 0 | -90
ENG-MT-SPS-MC-S-100 | Material Submittal for Electromechanical Works for Sewage Pump Stations | 7 | 11-May-25 A | 2025-05-20 | 2025-01-22 | 2025-01-29 | 0 | -90
Approval of Material |  | 10 | 11-May-25 A | 2025-06-01 | 2025-01-30 | 2025-02-10 | 155385.6 | -90
ENG-MT-SPS-MC-A-110 | Material Approval for Electromechanical Works for Sewage Pump Stations | 10 | 11-May-25 A | 2025-06-01 | 2025-01-30 | 2025-02-10 | 155385.6 | -90
Procurement Cycle |  | 538 | 11-Feb-25 A | 2026-11-15 | 2025-02-05 | 2026-10-05 | 20007775.71 | -6
Short Lead Time Items |  | 538 | 11-Feb-25 A | 2026-11-15 | 2025-02-05 | 2026-10-05 | 18899999.75 | -6
Infrastructure Networks |  | 538 | 11-Feb-25 A | 2026-11-15 | 2025-02-05 | 2026-10-05 | 17093229.15 | -6
Road Works |  | 533 | 11-Feb-25 A | 2026-11-15 | 2025-02-11 | 2026-10-05 | 4749284.6 | -6
Issuance of Purchase Orders |  | 17 | 11-Feb-25 A | 04-Mar-25 A | 2025-02-11 | 2025-03-03 | 0
Road Works |  | 12 | 11-Feb-25 A | 25-Feb-25 A | 2025-02-11 | 2025-02-25 | 0
PRO-RD-PO-100 | Issuance of Purchase Order for Subgrade of Road Works | 12 | 11-Feb-25 A | 25-Feb-25 A | 2025-02-11 | 2025-02-25 | 0
PRO-RD-PO-110 | Issuance of Purchase Order for Aggregate Base Course of Road Works | 12 | 11-Feb-25 A | 25-Feb-25 A | 2025-02-11 | 2025-02-25 | 0
PRO-RD-PO-120 | Issuance of Purchase Order for Prime Coat of Road Works | 12 | 11-Feb-25 A | 25-Feb-25 A | 2025-02-11 | 2025-02-25 | 0
PRO-RD-PO-130 | Issuance of Purchase Order for Bituminous Base & Wearing Courses of Road Works | 12 | 11-Feb-25 A | 25-Feb-25 A | 2025-02-11 | 2025-02-25 | 0
Pavement Works |  | 12 | 17-Feb-25 A | 04-Mar-25 A | 2025-02-17 | 2025-03-03 | 0
PRO-RD-PO-140 | Issuance of Purchase Order for Interlock Tiles of Landscaping | 12 | 17-Feb-25 A | 04-Mar-25 A | 2025-02-17 | 2025-03-03 | 0
PRO-RD-PO-150 | Issuance of Purchase Order for Curbstones of Landscaping | 12 | 17-Feb-25 A | 04-Mar-25 A | 2025-02-17 | 2025-03-03 | 0
Traffic Signs Boards and Roads Marking |  | 12 | 17-Feb-25 A | 04-Mar-25 A | 2025-02-17 | 2025-03-03 | 0
PRO-RD-PO-160 | Issuance of Purchase Order for Traffic Signs Boards of Road Works | 12 | 17-Feb-25 A | 04-Mar-25 A | 2025-02-17 | 2025-03-03 | 0
PRO-RD-PO-170 | Issuance of Purchase Order for Road Markings of Road Works | 12 | 17-Feb-25 A | 04-Mar-25 A | 2025-02-17 | 2025-03-03 | 0
Manufacturing of Material |  | 213 | 01-Apr-25 A | 2025-11-11 | 2025-02-26 | 2025-08-11 | 0 | 88
Road Works |  | 171 | 01-Apr-25 A | 2025-09-22 | 2025-02-26 | 2025-07-13 | 0 | 78
PRO-RD-MF-100 | Manufacturing of Subgrade for Road Works | 90 | 01-Apr-25 A | 2025-07-02 | 2025-02-26 | 2025-06-19 | 0 | 18
PRO-RD-MF-110 | Manufacturing of Aggregate Base Course for Road Works | 90 | 2025-05-13 | 2025-08-30 | 2025-02-26 | 2025-07-13 | 0 | -6
PRO-RD-MF-120 | Manufacturing of Prime Coat for Road Works | 110 | 2025-05-13 | 2025-09-22 | 2025-02-26 | 2025-07-13 | 0 | 52
PRO-RD-MF-130 | Manufacturing of Bituminous Base & Wearing Courses for Road Works | 110 | 2025-05-13 | 2025-09-22 | 2025-02-26 | 2025-07-13 | 0 | 78
Pavement Works |  | 110 | 2025-05-14 | 2025-09-24 | 2025-03-04 | 2025-07-19 | 0 | 25
PRO-RD-MF-140 | Manufacturing of Interlock Tiles for Landscaping | 110 | 2025-05-14 | 2025-09-24 | 2025-03-04 | 2025-07-19 | 0 | -1
PRO-RD-MF-150 | Manufacturing of Curbstones for Landscaping | 110 | 2025-05-14 | 2025-09-24 | 2025-03-04 | 2025-07-19 | 0 | 25
Traffic Signs Boards and Roads Marking |  | 142 | 2025-05-25 | 2025-11-11 | 2025-03-04 | 2025-08-11 | 0 | 88
PRO-RD-MF-160 | Manufacturing of Traffic Signs Boards for Road Works | 130 | 2025-05-25 | 2025-10-28 | 2025-03-04 | 2025-08-11 | 0 | 74
PRO-RD-MF-170 | Manufacturing of Road Markings for Road Works | 130 | 2025-06-12 | 2025-11-11 | 2025-03-04 | 2025-08-11 | 0 | 88
1st Material Delivery & Site Inspection |  | 118 | 2025-07-03 | 2025-11-18 | 2025-06-21 | 2025-08-18 | 0 | 88
Road Works |  | 76 | 2025-07-03 | 2025-09-30 | 2025-06-21 | 2025-07-20 | 0 | 78
PRO-RD-1DL-100 | 1ST Material Delivery for Subgrade of Road Works | 6 | 2025-07-03 | 2025-07-09 | 2025-06-21 | 2025-06-26 | 0 | 18
PRO-RD-1DL-110 | 1ST Material Delivery for Aggregate Base Course of Road Works | 6 | 2025-08-31 | 2025-09-06 | 2025-07-14 | 2025-07-20 | 0 | -6
PRO-RD-1DL-120 | 1ST Material Delivery for Prime Coat of Road Works | 6 | 2025-09-24 | 2025-09-30 | 2025-07-14 | 2025-07-20 | 0 | 52
PRO-RD-1DL-130 | 1ST Material Delivery for Bituminous Base & Wearing Courses of Road Works | 6 | 2025-09-24 | 2025-09-30 | 2025-07-14 | 2025-07-20 | 0 | 78
Pavement Works |  | 6 | 2025-09-25 | 2025-10-01 | 2025-07-20 | 2025-07-26 | 0 | 25
PRO-RD-1DL-140 | 1ST Material Delivery for Interlock Tiles of Landscaping | 6 | 2025-09-25 | 2025-10-01 | 2025-07-20 | 2025-07-26 | 0 | -1
PRO-RD-1DL-150 | 1ST Material Delivery for Curbstones of Landscaping | 6 | 2025-09-25 | 2025-10-01 | 2025-07-20 | 2025-07-26 | 0 | 25
Traffic Signs Boards and Roads Marking |  | 18 | 2025-10-29 | 2025-11-18 | 2025-08-12 | 2025-08-18 | 0 | 88
PRO-RD-1DL-160 | 1ST Material Delivery for Traffic Signs Boards of Road Works | 6 | 2025-10-29 | 2025-11-04 | 2025-08-12 | 2025-08-18 | 0 | 74
PRO-RD-1DL-170 | 1ST Material Delivery for Road Markings of Road Works | 6 | 2025-11-12 | 2025-11-18 | 2025-08-12 | 2025-08-18 | 0 | 88
Material Delivery & Site Inspection |  | 414 | 2025-07-10 | 2026-11-15 | 2025-06-28 | 2026-10-05 | 4749284.6 | -6
Road 18 Local 1 ( 479 LM ) |  | 232 | 2025-07-10 | 2026-04-11 | 2025-06-28 | 2026-02-25 | 281497.81 | -6
Pre-Bituminous Construction |  | 76 | 2025-07-10 | 2025-10-07 | 2025-06-28 | 2025-08-26 | 76292.54 | -6
PRO-R18-RD-DL-220 | Material Delivery & Site Inspection for Subgrade of Road Works | 26 | 2025-07-10 | 2025-08-09 | 2025-06-28 | 2025-07-27 | 29191.6 | 18
PRO-R18-RD-DL-230 | Material Delivery & Site Inspection for Aggregate Base Course of Road Works | 26 | 2025-09-07 | 2025-10-07 | 2025-07-28 | 2025-08-26 | 47100.94 | -6
Pavement Works |  | 52 | 2025-10-08 | 2025-12-07 | 2025-08-27 | 2025-10-27 | 66278.4 | -6
PRO-R18-RD-DL-180 | Material Delivery & Site Inspection of Interlock Tiles for Landscaping | 26 | 2025-10-08 | 2025-11-06 | 2025-08-27 | 2025-09-27 | 27711.36 | -6
PRO-R18-RD-DL-190 | Material Delivery & Site Inspection of Curbstones for Landscaping | 26 | 2025-11-08 | 2025-12-07 | 2025-09-28 | 2025-10-27 | 38567.04 | -6
Bituminous Construction |  | 52 | 2025-12-08 | 2026-02-05 | 2025-10-28 | 2025-12-27 | 132626.88 | -6
PRO-R18-RD-DL-240 | Material Delivery & Site Inspection for Prime Coat of Road Works | 26 | 2025-12-08 | 2026-01-06 | 2025-10-28 | 2025-11-26 | 26525.18 | -6
PRO-R18-RD-DL-250 | Material Delivery & Site Inspection for Bituminous Base & Wearing Courses of Road Works | 26 | 2026-01-07 | 2026-02-05 | 2025-11-27 | 2025-12-27 | 106101.7 | -6
Traffic Signs Boards and Roads Marking |  | 52 | 2026-02-07 | 2026-04-11 | 2025-12-28 | 2026-02-25 | 6299.98 | -6
PRO-R18-RD-DL-200 | Material Delivery & Site Inspection of Traffic Signs Boards For Road Works | 26 | 2026-02-07 | 2026-03-08 | 2025-12-28 | 2026-01-26 | 1971.2 | -6
PRO-R18-RD-DL-210 | Material Delivery & Site Inspection of Road Markings For Road Works | 26 | 2026-03-09 | 2026-04-11 | 2026-01-27 | 2026-02-25 | 4328.78 | -6
Road 17 Local 1 ( 500 LM ) |  | 232 | 2025-08-10 | 2026-05-11 | 2025-07-28 | 2026-03-31 | 290279.55 | -6
Pre-Bituminous Construction |  | 76 | 2025-08-10 | 2025-11-06 | 2025-07-28 | 2025-09-27 | 78894.26 | -6
PRO-R17-RD-DL-120 | Material Delivery & Site Inspection for Subgrade of Road Works | 26 | 2025-08-10 | 2025-09-08 | 2025-07-28 | 2025-08-26 | 30187.4 | 18
PRO-R17-RD-DL-130 | Material Delivery & Site Inspection for Aggregate Base Course of Road Works | 26 | 2025-10-08 | 2025-11-06 | 2025-08-27 | 2025-09-27 | 48706.86 | -6
Pavement Works |  | 52 | 2025-11-08 | 2026-01-06 | 2025-09-28 | 2025-11-26 | 68249.96 | -6
PRO-R17-RD-DL-100 | Material Delivery & Site Inspection of Interlock Tiles for Landscaping | 26 | 2025-11-08 | 2025-12-07 | 2025-09-28 | 2025-10-27 | 28367.48 | -6
PRO-R17-RD-DL-110 | Material Delivery & Site Inspection of Curbstones for Landscaping | 26 | 2025-12-08 | 2026-01-06 | 2025-10-28 | 2025-11-26 | 39882.48 | -6
Bituminous Construction |  | 52 | 2026-01-07 | 2026-03-08 | 2025-11-27 | 2026-01-26 | 137154.22 | -6
PRO-R17-RD-DL-160 | Material Delivery & Site Inspection for Prime Coat of Road Works | 26 | 2026-01-07 | 2026-02-05 | 2025-11-27 | 2025-12-27 | 27431.52 | -6
PRO-R17-RD-DL-170 | Material Delivery & Site Inspection for Bituminous Base & Wearing Courses of Road Works | 26 | 2026-02-07 | 2026-03-08 | 2025-12-28 | 2026-01-26 | 109722.7 | -6
Traffic Signs Boards and Roads Marking |  | 52 | 2026-03-09 | 2026-05-11 | 2026-01-27 | 2026-03-31 | 5981.11 | -6
PRO-R17-RD-DL-140 | Material Delivery & Site Inspection of Traffic Signs Boards For Road Works | 26 | 2026-03-09 | 2026-04-11 | 2026-01-27 | 2026-02-25 | 1504.8 | -6
PRO-R17-RD-DL-150 | Material Delivery & Site Inspection of Road Markings For Road Works | 26 | 2026-04-12 | 2026-05-11 | 2026-02-26 | 2026-03-31 | 4476.31 | -6
Road 16 Local 1 ( 527 LM ) |  | 232 | 2025-09-09 | 2026-06-15 | 2025-08-27 | 2026-04-30 | 305975.76 | -6
Pre-Bituminous Construction |  | 76 | 2025-09-09 | 2025-12-07 | 2025-08-27 | 2025-10-27 | 82976.44 | 95
PRO-R16-RD-DL-100 | Material Delivery & Site Inspection for Subgrade of Road Works | 26 | 2025-09-09 | 2025-10-09 | 2025-08-27 | 2025-09-27 | 31749.4 | 131
PRO-R16-RD-DL-110 | Material Delivery & Site Inspection for Aggregate Base Course of Road Works | 26 | 2025-11-08 | 2025-12-07 | 2025-09-28 | 2025-10-27 | 51227.04 | 95
Pavement Works |  | 52 | 2025-12-08 | 2026-02-05 | 2025-10-28 | 2025-12-27 | 72016.6 | 46
PRO-R16-RD-DL-120 | Material Delivery & Site Inspection of Interlock Tiles for Landscaping | 26 | 2025-12-08 | 2026-01-06 | 2025-10-28 | 2025-11-26 | 30070.36 | 72
PRO-R16-RD-DL-130 | Material Delivery & Site Inspection of Curbstones for Landscaping | 26 | 2026-01-07 | 2026-02-05 | 2025-11-27 | 2025-12-27 | 41946.24 | 46
Bituminous Construction |  | 52 | 2026-02-07 | 2026-04-11 | 2025-12-28 | 2026-02-25 | 144246.4 | 33
PRO-R16-RD-DL-160 | Material Delivery & Site Inspection for Prime Coat of Road Works | 26 | 2026-02-07 | 2026-03-08 | 2025-12-28 | 2026-01-26 | 28849.04 | 59
PRO-R16-RD-DL-170 | Material Delivery & Site Inspection for Bituminous Base & Wearing Courses of Road Works | 26 | 2026-03-09 | 2026-04-11 | 2026-01-27 | 2026-02-25 | 115397.36 | 20
Traffic Signs Boards and Roads Marking |  | 52 | 2026-04-12 | 2026-06-15 | 2026-02-26 | 2026-04-30 | 6736.31 | -6
PRO-R16-RD-DL-140 | Material Delivery & Site Inspection of Traffic Signs Boards For Road Works | 26 | 2026-04-12 | 2026-05-11 | 2026-02-26 | 2026-03-31 | 2028.4 | 20
PRO-R16-RD-DL-150 | Material Delivery & Site Inspection of Road Markings For Road Works | 26 | 2026-05-12 | 2026-06-15 | 2026-04-01 | 2026-04-30 | 4707.91 | -6
Road 15 Local 1 ( 556 LM ) |  | 232 | 2025-10-11 | 2026-07-15 | 2025-09-28 | 2026-06-04 | 321099.81 | -6
Pre-Bituminous Construction |  | 76 | 2025-10-11 | 2026-01-06 | 2025-09-28 | 2025-11-26 | 87059.8 | 95
PRO-R15-RD-DL-100 | Material Delivery & Site Inspection for Subgrade of Road Works | 26 | 2025-10-11 | 2025-11-09 | 2025-09-28 | 2025-10-27 | 33311.6 | 131
PRO-R15-RD-DL-110 | Material Delivery & Site Inspection for Aggregate Base Course of Road Works | 26 | 2025-12-08 | 2026-01-06 | 2025-10-28 | 2025-11-26 | 53748.2 | 95
Pavement Works |  | 52 | 2026-01-07 | 2026-03-08 | 2025-11-27 | 2026-01-26 | 75521.72 | 46
PRO-R15-RD-DL-120 | Material Delivery & Site Inspection of Interlock Tiles for Landscaping | 26 | 2026-01-07 | 2026-02-05 | 2025-11-27 | 2025-12-27 | 31511.24 | 72
PRO-R15-RD-DL-130 | Material Delivery & Site Inspection of Curbstones for Landscaping | 26 | 2026-02-07 | 2026-03-08 | 2025-12-28 | 2026-01-26 | 44010.48 | 46
Bituminous Construction |  | 52 | 2026-03-09 | 2026-05-11 | 2026-01-27 | 2026-03-31 | 151345.56 | 33
PRO-R15-RD-DL-160 | Material Delivery & Site Inspection for Prime Coat of Road Works | 26 | 2026-03-09 | 2026-04-11 | 2026-01-27 | 2026-02-25 | 30268.85 | 59
PRO-R15-RD-DL-170 | Material Delivery & Site Inspection for Bituminous Base & Wearing Courses of Road Works | 26 | 2026-04-12 | 2026-05-11 | 2026-02-26 | 2026-03-31 | 121076.71 | 20
Traffic Signs Boards and Roads Marking |  | 52 | 2026-05-12 | 2026-07-15 | 2026-04-01 | 2026-06-04 | 7172.73 | -6
PRO-R15-RD-DL-140 | Material Delivery & Site Inspection of Traffic Signs Boards For Road Works | 26 | 2026-05-12 | 2026-06-15 | 2026-04-01 | 2026-04-30 | 2233 | 20
PRO-R15-RD-DL-150 | Material Delivery & Site Inspection of Road Markings For Road Works | 26 | 2026-06-16 | 2026-07-15 | 2026-05-02 | 2026-06-04 | 4939.73 | -6
Road 10 Local 2 ( 2352 LM ) |  | 232 | 2025-11-10 | 2026-08-15 | 2025-10-28 | 2026-07-05 | 1305488.9 | -6
Pre-Bituminous Construction |  | 76 | 2025-11-10 | 2026-02-05 | 2025-10-28 | 2025-12-27 | 354466.21 | 95
PRO-R10-RD-DL-100 | Material Delivery & Site Inspection for Subgrade of Road Works | 26 | 2025-11-10 | 2025-12-09 | 2025-10-28 | 2025-11-26 | 135629 | 131
PRO-R10-RD-DL-110 | Material Delivery & Site Inspection for Aggregate Base Course of Road Works | 26 | 2026-01-07 | 2026-02-05 | 2025-11-27 | 2025-12-27 | 218837.21 | 95
Pavement Works |  | 52 | 2026-02-07 | 2026-04-11 | 2025-12-28 | 2026-02-25 | 307169.24 | 46
PRO-R10-RD-DL-120 | Material Delivery & Site Inspection of Interlock Tiles for Landscaping | 26 | 2026-02-07 | 2026-03-08 | 2025-12-28 | 2026-01-26 | 127980.68 | 72
PRO-R10-RD-DL-130 | Material Delivery & Site Inspection of Curbstones for Landscaping | 26 | 2026-03-09 | 2026-04-11 | 2026-01-27 | 2026-02-25 | 179188.56 | 46
Bituminous Construction |  | 52 | 2026-04-12 | 2026-06-15 | 2026-02-26 | 2026-04-30 | 616208.82 | 33
PRO-R10-RD-DL-160 | Material Delivery & Site Inspection for Prime Coat of Road Works | 26 | 2026-04-12 | 2026-05-11 | 2026-02-26 | 2026-03-31 | 123242.68 | 59
PRO-R10-RD-DL-170 | Material Delivery & Site Inspection for Bituminous Base & Wearing Courses of Road Works | 26 | 2026-05-12 | 2026-06-15 | 2026-04-01 | 2026-04-30 | 492966.14 | 20
Traffic Signs Boards and Roads Marking |  | 52 | 2026-06-16 | 2026-08-15 | 2026-05-02 | 2026-07-05 | 27644.63 | -6
PRO-R10-RD-DL-140 | Material Delivery & Site Inspection of Traffic Signs Boards For Road Works | 26 | 2026-06-16 | 2026-07-15 | 2026-05-02 | 2026-06-04 | 7532.8 | 20
PRO-R10-RD-DL-150 | Material Delivery & Site Inspection of Road Markings For Road Works | 26 | 2026-07-16 | 2026-08-15 | 2026-06-06 | 2026-07-05 | 20111.83 | -6
Road 14 Local 1 ( 584 LM ) |  | 232 | 2025-12-10 | 2026-09-14 | 2025-11-27 | 2026-08-04 | 562361.85 | -6
Pre-Bituminous Construction |  | 76 | 2025-12-10 | 2026-03-08 | 2025-11-27 | 2026-01-26 | 152641.94 | 95
PRO-R14-RD-DL-100 | Material Delivery & Site Inspection for Subgrade of Road Works | 26 | 2025-12-10 | 2026-01-08 | 2025-11-27 | 2025-12-27 | 58405.2 | 131
PRO-R14-RD-DL-110 | Material Delivery & Site Inspection for Aggregate Base Course of Road Works | 26 | 2026-02-07 | 2026-03-08 | 2025-12-28 | 2026-01-26 | 94236.74 | 95
Pavement Works |  | 52 | 2026-03-09 | 2026-05-11 | 2026-01-27 | 2026-03-31 | 132343.72 | 46
PRO-R14-RD-DL-120 | Material Delivery & Site Inspection of Interlock Tiles for Landscaping | 26 | 2026-03-09 | 2026-04-11 | 2026-01-27 | 2026-02-25 | 55180.6 | 72
PRO-R14-RD-DL-130 | Material Delivery & Site Inspection of Curbstones for Landscaping | 26 | 2026-04-12 | 2026-05-11 | 2026-02-26 | 2026-03-31 | 77163.12 | 46
Bituminous Construction |  | 52 | 2026-05-12 | 2026-07-15 | 2026-04-01 | 2026-06-04 | 265353.86 | 33
PRO-R14-RD-DL-160 | Material Delivery & Site Inspection for Prime Coat of Road Works | 26 | 2026-05-12 | 2026-06-15 | 2026-04-01 | 2026-04-30 | 53070.75 | 59
PRO-R14-RD-DL-170 | Material Delivery & Site Inspection for Bituminous Base & Wearing Courses of Road Works | 26 | 2026-06-16 | 2026-07-15 | 2026-05-02 | 2026-06-04 | 212283.11 | 20
Traffic Signs Boards and Roads Marking |  | 52 | 2026-07-16 | 2026-09-14 | 2026-06-06 | 2026-08-04 | 12022.34 | -6
PRO-R14-RD-DL-140 | Material Delivery & Site Inspection of Traffic Signs Boards For Road Works | 26 | 2026-07-16 | 2026-08-15 | 2026-06-06 | 2026-07-05 | 3361.6 | 20
PRO-R14-RD-DL-150 | Material Delivery & Site Inspection of Road Markings For Road Works | 26 | 2026-08-16 | 2026-09-14 | 2026-07-06 | 2026-08-04 | 8660.74 | -6
Road 09 Local 2 ( 2278 LM ) |  | 232 | 2026-01-10 | 2026-10-15 | 2025-12-28 | 2026-09-03 | 1301797.96 | -6
Pre-Bituminous Construction |  | 76 | 2026-01-10 | 2026-04-11 | 2025-12-28 | 2026-02-25 | 353471.42 | 95
PRO-R09-RD-DL-100 | Material Delivery & Site Inspection for Subgrade of Road Works | 26 | 2026-01-10 | 2026-02-08 | 2025-12-28 | 2026-01-26 | 135248.4 | 131
PRO-R09-RD-DL-110 | Material Delivery & Site Inspection for Aggregate Base Course of Road Works | 26 | 2026-03-09 | 2026-04-11 | 2026-01-27 | 2026-02-25 | 218223.02 | 95
Pavement Works |  | 52 | 2026-04-12 | 2026-06-15 | 2026-02-26 | 2026-04-30 | 306315.32 | 46
PRO-R09-RD-DL-120 | Material Delivery & Site Inspection of Interlock Tiles for Landscaping | 26 | 2026-04-12 | 2026-05-11 | 2026-02-26 | 2026-03-31 | 127629.56 | 72
PRO-R09-RD-DL-130 | Material Delivery & Site Inspection of Curbstones for Landscaping | 26 | 2026-05-12 | 2026-06-15 | 2026-04-01 | 2026-04-30 | 178685.76 | 46
Bituminous Construction |  | 52 | 2026-06-16 | 2026-08-15 | 2026-05-02 | 2026-07-05 | 614480.1 | 33
PRO-R09-RD-DL-160 | Material Delivery & Site Inspection for Prime Coat of Road Works | 26 | 2026-06-16 | 2026-07-15 | 2026-05-02 | 2026-06-04 | 122896.26 | 59
PRO-R09-RD-DL-170 | Material Delivery & Site Inspection for Bituminous Base & Wearing Courses of Road Works | 26 | 2026-07-16 | 2026-08-15 | 2026-06-06 | 2026-07-05 | 491583.84 | 20
Traffic Signs Boards and Roads Marking |  | 52 | 2026-08-16 | 2026-10-15 | 2026-07-06 | 2026-09-03 | 27531.13 | -6
PRO-R09-RD-DL-140 | Material Delivery & Site Inspection of Traffic Signs Boards For Road Works | 26 | 2026-08-16 | 2026-09-14 | 2026-07-06 | 2026-08-04 | 7475.6 | 20
PRO-R09-RD-DL-150 | Material Delivery & Site Inspection of Road Markings For Road Works | 26 | 2026-09-15 | 2026-10-15 | 2026-08-05 | 2026-09-03 | 20055.53 | -6
Road 11 Local 1 ( 670 LM ) |  | 232 | 2026-02-09 | 2026-11-15 | 2026-01-27 | 2026-10-05 | 380782.96 | -6
Pre-Bituminous Construction |  | 76 | 2026-02-09 | 2026-05-11 | 2026-01-27 | 2026-03-31 | 103435.39 | 95
PRO-R11-RD-DL-100 | Material Delivery & Site Inspection for Subgrade of Road Works | 26 | 2026-02-09 | 2026-03-10 | 2026-01-27 | 2026-02-25 | 39577.4 | 131
PRO-R11-RD-DL-110 | Material Delivery & Site Inspection for Aggregate Base Course of Road Works | 26 | 2026-04-12 | 2026-05-11 | 2026-02-26 | 2026-03-31 | 63857.99 | 95
Pavement Works |  | 52 | 2026-05-12 | 2026-07-15 | 2026-04-01 | 2026-06-04 | 89579.04 | 62
PRO-R11-RD-DL-120 | Material Delivery & Site Inspection of Interlock Tiles for Landscaping | 26 | 2026-05-12 | 2026-06-15 | 2026-04-01 | 2026-04-30 | 37290.72 | 88
PRO-R11-RD-DL-130 | Material Delivery & Site Inspection of Curbstones for Landscaping | 26 | 2026-06-16 | 2026-07-15 | 2026-05-02 | 2026-06-04 | 52288.32 | 46
Bituminous Construction |  | 52 | 2026-07-16 | 2026-09-14 | 2026-06-06 | 2026-08-04 | 179814.16 | 36
PRO-R11-RD-DL-160 | Material Delivery & Site Inspection for Prime Coat of Road Works | 26 | 2026-07-16 | 2026-08-15 | 2026-06-06 | 2026-07-05 | 35962.81 | 59
PRO-R11-RD-DL-170 | Material Delivery & Site Inspection for Bituminous Base & Wearing Courses of Road Works | 26 | 2026-08-16 | 2026-09-14 | 2026-07-06 | 2026-08-04 | 143851.35 | 36
Traffic Signs Boards and Roads Marking |  | 52 | 2026-09-15 | 2026-11-15 | 2026-08-05 | 2026-10-05 | 7954.37 | -6
PRO-R11-RD-DL-140 | Material Delivery & Site Inspection of Traffic Signs Boards For Road Works | 26 | 2026-09-15 | 2026-10-15 | 2026-08-05 | 2026-09-03 | 2085.6 | 20
PRO-R11-RD-DL-150 | Material Delivery & Site Inspection of Road Markings For Road Works | 26 | 2026-10-17 | 2026-11-15 | 2026-09-05 | 2026-10-05 | 5868.77 | -6
Sewage Network |  | 412 | 11-Feb-25 A | 2026-06-20 | 2025-02-05 | 2026-03-29 | 2490411.4 | 75
Issuance of Purchase Orders |  | 11 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-05 | 2025-02-17 | 0
Main Line Sections |  | 11 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-05 | 2025-02-17 | 0
PRO-SW-PO-100 | Issuance of Purchase Order for Main Line Pipes of Sewage Network | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
PRO-SW-PO-110 | Issuance of Purchase Order for Manhole of Sewage Network | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-05 | 2025-02-11 | 0
Testing and Finishes |  | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
PRO-SW-PO-120 | Issuance of Purchase Order for Manhole Covers of Sewage Network | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
PRO-SW-PO-140 | Issuance of Purchase Order for Membrane Insulation of Sewage Network | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
Manufacturing of Material |  | 192 | 12-Feb-25 A | 2025-10-05 | 2025-02-12 | 2025-07-17 | 0 | 95
Main Line Sections |  | 35 | 12-Feb-25 A | 2025-05-13 | 2025-02-12 | 2025-03-25 | 0 | -9
PRO-SW-MF-110 | Manufacturing of Manholes for Sewage Network | 30 | 12-Feb-25 A | 2025-05-13 | 2025-02-12 | 2025-03-19 | 0 | -11
PRO-SW-MF-100 | Manufacturing of Main Line Pipes for Sewage Network | 30 | 15-Feb-25 A | 24-Apr-25 A | 2025-02-18 | 2025-03-25 | 0
Testing and Finishes |  | 120 | 2025-05-13 | 2025-10-05 | 2025-02-18 | 2025-07-17 | 0 | 95
PRO-SW-MF-120 | Manufacturing of Manhole Covers for Sewage Network | 120 | 2025-05-13 | 2025-10-05 | 2025-02-18 | 2025-07-17 | 0 | 69
PRO-SW-MF-140 | Manufacturing of Membrane Insulation for Sewage Network | 120 | 2025-05-13 | 2025-10-05 | 2025-02-18 | 2025-07-17 | 0 | 95
1st Material Delivery & Site Inspection |  | 169 | 19-Mar-25 A | 2025-10-12 | 2025-03-19 | 2025-07-24 | 0 | 95
Main Line Sections |  | 7 | 19-Mar-25 A | 2025-05-14 | 2025-03-19 | 2025-03-26 | 0 | -10
PRO-SW-1DL-100 | 1ST Material Delivery for Main Line Pipes of Sewage Network | 6 | 19-Mar-25 A | 26-Apr-25 A | 2025-03-19 | 2025-03-25 | 0
PRO-SW-1DL-110 | 1ST Material Delivery for Manholes of Sewage Network | 6 | 10-Apr-25 A | 2025-05-14 | 2025-03-20 | 2025-03-26 | 0 | -11
Testing and Finishes |  | 6 | 2025-10-06 | 2025-10-12 | 2025-07-19 | 2025-07-24 | 0 | 95
PRO-SW-1DL-120 | 1ST Material Delivery for Manholes Covers of Sewage Network | 6 | 2025-10-06 | 2025-10-12 | 2025-07-19 | 2025-07-24 | 0 | 69
PRO-SW-1DL-140 | 1ST Material Delivery for Membrane Insulation of Sewage Network | 6 | 2025-10-06 | 2025-10-12 | 2025-07-19 | 2025-07-24 | 0 | 95
Material Delivery & Site Inspection |  | 360 | 13-Apr-25 A | 2026-06-20 | 2025-03-26 | 2026-03-29 | 2490411.4 | 75
Road 18 Local 1 ( 479 LM ) |  | 204 | 13-Apr-25 A | 2025-12-11 | 2025-03-27 | 2025-09-24 | 88831.66 | 69
Main Line Sections |  | 23 | 13-Apr-25 A | 2025-05-15 | 2025-03-27 | 2025-04-23 | 88831.66 | -11
PRO-R18-SW-DL-150 | Material Delivery & Site Inspection of Main Line Pipes for Sewage Network | 10 | 13-Apr-25 A | 28-Apr-25 A | 2025-04-13 | 2025-04-23 | 38527.46
PRO-R18-SW-DL-160 | Material Delivery & Site Inspection of Manholes for Sewage Network | 5 | 22-Apr-25 A | 2025-05-15 | 2025-03-27 | 2025-04-12 | 50304.2 | -11
Testing and Finishes |  | 52 | 2025-10-13 | 2025-12-11 | 2025-07-26 | 2025-09-24 | 0 | 69
PRO-R18-SW-DL-170 | Material Delivery & Site Inspection of Manholes Covers for Sewage Network | 26 | 2025-10-13 | 2025-11-11 | 2025-07-26 | 2025-08-24 | 0 | 69
PRO-R18-SW-DL-190 | Material Delivery & Site Inspection of Membrane Insulation for Sewage Network | 26 | 2025-11-12 | 2025-12-11 | 2025-08-25 | 2025-09-24 | 0 | 69
Road 17 Local 1 ( 500 LM ) |  | 201 | 2025-05-17 | 2026-01-11 | 2025-04-13 | 2025-10-25 | 85920.49 | 69
Main Line Sections |  | 15 | 2025-05-17 | 2025-06-02 | 2025-04-13 | 2025-05-10 | 85920.49 | -7
PRO-R17-SW-DL-100 | Material Delivery & Site Inspection of Main Line Pipes for Sewage Network | 14 | 2025-05-17 | 2025-06-01 | 2025-04-24 | 2025-05-10 | 46551.89 | -6
PRO-R17-SW-DL-110 | Material Delivery & Site Inspection of Manholes for Sewage Network | 15 | 2025-05-17 | 2025-06-02 | 2025-04-13 | 2025-04-29 | 39368.6 | -7
Testing and Finishes |  | 52 | 2025-11-12 | 2026-01-11 | 2025-08-25 | 2025-10-25 | 0 | 69
PRO-R17-SW-DL-120 | Material Delivery & Site Inspection of Manholes Covers for Sewage Network | 26 | 2025-11-12 | 2025-12-11 | 2025-08-25 | 2025-09-24 | 0 | 92
PRO-R17-SW-DL-130 | Material Delivery & Site Inspection of Membrane Insulation for Sewage Network | 26 | 2025-12-13 | 2026-01-11 | 2025-09-25 | 2025-10-25 | 0 | 69
Road 16 Local 1 ( 527 LM ) |  | 213 | 2025-06-02 | 2026-02-10 | 2025-04-30 | 2025-11-24 | 86366.8 | 69
Main Line Sections |  | 16 | 2025-06-02 | 2025-06-24 | 2025-04-30 | 2025-05-26 | 86366.8 | -2
PRO-R16-SW-DL-100 | Material Delivery & Site Inspection of Main Line Pipes for Sewage Network | 14 | 2025-06-02 | 2025-06-22 | 2025-05-11 | 2025-05-26 | 44427.6 | 0
PRO-R16-SW-DL-110 | Material Delivery & Site Inspection of Manholes for Sewage Network | 15 | 2025-06-03 | 2025-06-24 | 2025-04-30 | 2025-05-17 | 41939.2 | -2
Testing and Finishes |  | 52 | 2025-12-13 | 2026-02-10 | 2025-09-25 | 2025-11-24 | 0 | 69
PRO-R16-SW-DL-120 | Material Delivery & Site Inspection of Manholes Covers for Sewage Network | 26 | 2025-12-13 | 2026-01-11 | 2025-09-25 | 2025-10-25 | 0 | 92
PRO-R16-SW-DL-130 | Material Delivery & Site Inspection of Membrane Insulation for Sewage Network | 26 | 2026-01-12 | 2026-02-10 | 2025-10-26 | 2025-11-24 | 0 | 69
Road 15 Local 1 ( 556 LM ) |  | 225 | 2025-06-23 | 2026-03-12 | 2025-05-18 | 2025-12-24 | 134073.5 | 69
Main Line Sections |  | 17 | 2025-06-23 | 2025-07-12 | 2025-05-18 | 2025-06-16 | 134073.5 | 3
PRO-R15-SW-DL-100 | Material Delivery & Site Inspection of Main Line Pipes for Sewage Network | 14 | 2025-06-23 | 2025-07-08 | 2025-05-27 | 2025-06-16 | 61994.1 | 6
PRO-R15-SW-DL-110 | Material Delivery & Site Inspection of Manholes for Sewage Network | 15 | 2025-06-25 | 2025-07-12 | 2025-05-18 | 2025-06-03 | 72079.4 | 3
Testing and Finishes |  | 52 | 2026-01-12 | 2026-03-12 | 2025-10-26 | 2025-12-24 | 0 | 69
PRO-R15-SW-DL-120 | Material Delivery & Site Inspection of Manholes Covers for Sewage Network | 26 | 2026-01-12 | 2026-02-10 | 2025-10-26 | 2025-11-24 | 0 | 92
PRO-R15-SW-DL-130 | Material Delivery & Site Inspection of Membrane Insulation for Sewage Network | 26 | 2026-02-11 | 2026-03-12 | 2025-11-25 | 2025-12-24 | 0 | 69
Road 10 Local 2 ( 2352 LM ) |  | 237 | 2025-07-09 | 2026-04-15 | 2025-06-04 | 2026-01-24 | 459098.91 | 69
Main Line Sections |  | 18 | 2025-07-09 | 2025-07-29 | 2025-06-04 | 2025-07-02 | 459098.91 | 18
PRO-R10-SW-DL-100 | Material Delivery & Site Inspection of Main Line Pipes for Sewage Network | 14 | 2025-07-09 | 2025-07-24 | 2025-06-17 | 2025-07-02 | 345202.71 | 20
PRO-R10-SW-DL-110 | Material Delivery & Site Inspection of Manholes for Sewage Network | 15 | 2025-07-13 | 2025-07-29 | 2025-06-04 | 2025-06-25 | 113896.2 | 18
Testing and Finishes |  | 52 | 2026-02-11 | 2026-04-15 | 2025-11-25 | 2026-01-24 | 0 | 69
PRO-R10-SW-DL-120 | Material Delivery & Site Inspection of Manholes Covers for Sewage Network | 26 | 2026-02-11 | 2026-03-12 | 2025-11-25 | 2025-12-24 | 0 | 92
PRO-R10-SW-DL-130 | Material Delivery & Site Inspection of Membrane Insulation for Sewage Network | 26 | 2026-03-14 | 2026-04-15 | 2025-12-25 | 2026-01-24 | 0 | 69
Road 14 Local 1 ( 584 LM ) |  | 249 | 2025-07-26 | 2026-05-16 | 2025-06-26 | 2026-02-23 | 144627.84 | 69
Main Line Sections |  | 19 | 2025-07-26 | 2025-08-16 | 2025-06-26 | 2025-07-19 | 144627.84 | 33
PRO-R14-SW-DL-100 | Material Delivery & Site Inspection of Main Line Pipes for Sewage Network | 14 | 2025-07-26 | 2025-08-10 | 2025-07-03 | 2025-07-19 | 92919.44 | 36
PRO-R14-SW-DL-110 | Material Delivery & Site Inspection of Manholes for Sewage Network | 15 | 2025-07-30 | 2025-08-16 | 2025-06-26 | 2025-07-13 | 51708.4 | 33
Testing and Finishes |  | 52 | 2026-03-14 | 2026-05-16 | 2025-12-25 | 2026-02-23 | 0 | 69
PRO-R14-SW-DL-120 | Material Delivery & Site Inspection of Manholes Covers for Sewage Network | 26 | 2026-03-14 | 2026-04-15 | 2025-12-25 | 2026-01-24 | 0 | 92
PRO-R14-SW-DL-130 | Material Delivery & Site Inspection of Membrane Insulation for Sewage Network | 26 | 2026-04-16 | 2026-05-16 | 2026-01-25 | 2026-02-23 | 0 | 69
Road 09 Local 2 ( 2278 LM ) |  | 164 | 2025-05-13 | 2025-11-25 | 2025-03-26 | 2025-09-07 | 863910 | 245
Main Line Sections |  | 10 | 2025-05-13 | 2025-05-24 | 2025-03-26 | 2025-04-10 | 863910 | 75
PRO-R09-SW-DL-100 | Material Delivery & Site Inspection of Main Line Pipes for Rising Main Network | 10 | 2025-05-13 | 2025-05-24 | 2025-03-26 | 2025-04-10 | 621811.4 | 70
PRO-R09-SW-DL-110 | Material Delivery & Site Inspection of Manholes for Rising Main Network | 7 | 2025-05-15 | 2025-05-22 | 2025-03-27 | 2025-04-08 | 242098.6 | 76
Testing and Finishes |  | 38 | 2025-10-13 | 2025-11-25 | 2025-07-26 | 2025-09-07 | 0 | 245
PRO-R09-SW-DL-120 | Material Delivery & Site Inspection of Manholes Covers for Rising Main Network | 38 | 2025-10-13 | 2025-11-25 | 2025-07-26 | 2025-09-07 | 0 | 229
PRO-R09-SW-DL-130 | Material Delivery & Site Inspection of Membrane Insulation for Rising Main Network | 38 | 2025-10-13 | 2025-11-25 | 2025-07-26 | 2025-09-07 | 0 | 245
Road 11 Local 1 ( 670 LM ) |  | 261 | 2025-08-11 | 2026-06-20 | 2025-07-14 | 2026-03-29 | 627582.2 | 69
Main Line Sections |  | 20 | 2025-08-11 | 2025-09-02 | 2025-07-14 | 2025-08-04 | 627582.2 | 38
PRO-R11-SW-DL-100 | Material Delivery & Site Inspection of Main Line Pipes for Sewage Network | 14 | 2025-08-11 | 2025-08-26 | 2025-07-20 | 2025-08-04 | 541465.4 | 42
PRO-R11-SW-DL-110 | Material Delivery & Site Inspection of Manholes for Sewage Network | 15 | 2025-08-17 | 2025-09-02 | 2025-07-14 | 2025-07-30 | 86116.8 | 38
Testing and Finishes |  | 52 | 2026-04-16 | 2026-06-20 | 2026-01-25 | 2026-03-29 | 0 | 69
PRO-R11-SW-DL-120 | Material Delivery & Site Inspection of Manholes Covers for Sewage Network | 26 | 2026-04-16 | 2026-05-16 | 2026-01-25 | 2026-02-23 | 0 | 92
PRO-R11-SW-DL-130 | Material Delivery & Site Inspection of Membrane Insulation for Sewage Network | 26 | 2026-05-17 | 2026-06-20 | 2026-02-24 | 2026-03-29 | 0 | 69
Storm Drainage Network |  | 392 | 11-Feb-25 A | 2026-06-02 | 2025-02-11 | 2026-03-29 | 4387027.4 | 94
Issuance of Purchase Orders |  | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
Main Line Sections |  | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
PRO-SD-PO-100 | Issuance of Purchase Order for Manholes of Storm Drainage Network | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
PRO-SD-PO-110 | Issuance of Purchase Order for Main Line Pipes of Storm Drainage Network | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
Catch Basin Sections |  | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
PRO-SD-PO-130 | Issuance of Purchase Order for Catch Basins of Storm Drainage Network | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
PRO-SD-PO-150 | Issuance of Purchase Order for Catch Basin Pipes of Storm Drainage Network | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
Testing and Finishes |  | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
PRO-SD-PO-120 | Issuance of Purchase Order for Manhole Covers of Storm Drainage Network | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
PRO-SD-PO-140 | Issuance of Purchase Order for Catch Basin Covers of Storm Drainage Network | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
PRO-SD-PO-160 | Issuance of Purchase Order for Epoxy Insulation of Storm Drainage Network | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
Manufacturing of Material |  | 120 | 18-Feb-25 A | 2025-09-16 | 2025-02-18 | 2025-07-17 | 0 | 94
Main Line Sections |  | 50 | 18-Feb-25 A | 2025-06-24 | 2025-02-18 | 2025-04-22 | 0 | 29
PRO-SD-MF-100 | Manufacturing of Materials for Manholes of Storm Drainage Network | 50 | 18-Feb-25 A | 2025-06-24 | 2025-02-18 | 2025-04-22 | 0 | 29
PRO-SD-MF-110 | Manufacturing of Materials for Main Line Pipes of Storm Drainage Network | 40 | 18-Feb-25 A | 2025-05-28 | 2025-02-18 | 2025-04-10 | 0 | -9
Catch Basin Sections |  | 50 | 18-Feb-25 A | 2025-06-26 | 2025-02-18 | 2025-04-22 | 0 | 41
PRO-SD-MF-130 | Manufacturing of Materials for Catch Basins of Storm Drainage Network | 50 | 18-Feb-25 A | 2025-06-26 | 2025-02-18 | 2025-04-22 | 0 | 39
PRO-SD-MF-150 | Manufacturing of Materials for Catch Basin Pipes of Storm Drainage Network | 50 | 18-Feb-25 A | 2025-06-26 | 2025-02-18 | 2025-04-22 | 0 | 41
Testing and Finishes |  | 120 | 18-Feb-25 A | 2025-09-16 | 2025-02-18 | 2025-07-17 | 0 | 94
PRO-SD-MF-120 | Manufacturing of Materials for Manhole Covers of Storm Drainage Network | 120 | 18-Feb-25 A | 2025-09-16 | 2025-02-18 | 2025-07-17 | 0 | 74
PRO-SD-MF-140 | Manufacturing of Materials for Catch Basin Covers of Storm Drainage Network | 120 | 18-Feb-25 A | 2025-09-16 | 2025-02-18 | 2025-07-17 | 0 | 82
PRO-SD-MF-160 | Manufacturing of Materials for Epoxy Insulation of Storm Drainage Network | 120 | 18-Feb-25 A | 2025-09-16 | 2025-02-18 | 2025-07-17 | 0 | 94
1st Material Delivery & Site Inspection |  | 108 | 29-Apr-25 A | 2025-09-24 | 2025-04-12 | 2025-07-24 | 0 | 94
Main Line Sections |  | 36 | 29-Apr-25 A | 2025-07-01 | 2025-04-12 | 2025-04-29 | 0 | 29
PRO-SD-1DL-110 | 1ST Material Delivery for Main Line Pipes of Storm Drainage Network | 6 | 29-Apr-25 A | 30-Apr-25 A | 2025-04-12 | 2025-04-17 | 0
PRO-SD-1DL-100 | 1ST Material Delivery for Manholes of Storm Drainage Network | 6 | 2025-06-25 | 2025-07-01 | 2025-04-23 | 2025-04-29 | 0 | 29
Catch Basin Sections |  | 6 | 2025-06-28 | 2025-07-03 | 2025-04-23 | 2025-04-29 | 0 | 41
PRO-SD-1DL-120 | 1ST Material Delivery for Catch Basin Pipes of Storm Drainage Network | 6 | 2025-06-28 | 2025-07-03 | 2025-04-23 | 2025-04-29 | 0 | 41
PRO-SD-1DL-130 | 1ST Material Delivery for Catch Basins of Storm Drainage Network | 6 | 2025-06-28 | 2025-07-03 | 2025-04-23 | 2025-04-29 | 0 | 39
Testing and Finishes |  | 6 | 2025-09-17 | 2025-09-24 | 2025-07-19 | 2025-07-24 | 0 | 94
PRO-SD-1DL-140 | 1ST Material Delivery for Manholes Covers of Storm Drainage Network | 6 | 2025-09-17 | 2025-09-24 | 2025-07-19 | 2025-07-24 | 0 | 74
PRO-SD-1DL-150 | 1ST Material Delivery for Catch Basin Covers of Storm Drainage Network | 6 | 2025-09-17 | 2025-09-24 | 2025-07-19 | 2025-07-24 | 0 | 82
PRO-SD-1DL-160 | 1ST Material Delivery for Epoxy Insulation of Storm Drainage Network | 6 | 2025-09-17 | 2025-09-24 | 2025-07-19 | 2025-07-24 | 0 | 94
Material Delivery & Site Inspection |  | 310 | 01-May-25 A | 2026-06-02 | 2025-04-19 | 2026-03-29 | 4387027.4 | 94
Road 18 Local 1 ( 479 LM ) |  | 128 | 01-May-25 A | 2025-10-25 | 2025-04-19 | 2025-08-24 | 382010.27 | 94
Main Line Sections |  | 50 | 01-May-25 A | 2025-07-24 | 2025-04-19 | 2025-05-22 | 296268.03 | 29
PRO-R18-SD-DL-180 | Material Delivery & Site Inspection of Main Line Pipes of Storm Drainage Network | 17 | 01-May-25 A | 2025-06-22 | 2025-04-19 | 2025-05-07 | 244450.03 | -9
PRO-R18-SD-DL-170 | Material Delivery & Site Inspection of Manholes of Storm Drainage Network | 20 | 2025-07-02 | 2025-07-24 | 2025-04-30 | 2025-05-22 | 51818 | 29
Catch Basin Sections |  | 26 | 2025-07-05 | 2025-08-03 | 2025-04-30 | 2025-05-29 | 85742.24 | 41
PRO-R18-SD-DL-200 | Material Delivery & Site Inspection of Catch Basins for Storm Drainage Network | 26 | 2025-07-05 | 2025-08-03 | 2025-04-30 | 2025-05-29 | 85742.24 | 39
PRO-R18-SD-DL-220 | Material Delivery & Site Inspection of Catch Basin Pipes for Storm Drainage Network | 26 | 2025-07-05 | 2025-08-03 | 2025-04-30 | 2025-05-29 | 0 | 41
Testing and Finishes |  | 26 | 2025-09-25 | 2025-10-25 | 2025-07-26 | 2025-08-24 | 0 | 94
PRO-R18-SD-DL-190 | Material Delivery & Site Inspection of Manholes Covers for Storm Drainage Network | 26 | 2025-09-25 | 2025-10-25 | 2025-07-26 | 2025-08-24 | 0 | 74
PRO-R18-SD-DL-210 | Material Delivery & Site Inspection of Catch Basin Covers for Storm Drainage Network | 26 | 2025-09-25 | 2025-10-25 | 2025-07-26 | 2025-08-24 | 0 | 82
PRO-R18-SD-DL-230 | Material Delivery & Site Inspection of Epoxy Insulation for Storm Drainage Network | 26 | 2025-09-25 | 2025-10-25 | 2025-07-26 | 2025-08-24 | 0 | 94
Road 17 Local 1 ( 500 LM ) |  | 132 | 2025-06-23 | 2025-11-24 | 2025-05-08 | 2025-09-24 | 320555.14 | 114
Main Line Sections |  | 48 | 2025-06-23 | 2025-08-17 | 2025-05-08 | 2025-06-19 | 247434.9 | 198
PRO-R17-SD-DL-120 | Material Delivery & Site Inspection of Main Line Pipes of Storm Drainage Network | 17 | 2025-06-23 | 2025-07-12 | 2025-05-08 | 2025-05-27 | 209769.3 | -9
PRO-R17-SD-DL-100 | Material Delivery & Site Inspection of Manholes of Storm Drainage Network | 20 | 2025-07-26 | 2025-08-17 | 2025-05-24 | 2025-06-19 | 37665.6 | 198
Catch Basin Sections |  | 26 | 2025-08-04 | 2025-09-02 | 2025-05-31 | 2025-07-03 | 73120.24 | 54
PRO-R17-SD-DL-130 | Material Delivery & Site Inspection of Catch Basins for Storm Drainage Network | 26 | 2025-08-04 | 2025-09-02 | 2025-05-31 | 2025-07-03 | 73120.24 | 39
PRO-R17-SD-DL-110 | Material Delivery & Site Inspection of Catch Basin Pipes for Storm Drainage Network | 26 | 2025-08-04 | 2025-09-02 | 2025-05-31 | 2025-07-03 | 0 | 54
Testing and Finishes |  | 26 | 2025-10-26 | 2025-11-24 | 2025-08-25 | 2025-09-24 | 0 | 94
PRO-R17-SD-DL-140 | Material Delivery & Site Inspection of Manholes Covers for Storm Drainage Network | 26 | 2025-10-26 | 2025-11-24 | 2025-08-25 | 2025-09-24 | 0 | 74
PRO-R17-SD-DL-150 | Material Delivery & Site Inspection of Catch Basin Covers for Storm Drainage Network | 26 | 2025-10-26 | 2025-11-24 | 2025-08-25 | 2025-09-24 | 0 | 82
PRO-R17-SD-DL-160 | Material Delivery & Site Inspection of Epoxy Insulation for Storm Drainage Network | 26 | 2025-10-26 | 2025-11-24 | 2025-08-25 | 2025-09-24 | 0 | 94
Road 16 Local 1 ( 527 LM ) |  | 141 | 2025-07-13 | 2025-12-24 | 2025-05-28 | 2025-10-25 | 298252.62 | 108
Main Line Sections |  | 51 | 2025-07-13 | 2025-09-09 | 2025-05-28 | 2025-07-13 | 218475.02 | 198
PRO-R16-SD-DL-120 | Material Delivery & Site Inspection of Main Line Pipes of Storm Drainage Network | 17 | 2025-07-13 | 2025-07-31 | 2025-05-28 | 2025-06-21 | 178477.62 | -9
PRO-R16-SD-DL-100 | Material Delivery & Site Inspection of Manholes of Storm Drainage Network | 20 | 2025-08-18 | 2025-09-09 | 2025-06-21 | 2025-07-13 | 39997.4 | 198
Catch Basin Sections |  | 26 | 2025-09-03 | 2025-10-04 | 2025-07-05 | 2025-08-03 | 79777.6 | 54
PRO-R16-SD-DL-130 | Material Delivery & Site Inspection of Catch Basins for Storm Drainage Network | 26 | 2025-09-03 | 2025-10-04 | 2025-07-05 | 2025-08-03 | 79777.6 | 39
PRO-R16-SD-DL-110 | Material Delivery & Site Inspection of Catch Basin Pipes for Storm Drainage Network | 26 | 2025-09-03 | 2025-10-04 | 2025-07-05 | 2025-08-03 | 0 | 54
Testing and Finishes |  | 26 | 2025-11-25 | 2025-12-24 | 2025-09-25 | 2025-10-25 | 0 | 94
PRO-R16-SD-DL-140 | Material Delivery & Site Inspection of Manholes Covers for Storm Drainage Network | 26 | 2025-11-25 | 2025-12-24 | 2025-09-25 | 2025-10-25 | 0 | 74
PRO-R16-SD-DL-150 | Material Delivery & Site Inspection of Catch Basin Covers for Storm Drainage Network | 26 | 2025-11-25 | 2025-12-24 | 2025-09-25 | 2025-10-25 | 0 | 82
PRO-R16-SD-DL-160 | Material Delivery & Site Inspection of Epoxy Insulation for Storm Drainage Network | 26 | 2025-11-25 | 2025-12-24 | 2025-09-25 | 2025-10-25 | 0 | 94
Road 15 Local 1 ( 556 LM ) |  | 150 | 2025-08-02 | 2026-01-24 | 2025-06-22 | 2025-11-24 | 321352.76 | 108
Main Line Sections |  | 60 | 2025-08-02 | 2025-10-11 | 2025-06-22 | 2025-08-12 | 244937.08 | 198
PRO-R15-SD-DL-120 | Material Delivery & Site Inspection of Main Line Pipes of Storm Drainage Network | 17 | 2025-08-02 | 2025-08-20 | 2025-06-22 | 2025-07-10 | 187810.28 | -9
PRO-R15-SD-DL-100 | Material Delivery & Site Inspection of Manholes of Storm Drainage Network | 26 | 2025-09-10 | 2025-10-11 | 2025-07-14 | 2025-08-12 | 57126.8 | 198
Catch Basin Sections |  | 26 | 2025-10-05 | 2025-11-03 | 2025-08-04 | 2025-09-02 | 76415.68 | 54
PRO-R15-SD-DL-130 | Material Delivery & Site Inspection of Catch Basins for Storm Drainage Network | 26 | 2025-10-05 | 2025-11-03 | 2025-08-04 | 2025-09-02 | 76415.68 | 39
PRO-R15-SD-DL-110 | Material Delivery & Site Inspection of Catch Basin Pipes for Storm Drainage Network | 26 | 2025-10-05 | 2025-11-03 | 2025-08-04 | 2025-09-02 | 0 | 54
Testing and Finishes |  | 26 | 2025-12-25 | 2026-01-24 | 2025-10-26 | 2025-11-24 | 0 | 94
PRO-R15-SD-DL-140 | Material Delivery & Site Inspection of Manholes Covers for Storm Drainage Network | 26 | 2025-12-25 | 2026-01-24 | 2025-10-26 | 2025-11-24 | 0 | 74
PRO-R15-SD-DL-150 | Material Delivery & Site Inspection of Catch Basin Covers for Storm Drainage Network | 26 | 2025-12-25 | 2026-01-24 | 2025-10-26 | 2025-11-24 | 0 | 82
PRO-R15-SD-DL-160 | Material Delivery & Site Inspection of Epoxy Insulation for Storm Drainage Network | 26 | 2025-12-25 | 2026-01-24 | 2025-10-26 | 2025-11-24 | 0 | 94
Road 10 Local 2 ( 2352 LM ) |  | 159 | 2025-08-21 | 2026-02-23 | 2025-07-12 | 2025-12-24 | 1016364.63 | 108
Main Line Sections |  | 69 | 2025-08-21 | 2025-11-10 | 2025-07-12 | 2025-09-11 | 721889.11 | 198
PRO-R10-SD-DL-120 | Material Delivery & Site Inspection of Main Line Pipes of Storm Drainage Network | 17 | 2025-08-21 | 2025-09-09 | 2025-07-12 | 2025-07-30 | 460756.71 | -9
PRO-R10-SD-DL-100 | Material Delivery & Site Inspection of Manholes of Storm Drainage Network | 26 | 2025-10-11 | 2025-11-10 | 2025-08-12 | 2025-09-11 | 261132.4 | 198
Catch Basin Sections |  | 26 | 2025-11-04 | 2025-12-03 | 2025-09-03 | 2025-10-04 | 294475.52 | 54
PRO-R10-SD-DL-130 | Material Delivery & Site Inspection of Catch Basins for Storm Drainage Network | 26 | 2025-11-04 | 2025-12-03 | 2025-09-03 | 2025-10-04 | 294475.52 | 44
PRO-R10-SD-DL-110 | Material Delivery & Site Inspection of Catch Basin Pipes for Storm Drainage Network | 26 | 2025-11-04 | 2025-12-03 | 2025-09-03 | 2025-10-04 | 0 | 54
Testing and Finishes |  | 26 | 2026-01-25 | 2026-02-23 | 2025-11-25 | 2025-12-24 | 0 | 94
PRO-R10-SD-DL-140 | Material Delivery & Site Inspection of Manholes Covers for Storm Drainage Network | 26 | 2026-01-25 | 2026-02-23 | 2025-11-25 | 2025-12-24 | 0 | 74
PRO-R10-SD-DL-150 | Material Delivery & Site Inspection of Catch Basin Covers for Storm Drainage Network | 26 | 2026-01-25 | 2026-02-23 | 2025-11-25 | 2025-12-24 | 0 | 82
PRO-R10-SD-DL-160 | Material Delivery & Site Inspection of Epoxy Insulation for Storm Drainage Network | 26 | 2026-01-25 | 2026-02-23 | 2025-11-25 | 2025-12-24 | 0 | 94
Road 14 Local 1 ( 584 LM ) |  | 168 | 2025-09-10 | 2026-03-29 | 2025-07-31 | 2026-01-24 | 639796.96 | 108
Main Line Sections |  | 78 | 2025-09-10 | 2025-12-10 | 2025-07-31 | 2025-10-13 | 484794.08 | 198
PRO-R14-SD-DL-120 | Material Delivery & Site Inspection of Main Line Pipes of Storm Drainage Network | 17 | 2025-09-10 | 2025-09-30 | 2025-07-31 | 2025-08-19 | 331242.08 | -9
PRO-R14-SD-DL-100 | Material Delivery & Site Inspection of Manholes of Storm Drainage Network | 26 | 2025-11-10 | 2025-12-10 | 2025-09-11 | 2025-10-13 | 153552 | 198
Catch Basin Sections |  | 26 | 2025-12-04 | 2026-01-03 | 2025-10-05 | 2025-11-03 | 155002.88 | 112
PRO-R14-SD-DL-130 | Material Delivery & Site Inspection of Catch Basins for Storm Drainage Network | 26 | 2025-12-04 | 2026-01-03 | 2025-10-05 | 2025-11-03 | 155002.88 | 106
PRO-R14-SD-DL-110 | Material Delivery & Site Inspection of Catch Basin Pipes for Storm Drainage Network | 26 | 2025-12-04 | 2026-01-03 | 2025-10-05 | 2025-11-03 | 0 | 112
Testing and Finishes |  | 26 | 2026-02-24 | 2026-03-29 | 2025-12-25 | 2026-01-24 | 0 | 94
PRO-R14-SD-DL-140 | Material Delivery & Site Inspection of Manholes Covers for Storm Drainage Network | 26 | 2026-02-24 | 2026-03-29 | 2025-12-25 | 2026-01-24 | 0 | 74
PRO-R14-SD-DL-150 | Material Delivery & Site Inspection of Catch Basin Covers for Storm Drainage Network | 26 | 2026-02-24 | 2026-03-29 | 2025-12-25 | 2026-01-24 | 0 | 82
PRO-R14-SD-DL-160 | Material Delivery & Site Inspection of Epoxy Insulation for Storm Drainage Network | 26 | 2026-02-24 | 2026-03-29 | 2025-12-25 | 2026-01-24 | 0 | 94
Road 09 Local 2 ( 2278 LM ) |  | 177 | 2025-10-01 | 2026-04-28 | 2025-08-20 | 2026-02-23 | 866899.81 | 94
Main Line Sections |  | 73 | 2025-10-01 | 2025-12-24 | 2025-08-20 | 2025-10-27 | 533382.85 | 198
PRO-R09-SD-DL-120 | Material Delivery & Site Inspection of Main Line Pipes of Storm Drainage Network | 17 | 2025-10-01 | 2025-10-20 | 2025-08-20 | 2025-09-08 | 304195.65 | -9
PRO-R09-SD-DL-100 | Material Delivery & Site Inspection of Manholes of Storm Drainage Network | 12 | 2025-12-10 | 2025-12-24 | 2025-10-13 | 2025-10-27 | 229187.2 | 198
Catch Basin Sections |  | 26 | 2026-01-04 | 2026-02-02 | 2025-11-04 | 2025-12-03 | 333516.96 | 112
PRO-R09-SD-DL-130 | Material Delivery & Site Inspection of Catch Basins for Storm Drainage Network | 26 | 2026-01-04 | 2026-02-02 | 2025-11-04 | 2025-12-03 | 333516.96 | 106
PRO-R09-SD-DL-110 | Material Delivery & Site Inspection of Catch Basin Pipes for Storm Drainage Network | 26 | 2026-01-04 | 2026-02-02 | 2025-11-04 | 2025-12-03 | 0 | 112
Testing and Finishes |  | 26 | 2026-03-30 | 2026-04-28 | 2026-01-25 | 2026-02-23 | 0 | 94
PRO-R09-SD-DL-140 | Material Delivery & Site Inspection of Manholes Covers for Storm Drainage Network | 26 | 2026-03-30 | 2026-04-28 | 2026-01-25 | 2026-02-23 | 0 | 74
PRO-R09-SD-DL-150 | Material Delivery & Site Inspection of Catch Basin Covers for Storm Drainage Network | 26 | 2026-03-30 | 2026-04-28 | 2026-01-25 | 2026-02-23 | 0 | 82
PRO-R09-SD-DL-160 | Material Delivery & Site Inspection of Epoxy Insulation for Storm Drainage Network | 26 | 2026-03-30 | 2026-04-28 | 2026-01-25 | 2026-02-23 | 0 | 94
Road 11 Local 1 ( 670 LM ) |  | 186 | 2025-10-21 | 2026-06-02 | 2025-09-09 | 2026-03-29 | 541795.21 | 94
Main Line Sections |  | 82 | 2025-10-21 | 2026-01-24 | 2025-09-09 | 2025-11-26 | 426966.33 | 198
PRO-R11-SD-DL-120 | Material Delivery & Site Inspection of Main Line Pipes of Storm Drainage Network | 17 | 2025-10-21 | 2025-11-09 | 2025-09-09 | 2025-09-29 | 329435.33 | 14
PRO-R11-SD-DL-100 | Material Delivery & Site Inspection of Manholes of Storm Drainage Network | 26 | 2025-12-24 | 2026-01-24 | 2025-10-27 | 2025-11-26 | 97531 | 198
Catch Basin Sections |  | 26 | 2026-02-03 | 2026-03-04 | 2025-12-04 | 2026-01-03 | 114828.88 | 112
PRO-R11-SD-DL-130 | Material Delivery & Site Inspection of Catch Basins for Storm Drainage Network | 26 | 2026-02-03 | 2026-03-04 | 2025-12-04 | 2026-01-03 | 114828.88 | 106
PRO-R11-SD-DL-110 | Material Delivery & Site Inspection of Catch Basin Pipes for Storm Drainage Network | 26 | 2026-02-03 | 2026-03-04 | 2025-12-04 | 2026-01-03 | 0 | 112
Testing and Finishes |  | 26 | 2026-04-29 | 2026-06-02 | 2026-02-24 | 2026-03-29 | 0 | 94
PRO-R11-SD-DL-140 | Material Delivery & Site Inspection of Manholes Covers for Storm Drainage Network | 26 | 2026-04-29 | 2026-06-02 | 2026-02-24 | 2026-03-29 | 0 | 82
PRO-R11-SD-DL-150 | Material Delivery & Site Inspection of Catch Basin Covers for Storm Drainage Network | 26 | 2026-04-29 | 2026-06-02 | 2026-02-24 | 2026-03-29 | 0 | 82
PRO-R11-SD-DL-160 | Material Delivery & Site Inspection of Epoxy Insulation for Storm Drainage Network | 26 | 2026-04-29 | 2026-06-02 | 2026-02-24 | 2026-03-29 | 0 | 94
Potable Water Network |  | 357 | 11-Feb-25 A | 2026-04-15 | 2025-02-09 | 2026-02-09 | 2044188.4 | 118
Issuance of Purchase Orders |  | 12 | 11-Feb-25 A | 23-Feb-25 A | 2025-02-09 | 2025-02-23 | 0
Main Line Sections |  | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
PRO-PW-PO-100 | Issuance of Purchase Order for Main Line Pipes of Potable Water Network | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
PRO-PW-PO-110 | Issuance of Purchase Order for Valves of Potable Water Network | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
Fire Hydrant |  | 10 | 11-Feb-25 A | 23-Feb-25 A | 2025-02-11 | 2025-02-23 | 0
PRO-PW-PO-120 | Issuance of Purchase Order for Fire Hydrants of Potable Water Network | 10 | 11-Feb-25 A | 23-Feb-25 A | 2025-02-11 | 2025-02-23 | 0
Testing and Finishes |  | 10 | 11-Feb-25 A | 23-Feb-25 A | 2025-02-09 | 2025-02-19 | 0
PRO-PW-PO-130 | Issuance of Purchase Order for Surface Box of Potable Water Network | 10 | 11-Feb-25 A | 23-Feb-25 A | 2025-02-09 | 2025-02-19 | 0
Manufacturing of Material |  | 82 | 18-Feb-25 A | 2025-08-04 | 2025-02-18 | 2025-05-29 | 0 | 118
Main Line Sections |  | 60 | 18-Feb-25 A | 2025-06-29 | 2025-02-18 | 2025-05-04 | 0 | -16
PRO-PW-MF-100 | Manufacturing of Main Line Pipes for Potable Water Network | 60 | 18-Feb-25 A | 2025-06-28 | 2025-02-18 | 2025-05-04 | 0 | -15
PRO-PW-MF-110 | Manufacturing of Valves for Potable Water Network | 60 | 18-Feb-25 A | 2025-06-29 | 2025-02-18 | 2025-05-04 | 0 | -16
Fire Hydrant |  | 60 | 24-Feb-25 A | 2025-07-06 | 2025-02-24 | 2025-05-08 | 0 | -12
PRO-PW-MF-120 | Manufacturing of Fire Hydrants for Potable Water Network | 60 | 24-Feb-25 A | 2025-07-06 | 2025-02-24 | 2025-05-08 | 0 | -12
Testing and Finishes |  | 80 | 24-Feb-25 A | 2025-08-04 | 2025-02-20 | 2025-05-29 | 0 | 118
PRO-PW-MF-130 | Manufacturing for Surface Box of Potable Water Network | 80 | 24-Feb-25 A | 2025-08-04 | 2025-02-20 | 2025-05-29 | 0 | 118
1st Material Delivery & Site Inspection |  | 38 | 2025-06-29 | 2025-08-11 | 2025-05-05 | 2025-06-10 | 0 | 118
Main Line Sections |  | 7 | 2025-06-29 | 2025-07-06 | 2025-05-05 | 2025-05-11 | 0 | -16
PRO-PW-1DL-100 | 1ST Material Delivery for Main Line Pipes of Potable Water Network | 6 | 2025-06-29 | 2025-07-05 | 2025-05-05 | 2025-05-11 | 0 | -15
PRO-PW-1DL-110 | 1ST Material Delivery for Valves of Potable Water Network | 6 | 2025-06-30 | 2025-07-06 | 2025-05-05 | 2025-05-11 | 0 | -16
Fire Hydrant |  | 6 | 2025-07-07 | 2025-07-13 | 2025-05-10 | 2025-05-15 | 0 | -12
PRO-PW-1DL-120 | 1ST Material Delivery for Fire Hydrants of Potable Water Network | 6 | 2025-07-07 | 2025-07-13 | 2025-05-10 | 2025-05-15 | 0 | -12
Testing and Finishes |  | 6 | 2025-08-05 | 2025-08-11 | 2025-05-31 | 2025-06-10 | 0 | 118
PRO-PW-1DL-130 | 1ST Material Delivery for Finishes of Potable Water Network | 6 | 2025-08-05 | 2025-08-11 | 2025-05-31 | 2025-06-10 | 0 | 118
Material Delivery & Site Inspection |  | 240 | 2025-07-06 | 2026-04-15 | 2025-05-12 | 2026-02-09 | 2044188.4 | 118
Road 18 Local 1 ( 479 LM ) |  | 58 | 2025-07-06 | 2025-09-10 | 2025-05-12 | 2025-07-10 | 40698.67 | 118
Main Line Sections |  | 27 | 2025-07-06 | 2025-08-05 | 2025-05-12 | 2025-06-15 | 36176.67 | -16
PRO-R18-PW-DL-140 | Material Delivery & Site Inspection of Main Line Pipes for Potable Water Network | 26 | 2025-07-06 | 2025-08-04 | 2025-05-12 | 2025-06-15 | 30643.87 | -15
PRO-R18-PW-DL-150 | Material Delivery & Site Inspection of Valves for Potable Water Network | 26 | 2025-07-07 | 2025-08-05 | 2025-05-12 | 2025-06-15 | 5532.8 | -16
Fire Hydrant |  | 26 | 2025-07-14 | 2025-08-12 | 2025-05-17 | 2025-06-19 | 4522 | -12
PRO-R18-PW-DL-160 | Material Delivery & Site Inspection of Fire Hydrants for Potable Water Network | 26 | 2025-07-14 | 2025-08-12 | 2025-05-17 | 2025-06-19 | 4522 | -12
Testing and Finishes |  | 26 | 2025-08-12 | 2025-09-10 | 2025-06-11 | 2025-07-10 | 0 | 118
PRO-R18-PW-DL-170 | Material Delivery & Site Inspection for Finishes of Potable Water Network | 26 | 2025-08-12 | 2025-09-10 | 2025-06-11 | 2025-07-10 | 0 | 118
Road 17 Local 1 ( 500 LM ) |  | 58 | 2025-08-05 | 2025-10-12 | 2025-06-16 | 2025-08-10 | 39368.32 | 118
Main Line Sections |  | 27 | 2025-08-05 | 2025-09-04 | 2025-06-16 | 2025-07-15 | 32585.32 | -16
PRO-R17-PW-DL-100 | Material Delivery & Site Inspection of Main Line Pipes for Potable Water Network | 26 | 2025-08-05 | 2025-09-03 | 2025-06-16 | 2025-07-15 | 27052.52 | -15
PRO-R17-PW-DL-110 | Material Delivery & Site Inspection of Valves for Potable Water Network | 26 | 2025-08-06 | 2025-09-04 | 2025-06-16 | 2025-07-15 | 5532.8 | -16
Fire Hydrant |  | 26 | 2025-08-13 | 2025-09-11 | 2025-06-21 | 2025-07-20 | 6783 | -12
PRO-R17-PW-DL-120 | Material Delivery & Site Inspection of Fire Hydrants for Potable Water Network | 26 | 2025-08-13 | 2025-09-11 | 2025-06-21 | 2025-07-20 | 6783 | -12
Testing and Finishes |  | 26 | 2025-09-11 | 2025-10-12 | 2025-07-12 | 2025-08-10 | 0 | 118
PRO-R17-PW-DL-130 | Material Delivery & Site Inspection for Finishes of Potable Water Network | 26 | 2025-09-11 | 2025-10-12 | 2025-07-12 | 2025-08-10 | 0 | 118
Road 16 Local 1 ( 527 LM ) |  | 58 | 2025-09-04 | 2025-11-11 | 2025-07-16 | 2025-09-09 | 41224.23 | 118
Main Line Sections |  | 27 | 2025-09-04 | 2025-10-06 | 2025-07-16 | 2025-08-14 | 32180.23 | -16
PRO-R16-PW-DL-100 | Material Delivery & Site Inspection of Main Line Pipes for Potable Water Network | 26 | 2025-09-04 | 2025-10-05 | 2025-07-16 | 2025-08-14 | 28228.23 | -15
PRO-R16-PW-DL-110 | Material Delivery & Site Inspection of Valves for Potable Water Network | 26 | 2025-09-06 | 2025-10-06 | 2025-07-16 | 2025-08-14 | 3952 | -16
Fire Hydrant |  | 26 | 2025-09-13 | 2025-10-13 | 2025-07-21 | 2025-08-19 | 9044 | -12
PRO-R16-PW-DL-120 | Material Delivery & Site Inspection of Fire Hydrants for Potable Water Network | 26 | 2025-09-13 | 2025-10-13 | 2025-07-21 | 2025-08-19 | 9044 | -12
Testing and Finishes |  | 26 | 2025-10-13 | 2025-11-11 | 2025-08-11 | 2025-09-09 | 0 | 118
PRO-R16-PW-DL-130 | Material Delivery & Site Inspection for Finishes of Potable Water Network | 26 | 2025-10-13 | 2025-11-11 | 2025-08-11 | 2025-09-09 | 0 | 118
Road 15 Local 1 ( 556 LM ) |  | 58 | 2025-10-06 | 2025-12-11 | 2025-08-16 | 2025-10-11 | 43169.07 | 118
Main Line Sections |  | 27 | 2025-10-06 | 2025-11-05 | 2025-08-16 | 2025-09-14 | 34125.07 | -16
PRO-R15-PW-DL-100 | Material Delivery & Site Inspection of Main Line Pipes for Potable Water Network | 26 | 2025-10-06 | 2025-11-04 | 2025-08-16 | 2025-09-14 | 29382.67 | -15
PRO-R15-PW-DL-110 | Material Delivery & Site Inspection of Valves for Potable Water Network | 26 | 2025-10-07 | 2025-11-05 | 2025-08-16 | 2025-09-14 | 4742.4 | -16
Fire Hydrant |  | 26 | 2025-10-14 | 2025-11-12 | 2025-08-20 | 2025-09-18 | 9044 | -12
PRO-R15-PW-DL-120 | Material Delivery & Site Inspection of Fire Hydrants for Potable Water Network | 26 | 2025-10-14 | 2025-11-12 | 2025-08-20 | 2025-09-18 | 9044 | -12
Testing and Finishes |  | 26 | 2025-11-12 | 2025-12-11 | 2025-09-10 | 2025-10-11 | 0 | 118
PRO-R15-PW-DL-130 | Material Delivery & Site Inspection for Finishes of Potable Water Network | 26 | 2025-11-12 | 2025-12-11 | 2025-09-10 | 2025-10-11 | 0 | 118
Road 10 Local 2 ( 2352 LM ) |  | 58 | 2025-11-05 | 2026-01-11 | 2025-09-15 | 2025-11-10 | 1212124.85 | 118
Main Line Sections |  | 27 | 2025-11-05 | 2025-12-06 | 2025-09-15 | 2025-10-15 | 1110873.25 | -16
PRO-R10-PW-DL-100 | Material Delivery & Site Inspection of Main Line Pipes for Potable Water Network | 26 | 2025-11-05 | 2025-12-04 | 2025-09-15 | 2025-10-15 | 895358.85 | -15
PRO-R10-PW-DL-110 | Material Delivery & Site Inspection of Valves for Potable Water Network | 26 | 2025-11-06 | 2025-12-06 | 2025-09-15 | 2025-10-15 | 215514.4 | -16
Fire Hydrant |  | 26 | 2025-11-13 | 2025-12-13 | 2025-09-20 | 2025-10-20 | 33915 | -12
PRO-R10-PW-DL-120 | Material Delivery & Site Inspection of Fire Hydrants for Potable Water Network | 26 | 2025-11-13 | 2025-12-13 | 2025-09-20 | 2025-10-20 | 33915 | -12
Testing and Finishes |  | 26 | 2025-12-13 | 2026-01-11 | 2025-10-12 | 2025-11-10 | 67336.6 | 118
PRO-R10-PW-DL-130 | Material Delivery & Site Inspection for Finishes of Potable Water Network | 26 | 2025-12-13 | 2026-01-11 | 2025-10-12 | 2025-11-10 | 67336.6 | 118
Road 14 Local 1 ( 584 LM ) |  | 58 | 2025-12-06 | 2026-02-10 | 2025-10-16 | 2025-12-10 | 446763 | 118
Main Line Sections |  | 27 | 2025-12-06 | 2026-01-05 | 2025-10-16 | 2025-11-15 | 278913 | -16
PRO-R14-PW-DL-100 | Material Delivery & Site Inspection of Main Line Pipes for Potable Water Network | 26 | 2025-12-06 | 2026-01-04 | 2025-10-16 | 2025-11-15 | 132680 | -15
PRO-R14-PW-DL-110 | Material Delivery & Site Inspection of Valves for Potable Water Network | 26 | 2025-12-07 | 2026-01-05 | 2025-10-16 | 2025-11-15 | 146233 | -16
Fire Hydrant |  | 26 | 2025-12-14 | 2026-01-12 | 2025-10-21 | 2025-11-19 | 15827 | -12
PRO-R14-PW-DL-120 | Material Delivery & Site Inspection of Fire Hydrants for Potable Water Network | 26 | 2025-12-14 | 2026-01-12 | 2025-10-21 | 2025-11-19 | 15827 | -12
Testing and Finishes |  | 26 | 2026-01-12 | 2026-02-10 | 2025-11-11 | 2025-12-10 | 152023 | 118
PRO-R14-PW-DL-130 | Material Delivery & Site Inspection for Finishes of Potable Water Network | 26 | 2026-01-12 | 2026-02-10 | 2025-11-11 | 2025-12-10 | 152023 | 118
Road 09 Local 2 ( 2278 LM ) |  | 58 | 2026-01-05 | 2026-03-12 | 2025-11-16 | 2026-01-10 | 170110.61 | 118
Main Line Sections |  | 27 | 2026-01-05 | 2026-02-04 | 2025-11-16 | 2025-12-15 | 136195.61 | -16
PRO-R09-PW-DL-100 | Material Delivery & Site Inspection of Main Line Pipes for Potable Water Network | 26 | 2026-01-05 | 2026-02-03 | 2025-11-16 | 2025-12-15 | 117110.41 | -15
PRO-R09-PW-DL-110 | Material Delivery & Site Inspection of Valves for Potable Water Network | 26 | 2026-01-06 | 2026-02-04 | 2025-11-16 | 2025-12-15 | 19085.2 | -16
Fire Hydrant |  | 26 | 2026-01-13 | 2026-02-11 | 2025-11-20 | 2025-12-20 | 33915 | -12
PRO-R09-PW-DL-120 | Material Delivery & Site Inspection of Fire Hydrants for Potable Water Network | 26 | 2026-01-13 | 2026-02-11 | 2025-11-20 | 2025-12-20 | 33915 | -12
Testing and Finishes |  | 26 | 2026-02-11 | 2026-03-12 | 2025-12-11 | 2026-01-10 | 0 | 118
PRO-R09-PW-DL-130 | Material Delivery & Site Inspection for Finishes of Potable Water Network | 26 | 2026-02-11 | 2026-03-12 | 2025-12-11 | 2026-01-10 | 0 | 118
Road 11 Local 1 ( 670 LM ) |  | 58 | 2026-02-04 | 2026-04-15 | 2025-12-16 | 2026-02-09 | 50729.64 | 118
Main Line Sections |  | 27 | 2026-02-04 | 2026-03-07 | 2025-12-16 | 2026-01-14 | 39424.64 | -16
PRO-R11-PW-DL-100 | Material Delivery & Site Inspection of Main Line Pipes for Potable Water Network | 26 | 2026-02-04 | 2026-03-05 | 2025-12-16 | 2026-01-14 | 34682.24 | -15
PRO-R11-PW-DL-110 | Material Delivery & Site Inspection of Valves for Potable Water Network | 26 | 2026-02-05 | 2026-03-07 | 2025-12-16 | 2026-01-14 | 4742.4 | -16
Fire Hydrant |  | 26 | 2026-02-12 | 2026-03-14 | 2025-12-21 | 2026-01-19 | 11305 | -12
PRO-R11-PW-DL-120 | Material Delivery & Site Inspection of Fire Hydrants for Potable Water Network | 26 | 2026-02-12 | 2026-03-14 | 2025-12-21 | 2026-01-19 | 11305 | -12
Testing and Finishes |  | 26 | 2026-03-14 | 2026-04-15 | 2026-01-11 | 2026-02-09 | 0 | 118
PRO-R11-PW-DL-130 | Material Delivery & Site Inspection for Finishes of Potable Water Network | 26 | 2026-03-14 | 2026-04-15 | 2026-01-11 | 2026-02-09 | 0 | 118
Irrigation Network |  | 311 | 11-Feb-25 A | 2026-02-19 | 2025-02-11 | 2025-12-21 | 1248317.6 | -6
Issuance of Purchase Orders |  | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
Main Line Pipes |  | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
PRO-IR-PO-100 | Issuance of Purchase Order for Main Line Pipes of Irrigation Network | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
PRO-IR-PO-110 | Issuance of Purchase Order for Valves of Irrigation Network | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
Manufacturing of Material |  | 119 | 18-Feb-25 A | 2025-09-15 | 2025-02-18 | 2025-07-16 | 0 | -6
Main Line Pipes |  | 119 | 18-Feb-25 A | 2025-09-15 | 2025-02-18 | 2025-07-16 | 0 | -6
PRO-IR-MF-100 | Manufacturing of Main Line Pipes for Irrigation Network | 105 | 18-Feb-25 A | 2025-08-27 | 2025-02-18 | 2025-06-30 | 0 | 4
PRO-IR-MF-110 | Manufacturing of Valves for Irrigation Network | 119 | 18-Feb-25 A | 2025-09-15 | 2025-02-18 | 2025-07-16 | 0 | -6
1st Material Delivery & Site Inspection |  | 22 | 2025-08-28 | 2025-09-22 | 2025-07-01 | 2025-07-23 | 0 | -6
Main Line Pipes |  | 22 | 2025-08-28 | 2025-09-22 | 2025-07-01 | 2025-07-23 | 0 | -6
PRO-IR-1DL-100 | 1ST Material Delivery for Main Line Pipes of Irrigation Network | 6 | 2025-08-28 | 2025-09-03 | 2025-07-01 | 2025-07-07 | 0 | 4
PRO-IR-1DL-110 | 1ST Material Delivery for Valves of Irrigation Network | 6 | 2025-09-16 | 2025-09-22 | 2025-07-17 | 2025-07-23 | 0 | -6
Material Delivery & Site Inspection |  | 144 | 2025-09-04 | 2026-02-19 | 2025-07-08 | 2025-12-21 | 1248317.6 | -6
Road 18 Local 1 ( 479 LM ) |  | 32 | 2025-09-04 | 2025-10-12 | 2025-07-08 | 2025-08-11 | 18360.06 | -6
Main Line Pipes |  | 32 | 2025-09-04 | 2025-10-12 | 2025-07-08 | 2025-08-11 | 18360.06 | -6
PRO-R18-IR-DL-120 | Material Delivery & Site Inspection of Main Line Pipes for Irrigation Network | 16 | 2025-09-04 | 2025-09-22 | 2025-07-08 | 2025-07-26 | 13728.26 | 4
PRO-R18-IR-DL-130 | Material Delivery & Site Inspection of Valves for Irrigation Network | 16 | 2025-09-24 | 2025-10-12 | 2025-07-24 | 2025-08-11 | 4631.8 | -6
Road 17 Local 1 ( 500 LM ) |  | 32 | 2025-09-24 | 2025-10-30 | 2025-07-27 | 2025-08-30 | 147191.86 | -6
Main Line Pipes |  | 32 | 2025-09-24 | 2025-10-30 | 2025-07-27 | 2025-08-30 | 147191.86 | -6
PRO-R17-IR-DL-100 | Material Delivery & Site Inspection of Main Line Pipes for Irrigation Network | 16 | 2025-09-24 | 2025-10-12 | 2025-07-27 | 2025-08-13 | 136396.46 | 4
PRO-R17-IR-DL-110 | Material Delivery & Site Inspection of Valves for Irrigation Network | 16 | 2025-10-13 | 2025-10-30 | 2025-08-12 | 2025-08-30 | 10795.4 | -6
Road 16 Local 1 ( 527 LM ) |  | 32 | 2025-10-13 | 2025-11-18 | 2025-08-14 | 2025-09-17 | 20405.88 | -6
Main Line Pipes |  | 32 | 2025-10-13 | 2025-11-18 | 2025-08-14 | 2025-09-17 | 20405.88 | -6
PRO-R16-IR-DL-100 | Material Delivery & Site Inspection of Main Line Pipes for Irrigation Network | 16 | 2025-10-13 | 2025-10-30 | 2025-08-14 | 2025-09-01 | 14931.28 | 4
PRO-R16-IR-DL-110 | Material Delivery & Site Inspection of Valves for Irrigation Network | 16 | 2025-11-01 | 2025-11-18 | 2025-08-31 | 2025-09-17 | 5474.6 | -6
Road 15 Local 1 ( 556 LM ) |  | 32 | 2025-11-01 | 2025-12-07 | 2025-09-02 | 2025-10-07 | 19235.87 | -6
Main Line Pipes |  | 32 | 2025-11-01 | 2025-12-07 | 2025-09-02 | 2025-10-07 | 19235.87 | -6
PRO-R15-IR-DL-100 | Material Delivery & Site Inspection of Main Line Pipes for Irrigation Network | 16 | 2025-11-01 | 2025-11-18 | 2025-09-02 | 2025-09-20 | 15665.87 | 4
PRO-R15-IR-DL-110 | Material Delivery & Site Inspection of Valves for Irrigation Network | 16 | 2025-11-19 | 2025-12-07 | 2025-09-18 | 2025-10-07 | 3570 | -6
Road 10 Local 2 ( 2352 LM ) |  | 32 | 2025-11-19 | 2025-12-25 | 2025-09-21 | 2025-10-26 | 849336.53 | -6
Main Line Pipes |  | 32 | 2025-11-19 | 2025-12-25 | 2025-09-21 | 2025-10-26 | 849336.53 | -6
PRO-R19.2-IR-DL-100 | Material Delivery & Site Inspection of Main Line Pipes for Irrigation Network | 16 | 2025-11-19 | 2025-12-07 | 2025-09-21 | 2025-10-09 | 648983.93 | 4
PRO-R19.2-IR-DL-110 | Material Delivery & Site Inspection of Valves for Irrigation Network | 16 | 2025-12-08 | 2025-12-25 | 2025-10-08 | 2025-10-26 | 200352.6 | -6
Road 14 Local 1 ( 584 LM ) |  | 32 | 2025-12-08 | 2026-01-13 | 2025-10-11 | 2025-11-13 | 87194.13 | -6
Main Line Pipes |  | 32 | 2025-12-08 | 2026-01-13 | 2025-10-11 | 2025-11-13 | 87194.13 | -6
PRO-R14-IR-DL-100 | Material Delivery & Site Inspection of Main Line Pipes for Irrigation Network | 16 | 2025-12-08 | 2025-12-25 | 2025-10-11 | 2025-10-28 | 72793.73 | 4
PRO-R14-IR-DL-110 | Material Delivery & Site Inspection of Valves for Irrigation Network | 16 | 2025-12-27 | 2026-01-13 | 2025-10-27 | 2025-11-13 | 14400.4 | -6
Road 09 Local 2 ( 2278 LM ) |  | 32 | 2025-12-27 | 2026-02-01 | 2025-10-29 | 2025-12-02 | 80006.6 | -6
Main Line Pipes |  | 32 | 2025-12-27 | 2026-02-01 | 2025-10-29 | 2025-12-02 | 80006.6 | -6
PRO-R09-IR-DL-100 | Material Delivery & Site Inspection of Main Line Pipes for Irrigation Network | 16 | 2025-12-27 | 2026-01-13 | 2025-10-29 | 2025-11-16 | 63603 | 4
PRO-R09-IR-DL-110 | Material Delivery & Site Inspection of Valves for Irrigation Network | 16 | 2026-01-14 | 2026-02-01 | 2025-11-15 | 2025-12-02 | 16403.6 | -6
Road 11 Local 1 ( 670 LM ) |  | 32 | 2026-01-14 | 2026-02-19 | 2025-11-17 | 2025-12-21 | 26586.68 | -6
Main Line Pipes |  | 32 | 2026-01-14 | 2026-02-19 | 2025-11-17 | 2025-12-21 | 26586.68 | -6
PRO-R11-IR-DL-140 | Material Delivery & Site Inspection of Main Line Pipes for Irrigation Network | 16 | 2026-01-14 | 2026-02-01 | 2025-11-17 | 2025-12-04 | 18612.48 | 4
PRO-R11-IR-DL-150 | Material Delivery & Site Inspection of Valves for Irrigation Network | 16 | 2026-02-02 | 2026-02-19 | 2025-12-03 | 2025-12-21 | 7974.2 | -6
Medium Voltage Network |  | 373 | 11-Feb-25 A | 2026-05-06 | 2025-02-11 | 2026-03-04 | 885929.15 | 114
Issuance of Purchase Orders |  | 12 | 11-Feb-25 A | 25-Feb-25 A | 2025-02-11 | 2025-02-25 | 0
Cabling Works |  | 12 | 11-Feb-25 A | 25-Feb-25 A | 2025-02-11 | 2025-02-25 | 0
PRO-MV-PO-100 | Issuance of Purchase Order for Medium Voltage Cables of Medium Voltage Network | 12 | 11-Feb-25 A | 25-Feb-25 A | 2025-02-11 | 2025-02-25 | 0
RMU Concrete Works |  | 12 | 11-Feb-25 A | 25-Feb-25 A | 2025-02-11 | 2025-02-25 | 0
PRO-MV-PO-110 | Issuance of Purchase Order for RMU Concrete Foundations of Medium Voltage Network | 12 | 11-Feb-25 A | 25-Feb-25 A | 2025-02-11 | 2025-02-25 | 0
Termination and Testing Works |  | 12 | 11-Feb-25 A | 25-Feb-25 A | 2025-02-11 | 2025-02-25 | 0
PRO-MV-PO-120 | Issuance of Purchase Order for Termination and Joints Kits of Medium Voltage Network | 12 | 11-Feb-25 A | 25-Feb-25 A | 2025-02-11 | 2025-02-25 | 0
Manufacturing of Material |  | 160 | 26-Feb-25 A | 2025-11-17 | 2025-02-26 | 2025-09-09 | 0 | 124
Cabling Works |  | 52 | 26-Feb-25 A | 2025-07-05 | 2025-02-26 | 2025-05-01 | 0 | 50
PRO-MV-MF-100 | Manufacturing of Medium Voltage Cables for Medium Voltage Network | 52 | 26-Feb-25 A | 2025-07-05 | 2025-02-26 | 2025-05-01 | 0 | 50
RMU Concrete Works |  | 160 | 26-Feb-25 A | 2025-11-17 | 2025-02-26 | 2025-09-09 | 0 | 124
PRO-MV-MF-120 | Manufacturing of RMU Concrete Foundations for Medium Voltage Network | 160 | 26-Feb-25 A | 2025-11-17 | 2025-02-26 | 2025-09-09 | 0 | 124
Termination and Testing Works |  | 52 | 26-Feb-25 A | 2025-07-03 | 2025-02-26 | 2025-05-01 | 0 | 139
PRO-MV-MF-110 | Manufacturing of Termination and Joints Kits for Medium Voltage Network | 52 | 26-Feb-25 A | 2025-07-03 | 2025-02-26 | 2025-05-01 | 0 | 139
1st Material Delivery & Site Inspection |  | 168 | 2025-07-05 | 2026-01-17 | 2025-05-03 | 2025-11-10 | 0 | 124
Cabling Works |  | 12 | 2025-07-06 | 2025-07-19 | 2025-05-03 | 2025-05-15 | 0 | 50
PRO-MV-1DL-100 | 1ST Material Delivery for Medium Voltage Cables of Medium Voltage Network | 12 | 2025-07-06 | 2025-07-19 | 2025-05-03 | 2025-05-15 | 0 | 50
RMU Concrete Works |  | 52 | 2025-11-18 | 2026-01-17 | 2025-09-10 | 2025-11-10 | 0 | 124
PRO-MV-1DL-110 | 1ST Material Delivery for RMU Concrete Foundations of Medium Voltage Network | 52 | 2025-11-18 | 2026-01-17 | 2025-09-10 | 2025-11-10 | 0 | 124
Termination and Testing Works |  | 26 | 2025-07-05 | 2025-08-03 | 2025-05-03 | 2025-06-01 | 0 | 139
PRO-MV-1DL-120 | 1ST Material Delivery for Termination and Joints Kits of Medium Voltage Network | 26 | 2025-07-05 | 2025-08-03 | 2025-05-03 | 2025-06-01 | 0 | 139
Material Delivery & Site Inspection |  | 246 | 2025-07-20 | 2026-05-06 | 2025-05-17 | 2026-03-04 | 885929.15 | 114
Road 18 Local 1 ( 479 LM ) |  | 52 | 2025-07-20 | 2025-09-17 | 2025-05-17 | 2025-07-20 | 53120.53 | 126
Cabling Works |  | 26 | 2025-07-20 | 2025-08-18 | 2025-05-17 | 2025-06-19 | 52053.33 | 50
PRO-R18-MV-DL-120 | Material Delivery & Site Inspection of Medium Voltage Cables for Medium Voltage Network | 26 | 2025-07-20 | 2025-08-18 | 2025-05-17 | 2025-06-19 | 52053.33 | 50
Termination and Testing Works |  | 26 | 2025-08-19 | 2025-09-17 | 2025-06-21 | 2025-07-20 | 1067.2 | 126
PRO-R18-MV-DL-130 | Material Delivery & Site Inspection of Termination and Joints Kits for Medium Voltage Network | 26 | 2025-08-19 | 2025-09-17 | 2025-06-21 | 2025-07-20 | 1067.2 | 126
Road 17 Local 1 ( 500 LM ) |  | 220 | 2025-08-19 | 2026-05-06 | 2025-06-21 | 2026-03-04 | 54269.93 | 97
Cabling Works |  | 26 | 2025-08-19 | 2025-09-17 | 2025-06-21 | 2025-07-20 | 53736.33 | 50
PRO-R17-MV-DL-100 | Material Delivery & Site Inspection of Medium Voltage Cables for Medium Voltage Network | 26 | 2025-08-19 | 2025-09-17 | 2025-06-21 | 2025-07-20 | 53736.33 | 50
RMU Concrete Works |  | 38 | 2026-03-24 | 2026-05-06 | 2026-01-20 | 2026-03-04 | 0 | 97
PRO-R17-MV-DL-120 | Material Delivery & Site Inspection of RMU Concrete Foundations for Medium Voltage Network | 38 | 2026-03-24 | 2026-05-06 | 2026-01-20 | 2026-03-04 | 0 | 97
Termination and Testing Works |  | 26 | 2025-09-18 | 2025-10-19 | 2025-07-21 | 2025-08-19 | 533.6 | 126
PRO-R17-MV-DL-110 | Material Delivery & Site Inspection of Termination and Joints Kits for Medium Voltage Network | 26 | 2025-09-18 | 2025-10-19 | 2025-07-21 | 2025-08-19 | 533.6 | 126
Road 16 Local 1 ( 527 LM ) |  | 52 | 2025-09-18 | 2025-11-18 | 2025-07-21 | 2025-09-18 | 57473.87 | 126
Cabling Works |  | 26 | 2025-09-18 | 2025-10-19 | 2025-07-21 | 2025-08-19 | 56406.67 | 50
PRO-R16-MV-DL-100 | Material Delivery & Site Inspection of Medium Voltage Cables for Medium Voltage Network | 26 | 2025-09-18 | 2025-10-19 | 2025-07-21 | 2025-08-19 | 56406.67 | 50
Termination and Testing Works |  | 26 | 2025-10-20 | 2025-11-18 | 2025-08-20 | 2025-09-18 | 1067.2 | 126
PRO-R16-MV-DL-110 | Material Delivery & Site Inspection of Termination and Joints Kits for Medium Voltage Network | 26 | 2025-10-20 | 2025-11-18 | 2025-08-20 | 2025-09-18 | 1067.2 | 126
Road 15 Local 1 ( 556 LM ) |  | 52 | 2025-10-20 | 2025-12-18 | 2025-08-20 | 2025-10-20 | 59610.62 | 126
Cabling Works |  | 26 | 2025-10-20 | 2025-11-18 | 2025-08-20 | 2025-09-18 | 59077.02 | 50
PRO-R15-MV-DL-100 | Material Delivery & Site Inspection of Medium Voltage Cables for Medium Voltage Network | 26 | 2025-10-20 | 2025-11-18 | 2025-08-20 | 2025-09-18 | 59077.02 | 50
Termination and Testing Works |  | 26 | 2025-11-19 | 2025-12-18 | 2025-09-20 | 2025-10-20 | 533.6 | 126
PRO-R15-MV-DL-110 | Material Delivery & Site Inspection of Termination and Joints Kits for Medium Voltage Network | 26 | 2025-11-19 | 2025-12-18 | 2025-09-20 | 2025-10-20 | 533.6 | 126
Road 10 Local 2 ( 2352 LM ) |  | 104 | 2025-11-19 | 2026-03-19 | 2025-09-20 | 2026-01-19 | 122324.54 | 97
Cabling Works |  | 26 | 2025-11-19 | 2025-12-18 | 2025-09-20 | 2025-10-20 | 120190.14 | 50
PRO-R10-MV-DL-100 | Material Delivery & Site Inspection of Medium Voltage Cables for Medium Voltage Network | 26 | 2025-11-19 | 2025-12-18 | 2025-09-20 | 2025-10-20 | 120190.14 | 50
RMU Concrete Works |  | 26 | 2026-02-18 | 2026-03-19 | 2025-12-21 | 2026-01-19 | 0 | 97
PRO-R10-MV-DL-120 | Material Delivery & Site Inspection of RMU Concrete Foundations for Medium Voltage Network | 26 | 2026-02-18 | 2026-03-19 | 2025-12-21 | 2026-01-19 | 0 | 97
Termination and Testing Works |  | 26 | 2025-12-20 | 2026-01-18 | 2025-10-21 | 2025-11-19 | 2134.4 | 126
PRO-R10-MV-DL-110 | Material Delivery & Site Inspection of Termination and Joints Kits for Medium Voltage Network | 26 | 2025-12-20 | 2026-01-18 | 2025-10-21 | 2025-11-19 | 2134.4 | 126
Road 14 Local 1 ( 584 LM ) |  | 52 | 2025-12-20 | 2026-02-17 | 2025-10-21 | 2025-12-20 | 104639.56 | 126
Cabling Works |  | 26 | 2025-12-20 | 2026-01-18 | 2025-10-21 | 2025-11-19 | 103572.36 | 50
PRO-R14-MV-DL-100 | Material Delivery & Site Inspection of Medium Voltage Cables for Medium Voltage Network | 26 | 2025-12-20 | 2026-01-18 | 2025-10-21 | 2025-11-19 | 103572.36 | 50
Termination and Testing Works |  | 26 | 2026-01-19 | 2026-02-17 | 2025-11-20 | 2025-12-20 | 1067.2 | 126
PRO-R14-MV-DL-110 | Material Delivery & Site Inspection of Termination and Joints Kits for Medium Voltage Network | 26 | 2026-01-19 | 2026-02-17 | 2025-11-20 | 2025-12-20 | 1067.2 | 126
Road 09 Local 2 ( 2278 LM ) |  | 52 | 2026-01-19 | 2026-03-19 | 2025-11-20 | 2026-01-19 | 362539.37 | 126
Cabling Works |  | 26 | 2026-01-19 | 2026-02-17 | 2025-11-20 | 2025-12-20 | 359337.77 | 50
PRO-R09-MV-DL-100 | Material Delivery & Site Inspection of Medium Voltage Cables for Medium Voltage Network | 26 | 2026-01-19 | 2026-02-17 | 2025-11-20 | 2025-12-20 | 359337.77 | 50
Termination and Testing Works |  | 26 | 2026-02-18 | 2026-03-19 | 2025-12-21 | 2026-01-19 | 3201.6 | 126
PRO-R09-MV-DL-110 | Material Delivery & Site Inspection of Termination and Joints Kits for Medium Voltage Network | 26 | 2026-02-18 | 2026-03-19 | 2025-12-21 | 2026-01-19 | 3201.6 | 126
Road 11 Local 1 ( 670 LM ) |  | 52 | 2026-02-18 | 2026-04-22 | 2025-12-21 | 2026-02-18 | 71950.72 | 126
Cabling Works |  | 26 | 2026-02-18 | 2026-03-19 | 2025-12-21 | 2026-01-19 | 70883.52 | 97
PRO-R11-MV-DL-100 | Material Delivery & Site Inspection of Medium Voltage Cables for Medium Voltage Network | 26 | 2026-02-18 | 2026-03-19 | 2025-12-21 | 2026-01-19 | 70883.52 | 97
Termination and Testing Works |  | 26 | 2026-03-24 | 2026-04-22 | 2026-01-20 | 2026-02-18 | 1067.2 | 126
PRO-R11-MV-DL-110 | Material Delivery & Site Inspection of Termination and Joints Kits for Medium Voltage Network | 26 | 2026-03-24 | 2026-04-22 | 2026-01-20 | 2026-02-18 | 1067.2 | 126
Street Lighting Network |  | 462 | 11-Feb-25 A | 2026-08-23 | 2025-02-11 | 2026-06-23 | 924756.4 | 25
Issuance of Purchase Orders |  | 94 | 11-Feb-25 A | 2025-06-10 | 2025-02-11 | 2025-03-23 | 0 | 255
Cabling Works |  | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
PRO-SL-PO-100 | Issuance of Purchase Order for Lighting Cables of Street Lighting Network | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
Lighting Poles Works |  | 24 | 11-Feb-25 A | 2025-05-25 | 2025-02-11 | 2025-03-11 | 0 | 42
PRO-SL-PO-110 | Issuance of Purchase Order for Lighting Poles Foundations of Street Lighting Network | 12 | 11-Feb-25 A | 25-Feb-25 A | 2025-02-11 | 2025-02-25 | 0
PRO-SL-PO-120 | Issuance of Purchase Order for Lighting Poles of Street Lighting Network | 12 | 11-Feb-25 A | 25-Feb-25 A | 2025-02-11 | 2025-02-25 | 0
PRO-SL-PO-140 | Issuance of Purchase Order for Lighting Fixtures of Street Lighting Network | 12 | 26-Feb-25 A | 2025-05-25 | 2025-02-26 | 2025-03-11 | 0 | 42
Distribution Panel Board |  | 10 | 2025-05-26 | 2025-06-10 | 2025-03-12 | 2025-03-23 | 0 | 83
PRO-SL-PO-160 | Issuance of Purchase Order for Distrubution Panel Boards of Street Lighting Network | 10 | 2025-05-26 | 2025-06-10 | 2025-03-12 | 2025-03-23 | 0 | 83
Termination and Testing Works |  | 10 | 2025-05-26 | 2025-06-10 | 2025-03-12 | 2025-03-23 | 0 | 109
PRO-SL-PO-130 | Issuance of Purchase Order for Fuse Boxes of Street Lighting Network | 10 | 2025-05-26 | 2025-06-10 | 2025-03-12 | 2025-03-23 | 0 | 83
PRO-SL-PO-170 | Issuance of Purchase Order for Cable Lugs of Street Lighting Network | 10 | 2025-05-26 | 2025-06-10 | 2025-03-12 | 2025-03-23 | 0 | 109
Earthing System Works |  | 10 | 2025-05-26 | 2025-06-10 | 2025-03-12 | 2025-03-23 | 0 | 255
PRO-SL-PO-150 | Issuance of Purchase Order for Lighting Earthing of Street Lighting Network | 10 | 2025-05-26 | 2025-06-10 | 2025-03-12 | 2025-03-23 | 0 | 255
Manufacturing of Material |  | 186 | 18-Feb-25 A | 2025-10-04 | 2025-02-18 | 2025-07-24 | 0 | 183
Cabling Works |  | 60 | 18-Feb-25 A | 2025-07-08 | 2025-02-18 | 2025-05-04 | 0 | -16
PRO-SL-MF-100 | Manufacturing of Lighting Cables for Street Lighting Network | 60 | 18-Feb-25 A | 2025-07-08 | 2025-02-18 | 2025-05-04 | 0 | -16
Lighting Poles Works |  | 180 | 26-Feb-25 A | 2025-10-04 | 2025-02-26 | 2025-07-24 | 0 | -6
PRO-SL-MF-110 | Manufacturing of Lighting Poles Foundations for Street Lighting Network | 60 | 26-Feb-25 A | 2025-07-22 | 2025-02-26 | 2025-05-11 | 0 | -2
PRO-SL-MF-120 | Manufacturing of Lighting Poles for Street Lighting Network | 60 | 26-Feb-25 A | 2025-07-24 | 2025-02-26 | 2025-05-11 | 0 | -6
PRO-SL-MF-140 | Manufacturing of Lighting Fixtures for Street Lighting Network | 60 | 2025-07-26 | 2025-10-04 | 2025-05-12 | 2025-07-24 | 0 | -6
Distribution Panel Board |  | 26 | 2025-09-03 | 2025-10-04 | 2025-06-25 | 2025-07-24 | 0 | 11
PRO-SL-MF-160 | Manufacturing of Distrubution Panel Boards for Street Lighting Network | 26 | 2025-09-03 | 2025-10-04 | 2025-06-25 | 2025-07-24 | 0 | 11
Termination and Testing Works |  | 26 | 2025-09-03 | 2025-10-04 | 2025-06-25 | 2025-07-24 | 0 | 37
PRO-SL-MF-130 | Manufacturing of Fuse Boxes for Street Lighting Network | 26 | 2025-09-03 | 2025-10-04 | 2025-06-25 | 2025-07-24 | 0 | 11
PRO-SL-MF-170 | Manufacturing of Cable Lugs for Street Lighting Network | 26 | 2025-09-03 | 2025-10-04 | 2025-06-25 | 2025-07-24 | 0 | 37
Earthing System Works |  | 26 | 2025-09-03 | 2025-10-04 | 2025-06-25 | 2025-07-24 | 0 | 183
PRO-SL-MF-150 | Manufacturing of Lighting Earthing for Street Lighting Network | 26 | 2025-09-03 | 2025-10-04 | 2025-06-25 | 2025-07-24 | 0 | 183
1st Material Delivery & Site Inspection |  | 89 | 2025-07-09 | 2025-10-21 | 2025-05-05 | 2025-08-11 | 0 | 189
Cabling Works |  | 6 | 2025-07-09 | 2025-07-15 | 2025-05-05 | 2025-05-11 | 0 | -16
PRO-SL-1DL-100 | 1ST Material Delivery for Lighting Cables of Street Lighting Network | 6 | 2025-07-09 | 2025-07-15 | 2025-05-05 | 2025-05-11 | 0 | -16
Lighting Poles Works |  | 68 | 2025-07-23 | 2025-10-11 | 2025-05-12 | 2025-07-31 | 0 | -6
PRO-SL-1DL-110 | 1ST Material Delivery for Lighting Poles Foundations of Street Lighting Network | 6 | 2025-07-23 | 2025-07-29 | 2025-05-12 | 2025-05-18 | 0 | -2
PRO-SL-1DL-120 | 1ST Material Delivery for Lighting Poles of Street Lighting Network | 6 | 2025-07-26 | 2025-07-31 | 2025-05-12 | 2025-05-18 | 0 | 22
PRO-SL-1DL-140 | 1ST Material Delivery for Lighting Fixtures of Street Lighting Network | 6 | 2025-10-05 | 2025-10-11 | 2025-07-26 | 2025-07-31 | 0 | -6
Distribution Panel Board |  | 6 | 2025-10-05 | 2025-10-11 | 2025-07-26 | 2025-07-31 | 0 | 198
PRO-SL-1DL-160 | 1ST Material Delivery for Distrubution Panel Boards of Street Lighting Network | 6 | 2025-10-05 | 2025-10-11 | 2025-07-26 | 2025-07-31 | 0 | 198
Termination and Testing Works |  | 15 | 2025-10-05 | 2025-10-21 | 2025-07-26 | 2025-08-11 | 0 | 37
PRO-SL-1DL-130 | 1ST Material Delivery for Fuse Boxes of Street Lighting Network | 15 | 2025-10-05 | 2025-10-21 | 2025-07-26 | 2025-08-11 | 0 | 11
PRO-SL-1DL-170 | 1ST Material Delivery for Cable Lugs of Street Lighting Network | 15 | 2025-10-05 | 2025-10-21 | 2025-07-26 | 2025-08-11 | 0 | 37
Earthing System Works |  | 6 | 2025-10-05 | 2025-10-11 | 2025-07-26 | 2025-07-31 | 0 | 183
PRO-SL-1DL-150 | 1ST Material Delivery for Lighting Earthing of Street Lighting Network | 6 | 2025-10-05 | 2025-10-11 | 2025-07-26 | 2025-07-31 | 0 | 183
Material Delivery & Site Inspection |  | 338 | 2025-07-16 | 2026-08-23 | 2025-05-12 | 2026-06-23 | 924756.4 | 25
Road 18 Local 1 ( 479 LM ) |  | 156 | 2025-07-16 | 2026-01-14 | 2025-05-12 | 2025-11-15 | 40070.76 | -10
Cabling Works |  | 26 | 2025-07-16 | 2025-08-14 | 2025-05-12 | 2025-06-15 | 17346 | -16
PRO-R18-SL-DL-180 | Material Delivery & Site Inspection of Lighting Cables for Street Lighting Network | 26 | 2025-07-16 | 2025-08-14 | 2025-05-12 | 2025-06-15 | 17346 | -16
Lighting Poles Works |  | 78 | 2025-08-16 | 2025-11-15 | 2025-06-16 | 2025-09-14 | 17967.6 | -10
PRO-R18-SL-DL-190 | Material Delivery & Site Inspection of Lighting Poles Foundations for Street Lighting Network | 26 | 2025-08-16 | 2025-09-14 | 2025-06-16 | 2025-07-15 | 2280.6 | -16
PRO-R18-SL-DL-200 | Material Delivery & Site Inspection of Lighting Poles for Street Lighting Network | 26 | 2025-09-15 | 2025-10-15 | 2025-07-16 | 2025-08-14 | 11932.2 | -16
PRO-R18-SL-DL-220 | Material Delivery & Site Inspection of Lighting Fixtures for Street Lighting Network | 26 | 2025-10-16 | 2025-11-15 | 2025-08-16 | 2025-09-14 | 3754.8 | -10
Termination and Testing Works |  | 52 | 2025-11-16 | 2026-01-14 | 2025-09-15 | 2025-11-15 | 4757.16 | -10
PRO-R18-SL-DL-210 | Material Delivery & Site Inspection of Fuse Boxes for Street Lighting Network | 26 | 2025-11-16 | 2025-12-15 | 2025-09-15 | 2025-10-15 | 4757.16 | -10
PRO-R18-SL-DL-250 | Material Delivery & Site Inspection of Cable Lugs for Street Lighting Network | 26 | 2025-12-16 | 2026-01-14 | 2025-10-16 | 2025-11-15 | 0 | -10
Road 17 Local 1 ( 500 LM ) |  | 156 | 2025-08-16 | 2026-02-14 | 2025-06-16 | 2025-12-15 | 41272.22 | -10
Cabling Works |  | 26 | 2025-08-16 | 2025-09-14 | 2025-06-16 | 2025-07-15 | 17934 | 56
PRO-R17-SL-DL-100 | Material Delivery & Site Inspection of Lighting Cables for Street Lighting Network | 26 | 2025-08-16 | 2025-09-14 | 2025-06-16 | 2025-07-15 | 17934 | 56
Lighting Poles Works |  | 78 | 2025-09-15 | 2025-12-15 | 2025-07-16 | 2025-10-15 | 19257.6 | 13
PRO-R17-SL-DL-110 | Material Delivery & Site Inspection of Lighting Poles Foundations for Street Lighting Network | 26 | 2025-09-15 | 2025-10-15 | 2025-07-16 | 2025-08-14 | 2823.6 | -11
PRO-R17-SL-DL-120 | Material Delivery & Site Inspection of Lighting Poles for Street Lighting Network | 26 | 2025-10-16 | 2025-11-15 | 2025-08-16 | 2025-09-14 | 12500.4 | -16
PRO-R17-SL-DL-140 | Material Delivery & Site Inspection of Lighting Fixtures for Street Lighting Network | 26 | 2025-11-16 | 2025-12-15 | 2025-09-15 | 2025-10-15 | 3933.6 | 13
Termination and Testing Works |  | 52 | 2025-12-16 | 2026-02-14 | 2025-10-16 | 2025-12-15 | 4080.62 | -10
PRO-R17-SL-DL-130 | Material Delivery & Site Inspection of Fuse Boxes for Street Lighting Network | 26 | 2025-12-16 | 2026-01-14 | 2025-10-16 | 2025-11-15 | 4080.62 | -2
PRO-R17-SL-DL-170 | Material Delivery & Site Inspection of Cable Lugs for Street Lighting Network | 26 | 2026-01-15 | 2026-02-14 | 2025-11-16 | 2025-12-15 | 0 | -10
Road 16 Local 1 ( 527 LM ) |  | 156 | 2025-09-15 | 2026-03-16 | 2025-07-16 | 2026-01-14 | 42644.98 | -10
Cabling Works |  | 26 | 2025-09-15 | 2025-10-15 | 2025-07-16 | 2025-08-14 | 18816 | 56
PRO-R16-SL-DL-100 | Material Delivery & Site Inspection of Lighting Cables for Street Lighting Network | 26 | 2025-09-15 | 2025-10-15 | 2025-07-16 | 2025-08-14 | 18816 | 56
Lighting Poles Works |  | 78 | 2025-10-16 | 2026-01-14 | 2025-08-16 | 2025-11-15 | 19678.8 | 13
PRO-R16-SL-DL-110 | Material Delivery & Site Inspection of Lighting Poles Foundations for Street Lighting Network | 26 | 2025-10-16 | 2025-11-15 | 2025-08-16 | 2025-09-14 | 2497.8 | -11
PRO-R16-SL-DL-120 | Material Delivery & Site Inspection of Lighting Poles for Street Lighting Network | 26 | 2025-11-16 | 2025-12-15 | 2025-09-15 | 2025-10-15 | 13068.6 | -16
PRO-R16-SL-DL-140 | Material Delivery & Site Inspection of Lighting Fixtures for Street Lighting Network | 26 | 2025-12-16 | 2026-01-14 | 2025-10-16 | 2025-11-15 | 4112.4 | 13
Termination and Testing Works |  | 52 | 2026-01-15 | 2026-03-16 | 2025-11-16 | 2026-01-14 | 4150.18 | -10
PRO-R16-SL-DL-130 | Material Delivery & Site Inspection of Fuse Boxes for Street Lighting Network | 26 | 2026-01-15 | 2026-02-14 | 2025-11-16 | 2025-12-15 | 4150.18 | -2
PRO-R16-SL-DL-170 | Material Delivery & Site Inspection of Cable Lugs for Street Lighting Network | 26 | 2026-02-15 | 2026-03-16 | 2025-12-16 | 2026-01-14 | 0 | -10
Road 15 Local 1 ( 556 LM ) |  | 156 | 2025-10-16 | 2026-04-19 | 2025-08-16 | 2026-02-14 | 46404.51 | -10
Cabling Works |  | 26 | 2025-10-16 | 2025-11-15 | 2025-08-16 | 2025-09-14 | 19992 | 56
PRO-R15-SL-DL-100 | Material Delivery & Site Inspection of Lighting Cables for Street Lighting Network | 26 | 2025-10-16 | 2025-11-15 | 2025-08-16 | 2025-09-14 | 19992 | 56
Lighting Poles Works |  | 78 | 2025-11-16 | 2026-02-14 | 2025-09-15 | 2025-12-15 | 21390 | 13
PRO-R15-SL-DL-110 | Material Delivery & Site Inspection of Lighting Poles Foundations for Street Lighting Network | 26 | 2025-11-16 | 2025-12-15 | 2025-09-15 | 2025-10-15 | 2715 | -11
PRO-R15-SL-DL-120 | Material Delivery & Site Inspection of Lighting Poles for Street Lighting Network | 26 | 2025-12-16 | 2026-01-14 | 2025-10-16 | 2025-11-15 | 14205 | -16
PRO-R15-SL-DL-140 | Material Delivery & Site Inspection of Lighting Fixtures for Street Lighting Network | 26 | 2026-01-15 | 2026-02-14 | 2025-11-16 | 2025-12-15 | 4470 | 13
Termination and Testing Works |  | 52 | 2026-02-15 | 2026-04-19 | 2025-12-16 | 2026-02-14 | 5022.51 | -10
PRO-R15-SL-DL-130 | Material Delivery & Site Inspection of Fuse Boxes for Street Lighting Network | 26 | 2026-02-15 | 2026-03-16 | 2025-12-16 | 2026-01-14 | 5022.51 | -2
PRO-R15-SL-DL-170 | Material Delivery & Site Inspection of Cable Lugs for Street Lighting Network | 26 | 2026-03-17 | 2026-04-19 | 2026-01-15 | 2026-02-14 | 0 | -10
Road 10 Local 2 ( 2352 LM ) |  | 186 | 2025-10-12 | 2026-05-19 | 2025-08-02 | 2026-03-16 | 308183.7 | 38
Cabling Works |  | 26 | 2025-11-16 | 2025-12-15 | 2025-09-15 | 2025-10-15 | 80850 | 56
PRO-R10-SL-DL-100 | Material Delivery & Site Inspection of Lighting Cables for Street Lighting Network | 26 | 2025-11-16 | 2025-12-15 | 2025-09-15 | 2025-10-15 | 80850 | 56
Lighting Poles Works |  | 78 | 2025-12-16 | 2026-03-16 | 2025-10-16 | 2026-01-14 | 95061 | 13
PRO-R10-SL-DL-110 | Material Delivery & Site Inspection of Lighting Poles Foundations for Street Lighting Network | 26 | 2025-12-16 | 2026-01-14 | 2025-10-16 | 2025-11-15 | 23349 | -11
PRO-R10-SL-DL-120 | Material Delivery & Site Inspection of Lighting Poles for Street Lighting Network | 26 | 2026-01-15 | 2026-02-14 | 2025-11-16 | 2025-12-15 | 54547.2 | -16
PRO-R10-SL-DL-140 | Material Delivery & Site Inspection of Lighting Fixtures for Street Lighting Network | 26 | 2026-02-15 | 2026-03-16 | 2025-12-16 | 2026-01-14 | 17164.8 | 13
Distribution Panel Board |  | 26 | 2025-10-12 | 2025-11-10 | 2025-08-02 | 2025-08-31 | 103537.2 | 198
PRO-R10-SL-DL-160 | Material Delivery & Site Inspection of Distrubution Panel Boards for Street Lighting Network | 26 | 2025-10-12 | 2025-11-10 | 2025-08-02 | 2025-08-31 | 103537.2 | 198
Termination and Testing Works |  | 52 | 2026-03-17 | 2026-05-19 | 2026-01-15 | 2026-03-16 | 25217.5 | -10
PRO-R10-SL-DL-130 | Material Delivery & Site Inspection of Fuse Boxes for Street Lighting Network | 26 | 2026-03-17 | 2026-04-19 | 2026-01-15 | 2026-02-14 | 25217.5 | -2
PRO-R10-SL-DL-170 | Material Delivery & Site Inspection of Cable Lugs for Street Lighting Network | 26 | 2026-04-20 | 2026-05-19 | 2026-02-15 | 2026-03-16 | 0 | -10
Earthing System Works |  | 26 | 2025-10-12 | 2025-11-10 | 2025-08-02 | 2025-08-31 | 3518 | 183
PRO-R10-SL-DL-150 | Material Delivery & Site Inspection of Lighting Earthing for Street Lighting Network | 26 | 2025-10-12 | 2025-11-10 | 2025-08-02 | 2025-08-31 | 3518 | 183
Road 14 Local 1 ( 584 LM ) |  | 156 | 2025-12-16 | 2026-06-23 | 2025-10-16 | 2026-04-19 | 83451.11 | -10
Cabling Works |  | 26 | 2025-12-16 | 2026-01-14 | 2025-10-16 | 2025-11-15 | 34692 | 56
PRO-R14-SL-DL-100 | Material Delivery & Site Inspection of Lighting Cables for Street Lighting Network | 26 | 2025-12-16 | 2026-01-14 | 2025-10-16 | 2025-11-15 | 34692 | 56
Lighting Poles Works |  | 78 | 2026-01-15 | 2026-04-19 | 2025-11-16 | 2026-02-14 | 40753.6 | 13
PRO-R14-SL-DL-110 | Material Delivery & Site Inspection of Lighting Poles Foundations for Street Lighting Network | 26 | 2026-01-15 | 2026-02-14 | 2025-11-16 | 2025-12-15 | 4561.2 | -11
PRO-R14-SL-DL-120 | Material Delivery & Site Inspection of Lighting Poles for Street Lighting Network | 26 | 2026-02-15 | 2026-03-16 | 2025-12-16 | 2026-01-14 | 26380.4 | -16
PRO-R14-SL-DL-140 | Material Delivery & Site Inspection of Lighting Fixtures for Street Lighting Network | 26 | 2026-03-17 | 2026-04-19 | 2026-01-15 | 2026-02-14 | 9812 | 13
Termination and Testing Works |  | 52 | 2026-04-20 | 2026-06-23 | 2026-02-15 | 2026-04-19 | 8005.51 | -10
PRO-R14-SL-DL-130 | Material Delivery & Site Inspection of Fuse Boxes for Street Lighting Network | 26 | 2026-04-20 | 2026-05-19 | 2026-02-15 | 2026-03-16 | 8005.51 | -2
PRO-R14-SL-DL-170 | Material Delivery & Site Inspection of Cable Lugs for Street Lighting Network | 26 | 2026-05-20 | 2026-06-23 | 2026-03-17 | 2026-04-19 | 0 | -10
Road 09 Local 2 ( 2278 LM ) |  | 238 | 2025-10-12 | 2026-07-23 | 2025-08-02 | 2026-05-19 | 309582 | 36
Cabling Works |  | 26 | 2026-01-15 | 2026-02-14 | 2025-11-16 | 2025-12-15 | 80556 | 56
PRO-R09-SL-DL-100 | Material Delivery & Site Inspection of Lighting Cables for Street Lighting Network | 26 | 2026-01-15 | 2026-02-14 | 2025-11-16 | 2025-12-15 | 80556 | 56
Lighting Poles Works |  | 78 | 2026-02-15 | 2026-05-19 | 2025-12-16 | 2026-03-16 | 96772.2 | 13
PRO-R09-SL-DL-110 | Material Delivery & Site Inspection of Lighting Poles Foundations for Street Lighting Network | 26 | 2026-02-15 | 2026-03-16 | 2025-12-16 | 2026-01-14 | 23566.2 | -11
PRO-R09-SL-DL-120 | Material Delivery & Site Inspection of Lighting Poles for Street Lighting Network | 26 | 2026-03-17 | 2026-04-19 | 2026-01-15 | 2026-02-14 | 55683.6 | -16
PRO-R09-SL-DL-140 | Material Delivery & Site Inspection of Lighting Fixtures for Street Lighting Network | 26 | 2026-04-20 | 2026-05-19 | 2026-02-15 | 2026-03-16 | 17522.4 | 13
Distribution Panel Board |  | 26 | 2025-10-12 | 2025-11-10 | 2025-08-02 | 2025-08-31 | 103537.2 | 248
PRO-R09-SL-DL-160 | Material Delivery & Site Inspection of Distrubution Panel Boards for Street Lighting Network | 26 | 2025-10-12 | 2025-11-10 | 2025-08-02 | 2025-08-31 | 103537.2 | 248
Termination and Testing Works |  | 52 | 2026-05-20 | 2026-07-23 | 2026-03-17 | 2026-05-19 | 25198.6 | -10
PRO-R09-SL-DL-130 | Material Delivery & Site Inspection of Fuse Boxes for Street Lighting Network | 26 | 2026-05-20 | 2026-06-23 | 2026-03-17 | 2026-04-19 | 25198.6 | -2
PRO-R09-SL-DL-170 | Material Delivery & Site Inspection of Cable Lugs for Street Lighting Network | 26 | 2026-06-24 | 2026-07-23 | 2026-04-20 | 2026-05-19 | 0 | -10
Earthing System Works |  | 26 | 2025-10-12 | 2025-11-10 | 2025-08-02 | 2025-08-31 | 3518 | 197
PRO-R09-SL-DL-150 | Material Delivery & Site Inspection of Lighting Earthing for Street Lighting Network | 26 | 2025-10-12 | 2025-11-10 | 2025-08-02 | 2025-08-31 | 3518 | 197
Road 11 Local 1 ( 670 LM ) |  | 156 | 2026-02-15 | 2026-08-23 | 2025-12-16 | 2026-06-23 | 53147.12 | 25
Cabling Works |  | 26 | 2026-02-15 | 2026-03-16 | 2025-12-16 | 2026-01-14 | 23814 | 56
PRO-R11-SL-DL-100 | Material Delivery & Site Inspection of Lighting Cables for Street Lighting Network | 26 | 2026-02-15 | 2026-03-16 | 2025-12-16 | 2026-01-14 | 23814 | 56
Lighting Poles Works |  | 78 | 2026-03-17 | 2026-06-23 | 2026-01-15 | 2026-04-19 | 23956.8 | 77
PRO-R11-SL-DL-110 | Material Delivery & Site Inspection of Lighting Poles Foundations for Street Lighting Network | 26 | 2026-03-17 | 2026-04-19 | 2026-01-15 | 2026-02-14 | 3040.8 | -11
PRO-R11-SL-DL-120 | Material Delivery & Site Inspection of Lighting Poles for Street Lighting Network | 26 | 2026-04-20 | 2026-05-19 | 2026-02-15 | 2026-03-16 | 15909.6 | -16
PRO-R11-SL-DL-140 | Material Delivery & Site Inspection of Lighting Fixtures for Street Lighting Network | 26 | 2026-05-20 | 2026-06-23 | 2026-03-17 | 2026-04-19 | 5006.4 | 77
Termination and Testing Works |  | 52 | 2026-06-24 | 2026-08-23 | 2026-04-20 | 2026-06-23 | 5376.32 | -6
PRO-R11-SL-DL-130 | Material Delivery & Site Inspection of Fuse Boxes for Street Lighting Network | 26 | 2026-06-24 | 2026-07-23 | 2026-04-20 | 2026-05-19 | 5376.32 | 20
PRO-R11-SL-DL-170 | Material Delivery & Site Inspection of Cable Lugs for Street Lighting Network | 26 | 2026-07-25 | 2026-08-23 | 2026-05-20 | 2026-06-23 | 0 | -10
Telecom Network |  | 332 | 11-Feb-25 A | 2026-03-16 | 2025-02-11 | 2026-01-14 | 363314.2 | 100
Issuance of Purchase Orders |  | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
Ducts Works |  | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
PRO-TE-PO-100 | Issuance of Purchase Order for Ducts forTelecom Network | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
Manholes Works |  | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
PRO-TE-PO-110 | Issuance of Purchase Order for Manholes forTelecom Network | 6 | 11-Feb-25 A | 17-Feb-25 A | 2025-02-11 | 2025-02-17 | 0
Manufacturing of Material |  | 60 | 18-Feb-25 A | 2025-07-08 | 2025-02-18 | 2025-05-04 | 0 | 100
Ducts Works |  | 60 | 18-Feb-25 A | 2025-07-06 | 2025-02-18 | 2025-05-04 | 0 | 95
PRO-TE-MF-100 | Manufacturing of Ducts for Telecom Network | 60 | 18-Feb-25 A | 2025-07-06 | 2025-02-18 | 2025-05-04 | 0 | 95
Manholes Works |  | 60 | 18-Feb-25 A | 2025-07-08 | 2025-02-18 | 2025-05-04 | 0 | 100
PRO-TE-MF-110 | Manufacturing of Manholes for Telecom Network | 60 | 18-Feb-25 A | 2025-07-08 | 2025-02-18 | 2025-05-04 | 0 | 100
1st Material Delivery & Site Inspection |  | 8 | 2025-07-07 | 2025-07-15 | 2025-05-05 | 2025-05-11 | 0 | 100
Ducts Works |  | 6 | 2025-07-07 | 2025-07-13 | 2025-05-05 | 2025-05-11 | 0 | 95
PRO-TE-1DL-100 | 1ST Material Delivery for Ducts of Telecom Network | 6 | 2025-07-07 | 2025-07-13 | 2025-05-05 | 2025-05-11 | 0 | 95
Manholes Works |  | 6 | 2025-07-09 | 2025-07-15 | 2025-05-05 | 2025-05-11 | 0 | 100
PRO-TE-1DL-110 | 1ST Material Delivery for Manholes of Telecom Network | 6 | 2025-07-09 | 2025-07-15 | 2025-05-05 | 2025-05-11 | 0 | 100
Material Delivery & Site Inspection |  | 210 | 2025-07-14 | 2026-03-16 | 2025-05-12 | 2026-01-14 | 363314.2 | 100
Road 18 Local 1 ( 479 LM ) |  | 28 | 2025-07-14 | 2025-08-14 | 2025-05-12 | 2025-06-15 | 23603.2 | 100
Ducts Works |  | 26 | 2025-07-14 | 2025-08-12 | 2025-05-12 | 2025-06-15 | 17045 | 95
PRO-R18-TE-DL-120 | Material Delivery & Site Inspection for Ducts of Telecom Network | 26 | 2025-07-14 | 2025-08-12 | 2025-05-12 | 2025-06-15 | 17045 | 95
Manholes Works |  | 26 | 2025-07-16 | 2025-08-14 | 2025-05-12 | 2025-06-15 | 6558.2 | 100
PRO-R18-TE-DL-130 | Material Delivery & Site Inspection of Manholes for Telecom Network | 26 | 2025-07-16 | 2025-08-14 | 2025-05-12 | 2025-06-15 | 6558.2 | 100
Road 17 Local 1 ( 500 LM ) |  | 28 | 2025-08-13 | 2025-09-14 | 2025-06-16 | 2025-07-15 | 21358.9 | 100
Ducts Works |  | 26 | 2025-08-13 | 2025-09-11 | 2025-06-16 | 2025-07-15 | 17622.5 | 95
PRO-R17-TE-DL-100 | Material Delivery & Site Inspection for Ducts of Telecom Network | 26 | 2025-08-13 | 2025-09-11 | 2025-06-16 | 2025-07-15 | 17622.5 | 95
Manholes Works |  | 26 | 2025-08-16 | 2025-09-14 | 2025-06-16 | 2025-07-15 | 3736.4 | 100
PRO-R17-TE-DL-110 | Material Delivery & Site Inspection of Manholes for Telecom Network | 26 | 2025-08-16 | 2025-09-14 | 2025-06-16 | 2025-07-15 | 3736.4 | 100
Road 16 Local 1 ( 527 LM ) |  | 28 | 2025-09-13 | 2025-10-15 | 2025-07-16 | 2025-08-14 | 24127.4 | 100
Ducts Works |  | 26 | 2025-09-13 | 2025-10-13 | 2025-07-16 | 2025-08-14 | 18515 | 95
PRO-R16-TE-DL-100 | Material Delivery & Site Inspection for Ducts of Telecom Network | 26 | 2025-09-13 | 2025-10-13 | 2025-07-16 | 2025-08-14 | 18515 | 95
Manholes Works |  | 26 | 2025-09-15 | 2025-10-15 | 2025-07-16 | 2025-08-14 | 5612.4 | 100
PRO-R16-TE-DL-110 | Material Delivery & Site Inspection of Manholes for Telecom Network | 26 | 2025-09-15 | 2025-10-15 | 2025-07-16 | 2025-08-14 | 5612.4 | 100
Road 15 Local 1 ( 556 LM ) |  | 28 | 2025-10-14 | 2025-11-15 | 2025-08-16 | 2025-09-14 | 25018.65 | 100
Ducts Works |  | 26 | 2025-10-14 | 2025-11-12 | 2025-08-16 | 2025-09-14 | 19406.25 | 95
PRO-R15-TE-DL-100 | Material Delivery & Site Inspection for Ducts of Telecom Network | 26 | 2025-10-14 | 2025-11-12 | 2025-08-16 | 2025-09-14 | 19406.25 | 95
Manholes Works |  | 26 | 2025-10-16 | 2025-11-15 | 2025-08-16 | 2025-09-14 | 5612.4 | 100
PRO-R15-TE-DL-110 | Material Delivery & Site Inspection of Manholes for Telecom Network | 26 | 2025-10-16 | 2025-11-15 | 2025-08-16 | 2025-09-14 | 5612.4 | 100
Road 10 Local 2 ( 2352 LM ) |  | 28 | 2025-11-13 | 2025-12-15 | 2025-09-15 | 2025-10-15 | 97746.95 | 100
Ducts Works |  | 26 | 2025-11-13 | 2025-12-13 | 2025-09-15 | 2025-10-15 | 79033.75 | 95
PRO-R10-TE-DL-100 | Material Delivery & Site Inspection for Ducts of Telecom Network | 26 | 2025-11-13 | 2025-12-13 | 2025-09-15 | 2025-10-15 | 79033.75 | 95
Manholes Works |  | 26 | 2025-11-16 | 2025-12-15 | 2025-09-15 | 2025-10-15 | 18713.2 | 100
PRO-R10-TE-DL-110 | Material Delivery & Site Inspection of Manholes for Telecom Network | 26 | 2025-11-16 | 2025-12-15 | 2025-09-15 | 2025-10-15 | 18713.2 | 100
Road 14 Local 1 ( 584 LM ) |  | 28 | 2025-12-14 | 2026-01-14 | 2025-10-16 | 2025-11-15 | 43388.8 | 100
Ducts Works |  | 26 | 2025-12-14 | 2026-01-12 | 2025-10-16 | 2025-11-15 | 34040 | 95
PRO-R14-TE-DL-100 | Material Delivery & Site Inspection for Ducts of Telecom Network | 26 | 2025-12-14 | 2026-01-12 | 2025-10-16 | 2025-11-15 | 34040 | 95
Manholes Works |  | 26 | 2025-12-16 | 2026-01-14 | 2025-10-16 | 2025-11-15 | 9348.8 | 100
PRO-R14-TE-DL-110 | Material Delivery & Site Inspection of Manholes for Telecom Network | 26 | 2025-12-16 | 2026-01-14 | 2025-10-16 | 2025-11-15 | 9348.8 | 100
Road 09 Local 2 ( 2278 LM ) |  | 28 | 2026-01-13 | 2026-02-14 | 2025-11-16 | 2025-12-15 | 99400.4 | 100
Ducts Works |  | 26 | 2026-01-15 | 2026-02-14 | 2025-11-16 | 2025-12-15 | 20620.4 | 100
PRO-R09-TE-DL-110 | Material Delivery & Site Inspection of Manholes for Telecom Network | 26 | 2026-01-15 | 2026-02-14 | 2025-11-16 | 2025-12-15 | 20620.4 | 100
Manholes Works |  | 26 | 2026-01-13 | 2026-02-11 | 2025-11-16 | 2025-12-15 | 78780 | 95
PRO-R09-TE-DL-100 | Material Delivery & Site Inspection for Ducts of Telecom Network | 26 | 2026-01-13 | 2026-02-11 | 2025-11-16 | 2025-12-15 | 78780 | 95
Road 11 Local 1 ( 670 LM ) |  | 28 | 2026-02-12 | 2026-03-16 | 2025-12-16 | 2026-01-14 | 28669.9 | 100
Ducts Works |  | 26 | 2026-02-12 | 2026-03-14 | 2025-12-16 | 2026-01-14 | 23057.5 | 95
PRO-R11-TE-DL-100 | Material Delivery & Site Inspection for Ducts of Telecom Network | 26 | 2026-02-12 | 2026-03-14 | 2025-12-16 | 2026-01-14 | 23057.5 | 95
Manholes Works |  | 26 | 2026-02-15 | 2026-03-16 | 2025-12-16 | 2026-01-14 | 5612.4 | 100
PRO-R11-TE-DL-110 | Material Delivery & Site Inspection of Manholes for Telecom Network | 26 | 2026-02-15 | 2026-03-16 | 2025-12-16 | 2026-01-14 | 5612.4 | 100
Superstructure Works |  | 352 | 18-Feb-25 A | 2026-04-19 | 2025-02-18 | 2026-02-14 | 1806770.6 | 30
Issuance of Purchase Orders |  | 24 | 18-Feb-25 A | 2025-05-22 | 2025-02-18 | 2025-03-18 | 0 | 30
Sewage Pump Stations ( PS 06 ) |  | 12 | 18-Feb-25 A | 06-Mar-25 A | 2025-02-18 | 2025-03-04 | 0
PRO-SPS-CV-PO-10 | Issuance of Purchase Order for Civil Works for Sewage Pump Stations | 12 | 18-Feb-25 A | 06-Mar-25 A | 2025-02-18 | 2025-03-04 | 0
Storm Drainage Ponds ( PO-J1 , PO-J2 ) |  | 12 | 06-Mar-25 A | 2025-05-22 | 2025-03-05 | 2025-03-18 | 0 | 30
PRO-DPO-CV-PO-10 | Issuance of Purchase Order for Civil Works for Storm Drainage Ponds | 12 | 06-Mar-25 A | 2025-05-22 | 2025-03-05 | 2025-03-18 | 0 | 30
Manufacturing of Material |  | 244 | 06-Mar-25 A | 2025-12-24 | 2025-03-05 | 2025-10-25 | 0 | 30
Sewage Pump Stations ( PS 06 ) |  | 130 | 06-Mar-25 A | 2025-09-22 | 2025-03-05 | 2025-08-12 | 0 | 56
PRO-SPS-CV-MF-10 | Manufacturing of Civil Works for Sewage Pump Stations ( PS06 ) | 130 | 06-Mar-25 A | 2025-09-22 | 2025-03-05 | 2025-08-12 | 0 | 56
Storm Drainage Ponds ( PO-J1 , PO-J2 ) |  | 180 | 2025-05-24 | 2025-12-24 | 2025-03-19 | 2025-10-25 | 0 | 30
PRO-DPO-CV-MF-10 | Manufacturing of Civil Works for Storm Drainage Ponds ( PO-J1 ) | 120 | 2025-05-24 | 2025-10-15 | 2025-03-19 | 2025-08-14 | 0 | 30
PRO-DPO-CV-MF-20 | Manufacturing of Civil Works for Storm Drainage Ponds ( PO-J2 ) | 60 | 2025-10-16 | 2025-12-24 | 2025-08-16 | 2025-10-25 | 0 | 30
1st Material Delivery & Site Inspection |  | 105 | 2025-09-24 | 2026-01-24 | 2025-08-13 | 2025-11-24 | 0 | 30
Sewage Pump Stations ( PS 06 ) |  | 40 | 2025-09-24 | 2025-11-09 | 2025-08-13 | 2025-09-29 | 0 | 56
PRO-SPS-CV-1DL-10 | 1ST Material Delivery for Civil Works for Sewage Pump Stations ( PS 06 ) | 40 | 2025-09-24 | 2025-11-09 | 2025-08-13 | 2025-09-29 | 0 | 56
Storm Drainage Ponds ( PO-J1 , PO-J2 ) |  | 86 | 2025-10-16 | 2026-01-24 | 2025-08-16 | 2025-11-24 | 0 | 30
PRO-DPO-CV-1DL-10 | 1ST Material Delivery for Civil Works for Storm Drainage Ponds ( PO-J1 ) | 26 | 2025-10-16 | 2025-11-15 | 2025-08-16 | 2025-09-14 | 0 | 80
PRO-DPO-CV-1DL-20 | 1ST Material Delivery for Civil Works for Storm Drainage Ponds ( PO-J2 ) | 26 | 2025-12-25 | 2026-01-24 | 2025-10-26 | 2025-11-24 | 0 | 30
Material Delivery & Site Inspection |  | 135 | 2025-11-10 | 2026-04-19 | 2025-09-15 | 2026-02-14 | 1806770.6 | 30
Sewage Pump Stations ( PS 06 ) |  | 70 | 2025-11-10 | 2026-01-29 | 2025-09-30 | 2025-12-20 | 1213097 | 56
PRO-SPS-CV-DL-10 | Material Delivery & Site Inspection for Civil Works for Sewage Pump Stations ( PS 06 ) | 70 | 2025-11-10 | 2026-01-29 | 2025-09-30 | 2025-12-20 | 1213097 | 56
Storm Drainage Ponds ( PO-J1 , PO-J2 ) |  | 130 | 2025-11-16 | 2026-04-19 | 2025-09-15 | 2026-02-14 | 593673.6 | 30
PRO-DPO-CV-DL-10 | Material Delivery & Site Inspection for Civil Works for Storm Drainage Ponds ( PO-J1 ) | 70 | 2025-11-16 | 2026-02-04 | 2025-09-15 | 2025-12-06 | 508118 | 80
PRO-DPO-CV-DL-20 | Material Delivery & Site Inspection for Civil Works for Storm Drainage Ponds ( PO-J2 ) | 70 | 2026-01-25 | 2026-04-19 | 2025-11-25 | 2026-02-14 | 85555.6 | 30
Long Lead Time Items |  | 523 | 11-Feb-25 A | 2026-11-02 | 2025-02-10 | 2026-08-31 | 1107775.96 | -16
Infrastructure Networks |  | 353 | 11-Feb-25 A | 2026-04-12 | 2025-02-10 | 2026-02-05 | 71871.96 | 126
RMU Works of Medium Voltage Network |  | 353 | 11-Feb-25 A | 2026-04-12 | 2025-02-10 | 2026-02-05 | 71871.96 | 126
Issuance of Purchase Orders |  | 30 | 11-Feb-25 A | 2025-05-22 | 2025-02-10 | 2025-03-17 | 0 | -16
PRO-MV-LL-PO-10 | Issuance of Purchase Order for RMU of Medium Voltage Network | 30 | 11-Feb-25 A | 2025-05-22 | 2025-02-10 | 2025-03-17 | 0 | -16
Manufacturing of Material |  | 150 | 2025-05-24 | 2025-11-19 | 2025-03-18 | 2025-09-17 | 0 | -16
PRO-MV-LL-MF-10 | Manufacturing of RMU for Medium Voltage Network | 150 | 2025-05-24 | 2025-11-19 | 2025-03-18 | 2025-09-17 | 0 | -16
Material Shipping/Custom Clearance/Delivery |  | 90 | 2025-11-20 | 2026-03-04 | 2025-09-18 | 2026-01-01 | 0 | 108
PRO-MV-LL-SH/DL-10 | Material Delivery for RMU of Medium Voltage Network | 90 | 2025-11-20 | 2026-03-04 | 2025-09-18 | 2026-01-01 | 0 | 108
Material Site Inspection |  | 30 | 2026-03-05 | 2026-04-12 | 2026-01-03 | 2026-02-05 | 71871.96 | 126
Road 10 Local 2 ( 2352 LM ) |  | 30 | 2026-03-05 | 2026-04-12 | 2026-01-03 | 2026-02-05 | 47914.64 | 108
PRO-R10-MV-LL-MSI-10 | Material Site Inspection of RMU for Medium Voltage Network | 30 | 2026-03-05 | 2026-04-12 | 2026-01-03 | 2026-02-05 | 47914.64 | 108
Road 17 Local 1 ( 500 LM ) |  | 30 | 2026-03-05 | 2026-04-12 | 2026-01-03 | 2026-02-05 | 23957.32 | 126
PRO-R17-MV-LL-MSI-40 | Material Site Inspection of RMU for Medium Voltage Network | 30 | 2026-03-05 | 2026-04-12 | 2026-01-03 | 2026-02-05 | 23957.32 | 126
Superstructure Works |  | 290 | 2025-11-20 | 2026-11-02 | 2025-09-18 | 2026-08-31 | 1035904 | -16
Sewage Pump Stations ( PS 06 ) |  | 290 | 2025-11-20 | 2026-11-02 | 2025-09-18 | 2026-08-31 | 1035904 | -16
Issuance of Purchase Orders |  | 60 | 2025-11-20 | 2026-01-28 | 2025-09-18 | 2025-11-27 | 0 | -16
PRO-SPS-LL-PO-10 | Issuance of Purchase Order for Electromechanical Works for Sewage Pump Stations | 60 | 2025-11-20 | 2026-01-28 | 2025-09-18 | 2025-11-27 | 0 | -16
Manufacturing of Material |  | 100 | 2026-01-29 | 2026-06-02 | 2025-11-29 | 2026-03-28 | 0 | -16
PRO-SPS7-LL-MF-10 | Manufacturing of Electromechanical Works for Sewage Pump Stations ( PS 06 ) | 100 | 2026-01-29 | 2026-06-02 | 2025-11-29 | 2026-03-28 | 0 | -16
Material Shipping/Custom Clearance/Delivery |  | 80 | 2026-06-03 | 2026-09-03 | 2026-03-29 | 2026-07-04 | 0 | -16
PRO-SPS7-LL-SH/DL-10 | Material Delivery for Electromechanical Works for Sewage Pump Stations ( PS 06 ) | 80 | 2026-06-03 | 2026-09-03 | 2026-03-29 | 2026-07-04 | 0 | -16
Material Site Inspection |  | 50 | 2026-09-05 | 2026-11-02 | 2026-07-05 | 2026-08-31 | 1035904 | -16
PRO-SPS7-LL-MSI-10 | Material Site Inspection for Electromechanical Works for Sewage Pump Stations ( PS06 ) | 50 | 2026-09-05 | 2026-11-02 | 2026-07-05 | 2026-08-31 | 1035904 | -16
Construction Works |  | 588 | 09-Feb-25 A | 2027-01-16 | 2025-02-09 | 2026-12-28 | 78698418.61 | -4
Infrastructure Networks |  | 588 | 09-Feb-25 A | 2027-01-16 | 2025-02-09 | 2026-12-28 | 72319803.73 | -4
Phase 2 Block "J" |  | 565 | 09-Feb-25 A | 2026-12-20 | 2025-02-09 | 2026-12-01 | 59313511.25 | 19
Rising Main Network |  | 63 | 2025-07-30 | 2025-10-12 | 2025-09-01 | 2025-11-13 | 3537626.13 | 383
Main Line Sections |  | 63 | 2025-07-30 | 2025-10-12 | 2025-09-01 | 2025-11-13 | 1670107.33 | 383
CO-RM-SW-290 | Trench Excavation and Bedding Works for Main Lines of Rising Main Network | 21 | 2025-07-30 | 2025-08-23 | 2025-09-01 | 2025-09-25 | 334021.47 | 383
CO-RM-SW-300 | Pipes Laying Works for Main Lines of Rising Main Network | 21 | 2025-08-24 | 2025-09-16 | 2025-09-27 | 2025-10-20 | 1169075.13 | 383
CO-RM-SW-310 | Trench Backfilling and Compaction Works for Main Lines of Rising Main Network | 21 | 2025-09-17 | 2025-10-12 | 2025-10-21 | 2025-11-13 | 167010.73 | 383
Manholes |  | 19 | 2025-08-24 | 2025-09-14 | 2025-09-27 | 2025-10-18 | 1035466.54 | 385
CO-RM-SW-320 | Excavation Works for Main Line Manholes of Rising Main Network | 1 | 2025-08-24 | 2025-08-24 | 2025-09-27 | 2025-09-27 | 200412.88 | 385
CO-RM-SW-330 | Installation RC Footing Works for Main Line Manholes of Rising Main Network | 3 | 2025-08-25 | 2025-08-27 | 2025-09-28 | 2025-09-30 | 66804.29 | 385
CO-RM-SW-340 | Install Grp Liner Wall Works for Main Line Manholes of Rising Main Network | 6 | 2025-08-28 | 2025-09-03 | 2025-10-01 | 2025-10-07 | 501032.2 | 385
CO-RM-SW-350 | Pouring Grp Liner Wall Works for Main Line Manholes of Rising Main Network | 3 | 2025-09-04 | 2025-09-07 | 2025-10-08 | 2025-10-11 | 66804.29 | 385
CO-RM-SW-360 | Backfilling Works for Main Line Manholes of Rising Main Network | 5 | 2025-09-08 | 2025-09-13 | 2025-10-12 | 2025-10-16 | 100206.44 | 385
CO-RM-SW-370 | Testing Works for Main Line Manholes of Rising Main Network | 1 | 2025-09-14 | 2025-09-14 | 2025-10-18 | 2025-10-18 | 100206.44 | 385
Valves Chamber |  | 31 | 2025-08-24 | 2025-09-29 | 2025-09-27 | 2025-11-01 | 832052.26 | 394
CO-RM-SW-380 | Excavation Works for Valve Chambers and Washout chamber of Rising Main Network | 1 | 2025-08-24 | 2025-08-24 | 2025-09-27 | 2025-09-27 | 173090.88 | 394
CO-RM-SW-390 | RC Footing Works for Valve Chambers and Washout chamber of Rising Main Network | 6 | 2025-08-25 | 2025-08-31 | 2025-09-28 | 2025-10-04 | 43272.72 | 394
CO-RM-SW-400 | RC Wall Works for Valve Chambers and Washout chamber of Rising Main Network | 7 | 2025-09-01 | 2025-09-08 | 2025-10-05 | 2025-10-12 | 389454.48 | 394
CO-RM-SW-410 | RC Slab Works for Valve Chambers and Washout chamber of Rising Main Network | 7 | 2025-09-09 | 2025-09-16 | 2025-10-13 | 2025-10-20 | 43272.72 | 394
CO-RM-SW-420 | Insulation Works for Valve Chambers and Washout chamber of Rising Main Network | 2 | 2025-09-17 | 2025-09-18 | 2025-10-21 | 2025-10-22 | 43272.72 | 394
CO-RM-SW-430 | Backfilling Works for Valve Chambers and Washout chamber of Rising Main Network | 5 | 2025-09-20 | 2025-09-25 | 2025-10-23 | 2025-10-28 | 53143.29 | 394
CO-RM-SW-440 | Testing and Covering Works for Valve Chambers and Washout chamber of Rising Main Network | 3 | 2025-09-27 | 2025-09-29 | 2025-10-29 | 2025-11-01 | 86545.44 | 394
Road 09 Local 2 ( 2278 LM ) |  | 421 | 2025-06-02 | 2026-10-20 | 2025-07-09 | 2026-10-01 | 20167276.66 | -7
SW_1 |  | 415 | 2025-06-02 | 2026-10-13 | 2025-07-09 | 2026-09-24 | 16136077.81 | -8
Sewage Network |  | 34 | 2025-06-02 | 2025-07-15 | 2025-07-09 | 2025-08-17 | 2353866.35 | 53
Main Line Sections |  | 34 | 2025-06-02 | 2025-07-15 | 2025-07-09 | 2025-08-17 | 1714966.75 | 53
CO-R09.S01-SW-100 | Trench Excavation and Bedding Works for Main Lines of Sewage Network-[Road 09] -[SW-1] | 10 | 2025-06-02 | 2025-06-17 | 2025-07-09 | 2025-07-20 | 353398.99 | 45
CO-R09.S01-SW-120 | Pipes Laying Works for Main Lines of Sewage Network-[Road 09] -[SW-1] | 12 | 2025-06-18 | 2025-07-01 | 2025-07-21 | 2025-08-03 | 1184868.26 | 53
CO-R09.S01-SW-130 | Trench Backfilling and Compaction Works for Main Lines of Sewage Network-[Road 09] -[SW-1] | 12 | 2025-07-02 | 2025-07-15 | 2025-08-04 | 2025-08-17 | 176699.49 | 53
Manholes |  | 19 | 2025-06-18 | 2025-07-09 | 2025-07-21 | 2025-08-11 | 638899.61 | 58
CO-R09.S01-SW-160 | Excavation Works for Main Line Manholes of Sewage Network-[Road 09] -[SW-1] | 1 | 2025-06-18 | 2025-06-18 | 2025-07-21 | 2025-07-21 | 106483.27 | 58
CO-R09.S01-SW-170 | Installation RC Footing Works for Main Line Manholes of Sewage Network-[Road 09] -[SW-1] | 3 | 2025-06-19 | 2025-06-22 | 2025-07-22 | 2025-07-24 | 70988.85 | 58
CO-R09.S01-SW-180 | Install Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 09] -[SW-1] | 6 | 2025-06-23 | 2025-06-29 | 2025-07-26 | 2025-07-31 | 283955.38 | 58
CO-R09.S01-SW-190 | Pouring Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 09] -[SW-1] | 3 | 2025-06-30 | 2025-07-02 | 2025-08-02 | 2025-08-04 | 35494.42 | 58
CO-R09.S01-SW-200 | Backfilling Works for Main Line Manholes of Sewage Network-[Road 09] -[SW-1] | 5 | 2025-07-03 | 2025-07-08 | 2025-08-05 | 2025-08-10 | 106483.27 | 58
CO-R09.S01-SW-210 | Testing Works for Main Line Manholes of Sewage Network-[Road 09] -[SW-1] | 1 | 2025-07-09 | 2025-07-09 | 2025-08-11 | 2025-08-11 | 35494.42 | 58
Storm Drainage Network |  | 61 | 2025-09-28 | 2025-12-07 | 2025-09-08 | 2025-11-18 | 9132078.02 | 172
Main Line Sections |  | 61 | 2025-09-28 | 2025-12-07 | 2025-09-08 | 2025-11-18 | 8517909.28 | 172
CO-R09.S01-SD-100 | Trench Excavation and Bedding Works for Main Lines of Storm Drainage Network-[Road 09] -[SW-1] | 10 | 2025-09-28 | 2025-10-08 | 2025-09-08 | 2025-09-18 | 100408.21 | -16
CO-R09.S01-SD-120 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 09] -[SW-1] | 10 | 2025-10-09 | 2025-10-20 | 2025-09-20 | 2025-10-01 | 8367296.97 | -16
CO-R09.S01-SD-130 | Trench Backfilling and Compaction Works for Main Lines of Storm Drainage Network-[Road 09] -[SW-1] | 20 | 2025-11-15 | 2025-12-07 | 2025-10-27 | 2025-11-18 | 50204.11 | 172
Manholes |  | 21 | 2025-10-09 | 2025-11-02 | 2025-09-20 | 2025-10-14 | 364694.13 | 19
CO-R09.S01-SD-180 | Trench Excavation and Bedding Works for Manholes of Storm Drainage Network-[Road 09] -[SW-1] | 2 | 2025-10-09 | 2025-10-11 | 2025-09-20 | 2025-09-21 | 57583.28 | 19
CO-R09.S01-SD-190 | Install RC Footing Works for Manholes of Storm Drainage Network-[Road 09] -[SW-1] | 3 | 2025-10-12 | 2025-10-14 | 2025-09-22 | 2025-09-25 | 19194.43 | 19
CO-R09.S01-SD-200 | Install RC Wall Rings & Slab Works for Manholes of Storm Drainage Network-[Road 09] -[SW-1] | 7 | 2025-10-15 | 2025-10-22 | 2025-09-27 | 2025-10-04 | 172749.85 | 19
CO-R09.S01-SD-210 | Testing Works for Manholes of Storm Drainage Network-[Road 09] -[SW-1] | 2 | 2025-10-23 | 2025-10-25 | 2025-10-05 | 2025-10-06 | 38388.86 | 19
CO-R09.S01-SD-220 | Backfilling Works for Manholes of Storm Drainage Network-[Road 09] -[SW-1] | 7 | 2025-10-26 | 2025-11-02 | 2025-10-07 | 2025-10-14 | 76777.71 | 19
Catch Basin Sections |  | 30 | 2025-11-03 | 2025-12-07 | 2025-10-15 | 2025-11-18 | 249474.61 | 28
CO-R09.S01-SD-140 | Trench Excavation and Bedding Works for Catch Basins of Storm Drainage Network-[Road 09] -[SW-1] | 6 | 2025-11-03 | 2025-11-09 | 2025-10-15 | 2025-10-21 | 41579.1 | 28
CO-R09.S01-SD-150 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 09] -[SW-1] | 7 | 2025-11-10 | 2025-11-17 | 2025-10-22 | 2025-10-29 | 124737.3 | 28
CO-R09.S01-SD-160 | Testing Works for Catch Basins of Storm Drainage Network-[Road 09] -[SW-1] | 7 | 2025-11-18 | 2025-11-25 | 2025-10-30 | 2025-11-06 | 27719.4 | 28
CO-R09.S01-SD-170 | Trench Backfilling and Compaction Works for Catch Basins of Storm Drainage Network-[Road 09] -[SW-1] | 10 | 2025-11-26 | 2025-12-07 | 2025-11-08 | 2025-11-18 | 55438.8 | 28
Irrigation Network |  | 61 | 2025-12-08 | 2026-02-16 | 2025-11-19 | 2025-12-28 | 1602671.31 | 1
Main Line Pipes |  | 61 | 2025-12-08 | 2026-02-16 | 2025-11-19 | 2025-12-28 | 1602671.31 | 1
CO-R09.S01-IR-100 | Trench Excavation and Bedding Works for Main Lines of Irrigation Network-[Road 09] -[SW-1] | 7 | 2025-12-08 | 2025-12-15 | 2025-11-19 | 2025-11-26 | 42614.01 | 28
CO-R09.S01-IR-110 | Pipes Laying Works for Main Lines of Irrigation Network-[Road 09] -[SW-1] | 10 | 2026-01-06 | 2026-01-17 | 2025-11-27 | 2025-12-08 | 1419966.63 | 10
CO-R09.S01-IR-120 | Installation Works for Main Line Valves of Irrigation Network-[Road 09] -[SW-1] | 7 | 2026-01-28 | 2026-02-04 | 2025-12-09 | 2025-12-16 | 118783.66 | 1
CO-R09.S01-IR-140 | Trench Backfilling and Compaction Works for Main Lines of Irrigation Network-[Road 09] -[SW-1] | 10 | 2026-02-05 | 2026-02-16 | 2025-12-17 | 2025-12-28 | 21307.01 | 1
Street Lighting Network |  | 162 | 2026-02-17 | 2026-09-01 | 2025-12-29 | 2026-08-13 | 273720.46 | -8
Lighting Poles Works |  | 76 | 2026-02-17 | 2026-05-19 | 2025-12-29 | 2026-04-30 | 140446.74 | 16
CO-R09.S01-SL-100 | Foundation Excavation Works for Lighting Poles of Street Lighting Network-[Road 09] -[SW-1] | 10 | 2026-02-17 | 2026-02-28 | 2025-12-29 | 2026-01-08 | 4663.5 | 1
CO-R09.S01-SL-110 | Installation Works for Lighting Poles Foundation of Street Lighting Network-[Road 09] -[SW-1] | 12 | 2026-03-01 | 2026-03-14 | 2026-01-10 | 2026-01-22 | 17826.69 | 1
CO-R09.S01-SL-120 | Installation Works for Lighting Poles of Street Lighting Network-[Road 09] -[SW-1] | 11 | 2026-04-08 | 2026-04-20 | 2026-02-14 | 2026-02-25 | 51298.52 | 1
CO-R09.S01-SL-210 | Backfilling Works for Lighting Poles of Street Lighting Network-[Road 09] -[SW-1] | 12 | 2026-04-30 | 2026-05-13 | 2026-04-12 | 2026-04-25 | 18654.01 | -8
CO-R09.S01-SL-130 | Installation Works for Lighting Fixtures With Drop Wire of Street Lighting Network-[Road 09] -[SW-1] | 12 | 2026-05-06 | 2026-05-19 | 2026-04-18 | 2026-04-30 | 29350.02 | 16
CO-R09.S01-SL-200 | Testing Works for Lighting Poles of Street Lighting Network-[Road 09] -[SW-1] | 5 | 2026-05-14 | 2026-05-19 | 2026-04-26 | 2026-04-30 | 18654.01 | 16
Cabling Works |  | 30 | 2026-03-01 | 2026-04-07 | 2026-01-10 | 2026-02-12 | 94451.91 | 1
CO-R09.S01-SL-140 | Trench Excavation and Bedding Works for Street Lighting Network-[Road 09] -[SW-1] | 10 | 2026-03-01 | 2026-03-11 | 2026-01-10 | 2026-01-20 | 0 | 1
CO-R09.S01-SL-150 | Cable Laying Works for Street Lighting Network-[Road 09] -[SW-1] | 10 | 2026-03-12 | 2026-03-26 | 2026-01-21 | 2026-02-01 | 87705.35 | 1
CO-R09.S01-SL-160 | Trench Backfilling and Compaction Works for Street Lighting Network-[Road 09] -[SW-1] | 10 | 2026-03-28 | 2026-04-07 | 2026-02-02 | 2026-02-12 | 6746.57 | 1
Distrubution Panel Boards |  | 39 | 2026-07-19 | 2026-09-01 | 2026-06-30 | 2026-08-13 | 38821.81 | -8
CO-R09.S01-SL-170 | Foundation Excavation Works For Panel Boards of Street Lighting Network-[Road 09] -[SW-1] | 15 | 2026-07-19 | 2026-08-04 | 2026-06-30 | 2026-07-16 | 0 | -8
CO-R09.S01-SL-180 | Installation Works for Panel Board Concrete Foundations of Street Lighting Network-[Road 09] -[SW-1] | 12 | 2026-08-05 | 2026-08-18 | 2026-07-18 | 2026-07-30 | 0 | -8
CO-R09.S01-SL-220 | A wall of concrete blocks to install the KWH meter of Street Lighting Network-[Road 09] -[SW-1] | 12 | 2026-08-19 | 2026-09-01 | 2026-08-01 | 2026-08-13 | 38821.81 | -8
CO-R09.S01-SL-190 | Installation Works for Lighting Panel Boards of Street Lighting Network-[Road 09] -[SW-1] | 12 | 2026-08-19 | 2026-09-01 | 2026-08-01 | 2026-08-13 | 0 | -8
Medium Voltage Network |  | 16 | 2026-04-08 | 2026-04-26 | 2026-02-14 | 2026-03-03 | 1203791.39 | 5
Cabling Works |  | 16 | 2026-04-08 | 2026-04-26 | 2026-02-14 | 2026-03-03 | 1203791.39 | 5
CO-R09.S01-MV-100 | Trench Excavation and Bedding Works for Medium Voltage Network-[Road 09] -[SW-1] | 4 | 2026-04-08 | 2026-04-12 | 2026-02-14 | 2026-02-17 | 138631.25 | 5
CO-R09.S01-MV-110 | Cable Laying Works for Medium Voltage Network-[Road 09] -[SW-1] | 5 | 2026-04-13 | 2026-04-18 | 2026-02-18 | 2026-02-23 | 745612.1 | 5
CO-R09.S01-MV-120 | Trench Backfilling and Compaction Works for Medium Voltage Network-[Road 09] -[SW-1] | 7 | 2026-04-19 | 2026-04-26 | 2026-02-24 | 2026-03-03 | 319548.04 | 5
Telecom Network |  | 38 | 2026-05-21 | 2026-07-08 | 2026-05-03 | 2026-06-20 | 166584.78 | -16
Ducts Works |  | 12 | 2026-05-21 | 2026-06-08 | 2026-05-03 | 2026-05-16 | 132124 | -8
CO-R09.S01-TE-100 | Trench Excavation and Bedding Works for Ducts of Telecom Network-[Road 09] -[SW-1] | 2 | 2026-05-21 | 2026-05-23 | 2026-05-03 | 2026-05-04 | 13266 | -16
CO-R09.S01-TE-110 | Pipes Laying Works for Ducts of Telecom Network-[Road 09] -[SW-1] | 4 | 2026-05-24 | 2026-06-01 | 2026-05-05 | 2026-05-09 | 79227.5 | -8
CO-R09.S01-TE-120 | Pouring Plain Concrete Above Ducts of Telecom Network-[Road 09] -[SW-1] | 2 | 2026-06-02 | 2026-06-03 | 2026-05-10 | 2026-05-11 | 13266 | -8
CO-R09.S01-TE-130 | Trench Backfilling and Compaction Works for Ducts of Telecom Network-[Road 09] -[SW-1] | 4 | 2026-06-04 | 2026-06-08 | 2026-05-12 | 2026-05-16 | 26364.5 | -8
Manholes Works |  | 36 | 2026-05-24 | 2026-07-08 | 2026-05-05 | 2026-06-20 | 34460.78 | -16
CO-R09.S01-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 09] -[SW-1] | 12 | 2026-05-24 | 2026-06-10 | 2026-05-05 | 2026-05-18 | 7515.39 | -16
CO-R09.S01-TE-150 | Installation Works for Manholes of Telecom Network-[Road 09] -[SW-1] | 12 | 2026-06-11 | 2026-06-24 | 2026-05-19 | 2026-06-06 | 19430 | -16
CO-R09.S01-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 09] -[SW-1] | 12 | 2026-06-25 | 2026-07-08 | 2026-06-07 | 2026-06-20 | 7515.39 | -16
Road Works |  | 82 | 2026-07-09 | 2026-10-13 | 2026-06-21 | 2026-09-24 | 1403365.5 | -8
Pre-Bituminous Construction |  | 24 | 2026-07-09 | 2026-08-05 | 2026-06-21 | 2026-07-18 | 890287.34 | 20
CO-R09.S01-RD-P-100 | Capping and Subgrade Layer for Road Works-[Road 09] -[SW-1] | 21 | 2026-07-09 | 2026-08-02 | 2026-06-21 | 2026-07-14 | 524763.79 | -4
CO-R09.S01-RD-P-110 | Aggregate Base Course Layer for Road Works-[Road 09] -[SW-1] | 21 | 2026-07-13 | 2026-08-05 | 2026-06-24 | 2026-07-18 | 365523.55 | 20
Pavement Works |  | 58 | 2026-08-06 | 2026-10-13 | 2026-07-19 | 2026-09-24 | 513078.16 | -8
CO-R09.S01-RD-P-120 | Fixing of Curbstone for Sidewalks Pavement-[Road 09] -[SW-1] | 18 | 2026-08-06 | 2026-08-26 | 2026-07-19 | 2026-08-08 | 299298.65 | 20
CO-R09.S01-RD-P-130 | Fixing of Interlock Tiles for Sidewalks Pavement-[Road 09] -[SW-1] | 12 | 2026-09-29 | 2026-10-13 | 2026-09-09 | 2026-09-24 | 213779.51 | -8
SW_2 |  | 411 | 2025-06-18 | 2026-10-20 | 2025-07-21 | 2026-10-01 | 4031198.85 | -7
Sewage Network |  | 36 | 2025-06-18 | 2025-07-29 | 2025-07-21 | 2025-08-31 | 375529.05 | 51
Main Line Sections |  | 36 | 2025-06-18 | 2025-07-29 | 2025-07-21 | 2025-08-31 | 284501.38 | 51
CO-R09.S02-SW-100 | Trench Excavation and Bedding Works for Main Lines of Sewage Network-[Road 09]-[SW-2] | 12 | 2025-06-18 | 2025-07-01 | 2025-07-21 | 2025-08-03 | 63214.65 | 45
CO-R09.S02-SW-120 | Pipes Laying Works for Main Lines of Sewage Network-[Road 09]-[SW-2] | 12 | 2025-07-02 | 2025-07-15 | 2025-08-04 | 2025-08-17 | 189643.95 | 51
CO-R09.S02-SW-130 | Trench Backfilling and Compaction Works for Main Lines of Sewage Network-[Road 09]-[SW-2] | 12 | 2025-07-16 | 2025-07-29 | 2025-08-18 | 2025-08-31 | 31642.78 | 51
Manholes |  | 19 | 2025-07-02 | 2025-07-23 | 2025-08-04 | 2025-08-25 | 91027.67 | 56
CO-R09.S02-SW-160 | Excavation Works for Main Line Manholes of Sewage Network-[Road 09]-[SW-2] | 1 | 2025-07-02 | 2025-07-02 | 2025-08-04 | 2025-08-04 | 15171.28 | 56
CO-R09.S02-SW-170 | Installation RC Footing Works for Main Line Manholes of Sewage Network-[Road 09]-[SW-2] | 3 | 2025-07-03 | 2025-07-06 | 2025-08-05 | 2025-08-07 | 10114.19 | 56
CO-R09.S02-SW-180 | Install Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 09]-[SW-2] | 6 | 2025-07-07 | 2025-07-13 | 2025-08-09 | 2025-08-14 | 40456.74 | 56
CO-R09.S02-SW-190 | Pouring Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 09]-[SW-2] | 3 | 2025-07-14 | 2025-07-16 | 2025-08-16 | 2025-08-18 | 5057.09 | 56
CO-R09.S02-SW-200 | Backfilling Works for Main Line Manholes of Sewage Network-[Road 09]-[SW-2] | 5 | 2025-07-17 | 2025-07-22 | 2025-08-19 | 2025-08-24 | 15171.28 | 56
CO-R09.S02-SW-210 | Testing Works for Main Line Manholes of Sewage Network-[Road 09]-[SW-2] | 1 | 2025-07-23 | 2025-07-23 | 2025-08-25 | 2025-08-25 | 5057.09 | 56
Storm Drainage Network |  | 114 | 2025-10-09 | 2026-02-18 | 2025-09-20 | 2025-12-20 | 1079481.68 | 174
Main Line Sections |  | 37 | 2025-10-09 | 2025-11-20 | 2025-09-20 | 2025-11-02 | 465312.94 | 89
CO-R09.S02-SD-100 | Trench Excavation and Bedding Works for Main Lines of Storm Drainage Network-[Road 09]-[SW-2] | 10 | 2025-10-09 | 2025-10-20 | 2025-09-20 | 2025-10-01 | 103402.88 | -16
CO-R09.S02-SD-120 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 09]-[SW-2] | 10 | 2025-10-21 | 2025-11-01 | 2025-10-02 | 2025-10-13 | 310208.63 | -16
CO-R09.S02-SD-130 | Trench Backfilling and Compaction Works for Main Lines of Storm Drainage Network-[Road 09]-[SW-2] | 15 | 2025-11-04 | 2025-11-20 | 2025-10-16 | 2025-11-02 | 51701.44 | 89
Manholes |  | 16 | 2025-11-03 | 2025-11-20 | 2025-10-15 | 2025-11-02 | 364694.13 | 19
CO-R09.S02-SD-180 | Trench Excavation and Bedding Works for Manholes of Storm Drainage Network-[Road 09]-[SW-2] | 1 | 2025-11-03 | 2025-11-03 | 2025-10-15 | 2025-10-15 | 57583.28 | 19
CO-R09.S02-SD-190 | Install RC Footing Works for Manholes of Storm Drainage Network-[Road 09]-[SW-2] | 2 | 2025-11-04 | 2025-11-05 | 2025-10-16 | 2025-10-18 | 19194.43 | 19
CO-R09.S02-SD-200 | Install RC Wall Rings & Slab Works for Manholes of Storm Drainage Network-[Road 09]-[SW-2] | 4 | 2025-11-06 | 2025-11-10 | 2025-10-19 | 2025-10-22 | 172749.85 | 19
CO-R09.S02-SD-210 | Testing Works for Manholes of Storm Drainage Network-[Road 09]-[SW-2] | 2 | 2025-11-11 | 2025-11-12 | 2025-10-23 | 2025-10-25 | 38388.86 | 19
CO-R09.S02-SD-220 | Backfilling Works for Manholes of Storm Drainage Network-[Road 09]-[SW-2] | 7 | 2025-11-13 | 2025-11-20 | 2025-10-26 | 2025-11-02 | 76777.71 | 19
Catch Basin Sections |  | 77 | 2025-11-22 | 2026-02-18 | 2025-11-03 | 2025-12-20 | 249474.61 | 174
CO-R09.S02-SD-140 | Trench Excavation and Bedding Works for Catch Basins of Storm Drainage Network-[Road 09]-[SW-2] | 6 | 2025-11-22 | 2025-11-27 | 2025-11-03 | 2025-11-09 | 41579.1 | 19
CO-R09.S02-SD-150 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 09]-[SW-2] | 7 | 2026-01-29 | 2026-02-05 | 2025-11-30 | 2025-12-07 | 124737.3 | 174
CO-R09.S02-SD-160 | Testing Works for Catch Basins of Storm Drainage Network-[Road 09]-[SW-2] | 4 | 2026-02-07 | 2026-02-10 | 2025-12-08 | 2025-12-11 | 27719.4 | 174
CO-R09.S02-SD-170 | Trench Backfilling and Compaction Works for Catch Basins of Storm Drainage Network-[Road 09]-[SW-2] | 7 | 2026-02-11 | 2026-02-18 | 2025-12-13 | 2025-12-20 | 55438.8 | 174
Potable Water Network |  | 79 | 2025-11-22 | 2026-02-21 | 2025-11-03 | 2025-12-29 | 432458.35 | 33
Main Line Sections |  | 79 | 2025-11-22 | 2026-02-21 | 2025-11-03 | 2025-12-29 | 254907.68 | 33
CO-R09.S02-PW-100 | Trench Excavation and Bedding Works for Main Lines of Potable Water Network-[Road 09]-[SW-2] | 7 | 2025-11-22 | 2025-11-29 | 2025-11-03 | 2025-11-10 | 78463.98 | 89
CO-R09.S02-PW-110 | Pipes Laying and accessories for Main Lines of Potable Water Network-[Road 09]-[SW-2] | 8 | 2026-01-31 | 2026-02-08 | 2025-12-10 | 2025-12-18 | 96160.67 | 36
CO-R09.S02-PW-130 | Trench Backfilling and Compaction Works for Main Lines of Potable Water Network-[Road 09]-[SW-2] | 8 | 2026-02-12 | 2026-02-21 | 2025-12-21 | 2025-12-29 | 80283.03 | 33
Valve Chamber |  | 6 | 2025-11-30 | 2025-12-06 | 2025-11-11 | 2025-11-17 | 63935.42 | 99
CO-R09.S02-PW-210 | Installation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 09]-[SW-2] | 6 | 2025-11-30 | 2025-12-06 | 2025-11-11 | 2025-11-17 | 63935.42 | 99
Fire Hydrant |  | 72 | 2025-11-30 | 2026-02-21 | 2025-11-11 | 2025-12-29 | 113615.25 | 33
CO-R09.S02-PW-140 | Excavation Works for Fire Hydrants of Potable Water Network-[Road 09]-[SW-2] | 5 | 2025-11-30 | 2025-12-04 | 2025-11-11 | 2025-11-16 | 17042.29 | 89
CO-R09.S02-PW-150 | Installation Works for Fire Hydrant of Potable Water Network-[Road 09]-[SW-2] | 6 | 2026-02-09 | 2026-02-15 | 2025-12-17 | 2025-12-23 | 73849.91 | 33
CO-R09.S02-PW-160 | Trench Backfilling and Compaction Works for Fire Hydrants of Potable Water Network-[Road 09]-[SW-2] | 5 | 2026-02-16 | 2026-02-21 | 2025-12-24 | 2025-12-29 | 22723.05 | 33
Street Lighting Network |  | 167 | 2026-02-22 | 2026-09-13 | 2025-12-30 | 2026-08-25 | 573622.71 | 14
Lighting Poles Works |  | 95 | 2026-02-22 | 2026-06-20 | 2025-12-30 | 2026-06-01 | 140446.74 | -8
CO-R09.S02-SL-100 | Foundation Excavation Works for Lighting Poles of Street Lighting Network-[Road 09]-[SW-2] | 9 | 2026-02-22 | 2026-03-03 | 2025-12-30 | 2026-01-08 | 4663.5 | 33
CO-R09.S02-SL-110 | Installation Works for Lighting Poles Foundation of Street Lighting Network-[Road 09]-[SW-2] | 9 | 2026-03-10 | 2026-03-19 | 2026-01-10 | 2026-01-19 | 17826.69 | 28
CO-R09.S02-SL-120 | Installation Works for Lighting Poles of Street Lighting Network-[Road 09]-[SW-2] | 9 | 2026-04-13 | 2026-04-22 | 2026-02-08 | 2026-02-17 | 51298.52 | 11
CO-R09.S02-SL-210 | Backfilling Works for Lighting Poles of Street Lighting Network-[Road 09]-[SW-2] | 20 | 2026-05-14 | 2026-06-10 | 2026-04-26 | 2026-05-18 | 18654.01 | -8
CO-R09.S02-SL-130 | Installation Works for Lighting Fixtures With Drop Wire of Street Lighting Network-[Road 09]-[SW-2] | 17 | 2026-06-01 | 2026-06-20 | 2026-05-09 | 2026-06-01 | 29350.02 | -8
CO-R09.S02-SL-200 | Testing Works for Lighting Poles of Street Lighting Network-[Road 09]-[SW-2] | 8 | 2026-06-11 | 2026-06-20 | 2026-05-19 | 2026-06-01 | 18654.01 | -8
Cabling Works |  | 30 | 2026-04-23 | 2026-06-01 | 2026-02-18 | 2026-03-28 | 94451.91 | 44
CO-R09.S02-SL-140 | Trench Excavation and Bedding Works for Street Lighting Network-[Road 09]-[SW-2] | 10 | 2026-04-23 | 2026-05-04 | 2026-02-18 | 2026-03-01 | 0 | 44
CO-R09.S02-SL-150 | Cable Laying Works for Street Lighting Network-[Road 09]-[SW-2] | 10 | 2026-05-05 | 2026-05-16 | 2026-03-02 | 2026-03-12 | 87705.35 | 44
CO-R09.S02-SL-160 | Trench Backfilling and Compaction Works for Street Lighting Network-[Road 09]-[SW-2] | 10 | 2026-05-17 | 2026-06-01 | 2026-03-14 | 2026-03-28 | 6746.57 | 44
Distrubution Panel Boards |  | 48 | 2026-07-19 | 2026-09-13 | 2026-06-30 | 2026-08-25 | 338724.06 | 14
CO-R09.S02-SL-170 | Foundation Excavation Works For Panel Boards of Street Lighting Network-[Road 09]-[SW-2] | 10 | 2026-07-19 | 2026-07-29 | 2026-06-30 | 2026-07-11 | 43293.39 | 14
CO-R09.S02-SL-180 | Installation Works for Panel Board Concrete Foundations of Street Lighting Network-[Road 09]-[SW-2] | 10 | 2026-07-30 | 2026-08-10 | 2026-07-12 | 2026-07-22 | 48506.22 | 14
CO-R09.S02-SL-190 | Installation Works for Lighting Panel Boards of Street Lighting Network-[Road 09]-[SW-2] | 10 | 2026-08-11 | 2026-08-22 | 2026-07-23 | 2026-08-03 | 177856.16 | 14
CO-R09.S02-SL-220 | A wall of concrete blocks to install the KWH meter of Street Lighting Network-[Road 09]-[SW-2] | 18 | 2026-08-23 | 2026-09-13 | 2026-08-04 | 2026-08-25 | 69068.29 | 14
Telecom Network |  | 47 | 2026-06-09 | 2026-08-02 | 2026-05-17 | 2026-07-14 | 166741.56 | -16
Ducts Works |  | 24 | 2026-06-09 | 2026-07-06 | 2026-05-17 | 2026-06-17 | 132124 | 7
CO-R09.S02-TE-100 | Trench Excavation and Bedding Works for Ducts of Telecom Network-[Road 09]-[SW-2] | 3 | 2026-06-09 | 2026-06-11 | 2026-05-17 | 2026-05-19 | 13266 | -8
CO-R09.S02-TE-110 | Pipes Laying Works for Ducts of Telecom Network-[Road 09]-[SW-2] | 7 | 2026-06-13 | 2026-06-20 | 2026-05-20 | 2026-06-01 | 79227.5 | 7
CO-R09.S02-TE-120 | Pouring Plain Concrete Above Ducts of Telecom Network-[Road 09]-[SW-2] | 7 | 2026-06-21 | 2026-06-28 | 2026-06-02 | 2026-06-09 | 13266 | 7
CO-R09.S02-TE-130 | Trench Backfilling and Compaction Works for Ducts of Telecom Network-[Road 09]-[SW-2] | 7 | 2026-06-29 | 2026-07-06 | 2026-06-10 | 2026-06-17 | 26364.5 | 7
Manholes Works |  | 21 | 2026-07-09 | 2026-08-02 | 2026-06-21 | 2026-07-14 | 34617.56 | -16
CO-R09.S02-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 09]-[SW-2] | 7 | 2026-07-09 | 2026-07-16 | 2026-06-21 | 2026-06-28 | 6300.28 | -16
CO-R09.S02-TE-150 | Installation Works for Manholes of Telecom Network-[Road 09]-[SW-2] | 7 | 2026-07-18 | 2026-07-25 | 2026-06-29 | 2026-07-06 | 22017 | -16
CO-R09.S02-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 09]-[SW-2] | 7 | 2026-07-26 | 2026-08-02 | 2026-07-07 | 2026-07-14 | 6300.28 | -16
Road Works |  | 67 | 2026-08-03 | 2026-10-20 | 2026-07-15 | 2026-10-01 | 1403365.5 | -7
Pre-Bituminous Construction |  | 21 | 2026-08-03 | 2026-08-26 | 2026-07-15 | 2026-08-08 | 890287.34 | 33
CO-R09.S02-RD-P-100 | Capping and Subgrade Layer for Road Works-[Road 09]-[SW-2] | 12 | 2026-08-03 | 2026-08-16 | 2026-07-15 | 2026-07-28 | 524763.79 | -16
CO-R09.S02-RD-P-110 | Aggregate Base Course Layer for Road Works-[Road 09]-[SW-2] | 18 | 2026-08-06 | 2026-08-26 | 2026-07-19 | 2026-08-08 | 365523.55 | 33
Pavement Works |  | 61 | 2026-08-10 | 2026-10-20 | 2026-07-22 | 2026-10-01 | 513078.16 | -7
CO-R09.S02-RD-P-120 | Fixing of Curbstone for Sidewalks Pavement-[Road 09]-[SW-2] | 18 | 2026-08-10 | 2026-08-30 | 2026-07-22 | 2026-08-11 | 299298.65 | 33
CO-R09.S02-RD-P-130 | Fixing of Interlock Tiles for Sidewalks Pavement-[Road 09]-[SW-2] | 18 | 2026-09-29 | 2026-10-20 | 2026-09-09 | 2026-10-01 | 213779.51 | -7
Road 10 Local 2 ( 2352 LM ) |  | 438 | 2025-05-13 | 2026-10-20 | 2025-06-28 | 2026-10-01 | 14743071.03 | -16
SW-3 |  | 343 | 2025-09-03 | 2026-10-18 | 2025-08-16 | 2026-09-29 | 6415606.61 | -16
SW_3-East |  | 343 | 2025-09-03 | 2026-10-18 | 2025-08-16 | 2026-09-29 | 3350723.9 | -16
Storm Drainage Network |  | 79 | 2025-09-03 | 2025-12-04 | 2025-08-16 | 2025-10-23 | 521513.71 | 39
Main Line Sections |  | 45 | 2025-09-03 | 2025-10-26 | 2025-08-16 | 2025-10-07 | 203079.37 | 49
CO-R10.S03-ES-SD-100 | Trench Excavation and Bedding Works for Main Lines of Storm Drainage Network-[Road 10]-[SW-3] | 10 | 2025-09-03 | 2025-09-14 | 2025-08-16 | 2025-08-26 | 45128.75 | -16
CO-R10.S03-ES-SD-120 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 10]-[SW-3] | 15 | 2025-09-21 | 2025-10-08 | 2025-09-02 | 2025-09-18 | 135386.25 | 49
CO-R10.S03-ES-SD-130 | Trench Backfilling and Compaction Works for Main Lines of Storm Drainage Network-[Road 10]-[SW-3] | 15 | 2025-10-09 | 2025-10-26 | 2025-09-20 | 2025-10-07 | 22564.37 | 49
Manholes |  | 14 | 2025-09-21 | 2025-10-07 | 2025-09-02 | 2025-09-17 | 193344.83 | 59
CO-R10.S03-ES-SD-180 | Trench Excavation and Bedding Works for Manholes of Storm Drainage Network-[Road 10]-[SW-3] | 1 | 2025-09-21 | 2025-09-21 | 2025-09-02 | 2025-09-02 | 30528.13 | 59
CO-R10.S03-ES-SD-190 | Install RC Footing Works for Manholes of Storm Drainage Network-[Road 10]-[SW-3] | 1 | 2025-09-22 | 2025-09-22 | 2025-09-03 | 2025-09-03 | 10176.04 | 59
CO-R10.S03-ES-SD-200 | Install RC Wall Rings & Slab Works for Manholes of Storm Drainage Network-[Road 10]-[SW-3] | 4 | 2025-09-24 | 2025-09-28 | 2025-09-04 | 2025-09-08 | 91584.39 | 59
CO-R10.S03-ES-SD-210 | Testing Works for Manholes of Storm Drainage Network-[Road 10]-[SW-3] | 1 | 2025-09-29 | 2025-09-29 | 2025-09-09 | 2025-09-09 | 20352.09 | 59
CO-R10.S03-ES-SD-220 | Backfilling Works for Manholes of Storm Drainage Network-[Road 10]-[SW-3] | 7 | 2025-09-30 | 2025-10-07 | 2025-09-10 | 2025-09-17 | 40704.18 | 59
Catch Basin Sections |  | 50 | 2025-10-08 | 2025-12-04 | 2025-09-18 | 2025-10-23 | 125089.51 | 39
CO-R10.S03-ES-SD-140 | Trench Excavation and Bedding Works for Catch Basins of Storm Drainage Network-[Road 10]-[SW-3] | 6 | 2025-10-08 | 2025-10-14 | 2025-09-18 | 2025-09-25 | 20848.43 | 59
CO-R10.S03-ES-SD-150 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 10]-[SW-3] | 7 | 2025-11-08 | 2025-11-15 | 2025-09-27 | 2025-10-04 | 62544.75 | 39
CO-R10.S03-ES-SD-160 | Testing Works for Catch Basins of Storm Drainage Network-[Road 10]-[SW-3] | 10 | 2025-11-16 | 2025-11-26 | 2025-10-05 | 2025-10-15 | 13898.77 | 39
CO-R10.S03-ES-SD-170 | Trench Backfilling and Compaction Works for Catch Basins of Storm Drainage Network-[Road 10]-[SW-3] | 7 | 2025-11-27 | 2025-12-04 | 2025-10-16 | 2025-10-23 | 27797.55 | 39
Potable Water Network |  | 50 | 2025-10-27 | 2025-12-23 | 2025-10-08 | 2025-11-04 | 305749.95 | 23
Main Line Sections |  | 50 | 2025-10-27 | 2025-12-23 | 2025-10-08 | 2025-11-04 | 166921.39 | 23
CO-R10.S03-ES-PW-100 | Trench Excavation and Bedding Works for Main Lines of Potable Water Network-[Road 10]-[SW-3] | 6 | 2025-10-27 | 2025-11-02 | 2025-10-08 | 2025-10-14 | 37093.64 | 49
CO-R10.S03-ES-PW-110 | Pipes Laying and accessories for Main Lines of Potable Water Network-[Road 10]-[SW-3] | 6 | 2025-12-03 | 2025-12-09 | 2025-10-15 | 2025-10-21 | 92734.1 | 23
CO-R10.S03-ES-PW-130 | Trench Backfilling and Compaction Works for Main Lines of Potable Water Network-[Road 10]-[SW-3] | 6 | 2025-12-17 | 2025-12-23 | 2025-10-29 | 2025-11-04 | 37093.64 | 23
Valve Chamber |  | 16 | 2025-11-03 | 2025-11-20 | 2025-10-15 | 2025-11-02 | 82020.94 | 51
CO-R10.S03-ES-PW-170 | Excavation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-3] | 1 | 2025-11-03 | 2025-11-03 | 2025-10-15 | 2025-10-15 | 1160.87 | 51
CO-R10.S03-ES-PW-180 | RC Footing Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-3] | 3 | 2025-11-04 | 2025-11-06 | 2025-10-16 | 2025-10-19 | 6528.67 | 51
CO-R10.S03-ES-PW-190 | RC Wall Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-3] | 6 | 2025-11-08 | 2025-11-13 | 2025-10-20 | 2025-10-26 | 15233.56 | 51
CO-R10.S03-ES-PW-200 | RC Slab Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-3] | 2 | 2025-11-15 | 2025-11-16 | 2025-10-27 | 2025-10-28 | 8704.89 | 51
CO-R10.S03-ES-PW-210 | Insulation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-3] | 1 | 2025-11-17 | 2025-11-17 | 2025-10-29 | 2025-10-29 | 41688.07 | 51
CO-R10.S03-ES-PW-220 | Backfilling Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-3] | 3 | 2025-11-18 | 2025-11-20 | 2025-10-30 | 2025-11-02 | 8704.89 | 51
Fire Hydrant |  | 15 | 2025-12-07 | 2025-12-23 | 2025-10-19 | 2025-11-04 | 56807.63 | 23
CO-R10.S03-ES-PW-140 | Excavation Works for Fire Hydrants of Potable Water Network-[Road 10]-[SW-3] | 6 | 2025-12-07 | 2025-12-13 | 2025-10-19 | 2025-10-25 | 8521.14 | 23
CO-R10.S03-ES-PW-150 | Installation Works for Fire Hydrant of Potable Water Network-[Road 10]-[SW-3] | 6 | 2025-12-14 | 2025-12-20 | 2025-10-26 | 2025-11-01 | 36924.96 | 23
CO-R10.S03-ES-PW-160 | Trench Backfilling and Compaction Works for Fire Hydrants of Potable Water Network-[Road 10]-[SW-3] | 6 | 2025-12-17 | 2025-12-23 | 2025-10-29 | 2025-11-04 | 11361.53 | 23
Irrigation Network |  | 23 | 2025-12-24 | 2026-01-19 | 2025-11-05 | 2025-12-01 | 1058935.8 | 23
Main Line Pipes |  | 23 | 2025-12-24 | 2026-01-19 | 2025-11-05 | 2025-12-01 | 1058935.8 | 23
CO-R10.S03-ES-IR-100 | Trench Excavation and Bedding Works for Main Lines of Irrigation Network-[Road 10]-[SW-3] | 7 | 2025-12-24 | 2025-12-31 | 2025-11-05 | 2025-11-12 | 236979 | 23
CO-R10.S03-ES-IR-110 | Pipes Laying Works for Main Lines of Irrigation Network-[Road 10]-[SW-3] | 7 | 2026-01-01 | 2026-01-08 | 2025-11-13 | 2025-11-20 | 238185 | 23
CO-R10.S03-ES-IR-120 | Installation Works for Main Line Valves of Irrigation Network-[Road 10]-[SW-3] | 2 | 2026-01-10 | 2026-01-11 | 2025-11-22 | 2025-11-23 | 544074.3 | 23
CO-R10.S03-ES-IR-130 | Trench Backfilling and Compaction Works for Main Lines of Irrigation Network-[Road 10]-[SW-3] | 7 | 2026-01-12 | 2026-01-19 | 2025-11-24 | 2025-12-01 | 39697.5 | 23
Street Lighting Network |  | 147 | 2026-01-20 | 2026-07-18 | 2025-12-02 | 2026-06-29 | 398748.28 | 0
Lighting Poles Works |  | 65 | 2026-01-20 | 2026-04-08 | 2025-12-02 | 2026-02-16 | 68790.24 | 38
CO-R10.S03-ES-SL-100 | Foundation Excavation Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2026-01-20 | 2026-02-02 | 2025-12-02 | 2025-12-15 | 2284.16 | 23
CO-R10.S03-ES-SL-110 | Installation Works for Lighting Poles Foundation of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2026-01-26 | 2026-02-08 | 2025-12-08 | 2025-12-21 | 8731.44 | 23
CO-R10.S03-ES-SL-120 | Installation Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-3] | 18 | 2026-02-01 | 2026-02-21 | 2025-12-14 | 2026-01-03 | 25125.8 | 23
CO-R10.S03-ES-SL-130 | Installation Works for Lighting Fixtures With Drop Wire of Street Lighting Network-[Road 10]-[SW-3] | 18 | 2026-03-15 | 2026-04-08 | 2026-01-26 | 2026-02-16 | 14375.52 | 38
CO-R10.S03-ES-SL-210 | Backfilling Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2026-03-16 | 2026-04-02 | 2026-01-27 | 2026-02-10 | 9136.66 | 1
CO-R10.S03-ES-SL-200 | Testing Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-3] | 5 | 2026-04-02 | 2026-04-08 | 2026-02-10 | 2026-02-16 | 9136.66 | 38
Cabling Works |  | 30 | 2026-02-22 | 2026-03-31 | 2026-01-04 | 2026-02-07 | 47398.36 | 23
CO-R10.S03-ES-SL-140 | Trench Excavation and Bedding Works for Street Lighting Network-[Road 10]-[SW-3] | 10 | 2026-02-22 | 2026-03-04 | 2026-01-04 | 2026-01-14 | 0 | 23
CO-R10.S03-ES-SL-150 | Cable Laying Works for Street Lighting Network-[Road 10]-[SW-3] | 10 | 2026-03-05 | 2026-03-16 | 2026-01-15 | 2026-01-26 | 44012.74 | 23
CO-R10.S03-ES-SL-160 | Trench Backfilling and Compaction Works for Street Lighting Network-[Road 10]-[SW-3] | 10 | 2026-03-17 | 2026-03-31 | 2026-01-27 | 2026-02-07 | 3385.62 | 23
Distrubution Panel Boards |  | 21 | 2026-06-24 | 2026-07-18 | 2026-06-06 | 2026-06-29 | 282559.68 | 0
CO-R10.S03-ES-SL-170 | Foundation Excavation Works For Panel Boards of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2026-06-24 | 2026-07-07 | 2026-06-06 | 2026-06-18 | 21646.7 | 0
CO-R10.S03-ES-SL-220 | A wall of concrete blocks to install the KWH meter of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2026-07-01 | 2026-07-14 | 2026-06-13 | 2026-06-25 | 34550.61 | 3
CO-R10.S03-ES-SL-180 | Installation Works for Panel Board Concrete Foundations of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2026-07-01 | 2026-07-14 | 2026-06-13 | 2026-06-25 | 48506.22 | 0
CO-R10.S03-ES-SL-190 | Installation Works for Lighting Panel Boards of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2026-07-05 | 2026-07-18 | 2026-06-16 | 2026-06-29 | 177856.16 | 0
Telecom Network |  | 28 | 2026-03-17 | 2026-04-21 | 2026-01-27 | 2026-02-28 | 80544.72 | 70
Ducts Works |  | 28 | 2026-03-17 | 2026-04-21 | 2026-01-27 | 2026-02-28 | 66430.5 | 50
CO-R10.S03-ES-TE-100 | Trench Excavation and Bedding Works for Ducts of Telecom Network-[Road 10]-[SW-3] | 7 | 2026-03-17 | 2026-03-28 | 2026-01-27 | 2026-02-03 | 6700 | 23
CO-R10.S03-ES-TE-110 | Pipes Laying Works for Ducts of Telecom Network-[Road 10]-[SW-3] | 7 | 2026-03-29 | 2026-04-05 | 2026-02-04 | 2026-02-11 | 39764.5 | 50
CO-R10.S03-ES-TE-120 | Pouring Plain Concrete Above Ducts of Telecom Network-[Road 10]-[SW-3] | 7 | 2026-04-06 | 2026-04-13 | 2026-02-12 | 2026-02-19 | 6700 | 50
CO-R10.S03-ES-TE-130 | Trench Backfilling and Compaction Works for Ducts of Telecom Network-[Road 10]-[SW-3] | 7 | 2026-04-14 | 2026-04-21 | 2026-02-21 | 2026-02-28 | 13266 | 50
Manholes Works |  | 21 | 2026-03-29 | 2026-04-21 | 2026-02-04 | 2026-02-28 | 14114.22 | 70
CO-R10.S03-ES-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 10]-[SW-3] | 7 | 2026-03-29 | 2026-04-05 | 2026-02-04 | 2026-02-11 | 2199.61 | 68
CO-R10.S03-ES-TE-150 | Installation Works for Manholes of Telecom Network-[Road 10]-[SW-3] | 7 | 2026-04-06 | 2026-04-13 | 2026-02-12 | 2026-02-19 | 9715 | 70
CO-R10.S03-ES-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 10]-[SW-3] | 7 | 2026-04-14 | 2026-04-21 | 2026-02-21 | 2026-02-28 | 2199.61 | 70
Medium Voltage Network |  | 70 | 2026-04-18 | 2026-07-12 | 2026-02-24 | 2026-05-19 | 281579.54 | 50
Cabling Works |  | 24 | 2026-04-18 | 2026-05-14 | 2026-02-24 | 2026-03-26 | 201322.52 | 50
CO-R10.S03-ES-MV-100 | Trench Excavation and Bedding Works for Medium Voltage Network-[Road 10]-[SW-3] | 18 | 2026-04-18 | 2026-05-07 | 2026-02-24 | 2026-03-16 | 23183.87 | 50
CO-R10.S03-ES-MV-110 | Cable Laying Works for Medium Voltage Network-[Road 10]-[SW-3] | 18 | 2026-04-21 | 2026-05-11 | 2026-02-28 | 2026-03-19 | 124697.05 | 50
CO-R10.S03-ES-MV-120 | Trench Backfilling and Compaction Works for Medium Voltage Network-[Road 10]-[SW-3] | 18 | 2026-04-25 | 2026-05-14 | 2026-03-03 | 2026-03-26 | 53441.59 | 50
RMU Works |  | 46 | 2026-05-16 | 2026-07-12 | 2026-03-28 | 2026-05-19 | 80257.02 | 50
CO-R10.S03-ES-MV-130 | Foundation Excavation Works for RMU of Medium Voltage Network-[Road 10]-[SW-3] | 12 | 2026-05-16 | 2026-06-02 | 2026-03-28 | 2026-04-09 | 8025.7 | 50
CO-R10.S03-ES-MV-150 | Installation Works for RMU Concrete Foundations of Medium Voltage Network-[Road 10]-[SW-3] | 18 | 2026-06-03 | 2026-06-23 | 2026-04-11 | 2026-04-30 | 20064.26 | 50
CO-R10.S03-ES-MV-170 | Installation Works for RMU of Medium Voltage Network-[Road 10]-[SW-3] | 6 | 2026-06-24 | 2026-06-30 | 2026-05-02 | 2026-05-07 | 36115.66 | 50
CO-R10.S03-ES-MV-180 | Termination Works for RMU of Medium Voltage Network-[Road 10]-[SW-3] | 5 | 2026-07-01 | 2026-07-06 | 2026-05-09 | 2026-05-13 | 8025.7 | 50
CO-R10.S03-ES-MV-190 | Testing Works for RMU of Medium Voltage Network-[Road 10]-[SW-3] | 5 | 2026-07-07 | 2026-07-12 | 2026-05-14 | 2026-05-19 | 8025.7 | 50
Road Works |  | 144 | 2026-04-28 | 2026-10-18 | 2026-03-07 | 2026-09-29 | 703651.89 | -16
Pre-Bituminous Construction |  | 21 | 2026-04-28 | 2026-05-21 | 2026-03-07 | 2026-04-02 | 446397.22 | 71
CO-R10.S03-ES-RD-100 | Capping and Subgrade Layer for Road Works-[Road 10]-[SW-3] | 18 | 2026-04-28 | 2026-05-18 | 2026-03-07 | 2026-03-30 | 263120.65 | 65
CO-R10.S03-ES-RD-110 | Aggregate Base Course Layer for Road Works-[Road 10]-[SW-3] | 18 | 2026-05-02 | 2026-05-21 | 2026-03-10 | 2026-04-02 | 183276.57 | 71
Pavement Works |  | 138 | 2026-05-05 | 2026-10-18 | 2026-03-14 | 2026-09-29 | 257254.67 | -16
CO-R10.S03-ES-RD-120 | Fixing of Curbstone for Sidewalks Pavement-[Road 10]-[SW-3] | 18 | 2026-05-05 | 2026-05-25 | 2026-03-14 | 2026-04-06 | 150070.62 | 71
CO-R10.S03-ES-RD-130 | Fixing of Interlock Tiles for Sidewalks Pavement-[Road 10]-[SW-3] | 10 | 2026-10-07 | 2026-10-18 | 2026-09-17 | 2026-09-29 | 107184.05 | -16
SW_3-West |  | 263 | 2025-12-07 | 2026-10-18 | 2025-11-18 | 2026-09-29 | 3064882.71 | -16
Storm Drainage Network |  | 54 | 2025-12-07 | 2026-02-07 | 2025-11-18 | 2026-01-19 | 563172.64 | 5
Main Line Sections |  | 35 | 2025-12-07 | 2026-01-15 | 2025-11-18 | 2025-12-28 | 203079.37 | 0
CO-R10.S03-WE-SD-100 | Trench Excavation and Bedding Works for Main Lines of Storm Drainage Network-[Road 10]-[SW-3] | 10 | 2025-12-07 | 2025-12-17 | 2025-11-18 | 2025-11-29 | 45128.75 | -16
CO-R10.S03-WE-SD-120 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 10]-[SW-3] | 10 | 2025-12-18 | 2025-12-29 | 2025-11-30 | 2025-12-10 | 135386.25 | -16
CO-R10.S03-WE-SD-130 | Trench Backfilling and Compaction Works for Main Lines of Storm Drainage Network-[Road 10]-[SW-3] | 15 | 2025-12-30 | 2026-01-15 | 2025-12-11 | 2025-12-28 | 22564.37 | 0
Manholes |  | 14 | 2025-12-18 | 2026-01-03 | 2025-11-30 | 2025-12-15 | 235003.76 | 5
CO-R10.S03-WE-SD-180 | Trench Excavation and Bedding Works for Manholes of Storm Drainage Network-[Road 10]-[SW-3] | 1 | 2025-12-18 | 2025-12-18 | 2025-11-30 | 2025-11-30 | 37105.86 | 5
CO-R10.S03-WE-SD-190 | Install RC Footing Works for Manholes of Storm Drainage Network-[Road 10]-[SW-3] | 1 | 2025-12-20 | 2025-12-20 | 2025-12-01 | 2025-12-01 | 12368.62 | 5
CO-R10.S03-WE-SD-200 | Install RC Wall Rings & Slab Works for Manholes of Storm Drainage Network-[Road 10]-[SW-3] | 4 | 2025-12-21 | 2025-12-24 | 2025-12-02 | 2025-12-06 | 111317.57 | 5
CO-R10.S03-WE-SD-210 | Testing Works for Manholes of Storm Drainage Network-[Road 10]-[SW-3] | 1 | 2025-12-25 | 2025-12-25 | 2025-12-07 | 2025-12-07 | 24737.24 | 5
CO-R10.S03-WE-SD-220 | Backfilling Works for Manholes of Storm Drainage Network-[Road 10]-[SW-3] | 7 | 2025-12-27 | 2026-01-03 | 2025-12-08 | 2025-12-15 | 49474.48 | 5
Catch Basin Sections |  | 30 | 2026-01-04 | 2026-02-07 | 2025-12-16 | 2026-01-19 | 125089.51 | 5
CO-R10.S03-WE-SD-140 | Trench Excavation and Bedding Works for Catch Basins of Storm Drainage Network-[Road 10]-[SW-3] | 6 | 2026-01-04 | 2026-01-10 | 2025-12-16 | 2025-12-22 | 20848.43 | 5
CO-R10.S03-WE-SD-150 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 10]-[SW-3] | 7 | 2026-01-11 | 2026-01-18 | 2025-12-23 | 2025-12-30 | 62544.75 | 5
CO-R10.S03-WE-SD-160 | Testing Works for Catch Basins of Storm Drainage Network-[Road 10]-[SW-3] | 10 | 2026-01-19 | 2026-01-29 | 2025-12-31 | 2026-01-11 | 13898.77 | 5
CO-R10.S03-WE-SD-170 | Trench Backfilling and Compaction Works for Catch Basins of Storm Drainage Network-[Road 10]-[SW-3] | 7 | 2026-01-31 | 2026-02-07 | 2026-01-12 | 2026-01-19 | 27797.55 | 5
Potable Water Network |  | 24 | 2026-01-17 | 2026-02-12 | 2025-12-29 | 2026-01-25 | 308941.53 | 0
Main Line Sections |  | 24 | 2026-01-17 | 2026-02-12 | 2025-12-29 | 2026-01-25 | 166921.39 | 0
CO-R10.S03-WE-PW-100 | Trench Excavation and Bedding Works for Main Lines of Potable Water Network-[Road 10]-[SW-3] | 6 | 2026-01-17 | 2026-01-22 | 2025-12-29 | 2026-01-04 | 37093.64 | 0
CO-R10.S03-WE-PW-110 | Pipes Laying and accessories for Main Lines of Potable Water Network-[Road 10]-[SW-3] | 6 | 2026-01-24 | 2026-01-29 | 2026-01-05 | 2026-01-11 | 92734.1 | 0
CO-R10.S03-WE-PW-130 | Trench Backfilling and Compaction Works for Main Lines of Potable Water Network-[Road 10]-[SW-3] | 6 | 2026-02-07 | 2026-02-12 | 2026-01-19 | 2026-01-25 | 37093.64 | 0
Valve Chamber |  | 16 | 2026-01-24 | 2026-02-10 | 2026-01-05 | 2026-01-22 | 85212.52 | 2
CO-R10.S03-WE-PW-170 | Excavation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-3] | 1 | 2026-01-24 | 2026-01-24 | 2026-01-05 | 2026-01-05 | 4352.45 | 2
CO-R10.S03-WE-PW-180 | RC Footing Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-3] | 3 | 2026-01-25 | 2026-01-27 | 2026-01-06 | 2026-01-08 | 6528.67 | 2
CO-R10.S03-WE-PW-190 | RC Wall Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-3] | 6 | 2026-01-28 | 2026-02-03 | 2026-01-10 | 2026-01-15 | 15233.56 | 2
CO-R10.S03-WE-PW-200 | RC Slab Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-3] | 2 | 2026-02-04 | 2026-02-05 | 2026-01-17 | 2026-01-18 | 8704.89 | 2
CO-R10.S03-WE-PW-210 | Insulation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-3] | 1 | 2026-02-07 | 2026-02-07 | 2026-01-19 | 2026-01-19 | 41688.07 | 2
CO-R10.S03-WE-PW-220 | Backfilling Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-3] | 3 | 2026-02-08 | 2026-02-10 | 2026-01-20 | 2026-01-22 | 8704.89 | 2
Fire Hydrant |  | 15 | 2026-01-27 | 2026-02-12 | 2026-01-08 | 2026-01-25 | 56807.63 | 0
CO-R10.S03-WE-PW-140 | Excavation Works for Fire Hydrants of Potable Water Network-[Road 10]-[SW-3] | 6 | 2026-01-27 | 2026-02-02 | 2026-01-08 | 2026-01-14 | 8521.14 | 0
CO-R10.S03-WE-PW-150 | Installation Works for Fire Hydrant of Potable Water Network-[Road 10]-[SW-3] | 6 | 2026-02-03 | 2026-02-09 | 2026-01-15 | 2026-01-21 | 36924.96 | 0
CO-R10.S03-WE-PW-160 | Trench Backfilling and Compaction Works for Fire Hydrants of Potable Water Network-[Road 10]-[SW-3] | 6 | 2026-02-07 | 2026-02-12 | 2026-01-19 | 2026-01-25 | 11361.53 | 0
Irrigation Network |  | 23 | 2026-02-14 | 2026-03-11 | 2026-01-26 | 2026-02-21 | 954606.49 | 0
Main Line Pipes |  | 23 | 2026-02-14 | 2026-03-11 | 2026-01-26 | 2026-02-21 | 954606.49 | 0
CO-R10.S03-WE-IR-100 | Trench Excavation and Bedding Works for Main Lines of Irrigation Network-[Road 10]-[SW-3] | 7 | 2026-02-14 | 2026-02-21 | 2026-01-26 | 2026-02-02 | 236979 | 0
CO-R10.S03-WE-IR-110 | Pipes Laying Works for Main Lines of Irrigation Network-[Road 10]-[SW-3] | 7 | 2026-02-22 | 2026-03-01 | 2026-02-03 | 2026-02-10 | 238185 | 0
CO-R10.S03-WE-IR-120 | Installation Works for Main Line Valves of Irrigation Network-[Road 10]-[SW-3] | 2 | 2026-03-02 | 2026-03-03 | 2026-02-11 | 2026-02-12 | 439744.99 | 0
CO-R10.S03-WE-IR-130 | Trench Backfilling and Compaction Works for Main Lines of Irrigation Network-[Road 10]-[SW-3] | 7 | 2026-03-04 | 2026-03-11 | 2026-02-14 | 2026-02-21 | 39697.5 | 0
Street Lighting Network |  | 103 | 2026-03-12 | 2026-07-18 | 2026-02-22 | 2026-06-29 | 172385.9 | 0
Lighting Poles Works |  | 33 | 2026-03-12 | 2026-04-22 | 2026-02-22 | 2026-04-04 | 68790.24 | 25
CO-R10.S03-WE-SL-100 | Foundation Excavation Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2026-03-12 | 2026-03-29 | 2026-02-22 | 2026-03-07 | 2284.16 | 0
CO-R10.S03-WE-SL-110 | Installation Works for Lighting Poles Foundation of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2026-03-18 | 2026-04-04 | 2026-02-28 | 2026-03-12 | 8731.44 | 0
CO-R10.S03-WE-SL-120 | Installation Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-3] | 18 | 2026-03-28 | 2026-04-16 | 2026-03-05 | 2026-03-29 | 25125.8 | 0
CO-R10.S03-WE-SL-130 | Installation Works for Lighting Fixtures With Drop Wire of Street Lighting Network-[Road 10]-[SW-3] | 18 | 2026-04-02 | 2026-04-22 | 2026-03-11 | 2026-04-04 | 14375.52 | 25
CO-R10.S03-WE-SL-210 | Backfilling Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2026-04-04 | 2026-04-16 | 2026-03-12 | 2026-03-29 | 9136.66 | 25
CO-R10.S03-WE-SL-200 | Testing Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-3] | 5 | 2026-04-18 | 2026-04-22 | 2026-03-30 | 2026-04-04 | 9136.66 | 25
Cabling Works |  | 30 | 2026-04-18 | 2026-05-21 | 2026-03-30 | 2026-05-03 | 47398.36 | 0
CO-R10.S03-WE-SL-140 | Trench Excavation and Bedding Works for Street Lighting Network-[Road 10]-[SW-3] | 10 | 2026-04-18 | 2026-04-28 | 2026-03-30 | 2026-04-09 | 0 | 0
CO-R10.S03-WE-SL-150 | Cable Laying Works for Street Lighting Network-[Road 10]-[SW-3] | 10 | 2026-04-29 | 2026-05-10 | 2026-04-11 | 2026-04-21 | 44012.74 | 0
CO-R10.S03-WE-SL-160 | Trench Backfilling and Compaction Works for Street Lighting Network-[Road 10]-[SW-3] | 10 | 2026-05-11 | 2026-05-21 | 2026-04-22 | 2026-05-03 | 3385.62 | 0
Distrubution Panel Boards |  | 21 | 2026-06-24 | 2026-07-18 | 2026-06-06 | 2026-06-29 | 56197.3 | 0
CO-R10.S03-WE-SL-170 | Foundation Excavation Works For Panel Boards of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2026-06-24 | 2026-07-07 | 2026-06-06 | 2026-06-18 | 21646.7 | 0
CO-R10.S03-WE-SL-180 | Installation Works for Panel Board Concrete Foundations of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2026-07-01 | 2026-07-14 | 2026-06-13 | 2026-06-25 | 0 | 0
CO-R10.S03-WE-SL-220 | A wall of concrete blocks to install the KWH meter of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2026-07-01 | 2026-07-14 | 2026-06-13 | 2026-06-25 | 34550.61 | 3
CO-R10.S03-WE-SL-190 | Installation Works for Lighting Panel Boards of Street Lighting Network-[Road 10]-[SW-3] | 12 | 2026-07-05 | 2026-07-18 | 2026-06-16 | 2026-06-29 | 0 | 0
Telecom Network |  | 24 | 2026-07-06 | 2026-08-02 | 2026-06-17 | 2026-07-14 | 80544.72 | -9
Ducts Works |  | 24 | 2026-07-06 | 2026-08-02 | 2026-06-17 | 2026-07-14 | 66430.5 | -16
CO-R10.S03-WE-TE-100 | Trench Excavation and Bedding Works for Ducts of Telecom Network-[Road 10]-[SW-3] | 3 | 2026-07-06 | 2026-07-08 | 2026-06-17 | 2026-06-20 | 6700 | -16
CO-R10.S03-WE-TE-110 | Pipes Laying Works for Ducts of Telecom Network-[Road 10]-[SW-3] | 7 | 2026-07-09 | 2026-07-16 | 2026-06-21 | 2026-06-28 | 39764.5 | -16
CO-R10.S03-WE-TE-120 | Pouring Plain Concrete Above Ducts of Telecom Network-[Road 10]-[SW-3] | 7 | 2026-07-18 | 2026-07-25 | 2026-06-29 | 2026-07-06 | 6700 | -16
CO-R10.S03-WE-TE-130 | Trench Backfilling and Compaction Works for Ducts of Telecom Network-[Road 10]-[SW-3] | 7 | 2026-07-26 | 2026-08-02 | 2026-07-07 | 2026-07-14 | 13266 | -16
Manholes Works |  | 21 | 2026-07-09 | 2026-08-02 | 2026-06-21 | 2026-07-14 | 14114.22 | -9
CO-R10.S03-WE-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 10]-[SW-3] | 7 | 2026-07-09 | 2026-07-16 | 2026-06-21 | 2026-06-28 | 2199.61 | -16
CO-R10.S03-WE-TE-150 | Installation Works for Manholes of Telecom Network-[Road 10]-[SW-3] | 7 | 2026-07-18 | 2026-07-25 | 2026-06-29 | 2026-07-06 | 9715 | -9
CO-R10.S03-WE-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 10]-[SW-3] | 7 | 2026-07-26 | 2026-08-02 | 2026-07-07 | 2026-07-14 | 2199.61 | -9
Medium Voltage Network |  | 52 | 2026-07-29 | 2026-09-28 | 2026-07-11 | 2026-09-08 | 281579.54 | -16
Cabling Works |  | 16 | 2026-07-29 | 2026-08-16 | 2026-07-11 | 2026-07-28 | 201322.52 | -16
CO-R10.S03-WE-MV-100 | Trench Excavation and Bedding Works for Medium Voltage Network-[Road 10]-[SW-3] | 10 | 2026-07-29 | 2026-08-09 | 2026-07-11 | 2026-07-21 | 23183.87 | -16
CO-R10.S03-WE-MV-110 | Cable Laying Works for Medium Voltage Network-[Road 10]-[SW-3] | 10 | 2026-08-02 | 2026-08-12 | 2026-07-14 | 2026-07-25 | 124697.05 | -16
CO-R10.S03-WE-MV-120 | Trench Backfilling and Compaction Works for Medium Voltage Network-[Road 10]-[SW-3] | 10 | 2026-08-05 | 2026-08-16 | 2026-07-18 | 2026-07-28 | 53441.59 | -16
RMU Works |  | 36 | 2026-08-17 | 2026-09-28 | 2026-07-29 | 2026-09-08 | 80257.02 | -16
CO-R10.S03-WE-MV-130 | Foundation Excavation Works for RMU of Medium Voltage Network-[Road 10]-[SW-3] | 10 | 2026-08-17 | 2026-08-27 | 2026-07-29 | 2026-08-09 | 8025.7 | -16
CO-R10.S03-WE-MV-150 | Installation Works for RMU Concrete Foundations of Medium Voltage Network-[Road 10]-[SW-3] | 10 | 2026-08-29 | 2026-09-08 | 2026-08-10 | 2026-08-20 | 20064.26 | -16
CO-R10.S03-WE-MV-170 | Installation Works for RMU of Medium Voltage Network-[Road 10]-[SW-3] | 6 | 2026-09-09 | 2026-09-15 | 2026-08-22 | 2026-08-27 | 36115.66 | -16
CO-R10.S03-WE-MV-180 | Termination Works for RMU of Medium Voltage Network-[Road 10]-[SW-3] | 5 | 2026-09-16 | 2026-09-21 | 2026-08-29 | 2026-09-02 | 8025.7 | -16
CO-R10.S03-WE-MV-190 | Testing Works for RMU of Medium Voltage Network-[Road 10]-[SW-3] | 5 | 2026-09-22 | 2026-09-28 | 2026-09-03 | 2026-09-08 | 8025.7 | -16
Road Works |  | 60 | 2026-08-09 | 2026-10-18 | 2026-07-21 | 2026-09-29 | 703651.89 | -16
Pre-Bituminous Construction |  | 21 | 2026-08-09 | 2026-09-01 | 2026-07-21 | 2026-08-13 | 446397.22 | -13
CO-R10.S03-WE-RD-100 | Capping and Subgrade Layer for Road Works-[Road 10]-[SW-3] | 12 | 2026-08-09 | 2026-08-22 | 2026-07-21 | 2026-08-03 | 263120.65 | -13
CO-R10.S03-WE-RD-110 | Aggregate Base Course Layer for Road Works-[Road 10]-[SW-3] | 18 | 2026-08-12 | 2026-09-01 | 2026-07-25 | 2026-08-13 | 183276.57 | -13
Pavement Works |  | 54 | 2026-08-16 | 2026-10-18 | 2026-07-28 | 2026-09-29 | 257254.67 | -16
CO-R10.S03-WE-RD-120 | Fixing of Curbstone for Sidewalks Pavement-[Road 10]-[SW-3] | 18 | 2026-08-16 | 2026-09-05 | 2026-07-28 | 2026-08-17 | 150070.62 | -13
CO-R10.S03-WE-RD-130 | Fixing of Interlock Tiles for Sidewalks Pavement-[Road 10]-[SW-3] | 10 | 2026-10-07 | 2026-10-18 | 2026-09-17 | 2026-09-29 | 107184.05 | -16
SW-4 |  | 438 | 2025-05-13 | 2026-10-20 | 2025-06-28 | 2026-10-01 | 8327464.41 | -16
SW_4-East |  | 436 | 2025-05-13 | 2026-10-18 | 2025-06-28 | 2026-09-29 | 4169521.77 | -14
Sewage Network |  | 76 | 2025-05-13 | 2025-08-13 | 2025-06-28 | 2025-08-05 | 679036.18 | 18
Main Line Sections |  | 76 | 2025-05-13 | 2025-08-13 | 2025-06-28 | 2025-08-05 | 520397.13 | 18
CO-R10.S04-ES-SW-100 | Trench Excavation and Bedding Works for Main Lines of Sewage Network-[Road 10]-[SW-4] | 10 | 2025-05-13 | 2025-05-24 | 2025-06-28 | 2025-07-08 | 115643.81 | 52
CO-R10.S04-ES-SW-120 | Pipes Laying Works for Main Lines of Sewage Network-[Road 10]-[SW-4] | 12 | 2025-07-15 | 2025-07-28 | 2025-07-09 | 2025-07-22 | 346931.42 | 20
CO-R10.S04-ES-SW-130 | Trench Backfilling and Compaction Works for Main Lines of Sewage Network-[Road 10]-[SW-4] | 12 | 2025-07-31 | 2025-08-13 | 2025-07-23 | 2025-08-05 | 57821.9 | 18
Manholes |  | 26 | 2025-07-15 | 2025-08-13 | 2025-07-09 | 2025-07-23 | 158639.05 | 18
CO-R10.S04-ES-SW-160 | Excavation Works for Main Line Manholes of Sewage Network-[Road 10]-[SW-4] | 1 | 2025-07-15 | 2025-07-15 | 2025-07-09 | 2025-07-09 | 26439.84 | 31
CO-R10.S04-ES-SW-170 | Installation RC Footing Works for Main Line Manholes of Sewage Network-[Road 10]-[SW-4] | 2 | 2025-07-31 | 2025-08-02 | 2025-07-10 | 2025-07-12 | 17626.56 | 18
CO-R10.S04-ES-SW-180 | Install Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 10]-[SW-4] | 4 | 2025-08-03 | 2025-08-06 | 2025-07-13 | 2025-07-16 | 70506.24 | 18
CO-R10.S04-ES-SW-190 | Pouring Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 10]-[SW-4] | 1 | 2025-08-07 | 2025-08-07 | 2025-07-17 | 2025-07-17 | 8813.28 | 18
CO-R10.S04-ES-SW-200 | Backfilling Works for Main Line Manholes of Sewage Network-[Road 10]-[SW-4] | 4 | 2025-08-09 | 2025-08-12 | 2025-07-19 | 2025-07-22 | 26439.84 | 18
CO-R10.S04-ES-SW-210 | Testing Works for Main Line Manholes of Sewage Network-[Road 10]-[SW-4] | 1 | 2025-08-13 | 2025-08-13 | 2025-07-23 | 2025-07-23 | 8813.28 | 18
Storm Drainage Network |  | 130 | 2025-09-15 | 2026-02-14 | 2025-08-27 | 2026-01-26 | 809956.18 | -2
Main Line Sections |  | 110 | 2025-09-15 | 2026-01-21 | 2025-08-27 | 2026-01-03 | 491521.84 | -16
CO-R10.S04-ES-SD-100 | Trench Excavation and Bedding Works for Main Lines of Storm Drainage Network-[Road 10]-[SW-4] | 10 | 2025-09-15 | 2025-09-27 | 2025-08-27 | 2025-09-07 | 109227.08 | -16
CO-R10.S04-ES-SD-120 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 10]-[SW-4] | 10 | 2025-12-30 | 2026-01-10 | 2025-12-11 | 2025-12-22 | 327681.23 | -16
CO-R10.S04-ES-SD-130 | Trench Backfilling and Compaction Works for Main Lines of Storm Drainage Network-[Road 10]-[SW-4] | 10 | 2026-01-11 | 2026-01-21 | 2025-12-23 | 2026-01-03 | 54613.54 | -16
Manholes |  | 14 | 2025-12-30 | 2026-01-14 | 2025-12-11 | 2025-12-27 | 193344.83 | -10
CO-R10.S04-ES-SD-180 | Trench Excavation and Bedding Works for Manholes of Storm Drainage Network-[Road 10]-[SW-4] | 1 | 2025-12-30 | 2025-12-30 | 2025-12-11 | 2025-12-11 | 30528.13 | -10
CO-R10.S04-ES-SD-190 | Install RC Footing Works for Manholes of Storm Drainage Network-[Road 10]-[SW-4] | 1 | 2025-12-31 | 2025-12-31 | 2025-12-13 | 2025-12-13 | 10176.04 | -10
CO-R10.S04-ES-SD-200 | Install RC Wall Rings & Slab Works for Manholes of Storm Drainage Network-[Road 10]-[SW-4] | 4 | 2026-01-01 | 2026-01-05 | 2025-12-14 | 2025-12-17 | 91584.39 | -10
CO-R10.S04-ES-SD-210 | Testing Works for Manholes of Storm Drainage Network-[Road 10]-[SW-4] | 1 | 2026-01-06 | 2026-01-06 | 2025-12-18 | 2025-12-18 | 20352.09 | -10
CO-R10.S04-ES-SD-220 | Backfilling Works for Manholes of Storm Drainage Network-[Road 10]-[SW-4] | 7 | 2026-01-07 | 2026-01-14 | 2025-12-20 | 2025-12-27 | 40704.18 | -10
Catch Basin Sections |  | 26 | 2026-01-15 | 2026-02-14 | 2025-12-28 | 2026-01-26 | 125089.51 | -2
CO-R10.S04-ES-SD-140 | Trench Excavation and Bedding Works for Catch Basins of Storm Drainage Network-[Road 10]-[SW-4] | 6 | 2026-01-15 | 2026-01-21 | 2025-12-28 | 2026-01-03 | 20848.43 | -2
CO-R10.S04-ES-SD-150 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 10]-[SW-4] | 7 | 2026-01-22 | 2026-01-29 | 2026-01-04 | 2026-01-11 | 62544.75 | -2
CO-R10.S04-ES-SD-160 | Testing Works for Catch Basins of Storm Drainage Network-[Road 10]-[SW-4] | 10 | 2026-01-31 | 2026-02-10 | 2026-01-12 | 2026-01-22 | 13898.77 | -2
CO-R10.S04-ES-SD-170 | Trench Backfilling and Compaction Works for Catch Basins of Storm Drainage Network-[Road 10]-[SW-4] | 7 | 2026-02-07 | 2026-02-14 | 2026-01-19 | 2026-01-26 | 27797.55 | -2
Potable Water Network |  | 34 | 2026-01-22 | 2026-03-02 | 2026-01-04 | 2026-02-11 | 1634497.17 | -16
Main Line Sections |  | 34 | 2026-01-22 | 2026-03-02 | 2026-01-04 | 2026-02-11 | 1182832.74 | -16
CO-R10.S04-ES-PW-100 | Trench Excavation and Bedding Works for Main Lines of Potable Water Network-[Road 10]-[SW-4] | 10 | 2026-01-22 | 2026-02-02 | 2026-01-04 | 2026-01-14 | 262851.72 | -16
CO-R10.S04-ES-PW-110 | Pipes Laying and accessories for Main Lines of Potable Water Network-[Road 10]-[SW-4] | 10 | 2026-02-03 | 2026-02-14 | 2026-01-15 | 2026-01-26 | 657129.3 | -16
CO-R10.S04-ES-PW-130 | Trench Backfilling and Compaction Works for Main Lines of Potable Water Network-[Road 10]-[SW-4] | 7 | 2026-02-23 | 2026-03-02 | 2026-02-04 | 2026-02-11 | 262851.72 | -16
Valve Chamber |  | 16 | 2026-02-03 | 2026-02-21 | 2026-01-15 | 2026-02-02 | 451664.43 | -8
CO-R10.S04-ES-PW-170 | Excavation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-4] | 1 | 2026-02-03 | 2026-02-03 | 2026-01-15 | 2026-01-15 | 16109.01 | -14
CO-R10.S04-ES-PW-180 | RC Footing Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-4] | 3 | 2026-02-04 | 2026-02-07 | 2026-01-17 | 2026-01-19 | 19376.15 | -8
CO-R10.S04-ES-PW-190 | RC Wall Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-4] | 6 | 2026-02-08 | 2026-02-14 | 2026-01-20 | 2026-01-26 | 45211.01 | -8
CO-R10.S04-ES-PW-200 | RC Slab Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-4] | 2 | 2026-02-15 | 2026-02-16 | 2026-01-27 | 2026-01-28 | 25834.86 | -8
CO-R10.S04-ES-PW-210 | Insulation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-4] | 1 | 2026-02-17 | 2026-02-17 | 2026-01-29 | 2026-01-29 | 319298.55 | -8
CO-R10.S04-ES-PW-220 | Backfilling Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-4] | 3 | 2026-02-18 | 2026-02-21 | 2026-01-31 | 2026-02-02 | 25834.86 | -8
Fire Hydrant |  | 21 | 2026-02-07 | 2026-03-02 | 2026-01-19 | 2026-02-11 | 0 | -16
CO-R10.S04-ES-PW-140 | Excavation Works for Fire Hydrants of Potable Water Network-[Road 10]-[SW-4] | 7 | 2026-02-07 | 2026-02-14 | 2026-01-19 | 2026-01-26 | 0 | -16
CO-R10.S04-ES-PW-150 | Installation Works for Fire Hydrant of Potable Water Network-[Road 10]-[SW-4] | 7 | 2026-02-15 | 2026-02-22 | 2026-01-27 | 2026-02-03 | 0 | -16
CO-R10.S04-ES-PW-160 | Trench Backfilling and Compaction Works for Fire Hydrants of Potable Water Network-[Road 10]-[SW-4] | 7 | 2026-02-23 | 2026-03-02 | 2026-02-04 | 2026-02-11 | 0 | -16
Irrigation Network |  | 22 | 2026-03-03 | 2026-03-31 | 2026-02-12 | 2026-03-09 | 126219.66 | -16
Main Line Pipes |  | 22 | 2026-03-03 | 2026-03-31 | 2026-02-12 | 2026-03-09 | 126219.66 | -16
CO-R10.S04-ES-IR-100 | Trench Excavation and Bedding Works for Main Lines of Irrigation Network-[Road 10]-[SW-4] | 6 | 2026-03-03 | 2026-03-09 | 2026-02-12 | 2026-02-18 | 21367.62 | -16
CO-R10.S04-ES-IR-110 | Pipes Laying Works for Main Lines of Irrigation Network-[Road 10]-[SW-4] | 7 | 2026-03-10 | 2026-03-17 | 2026-02-19 | 2026-02-26 | 64102.85 | -16
CO-R10.S04-ES-IR-120 | Installation Works for Main Line Valves of Irrigation Network-[Road 10]-[SW-4] | 4 | 2026-03-18 | 2026-03-25 | 2026-02-28 | 2026-03-03 | 30065.35 | -16
CO-R10.S04-ES-IR-130 | Trench Backfilling and Compaction Works for Main Lines of Irrigation Network-[Road 10]-[SW-4] | 5 | 2026-03-26 | 2026-03-31 | 2026-03-04 | 2026-03-09 | 10683.85 | -16
Street Lighting Network |  | 77 | 2026-04-01 | 2026-07-04 | 2026-03-10 | 2026-06-15 | 135615.97 | 53
Lighting Poles Works |  | 33 | 2026-04-01 | 2026-05-09 | 2026-03-10 | 2026-04-20 | 68790.24 | 97
CO-R10.S04-ES-SL-100 | Foundation Excavation Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-4] | 7 | 2026-04-01 | 2026-04-08 | 2026-03-10 | 2026-03-17 | 2284.16 | -16
CO-R10.S04-ES-SL-110 | Installation Works for Lighting Poles Foundation of Street Lighting Network-[Road 10]-[SW-4] | 7 | 2026-04-07 | 2026-04-14 | 2026-03-16 | 2026-03-26 | 8731.44 | -16
CO-R10.S04-ES-SL-210 | Backfilling Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-4] | 15 | 2026-04-13 | 2026-04-29 | 2026-03-25 | 2026-04-11 | 9136.66 | -8
CO-R10.S04-ES-SL-120 | Installation Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-4] | 7 | 2026-04-13 | 2026-04-20 | 2026-03-25 | 2026-04-01 | 25125.8 | -16
CO-R10.S04-ES-SL-130 | Installation Works for Lighting Fixtures With Drop Wire of Street Lighting Network-[Road 10]-[SW-4] | 18 | 2026-04-19 | 2026-05-09 | 2026-03-31 | 2026-04-20 | 14375.52 | 97
CO-R10.S04-ES-SL-200 | Testing Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-4] | 7 | 2026-04-30 | 2026-05-07 | 2026-04-12 | 2026-04-19 | 9136.66 | 98
Cabling Works |  | 21 | 2026-04-21 | 2026-05-14 | 2026-04-02 | 2026-04-26 | 47398.36 | -16
CO-R10.S04-ES-SL-140 | Trench Excavation and Bedding Works for Street Lighting Network-[Road 10]-[SW-4] | 7 | 2026-04-21 | 2026-04-28 | 2026-04-02 | 2026-04-09 | 0 | -16
CO-R10.S04-ES-SL-150 | Cable Laying Works for Street Lighting Network-[Road 10]-[SW-4] | 7 | 2026-04-29 | 2026-05-06 | 2026-04-11 | 2026-04-18 | 44012.74 | -16
CO-R10.S04-ES-SL-160 | Trench Backfilling and Compaction Works for Street Lighting Network-[Road 10]-[SW-4] | 7 | 2026-05-07 | 2026-05-14 | 2026-04-19 | 2026-04-26 | 3385.62 | -16
Distrubution Panel Boards |  | 39 | 2026-05-16 | 2026-07-04 | 2026-04-27 | 2026-06-15 | 19427.37 | 12
CO-R10.S04-ES-SL-170 | Foundation Excavation Works For Panel Boards of Street Lighting Network-[Road 10]-[SW-4] | 18 | 2026-05-16 | 2026-06-09 | 2026-04-27 | 2026-05-17 | 0 | 3
CO-R10.S04-ES-SL-180 | Installation Works for Panel Board Concrete Foundations of Street Lighting Network-[Road 10]-[SW-4] | 12 | 2026-05-31 | 2026-06-13 | 2026-05-07 | 2026-05-20 | 0 | 12
CO-R10.S04-ES-SL-190 | Installation Works for Lighting Panel Boards of Street Lighting Network-[Road 10]-[SW-4] | 12 | 2026-06-14 | 2026-06-27 | 2026-05-21 | 2026-06-08 | 0 | 12
CO-R10.S04-ES-SL-220 | A wall of concrete blocks to install the KWH meter of Street Lighting Network-[Road 10]-[SW-4] | 18 | 2026-06-14 | 2026-07-04 | 2026-05-21 | 2026-06-15 | 19427.37 | 12
Telecom Network |  | 73 | 2026-05-13 | 2026-08-10 | 2026-04-25 | 2026-07-22 | 80544.72 | -16
Ducts Works |  | 28 | 2026-05-13 | 2026-06-18 | 2026-04-25 | 2026-05-31 | 66430.5 | 29
CO-R10.S04-ES-TE-100 | Trench Excavation and Bedding Works for Ducts of Telecom Network-[Road 10]-[SW-4] | 7 | 2026-05-13 | 2026-05-20 | 2026-04-25 | 2026-05-02 | 6700 | -16
CO-R10.S04-ES-TE-110 | Pipes Laying Works for Ducts of Telecom Network-[Road 10]-[SW-4] | 7 | 2026-05-21 | 2026-06-02 | 2026-05-03 | 2026-05-10 | 39764.5 | 29
CO-R10.S04-ES-TE-120 | Pouring Plain Concrete Above Ducts of Telecom Network-[Road 10]-[SW-4] | 7 | 2026-06-03 | 2026-06-10 | 2026-05-11 | 2026-05-18 | 6700 | 29
CO-R10.S04-ES-TE-130 | Trench Backfilling and Compaction Works for Ducts of Telecom Network-[Road 10]-[SW-4] | 7 | 2026-06-11 | 2026-06-18 | 2026-05-19 | 2026-05-31 | 13266 | 29
Manholes Works |  | 21 | 2026-07-18 | 2026-08-10 | 2026-06-29 | 2026-07-22 | 14114.22 | -16
CO-R10.S04-ES-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 10]-[SW-4] | 7 | 2026-07-18 | 2026-07-25 | 2026-06-29 | 2026-07-06 | 2199.61 | -16
CO-R10.S04-ES-TE-150 | Installation Works for Manholes of Telecom Network-[Road 10]-[SW-4] | 7 | 2026-07-26 | 2026-08-02 | 2026-07-07 | 2026-07-14 | 9715 | -16
CO-R10.S04-ES-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 10]-[SW-4] | 7 | 2026-08-03 | 2026-08-10 | 2026-07-15 | 2026-07-22 | 2199.61 | -16
Road Works |  | 58 | 2026-08-11 | 2026-10-18 | 2026-07-23 | 2026-09-29 | 703651.89 | -14
Pre-Bituminous Construction |  | 17 | 2026-08-11 | 2026-08-30 | 2026-07-23 | 2026-08-11 | 446397.22 | -11
CO-R10.S04-ES-RD-100 | Capping and Subgrade Layer for Road Works-[Road 10]-[SW-4] | 14 | 2026-08-11 | 2026-08-26 | 2026-07-23 | 2026-08-08 | 263120.65 | -16
CO-R10.S04-ES-RD-110 | Aggregate Base Course Layer for Road Works-[Road 10]-[SW-4] | 12 | 2026-08-17 | 2026-08-30 | 2026-07-29 | 2026-08-11 | 183276.57 | -11
Pavement Works |  | 50 | 2026-08-20 | 2026-10-18 | 2026-08-02 | 2026-09-29 | 257254.67 | -14
CO-R10.S04-ES-RD-120 | Fixing of Curbstone for Sidewalks Pavement-[Road 10]-[SW-4] | 12 | 2026-08-20 | 2026-09-02 | 2026-08-02 | 2026-08-15 | 150070.62 | -11
CO-R10.S04-ES-RD-130 | Fixing of Interlock Tiles for Sidewalks Pavement-[Road 10]-[SW-4] | 10 | 2026-10-07 | 2026-10-18 | 2026-09-17 | 2026-09-29 | 107184.05 | -14
SW_4-West |  | 351 | 2025-08-27 | 2026-10-20 | 2025-10-14 | 2026-10-01 | 4157942.64 | -16
Sewage Network |  | 36 | 2025-08-27 | 2025-10-08 | 2025-10-14 | 2025-11-24 | 705155.12 | 51
Main Line Sections |  | 36 | 2025-08-27 | 2025-10-08 | 2025-10-14 | 2025-11-24 | 520397.13 | 51
CO-R10.S04-WE-SW-100 | Trench Excavation and Bedding Works for Main Lines of Sewage Network-[Road 10]-[SW-4] | 12 | 2025-08-27 | 2025-09-09 | 2025-10-14 | 2025-10-27 | 115643.81 | 51
CO-R10.S04-WE-SW-120 | Pipes Laying Works for Main Lines of Sewage Network-[Road 10]-[SW-4] | 12 | 2025-09-10 | 2025-09-24 | 2025-10-28 | 2025-11-10 | 346931.42 | 51
CO-R10.S04-WE-SW-130 | Trench Backfilling and Compaction Works for Main Lines of Sewage Network-[Road 10]-[SW-4] | 12 | 2025-09-25 | 2025-10-08 | 2025-11-11 | 2025-11-24 | 57821.9 | 51
Manholes |  | 13 | 2025-09-10 | 2025-09-25 | 2025-10-28 | 2025-11-11 | 184757.99 | 62
CO-R10.S04-WE-SW-160 | Excavation Works for Main Line Manholes of Sewage Network-[Road 10]-[SW-4] | 1 | 2025-09-10 | 2025-09-10 | 2025-10-28 | 2025-10-28 | 30793 | 62
CO-R10.S04-WE-SW-170 | Installation RC Footing Works for Main Line Manholes of Sewage Network-[Road 10]-[SW-4] | 2 | 2025-09-11 | 2025-09-13 | 2025-10-29 | 2025-10-30 | 20528.67 | 62
CO-R10.S04-WE-SW-180 | Install Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 10]-[SW-4] | 4 | 2025-09-14 | 2025-09-17 | 2025-11-01 | 2025-11-04 | 82114.66 | 62
CO-R10.S04-WE-SW-190 | Pouring Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 10]-[SW-4] | 1 | 2025-09-18 | 2025-09-18 | 2025-11-05 | 2025-11-05 | 10264.33 | 62
CO-R10.S04-WE-SW-200 | Backfilling Works for Main Line Manholes of Sewage Network-[Road 10]-[SW-4] | 4 | 2025-09-20 | 2025-09-24 | 2025-11-06 | 2025-11-10 | 30793 | 62
CO-R10.S04-WE-SW-210 | Testing Works for Main Line Manholes of Sewage Network-[Road 10]-[SW-4] | 1 | 2025-09-25 | 2025-09-25 | 2025-11-11 | 2025-11-11 | 10264.33 | 62
Storm Drainage Network |  | 50 | 2025-12-18 | 2026-02-14 | 2025-11-30 | 2026-01-26 | 825971.79 | -2
Main Line Sections |  | 30 | 2025-12-18 | 2026-01-21 | 2025-11-30 | 2026-01-03 | 491521.84 | -16
CO-R10.S04-WE-SD-100 | Trench Excavation and Bedding Works for Main Lines of Storm Drainage Network-[Road 10]-[SW-4] | 10 | 2025-12-18 | 2025-12-29 | 2025-11-30 | 2025-12-10 | 109227.08 | -16
CO-R10.S04-WE-SD-120 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 10]-[SW-4] | 10 | 2025-12-30 | 2026-01-10 | 2025-12-11 | 2025-12-22 | 327681.23 | -16
CO-R10.S04-WE-SD-130 | Trench Backfilling and Compaction Works for Main Lines of Storm Drainage Network-[Road 10]-[SW-4] | 10 | 2026-01-11 | 2026-01-21 | 2025-12-23 | 2026-01-03 | 54613.54 | -16
Manholes |  | 14 | 2025-12-30 | 2026-01-14 | 2025-12-11 | 2025-12-27 | 209360.44 | -10
CO-R10.S04-WE-SD-180 | Trench Excavation and Bedding Works for Manholes of Storm Drainage Network-[Road 10]-[SW-4] | 1 | 2025-12-30 | 2025-12-30 | 2025-12-11 | 2025-12-11 | 33056.91 | -10
CO-R10.S04-WE-SD-190 | Install RC Footing Works for Manholes of Storm Drainage Network-[Road 10]-[SW-4] | 1 | 2025-12-31 | 2025-12-31 | 2025-12-13 | 2025-12-13 | 11018.97 | -10
CO-R10.S04-WE-SD-200 | Install RC Wall Rings & Slab Works for Manholes of Storm Drainage Network-[Road 10]-[SW-4] | 4 | 2026-01-01 | 2026-01-05 | 2025-12-14 | 2025-12-17 | 99170.74 | -10
CO-R10.S04-WE-SD-210 | Testing Works for Manholes of Storm Drainage Network-[Road 10]-[SW-4] | 1 | 2026-01-06 | 2026-01-06 | 2025-12-18 | 2025-12-18 | 22037.94 | -10
CO-R10.S04-WE-SD-220 | Backfilling Works for Manholes of Storm Drainage Network-[Road 10]-[SW-4] | 7 | 2026-01-07 | 2026-01-14 | 2025-12-20 | 2025-12-27 | 44075.88 | -10
Catch Basin Sections |  | 26 | 2026-01-15 | 2026-02-14 | 2025-12-28 | 2026-01-26 | 125089.51 | -2
CO-R10.S04-WE-SD-140 | Trench Excavation and Bedding Works for Catch Basins of Storm Drainage Network-[Road 10]-[SW-4] | 6 | 2026-01-15 | 2026-01-21 | 2025-12-28 | 2026-01-03 | 20848.43 | -2
CO-R10.S04-WE-SD-150 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 10]-[SW-4] | 7 | 2026-01-22 | 2026-01-29 | 2026-01-04 | 2026-01-11 | 62544.75 | -2
CO-R10.S04-WE-SD-160 | Testing Works for Catch Basins of Storm Drainage Network-[Road 10]-[SW-4] | 10 | 2026-01-31 | 2026-02-10 | 2026-01-12 | 2026-01-22 | 13898.77 | -2
CO-R10.S04-WE-SD-170 | Trench Backfilling and Compaction Works for Catch Basins of Storm Drainage Network-[Road 10]-[SW-4] | 7 | 2026-02-07 | 2026-02-14 | 2026-01-19 | 2026-01-26 | 27797.55 | -2
Potable Water Network |  | 34 | 2026-01-22 | 2026-03-02 | 2026-01-04 | 2026-02-11 | 1588922.79 | -16
Main Line Sections |  | 34 | 2026-01-22 | 2026-03-02 | 2026-01-04 | 2026-02-11 | 1182832.74 | -16
CO-R10.S04-WE-PW-100 | Trench Excavation and Bedding Works for Main Lines of Potable Water Network-[Road 10]-[SW-4] | 10 | 2026-01-22 | 2026-02-02 | 2026-01-04 | 2026-01-14 | 262851.72 | -16
CO-R10.S04-WE-PW-110 | Pipes Laying and accessories for Main Lines of Potable Water Network-[Road 10]-[SW-4] | 10 | 2026-02-03 | 2026-02-14 | 2026-01-15 | 2026-01-26 | 657129.3 | -16
CO-R10.S04-WE-PW-130 | Trench Backfilling and Compaction Works for Main Lines of Potable Water Network-[Road 10]-[SW-4] | 10 | 2026-02-19 | 2026-03-02 | 2026-02-01 | 2026-02-11 | 262851.72 | -16
Valve Chamber |  | 16 | 2026-02-03 | 2026-02-21 | 2026-01-15 | 2026-02-02 | 406090.05 | -8
CO-R10.S04-WE-PW-170 | Excavation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-4] | 1 | 2026-02-03 | 2026-02-03 | 2026-01-15 | 2026-01-15 | 8679.15 | -14
CO-R10.S04-WE-PW-180 | RC Footing Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-4] | 3 | 2026-02-04 | 2026-02-07 | 2026-01-17 | 2026-01-19 | 13018.73 | -8
CO-R10.S04-WE-PW-190 | RC Wall Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-4] | 6 | 2026-02-08 | 2026-02-14 | 2026-01-20 | 2026-01-26 | 30377.03 | -8
CO-R10.S04-WE-PW-200 | RC Slab Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-4] | 2 | 2026-02-15 | 2026-02-16 | 2026-01-27 | 2026-01-28 | 17358.3 | -8
CO-R10.S04-WE-PW-210 | Insulation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-4] | 1 | 2026-02-17 | 2026-02-17 | 2026-01-29 | 2026-01-29 | 319298.55 | -8
CO-R10.S04-WE-PW-220 | Backfilling Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 10]-[SW-4] | 3 | 2026-02-18 | 2026-02-21 | 2026-01-31 | 2026-02-02 | 17358.3 | -8
Fire Hydrant |  | 21 | 2026-02-07 | 2026-03-02 | 2026-01-19 | 2026-02-11 | 0 | -16
CO-R10.S04-WE-PW-140 | Excavation Works for Fire Hydrants of Potable Water Network-[Road 10]-[SW-4] | 7 | 2026-02-07 | 2026-02-14 | 2026-01-19 | 2026-01-26 | 0 | -16
CO-R10.S04-WE-PW-150 | Installation Works for Fire Hydrant of Potable Water Network-[Road 10]-[SW-4] | 7 | 2026-02-15 | 2026-02-22 | 2026-01-27 | 2026-02-03 | 0 | -16
CO-R10.S04-WE-PW-160 | Trench Backfilling and Compaction Works for Fire Hydrants of Potable Water Network-[Road 10]-[SW-4] | 7 | 2026-02-23 | 2026-03-02 | 2026-02-04 | 2026-02-11 | 0 | -16
Irrigation Network |  | 21 | 2026-03-03 | 2026-03-30 | 2026-02-12 | 2026-03-08 | 118080.36 | -16
Main Line Pipes |  | 21 | 2026-03-03 | 2026-03-30 | 2026-02-12 | 2026-03-08 | 118080.36 | -16
CO-R10.S04-WE-IR-100 | Trench Excavation and Bedding Works for Main Lines of Irrigation Network-[Road 10]-[SW-4] | 6 | 2026-03-03 | 2026-03-09 | 2026-02-12 | 2026-02-18 | 21367.69 | -16
CO-R10.S04-WE-IR-110 | Pipes Laying Works for Main Lines of Irrigation Network-[Road 10]-[SW-4] | 7 | 2026-03-10 | 2026-03-17 | 2026-02-19 | 2026-02-26 | 64103.07 | -16
CO-R10.S04-WE-IR-120 | Installation Works for Main Line Valves of Irrigation Network-[Road 10]-[SW-4] | 3 | 2026-03-18 | 2026-03-24 | 2026-02-28 | 2026-03-02 | 21925.75 | -16
CO-R10.S04-WE-IR-130 | Trench Backfilling and Compaction Works for Main Lines of Irrigation Network-[Road 10]-[SW-4] | 5 | 2026-03-25 | 2026-03-30 | 2026-03-03 | 2026-03-08 | 10683.85 | -16
Street Lighting Network |  | 97 | 2026-03-31 | 2026-07-26 | 2026-03-09 | 2026-07-07 | 135615.97 | 34
Lighting Poles Works |  | 37 | 2026-03-31 | 2026-05-12 | 2026-03-09 | 2026-04-23 | 68790.24 | 94
CO-R10.S04-WE-SL-100 | Foundation Excavation Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-4] | 10 | 2026-03-31 | 2026-04-11 | 2026-03-09 | 2026-03-19 | 2284.16 | -16
CO-R10.S04-WE-SL-110 | Installation Works for Lighting Poles Foundation of Street Lighting Network-[Road 10]-[SW-4] | 10 | 2026-04-06 | 2026-04-16 | 2026-03-15 | 2026-03-29 | 8731.44 | -16
CO-R10.S04-WE-SL-120 | Installation Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-4] | 18 | 2026-04-12 | 2026-05-02 | 2026-03-24 | 2026-04-13 | 25125.8 | -16
CO-R10.S04-WE-SL-210 | Backfilling Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-4] | 15 | 2026-04-18 | 2026-05-04 | 2026-03-30 | 2026-04-15 | 9136.66 | 94
CO-R10.S04-WE-SL-130 | Installation Works for Lighting Fixtures With Drop Wire of Street Lighting Network-[Road 10]-[SW-4] | 18 | 2026-04-22 | 2026-05-12 | 2026-04-04 | 2026-04-23 | 14375.52 | 94
CO-R10.S04-WE-SL-200 | Testing Works for Lighting Poles of Street Lighting Network-[Road 10]-[SW-4] | 7 | 2026-05-05 | 2026-05-12 | 2026-04-16 | 2026-04-23 | 9136.66 | 94
Cabling Works |  | 30 | 2026-05-03 | 2026-06-10 | 2026-04-14 | 2026-05-18 | 47398.36 | -16
CO-R10.S04-WE-SL-140 | Trench Excavation and Bedding Works for Street Lighting Network-[Road 10]-[SW-4] | 10 | 2026-05-03 | 2026-05-13 | 2026-04-14 | 2026-04-25 | 0 | -16
CO-R10.S04-WE-SL-150 | Cable Laying Works for Street Lighting Network-[Road 10]-[SW-4] | 10 | 2026-05-14 | 2026-05-25 | 2026-04-26 | 2026-05-06 | 44012.74 | -16
CO-R10.S04-WE-SL-160 | Trench Backfilling and Compaction Works for Street Lighting Network-[Road 10]-[SW-4] | 10 | 2026-05-31 | 2026-06-10 | 2026-05-07 | 2026-05-18 | 3385.62 | -16
Distrubution Panel Boards |  | 39 | 2026-06-11 | 2026-07-26 | 2026-05-19 | 2026-07-07 | 19427.37 | -7
CO-R10.S04-WE-SL-170 | Foundation Excavation Works For Panel Boards of Street Lighting Network-[Road 10]-[SW-4] | 18 | 2026-06-11 | 2026-07-01 | 2026-05-19 | 2026-06-13 | 0 | -16
CO-R10.S04-WE-SL-180 | Installation Works for Panel Board Concrete Foundations of Street Lighting Network-[Road 10]-[SW-4] | 12 | 2026-06-22 | 2026-07-05 | 2026-06-03 | 2026-06-16 | 0 | -7
CO-R10.S04-WE-SL-190 | Installation Works for Lighting Panel Boards of Street Lighting Network-[Road 10]-[SW-4] | 12 | 2026-07-06 | 2026-07-19 | 2026-06-17 | 2026-06-30 | 0 | -7
CO-R10.S04-WE-SL-220 | A wall of concrete blocks to install the KWH meter of Street Lighting Network-[Road 10]-[SW-4] | 18 | 2026-07-06 | 2026-07-26 | 2026-06-17 | 2026-07-07 | 19427.37 | -7
Telecom Network |  | 28 | 2026-07-09 | 2026-08-10 | 2026-06-21 | 2026-07-22 | 80544.72 | -16
Ducts Works |  | 28 | 2026-07-09 | 2026-08-10 | 2026-06-21 | 2026-07-22 | 66430.5 | -16
CO-R10.S04-WE-TE-100 | Trench Excavation and Bedding Works for Ducts of Telecom Network-[Road 10]-[SW-4] | 7 | 2026-07-09 | 2026-07-16 | 2026-06-21 | 2026-06-28 | 6700 | -16
CO-R10.S04-WE-TE-110 | Pipes Laying Works for Ducts of Telecom Network-[Road 10]-[SW-4] | 7 | 2026-07-18 | 2026-07-25 | 2026-06-29 | 2026-07-06 | 39764.5 | -16
CO-R10.S04-WE-TE-120 | Pouring Plain Concrete Above Ducts of Telecom Network-[Road 10]-[SW-4] | 7 | 2026-07-26 | 2026-08-02 | 2026-07-07 | 2026-07-14 | 6700 | -16
CO-R10.S04-WE-TE-130 | Trench Backfilling and Compaction Works for Ducts of Telecom Network-[Road 10]-[SW-4] | 7 | 2026-08-03 | 2026-08-10 | 2026-07-15 | 2026-07-22 | 13266 | -16
Manholes Works |  | 21 | 2026-07-18 | 2026-08-10 | 2026-06-29 | 2026-07-22 | 14114.22 | -16
CO-R10.S04-WE-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 10]-[SW-4] | 7 | 2026-07-18 | 2026-07-25 | 2026-06-29 | 2026-07-06 | 2199.61 | -16
CO-R10.S04-WE-TE-150 | Installation Works for Manholes of Telecom Network-[Road 10]-[SW-4] | 7 | 2026-07-26 | 2026-08-02 | 2026-07-07 | 2026-07-14 | 9715 | -16
CO-R10.S04-WE-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 10]-[SW-4] | 7 | 2026-08-03 | 2026-08-10 | 2026-07-15 | 2026-07-22 | 2199.61 | -16
Road Works |  | 60 | 2026-08-11 | 2026-10-20 | 2026-07-23 | 2026-10-01 | 703651.89 | -16
Pre-Bituminous Construction |  | 15 | 2026-08-11 | 2026-08-27 | 2026-07-23 | 2026-08-09 | 446397.22 | -9
CO-R10.S04-WE-RD-100 | Capping and Subgrade Layer for Road Works-[Road 10]-[SW-4] | 12 | 2026-08-11 | 2026-08-24 | 2026-07-23 | 2026-08-05 | 263120.65 | -14
CO-R10.S04-WE-RD-110 | Aggregate Base Course Layer for Road Works-[Road 10]-[SW-4] | 12 | 2026-08-15 | 2026-08-27 | 2026-07-27 | 2026-08-09 | 183276.57 | -9
Pavement Works |  | 54 | 2026-08-18 | 2026-10-20 | 2026-07-30 | 2026-10-01 | 257254.67 | -16
CO-R10.S04-WE-RD-120 | Fixing of Curbstone for Sidewalks Pavement-[Road 10]-[SW-4] | 12 | 2026-08-18 | 2026-08-31 | 2026-07-30 | 2026-08-12 | 150070.62 | -9
CO-R10.S04-WE-RD-130 | Fixing of Interlock Tiles for Sidewalks Pavement-[Road 10]-[SW-4] | 12 | 2026-10-07 | 2026-10-20 | 2026-09-17 | 2026-10-01 | 107184.05 | -16
Road 11 Local 1 ( 670 LM ) |  | 385 | 2025-07-30 | 2026-11-01 | 2025-09-01 | 2026-10-13 | 5058301.47 | -16
SW_5 |  | 383 | 2025-07-30 | 2026-10-29 | 2025-09-01 | 2026-10-11 | 2902814.46 | -16
Sewage Network |  | 43 | 2025-07-30 | 2025-09-17 | 2025-09-01 | 2025-10-13 | 1522819.84 | 38
Main Line Sections |  | 43 | 2025-07-30 | 2025-09-17 | 2025-09-01 | 2025-10-13 | 1426048.59 | 38
CO-R11.S05-SW-100 | Trench Excavation and Bedding Works for Main Lines of Sewage Network-[Road 11]-[SW-5] | 12 | 2025-07-30 | 2025-08-12 | 2025-09-01 | 2025-09-14 | 316901.49 | 45
CO-R11.S05-SW-120 | Pipes Laying Works for Main Lines of Sewage Network-[Road 11]-[SW-5] | 12 | 2025-08-17 | 2025-08-30 | 2025-09-15 | 2025-09-29 | 950696.36 | 42
CO-R11.S05-SW-130 | Trench Backfilling and Compaction Works for Main Lines of Sewage Network-[Road 11]-[SW-5] | 12 | 2025-09-04 | 2025-09-17 | 2025-09-30 | 2025-10-13 | 158450.74 | 38
Manholes |  | 28 | 2025-08-17 | 2025-09-17 | 2025-09-15 | 2025-09-30 | 96771.25 | 38
CO-R11.S05-SW-160 | Excavation Works for Main Line Manholes of Sewage Network-[Road 11]-[SW-5] | 1 | 2025-08-17 | 2025-08-17 | 2025-09-15 | 2025-09-15 | 16128.54 | 53
CO-R11.S05-SW-170 | Installation RC Footing Works for Main Line Manholes of Sewage Network-[Road 11]-[SW-5] | 2 | 2025-09-04 | 2025-09-06 | 2025-09-16 | 2025-09-17 | 10752.36 | 38
CO-R11.S05-SW-180 | Install Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 11]-[SW-5] | 4 | 2025-09-07 | 2025-09-10 | 2025-09-18 | 2025-09-22 | 43009.44 | 38
CO-R11.S05-SW-190 | Pouring Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 11]-[SW-5] | 1 | 2025-09-11 | 2025-09-11 | 2025-09-24 | 2025-09-24 | 5376.18 | 38
CO-R11.S05-SW-200 | Backfilling Works for Main Line Manholes of Sewage Network-[Road 11]-[SW-5] | 4 | 2025-09-13 | 2025-09-16 | 2025-09-25 | 2025-09-29 | 16128.54 | 38
CO-R11.S05-SW-210 | Testing Works for Main Line Manholes of Sewage Network-[Road 11]-[SW-5] | 1 | 2025-09-17 | 2025-09-17 | 2025-09-30 | 2025-09-30 | 5376.18 | 38
Storm Drainage Network |  | 70 | 2025-11-13 | 2026-02-02 | 2025-10-26 | 2026-01-14 | 704520.46 | 81
Main Line Sections |  | 70 | 2025-11-13 | 2026-02-02 | 2025-10-26 | 2026-01-14 | 390807.28 | 7
CO-R11.S05-SD-100 | Trench Excavation and Bedding Works for Main Lines of Storm Drainage Network-[Road 11]-[SW-5] | 10 | 2025-11-13 | 2025-11-24 | 2025-10-26 | 2025-11-05 | 86846.06 | -16
CO-R11.S05-SD-120 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 11]-[SW-5] | 10 | 2025-11-25 | 2025-12-06 | 2025-11-06 | 2025-11-17 | 260538.19 | -16
CO-R11.S05-SD-130 | Trench Backfilling and Compaction Works for Main Lines of Storm Drainage Network-[Road 11]-[SW-5] | 15 | 2026-01-17 | 2026-02-02 | 2025-12-29 | 2026-01-14 | 43423.03 | 7
Manholes |  | 14 | 2025-11-25 | 2025-12-10 | 2025-11-06 | 2025-11-22 | 240709.66 | 53
CO-R11.S05-SD-180 | Trench Excavation and Bedding Works for Manholes of Storm Drainage Network-[Road 11]-[SW-5] | 1 | 2025-11-25 | 2025-11-25 | 2025-11-06 | 2025-11-06 | 38006.79 | 53
CO-R11.S05-SD-190 | Install RC Footing Works for Manholes of Storm Drainage Network-[Road 11]-[SW-5] | 1 | 2025-11-26 | 2025-11-26 | 2025-11-08 | 2025-11-08 | 12668.93 | 53
CO-R11.S05-SD-200 | Install RC Wall Rings & Slab Works for Manholes of Storm Drainage Network-[Road 11]-[SW-5] | 4 | 2025-11-27 | 2025-12-01 | 2025-11-09 | 2025-11-12 | 114020.37 | 53
CO-R11.S05-SD-210 | Testing Works for Manholes of Storm Drainage Network-[Road 11]-[SW-5] | 1 | 2025-12-02 | 2025-12-02 | 2025-11-13 | 2025-11-13 | 25337.86 | 53
CO-R11.S05-SD-220 | Backfilling Works for Manholes of Storm Drainage Network-[Road 11]-[SW-5] | 7 | 2025-12-03 | 2025-12-10 | 2025-11-15 | 2025-11-22 | 50675.72 | 53
Catch Basin Sections |  | 30 | 2025-12-13 | 2026-01-15 | 2025-11-24 | 2025-12-28 | 73003.52 | 96
CO-R11.S05-SD-140 | Trench Excavation and Bedding Works for Catch Basins of Storm Drainage Network-[Road 11]-[SW-5] | 6 | 2025-12-13 | 2025-12-18 | 2025-11-24 | 2025-11-30 | 12167.25 | 96
CO-R11.S05-SD-150 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 11]-[SW-5] | 7 | 2025-12-20 | 2025-12-27 | 2025-12-01 | 2025-12-08 | 36501.76 | 96
CO-R11.S05-SD-160 | Testing Works for Catch Basins of Storm Drainage Network-[Road 11]-[SW-5] | 10 | 2025-12-28 | 2026-01-07 | 2025-12-09 | 2025-12-20 | 8111.5 | 96
CO-R11.S05-SD-170 | Trench Backfilling and Compaction Works for Catch Basins of Storm Drainage Network-[Road 11]-[SW-5] | 7 | 2026-01-08 | 2026-01-15 | 2025-12-21 | 2025-12-28 | 16223 | 96
Irrigation Network |  | 40 | 2026-01-17 | 2026-03-03 | 2025-12-29 | 2026-01-21 | 98466.8 | 77
Main Line Pipes |  | 40 | 2026-01-17 | 2026-03-03 | 2025-12-29 | 2026-01-21 | 98466.8 | 77
CO-R11.S05-IR-100 | Trench Excavation and Bedding Works for Main Lines of Irrigation Network-[Road 11]-[SW-5] | 4 | 2026-01-17 | 2026-01-20 | 2025-12-29 | 2026-01-01 | 12470.36 | 96
CO-R11.S05-IR-110 | Pipes Laying Works for Main Lines of Irrigation Network-[Road 11]-[SW-5] | 7 | 2026-01-28 | 2026-02-04 | 2026-01-03 | 2026-01-10 | 37411.08 | 90
CO-R11.S05-IR-120 | Installation Works for Main Line Valves of Irrigation Network-[Road 11]-[SW-5] | 3 | 2026-02-21 | 2026-02-23 | 2026-01-11 | 2026-01-13 | 42350.17 | 77
CO-R11.S05-IR-130 | Trench Backfilling and Compaction Works for Main Lines of Irrigation Network-[Road 11]-[SW-5] | 7 | 2026-02-24 | 2026-03-03 | 2026-01-14 | 2026-01-21 | 6235.18 | 77
Telecom Network |  | 37 | 2026-06-29 | 2026-08-10 | 2026-06-10 | 2026-07-22 | 47758.27 | -9
Ducts Works |  | 37 | 2026-06-29 | 2026-08-10 | 2026-06-10 | 2026-07-22 | 38357.5 | -16
CO-R11.S05-TE-100 | Trench Excavation and Bedding Works for Ducts of Telecom Network-[Road 11]-[SW-5] | 3 | 2026-06-29 | 2026-07-01 | 2026-06-10 | 2026-06-13 | 3819 | -16
CO-R11.S05-TE-110 | Pipes Laying Works for Ducts of Telecom Network-[Road 11]-[SW-5] | 7 | 2026-07-18 | 2026-07-25 | 2026-06-29 | 2026-07-06 | 23081.5 | -16
CO-R11.S05-TE-120 | Pouring Plain Concrete Above Ducts of Telecom Network-[Road 11]-[SW-5] | 7 | 2026-07-26 | 2026-08-02 | 2026-07-07 | 2026-07-14 | 3819 | -16
CO-R11.S05-TE-130 | Trench Backfilling and Compaction Works for Ducts of Telecom Network-[Road 11]-[SW-5] | 7 | 2026-08-03 | 2026-08-10 | 2026-07-15 | 2026-07-22 | 7638 | -16
Manholes Works |  | 21 | 2026-07-18 | 2026-08-10 | 2026-06-29 | 2026-07-22 | 9400.77 | -9
CO-R11.S05-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 11]-[SW-5] | 7 | 2026-07-18 | 2026-07-25 | 2026-06-29 | 2026-07-06 | 1256.92 | -16
CO-R11.S05-TE-150 | Installation Works for Manholes of Telecom Network-[Road 11]-[SW-5] | 7 | 2026-07-26 | 2026-08-02 | 2026-07-07 | 2026-07-14 | 6886.93 | -9
CO-R11.S05-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 11]-[SW-5] | 7 | 2026-08-03 | 2026-08-10 | 2026-07-15 | 2026-07-22 | 1256.92 | -9
Medium Voltage Network |  | 24 | 2026-08-10 | 2026-09-06 | 2026-07-22 | 2026-08-18 | 118681.75 | -16
Cabling Works |  | 24 | 2026-08-10 | 2026-09-06 | 2026-07-22 | 2026-08-18 | 118681.75 | -16
CO-R11.S05-MV-100 | Trench Excavation and Bedding Works for Medium Voltage Network-[Road 11]-[SW-5] | 18 | 2026-08-10 | 2026-08-30 | 2026-07-22 | 2026-08-11 | 13528.75 | -16
CO-R11.S05-MV-110 | Cable Laying Works for Medium Voltage Network-[Road 11]-[SW-5] | 18 | 2026-08-13 | 2026-09-02 | 2026-07-26 | 2026-08-15 | 73607.1 | -16
CO-R11.S05-MV-120 | Trench Backfilling and Compaction Works for Medium Voltage Network-[Road 11]-[SW-5] | 18 | 2026-08-17 | 2026-09-06 | 2026-07-29 | 2026-08-18 | 31545.9 | -16
Road Works |  | 60 | 2026-08-20 | 2026-10-29 | 2026-08-02 | 2026-10-11 | 410567.34 | -16
Pre-Bituminous Construction |  | 29 | 2026-08-20 | 2026-09-22 | 2026-08-02 | 2026-09-03 | 260522.45 | -13
CO-R11.S05-RD-P-100 | Capping and Subgrade Layer for Road Works-[Road 11]-[SW-5] | 18 | 2026-08-20 | 2026-09-09 | 2026-08-02 | 2026-08-22 | 153560.31 | -16
CO-R11.S05-RD-P-110 | Aggregate Base Course Layer for Road Works-[Road 11]-[SW-5] | 18 | 2026-09-02 | 2026-09-22 | 2026-08-15 | 2026-09-03 | 106962.14 | -13
Pavement Works |  | 46 | 2026-09-06 | 2026-10-29 | 2026-08-18 | 2026-10-11 | 150044.89 | -16
CO-R11.S05-RD-P-120 | Fixing of Curbstone for Sidewalks Pavement-[Road 11]-[SW-5] | 18 | 2026-09-06 | 2026-09-27 | 2026-08-18 | 2026-09-07 | 87582.94 | -13
CO-R11.S05-RD-P-130 | Fixing of Interlock Tiles for Sidewalks Pavement-[Road 11]-[SW-5] | 10 | 2026-10-19 | 2026-10-29 | 2026-09-30 | 2026-10-11 | 62461.96 | -16
SW_6 |  | 373 | 2025-08-13 | 2026-11-01 | 2025-09-15 | 2026-10-13 | 2155487 | -16
Sewage Network |  | 34 | 2025-08-13 | 2025-09-21 | 2025-09-15 | 2025-10-25 | 369332.4 | 45
Main Line Sections |  | 34 | 2025-08-13 | 2025-09-21 | 2025-09-15 | 2025-10-25 | 206461.5 | 45
CO-R11.S06-SW-100 | Trench Excavation and Bedding Works for Main Lines of Sewage Network-[Road 11]-[SW-6] | 12 | 2025-08-13 | 2025-08-26 | 2025-09-15 | 2025-09-29 | 45880.33 | 45
CO-R11.S06-SW-120 | Pipes Laying Works for Main Lines of Sewage Network-[Road 11]-[SW-6] | 12 | 2025-08-27 | 2025-09-09 | 2025-09-30 | 2025-10-13 | 137641 | 45
CO-R11.S06-SW-130 | Trench Backfilling and Compaction Works for Main Lines of Sewage Network-[Road 11]-[SW-6] | 10 | 2025-09-10 | 2025-09-21 | 2025-10-14 | 2025-10-25 | 22940.17 | 45
Manholes |  | 19 | 2025-08-27 | 2025-09-17 | 2025-09-30 | 2025-10-14 | 162870.9 | 48
CO-R11.S06-SW-160 | Excavation Works for Main Line Manholes of Sewage Network-[Road 11]-[SW-6] | 1 | 2025-08-27 | 2025-08-27 | 2025-09-30 | 2025-09-30 | 27145.15 | 54
CO-R11.S06-SW-170 | Installation RC Footing Works for Main Line Manholes of Sewage Network-[Road 11]-[SW-6] | 2 | 2025-09-04 | 2025-09-06 | 2025-10-01 | 2025-10-02 | 18096.77 | 48
CO-R11.S06-SW-180 | Install Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 11]-[SW-6] | 4 | 2025-09-07 | 2025-09-10 | 2025-10-04 | 2025-10-07 | 72387.07 | 48
CO-R11.S06-SW-190 | Pouring Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 11]-[SW-6] | 1 | 2025-09-11 | 2025-09-11 | 2025-10-08 | 2025-10-08 | 9048.38 | 48
CO-R11.S06-SW-200 | Backfilling Works for Main Line Manholes of Sewage Network-[Road 11]-[SW-6] | 4 | 2025-09-13 | 2025-09-16 | 2025-10-09 | 2025-10-13 | 27145.15 | 48
CO-R11.S06-SW-210 | Testing Works for Main Line Manholes of Sewage Network-[Road 11]-[SW-6] | 1 | 2025-09-17 | 2025-09-17 | 2025-10-14 | 2025-10-14 | 9048.38 | 48
Storm Drainage Network |  | 102 | 2025-11-25 | 2026-03-26 | 2025-11-06 | 2026-01-21 | 896613.51 | 106
Main Line Sections |  | 65 | 2025-11-25 | 2026-02-08 | 2025-11-06 | 2026-01-20 | 602440.24 | -12
CO-R11.S06-SD-100 | Trench Excavation and Bedding Works for Main Lines of Storm Drainage Network-[Road 11]-[SW-6] | 10 | 2025-11-25 | 2025-12-06 | 2025-11-06 | 2025-11-17 | 133875.61 | -16
CO-R11.S06-SD-120 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 11]-[SW-6] | 10 | 2025-12-07 | 2025-12-17 | 2025-11-18 | 2025-11-29 | 401626.83 | -16
CO-R11.S06-SD-130 | Trench Backfilling and Compaction Works for Main Lines of Storm Drainage Network-[Road 11]-[SW-6] | 15 | 2026-01-22 | 2026-02-08 | 2026-01-04 | 2026-01-20 | 66937.8 | -12
Manholes |  | 14 | 2025-12-07 | 2025-12-22 | 2025-11-18 | 2025-12-03 | 221169.75 | 29
CO-R11.S06-SD-180 | Trench Excavation and Bedding Works for Manholes of Storm Drainage Network-[Road 11]-[SW-6] | 1 | 2025-12-07 | 2025-12-07 | 2025-11-18 | 2025-11-18 | 34921.54 | 29
CO-R11.S06-SD-190 | Install RC Footing Works for Manholes of Storm Drainage Network-[Road 11]-[SW-6] | 1 | 2025-12-08 | 2025-12-08 | 2025-11-19 | 2025-11-19 | 11640.51 | 29
CO-R11.S06-SD-200 | Install RC Wall Rings & Slab Works for Manholes of Storm Drainage Network-[Road 11]-[SW-6] | 4 | 2025-12-09 | 2025-12-13 | 2025-11-20 | 2025-11-24 | 104764.62 | 29
CO-R11.S06-SD-210 | Testing Works for Manholes of Storm Drainage Network-[Road 11]-[SW-6] | 1 | 2025-12-14 | 2025-12-14 | 2025-11-25 | 2025-11-25 | 23281.03 | 29
CO-R11.S06-SD-220 | Backfilling Works for Manholes of Storm Drainage Network-[Road 11]-[SW-6] | 7 | 2025-12-15 | 2025-12-22 | 2025-11-26 | 2025-12-03 | 46562.05 | 29
Catch Basin Sections |  | 78 | 2025-12-23 | 2026-03-26 | 2025-12-04 | 2026-01-21 | 73003.52 | 106
CO-R11.S06-SD-140 | Trench Excavation and Bedding Works for Catch Basins of Storm Drainage Network-[Road 11]-[SW-6] | 7 | 2025-12-23 | 2025-12-30 | 2025-12-04 | 2025-12-11 | 12167.25 | 157
CO-R11.S06-SD-150 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 11]-[SW-6] | 7 | 2026-03-01 | 2026-03-08 | 2025-12-30 | 2026-01-06 | 36501.76 | 106
CO-R11.S06-SD-160 | Testing Works for Catch Basins of Storm Drainage Network-[Road 11]-[SW-6] | 6 | 2026-03-09 | 2026-03-15 | 2026-01-07 | 2026-01-13 | 8111.5 | 106
CO-R11.S06-SD-170 | Trench Backfilling and Compaction Works for Catch Basins of Storm Drainage Network-[Road 11]-[SW-6] | 7 | 2026-03-16 | 2026-03-26 | 2026-01-14 | 2026-01-21 | 16223 | 106
Potable Water Network |  | 43 | 2026-02-09 | 2026-04-02 | 2026-01-21 | 2026-02-28 | 158325.75 | -16
Main Line Sections |  | 43 | 2026-02-09 | 2026-04-02 | 2026-01-21 | 2026-02-28 | 104566.96 | -16
CO-R11.S06-PW-100 | Trench Excavation and Bedding Works for Main Lines of Potable Water Network-[Road 11]-[SW-6] | 6 | 2026-02-09 | 2026-02-15 | 2026-01-21 | 2026-01-27 | 23237.1 | -6
CO-R11.S06-PW-110 | Pipes Laying and accessories for Main Lines of Potable Water Network-[Road 11]-[SW-6] | 10 | 2026-02-28 | 2026-03-10 | 2026-01-28 | 2026-02-08 | 58092.76 | -16
CO-R11.S06-PW-130 | Trench Backfilling and Compaction Works for Main Lines of Potable Water Network-[Road 11]-[SW-6] | 10 | 2026-03-19 | 2026-04-02 | 2026-02-17 | 2026-02-28 | 23237.1 | -16
Valve Chamber |  | 6 | 2026-02-16 | 2026-02-22 | 2026-01-28 | 2026-02-03 | 15887.04 | 15
CO-R11.S06-PW-210 | Installation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 11]-[SW-6] | 6 | 2026-02-16 | 2026-02-22 | 2026-01-28 | 2026-02-03 | 15887.04 | 15
Fire Hydrant |  | 21 | 2026-03-07 | 2026-04-02 | 2026-02-04 | 2026-02-28 | 37871.75 | -16
CO-R11.S06-PW-140 | Excavation Works for Fire Hydrants of Potable Water Network-[Road 11]-[SW-6] | 7 | 2026-03-07 | 2026-03-14 | 2026-02-04 | 2026-02-11 | 5680.76 | -16
CO-R11.S06-PW-150 | Installation Works for Fire Hydrant of Potable Water Network-[Road 11]-[SW-6] | 7 | 2026-03-15 | 2026-03-25 | 2026-02-12 | 2026-02-19 | 24616.64 | -16
CO-R11.S06-PW-160 | Trench Backfilling and Compaction Works for Fire Hydrants of Potable Water Network-[Road 11]-[SW-6] | 7 | 2026-03-26 | 2026-04-02 | 2026-02-21 | 2026-02-28 | 7574.35 | -16
Street Lighting Network |  | 109 | 2026-04-04 | 2026-08-12 | 2026-03-01 | 2026-07-25 | 154109.78 | 37
Lighting Poles Works |  | 104 | 2026-04-04 | 2026-08-06 | 2026-03-01 | 2026-07-19 | 80255.28 | 42
CO-R11.S06-SL-100 | Foundation Excavation Works for Lighting Poles of Street Lighting Network-[Road 11]-[SW-6] | 12 | 2026-04-04 | 2026-04-16 | 2026-03-01 | 2026-03-14 | 2664.86 | -16
CO-R11.S06-SL-110 | Installation Works for Lighting Poles Foundation of Street Lighting Network-[Road 11]-[SW-6] | 10 | 2026-04-18 | 2026-04-28 | 2026-03-30 | 2026-04-09 | 10186.68 | -16
CO-R11.S06-SL-120 | Installation Works for Lighting Poles of Street Lighting Network-[Road 11]-[SW-6] | 18 | 2026-05-03 | 2026-05-23 | 2026-04-05 | 2026-04-25 | 29313.44 | -16
CO-R11.S06-SL-210 | Backfilling Works for Lighting Poles of Street Lighting Network-[Road 11]-[SW-6] | 15 | 2026-07-13 | 2026-07-29 | 2026-06-24 | 2026-07-11 | 10659.43 | 42
CO-R11.S06-SL-130 | Installation Works for Lighting Fixtures With Drop Wire of Street Lighting Network-[Road 11]-[SW-6] | 18 | 2026-07-18 | 2026-08-06 | 2026-06-29 | 2026-07-19 | 16771.44 | 42
CO-R11.S06-SL-200 | Testing Works for Lighting Poles of Street Lighting Network-[Road 11]-[SW-6] | 7 | 2026-07-30 | 2026-08-06 | 2026-07-12 | 2026-07-19 | 10659.43 | 42
Cabling Works |  | 30 | 2026-05-24 | 2026-07-01 | 2026-04-26 | 2026-06-03 | 55843.83 | -16
CO-R11.S06-SL-140 | Trench Excavation and Bedding Works for Street Lighting Network-[Road 11]-[SW-6] | 10 | 2026-05-24 | 2026-06-08 | 2026-04-26 | 2026-05-06 | 0 | -16
CO-R11.S06-SL-150 | Cable Laying Works for Street Lighting Network-[Road 11]-[SW-6] | 10 | 2026-06-09 | 2026-06-20 | 2026-05-07 | 2026-05-18 | 51854.99 | -16
CO-R11.S06-SL-160 | Trench Backfilling and Compaction Works for Street Lighting Network-[Road 11]-[SW-6] | 10 | 2026-06-21 | 2026-07-01 | 2026-05-19 | 2026-06-03 | 3988.85 | -16
Distrubution Panel Boards |  | 36 | 2026-07-02 | 2026-08-12 | 2026-06-14 | 2026-07-25 | 18010.67 | -10
CO-R11.S06-SL-170 | Foundation Excavation Works For Panel Boards of Street Lighting Network-[Road 11]-[SW-6] | 12 | 2026-07-02 | 2026-07-15 | 2026-06-14 | 2026-06-27 | 0 | -16
CO-R11.S06-SL-180 | Installation Works for Panel Board Concrete Foundations of Street Lighting Network-[Road 11]-[SW-6] | 12 | 2026-07-16 | 2026-07-29 | 2026-06-28 | 2026-07-11 | 0 | -16
CO-R11.S06-SL-190 | Installation Works for Lighting Panel Boards of Street Lighting Network-[Road 11]-[SW-6] | 12 | 2026-07-30 | 2026-08-12 | 2026-07-12 | 2026-07-25 | 0 | -16
CO-R11.S06-SL-220 | A wall of concrete blocks to install the KWH meter of Street Lighting Network-[Road 11]-[SW-6] | 12 | 2026-07-30 | 2026-08-12 | 2026-07-12 | 2026-07-25 | 18010.67 | -10
Telecom Network |  | 41 | 2026-07-02 | 2026-08-18 | 2026-06-14 | 2026-07-30 | 47758.27 | -16
Ducts Works |  | 41 | 2026-07-02 | 2026-08-18 | 2026-06-14 | 2026-07-30 | 38357.5 | -16
CO-R11.S06-TE-100 | Trench Excavation and Bedding Works for Ducts of Telecom Network-[Road 11]-[SW-6] | 3 | 2026-07-02 | 2026-07-05 | 2026-06-14 | 2026-06-16 | 3819 | -16
CO-R11.S06-TE-110 | Pipes Laying Works for Ducts of Telecom Network-[Road 11]-[SW-6] | 7 | 2026-07-26 | 2026-08-02 | 2026-07-07 | 2026-07-14 | 23081.5 | -16
CO-R11.S06-TE-120 | Pouring Plain Concrete Above Ducts of Telecom Network-[Road 11]-[SW-6] | 7 | 2026-08-03 | 2026-08-10 | 2026-07-15 | 2026-07-22 | 3819 | -16
CO-R11.S06-TE-130 | Trench Backfilling and Compaction Works for Ducts of Telecom Network-[Road 11]-[SW-6] | 7 | 2026-08-11 | 2026-08-18 | 2026-07-23 | 2026-07-30 | 7638 | -16
Manholes Works |  | 21 | 2026-07-26 | 2026-08-18 | 2026-07-07 | 2026-07-30 | 9400.77 | -16
CO-R11.S06-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 11]-[SW-6] | 7 | 2026-07-26 | 2026-08-02 | 2026-07-07 | 2026-07-14 | 1256.92 | -16
CO-R11.S06-TE-150 | Installation Works for Manholes of Telecom Network-[Road 11]-[SW-6] | 7 | 2026-08-03 | 2026-08-10 | 2026-07-15 | 2026-07-22 | 6886.93 | -16
CO-R11.S06-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 11]-[SW-6] | 7 | 2026-08-11 | 2026-08-18 | 2026-07-23 | 2026-07-30 | 1256.92 | -16
Medium Voltage Network |  | 18 | 2026-08-15 | 2026-09-03 | 2026-07-27 | 2026-08-16 | 118779.95 | -14
Cabling Works |  | 18 | 2026-08-15 | 2026-09-03 | 2026-07-27 | 2026-08-16 | 118779.95 | -14
CO-R11.S06-MV-100 | Trench Excavation and Bedding Works for Medium Voltage Network-[Road 11]-[SW-6] | 12 | 2026-08-15 | 2026-08-27 | 2026-07-27 | 2026-08-09 | 13626.94 | -14
CO-R11.S06-MV-110 | Cable Laying Works for Medium Voltage Network-[Road 11]-[SW-6] | 12 | 2026-08-18 | 2026-08-31 | 2026-07-30 | 2026-08-12 | 73607.1 | -14
CO-R11.S06-MV-120 | Trench Backfilling and Compaction Works for Medium Voltage Network-[Road 11]-[SW-6] | 12 | 2026-08-22 | 2026-09-03 | 2026-08-03 | 2026-08-16 | 31545.9 | -14
Road Works |  | 58 | 2026-08-25 | 2026-11-01 | 2026-08-06 | 2026-10-13 | 410567.34 | -16
Pre-Bituminous Construction |  | 23 | 2026-08-25 | 2026-09-20 | 2026-08-06 | 2026-09-01 | 260522.45 | -11
CO-R11.S06-RD-P-100 | Capping and Subgrade Layer for Road Works-[Road 11]-[SW-6] | 12 | 2026-08-25 | 2026-09-07 | 2026-08-06 | 2026-08-19 | 153560.31 | -14
CO-R11.S06-RD-P-110 | Aggregate Base Course Layer for Road Works-[Road 11]-[SW-6] | 18 | 2026-08-31 | 2026-09-20 | 2026-08-12 | 2026-09-01 | 106962.14 | -11
Pavement Works |  | 50 | 2026-09-03 | 2026-11-01 | 2026-08-16 | 2026-10-13 | 150044.89 | -16
CO-R11.S06-RD-P-120 | Fixing of Curbstone for Sidewalks Pavement-[Road 11]-[SW-6] | 18 | 2026-09-03 | 2026-09-24 | 2026-08-16 | 2026-09-05 | 87582.94 | -11
CO-R11.S06-RD-P-130 | Fixing of Interlock Tiles for Sidewalks Pavement-[Road 11]-[SW-6] | 10 | 2026-10-21 | 2026-11-01 | 2026-10-03 | 2026-10-13 | 62461.96 | -16
Road 14 Local 1 ( 584 LM ) |  | 443 | 2025-06-02 | 2026-11-15 | 2025-08-02 | 2026-10-27 | 5712476.87 | -16
SW_7 |  | 441 | 2025-06-02 | 2026-11-12 | 2025-08-02 | 2026-10-25 | 2002431.63 | -16
Sewage Network |  | 52 | 2025-07-02 | 2025-08-31 | 2025-08-04 | 2025-09-14 | 253824.77 | 33
Main Line Sections |  | 52 | 2025-07-02 | 2025-08-31 | 2025-08-04 | 2025-09-14 | 140076.06 | 33
CO-R14.S07-SW-100 | Trench Excavation and Bedding Works for Main Lines of Sewage Network-[Road 14]-[SW-7] | 12 | 2025-07-02 | 2025-07-15 | 2025-08-04 | 2025-08-17 | 31128.01 | 45
CO-R14.S07-SW-120 | Pipes Laying Works for Main Lines of Sewage Network-[Road 14]-[SW-7] | 12 | 2025-07-31 | 2025-08-13 | 2025-08-18 | 2025-08-31 | 93384.04 | 36
CO-R14.S07-SW-130 | Trench Backfilling and Compaction Works for Main Lines of Sewage Network-[Road 14]-[SW-7] | 12 | 2025-08-18 | 2025-08-31 | 2025-09-01 | 2025-09-14 | 15564.01 | 33
Manholes |  | 27 | 2025-07-31 | 2025-08-31 | 2025-08-18 | 2025-09-01 | 113748.71 | 33
CO-R14.S07-SW-160 | Excavation Works for Main Line Manholes of Sewage Network-[Road 14]-[SW-7] | 1 | 2025-07-31 | 2025-07-31 | 2025-08-18 | 2025-08-18 | 18958.12 | 47
CO-R14.S07-SW-170 | Installation RC Footing Works for Main Line Manholes of Sewage Network-[Road 14]-[SW-7] | 2 | 2025-08-18 | 2025-08-19 | 2025-08-19 | 2025-08-20 | 12638.75 | 33
CO-R14.S07-SW-180 | Install Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 14]-[SW-7] | 4 | 2025-08-20 | 2025-08-24 | 2025-08-21 | 2025-08-25 | 50554.98 | 33
CO-R14.S07-SW-190 | Pouring Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 14]-[SW-7] | 1 | 2025-08-25 | 2025-08-25 | 2025-08-26 | 2025-08-26 | 6319.37 | 33
CO-R14.S07-SW-200 | Backfilling Works for Main Line Manholes of Sewage Network-[Road 14]-[SW-7] | 4 | 2025-08-26 | 2025-08-30 | 2025-08-27 | 2025-08-31 | 18958.12 | 33
CO-R14.S07-SW-210 | Testing Works for Main Line Manholes of Sewage Network-[Road 14]-[SW-7] | 1 | 2025-08-31 | 2025-08-31 | 2025-09-01 | 2025-09-01 | 6319.37 | 33
Storm Drainage Network |  | 105 | 2025-10-21 | 2026-02-19 | 2025-10-02 | 2026-02-01 | 779816.1 | 7
Main Line Sections |  | 105 | 2025-10-21 | 2026-02-19 | 2025-10-02 | 2026-02-01 | 549894.93 | 7
CO-R14.S07-SD-100 | Trench Excavation and Bedding Works for Main Lines of Storm Drainage Network-[Road 14]-[SW-7] | 10 | 2025-10-21 | 2025-11-01 | 2025-10-02 | 2025-10-13 | 122198.87 | -16
CO-R14.S07-SD-120 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 14]-[SW-7] | 10 | 2025-11-02 | 2025-11-12 | 2025-10-14 | 2025-10-25 | 366596.62 | -16
CO-R14.S07-SD-130 | Trench Backfilling and Compaction Works for Main Lines of Storm Drainage Network-[Road 14]-[SW-7] | 15 | 2026-02-03 | 2026-02-19 | 2026-01-15 | 2026-02-01 | 61099.44 | 7
Manholes |  | 14 | 2025-11-02 | 2025-11-17 | 2025-10-14 | 2025-10-29 | 122187.63 | 28
CO-R14.S07-SD-180 | Trench Excavation and Bedding Works for Manholes of Storm Drainage Network-[Road 14]-[SW-7] | 1 | 2025-11-02 | 2025-11-02 | 2025-10-14 | 2025-10-14 | 19292.78 | 28
CO-R14.S07-SD-190 | Install RC Footing Works for Manholes of Storm Drainage Network-[Road 14]-[SW-7] | 1 | 2025-11-03 | 2025-11-03 | 2025-10-15 | 2025-10-15 | 6430.93 | 28
CO-R14.S07-SD-200 | Install RC Wall Rings & Slab Works for Manholes of Storm Drainage Network-[Road 14]-[SW-7] | 4 | 2025-11-04 | 2025-11-08 | 2025-10-16 | 2025-10-20 | 57878.35 | 28
CO-R14.S07-SD-210 | Testing Works for Manholes of Storm Drainage Network-[Road 14]-[SW-7] | 1 | 2025-11-09 | 2025-11-09 | 2025-10-21 | 2025-10-21 | 12861.86 | 28
CO-R14.S07-SD-220 | Backfilling Works for Manholes of Storm Drainage Network-[Road 14]-[SW-7] | 7 | 2025-11-10 | 2025-11-17 | 2025-10-22 | 2025-10-29 | 25723.71 | 28
Catch Basin Sections |  | 27 | 2025-11-29 | 2025-12-29 | 2025-11-10 | 2025-12-10 | 107733.53 | 19
CO-R14.S07-SD-140 | Trench Excavation and Bedding Works for Catch Basins of Storm Drainage Network-[Road 14]-[SW-7] | 6 | 2025-11-29 | 2025-12-04 | 2025-11-10 | 2025-11-16 | 17955.67 | 19
CO-R14.S07-SD-150 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 14]-[SW-7] | 7 | 2025-12-06 | 2025-12-13 | 2025-11-17 | 2025-11-24 | 53866.77 | 19
CO-R14.S07-SD-160 | Testing Works for Catch Basins of Storm Drainage Network-[Road 14]-[SW-7] | 4 | 2025-12-17 | 2025-12-21 | 2025-11-29 | 2025-12-02 | 11970.37 | 19
CO-R14.S07-SD-170 | Trench Backfilling and Compaction Works for Catch Basins of Storm Drainage Network-[Road 14]-[SW-7] | 7 | 2025-12-22 | 2025-12-29 | 2025-12-03 | 2025-12-10 | 23940.73 | 19
Irrigation Network |  | 58 | 2025-12-30 | 2026-03-07 | 2025-12-11 | 2026-01-19 | 275532.87 | -6
Main Line Pipes |  | 58 | 2025-12-30 | 2026-03-07 | 2025-12-11 | 2026-01-19 | 275532.87 | -6
CO-R14.S07-IR-100 | Trench Excavation and Bedding Works for Main Lines of Irrigation Network-[Road 14]-[SW-7] | 7 | 2025-12-30 | 2026-01-06 | 2025-12-11 | 2025-12-18 | 48770.61 | 19
CO-R14.S07-IR-110 | Pipes Laying Works for Main Lines of Irrigation Network-[Road 14]-[SW-7] | 10 | 2026-01-25 | 2026-02-04 | 2025-12-20 | 2025-12-30 | 146311.82 | 4
CO-R14.S07-IR-120 | Installation Works for Main Line Valves of Irrigation Network-[Road 14]-[SW-7] | 7 | 2026-02-16 | 2026-02-23 | 2025-12-31 | 2026-01-07 | 56059.64 | -6
CO-R14.S07-IR-130 | Trench Backfilling and Compaction Works for Main Lines of Irrigation Network-[Road 14]-[SW-7] | 10 | 2026-02-24 | 2026-03-07 | 2026-01-08 | 2026-01-19 | 24390.81 | -6
Street Lighting Network |  | 326 | 2025-06-02 | 2026-06-30 | 2025-08-02 | 2026-06-11 | 17596.88 | 43
Lighting Poles Works |  | 92 | 2026-03-08 | 2026-06-30 | 2026-01-20 | 2026-06-11 | 17596.88 | 43
CO-R14.S07-SL-100 | Foundation Excavation Works for Lighting Poles of Street Lighting Network-[Road 14]-[SW-7] | 12 | 2026-03-08 | 2026-03-24 | 2026-01-20 | 2026-02-02 | 421.43 | -6
CO-R14.S07-SL-110 | Installation Works for Lighting Poles Foundation of Street Lighting Network-[Road 14]-[SW-7] | 12 | 2026-03-25 | 2026-04-07 | 2026-02-03 | 2026-02-16 | 3140.96 | -6
CO-R14.S07-SL-120 | Installation Works for Lighting Poles of Street Lighting Network-[Road 14]-[SW-7] | 18 | 2026-04-08 | 2026-04-28 | 2026-02-17 | 2026-03-09 | 3792.87 | -6
CO-R14.S07-SL-130 | Installation Works for Lighting Fixtures With Drop Wire of Street Lighting Network-[Road 14]-[SW-7] | 18 | 2026-06-10 | 2026-06-30 | 2026-05-18 | 2026-06-11 | 7713.04 | 43
CO-R14.S07-SL-210 | Backfilling Works for Lighting Poles of Street Lighting Network-[Road 14]-[SW-7] | 12 | 2026-06-11 | 2026-06-24 | 2026-05-19 | 2026-06-06 | 842.86 | 42
CO-R14.S07-SL-200 | Testing Works for Lighting Poles of Street Lighting Network-[Road 14]-[SW-7] | 5 | 2026-06-25 | 2026-06-30 | 2026-06-07 | 2026-06-11 | 1685.72 | 43
Cabling Works |  | 30 | 2026-04-28 | 2026-06-07 | 2026-03-09 | 2026-04-16 | 0 | -6
CO-R14.S07-SL-140 | Trench Excavation and Bedding Works for Street Lighting Network-[Road 14]-[SW-7] | 10 | 2026-04-28 | 2026-05-10 | 2026-03-09 | 2026-03-24 | 0 | -6
CO-R14.S07-SL-150 | Cable Laying Works for Street Lighting Network-[Road 14]-[SW-7] | 10 | 2026-05-10 | 2026-05-21 | 2026-03-24 | 2026-04-05 | 0 | -6
CO-R14.S07-SL-160 | Trench Backfilling and Compaction Works for Street Lighting Network-[Road 14]-[SW-7] | 10 | 2026-05-21 | 2026-06-07 | 2026-04-05 | 2026-04-16 | 0 | -6
Distrubution Panel Boards |  | 24 | 2025-06-02 | 2025-07-03 | 2025-08-02 | 2025-08-28 | 0 | 341
CO-R14.S07-SL-170 | Foundation Excavation Works For Panel Boards of Street Lighting Network-[Road 14]-[SW-7] | 18 | 2025-06-02 | 2025-06-26 | 2025-08-02 | 2025-08-21 | 0 | 341
CO-R14.S07-SL-220 | A wall of concrete blocks to install the KWH meter of Street Lighting Network-[Road 14]-[SW-7] | 18 | 2025-06-10 | 2025-06-30 | 2025-08-05 | 2025-08-25 | 0 | 344
CO-R14.S07-SL-180 | Installation Works for Panel Board Concrete Foundations of Street Lighting Network-[Road 14]-[SW-7] | 18 | 2025-06-10 | 2025-06-30 | 2025-08-05 | 2025-08-25 | 0 | 341
CO-R14.S07-SL-190 | Installation Works for Lighting Panel Boards of Street Lighting Network-[Road 14]-[SW-7] | 18 | 2025-06-14 | 2025-07-03 | 2025-08-09 | 2025-08-28 | 0 | 341
Telecom Network |  | 58 | 2026-06-13 | 2026-08-18 | 2026-05-20 | 2026-07-30 | 69526.57 | -9
Ducts Works |  | 58 | 2026-06-13 | 2026-08-18 | 2026-05-20 | 2026-07-30 | 56983.5 | -16
CO-R14.S07-TE-100 | Trench Excavation and Bedding Works for Ducts of Telecom Network-[Road 14]-[SW-7] | 3 | 2026-06-13 | 2026-06-15 | 2026-05-20 | 2026-05-23 | 5594.5 | -8
CO-R14.S07-TE-110 | Pipes Laying Works for Ducts of Telecom Network-[Road 14]-[SW-7] | 7 | 2026-07-26 | 2026-08-02 | 2026-07-07 | 2026-07-14 | 34304 | -16
CO-R14.S07-TE-120 | Pouring Plain Concrete Above Ducts of Telecom Network-[Road 14]-[SW-7] | 7 | 2026-08-03 | 2026-08-10 | 2026-07-15 | 2026-07-22 | 5594.5 | -16
CO-R14.S07-TE-130 | Trench Backfilling and Compaction Works for Ducts of Telecom Network-[Road 14]-[SW-7] | 7 | 2026-08-11 | 2026-08-18 | 2026-07-23 | 2026-07-30 | 11490.5 | -16
Manholes Works |  | 21 | 2026-07-26 | 2026-08-18 | 2026-07-07 | 2026-07-30 | 12543.07 | -9
CO-R14.S07-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 14]-[SW-7] | 7 | 2026-07-26 | 2026-08-02 | 2026-07-07 | 2026-07-14 | 1885.38 | -16
CO-R14.S07-TE-150 | Installation Works for Manholes of Telecom Network-[Road 14]-[SW-7] | 7 | 2026-08-03 | 2026-08-10 | 2026-07-15 | 2026-07-22 | 8772.31 | -9
CO-R14.S07-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 14]-[SW-7] | 7 | 2026-08-11 | 2026-08-18 | 2026-07-23 | 2026-07-30 | 1885.38 | -9
Road Works |  | 73 | 2026-08-19 | 2026-11-12 | 2026-08-01 | 2026-10-25 | 606134.44 | -16
Pre-Bituminous Construction |  | 48 | 2026-08-19 | 2026-10-14 | 2026-08-01 | 2026-09-26 | 384458.71 | -13
CO-R14.S07-RD-P-100 | Capping and Subgrade Layer for Road Works-[Road 14]-[SW-7] | 18 | 2026-08-19 | 2026-09-08 | 2026-08-01 | 2026-08-20 | 226612.18 | -3
CO-R14.S07-RD-P-110 | Aggregate Base Course Layer for Road Works-[Road 14]-[SW-7] | 18 | 2026-09-24 | 2026-10-14 | 2026-09-05 | 2026-09-26 | 157846.53 | -13
Pavement Works |  | 40 | 2026-09-28 | 2026-11-12 | 2026-09-08 | 2026-10-25 | 221675.73 | -16
CO-R14.S07-RD-P-120 | Fixing of Curbstone for Sidewalks Pavement-[Road 14]-[SW-7] | 18 | 2026-09-28 | 2026-10-18 | 2026-09-08 | 2026-09-29 | 129248.23 | -13
CO-R14.S07-RD-P-130 | Fixing of Interlock Tiles for Sidewalks Pavement-[Road 14]-[SW-7] | 12 | 2026-10-31 | 2026-11-12 | 2026-10-12 | 2026-10-25 | 92427.51 | -16
SW_8 |  | 409 | 2025-07-16 | 2026-11-15 | 2025-08-18 | 2026-10-27 | 3710045.24 | -16
Sewage Network |  | 40 | 2025-07-16 | 2025-08-31 | 2025-08-18 | 2025-09-29 | 182228.17 | 43
Main Line Sections |  | 40 | 2025-07-16 | 2025-08-31 | 2025-08-18 | 2025-09-29 | 140076.06 | 43
CO-R14.S08-SW-100 | Trench Excavation and Bedding Works for Main Lines of Sewage Network-[Road 14]-[SW-8] | 12 | 2025-07-16 | 2025-07-29 | 2025-08-18 | 2025-08-31 | 31128.01 | 45
CO-R14.S08-SW-120 | Pipes Laying Works for Main Lines of Sewage Network-[Road 14]-[SW-8] | 12 | 2025-07-31 | 2025-08-13 | 2025-09-01 | 2025-09-14 | 93384.04 | 46
CO-R14.S08-SW-130 | Trench Backfilling and Compaction Works for Main Lines of Sewage Network-[Road 14]-[SW-8] | 12 | 2025-08-18 | 2025-08-31 | 2025-09-15 | 2025-09-29 | 15564.01 | 43
Manholes |  | 27 | 2025-07-31 | 2025-08-31 | 2025-09-01 | 2025-09-15 | 42152.11 | 43
CO-R14.S08-SW-160 | Excavation Works for Main Line Manholes of Sewage Network-[Road 14]-[SW-8] | 1 | 2025-07-31 | 2025-07-31 | 2025-09-01 | 2025-09-01 | 7025.35 | 57
CO-R14.S08-SW-170 | Installation RC Footing Works for Main Line Manholes of Sewage Network-[Road 14]-[SW-8] | 2 | 2025-08-18 | 2025-08-19 | 2025-09-02 | 2025-09-03 | 4683.57 | 43
CO-R14.S08-SW-180 | Install Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 14]-[SW-8] | 4 | 2025-08-20 | 2025-08-24 | 2025-09-04 | 2025-09-08 | 18734.27 | 43
CO-R14.S08-SW-190 | Pouring Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 14]-[SW-8] | 1 | 2025-08-25 | 2025-08-25 | 2025-09-09 | 2025-09-09 | 2341.78 | 43
CO-R14.S08-SW-200 | Backfilling Works for Main Line Manholes of Sewage Network-[Road 14]-[SW-8] | 4 | 2025-08-26 | 2025-08-30 | 2025-09-10 | 2025-09-14 | 7025.35 | 43
CO-R14.S08-SW-210 | Testing Works for Main Line Manholes of Sewage Network-[Road 14]-[SW-8] | 1 | 2025-08-31 | 2025-08-31 | 2025-09-15 | 2025-09-15 | 2341.78 | 43
Storm Drainage Network |  | 100 | 2025-11-02 | 2026-02-25 | 2025-10-14 | 2026-02-07 | 770955.69 | 140
Main Line Sections |  | 100 | 2025-11-02 | 2026-02-25 | 2025-10-14 | 2026-02-07 | 448217.55 | -12
CO-R14.S08-SD-100 | Trench Excavation and Bedding Works for Main Lines of Storm Drainage Network-[Road 14]-[SW-8] | 10 | 2025-11-02 | 2025-11-12 | 2025-10-14 | 2025-10-25 | 99603.9 | -16
CO-R14.S08-SD-120 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 14]-[SW-8] | 10 | 2025-11-13 | 2025-11-24 | 2025-10-26 | 2025-11-05 | 298811.7 | -16
CO-R14.S08-SD-130 | Trench Backfilling and Compaction Works for Main Lines of Storm Drainage Network-[Road 14]-[SW-8] | 15 | 2026-02-09 | 2026-02-25 | 2026-01-21 | 2026-02-07 | 49801.95 | -12
Manholes |  | 14 | 2025-11-13 | 2025-11-29 | 2025-10-26 | 2025-11-10 | 215004.61 | 64
CO-R14.S08-SD-180 | Trench Excavation and Bedding Works for Manholes of Storm Drainage Network-[Road 14]-[SW-8] | 1 | 2025-11-13 | 2025-11-13 | 2025-10-26 | 2025-10-26 | 33948.1 | 64
CO-R14.S08-SD-190 | Install RC Footing Works for Manholes of Storm Drainage Network-[Road 14]-[SW-8] | 1 | 2025-11-15 | 2025-11-15 | 2025-10-27 | 2025-10-27 | 11316.03 | 64
CO-R14.S08-SD-200 | Install RC Wall Rings & Slab Works for Manholes of Storm Drainage Network-[Road 14]-[SW-8] | 4 | 2025-11-16 | 2025-11-19 | 2025-10-28 | 2025-11-01 | 101844.29 | 64
CO-R14.S08-SD-210 | Testing Works for Manholes of Storm Drainage Network-[Road 14]-[SW-8] | 1 | 2025-11-20 | 2025-11-20 | 2025-11-02 | 2025-11-02 | 22632.06 | 64
CO-R14.S08-SD-220 | Backfilling Works for Manholes of Storm Drainage Network-[Road 14]-[SW-8] | 7 | 2025-11-22 | 2025-11-29 | 2025-11-03 | 2025-11-10 | 45264.13 | 64
Catch Basin Sections |  | 39 | 2025-12-06 | 2026-01-19 | 2025-11-17 | 2025-12-14 | 107733.53 | 172
CO-R14.S08-SD-140 | Trench Excavation and Bedding Works for Catch Basins of Storm Drainage Network-[Road 14]-[SW-8] | 6 | 2025-12-06 | 2025-12-11 | 2025-11-17 | 2025-11-23 | 17955.67 | 96
CO-R14.S08-SD-150 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 14]-[SW-8] | 7 | 2025-12-30 | 2026-01-06 | 2025-11-24 | 2025-12-01 | 53866.77 | 172
CO-R14.S08-SD-160 | Testing Works for Catch Basins of Storm Drainage Network-[Road 14]-[SW-8] | 4 | 2026-01-07 | 2026-01-11 | 2025-12-02 | 2025-12-06 | 11970.37 | 172
CO-R14.S08-SD-170 | Trench Backfilling and Compaction Works for Catch Basins of Storm Drainage Network-[Road 14]-[SW-8] | 7 | 2026-01-12 | 2026-01-19 | 2025-12-07 | 2025-12-14 | 23940.73 | 172
Potable Water Network |  | 38 | 2026-02-26 | 2026-04-14 | 2026-02-08 | 2026-03-25 | 1505676.01 | -11
Main Line Sections |  | 38 | 2026-02-26 | 2026-04-14 | 2026-02-08 | 2026-03-25 | 400030.2 | -11
CO-R14.S08-PW-100 | Trench Excavation and Bedding Works for Main Lines of Potable Water Network-[Road 14]-[SW-8] | 10 | 2026-02-26 | 2026-03-09 | 2026-02-08 | 2026-02-18 | 88895.6 | -10
CO-R14.S08-PW-110 | Pipes Laying and accessories for Main Lines of Potable Water Network-[Road 14]-[SW-8] | 10 | 2026-03-11 | 2026-03-25 | 2026-02-19 | 2026-03-02 | 222239 | -11
CO-R14.S08-PW-130 | Trench Backfilling and Compaction Works for Main Lines of Potable Water Network-[Road 14]-[SW-8] | 10 | 2026-04-04 | 2026-04-14 | 2026-03-11 | 2026-03-25 | 88895.6 | -11
Valve Chamber |  | 16 | 2026-03-26 | 2026-04-13 | 2026-03-03 | 2026-03-24 | 1052625.36 | -10
CO-R14.S08-PW-170 | Excavation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 14]-[SW-8] | 1 | 2026-03-26 | 2026-03-26 | 2026-03-03 | 2026-03-03 | 68410.35 | -10
CO-R14.S08-PW-180 | RC Footing Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 14]-[SW-8] | 3 | 2026-03-28 | 2026-03-30 | 2026-03-04 | 2026-03-07 | 102615.53 | -10
CO-R14.S08-PW-190 | RC Wall Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 14]-[SW-8] | 6 | 2026-03-31 | 2026-04-06 | 2026-03-08 | 2026-03-14 | 239436.23 | -10
CO-R14.S08-PW-200 | RC Slab Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 14]-[SW-8] | 2 | 2026-04-07 | 2026-04-08 | 2026-03-15 | 2026-03-16 | 136820.7 | -10
CO-R14.S08-PW-210 | Insulation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 14]-[SW-8] | 1 | 2026-04-09 | 2026-04-09 | 2026-03-17 | 2026-03-17 | 368521.86 | -10
CO-R14.S08-PW-220 | Backfilling Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 14]-[SW-8] | 3 | 2026-04-11 | 2026-04-13 | 2026-03-18 | 2026-03-24 | 136820.7 | -10
Fire Hydrant |  | 21 | 2026-03-18 | 2026-04-14 | 2026-02-26 | 2026-03-25 | 53020.45 | -11
CO-R14.S08-PW-140 | Excavation Works for Fire Hydrants of Potable Water Network-[Road 14]-[SW-8] | 7 | 2026-03-18 | 2026-03-29 | 2026-02-26 | 2026-03-05 | 7953.07 | -11
CO-R14.S08-PW-150 | Installation Works for Fire Hydrant of Potable Water Network-[Road 14]-[SW-8] | 7 | 2026-03-30 | 2026-04-06 | 2026-03-07 | 2026-03-14 | 34463.29 | -11
CO-R14.S08-PW-160 | Trench Backfilling and Compaction Works for Fire Hydrants of Potable Water Network-[Road 14]-[SW-8] | 7 | 2026-04-07 | 2026-04-14 | 2026-03-15 | 2026-03-25 | 10604.09 | -11
Street Lighting Network |  | 117 | 2026-04-15 | 2026-09-02 | 2026-03-26 | 2026-08-15 | 228554.13 | 36
Lighting Poles Works |  | 112 | 2026-04-15 | 2026-08-27 | 2026-03-26 | 2026-08-09 | 120382.92 | 42
CO-R14.S08-SL-820 | Foundation Excavation Works for Lighting Poles of Street Lighting Network-[Road 14]-[SW-8] | 12 | 2026-04-15 | 2026-04-28 | 2026-03-26 | 2026-04-08 | 3997.29 | -11
CO-R14.S08-SL-830 | Installation Works for Lighting Poles Foundation of Street Lighting Network-[Road 14]-[SW-8] | 10 | 2026-04-29 | 2026-05-10 | 2026-04-11 | 2026-04-21 | 15280.02 | -16
CO-R14.S08-SL-840 | Installation Works for Lighting Poles of Street Lighting Network-[Road 14]-[SW-8] | 10 | 2026-05-05 | 2026-05-16 | 2026-04-16 | 2026-04-27 | 43970.16 | -16
CO-R14.S08-SL-210 | Backfilling Works for Lighting Poles of Street Lighting Network-[Road 14]-[SW-8] | 15 | 2026-06-25 | 2026-07-12 | 2026-06-07 | 2026-06-23 | 15989.15 | 42
CO-R14.S08-SL-200 | Testing Works for Lighting Poles of Street Lighting Network-[Road 14]-[SW-8] | 7 | 2026-07-13 | 2026-07-20 | 2026-06-24 | 2026-07-01 | 15989.15 | 74
CO-R14.S08-SL-850 | Installation Works for Lighting Fixtures With Drop Wire of Street Lighting Network-[Road 14]-[SW-8] | 18 | 2026-08-08 | 2026-08-27 | 2026-07-20 | 2026-08-09 | 25157.16 | 42
Cabling Works |  | 30 | 2026-05-17 | 2026-06-24 | 2026-04-28 | 2026-06-06 | 81352.74 | -16
CO-R14.S08-SL-640 | Trench Excavation and Bedding Works for Street Lighting Network-[Road 14]-[SW-8] | 10 | 2026-05-17 | 2026-06-01 | 2026-04-28 | 2026-05-09 | 0 | -16
CO-R14.S08-SL-650 | Cable Laying Works for Street Lighting Network-[Road 14]-[SW-8] | 10 | 2026-06-02 | 2026-06-13 | 2026-05-10 | 2026-05-20 | 75541.83 | -16
CO-R14.S08-SL-660 | Trench Backfilling and Compaction Works for Street Lighting Network-[Road 14]-[SW-8] | 10 | 2026-06-14 | 2026-06-24 | 2026-05-21 | 2026-06-06 | 5810.91 | -16
Distrubution Panel Boards |  | 42 | 2026-07-16 | 2026-09-02 | 2026-06-28 | 2026-08-15 | 26818.47 | -16
CO-R14.S08-SL-DB-640 | Foundation Excavation Works For Panel Boards of Street Lighting Network-[Road 14]-[SW-8] | 18 | 2026-07-16 | 2026-08-05 | 2026-06-28 | 2026-07-18 | 0 | -2
CO-R14.S08-SL-DB-650 | Installation Works for Panel Board Concrete Foundations of Street Lighting Network-[Road 14]-[SW-8] | 18 | 2026-07-30 | 2026-08-19 | 2026-07-12 | 2026-08-01 | 0 | -11
CO-R14.S08-SL-220 | A wall of concrete blocks to install the KWH meter of Street Lighting Network-[Road 14]-[SW-8] | 25 | 2026-07-30 | 2026-08-27 | 2026-07-12 | 2026-08-09 | 26818.47 | -11
CO-R14.S08-SL-DB-660 | Installation Works for Lighting Panel Boards of Street Lighting Network-[Road 14]-[SW-8] | 18 | 2026-08-13 | 2026-09-02 | 2026-07-26 | 2026-08-15 | 0 | -16
Telecom Network |  | 54 | 2026-06-25 | 2026-08-26 | 2026-06-07 | 2026-08-08 | 69526.57 | -16
Ducts Works |  | 54 | 2026-06-25 | 2026-08-26 | 2026-06-07 | 2026-08-08 | 56983.5 | -16
CO-R14.S08-TE-100 | Trench Excavation and Bedding Works for Ducts of Telecom Network-[Road 14]-[SW-8] | 3 | 2026-06-25 | 2026-06-28 | 2026-06-07 | 2026-06-09 | 5594.5 | -16
CO-R14.S08-TE-110 | Pipes Laying Works for Ducts of Telecom Network-[Road 14]-[SW-8] | 7 | 2026-08-03 | 2026-08-10 | 2026-07-15 | 2026-07-22 | 34304 | -16
CO-R14.S08-TE-120 | Pouring Plain Concrete Above Ducts of Telecom Network-[Road 14]-[SW-8] | 7 | 2026-08-11 | 2026-08-18 | 2026-07-23 | 2026-07-30 | 5594.5 | -16
CO-R14.S08-TE-130 | Trench Backfilling and Compaction Works for Ducts of Telecom Network-[Road 14]-[SW-8] | 7 | 2026-08-19 | 2026-08-26 | 2026-08-01 | 2026-08-08 | 11490.5 | -16
Manholes Works |  | 21 | 2026-08-03 | 2026-08-26 | 2026-07-15 | 2026-08-08 | 12543.07 | -16
CO-R14.S08-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 14]-[SW-8] | 7 | 2026-08-03 | 2026-08-10 | 2026-07-15 | 2026-07-22 | 1885.38 | -16
CO-R14.S08-TE-150 | Installation Works for Manholes of Telecom Network-[Road 14]-[SW-8] | 7 | 2026-08-11 | 2026-08-18 | 2026-07-23 | 2026-07-30 | 8772.31 | -16
CO-R14.S08-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 14]-[SW-8] | 7 | 2026-08-19 | 2026-08-26 | 2026-08-01 | 2026-08-08 | 1885.38 | -16
Medium Voltage Network |  | 16 | 2026-08-29 | 2026-09-15 | 2026-08-10 | 2026-08-27 | 346970.24 | -14
Cabling Works |  | 16 | 2026-08-29 | 2026-09-15 | 2026-08-10 | 2026-08-27 | 346970.24 | -14
CO-R14.S08-MV-ML-640 | Trench Excavation and Bedding Works for Medium Voltage Network-[Road 14]-[SW-8] | 10 | 2026-08-29 | 2026-09-08 | 2026-08-10 | 2026-08-20 | 39931.43 | -14
CO-R14.S08-MV-ML-650 | Cable Laying Works for Medium Voltage Network-[Road 14]-[SW-8] | 10 | 2026-09-01 | 2026-09-12 | 2026-08-13 | 2026-08-24 | 214927.17 | -14
CO-R14.S08-MV-ML-660 | Trench Backfilling and Compaction Works for Medium Voltage Network-[Road 14]-[SW-8] | 10 | 2026-09-05 | 2026-09-15 | 2026-08-17 | 2026-08-27 | 92111.64 | -14
Road Works |  | 58 | 2026-09-08 | 2026-11-15 | 2026-08-20 | 2026-10-27 | 606134.44 | -16
Pre-Bituminous Construction |  | 29 | 2026-09-08 | 2026-10-12 | 2026-08-20 | 2026-09-22 | 384458.71 | -11
CO-R14.S08-RD-P-100 | Capping and Subgrade Layer for Road Works-[Road 14]-[SW-8] | 10 | 2026-09-08 | 2026-09-19 | 2026-08-20 | 2026-08-31 | 226612.18 | -14
CO-R14.S08-RD-P-110 | Aggregate Base Course Layer for Road Works-[Road 14]-[SW-8] | 18 | 2026-09-21 | 2026-10-12 | 2026-09-02 | 2026-09-22 | 157846.53 | -11
Pavement Works |  | 44 | 2026-09-26 | 2026-11-15 | 2026-09-06 | 2026-10-27 | 221675.73 | -16
CO-R14.S08-RD-P-120 | Fixing of Curbstone for Sidewalks Pavement-[Road 14]-[SW-8] | 18 | 2026-09-26 | 2026-10-15 | 2026-09-06 | 2026-09-27 | 129248.23 | -11
CO-R14.S08-RD-P-130 | Fixing of Interlock Tiles for Sidewalks Pavement-[Road 14]-[SW-8] | 12 | 2026-11-02 | 2026-11-15 | 2026-10-14 | 2026-10-27 | 92427.51 | -16
Road 15 Local 1 ( 556 LM ) |  | 485 | 01-Apr-25 A | 2026-11-26 | 2025-04-26 | 2026-11-08 | 2998388.03 | -16
SW_9 |  | 485 | 01-Apr-25 A | 2026-11-26 | 2025-04-26 | 2026-11-08 | 1438600.68 | -16
Earthworks |  | 22 | 01-Apr-25 A | 13-Apr-25 A | 2025-04-26 | 2025-05-20 | 156330.3
Earthworks |  | 22 | 01-Apr-25 A | 13-Apr-25 A | 2025-04-26 | 2025-05-20 | 156330.3
CO-R15.S09-EW-200 | Roadway Excavation Works Upto Design Level for Earthworks-[Road 15]-[SW-9] | 10 | 01-Apr-25 A | 12-Apr-25 A | 2025-04-26 | 2025-05-06 | 49403.66
CO-R15.S09-EW-110 | Embankments Works Upto Design Level for Earthworks-[Road 15]-[SW-9] | 12 | 01-Apr-25 A | 13-Apr-25 A | 2025-05-07 | 2025-05-20 | 106926.64
Sewage Network |  | 80 | 2025-05-13 | 2025-08-18 | 2025-05-21 | 2025-07-30 | 258854.06 | -16
Main Line Sections |  | 80 | 2025-05-13 | 2025-08-18 | 2025-05-21 | 2025-07-30 | 93424.03 | -16
CO-R15.S09-SW-100 | Trench Excavation and Bedding Works for Main Lines of Sewage Network-[Road 15]-[SW-9] | 12 | 2025-05-13 | 2025-05-26 | 2025-05-21 | 2025-06-03 | 20760.89 | 30
CO-R15.S09-SW-120 | Pipes Laying Works for Main Lines of Sewage Network-[Road 15]-[SW-9] | 12 | 2025-06-29 | 2025-07-12 | 2025-06-04 | 2025-06-22 | 62282.68 | 6
CO-R15.S09-SW-130 | Trench Backfilling and Compaction Works for Main Lines of Sewage Network-[Road 15]-[SW-9] | 10 | 2025-08-07 | 2025-08-18 | 2025-07-20 | 2025-07-30 | 10380.45 | -16
Manholes |  | 25 | 2025-06-29 | 2025-07-27 | 2025-06-04 | 2025-06-23 | 165430.04 | 3
CO-R15.S09-SW-160 | Excavation Works for Main Line Manholes of Sewage Network-[Road 15]-[SW-9] | 1 | 2025-06-29 | 2025-06-29 | 2025-06-04 | 2025-06-04 | 27571.67 | 15
CO-R15.S09-SW-170 | Installation RC Footing Works for Main Line Manholes of Sewage Network-[Road 15]-[SW-9] | 2 | 2025-07-14 | 2025-07-15 | 2025-06-10 | 2025-06-11 | 18381.12 | 3
CO-R15.S09-SW-180 | Install Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 15]-[SW-9] | 4 | 2025-07-16 | 2025-07-20 | 2025-06-12 | 2025-06-16 | 73524.46 | 3
CO-R15.S09-SW-190 | Pouring Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 15]-[SW-9] | 1 | 2025-07-21 | 2025-07-21 | 2025-06-17 | 2025-06-17 | 9190.56 | 3
CO-R15.S09-SW-200 | Backfilling Works for Main Line Manholes of Sewage Network-[Road 15]-[SW-9] | 4 | 2025-07-22 | 2025-07-26 | 2025-06-18 | 2025-06-22 | 27571.67 | 3
CO-R15.S09-SW-210 | Testing Works for Main Line Manholes of Sewage Network-[Road 15]-[SW-9] | 1 | 2025-07-27 | 2025-07-27 | 2025-06-23 | 2025-06-23 | 9190.56 | 3
Storm Drainage Network |  | 181 | 2025-08-11 | 2026-03-10 | 2025-07-23 | 2026-02-19 | 378475.18 | 7
Main Line Sections |  | 181 | 2025-08-11 | 2026-03-10 | 2025-07-23 | 2026-02-19 | 254113.41 | 7
CO-R15.S09-SD-100 | Trench Excavation and Bedding Works for Main Lines of Storm Drainage Network-[Road 15]-[SW-9] | 10 | 2025-08-11 | 2025-08-21 | 2025-07-23 | 2025-08-03 | 56469.65 | 26
CO-R15.S09-SD-120 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 15]-[SW-9] | 15 | 2025-08-23 | 2025-09-08 | 2025-08-04 | 2025-08-20 | 169408.94 | 26
CO-R15.S09-SD-130 | Trench Backfilling and Compaction Works for Main Lines of Storm Drainage Network-[Road 15]-[SW-9] | 16 | 2026-02-21 | 2026-03-10 | 2026-02-02 | 2026-02-19 | 28234.82 | 7
Manholes |  | 14 | 2025-08-23 | 2025-09-07 | 2025-08-04 | 2025-08-19 | 62915.48 | 26
CO-R15.S09-SD-180 | Trench Excavation and Bedding Works for Manholes of Storm Drainage Network-[Road 15]-[SW-9] | 1 | 2025-08-23 | 2025-08-23 | 2025-08-04 | 2025-08-04 | 9934.02 | 26
CO-R15.S09-SD-190 | Install RC Footing Works for Manholes of Storm Drainage Network-[Road 15]-[SW-9] | 1 | 2025-08-24 | 2025-08-24 | 2025-08-05 | 2025-08-05 | 3311.34 | 26
CO-R15.S09-SD-200 | Install RC Wall Rings & Slab Works for Manholes of Storm Drainage Network-[Road 15]-[SW-9] | 4 | 2025-08-25 | 2025-08-28 | 2025-08-06 | 2025-08-10 | 29802.07 | 26
CO-R15.S09-SD-210 | Testing Works for Manholes of Storm Drainage Network-[Road 15]-[SW-9] | 1 | 2025-08-30 | 2025-08-30 | 2025-08-11 | 2025-08-11 | 6622.68 | 26
CO-R15.S09-SD-220 | Backfilling Works for Manholes of Storm Drainage Network-[Road 15]-[SW-9] | 7 | 2025-08-31 | 2025-09-07 | 2025-08-12 | 2025-08-19 | 13245.36 | 26
Catch Basin Sections |  | 31 | 2025-09-08 | 2025-10-14 | 2025-08-20 | 2025-09-25 | 61446.29 | 26
CO-R15.S09-SD-140 | Trench Excavation and Bedding Works for Catch Basins of Storm Drainage Network-[Road 15]-[SW-9] | 7 | 2025-09-08 | 2025-09-15 | 2025-08-20 | 2025-08-27 | 10241.12 | 26
CO-R15.S09-SD-150 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 15]-[SW-9] | 7 | 2025-09-16 | 2025-09-24 | 2025-08-28 | 2025-09-04 | 30723.14 | 26
CO-R15.S09-SD-160 | Testing Works for Catch Basins of Storm Drainage Network-[Road 15]-[SW-9] | 7 | 2025-09-25 | 2025-10-02 | 2025-09-06 | 2025-09-13 | 6827.34 | 26
CO-R15.S09-SD-170 | Trench Backfilling and Compaction Works for Catch Basins of Storm Drainage Network-[Road 15]-[SW-9] | 10 | 2025-10-04 | 2025-10-14 | 2025-09-14 | 2025-09-25 | 13654.68 | 26
Irrigation Network |  | 59 | 2025-10-15 | 2025-12-22 | 2025-09-27 | 2025-11-04 | 59192.11 | 1
Main Line Pipes |  | 59 | 2025-10-15 | 2025-12-22 | 2025-09-27 | 2025-11-04 | 59192.11 | 1
CO-R15.S09-IR-100 | Trench Excavation and Bedding Works for Main Lines of Irrigation Network-[Road 15]-[SW-9] | 7 | 2025-10-15 | 2025-10-22 | 2025-09-27 | 2025-10-04 | 10496.14 | 26
CO-R15.S09-IR-110 | Pipes Laying Works for Main Lines of Irrigation Network-[Road 15]-[SW-9] | 10 | 2025-11-11 | 2025-11-22 | 2025-10-05 | 2025-10-15 | 31488.41 | 10
CO-R15.S09-IR-120 | Installation Works for Main Line Valves of Irrigation Network-[Road 15]-[SW-9] | 7 | 2025-12-03 | 2025-12-10 | 2025-10-16 | 2025-10-23 | 11959.5 | 1
CO-R15.S09-IR-130 | Trench Backfilling and Compaction Works for Main Lines of Irrigation Network-[Road 15]-[SW-9] | 10 | 2025-12-11 | 2025-12-22 | 2025-10-25 | 2025-11-04 | 5248.07 | 1
Telecom Network |  | 160 | 2026-02-14 | 2026-08-26 | 2025-12-16 | 2026-08-08 | 42063.27 | -9
Ducts Works |  | 160 | 2026-02-14 | 2026-08-26 | 2025-12-16 | 2026-08-08 | 32662.5 | -16
CO-R15.S09-TE-100 | Trench Excavation and Bedding Works for Ducts of Telecom Network-[Road 15]-[SW-9] | 7 | 2026-02-14 | 2026-02-21 | 2025-12-16 | 2025-12-23 | 3283 | 116
CO-R15.S09-TE-110 | Pipes Laying Works for Ducts of Telecom Network-[Road 15]-[SW-9] | 7 | 2026-08-03 | 2026-08-10 | 2026-07-15 | 2026-07-22 | 19530.5 | -16
CO-R15.S09-TE-120 | Pouring Plain Concrete Above Ducts of Telecom Network-[Road 15]-[SW-9] | 7 | 2026-08-11 | 2026-08-18 | 2026-07-23 | 2026-07-30 | 3283 | -16
CO-R15.S09-TE-130 | Trench Backfilling and Compaction Works for Ducts of Telecom Network-[Road 15]-[SW-9] | 7 | 2026-08-19 | 2026-08-26 | 2026-08-01 | 2026-08-08 | 6566 | -16
Manholes Works |  | 21 | 2026-08-03 | 2026-08-26 | 2026-07-15 | 2026-08-08 | 9400.77 | -9
CO-R15.S09-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 15]-[SW-9] | 7 | 2026-08-03 | 2026-08-10 | 2026-07-15 | 2026-07-22 | 1256.92 | -16
CO-R15.S09-TE-150 | Installation Works for Manholes of Telecom Network-[Road 15]-[SW-9] | 7 | 2026-08-11 | 2026-08-18 | 2026-07-23 | 2026-07-30 | 6886.93 | -9
CO-R15.S09-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 15]-[SW-9] | 7 | 2026-08-19 | 2026-08-26 | 2026-08-01 | 2026-08-08 | 1256.92 | -9
Medium Voltage Network |  | 24 | 2026-08-23 | 2026-09-19 | 2026-08-04 | 2026-08-31 | 197909.64 | -16
Cabling Works |  | 24 | 2026-08-23 | 2026-09-19 | 2026-08-04 | 2026-08-31 | 197909.64 | -16
CO-R15.S09-MV-ML-250 | Trench Excavation and Bedding Works for Medium Voltage Network-[Road 15]-[SW-9] | 18 | 2026-08-23 | 2026-09-12 | 2026-08-04 | 2026-08-24 | 22775.27 | -16
CO-R15.S09-MV-ML-260 | Cable Laying Works for Medium Voltage Network-[Road 15]-[SW-9] | 18 | 2026-08-26 | 2026-09-15 | 2026-08-08 | 2026-08-27 | 122594.06 | -16
CO-R15.S09-MV-ML-270 | Trench Backfilling and Compaction Works for Medium Voltage Network-[Road 15]-[SW-9] | 18 | 2026-08-30 | 2026-09-19 | 2026-08-11 | 2026-08-31 | 52540.31 | -16
Road Works |  | 73 | 2026-09-02 | 2026-11-26 | 2026-08-15 | 2026-11-08 | 345776.12 | -16
Pre-Bituminous Construction |  | 54 | 2026-09-02 | 2026-11-04 | 2026-08-15 | 2026-10-17 | 219277.24 | -13
CO-R15.S09-RD-P-100 | Capping and Subgrade Layer for Road Works-[Road 15]-[SW-9] | 18 | 2026-09-02 | 2026-09-22 | 2026-08-15 | 2026-09-03 | 129249.01 | -3
CO-R15.S09-RD-P-110 | Aggregate Base Course Layer for Road Works-[Road 15]-[SW-9] | 18 | 2026-10-15 | 2026-11-04 | 2026-09-27 | 2026-10-17 | 90028.24 | -13
Pavement Works |  | 34 | 2026-10-19 | 2026-11-26 | 2026-09-30 | 2026-11-08 | 126498.88 | -16
CO-R15.S09-RD-P-120 | Fixing of Curbstone for Sidewalks Pavement-[Road 15]-[SW-9] | 18 | 2026-10-19 | 2026-11-08 | 2026-09-30 | 2026-10-20 | 73717.55 | -13
CO-R15.S09-RD-P-130 | Fixing of Interlock Tiles for Sidewalks Pavement-[Road 15]-[SW-9] | 12 | 2026-11-14 | 2026-11-26 | 2026-10-26 | 2026-11-08 | 52781.33 | -16
SW_10 |  | 475 | 01-Apr-25 A | 2026-11-26 | 2025-05-07 | 2026-11-08 | 1559787.35 | -16
Earthworks |  | 10 | 01-Apr-25 A | 12-Apr-25 A | 2025-05-07 | 2025-05-18 | 49403.66
Earthworks |  | 10 | 01-Apr-25 A | 12-Apr-25 A | 2025-05-07 | 2025-05-18 | 49403.66
CO-R15.S10-EW-100 | Roadway Excavation Works Upto Design Level for Earthworks-[Road 15]-[SW-10] | 10 | 01-Apr-25 A | 12-Apr-25 A | 2025-05-07 | 2025-05-18 | 49403.66
Sewage Network |  | 90 | 2025-05-13 | 2025-08-30 | 2025-06-02 | 2025-08-11 | 145313.38 | -16
Main Line Sections |  | 90 | 2025-05-13 | 2025-08-30 | 2025-06-02 | 2025-08-11 | 93424.03 | -16
CO-R15.S10-SW-100 | Trench Excavation and Bedding Works for Main Lines of Sewage Network-[Road 15]-[SW-10] | 12 | 2025-05-13 | 2025-05-26 | 2025-06-02 | 2025-06-19 | 20760.89 | 40
CO-R15.S10-SW-120 | Pipes Laying Works for Main Lines of Sewage Network-[Road 15]-[SW-10] | 12 | 2025-06-29 | 2025-07-12 | 2025-06-21 | 2025-07-03 | 62282.68 | 16
CO-R15.S10-SW-130 | Trench Backfilling and Compaction Works for Main Lines of Sewage Network-[Road 15]-[SW-10] | 10 | 2025-08-19 | 2025-08-30 | 2025-07-31 | 2025-08-11 | 10380.45 | -16
Manholes |  | 25 | 2025-06-29 | 2025-07-27 | 2025-06-21 | 2025-07-06 | 51889.36 | 13
CO-R15.S10-SW-160 | Excavation Works for Main Line Manholes of Sewage Network-[Road 15]-[SW-10] | 1 | 2025-06-29 | 2025-06-29 | 2025-06-21 | 2025-06-21 | 8648.23 | 25
CO-R15.S10-SW-170 | Installation RC Footing Works for Main Line Manholes of Sewage Network-[Road 15]-[SW-10] | 2 | 2025-07-13 | 2025-07-15 | 2025-06-22 | 2025-06-24 | 5765.48 | 13
CO-R15.S10-SW-180 | Install Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 15]-[SW-10] | 4 | 2025-07-16 | 2025-07-20 | 2025-06-24 | 2025-06-29 | 23061.94 | 13
CO-R15.S10-SW-190 | Pouring Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 15]-[SW-10] | 1 | 2025-07-21 | 2025-07-21 | 2025-06-29 | 2025-06-30 | 2882.74 | 13
CO-R15.S10-SW-200 | Backfilling Works for Main Line Manholes of Sewage Network-[Road 15]-[SW-10] | 4 | 2025-07-22 | 2025-07-26 | 2025-06-30 | 2025-07-05 | 8648.23 | 13
CO-R15.S10-SW-210 | Testing Works for Main Line Manholes of Sewage Network-[Road 15]-[SW-10] | 1 | 2025-07-27 | 2025-07-27 | 2025-07-05 | 2025-07-06 | 2882.74 | 13
Storm Drainage Network |  | 175 | 2025-08-23 | 2026-03-15 | 2025-08-04 | 2026-02-24 | 707031.77 | 169
Main Line Sections |  | 175 | 2025-08-23 | 2026-03-15 | 2025-08-04 | 2026-02-24 | 531471.21 | -12
CO-R15.S10-SD-100 | Trench Excavation and Bedding Works for Main Lines of Storm Drainage Network-[Road 15]-[SW-10] | 10 | 2025-08-23 | 2025-09-02 | 2025-08-04 | 2025-08-14 | 119487.92 | -16
CO-R15.S10-SD-120 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 15]-[SW-10] | 15 | 2025-09-03 | 2025-09-20 | 2025-08-16 | 2025-09-01 | 358463.75 | 49
CO-R15.S10-SD-130 | Trench Backfilling and Compaction Works for Main Lines of Storm Drainage Network-[Road 15]-[SW-10] | 15 | 2026-02-26 | 2026-03-15 | 2026-02-08 | 2026-02-24 | 53519.55 | -12
Manholes |  | 14 | 2025-09-03 | 2025-09-18 | 2025-08-16 | 2025-08-31 | 114114.27 | 66
CO-R15.S10-SD-180 | Trench Excavation and Bedding Works for Manholes of Storm Drainage Network-[Road 15]-[SW-10] | 1 | 2025-09-03 | 2025-09-03 | 2025-08-16 | 2025-08-16 | 18018.04 | 66
CO-R15.S10-SD-190 | Install RC Footing Works for Manholes of Storm Drainage Network-[Road 15]-[SW-10] | 1 | 2025-09-04 | 2025-09-04 | 2025-08-17 | 2025-08-17 | 6006.01 | 66
CO-R15.S10-SD-200 | Install RC Wall Rings & Slab Works for Manholes of Storm Drainage Network-[Road 15]-[SW-10] | 4 | 2025-09-06 | 2025-09-09 | 2025-08-18 | 2025-08-21 | 54054.13 | 66
CO-R15.S10-SD-210 | Testing Works for Manholes of Storm Drainage Network-[Road 15]-[SW-10] | 1 | 2025-09-10 | 2025-09-10 | 2025-08-23 | 2025-08-23 | 12012.03 | 66
CO-R15.S10-SD-220 | Backfilling Works for Manholes of Storm Drainage Network-[Road 15]-[SW-10] | 7 | 2025-09-11 | 2025-09-18 | 2025-08-24 | 2025-08-31 | 24024.06 | 66
Catch Basin Sections |  | 54 | 2025-09-20 | 2025-11-22 | 2025-09-01 | 2025-10-02 | 61446.29 | 266
CO-R15.S10-SD-140 | Trench Excavation and Bedding Works for Catch Basins of Storm Drainage Network-[Road 15]-[SW-10] | 7 | 2025-09-20 | 2025-09-28 | 2025-09-01 | 2025-09-08 | 10241.12 | 66
CO-R15.S10-SD-150 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 15]-[SW-10] | 7 | 2025-10-30 | 2025-11-06 | 2025-09-09 | 2025-09-16 | 30723.14 | 39
CO-R15.S10-SD-160 | Testing Works for Catch Basins of Storm Drainage Network-[Road 15]-[SW-10] | 4 | 2025-11-08 | 2025-11-11 | 2025-09-17 | 2025-09-21 | 6827.34 | 266
CO-R15.S10-SD-170 | Trench Backfilling and Compaction Works for Catch Basins of Storm Drainage Network-[Road 15]-[SW-10] | 10 | 2025-11-11 | 2025-11-22 | 2025-09-21 | 2025-10-02 | 13654.68 | 266
Street Lighting Network |  | 264 | 2025-05-13 | 2026-03-25 | 2025-06-02 | 2026-02-02 | 135363.16 | 132
Lighting Poles Works |  | 77 | 2025-12-23 | 2026-03-25 | 2025-11-05 | 2026-02-02 | 71656.5 | 49
CO-R15.S10-SL-100 | Foundation Excavation Works for Lighting Poles of Street Lighting Network-[Road 15]-[SW-10] | 12 | 2025-12-23 | 2026-01-05 | 2025-11-05 | 2025-11-18 | 2379.34 | 1
CO-R15.S10-SL-110 | Installation Works for Lighting Poles Foundation of Street Lighting Network-[Road 15]-[SW-10] | 12 | 2026-01-06 | 2026-01-19 | 2025-11-19 | 2025-12-02 | 9095.25 | 1
CO-R15.S10-SL-120 | Installation Works for Lighting Poles of Street Lighting Network-[Road 15]-[SW-10] | 18 | 2026-02-24 | 2026-03-16 | 2026-01-07 | 2026-01-27 | 26172.71 | 1
CO-R15.S10-SL-130 | Installation Works for Lighting Fixtures With Drop Wire of Street Lighting Network-[Road 15]-[SW-10] | 18 | 2026-03-02 | 2026-03-25 | 2026-01-13 | 2026-02-02 | 14974.5 | 49
CO-R15.S10-SL-210 | Backfilling Works for Lighting Poles of Street Lighting Network-[Road 15]-[SW-10] | 12 | 2026-03-02 | 2026-03-16 | 2026-01-13 | 2026-01-27 | 9517.35 | 1
CO-R15.S10-SL-200 | Testing Works for Lighting Poles of Street Lighting Network-[Road 15]-[SW-10] | 5 | 2026-03-16 | 2026-03-25 | 2026-01-27 | 2026-02-02 | 9517.35 | 50
Cabling Works |  | 30 | 2026-01-20 | 2026-02-23 | 2025-12-03 | 2026-01-06 | 46881.24 | 1
CO-R15.S10-SL-140 | Trench Excavation and Bedding Works for Street Lighting Network-[Road 15]-[SW-10] | 10 | 2026-01-20 | 2026-01-31 | 2025-12-03 | 2025-12-14 | 0 | 1
CO-R15.S10-SL-150 | Cable Laying Works for Street Lighting Network-[Road 15]-[SW-10] | 10 | 2026-02-01 | 2026-02-11 | 2025-12-15 | 2025-12-25 | 43532.58 | 1
CO-R15.S10-SL-160 | Trench Backfilling and Compaction Works for Street Lighting Network-[Road 15]-[SW-10] | 10 | 2026-02-12 | 2026-02-23 | 2025-12-27 | 2026-01-06 | 3348.66 | 1
Distrubution Panel Boards |  | 24 | 2025-05-13 | 2025-06-14 | 2025-06-02 | 2025-07-03 | 16825.42 | 372
CO-R15.S10-SL-170 | Foundation Excavation Works For Panel Boards of Street Lighting Network-[Road 15]-[SW-10] | 18 | 2025-05-13 | 2025-06-02 | 2025-06-02 | 2025-06-26 | 0 | 372
CO-R15.S10-SL-180 | Installation Works for Panel Board Concrete Foundations of Street Lighting Network-[Road 15]-[SW-10] | 18 | 2025-05-17 | 2025-06-10 | 2025-06-10 | 2025-06-30 | 0 | 372
CO-R15.S10-SL-220 | A wall of concrete blocks to install the KWH meter of Street Lighting Network-[Road 15]-[SW-10] | 18 | 2025-05-17 | 2025-06-10 | 2025-06-10 | 2025-06-30 | 16825.42 | 375
CO-R15.S10-SL-190 | Installation Works for Lighting Panel Boards of Street Lighting Network-[Road 15]-[SW-10] | 18 | 2025-05-20 | 2025-06-14 | 2025-06-14 | 2025-07-03 | 0 | 372
Potable Water Network |  | 27 | 2026-03-16 | 2026-04-19 | 2026-02-25 | 2026-03-31 | 134835.99 | 109
Main Line Sections |  | 27 | 2026-03-16 | 2026-04-19 | 2026-02-25 | 2026-03-31 | 88651.55 | 109
CO-R15.S10-PW-100 | Trench Excavation and Bedding Works for Main Lines of Potable Water Network-[Road 15]-[SW-10] | 6 | 2026-03-16 | 2026-03-25 | 2026-02-25 | 2026-03-03 | 19700.35 | 109
CO-R15.S10-PW-110 | Pipes Laying and accessories for Main Lines of Potable Water Network-[Road 15]-[SW-10] | 6 | 2026-03-26 | 2026-04-01 | 2026-03-04 | 2026-03-10 | 49250.86 | 109
CO-R15.S10-PW-130 | Trench Backfilling and Compaction Works for Main Lines of Potable Water Network-[Road 15]-[SW-10] | 6 | 2026-04-13 | 2026-04-19 | 2026-03-25 | 2026-03-31 | 19700.35 | 109
Valve Chamber |  | 6 | 2026-04-02 | 2026-04-08 | 2026-03-11 | 2026-03-17 | 15887.04 | 118
CO-R15.S10-PW-210 | Installation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 15]-[SW-10] | 6 | 2026-04-02 | 2026-04-08 | 2026-03-11 | 2026-03-17 | 15887.04 | 118
Fire Hydrant |  | 18 | 2026-03-30 | 2026-04-19 | 2026-03-08 | 2026-03-31 | 30297.4 | 109
CO-R15.S10-PW-140 | Excavation Works for Fire Hydrants of Potable Water Network-[Road 15]-[SW-10] | 6 | 2026-03-30 | 2026-04-05 | 2026-03-08 | 2026-03-14 | 4544.61 | 109
CO-R15.S10-PW-150 | Installation Works for Fire Hydrant of Potable Water Network-[Road 15]-[SW-10] | 6 | 2026-04-06 | 2026-04-12 | 2026-03-15 | 2026-03-24 | 19693.31 | 109
CO-R15.S10-PW-160 | Trench Backfilling and Compaction Works for Fire Hydrants of Potable Water Network-[Road 15]-[SW-10] | 6 | 2026-04-13 | 2026-04-19 | 2026-03-25 | 2026-03-31 | 6059.48 | 109
Telecom Network |  | 160 | 2026-02-22 | 2026-09-03 | 2026-01-05 | 2026-08-16 | 42063.27 | -16
Ducts Works |  | 160 | 2026-02-22 | 2026-09-03 | 2026-01-05 | 2026-08-16 | 32662.5 | -16
CO-R15.S10-TE-100 | Trench Excavation and Bedding Works for Ducts of Telecom Network-[Road 15]-[SW-10] | 7 | 2026-02-22 | 2026-03-01 | 2026-01-05 | 2026-01-12 | 3283 | 36
CO-R15.S10-TE-110 | Pipes Laying Works for Ducts of Telecom Network-[Road 15]-[SW-10] | 7 | 2026-08-11 | 2026-08-18 | 2026-07-23 | 2026-07-30 | 19530.5 | -16
CO-R15.S10-TE-120 | Pouring Plain Concrete Above Ducts of Telecom Network-[Road 15]-[SW-10] | 7 | 2026-08-19 | 2026-08-26 | 2026-08-01 | 2026-08-08 | 3283 | -16
CO-R15.S10-TE-130 | Trench Backfilling and Compaction Works for Ducts of Telecom Network-[Road 15]-[SW-10] | 7 | 2026-08-27 | 2026-09-03 | 2026-08-09 | 2026-08-16 | 6566 | -16
Manholes Works |  | 21 | 2026-08-11 | 2026-09-03 | 2026-07-23 | 2026-08-16 | 9400.77 | -16
CO-R15.S10-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 15]-[SW-10] | 7 | 2026-08-11 | 2026-08-18 | 2026-07-23 | 2026-07-30 | 1256.92 | -16
CO-R15.S10-TE-150 | Installation Works for Manholes of Telecom Network-[Road 15]-[SW-10] | 7 | 2026-08-19 | 2026-08-26 | 2026-08-01 | 2026-08-08 | 6886.93 | -16
CO-R15.S10-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 15]-[SW-10] | 7 | 2026-08-27 | 2026-09-03 | 2026-08-09 | 2026-08-16 | 1256.92 | -16
Road Works |  | 71 | 2026-09-05 | 2026-11-26 | 2026-08-17 | 2026-11-08 | 345776.12 | -16
Pre-Bituminous Construction |  | 50 | 2026-09-05 | 2026-11-02 | 2026-08-17 | 2026-10-14 | 219277.24 | -11
CO-R15.S10-RD-P-100 | Capping and Subgrade Layer for Road Works-[Road 15]-[SW-10] | 18 | 2026-09-05 | 2026-09-26 | 2026-08-17 | 2026-09-06 | 129249.01 | -5
CO-R15.S10-RD-P-110 | Aggregate Base Course Layer for Road Works-[Road 15]-[SW-10] | 18 | 2026-10-13 | 2026-11-02 | 2026-09-24 | 2026-10-14 | 90028.24 | -11
Pavement Works |  | 36 | 2026-10-17 | 2026-11-26 | 2026-09-28 | 2026-11-08 | 126498.88 | -16
CO-R15.S10-RD-P-120 | Fixing of Curbstone for Sidewalks Pavement-[Road 15]-[SW-10] | 18 | 2026-10-17 | 2026-11-05 | 2026-09-28 | 2026-10-18 | 73717.55 | -11
CO-R15.S10-RD-P-130 | Fixing of Interlock Tiles for Sidewalks Pavement-[Road 15]-[SW-10] | 10 | 2026-11-16 | 2026-11-26 | 2026-10-28 | 2026-11-08 | 52781.33 | -16
Road 16 Local 1 ( 527 LM ) |  | 515 | 27-Mar-25 A | 2026-12-08 | 2025-03-29 | 2026-11-19 | 2501958.03 | -16
SW_11 |  | 512 | 27-Mar-25 A | 2026-12-05 | 2025-03-29 | 2026-11-16 | 1248387.13 | -13
Earthworks |  | 24 | 27-Mar-25 A | 19-Apr-25 A | 2025-03-29 | 2025-04-29 | 148998.64
Earthworks |  | 24 | 27-Mar-25 A | 19-Apr-25 A | 2025-03-29 | 2025-04-29 | 148998.64
CO-R16.S11-EW-100 | Roadway Excavation Works Upto Design Level for Earthworks-[Road 16]-[SW-11] | 10 | 27-Mar-25 A | 12-Apr-25 A | 2025-03-29 | 2025-04-13 | 47086.7
CO-R16.S11-EW-110 | Embankments Works Upto Design Level for Earthworks-[Road 16]-[SW-11] | 12 | 27-Mar-25 A | 19-Apr-25 A | 2025-04-16 | 2025-04-29 | 101911.93
Sewage Network |  | 34 | 2025-06-15 | 2025-07-23 | 2025-05-07 | 2025-07-07 | 144078.76 | -14
Main Line Sections |  | 34 | 2025-06-15 | 2025-07-23 | 2025-05-07 | 2025-07-07 | 62331.86 | -14
CO-R16.S11-SW-100 | Trench Excavation and Bedding Works for Main Lines of Sewage Network-[Road 16]-[SW-11] | 12 | 2025-06-15 | 2025-06-28 | 2025-05-07 | 2025-05-20 | 13851.53 | -16
CO-R16.S11-SW-120 | Pipes Laying Works for Main Lines of Sewage Network-[Road 16]-[SW-11] | 12 | 2025-06-29 | 2025-07-12 | 2025-05-21 | 2025-06-03 | 41554.58 | -14
CO-R16.S11-SW-130 | Trench Backfilling and Compaction Works for Main Lines of Sewage Network-[Road 16]-[SW-11] | 10 | 2025-07-13 | 2025-07-23 | 2025-06-26 | 2025-07-07 | 6925.76 | -14
Manholes |  | 13 | 2025-06-29 | 2025-07-13 | 2025-05-21 | 2025-06-04 | 81746.9 | -5
CO-R16.S11-SW-160 | Excavation Works for Main Line Manholes of Sewage Network-[Road 16]-[SW-11] | 1 | 2025-06-29 | 2025-06-29 | 2025-05-21 | 2025-05-21 | 13624.48 | -5
CO-R16.S11-SW-170 | Installation RC Footing Works for Main Line Manholes of Sewage Network-[Road 16]-[SW-11] | 2 | 2025-06-30 | 2025-07-01 | 2025-05-22 | 2025-05-24 | 9082.99 | -5
CO-R16.S11-SW-180 | Install Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 16]-[SW-11] | 4 | 2025-07-02 | 2025-07-06 | 2025-05-25 | 2025-05-28 | 36331.96 | -5
CO-R16.S11-SW-190 | Pouring Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 16]-[SW-11] | 1 | 2025-07-07 | 2025-07-07 | 2025-05-29 | 2025-05-29 | 4541.49 | -5
CO-R16.S11-SW-200 | Backfilling Works for Main Line Manholes of Sewage Network-[Road 16]-[SW-11] | 4 | 2025-07-08 | 2025-07-12 | 2025-05-31 | 2025-06-03 | 13624.48 | -5
CO-R16.S11-SW-210 | Testing Works for Main Line Manholes of Sewage Network-[Road 16]-[SW-11] | 1 | 2025-07-13 | 2025-07-13 | 2025-06-04 | 2025-06-04 | 4541.49 | -5
Storm Drainage Network |  | 218 | 2025-07-16 | 2026-03-31 | 2025-06-30 | 2026-03-09 | 324824.92 | 131
Main Line Sections |  | 218 | 2025-07-16 | 2026-03-31 | 2025-06-30 | 2026-03-09 | 212384.98 | 131
CO-R16.S11-SD-100 | Trench Excavation and Bedding Works for Main Lines of Storm Drainage Network-[Road 16]-[SW-11] | 10 | 2025-07-16 | 2025-07-27 | 2025-06-30 | 2025-07-10 | 47196.66 | 199
CO-R16.S11-SD-120 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 16]-[SW-11] | 15 | 2025-07-28 | 2025-08-13 | 2025-07-12 | 2025-07-28 | 141589.99 | 199
CO-R16.S11-SD-130 | Trench Backfilling and Compaction Works for Main Lines of Storm Drainage Network-[Road 16]-[SW-11] | 15 | 2026-03-11 | 2026-03-31 | 2026-02-21 | 2026-03-09 | 23598.33 | 131
Manholes |  | 14 | 2025-07-28 | 2025-08-12 | 2025-07-12 | 2025-07-27 | 53875.91 | 199
CO-R16.S11-SD-180 | Trench Excavation and Bedding Works for Manholes of Storm Drainage Network-[Road 16]-[SW-11] | 1 | 2025-07-28 | 2025-07-28 | 2025-07-12 | 2025-07-12 | 8506.72 | 199
CO-R16.S11-SD-190 | Install RC Footing Works for Manholes of Storm Drainage Network-[Road 16]-[SW-11] | 1 | 2025-07-29 | 2025-07-29 | 2025-07-13 | 2025-07-13 | 2835.57 | 199
CO-R16.S11-SD-200 | Install RC Wall Rings & Slab Works for Manholes of Storm Drainage Network-[Road 16]-[SW-11] | 4 | 2025-07-30 | 2025-08-03 | 2025-07-14 | 2025-07-17 | 25520.17 | 199
CO-R16.S11-SD-210 | Testing Works for Manholes of Storm Drainage Network-[Road 16]-[SW-11] | 1 | 2025-08-04 | 2025-08-04 | 2025-07-19 | 2025-07-19 | 5671.15 | 199
CO-R16.S11-SD-220 | Backfilling Works for Manholes of Storm Drainage Network-[Road 16]-[SW-11] | 7 | 2025-08-05 | 2025-08-12 | 2025-07-20 | 2025-07-27 | 11342.3 | 199
Catch Basin Sections |  | 53 | 2025-08-13 | 2025-10-14 | 2025-07-28 | 2025-08-28 | 58564.03 | 174
CO-R16.S11-SD-140 | Trench Excavation and Bedding Works for Catch Basins of Storm Drainage Network-[Road 16]-[SW-11] | 7 | 2025-08-13 | 2025-08-20 | 2025-07-28 | 2025-08-04 | 9760.77 | 199
CO-R16.S11-SD-150 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 16]-[SW-11] | 7 | 2025-09-20 | 2025-09-28 | 2025-08-05 | 2025-08-12 | 29282.02 | 174
CO-R16.S11-SD-160 | Testing Works for Catch Basins of Storm Drainage Network-[Road 16]-[SW-11] | 4 | 2025-09-29 | 2025-10-02 | 2025-08-13 | 2025-08-17 | 6507.08 | 174
CO-R16.S11-SD-170 | Trench Backfilling and Compaction Works for Catch Basins of Storm Drainage Network-[Road 16]-[SW-11] | 10 | 2025-10-04 | 2025-10-14 | 2025-08-18 | 2025-08-28 | 13014.16 | 174
Irrigation Network |  | 43 | 2025-10-15 | 2025-12-03 | 2025-08-30 | 2025-10-08 | 71176.08 | 165
Main Line Pipes |  | 43 | 2025-10-15 | 2025-12-03 | 2025-08-30 | 2025-10-08 | 71176.08 | 165
CO-R16.S11-IR-100 | Trench Excavation and Bedding Works for Main Lines of Irrigation Network-[Road 16]-[SW-11] | 7 | 2025-10-15 | 2025-10-22 | 2025-08-30 | 2025-09-06 | 10003.95 | 174
CO-R16.S11-IR-110 | Pipes Laying Works for Main Lines of Irrigation Network-[Road 16]-[SW-11] | 10 | 2025-10-23 | 2025-11-03 | 2025-09-07 | 2025-09-17 | 30011.94 | 174
CO-R16.S11-IR-120 | Installation Works for Main Line Valves of Irrigation Network-[Road 16]-[SW-11] | 7 | 2025-11-15 | 2025-11-22 | 2025-09-18 | 2025-09-27 | 26158.21 | 165
CO-R16.S11-IR-130 | Trench Backfilling and Compaction Works for Main Lines of Irrigation Network-[Road 16]-[SW-11] | 10 | 2025-11-23 | 2025-12-03 | 2025-09-28 | 2025-10-08 | 5001.98 | 165
Telecom Network |  | 186 | 2026-01-22 | 2026-09-03 | 2025-11-24 | 2026-08-16 | 40723.27 | -9
Ducts Works |  | 186 | 2026-01-22 | 2026-09-03 | 2025-11-24 | 2026-08-16 | 31322.5 | -9
CO-R16.S11-TE-100 | Trench Excavation and Bedding Works for Ducts of Telecom Network-[Road 16]-[SW-11] | 12 | 2026-01-22 | 2026-02-04 | 2025-11-24 | 2025-12-07 | 3149 | 116
CO-R16.S11-TE-110 | Pipes Laying Works for Ducts of Telecom Network-[Road 16]-[SW-11] | 7 | 2026-08-11 | 2026-08-18 | 2026-07-23 | 2026-07-30 | 18726.5 | -9
CO-R16.S11-TE-120 | Pouring Plain Concrete Above Ducts of Telecom Network-[Road 16]-[SW-11] | 7 | 2026-08-19 | 2026-08-26 | 2026-08-01 | 2026-08-08 | 3149 | -9
CO-R16.S11-TE-130 | Trench Backfilling and Compaction Works for Ducts of Telecom Network-[Road 16]-[SW-11] | 7 | 2026-08-27 | 2026-09-03 | 2026-08-09 | 2026-08-16 | 6298 | -9
Manholes Works |  | 21 | 2026-08-11 | 2026-09-03 | 2026-07-23 | 2026-08-16 | 9400.77 | -9
CO-R16.S11-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 16]-[SW-11] | 7 | 2026-08-11 | 2026-08-18 | 2026-07-23 | 2026-07-30 | 1256.92 | -16
CO-R16.S11-TE-150 | Installation Works for Manholes of Telecom Network-[Road 16]-[SW-11] | 7 | 2026-08-19 | 2026-08-26 | 2026-08-01 | 2026-08-08 | 6886.93 | -9
CO-R16.S11-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 16]-[SW-11] | 7 | 2026-08-27 | 2026-09-03 | 2026-08-09 | 2026-08-16 | 1256.92 | -9
Medium Voltage Network |  | 24 | 2026-09-13 | 2026-10-11 | 2026-08-25 | 2026-09-21 | 188963.88 | -16
Cabling Works |  | 24 | 2026-09-13 | 2026-10-11 | 2026-08-25 | 2026-09-21 | 188963.88 | -16
CO-R16.S11-MV-ML-280 | Trench Excavation and Bedding Works for Medium Voltage Network-[Road 16]-[SW-11] | 18 | 2026-09-13 | 2026-10-04 | 2026-08-25 | 2026-09-14 | 21708.23 | -16
CO-R16.S11-MV-ML-290 | Cable Laying Works for Medium Voltage Network-[Road 16]-[SW-11] | 18 | 2026-09-16 | 2026-10-07 | 2026-08-29 | 2026-09-17 | 117078.96 | -16
CO-R16.S11-MV-ML-300 | Trench Backfilling and Compaction Works for Medium Voltage Network-[Road 16]-[SW-11] | 18 | 2026-09-20 | 2026-10-11 | 2026-09-01 | 2026-09-21 | 50176.7 | -16
Road Works |  | 62 | 2026-09-24 | 2026-12-05 | 2026-09-05 | 2026-11-16 | 329621.59 | -13
Pre-Bituminous Construction |  | 54 | 2026-09-24 | 2026-11-25 | 2026-09-05 | 2026-11-07 | 208993.78 | -13
CO-R16.S11-RD-P-100 | Capping and Subgrade Layer for Road Works-[Road 16]-[SW-11] | 18 | 2026-09-24 | 2026-10-14 | 2026-09-05 | 2026-09-26 | 123187.67 | -9
CO-R16.S11-RD-P-110 | Aggregate Base Course Layer for Road Works-[Road 16]-[SW-11] | 18 | 2026-11-05 | 2026-11-25 | 2026-10-18 | 2026-11-07 | 85806.11 | -13
Pavement Works |  | 23 | 2026-11-09 | 2026-12-05 | 2026-10-21 | 2026-11-16 | 120627.81 | -13
CO-R16.S11-RD-P-120 | Fixing of Curbstone for Sidewalks Pavement-[Road 16]-[SW-11] | 18 | 2026-11-09 | 2026-11-29 | 2026-10-21 | 2026-11-10 | 70259.95 | -13
CO-R16.S11-RD-P-130 | Fixing of Interlock Tiles for Sidewalks Pavement-[Road 16]-[SW-11] | 10 | 2026-11-24 | 2026-12-05 | 2026-11-05 | 2026-11-16 | 50367.85 | -13
SW_12 |  | 505 | 27-Mar-25 A | 2026-12-08 | 2025-04-14 | 2026-11-19 | 1253570.89 | -16
Earthworks |  | 22 | 27-Mar-25 A | 20-Apr-25 A | 2025-04-14 | 2025-05-08 | 148998.64
Earthworks |  | 22 | 27-Mar-25 A | 20-Apr-25 A | 2025-04-14 | 2025-05-08 | 148998.64
CO-R16.S12-EW-100 | Roadway Excavation Works Upto Design Level for Earthworks-[Road 16]-[SW-12] | 10 | 27-Mar-25 A | 12-Apr-25 A | 2025-04-14 | 2025-04-24 | 47086.7
CO-R16.S12-EW-110 | Embankments Works Upto Design Level for Earthworks-[Road 16]-[SW-12] | 12 | 27-Mar-25 A | 20-Apr-25 A | 2025-04-26 | 2025-05-08 | 101911.93
Sewage Network |  | 34 | 2025-06-29 | 2025-08-06 | 2025-05-21 | 2025-07-19 | 116281.67 | -16
Main Line Sections |  | 34 | 2025-06-29 | 2025-08-06 | 2025-05-21 | 2025-07-19 | 71581.88 | -16
CO-R16.S12-SW-100 | Trench Excavation and Bedding Works for Main Lines of Sewage Network-[Road 16]-[SW-12] | 12 | 2025-06-29 | 2025-07-12 | 2025-05-21 | 2025-06-03 | 15907.09 | -16
CO-R16.S12-SW-120 | Pipes Laying Works for Main Lines of Sewage Network-[Road 16]-[SW-12] | 12 | 2025-07-13 | 2025-07-26 | 2025-06-04 | 2025-06-22 | 47721.26 | -16
CO-R16.S12-SW-130 | Trench Backfilling and Compaction Works for Main Lines of Sewage Network-[Road 16]-[SW-12] | 10 | 2025-07-27 | 2025-08-06 | 2025-07-08 | 2025-07-19 | 7953.54 | -16
Manholes |  | 13 | 2025-07-13 | 2025-07-27 | 2025-06-04 | 2025-06-23 | 44699.79 | -7
CO-R16.S12-SW-160 | Excavation Works for Main Line Manholes of Sewage Network-[Road 16]-[SW-12] | 1 | 2025-07-13 | 2025-07-13 | 2025-06-04 | 2025-06-04 | 7449.96 | -7
CO-R16.S12-SW-170 | Installation RC Footing Works for Main Line Manholes of Sewage Network-[Road 16]-[SW-12] | 2 | 2025-07-14 | 2025-07-15 | 2025-06-10 | 2025-06-11 | 4966.64 | -7
CO-R16.S12-SW-180 | Install Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 16]-[SW-12] | 4 | 2025-07-16 | 2025-07-20 | 2025-06-12 | 2025-06-16 | 19866.57 | -7
CO-R16.S12-SW-190 | Pouring Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 16]-[SW-12] | 1 | 2025-07-21 | 2025-07-21 | 2025-06-17 | 2025-06-17 | 2483.32 | -7
CO-R16.S12-SW-200 | Backfilling Works for Main Line Manholes of Sewage Network-[Road 16]-[SW-12] | 4 | 2025-07-22 | 2025-07-26 | 2025-06-18 | 2025-06-22 | 7449.96 | -7
CO-R16.S12-SW-210 | Testing Works for Main Line Manholes of Sewage Network-[Road 16]-[SW-12] | 1 | 2025-07-27 | 2025-07-27 | 2025-06-23 | 2025-06-23 | 2483.32 | -7
Storm Drainage Network |  | 210 | 2025-07-30 | 2026-04-05 | 2025-07-12 | 2026-03-14 | 489301.02 | 172
Main Line Sections |  | 210 | 2025-07-30 | 2026-04-05 | 2025-07-12 | 2026-03-14 | 376861.09 | -12
CO-R16.S12-SD-100 | Trench Excavation and Bedding Works for Main Lines of Storm Drainage Network-[Road 16]-[SW-12] | 10 | 2025-07-30 | 2025-08-10 | 2025-07-12 | 2025-07-22 | 83746.91 | 158
CO-R16.S12-SD-120 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 16]-[SW-12] | 15 | 2025-08-11 | 2025-08-27 | 2025-07-23 | 2025-08-09 | 251240.73 | 158
CO-R16.S12-SD-130 | Trench Backfilling and Compaction Works for Main Lines of Storm Drainage Network-[Road 16]-[SW-12] | 15 | 2026-03-16 | 2026-04-05 | 2026-02-25 | 2026-03-14 | 41873.45 | -12
Manholes |  | 14 | 2025-08-11 | 2025-08-26 | 2025-07-23 | 2025-08-07 | 53875.91 | 174
CO-R16.S12-SD-180 | Trench Excavation and Bedding Works for Manholes of Storm Drainage Network-[Road 16]-[SW-12] | 1 | 2025-08-11 | 2025-08-11 | 2025-07-23 | 2025-07-23 | 8506.72 | 174
CO-R16.S12-SD-190 | Install RC Footing Works for Manholes of Storm Drainage Network-[Road 16]-[SW-12] | 1 | 2025-08-12 | 2025-08-12 | 2025-07-24 | 2025-07-24 | 2835.57 | 174
CO-R16.S12-SD-200 | Install RC Wall Rings & Slab Works for Manholes of Storm Drainage Network-[Road 16]-[SW-12] | 4 | 2025-08-13 | 2025-08-17 | 2025-07-26 | 2025-07-29 | 25520.17 | 174
CO-R16.S12-SD-210 | Testing Works for Manholes of Storm Drainage Network-[Road 16]-[SW-12] | 1 | 2025-08-18 | 2025-08-18 | 2025-07-30 | 2025-07-30 | 5671.15 | 174
CO-R16.S12-SD-220 | Backfilling Works for Manholes of Storm Drainage Network-[Road 16]-[SW-12] | 7 | 2025-08-19 | 2025-08-26 | 2025-07-31 | 2025-08-07 | 11342.3 | 174
Catch Basin Sections |  | 49 | 2025-08-27 | 2025-10-23 | 2025-08-09 | 2025-09-09 | 58564.03 | 309
CO-R16.S12-SD-140 | Trench Excavation and Bedding Works for Catch Basins of Storm Drainage Network-[Road 16]-[SW-12] | 7 | 2025-08-27 | 2025-09-03 | 2025-08-09 | 2025-08-16 | 9760.77 | 330
CO-R16.S12-SD-150 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 16]-[SW-12] | 7 | 2025-09-30 | 2025-10-07 | 2025-08-17 | 2025-08-24 | 29282.02 | 309
CO-R16.S12-SD-160 | Testing Works for Catch Basins of Storm Drainage Network-[Road 16]-[SW-12] | 4 | 2025-10-08 | 2025-10-12 | 2025-08-25 | 2025-08-28 | 6507.08 | 309
CO-R16.S12-SD-170 | Trench Backfilling and Compaction Works for Catch Basins of Storm Drainage Network-[Road 16]-[SW-12] | 10 | 2025-10-13 | 2025-10-23 | 2025-08-30 | 2025-09-09 | 13014.16 | 309
Potable Water Network |  | 27 | 2026-04-06 | 2026-05-06 | 2026-03-15 | 2026-04-18 | 128644.71 | 106
Main Line Sections |  | 18 | 2026-04-06 | 2026-04-26 | 2026-03-15 | 2026-04-07 | 85108.11 | 115
CO-R16.S12-PW-100 | Trench Excavation and Bedding Works for Main Lines of Potable Water Network-[Road 16]-[SW-12] | 6 | 2026-04-06 | 2026-04-12 | 2026-03-15 | 2026-03-24 | 18912.91 | 106
CO-R16.S12-PW-110 | Pipes Laying and accessories for Main Lines of Potable Water Network-[Road 16]-[SW-12] | 6 | 2026-04-13 | 2026-04-19 | 2026-03-25 | 2026-03-31 | 47282.28 | 106
CO-R16.S12-PW-130 | Trench Backfilling and Compaction Works for Main Lines of Potable Water Network-[Road 16]-[SW-12] | 6 | 2026-04-20 | 2026-04-26 | 2026-04-01 | 2026-04-07 | 18912.91 | 115
Valve Chamber |  | 6 | 2026-04-20 | 2026-04-26 | 2026-04-01 | 2026-04-07 | 13239.2 | 115
CO-R16.S12-PW-210 | Installation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 16]-[SW-12] | 6 | 2026-04-20 | 2026-04-26 | 2026-04-01 | 2026-04-07 | 13239.2 | 115
Fire Hydrant |  | 18 | 2026-04-16 | 2026-05-06 | 2026-03-29 | 2026-04-18 | 30297.4 | 106
CO-R16.S12-PW-140 | Excavation Works for Fire Hydrants of Potable Water Network-[Road 16]-[SW-12] | 6 | 2026-04-16 | 2026-04-22 | 2026-03-29 | 2026-04-04 | 4544.61 | 106
CO-R16.S12-PW-150 | Installation Works for Fire Hydrant of Potable Water Network-[Road 16]-[SW-12] | 6 | 2026-04-23 | 2026-04-29 | 2026-04-05 | 2026-04-11 | 19693.31 | 106
CO-R16.S12-PW-160 | Trench Backfilling and Compaction Works for Fire Hydrants of Potable Water Network-[Road 16]-[SW-12] | 6 | 2026-04-30 | 2026-05-06 | 2026-04-12 | 2026-04-18 | 6059.48 | 106
Telecom Network |  | 181 | 2026-02-05 | 2026-09-12 | 2025-12-08 | 2026-08-24 | 40723.27 | -16
Ducts Works |  | 181 | 2026-02-05 | 2026-09-12 | 2025-12-08 | 2026-08-24 | 31322.5 | -16
CO-R16.S12-TE-100 | Trench Excavation and Bedding Works for Ducts of Telecom Network-[Road 16]-[SW-12] | 7 | 2026-02-05 | 2026-02-12 | 2025-12-08 | 2025-12-15 | 3149 | 116
CO-R16.S12-TE-110 | Pipes Laying Works for Ducts of Telecom Network-[Road 16]-[SW-12] | 7 | 2026-08-19 | 2026-08-26 | 2026-08-01 | 2026-08-08 | 18726.5 | -16
CO-R16.S12-TE-120 | Pouring Plain Concrete Above Ducts of Telecom Network-[Road 16]-[SW-12] | 7 | 2026-08-27 | 2026-09-03 | 2026-08-09 | 2026-08-16 | 3149 | -16
CO-R16.S12-TE-130 | Trench Backfilling and Compaction Works for Ducts of Telecom Network-[Road 16]-[SW-12] | 7 | 2026-09-05 | 2026-09-12 | 2026-08-17 | 2026-08-24 | 6298 | -16
Manholes Works |  | 21 | 2026-08-19 | 2026-09-12 | 2026-08-01 | 2026-08-24 | 9400.77 | -16
CO-R16.S12-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 16]-[SW-12] | 7 | 2026-08-19 | 2026-08-26 | 2026-08-01 | 2026-08-08 | 1256.92 | -16
CO-R16.S12-TE-150 | Installation Works for Manholes of Telecom Network-[Road 16]-[SW-12] | 7 | 2026-08-27 | 2026-09-03 | 2026-08-09 | 2026-08-16 | 6886.93 | -16
CO-R16.S12-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 16]-[SW-12] | 7 | 2026-09-05 | 2026-09-12 | 2026-08-17 | 2026-08-24 | 1256.92 | -16
Road Works |  | 74 | 2026-09-13 | 2026-12-08 | 2026-08-25 | 2026-11-19 | 329621.59 | -16
Pre-Bituminous Construction |  | 61 | 2026-09-13 | 2026-11-23 | 2026-08-25 | 2026-11-04 | 208993.78 | -11
CO-R16.S12-RD-P-100 | Capping and Subgrade Layer for Road Works-[Road 16]-[SW-12] | 18 | 2026-09-13 | 2026-10-04 | 2026-08-25 | 2026-09-14 | 123187.67 | 0
CO-R16.S12-RD-P-110 | Aggregate Base Course Layer for Road Works-[Road 16]-[SW-12] | 18 | 2026-11-03 | 2026-11-23 | 2026-10-15 | 2026-11-04 | 85806.11 | -11
Pavement Works |  | 28 | 2026-11-07 | 2026-12-08 | 2026-10-19 | 2026-11-19 | 120627.81 | -16
CO-R16.S12-RD-P-120 | Fixing of Curbstone for Sidewalks Pavement-[Road 16]-[SW-12] | 18 | 2026-11-07 | 2026-11-26 | 2026-10-19 | 2026-11-08 | 70259.95 | -11
CO-R16.S12-RD-P-130 | Fixing of Interlock Tiles for Sidewalks Pavement-[Road 16]-[SW-12] | 10 | 2026-11-28 | 2026-12-08 | 2026-11-09 | 2026-11-19 | 50367.85 | -16
Road 17 Local 1 ( 500 LM ) |  | 545 | 05-Mar-25 A | 2026-12-20 | 2025-03-05 | 2026-12-01 | 2535131.81 | -16
SW_13 |  | 544 | 05-Mar-25 A | 2026-12-19 | 2025-03-05 | 2026-11-30 | 1227494.74 | -15
Earthworks |  | 22 | 05-Mar-25 A | 20-Apr-25 A | 2025-03-05 | 2025-04-03 | 141667.06
Earthworks |  | 22 | 05-Mar-25 A | 20-Apr-25 A | 2025-03-05 | 2025-04-03 | 141667.06
CO-R17.S13-EW-100 | Roadway Excavation Works Upto Design Level for Earthworks-[Road 17]-[SW-13] | 10 | 05-Mar-25 A | 08-Apr-25 A | 2025-03-05 | 2025-03-16 | 44769.75
CO-R17.S13-EW-110 | Embankments Works Upto Design Level for Earthworks-[Road 17]-[SW-13] | 12 | 27-Mar-25 A | 20-Apr-25 A | 2025-03-17 | 2025-04-03 | 96897.3
Sewage Network |  | 43 | 07-May-25 A | 2025-06-30 | 2025-04-09 | 2025-06-14 | 163334.76 | -14
Main Line Sections |  | 43 | 07-May-25 A | 2025-06-30 | 2025-04-09 | 2025-06-14 | 71955.54 | -14
CO-R17.S13-SW-100 | Trench Excavation and Bedding Works for Main Lines of Sewage Network-[Road 17]-[SW-13] | 12 | 07-May-25 A | 2025-05-26 | 2025-04-09 | 2025-04-22 | 15990.12 | -16
CO-R17.S13-SW-120 | Pipes Laying Works for Main Lines of Sewage Network-[Road 17]-[SW-13] | 12 | 2025-05-27 | 2025-06-14 | 2025-04-30 | 2025-05-13 | 47970.36 | -10
CO-R17.S13-SW-130 | Trench Backfilling and Compaction Works for Main Lines of Sewage Network-[Road 17]-[SW-13] | 10 | 2025-06-19 | 2025-06-30 | 2025-05-29 | 2025-06-14 | 7995.06 | -14
Manholes |  | 19 | 2025-05-27 | 2025-06-22 | 2025-04-30 | 2025-05-15 | 91379.22 | -7
CO-R17.S13-SW-160 | Excavation Works for Main Line Manholes of Sewage Network-[Road 17]-[SW-13] | 1 | 2025-05-27 | 2025-05-27 | 2025-04-30 | 2025-04-30 | 15229.87 | -1
CO-R17.S13-SW-170 | Installation RC Footing Works for Main Line Manholes of Sewage Network-[Road 17]-[SW-13] | 2 | 2025-06-03 | 2025-06-10 | 2025-05-01 | 2025-05-04 | 10153.25 | -7
CO-R17.S13-SW-180 | Install Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 17]-[SW-13] | 4 | 2025-06-11 | 2025-06-15 | 2025-05-04 | 2025-05-08 | 40612.99 | -7
CO-R17.S13-SW-190 | Pouring Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 17]-[SW-13] | 1 | 2025-06-16 | 2025-06-16 | 2025-05-08 | 2025-05-10 | 5076.62 | -7
CO-R17.S13-SW-200 | Backfilling Works for Main Line Manholes of Sewage Network-[Road 17]-[SW-13] | 4 | 2025-06-17 | 2025-06-21 | 2025-05-10 | 2025-05-14 | 15229.87 | -7
CO-R17.S13-SW-210 | Testing Works for Main Line Manholes of Sewage Network-[Road 17]-[SW-13] | 1 | 2025-06-22 | 2025-06-22 | 2025-05-14 | 2025-05-15 | 5076.62 | -7
Storm Drainage Network |  | 248 | 2025-07-05 | 2026-04-23 | 2025-06-18 | 2026-04-05 | 260648.81 | 131
Main Line Sections |  | 248 | 2025-07-05 | 2026-04-23 | 2025-06-18 | 2026-04-05 | 119430.6 | 131
CO-R17.S13-SD-120 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 17]-[SW-13] | 20 | 2025-07-05 | 2025-07-27 | 2025-06-18 | 2025-07-10 | 102369.08 | 60
CO-R17.S13-SD-130 | Trench Backfilling and Compaction Works for Main Lines of Storm Drainage Network-[Road 17]-[SW-13] | 20 | 2026-04-01 | 2026-04-23 | 2026-03-10 | 2026-04-05 | 17061.51 | 131
Manholes |  | 14 | 2025-07-05 | 2025-07-20 | 2025-06-18 | 2025-07-03 | 85534.78 | 60
CO-R17.S13-SD-180 | Trench Excavation and Bedding Works for Manholes of Storm Drainage Network-[Road 17]-[SW-13] | 1 | 2025-07-05 | 2025-07-05 | 2025-06-18 | 2025-06-18 | 13505.49 | 60
CO-R17.S13-SD-190 | Install RC Footing Works for Manholes of Storm Drainage Network-[Road 17]-[SW-13] | 1 | 2025-07-06 | 2025-07-06 | 2025-06-19 | 2025-06-19 | 4501.83 | 60
CO-R17.S13-SD-200 | Install RC Wall Rings & Slab Works for Manholes of Storm Drainage Network-[Road 17]-[SW-13] | 4 | 2025-07-07 | 2025-07-10 | 2025-06-21 | 2025-06-24 | 40516.47 | 60
CO-R17.S13-SD-210 | Testing Works for Manholes of Storm Drainage Network-[Road 17]-[SW-13] | 1 | 2025-07-12 | 2025-07-12 | 2025-06-25 | 2025-06-25 | 9003.66 | 60
CO-R17.S13-SD-220 | Backfilling Works for Manholes of Storm Drainage Network-[Road 17]-[SW-13] | 7 | 2025-07-13 | 2025-07-20 | 2025-06-26 | 2025-07-03 | 18007.32 | 60
Catch Basin Sections |  | 59 | 2025-07-21 | 2025-09-28 | 2025-07-05 | 2025-08-06 | 55683.43 | 29
CO-R17.S13-SD-140 | Trench Excavation and Bedding Works for Catch Basins of Storm Drainage Network-[Road 17]-[SW-13] | 7 | 2025-07-21 | 2025-07-28 | 2025-07-05 | 2025-07-12 | 9280.57 | 60
CO-R17.S13-SD-150 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 17]-[SW-13] | 7 | 2025-09-03 | 2025-09-10 | 2025-07-14 | 2025-07-21 | 27841.72 | 29
CO-R17.S13-SD-160 | Testing Works for Catch Basins of Storm Drainage Network-[Road 17]-[SW-13] | 7 | 2025-09-11 | 2025-09-18 | 2025-07-22 | 2025-07-29 | 6187.05 | 29
CO-R17.S13-SD-170 | Trench Backfilling and Compaction Works for Catch Basins of Storm Drainage Network-[Road 17]-[SW-13] | 7 | 2025-09-20 | 2025-09-28 | 2025-07-30 | 2025-08-06 | 12374.1 | 29
Irrigation Network |  | 40 | 2025-09-29 | 2025-11-13 | 2025-08-07 | 2025-09-14 | 52768.56 | 22
Main Line Pipes |  | 40 | 2025-09-29 | 2025-11-13 | 2025-08-07 | 2025-09-14 | 52768.56 | 22
CO-R17.S13-IR-100 | Trench Excavation and Bedding Works for Main Lines of Irrigation Network-[Road 17]-[SW-13] | 7 | 2025-09-29 | 2025-10-06 | 2025-08-07 | 2025-08-14 | 9511.63 | 29
CO-R17.S13-IR-110 | Pipes Laying Works for Main Lines of Irrigation Network-[Road 17]-[SW-13] | 10 | 2025-10-07 | 2025-10-18 | 2025-08-16 | 2025-08-26 | 28534.88 | 29
CO-R17.S13-IR-120 | Installation Works for Main Line Valves of Irrigation Network-[Road 17]-[SW-13] | 7 | 2025-10-27 | 2025-11-03 | 2025-08-27 | 2025-09-03 | 9966.25 | 22
CO-R17.S13-IR-130 | Trench Backfilling and Compaction Works for Main Lines of Irrigation Network-[Road 17]-[SW-13] | 9 | 2025-11-04 | 2025-11-13 | 2025-09-04 | 2025-09-14 | 4755.81 | 22
Telecom Network |  | 209 | 2026-01-04 | 2026-09-12 | 2025-11-08 | 2026-08-24 | 35771.97 | -9
Ducts Works |  | 209 | 2026-01-04 | 2026-09-12 | 2025-11-08 | 2026-08-24 | 29513.5 | -9
CO-R17.S13-TE-100 | Trench Excavation and Bedding Works for Ducts of Telecom Network-[Road 17]-[SW-13] | 7 | 2026-01-04 | 2026-01-11 | 2025-11-08 | 2025-11-15 | 3015 | 118
CO-R17.S13-TE-110 | Pipes Laying Works for Ducts of Telecom Network-[Road 17]-[SW-13] | 7 | 2026-08-19 | 2026-08-26 | 2026-08-01 | 2026-08-08 | 17621 | -9
CO-R17.S13-TE-120 | Pouring Plain Concrete Above Ducts of Telecom Network-[Road 17]-[SW-13] | 7 | 2026-08-27 | 2026-09-03 | 2026-08-09 | 2026-08-16 | 3015 | -9
CO-R17.S13-TE-130 | Trench Backfilling and Compaction Works for Ducts of Telecom Network-[Road 17]-[SW-13] | 7 | 2026-09-05 | 2026-09-12 | 2026-08-17 | 2026-08-24 | 5862.5 | -9
Manholes Works |  | 21 | 2026-08-19 | 2026-09-12 | 2026-08-01 | 2026-08-24 | 6258.47 | -9
CO-R17.S13-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 17]-[SW-13] | 7 | 2026-08-19 | 2026-08-26 | 2026-08-01 | 2026-08-08 | 628.46 | -16
CO-R17.S13-TE-150 | Installation Works for Manholes of Telecom Network-[Road 17]-[SW-13] | 7 | 2026-08-27 | 2026-09-03 | 2026-08-09 | 2026-08-16 | 5001.55 | -9
CO-R17.S13-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 17]-[SW-13] | 7 | 2026-09-05 | 2026-09-12 | 2026-08-17 | 2026-08-24 | 628.46 | -9
Medium Voltage Network |  | 448 | 2025-05-13 | 2026-11-01 | 2025-04-05 | 2026-10-13 | 260274.98 | -10
Cabling Works |  | 24 | 2026-10-05 | 2026-11-01 | 2026-09-15 | 2026-10-13 | 180017.96 | -16
CO-R17.S13-MV-ML-310 | Trench Excavation and Bedding Works for Medium Voltage Network-[Road 17]-[SW-13] | 18 | 2026-10-05 | 2026-10-25 | 2026-09-15 | 2026-10-06 | 20639.76 | -16
CO-R17.S13-MV-ML-320 | Cable Laying Works for Medium Voltage Network-[Road 17]-[SW-13] | 18 | 2026-10-08 | 2026-10-28 | 2026-09-19 | 2026-10-10 | 111564.74 | -16
CO-R17.S13-MV-ML-330 | Trench Backfilling and Compaction Works for Medium Voltage Network-[Road 17]-[SW-13] | 18 | 2026-10-12 | 2026-11-01 | 2026-09-22 | 2026-10-13 | 47813.46 | -16
RMU Works |  | 426 | 2025-05-13 | 2026-10-06 | 2025-04-05 | 2026-09-16 | 80257.02 | 12
CO-R17.S13-MV-130 | Foundation Excavation Works for RMU of Medium Voltage Network-[Road 17]-[SW-13] | 6 | 2025-05-13 | 2025-05-19 | 2025-04-05 | 2025-04-10 | 8025.7 | 391
CO-R17.S13-MV-150 | Installation Works for RMU Concrete Foundations of Medium Voltage Network-[Road 17]-[SW-13] | 8 | 2026-09-09 | 2026-09-17 | 2026-08-22 | 2026-08-30 | 20064.26 | -6
CO-R17.S13-MV-170 | Installation Works for RMU of Medium Voltage Network-[Road 17]-[SW-13] | 5 | 2026-09-19 | 2026-09-24 | 2026-08-31 | 2026-09-05 | 36115.66 | -6
CO-R17.S13-MV-SS-150 | Termination Works for RMU of Medium Voltage Network-[Road 17]-[SW-13] | 5 | 2026-09-26 | 2026-09-30 | 2026-09-06 | 2026-09-10 | 8025.7 | 12
CO-R17.S13-MV-SS-160 | Testing Works for RMU of Medium Voltage Network-[Road 17]-[SW-13] | 5 | 2026-10-01 | 2026-10-06 | 2026-09-12 | 2026-09-16 | 8025.7 | 12
Road Works |  | 53 | 2026-10-19 | 2026-12-19 | 2026-09-30 | 2026-11-30 | 313028.6 | -15
Pre-Bituminous Construction |  | 45 | 2026-10-19 | 2026-12-09 | 2026-09-30 | 2026-11-21 | 198710.32 | -13
CO-R17.S13-RD-P-100 | Capping and Subgrade Layer for Road Works-[Road 17]-[SW-13] | 15 | 2026-10-19 | 2026-11-04 | 2026-09-30 | 2026-10-17 | 117126.34 | -16
CO-R17.S13-RD-P-110 | Aggregate Base Course Layer for Road Works-[Road 17]-[SW-13] | 12 | 2026-11-26 | 2026-12-09 | 2026-11-08 | 2026-11-21 | 81583.98 | -13
Pavement Works |  | 17 | 2026-11-30 | 2026-12-19 | 2026-11-11 | 2026-11-30 | 114318.28 | -15
CO-R17.S13-RD-P-120 | Fixing of Curbstone for Sidewalks Pavement-[Road 17]-[SW-13] | 12 | 2026-11-30 | 2026-12-13 | 2026-11-11 | 2026-11-24 | 66802.75 | -13
CO-R17.S13-RD-P-130 | Fixing of Interlock Tiles for Sidewalks Pavement-[Road 17]-[SW-13] | 10 | 2026-12-08 | 2026-12-19 | 2026-11-19 | 2026-11-30 | 47515.53 | -15
SW_14 |  | 535 | 27-Mar-25 A | 2026-12-20 | 2025-03-17 | 2026-12-01 | 1307637.06 | -16
Earthworks |  | 22 | 27-Mar-25 A | 21-Apr-25 A | 2025-03-17 | 2025-04-15 | 141667.06
Earthworks |  | 22 | 27-Mar-25 A | 21-Apr-25 A | 2025-03-17 | 2025-04-15 | 141667.06
CO-R17.S14-EW-100 | Roadway Excavation Works Upto Design Level for Earthworks-[Road 17]-[SW-14] | 10 | 27-Mar-25 A | 08-Apr-25 A | 2025-03-17 | 2025-03-27 | 44769.75
CO-R17.S14-EW-110 | Embankments Works Upto Design Level for Earthworks-[Road 17]-[SW-14] | 12 | 27-Mar-25 A | 21-Apr-25 A | 2025-03-29 | 2025-04-15 | 96897.3
Sewage Network |  | 36 | 2025-05-27 | 2025-07-12 | 2025-04-23 | 2025-06-25 | 95670.32 | -14
Main Line Sections |  | 36 | 2025-05-27 | 2025-07-12 | 2025-04-23 | 2025-06-25 | 68353.22 | -14
CO-R17.S14-SW-100 | Trench Excavation and Bedding Works for Main Lines of Sewage Network-[Road 17]-[SW-14] | 12 | 2025-05-27 | 2025-06-14 | 2025-04-23 | 2025-05-06 | 15189.6 | -16
CO-R17.S14-SW-120 | Pipes Laying Works for Main Lines of Sewage Network-[Road 17]-[SW-14] | 12 | 2025-06-15 | 2025-06-28 | 2025-05-07 | 2025-05-20 | 45568.81 | -12
CO-R17.S14-SW-130 | Trench Backfilling and Compaction Works for Main Lines of Sewage Network-[Road 17]-[SW-14] | 10 | 2025-07-01 | 2025-07-12 | 2025-06-15 | 2025-06-25 | 7594.8 | -14
Manholes |  | 13 | 2025-06-15 | 2025-06-29 | 2025-05-07 | 2025-05-21 | 27317.11 | -3
CO-R17.S14-SW-160 | Excavation Works for Main Line Manholes of Sewage Network-[Road 17]-[SW-14] | 1 | 2025-06-15 | 2025-06-15 | 2025-05-07 | 2025-05-07 | 4552.85 | -3
CO-R17.S14-SW-170 | Installation RC Footing Works for Main Line Manholes of Sewage Network-[Road 17]-[SW-14] | 2 | 2025-06-16 | 2025-06-17 | 2025-05-08 | 2025-05-10 | 3035.23 | -3
CO-R17.S14-SW-180 | Install Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 17]-[SW-14] | 4 | 2025-06-18 | 2025-06-22 | 2025-05-11 | 2025-05-14 | 12140.94 | -3
CO-R17.S14-SW-190 | Pouring Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 17]-[SW-14] | 1 | 2025-06-23 | 2025-06-23 | 2025-05-15 | 2025-05-15 | 1517.62 | -3
CO-R17.S14-SW-200 | Backfilling Works for Main Line Manholes of Sewage Network-[Road 17]-[SW-14] | 4 | 2025-06-24 | 2025-06-28 | 2025-05-17 | 2025-05-20 | 4552.85 | -3
CO-R17.S14-SW-210 | Testing Works for Main Line Manholes of Sewage Network-[Road 17]-[SW-14] | 1 | 2025-06-29 | 2025-06-29 | 2025-05-21 | 2025-05-21 | 1517.62 | -3
Storm Drainage Network |  | 242 | 2025-07-16 | 2026-04-28 | 2025-06-30 | 2026-04-09 | 355944.2 | 167
Main Line Sections |  | 242 | 2025-07-16 | 2026-04-28 | 2025-06-30 | 2026-04-09 | 246384.86 | 97
CO-R17.S14-SD-120 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 17]-[SW-14] | 20 | 2025-07-16 | 2025-08-07 | 2025-06-30 | 2025-07-22 | 211187.03 | 203
CO-R17.S14-SD-130 | Trench Backfilling and Compaction Works for Main Lines of Storm Drainage Network-[Road 17]-[SW-14] | 20 | 2026-04-06 | 2026-04-28 | 2026-03-15 | 2026-04-09 | 35197.84 | 97
Manholes |  | 14 | 2025-07-16 | 2025-07-31 | 2025-06-30 | 2025-07-15 | 53875.91 | 203
CO-R17.S14-SD-180 | Trench Excavation and Bedding Works for Manholes of Storm Drainage Network-[Road 17]-[SW-14] | 1 | 2025-07-16 | 2025-07-16 | 2025-06-30 | 2025-06-30 | 8506.72 | 203
CO-R17.S14-SD-190 | Install RC Footing Works for Manholes of Storm Drainage Network-[Road 17]-[SW-14] | 1 | 2025-07-17 | 2025-07-17 | 2025-07-01 | 2025-07-01 | 2835.57 | 203
CO-R17.S14-SD-200 | Install RC Wall Rings & Slab Works for Manholes of Storm Drainage Network-[Road 17]-[SW-14] | 4 | 2025-07-19 | 2025-07-22 | 2025-07-02 | 2025-07-06 | 25520.17 | 203
CO-R17.S14-SD-210 | Testing Works for Manholes of Storm Drainage Network-[Road 17]-[SW-14] | 1 | 2025-07-23 | 2025-07-23 | 2025-07-07 | 2025-07-07 | 5671.15 | 203
CO-R17.S14-SD-220 | Backfilling Works for Manholes of Storm Drainage Network-[Road 17]-[SW-14] | 7 | 2025-07-24 | 2025-07-31 | 2025-07-08 | 2025-07-15 | 11342.3 | 203
Catch Basin Sections |  | 53 | 2025-08-02 | 2025-10-02 | 2025-07-16 | 2025-08-12 | 55683.43 | 342
CO-R17.S14-SD-140 | Trench Excavation and Bedding Works for Catch Basins of Storm Drainage Network-[Road 17]-[SW-14] | 6 | 2025-08-02 | 2025-08-07 | 2025-07-16 | 2025-07-22 | 9280.57 | 203
CO-R17.S14-SD-150 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 17]-[SW-14] | 7 | 2025-09-11 | 2025-09-18 | 2025-07-23 | 2025-07-30 | 27841.72 | 174
CO-R17.S14-SD-160 | Testing Works for Catch Basins of Storm Drainage Network-[Road 17]-[SW-14] | 4 | 2025-09-20 | 2025-09-24 | 2025-07-31 | 2025-08-04 | 6187.05 | 342
CO-R17.S14-SD-170 | Trench Backfilling and Compaction Works for Catch Basins of Storm Drainage Network-[Road 17]-[SW-14] | 7 | 2025-09-25 | 2025-10-02 | 2025-08-05 | 2025-08-12 | 12374.1 | 342
Street Lighting Network |  | 231 | 2025-05-13 | 2026-02-11 | 2025-04-16 | 2025-12-14 | 242733.63 | 189
Lighting Poles Works |  | 77 | 2025-11-15 | 2026-02-11 | 2025-09-15 | 2025-12-14 | 128981.7 | 167
CO-R17.S14-SL-100 | Foundation Excavation Works for Lighting Poles of Street Lighting Network-[Road 17]-[SW-14] | 12 | 2025-11-15 | 2025-11-27 | 2025-09-15 | 2025-09-29 | 4282.81 | 22
CO-R17.S14-SL-110 | Installation Works for Lighting Poles Foundation of Street Lighting Network-[Road 17]-[SW-14] | 12 | 2025-11-29 | 2025-12-11 | 2025-09-30 | 2025-10-13 | 16371.45 | 22
CO-R17.S14-SL-120 | Installation Works for Lighting Poles of Street Lighting Network-[Road 17]-[SW-14] | 18 | 2026-01-17 | 2026-02-05 | 2025-11-18 | 2025-12-08 | 47110.88 | 22
CO-R17.S14-SL-130 | Installation Works for Lighting Fixtures With Drop Wire of Street Lighting Network-[Road 17]-[SW-14] | 18 | 2026-01-22 | 2026-02-11 | 2025-11-24 | 2025-12-14 | 26954.1 | 167
CO-R17.S14-SL-210 | Backfilling Works for Lighting Poles of Street Lighting Network-[Road 17]-[SW-14] | 12 | 2026-01-22 | 2026-02-05 | 2025-11-24 | 2025-12-08 | 17131.23 | 22
CO-R17.S14-SL-200 | Testing Works for Lighting Poles of Street Lighting Network-[Road 17]-[SW-14] | 5 | 2026-02-05 | 2026-02-11 | 2025-12-08 | 2025-12-14 | 17131.23 | 168
Cabling Works |  | 30 | 2025-12-13 | 2026-01-15 | 2025-10-14 | 2025-11-17 | 86178.75 | 22
CO-R17.S14-SL-140 | Trench Excavation and Bedding Works for Street Lighting Network-[Road 17]-[SW-14] | 10 | 2025-12-13 | 2025-12-23 | 2025-10-14 | 2025-10-25 | 0 | 22
CO-R17.S14-SL-150 | Cable Laying Works for Street Lighting Network-[Road 17]-[SW-14] | 10 | 2025-12-24 | 2026-01-04 | 2025-10-26 | 2025-11-05 | 80023.13 | 22
CO-R17.S14-SL-160 | Trench Backfilling and Compaction Works for Street Lighting Network-[Road 17]-[SW-14] | 10 | 2026-01-05 | 2026-01-15 | 2025-11-06 | 2025-11-17 | 6155.63 | 22
Distrubution Panel Boards |  | 24 | 2025-05-13 | 2025-06-14 | 2025-04-16 | 2025-05-13 | 27573.18 | 396
CO-R17.S14-SL-170 | Foundation Excavation Works For Panel Boards of Street Lighting Network-[Road 17]-[SW-14] | 18 | 2025-05-13 | 2025-06-02 | 2025-04-16 | 2025-05-06 | 0 | 396
CO-R17.S14-SL-180 | Installation Works for Panel Board Concrete Foundations of Street Lighting Network-[Road 17]-[SW-14] | 18 | 2025-05-17 | 2025-06-10 | 2025-04-20 | 2025-05-10 | 0 | 396
CO-R17.S14-SL-220 | A wall of concrete blocks to install the KWH meter of Street Lighting Network-[Road 17]-[SW-14] | 18 | 2025-05-17 | 2025-06-10 | 2025-04-20 | 2025-05-10 | 27573.18 | 399
CO-R17.S14-SL-190 | Installation Works for Lighting Panel Boards of Street Lighting Network-[Road 17]-[SW-14] | 18 | 2025-05-20 | 2025-06-14 | 2025-04-23 | 2025-05-13 | 0 | 396
Potable Water Network |  | 27 | 2026-04-29 | 2026-06-03 | 2026-04-11 | 2026-05-11 | 122821.28 | 97
Main Line Sections |  | 18 | 2026-04-29 | 2026-05-19 | 2026-04-11 | 2026-04-30 | 81563.35 | 106
CO-R17.S14-PW-100 | Trench Excavation and Bedding Works for Main Lines of Potable Water Network-[Road 17]-[SW-14] | 6 | 2026-04-29 | 2026-05-05 | 2026-04-11 | 2026-04-16 | 18125.19 | 97
CO-R17.S14-PW-110 | Pipes Laying and accessories for Main Lines of Potable Water Network-[Road 17]-[SW-14] | 6 | 2026-05-06 | 2026-05-12 | 2026-04-18 | 2026-04-23 | 45312.97 | 97
CO-R17.S14-PW-130 | Trench Backfilling and Compaction Works for Main Lines of Potable Water Network-[Road 17]-[SW-14] | 6 | 2026-05-12 | 2026-05-19 | 2026-04-23 | 2026-04-30 | 18125.19 | 106
Valve Chamber |  | 6 | 2026-05-12 | 2026-05-19 | 2026-04-23 | 2026-04-30 | 18534.88 | 106
CO-R17.S14-PW-210 | Installation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 17]-[SW-14] | 6 | 2026-05-12 | 2026-05-19 | 2026-04-23 | 2026-04-30 | 18534.88 | 106
Fire Hydrant |  | 18 | 2026-05-10 | 2026-06-03 | 2026-04-21 | 2026-05-11 | 22723.05 | 97
CO-R17.S14-PW-140 | Excavation Works for Fire Hydrants of Potable Water Network-[Road 17]-[SW-14] | 6 | 2026-05-10 | 2026-05-16 | 2026-04-21 | 2026-04-27 | 3408.46 | 97
CO-R17.S14-PW-150 | Installation Works for Fire Hydrant of Potable Water Network-[Road 17]-[SW-14] | 6 | 2026-05-17 | 2026-05-23 | 2026-04-28 | 2026-05-04 | 14769.98 | 97
CO-R17.S14-PW-160 | Trench Backfilling and Compaction Works for Fire Hydrants of Potable Water Network-[Road 17]-[SW-14] | 6 | 2026-05-24 | 2026-06-03 | 2026-05-05 | 2026-05-11 | 4544.61 | 97
Telecom Network |  | 207 | 2026-01-14 | 2026-09-20 | 2025-11-16 | 2026-09-01 | 35771.97 | -16
Ducts Works |  | 207 | 2026-01-14 | 2026-09-20 | 2025-11-16 | 2026-09-01 | 29513.5 | -16
CO-R17.S14-TE-100 | Trench Excavation and Bedding Works for Ducts of Telecom Network-[Road 17]-[SW-14] | 7 | 2026-01-14 | 2026-01-21 | 2025-11-16 | 2025-11-23 | 3015 | 116
CO-R17.S14-TE-110 | Pipes Laying Works for Ducts of Telecom Network-[Road 17]-[SW-14] | 7 | 2026-08-27 | 2026-09-03 | 2026-08-09 | 2026-08-16 | 17621 | -16
CO-R17.S14-TE-120 | Pouring Plain Concrete Above Ducts of Telecom Network-[Road 17]-[SW-14] | 7 | 2026-09-05 | 2026-09-12 | 2026-08-17 | 2026-08-24 | 3015 | -16
CO-R17.S14-TE-130 | Trench Backfilling and Compaction Works for Ducts of Telecom Network-[Road 17]-[SW-14] | 7 | 2026-09-13 | 2026-09-20 | 2026-08-25 | 2026-09-01 | 5862.5 | -16
Manholes Works |  | 21 | 2026-08-27 | 2026-09-20 | 2026-08-09 | 2026-09-01 | 6258.47 | -16
CO-R17.S14-TE-140 | Excavation Works for Manholes of Telecom Network-[Road 17]-[SW-14] | 7 | 2026-08-27 | 2026-09-03 | 2026-08-09 | 2026-08-16 | 628.46 | -16
CO-R17.S14-TE-150 | Installation Works for Manholes of Telecom Network-[Road 17]-[SW-14] | 7 | 2026-09-05 | 2026-09-12 | 2026-08-17 | 2026-08-24 | 5001.55 | -16
CO-R17.S14-TE-160 | Backfilling Works for Manholes of Telecom Network-[Road 17]-[SW-14] | 7 | 2026-09-13 | 2026-09-20 | 2026-08-25 | 2026-09-01 | 628.46 | -16
Road Works |  | 77 | 2026-09-21 | 2026-12-20 | 2026-09-02 | 2026-12-01 | 313028.6 | -16
Pre-Bituminous Construction |  | 66 | 2026-09-21 | 2026-12-07 | 2026-09-02 | 2026-11-18 | 198710.32 | -11
CO-R17.S14-RD-P-100 | Capping and Subgrade Layer for Road Works-[Road 17]-[SW-14] | 18 | 2026-09-21 | 2026-10-12 | 2026-09-02 | 2026-09-22 | 117126.34 | 4
CO-R17.S14-RD-P-110 | Aggregate Base Course Layer for Road Works-[Road 17]-[SW-14] | 12 | 2026-11-24 | 2026-12-07 | 2026-11-05 | 2026-11-18 | 81583.98 | -11
Pavement Works |  | 20 | 2026-11-28 | 2026-12-20 | 2026-11-09 | 2026-12-01 | 114318.28 | -16
CO-R17.S14-RD-P-120 | Fixing of Curbstone for Sidewalks Pavement-[Road 17]-[SW-14] | 12 | 2026-11-28 | 2026-12-10 | 2026-11-09 | 2026-11-22 | 66802.75 | -11
CO-R17.S14-RD-P-130 | Fixing of Interlock Tiles for Sidewalks Pavement-[Road 17]-[SW-14] | 10 | 2026-12-09 | 2026-12-20 | 2026-11-21 | 2026-12-01 | 47515.53 | -16
Road 18 Local 1 ( 479 LM ) |  | 320 | 09-Feb-25 A | 2026-02-28 | 2025-02-09 | 2026-01-01 | 2059281.23 | 252
SW_15 |  | 306 | 09-Feb-25 A | 2026-02-11 | 2025-02-09 | 2025-12-16 | 1079914.47 | 266
Earthworks |  | 22 | 09-Feb-25 A | 13-Apr-25 A | 2025-02-09 | 2025-03-06 | 136995.43
Earthworks |  | 22 | 09-Feb-25 A | 13-Apr-25 A | 2025-02-09 | 2025-03-06 | 136995.43
CO-R18.S15-EW-120 | Roadway Excavation Works Upto Design Level for Earthworks-[Road 18]-[SW-15] | 10 | 09-Feb-25 A | 13-Apr-25 A | 2025-02-09 | 2025-02-19 | 43293.41
CO-R18.S15-EW-130 | Embankments Works Upto Design Level for Earthworks-[Road 18]-[SW-15] | 12 | 20-Feb-25 A | 13-Apr-25 A | 2025-02-20 | 2025-03-06 | 93702.02
Sewage Network |  | 37 | 29-Apr-25 A | 2025-06-16 | 2025-03-08 | 2025-05-17 | 190373.18 | -12
Main Line Sections |  | 37 | 29-Apr-25 A | 2025-06-16 | 2025-03-08 | 2025-05-17 | 64497.54 | -12
CO-R18.S15-SW-220 | Trench Excavation and Bedding Works for Main Lines of Sewage Network-[Road 18]-[SW-15] | 6 | 29-Apr-25 A | 2025-05-19 | 2025-03-08 | 2025-03-20 | 14332.79 | -16
CO-R18.S15-SW-230 | Pipes Laying Works for Main Lines of Sewage Network-[Road 18]-[SW-15] | 10 | 30-Apr-25 A | 2025-05-31 | 2025-04-24 | 2025-05-05 | 42998.36 | -12
CO-R18.S15-SW-240 | Trench Backfilling and Compaction Works for Main Lines of Sewage Network-[Road 18]-[SW-15] | 10 | 2025-06-01 | 2025-06-16 | 2025-05-06 | 2025-05-17 | 7166.39 | -12
Manholes |  | 13 | 2025-05-20 | 2025-06-04 | 2025-04-24 | 2025-05-10 | 125875.65 | -5
CO-R18.S15-SW-250 | Excavation Works for Main Line Manholes of Sewage Network-[Road 18]-[SW-15] | 1 | 2025-05-20 | 2025-05-20 | 2025-04-24 | 2025-04-24 | 20979.27 | -5
CO-R18.S15-SW-260 | Installation RC Footing Works for Main Line Manholes of Sewage Network-[Road 18]-[SW-15] | 2 | 2025-05-21 | 2025-05-24 | 2025-04-26 | 2025-04-28 | 13986.18 | -5
CO-R18.S15-SW-270 | Install Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 18]-[SW-15] | 4 | 2025-05-24 | 2025-05-28 | 2025-04-28 | 2025-05-03 | 55944.73 | -5
CO-R18.S15-SW-280 | Pouring Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 18]-[SW-15] | 1 | 2025-05-28 | 2025-05-29 | 2025-05-03 | 2025-05-04 | 6993.09 | -5
CO-R18.S15-SW-290 | Backfilling Works for Main Line Manholes of Sewage Network-[Road 18]-[SW-15] | 4 | 2025-05-29 | 2025-06-03 | 2025-05-04 | 2025-05-08 | 20979.27 | -5
CO-R18.S15-SW-300 | Testing Works for Main Line Manholes of Sewage Network-[Road 18]-[SW-15] | 1 | 2025-06-03 | 2025-06-04 | 2025-05-08 | 2025-05-10 | 6993.09 | -5
Storm Drainage Network |  | 64 | 2025-06-29 | 2025-09-10 | 2025-05-29 | 2025-07-21 | 148390.32 | 318
Main Line Sections |  | 20 | 2025-07-22 | 2025-08-13 | 2025-06-26 | 2025-07-19 | 17814.26 | 342
CO-R18.S15-SD-250 | Trench Backfilling and Compaction Works for Main Lines of Storm Drainage Network-[Road 18]-[SW-15] | 20 | 2025-07-22 | 2025-08-13 | 2025-06-26 | 2025-07-19 | 17814.26 | 342
Manholes |  | 36 | 2025-06-29 | 2025-08-09 | 2025-05-29 | 2025-06-18 | 76731.35 | 29
CO-R18.S15-SD-300 | Trench Excavation and Bedding Works for Manholes of Storm Drainage Network-[Road 18]-[SW-15] | 1 | 2025-06-29 | 2025-06-29 | 2025-05-29 | 2025-05-29 | 12115.48 | 51
CO-R18.S15-SD-310 | Install RC Footing Works for Manholes of Storm Drainage Network-[Road 18]-[SW-15] | 1 | 2025-07-26 | 2025-07-26 | 2025-05-31 | 2025-05-31 | 4038.49 | 29
CO-R18.S15-SD-320 | Install RC Wall Rings & Slab Works for Manholes of Storm Drainage Network-[Road 18]-[SW-15] | 4 | 2025-07-27 | 2025-07-30 | 2025-06-01 | 2025-06-04 | 36346.43 | 29
CO-R18.S15-SD-330 | Testing Works for Manholes of Storm Drainage Network-[Road 18]-[SW-15] | 1 | 2025-07-31 | 2025-07-31 | 2025-06-10 | 2025-06-10 | 8076.98 | 29
CO-R18.S15-SD-340 | Backfilling Works for Manholes of Storm Drainage Network-[Road 18]-[SW-15] | 7 | 2025-08-02 | 2025-08-09 | 2025-06-11 | 2025-06-18 | 16153.97 | 29
Catch Basin Sections |  | 28 | 2025-08-10 | 2025-09-10 | 2025-06-19 | 2025-07-21 | 53844.71 | 31
CO-R18.S15-SD-260 | Trench Excavation and Bedding Works for Catch Basins of Storm Drainage Network-[Road 18]-[SW-15] | 7 | 2025-08-10 | 2025-08-17 | 2025-06-19 | 2025-06-26 | 8974.22 | 29
CO-R18.S15-SD-270 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 18]-[SW-15] | 7 | 2025-08-18 | 2025-08-25 | 2025-06-28 | 2025-07-05 | 26922.36 | 29
CO-R18.S15-SD-280 | Testing Works for Catch Basins of Storm Drainage Network-[Road 18]-[SW-15] | 7 | 2025-08-26 | 2025-09-02 | 2025-07-06 | 2025-07-13 | 5982.71 | 31
CO-R18.S15-SD-290 | Trench Backfilling and Compaction Works for Catch Basins of Storm Drainage Network-[Road 18]-[SW-15] | 7 | 2025-09-03 | 2025-09-10 | 2025-07-14 | 2025-07-21 | 11965.42 | 31
Irrigation Network |  | 38 | 2025-09-11 | 2025-10-26 | 2025-07-22 | 2025-08-28 | 88823.03 | 26
Main Line Pipes |  | 38 | 2025-09-11 | 2025-10-26 | 2025-07-22 | 2025-08-28 | 88823.03 | 26
CO-R18.S15-IR-140 | Trench Excavation and Bedding Works for Main Lines of Irrigation Network-[Road 18]-[SW-15] | 7 | 2025-09-11 | 2025-09-18 | 2025-07-22 | 2025-07-29 | 9197.93 | 31
CO-R18.S15-IR-150 | Pipes Laying Works for Main Lines of Irrigation Network-[Road 18]-[SW-15] | 10 | 2025-09-20 | 2025-10-01 | 2025-07-30 | 2025-08-10 | 27593.8 | 31
CO-R18.S15-IR-160 | Installation Works for Main Line Valves of Irrigation Network-[Road 18]-[SW-15] | 7 | 2025-10-08 | 2025-10-15 | 2025-08-11 | 2025-08-18 | 47432.33 | 26
CO-R18.S15-IR-170 | Trench Backfilling and Compaction Works for Main Lines of Irrigation Network-[Road 18]-[SW-15] | 9 | 2025-10-16 | 2025-10-26 | 2025-08-19 | 2025-08-28 | 4598.97 | 26
Telecom Network |  | 28 | 2025-10-27 | 2025-11-27 | 2025-08-30 | 2025-10-01 | 37842.27 | 252
Ducts Works |  | 28 | 2025-10-27 | 2025-11-27 | 2025-08-30 | 2025-10-01 | 28441.5 | 243
CO-R18.S15-TE-170 | Trench Excavation and Bedding Works for Ducts of Telecom Network-[Road 18]-[SW-15] | 7 | 2025-10-27 | 2025-11-03 | 2025-08-30 | 2025-09-06 | 2881 | 163
CO-R18.S15-TE-180 | Pipes Laying Works for Ducts of Telecom Network-[Road 18]-[SW-15] | 7 | 2025-11-04 | 2025-11-11 | 2025-09-07 | 2025-09-14 | 17085 | 243
CO-R18.S15-TE-230 | Pouring Plain Concrete Above Ducts of Telecom Network-[Road 18]-[SW-15] | 7 | 2025-11-12 | 2025-11-19 | 2025-09-15 | 2025-09-22 | 2881 | 243
CO-R18.S15-TE-190 | Trench Backfilling and Compaction Works for Ducts of Telecom Network-[Road 18]-[SW-15] | 7 | 2025-11-20 | 2025-11-27 | 2025-09-24 | 2025-10-01 | 5594.5 | 243
Manholes Works |  | 21 | 2025-11-04 | 2025-11-27 | 2025-09-07 | 2025-10-01 | 9400.77 | 252
CO-R18.S15-TE-200 | Excavation Works for Manholes of Telecom Network-[Road 18]-[SW-15] | 7 | 2025-11-04 | 2025-11-11 | 2025-09-07 | 2025-09-14 | 1256.92 | 252
CO-R18.S15-TE-210 | Installation Works for Manholes of Telecom Network-[Road 18]-[SW-15] | 7 | 2025-11-12 | 2025-11-19 | 2025-09-15 | 2025-09-22 | 6886.93 | 252
CO-R18.S15-TE-220 | Backfilling Works for Manholes of Telecom Network-[Road 18]-[SW-15] | 7 | 2025-11-20 | 2025-11-27 | 2025-09-24 | 2025-10-01 | 1256.92 | 252
Medium Voltage Network |  | 24 | 2025-12-29 | 2026-01-25 | 2025-11-02 | 2025-11-29 | 174316.44 | 213
Cabling Works |  | 24 | 2025-12-29 | 2026-01-25 | 2025-11-02 | 2025-11-29 | 174316.44 | 213
CO-R18.S15-MV-ML-340 | Trench Excavation and Bedding Works for Medium Voltage Network-[Road 18]-[SW-15] | 18 | 2025-12-29 | 2026-01-18 | 2025-11-02 | 2025-11-22 | 19958.11 | 213
CO-R18.S15-MV-ML-350 | Cable Laying Works for Medium Voltage Network-[Road 18]-[SW-15] | 18 | 2026-01-01 | 2026-01-21 | 2025-11-05 | 2025-11-25 | 108050.83 | 213
CO-R18.S15-MV-ML-360 | Trench Backfilling and Compaction Works for Medium Voltage Network-[Road 18]-[SW-15] | 18 | 2026-01-05 | 2026-01-25 | 2025-11-09 | 2025-11-29 | 46307.5 | 213
Road Works |  | 27 | 2026-01-12 | 2026-02-11 | 2025-11-16 | 2025-12-16 | 303173.81 | 266
Pre-Bituminous Construction |  | 21 | 2026-01-12 | 2026-02-04 | 2025-11-16 | 2025-12-09 | 192157.49 | 214
CO-R18.S15-RD-P-160 | Capping and Subgrade Layer for Road Works-[Road 18]-[SW-15] | 15 | 2026-01-12 | 2026-01-28 | 2025-11-16 | 2025-12-02 | 113263.41 | 214
CO-R18.S15-RD-P-170 | Aggregate Base Course Layer for Road Works-[Road 18]-[SW-15] | 18 | 2026-01-15 | 2026-02-04 | 2025-11-19 | 2025-12-09 | 78894.08 | 214
Pavement Works |  | 21 | 2026-01-19 | 2026-02-11 | 2025-11-23 | 2025-12-16 | 111016.32 | 266
CO-R18.S15-RD-P-140 | Fixing of Curbstone for Sidewalks Pavement-[Road 18]-[SW-15] | 18 | 2026-01-19 | 2026-02-08 | 2025-11-23 | 2025-12-13 | 64599.79 | 214
CO-R18.S15-RD-P-150 | Fixing of Interlock Tiles for Sidewalks Pavement-[Road 18]-[SW-15] | 18 | 2026-01-22 | 2026-02-11 | 2025-11-26 | 2025-12-16 | 46416.53 | 266
SW_16 |  | 310 | 20-Feb-25 A | 2026-02-28 | 2025-02-20 | 2026-01-01 | 979366.76 | 252
Earthworks |  | 22 | 20-Feb-25 A | 13-Apr-25 A | 2025-02-20 | 2025-03-18 | 136995.43
Earthworks |  | 22 | 20-Feb-25 A | 13-Apr-25 A | 2025-02-20 | 2025-03-18 | 136995.43
CO-R18.S16-EW-120 | Roadway Excavation Works Upto Design Level for Earthworks-[Road 18]-[SW-16] | 10 | 20-Feb-25 A | 13-Apr-25 A | 2025-02-20 | 2025-03-04 | 43293.41
CO-R18.S16-EW-130 | Embankments Works Upto Design Level for Earthworks-[Road 18]-[SW-16] | 12 | 05-Mar-25 A | 13-Apr-25 A | 2025-03-05 | 2025-03-18 | 93702.02
Sewage Network |  | 39 | 29-Apr-25 A | 2025-06-18 | 2025-03-22 | 2025-05-28 | 77076.12 | -14
Main Line Sections |  | 39 | 29-Apr-25 A | 2025-06-18 | 2025-03-22 | 2025-05-28 | 51284.6 | -14
CO-R18.S16-SW-220 | Trench Excavation and Bedding Works for Main Lines of Sewage Network-[Road 18]-[SW-16] | 6 | 29-Apr-25 A | 2025-05-19 | 2025-03-22 | 2025-04-08 | 11396.58 | -16
CO-R18.S16-SW-230 | Pipes Laying Works for Main Lines of Sewage Network-[Road 18]-[SW-16] | 12 | 30-Apr-25 A | 2025-06-02 | 2025-04-24 | 2025-05-07 | 34189.73 | -14
CO-R18.S16-SW-240 | Trench Backfilling and Compaction Works for Main Lines of Sewage Network-[Road 18]-[SW-16] | 10 | 2025-06-03 | 2025-06-18 | 2025-05-18 | 2025-05-28 | 5698.29 | -14
Manholes |  | 13 | 2025-05-20 | 2025-06-03 | 2025-04-24 | 2025-05-08 | 25791.52 | -5
CO-R18.S16-SW-250 | Excavation Works for Main Line Manholes of Sewage Network-[Road 18]-[SW-16] | 1 | 2025-05-20 | 2025-05-20 | 2025-04-24 | 2025-04-24 | 4298.59 | -5
CO-R18.S16-SW-260 | Installation RC Footing Works for Main Line Manholes of Sewage Network-[Road 18]-[SW-16] | 2 | 2025-05-21 | 2025-05-22 | 2025-04-26 | 2025-04-27 | 2865.72 | -5
CO-R18.S16-SW-270 | Install Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 18]-[SW-16] | 4 | 2025-05-24 | 2025-05-27 | 2025-04-28 | 2025-05-01 | 11462.9 | -5
CO-R18.S16-SW-280 | Pouring Grp Liner Wall Works for Main Line Manholes of Sewage Network-[Road 18]-[SW-16] | 1 | 2025-05-28 | 2025-05-28 | 2025-05-03 | 2025-05-03 | 1432.86 | -5
CO-R18.S16-SW-290 | Backfilling Works for Main Line Manholes of Sewage Network-[Road 18]-[SW-16] | 4 | 2025-05-29 | 2025-06-02 | 2025-05-04 | 2025-05-07 | 4298.59 | -5
CO-R18.S16-SW-300 | Testing Works for Main Line Manholes of Sewage Network-[Road 18]-[SW-16] | 1 | 2025-06-03 | 2025-06-03 | 2025-05-08 | 2025-05-08 | 1432.86 | -5
Storm Drainage Network |  | 73 | 2025-06-23 | 2025-09-15 | 2025-06-02 | 2025-08-11 | 178231.55 | 373
Main Line Sections |  | 20 | 2025-08-14 | 2025-09-06 | 2025-07-20 | 2025-08-11 | 31431.11 | 347
CO-R18.S16-SD-250 | Trench Backfilling and Compaction Works for Main Lines of Storm Drainage Network-[Road 18]-[SW-16] | 20 | 2025-08-14 | 2025-09-06 | 2025-07-20 | 2025-08-11 | 31431.11 | 347
Manholes |  | 14 | 2025-06-23 | 2025-07-08 | 2025-06-02 | 2025-06-22 | 92955.73 | 64
CO-R18.S16-SD-300 | Trench Excavation and Bedding Works for Manholes of Storm Drainage Network-[Road 18]-[SW-16] | 1 | 2025-06-23 | 2025-06-23 | 2025-06-02 | 2025-06-02 | 14677.22 | 64
CO-R18.S16-SD-310 | Install RC Footing Works for Manholes of Storm Drainage Network-[Road 18]-[SW-16] | 1 | 2025-06-24 | 2025-06-24 | 2025-06-03 | 2025-06-03 | 4892.41 | 64
CO-R18.S16-SD-320 | Install RC Wall Rings & Slab Works for Manholes of Storm Drainage Network-[Road 18]-[SW-16] | 4 | 2025-06-25 | 2025-06-29 | 2025-06-04 | 2025-06-12 | 44031.66 | 64
CO-R18.S16-SD-330 | Testing Works for Manholes of Storm Drainage Network-[Road 18]-[SW-16] | 1 | 2025-06-30 | 2025-06-30 | 2025-06-14 | 2025-06-14 | 9784.81 | 64
CO-R18.S16-SD-340 | Backfilling Works for Manholes of Storm Drainage Network-[Road 18]-[SW-16] | 7 | 2025-07-01 | 2025-07-08 | 2025-06-15 | 2025-06-22 | 19569.63 | 64
Catch Basin Sections |  | 59 | 2025-07-09 | 2025-09-15 | 2025-06-23 | 2025-07-26 | 53844.71 | 373
CO-R18.S16-SD-260 | Trench Excavation and Bedding Works for Catch Basins of Storm Drainage Network-[Road 18]-[SW-16] | 6 | 2025-07-09 | 2025-07-15 | 2025-06-23 | 2025-06-29 | 8974.22 | 64
CO-R18.S16-SD-270 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 18]-[SW-16] | 7 | 2025-08-26 | 2025-09-02 | 2025-07-06 | 2025-07-13 | 26922.36 | 29
CO-R18.S16-SD-280 | Testing Works for Catch Basins of Storm Drainage Network-[Road 18]-[SW-16] | 4 | 2025-09-03 | 2025-09-07 | 2025-07-14 | 2025-07-17 | 5982.71 | 373
CO-R18.S16-SD-290 | Trench Backfilling and Compaction Works for Catch Basins of Storm Drainage Network-[Road 18]-[SW-16] | 7 | 2025-09-08 | 2025-09-15 | 2025-07-19 | 2025-07-26 | 11965.42 | 373
Street Lighting Network |  | 215 | 2025-05-13 | 2026-01-24 | 2025-03-19 | 2025-11-27 | 116804.3 | 207
Lighting Poles Works |  | 77 | 2025-10-27 | 2026-01-24 | 2025-08-30 | 2025-11-27 | 60191.46 | 207
CO-R18.S16-SL-100 | Foundation Excavation Works for Lighting Poles of Street Lighting Network-[Road 18]-[SW-16] | 12 | 2025-10-27 | 2025-11-09 | 2025-08-30 | 2025-09-11 | 1998.64 | 26
CO-R18.S16-SL-110 | Installation Works for Lighting Poles Foundation of Street Lighting Network-[Road 18]-[SW-16] | 12 | 2025-11-10 | 2025-11-23 | 2025-09-13 | 2025-09-27 | 7640.01 | 26
CO-R18.S16-SL-120 | Installation Works for Lighting Poles of Street Lighting Network-[Road 18]-[SW-16] | 18 | 2025-12-29 | 2026-01-18 | 2025-11-02 | 2025-11-22 | 21985.08 | 26
CO-R18.S16-SL-130 | Installation Works for Lighting Fixtures With Drop Wire of Street Lighting Network-[Road 18]-[SW-16] | 18 | 2026-01-04 | 2026-01-24 | 2025-11-08 | 2025-11-27 | 12578.58 | 207
CO-R18.S16-SL-210 | Backfilling Works for Lighting Poles of Street Lighting Network-[Road 18]-[SW-16] | 12 | 2026-01-04 | 2026-01-18 | 2025-11-08 | 2025-11-22 | 7994.57 | 26
CO-R18.S16-SL-200 | Testing Works for Lighting Poles of Street Lighting Network-[Road 18]-[SW-16] | 5 | 2026-01-18 | 2026-01-24 | 2025-11-22 | 2025-11-27 | 7994.57 | 207
Cabling Works |  | 30 | 2025-11-24 | 2025-12-28 | 2025-09-28 | 2025-11-01 | 40676.37 | 26
CO-R18.S16-SL-140 | Trench Excavation and Bedding Works for Street Lighting Network-[Road 18]-[SW-16] | 10 | 2025-11-24 | 2025-12-04 | 2025-09-28 | 2025-10-08 | 0 | 26
CO-R18.S16-SL-150 | Cable Laying Works for Street Lighting Network-[Road 18]-[SW-16] | 10 | 2025-12-06 | 2025-12-16 | 2025-10-09 | 2025-10-20 | 37770.92 | 26
CO-R18.S16-SL-160 | Trench Backfilling and Compaction Works for Street Lighting Network-[Road 18]-[SW-16] | 10 | 2025-12-17 | 2025-12-28 | 2025-10-21 | 2025-11-01 | 2905.46 | 26
Distrubution Panel Boards |  | 24 | 2025-05-13 | 2025-06-14 | 2025-03-19 | 2025-04-20 | 15936.47 | 396
CO-R18.S16-SL-170 | Foundation Excavation Works For Panel Boards of Street Lighting Network-[Road 18]-[SW-16] | 18 | 2025-05-13 | 2025-06-02 | 2025-03-19 | 2025-04-13 | 0 | 396
CO-R18.S16-SL-180 | Installation Works for Panel Board Concrete Foundations of Street Lighting Network-[Road 18]-[SW-16] | 18 | 2025-05-17 | 2025-06-10 | 2025-03-23 | 2025-04-16 | 0 | 396
CO-R18.S16-SL-220 | A wall of concrete blocks to install the KWH meter of Street Lighting Network-[Road 18]-[SW-16] | 18 | 2025-05-17 | 2025-06-10 | 2025-03-23 | 2025-04-16 | 15936.47 | 399
CO-R18.S16-SL-190 | Installation Works for Lighting Panel Boards of Street Lighting Network-[Road 18]-[SW-16] | 18 | 2025-05-20 | 2025-06-14 | 2025-03-26 | 2025-04-20 | 0 | 396
Potable Water Network |  | 27 | 2025-09-07 | 2025-10-08 | 2025-08-12 | 2025-09-11 | 126074.85 | 347
Main Line Sections |  | 18 | 2025-09-07 | 2025-09-28 | 2025-08-12 | 2025-09-01 | 92391.27 | 356
CO-R18.S16-PW-230 | Trench Excavation and Bedding Works for Main Lines of Potable Water Network-[Road 18]-[SW-16] | 6 | 2025-09-07 | 2025-09-13 | 2025-08-12 | 2025-08-18 | 20531.39 | 347
CO-R18.S16-PW-240 | Pipes Laying and accessories for Main Lines of Potable Water Network-[Road 18]-[SW-16] | 6 | 2025-09-14 | 2025-09-20 | 2025-08-19 | 2025-08-25 | 51328.49 | 347
CO-R18.S16-PW-280 | Trench Backfilling and Compaction Works for Main Lines of Potable Water Network-[Road 18]-[SW-16] | 6 | 2025-09-20 | 2025-09-28 | 2025-08-25 | 2025-09-01 | 20531.39 | 356
Valve Chamber |  | 6 | 2025-09-20 | 2025-09-28 | 2025-08-25 | 2025-09-01 | 18534.88 | 356
CO-R18.S16-PW-330 | Installation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 18]-[SW-16] | 6 | 2025-09-20 | 2025-09-28 | 2025-08-25 | 2025-09-01 | 18534.88 | 356
Fire Hydrant |  | 18 | 2025-09-17 | 2025-10-08 | 2025-08-23 | 2025-09-11 | 15148.7 | 347
CO-R18.S16-PW-250 | Excavation Works for Fire Hydrants of Potable Water Network-[Road 18]-[SW-16] | 6 | 2025-09-17 | 2025-09-24 | 2025-08-23 | 2025-08-28 | 2272.3 | 347
CO-R18.S16-PW-260 | Installation Works for Fire Hydrant of Potable Water Network-[Road 18]-[SW-16] | 6 | 2025-09-25 | 2025-10-01 | 2025-08-30 | 2025-09-04 | 9846.66 | 347
CO-R18.S16-PW-270 | Trench Backfilling and Compaction Works for Fire Hydrants of Potable Water Network-[Road 18]-[SW-16] | 6 | 2025-10-02 | 2025-10-08 | 2025-09-06 | 2025-09-11 | 3029.74 | 347
Telecom Network |  | 28 | 2025-12-27 | 2026-01-27 | 2025-10-30 | 2025-12-01 | 41010.7 | 252
Ducts Works |  | 28 | 2025-12-27 | 2026-01-27 | 2025-10-30 | 2025-12-01 | 28441.5 | 252
CO-R18.S16-TE-170 | Trench Excavation and Bedding Works for Ducts of Telecom Network-[Road 18]-[SW-16] | 7 | 2025-12-27 | 2026-01-03 | 2025-10-30 | 2025-11-06 | 2881 | 118
CO-R18.S16-TE-180 | Pipes Laying Works for Ducts of Telecom Network-[Road 18]-[SW-16] | 7 | 2026-01-04 | 2026-01-11 | 2025-11-08 | 2025-11-15 | 17085 | 252
CO-R18.S16-TE-230 | Pouring Plain Concrete Above Ducts of Telecom Network-[Road 18]-[SW-16] | 7 | 2026-01-12 | 2026-01-19 | 2025-11-16 | 2025-11-23 | 2881 | 252
CO-R18.S16-TE-190 | Trench Backfilling and Compaction Works for Ducts of Telecom Network-[Road 18]-[SW-16] | 7 | 2026-01-20 | 2026-01-27 | 2025-11-24 | 2025-12-01 | 5594.5 | 252
Manholes Works |  | 21 | 2026-01-04 | 2026-01-27 | 2025-11-08 | 2025-12-01 | 12569.2 | 252
CO-R18.S16-TE-200 | Excavation Works for Manholes of Telecom Network-[Road 18]-[SW-16] | 7 | 2026-01-04 | 2026-01-11 | 2025-11-08 | 2025-11-15 | 1890.61 | 252
CO-R18.S16-TE-210 | Installation Works for Manholes of Telecom Network-[Road 18]-[SW-16] | 7 | 2026-01-12 | 2026-01-19 | 2025-11-16 | 2025-11-23 | 8787.99 | 252
CO-R18.S16-TE-220 | Backfilling Works for Manholes of Telecom Network-[Road 18]-[SW-16] | 7 | 2026-01-20 | 2026-01-27 | 2025-11-24 | 2025-12-01 | 1890.61 | 252
Road Works |  | 27 | 2026-01-28 | 2026-02-28 | 2025-12-02 | 2026-01-01 | 303173.81 | 252
Pre-Bituminous Construction |  | 21 | 2026-01-28 | 2026-02-21 | 2025-12-02 | 2025-12-25 | 192157.49 | 252
CO-R18.S16-RD-P-160 | Capping and Subgrade Layer for Road Works-[Road 18]-[SW-16] | 18 | 2026-01-28 | 2026-02-17 | 2025-12-02 | 2025-12-22 | 113263.41 | 252
CO-R18.S16-RD-P-170 | Aggregate Base Course Layer for Road Works-[Road 18]-[SW-16] | 18 | 2026-02-01 | 2026-02-21 | 2025-12-06 | 2025-12-25 | 78894.08 | 252
Pavement Works |  | 21 | 2026-02-04 | 2026-02-28 | 2025-12-09 | 2026-01-01 | 111016.32 | 252
CO-R18.S16-RD-P-140 | Fixing of Curbstone for Sidewalks Pavement-[Road 18]-[SW-16] | 18 | 2026-02-04 | 2026-02-24 | 2025-12-09 | 2025-12-29 | 64599.79 | 252
CO-R18.S16-RD-P-150 | Fixing of Interlock Tiles for Sidewalks Pavement-[Road 18]-[SW-16] | 18 | 2026-02-08 | 2026-02-28 | 2025-12-13 | 2026-01-01 | 46416.53 | 252
Finishes for Infrastructure Networks |  | 200 | 2026-05-23 | 2027-01-16 | 2026-05-04 | 2026-12-28 | 13006292.48 | -16
Phase 2 Block "J" |  | 200 | 2026-05-23 | 2027-01-16 | 2026-05-04 | 2026-12-28 | 13006292.48 | -16
Road 09 Local 2 ( 2278 LM ) |  | 155 | 2026-06-21 | 2026-12-19 | 2026-06-02 | 2026-11-30 | 3449609.39 | -7
Sewage Network |  | 27 | 2026-08-06 | 2026-09-06 | 2026-07-19 | 2026-08-18 | 289897.37 | 11
Testing and Finishes |  | 27 | 2026-08-06 | 2026-09-06 | 2026-07-19 | 2026-08-18 | 289897.37 | 11
CO-R09-SW-TF-100 | Final Testing For Main Line of Sewage Network-[Road 09] | 12 | 2026-08-06 | 2026-08-19 | 2026-07-19 | 2026-08-01 | 208794.34 | -16
CO-R09-SW-TF-110 | Install Manhole Cover Works for External Finishes of Sewage Network-[Road 09] | 12 | 2026-08-20 | 2026-09-02 | 2026-08-02 | 2026-08-15 | 40551.52 | -2
CO-R09-SW-TF-120 | Main Manhole Internal Finishes (Benching + Insulation) of Sewage Network-[Road 09] | 12 | 2026-08-24 | 2026-09-06 | 2026-08-05 | 2026-08-18 | 40551.52 | 11
Storm Drainage Network |  | 43 | 2026-08-03 | 2026-09-21 | 2026-07-15 | 2026-09-02 | 758678.88 | 53
Testing and Finishes |  | 43 | 2026-08-03 | 2026-09-21 | 2026-07-15 | 2026-09-02 | 758678.88 | 53
CO-R09-SD-TF-110 | Install Catch Basin Cover Works for External Finishes of Storm Drainage Network-[Road 09] | 16 | 2026-08-03 | 2026-08-20 | 2026-07-15 | 2026-08-02 | 27719.4 | 9
CO-R09-SD-TF-100 | Testing Work for Pipes of Storm Drainage Network-[Road 09] | 12 | 2026-08-06 | 2026-08-19 | 2026-07-19 | 2026-08-01 | 101957.42 | -16
CO-R09-SD-TF-120 | Main Manhole Internal Finishes (Benching + Insulation ) for Storm Drainage Network-[Road 09] | 16 | 2026-09-03 | 2026-09-21 | 2026-08-16 | 2026-09-02 | 601282.66 | -2
CO-R09-SD-TF-130 | Catch Basin Internal Finishes (Benching + Insulation ) for Storm Drainage Network-[Road 09] | 16 | 2026-09-03 | 2026-09-21 | 2026-08-16 | 2026-09-02 | 27719.4 | 53
Potable Water Network |  | 33 | 2026-08-20 | 2026-09-28 | 2026-08-02 | 2026-09-08 | 39231.99 | -7
Testing and Finishes |  | 33 | 2026-08-20 | 2026-09-28 | 2026-08-02 | 2026-09-08 | 39231.99 | -7
CO-R09-PW-TF-110 | Testing Work for Main Line of Potable Water Network-[Road 09] | 9 | 2026-08-20 | 2026-08-30 | 2026-08-02 | 2026-08-11 | 39231.99 | -16
CO-R09-PW-TF-100 | Final Finishes works and Covers for Valves and Valve Chambers of Potable Water Network-[Road 09] | 12 | 2026-08-31 | 2026-09-13 | 2026-08-12 | 2026-08-25 | 0 | -7
CO-R09-PW-TF-120 | Fire Hydrant Finishies (S.Box + Safety + Marker Post ) of Potable Water Network-[Road 09] | 12 | 2026-09-14 | 2026-09-28 | 2026-08-26 | 2026-09-08 | 0 | -7
Irrigation Network |  | 16 | 2026-08-17 | 2026-09-03 | 2026-07-29 | 2026-08-16 | 21307.01 | 13
Testing and Finishes |  | 16 | 2026-08-17 | 2026-09-03 | 2026-07-29 | 2026-08-16 | 21307.01 | 13
CO-R09-IR-TF-100 | Final Testing (pressure tests) of Irrigation Network-[Road 09] | 16 | 2026-08-17 | 2026-09-03 | 2026-07-29 | 2026-08-16 | 21307.01 | 13
Street Lighting Network |  | 86 | 2026-06-21 | 2026-09-29 | 2026-06-02 | 2026-09-09 | 189756.53 | 13
Termination and Testing Works |  | 84 | 2026-06-21 | 2026-09-27 | 2026-06-02 | 2026-09-07 | 177971.23 | 15
CO-R09-SL-TF-100 | Termination Works For Lighting Poles Cables of Street Lighting Network-[Road 09] | 12 | 2026-06-21 | 2026-07-04 | 2026-06-02 | 2026-06-15 | 80958.78 | -8
CO-R09-SL-TF-110 | Termination Works For Panel Board Cables of Street Lighting Network-[Road 09] | 11 | 2026-09-02 | 2026-09-14 | 2026-08-15 | 2026-08-26 | 64674.97 | -8
CO-R09-SL-TF-380 | Testing Works For Panel Board Cables of Street Lighting Network-[Road 09] | 10 | 2026-09-14 | 2026-09-27 | 2026-08-26 | 2026-09-07 | 32337.48 | 15
Earthing System Works |  | 74 | 2026-07-05 | 2026-09-29 | 2026-06-16 | 2026-09-09 | 11785.3 | -8
CO-R09-SL-ES-100 | Install Earthing System Works for Lighting Poles of Street Lighting Network-[Road 09] | 12 | 2026-07-05 | 2026-07-18 | 2026-06-16 | 2026-06-29 | 6125.14 | -8
CO-R09-SL-ES-110 | Install Earthing System Works for Lighting Panel Boards of Street Lighting Network-[Road 09] | 12 | 2026-09-14 | 2026-09-29 | 2026-08-26 | 2026-09-09 | 5660.16 | -8
Medium Voltage Network |  | 16 | 2026-07-09 | 2026-07-27 | 2026-06-21 | 2026-07-08 | 0 | 46
Termination and Testing Works |  | 16 | 2026-07-09 | 2026-07-27 | 2026-06-21 | 2026-07-08 | 0 | 46
CO-R09-MV-TF-100 | Termination Works of Medium Voltage Network-[Road 09] | 16 | 2026-07-09 | 2026-07-27 | 2026-06-21 | 2026-07-08 | 0 | 46
Road Works |  | 57 | 2026-10-13 | 2026-12-19 | 2026-09-24 | 2026-11-30 | 2150737.61 | -7
Bituminous Construction |  | 27 | 2026-10-13 | 2026-11-14 | 2026-09-24 | 2026-10-26 | 2058508.34 | -7
CO-R09-S1-RD-F-100 | Application of Prime Coat Layer for Road Works - S.W 01-[Road 09] | 12 | 2026-10-13 | 2026-10-27 | 2026-09-24 | 2026-10-08 | 576151.93 | -8
CO-R09-S1-RD-F-120 | Bituminous Base & Wearing Courses Layers for Road Works- S.W 01-[Road 09] | 12 | 2026-10-17 | 2026-10-31 | 2026-09-28 | 2026-10-12 | 453102.24 | -8
CO-R09-S2-RD-F-110 | Application of Prime Coat Layer for Road Works- S.W 02-[Road 09] | 18 | 2026-10-20 | 2026-11-10 | 2026-10-01 | 2026-10-22 | 576151.93 | -7
CO-R09-S2-RD-F-130 | Bituminous Base & Wearing Courses Layers for Road Works- S.W 02-[Road 09] | 18 | 2026-10-24 | 2026-11-14 | 2026-10-05 | 2026-10-26 | 453102.24 | -7
Traffic Signs Boards and Roads Marking |  | 42 | 2026-10-31 | 2026-12-19 | 2026-10-12 | 2026-11-30 | 92229.28 | -7
CO-R09-S1-RD-F-140 | Application of Road Marking Works For Road Works- S.W 01-[Road 09] | 12 | 2026-10-31 | 2026-11-14 | 2026-10-12 | 2026-10-26 | 33593.01 | -8
CO-R09-S1-RD-F-150 | Installation Works of Traffic Signs Boards For Road Works- S.W 01-[Road 09] | 12 | 2026-11-14 | 2026-11-28 | 2026-10-26 | 2026-11-09 | 12521.63 | -8
CO-R09-S2-RD-F-160 | Application of Road Marking Works For Road Works- S.W 02-[Road 09] | 15 | 2026-11-14 | 2026-12-01 | 2026-10-26 | 2026-11-12 | 33593.01 | -7
CO-R09-S2-RD-F-170 | Installation Works of Traffic Signs Boards For Road Works- S.W 02-[Road 09] | 15 | 2026-12-01 | 2026-12-19 | 2026-11-12 | 2026-11-30 | 12521.63 | -7
Road 10 Local 2 ( 2352 LM ) |  | 150 | 2026-05-23 | 2026-11-18 | 2026-05-04 | 2026-10-31 | 3613915.12 | -15
Sewage Network |  | 27 | 2026-08-17 | 2026-09-16 | 2026-07-29 | 2026-08-29 | 153798.13 | -16
Testing and Finishes |  | 27 | 2026-08-17 | 2026-09-16 | 2026-07-29 | 2026-08-29 | 153798.13 | -16
CO-R10-SW-TF-100 | Final Testing For Main Line of Sewage Network-[Road 10] | 12 | 2026-08-17 | 2026-08-30 | 2026-07-29 | 2026-08-11 | 115642.91 | -16
CO-R10-SW-TF-110 | Install Manhole Cover Works for External Finishes of Sewage Network-[Road 10] | 12 | 2026-08-31 | 2026-09-13 | 2026-08-12 | 2026-08-25 | 19077.61 | -16
CO-R10-SW-TF-130 | Main Manhole Internal Finishes (Benching + Insulation) of Sewage Network-[Road 10] | 12 | 2026-09-03 | 2026-09-16 | 2026-08-16 | 2026-08-29 | 19077.61 | -16
Storm Drainage Network |  | 42 | 2026-08-15 | 2026-10-03 | 2026-07-27 | 2026-09-13 | 712432.02 | -16
Testing and Finishes |  | 42 | 2026-08-15 | 2026-10-03 | 2026-07-27 | 2026-09-13 | 712432.02 | -16
CO-R10-SD-TF-100 | Testing Work for Pipes of Storm Drainage Network-[Road 10] | 16 | 2026-08-15 | 2026-09-01 | 2026-07-27 | 2026-08-13 | 154199.47 | -9
CO-R10-SD-TF-110 | Install Catch Basin Cover Works for External Finishes of Storm Drainage Network-[Road 10] | 16 | 2026-08-23 | 2026-09-09 | 2026-08-04 | 2026-08-22 | 27795.73 | -13
CO-R10-SD-TF-120 | Main Manhole Internal Finishes (Benching + Insulation ) for Storm Drainage Network-[Road 10] | 12 | 2026-09-14 | 2026-09-28 | 2026-08-26 | 2026-09-08 | 502641.74 | -15
CO-R10-SD-TF-130 | Catch Basin Internal Finishes (Benching + Insulation ) for Storm Drainage Network-[Road 10] | 16 | 2026-09-14 | 2026-10-03 | 2026-08-26 | 2026-09-13 | 27795.08 | -16
Potable Water Network |  | 24 | 2026-08-26 | 2026-09-22 | 2026-08-08 | 2026-09-03 | 299945.22 | -12
Testing and Finishes |  | 24 | 2026-08-26 | 2026-09-22 | 2026-08-08 | 2026-09-03 | 299945.22 | -12
CO-R10-PW-TF-100 | Final Finishes works and Covers for Valves and Valve Chambers of Potable Water Network-[Road 10] | 12 | 2026-08-26 | 2026-09-08 | 2026-08-08 | 2026-08-20 | 0 | -12
CO-R10-PW-TF-110 | Testing Work for Main Line of Potable Water Network-[Road 10] | 12 | 2026-08-31 | 2026-09-13 | 2026-08-12 | 2026-08-25 | 299945.22 | -16
CO-R10-PW-TF-120 | Fire Hydrant Finishies (S.Box + Safety + Marker Post ) of Potable Water Network-[Road 10] | 12 | 2026-09-09 | 2026-09-22 | 2026-08-22 | 2026-09-03 | 0 | -12
Irrigation Network |  | 10 | 2026-08-27 | 2026-09-07 | 2026-08-09 | 2026-08-19 | 100762.62 | -7
Testing and Finishes |  | 10 | 2026-08-27 | 2026-09-07 | 2026-08-09 | 2026-08-19 | 100762.62 | -7
CO-R10-IR-TF-120 | Final Testing (pressure tests) of Irrigation Network-[Road 10] | 10 | 2026-08-27 | 2026-09-07 | 2026-08-09 | 2026-08-19 | 100762.62 | -7
Street Lighting Network |  | 66 | 2026-05-23 | 2026-08-11 | 2026-05-04 | 2026-07-23 | 190052 | 13
Termination and Testing Works |  | 66 | 2026-05-23 | 2026-08-11 | 2026-05-04 | 2026-07-23 | 178266.7 | 13
CO-R10-SL-TF-140 | Termination Works For Lighting Poles Cables of Street Lighting Network-[Road 10] | 12 | 2026-05-23 | 2026-06-09 | 2026-05-04 | 2026-05-17 | 81254.25 | 0
CO-R10-SL-TF-150 | Termination Works For Panel Board Cables of Street Lighting Network-[Road 10] | 12 | 2026-07-27 | 2026-08-09 | 2026-07-08 | 2026-07-21 | 64674.97 | -7
CO-R10-SL-TF-380 | Testing Works For Panel Board Cables of Street Lighting Network-[Road 10] | 2 | 2026-08-10 | 2026-08-11 | 2026-07-22 | 2026-07-23 | 32337.48 | 13
Earthing System Works |  | 27 | 2026-06-10 | 2026-07-11 | 2026-05-18 | 2026-06-22 | 11785.3 | 0
CO-R10-SL-ES-140 | Install Earthing System Works for Lighting Poles of Street Lighting Network-[Road 10] | 12 | 2026-06-10 | 2026-06-23 | 2026-05-18 | 2026-06-04 | 6125.14 | 0
CO-R10-SL-ES-150 | Install Earthing System Works for Lighting Panel Boards of Street Lighting Network-[Road 10] | 12 | 2026-06-28 | 2026-07-11 | 2026-06-09 | 2026-06-22 | 5660.16 | 0
Medium Voltage Network |  | 7 | 2026-09-29 | 2026-10-06 | 2026-09-09 | 2026-09-16 | 0 | -16
Termination and Testing Works |  | 7 | 2026-09-29 | 2026-10-06 | 2026-09-09 | 2026-09-16 | 0 | -16
CO-R10-MV-TF-140 | Termination Works of Medium Voltage Network-[Road 10] | 7 | 2026-09-29 | 2026-10-06 | 2026-09-09 | 2026-09-16 | 0 | -16
Road Works |  | 27 | 2026-10-19 | 2026-11-18 | 2026-09-30 | 2026-10-31 | 2156925.13 | -15
Bituminous Construction |  | 15 | 2026-10-19 | 2026-11-04 | 2026-09-30 | 2026-10-17 | 2064314.89 | -16
CO-R10-S03-RD-F-110 | Application of Prime Coat Layer for Road Works- S.W 05-[Road 10] | 10 | 2026-10-19 | 2026-10-29 | 2026-09-30 | 2026-10-11 | 577776.85 | -16
CO-R10-S04-RD-F-140 | Application of Prime Coat Layer for Road Works- S.W 06-[Road 10] | 10 | 2026-10-21 | 2026-11-01 | 2026-10-03 | 2026-10-13 | 577776.85 | -16
CO-R10-S03-RD-F-120 | Bituminous Base & Wearing Courses Layers for Road Works- S.W 05-[Road 10] | 10 | 2026-10-22 | 2026-11-02 | 2026-10-04 | 2026-10-14 | 454380.6 | -16
CO-R10-S04-RD-F-150 | Bituminous Base & Wearing Courses Layers for Road Works- S.W 06-[Road 10] | 10 | 2026-10-25 | 2026-11-04 | 2026-10-06 | 2026-10-17 | 454380.6 | -16
Traffic Signs Boards and Roads Marking |  | 14 | 2026-11-03 | 2026-11-18 | 2026-10-15 | 2026-10-31 | 92610.24 | -15
CO-R10-S03-RD-F-160 | Application of Road Marking Works For Road Works- S.W 05-[Road 10] | 12 | 2026-11-03 | 2026-11-16 | 2026-10-15 | 2026-10-28 | 33687.68 | -16
CO-R10-S03-RD-F-100 | Installation Works of Traffic Signs Boards For Road Works- S.W 05-[Road 10] | 12 | 2026-11-03 | 2026-11-16 | 2026-10-15 | 2026-10-28 | 12617.44 | -16
CO-R10-S04-RD-F-170 | Application of Road Marking Works For Road Works- S.W 06-[Road 10] | 12 | 2026-11-05 | 2026-11-18 | 2026-10-18 | 2026-10-31 | 33687.68 | -16
CO-R10-S04-RD-F-130 | Installation Works of Traffic Signs Boards For Road Works- S.W 06-[Road 10] | 10 | 2026-11-08 | 2026-11-18 | 2026-10-20 | 2026-10-31 | 12617.44 | -15
Road 11 Local 1 ( 670 LM ) |  | 119 | 2026-07-14 | 2026-11-30 | 2026-05-18 | 2026-11-11 | 1241354.75 | -15
Sewage Network |  | 27 | 2026-08-31 | 2026-10-01 | 2026-08-12 | 2026-09-12 | 210240.04 | -16
Testing and Finishes |  | 27 | 2026-08-31 | 2026-10-01 | 2026-08-12 | 2026-09-12 | 210240.04 | -16
CO-R11-SW-TF-100 | Final Testing For Main Line of Sewage Network-[Road 11] | 12 | 2026-08-31 | 2026-09-13 | 2026-08-12 | 2026-08-25 | 181390.91 | -16
CO-R11-SW-TF-110 | Install Manhole Cover Works for External Finishes of Sewage Network-[Road 11] | 12 | 2026-09-14 | 2026-09-28 | 2026-08-26 | 2026-09-08 | 14424.56 | -16
CO-R11-SW-TF-130 | Main Manhole Internal Finishes (Benching + Insulation) of Sewage Network-[Road 11] | 12 | 2026-09-17 | 2026-10-01 | 2026-08-30 | 2026-09-12 | 14424.56 | -16
Storm Drainage Network |  | 42 | 2026-09-02 | 2026-10-21 | 2026-08-15 | 2026-10-03 | 360303.34 | -16
Testing and Finishes |  | 42 | 2026-09-02 | 2026-10-21 | 2026-08-15 | 2026-10-03 | 360303.34 | -16
CO-R11-SD-TF-100 | Testing Work for Pipes of Storm Drainage Network-[Road 11] | 16 | 2026-09-02 | 2026-09-20 | 2026-08-15 | 2026-09-01 | 89053.14 | -9
CO-R11-SD-TF-110 | Install Catch Basin Cover Works for External Finishes of Storm Drainage Network-[Road 11] | 12 | 2026-09-10 | 2026-09-24 | 2026-08-23 | 2026-09-05 | 8111.5 | -12
CO-R11-SD-TF-120 | Main Manhole Internal Finishes (Benching + Insulation ) for Storm Drainage Network-[Road 11] | 12 | 2026-09-29 | 2026-10-12 | 2026-09-09 | 2026-09-22 | 255027.2 | -15
CO-R11-SD-TF-130 | Catch Basin Internal Finishes (Benching + Insulation ) for Storm Drainage Network-[Road 11] | 16 | 2026-10-04 | 2026-10-21 | 2026-09-14 | 2026-10-03 | 8111.5 | -16
Potable Water Network |  | 24 | 2026-09-14 | 2026-10-12 | 2026-08-26 | 2026-09-22 | 11618.55 | -16
Testing and Finishes |  | 24 | 2026-09-14 | 2026-10-12 | 2026-08-26 | 2026-09-22 | 11618.55 | -16
CO-R11-PW-TF-110 | Testing Work for Main Line of Potable Water Network-[Road 11] | 12 | 2026-09-14 | 2026-09-28 | 2026-08-26 | 2026-09-08 | 11618.55 | -16
CO-R11-PW-TF-100 | Final Finishes works and Covers for Valves and Valve Chambers of Potable Water Network-[Road 11] | 12 | 2026-09-14 | 2026-09-28 | 2026-08-26 | 2026-09-08 | 0 | -16
CO-R11-PW-TF-120 | Fire Hydrant Finishies (S.Box + Safety + Marker Post ) of Potable Water Network-[Road 11] | 12 | 2026-09-29 | 2026-10-12 | 2026-09-09 | 2026-09-22 | 0 | -16
Irrigation Network |  | 10 | 2026-09-10 | 2026-09-21 | 2026-08-23 | 2026-09-02 | 6235.18 | -9
Testing and Finishes |  | 10 | 2026-09-10 | 2026-09-21 | 2026-08-23 | 2026-09-02 | 6235.18 | -9
CO-R11-IR-TF-130 | Final Testing (pressure tests) of Irrigation Network-[Road 11] | 10 | 2026-09-10 | 2026-09-21 | 2026-08-23 | 2026-09-02 | 6235.18 | -9
Street Lighting Network |  | 40 | 2026-07-14 | 2026-08-29 | 2026-05-18 | 2026-08-10 | 23933.07 | 0
Termination and Testing Works |  | 40 | 2026-07-14 | 2026-08-29 | 2026-05-18 | 2026-08-10 | 23933.07 | 0
CO-R11-SL-TF-160 | Termination Works For Lighting Poles Cables of Street Lighting Network-[Road 11] | 12 | 2026-07-14 | 2026-07-27 | 2026-05-18 | 2026-06-04 | 23933.07 | 20
CO-R11-SL-TF-170 | Termination Works For Panel Board Cables of Street Lighting Network-[Road 11] | 12 | 2026-08-13 | 2026-08-26 | 2026-07-26 | 2026-08-08 | 0 | -10
CO-R11-SL-TF-380 | Testing Works For Panel Board Cables of Street Lighting Network-[Road 11] | 2 | 2026-08-27 | 2026-08-29 | 2026-08-09 | 2026-08-10 | 0 | 0
Medium Voltage Network |  | 7 | 2026-10-07 | 2026-10-14 | 2026-09-17 | 2026-09-26 | 0 | -16
Termination and Testing Works |  | 7 | 2026-10-07 | 2026-10-14 | 2026-09-17 | 2026-09-26 | 0 | -16
CO-R11-MV-TF-160 | Termination Works of Medium Voltage Network-[Road 11] | 7 | 2026-10-07 | 2026-10-14 | 2026-09-17 | 2026-09-26 | 0 | -16
Road Works |  | 27 | 2026-10-31 | 2026-11-30 | 2026-10-12 | 2026-11-11 | 629024.57 | -15
Bituminous Construction |  | 17 | 2026-10-31 | 2026-11-18 | 2026-10-12 | 2026-10-31 | 602377.44 | -16
CO-R11-S05-RD-F-110 | Application of Prime Coat Layer for Road Works- S.W 07-[Road 11] | 10 | 2026-10-31 | 2026-11-10 | 2026-10-12 | 2026-10-22 | 168597.06 | -16
CO-R11-S06-RD-F-140 | Application of Prime Coat Layer for Road Works- S.W 08-[Road 11] | 12 | 2026-11-02 | 2026-11-15 | 2026-10-14 | 2026-10-27 | 168597.06 | -16
CO-R11-S05-RD-F-120 | Bituminous Base & Wearing Courses Layers for Road Works- S.W 07-[Road 11] | 12 | 2026-11-03 | 2026-11-16 | 2026-10-15 | 2026-10-28 | 132591.66 | -16
CO-R11-S06-RD-F-150 | Bituminous Base & Wearing Courses Layers for Road Works- S.W 08-[Road 11] | 12 | 2026-11-05 | 2026-11-18 | 2026-10-18 | 2026-10-31 | 132591.66 | -16
Traffic Signs Boards and Roads Marking |  | 12 | 2026-11-17 | 2026-11-30 | 2026-10-29 | 2026-11-11 | 26647.13 | -15
CO-R11-S05-RD-F-160 | Application of Road Marking Works For Road Works- S.W 07-[Road 11] | 10 | 2026-11-17 | 2026-11-28 | 2026-10-29 | 2026-11-09 | 9830.19 | -16
CO-R11-S05-RD-F-100 | Installation Works of Traffic Signs Boards For Road Works- S.W 07-[Road 11] | 10 | 2026-11-17 | 2026-11-28 | 2026-10-29 | 2026-11-09 | 3493.38 | -16
CO-R11-S06-RD-F-170 | Application of Road Marking Works For Road Works- S.W 08-[Road 11] | 10 | 2026-11-19 | 2026-11-30 | 2026-11-01 | 2026-11-11 | 9830.19 | -16
CO-R11-S06-RD-F-130 | Installation Works of Traffic Signs Boards For Road Works- S.W 08-[Road 11] | 10 | 2026-11-19 | 2026-11-30 | 2026-11-01 | 2026-11-11 | 3493.38 | -15
Road 14 Local 1 ( 584 LM ) |  | 117 | 2026-07-28 | 2026-12-12 | 2026-06-13 | 2026-11-23 | 1526012.39 | -15
Sewage Network |  | 27 | 2026-09-14 | 2026-10-15 | 2026-08-26 | 2026-09-27 | 48450.33 | -16
Testing and Finishes |  | 27 | 2026-09-14 | 2026-10-15 | 2026-08-26 | 2026-09-27 | 48450.33 | -16
CO-R14-SW-TF-100 | Final Testing For Main Line of Sewage Network-[Road 14] | 12 | 2026-09-14 | 2026-09-28 | 2026-08-26 | 2026-09-08 | 31128.01 | -16
CO-R14-SW-TF-110 | Install Manhole Cover Works for External Finishes of Sewage Network-[Road 14] | 12 | 2026-09-29 | 2026-10-12 | 2026-09-09 | 2026-09-22 | 8661.16 | -16
CO-R14-SW-TF-130 | Main Manhole Internal Finishes (Benching + Insulation) of Sewage Network-[Road 14] | 12 | 2026-10-03 | 2026-10-15 | 2026-09-13 | 2026-09-27 | 8661.16 | -16
Storm Drainage Network |  | 62 | 2026-08-29 | 2026-11-09 | 2026-08-10 | 2026-10-21 | 444653.25 | -16
Testing and Finishes |  | 62 | 2026-08-29 | 2026-11-09 | 2026-08-10 | 2026-10-21 | 444653.25 | -16
CO-R14-SD-TF-100 | Testing Work for Pipes of Storm Drainage Network-[Road 14] | 10 | 2026-08-29 | 2026-09-08 | 2026-08-10 | 2026-08-20 | 110901.39 | 1
CO-R14-SD-TF-110 | Install Catch Basin Cover Works for External Finishes of Storm Drainage Network-[Road 14] | 12 | 2026-09-26 | 2026-10-08 | 2026-09-06 | 2026-09-19 | 11970.37 | -12
CO-R14-SD-TF-120 | Main Manhole Internal Finishes (Benching + Insulation ) for Storm Drainage Network-[Road 14] | 12 | 2026-10-13 | 2026-10-26 | 2026-09-24 | 2026-10-07 | 309811.13 | -15
CO-R14-SD-TF-130 | Catch Basin Internal Finishes (Benching + Insulation ) for Storm Drainage Network-[Road 14] | 16 | 2026-10-22 | 2026-11-09 | 2026-10-04 | 2026-10-21 | 11970.37 | -16
Potable Water Network |  | 24 | 2026-09-29 | 2026-10-26 | 2026-09-09 | 2026-10-07 | 44447.8 | -16
Testing and Finishes |  | 24 | 2026-09-29 | 2026-10-26 | 2026-09-09 | 2026-10-07 | 44447.8 | -16
CO-R14-PW-TF-110 | Testing Work for Main Line of Potable Water Network-[Road 14] | 12 | 2026-09-29 | 2026-10-12 | 2026-09-09 | 2026-09-22 | 44447.8 | -16
CO-R14-PW-TF-100 | Final Finishes works and Covers for Valves and Valve Chambers of Potable Water Network-[Road 14] | 12 | 2026-09-29 | 2026-10-12 | 2026-09-09 | 2026-09-22 | 0 | -16
CO-R14-PW-TF-120 | Fire Hydrant Finishies (S.Box + Safety + Marker Post ) of Potable Water Network-[Road 14] | 12 | 2026-10-13 | 2026-10-26 | 2026-09-24 | 2026-10-07 | 0 | -16
Irrigation Network |  | 10 | 2026-09-22 | 2026-10-04 | 2026-09-03 | 2026-09-14 | 24385.3 | -9
Testing and Finishes |  | 10 | 2026-09-22 | 2026-10-04 | 2026-09-03 | 2026-09-14 | 24385.3 | -9
CO-R11-IR-TF-140 | Final Testing (pressure tests) of Irrigation Network-[Road 14] | 10 | 2026-09-22 | 2026-10-04 | 2026-09-03 | 2026-09-14 | 24385.3 | -9
Street Lighting Network |  | 46 | 2026-07-28 | 2026-09-19 | 2026-06-13 | 2026-08-31 | 34865.46 | -14
Termination and Testing Works |  | 46 | 2026-07-28 | 2026-09-19 | 2026-06-13 | 2026-08-31 | 34865.46 | -14
CO-R11-SL-TF-180 | Termination Works For Lighting Poles Cables of Street Lighting Network-[Road 14] | 12 | 2026-07-28 | 2026-08-10 | 2026-06-13 | 2026-06-25 | 34865.46 | 20
CO-R11-SL-TF-190 | Termination Works For Panel Board Cables of Street Lighting Network-[Road 14] | 12 | 2026-09-03 | 2026-09-16 | 2026-08-16 | 2026-08-29 | 0 | -16
CO-R14-SL-TF-380 | Testing Works For Panel Board Cables of Street Lighting Network-[Road 14] | 2 | 2026-09-17 | 2026-09-19 | 2026-08-30 | 2026-08-31 | 0 | -16
Medium Voltage Network |  | 7 | 2026-10-15 | 2026-10-22 | 2026-09-27 | 2026-10-04 | 0 | -16
Termination and Testing Works |  | 7 | 2026-10-15 | 2026-10-22 | 2026-09-27 | 2026-10-04 | 0 | -16
CO-R11-MV-TF-180 | Termination Works of Medium Voltage Network-[Road 14] | 7 | 2026-10-15 | 2026-10-22 | 2026-09-27 | 2026-10-04 | 0 | -16
Road Works |  | 25 | 2026-11-14 | 2026-12-12 | 2026-10-26 | 2026-11-23 | 929210.26 | -15
Bituminous Construction |  | 15 | 2026-11-14 | 2026-11-30 | 2026-10-26 | 2026-11-11 | 888935.43 | -16
CO-R11-S07-RD-F-110 | Application of Prime Coat Layer for Road Works- S.W 09-[Road 14] | 12 | 2026-11-14 | 2026-11-26 | 2026-10-26 | 2026-11-08 | 248802.26 | -16
CO-R11-S08-RD-F-140 | Application of Prime Coat Layer for Road Works- S.W 10-[Road 14] | 10 | 2026-11-16 | 2026-11-26 | 2026-10-28 | 2026-11-08 | 248802.26 | -16
CO-R11-S08-RD-F-150 | Bituminous Base & Wearing Courses Layers for Road Works- S.W 10-[Road 14] | 10 | 2026-11-19 | 2026-11-30 | 2026-11-01 | 2026-11-11 | 195665.46 | -16
CO-R11-S07-RD-F-120 | Bituminous Base & Wearing Courses Layers for Road Works- S.W 09-[Road 14] | 10 | 2026-11-19 | 2026-11-30 | 2026-11-01 | 2026-11-11 | 195665.46 | -16
Traffic Signs Boards and Roads Marking |  | 12 | 2026-11-29 | 2026-12-12 | 2026-11-10 | 2026-11-23 | 40274.83 | -15
CO-R11-S07-RD-F-100 | Installation Works of Traffic Signs Boards For Road Works- S.W 09-[Road 14] | 12 | 2026-11-29 | 2026-12-12 | 2026-11-10 | 2026-11-23 | 5630.68 | -16
CO-R11-S08-RD-F-170 | Application of Road Marking Works For Road Works- S.W 10-[Road 14] | 10 | 2026-12-01 | 2026-12-12 | 2026-11-12 | 2026-11-23 | 14506.73 | -16
CO-R11-S08-RD-F-130 | Installation Works of Traffic Signs Boards For Road Works- S.W 10-[Road 14] | 10 | 2026-12-01 | 2026-12-12 | 2026-11-12 | 2026-11-23 | 5630.68 | -15
CO-R11-S07-RD-F-160 | Application of Road Marking Works For Road Works- S.W 09-[Road 14] | 10 | 2026-12-01 | 2026-12-12 | 2026-11-12 | 2026-11-23 | 14506.73 | -16
Road 15 Local 1 ( 556 LM ) |  | 117 | 2026-08-11 | 2026-12-26 | 2026-06-27 | 2026-12-07 | 879744.69 | -15
Sewage Network |  | 27 | 2026-09-29 | 2026-10-29 | 2026-09-09 | 2026-10-11 | 44914.62 | -16
Testing and Finishes |  | 27 | 2026-09-29 | 2026-10-29 | 2026-09-09 | 2026-10-11 | 44914.62 | -16
CO-R15-SW-TF-100 | Final Testing For Main Line of Sewage Network-[Road 15] | 12 | 2026-09-29 | 2026-10-12 | 2026-09-09 | 2026-09-22 | 20768.02 | -16
CO-R15-SW-TF-110 | Install Manhole Cover Works for External Finishes of Sewage Network-[Road 15] | 12 | 2026-10-13 | 2026-10-26 | 2026-09-24 | 2026-10-07 | 12073.3 | -16
CO-R15-SW-TF-130 | Main Manhole Internal Finishes (Benching + Insulation) of Sewage Network-[Road 15] | 12 | 2026-10-17 | 2026-10-29 | 2026-09-28 | 2026-10-11 | 12073.3 | -16
Storm Drainage Network |  | 67 | 2026-09-10 | 2026-11-28 | 2026-08-23 | 2026-11-09 | 268610.58 | -16
Testing and Finishes |  | 67 | 2026-09-10 | 2026-11-28 | 2026-08-23 | 2026-11-09 | 268610.58 | -16
CO-R15-SD-TF-100 | Testing Work for Pipes of Storm Drainage Network-[Road 15] | 16 | 2026-09-10 | 2026-09-29 | 2026-08-23 | 2026-09-09 | 87978.78 | 0
CO-R15-SD-TF-110 | Install Catch Basin Cover Works for External Finishes of Storm Drainage Network-[Road 15] | 12 | 2026-10-10 | 2026-10-22 | 2026-09-20 | 2026-10-04 | 6827.34 | -12
CO-R15-SD-TF-120 | Main Manhole Internal Finishes (Benching + Insulation ) for Storm Drainage Network-[Road 15] | 12 | 2026-10-27 | 2026-11-09 | 2026-10-08 | 2026-10-21 | 166977.12 | -15
CO-R15-SD-TF-130 | Catch Basin Internal Finishes (Benching + Insulation ) for Storm Drainage Network-[Road 15] | 16 | 2026-11-10 | 2026-11-28 | 2026-10-22 | 2026-11-09 | 6827.34 | -16
Potable Water Network |  | 24 | 2026-10-13 | 2026-11-09 | 2026-09-24 | 2026-10-21 | 9843.19 | -16
Testing and Finishes |  | 24 | 2026-10-13 | 2026-11-09 | 2026-09-24 | 2026-10-21 | 9843.19 | -16
CO-R15-PW-TF-110 | Testing Work for Main Line of Potable Water Network-[Road 15] | 12 | 2026-10-13 | 2026-10-26 | 2026-09-24 | 2026-10-07 | 9843.19 | -16
CO-R15-PW-TF-100 | Final Finishes works and Covers for Valves and Valve Chambers of Potable Water Network-[Road 15] | 12 | 2026-10-13 | 2026-10-26 | 2026-09-24 | 2026-10-07 | 0 | -16
CO-R15-PW-TF-120 | Fire Hydrant Finishies (S.Box + Safety + Marker Post ) of Potable Water Network-[Road 15] | 12 | 2026-10-27 | 2026-11-09 | 2026-10-08 | 2026-10-21 | 0 | -16
Irrigation Network |  | 10 | 2026-10-05 | 2026-10-15 | 2026-09-15 | 2026-09-27 | 5248.07 | -9
Testing and Finishes |  | 10 | 2026-10-05 | 2026-10-15 | 2026-09-15 | 2026-09-27 | 5248.07 | -9
CO-R15-IR-TF-150 | Final Testing (pressure tests) of Irrigation Network-[Road 15] | 10 | 2026-10-05 | 2026-10-15 | 2026-09-15 | 2026-09-27 | 5248.07 | -9
Street Lighting Network |  | 62 | 2026-08-11 | 2026-10-22 | 2026-06-27 | 2026-10-04 | 20091.96 | -10
Termination and Testing Works |  | 62 | 2026-08-11 | 2026-10-22 | 2026-06-27 | 2026-10-04 | 20091.96 | -10
CO-R15-SL-TF-200 | Termination Works For Lighting Poles Cables of Street Lighting Network-[Road 15] | 12 | 2026-08-11 | 2026-08-24 | 2026-06-27 | 2026-07-09 | 20091.96 | 20
CO-R15-SL-TF-210 | Termination Works For Panel Board Cables of Street Lighting Network-[Road 15] | 12 | 2026-09-20 | 2026-10-04 | 2026-09-01 | 2026-09-14 | 0 | -16
CO-R15-SL-TF-380 | Testing Works For Panel Board Cables of Street Lighting Network-[Road 15] | 16 | 2026-10-05 | 2026-10-22 | 2026-09-15 | 2026-10-04 | 0 | -10
Medium Voltage Network |  | 7 | 2026-10-24 | 2026-10-31 | 2026-10-05 | 2026-10-12 | 0 | -16
Termination and Testing Works |  | 7 | 2026-10-24 | 2026-10-31 | 2026-10-05 | 2026-10-12 | 0 | -16
CO-R15-MV-TF-200 | Termination Works of Medium Voltage Network-[Road 15] | 7 | 2026-10-24 | 2026-10-31 | 2026-10-05 | 2026-10-12 | 0 | -16
Road Works |  | 25 | 2026-11-28 | 2026-12-26 | 2026-11-09 | 2026-12-07 | 531036.26 | -15
Bituminous Construction |  | 13 | 2026-11-28 | 2026-12-12 | 2026-11-09 | 2026-11-23 | 507007.63 | -16
CO-R15-S10-RD-F-140 | Application of Prime Coat Layer for Road Works- S.W 12-[Road 15] | 10 | 2026-11-28 | 2026-12-08 | 2026-11-09 | 2026-11-19 | 141904.59 | -16
CO-R15-S09-RD-F-110 | Application of Prime Coat Layer for Road Works- S.W 11-[Road 15] | 10 | 2026-11-28 | 2026-12-08 | 2026-11-09 | 2026-11-19 | 141904.59 | -16
CO-R15-S10-RD-F-150 | Bituminous Base & Wearing Courses Layers for Road Works- S.W 12-[Road 15] | 10 | 2026-12-01 | 2026-12-12 | 2026-11-12 | 2026-11-23 | 111599.22 | -16
CO-R15-S09-RD-F-120 | Bituminous Base & Wearing Courses Layers for Road Works- S.W 11-[Road 15] | 10 | 2026-12-01 | 2026-12-12 | 2026-11-12 | 2026-11-23 | 111599.22 | -16
Traffic Signs Boards and Roads Marking |  | 12 | 2026-12-13 | 2026-12-26 | 2026-11-24 | 2026-12-07 | 24028.64 | -15
CO-R15-S10-RD-F-170 | Application of Road Marking Works For Road Works- S.W 12-[Road 15] | 10 | 2026-12-13 | 2026-12-23 | 2026-11-24 | 2026-12-05 | 8274.04 | -16
CO-R15-S10-RD-F-130 | Installation Works of Traffic Signs Boards For Road Works- S.W 12-[Road 15] | 12 | 2026-12-13 | 2026-12-26 | 2026-11-24 | 2026-12-07 | 4178.79 | -15
CO-R15-S09-RD-F-160 | Application of Road Marking Works For Road Works- S.W 11-[Road 15] | 10 | 2026-12-13 | 2026-12-23 | 2026-11-24 | 2026-12-05 | 8274.04 | -16
CO-R15-S09-RD-F-100 | Installation Works of Traffic Signs Boards For Road Works- S.W 11-[Road 15] | 10 | 2026-12-13 | 2026-12-23 | 2026-11-24 | 2026-12-05 | 3301.76 | -16
Road 16 Local 1 ( 527 LM ) |  | 115 | 2026-08-25 | 2027-01-06 | 2026-07-11 | 2026-12-19 | 773713.29 | -15
Sewage Network |  | 27 | 2026-10-13 | 2026-11-12 | 2026-09-24 | 2026-10-25 | 28932.88 | -16
Testing and Finishes |  | 27 | 2026-10-13 | 2026-11-12 | 2026-09-24 | 2026-10-25 | 28932.88 | -16
CO-R16-SW-TF-100 | Final Testing For Main Line of Sewage Network-[Road 16] | 12 | 2026-10-13 | 2026-10-26 | 2026-09-24 | 2026-10-07 | 14883.24 | -16
CO-R16-SW-TF-110 | Install Manhole Cover Works for External Finishes of Sewage Network-[Road 16] | 12 | 2026-10-27 | 2026-11-09 | 2026-10-08 | 2026-10-21 | 7024.82 | -16
CO-R16-SW-TF-130 | Main Manhole Internal Finishes (Benching + Insulation) of Sewage Network-[Road 16] | 12 | 2026-10-31 | 2026-11-12 | 2026-10-12 | 2026-10-25 | 7024.82 | -16
Storm Drainage Network |  | 67 | 2026-09-30 | 2026-12-16 | 2026-09-10 | 2026-11-28 | 205611.77 | -16
Testing and Finishes |  | 67 | 2026-09-30 | 2026-12-16 | 2026-09-10 | 2026-11-28 | 205611.77 | -16
CO-R16-SD-TF-100 | Testing Work for Pipes of Storm Drainage Network-[Road 16] | 16 | 2026-09-30 | 2026-10-18 | 2026-09-10 | 2026-09-29 | 65471.79 | 0
CO-R16-SD-TF-110 | Install Catch Basin Cover Works for External Finishes of Storm Drainage Network-[Road 16] | 12 | 2026-10-24 | 2026-11-05 | 2026-10-05 | 2026-10-18 | 6507.08 | -12
CO-R16-SD-TF-120 | Main Manhole Internal Finishes (Benching + Insulation ) for Storm Drainage Network-[Road 16] | 12 | 2026-11-10 | 2026-11-23 | 2026-10-22 | 2026-11-04 | 127125.82 | -15
CO-R16-SD-TF-130 | Catch Basin Internal Finishes (Benching + Insulation ) for Storm Drainage Network-[Road 16] | 16 | 2026-11-29 | 2026-12-16 | 2026-11-10 | 2026-11-28 | 6507.08 | -16
Potable Water Network |  | 24 | 2026-10-27 | 2026-11-23 | 2026-10-08 | 2026-11-04 | 9456.46 | -16
Testing and Finishes |  | 24 | 2026-10-27 | 2026-11-23 | 2026-10-08 | 2026-11-04 | 9456.46 | -16
CO-R16-PW-TF-110 | Testing Work for Main Line of Potable Water Network-[Road 16] | 12 | 2026-10-27 | 2026-11-09 | 2026-10-08 | 2026-10-21 | 9456.46 | -16
CO-R16-PW-TF-100 | Final Finishes works and Covers for Valves and Valve Chambers of Potable Water Network-[Road 16] | 12 | 2026-10-27 | 2026-11-09 | 2026-10-08 | 2026-10-21 | 0 | -16
CO-R16-PW-TF-120 | Fire Hydrant Finishies (S.Box + Safety + Marker Post ) of Potable Water Network-[Road 16] | 12 | 2026-11-10 | 2026-11-23 | 2026-10-22 | 2026-11-04 | 0 | -16
Irrigation Network |  | 10 | 2026-10-17 | 2026-10-27 | 2026-09-28 | 2026-10-08 | 5001.98 | -9
Testing and Finishes |  | 10 | 2026-10-17 | 2026-10-27 | 2026-09-28 | 2026-10-08 | 5001.98 | -9
CO-R16-IR-TF-160 | Final Testing (pressure tests) of Irrigation Network-[Road 16] | 10 | 2026-10-17 | 2026-10-27 | 2026-09-28 | 2026-10-08 | 5001.98 | -9
Street Lighting Network |  | 52 | 2026-08-25 | 2026-10-25 | 2026-07-11 | 2026-10-06 | 18910.08 | -10
Termination and Testing Works |  | 52 | 2026-08-25 | 2026-10-25 | 2026-07-11 | 2026-10-06 | 18910.08 | -10
CO-R16-SL-TF-220 | Termination Works For Lighting Poles Cables of Street Lighting Network-[Road 16] | 12 | 2026-08-25 | 2026-09-07 | 2026-07-11 | 2026-07-23 | 18910.08 | 20
CO-R16-SL-TF-230 | Termination Works For Panel Board Cables of Street Lighting Network-[Road 16] | 12 | 2026-10-05 | 2026-10-18 | 2026-09-15 | 2026-09-29 | 0 | -16
CO-R16-SL-TF-380 | Testing Works For Panel Board Cables of Street Lighting Network-[Road 16] | 2 | 2026-10-24 | 2026-10-25 | 2026-10-05 | 2026-10-06 | 0 | -10
Medium Voltage Network |  | 7 | 2026-11-01 | 2026-11-08 | 2026-10-13 | 2026-10-20 | 0 | -16
Termination and Testing Works |  | 7 | 2026-11-01 | 2026-11-08 | 2026-10-13 | 2026-10-20 | 0 | -16
CO-R16-MV-TF-220 | Termination Works of Medium Voltage Network-[Road 16] | 7 | 2026-11-01 | 2026-11-08 | 2026-10-13 | 2026-10-20 | 0 | -16
Road Works |  | 25 | 2026-12-09 | 2027-01-06 | 2026-11-21 | 2026-12-19 | 505800.13 | -15
Bituminous Construction |  | 13 | 2026-12-09 | 2026-12-23 | 2026-11-21 | 2026-12-05 | 483233.48 | -16
CO-R16-S12-RD-F-140 | Application of Prime Coat Layer for Road Works- S.W 14-[Road 16] | 10 | 2026-12-09 | 2026-12-20 | 2026-11-21 | 2026-12-01 | 135251.56 | -16
CO-R16-S11-RD-F-110 | Application of Prime Coat Layer for Road Works - S.W 13-[Road 16] | 10 | 2026-12-09 | 2026-12-20 | 2026-11-21 | 2026-12-01 | 135251.56 | -16
CO-R16-S12-RD-F-150 | Bituminous Base & Wearing Courses Layers for Road Works- S.W 14-[Road 16] | 10 | 2026-12-13 | 2026-12-23 | 2026-11-24 | 2026-12-05 | 106365.18 | -16
CO-R16-S11-RD-F-120 | Bituminous Base & Wearing Courses Layers for Road Works- S.W 13-[Road 16] | 10 | 2026-12-13 | 2026-12-23 | 2026-11-24 | 2026-12-05 | 106365.18 | -16
Traffic Signs Boards and Roads Marking |  | 12 | 2026-12-24 | 2027-01-06 | 2026-12-06 | 2026-12-19 | 22566.65 | -15
CO-R16-S12-RD-F-170 | Application of Road Marking Works For Road Works- S.W 14-[Road 16] | 10 | 2026-12-24 | 2027-01-04 | 2026-12-06 | 2026-12-16 | 7885.75 | -16
CO-R16-S11-RD-F-160 | Application of Road Marking Works For Road Works- S.W 13-[Road 16] | 10 | 2026-12-24 | 2027-01-04 | 2026-12-06 | 2026-12-16 | 7885.75 | -16
CO-R16-S11-RD-F-100 | Installation Works of Traffic Signs Boards For Road Works- S.W 13-[Road 16] | 10 | 2026-12-24 | 2027-01-04 | 2026-12-06 | 2026-12-16 | 3397.57 | -16
CO-R16-S12-RD-F-130 | Installation Works of Traffic Signs Boards For Road Works- S.W 14-[Road 16] | 10 | 2026-12-27 | 2027-01-06 | 2026-12-08 | 2026-12-19 | 3397.57 | -15
Road 17 Local 1 ( 500 LM ) |  | 111 | 2026-09-08 | 2027-01-16 | 2026-07-25 | 2026-12-28 | 761880.98 | -16
Sewage Network |  | 27 | 2026-10-27 | 2026-11-26 | 2026-10-08 | 2026-11-08 | 28783.37 | -16
Testing and Finishes |  | 27 | 2026-10-27 | 2026-11-26 | 2026-10-08 | 2026-11-08 | 28783.37 | -16
CO-R17-SW-TF-100 | Final Testing For Main Line of Sewage Network-[Road 17] | 12 | 2026-10-27 | 2026-11-09 | 2026-10-08 | 2026-10-21 | 15594.88 | -16
CO-R17-SW-TF-110 | Install Manhole Cover Works for External Finishes of Sewage Network-[Road 17] | 12 | 2026-11-10 | 2026-11-23 | 2026-10-22 | 2026-11-04 | 6594.24 | -16
CO-R17-SW-TF-130 | Main Manhole Internal Finishes (Benching + Insulation) of Sewage Network-[Road 17] | 12 | 2026-11-14 | 2026-11-26 | 2026-10-26 | 2026-11-08 | 6594.24 | -16
Storm Drainage Network |  | 60 | 2026-10-22 | 2026-12-30 | 2026-10-04 | 2026-12-12 | 221766.94 | -16
Testing and Finishes |  | 60 | 2026-10-22 | 2026-12-30 | 2026-10-04 | 2026-12-12 | 221766.94 | -16
CO-R17-SD-TF-100 | Testing Work for Pipes of Storm Drainage Network-[Road 17] | 16 | 2026-10-22 | 2026-11-09 | 2026-10-04 | 2026-10-21 | 52222.09 | -3
CO-R17-SD-TF-110 | Install Catch Basin Cover Works for External Finishes of Storm Drainage Network-[Road 17] | 12 | 2026-11-07 | 2026-11-19 | 2026-10-19 | 2026-11-01 | 6187.05 | -12
CO-R17-SD-TF-120 | Main Manhole Internal Finishes (Benching + Insulation ) for Storm Drainage Network-[Road 17] | 12 | 2026-11-24 | 2026-12-07 | 2026-11-05 | 2026-11-18 | 157170.75 | -15
CO-R17-SD-TF-130 | Catch Basin Internal Finishes (Benching + Insulation ) for Storm Drainage Network-[Road 17] | 12 | 2026-12-17 | 2026-12-30 | 2026-11-29 | 2026-12-12 | 6187.05 | -16
Potable Water Network |  | 24 | 2026-11-10 | 2026-12-07 | 2026-10-22 | 2026-11-18 | 9062.59 | -16
Testing and Finishes |  | 24 | 2026-11-10 | 2026-12-07 | 2026-10-22 | 2026-11-18 | 9062.59 | -16
CO-R17-PW-TF-110 | Testing Work for Main Line of Potable Water Network-[Road 17] | 12 | 2026-11-10 | 2026-11-23 | 2026-10-22 | 2026-11-04 | 9062.59 | -16
CO-R17-PW-TF-100 | Final Finishes works and Covers for Valves and Valve Chambers of Potable Water Network-[Road 17] | 12 | 2026-11-10 | 2026-11-23 | 2026-10-22 | 2026-11-04 | 0 | -16
CO-R17-PW-TF-120 | Fire Hydrant Finishies (S.Box + Safety + Marker Post ) of Potable Water Network-[Road 17] | 12 | 2026-11-24 | 2026-12-07 | 2026-11-05 | 2026-11-18 | 0 | -16
Irrigation Network |  | 10 | 2026-11-05 | 2026-11-16 | 2026-10-18 | 2026-10-28 | 4755.81 | -16
Testing and Finishes |  | 10 | 2026-11-05 | 2026-11-16 | 2026-10-18 | 2026-10-28 | 4755.81 | -16
CO-R17-IR-TF-170 | Final Testing (pressure tests) of Irrigation Network-[Road 17] | 10 | 2026-11-05 | 2026-11-16 | 2026-10-18 | 2026-10-28 | 4755.81 | -16
Street Lighting Network |  | 48 | 2026-09-08 | 2026-11-03 | 2026-07-25 | 2026-10-15 | 18023.67 | -16
Termination and Testing Works |  | 48 | 2026-09-08 | 2026-11-03 | 2026-07-25 | 2026-10-15 | 18023.67 | -16
CO-R17-SL-TF-240 | Termination Works For Lighting Poles Cables of Street Lighting Network-[Road 17] | 12 | 2026-09-08 | 2026-09-21 | 2026-07-25 | 2026-08-06 | 18023.67 | 20
CO-R17-SL-TF-250 | Termination Works For Panel Board Cables of Street Lighting Network-[Road 17] | 12 | 2026-10-19 | 2026-11-01 | 2026-09-30 | 2026-10-13 | 0 | -16
CO-R17-SL-TF-380 | Testing Works For Panel Board Cables of Street Lighting Network-[Road 17] | 2 | 2026-11-02 | 2026-11-03 | 2026-10-14 | 2026-10-15 | 0 | -16
Medium Voltage Network |  | 7 | 2026-11-09 | 2026-11-16 | 2026-10-21 | 2026-10-28 | 0 | -16
Termination and Testing Works |  | 7 | 2026-11-09 | 2026-11-16 | 2026-10-21 | 2026-10-28 | 0 | -16
CO-R17-MV-TF-240 | Termination Works of Medium Voltage Network-[Road 17] | 7 | 2026-11-09 | 2026-11-16 | 2026-10-21 | 2026-10-28 | 0 | -16
Road Works |  | 23 | 2026-12-21 | 2027-01-16 | 2026-12-02 | 2026-12-28 | 479488.6 | -16
Bituminous Construction |  | 13 | 2026-12-21 | 2027-01-04 | 2026-12-02 | 2026-12-16 | 459452.03 | -16
CO-R17-S14-RD-F-140 | Application of Prime Coat Layer for Road Works- S.W 16-[Road 17] | 10 | 2026-12-21 | 2026-12-31 | 2026-12-02 | 2026-12-13 | 128594.88 | -16
CO-R17-S13-RD-F-110 | Application of Prime Coat Layer for Road Works- S.W 15-[Road 17] | 10 | 2026-12-21 | 2026-12-31 | 2026-12-02 | 2026-12-13 | 128594.88 | -16
CO-R17-S14-RD-F-150 | Bituminous Base & Wearing Courses Layers for Road Works- S.W 16-[Road 17] | 10 | 2026-12-24 | 2027-01-04 | 2026-12-06 | 2026-12-16 | 101131.14 | -16
CO-R17-S13-RD-F-120 | Bituminous Base & Wearing Courses Layers for Road Works- S.W 15-[Road 17] | 10 | 2026-12-24 | 2027-01-04 | 2026-12-06 | 2026-12-16 | 101131.14 | -16
Traffic Signs Boards and Roads Marking |  | 10 | 2027-01-05 | 2027-01-16 | 2026-12-17 | 2026-12-28 | 20036.56 | -16
CO-R17-S14-RD-F-170 | Application of Road Marking Works For Road Works- S.W 16-[Road 17] | 10 | 2027-01-05 | 2027-01-16 | 2026-12-17 | 2026-12-28 | 7497.74 | -16
CO-R17-S13-RD-F-160 | Application of Road Marking Works For Road Works- S.W 15-[Road 17] | 10 | 2027-01-05 | 2027-01-16 | 2026-12-17 | 2026-12-28 | 7497.74 | -16
CO-R17-S13-RD-F-100 | Installation Works of Traffic Signs Boards For Road Works- S.W 15-[Road 17] | 10 | 2027-01-05 | 2027-01-16 | 2026-12-17 | 2026-12-28 | 2520.54 | -16
CO-R17-S14-RD-F-130 | Installation Works of Traffic Signs Boards For Road Works- S.W 16-[Road 17] | 7 | 2027-01-09 | 2027-01-16 | 2026-12-21 | 2026-12-28 | 2520.54 | -16
Road 18 Local 1 ( 479 LM ) |  | 159 | 2026-07-05 | 2027-01-06 | 2026-06-16 | 2026-12-19 | 760061.88 | -8
Sewage Network |  | 24 | 2026-09-08 | 2026-10-06 | 2026-08-20 | 2026-09-16 | 29758.61 | 28
Testing and Finishes |  | 24 | 2026-09-08 | 2026-10-06 | 2026-08-20 | 2026-09-16 | 29758.61 | 28
CO-R18-SW-TF-100 | Final Testing For Main Line of Sewage Network-[Road 18] | 12 | 2026-09-08 | 2026-09-21 | 2026-08-20 | 2026-09-02 | 12906.7 | 28
CO-R18-SW-TF-110 | Install Manhole Cover Works for External Finishes of Sewage Network-[Road 18] | 12 | 2026-09-22 | 2026-10-06 | 2026-09-03 | 2026-09-16 | 8425.95 | 28
CO-R18-SW-TF-130 | Main Manhole Internal Finishes (Benching + Insulation) of Sewage Network-[Road 18] | 12 | 2026-09-22 | 2026-10-06 | 2026-09-03 | 2026-09-16 | 8425.95 | 28
Storm Drainage Network |  | 84 | 2026-08-22 | 2026-11-28 | 2026-08-03 | 2026-11-09 | 232600.88 | 12
Testing and Finishes |  | 84 | 2026-08-22 | 2026-11-28 | 2026-08-03 | 2026-11-09 | 232600.88 | 12
CO-R18-SD-TF-110 | Install Catch Basin Cover Works for External Finishes of Storm Drainage Network-[Road 18] | 16 | 2026-08-22 | 2026-09-08 | 2026-08-03 | 2026-08-20 | 5982.71 | 64
CO-R18-SD-TF-100 | Testing Work for Pipes of Storm Drainage Network-[Road 18] | 16 | 2026-10-22 | 2026-11-09 | 2026-10-04 | 2026-10-21 | 69261.98 | 12
CO-R18-SD-TF-120 | Main Manhole Internal Finishes (Benching + Insulation ) for Storm Drainage Network-[Road 18] | 16 | 2026-11-10 | 2026-11-28 | 2026-10-22 | 2026-11-09 | 151373.49 | 12
CO-R18-SD-TF-130 | Catch Basin Internal Finishes (Benching + Insulation ) for Storm Drainage Network-[Road 18] | 16 | 2026-11-10 | 2026-11-28 | 2026-10-22 | 2026-11-09 | 5982.71 | 12
Potable Water Network |  | 72 | 2026-09-14 | 2026-12-07 | 2026-08-26 | 2026-11-18 | 10265.7 | -16
Testing and Finishes |  | 72 | 2026-09-14 | 2026-12-07 | 2026-08-26 | 2026-11-18 | 10265.7 | -16
CO-R18-PW-TF-100 | Final Finishes works and Covers for Valves and Valve Chambers of Potable Water Network-[Road 18] | 12 | 2026-09-14 | 2026-09-28 | 2026-08-26 | 2026-09-08 | 0 | 32
CO-R18-PW-TF-120 | Fire Hydrant Finishies (S.Box + Safety + Marker Post ) of Potable Water Network-[Road 18] | 12 | 2026-09-29 | 2026-10-12 | 2026-09-09 | 2026-09-22 | 0 | 32
CO-R18-PW-TF-110 | Testing Work for Main Line of Potable Water Network-[Road 18] | 12 | 2026-11-24 | 2026-12-07 | 2026-11-05 | 2026-11-18 | 10265.7 | -16
Irrigation Network |  | 16 | 2026-09-05 | 2026-09-22 | 2026-08-17 | 2026-09-03 | 4598.97 | 30
Testing and Finishes |  | 16 | 2026-09-05 | 2026-09-22 | 2026-08-17 | 2026-09-03 | 4598.97 | 30
CO-R18-IR-TF-110 | Final Testing (pressure tests) of Irrigation Network-[Road 18] | 16 | 2026-09-05 | 2026-09-22 | 2026-08-17 | 2026-09-03 | 4598.97 | 30
Street Lighting Network |  | 76 | 2026-07-05 | 2026-10-01 | 2026-06-16 | 2026-09-12 | 17432.73 | 13
Termination and Testing Works |  | 76 | 2026-07-05 | 2026-10-01 | 2026-06-16 | 2026-09-12 | 17432.73 | 13
CO-R18-SL-TF-120 | Termination Works For Lighting Poles Cables of Street Lighting Network-[Road 18] | 12 | 2026-07-05 | 2026-07-19 | 2026-06-16 | 2026-06-30 | 17432.73 | 76
CO-R18-SL-TF-130 | Termination Works For Panel Board Cables of Street Lighting Network-[Road 18] | 12 | 2026-09-14 | 2026-09-29 | 2026-08-26 | 2026-09-09 | 0 | 13
CO-R18-SL-TF-380 | Testing Works For Panel Board Cables of Street Lighting Network-[Road 18] | 2 | 2026-09-29 | 2026-10-01 | 2026-09-09 | 2026-09-12 | 0 | 13
Medium Voltage Network |  | 16 | 2026-07-28 | 2026-08-15 | 2026-07-09 | 2026-07-27 | 0 | 63
Termination and Testing Works |  | 16 | 2026-07-28 | 2026-08-15 | 2026-07-09 | 2026-07-27 | 0 | 63
CO-R18-MV-TF-120 | Termination Works of Medium Voltage Network-[Road 18] | 16 | 2026-07-28 | 2026-08-15 | 2026-07-09 | 2026-07-27 | 0 | 63
Road Works |  | 61 | 2026-10-27 | 2027-01-06 | 2026-10-08 | 2026-12-19 | 465404.99 | -8
Bituminous Construction |  | 33 | 2026-10-27 | 2026-12-05 | 2026-10-08 | 2026-11-16 | 444300.05 | 6
CO-R18-S15-RD-F-100 | Application of Prime Coat Layer for Road Works- S.W 03-[Road 18] | 18 | 2026-10-27 | 2026-11-17 | 2026-10-08 | 2026-10-29 | 124355.48 | -2
CO-R18-S15-RD-F-110 | Bituminous Base & Wearing Courses Layers for Road Works- S.W 03-[Road 18] | 18 | 2026-10-31 | 2026-11-21 | 2026-10-12 | 2026-11-02 | 97794.54 | -2
CO-R18-S16-RD-F-150 | Application of Prime Coat Layer for Road Works- S.W 04-[Road 18] | 18 | 2026-11-10 | 2026-12-01 | 2026-10-22 | 2026-11-12 | 124355.48 | 6
CO-R18-S16-RD-F-170 | Bituminous Base & Wearing Courses Layers for Road Works- S.W 04-[Road 18] | 18 | 2026-11-14 | 2026-12-05 | 2026-10-26 | 2026-11-16 | 97794.54 | 6
Traffic Signs Boards and Roads Marking |  | 34 | 2026-11-28 | 2027-01-06 | 2026-11-09 | 2026-12-19 | 21104.95 | -8
CO-R18-S15-RD-F-120 | Application of Road Marking Works For Road Works- S.W 03-[Road 18] | 12 | 2026-11-28 | 2026-12-12 | 2026-11-09 | 2026-11-23 | 7250.71 | -8
CO-R18-S15-RD-F-130 | Installation Works of Traffic Signs Boards For Road Works- S.W 03-[Road 18] | 12 | 2026-12-12 | 2026-12-26 | 2026-11-23 | 2026-12-07 | 3301.76 | -8
CO-R18-S16-RD-F-140 | Application of Road Marking Works For Road Works- S.W 04-[Road 18] | 15 | 2026-12-19 | 2027-01-05 | 2026-11-30 | 2026-12-17 | 7250.71 | -7
CO-R18-S16-RD-F-160 | Installation Works of Traffic Signs Boards For Road Works- S.W 04-[Road 18] | 10 | 2026-12-26 | 2027-01-06 | 2026-12-07 | 2026-12-19 | 3301.76 | -8
Independent Works |  | 285 | 2026-02-09 | 2027-01-16 | 2026-01-21 | 2026-12-28 | 6378614.88 | -14
Tie In To Existing Networks |  | 100 | 2026-09-21 | 2027-01-16 | 2026-09-02 | 2026-12-28 | 0 | -14
Phase 2 Block "J" |  | 100 | 2026-09-21 | 2027-01-16 | 2026-09-02 | 2026-12-28 | 0 | -14
Road 09 Local 2 ( 2278 LM ) |  | 56 | 2026-11-04 | 2027-01-07 | 2026-10-17 | 2026-12-20 | 0 | -12
Storm Drainage Network |  | 7 | 2026-12-31 | 2027-01-07 | 2026-12-13 | 2026-12-20 | 0 | -12
TIE-SD-R09 | TIE IN Existing Network For Storm Drainage Network | 7 | 2026-12-31 | 2027-01-07 | 2026-12-13 | 2026-12-20 | 0 | -12
Sewage Network |  | 12 | 2026-11-28 | 2026-12-10 | 2026-11-09 | 2026-11-22 | 0 | 10
TIE-SW-R09 | TIE IN Existing Network For Sewage Network | 12 | 2026-11-28 | 2026-12-10 | 2026-11-09 | 2026-11-22 | 0 | 10
Potable Water Network |  | 12 | 2026-12-08 | 2026-12-21 | 2026-11-19 | 2026-12-02 | 0 | 1
TIE-PW-R09 | TIE IN Existing Network For Potable Water Network | 12 | 2026-12-08 | 2026-12-21 | 2026-11-19 | 2026-12-02 | 0 | 1
Irrigation Network |  | 12 | 2026-11-17 | 2026-11-30 | 2026-10-29 | 2026-11-11 | 0 | 19
TIE-IR-R09 | TIE IN Existing Network For Irrigation Network | 12 | 2026-11-17 | 2026-11-30 | 2026-10-29 | 2026-11-11 | 0 | 19
Meduim Voltage Network |  | 18 | 2026-11-17 | 2026-12-07 | 2026-10-29 | 2026-11-18 | 0 | 10
TIE-R09-MV | TIE IN Existing Network For Medium Voltage Network | 18 | 2026-11-17 | 2026-12-07 | 2026-10-29 | 2026-11-18 | 0 | 10
Street Lighting Network |  | 18 | 2026-11-04 | 2026-11-24 | 2026-10-17 | 2026-11-05 | 0 | 18
TIE-R09-SL | TIE IN Existing Network For Street Lighting Network | 18 | 2026-11-04 | 2026-11-24 | 2026-10-17 | 2026-11-05 | 0 | 18
Telecom Network |  | 10 | 2026-11-17 | 2026-11-28 | 2026-10-29 | 2026-11-09 | 0 | 8
TIE-R09-TE | TIE IN Existing Network For Telecom Network | 10 | 2026-11-17 | 2026-11-28 | 2026-10-29 | 2026-11-09 | 0 | 8
Road 10 Local 2 ( 2352 LM ) |  | 63 | 2026-11-04 | 2027-01-16 | 2026-10-17 | 2026-12-28 | 0 | -14
Storm Drainage Network |  | 7 | 2026-12-31 | 2027-01-07 | 2026-12-13 | 2026-12-20 | 0 | -12
TIE-SD-R10 | TIE IN Existing Network For Storm Drainage Network | 7 | 2026-12-31 | 2027-01-07 | 2026-12-13 | 2026-12-20 | 0 | -12
Sewage Network |  | 12 | 2026-11-28 | 2026-12-10 | 2026-11-09 | 2026-11-22 | 0 | 10
TIE-SW-R10 | TIE IN Existing Network For Sewage Network | 12 | 2026-11-28 | 2026-12-10 | 2026-11-09 | 2026-11-22 | 0 | 10
Potable Water Network |  | 12 | 2026-12-08 | 2026-12-21 | 2026-11-19 | 2026-12-02 | 0 | 1
TIE-PW-R10 | TIE IN Existing Network For Potable Water Network | 12 | 2026-12-08 | 2026-12-21 | 2026-11-19 | 2026-12-02 | 0 | 1
Irrigation Network |  | 12 | 2026-11-17 | 2026-11-30 | 2026-10-29 | 2026-11-11 | 0 | 19
TIE-IR-R10 | TIE IN Existing Network For Irrigation Network | 12 | 2026-11-17 | 2026-11-30 | 2026-10-29 | 2026-11-11 | 0 | 19
Meduim Voltage Network |  | 18 | 2026-11-17 | 2026-12-07 | 2026-10-29 | 2026-11-18 | 0 | 10
TIE-R10-MV | TIE IN Existing Network For Medium Voltage Network | 18 | 2026-11-17 | 2026-12-07 | 2026-10-29 | 2026-11-18 | 0 | 10
Street Lighting Network |  | 18 | 2026-11-04 | 2026-11-24 | 2026-10-17 | 2026-11-05 | 0 | 18
TIE-R10-SL | TIE IN Existing Network For Street Lighting Network | 18 | 2026-11-04 | 2026-11-24 | 2026-10-17 | 2026-11-05 | 0 | 18
Telecom Network |  | 10 | 2026-11-17 | 2026-11-28 | 2026-10-29 | 2026-11-09 | 0 | 8
TIE-R10-TE | TIE IN Existing Network For Telecom Network | 10 | 2026-11-17 | 2026-11-28 | 2026-10-29 | 2026-11-09 | 0 | 8
Road Works |  | 5 | 2027-01-11 | 2027-01-16 | 2026-12-23 | 2026-12-28 | 0 | -14
TIE-R10-RD | TIE IN Existing Network For Road Works | 5 | 2027-01-11 | 2027-01-16 | 2026-12-23 | 2026-12-28 | 0 | -14
Road 11 Local 1 ( 670 LM ) |  | 63 | 2026-11-04 | 2027-01-16 | 2026-10-17 | 2026-12-28 | 0 | -14
Storm Drainage Network |  | 7 | 2026-12-31 | 2027-01-07 | 2026-12-13 | 2026-12-20 | 0 | -12
TIE-SD-R11 | TIE IN Existing Network For Storm Drainage Network | 7 | 2026-12-31 | 2027-01-07 | 2026-12-13 | 2026-12-20 | 0 | -12
Sewage Network |  | 12 | 2026-11-28 | 2026-12-10 | 2026-11-09 | 2026-11-22 | 0 | 10
TIE-SW-R11 | TIE IN Existing Network For Sewage Network | 12 | 2026-11-28 | 2026-12-10 | 2026-11-09 | 2026-11-22 | 0 | 10
Potable Water Network |  | 12 | 2026-12-08 | 2026-12-21 | 2026-11-19 | 2026-12-02 | 0 | 1
TIE-PW-R11 | TIE IN Existing Network For Potable Water Network | 12 | 2026-12-08 | 2026-12-21 | 2026-11-19 | 2026-12-02 | 0 | 1
Irrigation Network |  | 12 | 2026-11-17 | 2026-11-30 | 2026-10-29 | 2026-11-11 | 0 | 19
TIE-IR-R11 | TIE IN Existing Network For Irrigation Network | 12 | 2026-11-17 | 2026-11-30 | 2026-10-29 | 2026-11-11 | 0 | 19
Meduim Voltage Network |  | 18 | 2026-11-17 | 2026-12-07 | 2026-10-29 | 2026-11-18 | 0 | 10
TIE-R11-MV | TIE IN Existing Network For Medium Voltage Network | 18 | 2026-11-17 | 2026-12-07 | 2026-10-29 | 2026-11-18 | 0 | 10
Street Lighting Network |  | 18 | 2026-11-04 | 2026-11-24 | 2026-10-17 | 2026-11-05 | 0 | 18
TIE-R11-SL | TIE IN Existing Network For Street Lighting Network | 18 | 2026-11-04 | 2026-11-24 | 2026-10-17 | 2026-11-05 | 0 | 18
Telecom Network |  | 10 | 2026-11-17 | 2026-11-28 | 2026-10-29 | 2026-11-09 | 0 | 8
TIE-R11-TE | TIE IN Existing Network For Telecom Network | 10 | 2026-11-17 | 2026-11-28 | 2026-10-29 | 2026-11-09 | 0 | 8
Road Works |  | 5 | 2027-01-11 | 2027-01-16 | 2026-12-23 | 2026-12-28 | 0 | -14
TIE-R11-RD | TIE IN Existing Network For Road Works | 5 | 2027-01-11 | 2027-01-16 | 2026-12-23 | 2026-12-28 | 0 | -14
Road 14 Local 1 ( 584 LM ) |  | 63 | 2026-11-04 | 2027-01-16 | 2026-10-17 | 2026-12-28 | 0 | -14
Storm Drainage Network |  | 7 | 2026-12-31 | 2027-01-07 | 2026-12-13 | 2026-12-20 | 0 | -12
TIE-SD-R14 | TIE IN Existing Network For Storm Drainage Network | 7 | 2026-12-31 | 2027-01-07 | 2026-12-13 | 2026-12-20 | 0 | -12
Sewage Network |  | 12 | 2026-11-28 | 2026-12-10 | 2026-11-09 | 2026-11-22 | 0 | 10
TIE-SW-R14 | TIE IN Existing Network For Sewage Network | 12 | 2026-11-28 | 2026-12-10 | 2026-11-09 | 2026-11-22 | 0 | 10
Potable Water Network |  | 12 | 2026-12-08 | 2026-12-21 | 2026-11-19 | 2026-12-02 | 0 | 1
TIE-PW-R14 | TIE IN Existing Network For Potable Water Network | 12 | 2026-12-08 | 2026-12-21 | 2026-11-19 | 2026-12-02 | 0 | 1
Irrigation Network |  | 12 | 2026-11-17 | 2026-11-30 | 2026-10-29 | 2026-11-11 | 0 | 19
TIE-IR-R14 | TIE IN Existing Network For Irrigation Network | 12 | 2026-11-17 | 2026-11-30 | 2026-10-29 | 2026-11-11 | 0 | 19
Meduim Voltage Network |  | 18 | 2026-11-17 | 2026-12-07 | 2026-10-29 | 2026-11-18 | 0 | 10
TIE-R14-MV | TIE IN Existing Network For Medium Voltage Network | 18 | 2026-11-17 | 2026-12-07 | 2026-10-29 | 2026-11-18 | 0 | 10
Street Lighting Network |  | 18 | 2026-11-04 | 2026-11-24 | 2026-10-17 | 2026-11-05 | 0 | 18
TIE-R14-SL | TIE IN Existing Network For Street Lighting Network | 18 | 2026-11-04 | 2026-11-24 | 2026-10-17 | 2026-11-05 | 0 | 18
Telecom Network |  | 10 | 2026-11-17 | 2026-11-28 | 2026-10-29 | 2026-11-09 | 0 | 8
TIE-R14-TE | TIE IN Existing Network For Telecom Network | 10 | 2026-11-17 | 2026-11-28 | 2026-10-29 | 2026-11-09 | 0 | 8
Road Works |  | 5 | 2027-01-11 | 2027-01-16 | 2026-12-23 | 2026-12-28 | 0 | -14
TIE-R14-RD | TIE IN Existing Network For Road Works | 5 | 2027-01-11 | 2027-01-16 | 2026-12-23 | 2026-12-28 | 0 | -14
Road 15 Local 1 ( 556 LM ) |  | 56 | 2026-11-04 | 2027-01-07 | 2026-10-17 | 2026-12-20 | 0 | -12
Storm Drainage Network |  | 7 | 2026-12-31 | 2027-01-07 | 2026-12-13 | 2026-12-20 | 0 | -12
TIE-SD-R15 | TIE IN Existing Network For Storm Drainage Network | 7 | 2026-12-31 | 2027-01-07 | 2026-12-13 | 2026-12-20 | 0 | -12
Sewage Network |  | 12 | 2026-11-28 | 2026-12-10 | 2026-11-09 | 2026-11-22 | 0 | 10
TIE-SW-R15 | TIE IN Existing Network For Sewage Network | 12 | 2026-11-28 | 2026-12-10 | 2026-11-09 | 2026-11-22 | 0 | 10
Potable Water Network |  | 12 | 2026-12-08 | 2026-12-21 | 2026-11-19 | 2026-12-02 | 0 | 1
TIE-PW-R15 | TIE IN Existing Network For Potable Water Network | 12 | 2026-12-08 | 2026-12-21 | 2026-11-19 | 2026-12-02 | 0 | 1
Irrigation Network |  | 12 | 2026-11-17 | 2026-11-30 | 2026-10-29 | 2026-11-11 | 0 | 19
TIE-IR-R15 | TIE IN Existing Network For Irrigation Network | 12 | 2026-11-17 | 2026-11-30 | 2026-10-29 | 2026-11-11 | 0 | 19
Meduim Voltage Network |  | 18 | 2026-11-17 | 2026-12-07 | 2026-10-29 | 2026-11-18 | 0 | 10
TIE-R15-MV | TIE IN Existing Network For Medium Voltage Network | 18 | 2026-11-17 | 2026-12-07 | 2026-10-29 | 2026-11-18 | 0 | 10
Street Lighting Network |  | 18 | 2026-11-04 | 2026-11-24 | 2026-10-17 | 2026-11-05 | 0 | 18
TIE-R15-SL | TIE IN Existing Network For Street Lighting Network | 18 | 2026-11-04 | 2026-11-24 | 2026-10-17 | 2026-11-05 | 0 | 18
Telecom Network |  | 10 | 2026-11-17 | 2026-11-28 | 2026-10-29 | 2026-11-09 | 0 | 8
TIE-R15-TE | TIE IN Existing Network For Telecom Network | 10 | 2026-11-17 | 2026-11-28 | 2026-10-29 | 2026-11-09 | 0 | 8
Road 16 Local 1 ( 527 LM ) |  | 56 | 2026-11-04 | 2027-01-07 | 2026-10-17 | 2026-12-20 | 0 | -12
Storm Drainage Network |  | 7 | 2026-12-31 | 2027-01-07 | 2026-12-13 | 2026-12-20 | 0 | -12
TIE-SD-R16 | TIE IN Existing Network For Storm Drainage Network | 7 | 2026-12-31 | 2027-01-07 | 2026-12-13 | 2026-12-20 | 0 | -12
Sewage Network |  | 12 | 2026-11-28 | 2026-12-10 | 2026-11-09 | 2026-11-22 | 0 | 10
TIE-SW-R16 | TIE IN Existing Network For Sewage Network | 12 | 2026-11-28 | 2026-12-10 | 2026-11-09 | 2026-11-22 | 0 | 10
Potable Water Network |  | 12 | 2026-12-08 | 2026-12-21 | 2026-11-19 | 2026-12-02 | 0 | 1
TIE-PW-R16 | TIE IN Existing Network For Potable Water Network | 12 | 2026-12-08 | 2026-12-21 | 2026-11-19 | 2026-12-02 | 0 | 1
Irrigation Network |  | 12 | 2026-11-17 | 2026-11-30 | 2026-10-29 | 2026-11-11 | 0 | 19
TIE-IR-R16 | TIE IN Existing Network For Irrigation Network | 12 | 2026-11-17 | 2026-11-30 | 2026-10-29 | 2026-11-11 | 0 | 19
Meduim Voltage Network |  | 18 | 2026-11-17 | 2026-12-07 | 2026-10-29 | 2026-11-18 | 0 | 10
TIE-R16-MV | TIE IN Existing Network For Medium Voltage Network | 18 | 2026-11-17 | 2026-12-07 | 2026-10-29 | 2026-11-18 | 0 | 10
Street Lighting Network |  | 18 | 2026-11-04 | 2026-11-24 | 2026-10-17 | 2026-11-05 | 0 | 18
TIE-R16-SL | TIE IN Existing Network For Street Lighting Network | 18 | 2026-11-04 | 2026-11-24 | 2026-10-17 | 2026-11-05 | 0 | 18
Telecom Network |  | 10 | 2026-11-17 | 2026-11-28 | 2026-10-29 | 2026-11-09 | 0 | 8
TIE-R16-TE | TIE IN Existing Network For Telecom Network | 10 | 2026-11-17 | 2026-11-28 | 2026-10-29 | 2026-11-09 | 0 | 8
Road 17 Local 1 ( 500 LM ) |  | 56 | 2026-11-04 | 2027-01-07 | 2026-10-17 | 2026-12-20 | 0 | -12
Storm Drainage Network |  | 7 | 2026-12-31 | 2027-01-07 | 2026-12-13 | 2026-12-20 | 0 | -12
TIE-SD-R17 | TIE IN Existing Network For Storm Drainage Network | 7 | 2026-12-31 | 2027-01-07 | 2026-12-13 | 2026-12-20 | 0 | -12
Sewage Network |  | 12 | 2026-11-28 | 2026-12-10 | 2026-11-09 | 2026-11-22 | 0 | 10
TIE-SW-R17 | TIE IN Existing Network For Sewage Network | 12 | 2026-11-28 | 2026-12-10 | 2026-11-09 | 2026-11-22 | 0 | 10
Potable Water Network |  | 12 | 2026-12-08 | 2026-12-21 | 2026-11-19 | 2026-12-02 | 0 | 1
TIE-PW-R17 | TIE IN Existing Network For Potable Water Network | 12 | 2026-12-08 | 2026-12-21 | 2026-11-19 | 2026-12-02 | 0 | 1
Irrigation Network |  | 12 | 2026-11-17 | 2026-11-30 | 2026-10-29 | 2026-11-11 | 0 | 19
TIE-IR-R17 | TIE IN Existing Network For Irrigation Network | 12 | 2026-11-17 | 2026-11-30 | 2026-10-29 | 2026-11-11 | 0 | 19
Meduim Voltage Network |  | 18 | 2026-11-17 | 2026-12-07 | 2026-10-29 | 2026-11-18 | 0 | 10
TIE-R17-MV | TIE IN Existing Network For Medium Voltage Network | 18 | 2026-11-17 | 2026-12-07 | 2026-10-29 | 2026-11-18 | 0 | 10
Street Lighting Network |  | 18 | 2026-11-04 | 2026-11-24 | 2026-10-17 | 2026-11-05 | 0 | 18
TIE-R17-SL | TIE IN Existing Network For Street Lighting Network | 18 | 2026-11-04 | 2026-11-24 | 2026-10-17 | 2026-11-05 | 0 | 18
Telecom Network |  | 10 | 2026-11-17 | 2026-11-28 | 2026-10-29 | 2026-11-09 | 0 | 8
TIE-R17-TE | TIE IN Existing Network For Telecom Network | 10 | 2026-11-17 | 2026-11-28 | 2026-10-29 | 2026-11-09 | 0 | 8
Road 18 Local 1 ( 479 LM ) |  | 93 | 2026-09-21 | 2027-01-07 | 2026-09-02 | 2026-12-20 | 0 | -12
Storm Drainage Network |  | 7 | 2026-12-31 | 2027-01-07 | 2026-12-13 | 2026-12-20 | 0 | -12
TIE-SD-R18 | TIE IN Existing Network For Storm Drainage Network | 7 | 2026-12-31 | 2027-01-07 | 2026-12-13 | 2026-12-20 | 0 | -12
Sewage Network |  | 12 | 2026-11-28 | 2026-12-10 | 2026-11-09 | 2026-11-22 | 0 | 10
TIE-SW-R18 | TIE IN Existing Network For Sewage Network | 12 | 2026-11-28 | 2026-12-10 | 2026-11-09 | 2026-11-22 | 0 | 10
Potable Water Network |  | 12 | 2026-12-08 | 2026-12-21 | 2026-11-19 | 2026-12-02 | 0 | 1
TIE-PW-R18 | TIE IN Existing Network For Potable Water Network | 12 | 2026-12-08 | 2026-12-21 | 2026-11-19 | 2026-12-02 | 0 | 1
Irrigation Network |  | 12 | 2026-11-17 | 2026-11-30 | 2026-10-29 | 2026-11-11 | 0 | 19
TIE-IR-R18 | TIE IN Existing Network For Irrigation Network | 12 | 2026-11-17 | 2026-11-30 | 2026-10-29 | 2026-11-11 | 0 | 19
Meduim Voltage Network |  | 18 | 2026-11-17 | 2026-12-07 | 2026-10-29 | 2026-11-18 | 0 | 10
TIE-R18-MV10 | TIE IN Existing Network For Medium Voltage Network | 18 | 2026-11-17 | 2026-12-07 | 2026-10-29 | 2026-11-18 | 0 | 10
Street Lighting Network |  | 18 | 2026-11-04 | 2026-11-24 | 2026-10-17 | 2026-11-05 | 0 | 18
TIE-R18-SL10 | TIE IN Existing Network For Street Lighting Network | 18 | 2026-11-04 | 2026-11-24 | 2026-10-17 | 2026-11-05 | 0 | 18
Telecom Network |  | 12 | 2026-09-21 | 2026-10-05 | 2026-09-02 | 2026-09-15 | 0 | 54
TIE-R18-TE10 | TIE IN Existing Network For Telecom Network | 12 | 2026-09-21 | 2026-10-05 | 2026-09-02 | 2026-09-15 | 0 | 54
Sewage Pump Stations |  | 221 | 2026-04-06 | 2026-12-24 | 2026-03-15 | 2026-12-01 | 4389808.32 | -16
Sewage Pump Station ( PS 06 ) |  | 221 | 2026-04-06 | 2026-12-24 | 2026-03-15 | 2026-12-01 | 4389808.32 | -16
Pump Station Main Building |  | 206 | 2026-04-06 | 2026-12-07 | 2026-03-15 | 2026-10-06 | 1526800.69 | -16
CO-SW-PS7-MB-100 | Excavation Main Bulding | 15 | 2026-04-06 | 2026-04-22 | 2026-03-15 | 2026-04-04 | 9567.6 | -12
CO-SW-PS7-MB-110 | Concrete Works of Superstrucure | 30 | 2026-04-23 | 2026-06-01 | 2026-04-05 | 2026-05-09 | 66973.2 | -12
CO-SW-PS7-MB-120 | Internal Finishes Works of Superstrucure | 30 | 2026-06-02 | 2026-07-06 | 2026-05-10 | 2026-06-17 | 19135.2 | -12
CO-SW-PS7-MB-130 | Internal Electrical Works | 30 | 2026-07-07 | 2026-08-10 | 2026-06-18 | 2026-07-22 | 697563.13 | 25
CO-SW-PS7-MB-140 | Internal Mechanical Works | 30 | 2026-08-11 | 2026-09-14 | 2026-07-23 | 2026-08-26 | 572620.86 | 25
CO-SW-PS7-MB-150 | Electromechanical Main Works | 30 | 2026-11-03 | 2026-12-07 | 2026-09-01 | 2026-10-06 | 160940.7 | -16
Generator With Umbrella Tank |  | 75 | 2026-07-07 | 2026-10-03 | 2026-06-18 | 2026-09-13 | 215256.93 | -12
CO-SW-PS7-GN-100 | Concrete Works of Base | 12 | 2026-07-07 | 2026-07-20 | 2026-06-18 | 2026-07-01 | 43051.39 | -12
CO-SW-PS7-GN-110 | Install Manually Operated Fuel Pump | 21 | 2026-07-21 | 2026-08-13 | 2026-07-02 | 2026-07-26 | 107628.47 | -12
CO-SW-PS7-GN-120 | Install Ground Fuel Tank | 21 | 2026-08-15 | 2026-09-07 | 2026-07-27 | 2026-08-19 | 43051.39 | -12
CO-SW-PS7-GN-130 | Fix Steel Structure for Umbrella | 21 | 2026-09-08 | 2026-10-03 | 2026-08-20 | 2026-09-13 | 21525.69 | -12
Motor Control Centre Building |  | 152 | 2026-06-02 | 2026-11-26 | 2026-05-10 | 2026-10-03 | 1971444.87 | -7
CO-SW-PS7-MCC-100 | Excavation Main Bulding | 16 | 2026-06-02 | 2026-06-20 | 2026-05-10 | 2026-06-01 | 96.48 | 24
CO-SW-PS7-MCC-110 | Concrete Works of Superstrucure | 21 | 2026-06-21 | 2026-07-14 | 2026-06-02 | 2026-06-25 | 108089.67 | 24
CO-SW-PS7-MCC-120 | Internal Finishes Works of Superstrucure | 21 | 2026-07-15 | 2026-08-08 | 2026-06-27 | 2026-07-20 | 65710.36 | 24
CO-SW-PS7-MCC-130 | Internal Electrical Works | 21 | 2026-08-09 | 2026-09-01 | 2026-07-21 | 2026-08-13 | 298746.3 | 24
CO-SW-PS7-MCC-140 | Internal Mechanical Works | 21 | 2026-09-02 | 2026-09-27 | 2026-08-15 | 2026-09-07 | 75272.49 | 24
CO-SW-PS7-MCC-150 | Electromechanical Main Works | 21 | 2026-11-03 | 2026-11-26 | 2026-09-08 | 2026-10-03 | 1423529.57 | -7
Simple Building Works |  | 50 | 2026-10-04 | 2026-11-30 | 2026-09-14 | 2026-11-11 | 468575.93 | -10
CO-SW-PS7-SBL-100 | Perimeter Fencing | 23 | 2026-10-04 | 2026-10-29 | 2026-09-14 | 2026-10-11 | 73149.3 | -12
CO-SW-PS7-SBL-110 | Outside Lighting | 27 | 2026-10-31 | 2026-11-30 | 2026-10-12 | 2026-11-11 | 16425.72 | -10
CO-SW-PS7-SBL-120 | Outside Duct Works | 23 | 2026-10-31 | 2026-11-25 | 2026-10-12 | 2026-11-07 | 9922.7 | -12
CO-SW-PS7-SBL-130 | Rectangular Wet Wells | 27 | 2026-10-31 | 2026-11-30 | 2026-10-12 | 2026-11-11 | 147819.42 | -10
CO-SW-PS7-SBL-140 | Round Wet Well Structure for basket screen | 27 | 2026-10-31 | 2026-11-30 | 2026-10-12 | 2026-11-11 | 67770.5 | -10
CO-SW-PS7-SBL-150 | Motorized basket screen | 27 | 2026-10-31 | 2026-11-30 | 2026-10-12 | 2026-11-11 | 153488.29 | -10
Site Work and Service Road |  | 25 | 2026-11-26 | 2026-12-24 | 2026-11-08 | 2026-12-01 | 207729.9 | -16
CO-SW-PS7-SWS-100 | Outside Strom Drainage System | 6 | 2026-11-26 | 2026-12-02 | 2026-11-08 | 2026-11-14 | 40230 | -12
CO-SW-PS7-SWS-110 | Bituminous Works | 15 | 2026-12-08 | 2026-12-24 | 2026-11-15 | 2026-12-01 | 167499.9 | -16
Storm Drainage Ponds |  | 178 | 2026-02-09 | 2026-09-12 | 2026-01-21 | 2026-08-24 | 1988806.56 | 24
Storm Drainage Pond ( PO-J1) |  | 157 | 2026-02-09 | 2026-08-18 | 2026-01-21 | 2026-07-30 | 1702195.3 | 35
CO-SD-PO-K1-100-P1 | Excavation & Filling Works - PART 1 | 21 | 2026-02-09 | 2026-03-04 | 2026-01-21 | 2026-02-14 | 418373.13 | 24
CO-SD-PO-K1-110-P1 | Finished Grouted Riprap - PART 1 | 21 | 2026-03-05 | 2026-04-01 | 2026-02-15 | 2026-03-10 | 5740.56 | 35
CO-SD-PO-K1-100-P2 | Excavation & Filling Works - PART 2 | 21 | 2026-03-05 | 2026-04-01 | 2026-02-15 | 2026-03-10 | 418373.13 | 35
CO-SD-PO-K1-110-P2 | Finished Grouted Riprap - PART 2 | 21 | 2026-04-02 | 2026-04-26 | 2026-03-11 | 2026-04-07 | 5740.56 | 35
CO-SD-PO-K1-100-P3 | Excavation & Filling Works - PART 3 | 21 | 2026-04-02 | 2026-04-26 | 2026-03-11 | 2026-04-07 | 418373.13 | 35
CO-SD-PO-K1-110-P3 | Finished Grouted Riprap - PART 3 | 21 | 2026-04-27 | 2026-05-20 | 2026-04-08 | 2026-05-02 | 5740.56 | 35
CO-SD-PO-K1-100-P4 | Excavation & Filling Works - PART 4 | 21 | 2026-04-27 | 2026-05-20 | 2026-04-08 | 2026-05-02 | 418373.13 | 35
CO-SD-PO-K1-110-P4 | Finished Grouted Riprap - PART 4 | 21 | 2026-05-21 | 2026-06-18 | 2026-05-03 | 2026-05-31 | 5740.56 | 35
CO-SD-PO-K1-120 | Outfall structure | 26 | 2026-06-20 | 2026-07-19 | 2026-06-01 | 2026-06-30 | 2870.28 | 35
CO-SD-PO-K1-130 | Acess Entrace Ramp | 26 | 2026-07-20 | 2026-08-18 | 2026-07-01 | 2026-07-30 | 2870.28 | 35
Storm Drainage Pond ( PO-J2) |  | 157 | 2026-03-05 | 2026-09-12 | 2026-02-15 | 2026-08-24 | 286611.26 | 24
CO-SD-PO-K2-100-P1 | Excavation & Filling Works - PART 1 | 21 | 2026-03-05 | 2026-04-01 | 2026-02-15 | 2026-03-10 | 68423.75 | 24
CO-SD-PO-K2-110-P1 | Finished Grouted Riprap - PART 1 | 21 | 2026-04-02 | 2026-04-26 | 2026-03-11 | 2026-04-07 | 2583.25 | 24
CO-SD-PO-K2-100-P2 | Excavation & Filling Works - PART 2 | 21 | 2026-04-02 | 2026-04-26 | 2026-03-11 | 2026-04-07 | 68423.75 | 24
CO-SD-PO-K2-110-P2 | Finished Grouted Riprap - PART 2 | 21 | 2026-04-27 | 2026-05-20 | 2026-04-08 | 2026-05-02 | 2583.25 | 24
CO-SD-PO-K2-100-P3 | Excavation & Filling Works - PART 3 | 21 | 2026-04-27 | 2026-05-20 | 2026-04-08 | 2026-05-02 | 68423.75 | 24
CO-SD-PO-K2-110-P3 | Finished Grouted Riprap - PART 3 | 21 | 2026-05-21 | 2026-06-18 | 2026-05-03 | 2026-05-31 | 2583.25 | 24
CO-SD-PO-K2-100-P4 | Excavation & Filling Works - PART 4 | 21 | 2026-05-21 | 2026-06-18 | 2026-05-03 | 2026-05-31 | 68423.75 | 24
CO-SD-PO-K2-110-P4 | Finished Grouted Riprap - PART 4 | 21 | 2026-06-20 | 2026-07-13 | 2026-06-01 | 2026-06-24 | 2583.25 | 24
CO-SD-PO-K2-120 | Outfall structure | 26 | 2026-07-14 | 2026-08-12 | 2026-06-25 | 2026-07-25 | 1291.63 | 24
CO-SD-PO-K2-130 | Acess Entrace Ramp | 26 | 2026-08-13 | 2026-09-12 | 2026-07-26 | 2026-08-24 | 1291.63 | 24
Testing and Comissioning |  | 114 | 2026-09-13 | 2027-01-24 | 2026-08-25 | 2027-01-03 | 11395586.42 | -16
Infrastructure Networks |  | 52 | 2026-11-25 | 2027-01-24 | 2026-11-07 | 2027-01-03 | 11075668.52 | -16
Irrigation Network |  | 12 | 2026-12-01 | 2026-12-14 | 2026-11-12 | 2026-11-25 | 624273.76 | 19
T/C-IR | Testing and Commissioning of Irrigation Network | 12 | 2026-12-01 | 2026-12-14 | 2026-11-12 | 2026-11-25 | 624273.76 | 19
Potable Water Network |  | 12 | 2026-12-22 | 2027-01-04 | 2026-12-03 | 2026-12-16 | 1022094.2 | 1
T/C-PW | Testing and Commissioning of Potable Water Network | 12 | 2026-12-22 | 2027-01-04 | 2026-12-03 | 2026-12-16 | 1022094.2 | 1
Sewage Network |  | 12 | 2027-01-11 | 2027-01-24 | 2026-12-19 | 2026-12-31 | 2308897.1 | -16
T/C-SW | Testing and Commissioning of Sewage Network | 12 | 2027-01-11 | 2027-01-24 | 2026-12-19 | 2026-12-31 | 2308897.1 | -16
Storm Drainage Network |  | 10 | 2027-01-09 | 2027-01-19 | 2026-12-21 | 2026-12-31 | 2866651.2 | -12
T/C-SD | Testing and Commissioning of Storm Drainage Network | 10 | 2027-01-09 | 2027-01-19 | 2026-12-21 | 2026-12-31 | 2866651.2 | -12
Street Lighting Network |  | 18 | 2026-11-25 | 2026-12-15 | 2026-11-07 | 2026-11-26 | 462378.2 | 18
T/C-SL | Testing and Commissioning of Street Lighting Network | 18 | 2026-11-25 | 2026-12-15 | 2026-11-07 | 2026-11-26 | 462378.2 | 18
Telecom Network |  | 10 | 2026-11-29 | 2026-12-09 | 2026-11-10 | 2026-11-21 | 181657.1 | 8
T/C-TE | Testing and Commissioning of Telecom Network | 10 | 2026-11-29 | 2026-12-09 | 2026-11-10 | 2026-11-21 | 181657.1 | 8
Medium Voltage Network |  | 10 | 2026-12-10 | 2026-12-21 | 2026-11-22 | 2026-12-02 | 478905.06 | 8
T/C-MV | Testing and Commissioning of Medium Voltage Network | 10 | 2026-12-10 | 2026-12-21 | 2026-11-22 | 2026-12-02 | 478905.06 | 8
Road Works |  | 5 | 2027-01-17 | 2027-01-21 | 2026-12-29 | 2027-01-03 | 3130811.9 | -14
T/C-RD | Testing and Commissioning of Road Works | 5 | 2027-01-17 | 2027-01-21 | 2026-12-29 | 2027-01-03 | 3130811.9 | -14
Independent Works |  | 114 | 2026-09-13 | 2027-01-24 | 2026-08-25 | 2026-12-31 | 319917.9 | -16
T/C-DPO | Testing and Commissioning of Storm Drainage Ponds | 30 | 2026-09-13 | 2026-10-18 | 2026-08-25 | 2026-09-29 | 296836.8 | 42
T/C-SPS | Testing and Commissioning of Sewage Pump Stations | 26 | 2026-12-26 | 2027-01-24 | 2026-12-02 | 2026-12-31 | 23081.1 | -16
Handing over and close out |  | 75 | 2026-11-04 | 2027-01-30 | 2026-10-17 | 2027-01-11 | 0 | -16
As-Built |  | 70 | 2026-11-04 | 2027-01-24 | 2026-10-17 | 2027-01-05 | 0 | -13
HO-150 | Submission As-Built Drawing For Street Lighting Network | 12 | 2026-11-04 | 2026-11-17 | 2026-10-17 | 2026-10-29 | 0 | 40
HO-180 | Submission As-Built Drawing For Irrigation Network | 12 | 2026-11-17 | 2026-11-30 | 2026-10-29 | 2026-11-11 | 0 | 17
HO-130 | Submission As-Built Drawing For Pond | 12 | 2026-12-01 | 2026-12-14 | 2026-11-12 | 2026-11-25 | 0 | 17
HO-160 | Submission As-Built Drawing For Telecom Network | 12 | 2026-12-01 | 2026-12-14 | 2026-11-12 | 2026-11-25 | 0 | 17
HO-170 | Submission As-Built Drawing For Medium Voltage Network | 12 | 2026-12-01 | 2026-12-14 | 2026-11-12 | 2026-11-25 | 0 | 17
HO-190 | As-Built Drawing For Potable Water Network | 12 | 2026-12-08 | 2026-12-21 | 2026-11-19 | 2026-12-02 | 0 | 11
HO-210 | Submission As-Built Drawing For Pump station | 12 | 2026-12-26 | 2027-01-07 | 2026-12-02 | 2026-12-15 | 0 | -4
HO-200 | Submission As-Built Drawing For Storm Network | 12 | 2026-12-31 | 2027-01-13 | 2026-12-13 | 2026-12-26 | 0 | -9
HO-140 | Submission As-Built Drawing For Roads Network | 5 | 2027-01-17 | 2027-01-21 | 2026-12-29 | 2027-01-03 | 0 | -16
HO-100 | Submission As-Built Drawing For Sewage Network | 7 | 2027-01-17 | 2027-01-24 | 2026-12-29 | 2027-01-05 | 0 | -13
De-Mobilization Works |  | 5 | 2027-01-25 | 2027-01-30 | 2027-01-04 | 2027-01-09 | 0 | -16
HO-220 | Removing Portable Caravan | 5 | 2027-01-25 | 2027-01-30 | 2027-01-04 | 2027-01-09 | 0 | -16
HO-230 | Remove Temporary Car Shades | 5 | 2027-01-25 | 2027-01-30 | 2027-01-04 | 2027-01-09 | 0 | -16
HO-120 | Remove material stock & Storage area | 5 | 2027-01-25 | 2027-01-30 | 2027-01-04 | 2027-01-09 | 0 | -16
Handing Over |  | 7 | 2027-01-23 | 2027-01-30 | 2027-01-04 | 2027-01-11 | 0 | -16
HO-250 | Review B.O.Q Qty. to ensure compliance with the actual status | 5 | 2027-01-23 | 2027-01-27 | 2027-01-04 | 2027-01-09 | 0 | -16
HO-260 | Review FIR Approval to ensure compliance with the actual status | 5 | 2027-01-23 | 2027-01-27 | 2027-01-04 | 2027-01-09 | 0 | -16
HO-270 | Review the sample drawing to ensure compliance with the actual status | 5 | 2027-01-23 | 2027-01-27 | 2027-01-04 | 2027-01-09 | 0 | -16
HO-110 | Final Testing Work | 5 | 2027-01-25 | 2027-01-30 | 2027-01-04 | 2027-01-09 | 0 | -16
HO-240 | Final Walkthrough and Inspection | 2 | 2027-01-28 | 2027-01-30 | 2027-01-10 | 2027-01-11 | 0 | -16
HO-280 | Punch List Completion | 2 | 2027-01-28 | 2027-01-30 | 2027-01-10 | 2027-01-11 | 0 | -16