## Procurement
Procurements Status
E.D.A. to Site procurement ID | RequiredonJob ConstructionactivityID | Sr. NO. | Project ID | ACT # in P6 | Item Description | Disciplines | (Long \Short) Lead Items | Unit | Quantity | Deleivred Material Qty. | Approval Status | The Impact (BOQ Cost) | Completion Rate | Remarks
PRO-R18-RD-DL-220 | CO-R18.S15-RD-P-160 | 1 | DAM3-02-007 | Capping and Subgrade Layer for Road Works-[Road 18]-[SW-15] | 300mm capping layer underneath subgrade , CBR≥15% | ROADS | Short Lead Items | m³ | 62839 | 22217 | APPROVED |  | 35.36%
PRO-R18-RD-DL-220 | CO-R18.S15-RD-P-160 | 2 | DAM3-02-007 | Capping and Subgrade Layer for Road Works-[Road 18]-[SW-15] | Subgrade 30 cm compacted thickness | ROADS | Short Lead Items | m³ | 60481 | 21356 | APPROVED |  | 35.31%
PRO-R18-RD-DL-230 | CO-R18.S15-RD-P-170 | 3 | DAM3-02-007 | Aggregate Base Course Layer for Road Works-[Road 18]-[SW-15] | Aggregate Base Course 20 cm compacted thickness | ROADS | Short Lead Items | m³ | 38931 | 11963 | APPROVED |  | 30.73%
PRO-R18-RD-DL-250 | CO-R09-S1-RD-F-120 | 4 | DAM3-02-007 | Bituminous Base & Wearing Courses Layers for Road Works- S.W 01-[Road 09] | Bituminous concrete wearing course, depth 50 mm thick, after compaction(Grading I - Class A) | ROADS | Short Lead Items | m132 | 9541 | 2814 | APPROVED |  | 29.49%
PRO-R18-RD-DL-250 | CO-R09-S1-RD-F-120 | 5 | DAM3-02-007 | Bituminous Base & Wearing Courses Layers for Road Works- S.W 01-[Road 09] | Bituminous base course(Grading I - Class A), 70mm thick after compaction | ROADS | Short Lead Items | m133 | 13392 | 2272.75 | APPROVED |  | 16.97%
PRO-R18-RD-DL-180 | CO-R18.S15-RD-P-150 | 6 | DAM3-02-007 | Fixing of Interlock Tiles for Sidewalks Pavement-[Road 18]-[SW-15] | INTERLOCK 20x10x6 CM DARK GRAY | ROADS | Short Lead Items | m² | 29030 | 7708 | APPROVED |  | 26.55%
PRO-R18-RD-DL-190 | CO-R18.S15-RD-P-140 | 7 | DAM3-02-007 | Fixing of Curbstone for Sidewalks Pavement-[Road 18]-[SW-15] | CURBSTONE | ROADS | Short Lead Items | PC | 42552 | 0 | APPROVED |  | 0%
PRO-R17-MV-LL-MSI-40 | CO-R10.S03-ES-MV-150 | 8 | DAM3-02-007 | Installation Works for RMU Concrete Foundations of Medium Voltage Network-[Road 10]-[SW-3 | RMU, SF6, 33KV, 400A, CB, 3WAY, NON-EXT, OTDR - SEC CODE: 908327004 | MEDIUM VOLTAGE | Long Lead Items | EACH | 5 | 0 | APPROVED |  | 0%
|  | 9 | DAM3-02-007 |  | M/V WARNING TAPE 15CM YELLOW COLOR EACH ROLL 300 MTR | MEDIUM VOLTAGE | Long Lead Items | EACH | 40.9767 | 65 | APPROVED |  | 158.6%
PRO-R17-MV-LL-MSI-40 | CO-R10.S03-ES-MV-150 | 10 | DAM3-02-007 | Installation Works for RMU Concrete Foundations of Medium Voltage Network-[Road 10]-[SW-3 | SWGR,RMU,AUTO,O/D,2LBS+1CB,33KV,3P-SEC CODE : 908321105 | MEDIUM VOLTAGE | Long Lead Items | EACH | 4 | 0 | APPROVED |  | 0%
PRO-R18-MV-DL-120 | CO-R18.S15-MV-ML-350 | 11 | DAM3-02-007 | Cable Laying Works for Medium Voltage Network-[Road 18]-[SW-15] | CABLE, PWR, 36KV, AL, 3X400/35MM2, XLPE/LLDPE-SEC CODE : 908114005 | MEDIUM VOLTAGE | Long Lead Items | METER | 12378 | 8378 | APPROVED |  | 67.68%
PRO-R18-MV-DL-120 | CO-R18.S15-MV-ML-350 | 12 | DAM3-02-007 | Cable Laying Works for Medium Voltage Network-[Road 18]-[SW-15] | UPVC PIPE 160MM 4.7MM X 6MTR CLASS-4 | MEDIUM VOLTAGE | Long Lead Items | EACH | 327.6667 | 613 | APPROVED |  | 100%
PRO-R18-SL-DL-200 | CO-R18.S16-SL-120 | 13 | DAM3-02-007 | Installation Works for Lighting Poles of Street Lighting Network-[Road 18]-[SW-16] | 12 MTR OCTAGONAL LIGHTING POLE FOR SINGLE ARM (AS PER APPROVAL) | STREET LIGHTING | Long Lead Items | EACH | 355 | 355 | APPROVED |  | 100%
PRO-R18-SL-DL-200 | CO-R18.S16-SL-120 | 14 | DAM3-02-007 | Installation Works for Lighting Poles of Street Lighting Network-[Road 18]-[SW-16] | 12 MTR OCTAGONAL LIGHTING POLE FOR DOUBE ARM (AS PER APPROVAL) | STREET LIGHTING | Long Lead Items | EACH | 4 | 4 | APPROVED |  | 100%
PRO-R18-SL-DL-200 | CO-R18.S16-SL-120 | 15 | DAM3-02-007 | Installation Works for Lighting Poles of Street Lighting Network-[Road 18]-[SW-16] | SINGLE ARM BRACKET LENGTH 1.5 METER FOR POLE 12M | STREET LIGHTING | Long Lead Items | EACH | 355 | 355 | APPROVED |  | 100%
PRO-R18-SL-DL-200 | CO-R18.S16-SL-120 | 16 | DAM3-02-007 | Installation Works for Lighting Poles of Street Lighting Network-[Road 18]-[SW-16] | DOUBLE ARM BRACKET LENGTH 1.5 METER FOR POLE 12M | STREET LIGHTING | Long Lead Items | EACH | 4 | 4 | APPROVED |  | 100%
PRO-R18-SL-DL-220 | CO-R18.S16-SL-130 | 17 | DAM3-02-007 | Installation Works for Lighting Fixtures With Drop Wire of Street Lighting Network-[Road 18]-[SW-16] | LIGHTING FIXTURE LED 141WAT | STREET LIGHTING | Long Lead Items | EACH | 355 | 0 | APPROVED |  | 0%
PRO-R18-SL-DL-220 | CO-R18.S16-SL-130 | 18 | DAM3-02-007 | Installation Works for Lighting Fixtures With Drop Wire of Street Lighting Network-[Road 18]-[SW-16] | LIGHTING FIXTURE LED 169WAT | STREET LIGHTING | Long Lead Items | EACH | 8 | 0 | APPROVED |  | 0%
PRO-R18-SL-DL-180 | CO-R18.S16-SL-150 | 19 | DAM3-02-007 | Cable Laying Works for Street Lighting Network-[Road 18]-[SW-16] | CABLE 3C X 2.5MM CU/ PVC,WHITE | STREET LIGHTING | Short Lead Items | METER | 4719 | 0 | APPROVED |  | 0%
PRO-R18-SL-DL-180 | CO-R18.S16-SL-150 | 20 | DAM3-02-007 | Cable Laying Works for Street Lighting Network-[Road 18]-[SW-16] | CABLE 4X25 MM2 CU/XLPE/SWA/PVC | STREET LIGHTING | Short Lead Items | METER | 20192 | 20192 | APPROVED |  | 100%
PRO-R18-SL-DL-180 | CO-R18.S16-SL-150 | 21 | DAM3-02-007 | Cable Laying Works for Street Lighting Network-[Road 18]-[SW-16] | 1X16mm2 CU/PVC/PVC , 600/1000 V | STREET LIGHTING | Short Lead Items | METER | 20192 | 20192 | APPROVED |  | 100%
PRO-R18-SL-DL-250 | CO-R18.S16-SL-180 | 22 | DAM3-02-007 | Installation Works for Panel Board Concrete Foundations of Street Lighting Network-[Road 18]-[SW-16] | STREET LIGHTING PANEL BOARD 100A AS PER AMANA APRROVED STANDARD | STREET LIGHTING | Long Lead Items | EACH | 6 | 0 | APPROVED |  | 0%
|  | 23 | DAM3-02-007 |  | ANCHOR POLT FOR 12 MRT LIGHTING POLE SIZE (400 X 25) MM | STREET LIGHTING | Long Lead Items | EACH | 1436 | 1436 | APPROVED |  | 100%
|  | 24 | DAM3-02-007 |  | STEEL REBAR 10MM | STREET LIGHTING | Long Lead Items | TON | 4.6162 | 5 | APPROVED |  | 108.3%
|  | 25 | DAM3-02-007 |  | STEEL REBAR 16MM | STREET LIGHTING | Long Lead Items | TON | 19.2613 | 19 | APPROVED |  | 98.64%
|  | 26 | DAM3-02-007 |  | UPVC PIPE CLASS-4 DIA 110MM, 6MTR LENGTH | STREET LIGHTING | Long Lead Items | PC | 400.6667 | 400 | APPROVED |  | 99.83%
|  | 27 | DAM3-02-007 |  | WARNING TAPE YELLOW (30CM) 6 ' EACH ROLL 300 MTR | STREET LIGHTING | Long Lead Items | EACH | 59.5533 | 58 | APPROVED |  | 97.39%
PRO-R18-SL-DL-250 | CO-R18.S16-SL-180 | 28 | DAM3-02-007 | Installation Works for Panel Board Concrete Foundations of Street Lighting Network-[Road 18]-[SW-16] | FOUNDATION FOR LIGHING PANEL BOARD 1.7M X 1.55 M X 0.9M WITH STEEL DOOR | STREET LIGHTING | Long Lead Items | EACH | 6 | 0 | APPROVED |  | 0%
PRO-R18-SL-DL-250 | CO-R18.S16-SL-150 | 29 | DAM3-02-007 | Cable Laying Works for Street Lighting Network-[Road 18]-[SW-16] | MANHOLE AT ROAD CROSSING (900X900X1200 mm) | STREET LIGHTING | Long Lead Items | EACH | 61 | 0 | APPROVED |  | 0%
PRO-R18-TE-DL-120 | CO-R18.S15-TE-180 | 30 | DAM3-02-007 | Pipes Laying Works for Ducts of Telecom Network-[Road 18]-[SW-15] | PIPE HDPE 50mm DIA , 40.8/50MM (ID/OD) PE 100, PN 16 , BLACK COLOR WITH NYLON ROPE , (AS PER MODON STANDERD) | TELECOM | Short Lead Items | METER | 17620 | 7800 | APPROVED |  | 44.27%
PRO-R18-TE-DL-120 | CO-R18.S15-TE-180 | 31 | DAM3-02-007 | Pipes Laying Works for Ducts of Telecom Network-[Road 18]-[SW-15] | PIPE HDPE 50mm DIA , 40.8/50MM (ID/OD) PE 100, PN 16 , BLUE COLOR WITH NYLON ROPE , (AS PER MODON STANDERD) | TELECOM | Short Lead Items | METER | 17620 | 7800 | APPROVED |  | 44.27%
PRO-R18-TE-DL-120 | CO-R18.S15-TE-180 | 32 | DAM3-02-007 | Pipes Laying Works for Ducts of Telecom Network-[Road 18]-[SW-15] | PIPE HDPE 50mm DIA , 40.8/50MM (ID/OD) PE 100, PN 16 , GREEN COLOR WITH NYLON ROPE , (AS PER MODON STANDERD) | TELECOM | Short Lead Items | METER | 17620 | 7800 | APPROVED |  | 44.27%
PRO-R18-TE-DL-130 | CO-R18.S15-TE-180 | 33 | DAM3-02-007 | Pipes Laying Works for Ducts of Telecom Network-[Road 18]-[SW-15] | MANHOLE TYPE-01 (2 WAY) SIZE (2000X1000X1000) MM , (AS PER MODON STANDERD) | TELECOM | Short Lead Items | EACH | 6 | 0 | APPROVED |  | 0%
|  | 34 | DAM3-02-007 |  | TELECOM WARNING TAPE , YELLOW COLOR , WIDTH 15 CM , ROLL 300 MRT , AS PER MODON STD | TELECOM | Short Lead Items | EACH | 29.37 | 57 | APPROVED |  | 194.1%
|  | 35 | DAM3-02-007 |  | SPACER 3*2 (6DUCT 50MM) , (AS PER MODON STANDERD) | TELECOM | Short Lead Items | EACH | 4405 | 5500 | APPROVED |  | 124.9%
PRO-R18-TE-DL-130 | CO-R18.S15-TE-180 | 36 | DAM3-02-007 | Pipes Laying Works for Ducts of Telecom Network-[Road 18]-[SW-15] | MANHOLE TYPE-02 (3 WAY) SIZE (2000X1000X1000) MM , (AS PER MODON STANDERD) | TELECOM | Short Lead Items | EACH | 68 | 8 | APPROVED |  | 11.76%
PRO-R18-TE-DL-130 | CO-R18.S15-TE-180 | 37 | DAM3-02-007 | Pipes Laying Works for Ducts of Telecom Network-[Road 18]-[SW-15] | MANHOLE TYPE-03 (4 WAY) SIZE (2000X1000X1000) MM , (AS PER MODON STANDERD) | TELECOM | Short Lead Items | EACH | 4 | 0 | APPROVED |  | 0%
PRO-R18-PW-DL-140 | CO-R18.S16-PW-240 | 38 | DAM3-02-007 | Pipes Laying and accessories for Main Lines of Potable Water Network-[Road 18]-[SW-16] | PIPE DIM 110 MM ( HDPE 16 BAR ) | POTABLE WATER | Short Lead Items | METER | 5.144 | 0 | APPROVED |  | 0%
PRO-R18-PW-DL-140 | CO-R18.S16-PW-240 | 39 | DAM3-02-007 | Pipes Laying and accessories for Main Lines of Potable Water Network-[Road 18]-[SW-16] | PIPE DIM 160 MM ( HDPE 16 BAR ) | POTABLE WATER | Short Lead Items | METER | 73 | 0 | APPROVED |  | 0%
PRO-R18-PW-DL-140 | CO-R18.S16-PW-240 | 40 | DAM3-02-007 | Pipes Laying and accessories for Main Lines of Potable Water Network-[Road 18]-[SW-16] | PIPE DIM 200 MM ( HDPE 16 BAR ) | POTABLE WATER | Short Lead Items | METER | 8218.325 | 7038 | APPROVED |  | 85.64%
PRO-R18-PW-DL-140 | CO-R18.S16-PW-240 | 41 | DAM3-02-007 | Pipes Laying and accessories for Main Lines of Potable Water Network-[Road 18]-[SW-16] | PIPE DIM 355 MM ( HDPE 16 BAR ) | POTABLE WATER | Short Lead Items | METER | 1429.183 | 696 | APPROVED |  | 48.7% |  | 12875.652 | 10884 | 0.84532
PRO-R18-PW-DL-140 | CO-R18.S16-PW-240 | 42 | DAM3-02-007 | Pipes Laying and accessories for Main Lines of Potable Water Network-[Road 18]-[SW-16] | PIPE DIM 560 MM ( HDPE 16 BAR ) | POTABLE WATER | Short Lead Items | METER | 970 | 970 | APPROVED |  | 100%
|  | 43 | DAM3-02-007 |  | PIPE DIM 630 MM ( HDPE 16 BAR ) | POTABLE WATER | Short Lead Items | METER | 2180 | 2180 | APPROVED |  | 100%
|  | 44 | DAM3-02-007 |  | EF - COUPLING 200MM - 16 BAR | POTABLE WATER | Short Lead Items | EACH | 687 | 595 | APPROVED |  | 86.61%
|  | 45 | DAM3-02-007 |  | EF-HDPE ELBOW 45D 200MM - PN16 | POTABLE WATER | Short Lead Items | EACH | 40 | 40 | APPROVED |  | 100%
|  | 46 | DAM3-02-007 |  | BW-HDPE ELBOW 45D 355MM - PN16 | POTABLE WATER | Short Lead Items | EACH | 12 | 12 | APPROVED |  | 100%
|  | 47 | DAM3-02-007 |  | EF-HDPE END CAP 200MM SDR9- PN16 | POTABLE WATER | Short Lead Items | EACH | 34 | 34 | APPROVED |  | 100%
|  | 48 | DAM3-02-007 |  | BW-HDPE END CAP 355MM SDR9- PN16 | POTABLE WATER | Short Lead Items | EACH | 5 | 5 | APPROVED |  | 100%
|  | 49 | DAM3-02-007 |  | BW-HDPE REDUCER 355/200 MM PN16 | POTABLE WATER | Short Lead Items | EACH | 3 | 3 | APPROVED |  | 100%
|  | 50 | DAM3-02-007 |  | BW-HDPE REDUCER 630/560 MM PN16 | POTABLE WATER | Short Lead Items | EACH | 1 | 1 | APPROVED |  | 100%
|  | 51 | DAM3-02-007 |  | EF-HDPE EQUAL TEE 200 PN16 | POTABLE WATER | Short Lead Items | EACH | 38 | 23 | APPROVED |  | 60.53%
|  | 52 | DAM3-02-007 |  | EF-HDPE TEE 200 x 110 x 200 PN16 | POTABLE WATER | Short Lead Items | EACH | 5 | 5 | APPROVED |  | 100%
|  | 53 | DAM3-02-007 |  | EF-HDPE TEE 200 x 160 x 200 PN16 | POTABLE WATER | Short Lead Items | EACH | 47 | 47 | APPROVED |  | 100%
|  | 54 | DAM3-02-007 |  | BW-HDPE EQUAL TEE 355 PN16 | POTABLE WATER | Short Lead Items | EACH | 7 | 7 | APPROVED |  | 100%
|  | 55 | DAM3-02-007 |  | BW-HDPE TEE 355 x 160 x 355 PN16 + ( EF-COUBLING 160 ) | POTABLE WATER | Short Lead Items | EACH | 8 | 8 | APPROVED |  | 100%
|  | 56 | DAM3-02-007 |  | BW-HDPE TEE 355 x 200 x 355 PN16 + ( EF-COUBLING 200 ) | POTABLE WATER | Short Lead Items | EACH | 3 | 3 | APPROVED |  | 100%
|  | 57 | DAM3-02-007 |  | BW-HDPE TEE 630 x 355 x 630 PN16 | POTABLE WATER | Short Lead Items | EACH | 1 | 1 | APPROVED |  | 100%
|  | 58 | DAM3-02-007 |  | EF-MALE ADAPTOR DN 110 MM PN16+ ( EF COUBLING ) | POTABLE WATER | Short Lead Items | EACH | 5 | 5 | APPROVED |  | 100%
|  | 59 | DAM3-02-007 |  | STEEL FLANGE FOR MALE ADAPTOR 110 MM | POTABLE WATER | Short Lead Items | EACH | 5 | 5 | APPROVED |  | 100%
|  | 60 | DAM3-02-007 |  | EF-MALE ADAPTOR DN 200 MM PN16+ ( EF COUBLING ) | POTABLE WATER | Short Lead Items | EACH | 156 | 156 | APPROVED |  | 100%
|  | 61 | DAM3-02-007 |  | EF-MALE ADAPTOR DN 160 MM PN16+ ( EF COUBLING ) | POTABLE WATER | Short Lead Items | EACH | 110 | 110 | APPROVED |  | 100%
|  | 62 | DAM3-02-007 |  | EF-MALE ADAPTOR DN 200 MM PN16+ ( EF COUBLING ) | POTABLE WATER | Short Lead Items | EACH | 156 | 156 | APPROVED |  | 100%
|  | 63 | DAM3-02-007 |  | STEEL FLANGE FOR MALE ADAPTOR 160 MM | POTABLE WATER | Short Lead Items | EACH | 110 | 110 | APPROVED |  | 100%
|  | 64 | DAM3-02-007 |  | BW-MALE ADAPTOR DN 355 MM PN16 | POTABLE WATER | Short Lead Items | EACH | 40 | 40 | APPROVED |  | 100%
|  | 65 | DAM3-02-007 |  | STEEL FLANGE FOR MALE ADAPTOR 355 MM | POTABLE WATER | Short Lead Items | EACH | 40 | 40 | APPROVED |  | 100%
|  | 66 | DAM3-02-007 |  | STEEL FLANGE FOR MALE ADAPTOR 200 MM | POTABLE WATER | Short Lead Items | EACH | 156 | 156 | APPROVED |  | 100%
PRO-R18-PW-DL-140 | CO-R18.S16-PW-240 | 67 | DAM3-02-007 | Pipes Laying and accessories for Main Lines of Potable Water Network-[Road 18]-[SW-16] | WARNING TAPE FOR Water NETWORK ( Detectable ) | POTABLE WATER | Short Lead Items | EACH | 34 | 34 | APPROVED |  | 100%
PRO-R18-SW-DL-150 | CO-R18.S15-SW-230 | 68 | DAM3-02-007 | Pipes Laying Works for Main Lines of Sewage Network-[Road 18]-[SW-15] | UPVC PIPE 160 MM, PN 10 SASO 1452, CLASS 4 | SEWERAGE | Short Lead Items | METER | 656.47 | 426 | APPROVED |  | 64.89%
PRO-R18-SW-DL-150 | CO-R18.S15-SW-230 | 69 | DAM3-02-007 | Pipes Laying Works for Main Lines of Sewage Network-[Road 18]-[SW-15] | UPVC PIPE 200 MM CLASS 4 | SEWERAGE | Short Lead Items | METER | 5244.65 | 4302 | APPROVED |  | 82.03%
PRO-R18-SW-DL-150 | CO-R18.S15-SW-230 | 70 | DAM3-02-007 | Pipes Laying Works for Main Lines of Sewage Network-[Road 18]-[SW-15] | UPVC PIPE 250 MM CLASS 4 | SEWERAGE | Short Lead Items | METER | 325.25 | 325.25 | APPROVED |  | 100%
PRO-R18-SW-DL-150 | CO-R18.S15-SW-230 | 71 | DAM3-02-007 | Pipes Laying Works for Main Lines of Sewage Network-[Road 18]-[SW-15] | UPVC PIPE 315 MM CLASS 4 | SEWERAGE | Short Lead Items | METER | 285 | 0 | APPROVED |  | 0%
PRO-R18-SW-DL-150 | CO-R18.S15-SW-230 | 72 | DAM3-02-007 | Pipes Laying Works for Main Lines of Sewage Network-[Road 18]-[SW-15] | GRP-PIPE-DIA0400-PN10.0-SN5000-UGS | SEWERAGE | Short Lead Items | METER | 261 | 1060 | APPROVED |  | 406.1%
PRO-R18-SW-DL-150 | CO-R18.S15-SW-230 | 73 | DAM3-02-007 | Pipes Laying Works for Main Lines of Sewage Network-[Road 18]-[SW-15] | GRP-PIPE-DIA0400-PN10.0-SN10000-UGS | SEWERAGE | Short Lead Items | METER | 1309 | 1309 | APPROVED |  | 100%
PRO-R18-SW-DL-150 | CO-R18.S15-SW-230 | 74 | DAM3-02-007 | Pipes Laying Works for Main Lines of Sewage Network-[Road 18]-[SW-15] | GRP-PIPE-DIA0500-PN10.00-SN10000-UGS | SEWERAGE | Short Lead Items | METER | 1352 | 1352 | APPROVED |  | 100%
PRO-R18-SW-DL-150 | CO-R18.S15-SW-230 | 75 | DAM3-02-007 | Pipes Laying Works for Main Lines of Sewage Network-[Road 18]-[SW-15] | GRP-PIPE-DIA0600-PN10.00-SN10000-UGS | SEWERAGE | Short Lead Items | METER | 847 | 847 | APPROVED |  | 100%
PRO-R18-SW-DL-150 | CO-R18.S15-SW-260 | 76 | DAM3-02-007 | Pipes Laying Works for Main Lines of Sewage Network-[Road 18]-[SW-15] | GRP LINER DIA 1200 MM 8MM THICKNESS | SEWERAGE | Short Lead Items | METER | 342.84 | 336 | APPROVED |  | 98%
PRO-R18-SW-DL-150 | CO-R18.S15-SW-260 | 77 | DAM3-02-007 | Pipes Laying Works for Main Lines of Sewage Network-[Road 18]-[SW-15] | GRP LINER DIA 1500 MM 8MM THICKNESS | SEWERAGE | Short Lead Items | METER | 98.5 | 92 | APPROVED |  | 93.4%
PRO-R18-SW-DL-150 | CO-R18.S15-SW-260 | 78 | DAM3-02-007 | Pipes Laying Works for Main Lines of Sewage Network-[Road 18]-[SW-15] | GRP LINER DIM 1600 MM 8MM | SEWERAGE | Short Lead Items | METER | 268 | 192 | APPROVED |  | 71.64%
PRO-R18-SW-DL-150 | CO-R18.S15-SW-260 | 79 | DAM3-02-007 | Pipes Laying Works for Main Lines of Sewage Network-[Road 18]-[SW-15] | GRP LINER DIM 1900 MM | SEWERAGE | Short Lead Items | METER | 32 | 32 | APPROVED |  | 100%
PRO-R18-SW-DL-150 | CO-R18.S15-SW-260 | 80 | DAM3-02-007 | Pipes Laying Works for Main Lines of Sewage Network-[Road 18]-[SW-15] | GRP LINER DIM 2100 MM 8MM | SEWERAGE | Short Lead Items | METER | 67 | 67 | APPROVED |  | 100%
PRO-R18-SW-DL-150 | CO-R18.S15-SW-260 | 81 | DAM3-02-007 | Pipes Laying Works for Main Lines of Sewage Network-[Road 18]-[SW-15] | GRP LINER DIM 2200 MM 8MM | SEWERAGE | Short Lead Items | METER | 22 | 22 | APPROVED |  | 100%
PRO-R18-SW-DL-150 | CO-R18.S15-SW-260 | 82 | DAM3-02-007 | Pipes Laying Works for Main Lines of Sewage Network-[Road 18]-[SW-15] | D.I. COVER AND FRAME WITH Ø600 CLEAR OPENING | SEWERAGE | Short Lead Items | EACH | 129 | 0 | APPROVED |  | 0%
PRO-R18-SD-DL-180 | CO-R18.S15-SD-240 | 83 | DAM3-02-007 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 18]-[SW-15] | UPVC-PIPE-DIA0300-PN10/CLASS (04) | STORM | Short Lead Items | METER | 9018.0406 | 6597 | APPROVED |  | 73.15%
PRO-R18-SD-DL-180 | CO-R18.S15-SD-240 | 84 | DAM3-02-007 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 18]-[SW-15] | UPVC-PIPE-DIA0400-PN10/CLASS (04) | STORM | Short Lead Items | METER | 892.0126 | 536 | APPROVED |  | 60.09%
PRO-R18-SD-DL-180 | CO-R18.S15-SD-240 | 85 | DAM3-02-007 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 18]-[SW-15] | GRP-PIPE-DIA0400-PN10-SN5000-UGS | STORM | Short Lead Items | METER | 2265.67 | 2265 | APPROVED |  | 99.97%
PRO-R18-SD-DL-180 | CO-R18.S15-SD-240 | 86 | DAM3-02-007 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 18]-[SW-15] | GRP-PIPE-DIA0500-PN10-SN5000-UGS | STORM | Short Lead Items | METER | 2235.81 | 2032 | APPROVED |  | 90.88%
PRO-R18-SD-DL-180 | CO-R18.S15-SD-240 | 87 | DAM3-02-007 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 18]-[SW-15] | GRP-PIPE-DIA0600-PN10-SN5000-UGS | STORM | Short Lead Items | METER | 1251.63 | 1140 | APPROVED |  | 91.08%
PRO-R18-SD-DL-180 | CO-R18.S15-SD-240 | 88 | DAM3-02-007 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 18]-[SW-15] | GRP-PIPE-DIA0700-PN10-SN5000-UGS | STORM | Short Lead Items | METER | 2518.8 | 2189.25 | APPROVED |  | 86.92%
PRO-R18-SD-DL-180 | CO-R18.S15-SD-240 | 89 | DAM3-02-007 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 18]-[SW-15] | GRP-PIPE-DIA0800-PN10-SN5000-UGS | STORM | Short Lead Items | METER | 1326.47 | 1100 | APPROVED |  | 82.93%
PRO-R18-SD-DL-180 | CO-R18.S15-SD-240 | 91 | DAM3-02-007 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 18]-[SW-15] | GRP-PIPE-DIA0900-PN10-SN5000-UGS | STORM | Short Lead Items | METER | 1014.9 | 1106 | APPROVED |  | 109%
PRO-R18-SD-DL-180 | CO-R18.S15-SD-240 | 93 | DAM3-02-007 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 18]-[SW-15] | GRP-PIPE-DIA01000-PN10-SN5000-UGS | STORM | Short Lead Items | METER | 994.02 | 849.7 | APPROVED |  | 85.48%
PRO-R18-SD-DL-180 | CO-R18.S15-SD-240 | 94 | DAM3-02-007 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 18]-[SW-15] | GRP-PIPE-DIA01100-PN10-SN5000-UGS | STORM | Short Lead Items | METER | 222.41 | 228 | APPROVED |  | 102.5%
PRO-R18-SD-DL-180 | CO-R18.S15-SD-240 | 95 | DAM3-02-007 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 18]-[SW-15] | GRP-PIPE-DIA01200-PN10-SN5000-UGS | STORM | Short Lead Items | METER | 219.74 | 219.74 | APPROVED |  | 100%
PRO-R18-SD-DL-180 | CO-R18.S15-SD-240 | 96 | DAM3-02-007 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 18]-[SW-15] | GRP-PIPE-DIA0900-PN10-SN10000-UGS | STORM | Short Lead Items | METER | 119 | 0 | APPROVED |  | 0%
PRO-R18-SD-DL-180 | CO-R18.S15-SD-240 | 97 | DAM3-02-007 | Pipes Laying Works for Main Lines of Storm Drainage Network-[Road 18]-[SW-15] | GRP-PIPE-DIA1000-PN10-SN10000-UGS | STORM | Short Lead Items | METER | 392.95 | 100 | APPROVED |  | 25.45%
PRO-R18-SD-DL-200 | CO-R18.S15-SD-270 | 98 | DAM3-02-007 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 18]-[SW-15 | GRP-PIPE-DIA01100-PN10-SN10000-UGS | STORM | Long Lead Items | EACH | 377 | 0 | APPROVED |  | 0%
PRO-R18-SD-DL-200 | CO-R18.S15-SD-270 | 99 | DAM3-02-007 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 18]-[SW-15 | GRP-PIPE-DIA01200-PN10-SN10000-UGS | STORM | Long Lead Items | EACH | 3366.29 | 3189.1522 | APPROVED |  | 94.74%
PRO-R18-SD-DL-200 | CO-R18.S15-SD-270 | 100 | DAM3-02-007 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 18]-[SW-15 | RC PRE-CAST CATCH BASIN 800 X 1800 X 1600 MM. | STORM | Long Lead Items | EACH | 10 | 10 | APPROVED |  | 100%
PRO-R18-SD-DL-200 | CO-R18.S15-SD-270 | 101 | DAM3-02-007 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 18]-[SW-15 | RC PRE-CAST CATCH BASIN 800 X 1800 X 1700 MM. | STORM | Long Lead Items | EACH | 4 | 4 | APPROVED |  | 100%
PRO-R18-SD-DL-200 | CO-R18.S15-SD-270 | 102 | DAM3-02-007 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 18]-[SW-15 | RC PRE-CAST CATCH BASIN 800 X 1800 X 1800 MM. | STORM | Long Lead Items | EACH | 125 | 118 | APPROVED |  | 94.4%
PRO-R18-SD-DL-200 | CO-R18.S15-SD-270 | 103 | DAM3-02-007 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 18]-[SW-15 | RC PRE-CAST CATCH BASIN 800 X 1800 X 1900 MM. | STORM | Long Lead Items | EACH | 4 | 4 | APPROVED |  | 100%
PRO-R18-SD-DL-200 | CO-R18.S15-SD-270 | 104 | DAM3-02-007 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 18]-[SW-15 | RC-PRE-CAST CATCH BASIN 1200 X 1200 X 1400 MM. | STORM | Long Lead Items | EACH | 18 | 18 | APPROVED |  | 100%
PRO-R18-SD-DL-200 | CO-R18.S15-SD-270 | 105 | DAM3-02-007 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 18]-[SW-15 | RC-PRE-CAST CATCH BASIN 1200 X 1200 X 1500 MM. | STORM | Long Lead Items | EACH | 333 | 316 | APPROVED |  | 94.89%
PRO-R18-SD-DL-200 | CO-R18.S15-SD-270 | 106 | DAM3-02-007 | Installation and Pipes Laying Connection Works for Catch Basins of Storm Drainage Network-[Road 18]-[SW-15 | RC-PRE-CAST CATCH BASIN 1200 X 1200 X 1900 MM. | STORM | Long Lead Items | EACH | 4 | 4 | APPROVED |  | 100%
|  | 107 | DAM3-02-007 |  | RC, Catch Basin Top Slab, Length of 1700 mm, Width of 1700 mm, Thickness of 250 mm, No Inner Coat , Bitumen Outer Coat | STORM | Long Lead Items | EACH | 355 | 90 | APPROVED |  | 25.35%
|  | 108 | DAM3-02-007 |  | RC, Catch Basin Top Slab, Length of 2300 mm, Width of 1300 mm, Thickness of 300 mm, Epoxy Inner Coat,Bitumen Outer Coat | STORM | Long Lead Items | EACH | 148 | 10 | APPROVED |  | 6.757%
PRO-R18-SD-DL-170 | CO-R18.S15-SD-310 | 109 | DAM3-02-007 | Install RC Footing Works for Manholes of Storm Drainage Network-[Road 18]-[SW-15] | RC PRECAST MANHOLE BASE 1200*300/350*1500, (400 MM - 600 MM DIA) | STORM | Long Lead Items | EACH | 79 | 72 | APPROVED |  | 91.14%
PRO-R18-SD-DL-170 | CO-R18.S15-SD-310 | 110 | DAM3-02-007 | Install RC Footing Works for Manholes of Storm Drainage Network-[Road 18]-[SW-15] | RC PRECAST MANHOLE BASE 1500*300/350*1500, (700 MM - 900 MM DIA) | STORM | Long Lead Items | EACH | 58 | 53 | APPROVED |  | 91.38%
PRO-R18-SD-DL-170 | CO-R18.S15-SD-310 | 111 | DAM3-02-007 | Install RC Footing Works for Manholes of Storm Drainage Network-[Road 18]-[SW-15] | RC PRECAST MANHOLE BASE 2000*300/350*2200, (1000-1200MM)DIA | STORM | Long Lead Items | EACH | 34 | 29 | APPROVED |  | 85.29%
|  | 112 | DAM3-02-007 |  | RING-1200/200/300 MM | STORM | Long Lead Items | EACH | 40 | 15 | APPROVED |  | 37.5%
|  | 113 | DAM3-02-007 |  | RING-1200/200/600 MM | STORM | Long Lead Items | EACH | 23 | 3 | APPROVED |  | 13.04%
PRO-R18-SD-DL-170 | CO-R09-SD-TF-110 | 114 | DAM3-02-007 | Install Catch Basin Cover Works for External Finishes of Storm Drainage Network-[Road 09] | RING-1200/200/900 MM | STORM | Long Lead Items | EACH | 13 | 4 | APPROVED |  | 30.77%
PRO-R18-SD-DL-170 | CO-R09-SD-TF-110 | 115 | DAM3-02-007 | Install Catch Basin Cover Works for External Finishes of Storm Drainage Network-[Road 09] | RING-1200/200/1200 MM | STORM | Long Lead Items | EACH | 5 | 5 | APPROVED |  | 100%
PRO-R18-SD-DL-170 | CO-R09-SD-TF-110 | 116 | DAM3-02-007 | Install Catch Basin Cover Works for External Finishes of Storm Drainage Network-[Road 09] | RING-1500/200/300 MM | STORM | Long Lead Items | EACH | 5 | 0 | APPROVED |  | 0%
PRO-R18-SD-DL-190 | CO-R09-SD-TF-110 | 117 | DAM3-02-007 | Install Catch Basin Cover Works for External Finishes of Storm Drainage Network-[Road 09] | RING-1500/200/600 MM | STORM | Short Lead Items | EACH | 17 | 11 | APPROVED |  | 64.71%
PRO-R18-SD-DL-191 | CO-R09-SD-TF-110 | 118 | DAM3-02-007 | Install Catch Basin Cover Works for External Finishes of Storm Drainage Network-[Road 09] | RING-1500/200/900 MM | STORM | Short Lead Items | EACH | 29 | 18 | APPROVED |  | 62.07%
|  | 119 | DAM3-02-007 |  | RING-1500/200/1200 MM | STORM | Short Lead Items | EACH | 15 | 7 | APPROVED |  | 46.67%
|  | 120 | DAM3-02-007 |  | RING-2000/200/300 MM | STORM | Short Lead Items | EACH | 9 | 0 | APPROVED |  | 0%
|  | 121 | DAM3-02-007 |  | RING-2000/200/600 MM | STORM | Short Lead Items | EACH | 9 | 0 | APPROVED |  | 0%
|  | 122 | DAM3-02-007 |  | RING-2000/200/900 MM | STORM | Short Lead Items | EACH | 7 | 0 | APPROVED |  | 0%
|  | 123 | DAM3-02-007 |  | RING-2000/200/1200 MM | STORM | Short Lead Items | EACH | 16 | 10 | APPROVED |  | 62.5%
|  | 124 | DAM3-02-007 |  | RC PRECAST FLAT COVER SLAB 1600/600/250MM | STORM | Short Lead Items | EACH | 79 | 27 | APPROVED |  | 34.18%
|  | 125 | DAM3-02-007 |  | RC PRECAST FLAT COVER SLAB 1900/600/250MM | STORM | Short Lead Items | EACH | 58 | 27 | APPROVED |  | 46.55%
|  | 126 | DAM3-02-007 |  | RC PRECAST FLAT COVER SLAB 2400/600/250MM | STORM | Short Lead Items | EACH | 34 | 7 | APPROVED |  | 20.59%
|  | 127 | DAM3-02-007 |  | GRATING DUCTILE-IRON MEDIUM DUTY COVERS AND FRAMES AS PER MINISTRY OF TRANSPORT SPECIFICATION, 600 MM CLEAR OPENING CONNECTED WITH THE MAIN FRAME WITH 300 MM STAINLESS STEEL 316 SECURITY CHAIN. | STORM | Short Lead Items | ROLL | 198 | 0 | APPROVED |  | 0%
|  | 128 | DAM3-02-007 |  | HEAVY DUTY DUCTILE IRON STORM COVER FOR CATH BASIN 600*600MM | STORM | Short Lead Items | ROLL | 355 | 0 | APPROVED |  | 0%
|  | 129 | DAM3-02-007 |  | HEAVY DUTY COVERS CLASS "D" 400 DOUBLE TRIANGULAR DUCTILE IRON GRATING AND FRAME 800 X 800 MM OVER BASE 635 X 635 OVER GRATE. | STORM | Short Lead Items | M3 | 296 | 0 | APPROVED |  | 0%
PRO-R18-SD-DL-192 | CO-R09-SD-TF-110 | 130 | DAM3-02-007 | Install Catch Basin Cover Works for External Finishes of Storm Drainage Network-[Road 09] | WARNING MAGNETIC TAPE FOR STORM NETWORK | STORM | Short Lead Items | EACH | 82 | 30 | APPROVED |  | 36.59%
PRO-R18-IR-DL-120 | CO-R18.S15-IR-150 | 131 | DAM3-02-007 | Pipes Laying Works for Main Lines of Irrigation Network-[Road 18]-[SW-15] | PIPE DIM 50 MM ( HDPE 16 BAR ) | IRRIGATION | Short Lead Items | METER | 156 | 0 | APPROVED |  | 0%
PRO-R18-IR-DL-120 | CO-R18.S15-IR-150 | 132 | DAM3-02-007 | Pipes Laying Works for Main Lines of Irrigation Network-[Road 18]-[SW-15] | PIPE DIM 110 MM ( HDPE 16 BAR ) | IRRIGATION | Short Lead Items | METER | 58 | 0 | APPROVED |  | 0%
PRO-R18-IR-DL-120 | CO-R18.S15-IR-150 | 133 | DAM3-02-007 | Pipes Laying Works for Main Lines of Irrigation Network-[Road 18]-[SW-15] | PIPE DIM 125 MM ( HDPE 16 BAR ) | IRRIGATION | Short Lead Items | METER | 10035.919 | 2200 | APPROVED |  | 21.92%
PRO-R18-IR-DL-120 | CO-R18.S15-IR-150 | 134 | DAM3-02-007 | Pipes Laying Works for Main Lines of Irrigation Network-[Road 18]-[SW-15] | PIPE DIM 280MM (HDPE 16PN) | IRRIGATION | Short Lead Items | METER | 477.5 | 170 | APPROVED |  | 35.6%
PRO-R18-IR-DL-120 | CO-R18.S15-IR-150 | 135 | DAM3-02-007 | Pipes Laying Works for Main Lines of Irrigation Network-[Road 18]-[SW-15] | PIPE DIM 400 MM ( HDPE 16 BAR ) | IRRIGATION | Short Lead Items | METER | 1860 | 1860 | APPROVED |  | 100%
PRO-R18-IR-DL-120 | CO-R18.S15-IR-150 | 136 | DAM3-02-007 | Pipes Laying Works for Main Lines of Irrigation Network-[Road 18]-[SW-15] | PIPE DIM 500 MM ( HDPE 16 BAR ) | IRRIGATION | Short Lead Items | METER | 3020 | 3020 | APPROVED |  | 100%
|  | 137 | DAM3-02-007 |  | EF - COUPLING 110MM - PN16 | IRRIGATION | Short Lead Items | EACH | 58 | 322 | APPROVED |  | 555.2%
|  | 138 | DAM3-02-007 |  | EF - COUPLING 125MM - PN16 | IRRIGATION | Short Lead Items | EACH | 100.3592 | 100 | APPROVED |  | 99.64%
|  | 139 | DAM3-02-007 |  | EF - COUPLING 280MM - PN16 | IRRIGATION | Short Lead Items | EACH | 39.7917 | 15 | APPROVED |  | 37.7%
|  | 140 | DAM3-02-007 |  | EF - COUPLING 250MM - PN16 | IRRIGATION | Short Lead Items | EACH | 0 | 2 | APPROVED |  | #DIV/0!
|  | 141 | DAM3-02-007 |  | EF-HDPE ELBOW 45D 125MM - PN16 | IRRIGATION | Short Lead Items | EACH | 26 | 0 | APPROVED |  | 0%
|  | 142 | DAM3-02-007 |  | EF-HDPE ELBOW 45D 280MM - PN16 | IRRIGATION | Short Lead Items | EACH | 6 | 6 | APPROVED |  | 100%
|  | 143 | DAM3-02-007 |  | EF-End Cap_125MM - PN16 | IRRIGATION | Short Lead Items | EACH | 44 | 44 | APPROVED |  | 100%
|  | 144 | DAM3-02-007 |  | EF-End Cap_280MM - PN16 | IRRIGATION | Short Lead Items | EACH | 1 | 1 | APPROVED |  | 100%
|  | 145 | DAM3-02-007 |  | EF-RED 280 x125 - PN16 | IRRIGATION | Short Lead Items | EACH | 4 | 0 | APPROVED |  | 0%
|  | 146 | DAM3-02-007 |  | EF-RED 500 X 400 - PN16 | IRRIGATION | Short Lead Items | EACH | 1 | 0 | APPROVED |  | 0%
|  | 147 | DAM3-02-007 |  | EF-TEE 125x110x125 - PN16 | IRRIGATION | Short Lead Items | EACH | 58 | 50 | APPROVED |  | 86.21%
|  | 148 | DAM3-02-007 |  | EF-TEE 280x110x280 - PN16 | IRRIGATION | Short Lead Items | EACH | 2 | 0 | APPROVED |  | 0%
|  | 149 | DAM3-02-007 |  | BW-TEE 500 X 280X500-PN16+ ( EF-COUBLING 280 ) | IRRIGATION | Short Lead Items | EACH | 1 | 0 | APPROVED |  | 0%
|  | 150 | DAM3-02-007 |  | EF-EQUAL TEE 125-PN16 | IRRIGATION | Short Lead Items | EACH | 50 | 50 | APPROVED |  | 100%