## General Information
Weekly Progress Report - Construction Projects |  | 2026-09-28
Contract General Information
Project Name | Development Industrial City-Alkharj
Project ID | 3121
Contractor | Moffreh Group
Consultant | EGIS
Stage | 42nd Week
Modon PM | Rakan Alotaibi
Key Dates
Contract Award Date | 2025-11-09
Contract Sign Date | 2025-11-16
Site Handover Date | 2025-12-03
Original Completion | 2027-12-02
Contract Award Date (Hijri) | 2025-11-09
Contract Sign Date (Hijri) | 2025-11-16
Site Handover Date (Hijri) | 2025-12-03
Original Completion (Hijri) | 2027-12-02
Revised Completion Date | 2027-12-02
Committed Completion Date | 2027-12-02
Forecast Completion | 2027-12-02
Variance | 0

## Weekly Progress Report
MODON - Weekly Progress Report - Construction Projects | [29 empty] | Data Date | 2026-09-28
Contract General Information | [5 empty] | Key Dates | [5 empty] | Cost Summary (SR) | [7 empty] | Performance Summary | [5 empty] | Project Scope
Project Name | Development Industrial City-Alkharj |  |  |  |  | Contract Award | 2025-11-09 | Contract Award (Hijri) | 2025-11-09 | Revised Completion | 2027-12-02 | Original Contract Value |  | 307891320 |  | O&M Value (if any) |  | 0 | EAC | Plan Value | 31.87% | Phys. Plan Value | 47.23% | Quality Score | 91% | Development of infrastructure networks in Al-Kharj industrial city, which is located almost 100 kilometers southeast of Riyadh, The project is comprised of two zones (A , B and Labor Community Area ), which have a total area of approximately 3.50 square kilometers
Project ID | 3121 |  | Stage | 1 |  | Contract Sign | 2025-11-16 | Contract Sign (Hijri) | 2025-11-16 | Committed Completion | 2027-12-02 | Revised Contract Value |  | 307891320 |  | Submitted Invoices (Gross Value) |  | 27726580 |  | Earned Value | 32.88% | Phys. Earn Value | 42.53%
Contractor | Moffreh Group |  | Status | 32 |  | Site Handover | 2025-12-03 | Site Handover (Hijri) | 2025-12-03 | Forecast Completion | 2027-12-02 | Estimate At Completion Value |  | 307891320 |  | Penalities & Retention |  | 2883658 |  | Variance | 1% | Variance | -4.7% | Safety Score | 90%
Consultant | EGIS |  | Modon PM | Rakan Alotaibi |  | Original Completion | 2027-12-02 | Original Completion (Hijri) | 2027-12-02 | Variance | 0 | Potential Changes |  | 0 |  | FIR Value (up To date) |  | 39726580 |  | FIR % | 13% | Invoiced % | 9.005%
Progress Overview
Earned Value Progress (SAR) | [13 empty] | Physical Progress (Effort) | [11 empty] | Earned Value Progress (%)
WBS |  | BOQ Value (SAR) | % Wt. | Weekly (SAR) |  | To Date (SAR) | [7 empty] | Budgeted | % Wt. | Weekly Physical Progress |  |  |  | To Date Physical Progress
|  |  |  | Planned | Earned | Original Plan | Revised Planned | Earned | Original Plan % | Revised Planned % | Earned % | Variance | SPI | (Manhours) |  | Planned | Earned | Plan % | Earned % | Planned | Earned | Plan % | Earned % | Variance | SPI
Engineering |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 9236740 | 3% | 0 | 0 | 0% | 0% | 9236740 | 9236740 | 100% | 100% | 0% | 1
Procurement |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 61578264 | 20% | 52652 | 0 | 0% | 0% | 51633374 | 34483828 | 83.8% | 56% | -27.8% | 0.66826
Construction |  | 239411880 | 77.8% | 2657471.87 | 2753236.62 | 173573613 | 98134929.61 | 101223342.86 | 72.5% | 41% | 42.3% | 1.3% | 1.03 | 206287184 | 67% | 2289788 | 2372302 | 1.1% | 1.2% | 84557117 | 87218221 | 41% | 42.3% | 1.3% | 1.0317
Testing & Commissioning |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 30789132 | 10% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0% | 0
Close Out |  | 68479440 | 22.2% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | 0% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0% | 0
| Total | 307891320 | 100% | 2657471.87 | 2753236.62 | 173573613 | 98134929.61 | 101223342.86 | 56.37% | 31.87% | 32.88% | 1.01% | 1.03 | 307891320 | 100% | 2342440 | 2372302 | 0.76% | 0.77% | 145427231 | 130938789 | 47.23% | 42.53% | -4.7% | 0.9
Construction Milestones
[26 empty] | Item No. | Milestones |  | Original (Baseline) | Latest Plan | Forecast | Days Change
[26 empty] | 1 | Site Handover Date |  | 2025-12-03 | 2025-12-03 | 2025-12-03 | 0
[26 empty] | 2 | Complete Mobilization |  | 2026-01-02 | 2026-01-02 | 2026-01-02 | 0
[26 empty] | 3 | Road works |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 0
[26 empty] | 4 | Medium voltage network |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 0
[26 empty] | 5 | All Networks |  | 2027-02-02 | 2027-02-02 | 2027-02-02 | 0
[26 empty] | 6 | Project Handover |  | 2027-12-02 | 2027-12-02 | 2027-12-02 | 0
Performance overview
Submittals Status | [10 empty] | Quality | [10 empty] | Safety
Design | [10 empty] | Quality Reports | [10 empty] | Safety Statistics | [7 empty] | Proactive Vs Reactive Actions Taken
Item Per WBS |  | Total | Total Submitted Drawings |  |  |  |  | Remaining | Pending | Total Submittals | Quality Reports |  | Issued | Closed | Pending | Avg. Closing (Days) | Pending |  |  |  |  | Category | Item |  | This Week |  | This Month | Year to Date | Cumulative
|  |  | A | B | C | D | Processed | [9 empty] | 0-10 Days | 11-20 Days | 21-30 Days | 31-60 Days | > 60 Days
#REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [11 empty] | General | #REF! |  | #REF! |  | #REF! | #REF! | #REF! |  |  | #REF!
#REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Non Conformance (NCR) |  | 3 | 3 | 0 | #REF! | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! | #REF! | #REF! |  |  | #REF!
#REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Site Instruction (SIR) |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Reactive | #REF! |  | #REF! |  | #REF! | #REF! | #REF!
#REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Material Inspection (MIR) |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! | #REF! | #REF!
#REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Field Inspection (FIR) |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! | #REF! | #REF!
TOTAL |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Key Submittals Approval Status | [11 empty] | #REF! |  | #REF! |  | #REF! | #REF! | #REF!
Material Approval | [10 empty] | 1 Quality Plan Approval |  |  | #REF! |  | 6 Baseline Approval |  |  |  | #REF! |  |  | #REF! |  | #REF! |  | #REF! | #REF! | #REF! | Total Hours Worked Vs Safe Hours Worked
Item Per WBS |  | Total | Total Submitted Material |  |  |  |  | Remaining to approve | Pending | Total Submittals | 2 Quality Plan Last Up |  |  | #REF! |  | 7 No of Approved Version of Schedule |  |  |  | #REF! |  |  | #REF! |  | #REF! |  | #REF! | #REF! | #REF!
|  |  | A | B | C | D | Processed | with Designer |  |  | 3 Safety Plan Approval |  |  | #REF! |  | 8 Last Approved Schedule |  |  |  | #REF! |  |  | #REF! |  | #REF! |  | #REF! | #REF! | #REF!
#REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 4 Safety Plan Last Up |  |  | #REF! |  | 9 BOQ Approval Date |  |  |  | #REF! |  |  | #REF! |  | #REF! |  | #REF! | #REF! | #REF!
#REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 5 Construction Plan Approval |  |  | #REF! |  | 10 No of Approved Version of BOQ |  |  |  | #REF! |  |  | #REF! |  | #REF! |  | #REF! | #REF! | #REF!
#REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Invoices Summary | [10 empty] | Proactive | #REF! |  | 0 |  | 22(28) | #REF! | #REF!
#REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Total Submitted Invoices |  | 0 | Submitted Invoices (SAR) |  |  | 27726580 |  | Contract Value (SR) | 307891320 |  |  | #REF! |  | #REF! |  | #REF! | #REF! | #REF!
#REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | PM Approved Invoices |  | 0 | PM Approved Invoices (SAR) |  |  | 0 |  | Planned Value (SR) | 98134930 |  |  | #REF! |  | #REF! |  | #REF! | #REF! | #REF!
TOTAL |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | No of Paid Invoices |  | 0 | Paid Invoices (SAR) |  |  | 0 |  | Earned Value (SR) | 101223343 |  |  | #REF! |  | #REF! |  | #REF! | #REF! | #REF!
Procurement Summary | [10 empty] | No of Pending Invoices |  | 0 | Last Submitted Period |  |  | 2026-08-31 |  | Submitted (SAR) | 27726580 |  |  | #REF! |  | #REF! |  | #REF! | #REF! | #REF!
Item Per WBS |  | Total Materials | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Material on Site | Remaining Materials | Material Delivery Completion (Date) |  |  | Advance Payment % |  | 0% | Advance Payment (SAR) |  |  | 0 |  | PM Approved (SAR) | 0 |  | Latest Contract Change Order Log
|  |  | A | B | C | D | Processed |  |  |  | Retention % |  | 0% | Retention (SAR) |  |  | 0 |  | Total Paid (SAR) | 0
#REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | Deduction / Penalties % |  | 0% | Deduction / Penalties (SAR) |  |  | 111000 |  |  |  |  | CCO No. | Date Added | Description of Change |  |  |  |  | Status | Cost | Sch Impact (Months) | Duration
#REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | Resources at Site
#REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | Head Count - Non Manual |  |  |  | Head Count - Manual |  |  |  | Total Head Count |  |  | 0 | NA | 0 |  |  |  |  | 0 | 0 | 0 | 0
#REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | Planned | Actual | Next Month Forecast | Saudi Staff | Planned | Actual | Next Month Forecast | Saudi Staff | Total Plan | Total Actual | Variance
#REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | 4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | NA
TOTAL |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | Manpower Breakdown by Trade | [6 empty] | Major Equipment
#REF! | [10 empty] | Key Trade | Planned | Actual |  |  |  |  | Type | Planned | Actual | Idle |  | NA
#REF! | [10 empty] | #REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF!
#REF! |  |  |  |  | #REF! | [5 empty] | #REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | Major Quantity Trackers
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | BOQ N0. | Item Description |  |  |  |  | Total Qty | Measu Unit | Plan to Date | Act to Date | Variance
#REF! | 372 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! |  | #REF! | [5 empty] | #REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | Total | #REF! | #REF! |  |  |  |  | Total | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[22 empty] | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[22 empty] | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[22 empty] | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[22 empty] | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
Weekly Prgoress Photos | [15 empty] | Top Issues and Risks
Concrete barriers delivery |  |  |  |  | Temporary mobilization Area | [5 empty] | Start works in Area A |  |  |  |  | Top 5 Issues
[16 empty] | Issue No | Date Identified | Issue Description |  |  |  | Responsible | Action Taken |  |  | Mitigation |  |  |  |  | Current Status | Duration Elapsed
[16 empty] | #REF! | #REF! | [14 empty] | #REF!
[16 empty] | #REF! | #REF! | [14 empty] | #REF!
[16 empty] | #REF! | #REF! | [14 empty] | #REF!
[16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | [7 empty] | #REF! | #REF!
[16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | [7 empty] | #REF! | #REF!
Formulas:
Latest Plan = [Original (Baseline)]
Forecast = [Original (Baseline)]

## SPI
SPI Weekly Interval
| Week 1 31.Aug.2026 | Week 2 07.Sep.2026 | Week 3 14.Sep.2026 | Week 4 21.Sep.2026 | Week 5 28.Sep.2026
Planned % | 26.95% | 28.57% | 29.71% | 31.01% | 31.87%
Earned % | 28.4% | 29.89% | 30.85% | 31.98% | 32.88% |  |  |  | 0.9%
SPI | 1.05 | 1.05 | 1.04 | 1.03 | 1.03 | [5 empty] | 1.13%
Activity Name | Start | Finish | Spreadsheet Field | time axis 2026-01-03 to 2027-11-27
ICKMO1-cost unite | 2026-01-03 | 2027-12-02 | Budgeted Units | 629778.8 | 817900.7 | 1117672.09 | 1784116.5 | 2205084.52 | 3042911.66 | 3538639.32 | 2840366.39 | 3077668.83 | 2799538.98 | 2407878.89 | 1910111.43 | 2315821.6 | 2136115.22 | 1765470.3 | 2035664.23 | 2793013.91 | 1763311.51 | 1890899.81 | 1102104.94 | 918553.47 | 1121640.58 | 817572.93 | 642466.71 | 1008995.59 | 1174931 | 1435794.43 | 2239774.91 | 2646690.01 | 3094900.96 | 3129603.42 | 3592896.68 | 4072913.57 | 4283580.02 | 4325302.09 | 3073364.65 | 3471431.71 | 1517990.46 | 2124434.92 | 2116641.49 | 2766161.76 | 3036723.69 | 2980679.07 | 3154463.77 | 3361260.25 | 3092750.6 | 2820097.36 | 1936116.4 | 1689048.51 | 1631346.56 | 1526831.33 | 1100100.45 | 669938.63 | 595679.44 | 1867307.04 | 2399894.43 | 1702100.45 | 4419281.23 | 5394379.93 | 4040128.22 | 5770854.6 | 5412649.59 | 6058633.75 | 5925758.5 | 6146311.55 | 4098294.02 | 2791974.4 | 2393701.31 | 2013645.32 | 1392043.12 | 1109050.6 | 1148278.55 | 1150798.13 | 917220.47 | 1953712.53 | 2600851.42 | 1922527.92 | 2010710.95 | 1876874.42 | 1711927.2 | 2346170.56 | 1162975.55 | 1496899.51 | 2137249.3 | 1766195 | 576780.31 | 457950 | 429942.57 | 203059.3 | 154448.87 | 70202.61 | 8712.77 | [6 empty] | 19849112.99 | 39698225.98
|  |  |  | 629778.8 | 1447679.5 | 2565351.59 | 4349468.09 | 6554552.61 | 9597464.27 | 13136103.59 | 15976469.98 | 19054138.81 | 21853677.79 | 24261556.68 | 26171668.11 | 28487489.71 | 30623604.93 | 32389075.23 | 34424739.46 | 37217753.37 | 38981064.88 | 40871964.69 | 41974069.63 | 42892623.1 | 44014263.68 | 44831836.61 | 45474303.32 | 46483298.91 | 47658229.91 | 49094024.34 | 51333799.25 | 53980489.26 | 57075390.22 | 60204993.64 | 63797890.32 | 67870803.89 | 72154383.91 | 76479686 | 79553050.65 | 83024482.36 | 84542472.82 | 86666907.74 | 88783549.23 | 91549710.99 | 94586434.68 | 97567113.75 | 100721577.52 | 104082837.77 | 107175588.37 | 109995685.73 | 111931802.13 | 113620850.64 | 115252197.2 | 116779028.53 | 117879128.98 | 118549067.61 | 119144747.05 | 121012054.09 | 123411948.52 | 125114048.97 | 129533330.2 | 134927710.13 | 138967838.35 | 144738692.95 | 150151342.54 | 156209976.29 | 162135734.79 | 168282046.34 | 172380340.36 | 175172314.76 | 177566016.07 | 179579661.39 | 180971704.51 | 182080755.11 | 183229033.66 | 184379831.79 | 185297052.26 | 187250764.79 | 189851616.21 | 191774144.13 | 193784855.08 | 195661729.5 | 197373656.7 | 199719827.26 | 200882802.81 | 202379702.32 | 204516951.62 | 206283146.62 | 206859926.93 | 207317876.93 | 207747819.5 | 207950878.8 | 208105327.67 | 208175530.28 | 208184243.05 | 208184243.05 | 208184243.05 | 208184243.05 | 208184243.05 | 208184243.05 | 208184243.05 | 228033356.04 | 267731582.02
|  |  |  | 0.0023523 | 0.0054072 | 0.0095818 | 0.016246 | 0.024482 | 0.035847 | 0.049064 | 0.059673 | 0.071169 | 0.081625 | 0.090619 | 0.097753 | 0.1064 | 0.11438 | 0.12098 | 0.12858 | 0.13901 | 0.1456 | 0.15266 | 0.15678 | 0.16021 | 0.1644 | 0.16745 | 0.16985 | 0.17362 | 0.17801 | 0.18337 | 0.19174 | 0.20162 | 0.21318 | 0.22487 | 0.23829 | 0.2535 | 0.2695 | 0.28566 | 0.29714 | 0.3101 | 0.31577 | 0.32371 | 0.33161 | 0.34195 | 0.35329 | 0.36442 | 0.3762 | 0.38876 | 0.40031 | 0.41084 | 0.41807 | 0.42438 | 0.43048 | 0.43618 | 0.44029 | 0.44279 | 0.44502 | 0.45199 | 0.46095 | 0.46731 | 0.48382 | 0.50397 | 0.51906 | 0.54061 | 0.56083 | 0.58346 | 0.60559 | 0.62855 | 0.64386 | 0.65428 | 0.66322 | 0.67075 | 0.67594 | 0.68009 | 0.68438 | 0.68867 | 0.6921 | 0.6994 | 0.70911 | 0.71629 | 0.7238 | 0.73081 | 0.73721 | 0.74597 | 0.75031 | 0.75591 | 0.76389 | 0.77048 | 0.77264 | 0.77435 | 0.77596 | 0.77671 | 0.77729 | 0.77755 | 0.77759 | 0.77759 | 0.77759 | 0.77759 | 0.77759 | 0.77759 | 0.77759 | 0.85172 | 1

## Weekly Progress Photos
Weekly Progress Photos | Date | 2026-09-28

## HSE
MODON HSE Site Inspection Report
Date |  |  | 2026-09-28 |  |  |  |  | Inspected By |  |  |  | MODON PM Name |  |  | Eng\Rakan
Project ID. |  |  | KH1-02-007 |  |  |  |  | Report No. | KHJ1-02-007-MAH-ST9-1-SUV-FIR-37-00
Project Name: |  |  | Development of infrastructure in Kharj Industrial City |  |  |  |  | Contractor | MOFARREH GROUP |  |  |  | Safety Performance |  | 0 |  |  | 90%
Inspections are a snapshot in time and refer only to the practices and documentation observed at the time of the Inspection. It remains the responsibility of the Consultant and Contractor to ensure that all aspects of Health & Safety are suitably managed.
1 |  | Good Practice |  |  | 2 | Need Improvement |  |  |  | 3 | Fail (Life Threatening Activity) / Comliance with Plan & Procedures |  | N/A | Atcitty Not Applicable for this Site Inspection Report
No. | Topic | [5 empty] | Wt. | HSE Compliance | No. | Topi+U11:AB15c | [5 empty] | Wt. | HSE Compliance
1 | Access and Egress - (General access to site, segregated from vehicles, / Overhead protection, while entering into the building /Adequate lighting provided when dark or overnight work) | [5 empty] | 5% | 2 | 14 | Scaffolding - (Temp. Scaffolding Work-platform (All types) - qualified scaffolder / Inspection / Tagged / Safe Access/egress / PTW/Falsework & Formwork) | [5 empty] | 5% | 1 |  |  |  | 1 | 100 | 1
2 | Traffic Management - (Loading/unloading/sheeting/temp. routes/speed/parking/competence) | [5 empty] | 2% | 1 | 15 | Scaffolding - (Temp. Scaffolding Work-platform (All types) - qualified scaffolder / Inspection / Tagged / Safe Access/egress / PTW/Falsework & Formwork) | [5 empty] | 4% | N/A |  |  |  | 2 | 75 | 2
3 | Site Signage - (Project Notice Board & General Signage) | [5 empty] | 2% | 1 | 16 | Mobile Elevated Work platform (MEWP) - (PTW/competence requirements/conditions/inspections/tagged/training/Full-body harness) | [5 empty] | 4% | N/A |  |  |  | 3 | 0 | 3
4 | PPE Compliance - (Use, storage, stock, handling & checks - Head, Foot, Eye, Hearing) | [5 empty] | 5% | 1 | 17 | Excavation & Trenches - (PTW/Edge protection/buffer zone/Slope/Benching/Shoring/Geo-tech report/Atmospheric hazards/Acess&egress/Emergency management / MS&RA/H.E) | [5 empty] | 3% | 2 | [5 empty] | N/A
5 | Housekeeping - (Material correctly stored/Rubbish cleaned & removed daily/slips & trips hazards) | [5 empty] | 3% | 1 | 18 | Confined Space - (PTW/Training/competence/Emergency Management/MS & RA/Safe access/egress) | [5 empty] | 5% | N/A
6 | Storage of Materials - (Transporting, storage, training and use - Combustible / Flammable / Hazardous substances (COSHH) | [6 empty] | N/A | 19 | Fire Protection - (Flammable/Oxy. LPG /Combustible separated/FE's/Flashback arrestor/Sparks & slags/Smoking area/PTW/Generators/MS & RA/Emergency Management) | [6 empty] | 1 |  | Red | Serious injury or death (immediately)
7 | Site Waste Management - (Hazardous waste /Combustible waste / Human waste / Construction waste - asphalt, cable, timber, paving roof sheeting tiles, plastic & bricks) | [5 empty] | 3% | 1 | 20 | Health & Welfare - (Adequate drinking water/shaded - eating & rest area/washing & sanitary facilities/Certified FA/FA Box & Stock/adequate toilets/Ambulance) | [6 empty] | 2 |  | Yellow | Minor or near miss (3 days to comply)
8 | Health Surveillance - (Expose to excessive noise/vibration/dust/silica/CO/cement/radiation/extreme weather condition) | [5 empty] | 3% | 1 | 21 | Environmental Incident Measures - (Spill/ Leakage / Concrete wash / vehicle & eqpts. wash / waste disposal/Sewers and drains/emissions/Emergency Management/Training/site run-off water) | [5 empty] | 5% | 2 |  | Green | No issues
9 | Electrical Safety - (Electrical qualified /RCD/GFCI/Industrial Cocket/LOTO/Cable-overhung or buried/Cords in good condition/current inspection tag) | [5 empty] | 3% | 2 | 22 | HSE Communications & Meetings - (Schedule HSE Meetings/Safety Committee meetings/Alerts / Lesson learned/Safety Bulletin contains latest HSE KPI) | [5 empty] | 5% | 1
10 | Tools & Equipment - (Includes, powered, hydraulic & pneumatic/Guards in place/Properly stored/RCD Protection/Earthed/Good condition & tagged) | [5 empty] | 3% | 2 | 23 | HSE Plan & Associated Procedures - (Approved updated HSE Plan/ CEMP/HAZComm/Procedures/Standards/Project Safety Risk Register) | [5 empty] | 3% | 1 |  | 26 points > 4 minors then is it’s a serious issue
11 | Manual Handling - (Lifting/loading/pulling/pushing/twisting/awkward posture/repetitive task/frequent and prolong physical effort/Reasonable practicable use of mechanical aid) | [5 empty] | 3% | 1 | 24 | Health, Safety & Environment Incident reporting - (Review of HSE Statistics, Reporting of Unsafe Act & Conditions/ Reporting of Near Miss incident/Reporting of FA cases/Record MT cases) | [5 empty] | 3% | N/A
12 | Vehicle and mobile equipment / Plant - (dumpers; excavators, cranes, piling rigs, grader, roller, loaders/condition/KSA License/certification) | [5 empty] | 3% | 2 | 25 | HSE Awareness, Training & Competence - (Policy /Objective & targets/Information, training/Climatic condition awareness/Reponses in emergency situation/ Safety Behavior Observation) | [5 empty] | 4% | 1
13 | Lifting Operations & Rigging - (Lifting Plan/Lifting devices & gears/PTW/Condition/3rd party certification/bank-man/rigger/slingers/man-basket/inspection record/tagged) | [5 empty] | 3% | 1 | 26 | Project Leadership Site Tours - (Provide evidence of proactive safety performance/Deficient discovered discussed/Positive feedback/Workers resolving safety issues) | [6 empty] | 2
Prepared by: |  |  |  | Mohamed Adel |  |  |  |  | Sent to MODON PM: |  |  |  | Eng\Rakan
Safety Results
1 |  | 13 |  |  |  | 2 |  | 8 |  |  | 3 | 0

## HSE-Stat
WEEKLY SAFETY STATISTICS REPORT
Category | Item | This Week | This Month | Year to Date | Cumulative
Reactive | Total Hours Worked | 39540 | 163990 | 1006985 | 1006985
| Safe Hours Worked | 39540 | 163990 | 1006985 | 1006985
| LTI | 0 | 0 | 0 | 0
| MTC (Healed w/o Disability) | 0 | 0 | 0 | 0
| MTC (Healed w/ Disability) | 0 | 0 | 0 | 0
| Near Miss | 0 | 0 | 2 | 2
| First Aid Cases | 0 | 1 | 6 | 6
| Fatality | 0 | 0 | 0 | 0
| Fire Incident Cases | 0 | 0 | 0 | 0
| Vehicle Incident | 0 | 0 | 0 | 0
| Property Damages | 0 | 0 | 3 | 3
Proactive | Induction Training | 13 | 72 | 1847 | 1847
| No.of Internal Training | 1 | 5 | 64 | 64
| No.of Internal Audit | 0 | 0 | 0 | 0
| No. of Toolbox Talks | 1 | 4 | 213 | 213
| Safety Awards/Incentives | 0 | 0 | 9 | 9

## Quality
QC OBSERVATIONS CHECKLIST
2025-03-04
Project No. |  |  | KHJ1-02-007 |  |  | OBS No. |  |  |  | 42 |  |  | Inspection Day: | 20-September-2026 to 26-September-2026
Project |  |  | DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY (MODON), RIYADH | [6 empty] | Contractor: Consultant: |  |  | MOFFAREH ALHARBI & PARTNERS Egis Saudi Egnieering
4 |  | Excellent |  | Quality Management System is being practiced and applies to MODON System | [10 empty] | 90 - 100 |  | QC Overall Score | 91% |  |  |  |  | 0% | 100 | 0.22883
3 |  | Good |  | Evidence of compliance with plans and procedures. | [10 empty] | 80 - 89 | [7 empty] | 0 | 89 | 0.20366
2 |  | Average |  | Indication level of compliance with standards but there is room for improvement | [10 empty] | 70 - 79 | [8 empty] | 79 | 0.18078
1 |  | Improve |  | Quality and Control is NOT being managed effectively. Needs Improvement | [10 empty] | ≤ 69 | [8 empty] | 69 | 0.15789
0 |  | N/A |  | Item was not applicable or this item was not reviewed during the inspection. | [10 empty] | Zero | [8 empty] | 100 | 0.22883
No. | Topic |  |  |  |  | E (4) | G (3) | A (2) | I (1) | N/A (0) | No. | Topic |  |  | E (4) | G (3) | A (2) | I (1) | N/A (0) |  |  |  |  | 437
[6 empty] | 100% | 89% | 79% | 69% | 100% |  |  |  |  | 100% | 89% | 79% | 69% | 100% | 0.91
1 | Control of Access to Site/Office | [5 empty] | 1 |  |  |  | 30 | QC of Excavation |  |  |  | 1 |  |  |  | 0.89 | 0.89 | [6 empty] | Item Count | Score | Distributtion
2 | Document Control Administration | [5 empty] | 1 |  |  |  | 31 | QC of Roads/Round about |  |  |  | 1 |  |  |  | 0.89 | 0.89 | [8 empty] | Overall | Relevant
3 | Project Documents and Progress | [5 empty] | 1 |  |  |  | 32 | QC of Interlock & Curbstone |  |  |  | 1 |  |  |  | 0.89 | 0.89 | 4 | 58 | counts |  | 4 | Excellent | 0 | 0 | 0% | 0%
4 | Contractor's Quality Plan/CM (Updated and Reviewed) | [5 empty] | 1 |  |  |  | 33 | Layers/Backfilling Sampling |  |  |  | 1 |  |  |  | 0.89 | 0.89 | 3 | 58 | counts |  | 3 | Good | 41 | 123 | 70.69% | 91.11%
5 | MS Log and Paperwork | [5 empty] | 1 |  |  |  | 34 | Pump Stations Units | [6 empty] | 1 | 0.89 | 1 | 2 | 58 | counts |  | 2 | Average | 4 | 8 | 6.9% | 8.89% |  | NB: Insert 1, or 0 in the required cell only.
6 | RFI, FIR, & MIR Procedure | [5 empty] | 1 |  |  |  | 35 | Quality of Form Work |  |  |  | 1 |  |  |  | 0.89 | 0.89 | 1 | 58 | counts |  | 1 | Improve | 0 | 0 | 0% | 0%
7 | RFI, FIR, & MIR Inventory system | [5 empty] | 1 |  |  |  | 36 | Design Change List | [6 empty] | 1 | 0.89 | 1 | 0 | 58 | counts |  | 0 | N/A | 13 | 0 | 22.41% | -
8 | NCRs Control & Procedure | [5 empty] | 1 |  |  |  | 37 | Quality of Concrete Placing |  |  |  | 1 |  |  |  | 0.89 | 0.89 | [5 empty] | Total | 58 | 131 | 100% | 100%
9 | NCR Log | [5 empty] | 1 |  |  |  | 38 | Concrete Surface Finishing |  |  |  | 1 |  |  |  | 0.89 | 0.89
10 | MODON Standard* | [5 empty] | 1 |  |  |  | 39 | Pedestals/Columns/Beams Alignment |  |  |  |  | 1 |  |  | 0.89 | 0.79 | [6 empty] | Maz Score Available: | 180 | <- Excludes N/A items
11 | Project Risk Plan/Management* | [5 empty] | 1 |  |  |  | 40 | Siporex Lifting & Unloading | [6 empty] | 1 | 0.89 | 1
12 | Monthly Quality Reports* | [5 empty] | 1 |  |  |  | 41 | Siporex Quality Pre-installation | [6 empty] | 1 | 0.89 | 1
13 | ITP | [5 empty] | 1 |  |  |  | 42 | Siporex Finishing Quality | [6 empty] | 1 | 0.89 | 1 | [5 empty] | Total Score |  | Percentage (%)
14 | MODON Weekly Report | [5 empty] | 1 |  |  |  | 43 | Roads / Parking Markings | [6 empty] | 1 | 0.89 | 1 |  | 58 |  |  |  | 131 |  | 72.78 |  | %
15 | Design Change Official Paperwork* | [6 empty] | 1 |  |  | 44 | QC of Finishing Outdoors | [6 empty] | 1 | 0.79 | 1 | [5 empty] | Max Score Available | [6 empty] | 31
16 | Design Change was Applied* | [5 empty] | 1 |  |  |  | 45 | Quality of Finishing Indoors |  |  |  | 1 |  |  |  | 0.89 | 0.89 | [5 empty] | 180 | [6 empty] | 32
17 | Material List | [5 empty] | 1 |  |  |  | 46 | Stairs Quality | [6 empty] | 1 | 0.89 | 1 | [12 empty] | 33
18 | Pending Material Status | [5 empty] | 1 |  |  |  | 47 | Tanks Method Statement Work | [6 empty] | 1 | 0.89 | 1 | [12 empty] | 34
19 | Lifting Plan* | [5 empty] | 1 |  |  |  | 48 | Electric Rooms | [6 empty] | 1 | 0.89 | 1 | [12 empty] | 35
20 | DWG Log | [5 empty] | 1 |  |  |  | 49 | QC of MCC/ATS Plant Units | [6 empty] | 1 | 0.89 | 1 | [12 empty] | 36
21 | Invoice Status | [6 empty] | 1 |  |  | 50 | Qualified Subcontractor |  |  |  | 1 |  |  |  | 0.79 | 0.89 | [12 empty] | 37
22 | Site Handover Letter | [8 empty] | 1 | 51 | Scaffold/Ladders/Slope/Bridge Compliance |  |  |  | 1 |  |  |  | 1 | 0.89 | [12 empty] | 38
23 | Material Testing Results & Certification | [5 empty] | 1 |  |  |  | 52 | Protection Applied to Completed Work |  |  |  | 1 |  |  |  | 0.89 | 0.89
24 | As Build Drawings Status* | [8 empty] | 1 | 53 | Storage Management in/out Control |  |  |  | 1 |  |  |  | 1 | 0.89
25 | Calibrated Lab Tools & Equipment | [5 empty] | 1 |  |  |  | 54 | Material Control |  |  |  | 1 |  |  |  | 0.89 | 0.89
26 | Storage Inventory System | [5 empty] | 1 |  |  |  | 55 | Manholes Storing and Quality |  |  |  | 1 |  |  |  | 0.89 | 0.89
27 | Logistics Plan | [5 empty] | 1 |  |  |  | 56 | Reinforced Steel Quality |  |  |  | 1 |  |  |  | 0.89 | 0.89
28 | Project Progress Planview | [6 empty] | 1 |  |  | 57 | Safety Overview |  |  |  | 1 |  |  |  | 0.79 | 0.89
29 | Sufficient Number of QC Inspectors | [5 empty] | 1 |  |  |  | 58 | Waste Management Control |  |  |  | 1 |  |  |  | 0.89 | 0.89
Score
[8 empty] | *QC % |  |  | 91%
Prepared by: |  |  |  | Engr. Adil Ghafoor Sulehria | [6 empty] | Issued to PM:
*QC Observations refer only to the practices and documentation observed at time of inspection. The responsibility of the CM and Contractor is to ensure that aspects of Quality are suitably managed. *Scores are a reflection of the general site conditions based upon the findings at the time of the walk through *If Applicable

## Quality-Stat
| Project ID: | KHJ1-02-007 |  | WEEKLY QUALITY STATISTICS REPORT (WQSR)
| Project Name: | DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY (MODON), RIYADH
Contractor: MOFFAREH ALHARBI & PARTNERS | For the Week of: | 20-September-2026 to 26-September-2026
Document Ref. Number | QWR-0042
The Following facts (provided as guideline) in figures indicate the current trends of Quality highlights improvement and areas of concerns as well towards overall site Quality aspects of this project.
GENERAL | Previous Week | This Week | Cumulative | Brief Description/Comment
Planned Project Progress | 29.71 | 1.3 | 31.01 | As Pre Revised Schedule
Actual Project Progress | 30.85 | 1.1 | 31.98
QAC Leading Indicators |  |  |  | Brief Description/Comment
No. of Quality Induction conducted | 1 | 0 | 1
No. of Quality Training Delivered* | 10 | 0 | 10
No. of Approved Field Inspection Report (FIR) | 52505 | 248 | 52753
No. of Rejected Field Inspection Report (FIR) | 0 | 14 | 14
No. of under review Field Inspection Report (FIR) | 0 | 31 | 31
No. of Approved Material Inspection Request (MIR) | 185 | 4 | 189 | 0.96
No. of Rejected Material Inspection Request (MIR) | 0 | 0 | 0
No. of Request For Information (RFI) - Open | 0 | 1 | 1
No. of Request For Information (RFI) - Closed | 116 | 2 | 118
No. of Approved Material Received Inspection Report (MRIR) | 103 | 0 | 103
No. of Rejected Material Received Inspection Report (MRIR) | 0 | 0 | 0
No. of Review/Approved Shop drawings | 2081 | 1 | 2028
No. of Rejected Shop drawings | 5 | 0 | 5
No. of under review Shop drawings | 20 | 5 | 25
Copy of weekly MOM and progress status* | 6 | 0 | 6
No. of Inspection & Test Plan (ITP) Reviewed/approved* | 29 | 1 | 30
No. of Quality inspections/Site walkthrough performed* | 104 | 0 | 104
No. of Quality Site Instruction Issued* | 7 | 0 | 7
No. of Non-Conformance Report (NCR) issued* | 36 | 1 | 37
Type & No. of Test performed* | 2003 | 93 | 2096 | Compaction-Soil Sampling-Borehole-Concrete Compressive Test
Amount & No.of Penalties/Fines Applied* | 7 | 0 | 7
No. of Change/ Variation Request | 0 | 0 | 0
No. of critical long lead iteams and status* | 0 | 0 | 0
No. of Internal/External Audit Conducted | 5 | 0 | 0
Work Done this week
E.g. 1 - Quality Toolbox Meeting for Borehole Geotechnical Investigation, Drilling and Sampling Activities. 2 - Quality inspections/Site walkthrough performed. 3 - Internal weekly MOM done.
Name: Adil Ghafoor |  |  |  | Approved By:
Position: QA QC Manager |  |  |  | Position:
Signature: |  |  |  | Signature:

## Weekly Quality
DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY (MODON), RIYADH | [25 empty] | DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY (MODON), RIYADH
The Contractor : MOFFAREH ALHARBI & PARTNERS | [25 empty] | The Contractor : MOFFAREH ALHARBI & PARTNERS
Report Number:KHJ1-02-007-MAH-TS9-1-QMS-QWR-0027-00 Contractors’ Submittal 20-September-2026 to 26-September-2026 ) | [25 empty] | 20-September-2026 to 26-September-2026
| FIR Detail | [8 empty] | NCR Detail | [6 empty] | MAR Detail | [9 empty] | Shop Drawing | [9 empty] | ITP ( Inspection Test Plan) | [8 empty] | MES ( Method statement)
|  | Received |  |  | Code A | Code B | Code C/D | UR | KPI % |  | Issued/Received |  |  | Closed | OPEN | KPI % |  | Received |  |  | Code A | Code B | Code C/D | UR | KPI % |  |  | Received |  |  | Code A | Code B | Code C/D | UR | KPI % |  |  | Received |  |  | Code A | Code B | Code C/D | UR | KPI % |  | Received |  |  | Code A | Code B | Code C/D | UR | KPI %
|  | Previous | Current | Cumulative | [6 empty] | Previous | Current | Cumulative |  |  |  |  | Previous | Current | Cumulative |  |  |  | UR |  |  |  | Previous | Current | Cumulative | [7 empty] | Previous | Current | Cumulative | [6 empty] | Previous | Current | Cumulative
| CIV |  | 13 |  | 3 | 9 | 0 | 1 |  | CIV |  | 0 |  | 0 | 0 |  | CIV |  | 0 |  | 0 | 0 | 0 | 0 |  |  | CIV |  | 0 |  | 0 | 0 | 0 | 0 |  |  | CIVIL |  | 0 |  | 0 | 0 | 0 | 0 |  | CIVIL |  | 0 |  | 0 | 0 | 0 | 0
| Road |  | 48 |  | 2 | 41 | 2 | 3 |  | Electrical |  | 0 |  | 0 | 0 |  | Electrical |  | 0 |  | 0 | 0 | 0 | 0 |  |  | Electrical |  | 0 |  | 0 | 0 | 0 | 0 |  |  | MEP |  | 0 |  | 0 | 0 | 0 | 0 |  | MEP |  | 0 |  | 0 | 0 | 0 | 1
| CBC |  | 14 |  | 2 | 11 | 1 | 0 |  | Mechanical |  | 1 |  | 0 | 1 |  | Mechanical |  | 0 |  | 0 | 0 | 0 | 0 |  |  | Mechanical |  | 0 |  | 0 | 0 | 0 | 0 |  |  | ELECTRICAL |  | 0 |  | 0 | 0 | 0 | 0 |  | ELECTRICAL |  | 0 |  | 0 | 0 | 0 | 0
| MEC |  | 0 |  | 0 | 0 | 0 | 0 |  | Sewer |  | 0 |  | 0 | 0 |  | Arc |  | 0 |  | 0 | 0 | 0 | 0 |  |  | General |  | 0 |  | 0 | 0 | 0 | 0 |  |  | ROD |  | 1 |  | 0 | 1 | 0 | 0 |  | ARC |  | 0 |  | 0 | 0 | 0 | 0
| Sewer |  | 48 |  | 0 | 43 | 0 | 5 |  | General |  | 0 |  | 0 | 0 |  | IRI |  | 0 |  | 0 | 0 | 0 | 0 |  |  | Arch |  | 0 |  | 0 | 0 | 0 | 0 |  |  | TEL |  | 0 |  | 0 | 0 | 0 | 0 |  | TEL |  | 1 |  | 0 | 0 | 1 | 0
| Storm |  | 89 |  | 0 | 74 | 2 | 13 | [18 empty] | ROAD |  | 0 |  | 0 | 0 | 0 | 0 |  |  | Arc |  | 0 |  | 0 | 0 | 0 | 0
| Electrical |  | 20 |  | 1 | 14 | 1 | 4 | [18 empty] | SEW |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
| TEL |  | 9 |  | 0 | 7 | 1 | 1 | [18 empty] | TEL |  | 0 |  | 0 | 0 | 0 | 0
| IRR |  | 21 |  | 0 | 14 | 3 | 4 | [18 empty] | STR |  | 0 |  | 0 | 0 | 0 | 0
| Survey |  | 0 |  | 0 | 0 | 0 | 0 | [18 empty] | CBC |  | 0 |  | 0 | 0 | 0 | 0
| POT |  | 31 |  | 1 | 26 | 4 | 0 | [18 empty] | LSC |  | 1 |  | 0 | 1 | 0 | 0
[27 empty] | IRR |  | 0 |  | 0 | 0 | 0 | 0 |  | 81
[27 empty] | POT |  | 0 |  | 0 | 0 | 0 | 0
| TOTAL |  | 293 |  | 9 | 239 | 14 | 31 | 95 | TOTAL |  | 0 |  | 0 | 0 | 0 | TOTAL |  | 0 |  | 0 | 0 | 0 | 0 | 100 |  | MEP |  | 0 |  | 0 | 0 | 0 | 0 |  |  | TOTAL |  | 0 |  | 0 | 1 | 0 | 0 | 100 | TOTAL |  | 1 |  | 0 | 0 | 1 | 0 | 0
[27 empty] | STR |  | 0 |  | 0 | 0 | 0 | 0
[27 empty] | TOTAL |  | 1 |  | 0 | 1 | 0 | 0 | 100
| PQD (Prequalification Documents) | [8 empty] | SIR/SOR Detail | [6 empty] | MRIR | [9 empty] | As built Drawing | [9 empty] | MIR ( Material Receiving Inspection)
|  | Received |  |  | Code A | Code B | Code C/D | UR | KPI % |  | Issued/Received |  |  | Closed | OPEN | KPI % |  | Received |  |  | Code A | Code B | Code C/D | UR | KPI % |  |  | Received |  |  | Code A | Code B | Code C/D | UR | KPI % |  |  | Received |  |  | Code A | Code B | Code C/D | UR | KPI %
|  | Previous | Current | Cumulative | [6 empty] | Previous | Current | [5 empty] | Previous | Current | Cumulative | [7 empty] | Previous | Current | Cumulative | [7 empty] | Previous | Current | Cumulative
| CIV |  | 0 |  | 0 | 0 | 0 | 0 |  | CIV |  | 0 |  | 0 | 0 |  | CIV |  | 0 |  | 0 | 0 | 0 | 0 |  |  | CIV |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CIV/ROD |  | 3 |  | 2 | 0 | 0 | 1
| ARCH |  | 0 |  | 0 | 0 | 0 | 0 |  | ARCH |  | 0 |  | 0 | 0 |  | ARCH |  | 0 |  | 0 | 0 | 0 | 0 |  |  | ARCH |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | ARCH |  | 0 |  | 0 | 0 | 0 | 0
| Electrical |  | 0 |  | 0 | 0 | 0 | 0 |  | Electrical |  | 0 |  | 0 | 0 |  | Electrical |  | 0 |  | 0 | 0 | 0 | 0 |  |  | Electrical |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Electrical |  | 0 |  | 0 | 0 | 0 | 0
| Mechanical |  | 0 |  | 0 | 0 | 0 | 0 |  | Mechanical |  | 0 |  | 0 | 0 |  | MEP |  | 0 |  | 0 | 0 | 0 | 0 |  |  | Mechanical |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Mechanical |  | 1 |  | 1 | 0 | 0 | 0
| General |  | 0 |  | 0 | 0 | 0 | 0 |  | General |  | 0 |  | 0 | 0 |  | Tel |  | 0 |  | 0 | 0 | 0 | 0 |  |  | General |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Telecom |  | 0 |  | 0 | 0 | 0 | 0
[17 empty] | Storm |  | 0 |  | 0 | 0 | 0 | 0 | [12 empty] | Storm |  | 0 |  | 0 | 0 | 0 | 0
[17 empty] | CBC |  | 0 |  | 0 | 0 | 0 | 0 | [12 empty] | General |  | 0 |  | 0 | 0 | 0 | 0
[17 empty] | ROD |  | 0 |  | 9 | 0 | 0 | 0 | [12 empty] | CBC |  | 2 |  | 1 | 0 | 0 | 1
| TOTAL |  | 0 |  | 0 | 0 | 0 | 0 | 100 | [7 empty] | TOTAL |  | 0 |  | 0 | 0 | 0 | 0 | 100 |  | TOTAL |  | 0 |  | 0 | 0 | 0 | 0 | 100 |  | LSC |  | 0 |  | 0 | 0 | 0 | 0
[10 empty] | TOTAL |  | 0 |  | 0 | 0 | 100 | [20 empty] | TOTAL |  | 6 |  | 4 | 0 | 0 | 2 | 100

## FIR Summary
QC OBSERVATIONS CHECKLIST FIR Summary
Serial # | FIR # | FIR Description | Date | Duration days | Comments
1.Civil (CIV)
1 | KHJ1-02-007-MAH-TS9-1-CIV-FIR-0147 | Inspection for Application of anti termite at Mosque floor as per highlight on attached (Mosque Area) | 2026-09-19 |  | Accepted
2 | KHJ1-02-007-MAH-TS9-1-CIV-FIR-0148 | Inspection for Application of polyethylene sheet Mosque floor as per highlight on attached (Mosque Area) | 2026-09-19 |  | Accepted
3 | KHJ1-02-007-MAH-TS9-1-CIV-FIR-0150 | Inspection for Reinforcement Steel Mosque Floor Slab on Grade in Mosque and Beam and Slab for Minaret as per highlight on attached (Mosque Area) | 2026-09-20 |  | Accepted
1 | KHJ1-02-007-MAH-TS9-1-CIV-FIR-0146 | Location, level and Compaction for Backfilling 13th layer at (level 499.80) as per highlighted in attached approved Shop Drawing Mosque Area | 2026-09-21 |  | Accepted as Noted
2 | KHJ1-02-007-MAH-TS9-1-CIV-FIR-0149 | Inspection for Blinding Concrete Pouring inside the Mosque foundations of Under Slab on Grade as per highlight drawing (Mosque Area) | 2026-09-21 |  | Accepted as Noted
3 | KHJ1-02-007-MAH-TS9-1-CIV-FIR-0151 | Inspection for Pouring Concrete Mosque floor Slab on Grade as per highlight on attached (Mosque Area) | 2026-09-21 |  | Accepted as Noted
4 | KHJ1-02-007-MAH-TS9-1-CIV-FIR-0152 | Inspection for Pouring Concrete Beams for Minaret (Level+16.60) as per highlight on attached (Mosque Area) | 2026-09-21 |  | Accepted as Noted
5 | KHJ1-02-007-MAH-TS9-1-CIV-FIR-0153 | Inspection for Pouring Concrete Roof Slab for Minaret (Level+16.60) as per highlight on attached (Mosque Area) | 2026-09-21 |  | Accepted as Noted
6 | KHJ1-02-007-MAH-TS9-1-CIV-FIR-0154 | Location, level and Compaction for Backfilling of thickness 20cm around the Mosque as per highlight on attached (Mosque Area) | 2026-09-24 |  | Accepted as Noted
7 | KHJ1-02-007-MAH-TS9-1-CIV-FIR-0155 | Inspection for Blinding Concrete Pouring inside the Mosque foundations of Under Slab on Grade as per highlight drawing (Mosque Area) | 2026-09-24 |  | Accepted as Noted
8 | KHJ1-02-007-MAH-TS9-1-CIV-FIR-0156 | Inspection for Reinforcement Steel Mosque Floor Slab on Grade as per highlight on attached (Mosque Area) | 2026-09-24 |  | Accepted as Noted
9 | KHJ1-02-007-MAH-TS9-1-CIV-FIR-0157 | Inspection for Pouring Concrete Mosque Floor Slab on Grade as per highlight on attached (Mosque Area) | 2026-09-24 |  | Accepted as Noted
1 | KHJ1-02-007-MAH-TS9-1-CIV-FIR-0158 | Location, level and Compaction for Backfilling 2nd layersof thickness 10 cm around the Mosque as per highlight on attached (Mosque Area) | 2026-09-26 |  | UR-Under Review
2.Road (ROD)
1 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0770 | Inspection for the removal of non-compliant aggregate Base Course Material for the closure of INCR # 0051 from Station 0+350 to 0+550 Local Collector Road #02 Zone B | 2026-09-22 |  | Accepted
2 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0796 | Sampling for Trial Mix for Bitumen Base Course (BBC) & Bitumen Wearing Course (BWC) & Raw Material at Tamdeen Asphalt Batch Plant. | 2026-09-22 |  | Accepted
1 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0767 | Inspection for Placement, Location, level and Compaction for Backfilling (A-2-4) from Stockpile # 10 of Sub Grade 2nd laye from Station 0+225 to 0+275 at Local Road # 10 Zone A. | 2026-09-21 |  | Accepted as Noted
2 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0768 | Location, level and Compaction for Backfilling (A-2-4) from Stockpile # 10 (Correction Layer) Bottom of Sub Grade from Station 0+187 to 0+300 at Collector Road # 01 Zone A. | 2026-09-21 |  | Accepted as Noted
3 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0769 | Inspection for Placement, Location, level and Compaction for Backfilling (A-2-4) from Stockpile # 10 of Sub Grade 2nd layer from Station 0+125 to 0+325 at Local Road # 08 Zone A. | 2026-09-21 |  | Accepted as Noted
4 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0771 | Inspection for Placement, Location, level and Compaction for 1st layer of Sub Grade from Station 1+875 to 2+100 at Collector Road #02 Zone B. | 2026-09-22 |  | Accepted as Noted
5 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0772 | Location, level and Compaction of Placement of Aggregate Base Course (200mm) Right Side Remaining Area from Station 0+550 to 0+750 at Arterial Road - 01 Zone B. | 2026-09-24 |  | Accepted as Noted
6 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0773 | Inspection for Sampling, Testing and Placement of Bituminous Base Course (70mm) Station 0+300 to 0+600 at Local Road - 04 Zone A | 2026-09-21 |  | Accepted as Noted
7 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0774 | Inspection for Sampling, Testing and Placement of Bituminous Base Course 1st layer (80mm) from Station 0+825to 0+970 (RHS) at Collector Road - 01 Zone A | 2026-09-21 |  | Accepted as Noted
8 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0775 | Inspection for Sampling, Testing and Placement of Bituminous Base Course 1st layer (80mm) from Station 0+825to 0+970 (LHS) at Collector Road - 01 Zone A | 2026-09-21 |  | Accepted as Noted
9 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0776 | Inspection for Placement, Location, level and Compaction of Aggregate Base Course(200mm) (A-1-a) from Station 0+400 to 0+600 at Local Road -08 Zone A | 2026-09-22 |  | Accepted as Noted
10 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0777 | Inspection for Placement, Location, level and Compaction for Backfilling (A-2-4) from Stockpile # 10 of Sub Grade 2nd laye from Station 0+025 to 0+650 at Local Road # 09 Zone A. | 2026-09-22 |  | Accepted as Noted
11 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0778 | Location, level and Compaction for Backfilling (A-2-4) from Stockpile # 10 (Correction Layer) Bottom of Sub Grade from Station 0+050 to 0+100 at Local Road # 11 Zone A. | 2026-09-22 |  | Accepted as Noted
12 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0779 | Inspection for Placement, Location, level and Compaction for Backfilling (A-2-4) from Stockpile # 10 of Sub Grade 1st laye from Station 0+190 to 0+300 at Collector Road # 01 Zone A. | 2026-09-22 |  | Accepted as Noted
13 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0780 | Inspection of Application of Prime Coat from Station 0+400 to 0+600 at Local Road -08 Zone A | 2026-09-21 |  | Accepted as Noted
14 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0782 | Inspection for Placement, Location, level and Compaction for Backfilling Up to TOE Layer (Bottom of Sub Grade) from Station 2+375 to 2+800 at Collector Road - 02 Zone B. | 2026-09-22 |  | Accepted as Noted
15 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0783 | Location, level and Compaction of Placement of Aggregate Base Course (200mm) from Station 0+025 to 0+62.5 at Local Road - 23 Zone B. | 2026-09-24 |  | Accepted as Noted
16 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0784 | Location, level and Compaction of Placement of Aggregate Base Course (200mm) Right Side Remaining Area from Station 0+750 to 0+900 at Arterial Road - 01 Zone B. | 2026-09-24 |  | Accepted as Noted
17 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0785 | Location, level and Compaction of Placement of Aggregate Base Course (200mm) Left Side Remaining Area from Station 0+750 to 0+900 at Arterial Road - 01 Zone B. | 2026-09-24 |  | Accepted as Noted
18 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0786 | Inspection for Application of Prime Coat Left Side Remaining Area from Station 0+750 to 0+900 and Right Side Remaining Area from Station 0+750 to 0+900 at Arterial Road - 01 Zone B.at Arterial Road - 01 Zone B. | 2026-09-24 |  | Accepted as Noted
19 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0787 | Inspection for Application of Tack Coat from Station 0+825to 0+970 (Both Side) at Collector Road - 01 Zone A | 2026-09-21 |  | Accepted as Noted
20 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0788 | Inspection for Sampling, Testing and Placement of Bituminous Base Course 2nd layer (70mm) from Station 0+825to 0+970 (RHS) at Collector Road - 01 Zone A | 2026-09-21 |  | Accepted as Noted
21 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0789 | Inspection for Sampling, Testing and Placement of Bituminous Base Course 2nd layer (70mm) from Station 0+825to 0+970 (LHS) at Collector Road - 01 Zone A | 2026-09-21 |  | Accepted as Noted
22 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0791 | Inspection for Placement, Location, level and Compaction for 1st layer of Sub Grade from Station 0+625 to 0+775 at Collector Road #02 Zone B. | 2026-09-22 |  | Accepted as Noted
23 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0792 | Location, level and Compaction for Backfilling (A-2-4) from Stockpile # 10 (Correction Layer) Bottom of Sub Grade from Station 0+040 to 0+250 at Local Road # 12 Zone A. | 2026-09-24 |  | Accepted as Noted
24 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0793 | Core sampling Inspection for Bitumen Base course (70mm) Station 0+300 to 0+600 at Local Road - 04 Zone A | 2026-09-22 |  | Accepted as Noted
25 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0794 | Core sampling Inspection for Bitumen Base course (15cm) Station (0+825 to 0+970) RHS (1st & 2nd Layer) at Collector Road # 01 Zone A | 2026-09-22 |  | Accepted as Noted
26 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0795 | Core sampling Inspection for Bitumen Base course (15cm) Station (0+825 to 0+970) LHS (1st & 2nd Layer) at Collector Road # 01 Zone A | 2026-09-22 |  | Accepted as Noted
27 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0797 | Inspection for Placement, Location, level and Compaction for Backfilling (A-2-4) from Stockpile #10 of Sub Grade 2nd laye from Station 0+187.5 to 0+300 at Collector Road # 01 Zone A. | 2026-09-24 |  | Accepted as Noted
28 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0798 | Location, level and Compaction for Backfilling (A-2-4) from Stockpile # 10 (Correction Layer) Bottom of Sub Grade from Station 0+010 to 0+025 (full width) at Local Road # 13 Zone A. | 2026-09-24 |  | Accepted as Noted
29 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0799 | Location, level and Compaction for Backfilling (A-2-4) from Stockpile # 10 (Correction Layer) Bottom of Sub Grade from Station 0+010 to 0+025 (full width) at Local Road # 14 Zone A. | 2026-09-24 |  | Accepted as Noted
30 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0800 | Inspection for Placement, Location, level and Compaction for Backfilling Up to TOE Layer (Bottom of Sub Grade) from Station 0+975 to 1+250 at Collector Road - 02 Zone B. | 2026-09-24 |  | Accepted as Noted
31 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0801 | Location, level and Compaction of Placement of Aggregate Base Course (200mm) Left Side of Road from Station 0+150 to 0+550 at Collector Road - 02 Zone B. | 2026-09-24 |  | Accepted as Noted
32 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0803 | Inspection for Application of Prime Coat Left Side of Road from Station 0+150 to 0+550 at Collector Road - 02 Zone B. | 2026-09-24 |  | Accepted as Noted
33 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0805 | Inspection for Placement, Location, level and Compaction for Backfilling (A-2-4) from Stockpile # 10 of Sub Grade 1st layer from Station 0+010 to 0+025 (full width) at Local Road # 13 Zone A. | 2026-09-24 |  | Accepted as Noted
34 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0806 | Inspection for Placement, Location, level and Compaction for Backfilling (A-2-4) from Stockpile # 10 of Sub Grade 1st layer from Station 0+010 to 0+025 (full width) at Local Road # 14 Zone A. | 2026-09-24 |  | Accepted as Noted
35 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0808 | Inspection of Application of Prime Coat fromStation 0+125 to 0+400 at Local Road -08 Zone A | 2026-09-24 |  | Accepted as Noted
36 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0809 | Inspection for Placement, Location, level and Compaction for Backfilling (A-2-4) from Stockpile # 10 of Sub Grade 1st layer from Station 0+050 to 0+100 at Local Road # 11 Zone A. | 2026-09-24 |  | Accepted as Noted
37 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0811 | Inspection for Placement, Location, level and Compaction for Backfilling (A-2-4) from Stockpile # 10 of Sub Grade 2nd layer from Station 0+010 to 0+025 (full width) at Local Road # 13 Zone A. | 2026-09-26 |  | Accepted as Noted
38 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0812 | Inspection for Placement, Location, level and Compaction for Backfilling (A-2-4) from Stockpile # 10 of Sub Grade 2nd layer from Station 0+010 to 0+025 (full width) at Local Road # 14 Zone A. | 2026-09-26 |  | Accepted as Noted
39 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0815 | Inspection of Application of Prime Coat from Station0+010 to 0+025 RD-13 & 0+010 to 0+025 RD-14 Zone A | 2026-09-24 |  | Accepted as Noted
1 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0760 | Core Sampling Inspection for Bitumen Base Course (7 cm) from Station 0+100 to 0+275 at local Road 23 Zone B | 2026-09-21 |  | Revised & Resubmit
2 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0781 | Inspection for Placement, Location, level and Compaction for Backfilling Up to TOE Layer (Bottom of Sub Grade) from Station 0+775 to 0+975 at Collector Road - 02 Zone B. | 2026-09-26 |  | Revised & Resubmit
3 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0804 | Inspection for Placement, Location, level and Compaction for Backfilling Shoulder (A-2-4) from Stockpile # 10 at Station 0+012.5 to 0+650 (LHS & RHS) at Local Road # 09 Zone A. | 2026-09-24 |  | Revised & Resubmit
1 | KHJ1-02-007-MAH-TS9-1-ROD-FIR-0735 | Inspection for Mock-up of Rockfill Material layer beside Local Road 27 at st 0+3200 in Zone B | 2026-09-21 |  | Under Review
3. Concrete Box Culvet (CBC)
1 | KHJ1-02-007-MAH-TS9-1-CBC-FIR-0112 | Inspection of Application of Joint Sealant and Bituminous Coating of MH-32-A to Access Shaft MH-31-A & MH-31-A to Access Shaft MH-30-A at Local Road # 02 Zone A. | 2026-09-21 |  | Accepted
2 | KHJ1-02-007-MAH-TS9-1-CBC-FIR-0119 | Inspection of Reinforcement for Base and Apron Slab Cast-in-Situ Part for Up stream and Down Stream at Culvert # 05 Local Road-23 Zone B. | 2026-09-21 |  | Accepted
1 | KHJ1-02-007-MAH-TS9-1-CBC-FIR-0104 | Inspection of Reinforcement for Box Conduit from Square MH-32-A to Access Shaft MH-31-A at Local Road # 02 Zone A. | 2026-09-21 |  | Accepted as Noted
2 | KHJ1-02-007-MAH-TS9-1-CBC-FIR-0105 | Inspection of Placement of Box Conduit from Square MH-32-A to Access Shaft MH-31-A after Blinding Concrete at Local Road # 02 Zone A. | 2026-09-21 |  | Accepted as Noted
3 | KHJ1-02-007-MAH-TS9-1-CBC-FIR-0106 | Inspection of Reinforcement for Box Conduit from Access Shaft MH-30-A to Access Shaft MH-31-A at Local Road # 02 Zone A. | 2026-09-21 |  | Accepted as Noted
4 | KHJ1-02-007-MAH-TS9-1-CBC-FIR-0107 | Inspection of Placement of Box Conduit from Access Shaft MH-30-A to Access Shaft MH-31-A after Blinding Concrete at Local Road # 02 Zone A. | 2026-09-21 |  | Accepted as Noted
5 | KHJ1-02-007-MAH-TS9-1-CBC-FIR-0108 | Inspection of Reinforcement for Box Conduit from Access Shaft MH-28-A to Access Shaft MH-27-A at Local Road # 02 Zone A. | 2026-09-21 |  | Accepted as Noted
6 | KHJ1-02-007-MAH-TS9-1-CBC-FIR-0109 | Inspection of Placement of Box Conduit from Access Shaft MH-28-A to Access Shaft MH-27-A after Blinding Concrete at Local Road # 02 Zone A. | 2026-09-21 |  | Accepted as Noted
7 | KHJ1-02-007-MAH-TS9-1-CBC-FIR-0110 | Inspection of Reinforcement for Box Conduit from Access Shaft MH-23-A to Access Shaft MH-22-A at Local Road # 02 Zone A. | 2026-09-21 |  | Accepted as Noted
8 | KHJ1-02-007-MAH-TS9-1-CBC-FIR-0111 | Inspection of Placement of Box Conduit from Access Shaft MH-23-A to Access Shaft MH-22-A after Blinding Concrete at Local Road # 02 Zone A. | 2026-09-21 |  | Accepted as Noted
9 | KHJ1-02-007-MAH-TS9-1-CBC-FIR-0113 | Inspection of Reinforcement for Box Conduit from Access Shaft MH-22-A to Access Shaft MH-21-A at Local Road # 02 Zone A. | 2026-09-21 |  | Accepted as Noted
10 | KHJ1-02-007-MAH-TS9-1-CBC-FIR-0114 | Inspection of Placement of Box Conduit from Access Shaft MH-22A to Access Shaft MH-21-A after Blinding Concrete at Local Road # 02 Zone A. | 2026-09-21 |  | Accepted as Noted
11 | KHJ1-02-007-MAH-TS9-1-CBC-FIR-0117 | Excavation, Location, level and Compaction of Concrete Box Conduit Line A from Access Shaft MH-21(A) to Access Shaft MH-20-(A) at Zone A. | 2026-09-24 |  | Accepted as Noted
1 | KHJ1-02-007-MAH-TS9-1-CBC-FIR-0116 | Excavation, Location, level and Compaction of Concrete Box Conduit Line A from Access Shaft MH-20(A) to Access Shaft MH-19-(A) at Zone A. | 2026-09-24 |  | C-Revised & Resubmit
4.Mechanical(MEC)
No FIR Submitted in Mechanical Decipline.
5.Sewer (SEW)
1 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1395 | Inspection of Sand Backfill around & above of Pipe up to Bottom of Sub Grade layer of sewer line from MH-3.13 to MH-3.13.1 at Local Road # 26 Zone-B. | 2026-09-20 |  | Accepted as Noted
2 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1396 | Inspection of Sand Backfill around & above of Pipe up to Bottom of Sub Grade layer of sewer line from MH-3.13 to MH-3.12 at Local Road # 26 Zone-B. | 2026-09-20 |  | Accepted as Noted
3 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1397 | Inspection of Sand Backfill around & above of Pipe up to Bottom of Sub Grade layer of sewer line from MH-3.13.2 to MH-3.13.2.1 at Local Road # 26 Zone-B. | 2026-09-20 |  | Accepted as Noted
4 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1399 | Inspection of Sand Backfill around & above of Pipe up to Bottom of Sub Grade layer of sewer line from MH-3.13.1 to MH-3.13.2 at Local Road # 26 Zone-B. | 2026-09-20 |  | Accepted as Noted
5 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1400 | Inspection of Sand Backfill around & above of Pipe up to Bottom of Sub Grade layer of sewer line from MH-3.11 to MH-3.10 at Arterial Road # 01 Zone-B. | 2026-09-20 |  | Accepted as Noted
6 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1401 | Inspection of Sand Backfill around & above of Pipe up to Bottom of Sub Grade layer of sewer line from MH-3.7 to MH-3.8 at Arterial Road # 01 Zone-B. | 2026-09-20 |  | Accepted as Noted
7 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1576 | Leak Test of GRP Pipe (Dia 200mm) of Sewer Line From Manhole MH-3.13.6 to MH-3.13.7 at local Road # 26 in Zone B | 2026-09-20 |  | Accepted as Noted
8 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1577 | Placement and Installation of Sewer Manhole Base MH-3.28.1.1 at local Road # 23 in Zone B | 2026-09-20 |  | Accepted as Noted
9 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1578 | Placement and Installation of Sewer Manhole Base MH-3.13.5 at local Road # 26 in Zone B | 2026-09-20 |  | Accepted as Noted
10 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1579 | Leak Test of GRP Pipe (Dia 150mm) of Sewer Line 2.23 From Manhole MH-2.23.4 to MH- 2.23.3 at local Road # 10 in Zone A | 2026-09-20 |  | Accepted as Noted
11 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1580 | Leak Test of GRP Pipe (Dia 150mm) of Sewer Line 2.23 From Manhole MH-2.23.1 to MH- 2.23 at local Road # 10 in Zone A | 2026-09-20 |  | Accepted as Noted
12 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1581 | Leak Test GRP pipe (Dia 150mm) Sewer line 2.21.6 from MH-2.21.6.4 to MH-2.21.6.3 at Local road # 12 Zone A | 2026-09-20 |  | Accepted as Noted
13 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1582 | Leak Test GRP pipe (Dia 150mm) Sewer line 2.23 from MH-2.23.1.1 to MH-2.23.1 at local road # 10 Zone A. | 2026-09-20 |  | Accepted as Noted
14 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1583 | Leak Test GRP pipe (Dia 150mm) Sewer line 2.23 from MH-2.23.2.1 to MH-2.23.2 at local road # 10 Zone A. | 2026-09-20 |  | Accepted as Noted
15 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1584 | Leak Test GRP pipe (Dia 150mm) Sewer line 2.216.2 from MH-2.21.6.2.1 to MH-2.21.6.2 at Local road # 12 Zone A | 2026-09-20 |  | Accepted as Noted
16 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1585 | Leak Test of GRP Pipe (Dia 200mm) of Sewer Line From Manhole MH-3.13.5 to MH-3.13.6 at local Road # 26 in Zone B | 2026-09-20 |  | Accepted as Noted
17 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1586 | Excavation ,Sand bedding and Installation of GRP pipe (Dia 150mm) Sewer Line 2.6.1A from MH-2.6.1A TO MH-2.6 at Road # 3 Zone A | 2026-09-21 |  | Accepted as Noted
18 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1587 | Inspection of Sand Backfill around & above of Pipe up to Bottom of Sub Grade layer of sewer line from MH-3.13.6 to MH-3.13.7 at Local Road # 26 Zone-B. | 2026-09-22 |  | Accepted as Noted
19 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1588 | Inspection of Sand Backfill around & above of Pipe up to Bottom of Sub Grade layer of sewer line from MH-3.13.8 to MH-3.13.7 at Local Road # 26 Zone-B. | 2026-09-22 |  | Accepted as Noted
20 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1589 | Inspection of Sand Backfill around & above of Pipe up to Bottom of Sub Grade layer of sewer line from MH-3.13.6 to MH-3.13.5 at Local Road # 26 Zone-B. | 2026-09-22 |  | Accepted as Noted
21 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1590 | Inspection of Sand Backfill around & above of Pipe up to Bottom of Sub Grade layer of sewer line from MH-3.13.6 to MH-3.13.6.1 at Local Road # 26 Zone-B. | 2026-09-22 |  | Accepted as Noted
22 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1591 | Leak Test of GRP Pipe (Dia 500mm) of Sewer Line from Manhole MH-3.22 to MH-3.23 at local Road # 27 in Zone B | 2026-09-21 |  | Accepted as Noted
23 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1593 | Excavation,Sand bedding and Installation of GRP pipe (Dia 150mm) Sewer line 2.9 from MH-2.9.1 to MH-2.9 at local road # 03 Zone A. | 2026-09-24 |  | Accepted as Noted
24 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1594 | Sand bedding and Installation of GRP pipe (Dia 150mm) Sewer line 1 from MH-1.24 to MH-1.23 at local road # 03 in Zone A. | 2026-09-24 |  | Accepted as Noted
25 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1595 | Sand bedding and Installation of GRP pipe (Dia 150mm) sewer line 1.10 from MH-1.10.13 to MH-1.10.12 at local road # 03 Zone-A. | 2026-09-24 |  | Accepted as Noted
26 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1596 | Excavation,Sand bedding and Installation of GRP pipe (Dia 150mm) Sewer line 2.8.1A from MH-2.8.1A to MH-2.8 at local road # 03 Zone-A. | 2026-09-24 |  | Accepted as Noted
27 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1597 | Excavation,Sand bedding and Installation of GRP pipe (Dia 150mm) Sewer line 2.10 from MH-2.10.1 to MH-2.10 at local road # 03 Zone-A. | 2026-09-24 |  | Accepted as Noted
28 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1599 | Inspection of Sand Backfill around & above of Pipe up to Bottom of Sub Grade layer of sewer line from MH-3.4 to MH-3.5 at Arterial Road # 01 Zone-B. | 2026-09-22 |  | Accepted as Noted
29 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1600 | Inspection of Sand Backfill around & above of Pipe up to Bottom of Sub Grade layer of sewer line from MH-3.3 to MH-3.4 at Arterial Road # 01 Zone-B | 2026-09-22 |  | Accepted as Noted
30 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1601 | Excavation ,Sand bedding and Installation of GRP pipe (Dia 150mm) Sewer Line 2.31 from MH-2.30.1 TO MH-2.30 at Road # 3 Zone A | 2026-09-24 |  | Accepted as Noted
31 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1606 | Inspection for Sand Backfill from Around & Top of Pipe to Bottom of Sub Grade layer of sewer line 2.21.6 from MH-2.21.6.1 to MH-2.21.6 at Local Road # 12 Zone-A. | 2026-09-26 |  | Accepted as Noted
32 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1607 | Inspection for Sand Backfill from Around & Top of Pipe to Bottom of Sub Grade layer of sewer line 2.21.6 from MH-2.21.6.2 to MH-2.21.6.1 at Local Road # 12 Zone-A. | 2026-09-26 |  | Accepted as Noted
33 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1608 | Inspection for Sand Backfill from Around & Top of Pipe to Bottom of Sub Grade layer of sewer line 2.21.6 from MH-2.21.6.3 to MH-2.21.6.2 at Local Road # 12 Zone-A. | 2026-09-26 |  | Accepted as Noted
34 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1609 | Inspection for Sand Backfill from Around & Top of Pipe to Bottom of Sub Grade layer of sewer line 2.21.6 from MH-2.21.6.4 to MH-2.21.6.3 at Local Road # 12 Zone-A. | 2026-09-26 |  | Accepted as Noted
35 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1610 | Inspection for Sand Backfill from Around & Top of Pipe to Bottom of Sub Grade layer of sewer line 2.21.6.1 from MH-2.21.6.1.1 to MH-2.21.6.1 at Local Road # 12 Zone-A. | 2026-09-26 |  | Accepted as Noted
36 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1611 | Inspection for Sand Backfill from Around & Top of Pipe to Bottom of Sub Grade layer of sewer line 2.21.6.2 from MH-2.21.6.2.1 to MH-2.21.6.2 at Local Road # 12 Zone-A. | 2026-09-26 |  | Accepted as Noted
37 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1612 | Inspection for Sand Backfill from Around & Top of Pipe to Bottom of Sub Grade layer of sewer line 2.23 from MH-2.23.4 to MH-2.23.3 at Local Road # 10 Zone-A. | 2026-09-26 |  | Accepted as Noted
38 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1613 | Inspection for Sand Backfill from Around & Top of Pipe to Bottom of Sub Grade layer of sewer line 2.23 from MH-2.23.3 to MH-2.23.2 at Local Road # 10 Zone-A. | 2026-09-26 |  | Accepted as Noted
39 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1614 | Inspection for Sand Backfill from Around & Top of Pipe to Bottom of Sub Grade layer of sewer line 2.23 from MH-2.23.2 to MH-2.23.1 at Local Road # 10 Zone-A. | 2026-09-26 |  | Accepted as Noted
40 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1615 | Inspection for Sand Backfill from Around & Top of Pipe to Bottom of Sub Grade layer of sewer line 2.23 from MH-2.23.1 to MH-2.23 at Local Road # 10 Zone-A. | 2026-09-26 |  | Accepted as Noted
41 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1616 | Inspection for Sand Backfill from Around & Top of Pipe to Bottom of Sub Grade layer of sewer line 2.23.1 from MH-2.23.1.1 to MH-2.23.1 at Local Road # 10 Zone-A. | 2026-09-26 |  | Accepted as Noted
42 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1617 | Inspection for Sand Backfill from Around & Top of Pipe to Bottom of Sub Grade layer of sewer line 2.23.2 from MH-2.23.2.1 to MH-2.23.2 at Local Road # 10 Zone-A. | 2026-09-26 |  | Accepted as Noted
43 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1618 | Leak Test of GRP Pipe (Dia 150mm) of Sewer Line From Manhole MH-3.49 to MH-3.49.1 at local Road # 18 in Zone B | 2026-09-26 |  | Accepted as Noted
1 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1592 | Excavation,Sand bedding and Installation of GRP pipe (Dia 150mm) Sewer line 1.22.1 from MH-1.22 to MH-1.21 at local road # 03 Zone A. | 2026-09-26 |  | UR-Under Review
2 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1602 | Inspection of Sand Backfill around & above of Pipe up to Bottom of Sub Grade layer of sewer line from MH-3.18 to MH-3.17 at Local Road # 27 Zone-B. | 2026-09-26 |  | UR-Under Review
3 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1603 | Inspection of Sand Backfill around & above of Pipe up to Bottom of Sub Grade layer of sewer line from MH-3.18 to MH-3.18.1 at Local Road # 27 Zone-B. | 2026-09-26 |  | UR-Under Review
4 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1604 | Inspection of Sand Backfill around & above of Pipe up to Bottom of Sub Grade layer of sewer line from MH-3.19 to MH-3.19.1 at Local Road # 27 Zone-B. | 2026-09-26 |  | UR-Under Review
5 | KHJ1-02-007-MAH-TS9-1-SEW-FIR-1605 | Inspection of Sand Backfill around & above of Pipe up to Bottom of Sub Grade layer of sewer line from MH-3.21 to MH-3.22 at Local Road # 27 Zone-B. | 2026-09-26 |  | UR-Under Review
6.Storm (STR)
1 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2391 | Inspection for Formwork and Concrete Pouring (C-35) around Storm MH-32(A)_16_2-SCB-2, MH-32(A)_16_2-DCB-1, MH-32(A)_16_1-DCB-2, MH-32(A)_16_1-SCB-1, MH-32(A)_16-SCB-5, MH-32(A)_16-SCB-4, MH-32(A)_16-DCB-3,at Local Road # 12 Zone A. | 2026-09-20 |  | Accepted as Noted
2 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2419 | Sand Bedding and installation of UPVC Pipe (Dia 400mm) of Storm Line From Manhole MH-1(E)-DCB-2 to MH-1(E )-SCB-1 at Collector Road # 02 in Zone B | 2026-09-21 |  | Accepted as Noted
3 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2420 | Placement and Installation of Storm Catch Basin MH-2(K)-SCB-2 at local Road # 23 in Zone B | 2026-09-20 |  | Accepted as Noted
4 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2421 | Placement and Installation of Storm Catch Basin MH-1(K)-SCB-2 at local Road # 23 in Zone B | 2026-09-20 |  | Accepted as Noted
5 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2422 | Placement and Installation of Storm Catch Basin MH-2(L)-SCB-1 at Collector Road # 02 in Zone B | 2026-09-20 |  | Accepted as Noted
6 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2423 | Placement and Installation of Storm Manhole Base MH-3(L) at Collector Road # 02 in Zone B | 2026-09-20 |  | Accepted as Noted
7 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2424 | Placement and Installation of Storm Manhole Base MH-4(L) at Collector Road # 02 in Zone B | 2026-09-20 |  | Accepted as Noted
8 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2425 | Placement and Installation of Storm Manhole Base MH-5(G)_2 at Collector Road # 02 in Zone B | 2026-09-20 |  | Accepted as Noted
9 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2426 | Blinding Concrete Pouring of Storm Catch Basin MH-36(A)_8-SCB-1 at Local Road # 07 Zone A. | 2026-09-21 |  | Accepted as Noted
10 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2427 | Blinding Concrete Pouring of Storm Catch Basin MH-36(A)_8-SCB-2 at Local Road # 07 Zone A. | 2026-09-21 |  | Accepted as Noted
11 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2428 | Blinding Concrete Pouring of Storm Catch Basin MH-36(A)_8-SCB-3 at Local Road # 07 Zone A. | 2026-09-21 |  | Accepted as Noted
12 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2429 | Inspection for Excavation, Location, level & Blinding Concrete Pouring of Storm Catch Basin MH-36(A)_8-SCB-4 at Local Road # 07 Zone A. | 2026-09-21 |  | Accepted as Noted
13 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2430 | Inspection for Excavation, Location, level & Blinding Concrete Pouring of Storm Catch Basin MH-36(A)_8-SCB-5 at Local Road # 07 Zone A. | 2026-09-21 |  | Accepted as Noted
14 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2431 | Inspection for Excavation, Location, level & Blinding Concrete Pouring of Storm Catch Basin MH-36(A)_8_1-SCB-1 at Local Road # 07 Zone A. | 2026-09-21 |  | Accepted as Noted
15 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2432 | Inspection for Excavation, Location, level & Blinding Concrete Pouring of Storm Catch Basin MH-36(A)_8_1-SCB-2 at Local Road # 07 Zone A. | 2026-09-21 |  | Accepted as Noted
16 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2433 | Inspection for Excavation, Location, level & Blinding Concrete Pouring of Storm Catch Basin MH-36(A)_8_1-SCB-3 at Local Road # 07 Zone A. | 2026-09-21 |  | Accepted as Noted
17 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2434 | Inspection for Excavation, Location, level & Blinding Concrete Pouring of Storm Catch Basin MH-36(A)_8_2-SCB-1 at Local Road # 07 Zone A. | 2026-09-21 |  | Accepted as Noted
18 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2435 | Inspection for Excavation, Location, level & Blinding Concrete Pouring of Storm Catch Basin MH-36(A)_8_2-SCB-2 at Local Road # 07 Zone A. | 2026-09-21 |  | Accepted as Noted
19 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2436 | Inspection for Excavation, Location, level & Blinding Concrete Pouring of Storm Catch Basin MH-36(A)_8_2-SCB-3 at Local Road # 07 Zone A. | 2026-09-21 |  | Accepted as Noted
20 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2437 | Inspection for Excavation, Location, level & Blinding Concrete Pouring of Storm Catch Basin MH-36(A)_8_3-SCB-1 at Local Road # 07 Zone A. | 2026-09-21 |  | Accepted as Noted
21 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2438 | IInspection for Excavation, Location, level & Blinding Concrete Pouring of Storm Catch Basin MH-36(A)_8_3-SCB-2 at Local Road # 07 Zone A. | 2026-09-21 |  | Accepted as Noted
22 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2439 | Inspection for Excavation, Location, level & Blinding Concrete Pouring of Storm Catch Basin MH-36(A)_8_3-SCB-3 at Local Road # 07 Zone A. | 2026-09-21 |  | Accepted as Noted
23 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2440 | IInspection for Excavation, Location, level & Blinding Concrete Pouring of Storm Catch Basin MH-36(A)_8_4-SCB-1 at Local Road # 07 Zone A. | 2026-09-21 |  | Accepted as Noted
24 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2441 | Inspection for Excavation, Location, level & Blinding Concrete Pouring of Storm Catch Basin MH-36(A)_8_4-SCB-2 at Local Road # 07 Zone A. | 2026-09-21 |  | Accepted as Noted
25 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2442 | Inspection for Excavation, Location, level & Blinding Concrete Pouring of Storm Catch Basin MH-36(A)_8_4-SCB-3 at Local Road # 07 Zone A. | 2026-09-21 |  | Accepted as Noted
26 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2443 | Inspection for Excavation, Location, level & Blinding Concrete Pouring of Storm Catch Basin MH-36(A)_8_5-SCB-1 at Local Road # 07 Zone A. | 2026-09-21 |  | Accepted as Noted
27 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2448 | Inspection for Formwork and Concrete Pouring (C-35) around Storm MH-32(A)_16, MH-32(A)_16_1 & MH-32(A)_16_2 at Local Road # 04 Zone A. | 2026-09-21 |  | Accepted as Noted
28 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2449 | Excavation,sand bedding and Installation of UPVC pipe (300mm) Secondary storm line MH-36A)_8_1-SCB-1 TO MH-36(A)_8_1 at Local Road # 7 Zone A | 2026-09-20 |  | Accepted as Noted
29 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2450 | Excavation,sand bedding and Installation of UPVC pipe (300mm) Secondary storm line MH-36A)_8_2-SCB-1 TO MH-36(A)_8_2 at Local Road # 7 Zone A | 2026-09-20 |  | Accepted as Noted
30 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2451 | Excavation,sand bedding and Installation of UPVC pipe (300mm) Secondary storm line MH-36A)_8_1-SCB-2 TO MH-36(A)_8_1-SCB-1 at Local Road # 7 Zone A | 2026-09-20 |  | Accepted as Noted
31 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2452 | Excavation,sand bedding and Installation of UPVC pipe (300mm) Secondary storm line MH-36A)_8_1-SCB-3 TO MH-36(A)_8_1-SCB-2 at Local Road # 7 Zone A | 2026-09-20 |  | Accepted as Noted
32 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2453 | Excavation,sand bedding and Installation of UPVC pipe (300mm) Secondary storm line MH-36A)_8_2-SCB-2 TO MH-36(A)_8_2-SCB-1 at Local Road # 7 Zone A | 2026-09-20 |  | Accepted as Noted
33 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2454 | Excavation,sand bedding and Installation of UPVC pipe (300mm) Secondary storm line MH-36A)_8_2-SCB-3 TO MH-36(A)_8_2-SCB-2 at Local Road # 7 Zone A | 2026-09-20 |  | Accepted as Noted
34 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2455 | Leak Test GRP pipe (Dia 600mm) Storm Line A-32 from MH-32(A)_19 to MH-32(A)_18 at Local road # 1 Zone A | 2026-09-20 |  | Accepted as Noted
35 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2456 | Inspection for Excavation and Blinding Concrete of Strom Catch basin MH-1(L)-SCB-1 at Collector Road # 02 Zone B. | 2026-09-21 |  | Accepted as Noted
36 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2457 | Inspection for Excavation and Blinding Concrete of Strom Catch basin MH-2(K)-SCB-3 at Local Road # 23 Zone B. | 2026-09-21 |  | Accepted as Noted
37 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2458 | Inspection of Sand Backfill around & above of Pipe to Bottom of Sub Grade layer and Laying of Warning Tape of Strom Catch Basin line from MH-1(C)-SCB-2 to MH-1(C)-SCB-1 at Collector Road # 02 Zone B. | 2026-09-21 |  | Accepted as Noted
38 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2459 | Inspection of Sand Backfill around & above of Pipe to Bottom of Sub Grade layer and Laying of Warning Tape of Strom Catch Basin line from MH-2(C)-SCB-2 to MH-2(C)-SCB-1 at Collector Road # 02 Zone B. | 2026-09-21 |  | Accepted as Noted
39 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2460 | Inspection of Sand Backfill around & above of Pipe to Bottom of Sub Grade layer and Laying of Warning Tape of Strom Catch Basin line from MH-1(G)-SCB-2 to MH-1(G)-SCB-1 at Collector Road # 02 Zone B. | 2026-09-21 |  | Accepted as Noted
40 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2461 | Placement and Installation of Storm Manhole Base MH-1(L) at local Collector Road # 02 in Zone B | 2026-09-20 |  | Accepted as Noted
41 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2462 | Placement and Installation of Storm Manhole Base MH-5(L) at local Collector Road # 02 in Zone B | 2026-09-20 |  | Accepted as Noted
42 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2463 | Placement and Installation of Storm Manhole Base MH-5(M)_3 at local Road # 26 in Zone B | 2026-09-20 |  | Accepted as Noted
43 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2464 | Placement and Installation of Storm Manhole Base MH-5(M)_2 at local Road # 26 in Zone B | 2026-09-20 |  | Accepted as Noted
44 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2465 | Placement and Installation of Storm Catch Basin MH-1(L)-SCB-1 at Collector Road # 02 in Zone B | 2026-09-20 |  | Accepted as Noted
45 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2466 | Placement and Installation of Storm Catch Basin MH-2(K)-SCB-3 at Local Road # 23 in Zone B | 2026-09-20 |  | Accepted as Noted
46 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2467 | Exacavtion ,sand bedding and Installation of GRP pipe (Dia 400mm) Storm Line A-57 from MH--57(A)_1 TO MH-57(A) at Road # 3 Zone A | 2026-09-21 |  | Accepted as Noted
47 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2470 | Inspection for Excavation and Blinding Concrete of Strom MH-8(O)_1 at Local Road # 27 Zone B. | 2026-09-22 |  | Accepted as Noted
48 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2471 | Inspection for Excavation and Blinding Concrete of Strom MH-6(O) at Local Road # 26 Zone B. | 2026-09-21 |  | Accepted as Noted
49 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2472 | Inspection for Excavation and Blinding Concrete of Strom MH-2(L) at Collector Road # 02 Zone B. | 2026-09-21 |  | Accepted as Noted
50 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2473 | Excavation, Sand Bedding and Installation of UPVC Pipe (Dia 300mm) of Storm Line from Manhole MH-3(G)-SCB-1 to MH-3(G)-SCB-2 at Collector Road # 02 in Zone B | 2026-09-22 |  | Accepted as Noted
51 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2474 | Placement and Installation of Manhole Base MH-6(O) at local Road # 26 in Zone B | 2026-09-21 |  | Accepted as Noted
52 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2475 | Placement and Installation of Manhole Base MH-8(O)_1 at local Road # 26 in Zone B | 2026-09-21 |  | Accepted as Noted
53 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2476 | Placement and Installation of Manhole Base MH-2(L) at Collector Road # 02 in Zone B | 2026-09-21 |  | Accepted as Noted
54 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2478 | Placement and Installation of Storm line Catch Basin MH-5(M)_2-SCB-1 at Local Road # 02 in Zone B | 2026-09-21 |  | Accepted as Noted
55 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2479 | Placement and Installation of Storm line Catch Basin MH-5(M)_2-SCB-2 at Local Road # 02 in Zone B | 2026-09-21 |  | Accepted as Noted
56 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2480 | Placement and Installation of Storm line Catch Basin MH-5(M)_3-SCB-1 at Local Road # 26 in Zone B | 2026-09-21 |  | Accepted as Noted
57 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2481 | Placement and Installation of Storm line Catch Basin MH-5(M)_3-SCB-2 at Local Road # 26 in Zone B | 2026-09-21 |  | Accepted as Noted
58 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2483 | Sand bedding and Installation of GRP pipe (Dia 400mm) Storm line A-36-6 from MH- 36(A)_6_1 to MH-36(A)_6 at local road # 08 Zone A. | 2026-09-24 |  | Accepted as Noted
59 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2484 | Excavation, sand bedding and Installation of UPVC pipe (300mm) Secondary storm line MH-32(A)_16_5_2-SCB-2 TO MH-32(A)_16_5_2-SCB-1 at Local Road # 12 Zone A | 2026-09-24 |  | Accepted as Noted
60 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2485 | Excavation, sand bedding and Installation of UPVC pipe (300mm) Secondary storm line MH-32(A)_16_5_2-SCB-3 TO MH-32(A)_16_5_2-SCB-2 at Local Road # 12 Zone A | 2026-09-24 |  | Accepted as Noted
61 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2486 | Excavation, sand bedding and Installation of UPVC pipe (300mm) Secondary storm line MH-32(A)_16_5_2-SCB-1 TO MH-32(A)_16_5_2 at Local Road # 12 Zone A | 2026-09-24 |  | Accepted as Noted
62 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2487 | Excavation, Sand Bedding and Installation of UPVC Pipe (Dia 400mm) of Storm Line from MH-32(A)_18_2 to MH-32(A)_18_1 at Local Road # 10 in Zone A | 2026-09-24 |  | Accepted as Noted
63 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2488 | Excavation, Sand Bedding and Installation of UPVC Pipe (Dia 400mm) of Storm Line from MH-32(A)_18_1 to MH-32(A)_18 at Local Road # 10 in Zone A | 2026-09-24 |  | Accepted as Noted
64 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2489 | Excavation, sand bedding and Installation of UPVC pipe (300mm) Secondary storm line MH-32(A)_16_5_1-SCB-1 TO MH-32(A)_16_5_1 at Local Road # 12 Zone A | 2026-09-24 |  | Accepted as Noted
65 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2490 | Sand bedding and Installation of GRP pipe (Dia 400mm) Storm Line A-32-16 from MH--32(A)_16_4 TO MH-32(A)_16_3 at Road # 04 Zone A | 2026-09-24 |  | Accepted as Noted
66 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2491 | Sand bedding and Installation of GRP pipe (Dia 400mm) Storm Line A-32-16 from MH--32(A)_16_5 TO MH-32(A)_16_4 at Road # 04 Zone A | 2026-09-24 |  | Accepted as Noted
67 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2496 | Excavation, Sand Bedding and Installation of GRP Pipe (Dia 400mm) of storm Line from Manhole MH-3(G) to MH-4(G) at Collector Road # 02 in Zone B. | 2026-09-24 |  | Accepted as Noted
68 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2497 | Excavation, Sand Bedding and Installation of UPVC Pipe (Dia 300mm) of Storm Line From Manhole MH-2(L)-SCB-1 to MH-2(L)-SCB-2 at Collector Road # 02 in Zone B | 2026-09-24 |  | Accepted as Noted
69 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2498 | Excavation, sand bedding and Installation of UPVC pipe (Dia 300mm) Secondary storm From MH-36(A)_8_3-SCB-1 to MH-36(A)_8_3 atRoad 07. Zone A | 2026-09-26 |  | Accepted as Noted
70 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2499 | Excavation, sand bedding and Installation of UPVC pipe (Dia 300mm) Secondary storm .From MH-36(A)_8_3.SCB-2 to Mh-36(A)_8_3-SCB-1 at Road # 7 Zone A | 2026-09-26 |  | Accepted as Noted
71 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2500 | Excavation, sand bedding and laying UPVC pipe (Dia 300mm) Secondary storm From MH-36(A)_8_3-SCB-3 to MH-36(A)_8_3-SCB-2 at Road # 7 Zone A | 2026-09-26 |  | Accepted as Noted
72 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2501 | Excavation, Sand Bedding and Installation of UPVC Pipe (Dia 300mm) of Storm Line from Manhole MH-3(L)-SCB-1 to MH-3(L)-SCB-2 at Collector road # 02 in Zone B | 2026-09-26 |  | Accepted as Noted
73 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2502 | Excavation, Sand Bedding and Installation of UPVC Pipe (Dia 300mm) of Storm Line from Manhole MH-1(L)-SCB-1 to MH-1(L)-SCB-2 at Collector Road # 02 in Zone B | 2026-09-26 |  | Accepted as Noted
74 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2503 | Leak Test of GRP Pipe (Dia 400mm) of Storm Line From Manhole MH-2(G) to MH-3(G) at Collector road # 02 in Zone B | 2026-09-26 |  | Accepted as Noted
1 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2209 | Sand Bedding and Installation of GRP Pipe (Dia 400mm) of Storm Line from Manhole MH-1(E)-SCB-1 to MH-1(E)-DCB-2 at Collector Road # 02 in Zone B | 2026-09-24 |  | Revised & Resubmit
2 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2482 | Sand bedding and Installation of GRP pipe (Dia 400mm) Storm line A-36-8 from MH- 36(A)_8_1 to MH-36(A)_8 at local road # 07 Zone A. | 2026-09-22 |  | Revised & Resubmit
1 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2016 | Excavation , Sand bedding and Installation of UPVC pipe (Dia 300mm) Secondary Storm Line MH-58(A)_1-SCB-1 to MH-58(A)_1 at Collector Road # 01 Zone A. | 2026-09-24 | 2 | UR-Under Review
2 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2186 | Inspection of Sand Backfill around & above of Pipe to Bottom of Sub Grade layer and Laying of Warning Tape of Strom line from MH-3(M) to MH-4(M) at Local Road # 25 Zone B. | 2026-09-26 | 1 | UR-Under Review
3 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2187 | Inspection of Sand Backfill around & above of Pipe to Bottom of Sub Grade layer and Laying of Warning Tape of Strom line from MH-4(M) to MH-5(M) at Local Road # 25 Zone B. | 2026-09-26 | 1 | UR-Under Review
4 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2188 | Inspection of Sand Backfill around & above of Pipe to Bottom of Sub Grade layer and Laying of Warning Tape of Strom Catch Basin line from MH-5(M) to MH-5(M)-SCB-3 at Local Road # 24 Zone B. | 2026-09-26 | 1 | UR-Under Review
5 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2189 | Inspection of Sand Backfill around & above of Pipe to Bottom of Sub Grade layer and Laying of Warning Tape of Strom Catch Basin line from MH-5(M) to MH-5(M)-SCB-1 at Local Road # 24 Zone B. | 2026-09-26 | 1 | UR-Under Review
6 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2190 | Inspection of Sand Backfill around & above of Pipe to Bottom of Sub Grade layer and Laying of Warning Tape of Strom Catch Basin line from MH-5(M)-SCB-1 to MH-5(M)-SCB-2 at Local Road # 25 Zone B. | 2026-09-26 | 1 | UR-Under Review
7 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2191 | Inspection of Sand Backfill around & above of Pipe to Bottom of Sub Grade layer and Laying of Warning Tape of Strom Catch Basin line from MH-5(M)-SCB-3 to MH-5(M)-SCB-4 at Local Road # 24 Zone B. | 2026-09-26 | 1 | UR-Under Review
8 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2468 | Plcaement and Installation of Catch Basin MH-32(A)_18_1-SCB-2,MH-32(A)_18_2-SCB-2,MH-32(A)_18-SCB-4,MH-32(A)_18-SCB-3 at Local road # 10 Zone A | 2026-09-20 | 1 | UR-Under Review
9 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2477 | Placement and Installation of Storm line Catch Basin MH-2(L)-SCB-2 at Collector Road # 02 in Zone B | 2026-09-21 | 1 | UR-Under Review
10 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2492 | Inspection of Sand Backfill around & above of Pipe to Bottom of Sub Grade layer and Laying of Warning Tape of Strom Catch Basin line from MH-5(G)_2-SCB-2 to MH-5(G)_2-SCB-1 at Collector Road # 02 Zone B | 2026-09-26 | 1 | UR-Under Review
11 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2493 | Inspection of Sand Backfill around & above of Pipe to Bottom of Sub Grade layer and Laying of Warning Tape of Strom line from MH-7(M)_1 to MH-7(M) at Local Road # 27 Zone B. | 2026-09-26 | 1 | UR-Under Review
12 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2494 | Inspection of Sand Backfill around & above of Pipe to Bottom of Sub Grade layer and Laying of Warning Tape of Strom Catch Basin line from MH-5(G)_1-SCB-3 to MH-5(G)_1-SCB-1 at Collector Road # 02 Zone B. | 2026-09-26 | 1 | UR-Under Review
13 | KHJ1-02-007-MAH-TS9-1-STR-FIR-2495 | Inspection of Sand Backfill around & above of Pipe to Bottom of Sub Grade layer and Laying of Warning Tape of Strom Catch Basin line from MH-5(G)-SCB-2 to MH-5(G)-DCB-1 at Collector Road # 02 Zone B. | 2026-09-26 | 1 | UR-Under Review
7.Electrical(ELE)
1 | KHJ1-02-007-MAH-TS9-1-ELE-FIR-0182 | Inspection for Excavation, Location, level, Installation & backfill of Street Lights Pole Foundations from (SLP-6/4/2/Y - 6/4/5/Y) RHS & (SPL-6/5/1/R - SPL-6/5/5/Y) LHS (09 No's) at Local Road # 15 Zone A | 2026-09-24 |  | Accepted
3 | KHJ1-02-007-MAH-TS9-1-ELE-FIR-0175 | Sand Backfill up to Bottom of Sub Grade and Laying of warning tape for Street Lighting Duct bank crossing at station (RD-14 STA. 0+205) at Local Road # 14 Zone A | 2026-09-16 |  | Accepted as Noted
4 | KHJ1-02-007-MAH-TS9-1-ELE-FIR-0176 | Sand Backfill up to Bottom of Sub Grade and Laying of warning tape for Street Lighting Duct bank crossing at station (RD-02 STA. 0+810) at Local Road # 02 Zone A | 2026-09-19 |  | Accepted as Noted
5 | KHJ1-02-007-MAH-TS9-1-ELE-FIR-0177 | Inspection for Excavation, Installation of Sleeve 2x110mm UPVC & Formwork and Concrete Pouring of Street Light Duct Bank at Station (RD-07 St. 0+025) Local Road # 07 Zone A. | 2026-09-20 |  | Accepted as Noted
6 | KHJ1-02-007-MAH-TS9-1-ELE-FIR-0178 | Inspection for Excavation, Installation of Sleeve 2x110mm UPVC & Formwork and Concrete Pouring of Street Light Duct Bank at Station (RD-03 St. 1+343) Local Road # 03 Zone A. | 2026-09-19 |  | Accepted as Noted
7 | KHJ1-02-007-MAH-TS9-1-ELE-FIR-0179 | Inspection for Excavation, Installation of Sleeve 2x110mm UPVC & Formwork and Concrete Pouring of Street Light Duct Bank at Station (RD-03 St. 1+803) Local Road # 03 Zone A. | 2026-09-19 |  | Accepted as Noted
8 | KHJ1-02-007-MAH-TS9-1-ELE-FIR-0180 | Inspection for Excavation, Installation of Sleeve 2x110mm UPVC & Formwork and Concrete Pouring of Street Light Duct Bank at Station (RD-03 St. 1+827) Local Road # 03 Zone A. | 2026-09-19 |  | Accepted as Noted
9 | KHJ1-02-007-MAH-TS9-1-ELE-FIR-0181 | Inspection for Excavation, Installation of Sleeve 2x110mm UPVC & Formwork and Concrete Pouring of Street Light Duct Bank at Station (RD-03 St. 2+438) Local Road # 03 Zone A. | 2026-09-19 |  | Accepted as Noted
10 | KHJ1-02-007-MAH-TS9-1-ELE-FIR-0184 | Inspection for Excavation, Installation of Sleeve 2x110mm UPVC & Formwork and Concrete Pouring of Street Light Duct Bank at Station (RD-07 St. 0+280) Local Road # 07 Zone A. | 2026-09-21 |  | Accepted as Noted
11 | KHJ1-02-007-MAH-TS9-1-ELE-FIR-0185 | Inspection for Excavation, Installation of Sleeve 2x110mm UPVC & Formwork and Concrete Pouring of Street Light Duct Bank at Station (RD-04 St. 0+020) Local Road # 04 Zone A. | 2026-09-22 |  | Accepted as Noted
12 | KHJ1-02-007-MAH-TS9-1-ELE-FIR-0186 | Excavation,Installation of Sleeve, Formwork and Concrete Pouring of Street Light Duct Bank Crossing at Station (CL-RD-02 St.2+500) Collector Road # 02 Zone B. | 2026-09-22 |  | Accepted as Noted
13 | KHJ1-02-007-MAH-TS9-1-ELE-FIR-0187 | Excavation,Installation of Sleeve, Formwork and Concrete Pouring of Street Light Duct Bank Crossing at Station (CL-RD-02 St.2+540) Collector Road # 02 Zone B. | 2026-09-22 |  | Accepted as Noted
14 | KHJ1-02-007-MAH-TS9-1-ELE-FIR-0188 | Sand Backfill up to Bottom of Sub Grade and Laying of warning tape for Street Lighting Duct bank crossing at station (RD-08 STA. 0+365) at Local Road # 08 Zone A | 2026-09-24 |  | Accepted as Noted
1 | KHJ1-02-007-MAH-TS9-1-ELE-FIR-0183 | Inspection for Excavation, Location, level, Installation & backfill of Street Lights (Mediun Pole) Foundations from (SLP-2/1/7/R - 2/1/10/R) (04 No's) at Collector Road # 01 Zone A | 2026-09-22 |  | C-Revised & Resubmit
1 | KHJ1-02-007-MAH-TS9-1-ELE-FIR-0189 | Excavation,Installation of Sleeve, Formwork and Concrete Pouring of Street Light Duct Bank Crossing at Station (CL-RD-02 St.0+040) Collector Road # 02 Zone B. | 2026-09-26 |  | UR-Under Review
2 | KHJ1-02-007-MAH-TS9-1-ELE-FIR-0190 | Excavation,Installation of Sleeve, Formwork and Concrete Pouring of Street Light Duct Bank Crossing at Station (CL-RD-02 St.0+050) Collector Road # 02 Zone B. | 2026-09-26 |  | UR-Under Review
3 | KHJ1-02-007-MAH-TS9-1-ELE-FIR-0191 | Excavation,Installation of Sleeve, Formwork and Concrete Pouring of Street Light Duct Bank Crossing (SL-DB-65) at Arterial Road # 01 Zone B. | 2026-09-26 |  | UR-Under Review
4 | KHJ1-02-007-MAH-TS9-1-ELE-FIR-0192 | Excavation,Installation of Sleeve, Formwork and Concrete Pouring of Street Light Duct Bank Crossing (SL-DB-66) at Arterial Road # 01 Zone B. | 2026-09-26 |  | UR-Under Review
8.TELECOM(TEL)
1 | KHJ1-02-007-MAH-TS9-1-TEL-FIR-0100 | Excavation ,sand bedding and installation of HDPE pipe (Dia 110mm) TSE network crossing TSE-LINE-05 BGV-116 road # 10 Zone A . | 2026-09-26 |  | Accepted as Noted
2 | KHJ1-02-007-MAH-TS9-1-TEL-FIR-0105 | Excavation,Installation of Sleeve,Formwork and Concrete Pouring of Irrigation Duct Bank Crossing at Station (St.1+189) Collector Road # 02 Zone B | 2026-09-20 |  | Accepted as Noted
3 | KHJ1-02-007-MAH-TS9-1-TEL-FIR-0107 | Pressure Test of HDPE Pipe (Dia 110mm) of TSE Irrigation Line from Station 0+450 to 0+775 at Collector Road # 02 in Zone B | 2026-09-20 |  | Accepted as Noted
4 | KHJ1-02-007-MAH-TS9-1-TEL-FIR-0108 | Pressure Test of HDPE Pipe (Dia 110mm) of TSE Irrigation Line from Station 0+775 to 0+900 at Collector Road # 02 in Zone B | 2026-09-21 |  | Accepted as Noted
5 | KHJ1-02-007-MAH-TS9-1-TEL-FIR-0109 | Excavation ,sand bedding and installation of HDPE pipe (Dia 110mm) TSE network crossing TSE-110-LINE-06 from STA 0+285 TO 0+312.5 at local road # 10 Zone A | 2026-09-21 |  | Accepted as Noted
6 | KHJ1-02-007-MAH-TS9-1-TEL-FIR-0110 | Excavation, Sand Bedding and Installation of HDPE Pipe (Dia 110mm) of Irrigation TSE -110 line 27 crossing BGV-22 station 0+205, Local Road # 23 in Zone B | 2026-09-21 |  | Accepted as Noted
7 | KHJ1-02-007-MAH-TS9-1-TEL-FIR-0111 | Pressure Test of HDPE Pipe (Dia 110mm) of Irrigation TSE Line 19 from Station 1+050 to 1+400 at Collector Road # 02 in Zone B | 2026-09-22 |  | Accepted as Noted
1 | KHJ1-02-007-MAH-TS9-1-TEL-FIR-0106 | Inspection of Sand Backfill around & above of Pipe 6x50mm HDPE Telecom Duct from (MH-2014 to MH-2012),(MH-2016 to MH-2014) along the Left Side of Road at Local Road # 20 Zone B. | 2026-09-20 |  | Revised & Resubmit
1 | KHJ1-02-007-MAH-TS9-1-TEL-FIR-0114 | Inspection for Excavation, Installation of 6x50mm HDPE Sleeve & Formwork and Concrete Pouring of Telecom Network Duct TE-DB 6X50 Crossing at Station (RD-03 STA. 0+080) Local Road # 03 Zone A. | 2026-09-26 |  | UR-Under Review
9.Irrigation (IRR)
1 | KHJ1-02-007-MAH-TS9-1-IRR-FIR-0265 | Excavation ,sand bedding and installation of HDPE pipe (Dia 110mm) TSE network crossing TSE-110-LINE-17 TO BGV-65 at road # 3 Zone A | 2026-09-20 |  | Accepted as Noted
2 | KHJ1-02-007-MAH-TS9-1-IRR-FIR-0267 | Excavation, Sand Bedding and Installation of HDPE Pipe (Dia 250mm) of Irrigation TSE-110 line-30 from Station 0+025 to 0+475 at local Road # 27 in Zone B | 2026-09-20 |  | Accepted as Noted
3 | KHJ1-02-007-MAH-TS9-1-IRR-FIR-0274 | Inspection for Excavation, Installation of Sleeve & Formwork and Concrete Pouring of Secondary Irrigation Duct-Bank Crossing at Station (0+179) Local Road # 07 Zone A. | 2026-09-20 |  | Accepted as Noted
4 | KHJ1-02-007-MAH-TS9-1-IRR-FIR-0275 | Excavation, sand bedding and installation of HDPE pipe (Dia 110mm) TSE-110-LINE-12 STA 0+670 TO 0+695 at road # 3 Zone A. | 2026-09-20 |  | Accepted as Noted
5 | KHJ1-02-007-MAH-TS9-1-IRR-FIR-0276 | Inspection of Sand Backfill around & above to Bottom of Sub Grade layer of HDPE Pipe (Dia 110mm) of Irrigation TSE Line-25 From Station 0+000 to 0+200 at local Road # 25 in Zone B. | 2026-09-21 |  | Accepted as Noted
6 | KHJ1-02-007-MAH-TS9-1-IRR-FIR-0277 | Sand Bedding and Installation of HDPE Pipe (Dia 110mm) of Irrigation TSE Line 27 from Station 0+125 to 0+225 at local Road # 23 in Zone B | 2026-09-21 |  | Accepted as Noted
7 | KHJ1-02-007-MAH-TS9-1-IRR-FIR-0278 | Excavation ,sand bedding and installation of HDPE pipe (Dia 110mm) TSE-110-LINE-02 TO BGV-88 (CROSSING ) at road # 3 Zone A | 2026-09-20 |  | Accepted as Noted
8 | KHJ1-02-007-MAH-TS9-1-IRR-FIR-0280 | Excavation,Installation of Sleeve,Formwork and Concrete Pouring of Irrigation Duct Bank Crossing at Station (St.0+970) Collector Road # 02 Zone B. | 2026-09-22 |  | Accepted as Noted
9 | KHJ1-02-007-MAH-TS9-1-IRR-FIR-0281 | Excavation, sand bedding and installation of HDPE pipe (Dia 110mm) TSE-110-LINE-09 0+620 TO 0+644 (CROSSING) at road # 3 Zone A. | 2026-09-21 |  | Accepted as Noted
10 | KHJ1-02-007-MAH-TS9-1-IRR-FIR-0287 | Excavation, Sand Bedding and Installation of HDPE Pipe (Dia 160mm) of Irrigation Line Crossing at BGV-B-45 (1+450) at local Road # 26 in Zone B | 2026-09-24 |  | Accepted as Noted
11 | KHJ1-02-007-MAH-TS9-1-IRR-FIR-0288 | Excavation, Sand Bedding and Installation of HDPE Pipe (Dia 160mm) of Irrigation TSE 110 Line 28 from station 0+100 at 0+207 at local Road # 24 in Zone B | 2026-09-24 |  | Accepted as Noted
12 | KHJ1-02-007-MAH-TS9-1-IRR-FIR-0289 | Excavation, Sand bedding and Installation of HDPE pipe (Dia 110mm) TSE crossing BGV-74 TSE-11 Sta: 0+445 at Road # 07 Zone A | 2026-09-26 |  | Accepted as Noted
13 | KHJ1-02-007-MAH-TS9-1-IRR-FIR-0290 | Inspection of Sand Backfill around & above of Potable Pipe to Bottom of Sub Grade & Laying of Warning Tape at HDPE pipe (Dia 110mm) TSE network crossing TSE-LINE-05 BGV-116 road # 10 Zone A | 2026-09-26 |  | Accepted as Noted
14 | KHJ1-02-007-MAH-TS9-1-IRR-FIR-0292 | Inspection of Sand Backfill around & above of Potable Pipe to Bottom of Sub Grade & Laying of Warning Tape at Secondary Irrigation Duct-Bank Crossing at Station (0+175) Local Road # 10 Zone A | 2026-09-26 |  | Accepted as Noted
1 | KHJ1-02-007-MAH-TS9-1-IRR-FIR-0269 | Excavation ,sand bedding and installation of HDPE pipe (Dia 110mm) TSE network crossing TSE-110-LINE-18 TO BGV-64 at road # 3 Zone A | 2026-09-20 |  | C-Revised & Resubmit
2 | KHJ1-02-007-MAH-TS9-1-IRR-FIR-0279 | Excavation ,sand bedding and installation of HDPE pipe (Dia 110mm) TSE-110-LINE-10 TO BGV-17 (CROSSING ) at road # 3 Zone A | 2026-09-20 |  | C-Revised & Resubmit
3 | KHJ1-02-007-MAH-TS9-1-IRR-FIR-0284 | Excavation ,sand bedding and installation of HDPE pipe (Dia 110mm) TSE-110-LINE-03 TO BGV-02 (CROSSING ) at road # 3 Zone A | 2026-09-24 |  | C-Revised & Resubmit
1 | KHJ1-02-007-MAH-TS9-1-IRR-FIR-0285 | Inspection of Sand Backfill around & above to Bottom of Sub Grade layer of HDPE Pipe (Dia 110mm) of TSE Irrigation line 22 from Station 0+050 to 0+450 at local road # 19 in Zone B | 2026-09-26 | 1 | UR-Under Review
2 | KHJ1-02-007-MAH-TS9-1-IRR-FIR-0286 | Inspection of Sand Backfill around & above to Bottom of Sub Grade layer of HDPE Pipe (Dia 110mm) of Irrigation TSE Line-21 From Station 0+100 to 0+225 at local Road # 18 in Zone B | 2026-09-26 | 1 | UR-Under Review
3 | KHJ1-02-007-MAH-TS9-1-IRR-FIR-0293 | Excavation, Sand Bedding and Installation of HDPE Pipe (Dia 160mm) of TSE Irrigation Crossing at BGV-B-46 station 1+555 at local road # 26 in Zone B | 2026-09-26 | 1 | UR-Under Review
4 | KHJ1-02-007-MAH-TS9-1-IRR-FIR-0294 | Excavation, Sand Bedding and Installation of HDPE Pipe (Dia 160mm) of TSE Irrigation Line 29 from station 0+250 to 0+550 at local road # 26 in Zone B | 2026-09-26 | 1 | UR-Under Review
10.Potable (POT)
1 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0272 | Inspection for Reinforcement of Base Slab of Potable Network Washout Chamber (B-2) at Collector Road # 02 Zone B. | 2026-09-21 |  | Accepted
1 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0256 | Excavation, Sand Bedding and Installation of HDPE Pipe (Dia 250mm) of potable Network Crossing Line 250-01 from Station 0+160 to 0+360 at local Road # 26 in Zone B | 2026-09-20 |  | Accepted as Noted
2 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0264 | Excavation, Sand Bedding and Installation of HDPE Pipe (Dia 160mm) of Potable Line Crossing at Station 0+575 (BGV-B-46) local Road 26 in Zone B | 2026-09-20 |  | Accepted as Noted
3 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0265 | Excavation, Sand Bedding and Installation of HDPE Pipe (Dia 160mm) of Potable Line Crossing at Station 1+340 (BGV-B-45) local Road 26 in Zone B | 2026-09-20 |  | Accepted as Noted
4 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0266 | Excavation, Sand Bedding and Installation of HDPE Pipe (Dia 250mm) of potable Network Crossing Line 250-01 from Station 0+360 to 0+525 at local Road # 26 in Zone B | 2026-09-20 |  | Accepted as Noted
5 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0267 | Inspection of Sand Backfill around & above of Pipe to Bottom of Sub Grade layer of HDPE Pipe (Dia 160mm) of Potable Line 200-1 at Station 0+225 (Fire Hydrant FH-B-4) at Collector Road # 02 in Zone B | 2026-09-21 |  | Accepted as Noted
6 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0268 | Inspection of Sand Backfill around & above of Pipe to Bottom of Sub Grade layer of HDPE Pipe (Dia 250mm) of Potable Line 250-02 From station 0+000 to 0+400 at Local Road # 27 in Zone B | 2026-09-21 |  | Accepted as Noted
7 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0269 | Excavation, Sand Bedding and Installation of HDPE Pipe (Dia 160mm) of Potable Line 160-01 from Station 0+000 to 0+100 at local Road # 25 in Zone B | 2026-09-21 |  | Accepted as Noted
8 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0270 | Excavation, Sand Bedding and Installation of HDPE Pipe (Dia 160mm) of Potable Line Crossing at BGV-B-47 (1+325) at local Road # 26 in Zone B | 2026-09-21 |  | Accepted as Noted
9 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0273 | Inspection for Formwork and Concrete of Base Slab of Potable Network Washout Chamber (B-2) at Collector Road # 02 Zone B. | 2026-09-22 |  | Accepted as Noted
10 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0274 | Excavation, Sand Bedding and Installation of HDPE Pipe (Dia 250mm) of potable Network Line 250-01 from Station 0+525 to 0+650 at local Road # 26 in Zone B | 2026-09-21 |  | Accepted as Noted
11 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0275 | Excavation, Sand Bedding and Installation of HDPE Pipe (Dia 200mm) of potable Network Line 200-01 from Station 3+675 to 3+825 at Arterial Road # 01 in Zone B | 2026-09-21 |  | Accepted as Noted
12 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0276 | Inspection of Sand Backfill around & above of Pipe to Bottom of Sub Grade laye of HDPE Pipe (Dia 160mm) of Potable Line Crossing at Station 1+554 (Fire Hydrant FH-B-09) at Collector Road # 02 in Zone B | 2026-09-22 |  | Accepted as Noted
13 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0277 | Inspection of Sand Backfill around & above of Pipe to Bottom of Sub Grade laye of HDPE Pipe (Dia 160mm) of Potable Line Crossing at Station 1+831 (Fire Hydrant FH-B-10) at Collector Road # 02 in Zone B | 2026-09-22 |  | Accepted as Noted
14 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0278 | Excavation ,sand bedding and installation of HDPE pipe (Dia 315mm) Potable water network Crossing LINE -315-1 ST 0+100 TO 0+130 Road # 3 Zone A | 2026-09-21 |  | Accepted as Noted
15 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0279 | Excavation ,sand bedding and installation of HDPE pipe (Dia 160mm) Potable water network Crossing LINE -250-5 TO BGV-A-86 ST 0+564 Road # 3 Zone A | 2026-09-21 |  | Accepted as Noted
16 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0280 | Excavation ,sand bedding and installation of HDPE pipe (Dia 160mm) Potable water network Crossing LINE -250-2 TO BGV-A-82 ST 0+765 Road # 3 Zone A | 2026-09-21 |  | Accepted as Noted
17 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0281 | Excavation ,sand bedding and installation of HDPE pipe (Dia 160mm) Potable water network Crossing LINE -250-3 TO BGV-A-74 ST 1+560 Road # 3 Zone A | 2026-09-21 |  | Accepted as Noted
18 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0282 | Excavation ,sand bedding and installation of HDPE pipe (Dia 160mm) Potable water network Crossing LINE -250-3 TO BGV-A-75 ST 1+445 Road # 3 Zone A | 2026-09-21 |  | Accepted as Noted
19 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0284 | Inspection of Sand Backfill around & above of Pipe to Bottom of Sub Grade laye of HDPE Pipe (Dia 200mm) of Potable Line 200-1 From Station 3+300 to 3+675 at Arterial Road # 01 in Zone B | 2026-09-22 |  | Accepted as Noted
20 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0285 | Inspection of Sand Backfill around & above of Pipe to Bottom of Sub Grade laye of HDPE Pipe (Dia 160mm) of Potable Line 200-06 From Station 0+390 to 0+575 at Local Road # 21 in Zone B | 2026-09-22 |  | Accepted as Noted
21 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0286 | Inspection of Sand Backfill around & above of Pipe to Bottom of Sub Grade laye of HDPE Pipe (Dia 160mm) of Potable Line Crossing at Station 0+034 (Fire Hydrant FH-B-05) at Collector Road # 02 in Zone B | 2026-09-22 |  | Accepted as Noted
22 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0287 | Excavation ,sand bedding and installation of HDPE pipe (Dia 250mm) Potable water network Crossing LINE -250-1 0+000 TO 0+025 Road # 3 Zone A | 2026-09-24 |  | Accepted as Noted
23 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0288 | Excavation ,sand bedding and installation of HDPE pipe (Dia 250mm) Potable water network Crossing LINE -250-4 TO BGV-A-83 Road # 3 Zone A | 2026-09-24 |  | Accepted as Noted
24 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0289 | Excavation, Sand Bedding and Installation of HDPE Pipe (Dia 250mm) of Potable Line 250-01 from station 0+650 to 0+700 at local road # 26 in Zone B | 2026-09-24 |  | Accepted as Noted
25 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0290 | Excavation, Sand Bedding and Installation of HDPE Pipe (Dia 250mm) of Potable Line 250-01 from station 1+325 to 1+475 at local road # 26 in Zone B | 2026-09-26 |  | Accepted as Noted
26 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0291 | Excavation, Sand Bedding and Installation of HDPE Pipe (Dia 250mm) of Potable Line 250-01 from station 0+700 to 0+875 at local road # 26 in Zone B | 2026-09-26 |  | Accepted as Noted
1 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0246 | Excavation ,sand bedding and installation of HDPE pipe (Dia 160mm) Potable water network LINE 250-3 TO BGV-A-70 road # 3 Zone A | 2026-09-20 |  | C-Revised & Resubmit
2 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0258 | Excavation ,sand bedding and installation of HDPE pipe (Dia 160mm) Potable water network LINE 250-3 TO BGV-A-76 road # 3 Zone A | 2026-09-20 |  | C-Revised & Resubmit
3 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0271 | Excavation ,sand bedding and installation of HDPE pipe (Dia 160mm) Potable water network Crossing LINE BGV-A-73 Road # 3 Zone A | 2026-09-20 |  | C-Revised & Resubmit
4 | KHJ1-02-007-MAH-TS9-1-POT-FIR-0283 | Excavation ,sand bedding and installation of HDPE pipe (Dia 160mm) Potable water network Crossing LINE -250-3 0+815 Road # 7 Zone A | 2026-09-22

## Procurement
حالة المشتريات الرئيسية - مشروع الخرج
اسم المشروع | Parent Project ID | القطاع | مواد التوريدات | المورد | رقم التواصل مع المورد | الموقف الحالي | تاريخ بدء التوريد المجدول | اجتماعات الموردين | خارجي/ داخلي | نسبة التوريد المحلي % | نسبة التوريد الخارجي % | اجمالي الكمية | الكمية التي تم توريدها | وحدة القياس | ملاحظات (حالة المادة - عوائق - تأخير - ظروف خارجية, التأخر بالدفع من المقاول أو المورد)
DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY | KHJ1-02-007 | مدن - الرياض | Curb stone | Sail Alreyadha Saudi Industrial Co (SIEFCO) | Mr. MUSTAFA KADRI | تحت التوريد | يونيو 2026 | تم الانتهاء | داخلي | 100% | 0% | 155879 | 36336 | LM | تم اعتماد العينة - التوريد جارى طبقا لاحتياجات الموقع | داخلي
DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY | KHJ1-02-007 | مدن - الرياض | Interlock | Sail Alreyadha Saudi Industrial Co (SIEFCO) | Mr. MUSTAFA KADRI | تحت التوريد | يونيو 2026 | تم الانتهاء | داخلي | 100% | 0% | 129381 | 0 | LM | لم يتم اعتماد العينة - التوريد متوقف لحين الاعتماد
DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY | KHJ1-02-007 | مدن - الرياض | Traffic signage | Agyad Sign | Mr. Amar Ashri | تحت التوريد | ابريل 2026 | تم الانتهاء | داخلي | 100% | 0% | 981 | 981 | NOS | تم الانتهاء | لم يقدم للإعتماد
DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY | KHJ1-02-007 | مدن - الرياض | Manhole ( Storm) | AL-BILAD CONCRETE PIPES CO. | Mr. Mahmoud Attia | تحت التوريد | ابريل 2026 | تم الانتهاء | داخلي | 100% | 0% | 300 | 256 | NOS | تم اعتماد العينة - الانتهاء فى التوريد اخر 20 oct | جاري الإعتماد
DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY | KHJ1-02-007 | مدن - الرياض | Manhole ( Sewage) | T. Nagadi Preformed Concrete Factory | Mr. Ahmed Eldeeb | تحت التوريد | ابريل 2026 | تم الانتهاء | داخلي | 100% | 0% | 346 | 340 | NOS | تم اعتماد العينة - الانتهاء من التوريد 20 oct | تم الإعتماد
DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY | KHJ1-02-007 | مدن - الرياض | DI Cover & FRAME (Sewage & Storm&ICT CATCH BASIN ) | UKC | Mr. Mohammad Hany | تحت التوريد | ابريل 2026 | تم الانتهاء | داخلي | 100% | 0% | 1768 | 1086 | NOS | تم اعتماد العينة - الانتهاء من التوريد 20 oct | تم اصدار امر الشراء ولم يتم الدفع
DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY | KHJ1-02-007 | مدن - الرياض | Concrete catch basin | Kaayan advanced construction | Mr. M salah | تحت التوريد | ابريل 2026 | تم الانتهاء | داخلي | 100% | 0% | 666 | 666 | NOS | تم الانتهاء | جاري التصنيع
DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY | KHJ1-02-007 | مدن - الرياض | Precast Concrete Box Culverts/Conduits including the wing walls | T. Nagadi Preformed Concrete Factory | Mr. Ahmed Eldeeb | تحت التوريد | مارس 2026 | تم الانتهاء | داخلي | 100% | 0% | 2914 | 2570 | LM | تم اعتماد العينة - الانتهاء فى التوريد اخر 20 Oct | جاري التوريد
DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY | KHJ1-02-007 | مدن - الرياض | Manhole (ICT) | AL-BILAD CONCRETE PIPES CO. | Mr. Mahmoud Attia | تحت التوريد | سبتمبر 2026 | تم الانتهاء | داخلي | 100% | 0% | 214 | 0 | NOS | تم اعتماد العينة - جارى انتاج المواد - الانتهاء من التوريد 20 Nov | تم التوريد
DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY | KHJ1-02-007 | مدن - الرياض | Low Voltage Cables, Copper & Aluminium, | Elsewedy | Mr. Abdullah | تحت التوريد | يونيو 2026 | تم الانتهاء | داخلي | 100% | 0% | 114893 | 97030 | LM | تم اعتماد العينة - جارى انتاج المواد - الانتهاء من التوريد 20 Nov
DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY | KHJ1-02-007 | مدن - الرياض | MV cable, waiting for SEC to wave off FAT test to start delivery |  | +966 53 484 9346 |  | يونيو 2026 | تم الانتهاء | داخلي | 100% | 0% | 72 | 56.7 | Km | تم اعتماد العينة - الانتهاء من التوريد اخر 20 Oct
DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY | KHJ1-02-007 | مدن - الرياض | Ring Main unit-RMU | Al Fanar | Mr. Fahmi Zaitoon | تم الانتهاء | تم الانتهاء | تم الانتهاء | داخلي | 100% | 0% | 5 | 5 | NOS | تم الانتهاء | LM
DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY | KHJ1-02-007 | مدن - الرياض | Unit Substation 13.8/0.4 kv , |  | +966 56 596 1202 | تم الانتهاء | تم الانتهاء | تم الانتهاء | داخلي | 100% | 0% | 5 | 5 | NOS | تم الانتهاء | m2
DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY | KHJ1-02-007 | مدن - الرياض | Street Lighting poles & Fixtures | Al-Babtain Power & Telecom | Mr. Reda Hegazy | تحت التوريد | يونيو 2026 | تم الانتهاء | داخلي | 100% | 0% | 981 | 863 | NOS | تم اعتماد العينة - الانتهاء من التوريد اخر 20 Oct | m3
DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY | KHJ1-02-007 | مدن - الرياض |  |  | +966 58 128 6668 | [6 empty] | 1152 | 970 | NOS |  | NOS
DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY | KHJ1-02-007 | مدن - الرياض | UPVC Pipes & Fittings | National Kham Plastic Factory Co. | Mr. M Rabie Elsaady | تم الانتهاء | تم الانتهاء | تم الانتهاء | داخلي | 100% | 0% | 1026 | 1026 | LM | تم الانتهاء
DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY | KHJ1-02-007 | مدن - الرياض | HDPE duct pipe | UNION PIPES INDUSTRY CO. LTD | Mr. Islam Ezzeldin | تم الانتهاء | تم الانتهاء | تم الانتهاء | داخلي | 100% | 0% | 291380 | 291380 | LM | تم الانتهاء | Km
DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY | KHJ1-02-007 | مدن - الرياض | HDPE Pipe & Fittings |  |  | تم الانتهاء | تم الانتهاء | تم الانتهاء | داخلي | 100% | 0% | 59088 | 59088 | LM | تم الانتهاء | Ton
DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY | KHJ1-02-007 | مدن - الرياض | potable Valve & accessories (Sluice) valves (Direct buried) | AVK (Gaweea Global Trading Est.) | Mr. Mohammad Sohail | تحت التوريد | يونيو 2026 | تم الانتهاء | داخلي | 100% | 0% | 2723 | 347 | EA | تم اعتماد العينة - الانتهاء من ى التوريد ا 20 Oct
DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY | KHJ1-02-007 | مدن - الرياض | Fire hydrant , Valve & Accessories |  | +966 54 320 2000 | تحت التوريد | يونيو 2026 | تم الانتهاء | داخلي | 100% | 0% | 310 | 217 | EA |  | set
DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY | KHJ1-02-007 | مدن - الرياض | GRP Pipes & Fittings | T. Nagadi Fiberglass Pipes Factory | Mr. Ahmed Eldeeb | تحت التوريد | فبراير 2026 | تم الانتهاء | داخلي | 100% | 0% | 49458 | 48676 | LM | تم اعتماد العينة - الانتهاء فى التوريد اخر 20 Oct
DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY | KHJ1-02-007 | مدن - الرياض | Secondary Irrigation | Gulf Bazar | "Mr. Youseff | تحت التوريد | يونيو 2026 | تم الانتهاء | داخلي | 100% | 0% | 1 | 0.3 | LOT | تم اعتماد العينة - جارى توريد المواد
DEVELOPMENT OF INFRASTRUCTURE NETWORKS, AL KHARJ INDUSTRIAL CITY | KHJ1-02-007 | مدن - الرياض | Plantataion & Shurbs |  | +966 54 337 2517" | تحت التوريد | اكتبر 2026 | تم الانتهاء | داخلي | 100% | 0% | 30556 | 0 | M2 | فى انتظار الاتفاق على الكمية النهائية

## Material Status
Procurement- Material Status | [20 empty] | Date | 2026-09-28
# | Material Description | Material Category | BOQ Number | Unit | Total Quantity | Long Lead Item | PR Status |  | PO Status |  | Delivery Time Frame |  |  | Delivery Status |  | MRIR Status |  |  | MIR Status |  |  | Comments
|  | Civil/Mech/Elec/Arch |  |  |  | Short/Long | 0/1 | Date | 0/1 | Date | Duration/Days | Start Date | End Date | Quantity | % | 0/1 | MRIR no. | Date | Yes / No | MIR no. | Date
1 | GRP Pipes | Mechanical | B3.33 14 13.01
1.1 | 150mm Diameter - SEWER | Mechanical |  | m | 4288 |  |  |  | 1 | 15/3/2026 | 80 | 15/3/2026 | 30/08/2026 | 4059.35 | 95% | yes | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0026& 48 | 2026-02-09 |  | KHJ1-02-007-MAH-TS9-1-STR-MIR-0048,KHJ1-02-007-MAH-TS9-1-STR-MIR-0047,KHJ1-02-007-MAH-TS9-1-MEC-MIR-0119
1.2 | 200mm Diameter - SEWER | Mechanical |  | m | 12884 |  |  |  | 1 | 15/3/2026 | 80 | 15/3/2026 | 30/08/2026 | 11985 | 93% | yes | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0006,KHJ1-02-007-МАН-TS9-1-MEC-MRIR-0068 | 2026-02-09 |  | KHJ1-02-007-MAH-TS9-1-STR-MIR-0047
1.3 | 250mm Diameter - SEWER | Mechanical |  | m | 2310 |  |  |  | 1 | 15/3/2026 | 80 | 15/3/2026 | 2026-01-08 | 2310 | 100% | yes | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0018,KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0037 | 2026-02-09 |  | KHJ1-02-007-MAH-TS9-1-MEC-MIR-0005
1.4 | 300mm Diameter - SEWER | Mechanical |  | m | 2700 |  |  |  | 1 | 15/3/2026 | 80 | 15/3/2026 | 2026-01-08 | 2700 | 100% | yes | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0001 | 2026-02-09 |  | KHJ1-02-007-MAH-TS9-1-MEC-MIR-0005
1.5 | 400mm Diameter -STORM & SEWER | Mechanical |  | m | 14097 |  |  |  | 1 | 15/3/2026 | 80 | 15/3/2026 | 30/08/2026 | 11696 | 83% | yes | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0068 | 2026-02-09 |  | KHJ1-02-007-MAH-TS9-1-STR-MIR-0047,KHJ1-02-007-MAH-TS9-1-STR-MIR-0103,KHJ1-02-007-MAH-TS9-1-MEC-MIR-0119
1.6 | 500mm Diameter -STORM & SEWER | Mechanical |  | m | 2389 |  |  |  | 1 | 15/3/2026 | 80 | 15/3/2026 | 2026-01-08 | 2388 | 100% | yes | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0015 & 48,KHJ1-02-007-MAH-TS9-1-STR-MIR-0047 | 2026-02-09 |  | KHJ1-02-007-MAH-TS9-1-MEC-MIR-0005,KHJ1-02-007-MAH-TS9-1-STR-MIR-0103,KHJ1-02-007-MAH-TS9-1-MEC-MIR-0119
1.7 | 600mm Diameter -STORM & SEWER | Mechanical |  | m | 4370 |  |  |  | 1 | 15/3/2026 | 80 | 15/3/2026 | 2026-01-08 | 4370 | 100% | yes | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0017,KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0019,KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0021 | 2026-02-09 |  | KHJ1-02-007-МАН-TS9-1-MEC-MRIR-0068,KHJ1-02-007-MAH-TS9-1-STR-MIR-0047
1.8 | 700mm Diameter -STORM | Mechanical |  | m | 1245 |  |  |  | 1 | 15/3/2026 | 80 | 15/3/2026 | 30/08/2026 | 1245 | 100% | yes | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0037,KHJ1-02-007-МАН-TS9-1-MEC-MRIR-0068 | 2026-02-09 |  | kHJ1-02-007-MAH-TS9-1-STR-MIR-0047,KHJ1-02-007-MAH-TS9-1-STR-MIR-0103
1.9 | 800mm Diameter -STORM | Mechanical |  | m | 1850 |  |  |  | 1 | 15/3/2026 | 80 | 15/3/2026 | 30/08/2026 | 1800 | 97% | yes | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0068 | 2026-02-09 |  | KHJ1-02-007-MAH-TS9-1-STR-MIR-0047,KHJ1-02-007-MAH-TS9-1-STR-MIR-0103
1.1 | 900mm Diameter -STORM | Mechanical |  | m | 870 |  |  |  | 1 | 15/3/2026 | 80 | 15/3/2026 | 30/08/2026 | 804 | 92% | yes | KHJ1-02-007-МАН-TS9-1-MEC-MRIR-0098 | 2026-02-09 |  | KHJ1-02-007-MAH-TS9-1-STR-MIR-0103
1.11 | 1000mm Diameter -STORM | Mechanical |  | m | 765 |  |  |  | 1 | 15/3/2026 | 80 | 15/3/2026 | 30/08/2026 | 720 | 94% | yes | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0001 | 2026-02-09
1.12 | 1200mm Diameter -STORM | Mechanical |  | m | 1690 |  |  |  | 1 | 15/3/2026 | 80 | 15/3/2026 | 2026-01-08 | 1690 | 100% | yes | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0001& 48,KHJ1-02-007-МАН-TS9-1-MEC-MRIR-0064 | 2026-02-09 |  | KHJ1-02-007-MAH-TS9-1-STR-MIR-0047,KHJ1-02-007-MAH-TS9-1-MEC-MIR-0119
2 | HDPE Pipes | Mechanical
2.1 | 32mm Diameter | Mechanical |  | m | 66692 |  |  |  | 1 | 2026-01-04 | 80 days | 18/3/2026 | 2026-01-08 | 66692 | 100% | YES | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0002 & 004 | 07 Feb & 14 FEB
2.2 | 50mm Diameter | Mechanical |  | m | 224688 |  |  |  | 1 | 2026-01-04 | 80 days | 18/3/2026 | 2026-01-08 | 224688 | 100% | YES | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0002 & 004 | 07 Feb & 14 FEB |  | KHJ1-02-007-МАН-TS9-1-TEL-MRIR-0082
2.3 | 75 mm Diameter | Mechanical |  | m |  |  |  |  | 1 | 2026-01-04 | 80 days | 18/3/2026 | 30/6/2026 | - | 0% | YES | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0002 & 004 | 07 Feb & 14 FEB
2.4 | 90mm Diameter | Mechanical |  | m | 900 |  |  |  | 1 | 2026-01-04 | 80 days | 18/3/2026 | 2026-01-08 | 900 | 100% | YES | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0002 & 004 | 07 Feb & 14 FEB |  | KHJ1-02-007-MAH-TS9-1-STR-MIR-0107
2.5 | 110mm Diameter | Mechanical |  | m | 27900 |  |  |  | 1 | 2026-01-04 | 80 days | 18/3/2026 | 2026-01-08 | 27900 | 100% | YES | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0002 & 004 | 07 Feb & 14 FEB |  | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0030
2.6 | 160mm Diameter | Mechanical |  | m | 9576 |  |  |  | 1 | 2026-01-04 | 80 days | 18/3/2026 | 30/6/2026 | 9576 | 100% | YES | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0002 & 004 | 07 Feb & 14 FEB |  | KHJ1-02-007-MAH-TS9-1-STR-MIR-0107,
2.7 | 200mm Diameter | Mechanical |  | m | 11496 |  |  |  | 1 | 2026-01-04 | 80 days | 18/3/2026 | 2026-01-08 | 11496 | 100% | YES | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0002 & 004 | 07 Feb & 14 FEB |  | KHJ1-02-007-MAH-TS9-1-STR-MIR-0107
2.8 | 250mm Diameter | Mechanical |  | m | 8772 |  |  |  | 1 | 2026-01-04 | 80 days | 18/3/2026 | 2026-01-08 | 8772 | 100% | YES | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0002 & 004 | 07 Feb & 14 FEB |  | KHJ1-02-007-MAH-TS9-1-CIV-MRIR-0030
2.9 | 315mm Diameter | Mechanical |  | m | 372 |  |  |  | 1 | 2026-01-04 | 80 days | 18/3/2026 | 2026-01-08 | 372 | 100% | YES | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0002 & 004 | 07 Feb & 14 FEB |  | KHJ1-02-007-MAH-TS9-1-CIV-MRIR-0030
2.1 | 355mm Diameter | Mechanical |  | m | 72 |  |  |  | 1 | 2026-01-04 | 80 days | 18/3/2026 | 2026-01-08 | 72 | 100% | YES | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0002 & 004 | 07 Feb & 14 FEB |  | KHJ1-02-007-MAH-TS9-1-CIV-MRIR-0030
3 | UPVC Pipes | Mechanical
| 110mm Diameter |  |  | m | 4800 |  |  |  | 1 | 2026-01-03 | 60 days | 15/3/2026 | 2026-01-08 | 4320 | 90% | yes
2.1 | 150mm Diameter |  |  | m | 9822 |  |  |  | 1 | 2026-01-03 | 60 days | 15/3/2026 | 2026-01-08 | 9822 | 100% | yes | KHJ1-02-007-МАН-TS9-1-MEC-MRIR-0063 | 2026-02-09 |  | KHJ1-02-007-MAH-TS9-1-STR-MIR-0107
2.2 | 200mm Diameter |  |  | m | 1062 |  |  |  | 1 | 2026-01-03 | 60 days | 15/3/2026 | 2026-01-08 | 1062 | 100% | yes | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0003,KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0025 | 2026-02-09 |  | KHJ1-02-007-MAH-TS9-1-STR-MIR-0102,KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0025
2.4 | 300mm Diameter |  |  | m | 13375 |  |  |  | 1 | 2026-01-03 | 60 days | 15/3/2026 | 30/6/2026 | 13375 | 100% | yes | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0003,KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0007,KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0033 | 2026-02-09 |  | KHJ1-02-007-MAH-TS9-1-STR-MIR-0102,KHJ1-02-007-MAH-TS9-1-CIV-MIR-0098
2.5 | 400mm Diameter |  |  | m | 915 |  |  |  | 1 | 2026-01-03 | 60 days | 15/3/2026 | 30/6/2026 | 915 | 100% | yes | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0011 | 2026-02-09 |  | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0011
4 | Back filling |  |  | m3 | 865580 |  |  |  | 1 | INREVIEW | 90 days | 2026-04-01 | 2026-07-31 | 470000 | 54% |  | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0046 & 47, 50 , 51 & 52 , 56
5 | Subgrade |  | B5.33 31 00.01 | m3 | 150796 |  |  |  | 0 |  | 90 | 20/4/2026 | 20/7/2026 | 106000 | 70% | 1 | KHJ1-02-007-MAH-TS9-1-ROD-MRIR-0038 KHJ1-02-007-MAH-TS9-1-ROD-MRIR-0049 KHJ1-02-007-MAH-TS9-1-ROD-MRIR-0053 |  |  | KHJ1-02-007-MAH-TS9-1-CIV-MIR-0001 KHJ1-02-007-MAH-TS9-1-CIV-MIR-0002
6 | Aggregate base course |  |  | m3 | 103310 |  |  |  | 1 | INREVIEW | 90 | 2026-01-06 | 2026-08-31 | 47500 | 46%
7 | Waterproofing membrane |  |  | lm | HBS |  |  |  | 1 | 15/3/2026 |  | as per site request to start
8 | Curbstone |  |  | EA | 155879 |  |  |  | 1 | 15/3/2026 | 90-100 | as per site request to start |  | 36336 | 23.31%
9 | Block work Accessories |  |  | m3 | HBS |  |  |  | 1 | confirmed | 10 days | as per site request to start | as per site request to start
10 | Sand Cement Plaster for Internal Walls |  |  | m3 | HBS |  |  |  | 1 | confirmed | 10 days | as per site request to start | as per site request to start
11 | Paint INTERNAL & External Areas |  |  | m2 | HBS |  |  |  | 1 | 2026-01-03 | 10 days | as per site request to start | as per site request to start
12 | Concrete Mix for PC works |  |  | m3 | 2600 |  |  |  | 1 | confirmed |  | as per site request to start | as per site request to start | 1500 | 57.69% |  | KHJ1-02-007-MAH-TS9-1-CIV-MAR-0054 & 54
13 | Concrete Mix for RC works |  |  | m3 | 3300 |  |  |  | 1 | confirmed | Done | Done | Done | 2000 | 60.61%
14 | Reinforcement Steel |  |  | ton | 470 |  |  |  | 1 | Done | Done | Done | Done | 420 | 89% | 1 | KHJ1-02-007-MAH-TS9-1-CIV-MAR-001-01KHJ1-02-007-MAH-TS9-1-CIV-MRIR-0029 KHJ1-02-007-MAH-TS9-1-CIV-MRIR-0036, |  |  | KHJ1-02-007-MAH-TS9-1-CIV-MIR-0004
15 | Paving blocks 200*100*60 mm |  |  | EA | 130000 |  |  |  | 1 | confirmed | 20 days | as per site request to start |  |  | 0
16 | Structural steeL for Prefab Portcabibn |  |  | EA | 4 |  |  |  | 1 | INREVIEW |  |  |  | 4 | 100%
17 | Plaster for External Walls |  |  | m2 | HBS |  |  |  | 1 | confirmed | 45 days | AS PER SITE NEEDED
18 | Porcelain Tiling |  |  | m2 | HBS |  |  |  | 0 | Sample has been submitted for approval
19 | False Ceilings |  |  | m2 | HBS |  |  |  | 1 | confirmed | 20 days | as per site request to start
20 | Access ladder |  |  | EA | HBS |  |  |  | 0 | confirmed under cancillation | 30 days
21 | Lighting Poles Precast Foundation & Bolt |  |  | EA | 981 |  |  |  | 859 | under process |  |  |  | 863 | 88%
22 | Traffic signage |  |  | EA | 981 |  |  |  | 1 | 15/3/2026 | 55 | as per site request to start |  | 981 | 100%
23 | Doors & Windows |  |  | EA | HBS |  |  |  | 0 | wait mock up sample from alumaco for approval
24 | Granite, ceramic |  |  | m2 | HBS |  |  |  | 0 | Sample has been submitted for approval | 30 days | as per site request to start
25 | Trees and Bushes-Landscape ( soft) |  |  | EA | HBS |  |  |  | 1 | confirmed | 21 days | as per site request to start
26 | Asphalt |  |  | m3 | 75000 |  |  |  | 1 | under review |  |  |  | 20000 | 27%
27 | ICT Manholes Cover with frame |  |  | EA | 214 |  |  |  | 1 | 27/04/2026 | 90 | as per site request to start |  | 0
28 | Telecome Manholes |  |  | EA | 214 |  |  |  | 0 |  | 15 |  |  | 0
29 | Generator |  |  | EA | HBS |  |  |  | 0 | Pqd under review | 30
30 | MV Cables |  |  | m | 72000 |  |  |  | 1 | INREVIEW | 84 DAYS | 2026-01-07 | 2026-01-09 | 56700 | 79%
31 | Public address System |  |  | EA | HBS |  |  |  | 0 | under process | 7
32 | Unit Substation & RMU |  |  | EA | 10 |  |  |  | 1 | 2026-01-04 | 140 | as per site request to start |  | 10 | 100%
33 | LV Cables |  |  | m | 114893 |  |  |  | 1 | INREVIEW | 100 | 15/5/2026 | 15/7/2026 | 97030 | 84%
35 | Electrical Panels |  |  | EA | 13 |  |  |  | 0 | under process | 30 days |  |  | 13 | 100%
36 | LV Conductors (part of the panels) |  |  | EA |  |  |  |  | 0 | under process
38 | Drain & Clean Out |  |  | m | HBS |  |  |  | 0 | under process
39 | Split AC Package |  |  | EA | HBS |  |  |  | 0 | under process
40 | Ventilation Unit-Fan |  |  | EA | HBS |  |  |  | 0 | under process | 15
41 | Fire Pump |  |  | EA | HBS |  |  |  | 0 |  | 120
42 | Street Lights Lighting Fixtures |  |  | EA | 1090 |  |  |  | 1 | 27/4/2026 | 70 |  |  | 970 | 89%
43 | Street Lighting Poles |  |  | EA | 981 |  |  |  | 1 | 27/04/2026 | 70 | 20/5/2026 | 30/6/2026 | 863 | 88%
44 | PVC & EMT conduits |  |  | EA | HBS |  |  |  | 1 | INREVIEW | 15
45 | CCTV Pole |  |  | EA | HBS |  |  |  | 0 | under process
46 | Underground Ducts-HDPE |  |  | m | HBS |  |  |  | 1 | 15/3/2026 | 70 | 28/3/2026 | 30/7/2026 |  |  | 1 | KHJ1-02-007-MAH-TS9-1-ELE-MRIR-0042 KHJ1-02-007-MAH-TS9-1-ELE-MRIR-0040
47 | LIGHTING FIXTURES (buildings Internal) |  |  | EA | HBS |  |  |  | 0 |  | 15
48 | Earthing System |  |  | EA | 620 |  |  |  | 1 |  | 30 days | 15/5/2026 | 15/6/2026 | 620 | 100% | 1 | KHJ1-02-007-MAH-TS9-1-ELE-MRIR-0043
49 | Cable glands, lugs and accessories |  |  | EA |  |  |  |  | 0 | under process
50 | Wiring Devices and Switches |  |  | EA | HBS |  |  |  | 1 |  | 15
51 | DALI Cabinet (external lighting control) |  |  | EA | HBS |  |  |  | 0 | under process
52 | GI duct work with insulation & Support |  |  | EA | HBS |  |  |  | 0 | under process
53 | External Lighting Fixtures |  |  | EA | HBS |  |  |  | 0 | under process
54 | Manhole Covers |  |  | EA | 1554 |  |  |  | 1 | 16/4/2026 | 60 | AS PER SITE NEEDED |  | 785 | 51%
55 | Sewer Manholes |  |  | EA | 346 |  |  |  | 1 | 15/3/2026 | 46 | AS PER SITE NEEDED |  | 340 | 98% | 1 | KHJ-1-02-007-MAH-TS9-1-MEC-MRIR-0010-00 KHJ-1-02-007-MAH-TS9-1-MEC-MRIR-0012-01,KHJ1-02-007-МАН-TS9-1-SEW-MRIR-0057 |  |  | KHJ1-02-007-MAH-TS9-1-STR-MIR-0027,KHJ1-02-007-MAH-TS9-1-STR-MIR-0065-00
56 | Storm Manholes |  |  | EA | 300 |  |  |  | 1 | 15/3/2026 | 70 | 15/3/2026 | 2026-01-07 | 256 | 85% | 1 | KHJ-1-02-007-MAH-TS9-1-MEC-MRIR-0012-00 KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0034,KHJ1-02-007-МАН-TS9-1-SEW-MRIR-0057 |  |  | KHJ1-02-007-МАН-TS9-1-STR-MRIR-0104,KHJ1-02-007-MAH-TS9-1-STR -MIR-0031
57 | Connection Chamber |  |  | EA | 23 |  |  |  | 0 | under process |  |  |  | 0
58 | inspection Chambers |  |  | EA | 31 |  |  |  | 0 | under process |  |  |  | 0
59 | Catch Basin |  |  | EA | 666 |  |  |  | 1 | 15/3/2026 | 70 | 2026-01-05 | 2026-10-07 | 653 | 98% |  | KHJ1-02-007-МАН-TS9-1-MEC-MRIR-0065,KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0080,KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0107 |  |  | KHJ1-02-007-MAH-TS9-1-STR-MIR-0009,KHJ1-02-007-MAH-TS9-1-MEC-MIR-0023,KHJ1-02-007-MAH-TS9-1-STR-MIR-0051-00,KHJ1-02-007-MAH-TS9-1-STR-MIR-0066-00
61 | Secondary Irrigation System |  |  | EA |  |  |  |  | 1 | INREVIEW | 90 | 2026-01-06 | 2026-01-09 | 0.67 | 67%
62 | Sanitory Ware, Plumbing Fixtures, Toilet Accessories |  |  | EA | HBS |  |  |  | 0 |  | 15
63 | Ductile Iron Valves & Fittings |  |  | EA | 810 |  |  |  | 1 | INREVIEW | 130 | 2026-01-05 | 30/7/2026 | 394 | 49% |  |  |  |  | KHJ1-02-007-MAH-TS9-1-MEC-MIR-0053,KHJ1-02-007-MAH-TS9-1-STR-MIR-0067
64 | Hose Bib |  |  | EA |  |  |  |  | 0
65 | PPR Pipes & Fittings |  |  | EA | HBS |  |  |  | 1 | INREVIEW | 15 | as per site request | [7 empty] | KHJ1-02-007-MAH-TS9-1-STR-MIR-0078
66 | Irrigation Manholes Cover with frame |  |  | EA | 20 |  |  |  | 0 | under process |  |  |  | 0
67 | Potable Manholes Cover with frame |  |  | EA | 34 |  |  |  | 0 | under process |  |  |  | 0
68 | Bitumen Paint (Bituminous Damp proofing) |  |  | EA | HBS |  |  |  | 0 | under process | [5 empty] | 1 | KHJ1-02-007-MAH-TS9-1-MEC-MRIR-0041
69 | Anti Termite & Pest Control |  |  | EA | HBS |  |  |  | 1 | 2026-01-02 | FINISHED
70 | OS & Y Gate valve |  |  | EA | HBS |  |  |  | 0 | under process
71 | Termination Kits |  |  | EA | 182 |  |  |  | 1 | 27/04/2026 | 60 days | as per site request |  | 182 | 100%
72 | Fire Hydrants |  |  | EA | 310 |  |  |  | 1 | 2026-02-04 | 130 days | 30/4/2026 | 30/7/2026 | 217 | 70% |  |  |  |  | KHJ1-02-007-MAH-TS9-1-STR-MIR-0010
73 | Fire Extinguisher |  |  | EA | HBS |  |  |  | 0 |  | 07 DAYS
74 | Fire Alarm systems & cable |  |  | EA | HBS |  |  |  | 0 | under process | 45 days
75 | Water Heater |  |  | EA | HBS |  |  |  | 0 | under process | 15 DAYS
76 | HDPE House Connections Chambers |  |  | LM | HBS |  |  |  | 0 | under process | 45 days
77 | Concrete Culvert Box |  |  | LM | 1064 |  |  |  | 1 |  |  |  |  | 720 | 68% | 1 | KHJ1-02-007-MAH-TS9-1-CIV-MRIR-0027 KHJ1-02-007-MAH-TS9-1-CBC-MRIR-0044
78 | Polythlien sheets |  |  | m2 | HBS |  |  |  | 1 | 31/3/2026 |  |  |  | 120 |  | 1 | KHJ1-02-007-MAH-TS9-1-CIV-MRIR-0031
76 | HDPE House Connections Chambers |  |  | LM |  |  |  |  | 0 | under process | 45 days
77 | Concrete Culvert Box |  |  | LM | 1850 |  |  |  | 1 |  |  |  |  | 1850 | 100% | 1 | KHJ1-02-007-MAH-TS9-1-CIV-MRIR-0027 KHJ1-02-007-MAH-TS9-1-CBC-MRIR-0044
78 | Polythlien sheets |  |  | m2 |  |  |  |  | 120 | 31/3/2026 |  |  |  | 120 | 100% | 1 | KHJ1-02-007-MAH-TS9-1-CIV-MRIR-0031

## Invoice Log
Weekly Progress Report - Invoice Log
Project Value | [8 empty] | Payment Status | [7 empty] | Invoices Summary | [9 empty] | Average Invoices durations
Original Contract Value |  |  | 307891320 |  | O&M Value |  | 0 | EAC | Advance Payment % |  |  |  | Advance Payment (SAR) |  | 0 |  | No of Submitted Invoices |  | 0 |  | Submitted Invoices (SAR) |  | 27726580 |  | Submiited Invoice Peroid | 46265 | CM / PgM Average Approval duration |  | #DIV/0!
Revised Contract Value |  | 21100000 | 307891320 |  | Revised O&M Value |  | 0 | #REF! | Retention % |  | 0% |  | Retention (SAR) |  | 0 |  | No of Approved Invoices (CM) |  | 0 |  | Approved Invoices (CM) (SAR) |  | 0 |  |  |  | MODON PM & Accounts Average Approval duration |  | -
Estimate At Completion Value |  | 20900000 | 307891320 |  | Submitted Invoices (Gross Value) |  | 27726580 |  | Penalties and deduction % |  | 0% |  | AP Recovery (SAR) |  | 2772658 |  | No of Approved Invoices (PM) |  | 0 |  | Approved Invoices (PM) (SAR) |  | 0 |  | Invoice Submitted Compared to Contract Value | 0.090053 | Payments Average Duration |  | -
Potential Changes |  | 200000 | 0 |  | Total Deduction |  | 2883658 |  | Penalties and deduction (SAR) |  | 111000 |  | Retention Cumulative (SAR) |  | 2772658 |  | No of Paid Invoices |  | 0 |  | Paid Invoices (SAR) |  | 0 |  |  |  | Invoices Average total Duration
Invoice Reference |  |  |  | Invoice Value |  |  |  |  | Period Covered |  | CM / PgM Approval Timeline |  |  |  | Modon PM & Accounts Approval | [6 empty] | Payment Status |  |  |  |  | Total Invoice Duration | Remarks
# | Invoice No. | Doc Control reference | Submittal Rev. # | Gross Value | Retention | Amount After Retention | Deduction / Penalties | Amount (net) + VAT 15% | Start Date | End Date | Date to CM / PgM | CM / PgM Approval (Yes/No) | CM / PgM Reply Date | Days Elapsed | Date to PM | PM Approval (Yes/No) | PM Reply Date | Date to Accounts | Accounts Approval (Yes/No) | Accounts Approval Date | Days Elapsed | Date Paid | Amount Paid | Paid % | Payment Period (d) | Amount Pending
1 | 1 | NA | 1 | 1681886.27 | 168188.63 | 1513697.64 | 34000 | 1706752.29 | 2026-12-15 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | - | 2026-03-25 | 2026-03-25 | 2026-03-25
2 | 2 | NA | 2 | 5120873.79 | 512087.38 | 4608786.41 | 64000 | 5236104.37 | 2026-03-25 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-04 | - | 2026-06-04 | 2026-06-04 | 2026-06-04
3 | 3 | NA | 3 | 6277339.47 | 627733.95 | 5649605.52 | 0 | 6497046.35 | 2026-06-05 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | - | 2026-07-27 | 2026-07-27 | 2026-07-27
4 | 4 | NA | 4 | 14646480.26 | 1464648.03 | 13181832.23 | 13000 | 15146107.06 | 2026-07-28 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-08-31 |  | 2026-09-02 | 2026-09-06 | 2026-09-06
5 |  | NA
6 |  | NA
7 |  | NA
8 |  | NA
9 |  | NA
10 |  | NA
TOTAL |  |  |  | 27726579.79 | 2772657.99 | 24953921.8 | 111000 | 28586010.07 | [17 empty] | 0
Formulas:
Payment Status = +[End Date, row above]+1
Note on K5: Without O&M Cost
Note on D6: Without O&M Cost
Note on G6: Without O&M Cost

## Milestones
Contractiual Milestones
Item No. | Milestones | Original (Baseline) | Latest | Forecast | Days Change
1 | Site Handover Date | 2025-12-03 | 2025-12-03 | 2025-12-03 | 0
2 | Complete Mobilization | 2026-01-02 | 2026-01-02 | 2026-01-02 | 0
3 | Road works | 2026-10-02 | 2026-10-02 | 2026-10-02 | 0
4 | Medium voltage network | 2026-10-02 | 2026-10-02 | 2026-10-02 | 0
5 | All Networks | 2027-02-02 | 2027-02-02 | 2027-02-02 | 0
6 | Project Handover | 2027-12-02 | 2027-12-02 | 2027-12-02 | 0
Formulas:
Original (Baseline) = [Original (Baseline), row above]+30
Latest = [Latest, row above]+30

## Progress
Project Scope Statement | Development of infrastructure networks in Al-Kharj industrial city, which is located almost 100 kilometers southeast of Riyadh, The project is comprised of two zones (A , B and Labor Community Area ), which have a total area of approximately 3.50 square kilometers
Earned Value Progress (SAR) | [7 empty] | Physical Progress (Effort)
WBS | BOQ Value (SAR) | % Wt. | Weekly (SAR) |  | To Date (SAR) |  |  | Budgeted | % Wt. | Weekly Physical Progress |  | To Date Physical Progress
|  |  | Planned | Actual | Orignal Planned | Revised Planned | Actual | (Manhours) |  | Planned | Earned | Planned | Earned
Engineering | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 9236740 | 3% | 0 | 0 | 9236740 | 9236740 |  |  | 0.03
Procurement | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 61578264 | 20% | 52652 | 0 | 51633374 | 34483828 |  |  | 0.11
Construction | 239411880 | 77.8% | 2657471.87 | 2753236.62 | 173573613 | 98134929.61 | 101223342.86 | 206287184 | 67% | 2289788 | 2372302 | 84557117 | 87218221 |  | 0.4228 | 0.28
Testing & Commissioning | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 30789132 | 10% | 0 | 0 | 0 | 0
Close Out | 68479440 | 22.2% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0
Total | 307891320 | 100% | 2657471.87 | 2753236.62 | 173573613 | 98134929.61 | 101223342.86 | 307891320 | 1 | 2342440 | 2372302 | 145427231 | 130938789
Total | 267731583 |  | 0.86% | 0.89% | 56.37% | 31.87% | 32.88% | 100% | 0% | 0.76% | 0.77% | 47.23% | 42.53%
208184242.185 | 2677315.83 | 2026-09-28 | 88020298.1391 |  | To Date (SAR) |  |  |  |  | To Date (SAR)
|  |  | 56008474.4539 |  | Orignal Planned | Revised Planned | Actual |  |  | Orignal Planned | Revised Planned | Actual
|  |  | 32011823.6852 |  | 0 | 0 | 0 |  |  | 9236740 | 9236740 | 9236740
|  |  | 11.63% |  | 0 | 0 | 0 |  |  | 53480722 | 51580722 | 34483828
[5 empty] | 173573613 | 95477457.74 | 98470106.24 | 85626179.3391 |  | 107888197.23 | 82267329 | 84845919
|  | 2026-09-21 | 85626179.3391 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
|  |  | 51717123.0485 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
|  |  | 33909056.2907 |  | 173573613 | 95477457.74 | 98470106.24 |  |  | 173407470.53 | 144984791 | 128566487
|  |  | 12.32% |  | 56.37% | 31.01% | 31.98% |  | 0.05% | 56.32% | 47.09% | 41.76% | -8.88%
5.33%
4.7%
Activity Name | Budgeted Cost | Budgeted Units | Spreadsheet Field | time axis 2026-01-10 to 2027-05-29
WBS: ICKM01-13.Sep.2026-3.PRO PROCUREMENT | 0 | 2622.73 | Budgeted Units | 2.73 | 46.36 | 72.27 | 89.09 | 93.64 | 98.18 | 100.91 | 99.55 | 95.45 | 92.73 | 90 | 87.27 | 86.52 | 82.27 | 74.09 | 71.36 | 68.18 | 64.09 | 60.45 | 58.18 | 53.18 | 35.91 | 31.33 | 22.16 | 20.34 | 19.43 | 19.43 | 19.43 | 19.43 | 16.7 | 16.7 | 16.7 | 15.8 | 14.43 | 35.8 | 79.43 | 81.27 | 81.27 | 79 | 56.73 | 45.82 | 43.09 | 37.64 | 37.64 | 20.73 | 17.27 | 14.55 | 13.64 | 13.64 | 13.18 | 10.91 | 10.91 | 10.91 | 7.27 | 5.45 | 5.45 | 5 | 2.73 | 2.73 | 2.73 | 2.73 | 2.73 | 2.73 | 2.73 | 2.73 | 2.73 | 2.73 | 2.73 | 2.73 | 2.73 | 2.73 | 2.73 | 0.91
|  |  |  | 0.0010409 | 0.017676 | 0.027555 | 0.033968 | 0.035703 | 0.037434 | 0.038475 | 0.037957 | 0.036393 | 0.035356 | 0.034315 | 0.033274 | 0.032989 | 0.031368 | 0.028249 | 0.027208 | 0.025996 | 0.024436 | 0.023049 | 0.022183 | 0.020277 | 0.013692 | 0.011946 | 0.0084492 | 0.0077553 | 0.0074083 | 0.0074083 | 0.0074083 | 0.0074083 | 0.0063674 | 0.0063674 | 0.0063674 | 0.0060243 | 0.0055019 | 0.01365 | 0.030285 | 0.030987 | 0.030987 | 0.030121 | 0.02163 | 0.01747 | 0.016429 | 0.014351 | 0.014351 | 0.007904 | 0.0065847 | 0.0055477 | 0.0052007 | 0.0052007 | 0.0050253 | 0.0041598 | 0.0041598 | 0.0041598 | 0.0027719 | 0.002078 | 0.002078 | 0.0019064 | 0.0010409 | 0.0010409 | 0.0010409 | 0.0010409 | 0.0010409 | 0.0010409 | 0.0010409 | 0.0010409 | 0.0010409 | 0.0010409 | 0.0010409 | 0.0010409 | 0.0010409 | 0.0010409 | 0.0010409 | 0.00034697
|  |  |  | 0.0010409 | 0.018717 | 0.046272 | 0.080241 | 0.11594 | 0.15338 | 0.19185 | 0.22981 | 0.2662 | 0.30156 | 0.33588 | 0.36915 | 0.40214 | 0.43351 | 0.46176 | 0.48896 | 0.51496 | 0.5394 | 0.56244 | 0.58463 | 0.6049 | 0.6186 | 0.63054 | 0.63899 | 0.64675 | 0.65415 | 0.66156 | 0.66897 | 0.67638 | 0.68275 | 0.68911 | 0.69548 | 0.70151 | 0.70701 | 0.72066 | 0.75094 | 0.78193 | 0.81292 | 0.84304 | 0.86467 | 0.88214 | 0.89857 | 0.91292 | 0.92727 | 0.93517 | 0.94176 | 0.94731 | 0.95251 | 0.95771 | 0.96273 | 0.96689 | 0.97105 | 0.97521 | 0.97798 | 0.98006 | 0.98214 | 0.98405 | 0.98509 | 0.98613 | 0.98717 | 0.98821 | 0.98925 | 0.99029 | 0.99133 | 0.99237 | 0.99342 | 0.99446 | 0.9955 | 0.99654 | 0.99758 | 0.99862 | 0.99966 | 1

## Physical-Chart Data
| Baseline Plan |  |  | Revised / Recovery Plan |  |  | Earned Effort %
Month | Monthly Effort | Cum Effort | Plan Wt.% | Monthly Effort | Cum. Effort | Plan Wt.% | Monthly Effort | Cum Effort | Cum.Act. Wt.%
2025-12-01 | 8419524 | 8419524 | 2.7% | 0 | 0 | 0% | 1338657.92 | 1338657.91 | 0.4%
2026-01-31 | 2196489 | 10616013 | 3.4% | 615782.65 | 615782.65 | 0.2% | 10173800.12 | 11512458.03 | 3.7%
2026-02-28 | 14420331 | 25036344 | 8.1% | 7697283.07 | 8313065.72 | 2.7% | 8835142.21 | 20347600.24 | 6.6%
2026-03-31 | 33339297 | 58375641 | 19% | 19089262.03 | 27402327.75 | 8.9% | 6425557.98 | 26773158.22 | 8.7%
2026-04-30 | 37611630 | 95987271 | 31.2% | 21552392.61 | 48954720.36 | 15.9% | 26211859.31 | 52985017.61 | 17.21%
2026-05-31 | 22056707 | 118043978 | 38.3% | 19089262.02 | 68043982.38 | 22.1% | 15635952.77 | 68620970.38 | 22.3%
2026-06-30 | 18108751 | 136152729 | 44.2% | 21244501.29 | 89288483.67 | 29% | 20889194.46 | 89510164.84 | 29.1%
2026-07-31 | 24569297 | 160722026 | 52.2% | 24631305.84 | 113919789.51 | 37% | 15847782.01 | 105357946.85 | 34.2%
2026-08-31 | 23526180 | 184248206 | 59.8% | 20320827.32 | 134240616.83 | 43.6% | 10354077.18 | 115712024.03 | 37.6%
2026-09-30 | 48356422 | 232604628 | 75.5% | 13239326.89 | 147479943.72 | 47.9% | 15226764.97 | 130938789 | 42.5% | 202264893.913
2026-10-31 | 23001344 | 255605972 | 83% | 30789132.3 | 178269076.02 | 57.9%
2026-11-30 | 12608740 | 268214712 | 87.1% | 37562741.4 | 215831817.42 | 70.1%
2026-12-31 | 972462 | 269187174 | 87.4% | 19089262.03 | 234921079.45 | 76.3%
2027-01-31 | 12810602 | 281997776 | 91.6% | 2463130.58 | 237384210.03 | 77.1%
2027-02-28 | 6202280 | 288200056 | 93.6% | 17549805.41 | 254934015.44 | 82.8%
2027-03-31 | 5580537 | 293780593 | 95.4% | 28018110.4 | 282952125.84 | 91.9%
2027-04-30 | 6212230 | 299992823 | 97.4% | 7081500.43 | 290033626.27 | 94.2%
2027-05-31 | 2647466 | 302640289 | 98.3% | 5234152.49 | 295267778.76 | 95.9%
2027-06-30 | 2923583 | 305563872 | 99.2% | 7081500.43 | 302349279.19 | 98.2%
2027-07-31 | 1336381 | 306900253 | 99.7% | 3386804.55 | 305736083.74 | 99.3%
2027-08-31 | 651250 | 307551503 | 99.9% | 1847347.94 | 307583431.68 | 99.9%
2027-09-30 | 324742 | 307876245 | 100% | 307891.32 | 307891323 | 100%
2027-10-31 | 15078 | 307891323 | 100% | 0 | 307891323 | 100%
2027-11-30 |  |  |  | 0 | 307891323 | 100%
2027-12-31 |  |  |  | 0 | 307891323 | 100%
Formulas:
Month = EOMONTH([Month, row above],1)

## Manpower
|  | Head-Count (Non-Manual) | [23 empty] | 2026-09-28
|  | MONTHS | 2025-12-01 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31
|  | Planned - Cumulative | 2 | 47 | 201 | 385 | 544 | 422 | 413 | 596 | 642 | 435 | 677 | 841 | 554 | 106 | 252 | 689 | 284 | 76 | 206 | 110 | 70 | 26 | 1 | 0 | 0
|  | Actual Cumulative | 20 | 105 | 190 | 303 | 428 | 588 | 650 | 670 | 659 | 659
|  |  | 0% | 1% | 3% | 5% | 7% | 6% | 5% | 8% | 8% | 6% | 9% | 11% | 7% | 1% | 3% | 9% | 4% | 1% | 3% | 1% | 1% | 0% | 0% | 0% | 0%
|  | 0 | 0% | 1% | 4% | 9% | 16% | 22% | 27% | 35% | 43% | 49% | 58% | 69% | 76% | 77% | 80% | 89% | 93% | 94% | 97% | 98% | 99% | 99% | 99% | 99% | 99%
Activity Name | Budgeted Units | Spreadsheet Field | time axis 2026-01-03 to 2027-10-02
Total | 438870 | Budgeted Units | 366.57 | 402 | 939.76 | 1640.43 | 2420.86 | 2994.67 | 4137.43 | 3390.86 | 3969.29 | 4335.12 | 4958.12 | 6138.48 | 7085.33 | 7830.36 | 7246.45 | 7602.52 | 6979 | 6002.62 | 5754.74 | 5606.02 | 5680.93 | 4778.64 | 4859.33 | 5284.1 | 5857.07 | 6779.79 | 7609.57 | 8197.24 | 8168.4 | 7819.24 | 7754.66 | 8665.22 | 8681.3 | 7866 | 7370.44 | 6580.38 | 5683.47 | 4986.32 | 4728.68 | 5953.26 | 8468.39 | 10786.19 | 10828.43 | 11658.1 | 11511.97 | 10653.86 | 10936.17 | 9666.28 | 8329.5 | 7255.48 | 6892.17 | 4794.98 | 2918.56 | 1512.46 | 1012.33 | 492.14 | 325.9 | 1499.38 | 4212.95 | 6067.24 | 7127.19 | 8262.24 | 10063.81 | 9736.19 | 7891.29 | 6633.45 | 4024.88 | 2461.43 | 1913.24 | 1416.43 | 835.1 | 868.67 | 872.08 | 650.9 | 4362.42 | 2582.76 | 2419.82 | 2437.59 | 2020.49 | 1446.04 | 1341.43 | 894.21 | 1181.87 | 1055.1 | 794.44 | 712.57 | 619.5 | 422.67 | 360.16 | 286.41 | 217 | 31.5 | 31.5
|  |  | 366.57 | 768.57 | 1708.33 | 3348.76 | 5769.62 | 8764.29 | 12901.72 | 16292.58 | 20261.87 | 24596.99 | 29555.11 | 35693.59 | 42778.92 | 50609.28 | 57855.73 | 65458.25 | 72437.25 | 78439.87 | 84194.61 | 89800.63 | 95481.56 | 100260.2 | 105119.53 | 110403.63 | 116260.7 | 123040.49 | 130650.06 | 138847.3 | 147015.7 | 154834.94 | 162589.6 | 171254.82 | 179936.12 | 187802.12 | 195172.56 | 201752.94 | 207436.41 | 212422.73 | 217151.41 | 223104.67 | 231573.06 | 242359.25 | 253187.68 | 264845.78 | 276357.75 | 287011.61 | 297947.78 | 307614.06 | 315943.56 | 323199.04 | 330091.21 | 334886.19 | 337804.75 | 339317.21 | 340329.54 | 340821.68 | 341147.58 | 342646.96 | 346859.91 | 352927.15 | 360054.34 | 368316.58 | 378380.39 | 388116.58 | 396007.87 | 402641.32 | 406666.2 | 409127.63 | 411040.87 | 412457.3 | 413292.4 | 414161.07 | 415033.15 | 415684.05 | 420046.47 | 422629.23 | 425049.05 | 427486.64 | 429507.13 | 430953.17 | 432294.6 | 433188.81 | 434370.68 | 435425.78 | 436220.22 | 436932.79 | 437552.29 | 437974.96 | 438335.12 | 438621.53 | 438838.53 | 438870.03 | 438901.53
|  |  | 0.08% | 0.18% | 0.39% | 0.76% | 1.31% | 2% | 2.94% | 3.71% | 4.62% | 5.6% | 6.73% | 8.13% | 9.75% | 11.53% | 13.18% | 14.91% | 16.5% | 17.87% | 19.18% | 20.46% | 21.75% | 22.84% | 23.95% | 25.15% | 26.49% | 28.03% | 29.77% | 31.64% | 33.5% | 35.28% | 37.04% | 39.02% | 41% | 42.79% | 44.47% | 45.97% | 47.26% | 48.4%

## Risk Register
RISK Register
Department:
Program
Project: | Development Industrial City-Alkharj
Project No.: | 3121
Project Location: | Industrial City-Alkharj
Risk Data | [5 empty] | Category |  |  | Risk Description |  |  | Risk Control Dates |  | Risk Manageability | Risk Proximity | Most Likely |  |  | Risk Owner | Risk Response & Treatment Action |  |  |  | Treatment Control Dates |  |  | Most Likely |  |  | Treatment Status
Risk ID | Region | Section / Group | City | Project ID | Risk Status | T/O/I | Internal/External | Category | Cause / Source | Risk | Consequence / Effect | Identified | Closed |  |  | Liklihood | Impact | Risk Score |  | Risk Response Strategy | Treatment Action | Treatment Acton Description | Treatment Action Owner | Start | Due | Closed | Liklihood | Impact | Risk Score
1 | Central | Central | Al Kharj | KHJ1-02-007 | Close | Issue | External | Construction / Obstacle | Site Obstacle | Existing Site offices, fencing and work shop in zone B | Project progress delay | 31, Dec 2025 | Closed | Moderate | Distant | High | High |  | Client | Share | Control | Email has been sent to the consultant, to advise and address this issue with stakeholder | Client | 31, Dec 2025 | 27, Jan 2026 |  | Medium | Medium |  | Open
2 | Central | Central | Al Kharj | KHJ1-02-007 | Close | Issue | External | Design / Planning | Drawings | Helipad Location and end user requirement | Project progress delay | 31, Dec 2025 | Location Closed Pending Requirments | Moderate | Distant | High | High |  | Client | Share | Control | As discussed an RFI has been sent with all required to start working on a resoluation and open aprper communication channel with the end user | Client | 31, Dec 2025 | 15, Feb 2026 |  | Medium | Medium |  | Open
3 | Central | Central | Al Kharj | KHJ1-02-007 | Open | Issue | Internal | Authorities / Permits | Drawings | Portacabin services Tie-ins | Project progress delay | 31, Dec 2025 | Closed | Moderate | Distant | Low | Medium |  | Client | Share | Control | Working on it with the client | Client | 31, Dec 2025 | 5, Feb 2026 |  | Low | Low |  | Open
4 | Central | Central | Al Kharj | KHJ1-02-007 | Open | Issue | External | Weather / Environmental | Weather | Rains/ Winds/ Dust/Hrash | Project progress delay | Expected | Open | Hard | Distant | High | High |  | - | Accept | Mitigate | - | - | - | - |  | Medium | Medium |  | Open
5 | Central | Central | Al Kharj | KHJ1-02-007 | Open | Issue | Internal | Procurment / Logistic | Procurement | Subgrade Fill/Manholes/ Pipes | Project progress delay | 28, Dec. 2026 | open | Moderate | Distant | High | High |  | MMAH | Treat | Mitigate | Working on it to resolve the delay and assign many suppliers | MMAH | 20, Dec 2025 | 15, Feb 2026 |  | Medium | Medium |  | Open
6 | Central | Central | Al Kharj | KHJ1-02-007 | Open | Issue | Internal | Safety / Quality | Construction Work | Deep Excavation | Project progress delay | Expected | closed | Moderate | Distant | High | High |  | MMAH | Treat | Mitigate | Safety measures and plans | MMAH | 07, Feb 2026 | 15, Feb 2027 |  | Medium | Medium |  | Open
7 | Central | Central | Al Kharj | KHJ1-02-007 | Open | Issue | Internal | Interface / Communication | Construction Work | Existing Services & Roads | Project progress delay | Expected | closed | Moderate | Distant | High | High |  | Client &MMAH | Share | Mitigate | it will be coordinate with the client and the EndUsers of those existing sevices | Client &MMAH | 07, Feb 2026 | 15, Feb 2027 |  | Medium | Medium |  | Open
8 | Central | Central | Al Kharj | KHJ1-02-007 | Open | Issue | Internal | Procurment / Logistic | Procurement | Delay in procurement of key materials | Project progress delay | Expected | closed | Moderate | Distant | High | High |  | - | Treat | Mitigate | Working on it to resolve the delay and assign many suppliers | MMAH
NOTES:
Risk Status: 1.Open, 2.Closed, or 3.Realized
T/O/I: 1.Threat, 2.Opportunity, or 3.Issue
Category (select 1):
1. Political
2. Legal, Regulatory, Compliance
3. Funding, Finance, Budget
4. Management, Governance, Policies, KPI, Performance
5. Human Resources | [21 empty] | `
6. Stakeholders, Authorities, Approvals, Permits
7. Requirements, Specifications, Scope, Procurement, Contract
8. Process, Tools, Technique, Technology
9. Design, Engineering
10. Construction, Execution
11. Testing, Commissioning, Handover
12. Operation, Maintenance
Risk Description (add all 3):
1. Source/Cause
2. Event = Threat, Opportunity, or Issue
3. Consequence/Effect
Risk Response Strategy for Threats: 1.Terminate, 2.Tolerate, 3.Transfer, or 4.Treat
Risk Response Strategy for Opportunities: 1.Ignore, 2.Share, or 3.Enhance/Exploit
Treatment Action: 1.Mitigate, 2.Control, or 3.Fall Back
Treatment Status: 1.Unapproved, 2.Active, or 3.Closed
Risk Level/Score: Likelihood x Highest Impact (Safety, Cost, Schedule, Environment, Quality, or Reputation. See Risk Scoring Matrix tab)

## Issues
Issues Log | [5 empty] | 2026-09-28
Issue No | Date Identified | Issue Description | Responsibility | Action Taken | Current Status | Expected/Actual Closure | Duration Elapsed
1 |  | Site Obstacles | Client | An RFI has been sent with all required to start working on a resolution and open aprper communication channel with the end user : 1-Existing obstacles between the factory boundary and Local Roads 19 and 20 are preventing the commencement of the planned works. 2- Along Local Road 18, there are old rooms and a fenced storage area currently in use, in addition to installed signage. 3-A diesel tank is located within the affected area; clarification is required regarding the party responsible for its removal. 4- The crusher area must be officially handed over to MAH to proceed with surveying, as the existing NGL differs from the approved design levels. 5-An existing fenced storage area and site offices must be removed to allow access and ensure uninterrupted progress of the works) Action Taken : Meeting Held in Maddon Office and discussed the all challenges with all parties, and all challenges in process to be solved and removed . | Closed | 2026-02-15
2 |  | Logistic / Procurement | MG | Logistics and Procurement services to be improved and expedited. | Closed | 2026-04-25
3 |  | MV Network | MG | Finalize a deal with approved SEC contractor and Consultant to carry out the work and supervise it. | Closed | 2026-04-25
4 |  | Contract Milestones | MG | MMAH Team Needs to recover and Put the follwing on track. 1- Engineering Work Completion. " Closed" 2- Procurement Work. " Closed" 3- Construction Work. " On Going" | Open | 2026-08-30
5 | 20-Apr-2026 | Overall delay against approved baseline | MG | Prepare & implement recovery plan, add resources, additional shifts " Closed" | Closed | 2026-04-30
6 |  | Technical | MG | Identify and utilize potential financial/technical savings within the project | Open
7 |  | Construction | MG | Continue asphalt works without interruption | Open
8 |  | Construction | MG | The close proximity of the Medium Voltage (MV) network to the water and irrigation networks is preventing the commencement of internal MV network works | Open
9 |  | Construction | MG | Ongoing excavation in the box culvert area in Zone A for completion of the stormwater drainage network is conflicting with existing utilities, including Low Voltage (LV) and Medium Voltage (MV) cables, as well as water and irrigation pipelines | Open

## CCO
CONTRACT CHANGE ORDER (CCO)
CCO No. | Date Added | Description of Change | Status | SR | Sch Impact (Months) | Date Approved | Duration (days)
NA
NA
NA
NA
NA
NA
NA
NA
NA
NA

## Testing
Testing and Commissioning
Item | Planned Start Date | Planned Finish Date | Forecast Start Date | Forecast Finish Date | Actual Start Date | Actual Finish Date | % Completed | Open Comments | Closed Comments
Testing & Commissioning
Total

## KHARAJ CABLES TAKEOFF ZONE A (hidden)
ITEM | TOTAL LENGTH | NO. OF CABLES | EXCAVATION LENGTH | FACTOR | FINAL EXCAVATION LENGTH | ADJUSTMENT | FINAL CABLE LENGTH
1 CABLE | 14718.178 | 1 | 14718.178 | 1.05 | 15454.0869 | 15454 | 15454
2 CABLES | 4947.804 | 2 | 2473.902 | 1.05 | 2597.5971 | 2597 | 5194
3 CABLES | 1455.314 | 3 | 485.1047 | 1.05 | 509.3599 | 509 | 1527
5 CABLES | 726.669 | 5 | 145.3338 | 1.05 | 152.6005 | 152 | 760
6 CABLES | 5936.842 | 6 | 989.4737 | 1.05 | 1038.9473 | 1038 | 6228
Total | [6 empty] | 29163
No. of Cables | DIM. | EXCAVATION AREA | EXCAVATION QTY. | ADJUSTED EXCAVATION QTY.
1 CABLE | 0.4 X 0.8 | 0.32 | 4945.28 | 4945
2 CABLES | 0.6 X 0.8 | 0.48 | 1246.56 | 1246
3 CABLES | 0.9 X 0.8 | 0.72 | 366.48 | 366
5 CABLES | 1.5 X 0.8 | 1.2 | 182.4 | 182
6 CABLES | 1.8 X 0.8 | 1.44 | 1494.72 | 1494

## KHATRAJ ZONE B (hidden)
ITEM | TOTAL LENGTH | NO. OF CABLES | EXCAVATION LENGTH | FACTOR | FINAL EXCAVATION LENGTH | ADUSTED EXCAVATION | FINAL CABLE LENGTH
1 CABLE | 4837.863 | 1 | 4837.863 | 1.05 | 5079.7562 | 5079 | 5079
2 CABLES | 11669.626 | 2 | 5834.813 | 1.05 | 6126.5536 | 6126 | 12252
3 CABLES | 2142.739 | 3 | 714.2463 | 1.05 | 749.9587 | 749 | 2247
4 CABLES | 1869.225 | 4 | 467.3062 | 1.05 | 490.6716 | 490 | 1960
8 CABLES | 25123.545 | 8 | 3140.4431 | 1.05 | 3297.4653 | 3297 | 26376
Total | [6 empty] | 47914
CABLE ITEM | No. of Cables | increment | Cable excavation actual width
1 CABLE | 1 | 0.4 | 0.4
2 CABLES | 2 | 0.3 | 0.6
3 CABLES | 3 | 0.3 | 0.9
4 CABLES | 4 | 0.3 | 1.2
8 CABLES | 8 | 0.3 | 2.4
5 CABLES | 5 | 0.3 | 1.5
6 CABLES | 6 | 0.3 | 1.8
No. of Cables | DIM. | EXCAVATION AREA | EXCAVATION QTY. | ADJUSTED EXCAVATION QTY.
1 CABLE | 0.4 X 0.8 | 0.32 | 1625.28 | 1625
2 CABLES | 0.6 X 0.8 | 0.48 | 2940.48 | 2940
3 CABLES | 0.9 X 0.8 | 0.72 | 539.28 | 539
4 CABLES | 1.2 X 0.8 | 0.96 | 470.4 | 470
8 CABLES | 2.4 X 0.8 | 1.92 | 6330.24 | 6330

## TOTAL ITEMS FOR ZONE A&B (hidden)
ITEM | TOTAL CABLE LENGTH | EXCAVATION QTY.
1 CABLE | 20533 | 6570
2 CABLES | 17446 | 4186
3 CABLES | 3774 | 905
4 CABLES | 1960 | 470
5 CABLES | 760 | 182
6 CABLES | 6228 | 1494
8 CABLES | 26376 | 6330
Total | 77077

## STANDBY BOQ (hidden)
#REF! | [6 empty] | #REF!
جدول الكميات | [6 empty] | BILL OF QUANTITIES
البند | وصف البند | الوحدة | الكمية | السعر (ريال سعودي) | المبلغ (ريال سعودي) | ITEM DESCRIPTION | ITEM
|  | Unit | QUANTITY | PRICE (S.R) | AMOUNT (S.R)
أعمال الطرق | [5 empty] | ROAD WORKS
02 41 00 | أعمال الهدم |  |  |  |  | DEMOLITION | 02 41 00
B1.02 41 00.1 | إزالة أسفلت قائم | m2 | 2200 |  |  | Demolition of existing Asphalt | B1.02 41 00.1
B1.02 41 00.2 | اعداد طبقة الاساس الحصوي القائمة | m2 | 2200 |  |  | Compaction of existing aggregate base course layer | B1.02 41 00.2
B1.02 41 00.3 | إزالة بردورات قائمه | m | 464 |  |  | Demolition of existing Kerbs | B1.02 41 00.3
31 22 00 | الأعمال الترابية و التسوية |  | 0 |  |  | EARTHWORKS AND SITE GRADING | 31 22 00
B1.31 22 00.01 | حفريات الطرق | m3 | 205106 |  |  | Excavation for cuttings | B1.31 22 00.01
B1.31 22 00.02 | ردميات الطرق | m3 | 1378709 |  |  | Fill to the roads | B1.31 22 00.02
B1.31 22 00.03 | طبقة القاعدة | m3 | 222337 |  |  | Subgrade | B1.31 22 00.03
32 11 23 | طبقة أساس حصوية |  | 0 |  |  | AGGREGATE BASE COURSE | 32 11 23
B1.32 11 23.01 | طبقة أساس حصوية | m3 | 145216 |  |  | Aggregate base course | B1.32 11 23.01
32 11 26 | الإنشاء البيتوميني |  | 0 |  |  | BITUMINOUS CONSTRUCTION | 32 11 26
B1.32 11 26.02 | الطبقة الأساس البيتومينية (تدرج 1 - صنف أ)، شاملاً الطبقة اللاصقة (MC1) & (RC2) . | m3 | 63389 |  |  | Bituminous base course (Grading I - Class A), including Prime Coat (MC1) & (RC2). | B1.32 11 26.02
32 12 16 | طبقة السطح العليا |  | 0 |  |  | ASPHALT WEARING COURSE | 32 12 16
B1.32 12 16.01 | طبقة السطح العليا من الخرسانة البيتومينية (تدرج 1 - صنف أ) شاملاً الطبقة اللاصقة (RC2) . | m3 | 36304 |  |  | Bituminous concrete wearing course, (Grading I - Class A), including tack coat (RC2). | B1.32 12 16.01
32 14 13 | بردورات مسبقة الصب |  | 0 |  |  | PRECAST CONCRETE CURB | 32 14 13
B1.32 14 13.01 | بردورات نوع (K1A) | m | 79448 |  |  | Concrete curb, Type (K1A) | B1.32 14 13.01
B1.32 14 13.02 | بردورات نوع (K1B) | m | 21624 |  |  | Concrete curb, Type (K1B) | B1.32 14 13.02
B1.32 14 13.03 | بردورات نوع (K2) | m | 2755 |  |  | Concrete curb, Type (K2) | B1.32 14 13.03
| يتم ترحيل الطرق - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO ROADS - COLLECTION
32 17 23 | العلامات الأرضية |  |  |  |  | PAVEMENT MARKINGS | 32 17 23
32 17 23.01 | دهان ثرموبلاستيك (أبيض / أصفر) |  |  |  |  | Thermoplastic pavement marking (White/Yellow) | 32 17 23.01
B1.32 17 23.01.01 | دهانات مرورية بيضاء عاكسة بلاستيكية حرارية | m² | 18149 |  |  | Retroreflective Thermoplastic White Traffic | B1.32 17 23.01.01
B1.32 17 23.01.02 | دهانات مرورية صفراء عاكسة بلاستيكية حرارية | m² | 11771 |  |  | Retroreflective Thermoplastic Yellow Traffic | B1.32 17 23.01.02
10 14 53 | اللوحات الإرشادية للطرق |  | 0 |  |  | TRAFFIC SIGNAGE | 10 14 53
B1.10 14 53.01 | لوحات مرورية المثبتة بالأرض مصنوعة من ألواح ألومنيوم مع حواملها القابلة للإنفصال بالقاعدة مكونة من لوحة مروريه وعمود واحد مع كافة الاكسسورات وكل ما يلزم حسب المخططات والمواصفات. | Unit | 482 |  |  | Traffic signs, ground mounted, 1 Sheet Alumenium, (breakaway) Single post, with all accessories according to the drawings and specifications. | B1.10 14 53.01
B1.10 14 53.02 | لوحات مرورية المثبتة بالأرض مصنوعة من ألواح ألومنيوم مع حواملها القابلة للإنفصال بالقاعدة مكونة من لوحتين مروريتين وعمود واحد مع كافة الاكسسورات وكل ما يلزم حسب المخططات والمواصفات. | Unit | 275 |  |  | Traffic signs, ground mounted, 2 Sheet Alumenium, (breakaway) Single post, with all accessories according to the drawings and specifications. | B1.10 14 53.02
B1.10 14 53.03 | لوحات مرورية مصنوعة من ألواح الإلمنيوم مع حواملها (قابلة للانفصال بالقاعدة) مكونة من لوحه مروريه وعمودين مع كافات الاكسسورات، وكل ما يلزم حسب المخططات والمواصفات. | Unit | 45 |  |  | Traffic signs, ground mounted, Sheet Alumenium, (breakaway) Double post with all accessories according to the drawings and specifications. | B1.10 14 53.03
B1.10 14 53.04 | علامات أرضية بارزة عاكسة (نوع - أ) | Unit | 500 |  |  | Retroreflective raised pavement markers (Type A) | B1.10 14 53.04
B1.10 14 53.05 | علامات أرضية بارزة مصنوعة من السيراميك | Unit | 500 |  |  | Ceramic raised pavement markers | B1.10 14 53.05
B1.10 14 53.06 | علامات أرضية مضيئة تعمل بالطاقة الشمسية (عيون القط) | Unit | 500 |  |  | Solar powered lighting cateyes pavement markers | B1.10 14 53.06
0
0
0
0
0
| يتم ترحيل الطرق - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO ROADS - COLLECTION
الأعمال الكهربائية |  |  |  |  | 0 | ELECTRICAL WORKS
31 23 00 | خندق كابل الجهد المتوسط |  |  |  | 0 | MEDIUM VOLTAGE CABLE TRENCH | 31 23 00
B2.31 23 00.01 | حفر خندق كابل بعرض 40 سم وعمق 80 سم يسع لعدد (1) كابل | m³ | 4945 |  |  | Excavation for Trench size 40cm wide and 80cm deep (for 1 cable) | B2.31 23 00.01
B2.31 23 00.02 | حفر خندق كابل بعرض 60 سم وعمق 80 سم يسع لعدد (2) كابل | m³ | 1246 |  |  | Excavation for Trench size 60cm wide and 80cm deep ( for 2 cables) | B2.31 23 00.02
B2.31 23 00.03 | حفر خندق كابل بعرض 90 سم وعمق 80 سم يسع لعدد (3) كابل | m³ | 325 |  |  | Excavation for Trench size 90cm wide and 80cm deep ( for 3 cables) | B2.31 23 00.03
B2.31 23 00.04 | حفر خندق كابل بعرض 150 سم وعمق 80 سم يسع لعدد (5) كابل | m³ | 182 |  |  | Excavation for Trench size 150 cm wide and 80 cm deep ( for 5 cables) | B2.31 23 00.04
B2.31 23 00.05 | حفر خندق كابل بعرض 180 سم وعمق 80 سم يسع لعدد (6) كابل | m³ | 1494 |  |  | Excavation for Trench size 180 cm wide and 80 cm deep ( for 6 cables) | B2.31 23 00.05
33 71 19 | عبارات كابلات الجهد المتوسط |  | 0 |  |  | MEDIUM VOLTAGE CABLES DUCT BANKS | 33 71 19
B2.33 71 19.01 | عبارة لعدد ( 2 ) ماسورة | m | 454 |  |  | Duct bank 2 way | B2.33 71 19.01
B2.33 71 19.02 | عبارة لعدد (4) ماسورة | m | 101 |  |  | Duct bank 4 way | B2.33 71 19.02
26 05 13.16 | كيابل الجهد المتوسط |  |  |  | 0 | MEDIUM VOLTAGE CABLES | 26 05 13.16
B2.26.05.13.16.01 | كيبل جهد 15 ك.ف.500*3C مم2 AL/ XLPE/ LLDPE غير مسلح | m | 29163 |  |  | Cable: 15KV 3Cx500mm² AL/XLPE/LLDPE unarmored | B2.26.05.13.16.01
B2.26.05.13.16.02 | كابل نحاس أحادي القلب جهد 15 ك.ف غير مسلح (3x1Cx50mm²,Cu/LLDPE/PVC). | m | 45 |  |  | Single Core Cables, Copper, 15kV (3x1Cx50mm²,Cu/LLDPE/PVC). | B2.26.05.13.16.02
B2.26.05.13.16.03 | وصلات كيابل مستقيمة جهد 15 ك.ف. 3C x 500 مم2 Al /XLPE/LLDPE غير مسلح | Unit | 66 |  |  | Straight joints cables for 15KV 3x500mm² AL/XLPE/LLDPE unarmored | B2.26.05.13.16.03
B2.26.05.13.16.04 | نهاية كابل جهد 15 ك.ف. 3C x 500 مم2 Al /XLPE/LLDPE | Unit | 24 |  |  | Cable Termination for 15KV 3Cx500mm² AL/XLPE/LLDPE | B2.26.05.13.16.04
| يتم ترحيل شبكة التوزيع الكهربائية - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO ELECTRICAL DISTRIBUTION NETWORK - COLLECTION
26 13 00 | مفاتيح الجهد المتوسط |  |  |  | 0 | MEDIUM VOLTAGE SWITCHGEARS | 26 13 00
B2.26 13 00.01 | مفتاح جهد متوسط (13.8 ك.ف) (وحدة الربط الحلقي) لنقاط الفتح بين المغذيات (NOP) من النوع الخارجي طبقاً لمواصفات الشركة السعودية للكهرباء ومتطلباتها | Unit | 6 |  |  | Normally Open Point (R M U) 13.8 kv for Outdoor type according to the Saudi Electric Company specifications and requirements | B2.26 13 00.01
| إنارة الطرق |  |  |  | 0 | ROAD LIGHTING
26 11 16 | محطات الإنارة |  |  |  | 0 | STREET LIGHTING SUB-STATION | 26 11 16
B2.26 11 16.01 | محطة مصندقة 13.8/0.4 ك ف ، 500 ك.ف .ا, شاملة القواعد الخرسانية والسياج .حسب مواصفات ومعايير شركة الكهرباء | Unit | 5 |  |  | Unit Substation 13.8/0.4 K V, 500kVA ,Including concrete foundations and fencing, According to the specifications and standards of SEC | B2.26 11 16.01
B2.26 11 16.04 | وحدة الجهد المتوسط الحلقية الالية 15 ك ف , RMU. حسب مواصفات ومعايير شركة الكهرباء | Unit | 5 |  |  | Ring Main Unit RMU, 15 KV, According to the specifications and standards of SEC | B2.26 11 16.04
26 05 19 | كابلات الضغط المنخفض |  |  |  | 0 | LOW VOLTAGE CABLES | 26 05 19
B2.26 05 19.01 | كابل الومنيوم, (4Cx185mm²,AL/XLPE/PVC). | m | 100 |  |  | Cables, Aluminium, (4Cx185mm²,AL/XLPE/PVC). | B2.26 05 19.01
B2.26 05 19.02 | كابل نحاس, (4Cx50mm²,Cu/XLPE/SWA/PVC + 1x25mm² PVC/ECC). | m | 50 |  |  | Cables, Copper, (4Cx50mm²,Cu/XLPE/SWA/PVC + 1x25mm² PVC/ECC). | B2.26 05 19.02
B2.26 05 19.03 | كابل نحاس, (4Cx95mm²,Cu/XLPE/SWA/PVC + 1x50mm² PVC/ECC). | m | 7240 |  |  | Cables, Copper, (4Cx95mm²,Cu/XLPE/SWA/PVC + 1x50mm² PVC/ECC). | B2.26 05 19.03
B2.26 05 19.04 | كابل نحاس, (4Cx16mm²,Cu/XLPE/SWA/PVC +1x10mm² PVC/PVC) | m | 57370 |  |  | Cables, Copper, (4Cx16mm²,Cu/XLPE/SWA/PVC +1x10mm² PVC/PVC) | B2.26 05 19.04
26 27 33 | لوحات توزيع الجهد المنخفض |  |  |  | 0 | LOW VOLTAGE DISTRIBUTION PANEL | 26 27 33
B2.26 27 33.01 | كابينه توزيع الجهد المنخفض Main: 100A, MCCB | Unit | 5 |  |  | 100A MCCB Low Voltage Distribution Cabinet. | B2.26 27 33.01
| يتم ترحيل شبكة التوزيع الكهربائية - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO ELECTRICAL DISTRIBUTION NETWORK - COLLECTION
26 56 19 | أعمدة إنارة |  |  |  | 0 | LIGHTING POLES | 26 56 19
B2.26 56 19.01 | أعمدة أنارة مع ذراعين ، إرتفاع 16 متر، تشمل علبة توزيع الطاقة والكوابل، والقاعدة الخرسانية | Unit | 107 |  |  | Lighting poles with double arm, height of ( 16 ) meters, including the power distribution box, cables , and RCC foundation. | B2.26 56 19.01
B2.26 56 19.02 | أعمدة أنارة مع ذراع واحد ، إرتفاع 16 متر، تشمل علبة توزيع الطاقة والكوابل، والقاعدة الخرسانية | Unit | 8 |  |  | Lighting poles with single arm, height of ( 16 ) meters, including the power distribution box, cables , and RCC foundation. | B2.26 56 19.02
B2.26 56 19.03 | أعمدة أنارة مع ذراع واحد ، إرتفاع 12 متر، تشمل علبة توزيع الطاقة والكوابل، والقاعدة الخرسانية | Unit | 748 |  |  | Lighting poles with single arm, height of ( 12 ) meters, including the power distribution box, cables , and RCC foundation. | B2.26 56 19.03
26 56 19 | وحدات إنارة الشوارع |  |  |  | 0 | STREET LIGHTING LUMINAIRE | 26 56 19
B2.26.56.19.04 | وحدة إنارة LED نظام اضاءة بمخرج ≥ 50000 lumen كاملة مع جهاز التحكم والمصباح ، (305) واط, 230 فولت, 60 هرتز . | Unit | 70 |  |  | Street Lighting ( LED) Luminaire,of Output≥ 50000 lumen complete with control gear and lamp, 305 WATT, 230 Volt, 60 HZ | B2.26.56.19.04
B2.26.56.19.05 | وحدة إنارة LED نظام اضاءة بمخرج ≥ 26000 lumen كاملة مع جهاز التحكم والمصباح ، (154) واط, 230 فولت, 60 هرتز . | Unit | 214 | 0 |  | Street Lighting ( LED) Luminaire,of Output≥ 26000 lumen complete with control gear and lamp, 154 WATT, 230 Volt, 60 HZ | B2.26.56.19.05
B2.26.56.19.06 | وحدة إنارة LED نظام اضاءة بمخرج ≥ 19000 lumen كاملة مع جهاز التحكم والمصباح ، (114) واط, 230 فولت, 60 هرتز . | Unit | 748 | 0 |  | Street Lighting ( LED) Luminaire,of Output≥ 19000 lumen complete with control gear and lamp, 114 WATT, 230 Volt, 60 HZ | B2.26.56.19.06
26 05 26 | نظام التاريض |  |  |  | 0 | EARTHING SYSTEM | 26 05 26
B2.26 05 26.01 | يشمل تأريض الأعمدة والصوارى وكبائن التغذية ومحطة التوزيع ووحدات الربط الحلقي ومغذيات الجهد المنخفض لدوائر الإنارة وعداد قياس الطاقة. | Unit | 86 |  |  | Including earthing of lighting poles ,masts. feeder pillars , unit substations, RMU, L.V feeders and KWH meter. | B2.26 05 26.01
33 71 19 | عبارات عبور كابلات الطرق |  | 0 |  |  | ROAD CROSSING DUCTS | 33 71 19
B2.33 71 19.04 | عبارة طرق لكابلات إنارة شوارع ذات أثنين منفذ من مواسير بوليفنيل الكلوريد (2x100 مم) | m | 5074 |  |  | Road crossing ducts, 2 way (2 x 100mm PVC) | B2.33 71 19.04
26 24 16 | لوحات الانارة وكبائن التوزيع |  | 0 |  |  | LIGHTING PANELS | 26 24 16
B2.26 24 16.01 | كبائن التوزيع لدوائر الانارة | Unit | 13 |  |  | Street Lighting Feeder pillars | B2.26 24 16.01
B2.26 24 16.02 | توريد وتركيب جدار مع الإطار لتركيب عداد قياس الطاقة من بلوك خرساني حسب معايير ومواصفات الشركة السعودية للكهرباء. | Unit | 5 |  |  | Supply and installation of concrete block wall including the frame and the concrete block wall for installation of KWH meter according to the standards and specifications of SEC. | B2.26 24 16.02
33 71 19.13 | حفر سحب الكابلات |  | 0 |  |  | DRAWPITS | 33 71 19.13
B2.33 71 19.13.01 | حفرة سحب مع غطاء حديد متوسط التحمل بأبعاد 600*600*1000 مم | Unit | 187 |  |  | Drawpit with medium duty steel cover, size 600x600x1000mm | B2.33 71 19.13.01
0
| يتم ترحيل شبكة التوزيع الكهربائية - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO ELECTRICAL DISTRIBUTION NETWORK - COLLECTION
| الاتصالات |  |  |  | 0 | TELECOMMUNICATIONS
33 71 19 | عبارات عبور كابلات الطرق من الخرسانة المسلحة |  |  |  | 0 | ROAD CROSSING REINFORCED CONCRETE ENCASEMENT DUCTS | 33 71 19
B2.33 71 19.05 | عبارات عبور الطريق من المواسير البولي ايثلين 6 خطوط بقطر 50 مم | m | 1700 |  |  | 6 way 50mm HDPE duct | B2.33 71 19.05
33 71 19 | عبارات عبور كابلات الطرق من الخرسانة الغير مسلحة |  | 0 |  |  | UNREINFORCED CONCRETE DUCTS | 33 71 19 | 23380
B2.33 71 19.06 | عبارات عبور الطريق من المواسير البولي ايثلين 6 خطوط بقطر 50 مم | m | 34650 |  |  | 6 way 50mm HDPE duct | B2.33 71 19.06
33 71 19 | العبارات |  | 0 |  |  | DUCTS | 33 71 19 | 370
B2.33 71 19.07 | المواسير من البولي ايثلين 2 خطوط بقطر 32 مم | m | 30590 |  |  | 2 x 32 mm diameter HDPE ducts | B2.33 71 19.07
33 71 19.13 | غرف تفتيش (مانهولات) |  | 0 |  |  | MANHOLES | 33 71 19.13
B2.33.71.19.13.02 | غرفة تقتيش (مانهول) من النوع 1 | nr | 79 |  |  | Manhole type 1 | B2.33.71.19.13.02
B2.33.71.19.13.03 | غرفة تقتيش (مانهول) من النوع 2 | nr | 103 |  |  | Manhole type 2 | B2.33.71.19.13.03
B2.33.71.19.13.04 | غرفة تقتيش (مانهول) من النوع 3 | nr | 2 |  |  | Manhole type 3 | B2.33.71.19.13.04
0
0
0
0
0
0
0
0
0
| يتم ترحيل شبكة التوزيع الكهربائية - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO ELECTRICAL DISTRIBUTION NETWORK - COLLECTION
شبكة مياه الشرب |  |  |  |  | 0 | POTABLE WATER NETWORK
| أعمال المواسير - المواسير |  |  |  | 0 | PIPEWORK-PIPES
33 14 13 | مواسير من البولي إيتلين العالي الكثافة PE 100 SDR 11 (PN 16 Bar) |  |  |  | 0 | High Density Polyethylene pipes PE 100 SDR 11 (PN 16 Bar) | 33 14 13
| قطر 110 مم |  |  |  | 0 | 110mm Diameter
B3.33 14 13.01 | عمق 0 - 1.5 م | m | 51 |  |  | Depth: 0.0m - 1.5m | B3.33 14 13.01 |  | 370
B3.33 14 13.02 | عمق 1.51 - 2.5 م | m | 14 |  |  | Depth: 1.51m - 2.5m | B3.33 14 13.02 |  | 420
B3.33 14 13.03 | عمق اكبر من 2.51 م | m | 10 |  |  | Depth: Greater than 2.51m | B3.33 14 13.03
| قطر 160 مم |  | 0 |  |  | 160mm Diameter
B3.33 14 13.04 | عمق 0 - 1.5 م | m | 4464 |  |  | Depth: 0.0m - 1.5m | B3.33 14 13.04 |  | 370
B3.33 14 13.05 | عمق 1.51 - 2.5 م | m | 633 |  |  | Depth: 1.51m - 2.5m | B3.33 14 13.05 |  | 420
B3.33 14 13.03 | عمق اكبر من 2.51 م | m | 10 |  |  | Depth: Greater than 2.51m | B3.33 14 13.03
| قطر 200 مم |  | 0 |  |  | 200mm Diameter
B3.33 14 13.07 | عمق 0 - 1.5 م | m | 9788 |  |  | Depth: 0.0m - 1.5m | B3.33 14 13.07 | 320
B3.33 14 13.08 | عمق 1.51 - 2.5 م | m | 1416 |  |  | Depth: 1.51m - 2.5m | B3.33 14 13.08 | 350
B3.33 14 13.09 | عمق 2.51 - 3.5 م | m | 71 |  |  | Depth: 2.51m - 3.5m | B3.33 14 13.09 | 380
B3.33 14 13.03 | عمق اكبر من 3.51 م | m | 10 |  |  | Depth: Greater than 3.51m | B3.33 14 13.03
| قطر 250 مم |  | 0 |  |  | 250mm Diameter
B3.33 14 13.11 | عمق 0 - 1.5 م | m | 7254 |  |  | Depth: 0.0m - 1.5m | B3.33 14 13.11 | 320
B3.33 14 13.12 | عمق 1.51 - 2.5 م | m | 1431 |  |  | Depth: 1.51m - 2.5m | B3.33 14 13.12 | 350
B3.33 14 13.13 | عمق 2.51 - 3.5 م | m | 69 |  |  | Depth: 2.51m - 3.5m | B3.33 14 13.13 | 380
B3.33 14 13.14 | عمق اكبر من 3.51 م | m | 10 |  |  | Depth: Greater than 3.51m | B3.33 14 13.14
| يتم ترحيل شبكة مياه الشرب - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO POTABLE WATER NETWORK - COLLECTION
| أعمال المواسير - المواسير |  |  |  | 0 | PIPEWORK-PIPES
| قطر 315 مم |  | 0 |  |  | 315mm Diameter
B3.33 14 13.15 | عمق 0 - 1.5 م | m | 201 |  |  | Depth: 0.0m - 1.5m | B3.33 14 13.15
B3.33 14 13.16 | عمق 1.51 - 2.5 م | m | 151 |  |  | Depth: 1.51m - 2.5m | B3.33 14 13.16
B3.33 14 13.17 | عمق اكبر من 2.51 م | m | 10 |  |  | Depth: Greater than 2.51m | B3.33 14 13.17
| قطر 355 مم |  | 0 |  |  | 355mm Diameter
B3.33 14 13.18 | عمق 0 - 1.5 م | m | 60 |  |  | Depth: 0.0m - 1.5m | B3.33 14 13.18
B3.33 14 13.19 | عمق اكبر من 1.51 م | m | 10 |  |  | Depth: Greater than 1.51m | B3.33 14 13.19
| أعمال المواسير - المواسير |  |  |  | 0 | PIPEWORK-PIPES
33 14 11 | تغليف خرسانية للمواسير |  |  |  | 0 | Pipe Encasements, | 33 14 11
B3.33 14 11.01 | تغليف خرسانية لمواسير قطر 160 مم | m | 289 |  |  | Pipe encasement diameter 160 mm | B3.33 14 11.01
B3.33 14 11.02 | تغليف خرسانية لمواسير قطر 200 مم | m | 562 |  |  | Pipe encasement diameter 200 mm | B3.33 14 11.02
B3.33 14 11.03 | تغليف خرسانية لمواسير قطر 250 مم | m | 553 |  |  | Pipe encasement diameter 250 mm | B3.33 14 11.03
B3.33 14 11.04 | تغليف خرسانية لمواسير قطر 315 مم | m | 7 |  |  | Pipe encasement diameter 315 mm | B3.33 14 11.04
B3.33 14 11.05 | تغليف خرسانية لمواسير قطر 355 مم | m | 60 |  |  | Pipe encasement diameter 355 mm | B3.33 14 11.05
| أعمال المواسير - الصمامات |  |  |  | 0 | PIPEWORK - VALVES
33 14 19 | الصمامات |  |  |  | 0 | Valves | 33 14 19
0 | الصمام البوابي (مدفون) |  |  |  | 0 | Gate (Sluice) valves (Direct buried)
B3.33 14 19.01 | صمام قفل بوابي بقطر 150 مم على خط مواسير بقطر160 مم . | nr | 19 |  |  | Gate valves dia (150) mm on pipe dia (160) mm . | B3.33 14 19.01
B3.33 14 19.02 | صمام قفل بوابي بقطر 200 مم على خط مواسير بقطر200 مم . | nr | 45 |  |  | Gate valves dia (200) mm on pipe dia (200) mm . | B3.33 14 19.02
B3.33 14 19.03 | صمام قفل بوابي بقطر 250 مم على خط مواسير بقطر250 مم . | nr | 39 |  |  | Gate valves dia (250) mm on pipe dia (250) mm . | B3.33 14 19.03
| يتم ترحيل شبكة مياه الشرب - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO POTABLE WATER NETWORK - COLLECTION
| أعمال المواسير - الصمامات |  |  |  | 0 | PIPEWORK - VALVES
33 14 19 | الصمامات |  |  |  | 0 | Valves | 33 14 19
0 | صمامات الفراشة |  |  |  | 0 | Butterfly valves
B3.33 14 19.04 | صمام فراشة بقطر 300 مم على خط مواسير بقطر315 مم . | nr | 2 |  |  | Butterfly valves with dia (300) mm on pipe dia (315) mm . | B3.33 14 19.04
B3.33 14 19.05 | صمام فراشة بقطر 350 مم على خط مواسير بقطر355 مم . | nr | 1 |  |  | Butterfly valves with dia (350) mm on pipe dia (355) mm . | B3.33 14 19.05
0 | صمام التنظيف (الغسيل) |  | 0 |  |  | Wash-out Valves
B3.33 14 19.06 | محابس غسيل بقطر 100 مم على خط مواسير بقطر160 مم . | nr | 2 |  |  | Wash out valve with dia 100 mm on pipe dia (160) mm . | B3.33 14 19.06
B3.33 14 19.07 | محابس غسيل بقطر 100 مم على خط مواسير بقطر200 مم . | nr | 8 |  |  | Wash out valve with dia 100 mm on pipe dia (200) mm . | B3.33 14 19.07
B3.33 14 19.08 | محابس غسيل بقطر 100 مم على خط مواسير بقطر250 مم . | nr | 4 |  |  | Wash out valve with dia 100 mm on pipe dia (250) mm . | B3.33 14 19.08
B3.33 14 19.09 | محابس غسيل بقطر 100 مم على خط مواسير بقطر315 مم . | nr | 2 |  |  | Wash out valve with dia 100 mm on pipe dia (315) mm . | B3.33 14 19.09
0 | صمامات الهواء |  | 0 |  |  | Air Valves
B3.33 14 19.10 | محابس هواء بقطر 50 مم على خط مواسير بقطر 160 مم. | nr | 1 |  |  | Air valves with dia 50 mm on pipe dia (160) mm. | B3.33 14 19.10
B3.33 14 19.11 | محابس هواء بقطر 50 مم على خط مواسير بقطر 200 مم. | nr | 7 |  |  | Air valves with dia 50 mm on pipe dia (200) mm. | B3.33 14 19.11
B3.33 14 19.12 | محابس هواء بقطر 50 مم على خط مواسير بقطر 250 مم. | nr | 5 |  |  | Air valves with dia 50 mm on pipe dia (250) mm. | B3.33 14 19.12
0 | فوهات حريق |  | 0 |  |  | Fire Hydrant
B3.33 14 19.13 | فوهة حريق 3 مخارج (مخرجين قياس 2.5 بوصة ومخرج قياس 4 بوصة) على شكل اسطوانة مفرغة جافة قابلة للإنفصال. | nr | 280 |  |  | 3-outlet fire hydrant (2 x 2.5 inch and 1 x 4.5 inch) in the form of a separate dry vacuum cylinder | B3.33 14 19.13
0
0
0
0
| يتم ترحيل شبكة مياه الشرب - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO POTABLE WATER NETWORK - COLLECTION
0 | أعمال المواسير - غرف تفتيش الصمامات - الأعمال المدنية |  |  |  | 0 | PIPEWORK-Valve chambers - Civil Works
B3.33 14 13 | غرف تفتيش للصمامات |  |  |  | 0 | Valve chambers | B3.33 14 13
B3.33 14 13.01 | غرفة على خط أنبوب بقطر 315 مم | nr | 2 |  |  | Chamber at pipe 315 mm Dia | B3.33 14 13.01
B3.33 14 13.02 | غرفة على خط أنبوب بقطر 355 مم | nr | 1 |  |  | Chamber at pipe 355 mm Dia | B3.33 14 13.02
0 | غرف تفتيش للتنظيف (الغسيل) |  | 0 |  |  | Wash out chambers
B3.33 14 13.03 | غرفة تنظيف على خط مواسير بقطر 160 مم | nr | 2 |  |  | Wash out chamber; on 160 mm dia pipeline | B3.33 14 13.03
B3.33 14 13.04 | غرفة تنظيف على خط مواسير بقطر 200 مم | nr | 8 |  |  | Wash out chamber; on 200 mm dia pipeline | B3.33 14 13.04
B3.33 14 13.05 | غرفة تنظيف على خط مواسير بقطر 250 مم | nr | 4 |  |  | Wash out chamber; on 250 mm dia pipeline | B3.33 14 13.05
B3.33 14 13.06 | غرفة تنظيف على خط مواسير بقطر 315 مم | nr | 2 |  |  | Wash out chamber; on 315 mm dia pipeline | B3.33 14 13.06
0 | غرف صمامات الهواء |  | 0 |  |  | Air Valve chambers
B3.33 14 13.07 | غرفة صمام الهواء على خط مواسير بقطر 160 مم | nr | 1 |  |  | Air valve chamber; on 160 mm dia pipeline | B3.33 14 13.07
B3.33 14 13.08 | غرفة صمام الهواء على خط مواسير بقطر 200 مم | nr | 7 |  |  | Air valve chamber; on 200 mm dia pipeline | B3.33 14 13.08
B3.33 14 13.09 | غرفة صمام الهواء على خط مواسير بقطر 250 مم | nr | 5 |  |  | Air valve chamber; on 250 mm dia pipeline | B3.33 14 13.09
33 71 19 | الوصلات القاطعة للشوارع |  | 0 |  |  | Road Crossing | 33 71 19
B3.33 71 19.01 | وصله HDPE قاطعة للشوارع بقطر 160 مم (تشمل أغطية النهايات, محبس العزل, الخ...) | nr | 93 |  |  | HDPE road croosing with dia 160 mm (Including end cap, isolation valve, etc...) | B3.33 71 19.01
33 05 04 | أعمال الهدم والإزالات |  | 0 |  |  | Demolition works | 33 05 04
B3.33 05 04.01 | إزالة ماسورة قطر 200 مم | nr | 180 |  |  | Removal of Pipe diameter 200 mm | B3.33 05 04.01
B3.33 05 04.02 | إزالة ماسورة قطر 500 مم | nr | 325 |  |  | Removal of Pipe diameter 500 mm | B3.33 05 04.02
0
0
| يتم ترحيل شبكة مياه الشرب - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO POTABLE WATER NETWORK - COLLECTION
شبكة الري |  |  |  |  | 0 |  | TSE NETWORK
0 | أعمال المواسير - المواسير |  |  |  | 0 | PIPEWORK-PIPES
33 31 00 | مواسير من البولي إيتلين العالي الكثافة PE 100 SDR 11 (PN 16 Bar) |  |  |  | 0 | High Density Polyethylene pipes PE 100 SDR 11 ( PN 16 Bar) | 33 31 00
| قطر 110 مم |  |  |  | 0 | 110mm Diameter
B4.33 31 00.01 | عمق 0 - 1.5 م | m | 17946 |  |  | Depth: 0.0m - 1.5m | B4.33 31 00.01
B4.33 31 00.02 | عمق 1.51 - 2.5 م | m | 7162 |  |  | Depth: 1.51m - 2.5m | B4.33 31 00.02
B4.33 31 00.03 | عمق 2.51 - 3.5 م | m | 1426 |  |  | Depth: 2.51m - 3.5m | B4.33 31 00.03
B4.33 31 00.04 | عمق اكبر من 3.51 م | m | 10 |  |  | Depth: Greater than 3.51m | B4.33 31 00.04
| قطر 160 مم |  | 0 |  |  | 160mm Diameter
B4.33 31 00.05 | عمق 0 - 1.5 م | m | 5 |  |  | Depth: 0.0m - 1.5m | B4.33 31 00.05
B4.33 31 00.06 | عمق 1.50 - 2.5 م | m | 305 |  |  | Depth: 1.50m - 2.5m | B4.33 31 00.06
B4.33 31 00.07 | عمق 2.51 - 3.5 م | m | 453 |  |  | Depth: 2.51m - 3.5m | B4.33 31 00.07
B4.33 31 00.08 | عمق اكبر من 3.51 م | m | 10 |  |  | Depth: Greater than 3.51m | B4.33 31 00.08
| قطر 200 مم |  | 0 |  |  | 200mm Diameter
B4.33 31 00.09 | عمق 0 - 1.5 م | m | 85 |  |  | Depth: 0.0m - 1.5m | B4.33 31 00.09
B4.33 31 00.10 | عمق اكبر من 1.51 م | m | 10 |  |  | Depth: Greater than 1.51m | B4.33 31 00.10
32 81 11 | مجاري تمديدات انابيب الري من نوع uPVC من الفئة 4 |  | 0 |  |  | Class 4 uPVC irrigation ducts | 32 81 11
B4.32 81 11.01 | قطر 200 مم | m | 1638 |  |  | Pipe with diameter 200 mm. | B4.32 81 11.01
0
| يتم ترحيل شبكة مياه المعالجة - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO TSE NETWORK - COLLECTION
0 | أعمال المواسير - المواسير |  |  |  | 0 | PIPEWORK-PIPES
B4.33 14 11 | مواسير تغليف خرسانية |  |  |  | 0 | Pipe Encasements, | B4.33 14 11
B4.33 14 11.01 | تغليف خرساني لمواسير قطر 110 مم | m | 1200 |  |  | Pipe encasement dia 110 mm | B4.33 14 11.01
B4.33 14 11.02 | تغليف خرساني لمواسير قطر 160 مم | m | 150 |  |  | Pipe encasement dia 160 mm | B4.33 14 11.02
B4.33 14 11.03 | تغليف خرساني لمواسير قطر 200 مم | m | 20 |  |  | Pipe encasement dia 200 mm | B4.33 14 11.03
0 | أعمال المواسير - الصمامات |  |  |  | 0 | PIPEWORK - VALVES
33 14 19 | الصمامات |  |  |  | 0 | Valves | 33 14 19
0 | الصمام البوابي (مدفون) |  |  |  | 0 | Gate (Sluice) valves (Direct buried)
B4.33 14 19.01 | محابس قفل بوابي بقطر 100 مم على خط مواسير بقطر110 مم . | nr | 81 |  |  | Gate valves dia (100) mm on pipe dia (110) mm . | B4.33 14 19.01
B4.33 14 19.02 | محابس قفل بوابي بقطر 150 مم على خط مواسير بقطر160 مم . | nr | 4 |  |  | Gate valves dia (150) mm on pipe dia (160) mm . | B4.33 14 19.02
B4.33 14 19.03 | محابس قفل بوابي بقطر 200 مم على خط مواسير بقطر200 مم . | nr | 1 |  |  | Gate valves dia (200) mm on pipe dia (200) mm . | B4.33 14 19.03
| صمام التنظيف (الغسيل) |  |  |  | 0 | Wash-out Valves
B4.33 14 19.04 | محابس غسيل بقطر 100 مم على خط مواسير بقطر110 مم . | nr | 9 |  |  | Wash out valve with dia 100 mm on pipe dia (110) mm . | B4.33 14 19.04
| صمامات الهواء |  |  |  |  | Air Valves
B4.33 14 19.05 | محابس هواء بقطر 50 مم على خط مواسير بقطر110 مم . | nr | 9 |  |  | Air valves with dia 50 mm on pipe dia (110) mm . | B4.33 14 19.05
0
0
0
0
0
0
0
0
| يتم ترحيل شبكة مياه المعالجة - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO TSE NETWORK - COLLECTION
B4.33 14 13 | أعمال المواسير - غرف تفتيش الصمامات - الأعمال المدنية |  |  |  | 0 | PIPEWORK-Valve chambers - Civil Works | B4.33 14 13
0 | غرف تفتيش للتنظيف (الغسيل) |  |  |  | 0 | Wash out chambers
B4.33 14 13.01 | غرفة تنظيف على خط مواسير بقطر 110 مم | nr | 9 |  |  | Wash out chamber; on 110 mm dia pipeline | B4.33 14 13.01
0 | غرف صمامات الهواء |  | 0 |  |  | Air Valve chambers
B4.33 14 13.02 | غرفة صمام الهواء على خط مواسير بقطر 110 مم | nr | 9 |  |  | Air valve chamber; on 110 mm dia pipeline | B4.33 14 13.02
32 84 00 | الوصلات القاطعة للشوارع |  | 0 |  |  | Road Crossing | 32 84 00
B4.32 84 00.01 | وصله HDPE قاطعة للشوارع بقطر 110 مم (تشمل أغطية النهايات, محبس العزل, الخ...) | nr | 81 |  |  | HDPE road croosing with dia 110 mm (Including end cap, isolation valve, etc...) | B4.32 84 00.01
32 80 00 | كابلات الري |  | 0 |  |  | Irrigation Cables | 32 80 00
B4.32 80 00.01 | كابل مزدوج مبروم 12 AWG بين الصمامات وأجهزة التحكم ، يجب سحب الكابلات من خلال مواسير 32Ø UPVC و صندوق صمام دائري كل 100 متر للفحص | m | 28200 |  |  | Decoder cables 12 AWG between valves and controllers, The cables shall be pulled through 32Ø UPVC conduit and inspection 10" round valve box every 100 meters, as per standard specification and drawings | B4.32 80 00.01
0
0
0
0
0
0
0
0
0
0
0
0
0
| يتم ترحيل شبكة مياه المعالجة - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO TSE NETWORK - COLLECTION
شبكة الصرف الصحي |  |  |  |  | 0 |  | SEWERAGE NETWORK
| أعمال المواسير - المواسير |  |  |  | 0 | PIPEWORK-PIPES
33 31 00 | مواسير GRP: الصلابة 5000 حتى عمق 3.5 م الصلابة 10000 لأي عمق أكثر من 3.5 م |  |  |  | 0 | Glass Reinforced Plastic (GRP): SN 5000 up to depth 3.5 m SN 10000 depth more than 3.5 m | 33 31 00
| قطر 150 مم |  |  |  | 0 | 150mm Diameter
B5.33 31 00.01 | عمق 0.0 - 1.5 م | m | 2693 |  |  | Depth : 0.0m - 1.5m | B5.33 31 00.01
B5.33 31 00.02 | عمق 1.51 - 2.5 م | m | 1237 |  |  | Depth : 1.51m - 2.5m | B5.33 31 00.02
B5.33 31 00.03 | عمق 2.51 - 3.5 م | m | 131 |  |  | Depth : 2.51m - 3.5m | B5.33 31 00.03
B4.33 31 00.04 | عمق اكبر من 3.51 م | m | 20 |  |  | Depth: Greater than 3.51m | B4.33 31 00.04
| قطر 200 مم |  | 0 |  |  | 200mm Diameter
B5.33 31 00.05 | عمق 0.0 - 1.5 م | m | 4588 |  |  | Depth : 0.0m - 1.5m | B5.33 31 00.05
B5.33 31 00.06 | عمق 1.51 - 2.5 م | m | 4052 |  |  | Depth: 1.51m - 2.5m | B5.33 31 00.06
B5.33 31 00.07 | عمق 2.51 - 3.5 م | m | 1579 |  |  | Depth: 2.51m - 3.5m | B5.33 31 00.07
B5.33 31 00.08 | عمق 3.51 - 4.5 م | m | 446 |  |  | Depth: 3.51m - 4.5m | B5.33 31 00.08
B5.33 31 00.09 | عمق 4.51 - 5.5 م | m | 559 |  |  | Depth: 4.51m - 5.5m | B5.33 31 00.09
B5.33 31 00.10 | عمق اكبر من 5.51 م | m | 10 |  |  | Depth: Greater than 5.51m | B5.33 31 00.10
| قطر 250 مم |  | 0 |  |  | 250mm Diameter
B5.33 31 00.11 | عمق 0.0 - 1.5 م | m | 20 |  |  | Depth : 0.0m - 1.5m | B5.33 31 00.11
B5.33 31 00.12 | عمق 1.51 - 2.5 م | m | 317 |  |  | Depth: 1.51m - 2.5m | B5.33 31 00.12
B5.33 31 00.13 | عمق 2.51 -3.5 م | m | 10 |  |  | Depth: 2.51m - 3.5m | B5.33 31 00.13
B5.33 31 00.14 | عمق 3.51 - 4.5 م | m | 606 |  |  | Depth: 3.51m - 4.5m | B5.33 31 00.14
B5.33 31 00.15 | عمق 4.51 - 5.5 م | m | 528 |  |  | Depth: 4.51m - 5.5m | B5.33 31 00.15
B5.33 31 00.16 | عمق اكبر من 5.51 م | m | 10 |  |  | Depth: Greater than 5.51m | B5.33 31 00.16
| يتم ترحيل شبكة الصرف الصحي - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO SEWERAGE NETWORK - COLLECTION
| أعمال المواسير - المواسير |  |  |  | 0 | PIPEWORK-PIPES
33 31 00 | مواسير GRP: الصلابة 5000 حتى عمق 3.5 م الصلابة 10000 لأي عمق أكثر من 3.5 م |  |  |  | 0 | Glass Reinforced Plastic (GRP): SN 5000 up to depth 3.5 m SN 10000 depth more than 3.5 m | 33 31 00
| قطر 300 مم |  |  |  | 0 | 300mm Diameter
B5.33 31 00.17 | عمق 0.0 - 1.5 م | m | 70 |  |  | Depth: 0.0m - 1.5m | B5.33 31 00.17
B5.33 31 00.18 | عمق 1.50 - 2.5 م | m | 776 |  |  | Depth: 1.50m - 2.5m | B5.33 31 00.18
B5.33 31 00.19 | عمق 2.51 - 3.5 م | m | 733 |  |  | Depth: 2.51m - 3.5m | B5.33 31 00.19
B5.33 31 00.20 | عمق 3.51 - 4.5 م | m | 200 |  |  | Depth: 3.51m - 4.5m | B5.33 31 00.20
B5.33 31 00.21 | عمق 4.51 - 5.5 م | m | 445 |  |  | Depth: 4.51m - 5.5m | B5.33 31 00.21
B5.33 31 00.22 | عمق اكبر من 5.51 م | m | 10 |  |  | Depth: Greater than 5.51m | B5.33 31 00.22
| قطر 400 مم |  | 0 |  |  | 400mm Diameter
B5.33 31 00.23 | عمق 0.0 - 1.5 م | m | 10 |  |  | Depth: 0.0m - 1.5m | B5.33 31 00.23
B5.33 31 00.24 | عمق 1.50 - 2.5 م | m | 10 |  |  | Depth: 1.50m - 2.5m | B5.33 31 00.24
B5.33 31 00.25 | عمق 2.51 - 3.5 م | m | 10 |  |  | Depth: 2.51m - 3.5m | B5.33 31 00.25
B5.33 31 00.26 | عمق 3.50 - 4.5 م | m | 425 |  |  | Depth: 3.50m - 4.5m | B5.33 31 00.26
B5.33 31 00.27 | عمق 4.51 - 5.5 م | m | 612 |  |  | Depth: 4.51m - 5.5m | B5.33 31 00.27
B5.33 31 00.28 | عمق اكبر من 5.51 م | m | 10 |  |  | Depth: Greater than 5.51m | B5.33 31 00.28
| قطر 500 مم |  | 0 |  |  | 500mm Diameter
B5.33 31 00.29 | عمق 0.0 - 1.5 م | m | 10 |  |  | Depth: 0.0m - 1.5m | B5.33 31 00.29
B5.33 31 00.30 | عمق 1.50 - 2.5 م | m | 10 |  |  | Depth: 1.50m - 2.5m | B5.33 31 00.30
B5.33 31 00.31 | عمق 2.51 - 3.5 م | m | 10 |  |  | Depth: 2.51m - 3.5m | B5.33 31 00.31
B5.33 31 00.32 | عمق 3.51 - 4.5 م | m | 924 |  |  | Depth: 3.51m - 4.5m | B5.33 31 00.32
B5.33 31 00.33 | عمق اكبر من 5.51 م | m | 10 |  |  | Depth: Greater than 5.51m | B5.33 31 00.33
| يتم ترحيل شبكة الصرف الصحي - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO SEWERAGE NETWORK - COLLECTION
| أعمال المواسير - المواسير |  |  |  | 0 | PIPEWORK-PIPES
33 31 00 | مواسير GRP: الصلابة 5000 حتى عمق 3.5 م الصلابة 10000 لأي عمق أكثر من 3.5 م |  |  |  | 0 | Glass Reinforced Plastic (GRP): SN 5000 up to depth 3.5 m SN 10000 depth more than 3.5 m | 33 31 00
| قطر 600 مم |  | 0 |  |  | 600mm Diameter
B5.33 31 00.34 | عمق 2.51 - 3.5 م | m | 98 |  |  | Depth: 2.51m - 3.5m | B5.33 31 00.34
B5.33 31 00.35 | عمق 3.51 - 4.5 م | m | 392 |  |  | Depth: 3.51m - 4.5m | B5.33 31 00.35
B5.33 31 00.36 | عمق 4.51 - 5.5 م | m | 372 |  |  | Depth: 4.51m - 5.5m | B5.33 31 00.36
B5.33 31 00.37 | عمق 5.51 - 6.5 م | m | 373 |  |  | Depth: 5.51m - 6.5m | B5.33 31 00.37
B5.33 31 00.38 | عمق اكبر من 6.51 م | m | 10 |  |  | Depth: Greater than 6.51m | B5.33 31 00.38
| أعمال المواسير - المانهولات وملحقات أعمال المواسير |  |  |  | 0 | PIPEWORK ANCILLARIES
33 05 13 | غرف المانهولات |  |  |  | 0 | Manholes | 33 05 13
| غرف مانهولات (مطابق) بقطر داخلى 1200 مم |  |  |  | 0 | Precast Manhole ring 1200 mm internal dia.
B5.33 05 13.01 | مانهول بعمق 0-1.5 م | nr | 87 |  |  | MH depth 0 - 1.5m | B5.33 05 13.01
B5.33 05 13.02 | مانهول بعمق 1.51-2.5 م | nr | 113 |  |  | MH depth 1.51 - 2.5m | B5.33 05 13.02
B5.33 05 13.03 | مانهول بعمق 1.51-2.5 م مع سقوط خلفي | nr | 2 |  |  | MH depth 1.51 - 2.5m with back drop | B5.33 05 13.03
B5.33 05 13.04 | مانهول بعمق 2.51-3.5 م | nr | 45 |  |  | MH depth 2.51 - 3.5m | B5.33 05 13.04
B5.33 05 13.05 | مانهول بعمق 2.51-3.5 م مع سقوط خلفي | nr | 21 |  |  | MH depth 2.51 - 3.5m with back drop | B5.33 05 13.05
B5.33 05 13.06 | مانهول بعمق 3.51-4.5 م | nr | 11 |  |  | MH depth 3.51 -4.5m | B5.33 05 13.06
B5.33 05 13.07 | مانهول بعمق 3.51-4.5 م مع سقوط خلفي | nr | 14 |  |  | MH depth 3.51 -4.5m with back drop | B5.33 05 13.07
B5.33 05 13.08 | مانهول بعمق 4.51-5.5 م | nr | 25 |  |  | MH depth 4.51 -5.5m | B5.33 05 13.08
B5.33 05 13.09 | مانهول بعمق 4.51-5.5 م مع سقوط خلفي | nr | 18 |  |  | MH depth 4.51 -5.5m with back drop | B5.33 05 13.09
B5.33 05 13.10 | مانهول بعمق 5.51-6.5 م | nr | 2 |  |  | MH depth 5.51 -6.5m | B5.33 05 13.10
B5.33 05 13.11 | مانهول بعمق 5.51-6.5 م مع سقوط خلفي | nr | 3 |  |  | MH depth 5.51 -6.5m with back drop | B5.33 05 13.11
B5.33 05 13.12 | مانهول بعمق 6.51-7.5 م | nr | 1 |  |  | MH depth 6.51 -7.5m | B5.33 05 13.12
| غرف مانهولات (مطابق) بقطر داخلى 1600 مم |  | 0 |  |  | Precast Manhole ring 1600 mm internal dia.
B5.33 05 13.13 | مانهول بعمق 5.51-6.5 م | nr | 1 |  |  | MH depth 5.51 -6.5m | B5.33 05 13.13
B5.33 05 13.14 | مانهول بعمق 6.51-7.5 م | nr | 1 |  |  | MH depth 6.51 -7.5m | B5.33 05 13.14
| يتم ترحيل شبكة الصرف الصحي - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO SEWERAGE NETWORK - COLLECTION
شبكة صرف مياه الأمطار |  |  |  |  | 0 |  | STORM WATER DRAINAGE NETWORK
0 | الفئة (I): أعمال المواسير - المواسير |  |  |  | 0 | CLASS I: PIPEWORK-PIPES
33 42 11 | المواسير الدائرية (GRP) |  |  |  | 0 | Circular pipes (GRP) | 33 42 11
0 | مواسير GRP: الصلابة 5000 حتى عمق 3.5 م الصلابة 10000 لأي عمق أكثر من 3.5 م |  |  |  | 0 | Glass Reinforced Plastic (GRP): SN 5000 up to depth 3.5 m SN 10000 depth more than 3.5 m
0 | قطر 400 مم |  |  |  | 0 | 400mm Diameter
B6.33 42 11.01 | عمق 0 - 1.5 م | m | 10430 |  |  | Depth: 0.0m - 1.5m | B6.33 42 11.01
B6.33 42 11.02 | عمق 1.51 - 2.5 م | m | 1715 |  |  | Depth : 1.51m - 2.5m | B6.33 42 11.02
B6.33 42 11.03 | عمق 2.51 - 3.5 م | m | 180 |  |  | Depth : 2.51m - 3.5m | B6.33 42 11.03
B6.33 42 11.04 | عمق 3.51 - 4.5 م | m | 275 |  |  | Depth: 3.51m - 4.5m | B6.33 42 11.04
B5.33 31 00.05 | عمق اكبر من 4.51 م | m | 15 |  |  | Depth: Greater than 4.51m | B5.33 31 00.05
0 | قطر 500 مم |  | 0 |  |  | 500mm Diameter
B6.33 42 11.06 | عمق 0 - 1.5 م | m | 750 |  |  | Depth: 0.0m - 1.5m | B6.33 42 11.06
B6.33 42 11.07 | عمق 1.51 - 2.5 م | m | 165 |  |  | Depth : 1.51m - 2.5m | B6.33 42 11.07
B6.33 42 11.08 | عمق 2.51 - 3.5 م | m | 55 |  |  | Depth : 2.51m - 3.5m | B6.33 42 11.08
B6.33 42 11.09 | عمق 3.51 - 4.5 م | m | 190 |  |  | Depth: 3.51m - 4.5m | B6.33 42 11.09
B6.33 42 11.10 | عمق اكبر من 4.51 م | m | 15 |  |  | Depth: Greater than 4.51m | B6.33 42 11.10
0 | قطر 600 مم |  | 0 |  |  | 600mm Diameter
B6.33 42 11.11 | عمق 0 - 1.5 م | m | 590 |  |  | Depth: 0.0m - 1.5m | B6.33 42 11.11
B6.33 42 11.12 | عمق 1.51 - 2.5 م | m | 1710 |  |  | Depth : 1.51m - 2.5m | B6.33 42 11.12
B6.33 42 11.13 | عمق 2.51 - 3.5 م | m | 360 |  |  | Depth : 2.51m - 3.5m | B6.33 42 11.13
B6.33 42 11.14 | عمق اكبر من 3.51 م | m | 15 |  |  | Depth: Greater than 3.51m | B6.33 42 11.14
0 | يتم ترحيل شبكة صرف مياه الأمطار - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO STORMWATER NETWORK - COLLECTION
33 42 11 | المواسير الدائرية (GRP) |  |  |  | 0 | Circular pipes (GRP) | 33 42 11
0 | مواسير GRP: الصلابة 5000 حتى عمق 3.5 م الصلابة 10000 لأي عمق أكثر من 3.5 م |  |  |  | 0 | Glass Reinforced Plastic (GRP): SN 5000 up to depth 3.5 m SN 10000 depth more than 3.5 m
0 | قطر 700 مم |  | 0 |  |  | 700mm Diameter
B6.33 42 11.15 | عمق 0 - 1.5 م | m | 10 |  |  | Depth: 0.0m - 1.5m | B6.33 42 11.15
B6.33 42 11.16 | عمق 1.5 - 2.5 م | m | 460 |  |  | Depth: 1.50m - 2.5m | B6.33 42 11.16
B6.33 42 11.17 | عمق 2.51 - 3.5 م | m | 190 |  |  | Depth : 2.51m - 3.5m | B6.33 42 11.17
B6.33 42 11.18 | عمق اكبر من 3.51 م | m | 15 |  |  | Depth: Greater than 3.51m | B6.33 42 11.18
0 | قطر 800 مم |  |  |  | 0 | 800mm Diameter
B6.33 42 11.19 | عمق 0 - 1.5 م | m | 10 |  |  | Depth: 0.0m - 1.5m | B6.33 42 11.19
B6.33 42 11.20 | عمق 1.50 - 2.5 م | m | 1405 |  |  | Depth : 1.50m - 2.5m | B6.33 42 11.20
B6.33 42 11.21 | عمق 2.51 - 3.5 م | m | 400 |  |  | Depth : 2.51m - 3.5m | B6.33 42 11.21
B6.33 42 11.22 | عمق اكبر من 3.51 م | m | 15 |  |  | Depth: Greater than 3.51m | B6.33 42 11.22
0 | قطر 900 مم |  | 0 |  |  | 900mm Diameter
B6.33 42 11.23 | عمق 0 - 1.5 م | m | 10 |  |  | Depth: 0.0m - 1.5m | B6.33 42 11.23
B6.33 42 11.24 | عمق 1.50 - 2.5 م | m | 625 |  |  | Depth : 1.50m - 2.5m | B6.33 42 11.24
B6.33 42 11.25 | عمق 2.50 - 3.5 م | m | 180 |  |  | Depth : 2.50m - 3.5m | B6.33 42 11.25
B6.33 42 11.26 | عمق اكبر من 3.51 م | m | 15 |  |  | Depth: Greater than 3.51m | B6.33 42 11.26
0 | يتم ترحيل شبكة صرف مياه الأمطار - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO STORMWATER NETWORK - COLLECTION
33 42 11 | المواسير الدائرية (GRP) |  |  |  | 0 | Circular pipes (GRP) | 33 42 11
0 | مواسير GRP: الصلابة 5000 حتى عمق 3.5 م الصلابة 10000 لأي عمق أكثر من 3.5 م |  |  |  | 0 | Glass Reinforced Plastic (GRP): SN 5000 up to depth 3.5 m SN 10000 depth more than 3.5 m
0 | قطر 1000 مم |  | 0 |  |  | 1000mm Diameter
B6.33 42 11.27 | عمق 0 - 1.5 م | m | 10 |  |  | Depth: 0.0m - 1.5m | B6.33 42 11.27
B6.33 42 11.28 | عمق 1.50 - 2.5 م | m | 10 |  |  | Depth : 1.50m - 2.5m | B6.33 42 11.28
B6.33 42 11.29 | عمق 2.51 - 3.5 م | m | 620 |  |  | Depth : 2.51m - 3.5m | B6.33 42 11.29
B6.33 42 11.30 | عمق 3.51 - 4.5 م | m | 65 |  |  | Depth: 3.51m - 4.5m | B6.33 42 11.30
B6.33 42 11.31 | عمق اكبر من 4.51 م | m | 15 |  |  | Depth: Greater than 4.51m | B6.33 42 11.31
0 | قطر 1200 مم |  | 0 |  |  | 1200mm Diameter
B6.33 42 11.32 | عمق 0 - 1.5 م | m | 10 |  |  | Depth: 0.0m - 1.5m | B6.33 42 11.32
B6.33 42 11.33 | عمق 1.50 - 2.5 م | m | 100 |  |  | Depth : 1.50m - 2.5m | B6.33 42 11.33
B6.33 42 11.34 | عمق 2.51 - 3.5 م | m | 1000 |  |  | Depth: 2.51m - 3.5m | B6.33 42 11.34
B6.33 42 11.35 | عمق 3.51 - 4.5 م | m | 250 |  |  | Depth: 3.51m - 4.5m | B6.33 42 11.35
B6.33 42 11.36 | عمق 4.51 - 5.5 م | m | 315 |  |  | Depth: 4.51m - 5.5m | B6.33 42 11.36
B6.33 42 11.37 | عمق اكبر من 5.51 م | m | 15 |  |  | Depth: Greater than 5.51m | B6.33 42 11.37
0
0 | يتم ترحيل شبكة صرف مياه الأمطار - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO STORMWATER NETWORK - COLLECTION
33 42 11 | المواسير الدائرية (uPVC) |  |  |  | 0 | Circular pipes (uPVC) | 33 42 11
0 | مواسير من البلاستك ( uPVC) من الفئة 4 لزوم مصائد الأمطار |  |  |  | 0 | Class 4 uPVC For catch basins
0 | قطر 300 مم |  |  |  | 0 | 300mm Diameter
B6.33 42 11.38 | عمق 0 - 1.5 م | m | 12550 |  |  | Depth: 0.0m - 1.5m | B6.33 42 11.38
0 | قطر 400 مم |  | 0 |  |  | 400mm Diameter
B6.33 42 11.39 | عمق 0 - 1.5 م | m | 840 |  |  | Depth: 0.0m - 1.5m | B6.33 42 11.39
0 | الفئة (K): أعمال المواسير - المانهولات (مطابق) وملحقات أعمال المواسير |  |  |  | 0 | CLASS K: PIPEWORK-MANHOLES AND PIPEWORK ANCILLARIES
33 05 39 | مانهولات من الخرسانة لدخول المياه |  |  |  | 0 | Inlet Manholes | 33 05 39
0 | مانهول دائري بقطر داخلي 1200 مم |  |  |  | 0 | Precast Manhole ring 1200 mm internal dia.
B6.33 05 39.01 | مانهول بعمق 1.50-2.5 م | nr | 117 |  |  | MH depth 1.50 - 2.5m | B6.33 05 39.01
B6.33 05 39.02 | مانهول بعمق 1.50-2.5 م مع سقوط خلفي | nr | 25 |  |  | MH depth 1.50 - 2.5m With backdrop | B6.33 05 39.02
B6.33 05 39.03 | مانهول بعمق 2.51-3.5 م | nr | 16 |  |  | MH depth 2.51 - 3.5m | B6.33 05 39.03
B6.33 05 39.04 | مانهول بعمق 2.51-3.5 م مع سقوط خلفي | nr | 10 |  |  | MH depth 2.51 - 3.5m With backdrop | B6.33 05 39.04
B6.33 05 39.05 | مانهول بعمق 3.51-4.5 م | nr | 1 |  |  | MH depth 3.51 - 4.5m | B6.33 05 39.05
B6.33 05 39.06 | مانهول بعمق 3.51-4.5 م مع سقوط خلفي | nr | 1 |  |  | MH depth 3.51 - 4.5m With backdrop | B6.33 05 39.06
B6.33 05 39.07 | مانهول بعمق 4.51-5.5 م | nr | 2 |  |  | MH depth 4.51 - 5.5m | B6.33 05 39.07
B6.33 05 39.08 | مانهول بعمق 4.51-5.5 م مع سقوط خلفي | nr | 1 |  |  | MH depth 4.51 - 5.5m With backdrop | B6.33 05 39.08
B6.33 05 39.09 | مانهول بعمق اكبر من 5.51 م | nr | 1 |  |  | MH depth greater than 5.51m | B6.33 05 39.09
0
0 | يتم ترحيل شبكة صرف مياه الأمطار - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO STORMWATER NETWORK - COLLECTION
0 | الفئة (K): أعمال المواسير - المانهولات (مطابق) وملحقات أعمال المواسير |  |  |  | 0 | CLASS K: PIPEWORK-MANHOLES AND PIPEWORK ANCILLARIES
33 05 39 | مانهولات من الخرسانة لدخول المياه |  |  |  | 0 | Inlet Manholes | 33 05 39
0 | مانهول دائري بقطر داخلي 1200 مم بغطاء شبكي |  | 0 |  |  | Precast Manhole ring 1200 mm internal dia. With grated cover
B6.33 05 39.10 | مانهول بعمق 1.50-2.5 م | nr | 18 |  |  | MH depth 1.50 - 2.5m | B6.33 05 39.10
B6.33 05 39.11 | مانهول بعمق 3.50-4.5 م | nr | 1 |  |  | MH depth 3.50 - 4.5m | B6.33 05 39.11
0 | مانهول دائري بقطر داخلي 1500 مم |  | 0 |  |  | Precast Manhole ring 1500 mm internal dia.
B6.33 05 39.12 | مانهول بعمق 1.5-2.5 م | nr | 5 |  |  | MH depth 1.5 - 2.5m | B6.33 05 39.12
B6.33 05 39.13 | مانهول بعمق 2.51-3.5 م | nr | 16 |  |  | MH depth 2.51 - 3.5m | B6.33 05 39.13
B6.33 05 39.14 | مانهول بعمق 2.51-3.5 م مع سقوط خلفي | nr | 12 |  |  | MH depth 2.51 - 3.5m With backdrop | B6.33 05 39.14
B6.33 05 39.15 | مانهول بعمق 3.51-4.5 م | nr | 1 |  |  | MH depth 3.51 - 4.5m | B6.33 05 39.15
B6.33 05 39.16 | مانهول بعمق 3.51-4.5 م مع سقوط خلفي | nr | 2 |  |  | MH depth 3.51 - 4.5m With backdrop | B6.33 05 39.16
0 | مانهول دائري بقطر داخلي 2000 مم |  | 0 |  |  | Precast Manhole ring 2000 mm internal dia.
B6.33 05 39.17 | مانهول بعمق 2.5-3.5 م | nr | 5 |  |  | MH depth 2.51 - 3.5m | B6.33 05 39.17
B6.33 05 39.18 | مانهول بعمق 2.51-3.5 م مع سقوط خلفي | nr | 1 |  |  | MH depth 2.51 - 3.5m With backdrop | B6.33 05 39.18
B6.33 05 39.19 | مانهول بعمق 3.51-4.5 م | nr | 5 |  |  | MH depth 3.51 - 4.5m | B6.33 05 39.19
B6.33 05 39.20 | مانهول بعمق 3.51-4.5 م مع سقوط خلفي | nr | 11 |  |  | MH depth 3.51 - 4.5m With backdrop | B6.33 05 39.20
B6.33 05 39.22 | مانهول بعمق 4.51-5.5 م | nr | 1 |  |  | MH depth 4.51 - 5.5m | B6.33 05 39.22
B6.33 05 39.23 | مانهول بعمق 4.51-5.5 م مع سقوط خلفي | nr | 2 |  |  | MH depth 4.51 - 5.5m With backdrop | B6.33 05 39.23
B6.33 05 39.24 | مانهول بعمق 5.51-6.5 م | nr | 2 |  |  | MH depth 5.51 - 6.5m | B6.33 05 39.24
B6.33 05 39.25 | مانهول بعمق 5.51-6.5 م مع سقوط خلفي | nr | 2 |  |  | MH depth 5.51 - 6.5m With backdrop | B6.33 05 39.25
0 | يتم ترحيل شبكة صرف مياه الأمطار - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO STORMWATER NETWORK - COLLECTION
0 | الفئة (K): أعمال المواسير - المانهولات (مطابق) وملحقات أعمال المواسير |  |  |  | 0 | CLASS K: PIPEWORK-MANHOLES AND PIPEWORK ANCILLARIES
0 | فتحات الدخول أعلي الأنابيب الصندوقية |  |  |  | 0 | Access Opening above the Box coduits
B6.33 05 39.27 | فتحة بأبعاد داخلية 1000*1000 مم وعلي أعماق مختلفة | nr | 31 |  |  | Access opening with dimensions1000*1000 mm at variable depth | B6.33 05 39.27
0 | مانهول مربع الشكل بأبعاد داخلية 3000* 3000 مم |  |  |  |  | Precast Manholes internal diminsion 3000 * 3000 mm
B6.33 05 39.28 | مانهول بعمق 3.0 -4.0 م | nr | 2 |  |  | MH depth 3.0 - 4.0m | B6.33 05 39.28
0 | مصائد الأمطار |  |  |  |  | Concrete catch basin
B6.33 05 39.29 | أحواض تجميع مياه الأمطار Single Catch Basins | nr | 521 |  |  | Single Catch basin | B6.33 05 39.29
B6.33 05 39.30 | أحواض تجميع مياه الأمطار Double Catch Basins | nr | 97 |  |  | Double Catch basin | B6.33 05 39.30
33 42 16 | عبارات/علب صندوقية من الخرسانة الجاهزة وتشمل حوائط التوجيه |  |  |  |  | Precast Concrete Box Culverts/Conduits including the wing walls | 33 42 16
B6.03 30 00.01 | خرسانة عادية للعبارات الصندوقية | m3 | 1020 |  | 0 | Plain Concrete for box culvert | B6.03 30 00.01
B6.03 30 00.02 | خرسانة مسلحة للعبارات الصندوقية شاملة أعمال العزل البيتوميني (يتم قياس حديد التسليح في بند منفصل) | m3 | 10225 |  | 0 | Reinforced Concrete for box culvert including bitumenous coating (Steel Reinforcement is measured separately) | B6.03 30 00.02
B6.03 30 00.03 | حديد تسليح للعبارات الصندوقية وفقا للمخططات وحسب توجيهات المهندس المشرف. | ton | 1015 |  |  | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | B6.03 30 00.03
0 | المصبات الخرسانية |  |  |  |  | Concrete Outfalls
B6.33 05 39.30 | هيكل المصب الخرساني | nr | 1 |  |  | Concrete Outfall structure | B6.33 05 39.30
0 | المدخل الخرساني |  |  |  |  | Concrete inlets
B6.33 05 39.31 | هيكل المدخل الخرساني | nr | 1 |  |  | Concrete inlet structure | B6.33 05 39.31
B6.31 22 00 | ساتر ترابي |  |  |  |  | Dike | B6.31 22 00
B6.31 22 00.01 | ردميات من مواد طبيعيه كما هو موضح بالرسومات. | m³ | 1200 |  |  | Natural ground compacted soil as showin in drawings. | B6.31 22 00.01
B6.31 22 00.02 | أعمال التكسية الحجرية (Grouted Riprap) بسمك لا يقل عن 0.3 م كما هو موضح بالرسومات . | m² | 880 |  |  | Grouted Riprap for protection with thick 0.3 m minimum as shown in drawings. | B6.31 22 00.02
0 |  |  |  |  | 0
0 | يتم ترحيل شبكة صرف مياه الأمطار - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO STORMWATER NETWORK - COLLECTION
B6.31 22 00 | قنوات الصرف المكشوف |  |  |  | 0 | OPEN CHANNEL | B6.31 22 00
B6.31 22 00.01 | إزالة أعمال التدبيش لقاع القناة القائمه | m² | 800 |  |  | Demolition works for the riprap at the existing channel | B6.31 22 00.01
B6.31 22 00.02 | حفريات القنوات السطحية المفتوحة لتصريف الأمطار في جميع أنواع التربة لمختلف الأعماق متضمناً أعمال تسوية وتجهيز السطح بعد الحفر والتخلص من ناتج الحفر | m³ | 2130 |  |  | Channel excavation in all type of soil for any depth including levelling, compaction and disposal of surplus material | B6.31 22 00.02
B6.31 22 00.03 | ردميات من مواد طبيعيه لزوم أرضيه القناه كما هو موضح بالرسومات. | m³ | 16515 |  |  | Natural ground compacted soil for bed as showin in drawings. | B6.31 22 00.03
B6.31 22 00.04 | أعمال التكسية الحجرية (Grouted Riprap) لأسطح القنوات المفتوحة بسمك لا يقل عن 0.3 م كما هو موضح بالرسومات . | m² | 25700 |  |  | Grouted Riprap for protection with thick 0.3 m minimum as shown in drawings. | B6.31 22 00.04
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| يتم ترحيل شبكة صرف مياه الأمطار - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO STORMWATER NETWORK - COLLECTION
أعمال الري والمناظر الطبيعة |  |  |  |  | 0 |  | LANDSCAPE AND IRRIGATION WORKS
| أعمال المناظر الطبيعة |  |  |  | 0 | LANDSCAPE WORKS
| النباتات |  |  |  | 0 | PLANTS
| توريد وزراعة الأشجار والنباتات بما في ذلك أعمال الموقع وأعمال التربة الزراعية |  |  |  | 0 | Supply and planting the trees and plants; including site preparation, agricultural soil
32 92 00 | غطاء التربة |  |  |  | 0 | GROUND COVER AND SHRUBS | 32 92 00
B7.32 92 00.01 | لانتانا مونتيفيديويه | m2 | 8414 |  |  | Lantana montevidensis | B7.32 92 00.01
B7.32 92 00.02 | رجلة الزهور | m2 | 6841 |  |  | Portulaca grandiflora | B7.32 92 00.02
B7.32 92 00.03 | دودونيا فيسكوزا | m2 | 8414 |  |  | Dodonaea viscosa | B7.32 92 00.03
B7.32 92 00.04 | الرغل الملحي | m2 | 6887 |  |  | Atriplex halimus | B7.32 92 00.04
32 93 00 | الأشجار والنخيل |  | 0 |  |  | Trees/ Palms | 32 93 00
B7.32 93 00.01 | شجر جوانب الطريق - شجر المخيط | nr | 252 |  |  | Roadside tree - Cordia sebestena | B7.32 93 00.01
B7.32 93 00.02 | شجر جوانب الطريق - شجر الباركنسونية الحاده | nr | 150 |  |  | Roadside tree - Parkinsonia aculeata | B7.32 93 00.02
B7.32 93 00.03 | شجر جوانب الطريق - شجر السيسام | nr | 157 |  |  | Roadside tree - Dalbergia sissoo | B7.32 93 00.03
B7.32 93 00.04 | شجر جوانب الطريق - شجر أكاسيا أستنوفيلا | nr | 156 |  |  | Roadside tree - Acacia stenophylla | B7.32 93 00.04
B7.32 93 00.05 | شجر جوانب الطريق - شجر الخطمي الساحلي | nr | 598 |  |  | Roadside tree - Hibiscus tiliaceus | B7.32 93 00.05
B7.32 93 00.06 | شجر جوانب الطريق - شجر النيم | nr | 260 |  |  | Roadside tree - Azadirachta indica | B7.32 93 00.06
0
0
0
0
0
0
0
| يتم ترحيل أعمال الري والمناظر الطبيعة - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO LANDSCAPE AND IRRIGATION WORKS - COLLECTION
32 93 34 | بنود متنوعة لأعمال التشجير: |  |  |  | 0 | Miscellaneous landscaping items | 32 93 34
B7.32 93 34.01 | توريد وإنشاء بلاطات خرسانية مسبقة الصب 200*200*60 مم للأرصفة بلون بيج متنوع وتشطيب أملس | m2 | 102460 |  |  | Supply and install Precast concrete block paving for sidewalk, mixed grey colour (light grey + mid grey + dark grey), 200 x 200 x 60mm with shot blasted finish. | B7.32 93 34.01
B7.32 93 34.02 | توريد وإنشاء بلاطات خرسانية مسبقة الصب 200*200*60 مم للتقاطعات بلون بيج فاتح وتشطيب أملس | m2 | 9120 |  |  | Supply and install Precast concrete block paving for main intrsection, colour light grey, 200 x 200 x 60mm with shot blasted finish. | B7.32 93 34.02
B7.32 93 34.03 | توريد وإنشاء بلاطات خرسانية مسبقة الصب 200*200*60 مم للتقاطعات بلون بيج متوسط وتشطيب أملس | m2 | 7150 |  |  | Supply and install Precast concrete block paving for main intrsection, colour mid grey, 200 x 200 x 60mm with shot blasted finish. | B7.32 93 34.03
B7.32 93 34.04 | توريد وإنشاء بلاطات خرسانية مسبقة الصب 200*200*60 مم للتقاطعات بلون بيج غامق متنوع وتشطيب أملس | m2 | 5878 |  |  | Supply and install Precast concrete block paving for main intrsection, colour dark grey, 200 x 200 x 60mm with shot blasted finish. | B7.32 93 34.04
B7.32 93 34.05 | الحصى الصغير: في حجم من 30 - 50 مم كحد أقصى، لون بيج فاتح ومتوسط وغامق، بسمك 70مم | m2 | 13879 |  |  | Gravel, mixed dark beige + medium beige + light beige, 30 - 50mm dia., laid 70mm deep | B7.32 93 34.05
B7.32 93 34.06 | بردورة من الخرسانة 300*500*100 مم (احواض الزراعه والمسطحات الخضراء) تلصق بمونة الأسمنت والرمل سمك 20 مم على فرشة تأسيس من الخرسانة العادية 300مم بسمك 100 مم. وكل الأعمال اللازمة طبقا للمخططات والمواصفات (C01). | m | 91270 |  |  | 300 x 500 x 100 mm concrete heel kerb (shrubs & groundcovers planting bed, sidewalk edge) set on 20 mm thick mortar setting bed on 300mm width, 100mm thick. Plain concrete bed and all the related works as per drawings and specification (C01). | B7.32 93 34.06
| شبكة الري الفرعيه |  | 0 |  |  | SECONDARY IRRIGATION
33 14 11 | مواسير بولي اثيلين عالي الكثافة للشبكة الثانوية |  | 0 |  |  | High Density Polyethylene pipes for secondary network | 33 14 11
B7.33.14.11.01 | مواسير قطر 90 مم عمق 0 إلى 1.5 م - 10 بار | m | 6 |  |  | Pipe line O.D 90 mm PN 10, in depth 0 to 1.5 m | B7.33.14.11.01
B7.33.14.11.02 | مواسير قطر 75 مم عمق 0 إلى 1.5 م - 10 بار | m | 187 |  |  | Pipe line O.D 75 mm PN 10, in depth 0 to 1.5 m | B7.33.14.11.02
B7.33.14.11.03 | مواسير قطر 63 مم عمق 0 إلى 1.5 م - 10 بار | m | 1074 |  |  | Pipe line O.D 63 mm PN 10, in depth 0 to 1.5 m | B7.33.14.11.03
B7.33.14.11.04 | مواسير قطر 50 مم عمق 0 إلى 1.5 م - 10 بار | m | 10129 |  |  | Pipe line O.D 50 mm PN 10, in depth 0 to 1.5 m | B7.33.14.11.04
B7.33.14.11.05 | مواسير قطر32 مم عمق 0 إلى 1.5 م - 10 بار | m | 35599 |  |  | Pipe line O.D 32 mm PN 10, in depth 0 to 1.5 m | B7.33.14.11.05
0
0
0
0
| يتم ترحيل أعمال الري والمناظر الطبيعة - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO LANDSCAPE AND IRRIGATION WORKS - COLLECTION
33 14 19 | التصميم التفصيلي وتوريد وتركيب (بما في ذلك توصيلات الكهرباء والتحكم وبرمجة الأنظمة) واختبار وتهيئة وضمان 18 شهر لشبكة الري ومكوناتها، حسب المخططات ومواصفات المصنع المعتمد والموافقة النهائية من مدن على المواصفات |  |  |  | 0 | Design, Delive, install, wiring, control, programming, testing, commissioning, start-up, 18 months guarantee and warrantee of complete irrigation system as per the design and the specifications of the approved supplier (specifications and materials subject to approval of MODON) | 33 14 19
B7.33.14.19.01 | توريد وتركيب محبس سولينويد بمنظم ضغط ( 1") داخل صندوق PVC يشمل جميع الملحقات من ( وحدة تنظيم الضغط، ومناسب لمياه TSE، وفلتر ، , ومحبس بوابي يدوي، وصندوق الصمام مع الغطاء، وجميع الملحقات الأخرى اللازمة لإكمال الأعمال وفقًا للمواصفات والرسومات.) | nr | 5 |  |  | Supply and installation of Electrical Solenoid Valve ( 1") inside PVC box with all accessories( pressure regulator module, manual bleeding, expedient for TSE water, in line filter, manual valve, valve box with cover, and all other accessories necessary to complete the works in accordance with specification and drawings.) | B7.33.14.19.01
B7.33.14.19.02 | توريد وتركيب محبس سولينويد بمنظم ضغط ( 1.5") داخل صندوق PVC يشمل جميع الملحقات من ( وحدة تنظيم الضغط، ومناسب لمياه TSE، وفلتر ، , ومحبس بوابي يدوي، وصندوق الصمام مع الغطاء، وجميع الملحقات الأخرى اللازمة لإكمال الأعمال وفقًا للمواصفات والرسومات.) | nr | 59 |  |  | Supply and installation of Electrical Solenoid Valve ( 1.5") inside PVC box with all accessories( pressure regulator module, manual bleeding, expedient for TSE water, in line filter, manual valve, valve box with cover, and all other accessories necessary to complete the works in accordance with specification and drawings.) | B7.33.14.19.02
B7.33.14.19.03 | توريد وتركيب محبس سولينويد بمنظم ضغط ( 2") داخل صندوق PVC يشمل جميع الملحقات من ( وحدة تنظيم الضغط، ومناسب لمياه TSE، وفلتر ، , ومحبس بوابي يدوي، وصندوق الصمام مع الغطاء، وجميع الملحقات الأخرى اللازمة لإكمال الأعمال وفقًا للمواصفات والرسومات.) | nr | 14 |  |  | Supply and installation of Electrical Solenoid Valve ( 2") inside PVC box with all accessories ( pressure regulator module, manual bleeding, flow control, expedient for TSE water, in line filter, manual valve, valve box with cover, and all other accessories necessary to complete the works in accordance with specification and drawings.) | B7.33.14.19.03
B7.33.14.19.04 | وصلة ربط سريع مقاس 1 بوصة داخل صندوق PVC | nr | 63 |  |  | Supply and installation of 1" quick coupler valve inside PVC box | B7.33.14.19.04
B7.32.80.00.01 | توريد وتركيب أنابيب LDPE DN 16mm (PN 4) بما في ذلك الوصلات و السوادل و جميع الملحقات الأخرى اللازمة لإكمال الأعمال وفقاً للمواصفات والرسومات. | m | 2000 |  |  | Supply and install LDPE plain pipes DN 16mm (PN 4) including compression fittings, saddles and all other accessories necessary to complete the works in accordance with specifications and drawings. | B7.32.80.00.01
B7.32.80.00.02 | توريد وتركيب منقطات تعويض الضغط ، بما في ذلك جميع الملحقات اللازمة لإكمال الأعمال طبقاً للمواصفات والرسومات. (نقاطات بتصرف 26.5LPH للأشجار ) | nr | 6316 |  |  | Supply and install online pressure compensating emitters, including all accessories necessary to complete the works in accordance with specifications and drawings.(Pressure compensating 37.85LPH emitter for trees) | B7.32.80.00.02
B7.32.80.00.03 | توريد وتركيب أنابيب بولي إيثيلين منخفضة الكثافة بقطر 16 مم (OD) بما في ذلك خط P.C. النقاطات والملحقات و الوصلات ، وجميع المتطلبات اللازمة لإنهاء العمل وفقًا للرسومات (خط التنقيط بتصرف 3.4LPH مع تباعد بين الباعثات 45 سم وتباعد بين الخطوط مسافة 35 سم) | m | 87562 |  |  | Supply and installation of 16 mm dia (O.D.) linear low density polyethylene tubing including in line P.C. emitters, accessories, stakes, takeoff /risers connections from laterals, and all requirements needed to finish work as per drawings (In line dripper line 3.4LPH dripper with spacing between emitters 45 cm and dripline spaced at 35cm ) | B7.32.80.00.03
B7.32.80.00.04 | توريد وتركيب جهاز تحكم متقدم حسب اعتماد المالك، يمكنه الاتصال بنظام التحكم المركزي وقادر على التكامل مع أنظمة المدينة الذكية أو نظام BMS أو نظام Scada ، يمكنه تسجيل معدل التدفق الحقيقي لكل محطة | nr | 2 |  |  | Supply and installation of Advanced Irrigation controller subject to client approval, can connect with Centarl Control system and cabable to integrate with Smart City systems,BMS or Scada system ,Can record the real flow rate per stations, | B7.32.80.00.04
B7.32.80.00.05 | توريد وتركيب وحدة فك ترميز أحادية المحطة لتوصيل الصمام بوحدة التحكم الميدانية بما في ذلك الموصلات المقاومة للمياه وجميع الملحقات الأخرى اللازمة لإكمال الأعمال وفقًا للمواصفات والرسومات (وحدة فك ترميز واحدة) | nr | 78 |  |  | Supply and install single station decoder for valve connection to field controller including waterproof connectors and all other accessories necessary to complete the works in accordance with specifications and drawings (Decoder Single station ). | B7.32.80.00.05
0 | يتم ترحيل أعمال الري والمناظر الطبيعة - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO LANDSCAPE AND IRRIGATION WORKS - COLLECTION
| التجميع |  |  |  |  | COLLECTION
| الصفحة 1 |  |  |  | 0 | Page 1
| الصفحة 2 |  |  |  | 0 | Page 2
| الصفحة 3 |  |  |  |  | Page 3
| الصفحة 4 |  |  |  |  | Page 4
| الصفحة 5 |  |  |  |  | Page 5
| الصفحة 6 |  |  |  |  | Page 6
| الصفحة 7 |  |  |  |  | Page 7
| الصفحة 8 |  |  |  |  | Page 8
| الصفحة 9 |  |  |  |  | Page 9
| الصفحة 10 |  |  |  |  | Page 10
| الصفحة 11 |  |  |  | 0 | Page 11
| الصفحة 12 |  |  |  | 0 | Page 12
| الصفحة 13 |  |  |  | 0 | Page 13
| الصفحة 14 |  |  |  | 0 | Page 14
| الصفحة 15 |  |  |  |  | Page 15
| الصفحة 16 |  |  |  | 0 | Page 16
| الصفحة 17 |  |  |  | 0 | Page 17
| الصفحة 18 |  |  |  | 0 | Page 18
| الصفحة 19 |  |  |  | 0 | Page 19
| الصفحة 20 |  |  |  | 0 | Page 20
| الصفحة 21 |  |  |  | 0 | Page 21
| الصفحة 22 |  |  |  | 0 | Page 22
| الصفحة 23 |  |  |  | 0 | Page 23
| الصفحة 24 |  |  |  |  | Page 24
| الصفحة 25 |  |  |  | 0 | Page 25
| الصفحة 26 |  |  |  | 0 | Page 26
| يتم ترحيل ملخص الجدول للملخص الإجمالي | ريال سعودي |  |  | 0 | BILL OF SUMMARY CARRIED TO GRAND TOTAL
check
|  |  |  | Product | 0
|  |  |  | Sum | 0
|  |  |  | Total | 0
|  |  |  | Difference(10) | 10

## OLD BOQ (hidden)
#REF! | [6 empty] | #REF!
جدول الكميات | [6 empty] | BILL OF QUANTITIES
البند | وصف البند | الوحدة | الكمية | السعر (ريال سعودي) | المبلغ (ريال سعودي) | ITEM DESCRIPTION | ITEM
|  | Unit | QUANTITY | PRICE (S.R) | AMOUNT (S.R)
أعمال الطرق | [5 empty] | ROAD WORKS
02 41 00 | أعمال الهدم |  |  |  |  | DEMOLITION | 02 41 00
B1.02 41 00.1 | إزالة أسفلت قائم | m2 | 2200 |  |  | Demolition of existing Asphalt | B1.02 41 00.1
B1.02 41 00.2 | اعداد طبقة الاساس الحصوي القائمة | m2 | 2200 |  |  | Compaction of existing aggregate base course layer | B1.02 41 00.2
B1.02 41 00.3 | إزالة بردورات قائمه | m | 464 |  |  | Demolition of existing Kerbs | B1.02 41 00.3
31 22 00 | الأعمال الترابية و التسوية |  | 0 |  |  | EARTHWORKS AND SITE GRADING | 31 22 00
B1.31 22 00.01 | حفريات الطرق | m3 | 205106 |  |  | Excavation for cuttings | B1.31 22 00.01
B1.31 22 00.02 | ردميات الطرق | m3 | 1378709 |  |  | Fill to the roads | B1.31 22 00.02
B1.31 22 00.03 | طبقة القاعدة | m3 | 222337 |  |  | Subgrade | B1.31 22 00.03
32 11 23 | طبقة أساس حصوية |  | 0 |  |  | AGGREGATE BASE COURSE | 32 11 23
B1.32 11 23.01 | طبقة أساس حصوية | m3 | 145216 |  |  | Aggregate base course | B1.32 11 23.01
32 11 26 | الإنشاء البيتوميني |  | 0 |  |  | BITUMINOUS CONSTRUCTION | 32 11 26
B1.32 11 26.02 | الطبقة الأساس البيتومينية (تدرج 1 - صنف أ)، شاملاً الطبقة اللاصقة (MC1) & (RC2) . | m3 | 63389 |  |  | Bituminous base course (Grading I - Class A), including Prime Coat (MC1) & (RC2). | B1.32 11 26.02
32 12 16 | طبقة السطح العليا |  | 0 |  |  | ASPHALT WEARING COURSE | 32 12 16
B1.32 12 16.01 | طبقة السطح العليا من الخرسانة البيتومينية (تدرج 1 - صنف أ) شاملاً الطبقة اللاصقة (RC2) . | m3 | 36304 |  |  | Bituminous concrete wearing course, (Grading I - Class A), including tack coat (RC2). | B1.32 12 16.01
32 14 13 | بردورات مسبقة الصب |  | 0 |  |  | PRECAST CONCRETE CURB | 32 14 13
B1.32 14 13.01 | بردورات نوع (K1A) | m | 79448 |  |  | Concrete curb, Type (K1A) | B1.32 14 13.01
B1.32 14 13.02 | بردورات نوع (K1B) | m | 21624 |  |  | Concrete curb, Type (K1B) | B1.32 14 13.02
B1.32 14 13.03 | بردورات نوع (K2) | m | 2755 |  |  | Concrete curb, Type (K2) | B1.32 14 13.03
| يتم ترحيل الطرق - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO ROADS - COLLECTION
32 17 23 | العلامات الأرضية |  |  |  |  | PAVEMENT MARKINGS | 32 17 23
32 17 23.01 | دهان ثرموبلاستيك (أبيض / أصفر) |  |  |  |  | Thermoplastic pavement marking (White/Yellow) | 32 17 23.01
B1.32 17 23.01.01 | دهانات مرورية بيضاء عاكسة بلاستيكية حرارية | m² | 18149 |  |  | Retroreflective Thermoplastic White Traffic | B1.32 17 23.01.01
B1.32 17 23.01.02 | دهانات مرورية صفراء عاكسة بلاستيكية حرارية | m² | 11771 |  |  | Retroreflective Thermoplastic Yellow Traffic | B1.32 17 23.01.02
10 14 53 | اللوحات الإرشادية للطرق |  | 0 |  |  | TRAFFIC SIGNAGE | 10 14 53
B1.10 14 53.01 | لوحات مرورية المثبتة بالأرض مصنوعة من ألواح ألومنيوم مع حواملها القابلة للإنفصال بالقاعدة مكونة من لوحة مروريه وعمود واحد مع كافة الاكسسورات وكل ما يلزم حسب المخططات والمواصفات. | Unit | 482 |  |  | Traffic signs, ground mounted, 1 Sheet Alumenium, (breakaway) Single post, with all accessories according to the drawings and specifications. | B1.10 14 53.01
B1.10 14 53.02 | لوحات مرورية المثبتة بالأرض مصنوعة من ألواح ألومنيوم مع حواملها القابلة للإنفصال بالقاعدة مكونة من لوحتين مروريتين وعمود واحد مع كافة الاكسسورات وكل ما يلزم حسب المخططات والمواصفات. | Unit | 275 |  |  | Traffic signs, ground mounted, 2 Sheet Alumenium, (breakaway) Single post, with all accessories according to the drawings and specifications. | B1.10 14 53.02
B1.10 14 53.03 | لوحات مرورية مصنوعة من ألواح الإلمنيوم مع حواملها (قابلة للانفصال بالقاعدة) مكونة من لوحه مروريه وعمودين مع كافات الاكسسورات، وكل ما يلزم حسب المخططات والمواصفات. | Unit | 45 |  |  | Traffic signs, ground mounted, Sheet Alumenium, (breakaway) Double post with all accessories according to the drawings and specifications. | B1.10 14 53.03
B1.10 14 53.04 | علامات أرضية بارزة عاكسة (نوع - أ) | Unit | 500 |  |  | Retroreflective raised pavement markers (Type A) | B1.10 14 53.04
B1.10 14 53.05 | علامات أرضية بارزة مصنوعة من السيراميك | Unit | 500 |  |  | Ceramic raised pavement markers | B1.10 14 53.05
B1.10 14 53.06 | علامات أرضية مضيئة تعمل بالطاقة الشمسية (عيون القط) | Unit | 500 |  |  | Solar powered lighting cateyes pavement markers | B1.10 14 53.06
0
0
0
0
0
| يتم ترحيل الطرق - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO ROADS - COLLECTION
الأعمال الكهربائية |  |  |  |  | 0 | ELECTRICAL WORKS
31 23 00 | خندق كابل الجهد المتوسط |  |  |  | 0 | MEDIUM VOLTAGE CABLE TRENCH | 31 23 00
B2.31 23 00.01 | حفر خندق كابل عرض 2.4 م وعمق 80 سم | m³ | 4992 |  |  | Excavation for Trench size 2.4m wide and 80cm deep | B2.31 23 00.01
B2.31 23 00.02 | حفر خندق كابل عرض 1.2 م وعمق 80 سم | m³ | 1834 |  |  | Excavation for Trench size 1.2m wide and 80cm deep | B2.31 23 00.02
B2.31 23 00.03 | حفر خندق كابل عرض 0.9 م وعمق 80 سم | m³ | 568 |  |  | Excavation for Trench size 0.9m wide and 80cm deep | B2.31 23 00.03
B2.31 23 00.04 | حفر خندق كابل عرض 0.6 م وعمق 80 سم | m³ | 2294 |  |  | Excavation for Trench size 0.6m wide and 80cm deep | B2.31 23 00.04
B2.31 23 00.05 | حفر خندق كابل عرض 0.4 م وعمق 80 سم | m³ | 8008 |  |  | Excavation for Trench size 0.4m wide and 80cm deep | B2.31 23 00.05
33 71 19 | عبارات كابلات الجهد المتوسط |  | 0 |  |  | MEDIUM VOLTAGE CABLES DUCT BANKS | 33 71 19
B2.33 71 19.01 | عبارات كوابل 6 مسارات (6x150mm duct) | m | 225 |  |  | 6-way Duct Bank (6x150mm duct) | B2.33 71 19.01
B2.33 71 19.02 | عبارات كوابل 4 مسارات (4x150mm duct) | m | 330 |  |  | 4-way Duct Bank (4x150mm duct) | B2.33 71 19.02
B2.33 71 19.03 | عبارات كوابل 2 مسارات (2x150mm duct) | m | 677 |  |  | 2-way Duct Bank (2x150mm duct) | B2.33 71 19.03
26 05 13.16 | كيابل الجهد المتوسط |  |  |  | 0 | MEDIUM VOLTAGE CABLES | 26 05 13.16
B2.26.05.13.16.01 | كيبل جهد 15 ك.ف.500*3C مم2 AL/ XLPE/ LLDPE غير مسلح | m | 41635 |  |  | Cable: 15KV 3Cx500mm² AL/XLPE/LLDPE unarmored | B2.26.05.13.16.01
B2.26.05.13.16.02 | كابل نحاس أحادي القلب جهد 15 ك.ف غير مسلح (3x1Cx50mm²,Cu/LLDPE/PVC). | m | 45 |  |  | Single Core Cables, Copper, 15kV (3x1Cx50mm²,Cu/LLDPE/PVC). | B2.26.05.13.16.02
B2.26.05.13.16.03 | وصلات كيابل مستقيمة جهد 15 ك.ف. 3C x 500 مم2 Al /XLPE/LLDPE غير مسلح | Unit | 83 |  |  | Straight joints cables for 15KV 3x500mm² AL/XLPE/LLDPE unarmored | B2.26.05.13.16.03
B2.26.05.13.16.04 | نهاية كابل جهد 15 ك.ف. 3C x 500 مم2 Al /XLPE/LLDPE | Unit | 30 |  |  | Cable Termination for 15KV 3Cx500mm² AL/XLPE/LLDPE | B2.26.05.13.16.04
B2.26.05.13.16.05 | كيبل جهد 36 ك.ف.400*3C مم2 AL/ XLPE/ LLDPE غير مسلح | m | 23760 |  |  | Cable: 36KV 3Cx400mm² AL/XLPE/LLDPE unarmored | B2.26.05.13.16.05
B2.26.05.13.16.06 | كابل نحاس أحادي القلب جهد 36 ك.ف غير مسلح (3x1Cx50mm²,Cu/LLDPE/PVC). | m | 30 |  |  | Single Core Cables, Copper, 36kV (3x1Cx50mm²,Cu/LLDPE/PVC). | B2.26.05.13.16.06
B2.26.05.13.16.07 | وصلات كيابل مستقيمة جهد 36 ك.ف. 3C x 400 مم2 Al /XLPE/LLDPE غير مسلح | Unit | 48 |  |  | Straight joints cables for 36KV 3x400mm² AL/XLPE/LLDPE unarmored | B2.26.05.13.16.07
B2.26.05.13.16.08 | نهاية كابل جهد 36 ك.ف. 3C x 400 مم2 Al /XLPE/LLDPE | Unit | 28 |  |  | Cable Termination for 36KV 3Cx400mm² AL/XLPE/LLDPE | B2.26.05.13.16.08
| يتم ترحيل شبكة التوزيع الكهربائية - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO ELECTRICAL DISTRIBUTION NETWORK - COLLECTION
26 13 00 | مفاتيح الجهد المتوسط |  |  |  | 0 | MEDIUM VOLTAGE SWITCHGEARS | 26 13 00
B2.26 13 00.01 | مفتاح جهد متوسط (13.8 ك.ف) (وحدة الربط الحلقي) لنقاط الفتح بين المغذيات (NOP) من النوع الخارجي طبقاً لمواصفات الشركة السعودية للكهرباء ومتطلباتها | Unit | 4 |  |  | Normally Open Point (R M U) 13.8 kv for Outdoor type according to the Saudi Electric Company specifications and requirements | B2.26 13 00.01
B2.26 13 00.02 | مفتاح جهد متوسط (33 ك.ف) (وحدة الربط الحلقي) لنقاط الفتح بين المغذيات (NOP) من النوع الخارجي طبقاً لمواصفات الشركة السعودية للكهرباء ومتطلباتها | Unit | 2 |  |  | Normally Open Point (R M U) 33 kv for Outdoor type according to the Saudi Electric Company specifications and requirements | B2.26 13 00.02
| إنارة الطرق |  |  |  | 0 | ROAD LIGHTING
26 11 16 | محطات الإنارة |  |  |  | 0 | STREET LIGHTING SUB-STATION | 26 11 16
B2.26 11 16.01 | محطة مصندقة 13.8/0.4 ك ف ، 500 ك.ف .ا, شاملة القواعد الخرسانية والسياج .حسب مواصفات ومعايير شركة الكهرباء | Unit | 3 |  |  | Unit Substation 13.8/0.4 K V, 500kVA ,Including concrete foundations and fencing, According to the specifications and standards of SEC | B2.26 11 16.01
B2.26 11 16.02 | وحدة الجهد المتوسط الحلقية الالية 13.8 ك ف , RMU. حسب مواصفات ومعايير شركة الكهرباء | Unit | 3 |  |  | Ring Main Unit RMU, 13.8KV, According to the specifications and standards of SEC | B2.26 11 16.02
B2.26 11 16.03 | محطة مصندقة 33/0.4 ك ف ، 500 ك.ف .ا, شاملة القواعد الخرسانية والسياج .حسب مواصفات ومعايير شركة الكهرباء | Unit | 2 |  |  | Unit Substation 33/0.4 K V, 500kVA ,Including concrete foundations and fencing, According to the specifications and standards of SEC | B2.26 11 16.03
B2.26 11 16.04 | وحدة الجهد المتوسط الحلقية الالية 33 ك ف , RMU. حسب مواصفات ومعايير شركة الكهرباء | Unit | 2 |  |  | Ring Main Unit RMU, 33KV, According to the specifications and standards of SEC | B2.26 11 16.04
26 05 19 | كابلات الضغط المنخفض |  |  |  | 0 | LOW VOLTAGE CABLES | 26 05 19
B2.26 05 19.01 | كابل الومنيوم, (4Cx185mm²,AL/XLPE/PVC). | m | 100 |  |  | Cables, Aluminium, (4Cx185mm²,AL/XLPE/PVC). | B2.26 05 19.01
B2.26 05 19.02 | كابل نحاس, (4Cx50mm²,Cu/XLPE/SWA/PVC + 1x25mm² PVC/ECC). | m | 50 |  |  | Cables, Copper, (4Cx50mm²,Cu/XLPE/SWA/PVC + 1x25mm² PVC/ECC). | B2.26 05 19.02
B2.26 05 19.03 | كابل نحاس, (4Cx95mm²,Cu/XLPE/SWA/PVC + 1x50mm² PVC/ECC). | m | 7240 |  |  | Cables, Copper, (4Cx95mm²,Cu/XLPE/SWA/PVC + 1x50mm² PVC/ECC). | B2.26 05 19.03
B2.26 05 19.04 | كابل نحاس, (4Cx16mm²,Cu/XLPE/SWA/PVC +1x10mm² PVC/PVC) | m | 57370 |  |  | Cables, Copper, (4Cx16mm²,Cu/XLPE/SWA/PVC +1x10mm² PVC/PVC) | B2.26 05 19.04
26 27 33 | لوحات توزيع الجهد المنخفض |  |  |  | 0 | LOW VOLTAGE DISTRIBUTION PANEL | 26 27 33
B2.26 27 33.01 | كابينه توزيع الجهد المنخفض Main: 100A, MCCB | Unit | 5 |  |  | 100A MCCB Low Voltage Distribution Cabinet. | B2.26 27 33.01
| يتم ترحيل شبكة التوزيع الكهربائية - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO ELECTRICAL DISTRIBUTION NETWORK - COLLECTION
26 56 19 | أعمدة إنارة |  |  |  | 0 | LIGHTING POLES | 26 56 19
B2.26 56 19.01 | أعمدة أنارة مع ذراعين ، إرتفاع 16 متر، تشمل علبة توزيع الطاقة والكوابل، والقاعدة الخرسانية | Unit | 107 |  |  | Lighting poles with double arm, height of ( 16 ) meters, including the power distribution box, cables , and RCC foundation. | B2.26 56 19.01
B2.26 56 19.02 | أعمدة أنارة مع ذراع واحد ، إرتفاع 16 متر، تشمل علبة توزيع الطاقة والكوابل، والقاعدة الخرسانية | Unit | 8 |  |  | Lighting poles with single arm, height of ( 16 ) meters, including the power distribution box, cables , and RCC foundation. | B2.26 56 19.02
B2.26 56 19.03 | أعمدة أنارة مع ذراع واحد ، إرتفاع 12 متر، تشمل علبة توزيع الطاقة والكوابل، والقاعدة الخرسانية | Unit | 748 |  |  | Lighting poles with single arm, height of ( 12 ) meters, including the power distribution box, cables , and RCC foundation. | B2.26 56 19.03
26 56 19 | وحدات إنارة الشوارع |  |  |  | 0 | STREET LIGHTING LUMINAIRE | 26 56 19
B2.26.56.19.04 | وحدة إنارة LED نظام اضاءة بمخرج ≥ 50000 lumen كاملة مع جهاز التحكم والمصباح ، (305) واط, 230 فولت, 60 هرتز . | Unit | 70 |  |  | Street Lighting ( LED) Luminaire,of Output≥ 50000 lumen complete with control gear and lamp, 305 WATT, 230 Volt, 60 HZ | B2.26.56.19.04
B2.26.56.19.05 | وحدة إنارة LED نظام اضاءة بمخرج ≥ 26000 lumen كاملة مع جهاز التحكم والمصباح ، (154) واط, 230 فولت, 60 هرتز . | Unit | 214 | 0 |  | Street Lighting ( LED) Luminaire,of Output≥ 26000 lumen complete with control gear and lamp, 154 WATT, 230 Volt, 60 HZ | B2.26.56.19.05
B2.26.56.19.06 | وحدة إنارة LED نظام اضاءة بمخرج ≥ 19000 lumen كاملة مع جهاز التحكم والمصباح ، (114) واط, 230 فولت, 60 هرتز . | Unit | 748 | 0 |  | Street Lighting ( LED) Luminaire,of Output≥ 19000 lumen complete with control gear and lamp, 114 WATT, 230 Volt, 60 HZ | B2.26.56.19.06
26 05 26 | نظام التاريض |  |  |  | 0 | EARTHING SYSTEM | 26 05 26
B2.26 05 26.01 | يشمل تأريض الأعمدة والصوارى وكبائن التغذية ومحطة التوزيع ووحدات الربط الحلقي ومغذيات الجهد المنخفض لدوائر الإنارة وعداد قياس الطاقة. | Unit | 86 |  |  | Including earthing of lighting poles ,masts. feeder pillars , unit substations, RMU, L.V feeders and KWH meter. | B2.26 05 26.01
33 71 19 | عبارات عبور كابلات الطرق |  | 0 |  |  | ROAD CROSSING DUCTS | 33 71 19
B2.33 71 19.04 | عبارة طرق لكابلات إنارة شوارع ذات أثنين منفذ من مواسير بوليفنيل الكلوريد (2x100 مم) | m | 5074 |  |  | Road crossing ducts, 2 way (2 x 100mm PVC) | B2.33 71 19.04
26 24 16 | لوحات الانارة وكبائن التوزيع |  | 0 |  |  | LIGHTING PANELS | 26 24 16
B2.26 24 16.01 | كبائن التوزيع لدوائر الانارة | Unit | 13 |  |  | Street Lighting Feeder pillars | B2.26 24 16.01
B2.26 24 16.02 | توريد وتركيب جدار مع الإطار لتركيب عداد قياس الطاقة من بلوك خرساني حسب معايير ومواصفات الشركة السعودية للكهرباء. | Unit | 5 |  |  | Supply and installation of concrete block wall including the frame and the concrete block wall for installation of KWH meter according to the standards and specifications of SEC. | B2.26 24 16.02
33 71 19.13 | حفر سحب الكابلات |  | 0 |  |  | DRAWPITS | 33 71 19.13
B2.33 71 19.13.01 | حفرة سحب مع غطاء حديد متوسط التحمل بأبعاد 600*600*1000 مم | Unit | 187 |  |  | Drawpit with medium duty steel cover, size 600x600x1000mm | B2.33 71 19.13.01
0
| يتم ترحيل شبكة التوزيع الكهربائية - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO ELECTRICAL DISTRIBUTION NETWORK - COLLECTION
| الاتصالات |  |  |  | 0 | TELECOMMUNICATIONS
33 71 19 | عبارات عبور كابلات الطرق من الخرسانة المسلحة |  |  |  | 0 | ROAD CROSSING REINFORCED CONCRETE ENCASEMENT DUCTS | 33 71 19
B2.33 71 19.05 | عبارات عبور الطريق من المواسير البولي ايثلين 6 خطوط بقطر 50 مم | m | 1700 |  |  | 6 way 50mm HDPE duct | B2.33 71 19.05
33 71 19 | عبارات عبور كابلات الطرق من الخرسانة الغير مسلحة |  | 0 |  |  | UNREINFORCED CONCRETE DUCTS | 33 71 19 | 23380
B2.33 71 19.06 | عبارات عبور الطريق من المواسير البولي ايثلين 6 خطوط بقطر 50 مم | m | 34650 |  |  | 6 way 50mm HDPE duct | B2.33 71 19.06
33 71 19 | العبارات |  | 0 |  |  | DUCTS | 33 71 19 | 370
B2.33 71 19.07 | المواسير من البولي ايثلين 2 خطوط بقطر 32 مم | m | 30590 |  |  | 2 x 32 mm diameter HDPE ducts | B2.33 71 19.07
33 71 19.13 | غرف تفتيش (مانهولات) |  | 0 |  |  | MANHOLES | 33 71 19.13
B2.33.71.19.13.02 | غرفة تقتيش (مانهول) من النوع 1 | nr | 79 |  |  | Manhole type 1 | B2.33.71.19.13.02
B2.33.71.19.13.03 | غرفة تقتيش (مانهول) من النوع 2 | nr | 103 |  |  | Manhole type 2 | B2.33.71.19.13.03
B2.33.71.19.13.04 | غرفة تقتيش (مانهول) من النوع 3 | nr | 2 |  |  | Manhole type 3 | B2.33.71.19.13.04
0
0
0
0
0
0
0
0
0
| يتم ترحيل شبكة التوزيع الكهربائية - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO ELECTRICAL DISTRIBUTION NETWORK - COLLECTION
شبكة مياه الشرب |  |  |  |  | 0 | POTABLE WATER NETWORK
| أعمال المواسير - المواسير |  |  |  | 0 | PIPEWORK-PIPES
33 14 13 | مواسير من البولي إيتلين العالي الكثافة PE 100 SDR 11 (PN 16 Bar) |  |  |  | 0 | High Density Polyethylene pipes PE 100 SDR 11 (PN 16 Bar) | 33 14 13
| قطر 110 مم |  |  |  | 0 | 110mm Diameter
B3.33 14 13.01 | عمق 0 - 1.5 م | m | 51 |  |  | Depth: 0.0m - 1.5m | B3.33 14 13.01 |  | 370
B3.33 14 13.02 | عمق 1.51 - 2.5 م | m | 14 |  |  | Depth: 1.51m - 2.5m | B3.33 14 13.02 |  | 420
B3.33 14 13.03 | عمق اكبر من 2.51 م | m | 10 |  |  | Depth: Greater than 2.51m | B3.33 14 13.03
| قطر 160 مم |  | 0 |  |  | 160mm Diameter
B3.33 14 13.04 | عمق 0 - 1.5 م | m | 4464 |  |  | Depth: 0.0m - 1.5m | B3.33 14 13.04 |  | 370
B3.33 14 13.05 | عمق 1.51 - 2.5 م | m | 633 |  |  | Depth: 1.51m - 2.5m | B3.33 14 13.05 |  | 420
B3.33 14 13.03 | عمق اكبر من 2.51 م | m | 10 |  |  | Depth: Greater than 2.51m | B3.33 14 13.03
| قطر 200 مم |  | 0 |  |  | 200mm Diameter
B3.33 14 13.07 | عمق 0 - 1.5 م | m | 9788 |  |  | Depth: 0.0m - 1.5m | B3.33 14 13.07 | 320
B3.33 14 13.08 | عمق 1.51 - 2.5 م | m | 1416 |  |  | Depth: 1.51m - 2.5m | B3.33 14 13.08 | 350
B3.33 14 13.09 | عمق 2.51 - 3.5 م | m | 71 |  |  | Depth: 2.51m - 3.5m | B3.33 14 13.09 | 380
B3.33 14 13.03 | عمق اكبر من 3.51 م | m | 10 |  |  | Depth: Greater than 3.51m | B3.33 14 13.03
| قطر 250 مم |  | 0 |  |  | 250mm Diameter
B3.33 14 13.11 | عمق 0 - 1.5 م | m | 7254 |  |  | Depth: 0.0m - 1.5m | B3.33 14 13.11 | 320
B3.33 14 13.12 | عمق 1.51 - 2.5 م | m | 1431 |  |  | Depth: 1.51m - 2.5m | B3.33 14 13.12 | 350
B3.33 14 13.13 | عمق 2.51 - 3.5 م | m | 69 |  |  | Depth: 2.51m - 3.5m | B3.33 14 13.13 | 380
B3.33 14 13.14 | عمق اكبر من 3.51 م | m | 10 |  |  | Depth: Greater than 3.51m | B3.33 14 13.14
| يتم ترحيل شبكة مياه الشرب - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO POTABLE WATER NETWORK - COLLECTION
| أعمال المواسير - المواسير |  |  |  | 0 | PIPEWORK-PIPES
| قطر 315 مم |  | 0 |  |  | 315mm Diameter
B3.33 14 13.15 | عمق 0 - 1.5 م | m | 201 |  |  | Depth: 0.0m - 1.5m | B3.33 14 13.15
B3.33 14 13.16 | عمق 1.51 - 2.5 م | m | 151 |  |  | Depth: 1.51m - 2.5m | B3.33 14 13.16
B3.33 14 13.17 | عمق اكبر من 2.51 م | m | 10 |  |  | Depth: Greater than 2.51m | B3.33 14 13.17
| قطر 355 مم |  | 0 |  |  | 355mm Diameter
B3.33 14 13.18 | عمق 0 - 1.5 م | m | 60 |  |  | Depth: 0.0m - 1.5m | B3.33 14 13.18
B3.33 14 13.19 | عمق اكبر من 1.51 م | m | 10 |  |  | Depth: Greater than 1.51m | B3.33 14 13.19
| أعمال المواسير - المواسير |  |  |  | 0 | PIPEWORK-PIPES
33 14 11 | تغليف خرسانية للمواسير |  |  |  | 0 | Pipe Encasements, | 33 14 11
B3.33 14 11.01 | تغليف خرسانية لمواسير قطر 160 مم | m | 289 |  |  | Pipe encasement diameter 160 mm | B3.33 14 11.01
B3.33 14 11.02 | تغليف خرسانية لمواسير قطر 200 مم | m | 562 |  |  | Pipe encasement diameter 200 mm | B3.33 14 11.02
B3.33 14 11.03 | تغليف خرسانية لمواسير قطر 250 مم | m | 553 |  |  | Pipe encasement diameter 250 mm | B3.33 14 11.03
B3.33 14 11.04 | تغليف خرسانية لمواسير قطر 315 مم | m | 7 |  |  | Pipe encasement diameter 315 mm | B3.33 14 11.04
B3.33 14 11.05 | تغليف خرسانية لمواسير قطر 355 مم | m | 60 |  |  | Pipe encasement diameter 355 mm | B3.33 14 11.05
| أعمال المواسير - الصمامات |  |  |  | 0 | PIPEWORK - VALVES
33 14 19 | الصمامات |  |  |  | 0 | Valves | 33 14 19
0 | الصمام البوابي (مدفون) |  |  |  | 0 | Gate (Sluice) valves (Direct buried)
B3.33 14 19.01 | صمام قفل بوابي بقطر 150 مم على خط مواسير بقطر160 مم . | nr | 19 |  |  | Gate valves dia (150) mm on pipe dia (160) mm . | B3.33 14 19.01
B3.33 14 19.02 | صمام قفل بوابي بقطر 200 مم على خط مواسير بقطر200 مم . | nr | 45 |  |  | Gate valves dia (200) mm on pipe dia (200) mm . | B3.33 14 19.02
B3.33 14 19.03 | صمام قفل بوابي بقطر 250 مم على خط مواسير بقطر250 مم . | nr | 39 |  |  | Gate valves dia (250) mm on pipe dia (250) mm . | B3.33 14 19.03
| يتم ترحيل شبكة مياه الشرب - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO POTABLE WATER NETWORK - COLLECTION
| أعمال المواسير - الصمامات |  |  |  | 0 | PIPEWORK - VALVES
33 14 19 | الصمامات |  |  |  | 0 | Valves | 33 14 19
0 | صمامات الفراشة |  |  |  | 0 | Butterfly valves
B3.33 14 19.04 | صمام فراشة بقطر 300 مم على خط مواسير بقطر315 مم . | nr | 2 |  |  | Butterfly valves with dia (300) mm on pipe dia (315) mm . | B3.33 14 19.04
B3.33 14 19.05 | صمام فراشة بقطر 350 مم على خط مواسير بقطر355 مم . | nr | 1 |  |  | Butterfly valves with dia (350) mm on pipe dia (355) mm . | B3.33 14 19.05
0 | صمام التنظيف (الغسيل) |  | 0 |  |  | Wash-out Valves
B3.33 14 19.06 | محابس غسيل بقطر 100 مم على خط مواسير بقطر160 مم . | nr | 2 |  |  | Wash out valve with dia 100 mm on pipe dia (160) mm . | B3.33 14 19.06
B3.33 14 19.07 | محابس غسيل بقطر 100 مم على خط مواسير بقطر200 مم . | nr | 8 |  |  | Wash out valve with dia 100 mm on pipe dia (200) mm . | B3.33 14 19.07
B3.33 14 19.08 | محابس غسيل بقطر 100 مم على خط مواسير بقطر250 مم . | nr | 4 |  |  | Wash out valve with dia 100 mm on pipe dia (250) mm . | B3.33 14 19.08
B3.33 14 19.09 | محابس غسيل بقطر 100 مم على خط مواسير بقطر315 مم . | nr | 2 |  |  | Wash out valve with dia 100 mm on pipe dia (315) mm . | B3.33 14 19.09
0 | صمامات الهواء |  | 0 |  |  | Air Valves
B3.33 14 19.10 | محابس هواء بقطر 50 مم على خط مواسير بقطر 160 مم. | nr | 1 |  |  | Air valves with dia 50 mm on pipe dia (160) mm. | B3.33 14 19.10
B3.33 14 19.11 | محابس هواء بقطر 50 مم على خط مواسير بقطر 200 مم. | nr | 7 |  |  | Air valves with dia 50 mm on pipe dia (200) mm. | B3.33 14 19.11
B3.33 14 19.12 | محابس هواء بقطر 50 مم على خط مواسير بقطر 250 مم. | nr | 5 |  |  | Air valves with dia 50 mm on pipe dia (250) mm. | B3.33 14 19.12
0 | فوهات حريق |  | 0 |  |  | Fire Hydrant
B3.33 14 19.13 | فوهة حريق 3 مخارج (مخرجين قياس 2.5 بوصة ومخرج قياس 4 بوصة) على شكل اسطوانة مفرغة جافة قابلة للإنفصال. | nr | 280 |  |  | 3-outlet fire hydrant (2 x 2.5 inch and 1 x 4.5 inch) in the form of a separate dry vacuum cylinder | B3.33 14 19.13
0
0
0
0
| يتم ترحيل شبكة مياه الشرب - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO POTABLE WATER NETWORK - COLLECTION
0 | أعمال المواسير - غرف تفتيش الصمامات - الأعمال المدنية |  |  |  | 0 | PIPEWORK-Valve chambers - Civil Works
B3.33 14 13 | غرف تفتيش للصمامات |  |  |  | 0 | Valve chambers | B3.33 14 13
B3.33 14 13.01 | غرفة على خط أنبوب بقطر 315 مم | nr | 2 |  |  | Chamber at pipe 315 mm Dia | B3.33 14 13.01
B3.33 14 13.02 | غرفة على خط أنبوب بقطر 355 مم | nr | 1 |  |  | Chamber at pipe 355 mm Dia | B3.33 14 13.02
0 | غرف تفتيش للتنظيف (الغسيل) |  | 0 |  |  | Wash out chambers
B3.33 14 13.03 | غرفة تنظيف على خط مواسير بقطر 160 مم | nr | 2 |  |  | Wash out chamber; on 160 mm dia pipeline | B3.33 14 13.03
B3.33 14 13.04 | غرفة تنظيف على خط مواسير بقطر 200 مم | nr | 8 |  |  | Wash out chamber; on 200 mm dia pipeline | B3.33 14 13.04
B3.33 14 13.05 | غرفة تنظيف على خط مواسير بقطر 250 مم | nr | 4 |  |  | Wash out chamber; on 250 mm dia pipeline | B3.33 14 13.05
B3.33 14 13.06 | غرفة تنظيف على خط مواسير بقطر 315 مم | nr | 2 |  |  | Wash out chamber; on 315 mm dia pipeline | B3.33 14 13.06
0 | غرف صمامات الهواء |  | 0 |  |  | Air Valve chambers
B3.33 14 13.07 | غرفة صمام الهواء على خط مواسير بقطر 160 مم | nr | 1 |  |  | Air valve chamber; on 160 mm dia pipeline | B3.33 14 13.07
B3.33 14 13.08 | غرفة صمام الهواء على خط مواسير بقطر 200 مم | nr | 7 |  |  | Air valve chamber; on 200 mm dia pipeline | B3.33 14 13.08
B3.33 14 13.09 | غرفة صمام الهواء على خط مواسير بقطر 250 مم | nr | 5 |  |  | Air valve chamber; on 250 mm dia pipeline | B3.33 14 13.09
33 71 19 | الوصلات القاطعة للشوارع |  | 0 |  |  | Road Crossing | 33 71 19
B3.33 71 19.01 | وصله HDPE قاطعة للشوارع بقطر 160 مم (تشمل أغطية النهايات, محبس العزل, الخ...) | nr | 93 |  |  | HDPE road croosing with dia 160 mm (Including end cap, isolation valve, etc...) | B3.33 71 19.01
33 05 04 | أعمال الهدم والإزالات |  | 0 |  |  | Demolition works | 33 05 04
B3.33 05 04.01 | إزالة ماسورة قطر 200 مم | nr | 180 |  |  | Removal of Pipe diameter 200 mm | B3.33 05 04.01
B3.33 05 04.02 | إزالة ماسورة قطر 500 مم | nr | 325 |  |  | Removal of Pipe diameter 500 mm | B3.33 05 04.02
0
0
| يتم ترحيل شبكة مياه الشرب - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO POTABLE WATER NETWORK - COLLECTION
شبكة الري |  |  |  |  | 0 |  | TSE NETWORK
0 | أعمال المواسير - المواسير |  |  |  | 0 | PIPEWORK-PIPES
33 31 00 | مواسير من البولي إيتلين العالي الكثافة PE 100 SDR 11 (PN 16 Bar) |  |  |  | 0 | High Density Polyethylene pipes PE 100 SDR 11 ( PN 16 Bar) | 33 31 00
| قطر 110 مم |  |  |  | 0 | 110mm Diameter
B4.33 31 00.01 | عمق 0 - 1.5 م | m | 17946 |  |  | Depth: 0.0m - 1.5m | B4.33 31 00.01
B4.33 31 00.02 | عمق 1.51 - 2.5 م | m | 7162 |  |  | Depth: 1.51m - 2.5m | B4.33 31 00.02
B4.33 31 00.03 | عمق 2.51 - 3.5 م | m | 1426 |  |  | Depth: 2.51m - 3.5m | B4.33 31 00.03
B4.33 31 00.04 | عمق اكبر من 3.51 م | m | 10 |  |  | Depth: Greater than 3.51m | B4.33 31 00.04
| قطر 160 مم |  | 0 |  |  | 160mm Diameter
B4.33 31 00.05 | عمق 0 - 1.5 م | m | 5 |  |  | Depth: 0.0m - 1.5m | B4.33 31 00.05
B4.33 31 00.06 | عمق 1.50 - 2.5 م | m | 305 |  |  | Depth: 1.50m - 2.5m | B4.33 31 00.06
B4.33 31 00.07 | عمق 2.51 - 3.5 م | m | 453 |  |  | Depth: 2.51m - 3.5m | B4.33 31 00.07
B4.33 31 00.08 | عمق اكبر من 3.51 م | m | 10 |  |  | Depth: Greater than 3.51m | B4.33 31 00.08
| قطر 200 مم |  | 0 |  |  | 200mm Diameter
B4.33 31 00.09 | عمق 0 - 1.5 م | m | 85 |  |  | Depth: 0.0m - 1.5m | B4.33 31 00.09
B4.33 31 00.10 | عمق اكبر من 1.51 م | m | 10 |  |  | Depth: Greater than 1.51m | B4.33 31 00.10
32 81 11 | مجاري تمديدات انابيب الري من نوع uPVC من الفئة 4 |  | 0 |  |  | Class 4 uPVC irrigation ducts | 32 81 11
B4.32 81 11.01 | قطر 200 مم | m | 1638 |  |  | Pipe with diameter 200 mm. | B4.32 81 11.01
0
| يتم ترحيل شبكة مياه المعالجة - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO TSE NETWORK - COLLECTION
0 | أعمال المواسير - المواسير |  |  |  | 0 | PIPEWORK-PIPES
B4.33 14 11 | مواسير تغليف خرسانية |  |  |  | 0 | Pipe Encasements, | B4.33 14 11
B4.33 14 11.01 | تغليف خرساني لمواسير قطر 110 مم | m | 1200 |  |  | Pipe encasement dia 110 mm | B4.33 14 11.01
B4.33 14 11.02 | تغليف خرساني لمواسير قطر 160 مم | m | 150 |  |  | Pipe encasement dia 160 mm | B4.33 14 11.02
B4.33 14 11.03 | تغليف خرساني لمواسير قطر 200 مم | m | 20 |  |  | Pipe encasement dia 200 mm | B4.33 14 11.03
0 | أعمال المواسير - الصمامات |  |  |  | 0 | PIPEWORK - VALVES
33 14 19 | الصمامات |  |  |  | 0 | Valves | 33 14 19
0 | الصمام البوابي (مدفون) |  |  |  | 0 | Gate (Sluice) valves (Direct buried)
B4.33 14 19.01 | محابس قفل بوابي بقطر 100 مم على خط مواسير بقطر110 مم . | nr | 81 |  |  | Gate valves dia (100) mm on pipe dia (110) mm . | B4.33 14 19.01
B4.33 14 19.02 | محابس قفل بوابي بقطر 150 مم على خط مواسير بقطر160 مم . | nr | 4 |  |  | Gate valves dia (150) mm on pipe dia (160) mm . | B4.33 14 19.02
B4.33 14 19.03 | محابس قفل بوابي بقطر 200 مم على خط مواسير بقطر200 مم . | nr | 1 |  |  | Gate valves dia (200) mm on pipe dia (200) mm . | B4.33 14 19.03
| صمام التنظيف (الغسيل) |  |  |  | 0 | Wash-out Valves
B4.33 14 19.04 | محابس غسيل بقطر 100 مم على خط مواسير بقطر110 مم . | nr | 9 |  |  | Wash out valve with dia 100 mm on pipe dia (110) mm . | B4.33 14 19.04
| صمامات الهواء |  |  |  |  | Air Valves
B4.33 14 19.05 | محابس هواء بقطر 50 مم على خط مواسير بقطر110 مم . | nr | 9 |  |  | Air valves with dia 50 mm on pipe dia (110) mm . | B4.33 14 19.05
0
0
0
0
0
0
0
0
| يتم ترحيل شبكة مياه المعالجة - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO TSE NETWORK - COLLECTION
B4.33 14 13 | أعمال المواسير - غرف تفتيش الصمامات - الأعمال المدنية |  |  |  | 0 | PIPEWORK-Valve chambers - Civil Works | B4.33 14 13
0 | غرف تفتيش للتنظيف (الغسيل) |  |  |  | 0 | Wash out chambers
B4.33 14 13.01 | غرفة تنظيف على خط مواسير بقطر 110 مم | nr | 9 |  |  | Wash out chamber; on 110 mm dia pipeline | B4.33 14 13.01
0 | غرف صمامات الهواء |  | 0 |  |  | Air Valve chambers
B4.33 14 13.02 | غرفة صمام الهواء على خط مواسير بقطر 110 مم | nr | 9 |  |  | Air valve chamber; on 110 mm dia pipeline | B4.33 14 13.02
32 84 00 | الوصلات القاطعة للشوارع |  | 0 |  |  | Road Crossing | 32 84 00
B4.32 84 00.01 | وصله HDPE قاطعة للشوارع بقطر 110 مم (تشمل أغطية النهايات, محبس العزل, الخ...) | nr | 81 |  |  | HDPE road croosing with dia 110 mm (Including end cap, isolation valve, etc...) | B4.32 84 00.01
32 80 00 | كابلات الري |  | 0 |  |  | Irrigation Cables | 32 80 00
B4.32 80 00.01 | كابل مزدوج مبروم 12 AWG بين الصمامات وأجهزة التحكم ، يجب سحب الكابلات من خلال مواسير 32Ø UPVC و صندوق صمام دائري كل 100 متر للفحص | m | 28200 |  |  | Decoder cables 12 AWG between valves and controllers, The cables shall be pulled through 32Ø UPVC conduit and inspection 10" round valve box every 100 meters, as per standard specification and drawings | B4.32 80 00.01
0
0
0
0
0
0
0
0
0
0
0
0
0
| يتم ترحيل شبكة مياه المعالجة - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO TSE NETWORK - COLLECTION
شبكة الصرف الصحي |  |  |  |  | 0 |  | SEWERAGE NETWORK
| أعمال المواسير - المواسير |  |  |  | 0 | PIPEWORK-PIPES
33 31 00 | مواسير GRP: الصلابة 5000 حتى عمق 3.5 م الصلابة 10000 لأي عمق أكثر من 3.5 م |  |  |  | 0 | Glass Reinforced Plastic (GRP): SN 5000 up to depth 3.5 m SN 10000 depth more than 3.5 m | 33 31 00
| قطر 150 مم |  |  |  | 0 | 150mm Diameter
B5.33 31 00.01 | عمق 0.0 - 1.5 م | m | 2693 |  |  | Depth : 0.0m - 1.5m | B5.33 31 00.01
B5.33 31 00.02 | عمق 1.51 - 2.5 م | m | 1237 |  |  | Depth : 1.51m - 2.5m | B5.33 31 00.02
B5.33 31 00.03 | عمق 2.51 - 3.5 م | m | 131 |  |  | Depth : 2.51m - 3.5m | B5.33 31 00.03
B4.33 31 00.04 | عمق اكبر من 3.51 م | m | 20 |  |  | Depth: Greater than 3.51m | B4.33 31 00.04
| قطر 200 مم |  | 0 |  |  | 200mm Diameter
B5.33 31 00.05 | عمق 0.0 - 1.5 م | m | 4588 |  |  | Depth : 0.0m - 1.5m | B5.33 31 00.05
B5.33 31 00.06 | عمق 1.51 - 2.5 م | m | 4052 |  |  | Depth: 1.51m - 2.5m | B5.33 31 00.06
B5.33 31 00.07 | عمق 2.51 - 3.5 م | m | 1579 |  |  | Depth: 2.51m - 3.5m | B5.33 31 00.07
B5.33 31 00.08 | عمق 3.51 - 4.5 م | m | 446 |  |  | Depth: 3.51m - 4.5m | B5.33 31 00.08
B5.33 31 00.09 | عمق 4.51 - 5.5 م | m | 559 |  |  | Depth: 4.51m - 5.5m | B5.33 31 00.09
B5.33 31 00.10 | عمق اكبر من 5.51 م | m | 10 |  |  | Depth: Greater than 5.51m | B5.33 31 00.10
| قطر 250 مم |  | 0 |  |  | 250mm Diameter
B5.33 31 00.11 | عمق 0.0 - 1.5 م | m | 20 |  |  | Depth : 0.0m - 1.5m | B5.33 31 00.11
B5.33 31 00.12 | عمق 1.51 - 2.5 م | m | 317 |  |  | Depth: 1.51m - 2.5m | B5.33 31 00.12
B5.33 31 00.13 | عمق 2.51 -3.5 م | m | 10 |  |  | Depth: 2.51m - 3.5m | B5.33 31 00.13
B5.33 31 00.14 | عمق 3.51 - 4.5 م | m | 606 |  |  | Depth: 3.51m - 4.5m | B5.33 31 00.14
B5.33 31 00.15 | عمق 4.51 - 5.5 م | m | 528 |  |  | Depth: 4.51m - 5.5m | B5.33 31 00.15
B5.33 31 00.16 | عمق اكبر من 5.51 م | m | 10 |  |  | Depth: Greater than 5.51m | B5.33 31 00.16
| يتم ترحيل شبكة الصرف الصحي - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO SEWERAGE NETWORK - COLLECTION
| أعمال المواسير - المواسير |  |  |  | 0 | PIPEWORK-PIPES
33 31 00 | مواسير GRP: الصلابة 5000 حتى عمق 3.5 م الصلابة 10000 لأي عمق أكثر من 3.5 م |  |  |  | 0 | Glass Reinforced Plastic (GRP): SN 5000 up to depth 3.5 m SN 10000 depth more than 3.5 m | 33 31 00
| قطر 300 مم |  |  |  | 0 | 300mm Diameter
B5.33 31 00.17 | عمق 0.0 - 1.5 م | m | 70 |  |  | Depth: 0.0m - 1.5m | B5.33 31 00.17
B5.33 31 00.18 | عمق 1.50 - 2.5 م | m | 776 |  |  | Depth: 1.50m - 2.5m | B5.33 31 00.18
B5.33 31 00.19 | عمق 2.51 - 3.5 م | m | 733 |  |  | Depth: 2.51m - 3.5m | B5.33 31 00.19
B5.33 31 00.20 | عمق 3.51 - 4.5 م | m | 200 |  |  | Depth: 3.51m - 4.5m | B5.33 31 00.20
B5.33 31 00.21 | عمق 4.51 - 5.5 م | m | 445 |  |  | Depth: 4.51m - 5.5m | B5.33 31 00.21
B5.33 31 00.22 | عمق اكبر من 5.51 م | m | 10 |  |  | Depth: Greater than 5.51m | B5.33 31 00.22
| قطر 400 مم |  | 0 |  |  | 400mm Diameter
B5.33 31 00.23 | عمق 0.0 - 1.5 م | m | 10 |  |  | Depth: 0.0m - 1.5m | B5.33 31 00.23
B5.33 31 00.24 | عمق 1.50 - 2.5 م | m | 10 |  |  | Depth: 1.50m - 2.5m | B5.33 31 00.24
B5.33 31 00.25 | عمق 2.51 - 3.5 م | m | 10 |  |  | Depth: 2.51m - 3.5m | B5.33 31 00.25
B5.33 31 00.26 | عمق 3.50 - 4.5 م | m | 425 |  |  | Depth: 3.50m - 4.5m | B5.33 31 00.26
B5.33 31 00.27 | عمق 4.51 - 5.5 م | m | 612 |  |  | Depth: 4.51m - 5.5m | B5.33 31 00.27
B5.33 31 00.28 | عمق اكبر من 5.51 م | m | 10 |  |  | Depth: Greater than 5.51m | B5.33 31 00.28
| قطر 500 مم |  | 0 |  |  | 500mm Diameter
B5.33 31 00.29 | عمق 0.0 - 1.5 م | m | 10 |  |  | Depth: 0.0m - 1.5m | B5.33 31 00.29
B5.33 31 00.30 | عمق 1.50 - 2.5 م | m | 10 |  |  | Depth: 1.50m - 2.5m | B5.33 31 00.30
B5.33 31 00.31 | عمق 2.51 - 3.5 م | m | 10 |  |  | Depth: 2.51m - 3.5m | B5.33 31 00.31
B5.33 31 00.32 | عمق 3.51 - 4.5 م | m | 924 |  |  | Depth: 3.51m - 4.5m | B5.33 31 00.32
B5.33 31 00.33 | عمق اكبر من 5.51 م | m | 10 |  |  | Depth: Greater than 5.51m | B5.33 31 00.33
| يتم ترحيل شبكة الصرف الصحي - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO SEWERAGE NETWORK - COLLECTION
| أعمال المواسير - المواسير |  |  |  | 0 | PIPEWORK-PIPES
33 31 00 | مواسير GRP: الصلابة 5000 حتى عمق 3.5 م الصلابة 10000 لأي عمق أكثر من 3.5 م |  |  |  | 0 | Glass Reinforced Plastic (GRP): SN 5000 up to depth 3.5 m SN 10000 depth more than 3.5 m | 33 31 00
| قطر 600 مم |  | 0 |  |  | 600mm Diameter
B5.33 31 00.34 | عمق 2.51 - 3.5 م | m | 98 |  |  | Depth: 2.51m - 3.5m | B5.33 31 00.34
B5.33 31 00.35 | عمق 3.51 - 4.5 م | m | 392 |  |  | Depth: 3.51m - 4.5m | B5.33 31 00.35
B5.33 31 00.36 | عمق 4.51 - 5.5 م | m | 372 |  |  | Depth: 4.51m - 5.5m | B5.33 31 00.36
B5.33 31 00.37 | عمق 5.51 - 6.5 م | m | 373 |  |  | Depth: 5.51m - 6.5m | B5.33 31 00.37
B5.33 31 00.38 | عمق اكبر من 6.51 م | m | 10 |  |  | Depth: Greater than 6.51m | B5.33 31 00.38
| أعمال المواسير - المانهولات وملحقات أعمال المواسير |  |  |  | 0 | PIPEWORK ANCILLARIES
33 05 13 | غرف المانهولات |  |  |  | 0 | Manholes | 33 05 13
| غرف مانهولات (مطابق) بقطر داخلى 1200 مم |  |  |  | 0 | Precast Manhole ring 1200 mm internal dia.
B5.33 05 13.01 | مانهول بعمق 0-1.5 م | nr | 87 |  |  | MH depth 0 - 1.5m | B5.33 05 13.01
B5.33 05 13.02 | مانهول بعمق 1.51-2.5 م | nr | 113 |  |  | MH depth 1.51 - 2.5m | B5.33 05 13.02
B5.33 05 13.03 | مانهول بعمق 1.51-2.5 م مع سقوط خلفي | nr | 2 |  |  | MH depth 1.51 - 2.5m with back drop | B5.33 05 13.03
B5.33 05 13.04 | مانهول بعمق 2.51-3.5 م | nr | 45 |  |  | MH depth 2.51 - 3.5m | B5.33 05 13.04
B5.33 05 13.05 | مانهول بعمق 2.51-3.5 م مع سقوط خلفي | nr | 21 |  |  | MH depth 2.51 - 3.5m with back drop | B5.33 05 13.05
B5.33 05 13.06 | مانهول بعمق 3.51-4.5 م | nr | 11 |  |  | MH depth 3.51 -4.5m | B5.33 05 13.06
B5.33 05 13.07 | مانهول بعمق 3.51-4.5 م مع سقوط خلفي | nr | 14 |  |  | MH depth 3.51 -4.5m with back drop | B5.33 05 13.07
B5.33 05 13.08 | مانهول بعمق 4.51-5.5 م | nr | 25 |  |  | MH depth 4.51 -5.5m | B5.33 05 13.08
B5.33 05 13.09 | مانهول بعمق 4.51-5.5 م مع سقوط خلفي | nr | 18 |  |  | MH depth 4.51 -5.5m with back drop | B5.33 05 13.09
B5.33 05 13.10 | مانهول بعمق 5.51-6.5 م | nr | 2 |  |  | MH depth 5.51 -6.5m | B5.33 05 13.10
B5.33 05 13.11 | مانهول بعمق 5.51-6.5 م مع سقوط خلفي | nr | 3 |  |  | MH depth 5.51 -6.5m with back drop | B5.33 05 13.11
B5.33 05 13.12 | مانهول بعمق 6.51-7.5 م | nr | 1 |  |  | MH depth 6.51 -7.5m | B5.33 05 13.12
| غرف مانهولات (مطابق) بقطر داخلى 1600 مم |  | 0 |  |  | Precast Manhole ring 1600 mm internal dia.
B5.33 05 13.13 | مانهول بعمق 5.51-6.5 م | nr | 1 |  |  | MH depth 5.51 -6.5m | B5.33 05 13.13
B5.33 05 13.14 | مانهول بعمق 6.51-7.5 م | nr | 1 |  |  | MH depth 6.51 -7.5m | B5.33 05 13.14
| يتم ترحيل شبكة الصرف الصحي - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO SEWERAGE NETWORK - COLLECTION
شبكة صرف مياه الأمطار |  |  |  |  | 0 |  | STORM WATER DRAINAGE NETWORK
0 | الفئة (I): أعمال المواسير - المواسير |  |  |  | 0 | CLASS I: PIPEWORK-PIPES
33 42 11 | المواسير الدائرية (GRP) |  |  |  | 0 | Circular pipes (GRP) | 33 42 11
0 | مواسير GRP: الصلابة 5000 حتى عمق 3.5 م الصلابة 10000 لأي عمق أكثر من 3.5 م |  |  |  | 0 | Glass Reinforced Plastic (GRP): SN 5000 up to depth 3.5 m SN 10000 depth more than 3.5 m
0 | قطر 400 مم |  |  |  | 0 | 400mm Diameter
B6.33 42 11.01 | عمق 0 - 1.5 م | m | 10430 |  |  | Depth: 0.0m - 1.5m | B6.33 42 11.01
B6.33 42 11.02 | عمق 1.51 - 2.5 م | m | 1715 |  |  | Depth : 1.51m - 2.5m | B6.33 42 11.02
B6.33 42 11.03 | عمق 2.51 - 3.5 م | m | 180 |  |  | Depth : 2.51m - 3.5m | B6.33 42 11.03
B6.33 42 11.04 | عمق 3.51 - 4.5 م | m | 275 |  |  | Depth: 3.51m - 4.5m | B6.33 42 11.04
B5.33 31 00.05 | عمق اكبر من 4.51 م | m | 15 |  |  | Depth: Greater than 4.51m | B5.33 31 00.05
0 | قطر 500 مم |  | 0 |  |  | 500mm Diameter
B6.33 42 11.06 | عمق 0 - 1.5 م | m | 750 |  |  | Depth: 0.0m - 1.5m | B6.33 42 11.06
B6.33 42 11.07 | عمق 1.51 - 2.5 م | m | 165 |  |  | Depth : 1.51m - 2.5m | B6.33 42 11.07
B6.33 42 11.08 | عمق 2.51 - 3.5 م | m | 55 |  |  | Depth : 2.51m - 3.5m | B6.33 42 11.08
B6.33 42 11.09 | عمق 3.51 - 4.5 م | m | 190 |  |  | Depth: 3.51m - 4.5m | B6.33 42 11.09
B6.33 42 11.10 | عمق اكبر من 4.51 م | m | 15 |  |  | Depth: Greater than 4.51m | B6.33 42 11.10
0 | قطر 600 مم |  | 0 |  |  | 600mm Diameter
B6.33 42 11.11 | عمق 0 - 1.5 م | m | 590 |  |  | Depth: 0.0m - 1.5m | B6.33 42 11.11
B6.33 42 11.12 | عمق 1.51 - 2.5 م | m | 1710 |  |  | Depth : 1.51m - 2.5m | B6.33 42 11.12
B6.33 42 11.13 | عمق 2.51 - 3.5 م | m | 360 |  |  | Depth : 2.51m - 3.5m | B6.33 42 11.13
B6.33 42 11.14 | عمق اكبر من 3.51 م | m | 15 |  |  | Depth: Greater than 3.51m | B6.33 42 11.14
0 | يتم ترحيل شبكة صرف مياه الأمطار - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO STORMWATER NETWORK - COLLECTION
33 42 11 | المواسير الدائرية (GRP) |  |  |  | 0 | Circular pipes (GRP) | 33 42 11
0 | مواسير GRP: الصلابة 5000 حتى عمق 3.5 م الصلابة 10000 لأي عمق أكثر من 3.5 م |  |  |  | 0 | Glass Reinforced Plastic (GRP): SN 5000 up to depth 3.5 m SN 10000 depth more than 3.5 m
0 | قطر 700 مم |  | 0 |  |  | 700mm Diameter
B6.33 42 11.15 | عمق 0 - 1.5 م | m | 10 |  |  | Depth: 0.0m - 1.5m | B6.33 42 11.15
B6.33 42 11.16 | عمق 1.5 - 2.5 م | m | 460 |  |  | Depth: 1.50m - 2.5m | B6.33 42 11.16
B6.33 42 11.17 | عمق 2.51 - 3.5 م | m | 190 |  |  | Depth : 2.51m - 3.5m | B6.33 42 11.17
B6.33 42 11.18 | عمق اكبر من 3.51 م | m | 15 |  |  | Depth: Greater than 3.51m | B6.33 42 11.18
0 | قطر 800 مم |  |  |  | 0 | 800mm Diameter
B6.33 42 11.19 | عمق 0 - 1.5 م | m | 10 |  |  | Depth: 0.0m - 1.5m | B6.33 42 11.19
B6.33 42 11.20 | عمق 1.50 - 2.5 م | m | 1405 |  |  | Depth : 1.50m - 2.5m | B6.33 42 11.20
B6.33 42 11.21 | عمق 2.51 - 3.5 م | m | 400 |  |  | Depth : 2.51m - 3.5m | B6.33 42 11.21
B6.33 42 11.22 | عمق اكبر من 3.51 م | m | 15 |  |  | Depth: Greater than 3.51m | B6.33 42 11.22
0 | قطر 900 مم |  | 0 |  |  | 900mm Diameter
B6.33 42 11.23 | عمق 0 - 1.5 م | m | 10 |  |  | Depth: 0.0m - 1.5m | B6.33 42 11.23
B6.33 42 11.24 | عمق 1.50 - 2.5 م | m | 625 |  |  | Depth : 1.50m - 2.5m | B6.33 42 11.24
B6.33 42 11.25 | عمق 2.50 - 3.5 م | m | 180 |  |  | Depth : 2.50m - 3.5m | B6.33 42 11.25
B6.33 42 11.26 | عمق اكبر من 3.51 م | m | 15 |  |  | Depth: Greater than 3.51m | B6.33 42 11.26
0 | يتم ترحيل شبكة صرف مياه الأمطار - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO STORMWATER NETWORK - COLLECTION
33 42 11 | المواسير الدائرية (GRP) |  |  |  | 0 | Circular pipes (GRP) | 33 42 11
0 | مواسير GRP: الصلابة 5000 حتى عمق 3.5 م الصلابة 10000 لأي عمق أكثر من 3.5 م |  |  |  | 0 | Glass Reinforced Plastic (GRP): SN 5000 up to depth 3.5 m SN 10000 depth more than 3.5 m
0 | قطر 1000 مم |  | 0 |  |  | 1000mm Diameter
B6.33 42 11.27 | عمق 0 - 1.5 م | m | 10 |  |  | Depth: 0.0m - 1.5m | B6.33 42 11.27
B6.33 42 11.28 | عمق 1.50 - 2.5 م | m | 10 |  |  | Depth : 1.50m - 2.5m | B6.33 42 11.28
B6.33 42 11.29 | عمق 2.51 - 3.5 م | m | 620 |  |  | Depth : 2.51m - 3.5m | B6.33 42 11.29
B6.33 42 11.30 | عمق 3.51 - 4.5 م | m | 65 |  |  | Depth: 3.51m - 4.5m | B6.33 42 11.30
B6.33 42 11.31 | عمق اكبر من 4.51 م | m | 15 |  |  | Depth: Greater than 4.51m | B6.33 42 11.31
0 | قطر 1200 مم |  | 0 |  |  | 1200mm Diameter
B6.33 42 11.32 | عمق 0 - 1.5 م | m | 10 |  |  | Depth: 0.0m - 1.5m | B6.33 42 11.32
B6.33 42 11.33 | عمق 1.50 - 2.5 م | m | 100 |  |  | Depth : 1.50m - 2.5m | B6.33 42 11.33
B6.33 42 11.34 | عمق 2.51 - 3.5 م | m | 1000 |  |  | Depth: 2.51m - 3.5m | B6.33 42 11.34
B6.33 42 11.35 | عمق 3.51 - 4.5 م | m | 250 |  |  | Depth: 3.51m - 4.5m | B6.33 42 11.35
B6.33 42 11.36 | عمق 4.51 - 5.5 م | m | 315 |  |  | Depth: 4.51m - 5.5m | B6.33 42 11.36
B6.33 42 11.37 | عمق اكبر من 5.51 م | m | 15 |  |  | Depth: Greater than 5.51m | B6.33 42 11.37
0
0 | يتم ترحيل شبكة صرف مياه الأمطار - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO STORMWATER NETWORK - COLLECTION
33 42 11 | المواسير الدائرية (uPVC) |  |  |  | 0 | Circular pipes (uPVC) | 33 42 11
0 | مواسير من البلاستك ( uPVC) من الفئة 4 لزوم مصائد الأمطار |  |  |  | 0 | Class 4 uPVC For catch basins
0 | قطر 300 مم |  |  |  | 0 | 300mm Diameter
B6.33 42 11.38 | عمق 0 - 1.5 م | m | 12550 |  |  | Depth: 0.0m - 1.5m | B6.33 42 11.38
0 | قطر 400 مم |  | 0 |  |  | 400mm Diameter
B6.33 42 11.39 | عمق 0 - 1.5 م | m | 840 |  |  | Depth: 0.0m - 1.5m | B6.33 42 11.39
0 | الفئة (K): أعمال المواسير - المانهولات (مطابق) وملحقات أعمال المواسير |  |  |  | 0 | CLASS K: PIPEWORK-MANHOLES AND PIPEWORK ANCILLARIES
33 05 39 | مانهولات من الخرسانة لدخول المياه |  |  |  | 0 | Inlet Manholes | 33 05 39
0 | مانهول دائري بقطر داخلي 1200 مم |  |  |  | 0 | Precast Manhole ring 1200 mm internal dia.
B6.33 05 39.01 | مانهول بعمق 1.50-2.5 م | nr | 117 |  |  | MH depth 1.50 - 2.5m | B6.33 05 39.01
B6.33 05 39.02 | مانهول بعمق 1.50-2.5 م مع سقوط خلفي | nr | 25 |  |  | MH depth 1.50 - 2.5m With backdrop | B6.33 05 39.02
B6.33 05 39.03 | مانهول بعمق 2.51-3.5 م | nr | 16 |  |  | MH depth 2.51 - 3.5m | B6.33 05 39.03
B6.33 05 39.04 | مانهول بعمق 2.51-3.5 م مع سقوط خلفي | nr | 10 |  |  | MH depth 2.51 - 3.5m With backdrop | B6.33 05 39.04
B6.33 05 39.05 | مانهول بعمق 3.51-4.5 م | nr | 1 |  |  | MH depth 3.51 - 4.5m | B6.33 05 39.05
B6.33 05 39.06 | مانهول بعمق 3.51-4.5 م مع سقوط خلفي | nr | 1 |  |  | MH depth 3.51 - 4.5m With backdrop | B6.33 05 39.06
B6.33 05 39.07 | مانهول بعمق 4.51-5.5 م | nr | 2 |  |  | MH depth 4.51 - 5.5m | B6.33 05 39.07
B6.33 05 39.08 | مانهول بعمق 4.51-5.5 م مع سقوط خلفي | nr | 1 |  |  | MH depth 4.51 - 5.5m With backdrop | B6.33 05 39.08
B6.33 05 39.09 | مانهول بعمق اكبر من 5.51 م | nr | 1 |  |  | MH depth greater than 5.51m | B6.33 05 39.09
0
0 | يتم ترحيل شبكة صرف مياه الأمطار - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO STORMWATER NETWORK - COLLECTION
0 | الفئة (K): أعمال المواسير - المانهولات (مطابق) وملحقات أعمال المواسير |  |  |  | 0 | CLASS K: PIPEWORK-MANHOLES AND PIPEWORK ANCILLARIES
33 05 39 | مانهولات من الخرسانة لدخول المياه |  |  |  | 0 | Inlet Manholes | 33 05 39
0 | مانهول دائري بقطر داخلي 1200 مم بغطاء شبكي |  | 0 |  |  | Precast Manhole ring 1200 mm internal dia. With grated cover
B6.33 05 39.10 | مانهول بعمق 1.50-2.5 م | nr | 18 |  |  | MH depth 1.50 - 2.5m | B6.33 05 39.10
B6.33 05 39.11 | مانهول بعمق 3.50-4.5 م | nr | 1 |  |  | MH depth 3.50 - 4.5m | B6.33 05 39.11
0 | مانهول دائري بقطر داخلي 1500 مم |  | 0 |  |  | Precast Manhole ring 1500 mm internal dia.
B6.33 05 39.12 | مانهول بعمق 1.5-2.5 م | nr | 5 |  |  | MH depth 1.5 - 2.5m | B6.33 05 39.12
B6.33 05 39.13 | مانهول بعمق 2.51-3.5 م | nr | 16 |  |  | MH depth 2.51 - 3.5m | B6.33 05 39.13
B6.33 05 39.14 | مانهول بعمق 2.51-3.5 م مع سقوط خلفي | nr | 12 |  |  | MH depth 2.51 - 3.5m With backdrop | B6.33 05 39.14
B6.33 05 39.15 | مانهول بعمق 3.51-4.5 م | nr | 1 |  |  | MH depth 3.51 - 4.5m | B6.33 05 39.15
B6.33 05 39.16 | مانهول بعمق 3.51-4.5 م مع سقوط خلفي | nr | 2 |  |  | MH depth 3.51 - 4.5m With backdrop | B6.33 05 39.16
0 | مانهول دائري بقطر داخلي 2000 مم |  | 0 |  |  | Precast Manhole ring 2000 mm internal dia.
B6.33 05 39.17 | مانهول بعمق 2.5-3.5 م | nr | 5 |  |  | MH depth 2.51 - 3.5m | B6.33 05 39.17
B6.33 05 39.18 | مانهول بعمق 2.51-3.5 م مع سقوط خلفي | nr | 1 |  |  | MH depth 2.51 - 3.5m With backdrop | B6.33 05 39.18
B6.33 05 39.19 | مانهول بعمق 3.51-4.5 م | nr | 5 |  |  | MH depth 3.51 - 4.5m | B6.33 05 39.19
B6.33 05 39.20 | مانهول بعمق 3.51-4.5 م مع سقوط خلفي | nr | 11 |  |  | MH depth 3.51 - 4.5m With backdrop | B6.33 05 39.20
B6.33 05 39.22 | مانهول بعمق 4.51-5.5 م | nr | 1 |  |  | MH depth 4.51 - 5.5m | B6.33 05 39.22
B6.33 05 39.23 | مانهول بعمق 4.51-5.5 م مع سقوط خلفي | nr | 2 |  |  | MH depth 4.51 - 5.5m With backdrop | B6.33 05 39.23
B6.33 05 39.24 | مانهول بعمق 5.51-6.5 م | nr | 2 |  |  | MH depth 5.51 - 6.5m | B6.33 05 39.24
B6.33 05 39.25 | مانهول بعمق 5.51-6.5 م مع سقوط خلفي | nr | 2 |  |  | MH depth 5.51 - 6.5m With backdrop | B6.33 05 39.25
0 | يتم ترحيل شبكة صرف مياه الأمطار - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO STORMWATER NETWORK - COLLECTION
0 | الفئة (K): أعمال المواسير - المانهولات (مطابق) وملحقات أعمال المواسير |  |  |  | 0 | CLASS K: PIPEWORK-MANHOLES AND PIPEWORK ANCILLARIES
0 | فتحات الدخول أعلي الأنابيب الصندوقية |  |  |  | 0 | Access Opening above the Box coduits
B6.33 05 39.27 | فتحة بأبعاد داخلية 1000*1000 مم وعلي أعماق مختلفة | nr | 31 |  |  | Access opening with dimensions1000*1000 mm at variable depth | B6.33 05 39.27
0 | مانهول مربع الشكل بأبعاد داخلية 3000* 3000 مم |  |  |  |  | Precast Manholes internal diminsion 3000 * 3000 mm
B6.33 05 39.28 | مانهول بعمق 3.0 -4.0 م | nr | 2 |  |  | MH depth 3.0 - 4.0m | B6.33 05 39.28
0 | مصائد الأمطار |  |  |  |  | Concrete catch basin
B6.33 05 39.29 | أحواض تجميع مياه الأمطار Single Catch Basins | nr | 521 |  |  | Single Catch basin | B6.33 05 39.29
B6.33 05 39.30 | أحواض تجميع مياه الأمطار Double Catch Basins | nr | 97 |  |  | Double Catch basin | B6.33 05 39.30
33 42 16 | عبارات/علب صندوقية من الخرسانة الجاهزة وتشمل حوائط التوجيه |  |  |  |  | Precast Concrete Box Culverts/Conduits including the wing walls | 33 42 16
B6.03 30 00.01 | خرسانة عادية للعبارات الصندوقية | m3 | 1020 |  | 0 | Plain Concrete for box culvert | B6.03 30 00.01
B6.03 30 00.02 | خرسانة مسلحة للعبارات الصندوقية شاملة أعمال العزل البيتوميني (يتم قياس حديد التسليح في بند منفصل) | m3 | 10225 |  | 0 | Reinforced Concrete for box culvert including bitumenous coating (Steel Reinforcement is measured separately) | B6.03 30 00.02
B6.03 30 00.03 | حديد تسليح للعبارات الصندوقية وفقا للمخططات وحسب توجيهات المهندس المشرف. | ton | 1015 |  |  | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | B6.03 30 00.03
0 | المصبات الخرسانية |  |  |  |  | Concrete Outfalls
B6.33 05 39.30 | هيكل المصب الخرساني | nr | 1 |  |  | Concrete Outfall structure | B6.33 05 39.30
0 | المدخل الخرساني |  |  |  |  | Concrete inlets
B6.33 05 39.31 | هيكل المدخل الخرساني | nr | 1 |  |  | Concrete inlet structure | B6.33 05 39.31
B6.31 22 00 | ساتر ترابي |  |  |  |  | Dike | B6.31 22 00
B6.31 22 00.01 | ردميات من مواد طبيعيه كما هو موضح بالرسومات. | m³ | 1200 |  |  | Natural ground compacted soil as showin in drawings. | B6.31 22 00.01
B6.31 22 00.02 | أعمال التكسية الحجرية (Grouted Riprap) بسمك لا يقل عن 0.3 م كما هو موضح بالرسومات . | m² | 880 |  |  | Grouted Riprap for protection with thick 0.3 m minimum as shown in drawings. | B6.31 22 00.02
0 |  |  |  |  | 0
0 | يتم ترحيل شبكة صرف مياه الأمطار - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO STORMWATER NETWORK - COLLECTION
B6.31 22 00 | قنوات الصرف المكشوف |  |  |  | 0 | OPEN CHANNEL | B6.31 22 00
B6.31 22 00.01 | إزالة أعمال التدبيش لقاع القناة القائمه | m² | 800 |  |  | Demolition works for the riprap at the existing channel | B6.31 22 00.01
B6.31 22 00.02 | حفريات القنوات السطحية المفتوحة لتصريف الأمطار في جميع أنواع التربة لمختلف الأعماق متضمناً أعمال تسوية وتجهيز السطح بعد الحفر والتخلص من ناتج الحفر | m³ | 2130 |  |  | Channel excavation in all type of soil for any depth including levelling, compaction and disposal of surplus material | B6.31 22 00.02
B6.31 22 00.03 | ردميات من مواد طبيعيه لزوم أرضيه القناه كما هو موضح بالرسومات. | m³ | 16515 |  |  | Natural ground compacted soil for bed as showin in drawings. | B6.31 22 00.03
B6.31 22 00.04 | أعمال التكسية الحجرية (Grouted Riprap) لأسطح القنوات المفتوحة بسمك لا يقل عن 0.3 م كما هو موضح بالرسومات . | m² | 25700 |  |  | Grouted Riprap for protection with thick 0.3 m minimum as shown in drawings. | B6.31 22 00.04
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| يتم ترحيل شبكة صرف مياه الأمطار - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO STORMWATER NETWORK - COLLECTION
أعمال الري والمناظر الطبيعة |  |  |  |  | 0 |  | LANDSCAPE AND IRRIGATION WORKS
| أعمال المناظر الطبيعة |  |  |  | 0 | LANDSCAPE WORKS
| النباتات |  |  |  | 0 | PLANTS
| توريد وزراعة الأشجار والنباتات بما في ذلك أعمال الموقع وأعمال التربة الزراعية |  |  |  | 0 | Supply and planting the trees and plants; including site preparation, agricultural soil
32 92 00 | غطاء التربة |  |  |  | 0 | GROUND COVER AND SHRUBS | 32 92 00
B7.32 92 00.01 | لانتانا مونتيفيديويه | m2 | 8414 |  |  | Lantana montevidensis | B7.32 92 00.01
B7.32 92 00.02 | رجلة الزهور | m2 | 6841 |  |  | Portulaca grandiflora | B7.32 92 00.02
B7.32 92 00.03 | دودونيا فيسكوزا | m2 | 8414 |  |  | Dodonaea viscosa | B7.32 92 00.03
B7.32 92 00.04 | الرغل الملحي | m2 | 6887 |  |  | Atriplex halimus | B7.32 92 00.04
32 93 00 | الأشجار والنخيل |  | 0 |  |  | Trees/ Palms | 32 93 00
B7.32 93 00.01 | شجر جوانب الطريق - شجر المخيط | nr | 252 |  |  | Roadside tree - Cordia sebestena | B7.32 93 00.01
B7.32 93 00.02 | شجر جوانب الطريق - شجر الباركنسونية الحاده | nr | 150 |  |  | Roadside tree - Parkinsonia aculeata | B7.32 93 00.02
B7.32 93 00.03 | شجر جوانب الطريق - شجر السيسام | nr | 157 |  |  | Roadside tree - Dalbergia sissoo | B7.32 93 00.03
B7.32 93 00.04 | شجر جوانب الطريق - شجر أكاسيا أستنوفيلا | nr | 156 |  |  | Roadside tree - Acacia stenophylla | B7.32 93 00.04
B7.32 93 00.05 | شجر جوانب الطريق - شجر الخطمي الساحلي | nr | 598 |  |  | Roadside tree - Hibiscus tiliaceus | B7.32 93 00.05
B7.32 93 00.06 | شجر جوانب الطريق - شجر النيم | nr | 260 |  |  | Roadside tree - Azadirachta indica | B7.32 93 00.06
0
0
0
0
0
0
0
| يتم ترحيل أعمال الري والمناظر الطبيعة - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO LANDSCAPE AND IRRIGATION WORKS - COLLECTION
32 93 34 | بنود متنوعة لأعمال التشجير: |  |  |  | 0 | Miscellaneous landscaping items | 32 93 34
B7.32 93 34.01 | توريد وإنشاء بلاطات خرسانية مسبقة الصب 200*200*60 مم للأرصفة بلون بيج متنوع وتشطيب أملس | m2 | 102460 |  |  | Supply and install Precast concrete block paving for sidewalk, mixed grey colour (light grey + mid grey + dark grey), 200 x 200 x 60mm with shot blasted finish. | B7.32 93 34.01
B7.32 93 34.02 | توريد وإنشاء بلاطات خرسانية مسبقة الصب 200*200*60 مم للتقاطعات بلون بيج فاتح وتشطيب أملس | m2 | 9120 |  |  | Supply and install Precast concrete block paving for main intrsection, colour light grey, 200 x 200 x 60mm with shot blasted finish. | B7.32 93 34.02
B7.32 93 34.03 | توريد وإنشاء بلاطات خرسانية مسبقة الصب 200*200*60 مم للتقاطعات بلون بيج متوسط وتشطيب أملس | m2 | 7150 |  |  | Supply and install Precast concrete block paving for main intrsection, colour mid grey, 200 x 200 x 60mm with shot blasted finish. | B7.32 93 34.03
B7.32 93 34.04 | توريد وإنشاء بلاطات خرسانية مسبقة الصب 200*200*60 مم للتقاطعات بلون بيج غامق متنوع وتشطيب أملس | m2 | 5878 |  |  | Supply and install Precast concrete block paving for main intrsection, colour dark grey, 200 x 200 x 60mm with shot blasted finish. | B7.32 93 34.04
B7.32 93 34.05 | الحصى الصغير: في حجم من 30 - 50 مم كحد أقصى، لون بيج فاتح ومتوسط وغامق، بسمك 70مم | m2 | 13879 |  |  | Gravel, mixed dark beige + medium beige + light beige, 30 - 50mm dia., laid 70mm deep | B7.32 93 34.05
B7.32 93 34.06 | بردورة من الخرسانة 300*500*100 مم (احواض الزراعه والمسطحات الخضراء) تلصق بمونة الأسمنت والرمل سمك 20 مم على فرشة تأسيس من الخرسانة العادية 300مم بسمك 100 مم. وكل الأعمال اللازمة طبقا للمخططات والمواصفات (C01). | m | 91270 |  |  | 300 x 500 x 100 mm concrete heel kerb (shrubs & groundcovers planting bed, sidewalk edge) set on 20 mm thick mortar setting bed on 300mm width, 100mm thick. Plain concrete bed and all the related works as per drawings and specification (C01). | B7.32 93 34.06
| شبكة الري الفرعيه |  | 0 |  |  | SECONDARY IRRIGATION
33 14 11 | مواسير بولي اثيلين عالي الكثافة للشبكة الثانوية |  | 0 |  |  | High Density Polyethylene pipes for secondary network | 33 14 11
B7.33.14.11.01 | مواسير قطر 90 مم عمق 0 إلى 1.5 م - 10 بار | m | 6 |  |  | Pipe line O.D 90 mm PN 10, in depth 0 to 1.5 m | B7.33.14.11.01
B7.33.14.11.02 | مواسير قطر 75 مم عمق 0 إلى 1.5 م - 10 بار | m | 187 |  |  | Pipe line O.D 75 mm PN 10, in depth 0 to 1.5 m | B7.33.14.11.02
B7.33.14.11.03 | مواسير قطر 63 مم عمق 0 إلى 1.5 م - 10 بار | m | 1074 |  |  | Pipe line O.D 63 mm PN 10, in depth 0 to 1.5 m | B7.33.14.11.03
B7.33.14.11.04 | مواسير قطر 50 مم عمق 0 إلى 1.5 م - 10 بار | m | 10129 |  |  | Pipe line O.D 50 mm PN 10, in depth 0 to 1.5 m | B7.33.14.11.04
B7.33.14.11.05 | مواسير قطر32 مم عمق 0 إلى 1.5 م - 10 بار | m | 35599 |  |  | Pipe line O.D 32 mm PN 10, in depth 0 to 1.5 m | B7.33.14.11.05
0
0
0
0
| يتم ترحيل أعمال الري والمناظر الطبيعة - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO LANDSCAPE AND IRRIGATION WORKS - COLLECTION
33 14 19 | التصميم التفصيلي وتوريد وتركيب (بما في ذلك توصيلات الكهرباء والتحكم وبرمجة الأنظمة) واختبار وتهيئة وضمان 18 شهر لشبكة الري ومكوناتها، حسب المخططات ومواصفات المصنع المعتمد والموافقة النهائية من مدن على المواصفات |  |  |  | 0 | Design, Delive, install, wiring, control, programming, testing, commissioning, start-up, 18 months guarantee and warrantee of complete irrigation system as per the design and the specifications of the approved supplier (specifications and materials subject to approval of MODON) | 33 14 19
B7.33.14.19.01 | توريد وتركيب محبس سولينويد بمنظم ضغط ( 1") داخل صندوق PVC يشمل جميع الملحقات من ( وحدة تنظيم الضغط، ومناسب لمياه TSE، وفلتر ، , ومحبس بوابي يدوي، وصندوق الصمام مع الغطاء، وجميع الملحقات الأخرى اللازمة لإكمال الأعمال وفقًا للمواصفات والرسومات.) | nr | 5 |  |  | Supply and installation of Electrical Solenoid Valve ( 1") inside PVC box with all accessories( pressure regulator module, manual bleeding, expedient for TSE water, in line filter, manual valve, valve box with cover, and all other accessories necessary to complete the works in accordance with specification and drawings.) | B7.33.14.19.01
B7.33.14.19.02 | توريد وتركيب محبس سولينويد بمنظم ضغط ( 1.5") داخل صندوق PVC يشمل جميع الملحقات من ( وحدة تنظيم الضغط، ومناسب لمياه TSE، وفلتر ، , ومحبس بوابي يدوي، وصندوق الصمام مع الغطاء، وجميع الملحقات الأخرى اللازمة لإكمال الأعمال وفقًا للمواصفات والرسومات.) | nr | 59 |  |  | Supply and installation of Electrical Solenoid Valve ( 1.5") inside PVC box with all accessories( pressure regulator module, manual bleeding, expedient for TSE water, in line filter, manual valve, valve box with cover, and all other accessories necessary to complete the works in accordance with specification and drawings.) | B7.33.14.19.02
B7.33.14.19.03 | توريد وتركيب محبس سولينويد بمنظم ضغط ( 2") داخل صندوق PVC يشمل جميع الملحقات من ( وحدة تنظيم الضغط، ومناسب لمياه TSE، وفلتر ، , ومحبس بوابي يدوي، وصندوق الصمام مع الغطاء، وجميع الملحقات الأخرى اللازمة لإكمال الأعمال وفقًا للمواصفات والرسومات.) | nr | 14 |  |  | Supply and installation of Electrical Solenoid Valve ( 2") inside PVC box with all accessories ( pressure regulator module, manual bleeding, flow control, expedient for TSE water, in line filter, manual valve, valve box with cover, and all other accessories necessary to complete the works in accordance with specification and drawings.) | B7.33.14.19.03
B7.33.14.19.04 | وصلة ربط سريع مقاس 1 بوصة داخل صندوق PVC | nr | 63 |  |  | Supply and installation of 1" quick coupler valve inside PVC box | B7.33.14.19.04
B7.32.80.00.01 | توريد وتركيب أنابيب LDPE DN 16mm (PN 4) بما في ذلك الوصلات و السوادل و جميع الملحقات الأخرى اللازمة لإكمال الأعمال وفقاً للمواصفات والرسومات. | m | 2000 |  |  | Supply and install LDPE plain pipes DN 16mm (PN 4) including compression fittings, saddles and all other accessories necessary to complete the works in accordance with specifications and drawings. | B7.32.80.00.01
B7.32.80.00.02 | توريد وتركيب منقطات تعويض الضغط ، بما في ذلك جميع الملحقات اللازمة لإكمال الأعمال طبقاً للمواصفات والرسومات. (نقاطات بتصرف 26.5LPH للأشجار ) | nr | 6316 |  |  | Supply and install online pressure compensating emitters, including all accessories necessary to complete the works in accordance with specifications and drawings.(Pressure compensating 37.85LPH emitter for trees) | B7.32.80.00.02
B7.32.80.00.03 | توريد وتركيب أنابيب بولي إيثيلين منخفضة الكثافة بقطر 16 مم (OD) بما في ذلك خط P.C. النقاطات والملحقات و الوصلات ، وجميع المتطلبات اللازمة لإنهاء العمل وفقًا للرسومات (خط التنقيط بتصرف 3.4LPH مع تباعد بين الباعثات 45 سم وتباعد بين الخطوط مسافة 35 سم) | m | 87562 |  |  | Supply and installation of 16 mm dia (O.D.) linear low density polyethylene tubing including in line P.C. emitters, accessories, stakes, takeoff /risers connections from laterals, and all requirements needed to finish work as per drawings (In line dripper line 3.4LPH dripper with spacing between emitters 45 cm and dripline spaced at 35cm ) | B7.32.80.00.03
B7.32.80.00.04 | توريد وتركيب جهاز تحكم متقدم حسب اعتماد المالك، يمكنه الاتصال بنظام التحكم المركزي وقادر على التكامل مع أنظمة المدينة الذكية أو نظام BMS أو نظام Scada ، يمكنه تسجيل معدل التدفق الحقيقي لكل محطة | nr | 2 |  |  | Supply and installation of Advanced Irrigation controller subject to client approval, can connect with Centarl Control system and cabable to integrate with Smart City systems,BMS or Scada system ,Can record the real flow rate per stations, | B7.32.80.00.04
B7.32.80.00.05 | توريد وتركيب وحدة فك ترميز أحادية المحطة لتوصيل الصمام بوحدة التحكم الميدانية بما في ذلك الموصلات المقاومة للمياه وجميع الملحقات الأخرى اللازمة لإكمال الأعمال وفقًا للمواصفات والرسومات (وحدة فك ترميز واحدة) | nr | 78 |  |  | Supply and install single station decoder for valve connection to field controller including waterproof connectors and all other accessories necessary to complete the works in accordance with specifications and drawings (Decoder Single station ). | B7.32.80.00.05
0 | يتم ترحيل أعمال الري والمناظر الطبيعة - إلى التجميع | ريال سعودي |  |  | 0 | CARRIED TO LANDSCAPE AND IRRIGATION WORKS - COLLECTION
| التجميع |  |  |  |  | COLLECTION
| الصفحة 1 |  |  |  | 0 | Page 1
| الصفحة 2 |  |  |  | 0 | Page 2
| الصفحة 3 |  |  |  |  | Page 3
| الصفحة 4 |  |  |  |  | Page 4
| الصفحة 5 |  |  |  |  | Page 5
| الصفحة 6 |  |  |  |  | Page 6
| الصفحة 7 |  |  |  |  | Page 7
| الصفحة 8 |  |  |  |  | Page 8
| الصفحة 9 |  |  |  |  | Page 9
| الصفحة 10 |  |  |  |  | Page 10
| الصفحة 11 |  |  |  | 0 | Page 11
| الصفحة 12 |  |  |  | 0 | Page 12
| الصفحة 13 |  |  |  | 0 | Page 13
| الصفحة 14 |  |  |  | 0 | Page 14
| الصفحة 15 |  |  |  |  | Page 15
| الصفحة 16 |  |  |  | 0 | Page 16
| الصفحة 17 |  |  |  | 0 | Page 17
| الصفحة 18 |  |  |  | 0 | Page 18
| الصفحة 19 |  |  |  | 0 | Page 19
| الصفحة 20 |  |  |  | 0 | Page 20
| الصفحة 21 |  |  |  | 0 | Page 21
| الصفحة 22 |  |  |  | 0 | Page 22
| الصفحة 23 |  |  |  | 0 | Page 23
| الصفحة 24 |  |  |  |  | Page 24
| الصفحة 25 |  |  |  | 0 | Page 25
| الصفحة 26 |  |  |  | 0 | Page 26
| يتم ترحيل ملخص الجدول للملخص الإجمالي | ريال سعودي |  |  | 0 | BILL OF SUMMARY CARRIED TO GRAND TOTAL
check
|  |  |  | Product | 0
|  |  |  | Sum | 0
|  |  |  | Total | 0
|  |  |  | Difference(10) | 10