## DB
MODON - Weekly Progress Report - Construction Projects
| Contract General Information | [7 empty] | Key Dates | [10 empty] | Cost Summary (SR) | [8 empty] | Performance Summary | [11 empty] | Shop Drawings |  |  |  | Material Approval |  |  | Procurement Summary | [6 empty] | Quality Reports | [15 empty] | Key Submittals Approval Status | [9 empty] | Invoices Summary | [13 empty] | Resources at Site | [6 empty] | Safety Statistics | [63 empty] | Primavera P6 Schedule Status | [7 empty] | Testing And Commissioning
Data Date | Project Name | Project ID | Contractor | Consultant | Stage | Status | Modon PM | Project Scope | Contract Award | Contract Sign | Site Handover | Original Completion | Contract Award (Hijri) | Contract Sign (Hijri) | Site Handover (Hijri) | Original Completion (Hijri) | Revised Completion | Committed Completion | Forecast Completion | Original Contract Value | Revised Contract Value | Estimate At Completion Value | Potential Changes | O&M Value | Revised O&M Value | Submitted Invoices (Gross Value) | Total Deduction | Original Plan Value | Plan Value | Earn Value | Phys. Plan Value | Phys. Earn Value | Quality Score | Safety Score | Weekly PV (SAR) | Weekly EV (SAR) | Weekly PV % | Weekly PV % | Weekly Phys PV% | Weekly Phys PV% | Total SD Planned | SD Remaining | SD Pending | Total SD Submittals | Planned Materials Approv | Material Pending Approval | Materila Total Submittals | Total Materials | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Material on Site | Remaining Materials | Material Delivery Completion (Date) | NCR Issued | NCR Closed | NCR Pending | NCR Avg. Closing (Days) | SIR Issued | SIR Closed | SIR Pending | SIR Avg. Closing (Days) | MIR Issued | MIR Closed | MIR Pending | MIR Avg. Closing (Days) | FIR Issued | FIR Closed | FIR Pending | FIR Avg. Closing (Days) | 1 Quality Plan Approval | 2 Quality Plan Last Up | 3 Safety Plan Approval | 4 Safety Plan Last Up | 5 Construction Plan Approval | 6 Baseline Approval | 7 No of Approved Version of Schedule | 8 Last Approved Schedule | 9 BOQ Approval Date | 10 No of Approved Version of BOQ | Total Submitted Invoices | PM Approved Invoices | No of Paid Invoices | No of Pending Invoices | Advance Payment % | Retention % | Deduction / Penalties % | Submitted Invoices (SAR) | PM Approved Invoices (SAR) | Paid Invoices (SAR) | Last Submitted Period | Advance Payment (SAR) | Retention (SAR) | Deduction / Penalties (SAR) | Planned Head Count | Actual Head Count | Saudi Staff | Labor Planned | Labor Actual | Equipment Planned | Equipment Actual | This Week Total Hours Worked | This Week Safe Hours Worked | This Week LTI | This Week MTC (Healed w/o Disability) | This Week MTC (Healed w/ Disability) | This Week Near Miss | This Week First Aid Cases | This Week Fatality | This Week Fire Incident Cases | This Week Vehicle Incident | This Week Property Damages | This Week Induction Training | This Week No.of Internal Training | This Week No.of Internal Audit | This Week No. of Toolbox Talks | This Week Safety Awards/Incentives | This Month Total Hours Worked | This Month Safe Hours Worked | This Month LTI | This Month MTC (Healed w/o Disability) | This Month MTC (Healed w/ Disability) | This Month Near Miss | This Month First Aid Cases | This Month Fatality | This Month Fire Incident Cases | This Month Vehicle Incident | This Month Property Damages | This Month Induction Training | This Month No.of Internal Training | This Month No.of Internal Audit | This Month No. of Toolbox Talks | This Month Safety Awards/Incentives | YTD Total Hours Worked | YTD Safe Hours Worked | YTD LTI | YTD MTC (Healed w/o Disability) | YTD MTC (Healed w/ Disability) | YTD Near Miss | YTD First Aid Cases | YTD Fatality | YTD Fire Incident Cases | YTD Vehicle Incident | YTD Property Damages | YTD Induction Training | YTD No.of Internal Training | YTD No.of Internal Audit | YTD No. of Toolbox Talks | YTD Safety Awards/Incentives | Cum Total Hours Worked | Cum Safe Hours Worked | Cum LTI | Cum MTC (Healed w/o Disability) | Cum MTC (Healed w/ Disability) | Cum Near Miss | Cum First Aid Cases | Cum Fatality | Cum Fire Incident Cases | Cum Vehicle Incident | Cum Property Damages | Cum Induction Training | Cum No.of Internal Training | Cum No.of Internal Audit | Cum No. of Toolbox Talks | Cum Safety Awards/Incentives | Total Act. | Not Started | In Progress | Completed | Critical Path Act.Last Week | Critical Path Act.This Week | Failed start Last Week | Failed start This Week | Planned Start Date | Planned Finish Date | Forecast Start Date | Forecast Finish Date | Actual Start Date | Actual Finish Date | % Completed | Open Comments | Closed Comments
11-10-2026 | Completion Of The Infrastructure Development Of The First Phase In The Third Industrial City In Jeddah | JDH3 - 02 - 008 | ALRAWAF CONTRACTING | egis | Construction | Active | Shuaib A.Alshuaibi | The project includes Completion of works construction of Sewage piping network with manhole Construction.Construction of a Stormwater piping network with catch basins and manholes which will be connected to pond. Construction of Irrigation Network, inculding pipes, valve chambers. Potable water piping network including pipes and valve chambers. 13.8 KV medium voltage cable. Installation of street lighting poles along main roads.Execution of the communication network, including the installation of underground ducts and the extension of communication cables to provide telecom and data services to the site. Completion and preparation of internal and external roads, including asphalt layers and sidewalks. | 2024-06-26 | 2024-07-22 | 2024-07-29 | 2026-07-28 | 20-12-1445 | 16-1-1446 | 23-1-1446 | 14-2-1448 | 2026-09-26 | 2026-09-26 | 2026-11-15 | 319744875.73 | 319744875.73 | 319744875.73 | 0 | 0 | 0 | 250214132.9388 | -25281413.2939 | 100% | 100% | 98.76% | 99.93% | 98.91% | 0.90552 | 0.81818 | 0 | 467114.68 | 0% | 0.1461% | 0% | 0.08117% | 2539 | 24 | 14 | 2518 | 78 | 36 | 78 | 20 | 20 | 12 | 8 | 10 | 0 | 0 | 102 | 99 | 3 | 7 | 187 | 177 | 10 | 5 | 357 | 355 | 2 | 0 | 30963 | 30863 | 100 | 0 | 2024-12-28 | 2024-12-28 | 2024-08-19 | 2024-10-17 | 2025-03-27 | 2024-08-29 | 3 | 2024-10-21 | 2024-09-03 | 1 | 0 | 23 | 0 | 0 | 0.1 | 0 | 0.00081315 | 250214132.9388 | 246537903.1817 | 0 | 2026-08-31 | 31974487.573 | 0 | -260000 | 0 | 1092 | 0 | 0 | 92 | 167 | 135 | 22920 | 22920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 8 | 0 | 97050 | 97050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 34 | 0 | 1866079 | 1866079 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 1 | 0 | 96 | 145 | 0 | 3181 | 0 | 2210362 | 2210362 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 1 | 0 | 223 | 178 | 0 | 3335 | 0 | 9236 | 141 | 75 | 9020 | 215 | 216 | 366 | 324 | [6 empty] | 0% | 0 | 0

## Weekly Progress Report
MODON - Weekly Progress Report - Construction Projects | [30 empty] | Data Date | 11-10-2026
Contract General Information | [5 empty] | Key Dates | [5 empty] | Cost Summary (SR) | [7 empty] | Performance Summary | [5 empty] | Project Scope
Project Name | Completion Of The Infrastructure Development Of The First Phase In The Third Industrial City In Jeddah |  |  |  |  | Contract Award | 2024-06-26 | Contract Award (Hijri) | 20-12-1445 | Revised Completion | 2026-09-26 | Original Contract Value |  | 319744875.73 |  | O&M Value |  | 0 | EAC | Plan Value | 100% | Phys. Plan Value | 99.93% | Quality Score | 90.55% | The project includes Completion of works construction of Sewage piping network with manhole Construction.Construction of a Stormwater piping network with catch basins and manholes which will be connected to pond. Construction of Irrigation Network, inculding pipes, valve chambers. Potable water piping network including pipes and valve chambers. 13.8 KV medium voltage cable. Installation of street lighting poles along main roads.Execution of the communication network, including the installation of underground ducts and the extension of communication cables to provide telecom and data services to the site. Completion and preparation of internal and external roads, including asphalt layers and sidewalks.
Project ID | JDH3 - 02 - 008 |  | Stage | Construction |  | Contract Sign | 2024-07-22 | Contract Sign (Hijri) | 16-1-1446 | Committed Completion | 2026-09-26 | Revised Contract Value |  | 319744875.73 | EAC | Revised O&M Value |  | 0 | #REF! | Earn Value | 98.76% | Phys. Earn Value | 98.91% |  | ¢¢¢¢¢ ¢¢¢¢£
Contractor | ALRAWAF CONTRACTING |  | Status | Active |  | Site Handover | 2024-07-29 | Site Handover (Hijri) | 23-1-1446 | Forecast Completion | 2026-11-15 | Estimate At Completion Value |  | 319744875.73 | #REF! | Submitted Invoices (Gross Value) |  | 250214132.9388 |  | Variance | -1.244% | Variance | -1.02% | Safety Score | 81.82%
Consultant | egis |  | Modon PM | Shuaib A.Alshuaibi |  | Original Completion | 2026-07-28 | Original Completion (Hijri) | 14-2-1448 | Variance | -50 | Potential Changes |  | 0 |  | Total Deduction |  | -25281413.2939 |  | SPI | 0.98756 | SPI | 0.98979 |  | ¢¢¢¢¢ ¢¢¢££
Progress Overview
Earned Value Progress (SAR) | [13 empty] | Physical Progress (Effort) | [11 empty] | Earned Value Progress (%)
WBS |  | BOQ Value (SAR) | % Wt. | Weekly (SAR) |  | To Date (SAR) | [7 empty] | Budgeted | % Wt. | Weekly Physical Progress |  |  |  | To Date Physical Progress
|  |  |  | Planned | Earned | Revised Plan | Revised Plan | Earned | Revised Plan | Revised Plan | Earned % | Variance | SPI | (Manhours) |  | Planned | Earned | Plan % | Earned % | Planned | Earned | Plan % | Earned % | Variance | SPI
JDH3-02-008-Authorities Permits & Approval - AT |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | 0% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
JDH3-02-008-Engineering |  | 9592346.27 | 3% | 0 | 0 | 9592346.27 | 9592346.27 | 9592346.27 | 100% | 100% | 100% | 0% | 1 | 0 | 0% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
JDH3-02-008-Procurement |  | 63948975.15 | 20% | 0 | 0 | 63948975.15 | 63948975.15 | 63948975.15 | 100% | 100% | 100% | 0% | 1 | 0 | 0% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
JDH3-02-008-Construction |  | 214229066.74 | 67% | 0 | 245364.71 | 214229066.75 | 214229066.75 | 211868512.08 | 100% | 100% | 98.9% | -1.102% | 0.98898 | 48045 | 100% | 0 | 39 | 0% | 0.08117% | 48012 | 47522 | 99.93% | 98.91% | -1.02% | 0.98979
Pond and Swales - PS |  | 27026697.61 | 8.453% | 0 | 0 | 27026697.61 | 27026697.61 | 27026697.61 | 100% | 100% | 100% | 0% | 1 | 3720 | 7.743% | 0 | 0 | 0% | 0% | 3720 | 3720 | 100% | 100% | 0% | 1
High Mast |  | 2003227.67 | 0.6265% | 0 | 0 | 2003227.67 | 2003227.67 | 2003227.67 | 100% | 100% | 100% | 0% | 1 | 1222 | 2.543% | 0 | 0 | 0% | 0% | 1222 | 1222 | 100% | 100% | 0% | 1
ELDREES |  | 353857.85 | 0.1107% | 0 | 0 | 353857.85 | 353857.85 | 353857.85 | 100% | 100% | 100% | 0% | 1 | 125 | 0.2602% | 0 | 0 | 0% | 0% | 125 | 125 | 100% | 100% | 0% | 1
MR |  | 73833427.39 | 23.09% | 0 | 0 | 73833427.4 | 73833427.4 | 73419906.67 | 100% | 100% | 99.44% | -0.5601% | 0.9944 | 17520 | 36.47% | 0 | 0 | 0% | 0% | 17507 | 17409 | 99.93% | 99.37% | -0.5594% | 0.9944
Z01 |  | 12724318.75 | 3.98% | 0 | 0 | 12724318.75 | 12724318.75 | 12724318.75 | 100% | 100% | 100% | 0% | 1 | 2771 | 5.768% | 0 | 0 | 0% | 0% | 2770 | 2771 | 99.96% | 100% | 0.03609% | 1.0004
Z02 |  | 1453405.84 | 0.4546% | 0 | 74152.78 | 1453405.84 | 1453405.84 | 1268023.88 | 100% | 100% | 87.24% | -12.76% | 0.87245 | 484 | 1.007% | 0 | 11 | 0% | 2.273% | 484 | 457 | 100% | 94.42% | -5.579% | 0.94421
Z02-1 |  | 10584845.88 | 3.31% | 319 | 0 | 10584845.88 | 10584845.88 | 10584845.88 | 100% | 100% | 100% | 0% | 1 | 2709 | 5.638% | 0 | 0 | 0% | 0% | 2693 | 2709 | 99.41% | 100% | 0.5906% | 1.0059
Z02-2 |  | 11951476.53 | 3.738% | 0 | 0 | 11951476.53 | 11951476.53 | 11951476.53 | 100% | 100% | 100% | 0% | 1 | 3089 | 6.429% | 0 | 0 | 0% | 0% | 3089 | 3089 | 100% | 100% | 0% | 1
Z03 |  | 709820.88 | 0.222% | 0 | 0 | 709820.88 | 709820.88 | 709820.88 | 100% | 100% | 100% | 0% | 1 | 378 | 0.7868% | 0 | 0 | 0% | 0% | 378 | 378 | 100% | 100% | 0% | 1
Z04 |  | 791520.69 | 0.2475% | 0 | 0 | 791520.69 | 791520.69 | 582653.1 | 100% | 100% | 73.61% | -26.39% | 0.73612 | 337 | 0.7014% | 0 | 0 | 0% | 0% | 337 | 310 | 100% | 91.99% | -8.012% | 0.91988
Z05 |  | 6381167.02 | 1.996% | 0 | 102028.39 | 6381167.02 | 6381167.02 | 5519896.28 | 100% | 100% | 86.5% | -13.5% | 0.86503 | 3703 | 7.707% | 0 | 13 | 0% | 0.3511% | 3703 | 3458 | 100% | 93.38% | -6.616% | 0.93384
Z06 | 1988934.425 | 15215701.87 | 4.759% | 0 | 43378.29 | 15215701.87 | 15215701.87 | 15151456 | 100% | 100% | 99.58% | -0.4222% | 0.99578 | 3016 | 6.277% | 0 | 8 | 0% | 0.2653% | 3016 | 3004 | 100% | 99.6% | -0.3979% | 0.99602
Z07 |  | 14082634.67 | 4.404% | 0 | 0 | 14082634.67 | 14082634.67 | 14082634.67 | 100% | 100% | 100% | 0% | 1 | 2682 | 5.582% | 0 | 0 | 0% | 0% | 2682 | 2682 | 100% | 100% | 0% | 1
Z07-1 |  | 9569376.8 | 2.993% | 0 | 0 | 9569376.8 | 9569376.8 | 9569376.8 | 100% | 100% | 100% | 0% | 1 | 2065 | 4.298% | 0 | 0 | 0% | 0% | 2065 | 2065 | 100% | 100% | 0% | 1
Z08 |  | 1069834.54 | 0.3346% | 0 | 0 | 1069834.54 | 1069834.54 | 744135.82 | 100% | 100% | 69.56% | -30.44% | 0.69556 | 339 | 0.7056% | 0 | 0 | 0% | 0% | 339 | 296 | 100% | 87.32% | -12.68% | 0.87316
Z09 |  | 5049850.44 | 1.579% | 0 | 16732.15 | 5049850.44 | 5049850.44 | 4963978.18 | 100% | 100% | 98.3% | -1.7% | 0.983 | 886 | 1.844% | 0 | 3 | 0% | 0.3386% | 884 | 872 | 99.77% | 98.42% | -1.354% | 0.98643
Z10 | 3977868.85 | 8833596.85 | 2.763% | 0 | 0 | 8833596.85 | 8833596.85 | 8666952.26 | 100% | 100% | 98.11% | -1.886% | 0.98114 | 1532 | 3.189% | 0 | 0 | 0% | 0% | 1532 | 1511 | 100% | 98.63% | -1.371% | 0.98629
Z11 |  | 201779.17 | 0.06311% | 0 | 0 | 201779.17 | 201779.17 | 192096.05 | 100% | 100% | 95.2% | -4.799% | 0.95201 | 314 | 0.6536% | 0 | 0 | 0% | 0% | 314 | 313 | 100% | 99.68% | -0.3185% | 0.99682
Z13 |  | 5395935.48 | 1.688% | 0 | 0 | 5395935.48 | 5395935.48 | 5395935.48 | 100% | 100% | 100% | 0% | 1 | 526 | 1.095% | 0 | 0 | 0% | 0% | 526 | 526 | 100% | 100% | 0% | 1
CCTV |  | 5075749.66 | 1.587% | 0 | 0 | 5075749.66 | 5075749.66 | 5075749.66 | 100% | 100% | 100% | 0% | 1 | 9 | 0.01873% | 0 | 0 | 0% | 0% | 9 | 9 | 100% | 100% | 0% | 1
New Scope |  | 1920841.16 | 0.6007% | 0 | 9073.11 | 1920841.16 | 1920841.16 | 1881472.05 | 100% | 100% | 97.95% | -2.05% | 0.9795 | 617 | 1.284% | 0 | 3 | 0% | 0.4862% | 617 | 595 | 100% | 96.43% | -3.566% | 0.96434
JDH3-02-008-Close Out |  | 31974487.57 | 10% | 0 | 221749.97 | 31974487.57 | 31974487.57 | 30357173.38 | 100% | 100% | 94.94% | -5.058% | 0.94942 | 0 | 0% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
| Total | 319744875.73 | 100% | 0 | 467114.68 | 319744875.74 | 319744875.74 | 315767006.88 | 100% | 100% | 98.76% | -1.244% | 0.98756 | 48045 | 100% | 0 | 39 | 0% | 0.08117% | 48012 | 47522 | 99.93% | 98.91% | -1.02% | 0.98979
Construction Milestones
[26 empty] | Item No. | Milestones |  | Original (Baseline) | Latest Plan | Forecast | Status | Days Change
[26 empty] | 1 | Award Date |  | 2024-06-26 | 2024-06-26 | 2024-06-26 | A | 0
[26 empty] | 2 | Contract Sign Date |  | 2024-07-22 | 2024-07-22 | 2024-07-22 | A | 0
[26 empty] | 3 | Site Handover Date |  | 2024-07-29 | 2024-07-29 | 2024-07-29 | A | 0
[26 empty] | 4 | Complete Mobilization |  | 2024-09-03 | 2024-09-03 | 2024-10-26 | A | 0
[26 empty] | 5 | Complete existing condition survey, submission of Final Reports |  | 2025-09-07 | 2025-07-23 | 2025-07-23 | A | 0
[26 empty] | 6 | Complete Earthworks |  | 2026-07-07 | 2026-07-05 | 2026-07-02 | F | 3
[6 empty] | 20000000 | [19 empty] | 7 | Complete steel structure errection for all blocks |  | 2026-07-02 | 2026-04-05 | 2026-02-25 | F | 39
[26 empty] | 8 | Complete all Civil Works |  | 2026-07-07 | 2026-07-05 | 2026-07-02 | F | 3
[26 empty] | 9 | Complete Mechanical Works |  | 2025-10-01 | 2026-07-05 | 2026-06-27 | F | 8
Performance overview
Submittals Status | [10 empty] | Quality | [10 empty] | Safety
Shop Drawings | [10 empty] | Quality Reports | [10 empty] | Safety Statistics | [7 empty] | Proactive Vs Reactive Actions Taken
Item Per WBS |  | Total | Total Submitted Drawings |  |  |  |  | Remaining | Pending | Total Submittals | Quality Reports |  | Issued | Closed | Pending | Avg. Closing (Days) | Pending |  |  |  |  | Category | Item |  | This Week |  | This Month | Year to Date | Cumulative
|  |  | A | B | C | D | Processed | [9 empty] | 0-10 Days | 11-20 Days | 21-30 Days | 31-60 Days | > 60 Days
Road |  | 1940 | 84 | 1700 | 4 | 138 | 14 | 0 | 14 | 1940 | [11 empty] | General | Total Hours Worked |  | 22920 |  | 97050 | 1866079 | 2210362 |  |  | Proactive | 3736
Infrastructure |  | 437 | 4 | 423 | 8 | 2 | 0 | 0 | 0 | 437 | Non Conformance (NCR) |  | 102 | 99 | 3 | 7 | 1 | 0 | 0 | 0 | 0 |  | Safe Hours Worked |  | 22920 |  | 97050 | 1866079 | 2210362 |  |  | Reactive | 12
Electrical |  | 158 | 21 | 111 | 2 | 0 | 0 | 24 | 0 | 134 | Site Instruction (SIR) |  | 187 | 177 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | Reactive | LTI |  | 0 |  | 0 | 0 | 0
|  | 3 | 0 | 3 | 0 | 0 | 0 |  | 0 | 3 | Material Inspection (MIR) |  | 357 | 355 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | MTC (Healed w/o Disability) |  | 0 |  | 0 | 0 | 0
|  | 1 | 0 | 1 | 3 | 0 | 0 |  | 0 | 4 | Field Inspection (FIR) |  | 30963 | 30863 | 100 | 0 | 0 | 0 | 0 | 0 | 0 |  | MTC (Healed w/ Disability) |  | 0 |  | 0 | 0 | 0
TOTAL |  | 2539 | 109 | 2238 | 17 | 140 | 14 | 24 | 14 | 2518 | Key Submittals Approval Status | [11 empty] | Near Miss |  | 0 |  | 0 | 9 | 11
Material Approval | [10 empty] | 1 Quality Plan Approval |  |  | 2024-12-28 |  | 6 Baseline Approval |  |  |  | 2024-08-29 |  |  | First Aid Cases |  | 0 |  | 0 | 0 | 0 | Total Hours Worked Vs Safe Hours Worked
Item Per WBS |  | Total | Total Submitted Material |  |  |  |  | Remaining to approve | Pending | Total Submittals | 2 Quality Plan Last Up |  |  | 2024-12-28 |  | 7 No of Approved Version of Schedule |  |  |  | 3 |  |  | Fatality |  | 0 |  | 0 | 0 | 0
|  |  | A | B | C | D | Processed | with Designer |  |  | 3 Safety Plan Approval |  |  | 2024-08-19 |  | 8 Last Approved Schedule |  |  |  | 2024-10-21 |  |  | Fire Incident Cases |  | 0 |  | 0 | 0 | 0
Road |  | 35 | 1 | 6 | 2 | 0 | 26 | 0 | 26 | 35 | 4 Safety Plan Last Up |  |  | 2024-10-17 |  | 9 BOQ Approval Date |  |  |  | 2024-09-03 |  |  | Vehicle Incident |  | 0 |  | 0 | 1 | 1
Infrastructure |  | 23 | 14 | 7 | 1 | 0 | 1 | 0 | 1 | 23 | 5 Construction Plan Approval |  |  | 2025-03-27 |  | 10 No of Approved Version of BOQ |  |  |  | 1 |  |  | Property Damages |  | 0 |  | 0 | 0 | 0
Electrical |  | 20 | 1 | 9 | 1 | 0 | 9 | 0 | 9 | 20 | Invoices Summary | [10 empty] | Proactive | Induction Training |  | 0 |  | 0 | 96 | 223
[9 empty] | 0 |  | Total Submitted Invoices |  | 0 | Submitted Invoices (SAR) |  |  | 250214132.9388 |  | Contract Value (SR) | 319744875.73 |  |  | No.of Internal Training |  | 2 |  | 7 | 145 | 178
[11 empty] | PM Approved Invoices |  | 23 | PM Approved Invoices (SAR) |  |  | 246537903.1817 |  | Planned Value (SR) | 319744875.74 |  |  | No.of Internal Audit |  | 0 |  | 0 | 0 | 0
TOTAL |  | 78 | 16 | 22 | 4 | 0 | 36 | 0 | 36 | 78 | No of Paid Invoices |  | 0 | Paid Invoices (SAR) |  |  | 0 |  | Earned Value (SR) | 315767006.88 |  |  | No. of Toolbox Talks |  | 8 |  | 34 | 3181 | 3335
Procurement Summary | [10 empty] | No of Pending Invoices |  | 0 | Last Submitted Period |  |  | 2026-08-31 |  | Submitted (SAR) | 250214132.9388 |  |  | Safety Awards/Incentives |  | 0 |  | 0 | 0 | 0
Item Per WBS |  | Total Materials | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Material on Site | Remaining Materials | Material Delivery Completion (Date) |  |  | Advance Payment % |  | 10% | Advance Payment (SAR) |  |  | 31974487.573 |  | PM Approved (SAR) | 246537903.1817 |  | Latest Contract Change Order Log
|  |  | A | B | C | D | Processed |  |  |  | Retention % |  | 0% | Retention (SAR) |  |  | 0 |  | Total Paid (SAR) | 0
Road |  | 4 | 4 | 3 | 1 | 3 |  |  |  |  | Deduction / Penalties % |  | 0.08131% | Deduction / Penalties (SAR) |  |  | -260000 |  |  |  |  | CCO No. | Date Added | Description of Change |  |  |  |  | Status | Cost | Sch Impact (Months) | Date Approved | Duration
Infrastructure |  | 8 | 8 | 7 | 1 | 7 |  |  |  |  | Resources at Site
Electrical |  | 8 | 8 | 2 | 6 | [5 empty] | Head Count - Manual |  |  |  | Head Count - Non Manual |  |  |  | Total Head Count |  |  | 1 | 2025-07-16 | Revised BOQ |  |  |  |  | Completed | - | - | 2025-07-23 | -
[11 empty] | Planned | Actual | Next Month Forecast | Saudi Staff | Planned | Actual | Next Month Forecast | Saudi Staff | Total Plan | Total Actual | Variance
[11 empty] | 0 | 1092 | 0 | 0 | 0 | 92 | 0 | 0 | 0 | 1184 | 1184
TOTAL |  | 20 | 20 | 12 | 8 | 10 | 0 | 0 |  |  | Manpower Breakdown by Trade | [6 empty] | Major Equipment
Primavera P6 Schedule Status | [10 empty] | Key Trade | Planned | Actual |  |  |  |  | Type | Planned | Actual | Idle
Project Activities Overview | [10 empty] | General Labor | 288 | 139 |  |  |  |  | Excavator | 55 | 49 | 1
Schedule Statistics |  |  |  |  | Active Schedule Activities | [5 empty] | Carpenter | 42 | 39 |  |  |  |  | Loader | 5 | 4 | 0 | Major Quantity Trackers
Total Act. | Not Started | In Progress | Completed | % | Active | Ahead | On | Behind | Flag | 0 | Plumber | 26 | 39 |  |  |  |  | Dozer | 2 | 1 | 0 | Unit | Material |  |  |  |  | Original BOQ Qty | Revised BOQ Qty (Under Review) | Delivered Qty | Remaining | Delivery % | Installed QTY
9236 | 141 | 75 | 9020 | 97.66% | 75 | 9020 | 75 | 66 | 9029 |  | Electrician | 0 | 0 |  |  |  |  | Dumper | 50 | 37 | 1 | m | UPVC 300 mm Dia |  |  |  |  | 28700 | 29079.778 | 29079.778 | 0 | 100% | 29079.778
Critical Path Activities |  |  | Free Float Management (Total) |  |  |  | Failed Start Activities |  |  |  | Steel Fixer | 36 | 39 |  |  |  |  | Fork lift | 2 | 1 | 0 | m | GRP– 400 Dia |  |  |  |  | 4770 | 11757.93 | 11757.93 | 0 | 100% | 11757.93
|  |  | Greater Than 14 Days |  | Less Than 14 Days | [5 empty] | Mason | 38 | 0 |  |  |  |  | Grader | 1 | 0 | 0 | m | GRP– 500 Dia |  |  |  |  | 4350 | 4240.12 | 4240.12 | 0 | 100% | 4240.12
Last Week | This Week | Diff | Last Week | This Week | Last Week | This Week | Last Week | This Week | Flag | 0 | Others | 172 | 133 |  |  |  |  | Other | 52 | 43 | 1 | m | GRP– 600 Dia |  |  |  |  | 5050 | 5965.71 | 5965.71 | 0 | 100% | 5965.71
215 | 216 | -1 | 240 | 267 | 2934 | 2812 | 366 | 324 | 42 |  | Total | 602 | 389 |  |  |  |  | Total | 167 | 135 | 3 | m | GRP– 700 Dia |  |  |  |  | 5550 | 5347.16 | 5347.16 | 0 | 100% | 5347.16
Testing And Commissioning | [15 empty] | Top Issues and Risks
Top 5 Issues
Item | Planned Start Date |  | Planned Finish Date |  | Forecast Start Date |  | Forecast Finish Date |  | Actual Start Date |  | Actual Finish Date |  | % Completed | Open Comments | Closed Comments | Issue No | Date Identified | Issue Description |  |  |  | Responsible | Action Taken |  |  | Mitigation |  |  |  |  | Current Status | Expected/Actual Closure | Duration Elapsed
Mechanical System | 2025-01-27 |  | 2025-12-02 |  | 2025-03-22 |  | 2026-01-25 | [5 empty] | 0% | 0 | 0 | 1 | 2024-09-17 | The surveying in the project was initially conducted by taking random points until an email was sent by the owner on August 27, 2024, stating the need to change the method of collecting survey points. As a result, the work had to be redone, leading to an increase in the workload beyond what was planned, which caused a delay in the project. |  |  |  | Modon | The work is ongoing according to Madon's requirements. | [7 empty] | Closed | 2024-08-27 | 29
Electrical System | 2025-03-13 |  | 2025-08-06 |  |  |  | 2025-09-29 | [5 empty] | 0% | 0 | 0 | 2 | 2024-09-17 | GPS device signal was disconnecting because of bad weather conditions and strong winds, there were delays in the surveying work . |  |  |  | Other | Waiting until the weather improves | [7 empty] | Closed
Fire System | [12 empty] | 0% | 0 | 0 | 3 | 2024-09-17 | RFI There is an issue with the official response, as we have not received all the replies except for some matters related to electricity. |  |  |  | Modon | Acclerate official response | [7 empty] | Closed
Other Testing (Manhole Testing) | [12 empty] | 0% | 0 | 0 | 4 | 2024-09-24 | The As-Built drawings do not match the actual site conditions, which requires excavation with Equipments across the connection area. |  |  |  | Modon | A report on the As-Built status was submitted to the consultant on 19th August 2024 | [7 empty] | Active | 2024-09-30 | 42
Total | [12 empty] | 0% | 0 | 0 | 5 | 2024-09-24 | There was a delay in responding to the RFI. |  |  |  | Modon | There was a delay in responding to the inquiries, which were officially submitted to the consultant via emails starting from 10th August 2024. The inquiries were fully addressed by 12th September 2024 through online meetings. However, we have only received official responses for 51 out of 56 inquiries | [7 empty] | Closed | 2024-09-30 | 51
Formulas:
Remaining = MAX(I88:[Remaining, row above])
10,425,589

## General Information
Weekly Progress Report - Construction Projects |  |  | Data Date | 11-10-2026
Contract General Information
Project Name | Completion Of The Infrastructure Development Of The First Phase In The Third Industrial City In Jeddah |  |  | 11-10-2026
Project ID | JDH3 - 02 - 008
Contractor | ALRAWAF CONTRACTING | [5 empty] | 805 | 790
Consultant | egis
Stage | Construction | [5 empty] | 101.9%
Status | Active
Modon PM | Shuaib A.Alshuaibi
Key Dates
Contract Award Date | 2024-06-26 |  |  |  | تاريخ تسليم الموقع |  |  |  | تاريخ تسليم الموقع
Contract Sign Date | 2024-07-22 |  |  |  | إجمالي قيمة المصروف |  |  |  | إجمالي قيمة المصروف
Site Handover Date | 2024-07-29 |  |  |  | شامل ضريبة القيمة المضافة |  |  |  | شامل ضريبة القيمة المضافة
Original Completion | 2026-07-28 |  |  |  | الحاجة لأوامر تغيير |  |  |  | الحاجة لأوامر تغيير
Contract Award Date (Hijri) | 20-12-1445 |  |  |  | مدة المشروع المستهدفة |  |  |  | مدة المشروع المستهدفة
Contract Sign Date (Hijri) | 16-1-1446 |  |  |  | تاريخ نهاية المشروع المستهدفة |  |  |  | تاريخ نهاية المشروع المستهدفة
Site Handover Date (Hijri) | 23-1-1446 |  |  |  | نسبة المدة المنقضية المستهدفة |  |  |  | نسبة المدة المنقضية المستهدفة
Original Completion (Hijri) | 14-2-1448 |  |  |  | نسبة إنجاز المشروع الفعلية |  |  |  | نسبة إنجاز المشروع الفعلية
Revised Completion Date | 2026-09-26 |  |  |  | النسبة المستهدفة للربع القادم |  |  |  | النسبة المستهدفة للربع القادم
Committed Completion Date | 2026-09-26
Forecast Completion | 2026-11-15 |  |  |  |  | 319744875.7217 |  | 367706607.08
Variance | -50 | [6 empty] | 312550616.018 |  | 319744875.64 | 47961731.346
[8 empty] | 997065.03 |  | 367706606.986
Key Project Submittals | Submission Date | Days taken to approve orginal plan from site handover date
Quality Plan submission | 2024-08-20 | 22
Quality Plan approval | 2024-12-28
Quality Plan Last Update | 2024-12-28
Safety Plan submission | 2024-08-05 | 7
Safety Plan approval | 2024-08-19
Safety Plan Last Update | 2024-10-17
Risk Management Plan submission | 2024-08-20 | 22
Risk Management Plan approval | 2024-09-03
Risk Management Plan Last Update | 2024-10-20
Baseline Schedule submission | 2024-08-17 | 19
Baseline Schedule approval | 2024-08-29
No of Schedule Versions | 3
Last Revised Schedule Approval Date | 2024-10-21
BOQ submission | 2024-08-20 | 22
BOQ approval | 2024-09-03
No of Approved Version of BOQ | 1
Construction Plan submission | 2024-09-03 | 36
Construction Plan Approval | 2025-03-27
Note on D25: AlNuaim, Abdulaziz: As per contract requirments submission of Plans should be 30 days after site handover

## Progress
Project Scope Statement | The project includes Completion of works construction of Sewage piping network with manhole Construction.Construction of a Stormwater piping network with catch basins and manholes which will be connected to pond. Construction of Irrigation Network, inculding pipes, valve chambers. Potable water piping network including pipes and valve chambers. 13.8 KV medium voltage cable. Installation of street lighting poles along main roads.Execution of the communication network, including the installation of underground ducts and the extension of communication cables to provide telecom and data services to the site. Completion and preparation of internal and external roads, including asphalt layers and sidewalks.
[24 empty] | Activity ID | Activity Name | Budgeted Total Cost | Earned Value Cost | Actual Labor Units | Budgeted Labor Units | Planned Value Labor Units | Planned Value Cost | Performance % Complete | Schedule % Complete | Total Float | Start | Finish | BL Project Start | BL Project Finish
Earned Value Progress (SAR) | [9 empty] | Physical Progress (Effort) | [13 empty] | Completion of the Infrastructure development of the 1st phase in the 3rd industrial city in Jeddah |  | 319744875.73 | 315299892.21 | 47483 | 48045 | 48012 | 319744875.74 | 98.61% | 100% | -59 | 29-Jul-24 A | 2026-11-24 | 2024-07-29 | 2026-09-26
WBS |  | BOQ Value (SAR) | % Wt. | Weekly (SAR) |  |  | To Date (SAR) |  |  | Budgeted | % Wt. | Weekly Physical Progress |  | To Date Physical Progress | [9 empty] | JDH3-02-008-Milestones - MI |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | -59 | 29-Jul-24 A | 2026-11-24 | 2024-07-29 | 2026-09-26
|  |  |  | Planned | Earned | Revised Plan | Revised Plan | Earned |  | (Manhours) |  | Planned | Earned | Planned | Earned |  | 0 | 0 | 0 | 0 |  | Planned Value Cost | Earned Value Cost | JDH3-02-008-Mobilization - Mob |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | 29-Jul-24 A | 01-Feb-25 A | 2024-07-29 | 2025-02-01
JDH3-02-008-Authorities Permits & Approval - AT |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | JDH3-02-008-Authorities Permits & Approval - AT | 0 | 0 | 0 | 0 |  | 0 | 0 | JDH3-02-008-Authorities Permits & Approval - AT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | 21-Oct-24 A | 19-Sep-26 A | 2024-10-21 | 2026-09-14
JDH3-02-008-Engineering |  | 9592346.27 | 3% | 0 | 0 | 9592346.27 | 9592346.27 | 9592346.27 |  | 0 | 0% | 0 | 0 | 0 | 0 | JDH3-02-008-Engineering | 0 | 0 | 0 | 0 | JDH3-02-008-Engineering | 0 | 0 | JDH3-02-008-Engineering |  | 9592346.27 | 9592346.27 | 0 | 0 | 0 | 9592346.27 | 100% | 100% | -13 | 05-Aug-24 A | 2026-10-11 | 2024-08-05 | 2026-07-04
JDH3-02-008-Procurement |  | 63948975.15 | 20% | 0 | 0 | 63948975.15 | 63948975.15 | 63948975.15 |  | 0 | 0% | 0 | 0 | 0 | 0 | JDH3-02-008-Procurement | 0 | 0 | 0 | 0 | JDH3-02-008-Procurement | 0 | 0 | JDH3-02-008-Procurement |  | 63948975.15 | 63948975.15 | 0 | 0 | 0 | 63948975.15 | 100% | 100% |  | 10-Oct-24 A | 26-Sep-26 A | 2024-10-10 | 2026-07-27
JDH3-02-008-Construction |  | 214229066.74 | 67% | 0 | 245364.71 | 214229066.75 | 214229066.75 | 211868512.08 |  | 48045 | 100% | 0 | 39 | 48012 | 47522 | JDH3-02-008-Construction | 0 | 48012 | 39 | 47483 | JDH3-02-008-Construction | 0 | 245364.71 | JDH3-02-008-Construction |  | 214229066.74 | 211623147.37 | 47483 | 48045 | 48012 | 214229066.75 | 98.78% | 100% | -31 | 16-Aug-24 A | 2026-10-27 | 2024-08-17 | 2026-09-26
Pond and Swales - PS |  | 27026697.61 | 8.453% | 0 | 0 | 27026697.61 | 27026697.61 | 27026697.61 |  | 3720 | 7.743% | 0 | 0 | 3720 | 3720 | Pond and Swales - PS | 0 | 3720 | 0 | 3720 | Pond and Swales - PS | 0 | 0 | Pond and Swales - PS |  | 27026697.61 | 27026697.61 | 3720 | 3720 | 3720 | 27026697.61 | 100% | 100% |  | 28-Sep-24 A | 25-Dec-25 A | 2024-09-28 | 2025-12-25
High Mast |  | 2003227.67 | 0.6265% | 0 | 0 | 2003227.67 | 2003227.67 | 2003227.67 |  | 1222 | 2.543% | 0 | 0 | 1222 | 1222 | High Mast | 0 | 1222 | 0 | 1222 | High Mast | 0 | 0 | High Mast |  | 2003227.67 | 2003227.67 | 1222 | 1222 | 1222 | 2003227.67 | 100% | 100% | -8 | 20-Aug-25 A | 2026-10-04 | 2025-08-20 | 2026-07-29
ELDREES |  | 353857.85 | 0.1107% | 0 | 0 | 353857.85 | 353857.85 | 353857.85 |  | 125 | 0.2602% | 0 | 0 | 125 | 125 | ELDREES | 0 | 125 | 0 | 125 | ELDREES | 0 | 0 | ELDREES |  | 353857.85 | 353857.85 | 125 | 125 | 125 | 353857.85 | 100% | 100% |  | 10-Jan-26 A | 09-Sep-26 A | 2026-01-10 | 2026-07-12
MR |  | 73833427.39 | 23.09% | 0 | 0 | 73833427.4 | 73833427.4 | 73419906.67 |  | 17520 | 36.47% | 0 | 0 | 17507 | 17409 | MR | 0 | 17507 | 0 | 17409 | MR | 0 | 0 | MR |  | 73833427.39 | 73419906.67 | 17409 | 17520 | 17507 | 73833427.4 | 99.44% | 100% | -14 | 12-Oct-24 A | 2026-10-10 | 2024-10-12 | 2026-09-26
Z01 |  | 12724318.75 | 3.98% | 0 | 0 | 12724318.75 | 12724318.75 | 12724318.75 |  | 2771 | 5.768% | 0 | 0 | 2770 | 2771 | Z01 | 0 | 2770 | 0 | 2771 | Z01 | 0 | 0 | Z01 |  | 12724318.75 | 12724318.75 | 2771 | 2771 | 2770 | 12724318.75 | 100% | 100% | -8 | 14-Sep-24 A | 2026-10-04 | 2024-09-14 | 2026-09-25
Z02 |  | 1453405.84 | 0.4546% | 0 | 74152.78 | 1453405.84 | 1453405.84 | 1268023.88 |  | 484 | 1.007% | 0 | 11 | 484 | 457 | Z02 | 0 | 484 | 11 | 446 | Z02 | 0 | 74152.78 | Z02 |  | 1453405.84 | 1193871.1 | 446 | 484 | 484 | 1453405.84 | 82.14% | 100% | -14 | 16-Aug-25 A | 2026-10-10 | 2025-08-16 | 2026-08-26
Z02-1 |  | 10584845.88 | 3.31% | 0 | 0 | 10584845.88 | 10584845.88 | 10584845.88 |  | 2709 | 5.638% | 0 | 0 | 2693 | 2709 | Z02-1 | 0 | 2693 | 0 | 2709 | Z02-1 | 0 | 0 | Z02-1 |  | 10584845.88 | 10584845.88 | 2709 | 2709 | 2693 | 10584845.88 | 100% | 100% | -16 | 02-Sep-24 A | 2026-10-12 | 2024-09-02 | 2026-09-03
Z02-2 |  | 11951476.53 | 3.738% | 0 | 0 | 11951476.53 | 11951476.53 | 11951476.53 |  | 3089 | 6.429% | 0 | 0 | 3089 | 3089 | Z02-2 | 0 | 3089 | 0 | 3089 | Z02-2 | 0 | 0 | Z02-2 |  | 11951476.53 | 11951476.53 | 3089 | 3089 | 3089 | 11951476.53 | 100% | 100% | -8 | 11-Sep-24 A | 2026-10-04 | 2024-09-11 | 2026-09-12
Z03 |  | 709820.88 | 0.222% | 0 | 0 | 709820.88 | 709820.88 | 709820.88 |  | 378 | 0.7868% | 0 | 0 | 378 | 378 | Z03 | 0 | 378 | 0 | 378 | Z03 | 0 | 0 | Z03 |  | 709820.88 | 709820.88 | 378 | 378 | 378 | 709820.88 | 100% | 100% | -8 | 03-Nov-24 A | 2026-10-04 | 2024-11-03 | 2026-08-23
Z04 |  | 791520.69 | 0.2475% | 0 | 0 | 791520.69 | 791520.69 | 582653.1 |  | 337 | 0.7014% | 0 | 0 | 337 | 310 | Z04 | 0 | 337 | 0 | 310 | Z04 | 0 | 0 | Z04 |  | 791520.69 | 582653.1 | 310 | 337 | 337 | 791520.69 | 73.61% | 100% | -24 | 19-Oct-24 A | 2026-10-20 | 2024-10-19 | 2026-08-23
Z05 |  | 6381167.02 | 1.996% | 0 | 102028.39 | 6381167.02 | 6381167.02 | 5519896.28 |  | 3703 | 7.707% | 0 | 13 | 3703 | 3458 | Z05 | 0 | 3703 | 13 | 3445 | Z05 | 0 | 102028.39 | Z05 |  | 6381167.02 | 5417867.89 | 3445 | 3703 | 3703 | 6381167.02 | 84.9% | 100% | -25 | 25-Jun-25 A | 2026-10-21 | 2025-06-25 | 2026-09-07
Z06 |  | 15215701.87 | 4.759% | 0 | 43378.29 | 15215701.87 | 15215701.87 | 15151456 |  | 3016 | 6.277% | 0 | 8 | 3016 | 3004 | Z06 | 0 | 3016 | 8 | 2996 | Z06 | 0 | 43378.29 | Z06 |  | 15215701.87 | 15108077.71 | 2996 | 3016 | 3016 | 15215701.87 | 99.29% | 100% | -17 | 16-Aug-24 A | 2026-10-13 | 2024-08-17 | 2026-09-26
Z07 |  | 14082634.67 | 4.404% | 0 | 0 | 14082634.67 | 14082634.67 | 14082634.67 |  | 2682 | 5.582% | 0 | 0 | 2682 | 2682 | Z07 | 0 | 2682 | 0 | 2682 | Z07 | 0 | 0 | Z07 |  | 14082634.67 | 14082634.67 | 2682 | 2682 | 2682 | 14082634.67 | 100% | 100% |  | 20-Aug-24 A | 27-Sep-26 A | 2024-08-20 | 2026-09-15
Z07-1 |  | 9569376.8 | 2.993% | 0 | 0 | 9569376.8 | 9569376.8 | 9569376.8 |  | 2065 | 4.298% | 0 | 0 | 2065 | 2065 | Z07-1 | 0 | 2065 | 0 | 2065 | Z07-1 | 0 | 0 | Z07-1 |  | 9569376.8 | 9569376.8 | 2065 | 2065 | 2065 | 9569376.8 | 100% | 100% | -8 | 04-Sep-24 A | 2026-10-04 | 2024-09-04 | 2026-08-29
Z08 |  | 1069834.54 | 0.3346% | 0 | 0 | 1069834.54 | 1069834.54 | 744135.82 |  | 339 | 0.7056% | 0 | 0 | 339 | 296 | Z08 | 0 | 339 | 0 | 296 | Z08 | 0 | 0 | Z08 |  | 1069834.54 | 744135.82 | 296 | 339 | 339 | 1069834.54 | 69.56% | 100% | -31 | 05-Oct-24 A | 2026-10-27 | 2024-10-05 | 2026-09-21
Z09 |  | 5049850.44 | 1.579% | 0 | 16732.15 | 5049850.44 | 5049850.44 | 4963978.18 |  | 886 | 1.844% | 0 | 3 | 884 | 872 | Z09 | 0 | 884 | 3 | 869 | Z09 | 0 | 16732.15 | Z09 |  | 5049850.44 | 4947246.03 | 869 | 886 | 884 | 5049850.44 | 97.97% | 100% | -24 | 15-Nov-25 A | 2026-10-20 | 2025-11-15 | 2026-09-07
Z10 |  | 8833596.85 | 2.763% | 0 | 0 | 8833596.85 | 8833596.85 | 8666952.26 |  | 1532 | 3.189% | 0 | 0 | 1532 | 1511 | Z10 | 0 | 1532 | 0 | 1511 | Z10 | 0 | 0 | Z10 |  | 8833596.85 | 8666952.26 | 1511 | 1532 | 1532 | 8833596.85 | 98.11% | 100% | -11 | 28-Jun-25 A | 2026-10-07 | 2025-06-28 | 2026-09-21
Z11 |  | 201779.17 | 0.06311% | 0 | 0 | 201779.17 | 201779.17 | 192096.05 |  | 314 | 0.6536% | 0 | 0 | 314 | 313 | Z11 | 0 | 314 | 0 | 313 | Z11 | 0 | 0 | Z11 |  | 201779.17 | 192096.05 | 313 | 314 | 314 | 201779.17 | 95.2% | 100% | -28 | 02-Nov-24 A | 2026-10-19 | 2024-11-02 | 2026-09-21
Z13 |  | 5395935.48 | 1.688% | 0 | 0 | 5395935.48 | 5395935.48 | 5395935.48 |  | 526 | 1.095% | 0 | 0 | 526 | 526 | Z13 | 0 | 526 | 0 | 526 | Z13 | 0 | 0 | Z13 |  | 5395935.48 | 5395935.48 | 526 | 526 | 526 | 5395935.48 | 100% | 100% | -8 | 28-Apr-25 A | 2026-10-04 | 2025-04-28 | 2026-09-05
CCTV |  | 5075749.66 | 1.587% | 0 | 0 | 5075749.66 | 5075749.66 | 5075749.66 |  | 9 | 0.01873% | 0 | 0 | 9 | 9 | CCTV | 0 | 9 | 0 | 9 | CCTV | 0 | 0 | CCTV |  | 5075749.66 | 5075749.66 | 9 | 9 | 9 | 5075749.66 | 100% | 100% |  | 08-Oct-25 A | 22-Jan-26 A | 2025-10-08 | 2026-01-22
New Scope |  | 1920841.16 | 0.6007% | 0 | 9073.11 | 1920841.16 | 1920841.16 | 1881472.05 |  | 617 | 1.284% | 0 | 3 | 617 | 595 | New Scope | 0 | 617 | 3 | 592 | New Scope | 0 | 9073.11 | New Scope |  | 1920841.16 | 1872398.94 | 592 | 617 | 617 | 1920841.16 | 97.48% | 100% | -13 | 12-Jul-26 A | 2026-10-09 | 2026-07-02 | 2026-09-24
JDH3-02-008-Close Out |  | 31974487.57 | 10% | 0 | 221749.97 | 31974487.57 | 31974487.57 | 30357173.38 |  | 0 | 0% | 0 | 0 | 0 | 0 | JDH3-02-008-Close Out | 0 | 0 | 0 | 0 | JDH3-02-008-Close Out | 0 | 221749.97 | JDH3-02-008-Close Out |  | 31974487.57 | 30135423.41 | 0 | 0 | 0 | 31974487.57 | 94.25% | 100% | -51 | 15-Oct-25 A | 2026-11-24 | 2025-10-15 | 2026-09-26
Total | Total | 319744875.73 | 100% | 0 | 467114.68 | 319744875.74 | 319744875.74 | 315767006.88 | 0 | 48045 | 100% | 0 | 39 | 48012 | 47522
[7 empty] | 100% | 98.76% | [5 empty] | 99.93% | 98.91%
[20 empty] | Activity ID | Activity Name | Budgeted Total Cost | Earned Value Cost | Actual Labor Units | Budgeted Labor Units | Planned Value Labor Units | Planned Value Cost | Performance % Complete | Schedule % Complete | Total Float | Start | Finish | BL Project Start | BL Project Finish
[20 empty] | Completion of the Infrastructure development of the 1st phase in the 3rd industrial city in Jeddah |  | 319744875.73 | 315767006.89 | 47522 | 48045 | 48012 | 319744875.74 | 98.76% | 100% | -66 | 29-Jul-24 A | 2026-12-01 | 2024-07-29 | 2026-09-26
[20 empty] | JDH3-02-008-Milestones - MI |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | -66 | 29-Jul-24 A | 2026-12-01 | 2024-07-29 | 2026-09-26
[20 empty] | JDH3-02-008-Mobilization - Mob |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | 29-Jul-24 A | 01-Feb-25 A | 2024-07-29 | 2025-02-01
[20 empty] | JDH3-02-008-Authorities Permits & Approval - AT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | 21-Oct-24 A | 19-Sep-26 A | 2024-10-21 | 2026-09-14
[20 empty] | JDH3-02-008-Engineering |  | 9592346.27 | 9592346.27 | 0 | 0 | 0 | 9592346.27 | 100% | 100% | -19 | 05-Aug-24 A | 2026-10-18 | 2024-08-05 | 2026-07-04
[20 empty] | JDH3-02-008-Procurement |  | 63948975.15 | 63948975.15 | 0 | 0 | 0 | 63948975.15 | 100% | 100% |  | 10-Oct-24 A | 26-Sep-26 A | 2024-10-10 | 2026-07-27
[20 empty] | JDH3-02-008-Construction |  | 214229066.74 | 211868512.08 | 47522 | 48045 | 48012 | 214229066.75 | 98.9% | 100% | -38 | 16-Aug-24 A | 2026-11-03 | 2024-08-17 | 2026-09-26
[20 empty] | Pond and Swales - PS |  | 27026697.61 | 27026697.61 | 3720 | 3720 | 3720 | 27026697.61 | 100% | 100% |  | 28-Sep-24 A | 25-Dec-25 A | 2024-09-28 | 2025-12-25
[20 empty] | High Mast |  | 2003227.67 | 2003227.67 | 1222 | 1222 | 1222 | 2003227.67 | 100% | 100% | -15 | 20-Aug-25 A | 2026-10-11 | 2025-08-20 | 2026-07-29
[20 empty] | ELDREES |  | 353857.85 | 353857.85 | 125 | 125 | 125 | 353857.85 | 100% | 100% |  | 10-Jan-26 A | 09-Sep-26 A | 2026-01-10 | 2026-07-12
[20 empty] | MR |  | 73833427.39 | 73419906.67 | 17409 | 17520 | 17507 | 73833427.4 | 99.44% | 100% | -21 | 12-Oct-24 A | 2026-10-17 | 2024-10-12 | 2026-09-26
[20 empty] | Z01 |  | 12724318.75 | 12724318.75 | 2771 | 2771 | 2770 | 12724318.75 | 100% | 100% | -15 | 14-Sep-24 A | 2026-10-11 | 2024-09-14 | 2026-09-25
[20 empty] | Z02 |  | 1453405.84 | 1268023.88 | 457 | 484 | 484 | 1453405.84 | 87.24% | 100% | -21 | 16-Aug-25 A | 2026-10-17 | 2025-08-16 | 2026-08-26
[20 empty] | Z02-1 |  | 10584845.88 | 10584845.88 | 2709 | 2709 | 2693 | 10584845.88 | 100% | 100% | -23 | 02-Sep-24 A | 2026-10-19 | 2024-09-02 | 2026-09-03
[20 empty] | Z02-2 |  | 11951476.53 | 11951476.53 | 3089 | 3089 | 3089 | 11951476.53 | 100% | 100% | -15 | 11-Sep-24 A | 2026-10-11 | 2024-09-11 | 2026-09-12
[20 empty] | Z03 |  | 709820.88 | 709820.88 | 378 | 378 | 378 | 709820.88 | 100% | 100% | -15 | 03-Nov-24 A | 2026-10-11 | 2024-11-03 | 2026-08-23
[20 empty] | Z04 |  | 791520.69 | 582653.1 | 310 | 337 | 337 | 791520.69 | 73.61% | 100% | -31 | 19-Oct-24 A | 2026-10-27 | 2024-10-19 | 2026-08-23
[20 empty] | Z05 |  | 6381167.02 | 5519896.28 | 3458 | 3703 | 3703 | 6381167.02 | 86.5% | 100% | -32 | 25-Jun-25 A | 2026-10-28 | 2025-06-25 | 2026-09-07
[20 empty] | Z06 |  | 15215701.87 | 15151456 | 3004 | 3016 | 3016 | 15215701.87 | 99.58% | 100% | -19 | 16-Aug-24 A | 2026-10-15 | 2024-08-17 | 2026-09-26
[20 empty] | Z07 |  | 14082634.67 | 14082634.67 | 2682 | 2682 | 2682 | 14082634.67 | 100% | 100% |  | 20-Aug-24 A | 27-Sep-26 A | 2024-08-20 | 2026-09-15
[20 empty] | Z07-1 |  | 9569376.8 | 9569376.8 | 2065 | 2065 | 2065 | 9569376.8 | 100% | 100% | -15 | 04-Sep-24 A | 2026-10-11 | 2024-09-04 | 2026-08-29
[20 empty] | Z08 |  | 1069834.54 | 744135.82 | 296 | 339 | 339 | 1069834.54 | 69.56% | 100% | -38 | 05-Oct-24 A | 2026-11-03 | 2024-10-05 | 2026-09-21
[20 empty] | Z09 |  | 5049850.44 | 4963978.18 | 872 | 886 | 884 | 5049850.44 | 98.3% | 100% | -31 | 15-Nov-25 A | 2026-10-27 | 2025-11-15 | 2026-09-07
[20 empty] | Z10 |  | 8833596.85 | 8666952.26 | 1511 | 1532 | 1532 | 8833596.85 | 98.11% | 100% | -18 | 28-Jun-25 A | 2026-10-14 | 2025-06-28 | 2026-09-21
[20 empty] | Z11 |  | 201779.17 | 192096.05 | 313 | 314 | 314 | 201779.17 | 95.2% | 100% | -35 | 02-Nov-24 A | 2026-10-26 | 2024-11-02 | 2026-09-21
[20 empty] | Z13 |  | 5395935.48 | 5395935.48 | 526 | 526 | 526 | 5395935.48 | 100% | 100% | -15 | 28-Apr-25 A | 2026-10-11 | 2025-04-28 | 2026-09-05
[20 empty] | CCTV |  | 5075749.66 | 5075749.66 | 9 | 9 | 9 | 5075749.66 | 100% | 100% |  | 08-Oct-25 A | 22-Jan-26 A | 2025-10-08 | 2026-01-22
[20 empty] | New Scope |  | 1920841.16 | 1881472.05 | 595 | 617 | 617 | 1920841.16 | 97.95% | 100% | -20 | 12-Jul-26 A | 2026-10-16 | 2026-07-02 | 2026-09-24
[20 empty] | JDH3-02-008-Close Out |  | 31974487.57 | 30357173.38 | 0 | 0 | 0 | 31974487.57 | 94.94% | 100% | -57 | 15-Oct-25 A | 2026-12-01 | 2025-10-15 | 2026-09-26
1.01

## Invoice progress
Type of work | This week progress |  |  | Total | 7422216.33
Storm | 498812.4 |  |  | Sewage Network | 0
Box culvert | 0 |  | 498812.4 | Storm Network | 1000000
Open channel | 0 |  | 900000 | Ponds | 0
Sewer | 0 |  |  | Box Culvert | 0
Irrigation | 27733.5 |  |  | Swales
Potable Water | 0 | 1288421 |  | Network
Electrical | 0 |  |  | Catch Basin | 554236
Roads | 36473.4 |  |  | TSE Network | 30815
CCTV Works | 0 |  |  | Potable Water Network
Total | 563019.3 |  |  | Street Lighting Network
Telecommunications Network
|  |  | 0.9 | Road Works | 40526
|  |  |  | CCTV Works | 0

## Weekly Photos (hidden)
|  | Data Date | 11-10-2026
Aggregate Base Coarse at Zone 2-2 | Laying of Asphalt at Zone 2-2
Storm pipe installation at Zone 13 | Potable water pipe installation at Zone 13
Pond excavation at Zone 6 | Pond excavation at Zone 12
Potable water pipe installation at Zone 2-2 | Irrigation line 450mm backilling at Zone 2-2
Open channel rip rap works at Zone 2-1 | Open channel rip rap works at Zone 7
Sewer network excavation at Zone 2-1 L72 | Open channel rip rap works at Zone 01

## Quality
QC OBSERVATIONS CHECKLIST
Project No. |  |  | JDH3-02-008 |  |  | OBS No. | [6 empty] | Inspection Day: |  | 11-10-2026
Project |  |  | Completion of the Infrastructure Development of the 1st Phase in the 3rd Industrial City in Jeddah | [6 empty] | Contractor: Consultant: |  |  | Al-Rawaf Contracting
4 |  | Excellent |  | Quality Management System is being practiced and applies to MODON System | [11 empty] | 90 - 100 |  | QC Overall Score | 90.55% |  |  |  |  | 0% | 100 | 0.22883
3 |  | Good |  | Evidence of compliance with plans and procedures. | [11 empty] | 80 - 89 | [7 empty] | 0 | 89 | 0.20366
2 |  | Average |  | Indication level of compliance with standards but there is room for improvement | [11 empty] | 70 - 79 | [8 empty] | 79 | 0.18078
1 |  | Improve |  | Quality and Control is NOT being managed effectively. Needs Improvement | [11 empty] | ≤ 69 | [8 empty] | 69 | 0.15789
0 |  | N/A |  | Item was not applicable or this item was not reviewed during the inspection. | [11 empty] | Zero | [8 empty] | 100 | 0.22883
No. | Topic |  |  |  |  | E (4) | G (3) | A (2) | I (1) | N/A (0) | No. | Topic |  |  |  | E (4) | G (3) | A (2) | I (1) | N/A (0) |  |  |  |  | 437
[6 empty] | 100% | 89% | 79% | 69% | 100% | [5 empty] | 100% | 89% | 79% | 69% | 100% | 90.55%
1 | Control of Access to Site/Office | [5 empty] | 1 |  |  |  | 30 | QC of Excavation |  |  |  |  | 1 |  | 0 |  | 0.89 | 0.89 | [6 empty] | Item Count | Score | Distributtion
2 | Document Control Administration |  |  |  |  | 1 | 0 |  |  |  | 31 | QC of Roads/Round about |  |  |  |  | 1 | 0 |  | 0 | 1 | 0.89 | [8 empty] | Overall | Relevant
3 | Project Documents and Progress | [5 empty] | 1 |  |  |  | 32 | QC of Interlock & Curbstone | [5 empty] | 1 | 0 | 0 | 0.89 | 0.79 | 4 | 58 | counts |  | 4 | Excellent | 2 | 8 | 3.448% | 5%
4 | Contractor's Quality Plan/CM (Updated and Reviewed) | [5 empty] | 1 | 0 |  |  | 33 | Layers/Backfilling Sampling |  |  |  |  | 1 | 0 |  |  | 0.89 | 0.89 | 3 | 58 | counts |  | 3 | Good | 25 | 75 | 43.1% | 62.5%
5 | MS Log and Paperwork | [5 empty] | 1 |  |  |  | 34 | Pump Stations Units | [7 empty] | 1 | 0.89 | 1 | 2 | 58 | counts |  | 2 | Average | 13 | 26 | 22.41% | 32.5%
6 | RFI, FIR, & MIR Procedure | [5 empty] | 1 |  |  |  | 35 | Quality of Form Work |  |  |  |  | 1 | 0 |  | 0 | 0.89 | 0.89 | 1 | 58 | counts |  | 1 | Improve | 0 | 0 | 0% | 0%
7 | RFI, FIR, & MIR Inventory system | [5 empty] | 1 |  |  |  | 36 | Design Change List | [5 empty] | 1 |  | 0 | 0.89 | 0.79 | 0 | 58 | counts |  | 0 | N/A | 18 | 0 | 31.03% | -
8 | NCRs Control & Procedure | [5 empty] | 1 | 0 |  |  | 37 | Quality of Concrete Placing | [5 empty] | 1 |  | 0 | 0.89 | 0.79 | [5 empty] | Total | 58 | 109 | 100% | 100%
9 | NCR Log | [5 empty] | 1 |  |  |  | 38 | Concrete Surface Finishing | [5 empty] | 1 |  | 0 | 0.89 | 0.79
10 | MODON Standard* | [5 empty] | 1 | 0 |  |  | 39 | Pedestals/Columns/Beams Alignment | [7 empty] | 1 | 0.89 | 1 | [6 empty] | Maz Score Available: | 160 | <- Excludes N/A items
11 | Project Risk Plan/Management* | [6 empty] | 1 |  |  | 40 | Siporex Lifting & Unloading | [7 empty] | 1 | 0.79 | 1
12 | Monthly Quality Reports* | [5 empty] | 1 | 0 |  |  | 41 | Siporex Quality Pre-installation | [7 empty] | 1 | 0.89 | 1
13 | ITP | [5 empty] | 1 | 0 |  |  | 42 | Siporex Finishing Quality | [7 empty] | 1 | 0.89 | 1 | [5 empty] | Total Score |  | Percentage (%)
14 | MODON Weekly Report | [5 empty] | 1 |  |  |  | 43 | Roads / Parking Markings |  |  |  |  | 1 |  |  | 0 | 0.89 | 0.89 |  | 58 |  |  |  | 109 |  | 68.125 |  | %
15 | Design Change Official Paperwork* | [8 empty] | 1 | 44 | QC of Finishing Outdoors | [7 empty] | 1 | 1 | 1 | [5 empty] | Max Score Available
16 | Design Change was Applied* | [8 empty] | 1 | 45 | Quality of Finishing Indoors | [7 empty] | 1 | 1 | 1 | [5 empty] | 160
17 | Material List |  |  |  |  | 0 | 1 | 0 |  |  | 46 | Stairs Quality | [7 empty] | 1 | 0.89 | 1
18 | Pending Material Status | [5 empty] | 1 | 0 |  |  | 47 | Tanks Method Statement Work | [7 empty] | 1 | 0.89 | 1
19 | Lifting Plan* | [6 empty] | 1 |  | 0 | 48 | Electric Rooms | [7 empty] | 1 | 0.79 | 1
20 | DWG Log | [5 empty] | 1 | 0 |  |  | 49 | QC of MCC/ATS Plant Units | [5 empty] | 1 |  |  | 0.89 | 0.79
21 | Invoice Status | [8 empty] | 1 | 50 | Qualified Subcontractor | [5 empty] | 1 | 0 | 0 | 1 | 0.79
22 | Site Handover Letter | [8 empty] | 1 | 51 | Scaffold/Ladders/Slope/Bridge Compliance | [7 empty] | 1 | 1 | 1
23 | Material Testing Results & Certification | [5 empty] | 1 | 0 |  |  | 52 | Protection Applied to Completed Work | [7 empty] | 1 | 0.89 | 1
24 | As Build Drawings Status* | [6 empty] | 1 |  | 0 | 53 | Storage Management in/out Control |  |  |  |  | 1 |  |  |  | 0.79 | 0.89
25 | Calibrated Lab Tools & Equipment |  |  |  |  | 1 | 0 |  |  |  | 54 | Material Control |  |  |  |  | 1 | 0 |  |  | 1 | 0.89
26 | Storage Inventory System | [6 empty] | 1 |  | 0 | 55 | Manholes Storing and Quality |  |  |  |  | 1 | 0 |  | 0 | 0.79 | 0.89
27 | Logistics Plan | [5 empty] | 0 |  |  | 1 | 56 | Reinforced Steel Quality | [5 empty] | 1 |  | 0 | 1 | 0.79
28 | Project Progress Planview | [6 empty] | 1 |  |  | 57 | Safety Overview | [5 empty] | 1 |  |  | 0.79 | 0.79
29 | Sufficient Number of QC Inspectors | [5 empty] | 1 | 0 | 0 |  | 58 | Waste Management Control |  |  |  |  | 0 |  |  | 1 | 0.89 | 1
0
Score
[8 empty] | *QC % |  |  | 90.55%
Prepared by: |  |  |  | Eng.Hassan El Shorbagy(Quality Representative) | [6 empty] | Issued to PM: |  |  | Eng. Mohammed AL-Naggar (PM)
*QC Observations refer only to the practices and documentation observed at time of inspection. The responsibility of the CM and Contractor is to ensure that aspects of Quality are suitably managed. *Scores are a reflection of the general site conditions based upon the findings at the time of the walk through *If Applicable

## Quality-Stat
Quality Reports | [12 empty] | SUMMARY | [7 empty] | SUMMARY
Item |  | Issued | Closed | Pending | Avg. Closing (Days) | Pending | [6 empty] | PLANS | [7 empty] | RFI
[6 empty] | 0-10 Days | 11-20 Days | 21-30 Days | 31-60 Days | > 60 Days |  |  | ITEM | ALL | A | B | C | D | UR |  | ITEM | ALL | Closed | Open
[13 empty] | PLANS | 32 | 1 | 27 | 2 | 1 | 1 |  | RFI CVL | 186 | 186 | 0
Non Conforomance Report (NCR) |  | 102 | 99 | 3 | 7 | 1 | [6 empty] | TOTAL | 32 | 1 | 27 | 2 | 1 | 1 |  | RFI ELE | 24 | 24 | 0
Site Instruction (SI) |  | 187 | 177 | 10 | 5 | 1 | [14 empty] | RFI MEC | 24 | 24 | 0
Material Inspection Report (MIR) |  | 357 | 355 | 2 | [8 empty] | PQA SUBCONTRACTOR | [7 empty] | RFI GEN | 4 | 4 | 0
Work Inspection Report (WIR) |  | 30963 | 30863 | 100 | [8 empty] | ITEM | ALL | A | B | C | D | UR |  | TOTAL | 238 | 238 | 0
[14 empty] | 31 | 0 | 20 | 9 | 2 | 0
Shop Drawings | [12 empty] | TOTAL | 31 | 0 | 20 | 9 | 2 | 0
Item Per WBS |  |  | Total | Total Drawings Submitted |  |  |  |  | Remaining Drawings | Pending | Total Submittals
|  |  |  | A | B | C | D | Processed | with Designer | Submittals With Consultant
Road |  |  | 1940 | 84 | 1700 | 4 | 138 | 14 | 0 | 14 | 1940 | 100% | PQA | [7 empty] | FIR
infrastructure |  | Structural | 437 | 4 | 423 | 8 | 2 | 0 | 0 | 0 | 437 | 100% | ITEM | ALL | A | B | C | D | UR |  | ITEM | ALL | A | B | C | D | UR
Electrical & Telecommunication |  |  | 158 | 21 | 111 | 2 | 0 | 0 | 24 | 0 | 134 | 84.81% | CVL | 60 | 12 | 40 | 5 | 3 | 0 |  | CVL | 14998 | 4727 | 9693 | 182 | 19 | 78
General |  |  | 3 | 0 | 3 | 0 | 0 | 0 |  | 0 | 3 | 100% | ELE | 21 | 1 | 15 | 1 | 4 | 0 |  | ELE | 349 | 125 | 208 | 8 | 7 | 0
SVY |  |  | 1 | 0 | 1 | 3 | 0 | 0 |  | 0 | 4 | 400% | GEN | 0 | 0 | 0 | 0 | 0 | 0 |  | MEC | 2759 | 1079 | 1598 | 29 | 15 | 1
TOTAL |  |  | 2539 | 109 | 2238 | 17 | 140 | 14 | 24 | 14 | 2518 |  | MEC | 24 | 16 | 7 | 1 | 0 | 0 |  | SVY | 12857 | 42 | 11563 | 664 | 14 | 21
[13 empty] | TOTAL | 105 | 29 | 62 | 7 | 7 | 0 |  | TOTAL | 30963 | 5973 | 23062 | 883 | 55 | 100
Material Approval | [12 empty] | MST | [7 empty] | MIR
Item Per WBS |  |  | Total | Total Materials Submitted |  |  |  |  | Remaining to approve | Pending | Total Submittals |  | ITEM | ALL | A | B | C | D | UR |  | ITEM | ALL | A | B | C | D | UR
|  |  |  | A | B | C | D | Processed | with Designer | Submittals With Consultant |  |  | CVL | 9 | 0 | 0 | 0 | 1 | 8 |  | CVL | 125 | 123 | 0 | 2 | 0 | 0
Road |  |  | 35 | 1 | 6 | 2 | 0 | 26 | 0 | 26 | 35 | 100% | ELE | 3 | 0 | 0 | 0 | 0 | 3 |  | ELE | 27 | 27 | 0 | 0 | 0 | 0
infrastructure |  | Structural | 23 | 14 | 7 | 1 | 0 | 1 | 0 | 1 | 23 | 100% | MEC | 5 | 0 | 0 | 0 | 1 | 4 |  | MEC | 205 | 205 | 0 | 0 | 0 | 0
Electrical |  |  | 20 | 1 | 9 | 1 | 0 | 9 | 0 | 9 | 20 | 100%
[10 empty] | 0 |  |  | TOTAL | 17 | 0 | 0 | 0 | 2 | 15 |  | TOTAL | 357 | 355 | 0 | 2 | 0 | 0
TOTAL |  |  | 78 | 16 | 22 | 4 | 0 | 36 | 0 | 36 | 78 | 100% | SDW | [7 empty] | INS
[13 empty] | ITEM | ALL | A | B | C | D | UR |  | ITEM | ALL | A | B | C | D | UR | Not Respond
Procurement Summary | [12 empty] | CVL | 1940 | 84 | 1700 | 4 | 138 | 14 |  | CVL | 7 | 1 | 6 | 0 | 0 | 0 | 0
Item Per WBS |  |  | Total Materials | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Actual Material on Site | Remaining Materials | Material Delivery Completion (Date) |  |  |  | ELE | 158 | 21 | 111 | 2 | 0 | 0 | 24 Returned | HSF | 95 | 2 | 84 | 0 | 0 | 9 | 0
|  |  |  | A | B | C | D | Processed |  |  |  |  | GEN | 3 | 0 | 3 | 0 | 0 | 0 |  | QAC | 85 | 32 | 52 | 0 | 0 | 1 | 0
Road |  |  | 4 | 4 | 3 | 1 | 3 |  | 2025-11-29 |  |  |  | MEC | 437 | 4 | 423 | 8 | 2 | 0
infrastructure |  | Structural | 8 | 8 | 7 | 1 | 7 |  | 2026-04-07 |  |  |  | SVY | 1 | 0 | 1 | 3 | 0 | 0 |  | TOTAL | 187 | 35 | 142 | 0 | 0 | 10 | 0
Electrical |  |  | 8 | 8 | 2 | 6 |  |  | 2026-02-25 |  |  |  | TOTAL | 2539 | 109 | 2238 | 17 | 140 | 14
[13 empty] | MAC | [7 empty] | NCR
TOTAL |  |  | 20 | 20 | 12 | 8 | 10 | 0 |  |  |  |  | ITEM | ALL | A | B | C | D | UR |  | ITEM | ALL | A | B | C | D | UR | Not Respond
[13 empty] | CVL | 35 | 1 | 6 | 2 | 0 | 26 |  | Cont | 4 | 0 | 4 | 0 | 0 | 0 | 0
Consultant Quality Inspections / Observations (Weekly Basis) | [7 empty] | Overall Average | #DIV/0! |  | Average Closing | #DIV/0! | ELE | 20 | 1 | 9 | 1 | 0 | 9 |  | HSF | 53 | 1 | 47 | 0 | 0 | 0 | 0
Week Number | Date of Audit | Date Issued | Numbers Of Comments | Quality Score | Date Closed | Closure Duration |  | This Week Score | #REF! |  | Average Number of Comments Per Audit | #DIV/0! | MEC | 23 | 14 | 7 | 1 | 0 | 1 |  | QAC | 45 | 17 | 25 | 0 | 0 | 3 | 0
[13 empty] | TOTAL | 78 | 16 | 22 | 4 | 0 | 36
[21 empty] | TOTAL | 102 | 18 | 76 | 0 | 0 | 3 | 0
ITP
[13 empty] | ITEM | ALL | A | B | C | D | UR |  | ASB
[13 empty] | CVL | 8 | 0 | 0 | 0 | 0 | 8 |  | ITEM | ALL | A | B | C | D | UR
[13 empty] | ELE | 3 | 0 | 0 | 0 | 0 | 3 |  | CVL | 165 | 122 | 23 | 8 | 7 | 3
[13 empty] | MEC | 4 | 0 | 0 | 0 | 0 | 4 |  | ELE | 56 | 56 | 0 | 0 | 0 | 0
[13 empty] | TOTAL | 15 | 0 | 0 | 0 | 0 | 15 |  | GEN | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | MEC | 393 | 309 | 52 | 4 | 2 | 21
[21 empty] | TOTAL | 614 | 487 | 75 | 12 | 9 | 24
Note on A41: Malik, Muhammad: This refers to quality observation sheet

## HSE
MODON HSE Site Inspection Report
Date |  |  | 2026-07-26 |  |  |  |  | Inspected By:
Project ID. |  |  | JDH3-02-008-MOD-1-HSE-REP-03 |  |  |  |  | Report No. | 00080 |  |  |  |  | MODON PM Name
Project Name: |  |  | completion of the infrastructure development in the 3rd industrial city in Jeddah |  |  |  |  | Contractor: |  | Alrawaf |  |  |  |  | Safety Performance |  |  |  | 81.82%
Inspections are a snapshot in time and refer only to the practices and documentation observed at the time of the Inspection. It remains the responsibility of the Consultant and Contractor to ensure that all aspects of Health & Safety are suitably managed.
1 |  | Good Practice |  |  | 2 | Need Improvement | [5 empty] | 3 | Fail (Life Threatening Activity) / Comliance with Plan & Procedures |  | N/A | Atcitty Not Applicable for this Site Inspection Report
No. | Topic | [5 empty] | Wt. | HSE Compliance |  |  | No. | Topic |  |  |  |  | Wt. | HSE Compliance
2024-07-29
1 | Access and Egress - (General access to site, segregated from vehicles, / Overhead protection, while entering into the building /Adequate lighting provided when dark or overnight work) | [5 empty] | 5% | 1 |  |  | 14 | Work at Height - (PPE/Fall Protection(Same level, above and blow) / Training / Fall restraint / competency /Safe access & egress to and from work at height / Ladders / Openings (floor/shafts/Provision of emergency rescue) |  |  |  |  | 5% | N/A |  |  |  | 1 | 100 | 1 | 2024-10-14 | 78 | 10.68%
2 | Traffic Management - (Loading/unloading/sheeting/temp. routes/speed/parking/competence) | [5 empty] | 3% | 2 |  |  | 15 | Scaffolding - (Temp. Scaffolding Work-platform (All types) - qualified scaffolder / Inspection / Tagged / Safe Access/egress / PTW/Falsework & Formwork) |  |  |  |  | 4% | N/A |  |  |  | 2 | 75 | 2
3 | Site Signage - (Project Notice Board & General Signage) | [5 empty] | 2% | 2 |  |  | 16 | Mobile Elevated Work platform (MEWP) - (PTW/competence requirements/conditions/inspections/tagged/training/Full-body harness) |  |  |  |  | 4% | N/A |  |  |  | 3 | 0 | 3 | 2026-07-28 | 730
4 | PPE Compliance - (Use, storage, stock, handling & checks - Head, Foot, Eye, Hearing) | [5 empty] | 5% | 2 |  |  | 17 | Excavation & Trenches - (PTW/Edge protection/buffer zone/Slope/Benching/Shoring/Geo-tech report/Atmospheric hazards/Acess&egress/Emergency management / MS&RA/H.E) |  |  |  |  | 3% | 1 | [5 empty] | N/A
5 | Housekeeping - (Material correctly stored/Rubbish cleaned & removed daily/slips & trips hazards) | [5 empty] | 3% | 2 |  |  | 18 | Confined Space - (PTW/Training/competence/Emergency Management/MS & RA/Safe access/egress) |  |  |  |  | 5% | 2
6 | Storage of Materials - (Transporting, storage, training and use - Combustible / Flammable / Hazardous substances (COSHH) | [6 empty] | 2 |  |  | 19 | Fire Protection - (Flammable/Oxy. LPG /Combustible separated/FE's/Flashback arrestor/Sparks & slags/Smoking area/PTW/Generators/MS & RA/Emergency Management) | [5 empty] | 1 |  | Red | Serious injury or death (immediately)
7 | Site Waste Management - (Hazardous waste /Combustible waste / Human waste / Construction waste - asphalt, cable, timber, paving roof sheeting tiles, plastic & bricks) | [6 empty] | 2 |  |  | 20 | Health & Welfare - (Adequate drinking water/shaded - eating & rest area/washing & sanitary facilities/Certified FA/FA Box & Stock/adequate toilets/Ambulance) | [5 empty] | 3 |  | Yellow | Minor or near miss (3 days to comply)
8 | Health Surveillance - (Expose to excessive noise/vibration/dust/silica/CO/cement/radiation/extreme weather condition) | [5 empty] | 3% | 1 |  |  | 21 | Environmental Incident Measures - (Spill/ Leakage / Concrete wash / vehicle & eqpts. wash / waste disposal/Sewers and drains/emissions/Emergency Management/Training/site run-off water) |  |  |  |  | 5% | 2 |  | Green | No issues
9 | Electrical Safety - (Electrical qualified /RCD/GFCI/Industrial Cocket/LOTO/Cable-overhung or buried/Cords in good condition/current inspection tag) | [5 empty] | 5% | 1 |  |  | 22 | HSE Communications & Meetings - (Schedule HSE Meetings/Safety Committee meetings/Alerts / Lesson learned/Safety Bulletin contains latest HSE KPI) |  |  |  |  | 5% | 1
10 | Tools & Equipment - (Includes, powered, hydraulic & pneumatic/Guards in place/Properly stored/RCD Protection/Earthed/Good condition & tagged) | [5 empty] | 3% | 2 |  |  | 23 | HSE Plan & Associated Procedures - (Approved updated HSE Plan/ CEMP/HAZComm/Procedures/Standards/Project Safety Risk Register) |  |  |  |  | 3% | 1 |  | 26 points > 4 minors then is it’s a serious issue
11 | Manual Handling - (Lifting/loading/pulling/pushing/twisting/awkward posture/repetitive task/frequent and prolong physical effort/Reasonable practicable use of mechanical aid) | [5 empty] | 3% | 1 |  |  | 24 | Health, Safety & Environment Incident reporting - (Review of HSE Statistics, Reporting of Unsafe Act & Conditions/ Reporting of Near Miss incident/Reporting of FA cases/Record MT cases) |  |  |  |  | 3% | 2
12 | Vehicle and mobile equipment / Plant - (dumpers; excavators, cranes, piling rigs, grader, roller, loaders/condition/KSA License/certification) | [5 empty] | 5% | 2 |  |  | 25 | HSE Awareness, Training & Competence - (Policy /Objective & targets/Information, training/Climatic condition awareness/Reponses in emergency situation/ Safety Behavior Observation) |  |  |  |  | 4% | 2
13 | Lifting Operations & Rigging - (Lifting Plan/Lifting devices & gears/PTW/Condition/3rd party certification/bank-man/rigger/slingers/man-basket/inspection record/tagged) | [6 empty] | N/A |  |  | 26 | Project Leadership Site Tours - (Provide evidence of proactive safety performance/Deficient discovered discussed/Positive feedback/Workers resolving safety issues) | [5 empty] | 1
Prepared by: |  |  |  | Mohamed Ali | [6 empty] | Sent to MODON PM:
Safety Results
1 |  | 9 |  |  |  | 2 |  | 12 |  |  |  |  | 3 | 1
Note on C13: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Safe access / egress for people to their work area 2 - Safe access / egress for construction vehicles 3 - Access properly restricted-site fencing provided and maintained 4 - Access proper and not blocked 5 - Safe access is available for rescue operation 6 - Storage access / exit are clearly marked and unobstructed 8 - Access and egress is in good condition, hand holds, ladder etc. are sound and in place 9 - Ensure unauthorized public access is prevented 11 - Site assembled ladders or make-shift tables for access are forbidden on site. 13 - Use proper bridges, walkways or gangways to access or cross trenches or an excavation area 14 - Surrounding areas are cleared and barricaded and access restricted to all unauthorized trades while crane in operation 15 - To ensure early access to accredited medical / rehabilitation services 16 - Parking vehicles on site access roads causing obstruction 17 - All personnel will be instructed that access to firefighting equipment must remain clear at all times 18 - Access control gates to be locked out of hours 19 - Site access gates to be designed and located to, where possible, avoid clashes with external hazards / activities
Note on T13: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Personal Fall Arrest System; 1 - Is the suitable harness harnesses is provided 2 - Are shock absorbing lanyard with 2 locking snap hooks. 3 - Is anchorage point strong enough and can support 5,000 Ibs. 4 - Do inspection checklist is being implemented before use. 5 - Is the emergency plan for rescue in place Personal Fall Restraint System; 1 - The fall restraint equipment should be set and adjusted so there is no free fall over the edge. 2 - A harness or body belt may be used 3 - The anchorage point must support 4 times the intended load. Positioning System; 1 - Is a suitable harness or body belt provided 2 - Is there a not more than 2' free fall maintained 3 - Is the anchorage point capable of supporting 2 times the intended load or 3.000 Ibs, whichever is greater 4 - Is 100% tie-off (protection from falls at all times, even when moving from point to point) provided while using personal fall protection with two lanyards Fall Protection System; 1 - Suitable edge protection and work platforms are to be provided to prevent a fall occurring 2 - Where the provision of edge protection or adequate platforms cannot be provided safety nets or other soft-landing systems such as inflatable bags are to be used to minimize the consequences of a fall. 3 - If nets are used, they must be installed by a competent rigger and fitted as close under the work surface as possible. 4 - Areas below roof works are to be cordoned off and properly signed to prevent personnel being injured from falling materials 5 - If access onto the roof cannot be avoided, edge protection is to be installed 6 - Floor and wall openings are to be protected using covers of adequate strength to withstand the expected load that will be imposed and securely fixed. 7 - Penetrations in walls such as those provided for lift shafts, door openings, etc. are to be closed with suitable strength material or have fixed protective barriers around the penetration with a sign warning personnel of the danger of falling.
Note on C14: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are arrival and departure of vehicles and delivery accompany by security department? 2 - Are proper loading, unloading and securing loads, being properly controlled? 3 - Is the proper sheeting & coupling in place when transporting and disposing material to and from site? 4 - Is the parking to the designated parking lot and in reverse order? 5 - Is the designated speed limit adhered on workplace? 6 - Provision of ramps, traffic signs, cones, barriers, demarcation posts and tape, flashing lights and any other traffic control devices. 7 - Do visiting drivers are being inducted at the workplace, prior to enter on the workplace? 8 - Are visiting drivers restricted to dangerous areas, e.g. moving to and from they vehicles to washrooms, lavatory & offices etc.? 9 - Do drivers observe site rules and procedures, for delivery, loading and unloading? 10 - Are the areas wide enough for the safe movement of large vehicles (including visiting vehicles)? 11 - Does drivers are competent, hold valid local driving license and competent training? 12 - Ensure the vehicle and trailers have their brakes applied and all stabilizers properly positioned before beginning loading or unloading?
Note on T14: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Base soundness, load adequately spread (base plate jacks, base plate on firm ground). 2 - Line of standard (vertical) and ledger (horizontal) secure and plumb. 3 - Spacing of transoms on platforms, support for Scaff boards, boards are not over protruded and boards are secured. 4 - Staggering of joints vertical and horizontal. 5 - Guardrail / fall protection. (Top rail – Min.1mtr, Mid rail – 470mm from floor and Toe boards – Minimum150mm) 6 - Longitude and bracing on standards and ledgers. 7 - If close to structure, ties must be on lift below to top working platform and every 3m, load bearing couplers used or tie with certified anchor bolts (eye bolts). 8 - Clamps and tubes used are of correct fittings, size and free from defects. 9 - Tubes & fittings free from defects / deformation. 10 - Safe and proper access available to the working platform. 11 - Scaff tags signed, displayed and up to date. 12 - If close to slab edge/opening scaffold tied and secured to structure correctly.
Note on C15: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a Project Notice Board - (showing HSE Statistics / Safety alerts / lesson learned)? 2 - Is there prominent safety boards that are depicting the mandatory PPE on the workplace? 3 - Are other safety required signs are prominently installed on the workplace in relevant to their work-task, as following: > Hazardous Substances - e.g. respiratory protection Sign > Working at Height - e.g. Full body Harness Sign > Working UG - e.g. Full body Harness, SCBA, Ventilation, PTW Signage etc. > Working with Electrical - e.g. Leather Gloves, Goggles, Face shield, Electric shock proof helmet & shoes > Working with Chemicals - Signage = e.g. Impermeable gloves/clothing's, long sleeves, Goggles 4 - General Site Safety Signs: > Prohibition Sign = (e.g., ‘no access for unauthorized persons’). > Warning Signs = (e.g., ‘danger: electricity’) > Mandatory Signs = e.g., ‘eye protection must be worn’) > Emergency Escape or First Aid Sign = e.g., ‘emergency exit/escape route’) > Safety Color Signs = (e.g., yellow means ‘be careful’ or ‘take precautions’) > Illuminated Signs = (e.g., many emergency exit signs) > Acoustic Signals =( e.g., fire alarm) > Fire safety sign > Supplementary Signs = "This way"
Note on T15: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Man-Lift operators are to be competent and trained to operate the specific Man-Lift by examination and hold a current approved certificate / license from an approved and internationally recognized source (TUV, SGS etc. 1 - All Man-Lifts shall be inspected by a 3rd party on an annual basis. 2 - All Man-Lifts shall display a sticker corresponding to the 3rd party inspection certificate. 3 - The manufacturer's instruction manual must be on site for each and every type of Man-Lift in use. 4- A pre-start daily operator inspection of the equipment will be performed and documented on a daily basis as per the manufacturer's instructions. The user is responsible for ensuring this has occurred. 5 - The use of a Man-Lift as, or in lieu of, a Crane is strictly prohibited. Man-Lifts are to be used only for lifting personnel and small tools within the designed Safe Working Load. 6 - The platform is not to be loaded in excess of the designed working load; the safe working load of the platform is to be clearly displayed on both the platform, and body of the equipment. 7 - All persons inside work platforms shall wear a full-body harness attached to the designated anchor point. Personnel must stand on the floor of the working platform; standing on the handrails is strictly prohibited. Harnesses must not be attached to other structures outside of the working platform. 8 - Personnel must stay inside the working platform at all times; the platform must not be used as an access to structures. The use of staging or ladders to extend height is strictly forbidden. 9 - Securing the boom or work platform to any structure is strictly prohibited. The boom or working platform must not be rested upon on any structure, nor is the Man-Lift to be used as a jack/ prop or tie to support other structures. 10 - All Man-Lifts must be equipped with a 5kg (10lb) fire extinguisher. 11 - No man-lifts are to be operated that have had safety devices removed or disabled. Daily operator inspections are to include the testing of these devices (limit switches, alarms and hazard flashing beacons). 12 - Specific Man-Lifts are fitted with outriggers and/or stabilizers which must be used as per manufacturer's instructions. 13 - The work area surrounding the man-lift is to be cordoned off using barricades and signage if the area is used by other workers or vehicles. A full traffic management plan is required for all works involving man-lifts when working on highways. Under no circumstances is any part of a man-lift to extend or swing into a line of traffic.
Note on C16: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Does required mandatory PPE (refer specification BS, EN & ANSI) is provided, as following? > Safety helmet (see below for color scheme) > Safety glasses (shaded for outdoor work and clear inside structures and during non-daylight hours) > Safety boots (safety shoes are prohibited) > Orange hi-visibility vest 2 - Additional PPE shall be provided to a specific task 3 - Do specific PPE is provided according to their job requirement? > To work at height - Full Body harness / Fall arrest Devices / Fall Restraint Devices / V & H Lifeline etc. > To work in the confined space - Full Bodyarness, Tripod with retractable lifeline, SCBA, Masks etc. > 4 - Are the PPE stored appropriately to prevent deformation or distortion? 5 - Has self assessment being carried out for in according to the work requirements? 6 - EYEWEAR (Glasses/Goggles/Face Shields) > Eyewear cleaning supplies available. > Safety glasses in good condition and lenses free of scratches. > Goggles adjustment strap not cracked or frayed, not deformed, or lenses not > Face shields in good condition, including adjustment band, and free of scratches or 7 - HEAD PROTECTION > Hard hat bill and suspension attached as allowed by manufacturer. > is pliable, free of dents, cracks, nicks, or any damage due to impact. > Suspension maintained at 1.25 inches from inside of shell. > Suspension free of cuts or fraying, torn headband, adjustment strap workable. > Electrical hard hat matched to hazard classification. > Dated to determine whether within manufacturer’s allowable 5-year use time period. 8 - HAND PROTECTION > Available in sizes matched to employee. > Gloves free of rips tears, abrasions, or holes. > Matched to manufacturer’s specification for chemicals used onsite. > Electrical gloves matched to hazard and periodically inspected for insulating rating. > Maintained in a clean and sanitary condition, decontaminated or disposed properly. 9 - BODY PROTECTION > Available in sizes matched to employee. > Maintained in a clean and sanitary condition, decontaminated or disposed properly. > Vapor-tight fully encapsulated suits tested at required periodic intervals. > Flame-resistant clothing matched to electrical hazard and arc flash rating. > Welding gear matched to degree of hazard and free of cuts, tears or burn holes. > Flotation gear available for work near or on water and in good condition. 10 - HOT AND COLD BODY PROTECTION > Cooling gear available based on degree of heat stress hazard. > Cooling gear in operable, clean, and sanitary condition. > Cold-weather gear provided based on needs assessment. > Cold-weather gear available in sizes to match employees. > Cold-weather gear is in free of tears, rips, or holes and in maintained in a clean condition. 11 - TRAINING > Initial PPE training completed by employees. > Training conducted when new types or styles of PPE are issued. > PPE selection, use, and maintenance reviewed at daily safety briefings. 12 - Provision of impermeable clothing appropriate for the work being performed? 13 - Wearing of shorts, sleeveless shirts, loose clothing are prohibited across the MODON Projects. 14 - Clothing contaminated with grease, oils, fuels and other hazardous substances is not to be worn.
Note on T16: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a valid Excavation PTW in place? 2 - Are spoils, materials, and equipment set back at least 1.5 meters from the edge of the excavation? 3 - Are walkways and bridges over excavations structurally sound, minimum 0.5 meter in width and equipped with standard guard rails and toe boards? 4 - Are warning systems established and used when mobile equipment is operating near the edge of an excavation? 5 - Are employees prohibited from working on the faces of sloped or benched excavations above other employees? 6 - Are the exact locations of Utilities (piping, electrical, etc.) clearly marked? 7 - Are underground installations protected, supported, or removed when an excavation is open? 8 - Are ladders or other means of access and egress in place as per the PTW requirements? 9 - Are all workers within 7.6 meters of a means of access and egress to a trench? 10 - Are ALL ramps constructed of materials of uniform thickness, cleated together, equipped with no-slip surfaces? 11 - Are employees protected from cave-ins when entering or exiting excavation? 12 - Are precautions taken to protect employees from water accumulation and dewatering is being carried out? 13 - Is surface water or runoff diverted after every rainstorm or other hazard-increasing occurrence? 14 - Is the excavation classified as a confined space? If so, is their a valid confined space PTW and is the atmosphere being tested when there is a reasonable possibility of an oxygen-deficient, oxygen-enriched, combustible, toxic, or other harmful contaminant? 15 - Have materials and/or equipment chosen for shoring been based upon soils analysis, trench depth and expected loads (as per Excavation PTW)? 16 - Are shoring materials and equipment that are used for protective systems inspected and in good condition? 17 - Are damaged shoring materials and equipment immediately removed from service? 18 - Are damaged shoring materials and equipment inspected by a Registered Professional Engineer after repairs are made and before being placed back in service? 19 - Are protective systems installed without exposing employees to hazards of cave-ins, collapses, or threat of being struck by materials or equipment? 20 - Are ALL members of support systems securely fastened together to prevent failure? 21 - Are support systems provided to insure stability of adjacent structures, buildings, roadways, sidewalks, etc.? 22 - Are excavations below the level of the base or footing supported, and approved by a Registered Professional Engineer? 23 - Does back-filling progress with the removal of the support system? 24 - Is a shield system installed to prevent lateral movement? 25 - Are employees prohibited from remaining in a shield system during vertical movement?
Note on C17: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Sites are to be kept clean and tidy and free from slip, trip and fall hazards. 2 - Do all personnel trained in the importance of good housekeeping, managers, supervisors undertake regular monitoring and inspection of the workplace? 3 - Workplace are to be left clean and tidy at the end of each shift and where there is an accumulation of materials throughout the shift, at regular intervals as required to maintain a clean and safe site. 4 - Buildings under construction and nearing completion must ensure that all combustible and flammable materials are removed at the end of each shift. 5 - Nails are to be removed from timber as soon as possible, where this is not practical they are to be flattened and placed in a safe area (barrier and signs) until nails can be removed at a later time. 6 - Materials are to be stored so as they do not pose a risk to personnel stacking, removing or walking by (further guidance is given in the materials storage and handling section). 7 - All spills are to be cleaned up immediately using absorbent material. 8 - Cables/hoses/other trailing leads are to be protected, buried or secured above head height to avoid a slip trip, fall hazard. 9 - Waste is to be placed in designated containers and covered to protect against high winds, pests or risk of fire. Waste containers are to be emptied on a regular basis to prevent a build-up of material. 10 - Loose or light materials that are stored on roofs or open spaces are to be secured to prevent them from inclement weather. Location: 1 - Receptacles located inside buildings shall be kept at least 18 inches away from combustible walls and partitions. 2 - Receptacles for combustible trash that are located outside of buildings shall be placed at least 15 feet from the building or combustible material. Use: 1 - Cigarettes, cigar butts, matches, and similar potential ignition sources should never be placed in a trash receptacle. Proper receptacles for such items should be provided in areas designated for smoking. 2 - Broken glass, empty jars, scrap metal, and similar construction material should never be placed in office trash containers. A roll-off bin or other appropriate container should be used to hold construction debris. Environmental: 1 - Container storage areas shall be kept clean and free of trash. Improper disposal of food waste can attract pests and vermin. Prevention methods that do not involve the use of toxic chemicals is the preferred method of pest control. 2 - Outdoor containers should be kept covered when not in use so as to avoid attracting pests and to prevent the entry of water. Dripping or leaking trash containers may violate local storm water quality discharge regulations. 3 - Promote recycling by contracting with a waste removal company that provides reuse as part of the waste processing or by providing segregated bins for the collection of office paper, aluminum cans, plastic bottles, and toner cartridges. Rinse empty cans and bottles of sugar-based soda so as not to attract ants and other pests. 4 - Proper lighting (indoor) or during Night Shift are provided. Accurately installed. No impairement or poor visibilty is generated. No shadow due to installation of lights are presents.
Note on T17: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Permit is taken for confined space entry and all recommended precautions are in place. 2 - Operatives are trained and fit for the specified job. 3 - Confined space is well ventilated by means of mechanical ventilation. (Exhaust fan, blowers, low velocity air hose etc.). 4 - Rescue system (Tripod with hoisting device, Rescue Harness etc.) in place and sufficient trained persons are available for the rescue operation. 5 - Safe access is available for rescue operation. (Manhole size - Min. 450 mm X 407 mm or 457 mm Dia.) 6 - Atmospheric monitoring conducted and confined space is safe to enter. Percentage of gas concentration will be monitored and recorded every 4 hrs. A. Oxygen percentage. (Permissible limit – 19.5% to 23.5%) B. Flammable gas or vapors.(Permissible limit - <10% of LFL) C. Carbon Monoxide. (Permissible limit - <50ppm) D. Hydrogen sulfide.(Permissible limit - <10ppm) E. Any other toxic gas or vapors. _______________________________ 7 - Minimum two persons shall be assigned to work in the confined space. One person will remain in the entrance at all times to monitor the work 8 - All persons shall wear safety harness, which should be connected to safety line from outside at all times. 9 - All electrical equipment & leads are free from damage and guards in place. 10 - All electrical tools & equipment are connected through ELCB. 11 - Compressed gas cylinders are kept outside the confined space. 12 - supervisor / Foreman will be available at all time to monitor the work and for the rescue operation. 13 - Tool box talk conducted for the entire team and they are well aware of the risks. 14 - Proper communication system is available in between persons inside and standby person. 15 - Trained First aider with first aid kit will be available when working in the confined space. 16 - Confined space entry register is available and shift records will be maintained. -
Note on C18: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Combustible: 1 - Ensure oily rags, combustible material and other flammable substances which may ignite are not accumulated and that they are removed without delay to the designated disposal / storage area. 2 - Combustible materials shall not be stored within 20 feet (6.1 meters) of compressed gas cylinders. 3 - Safety cans used for dispensing combustible liquids shall be kept at a point of use 4 - Storage rooms for combustible liquids must have explosion-proof light fixtures 5 - No flames - hot work or smoking is be permitted in combustible liquid storage areas. Flammable: 1 - Adequate training in the use and storage of flammable liquids is in place. 2 - Storage of Flammable liquids in accordance with NFPA approved flammable storage lockers or in low value structures at least 50 feet from any other structure. 3 - Do not store other combustible materials near flammable storage areas 4 - Bulk drums of flammable liquids must be grounded and bonded to containers during dispensing 5 - Portable containers of gasoline or diesel are not to exceed 5 gallons 6 - Safety cans used for dispensing flammable liquids shall be kept at a point of use 7 - Appropriate fire extinguishers are to be mounted within 75 feet of outside areas containing flammable liquids, and within 10 feet of any inside storage area for such materials. 8 - Storage rooms for flammable liquids must have explosion-proof light fixtures 9 - No flames - hot work or smoking is be permitted in flammable or combustible liquid storage areas. 10 - Flammable liquid transfer areas are to be separated from other operations by distance or by construction having proper fire resistance. 11 - When not in use flammable liquids shall be kept in covered containers. 12 - Flammable materials are considered hazardous and as such, material safety data sheets and appropriate hazard communication training for affected employees is required 13 - Maintain high levels of housekeeping, particularly with relations to flammable materials. 14 - Where flammable materials are handled in the course of work, safe work procedures must be prepared and documented with reference made to the Material Safety Data Sheets (MSDS‘s) for the materials concerned. 15 - All people handling, working with or in control of flammable substances must be properly trained and supervised (documentation to be maintained). 16 - Lead, dust, fumes and vapor constitute a major health hazard to workers. Hazardous Substances COSHH 1 - Under COSHH the risk presented by any hazardous substance assessed using hierarchy of control, stored, transported, created or disposed and usage at the workplace; > Very toxic or toxic: Substances that, in low quantities, cause death or acute or chronic damage to health when inhaled, swallowed or absorbed via the skin > Harmful: Substances that may cause death or acute or chronic damage to health when inhaled, swallowed or absorbed via the skin > Corrosive: Substances that may, on contact with living tissues, destroy them > inhalation into the lungs, when the substance is in the form of a gas, vapor, fume, mist, aerosol or dust > absorption through the skin or eyes by contact with a substance that can penetrate unbroken skin, or is absorbed through unprotected cuts or grazes > injection by contact with contaminated sharp objects or high-pressure equipment, e.g. water jetting > ingestion by swallowing particles of a hazardous substance resulting from hand-to- mouth transfer
Note on T18: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are regular and frequent fire safety inspections carried out? 2 - Have a sufficient number of fire marshals/evacuation officers been appointed? 3 - Are water supplies adequate? 4 - Does the building or site have a written fire procedure? 5 - Is there an effective permit to work system in operation for all hot work and other fire related work? 6 - Do all doors from areas from which a large number of people may have to escape open in the direction of travel? 7 - Do all emergency exit doors (i.e. doors not in normal use) have clear instructions displayed on how to open? 8 - Are all escape routes clear and unobstructed? 9 - Are all fire exit doors correctly signed? 10 - Is all fire fighting equipment immediately visible or correctly signed? 11 - Are all flammable and explosive substances adequately signed to indicate their presence and danger? 12 - Where necessary, is there a sufficient number of emergency lights to adequately illuminate all internal escape routes, exit doors and signs? 13 - Where automatic fire detection is deemed to be necessary is there an adequate number of detectors in the critical areas? 14 - Where the means of raising the alarm is by hand-operated devices, can the operation of one device be heard throughout the entire building or site? 15 - Is there an adequate number of fire extinguishers in the building? 16 - Is there firefighting equipment other than extinguishers in the building? 17 - Are all electrical circuits and fixed electrical installations examined and tested at an acceptable frequency? 18 - Is housekeeping to an acceptable standard? 19 - Have all staff been trained in fire procedures in the last twelve months? 20 - Are all fire drills adequately recorded?
Note on C19: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - General construction waste streams generated including; > Asphalt, cable, timber, paving, roof sheeting, tiles, plastic sheeting and brickwork. > Excess concrete, spoil material from excavations. > General waste, such as putrescible food scraps and packaging from workers. > General (food) waste, construction/concrete waste, hazardous waste, paper/cardboard and waste water/sewage. 2 - Are hazardous waste identified with hazardous Waste label. 3 - Containers are properly labeled in according to their contents. 4 - Container inspections are documented in writing using the Container Inspection Checklist. 5 - Weekly inspections logged into book using the Accumulation Area Inspection Log Sheet. “NO SMOKING OR OPEN FLAME” sign posted. 6 Disposal facilities identified, evaluated using the procedures. 7 - Disposal facility accepted waste and issue approval letter. 8 - Waste transfer/dispose tracked using Waste Tracking Form. 9 - Waste streams, such as asphalt and concrete, to be recycled should be segregated and separately stored. 10 - Spill Release Contingency: 1 - Prior to beginning operations, ensure that on-site spill response capabilities (containment and personal protective equipment) are consistent with task requirements described in job hazard analysis.
Note on T19: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: HHE is required at all locations where chemical hazards exist, such as; storing, transferring and handling facilities, under routine conditions. The HHE scope shall include the physical, chemical, radiological, and biological health hazards. Physical health hazards include elevated noise and vibration exposures, repetitive motion work operations, ionizing and non-ionizing radiation exposures heat and cold stress and biological hazards include infectious disease agents. HHE shall be performed before the site mobilization; 1 - Is the adequate eating or mess area is provided and sufficient for number of workers? 2 - Are sufficient tables and Chair are provide and Kept Clean? 3 - Are FEs, signs, pest control being implemented? 4 - Is washing Area sufficient and Kept Clean? 5- Cooking Area Kept Clean? 6 - L.P.G. Cylinder stored outside, secured & upright 7 - Sufficient drinking water provided. Filters changed (as per manufacturer recommendation)? 8 - Sufficient toilets, washbasins, cleaned/disinfectant provided? 9 - Provision of First Aider 10 - Provision of Nurse 11 - Provision of First Aid Kit 12 - Provision of site clinic with required first aid equipment and items. 13 - Provision of shaded area on the workplace 14 - Provision of Ambulance or an equal arrangement in place" 15 - Smoking area is Prohibited other than designated smoking areas, clear of flammable and combustible materials? 16 - All toilets, washing, rest and eating facilities to be kept clean, hygienic and be well maintained at all times? 17 - Waste Management - Covered bins, emptied daily, close proximity, color coded etc.? 18 - Are the monitoring, including integrated air sampling, noise dosimetry and other exposure assessments, being carried out? 19 - Are the Physical, chemical, and biological stresses, being identified, results are taken with action level to prevent sickness, impaired health, significant discomfort, or inefficiency in workers? 20 - Are WEL, LEL, OEL PEL & TLV linked to control workers airborne exposure to a chemical in a concentration above which is likely to cause death or immediate or delayed permanent adverse health effects or prevent escape from such an environment, if bening implemented?
Note on C20: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Is the hierarchy of Control is beng carried out on the following and recorded; 1 - Exposure to Chemical; e.g. - Dust, Gas, Mist, Vapor 2 - Exposure to Radiation; e.g. - Pipe radiography etc. 3 - Exposure to Biological Hazard; e.g. - Bloodborne pathogens / Legionella / Leptospirosis 4 - Exposure to noise; e.g. Loss of hearing / Physical damage to hearing mechanism 5 - Heat and cold stress work; e.g. - Heat-stroke, Heat stress / Frostbite / 6 - Repetitive Motion Work; e.g. - Musculoskeletal disorder, awkward position etc. 7 - Is the risk assessment carried out on the hazardous material and covering the following; > Allowable exposure limits, > Exposure monitoring requirements, > Methods of compliance for potential over exposure conditions, > Medical surveillance program, > Hazard communication, employee training requirements, 8- Is the IH Surveillance Plan should being implemented and have rocored on the following; > Which exposure groups require IH monitoring and medical surveillance > Specific substances or agents to be monitored, > The OELs to be used to evaluate results > The statistical basis to continue or cease monitoring > Specific medical testing/protocol to be implemented 9 - Do we've program on identifies work conditions such as the following, the exposure must first be mitigated or work shall not be performed. > Oxygen concentrations less than 19.5% or greater than 23.5%, or > Atmospheres greater than 1% of the Lower Explosive Limit, or > Atmospheres that are >50% of Immediately Dangerous to Life or Health (IDLH) concentrations, or > Work with sensitizers or known human carcinogens, mutagens, or teratogens without process isolation or fully encapsulating personal protection, or > Work with highly infectious biological agents without process isolation
Note on T20: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are all dispensing areas diked or properly graded to control drainage of spilled fuel? 2 - are all workers and operatives are trained to use spill response kit? 3 - Is the procedure in place for collecting and/or containing, and disposing of spilled materials? 4 - All tanks & vessels areas are diked to contain accidental spills?. 5 - Do measures taken to prevent an accidental contaminated runoff from construction , operation, maintenance, plant and storage areas? 6 - Do measures taken to control on deposits of oils, greases and fuels, from site plant and vehicle operations, mechanical failures, spillages and discharges to ground or drains and the dispersion of unattended spills by plant / vehicle movements?. 7 - Do measures taken to control on fuels, oils and other hazardous chemicals spilled on site during re-fueling, storage or transport operations?. 8 - Do we have an Emergency Response Procedure will be followed in the event of environmental emergency such as an oil or chemical spill? 9 - Is there a procedure for concrete wash, clean and dispose to prevent ground contamination, such as; Concrete wash pits with leak proof sedimentation tanks will be provided for washing concrete mixer trucks. The design and location of such wash pits shall be agreed with the Project Manager prior to its construction on site. Concrete dumping or spillages of any kind shall not be allowed in any other location on site? 10 - Is there a procedure to used in the situation of a major spills that will have an impact on the surrounding environment will be promptly reported to the Fire Brigade? 11 - Are there a procedure of disposing off any damage/leakage drums or containers shall be removed in accordance with the local requirements? 12 - Are there a procedure of dealing with spilled contaminated soils, resulted and remediated, accordingly? 13 - Are all personnel trained in the use of spill procedure and response and the adequate spill kits are available on site?
Note on C21: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - All electrical extension cords are equipped with nonconductive plugs 2 - Cords must not be spliced or draped over nails, metal objects 3 - The use of extension cords by means of multiple outlet plugs from single outlets is prohibited 4 - All electrical service removals, alterations and equipment installations are performed by an authorized electrician 5 - Faulty electrical installation 6 - Electrical supply disruption 7 - Exposed cables 8 - Trip / fall hazards from installed cables 9 - Fire hazard Electrical overload 10 - electrocution 11 - Electrical (short circuit) - Contact with exposed conductors or a device that is incorrectly or inadvertently grounded, such as when a metal ladder comes into contact with power lines 12 - Electrical - (static discharge) 13 - Electrical Fire - Use of electrical power that results in electrical overheating or arcing to the point of combustion or ignition of flammables, or electrical component damage 14 - Improper grounding 15 - Damaged insulation 16 - Exposed electrical parts 17 - Overloaded circuits 18 - Inadequate wiring 19 - Wet conditions 20 - Overhead power lines 21 - Damaged tools and equipment
Note on T21: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a meaningful and an effective consultation and communication on health and safety matters being implemented through out the project? 2 - Is the Consultation and communication on health and safety matters in place through the following mechanisms: > Project specific induction - (prior to commencement of contracted work) > Work activity Induction (in SWMS or equivalent) - (prior to commencement any construction work) > Toolbox Meetings - (Monthly intervals or generally when there is the introduction of a new process (SWMS) or when discussing OHS issues/topics). > Subcontractor Meetings - (weekly) > Project team meetings - (weekly) > HSE Committee Meeting - (as agreed with the HSE Committee) > OHS Report - (monthly) > Project Notice Board and general signage - (as required) 3 - Is there a method of communication is to be established in the work procedures to allow constant monitoring of those persons working in the confined space? 4 - Is there a material safety data sheets and appropriate hazard communication training for affected employees is in place? 5 - Are all environmental aspects and impacts been communicated to employees? 6 - Dose the notice
Note on C22: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1- Check that all the workers are using safe hand tools/power tools and instruct them to operate and maintain the same in safe manner 2 - Ensure power tools and hand tools are checked prior to issue 3 - Damaged tools and equipment 4 - Electrical tools or electrical equipment are not to be issued for use until inspected. 5 - Electrical tools or electrical equipment are not to be issued for use until inspected. 6 - "Defective" electrical tools and equipment are to be tagged and removed from service until repaired and inspected 7 - The frequency for inspection of construction electrical tools and electrical equipment shall be monthly and inspection indicated by attached color-coded tape or color- coded tie wraps and a color coded inspection tag with Contractor‘s name, the supervisor, the inspection date, equipment number and signature of competent inspector displayed on the tag. 8 - Checking the cords for worn or cracked insulation. 9 - Checking the cords entry to plug and tool housing for frayed or worn insulation and strain relief. 10 - Checking the plug prongs for damage. 11 - Checking the plug for exposed connectors 12 - Checking the equipment housing for damage. 13 - Checking trigger locks to ensure they have been removed 14 - Checking the leads for signs of wear, poor connections at probes, etc. 15 - Checking the housing and the readout window for cracks, loose screws, etc. 16 - Check all Ground Fault Circuit Interrupters (GFCI) during the monthly inspections. 17 - Machines are free from any defects / damage. 18 - Pressure switch and safety guards in place where applicable. 19 - Leads are fitted with correct plugs & sockets and free from damages. 20 - Leads wires are free from joints, cuts and other defects. 21 - Leads are suitably rated for the electric current. 22 - Machines / Tools are equipped with properly functioning dead man switch. 23 - Tools issue and maintenance record is properly maintained. 24 - Tools are correctly stored. 25 - Discarded Tools / cords are marked and stored separately.
Note on T22: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is the Project HSE Plan presents actions, responsibilities, protocol, conformance, verification and containment activities to be undertaken by project staff and sub-contractors at all times during the construction phase of the project. 2 - Is the implementation of the HSE plan is being monitored, evaluated for accuracy and any changes made communicated to all relevant personnel. 3 - Is the HSE Plan, CEMP, Security Plan, HAZcomm., standards & procedures are updated, signed, approved and distributed, acknowledged to the construction team's responsible individuals? 4 -Is the project overall safety risk register developed, approved and being implemented?
Note on C23: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Immediate Postural and Load Factor; 1- Is the body position stable? 2 - Is the trunk of the body straight (not twisted)? 3 - Is the operation carried out by one person? 4 - Is the load kept close to the body? 5 - Can the handler avoid stretching upwards? 6 - Can the handler avoid a prolonged period in one posture? 7 - Can the handler perform the task without overreaching? 8 - Are both hands used for grasping? 9 - Are the hands less than a shoulder width apart? 10 - Is the load positioned centrally in front of the body? 11 - Is the load reasonably symmetrical? 12 - Is the load stable and easy to grasp? 13 - Can handlers move and position themselves freely? Environmental Risk Factor; 1 - Too hot? 2 - Too cold? 3 - Too bright? 4 - Too dark? 5 - Too noisy to allow effective communication? 6 - Too wet? 7 - Slippery underfoot? 8 - Does any personal protective equipment interfere with the task? Carrying; 1 - Is the load carried at knuckle height? 2 - Is the load carried at arm's length from the body? 3 - Is the load carried for more than 10 meters? Seated Work; 1 - Is the load lifted from below thigh height? 2 - Is the load lifted to above shoulder height? 3 - Is the load lifted at arm's length from the body? 4 - Does the handler have to twist significantly to the side? 5 - Is the load heavier than 5kg? Pushing and Pulling; 1 - Does the pushing and pulling take place below knuckle height? 2 - Does the pushing and pulling take place above shoulder height? 3 - Is the initial or maximum force required to push or pull the load more than 25kg? 4 - Is the continuous force required to keep the load in motion more than 10kg?
Note on T23: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a system of proper HSE reporting in place, such as; all work-related incidents including near misses, injuries, illnesses, property damage, environmental incidents, security events and motor vehicle incidents, using proper protocol followed? 2 - Is the HSE incidents, accident, near misses, unsafe acts/conditions and dangerous occurrences are being reporting in timely manner and in the approved company format? 3 - Are the workers informed, trained in reporting all near misses, unsafe acts/conditions to the appropriate authority or line of manager? 4 - Is the Weekly / Monthly HSE Statistics data, including (leading & lagging) indicators, reviewed by the senior management?
Note on C24: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: CHECKS; 1 - Plant guarding is in place and in good condition to prevent injury from parts disintegrating or failing 2 - Access and egress is in good condition, hand holds, ladder etc. are sound and in place 3 - Operator's seat and controls are in good condition and all safety devices (limiters and indicators) are labelled and fully operational. 4 - Operator's manual / instructions supplied by the manufacturer of the plant are available in the plant. 5 - Hazards with the use of the plant are identified, i.e. Safe working limits on batters, operator safety instructions etc., are displayed clearly in the cabin of the plant for operator reference. I.E. PLANT SPECIFIC RISK ASSESSMENT. 6 - Hazard controls, i.e. seat belts must be worn and hearing protection must be worn, caution/danger signs (counter weight slewing area, excavators and cranes) etc. are displayed in the cabin or on the plant in a position relevant to the hazard. 7 - Operator cabin/work platform access is clean and free of debris, loose tools, equipment, grease oil and is in an orderly condition. 8 - Plant is clean and free from oil leaks and oil build up. 9 - Plant Pre Start inspection is complete and a record of the inspection will be provided at commencement on the site. 10 - Certification of operator / proof of competency. 11 - Operational Noise Level - Statement of conforming emission level. 12 - Plant has no areas of excessive wear or damage. Mobile plant required to have; 1 - Plant is fitted with a Roll Over Protection Structure (R.O.P.S.) and operator restraint. 2 - Plant is fitted with a front horn and reversing beeper. 3 - Plant is fitted with a rotating or flashing amber beacon. Plant used to lift Material and equipment; Backhoes, excavators, cranes and loaders used as crane from designed lifting points. The Safe Working Load of the plant item is displayed on the plant as: EITHER; A Crane Chart supplied by the manufacturer specific to the plant item in the cabin of the plant for operator reference OR; The Safe Working Load of the equipment on the boom of the loader bucket and of the dipper arm of excavators - a combination of both is required for backhoes e.g. SWL 1.2ton. Personal Lifting Equipment - (Cherry Pickers, boom lift and elevated platform) 1 - Safety Working Load is displayed on work bucket / platform. 2 - Fully body harnesses and lanyards are to be provided for personnel using the equipment. 3 - Safety Instruction for the operation of the equipment is clearly displayed in the work bucket / platform. 4 - The supplier have provided training for personnel using the platform in the safe use of the equipment
Note on T24: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Do all personnel have the correct information, instruction and training according to their role and responsibilities? 2 - Is the contractor promoting awareness of company standards and regulations among their employees on a regular basis, or when it is necessary? 3 - Do all personnel have completed basic relevant awareness training, such as; Fire Awareness Training, Heat Stress awareness Training, Safety Signs and Color Code awareness Training, Environmental Awareness Training, Using Fire Extinguisher Awareness Training, Emergency reporting Awareness Training, Unsafe Act/Conditions reporting awareness training, Evacuation Procedure Awareness Training?
Note on C25: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Crane Inspected 2 - Operator certified 3 - Lift Plan approved 4 - PTW obtained 5 - lifting equipment is suitable for the use it is being put to, marked with safe working load, properly maintained and inspected, and receives a periodic thorough examination. 6 - Are all members of the lifting operations team including the Appointed Person, Crane Drivers and Slingers / Signalers / Banksmen will be competent and have such practical and theoretical knowledge and experience as is necessary to carry out their duties. 7 - Bank man is available and certified 8 - The crane operator have a practical and theoretical knowledge of lifting operations 9 - Lifting operations will be undertaken by a minimum of three competent people the crane operator, slinger / signaler (slinger and signaler can be one person) / banks man / flagman (banks man and flagmen can be one person) and Supervisor 10 - Certification of Lifting Equipment / Lifting Gear / Lifting Devices 11 - Lifting plan prepared/approved/communicated 12 - Lifting gear (Chain sling, shackle, webbing sling, lifting clamps etc.) / devices (Chain block, Winch, Monorail etc.) are checked, inspected & tagged - ( size, length, dia, width, SWL,Condition & defects. 13 - All lifting equipment / gears have valid test certificates and are in good condition.
Note on T25: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there process of SBO for leadership to identify and reinforce safe work practices/behaviors? 2 - Is there process of SBO for leadership to identify and improve on at-risk practices? 3 - Is there process of SBO for leadership to identify and improve on practices, conditions, controls, and compliance that eliminate or reduce hazards? 4 - Is there a process of SBO for leadership to make positive, corrective, cooperative, collaborative feedback/recommendations? 5 - Is there a training program for BBST, that how to identify critical safety behavior and how to provide feedback and the number of personnel trained. 6 - Is there a program for the leadership to carry out SBO once a month or twice (depends project scope of work), and record available?

## HSE-Stat
Safety Statistics
Category | Item |  | This Week | This Month | Year to Date | Cumulative
Category | Total Hours Worked |  | 22920 | 97050 | 1866079 | 2210362
| Safe Hours Worked |  | 22920 | 97050 | 1866079 | 2210362
| LTI |  | 0 | 0 | 0 | 0
| MTC (Healed w/o Disability) |  | 0 | 0 | 0 | 0
| MTC (Healed w/ Disability) |  | 0 | 0 | 0 | 0
| Near Miss |  | 0 | 0 | 9 | 11
| First Aid Cases |  | 0 | 0 | 0 | 0 | [6 empty] | 64
| Fatality |  | 0 | 0 | 0 | 0
| Fire Incident Cases |  | 0 | 0 | 0 | 0
| Vehicle Incident |  | 0 | 0 | 1 | 1
| Property Damages |  | 0 | 0 | 0 | 0
Proactive | Induction Training |  | 0 | 0 | 96 | 223
| No.of Internal Training |  | 2 | 7 | 145 | 178
| No.of Internal Audit |  | 0 | 0 | 0 | 0
| No. of Toolbox Talks |  | 8 | 34 | 3181 | 3335
| Safety Awards/Incentives |  | 0 | 0 | 0 | 0
[7 empty] | Category | Item | This Week | This Month | Year to Date | Cumulative
Consultant Safety Inspection (Weekly Basis) | [6 empty] | Overall Average | #DIV/0!
Week Number | Date of Audit | Date Issued | Numbers Of Comments | Overall Score | Date Closed | Closure Duration | This Week Score | 81.82%

## Major Quantities
Material | Unit | Original BOQ Qty | Revised BOQ | Delivered Qty | Delivery % | Installed Qty | Installed Qty %
Sewage Network
GRP–200 Dia | m | 29181 | 21379.41 | 21379.41 | 100% | 21379.41 | 100%
GRP–250 Dia | m | 380 | 4579.41 | 4579.41 | 100% | 4579.41 | 100%
GRP–300 Dia | m | 0 | 204.61 | 204.61 | 100% | 204.61 | 100%
GRP–400 Dia | m | 0 | 531.89 | 531.89 | 100% | 531.89 | 100%
Sewage Manholes | Nr | 361 | 355 | 355 | 100% | 355 | 100%
Storm Network
UPVC 300 mm Dia | m | 28700 | 29079.778 | 29079.778 | 100% | 29079.778 | 100%
GRP– 400 Dia | m | 4770 | 11757.93 | 11757.93 | 100% | 11757.93 | 100%
GRP– 500 Dia | m | 4350 | 4240.12 | 4240.12 | 100% | 4240.12 | 100%
GRP– 600 Dia | m | 5050 | 5965.71 | 5965.71 | 100% | 5965.71 | 100%
GRP– 700 Dia | m | 5550 | 5347.16 | 5347.16 | 100% | 5347.16 | 100%
GRP– 800 Dia | m | 6900 | 6312.41 | 6312.41 | 100% | 6312.41 | 100%
GRP– 900 Dia | m | 8250 | 7735.76 | 7735.76 | 100% | 7735.76 | 100%
GRP– 1000 Dia | m | 3200 | 2855.86 | 2855.86 | 100% | 2855.86 | 100%
GRP– 1100 Dia | m | 2370 | 1771.08 | 1771.08 | 100% | 1771.08 | 100%
GRP– 1200 Dia | m | 3900 | 8971.96 | 8971.96 | 100% | 8971.96 | 100%
GRP– 1400 Dia | m | 0 | 425.38 | 425.38 | 100% | 425.38 | 100%
Manhole– 1200 Dia | Nr | 75 | 203 | 203 | 100% | 203 | 100%
Manhole– 1500 Dia | Nr | 195 | 418 | 418 | 100% | 418 | 100%
Manhole– 2000 Dia | Nr | 410 | 219 | 219 | 100% | 219 | 100%
Catch Basin Single | Nr | 690 | 1007 | 1007 | 100% | 1007 | 100%
Catch Basin Double | Nr | 630 | 761 | 761 | 100% | 761 | 100%
Potable Water Network
HDPE PIPE DN 160 | m | 17812 | 8045 | 8045 | 100% | 8045 | 100%
HDPE PIPE DN 225 | m | 5660 | 2000 | 2000 | 100% | 2000 | 100%
HDPE PIPE DN 315 | m | 270 | 215 | 215 | 100% | 215 | 100%
HDPE PIPE DN 450 | m | 0 | 1890 | 1890 | 100% | 1890 | 100%
Buried Gate Valves 150 | Nr | 68 | 68 | 68 | 100% | 68 | 100%
Buried Gate Valves 200 | Nr | 9 | 9 | 9 | 100% | 9 | 100%
Butterfly Valves 300 | Nr | 239 | 2 | 2 | 100% | 2 | 100%
Wash-out Valves 100 | Nr | 2 | 3 | 3 | 100% | 3 | 100%
Air Valves 50 | Nr | 7 | 1 | 1 | 100% | 1 | 100%
Fire hydrant | Nr | 2 | 193 | 193 | 100% | 193 | 100%
Fire hydrant ULFM 150 | Nr | 218 | 193 | 193 | 100% | 193 | 100%
Irrigation Network
HDPE PIPE DN 125 | m | 9460 | 24479 | 24479 | 100% | 24479 | 100%
HDPE PIPE DN 250 | m | 38800 | 28362 | 28362 | 100% | 28362 | 100%
HDPE PIPE DN 315 | m | 10249 | 7061 | 7061 | 100% | 7061 | 100%
HDPE PIPE DN 450 | m | 8462 | 8870 | 8870 | 100% | 8870 | 100%
HDPE PIPE DN 630 | m | 3014 | 2221 | 2221 | 100% | 2221 | 100%
GRP PIPE DN 800 | m | 1340 | 1340 | 1340 | 100% | 1340 | 100%
Buried Gate Valves 100 | Nr | 314 | 314 | 314 | 100% | 314 | 100%
Buried Gate Valves 250 | Nr | 141 | 141 | 141 | 100% | 141 | 100%
Butterfly Valves 300 | Nr | 20 | 20 | 20 | 100% | 20 | 100%
Butterfly Valves 400 | Nr | 30 | 30 | 30 | 100% | 30 | 100%
Butterfly Valves 600 | Nr | 9 | 9 | 9 | 100% | 9 | 100%
Butterfly Valves 800 | Nr | 2 | 2 | 2 | 100% | 2 | 100%
Wash-out Valves 100 | Nr | 998 | 22 | 22 | 100% | 22 | 100%
Wash-out Valves 150 | Nr | 736 | 6 | 6 | 100% | 6 | 100%
Wash-out Valves 200 | Nr | 103 | 1 | 1 | 100% | 1 | 100%
Air Valves 50 | Nr | 46 | 33 | 33 | 100% | 33 | 100%
Air Valves 65 | Nr | 82 | 11 | 11 | 100% | 11 | 100%
Road works
Bituminous base course (Grading I - Class A), including Prime Coat (MC1) | m3 | 2255 | 1735 | 1735 | 100% | 1735 | 100%
Bituminous concrete wearing course, (Grading I - Class A), including tack coat (RC2) | m3 | 63689 | 1240 | 1240 | 100% | 1240 | 100%
Precast Concrete Kerb, Type K1-D | m | 187209 | 15100 | 15100 | 100% | 15100 | 100%
Precast Concrete Kerb, Type L1 | m | 123805 | 1972.25 | 1972.25 | 100% | 1972.25 | 100%
Depressed curbs Type K2 | m | 2850 | 750 | 750 | 100% | 750 | 100%
Interlock | m2 | 59537.2818 | 1576 | 1576 | 100% | 1576 | 100%
Traffic signs, ground mounted, Sheet Alumenium, (breakaway)Single post, with all accessories | unit | 1295 | 31 | 31 | 100% | 31 | 100%
Traffic signs, ground mounted, Sheet Alumenium, (breakaway) Double post with all accessories | unit | 113 | 4 | 4 | 100% | 4 | 100%
Electrical network
MEDIUM VOLTAGE CABLES DUCT BANKS |  |  |  | 0 |  | 0
Duct bank for (4) cables | m | 950 | 0 | 0 |  | 0
MEDIUM VOLTAGE CABLES |  |  |  | 0 |  | 0
3 Core AL . Cable 13.8 kV 3Cx500 mm² AL./XLPE /PVC. Unarmored | m | 30720 | 0 | 0 |  | 0
Straight joints cables for 13.8 kv 3Cx 500 mm², Al /XLPE/LLDPE | unit | 70 | 0 | 0 |  | 0
Cable Termination for 13.8 kv 3Cx 500 mm², Al /XLPE/LLDPE | unit | 8 | 0 | 0 |  | 0
MEDIUM VOLTAGE SWITCHGEARS |  |  |  | 0 |  | 0
Nrrmally Open Point (R M U) 13.8 kv for Outdoor type according to the Saudi Electric Company specifications and requirements | unit | 2 | 0 | 0 |  | 0
Street Lighting
STREET LIGHTING SUB-STATION |  |  |  | 0 |  | 0
Unit Substation 13.8/0.4 K V, 500kVA ,Including concrete foundations and fencing, And all accorciess of cables , terminations , lugs , ...., According to the specifications and standards of SEC | Unit | 3 | 0 | 0 |  | 0
Ring Main Unit RMU, 13.8KV, According to the specifications and standards of SEC | Unit | 3 | 0 | 0 |  | 0
LOW VOLTAGE CABLES |  |  |  | 0 |  | 0
Stranded armored Cables, Copper, 4Cx6 mm² XLPE /PVC/SWA | m | 3065 | 1826 | 1826 | 100% | 1826
Stranded armored Cables, Copper, 4Cx10 mm² XLPE /PVC/SWA | m | 2890 | 2092 | 2092 | 100% | 2092
Stranded armored Cables, Copper, 4Cx16 mm² XLPE /PVC/SWA | m | 1712 | 896 | 896 | 100% | 896
Stranded armored Cables, Copper, 4Cx25 mm² XLPE /PVC/SWA | m | 15218 | 7396 | 7396 | 100% | 7396 | 100%
Stranded armored Cables, Copper, 4Cx35 mm² XLPE /PVC/SWA | m | 1150 | 11757 | 11757 | 100% | 11757 | 100%
Stranded armored Cables, Copper, 4Cx50 mm² XLPE /PVC/SWA | m | 120 | 120 | 120 | 100% | 120
Stranded armored Cables, Copper, 4Cx150 mm² XLPE /PVC/SWA | m | 0 | 1500 | 1500 | 100% | 1500
Supply and install single core PVC insulated copper conductor cables for circuit protective conductor (CPC) / ECC, size 6 mm² | m | 930 | 4208 | 4208 | 100% | 4208
Supply and install single core PVC insulated copper conductor cables for circuit protective conductor (CPC) / ECC, size 16 mm² | m | 1270 | 20049 | 20049 | 100% | 20049
Supply and install single core PVC insulated copper conductor cables for circuit protective conductor (CPC) / ECC, size 70 mm² | m |  | 2700 | 2700 | 100% | 2700
Supply and install single core PVC insulated copper conductor cables for circuit protective conductor (CPC) / ECC, size 70 mm² | m |  | 2700 | 2700 | 100% | 2700
LIGHTING POLES |  |  |  | 0 |  | 0
Lighting poles with 2 arms, height of ( 12 ) meters, including the power distribution box, cables , and RCC foundation. | Unit | 10 | 10 | 10 | 100% | 10 | 100%
Lighting poles with 1 arm, height of ( 12 ) meters, including the power distribution box, cables , and RCC foundation. | Unit | 255 | 220 | 220 | 100% | 220 | 100%
STREET LIGHTING LUMINAIRE |  |  |  | 0 |  | 0
Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) WATT. | Unit | 275 | 240 | 240 | 100% | 240 | 100%
Light fixtures LED 342 watts | Unit |  | 88 | 88 | 100% | 88 | 100%
Light fixtures LED 208 watts | Unit |  | 102 | 102 | 100% | 102 | 100%
EARTHING SYSTEM |  |  |  | 0 |  | 0
Including earthing of lighting poles ,masts. feeder pillars , unit substations, L.V feeders and KWH meter. | Unit | 20 | 20 | 20 | 100% | 20
ROAD CROSSING DUCTS |  |  |  | 0 |  | 0
ROAD CROSSING DUCT مواسير 160مم UPVC | m | 1440 | 1116 | 1116 | 100% | 1116
DRAWPITS |  |  |  | 0 |  | 0
Drawpit with medium duty steel cover, size600x600x1000mm | Unit | 2 | 783 | 783 | 100% | 783 | 100%
Drawpit with medium duty steel cover, size900x900x1200mm | Unit | 46 | 151 | 151 | 100% | 151
Drawpit with medium duty steel cover, size 900x1800x1200mm | Unit | 4 | 18 | 18 | 100% | 18
Lighting panels |  |  |  | 0 |  | 0
Street Lighting panels | Unit | 3 | 3 | 3 | 100% | 3
Supply and installation of KWH meter mounting frame including concrete block for installation of KWH meter according to the standards and specifications of SEC. | Unit | 3 | 3 | 3 | 100% | 3
Telecommunication netwrok
DUCTS |  |  |  | 0 |  | 0
6-ways ducts, 50mm diameter | m | 8100 | 8100 | 8100 | 100% | 8100 | 100%
MANHOLES |  |  |  | 0 |  | 0
Manhole Type 1 | Nr | 93 | 90 | 90 | 100% | 90
Manhole Type 2 | Nr |  |  | 0 |  | 0
CCTV
Pole | Nr | 0 | 18 | 18 | 100% | 18 | 100%
LV Cables | m | 0 | 500 | 500 | 100% | 500 | 100%
Camera and Antina | Nr | 0 | 82 | 82 | 100% | 82 | 100%
Monitors | Nr | 0 | 10 | 10 | 100% | 10 | 100%
Rack And Switch | Nr | 0 | 4 | 4 | 100% | 4 | 100%

## Invoice Log
Weekly Progress Report - Invoice Log | [32 empty] | Y
Project Value | [9 empty] | Payment Status | [7 empty] | Invoices Summary | [9 empty] | Average Invoices durations |  |  |  |  | N
Original Contract Value |  |  |  | 319744875.73 |  | O&M Value |  | 0 |  | Advance Payment % |  | 10% |  | Advance Payment (SAR) |  | 31974487.573 |  | No of Submitted Invoices |  | 0 |  | Submitted Invoices (SAR) |  | 250214132.9388 |  | Submiited Invoice Peroid | 2026-08-31 | CM / PgM Average Approval duration |  | 0.56522 | Average Invoice Value | 10425588.8725
Revised Contract Value |  |  |  | 319744875.73 |  | Revised O&M Value |  | 0 |  | Retention % |  | 0% |  | Retention (SAR) |  | 0 |  | No of Approved Invoices (CM) |  | 23 |  | Approved Invoices (CM) (SAR) |  | 246537903.1817 |  |  |  | MODON PM & Accounts Average Approval duration |  | #DIV/0!
Estimate At Completion Value |  |  |  | 319744875.73 |  | Submitted Invoices (Gross Value) |  | 250214132.9388 |  | Penalties and deduction % |  | 0.08131% |  | AP Recovery (SAR) |  | -25021413.2939 |  | No of Approved Invoices (PM) |  | 23 |  | Approved Invoices (PM) (SAR) |  | 246537903.1817 |  | Invoice Submitted Compared to Contract Value | 78.25% | Payments Average Duration |  | #DIV/0!
Potential Changes |  |  |  | 0 |  | Total Deduction |  | -25281413.2939 |  | Penalties and deduction (SAR) |  | -260000 |  | Retention Cumulative (SAR) |  | 0 |  | No of Paid Invoices |  | 0 |  | Paid Invoices (SAR) |  | 0 |  |  |  | Invoices Average total Duration
Invoice Reference |  |  |  | Invoice Value |  |  |  |  | Period Covered |  |  | CM / PgM Approval Timeline |  |  |  | Modon PM & Accounts Approval | [6 empty] | Payment Status |  |  |  |  | Total Invoice Duration | Remarks
# | Invoice No. | Doc Control reference | Submittal Rev. # | Gross Value | AP Recovery | Retention | VAT 5%/15% | Deduction / Penalties | Amount (net) | Start Date | End Date | Date to CM / PgM | CM / PgM Approval (Yes/No) | CM / PgM Reply Date | Days Elapsed | Date to PM | PM Approval (Yes/No) | PM Reply Date | Date to Accounts | Accounts Approval (Yes/No) | Accounts Approval Date | Days Elapsed | Date Paid | Amount Paid | Paid % | Payment Period (d) | Amount Pending
1 | #01 | JDH3-02-008-RWF-TS9-1-GEN-IPC-0120-00 | 0 | 3023610.066 | -302361.0066 | 0 | 408187.3589 |  | 3129436.4183 | 2024-07-29 | 2024-10-29 | 2024-10-29 | Y | 2024-10-29 | 0 | 2024-10-29 | Y | 2024-10-30
2 | #02 | JDH3-02-008-RWF-TS9-1-GEN-IPC-0162-00 | 0 | 1950678.159 | -195067.8159 | 0 | 263341.5515 |  | 2018951.8946 | 2024-10-30 | 2024-11-25 | 2024-11-25 | Y | 2024-11-25 | 0 | 2024-11-25 | Y | 2024-11-27 | [13 empty] | format if no, make shaded
3 | #03 | JDH3-02-008-RWF-TS9-1-GEN-IPC-0196-00 | 0 | 6773509.465 | -677350.9465 | 0 | 914423.7778 | -58000 | 6952582.2963 | 2024-11-26 | 2024-12-21 | 2024-12-22 | Y | 2024-12-22 | 0 | 2024-12-22 | Y | 2024-12-23
4 | #04 | JDH3-02-008-RWF-TS9-1-GEN-IPC-0216-00 | 0 | 2399993.3 | -239999.33 | 0 | 323999.0955 |  | 2483993.0655 | 2024-12-22 | 2024-12-31 | 2025-01-01 | Y | 2025-01-01 | 0 | 2025-01-01 | Y | 2025-01-01
5 | #05 | JDH3-02-008-RWF-TS9-1-GEN-IPC-0250-00 | 0 | 5065410.21 | -506541.021 | 0 | 683830.3784 | -125000 | 5117699.5674 | 2025-01-01 | 2025-01-27 | 2025-01-27 | Y | 2025-01-27 | 0 | 2025-01-27 | Y | 2025-01-27
6 | #06 | JDH3-02-008-RWF-TS9-1-GEN-IPC-0328-00 | 0 | 4209873.549 | -420987.3549 | 0 | 568332.9291 |  | 4357219.1232 | 2025-01-28 | 2025-03-01 | 2025-03-03 | Y | 2025-03-03 | 0 | 2025-03-03 | Y | 2025-03-03
7 | #07 | JDH3-02-008-RWF-TS9-1-GEN-IPC-0348-00 | 0 | 2256432.9 | -225643.29 | 0 | 304618.4415 |  | 2335408.0515 | 2025-03-02 | 2025-03-25 | 2025-03-25 | Y | 2025-03-25 | 0 | 2025-03-25 | Y | 2025-03-25
8 | #08 | JDH3-02-008-RWF-TS9-1-GEN-IPC-0403-00 | 0 | 5913349.88 | -591334.988 | 0 | 798302.2338 |  | 6120317.1258 | 2025-03-26 | 2025-04-29 | 2025-04-30 | Y | 2025-04-30 | 0 | 2025-04-30 | Y | 2025-04-30
9 | #09 | JDH3-02-008-RWF-TS9-1-GEN-IPC-0455-00 | 0 | 5666519.75 | -566651.975 | 0 | 764980.1663 |  | 5864847.9413 | 2025-04-30 | 2025-05-31 | 2025-06-01 | Y | 2025-06-01 | 0 | 2025-06-01 | Y | 2025-06-01
10 | #10 | JDH3-02-008-RWF-TS9-1-GEN-IPC-0484-00 | 0 | 4491831.043 | -449183.1043 | 0 | 606397.1908 |  | 4649045.1295 | 2025-06-01 | 2025-06-29 | 2025-07-01 | Y | 2025-07-01 | 0 | 2025-07-01 | Y | 2025-07-01
11 | #11 | JDH3-02-008-RWF-TS9-1-GEN-IPC-0504-00 | 0 | 30018472.118 | -3001847.2118 | 0 | 4052493.7359 |  | 31069118.6421 | 2025-06-30 | 2025-07-28 | 2025-07-29 | Y | 2025-07-29 | 0 | 2025-07-29 | Y | 2025-07-29
12 | #12 | JDH3-02-008-RWF-TS9-1-GEN-IPC-0573-00 | 0 | 20138174.8 | -2013817.48 | 0 | 2718653.598 |  | 20843010.918 | 2025-07-29 | 2025-09-02 | 2025-09-03 | Y | 2025-09-03 | 0 | 2025-09-03 | Y | 2025-09-03
13 | #13 | JDH3-02-008-RWF-TS9-1-GEN-IPC-0609-00 | 0 | 19138829.48 | -1913882.948 | 0 | 2583741.9798 |  | 19808688.5118 | 2025-09-03 | 2025-10-01 | 2025-10-02 | Y | 2025-10-02 | 0 | 2025-10-02 | Y | 2025-10-02
14 | #14 | JDH3-02-008-RWF-TS9-1-GEN-IPC-0645-00 | 0 | 17166096.7363 | -1716609.6736 | 0 | 2317423.0594 |  | 17766910.1221 | 2025-10-02 | 2025-11-03 | 2025-11-04 | Y | 2025-11-04 | 0 | 2025-11-04 | Y | 2025-11-04
15 | #15 | JDH3-02-008-RWF-TS9-1-GEN-IPC-0667-00 | 0 | 16969912.3169 | -1696991.2317 | 0 | 2290938.1628 |  | 17563859.248 | 2025-11-04 | 2025-11-30 | 2025-12-01 | Y | 2025-12-01 | 0 | 2025-12-01 | Y | 2025-12-01
16 | #16 | JDH3-02-008-RWF-TS9-1-GEN-IPC-0707-00 | 0 | 21074977.1 | -2107497.71 | 0 | 2845121.9085 |  | 21812601.2985 | 2025-12-01 | 2026-01-02 | 2026-01-03 | Y | 2026-01-03 | 0 | 2026-01-03 | Y | 2026-01-03
17 | #17 | JDH3-02-008-RWF-TS9-1-GEN-IPC-0743-00 | 0 | 19156496.58 | -1915649.658 | 0 | 2586127.0383 |  | 19826973.9603 | 2026-01-01 | 2026-02-03 | 2026-02-04 | Y | 2026-02-04 | 0 | 2026-02-04 | Y | 2026-02-04
18 | #18 | JDH3-02-008-RWF-TS9-1-GEN-IPC-0791-00 | 0 | 8008551.566 | -800855.1566 | 0 | 1081154.4614 |  | 8288850.8708 | 2026-02-04 | 2026-02-28 | 2026-03-17 | Y | 2026-03-24 | 7 | 2026-03-24 | Y | 2026-03-25
19 | #19 | JDH3-02-008-RWF-TS9-1-GEN-IPC-0793-00 | 0 | 7771884.8061 | -777188.4806 | 0 | 1049204.4488 |  | 8043900.7743 | 2026-03-01 | 2026-03-31 | 2026-04-05 | Y | 2026-04-05 | 0 | 2026-04-07 | Y | 2026-04-07
20 | #20 | JDH3-02-008-RWF-TS9-1-GEN-IPC-0808-00 | 0 | 9252098 | -925209.8 | 0 | 1249033.23 | -77000 | 9498921.43 | 2026-04-01 | 2026-04-30 | 2026-05-02 | Y | 2026-05-05 | 3 | 2026-05-06 | Y | 2026-05-06
21 | #21 | JDH3-02-008-RWF-TS9-1-GEN-IPC-0850-00 | 0 | 11034645 | -1103464.5 | 0 | 1489677.075 |  | 11420857.575 | 2026-05-01 | 2026-05-31 | 2026-06-02 | Y | 2026-06-05 | 3 | 2026-06-06 | Y | 2026-06-06
22 | #22 | JDH3-02-008-RWF-TS9-1-GEN-IPC-0890-00 | 0 | 7785923.9373 | -778592.3937 | 0 | 1051099.7315 |  | 8058431.2751 | 2026-06-01 | 2026-06-30 | 2026-07-04 | Y | 2026-07-04 | 0 | 2026-07-05 | Y | 2026-07-05 | [10 empty] | Under Review
23 | #23 | JDH3-02-008-RWF-TS9-1-GEN-IPC-0892-00 | 0 | 9184809.6062 | -918480.9606 | 0 | 1239949.2968 |  | 9506277.9424 | 2026-07-01 | 2026-07-31 | 2026-08-01 | Y | 2026-08-01 | 0 | 2026-08-04 | Y | 2026-08-04 | [10 empty] | Under Review
24 | #24 | JDH3-02-008-RWF-TS9-1-GEN-IPC-0903-00 | 0 | 11762052.57 | -1176205.257 | 0 | 1587877.097 |  | 12173724.41 | 2026-08-01 | 2026-08-31
25
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
|  |  | TOTAL | 250214132.9388 | -25021413.2939 | 0 |  | -260000 | 258711627.5917 | [14 empty] | 0 |  |  | 0
Note on J3: Without O&M Cost

## Invoice Ammount FIR
Weekly Report No. | Date Of Report | Time Intervals | Cumulative | Total Amount % (as Per Fir) | 319744875.72
1 | 2024-09-16 | 0 | 0 | 0%
2 | 2024-09-23 | 0 | 0 | 0%
3 | 2024-09-30 | 0 | 0 | 0%
4 | 2024-10-07 | 0 | 0 | 0%
5 | 2024-10-14 | 1103925.1052 | 1103925.1052 | 0.3453%
6 | 2024-10-21 | 1010342.2873 | 2114267.3925 | 0.6612%
7 | 2024-10-28 | 1519502.2716 | 3633769.6642 | 1.136%
8 | 2024-11-04 | 1370507.6873 | 5004277.3515 | 1.565%
9 | 2024-11-11 | 1097333.3679 | 6101610.7194 | 1.908%
10 | 2024-11-18 | 0 | 6101610.7194 | 1.908%
11 | 2024-11-25 | 1143192.8724 | 7244803.5918 | 2.266%
12 | 2024-12-02 | 827265.6716 | 8072069.2634 | 2.525%
13 | 2024-12-09 | 1646697.3881 | 9718766.6515 | 3.04%
14 | 2024-12-16 | 1135896.8657 | 10854663.5172 | 3.395%
15 | 2024-12-23 | 1092701.6418 | 11947365.159 | 3.737%
16 | 2024-12-30 | 2387944.3284 | 14335309.4873 | 4.483%
17 | 2025-01-06 | 1689182.1642 | 16024491.6515 | 5.012%
18 | 2025-01-13 | 1242575.6716 | 17267067.3231 | 5.4%
19 | 2025-01-20 | 1820039.0299 | 19087106.353 | 5.969%
20 | 2025-01-27 | 2367803.1343 | 21454909.4873 | 6.71%
21 | 2025-02-03 | 1901508.8657 | 23356418.353 | 7.305%
22 | 2025-02-10 | 1278496.4179 | 24634914.7709 | 7.705%
23 | 2025-02-17 | 1418687.7933 | 26053602.5642 | 8.148%
24 | 2025-02-24 | 930289.4776 | 26983892.0418 | 8.439%
25 | 2025-03-03 | 1121855.3731 | 28105747.4149 | 8.79%
26 | 2025-03-10 | 1413685.1754 | 29519432.5903 | 9.232%
27 | 2025-03-17 | 2174875.9194 | 31694308.5097 | 9.912%
28 | 2025-03-24 | 1422717.3134 | 33117025.8231 | 10.36%
29 | 2025-04-07 | 945273.5821 | 34062299.4052 | 10.65%
30 | 2025-04-14 | 2449678.4328 | 36511977.8381 | 11.42%
31 | 2025-04-21 | 3165989.9254 | 39677967.7634 | 12.41%
32 | 2025-04-28 | 3134879.9254 | 42812847.6888 | 13.39%
33 | 2025-05-05 | 3048918.8291 | 45861766.5179 | 14.34%
34 | 2025-05-12 | 3039488.3582 | 48901254.8761 | 15.29%
35 | 2025-05-19 | 2496481.7164 | 51397736.5925 | 16.07%
36 | 2025-05-26 | 2007573.1343 | 53405309.7269 | 16.7%
37 | 2025-06-01 | 2059391.4179 | 55464701.1448 | 17.35%
38 | 2025-06-15 | 2888513.1343 | 58353214.2791 | 18.25%
39 | 2025-06-22 | 2831252.3134 | 61184466.5925 | 19.14%
40 | 2025-06-29 | 6232949.7761 | 67417416.3687 | 21.08%
41 | 2025-07-06 | 3697661.1194 | 71115077.4881 | 22.24%
42 | 2025-07-13 | 7788220.1493 | 78903297.6373 | 24.68%
43 | 2025-07-20 | 4408300.4478 | 83311598.0851 | 26.06%
44 | 2025-07-27 | 2910172.9104 | 86221770.9955 | 26.97%
45 | 2025-08-03 | 3571862.3881 | 89793633.3836 | 28.08%
46 | 2025-08-10 | 4273059.1045 | 94066692.4881 | 29.42%
47 | 2025-08-17 | 3159385.2985 | 97226077.7866 | 30.41%
48 | 2025-08-24 | 3730589.1045 | 100956666.891 | 31.57%
49 | 2025-08-31 | 4143600.2985 | 105100267.1896 | 32.87%
50 | 2025-09-07 | 3754030.0746 | 108854297.2642 | 34.04%
51 | 2025-09-14 | 3126731.649 | 111981028.9132 | 35.02%
52 | 2025-09-21 | 4339038.0282 | 116320066.9414 | 36.38%
53 | 2025-09-28 | 4368902.5047 | 120688969.4461 | 37.75%
54 | 2025-10-05 | 2198902.5 | 122887871.9461 | 38.43%
55 | 2025-10-12 | 2273290.68 | 125161162.6261 | 39.14%
56 | 2025-10-19 | 5362773.94 | 130523936.5661 | 40.82%
57 | 2025-10-22 | 4774426.2604 | 135298362.8265 | 42.31%
58 | 2025-10-29 | 4127908.3035 | 139426271.13 | 43.61%
59 | 2025-11-05 | 4395836.4298 | 143822107.5598 | 44.98%
60 | 2025-11-16 | 5032453.4696 | 148854561.0294 | 46.55%
61 | 2025-11-23 | 3715706.9091 | 152570267.9385 | 47.72%
62 | 2025-11-30 | 3633446.3793 | 156203714.3178 | 48.85%
63 | 2025-12-07 | 5380732.53 | 161584446.8478 | 50.54%
64 | 2025-12-14 | 4517005.36 | 166101452.2078 | 51.95%
65 | 2025-12-21 | 5270940.9343 | 171372393.1422 | 53.6%
66 | 2025-12-28 | 3829106.7522 | 175201499.8944 | 54.79%
67 | 2026-01-04 | 2961816.2549 | 178163316.1493 | 55.72%
68 | 2026-01-11 | 2716890.8654 | 180880207.0146 | 56.57%
69 | 2026-01-18 | 2961816.25 | 183842023.2646 | 57.5%
70 | 2026-01-25 | 3378130.45 | 187220153.7146 | 58.55%
71 | 2026-02-01 | 3365955.3 | 190586109.0146 | 59.61%
72 | 2026-02-08 | 4026503.22 | 194612612.2346 | 60.86%
73 | 2026-02-15 | 3073326.73 | 197685938.9646 | 61.83%
74 | 2026-02-22 | 1624866.55 | 199310805.5146 | 62.33%
75 | 2026-03-01 | 1584439.8702 | 200895245.3849 | 62.83%
76 | 2026-03-08 | 1254832.12 | 202150077.5049 | 63.22%
77 | 2026-03-15 | 1398229.23 | 203548306.7349 | 63.66%
78 | 2026-03-29 | 1014430.82 | 204562737.5549 | 63.98%
79 | 2026-04-05 | 2389958.58 | 206952696.1349 | 64.72%
80 | 2026-04-12 | 1798326.7235 | 208751022.8584 | 65.29%
81 | 2026-04-19 | 2094142.65 | 210845165.5084 | 65.94%
82 | 2026-04-26 | 2389958.58 | 213235124.0884 | 66.69%
83 | 2026-05-03 | 2121614.32 | 215356738.4084 | 67.35%
84 | 2026-05-10 | 2084045.8073 | 217440784.2157 | 68%
85 | 2026-05-17 | 1772969.9004 | 219213754.116 | 68.56%
86 | 2026-05-24 | 2705760.9838 | 221919515.0998 | 69.41%
87 | 2026-06-07 | 2913635.9549 | 224833151.0548 | 70.32%
88 | 2026-06-14 | 1915772.0919 | 226748923.1467 | 70.92%
89 | 2026-06-21 | 1358074.2775 | 228106997.4242 | 71.34%
90 | 2026-06-28 | 1157982.8011 | 229264980.2253 | 71.7%
91 | 2026-07-05 | 1748243.9676 | 231013224.193 | 72.25%
92 | 2026-07-12 | 1651606.463 | 232664830.6559 | 72.77%
93 | 2026-07-19 | 2782350.5876 | 235447181.2435 | 73.64%
94 | 2026-07-26 | 3116232.6581 | 238563413.9016 | 74.61%
95 | 2026-08-02 | 3563202.0357 | 242126615.9372 | 75.72%
96 | 2026-08-09 | 2642681.4674 | 244769297.4046 | 76.55%
97 | 2026-08-16 | 2417117.2413 | 247186414.6459 | 77.31%
98 | 2026-08-23 | 1990039.9485 | 249176454.5943 | 77.93%
99 | 2026-08-30 | 1973917.2419 | 251150371.8363 | 78.55%
100 | 2026-09-06 | 2343484.5488 | 253493856.3851 | 79.28%
101 | 2026-09-13 | 4523007.1032 | 258016863.4883 | 80.69%
102 | 2026-09-20 | 11309798.688 | 269326662.1763 | 84.23%
103 | 2026-09-27 | 6679994.697 | 276006656.8733 | 86.32%
104 | 2026-10-04 | 1218219.3 | 277224876.1733 | 86.7%
105 | 2026-10-11 | 563019.3 | 277787895.4733 | 86.88%

## CCO
CONTRACT CHANGE ORDER (CCO)
CCO No. | Date Added | Description of Change | Status | SR | Sch Impact (Months) | Date Approved | Duration (days)
1 | 2025-07-16 | Revised BOQ | Completed | - | - | 2025-07-23 | -
2 | 2026-07-05 | EOT Approval | Completed | - | 2 | 2026-06-29 | -

## Procurement (hidden)
Sr. NO. | Project ID | ACT # in P6 | Item Description | Discipline | (Long\Short) Lead Items | BOQ. No. | Unit | Quantity | Proc. Qty | Required P.O Date | Date of Pur. Order Issued | Purchase Order No. | Supplier | Supplier Phone | Method of Shipping | Required on Job | E.D.A. to Site | A.D.A. to Site | Lead Time | Approval Status | The Impact (BOQ Cost) | Delivered Qty | Completion Rate | Remarks
1 | JDH3-02-008 | JDH3-02-008RRDPR733 | Pavement Materials - Retroreflective Thermoplastic White Traffic lines- Retroreflective Thermoplastic Yellow, Traffic lines | Road Marking | Short Lead Iteam | B1.32 17 23.01/B1.32 17 23.02 | m² | 19030 |  | 2025-03-01 17:00 |  |  |  |  | Land | 2025-03-21 17:00 |  |  |  |  | 1036754.4 |  | 0% | to be descoped. Needs to be revised as per revised BOQ
2 | JDH3-02-008 | JDH3-02-008RRDPR733 | Pavement Materials -Straight Arrow -(Right/left ) Arrow- Right-left Arrow-Straight-Right Arrow- Straight-Left Arrow | Road Marking | Short Lead Iteam | B1.32 17 23.03/B1.32 17 23.04//B1.32 17 23.05//B1.32 17 23.06//B1.32 17 23.07 | nr | 948.5 |  | 2025-03-01 17:00 |  |  |  |  | Land | 2025-03-21 17:00 |  |  |  |  | 105852.6 |  | 0% | to be descoped. Needs to be revised as per revised BOQ
3 | JDH3-02-008 | JDH3-02-008RRDPR733 | TRAFFIC SIGNAGE | Signage | Short Lead Iteam | B1.10 14 53.01 / B1.10 14 53.02 | unit | 1408 |  | 2025-03-01 17:00 |  |  |  |  | Land | 2025-03-21 17:00 |  |  |  |  | 2793027.98 |  | 0% | to be descoped. Needs to be revised as per revised BOQ
4 | JDH3-02-008 | JDH3-02-008RRDPR732 | PRECAST CONCRETE CURB | Kerbstone | Short Lead Iteam | B1.32 14 13.01/B1.32 14 13.02/B1.32 14 13.03 | m | 313864 | 57030 | 2025-02-22 17:00 | 2024-10-29 | 24105611 | Taiba Al Khair Development. Co | +966 126946407 | Land | 2025-03-14 17:00 |  | 2024-11-11 |  | Material Approved | 20387468.17 | 15084 | 4.806%
5 | JDH3-02-008 | JDH3-02-008RRDPR732 | PRECAST INTERLOCKING BLOCK PAVERS | Interlock | Short Lead Iteam | B1.32 14 13.13.01 | m² | 59537.2818 | 25990 | 2025-02-22 17:00 | 2024-10-29 | 24105611 | Taiba Al Khair Development. Co | +966 126946407 | Land | 2025-03-14 17:00 |  | 2024-11-11 |  | Material Approved | 3764542.3282 | 4088.24 | 6.867%
6 | JDH3-02-008 | JDH3-02-008RRDPR731 | EARTHWORKS AND SITE GRADING-300mm thick Subgrade AGGREGATE BASE COURSE-300mm thick Aggregate base course BITUMINOUS CONSTRUCTION-Bituminous concrete wearing course, (Grading I - Class A), including tack coat (RC2) | Road work | Short Lead Iteam | B1.31 22 00.01/B1.32 11 23.01/B1.32 11 26.01 | m3 | 9021 | 2520 | 2025-02-15 17:00 |  |  | Masharaf EL Torq |  | Land | 2025-03-07 17:00 |  |  |  | Material Approved | 1688143.5 | 2520 | 27.93%
7 | JDH3-02-008 | JDH3-02-008RRDPR730 | ASPHALT WEARING COURSE -Bituminous concrete wearing course, (Grading I - Class A), including tack coat (RC2) | Road work | Short Lead Iteam | B1.32 12 16.01 | m3 | 63689 |  | 2025-02-08 17:00 |  |  | خلاطة الرواف |  | Land | 2025-02-28 17:00 |  |  |  |  | 37237047.63 |  | 0%
8 | JDH3-02-008 | JDH3-02-008RELPR714 | MEDIUM VOLTAGE CABLES DUCT BANKS | MV | Short Lead Iteam | B2.33 71 19.01 | m | 950 |  | 2025-01-13 17:00 |  |  |  |  | Land | 2025-04-13 17:00 |  |  |  |  | 383534 |  | 0% | to be descoped. Needs to be revised as per revised BOQ
9 | JDH3-02-008 | JDH3-02-008RELPR713 | LOW VOLTAGE CABLES | LV | Short Lead Iteam | B2.26 05 19.01/B2.26 05 19.02/B2.26 05 19.03/B2.26 05 19.04/B2.26 05 19.05/B2.26 05 19.06 / B2.26 05 19.07/B2.26 05 19.08 | m | 26353 | 106000 | 2025-01-27 17:00 | 2024-12-09 | 24106558 | Jeddah cabels | +9662 6644350 | Land | 2025-04-27 17:00 | 2025-05-10 |  | 102.2917 | Material Approved | 1809503.29 | 38238 | 36.07%
10 | JDH3-02-008 | JDH3-02-008RELPR715 | MEDIUM VOLTAGE CABLES - 3 Core AL . Cable 13.8 kV 3Cx500 mm² AL./XLPE /PVC. Unarmored | MV | Long Lead Iteam | B2.26.05.13.16.01 | m | 30720 |  | 2025-01-20 17:00 |  |  |  |  | Land | 2025-04-20 17:00 |  |  |  |  | 6574694.4 |  | 0% | to be descoped. Needs to be revised as per revised BOQ
11 | JDH3-02-008 | JDH3-02-008RELPR715 | MEDIUM VOLTAGE CABLES -Straight joints cables for 13.8 kv 3Cx 500 mm², Al /XLPE/LLDPE -Cable Termination for 13.8 kv 3Cx 500 mm², Al /XLPE/LLDPE | MV | Long Lead Iteam | B2.26.05.13.16.02/B2.26.05.13.16.03 | unit | 78 |  | 2025-01-20 17:00 |  |  |  |  | Land | 2025-04-20 17:00 |  |  |  |  | 246611.04 |  | 0% | to be descoped. Needs to be revised as per revised BOQ
12 | JDH3-02-008 | JDH3-02-008RELPR712 | MEDIUM VOLTAGE SWITCHGEARS - Normally Open Point (R M U) 13.8 kv for Outdoor type according to the Saudi Electric Company specifications and requirements | MV | Long Lead Iteam | B2.26 13 00.01 | unit | 2 |  | 2025-01-27 17:00 |  |  |  |  | Land | 2025-04-27 17:00 |  |  |  |  | 106864.94 |  | 0% | to be descoped. Needs to be revised as per revised BOQ
13 | JDH3-02-008 | JDH3-02-008RSLPR725 | ROAD CROSSING DUCTS | Ducts | Short Lead Iteam | B2.33 71 19.01.SL/B2.33 71 19.02/B2.33 71 19.03 | m | 580 |  | 2025-01-27 17:00 |  |  | National Kham Plastic Factory |  | Land | 2025-02-16 17:00 |  |  |  | Material Approved | 100067.1 |  | 0%
14 | JDH3-02-008 | JDH3-02-008RSLPR718 | DRAWPITS | Street Lighting | Long Lead Iteam | B2.33 71 19.13.01/B2.33 71 19.13.02/B2.33 71 19.13.03 | Unit | 52 |  | 2025-01-27 17:00 |  |  | FALCOM |  | Land | 2025-04-27 17:00 |  |  |  | Material Approved | 12836.44 |  | 0%
15 | JDH3-02-008 | JDH3-02-008RSLPR719 | LIGHTING POLES | Street Lighting | Long Lead Iteam | B2.26.56.19.01/ B2.26 56 19.02 | Unit | 265 |  | 2025-01-20 17:00 | 2025-05-05 |  | Alyamama & Bantain |  | Land | 2025-04-20 17:00 | 2025-05-30 |  | 129.2917 | Material Approved | 1417732.55 |  | 0%
16 | JDH3-02-008 | JDH3-02-008RSLPR722 | STREET LIGHTING LUMINAIRE | Street Lighting | Long Lead Iteam | B2.26.56.19.01/B2.26.56.19.02/B2.26.56.19.03 | Unit | 370 |  | 2025-01-06 17:00 |  |  | SAUDI LIGHTING PHILIPS |  | Land | 2025-04-06 17:00 |  |  |  | Material Approved | 401054 |  | 0%
17 | JDH3-02-008 | JDH3-02-008RSLPR717 | STREET LIGHTING SUB-STATION | Street Lighting | Long Lead Iteam | B2.26 11 16.02 | Unit | 3 |  | 2025-01-20 17:00 |  |  |  |  | Land | 2025-04-20 17:00 |  |  |  |  | 230183.31 |  | 0% | to be descoped. Needs to be revised as per revised BOQ
18 | JDH3-02-008 | JDH3-02-008RSLPR723 | Ring Main Unit RMU, 13.8KV, According to the specifications and standards of SEC | Street Lighting | Long Lead Iteam | B2.26 11 16.04 | Unit | 3 |  | 2025-01-13 17:00 |  |  |  |  | Land | 2025-04-13 17:00 |  |  |  |  | 53432.47 |  | 0% | to be descoped. Needs to be revised as per revised BOQ
19 | JDH3-02-008 | JDH3-02-008RSLPR720 | EARTHING SYSTEM | Street Lighting | Long Lead Iteam | B2.26 05 26.01 | Unit | 20 |  | 2024-12-30 17:00 |  |  | Furse- Tabark Company |  | Land | 2025-03-30 17:00 |  |  |  | Material Approved | 11284.8 |  | 0%
20 | JDH3-02-008 | JDH3-02-008RSLPR721 | Lighting panels | Street Lighting | Long Lead Iteam | B2.26 24 16.01/B2.26 24 16.02 | Unit | 6 |  | 2024-12-30 17:00 |  |  |  |  | Land | 2025-03-30 17:00 |  |  |  |  | 72465.81 |  | 0%
21 | JDH3-02-008 | JDH3-02-008RTCPR727 | TELECOMMUNICATIONS-DUCTS | Ducts | Short Lead Iteam | B2.33 71 19.02.TEL | m | 8100 |  | 2025-02-03 17:00 |  |  | Alwasail Industrial Co |  | Land | 2025-02-23 17:00 |  |  |  | Material Approved | 827415 |  | 0%
22 | JDH3-02-008 | JDH3-02-008RTCPR728 | TELECOMMUNICATIONS-MANHOLES | Telecommunication | Short Lead Iteam | B2.33.71.19.13.01 | nr | 93 |  | 2025-02-10 17:00 |  |  | FALCOM |  | Land | 2025-03-02 17:00 |  |  |  | Material Approved | 411654.48 |  | 0%
23 | JDH3-02-008 | JDH3-02-008RWTPR697 | PIPEWORK - VALVES | Potable water | Short Lead Iteam | B3.33 14 19.01/B3.33 14 19.02/B3.33 14 19.03/B3.33 14 19.05/B3.33 14 19.06/B3.33 14 19.08 | nr | 250 | 178 | 2025-01-13 17:00 | 2024-10-27 | 24105567 | SPS | +966504401239 | Land | 2025-04-13 17:00 |  | 2024-11-01 |  | Material Approved | 3767041.47 | 178 | 71.2%
24 | JDH3-02-008 | JDH3-02-008RWTPR694 | POTABLE WATER -PIPEWORK-PIPES- High Density Polyethylene pipes PE 100 SDR 11 (PN 16 Bars) | Potable water | Short Lead Iteam | B3.33 14 13.01/B3.33 14 13.02/B3.33 14 13.03/B3.33 14 13.04/B3.33 14 13.05 | m | 23742 | 5520 | 2024-12-30 17:00 | 2024-11-25 | 24106224 | sps MUNIF | +966504401239 +966507779468 | Land | 2025-03-30 17:00 |  | 2024-12-01 |  | Material Approved | 5352889.06 | 5520 | 23.25%
25 | JDH3-02-008 | JDH3-02-008RWTPR690 | POTABLE WATER - PIPEWORK-Valve chambers - Civil Works | Potable water | Short Lead Iteam | B3.33 14 13.011/B3.33 14 13.011/B3.33 14 13.10 | nr | 11 |  | 2024-12-30 17:00 |  |  | العربية الراجحي |  | Land | 2025-03-30 17:00 |  |  |  |  | 182271.65 |  | 0% | to be constructed at site
26 | JDH3-02-008 | JDH3-02-008RSEPR705 | TSE NETWORK -High Density Polyethylene pipes PE 100 SDR 11 ( PN 16 Bars) | TSE | Short Lead Iteam | B4.33 31 00.01/B4.33 31 00.02/B4.33 31 00.03/B4.33 31 00.04/B4.33 31 00.05/B4.33 31 00.06/B4.33 31 00.07/B4.33 31 00.08/B4.33 31 00.09/B4.33 31 00.10B4.33 31 00.11/B4.33 31 00.12/B4.33 31 00.13/B4.33 31 00.14/B4.33 31 00.15/B4.33 31 00.16/B4.33 31 00.17/B4.33 31 00.18 | m | 69985 | 57408 | 2024-10-21 17:00 | 25-11-24 & 11-12-24 | 24106224 & 24106620 | sps MUNIF/ Al Wasail Industrial Company | +966504401239 +966507779468 | Land | 2025-01-19 17:00 |  | 2024-12-01 |  | Material Approved | 37305016.86 | 38800 | 55.44%
27 | JDH3-02-008 | JDH3-02-008RSEPR704 | TSE NETWORK -Glass Reinforced Plastic (GRP) Pipe | TSE | Short Lead Iteam | B4.33 05 36.01/B4.33 05 36.02/B4.33 05 36.03/B4.33 05 36.04/B4.33 05 36.05/B4.33 05 36.06/B4.33 05 36.07 | m | 998 |  | 2024-10-21 17:00 |  |  | T- NAGADI | +966564510408 | Land | 2024-11-10 17:00 |  |  |  | Material Approved | 1705859.33 |  | 0%
28 | JDH3-02-008 | JDH3-02-008RSEPR707 | TSE NETWORK - PIPEWORK - VALVES | TSE | Long Lead Iteam | B4.33 14 19.01/B4.33 14 19.02/B4.33 14 19.03/B4.33 14 19.04/B4.33 14 19.05/B4.33 14 19.06/B4.33 14 19.07/B4.33 14 19.08/B4.33 14 19.09/B4.33 14 19.15/B4.33 14 19.16/B4.33 14 19.17 | nr | 967 |  | 2024-10-21 11:00 |  |  | SPS | +966504401239 | Land | 2025-01-19 11:00 |  |  |  | Material Approved | 7069890.72 |  | 0%
29 | JDH3-02-008 | JDH3-02-008RSEPR701 | TSE NETWORK -PIPEWORK-Valve chambers - Civil Works | TSE | Short Lead Iteam | B4.33 14 13.01/B4.33 14 13.02/B4.33 14 13.03/B4.33 14 13.06/B4.33 14 13.07/B4.33 14 13.08/B4.33 14 13.10/B4.33 14 13.11/B4.33 14 13.12 | nr | 231 |  | 2024-10-21 17:00 |  |  | العربية الراجحي |  | Land | 2024-11-10 17:00 |  |  |  |  | 2976403.01 |  | 0% | to be constructed at site
30 | JDH3-02-008 | JDH3-02-008RSSPR677 | SEWERAGE NETWORK-Glass Reinforced Plastic (GRP): SN 5000 up to depth 3.5 m SN 10000 depth more than 3.5 m | Sewer drainage | Short Lead Iteam | B5.33 31 00.03/B5.33 31 00.04/B5.33 31 00.05/B5.33 31 00.10/B5.33 31 00.11/B5.33 31 00.12/B5.33 31 00.13 | m | 29561 | 10548 | 2024-09-29 17:00 | 2024-10-20 | 3100000503 & 24105376 | T- NAGADI | +966564510408 | Land | 2024-10-19 17:00 |  | 2024-11-23 |  | Material Approved | 13012996.09 | 10548 | 35.68%
31 | JDH3-02-008 | JDH3-02-008RSSPR674 | SEWERAGE NETWORK- PIPEWORK - MANHOLES AND PIPEWORK ANCILLARIES | Sewer drainage | Short Lead Iteam | B5.33 05 13.01/B5.33 05 13.02/B5.33 05 13.03/B5.33 05 13.04/B5.33 05 13.05/B5.33 05 13.06/B5.33 05 13.15/B5.33 05 13.16/B5.33 05 13.17/B5.33 05 13.18/B5.33 05 13.19/B5.33 05 13.20/B5.33 05 13.21/B5.33 05 13.22/B5.33 05 13.23/B5.33 05 13.24 | nr | 361 | 107 | 2024-09-29 17:00 | 2024-11-12 | 24105949 | T- NAGADI | +966564510408 | Land | 2024-10-19 17:00 |  | 2024-11-30 |  | Material Approved | 468902.17 | 107 | 29.64%
32 | JDH3-02-008 | JDH3-02-008RSTPR685 | STORM WATER DRAINAGE NETWORK-Circular pipes (uPVC) | Strom water | Short Lead Iteam | B6.33 14 11.01 | m | 28700 | 23562 | 2024-10-07 17:00 | 27-10-24 14-12-24 & 15-04-2025 | 3100000788 & 3100003912 | NATIONAL KHAM MUNIF | +966580580520 +966507779468 | Land | 2025-01-05 17:00 |  | 2024-11-09 |  | Material Approved | 16752190 | 2460 | 8.571%
33 | JDH3-02-008 | JDH3-02-008RSTPR684 | STORM WATER DRAINAGE NETWORK-Circular pipes (GRP)-SN 5000 up to depth 3.5 m SN 10000 depth more than 3.5 m | Strom water | Short Lead Iteam | B6.33 42 11.01/B6.33 42 11.02/B6.33 42 11.03/B6.33 42 11.04/B6.33 42 11.05/B6.33 42 11.06/B6.33 42 11.07/B6.33 42 11.08/B6.33 42 11.09/B6.33 42 11.10/B6.33 42 11.11/B6.33 42 11.12/B6.33 42 11.13/B6.33 42 11.14/B6.33 42 11.15/B6.33 42 11.16/B6.33 42 11.19/B6.33 42 11.20/B6.33 42 11.21/B6.33 42 11.22/B6.33 42 11.23/B6.33 42 11.24 | m | 44340 | 44514 | 2024-10-03 17:00 | 27-10-24 & 04-11-24 | 3100001250, 3100003898 & 3100001230 | Advanced Pipe Solutions Company | +96613 812 7766 | Land | 2024-10-23 17:00 |  | 2024-11-28 |  | Material Approved | 48410377 | 26646 | 60.09%
34 | JDH3-02-008 | JDH3-02-008RSTPR681 | STORM WATER DRAINAGE NETWORK-Precast concrete Box culverts (Box conduit) | Strom water | Short Lead Iteam | B6.35 42 16.01/B6.36 42 16.02/B6.34 42 16.03/B6.35 42 16.04/B6.34 42 16.05/B6.34 42 16.06/B6.34 42 16.07/B6.34 42 16.08/B6.34 42 16.09 | m | 3760 |  | 2024-10-07 17:00 |  |  |  |  | Land | 2024-10-27 17:00 |  | 2024-11-21 |  | Material Approved | 24770880.17 | 1096 | 29.15% | Box culvert is constructed at site
35 | JDH3-02-008 | JD3RZ02-1L69ST6773 | STORM NETWORK- PIPEWORK - MANHOLES AND PIPEWORK ANCILLARIES | Strom water | Short Lead Iteam | B6.33 05 39.01/ B6.33 05 39.02/ B6.33 05 39.03/ B6.33 05 39.04/ B6.33 05 39.05/ B6.33 05 39.06/ B6.33 05 39.07/ B6.33 05 39.08 | nr | 680 | 558 | 2024-09-29 17:00 | 2024-12-11 | 24106626 | T- NAGADI | +966564510408 | Land | 2024-10-19 17:00 |  | 2025-01-24 |  | Material Approved | 468902.17 | 135 | 19.85%
36 | JDH3-02-008 | JDH3-02-008RSTPR686 | STORM WATER DRAINAGE NETWORK-Catch basin | Strom water | Short Lead Iteam | B6.33 05 39.09/B6.33 05 39.10 | nr | 1320 | 511 | 2024-10-13 17:00 | 2025-01-22 | 25100372 | T- NAGADI FALCON | +966564510408 | Land | 2024-11-02 17:00 |  | 2025-02-06 |  | Material Approved | 14713071 | 67 | 5.076%
37 | JDH3-02-008 | JDH3-02-008RSTPR680 | STORM WATER DRAINAGE NETWORK-Riprap with thickness 300mm | Strom water | Short Lead Iteam | B6.03 30 00.01/B6.03 30 00.03/B6.03 30 00.05/B6.03 30 00.07 | m2 | 165820 | 77130 | 2024-10-03 17:00 |  |  | Beto Co LTD |  | Land | 2024-10-23 17:00 |  | 2024-11-18 |  | Material Approved | 16864573.3 | 100000 | 60.31%
38 | JDH3-02-008 | JDH3-02-008RSTPR683 | STORM WATER DRAINAGE NETWORK-Insulation for channel bed and side slopes with 500mm thickness | Strom water | Short Lead Iteam | B6.31 25 00.01/B6.31 25 00.02/B6.31 25 00.03/B6.31 25 00.04 | m2 | 122003 |  | 2024-10-03 17:00 |  |  | الكسارة |  | Land | 2024-10-23 17:00 |  |  |  |  | 6172131.77 |  | 0% | to be descoped. Needs to be revised as per revised BOQ
39 | JDH3-02-008 | JDH3-02-008RSTPR682 | STORM WATER DRAINAGE NETWORK-Filling | Strom water | Short Lead Iteam | B6.31 22 00.11/B6.31 22 00.12/B6.31 22 00.08/B6.31 22 00.09/B6.31 22 00.05/B6.31 22 00.06/B6.31 22 00.02/B6.31 22 00.03 | m³ | 7050 |  | 2024-10-03 17:00 |  |  | الكسارة |  | Land | 2024-10-23 17:00 |  |  |  |  | 250972.5 |  | 0% | to be descoped. Needs to be revised as per revised BOQ
40 | JDH3-02-008 | JDH3-02-008RSTPR680 | STORM WATER DRAINAGE NETWORK-Swales -Concrete lining 35Mpa | Strom water | Short Lead Iteam | B6.03 30 00.09 | m³ | 1500 |  | 2024-10-03 17:00 |  |  | العربية |  | Land | 2024-10-23 17:00 |  |  |  |  | 2276415 |  | 0% | to be descoped. Needs to be revised as per revised BOQ
41 | JDH3-02-008 | JDH3-02-008RSTPR680 | STORM WATER DRAINAGE NETWORK-Manhole cover | Strom water | Short Lead Iteam | B5.33 05 13.01/B5.33 05 13.02/B5.33 05 13.03/B5.33 05 13.04/B5.33 05 13.05/B5.33 05 13.06/B5.33 05 13.15/B5.33 05 13.16/B5.33 05 13.17/B5.33 05 13.18/B5.33 05 13.19/B5.33 05 13.20/B5.33 05 13.21/B5.33 05 13.22/B5.33 05 13.23/B5.33 05 13.24B6.33 05 39.01/ B6.33 05 39.02/ B6.33 05 39.03/ B6.33 05 39.04/ B6.33 05 39.05/ B6.33 05 39.06/ B6.33 05 39.07/ B6.33 05 39.08 | nr | 1041 | 689 | 2024-09-04 17:00 | 2025-03-06 | 3100002066 | JDFF |  | Land | 2024-10-19 17:00 |  | 2025-04-23 |  | Material Approved | 468902.17 | 101 | 9.702%
42 | JDH3-02-008 | JDH3-02-008RSTPR680 | POTABLE WATER NETWORK-FIRE HYDRANT | Potable water | Short Lead Iteam | B3.33 14 19.08 | nr | 218 | 200 | 2025-02-24 |  | 3100000790 | SPS |  | Land | 2025-02-24 |  | 2024-11-10 |  | Material Approved | 3115939.78 | 173 | 79.36%

## Issues
[8 empty] | 11-10-2026 | Status | Responsibility
[9 empty] | Open | Contractor
[9 empty] | Closed | Consultant
Modon
Third Party
Other
Issue Log
Issue No | Date Identified | Issue Description | Responsibility | Action Taken | Current Status | Expected/Actual Closure | Duration Elapsed
1 | 2024-09-17 | The surveying in the project was initially conducted by taking random points until an email was sent by the owner on August 27, 2024, stating the need to change the method of collecting survey points. As a result, the work had to be redone, leading to an increase in the workload beyond what was planned, which caused a delay in the project. | Modon | The work is ongoing according to Madon's requirements. | Closed | 2024-08-27 | 29
2 | 2024-09-17 | GPS device signal was disconnecting because of bad weather conditions and strong winds, there were delays in the surveying work . | Other | Waiting until the weather improves | Closed
3 | 2024-09-17 | RFI There is an issue with the official response, as we have not received all the replies except for some matters related to electricity. | Modon | Acclerate official response | Closed
4 | 2024-09-24 | The As-Built drawings do not match the actual site conditions, which requires excavation with Equipments across the connection area. | Modon | A report on the As-Built status was submitted to the consultant on 19th August 2024 | Active | 2024-09-30 | 42
5 | 2024-09-24 | There was a delay in responding to the RFI. | Modon | There was a delay in responding to the inquiries, which were officially submitted to the consultant via emails starting from 10th August 2024. The inquiries were fully addressed by 12th September 2024 through online meetings. However, we have only received official responses for 51 out of 56 inquiries | Closed | 2024-09-30 | 51
6 | 2024-09-24 | The cross section (utility corridor) included in the contract documents does not match the actual site conditions. | Modon | A cross section for each road must be prepared and approved before starting the plans | Active
7 | 2024-09-24 | One of the factories is located within the work area, which requires a redistribution of the networks in these roads. We have not yet received the official response from the consultant regarding the solution. | Modon |  | Active
8 | 2024-09-24 | The scope of work has changed, as the survey indicates the presence of existing lines, which alters the redistribution of the networks and reduces the value of the work, as occurred with the industrial sewage and water networks. | Modon |  | Active
9 | 2024-09-24 | The scope of work for the industrial sewage network has changed | Modon | The matter is currently under review, and the drawings are being revised | Closed | 2024-08-24 | 37
10 | 2024-09-24 | Changes in scope of Storm networks | Modon | The matter is currently under review, and the drawings are being revised | Closed | 2024-09-04 | 20
11 | 2024-09-24 | Changes in design of Ponds | Modon | The matter is currently under review, and the drawings are being revised | Closed | 2024-09-04 | 20
12 | 2024-09-24 | Changes in design of Swales | Modon | The matter is currently under review, and the drawings are being revised | Closed | 2024-09-04 | 20
13 | 2024-09-24 | Receipt of the approved and stamped plans (design or specifications) from the owner on the dates (24-7-2024, 24-8-2024, 4-9-2024, and 10-9-2024) | Modon |  | Closed
14 | 2024-10-21 | The scope of work has changed, as the survey indicates the presence of existing lines of MV lines | Modon |  | Active | 2024-11-15 | 720
15 | 2024-11-10 | Box culvert excavation at Zone 01 has more exsiting utilities | Contractor | Work has to be completed very carefully. Slow progress will be maintained. | Active
16 | 2024-11-10 | Box culvert excavation at Zone 06 conflict with factory also entrance | Modon | Work has to be completed very carefully. Slow progress will be maintained. | Active
17 | 2024-12-20 | MV cable as built data didn't provide to contractor | Modon | Work has to be completed very carefully. Slow progress will be maintained. | Active
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
Formulas:
Duration Elapsed = TODAY()-[Date Identified]

## Manpower
Head-Count (Manual)
MONTHS | 2024-07-29 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31
Plan - Monthly | 0 | 4.8 | 170.4 | 214.4 | 161 | 296.5 | 383.8 | 291.7 | 228.3 | 165.2 | 89.3 | 100.7 | 101.9 | 211.9 | 411.1 | 601.8 | 447.5 | 472.1 | 662.5 | 794.1 | 675.6 | 502 | 413 | 255 | 14.3
Planned - Cumulative | 0 | 4.8 | 175.2 | 389.6 | 550.6 | 847.1 | 1230.9 | 1522.6 | 1750.9 | 1916.1 | 2005.4 | 2106.1 | 2208 | 2419.9 | 2831 | 3432.8 | 3880.3 | 4352.4 | 5014.9 | 5809 | 6484.6 | 6986.6 | 7399.6 | 7654.6 | 7668.9
Actual - Monthly | 0.93333 | 5 | 15 | 73 | 151 | 206 | 220 | 144 | 258 | 296 | 422 | 419 | 423 | 359 | 394 | 389 | 447.5 | 472.1 | 312
Actual Cumulative | 0.93333 | 5.1077 | 20.1077 | 93.1077 | 244.1077 | 450.1077 | 670.1077 | 814.1077 | 1072.1077 | 1368.1077 | 1790.1077 | 2209.1077 | 2632.1077 | 2991.1077 | 3385.1077 | 3774.1077 | 4221.6077 | 4693.7077 | 5005.7077
Forecast - Monthly | [19 empty] | 794.1 | 675.6 | 502 | 413 | 255 | 14.3
Saudi Monthly - Actual
Head-Count (Non-Manual)
MONTHS | 2024-07-29 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31
Plan - Monthly | 13 | 20 | 25 | 27 | 30 | 32 | 35 | 37 | 40 | 43 | 45 | 46 | 46 | 46 | 86 | 86 | 90 | 92 | 93 | 93 | 93 | 93 | 76 | 60 | 49
Planned - Cumulative | 13 | 33 | 58 | 85 | 115 | 147 | 182 | 219 | 259 | 302 | 347 | 393 | 439 | 485 | 571 | 657 | 747 | 839 | 932 | 1025 | 1118 | 1211 | 1287 | 1347 | 1396
Actual - Monthly | 0.93333 | 10 | 14 | 23 | 26 | 30 | 33 | 34 | 42 | 79 | 110 | 161 | 161 | 109 | 118 | 116 | 114 | 114 | 75 | [20 empty] | 30
Actual Cumulative | 0.93333 | 10.9333 | 24.9333 | 47.9333 | 73.9333 | 103.9333 | 136.9333 | 170.9333 | 212.9333 | 291.9333 | 401.9333 | 562.9333 | 723.9333 | 832.9333 | 950.9333 | 1066.9333 | 1180.9333 | 1294.9333 | 1369.9333
Forecast - Monthly | [19 empty] | 115 | 115 | 115 | 102 | 60 | 49
Saudi - Actual | 0 | 1 | 1 | 0.77778 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2
Head-Count (Manual) | [31 empty] | Month |  | 2026-10-31 |  |  |  | 2026-11-30
Planned | Actual |  | Variance |  | Forecast Next Month |  | Saudi Staff
0 | 1092 |  | 1092 |  | 0 |  | 0
Head-Count (Non-Manual) | [10 empty] | Man Power by Trade
Planned | Actual |  | Variance |  | Forecast Next Month |  | Saudi Staff |  |  |  | Key Trade |  | General Labor |  | Carpenter |  | Plumber |  | Electrician |  | Steel Fixer |  | Mason |  | Others |  | Total
0 | 92 |  | 92 |  | 0 |  | 0 |  |  |  | Plan |  | 288 |  | 42 |  | 26 |  | 0 |  | 36 |  | 38 |  | 172 |  | 602
[11 empty] | Actual |  | 139 |  | 39 |  | 39 |  | 0 |  | 39 |  | 0 |  | 133 |  | 389
Equipment
MONTHS | 2024-07-29 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31
Plan - Monthly | 0 | 2.8 | 80.8 | 68 | 49.1 | 112 | 145.9 | 98.5 | 58.5 | 57.9 | 42.4 | 41.4 | 34.3 | 95.1 | 183.6 | 166.6 | 94.8 | 133.1 | 216.8 | 248.5 | 195.6 | 135.9 | 124.2 | 90.3 | 9.4
Planned - Cumulative | 0 | 2.8 | 83.6 | 151.6 | 200.7 | 312.7 | 458.6 | 557.1 | 615.6 | 673.5 | 715.9 | 757.3 | 791.6 | 886.7 | 1070.3 | 1236.9 | 1331.7 | 1464.8 | 1681.6 | 1930.1 | 2125.7 | 2261.6 | 2385.8 | 2476.1 | 2485.5
Actual - Monthly |  |  | 15 | 52 | 50 | 61 | 58 | 35 | 91 | 141 | 187 | 186 | 181 | 108 | 133 | 138
Actual Cumulative |  |  | 1.5 | 53.5 | 103.5 | 164.5 | 222.5 | 257.5 | 348.5 | 489.5 | 676.5 | 862.5 | 1043.5 | 1151.5 | 1284.5 | 1422.5
Forecast - Monthly | [16 empty] | 94.8 | 133.1 | 216.8 | 248.5 | 195.6 | 135.9 | 124.2 | 90.3 | 9.4
Equipment Count (Manhour)
Planned | Actual |  | Idle |  | Variance |  | Forecast Next Month
0 | 135 |  | 3 |  | 135 |  | 0
Type | Excavator | Fork lift | Loader | Dumper | Dozer | Grader | Dumper |  | Fork lift |  | Grader |  | Other |  | Total
Plan | 55 |  | 5 |  | 2 |  | 50 |  | 2 |  | 1 |  | 52 |  | 167
Actual | 49 |  | 4 |  | 1 |  | 37 |  | 1 |  |  |  | 43 |  | 135
Idle | 1 | [5 empty] | 1 | [5 empty] | 1 |  | 3
Manpower Calculation
| 2024-07-29 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31
|  | 48 | 1704 | 2144 | 1610 | 2965 | 3838 | 2917 | 2283 | 1652 | 893 | 1007 | 1019 | 2119 | 4111 | 6018 | 4475 | 4721 | 6625 | 7941 | 6756 | 5020 | 4130 | 2550 | 143
|  | 48 | 1752 | 3896 | 5506 | 8471 | 12309 | 15226 | 17509 | 19161 | 20054 | 21061 | 22080 | 24199 | 28310 | 34328 | 38803 | 43524 | 50149 | 58090 | 64846 | 69866 | 73996 | 76546 | 76689
| 28 | 1300 | 1260 | 8588 | 9555
| 28 | 1328 | 4019 | 12607 | 22162
[5 empty] | 6196 | 10380 | 9361 | 20963 | 21978 | 25326 | 28991 | 31119 | 40775 | 39548 | 47389 | 35135 | 20733 | 30705 | 26460 | 13085 | 11881 | 6612 | 4265 | 2218 | 1741 | 1349 | 1547 | 390
|  |  | 250 | 210
Work day in Months | 3 | 26 | 25 | 27 | 25 | 27 | 26 | 24 | 27 | 26 | 26 | 26 | 27 | 26 | 26 | 26 | 26 | 27 | 26 | 24 | 27 | 26 | 26 | 26 | 24 | 26 | 26 | 26
Man-day - Plan | 0 | 4.8 | 170.4 | 214.4 | 161 | 296.5 | 383.8 | 291.7 | 228.3 | 165.2 | 89.3 | 100.7 | 101.9 | 211.9 | 411.1 | 601.8 | 447.5 | 472.1 | 662.5 | 794.1 | 675.6 | 502 | 413 | 255 | 14.3 | 0 | 0 | 0
Man-day - Cu Plan | 0 | 4.8 | 175.2 | 389.6 | 550.6 | 847.1 | 1230.9 | 1522.6 | 1750.9 | 1916.1 | 2005.4 | 2106.1 | 2208 | 2419.9 | 2831 | 3432.8 | 3880.3 | 4352.4 | 5014.9 | 5809 | 6484.6 | 6986.6 | 7399.6 | 7654.6 | 7668.9 | 0 | 0 | 0
Man-day - Actual | 2.8 | 130 | 126 | 858.8 | 955.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Man-day - Cu. Act | 2.8 | 132.8 | 401.9 | 1260.7 | 2216.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Man-day - Remai. |  |  |  | 0 | 619.6 | 1038 | 936.1 | 2096.3 | 2197.8 | 2532.6 | 2899.1 | 3111.9 | 4077.5 | 3954.8 | 4738.9 | 3513.5 | 2073.3 | 3070.5 | 2646 | 1308.5 | 1188.1 | 661.2 | 426.5 | 221.8 | 174.1 | 134.9 | 154.7 | 39
Man-day - Saudi |  |  | 25 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 1.8462 | 68.16 | 79.4074 | 64.4 | 109.8148 | 147.6154 | 121.5417 | 84.5556 | 63.5385 | 34.3462 | 38.7308 | 37.7407 | 81.5 | 158.1154 | 231.4615 | 172.1154 | 174.8519 | 254.8077 | 330.875 | 250.2222 | 193.0769 | 158.8462 | 98.0769 | 5.9583
Averaga by month
Man-day - Plan | 0 | 0.18462 | 6.816 | 7.9407 | 6.44 | 10.9815 | 14.7615 | 12.1542 | 8.4556 | 6.3538 | 3.4346 | 3.8731 | 3.7741 | 8.15 | 15.8115 | 23.1462 | 17.2115 | 17.4852 | 25.4808 | 33.0875 | 25.0222 | 19.3077 | 15.8846 | 9.8077 | 0.59583 | 0 | 0 | 0
Man-day - Cu Plan | 0 | 0.18462 | 7.008 | 14.4296 | 22.024 | 31.3741 | 47.3423 | 63.4417 | 64.8481 | 73.6962 | 77.1308 | 81.0038 | 81.7778 | 93.0731 | 108.8846 | 132.0308 | 149.2423 | 161.2 | 192.8808 | 242.0417 | 240.1704 | 268.7154 | 284.6 | 294.4077 | 319.5375 | 0 | 0 | 0
Man-day - Actual | 0.93333 | 5 | 5.04 | 31.8074 | 38.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Man-day - Cu. Act | 0.93333 | 5.1077 | 16.076 | 46.6926 | 88.648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Man-day - Remai. | 0 | 0 | 0 | 0 | 24.784 | 38.4444 | 36.0038 | 87.3458 | 81.4 | 97.4077 | 111.5038 | 119.6885 | 151.0185 | 152.1077 | 182.2654 | 135.1346 | 79.7423 | 113.7222 | 101.7692 | 54.5208 | 44.0037 | 25.4308 | 16.4038 | 8.5308 | 7.2542 | 5.1885 | 5.95 | 1.5
Man-day - Saudi | 0 | 0 | 1 | 0.77778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Equipment Calculation
Work day in Months |  |  |  | 15 | 25 | 27 | 26 | 24 | 27 | 26 | 26 | 26 | 27 | 26 | 26 | 26 | 26 | 27 | 26 | 24 | 27 | 26 | 26 | 26 | 24 | 26 | 26 | 26
Plan |  | 28 | 808 | 680 | 491 | 1120 | 1459 | 985 | 585 | 579 | 424 | 414 | 343 | 951 | 1836 | 1666 | 948 | 1331 | 2168 | 2485 | 1956 | 1359 | 1242 | 903 | 94
Cu Plan |  | 28 | 836 | 1516 | 2007 | 3127 | 4586 | 5571 | 6156 | 6735 | 7159 | 7573 | 7916 | 8867 | 10703 | 12369 | 13317 | 14648 | 16816 | 19301 | 21257 | 22616 | 23858 | 24761 | 24855
Actual | 2024-09-30: 20; 2024-10-31: 1268; 2024-11-30: 621
Cu. Act | 2024-09-30: 20; 2024-10-31: 1288; 2024-11-30: 1909
Remai. |  |  |  | 83 | 569 | 1009 | 1644 | 2794 | 1954 | 2846 | 3540 | 4676 | 5400 | 5084 | 3791 | 5797 | 2901 | 820 | 1103 | 663 | 503 | 75 | 6 | 5 | 2 | 0.11
| 0 | 2.8 | 80.8 | 68 | 49.1 | 112 | 145.9 | 98.5 | 58.5 | 57.9 | 42.4 | 41.4 | 34.3 | 95.1 | 183.6 | 166.6 | 94.8 | 133.1 | 216.8 | 248.5 | 195.6 | 135.9 | 124.2 | 90.3 | 9.4
| 0 | 2.8 | 83.6 | 151.6 | 200.7 | 312.7 | 458.6 | 557.1 | 615.6 | 673.5 | 715.9 | 757.3 | 791.6 | 886.7 | 1070.3 | 1236.9 | 1331.7 | 1464.8 | 1681.6 | 1930.1 | 2125.7 | 2261.6 | 2385.8 | 2476.1 | 2485.5
|  |  |  | 45.3333 | 19.64 | 41.4815 | 56.1154 | 41.0417 | 21.6667 | 22.2692 | 16.3077 | 15.9231 | 12.7037 | 36.5769 | 70.6154 | 64.0769 | 36.4615 | 49.2963 | 83.3846 | 103.5417 | 72.4444 | 52.2692 | 47.7692 | 34.7308 | 3.9167 | 0
|  |  |  | 101.0667 | 80.28 | 115.8148 | 176.3846 | 232.125 | 228 | 259.0385 | 275.3462 | 291.2692 | 293.1852 | 341.0385 | 411.6538 | 475.7308 | 512.1923 | 542.5185 | 646.7692 | 804.2083 | 787.2963 | 869.8462 | 917.6154 | 952.3462 | 1035.625 | 0
|  |  | 2 | 84.5333 | 24.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 2 | 85.8667 | 76.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 5.5333 | 22.76 | 37.3704 | 63.2308 | 116.4167 | 72.3704 | 109.4615 | 136.1538 | 179.8462 | 200 | 195.5385 | 145.8077 | 222.9615 | 111.5769 | 30.3704 | 42.4231 | 27.625 | 18.6296 | 2.8846 | 0.23077 | 0.19231 | 0.083333 | 0.0042308
Activity ID | Activity Name | Resource ID Name | Start | Finish | Spreadsheet Field | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01
Modon |  |  | 28-Sep-24 A | 2027-05-03 | Budgeted Units | 48 | 1575 | 1663 | 1363 | 2271 | 1865 | 1515 | 848 | 563 | 387 | 467 | 555 | 1539 | 2780 | 3980 | 3188 | 3483 | 4756 | 5510 | 3949 | 1702 | 1644 | 1688 | 1589 | 3797 | 5243 | 4311 | 3930 | 4024 | 2885 | 1368 | 1346 | 837 | 15
Modon |  |  | 28-Sep-24 A | 2027-05-03 | Cum Budgeted Units | 48 | 1623 | 3286 | 4649 | 6920 | 8785 | 10300 | 11149 | 11711 | 12098 | 12566 | 13121 | 14660 | 17440 | 21420 | 24608 | 28092 | 32848 | 38357 | 42306 | 44008 | 45652 | 47341 | 48930 | 52727 | 57970 | 62281 | 66211 | 70235 | 73120 | 74488 | 75834 | 76671 | 76686
Unskilled Labor |  | MD-JDH3-LR-01.Unskilled Labor | 28-Oct-24 A | 2027-05-03 | Budgeted Units | 17 | 663 | 742 | 575 | 991 | 803 | 671 | 295 | 213 | 104 | 107 | 227 | 502 | 1026 | 1950 | 1468 | 1552 | 1372 | 2128 | 1630 | 762 | 784 | 736 | 668 | 1687 | 2397 | 2102 | 1900 | 1936 | 1490 | 704 | 646 | 396 | 3
Unskilled Labor |  | MD-JDH3-LR-01.Unskilled Labor | 28-Oct-24 A | 2027-05-03 | Cum Budgeted Units | 17 | 680 | 1422 | 1997 | 2988 | 3791 | 4462 | 4757 | 4969 | 5074 | 5181 | 5408 | 5910 | 6936 | 8886 | 10355 | 11907 | 13279 | 15407 | 17037 | 17799 | 18583 | 19320 | 19988 | 21674 | 24071 | 26173 | 28074 | 30010 | 31500 | 32204 | 32851 | 33246 | 33249
Electrician |  | MD-JDH3-LR-02.Electrician | 19-Jul-25 A | 2027-04-24 | Budgeted Units | 2025-04-01: 1; 2025-10-01: 20; 2025-11-01: 18; 2025-12-01: 10; 2026-01-01: 74; 2026-02-01: 47; 2026-03-01: 28; 2026-09-01: 2; 2026-12-01: 194; 2027-01-01: 86; 2027-02-01: 45; 2027-03-01: 18; 2027-04-01: 53
Electrician |  | MD-JDH3-LR-02.Electrician | 19-Jul-25 A | 2027-04-24 | Cum Budgeted Units | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 21 | 39 | 50 | 124 | 171 | 199 | 199 | 199 | 199 | 199 | 199 | 201 | 201 | 201 | 395 | 481 | 525 | 543 | 596 | 596
Equipment Opreator |  | MD-JDH3-LR-04.Equipment Opreator | 28-Sep-24 A | 2027-05-03 | Budgeted Units | 28 | 762 | 533 | 452 | 932 | 737 | 529 | 268 | 195 | 229 | 302 | 234 | 863 | 1296 | 1131 | 931 | 1174 | 1740 | 1766 | 1099 | 538 | 660 | 382 | 363 | 1081 | 1569 | 1114 | 1046 | 1110 | 746 | 409 | 335 | 286 | 13
Equipment Opreator |  | MD-JDH3-LR-04.Equipment Opreator | 28-Sep-24 A | 2027-05-03 | Cum Budgeted Units | 28 | 790 | 1323 | 1775 | 2707 | 3444 | 3973 | 4241 | 4436 | 4665 | 4967 | 5201 | 6065 | 7361 | 8492 | 9423 | 10597 | 12337 | 14103 | 15202 | 15740 | 16401 | 16782 | 17146 | 18226 | 19795 | 20909 | 21956 | 23066 | 23812 | 24220 | 24555 | 24842 | 24854
Mason |  | MD-JDH3-LR-03.Mason | 28-Oct-24 A | 2027-03-18 | Budgeted Units |  |  | 124 | 56 | 46 | 113 | 29 | 39 | 33 | 24 | 39 | 84 | 99 | 122 | 322 | 144 | 58 | 16 | 55 | 174 | 36 | 2 | 25 | 38 | 53 | 115 | 85 | 61 | 43 | 62 | 46 | 36
Mason |  | MD-JDH3-LR-03.Mason | 28-Oct-24 A | 2027-03-18 | Cum Budgeted Units |  |  | 124 | 180 | 226 | 339 | 368 | 407 | 440 | 464 | 503 | 587 | 686 | 808 | 1130 | 1274 | 1331 | 1348 | 1402 | 1576 | 1612 | 1614 | 1639 | 1677 | 1730 | 1845 | 1930 | 1991 | 2034 | 2095 | 2142 | 2178 | 2178 | 2178
Carpenter |  | MD-JDH3-LR-05.Carpenter | 03-Dec-24 A | 2027-04-14 | Budgeted Units |  | 29 | 109 | 101 | 64 | 59 | 101 | 106 | 48 | 4 |  |  | 9 | 90 | 147 | 187 | 210 | 628 | 565 | 403 | 148 | 22 | 244 | 208 | 366 | 407 | 359 | 302 | 167 | 112 | 9 | 96 | 3
Carpenter |  | MD-JDH3-LR-05.Carpenter | 03-Dec-24 A | 2027-04-14 | Cum Budgeted Units |  | 29 | 138 | 239 | 303 | 361 | 463 | 568 | 616 | 620 | 620 | 620 | 629 | 719 | 867 | 1054 | 1264 | 1892 | 2457 | 2860 | 3007 | 3030 | 3274 | 3482 | 3848 | 4256 | 4614 | 4916 | 5084 | 5195 | 5205 | 5300 | 5303 | 5303
Steel Fixer |  | MD-JDH3-LR-06.Steel Fixer | 11-Dec-24 A | 2027-03-29 | Budgeted Units |  |  | 94 | 97 | 35 | 46 | 77 | 105 | 46 |  |  |  |  | 76 | 125 | 183 | 170 | 623 | 529 | 388 | 147 | 4 | 234 | 205 | 342 | 376 | 307 | 262 | 133 | 98 |  | 92
Steel Fixer |  | MD-JDH3-LR-06.Steel Fixer | 11-Dec-24 A | 2027-03-29 | Cum Budgeted Units |  |  | 94 | 191 | 226 | 273 | 350 | 454 | 501 | 501 | 501 | 501 | 501 | 577 | 702 | 885 | 1054 | 1678 | 2207 | 2595 | 2742 | 2745 | 2980 | 3185 | 3527 | 3902 | 4209 | 4471 | 4604 | 4703 | 4703 | 4794 | 4794 | 4794
Skilled labor |  | MD-JDH3-LR-07.Skilled labor | 28-Sep-24 A | 2027-04-24 | Budgeted Units | 1 | 20 | 14 | 29 | 50 | 20 | 23 | 10 | 14 | 16 | 10 | 10 | 21 | 52 | 114 | 82 | 119 | 204 | 287 | 108 | 7 | 20 | 8 | 19 | 50 | 63 | 68 | 59 | 189 | 105 | 33 | 13 | 47
Skilled labor |  | MD-JDH3-LR-07.Skilled labor | 28-Sep-24 A | 2027-04-24 | Cum Budgeted Units | 1 | 21 | 35 | 64 | 114 | 134 | 157 | 167 | 181 | 197 | 207 | 217 | 238 | 289 | 403 | 485 | 604 | 808 | 1095 | 1203 | 1210 | 1230 | 1239 | 1258 | 1307 | 1371 | 1439 | 1498 | 1687 | 1792 | 1825 | 1838 | 1885 | 1885
Plumber |  | MD-JDH3-LR-08.Plumber | 01-Dec-24 A | 2027-04-25 | Budgeted Units | 2 | 101 | 46 | 54 | 154 | 86 | 85 | 26 | 12 | 9 | 10 |  | 46 | 117 | 171 | 175 | 191 | 97 | 133 | 119 | 64 | 152 | 58 | 87 | 219 | 315 | 277 | 298 | 252 | 187 | 121 | 111 | 51
Plumber |  | MD-JDH3-LR-08.Plumber | 01-Dec-24 A | 2027-04-25 | Cum Budgeted Units | 2 | 103 | 149 | 203 | 357 | 443 | 528 | 554 | 566 | 576 | 585 | 585 | 631 | 749 | 919 | 1095 | 1285 | 1383 | 1516 | 1635 | 1698 | 1850 | 1908 | 1996 | 2215 | 2530 | 2807 | 3104 | 3356 | 3543 | 3664 | 3775 | 3826 | 3826

## Milestones
Project Name
Item No. | Milestones | Original (Baseline) | Reivised | Forecast |  | Days Change
| Contract Duration Current Contract Weeks : 115 of 103 | 103.4286 | 103 | 103 |  | 0 | 114.8571 | 103
1 | Award Date | 2024-06-26 | 2024-06-26 | 2024-06-26 | A | 0
2 | Contract Sign Date | 2024-07-22 | 2024-07-22 | 2024-07-22 | A | 0
3 | Site Handover Date | 2024-07-29 | 2024-07-29 | 2024-07-29 | A | 0
4 | Complete Mobilization | 2024-09-03 | 2024-09-03 | 2024-10-26 | A | 0
5 | Complete existing condition survey, submission of Final Reports | 2025-09-07 | 2025-07-23 | 2025-07-23 | A | 0
6 | Complete Earthworks | 2026-07-07 | 2026-07-05 | 2026-07-02 | F | 3
7 | Complete steel structure errection for all blocks | 2026-07-02 | 2026-04-05 | 2026-02-25 | F | 39
8 | Complete all Civil Works | 2026-07-07 | 2026-07-05 | 2026-07-02 | F | 3
9 | Complete Mechanical Works | 2025-10-01 | 2026-07-05 | 2026-06-27 | F | 8
10 | Complete all Works including Testing & Commissioning, Cleanup, Closeout Documentation and Ready for Initial Handover | 2026-07-28 | 2026-07-28 | 2026-07-28 | F | 0
11 | Complete Demobilization | 2026-07-23 | 2026-07-20 | 2026-07-20 | F | 0

## Schedule
Primavera P6 Schedule Status | [11 empty] | Data Date | 11-10-2026
Project Activities Overview | [9 empty] | # Activities | 9236
Schedule Statistics |  |  |  |  | Active Schedule Activities |  |  |  |  | # Not Started | 141
Total Act. | Not Started | In Progress | Completed | % | Active | Ahead | On | Behind | Flag | # In Progress | 75
9236 | 141 | 75 | 9020 | 97.66% | 75 | 9020 | 75 | 66 | 9029 | # Completed | 9020
Critical Path Activities |  |  | Free Float Management (Total) |  |  |  | Failed Start Activities
|  |  | Greater Than 14 Days |  | Less Than 14 Days | [6 empty] | # Activities | 9236
Last Week | This Week | Diff | Last Week | This Week | Last Week | This Week | Last Week | This Week | Flag |  |  |  | # Not Started | 141
215 | 216 | -1 | 240 | 267 | 2934 | 2812 | 366 | 324 | 42 |  |  |  | # In Progress | 75
[13 empty] | # Completed | 9020
[13 empty] | # Relationships | 14995
66
| Activity ID | Activity Name | Activity Count | BL Project Start | BL Project Finish | Actual Start | Actual Finish
| Completion of the Infrastructure development of the 1st phase in the 3rd industrial city in Jeddah |  | 4879 | 2024-08-20 | 2026-07-28 | 2025-03-12 |  | FALSE | FALSE
| A1000 | Start of Sewage network Z02 - 1 MI - SS | 1 | 2024-12-05 |  |  |  | FALSE | yes
| A1010 | Finish of Sewage network Z02 - 1 MI - SS | 1 |  | 2025-03-25 |  |  | yes | FALSE
| A1030 | Finish of Sewage network Z02 - 2 MI - SS | 1 |  | 2025-01-14 |  |  | yes | FALSE
| A1040 | Start of Sewage network Z07 - 1 MI - SS | 1 | 2024-12-07 |  |  |  | FALSE | yes
| A1050 | Finish of Sewage network Z07 - 1 MI - SS | 1 |  | 2024-12-07 |  |  | yes | FALSE
| A1070 | Finish of Sewage network MR MI - SS | 1 |  | 2026-01-12 |  |  | yes | FALSE
| A1090 | Finish of Storm Network Z01 MI - ST | 1 |  | 2026-06-06 |  |  | yes | FALSE
| A1100 | Start of Storm Network Z02 - 1 MI - ST | 1 | 2024-11-24 |  |  |  | FALSE | yes
| A1110 | Finish of Storm Network Z02 - 1 MI - ST | 1 |  | 2025-05-11 |  |  | yes | FALSE
| A1130 | Finish of Storm Network Z02 - 2 MI - ST | 1 |  | 2025-03-12 |  |  | yes | FALSE
| A1140 | Start of Storm Network Z06 MI - ST | 1 | 2025-08-02 |  |  |  | FALSE | yes
| A1150 | Finish of Storm Network Z06 MI - ST | 1 |  | 2026-03-11 |  |  | yes | FALSE
| A1170 | Finish of Storm Network Z07 MI - ST | 1 |  | 2026-01-08 |  |  | yes | FALSE
| A1180 | Start of Storm Network Z07 - 1 MI - ST | 1 | 2024-12-07 |  |  |  | FALSE | yes
| A1190 | Finish of Storm Network Z07 - 1 MI - ST | 1 |  | 2024-12-26 |  |  | yes | FALSE
| A1210 | Finish of Storm Network MR MI - ST | 1 |  | 2026-06-15 |  |  | yes | FALSE
| A1230 | Finish of TSE Network Z01 MI - TSE | 1 |  | 2026-07-05 |  |  | yes | FALSE
| A1250 | Finish of TSE Network Z02 MI - TSE | 1 |  | 2025-10-16 |  |  | yes | FALSE
| A1270 | Finish of TSE Network Z02 - 1 MI - TSE | 1 |  | 2025-05-11 |  |  | yes | FALSE
| A1290 | Finish of TSE Network Z02 - 2 MI - TSE | 1 |  | 2025-01-20 |  |  | yes | FALSE
| A1310 | Finish of TSE Network Z03 MI - TSE | 1 |  | 2026-01-05 |  |  | yes | FALSE
| A1320 | Start of TSE Network Z04 MI - TSE | 1 | 2026-04-15 |  |  |  | FALSE | yes
| A1330 | Finish of TSE Network Z04 MI - TSE | 1 |  | 2026-06-17 |  |  | yes | FALSE
| A1350 | Finish of TSE Network Z05 MI - TSE | 1 |  | 2025-10-27 |  |  | yes | FALSE
| A1360 | Start of TSE Network Z06 MI - TSE | 1 | 2025-08-02 |  |  |  | FALSE | yes
| A1370 | Finish of TSE Network Z06 MI - TSE | 1 |  | 2026-03-10 |  |  | yes | FALSE
| A1390 | Finish of TSE Network Z07 MI - TSE | 1 |  | 2026-01-26 |  |  | yes | FALSE
| A1400 | Start of TSE Network Z07 - 1 MI - TSE | 1 | 2024-12-22 |  |  |  | FALSE | yes
| A1410 | Finish of TSE Network Z07 - 1 MI - TSE | 1 |  | 2024-12-22 |  |  | yes | FALSE
| A1430 | Finish of TSE Network Z08 MI - TSE | 1 |  | 2026-03-22 |  |  | yes | FALSE
| A1450 | Finish of TSE Network MR MI - TSE | 1 |  | 2026-07-04 |  |  | yes | FALSE
| A1460 | Start of PT - WT network Z02 - 1 MI - WT | 1 | 2024-12-07 |  |  |  | FALSE | yes
| A1470 | Finish of PT - WT Network Z02 - 1 MI - WT | 1 |  | 2025-03-25 |  |  | yes | FALSE
| A1490 | Finish of PT - WT Network Z02 - 2 MI - WT | 1 |  | 2025-02-23 |  |  | yes | FALSE
| A1500 | Start of PT - WT network Z07 - 1 MI - WT | 1 | 2024-11-02 |  |  |  | FALSE | yes
| A1510 | Finish of PT - WT Network Z07 - 1 MI - WT | 1 |  | 2025-02-23 |  |  | yes | FALSE
| A1530 | Finish of PT - WT Network Z07 MI - WT | 1 |  | 2026-01-28 |  |  | yes | FALSE
| A1540 | Start of PT - WT network Z06 MI - WT | 1 | 2025-08-02 |  |  |  | FALSE | yes
| A1550 | Finish of PT - WT Network Z06 MI - WT | 1 |  | 2026-04-14 |  |  | yes | FALSE
| A1590 | Finish of PT - WT Network MR MI - WT | 1 |  | 2026-07-05 |  |  | yes | FALSE
| A1670 | Finish of ELECTRICAL Network Z02 - 2 MI - EL - SL - TC | 1 |  | 2025-05-18 |  |  | yes | FALSE
| A1810 | Finish of Road Network Z02 - 2 MI - RD | 1 |  | 2025-06-14 |  |  | yes | FALSE
| A1840 | Start of Storm Network Z04 MI - ST | 1 | 2026-04-15 |  |  |  | FALSE | yes
| A1850 | Finish of Storm Network Z04 MI - ST | 1 |  | 2026-05-07 |  |  | yes | FALSE
| A1870 | Finish Storm Network Z05 MI - ST | 1 |  | 2025-11-19 |  |  | yes | FALSE
| A1990 | Finish of Road Network Z11 MI - RD | 1 |  | 2026-03-11 |  |  | yes | FALSE
| A2100 | Demobilize Manpower | 1 | 2026-07-15 | 2026-07-18 |  |  | FALSE | yes
| A2110 | Removal Equipments from The site | 1 | 2026-07-15 | 2026-07-19 |  |  | FALSE | yes
| A2120 | Site Clean Up | 1 | 2026-07-15 | 2026-07-19 |  |  | FALSE | yes
| A2130 | Removal of Site Offices and Structures | 1 | 2026-07-15 | 2026-07-20 |  |  | FALSE | yes
| A3290 | Restoration of Ground Surface | 1 | 2026-07-15 | 2026-07-20 |  |  | FALSE | yes
| A3300 | Warranties and Guarantess | 1 | 2026-07-15 | 2026-07-22 |  |  | FALSE | yes
| A3310 | Supply Operational Spares | 1 | 2026-07-09 | 2026-07-14 |  |  | FALSE | yes
| A3320 | Training | 1 | 2026-07-15 | 2026-07-22 |  |  | FALSE | yes
| A3330 | Manual | 1 | 2026-07-15 | 2026-07-22 |  |  | FALSE | yes
| A3390 | Finish of Electrical Network HM MI - EL | 1 |  | 2026-04-01 |  |  | yes | FALSE
| A3410 | Finish of PONDS - PS | 1 |  | 2026-03-17 |  |  | yes | FALSE
| A3450 | Finish of PT - WT Network Z01 MI - WT | 1 |  | 2026-06-22 |  |  | yes | FALSE
| A3520 | Finish of Storm Network Z08 MI - ST | 1 |  | 2026-03-15 |  |  | yes | FALSE
| A3540 | Finish of Storm Network Z11 MI - ST | 1 |  | 2026-03-02 |  |  | yes | FALSE
| A3560 | Finish of Storm Network Z12 MI - ST | 1 |  | 2026-02-14 |  |  | yes | FALSE
| A3610 | Finish of Storm Network Z13 MI - ST | 1 |  | 2026-06-25 |  |  | yes | FALSE
| A3620 | Finish of ELECTRICAL Network MR MI - EL - SL - TC | 1 |  | 2026-07-08 |  |  | yes | FALSE
| A3630 | Finish of Road Network MR MI - RD | 1 |  | 2026-07-09 |  |  | yes | FALSE
| A3660 | Finish of Storm Network Z02 MI - ST | 1 |  | 2025-11-02 |  |  | yes | FALSE
| A3680 | Finish of ELECTRICAL Network Z02 - 1 MI - EL - SL - TC | 1 |  | 2025-05-11 |  |  | yes | FALSE
| A3690 | Start of ELECTRICAL Network Z02 - 1 MI - EL - SL - TC | 1 | 2025-03-26 |  |  |  | FALSE | yes
| A3700 | Finish of ELECTRICAL Network Z07 - 1 MI - EL - SL - TC | 1 |  | 2025-01-28 |  |  | yes | FALSE
| A3710 | Start of ELECTRICAL Network Z07 - 1 MI - EL - SL - TC | 1 | 2024-12-29 |  |  |  | FALSE | yes
| A3722 | Finish Approval of all asbuilt dwg - MI | 1 |  |  |  |  | yes | FALSE
| A3730 | Finish All works of Testing And Commissioning - MI | 1 |  | 2026-07-13 |  |  | yes | FALSE
| A3740 | Finish of PT - WT Network Z13 MI - WT | 1 |  | 2026-06-24 |  |  | yes | FALSE
| A3750 | Finish of TSE Network Z13 MI - TSE | 1 |  | 2026-06-13 |  |  | yes | FALSE
| A3770 | Start of TSE Network Z13 MI - TSE | 1 | 2026-02-28 |  |  |  | FALSE | yes
| A3820 | Start of Sewage network MR MI - SS | 1 | 2026-03-16 |  |  |  | FALSE | yes
| A3830 | Finish of Sewage network MR MI - SS | 1 |  | 2026-07-08 |  |  | yes | FALSE
| A3840 | Start of Sewage network Z10 MI - SS | 1 | 2026-03-21 |  |  |  | FALSE | yes
| A3850 | Finish of Sewage network Z10 MI - SS | 1 |  | 2026-06-28 |  |  | yes | FALSE
| JD3RCJDH2CCTV02 | Poles civil work - JDH2 - CCTV | 1 | 2025-10-16 | 2025-11-08 | 2025-10-16 |  | yes | FALSE
| JD3RCJDH2CCTV03 | Poles installation - JDH2 - CCTV | 1 | 2025-12-27 | 2026-01-29 |  |  | FALSE | yes
| JD3RCJDH2CCTV04 | Electrical work - JDH2 - CCTV | 1 | 2025-10-28 | 2025-12-10 |  |  | FALSE | yes
| JD3RCJDH2CCTV05 | Passive work - JDH2 - CCTV | 1 | 2026-01-31 | 2026-02-28 |  |  | FALSE | yes
| JD3RCJDH2CCTV06 | Active devices installation - JDH2 - CCTV | 1 | 2026-03-01 | 2026-03-30 |  |  | FALSE | yes
| JD3RCJDH2CCTV07 | Control room preparation - JDH2 - CCTV | 1 | 2025-10-28 | 2025-12-07 |  |  | FALSE | yes
| JD3RCJDH2CCTV08 | Configuration - JDH2 - CCTV | 1 | 2026-03-31 | 2026-04-16 |  |  | FALSE | yes
| JD3RCJDH3CCTV03 | Poles installation - JDH3 - CCTV | 1 | 2025-12-27 | 2026-01-29 | 2025-10-30 |  | FALSE | yes
| JD3RCJDH3CCTV04 | Electrical work - JDH3 - CCTV | 1 | 2025-10-28 | 2025-12-10 |  |  | FALSE | yes
| JD3RCJDH3CCTV05 | Passive work - JDH3 - CCTV | 1 | 2026-01-31 | 2026-02-28 |  |  | FALSE | yes
| JD3RCJDH3CCTV06 | Active devices installation - JDH3 - CCTV | 1 | 2026-03-01 | 2026-03-30 |  |  | FALSE | yes
| JD3RCJDH3CCTV07 | Control room preparation - JDH3 - CCTV | 1 | 2025-10-28 | 2025-12-07 |  |  | FALSE | yes
| JD3RCJDH3CCTV08 | Configuration - JDH3 - CCTV | 1 | 2026-03-31 | 2026-04-16 |  |  | FALSE | yes
| JD3RH&MSL20010 | INSTALLING for single core PVC insulated copper conductor cables - NB2.26 05 19.09 - size 70 mm² - H&M - H&M - SL | 1 | 2026-01-06 | 2026-01-11 |  |  | FALSE | yes
| JD3RH&MSL20011 | Termination for single core PVC insulated copper conductor cables - NB2.26 05 19.09 - size 70 mm² - H&M - H&M - SL | 1 | 2026-01-12 | 2026-01-17 |  |  | FALSE | yes
| JD3RH&MSL20012 | INSTALLING for Stranded armored Cables, Copper - NB2.26 05 19.10 - 4Cx150 mm² XLPE /PVC/SWA - H&M - H&M - SL | 1 | 2026-01-12 | 2026-01-17 |  |  | FALSE | yes
| JD3RH&MSL20013 | Termination for Stranded armored Cables, Copper - NB2.26 05 19.10 - 4Cx150 mm² XLPE /PVC/SWA - H&M - H&M - SL | 1 | 2026-01-18 | 2026-01-22 |  |  | FALSE | yes
| JD3RH&MSL20015 | Termination for Light fixtures LED 342 wats including cables - NB2.26 05 19.11 - H&M - H&M - SL | 1 | 2026-01-20 | 2026-01-21 | 2025-09-19 |  | FALSE | yes
| JD3RH&MSL20016 | Excavation Works for Copper Cables - B2.26 05 19.02 - 4Cx10 mm² - H&M - H&M - SL | 1 | 2026-01-06 | 2026-01-10 |  |  | FALSE | yes
| JD3RH&MSL20017 | Installation for Copper Cables - B2.26 05 19.02 - 4Cx10 mm² - H&M - H&M - SL | 1 | 2026-01-11 | 2026-01-14 |  |  | FALSE | yes
| JD3RH&MSL20018 | Backfilling, Warning Tabe Works for Copper Cables - B2.26 05 19.02 - 4Cx10 mm² - H&M - H&M - SL | 1 | 2026-01-15 | 2026-01-19 |  |  | FALSE | yes
| JD3RH&MSL20019 | Testing and Commitioning for Copper Cables - B2.26 05 19.02 - 4Cx10 mm² - H&M - H&M - SL | 1 | 2026-01-20 | 2026-01-24 |  |  | FALSE | yes
| JD3RH&MSL20020 | Excavation Works for Copper Cables - B2.26 05 19.04 - 4Cx25 mm² - H&M - H&M - SL | 1 | 2026-01-11 | 2026-01-17 | 2025-09-20 |  | FALSE | yes
| JD3RH&MSL20021 | Installation for Copper Cables - B2.26 05 19.04 - 4Cx25 mm² - H&M - H&M - SL | 1 | 2026-01-18 | 2026-01-24 | 2025-09-24 |  | FALSE | yes
| JD3RH&MSL20022 | Backfilling, Warning Tabe Works for Copper Cables - B2.26 05 19.04 - 4Cx25 mm² - H&M - H&M - SL | 1 | 2026-01-25 | 2026-01-31 | 2025-09-30 |  | FALSE | yes
| JD3RH&MSL20023 | Testing and Commitioning for Copper Cables - B2.26 05 19.04 - 4Cx25 mm² - H&M - H&M - SL | 1 | 2026-02-01 | 2026-02-07 |  |  | FALSE | yes
| JD3RH&MSL20024 | Excavation Works for Copper Cables - B2.26 05 19.05 - 4Cx35 mm² - H&M - H&M - SL | 1 | 2026-01-06 | 2026-01-25 | 2025-09-16 |  | FALSE | yes
| JD3RH&MSL20025 | Installation for Copper Cables - B2.26 05 19.05 - 4Cx35 mm² - H&M - H&M - SL | 1 | 2026-01-26 | 2026-02-14 | 2025-09-20 |  | FALSE | yes
| JD3RH&MSL20026 | Backfilling, Warning Tabe Works for Copper Cables - B2.26 05 19.05 - 4Cx35 mm² - H&M - H&M - SL | 1 | 2026-02-15 | 2026-03-05 | 2025-09-23 |  | FALSE | yes
| JD3RH&MSL20027 | Testing and Commitioning for Copper Cables - B2.26 05 19.05 - 4Cx35 mm² - H&M - H&M - SL | 1 | 2026-03-07 | 2026-03-25 | 2025-09-27 |  | FALSE | yes
| JD3RH&MSL20028 | Excavation Works for Copper Cables - B2.26 05 19.06 - 4Cx50 mm² - H&M - H&M - SL | 1 | 2026-01-06 | 2026-01-08 |  |  | FALSE | yes
| JD3RH&MSL20029 | Installation for Copper Cables - B2.26 05 19.06 - 4Cx50 mm² - H&M - H&M - SL | 1 | 2026-01-10 | 2026-01-12 |  |  | FALSE | yes
| JD3RH&MSL20030 | Backfilling, Warning Tabe Works for Copper Cables - B2.26 05 19.06 - 4Cx50 mm² - H&M - H&M - SL | 1 | 2026-01-13 | 2026-01-15 |  |  | FALSE | yes
| JD3RH&MSL20031 | Testing and Commitioning for Copper Cables - B2.26 05 19.06 - 4Cx50 mm² - H&M - H&M - SL | 1 | 2026-01-17 | 2026-01-19 |  |  | FALSE | yes
| JD3RH&MSL20032 | INSTALLING for insulated copper conductor - B2.26 05 19.07 - 6 mm² - H&M - H&M - SL | 1 | 2026-01-06 | 2026-01-07 |  |  | FALSE | yes
| JD3RH&MSL20033 | TESTING AND COMMITIONING for insulated copper conductor - B2.26 05 19.07 - 6 mm² - H&M - H&M - SL | 1 | 2026-01-08 | 2026-01-10 |  |  | FALSE | yes
| JD3RH&MSL20034 | INSTALLING for insulated copper conductor - B2.26 05 19.08 - 16 mm² - H&M - H&M - SL | 1 | 2026-01-06 | 2026-01-29 |  |  | FALSE | yes
| JD3RH&MSL20035 | TESTING AND COMMITIONING for insulated copper conductor - B2.26 05 19.08 - 16 mm² - H&M - H&M - SL | 1 | 2026-01-31 | 2026-02-23 |  |  | FALSE | yes
| JD3RH&MSL20036 | Excavation Works for PVC Pipes - B2.33 71 19.02 - 4×150mm - H&M - H&M - SL | 1 | 2026-02-24 | 2026-02-25 |  |  | FALSE | yes
| JD3RH&MSL20037 | Installation for PVC Pipes - B2.33 71 19.02 - 4×150mm - H&M - H&M - SL | 1 | 2026-02-26 | 2026-03-02 |  |  | FALSE | yes
| JD3RH&MSL20038 | Pouring Concrete Cover for PVC Pipes - B2.33 71 19.02 - 4×150mm - H&M - H&M - SL | 1 | 2026-03-03 | 2026-03-07 |  |  | FALSE | yes
| JD3RH&MSL20039 | Testing and Backfilling Works for PVC Pipes - B2.33 71 19.02 - 4×150mm - H&M - H&M - SL | 1 | 2026-03-08 | 2026-03-11 |  |  | FALSE | yes
| JD3RH&MSL20040 | Excavation Works for PVC Pipes - B2.33 71 19.03 - 6×150mm - H&M - H&M - SL | 1 | 2026-02-26 | 2026-02-28 |  |  | FALSE | yes
| JD3RH&MSL20041 | Installation for PVC Pipes - B2.33 71 19.03 - 6×150mm - H&M - H&M - SL | 1 | 2026-03-01 | 2026-03-02 |  |  | FALSE | yes
| JD3RH&MSL20042 | Pouring Concrete Cover for PVC Pipes - B2.33 71 19.03 - 6×150mm - H&M - H&M - SL | 1 | 2026-03-03 | 2026-03-04 |  |  | FALSE | yes
| JD3RH&MSL20043 | Testing and Backfilling Works for PVC Pipes - B2.33 71 19.03 - 6×150mm - H&M - H&M - SL | 1 | 2026-03-05 | 2026-03-07 |  |  | FALSE | yes
| JD3RH&MSL20044 | Excavation for Drawpit - B2.33 71 19.13.01 - 600x600x1000mm - H&M - H&M - SL | 1 | 2026-02-26 | 2026-03-08 | 2025-08-20 |  | FALSE | yes
| JD3RH&MSL20045 | Installation for Drawpit - B2.33 71 19.13.01 - 600x600x1000mm - H&M - H&M - SL | 1 | 2026-03-09 | 2026-03-21 | 2025-08-27 |  | FALSE | yes
| JD3RH&MSL20046 | Backfilling for Drawpit - B2.33 71 19.13.01 - 600x600x1000mm - H&M - H&M - SL | 1 | 2026-03-22 | 2026-03-31 | 2025-08-31 |  | FALSE | yes
| JD3RH&MSL20047 | Excavation for Street Lighting panels - B2.26 24 16.01 - H&M - H&M - SL | 1 | 2026-03-01 | 2026-03-02 |  |  | FALSE | yes
| JD3RH&MSL20048 | Installation for Street Lighting panels - B2.26 24 16.01 - H&M - H&M - SL | 1 | 2026-03-03 | 2026-03-04 |  |  | FALSE | yes
| JD3RH&MSL20049 | Backfilling for Street Lighting panels - B2.26 24 16.01 - H&M - H&M - SL | 1 | 2026-03-05 | 2026-03-07 |  |  | FALSE | yes
| JD3RH&MSL20050 | Excavation for KWH meter - B2.26 24 16.02 - H&M - H&M - SL | 1 | 2026-03-08 | 2026-03-09 |  |  | FALSE | yes
| JD3RH&MSL20051 | Installation for KWH meter - B2.26 24 16.02 - H&M - H&M - SL | 1 | 2026-03-10 | 2026-03-11 |  |  | FALSE | yes
| JD3RH&MSL20052 | Backfilling for KWH meter - B2.26 24 16.02 - H&M - H&M - SL | 1 | 2026-03-12 | 2026-03-14 |  |  | FALSE | yes
| JD3RH&MSL20053 | Excavation for KWH meter - NB2.26 24 16.02 - H&M - H&M - SL | 1 | 2026-03-15 | 2026-03-16 |  |  | FALSE | yes
| JD3RH&MSL20054 | Installation for KWH meter - NB2.26 24 16.02 - H&M - H&M - SL | 1 | 2026-03-17 | 2026-03-18 |  |  | FALSE | yes
| JD3RH&MSL20055 | Backfilling for KWH meter - NB2.26 24 16.02 - H&M - H&M - SL | 1 | 2026-03-19 | 2026-03-21 |  |  | FALSE | yes
| JD3RH&MSL20060 | Termination for Light fixtures LED 208 wats including cables - NB2.26 56 19.01 - H&M - H&M - SL | 1 | 2026-03-24 | 2026-03-25 |  |  | FALSE | yes
| JD3RH&MSL200601 | Excavation for Drawpit - B2.33 71 19.13.03 - H&M - H&M - SL | 1 | 2026-03-26 | 2026-03-28 |  |  | FALSE | yes
| JD3RH&MSL200602 | Installation for Drawpit - B2.33 71 19.13.03 - H&M - H&M - SL | 1 | 2026-03-29 | 2026-03-30 |  |  | FALSE | yes
| JD3RH&MSL200603 | Backfilling for Drawpit - B2.33 71 19.13.03 - H&M - H&M - SL | 1 | 2026-03-31 | 2026-04-01 |  |  | FALSE | yes
| JD3RMRC01ST100.R | Channel excavation for Swales - B6.31 22 00.13 - MR - C - 01 - ST - Remaining | 1 | 2024-09-26 | 2024-10-08 | 2025-08-02 |  | FALSE | FALSE
| JD3RMRC01ST300.R | Riprap with side slopes 1.5:1 for Swales - NB6.31 22 00.16 - MR - C - 01 - ST - Remaining | 1 | 2024-10-31 | 2024-11-17 | 2025-08-16 |  | FALSE | FALSE
| JD3RMRC01ST50996 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 01 - ST | 1 | 2024-11-23 | 2024-11-24 |  |  | FALSE | yes
| JD3RMRC01ST50997 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 01 - ST | 1 | 2024-11-25 | 2024-11-26 |  |  | FALSE | yes
| JD3RMRC01ST50998 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 01 - ST | 1 | 2024-11-27 | 2024-11-28 |  |  | FALSE | yes
| JD3RMRC01TSE51062 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 01 - TSE | 1 | 2024-12-02 | 2024-12-03 |  |  | FALSE | yes
| JD3RMRC01TSE51063 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 01 - TS | 1 | 2024-12-04 | 2024-12-05 |  |  | FALSE | yes
| JD3RMRC01TSE51064 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 01 - TSE | 1 | 2024-12-07 | 2024-12-08 |  |  | FALSE | yes
| JD3RMRC01TSE51065 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 01 - TSE | 1 | 2024-12-09 | 2024-12-10 |  |  | FALSE | yes
| JD3RMRC01TSE51066 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 01 - TSE | 1 | 2024-12-14 | 2024-12-15 |  |  | FALSE | yes
| JD3RMRC01TSE51187 | Installationfor gate valves 100 mm - B4.33 14 19.01 - MR - C - 01 - TSE | 1 | 2024-12-09 | 2024-12-10 |  |  | FALSE | yes
| JD3RMRC01TSE51188 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - MR - C - 01 - TSE | 1 | 2024-12-11 | 2024-12-12 |  |  | FALSE | yes
| JD3RMRC02ST100.R | Channel excavation for Swales - B6.31 22 00.13 - MR - C - 02 - ST - Remaining | 1 | 2024-12-25 | 2025-01-11 | 2025-08-06 |  | FALSE | FALSE
| JD3RMRC02ST300 | Riprap with side slopes 1.5:1 for Swales - NB6.31 22 00.16 - MR - C - 02 - ST | 1 | 2025-01-12 | 2025-01-28 | 2025-08-16 |  | FALSE | FALSE
| JD3RMRC02ST51709 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 02 - ST | 1 | 2025-02-05 | 2025-02-06 |  |  | FALSE | yes
| JD3RMRC02ST51710 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 02 - ST | 1 | 2025-02-08 | 2025-02-09 |  |  | FALSE | yes
| JD3RMRC02ST51711 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 02 - ST | 1 | 2025-02-10 | 2025-02-11 |  |  | FALSE | yes
| JD3RMRC02TSE51775 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 02 - TSE | 1 | 2025-02-12 | 2025-02-13 |  |  | FALSE | yes
| JD3RMRC02TSE51776 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 02 - TS | 1 | 2025-02-15 | 2025-02-16 |  |  | FALSE | yes
| JD3RMRC02TSE51777 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 02 - TSE | 1 | 2025-02-17 | 2025-02-18 |  |  | FALSE | yes
| JD3RMRC02TSE51778 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 02 - TSE | 1 | 2025-02-19 | 2025-02-20 |  |  | FALSE | yes
| JD3RMRC02TSE51779 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 02 - TSE | 1 | 2025-03-03 | 2025-03-04 |  |  | FALSE | yes
| JD3RMRC02TSE51780 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - C - 02 - TSE | 1 | 2025-02-12 | 2025-02-13 |  |  | FALSE | yes
| JD3RMRC02TSE51781 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - C - 02 - TS | 1 | 2025-02-15 | 2025-02-16 |  |  | FALSE | yes
| JD3RMRC02TSE51782 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - C - 02 - TSE | 1 | 2025-02-17 | 2025-02-18 |  |  | FALSE | yes
| JD3RMRC02TSE51783 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - C - 02 - TSE | 1 | 2025-02-19 | 2025-02-20 |  |  | FALSE | yes
| JD3RMRC02TSE51784 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - C - 02 - TSE | 1 | 2025-03-03 | 2025-03-04 |  |  | FALSE | yes
| JD3RMRC02TSE51815 | Excavation Worksfor HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 02 - TSE | 1 | 2025-02-12 | 2025-02-15 | 2025-08-11 |  | FALSE | FALSE
| JD3RMRC02TSE51816 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 02 - TSE | 1 | 2025-02-16 | 2025-02-18 | 2025-08-16 |  | FALSE | FALSE
| JD3RMRC02TSE51817 | Installing for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 02 - TSE | 1 | 2025-02-19 | 2025-02-25 | 2025-08-18 |  | FALSE | FALSE
| JD3RMRC02TSE51818 | Testing for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 02 - TSE | 1 | 2025-02-26 | 2025-03-02 | 2025-09-16 |  | FALSE | FALSE
| JD3RMRC02TSE51819 | Backfillingfor HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 02 - TSE | 1 | 2025-03-03 | 2025-03-06 | 2025-08-26 |  | FALSE | FALSE
| JD3RMRC02TSE51850 | Excavation Worksfor HDPE Pipes 630 mm - depth from 1.51 to 2.5 m - B4.33 31 00.16 - MR - C - 02 - TSE | 1 | 2025-02-12 | 2025-02-13 |  |  | FALSE | yes
| JD3RMRC02TSE51851 | Soil Replacement and Bedding Works for HDPE Pipes 630 mm - depth from 1.51 to 2.5 m - B4.33 31 00.16 - MR - C - 02 - TSE | 1 | 2025-02-15 | 2025-02-16 |  |  | FALSE | yes
| JD3RMRC02TSE51852 | Installing for HDPE Pipes 630 mm - depth from 1.51 to 2.5 m - B4.33 31 00.16 - MR - C - 02 - TSE | 1 | 2025-02-17 | 2025-02-18 |  |  | FALSE | yes
| JD3RMRC02TSE51853 | Testing for HDPE Pipes 630 mm - depth from 1.51 to 2.5 m - B4.33 31 00.16 - MR - C - 02 - TSE | 1 | 2025-02-19 | 2025-02-20 |  |  | FALSE | yes
| JD3RMRC02TSE51854 | Backfillingfor HDPE Pipes 630 mm - depth from 1.51 to 2.5 m - B4.33 31 00.16 - MR - C - 02 - TSE | 1 | 2025-03-03 | 2025-03-04 |  |  | FALSE | yes
| JD3RMRC02TSE51855 | Excavation Worksfor HDPE Pipes 630 mm - depth from 2.51 to 3.5 m - B4.33 31 00.17 - MR - C - 02 - TSE | 1 | 2025-02-12 | 2025-02-13 |  |  | FALSE | yes
| JD3RMRC02TSE51856 | Soil Replacement and Bedding Works for HDPE Pipes 630 mm - depth from 2.51 to 3.5 m - B4.33 31 00.17 - MR - C - 02 - TSE | 1 | 2025-02-15 | 2025-02-16 |  |  | FALSE | yes
| JD3RMRC02TSE51857 | Installing for HDPE Pipes 630 mm - depth from 2.51 to 3.5 m - B4.33 31 00.17 - MR - C - 02 - TSE | 1 | 2025-02-17 | 2025-02-18 |  |  | FALSE | yes
| JD3RMRC02TSE51858 | Testing for HDPE Pipes 630 mm - depth from 2.51 to 3.5 m - B4.33 31 00.17 - MR - C - 02 - TSE | 1 | 2025-02-19 | 2025-02-20 |  |  | FALSE | yes
| JD3RMRC02TSE51859 | Backfillingfor HDPE Pipes 630 mm - depth from 2.51 to 3.5 m - B4.33 31 00.17 - MR - C - 02 - TSE | 1 | 2025-03-03 | 2025-03-04 |  |  | FALSE | yes
| JD3RMRC02TSE51900 | Installationfor gate valves 100 mm - B4.33 14 19.01 - MR - C - 02 - TSE | 1 | 2025-02-26 | 2025-02-27 |  |  | FALSE | yes
| JD3RMRC02TSE51901 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - MR - C - 02 - TSE | 1 | 2025-03-01 | 2025-03-02 |  |  | FALSE | yes
| JD3RMRC02TSE51902 | Installationfor gate valves 250 mm - B4.33 14 19.02 - MR - C - 02 - TSE | 1 | 2025-02-26 | 2025-02-27 |  |  | FALSE | yes
| JD3RMRC02TSE51903 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - MR - C - 02 - TSE | 1 | 2025-03-01 | 2025-03-02 |  |  | FALSE | yes
| JD3RMRC02TSE51906 | Installationfor butterfly valves 400 mm. - B4.33 14 19.04 - MR - C - 02 - TSE | 1 | 2025-02-26 | 2025-02-27 |  |  | FALSE | yes
| JD3RMRC02TSE51907 | Testing And Commtionningfor butterfly valves 400 mm. - B4.33 14 19.04 - MR - C - 02 - TSE | 1 | 2025-03-01 | 2025-03-02 |  |  | FALSE | yes
| JD3RMRC02TSE51920 | Installationfor Air valves 65 mm. - on pipes with diameter 355 - 630 mm - B4.33 14 19.16 - MR - C - 02 - TSE | 1 | 2025-02-26 | 2025-02-27 |  |  | FALSE | yes
| JD3RMRC02TSE51921 | Testing And Commtionningfor Air valves 65 mm. - on pipes with diameter 355 - 630 mm - B4.33 14 19.16 - MR - C - 02 - TSE | 1 | 2025-03-01 | 2025-03-02 |  |  | FALSE | yes
| JD3RMRC02TSE51924 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - C - 02 - TSE | 1 | 2025-02-12 | 2025-02-13 |  |  | FALSE | yes
| JD3RMRC02TSE51925 | Plain Concrete Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - C - 02 - TSE | 1 | 2025-02-15 | 2025-02-16 |  |  | FALSE | yes
| JD3RMRC02TSE51926 | INSTALLATIONfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - C - 02 - TSE | 1 | 2025-02-17 | 2025-02-18 |  |  | FALSE | yes
| JD3RMRC02TSE51927 | Backfilling Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - C - 02 - TSE | 1 | 2025-02-19 | 2025-02-20 |  |  | FALSE | yes
| JD3RMRC02TSE51952 | EXCAVATION and Bedding Worksfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - C - 02 - TSE | 1 | 2025-02-12 | 2025-02-13 |  |  | FALSE | yes
| JD3RMRC02TSE51953 | Plain Concrete Worksfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - C - 02 - TSE | 1 | 2025-02-15 | 2025-02-16 |  |  | FALSE | yes
| JD3RMRC02TSE51954 | INSTALLATIONfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - C - 02 - TSE | 1 | 2025-02-17 | 2025-02-18 |  |  | FALSE | yes
| JD3RMRC02TSE51955 | Backfilling Worksfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - C - 02 - TSE | 1 | 2025-02-19 | 2025-02-20 |  |  | FALSE | yes
| JD3RMRC03SL52740 | Supply, construct, connect and test earthing pitsfor Street Lighting EARTHING SYSTEM - B2.26 05 26.01 - MR - C - 03 - SL | 1 | 2025-10-21 | 2025-10-22 |  |  | FALSE | yes
| JD3RMRC03ST100.R1 | Channel excavation for Swales - B6.31 22 00.13 - MR - C - 03 - ST - Remaining | 1 | 2025-07-03 | 2025-07-19 |  |  | FALSE | yes
| JD3RMRC03ST302.R | Riprap with side slopes 1.5:1 for Swales - NB6.31 22 00.16 - MR - C - 03 - ST | 1 | 2025-10-04 | 2025-10-21 |  |  | FALSE | yes
| JD3RMRC03ST52212 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - C - 03 - ST | 1 | 2025-06-02 | 2025-06-03 |  |  | FALSE | yes
| JD3RMRC03ST52213 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - C - 03 | 1 | 2025-06-04 | 2025-06-05 |  |  | FALSE | yes
| JD3RMRC03ST52214 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - C - 03 - ST | 1 | 2025-06-07 | 2025-06-08 |  |  | FALSE | yes
| JD3RMRC03ST52215 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - C - 03 - ST | 1 | 2025-06-09 | 2025-06-10 |  |  | FALSE | yes
| JD3RMRC03ST52216 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - C - 03 - ST | 1 | 2025-06-11 | 2025-06-12 |  |  | FALSE | yes
| JD3RMRC03ST52242 | Excavation Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - C - 03 - ST | 1 | 2025-06-02 | 2025-06-03 |  |  | FALSE | yes
| JD3RMRC03ST52243 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - C - 03 - | 1 | 2025-06-04 | 2025-06-05 |  |  | FALSE | yes
| JD3RMRC03ST52244 | Installing for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - C - 03 - ST | 1 | 2025-06-07 | 2025-06-08 |  |  | FALSE | yes
| JD3RMRC03ST52245 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - C - 03 - ST | 1 | 2025-06-09 | 2025-06-10 |  |  | FALSE | yes
| JD3RMRC03ST52246 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - C - 03 - ST | 1 | 2025-06-16 | 2025-06-17 |  |  | FALSE | yes
| JD3RMRC03ST52317 | Excavation Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 03 - ST | 1 | 2025-06-02 | 2025-06-03 |  |  | FALSE | yes
| JD3RMRC03ST52318 | Soil Replacement and Bedding Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 03 | 1 | 2025-06-04 | 2025-06-05 |  |  | FALSE | yes
| JD3RMRC03ST52319 | Installing for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 03 - ST | 1 | 2025-06-07 | 2025-06-08 |  |  | FALSE | yes
| JD3RMRC03ST52320 | Primary Test for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 03 - ST | 1 | 2025-06-09 | 2025-06-10 |  |  | FALSE | yes
| JD3RMRC03ST52321 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 03 - ST | 1 | 2025-06-16 | 2025-06-17 |  |  | FALSE | yes
| JD3RMRC03ST52327 | Excavation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 03 - ST | 1 | 2025-10-22 | 2025-10-26 |  |  | FALSE | yes
| JD3RMRC03ST52328 | Plain Concrete Works For Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 03 - ST | 1 | 2025-10-27 | 2025-10-28 |  |  | FALSE | yes
| JD3RMRC03ST52329 | Raft Foundation for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 03 - ST | 1 | 2025-10-29 | 2025-11-10 |  |  | FALSE | yes
| JD3RMRC03ST52330 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 03 - ST | 1 | 2025-11-11 | 2025-11-30 |  |  | FALSE | yes
| JD3RMRC03ST52331 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 03 - ST | 1 | 2025-12-01 | 2025-12-20 |  |  | FALSE | yes
| JD3RMRC03ST52332 | Isolation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 03 - ST | 1 | 2025-12-21 | 2025-12-27 |  |  | FALSE | yes
| JD3RMRC03ST52333 | Backfilling Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 03 - ST | 1 | 2025-12-28 | 2025-12-29 |  |  | FALSE | yes
| JD3RMRC03ST52355 | Excavation Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 03 - ST | 1 | 2025-10-27 | 2025-10-30 |  |  | FALSE | yes
| JD3RMRC03ST52356 | Plain Concrete Works For Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 03 - ST | 1 | 2025-11-01 | 2025-11-02 |  |  | FALSE | yes
| JD3RMRC03ST52357 | Raft Foundation for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 03 - ST | 1 | 2025-11-03 | 2025-11-16 |  |  | FALSE | yes
| JD3RMRC03ST52358 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.05 - MR - C - 03 - ST | 1 | 2025-11-17 | 2025-12-07 |  |  | FALSE | yes
| JD3RMRC03ST52359 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.05 - MR - C - 03 - ST | 1 | 2025-12-08 | 2025-12-28 |  |  | FALSE | yes
| JD3RMRC03ST52360 | Isolation Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 03 - ST | 1 | 2025-12-29 | 2026-01-04 |  |  | FALSE | yes
| JD3RMRC03ST52361 | Backfilling Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 03 - ST | 1 | 2026-01-05 | 2026-01-06 |  |  | FALSE | yes
| JD3RMRC03ST52362 | Excavation Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 03 - ST | 1 | 2025-11-01 | 2025-11-04 |  |  | FALSE | yes
| JD3RMRC03ST52363 | Plain Concrete Works For Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 03 - ST | 1 | 2025-11-05 | 2025-11-06 |  |  | FALSE | yes
| JD3RMRC03ST52364 | Raft Foundation for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 03 - ST | 1 | 2025-11-08 | 2025-11-20 |  |  | FALSE | yes
| JD3RMRC03ST52365 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 03 - ST | 1 | 2025-11-22 | 2025-12-11 |  |  | FALSE | yes
| JD3RMRC03ST52366 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 03 - ST | 1 | 2025-12-13 | 2026-01-01 |  |  | FALSE | yes
| JD3RMRC03ST52367 | Isolation Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 03 - ST | 1 | 2026-01-03 | 2026-01-08 |  |  | FALSE | yes
| JD3RMRC03ST52368 | Backfilling Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 03 - ST | 1 | 2026-01-10 | 2026-01-11 |  |  | FALSE | yes
| JD3RMRC03ST52405 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - C - 03 - ST | 1 | 2025-06-02 | 2025-06-03 |  |  | FALSE | yes
| JD3RMRC03ST52406 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - C - 03 - ST | 1 | 2025-06-04 | 2025-06-05 |  |  | FALSE | yes
| JD3RMRC03ST52407 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - C - 03 - ST | 1 | 2025-06-07 | 2025-06-08 |  |  | FALSE | yes
| JD3RMRC03ST52408 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - C - 03 - ST | 1 | 2025-06-09 | 2025-06-10 |  |  | FALSE | yes
| JD3RMRC03ST52409 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - C - 03 - ST | 1 | 2025-06-11 | 2025-06-12 |  |  | FALSE | yes
| JD3RMRC03ST52410 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 03 - ST | 1 | 2025-06-02 | 2025-06-03 |  |  | FALSE | yes
| JD3RMRC03ST52411 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 03 - ST | 1 | 2025-06-04 | 2025-06-05 |  |  | FALSE | yes
| JD3RMRC03ST52412 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 03 - ST | 1 | 2025-06-07 | 2025-06-08 |  |  | FALSE | yes
| JD3RMRC03ST52413 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 03 - ST | 1 | 2025-06-09 | 2025-06-10 |  |  | FALSE | yes
| JD3RMRC03ST52414 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 03 - ST | 1 | 2025-06-11 | 2025-06-12 |  |  | FALSE | yes
| JD3RMRC03ST52420 | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 03 - ST | 1 | 2025-06-02 | 2025-06-03 |  |  | FALSE | yes
| JD3RMRC03ST52421 | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 03 - ST | 1 | 2025-06-04 | 2025-06-05 |  |  | FALSE | yes
| JD3RMRC03ST52422 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 03 - ST | 1 | 2025-06-07 | 2025-06-08 |  |  | FALSE | yes
| JD3RMRC03ST52423 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 03 - ST | 1 | 2025-06-09 | 2025-06-10 |  |  | FALSE | yes
| JD3RMRC03ST52424 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 03 - ST | 1 | 2025-06-11 | 2025-06-12 |  |  | FALSE | yes
| JD3RMRC03ST52430 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - MR - C - 03 - ST | 1 | 2025-06-02 | 2025-06-03 |  |  | FALSE | yes
| JD3RMRC03ST52431 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - MR - C - 03 - ST | 1 | 2025-06-04 | 2025-06-05 |  |  | FALSE | yes
| JD3RMRC03ST52432 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - MR - C - 03 - ST | 1 | 2025-06-07 | 2025-06-08 |  |  | FALSE | yes
| JD3RMRC03ST52433 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - MR - C - 03 - ST | 1 | 2025-06-09 | 2025-06-10 |  |  | FALSE | yes
| JD3RMRC03ST524341 | Concrete encasement for pipes - NNB6.33 42 11.25 - MR - C - 03 - ST | 1 | 2025-06-09 | 2025-06-15 |  |  | FALSE | yes
| JD3RMRC03TSE52488 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 03 - TSE | 1 | 2025-06-04 | 2025-06-09 | 2025-08-11 |  | FALSE | FALSE
| JD3RMRC03TSE52489 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 03 - TS | 1 | 2025-06-10 | 2025-06-16 | 2025-08-17 |  | FALSE | FALSE
| JD3RMRC03TSE52490 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 03 - TSE | 1 | 2025-06-17 | 2025-06-28 | 2025-08-24 |  | FALSE | FALSE
| JD3RMRC03TSE52491 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 03 - TSE | 1 | 2025-06-29 | 2025-07-06 | 2025-09-16 |  | FALSE | FALSE
| JD3RMRC03TSE52492 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 03 - TSE | 1 | 2025-07-07 | 2025-07-14 | 2025-08-12 |  | FALSE | FALSE
| JD3RMRC03TSE52493 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - C - 03 - TSE | 1 | 2025-07-15 | 2025-07-31 | 2025-08-21 |  | FALSE | FALSE
| JD3RMRC03TSE52494 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - C - 03 - TS | 1 | 2025-08-02 | 2025-08-19 | 2025-08-28 |  | FALSE | FALSE
| JD3RMRC03TSE52495 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - C - 03 - TSE | 1 | 2025-08-20 | 2025-09-06 | 2025-08-31 |  | FALSE | FALSE
| JD3RMRC03TSE52496 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - C - 03 - TSE | 1 | 2025-09-07 | 2025-09-28 | 2025-09-01 |  | FALSE | yes
| JD3RMRC03TSE52497 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - C - 03 - TSE | 1 | 2025-09-29 | 2025-10-20 | 2025-09-02 |  | FALSE | yes
| JD3RMRC03TSE52498 | Excavation Worksfor HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - C - 03 - TSE | 1 | 2025-08-02 | 2025-08-03 |  |  | FALSE | yes
| JD3RMRC03TSE52499 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - C - 03 - TSE | 1 | 2025-08-04 | 2025-08-05 |  |  | FALSE | yes
| JD3RMRC03TSE52500 | Installing for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - C - 03 - TSE | 1 | 2025-08-06 | 2025-08-07 |  |  | FALSE | yes
| JD3RMRC03TSE52501 | Testing for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - C - 03 - TSE | 1 | 2025-08-09 | 2025-08-10 |  |  | FALSE | yes
| JD3RMRC03TSE52502 | Backfillingfor HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - C - 03 - TSE | 1 | 2025-08-11 | 2025-08-12 |  |  | FALSE | yes
| JD3RMRC03TSE52528 | Excavation Worksfor HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 03 - TSE | 1 | 2025-08-04 | 2025-08-05 |  |  | FALSE | yes
| JD3RMRC03TSE52529 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 03 - TSE | 1 | 2025-08-06 | 2025-08-07 |  |  | FALSE | yes
| JD3RMRC03TSE52530 | Installing for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 03 - TSE | 1 | 2025-08-09 | 2025-08-10 |  |  | FALSE | yes
| JD3RMRC03TSE52531 | Testing for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 03 - TSE | 1 | 2025-08-11 | 2025-08-12 |  |  | FALSE | yes
| JD3RMRC03TSE52532 | Backfillingfor HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 03 - TSE | 1 | 2025-08-13 | 2025-08-14 |  |  | FALSE | yes
| JD3RMRC03TSE52578 | Excavation Worksfor GRP Pipes 800 mm - depth from 0 to 1.5 m - B4.33 05 36.01 - MR - C - 03 - TSE | 1 | 2025-08-06 | 2025-08-07 |  |  | FALSE | yes
| JD3RMRC03TSE52579 | Soil Replacement and Bedding Works for GRP Pipes 800 mm - depth from 0 to 1.5 m - B4.33 05 36.01 - MR - C - 03 - TSE | 1 | 2025-08-09 | 2025-08-10 |  |  | FALSE | yes
| JD3RMRC03TSE52580 | Installing for GRP Pipes 800 mm - depth from 0 to 1.5 m - B4.33 05 36.01 - MR - C - 03 - TSE | 1 | 2025-08-11 | 2025-08-12 |  |  | FALSE | yes
| JD3RMRC03TSE52581 | Testing for GRP Pipes 800 mm - depth from 0 to 1.5 m - B4.33 05 36.01 - MR - C - 03 - TSE | 1 | 2025-08-13 | 2025-08-14 |  |  | FALSE | yes
| JD3RMRC03TSE52582 | Backfillingfor GRP Pipes 800 mm - depth from 0 to 1.5 m - B4.33 05 36.01 - MR - C - 03 - TSE | 1 | 2025-08-23 | 2025-08-24 |  |  | FALSE | yes
| JD3RMRC03TSE52583 | Excavation Worksfor GRP Pipes 800 mm - depth from 1.51 to 2.5 m - B4.33 05 36.02 - MR - C - 03 - TSE | 1 | 2025-08-09 | 2025-08-10 |  |  | FALSE | yes
| JD3RMRC03TSE52584 | Soil Replacement and Bedding Works for GRP Pipes 800 mm - depth from 1.51 to 2.5 m - B4.33 05 36.02 - MR - C - 03 - TSE | 1 | 2025-08-11 | 2025-08-12 |  |  | FALSE | yes
| JD3RMRC03TSE52585 | Installing for GRP Pipes 800 mm - depth from 1.51 to 2.5 m - B4.33 05 36.02 - MR - C - 03 - TSE | 1 | 2025-08-13 | 2025-08-14 |  |  | FALSE | yes
| JD3RMRC03TSE52586 | Testing for GRP Pipes 800 mm - depth from 1.51 to 2.5 m - B4.33 05 36.02 - MR - C - 03 - TSE | 1 | 2025-08-16 | 2025-08-17 |  |  | FALSE | yes
| JD3RMRC03TSE52587 | Backfillingfor GRP Pipes 800 mm - depth from 1.51 to 2.5 m - B4.33 05 36.02 - MR - C - 03 - TSE | 1 | 2025-08-23 | 2025-08-24 |  |  | FALSE | yes
| JD3RMRC03TSE52588 | Excavation Worksfor GRP Pipes 800 mm - depth from 2.51 to 3.5 m - B4.33 05 36.03 - MR - C - 03 - TSE | 1 | 2025-08-11 | 2025-08-12 |  |  | FALSE | yes
| JD3RMRC03TSE52589 | Soil Replacement and Bedding Works for GRP Pipes 800 mm - depth from 2.51 to 3.5 m - B4.33 05 36.03 - MR - C - 03 - TSE | 1 | 2025-08-13 | 2025-08-14 |  |  | FALSE | yes
| JD3RMRC03TSE52590 | Installing for GRP Pipes 800 mm - depth from 2.51 to 3.5 m - B4.33 05 36.03 - MR - C - 03 - TSE | 1 | 2025-08-16 | 2025-08-17 |  |  | FALSE | yes
| JD3RMRC03TSE52591 | Testing for GRP Pipes 800 mm - depth from 2.51 to 3.5 m - B4.33 05 36.03 - MR - C - 03 - TSE | 1 | 2025-08-18 | 2025-08-19 |  |  | FALSE | yes
| JD3RMRC03TSE52592 | Backfillingfor GRP Pipes 800 mm - depth from 2.51 to 3.5 m - B4.33 05 36.03 - MR - C - 03 - TSE | 1 | 2025-08-23 | 2025-08-24 |  |  | FALSE | yes
| JD3RMRC03TSE52613 | Installationfor gate valves 100 mm - B4.33 14 19.01 - MR - C - 03 - TSE | 1 | 2025-08-11 | 2025-08-16 | 2025-10-04 |  | FALSE | FALSE
| JD3RMRC03TSE52614 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - MR - C - 03 - TSE | 1 | 2025-08-17 | 2025-08-21 | 2025-10-04 |  | FALSE | FALSE
| JD3RMRC03TSE52615 | Installationfor gate valves 250 mm - B4.33 14 19.02 - MR - C - 03 - TSE | 1 | 2025-08-11 | 2025-08-13 | 2025-10-04 |  | FALSE | FALSE
| JD3RMRC03TSE52616 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - MR - C - 03 - TSE | 1 | 2025-08-14 | 2025-08-17 | 2025-10-04 |  | FALSE | FALSE
| JD3RMRC03TSE52623 | Installationfor butterfly valves 800 mm. - B4.33 14 19.06 - MR - C - 03 - TSE | 1 | 2025-08-11 | 2025-08-12 |  |  | FALSE | yes
| JD3RMRC03TSE52624 | Testing And Commtionningfor butterfly valves 800 mm. - B4.33 14 19.06 - MR - C - 03 - TSE | 1 | 2025-08-13 | 2025-08-14 |  |  | FALSE | yes
| JD3RMRC03TSE52629 | Installationfor Wash - Out valves 200 mm. - on pipes with diameter 700 - 1200 mm - B4.33 14 19.09 - MR - C - 03 - TSE | 1 | 2025-08-11 | 2025-08-12 |  |  | FALSE | yes
| JD3RMRC03TSE52630 | Testing And Commtionningfor Wash - Out valves 200 mm. - on pipes with diameter 700 - 1200 mm - B4.33 14 19.09 - MR - C - | 1 | 2025-08-13 | 2025-08-14 |  |  | FALSE | yes
| JD3RMRC03TSE52631 | Installationfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - MR - C - 03 - TSE | 1 | 2025-08-11 | 2025-08-12 |  |  | FALSE | yes
| JD3RMRC03TSE52632 | Testing And Commtionningfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - MR - C - 03 - | 1 | 2025-08-13 | 2025-08-14 |  |  | FALSE | yes
| JD3RMRC03TSE52645 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 700 to 1000 MM - B4.33 14 13.03 - MR - C - 03 - TSE | 1 | 2025-08-13 | 2025-08-14 |  |  | FALSE | yes
| JD3RMRC03TSE52646 | Plain Concrete Worksfor R.C Valve Chamber - 700 to 1000 MM - B4.33 14 13.03 - MR - C - 03 - TSE | 1 | 2025-08-16 | 2025-08-17 |  |  | FALSE | yes
| JD3RMRC03TSE52647 | INSTALLATIONfor R.C Valve Chamber - 700 to 1000 MM - B4.33 14 13.03 - MR - C - 03 - TSE | 1 | 2025-08-18 | 2025-08-19 |  |  | FALSE | yes
| JD3RMRC03TSE52648 | Backfilling Worksfor R.C Valve Chamber - 700 to 1000 MM - B4.33 14 13.03 - MR - C - 03 - TSE | 1 | 2025-08-23 | 2025-08-24 |  |  | FALSE | yes
| JD3RMRC03TSE52657 | EXCAVATION and Bedding Worksfor Wash - out Valve Chamber - 700 to 1200 MM - B4.33 14 13.08 - MR - C - 03 - TSE | 1 | 2025-08-16 | 2025-08-17 |  |  | FALSE | yes
| JD3RMRC03TSE52658 | Plain Concrete Worksfor Wash - out Valve Chamber - 700 to 1200 MM - B4.33 14 13.08 - MR - C - 03 - TSE | 1 | 2025-08-18 | 2025-08-19 |  |  | FALSE | yes
| JD3RMRC03TSE52659 | INSTALLATIONfor Wash - out Valve Chamber - 700 to 1200 MM - B4.33 14 13.08 - MR - C - 03 - TSE | 1 | 2025-08-20 | 2025-08-21 |  |  | FALSE | yes
| JD3RMRC03TSE52660 | Backfilling Worksfor Wash - out Valve Chamber - 700 to 1200 MM - B4.33 14 13.08 - MR - C - 03 - TSE | 1 | 2025-08-23 | 2025-08-24 |  |  | FALSE | yes
| JD3RMRC03TSE52661 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - C - 03 - TSE | 1 | 2025-08-18 | 2025-08-19 |  |  | FALSE | yes
| JD3RMRC03TSE52662 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - C - 03 - TSE | 1 | 2025-08-20 | 2025-08-21 |  |  | FALSE | yes
| JD3RMRC03TSE52663 | INSTALLATIONfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - C - 03 - TSE | 1 | 2025-08-23 | 2025-08-24 |  |  | FALSE | yes
| JD3RMRC03TSE52664 | Backfilling Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - C - 03 - TSE | 1 | 2025-08-25 | 2025-08-26 |  |  | FALSE | yes
| JD3RMRC05ST100 | Channel excavation for Swales - B6.31 22 00.13 - MR - C - 05 - ST | 1 | 2025-09-04 | 2025-09-23 | 2025-04-10 |  | FALSE | yes
| JD3RMRC05ST100.R | Channel excavation for Swales - B6.31 22 00.13 - MR - C - 05 - ST - Remaining | 1 | 2025-09-24 | 2025-10-06 |  |  | FALSE | yes
| JD3RMRC05ST200 | Riprap With side slopes 1:1 for Swales - NB6.31 22 00.15 - MR - C - 05 - ST | 1 | 2025-10-07 | 2025-10-26 | 2025-04-26 |  | FALSE | yes
| JD3RMRC05ST300.R | Riprap with side slopes 1.5:1 for Swales - NB6.31 22 00.16 - MR - C - 05 - ST - Remaining | 1 | 2025-11-05 | 2025-11-25 |  |  | FALSE | yes
| JD3RMRC05ST53040 | Excavation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 05 - ST | 1 | 2025-09-04 | 2025-09-06 |  |  | FALSE | yes
| JD3RMRC05ST53041 | Plain Concrete Works For Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 05 - ST | 1 | 2025-09-07 | 2025-09-08 |  |  | FALSE | yes
| JD3RMRC05ST53042 | Raft Foundation for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 05 - ST | 1 | 2025-09-09 | 2025-09-13 |  |  | FALSE | yes
| JD3RMRC05ST53043 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 05 - ST | 1 | 2025-09-14 | 2025-09-20 |  |  | FALSE | yes
| JD3RMRC05ST53044 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 05 - ST | 1 | 2025-09-21 | 2025-09-27 |  |  | FALSE | yes
| JD3RMRC05ST53045 | Isolation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 05 - ST | 1 | 2025-09-28 | 2025-09-29 |  |  | FALSE | yes
| JD3RMRC05ST53046 | Backfilling Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 05 - ST | 1 | 2025-09-30 | 2025-10-01 |  |  | FALSE | yes
| JD3RMRC05ST53054 | Excavation Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - MR - C - 05 - ST | 1 | 2025-09-07 | 2025-09-09 |  |  | FALSE | yes
| JD3RMRC05ST53055 | Plain Concrete Works For Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - MR - C - 05 - ST | 1 | 2025-09-10 | 2025-09-11 |  |  | FALSE | yes
| JD3RMRC05ST53056 | Raft Foundation for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - MR - C - 05 - ST | 1 | 2025-09-13 | 2025-09-23 |  |  | FALSE | yes
| JD3RMRC05ST53057 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.03 - MR - C - 05 - ST | 1 | 2025-09-24 | 2025-10-11 |  |  | FALSE | yes
| JD3RMRC05ST53058 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.03 - MR - C - 05 - ST | 1 | 2025-10-12 | 2025-10-28 |  |  | FALSE | yes
| JD3RMRC05ST53059 | Isolation Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - MR - C - 05 - ST | 1 | 2025-10-29 | 2025-11-03 |  |  | FALSE | yes
| JD3RMRC05ST53060 | Backfilling Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - MR - C - 05 - ST | 1 | 2025-11-04 | 2025-11-05 |  |  | FALSE | yes
| JD3RMRC05ST53061 | Excavation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 05 - ST | 1 | 2025-09-10 | 2025-09-13 |  |  | FALSE | yes
| JD3RMRC05ST53062 | Plain Concrete Works For Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 05 - ST | 1 | 2025-09-14 | 2025-09-15 |  |  | FALSE | yes
| JD3RMRC05ST53063 | Raft Foundation for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 05 - ST | 1 | 2025-09-16 | 2025-09-27 |  |  | FALSE | yes
| JD3RMRC05ST53064 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 05 - ST | 1 | 2025-09-28 | 2025-10-14 |  |  | FALSE | yes
| JD3RMRC05ST53065 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 05 - ST | 1 | 2025-10-16 | 2025-11-02 |  |  | FALSE | yes
| JD3RMRC05ST53066 | Isolation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 05 - ST | 1 | 2025-11-03 | 2025-11-08 |  |  | FALSE | yes
| JD3RMRC05ST53067 | Backfilling Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 05 - ST | 1 | 2025-11-09 | 2025-11-10 |  |  | FALSE | yes
| JD3RMRC05ST53068 | Excavation Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 05 - ST | 1 | 2025-09-14 | 2025-09-15 |  |  | FALSE | yes
| JD3RMRC05ST53069 | Plain Concrete Works For Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 05 - ST | 1 | 2025-09-16 | 2025-09-17 |  |  | FALSE | yes
| JD3RMRC05ST53070 | Raft Foundation for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 05 - ST | 1 | 2025-09-18 | 2025-09-20 |  |  | FALSE | yes
| JD3RMRC05ST53071 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.05 - MR - C - 05 - ST | 1 | 2025-09-21 | 2025-09-22 |  |  | FALSE | yes
| JD3RMRC05ST53072 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.05 - MR - C - 05 - ST | 1 | 2025-09-23 | 2025-09-24 |  |  | FALSE | yes
| JD3RMRC05ST53073 | Isolation Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 05 - ST | 1 | 2025-09-25 | 2025-09-27 |  |  | FALSE | yes
| JD3RMRC05ST53074 | Backfilling Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 05 - ST | 1 | 2025-09-28 | 2025-09-29 |  |  | FALSE | yes
| JD3RMRC05ST53075 | Excavation Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 05 - ST | 1 | 2025-09-30 | 2025-10-01 |  |  | FALSE | yes
| JD3RMRC05ST53076 | Plain Concrete Works For Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 05 - ST | 1 | 2025-10-02 | 2025-10-04 |  |  | FALSE | yes
| JD3RMRC05ST53077 | Raft Foundation for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 05 - ST | 1 | 2025-10-05 | 2025-10-06 |  |  | FALSE | yes
| JD3RMRC05ST53078 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 05 - ST | 1 | 2025-10-07 | 2025-10-08 |  |  | FALSE | yes
| JD3RMRC05ST53079 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 05 - ST | 1 | 2025-10-09 | 2025-10-11 |  |  | FALSE | yes
| JD3RMRC05ST53080 | Isolation Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 05 - ST | 1 | 2025-10-12 | 2025-10-13 |  |  | FALSE | yes
| JD3RMRC05ST53081 | Backfilling Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 05 - ST | 1 | 2025-10-14 | 2025-10-15 |  |  | FALSE | yes
| JD3RMRC05ST53118 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - C - 05 - ST | 1 | 2025-11-11 | 2025-11-12 |  |  | FALSE | yes
| JD3RMRC05ST53119 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - C - 05 - ST | 1 | 2025-11-13 | 2025-11-15 |  |  | FALSE | yes
| JD3RMRC05ST53120 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - C - 05 - ST | 1 | 2025-11-16 | 2025-11-17 |  |  | FALSE | yes
| JD3RMRC05ST53121 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - C - 05 - ST | 1 | 2025-11-18 | 2025-11-19 |  |  | FALSE | yes
| JD3RMRC05ST53122 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - C - 05 - ST | 1 | 2025-11-20 | 2025-11-22 |  |  | FALSE | yes
| JD3RMRC05ST53123 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 05 - ST | 1 | 2025-11-13 | 2025-11-15 |  |  | FALSE | yes
| JD3RMRC05ST53124 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 05 - ST | 1 | 2025-11-16 | 2025-11-17 |  |  | FALSE | yes
| JD3RMRC05ST53125 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 05 - ST | 1 | 2025-11-18 | 2025-11-19 |  |  | FALSE | yes
| JD3RMRC05ST53126 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 05 - ST | 1 | 2025-11-20 | 2025-11-22 |  |  | FALSE | yes
| JD3RMRC05ST53127 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 05 - ST | 1 | 2025-11-23 | 2025-11-24 |  |  | FALSE | yes
| JD3RMRC05TSE53201 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 05 - TSE | 1 | 2025-11-26 | 2025-11-27 |  |  | FALSE | yes
| JD3RMRC05TSE53202 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 05 - TS | 1 | 2025-11-29 | 2025-11-30 |  |  | FALSE | yes
| JD3RMRC05TSE53203 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 05 - TSE | 1 | 2025-12-01 | 2025-12-02 |  |  | FALSE | yes
| JD3RMRC05TSE53204 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 05 - TSE | 1 | 2025-12-03 | 2025-12-04 |  |  | FALSE | yes
| JD3RMRC05TSE53205 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 05 - TSE | 1 | 2025-12-20 | 2025-12-21 |  |  | FALSE | yes
| JD3RMRC05TSE53211 | Excavation Worksfor HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - C - 05 - TSE | 1 | 2025-11-26 | 2025-11-30 |  |  | FALSE | yes
| JD3RMRC05TSE53212 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - C - 05 - TSE | 1 | 2025-12-01 | 2025-12-04 |  |  | FALSE | yes
| JD3RMRC05TSE53213 | Installing for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - C - 05 - TSE | 1 | 2025-12-06 | 2025-12-14 |  |  | FALSE | yes
| JD3RMRC05TSE53214 | Testing for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - C - 05 - TSE | 1 | 2025-12-15 | 2025-12-20 |  |  | FALSE | yes
| JD3RMRC05TSE53215 | Backfillingfor HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - C - 05 - TSE | 1 | 2025-12-21 | 2025-12-25 |  |  | FALSE | yes
| JD3RMRC05TSE53281 | Excavation Worksfor HDPE Pipes 630 mm - depth from 2.51 to 3.5 m - B4.33 31 00.17 - MR - C - 05 - TSE | 1 | 2025-12-06 | 2025-12-07 |  |  | FALSE | yes
| JD3RMRC05TSE53282 | Soil Replacement and Bedding Works for HDPE Pipes 630 mm - depth from 2.51 to 3.5 m - B4.33 31 00.17 - MR - C - 05 - TSE | 1 | 2025-12-08 | 2025-12-09 |  |  | FALSE | yes
| JD3RMRC05TSE53283 | Installing for HDPE Pipes 630 mm - depth from 2.51 to 3.5 m - B4.33 31 00.17 - MR - C - 05 - TSE | 1 | 2025-12-10 | 2025-12-11 |  |  | FALSE | yes
| JD3RMRC05TSE53284 | Testing for HDPE Pipes 630 mm - depth from 2.51 to 3.5 m - B4.33 31 00.17 - MR - C - 05 - TSE | 1 | 2025-12-13 | 2025-12-14 |  |  | FALSE | yes
| JD3RMRC05TSE53285 | Backfillingfor HDPE Pipes 630 mm - depth from 2.51 to 3.5 m - B4.33 31 00.17 - MR - C - 05 - TSE | 1 | 2025-12-21 | 2025-12-22 |  |  | FALSE | yes
| JD3RMRC05TSE53326 | Installationfor gate valves 100 mm - B4.33 14 19.01 - MR - C - 05 - TSE | 1 | 2025-12-15 | 2025-12-16 |  |  | FALSE | yes
| JD3RMRC05TSE53327 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - MR - C - 05 - TSE | 1 | 2025-12-17 | 2025-12-18 |  |  | FALSE | yes
| JD3RMRC05TSE53330 | Installationfor butterfly valves 300 mm. - B4.33 14 19.03 - MR - C - 05 - TSE | 1 | 2025-12-15 | 2025-12-16 |  |  | FALSE | yes
| JD3RMRC05TSE53331 | Testing And Commtionningfor butterfly valves 300 mm. - B4.33 14 19.03 - MR - C - 05 - TSE | 1 | 2025-12-17 | 2025-12-18 |  |  | FALSE | yes
| JD3RMRC05TSE53338 | Installationfor Wash - Out valves 100 mm. - on pipes with diameter 110 - 400 mm - B4.33 14 19.07 - MR - C - 05 - TSE | 1 | 2025-12-15 | 2025-12-16 |  |  | FALSE | yes
| JD3RMRC05TSE53339 | Testing And Commtionningfor Wash - Out valves 100 mm. - on pipes with diameter 110 - 400 mm - B4.33 14 19.07 - MR - C - | 1 | 2025-12-17 | 2025-12-18 |  |  | FALSE | yes
| JD3RMRC05TSE53350 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - C - 05 - TSE | 1 | 2025-11-26 | 2025-11-27 |  |  | FALSE | yes
| JD3RMRC05TSE53351 | Plain Concrete Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - C - 05 - TSE | 1 | 2025-11-29 | 2025-11-30 |  |  | FALSE | yes
| JD3RMRC05TSE53352 | INSTALLATIONfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - C - 05 - TSE | 1 | 2025-12-01 | 2025-12-02 |  |  | FALSE | yes
| JD3RMRC05TSE53353 | Backfilling Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - C - 05 - TSE | 1 | 2025-12-03 | 2025-12-04 |  |  | FALSE | yes
| JD3RMRC05TSE53362 | EXCAVATION and Bedding Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - C - 05 - TSE | 1 | 2025-11-26 | 2025-11-27 |  |  | FALSE | yes
| JD3RMRC05TSE53363 | Plain Concrete Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - C - 05 - TSE | 1 | 2025-11-29 | 2025-11-30 |  |  | FALSE | yes
| JD3RMRC05TSE53364 | INSTALLATIONfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - C - 05 - TSE | 1 | 2025-12-01 | 2025-12-02 |  |  | FALSE | yes
| JD3RMRC05TSE53365 | Backfilling Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - C - 05 - TSE | 1 | 2025-12-03 | 2025-12-04 |  |  | FALSE | yes
| JD3RMRC06SS53517 | Trench excavation for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - MR - C - 06 - SS | 1 | 2026-01-04 | 2026-01-05 |  |  | FALSE | yes
| JD3RMRC06SS53518 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - MR - C - 06 - S | 1 | 2026-01-06 | 2026-01-07 |  |  | FALSE | yes
| JD3RMRC06SS53519 | Installing for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - MR - C - 06 - SS | 1 | 2026-01-08 | 2026-01-10 |  |  | FALSE | yes
| JD3RMRC06SS53520 | Primary Test for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - MR - C - 06 - SS | 1 | 2026-01-11 | 2026-01-12 |  |  | FALSE | yes
| JD3RMRC06SS53521 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - MR - C - 06 - S | 1 | 2026-01-13 | 2026-01-14 |  |  | FALSE | yes
| JD3RMRC06SS53532 | Trench excavation for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50 - B5.33 31 00.12 - MR - C - 06 - SS | 1 | 2026-01-06 | 2026-01-13 |  |  | FALSE | yes
| JD3RMRC06SS53533 | Soil Replacement and Bedding Works for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50 - B5.33 31 00.12 - MR - C - 06 - S | 1 | 2026-01-14 | 2026-01-21 |  |  | FALSE | yes
| JD3RMRC06SS53534 | Installing for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50 - B5.33 31 00.12 - MR - C - 06 - SS | 1 | 2026-01-22 | 2026-01-31 |  |  | FALSE | yes
| JD3RMRC06SS53535 | Primary Test for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50 - B5.33 31 00.12 - MR - C - 06 - SS | 1 | 2026-02-01 | 2026-02-08 |  |  | FALSE | yes
| JD3RMRC06SS53536 | Backfilling and warning tabe Works for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50 - B5.33 31 00.12 - MR - C - 06 - S | 1 | 2026-02-09 | 2026-02-19 |  |  | FALSE | yes
| JD3RMRC06SS53566 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - MR - C - 06 - SS | 1 | 2026-01-14 | 2026-01-18 |  |  | FALSE | yes
| JD3RMRC06SS53567 | Installation of Base Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - MR - C - 06 - SS | 1 | 2026-01-19 | 2026-01-27 |  |  | FALSE | yes
| JD3RMRC06SS53568 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - MR - | 1 | 2026-01-28 | 2026-02-05 |  |  | FALSE | yes
| JD3RMRC06SS53569 | Backfilling Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - MR - C - 06 - SS | 1 | 2026-02-07 | 2026-02-10 |  |  | FALSE | yes
| JD3RMRC06SS53570 | Finishing, Benching Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - MR - C - 06 - SS | 1 | 2026-02-11 | 2026-02-15 |  |  | FALSE | yes
| JD3RMRC06ST100 | Channel excavation for Swales - B6.31 22 00.13 - MR - C - 06 - ST | 1 | 2026-01-04 | 2026-01-17 | 2025-11-01 |  | FALSE | yes
| JD3RMRC06ST300 | Riprap with side slopes 1.5:1 for Swales - NB6.31 22 00.16 - MR - C - 06 - ST | 1 | 2026-01-18 | 2026-02-05 | 2025-11-03 |  | FALSE | yes
| JD3RMRC06ST53638 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - C - 06 - ST | 1 | 2026-02-21 | 2026-02-22 |  |  | FALSE | yes
| JD3RMRC06ST53639 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - C - 06 | 1 | 2026-02-23 | 2026-02-24 |  |  | FALSE | yes
| JD3RMRC06ST53640 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - C - 06 - ST | 1 | 2026-02-25 | 2026-02-26 |  |  | FALSE | yes
| JD3RMRC06ST53641 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - C - 06 - ST | 1 | 2026-02-28 | 2026-03-01 |  |  | FALSE | yes
| JD3RMRC06ST53642 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - C - 06 - ST | 1 | 2026-03-02 | 2026-03-03 |  |  | FALSE | yes
| JD3RMRC06ST53668 | Excavation Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - C - 06 - ST | 1 | 2026-02-21 | 2026-02-22 |  |  | FALSE | yes
| JD3RMRC06ST53669 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - C - 06 - | 1 | 2026-02-23 | 2026-02-24 |  |  | FALSE | yes
| JD3RMRC06ST53670 | Installing for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - C - 06 - ST | 1 | 2026-02-25 | 2026-02-26 |  |  | FALSE | yes
| JD3RMRC06ST53671 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - C - 06 - ST | 1 | 2026-02-28 | 2026-03-01 |  |  | FALSE | yes
| JD3RMRC06ST53672 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - C - 06 - ST | 1 | 2026-03-02 | 2026-03-03 |  |  | FALSE | yes
| JD3RMRC06ST53743 | Excavation Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 06 - ST | 1 | 2026-02-21 | 2026-02-22 |  |  | FALSE | yes
| JD3RMRC06ST53744 | Soil Replacement and Bedding Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 06 | 1 | 2026-02-23 | 2026-02-24 |  |  | FALSE | yes
| JD3RMRC06ST53745 | Installing for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 06 - ST | 1 | 2026-02-25 | 2026-02-26 |  |  | FALSE | yes
| JD3RMRC06ST53746 | Primary Test for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 06 - ST | 1 | 2026-02-28 | 2026-03-01 |  |  | FALSE | yes
| JD3RMRC06ST53747 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 06 - ST | 1 | 2026-03-02 | 2026-03-03 |  |  | FALSE | yes
| JD3RMRC06ST53781 | Excavation Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 06 - ST | 1 | 2026-02-07 | 2026-02-08 |  |  | FALSE | yes
| JD3RMRC06ST53782 | Plain Concrete Works For Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 06 - ST | 1 | 2026-02-09 | 2026-02-10 |  |  | FALSE | yes
| JD3RMRC06ST53783 | Raft Foundation for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 06 - ST | 1 | 2026-02-11 | 2026-02-12 |  |  | FALSE | yes
| JD3RMRC06ST53784 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.05 - MR - C - 06 - ST | 1 | 2026-02-14 | 2026-02-16 |  |  | FALSE | yes
| JD3RMRC06ST53785 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.05 - MR - C - 06 - ST | 1 | 2026-02-17 | 2026-02-19 |  |  | FALSE | yes
| JD3RMRC06ST53786 | Isolation Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 06 - ST | 1 | 2026-02-21 | 2026-02-22 |  |  | FALSE | yes
| JD3RMRC06ST53787 | Backfilling Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 06 - ST | 1 | 2026-02-23 | 2026-02-24 |  |  | FALSE | yes
| JD3RMRC06ST53788 | Excavation Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 06 - ST | 1 | 2026-02-09 | 2026-02-10 |  |  | FALSE | yes
| JD3RMRC06ST53789 | Plain Concrete Works For Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 06 - ST | 1 | 2026-02-11 | 2026-02-12 |  |  | FALSE | yes
| JD3RMRC06ST53790 | Raft Foundation for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 06 - ST | 1 | 2026-02-14 | 2026-02-15 |  |  | FALSE | yes
| JD3RMRC06ST53791 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 06 - ST | 1 | 2026-02-16 | 2026-02-18 |  |  | FALSE | yes
| JD3RMRC06ST53792 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 06 - ST | 1 | 2026-02-19 | 2026-02-22 |  |  | FALSE | yes
| JD3RMRC06ST53793 | Isolation Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 06 - ST | 1 | 2026-02-23 | 2026-02-24 |  |  | FALSE | yes
| JD3RMRC06ST53794 | Backfilling Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 06 - ST | 1 | 2026-02-25 | 2026-02-26 |  |  | FALSE | yes
| JD3RMRC06ST53836 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 06 - ST | 1 | 2026-02-21 | 2026-02-22 |  |  | FALSE | yes
| JD3RMRC06ST53837 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 06 - ST | 1 | 2026-02-23 | 2026-02-24 |  |  | FALSE | yes
| JD3RMRC06ST53838 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 06 - ST | 1 | 2026-02-25 | 2026-02-26 |  |  | FALSE | yes
| JD3RMRC06ST53839 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 06 - ST | 1 | 2026-02-28 | 2026-03-01 |  |  | FALSE | yes
| JD3RMRC06ST53840 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 06 - ST | 1 | 2026-03-02 | 2026-03-03 |  |  | FALSE | yes
| JD3RMRC06ST53856 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - MR - C - 06 - ST | 1 | 2026-02-21 | 2026-02-22 |  |  | FALSE | yes
| JD3RMRC06ST53857 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - MR - C - 06 - ST | 1 | 2026-02-23 | 2026-02-24 |  |  | FALSE | yes
| JD3RMRC06ST53858 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - MR - C - 06 - ST | 1 | 2026-02-25 | 2026-02-26 |  |  | FALSE | yes
| JD3RMRC06ST53859 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - MR - C - 06 - ST | 1 | 2026-02-28 | 2026-03-01 |  |  | FALSE | yes
| JD3RMRC06SUR01 | Surveying Works C - 06 | 1 |  |  |  |  | yes | FALSE
| JD3RMRC06TSE53914 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 06 - TSE | 1 | 2026-03-04 | 2026-03-05 |  |  | FALSE | yes
| JD3RMRC06TSE53915 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 06 - TS | 1 | 2026-03-07 | 2026-03-08 |  |  | FALSE | yes
| JD3RMRC06TSE53916 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 06 - TSE | 1 | 2026-03-09 | 2026-03-10 |  |  | FALSE | yes
| JD3RMRC06TSE53917 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 06 - TSE | 1 | 2026-03-11 | 2026-03-12 |  |  | FALSE | yes
| JD3RMRC06TSE53918 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 06 - TSE | 1 | 2026-03-29 | 2026-03-30 |  |  | FALSE | yes
| JD3RMRC06TSE53919 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - C - 06 - TSE | 1 | 2026-03-04 | 2026-03-05 |  |  | FALSE | yes
| JD3RMRC06TSE53920 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - C - 06 - TS | 1 | 2026-03-07 | 2026-03-08 |  |  | FALSE | yes
| JD3RMRC06TSE53921 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - C - 06 - TSE | 1 | 2026-03-09 | 2026-03-12 |  |  | FALSE | yes
| JD3RMRC06TSE53922 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - C - 06 - TSE | 1 | 2026-03-14 | 2026-03-16 |  |  | FALSE | yes
| JD3RMRC06TSE53923 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - C - 06 - TSE | 1 | 2026-03-29 | 2026-03-31 |  |  | FALSE | yes
| JD3RMRC06TSE53924 | Excavation Worksfor HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - C - 06 - TSE | 1 | 2026-03-04 | 2026-03-08 | 2025-08-06 |  | FALSE | yes
| JD3RMRC06TSE53925 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - C - 06 - TSE | 1 | 2026-03-09 | 2026-03-14 | 2025-08-13 |  | FALSE | yes
| JD3RMRC06TSE53926 | Installing for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - C - 06 - TSE | 1 | 2026-03-15 | 2026-03-23 | 2025-08-18 |  | FALSE | yes
| JD3RMRC06TSE53927 | Testing for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - C - 06 - TSE | 1 | 2026-03-24 | 2026-03-29 | 2025-09-09 |  | FALSE | yes
| JD3RMRC06TSE53928 | Backfillingfor HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - C - 06 - TSE | 1 | 2026-03-30 | 2026-04-04 | 2025-08-04 |  | FALSE | yes
| JD3RMRC06TSE53954 | Excavation Worksfor HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 06 - TSE | 1 | 2026-03-04 | 2026-03-05 |  |  | FALSE | yes
| JD3RMRC06TSE53955 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 06 - TSE | 1 | 2026-03-07 | 2026-03-08 |  |  | FALSE | yes
| JD3RMRC06TSE53956 | Installing for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 06 - TSE | 1 | 2026-03-09 | 2026-03-10 |  |  | FALSE | yes
| JD3RMRC06TSE53957 | Testing for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 06 - TSE | 1 | 2026-03-11 | 2026-03-12 |  |  | FALSE | yes
| JD3RMRC06TSE53958 | Backfillingfor HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 06 - TSE | 1 | 2026-03-29 | 2026-03-30 |  |  | FALSE | yes
| JD3RMRC06TSE53959 | Excavation Worksfor HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - MR - C - 06 - TSE | 1 | 2026-03-04 | 2026-03-05 |  |  | FALSE | yes
| JD3RMRC06TSE53960 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - MR - C - 06 - TSE | 1 | 2026-03-07 | 2026-03-08 |  |  | FALSE | yes
| JD3RMRC06TSE53961 | Installing for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - MR - C - 06 - TSE | 1 | 2026-03-09 | 2026-03-10 |  |  | FALSE | yes
| JD3RMRC06TSE53962 | Testing for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - MR - C - 06 - TSE | 1 | 2026-03-11 | 2026-03-12 |  |  | FALSE | yes
| JD3RMRC06TSE53963 | Backfillingfor HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - MR - C - 06 - TSE | 1 | 2026-03-29 | 2026-03-30 |  |  | FALSE | yes
| JD3RMRC06TSE54039 | Installationfor gate valves 100 mm - B4.33 14 19.01 - MR - C - 06 - TSE | 1 | 2026-03-24 | 2026-03-25 |  |  | FALSE | yes
| JD3RMRC06TSE54040 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - MR - C - 06 - TSE | 1 | 2026-03-26 | 2026-03-28 |  |  | FALSE | yes
| JD3RMRC06TSE54041 | Installationfor gate valves 250 mm - B4.33 14 19.02 - MR - C - 06 - TSE | 1 | 2026-03-24 | 2026-03-25 |  |  | FALSE | yes
| JD3RMRC06TSE54042 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - MR - C - 06 - TSE | 1 | 2026-03-26 | 2026-03-28 |  |  | FALSE | yes
| JD3RMRC06TSE54043 | Installationfor butterfly valves 300 mm. - B4.33 14 19.03 - MR - C - 06 - TSE | 1 | 2026-03-24 | 2026-03-25 |  |  | FALSE | yes
| JD3RMRC06TSE54044 | Testing And Commtionningfor butterfly valves 300 mm. - B4.33 14 19.03 - MR - C - 06 - TSE | 1 | 2026-03-26 | 2026-03-28 |  |  | FALSE | yes
| JD3RMRC06TSE54051 | Installationfor Wash - Out valves 100 mm. - on pipes with diameter 110 - 400 mm - B4.33 14 19.07 - MR - C - 06 - TSE | 1 | 2026-03-24 | 2026-03-25 |  |  | FALSE | yes
| JD3RMRC06TSE54052 | Testing And Commtionningfor Wash - Out valves 100 mm. - on pipes with diameter 110 - 400 mm - B4.33 14 19.07 - MR - C - | 1 | 2026-03-26 | 2026-03-28 |  |  | FALSE | yes
| JD3RMRC06TSE54063 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - C - 06 - TSE | 1 | 2026-03-04 | 2026-03-05 |  |  | FALSE | yes
| JD3RMRC06TSE54064 | Plain Concrete Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - C - 06 - TSE | 1 | 2026-03-07 | 2026-03-08 |  |  | FALSE | yes
| JD3RMRC06TSE54065 | INSTALLATIONfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - C - 06 - TSE | 1 | 2026-03-09 | 2026-03-10 |  |  | FALSE | yes
| JD3RMRC06TSE54066 | Backfilling Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - C - 06 - TSE | 1 | 2026-03-11 | 2026-03-12 |  |  | FALSE | yes
| JD3RMRC06TSE54075 | EXCAVATION and Bedding Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - C - 06 - TSE | 1 | 2026-03-04 | 2026-03-05 |  |  | FALSE | yes
| JD3RMRC06TSE54076 | Plain Concrete Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - C - 06 - TSE | 1 | 2026-03-07 | 2026-03-08 |  |  | FALSE | yes
| JD3RMRC06TSE54077 | INSTALLATIONfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - C - 06 - TSE | 1 | 2026-03-09 | 2026-03-10 |  |  | FALSE | yes
| JD3RMRC06TSE54078 | Backfilling Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - C - 06 - TSE | 1 | 2026-03-24 | 2026-03-25 |  |  | FALSE | yes
| JD3RMRC07ST100 | Channel excavation for Swales - B6.31 22 00.13 - MR - C - 07 - ST | 1 | 2026-04-13 | 2026-04-19 | 2025-11-01 |  | FALSE | yes
| JD3RMRC07ST300 | Riprap with side slopes 1.5:1 for Swales - NB6.31 22 00.16 - MR - C - 07 - ST | 1 | 2026-04-20 | 2026-04-26 | 2025-11-03 |  | FALSE | yes
| JD3RMRC07ST54480 | Excavation Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - MR - C - 07 - ST | 1 | 2026-04-13 | 2026-04-14 |  |  | FALSE | yes
| JD3RMRC07ST54481 | Plain Concrete Works For Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - MR - C - 07 - ST | 1 | 2026-04-15 | 2026-04-16 |  |  | FALSE | yes
| JD3RMRC07ST54482 | Raft Foundation for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - MR - C - 07 - ST | 1 | 2026-04-18 | 2026-04-21 |  |  | FALSE | yes
| JD3RMRC07ST54483 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.03 - MR - C - 07 - ST | 1 | 2026-04-22 | 2026-04-28 |  |  | FALSE | yes
| JD3RMRC07ST54484 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.03 - MR - C - 07 - ST | 1 | 2026-04-29 | 2026-05-05 |  |  | FALSE | yes
| JD3RMRC07ST54485 | Isolation Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - MR - C - 07 - ST | 1 | 2026-05-06 | 2026-05-07 |  |  | FALSE | yes
| JD3RMRC07ST54486 | Backfilling Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - MR - C - 07 - ST | 1 | 2026-05-09 | 2026-05-10 |  |  | FALSE | yes
| JD3RMRC07ST54487 | Excavation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 07 - ST | 1 | 2026-04-15 | 2026-04-16 |  |  | FALSE | yes
| JD3RMRC07ST54488 | Plain Concrete Works For Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 07 - ST | 1 | 2026-04-18 | 2026-04-19 |  |  | FALSE | yes
| JD3RMRC07ST54489 | Raft Foundation for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 07 - ST | 1 | 2026-04-20 | 2026-04-23 |  |  | FALSE | yes
| JD3RMRC07ST54490 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 07 - ST | 1 | 2026-04-25 | 2026-04-30 |  |  | FALSE | yes
| JD3RMRC07ST54491 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 07 - ST | 1 | 2026-05-02 | 2026-05-07 |  |  | FALSE | yes
| JD3RMRC07ST54492 | Isolation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 07 - ST | 1 | 2026-05-09 | 2026-05-10 |  |  | FALSE | yes
| JD3RMRC07ST54493 | Backfilling Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 07 - ST | 1 | 2026-05-11 | 2026-05-12 |  |  | FALSE | yes
| JD3RMRC07ST54494 | Excavation Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 07 - ST | 1 | 2026-04-18 | 2026-04-19 |  |  | FALSE | yes
| JD3RMRC07ST54495 | Plain Concrete Works For Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 07 - ST | 1 | 2026-04-20 | 2026-04-21 |  |  | FALSE | yes
| JD3RMRC07ST54496 | Raft Foundation for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 07 - ST | 1 | 2026-04-22 | 2026-04-25 |  |  | FALSE | yes
| JD3RMRC07ST54497 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.05 - MR - C - 07 - ST | 1 | 2026-04-26 | 2026-04-29 |  |  | FALSE | yes
| JD3RMRC07ST54498 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.05 - MR - C - 07 - ST | 1 | 2026-04-30 | 2026-05-04 |  |  | FALSE | yes
| JD3RMRC07ST54499 | Isolation Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 07 - ST | 1 | 2026-05-05 | 2026-05-06 |  |  | FALSE | yes
| JD3RMRC07ST54500 | Backfilling Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 07 - ST | 1 | 2026-05-13 | 2026-05-14 |  |  | FALSE | yes
| JD3RMRC07ST54501 | Excavation Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 07 - ST | 1 | 2026-04-20 | 2026-04-21 |  |  | FALSE | yes
| JD3RMRC07ST54502 | Plain Concrete Works For Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 07 - ST | 1 | 2026-04-22 | 2026-04-23 |  |  | FALSE | yes
| JD3RMRC07ST54503 | Raft Foundation for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 07 - ST | 1 | 2026-04-25 | 2026-04-27 |  |  | FALSE | yes
| JD3RMRC07ST54504 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 07 - ST | 1 | 2026-04-28 | 2026-05-02 |  |  | FALSE | yes
| JD3RMRC07ST54505 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 07 - ST | 1 | 2026-05-03 | 2026-05-06 |  |  | FALSE | yes
| JD3RMRC07ST54506 | Isolation Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 07 - ST | 1 | 2026-05-07 | 2026-05-09 |  |  | FALSE | yes
| JD3RMRC07ST54507 | Backfilling Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 07 - ST | 1 | 2026-05-16 | 2026-05-17 |  |  | FALSE | yes
| JD3RMRC07ST54549 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 07 - ST | 1 | 2026-04-22 | 2026-04-23 |  |  | FALSE | yes
| JD3RMRC07ST54550 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 07 - ST | 1 | 2026-04-25 | 2026-04-26 |  |  | FALSE | yes
| JD3RMRC07ST54551 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 07 - ST | 1 | 2026-04-27 | 2026-04-28 |  |  | FALSE | yes
| JD3RMRC07ST54552 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 07 - ST | 1 | 2026-04-29 | 2026-04-30 |  |  | FALSE | yes
| JD3RMRC07ST54553 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 07 - ST | 1 | 2026-05-02 | 2026-05-03 |  |  | FALSE | yes
| JD3RMRC07TSE54627 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 07 - TSE | 1 | 2026-05-18 | 2026-05-19 |  |  | FALSE | yes
| JD3RMRC07TSE54628 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 07 - TS | 1 | 2026-05-20 | 2026-05-21 |  |  | FALSE | yes
| JD3RMRC07TSE54629 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 07 - TSE | 1 | 2026-05-23 | 2026-05-24 |  |  | FALSE | yes
| JD3RMRC07TSE54630 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 07 - TSE | 1 | 2026-05-25 | 2026-05-26 |  |  | FALSE | yes
| JD3RMRC07TSE54631 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 07 - TSE | 1 | 2026-06-04 | 2026-06-06 |  |  | FALSE | yes
| JD3RMRC07TSE54754 | Installationfor gate valves 250 mm - B4.33 14 19.02 - MR - C - 07 - TSE | 1 | 2026-05-25 | 2026-05-26 |  |  | FALSE | yes
| JD3RMRC07TSE54755 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - MR - C - 07 - TSE | 1 | 2026-05-27 | 2026-05-28 |  |  | FALSE | yes
| JD3RMRC07TSE54764 | Installationfor Wash - Out valves 100 mm. - on pipes with diameter 110 - 400 mm - B4.33 14 19.07 - MR - C - 07 - TSE | 1 | 2026-05-31 | 2026-06-01 |  |  | FALSE | yes
| JD3RMRC07TSE54765 | Testing And Commtionningfor Wash - Out valves 100 mm. - on pipes with diameter 110 - 400 mm - B4.33 14 19.07 - MR - C - | 1 | 2026-06-02 | 2026-06-03 |  |  | FALSE | yes
| JD3RMRC07TSE54788 | EXCAVATION and Bedding Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - C - 07 - TSE | 1 | 2026-05-18 | 2026-05-19 |  |  | FALSE | yes
| JD3RMRC07TSE54789 | Plain Concrete Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - C - 07 - TSE | 1 | 2026-05-20 | 2026-05-21 |  |  | FALSE | yes
| JD3RMRC07TSE54790 | INSTALLATIONfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - C - 07 - TSE | 1 | 2026-05-23 | 2026-05-24 |  |  | FALSE | yes
| JD3RMRC07TSE54791 | Backfilling Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - C - 07 - TSE | 1 | 2026-06-04 | 2026-06-06 |  |  | FALSE | yes
| JD3RMRC08ST100.R | Channel excavation for Swales - B6.31 22 00.13 - MR - C - 08 - ST - Remaining | 1 | 2025-08-30 | 2025-09-11 | 2025-08-17 |  | FALSE | yes
| JD3RMRC08ST300.R | Riprap with side slopes 1.5:1 for Swales - NB6.31 22 00.16 - MR - C - 08 - ST - Remaining | 1 | 2025-10-01 | 2025-10-20 | 2025-08-25 |  | FALSE | yes
| JD3RMRC08ST55169 | Excavation Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 08 - ST | 1 | 2025-10-30 | 2025-11-01 |  |  | FALSE | yes
| JD3RMRC08ST55170 | Soil Replacement and Bedding Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 08 | 1 | 2025-11-02 | 2025-11-03 |  |  | FALSE | yes
| JD3RMRC08ST55171 | Installing for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 08 - ST | 1 | 2025-11-04 | 2025-11-05 |  |  | FALSE | yes
| JD3RMRC08ST55172 | Primary Test for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 08 - ST | 1 | 2025-11-06 | 2025-11-08 |  |  | FALSE | yes
| JD3RMRC08ST55173 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 08 - ST | 1 | 2025-11-09 | 2025-11-10 |  |  | FALSE | yes
| JD3RMRC08ST55179 | Excavation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 08 - ST | 1 | 2025-10-23 | 2025-10-25 |  |  | FALSE | yes
| JD3RMRC08ST55180 | Plain Concrete Works For Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 08 - ST | 1 | 2025-10-26 | 2025-10-27 |  |  | FALSE | yes
| JD3RMRC08ST55181 | Raft Foundation for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 08 - ST | 1 | 2025-10-28 | 2025-10-30 |  |  | FALSE | yes
| JD3RMRC08ST55182 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 08 - ST | 1 | 2025-11-01 | 2025-11-04 |  |  | FALSE | yes
| JD3RMRC08ST55183 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 08 - ST | 1 | 2025-11-05 | 2025-11-09 |  |  | FALSE | yes
| JD3RMRC08ST55184 | Isolation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 08 - ST | 1 | 2025-11-10 | 2025-11-11 |  |  | FALSE | yes
| JD3RMRC08ST55185 | Backfilling Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 08 - ST | 1 | 2025-11-12 | 2025-11-13 |  |  | FALSE | yes
| JD3RMRC08ST55257 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - C - 08 - ST | 1 | 2025-10-28 | 2025-10-29 |  |  | FALSE | yes
| JD3RMRC08ST55258 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - C - 08 - ST | 1 | 2025-10-30 | 2025-11-01 |  |  | FALSE | yes
| JD3RMRC08ST55259 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - C - 08 - ST | 1 | 2025-11-02 | 2025-11-03 |  |  | FALSE | yes
| JD3RMRC08ST55260 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - C - 08 - ST | 1 | 2025-11-04 | 2025-11-05 |  |  | FALSE | yes
| JD3RMRC08ST55261 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - C - 08 - ST | 1 | 2025-11-06 | 2025-11-08 |  |  | FALSE | yes
| JD3RMRC08ST55262 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 08 - ST | 1 | 2025-10-30 | 2025-11-01 |  |  | FALSE | yes
| JD3RMRC08ST55263 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 08 - ST | 1 | 2025-11-02 | 2025-11-03 |  |  | FALSE | yes
| JD3RMRC08ST55264 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 08 - ST | 1 | 2025-11-04 | 2025-11-05 |  |  | FALSE | yes
| JD3RMRC08ST55265 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 08 - ST | 1 | 2025-11-06 | 2025-11-08 |  |  | FALSE | yes
| JD3RMRC08ST55266 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 08 - ST | 1 | 2025-11-09 | 2025-11-10 |  |  | FALSE | yes
| JD3RMRC09ST100 | Channel excavation for Swales - B6.31 22 00.13 - MR - C - 09 - ST | 1 | 2024-09-10 | 2024-10-02 | 2025-04-15 |  | FALSE | FALSE
| JD3RMRC09ST100.R | Channel excavation for Swales - B6.31 22 00.13 - MR - C - 09 - ST - Remaining | 1 | 2024-10-03 | 2024-10-14 |  |  | FALSE | yes
| JD3RMRC09ST300.R | Riprap with side slopes 1.5:1 for Swales - NB6.31 22 00.16 - MR - C - 09 - ST - Remaining | 1 | 2024-10-17 | 2024-11-10 | 2025-08-13 |  | FALSE | FALSE
| JD3RMRC09ST55882 | Excavation Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 09 - ST | 1 | 2024-11-11 | 2024-11-12 |  |  | FALSE | yes
| JD3RMRC09ST55883 | Soil Replacement and Bedding Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 09 | 1 | 2024-11-13 | 2024-11-14 |  |  | FALSE | yes
| JD3RMRC09ST55884 | Installing for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 09 - ST | 1 | 2024-11-16 | 2024-11-17 |  |  | FALSE | yes
| JD3RMRC09ST55885 | Primary Test for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 09 - ST | 1 | 2024-11-18 | 2024-11-19 |  |  | FALSE | yes
| JD3RMRC09ST55886 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 09 - ST | 1 | 2024-11-20 | 2024-11-21 |  |  | FALSE | yes
| JD3RMRC10ST100.R | Channel excavation for Swales - B6.31 22 00.13 - MR - C - 10 - ST - Remaining | 1 | 2025-01-11 | 2025-01-26 |  |  | FALSE | yes
| JD3RMRC10ST300.R | Riprap with side slopes 1.5:1 for Swales - NB6.31 22 00.16 - MR - C - 10 - ST - Remaining | 1 | 2025-02-03 | 2025-02-20 |  |  | FALSE | yes
| JD3RMRC10ST56595 | Excavation Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 10 - ST | 1 | 2025-04-10 | 2025-04-14 | 2025-08-11 |  | FALSE | FALSE
| JD3RMRC10ST56596 | Soil Replacement and Bedding Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 10 | 1 | 2025-04-15 | 2025-04-19 | 2025-08-13 |  | FALSE | FALSE
| JD3RMRC10ST56597 | Installing for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 10 - ST | 1 | 2025-04-20 | 2025-04-23 | 2025-08-15 |  | FALSE | FALSE
| JD3RMRC10ST56598 | Primary Test for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 10 - ST | 1 | 2025-04-24 | 2025-04-28 |  |  | FALSE | yes
| JD3RMRC10ST56599 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 10 - ST | 1 | 2025-04-29 | 2025-05-04 |  |  | FALSE | yes
| JD3RMRC10ST56633 | Excavation Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 10 - ST | 1 | 2025-02-24 | 2025-02-25 |  |  | FALSE | yes
| JD3RMRC10ST56634 | Plain Concrete Works For Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 10 - ST | 1 | 2025-02-26 | 2025-02-27 |  |  | FALSE | yes
| JD3RMRC10ST56635 | Raft Foundation for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 10 - ST | 1 | 2025-03-01 | 2025-03-08 |  |  | FALSE | yes
| JD3RMRC10ST56636 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.05 - MR - C - 10 - ST | 1 | 2025-03-09 | 2025-03-19 |  |  | FALSE | yes
| JD3RMRC10ST56637 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.05 - MR - C - 10 - ST | 1 | 2025-03-20 | 2025-03-31 |  |  | FALSE | yes
| JD3RMRC10ST56638 | Isolation Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 10 - ST | 1 | 2025-04-01 | 2025-04-05 |  |  | FALSE | yes
| JD3RMRC10ST56639 | Backfilling Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 10 - ST | 1 | 2025-04-06 | 2025-04-07 |  |  | FALSE | yes
| JD3RMRC10ST56640 | Excavation Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 10 - ST | 1 | 2025-02-22 | 2025-02-23 |  |  | FALSE | yes
| JD3RMRC10ST56641 | Plain Concrete Works For Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 10 - ST | 1 | 2025-02-24 | 2025-02-25 |  |  | FALSE | yes
| JD3RMRC10ST56642 | Raft Foundation for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 10 - ST | 1 | 2025-02-26 | 2025-03-05 |  |  | FALSE | yes
| JD3RMRC10ST56643 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 10 - ST | 1 | 2025-03-06 | 2025-03-17 |  |  | FALSE | yes
| JD3RMRC10ST56644 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 10 - ST | 1 | 2025-03-18 | 2025-03-29 |  |  | FALSE | yes
| JD3RMRC10ST56645 | Isolation Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 10 - ST | 1 | 2025-03-30 | 2025-04-02 |  |  | FALSE | yes
| JD3RMRC10ST56646 | Backfilling Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 10 - ST | 1 | 2025-04-03 | 2025-04-05 |  |  | FALSE | yes
| JD3RMRC10ST56688 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 10 - ST | 1 | 2025-04-08 | 2025-04-09 |  |  | FALSE | yes
| JD3RMRC10ST56689 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 10 - ST | 1 | 2025-04-10 | 2025-04-12 |  |  | FALSE | yes
| JD3RMRC10ST56690 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 10 - ST | 1 | 2025-04-13 | 2025-04-14 |  |  | FALSE | yes
| JD3RMRC10ST56691 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 10 - ST | 1 | 2025-04-15 | 2025-04-16 |  |  | FALSE | yes
| JD3RMRC10ST56692 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 10 - ST | 1 | 2025-04-17 | 2025-04-19 |  |  | FALSE | yes
| JD3RMRC10ST56698 | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 10 - ST | 1 | 2025-04-10 | 2025-04-12 | 2025-08-11 |  | FALSE | FALSE
| JD3RMRC10ST56699 | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 10 - ST | 1 | 2025-04-13 | 2025-04-14 | 2025-08-15 |  | FALSE | FALSE
| JD3RMRC10ST56700 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 10 - ST | 1 | 2025-04-15 | 2025-04-16 |  |  | FALSE | yes
| JD3RMRC10ST56701 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 10 - ST | 1 | 2025-04-17 | 2025-04-19 |  |  | FALSE | yes
| JD3RMRC10ST56702 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 10 - ST | 1 | 2025-04-20 | 2025-04-21 |  |  | FALSE | yes
| JD3RMRC11ST100.R | Channel excavation for Swales - B6.31 22 00.13 - MR - C - 11 - ST - Remaining | 1 | 2025-09-09 | 2025-10-02 | 2025-08-19 |  | FALSE | yes
| JD3RMRC11ST301 | Riprap with side slopes 1.5:1 for Swales - NB6.31 22 00.16 - MR - C - 11 - ST | 1 | 2025-11-06 | 2025-11-27 | 2025-08-16 |  | FALSE | yes
| JD3RMRC11ST57318 | Excavation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 11 - ST | 1 | 2025-10-09 | 2025-10-11 |  |  | FALSE | yes
| JD3RMRC11ST57319 | Plain Concrete Works For Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 11 - ST | 1 | 2025-10-12 | 2025-10-13 |  |  | FALSE | yes
| JD3RMRC11ST57320 | Raft Foundation for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 11 - ST | 1 | 2025-10-14 | 2025-10-15 |  |  | FALSE | yes
| JD3RMRC11ST57321 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 11 - ST | 1 | 2025-10-16 | 2025-10-18 |  |  | FALSE | yes
| JD3RMRC11ST57322 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 11 - ST | 1 | 2025-10-19 | 2025-10-20 |  |  | FALSE | yes
| JD3RMRC11ST57323 | Isolation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 11 - ST | 1 | 2025-10-21 | 2025-10-22 |  |  | FALSE | yes
| JD3RMRC11ST57324 | Backfilling Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - MR - C - 11 - ST | 1 | 2025-10-23 | 2025-10-25 |  |  | FALSE | yes
| JD3RMRC11ST57332 | Excavation Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - MR - C - 11 - ST | 1 | 2025-10-04 | 2025-10-08 |  |  | FALSE | yes
| JD3RMRC11ST57333 | Plain Concrete Works For Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - MR - C - 11 - ST | 1 | 2025-10-09 | 2025-10-11 |  |  | FALSE | yes
| JD3RMRC11ST57334 | Raft Foundation for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - MR - C - 11 - ST | 1 | 2025-10-12 | 2025-10-28 |  |  | FALSE | yes
| JD3RMRC11ST57335 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.03 - MR - C - 11 - ST | 1 | 2025-10-29 | 2025-11-19 |  |  | FALSE | yes
| JD3RMRC11ST57336 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.03 - MR - C - 11 - ST | 1 | 2025-11-20 | 2025-12-11 |  |  | FALSE | yes
| JD3RMRC11ST57337 | Isolation Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - MR - C - 11 - ST | 1 | 2025-12-13 | 2025-12-21 |  |  | FALSE | yes
| JD3RMRC11ST57338 | Backfilling Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - MR - C - 11 - ST | 1 | 2025-12-22 | 2025-12-24 |  |  | FALSE | yes
| JD3RMRC11ST57339 | Excavation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 11 - ST | 1 | 2025-10-12 | 2025-10-16 |  |  | FALSE | yes
| JD3RMRC11ST57340 | Plain Concrete Works For Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 11 - ST | 1 | 2025-10-18 | 2025-10-19 |  |  | FALSE | yes
| JD3RMRC11ST57341 | Raft Foundation for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 11 - ST | 1 | 2025-10-20 | 2025-11-05 |  |  | FALSE | yes
| JD3RMRC11ST57342 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 11 - ST | 1 | 2025-11-06 | 2025-11-27 |  |  | FALSE | yes
| JD3RMRC11ST57343 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 11 - ST | 1 | 2025-11-29 | 2025-12-20 |  |  | FALSE | yes
| JD3RMRC11ST57344 | Isolation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 11 - ST | 1 | 2025-12-21 | 2025-12-29 |  |  | FALSE | yes
| JD3RMRC11ST57345 | Backfilling Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 11 - ST | 1 | 2025-12-30 | 2026-01-01 |  |  | FALSE | yes
| JD3RMRC11ST57401 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 11 - ST | 1 | 2025-11-29 | 2025-11-30 |  |  | FALSE | yes
| JD3RMRC11ST57402 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 11 - ST | 1 | 2025-12-01 | 2025-12-03 |  |  | FALSE | yes
| JD3RMRC11ST57403 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 11 - ST | 1 | 2025-12-04 | 2025-12-07 |  |  | FALSE | yes
| JD3RMRC11ST57404 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 11 - ST | 1 | 2025-12-08 | 2025-12-09 |  |  | FALSE | yes
| JD3RMRC11ST57405 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 11 - ST | 1 | 2025-12-10 | 2025-12-11 |  |  | FALSE | yes
| JD3RMRC11TSE57479 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 11 - TSE | 1 | 2026-01-03 | 2026-01-04 |  |  | FALSE | yes
| JD3RMRC11TSE57480 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 11 - TS | 1 | 2026-01-05 | 2026-01-06 |  |  | FALSE | yes
| JD3RMRC11TSE57481 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 11 - TSE | 1 | 2026-01-07 | 2026-01-08 |  |  | FALSE | yes
| JD3RMRC11TSE57482 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 11 - TSE | 1 | 2026-01-10 | 2026-01-11 |  |  | FALSE | yes
| JD3RMRC11TSE57483 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 11 - TSE | 1 | 2026-02-22 | 2026-02-23 |  |  | FALSE | yes
| JD3RMRC11TSE57484.R | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - C - 11 - TSE - Remaining | 1 | 2026-01-15 | 2026-01-17 |  |  | FALSE | yes
| JD3RMRC11TSE57485.R | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - C - 11 - TS | 1 | 2026-01-26 | 2026-01-27 |  |  | FALSE | yes
| JD3RMRC11TSE57486.R | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - C - 11 - TSE - Remaining | 1 | 2026-02-15 | 2026-02-16 | 2025-09-09 |  | FALSE | yes
| JD3RMRC11TSE57487 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - C - 11 - TSE | 1 | 2026-02-17 | 2026-03-01 | 2025-09-03 |  | FALSE | yes
| JD3RMRC11TSE57488 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - C - 11 - TSE | 1 | 2026-03-02 | 2026-03-14 | 2025-09-09 |  | FALSE | yes
| JD3RMRC11TSE57519 | Excavation Worksfor HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 11 - TSE | 1 | 2026-01-18 | 2026-01-19 |  |  | FALSE | yes
| JD3RMRC11TSE57520 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 11 - TSE | 1 | 2026-01-20 | 2026-01-21 |  |  | FALSE | yes
| JD3RMRC11TSE57521 | Installing for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 11 - TSE | 1 | 2026-01-22 | 2026-01-24 |  |  | FALSE | yes
| JD3RMRC11TSE57522 | Testing for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 11 - TSE | 1 | 2026-01-25 | 2026-01-26 |  |  | FALSE | yes
| JD3RMRC11TSE57523 | Backfillingfor HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 11 - TSE | 1 | 2026-01-27 | 2026-01-28 |  |  | FALSE | yes
| JD3RMRC11TSE57528 | Backfillingfor HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - MR - C - 11 - TSE | 1 | 2026-02-03 | 2026-02-05 | 2025-09-16 |  | FALSE | yes
| JD3RMRC11TSE57604 | Installationfor gate valves 100 mm - B4.33 14 19.01 - MR - C - 11 - TSE | 1 | 2026-02-17 | 2026-02-18 |  |  | FALSE | yes
| JD3RMRC11TSE57605 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - MR - C - 11 - TSE | 1 | 2026-02-19 | 2026-02-21 |  |  | FALSE | yes
| JD3RMRC11TSE57606 | Installationfor gate valves 250 mm - B4.33 14 19.02 - MR - C - 11 - TSE | 1 | 2026-02-17 | 2026-02-18 |  |  | FALSE | yes
| JD3RMRC11TSE57607 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - MR - C - 11 - TSE | 1 | 2026-02-19 | 2026-02-21 |  |  | FALSE | yes
| JD3RMRC11TSE57610 | Installationfor butterfly valves 400 mm. - B4.33 14 19.04 - MR - C - 11 - TSE | 1 | 2026-02-17 | 2026-02-18 |  |  | FALSE | yes
| JD3RMRC11TSE57611 | Testing And Commtionningfor butterfly valves 400 mm. - B4.33 14 19.04 - MR - C - 11 - TSE | 1 | 2026-02-19 | 2026-02-21 |  |  | FALSE | yes
| JD3RMRC11TSE57616 | Installationfor Wash - Out valves 100 mm. - on pipes with diameter 110 - 400 mm - B4.33 14 19.07 - MR - C - 11 - TSE | 1 | 2026-02-17 | 2026-02-18 |  |  | FALSE | yes
| JD3RMRC11TSE57617 | Testing And Commtionningfor Wash - Out valves 100 mm. - on pipes with diameter 110 - 400 mm - B4.33 14 19.07 - MR - C - | 1 | 2026-02-19 | 2026-02-21 |  |  | FALSE | yes
| JD3RMRC11TSE57618 | Installationfor Wash - Out valves 150 mm. - on pipes with diameter 450 - 630 mm - B4.33 14 19.08 - MR - C - 11 - TSE | 1 | 2026-02-17 | 2026-02-18 |  |  | FALSE | yes
| JD3RMRC11TSE57619 | Testing And Commtionningfor Wash - Out valves 150 mm. - on pipes with diameter 450 - 630 mm - B4.33 14 19.08 - MR - C - | 1 | 2026-02-19 | 2026-02-21 |  |  | FALSE | yes
| JD3RMRC11TSE57622 | Installationfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - MR - C - 11 - TSE | 1 | 2026-02-17 | 2026-02-18 |  |  | FALSE | yes
| JD3RMRC11TSE57623 | Testing And Commtionningfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - MR - C - 11 - | 1 | 2026-02-19 | 2026-02-21 |  |  | FALSE | yes
| JD3RMRC11TSE57628 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - C - 11 - TSE | 1 | 2026-01-26 | 2026-01-27 |  |  | FALSE | yes
| JD3RMRC11TSE57629 | Plain Concrete Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - C - 11 - TSE | 1 | 2026-01-28 | 2026-01-29 |  |  | FALSE | yes
| JD3RMRC11TSE57630 | INSTALLATIONfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - C - 11 - TSE | 1 | 2026-01-31 | 2026-02-01 |  |  | FALSE | yes
| JD3RMRC11TSE57631 | Backfilling Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - C - 11 - TSE | 1 | 2026-02-22 | 2026-02-23 |  |  | FALSE | yes
| JD3RMRC11TSE57640 | EXCAVATION and Bedding Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - C - 11 - TSE | 1 | 2026-01-28 | 2026-01-29 |  |  | FALSE | yes
| JD3RMRC11TSE57641 | Plain Concrete Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - C - 11 - TSE | 1 | 2026-01-31 | 2026-02-01 |  |  | FALSE | yes
| JD3RMRC11TSE57642 | INSTALLATIONfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - C - 11 - TSE | 1 | 2026-02-02 | 2026-02-03 |  |  | FALSE | yes
| JD3RMRC11TSE57643 | Backfilling Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - C - 11 - TSE | 1 | 2026-02-04 | 2026-02-05 |  |  | FALSE | yes
| JD3RMRC11TSE57644 | EXCAVATION and Bedding Worksfor Wash - out Valve Chamber - 450 to 630 MM - B4.33 14 13.07 - MR - C - 11 - TSE | 1 | 2026-01-03 | 2026-01-04 |  |  | FALSE | yes
| JD3RMRC11TSE57645 | Plain Concrete Worksfor Wash - out Valve Chamber - 450 to 630 MM - B4.33 14 13.07 - MR - C - 11 - TSE | 1 | 2026-01-05 | 2026-01-06 |  |  | FALSE | yes
| JD3RMRC11TSE57646 | INSTALLATIONfor Wash - out Valve Chamber - 450 to 630 MM - B4.33 14 13.07 - MR - C - 11 - TSE | 1 | 2026-01-07 | 2026-01-08 |  |  | FALSE | yes
| JD3RMRC11TSE57647 | Backfilling Worksfor Wash - out Valve Chamber - 450 to 630 MM - B4.33 14 13.07 - MR - C - 11 - TSE | 1 | 2026-01-10 | 2026-01-11 |  |  | FALSE | yes
| JD3RMRC11TSE57652 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - C - 11 - TSE | 1 | 2026-01-03 | 2026-01-04 |  |  | FALSE | yes
| JD3RMRC11TSE57653 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - C - 11 - TSE | 1 | 2026-01-05 | 2026-01-06 |  |  | FALSE | yes
| JD3RMRC11TSE57654 | INSTALLATIONfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - C - 11 - TSE | 1 | 2026-01-07 | 2026-01-08 |  |  | FALSE | yes
| JD3RMRC11TSE57655 | Backfilling Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - C - 11 - TSE | 1 | 2026-01-10 | 2026-01-11 |  |  | FALSE | yes
| JD3RMRC12ST100 | Channel excavation for Swales - B6.31 22 00.13 - MR - C - 12 - ST | 1 | 2026-03-23 | 2026-04-09 | 2025-06-14 |  | FALSE | yes
| JD3RMRC12ST300 | Riprap with side slopes 1.5:1 for Swales - NB6.31 22 00.16 - MR - C - 12 - ST | 1 | 2026-04-11 | 2026-05-02 | 2025-08-13 |  | FALSE | yes
| JD3RMRC12TSE58192 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 12 - TSE | 1 | 2026-05-14 | 2026-05-16 |  |  | FALSE | yes
| JD3RMRC12TSE58193 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 12 - TS | 1 | 2026-05-17 | 2026-05-18 |  |  | FALSE | yes
| JD3RMRC12TSE58194 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 12 - TSE | 1 | 2026-05-19 | 2026-05-20 |  |  | FALSE | yes
| JD3RMRC12TSE58195 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 12 - TSE | 1 | 2026-05-21 | 2026-05-23 |  |  | FALSE | yes
| JD3RMRC12TSE58196 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 12 - TSE | 1 | 2026-05-26 | 2026-05-27 |  |  | FALSE | yes
| JD3RMRC12TSE58197.R | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - C - 12 - TSE - Remaining | 1 | 2026-05-21 | 2026-05-23 |  |  | FALSE | yes
| JD3RMRC12TSE58198.R | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - C - 12 - TS | 1 | 2026-05-26 | 2026-05-27 |  |  | FALSE | yes
| JD3RMRC12TSE58199.R | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - C - 12 - TSE - Remaining | 1 | 2026-06-03 | 2026-06-04 |  |  | FALSE | yes
| JD3RMRC12TSE58200.R | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - C - 12 - TSE - Remaining | 1 | 2026-06-09 | 2026-06-10 |  |  | FALSE | yes
| JD3RMRC12TSE58201.R | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - C - 12 - TSE - Remaining | 1 | 2026-06-15 | 2026-06-16 |  |  | FALSE | yes
| JD3RMRC12TSE58232 | Excavation Worksfor HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 12 - TSE | 1 | 2026-05-14 | 2026-05-16 |  |  | FALSE | yes
| JD3RMRC12TSE58233 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 12 - TSE | 1 | 2026-05-17 | 2026-05-18 |  |  | FALSE | yes
| JD3RMRC12TSE58234 | Installing for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 12 - TSE | 1 | 2026-05-19 | 2026-05-20 |  |  | FALSE | yes
| JD3RMRC12TSE58235 | Testing for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 12 - TSE | 1 | 2026-05-21 | 2026-05-23 |  |  | FALSE | yes
| JD3RMRC12TSE58236 | Backfillingfor HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 12 - TSE | 1 | 2026-06-17 | 2026-06-18 |  |  | FALSE | yes
| JD3RMRC12TSE58262 | Excavation Worksfor HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - C - 12 - TSE | 1 | 2026-05-14 | 2026-05-16 |  |  | FALSE | yes
| JD3RMRC12TSE58263 | Soil Replacement and Bedding Works for HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - C - 12 - TSE | 1 | 2026-05-17 | 2026-05-18 |  |  | FALSE | yes
| JD3RMRC12TSE58264 | Installing for HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - C - 12 - TSE | 1 | 2026-05-19 | 2026-05-20 |  |  | FALSE | yes
| JD3RMRC12TSE58265 | Testing for HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - C - 12 - TSE | 1 | 2026-05-21 | 2026-05-23 |  |  | FALSE | yes
| JD3RMRC12TSE58266 | Backfillingfor HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - C - 12 - TSE | 1 | 2026-05-26 | 2026-05-27 |  |  | FALSE | yes
| JD3RMRC12TSE58317 | Installationfor gate valves 100 mm - B4.33 14 19.01 - MR - C - 12 - TSE | 1 | 2026-05-21 | 2026-05-23 |  |  | FALSE | yes
| JD3RMRC12TSE58318 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - MR - C - 12 - TSE | 1 | 2026-05-24 | 2026-05-25 |  |  | FALSE | yes
| JD3RMRC12TSE58319 | Installationfor gate valves 250 mm - B4.33 14 19.02 - MR - C - 12 - TSE | 1 | 2026-05-21 | 2026-05-23 |  |  | FALSE | yes
| JD3RMRC12TSE58320 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - MR - C - 12 - TSE | 1 | 2026-05-24 | 2026-05-25 |  |  | FALSE | yes
| JD3RMRC12TSE58335 | Installationfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - MR - C - 12 - TSE | 1 | 2026-05-21 | 2026-05-23 |  |  | FALSE | yes
| JD3RMRC12TSE58336 | Testing And Commtionningfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - MR - C - 12 - | 1 | 2026-05-24 | 2026-05-25 |  |  | FALSE | yes
| JD3RMRC12TSE58365 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - C - 12 - TSE | 1 | 2026-05-14 | 2026-05-16 |  |  | FALSE | yes
| JD3RMRC12TSE58366 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - C - 12 - TSE | 1 | 2026-05-17 | 2026-05-18 |  |  | FALSE | yes
| JD3RMRC12TSE58367 | INSTALLATIONfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - C - 12 - TSE | 1 | 2026-05-19 | 2026-05-20 |  |  | FALSE | yes
| JD3RMRC12TSE58368 | Backfilling Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - C - 12 - TSE | 1 | 2026-06-20 | 2026-06-21 |  |  | FALSE | yes
| JD3RMRC13SL59158 | Excavation Worksfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - MR - C - 13 - SL | 1 | 2026-03-10 | 2026-03-11 |  |  | FALSE | yes
| JD3RMRC13SL59159 | Installationfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - MR - C - 13 - SL | 1 | 2026-03-12 | 2026-03-14 |  |  | FALSE | yes
| JD3RMRC13SL59160 | Pouring Concrete Coverfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - MR - C - 13 - SL | 1 | 2026-03-15 | 2026-03-16 |  |  | FALSE | yes
| JD3RMRC13SL59161 | Testing and Backfilling Worksfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - MR - C - 13 - SL | 1 | 2026-03-17 | 2026-03-18 |  |  | FALSE | yes
| JD3RMRC13SL59173 | Excavationfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - MR - C - 13 - SL | 1 | 2026-03-10 | 2026-03-11 |  |  | FALSE | yes
| JD3RMRC13SL59174 | Installationfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - MR - C - 13 - SL | 1 | 2026-03-12 | 2026-03-14 |  |  | FALSE | yes
| JD3RMRC13SL59175 | Backfillingfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - MR - C - 13 - SL | 1 | 2026-03-15 | 2026-03-16 |  |  | FALSE | yes
| JD3RMRC13ST100.R | Channel excavation for Swales - B6.31 22 00.13 - MR - C - 13 - ST - Remaining | 1 | 2025-09-18 | 2025-10-06 | 2025-11-03 |  | FALSE | FALSE
| JD3RMRC13ST300.R | Riprap with side slopes 1.5:1 for Swales - NB6.31 22 00.16 - MR - C - 13 - ST - Remaining | 1 | 2025-10-26 | 2025-11-13 | 2025-08-13 |  | FALSE | yes
| JD3RMRC13ST58629 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - C - 13 - ST | 1 | 2026-01-22 | 2026-01-24 |  |  | FALSE | yes
| JD3RMRC13ST58630 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - C - 13 | 1 | 2026-01-25 | 2026-01-26 |  |  | FALSE | yes
| JD3RMRC13ST58631 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - C - 13 - ST | 1 | 2026-01-27 | 2026-01-28 |  |  | FALSE | yes
| JD3RMRC13ST58632 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - C - 13 - ST | 1 | 2026-01-29 | 2026-01-31 |  |  | FALSE | yes
| JD3RMRC13ST58633 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - C - 13 - ST | 1 | 2026-02-01 | 2026-02-02 |  |  | FALSE | yes
| JD3RMRC13ST58659 | Excavation Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - C - 13 - ST | 1 | 2026-01-27 | 2026-01-28 |  |  | FALSE | yes
| JD3RMRC13ST58660 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - C - 13 - | 1 | 2026-01-29 | 2026-01-31 |  |  | FALSE | yes
| JD3RMRC13ST58661 | Installing for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - C - 13 - ST | 1 | 2026-02-01 | 2026-02-02 |  |  | FALSE | yes
| JD3RMRC13ST58662 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - C - 13 - ST | 1 | 2026-02-03 | 2026-02-04 |  |  | FALSE | yes
| JD3RMRC13ST58663 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - C - 13 - ST | 1 | 2026-02-05 | 2026-02-07 |  |  | FALSE | yes
| JD3RMRC13ST58758 | Excavation Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - MR - C - 13 - ST | 1 | 2025-12-07 | 2025-12-08 |  |  | FALSE | yes
| JD3RMRC13ST58759 | Plain Concrete Works For Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - MR - C - 13 - ST | 1 | 2025-12-09 | 2025-12-10 |  |  | FALSE | yes
| JD3RMRC13ST58760 | Raft Foundation for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - MR - C - 13 - ST | 1 | 2025-12-11 | 2025-12-14 |  |  | FALSE | yes
| JD3RMRC13ST58761 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.03 - MR - C - 13 - ST | 1 | 2025-12-15 | 2025-12-18 |  |  | FALSE | yes
| JD3RMRC13ST58762 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.03 - MR - C - 13 - ST | 1 | 2025-12-20 | 2025-12-23 |  |  | FALSE | yes
| JD3RMRC13ST58763 | Isolation Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - MR - C - 13 - ST | 1 | 2025-12-24 | 2025-12-25 |  |  | FALSE | yes
| JD3RMRC13ST58764 | Backfilling Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - MR - C - 13 - ST | 1 | 2025-12-27 | 2025-12-28 |  |  | FALSE | yes
| JD3RMRC13ST58765 | Excavation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 13 - ST | 1 | 2025-11-15 | 2025-11-16 |  |  | FALSE | yes
| JD3RMRC13ST58766 | Plain Concrete Works For Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 13 - ST | 1 | 2025-11-17 | 2025-11-18 |  |  | FALSE | yes
| JD3RMRC13ST58767 | Raft Foundation for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 13 - ST | 1 | 2025-11-19 | 2025-11-22 |  |  | FALSE | yes
| JD3RMRC13ST58768 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 13 - ST | 1 | 2025-11-23 | 2025-11-26 |  |  | FALSE | yes
| JD3RMRC13ST58769 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 13 - ST | 1 | 2025-11-27 | 2025-12-01 |  |  | FALSE | yes
| JD3RMRC13ST58770 | Isolation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 13 - ST | 1 | 2025-12-02 | 2025-12-03 |  |  | FALSE | yes
| JD3RMRC13ST58771 | Backfilling Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - C - 13 - ST | 1 | 2025-12-04 | 2025-12-06 |  |  | FALSE | yes
| JD3RMRC13ST58772 | Excavation Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 13 - ST | 1 | 2025-12-29 | 2025-12-30 |  |  | FALSE | yes
| JD3RMRC13ST58773 | Plain Concrete Works For Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 13 - ST | 1 | 2025-12-31 | 2026-01-01 |  |  | FALSE | yes
| JD3RMRC13ST58774 | Raft Foundation for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 13 - ST | 1 | 2026-01-03 | 2026-01-05 |  |  | FALSE | yes
| JD3RMRC13ST58775 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.05 - MR - C - 13 - ST | 1 | 2026-01-06 | 2026-01-10 |  |  | FALSE | yes
| JD3RMRC13ST58776 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.05 - MR - C - 13 - ST | 1 | 2026-01-11 | 2026-01-14 |  |  | FALSE | yes
| JD3RMRC13ST58777 | Isolation Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 13 - ST | 1 | 2026-01-15 | 2026-01-17 |  |  | FALSE | yes
| JD3RMRC13ST58778 | Backfilling Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 13 - ST | 1 | 2026-01-18 | 2026-01-19 |  |  | FALSE | yes
| JD3RMRC13ST58779 | Excavation Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 13 - ST | 1 | 2026-01-20 | 2026-01-21 |  |  | FALSE | yes
| JD3RMRC13ST58780 | Plain Concrete Works For Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 13 - ST | 1 | 2026-01-22 | 2026-01-24 |  |  | FALSE | yes
| JD3RMRC13ST58781 | Raft Foundation for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 13 - ST | 1 | 2026-01-25 | 2026-01-27 |  |  | FALSE | yes
| JD3RMRC13ST58782 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 13 - ST | 1 | 2026-01-28 | 2026-02-01 |  |  | FALSE | yes
| JD3RMRC13ST58783 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 13 - ST | 1 | 2026-02-02 | 2026-02-05 |  |  | FALSE | yes
| JD3RMRC13ST58784 | Isolation Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 13 - ST | 1 | 2026-02-07 | 2026-02-08 |  |  | FALSE | yes
| JD3RMRC13ST58785 | Backfilling Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 13 - ST | 1 | 2026-02-09 | 2026-02-10 |  |  | FALSE | yes
| JD3RMRC13ST58827 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 13 - ST | 1 | 2026-01-22 | 2026-01-24 |  |  | FALSE | yes
| JD3RMRC13ST58828 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 13 - ST | 1 | 2026-01-25 | 2026-01-26 |  |  | FALSE | yes
| JD3RMRC13ST58829 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 13 - ST | 1 | 2026-01-27 | 2026-01-28 |  |  | FALSE | yes
| JD3RMRC13ST58830 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 13 - ST | 1 | 2026-01-29 | 2026-01-31 |  |  | FALSE | yes
| JD3RMRC13ST58831 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 13 - ST | 1 | 2026-02-01 | 2026-02-02 |  |  | FALSE | yes
| JD3RMRC13ST58837 | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 13 - ST | 1 | 2026-01-29 | 2026-01-31 |  |  | FALSE | yes
| JD3RMRC13ST58838 | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 13 - ST | 1 | 2026-02-01 | 2026-02-02 |  |  | FALSE | yes
| JD3RMRC13ST58839 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 13 - ST | 1 | 2026-02-03 | 2026-02-04 |  |  | FALSE | yes
| JD3RMRC13ST58840 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 13 - ST | 1 | 2026-02-05 | 2026-02-07 |  |  | FALSE | yes
| JD3RMRC13ST58841 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 13 - ST | 1 | 2026-02-08 | 2026-02-09 |  |  | FALSE | yes
| JD3RMRC13ST58847 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - MR - C - 13 - ST | 1 | 2026-02-01 | 2026-02-02 |  |  | FALSE | yes
| JD3RMRC13ST58848 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - MR - C - 13 - ST | 1 | 2026-02-03 | 2026-02-04 |  |  | FALSE | yes
| JD3RMRC13ST58849 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - MR - C - 13 - ST | 1 | 2026-02-05 | 2026-02-07 |  |  | FALSE | yes
| JD3RMRC13ST58850 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - MR - C - 13 - ST | 1 | 2026-02-08 | 2026-02-09 |  |  | FALSE | yes
| JD3RMRC13TSE58905 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 13 - TSE | 1 | 2026-02-11 | 2026-02-12 |  |  | FALSE | yes
| JD3RMRC13TSE58906 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 13 - TS | 1 | 2026-02-14 | 2026-02-15 |  |  | FALSE | yes
| JD3RMRC13TSE58907 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 13 - TSE | 1 | 2026-02-16 | 2026-02-17 |  |  | FALSE | yes
| JD3RMRC13TSE58908 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 13 - TSE | 1 | 2026-02-18 | 2026-02-19 |  |  | FALSE | yes
| JD3RMRC13TSE58909 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 13 - TSE | 1 | 2026-03-05 | 2026-03-07 |  |  | FALSE | yes
| JD3RMRC13TSE58978 | Testing for HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - C - 13 - TSE | 1 | 2026-02-18 | 2026-02-19 |  |  | FALSE | yes
| JD3RMRC13TSE58979 | Backfillingfor HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - C - 13 - TSE | 1 | 2026-03-05 | 2026-03-07 |  |  | FALSE | yes
| JD3RMRC13TSE58983 | Testing for HDPE Pipes 630 mm - depth from 1.51 to 2.5 m - B4.33 31 00.16 - MR - C - 13 - TSE | 1 | 2026-02-18 | 2026-02-19 |  |  | FALSE | yes
| JD3RMRC13TSE58984 | Backfillingfor HDPE Pipes 630 mm - depth from 1.51 to 2.5 m - B4.33 31 00.16 - MR - C - 13 - TSE | 1 | 2026-03-05 | 2026-03-07 |  |  | FALSE | yes
| JD3RMRC13TSE59036 | Installationfor butterfly valves 400 mm. - B4.33 14 19.04 - MR - C - 13 - TSE | 1 | 2026-03-01 | 2026-03-02 |  |  | FALSE | yes
| JD3RMRC13TSE59037 | Testing And Commtionningfor butterfly valves 400 mm. - B4.33 14 19.04 - MR - C - 13 - TSE | 1 | 2026-03-03 | 2026-03-04 |  |  | FALSE | yes
| JD3RMRC13TSE59038 | Installationfor butterfly valves 600 mm. - B4.33 14 19.05 - MR - C - 13 - TSE | 1 | 2026-03-01 | 2026-03-02 |  |  | FALSE | yes
| JD3RMRC13TSE59039 | Testing And Commtionningfor butterfly valves 600 mm. - B4.33 14 19.05 - MR - C - 13 - TSE | 1 | 2026-03-03 | 2026-03-04 |  |  | FALSE | yes
| JD3RMRC13TSE59054 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - C - 13 - TSE | 1 | 2026-02-11 | 2026-02-12 |  |  | FALSE | yes
| JD3RMRC13TSE59055 | Plain Concrete Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - C - 13 - TSE | 1 | 2026-02-14 | 2026-02-15 |  |  | FALSE | yes
| JD3RMRC13TSE59056 | INSTALLATIONfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - C - 13 - TSE | 1 | 2026-02-16 | 2026-02-17 |  |  | FALSE | yes
| JD3RMRC13TSE59057 | Backfilling Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - C - 13 - TSE | 1 | 2026-02-18 | 2026-02-19 |  |  | FALSE | yes
| JD3RMRC13TSE59058 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 500 to 630 MM - B4.33 14 13.02 - MR - C - 13 - TSE | 1 | 2026-02-11 | 2026-02-12 |  |  | FALSE | yes
| JD3RMRC13TSE59059 | Plain Concrete Worksfor R.C Valve Chamber - 500 to 630 MM - B4.33 14 13.02 - MR - C - 13 - TSE | 1 | 2026-02-14 | 2026-02-15 |  |  | FALSE | yes
| JD3RMRC13TSE59060 | INSTALLATIONfor R.C Valve Chamber - 500 to 630 MM - B4.33 14 13.02 - MR - C - 13 - TSE | 1 | 2026-02-16 | 2026-02-17 |  |  | FALSE | yes
| JD3RMRC13TSE59061 | Backfilling Worksfor R.C Valve Chamber - 500 to 630 MM - B4.33 14 13.02 - MR - C - 13 - TSE | 1 | 2026-02-21 | 2026-02-22 |  |  | FALSE | yes
| JD3RMRC14ST100.R | Channel excavation for Swales - B6.31 22 00.13 - MR - C - 14 - ST - Remaining | 1 | 2026-02-11 | 2026-02-24 | 2025-08-10 |  | FALSE | yes
| JD3RMRC14ST300.R | Riprap with side slopes 1.5:1 for Swales - NB6.31 22 00.16 - MR - C - 14 - ST - Remaining | 1 | 2026-03-04 | 2026-03-24 | 2025-08-12 |  | FALSE | yes
| JD3RMRC14ST59485 | Excavation Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 14 - ST | 1 | 2026-03-28 | 2026-03-29 |  |  | FALSE | yes
| JD3RMRC14ST59486 | Plain Concrete Works For Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 14 - ST | 1 | 2026-03-30 | 2026-03-31 |  |  | FALSE | yes
| JD3RMRC14ST59487 | Raft Foundation for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 14 - ST | 1 | 2026-04-01 | 2026-04-06 |  |  | FALSE | yes
| JD3RMRC14ST59488 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.05 - MR - C - 14 - ST | 1 | 2026-04-07 | 2026-04-14 |  |  | FALSE | yes
| JD3RMRC14ST59489 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.05 - MR - C - 14 - ST | 1 | 2026-04-15 | 2026-04-22 |  |  | FALSE | yes
| JD3RMRC14ST59490 | Isolation Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 14 - ST | 1 | 2026-04-23 | 2026-04-26 |  |  | FALSE | yes
| JD3RMRC14ST59491 | Backfilling Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - MR - C - 14 - ST | 1 | 2026-04-27 | 2026-04-28 |  |  | FALSE | yes
| JD3RMRC14ST59492 | Excavation Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 14 - ST | 1 | 2026-03-25 | 2026-03-26 |  |  | FALSE | yes
| JD3RMRC14ST59493 | Plain Concrete Works For Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 14 - ST | 1 | 2026-03-28 | 2026-03-29 |  |  | FALSE | yes
| JD3RMRC14ST59494 | Raft Foundation for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 14 - ST | 1 | 2026-03-30 | 2026-04-04 |  |  | FALSE | yes
| JD3RMRC14ST59495 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 14 - ST | 1 | 2026-04-05 | 2026-04-12 |  |  | FALSE | yes
| JD3RMRC14ST59496 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 14 - ST | 1 | 2026-04-13 | 2026-04-20 |  |  | FALSE | yes
| JD3RMRC14ST59497 | Isolation Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 14 - ST | 1 | 2026-04-21 | 2026-04-23 |  |  | FALSE | yes
| JD3RMRC14ST59498 | Backfilling Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - MR - C - 14 - ST | 1 | 2026-04-25 | 2026-04-26 |  |  | FALSE | yes
| JD3RMRC14ST59540 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 14 - ST | 1 | 2026-04-09 | 2026-04-11 |  |  | FALSE | yes
| JD3RMRC14ST59541 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 14 - ST | 1 | 2026-04-12 | 2026-04-13 |  |  | FALSE | yes
| JD3RMRC14ST59542 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 14 - ST | 1 | 2026-04-14 | 2026-04-15 |  |  | FALSE | yes
| JD3RMRC14ST59543 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 14 - ST | 1 | 2026-04-16 | 2026-04-18 |  |  | FALSE | yes
| JD3RMRC14ST59544 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - C - 14 - ST | 1 | 2026-04-19 | 2026-04-20 |  |  | FALSE | yes
| JD3RMRC14ST59550 | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 14 - ST | 1 | 2026-04-12 | 2026-04-13 |  |  | FALSE | yes
| JD3RMRC14ST59551 | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 14 - ST | 1 | 2026-04-14 | 2026-04-15 |  |  | FALSE | yes
| JD3RMRC14ST59552 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 14 - ST | 1 | 2026-04-16 | 2026-04-18 |  |  | FALSE | yes
| JD3RMRC14ST59553 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 14 - ST | 1 | 2026-04-19 | 2026-04-20 |  |  | FALSE | yes
| JD3RMRC14ST59554 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 14 - ST | 1 | 2026-04-21 | 2026-04-22 |  |  | FALSE | yes
| JD3RMRC14TSE59618 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 14 - TSE | 1 | 2026-04-29 | 2026-04-30 |  |  | FALSE | yes
| JD3RMRC14TSE59619 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 14 - TS | 1 | 2026-05-02 | 2026-05-03 |  |  | FALSE | yes
| JD3RMRC14TSE59620 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 14 - TSE | 1 | 2026-05-04 | 2026-05-05 |  |  | FALSE | yes
| JD3RMRC14TSE59621 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 14 - TSE | 1 | 2026-05-06 | 2026-05-07 |  |  | FALSE | yes
| JD3RMRC14TSE59622 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - C - 14 - TSE | 1 | 2026-05-19 | 2026-05-20 |  |  | FALSE | yes
| JD3RMRC14TSE59743 | Installationfor gate valves 100 mm - B4.33 14 19.01 - MR - C - 14 - TSE | 1 | 2026-05-14 | 2026-05-16 |  |  | FALSE | yes
| JD3RMRC14TSE59744 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - MR - C - 14 - TSE | 1 | 2026-05-17 | 2026-05-18 |  |  | FALSE | yes
| JD3RMRC14TSE59751 | Installationfor butterfly valves 600 mm. - B4.33 14 19.05 - MR - C - 14 - TSE | 1 | 2026-05-14 | 2026-05-16 |  |  | FALSE | yes
| JD3RMRC14TSE59752 | Testing And Commtionningfor butterfly valves 600 mm. - B4.33 14 19.05 - MR - C - 14 - TSE | 1 | 2026-05-17 | 2026-05-18 |  |  | FALSE | yes
| JD3RMRC14TSE59763 | Installationfor Air valves 65 mm. - on pipes with diameter 355 - 630 mm - B4.33 14 19.16 - MR - C - 14 - TSE | 1 | 2026-05-14 | 2026-05-16 |  |  | FALSE | yes
| JD3RMRC14TSE59764 | Testing And Commtionningfor Air valves 65 mm. - on pipes with diameter 355 - 630 mm - B4.33 14 19.16 - MR - C - 14 - TSE | 1 | 2026-05-17 | 2026-05-18 |  |  | FALSE | yes
| JD3RMRC14TSE59771 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 500 to 630 MM - B4.33 14 13.02 - MR - C - 14 - TSE | 1 | 2026-04-29 | 2026-04-30 |  |  | FALSE | yes
| JD3RMRC14TSE59772 | Plain Concrete Worksfor R.C Valve Chamber - 500 to 630 MM - B4.33 14 13.02 - MR - C - 14 - TSE | 1 | 2026-05-02 | 2026-05-03 |  |  | FALSE | yes
| JD3RMRC14TSE59773 | INSTALLATIONfor R.C Valve Chamber - 500 to 630 MM - B4.33 14 13.02 - MR - C - 14 - TSE | 1 | 2026-05-04 | 2026-05-05 |  |  | FALSE | yes
| JD3RMRC14TSE59774 | Backfilling Worksfor R.C Valve Chamber - 500 to 630 MM - B4.33 14 13.02 - MR - C - 14 - TSE | 1 | 2026-05-06 | 2026-05-07 |  |  | FALSE | yes
| JD3RMRC14TSE59795 | EXCAVATION and Bedding Worksfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - C - 14 - TSE | 1 | 2026-04-29 | 2026-04-30 |  |  | FALSE | yes
| JD3RMRC14TSE59796 | Plain Concrete Worksfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - C - 14 - TSE | 1 | 2026-05-02 | 2026-05-03 |  |  | FALSE | yes
| JD3RMRC14TSE59797 | INSTALLATIONfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - C - 14 - TSE | 1 | 2026-05-04 | 2026-05-05 |  |  | FALSE | yes
| JD3RMRC14TSE59798 | Backfilling Worksfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - C - 14 - TSE | 1 | 2026-05-24 | 2026-05-25 |  |  | FALSE | yes
| JD3RMRC15ST300 | Riprap with side slopes 1.5:1 for Swales - NB6.31 22 00.16 - MR - C - 15 - ST | 1 | 2026-03-22 | 2026-04-12 | 2025-09-14 |  | FALSE | yes
| JD3RMRC15ST60055 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - C - 15 - ST | 1 | 2026-04-23 | 2026-04-25 |  |  | FALSE | yes
| JD3RMRC15ST60056 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - C - 15 | 1 | 2026-04-26 | 2026-04-27 |  |  | FALSE | yes
| JD3RMRC15ST60057 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - C - 15 - ST | 1 | 2026-04-28 | 2026-04-29 |  |  | FALSE | yes
| JD3RMRC15ST60058 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - C - 15 - ST | 1 | 2026-04-30 | 2026-05-02 |  |  | FALSE | yes
| JD3RMRC15ST60059 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - C - 15 - ST | 1 | 2026-05-03 | 2026-05-04 |  |  | FALSE | yes
| JD3RMRC15ST60085 | Excavation Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - C - 15 - ST | 1 | 2026-04-13 | 2026-04-14 |  |  | FALSE | yes
| JD3RMRC15ST60086 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - C - 15 - | 1 | 2026-04-15 | 2026-04-16 |  |  | FALSE | yes
| JD3RMRC15ST60087 | Installing for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - C - 15 - ST | 1 | 2026-04-18 | 2026-04-19 |  |  | FALSE | yes
| JD3RMRC15ST60088 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - C - 15 - ST | 1 | 2026-04-20 | 2026-04-21 |  |  | FALSE | yes
| JD3RMRC15ST60089 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - C - 15 - ST | 1 | 2026-04-22 | 2026-04-23 |  |  | FALSE | yes
| JD3RMRC15ST60163 | Primary Test for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 15 - ST | 1 | 2026-04-26 | 2026-04-28 | 2025-08-26 |  | FALSE | yes
| JD3RMRC15ST60164 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - C - 15 - ST | 1 | 2026-04-29 | 2026-05-03 | 2025-08-28 |  | FALSE | yes
| JD3RMRC15ST60263 | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 15 - ST | 1 | 2026-04-19 | 2026-04-20 |  |  | FALSE | yes
| JD3RMRC15ST60264 | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 15 - ST | 1 | 2026-04-21 | 2026-04-22 |  |  | FALSE | yes
| JD3RMRC15ST60265 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 15 - ST | 1 | 2026-04-23 | 2026-04-25 |  |  | FALSE | yes
| JD3RMRC15ST60266 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 15 - ST | 1 | 2026-04-26 | 2026-04-27 |  |  | FALSE | yes
| JD3RMRC15ST60267 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - C - 15 - ST | 1 | 2026-04-28 | 2026-04-29 |  |  | FALSE | yes
| JD3RMRC15ST60273 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - MR - C - 15 - ST | 1 | 2026-04-21 | 2026-04-22 |  |  | FALSE | yes
| JD3RMRC15ST60274 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - MR - C - 15 - ST | 1 | 2026-04-23 | 2026-04-25 |  |  | FALSE | yes
| JD3RMRC15ST60275 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - MR - C - 15 - ST | 1 | 2026-04-26 | 2026-04-27 |  |  | FALSE | yes
| JD3RMRC15ST60276 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - MR - C - 15 - ST | 1 | 2026-04-28 | 2026-04-29 |  |  | FALSE | yes
| JD3RMRC15SUR01 | Surveying Works C - 15 | 1 |  |  |  |  | yes | FALSE
| JD3RMRC15TSE60371 | Excavation Worksfor HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 15 - TSE | 1 | 2026-05-10 | 2026-05-11 |  |  | FALSE | yes
| JD3RMRC15TSE60372 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 15 - TSE | 1 | 2026-05-12 | 2026-05-13 |  |  | FALSE | yes
| JD3RMRC15TSE60373 | Installing for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 15 - TSE | 1 | 2026-05-14 | 2026-05-16 |  |  | FALSE | yes
| JD3RMRC15TSE60374 | Testing for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 15 - TSE | 1 | 2026-05-17 | 2026-05-18 |  |  | FALSE | yes
| JD3RMRC15TSE60375 | Backfillingfor HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - C - 15 - TSE | 1 | 2026-05-30 | 2026-05-31 |  |  | FALSE | yes
| JD3RMRC15TSE60376 | Excavation Worksfor HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - MR - C - 15 - TSE | 1 | 2026-05-12 | 2026-05-13 |  |  | FALSE | yes
| JD3RMRC15TSE60377 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - MR - C - 15 - TSE | 1 | 2026-05-14 | 2026-05-16 |  |  | FALSE | yes
| JD3RMRC15TSE60378 | Installing for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - MR - C - 15 - TSE | 1 | 2026-05-17 | 2026-05-18 |  |  | FALSE | yes
| JD3RMRC15TSE60379 | Testing for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - MR - C - 15 - TSE | 1 | 2026-05-19 | 2026-05-20 |  |  | FALSE | yes
| JD3RMRC15TSE60380 | Backfillingfor HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - MR - C - 15 - TSE | 1 | 2026-05-27 | 2026-05-28 |  |  | FALSE | yes
| JD3RMRC15TSE60458 | Installationfor gate valves 250 mm - B4.33 14 19.02 - MR - C - 15 - TSE | 1 | 2026-05-23 | 2026-05-24 |  |  | FALSE | yes
| JD3RMRC15TSE60459 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - MR - C - 15 - TSE | 1 | 2026-05-25 | 2026-05-26 |  |  | FALSE | yes
| JD3RMRC15TSE60462 | Installationfor butterfly valves 400 mm. - B4.33 14 19.04 - MR - C - 15 - TSE | 1 | 2026-05-23 | 2026-05-24 |  |  | FALSE | yes
| JD3RMRC15TSE60463 | Testing And Commtionningfor butterfly valves 400 mm. - B4.33 14 19.04 - MR - C - 15 - TSE | 1 | 2026-05-25 | 2026-05-26 |  |  | FALSE | yes
| JD3RMRC15TSE60470 | Installationfor Wash - Out valves 150 mm. - on pipes with diameter 450 - 630 mm - B4.33 14 19.08 - MR - C - 15 - TSE | 1 | 2026-05-23 | 2026-05-24 |  |  | FALSE | yes
| JD3RMRC15TSE60471 | Testing And Commtionningfor Wash - Out valves 150 mm. - on pipes with diameter 450 - 630 mm - B4.33 14 19.08 - MR - C - | 1 | 2026-05-25 | 2026-05-26 |  |  | FALSE | yes
| JD3RMRC15TSE60476 | Installationfor Air valves 65 mm. - on pipes with diameter 355 - 630 mm - B4.33 14 19.16 - MR - C - 15 - TSE | 1 | 2026-05-23 | 2026-05-24 |  |  | FALSE | yes
| JD3RMRC15TSE60477 | Testing And Commtionningfor Air valves 65 mm. - on pipes with diameter 355 - 630 mm - B4.33 14 19.16 - MR - C - 15 - TSE | 1 | 2026-05-25 | 2026-05-26 |  |  | FALSE | yes
| JD3RMRC15TSE60480 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - C - 15 - TSE | 1 | 2026-05-14 | 2026-05-16 |  |  | FALSE | yes
| JD3RMRC15TSE60481 | Plain Concrete Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - C - 15 - TSE | 1 | 2026-05-17 | 2026-05-18 |  |  | FALSE | yes
| JD3RMRC15TSE60482 | INSTALLATIONfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - C - 15 - TSE | 1 | 2026-05-19 | 2026-05-20 |  |  | FALSE | yes
| JD3RMRC15TSE60483 | Backfilling Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - C - 15 - TSE | 1 | 2026-05-21 | 2026-05-23 |  |  | FALSE | yes
| JD3RMRC15TSE60496 | EXCAVATION and Bedding Worksfor Wash - out Valve Chamber - 450 to 630 MM - B4.33 14 13.07 - MR - C - 15 - TSE | 1 | 2026-05-17 | 2026-05-18 |  |  | FALSE | yes
| JD3RMRC15TSE60497 | Plain Concrete Worksfor Wash - out Valve Chamber - 450 to 630 MM - B4.33 14 13.07 - MR - C - 15 - TSE | 1 | 2026-05-19 | 2026-05-20 |  |  | FALSE | yes
| JD3RMRC15TSE60498 | INSTALLATIONfor Wash - out Valve Chamber - 450 to 630 MM - B4.33 14 13.07 - MR - C - 15 - TSE | 1 | 2026-05-21 | 2026-05-23 |  |  | FALSE | yes
| JD3RMRC15TSE60499 | Backfilling Worksfor Wash - out Valve Chamber - 450 to 630 MM - B4.33 14 13.07 - MR - C - 15 - TSE | 1 | 2026-05-24 | 2026-05-25 |  |  | FALSE | yes
| JD3RMRC15TSE60508 | EXCAVATION and Bedding Worksfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - C - 15 - TSE | 1 | 2026-05-19 | 2026-05-20 |  |  | FALSE | yes
| JD3RMRC15TSE60509 | Plain Concrete Worksfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - C - 15 - TSE | 1 | 2026-05-21 | 2026-05-23 |  |  | FALSE | yes
| JD3RMRC15TSE60510 | INSTALLATIONfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - C - 15 - TSE | 1 | 2026-05-24 | 2026-05-25 |  |  | FALSE | yes
| JD3RMRC15TSE60511 | Backfilling Worksfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - C - 15 - TSE | 1 | 2026-05-26 | 2026-05-27 |  |  | FALSE | yes
| JD3RMRC15WT60281 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - MR - C - 15 - WT | 1 | 2026-05-28 | 2026-05-30 |  |  | FALSE | yes
| JD3RMRC15WT60282 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - MR - C - 15 - WT | 1 | 2026-05-31 | 2026-06-01 |  |  | FALSE | yes
| JD3RMRC15WT60283 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - MR - C - 15 - WT | 1 | 2026-06-02 | 2026-06-03 |  |  | FALSE | yes
| JD3RMRC15WT60284 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - MR - C - 15 - WT | 1 | 2026-06-04 | 2026-06-06 |  |  | FALSE | yes
| JD3RMRC15WT60285 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - MR - C - 15 - WT | 1 | 2026-06-07 | 2026-06-08 |  |  | FALSE | yes
| JD3RMRC15WT60290 | Backfillingfor HDPE Pipes 225 mm - depth from 0 to 1.5 m - B3.33 14 13.02 - MR - C - 15 - WT | 1 | 2026-06-29 | 2026-07-05 |  |  | FALSE | yes
| JD3RMRC15WT60308 | INSTALLATIONfor gate valves 200 mm - B3.33 14 19.02 - MR - C - 15 - WT | 1 | 2026-06-22 | 2026-06-23 |  |  | FALSE | yes
| JD3RMRC15WT60309 | TESTING AND COMMITIONfor gate valves 200 mm - B3.33 14 19.02 - MR - C - 15 - WT | 1 | 2026-06-24 | 2026-06-25 |  |  | FALSE | yes
| JD3RMRC15WT60316 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - MR - C - 15 - WT | 1 | 2026-06-06 | 2026-06-07 |  |  | FALSE | yes
| JD3RMRC15WT60317 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - MR - C - 15 - WT | 1 | 2026-06-08 | 2026-06-09 |  |  | FALSE | yes
| JD3RMRC15WT60318 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - MR - C - 15 - WT | 1 | 2026-06-27 | 2026-06-28 |  |  | FALSE | yes
| JD3RMRL01SL61289 | Installation of reinforced concrete foundationfor LIGHTING POLE one arm - B2.26 56 19.02 - MR - L - 01 - SL | 1 | 2026-05-21 | 2026-05-26 | 2025-10-23 |  | FALSE | yes
| JD3RMRL01SL61290 | Backfilling of reinforced concrete foundationfor LIGHTING POLE one arm - B2.26 56 19.02 - MR - L - 01 - SL | 1 | 2026-05-27 | 2026-05-31 |  |  | FALSE | yes
| JD3RMRL01SL61291 | Installation Worksfor LIGHTING POLE one arm - B2.26 56 19.02 - MR - L - 01 - SL | 1 | 2026-06-01 | 2026-06-11 | 2025-10-23 |  | FALSE | yes
| JD3RMRL01SL61292 | Testing and Commitioningfor LIGHTING POLE one arm - B2.26 56 19.02 - MR - L - 01 - SL | 1 | 2026-06-13 | 2026-06-23 |  |  | FALSE | yes
| JD3RMRL01SL61293 | Installationfor Lighting( LED ) Luminaire 150 WATT - B2.26.56.19.01 - MR - L - 01 - SL | 1 | 2026-05-27 | 2026-05-31 |  |  | FALSE | yes
| JD3RMRL01SL61296 | Supply, construct, connect and test earthing pitsfor Street Lighting EARTHING SYSTEM - B2.26 05 26.01 - MR - L - 01 - SL | 1 | 2026-06-01 | 2026-06-02 |  |  | FALSE | yes
| JD3RMRL01SL61301 | Excavation Worksfor PVC Pipes 4×150mm - B2.33 71 19.02 - MR - L - 01 - SL | 1 | 2026-05-17 | 2026-05-18 |  |  | FALSE | yes
| JD3RMRL01SL61302 | Installationfor PVC Pipes 4×150mm - B2.33 71 19.02 - MR - L - 01 - SL | 1 | 2026-05-19 | 2026-05-20 |  |  | FALSE | yes
| JD3RMRL01SL61303 | Pouring Concrete Coverfor PVC Pipes 4×150mm - B2.33 71 19.02 - MR - L - 01 - SL | 1 | 2026-05-21 | 2026-05-23 |  |  | FALSE | yes
| JD3RMRL01SL61304 | Testing and Backfilling Worksfor PVC Pipes 4×150mm - B2.33 71 19.02 - MR - L - 01 - SL | 1 | 2026-06-03 | 2026-06-04 |  |  | FALSE | yes
| JD3RMRL01SL61309 | Excavationfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - MR - L - 01 - SL | 1 | 2026-05-17 | 2026-05-20 | 2025-10-23 |  | FALSE | yes
| JD3RMRL01SL61310 | Installationfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - MR - L - 01 - SL | 1 | 2026-05-21 | 2026-05-26 | 2025-10-23 |  | FALSE | yes
| JD3RMRL01SL61311 | Backfillingfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - MR - L - 01 - SL | 1 | 2026-05-27 | 2026-05-31 |  |  | FALSE | yes
| JD3RMRL01SL61312 | Excavationfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - MR - L - 01 - SL | 1 | 2026-05-17 | 2026-05-18 |  |  | FALSE | yes
| JD3RMRL01SL61313 | Installationfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - MR - L - 01 - SL | 1 | 2026-05-19 | 2026-05-20 |  |  | FALSE | yes
| JD3RMRL01SL61314 | Backfillingfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - MR - L - 01 - SL | 1 | 2026-05-21 | 2026-05-23 |  |  | FALSE | yes
| JD3RMRL01ST524344 | Concrete encasement for pipes - NNB6.33 42 11.25 - MR - L - 01 - ST | 1 | 2025-12-13 | 2025-12-31 |  |  | FALSE | yes
| JD3RMRL01ST60768 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - L - 01 - ST | 1 | 2025-11-23 | 2025-11-25 |  |  | FALSE | yes
| JD3RMRL01ST60769 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - L - 01 | 1 | 2025-11-26 | 2025-11-30 |  |  | FALSE | yes
| JD3RMRL01ST60770 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - L - 01 - ST | 1 | 2025-12-01 | 2025-12-06 |  |  | FALSE | yes
| JD3RMRL01ST60771 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - L - 01 - ST | 1 | 2025-12-07 | 2025-12-11 |  |  | FALSE | yes
| JD3RMRL01ST60772 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - L - 01 - ST | 1 | 2026-01-01 | 2026-01-07 |  |  | FALSE | yes
| JD3RMRL01ST60773 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - MR - L - 01 - ST | 1 | 2025-11-26 | 2025-11-27 |  |  | FALSE | yes
| JD3RMRL01ST60774 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - MR - L - 01 - | 1 | 2025-11-29 | 2025-11-30 |  |  | FALSE | yes
| JD3RMRL01ST60775 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - MR - L - 01 - ST | 1 | 2025-12-01 | 2025-12-02 |  |  | FALSE | yes
| JD3RMRL01ST60776 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - MR - L - 01 - ST | 1 | 2025-12-03 | 2025-12-04 |  |  | FALSE | yes
| JD3RMRL01ST60777 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - MR - L - 01 - ST | 1 | 2026-01-01 | 2026-01-03 |  |  | FALSE | yes
| JD3RMRL01ST60778 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - MR - L - 01 - ST | 1 | 2025-11-26 | 2025-11-30 | 2025-08-05 |  | FALSE | yes
| JD3RMRL01ST60779 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - MR - L - 01 - | 1 | 2025-12-01 | 2025-12-04 | 2025-08-10 |  | FALSE | yes
| JD3RMRL01ST60780 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - MR - L - 01 - ST | 1 | 2025-12-06 | 2025-12-09 | 2025-08-15 |  | FALSE | yes
| JD3RMRL01ST60781 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - MR - L - 01 - ST | 1 | 2025-12-10 | 2025-12-14 |  |  | FALSE | yes
| JD3RMRL01ST60782 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - MR - L - 01 - ST | 1 | 2026-01-01 | 2026-01-06 | 2025-09-20 |  | FALSE | yes
| JD3RMRL01ST60791 | Primary Test for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - MR - L - 01 - ST | 1 | 2025-12-03 | 2025-12-04 |  |  | FALSE | yes
| JD3RMRL01ST60796 | Primary Test for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m - B6.33 42 11.05 - MR - L - 01 - ST | 1 | 2025-12-10 | 2025-12-11 |  |  | FALSE | yes
| JD3RMRL01ST60797 | Backfilling Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m - B6.33 42 11.05 - MR - L - 01 - ST | 1 | 2026-01-01 | 2026-01-03 | 2025-09-20 |  | FALSE | yes
| JD3RMRL01ST60801 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - L - 01 - ST | 1 | 2025-12-13 | 2025-12-14 |  |  | FALSE | yes
| JD3RMRL01ST60811 | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - MR - L - 01 - ST | 1 | 2025-12-18 | 2025-12-21 |  |  | FALSE | yes
| JD3RMRL01ST60812 | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - MR - L - 01 - ST | 1 | 2025-12-22 | 2025-12-25 |  |  | FALSE | yes
| JD3RMRL01ST60821 | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - MR - L - 01 - ST | 1 | 2025-12-20 | 2025-12-21 |  |  | FALSE | yes
| JD3RMRL01ST60822 | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - MR - L - 01 - ST | 1 | 2025-12-22 | 2025-12-24 |  |  | FALSE | yes
| JD3RMRL01ST60831 | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - MR - L - 01 - ST | 1 | 2025-12-21 | 2025-12-22 |  |  | FALSE | yes
| JD3RMRL01ST60832 | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - MR - L - 01 - ST | 1 | 2025-12-23 | 2025-12-24 | 2025-09-17 |  | FALSE | yes
| JD3RMRL01ST60846 | Primary Test for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m - B6.33 42 11.15 - MR - L - 01 - ST | 1 | 2025-12-23 | 2025-12-24 |  |  | FALSE | yes
| JD3RMRL01ST60851 | Primary Test for GRP Pipe Line 1000 mm - depth from 2.51 to 3.50 m - B6.33 42 11.16 - MR - L - 01 - ST | 1 | 2025-12-25 | 2025-12-27 |  |  | FALSE | yes
| JD3RMRL01ST60852 | Backfilling Works for GRP Pipe Line 1000 mm - depth from 2.51 to 3.50 m - B6.33 42 11.16 - MR - L - 01 - ST | 1 | 2025-12-28 | 2025-12-29 |  |  | FALSE | yes
| JD3RMRL01ST60860 | Installing for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m - B6.33 42 11.20 - MR - L - 01 - ST | 1 | 2025-12-25 | 2025-12-27 | 2025-08-26 |  | FALSE | yes
| JD3RMRL01ST60861 | Primary Test for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m - B6.33 42 11.20 - MR - L - 01 - ST | 1 | 2025-12-28 | 2025-12-29 |  |  | FALSE | yes
| JD3RMRL01ST60862 | Backfilling Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m - B6.33 42 11.20 - MR - L - 01 - ST | 1 | 2025-12-30 | 2026-01-01 | 2025-09-16 |  | FALSE | yes
| JD3RMRL01ST60881 | Primary Test for GRP Pipe Line 1200 mm - depth from 2.51 to 3.50 m - B6.33 42 11.24 - MR - L - 01 - ST | 1 | 2025-12-30 | 2025-12-31 |  |  | FALSE | yes
| JD3RMRL01ST60882 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 2.51 to 3.50 m - B6.33 42 11.24 - MR - L - 01 - ST | 1 | 2026-01-01 | 2026-01-03 |  |  | FALSE | yes
| JD3RMRL01ST60951 | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - MR - L - 01 - ST | 1 | 2025-12-25 | 2025-12-27 | 2025-08-22 |  | FALSE | yes
| JD3RMRL01ST60952 | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - MR - L - 01 - ST | 1 | 2025-12-28 | 2025-12-30 | 2025-08-24 |  | FALSE | yes
| JD3RMRL01ST60953 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - MR - L - 01 - ST | 1 | 2025-12-31 | 2026-01-03 | 2025-08-26 |  | FALSE | yes
| JD3RMRL01ST60954 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - MR - L - 01 - ST | 1 | 2026-01-04 | 2026-01-05 |  |  | FALSE | yes
| JD3RMRL01ST60955 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - MR - L - 01 - ST | 1 | 2026-01-06 | 2026-01-07 |  |  | FALSE | yes
| JD3RMRL01ST60961 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - L - 01 - ST | 1 | 2025-12-28 | 2025-12-29 | 2025-08-22 |  | FALSE | yes
| JD3RMRL01ST60962 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - L - 01 - ST | 1 | 2025-12-30 | 2025-12-31 | 2025-08-24 |  | FALSE | yes
| JD3RMRL01ST60963 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - L - 01 - ST | 1 | 2026-01-01 | 2026-01-03 | 2025-08-26 |  | FALSE | yes
| JD3RMRL01ST60964 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - L - 01 - ST | 1 | 2026-01-04 | 2026-01-05 |  |  | FALSE | yes
| JD3RMRL01ST60965 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - L - 01 - ST | 1 | 2026-01-06 | 2026-01-07 |  |  | FALSE | yes
| JD3RMRL01ST60966 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - L - 01 - ST | 1 | 2025-12-30 | 2025-12-31 |  |  | FALSE | yes
| JD3RMRL01ST60967 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - L - 01 - ST | 1 | 2026-01-01 | 2026-01-03 |  |  | FALSE | yes
| JD3RMRL01ST60968 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - L - 01 - ST | 1 | 2026-01-04 | 2026-01-05 |  |  | FALSE | yes
| JD3RMRL01ST60969 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - L - 01 - ST | 1 | 2026-01-06 | 2026-01-07 |  |  | FALSE | yes
| JD3RMRL01ST60970 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - L - 01 - ST | 1 | 2026-01-08 | 2026-01-10 |  |  | FALSE | yes
| JD3RMRL01ST60981 | Excavation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - MR - L - 01 - ST | 1 | 2026-01-01 | 2026-01-03 |  |  | FALSE | yes
| JD3RMRL01ST60982 | Base Plain Concrete Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - MR - L - 01 - ST | 1 | 2026-01-04 | 2026-01-05 |  |  | FALSE | yes
| JD3RMRL01ST60983 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - MR - L - 01 - ST | 1 | 2026-01-06 | 2026-01-07 |  |  | FALSE | yes
| JD3RMRL01ST60984 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - MR - L - 01 - ST | 1 | 2026-01-08 | 2026-01-10 |  |  | FALSE | yes
| JD3RMRL01ST60985 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - MR - L - 01 - ST | 1 | 2026-01-11 | 2026-01-12 |  |  | FALSE | yes
| JD3RMRL01ST60986 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - MR - L - 01 - ST | 1 | 2026-01-04 | 2026-01-07 |  |  | FALSE | yes
| JD3RMRL01ST60987 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - MR - L - 01 - ST | 1 | 2026-01-08 | 2026-01-14 |  |  | FALSE | yes
| JD3RMRL01ST60988 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - MR - L - 01 - ST | 1 | 2026-01-15 | 2026-01-21 |  |  | FALSE | yes
| JD3RMRL01ST60989 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - MR - L - 01 - ST | 1 | 2026-01-22 | 2026-01-26 |  |  | FALSE | yes
| JD3RMRL01ST60990 | EXCAVATION Works for Catchbasine double - B6.33 05 39.10 - MR - L - 01 - ST | 1 | 2026-01-08 | 2026-01-12 |  |  | FALSE | yes
| JD3RMRL01ST60991 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - MR - L - 01 - ST | 1 | 2026-01-13 | 2026-01-18 |  |  | FALSE | yes
| JD3RMRL01ST60992 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - MR - L - 01 - ST | 1 | 2026-01-19 | 2026-01-24 |  |  | FALSE | yes
| JD3RMRL01ST60993 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - MR - L - 01 - ST | 1 | 2026-01-25 | 2026-01-28 |  |  | FALSE | yes
| JD3RMRL01TSE61044 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - L - 01 - TSE | 1 | 2026-01-29 | 2026-02-01 |  |  | FALSE | yes
| JD3RMRL01TSE61045 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - L - 01 - TS | 1 | 2026-02-02 | 2026-02-04 |  |  | FALSE | yes
| JD3RMRL01TSE61046 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - L - 01 - TSE | 1 | 2026-02-05 | 2026-02-11 |  |  | FALSE | yes
| JD3RMRL01TSE61047 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - L - 01 - TSE | 1 | 2026-02-12 | 2026-02-16 |  |  | FALSE | yes
| JD3RMRL01TSE61048 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - L - 01 - TSE | 1 | 2026-02-17 | 2026-02-21 |  |  | FALSE | yes
| JD3RMRL01TSE61049.R | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - L - 01 - TSE - Remaining | 1 | 2026-02-19 | 2026-02-21 | 2025-08-14 |  | FALSE | yes
| JD3RMRL01TSE61050.R | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - L - 01 - TS | 1 | 2026-03-11 | 2026-03-12 | 2025-08-16 |  | FALSE | yes
| JD3RMRL01TSE61051.R | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - L - 01 - TSE - Remaining | 1 | 2026-03-29 | 2026-03-30 | 2025-08-28 |  | FALSE | yes
| JD3RMRL01TSE61052.R | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - L - 01 - TSE - Remaining | 1 | 2026-04-21 | 2026-04-22 |  |  | FALSE | yes
| JD3RMRL01TSE61053.R | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - L - 01 - TSE - Remaining | 1 | 2026-05-14 | 2026-05-16 | 2025-08-23 |  | FALSE | yes
| JD3RMRL01TSE61054.R | Excavation Worksfor HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - L - 01 - TSE - Remaining | 1 | 2026-02-22 | 2026-02-23 |  |  | FALSE | yes
| JD3RMRL01TSE61055.R | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - L - 01 - TSE - | 1 | 2026-02-24 | 2026-02-25 |  |  | FALSE | yes
| JD3RMRL01TSE61056.R | Installing for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - L - 01 - TSE - Remaining | 1 | 2026-02-28 | 2026-03-01 |  |  | FALSE | yes
| JD3RMRL01TSE61057 | Testing for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - L - 01 - TSE | 1 | 2026-03-02 | 2026-03-03 |  |  | FALSE | yes
| JD3RMRL01TSE61058 | Backfillingfor HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - L - 01 - TSE | 1 | 2026-04-12 | 2026-04-13 |  |  | FALSE | yes
| JD3RMRL01TSE61059 | Excavation Worksfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - MR - L - 01 - TSE | 1 | 2026-02-24 | 2026-02-25 |  |  | FALSE | yes
| JD3RMRL01TSE61060 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - MR - L - 01 - TSE | 1 | 2026-02-26 | 2026-02-28 |  |  | FALSE | yes
| JD3RMRL01TSE61061 | Installing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - MR - L - 01 - TSE | 1 | 2026-03-01 | 2026-03-02 |  |  | FALSE | yes
| JD3RMRL01TSE61062 | Testing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - MR - L - 01 - TSE | 1 | 2026-03-03 | 2026-03-04 |  |  | FALSE | yes
| JD3RMRL01TSE61063 | Backfillingfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - MR - L - 01 - TSE | 1 | 2026-04-12 | 2026-04-13 |  |  | FALSE | yes
| JD3RMRL01TSE61084 | Excavation Worksfor HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - L - 01 - TSE | 1 | 2026-01-29 | 2026-01-31 |  |  | FALSE | yes
| JD3RMRL01TSE61085 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - L - 01 - TSE | 1 | 2026-02-01 | 2026-02-02 |  |  | FALSE | yes
| JD3RMRL01TSE61086 | Installing for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - L - 01 - TSE | 1 | 2026-02-03 | 2026-02-07 |  |  | FALSE | yes
| JD3RMRL01TSE61087 | Testing for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - L - 01 - TSE | 1 | 2026-02-08 | 2026-02-10 |  |  | FALSE | yes
| JD3RMRL01TSE61088 | Backfillingfor HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - L - 01 - TSE | 1 | 2026-04-12 | 2026-04-14 |  |  | FALSE | yes
| JD3RMRL01TSE61089 | Excavation Worksfor HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - MR - L - 01 - TSE | 1 | 2026-01-29 | 2026-02-04 |  |  | FALSE | yes
| JD3RMRL01TSE61090 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - MR - L - 01 - TSE | 1 | 2026-02-05 | 2026-02-11 |  |  | FALSE | yes
| JD3RMRL01TSE61091 | Installing for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - MR - L - 01 - TSE | 1 | 2026-02-12 | 2026-02-24 |  |  | FALSE | yes
| JD3RMRL01TSE61092 | Testing for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - MR - L - 01 - TSE | 1 | 2026-02-25 | 2026-03-05 |  |  | FALSE | yes
| JD3RMRL01TSE61093 | Backfillingfor HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - MR - L - 01 - TSE | 1 | 2026-03-07 | 2026-03-15 |  |  | FALSE | yes
| JD3RMRL01TSE61114 | Excavation Worksfor HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - L - 01 - TSE | 1 | 2026-01-29 | 2026-01-31 |  |  | FALSE | yes
| JD3RMRL01TSE61115 | Soil Replacement and Bedding Works for HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - L - 01 - TSE | 1 | 2026-02-01 | 2026-02-02 |  |  | FALSE | yes
| JD3RMRL01TSE61116 | Installing for HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - L - 01 - TSE | 1 | 2026-02-03 | 2026-02-04 |  |  | FALSE | yes
| JD3RMRL01TSE61117 | Testing for HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - L - 01 - TSE | 1 | 2026-02-05 | 2026-02-07 |  |  | FALSE | yes
| JD3RMRL01TSE61118 | Backfillingfor HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - L - 01 - TSE | 1 | 2026-02-08 | 2026-02-09 |  |  | FALSE | yes
| JD3RMRL01TSE61169 | Installationfor gate valves 100 mm - B4.33 14 19.01 - MR - L - 01 - TSE | 1 | 2026-03-31 | 2026-04-05 |  |  | FALSE | yes
| JD3RMRL01TSE61170 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - MR - L - 01 - TSE | 1 | 2026-04-06 | 2026-04-11 |  |  | FALSE | yes
| JD3RMRL01TSE61171 | Installationfor gate valves 250 mm - B4.33 14 19.02 - MR - L - 01 - TSE | 1 | 2026-03-31 | 2026-04-04 |  |  | FALSE | yes
| JD3RMRL01TSE61172 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - MR - L - 01 - TSE | 1 | 2026-04-05 | 2026-04-08 |  |  | FALSE | yes
| JD3RMRL01TSE61173 | Installationfor butterfly valves 300 mm. - B4.33 14 19.03 - MR - L - 01 - TSE | 1 | 2026-03-31 | 2026-04-01 |  |  | FALSE | yes
| JD3RMRL01TSE61174 | Testing And Commtionningfor butterfly valves 300 mm. - B4.33 14 19.03 - MR - L - 01 - TSE | 1 | 2026-04-02 | 2026-04-04 |  |  | FALSE | yes
| JD3RMRL01TSE61175 | Installationfor butterfly valves 400 mm. - B4.33 14 19.04 - MR - L - 01 - TSE | 1 | 2026-03-31 | 2026-04-01 |  |  | FALSE | yes
| JD3RMRL01TSE61176 | Testing And Commtionningfor butterfly valves 400 mm. - B4.33 14 19.04 - MR - L - 01 - TSE | 1 | 2026-04-02 | 2026-04-04 |  |  | FALSE | yes
| JD3RMRL01TSE61181 | Installationfor Wash - Out valves 100 mm. - on pipes with diameter 110 - 400 mm - B4.33 14 19.07 - MR - L - 01 - TSE | 1 | 2026-03-31 | 2026-04-01 |  |  | FALSE | yes
| JD3RMRL01TSE61182 | Testing And Commtionningfor Wash - Out valves 100 mm. - on pipes with diameter 110 - 400 mm - B4.33 14 19.07 - MR - L - | 1 | 2026-04-02 | 2026-04-04 |  |  | FALSE | yes
| JD3RMRL01TSE61187 | Installationfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - MR - L - 01 - TSE | 1 | 2026-03-31 | 2026-04-01 |  |  | FALSE | yes
| JD3RMRL01TSE61188 | Testing And Commtionningfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - MR - L - 01 - | 1 | 2026-04-02 | 2026-04-04 |  |  | FALSE | yes
| JD3RMRL01TSE61189 | Installationfor Air valves 65 mm. - on pipes with diameter 355 - 630 mm - B4.33 14 19.16 - MR - L - 01 - TSE | 1 | 2026-03-31 | 2026-04-01 |  |  | FALSE | yes
| JD3RMRL01TSE61190 | Testing And Commtionningfor Air valves 65 mm. - on pipes with diameter 355 - 630 mm - B4.33 14 19.16 - MR - L - 01 - TSE | 1 | 2026-04-02 | 2026-04-04 |  |  | FALSE | yes
| JD3RMRL01TSE61193 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - L - 01 - TSE | 1 | 2026-01-29 | 2026-01-31 |  |  | FALSE | yes
| JD3RMRL01TSE61194 | Plain Concrete Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - L - 01 - TSE | 1 | 2026-02-01 | 2026-02-02 |  |  | FALSE | yes
| JD3RMRL01TSE61195 | INSTALLATIONfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - L - 01 - TSE | 1 | 2026-02-03 | 2026-02-04 |  |  | FALSE | yes
| JD3RMRL01TSE61196 | Backfilling Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - L - 01 - TSE | 1 | 2026-02-05 | 2026-02-07 |  |  | FALSE | yes
| JD3RMRL01TSE61205 | EXCAVATION and Bedding Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - L - 01 - TSE | 1 | 2026-01-29 | 2026-01-31 |  |  | FALSE | yes
| JD3RMRL01TSE61206 | Plain Concrete Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - L - 01 - TSE | 1 | 2026-02-01 | 2026-02-02 |  |  | FALSE | yes
| JD3RMRL01TSE61207 | INSTALLATIONfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - L - 01 - TSE | 1 | 2026-02-03 | 2026-02-04 |  |  | FALSE | yes
| JD3RMRL01TSE61208 | Backfilling Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - L - 01 - TSE | 1 | 2026-02-05 | 2026-02-07 |  |  | FALSE | yes
| JD3RMRL01TSE61217 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - L - 01 - TSE | 1 | 2026-01-29 | 2026-01-31 |  |  | FALSE | yes
| JD3RMRL01TSE61218 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - L - 01 - TSE | 1 | 2026-02-01 | 2026-02-02 |  |  | FALSE | yes
| JD3RMRL01TSE61219 | INSTALLATIONfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - L - 01 - TSE | 1 | 2026-02-03 | 2026-02-04 |  |  | FALSE | yes
| JD3RMRL01TSE61220 | Backfilling Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - L - 01 - TSE | 1 | 2026-02-05 | 2026-02-07 |  |  | FALSE | yes
| JD3RMRL01TSE61221 | EXCAVATION and Bedding Worksfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - L - 01 - TSE | 1 | 2026-01-29 | 2026-01-31 |  |  | FALSE | yes
| JD3RMRL01TSE61222 | Plain Concrete Worksfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - L - 01 - TSE | 1 | 2026-02-01 | 2026-02-02 |  |  | FALSE | yes
| JD3RMRL01TSE61223 | INSTALLATIONfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - L - 01 - TSE | 1 | 2026-02-03 | 2026-02-04 |  |  | FALSE | yes
| JD3RMRL01TSE61224 | Backfilling Worksfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - L - 01 - TSE | 1 | 2026-02-05 | 2026-02-07 |  |  | FALSE | yes
| JD3RMRL03SS61352 | Installing for GRP Pipe Line 200 mm - depth from 0.00 to 1.50 - B5.33 31 00.03 - MR - L - 03 - SS | 1 | 2025-09-08 | 2025-09-09 |  |  | FALSE | yes
| JD3RMRL03SS61353 | Primary Test for GRP Pipe Line 200 mm - depth from 0.00 to 1.50 - B5.33 31 00.03 - MR - L - 03 - SS | 1 | 2025-09-10 | 2025-09-11 |  |  | FALSE | yes
| JD3RMRL03SS61354 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - depth from 0.00 to 1.50 - B5.33 31 00.03 - MR - L - 03 - S | 1 | 2025-09-13 | 2025-09-14 |  |  | FALSE | yes
| JD3RMRL03SS61355 | Trench excavation for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - MR - L - 03 - SS | 1 | 2025-09-06 | 2025-09-11 | 2025-10-25 |  | FALSE | FALSE
| JD3RMRL03SS61356 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - MR - L - 03 - S | 1 | 2025-09-15 | 2025-09-21 | 2025-10-25 |  | FALSE | FALSE
| JD3RMRL03SS61357 | Installing for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - MR - L - 03 - SS | 1 | 2025-09-22 | 2025-09-29 |  |  | FALSE | yes
| JD3RMRL03SS61358 | Primary Test for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - MR - L - 03 - SS | 1 | 2025-09-30 | 2025-10-06 |  |  | FALSE | yes
| JD3RMRL03SS61359 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - MR - L - 03 - S | 1 | 2025-10-07 | 2025-10-16 |  |  | FALSE | yes
| JD3RMRL03SS61360 | Trench excavation for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - MR - L - 03 - SS | 1 | 2025-09-13 | 2025-09-14 |  |  | FALSE | yes
| JD3RMRL03SS61361 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - MR - L - 03 - S | 1 | 2025-09-15 | 2025-09-16 |  |  | FALSE | yes
| JD3RMRL03SS61362 | Installing for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - MR - L - 03 - SS | 1 | 2025-09-17 | 2025-09-20 |  |  | FALSE | yes
| JD3RMRL03SS61363 | Primary Test for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - MR - L - 03 - SS | 1 | 2025-09-21 | 2025-09-22 |  |  | FALSE | yes
| JD3RMRL03SS61364 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - MR - L - 03 - S | 1 | 2025-09-23 | 2025-09-25 |  |  | FALSE | yes
| JD3RMRL03SS61370 | Trench excavation for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50 - B5.33 31 00.11 - MR - L - 03 - SS | 1 | 2025-09-15 | 2025-09-17 |  |  | FALSE | yes
| JD3RMRL03SS61371 | Soil Replacement and Bedding Works for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50 - B5.33 31 00.11 - MR - L - 03 - S | 1 | 2025-09-18 | 2025-09-21 |  |  | FALSE | yes
| JD3RMRL03SS61372 | Installing for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50 - B5.33 31 00.11 - MR - L - 03 - SS | 1 | 2025-09-22 | 2025-09-24 |  |  | FALSE | yes
| JD3RMRL03SS61373 | Primary Test for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50 - B5.33 31 00.11 - MR - L - 03 - SS | 1 | 2025-09-25 | 2025-09-28 |  |  | FALSE | yes
| JD3RMRL03SS61374 | Backfilling and warning tabe Works for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50 - B5.33 31 00.11 - MR - L - 03 - S | 1 | 2025-09-29 | 2025-10-02 |  |  | FALSE | yes
| JD3RMRL03SS61375 | Trench excavation for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50 - B5.33 31 00.12 - MR - L - 03 - SS | 1 | 2025-09-18 | 2025-09-22 |  |  | FALSE | yes
| JD3RMRL03SS61376 | Soil Replacement and Bedding Works for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50 - B5.33 31 00.12 - MR - L - 03 - S | 1 | 2025-09-23 | 2025-09-27 |  |  | FALSE | yes
| JD3RMRL03SS61377 | Installing for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50 - B5.33 31 00.12 - MR - L - 03 - SS | 1 | 2025-09-28 | 2025-10-02 |  |  | FALSE | yes
| JD3RMRL03SS61378 | Primary Test for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50 - B5.33 31 00.12 - MR - L - 03 - SS | 1 | 2025-10-04 | 2025-10-07 |  |  | FALSE | yes
| JD3RMRL03SS61379 | Backfilling and warning tabe Works for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50 - B5.33 31 00.12 - MR - L - 03 - S | 1 | 2025-10-08 | 2025-10-14 |  |  | FALSE | yes
| JD3RMRL03SS613801 | Trench excavation for GRP Pipe Line 300 mm - Depth from 4.51 to 5.50 - B5.33 31 00.13 - MR - L - 03 - SS | 1 | 2025-09-23 | 2025-09-24 |  |  | FALSE | yes
| JD3RMRL03SS613802 | Trench excavation for GRP Pipe Line 400 mm - Depth from 4.51 to 5.50 - B5.33 31 00.13 - MR - L - 03 - SS | 1 | 2025-09-25 | 2025-09-29 | 2025-10-16 |  | FALSE | FALSE
| JD3RMRL03SS613811 | Soil Replacement and Bedding Works for GRP Pipe Line 300 mm - Depth from 4.51 to 5.50 - B5.33 31 00.13 - MR - L - 03 - S | 1 | 2025-09-25 | 2025-09-27 |  |  | FALSE | yes
| JD3RMRL03SS613812 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - Depth from 4.51 to 5.50 - B5.33 31 00.13 - MR - L - 03 - S | 1 | 2025-09-30 | 2025-10-04 | 2025-10-16 |  | FALSE | FALSE
| JD3RMRL03SS613821 | Installing for GRP Pipe Line 300 mm - Depth from 4.51 to 5.50 - B5.33 31 00.13 - MR - L - 03 - SS | 1 | 2025-09-28 | 2025-09-29 |  |  | FALSE | yes
| JD3RMRL03SS613822 | Installing for GRP Pipe Line 400 mm - Depth from 4.51 to 5.50 - B5.33 31 00.13 - MR - L - 03 - SS | 1 | 2025-10-05 | 2025-10-09 | 2025-10-16 |  | FALSE | FALSE
| JD3RMRL03SS613831 | Primary Test for GRP Pipe Line 300 mm - Depth from 4.51 to 5.50 - B5.33 31 00.13 - MR - L - 03 - SS | 1 | 2025-09-30 | 2025-10-01 |  |  | FALSE | yes
| JD3RMRL03SS613832 | Primary Test for GRP Pipe Line 400 mm - Depth from 4.51 to 5.50 - B5.33 31 00.13 - MR - L - 03 - SS | 1 | 2025-10-11 | 2025-10-14 |  |  | FALSE | yes
| JD3RMRL03SS613841 | Backfilling and warning tabe Works for GRP Pipe Line 300 mm - Depth from 4.51 to 5.50 - B5.33 31 00.13 - MR - L - 03 - S | 1 | 2025-10-02 | 2025-10-05 |  |  | FALSE | yes
| JD3RMRL03SS613842 | Backfilling and warning tabe Works for GRP Pipe Line 400 mm - Depth from 4.51 to 5.50 - B5.33 31 00.13 - MR - L - 03 - S | 1 | 2025-10-18 | 2025-10-23 | 2025-10-16 |  | FALSE | yes
| JD3RMRL03SS61397 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - MR - L - 03 - SS | 1 | 2025-09-30 | 2025-10-01 | 2025-10-25 |  | FALSE | FALSE
| JD3RMRL03SS61398 | Installation of Base Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - MR - L - 03 - SS | 1 | 2025-10-02 | 2025-10-07 | 2025-10-25 |  | FALSE | FALSE
| JD3RMRL03SS61399 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - MR - | 1 | 2025-10-08 | 2025-10-13 | 2025-10-25 |  | FALSE | FALSE
| JD3RMRL03SS61400 | Backfilling Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - MR - L - 03 - SS | 1 | 2025-10-14 | 2025-10-16 |  |  | FALSE | yes
| JD3RMRL03SS61401 | Finishing, Benching Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - MR - L - 03 - SS | 1 | 2025-10-18 | 2025-10-20 |  |  | FALSE | yes
| JD3RMRL03SS61409 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - MR - L - 03 - SS | 1 | 2025-10-25 | 2025-11-02 |  |  | FALSE | yes
| JD3RMRL03SS61410 | Installation of Base Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - MR - L - 03 - SS | 1 | 2025-11-03 | 2025-11-23 |  |  | FALSE | yes
| JD3RMRL03SS61411 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - MR - | 1 | 2025-11-24 | 2025-12-14 |  |  | FALSE | yes
| JD3RMRL03SS61412 | Backfilling Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - MR - L - 03 - SS | 1 | 2025-12-15 | 2025-12-24 |  |  | FALSE | yes
| JD3RMRL03SS61413 | Finishing, Benching Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - MR - L - 03 - SS | 1 | 2025-12-25 | 2026-01-03 |  |  | FALSE | yes
| JD3RMRL03ST61481 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - L - 03 - ST | 1 | 2026-01-28 | 2026-01-31 |  |  | FALSE | yes
| JD3RMRL03ST61482 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - L - 03 | 1 | 2026-02-01 | 2026-02-04 |  |  | FALSE | yes
| JD3RMRL03ST61483 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - L - 03 - ST | 1 | 2026-02-05 | 2026-02-10 |  |  | FALSE | yes
| JD3RMRL03ST61484 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - L - 03 - ST | 1 | 2026-02-23 | 2026-02-28 |  |  | FALSE | yes
| JD3RMRL03ST61485 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - L - 03 - ST | 1 | 2026-03-01 | 2026-03-07 |  |  | FALSE | yes
| JD3RMRL03ST61490 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - MR - L - 03 - ST | 1 | 2026-02-04 | 2026-02-05 |  |  | FALSE | yes
| JD3RMRL03ST61491 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - MR - L - 03 - ST | 1 | 2026-02-01 | 2026-02-02 |  |  | FALSE | yes
| JD3RMRL03ST61492 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - MR - L - 03 - | 1 | 2026-02-03 | 2026-02-04 |  |  | FALSE | yes
| JD3RMRL03ST61493 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - MR - L - 03 - ST | 1 | 2026-02-05 | 2026-02-07 |  |  | FALSE | yes
| JD3RMRL03ST61494 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - MR - L - 03 - ST | 1 | 2026-02-08 | 2026-02-09 |  |  | FALSE | yes
| JD3RMRL03ST61495 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - MR - L - 03 - ST | 1 | 2026-02-10 | 2026-02-12 |  |  | FALSE | yes
| JD3RMRL03ST61501.R | Excavation Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - MR - L - 03 - ST - Remaining | 1 | 2026-02-05 | 2026-02-07 |  |  | FALSE | yes
| JD3RMRL03ST61502.R | Soil Replacement and Bedding Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - MR - L - 03 - | 1 | 2026-02-08 | 2026-02-09 |  |  | FALSE | yes
| JD3RMRL03ST61503.R | Installing for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - MR - L - 03 - ST - Remaining | 1 | 2026-02-10 | 2026-02-11 |  |  | FALSE | yes
| JD3RMRL03ST61504 | Primary Test for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - MR - L - 03 - ST | 1 | 2026-02-12 | 2026-02-14 |  |  | FALSE | yes
| JD3RMRL03ST61505 | Backfilling Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - MR - L - 03 - ST | 1 | 2026-02-15 | 2026-02-16 |  |  | FALSE | yes
| JD3RMRL03ST61510.R | Backfilling Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m - B6.33 42 11.05 - MR - L - 03 - ST - Remaining | 1 | 2026-02-17 | 2026-02-18 |  |  | FALSE | yes
| JD3RMRL03ST61514 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - L - 03 - ST | 1 | 2026-02-15 | 2026-02-16 |  |  | FALSE | yes
| JD3RMRL03ST61515 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - L - 03 - ST | 1 | 2026-02-19 | 2026-02-21 |  |  | FALSE | yes
| JD3RMRL03ST61520.R | Backfilling Works for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m - B6.33 42 11.07 - MR - L - 03 - ST - Remaining | 1 | 2026-03-01 | 2026-03-02 |  |  | FALSE | yes
| JD3RMRL03ST61595 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 2.51 to 3.50 m - B6.33 42 11.24 - MR - L - 03 - ST | 1 | 2026-03-23 | 2026-03-25 | 2025-09-13 |  | FALSE | yes
| JD3RMRL03ST61666 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - MR - L - 03 - ST | 1 | 2026-03-31 | 2026-04-01 | 2025-07-26 |  | FALSE | yes
| JD3RMRL03ST61667 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - MR - L - 03 - ST | 1 | 2026-04-02 | 2026-04-04 |  |  | FALSE | yes
| JD3RMRL03ST61668 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - MR - L - 03 - ST | 1 | 2026-04-05 | 2026-04-06 |  |  | FALSE | yes
| JD3RMRL03ST61676 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - L - 03 - ST | 1 | 2026-03-05 | 2026-03-07 | 2025-05-18 |  | FALSE | yes
| JD3RMRL03ST61677 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - L - 03 - ST | 1 | 2026-03-29 | 2026-03-30 |  |  | FALSE | yes
| JD3RMRL03ST61678 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - L - 03 - ST | 1 | 2026-03-31 | 2026-04-01 |  |  | FALSE | yes
| JD3RMRL03ST61681 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - L - 03 - ST | 1 | 2026-04-02 | 2026-04-04 |  |  | FALSE | yes
| JD3RMRL03ST61682 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - L - 03 - ST | 1 | 2026-04-05 | 2026-04-06 |  |  | FALSE | yes
| JD3RMRL03ST61683 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - L - 03 - ST | 1 | 2026-04-07 | 2026-04-08 |  |  | FALSE | yes
| JD3RMRL03ST61694 | Excavation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - MR - L - 03 - ST | 1 | 2026-03-31 | 2026-04-01 | 2025-10-16 |  | FALSE | yes
| JD3RMRL03ST61695 | Base Plain Concrete Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - MR - L - 03 - ST | 1 | 2026-04-02 | 2026-04-05 | 2025-10-19 |  | FALSE | yes
| JD3RMRL03ST61696 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - MR - L - 03 - ST | 1 | 2026-04-06 | 2026-04-08 | 2025-10-21 |  | FALSE | yes
| JD3RMRL03ST61697 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - MR - L - 03 - ST | 1 | 2026-04-09 | 2026-04-11 |  |  | FALSE | yes
| JD3RMRL03ST61698 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - MR - L - 03 - ST | 1 | 2026-04-12 | 2026-04-13 |  |  | FALSE | yes
| JD3RMRL03ST61699 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - MR - L - 03 - ST | 1 | 2026-04-02 | 2026-04-05 |  |  | FALSE | yes
| JD3RMRL03ST61700 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - MR - L - 03 - ST | 1 | 2026-04-06 | 2026-04-11 |  |  | FALSE | yes
| JD3RMRL03ST61701 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - MR - L - 03 - ST | 1 | 2026-04-12 | 2026-04-16 |  |  | FALSE | yes
| JD3RMRL03ST61702 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - MR - L - 03 - ST | 1 | 2026-04-18 | 2026-04-20 |  |  | FALSE | yes
| JD3RMRL03ST61703 | EXCAVATION Works for Catchbasine double - B6.33 05 39.10 - MR - L - 03 - ST | 1 | 2026-04-06 | 2026-04-08 |  |  | FALSE | yes
| JD3RMRL03ST61704 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - MR - L - 03 - ST | 1 | 2026-04-09 | 2026-04-14 |  |  | FALSE | yes
| JD3RMRL03ST61705 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - MR - L - 03 - ST | 1 | 2026-04-15 | 2026-04-20 |  |  | FALSE | yes
| JD3RMRL03ST61706 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - MR - L - 03 - ST | 1 | 2026-04-21 | 2026-04-23 |  |  | FALSE | yes
| JD3RMRL03TSE61757.R | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - L - 03 - TSE - Remaining | 1 | 2026-05-02 | 2026-05-03 |  |  | FALSE | yes
| JD3RMRL03TSE61758.R | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - L - 03 - TS | 1 | 2026-05-10 | 2026-05-11 |  |  | FALSE | yes
| JD3RMRL03TSE61759.R | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - L - 03 - TSE - Remaining | 1 | 2026-05-24 | 2026-05-25 |  |  | FALSE | yes
| JD3RMRL03TSE61760.R | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - L - 03 - TSE - Remaining | 1 | 2026-06-02 | 2026-06-03 |  |  | FALSE | yes
| JD3RMRL03TSE61761.R | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - L - 03 - TSE - Remaining | 1 | 2026-06-11 | 2026-06-13 |  |  | FALSE | yes
| JD3RMRL03TSE61762 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - L - 03 - TSE | 1 | 2026-05-04 | 2026-05-10 | 2025-10-01 |  | FALSE | yes
| JD3RMRL03TSE61763 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - L - 03 - TS | 1 | 2026-05-11 | 2026-05-13 | 2025-10-05 |  | FALSE | yes
| JD3RMRL03TSE61764 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - L - 03 - TSE | 1 | 2026-06-14 | 2026-06-24 | 2025-10-25 |  | FALSE | yes
| JD3RMRL03TSE61765 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - L - 03 - TSE | 1 | 2026-06-25 | 2026-06-28 |  |  | FALSE | yes
| JD3RMRL03TSE61766 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - L - 03 - TSE | 1 | 2026-06-29 | 2026-07-01 |  |  | FALSE | yes
| JD3RMRL03TSE61767 | Excavation Worksfor HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - L - 03 - TSE | 1 | 2026-05-11 | 2026-05-12 |  |  | FALSE | yes
| JD3RMRL03TSE61768 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - L - 03 - TSE | 1 | 2026-05-13 | 2026-05-14 |  |  | FALSE | yes
| JD3RMRL03TSE61769 | Installing for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - L - 03 - TSE | 1 | 2026-05-16 | 2026-05-17 |  |  | FALSE | yes
| JD3RMRL03TSE61770 | Testing for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - L - 03 - TSE | 1 | 2026-05-18 | 2026-05-19 |  |  | FALSE | yes
| JD3RMRL03TSE61771 | Backfillingfor HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - L - 03 - TSE | 1 | 2026-06-13 | 2026-06-14 |  |  | FALSE | yes
| JD3RMRL03TSE61772 | Excavation Worksfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - MR - L - 03 - TSE | 1 | 2026-05-13 | 2026-05-14 |  |  | FALSE | yes
| JD3RMRL03TSE61773 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - MR - L - 03 - TSE | 1 | 2026-05-16 | 2026-05-17 |  |  | FALSE | yes
| JD3RMRL03TSE61774 | Installing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - MR - L - 03 - TSE | 1 | 2026-05-18 | 2026-05-20 |  |  | FALSE | yes
| JD3RMRL03TSE61775 | Testing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - MR - L - 03 - TSE | 1 | 2026-05-21 | 2026-05-23 |  |  | FALSE | yes
| JD3RMRL03TSE61776 | Backfillingfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - MR - L - 03 - TSE | 1 | 2026-06-15 | 2026-06-16 |  |  | FALSE | yes
| JD3RMRL03TSE61777 | Excavation Worksfor HDPE Pipes 315 mm - depth from 2.51 to 3.5 m - B4.33 31 00.05 - MR - L - 03 - TSE | 1 | 2026-05-16 | 2026-05-17 |  |  | FALSE | yes
| JD3RMRL03TSE61778 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 2.51 to 3.5 m - B4.33 31 00.05 - MR - L - 03 - TSE | 1 | 2026-05-18 | 2026-05-19 |  |  | FALSE | yes
| JD3RMRL03TSE61779 | Installing for HDPE Pipes 315 mm - depth from 2.51 to 3.5 m - B4.33 31 00.05 - MR - L - 03 - TSE | 1 | 2026-05-20 | 2026-05-21 |  |  | FALSE | yes
| JD3RMRL03TSE61780 | Testing for HDPE Pipes 315 mm - depth from 2.51 to 3.5 m - B4.33 31 00.05 - MR - L - 03 - TSE | 1 | 2026-05-23 | 2026-05-24 |  |  | FALSE | yes
| JD3RMRL03TSE61781 | Backfillingfor HDPE Pipes 315 mm - depth from 2.51 to 3.5 m - B4.33 31 00.05 - MR - L - 03 - TSE | 1 | 2026-06-17 | 2026-06-18 |  |  | FALSE | yes
| JD3RMRL03TSE61799 | Installing for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - L - 03 - TSE | 1 | 2026-05-23 | 2026-05-24 |  |  | FALSE | yes
| JD3RMRL03TSE61800 | Testing for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - L - 03 - TSE | 1 | 2026-05-25 | 2026-05-26 |  |  | FALSE | yes
| JD3RMRL03TSE61801 | Backfillingfor HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - L - 03 - TSE | 1 | 2026-06-20 | 2026-06-21 |  |  | FALSE | yes
| JD3RMRL03TSE61804 | Installing for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - MR - L - 03 - TSE | 1 | 2026-05-25 | 2026-05-26 |  |  | FALSE | yes
| JD3RMRL03TSE61805 | Testing for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - MR - L - 03 - TSE | 1 | 2026-05-27 | 2026-05-28 |  |  | FALSE | yes
| JD3RMRL03TSE61806 | Backfillingfor HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - MR - L - 03 - TSE | 1 | 2026-05-30 | 2026-05-31 |  |  | FALSE | yes
| JD3RMRL03TSE61827 | Excavation Worksfor HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - L - 03 - TSE | 1 | 2026-05-23 | 2026-05-24 |  |  | FALSE | yes
| JD3RMRL03TSE61828 | Soil Replacement and Bedding Works for HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - L - 03 - TSE | 1 | 2026-05-25 | 2026-05-26 |  |  | FALSE | yes
| JD3RMRL03TSE61829 | Installing for HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - L - 03 - TSE | 1 | 2026-05-27 | 2026-05-28 |  |  | FALSE | yes
| JD3RMRL03TSE61830 | Testing for HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - L - 03 - TSE | 1 | 2026-05-30 | 2026-05-31 |  |  | FALSE | yes
| JD3RMRL03TSE61831 | Backfillingfor HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - L - 03 - TSE | 1 | 2026-06-01 | 2026-06-02 |  |  | FALSE | yes
| JD3RMRL03TSE61832 | Excavation Worksfor HDPE Pipes 630 mm - depth from 1.51 to 2.5 m - B4.33 31 00.16 - MR - L - 03 - TSE | 1 | 2026-05-25 | 2026-05-26 |  |  | FALSE | yes
| JD3RMRL03TSE61833 | Soil Replacement and Bedding Works for HDPE Pipes 630 mm - depth from 1.51 to 2.5 m - B4.33 31 00.16 - MR - L - 03 - TSE | 1 | 2026-05-27 | 2026-05-28 |  |  | FALSE | yes
| JD3RMRL03TSE61834 | Installing for HDPE Pipes 630 mm - depth from 1.51 to 2.5 m - B4.33 31 00.16 - MR - L - 03 - TSE | 1 | 2026-05-30 | 2026-05-31 |  |  | FALSE | yes
| JD3RMRL03TSE61835 | Testing for HDPE Pipes 630 mm - depth from 1.51 to 2.5 m - B4.33 31 00.16 - MR - L - 03 - TSE | 1 | 2026-06-01 | 2026-06-02 |  |  | FALSE | yes
| JD3RMRL03TSE61836 | Backfillingfor HDPE Pipes 630 mm - depth from 1.51 to 2.5 m - B4.33 31 00.16 - MR - L - 03 - TSE | 1 | 2026-06-03 | 2026-06-04 |  |  | FALSE | yes
| JD3RMRL03TSE61837 | Excavation Worksfor HDPE Pipes 630 mm - depth from 2.51 to 3.5 m - B4.33 31 00.17 - MR - L - 03 - TSE | 1 | 2026-05-27 | 2026-05-28 |  |  | FALSE | yes
| JD3RMRL03TSE61838 | Soil Replacement and Bedding Works for HDPE Pipes 630 mm - depth from 2.51 to 3.5 m - B4.33 31 00.17 - MR - L - 03 - TSE | 1 | 2026-05-30 | 2026-05-31 |  |  | FALSE | yes
| JD3RMRL03TSE61839 | Installing for HDPE Pipes 630 mm - depth from 2.51 to 3.5 m - B4.33 31 00.17 - MR - L - 03 - TSE | 1 | 2026-06-01 | 2026-06-02 |  |  | FALSE | yes
| JD3RMRL03TSE61840 | Testing for HDPE Pipes 630 mm - depth from 2.51 to 3.5 m - B4.33 31 00.17 - MR - L - 03 - TSE | 1 | 2026-06-03 | 2026-06-04 |  |  | FALSE | yes
| JD3RMRL03TSE61841 | Backfillingfor HDPE Pipes 630 mm - depth from 2.51 to 3.5 m - B4.33 31 00.17 - MR - L - 03 - TSE | 1 | 2026-06-06 | 2026-06-07 |  |  | FALSE | yes
| JD3RMRL03TSE61882 | Installationfor gate valves 100 mm - B4.33 14 19.01 - MR - L - 03 - TSE | 1 | 2026-06-03 | 2026-06-07 |  |  | FALSE | yes
| JD3RMRL03TSE61883 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - MR - L - 03 - TSE | 1 | 2026-06-08 | 2026-06-11 |  |  | FALSE | yes
| JD3RMRL03TSE61884 | Installationfor gate valves 250 mm - B4.33 14 19.02 - MR - L - 03 - TSE | 1 | 2026-06-03 | 2026-06-06 |  |  | FALSE | yes
| JD3RMRL03TSE61885 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - MR - L - 03 - TSE | 1 | 2026-06-07 | 2026-06-09 |  |  | FALSE | yes
| JD3RMRL03TSE61886 | Installationfor butterfly valves 300 mm. - B4.33 14 19.03 - MR - L - 03 - TSE | 1 | 2026-06-03 | 2026-06-04 |  |  | FALSE | yes
| JD3RMRL03TSE61887 | Testing And Commtionningfor butterfly valves 300 mm. - B4.33 14 19.03 - MR - L - 03 - TSE | 1 | 2026-06-06 | 2026-06-07 |  |  | FALSE | yes
| JD3RMRL03TSE61890 | Installationfor butterfly valves 600 mm. - B4.33 14 19.05 - MR - L - 03 - TSE | 1 | 2026-06-03 | 2026-06-04 |  |  | FALSE | yes
| JD3RMRL03TSE61891 | Testing And Commtionningfor butterfly valves 600 mm. - B4.33 14 19.05 - MR - L - 03 - TSE | 1 | 2026-06-06 | 2026-06-07 |  |  | FALSE | yes
| JD3RMRL03TSE61894 | Installationfor Wash - Out valves 100 mm. - on pipes with diameter 110 - 400 mm - B4.33 14 19.07 - MR - L - 03 - TSE | 1 | 2026-06-03 | 2026-06-04 |  |  | FALSE | yes
| JD3RMRL03TSE61895 | Testing And Commtionningfor Wash - Out valves 100 mm. - on pipes with diameter 110 - 400 mm - B4.33 14 19.07 - MR - L - | 1 | 2026-06-06 | 2026-06-07 |  |  | FALSE | yes
| JD3RMRL03TSE61900 | Installationfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - MR - L - 03 - TSE | 1 | 2026-06-03 | 2026-06-04 |  |  | FALSE | yes
| JD3RMRL03TSE61901 | Testing And Commtionningfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - MR - L - 03 - | 1 | 2026-06-06 | 2026-06-07 |  |  | FALSE | yes
| JD3RMRL03TSE61902 | Installationfor Air valves 65 mm. - on pipes with diameter 355 - 630 mm - B4.33 14 19.16 - MR - L - 03 - TSE | 1 | 2026-06-03 | 2026-06-04 |  |  | FALSE | yes
| JD3RMRL03TSE61903 | Testing And Commtionningfor Air valves 65 mm. - on pipes with diameter 355 - 630 mm - B4.33 14 19.16 - MR - L - 03 - TSE | 1 | 2026-06-06 | 2026-06-07 |  |  | FALSE | yes
| JD3RMRL03TSE61906 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - L - 03 - TSE | 1 | 2026-05-30 | 2026-05-31 |  |  | FALSE | yes
| JD3RMRL03TSE61907 | Plain Concrete Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - L - 03 - TSE | 1 | 2026-06-01 | 2026-06-02 |  |  | FALSE | yes
| JD3RMRL03TSE61908 | INSTALLATIONfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - L - 03 - TSE | 1 | 2026-06-03 | 2026-06-04 |  |  | FALSE | yes
| JD3RMRL03TSE61909 | Backfilling Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - L - 03 - TSE | 1 | 2026-06-06 | 2026-06-07 |  |  | FALSE | yes
| JD3RMRL03TSE61910 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 500 to 630 MM - B4.33 14 13.02 - MR - L - 03 - TSE | 1 | 2026-06-01 | 2026-06-02 |  |  | FALSE | yes
| JD3RMRL03TSE61911 | Plain Concrete Worksfor R.C Valve Chamber - 500 to 630 MM - B4.33 14 13.02 - MR - L - 03 - TSE | 1 | 2026-06-03 | 2026-06-04 |  |  | FALSE | yes
| JD3RMRL03TSE61912 | INSTALLATIONfor R.C Valve Chamber - 500 to 630 MM - B4.33 14 13.02 - MR - L - 03 - TSE | 1 | 2026-06-06 | 2026-06-07 |  |  | FALSE | yes
| JD3RMRL03TSE61913 | Backfilling Worksfor R.C Valve Chamber - 500 to 630 MM - B4.33 14 13.02 - MR - L - 03 - TSE | 1 | 2026-06-08 | 2026-06-09 |  |  | FALSE | yes
| JD3RMRL03TSE61918 | EXCAVATION and Bedding Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - L - 03 - TSE | 1 | 2026-06-03 | 2026-06-04 |  |  | FALSE | yes
| JD3RMRL03TSE61919 | Plain Concrete Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - L - 03 - TSE | 1 | 2026-06-06 | 2026-06-07 |  |  | FALSE | yes
| JD3RMRL03TSE61920 | INSTALLATIONfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - L - 03 - TSE | 1 | 2026-06-08 | 2026-06-09 |  |  | FALSE | yes
| JD3RMRL03TSE61921 | Backfilling Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - L - 03 - TSE | 1 | 2026-06-10 | 2026-06-11 |  |  | FALSE | yes
| JD3RMRL03TSE61930 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - L - 03 - TSE | 1 | 2026-06-06 | 2026-06-07 |  |  | FALSE | yes
| JD3RMRL03TSE61931 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - L - 03 - TSE | 1 | 2026-06-08 | 2026-06-09 |  |  | FALSE | yes
| JD3RMRL03TSE61932 | INSTALLATIONfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - L - 03 - TSE | 1 | 2026-06-10 | 2026-06-11 |  |  | FALSE | yes
| JD3RMRL03TSE61933 | Backfilling Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - L - 03 - TSE | 1 | 2026-06-13 | 2026-06-14 |  |  | FALSE | yes
| JD3RMRL03TSE61934 | EXCAVATION and Bedding Worksfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - L - 03 - TSE | 1 | 2026-06-08 | 2026-06-09 |  |  | FALSE | yes
| JD3RMRL03TSE61935 | Plain Concrete Worksfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - L - 03 - TSE | 1 | 2026-06-10 | 2026-06-11 |  |  | FALSE | yes
| JD3RMRL03TSE61936 | INSTALLATIONfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - L - 03 - TSE | 1 | 2026-06-13 | 2026-06-14 |  |  | FALSE | yes
| JD3RMRL03TSE61937 | Backfilling Worksfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - L - 03 - TSE | 1 | 2026-07-02 | 2026-07-04 |  |  | FALSE | yes
| JD3RMRL17SS62068 | Trench excavation for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - MR - L - 17 - SS | 1 | 2025-09-11 | 2025-10-01 | 2025-10-25 |  | FALSE | FALSE
| JD3RMRL17SS62069 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - MR - L - 17 - S | 1 | 2025-10-02 | 2025-10-22 | 2025-10-27 |  | FALSE | FALSE
| JD3RMRL17SS62070 | Installing for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - MR - L - 17 - SS | 1 | 2025-11-04 | 2025-11-27 | 2025-10-30 |  | FALSE | yes
| JD3RMRL17SS62071 | Primary Test for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - MR - L - 17 - SS | 1 | 2025-11-29 | 2025-12-18 |  |  | FALSE | yes
| JD3RMRL17SS62072 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - MR - L - 17 - S | 1 | 2025-12-20 | 2026-01-12 |  |  | FALSE | yes
| JD3RMRL17SS62073 | Trench excavation for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - MR - L - 17 - SS | 1 | 2025-10-02 | 2025-10-07 |  |  | FALSE | yes
| JD3RMRL17SS62074 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - MR - L - 17 - S | 1 | 2025-10-08 | 2025-10-13 |  |  | FALSE | yes
| JD3RMRL17SS62075 | Installing for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - MR - L - 17 - SS | 1 | 2025-10-14 | 2025-10-20 |  |  | FALSE | yes
| JD3RMRL17SS62076 | Primary Test for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - MR - L - 17 - SS | 1 | 2025-10-21 | 2025-10-26 |  |  | FALSE | yes
| JD3RMRL17SS62077 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - MR - L - 17 - S | 1 | 2025-10-27 | 2025-11-03 |  |  | FALSE | yes
| JD3RMRL17SS62083 | Trench excavation for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50 - B5.33 31 00.11 - MR - L - 17 - SS | 1 | 2025-10-08 | 2025-10-09 |  |  | FALSE | yes
| JD3RMRL17SS62084 | Soil Replacement and Bedding Works for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50 - B5.33 31 00.11 - MR - L - 17 - S | 1 | 2025-10-11 | 2025-10-12 |  |  | FALSE | yes
| JD3RMRL17SS62085 | Installing for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50 - B5.33 31 00.11 - MR - L - 17 - SS | 1 | 2025-10-13 | 2025-10-14 |  |  | FALSE | yes
| JD3RMRL17SS62086 | Primary Test for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50 - B5.33 31 00.11 - MR - L - 17 - SS | 1 | 2025-10-15 | 2025-10-16 |  |  | FALSE | yes
| JD3RMRL17SS62087 | Backfilling and warning tabe Works for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50 - B5.33 31 00.11 - MR - L - 17 - S | 1 | 2025-10-18 | 2025-10-20 |  |  | FALSE | yes
| JD3RMRL17SS62102 | Finishing, Benching Works for Manholes 1200 mm - Depth from 0.00 to 1.50 - B5.33 05 13.01 - MR - L - 17 - SS | 1 | 2025-10-20 | 2025-10-21 |  |  | FALSE | yes
| JD3RMRL17SS62110 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - MR - L - 17 - SS | 1 | 2025-10-13 | 2025-10-16 |  |  | FALSE | yes
| JD3RMRL17SS62111 | Installation of Base Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - MR - L - 17 - SS | 1 | 2025-10-18 | 2025-10-28 |  |  | FALSE | yes
| JD3RMRL17SS62112 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - MR - | 1 | 2025-10-29 | 2025-11-09 |  |  | FALSE | yes
| JD3RMRL17SS62113 | Backfilling Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - MR - L - 17 - SS | 1 | 2025-11-10 | 2025-11-16 |  |  | FALSE | yes
| JD3RMRL17SS62114 | Finishing, Benching Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - MR - L - 17 - SS | 1 | 2025-11-17 | 2025-11-22 |  |  | FALSE | yes
| JD3RMRL17SS62122 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - MR - L - 17 - SS | 1 | 2025-10-18 | 2025-10-20 |  |  | FALSE | yes
| JD3RMRL17SS62123 | Installation of Base Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - MR - L - 17 - SS | 1 | 2025-10-21 | 2025-10-28 |  |  | FALSE | yes
| JD3RMRL17SS62124 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - MR - | 1 | 2025-10-29 | 2025-11-05 |  |  | FALSE | yes
| JD3RMRL17SS62125 | Backfilling Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - MR - L - 17 - SS | 1 | 2025-11-06 | 2025-11-10 |  |  | FALSE | yes
| JD3RMRL17SS62126 | Finishing, Benching Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - MR - L - 17 - SS | 1 | 2025-11-11 | 2025-11-13 |  |  | FALSE | yes
| JD3RMRL17SUR01 | Surveying Works L - 17 | 1 |  |  |  |  | yes | FALSE
| JD3RMRL34TSE63183 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - L - 34 - TSE | 1 | 2026-01-21 | 2026-01-24 |  |  | FALSE | yes
| JD3RMRL34TSE63184 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - L - 34 - TS | 1 | 2026-01-25 | 2026-01-27 |  |  | FALSE | yes
| JD3RMRL34TSE63185 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - L - 34 - TSE | 1 | 2026-01-28 | 2026-02-02 |  |  | FALSE | yes
| JD3RMRL34TSE63186 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - L - 34 - TSE | 1 | 2026-02-03 | 2026-02-07 |  |  | FALSE | yes
| JD3RMRL34TSE63187 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - L - 34 - TSE | 1 | 2026-02-08 | 2026-02-11 |  |  | FALSE | yes
| JD3RMRL34TSE63188.R | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - L - 34 - TSE - Remaining | 1 | 2026-02-16 | 2026-02-17 | 2025-08-21 |  | FALSE | yes
| JD3RMRL34TSE63189.R | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - L - 34 - TS | 1 | 2026-03-12 | 2026-03-14 | 2025-08-24 |  | FALSE | yes
| JD3RMRL34TSE63190.R | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - L - 34 - TSE - Remaining | 1 | 2026-04-04 | 2026-04-05 | 2025-08-26 |  | FALSE | yes
| JD3RMRL34TSE63191 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - L - 34 - TSE | 1 | 2026-04-04 | 2026-04-18 | 2025-03-12 |  | FALSE | yes
| JD3RMRL34TSE63191.R | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - L - 34 - TSE - Remaining | 1 | 2026-04-19 | 2026-04-20 |  |  | FALSE | yes
| JD3RMRL34TSE63192.R | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - L - 34 - TSE - Remaining | 1 | 2026-05-04 | 2026-05-05 | 2025-08-27 |  | FALSE | yes
| JD3RMRL34TSE63193 | Excavation Worksfor HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - L - 34 - TSE | 1 | 2026-01-25 | 2026-01-26 |  |  | FALSE | yes
| JD3RMRL34TSE63194 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - L - 34 - TSE | 1 | 2026-01-27 | 2026-01-28 |  |  | FALSE | yes
| JD3RMRL34TSE63195 | Installing for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - L - 34 - TSE | 1 | 2026-01-29 | 2026-02-01 |  |  | FALSE | yes
| JD3RMRL34TSE63196 | Testing for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - L - 34 - TSE | 1 | 2026-02-02 | 2026-02-03 |  |  | FALSE | yes
| JD3RMRL34TSE63197 | Backfillingfor HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - L - 34 - TSE | 1 | 2026-02-04 | 2026-02-05 |  |  | FALSE | yes
| JD3RMRL34TSE63198 | Excavation Worksfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - MR - L - 34 - TSE | 1 | 2026-01-27 | 2026-01-28 |  |  | FALSE | yes
| JD3RMRL34TSE63199 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - MR - L - 34 - TSE | 1 | 2026-01-29 | 2026-01-31 |  |  | FALSE | yes
| JD3RMRL34TSE63200 | Installing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - MR - L - 34 - TSE | 1 | 2026-02-01 | 2026-02-02 |  |  | FALSE | yes
| JD3RMRL34TSE63201 | Testing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - MR - L - 34 - TSE | 1 | 2026-02-03 | 2026-02-04 |  |  | FALSE | yes
| JD3RMRL34TSE63202 | Backfillingfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - MR - L - 34 - TSE | 1 | 2026-02-05 | 2026-02-07 |  |  | FALSE | yes
| JD3RMRL34TSE63228 | Excavation Worksfor HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - MR - L - 34 - TSE | 1 | 2026-02-02 | 2026-02-03 |  |  | FALSE | yes
| JD3RMRL34TSE63229 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - MR - L - 34 - TSE | 1 | 2026-02-04 | 2026-02-05 |  |  | FALSE | yes
| JD3RMRL34TSE63230 | Installing for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - MR - L - 34 - TSE | 1 | 2026-02-07 | 2026-02-09 |  |  | FALSE | yes
| JD3RMRL34TSE63231 | Testing for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - MR - L - 34 - TSE | 1 | 2026-02-10 | 2026-02-11 |  |  | FALSE | yes
| JD3RMRL34TSE63232 | Backfillingfor HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - MR - L - 34 - TSE | 1 | 2026-02-12 | 2026-02-14 |  |  | FALSE | yes
| JD3RMRL34TSE63253 | Excavation Worksfor HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - L - 34 - TSE | 1 | 2026-02-04 | 2026-02-05 |  |  | FALSE | yes
| JD3RMRL34TSE63254 | Soil Replacement and Bedding Works for HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - L - 34 - TSE | 1 | 2026-02-07 | 2026-02-08 |  |  | FALSE | yes
| JD3RMRL34TSE63255 | Installing for HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - L - 34 - TSE | 1 | 2026-02-09 | 2026-02-10 |  |  | FALSE | yes
| JD3RMRL34TSE63256 | Testing for HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - L - 34 - TSE | 1 | 2026-02-11 | 2026-02-12 |  |  | FALSE | yes
| JD3RMRL34TSE63257 | Backfillingfor HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - L - 34 - TSE | 1 | 2026-02-14 | 2026-02-15 |  |  | FALSE | yes
| JD3RMRL34TSE63258 | Excavation Worksfor HDPE Pipes 630 mm - depth from 1.51 to 2.5 m - B4.33 31 00.16 - MR - L - 34 - TSE | 1 | 2026-02-07 | 2026-02-08 |  |  | FALSE | yes
| JD3RMRL34TSE63259 | Soil Replacement and Bedding Works for HDPE Pipes 630 mm - depth from 1.51 to 2.5 m - B4.33 31 00.16 - MR - L - 34 - TSE | 1 | 2026-02-09 | 2026-02-10 |  |  | FALSE | yes
| JD3RMRL34TSE63260 | Installing for HDPE Pipes 630 mm - depth from 1.51 to 2.5 m - B4.33 31 00.16 - MR - L - 34 - TSE | 1 | 2026-02-11 | 2026-02-12 |  |  | FALSE | yes
| JD3RMRL34TSE63261 | Testing for HDPE Pipes 630 mm - depth from 1.51 to 2.5 m - B4.33 31 00.16 - MR - L - 34 - TSE | 1 | 2026-02-14 | 2026-02-15 |  |  | FALSE | yes
| JD3RMRL34TSE63262 | Backfillingfor HDPE Pipes 630 mm - depth from 1.51 to 2.5 m - B4.33 31 00.16 - MR - L - 34 - TSE | 1 | 2026-02-16 | 2026-02-17 |  |  | FALSE | yes
| JD3RMRL34TSE63308 | Installationfor gate valves 100 mm - B4.33 14 19.01 - MR - L - 34 - TSE | 1 | 2026-02-14 | 2026-02-16 | 2025-10-09 |  | FALSE | yes
| JD3RMRL34TSE63309 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - MR - L - 34 - TSE | 1 | 2026-02-17 | 2026-02-19 |  |  | FALSE | yes
| JD3RMRL34TSE63310 | Installationfor gate valves 250 mm - B4.33 14 19.02 - MR - L - 34 - TSE | 1 | 2026-02-14 | 2026-02-18 |  |  | FALSE | yes
| JD3RMRL34TSE63311 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - MR - L - 34 - TSE | 1 | 2026-02-21 | 2026-02-25 |  |  | FALSE | yes
| JD3RMRL34TSE63312 | Installationfor butterfly valves 300 mm. - B4.33 14 19.03 - MR - L - 34 - TSE | 1 | 2026-02-19 | 2026-02-21 |  |  | FALSE | yes
| JD3RMRL34TSE63313 | Testing And Commtionningfor butterfly valves 300 mm. - B4.33 14 19.03 - MR - L - 34 - TSE | 1 | 2026-02-22 | 2026-02-23 |  |  | FALSE | yes
| JD3RMRL34TSE63314 | Installationfor butterfly valves 400 mm. - B4.33 14 19.04 - MR - L - 34 - TSE | 1 | 2026-02-22 | 2026-02-23 |  |  | FALSE | yes
| JD3RMRL34TSE63315 | Testing And Commtionningfor butterfly valves 400 mm. - B4.33 14 19.04 - MR - L - 34 - TSE | 1 | 2026-02-26 | 2026-02-28 |  |  | FALSE | yes
| JD3RMRL34TSE63320 | Installationfor Wash - Out valves 100 mm. - on pipes with diameter 110 - 400 mm - B4.33 14 19.07 - MR - L - 34 - TSE | 1 | 2026-02-24 | 2026-02-25 |  |  | FALSE | yes
| JD3RMRL34TSE63321 | Testing And Commtionningfor Wash - Out valves 100 mm. - on pipes with diameter 110 - 400 mm - B4.33 14 19.07 - MR - L - | 1 | 2026-02-26 | 2026-02-28 |  |  | FALSE | yes
| JD3RMRL34TSE63326 | Installationfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - MR - L - 34 - TSE | 1 | 2026-02-26 | 2026-02-28 |  |  | FALSE | yes
| JD3RMRL34TSE63327 | Testing And Commtionningfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - MR - L - 34 - | 1 | 2026-03-01 | 2026-03-02 |  |  | FALSE | yes
| JD3RMRL34TSE63328 | Installationfor Air valves 65 mm. - on pipes with diameter 355 - 630 mm - B4.33 14 19.16 - MR - L - 34 - TSE | 1 | 2026-03-01 | 2026-03-02 |  |  | FALSE | yes
| JD3RMRL34TSE63329 | Testing And Commtionningfor Air valves 65 mm. - on pipes with diameter 355 - 630 mm - B4.33 14 19.16 - MR - L - 34 - TSE | 1 | 2026-03-03 | 2026-03-04 |  |  | FALSE | yes
| JD3RMRL34TSE63332 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - L - 34 - TSE | 1 | 2026-02-09 | 2026-02-10 |  |  | FALSE | yes
| JD3RMRL34TSE63333 | Plain Concrete Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - L - 34 - TSE | 1 | 2026-02-11 | 2026-02-12 |  |  | FALSE | yes
| JD3RMRL34TSE63334 | INSTALLATIONfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - L - 34 - TSE | 1 | 2026-02-14 | 2026-02-15 |  |  | FALSE | yes
| JD3RMRL34TSE63335 | Backfilling Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - L - 34 - TSE | 1 | 2026-02-16 | 2026-02-17 |  |  | FALSE | yes
| JD3RMRL34TSE63344 | EXCAVATION and Bedding Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - L - 34 - TSE | 1 | 2026-02-11 | 2026-02-12 |  |  | FALSE | yes
| JD3RMRL34TSE63345 | Plain Concrete Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - L - 34 - TSE | 1 | 2026-02-14 | 2026-02-15 |  |  | FALSE | yes
| JD3RMRL34TSE63346 | INSTALLATIONfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - L - 34 - TSE | 1 | 2026-02-16 | 2026-02-17 |  |  | FALSE | yes
| JD3RMRL34TSE63347 | Backfilling Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - MR - L - 34 - TSE | 1 | 2026-02-18 | 2026-02-19 |  |  | FALSE | yes
| JD3RMRL34TSE63356 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - L - 34 - TSE | 1 | 2026-02-14 | 2026-02-15 |  |  | FALSE | yes
| JD3RMRL34TSE63357 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - L - 34 - TSE | 1 | 2026-02-16 | 2026-02-17 |  |  | FALSE | yes
| JD3RMRL34TSE63358 | INSTALLATIONfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - L - 34 - TSE | 1 | 2026-02-18 | 2026-02-19 |  |  | FALSE | yes
| JD3RMRL34TSE63359 | Backfilling Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - L - 34 - TSE | 1 | 2026-02-21 | 2026-02-22 |  |  | FALSE | yes
| JD3RMRL34TSE63360 | EXCAVATION and Bedding Worksfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - L - 34 - TSE | 1 | 2026-02-16 | 2026-02-17 |  |  | FALSE | yes
| JD3RMRL34TSE63361 | Plain Concrete Worksfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - L - 34 - TSE | 1 | 2026-02-18 | 2026-02-19 |  |  | FALSE | yes
| JD3RMRL34TSE63362 | INSTALLATIONfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - L - 34 - TSE | 1 | 2026-02-21 | 2026-02-22 |  |  | FALSE | yes
| JD3RMRL34TSE63363 | Backfilling Worksfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - L - 34 - TSE | 1 | 2026-02-23 | 2026-02-24 |  |  | FALSE | yes
| JD3RMRL51SL64111 | Excavation Worksfor Copper Cables 4Cx10 mm² - B2.26 05 19.02 - MR - L - 51 - SL | 1 | 2026-06-13 | 2026-06-15 |  |  | FALSE | yes
| JD3RMRL51SL64112 | Installationfor Copper Cables 4Cx10 mm² - B2.26 05 19.02 - MR - L - 51 - SL | 1 | 2026-06-16 | 2026-06-18 |  |  | FALSE | yes
| JD3RMRL51SL64113 | Backfilling, Warning Tabe Worksfor Copper Cables 4Cx10 mm² - B2.26 05 19.02 - MR - L - 51 - SL | 1 | 2026-06-20 | 2026-06-22 |  |  | FALSE | yes
| JD3RMRL51SL64114 | Testing and Commitioning for Copper Cables 4Cx10 mm² - B2.26 05 19.02 - MR - L - 51 - SL | 1 | 2026-06-23 | 2026-06-25 |  |  | FALSE | yes
| JD3RMRL51SL64119 | Excavation Worksfor Copper Cables 4Cx25 mm² - B2.26 05 19.04 - MR - L - 51 - SL | 1 | 2026-06-13 | 2026-06-15 |  |  | FALSE | yes
| JD3RMRL51SL64120 | Installationfor Copper Cables 4Cx25 mm² - B2.26 05 19.04 - MR - L - 51 - SL | 1 | 2026-06-16 | 2026-06-18 |  |  | FALSE | yes
| JD3RMRL51SL64121 | Backfilling, Warning Tabe Worksfor Copper Cables 4Cx25 mm² - B2.26 05 19.04 - MR - L - 51 - SL | 1 | 2026-06-20 | 2026-06-22 |  |  | FALSE | yes
| JD3RMRL51SL64122 | Testing and Commitioning for Copper Cables 4Cx25 mm² - B2.26 05 19.04 - MR - L - 51 - SL | 1 | 2026-06-27 | 2026-06-29 |  |  | FALSE | yes
| JD3RMRL51SL64131 | INSTALLINGfor insulated copper conductor 6 mm² - B2.26 05 19.07 - MR - L - 51 - SL | 1 | 2026-06-20 | 2026-06-22 |  |  | FALSE | yes
| JD3RMRL51SL64132 | TESTING AND COMMITIONINGfor insulated copper conductor 6 mm² - B2.26 05 19.07 - MR - L - 51 - SL | 1 | 2026-06-23 | 2026-06-25 |  |  | FALSE | yes
| JD3RMRL51SL64133 | INSTALLINGfor insulated copper conductor 16 mm² - B2.26 05 19.08 - MR - L - 51 - SL | 1 | 2026-06-20 | 2026-06-22 |  |  | FALSE | yes
| JD3RMRL51SL64134 | TESTING AND COMMITIONINGfor insulated copper conductor 16 mm² - B2.26 05 19.08 - MR - L - 51 - SL | 1 | 2026-06-23 | 2026-06-25 |  |  | FALSE | yes
| JD3RMRL51SL64135 | Excavation of reinforced concrete foundationfor LIGHTING POLE two arms - B2.26 56 19.01 - MR - L - 51 - SL | 1 | 2026-06-13 | 2026-06-14 |  |  | FALSE | yes
| JD3RMRL51SL64136 | Installation of reinforced concrete foundationfor LIGHTING POLE two arms - B2.26 56 19.01 - MR - L - 51 - SL | 1 | 2026-06-15 | 2026-06-16 |  |  | FALSE | yes
| JD3RMRL51SL64137 | Backfilling of reinforced concrete foundationfor LIGHTING POLE two arms - B2.26 56 19.01 - MR - L - 51 - SL | 1 | 2026-06-17 | 2026-06-18 |  |  | FALSE | yes
| JD3RMRL51SL64138 | Installation Worksfor LIGHTING POLE two arms - B2.26 56 19.01 - MR - L - 51 - SL | 1 | 2026-06-20 | 2026-06-21 |  |  | FALSE | yes
| JD3RMRL51SL64139 | Testing and Commitioningfor LIGHTING POLE two arms - B2.26 56 19.01 - MR - L - 51 - SL | 1 | 2026-06-22 | 2026-06-23 |  |  | FALSE | yes
| JD3RMRL51SL64140 | Excavation of reinforced concrete foundationfor LIGHTING POLE one arm - B2.26 56 19.02 - MR - L - 51 - SL | 1 | 2026-06-13 | 2026-06-14 |  |  | FALSE | yes
| JD3RMRL51SL64141 | Installation of reinforced concrete foundationfor LIGHTING POLE one arm - B2.26 56 19.02 - MR - L - 51 - SL | 1 | 2026-06-15 | 2026-06-16 |  |  | FALSE | yes
| JD3RMRL51SL64142 | Backfilling of reinforced concrete foundationfor LIGHTING POLE one arm - B2.26 56 19.02 - MR - L - 51 - SL | 1 | 2026-06-17 | 2026-06-18 |  |  | FALSE | yes
| JD3RMRL51SL64143 | Installation Worksfor LIGHTING POLE one arm - B2.26 56 19.02 - MR - L - 51 - SL | 1 | 2026-06-20 | 2026-06-23 |  |  | FALSE | yes
| JD3RMRL51SL64144 | Testing and Commitioningfor LIGHTING POLE one arm - B2.26 56 19.02 - MR - L - 51 - SL | 1 | 2026-06-24 | 2026-06-28 |  |  | FALSE | yes
| JD3RMRL51SL64145 | Installationfor Lighting( LED ) Luminaire 150 WATT - B2.26.56.19.01 - MR - L - 51 - SL | 1 | 2026-06-17 | 2026-06-21 |  |  | FALSE | yes
| JD3RMRL51SL64148 | Supply, construct, connect and test earthing pitsfor Street Lighting EARTHING SYSTEM - B2.26 05 26.01 - MR - L - 51 - SL | 1 | 2026-06-22 | 2026-06-23 |  |  | FALSE | yes
| JD3RMRL51SL64149 | Excavation Worksfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - MR - L - 51 - SL | 1 | 2026-06-13 | 2026-06-15 |  |  | FALSE | yes
| JD3RMRL51SL64150 | Installationfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - MR - L - 51 - SL | 1 | 2026-06-16 | 2026-06-21 |  |  | FALSE | yes
| JD3RMRL51SL64151 | Pouring Concrete Coverfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - MR - L - 51 - SL | 1 | 2026-06-22 | 2026-06-27 |  |  | FALSE | yes
| JD3RMRL51SL64152 | Testing and Backfilling Worksfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - MR - L - 51 - SL | 1 | 2026-06-28 | 2026-07-02 |  |  | FALSE | yes
| JD3RMRL51SL64153 | Excavation Worksfor PVC Pipes 4×150mm - B2.33 71 19.02 - MR - L - 51 - SL | 1 | 2026-06-13 | 2026-06-14 |  |  | FALSE | yes
| JD3RMRL51SL64154 | Installationfor PVC Pipes 4×150mm - B2.33 71 19.02 - MR - L - 51 - SL | 1 | 2026-06-15 | 2026-06-16 |  |  | FALSE | yes
| JD3RMRL51SL64155 | Pouring Concrete Coverfor PVC Pipes 4×150mm - B2.33 71 19.02 - MR - L - 51 - SL | 1 | 2026-06-17 | 2026-06-18 |  |  | FALSE | yes
| JD3RMRL51SL64156 | Testing and Backfilling Worksfor PVC Pipes 4×150mm - B2.33 71 19.02 - MR - L - 51 - SL | 1 | 2026-06-20 | 2026-06-21 |  |  | FALSE | yes
| JD3RMRL51SL64161 | Excavationfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - MR - L - 51 - SL | 1 | 2026-06-13 | 2026-06-14 |  |  | FALSE | yes
| JD3RMRL51SL64162 | Installationfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - MR - L - 51 - SL | 1 | 2026-06-15 | 2026-06-16 |  |  | FALSE | yes
| JD3RMRL51SL64163 | Backfillingfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - MR - L - 51 - SL | 1 | 2026-06-17 | 2026-06-18 |  |  | FALSE | yes
| JD3RMRL51SL64164 | Excavationfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - MR - L - 51 - SL | 1 | 2026-06-13 | 2026-06-14 |  |  | FALSE | yes
| JD3RMRL51SL64165 | Installationfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - MR - L - 51 - SL | 1 | 2026-06-15 | 2026-06-16 |  |  | FALSE | yes
| JD3RMRL51SL64166 | Backfillingfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - MR - L - 51 - SL | 1 | 2026-06-17 | 2026-06-18 |  |  | FALSE | yes
| JD3RMRL51SS521431 | Backfilling Works for Manholes 1200 mm - Depth from 3.51 to 4.50 - B5.33 05 13.05 - MR - C - 03 - SS | 1 | 2025-10-13 | 2025-10-14 |  |  | FALSE | yes
| JD3RMRL51SS521441 | Finishing, Benching Works for Manholes 1200 mm - Depth from 3.51 to 4.50 - B5.33 05 13.05 - MR - C - 03 - SS | 1 | 2025-10-15 | 2025-10-16 |  |  | FALSE | yes
| JD3RMRL51SS63539 | Backfilling Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - MR - L - 51 - SS | 1 | 2025-10-06 | 2025-10-07 |  |  | FALSE | yes
| JD3RMRL51SS63540 | Finishing, Benching Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - MR - L - 51 - SS | 1 | 2025-10-08 | 2025-10-09 |  |  | FALSE | yes
| JD3RMRL51SS63551 | Backfilling Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - MR - L - 51 - SS | 1 | 2025-10-08 | 2025-10-09 |  |  | FALSE | yes
| JD3RMRL51SS63552 | Finishing, Benching Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - MR - L - 51 - SS | 1 | 2025-10-11 | 2025-10-12 |  |  | FALSE | yes
| JD3RMRL51ST524350 | Concrete encasement for pipes - NNB6.33 42 11.25 - MR - L - 51 - ST | 1 | 2026-02-21 | 2026-03-05 |  |  | FALSE | yes
| JD3RMRL51ST63620 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - L - 51 - ST | 1 | 2026-01-25 | 2026-02-01 | 2025-10-11 |  | FALSE | yes
| JD3RMRL51ST63621 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - L - 51 | 1 | 2026-02-02 | 2026-02-11 |  |  | FALSE | yes
| JD3RMRL51ST63622 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - L - 51 - ST | 1 | 2026-02-12 | 2026-02-24 |  |  | FALSE | yes
| JD3RMRL51ST63623 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - L - 51 - ST | 1 | 2026-02-25 | 2026-03-09 |  |  | FALSE | yes
| JD3RMRL51ST63624 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - L - 51 - ST | 1 | 2026-03-10 | 2026-03-25 |  |  | FALSE | yes
| JD3RMRL51ST63625.R | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - MR - L - 51 - ST - Remaining | 1 | 2026-02-02 | 2026-02-03 | 2025-08-16 |  | FALSE | yes
| JD3RMRL51ST63626.R | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - MR - L - 51 - | 1 | 2026-02-04 | 2026-02-05 | 2025-08-17 |  | FALSE | yes
| JD3RMRL51ST63627.R | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - MR - L - 51 - ST - Remaining | 1 | 2026-02-07 | 2026-02-08 | 2025-08-18 |  | FALSE | yes
| JD3RMRL51ST63628.R | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - MR - L - 51 - ST - Remaining | 1 | 2026-02-11 | 2026-02-12 | 2025-09-10 |  | FALSE | yes
| JD3RMRL51ST63629 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - MR - L - 51 - ST | 1 | 2026-02-14 | 2026-02-23 | 2025-10-25 |  | FALSE | yes
| JD3RMRL51ST63630 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - MR - L - 51 - ST | 1 | 2025-10-18 | 2025-10-19 |  |  | FALSE | yes
| JD3RMRL51ST63631 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - MR - L - 51 - | 1 | 2025-10-20 | 2025-10-21 |  |  | FALSE | yes
| JD3RMRL51ST63632 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - MR - L - 51 - ST | 1 | 2025-10-22 | 2025-10-23 |  |  | FALSE | yes
| JD3RMRL51ST63633 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - MR - L - 51 - ST | 1 | 2025-10-25 | 2025-10-26 |  |  | FALSE | yes
| JD3RMRL51ST63634 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - MR - L - 51 - ST | 1 | 2026-03-10 | 2026-03-11 |  |  | FALSE | yes
| JD3RMRL51ST63635.R | Excavation Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m - B6.33 42 11.03 - MR - L - 51 - ST - Remaining | 1 | 2026-02-04 | 2026-02-05 | 2025-09-10 |  | FALSE | yes
| JD3RMRL51ST63636.R | Soil Replacement and Bedding Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m - B6.33 42 11.03 - MR - L - 51 - | 1 | 2026-02-07 | 2026-02-08 | 2025-09-20 |  | FALSE | yes
| JD3RMRL51ST63637.R | Installing for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m - B6.33 42 11.03 - MR - L - 51 - ST - Remaining | 1 | 2026-02-09 | 2026-02-10 | 2025-09-23 |  | FALSE | yes
| JD3RMRL51ST63638 | Primary Test for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m - B6.33 42 11.03 - MR - L - 51 - ST | 1 | 2026-02-11 | 2026-02-12 |  |  | FALSE | yes
| JD3RMRL51ST63639 | Backfilling Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m - B6.33 42 11.03 - MR - L - 51 - ST | 1 | 2026-03-07 | 2026-03-08 |  |  | FALSE | yes
| JD3RMRL51ST63642.R | Installing for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - MR - L - 51 - ST - Remaining | 1 | 2026-02-11 | 2026-02-12 | 2025-08-23 |  | FALSE | yes
| JD3RMRL51ST63643.R | Primary Test for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - MR - L - 51 - ST - Remaining | 1 | 2026-02-14 | 2026-02-15 | 2025-10-25 |  | FALSE | yes
| JD3RMRL51ST63644.R | Backfilling Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - MR - L - 51 - ST - Remaining | 1 | 2026-02-16 | 2026-02-17 | 2025-08-26 |  | FALSE | yes
| JD3RMRL51ST63653 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - L - 51 - ST | 1 | 2026-02-16 | 2026-02-18 | 2025-08-20 |  | FALSE | yes
| JD3RMRL51ST63654 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - L - 51 - ST | 1 | 2026-02-19 | 2026-02-23 | 2025-08-23 |  | FALSE | yes
| JD3RMRL51ST63658.R | Primary Test for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m - B6.33 42 11.07 - MR - L - 51 - ST - Remaining | 1 | 2026-02-18 | 2026-02-19 | 2025-10-25 |  | FALSE | yes
| JD3RMRL51ST63659.R | Backfilling Works for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m - B6.33 42 11.07 - MR - L - 51 - ST - Remaining | 1 | 2026-02-21 | 2026-02-22 | 2025-10-25 |  | FALSE | yes
| JD3RMRL51ST63663.R | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - MR - L - 51 - ST - Remaining | 1 | 2026-02-21 | 2026-02-22 |  |  | FALSE | yes
| JD3RMRL51ST63664.R | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - MR - L - 51 - ST - Remaining | 1 | 2026-02-23 | 2026-02-24 |  |  | FALSE | yes
| JD3RMRL51ST63673.R | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - MR - L - 51 - ST - Remaining | 1 | 2026-02-23 | 2026-02-24 | 2025-10-25 |  | FALSE | yes
| JD3RMRL51ST63674.R | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - MR - L - 51 - ST - Remaining | 1 | 2026-02-25 | 2026-02-26 | 2025-10-26 |  | FALSE | yes
| JD3RMRL51ST63683.R | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - MR - L - 51 - ST - Remaining | 1 | 2026-02-28 | 2026-03-01 | 2025-10-25 |  | FALSE | yes
| JD3RMRL51ST63684.R | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - MR - L - 51 - ST - Remaining | 1 | 2026-03-02 | 2026-03-03 | 2025-10-27 |  | FALSE | yes
| JD3RMRL51ST63695.R | Excavation Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m - B6.33 42 11.15 - MR - L - 51 - ST - Remaining | 1 | 2026-02-23 | 2026-02-24 | 2025-09-20 |  | FALSE | yes
| JD3RMRL51ST63696.R | Soil Replacement and Bedding Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m - B6.33 42 11.15 - MR - L - 51 | 1 | 2026-02-25 | 2026-02-26 | 2025-09-22 |  | FALSE | yes
| JD3RMRL51ST63697.R | Installing for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m - B6.33 42 11.15 - MR - L - 51 - ST - Remaining | 1 | 2026-02-28 | 2026-03-01 | 2025-09-24 |  | FALSE | yes
| JD3RMRL51ST63698.R | Primary Test for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m - B6.33 42 11.15 - MR - L - 51 - ST - Remaining | 1 | 2026-03-02 | 2026-03-03 |  |  | FALSE | yes
| JD3RMRL51ST63699.R | Backfilling Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m - B6.33 42 11.15 - MR - L - 51 - ST - Remaining | 1 | 2026-03-07 | 2026-03-08 |  |  | FALSE | yes
| JD3RMRL51ST63713.R | Primary Test for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m - B6.33 42 11.20 - MR - L - 51 - ST - Remaining | 1 | 2026-03-07 | 2026-03-08 | 2025-08-20 |  | FALSE | yes
| JD3RMRL51ST63714.R | Backfilling Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m - B6.33 42 11.20 - MR - L - 51 - ST - Remaining | 1 | 2026-03-14 | 2026-03-15 | 2025-08-23 |  | FALSE | yes
| JD3RMRL51ST63729.R | Backfilling Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - L - 51 - ST - Remaining | 1 | 2026-03-02 | 2026-03-03 | 2025-08-25 |  | FALSE | yes
| JD3RMRL51ST63803.R | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - MR - L - 51 - ST - Remaining | 1 | 2026-03-02 | 2026-03-03 |  |  | FALSE | yes
| JD3RMRL51ST63804.R | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - MR - L - 51 - ST - Remaining | 1 | 2026-03-05 | 2026-03-07 |  |  | FALSE | yes
| JD3RMRL51ST63805.R | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - MR - L - 51 - ST - Remainin | 1 | 2026-03-11 | 2026-03-12 | 2025-09-16 |  | FALSE | yes
| JD3RMRL51ST63806 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - MR - L - 51 - ST | 1 | 2026-03-14 | 2026-03-16 |  |  | FALSE | yes
| JD3RMRL51ST63807 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - MR - L - 51 - ST | 1 | 2026-03-17 | 2026-03-19 |  |  | FALSE | yes
| JD3RMRL51ST63816 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - L - 51 - ST | 1 | 2026-03-11 | 2026-03-12 |  |  | FALSE | yes
| JD3RMRL51ST63817 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - L - 51 - ST | 1 | 2026-03-14 | 2026-03-15 |  |  | FALSE | yes
| JD3RMRL51ST63818 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - L - 51 - ST | 1 | 2026-01-13 | 2026-01-14 | 2025-09-16 |  | FALSE | yes
| JD3RMRL51ST63819 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - L - 51 - ST | 1 | 2026-01-15 | 2026-01-19 | 2025-09-22 |  | FALSE | yes
| JD3RMRL51ST63820 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - L - 51 - ST | 1 | 2026-01-20 | 2026-01-24 | 2025-10-20 |  | FALSE | yes
| JD3RMRL51ST63821 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - L - 51 - ST | 1 | 2026-01-25 | 2026-01-27 |  |  | FALSE | yes
| JD3RMRL51ST63822 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - L - 51 - ST | 1 | 2026-01-28 | 2026-01-31 |  |  | FALSE | yes
| JD3RMRL51ST63828 | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - L - 51 - ST | 1 | 2026-01-15 | 2026-01-17 |  |  | FALSE | yes
| JD3RMRL51ST63829 | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - L - 51 - ST | 1 | 2026-01-18 | 2026-01-19 |  |  | FALSE | yes
| JD3RMRL51ST63830 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - L - 51 - ST | 1 | 2026-01-20 | 2026-01-21 |  |  | FALSE | yes
| JD3RMRL51ST63831 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - L - 51 - ST | 1 | 2026-01-22 | 2026-01-24 |  |  | FALSE | yes
| JD3RMRL51ST63832 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - L - 51 - ST | 1 | 2026-01-25 | 2026-01-26 |  |  | FALSE | yes
| JD3RMRL51ST63833.R | Excavation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - MR - L - 51 - ST - Remaining | 1 | 2026-03-07 | 2026-03-08 | 2025-09-20 |  | FALSE | yes
| JD3RMRL51ST63834.R | Base Plain Concrete Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - MR - L - 51 - ST - Remaining | 1 | 2026-03-10 | 2026-03-11 | 2025-09-23 |  | FALSE | yes
| JD3RMRL51ST63835.R | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - MR - L - 51 - ST - Remainin | 1 | 2026-03-16 | 2026-03-17 | 2025-09-25 |  | FALSE | yes
| JD3RMRL51ST63836 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - MR - L - 51 - ST | 1 | 2026-03-18 | 2026-03-21 |  |  | FALSE | yes
| JD3RMRL51ST63837 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - MR - L - 51 - ST | 1 | 2026-03-22 | 2026-03-24 |  |  | FALSE | yes
| JD3RMRL51ST63838 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - MR - L - 51 - ST | 1 | 2026-01-18 | 2026-01-26 | 2025-10-11 |  | FALSE | yes
| JD3RMRL51ST63839 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - MR - L - 51 - ST | 1 | 2026-01-27 | 2026-02-08 |  |  | FALSE | yes
| JD3RMRL51ST63840 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - MR - L - 51 - ST | 1 | 2026-02-09 | 2026-02-21 |  |  | FALSE | yes
| JD3RMRL51ST63841 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - MR - L - 51 - ST | 1 | 2026-02-22 | 2026-03-02 |  |  | FALSE | yes
| JD3RMRL51ST63842 | EXCAVATION Works for Catchbasine double - B6.33 05 39.10 - MR - L - 51 - ST | 1 | 2026-01-27 | 2026-02-03 |  |  | FALSE | yes
| JD3RMRL51ST63843 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - MR - L - 51 - ST | 1 | 2026-02-04 | 2026-02-15 |  |  | FALSE | yes
| JD3RMRL51ST63844 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - MR - L - 51 - ST | 1 | 2026-02-16 | 2026-02-26 |  |  | FALSE | yes
| JD3RMRL51ST63845 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - MR - L - 51 - ST | 1 | 2026-02-28 | 2026-03-07 |  |  | FALSE | yes
| JD3RMRL51TC64176 | Excavation Worksfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - MR - L - 51 - TC | 1 | 2026-06-16 | 2026-06-18 |  |  | FALSE | yes
| JD3RMRL51TC64177 | Installationfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - MR - L - 51 - TC | 1 | 2026-06-20 | 2026-06-27 |  |  | FALSE | yes
| JD3RMRL51TC64178 | Pouring Concrete Coverfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - MR - L - 51 - TC | 1 | 2026-06-28 | 2026-07-05 |  |  | FALSE | yes
| JD3RMRL51TC64179 | Backfilling Worksfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - MR - L - 51 - TC | 1 | 2026-07-06 | 2026-07-08 |  |  | FALSE | yes
| JD3RMRL51TC64180 | Excavation and Bedding Worksfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - MR - L - 51 - TC | 1 | 2026-06-20 | 2026-06-23 |  |  | FALSE | yes
| JD3RMRL51TC64181 | Installationfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - MR - L - 51 - TC | 1 | 2026-06-24 | 2026-06-28 |  |  | FALSE | yes
| JD3RMRL51TC64182 | Backfilling Worksfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - MR - L - 51 - TC | 1 | 2026-06-29 | 2026-07-02 |  |  | FALSE | yes
| JD3RMRL51TSE63896 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - L - 51 - TSE | 1 | 2026-03-25 | 2026-03-26 |  |  | FALSE | yes
| JD3RMRL51TSE63897 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - L - 51 - TS | 1 | 2026-03-28 | 2026-03-29 |  |  | FALSE | yes
| JD3RMRL51TSE63898 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - L - 51 - TSE | 1 | 2026-03-30 | 2026-04-01 |  |  | FALSE | yes
| JD3RMRL51TSE63899 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - L - 51 - TSE | 1 | 2026-04-02 | 2026-04-04 |  |  | FALSE | yes
| JD3RMRL51TSE63900 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - L - 51 - TSE | 1 | 2026-05-07 | 2026-05-09 |  |  | FALSE | yes
| JD3RMRL51TSE63901.R | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - L - 51 - TSE - Remaining | 1 | 2026-04-04 | 2026-04-05 | 2025-10-05 |  | FALSE | yes
| JD3RMRL51TSE63902.R | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - L - 51 - TS | 1 | 2026-04-12 | 2026-04-13 | 2025-10-07 |  | FALSE | yes
| JD3RMRL51TSE63903.R | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - L - 51 - TSE - Remaining | 1 | 2026-04-26 | 2026-04-27 | 2025-10-05 |  | FALSE | yes
| JD3RMRL51TSE63904.R | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - L - 51 - TSE - Remaining | 1 | 2026-05-05 | 2026-05-06 | 2025-10-22 |  | FALSE | yes
| JD3RMRL51TSE63905.R | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - MR - L - 51 - TSE - Remaining | 1 | 2026-05-14 | 2026-05-16 | 2025-10-25 |  | FALSE | yes
| JD3RMRL51TSE63906 | Excavation Worksfor HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - L - 51 - TSE | 1 | 2026-04-04 | 2026-04-05 |  |  | FALSE | yes
| JD3RMRL51TSE63907 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - L - 51 - TSE | 1 | 2026-04-06 | 2026-04-07 |  |  | FALSE | yes
| JD3RMRL51TSE63908 | Installing for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - L - 51 - TSE | 1 | 2026-04-08 | 2026-04-09 |  |  | FALSE | yes
| JD3RMRL51TSE63909 | Testing for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - L - 51 - TSE | 1 | 2026-04-11 | 2026-04-12 |  |  | FALSE | yes
| JD3RMRL51TSE63910 | Backfillingfor HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - MR - L - 51 - TSE | 1 | 2026-05-07 | 2026-05-09 |  |  | FALSE | yes
| JD3RMRL51TSE63911.R | Excavation Worksfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - MR - L - 51 - TSE - Remaining | 1 | 2026-04-12 | 2026-04-13 |  |  | FALSE | yes
| JD3RMRL51TSE63912.R | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - MR - L - 51 - TSE | 1 | 2026-04-19 | 2026-04-20 |  |  | FALSE | yes
| JD3RMRL51TSE63913.R | Installing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - MR - L - 51 - TSE - Remaining | 1 | 2026-04-30 | 2026-05-02 |  |  | FALSE | yes
| JD3RMRL51TSE63914 | Testing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - MR - L - 51 - TSE | 1 | 2026-05-03 | 2026-05-10 |  |  | FALSE | yes
| JD3RMRL51TSE63915 | Backfillingfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - MR - L - 51 - TSE | 1 | 2026-05-17 | 2026-05-24 |  |  | FALSE | yes
| JD3RMRL51TSE63949 | Testing for HDPE Pipes 450 mm - depth from 2.51 to 3.5 m - B4.33 31 00.11 - MR - L - 51 - TSE | 1 | 2026-04-01 | 2026-04-02 |  |  | FALSE | yes
| JD3RMRL51TSE63950 | Backfillingfor HDPE Pipes 450 mm - depth from 2.51 to 3.5 m - B4.33 31 00.11 - MR - L - 51 - TSE | 1 | 2026-05-07 | 2026-05-09 |  |  | FALSE | yes
| JD3RMRL51TSE63969 | Testing for HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - L - 51 - TSE | 1 | 2026-04-01 | 2026-04-02 |  |  | FALSE | yes
| JD3RMRL51TSE63970 | Backfillingfor HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - L - 51 - TSE | 1 | 2026-05-07 | 2026-05-09 |  |  | FALSE | yes
| JD3RMRL51TSE63974 | Testing for HDPE Pipes 630 mm - depth from 1.51 to 2.5 m - B4.33 31 00.16 - MR - L - 51 - TSE | 1 | 2026-04-01 | 2026-04-02 |  |  | FALSE | yes
| JD3RMRL51TSE63975 | Backfillingfor HDPE Pipes 630 mm - depth from 1.51 to 2.5 m - B4.33 31 00.16 - MR - L - 51 - TSE | 1 | 2026-05-07 | 2026-05-09 |  |  | FALSE | yes
| JD3RMRL51TSE63979 | Testing for HDPE Pipes 630 mm - depth from 2.51 to 3.5 m - B4.33 31 00.17 - MR - L - 51 - TSE | 1 | 2026-04-01 | 2026-04-02 |  |  | FALSE | yes
| JD3RMRL51TSE63980 | Backfillingfor HDPE Pipes 630 mm - depth from 2.51 to 3.5 m - B4.33 31 00.17 - MR - L - 51 - TSE | 1 | 2026-04-04 | 2026-04-05 |  |  | FALSE | yes
| JD3RMRL51TSE64021 | Installationfor gate valves 100 mm - B4.33 14 19.01 - MR - L - 51 - TSE | 1 | 2026-05-10 | 2026-05-12 |  |  | FALSE | yes
| JD3RMRL51TSE64022 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - MR - L - 51 - TSE | 1 | 2026-05-13 | 2026-05-16 |  |  | FALSE | yes
| JD3RMRL51TSE64023 | Installationfor gate valves 250 mm - B4.33 14 19.02 - MR - L - 51 - TSE | 1 | 2026-05-03 | 2026-05-04 |  |  | FALSE | yes
| JD3RMRL51TSE64024 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - MR - L - 51 - TSE | 1 | 2026-05-05 | 2026-05-06 |  |  | FALSE | yes
| JD3RMRL51TSE64025 | Installationfor butterfly valves 300 mm. - B4.33 14 19.03 - MR - L - 51 - TSE | 1 | 2026-05-03 | 2026-05-04 |  |  | FALSE | yes
| JD3RMRL51TSE64026 | Testing And Commtionningfor butterfly valves 300 mm. - B4.33 14 19.03 - MR - L - 51 - TSE | 1 | 2026-05-10 | 2026-05-11 |  |  | FALSE | yes
| JD3RMRL51TSE64027 | Installationfor butterfly valves 400 mm. - B4.33 14 19.04 - MR - L - 51 - TSE | 1 | 2026-05-03 | 2026-05-04 |  |  | FALSE | yes
| JD3RMRL51TSE64028 | Testing And Commtionningfor butterfly valves 400 mm. - B4.33 14 19.04 - MR - L - 51 - TSE | 1 | 2026-05-07 | 2026-05-09 |  |  | FALSE | yes
| JD3RMRL51TSE64029 | Installationfor butterfly valves 600 mm. - B4.33 14 19.05 - MR - L - 51 - TSE | 1 | 2026-05-03 | 2026-05-04 |  |  | FALSE | yes
| JD3RMRL51TSE64030 | Testing And Commtionningfor butterfly valves 600 mm. - B4.33 14 19.05 - MR - L - 51 - TSE | 1 | 2026-05-05 | 2026-05-06 |  |  | FALSE | yes
| JD3RMRL51TSE64039 | Installationfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - MR - L - 51 - TSE | 1 | 2026-05-03 | 2026-05-04 |  |  | FALSE | yes
| JD3RMRL51TSE64040 | Testing And Commtionningfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - MR - L - 51 - | 1 | 2026-05-05 | 2026-05-06 |  |  | FALSE | yes
| JD3RMRL51TSE64041 | Installationfor Air valves 65 mm. - on pipes with diameter 355 - 630 mm - B4.33 14 19.16 - MR - L - 51 - TSE | 1 | 2026-05-03 | 2026-05-04 |  |  | FALSE | yes
| JD3RMRL51TSE64042 | Testing And Commtionningfor Air valves 65 mm. - on pipes with diameter 355 - 630 mm - B4.33 14 19.16 - MR - L - 51 - TSE | 1 | 2026-05-05 | 2026-05-06 |  |  | FALSE | yes
| JD3RMRL51TSE64045 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - L - 51 - TSE | 1 | 2026-03-25 | 2026-03-26 |  |  | FALSE | yes
| JD3RMRL51TSE64046 | Plain Concrete Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - L - 51 - TSE | 1 | 2026-03-28 | 2026-03-29 |  |  | FALSE | yes
| JD3RMRL51TSE64047 | INSTALLATIONfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - L - 51 - TSE | 1 | 2026-03-30 | 2026-03-31 |  |  | FALSE | yes
| JD3RMRL51TSE64048 | Backfilling Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - L - 51 - TSE | 1 | 2026-04-01 | 2026-04-02 |  |  | FALSE | yes
| JD3RMRL51TSE64049 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 500 to 630 MM - B4.33 14 13.02 - MR - L - 51 - TSE | 1 | 2026-03-25 | 2026-03-26 |  |  | FALSE | yes
| JD3RMRL51TSE64050 | Plain Concrete Worksfor R.C Valve Chamber - 500 to 630 MM - B4.33 14 13.02 - MR - L - 51 - TSE | 1 | 2026-03-28 | 2026-03-29 |  |  | FALSE | yes
| JD3RMRL51TSE64051 | INSTALLATIONfor R.C Valve Chamber - 500 to 630 MM - B4.33 14 13.02 - MR - L - 51 - TSE | 1 | 2026-03-30 | 2026-03-31 |  |  | FALSE | yes
| JD3RMRL51TSE64052 | Backfilling Worksfor R.C Valve Chamber - 500 to 630 MM - B4.33 14 13.02 - MR - L - 51 - TSE | 1 | 2026-04-01 | 2026-04-02 |  |  | FALSE | yes
| JD3RMRL51TSE64069 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - L - 51 - TSE | 1 | 2026-03-25 | 2026-03-26 |  |  | FALSE | yes
| JD3RMRL51TSE64070 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - L - 51 - TSE | 1 | 2026-03-28 | 2026-03-29 |  |  | FALSE | yes
| JD3RMRL51TSE64071 | INSTALLATIONfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - L - 51 - TSE | 1 | 2026-03-30 | 2026-03-31 |  |  | FALSE | yes
| JD3RMRL51TSE64072 | Backfilling Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - L - 51 - TSE | 1 | 2026-04-01 | 2026-04-02 |  |  | FALSE | yes
| JD3RMRL51TSE64073 | EXCAVATION and Bedding Worksfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - L - 51 - TSE | 1 | 2026-03-25 | 2026-03-26 |  |  | FALSE | yes
| JD3RMRL51TSE64074 | Plain Concrete Worksfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - L - 51 - TSE | 1 | 2026-03-28 | 2026-03-29 |  |  | FALSE | yes
| JD3RMRL51TSE64075 | INSTALLATIONfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - L - 51 - TSE | 1 | 2026-03-30 | 2026-03-31 |  |  | FALSE | yes
| JD3RMRL51TSE64076 | Backfilling Worksfor Air Valve Chamber - on 355 - 630 mm - B4.33 14 13.11 - MR - L - 51 - TSE | 1 | 2026-04-01 | 2026-04-02 |  |  | FALSE | yes
| JD3RMRL51WT63846 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - MR - L - 51 - WT | 1 | 2026-05-07 | 2026-05-10 | 2025-09-20 |  | FALSE | yes
| JD3RMRL51WT63847 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - MR - L - 51 - WT | 1 | 2026-05-11 | 2026-05-13 | 2025-09-23 |  | FALSE | yes
| JD3RMRL51WT63848 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - MR - L - 51 - WT | 1 | 2026-05-14 | 2026-05-19 | 2025-09-27 |  | FALSE | yes
| JD3RMRL51WT63849 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - MR - L - 51 - WT | 1 | 2026-05-20 | 2026-05-23 |  |  | FALSE | yes
| JD3RMRL51WT63850 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - MR - L - 51 - WT | 1 | 2026-06-08 | 2026-06-10 |  |  | FALSE | yes
| JD3RMRL51WT63854 | Testing for HDPE Pipes 225 mm - depth from 0 to 1.5 m - B3.33 14 13.02 - MR - L - 51 - WT | 1 | 2026-05-25 | 2026-05-28 |  |  | FALSE | yes
| JD3RMRL51WT63855 | Backfillingfor HDPE Pipes 225 mm - depth from 0 to 1.5 m - B3.33 14 13.02 - MR - L - 51 - WT | 1 | 2026-06-08 | 2026-06-11 |  |  | FALSE | yes
| JD3RMRL51WT63856 | Excavation Worksfor HDPE Pipes 450 mm - depth from 0 to 1.5 m - B3.33 14 13.03 - MR - L - 51 - WT | 1 | 2026-05-25 | 2026-05-26 |  |  | FALSE | yes
| JD3RMRL51WT63857 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B3.33 14 13.03 - MR - L - 51 - WT | 1 | 2026-05-27 | 2026-05-28 |  |  | FALSE | yes
| JD3RMRL51WT63858 | Installing for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B3.33 14 13.03 - MR - L - 51 - WT | 1 | 2026-05-30 | 2026-06-01 |  |  | FALSE | yes
| JD3RMRL51WT63859 | Testing for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B3.33 14 13.03 - MR - L - 51 - WT | 1 | 2026-06-02 | 2026-06-03 |  |  | FALSE | yes
| JD3RMRL51WT63860 | Backfillingfor HDPE Pipes 450 mm - depth from 0 to 1.5 m - B3.33 14 13.03 - MR - L - 51 - WT | 1 | 2026-06-08 | 2026-06-09 |  |  | FALSE | yes
| JD3RMRL51WT63861 | Excavation Worksfor HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B3.33 14 13.04 - MR - L - 51 - WT | 1 | 2026-05-27 | 2026-05-28 |  |  | FALSE | yes
| JD3RMRL51WT63862 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B3.33 14 13.04 - MR - L - 51 - WT | 1 | 2026-05-30 | 2026-05-31 |  |  | FALSE | yes
| JD3RMRL51WT63863 | Installing for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B3.33 14 13.04 - MR - L - 51 - WT | 1 | 2026-06-01 | 2026-06-02 |  |  | FALSE | yes
| JD3RMRL51WT63864 | Testing for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B3.33 14 13.04 - MR - L - 51 - WT | 1 | 2026-06-03 | 2026-06-04 |  |  | FALSE | yes
| JD3RMRL51WT63865 | Backfillingfor HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B3.33 14 13.04 - MR - L - 51 - WT | 1 | 2026-06-08 | 2026-06-09 |  |  | FALSE | yes
| JD3RMRL51WT63871 | INSTALLATIONfor gate valves 150 mm - B3.33 14 19.01 - MR - L - 51 - WT | 1 | 2026-06-03 | 2026-06-04 |  |  | FALSE | yes
| JD3RMRL51WT63872 | TESTING AND COMMITIONfor gate valves 150 mm - B3.33 14 19.01 - MR - L - 51 - WT | 1 | 2026-06-06 | 2026-06-07 |  |  | FALSE | yes
| JD3RMRL51WT63873 | INSTALLATIONfor gate valves 200 mm - B3.33 14 19.02 - MR - L - 51 - WT | 1 | 2026-06-03 | 2026-06-04 |  |  | FALSE | yes
| JD3RMRL51WT63874 | TESTING AND COMMITIONfor gate valves 200 mm - B3.33 14 19.02 - MR - L - 51 - WT | 1 | 2026-06-06 | 2026-06-07 |  |  | FALSE | yes
| JD3RMRL51WT63875 | INSTALLATIONfor Butterfly Valves 300 mm - B3.33 14 19.03 - MR - L - 51 - WT | 1 | 2026-06-03 | 2026-06-04 |  |  | FALSE | yes
| JD3RMRL51WT63876 | TESTING AND COMMITIONfor Butterfly Valves 300 mm - B3.33 14 19.03 - MR - L - 51 - WT | 1 | 2026-06-06 | 2026-06-07 |  |  | FALSE | yes
| JD3RMRL51WT63877 | INSTALLATIONfor Wash - Out Valve 100 mm - B3.33 14 19.05 - MR - L - 51 - WT | 1 | 2026-06-03 | 2026-06-04 |  |  | FALSE | yes
| JD3RMRL51WT63878 | TESTING AND COMMITIONfor Wash - Out Valve 100 mm - B3.33 14 19.05 - MR - L - 51 - WT | 1 | 2026-06-06 | 2026-06-07 |  |  | FALSE | yes
| JD3RMRL51WT63879 | INSTALLATIONfor Air Valve 50 mm - B3.33 14 19.06 - MR - L - 51 - WT | 1 | 2026-06-03 | 2026-06-04 |  |  | FALSE | yes
| JD3RMRL51WT63880 | TESTING AND COMMITIONfor Air Valve 50 mm - B3.33 14 19.06 - MR - L - 51 - WT | 1 | 2026-06-06 | 2026-06-07 |  |  | FALSE | yes
| JD3RMRL51WT63881 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - MR - L - 51 - WT | 1 | 2026-05-25 | 2026-05-27 |  |  | FALSE | yes
| JD3RMRL51WT63882 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - MR - L - 51 - WT | 1 | 2026-05-28 | 2026-06-02 |  |  | FALSE | yes
| JD3RMRL51WT63883 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - MR - L - 51 - WT | 1 | 2026-06-03 | 2026-06-07 |  |  | FALSE | yes
| JD3RMRL51WT63884 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 315 to 400 MM - B3.33 14 13.011 - MR - L - 51 - WT | 1 | 2026-05-25 | 2026-05-26 |  |  | FALSE | yes
| JD3RMRL51WT63885 | Plain Concrete Worksfor R.C Valve Chamber - 315 to 400 MM - B3.33 14 13.011 - MR - L - 51 - WT | 1 | 2026-05-27 | 2026-05-28 |  |  | FALSE | yes
| JD3RMRL51WT63886 | INSTALLATIONfor R.C Valve Chamber - 315 to 400 MM - B3.33 14 13.011 - MR - L - 51 - WT | 1 | 2026-05-30 | 2026-05-31 |  |  | FALSE | yes
| JD3RMRL51WT63887 | Backfilling Worksfor R.C Valve Chamber - 315 to 400 MM - B3.33 14 13.011 - MR - L - 51 - WT | 1 | 2026-06-08 | 2026-06-09 |  |  | FALSE | yes
| JD3RMRL51WT63888 | EXCAVATION and Bedding Worksfor Wash - out Valve Chamber - 110 to 400 MM - B3.33 14 13.06 - MR - L - 51 - WT | 1 | 2026-05-25 | 2026-05-26 |  |  | FALSE | yes
| JD3RMRL51WT63889 | Plain Concrete Worksfor Wash - out Valve Chamber - 110 to 400 MM - B3.33 14 13.06 - MR - L - 51 - WT | 1 | 2026-05-27 | 2026-05-28 |  |  | FALSE | yes
| JD3RMRL51WT63890 | INSTALLATIONfor Wash - out Valve Chamber - 110 to 400 MM - B3.33 14 13.06 - MR - L - 51 - WT | 1 | 2026-05-30 | 2026-05-31 |  |  | FALSE | yes
| JD3RMRL51WT63891 | Backfilling Worksfor Wash - out Valve Chamber - 110 to 400 MM - B3.33 14 13.06 - MR - L - 51 - WT | 1 | 2026-06-08 | 2026-06-09 |  |  | FALSE | yes
| JD3RMRL51WT63892 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 450 mm - B3.33 14 13.10 - MR - L - 51 - WT | 1 | 2026-05-25 | 2026-05-26 |  |  | FALSE | yes
| JD3RMRL51WT63893 | Plain Concrete Worksfor Air Valve Chamber - less than 450 mm - B3.33 14 13.10 - MR - L - 51 - WT | 1 | 2026-05-27 | 2026-05-28 |  |  | FALSE | yes
| JD3RMRL51WT63894 | INSTALLATIONfor Air Valve Chamber - less than 450 mm - B3.33 14 13.10 - MR - L - 51 - WT | 1 | 2026-05-30 | 2026-05-31 |  |  | FALSE | yes
| JD3RMRL51WT63895 | Backfilling Worksfor Air Valve Chamber - less than 450 mm - B3.33 14 13.10 - MR - L - 51 - WT | 1 | 2026-06-08 | 2026-06-09 |  |  | FALSE | yes
| JD3RMRL58SL64820 | Excavation Worksfor Copper Cables 4Cx6 mm² - B2.26 05 19.01 - MR - L - 58 - SL | 1 | 2026-06-14 | 2026-06-16 |  |  | FALSE | yes
| JD3RMRL58SL64821 | Installationfor Copper Cables 4Cx6 mm² - B2.26 05 19.01 - MR - L - 58 - SL | 1 | 2026-06-17 | 2026-06-20 |  |  | FALSE | yes
| JD3RMRL58SL64822 | Backfilling, Warning Tabe Worksfor Copper Cables 4Cx6 mm² - B2.26 05 19.01 - MR - L - 58 - SL | 1 | 2026-06-21 | 2026-06-23 |  |  | FALSE | yes
| JD3RMRL58SL64823 | Testing and Commitioning for Copper Cables 4Cx6 mm² - B2.26 05 19.01 - MR - L - 58 - SL | 1 | 2026-06-28 | 2026-06-30 |  |  | FALSE | yes
| JD3RMRL58SL64844 | INSTALLINGfor insulated copper conductor 6 mm² - B2.26 05 19.07 - MR - L - 58 - SL | 1 | 2026-06-21 | 2026-06-23 |  |  | FALSE | yes
| JD3RMRL58SL64845 | TESTING AND COMMITIONINGfor insulated copper conductor 6 mm² - B2.26 05 19.07 - MR - L - 58 - SL | 1 | 2026-06-24 | 2026-06-27 |  |  | FALSE | yes
| JD3RMRL58SL64861 | Supply, construct, connect and test earthing pitsfor Street Lighting EARTHING SYSTEM - B2.26 05 26.01 - MR - L - 58 - SL | 1 | 2026-06-24 | 2026-06-25 |  |  | FALSE | yes
| JD3RMRL58SL64862 | Excavation Worksfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - MR - L - 58 - SL | 1 | 2026-06-14 | 2026-06-15 |  |  | FALSE | yes
| JD3RMRL58SL64863 | Installationfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - MR - L - 58 - SL | 1 | 2026-06-16 | 2026-06-17 |  |  | FALSE | yes
| JD3RMRL58SL64864 | Pouring Concrete Coverfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - MR - L - 58 - SL | 1 | 2026-06-18 | 2026-06-20 |  |  | FALSE | yes
| JD3RMRL58SL64865 | Testing and Backfilling Worksfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - MR - L - 58 - SL | 1 | 2026-06-21 | 2026-06-22 |  |  | FALSE | yes
| JD3RMRL58SL64866 | Excavation Worksfor PVC Pipes 4×150mm - B2.33 71 19.02 - MR - L - 58 - SL | 1 | 2026-06-14 | 2026-06-15 |  |  | FALSE | yes
| JD3RMRL58SL64867 | Installationfor PVC Pipes 4×150mm - B2.33 71 19.02 - MR - L - 58 - SL | 1 | 2026-06-16 | 2026-06-17 |  |  | FALSE | yes
| JD3RMRL58SL64868 | Pouring Concrete Coverfor PVC Pipes 4×150mm - B2.33 71 19.02 - MR - L - 58 - SL | 1 | 2026-06-18 | 2026-06-20 |  |  | FALSE | yes
| JD3RMRL58SL64869 | Testing and Backfilling Worksfor PVC Pipes 4×150mm - B2.33 71 19.02 - MR - L - 58 - SL | 1 | 2026-06-21 | 2026-06-22 |  |  | FALSE | yes
| JD3RMRL58SL64877 | Excavationfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - MR - L - 58 - SL | 1 | 2026-06-14 | 2026-06-15 |  |  | FALSE | yes
| JD3RMRL58SL64878 | Installationfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - MR - L - 58 - SL | 1 | 2026-06-16 | 2026-06-17 |  |  | FALSE | yes
| JD3RMRL58SL64879 | Backfillingfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - MR - L - 58 - SL | 1 | 2026-06-18 | 2026-06-20 |  |  | FALSE | yes
| JD3RMRL58ST100 | Channel excavation for Swales - B6.31 22 00.13 - MR - L - 58 - ST | 1 | 2025-09-28 | 2025-10-11 | 2025-10-30 |  | FALSE | FALSE
| JD3RMRL58ST300 | Riprap with side slopes 1.5:1 for Swales - NB6.31 22 00.16 - MR - L - 58 - ST | 1 | 2025-10-12 | 2025-10-26 | 2025-11-03 |  | FALSE | FALSE
| JD3RMRL58ST524362 | Concrete encasement for pipes - NNB6.33 42 11.25 - MR - L - 58 - ST | 1 | 2025-12-11 | 2025-12-17 |  |  | FALSE | yes
| JD3RMRL58ST64333 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - L - 58 - ST | 1 | 2025-10-16 | 2025-10-22 | 2025-09-03 |  | FALSE | yes
| JD3RMRL58ST64334 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - L - 58 | 1 | 2025-10-23 | 2025-10-30 | 2025-09-05 |  | FALSE | yes
| JD3RMRL58ST64335 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - L - 58 - ST | 1 | 2025-11-01 | 2025-11-09 | 2025-09-15 |  | FALSE | yes
| JD3RMRL58ST64336 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - L - 58 - ST | 1 | 2025-11-10 | 2025-11-18 |  |  | FALSE | yes
| JD3RMRL58ST64337 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - MR - L - 58 - ST | 1 | 2025-12-18 | 2025-12-30 |  |  | FALSE | yes
| JD3RMRL58ST64338 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - MR - L - 58 - ST | 1 | 2025-10-12 | 2025-10-15 |  |  | FALSE | yes
| JD3RMRL58ST64339 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - MR - L - 58 - | 1 | 2025-10-16 | 2025-10-20 |  |  | FALSE | yes
| JD3RMRL58ST64340 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - MR - L - 58 - ST | 1 | 2025-10-21 | 2025-10-25 |  |  | FALSE | yes
| JD3RMRL58ST64341 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - MR - L - 58 - ST | 1 | 2025-10-26 | 2025-10-29 |  |  | FALSE | yes
| JD3RMRL58ST64342 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - MR - L - 58 - ST | 1 | 2025-10-30 | 2025-11-04 |  |  | FALSE | yes
| JD3RMRL58ST64343.R | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - MR - L - 58 - ST - Remaining | 1 | 2025-11-10 | 2025-11-11 | 2025-08-23 |  | FALSE | yes
| JD3RMRL58ST64344.R | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - MR - L - 58 - | 1 | 2025-11-15 | 2025-11-16 | 2025-08-26 |  | FALSE | yes
| JD3RMRL58ST64345.R | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - MR - L - 58 - ST - Remaining | 1 | 2025-11-20 | 2025-11-22 | 2025-10-05 |  | FALSE | yes
| JD3RMRL58ST64346.R | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - MR - L - 58 - ST - Remaining | 1 | 2025-11-25 | 2025-11-26 | 2025-08-28 |  | FALSE | yes
| JD3RMRL58ST64347.R | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - MR - L - 58 - ST - Remaining | 1 | 2025-12-02 | 2025-12-03 |  |  | FALSE | yes
| JD3RMRL58ST64352.R | Backfilling Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m - B6.33 42 11.03 - MR - L - 58 - ST - Remaining | 1 | 2025-11-24 | 2025-11-25 |  |  | FALSE | yes
| JD3RMRL58ST64356 | Primary Test for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - MR - L - 58 - ST | 1 | 2025-11-22 | 2025-11-23 |  |  | FALSE | yes
| JD3RMRL58ST64357 | Backfilling Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - MR - L - 58 - ST | 1 | 2025-11-24 | 2025-11-25 |  |  | FALSE | yes
| JD3RMRL58ST64366 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - L - 58 - ST | 1 | 2025-11-29 | 2025-12-01 | 2025-08-20 |  | FALSE | yes
| JD3RMRL58ST64367 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - MR - L - 58 - ST | 1 | 2025-12-02 | 2025-12-07 | 2025-08-24 |  | FALSE | yes
| JD3RMRL58ST64376 | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - MR - L - 58 - ST | 1 | 2025-12-09 | 2025-12-10 |  |  | FALSE | yes
| JD3RMRL58ST64377 | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - MR - L - 58 - ST | 1 | 2025-12-11 | 2025-12-13 |  |  | FALSE | yes
| JD3RMRL58ST64381 | Primary Test for GRP Pipe Line 800 mm - depth from 0.00 to 1.50 m - B6.33 42 11.09 - MR - L - 58 - ST | 1 | 2025-12-11 | 2025-12-13 |  |  | FALSE | yes
| JD3RMRL58ST64382 | Backfilling Works for GRP Pipe Line 800 mm - depth from 0.00 to 1.50 m - B6.33 42 11.09 - MR - L - 58 - ST | 1 | 2025-12-14 | 2025-12-15 |  |  | FALSE | yes
| JD3RMRL58ST64386 | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - MR - L - 58 - ST | 1 | 2025-12-16 | 2025-12-17 |  |  | FALSE | yes
| JD3RMRL58ST64387 | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - MR - L - 58 - ST | 1 | 2025-12-18 | 2025-12-20 |  |  | FALSE | yes
| JD3RMRL58ST64427 | Backfilling Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m - B6.33 42 11.20 - MR - L - 58 - ST | 1 | 2025-12-16 | 2025-12-17 | 2025-08-23 |  | FALSE | yes
| JD3RMRL58ST64438 | Excavation Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - L - 58 - ST | 1 | 2025-12-09 | 2025-12-16 | 2025-08-15 |  | FALSE | yes
| JD3RMRL58ST64439 | Soil Replacement and Bedding Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - L - 58 | 1 | 2025-12-17 | 2025-12-24 | 2025-08-20 |  | FALSE | yes
| JD3RMRL58ST64440 | Installing for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - L - 58 - ST | 1 | 2025-12-25 | 2026-01-03 | 2025-08-24 |  | FALSE | yes
| JD3RMRL58ST64441 | Primary Test for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - L - 58 - ST | 1 | 2026-01-04 | 2026-01-11 | 2025-08-29 |  | FALSE | yes
| JD3RMRL58ST64442 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - MR - L - 58 - ST | 1 | 2026-01-12 | 2026-01-22 | 2025-08-31 |  | FALSE | yes
| JD3RMRL58ST64471.R | Raft Foundation for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - L - 58 - ST | 1 | 2025-12-25 | 2025-12-27 | 2025-08-20 |  | FALSE | yes
| JD3RMRL58ST64472.R | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - L - 58 - ST | 1 | 2026-01-13 | 2026-01-14 | 2025-08-23 |  | FALSE | yes
| JD3RMRL58ST64473.R | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - L - 58 - ST | 1 | 2026-02-01 | 2026-02-02 | 2025-08-24 |  | FALSE | yes
| JD3RMRL58ST64474.R | Isolation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - L - 58 - ST | 1 | 2026-02-16 | 2026-02-17 | 2025-08-26 |  | FALSE | yes
| JD3RMRL58ST64475.R | Backfilling Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - MR - L - 58 - ST | 1 | 2026-02-21 | 2026-02-22 | 2025-08-30 |  | FALSE | yes
| JD3RMRL58ST64499 | Raft Foundation for Box Culvert Dim (4000x2000) depth from 3.51 to 4.50 - B6.34 42 16.08 - MR - L - 58 - ST | 1 | 2026-02-28 | 2026-03-01 | 2025-10-15 |  | FALSE | yes
| JD3RMRL58ST64500 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.08 - MR - L - 58 - ST | 1 | 2026-03-02 | 2026-03-03 | 2025-10-18 |  | FALSE | yes
| JD3RMRL58ST64501 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.08 - MR - L - 58 - ST | 1 | 2026-03-04 | 2026-03-05 | 2025-10-19 |  | FALSE | yes
| JD3RMRL58ST64502 | Isolation Works for Box Culvert Dim (4000x2000) depth from 3.51 to 4.50 - B6.34 42 16.08 - MR - L - 58 - ST | 1 | 2026-03-07 | 2026-03-08 | 2025-10-20 |  | FALSE | yes
| JD3RMRL58ST64503 | Backfilling Works for Box Culvert Dim (4000x2000) depth from 3.51 to 4.50 - B6.34 42 16.08 - MR - L - 58 - ST | 1 | 2026-03-09 | 2026-03-10 | 2025-10-21 |  | FALSE | yes
| JD3RMRL58ST64516.R | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - MR - L - 58 - ST - Remaining | 1 | 2025-12-17 | 2025-12-18 |  |  | FALSE | yes
| JD3RMRL58ST64517.R | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - MR - L - 58 - ST - Remaining | 1 | 2025-12-20 | 2025-12-21 |  |  | FALSE | yes
| JD3RMRL58ST64518.R | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - MR - L - 58 - ST - Remainin | 1 | 2025-12-27 | 2025-12-28 | 2025-10-26 |  | FALSE | yes
| JD3RMRL58ST64519 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - MR - L - 58 - ST | 1 | 2025-12-29 | 2025-12-31 |  |  | FALSE | yes
| JD3RMRL58ST64520 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - MR - L - 58 - ST | 1 | 2026-01-01 | 2026-01-04 |  |  | FALSE | yes
| JD3RMRL58ST64526.R | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - L - 58 - ST - Remaining | 1 | 2025-12-20 | 2025-12-21 |  |  | FALSE | yes
| JD3RMRL58ST64527 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - L - 58 - ST | 1 | 2025-12-22 | 2025-12-23 | 2025-10-25 |  | FALSE | yes
| JD3RMRL58ST64528 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - L - 58 - ST | 1 | 2025-12-24 | 2025-12-25 | 2025-10-26 |  | FALSE | yes
| JD3RMRL58ST64529 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - L - 58 - ST | 1 | 2025-12-27 | 2025-12-28 |  |  | FALSE | yes
| JD3RMRL58ST64530 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - MR - L - 58 - ST | 1 | 2025-12-29 | 2025-12-30 |  |  | FALSE | yes
| JD3RMRL58ST64531 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - L - 58 - ST | 1 | 2025-12-17 | 2025-12-18 |  |  | FALSE | yes
| JD3RMRL58ST64532 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - L - 58 - ST | 1 | 2025-12-20 | 2025-12-24 |  |  | FALSE | yes
| JD3RMRL58ST64533 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - L - 58 - ST | 1 | 2025-12-25 | 2025-12-30 |  |  | FALSE | yes
| JD3RMRL58ST64534 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - L - 58 - ST | 1 | 2025-12-31 | 2026-01-03 |  |  | FALSE | yes
| JD3RMRL58ST64535 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - MR - L - 58 - ST | 1 | 2026-01-04 | 2026-01-06 |  |  | FALSE | yes
| JD3RMRL58ST64541 | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - L - 58 - ST | 1 | 2025-12-20 | 2025-12-21 |  |  | FALSE | yes
| JD3RMRL58ST64542 | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - L - 58 - ST | 1 | 2025-12-22 | 2025-12-23 |  |  | FALSE | yes
| JD3RMRL58ST64543 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - L - 58 - ST | 1 | 2025-12-24 | 2025-12-25 |  |  | FALSE | yes
| JD3RMRL58ST64544 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - L - 58 - ST | 1 | 2025-12-27 | 2025-12-28 |  |  | FALSE | yes
| JD3RMRL58ST64545 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - MR - L - 58 - ST | 1 | 2025-12-29 | 2025-12-30 |  |  | FALSE | yes
| JD3RMRL58ST64546.R | Excavation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - MR - L - 58 - ST - Remaining | 1 | 2025-12-22 | 2025-12-23 |  |  | FALSE | yes
| JD3RMRL58ST64547.R | Base Plain Concrete Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - MR - L - 58 - ST - Remaining | 1 | 2025-12-24 | 2025-12-25 |  |  | FALSE | yes
| JD3RMRL58ST64548.R | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - MR - L - 58 - ST - Remainin | 1 | 2025-12-27 | 2025-12-28 |  |  | FALSE | yes
| JD3RMRL58ST64549 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - MR - L - 58 - ST | 1 | 2025-12-29 | 2025-12-30 |  |  | FALSE | yes
| JD3RMRL58ST64550 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - MR - L - 58 - ST | 1 | 2025-12-31 | 2026-01-01 |  |  | FALSE | yes
| JD3RMRL58ST64551 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - MR - L - 58 - ST | 1 | 2025-12-22 | 2025-12-29 | 2025-10-25 |  | FALSE | yes
| JD3RMRL58ST64552 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - MR - L - 58 - ST | 1 | 2025-12-30 | 2026-01-10 |  |  | FALSE | yes
| JD3RMRL58ST64553 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - MR - L - 58 - ST | 1 | 2026-01-11 | 2026-01-21 |  |  | FALSE | yes
| JD3RMRL58ST64554 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - MR - L - 58 - ST | 1 | 2026-01-22 | 2026-01-29 |  |  | FALSE | yes
| JD3RMRL58ST64555 | EXCAVATION Works for Catchbasine double - B6.33 05 39.10 - MR - L - 58 - ST | 1 | 2026-01-31 | 2026-02-05 |  |  | FALSE | yes
| JD3RMRL58ST64556 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - MR - L - 58 - ST | 1 | 2026-02-07 | 2026-02-15 |  |  | FALSE | yes
| JD3RMRL58ST64557 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - MR - L - 58 - ST | 1 | 2026-02-16 | 2026-02-24 |  |  | FALSE | yes
| JD3RMRL58ST64558 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - MR - L - 58 - ST | 1 | 2026-02-25 | 2026-03-03 |  |  | FALSE | yes
| JD3RMRL58TSE64609 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - L - 58 - TSE | 1 | 2026-04-09 | 2026-04-11 |  |  | FALSE | yes
| JD3RMRL58TSE64610 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - L - 58 - TS | 1 | 2026-04-12 | 2026-04-13 |  |  | FALSE | yes
| JD3RMRL58TSE64611 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - L - 58 - TSE | 1 | 2026-04-14 | 2026-04-16 |  |  | FALSE | yes
| JD3RMRL58TSE64612 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - L - 58 - TSE | 1 | 2026-04-18 | 2026-04-19 |  |  | FALSE | yes
| JD3RMRL58TSE64613 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - MR - L - 58 - TSE | 1 | 2026-06-01 | 2026-06-02 |  |  | FALSE | yes
| JD3RMRL58TSE64624 | Excavation Worksfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - MR - L - 58 - TSE | 1 | 2026-04-19 | 2026-04-20 |  |  | FALSE | yes
| JD3RMRL58TSE64625 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - MR - L - 58 - TSE | 1 | 2026-04-21 | 2026-04-22 |  |  | FALSE | yes
| JD3RMRL58TSE64626 | Installing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - MR - L - 58 - TSE | 1 | 2026-04-23 | 2026-04-25 |  |  | FALSE | yes
| JD3RMRL58TSE64627 | Testing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - MR - L - 58 - TSE | 1 | 2026-04-26 | 2026-04-27 |  |  | FALSE | yes
| JD3RMRL58TSE64628 | Backfillingfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - MR - L - 58 - TSE | 1 | 2026-06-01 | 2026-06-02 |  |  | FALSE | yes
| JD3RMRL58TSE64649 | Excavation Worksfor HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - L - 58 - TSE | 1 | 2026-04-21 | 2026-04-22 |  |  | FALSE | yes
| JD3RMRL58TSE64650 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - L - 58 - TSE | 1 | 2026-04-23 | 2026-04-25 |  |  | FALSE | yes
| JD3RMRL58TSE64651 | Installing for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - L - 58 - TSE | 1 | 2026-04-26 | 2026-04-27 |  |  | FALSE | yes
| JD3RMRL58TSE64652 | Testing for HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - L - 58 - TSE | 1 | 2026-04-28 | 2026-04-29 |  |  | FALSE | yes
| JD3RMRL58TSE64653 | Backfillingfor HDPE Pipes 450 mm - depth from 0 to 1.5 m - B4.33 31 00.09 - MR - L - 58 - TSE | 1 | 2026-06-01 | 2026-06-02 |  |  | FALSE | yes
| JD3RMRL58TSE64657 | Testing for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - MR - L - 58 - TSE | 1 | 2026-05-06 | 2026-05-10 | 2025-08-23 |  | FALSE | yes
| JD3RMRL58TSE64659 | Excavation Worksfor HDPE Pipes 450 mm - depth from 2.51 to 3.5 m - B4.33 31 00.11 - MR - L - 58 - TSE | 1 | 2026-04-27 | 2026-04-29 | 2025-08-23 |  | FALSE | yes
| JD3RMRL58TSE64660 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 2.51 to 3.5 m - B4.33 31 00.11 - MR - L - 58 - TSE | 1 | 2026-04-30 | 2026-05-03 | 2025-08-26 |  | FALSE | yes
| JD3RMRL58TSE64661 | Installing for HDPE Pipes 450 mm - depth from 2.51 to 3.5 m - B4.33 31 00.11 - MR - L - 58 - TSE | 1 | 2026-05-04 | 2026-05-09 | 2025-08-30 |  | FALSE | yes
| JD3RMRL58TSE64662 | Testing for HDPE Pipes 450 mm - depth from 2.51 to 3.5 m - B4.33 31 00.11 - MR - L - 58 - TSE | 1 | 2026-05-10 | 2026-05-12 |  |  | FALSE | yes
| JD3RMRL58TSE64663 | Backfillingfor HDPE Pipes 450 mm - depth from 2.51 to 3.5 m - B4.33 31 00.11 - MR - L - 58 - TSE | 1 | 2026-06-01 | 2026-06-03 | 2025-09-06 |  | FALSE | yes
| JD3RMRL58TSE64679 | Excavation Worksfor HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - L - 58 - TSE | 1 | 2026-04-30 | 2026-05-02 |  |  | FALSE | yes
| JD3RMRL58TSE64680 | Soil Replacement and Bedding Works for HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - L - 58 - TSE | 1 | 2026-05-03 | 2026-05-04 |  |  | FALSE | yes
| JD3RMRL58TSE64681 | Installing for HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - L - 58 - TSE | 1 | 2026-05-05 | 2026-05-06 |  |  | FALSE | yes
| JD3RMRL58TSE64682 | Testing for HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - L - 58 - TSE | 1 | 2026-05-07 | 2026-05-09 |  |  | FALSE | yes
| JD3RMRL58TSE64683 | Backfillingfor HDPE Pipes 630 mm - depth from 0 to 1.5 m - B4.33 31 00.15 - MR - L - 58 - TSE | 1 | 2026-05-10 | 2026-05-11 |  |  | FALSE | yes
| JD3RMRL58TSE64684 | Excavation Worksfor HDPE Pipes 630 mm - depth from 1.51 to 2.5 m - B4.33 31 00.16 - MR - L - 58 - TSE | 1 | 2026-05-03 | 2026-05-05 |  |  | FALSE | yes
| JD3RMRL58TSE64685 | Soil Replacement and Bedding Works for HDPE Pipes 630 mm - depth from 1.51 to 2.5 m - B4.33 31 00.16 - MR - L - 58 - TSE | 1 | 2026-05-06 | 2026-05-09 |  |  | FALSE | yes
| JD3RMRL58TSE64686 | Installing for HDPE Pipes 630 mm - depth from 1.51 to 2.5 m - B4.33 31 00.16 - MR - L - 58 - TSE | 1 | 2026-05-10 | 2026-05-14 |  |  | FALSE | yes
| JD3RMRL58TSE64687 | Testing for HDPE Pipes 630 mm - depth from 1.51 to 2.5 m - B4.33 31 00.16 - MR - L - 58 - TSE | 1 | 2026-05-16 | 2026-05-19 |  |  | FALSE | yes
| JD3RMRL58TSE64688 | Backfillingfor HDPE Pipes 630 mm - depth from 1.51 to 2.5 m - B4.33 31 00.16 - MR - L - 58 - TSE | 1 | 2026-05-20 | 2026-05-24 |  |  | FALSE | yes
| JD3RMRL58TSE64689 | Excavation Worksfor HDPE Pipes 630 mm - depth from 2.51 to 3.5 m - B4.33 31 00.17 - MR - L - 58 - TSE | 1 | 2026-05-06 | 2026-05-07 |  |  | FALSE | yes
| JD3RMRL58TSE64690 | Soil Replacement and Bedding Works for HDPE Pipes 630 mm - depth from 2.51 to 3.5 m - B4.33 31 00.17 - MR - L - 58 - TSE | 1 | 2026-05-09 | 2026-05-10 |  |  | FALSE | yes
| JD3RMRL58TSE64691 | Installing for HDPE Pipes 630 mm - depth from 2.51 to 3.5 m - B4.33 31 00.17 - MR - L - 58 - TSE | 1 | 2026-05-11 | 2026-05-12 |  |  | FALSE | yes
| JD3RMRL58TSE64692 | Testing for HDPE Pipes 630 mm - depth from 2.51 to 3.5 m - B4.33 31 00.17 - MR - L - 58 - TSE | 1 | 2026-05-13 | 2026-05-14 |  |  | FALSE | yes
| JD3RMRL58TSE64693 | Backfillingfor HDPE Pipes 630 mm - depth from 2.51 to 3.5 m - B4.33 31 00.17 - MR - L - 58 - TSE | 1 | 2026-05-16 | 2026-05-17 |  |  | FALSE | yes
| JD3RMRL58TSE64734 | Installationfor gate valves 100 mm - B4.33 14 19.01 - MR - L - 58 - TSE | 1 | 2026-05-16 | 2026-05-17 |  |  | FALSE | yes
| JD3RMRL58TSE64735 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - MR - L - 58 - TSE | 1 | 2026-05-18 | 2026-05-19 |  |  | FALSE | yes
| JD3RMRL58TSE64736 | Installationfor gate valves 250 mm - B4.33 14 19.02 - MR - L - 58 - TSE | 1 | 2026-05-18 | 2026-05-19 |  |  | FALSE | yes
| JD3RMRL58TSE64737 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - MR - L - 58 - TSE | 1 | 2026-05-20 | 2026-05-21 |  |  | FALSE | yes
| JD3RMRL58TSE64740 | Installationfor butterfly valves 400 mm. - B4.33 14 19.04 - MR - L - 58 - TSE | 1 | 2026-05-20 | 2026-05-21 |  |  | FALSE | yes
| JD3RMRL58TSE64741 | Testing And Commtionningfor butterfly valves 400 mm. - B4.33 14 19.04 - MR - L - 58 - TSE | 1 | 2026-05-23 | 2026-05-24 |  |  | FALSE | yes
| JD3RMRL58TSE64742 | Installationfor butterfly valves 600 mm. - B4.33 14 19.05 - MR - L - 58 - TSE | 1 | 2026-05-23 | 2026-05-24 |  |  | FALSE | yes
| JD3RMRL58TSE64743 | Testing And Commtionningfor butterfly valves 600 mm. - B4.33 14 19.05 - MR - L - 58 - TSE | 1 | 2026-05-25 | 2026-05-26 |  |  | FALSE | yes
| JD3RMRL58TSE64748 | Installationfor Wash - Out valves 150 mm. - on pipes with diameter 450 - 630 mm - B4.33 14 19.08 - MR - L - 58 - TSE | 1 | 2026-05-25 | 2026-05-26 |  |  | FALSE | yes
| JD3RMRL58TSE64749 | Testing And Commtionningfor Wash - Out valves 150 mm. - on pipes with diameter 450 - 630 mm - B4.33 14 19.08 - MR - L - | 1 | 2026-05-27 | 2026-05-28 |  |  | FALSE | yes
| JD3RMRL58TSE64752 | Installationfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - MR - L - 58 - TSE | 1 | 2026-05-27 | 2026-05-28 |  |  | FALSE | yes
| JD3RMRL58TSE64753 | Testing And Commtionningfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - MR - L - 58 - | 1 | 2026-05-30 | 2026-05-31 |  |  | FALSE | yes
| JD3RMRL58TSE64758 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - L - 58 - TSE | 1 | 2026-05-09 | 2026-05-10 |  |  | FALSE | yes
| JD3RMRL58TSE64759 | Plain Concrete Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - L - 58 - TSE | 1 | 2026-05-11 | 2026-05-12 |  |  | FALSE | yes
| JD3RMRL58TSE64760 | INSTALLATIONfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - L - 58 - TSE | 1 | 2026-05-13 | 2026-05-16 |  |  | FALSE | yes
| JD3RMRL58TSE64761 | Backfilling Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - MR - L - 58 - TSE | 1 | 2026-05-17 | 2026-05-19 |  |  | FALSE | yes
| JD3RMRL58TSE64762 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 500 to 630 MM - B4.33 14 13.02 - MR - L - 58 - TSE | 1 | 2026-05-11 | 2026-05-12 |  |  | FALSE | yes
| JD3RMRL58TSE64763 | Plain Concrete Worksfor R.C Valve Chamber - 500 to 630 MM - B4.33 14 13.02 - MR - L - 58 - TSE | 1 | 2026-05-13 | 2026-05-14 |  |  | FALSE | yes
| JD3RMRL58TSE64764 | INSTALLATIONfor R.C Valve Chamber - 500 to 630 MM - B4.33 14 13.02 - MR - L - 58 - TSE | 1 | 2026-05-16 | 2026-05-17 |  |  | FALSE | yes
| JD3RMRL58TSE64765 | Backfilling Worksfor R.C Valve Chamber - 500 to 630 MM - B4.33 14 13.02 - MR - L - 58 - TSE | 1 | 2026-05-18 | 2026-05-19 |  |  | FALSE | yes
| JD3RMRL58TSE64774 | EXCAVATION and Bedding Worksfor Wash - out Valve Chamber - 450 to 630 MM - B4.33 14 13.07 - MR - L - 58 - TSE | 1 | 2026-05-13 | 2026-05-14 |  |  | FALSE | yes
| JD3RMRL58TSE64775 | Plain Concrete Worksfor Wash - out Valve Chamber - 450 to 630 MM - B4.33 14 13.07 - MR - L - 58 - TSE | 1 | 2026-05-16 | 2026-05-17 |  |  | FALSE | yes
| JD3RMRL58TSE64776 | INSTALLATIONfor Wash - out Valve Chamber - 450 to 630 MM - B4.33 14 13.07 - MR - L - 58 - TSE | 1 | 2026-05-18 | 2026-05-19 |  |  | FALSE | yes
| JD3RMRL58TSE64777 | Backfilling Worksfor Wash - out Valve Chamber - 450 to 630 MM - B4.33 14 13.07 - MR - L - 58 - TSE | 1 | 2026-05-20 | 2026-05-21 |  |  | FALSE | yes
| JD3RMRL58TSE64782 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - L - 58 - TSE | 1 | 2026-05-16 | 2026-05-17 |  |  | FALSE | yes
| JD3RMRL58TSE64783 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - L - 58 - TSE | 1 | 2026-05-18 | 2026-05-19 |  |  | FALSE | yes
| JD3RMRL58TSE64784 | INSTALLATIONfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - L - 58 - TSE | 1 | 2026-05-20 | 2026-05-21 |  |  | FALSE | yes
| JD3RMRL58TSE64785 | Backfilling Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - MR - L - 58 - TSE | 1 | 2026-05-23 | 2026-05-24 |  |  | FALSE | yes
| JD3RMRL58WT64559 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - MR - L - 58 - WT | 1 | 2026-05-25 | 2026-05-26 |  |  | FALSE | yes
| JD3RMRL58WT64560 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - MR - L - 58 - WT | 1 | 2026-05-27 | 2026-05-28 |  |  | FALSE | yes
| JD3RMRL58WT64561 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - MR - L - 58 - WT | 1 | 2026-05-30 | 2026-05-31 |  |  | FALSE | yes
| JD3RMRL58WT64562 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - MR - L - 58 - WT | 1 | 2026-06-01 | 2026-06-02 |  |  | FALSE | yes
| JD3RMRL58WT64563 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - MR - L - 58 - WT | 1 | 2026-06-03 | 2026-06-04 |  |  | FALSE | yes
| JD3RMRL58WT64594 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - MR - L - 58 - WT | 1 | 2026-06-07 | 2026-06-08 |  |  | FALSE | yes
| JD3RMRL58WT64595 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - MR - L - 58 - WT | 1 | 2026-06-09 | 2026-06-10 |  |  | FALSE | yes
| JD3RMRL58WT64596 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - MR - L - 58 - WT | 1 | 2026-06-11 | 2026-06-13 |  |  | FALSE | yes
| JD3RMRMR1ST101.R1 | Channel excavation for Swales - B6.31 22 00.13 - MR - R1 - ST - Remaining | 1 | 2025-09-23 | 2025-10-12 | 2025-08-02 |  | FALSE | yes
| JD3RMRMR1ST101.R2 | Channel excavation for Swales - B6.31 22 00.13 - MR - R1 - ST - Remaining | 1 | 2025-10-13 | 2025-11-01 |  |  | FALSE | yes
| JD3RMRMR1ST102 | Channel excavation for Swales - B6.31 22 00.13 - MR - R1 - ST | 1 | 2025-11-02 | 2025-11-24 |  |  | FALSE | yes
| JD3RMRMR1ST102.R1 | Channel excavation for Swales - B6.31 22 00.13 - MR - R1 - ST | 1 | 2025-11-25 | 2025-12-17 |  |  | FALSE | yes
| JD3RMRMR1ST102.R2 | Channel excavation for Swales - B6.31 22 00.13 - MR - R1 - ST | 1 | 2025-12-18 | 2026-01-10 |  |  | FALSE | yes
| JD3RMRMR1ST200 | Riprap With side slopes 1:1 for Swales - NB6.31 22 00.15 - MR - R1 - ST | 1 | 2025-09-23 | 2025-09-30 |  |  | FALSE | yes
| JD3RMRMR1ST301.R2 | Riprap with side slopes 1.5:1 for Swales - NB6.31 22 00.16 - MR - R1 - ST | 1 | 2026-01-04 | 2026-01-27 | 2025-09-06 |  | FALSE | yes
| JD3RMRMR1ST302 | Riprap with side slopes 1.5:1 for Swales - NB6.31 22 00.16 - MR - R1 - ST | 1 | 2026-01-28 | 2026-02-19 |  |  | FALSE | yes
| JD3RMRMR1ST302.R1 | Riprap with side slopes 1.5:1 for Swales - NB6.31 22 00.16 - MR - R1 - ST | 1 | 2026-02-21 | 2026-03-15 |  |  | FALSE | yes
| JD3RMRMR1ST302.R2 | Riprap with side slopes 1.5:1 for Swales - NB6.31 22 00.16 - MR - R1 - ST | 1 | 2026-03-16 | 2026-04-07 |  |  | FALSE | yes
| JD3RMRMR1ST303 | Riprap with side slopes 1.5:1 for Swales - NB6.31 22 00.16 - MR - R1 - ST | 1 | 2026-01-28 | 2026-02-19 |  |  | FALSE | yes
| JD3RMRMR1ST303.R1 | Riprap with side slopes 1.5:1 for Swales - NB6.31 22 00.16 - MR - R1 - ST | 1 | 2026-02-21 | 2026-03-15 |  |  | FALSE | yes
| JD3RMRMR1ST303.R2 | Riprap with side slopes 1.5:1 for Swales - NB6.31 22 00.16 - MR - R1 - ST | 1 | 2026-03-16 | 2026-04-07 |  |  | FALSE | yes
| JD3RMRMR1ST400 | Concrete lining 35Mpa with slopes and channel protection for Swales - B6.03 30 00.09 - MR - R1 - ST | 1 | 2026-04-08 | 2026-04-13 | 2025-08-27 |  | FALSE | yes
| JD3RMRMR2ST100.R | Channel excavation for Swales - B6.31 22 00.13 - MR - R2 - ST - Remaining | 1 | 2026-02-03 | 2026-02-24 | 2025-11-03 |  | FALSE | yes
| JD3RMRMR2ST301 | Riprap with side slopes 1.5:1 for Swales - NB6.31 22 00.16 - MR - R2 - ST | 1 | 2026-03-18 | 2026-04-07 | 2025-10-30 |  | FALSE | yes
| JD3RMRMR2ST301.R1 | Riprap with side slopes 1.5:1 for Swales - NB6.31 22 00.16 - MR - R2 - ST | 1 | 2026-04-08 | 2026-04-28 |  |  | FALSE | yes
| JD3RMRMR2ST301.R2 | Riprap with side slopes 1.5:1 for Swales - NB6.31 22 00.16 - MR - R2 - ST | 1 | 2026-04-29 | 2026-05-19 |  |  | FALSE | yes
| JD3RMRMR2ST301.R3 | Riprap with side slopes 1.5:1 for Swales - NB6.31 22 00.16 - MR - R2 - ST | 1 | 2026-05-20 | 2026-06-09 |  |  | FALSE | yes
| JD3RMRR1ST20637 | Excavation Works for Box Culvert - B6.35 42 16.01 - Dim (1000x1000) depth from 2.51 to 3.50 - MR - R1 - ST | 1 | 2026-02-21 | 2026-02-23 |  |  | FALSE | yes
| JD3RMRR1ST20638 | Plain Concrete Works for Box Culvert - B6.35 42 16.01 - Dim (1000x1000) depth from 2.51 to 3.50 - MR - R1 - ST | 1 | 2026-02-24 | 2026-02-25 |  |  | FALSE | yes
| JD3RMRR1ST20639 | Raft Foundation for Box Culvert - B6.35 42 16.01 - Dim (1000x1000) depth from 2.51 to 3.50 - MR - R1 - ST | 1 | 2026-02-26 | 2026-03-08 |  |  | FALSE | yes
| JD3RMRR1ST20640 | Wing Wall for Box Culvert - B6.35 42 16.01 - Dim (1000x1000) depth from 2.51 to 3.50 - MR - R1 - ST | 1 | 2026-03-09 | 2026-03-23 |  |  | FALSE | yes
| JD3RMRR1ST20641 | Slab for Box Culvert - B6.35 42 16.01 - Dim (1000x1000) depth from 2.51 to 3.50 - MR - R1 - ST | 1 | 2026-03-24 | 2026-04-07 |  |  | FALSE | yes
| JD3RMRR1ST20642 | Isolation Works for Box Culvert - B6.35 42 16.01 - Dim (1000x1000) depth from 2.51 to 3.50 - MR - R1 - ST | 1 | 2026-04-08 | 2026-04-13 |  |  | FALSE | yes
| JD3RMRR1ST20643 | Backfilling Works for Box Culvert - B6.35 42 16.01 - Dim (1000x1000) depth from 2.51 to 3.50 - MR - R1 - ST | 1 | 2026-04-14 | 2026-04-15 |  |  | FALSE | yes
| JD3RMRR1ST20672 | Excavation Works for Box Culvert - B6.34 42 16.05 - Dim (3000x1500) depth from 1.51 to 2.50 - MR - R1 - ST | 1 | 2026-03-07 | 2026-03-16 |  |  | FALSE | yes
| JD3RMRR1ST206721 | Excavation Works for Box Culvert - B6.34 42 16.06 - Dim (3000x1500) depth from 2.51 to 3.50 - MR - R1 - ST | 1 | 2026-02-24 | 2026-03-05 |  |  | FALSE | yes
| JD3RMRR1ST20673 | Plain Concrete Works for Box Culvert - B6.34 42 16.05 - Dim (3000x1500) depth from 1.51 to 2.50 - MR - R1 - ST | 1 | 2026-03-17 | 2026-03-19 |  |  | FALSE | yes
| JD3RMRR1ST206731 | Plain Concrete Works for Box Culvert - B6.34 42 16.06 - Dim (3000x1500) depth from 2.51 to 3.50 - MR - R1 - ST | 1 | 2026-03-07 | 2026-03-09 |  |  | FALSE | yes
| JD3RMRR1ST20674 | Raft Foundation for Box Culvert - B6.34 42 16.05 - Dim (3000x1500) depth from 1.51 to 2.50 - MR - R1 - ST | 1 | 2026-03-21 | 2026-04-05 |  |  | FALSE | yes
| JD3RMRR1ST206741 | Raft Foundation for Box Culvert - B6.34 42 16.06 - Dim (3000x1500) depth from 2.51 to 3.50 - MR - R1 - ST | 1 | 2026-03-10 | 2026-03-25 |  |  | FALSE | yes
| JD3RMRR1ST20675 | Wing Wall for Box Culvert - B6.34 42 16.05 - Dim (3000x1500) depth from 1.51 to 2.50 - MR - R1 - ST | 1 | 2026-04-06 | 2026-04-29 |  |  | FALSE | yes
| JD3RMRR1ST206751 | Wing Wall for Box Culvert - B6.34 42 16.06 - Dim (1000x1000) depth from 2.51 to 3.50 - MR - R1 - ST | 1 | 2026-03-26 | 2026-04-19 |  |  | FALSE | yes
| JD3RMRR1ST20676 | Slab for Box Culvert - B6.34 42 16.05 - Dim (3000x1500) depth from 1.51 to 2.50 - MR - R1 - ST | 1 | 2026-04-30 | 2026-05-24 |  |  | FALSE | yes
| JD3RMRR1ST206761 | Slab for Box Culvert - B6.34 42 16.06 - Dim (1000x1000) depth from 2.51 to 3.50 - MR - R1 - ST | 1 | 2026-04-20 | 2026-05-13 |  |  | FALSE | yes
| JD3RMRR1ST20677 | Isolation Works for Box Culvert - B6.34 42 16.05 - Dim (3000x1500) depth from 1.51 to 2.50 - MR - R1 - ST | 1 | 2026-05-25 | 2026-06-09 |  |  | FALSE | yes
| JD3RMRR1ST206771 | Isolation Works for Box Culvert - B6.34 42 16.06 - Dim (3000x1500) depth from 2.51 to 3.50 - MR - R1 - ST | 1 | 2026-05-14 | 2026-05-30 |  |  | FALSE | yes
| JD3RMRR1ST20678 | Backfilling Works for Box Culvert - B6.34 42 16.05 - Dim (3000x1500) depth from 1.51 to 2.50 - MR - R1 - ST | 1 | 2026-06-10 | 2026-06-15 |  |  | FALSE | yes
| JD3RMRR1ST206781 | Backfilling Works for Box Culvert - B6.34 42 16.06 - Dim (3000x1500) depth from 2.51 to 3.50 - MR - R1 - ST | 1 | 2026-05-31 | 2026-06-04 |  |  | FALSE | yes
| JD3RMRR1ST20715 | Excavation Works for Manholes - B6.33 05 39.04 - Diam 1500 depth from 1.51 to 2.50 - MR - R1 - ST | 1 | 2026-05-20 | 2026-05-21 |  |  | FALSE | yes
| JD3RMRR1ST207151 | Excavation Works for Manholes - B6.33 05 39.05 - Diam 1500 depth from 2.51 to 3.50 - MR - R1 - ST | 1 | 2026-05-23 | 2026-05-24 |  |  | FALSE | yes
| JD3RMRR1ST20716 | Base Plain Concrete Works for Manholes - B6.33 05 39.04 - Diam 1500 depth from 1.51 to 2.50 - MR - R1 - ST | 1 | 2026-05-23 | 2026-05-24 |  |  | FALSE | yes
| JD3RMRR1ST207161 | Base Plain Concrete Works for Manholes - B6.33 05 39.05 - Diam 1500 depth from 1.51 to 2.50 - MR - R1 - ST | 1 | 2026-05-25 | 2026-05-28 |  |  | FALSE | yes
| JD3RMRR1ST20717 | Manhole Installation Works for Manholes - B6.33 05 39.04 - Diam 1500 depth from 1.51 to 2.50 - MR - R1 - ST | 1 | 2026-05-25 | 2026-05-26 |  |  | FALSE | yes
| JD3RMRR1ST207171 | Manhole Installation Works for Manholes - B6.33 05 39.05 - Diam 1500 depth from 1.51 to 2.50 - MR - R1 - ST | 1 | 2026-05-30 | 2026-06-02 |  |  | FALSE | yes
| JD3RMRR1ST20718 | FINISHING Works and Backfilling Works for Manholes - B6.33 05 39.04 - Diam 1500 depth from 1.51 to 2.50 - MR - R1 - ST | 1 | 2026-05-27 | 2026-05-28 |  |  | FALSE | yes
| JD3RMRR1ST207181 | FINISHING Works and Backfilling Works for Manholes - B6.33 05 39.05 - Diam 1500 depth from 1.51 to 2.50 - MR - R1 - ST | 1 | 2026-06-03 | 2026-06-06 |  |  | FALSE | yes
| JD3RMRR1ST20719 | TESTING AND COMMITIONING Works for Manholes - B6.33 05 39.04 - Diam 1500 depth from 1.51 to 2.50 - MR - R1 - ST | 1 | 2026-05-30 | 2026-05-31 |  |  | FALSE | yes
| JD3RMRR1ST207191 | TESTING AND COMMITIONING Works for Manholes - B6.33 05 39.05 - Diam 1500 depth from 1.51 to 2.50 - MR - R1 - ST | 1 | 2026-06-07 | 2026-06-09 |  |  | FALSE | yes
| JD3RMRR1ST20732 | Manhole Installation Works for Manholes - B6.33 05 39.07 - Diam 2000 depth from 1.51 to 2.50 - MR - R1 - ST | 1 | 2026-06-02 | 2026-06-07 |  |  | FALSE | yes
| JD3RMRR1ST20733 | FINISHING Works and Backfilling Works for Manholes - B6.33 05 39.07 - Diam 2000 depth from 1.51 to 2.50 - MR - R1 - ST | 1 | 2026-06-08 | 2026-06-10 |  |  | FALSE | yes
| JD3RMRR1ST20734 | TESTING AND COMMITIONING Works for Manholes - B6.33 05 39.07 - Diam 2000 depth from 1.51 to 2.50 - MR - R1 - ST | 1 | 2026-06-11 | 2026-06-14 |  |  | FALSE | yes
| JD3RMRR2ST20637 | Excavation Works for Box Culvert - B6.35 42 16.01 - Dim (1000x1000) depth from 2.51 to 3.50 - MR - R2 - ST | 1 | 2026-03-05 | 2026-03-07 |  |  | FALSE | yes
| JD3RMRR2ST20638 | Plain Concrete Works for Box Culvert - B6.35 42 16.01 - Dim (1000x1000) depth from 2.51 to 3.50 - MR - R2 - ST | 1 | 2026-02-03 | 2026-02-04 |  |  | FALSE | yes
| JD3RMRR2ST20639 | Raft Foundation for Box Culvert - B6.35 42 16.01 - Dim (1000x1000) depth from 2.51 to 3.50 - MR - R2 - ST | 1 | 2026-02-05 | 2026-02-10 |  |  | FALSE | yes
| JD3RMRR2ST20640 | Wing Wall for Box Culvert - B6.35 42 16.01 - Dim (1000x1000) depth from 2.51 to 3.50 - MR - R2 - ST | 1 | 2026-02-11 | 2026-02-18 |  |  | FALSE | yes
| JD3RMRR2ST20641 | Slab for Box Culvert - B6.35 42 16.01 - Dim (1000x1000) depth from 2.51 to 3.50 - MR - R2 - ST | 1 | 2026-02-19 | 2026-02-26 |  |  | FALSE | yes
| JD3RMRR2ST20642 | Isolation Works for Box Culvert - B6.35 42 16.01 - Dim (1000x1000) depth from 2.51 to 3.50 - MR - R2 - ST | 1 | 2026-02-28 | 2026-03-02 |  |  | FALSE | yes
| JD3RMRR2ST20643 | Backfilling Works for Box Culvert - B6.35 42 16.01 - Dim (1000x1000) depth from 2.51 to 3.50 - MR - R2 - ST | 1 | 2026-03-03 | 2026-03-04 |  |  | FALSE | yes
| JD3RMRR2ST20715 | Excavation Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - MR - R2 - ST | 1 | 2026-03-17 | 2026-03-18 |  |  | FALSE | yes
| JD3RMRR2ST20716 | Base Plain Concrete Works for Manholes - B6.33 05 39.04 - Diam 1500 depth from 1.51 to 2.50 - MR - R2 - ST | 1 | 2026-03-19 | 2026-03-21 |  |  | FALSE | yes
| JD3RMRR2ST20717 | Manhole Installation Works for Manholes - B6.33 05 39.04 - Diam 1500 depth from 1.51 to 2.50 - MR - R2 - ST | 1 | 2026-03-22 | 2026-03-23 |  |  | FALSE | yes
| JD3RMRR2ST20718 | FINISHING Works and Backfilling Works for Manholes - B6.33 05 39.04 - Diam 1500 depth from 1.51 to 2.50 - MR - R2 - ST | 1 | 2026-03-24 | 2026-03-25 |  |  | FALSE | yes
| JD3RMRR2ST20719 | TESTING AND COMMITIONING Works for Manholes - B6.33 05 39.04 - Diam 1500 depth from 1.51 to 2.50 - MR - R2 - ST | 1 | 2026-03-26 | 2026-03-28 |  |  | FALSE | yes
| JD3RMRR2ST20730 | Excavation Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - MR - R2 - ST | 1 | 2026-03-15 | 2026-03-16 |  |  | FALSE | yes
| JD3RMRR2ST20731 | Base Plain Concrete Works for Manholes - B6.33 05 39.07 - Diam 2000 depth from 1.51 to 2.50 - MR - R2 - ST | 1 | 2026-03-17 | 2026-03-18 |  |  | FALSE | yes
| JD3RMRR2ST20732 | Manhole Installation Works for Manholes - B6.33 05 39.07 - Diam 2000 depth from 1.51 to 2.50 - MR - R2 - ST | 1 | 2026-03-19 | 2026-03-21 |  |  | FALSE | yes
| JD3RMRR2ST20733 | FINISHING Works and Backfilling Works for Manholes - B6.33 05 39.07 - Diam 2000 depth from 1.51 to 2.50 - MR - R2 - ST | 1 | 2026-03-22 | 2026-03-23 |  |  | FALSE | yes
| JD3RMRR2ST20734 | TESTING AND COMMITIONING Works for Manholes - B6.33 05 39.07 - Diam 2000 depth from 1.51 to 2.50 - MR - R2 - ST | 1 | 2026-03-24 | 2026-03-25 |  |  | FALSE | yes
| JD3RMRR2ST20748 | Excavation Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - MR - R2 - ST | 1 | 2026-03-10 | 2026-03-11 |  |  | FALSE | yes
| JD3RMRR2ST207481 | Excavation Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - MR - R2 - ST | 1 | 2026-03-10 | 2026-03-11 |  |  | FALSE | yes
| JD3RMRR2ST20749 | Soil Replacement and Bedding Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - MR - R2 - | 1 | 2026-03-12 | 2026-03-14 |  |  | FALSE | yes
| JD3RMRR2ST207491 | Soil Replacement and Bedding Works for UPVC Pipe Line - B6.33 42 11.06 - 600 mm - depth from 1.51 to 2.50 m - MR - R2 - | 1 | 2026-03-12 | 2026-03-14 |  |  | FALSE | yes
| JD3RMRR2ST20750 | Installing for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - MR - R2 - ST | 1 | 2026-03-15 | 2026-03-16 |  |  | FALSE | yes
| JD3RMRR2ST207501 | Installing for UPVC Pipe Line - B6.33 42 11.06 - 600 mm - depth from 1.51 to 2.50 m - MR - R2 - ST | 1 | 2026-03-15 | 2026-03-17 |  |  | FALSE | yes
| JD3RMRR2ST20751 | Primary Test for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - MR - R2 - ST | 1 | 2026-03-17 | 2026-03-18 |  |  | FALSE | yes
| JD3RMRR2ST207511 | Primary Test for UPVC Pipe Line - B6.33 42 11.06 - 600 mm - depth from 1.51 to 2.50 m - MR - R2 - ST | 1 | 2026-03-18 | 2026-03-21 |  |  | FALSE | yes
| JD3RMRR2ST20752 | Backfilling Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - MR - R2 - ST | 1 | 2026-03-19 | 2026-03-22 |  |  | FALSE | yes
| JD3RMRR2ST207521 | Backfilling Works for UPVC Pipe Line - B6.33 42 11.06 - 600 mm - depth from 1.51 to 2.50 m - MR - R2 - ST | 1 | 2026-03-22 | 2026-03-25 |  |  | FALSE | yes
| JD3RMRR2ST209311 | Excavation Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - MR - R2 - ST | 1 | 2026-03-12 | 2026-03-14 |  |  | FALSE | yes
| JD3RMRR2ST209321 | Catchbasine Installation Works for Catchbasine single - B6.33 05 39.09 - MR - R2 - ST | 1 | 2026-03-15 | 2026-03-17 |  |  | FALSE | yes
| JD3RMRR2ST209331 | FINISHING Works for Catchbasine single - B6.33 05 39.09 - MR - R2 - ST | 1 | 2026-03-18 | 2026-03-21 |  |  | FALSE | yes
| JD3RMRR2ST209341 | TESTING AND COMMITIONING RELEASED for Catchbasine single - B6.33 05 39.09 - MR - R2 - ST | 1 | 2026-03-22 | 2026-03-23 |  |  | FALSE | yes
| JD3RPS524371 | Filling with imported material - B6.31 22 00.12 - Z02 - 2 - L - 74 - ST | 1 | 2025-01-09 | 2025-01-28 | 2025-10-25 |  | FALSE | FALSE
| JD3RPS524372 | Filling with imported material - B6.31 22 00.12 - Z02 - 2 - L - 75 - ST | 1 | 2025-02-03 | 2025-02-25 | 2025-10-25 |  | FALSE | FALSE
| JD3RZ01L02ST163 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z01 - L - 02 - ST | 1 | 2025-12-28 | 2025-12-30 |  |  | FALSE | yes
| JD3RZ01L02ST164 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z01 - L - 02 | 1 | 2025-12-31 | 2026-01-03 |  |  | FALSE | yes
| JD3RZ01L02ST165 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z01 - L - 02 - ST | 1 | 2026-01-04 | 2026-01-07 |  |  | FALSE | yes
| JD3RZ01L02ST166 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z01 - L - 02 - ST | 1 | 2026-01-10 | 2026-01-13 |  |  | FALSE | yes
| JD3RZ01L02ST167 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z01 - L - 02 - ST | 1 | 2026-02-22 | 2026-02-26 |  |  | FALSE | yes
| JD3RZ01L02ST168 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z01 - L - 02 - ST | 1 | 2025-12-31 | 2026-01-01 |  |  | FALSE | yes
| JD3RZ01L02ST169 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z01 - L - 02 | 1 | 2026-01-03 | 2026-01-04 |  |  | FALSE | yes
| JD3RZ01L02ST170 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z01 - L - 02 - ST | 1 | 2026-01-05 | 2026-01-06 |  |  | FALSE | yes
| JD3RZ01L02ST171 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z01 - L - 02 - ST | 1 | 2026-01-07 | 2026-01-08 |  |  | FALSE | yes
| JD3RZ01L02ST172 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z01 - L - 02 - ST | 1 | 2026-02-19 | 2026-02-21 |  |  | FALSE | yes
| JD3RZ01L02ST176 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z01 - L - 02 - ST | 1 | 2026-01-14 | 2026-01-17 |  |  | FALSE | yes
| JD3RZ01L02ST177 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z01 - L - 02 - ST | 1 | 2026-02-19 | 2026-02-24 | 2025-09-20 |  | FALSE | yes
| JD3RZ01L02ST183 | Excavation Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - Z01 - L - 02 - ST | 1 | 2026-01-06 | 2026-01-07 | 2025-09-03 |  | FALSE | yes
| JD3RZ01L02ST184 | Soil Replacement and Bedding Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - Z01 - L - 02 | 1 | 2026-01-08 | 2026-01-10 | 2025-09-06 |  | FALSE | yes
| JD3RZ01L02ST185 | Installing for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - Z01 - L - 02 - ST | 1 | 2026-01-11 | 2026-01-12 |  |  | FALSE | yes
| JD3RZ01L02ST186 | Primary Test for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - Z01 - L - 02 - ST | 1 | 2026-01-13 | 2026-01-14 |  |  | FALSE | yes
| JD3RZ01L02ST187 | Backfilling Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - Z01 - L - 02 - ST | 1 | 2026-02-19 | 2026-02-21 |  |  | FALSE | yes
| JD3RZ01L02ST193 | Excavation Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - Z01 - L - 02 - ST | 1 | 2026-01-08 | 2026-01-10 | 2025-09-03 |  | FALSE | yes
| JD3RZ01L02ST194 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - Z01 - L - 02 | 1 | 2026-01-11 | 2026-01-12 | 2025-09-06 |  | FALSE | yes
| JD3RZ01L02ST195 | Installing for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - Z01 - L - 02 - ST | 1 | 2026-01-13 | 2026-01-14 | 2025-09-10 |  | FALSE | yes
| JD3RZ01L02ST196 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - Z01 - L - 02 - ST | 1 | 2026-01-15 | 2026-01-17 | 2025-10-05 |  | FALSE | yes
| JD3RZ01L02ST197 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - Z01 - L - 02 - ST | 1 | 2026-02-19 | 2026-02-21 | 2025-09-13 |  | FALSE | yes
| JD3RZ01L02ST253 | Excavation Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m - B6.33 42 11.20 - Z01 - L - 02 - ST | 1 | 2026-01-15 | 2026-01-17 | 2025-08-15 |  | FALSE | yes
| JD3RZ01L02ST254 | Soil Replacement and Bedding Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m - B6.33 42 11.20 - Z01 - L - 02 | 1 | 2026-01-18 | 2026-01-19 | 2025-08-17 |  | FALSE | yes
| JD3RZ01L02ST255 | Installing for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m - B6.33 42 11.20 - Z01 - L - 02 - ST | 1 | 2026-01-20 | 2026-01-22 | 2025-09-06 |  | FALSE | yes
| JD3RZ01L02ST256 | Primary Test for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m - B6.33 42 11.20 - Z01 - L - 02 - ST | 1 | 2026-01-24 | 2026-01-25 | 2025-10-01 |  | FALSE | yes
| JD3RZ01L02ST257 | Backfilling Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m - B6.33 42 11.20 - Z01 - L - 02 - ST | 1 | 2026-02-19 | 2026-02-22 | 2025-09-20 |  | FALSE | yes
| JD3RZ01L02ST346 | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z01 - L - 02 - ST | 1 | 2026-01-22 | 2026-01-24 | 2025-09-16 |  | FALSE | yes
| JD3RZ01L02ST347 | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z01 - L - 02 - ST | 1 | 2026-01-25 | 2026-01-27 | 2025-09-17 |  | FALSE | yes
| JD3RZ01L02ST348 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z01 - L - 02 - ST | 1 | 2026-01-28 | 2026-01-31 | 2025-09-18 |  | FALSE | yes
| JD3RZ01L02ST349 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z01 - L - 02 - S | 1 | 2026-02-01 | 2026-02-02 |  |  | FALSE | yes
| JD3RZ01L02ST350 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z01 - L - 02 - ST | 1 | 2026-02-03 | 2026-02-04 |  |  | FALSE | yes
| JD3RZ01L02ST358 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z01 - L - 02 - ST | 1 | 2026-01-29 | 2026-01-31 | 2025-09-18 |  | FALSE | yes
| JD3RZ01L02ST359 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z01 - L - 02 - S | 1 | 2026-02-01 | 2026-02-02 |  |  | FALSE | yes
| JD3RZ01L02ST360 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z01 - L - 02 - ST | 1 | 2026-02-03 | 2026-02-04 |  |  | FALSE | yes
| JD3RZ01L02ST371 | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z01 - L - 02 - ST | 1 | 2026-01-27 | 2026-01-28 |  |  | FALSE | yes
| JD3RZ01L02ST372 | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z01 - L - 02 - ST | 1 | 2026-01-29 | 2026-01-31 |  |  | FALSE | yes
| JD3RZ01L02ST373 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z01 - L - 02 - ST | 1 | 2026-02-01 | 2026-02-02 |  |  | FALSE | yes
| JD3RZ01L02ST374 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z01 - L - 02 - S | 1 | 2026-02-03 | 2026-02-04 |  |  | FALSE | yes
| JD3RZ01L02ST375 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z01 - L - 02 - ST | 1 | 2026-02-05 | 2026-02-07 |  |  | FALSE | yes
| JD3RZ01L02ST378 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z01 - L - 02 - ST | 1 | 2026-02-03 | 2026-02-04 | 2025-09-18 |  | FALSE | yes
| JD3RZ01L02ST379 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z01 - L - 02 - S | 1 | 2026-02-05 | 2026-02-07 |  |  | FALSE | yes
| JD3RZ01L02ST380 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z01 - L - 02 - ST | 1 | 2026-02-08 | 2026-02-09 |  |  | FALSE | yes
| JD3RZ01L02ST381 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - Z01 - L - 02 - ST | 1 | 2026-02-01 | 2026-02-03 |  |  | FALSE | yes
| JD3RZ01L02ST382 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - Z01 - L - 02 - ST | 1 | 2026-02-04 | 2026-02-08 |  |  | FALSE | yes
| JD3RZ01L02ST383 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - Z01 - L - 02 - ST | 1 | 2026-02-09 | 2026-02-12 |  |  | FALSE | yes
| JD3RZ01L02ST384 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - Z01 - L - 02 - ST | 1 | 2026-02-14 | 2026-02-16 |  |  | FALSE | yes
| JD3RZ01L02ST385 | EXCAVATION Works for Catchbasine double - B6.33 05 39.10 - Z01 - L - 02 - ST | 1 | 2026-02-04 | 2026-02-05 |  |  | FALSE | yes
| JD3RZ01L02ST386 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - Z01 - L - 02 - ST | 1 | 2026-02-07 | 2026-02-09 |  |  | FALSE | yes
| JD3RZ01L02ST387 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z01 - L - 02 - ST | 1 | 2026-02-10 | 2026-02-12 |  |  | FALSE | yes
| JD3RZ01L02ST388 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z01 - L - 02 - ST | 1 | 2026-02-14 | 2026-02-15 |  |  | FALSE | yes
| JD3RZ01L02ST524345 | Concrete encasement for pipes - NNB6.33 42 11.25 - Z01 - L - 02 - ST | 1 | 2026-01-27 | 2026-02-18 |  |  | FALSE | yes
| JD3RZ01L02SUR01 | Surveying Works L - 02 | 1 |  |  |  |  | yes | FALSE
| JD3RZ01L02TSE439 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z01 - L - 02 - TSE | 1 | 2026-02-28 | 2026-03-01 |  |  | FALSE | yes
| JD3RZ01L02TSE440 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z01 - L - 02 - T | 1 | 2026-03-02 | 2026-03-03 |  |  | FALSE | yes
| JD3RZ01L02TSE441 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z01 - L - 02 - TSE | 1 | 2026-03-04 | 2026-03-05 |  |  | FALSE | yes
| JD3RZ01L02TSE442 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z01 - L - 02 - TSE | 1 | 2026-03-07 | 2026-03-08 |  |  | FALSE | yes
| JD3RZ01L02TSE443 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z01 - L - 02 - TSE | 1 | 2026-03-29 | 2026-03-30 |  |  | FALSE | yes
| JD3RZ01L02TSE444 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z01 - L - 02 - TSE | 1 | 2026-03-02 | 2026-03-07 |  |  | FALSE | yes
| JD3RZ01L02TSE445 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z01 - L - 02 - T | 1 | 2026-03-08 | 2026-03-12 |  |  | FALSE | yes
| JD3RZ01L02TSE446 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z01 - L - 02 - TSE | 1 | 2026-03-14 | 2026-03-23 |  |  | FALSE | yes
| JD3RZ01L02TSE447 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z01 - L - 02 - TSE | 1 | 2026-03-24 | 2026-03-30 |  |  | FALSE | yes
| JD3RZ01L02TSE448 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z01 - L - 02 - TSE | 1 | 2026-03-31 | 2026-04-06 |  |  | FALSE | yes
| JD3RZ01L02TSE564 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z01 - L - 02 - TSE | 1 | 2026-03-24 | 2026-03-25 |  |  | FALSE | yes
| JD3RZ01L02TSE565 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z01 - L - 02 - TSE | 1 | 2026-03-26 | 2026-03-28 |  |  | FALSE | yes
| JD3RZ01L02TSE566 | Installationfor gate valves 250 mm - B4.33 14 19.02 - Z01 - L - 02 - TSE | 1 | 2026-03-24 | 2026-03-25 |  |  | FALSE | yes
| JD3RZ01L02TSE567 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - Z01 - L - 02 - TSE | 1 | 2026-03-26 | 2026-03-28 |  |  | FALSE | yes
| JD3RZ01L02TSE582 | Installationfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - Z01 - L - 02 - TSE | 1 | 2026-03-24 | 2026-03-25 |  |  | FALSE | yes
| JD3RZ01L02TSE583 | Testing And Commtionningfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - Z01 - L - 02 | 1 | 2026-03-26 | 2026-03-28 |  |  | FALSE | yes
| JD3RZ01L02TSE612 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z01 - L - 02 - TSE | 1 | 2026-03-08 | 2026-03-09 |  |  | FALSE | yes
| JD3RZ01L02TSE613 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z01 - L - 02 - TSE | 1 | 2026-03-10 | 2026-03-11 |  |  | FALSE | yes
| JD3RZ01L02TSE614 | INSTALLATIONfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z01 - L - 02 - TSE | 1 | 2026-03-12 | 2026-03-14 |  |  | FALSE | yes
| JD3RZ01L02TSE615 | Backfilling Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z01 - L - 02 - TSE | 1 | 2026-03-29 | 2026-03-30 |  |  | FALSE | yes
| JD3RZ01L02WT389 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z01 - L - 02 - WT | 1 | 2026-04-07 | 2026-04-08 |  |  | FALSE | yes
| JD3RZ01L02WT390 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z01 - L - 02 - WT | 1 | 2026-04-09 | 2026-04-11 |  |  | FALSE | yes
| JD3RZ01L02WT391 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z01 - L - 02 - WT | 1 | 2026-04-12 | 2026-04-13 |  |  | FALSE | yes
| JD3RZ01L02WT392 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z01 - L - 02 - WT | 1 | 2026-04-14 | 2026-04-15 |  |  | FALSE | yes
| JD3RZ01L02WT393 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z01 - L - 02 - WT | 1 | 2026-04-16 | 2026-04-18 |  |  | FALSE | yes
| JD3RZ01L02WT424 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z01 - L - 02 - WT | 1 | 2026-04-09 | 2026-04-11 |  |  | FALSE | yes
| JD3RZ01L02WT425 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z01 - L - 02 - WT | 1 | 2026-04-12 | 2026-04-13 |  |  | FALSE | yes
| JD3RZ01L02WT426 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z01 - L - 02 - WT | 1 | 2026-04-14 | 2026-04-15 |  |  | FALSE | yes
| JD3RZ01L08ST1005.R | Excavation Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - Z01 - L - 08 - ST | 1 | 2026-02-07 | 2026-02-08 |  |  | FALSE | yes
| JD3RZ01L08ST1006.R | Plain Concrete Works For Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - Z01 - L - 08 - ST | 1 | 2026-02-09 | 2026-02-10 |  |  | FALSE | yes
| JD3RZ01L08ST1007.R | Raft Foundation for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - Z01 - L - 08 - ST | 1 | 2026-02-11 | 2026-02-12 |  |  | FALSE | yes
| JD3RZ01L08ST1008.R | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.03 - Z01 - L - 08 - ST | 1 | 2026-02-15 | 2026-02-16 |  |  | FALSE | yes
| JD3RZ01L08ST1009.R | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.03 - Z01 - L - 08 - ST | 1 | 2026-02-18 | 2026-02-19 |  |  | FALSE | yes
| JD3RZ01L08ST1010.R | Isolation Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - Z01 - L - 08 - ST | 1 | 2026-02-21 | 2026-02-22 |  |  | FALSE | yes
| JD3RZ01L08ST1011.R | Backfilling Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - Z01 - L - 08 - ST | 1 | 2026-02-23 | 2026-02-24 |  |  | FALSE | yes
| JD3RZ01L08ST1012 | Excavation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - Z01 - L - 08 - ST | 1 | 2026-02-09 | 2026-02-14 | 2025-08-20 |  | FALSE | yes
| JD3RZ01L08ST1013 | Plain Concrete Works For Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - Z01 - L - 08 - ST | 1 | 2026-02-15 | 2026-02-16 | 2025-08-21 |  | FALSE | yes
| JD3RZ01L08ST1014 | Raft Foundation for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - Z01 - L - 08 - ST | 1 | 2026-02-25 | 2026-03-10 | 2025-08-23 |  | FALSE | yes
| JD3RZ01L08ST1015 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - Z01 - L - 08 - ST | 1 | 2026-03-11 | 2026-03-31 | 2025-08-26 |  | FALSE | yes
| JD3RZ01L08ST1016 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - Z01 - L - 08 - ST | 1 | 2026-04-01 | 2026-04-14 | 2025-08-26 |  | FALSE | yes
| JD3RZ01L08ST1017 | Isolation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - Z01 - L - 08 - ST | 1 | 2026-04-15 | 2026-04-18 | 2025-08-31 |  | FALSE | yes
| JD3RZ01L08ST1018 | Backfilling Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - Z01 - L - 08 - ST | 1 | 2026-04-19 | 2026-04-21 | 2025-08-31 |  | FALSE | yes
| JD3RZ01L08ST1026 | Excavation Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - Z01 - L - 08 - ST | 1 | 2026-02-09 | 2026-02-15 | 2025-08-20 |  | FALSE | yes
| JD3RZ01L08ST1027 | Plain Concrete Works For Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - Z01 - L - 08 - ST | 1 | 2026-02-16 | 2026-02-17 | 2025-08-21 |  | FALSE | yes
| JD3RZ01L08ST1028 | Raft Foundation for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - Z01 - L - 08 - ST | 1 | 2026-02-18 | 2026-03-03 | 2025-08-26 |  | FALSE | yes
| JD3RZ01L08ST1029 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.06 - Z01 - L - 08 - ST | 1 | 2026-03-04 | 2026-03-22 | 2025-08-31 |  | FALSE | yes
| JD3RZ01L08ST1030 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.06 - Z01 - L - 08 - ST | 1 | 2026-03-23 | 2026-04-05 | 2025-08-31 |  | FALSE | yes
| JD3RZ01L08ST1031 | Isolation Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - Z01 - L - 08 - ST | 1 | 2026-04-06 | 2026-04-08 | 2025-09-14 |  | FALSE | yes
| JD3RZ01L08ST1032 | Backfilling Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - Z01 - L - 08 - ST | 1 | 2026-04-19 | 2026-04-23 | 2025-09-17 |  | FALSE | yes
| JD3RZ01L08ST1059 | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z01 - L - 08 - ST | 1 | 2026-03-12 | 2026-03-14 |  |  | FALSE | yes
| JD3RZ01L08ST1060 | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z01 - L - 08 - ST | 1 | 2026-03-15 | 2026-03-16 |  |  | FALSE | yes
| JD3RZ01L08ST1061 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z01 - L - 08 - ST | 1 | 2026-03-17 | 2026-03-18 |  |  | FALSE | yes
| JD3RZ01L08ST1062 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z01 - L - 08 - S | 1 | 2026-03-19 | 2026-03-21 |  |  | FALSE | yes
| JD3RZ01L08ST1063 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z01 - L - 08 - ST | 1 | 2026-03-22 | 2026-03-23 |  |  | FALSE | yes
| JD3RZ01L08ST1069 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z01 - L - 08 - ST | 1 | 2026-03-15 | 2026-03-16 |  |  | FALSE | yes
| JD3RZ01L08ST1070 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z01 - L - 08 - ST | 1 | 2026-03-17 | 2026-03-18 |  |  | FALSE | yes
| JD3RZ01L08ST1071 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z01 - L - 08 - ST | 1 | 2026-03-19 | 2026-03-21 |  |  | FALSE | yes
| JD3RZ01L08ST1072 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z01 - L - 08 - S | 1 | 2026-03-22 | 2026-03-23 |  |  | FALSE | yes
| JD3RZ01L08ST1073 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z01 - L - 08 - ST | 1 | 2026-03-24 | 2026-03-25 |  |  | FALSE | yes
| JD3RZ01L08ST1074 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z01 - L - 08 - ST | 1 | 2026-03-17 | 2026-03-19 | 2025-11-01 |  | FALSE | yes
| JD3RZ01L08ST1075 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z01 - L - 08 - ST | 1 | 2026-03-21 | 2026-03-25 | 2025-11-03 |  | FALSE | yes
| JD3RZ01L08ST1076 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z01 - L - 08 - ST | 1 | 2026-03-26 | 2026-03-31 |  |  | FALSE | yes
| JD3RZ01L08ST1077 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z01 - L - 08 - S | 1 | 2026-04-01 | 2026-04-04 |  |  | FALSE | yes
| JD3RZ01L08ST1078 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z01 - L - 08 - ST | 1 | 2026-04-05 | 2026-04-07 |  |  | FALSE | yes
| JD3RZ01L08ST1089 | Excavation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z01 - L - 08 - ST | 1 | 2026-03-21 | 2026-03-22 |  |  | FALSE | yes
| JD3RZ01L08ST1090 | Base Plain Concrete Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z01 - L - 08 - ST | 1 | 2026-03-23 | 2026-03-24 |  |  | FALSE | yes
| JD3RZ01L08ST1091 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z01 - L - 08 - ST | 1 | 2026-03-25 | 2026-03-26 |  |  | FALSE | yes
| JD3RZ01L08ST1092 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z01 - L - 08 - S | 1 | 2026-03-28 | 2026-03-29 |  |  | FALSE | yes
| JD3RZ01L08ST1093 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z01 - L - 08 - ST | 1 | 2026-03-30 | 2026-03-31 |  |  | FALSE | yes
| JD3RZ01L08ST1094 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - Z01 - L - 08 - ST | 1 | 2026-03-23 | 2026-03-25 |  |  | FALSE | yes
| JD3RZ01L08ST1095 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - Z01 - L - 08 - ST | 1 | 2026-03-26 | 2026-03-31 |  |  | FALSE | yes
| JD3RZ01L08ST1096 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - Z01 - L - 08 - ST | 1 | 2026-04-01 | 2026-04-06 |  |  | FALSE | yes
| JD3RZ01L08ST1097 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - Z01 - L - 08 - ST | 1 | 2026-04-07 | 2026-04-09 |  |  | FALSE | yes
| JD3RZ01L08ST1098 | EXCAVATION Works for Catchbasine double - B6.33 05 39.10 - Z01 - L - 08 - ST | 1 | 2026-03-26 | 2026-03-29 |  |  | FALSE | yes
| JD3RZ01L08ST1099 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - Z01 - L - 08 - ST | 1 | 2026-03-30 | 2026-04-02 |  |  | FALSE | yes
| JD3RZ01L08ST1100 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z01 - L - 08 - ST | 1 | 2026-04-04 | 2026-04-07 |  |  | FALSE | yes
| JD3RZ01L08ST1101 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z01 - L - 08 - ST | 1 | 2026-04-08 | 2026-04-11 |  |  | FALSE | yes
| JD3RZ01L08ST524346 | Concrete encasement for pipes - NNB6.33 42 11.25 - Z01 - L - 08 - ST | 1 | 2026-03-17 | 2026-03-23 |  |  | FALSE | yes
| JD3RZ01L08ST876 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z01 - L - 08 - ST | 1 | 2026-02-16 | 2026-02-18 |  |  | FALSE | yes
| JD3RZ01L08ST877 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z01 - L - 08 | 1 | 2026-02-19 | 2026-02-22 |  |  | FALSE | yes
| JD3RZ01L08ST878 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z01 - L - 08 - ST | 1 | 2026-02-23 | 2026-02-26 |  |  | FALSE | yes
| JD3RZ01L08ST879 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z01 - L - 08 - ST | 1 | 2026-02-28 | 2026-03-03 |  |  | FALSE | yes
| JD3RZ01L08ST880 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z01 - L - 08 - ST | 1 | 2026-03-24 | 2026-03-29 |  |  | FALSE | yes
| JD3RZ01L08ST881 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z01 - L - 08 - ST | 1 | 2026-02-19 | 2026-02-21 |  |  | FALSE | yes
| JD3RZ01L08ST882 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z01 - L - 08 | 1 | 2026-02-22 | 2026-02-23 |  |  | FALSE | yes
| JD3RZ01L08ST883 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z01 - L - 08 - ST | 1 | 2026-02-24 | 2026-02-25 |  |  | FALSE | yes
| JD3RZ01L08ST884 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z01 - L - 08 - ST | 1 | 2026-02-26 | 2026-02-28 |  |  | FALSE | yes
| JD3RZ01L08ST885 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z01 - L - 08 - ST | 1 | 2026-03-24 | 2026-03-25 |  |  | FALSE | yes
| JD3RZ01L08ST886 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z01 - L - 08 - ST | 1 | 2026-02-22 | 2026-02-23 | 2025-10-29 |  | FALSE | yes
| JD3RZ01L08ST887 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z01 - L - 08 | 1 | 2026-02-24 | 2026-02-25 | 2025-11-01 |  | FALSE | yes
| JD3RZ01L08ST888 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z01 - L - 08 - ST | 1 | 2026-02-26 | 2026-02-28 | 2025-11-03 |  | FALSE | yes
| JD3RZ01L08ST889 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z01 - L - 08 - ST | 1 | 2026-03-01 | 2026-03-02 |  |  | FALSE | yes
| JD3RZ01L08ST890 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z01 - L - 08 - ST | 1 | 2026-03-24 | 2026-03-26 |  |  | FALSE | yes
| JD3RZ01L08ST893 | Installing for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m - B6.33 42 11.03 - Z01 - L - 08 - ST | 1 | 2026-03-01 | 2026-03-02 |  |  | FALSE | yes
| JD3RZ01L08ST894 | Primary Test for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m - B6.33 42 11.03 - Z01 - L - 08 - ST | 1 | 2026-03-03 | 2026-03-04 |  |  | FALSE | yes
| JD3RZ01L08ST895 | Backfilling Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m - B6.33 42 11.03 - Z01 - L - 08 - ST | 1 | 2026-03-24 | 2026-03-25 |  |  | FALSE | yes
| JD3RZ01L08ST896 | Excavation Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - Z01 - L - 08 - ST | 1 | 2026-02-26 | 2026-02-28 | 2025-10-30 |  | FALSE | yes
| JD3RZ01L08ST897 | Soil Replacement and Bedding Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - Z01 - L - 08 | 1 | 2026-03-01 | 2026-03-02 | 2025-11-02 |  | FALSE | yes
| JD3RZ01L08ST898 | Installing for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - Z01 - L - 08 - ST | 1 | 2026-03-03 | 2026-03-04 | 2025-11-04 |  | FALSE | yes
| JD3RZ01L08ST899 | Primary Test for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - Z01 - L - 08 - ST | 1 | 2026-03-05 | 2026-03-07 |  |  | FALSE | yes
| JD3RZ01L08ST900 | Backfilling Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - Z01 - L - 08 - ST | 1 | 2026-03-24 | 2026-03-25 |  |  | FALSE | yes
| JD3RZ01L08ST918 | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - Z01 - L - 08 - ST | 1 | 2026-03-05 | 2026-03-07 |  |  | FALSE | yes
| JD3RZ01L08ST919 | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - Z01 - L - 08 - ST | 1 | 2026-03-08 | 2026-03-09 |  |  | FALSE | yes
| JD3RZ01L08ST920 | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - Z01 - L - 08 - ST | 1 | 2026-03-24 | 2026-03-25 |  |  | FALSE | yes
| JD3RZ01L08ST929 | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - Z01 - L - 08 - ST | 1 | 2026-03-10 | 2026-03-11 |  |  | FALSE | yes
| JD3RZ01L08ST936 | Excavation Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - Z01 - L - 08 - ST | 1 | 2026-03-05 | 2026-03-07 | 2025-10-01 |  | FALSE | yes
| JD3RZ01L08ST937 | Soil Replacement and Bedding Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - Z01 - L - 08 | 1 | 2026-03-08 | 2026-03-09 | 2025-10-02 |  | FALSE | yes
| JD3RZ01L08ST938 | Installing for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - Z01 - L - 08 - ST | 1 | 2026-03-10 | 2026-03-11 | 2025-10-05 |  | FALSE | yes
| JD3RZ01L08ST939 | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - Z01 - L - 08 - ST | 1 | 2026-03-12 | 2026-03-14 |  |  | FALSE | yes
| JD3RZ01L08ST940 | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - Z01 - L - 08 - ST | 1 | 2026-03-24 | 2026-03-26 |  |  | FALSE | yes
| JD3RZ01L08ST941 | Excavation Works for GRP Pipe Line 900 mm - depth from 2.51 to 3.50 m - B6.33 42 11.13 - Z01 - L - 08 - ST | 1 | 2026-03-08 | 2026-03-09 |  |  | FALSE | yes
| JD3RZ01L08ST942 | Soil Replacement and Bedding Works for GRP Pipe Line 900 mm - depth from 2.51 to 3.50 m - B6.33 42 11.13 - Z01 - L - 08 | 1 | 2026-03-10 | 2026-03-11 |  |  | FALSE | yes
| JD3RZ01L08ST943 | Installing for GRP Pipe Line 900 mm - depth from 2.51 to 3.50 m - B6.33 42 11.13 - Z01 - L - 08 - ST | 1 | 2026-03-12 | 2026-03-14 |  |  | FALSE | yes
| JD3RZ01L08ST944 | Primary Test for GRP Pipe Line 900 mm - depth from 2.51 to 3.50 m - B6.33 42 11.13 - Z01 - L - 08 - ST | 1 | 2026-03-15 | 2026-03-16 |  |  | FALSE | yes
| JD3RZ01L08ST945 | Backfilling Works for GRP Pipe Line 900 mm - depth from 2.51 to 3.50 m - B6.33 42 11.13 - Z01 - L - 08 - ST | 1 | 2026-03-24 | 2026-03-25 |  |  | FALSE | yes
| JD3RZ01L08ST986 | Excavation Works for GRP Pipe Line 1200 mm - depth from 2.51 to 3.50 m - B6.33 42 11.24 - Z01 - L - 08 - ST | 1 | 2026-03-10 | 2026-03-11 |  |  | FALSE | yes
| JD3RZ01L08ST987 | Soil Replacement and Bedding Works for GRP Pipe Line 1200 mm - depth from 2.51 to 3.50 m - B6.33 42 11.24 - Z01 - L - 08 | 1 | 2026-03-12 | 2026-03-14 |  |  | FALSE | yes
| JD3RZ01L08ST988 | Installing for GRP Pipe Line 1200 mm - depth from 2.51 to 3.50 m - B6.33 42 11.24 - Z01 - L - 08 - ST | 1 | 2026-03-15 | 2026-03-16 |  |  | FALSE | yes
| JD3RZ01L08ST989 | Primary Test for GRP Pipe Line 1200 mm - depth from 2.51 to 3.50 m - B6.33 42 11.24 - Z01 - L - 08 - ST | 1 | 2026-03-17 | 2026-03-18 |  |  | FALSE | yes
| JD3RZ01L08ST990 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 2.51 to 3.50 m - B6.33 42 11.24 - Z01 - L - 08 - ST | 1 | 2026-03-24 | 2026-03-25 |  |  | FALSE | yes
| JD3RZ01L08TSE1152 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z01 - L - 08 - TSE | 1 | 2026-04-12 | 2026-04-13 |  |  | FALSE | yes
| JD3RZ01L08TSE1153 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z01 - L - 08 - T | 1 | 2026-04-14 | 2026-04-15 |  |  | FALSE | yes
| JD3RZ01L08TSE1154 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z01 - L - 08 - TSE | 1 | 2026-04-16 | 2026-04-18 |  |  | FALSE | yes
| JD3RZ01L08TSE1155 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z01 - L - 08 - TSE | 1 | 2026-04-19 | 2026-04-20 |  |  | FALSE | yes
| JD3RZ01L08TSE1156 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z01 - L - 08 - TSE | 1 | 2026-05-06 | 2026-05-07 |  |  | FALSE | yes
| JD3RZ01L08TSE1157 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z01 - L - 08 - TSE | 1 | 2026-04-14 | 2026-04-18 |  |  | FALSE | yes
| JD3RZ01L08TSE1158 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z01 - L - 08 - T | 1 | 2026-04-19 | 2026-04-22 |  |  | FALSE | yes
| JD3RZ01L08TSE1159 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z01 - L - 08 - TSE | 1 | 2026-04-23 | 2026-04-30 |  |  | FALSE | yes
| JD3RZ01L08TSE1160 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z01 - L - 08 - TSE | 1 | 2026-05-02 | 2026-05-06 |  |  | FALSE | yes
| JD3RZ01L08TSE1161 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z01 - L - 08 - TSE | 1 | 2026-05-07 | 2026-05-12 |  |  | FALSE | yes
| JD3RZ01L08TSE1277 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z01 - L - 08 - TSE | 1 | 2026-05-02 | 2026-05-03 |  |  | FALSE | yes
| JD3RZ01L08TSE1278 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z01 - L - 08 - TSE | 1 | 2026-05-04 | 2026-05-05 |  |  | FALSE | yes
| JD3RZ01L08TSE1279 | Installationfor gate valves 250 mm - B4.33 14 19.02 - Z01 - L - 08 - TSE | 1 | 2026-05-02 | 2026-05-03 |  |  | FALSE | yes
| JD3RZ01L08TSE1280 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - Z01 - L - 08 - TSE | 1 | 2026-05-04 | 2026-05-05 |  |  | FALSE | yes
| JD3RZ01L08TSE1289 | Installationfor Wash - Out valves 100 mm. - on pipes with diameter 110 - 400 mm - B4.33 14 19.07 - Z01 - L - 08 - TSE | 1 | 2026-05-02 | 2026-05-03 |  |  | FALSE | yes
| JD3RZ01L08TSE1290 | Testing And Commtionningfor Wash - Out valves 100 mm. - on pipes with diameter 110 - 400 mm - B4.33 14 19.07 - Z01 - L - | 1 | 2026-05-04 | 2026-05-05 |  |  | FALSE | yes
| JD3RZ01L08TSE1313 | EXCAVATION and Bedding Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - Z01 - L - 08 - TSE | 1 | 2026-04-19 | 2026-04-20 |  |  | FALSE | yes
| JD3RZ01L08TSE1314 | Plain Concrete Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - Z01 - L - 08 - TSE | 1 | 2026-04-21 | 2026-04-22 |  |  | FALSE | yes
| JD3RZ01L08TSE1315 | INSTALLATIONfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - Z01 - L - 08 - TSE | 1 | 2026-04-23 | 2026-04-25 |  |  | FALSE | yes
| JD3RZ01L08TSE1316 | Backfilling Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - Z01 - L - 08 - TSE | 1 | 2026-05-06 | 2026-05-07 |  |  | FALSE | yes
| JD3RZ01L08WT1102 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z01 - L - 08 - WT | 1 | 2026-05-13 | 2026-05-14 |  |  | FALSE | yes
| JD3RZ01L08WT1103 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z01 - L - 08 - WT | 1 | 2026-05-16 | 2026-05-17 |  |  | FALSE | yes
| JD3RZ01L08WT1104 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z01 - L - 08 - WT | 1 | 2026-05-18 | 2026-05-19 |  |  | FALSE | yes
| JD3RZ01L08WT1105 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z01 - L - 08 - WT | 1 | 2026-05-20 | 2026-05-21 |  |  | FALSE | yes
| JD3RZ01L08WT1106 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z01 - L - 08 - WT | 1 | 2026-05-23 | 2026-05-24 |  |  | FALSE | yes
| JD3RZ01L08WT1137 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z01 - L - 08 - WT | 1 | 2026-05-16 | 2026-05-17 |  |  | FALSE | yes
| JD3RZ01L08WT1138 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z01 - L - 08 - WT | 1 | 2026-05-18 | 2026-05-19 |  |  | FALSE | yes
| JD3RZ01L08WT1139 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z01 - L - 08 - WT | 1 | 2026-05-20 | 2026-05-21 |  |  | FALSE | yes
| JD3RZ01L09ST1589 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z01 - L - 09 - ST | 1 | 2026-02-09 | 2026-02-11 | 2025-10-22 |  | FALSE | yes
| JD3RZ01L09ST1590 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z01 - L - 09 | 1 | 2026-02-12 | 2026-02-15 | 2025-10-25 |  | FALSE | yes
| JD3RZ01L09ST1591 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z01 - L - 09 - ST | 1 | 2026-02-16 | 2026-02-19 | 2025-10-30 |  | FALSE | yes
| JD3RZ01L09ST1592 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z01 - L - 09 - ST | 1 | 2026-02-21 | 2026-02-24 |  |  | FALSE | yes
| JD3RZ01L09ST1593 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z01 - L - 09 - ST | 1 | 2026-03-08 | 2026-03-12 |  |  | FALSE | yes
| JD3RZ01L09ST1594 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z01 - L - 09 - ST | 1 | 2026-02-12 | 2026-02-14 |  |  | FALSE | yes
| JD3RZ01L09ST1595 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z01 - L - 09 | 1 | 2026-02-15 | 2026-02-16 |  |  | FALSE | yes
| JD3RZ01L09ST1596 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z01 - L - 09 - ST | 1 | 2026-02-17 | 2026-02-18 |  |  | FALSE | yes
| JD3RZ01L09ST1597 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z01 - L - 09 - ST | 1 | 2026-02-19 | 2026-02-21 |  |  | FALSE | yes
| JD3RZ01L09ST1598 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z01 - L - 09 - ST | 1 | 2026-03-08 | 2026-03-09 |  |  | FALSE | yes
| JD3RZ01L09ST1599 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z01 - L - 09 - ST | 1 | 2026-02-15 | 2026-02-16 |  |  | FALSE | yes
| JD3RZ01L09ST1600 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z01 - L - 09 | 1 | 2026-02-17 | 2026-02-18 |  |  | FALSE | yes
| JD3RZ01L09ST1601 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z01 - L - 09 - ST | 1 | 2026-02-19 | 2026-02-21 |  |  | FALSE | yes
| JD3RZ01L09ST1602 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z01 - L - 09 - ST | 1 | 2026-02-22 | 2026-02-23 |  |  | FALSE | yes
| JD3RZ01L09ST1603 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z01 - L - 09 - ST | 1 | 2026-03-08 | 2026-03-09 |  |  | FALSE | yes
| JD3RZ01L09ST1612 | Primary Test for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - Z01 - L - 09 - ST | 1 | 2026-02-24 | 2026-02-25 |  |  | FALSE | yes
| JD3RZ01L09ST1622 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - Z01 - L - 09 - ST | 1 | 2026-02-26 | 2026-02-28 |  |  | FALSE | yes
| JD3RZ01L09ST1642.R | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - Z01 - L - 09 - ST - Remaining | 1 | 2026-02-22 | 2026-02-23 |  |  | FALSE | yes
| JD3RZ01L09ST1652.R | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - Z01 - L - 09 - ST - Remaining | 1 | 2026-02-24 | 2026-02-25 |  |  | FALSE | yes
| JD3RZ01L09ST1702 | Primary Test for GRP Pipe Line 1200 mm - depth from 2.51 to 3.50 m - B6.33 42 11.24 - Z01 - L - 09 - ST | 1 | 2026-03-01 | 2026-03-02 |  |  | FALSE | yes
| JD3RZ01L09ST1774 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z01 - L - 09 - ST | 1 | 2026-03-01 | 2026-03-02 |  |  | FALSE | yes
| JD3RZ01L09ST1775 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z01 - L - 09 - S | 1 | 2026-03-03 | 2026-03-04 |  |  | FALSE | yes
| JD3RZ01L09ST1776 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z01 - L - 09 - ST | 1 | 2026-03-05 | 2026-03-07 |  |  | FALSE | yes
| JD3RZ01L09ST1784.R | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z01 - L - 09 - ST - Remaini | 1 | 2026-02-24 | 2026-02-25 |  |  | FALSE | yes
| JD3RZ01L09ST1785 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z01 - L - 09 - S | 1 | 2026-02-26 | 2026-02-28 |  |  | FALSE | yes
| JD3RZ01L09ST1786 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z01 - L - 09 - ST | 1 | 2026-03-01 | 2026-03-02 |  |  | FALSE | yes
| JD3RZ01L09ST1787 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z01 - L - 09 - ST | 1 | 2026-02-26 | 2026-02-28 |  |  | FALSE | yes
| JD3RZ01L09ST1788 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z01 - L - 09 - ST | 1 | 2026-03-01 | 2026-03-02 |  |  | FALSE | yes
| JD3RZ01L09ST1789 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z01 - L - 09 - ST | 1 | 2026-03-03 | 2026-03-04 |  |  | FALSE | yes
| JD3RZ01L09ST1790 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z01 - L - 09 - S | 1 | 2026-03-05 | 2026-03-07 |  |  | FALSE | yes
| JD3RZ01L09ST1791 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z01 - L - 09 - ST | 1 | 2026-03-08 | 2026-03-09 |  |  | FALSE | yes
| JD3RZ01L09ST1804.R | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z01 - L - 09 - ST - Remaini | 1 | 2026-02-26 | 2026-02-28 |  |  | FALSE | yes
| JD3RZ01L09ST1805 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z01 - L - 09 - S | 1 | 2026-03-01 | 2026-03-02 |  |  | FALSE | yes
| JD3RZ01L09ST1806 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z01 - L - 09 - ST | 1 | 2026-03-03 | 2026-03-04 |  |  | FALSE | yes
| JD3RZ01L09ST1807 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - Z01 - L - 09 - ST | 1 | 2026-03-01 | 2026-03-02 | 2025-10-26 |  | FALSE | yes
| JD3RZ01L09ST1808 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - Z01 - L - 09 - ST | 1 | 2026-03-03 | 2026-03-05 |  |  | FALSE | yes
| JD3RZ01L09ST1809 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - Z01 - L - 09 - ST | 1 | 2026-03-07 | 2026-03-09 |  |  | FALSE | yes
| JD3RZ01L09ST1810 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - Z01 - L - 09 - ST | 1 | 2026-03-10 | 2026-03-11 |  |  | FALSE | yes
| JD3RZ01L09ST1811 | EXCAVATION Works for Catchbasine double - B6.33 05 39.10 - Z01 - L - 09 - ST | 1 | 2026-03-03 | 2026-03-04 |  |  | FALSE | yes
| JD3RZ01L09ST1812 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - Z01 - L - 09 - ST | 1 | 2026-03-05 | 2026-03-08 |  |  | FALSE | yes
| JD3RZ01L09ST1813 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z01 - L - 09 - ST | 1 | 2026-03-09 | 2026-03-11 |  |  | FALSE | yes
| JD3RZ01L09ST1814 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z01 - L - 09 - ST | 1 | 2026-03-12 | 2026-03-14 |  |  | FALSE | yes
| JD3RZ01L09ST524347 | Concrete encasement for pipes - NNB6.33 42 11.25 - Z01 - L - 09 - ST | 1 | 2026-03-01 | 2026-03-07 |  |  | FALSE | yes
| JD3RZ01L09TSE1865 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z01 - L - 09 - TSE | 1 | 2026-03-14 | 2026-03-17 |  |  | FALSE | yes
| JD3RZ01L09TSE1866 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z01 - L - 09 - T | 1 | 2026-03-18 | 2026-03-23 |  |  | FALSE | yes
| JD3RZ01L09TSE1867 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z01 - L - 09 - TSE | 1 | 2026-03-24 | 2026-04-01 |  |  | FALSE | yes
| JD3RZ01L09TSE1868 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z01 - L - 09 - TSE | 1 | 2026-04-02 | 2026-04-07 |  |  | FALSE | yes
| JD3RZ01L09TSE1869 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z01 - L - 09 - TSE | 1 | 2026-04-08 | 2026-04-13 |  |  | FALSE | yes
| JD3RZ01L09TSE1990 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z01 - L - 09 - TSE | 1 | 2026-04-02 | 2026-04-04 |  |  | FALSE | yes
| JD3RZ01L09TSE1991 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z01 - L - 09 - TSE | 1 | 2026-04-05 | 2026-04-06 |  |  | FALSE | yes
| JD3RZ01L09TSE2002 | Installationfor Wash - Out valves 100 mm. - on pipes with diameter 110 - 400 mm - B4.33 14 19.07 - Z01 - L - 09 - TSE | 1 | 2026-04-02 | 2026-04-04 |  |  | FALSE | yes
| JD3RZ01L09TSE2003 | Testing And Commtionningfor Wash - Out valves 100 mm. - on pipes with diameter 110 - 400 mm - B4.33 14 19.07 - Z01 - L - | 1 | 2026-04-05 | 2026-04-06 |  |  | FALSE | yes
| JD3RZ01L09TSE2008 | Installationfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - Z01 - L - 09 - TSE | 1 | 2026-04-02 | 2026-04-04 |  |  | FALSE | yes
| JD3RZ01L09TSE2009 | Testing And Commtionningfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - Z01 - L - 09 | 1 | 2026-04-05 | 2026-04-06 |  |  | FALSE | yes
| JD3RZ01L09TSE2026 | EXCAVATION and Bedding Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - Z01 - L - 09 - TSE | 1 | 2026-03-18 | 2026-03-19 |  |  | FALSE | yes
| JD3RZ01L09TSE2027 | Plain Concrete Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - Z01 - L - 09 - TSE | 1 | 2026-03-21 | 2026-03-22 |  |  | FALSE | yes
| JD3RZ01L09TSE2028 | INSTALLATIONfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - Z01 - L - 09 - TSE | 1 | 2026-03-23 | 2026-03-24 |  |  | FALSE | yes
| JD3RZ01L09TSE2029 | Backfilling Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - Z01 - L - 09 - TSE | 1 | 2026-04-07 | 2026-04-08 |  |  | FALSE | yes
| JD3RZ01L09TSE2038 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z01 - L - 09 - TSE | 1 | 2026-03-18 | 2026-03-19 |  |  | FALSE | yes
| JD3RZ01L09TSE2039 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z01 - L - 09 - TSE | 1 | 2026-03-21 | 2026-03-22 |  |  | FALSE | yes
| JD3RZ01L09TSE2040 | INSTALLATIONfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z01 - L - 09 - TSE | 1 | 2026-03-23 | 2026-03-24 |  |  | FALSE | yes
| JD3RZ01L09TSE2041 | Backfilling Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z01 - L - 09 - TSE | 1 | 2026-04-07 | 2026-04-08 |  |  | FALSE | yes
| JD3RZ01L09WT1815 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z01 - L - 09 - WT | 1 | 2026-04-14 | 2026-04-15 |  |  | FALSE | yes
| JD3RZ01L09WT1816 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z01 - L - 09 - WT | 1 | 2026-04-16 | 2026-04-18 |  |  | FALSE | yes
| JD3RZ01L09WT1817 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z01 - L - 09 - WT | 1 | 2026-04-19 | 2026-04-20 |  |  | FALSE | yes
| JD3RZ01L09WT1818 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z01 - L - 09 - WT | 1 | 2026-04-21 | 2026-04-22 |  |  | FALSE | yes
| JD3RZ01L09WT1819 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z01 - L - 09 - WT | 1 | 2026-04-23 | 2026-04-25 |  |  | FALSE | yes
| JD3RZ01L09WT1850 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z01 - L - 09 - WT | 1 | 2026-04-14 | 2026-04-15 |  |  | FALSE | yes
| JD3RZ01L09WT1851 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z01 - L - 09 - WT | 1 | 2026-04-16 | 2026-04-18 |  |  | FALSE | yes
| JD3RZ01L09WT1852 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z01 - L - 09 - WT | 1 | 2026-04-19 | 2026-04-20 |  |  | FALSE | yes
| JD3RZ01L10ST2302 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z01 - L - 10 - ST | 1 | 2026-04-25 | 2026-04-27 | 2025-10-30 |  | FALSE | yes
| JD3RZ01L10ST2303 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z01 - L - 10 | 1 | 2026-04-28 | 2026-04-30 | 2025-11-03 |  | FALSE | yes
| JD3RZ01L10ST2304 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z01 - L - 10 - ST | 1 | 2026-05-02 | 2026-05-05 | 2025-11-04 |  | FALSE | yes
| JD3RZ01L10ST2305 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z01 - L - 10 - ST | 1 | 2026-05-06 | 2026-05-10 |  |  | FALSE | yes
| JD3RZ01L10ST2306 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z01 - L - 10 - ST | 1 | 2026-06-04 | 2026-06-09 |  |  | FALSE | yes
| JD3RZ01L10ST2307 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z01 - L - 10 - ST | 1 | 2026-04-28 | 2026-04-29 |  |  | FALSE | yes
| JD3RZ01L10ST2308 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z01 - L - 10 | 1 | 2026-04-30 | 2026-05-02 |  |  | FALSE | yes
| JD3RZ01L10ST2309 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z01 - L - 10 - ST | 1 | 2026-05-03 | 2026-05-04 |  |  | FALSE | yes
| JD3RZ01L10ST2310 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z01 - L - 10 - ST | 1 | 2026-05-05 | 2026-05-06 |  |  | FALSE | yes
| JD3RZ01L10ST2311 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z01 - L - 10 - ST | 1 | 2026-06-04 | 2026-06-06 |  |  | FALSE | yes
| JD3RZ01L10ST2312 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z01 - L - 10 - ST | 1 | 2026-05-21 | 2026-05-23 |  |  | FALSE | yes
| JD3RZ01L10ST2313 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z01 - L - 10 | 1 | 2026-05-24 | 2026-05-25 |  |  | FALSE | yes
| JD3RZ01L10ST2314 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z01 - L - 10 - ST | 1 | 2026-05-26 | 2026-05-27 |  |  | FALSE | yes
| JD3RZ01L10ST2315 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z01 - L - 10 - ST | 1 | 2026-05-28 | 2026-05-30 |  |  | FALSE | yes
| JD3RZ01L10ST2316 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z01 - L - 10 - ST | 1 | 2026-06-04 | 2026-06-06 |  |  | FALSE | yes
| JD3RZ01L10ST2325.R | Primary Test for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - Z01 - L - 10 - ST - Remaining | 1 | 2026-05-07 | 2026-05-09 |  |  | FALSE | yes
| JD3RZ01L10ST2365.R | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - Z01 - L - 10 - ST - Remaining | 1 | 2026-05-21 | 2026-05-23 | 2025-10-19 |  | FALSE | yes
| JD3RZ01L10ST2487 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z01 - L - 10 - ST | 1 | 2026-05-14 | 2026-05-16 | 2025-10-21 |  | FALSE | yes
| JD3RZ01L10ST2488 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z01 - L - 10 - S | 1 | 2026-05-17 | 2026-05-18 |  |  | FALSE | yes
| JD3RZ01L10ST2489 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z01 - L - 10 - ST | 1 | 2026-06-04 | 2026-06-06 |  |  | FALSE | yes
| JD3RZ01L10ST2498 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z01 - L - 10 - S | 1 | 2026-05-19 | 2026-05-20 |  |  | FALSE | yes
| JD3RZ01L10ST2499 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z01 - L - 10 - ST | 1 | 2026-06-04 | 2026-06-06 |  |  | FALSE | yes
| JD3RZ01L10ST2502 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z01 - L - 10 - ST | 1 | 2026-05-19 | 2026-05-20 |  |  | FALSE | yes
| JD3RZ01L10ST2503 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z01 - L - 10 - S | 1 | 2026-05-21 | 2026-05-23 |  |  | FALSE | yes
| JD3RZ01L10ST2504 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z01 - L - 10 - ST | 1 | 2026-06-04 | 2026-06-06 |  |  | FALSE | yes
| JD3RZ01L10ST2520 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - Z01 - L - 10 - ST | 1 | 2026-05-17 | 2026-05-18 |  |  | FALSE | yes
| JD3RZ01L10ST2521 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - Z01 - L - 10 - ST | 1 | 2026-05-19 | 2026-05-21 |  |  | FALSE | yes
| JD3RZ01L10ST2522 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - Z01 - L - 10 - ST | 1 | 2026-05-23 | 2026-05-25 |  |  | FALSE | yes
| JD3RZ01L10ST2523 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - Z01 - L - 10 - ST | 1 | 2026-06-04 | 2026-06-06 |  |  | FALSE | yes
| JD3RZ01L10ST2524 | EXCAVATION Works for Catchbasine double - B6.33 05 39.10 - Z01 - L - 10 - ST | 1 | 2026-05-19 | 2026-05-20 |  |  | FALSE | yes
| JD3RZ01L10ST2525 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - Z01 - L - 10 - ST | 1 | 2026-05-21 | 2026-05-24 |  |  | FALSE | yes
| JD3RZ01L10ST2526 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z01 - L - 10 - ST | 1 | 2026-05-25 | 2026-05-27 |  |  | FALSE | yes
| JD3RZ01L10ST2527 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z01 - L - 10 - ST | 1 | 2026-06-04 | 2026-06-06 |  |  | FALSE | yes
| JD3RZ01L10ST524348 | Concrete encasement for pipes - NNB6.33 42 11.25 - Z01 - L - 10 - ST | 1 | 2026-05-28 | 2026-06-03 |  |  | FALSE | yes
| JD3RZ01L10TSE2578 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z01 - L - 10 - TSE | 1 | 2026-06-07 | 2026-06-10 |  |  | FALSE | yes
| JD3RZ01L10TSE2579 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z01 - L - 10 - T | 1 | 2026-06-11 | 2026-06-15 |  |  | FALSE | yes
| JD3RZ01L10TSE2580 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z01 - L - 10 - TSE | 1 | 2026-06-16 | 2026-06-23 |  |  | FALSE | yes
| JD3RZ01L10TSE2581 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z01 - L - 10 - TSE | 1 | 2026-06-24 | 2026-06-29 |  |  | FALSE | yes
| JD3RZ01L10TSE2582 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z01 - L - 10 - TSE | 1 | 2026-06-30 | 2026-07-05 |  |  | FALSE | yes
| JD3RZ01L10TSE2583 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z01 - L - 10 - TSE | 1 | 2026-06-11 | 2026-06-13 |  |  | FALSE | yes
| JD3RZ01L10TSE2584 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z01 - L - 10 - T | 1 | 2026-06-14 | 2026-06-15 |  |  | FALSE | yes
| JD3RZ01L10TSE2585 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z01 - L - 10 - TSE | 1 | 2026-06-16 | 2026-06-17 |  |  | FALSE | yes
| JD3RZ01L10TSE2586 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z01 - L - 10 - TSE | 1 | 2026-06-18 | 2026-06-20 |  |  | FALSE | yes
| JD3RZ01L10TSE2587 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z01 - L - 10 - TSE | 1 | 2026-06-29 | 2026-06-30 |  |  | FALSE | yes
| JD3RZ01L10TSE2703 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z01 - L - 10 - TSE | 1 | 2026-06-24 | 2026-06-25 |  |  | FALSE | yes
| JD3RZ01L10TSE2704 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z01 - L - 10 - TSE | 1 | 2026-06-27 | 2026-06-28 |  |  | FALSE | yes
| JD3RZ01L10TSE2715 | Installationfor Wash - Out valves 100 mm. - on pipes with diameter 110 - 400 mm - B4.33 14 19.07 - Z01 - L - 10 - TSE | 1 | 2026-06-24 | 2026-06-25 |  |  | FALSE | yes
| JD3RZ01L10TSE2716 | Testing And Commtionningfor Wash - Out valves 100 mm. - on pipes with diameter 110 - 400 mm - B4.33 14 19.07 - Z01 - L - | 1 | 2026-06-27 | 2026-06-28 |  |  | FALSE | yes
| JD3RZ01L10TSE2739 | EXCAVATION and Bedding Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - Z01 - L - 10 - TSE | 1 | 2026-06-14 | 2026-06-15 |  |  | FALSE | yes
| JD3RZ01L10TSE2740 | Plain Concrete Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - Z01 - L - 10 - TSE | 1 | 2026-06-16 | 2026-06-17 |  |  | FALSE | yes
| JD3RZ01L10TSE2741 | INSTALLATIONfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - Z01 - L - 10 - TSE | 1 | 2026-06-18 | 2026-06-20 |  |  | FALSE | yes
| JD3RZ01L10TSE2742 | Backfilling Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - Z01 - L - 10 - TSE | 1 | 2026-07-01 | 2026-07-02 |  |  | FALSE | yes
| JD3RZ01L10WT2528 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z01 - L - 10 - WT | 1 | 2026-06-11 | 2026-06-13 |  |  | FALSE | yes
| JD3RZ01L10WT2529 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z01 - L - 10 - WT | 1 | 2026-06-14 | 2026-06-15 |  |  | FALSE | yes
| JD3RZ01L10WT2530 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z01 - L - 10 - WT | 1 | 2026-06-16 | 2026-06-17 |  |  | FALSE | yes
| JD3RZ01L10WT2531 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z01 - L - 10 - WT | 1 | 2026-06-18 | 2026-06-20 |  |  | FALSE | yes
| JD3RZ01L10WT2532 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z01 - L - 10 - WT | 1 | 2026-06-21 | 2026-06-22 |  |  | FALSE | yes
| JD3RZ01L10WT2563 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z01 - L - 10 - WT | 1 | 2026-06-14 | 2026-06-15 |  |  | FALSE | yes
| JD3RZ01L10WT2564 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z01 - L - 10 - WT | 1 | 2026-06-16 | 2026-06-17 |  |  | FALSE | yes
| JD3RZ01L10WT2565 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z01 - L - 10 - WT | 1 | 2026-06-18 | 2026-06-20 |  |  | FALSE | yes
| JD3RZ01L11ST3015 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z01 - L - 11 - ST | 1 | 2026-03-23 | 2026-03-25 | 2025-10-22 |  | FALSE | yes
| JD3RZ01L11ST3016 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z01 - L - 11 | 1 | 2026-03-26 | 2026-03-29 | 2025-10-25 |  | FALSE | yes
| JD3RZ01L11ST3017 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z01 - L - 11 - ST | 1 | 2026-03-30 | 2026-04-02 | 2025-11-01 |  | FALSE | yes
| JD3RZ01L11ST3018 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z01 - L - 11 - ST | 1 | 2026-04-04 | 2026-04-05 |  |  | FALSE | yes
| JD3RZ01L11ST3019 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z01 - L - 11 - ST | 1 | 2026-04-29 | 2026-05-02 |  |  | FALSE | yes
| JD3RZ01L11ST3022 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z01 - L - 11 - ST | 1 | 2026-03-31 | 2026-04-01 |  |  | FALSE | yes
| JD3RZ01L11ST3023 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z01 - L - 11 - ST | 1 | 2026-04-02 | 2026-04-04 |  |  | FALSE | yes
| JD3RZ01L11ST3024 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z01 - L - 11 - ST | 1 | 2026-04-29 | 2026-04-30 |  |  | FALSE | yes
| JD3RZ01L11ST3025 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z01 - L - 11 - ST | 1 | 2026-03-29 | 2026-03-30 |  |  | FALSE | yes
| JD3RZ01L11ST3026 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z01 - L - 11 | 1 | 2026-03-31 | 2026-04-01 |  |  | FALSE | yes
| JD3RZ01L11ST3027 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z01 - L - 11 - ST | 1 | 2026-04-02 | 2026-04-04 |  |  | FALSE | yes
| JD3RZ01L11ST3028 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z01 - L - 11 - ST | 1 | 2026-04-05 | 2026-04-06 |  |  | FALSE | yes
| JD3RZ01L11ST3029 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z01 - L - 11 - ST | 1 | 2026-04-29 | 2026-04-30 |  |  | FALSE | yes
| JD3RZ01L11ST3038 | Primary Test for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - Z01 - L - 11 - ST | 1 | 2026-04-07 | 2026-04-08 |  |  | FALSE | yes
| JD3RZ01L11ST3048 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - Z01 - L - 11 - ST | 1 | 2026-04-09 | 2026-04-11 |  |  | FALSE | yes
| JD3RZ01L11ST3049 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - Z01 - L - 11 - ST | 1 | 2026-04-29 | 2026-04-30 |  |  | FALSE | yes
| JD3RZ01L11ST3057 | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - Z01 - L - 11 - ST | 1 | 2026-04-09 | 2026-04-11 | 2025-09-20 |  | FALSE | yes
| JD3RZ01L11ST3058 | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - Z01 - L - 11 - ST | 1 | 2026-04-12 | 2026-04-13 |  |  | FALSE | yes
| JD3RZ01L11ST3059 | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - Z01 - L - 11 - ST | 1 | 2026-04-29 | 2026-05-02 |  |  | FALSE | yes
| JD3RZ01L11ST3068 | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - Z01 - L - 11 - ST | 1 | 2026-04-14 | 2026-04-15 |  |  | FALSE | yes
| JD3RZ01L11ST3069 | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - Z01 - L - 11 - ST | 1 | 2026-04-29 | 2026-05-02 |  |  | FALSE | yes
| JD3RZ01L11ST3078 | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - Z01 - L - 11 - ST | 1 | 2026-04-21 | 2026-04-22 |  |  | FALSE | yes
| JD3RZ01L11ST3079 | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - Z01 - L - 11 - ST | 1 | 2026-04-29 | 2026-04-30 |  |  | FALSE | yes
| JD3RZ01L11ST3090 | Excavation Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m - B6.33 42 11.15 - Z01 - L - 11 - ST | 1 | 2026-04-13 | 2026-04-14 |  |  | FALSE | yes
| JD3RZ01L11ST3091 | Soil Replacement and Bedding Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m - B6.33 42 11.15 - Z01 - L - 11 | 1 | 2026-04-15 | 2026-04-16 |  |  | FALSE | yes
| JD3RZ01L11ST3092 | Installing for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m - B6.33 42 11.15 - Z01 - L - 11 - ST | 1 | 2026-04-18 | 2026-04-19 |  |  | FALSE | yes
| JD3RZ01L11ST3093 | Primary Test for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m - B6.33 42 11.15 - Z01 - L - 11 - ST | 1 | 2026-04-20 | 2026-04-21 |  |  | FALSE | yes
| JD3RZ01L11ST3094 | Backfilling Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m - B6.33 42 11.15 - Z01 - L - 11 - ST | 1 | 2026-04-29 | 2026-04-30 |  |  | FALSE | yes
| JD3RZ01L11ST3123 | Primary Test for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - Z01 - L - 11 - ST | 1 | 2026-04-22 | 2026-04-23 |  |  | FALSE | yes
| JD3RZ01L11ST3124 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - Z01 - L - 11 - ST | 1 | 2026-04-29 | 2026-04-30 |  |  | FALSE | yes
| JD3RZ01L11ST3198 | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z01 - L - 11 - ST | 1 | 2026-04-18 | 2026-04-19 |  |  | FALSE | yes
| JD3RZ01L11ST3199 | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z01 - L - 11 - ST | 1 | 2026-04-20 | 2026-04-21 |  |  | FALSE | yes
| JD3RZ01L11ST3200 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z01 - L - 11 - ST | 1 | 2026-04-22 | 2026-04-23 |  |  | FALSE | yes
| JD3RZ01L11ST3201 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z01 - L - 11 - S | 1 | 2026-04-25 | 2026-04-26 |  |  | FALSE | yes
| JD3RZ01L11ST3202 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z01 - L - 11 - ST | 1 | 2026-04-27 | 2026-04-28 |  |  | FALSE | yes
| JD3RZ01L11ST3208 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z01 - L - 11 - ST | 1 | 2026-04-20 | 2026-04-21 |  |  | FALSE | yes
| JD3RZ01L11ST3209 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z01 - L - 11 - ST | 1 | 2026-04-22 | 2026-04-23 |  |  | FALSE | yes
| JD3RZ01L11ST3210 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z01 - L - 11 - ST | 1 | 2026-04-25 | 2026-04-26 |  |  | FALSE | yes
| JD3RZ01L11ST3211 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z01 - L - 11 - S | 1 | 2026-04-27 | 2026-04-28 |  |  | FALSE | yes
| JD3RZ01L11ST3212 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z01 - L - 11 - ST | 1 | 2026-04-29 | 2026-04-30 |  |  | FALSE | yes
| JD3RZ01L11ST3213 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z01 - L - 11 - ST | 1 | 2026-04-22 | 2026-04-23 |  |  | FALSE | yes
| JD3RZ01L11ST3214 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z01 - L - 11 - ST | 1 | 2026-04-25 | 2026-04-26 |  |  | FALSE | yes
| JD3RZ01L11ST3215 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z01 - L - 11 - ST | 1 | 2026-04-27 | 2026-04-28 |  |  | FALSE | yes
| JD3RZ01L11ST3216 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z01 - L - 11 - S | 1 | 2026-04-29 | 2026-04-30 |  |  | FALSE | yes
| JD3RZ01L11ST3217 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z01 - L - 11 - ST | 1 | 2026-05-02 | 2026-05-03 |  |  | FALSE | yes
| JD3RZ01L11ST3228 | Excavation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z01 - L - 11 - ST | 1 | 2026-04-25 | 2026-04-26 |  |  | FALSE | yes
| JD3RZ01L11ST3229 | Base Plain Concrete Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z01 - L - 11 - ST | 1 | 2026-04-27 | 2026-04-28 |  |  | FALSE | yes
| JD3RZ01L11ST3230 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z01 - L - 11 - ST | 1 | 2026-04-29 | 2026-04-30 |  |  | FALSE | yes
| JD3RZ01L11ST3231 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z01 - L - 11 - S | 1 | 2026-05-02 | 2026-05-03 |  |  | FALSE | yes
| JD3RZ01L11ST3232 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z01 - L - 11 - ST | 1 | 2026-05-04 | 2026-05-05 |  |  | FALSE | yes
| JD3RZ01L11ST3233 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - Z01 - L - 11 - ST | 1 | 2026-04-27 | 2026-04-28 | 2025-10-26 |  | FALSE | yes
| JD3RZ01L11ST3234 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - Z01 - L - 11 - ST | 1 | 2026-04-29 | 2026-05-02 |  |  | FALSE | yes
| JD3RZ01L11ST3235 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - Z01 - L - 11 - ST | 1 | 2026-05-03 | 2026-05-05 |  |  | FALSE | yes
| JD3RZ01L11ST3236 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - Z01 - L - 11 - ST | 1 | 2026-05-06 | 2026-05-07 |  |  | FALSE | yes
| JD3RZ01L11ST3237 | EXCAVATION Works for Catchbasine double - B6.33 05 39.10 - Z01 - L - 11 - ST | 1 | 2026-04-29 | 2026-04-30 |  |  | FALSE | yes
| JD3RZ01L11ST3238 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - Z01 - L - 11 - ST | 1 | 2026-05-02 | 2026-05-04 |  |  | FALSE | yes
| JD3RZ01L11ST3239 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z01 - L - 11 - ST | 1 | 2026-05-05 | 2026-05-07 |  |  | FALSE | yes
| JD3RZ01L11ST3240 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z01 - L - 11 - ST | 1 | 2026-05-09 | 2026-05-10 |  |  | FALSE | yes
| JD3RZ01L11ST524349 | Concrete encasement for pipes - NNB6.33 42 11.25 - Z01 - L - 11 - ST | 1 | 2026-04-22 | 2026-04-28 |  |  | FALSE | yes
| JD3RZ01L11SUR01 | Surveying Works L - 11 | 1 |  |  |  |  | yes | FALSE
| JD3RZ01L11TSE3291 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z01 - L - 11 - TSE | 1 | 2026-05-09 | 2026-05-10 |  |  | FALSE | yes
| JD3RZ01L11TSE3292 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z01 - L - 11 - T | 1 | 2026-05-11 | 2026-05-12 |  |  | FALSE | yes
| JD3RZ01L11TSE3293 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z01 - L - 11 - TSE | 1 | 2026-05-13 | 2026-05-17 |  |  | FALSE | yes
| JD3RZ01L11TSE3294 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z01 - L - 11 - TSE | 1 | 2026-05-18 | 2026-05-19 |  |  | FALSE | yes
| JD3RZ01L11TSE3295 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z01 - L - 11 - TSE | 1 | 2026-05-30 | 2026-05-31 |  |  | FALSE | yes
| JD3RZ01L11TSE3416 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z01 - L - 11 - TSE | 1 | 2026-05-25 | 2026-05-26 |  |  | FALSE | yes
| JD3RZ01L11TSE3417 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z01 - L - 11 - TSE | 1 | 2026-05-27 | 2026-05-28 |  |  | FALSE | yes
| JD3RZ01L11TSE3434 | Installationfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - Z01 - L - 11 - TSE | 1 | 2026-05-25 | 2026-05-26 |  |  | FALSE | yes
| JD3RZ01L11TSE3435 | Testing And Commtionningfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - Z01 - L - 11 | 1 | 2026-05-27 | 2026-05-28 |  |  | FALSE | yes
| JD3RZ01L11TSE3464 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z01 - L - 11 - TSE | 1 | 2026-05-18 | 2026-05-19 |  |  | FALSE | yes
| JD3RZ01L11TSE3465 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z01 - L - 11 - TSE | 1 | 2026-05-20 | 2026-05-21 |  |  | FALSE | yes
| JD3RZ01L11TSE3466 | INSTALLATIONfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z01 - L - 11 - TSE | 1 | 2026-05-23 | 2026-05-24 |  |  | FALSE | yes
| JD3RZ01L11TSE3467 | Backfilling Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z01 - L - 11 - TSE | 1 | 2026-05-30 | 2026-05-31 |  |  | FALSE | yes
| JD3RZ01L11WT3241 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z01 - L - 11 - WT | 1 | 2026-06-01 | 2026-06-02 |  |  | FALSE | yes
| JD3RZ01L11WT3242 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z01 - L - 11 - WT | 1 | 2026-06-03 | 2026-06-04 |  |  | FALSE | yes
| JD3RZ01L11WT3243 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z01 - L - 11 - WT | 1 | 2026-06-06 | 2026-06-07 |  |  | FALSE | yes
| JD3RZ01L11WT3244 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z01 - L - 11 - WT | 1 | 2026-06-08 | 2026-06-09 |  |  | FALSE | yes
| JD3RZ01L11WT3245 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z01 - L - 11 - WT | 1 | 2026-06-10 | 2026-06-11 |  |  | FALSE | yes
| JD3RZ01L11WT3276 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z01 - L - 11 - WT | 1 | 2026-06-03 | 2026-06-04 |  |  | FALSE | yes
| JD3RZ01L11WT3277 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z01 - L - 11 - WT | 1 | 2026-06-06 | 2026-06-07 |  |  | FALSE | yes
| JD3RZ01L11WT3278 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z01 - L - 11 - WT | 1 | 2026-06-08 | 2026-06-09 |  |  | FALSE | yes
| JD3RZ02-1L69SL7079 | Excavation Worksfor Copper Cables 4Cx25 mm² - B2.26 05 19.04 - Z02 - 1 - L - 69 - SL | 1 | 2025-01-13 | 2025-01-15 |  |  | FALSE | yes
| JD3RZ02-1L69SL7080 | Installationfor Copper Cables 4Cx25 mm² - B2.26 05 19.04 - Z02 - 1 - L - 69 - SL | 1 | 2025-03-26 | 2025-03-29 |  |  | FALSE | yes
| JD3RZ02-1L69SL7081 | Backfilling, Warning Tabe Worksfor Copper Cables 4Cx25 mm² - B2.26 05 19.04 - Z02 - 1 - L - 69 - SL | 1 | 2025-03-30 | 2025-04-01 |  |  | FALSE | yes
| JD3RZ02-1L69SL7082 | Testing and Commitioning for Copper Cables 4Cx25 mm² - B2.26 05 19.04 - Z02 - 1 - L - 69 - SL | 1 | 2025-04-02 | 2025-04-05 |  |  | FALSE | yes
| JD3RZ02-1L69SL7093 | INSTALLINGfor insulated copper conductor 16 mm² - B2.26 05 19.08 - Z02 - 1 - L - 69 - SL | 1 | 2025-03-30 | 2025-04-01 |  |  | FALSE | yes
| JD3RZ02-1L69SL7094 | TESTING AND COMMITIONINGfor insulated copper conductor 16 mm² - B2.26 05 19.08 - Z02 - 1 - L - 69 - SL | 1 | 2025-04-02 | 2025-04-05 |  |  | FALSE | yes
| JD3RZ02-1L69SL7100 | Excavation of reinforced concrete foundationfor LIGHTING POLE one arm - B2.26 56 19.02 - Z02 - 1 - L - 69 - SL | 1 | 2025-01-18 | 2025-01-19 |  |  | FALSE | yes
| JD3RZ02-1L69SL7101 | Installation of reinforced concrete foundationfor LIGHTING POLE one arm - B2.26 56 19.02 - Z02 - 1 - L - 69 - SL | 1 | 2025-01-20 | 2025-01-21 |  |  | FALSE | yes
| JD3RZ02-1L69SL7102 | Backfilling of reinforced concrete foundationfor LIGHTING POLE one arm - B2.26 56 19.02 - Z02 - 1 - L - 69 - SL | 1 | 2025-01-22 | 2025-01-23 |  |  | FALSE | yes
| JD3RZ02-1L69SL7103 | Installation Worksfor LIGHTING POLE one arm - B2.26 56 19.02 - Z02 - 1 - L - 69 - SL | 1 | 2025-01-25 | 2025-01-27 |  |  | FALSE | yes
| JD3RZ02-1L69SL7104 | Testing and Commitioningfor LIGHTING POLE one arm - B2.26 56 19.02 - Z02 - 1 - L - 69 - SL | 1 | 2025-04-06 | 2025-04-08 |  |  | FALSE | yes
| JD3RZ02-1L69SL7105 | Installationfor Lighting( LED ) Luminaire 150 WATT - B2.26.56.19.01 - Z02 - 1 - L - 69 - SL | 1 | 2025-01-25 | 2025-01-26 |  |  | FALSE | yes
| JD3RZ02-1L69SL7108 | Supply, construct, connect and test earthing pitsfor Street Lighting EARTHING SYSTEM - B2.26 05 26.01 - Z02 - 1 - L - 69 | 1 | 2025-01-22 | 2025-01-23 |  |  | FALSE | yes
| JD3RZ02-1L69SL7121 | Excavationfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - Z02 - 1 - L - 69 - SL | 1 | 2025-01-20 | 2025-01-21 |  |  | FALSE | yes
| JD3RZ02-1L69SL7122 | Installationfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - Z02 - 1 - L - 69 - SL | 1 | 2025-01-22 | 2025-01-23 |  |  | FALSE | yes
| JD3RZ02-1L69SL7123 | Backfillingfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - Z02 - 1 - L - 69 - SL | 1 | 2025-01-25 | 2025-01-26 |  |  | FALSE | yes
| JD3RZ02-1L69SS6512 | Finishing, Benching Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z02 - 1 - L - 69 - SS | 1 | 2024-10-08 | 2024-10-09 |  |  | FALSE | yes
| JD3RZ02-1L69ST6580 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-08 | 2024-10-09 |  |  | FALSE | yes
| JD3RZ02-1L69ST6581 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z02 - 1 - L | 1 | 2024-10-10 | 2024-10-12 |  |  | FALSE | yes
| JD3RZ02-1L69ST6582 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-13 | 2024-10-15 |  |  | FALSE | yes
| JD3RZ02-1L69ST6583 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-16 | 2024-10-19 |  |  | FALSE | yes
| JD3RZ02-1L69ST6584 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-20 | 2024-10-22 |  |  | FALSE | yes
| JD3RZ02-1L69ST6585.R | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 1 - L - 69 - ST - Remaini | 1 | 2024-10-10 | 2024-10-12 |  |  | FALSE | yes
| JD3RZ02-1L69ST6586.R | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 1 - L - | 1 | 2024-10-13 | 2024-10-14 |  |  | FALSE | yes
| JD3RZ02-1L69ST6587.R | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 1 - L - 69 - ST - Remaining | 1 | 2024-10-15 | 2024-10-16 |  |  | FALSE | yes
| JD3RZ02-1L69ST6588 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-17 | 2024-10-19 | 2025-09-06 |  | FALSE | FALSE
| JD3RZ02-1L69ST6589 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-20 | 2024-10-22 |  |  | FALSE | yes
| JD3RZ02-1L69ST6590 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-10 | 2024-10-12 |  |  | FALSE | yes
| JD3RZ02-1L69ST6591 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z02 - 1 - L - | 1 | 2024-10-13 | 2024-10-14 |  |  | FALSE | yes
| JD3RZ02-1L69ST6592 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-15 | 2024-10-16 |  |  | FALSE | yes
| JD3RZ02-1L69ST6593 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-17 | 2024-10-19 |  |  | FALSE | yes
| JD3RZ02-1L69ST6594 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-20 | 2024-10-21 |  |  | FALSE | yes
| JD3RZ02-1L69ST6615 | Excavation Works for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m - B6.33 42 11.07 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-15 | 2024-10-16 | 2025-08-20 |  | FALSE | FALSE
| JD3RZ02-1L69ST6616 | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m - B6.33 42 11.07 - Z02 - 1 - L - | 1 | 2024-10-17 | 2024-10-19 | 2025-08-26 |  | FALSE | FALSE
| JD3RZ02-1L69ST6617 | Installing for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m - B6.33 42 11.07 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-20 | 2024-10-21 | 2025-08-28 |  | FALSE | FALSE
| JD3RZ02-1L69ST6618 | Primary Test for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m - B6.33 42 11.07 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-22 | 2024-10-23 | 2025-09-17 |  | FALSE | FALSE
| JD3RZ02-1L69ST6619 | Backfilling Works for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m - B6.33 42 11.07 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-24 | 2024-10-26 | 2025-09-20 |  | FALSE | FALSE
| JD3RZ02-1L69ST6765 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-22 | 2024-10-23 | 2025-09-17 |  | FALSE | FALSE
| JD3RZ02-1L69ST6766 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z02 - 1 - L - 69 | 1 | 2024-10-24 | 2024-10-26 |  |  | FALSE | yes
| JD3RZ02-1L69ST6767 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-27 | 2024-10-28 |  |  | FALSE | yes
| JD3RZ02-1L69ST6775.R | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z02 - 1 - L - 69 - ST - Rem | 1 | 2024-10-24 | 2024-10-26 | 2025-09-11 |  | FALSE | FALSE
| JD3RZ02-1L69ST6776 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z02 - 1 - L - 69 | 1 | 2024-10-27 | 2024-10-28 |  |  | FALSE | yes
| JD3RZ02-1L69ST6777 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-29 | 2024-10-30 |  |  | FALSE | yes
| JD3RZ02-1L69ST6778 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-20 | 2024-10-21 | 2025-09-16 |  | FALSE | FALSE
| JD3RZ02-1L69ST6779 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-22 | 2024-10-23 | 2025-09-18 |  | FALSE | FALSE
| JD3RZ02-1L69ST6780 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-24 | 2024-10-26 |  |  | FALSE | yes
| JD3RZ02-1L69ST6781 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z02 - 1 - L - 69 | 1 | 2024-10-27 | 2024-10-28 |  |  | FALSE | yes
| JD3RZ02-1L69ST6782 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-29 | 2024-10-30 |  |  | FALSE | yes
| JD3RZ02-1L69ST6790.R | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z02 - 1 - L - 69 - ST - Rem | 1 | 2024-10-29 | 2024-10-30 |  |  | FALSE | yes
| JD3RZ02-1L69ST6791 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z02 - 1 - L - 69 | 1 | 2024-10-31 | 2024-11-02 |  |  | FALSE | yes
| JD3RZ02-1L69ST6792 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z02 - 1 - L - 69 - ST | 1 | 2024-11-03 | 2024-11-04 |  |  | FALSE | yes
| JD3RZ02-1L69ST6798 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-22 | 2024-10-23 |  |  | FALSE | yes
| JD3RZ02-1L69ST6799 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-24 | 2024-10-27 |  |  | FALSE | yes
| JD3RZ02-1L69ST6800 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-28 | 2024-10-30 |  |  | FALSE | yes
| JD3RZ02-1L69ST6801 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-31 | 2024-11-02 |  |  | FALSE | yes
| JD3RZ02-1L69ST6802 | EXCAVATION Works for Catchbasine double - B6.33 05 39.10 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-24 | 2024-10-26 |  |  | FALSE | yes
| JD3RZ02-1L69ST6803 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-27 | 2024-10-29 |  |  | FALSE | yes
| JD3RZ02-1L69ST6804 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z02 - 1 - L - 69 - ST | 1 | 2024-10-30 | 2024-11-02 |  |  | FALSE | yes
| JD3RZ02-1L69ST6805 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z02 - 1 - L - 69 - ST | 1 | 2024-11-03 | 2024-11-04 |  |  | FALSE | yes
| JD3RZ02-1L69TC7136 | Excavation Worksfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z02 - 1 - L - 69 - TC | 1 | 2025-01-16 | 2025-01-18 |  |  | FALSE | yes
| JD3RZ02-1L69TC7137 | Installationfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z02 - 1 - L - 69 - TC | 1 | 2025-01-19 | 2025-01-22 |  |  | FALSE | yes
| JD3RZ02-1L69TC7138 | Pouring Concrete Coverfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z02 - 1 - L - 69 - | 1 | 2025-01-23 | 2025-01-27 |  |  | FALSE | yes
| JD3RZ02-1L69TC7139 | Backfilling Worksfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z02 - 1 - L - 69 - TC | 1 | 2025-04-09 | 2025-04-10 |  |  | FALSE | yes
| JD3RZ02-1L69TC7140 | Excavation and Bedding Worksfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z02 - 1 - L - 69 - TC | 1 | 2025-01-19 | 2025-01-20 |  |  | FALSE | yes
| JD3RZ02-1L69TC7141 | Installationfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z02 - 1 - L - 69 - TC | 1 | 2025-01-21 | 2025-01-22 |  |  | FALSE | yes
| JD3RZ02-1L69TC7142 | Backfilling Worksfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z02 - 1 - L - 69 - TC | 1 | 2025-01-23 | 2025-01-25 |  |  | FALSE | yes
| JD3RZ02-1L69TSE6856 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 1 - L - 69 - TSE | 1 | 2024-11-05 | 2024-11-06 |  |  | FALSE | yes
| JD3RZ02-1L69TSE6857 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 1 - L - 69 | 1 | 2024-11-07 | 2024-11-09 |  |  | FALSE | yes
| JD3RZ02-1L69TSE6858 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 1 - L - 69 - TSE | 1 | 2024-12-07 | 2024-12-08 |  |  | FALSE | yes
| JD3RZ02-1L69TSE6859 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 1 - L - 69 - TSE | 1 | 2024-12-09 | 2024-12-10 |  |  | FALSE | yes
| JD3RZ02-1L69TSE6860 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 1 - L - 69 - TSE | 1 | 2024-12-23 | 2024-12-24 |  |  | FALSE | yes
| JD3RZ02-1L69TSE6863 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - 1 - L - 69 - TSE | 1 | 2024-12-07 | 2024-12-15 | 2025-09-03 |  | FALSE | FALSE
| JD3RZ02-1L69TSE6864 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - 1 - L - 69 - TSE | 1 | 2024-12-16 | 2024-12-21 | 2025-09-06 |  | FALSE | FALSE
| JD3RZ02-1L69TSE6865 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - 1 - L - 69 - TSE | 1 | 2024-12-25 | 2024-12-30 | 2025-09-09 |  | FALSE | FALSE
| JD3RZ02-1L69TSE6981 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z02 - 1 - L - 69 - TSE | 1 | 2024-12-16 | 2024-12-18 |  |  | FALSE | yes
| JD3RZ02-1L69TSE6982 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z02 - 1 - L - 69 - TSE | 1 | 2024-12-19 | 2024-12-22 |  |  | FALSE | yes
| JD3RZ02-1L69TSE6983 | Installationfor gate valves 250 mm - B4.33 14 19.02 - Z02 - 1 - L - 69 - TSE | 1 | 2024-12-16 | 2024-12-17 |  |  | FALSE | yes
| JD3RZ02-1L69TSE6984 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - Z02 - 1 - L - 69 - TSE | 1 | 2024-12-18 | 2024-12-19 |  |  | FALSE | yes
| JD3RZ02-1L69WT6809 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z02 - 1 - L - 69 - WT | 1 | 2024-12-04 | 2024-12-10 | 2025-10-23 |  | FALSE | FALSE
| JD3RZ02-1L69WT6831 | INSTALLATIONfor gate valves 150 mm - B3.33 14 19.01 - Z02 - 1 - L - 69 - WT | 1 | 2025-01-04 | 2025-01-06 |  |  | FALSE | yes
| JD3RZ02-1L69WT6832 | TESTING AND COMMITIONfor gate valves 150 mm - B3.33 14 19.01 - Z02 - 1 - L - 69 - WT | 1 | 2025-01-07 | 2025-01-09 |  |  | FALSE | yes
| JD3RZ02-1L69WT6837 | INSTALLATIONfor Wash - Out Valve 100 mm - B3.33 14 19.05 - Z02 - 1 - L - 69 - WT | 1 | 2025-01-04 | 2025-01-05 |  |  | FALSE | yes
| JD3RZ02-1L69WT6838 | TESTING AND COMMITIONfor Wash - Out Valve 100 mm - B3.33 14 19.05 - Z02 - 1 - L - 69 - WT | 1 | 2025-01-06 | 2025-01-07 |  |  | FALSE | yes
| JD3RZ02-1L69WT6841 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z02 - 1 - L - 69 - WT | 1 | 2024-12-25 | 2024-12-26 |  |  | FALSE | yes
| JD3RZ02-1L69WT6842 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z02 - 1 - L - 69 - WT | 1 | 2024-12-28 | 2024-12-29 |  |  | FALSE | yes
| JD3RZ02-1L69WT6843 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z02 - 1 - L - 69 - WT | 1 | 2024-12-30 | 2024-12-31 |  |  | FALSE | yes
| JD3RZ02-1L69WT6848 | EXCAVATION and Bedding Worksfor Wash - out Valve Chamber - 110 to 400 MM - B3.33 14 13.06 - Z02 - 1 - L - 69 - WT | 1 | 2024-12-28 | 2024-12-29 |  |  | FALSE | yes
| JD3RZ02-1L69WT6849 | Plain Concrete Worksfor Wash - out Valve Chamber - 110 to 400 MM - B3.33 14 13.06 - Z02 - 1 - L - 69 - WT | 1 | 2024-12-30 | 2024-12-31 |  |  | FALSE | yes
| JD3RZ02-1L69WT6850 | INSTALLATIONfor Wash - out Valve Chamber - 110 to 400 MM - B3.33 14 13.06 - Z02 - 1 - L - 69 - WT | 1 | 2025-01-01 | 2025-01-02 |  |  | FALSE | yes
| JD3RZ02-1L69WT6851 | Backfilling Worksfor Wash - out Valve Chamber - 110 to 400 MM - B3.33 14 13.06 - Z02 - 1 - L - 69 - WT | 1 | 2025-01-11 | 2025-01-12 |  |  | FALSE | yes
| JD3RZ02-1L70TSE7569 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 1 - L - 70 - TSE | 1 | 2024-12-07 | 2024-12-10 | 2025-08-23 |  | FALSE | FALSE
| JD3RZ02-1L70TSE7570 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 1 - L - 70 | 1 | 2024-12-11 | 2024-12-15 | 2025-09-03 |  | FALSE | FALSE
| JD3RZ02-1L70TSE7571 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 1 - L - 70 - TSE | 1 | 2024-12-16 | 2024-12-23 | 2025-09-06 |  | FALSE | FALSE
| JD3RZ02-1L70TSE7572 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 1 - L - 70 - TSE | 1 | 2024-12-24 | 2024-12-29 | 2025-09-09 |  | FALSE | FALSE
| JD3RZ02-1L70TSE7573 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 1 - L - 70 - TSE | 1 | 2024-12-30 | 2025-01-04 | 2025-09-14 |  | FALSE | FALSE
| JD3RZ02-1L70TSE7574 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - 1 - L - 70 - TSE | 1 | 2024-12-11 | 2024-12-12 |  |  | FALSE | yes
| JD3RZ02-1L70TSE7575 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - 1 - L - 70 | 1 | 2024-12-14 | 2024-12-15 |  |  | FALSE | yes
| JD3RZ02-1L70TSE7576 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - 1 - L - 70 - TSE | 1 | 2024-12-16 | 2024-12-17 |  |  | FALSE | yes
| JD3RZ02-1L70TSE7577 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - 1 - L - 70 - TSE | 1 | 2024-12-18 | 2024-12-19 |  |  | FALSE | yes
| JD3RZ02-1L70TSE7578 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - 1 - L - 70 - TSE | 1 | 2024-12-29 | 2024-12-30 |  |  | FALSE | yes
| JD3RZ02-1L70TSE7694 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z02 - 1 - L - 70 - TSE | 1 | 2024-12-24 | 2024-12-25 |  |  | FALSE | yes
| JD3RZ02-1L70TSE7695 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z02 - 1 - L - 70 - TSE | 1 | 2024-12-26 | 2024-12-28 |  |  | FALSE | yes
| JD3RZ02-1L71SL8505 | Excavation Worksfor Copper Cables 4Cx25 mm² - B2.26 05 19.04 - Z02 - 1 - L - 71 - SL | 1 | 2025-04-20 | 2025-04-22 |  |  | FALSE | yes
| JD3RZ02-1L71SL8506 | Installationfor Copper Cables 4Cx25 mm² - B2.26 05 19.04 - Z02 - 1 - L - 71 - SL | 1 | 2025-04-23 | 2025-04-26 |  |  | FALSE | yes
| JD3RZ02-1L71SL8507 | Backfilling, Warning Tabe Worksfor Copper Cables 4Cx25 mm² - B2.26 05 19.04 - Z02 - 1 - L - 71 - SL | 1 | 2025-04-27 | 2025-04-29 |  |  | FALSE | yes
| JD3RZ02-1L71SL8508 | Testing and Commitioning for Copper Cables 4Cx25 mm² - B2.26 05 19.04 - Z02 - 1 - L - 71 - SL | 1 | 2025-05-05 | 2025-05-07 |  |  | FALSE | yes
| JD3RZ02-1L71SL8519 | INSTALLINGfor insulated copper conductor 16 mm² - B2.26 05 19.08 - Z02 - 1 - L - 71 - SL | 1 | 2025-04-28 | 2025-04-30 |  |  | FALSE | yes
| JD3RZ02-1L71SL8520 | TESTING AND COMMITIONINGfor insulated copper conductor 16 mm² - B2.26 05 19.08 - Z02 - 1 - L - 71 - SL | 1 | 2025-05-01 | 2025-05-04 |  |  | FALSE | yes
| JD3RZ02-1L71SL8526 | Excavation of reinforced concrete foundationfor LIGHTING POLE one arm - B2.26 56 19.02 - Z02 - 1 - L - 71 - SL | 1 | 2025-04-23 | 2025-04-24 |  |  | FALSE | yes
| JD3RZ02-1L71SL8527 | Installation of reinforced concrete foundationfor LIGHTING POLE one arm - B2.26 56 19.02 - Z02 - 1 - L - 71 - SL | 1 | 2025-04-26 | 2025-04-27 |  |  | FALSE | yes
| JD3RZ02-1L71SL8528 | Backfilling of reinforced concrete foundationfor LIGHTING POLE one arm - B2.26 56 19.02 - Z02 - 1 - L - 71 - SL | 1 | 2025-04-28 | 2025-04-29 |  |  | FALSE | yes
| JD3RZ02-1L71SL8529 | Installation Worksfor LIGHTING POLE one arm - B2.26 56 19.02 - Z02 - 1 - L - 71 - SL | 1 | 2025-04-30 | 2025-05-04 |  |  | FALSE | yes
| JD3RZ02-1L71SL8530 | Testing and Commitioningfor LIGHTING POLE one arm - B2.26 56 19.02 - Z02 - 1 - L - 71 - SL | 1 | 2025-05-07 | 2025-05-11 |  |  | FALSE | yes
| JD3RZ02-1L71SL8531 | Installationfor Lighting( LED ) Luminaire 150 WATT - B2.26.56.19.01 - Z02 - 1 - L - 71 - SL | 1 | 2025-05-05 | 2025-05-06 |  |  | FALSE | yes
| JD3RZ02-1L71SL8535 | Excavation Worksfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - Z02 - 1 - L - 71 - SL | 1 | 2025-04-26 | 2025-04-27 |  |  | FALSE | yes
| JD3RZ02-1L71SL8536 | Installationfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - Z02 - 1 - L - 71 - SL | 1 | 2025-04-28 | 2025-04-29 |  |  | FALSE | yes
| JD3RZ02-1L71SL8537 | Pouring Concrete Coverfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - Z02 - 1 - L - 71 - SL | 1 | 2025-04-30 | 2025-05-01 |  |  | FALSE | yes
| JD3RZ02-1L71SL8538 | Testing and Backfilling Worksfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - Z02 - 1 - L - 71 - SL | 1 | 2025-05-05 | 2025-05-06 |  |  | FALSE | yes
| JD3RZ02-1L71SL8547 | Excavationfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - Z02 - 1 - L - 71 - SL | 1 | 2025-04-28 | 2025-04-29 |  |  | FALSE | yes
| JD3RZ02-1L71SL8548 | Installationfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - Z02 - 1 - L - 71 - SL | 1 | 2025-04-30 | 2025-05-01 |  |  | FALSE | yes
| JD3RZ02-1L71SL8549 | Backfillingfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - Z02 - 1 - L - 71 - SL | 1 | 2025-05-05 | 2025-05-06 |  |  | FALSE | yes
| JD3RZ02-1L71SL8550 | Excavationfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - Z02 - 1 - L - 71 - SL | 1 | 2025-04-30 | 2025-05-01 |  |  | FALSE | yes
| JD3RZ02-1L71SL8551 | Installationfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - Z02 - 1 - L - 71 - SL | 1 | 2025-05-03 | 2025-05-04 |  |  | FALSE | yes
| JD3RZ02-1L71SL8552 | Backfillingfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - Z02 - 1 - L - 71 - SL | 1 | 2025-05-05 | 2025-05-06 |  |  | FALSE | yes
| JD3RZ02-1L71SS521401 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 3.51 to 4.50 - B5.33 05 13.05 - MR - C - 03 - SS | 1 | 2025-01-08 | 2025-01-09 | 2025-08-02 |  | FALSE | FALSE
| JD3RZ02-1L71SS521411 | Installation of Base Works for Manholes 1200 mm - Depth from 3.51 to 4.50 - B5.33 05 13.05 - MR - C - 03 - SS | 1 | 2025-01-11 | 2025-01-12 | 2025-08-04 |  | FALSE | FALSE
| JD3RZ02-1L71SS521421 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 3.51 to 4.50 - B5.33 05 13.05 - MR - | 1 | 2025-01-13 | 2025-01-14 | 2025-10-19 |  | FALSE | FALSE
| JD3RZ02-1L71SS521431 | Backfilling Works for Manholes 1200 mm - Depth from 3.51 to 4.50 - B5.33 05 13.05 - MR - C - 03 - SS | 1 | 2025-01-15 | 2025-01-16 |  |  | FALSE | yes
| JD3RZ02-1L71SS521441 | Finishing, Benching Works for Manholes 1200 mm - Depth from 3.51 to 4.50 - B5.33 05 13.05 - MR - C - 03 - SS | 1 | 2025-01-18 | 2025-01-19 |  |  | FALSE | yes
| JD3RZ02-1L71SS7925 | Backfilling Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z02 - 1 - L - 71 - SS | 1 | 2025-01-11 | 2025-01-12 |  |  | FALSE | yes
| JD3RZ02-1L71SS7926 | Finishing, Benching Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z02 - 1 - L - 71 - SS | 1 | 2025-01-13 | 2025-01-14 |  |  | FALSE | yes
| JD3RZ02-1L71SS7937 | Backfilling Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z02 - 1 - L - 71 - SS | 1 | 2025-01-15 | 2025-01-16 |  |  | FALSE | yes
| JD3RZ02-1L71SS7938 | Finishing, Benching Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z02 - 1 - L - 71 - SS | 1 | 2025-01-18 | 2025-01-19 |  |  | FALSE | yes
| JD3RZ02-1L71ST8006 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z02 - 1 - L - 71 - ST | 1 | 2025-01-21 | 2025-01-23 |  |  | FALSE | yes
| JD3RZ02-1L71ST8007 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z02 - 1 - L | 1 | 2025-01-25 | 2025-01-27 |  |  | FALSE | yes
| JD3RZ02-1L71ST8008 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z02 - 1 - L - 71 - ST | 1 | 2025-01-28 | 2025-02-01 |  |  | FALSE | yes
| JD3RZ02-1L71ST8009 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z02 - 1 - L - 71 - ST | 1 | 2025-02-02 | 2025-02-05 |  |  | FALSE | yes
| JD3RZ02-1L71ST8010 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z02 - 1 - L - 71 - ST | 1 | 2025-02-06 | 2025-02-11 |  |  | FALSE | yes
| JD3RZ02-1L71ST8011 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 1 - L - 71 - ST | 1 | 2025-01-25 | 2025-01-26 |  |  | FALSE | yes
| JD3RZ02-1L71ST8012 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 1 - L - | 1 | 2025-01-27 | 2025-01-28 |  |  | FALSE | yes
| JD3RZ02-1L71ST8013 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 1 - L - 71 - ST | 1 | 2025-01-29 | 2025-01-30 |  |  | FALSE | yes
| JD3RZ02-1L71ST8014 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 1 - L - 71 - ST | 1 | 2025-02-01 | 2025-02-02 |  |  | FALSE | yes
| JD3RZ02-1L71ST8015 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 1 - L - 71 - ST | 1 | 2025-02-03 | 2025-02-04 |  |  | FALSE | yes
| JD3RZ02-1L71ST8016.R | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z02 - 1 - L - 71 - ST - Remaini | 1 | 2025-01-27 | 2025-01-28 | 2025-10-22 |  | FALSE | FALSE
| JD3RZ02-1L71ST8017.R | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z02 - 1 - L - | 1 | 2025-01-29 | 2025-01-30 | 2025-10-22 |  | FALSE | FALSE
| JD3RZ02-1L71ST8018.R | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z02 - 1 - L - 71 - ST - Remaining | 1 | 2025-02-01 | 2025-02-02 | 2025-10-22 |  | FALSE | FALSE
| JD3RZ02-1L71ST8019 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z02 - 1 - L - 71 - ST | 1 | 2025-02-03 | 2025-02-04 | 2025-08-25 |  | FALSE | FALSE
| JD3RZ02-1L71ST8020 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z02 - 1 - L - 71 - ST | 1 | 2025-02-05 | 2025-02-06 | 2025-08-30 |  | FALSE | FALSE
| JD3RZ02-1L71ST8192 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z02 - 1 - L - 71 | 1 | 2025-02-16 | 2025-02-17 |  |  | FALSE | yes
| JD3RZ02-1L71ST8193 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z02 - 1 - L - 71 - ST | 1 | 2025-02-18 | 2025-02-19 |  |  | FALSE | yes
| JD3RZ02-1L71ST8202 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z02 - 1 - L - 71 | 1 | 2025-02-18 | 2025-02-19 |  |  | FALSE | yes
| JD3RZ02-1L71ST8203 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z02 - 1 - L - 71 - ST | 1 | 2025-02-20 | 2025-02-22 |  |  | FALSE | yes
| JD3RZ02-1L71ST8207 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z02 - 1 - L - 71 | 1 | 2025-02-18 | 2025-02-19 |  |  | FALSE | yes
| JD3RZ02-1L71ST8208 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z02 - 1 - L - 71 - ST | 1 | 2025-02-20 | 2025-02-22 |  |  | FALSE | yes
| JD3RZ02-1L71ST8221.R | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z02 - 1 - L - 71 - ST - Rem | 1 | 2025-02-20 | 2025-02-22 | 2025-08-20 |  | FALSE | FALSE
| JD3RZ02-1L71ST8222 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z02 - 1 - L - 71 | 1 | 2025-02-23 | 2025-02-24 |  |  | FALSE | yes
| JD3RZ02-1L71ST8223 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z02 - 1 - L - 71 - ST | 1 | 2025-02-25 | 2025-02-26 |  |  | FALSE | yes
| JD3RZ02-1L71ST8224 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - Z02 - 1 - L - 71 - ST | 1 | 2025-02-13 | 2025-02-15 |  |  | FALSE | yes
| JD3RZ02-1L71ST8225 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - Z02 - 1 - L - 71 - ST | 1 | 2025-02-16 | 2025-02-18 |  |  | FALSE | yes
| JD3RZ02-1L71ST8226 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - Z02 - 1 - L - 71 - ST | 1 | 2025-02-19 | 2025-02-22 |  |  | FALSE | yes
| JD3RZ02-1L71ST8227 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - Z02 - 1 - L - 71 - ST | 1 | 2025-02-23 | 2025-02-24 |  |  | FALSE | yes
| JD3RZ02-1L71ST8228 | EXCAVATION Works for Catchbasine double - B6.33 05 39.10 - Z02 - 1 - L - 71 - ST | 1 | 2025-02-16 | 2025-02-17 |  |  | FALSE | yes
| JD3RZ02-1L71ST8229 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - Z02 - 1 - L - 71 - ST | 1 | 2025-02-18 | 2025-02-20 |  |  | FALSE | yes
| JD3RZ02-1L71ST8230 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z02 - 1 - L - 71 - ST | 1 | 2025-02-22 | 2025-02-24 |  |  | FALSE | yes
| JD3RZ02-1L71ST8231 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z02 - 1 - L - 71 - ST | 1 | 2025-02-27 | 2025-03-01 |  |  | FALSE | yes
| JD3RZ02-1L71TC8562 | Excavation Worksfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z02 - 1 - L - 71 - TC | 1 | 2025-04-20 | 2025-04-21 |  |  | FALSE | yes
| JD3RZ02-1L71TC8563 | Installationfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z02 - 1 - L - 71 - TC | 1 | 2025-04-22 | 2025-04-26 |  |  | FALSE | yes
| JD3RZ02-1L71TC8564 | Pouring Concrete Coverfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z02 - 1 - L - 71 - | 1 | 2025-04-27 | 2025-04-30 |  |  | FALSE | yes
| JD3RZ02-1L71TC8565 | Backfilling Worksfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z02 - 1 - L - 71 - TC | 1 | 2025-05-01 | 2025-05-03 |  |  | FALSE | yes
| JD3RZ02-1L71TC8566 | Excavation and Bedding Worksfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z02 - 1 - L - 71 - TC | 1 | 2025-04-22 | 2025-04-23 |  |  | FALSE | yes
| JD3RZ02-1L71TC8567 | Installationfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z02 - 1 - L - 71 - TC | 1 | 2025-04-24 | 2025-04-26 |  |  | FALSE | yes
| JD3RZ02-1L71TC8568 | Backfilling Worksfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z02 - 1 - L - 71 - TC | 1 | 2025-04-27 | 2025-04-28 |  |  | FALSE | yes
| JD3RZ02-1L71TSE8282 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 1 - L - 71 - TSE | 1 | 2025-03-02 | 2025-03-05 | 2025-08-09 |  | FALSE | FALSE
| JD3RZ02-1L71TSE8283 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 1 - L - 71 | 1 | 2025-03-06 | 2025-03-10 | 2025-08-14 |  | FALSE | FALSE
| JD3RZ02-1L71TSE8284 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 1 - L - 71 - TSE | 1 | 2025-03-11 | 2025-03-18 | 2025-08-18 |  | FALSE | FALSE
| JD3RZ02-1L71TSE8285 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 1 - L - 71 - TSE | 1 | 2025-03-19 | 2025-03-24 | 2025-08-31 |  | FALSE | FALSE
| JD3RZ02-1L71TSE8286 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 1 - L - 71 - TSE | 1 | 2025-03-25 | 2025-03-30 | 2025-08-25 |  | FALSE | FALSE
| JD3RZ02-1L71TSE8407 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z02 - 1 - L - 71 - TSE | 1 | 2025-03-19 | 2025-03-20 |  |  | FALSE | yes
| JD3RZ02-1L71TSE8408 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z02 - 1 - L - 71 - TSE | 1 | 2025-03-22 | 2025-03-23 |  |  | FALSE | yes
| JD3RZ02-1L71WT8237 | Excavation Worksfor HDPE Pipes 225 mm - depth from 0 to 1.5 m - B3.33 14 13.02 - Z02 - 1 - L - 71 - WT | 1 | 2025-03-31 | 2025-04-01 |  |  | FALSE | yes
| JD3RZ02-1L71WT8238 | Soil Replacement and Bedding Works for HDPE Pipes 225 mm - depth from 0 to 1.5 m - B3.33 14 13.02 - Z02 - 1 - L - 71 - W | 1 | 2025-04-02 | 2025-04-03 |  |  | FALSE | yes
| JD3RZ02-1L71WT8239 | Installing for HDPE Pipes 225 mm - depth from 0 to 1.5 m - B3.33 14 13.02 - Z02 - 1 - L - 71 - WT | 1 | 2025-04-05 | 2025-04-06 |  |  | FALSE | yes
| JD3RZ02-1L71WT8240 | Testing for HDPE Pipes 225 mm - depth from 0 to 1.5 m - B3.33 14 13.02 - Z02 - 1 - L - 71 - WT | 1 | 2025-04-07 | 2025-04-08 |  |  | FALSE | yes
| JD3RZ02-1L71WT8241 | Backfillingfor HDPE Pipes 225 mm - depth from 0 to 1.5 m - B3.33 14 13.02 - Z02 - 1 - L - 71 - WT | 1 | 2025-04-14 | 2025-04-15 |  |  | FALSE | yes
| JD3RZ02-1L71WT8257 | INSTALLATIONfor gate valves 150 mm - B3.33 14 19.01 - Z02 - 1 - L - 71 - WT | 1 | 2025-04-07 | 2025-04-08 |  |  | FALSE | yes
| JD3RZ02-1L71WT8258 | TESTING AND COMMITIONfor gate valves 150 mm - B3.33 14 19.01 - Z02 - 1 - L - 71 - WT | 1 | 2025-04-09 | 2025-04-10 |  |  | FALSE | yes
| JD3RZ02-1L71WT8267 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z02 - 1 - L - 71 - WT | 1 | 2025-04-02 | 2025-04-03 |  |  | FALSE | yes
| JD3RZ02-1L71WT8268 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z02 - 1 - L - 71 - WT | 1 | 2025-04-05 | 2025-04-06 |  |  | FALSE | yes
| JD3RZ02-1L71WT8269 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z02 - 1 - L - 71 - WT | 1 | 2025-04-12 | 2025-04-13 |  |  | FALSE | yes
| JD3RZ02-1L72SL9218 | Excavation Worksfor Copper Cables 4Cx25 mm² - B2.26 05 19.04 - Z02 - 1 - L - 72 - SL | 1 | 2025-03-26 | 2025-03-29 |  |  | FALSE | yes
| JD3RZ02-1L72SL9219 | Installationfor Copper Cables 4Cx25 mm² - B2.26 05 19.04 - Z02 - 1 - L - 72 - SL | 1 | 2025-03-30 | 2025-04-01 |  |  | FALSE | yes
| JD3RZ02-1L72SL9220 | Backfilling, Warning Tabe Worksfor Copper Cables 4Cx25 mm² - B2.26 05 19.04 - Z02 - 1 - L - 72 - SL | 1 | 2025-04-02 | 2025-04-05 |  |  | FALSE | yes
| JD3RZ02-1L72SL9221 | Testing and Commitioning for Copper Cables 4Cx25 mm² - B2.26 05 19.04 - Z02 - 1 - L - 72 - SL | 1 | 2025-04-09 | 2025-04-12 |  |  | FALSE | yes
| JD3RZ02-1L72SL9232 | INSTALLINGfor insulated copper conductor 16 mm² - B2.26 05 19.08 - Z02 - 1 - L - 72 - SL | 1 | 2025-04-02 | 2025-04-05 |  |  | FALSE | yes
| JD3RZ02-1L72SL9233 | TESTING AND COMMITIONINGfor insulated copper conductor 16 mm² - B2.26 05 19.08 - Z02 - 1 - L - 72 - SL | 1 | 2025-04-06 | 2025-04-08 |  |  | FALSE | yes
| JD3RZ02-1L72SL9239 | Excavation of reinforced concrete foundationfor LIGHTING POLE one arm - B2.26 56 19.02 - Z02 - 1 - L - 72 - SL | 1 | 2025-03-30 | 2025-03-31 |  |  | FALSE | yes
| JD3RZ02-1L72SL9240 | Installation of reinforced concrete foundationfor LIGHTING POLE one arm - B2.26 56 19.02 - Z02 - 1 - L - 72 - SL | 1 | 2025-04-01 | 2025-04-02 |  |  | FALSE | yes
| JD3RZ02-1L72SL9241 | Backfilling of reinforced concrete foundationfor LIGHTING POLE one arm - B2.26 56 19.02 - Z02 - 1 - L - 72 - SL | 1 | 2025-04-03 | 2025-04-05 |  |  | FALSE | yes
| JD3RZ02-1L72SL9242 | Installation Worksfor LIGHTING POLE one arm - B2.26 56 19.02 - Z02 - 1 - L - 72 - SL | 1 | 2025-04-06 | 2025-04-09 |  |  | FALSE | yes
| JD3RZ02-1L72SL9243 | Testing and Commitioningfor LIGHTING POLE one arm - B2.26 56 19.02 - Z02 - 1 - L - 72 - SL | 1 | 2025-04-10 | 2025-04-14 |  |  | FALSE | yes
| JD3RZ02-1L72SL9244 | Installationfor Lighting( LED ) Luminaire 150 WATT - B2.26.56.19.01 - Z02 - 1 - L - 72 - SL | 1 | 2025-04-10 | 2025-04-12 |  |  | FALSE | yes
| JD3RZ02-1L72SL9247 | Supply, construct, connect and test earthing pitsfor Street Lighting EARTHING SYSTEM - B2.26 05 26.01 - Z02 - 1 - L - 72 | 1 | 2025-04-10 | 2025-04-12 |  |  | FALSE | yes
| JD3RZ02-1L72SL9248 | Excavation Worksfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - Z02 - 1 - L - 72 - SL | 1 | 2025-04-01 | 2025-04-02 |  |  | FALSE | yes
| JD3RZ02-1L72SL9249 | Installationfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - Z02 - 1 - L - 72 - SL | 1 | 2025-04-03 | 2025-04-05 |  |  | FALSE | yes
| JD3RZ02-1L72SL9250 | Pouring Concrete Coverfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - Z02 - 1 - L - 72 - SL | 1 | 2025-04-06 | 2025-04-07 |  |  | FALSE | yes
| JD3RZ02-1L72SL9251 | Testing and Backfilling Worksfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - Z02 - 1 - L - 72 - SL | 1 | 2025-04-08 | 2025-04-09 |  |  | FALSE | yes
| JD3RZ02-1L72SL9260 | Excavationfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - Z02 - 1 - L - 72 - SL | 1 | 2025-04-03 | 2025-04-05 |  |  | FALSE | yes
| JD3RZ02-1L72SL9261 | Installationfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - Z02 - 1 - L - 72 - SL | 1 | 2025-04-06 | 2025-04-07 |  |  | FALSE | yes
| JD3RZ02-1L72SL9262 | Backfillingfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - Z02 - 1 - L - 72 - SL | 1 | 2025-04-08 | 2025-04-09 |  |  | FALSE | yes
| JD3RZ02-1L72SL9263 | Excavationfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - Z02 - 1 - L - 72 - SL | 1 | 2025-04-06 | 2025-04-07 |  |  | FALSE | yes
| JD3RZ02-1L72SL9264 | Installationfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - Z02 - 1 - L - 72 - SL | 1 | 2025-04-08 | 2025-04-09 |  |  | FALSE | yes
| JD3RZ02-1L72SL9265 | Backfillingfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - Z02 - 1 - L - 72 - SL | 1 | 2025-04-13 | 2025-04-14 |  |  | FALSE | yes
| JD3RZ02-1L72SS521441 | Finishing, Benching Works for Manholes 1200 mm - Depth from 3.51 to 4.50 - B5.33 05 13.05 - MR - C - 03 - SS | 1 | 2025-01-07 | 2025-01-08 |  |  | FALSE | yes
| JD3RZ02-1L72SS8638 | Backfilling Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z02 - 1 - L - 72 - SS | 1 | 2024-12-21 | 2024-12-22 |  |  | FALSE | yes
| JD3RZ02-1L72SS8639 | Finishing, Benching Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z02 - 1 - L - 72 - SS | 1 | 2024-12-23 | 2024-12-24 |  |  | FALSE | yes
| JD3RZ02-1L72SS8651 | Finishing, Benching Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z02 - 1 - L - 72 - SS | 1 | 2025-01-13 | 2025-01-14 |  |  | FALSE | yes
| JD3RZ02-1L72ST524363 | Concrete encasement for pipes - NNB6.33 42 11.25 - Z02 - 1 - L - 72 - ST | 1 | 2025-02-08 | 2025-02-10 |  |  | FALSE | yes
| JD3RZ02-1L72ST8719 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z02 - 1 - L - 72 - ST | 1 | 2025-01-18 | 2025-01-19 |  |  | FALSE | yes
| JD3RZ02-1L72ST8720 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z02 - 1 - L | 1 | 2025-01-20 | 2025-01-22 |  |  | FALSE | yes
| JD3RZ02-1L72ST8721 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z02 - 1 - L - 72 - ST | 1 | 2025-01-23 | 2025-01-26 |  |  | FALSE | yes
| JD3RZ02-1L72ST8722 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z02 - 1 - L - 72 - ST | 1 | 2025-01-27 | 2025-01-29 |  |  | FALSE | yes
| JD3RZ02-1L72ST8723 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z02 - 1 - L - 72 - ST | 1 | 2025-02-11 | 2025-02-15 |  |  | FALSE | yes
| JD3RZ02-1L72ST8724 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 1 - L - 72 - ST | 1 | 2025-01-20 | 2025-01-21 |  |  | FALSE | yes
| JD3RZ02-1L72ST8725 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 1 - L - | 1 | 2025-01-22 | 2025-01-23 |  |  | FALSE | yes
| JD3RZ02-1L72ST8726 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 1 - L - 72 - ST | 1 | 2025-01-25 | 2025-01-26 |  |  | FALSE | yes
| JD3RZ02-1L72ST8727 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 1 - L - 72 - ST | 1 | 2025-01-27 | 2025-01-28 |  |  | FALSE | yes
| JD3RZ02-1L72ST8728 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 1 - L - 72 - ST | 1 | 2025-02-16 | 2025-02-17 |  |  | FALSE | yes
| JD3RZ02-1L72ST8729 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z02 - 1 - L - 72 - ST | 1 | 2025-01-22 | 2025-01-23 |  |  | FALSE | yes
| JD3RZ02-1L72ST8730 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z02 - 1 - L - | 1 | 2025-01-25 | 2025-01-26 |  |  | FALSE | yes
| JD3RZ02-1L72ST8731 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z02 - 1 - L - 72 - ST | 1 | 2025-01-27 | 2025-01-28 |  |  | FALSE | yes
| JD3RZ02-1L72ST8732 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z02 - 1 - L - 72 - ST | 1 | 2025-01-29 | 2025-01-30 |  |  | FALSE | yes
| JD3RZ02-1L72ST8733 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z02 - 1 - L - 72 - ST | 1 | 2025-02-18 | 2025-02-19 |  |  | FALSE | yes
| JD3RZ02-1L72ST8904.R | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z02 - 1 - L - 72 - ST - Rem | 1 | 2025-02-08 | 2025-02-09 |  |  | FALSE | yes
| JD3RZ02-1L72ST8905 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z02 - 1 - L - 72 | 1 | 2025-02-10 | 2025-02-11 |  |  | FALSE | yes
| JD3RZ02-1L72ST8906 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z02 - 1 - L - 72 - ST | 1 | 2025-02-26 | 2025-02-27 |  |  | FALSE | yes
| JD3RZ02-1L72ST8915 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z02 - 1 - L - 72 | 1 | 2025-02-15 | 2025-02-16 |  |  | FALSE | yes
| JD3RZ02-1L72ST8916 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z02 - 1 - L - 72 - ST | 1 | 2025-03-01 | 2025-03-02 |  |  | FALSE | yes
| JD3RZ02-1L72ST8919 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z02 - 1 - L - 72 - ST | 1 | 2025-02-15 | 2025-02-16 | 2025-10-21 |  | FALSE | FALSE
| JD3RZ02-1L72ST8920 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z02 - 1 - L - 72 | 1 | 2025-02-17 | 2025-02-18 |  |  | FALSE | yes
| JD3RZ02-1L72ST8921 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z02 - 1 - L - 72 - ST | 1 | 2025-03-03 | 2025-03-04 |  |  | FALSE | yes
| JD3RZ02-1L72ST8934.R | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z02 - 1 - L - 72 - ST - Rem | 1 | 2025-02-19 | 2025-02-20 |  |  | FALSE | yes
| JD3RZ02-1L72ST8935 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z02 - 1 - L - 72 | 1 | 2025-02-22 | 2025-02-23 |  |  | FALSE | yes
| JD3RZ02-1L72ST8936 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z02 - 1 - L - 72 - ST | 1 | 2025-03-05 | 2025-03-06 |  |  | FALSE | yes
| JD3RZ02-1L72ST8937 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - Z02 - 1 - L - 72 - ST | 1 | 2025-02-17 | 2025-02-18 |  |  | FALSE | yes
| JD3RZ02-1L72ST8938 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - Z02 - 1 - L - 72 - ST | 1 | 2025-02-19 | 2025-02-22 |  |  | FALSE | yes
| JD3RZ02-1L72ST8939 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - Z02 - 1 - L - 72 - ST | 1 | 2025-02-23 | 2025-02-25 |  |  | FALSE | yes
| JD3RZ02-1L72ST8940 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - Z02 - 1 - L - 72 - ST | 1 | 2025-03-08 | 2025-03-09 |  |  | FALSE | yes
| JD3RZ02-1L72ST8941 | EXCAVATION Works for Catchbasine double - B6.33 05 39.10 - Z02 - 1 - L - 72 - ST | 1 | 2025-02-19 | 2025-02-20 |  |  | FALSE | yes
| JD3RZ02-1L72ST8942 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - Z02 - 1 - L - 72 - ST | 1 | 2025-02-22 | 2025-02-24 |  |  | FALSE | yes
| JD3RZ02-1L72ST8943 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z02 - 1 - L - 72 - ST | 1 | 2025-02-25 | 2025-02-27 |  |  | FALSE | yes
| JD3RZ02-1L72ST8944 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z02 - 1 - L - 72 - ST | 1 | 2025-03-01 | 2025-03-02 |  |  | FALSE | yes
| JD3RZ02-1L72TC9275 | Excavation Worksfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z02 - 1 - L - 72 - TC | 1 | 2025-04-08 | 2025-04-09 |  |  | FALSE | yes
| JD3RZ02-1L72TC9276 | Installationfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z02 - 1 - L - 72 - TC | 1 | 2025-04-10 | 2025-04-14 |  |  | FALSE | yes
| JD3RZ02-1L72TC9277 | Pouring Concrete Coverfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z02 - 1 - L - 72 - | 1 | 2025-04-15 | 2025-04-19 |  |  | FALSE | yes
| JD3RZ02-1L72TC9278 | Backfilling Worksfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z02 - 1 - L - 72 - TC | 1 | 2025-04-20 | 2025-04-21 |  |  | FALSE | yes
| JD3RZ02-1L72TC9279 | Excavation and Bedding Worksfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z02 - 1 - L - 72 - TC | 1 | 2025-04-10 | 2025-04-12 |  |  | FALSE | yes
| JD3RZ02-1L72TC9280 | Installationfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z02 - 1 - L - 72 - TC | 1 | 2025-04-13 | 2025-04-14 |  |  | FALSE | yes
| JD3RZ02-1L72TC9281 | Backfilling Worksfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z02 - 1 - L - 72 - TC | 1 | 2025-04-15 | 2025-04-16 |  |  | FALSE | yes
| JD3RZ02-1L72TSE8995 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 1 - L - 72 - TSE | 1 | 2025-02-22 | 2025-02-24 |  |  | FALSE | yes
| JD3RZ02-1L72TSE8996 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 1 - L - 72 | 1 | 2025-02-25 | 2025-02-27 |  |  | FALSE | yes
| JD3RZ02-1L72TSE8997 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 1 - L - 72 - TSE | 1 | 2025-03-01 | 2025-03-06 |  |  | FALSE | yes
| JD3RZ02-1L72TSE8998 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 1 - L - 72 - TSE | 1 | 2025-03-10 | 2025-03-13 |  |  | FALSE | yes
| JD3RZ02-1L72TSE8999 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 1 - L - 72 - TSE | 1 | 2025-03-15 | 2025-03-18 |  |  | FALSE | yes
| JD3RZ02-1L72TSE9120 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z02 - 1 - L - 72 - TSE | 1 | 2025-03-08 | 2025-03-09 |  |  | FALSE | yes
| JD3RZ02-1L72TSE9121 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z02 - 1 - L - 72 - TSE | 1 | 2025-03-10 | 2025-03-11 |  |  | FALSE | yes
| JD3RZ02-1L72WT8945 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z02 - 1 - L - 72 - WT | 1 | 2025-02-25 | 2025-03-01 | 2025-08-16 |  | FALSE | FALSE
| JD3RZ02-1L72WT8946 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z02 - 1 - L - 72 - W | 1 | 2025-03-02 | 2025-03-06 | 2025-08-20 |  | FALSE | FALSE
| JD3RZ02-1L72WT8947 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z02 - 1 - L - 72 - WT | 1 | 2025-03-08 | 2025-03-16 | 2025-08-23 |  | FALSE | FALSE
| JD3RZ02-1L72WT8948 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z02 - 1 - L - 72 - WT | 1 | 2025-03-17 | 2025-03-22 | 2025-09-16 |  | FALSE | FALSE
| JD3RZ02-1L72WT8949 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z02 - 1 - L - 72 - WT | 1 | 2025-03-26 | 2025-03-31 | 2025-08-27 |  | FALSE | FALSE
| JD3RZ02-1L72WT8970 | INSTALLATIONfor gate valves 150 mm - B3.33 14 19.01 - Z02 - 1 - L - 72 - WT | 1 | 2025-03-08 | 2025-03-09 |  |  | FALSE | yes
| JD3RZ02-1L72WT8971 | TESTING AND COMMITIONfor gate valves 150 mm - B3.33 14 19.01 - Z02 - 1 - L - 72 - WT | 1 | 2025-03-10 | 2025-03-11 |  |  | FALSE | yes
| JD3RZ02-1L72WT8980 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z02 - 1 - L - 72 - WT | 1 | 2025-03-19 | 2025-03-20 |  |  | FALSE | yes
| JD3RZ02-1L72WT8981 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z02 - 1 - L - 72 - WT | 1 | 2025-03-22 | 2025-03-23 |  |  | FALSE | yes
| JD3RZ02-1L72WT8982 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z02 - 1 - L - 72 - WT | 1 | 2025-03-24 | 2025-03-25 |  |  | FALSE | yes
| JD3RZ02-1L73SL9931 | Excavation Worksfor Copper Cables 4Cx25 mm² - B2.26 05 19.04 - Z02 - 1 - L - 73 - SL | 1 | 2025-03-22 | 2025-03-24 |  |  | FALSE | yes
| JD3RZ02-1L73SL9932 | Installationfor Copper Cables 4Cx25 mm² - B2.26 05 19.04 - Z02 - 1 - L - 73 - SL | 1 | 2025-03-26 | 2025-03-29 |  |  | FALSE | yes
| JD3RZ02-1L73SL9933 | Backfilling, Warning Tabe Worksfor Copper Cables 4Cx25 mm² - B2.26 05 19.04 - Z02 - 1 - L - 73 - SL | 1 | 2025-03-30 | 2025-04-01 |  |  | FALSE | yes
| JD3RZ02-1L73SL9934 | Testing and Commitioning for Copper Cables 4Cx25 mm² - B2.26 05 19.04 - Z02 - 1 - L - 73 - SL | 1 | 2025-04-06 | 2025-04-08 |  |  | FALSE | yes
| JD3RZ02-1L73SL9945 | INSTALLINGfor insulated copper conductor 16 mm² - B2.26 05 19.08 - Z02 - 1 - L - 73 - SL | 1 | 2025-03-30 | 2025-04-01 |  |  | FALSE | yes
| JD3RZ02-1L73SL9946 | TESTING AND COMMITIONINGfor insulated copper conductor 16 mm² - B2.26 05 19.08 - Z02 - 1 - L - 73 - SL | 1 | 2025-04-02 | 2025-04-05 |  |  | FALSE | yes
| JD3RZ02-1L73SL9952 | Excavation of reinforced concrete foundationfor LIGHTING POLE one arm - B2.26 56 19.02 - Z02 - 1 - L - 73 - SL | 1 | 2025-03-25 | 2025-03-26 |  |  | FALSE | yes
| JD3RZ02-1L73SL9953 | Installation of reinforced concrete foundationfor LIGHTING POLE one arm - B2.26 56 19.02 - Z02 - 1 - L - 73 - SL | 1 | 2025-03-27 | 2025-03-29 |  |  | FALSE | yes
| JD3RZ02-1L73SL9954 | Backfilling of reinforced concrete foundationfor LIGHTING POLE one arm - B2.26 56 19.02 - Z02 - 1 - L - 73 - SL | 1 | 2025-03-30 | 2025-03-31 |  |  | FALSE | yes
| JD3RZ02-1L73SL9955 | Installation Worksfor LIGHTING POLE one arm - B2.26 56 19.02 - Z02 - 1 - L - 73 - SL | 1 | 2025-04-01 | 2025-04-03 |  |  | FALSE | yes
| JD3RZ02-1L73SL9956 | Testing and Commitioningfor LIGHTING POLE one arm - B2.26 56 19.02 - Z02 - 1 - L - 73 - SL | 1 | 2025-04-05 | 2025-04-07 |  |  | FALSE | yes
| JD3RZ02-1L73SL9957 | Installationfor Lighting( LED ) Luminaire 150 WATT - B2.26.56.19.01 - Z02 - 1 - L - 73 - SL | 1 | 2025-03-30 | 2025-03-31 |  |  | FALSE | yes
| JD3RZ02-1L73SL9960 | Supply, construct, connect and test earthing pitsfor Street Lighting EARTHING SYSTEM - B2.26 05 26.01 - Z02 - 1 - L - 73 | 1 | 2025-04-01 | 2025-04-02 |  |  | FALSE | yes
| JD3RZ02-1L73SL9961 | Excavation Worksfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - Z02 - 1 - L - 73 - SL | 1 | 2025-03-27 | 2025-03-29 |  |  | FALSE | yes
| JD3RZ02-1L73SL9962 | Installationfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - Z02 - 1 - L - 73 - SL | 1 | 2025-03-30 | 2025-03-31 |  |  | FALSE | yes
| JD3RZ02-1L73SL9963 | Pouring Concrete Coverfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - Z02 - 1 - L - 73 - SL | 1 | 2025-04-01 | 2025-04-02 |  |  | FALSE | yes
| JD3RZ02-1L73SL9964 | Testing and Backfilling Worksfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - Z02 - 1 - L - 73 - SL | 1899-12-31 | 2025-04-03 | 2025-04-05 |  |  | FALSE | yes
| JD3RZ02-1L73SL9973 | Excavationfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - Z02 - 1 - L - 73 - SL | 1 | 2025-03-30 | 2025-03-31 |  |  | FALSE | yes
| JD3RZ02-1L73SL9974 | Installationfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - Z02 - 1 - L - 73 - SL | 1 | 2025-04-01 | 2025-04-02 |  |  | FALSE | yes
| JD3RZ02-1L73SL9975 | Backfillingfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - Z02 - 1 - L - 73 - SL | 1 | 2025-04-03 | 2025-04-05 |  |  | FALSE | yes
| JD3RZ02-1L73SL9976 | Excavationfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - Z02 - 1 - L - 73 - SL | 1 | 2025-04-01 | 2025-04-02 |  |  | FALSE | yes
| JD3RZ02-1L73SL9977 | Installationfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - Z02 - 1 - L - 73 - SL | 1899-12-31 | 2025-04-03 | 2025-04-05 |  |  | FALSE | yes
| JD3RZ02-1L73SL9978 | Backfillingfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - Z02 - 1 - L - 73 - SL | 1 | 2025-04-06 | 2025-04-07 |  |  | FALSE | yes
| JD3RZ02-1L73SL9982 | Excavationfor Street Lighting panels - B2.26 24 16.01 - Z02 - 1 - L - 73 - SL | 1 | 2025-04-03 | 2025-04-05 |  |  | FALSE | yes
| JD3RZ02-1L73SL9983 | Installationfor Street Lighting panels - B2.26 24 16.01 - Z02 - 1 - L - 73 - SL | 1 | 2025-04-06 | 2025-04-07 |  |  | FALSE | yes
| JD3RZ02-1L73SL9984 | Backfillingfor Street Lighting panels - B2.26 24 16.01 - Z02 - 1 - L - 73 - SL | 1 | 2025-04-08 | 2025-04-09 |  |  | FALSE | yes
| JD3RZ02-1L73SL9985 | Excavationfor KWH meter - B2.26 24 16.02 - Z02 - 1 - L - 73 - SL | 1 | 2025-04-06 | 2025-04-07 |  |  | FALSE | yes
| JD3RZ02-1L73SL99851 | Excavation for Drawpit - B2.33 71 19.13.03 - Z02 - 1 - L - 73 - SL | 1 | 2025-04-08 | 2025-04-09 |  |  | FALSE | yes
| JD3RZ02-1L73SL9986 | Installationfor KWH meter - B2.26 24 16.02 - Z02 - 1 - L - 73 - SL | 1 | 2025-04-08 | 2025-04-09 |  |  | FALSE | yes
| JD3RZ02-1L73SL99861 | Installation for Drawpit - B2.33 71 19.13.03 - Z02 - 1 - L - 73 - SL | 1 | 2025-04-10 | 2025-04-12 |  |  | FALSE | yes
| JD3RZ02-1L73SL9987 | Backfillingfor KWH meter - B2.26 24 16.02 - Z02 - 1 - L - 73 - SL | 1 | 2025-04-10 | 2025-04-12 |  |  | FALSE | yes
| JD3RZ02-1L73SL99871 | Backfilling for Drawpit - B2.33 71 19.13.03 - Z02 - 1 - L - 73 - SL | 1 | 2025-04-13 | 2025-04-14 |  |  | FALSE | yes
| JD3RZ02-1L73SS521401 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 3.51 to 4.50 - B5.33 05 13.05 - MR - C - 03 - SS | 1 | 2025-02-08 | 2025-02-09 | 2025-08-18 |  | FALSE | FALSE
| JD3RZ02-1L73SS521411 | Installation of Base Works for Manholes 1200 mm - Depth from 3.51 to 4.50 - B5.33 05 13.05 - MR - C - 03 - SS | 1 | 2025-02-10 | 2025-02-13 | 2025-08-21 |  | FALSE | FALSE
| JD3RZ02-1L73SS521421 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 3.51 to 4.50 - B5.33 05 13.05 - MR - | 1 | 2025-02-15 | 2025-02-18 | 2025-08-25 |  | FALSE | FALSE
| JD3RZ02-1L73SS521431 | Backfilling Works for Manholes 1200 mm - Depth from 3.51 to 4.50 - B5.33 05 13.05 - MR - C - 03 - SS | 1 | 2025-02-19 | 2025-02-20 | 2025-11-02 |  | FALSE | FALSE
| JD3RZ02-1L73SS521441 | Finishing, Benching Works for Manholes 1200 mm - Depth from 3.51 to 4.50 - B5.33 05 13.05 - MR - C - 03 - SS | 1 | 2025-02-22 | 2025-02-23 | 2025-11-04 |  | FALSE | FALSE
| JD3RZ02-1L73SS9348 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z02 - 1 - L - 73 - SS | 1 | 2025-02-03 | 2025-02-04 | 2025-10-30 |  | FALSE | FALSE
| JD3RZ02-1L73SS9349 | Installation of Base Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z02 - 1 - L - 73 - SS | 1 | 2025-02-05 | 2025-02-06 | 2025-11-02 |  | FALSE | FALSE
| JD3RZ02-1L73SS9350 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z02 | 1 | 2025-02-08 | 2025-02-09 | 2025-11-04 |  | FALSE | FALSE
| JD3RZ02-1L73SS9351 | Backfilling Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z02 - 1 - L - 73 - SS | 1 | 2025-02-10 | 2025-02-11 | 2025-11-04 |  | FALSE | FALSE
| JD3RZ02-1L73SS9352 | Finishing, Benching Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z02 - 1 - L - 73 - SS | 1 | 2025-02-12 | 2025-02-13 | 2025-11-05 |  | FALSE | FALSE
| JD3RZ02-1L73SS9365 | Excavation and PC Blinding Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.06 - Z02 - 1 - L | 1 | 2025-02-05 | 2025-02-06 | 2025-10-30 |  | FALSE | FALSE
| JD3RZ02-1L73SS9366 | Installation of Base Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.06 - Z02 - 1 - L - 73 - | 1 | 2025-02-08 | 2025-02-09 | 2025-11-02 |  | FALSE | FALSE
| JD3RZ02-1L73SS9367 | Installation of Manhole Ring and Cover Slab Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13. | 1 | 2025-02-10 | 2025-02-11 | 2025-11-04 |  | FALSE | FALSE
| JD3RZ02-1L73SS9368 | Installation of fitting Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.06 - Z02 - 1 - L - 7 | 1 | 2025-02-12 | 2025-02-13 | 2025-11-04 |  | FALSE | FALSE
| JD3RZ02-1L73SS9369 | Concrete Encasement Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.06 - Z02 - 1 - L - 73 - | 1 | 2025-02-15 | 2025-02-16 | 2025-11-05 |  | FALSE | FALSE
| JD3RZ02-1L73SS9370 | Backfilling Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.06 - Z02 - 1 - L - 73 - SS | 1 | 2025-02-17 | 2025-02-18 |  |  | FALSE | yes
| JD3RZ02-1L73SS9371 | Finishing, Benching Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.06 - Z02 - 1 - L - 73 - | 1 | 2025-02-19 | 2025-02-20 |  |  | FALSE | yes
| JD3RZ02-1L73ST9432 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z02 - 1 - L - 73 - ST | 1 | 2025-03-23 | 2025-03-24 | 2025-10-30 |  | FALSE | FALSE
| JD3RZ02-1L73ST9433 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z02 - 1 - L | 1 | 2025-03-25 | 2025-03-27 | 2025-11-02 |  | FALSE | FALSE
| JD3RZ02-1L73ST9434 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z02 - 1 - L - 73 - ST | 1 | 2025-03-29 | 2025-03-31 | 2025-11-05 |  | FALSE | FALSE
| JD3RZ02-1L73ST9435 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z02 - 1 - L - 73 - ST | 1 | 2025-04-01 | 2025-04-03 |  |  | FALSE | yes
| JD3RZ02-1L73ST9436 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z02 - 1 - L - 73 - ST | 1 | 2025-04-05 | 2025-04-08 |  |  | FALSE | yes
| JD3RZ02-1L73ST9437 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 1 - L - 73 - ST | 1 | 2025-03-25 | 2025-03-26 | 2025-10-20 |  | FALSE | FALSE
| JD3RZ02-1L73ST9438 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 1 - L - | 1 | 2025-03-27 | 2025-03-29 | 2025-10-21 |  | FALSE | FALSE
| JD3RZ02-1L73ST9439 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 1 - L - 73 - ST | 1 | 2025-03-30 | 2025-03-31 | 2025-10-22 |  | FALSE | FALSE
| JD3RZ02-1L73ST9440 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 1 - L - 73 - ST | 1 | 2025-04-01 | 2025-04-02 | 2025-10-23 |  | FALSE | FALSE
| JD3RZ02-1L73ST9441 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 1 - L - 73 - ST | 1 | 2025-04-03 | 2025-04-05 | 2025-10-25 |  | FALSE | FALSE
| JD3RZ02-1L73ST9458 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m - B6.33 42 11.05 - Z02 - 1 - L - | 1 | 2025-04-06 | 2025-04-07 | 2025-10-25 |  | FALSE | FALSE
| JD3RZ02-1L73ST9459 | Installing for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m - B6.33 42 11.05 - Z02 - 1 - L - 73 - ST | 1 | 2025-04-08 | 2025-04-09 |  |  | FALSE | yes
| JD3RZ02-1L73ST9460 | Primary Test for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m - B6.33 42 11.05 - Z02 - 1 - L - 73 - ST | 1 | 2025-04-10 | 2025-04-12 |  |  | FALSE | yes
| JD3RZ02-1L73ST9461 | Backfilling Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m - B6.33 42 11.05 - Z02 - 1 - L - 73 - ST | 1 | 2025-04-14 | 2025-04-15 |  |  | FALSE | yes
| JD3RZ02-1L73ST9464 | Installing for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - Z02 - 1 - L - 73 - ST | 1 | 2025-04-10 | 2025-04-12 | 2025-08-27 |  | FALSE | FALSE
| JD3RZ02-1L73ST9465 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - Z02 - 1 - L - 73 - ST | 1 | 2025-04-13 | 2025-04-14 | 2025-08-30 |  | FALSE | FALSE
| JD3RZ02-1L73ST9466 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - Z02 - 1 - L - 73 - ST | 1 | 2025-04-16 | 2025-04-17 | 2025-10-07 |  | FALSE | FALSE
| JD3RZ02-1L73ST9544 | Installing for GRP Pipe Line 1200 mm - depth from 2.51 to 3.50 m - B6.33 42 11.24 - Z02 - 1 - L - 73 - ST | 1 | 2025-04-15 | 2025-04-16 | 2025-10-25 |  | FALSE | FALSE
| JD3RZ02-1L73ST9545 | Primary Test for GRP Pipe Line 1200 mm - depth from 2.51 to 3.50 m - B6.33 42 11.24 - Z02 - 1 - L - 73 - ST | 1 | 2025-04-17 | 2025-04-19 |  |  | FALSE | yes
| JD3RZ02-1L73ST9546 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 2.51 to 3.50 m - B6.33 42 11.24 - Z02 - 1 - L - 73 - ST | 1 | 2025-04-21 | 2025-04-22 |  |  | FALSE | yes
| JD3RZ02-1L73ST9565 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.03 - Z02 - 1 - L - 73 - ST | 1 | 2025-03-11 | 2025-03-17 | 2025-10-25 |  | FALSE | FALSE
| JD3RZ02-1L73ST9566 | Isolation Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - Z02 - 1 - L - 73 - ST | 1 | 2025-03-18 | 2025-03-19 |  |  | FALSE | yes
| JD3RZ02-1L73ST9567 | Backfilling Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - B6.34 42 16.03 - Z02 - 1 - L - 73 - ST | 1 | 2025-03-20 | 2025-03-22 |  |  | FALSE | yes
| JD3RZ02-1L73ST9615 | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z02 - 1 - L - 73 - ST | 1 | 2025-02-25 | 2025-02-26 | 2025-08-09 |  | FALSE | FALSE
| JD3RZ02-1L73ST9616 | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z02 - 1 - L - 73 - ST | 1 | 2025-02-27 | 2025-03-01 | 2025-08-12 |  | FALSE | FALSE
| JD3RZ02-1L73ST9617 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z02 - 1 - L - 73 - ST | 1 | 2025-03-02 | 2025-03-03 | 2025-10-05 |  | FALSE | FALSE
| JD3RZ02-1L73ST9618 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z02 - 1 - L - 73 | 1 | 2025-03-04 | 2025-03-05 |  |  | FALSE | yes
| JD3RZ02-1L73ST9619 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z02 - 1 - L - 73 - ST | 1 | 2025-03-06 | 2025-03-08 |  |  | FALSE | yes
| JD3RZ02-1L73ST9628 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z02 - 1 - L - 73 | 1 | 2025-03-10 | 2025-03-11 |  |  | FALSE | yes
| JD3RZ02-1L73ST9629 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z02 - 1 - L - 73 - ST | 1 | 2025-03-12 | 2025-03-13 |  |  | FALSE | yes
| JD3RZ02-1L73ST9630 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z02 - 1 - L - 73 - ST | 1 | 2025-03-05 | 2025-03-06 |  |  | FALSE | yes
| JD3RZ02-1L73ST9631 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z02 - 1 - L - 73 - ST | 1 | 2025-03-08 | 2025-03-09 |  |  | FALSE | yes
| JD3RZ02-1L73ST9632 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z02 - 1 - L - 73 - ST | 1 | 2025-03-10 | 2025-03-11 |  |  | FALSE | yes
| JD3RZ02-1L73ST9633 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z02 - 1 - L - 73 | 1 | 2025-03-12 | 2025-03-13 |  |  | FALSE | yes
| JD3RZ02-1L73ST9634 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z02 - 1 - L - 73 - ST | 1 | 2025-03-15 | 2025-03-16 |  |  | FALSE | yes
| JD3RZ02-1L73ST9645 | Excavation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z02 - 1 - L - 73 - ST | 1 | 2025-03-08 | 2025-03-09 | 2025-10-18 |  | FALSE | FALSE
| JD3RZ02-1L73ST9646 | Base Plain Concrete Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z02 - 1 - L - 73 - ST | 1 | 2025-03-10 | 2025-03-11 | 2025-10-19 |  | FALSE | FALSE
| JD3RZ02-1L73ST9647 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z02 - 1 - L - 73 - ST | 1 | 2025-03-12 | 2025-03-13 | 2025-10-21 |  | FALSE | FALSE
| JD3RZ02-1L73ST9648 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z02 - 1 - L - 73 | 1 | 2025-03-15 | 2025-03-16 |  |  | FALSE | yes
| JD3RZ02-1L73ST9649 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z02 - 1 - L - 73 - ST | 1 | 2025-03-17 | 2025-03-18 |  |  | FALSE | yes
| JD3RZ02-1L73ST9650 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - Z02 - 1 - L - 73 - ST | 1 | 2025-03-10 | 2025-03-12 | 2025-10-29 |  | FALSE | FALSE
| JD3RZ02-1L73ST9651 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - Z02 - 1 - L - 73 - ST | 1 | 2025-03-13 | 2025-03-17 | 2025-11-01 |  | FALSE | FALSE
| JD3RZ02-1L73ST9652 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - Z02 - 1 - L - 73 - ST | 1 | 2025-03-18 | 2025-03-22 |  |  | FALSE | yes
| JD3RZ02-1L73ST9653 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - Z02 - 1 - L - 73 - ST | 1899-12-31 | 2025-03-23 | 2025-03-25 |  |  | FALSE | yes
| JD3RZ02-1L73ST9654 | EXCAVATION Works for Catchbasine double - B6.33 05 39.10 - Z02 - 1 - L - 73 - ST | 1 | 2025-03-13 | 2025-03-15 | 2025-10-29 |  | FALSE | FALSE
| JD3RZ02-1L73ST9655 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - Z02 - 1 - L - 73 - ST | 1 | 2025-03-16 | 2025-03-18 | 2025-11-04 |  | FALSE | FALSE
| JD3RZ02-1L73ST9656 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z02 - 1 - L - 73 - ST | 1 | 2025-03-19 | 2025-03-22 |  |  | FALSE | yes
| JD3RZ02-1L73ST9657 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z02 - 1 - L - 73 - ST | 1 | 2025-03-23 | 2025-03-24 |  |  | FALSE | yes
| JD3RZ02-1L73TC9988 | Excavation Worksfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z02 - 1 - L - 73 - TC | 1899-12-31 | 2025-04-09 | 2025-04-10 |  |  | FALSE | yes
| JD3RZ02-1L73TC9989 | Installationfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z02 - 1 - L - 73 - TC | 1 | 2025-04-12 | 2025-04-15 |  |  | FALSE | yes
| JD3RZ02-1L73TC9990 | Pouring Concrete Coverfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z02 - 1 - L - 73 - | 1 | 2025-04-16 | 2025-04-20 |  |  | FALSE | yes
| JD3RZ02-1L73TC9991 | Backfilling Worksfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z02 - 1 - L - 73 - TC | 1 | 2025-05-05 | 2025-05-06 |  |  | FALSE | yes
| JD3RZ02-1L73TC9992 | Excavation and Bedding Worksfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z02 - 1 - L - 73 - TC | 1 | 2025-04-24 | 2025-04-26 |  |  | FALSE | yes
| JD3RZ02-1L73TC9993 | Installationfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z02 - 1 - L - 73 - TC | 1 | 2025-04-27 | 2025-04-28 |  |  | FALSE | yes
| JD3RZ02-1L73TC9994 | Backfilling Worksfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z02 - 1 - L - 73 - TC | 1 | 2025-04-29 | 2025-04-30 |  |  | FALSE | yes
| JD3RZ02-1L73TSE9708 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 1 - L - 73 - TSE | 1 | 2025-03-13 | 2025-03-15 |  |  | FALSE | yes
| JD3RZ02-1L73TSE9709 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 1 - L - 73 | 1 | 2025-03-26 | 2025-03-27 |  |  | FALSE | yes
| JD3RZ02-1L73TSE9710 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 1 - L - 73 - TSE | 1 | 2025-03-29 | 2025-03-30 |  |  | FALSE | yes
| JD3RZ02-1L73TSE9711 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 1 - L - 73 - TSE | 1 | 2025-04-23 | 2025-04-24 |  |  | FALSE | yes
| JD3RZ02-1L73TSE9712 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 1 - L - 73 - TSE | 1 | 2025-04-26 | 2025-04-27 |  |  | FALSE | yes
| JD3RZ02-1L73TSE9713 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - 1 - L - 73 - TSE | 1 | 2025-03-16 | 2025-03-19 |  |  | FALSE | yes
| JD3RZ02-1L73TSE9714 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - 1 - L - 73 | 1 | 2025-03-20 | 2025-03-24 |  |  | FALSE | yes
| JD3RZ02-1L73TSE9715 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - 1 - L - 73 - TSE | 1 | 2025-03-25 | 2025-04-01 |  |  | FALSE | yes
| JD3RZ02-1L73TSE9716 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - 1 - L - 73 - TSE | 1 | 2025-04-23 | 2025-04-28 |  |  | FALSE | yes
| JD3RZ02-1L73TSE9717 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - 1 - L - 73 - TSE | 1 | 2025-04-29 | 2025-05-04 |  |  | FALSE | yes
| JD3RZ02-1L73TSE9833 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z02 - 1 - L - 73 - TSE | 1 | 2025-04-02 | 2025-04-03 |  |  | FALSE | yes
| JD3RZ02-1L73TSE9834 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z02 - 1 - L - 73 - TSE | 1899-12-31 | 2025-04-07 | 2025-04-08 |  |  | FALSE | yes
| JD3RZ02-1L73TSE9835 | Installationfor gate valves 250 mm - B4.33 14 19.02 - Z02 - 1 - L - 73 - TSE | 1 | 2025-04-02 | 2025-04-03 |  |  | FALSE | yes
| JD3RZ02-1L73TSE9836 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - Z02 - 1 - L - 73 - TSE | 1 | 2025-04-05 | 2025-04-06 |  |  | FALSE | yes
| JD3RZ02-1L73TSE9845 | Installationfor Wash - Out valves 100 mm. - on pipes with diameter 110 - 400 mm - B4.33 14 19.07 - Z02 - 1 - L - 73 - TS | 1 | 2025-04-02 | 2025-04-03 |  |  | FALSE | yes
| JD3RZ02-1L73TSE9846 | Testing And Commtionningfor Wash - Out valves 100 mm. - on pipes with diameter 110 - 400 mm - B4.33 14 19.07 - Z02 - 1 - | 1 | 2025-04-05 | 2025-04-06 |  |  | FALSE | yes
| JD3RZ02-1L73TSE9869 | EXCAVATION and Bedding Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - Z02 - 1 - L - 73 - TSE | 1899-12-31 | 2025-03-20 | 2025-03-22 |  |  | FALSE | yes
| JD3RZ02-1L73TSE9870 | Plain Concrete Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - Z02 - 1 - L - 73 - TSE | 1 | 2025-03-23 | 2025-03-24 |  |  | FALSE | yes
| JD3RZ02-1L73TSE9871 | INSTALLATIONfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - Z02 - 1 - L - 73 - TSE | 1 | 2025-03-25 | 2025-03-26 |  |  | FALSE | yes
| JD3RZ02-1L73TSE9872 | Backfilling Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - Z02 - 1 - L - 73 - TSE | 1 | 2025-03-27 | 2025-03-29 |  |  | FALSE | yes
| JD3RZ02-1L73WT9658 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z02 - 1 - L - 73 - WT | 1 | 2025-03-16 | 2025-03-17 |  |  | FALSE | yes
| JD3RZ02-1L73WT9659 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z02 - 1 - L - 73 - W | 1 | 2025-03-18 | 2025-03-19 |  |  | FALSE | yes
| JD3RZ02-1L73WT9660 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z02 - 1 - L - 73 - WT | 1 | 2025-03-20 | 2025-03-22 |  |  | FALSE | yes
| JD3RZ02-1L73WT9661 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z02 - 1 - L - 73 - WT | 1 | 2025-03-23 | 2025-03-24 |  |  | FALSE | yes
| JD3RZ02-1L73WT9662 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z02 - 1 - L - 73 - WT | 1 | 2025-04-07 | 2025-04-08 |  |  | FALSE | yes
| JD3RZ02-1L73WT9663 | Excavation Worksfor HDPE Pipes 225 mm - depth from 0 to 1.5 m - B3.33 14 13.02 - Z02 - 1 - L - 73 - WT | 1 | 2025-03-18 | 2025-03-20 |  |  | FALSE | yes
| JD3RZ02-1L73WT9664 | Soil Replacement and Bedding Works for HDPE Pipes 225 mm - depth from 0 to 1.5 m - B3.33 14 13.02 - Z02 - 1 - L - 73 - W | 1 | 2025-03-22 | 2025-03-25 |  |  | FALSE | yes
| JD3RZ02-1L73WT9665 | Installing for HDPE Pipes 225 mm - depth from 0 to 1.5 m - B3.33 14 13.02 - Z02 - 1 - L - 73 - WT | 1 | 2025-03-26 | 2025-04-01 |  |  | FALSE | yes
| JD3RZ02-1L73WT9666 | Testing for HDPE Pipes 225 mm - depth from 0 to 1.5 m - B3.33 14 13.02 - Z02 - 1 - L - 73 - WT | 1 | 2025-04-15 | 2025-04-19 |  |  | FALSE | yes
| JD3RZ02-1L73WT9667 | Backfillingfor HDPE Pipes 225 mm - depth from 0 to 1.5 m - B3.33 14 13.02 - Z02 - 1 - L - 73 - WT | 1 | 2025-04-20 | 2025-04-23 |  |  | FALSE | yes
| JD3RZ02-1L73WT9685 | INSTALLATIONfor gate valves 200 mm - B3.33 14 19.02 - Z02 - 1 - L - 73 - WT | 1 | 2025-04-02 | 2025-04-03 |  |  | FALSE | yes
| JD3RZ02-1L73WT9686 | TESTING AND COMMITIONfor gate valves 200 mm - B3.33 14 19.02 - Z02 - 1 - L - 73 - WT | 1899-12-31 | 2025-04-05 | 2025-04-06 |  |  | FALSE | yes
| JD3RZ02-1L73WT9693 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z02 - 1 - L - 73 - WT | 1 | 2025-03-22 | 2025-03-23 |  |  | FALSE | yes
| JD3RZ02-1L73WT9694 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z02 - 1 - L - 73 - WT | 1 | 2025-03-24 | 2025-03-25 |  |  | FALSE | yes
| JD3RZ02-1L73WT9695 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z02 - 1 - L - 73 - WT | 1 | 2025-03-26 | 2025-03-27 |  |  | FALSE | yes
| JD3RZ02-2C16ST10148 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z02 - 2 - C - 16 - ST | 1 | 2025-02-12 | 2025-02-16 |  |  | FALSE | yes
| JD3RZ02-2C16ST10149 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z02 - 2 - C - 16 - ST | 1899-12-31 | 2025-03-08 | 2025-03-12 |  |  | FALSE | yes
| JD3RZ02-2C16ST10150 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 2 - C - 16 - ST | 1 | 2025-02-04 | 2025-02-05 |  |  | FALSE | yes
| JD3RZ02-2C16ST10151 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 2 - C - | 1 | 2025-02-06 | 2025-02-08 |  |  | FALSE | yes
| JD3RZ02-2C16ST10152 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 2 - C - 16 - ST | 1 | 2025-02-09 | 2025-02-10 |  |  | FALSE | yes
| JD3RZ02-2C16ST10153 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 2 - C - 16 - ST | 1899-12-31 | 2025-02-11 | 2025-02-12 |  |  | FALSE | yes
| JD3RZ02-2C16ST10154 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 2 - C - 16 - ST | 1 | 2025-03-05 | 2025-03-06 |  |  | FALSE | yes
| JD3RZ02-2C16ST10199 | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - Z02 - 2 - C - 16 - ST | 1 | 2025-03-08 | 2025-03-10 | 2025-08-22 |  | FALSE | FALSE
| JD3RZ02-2C16ST10209.R | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - Z02 - 2 - C - 16 - ST - Remain | 1 | 2025-03-11 | 2025-03-12 | 2025-08-20 |  | FALSE | FALSE
| JD3RZ02-2C16ST10224 | Backfilling Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m - B6.33 42 11.15 - Z02 - 2 - C - 16 - ST | 1 | 2025-02-24 | 2025-02-26 | 2025-08-16 |  | FALSE | FALSE
| JD3RZ02-2C16ST10281 | Excavation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - Z02 - 2 - C - 16 - ST | 1899-12-31 | 2024-10-07 | 2024-10-08 | 2025-09-03 |  | FALSE | FALSE
| JD3RZ02-2C16ST10282 | Plain Concrete Works For Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - Z02 - 2 - C - 16 - ST | 1 | 2024-10-09 | 2024-10-10 | 2025-10-11 |  | FALSE | FALSE
| JD3RZ02-2C16ST10283 | Raft Foundation for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - Z02 - 2 - C - 16 - ST | 1 | 2024-10-12 | 2024-10-17 | 2025-11-02 |  | FALSE | FALSE
| JD3RZ02-2C16ST10284 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - Z02 - 2 - C - 16 - ST | 1 | 2025-01-07 | 2025-01-15 | 2025-11-04 |  | FALSE | FALSE
| JD3RZ02-2C16ST10285 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - Z02 - 2 - C - 16 - ST | 1 | 2025-01-16 | 2025-01-25 |  |  | FALSE | yes
| JD3RZ02-2C16ST10286 | Isolation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - Z02 - 2 - C - 16 - ST | 1 | 2025-01-26 | 2025-01-28 |  |  | FALSE | yes
| JD3RZ02-2C16ST10287 | Backfilling Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - Z02 - 2 - C - 16 - ST | 1 | 2025-01-29 | 2025-01-30 |  |  | FALSE | yes
| JD3RZ02-2C16ST10330 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z02 - 2 - C - 16 - ST | 1 | 2025-02-18 | 2025-02-19 |  |  | FALSE | yes
| JD3RZ02-2C16ST10331 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z02 - 2 - C - 16 | 1 | 2025-02-20 | 2025-02-22 |  |  | FALSE | yes
| JD3RZ02-2C16ST10332 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z02 - 2 - C - 16 - ST | 1 | 2025-02-23 | 2025-02-24 |  |  | FALSE | yes
| JD3RZ02-2C16ST10340.R | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z02 - 2 - C - 16 - ST - Rem | 1 | 2025-02-20 | 2025-02-22 |  |  | FALSE | yes
| JD3RZ02-2C16ST10341 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z02 - 2 - C - 16 | 1 | 2025-02-23 | 2025-02-24 |  |  | FALSE | yes
| JD3RZ02-2C16ST10342 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z02 - 2 - C - 16 - ST | 1 | 2025-02-25 | 2025-02-26 |  |  | FALSE | yes
| JD3RZ02-2C16ST10343 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z02 - 2 - C - 16 - ST | 1 | 2025-02-18 | 2025-02-19 |  |  | FALSE | yes
| JD3RZ02-2C16ST10344 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z02 - 2 - C - 16 - ST | 1 | 2025-02-20 | 2025-02-23 |  |  | FALSE | yes
| JD3RZ02-2C16ST10345 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z02 - 2 - C - 16 - ST | 1 | 2025-02-24 | 2025-02-26 |  |  | FALSE | yes
| JD3RZ02-2C16ST10346 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z02 - 2 - C - 16 | 1 | 2025-02-27 | 2025-03-01 |  |  | FALSE | yes
| JD3RZ02-2C16ST10347 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z02 - 2 - C - 16 - ST | 1 | 2025-03-02 | 2025-03-03 |  |  | FALSE | yes
| JD3RZ02-2C16ST10361 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z02 - 2 - C - 16 | 1 | 2025-03-03 | 2025-03-04 |  |  | FALSE | yes
| JD3RZ02-2C16ST10362 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z02 - 2 - C - 16 - ST | 1 | 2025-03-05 | 2025-03-06 |  |  | FALSE | yes
| JD3RZ02-2C16ST10364 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - Z02 - 2 - C - 16 - ST | 1 | 2025-02-24 | 2025-02-27 | 2025-10-13 |  | FALSE | FALSE
| JD3RZ02-2C16ST10365 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - Z02 - 2 - C - 16 - ST | 1 | 2025-03-01 | 2025-03-04 | 2025-10-15 |  | FALSE | FALSE
| JD3RZ02-2C16ST10366 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - Z02 - 2 - C - 16 - ST | 1 | 2025-03-08 | 2025-03-10 |  |  | FALSE | yes
| JD3RZ02-2C16ST10367 | EXCAVATION Works for Catchbasine double - B6.33 05 39.10 - Z02 - 2 - C - 16 - ST | 1 | 2025-02-24 | 2025-02-25 | 2025-10-13 |  | FALSE | FALSE
| JD3RZ02-2C16ST10368 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - Z02 - 2 - C - 16 - ST | 1 | 2025-02-26 | 2025-03-01 | 2025-10-14 |  | FALSE | FALSE
| JD3RZ02-2C16ST10369 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z02 - 2 - C - 16 - ST | 1 | 2025-03-02 | 2025-03-04 | 2025-10-15 |  | FALSE | FALSE
| JD3RZ02-2C16ST10370 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z02 - 2 - C - 16 - ST | 1 | 2025-03-11 | 2025-03-12 |  |  | FALSE | yes
| JD3RZ02-2C16ST524343 | Concrete encasement for pipes - NNB6.33 42 11.25 - MR - C - 16 - ST | 1 | 2025-02-13 | 2025-03-04 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10421 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 2 - C - 16 - TSE | 1 | 2025-03-13 | 2025-03-15 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10422 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 2 - C - 16 | 1 | 2025-03-16 | 2025-03-17 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10423 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 2 - C - 16 - TSE | 1 | 2025-03-18 | 2025-03-20 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10424 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 2 - C - 16 - TSE | 1 | 2025-03-22 | 2025-03-23 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10425 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-08 | 2025-04-09 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10426 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - 2 - C - 16 - TSE | 1 | 2025-03-16 | 2025-03-17 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10427 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - 2 - C - 16 | 1 | 2025-03-18 | 2025-03-19 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10428 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - 2 - C - 16 - TSE | 1 | 2025-03-20 | 2025-03-22 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10429 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - 2 - C - 16 - TSE | 1 | 2025-03-23 | 2025-03-24 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10430 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-08 | 2025-04-09 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10431 | Excavation Worksfor HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - Z02 - 2 - C - 16 - TSE | 1 | 2025-03-18 | 2025-03-19 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10432 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - Z02 - 2 - C - 16 - T | 1 | 2025-03-20 | 2025-03-22 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10433 | Installing for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - Z02 - 2 - C - 16 - TSE | 1 | 2025-03-23 | 2025-03-24 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10434 | Testing for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - Z02 - 2 - C - 16 - TSE | 1 | 2025-03-25 | 2025-03-26 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10435 | Backfillingfor HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-08 | 2025-04-09 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10470 | Backfillingfor HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-01 | 2025-04-02 | 2025-08-20 |  | FALSE | FALSE
| JD3RZ02-2C16TSE10475 | Backfillingfor HDPE Pipes 450 mm - depth from 2.51 to 3.5 m - B4.33 31 00.11 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-03 | 2025-04-05 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10480 | Backfillingfor HDPE Pipes 450 mm - depth from 3.51 to 4.5 m - B4.33 31 00.12 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-06 | 2025-04-07 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10485 | Backfillingfor HDPE Pipes 450 mm - depth from 4.51 to 5.5 m - B4.33 31 00.13 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-08 | 2025-04-09 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10514 | Testing for GRP Pipes 800 mm - depth from 0 to 1.5 m - B4.33 05 36.01 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-08 | 2025-04-09 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10515 | Backfillingfor GRP Pipes 800 mm - depth from 0 to 1.5 m - B4.33 05 36.01 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-10 | 2025-04-12 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10520 | Backfillingfor GRP Pipes 800 mm - depth from 1.51 to 2.5 m - B4.33 05 36.02 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-13 | 2025-04-15 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10524 | Testing for GRP Pipes 800 mm - depth from 2.51 to 3.5 m - B4.33 05 36.03 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-13 | 2025-04-14 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10525 | Backfillingfor GRP Pipes 800 mm - depth from 2.51 to 3.5 m - B4.33 05 36.03 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-15 | 2025-04-16 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10529 | Testing for GRP Pipes 800 mm - depth from 3.51 to 4.5 m - B4.33 05 36.04 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-15 | 2025-04-16 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10530 | Backfillingfor GRP Pipes 800 mm - depth from 3.51 to 4.5 m - B4.33 05 36.04 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-17 | 2025-04-19 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10534 | Testing for GRP Pipes 800 mm - depth from 4.51 to 5.5 m - B4.33 05 36.05 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-03 | 2025-04-05 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10535 | Backfillingfor GRP Pipes 800 mm - depth from 4.51 to 5.5 m - B4.33 05 36.05 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-06 | 2025-04-07 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10546 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-03 | 2025-04-05 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10547 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-06 | 2025-04-07 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10552 | Installationfor butterfly valves 400 mm. - B4.33 14 19.04 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-06 | 2025-04-07 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10553 | Testing And Commtionningfor butterfly valves 400 mm. - B4.33 14 19.04 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-08 | 2025-04-09 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10560 | Installationfor Wash - Out valves 150 mm. - on pipes with diameter 450 - 630 mm - B4.33 14 19.08 - Z02 - 2 - C - 16 - TS | 1 | 2025-03-29 | 2025-03-30 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10561 | Testing And Commtionningfor Wash - Out valves 150 mm. - on pipes with diameter 450 - 630 mm - B4.33 14 19.08 - Z02 - 2 - | 1 | 2025-03-31 | 2025-04-01 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10570 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - Z02 - 2 - C - 16 - TSE | 1 | 2025-03-30 | 2025-03-31 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10571 | Plain Concrete Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-01 | 2025-04-02 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10572 | INSTALLATIONfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-03 | 2025-04-05 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10573 | Backfilling Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-06 | 2025-04-07 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10586 | EXCAVATION and Bedding Worksfor Wash - out Valve Chamber - 450 to 630 MM - B4.33 14 13.07 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-01 | 2025-04-02 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10587 | Plain Concrete Worksfor Wash - out Valve Chamber - 450 to 630 MM - B4.33 14 13.07 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-03 | 2025-04-05 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10588 | INSTALLATIONfor Wash - out Valve Chamber - 450 to 630 MM - B4.33 14 13.07 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-06 | 2025-04-07 |  |  | FALSE | yes
| JD3RZ02-2C16TSE10589 | Backfilling Worksfor Wash - out Valve Chamber - 450 to 630 MM - B4.33 14 13.07 - Z02 - 2 - C - 16 - TSE | 1 | 2025-04-08 | 2025-04-09 |  |  | FALSE | yes
| JD3RZ02-2L74RD11438 | Supply and installation Traffic signs with Single postfor ROADS - B1.10 14 53.01 - Z02 - 2 - L - 74 - RD | 1 | 2025-05-15 | 2025-05-17 | 2025-10-30 |  | FALSE | FALSE
| JD3RZ02-2L74RD11439 | Supply and installation Traffic signs with Double postfor ROADS - B1.10 14 53.02 - Z02 - 2 - L - 74 - RD | 1 | 2025-05-18 | 2025-05-19 | 2025-11-02 |  | FALSE | FALSE
| JD3RZ02-2L74SS10777 | Backfilling Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z02 - 2 - L - 74 - SS | 1 | 2025-01-02 | 2025-01-04 |  |  | FALSE | yes
| JD3RZ02-2L74SS521431 | Backfilling Works for Manholes 1200 mm - Depth from 3.51 to 4.50 - B5.33 05 13.05 - MR - C - 03 - SS | 1 | 2025-01-05 | 2025-01-06 |  |  | FALSE | yes
| JD3RZ02-2L74ST11045 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z02 - 2 - L - 74 - ST | 1 | 2025-01-09 | 2025-01-11 |  |  | FALSE | yes
| JD3RZ02-2L74ST11060 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z02 - 2 - L - 74 - ST | 1 | 2025-01-12 | 2025-01-13 |  |  | FALSE | yes
| JD3RZ02-2L74ST11078 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - Z02 - 2 - L - 74 - ST | 1 | 2025-01-07 | 2025-01-11 |  |  | FALSE | yes
| JD3RZ02-2L74ST11079 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - Z02 - 2 - L - 74 - ST | 1 | 2025-01-12 | 2025-01-14 |  |  | FALSE | yes
| JD3RZ02-2L74ST11082 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z02 - 2 - L - 74 - ST | 1 | 2025-01-09 | 2025-01-12 |  |  | FALSE | yes
| JD3RZ02-2L74ST11083 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z02 - 2 - L - 74 - ST | 1 | 2025-01-13 | 2025-01-14 |  |  | FALSE | yes
| JD3RZ02-2L74ST524364 | Concrete encasement for pipes - NNB6.33 42 11.25 - Z02 - 2 - L - 74 - ST | 1 | 2025-01-07 | 2025-01-09 |  |  | FALSE | yes
| JD3RZ02-2L74TC11414 | Excavation Worksfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z02 - 2 - L - 74 - TC | 1 | 2025-05-03 | 2025-05-04 | 2025-08-10 |  | FALSE | FALSE
| JD3RZ02-2L74TC11415 | Installationfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z02 - 2 - L - 74 - TC | 1 | 2025-05-05 | 2025-05-10 | 2025-08-16 |  | FALSE | FALSE
| JD3RZ02-2L74TC11416 | Pouring Concrete Coverfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z02 - 2 - L - 74 - | 1 | 2025-05-11 | 2025-05-15 | 2025-08-20 |  | FALSE | FALSE
| JD3RZ02-2L74TC11417 | Backfilling Worksfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z02 - 2 - L - 74 - TC | 1 | 2025-05-17 | 2025-05-18 |  |  | FALSE | yes
| JD3RZ02-2L74TC11418 | Excavation and Bedding Worksfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z02 - 2 - L - 74 - TC | 1 | 2025-05-05 | 2025-05-07 |  |  | FALSE | yes
| JD3RZ02-2L74TC11419 | Installationfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z02 - 2 - L - 74 - TC | 1 | 2025-05-08 | 2025-05-11 |  |  | FALSE | yes
| JD3RZ02-2L74TC11420 | Backfilling Worksfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z02 - 2 - L - 74 - TC | 1 | 2025-05-12 | 2025-05-14 |  |  | FALSE | yes
| JD3RZ02-2L74TSE11265 | Installationfor butterfly valves 400 mm. - B4.33 14 19.04 - Z02 - 2 - L - 74 - TSE | 1 | 2025-02-05 | 2025-02-06 |  |  | FALSE | yes
| JD3RZ02-2L74TSE11266 | Testing And Commtionningfor butterfly valves 400 mm. - B4.33 14 19.04 - Z02 - 2 - L - 74 - TSE | 1 | 2025-02-08 | 2025-02-09 |  |  | FALSE | yes
| JD3RZ02-2L74TSE11267 | Installationfor butterfly valves 600 mm. - B4.33 14 19.05 - Z02 - 2 - L - 74 - TSE | 1 | 2025-02-05 | 2025-02-06 |  |  | FALSE | yes
| JD3RZ02-2L74TSE11268 | Testing And Commtionningfor butterfly valves 600 mm. - B4.33 14 19.05 - Z02 - 2 - L - 74 - TSE | 1 | 2025-02-08 | 2025-02-09 |  |  | FALSE | yes
| JD3RZ02-2L74TSE11283 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - Z02 - 2 - L - 74 - TSE | 1 | 2025-01-09 | 2025-01-11 |  |  | FALSE | yes
| JD3RZ02-2L74TSE11284 | Plain Concrete Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - Z02 - 2 - L - 74 - TSE | 1 | 2025-01-12 | 2025-01-13 |  |  | FALSE | yes
| JD3RZ02-2L74TSE11285 | INSTALLATIONfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - Z02 - 2 - L - 74 - TSE | 1 | 2025-01-14 | 2025-01-15 |  |  | FALSE | yes
| JD3RZ02-2L74TSE11286 | Backfilling Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - Z02 - 2 - L - 74 - TSE | 1 | 2025-01-16 | 2025-01-18 |  |  | FALSE | yes
| JD3RZ02-2L74TSE11287 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 500 to 630 MM - B4.33 14 13.02 - Z02 - 2 - L - 74 - TSE | 1 | 2025-01-12 | 2025-01-13 |  |  | FALSE | yes
| JD3RZ02-2L74TSE11288 | Plain Concrete Worksfor R.C Valve Chamber - 500 to 630 MM - B4.33 14 13.02 - Z02 - 2 - L - 74 - TSE | 1 | 2025-01-14 | 2025-01-15 |  |  | FALSE | yes
| JD3RZ02-2L74TSE11289 | INSTALLATIONfor R.C Valve Chamber - 500 to 630 MM - B4.33 14 13.02 - Z02 - 2 - L - 74 - TSE | 1 | 2025-01-16 | 2025-01-18 |  |  | FALSE | yes
| JD3RZ02-2L74TSE11290 | Backfilling Worksfor R.C Valve Chamber - 500 to 630 MM - B4.33 14 13.02 - Z02 - 2 - L - 74 - TSE | 1 | 2025-01-19 | 2025-01-20 |  |  | FALSE | yes
| JD3RZ02-2L74WT11109 | INSTALLATIONfor gate valves 150 mm - B3.33 14 19.01 - Z02 - 2 - L - 74 - WT | 1 | 2025-01-28 | 2025-01-30 |  |  | FALSE | yes
| JD3RZ02-2L74WT11110 | TESTING AND COMMITIONfor gate valves 150 mm - B3.33 14 19.01 - Z02 - 2 - L - 74 - WT | 1 | 2025-02-01 | 2025-02-03 |  |  | FALSE | yes
| JD3RZ02-2L74WT11119 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z02 - 2 - L - 74 - WT | 1 | 2025-01-23 | 2025-01-25 |  |  | FALSE | yes
| JD3RZ02-2L74WT11120 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z02 - 2 - L - 74 - WT | 1 | 2025-01-26 | 2025-01-27 |  |  | FALSE | yes
| JD3RZ02-2L74WT11121 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z02 - 2 - L - 74 - WT | 1 | 2025-01-28 | 2025-01-29 |  |  | FALSE | yes
| JD3RZ02-2L75RD12151 | Supply and installation Traffic signs with Single postfor ROADS - B1.10 14 53.01 - Z02 - 2 - L - 75 - RD | 1 | 2025-06-12 | 2025-06-14 | 2025-10-30 |  | FALSE | FALSE
| JD3RZ02-2L75ST11576 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 2 - L - 75 - ST | 1 | 2024-12-15 | 2024-12-16 |  |  | FALSE | yes
| JD3RZ02-2L75ST11577 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 2 - L - | 1 | 2024-12-17 | 2024-12-18 |  |  | FALSE | yes
| JD3RZ02-2L75ST11578 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 2 - L - 75 - ST | 1 | 2024-12-19 | 2024-12-21 |  |  | FALSE | yes
| JD3RZ02-2L75ST11579 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 2 - L - 75 - ST | 1 | 2024-12-22 | 2024-12-23 |  |  | FALSE | yes
| JD3RZ02-2L75ST11580 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z02 - 2 - L - 75 - ST | 1 | 2024-12-24 | 2024-12-25 |  |  | FALSE | yes
| JD3RZ02-2L75ST11753 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 0.00 to 1.50 - B6.33 05 39.01 - Z02 - 2 - L - 75 - ST | 1 | 2025-01-07 | 2025-01-08 |  |  | FALSE | yes
| JD3RZ02-2L75ST11758 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z02 - 2 - L - 75 - ST | 1 | 2025-01-09 | 2025-01-11 |  |  | FALSE | yes
| JD3RZ02-2L75ST11773 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z02 - 2 - L - 75 - ST | 1 | 2025-01-12 | 2025-01-13 |  |  | FALSE | yes
| JD3RZ02-2L75ST11793 | EXCAVATION Works for Catchbasine double - B6.33 05 39.10 - Z02 - 2 - L - 75 - ST | 1 | 2025-01-05 | 2025-01-06 |  |  | FALSE | yes
| JD3RZ02-2L75ST11794 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - Z02 - 2 - L - 75 - ST | 1 | 2025-01-07 | 2025-01-08 |  |  | FALSE | yes
| JD3RZ02-2L75ST11795 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z02 - 2 - L - 75 - ST | 1 | 2025-01-09 | 2025-01-11 |  |  | FALSE | yes
| JD3RZ02-2L75ST11796 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z02 - 2 - L - 75 - ST | 1 | 2025-01-12 | 2025-01-13 |  |  | FALSE | yes
| JD3RZ02-2L75TC12127 | Excavation Worksfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z02 - 2 - L - 75 - TC | 1 | 2025-04-20 | 2025-04-22 | 2025-08-10 |  | FALSE | FALSE
| JD3RZ02-2L75TC12128 | Installationfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z02 - 2 - L - 75 - TC | 1 | 2025-04-23 | 2025-04-29 | 2025-08-16 |  | FALSE | FALSE
| JD3RZ02-2L75TC12129 | Pouring Concrete Coverfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z02 - 2 - L - 75 - | 1 | 2025-04-30 | 2025-05-06 | 2025-08-20 |  | FALSE | FALSE
| JD3RZ02-2L75TC12130 | Backfilling Worksfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z02 - 2 - L - 75 - TC | 1 | 2025-05-07 | 2025-05-10 |  |  | FALSE | yes
| JD3RZ02-2L75TC12131 | Excavation and Bedding Worksfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z02 - 2 - L - 75 - TC | 1 | 2025-04-23 | 2025-04-26 | 2025-08-10 |  | FALSE | FALSE
| JD3RZ02-2L75TC12132 | Installationfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z02 - 2 - L - 75 - TC | 1 | 2025-04-27 | 2025-04-29 | 2025-08-16 |  | FALSE | FALSE
| JD3RZ02-2L75TC12133 | Backfilling Worksfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z02 - 2 - L - 75 - TC | 1 | 2025-04-30 | 2025-05-03 | 2025-08-20 |  | FALSE | FALSE
| JD3RZ02-2L75TSE11852 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - 2 - L - 75 - TSE | 1 | 2025-01-14 | 2025-01-15 |  |  | FALSE | yes
| JD3RZ02-2L75TSE11853 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - 2 - L - 75 | 1 | 2025-01-16 | 2025-01-18 |  |  | FALSE | yes
| JD3RZ02-2L75TSE11854 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - 2 - L - 75 - TSE | 1 | 2025-01-19 | 2025-01-20 |  |  | FALSE | yes
| JD3RZ02-2L75TSE11855 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - 2 - L - 75 - TSE | 1 | 2025-01-21 | 2025-01-22 |  |  | FALSE | yes
| JD3RZ02-2L75TSE11856 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - 2 - L - 75 - TSE | 1 | 2025-01-23 | 2025-01-25 |  |  | FALSE | yes
| JD3RZ02-2L75TSE11897 | Excavation Worksfor HDPE Pipes 450 mm - depth from 2.51 to 3.5 m - B4.33 31 00.11 - Z02 - 2 - L - 75 - TSE | 1 | 2025-01-16 | 2025-01-18 |  |  | FALSE | yes
| JD3RZ02-2L75TSE11898 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 2.51 to 3.5 m - B4.33 31 00.11 - Z02 - 2 - L - 75 | 1 | 2025-01-19 | 2025-01-20 |  |  | FALSE | yes
| JD3RZ02-2L75TSE11899 | Installing for HDPE Pipes 450 mm - depth from 2.51 to 3.5 m - B4.33 31 00.11 - Z02 - 2 - L - 75 - TSE | 1 | 2025-01-21 | 2025-01-22 |  |  | FALSE | yes
| JD3RZ02-2L75TSE11900 | Testing for HDPE Pipes 450 mm - depth from 2.51 to 3.5 m - B4.33 31 00.11 - Z02 - 2 - L - 75 - TSE | 1 | 2025-01-23 | 2025-01-25 |  |  | FALSE | yes
| JD3RZ02-2L75TSE11901 | Backfillingfor HDPE Pipes 450 mm - depth from 2.51 to 3.5 m - B4.33 31 00.11 - Z02 - 2 - L - 75 - TSE | 1 | 2025-01-28 | 2025-01-29 |  |  | FALSE | yes
| JD3RZ02-2L75TSE11976 | Installationfor butterfly valves 300 mm. - B4.33 14 19.03 - Z02 - 2 - L - 75 - TSE | 1 | 2025-01-26 | 2025-01-27 |  |  | FALSE | yes
| JD3RZ02-2L75TSE11977 | Testing And Commtionningfor butterfly valves 300 mm. - B4.33 14 19.03 - Z02 - 2 - L - 75 - TSE | 1 | 2025-01-28 | 2025-01-29 |  |  | FALSE | yes
| JD3RZ02-2L75TSE11996 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - Z02 - 2 - L - 75 - TSE | 1 | 2025-01-19 | 2025-01-20 |  |  | FALSE | yes
| JD3RZ02-2L75TSE11997 | Plain Concrete Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - Z02 - 2 - L - 75 - TSE | 1 | 2025-01-21 | 2025-01-22 |  |  | FALSE | yes
| JD3RZ02-2L75TSE11998 | INSTALLATIONfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - Z02 - 2 - L - 75 - TSE | 1 | 2025-01-23 | 2025-01-25 |  |  | FALSE | yes
| JD3RZ02-2L75TSE11999 | Backfilling Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - Z02 - 2 - L - 75 - TSE | 1 | 2025-01-30 | 2025-02-01 |  |  | FALSE | yes
| JD3RZ02-2L75WT11797.R | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z02 - 2 - L - 75 - WT - Remaining | 1 | 2025-01-26 | 2025-01-27 |  |  | FALSE | yes
| JD3RZ02-2L75WT11798.R | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z02 - 2 - L - 75 - W | 1 | 2025-01-29 | 2025-01-30 |  |  | FALSE | yes
| JD3RZ02-2L75WT11799.R | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z02 - 2 - L - 75 - WT - Remaining | 1 | 2025-02-08 | 2025-02-09 |  |  | FALSE | yes
| JD3RZ02-2L75WT11800.R | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z02 - 2 - L - 75 - WT - Remaining | 1 | 2025-02-13 | 2025-02-15 |  |  | FALSE | yes
| JD3RZ02-2L75WT11801.R | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z02 - 2 - L - 75 - WT - Remaining | 1 | 2025-02-19 | 2025-02-20 |  |  | FALSE | yes
| JD3RZ02-2L75WT11802 | Excavation Worksfor HDPE Pipes 225 mm - depth from 0 to 1.5 m - B3.33 14 13.02 - Z02 - 2 - L - 75 - WT | 1 | 2025-02-02 | 2025-02-03 |  |  | FALSE | yes
| JD3RZ02-2L75WT11803 | Soil Replacement and Bedding Works for HDPE Pipes 225 mm - depth from 0 to 1.5 m - B3.33 14 13.02 - Z02 - 2 - L - 75 - W | 1 | 2025-02-04 | 2025-02-05 |  |  | FALSE | yes
| JD3RZ02-2L75WT11804 | Installing for HDPE Pipes 225 mm - depth from 0 to 1.5 m - B3.33 14 13.02 - Z02 - 2 - L - 75 - WT | 1 | 2025-02-06 | 2025-02-08 |  |  | FALSE | yes
| JD3RZ02-2L75WT11805 | Testing for HDPE Pipes 225 mm - depth from 0 to 1.5 m - B3.33 14 13.02 - Z02 - 2 - L - 75 - WT | 1 | 2025-02-09 | 2025-02-10 |  |  | FALSE | yes
| JD3RZ02-2L75WT11806 | Backfillingfor HDPE Pipes 225 mm - depth from 0 to 1.5 m - B3.33 14 13.02 - Z02 - 2 - L - 75 - WT | 1 | 2025-02-13 | 2025-02-15 |  |  | FALSE | yes
| JD3RZ02-2L75WT11822 | INSTALLATIONfor gate valves 150 mm - B3.33 14 19.01 - Z02 - 2 - L - 75 - WT | 1 | 2025-02-09 | 2025-02-10 |  |  | FALSE | yes
| JD3RZ02-2L75WT11823 | TESTING AND COMMITIONfor gate valves 150 mm - B3.33 14 19.01 - Z02 - 2 - L - 75 - WT | 1 | 2025-02-11 | 2025-02-12 |  |  | FALSE | yes
| JD3RZ02-2L75WT11824 | INSTALLATIONfor gate valves 200 mm - B3.33 14 19.02 - Z02 - 2 - L - 75 - WT | 1 | 2025-02-09 | 2025-02-10 |  |  | FALSE | yes
| JD3RZ02-2L75WT11825 | TESTING AND COMMITIONfor gate valves 200 mm - B3.33 14 19.02 - Z02 - 2 - L - 75 - WT | 1 | 2025-02-11 | 2025-02-12 |  |  | FALSE | yes
| JD3RZ02-2L75WT11832 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z02 - 2 - L - 75 - WT | 1 | 2025-02-04 | 2025-02-05 |  |  | FALSE | yes
| JD3RZ02-2L75WT11833 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z02 - 2 - L - 75 - WT | 1 | 2025-02-06 | 2025-02-08 |  |  | FALSE | yes
| JD3RZ02-2L75WT11834 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z02 - 2 - L - 75 - WT | 1 | 2025-02-09 | 2025-02-10 |  |  | FALSE | yes
| JD3RZ02-2RCBST21426.R | Excavation Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z02 - 2 - RCB - ST - Remaini | 1 | 2024-08-26 | 2024-08-27 |  |  | FALSE | yes
| JD3RZ02-2RCBST21427.R | Soil Replacement and Bedding Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z02 - 2 - | 1 | 2024-08-28 | 2024-08-29 |  |  | FALSE | yes
| JD3RZ02-2RCBST21428.R | Installing for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z02 - 2 - RCB - ST - Remaining | 1 | 2024-08-31 | 2024-09-01 |  |  | FALSE | yes
| JD3RZ02-2RCBST21429.R | Primary Test for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z02 - 2 - RCB - ST - Remaining | 1 | 2024-09-02 | 2024-09-03 |  |  | FALSE | yes
| JD3RZ02-2RCBST21430.R | Backfilling Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z02 - 2 - RCB - ST - Remain | 1 | 2024-09-04 | 2024-09-05 |  |  | FALSE | yes
| JD3RZ02-2RCBST21436 | Excavation Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z02 - 2 - RCB - ST | 1 | 2024-12-22 | 2024-12-23 |  |  | FALSE | yes
| JD3RZ02-2RCBST21437 | Soil Replacement and Bedding Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z02 - 2 - R | 1 | 2024-12-24 | 2024-12-25 |  |  | FALSE | yes
| JD3RZ02-2RCBST21438 | Installing for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z02 - 2 - RCB - ST | 1 | 2024-12-26 | 2024-12-28 |  |  | FALSE | yes
| JD3RZ02-2RCBST21439 | Primary Test for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z02 - 2 - RCB - ST | 1 | 2024-12-29 | 2024-12-30 |  |  | FALSE | yes
| JD3RZ02-2RCBST21440 | Backfilling Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z02 - 2 - RCB - ST | 1 | 2025-01-02 | 2025-01-04 |  |  | FALSE | yes
| JD3RZ02-2RCBST21644 | EXCAVATION Works for Catchbasine - B6.33 05 39.09 - single - Z02 - 2 - RCB - ST | 1 | 2024-12-24 | 2024-12-25 |  |  | FALSE | yes
| JD3RZ02-2RCBST21645 | Catchbasine Installation Works for Catchbasine - B6.33 05 39.09 - single - Z02 - 2 - RCB - ST | 1 | 2024-12-26 | 2024-12-28 |  |  | FALSE | yes
| JD3RZ02-2RCBST21646 | FINISHING Works for Catchbasine - B6.33 05 39.09 - single - Z02 - 2 - RCB - ST | 1 | 2024-12-29 | 2024-12-30 |  |  | FALSE | yes
| JD3RZ02-2RCBST21647 | TESTING AND COMMITIONING RELEASED for Catchbasine - B6.33 05 39.09 - single - Z02 - 2 - RCB - ST | 1 | 2024-12-31 | 2025-01-01 |  |  | FALSE | yes
| JD3RZ02-2RCBST21650 | FINISHING Works for Catchbasine - B6.33 05 39.10 - double - Z02 - 2 - RCB - ST | 1 | 2024-12-26 | 2024-12-28 |  |  | FALSE | yes
| JD3RZ02-2RCBST21651 | TESTING AND COMMITIONING RELEASED for Catchbasine - B6.33 05 39.10 - double - Z02 - 2 - RCB - ST | 1 | 2024-12-29 | 2024-12-30 |  |  | FALSE | yes
| JD3RZ02L47SUR01 | Surveying Works L - 47 | 1 |  |  |  |  | yes | FALSE
| JD3RZ02L47TSE4004 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - L - 47 - TSE | 1 | 2025-09-15 | 2025-09-17 |  |  | FALSE | yes
| JD3RZ02L47TSE4005 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - L - 47 - T | 1 | 2025-09-18 | 2025-09-21 |  |  | FALSE | yes
| JD3RZ02L47TSE4006 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - L - 47 - TSE | 1 | 2025-09-22 | 2025-09-27 |  |  | FALSE | yes
| JD3RZ02L47TSE4007 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - L - 47 - TSE | 1 | 2025-09-28 | 2025-09-30 |  |  | FALSE | yes
| JD3RZ02L47TSE4008 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - L - 47 - TSE | 1 | 2025-10-11 | 2025-10-13 |  |  | FALSE | yes
| JD3RZ02L47TSE4009 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - L - 47 - TSE | 1 | 2025-09-18 | 2025-09-22 |  |  | FALSE | yes
| JD3RZ02L47TSE4010 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - L - 47 - T | 1 | 2025-09-23 | 2025-09-27 |  |  | FALSE | yes
| JD3RZ02L47TSE4011 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - L - 47 - TSE | 1 | 2025-09-28 | 2025-10-05 |  |  | FALSE | yes
| JD3RZ02L47TSE4012 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - L - 47 - TSE | 1 | 2025-10-06 | 2025-10-11 |  |  | FALSE | yes
| JD3RZ02L47TSE4013 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - L - 47 - TSE | 1 | 2025-10-12 | 2025-10-16 |  |  | FALSE | yes
| JD3RZ02L47TSE4129 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z02 - L - 47 - TSE | 1 | 2025-10-06 | 2025-10-07 |  |  | FALSE | yes
| JD3RZ02L47TSE4130 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z02 - L - 47 - TSE | 1 | 2025-10-08 | 2025-10-09 |  |  | FALSE | yes
| JD3RZ02L47TSE4131 | Installationfor gate valves 250 mm - B4.33 14 19.02 - Z02 - L - 47 - TSE | 1 | 2025-10-06 | 2025-10-07 |  |  | FALSE | yes
| JD3RZ02L47TSE4132 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - Z02 - L - 47 - TSE | 1 | 2025-10-08 | 2025-10-09 |  |  | FALSE | yes
| JD3RZ02L47TSE4147 | Installationfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - Z02 - L - 47 - TSE | 1 | 2025-10-06 | 2025-10-07 |  |  | FALSE | yes
| JD3RZ02L47TSE4148 | Testing And Commtionningfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - Z02 - L - 47 | 1 | 2025-10-08 | 2025-10-09 |  |  | FALSE | yes
| JD3RZ02L47TSE4177 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z02 - L - 47 - TSE | 1 | 2025-09-23 | 2025-09-24 |  |  | FALSE | yes
| JD3RZ02L47TSE4178 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z02 - L - 47 - TSE | 1 | 2025-09-25 | 2025-09-27 |  |  | FALSE | yes
| JD3RZ02L47TSE4179 | INSTALLATIONfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z02 - L - 47 - TSE | 1 | 2025-09-28 | 2025-09-29 |  |  | FALSE | yes
| JD3RZ02L47TSE4180 | Backfilling Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z02 - L - 47 - TSE | 1 | 2025-10-11 | 2025-10-12 |  |  | FALSE | yes
| JD3RZ02L48SUR01 | Surveying Works L - 48 | 1 |  |  |  |  | yes | FALSE
| JD3RZ02L48TSE4717 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - L - 48 - TSE | 1 | 2025-09-20 | 2025-09-21 |  |  | FALSE | yes
| JD3RZ02L48TSE4718 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - L - 48 - T | 1 | 2025-09-22 | 2025-09-23 |  |  | FALSE | yes
| JD3RZ02L48TSE4719 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - L - 48 - TSE | 1 | 2025-09-24 | 2025-09-27 |  |  | FALSE | yes
| JD3RZ02L48TSE4720 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - L - 48 - TSE | 1 | 2025-09-28 | 2025-09-29 |  |  | FALSE | yes
| JD3RZ02L48TSE4721 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - L - 48 - TSE | 1 | 2025-09-30 | 2025-10-01 |  |  | FALSE | yes
| JD3RZ02L48TSE4842 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z02 - L - 48 - TSE | 1 | 2025-09-24 | 2025-09-25 |  |  | FALSE | yes
| JD3RZ02L48TSE4843 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z02 - L - 48 - TSE | 1 | 2025-09-27 | 2025-09-28 |  |  | FALSE | yes
| JD3RZ02L49TSE5433 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - L - 49 - TSE | 1 | 2025-09-30 | 2025-10-02 |  |  | FALSE | yes
| JD3RZ02L49TSE5434 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - L - 49 - TSE | 1 | 2025-10-04 | 2025-10-06 |  |  | FALSE | yes
| JD3RZ02L49TSE5555 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z02 - L - 49 - TSE | 1 | 2025-09-25 | 2025-09-27 | 2025-10-09 |  | FALSE | FALSE
| JD3RZ02L49TSE5556 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z02 - L - 49 - TSE | 1 | 2025-09-28 | 2025-09-29 |  |  | FALSE | yes
| JD3RZ02L50SUR01 | Surveying Works L - 50 | 1 |  |  |  |  | yes | FALSE
| JD3RZ02L50TSE6143 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - L - 50 - TSE | 1 | 2025-09-20 | 2025-09-22 |  |  | FALSE | yes
| JD3RZ02L50TSE6144 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - L - 50 - T | 1 | 2025-09-23 | 2025-09-25 |  |  | FALSE | yes
| JD3RZ02L50TSE6145 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - L - 50 - TSE | 1 | 2025-09-27 | 2025-10-01 |  |  | FALSE | yes
| JD3RZ02L50TSE6146 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - L - 50 - TSE | 1 | 2025-10-02 | 2025-10-05 |  |  | FALSE | yes
| JD3RZ02L50TSE6147 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z02 - L - 50 - TSE | 1 | 2025-10-07 | 2025-10-09 |  |  | FALSE | yes
| JD3RZ02L50TSE6148 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - L - 50 - TSE | 1 | 2025-09-23 | 2025-09-24 |  |  | FALSE | yes
| JD3RZ02L50TSE6149 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - L - 50 - T | 1 | 2025-09-25 | 2025-09-27 |  |  | FALSE | yes
| JD3RZ02L50TSE6150 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - L - 50 - TSE | 1 | 2025-09-28 | 2025-09-29 |  |  | FALSE | yes
| JD3RZ02L50TSE6151 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - L - 50 - TSE | 1 | 2025-09-30 | 2025-10-01 |  |  | FALSE | yes
| JD3RZ02L50TSE6152 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z02 - L - 50 - TSE | 1 | 2025-10-07 | 2025-10-08 |  |  | FALSE | yes
| JD3RZ02L50TSE6268 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z02 - L - 50 - TSE | 1 | 2025-10-02 | 2025-10-04 |  |  | FALSE | yes
| JD3RZ02L50TSE6269 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z02 - L - 50 - TSE | 1 | 2025-10-05 | 2025-10-06 |  |  | FALSE | yes
| JD3RZ02L50TSE6270 | Installationfor gate valves 250 mm - B4.33 14 19.02 - Z02 - L - 50 - TSE | 1 | 2025-10-02 | 2025-10-04 |  |  | FALSE | yes
| JD3RZ02L50TSE6271 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - Z02 - L - 50 - TSE | 1 | 2025-10-05 | 2025-10-06 |  |  | FALSE | yes
| JD3RZ02RCBST21200 | Excavation Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z02 - RCB - ST | 1 | 2025-09-11 | 2025-09-16 |  |  | FALSE | yes
| JD3RZ02RCBST21201 | Soil Replacement and Bedding Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z02 - RCB | 1 | 2025-09-17 | 2025-09-23 |  |  | FALSE | yes
| JD3RZ02RCBST21202 | Installing for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z02 - RCB - ST | 1 | 2025-09-24 | 2025-10-01 |  |  | FALSE | yes
| JD3RZ02RCBST21203 | Primary Test for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z02 - RCB - ST | 1 | 2025-10-02 | 2025-10-09 |  |  | FALSE | yes
| JD3RZ02RCBST21204 | Backfilling Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z02 - RCB - ST | 1 | 2025-10-11 | 2025-10-20 |  |  | FALSE | yes
| JD3RZ02RCBST21210 | Excavation Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z02 - RCB - ST | 1 | 2025-09-17 | 2025-09-22 |  |  | FALSE | yes
| JD3RZ02RCBST21211 | Soil Replacement and Bedding Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z02 - RCB - | 1 | 2025-09-23 | 2025-09-28 |  |  | FALSE | yes
| JD3RZ02RCBST21212 | Installing for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z02 - RCB - ST | 1 | 2025-09-29 | 2025-10-05 |  |  | FALSE | yes
| JD3RZ02RCBST21213 | Primary Test for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z02 - RCB - ST | 1 | 2025-10-06 | 2025-10-11 |  |  | FALSE | yes
| JD3RZ02RCBST21214 | Backfilling Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z02 - RCB - ST | 1 | 2025-10-12 | 2025-10-19 |  |  | FALSE | yes
| JD3RZ02RCBST21418 | EXCAVATION Works for Catchbasine - B6.33 05 39.09 - single - Z02 - RCB - ST | 1 | 2025-09-17 | 2025-09-25 |  |  | FALSE | yes
| JD3RZ02RCBST21419 | Catchbasine Installation Works for Catchbasine - B6.33 05 39.09 - single - Z02 - RCB - ST | 1 | 2025-09-27 | 2025-10-09 |  |  | FALSE | yes
| JD3RZ02RCBST21420 | FINISHING Works for Catchbasine - B6.33 05 39.09 - single - Z02 - RCB - ST | 1 | 2025-10-11 | 2025-10-23 |  |  | FALSE | yes
| JD3RZ02RCBST21421 | TESTING AND COMMITIONING RELEASED for Catchbasine - B6.33 05 39.09 - single - Z02 - RCB - ST | 1 | 2025-10-25 | 2025-11-02 |  |  | FALSE | yes
| JD3RZ02RCBST21422 | EXCAVATION Works for Catchbasine - B6.33 05 39.10 - double - Z02 - RCB - ST | 1 | 2025-09-17 | 2025-09-21 |  |  | FALSE | yes
| JD3RZ02RCBST21423 | Catchbasine Installation Works for Catchbasine - B6.33 05 39.10 - double - Z02 - RCB - ST | 1 | 2025-09-22 | 2025-09-28 |  |  | FALSE | yes
| JD3RZ02RCBST21424 | FINISHING Works for Catchbasine - B6.33 05 39.10 - double - Z02 - RCB - ST | 1 | 2025-09-29 | 2025-10-05 |  |  | FALSE | yes
| JD3RZ02RCBST21425 | TESTING AND COMMITIONING RELEASED for Catchbasine - B6.33 05 39.10 - double - Z02 - RCB - ST | 1 | 2025-10-06 | 2025-10-09 |  |  | FALSE | yes
| JD3RZ03L12SUR01 | Surveying Works L - 12 | 1 |  |  |  |  | yes | FALSE
| JD3RZ03L12TSE12560 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z03 - L - 12 - TSE | 1 | 2025-11-26 | 2025-11-27 |  |  | FALSE | yes
| JD3RZ03L12TSE12561 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z03 - L - 12 - T | 1 | 2025-11-29 | 2025-11-30 |  |  | FALSE | yes
| JD3RZ03L12TSE12562 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z03 - L - 12 - TSE | 1 | 2025-12-01 | 2025-12-02 |  |  | FALSE | yes
| JD3RZ03L12TSE12563 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z03 - L - 12 - TSE | 1 | 2025-12-03 | 2025-12-04 |  |  | FALSE | yes
| JD3RZ03L12TSE12564 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z03 - L - 12 - TSE | 1 | 2025-12-23 | 2025-12-24 |  |  | FALSE | yes
| JD3RZ03L12TSE12565 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z03 - L - 12 - TSE | 1 | 2025-11-29 | 2025-12-02 | 2025-10-23 |  | FALSE | yes
| JD3RZ03L12TSE12566 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z03 - L - 12 - T | 1 | 2025-12-03 | 2025-12-08 | 2025-10-25 |  | FALSE | yes
| JD3RZ03L12TSE12567 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z03 - L - 12 - TSE | 1 | 2025-12-09 | 2025-12-17 | 2025-10-27 |  | FALSE | yes
| JD3RZ03L12TSE12568 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z03 - L - 12 - TSE | 1 | 2025-12-18 | 2025-12-24 |  |  | FALSE | yes
| JD3RZ03L12TSE12569 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z03 - L - 12 - TSE | 1 | 2025-12-25 | 2025-12-31 |  |  | FALSE | yes
| JD3RZ03L12TSE12685 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z03 - L - 12 - TSE | 1 | 2025-12-18 | 2025-12-20 |  |  | FALSE | yes
| JD3RZ03L12TSE12686 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z03 - L - 12 - TSE | 1 | 2025-12-21 | 2025-12-22 |  |  | FALSE | yes
| JD3RZ03L12TSE12687 | Installationfor gate valves 250 mm - B4.33 14 19.02 - Z03 - L - 12 - TSE | 1 | 2025-12-18 | 2025-12-20 |  |  | FALSE | yes
| JD3RZ03L12TSE12688 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - Z03 - L - 12 - TSE | 1 | 2025-12-21 | 2025-12-22 |  |  | FALSE | yes
| JD3RZ03L12TSE12703 | Installationfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - Z03 - L - 12 - TSE | 1 | 2025-12-18 | 2025-12-20 |  |  | FALSE | yes
| JD3RZ03L12TSE12704 | Testing And Commtionningfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - Z03 - L - 12 | 1 | 2025-12-21 | 2025-12-22 |  |  | FALSE | yes
| JD3RZ03L12TSE12733 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z03 - L - 12 - TSE | 1 | 2025-12-03 | 2025-12-04 |  |  | FALSE | yes
| JD3RZ03L12TSE12734 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z03 - L - 12 - TSE | 1 | 2025-12-06 | 2025-12-07 |  |  | FALSE | yes
| JD3RZ03L12TSE12735 | INSTALLATIONfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z03 - L - 12 - TSE | 1 | 2025-12-08 | 2025-12-09 |  |  | FALSE | yes
| JD3RZ03L12TSE12736 | Backfilling Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z03 - L - 12 - TSE | 1 | 2025-12-23 | 2025-12-24 |  |  | FALSE | yes
| JD3RZ03L13TSE13273.R | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z03 - L - 13 - TSE - Remaining | 1 | 2025-12-04 | 2025-12-06 | 2025-08-26 |  | FALSE | yes
| JD3RZ03L13TSE13274.R | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z03 - L - 13 - T | 1 | 2025-12-10 | 2025-12-11 | 2025-08-20 |  | FALSE | yes
| JD3RZ03L13TSE13275 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z03 - L - 13 - TSE | 1 | 2025-12-13 | 2025-12-22 | 2025-08-23 |  | FALSE | yes
| JD3RZ03L13TSE13276 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z03 - L - 13 - TSE | 1 | 2025-12-23 | 2025-12-29 |  |  | FALSE | yes
| JD3RZ03L13TSE13277 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z03 - L - 13 - TSE | 1 | 2025-12-30 | 2026-01-05 | 2025-08-26 |  | FALSE | yes
| JD3RZ03L13TSE13278 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z03 - L - 13 - TSE | 1 | 2025-12-07 | 2025-12-08 |  |  | FALSE | yes
| JD3RZ03L13TSE13279 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z03 - L - 13 - T | 1 | 2025-12-09 | 2025-12-10 |  |  | FALSE | yes
| JD3RZ03L13TSE13280 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z03 - L - 13 - TSE | 1 | 2025-12-11 | 2025-12-13 |  |  | FALSE | yes
| JD3RZ03L13TSE13281 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z03 - L - 13 - TSE | 1 | 2025-12-14 | 2025-12-15 |  |  | FALSE | yes
| JD3RZ03L13TSE13282 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z03 - L - 13 - TSE | 1 | 2025-12-28 | 2025-12-29 |  |  | FALSE | yes
| JD3RZ03L13TSE13283 | Excavation Worksfor HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - Z03 - L - 13 - TSE | 1 | 2025-12-09 | 2025-12-10 |  |  | FALSE | yes
| JD3RZ03L13TSE13284 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - Z03 - L - 13 - TSE | 1 | 2025-12-11 | 2025-12-13 |  |  | FALSE | yes
| JD3RZ03L13TSE13285 | Installing for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - Z03 - L - 13 - TSE | 1 | 2025-12-14 | 2025-12-15 |  |  | FALSE | yes
| JD3RZ03L13TSE13286 | Testing for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - Z03 - L - 13 - TSE | 1 | 2025-12-16 | 2025-12-17 |  |  | FALSE | yes
| JD3RZ03L13TSE13287 | Backfillingfor HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - Z03 - L - 13 - TSE | 1 | 2025-12-18 | 2025-12-20 |  |  | FALSE | yes
| JD3RZ03L13TSE13398 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z03 - L - 13 - TSE | 1 | 2025-12-23 | 2025-12-24 |  |  | FALSE | yes
| JD3RZ03L13TSE13399 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z03 - L - 13 - TSE | 1 | 2025-12-25 | 2025-12-27 |  |  | FALSE | yes
| JD3RZ03L14TSE13986.R | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z03 - L - 14 - TSE - Remaining | 1 | 2025-12-09 | 2025-12-10 | 2025-08-26 |  | FALSE | yes
| JD3RZ03L14TSE13987.R | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z03 - L - 14 - T | 1 | 2025-12-14 | 2025-12-15 | 2025-08-27 |  | FALSE | yes
| JD3RZ03L14TSE13988.R | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z03 - L - 14 - TSE - Remaining | 1 | 2025-12-22 | 2025-12-23 | 2025-08-30 |  | FALSE | yes
| JD3RZ03L14TSE13989 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z03 - L - 14 - TSE | 1 | 2025-12-24 | 2025-12-29 | 2025-08-31 |  | FALSE | yes
| JD3RZ03L14TSE13990 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z03 - L - 14 - TSE | 1 | 2025-12-30 | 2026-01-04 | 2025-09-09 |  | FALSE | yes
| JD3RZ03L14TSE14111 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z03 - L - 14 - TSE | 1 | 2025-12-24 | 2025-12-25 |  |  | FALSE | yes
| JD3RZ03L14TSE14112 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z03 - L - 14 - TSE | 1 | 2025-12-24 | 2025-12-25 |  |  | FALSE | yes
| JD3RZ03L15TSE14824 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z03 - L - 15 - TSE | 1 | 2025-12-18 | 2025-12-20 |  |  | FALSE | yes
| JD3RZ03L15TSE14825 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z03 - L - 15 - TSE | 1 | 2025-12-21 | 2025-12-22 |  |  | FALSE | yes
| JD3RZ03L16TSE15412 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z03 - L - 16 - TSE | 1 | 2025-11-29 | 2025-12-01 |  |  | FALSE | yes
| JD3RZ03L16TSE15413 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z03 - L - 16 - T | 1 | 2025-12-02 | 2025-12-04 |  |  | FALSE | yes
| JD3RZ03L16TSE15414 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z03 - L - 16 - TSE | 1 | 2025-12-06 | 2025-12-10 |  |  | FALSE | yes
| JD3RZ03L16TSE15415 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z03 - L - 16 - TSE | 1 | 2025-12-11 | 2025-12-15 |  |  | FALSE | yes
| JD3RZ03L16TSE15416 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z03 - L - 16 - TSE | 1 | 2025-12-28 | 2025-12-31 |  |  | FALSE | yes
| JD3RZ03L16TSE15421 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z03 - L - 16 - TSE | 1 | 2025-12-29 | 2026-01-03 | 2025-10-16 |  | FALSE | yes
| JD3RZ03L16TSE15537 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z03 - L - 16 - TSE | 1 | 2025-12-23 | 2025-12-24 |  |  | FALSE | yes
| JD3RZ03L16TSE15538 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z03 - L - 16 - TSE | 1 | 2025-12-25 | 2025-12-27 |  |  | FALSE | yes
| JD3RZ03L16TSE15539 | Installationfor gate valves 250 mm - B4.33 14 19.02 - Z03 - L - 16 - TSE | 1 | 2025-12-23 | 2025-12-24 |  |  | FALSE | yes
| JD3RZ03L16TSE15540 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - Z03 - L - 16 - TSE | 1 | 2025-12-25 | 2025-12-27 |  |  | FALSE | yes
| JD3RZ04L38TSE16838 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z04 - L - 38 - TSE | 1 | 2026-05-26 | 2026-05-27 |  |  | FALSE | yes
| JD3RZ04L38TSE16839 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z04 - L - 38 - T | 1 | 2026-05-28 | 2026-05-30 |  |  | FALSE | yes
| JD3RZ04L38TSE16840 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z04 - L - 38 - TSE | 1 | 2026-05-31 | 2026-06-01 |  |  | FALSE | yes
| JD3RZ04L38TSE16841 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z04 - L - 38 - TSE | 1 | 2026-06-02 | 2026-06-03 |  |  | FALSE | yes
| JD3RZ04L38TSE16842 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z04 - L - 38 - TSE | 1 | 2026-06-14 | 2026-06-15 |  |  | FALSE | yes
| JD3RZ04L38TSE16963 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z04 - L - 38 - TSE | 1 | 2026-06-09 | 2026-06-10 |  |  | FALSE | yes
| JD3RZ04L38TSE16964 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z04 - L - 38 - TSE | 1 | 2026-06-11 | 2026-06-13 |  |  | FALSE | yes
| JD3RZ04L38TSE16965 | Installationfor gate valves 250 mm - B4.33 14 19.02 - Z04 - L - 38 - TSE | 1 | 2026-06-09 | 2026-06-10 |  |  | FALSE | yes
| JD3RZ04L38TSE16966 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - Z04 - L - 38 - TSE | 1 | 2026-06-11 | 2026-06-13 |  |  | FALSE | yes
| JD3RZ04L39TSE17676 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z04 - L - 39 - TSE | 1 | 2026-05-11 | 2026-05-12 |  |  | FALSE | yes
| JD3RZ04L39TSE17677 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z04 - L - 39 - TSE | 1 | 2026-05-13 | 2026-05-14 |  |  | FALSE | yes
| JD3RZ04L40TSE18264 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z04 - L - 40 - TSE | 1 | 2026-05-02 | 2026-05-04 |  |  | FALSE | yes
| JD3RZ04L40TSE18265 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z04 - L - 40 - T | 1 | 2026-05-05 | 2026-05-09 |  |  | FALSE | yes
| JD3RZ04L40TSE18266 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z04 - L - 40 - TSE | 1 | 2026-05-10 | 2026-05-16 |  |  | FALSE | yes
| JD3RZ04L40TSE18267 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z04 - L - 40 - TSE | 1 | 2026-05-17 | 2026-05-20 |  |  | FALSE | yes
| JD3RZ04L40TSE18268 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z04 - L - 40 - TSE | 1 | 2026-05-21 | 2026-05-25 |  |  | FALSE | yes
| JD3RZ04L40TSE18389 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z04 - L - 40 - TSE | 1 | 2026-05-17 | 2026-05-18 |  |  | FALSE | yes
| JD3RZ04L40TSE18390 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z04 - L - 40 - TSE | 1 | 2026-05-19 | 2026-05-20 |  |  | FALSE | yes
| JD3RZ04L41TSE18977.R | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z04 - L - 41 - TSE - Remaining | 1 | 2026-05-13 | 2026-05-14 | 2025-08-27 |  | FALSE | yes
| JD3RZ04L41TSE18978.R | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z04 - L - 41 - T | 1 | 2026-05-17 | 2026-05-18 | 2025-08-30 |  | FALSE | yes
| JD3RZ04L41TSE18979.R | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z04 - L - 41 - TSE - Remaining | 1 | 2026-05-23 | 2026-05-24 | 2025-08-31 |  | FALSE | yes
| JD3RZ04L41TSE18980 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z04 - L - 41 - TSE | 1 | 2026-05-27 | 2026-05-31 | 2025-08-30 |  | FALSE | yes
| JD3RZ04L41TSE18981 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z04 - L - 41 - TSE | 1 | 2026-06-01 | 2026-06-04 | 2025-08-31 |  | FALSE | yes
| JD3RZ04L41TSE19102 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z04 - L - 41 - TSE | 1 | 2026-05-25 | 2026-05-26 |  |  | FALSE | yes
| JD3RZ04L41TSE19103 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z04 - L - 41 - TSE | 1 | 2026-05-27 | 2026-05-28 |  |  | FALSE | yes
| JD3RZ04RCBST21878 | Excavation Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z04 - RCB - ST | 1 | 2026-04-15 | 2026-04-16 |  |  | FALSE | yes
| JD3RZ04RCBST21879 | Soil Replacement and Bedding Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z04 - RCB | 1 | 2026-04-18 | 2026-04-19 |  |  | FALSE | yes
| JD3RZ04RCBST21880 | Installing for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z04 - RCB - ST | 1 | 2026-04-20 | 2026-04-22 |  |  | FALSE | yes
| JD3RZ04RCBST21881 | Primary Test for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z04 - RCB - ST | 1 | 2026-04-23 | 2026-04-26 |  |  | FALSE | yes
| JD3RZ04RCBST21882 | Backfilling Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z04 - RCB - ST | 1 | 2026-04-27 | 2026-04-30 |  |  | FALSE | yes
| JD3RZ04RCBST21888 | Excavation Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z04 - RCB - ST | 1 | 2026-04-18 | 2026-04-19 |  |  | FALSE | yes
| JD3RZ04RCBST21889 | Soil Replacement and Bedding Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z04 - RCB - | 1 | 2026-04-20 | 2026-04-21 |  |  | FALSE | yes
| JD3RZ04RCBST21890 | Installing for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z04 - RCB - ST | 1 | 2026-04-22 | 2026-04-25 |  |  | FALSE | yes
| JD3RZ04RCBST21891 | Primary Test for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z04 - RCB - ST | 1 | 2026-04-26 | 2026-04-27 |  |  | FALSE | yes
| JD3RZ04RCBST21892 | Backfilling Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z04 - RCB - ST | 1 | 2026-04-28 | 2026-04-30 |  |  | FALSE | yes
| JD3RZ04RCBST22096 | EXCAVATION Works for Catchbasine - B6.33 05 39.09 - single - Z04 - RCB - ST | 1 | 2026-04-20 | 2026-04-22 |  |  | FALSE | yes
| JD3RZ04RCBST22097 | Catchbasine Installation Works for Catchbasine - B6.33 05 39.09 - single - Z04 - RCB - ST | 1 | 2026-04-23 | 2026-04-28 |  |  | FALSE | yes
| JD3RZ04RCBST22098 | FINISHING Works for Catchbasine - B6.33 05 39.09 - single - Z04 - RCB - ST | 1 | 2026-04-29 | 2026-05-04 |  |  | FALSE | yes
| JD3RZ04RCBST22099 | TESTING AND COMMITIONING RELEASED for Catchbasine - B6.33 05 39.09 - single - Z04 - RCB - ST | 1 | 2026-05-05 | 2026-05-07 |  |  | FALSE | yes
| JD3RZ04RCBST22100 | EXCAVATION Works for Catchbasine - B6.33 05 39.10 - double - Z04 - RCB - ST | 1 | 2026-04-23 | 2026-04-25 |  |  | FALSE | yes
| JD3RZ04RCBST22101 | Catchbasine Installation Works for Catchbasine - B6.33 05 39.10 - double - Z04 - RCB - ST | 1 | 2026-04-26 | 2026-04-28 |  |  | FALSE | yes
| JD3RZ04RCBST22102 | FINISHING Works for Catchbasine - B6.33 05 39.10 - double - Z04 - RCB - ST | 1 | 2026-04-29 | 2026-05-02 |  |  | FALSE | yes
| JD3RZ04RCBST22103 | TESTING AND COMMITIONING RELEASED for Catchbasine - B6.33 05 39.10 - double - Z04 - RCB - ST | 1 | 2026-05-03 | 2026-05-04 |  |  | FALSE | yes
| JD3RZ05L04SUR01 | Surveying Works L - 04 | 1 |  |  |  |  | yes | FALSE
| JD3RZ05L04TSE19690 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z05 - L - 04 - TSE | 1 | 2025-09-20 | 2025-09-21 |  |  | FALSE | yes
| JD3RZ05L04TSE19691 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z05 - L - 04 - T | 1 | 2025-09-22 | 2025-09-23 |  |  | FALSE | yes
| JD3RZ05L04TSE19692 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z05 - L - 04 - TSE | 1 | 2025-09-24 | 2025-09-25 |  |  | FALSE | yes
| JD3RZ05L04TSE19693 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z05 - L - 04 - TSE | 1 | 2025-09-27 | 2025-09-28 |  |  | FALSE | yes
| JD3RZ05L04TSE19694 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z05 - L - 04 - TSE | 1 | 2025-10-14 | 2025-10-15 |  |  | FALSE | yes
| JD3RZ05L04TSE19698 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z05 - L - 04 - TSE | 1 | 2025-10-09 | 2025-10-14 |  |  | FALSE | yes
| JD3RZ05L04TSE19699 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z05 - L - 04 - TSE | 1 | 2025-10-15 | 2025-10-20 |  |  | FALSE | yes
| JD3RZ05L04TSE19815 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z05 - L - 04 - TSE | 1 | 2025-10-09 | 2025-10-11 |  |  | FALSE | yes
| JD3RZ05L04TSE19816 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z05 - L - 04 - TSE | 1 | 2025-10-12 | 2025-10-13 |  |  | FALSE | yes
| JD3RZ05L04TSE19817 | Installationfor gate valves 250 mm - B4.33 14 19.02 - Z05 - L - 04 - TSE | 1 | 2025-09-27 | 2025-09-28 |  |  | FALSE | yes
| JD3RZ05L04TSE19818 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - Z05 - L - 04 - TSE | 1 | 2025-09-29 | 2025-09-30 |  |  | FALSE | yes
| JD3RZ05L05SUR01 | Surveying Works L - 05 | 1 |  |  |  |  | yes | FALSE
| JD3RZ05L05TSE20403 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z05 - L - 05 - TSE | 1 | 2025-09-20 | 2025-09-24 |  |  | FALSE | yes
| JD3RZ05L05TSE20404 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z05 - L - 05 - T | 1 | 2025-09-25 | 2025-09-30 |  |  | FALSE | yes
| JD3RZ05L05TSE20405 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z05 - L - 05 - TSE | 1 | 2025-10-01 | 2025-10-11 |  |  | FALSE | yes
| JD3RZ05L05TSE20406 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z05 - L - 05 - TSE | 1 | 2025-10-12 | 2025-10-18 |  |  | FALSE | yes
| JD3RZ05L05TSE20407 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z05 - L - 05 - TSE | 1 | 2025-10-19 | 2025-10-25 |  |  | FALSE | yes
| JD3RZ05L05TSE20528 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z05 - L - 05 - TSE | 1 | 2025-10-12 | 2025-10-13 |  |  | FALSE | yes
| JD3RZ05L05TSE20529 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z05 - L - 05 - TSE | 1 | 2025-10-14 | 2025-10-15 |  |  | FALSE | yes
| JD3RZ05L06SUR01 | Surveying Works L - 06 | 1 |  |  |  |  | yes | FALSE
| JD3RZ05L06TSE21116 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z05 - L - 06 - TSE | 1 | 2025-09-20 | 2025-09-24 |  |  | FALSE | yes
| JD3RZ05L06TSE21117 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z05 - L - 06 - T | 1 | 2025-09-25 | 2025-09-30 |  |  | FALSE | yes
| JD3RZ05L06TSE21118 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z05 - L - 06 - TSE | 1 | 2025-10-01 | 2025-10-11 |  |  | FALSE | yes
| JD3RZ05L06TSE21119 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z05 - L - 06 - TSE | 1 | 2025-10-12 | 2025-10-18 |  |  | FALSE | yes
| JD3RZ05L06TSE21120 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z05 - L - 06 - TSE | 1 | 2025-10-19 | 2025-10-25 |  |  | FALSE | yes
| JD3RZ05L06TSE21241 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z05 - L - 06 - TSE | 1 | 2025-10-12 | 2025-10-13 |  |  | FALSE | yes
| JD3RZ05L06TSE21242 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z05 - L - 06 - TSE | 1 | 2025-10-14 | 2025-10-15 |  |  | FALSE | yes
| JD3RZ05L07SUR01 | Surveying Works L - 07 | 1 |  |  |  |  | yes | FALSE
| JD3RZ05L07TSE21829 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z05 - L - 07 - TSE | 1 | 2025-09-20 | 2025-09-21 |  |  | FALSE | yes
| JD3RZ05L07TSE21830 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z05 - L - 07 - T | 1 | 2025-09-22 | 2025-09-23 |  |  | FALSE | yes
| JD3RZ05L07TSE21831 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z05 - L - 07 - TSE | 1 | 2025-09-24 | 2025-09-25 |  |  | FALSE | yes
| JD3RZ05L07TSE21832 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z05 - L - 07 - TSE | 1 | 2025-09-27 | 2025-09-28 |  |  | FALSE | yes
| JD3RZ05L07TSE21833 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z05 - L - 07 - TSE | 1 | 2025-10-19 | 2025-10-20 |  |  | FALSE | yes
| JD3RZ05L07TSE21834 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z05 - L - 07 - TSE | 1 | 2025-09-22 | 2025-09-27 |  |  | FALSE | yes
| JD3RZ05L07TSE21835 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z05 - L - 07 - T | 1 | 2025-09-28 | 2025-10-02 |  |  | FALSE | yes
| JD3RZ05L07TSE21836 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z05 - L - 07 - TSE | 1 | 2025-10-04 | 2025-10-13 |  |  | FALSE | yes
| JD3RZ05L07TSE21837 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z05 - L - 07 - TSE | 1 | 2025-10-14 | 2025-10-20 |  |  | FALSE | yes
| JD3RZ05L07TSE21838 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z05 - L - 07 - TSE | 1 | 2025-10-21 | 2025-10-27 |  |  | FALSE | yes
| JD3RZ05L07TSE21954 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z05 - L - 07 - TSE | 1 | 2025-10-14 | 2025-10-15 |  |  | FALSE | yes
| JD3RZ05L07TSE21955 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z05 - L - 07 - TSE | 1 | 2025-10-16 | 2025-10-18 |  |  | FALSE | yes
| JD3RZ05L07TSE21956 | Installationfor gate valves 250 mm - B4.33 14 19.02 - Z05 - L - 07 - TSE | 1 | 2025-09-27 | 2025-09-28 |  |  | FALSE | yes
| JD3RZ05L07TSE21957 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - Z05 - L - 07 - TSE | 1 | 2025-09-29 | 2025-09-30 |  |  | FALSE | yes
| JD3RZ05L07TSE21972 | Installationfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - Z05 - L - 07 - TSE | 1 | 2025-10-14 | 2025-10-15 |  |  | FALSE | yes
| JD3RZ05L07TSE21973 | Testing And Commtionningfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - Z05 - L - 07 | 1 | 2025-10-16 | 2025-10-18 |  |  | FALSE | yes
| JD3RZ05L07TSE22002 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z05 - L - 07 - TSE | 1 | 2025-09-28 | 2025-09-29 |  |  | FALSE | yes
| JD3RZ05L07TSE22003 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z05 - L - 07 - TSE | 1 | 2025-09-30 | 2025-10-01 |  |  | FALSE | yes
| JD3RZ05L07TSE22004 | INSTALLATIONfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z05 - L - 07 - TSE | 1 | 2025-10-02 | 2025-10-04 |  |  | FALSE | yes
| JD3RZ05L07TSE22005 | Backfilling Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z05 - L - 07 - TSE | 1 | 2025-10-05 | 2025-10-06 |  |  | FALSE | yes
| JD3RZ05RCBST20974 | Excavation Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z05 - RCB - ST | 1 | 2025-09-11 | 2025-09-17 |  |  | FALSE | yes
| JD3RZ05RCBST20975 | Soil Replacement and Bedding Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z05 - RCB | 1 | 2025-09-18 | 2025-09-25 |  |  | FALSE | yes
| JD3RZ05RCBST20976 | Installing for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z05 - RCB - ST | 1 | 2025-09-27 | 2025-10-06 |  |  | FALSE | yes
| JD3RZ05RCBST20977 | Primary Test for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z05 - RCB - ST | 1 | 2025-10-07 | 2025-10-16 |  |  | FALSE | yes
| JD3RZ05RCBST20978 | Backfilling Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z05 - RCB - ST | 1 | 2025-10-18 | 2025-10-30 |  |  | FALSE | yes
| JD3RZ05RCBST20984 | Excavation Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z05 - RCB - ST | 1 | 2025-09-18 | 2025-09-24 |  |  | FALSE | yes
| JD3RZ05RCBST20985 | Soil Replacement and Bedding Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z05 - RCB - | 1 | 2025-09-25 | 2025-10-01 |  |  | FALSE | yes
| JD3RZ05RCBST20986 | Installing for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z05 - RCB - ST | 1 | 2025-10-02 | 2025-10-09 |  |  | FALSE | yes
| JD3RZ05RCBST20987 | Primary Test for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z05 - RCB - ST | 1 | 2025-10-11 | 2025-10-16 |  |  | FALSE | yes
| JD3RZ05RCBST20988 | Backfilling Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z05 - RCB - ST | 1 | 2025-10-18 | 2025-10-27 |  |  | FALSE | yes
| JD3RZ05RCBST21192 | EXCAVATION Works for Catchbasine - B6.33 05 39.09 - single - Z05 - RCB - ST | 1 | 2025-09-25 | 2025-10-06 |  |  | FALSE | yes
| JD3RZ05RCBST21193 | Catchbasine Installation Works for Catchbasine - B6.33 05 39.09 - single - Z05 - RCB - ST | 1 | 2025-10-07 | 2025-10-22 |  |  | FALSE | yes
| JD3RZ05RCBST21194 | FINISHING Works for Catchbasine - B6.33 05 39.09 - single - Z05 - RCB - ST | 1 | 2025-10-23 | 2025-11-08 |  |  | FALSE | yes
| JD3RZ05RCBST21195 | TESTING AND COMMITIONING RELEASED for Catchbasine - B6.33 05 39.09 - single - Z05 - RCB - ST | 1 | 2025-11-09 | 2025-11-19 |  |  | FALSE | yes
| JD3RZ05RCBST21196 | EXCAVATION Works for Catchbasine - B6.33 05 39.10 - double - Z05 - RCB - ST | 1 | 2025-10-07 | 2025-10-12 |  |  | FALSE | yes
| JD3RZ05RCBST21197 | Catchbasine Installation Works for Catchbasine - B6.33 05 39.10 - double - Z05 - RCB - ST | 1 | 2025-10-13 | 2025-10-20 |  |  | FALSE | yes
| JD3RZ05RCBST21198 | FINISHING Works for Catchbasine - B6.33 05 39.10 - double - Z05 - RCB - ST | 1 | 2025-10-21 | 2025-10-28 |  |  | FALSE | yes
| JD3RZ05RCBST21199 | TESTING AND COMMITIONING RELEASED for Catchbasine - B6.33 05 39.10 - double - Z05 - RCB - ST | 1 | 2025-10-29 | 2025-11-03 |  |  | FALSE | yes
| JD3RZ06L53ST22267 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z06 - L - 53 | 1 | 2025-08-13 | 2025-08-16 | 2025-10-08 |  | FALSE | FALSE
| JD3RZ06L53ST22268 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z06 - L - 53 - ST | 1 | 2025-08-17 | 2025-08-20 | 2025-10-11 |  | FALSE | FALSE
| JD3RZ06L53ST22269 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z06 - L - 53 - ST | 1 | 2025-08-21 | 2025-08-25 |  |  | FALSE | yes
| JD3RZ06L53ST22270 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z06 - L - 53 - ST | 1 | 2025-09-03 | 2025-09-08 |  |  | FALSE | yes
| JD3RZ06L53ST22276 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z06 - L - 53 - ST | 1 | 2025-08-16 | 2025-08-17 | 2025-08-20 |  | FALSE | FALSE
| JD3RZ06L53ST22277 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z06 - L - 53 | 1 | 2025-08-18 | 2025-08-19 | 2025-08-23 |  | FALSE | FALSE
| JD3RZ06L53ST22278 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z06 - L - 53 - ST | 1 | 2025-08-20 | 2025-08-21 | 2025-08-25 |  | FALSE | FALSE
| JD3RZ06L53ST22279 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z06 - L - 53 - ST | 1 | 2025-08-23 | 2025-08-24 | 2025-10-01 |  | FALSE | FALSE
| JD3RZ06L53ST22280 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z06 - L - 53 - ST | 1 | 2025-09-03 | 2025-09-04 | 2025-10-05 |  | FALSE | FALSE
| JD3RZ06L53ST22451 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z06 - L - 53 - ST | 1 | 2025-08-27 | 2025-08-28 |  |  | FALSE | yes
| JD3RZ06L53ST22452 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z06 - L - 53 - S | 1 | 2025-08-30 | 2025-08-31 |  |  | FALSE | yes
| JD3RZ06L53ST22453 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z06 - L - 53 - ST | 1 | 2025-09-01 | 2025-09-02 |  |  | FALSE | yes
| JD3RZ06L53ST22461 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z06 - L - 53 - ST | 1 | 2025-08-30 | 2025-08-31 |  |  | FALSE | yes
| JD3RZ06L53ST22462 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z06 - L - 53 - S | 1 | 2025-09-01 | 2025-09-02 |  |  | FALSE | yes
| JD3RZ06L53ST22463 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z06 - L - 53 - ST | 1 | 2025-09-03 | 2025-09-04 |  |  | FALSE | yes
| JD3RZ06L53ST22466.R | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z06 - L - 53 - ST - Remaini | 1 | 2025-09-01 | 2025-09-02 |  |  | FALSE | yes
| JD3RZ06L53ST22467 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z06 - L - 53 - S | 1 | 2025-09-03 | 2025-09-04 |  |  | FALSE | yes
| JD3RZ06L53ST22468 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z06 - L - 53 - ST | 1 | 2025-09-06 | 2025-09-07 |  |  | FALSE | yes
| JD3RZ06L53ST22479 | Excavation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z06 - L - 53 - ST | 1 | 2025-08-27 | 2025-08-28 | 2025-08-22 |  | FALSE | yes
| JD3RZ06L53ST22480 | Base Plain Concrete Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z06 - L - 53 - ST | 1 | 2025-08-30 | 2025-08-31 | 2025-08-25 |  | FALSE | yes
| JD3RZ06L53ST22481 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z06 - L - 53 - ST | 1 | 2025-09-03 | 2025-09-04 |  |  | FALSE | yes
| JD3RZ06L53ST22482 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z06 - L - 53 - S | 1 | 2025-09-06 | 2025-09-07 |  |  | FALSE | yes
| JD3RZ06L53ST22483 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z06 - L - 53 - ST | 1 | 2025-09-08 | 2025-09-09 |  |  | FALSE | yes
| JD3RZ06L53ST22485 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - Z06 - L - 53 - ST | 1 | 2025-09-01 | 2025-09-03 |  |  | FALSE | yes
| JD3RZ06L53ST22486 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - Z06 - L - 53 - ST | 1 | 2025-09-04 | 2025-09-07 |  |  | FALSE | yes
| JD3RZ06L53ST22487 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - Z06 - L - 53 - ST | 1 | 2025-09-08 | 2025-09-09 |  |  | FALSE | yes
| JD3RZ06L53ST22489 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - Z06 - L - 53 - ST | 1 | 2025-09-03 | 2025-09-06 |  |  | FALSE | yes
| JD3RZ06L53ST22490 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z06 - L - 53 - ST | 1 | 2025-09-07 | 2025-09-09 |  |  | FALSE | yes
| JD3RZ06L53ST22491 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z06 - L - 53 - ST | 1 | 2025-09-10 | 2025-09-11 |  |  | FALSE | yes
| JD3RZ06L53ST524358 | Concrete encasement for pipes - NNB6.33 42 11.25 - Z06 - L - 53 - ST | 1 | 2025-08-27 | 2025-09-02 |  |  | FALSE | yes
| JD3RZ06L53TSE22542 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z06 - L - 53 - TSE | 1 | 2025-09-13 | 2025-09-16 |  |  | FALSE | yes
| JD3RZ06L53TSE22543 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z06 - L - 53 - T | 1 | 2025-09-17 | 2025-09-21 |  |  | FALSE | yes
| JD3RZ06L53TSE22544 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z06 - L - 53 - TSE | 1 | 2025-09-22 | 2025-09-29 |  |  | FALSE | yes
| JD3RZ06L53TSE22545 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z06 - L - 53 - TSE | 1 | 2025-09-30 | 2025-10-05 |  |  | FALSE | yes
| JD3RZ06L53TSE22546 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z06 - L - 53 - TSE | 1 | 2025-10-06 | 2025-10-11 |  |  | FALSE | yes
| JD3RZ06L53TSE22547 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z06 - L - 53 - TSE | 1 | 2025-09-17 | 2025-09-18 |  |  | FALSE | yes
| JD3RZ06L53TSE22548 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z06 - L - 53 - T | 1 | 2025-09-20 | 2025-09-21 |  |  | FALSE | yes
| JD3RZ06L53TSE22549 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z06 - L - 53 - TSE | 1 | 2025-09-22 | 2025-09-23 |  |  | FALSE | yes
| JD3RZ06L53TSE22550 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z06 - L - 53 - TSE | 1 | 2025-09-24 | 2025-09-25 |  |  | FALSE | yes
| JD3RZ06L53TSE22551 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z06 - L - 53 - TSE | 1 | 2025-10-12 | 2025-10-13 |  |  | FALSE | yes
| JD3RZ06L53TSE22667 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z06 - L - 53 - TSE | 1 | 2025-09-30 | 2025-10-01 |  |  | FALSE | yes
| JD3RZ06L53TSE22668 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z06 - L - 53 - TSE | 1 | 2025-10-02 | 2025-10-04 |  |  | FALSE | yes
| JD3RZ06L53TSE22669 | Installationfor gate valves 250 mm - B4.33 14 19.02 - Z06 - L - 53 - TSE | 1 | 2025-09-30 | 2025-10-01 |  |  | FALSE | yes
| JD3RZ06L53TSE22670 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - Z06 - L - 53 - TSE | 1 | 2025-10-02 | 2025-10-04 |  |  | FALSE | yes
| JD3RZ06L53WT22492 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z06 - L - 53 - WT | 1 | 2025-10-14 | 2025-10-15 |  |  | FALSE | yes
| JD3RZ06L53WT22493 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z06 - L - 53 - WT | 1 | 2025-10-16 | 2025-10-18 |  |  | FALSE | yes
| JD3RZ06L53WT22494 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z06 - L - 53 - WT | 1 | 2025-10-19 | 2025-10-20 |  |  | FALSE | yes
| JD3RZ06L53WT22495 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z06 - L - 53 - WT | 1 | 2025-10-21 | 2025-10-22 |  |  | FALSE | yes
| JD3RZ06L53WT22496 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z06 - L - 53 - WT | 1 | 2025-10-23 | 2025-10-25 |  |  | FALSE | yes
| JD3RZ06L53WT22527 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z06 - L - 53 - WT | 1 | 2025-10-16 | 2025-10-18 |  |  | FALSE | yes
| JD3RZ06L53WT22528 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z06 - L - 53 - WT | 1 | 2025-10-19 | 2025-10-20 |  |  | FALSE | yes
| JD3RZ06L53WT22529 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z06 - L - 53 - WT | 1 | 2025-10-21 | 2025-10-22 |  |  | FALSE | yes
| JD3RZ06L54ST22979 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z06 - L - 54 - ST | 1 | 2025-08-18 | 2025-08-20 |  |  | FALSE | yes
| JD3RZ06L54ST22980 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z06 - L - 54 | 1 | 2025-08-21 | 2025-08-24 |  |  | FALSE | yes
| JD3RZ06L54ST22981 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z06 - L - 54 - ST | 1 | 2025-08-25 | 2025-08-28 |  |  | FALSE | yes
| JD3RZ06L54ST22982 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z06 - L - 54 - ST | 1 | 2025-08-30 | 2025-09-02 |  |  | FALSE | yes
| JD3RZ06L54ST22983 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z06 - L - 54 - ST | 1 | 2025-09-18 | 2025-09-23 |  |  | FALSE | yes
| JD3RZ06L54ST22988 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z06 - L - 54 - ST | 1 | 2025-08-31 | 2025-09-01 |  |  | FALSE | yes
| JD3RZ06L54ST22989 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z06 - L - 54 - ST | 1 | 2025-08-24 | 2025-08-25 | 2025-08-16 |  | FALSE | yes
| JD3RZ06L54ST22990 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z06 - L - 54 | 1 | 2025-08-26 | 2025-08-27 | 2025-08-18 |  | FALSE | yes
| JD3RZ06L54ST22991 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z06 - L - 54 - ST | 1 | 2025-08-28 | 2025-08-30 | 2025-08-21 |  | FALSE | yes
| JD3RZ06L54ST22992 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z06 - L - 54 - ST | 1 | 2025-08-31 | 2025-09-01 | 2025-09-06 |  | FALSE | FALSE
| JD3RZ06L54ST22993 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z06 - L - 54 - ST | 1 | 2025-09-07 | 2025-09-08 |  |  | FALSE | yes
| JD3RZ06L54ST23023.R | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - Z06 - L - 54 - ST - Remaining | 1 | 2025-09-04 | 2025-09-06 |  |  | FALSE | yes
| JD3RZ06L54ST23033.R | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - Z06 - L - 54 - ST - Remaining | 1 | 2025-09-08 | 2025-09-09 |  |  | FALSE | yes
| JD3RZ06L54ST23043.R | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - Z06 - L - 54 - ST - Remaining | 1 | 2025-09-14 | 2025-09-15 | 2025-10-23 |  | FALSE | FALSE
| JD3RZ06L54ST23048.R | Backfilling Works for GRP Pipe Line 900 mm - depth from 2.51 to 3.50 m - B6.33 42 11.13 - Z06 - L - 54 - ST - Remaining | 1 | 2025-09-16 | 2025-09-17 |  |  | FALSE | yes
| JD3RZ06L54ST23164 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z06 - L - 54 - ST | 1 | 2025-08-31 | 2025-09-01 |  |  | FALSE | yes
| JD3RZ06L54ST23165 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z06 - L - 54 - S | 1 | 2025-09-02 | 2025-09-03 |  |  | FALSE | yes
| JD3RZ06L54ST23166 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z06 - L - 54 - ST | 1 | 2025-09-04 | 2025-09-06 |  |  | FALSE | yes
| JD3RZ06L54ST23174.R | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z06 - L - 54 - ST - Remaini | 1 | 2025-09-07 | 2025-09-08 |  |  | FALSE | yes
| JD3RZ06L54ST23175 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z06 - L - 54 - S | 1 | 2025-09-09 | 2025-09-10 |  |  | FALSE | yes
| JD3RZ06L54ST23176 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z06 - L - 54 - ST | 1 | 2025-09-11 | 2025-09-13 |  |  | FALSE | yes
| JD3RZ06L54ST23179 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z06 - L - 54 - ST | 1 | 2025-09-03 | 2025-09-06 |  |  | FALSE | yes
| JD3RZ06L54ST23180 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z06 - L - 54 - S | 1 | 2025-09-07 | 2025-09-08 |  |  | FALSE | yes
| JD3RZ06L54ST23181 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z06 - L - 54 - ST | 1 | 2025-09-14 | 2025-09-15 |  |  | FALSE | yes
| JD3RZ06L54ST23197 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - Z06 - L - 54 - ST | 1 | 2025-08-31 | 2025-09-01 |  |  | FALSE | yes
| JD3RZ06L54ST23198 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - Z06 - L - 54 - ST | 1 | 2025-09-02 | 2025-09-04 |  |  | FALSE | yes
| JD3RZ06L54ST23199 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - Z06 - L - 54 - ST | 1 | 2025-09-06 | 2025-09-08 |  |  | FALSE | yes
| JD3RZ06L54ST23200 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - Z06 - L - 54 - ST | 1 | 2025-09-09 | 2025-09-10 |  |  | FALSE | yes
| JD3RZ06L54ST23201 | EXCAVATION Works for Catchbasine double - B6.33 05 39.10 - Z06 - L - 54 - ST | 1 | 2025-09-02 | 2025-09-03 |  |  | FALSE | yes
| JD3RZ06L54ST23202 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - Z06 - L - 54 - ST | 1 | 2025-09-04 | 2025-09-07 |  |  | FALSE | yes
| JD3RZ06L54ST23203 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z06 - L - 54 - ST | 1 | 2025-09-08 | 2025-09-10 |  |  | FALSE | yes
| JD3RZ06L54ST23204 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z06 - L - 54 - ST | 1 | 2025-09-16 | 2025-09-17 |  |  | FALSE | yes
| JD3RZ06L54ST524351 | Concrete encasement for pipes - NNB6.33 42 11.25 - Z06 - L - 54 - ST | 1 | 2025-08-31 | 2025-09-06 |  |  | FALSE | yes
| JD3RZ06L54TSE23255 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z06 - L - 54 - TSE | 1 | 2025-09-24 | 2025-09-29 |  |  | FALSE | yes
| JD3RZ06L54TSE23256 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z06 - L - 54 - T | 1 | 2025-09-30 | 2025-10-05 |  |  | FALSE | yes
| JD3RZ06L54TSE23257 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z06 - L - 54 - TSE | 1 | 2025-10-06 | 2025-10-15 |  |  | FALSE | yes
| JD3RZ06L54TSE23258 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z06 - L - 54 - TSE | 1 | 2025-10-16 | 2025-10-22 |  |  | FALSE | yes
| JD3RZ06L54TSE23259 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z06 - L - 54 - TSE | 1 | 2025-10-23 | 2025-10-29 |  |  | FALSE | yes
| JD3RZ06L54TSE23260 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z06 - L - 54 - TSE | 1 | 2025-09-24 | 2025-09-25 |  |  | FALSE | yes
| JD3RZ06L54TSE23261 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z06 - L - 54 - T | 1 | 2025-09-27 | 2025-09-28 |  |  | FALSE | yes
| JD3RZ06L54TSE23262 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z06 - L - 54 - TSE | 1 | 2025-09-29 | 2025-09-30 |  |  | FALSE | yes
| JD3RZ06L54TSE23263 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z06 - L - 54 - TSE | 1 | 2025-10-01 | 2025-10-02 |  |  | FALSE | yes
| JD3RZ06L54TSE23264 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z06 - L - 54 - TSE | 1 | 2025-10-21 | 2025-10-22 |  |  | FALSE | yes
| JD3RZ06L54TSE23380 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z06 - L - 54 - TSE | 1 | 2025-10-16 | 2025-10-18 |  |  | FALSE | yes
| JD3RZ06L54TSE23381 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z06 - L - 54 - TSE | 1 | 2025-10-19 | 2025-10-20 |  |  | FALSE | yes
| JD3RZ06L54TSE23382 | Installationfor gate valves 250 mm - B4.33 14 19.02 - Z06 - L - 54 - TSE | 1 | 2025-10-16 | 2025-10-18 |  |  | FALSE | yes
| JD3RZ06L54TSE23383 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - Z06 - L - 54 - TSE | 1 | 2025-10-19 | 2025-10-20 |  |  | FALSE | yes
| JD3RZ06L54WT23205 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z06 - L - 54 - WT | 1 | 2025-10-30 | 2025-11-01 |  |  | FALSE | yes
| JD3RZ06L54WT23206 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z06 - L - 54 - WT | 1 | 2025-11-02 | 2025-11-03 |  |  | FALSE | yes
| JD3RZ06L54WT23207 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z06 - L - 54 - WT | 1 | 2025-11-04 | 2025-11-05 |  |  | FALSE | yes
| JD3RZ06L54WT23208 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z06 - L - 54 - WT | 1 | 2025-11-06 | 2025-11-08 |  |  | FALSE | yes
| JD3RZ06L54WT23209 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z06 - L - 54 - WT | 1 | 2025-11-09 | 2025-11-10 |  |  | FALSE | yes
| JD3RZ06L54WT23240 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z06 - L - 54 - WT | 1 | 2025-10-30 | 2025-11-01 |  |  | FALSE | yes
| JD3RZ06L54WT23241 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z06 - L - 54 - WT | 1 | 2025-11-02 | 2025-11-03 |  |  | FALSE | yes
| JD3RZ06L54WT23242 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z06 - L - 54 - WT | 1 | 2025-11-04 | 2025-11-05 |  |  | FALSE | yes
| JD3RZ06L55ST23694 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z06 - L - 55 - ST | 1 | 2025-10-09 | 2025-10-12 | 2025-10-07 |  | FALSE | yes
| JD3RZ06L55ST23695 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z06 - L - 55 - ST | 1 | 2025-10-13 | 2025-10-15 |  |  | FALSE | yes
| JD3RZ06L55ST23696 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z06 - L - 55 - ST | 1 | 2025-10-22 | 2025-10-26 |  |  | FALSE | yes
| JD3RZ06L55ST23700 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z06 - L - 55 - ST | 1 | 2025-10-13 | 2025-10-14 |  |  | FALSE | yes
| JD3RZ06L55ST23701 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z06 - L - 55 - ST | 1 | 2025-10-22 | 2025-10-23 |  |  | FALSE | yes
| JD3RZ06L55ST23703 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z06 - L - 55 | 1 | 2025-10-11 | 2025-10-12 |  |  | FALSE | yes
| JD3RZ06L55ST23704 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z06 - L - 55 - ST | 1 | 2025-10-13 | 2025-10-14 |  |  | FALSE | yes
| JD3RZ06L55ST23705 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z06 - L - 55 - ST | 1 | 2025-10-15 | 2025-10-16 |  |  | FALSE | yes
| JD3RZ06L55ST23736.R | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - Z06 - L - 55 - ST - Remaining | 1 | 2025-10-25 | 2025-10-26 |  |  | FALSE | yes
| JD3RZ06L55ST23746.R | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - Z06 - L - 55 - ST - Remaining | 1 | 2025-10-27 | 2025-10-28 |  |  | FALSE | yes
| JD3RZ06L55ST23756.R | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - Z06 - L - 55 - ST - Remaining | 1 | 2025-10-29 | 2025-10-30 |  |  | FALSE | yes
| JD3RZ06L55ST23785 | Primary Test for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m - B6.33 42 11.20 - Z06 - L - 55 - ST | 1 | 2025-11-01 | 2025-11-02 |  |  | FALSE | yes
| JD3RZ06L55ST23786 | Backfilling Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m - B6.33 42 11.20 - Z06 - L - 55 - ST | 1 | 2025-11-03 | 2025-11-04 |  |  | FALSE | yes
| JD3RZ06L55ST23877.R | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z06 - L - 55 - ST - Remaini | 1 | 2025-11-03 | 2025-11-04 |  |  | FALSE | yes
| JD3RZ06L55ST23878 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z06 - L - 55 - S | 1 | 2025-11-05 | 2025-11-06 |  |  | FALSE | yes
| JD3RZ06L55ST23879 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z06 - L - 55 - ST | 1 | 2025-11-08 | 2025-11-09 |  |  | FALSE | yes
| JD3RZ06L55ST23887.R | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z06 - L - 55 - ST - Remaini | 1 | 2025-11-05 | 2025-11-06 |  |  | FALSE | yes
| JD3RZ06L55ST23888 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z06 - L - 55 - S | 1 | 2025-11-08 | 2025-11-09 |  |  | FALSE | yes
| JD3RZ06L55ST23889 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z06 - L - 55 - ST | 1 | 2025-11-10 | 2025-11-11 |  |  | FALSE | yes
| JD3RZ06L55ST23892.R | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z06 - L - 55 - ST - Remaini | 1 | 2025-11-08 | 2025-11-09 |  |  | FALSE | yes
| JD3RZ06L55ST23893 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z06 - L - 55 - S | 1 | 2025-11-10 | 2025-11-11 |  |  | FALSE | yes
| JD3RZ06L55ST23894 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z06 - L - 55 - ST | 1 | 2025-11-12 | 2025-11-13 |  |  | FALSE | yes
| JD3RZ06L55ST23907 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z06 - L - 55 - ST | 1 | 2025-10-15 | 2025-10-16 |  |  | FALSE | yes
| JD3RZ06L55ST23908 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z06 - L - 55 - S | 1 | 2025-10-18 | 2025-10-19 |  |  | FALSE | yes
| JD3RZ06L55ST23909 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z06 - L - 55 - ST | 1 | 2025-10-20 | 2025-10-21 |  |  | FALSE | yes
| JD3RZ06L55ST23911 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - Z06 - L - 55 - ST | 1 | 2025-10-15 | 2025-10-18 |  |  | FALSE | yes
| JD3RZ06L55ST23912 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - Z06 - L - 55 - ST | 1 | 2025-10-19 | 2025-10-21 |  |  | FALSE | yes
| JD3RZ06L55ST23913 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - Z06 - L - 55 - ST | 1 | 2025-10-22 | 2025-10-23 |  |  | FALSE | yes
| JD3RZ06L55ST23915 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - Z06 - L - 55 - ST | 1 | 2025-10-18 | 2025-10-20 |  |  | FALSE | yes
| JD3RZ06L55ST23916 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z06 - L - 55 - ST | 1 | 2025-10-21 | 2025-10-23 |  |  | FALSE | yes
| JD3RZ06L55ST23917 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z06 - L - 55 - ST | 1 | 2025-10-25 | 2025-10-26 |  |  | FALSE | yes
| JD3RZ06L55ST524352 | Concrete encasement for pipes - NNB6.33 42 11.25 - Z06 - L - 55 - ST | 1 | 2025-10-15 | 2025-10-21 |  |  | FALSE | yes
| JD3RZ06L55TSE23968 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z06 - L - 55 - TSE | 1 | 2025-11-15 | 2025-11-17 |  |  | FALSE | yes
| JD3RZ06L55TSE23969 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z06 - L - 55 - T | 1 | 2025-11-18 | 2025-11-20 |  |  | FALSE | yes
| JD3RZ06L55TSE23970 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z06 - L - 55 - TSE | 1 | 2025-11-22 | 2025-11-27 |  |  | FALSE | yes
| JD3RZ06L55TSE23971 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z06 - L - 55 - TSE | 1 | 2025-11-29 | 2025-12-02 |  |  | FALSE | yes
| JD3RZ06L55TSE23972 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z06 - L - 55 - TSE | 1 | 2025-12-03 | 2025-12-07 |  |  | FALSE | yes
| JD3RZ06L55TSE23973 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z06 - L - 55 - TSE | 1 | 2025-11-15 | 2025-11-16 |  |  | FALSE | yes
| JD3RZ06L55TSE23974 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z06 - L - 55 - T | 1 | 2025-11-17 | 2025-11-18 |  |  | FALSE | yes
| JD3RZ06L55TSE23975 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z06 - L - 55 - TSE | 1 | 2025-11-19 | 2025-11-20 |  |  | FALSE | yes
| JD3RZ06L55TSE23976 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z06 - L - 55 - TSE | 1 | 2025-11-22 | 2025-11-23 |  |  | FALSE | yes
| JD3RZ06L55TSE23977 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z06 - L - 55 - TSE | 1 | 2025-12-03 | 2025-12-04 |  |  | FALSE | yes
| JD3RZ06L55TSE24093 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z06 - L - 55 - TSE | 1 | 2025-11-29 | 2025-11-30 |  |  | FALSE | yes
| JD3RZ06L55TSE24094 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z06 - L - 55 - TSE | 1 | 2025-12-01 | 2025-12-02 |  |  | FALSE | yes
| JD3RZ06L55WT23918 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z06 - L - 55 - WT | 1 | 2025-12-08 | 2025-12-09 |  |  | FALSE | yes
| JD3RZ06L55WT23919 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z06 - L - 55 - WT | 1 | 2025-12-10 | 2025-12-11 |  |  | FALSE | yes
| JD3RZ06L55WT23920 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z06 - L - 55 - WT | 1 | 2025-12-13 | 2025-12-14 |  |  | FALSE | yes
| JD3RZ06L55WT23921 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z06 - L - 55 - WT | 1 | 2025-12-15 | 2025-12-16 |  |  | FALSE | yes
| JD3RZ06L55WT23922 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z06 - L - 55 - WT | 1 | 2025-12-17 | 2025-12-18 |  |  | FALSE | yes
| JD3RZ06L55WT23953 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z06 - L - 55 - WT | 1 | 2025-12-08 | 2025-12-09 |  |  | FALSE | yes
| JD3RZ06L55WT23954 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z06 - L - 55 - WT | 1 | 2025-12-10 | 2025-12-11 |  |  | FALSE | yes
| JD3RZ06L55WT23955 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z06 - L - 55 - WT | 1 | 2025-12-13 | 2025-12-14 |  |  | FALSE | yes
| JD3RZ06L56ST24405 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z06 - L - 56 - ST | 1 | 2025-10-26 | 2025-10-30 |  |  | FALSE | yes
| JD3RZ06L56ST24406 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z06 - L - 56 | 1 | 2025-11-01 | 2025-11-06 |  |  | FALSE | yes
| JD3RZ06L56ST24407 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z06 - L - 56 - ST | 1 | 2025-11-08 | 2025-11-15 |  |  | FALSE | yes
| JD3RZ06L56ST24408 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z06 - L - 56 - ST | 1 | 2025-11-16 | 2025-11-23 |  |  | FALSE | yes
| JD3RZ06L56ST24409 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z06 - L - 56 - ST | 1 | 2025-12-24 | 2026-01-03 |  |  | FALSE | yes
| JD3RZ06L56ST24410 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z06 - L - 56 - ST | 1 | 2025-11-01 | 2025-11-02 |  |  | FALSE | yes
| JD3RZ06L56ST24411 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z06 - L - 56 | 1 | 2025-11-03 | 2025-11-04 |  |  | FALSE | yes
| JD3RZ06L56ST24412 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z06 - L - 56 - ST | 1 | 2025-11-05 | 2025-11-06 |  |  | FALSE | yes
| JD3RZ06L56ST24413 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z06 - L - 56 - ST | 1 | 2025-11-08 | 2025-11-09 |  |  | FALSE | yes
| JD3RZ06L56ST24414 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z06 - L - 56 - ST | 1 | 2025-12-24 | 2025-12-25 |  |  | FALSE | yes
| JD3RZ06L56ST24415.R | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z06 - L - 56 - ST - Remaining | 1 | 2025-11-01 | 2025-11-02 |  |  | FALSE | yes
| JD3RZ06L56ST24416.R | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z06 - L - 56 | 1 | 2025-11-03 | 2025-11-04 |  |  | FALSE | yes
| JD3RZ06L56ST24417.R | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z06 - L - 56 - ST - Remaining | 1 | 2025-11-05 | 2025-11-06 |  |  | FALSE | yes
| JD3RZ06L56ST24418.R | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z06 - L - 56 - ST - Remaining | 1 | 2025-11-08 | 2025-11-09 |  |  | FALSE | yes
| JD3RZ06L56ST24419 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z06 - L - 56 - ST | 1 | 2026-01-26 | 2026-01-31 |  |  | FALSE | yes
| JD3RZ06L56ST24428.R | Primary Test for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - Z06 - L - 56 - ST - Remaining | 1 | 2025-11-10 | 2025-11-11 | 2025-09-16 |  | FALSE | yes
| JD3RZ06L56ST24429.R | Backfilling Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - Z06 - L - 56 - ST - Remaining | 1 | 2025-11-12 | 2025-11-13 | 2025-08-28 |  | FALSE | yes
| JD3RZ06L56ST24435.R | Excavation Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - Z06 - L - 56 - ST - Remaining | 1 | 2025-11-05 | 2025-11-06 | 2025-09-03 |  | FALSE | yes
| JD3RZ06L56ST24436.R | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - Z06 - L - 56 | 1 | 2025-11-08 | 2025-11-09 | 2025-09-11 |  | FALSE | yes
| JD3RZ06L56ST24437.R | Installing for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - Z06 - L - 56 - ST - Remaining | 1 | 2025-11-10 | 2025-11-11 | 2025-09-13 |  | FALSE | yes
| JD3RZ06L56ST24438 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - Z06 - L - 56 - ST | 1 | 2025-11-12 | 2025-11-15 | 2025-08-21 |  | FALSE | yes
| JD3RZ06L56ST24439 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - Z06 - L - 56 - ST | 1 | 2025-11-16 | 2025-11-19 | 2025-08-24 |  | FALSE | yes
| JD3RZ06L56ST24445.R | Excavation Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - Z06 - L - 56 - ST - Remaining | 1 | 2025-11-08 | 2025-11-09 | 2025-08-31 |  | FALSE | yes
| JD3RZ06L56ST24446.R | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - Z06 - L - 56 | 1 | 2025-11-10 | 2025-11-11 | 2025-09-03 |  | FALSE | yes
| JD3RZ06L56ST24447.R | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - Z06 - L - 56 - ST - Remaining | 1 | 2025-11-12 | 2025-11-13 | 2025-09-03 |  | FALSE | yes
| JD3RZ06L56ST24448 | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - Z06 - L - 56 - ST | 1 | 2025-11-15 | 2025-11-16 | 2025-08-21 |  | FALSE | yes
| JD3RZ06L56ST24449 | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - Z06 - L - 56 - ST | 1 | 2025-11-17 | 2025-11-19 | 2025-08-23 |  | FALSE | yes
| JD3RZ06L56ST24457.R | Installing for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - Z06 - L - 56 - ST - Remaining | 1 | 2025-11-15 | 2025-11-16 | 2025-10-05 |  | FALSE | yes
| JD3RZ06L56ST24458 | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - Z06 - L - 56 - ST | 1 | 2025-11-17 | 2025-11-18 | 2025-08-20 |  | FALSE | yes
| JD3RZ06L56ST24459 | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - Z06 - L - 56 - ST | 1 | 2025-11-19 | 2025-11-22 | 2025-08-23 |  | FALSE | yes
| JD3RZ06L56ST24468.R | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - Z06 - L - 56 - ST - Remaining | 1 | 2025-11-19 | 2025-11-20 | 2025-08-07 |  | FALSE | yes
| JD3RZ06L56ST24469.R | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - Z06 - L - 56 - ST - Remaining | 1 | 2025-11-22 | 2025-11-23 | 2025-08-30 |  | FALSE | yes
| JD3RZ06L56ST24514 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - Z06 - L - 56 - ST | 1 | 2025-12-20 | 2025-12-21 |  |  | FALSE | yes
| JD3RZ06L56ST24546 | Isolation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - Z06 - L - 56 - ST | 1 | 2025-12-03 | 2025-12-04 | 2025-10-16 |  | FALSE | yes
| JD3RZ06L56ST24547 | Backfilling Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - Z06 - L - 56 - ST | 1 | 2025-12-06 | 2025-12-07 | 2025-10-19 |  | FALSE | yes
| JD3RZ06L56ST24576 | Excavation Works for Box Culvert Dim (4000*1500) depth from 3.51 to 4.50 - B6.34 42 16.09 - Z06 - L - 56 - ST | 1 | 2025-12-08 | 2025-12-09 |  |  | FALSE | yes
| JD3RZ06L56ST24577 | Plain Concrete Works For Box Culvert Dim (4000*1500) depth from 3.51 to 4.50 - B6.34 42 16.09 - Z06 - L - 56 - ST | 1 | 2025-12-10 | 2025-12-11 |  |  | FALSE | yes
| JD3RZ06L56ST24578 | Raft Foundation for Box Culvert Dim (4000*1500) depth from 3.51 to 4.50 - B6.34 42 16.09 - Z06 - L - 56 - ST | 1 | 2025-12-13 | 2025-12-14 |  |  | FALSE | yes
| JD3RZ06L56ST24579 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.09 - Z06 - L - 56 - ST | 1 | 2025-12-15 | 2025-12-17 |  |  | FALSE | yes
| JD3RZ06L56ST24580 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.09 - Z06 - L - 56 - ST | 1 | 2025-12-18 | 2025-12-21 |  |  | FALSE | yes
| JD3RZ06L56ST24581 | Isolation Works for Box Culvert Dim (4000*1500) depth from 3.51 to 4.50 - B6.34 42 16.09 - Z06 - L - 56 - ST | 1 | 2025-12-22 | 2025-12-23 |  |  | FALSE | yes
| JD3RZ06L56ST24582 | Backfilling Works for Box Culvert Dim (4000*1500) depth from 3.51 to 4.50 - B6.34 42 16.09 - Z06 - L - 56 - ST | 1 | 2025-12-24 | 2025-12-25 |  |  | FALSE | yes
| JD3RZ06L56ST24588.R | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z06 - L - 56 - ST - Remaining | 1 | 2025-11-15 | 2025-11-16 | 2025-09-16 |  | FALSE | yes
| JD3RZ06L56ST24589.R | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z06 - L - 56 - ST - Remainin | 1 | 2025-11-17 | 2025-11-18 |  |  | FALSE | yes
| JD3RZ06L56ST24590.R | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z06 - L - 56 - ST - Remaini | 1 | 2025-11-19 | 2025-11-20 |  |  | FALSE | yes
| JD3RZ06L56ST24591 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z06 - L - 56 - S | 1 | 2025-11-22 | 2025-11-24 |  |  | FALSE | yes
| JD3RZ06L56ST24592 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z06 - L - 56 - ST | 1 | 2025-12-22 | 2025-12-24 |  |  | FALSE | yes
| JD3RZ06L56ST24601 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z06 - L - 56 - S | 1 | 2025-11-24 | 2025-11-25 |  |  | FALSE | yes
| JD3RZ06L56ST24602 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z06 - L - 56 - ST | 1 | 2025-12-25 | 2025-12-27 |  |  | FALSE | yes
| JD3RZ06L56ST24603.R | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z06 - L - 56 - ST - Remaining | 1 | 2025-11-19 | 2025-11-20 | 2025-08-24 |  | FALSE | yes
| JD3RZ06L56ST24604.R | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z06 - L - 56 - ST - Remainin | 1 | 2025-11-22 | 2025-11-23 | 2025-08-26 |  | FALSE | yes
| JD3RZ06L56ST24605.R | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z06 - L - 56 - ST - Remaini | 1 | 2025-11-24 | 2025-11-25 | 2025-08-28 |  | FALSE | yes
| JD3RZ06L56ST24606 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z06 - L - 56 - S | 1 | 2025-11-26 | 2025-11-29 |  |  | FALSE | yes
| JD3RZ06L56ST24607 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z06 - L - 56 - ST | 1 | 2026-01-22 | 2026-01-25 |  |  | FALSE | yes
| JD3RZ06L56ST24620 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z06 - L - 56 - ST | 1 | 2025-12-17 | 2025-12-18 | 2025-09-20 |  | FALSE | yes
| JD3RZ06L56ST24621 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z06 - L - 56 - S | 1 | 2025-12-20 | 2025-12-21 |  |  | FALSE | yes
| JD3RZ06L56ST24622 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z06 - L - 56 - ST | 1 | 2026-01-20 | 2026-01-21 |  |  | FALSE | yes
| JD3RZ06L56ST24623 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - Z06 - L - 56 - ST | 1 | 2025-12-15 | 2025-12-20 |  |  | FALSE | yes
| JD3RZ06L56ST24624 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - Z06 - L - 56 - ST | 1 | 2025-12-21 | 2025-12-29 |  |  | FALSE | yes
| JD3RZ06L56ST24625 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - Z06 - L - 56 - ST | 1 | 2025-12-30 | 2026-01-07 |  |  | FALSE | yes
| JD3RZ06L56ST24626 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - Z06 - L - 56 - ST | 1 | 2026-01-08 | 2026-01-13 |  |  | FALSE | yes
| JD3RZ06L56ST24627 | EXCAVATION Works for Catchbasine double - B6.33 05 39.10 - Z06 - L - 56 - ST | 1 | 2025-12-21 | 2025-12-25 |  |  | FALSE | yes
| JD3RZ06L56ST24628 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - Z06 - L - 56 - ST | 1 | 2025-12-27 | 2026-01-03 |  |  | FALSE | yes
| JD3RZ06L56ST24629 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z06 - L - 56 - ST | 1 | 2026-01-04 | 2026-01-11 |  |  | FALSE | yes
| JD3RZ06L56ST24630 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z06 - L - 56 - ST | 1 | 2026-01-14 | 2026-01-19 |  |  | FALSE | yes
| JD3RZ06L56ST524353 | Concrete encasement for pipes - NNB6.33 42 11.25 - Z06 - L - 56 - ST | 1 | 2025-12-17 | 2025-12-23 |  |  | FALSE | yes
| JD3RZ06L56TSE24681 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z06 - L - 56 - TSE | 1 | 2025-12-27 | 2025-12-29 |  |  | FALSE | yes
| JD3RZ06L56TSE24682 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z06 - L - 56 - T | 1 | 2025-12-30 | 2026-01-01 |  |  | FALSE | yes
| JD3RZ06L56TSE24683 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z06 - L - 56 - TSE | 1 | 2026-01-03 | 2026-01-07 |  |  | FALSE | yes
| JD3RZ06L56TSE24684 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z06 - L - 56 - TSE | 1 | 2026-01-08 | 2026-01-11 |  |  | FALSE | yes
| JD3RZ06L56TSE24685 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z06 - L - 56 - TSE | 1 | 2026-02-21 | 2026-02-23 |  |  | FALSE | yes
| JD3RZ06L56TSE24686 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z06 - L - 56 - TSE | 1 | 2025-12-30 | 2026-01-08 |  |  | FALSE | yes
| JD3RZ06L56TSE24687 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z06 - L - 56 - T | 1 | 2026-01-10 | 2026-01-20 |  |  | FALSE | yes
| JD3RZ06L56TSE24688 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z06 - L - 56 - TSE | 1 | 2026-01-21 | 2026-02-10 |  |  | FALSE | yes
| JD3RZ06L56TSE24689 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z06 - L - 56 - TSE | 1 | 2026-02-11 | 2026-02-24 |  |  | FALSE | yes
| JD3RZ06L56TSE24690 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z06 - L - 56 - TSE | 1 | 2026-02-25 | 2026-03-10 |  |  | FALSE | yes
| JD3RZ06L56TSE24806 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z06 - L - 56 - TSE | 1 | 2026-02-11 | 2026-02-15 |  |  | FALSE | yes
| JD3RZ06L56TSE24807 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z06 - L - 56 - TSE | 1 | 2026-02-16 | 2026-02-19 |  |  | FALSE | yes
| JD3RZ06L56TSE24808 | Installationfor gate valves 250 mm - B4.33 14 19.02 - Z06 - L - 56 - TSE | 1 | 2026-02-11 | 2026-02-14 |  |  | FALSE | yes
| JD3RZ06L56TSE24809 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - Z06 - L - 56 - TSE | 1 | 2026-02-15 | 2026-02-17 |  |  | FALSE | yes
| JD3RZ06L56TSE24818 | Installationfor Wash - Out valves 100 mm. - on pipes with diameter 110 - 400 mm - B4.33 14 19.07 - Z06 - L - 56 - TSE | 1 | 2026-02-11 | 2026-02-12 |  |  | FALSE | yes
| JD3RZ06L56TSE24819 | Testing And Commtionningfor Wash - Out valves 100 mm. - on pipes with diameter 110 - 400 mm - B4.33 14 19.07 - Z06 - L - | 1 | 2026-02-14 | 2026-02-15 |  |  | FALSE | yes
| JD3RZ06L56TSE24824 | Installationfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - Z06 - L - 56 - TSE | 1 | 2026-02-11 | 2026-02-12 |  |  | FALSE | yes
| JD3RZ06L56TSE24825 | Testing And Commtionningfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - Z06 - L - 56 | 1 | 2026-02-14 | 2026-02-15 |  |  | FALSE | yes
| JD3RZ06L56TSE24842 | EXCAVATION and Bedding Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - Z06 - L - 56 - TSE | 1 | 2026-01-10 | 2026-01-11 |  |  | FALSE | yes
| JD3RZ06L56TSE24843 | Plain Concrete Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - Z06 - L - 56 - TSE | 1 | 2026-01-12 | 2026-01-13 |  |  | FALSE | yes
| JD3RZ06L56TSE24844 | INSTALLATIONfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - Z06 - L - 56 - TSE | 1 | 2026-01-14 | 2026-01-15 |  |  | FALSE | yes
| JD3RZ06L56TSE24845 | Backfilling Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - Z06 - L - 56 - TSE | 1 | 2026-01-17 | 2026-01-18 |  |  | FALSE | yes
| JD3RZ06L56TSE24854 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z06 - L - 56 - TSE | 1 | 2026-01-12 | 2026-01-13 |  |  | FALSE | yes
| JD3RZ06L56TSE24855 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z06 - L - 56 - TSE | 1 | 2026-01-14 | 2026-01-15 |  |  | FALSE | yes
| JD3RZ06L56TSE24856 | INSTALLATIONfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z06 - L - 56 - TSE | 1 | 2026-01-17 | 2026-01-18 |  |  | FALSE | yes
| JD3RZ06L56TSE24857 | Backfilling Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z06 - L - 56 - TSE | 1 | 2026-01-19 | 2026-01-20 |  |  | FALSE | yes
| JD3RZ06L56WT24631 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z06 - L - 56 - WT | 1 | 2026-03-11 | 2026-03-12 |  |  | FALSE | yes
| JD3RZ06L56WT24632 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z06 - L - 56 - WT | 1 | 2026-03-14 | 2026-03-15 |  |  | FALSE | yes
| JD3RZ06L56WT24633 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z06 - L - 56 - WT | 1 | 2026-03-16 | 2026-03-17 |  |  | FALSE | yes
| JD3RZ06L56WT24634 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z06 - L - 56 - WT | 1 | 2026-03-18 | 2026-03-19 |  |  | FALSE | yes
| JD3RZ06L56WT24635 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z06 - L - 56 - WT | 1 | 2026-03-21 | 2026-03-22 |  |  | FALSE | yes
| JD3RZ06L56WT24666 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z06 - L - 56 - WT | 1 | 2026-03-14 | 2026-03-15 |  |  | FALSE | yes
| JD3RZ06L56WT24667 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z06 - L - 56 - WT | 1 | 2026-03-16 | 2026-03-17 |  |  | FALSE | yes
| JD3RZ06L56WT24668 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z06 - L - 56 - WT | 1 | 2026-03-18 | 2026-03-19 |  |  | FALSE | yes
| JD3RZ06L57ST25118 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z06 - L - 57 - ST | 1 | 2026-02-05 | 2026-02-08 |  |  | FALSE | yes
| JD3RZ06L57ST25119 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z06 - L - 57 | 1 | 2026-02-09 | 2026-02-11 |  |  | FALSE | yes
| JD3RZ06L57ST25120 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z06 - L - 57 - ST | 1 | 2026-02-12 | 2026-02-16 |  |  | FALSE | yes
| JD3RZ06L57ST25121 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z06 - L - 57 - ST | 1 | 2026-02-17 | 2026-02-21 |  |  | FALSE | yes
| JD3RZ06L57ST25122 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z06 - L - 57 - ST | 1 | 2026-02-25 | 2026-03-02 |  |  | FALSE | yes
| JD3RZ06L57ST25123 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z06 - L - 57 - ST | 1 | 2026-02-09 | 2026-02-10 |  |  | FALSE | yes
| JD3RZ06L57ST25124 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z06 - L - 57 | 1 | 2026-02-11 | 2026-02-12 |  |  | FALSE | yes
| JD3RZ06L57ST25125 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z06 - L - 57 - ST | 1 | 2026-02-14 | 2026-02-15 |  |  | FALSE | yes
| JD3RZ06L57ST25126 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z06 - L - 57 - ST | 1 | 2026-02-22 | 2026-02-23 |  |  | FALSE | yes
| JD3RZ06L57ST25127 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z06 - L - 57 - ST | 1 | 2026-02-25 | 2026-02-26 |  |  | FALSE | yes
| JD3RZ06L57ST25128.R | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z06 - L - 57 - ST - Remaining | 1 | 2026-02-11 | 2026-02-12 | 2025-10-18 |  | FALSE | yes
| JD3RZ06L57ST25129.R | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z06 - L - 57 | 1 | 2026-02-14 | 2026-02-15 | 2025-10-20 |  | FALSE | yes
| JD3RZ06L57ST25130.R | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z06 - L - 57 - ST - Remaining | 1 | 2026-02-16 | 2026-02-17 | 2025-10-23 |  | FALSE | yes
| JD3RZ06L57ST25131 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z06 - L - 57 - ST | 1 | 2026-02-22 | 2026-02-23 | 2025-10-27 |  | FALSE | yes
| JD3RZ06L57ST25132 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z06 - L - 57 - ST | 1 | 2026-02-25 | 2026-02-26 |  |  | FALSE | yes
| JD3RZ06L57ST25137.R | Backfilling Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m - B6.33 42 11.03 - Z06 - L - 57 - ST - Remaining | 1 | 2026-02-28 | 2026-03-01 |  |  | FALSE | yes
| JD3RZ06L57ST25152 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - Z06 - L - 57 - ST | 1 | 2026-03-04 | 2026-03-05 | 2025-08-28 |  | FALSE | yes
| JD3RZ06L57ST25162 | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - Z06 - L - 57 - ST | 1 | 2026-03-07 | 2026-03-08 | 2025-08-31 |  | FALSE | yes
| JD3RZ06L57ST25172 | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - Z06 - L - 57 - ST | 1 | 2026-02-24 | 2026-02-25 | 2025-08-31 |  | FALSE | yes
| JD3RZ06L57ST25198 | Excavation Works for GRP Pipe Line 1000 mm - depth from 2.51 to 3.50 m - B6.33 42 11.16 - Z06 - L - 57 - ST | 1 | 2026-02-11 | 2026-02-12 |  |  | FALSE | yes
| JD3RZ06L57ST25199 | Soil Replacement and Bedding Works for GRP Pipe Line 1000 mm - depth from 2.51 to 3.50 m - B6.33 42 11.16 - Z06 - L - 57 | 1 | 2026-02-14 | 2026-02-15 |  |  | FALSE | yes
| JD3RZ06L57ST25200 | Installing for GRP Pipe Line 1000 mm - depth from 2.51 to 3.50 m - B6.33 42 11.16 - Z06 - L - 57 - ST | 1 | 2026-02-16 | 2026-02-17 |  |  | FALSE | yes
| JD3RZ06L57ST25201 | Primary Test for GRP Pipe Line 1000 mm - depth from 2.51 to 3.50 m - B6.33 42 11.16 - Z06 - L - 57 - ST | 1 | 2026-02-18 | 2026-02-19 |  |  | FALSE | yes
| JD3RZ06L57ST25202 | Backfilling Works for GRP Pipe Line 1000 mm - depth from 2.51 to 3.50 m - B6.33 42 11.16 - Z06 - L - 57 - ST | 1 | 2026-02-22 | 2026-02-23 |  |  | FALSE | yes
| JD3RZ06L57ST25260 | Backfilling Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - Z06 - L - 57 - ST | 1 | 2025-12-02 | 2025-12-03 | 2025-10-20 |  | FALSE | yes
| JD3RZ06L57ST25268 | Excavation Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - Z06 - L - 57 - ST | 1 | 2025-11-01 | 2025-11-10 | 2025-09-03 |  | FALSE | yes
| JD3RZ06L57ST25269 | Plain Concrete Works For Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - Z06 - L - 57 - ST | 1 | 2025-11-11 | 2025-11-13 | 2025-09-06 |  | FALSE | yes
| JD3RZ06L57ST25270 | Raft Foundation for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - Z06 - L - 57 - ST | 1 | 2025-11-15 | 2025-11-27 | 2025-09-09 |  | FALSE | yes
| JD3RZ06L57ST25271 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.06 - Z06 - L - 57 - ST | 1 | 2025-11-29 | 2025-12-22 | 2025-09-13 |  | FALSE | yes
| JD3RZ06L57ST25272 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.06 - Z06 - L - 57 - ST | 1 | 2025-12-23 | 2026-01-15 | 2025-09-14 |  | FALSE | yes
| JD3RZ06L57ST25273 | Isolation Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - Z06 - L - 57 - ST | 1 | 2026-01-17 | 2026-01-29 | 2025-09-16 |  | FALSE | yes
| JD3RZ06L57ST25274 | Backfilling Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - Z06 - L - 57 - ST | 1 | 2026-01-31 | 2026-02-04 | 2025-09-18 |  | FALSE | yes
| JD3RZ06L57ST25301.R | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z06 - L - 57 - ST - Remaining | 1 | 2026-02-18 | 2026-02-19 |  |  | FALSE | yes
| JD3RZ06L57ST25302.R | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z06 - L - 57 - ST - Remainin | 1 | 2026-02-21 | 2026-02-22 |  |  | FALSE | yes
| JD3RZ06L57ST25303.R | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z06 - L - 57 - ST - Remaini | 1 | 2026-02-23 | 2026-02-24 | 2025-08-14 |  | FALSE | yes
| JD3RZ06L57ST25304 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z06 - L - 57 - S | 1 | 2026-02-25 | 2026-02-26 |  |  | FALSE | yes
| JD3RZ06L57ST25305 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z06 - L - 57 - ST | 1 | 2026-02-28 | 2026-03-01 |  |  | FALSE | yes
| JD3RZ06L57ST25314 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z06 - L - 57 - S | 1 | 2026-02-28 | 2026-03-01 |  |  | FALSE | yes
| JD3RZ06L57ST25315 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z06 - L - 57 - ST | 1 | 2026-03-02 | 2026-03-03 |  |  | FALSE | yes
| JD3RZ06L57ST25316.R | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z06 - L - 57 - ST - Remaining | 1 | 2026-02-14 | 2026-02-15 |  |  | FALSE | yes
| JD3RZ06L57ST25317 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z06 - L - 57 - ST | 1 | 2026-02-16 | 2026-02-19 |  |  | FALSE | yes
| JD3RZ06L57ST25318 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z06 - L - 57 - ST | 1 | 2026-02-21 | 2026-02-24 |  |  | FALSE | yes
| JD3RZ06L57ST25319 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z06 - L - 57 - S | 1 | 2026-02-25 | 2026-02-26 |  |  | FALSE | yes
| JD3RZ06L57ST25320 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z06 - L - 57 - ST | 1 | 2026-02-28 | 2026-03-01 |  |  | FALSE | yes
| JD3RZ06L57ST25331 | Excavation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z06 - L - 57 - ST | 1 | 2026-02-18 | 2026-02-19 | 2025-08-09 |  | FALSE | yes
| JD3RZ06L57ST25332 | Base Plain Concrete Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z06 - L - 57 - ST | 1 | 2026-02-21 | 2026-02-22 | 2025-08-12 |  | FALSE | yes
| JD3RZ06L57ST25333 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z06 - L - 57 - ST | 1 | 2026-02-23 | 2026-02-24 | 2025-08-15 |  | FALSE | yes
| JD3RZ06L57ST25334 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z06 - L - 57 - S | 1 | 2026-02-25 | 2026-02-26 |  |  | FALSE | yes
| JD3RZ06L57ST25335 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z06 - L - 57 - ST | 1 | 2026-03-01 | 2026-03-02 |  |  | FALSE | yes
| JD3RZ06L57ST25336 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - Z06 - L - 57 - ST | 1 | 2026-02-21 | 2026-02-23 |  |  | FALSE | yes
| JD3RZ06L57ST25337 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - Z06 - L - 57 - ST | 1 | 2026-02-24 | 2026-02-28 |  |  | FALSE | yes
| JD3RZ06L57ST25338 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - Z06 - L - 57 - ST | 1 | 2026-03-01 | 2026-03-04 |  |  | FALSE | yes
| JD3RZ06L57ST25339 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - Z06 - L - 57 - ST | 1 | 2026-03-05 | 2026-03-08 |  |  | FALSE | yes
| JD3RZ06L57ST25340 | EXCAVATION Works for Catchbasine double - B6.33 05 39.10 - Z06 - L - 57 - ST | 1 | 2026-02-24 | 2026-02-26 |  |  | FALSE | yes
| JD3RZ06L57ST25341 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - Z06 - L - 57 - ST | 1 | 2026-02-28 | 2026-03-03 |  |  | FALSE | yes
| JD3RZ06L57ST25342 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z06 - L - 57 - ST | 1 | 2026-03-04 | 2026-03-08 |  |  | FALSE | yes
| JD3RZ06L57ST25343 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z06 - L - 57 - ST | 1 | 2026-03-09 | 2026-03-11 |  |  | FALSE | yes
| JD3RZ06L57ST524354 | Concrete encasement for pipes - NNB6.33 42 11.25 - Z06 - L - 57 - ST | 1 | 2026-02-18 | 2026-02-24 |  |  | FALSE | yes
| JD3RZ06L57TSE25394 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z06 - L - 57 - TSE | 1 | 2026-03-12 | 2026-03-14 |  |  | FALSE | yes
| JD3RZ06L57TSE25395 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z06 - L - 57 - T | 1 | 2026-03-15 | 2026-03-16 |  |  | FALSE | yes
| JD3RZ06L57TSE25396 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z06 - L - 57 - TSE | 1 | 2026-03-17 | 2026-03-18 |  |  | FALSE | yes
| JD3RZ06L57TSE25397 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z06 - L - 57 - TSE | 1 | 2026-03-19 | 2026-03-21 |  |  | FALSE | yes
| JD3RZ06L57TSE25398 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z06 - L - 57 - TSE | 1 | 2026-03-30 | 2026-03-31 |  |  | FALSE | yes
| JD3RZ06L57TSE25399 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z06 - L - 57 - TSE | 1 | 2026-03-12 | 2026-03-15 |  |  | FALSE | yes
| JD3RZ06L57TSE25400 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z06 - L - 57 - T | 1 | 2026-03-16 | 2026-03-19 |  |  | FALSE | yes
| JD3RZ06L57TSE25401 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z06 - L - 57 - TSE | 1 | 2026-03-21 | 2026-03-24 |  |  | FALSE | yes
| JD3RZ06L57TSE25402 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z06 - L - 57 - TSE | 1 | 2026-03-25 | 2026-03-29 |  |  | FALSE | yes
| JD3RZ06L57TSE25403 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z06 - L - 57 - TSE | 1 | 2026-03-30 | 2026-04-02 |  |  | FALSE | yes
| JD3RZ06L57TSE25519 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z06 - L - 57 - TSE | 1 | 2026-03-25 | 2026-03-26 |  |  | FALSE | yes
| JD3RZ06L57TSE25520 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z06 - L - 57 - TSE | 1 | 2026-03-28 | 2026-03-29 |  |  | FALSE | yes
| JD3RZ06L57TSE25521 | Installationfor gate valves 250 mm - B4.33 14 19.02 - Z06 - L - 57 - TSE | 1 | 2026-03-25 | 2026-03-26 |  |  | FALSE | yes
| JD3RZ06L57TSE25522 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - Z06 - L - 57 - TSE | 1 | 2026-03-28 | 2026-03-29 |  |  | FALSE | yes
| JD3RZ06L57WT25344 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z06 - L - 57 - WT | 1 | 2026-04-04 | 2026-04-05 |  |  | FALSE | yes
| JD3RZ06L57WT25345 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z06 - L - 57 - WT | 1 | 2026-04-06 | 2026-04-07 |  |  | FALSE | yes
| JD3RZ06L57WT25346 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z06 - L - 57 - WT | 1 | 2026-04-08 | 2026-04-09 |  |  | FALSE | yes
| JD3RZ06L57WT25347 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z06 - L - 57 - WT | 1 | 2026-04-11 | 2026-04-12 |  |  | FALSE | yes
| JD3RZ06L57WT25348 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z06 - L - 57 - WT | 1 | 2026-04-13 | 2026-04-14 |  |  | FALSE | yes
| JD3RZ06L57WT25379 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z06 - L - 57 - WT | 1 | 2026-04-04 | 2026-04-05 |  |  | FALSE | yes
| JD3RZ06L57WT25380 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z06 - L - 57 - WT | 1 | 2026-04-06 | 2026-04-07 |  |  | FALSE | yes
| JD3RZ06L57WT25381 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z06 - L - 57 - WT | 1 | 2026-04-08 | 2026-04-09 |  |  | FALSE | yes
| JD3RZ07-1L59SL32030 | Excavation Worksfor Copper Cables 4Cx16 mm² - B2.26 05 19.03 - Z07 - 1 - L - 59 - SL | 1 | 2024-12-29 | 2024-12-31 |  |  | FALSE | yes
| JD3RZ07-1L59SL32031 | Installationfor Copper Cables 4Cx16 mm² - B2.26 05 19.03 - Z07 - 1 - L - 59 - SL | 1 | 2025-01-01 | 2025-01-04 |  |  | FALSE | yes
| JD3RZ07-1L59SL32032 | Backfilling, Warning Tabe Worksfor Copper Cables 4Cx16 mm² - B2.26 05 19.03 - Z07 - 1 - L - 59 - SL | 1 | 2025-01-05 | 2025-01-07 |  |  | FALSE | yes
| JD3RZ07-1L59SL32033 | Testing and Commitioning for Copper Cables 4Cx16 mm² - B2.26 05 19.03 - Z07 - 1 - L - 59 - SL | 1 | 2025-01-12 | 2025-01-14 |  |  | FALSE | yes
| JD3RZ07-1L59SL32046 | INSTALLINGfor insulated copper conductor 6 mm² - B2.26 05 19.07 - Z07 - 1 - L - 59 - SL | 1 | 2025-01-05 | 2025-01-07 |  |  | FALSE | yes
| JD3RZ07-1L59SL32047 | TESTING AND COMMITIONINGfor insulated copper conductor 6 mm² - B2.26 05 19.07 - Z07 - 1 - L - 59 - SL | 1 | 2025-01-08 | 2025-01-11 |  |  | FALSE | yes
| JD3RZ07-1L59SL32055 | Excavation of reinforced concrete foundationfor LIGHTING POLE one arm - B2.26 56 19.02 - Z07 - 1 - L - 59 - SL | 1 | 2025-01-01 | 2025-01-02 |  |  | FALSE | yes
| JD3RZ07-1L59SL32056 | Installation of reinforced concrete foundationfor LIGHTING POLE one arm - B2.26 56 19.02 - Z07 - 1 - L - 59 - SL | 1 | 2025-01-04 | 2025-01-06 |  |  | FALSE | yes
| JD3RZ07-1L59SL32057 | Backfilling of reinforced concrete foundationfor LIGHTING POLE one arm - B2.26 56 19.02 - Z07 - 1 - L - 59 - SL | 1 | 2025-01-07 | 2025-01-08 |  |  | FALSE | yes
| JD3RZ07-1L59SL32058 | Installation Worksfor LIGHTING POLE one arm - B2.26 56 19.02 - Z07 - 1 - L - 59 - SL | 1 | 2025-01-09 | 2025-01-14 |  |  | FALSE | yes
| JD3RZ07-1L59SL32059 | Testing and Commitioningfor LIGHTING POLE one arm - B2.26 56 19.02 - Z07 - 1 - L - 59 - SL | 1 | 2025-01-15 | 2025-01-20 |  |  | FALSE | yes
| JD3RZ07-1L59SL32060 | Installationfor Lighting( LED ) Luminaire 150 WATT - B2.26.56.19.01 - Z07 - 1 - L - 59 - SL | 1 | 2025-01-07 | 2025-01-08 |  |  | FALSE | yes
| JD3RZ07-1L59SL32063 | Supply, construct, connect and test earthing pitsfor Street Lighting EARTHING SYSTEM - B2.26 05 26.01 - Z07 - 1 - L - 59 | 1 | 2025-01-09 | 2025-01-11 |  |  | FALSE | yes
| JD3RZ07-1L59SL32064 | Excavation Worksfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - Z07 - 1 - L - 59 - SL | 1 | 2025-01-04 | 2025-01-05 |  |  | FALSE | yes
| JD3RZ07-1L59SL32065 | Installationfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - Z07 - 1 - L - 59 - SL | 1 | 2025-01-06 | 2025-01-07 |  |  | FALSE | yes
| JD3RZ07-1L59SL32066 | Pouring Concrete Coverfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - Z07 - 1 - L - 59 - SL | 1 | 2025-01-08 | 2025-01-09 |  |  | FALSE | yes
| JD3RZ07-1L59SL32067 | Testing and Backfilling Worksfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - Z07 - 1 - L - 59 - SL | 1 | 2025-01-11 | 2025-01-12 |  |  | FALSE | yes
| JD3RZ07-1L59SL32076 | Excavationfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - Z07 - 1 - L - 59 - SL | 1 | 2025-01-06 | 2025-01-07 |  |  | FALSE | yes
| JD3RZ07-1L59SL32077 | Installationfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - Z07 - 1 - L - 59 - SL | 1 | 2025-01-08 | 2025-01-11 |  |  | FALSE | yes
| JD3RZ07-1L59SL32078 | Backfillingfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - Z07 - 1 - L - 59 - SL | 1 | 2025-01-12 | 2025-01-13 |  |  | FALSE | yes
| JD3RZ07-1L59SL32079 | Excavationfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - Z07 - 1 - L - 59 - SL | 1 | 2025-01-08 | 2025-01-09 |  |  | FALSE | yes
| JD3RZ07-1L59SL32080 | Installationfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - Z07 - 1 - L - 59 - SL | 1 | 2025-01-11 | 2025-01-12 |  |  | FALSE | yes
| JD3RZ07-1L59SL32081 | Backfillingfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - Z07 - 1 - L - 59 - SL | 1 | 2025-01-13 | 2025-01-14 |  |  | FALSE | yes
| JD3RZ07-1L59SS31467.R | Finishing, Benching Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z07 - 1 - L - 59 - SS - Rema | 1 | 2024-09-25 | 2024-09-26 | 2025-08-11 |  | FALSE | FALSE
| JD3RZ07-1L59SS521401 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 3.51 to 4.50 - B5.33 05 13.05 - MR - C - 03 - SS | 1 | 2024-09-04 | 2024-09-05 |  |  | FALSE | yes
| JD3RZ07-1L59SS521411 | Installation of Base Works for Manholes 1200 mm - Depth from 3.51 to 4.50 - B5.33 05 13.05 - MR - C - 03 - SS | 1 | 2024-09-09 | 2024-09-10 |  |  | FALSE | yes
| JD3RZ07-1L59SS521421 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 3.51 to 4.50 - B5.33 05 13.05 - MR - | 1 | 2024-09-11 | 2024-09-12 |  |  | FALSE | yes
| JD3RZ07-1L59SS521431 | Backfilling Works for Manholes 1200 mm - Depth from 3.51 to 4.50 - B5.33 05 13.05 - MR - C - 03 - SS | 1 | 2024-09-14 | 2024-09-15 |  |  | FALSE | yes
| JD3RZ07-1L59SS521441 | Finishing, Benching Works for Manholes 1200 mm - Depth from 3.51 to 4.50 - B5.33 05 13.05 - MR - C - 03 - SS | 1 | 2024-09-16 | 2024-09-17 |  |  | FALSE | yes
| JD3RZ07-1L59ST31538 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - 1 - L - 59 - ST | 1 | 2024-09-28 | 2024-10-01 |  |  | FALSE | yes
| JD3RZ07-1L59ST31539 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - 1 - L - 59 - ST | 1 | 2024-10-26 | 2024-10-30 |  |  | FALSE | yes
| JD3RZ07-1L59ST31540.R | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - 1 - L - 59 - ST - Remaini | 1 | 2024-09-18 | 2024-09-19 | 2025-10-24 |  | FALSE | FALSE
| JD3RZ07-1L59ST31541.R | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - 1 - L - | 1 | 2024-09-21 | 2024-09-22 | 2025-10-26 |  | FALSE | FALSE
| JD3RZ07-1L59ST31542.R | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - 1 - L - 59 - ST - Remaining | 1 | 2024-09-24 | 2024-09-25 | 2025-10-27 |  | FALSE | FALSE
| JD3RZ07-1L59ST31543.R | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - 1 - L - 59 - ST - Remaining | 1 | 2024-09-26 | 2024-09-28 | 2025-08-30 |  | FALSE | FALSE
| JD3RZ07-1L59ST31544.R | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - 1 - L - 59 - ST - Remain | 1 | 2024-09-30 | 2024-10-01 | 2025-09-07 |  | FALSE | FALSE
| JD3RZ07-1L59ST31569.R | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - Z07 - 1 - L - 59 - ST - Remain | 1 | 2024-10-21 | 2024-10-22 | 2025-08-28 |  | FALSE | FALSE
| JD3RZ07-1L59ST31579 | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - Z07 - 1 - L - 59 - ST | 1 | 2024-10-21 | 2024-10-22 | 2025-08-30 |  | FALSE | FALSE
| JD3RZ07-1L59ST31589 | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - Z07 - 1 - L - 59 - ST | 1 | 2024-10-21 | 2024-10-22 | 2025-08-30 |  | FALSE | FALSE
| JD3RZ07-1L59ST31599 | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - Z07 - 1 - L - 59 - ST | 1 | 2024-10-21 | 2024-10-22 | 2025-08-30 |  | FALSE | FALSE
| JD3RZ07-1L59ST31614 | Backfilling Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m - B6.33 42 11.15 - Z07 - 1 - L - 59 - ST | 1 | 2024-10-03 | 2024-10-05 | 2025-08-30 |  | FALSE | FALSE
| JD3RZ07-1L59ST31720.R | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - 1 - L - 59 - ST - Rem | 1 | 2024-10-08 | 2024-10-09 |  |  | FALSE | yes
| JD3RZ07-1L59ST31721 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - 1 - L - 59 | 1 | 2024-10-10 | 2024-10-12 |  |  | FALSE | yes
| JD3RZ07-1L59ST31722 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - 1 - L - 59 - ST | 1 | 2024-10-13 | 2024-10-14 |  |  | FALSE | yes
| JD3RZ07-1L59ST31730.R | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - 1 - L - 59 - ST - Rem | 1 | 2024-10-10 | 2024-10-12 |  |  | FALSE | yes
| JD3RZ07-1L59ST31731 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - 1 - L - 59 | 1 | 2024-10-13 | 2024-10-14 |  |  | FALSE | yes
| JD3RZ07-1L59ST31732 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - 1 - L - 59 - ST | 1 | 2024-10-15 | 2024-10-16 |  |  | FALSE | yes
| JD3RZ07-1L59ST31733 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - 1 - L - 59 - ST | 1 | 2024-10-14 | 2024-10-15 | 2025-08-16 |  | FALSE | FALSE
| JD3RZ07-1L59ST31734 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - 1 - L - 59 - ST | 1 | 2024-10-16 | 2024-10-17 | 2025-08-18 |  | FALSE | FALSE
| JD3RZ07-1L59ST31735 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - 1 - L - 59 - ST | 1 | 2024-10-19 | 2024-10-20 |  |  | FALSE | yes
| JD3RZ07-1L59ST31736 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - 1 - L - 59 | 1 | 2024-10-21 | 2024-10-22 |  |  | FALSE | yes
| JD3RZ07-1L59ST31737 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - 1 - L - 59 - ST | 1 | 2024-10-23 | 2024-10-24 |  |  | FALSE | yes
| JD3RZ07-1L59ST31745 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - 1 - L - 59 - ST | 1 | 2024-10-06 | 2024-10-07 |  |  | FALSE | yes
| JD3RZ07-1L59ST31746 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - 1 - L - 59 | 1 | 2024-10-08 | 2024-10-09 |  |  | FALSE | yes
| JD3RZ07-1L59ST31747 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - 1 - L - 59 - ST | 1 | 2024-10-10 | 2024-10-12 |  |  | FALSE | yes
| JD3RZ07-1L59ST31750 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z07 - 1 - L - 59 - ST | 1 | 2024-10-21 | 2024-10-22 |  |  | FALSE | yes
| JD3RZ07-1L59ST31751 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z07 - 1 - L - 59 | 1 | 2024-10-23 | 2024-10-24 |  |  | FALSE | yes
| JD3RZ07-1L59ST31752 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z07 - 1 - L - 59 - ST | 1 | 2024-10-26 | 2024-10-27 |  |  | FALSE | yes
| JD3RZ07-1L59ST31754 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - Z07 - 1 - L - 59 - ST | 1 | 2024-10-22 | 2024-10-26 |  |  | FALSE | yes
| JD3RZ07-1L59ST31755 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - Z07 - 1 - L - 59 - ST | 1 | 2024-10-27 | 2024-10-30 |  |  | FALSE | yes
| JD3RZ07-1L59ST31756 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - Z07 - 1 - L - 59 - ST | 1 | 2024-10-31 | 2024-11-03 |  |  | FALSE | yes
| JD3RZ07-1L59ST31758 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - Z07 - 1 - L - 59 - ST | 1 | 2024-10-26 | 2024-10-29 |  |  | FALSE | yes
| JD3RZ07-1L59ST31759 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z07 - 1 - L - 59 - ST | 1 | 2024-10-30 | 2024-11-03 |  |  | FALSE | yes
| JD3RZ07-1L59ST31760 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z07 - 1 - L - 59 - ST | 1 | 2024-11-04 | 2024-11-06 |  |  | FALSE | yes
| JD3RZ07-1L59ST524359 | Concrete encasement for pipes - NNB6.33 42 11.25 - Z07 - 1 - L - 59 - ST | 1 | 2024-10-19 | 2024-10-24 |  |  | FALSE | yes
| JD3RZ07-1L59TC32091 | Excavation Worksfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z07 - 1 - L - 59 - TC | 1 | 2025-01-01 | 2025-01-02 |  |  | FALSE | yes
| JD3RZ07-1L59TC32092 | Installationfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z07 - 1 - L - 59 - TC | 1 | 2025-01-04 | 2025-01-07 |  |  | FALSE | yes
| JD3RZ07-1L59TC32093 | Pouring Concrete Coverfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z07 - 1 - L - 59 - | 1 | 2025-01-08 | 2025-01-12 |  |  | FALSE | yes
| JD3RZ07-1L59TC32094 | Backfilling Worksfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z07 - 1 - L - 59 - TC | 1 | 2025-01-13 | 2025-01-14 |  |  | FALSE | yes
| JD3RZ07-1L59TC32095 | Excavation and Bedding Worksfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z07 - 1 - L - 59 - TC | 1 | 2025-01-15 | 2025-01-16 |  |  | FALSE | yes
| JD3RZ07-1L59TC32096 | Installationfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z07 - 1 - L - 59 - TC | 1 | 2025-01-18 | 2025-01-19 |  |  | FALSE | yes
| JD3RZ07-1L59TC32097 | Backfilling Worksfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z07 - 1 - L - 59 - TC | 1 | 2025-01-21 | 2025-01-22 |  |  | FALSE | yes
| JD3RZ07-1L59TSE31811 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - 1 - L - 59 - TSE | 1 | 2024-11-07 | 2024-11-12 | 2025-08-07 |  | FALSE | FALSE
| JD3RZ07-1L59TSE31812 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - 1 - L - 59 | 1 | 2024-11-13 | 2024-11-18 | 2025-08-13 |  | FALSE | FALSE
| JD3RZ07-1L59TSE31813 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - 1 - L - 59 - TSE | 1 | 2024-11-19 | 2024-11-28 | 2025-08-18 |  | FALSE | FALSE
| JD3RZ07-1L59TSE31814 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - 1 - L - 59 - TSE | 1 | 2024-11-30 | 2024-12-05 | 2025-08-30 |  | FALSE | FALSE
| JD3RZ07-1L59TSE31815 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - 1 - L - 59 - TSE | 1 | 2024-12-07 | 2024-12-12 | 2025-08-06 |  | FALSE | FALSE
| JD3RZ07-1L59TSE31816 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z07 - 1 - L - 59 - TSE | 1 | 2024-11-13 | 2024-11-14 |  |  | FALSE | yes
| JD3RZ07-1L59TSE31817 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z07 - 1 - L - 59 | 1 | 2024-11-16 | 2024-11-17 |  |  | FALSE | yes
| JD3RZ07-1L59TSE31818 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z07 - 1 - L - 59 - TSE | 1 | 2024-11-18 | 2024-11-19 |  |  | FALSE | yes
| JD3RZ07-1L59TSE31819 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z07 - 1 - L - 59 - TSE | 1 | 2024-11-20 | 2024-11-21 |  |  | FALSE | yes
| JD3RZ07-1L59TSE31820 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z07 - 1 - L - 59 - TSE | 1 | 2024-12-07 | 2024-12-08 |  |  | FALSE | yes
| JD3RZ07-1L59TSE31936 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z07 - 1 - L - 59 - TSE | 1 | 2024-11-30 | 2024-12-01 |  |  | FALSE | yes
| JD3RZ07-1L59TSE31937 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z07 - 1 - L - 59 - TSE | 1 | 2024-12-04 | 2024-12-05 |  |  | FALSE | yes
| JD3RZ07-1L59WT31765 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - 1 - L - 59 - WT | 1 | 2024-12-21 | 2024-12-26 | 2025-08-30 |  | FALSE | FALSE
| JD3RZ07-1L59WT31786 | INSTALLATIONfor gate valves 150 mm - B3.33 14 19.01 - Z07 - 1 - L - 59 - WT | 1 | 2024-12-05 | 2024-12-07 |  |  | FALSE | yes
| JD3RZ07-1L59WT31787 | TESTING AND COMMITIONfor gate valves 150 mm - B3.33 14 19.01 - Z07 - 1 - L - 59 - WT | 1 | 2024-12-08 | 2024-12-09 |  |  | FALSE | yes
| JD3RZ07-1L59WT31796 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z07 - 1 - L - 59 - WT | 1 | 2024-12-14 | 2024-12-15 |  |  | FALSE | yes
| JD3RZ07-1L59WT31797 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z07 - 1 - L - 59 - WT | 1 | 2024-12-16 | 2024-12-17 |  |  | FALSE | yes
| JD3RZ07-1L59WT31798 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z07 - 1 - L - 59 - WT | 1 | 2024-12-18 | 2024-12-19 |  |  | FALSE | yes
| JD3RZ07-1L60SL32768 | Excavation of reinforced concrete foundationfor LIGHTING POLE one arm - B2.26 56 19.02 - Z07 - 1 - L - 60 - SL | 1 | 2024-12-30 | 2024-12-31 |  |  | FALSE | yes
| JD3RZ07-1L60SL32769 | Installation of reinforced concrete foundationfor LIGHTING POLE one arm - B2.26 56 19.02 - Z07 - 1 - L - 60 - SL | 1 | 2025-01-01 | 2025-01-04 |  |  | FALSE | yes
| JD3RZ07-1L60SL32770 | Backfilling of reinforced concrete foundationfor LIGHTING POLE one arm - B2.26 56 19.02 - Z07 - 1 - L - 60 - SL | 1 | 2025-01-05 | 2025-01-06 |  |  | FALSE | yes
| JD3RZ07-1L60SL32771 | Installation Worksfor LIGHTING POLE one arm - B2.26 56 19.02 - Z07 - 1 - L - 60 - SL | 1 | 2025-01-07 | 2025-01-12 |  |  | FALSE | yes
| JD3RZ07-1L60SL32772 | Testing and Commitioningfor LIGHTING POLE one arm - B2.26 56 19.02 - Z07 - 1 - L - 60 - SL | 1 | 2025-01-13 | 2025-01-18 |  |  | FALSE | yes
| JD3RZ07-1L60SL32773 | Installationfor Lighting( LED ) Luminaire 150 WATT - B2.26.56.19.01 - Z07 - 1 - L - 60 - SL | 1 | 2025-01-05 | 2025-01-06 |  |  | FALSE | yes
| JD3RZ07-1L60SL32776 | Supply, construct, connect and test earthing pitsfor Street Lighting EARTHING SYSTEM - B2.26 05 26.01 - Z07 - 1 - L - 60 | 1 | 2025-01-07 | 2025-01-08 |  |  | FALSE | yes
| JD3RZ07-1L60SL32777 | Excavation Worksfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - Z07 - 1 - L - 60 - SL | 1 | 2025-01-01 | 2025-01-02 |  |  | FALSE | yes
| JD3RZ07-1L60SL32778 | Installationfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - Z07 - 1 - L - 60 - SL | 1 | 2025-01-04 | 2025-01-05 |  |  | FALSE | yes
| JD3RZ07-1L60SL32779 | Pouring Concrete Coverfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - Z07 - 1 - L - 60 - SL | 1 | 2025-01-06 | 2025-01-07 |  |  | FALSE | yes
| JD3RZ07-1L60SL32780 | Testing and Backfilling Worksfor PVC Pipes 2×150mm - B2.33 71 19.01.SL - Z07 - 1 - L - 60 - SL | 1 | 2025-01-08 | 2025-01-09 |  |  | FALSE | yes
| JD3RZ07-1L60SL32789 | Excavationfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - Z07 - 1 - L - 60 - SL | 1 | 2025-01-04 | 2025-01-05 |  |  | FALSE | yes
| JD3RZ07-1L60SL32790 | Installationfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - Z07 - 1 - L - 60 - SL | 1 | 2025-01-06 | 2025-01-08 |  |  | FALSE | yes
| JD3RZ07-1L60SL32791 | Backfillingfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - Z07 - 1 - L - 60 - SL | 1 | 2025-01-09 | 2025-01-11 |  |  | FALSE | yes
| JD3RZ07-1L60SL32792 | Excavationfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - Z07 - 1 - L - 60 - SL | 1 | 2025-01-06 | 2025-01-07 |  |  | FALSE | yes
| JD3RZ07-1L60SL32793 | Installationfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - Z07 - 1 - L - 60 - SL | 1 | 2025-01-08 | 2025-01-09 |  |  | FALSE | yes
| JD3RZ07-1L60SL32794 | Backfillingfor Drawpit 900x900x1200mm - B2.33 71 19.13.02 - Z07 - 1 - L - 60 - SL | 1 | 2025-01-11 | 2025-01-12 |  |  | FALSE | yes
| JD3RZ07-1L60SS32131.R | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - Z07 - 1 - L - 6 | 1 | 2024-10-23 | 2024-10-24 | 2025-08-20 |  | FALSE | FALSE
| JD3RZ07-1L60SS32179 | Backfilling Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z07 - 1 - L - 60 - SS | 1 | 2024-10-26 | 2024-10-27 |  |  | FALSE | yes
| JD3RZ07-1L60SS32180 | Finishing, Benching Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z07 - 1 - L - 60 - SS | 1 | 2024-10-26 | 2024-10-27 |  |  | FALSE | yes
| JD3RZ07-1L60SS521401 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 3.51 to 4.50 - B5.33 05 13.05 - MR - C - 03 - SS | 1 | 2024-10-28 | 2024-10-29 | 2025-08-08 |  | FALSE | FALSE
| JD3RZ07-1L60SS521411 | Installation of Base Works for Manholes 1200 mm - Depth from 3.51 to 4.50 - B5.33 05 13.05 - MR - C - 03 - SS | 1 | 2024-10-30 | 2024-11-04 | 2025-08-14 |  | FALSE | FALSE
| JD3RZ07-1L60SS521421 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 3.51 to 4.50 - B5.33 05 13.05 - MR - | 1 | 2024-11-05 | 2024-11-10 | 2025-08-20 |  | FALSE | FALSE
| JD3RZ07-1L60SS521431 | Backfilling Works for Manholes 1200 mm - Depth from 3.51 to 4.50 - B5.33 05 13.05 - MR - C - 03 - SS | 1 | 2024-11-11 | 2024-11-13 |  |  | FALSE | yes
| JD3RZ07-1L60SS521441 | Finishing, Benching Works for Manholes 1200 mm - Depth from 3.51 to 4.50 - B5.33 05 13.05 - MR - C - 03 - SS | 1 | 2024-11-14 | 2024-11-16 |  |  | FALSE | yes
| JD3RZ07-1L60ST32249 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - 1 - L | 1 | 2024-10-29 | 2024-10-31 | 2025-09-09 |  | FALSE | FALSE
| JD3RZ07-1L60ST32250 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - 1 - L - 60 - ST | 1 | 2024-11-02 | 2024-11-05 | 2025-09-13 |  | FALSE | FALSE
| JD3RZ07-1L60ST32251 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - 1 - L - 60 - ST | 1 | 2024-11-06 | 2024-11-10 |  |  | FALSE | yes
| JD3RZ07-1L60ST32252 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - 1 - L - 60 - ST | 1 | 2024-12-16 | 2024-12-21 |  |  | FALSE | yes
| JD3RZ07-1L60ST32253.R | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - 1 - L - 60 - ST - Remaini | 1 | 2024-10-29 | 2024-10-30 | 2025-08-02 |  | FALSE | FALSE
| JD3RZ07-1L60ST32254.R | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - 1 - L - | 1 | 2024-10-31 | 2024-11-02 | 2025-08-04 |  | FALSE | FALSE
| JD3RZ07-1L60ST32255.R | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - 1 - L - 60 - ST - Remaining | 1 | 2024-11-03 | 2024-11-04 | 2025-08-07 |  | FALSE | FALSE
| JD3RZ07-1L60ST32256.R | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - 1 - L - 60 - ST - Remaining | 1 | 2024-11-05 | 2024-11-06 | 2025-08-09 |  | FALSE | FALSE
| JD3RZ07-1L60ST32257 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - 1 - L - 60 - ST | 1 | 2024-11-07 | 2024-11-09 | 2025-08-11 |  | FALSE | FALSE
| JD3RZ07-1L60ST32302.R | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - Z07 - 1 - L - 60 - ST - Remain | 1 | 2024-11-12 | 2024-11-13 | 2025-08-30 |  | FALSE | FALSE
| JD3RZ07-1L60ST32342 | Backfilling Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m - B6.33 42 11.20 - Z07 - 1 - L - 60 - ST | 1 | 2024-12-11 | 2024-12-12 | 2025-08-30 |  | FALSE | FALSE
| JD3RZ07-1L60ST32357 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - Z07 - 1 - L - 60 - ST | 1 | 2024-12-11 | 2024-12-12 | 2025-08-30 |  | FALSE | FALSE
| JD3RZ07-1L60ST32434 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - 1 - L - 60 | 1 | 2024-12-14 | 2024-12-15 |  |  | FALSE | yes
| JD3RZ07-1L60ST32435 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - 1 - L - 60 - ST | 1 | 2024-12-16 | 2024-12-17 |  |  | FALSE | yes
| JD3RZ07-1L60ST32443.R | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - 1 - L - 60 - ST - Rem | 1 | 2024-12-14 | 2024-12-15 |  |  | FALSE | yes
| JD3RZ07-1L60ST32444 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - 1 - L - 60 | 1 | 2024-12-16 | 2024-12-17 |  |  | FALSE | yes
| JD3RZ07-1L60ST32445 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - 1 - L - 60 - ST | 1 | 2024-12-18 | 2024-12-19 |  |  | FALSE | yes
| JD3RZ07-1L60ST32449 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - 1 - L - 60 | 1 | 2024-12-18 | 2024-12-19 |  |  | FALSE | yes
| JD3RZ07-1L60ST32450 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - 1 - L - 60 - ST | 1 | 2024-12-21 | 2024-12-22 |  |  | FALSE | yes
| JD3RZ07-1L60ST32459 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - 1 - L - 60 | 1 | 2024-12-21 | 2024-12-22 |  |  | FALSE | yes
| JD3RZ07-1L60ST32460 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - 1 - L - 60 - ST | 1 | 2024-12-23 | 2024-12-24 |  |  | FALSE | yes
| JD3RZ07-1L60ST32464 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z07 - 1 - L - 60 | 1 | 2024-12-23 | 2024-12-24 |  |  | FALSE | yes
| JD3RZ07-1L60ST32465 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z07 - 1 - L - 60 - ST | 1 | 2024-12-25 | 2024-12-26 |  |  | FALSE | yes
| JD3RZ07-1L60ST32467 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - Z07 - 1 - L - 60 - ST | 1 | 2024-11-20 | 2024-11-24 | 2025-10-11 |  | FALSE | FALSE
| JD3RZ07-1L60ST32468 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - Z07 - 1 - L - 60 - ST | 1 | 2024-11-25 | 2024-11-28 |  |  | FALSE | yes
| JD3RZ07-1L60ST32469 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - Z07 - 1 - L - 60 - ST | 1 | 2024-11-30 | 2024-12-02 |  |  | FALSE | yes
| JD3RZ07-1L60ST32471 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - Z07 - 1 - L - 60 - ST | 1 | 2024-11-23 | 2024-11-25 | 2025-10-12 |  | FALSE | FALSE
| JD3RZ07-1L60ST32472 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z07 - 1 - L - 60 - ST | 1 | 2024-11-26 | 2024-11-28 |  |  | FALSE | yes
| JD3RZ07-1L60ST32473 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z07 - 1 - L - 60 - ST | 1 | 2024-11-30 | 2024-12-01 |  |  | FALSE | yes
| JD3RZ07-1L60ST524360 | Concrete encasement for pipes - NNB6.33 42 11.25 - Z07 - 1 - L - 60 - ST | 1 | 2024-12-09 | 2024-12-15 |  |  | FALSE | yes
| JD3RZ07-1L60TC32804 | Excavation Worksfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z07 - 1 - L - 60 - TC | 1 | 2025-01-01 | 2025-01-02 |  |  | FALSE | yes
| JD3RZ07-1L60TC32805 | Installationfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z07 - 1 - L - 60 - TC | 1 | 2025-01-04 | 2025-01-07 |  |  | FALSE | yes
| JD3RZ07-1L60TC32806 | Pouring Concrete Coverfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z07 - 1 - L - 60 - | 1 | 2025-01-08 | 2025-01-12 |  |  | FALSE | yes
| JD3RZ07-1L60TC32807 | Backfilling Worksfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z07 - 1 - L - 60 - TC | 1 | 2025-01-13 | 2025-01-14 |  |  | FALSE | yes
| JD3RZ07-1L60TC32808 | Excavation and Bedding Worksfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z07 - 1 - L - 60 - TC | 1 | 2025-01-13 | 2025-01-14 |  |  | FALSE | yes
| JD3RZ07-1L60TC32809 | Installationfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z07 - 1 - L - 60 - TC | 1 | 2025-01-15 | 2025-01-16 |  |  | FALSE | yes
| JD3RZ07-1L60TC32810 | Backfilling Worksfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z07 - 1 - L - 60 - TC | 1 | 2025-01-18 | 2025-01-19 |  |  | FALSE | yes
| JD3RZ07-1L60TSE32649 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z07 - 1 - L - 60 - TSE | 1 | 2024-12-10 | 2024-12-11 |  |  | FALSE | yes
| JD3RZ07-1L60TSE32650 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z07 - 1 - L - 60 - TSE | 1 | 2024-12-12 | 2024-12-14 |  |  | FALSE | yes
| JD3RZ07-1L60WT32474.R | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - 1 - L - 60 - WT - Remaining | 1 | 2024-11-25 | 2024-11-26 |  |  | FALSE | yes
| JD3RZ07-1L60WT32475.R | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - 1 - L - 60 - W | 1 | 2024-12-02 | 2024-12-03 |  |  | FALSE | yes
| JD3RZ07-1L60WT32476.R | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - 1 - L - 60 - WT - Remaining | 1 | 2024-12-15 | 2024-12-16 |  |  | FALSE | yes
| JD3RZ07-1L60WT32477.R | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - 1 - L - 60 - WT - Remaining | 1 | 2024-12-22 | 2024-12-23 |  |  | FALSE | yes
| JD3RZ07-1L60WT32478.R | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - 1 - L - 60 - WT - Remaining | 1 | 2024-12-24 | 2024-12-25 |  |  | FALSE | yes
| JD3RZ07-1L60WT32499 | INSTALLATIONfor gate valves 150 mm - B3.33 14 19.01 - Z07 - 1 - L - 60 - WT | 1 | 2024-12-17 | 2024-12-18 |  |  | FALSE | yes
| JD3RZ07-1L60WT32500 | TESTING AND COMMITIONfor gate valves 150 mm - B3.33 14 19.01 - Z07 - 1 - L - 60 - WT | 1 | 2024-12-19 | 2024-12-21 |  |  | FALSE | yes
| JD3RZ07-1L60WT32509 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z07 - 1 - L - 60 - WT | 1 | 2024-12-22 | 2024-12-23 |  |  | FALSE | yes
| JD3RZ07-1L60WT32510 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z07 - 1 - L - 60 - WT | 1 | 2024-12-24 | 2024-12-26 |  |  | FALSE | yes
| JD3RZ07-1L60WT32511 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z07 - 1 - L - 60 - WT | 1 | 2024-12-28 | 2024-12-29 |  |  | FALSE | yes
| JD3RZ07-1L62SL34161 | Excavation Worksfor Copper Cables 4Cx6 mm² - B2.26 05 19.01 - Z07 - 1 - L - 62 - SL | 1 | 2024-12-29 | 2025-01-01 |  |  | FALSE | yes
| JD3RZ07-1L62SL34162 | Installationfor Copper Cables 4Cx6 mm² - B2.26 05 19.01 - Z07 - 1 - L - 62 - SL | 1 | 2025-01-02 | 2025-01-06 |  |  | FALSE | yes
| JD3RZ07-1L62SL34163 | Backfilling, Warning Tabe Worksfor Copper Cables 4Cx6 mm² - B2.26 05 19.01 - Z07 - 1 - L - 62 - SL | 1 | 2025-01-07 | 2025-01-11 |  |  | FALSE | yes
| JD3RZ07-1L62SL34164 | Testing and Commitioning for Copper Cables 4Cx6 mm² - B2.26 05 19.01 - Z07 - 1 - L - 62 - SL | 1 | 2025-01-16 | 2025-01-20 |  |  | FALSE | yes
| JD3RZ07-1L62SL34185 | INSTALLINGfor insulated copper conductor 6 mm² - B2.26 05 19.07 - Z07 - 1 - L - 62 - SL | 1 | 2025-01-07 | 2025-01-11 |  |  | FALSE | yes
| JD3RZ07-1L62SL34186 | TESTING AND COMMITIONINGfor insulated copper conductor 6 mm² - B2.26 05 19.07 - Z07 - 1 - L - 62 - SL | 1 | 2025-01-12 | 2025-01-15 |  |  | FALSE | yes
| JD3RZ07-1L62SL34194 | Excavation of reinforced concrete foundationfor LIGHTING POLE one arm - B2.26 56 19.02 - Z07 - 1 - L - 62 - SL | 1 | 2025-01-02 | 2025-01-04 |  |  | FALSE | yes
| JD3RZ07-1L62SL34195 | Installation of reinforced concrete foundationfor LIGHTING POLE one arm - B2.26 56 19.02 - Z07 - 1 - L - 62 - SL | 1 | 2025-01-05 | 2025-01-07 |  |  | FALSE | yes
| JD3RZ07-1L62SL34196 | Backfilling of reinforced concrete foundationfor LIGHTING POLE one arm - B2.26 56 19.02 - Z07 - 1 - L - 62 - SL | 1 | 2025-01-08 | 2025-01-09 |  |  | FALSE | yes
| JD3RZ07-1L62SL34197 | Installation Worksfor LIGHTING POLE one arm - B2.26 56 19.02 - Z07 - 1 - L - 62 - SL | 1 | 2025-01-11 | 2025-01-15 |  |  | FALSE | yes
| JD3RZ07-1L62SL34198 | Testing and Commitioningfor LIGHTING POLE one arm - B2.26 56 19.02 - Z07 - 1 - L - 62 - SL | 1 | 2025-01-16 | 2025-01-21 |  |  | FALSE | yes
| JD3RZ07-1L62SL34199 | Installationfor Lighting( LED ) Luminaire 150 WATT - B2.26.56.19.01 - Z07 - 1 - L - 62 - SL | 1 | 2025-01-08 | 2025-01-09 |  |  | FALSE | yes
| JD3RZ07-1L62SL34202 | Supply, construct, connect and test earthing pitsfor Street Lighting EARTHING SYSTEM - B2.26 05 26.01 - Z07 - 1 - L - 62 | 1 | 2025-01-11 | 2025-01-12 |  |  | FALSE | yes
| JD3RZ07-1L62SL34215 | Excavationfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - Z07 - 1 - L - 62 - SL | 1 | 2025-01-13 | 2025-01-14 |  |  | FALSE | yes
| JD3RZ07-1L62SL34216 | Installationfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - Z07 - 1 - L - 62 - SL | 1 | 2025-01-15 | 2025-01-18 |  |  | FALSE | yes
| JD3RZ07-1L62SL34217 | Backfillingfor Drawpit 600x600x1000mm - B2.33 71 19.13.01 - Z07 - 1 - L - 62 - SL | 1 | 2025-01-19 | 2025-01-20 |  |  | FALSE | yes
| JD3RZ07-1L62SS33567.R | Backfilling and warning tabe Works for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50 - B5.33 31 00.11 - Z07 - 1 - L - 6 | 1 | 2024-10-14 | 2024-10-15 | 2025-09-14 |  | FALSE | FALSE
| JD3RZ07-1L62SS33572 | Backfilling and warning tabe Works for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50 - B5.33 31 00.12 - Z07 - 1 - L - 6 | 1 | 2024-09-14 | 2024-09-15 |  |  | FALSE | yes
| JD3RZ07-1L62SS33604.R | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z07 | 1 | 2024-09-18 | 2024-09-19 | 2025-10-04 |  | FALSE | FALSE
| JD3RZ07-1L62SS33605 | Backfilling Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z07 - 1 - L - 62 - SS | 1 | 2024-09-21 | 2024-09-22 |  |  | FALSE | yes
| JD3RZ07-1L62SS33606 | Finishing, Benching Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z07 - 1 - L - 62 - SS | 1 | 2024-09-24 | 2024-09-25 |  |  | FALSE | yes
| JD3RZ07-1L62SS521431 | Backfilling Works for Manholes 1200 mm - Depth from 3.51 to 4.50 - B5.33 05 13.05 - MR - C - 03 - SS | 1 | 2024-10-07 | 2024-10-09 |  |  | FALSE | yes
| JD3RZ07-1L62SS521441 | Finishing, Benching Works for Manholes 1200 mm - Depth from 3.51 to 4.50 - B5.33 05 13.05 - MR - C - 03 - SS | 1 | 2024-10-10 | 2024-10-13 |  |  | FALSE | yes
| JD3RZ07-1L62ST33677 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - 1 - L - 62 - ST | 1 | 2024-09-18 | 2024-09-22 |  |  | FALSE | yes
| JD3RZ07-1L62ST33678 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - 1 - L - 62 - ST | 1 | 2024-10-05 | 2024-10-09 |  |  | FALSE | yes
| JD3RZ07-1L62ST33679 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - 1 - L - 62 - ST | 1 | 2024-09-10 | 2024-09-11 | 2025-08-07 |  | FALSE | FALSE
| JD3RZ07-1L62ST33680 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - 1 - L - | 1 | 2024-09-12 | 2024-09-14 | 2025-08-10 |  | FALSE | FALSE
| JD3RZ07-1L62ST33681 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - 1 - L - 62 - ST | 1 | 2024-09-15 | 2024-09-16 | 2025-08-12 |  | FALSE | FALSE
| JD3RZ07-1L62ST33682 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - 1 - L - 62 - ST | 1 | 2024-09-17 | 2024-09-18 | 2025-08-14 |  | FALSE | FALSE
| JD3RZ07-1L62ST33683 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - 1 - L - 62 - ST | 1 | 2024-10-05 | 2024-10-06 | 2025-08-28 |  | FALSE | FALSE
| JD3RZ07-1L62ST33708 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - Z07 - 1 - L - 62 - ST | 1 | 2024-10-05 | 2024-10-06 | 2025-08-30 |  | FALSE | FALSE
| JD3RZ07-1L62ST33728.R | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - Z07 - 1 - L - 62 - ST - Remain | 1 | 2024-10-13 | 2024-10-14 | 2025-08-30 |  | FALSE | FALSE
| JD3RZ07-1L62ST33738 | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - Z07 - 1 - L - 62 - ST | 1 | 2024-10-23 | 2024-10-24 | 2025-08-24 |  | FALSE | FALSE
| JD3RZ07-1L62ST33753 | Backfilling Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m - B6.33 42 11.15 - Z07 - 1 - L - 62 - ST | 1 | 2024-10-26 | 2024-10-27 | 2025-08-31 |  | FALSE | FALSE
| JD3RZ07-1L62ST33859 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - 1 - L - 62 - ST | 1 | 2024-10-21 | 2024-10-22 |  |  | FALSE | yes
| JD3RZ07-1L62ST33860 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - 1 - L - 62 | 1 | 2024-10-23 | 2024-10-24 |  |  | FALSE | yes
| JD3RZ07-1L62ST33861 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - 1 - L - 62 - ST | 1 | 2024-10-26 | 2024-10-27 |  |  | FALSE | yes
| JD3RZ07-1L62ST33869.R | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - 1 - L - 62 - ST - Rem | 1 | 2024-10-05 | 2024-10-06 |  |  | FALSE | yes
| JD3RZ07-1L62ST33870 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - 1 - L - 62 | 1 | 2024-10-07 | 2024-10-08 |  |  | FALSE | yes
| JD3RZ07-1L62ST33871 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - 1 - L - 62 - ST | 1 | 2024-10-09 | 2024-10-10 |  |  | FALSE | yes
| JD3RZ07-1L62ST33884.R | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - 1 - L - 62 - ST - Rem | 1 | 2024-10-05 | 2024-10-06 |  |  | FALSE | yes
| JD3RZ07-1L62ST33885 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - 1 - L - 62 | 1 | 2024-10-07 | 2024-10-08 |  |  | FALSE | yes
| JD3RZ07-1L62ST33886 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - 1 - L - 62 - ST | 1 | 2024-10-09 | 2024-10-10 |  |  | FALSE | yes
| JD3RZ07-1L62ST33889 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z07 - 1 - L - 62 - ST | 1 | 2024-10-23 | 2024-10-24 |  |  | FALSE | yes
| JD3RZ07-1L62ST33890 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z07 - 1 - L - 62 | 1 | 2024-10-26 | 2024-10-27 |  |  | FALSE | yes
| JD3RZ07-1L62ST33891 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z07 - 1 - L - 62 - ST | 1 | 2024-10-28 | 2024-10-29 |  |  | FALSE | yes
| JD3RZ07-1L62ST33892 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - Z07 - 1 - L - 62 - ST | 1 | 2024-10-16 | 2024-10-19 | 2025-10-05 |  | FALSE | FALSE
| JD3RZ07-1L62ST33893 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - Z07 - 1 - L - 62 - ST | 1 | 2024-10-20 | 2024-10-23 | 2025-10-07 |  | FALSE | FALSE
| JD3RZ07-1L62ST33894 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - Z07 - 1 - L - 62 - ST | 1 | 2024-10-24 | 2024-10-28 |  |  | FALSE | yes
| JD3RZ07-1L62ST33895 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - Z07 - 1 - L - 62 - ST | 1 | 2024-10-29 | 2024-10-31 |  |  | FALSE | yes
| JD3RZ07-1L62ST33896 | EXCAVATION Works for Catchbasine double - B6.33 05 39.10 - Z07 - 1 - L - 62 - ST | 1 | 2024-10-16 | 2024-10-17 | 2025-10-20 |  | FALSE | FALSE
| JD3RZ07-1L62ST33897 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - Z07 - 1 - L - 62 - ST | 1 | 2024-10-19 | 2024-10-21 |  |  | FALSE | yes
| JD3RZ07-1L62ST33898 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z07 - 1 - L - 62 - ST | 1 | 2024-10-22 | 2024-10-24 |  |  | FALSE | yes
| JD3RZ07-1L62ST33899 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z07 - 1 - L - 62 - ST | 1 | 2024-10-26 | 2024-10-27 |  |  | FALSE | yes
| JD3RZ07-1L62ST524361 | Concrete encasement for pipes - NNB6.33 42 11.25 - Z07 - 1 - L - 60 - ST | 1 | 2024-09-28 | 2024-10-03 |  |  | FALSE | yes
| JD3RZ07-1L62TC34230 | Excavation Worksfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z07 - 1 - L - 62 - TC | 1 | 2025-01-02 | 2025-01-04 |  |  | FALSE | yes
| JD3RZ07-1L62TC34231 | Installationfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z07 - 1 - L - 62 - TC | 1 | 2025-01-05 | 2025-01-08 |  |  | FALSE | yes
| JD3RZ07-1L62TC34232 | Pouring Concrete Coverfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z07 - 1 - L - 62 - | 1 | 2025-01-09 | 2025-01-13 |  |  | FALSE | yes
| JD3RZ07-1L62TC34233 | Backfilling Worksfor Trenches 6 - ways ducts, 50mm - 1x110 MM & 5 x 32MM - B2.33 71 19.02.TEL - Z07 - 1 - L - 62 - TC | 1 | 2025-01-14 | 2025-01-15 |  |  | FALSE | yes
| JD3RZ07-1L62TC34234 | Excavation and Bedding Worksfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z07 - 1 - L - 62 - TC | 1 | 2025-01-22 | 2025-01-23 |  |  | FALSE | yes
| JD3RZ07-1L62TC34235 | Installationfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z07 - 1 - L - 62 - TC | 1 | 2025-01-25 | 2025-01-26 |  |  | FALSE | yes
| JD3RZ07-1L62TC34236 | Backfilling Worksfor Manhole Type 1 - 120x120x150 CM - B2.33.71.19.13.01 - Z07 - 1 - L - 62 - TC | 1 | 2025-01-27 | 2025-01-28 |  |  | FALSE | yes
| JD3RZ07-1L62TSE33950 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - 1 - L - 62 - TSE | 1 | 2024-11-02 | 2024-11-03 |  |  | FALSE | yes
| JD3RZ07-1L62TSE33951 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - 1 - L - 62 | 1 | 2024-11-04 | 2024-11-05 |  |  | FALSE | yes
| JD3RZ07-1L62TSE33952 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - 1 - L - 62 - TSE | 1 | 2024-11-06 | 2024-11-07 |  |  | FALSE | yes
| JD3RZ07-1L62TSE33953 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - 1 - L - 62 - TSE | 1 | 2024-11-09 | 2024-11-10 |  |  | FALSE | yes
| JD3RZ07-1L62TSE33954 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - 1 - L - 62 - TSE | 1 | 2024-11-28 | 2024-11-30 |  |  | FALSE | yes
| JD3RZ07-1L62TSE34075 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z07 - 1 - L - 62 - TSE | 1 | 2024-11-23 | 2024-11-24 |  |  | FALSE | yes
| JD3RZ07-1L62TSE34076 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z07 - 1 - L - 62 - TSE | 1 | 2024-11-25 | 2024-11-26 |  |  | FALSE | yes
| JD3RZ07-1L62TSE34077 | Installationfor gate valves 250 mm - B4.33 14 19.02 - Z07 - 1 - L - 62 - TSE | 1 | 2024-11-23 | 2024-11-24 |  |  | FALSE | yes
| JD3RZ07-1L62TSE34078 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - Z07 - 1 - L - 62 - TSE | 1 | 2024-11-26 | 2024-11-27 |  |  | FALSE | yes
| JD3RZ07-1L62TSE34093 | Installationfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - Z07 - 1 - L - 62 - TSE | 1 | 2024-11-23 | 2024-11-24 |  |  | FALSE | yes
| JD3RZ07-1L62TSE34094 | Testing And Commtionningfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - Z07 - 1 - L - | 1 | 2024-11-25 | 2024-11-26 |  |  | FALSE | yes
| JD3RZ07-1L62TSE34123 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z07 - 1 - L - 62 - TSE | 1 | 2024-11-09 | 2024-11-10 |  |  | FALSE | yes
| JD3RZ07-1L62TSE34124 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z07 - 1 - L - 62 - TSE | 1 | 2024-11-11 | 2024-11-12 |  |  | FALSE | yes
| JD3RZ07-1L62TSE34125 | INSTALLATIONfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z07 - 1 - L - 62 - TSE | 1 | 2024-11-13 | 2024-11-14 |  |  | FALSE | yes
| JD3RZ07-1L62TSE34126 | Backfilling Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z07 - 1 - L - 62 - TSE | 1 | 2024-11-16 | 2024-11-17 |  |  | FALSE | yes
| JD3RZ07-1L62WT33900 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - 1 - L - 62 - WT | 1 | 2024-11-04 | 2024-11-09 | 2025-08-02 |  | FALSE | FALSE
| JD3RZ07-1L62WT33901 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - 1 - L - 62 - W | 1 | 2024-11-10 | 2024-11-14 | 2025-08-07 |  | FALSE | FALSE
| JD3RZ07-1L62WT33902 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - 1 - L - 62 - WT | 1 | 2024-11-16 | 2024-11-25 | 2025-08-13 |  | FALSE | FALSE
| JD3RZ07-1L62WT33903 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - 1 - L - 62 - WT | 1 | 2024-11-26 | 2024-12-02 | 2025-09-20 |  | FALSE | FALSE
| JD3RZ07-1L62WT33904 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - 1 - L - 62 - WT | 1 | 2024-12-03 | 2024-12-09 | 2025-08-26 |  | FALSE | FALSE
| JD3RZ07-1L62WT33905 | Excavation Worksfor HDPE Pipes 225 mm - depth from 0 to 1.5 m - B3.33 14 13.02 - Z07 - 1 - L - 62 - WT | 1 | 2024-11-10 | 2024-11-11 |  |  | FALSE | yes
| JD3RZ07-1L62WT33906 | Soil Replacement and Bedding Works for HDPE Pipes 225 mm - depth from 0 to 1.5 m - B3.33 14 13.02 - Z07 - 1 - L - 62 - W | 1 | 2024-11-13 | 2024-11-14 |  |  | FALSE | yes
| JD3RZ07-1L62WT33907 | Installing for HDPE Pipes 225 mm - depth from 0 to 1.5 m - B3.33 14 13.02 - Z07 - 1 - L - 62 - WT | 1 | 2024-11-16 | 2024-11-17 |  |  | FALSE | yes
| JD3RZ07-1L62WT33908 | Testing for HDPE Pipes 225 mm - depth from 0 to 1.5 m - B3.33 14 13.02 - Z07 - 1 - L - 62 - WT | 1 | 2024-11-18 | 2024-11-19 |  |  | FALSE | yes
| JD3RZ07-1L62WT33909 | Backfillingfor HDPE Pipes 225 mm - depth from 0 to 1.5 m - B3.33 14 13.02 - Z07 - 1 - L - 62 - WT | 1 | 2024-12-03 | 2024-12-04 |  |  | FALSE | yes
| JD3RZ07-1L62WT33925 | INSTALLATIONfor gate valves 150 mm - B3.33 14 19.01 - Z07 - 1 - L - 62 - WT | 1 | 2024-11-26 | 2024-11-27 |  |  | FALSE | yes
| JD3RZ07-1L62WT33926 | TESTING AND COMMITIONfor gate valves 150 mm - B3.33 14 19.01 - Z07 - 1 - L - 62 - WT | 1 | 2024-12-01 | 2024-12-02 |  |  | FALSE | yes
| JD3RZ07-1L62WT33935 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z07 - 1 - L - 62 - WT | 1 | 2024-11-12 | 2024-11-13 |  |  | FALSE | yes
| JD3RZ07-1L62WT33936 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z07 - 1 - L - 62 - WT | 1 | 2024-11-14 | 2024-11-16 |  |  | FALSE | yes
| JD3RZ07-1L62WT33937 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z07 - 1 - L - 62 - WT | 1 | 2024-11-17 | 2024-11-18 |  |  | FALSE | yes
| JD3RZ07C04ST259411 | Excavation Works for GRP Pipe Line 1400 mm - depth from 1.51 to 2.50 m - NNB6.33 42 11.25 - Z07 - C - 04 - ST | 1 | 2025-06-09 | 2025-06-11 |  |  | FALSE | yes
| JD3RZ07C04ST259421 | Soil Replacement and Bedding Works for GRP Pipe Line 1400 mm - depth from 1.51 to 2.50 m - NNB6.33 42 11.25 - Z07 - C - | 1 | 2025-06-12 | 2025-06-15 |  |  | FALSE | yes
| JD3RZ07C04ST259431 | Installing for GRP Pipe Line 1400 mm - depth from 1.51 to 2.50 m - NNB6.33 42 11.25 - Z07 - C - 04 - ST | 1 | 2025-06-16 | 2025-06-19 |  |  | FALSE | yes
| JD3RZ07C04ST259441 | Primary Test for GRP Pipe Line 1400 mm - depth from 1.51 to 2.50 m - NNB6.33 42 11.25 - Z07 - C - 04 - ST | 1 | 2025-07-05 | 2025-07-07 |  |  | FALSE | yes
| JD3RZ07C04ST259451 | Backfilling Works for GRP Pipe Line 1400 mm - depth from 1.51 to 2.50 m - NNB6.33 42 11.25 - Z07 - C - 04 - ST | 1 | 2025-07-08 | 2025-07-13 |  |  | FALSE | yes
| JD3RZ07C04ST25952.R | Backfilling Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.01 - Z07 - C - 04 - ST | 1 | 2025-05-05 | 2025-05-06 | 2025-08-13 |  | FALSE | FALSE
| JD3RZ07C04ST25967 | Excavation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - Z07 - C - 04 - ST | 1 | 2025-05-07 | 2025-05-08 |  |  | FALSE | yes
| JD3RZ07C04ST25968 | Plain Concrete Works For Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - Z07 - C - 04 - ST | 1 | 2025-05-10 | 2025-05-11 |  |  | FALSE | yes
| JD3RZ07C04ST25969 | Raft Foundation for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - Z07 - C - 04 - ST | 1 | 2025-05-12 | 2025-05-13 |  |  | FALSE | yes
| JD3RZ07C04ST25970 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - Z07 - C - 04 - ST | 1 | 2025-05-14 | 2025-05-17 |  |  | FALSE | yes
| JD3RZ07C04ST25971 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - Z07 - C - 04 - ST | 1 | 2025-05-18 | 2025-05-20 |  |  | FALSE | yes
| JD3RZ07C04ST25972 | Isolation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - Z07 - C - 04 - ST | 1 | 2025-05-21 | 2025-05-22 |  |  | FALSE | yes
| JD3RZ07C04ST25973 | Backfilling Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.35 42 16.04 - Z07 - C - 04 - ST | 1 | 2025-05-24 | 2025-05-25 |  |  | FALSE | yes
| JD3RZ07C04ST25974 | Excavation Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - Z07 - C - 04 - ST | 1 | 2025-05-26 | 2025-06-08 |  |  | FALSE | yes
| JD3RZ07C04ST25975 | Plain Concrete Works For Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - Z07 - C - 04 - ST | 1 | 2025-06-09 | 2025-06-17 |  |  | FALSE | yes
| JD3RZ07C04ST25976 | Raft Foundation for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - Z07 - C - 04 - ST | 1 | 2025-06-18 | 2025-07-07 |  |  | FALSE | yes
| JD3RZ07C04ST25977 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.05 - Z07 - C - 04 - ST | 1 | 2025-07-08 | 2025-07-31 |  |  | FALSE | yes
| JD3RZ07C04ST25978 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.05 - Z07 - C - 04 - ST | 1 | 2025-08-02 | 2025-08-25 |  |  | FALSE | yes
| JD3RZ07C04ST25979 | Isolation Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - Z07 - C - 04 - ST | 1 | 2025-08-26 | 2025-09-14 |  |  | FALSE | yes
| JD3RZ07C04ST25980 | Backfilling Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - B6.34 42 16.05 - Z07 - C - 04 - ST | 1 | 2025-09-15 | 2025-09-20 |  |  | FALSE | yes
| JD3RZ07C04ST25981 | Excavation Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - Z07 - C - 04 - ST | 1 | 2025-09-21 | 2025-10-01 |  |  | FALSE | yes
| JD3RZ07C04ST25982 | Plain Concrete Works For Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - Z07 - C - 04 - ST | 1 | 2025-10-02 | 2025-10-06 |  |  | FALSE | yes
| JD3RZ07C04ST25983 | Raft Foundation for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - Z07 - C - 04 - ST | 1 | 2025-10-07 | 2025-10-26 |  |  | FALSE | yes
| JD3RZ07C04ST25984 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.06 - Z07 - C - 04 - ST | 1 | 2025-10-27 | 2025-11-19 |  |  | FALSE | yes
| JD3RZ07C04ST25985 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - B6.34 42 16.06 - Z07 - C - 04 - ST | 1 | 2025-11-20 | 2025-12-14 |  |  | FALSE | yes
| JD3RZ07C04ST25986 | Isolation Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - Z07 - C - 04 - ST | 1 | 2025-12-15 | 2026-01-03 |  |  | FALSE | yes
| JD3RZ07C04ST25987 | Backfilling Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - B6.34 42 16.06 - Z07 - C - 04 - ST | 1 | 2026-01-04 | 2026-01-08 |  |  | FALSE | yes
| JD3RZ07C04ST26024 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - C - 04 - ST | 1 | 2025-06-12 | 2025-06-14 |  |  | FALSE | yes
| JD3RZ07C04ST26025 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - C - 04 - ST | 1 | 2025-06-15 | 2025-06-16 |  |  | FALSE | yes
| JD3RZ07C04ST26026 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - C - 04 - ST | 1 | 2025-06-17 | 2025-06-18 |  |  | FALSE | yes
| JD3RZ07C04ST26027 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - C - 04 - S | 1 | 2025-06-19 | 2025-06-21 |  |  | FALSE | yes
| JD3RZ07C04ST26028 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - C - 04 - ST | 1 | 2025-06-22 | 2025-06-23 |  |  | FALSE | yes
| JD3RZ07C04ST26029 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - C - 04 - ST | 1 | 2025-06-15 | 2025-06-17 |  |  | FALSE | yes
| JD3RZ07C04ST26030 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - C - 04 - ST | 1 | 2025-06-18 | 2025-06-24 |  |  | FALSE | yes
| JD3RZ07C04ST26031 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - C - 04 - ST | 1 | 2025-06-25 | 2025-07-01 |  |  | FALSE | yes
| JD3RZ07C04ST26032 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - C - 04 - S | 1 | 2025-07-02 | 2025-07-06 |  |  | FALSE | yes
| JD3RZ07C04ST26033 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - C - 04 - ST | 1 | 2025-07-07 | 2025-07-10 |  |  | FALSE | yes
| JD3RZ07C04ST26039 | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - C - 04 - ST | 1 | 2025-06-18 | 2025-06-19 |  |  | FALSE | yes
| JD3RZ07C04ST26040 | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - C - 04 - ST | 1 | 2025-06-21 | 2025-06-24 |  |  | FALSE | yes
| JD3RZ07C04ST26041 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - C - 04 - ST | 1 | 2025-06-25 | 2025-06-29 |  |  | FALSE | yes
| JD3RZ07C04ST26042 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - C - 04 - S | 1 | 2025-06-30 | 2025-07-01 |  |  | FALSE | yes
| JD3RZ07C04ST26043 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - C - 04 - ST | 1 | 2025-07-02 | 2025-07-03 |  |  | FALSE | yes
| JD3RZ07C04ST26044 | Excavation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z07 - C - 04 - ST | 1 | 2025-06-21 | 2025-06-22 |  |  | FALSE | yes
| JD3RZ07C04ST26045 | Base Plain Concrete Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z07 - C - 04 - ST | 1 | 2025-06-23 | 2025-06-24 |  |  | FALSE | yes
| JD3RZ07C04ST26046 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z07 - C - 04 - ST | 1 | 2025-06-25 | 2025-06-26 |  |  | FALSE | yes
| JD3RZ07C04ST26047 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z07 - C - 04 - S | 1 | 2025-06-28 | 2025-06-29 |  |  | FALSE | yes
| JD3RZ07C04ST26048 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z07 - C - 04 - ST | 1 | 2025-07-05 | 2025-07-06 |  |  | FALSE | yes
| JD3RZ07C04ST524342 | Concrete encasement for pipes - NNB6.33 42 11.25 - MR - C - 03 - ST | 1 | 2025-06-21 | 2025-07-03 |  |  | FALSE | yes
| JD3RZ07C04TSE26117 | Excavation Worksfor HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - Z07 - C - 04 - TSE | 1 | 2026-01-10 | 2026-01-11 |  |  | FALSE | yes
| JD3RZ07C04TSE26118 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - Z07 - C - 04 - TSE | 1 | 2026-01-12 | 2026-01-13 |  |  | FALSE | yes
| JD3RZ07C04TSE26119 | Installing for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - Z07 - C - 04 - TSE | 1 | 2026-01-14 | 2026-01-18 |  |  | FALSE | yes
| JD3RZ07C04TSE26120 | Testing for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - Z07 - C - 04 - TSE | 1 | 2026-01-19 | 2026-01-21 |  |  | FALSE | yes
| JD3RZ07C04TSE26121 | Backfillingfor HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - Z07 - C - 04 - TSE | 1 | 2026-01-24 | 2026-01-26 |  |  | FALSE | yes
| JD3RZ07C04TSE26122 | Excavation Worksfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - Z07 - C - 04 - TSE | 1 | 2026-01-12 | 2026-01-13 |  |  | FALSE | yes
| JD3RZ07C04TSE26123 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - Z07 - C - 04 - TS | 1 | 2026-01-14 | 2026-01-15 |  |  | FALSE | yes
| JD3RZ07C04TSE26124 | Installing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - Z07 - C - 04 - TSE | 1 | 2026-01-17 | 2026-01-18 |  |  | FALSE | yes
| JD3RZ07C04TSE26125 | Testing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - Z07 - C - 04 - TSE | 1 | 2026-01-19 | 2026-01-20 |  |  | FALSE | yes
| JD3RZ07C04TSE26126 | Backfillingfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - Z07 - C - 04 - TSE | 1 | 2026-01-21 | 2026-01-22 |  |  | FALSE | yes
| JD3RZ07C04WT26057 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - C - 04 - WT | 1 | 2026-01-12 | 2026-01-13 |  |  | FALSE | yes
| JD3RZ07C04WT26058 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - C - 04 - WT | 1 | 2026-01-14 | 2026-01-15 |  |  | FALSE | yes
| JD3RZ07C04WT26059 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - C - 04 - WT | 1 | 2026-01-17 | 2026-01-18 |  |  | FALSE | yes
| JD3RZ07C04WT26060 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - C - 04 - WT | 1 | 2026-01-19 | 2026-01-20 |  |  | FALSE | yes
| JD3RZ07C04WT26061 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - C - 04 - WT | 1 | 2026-01-21 | 2026-01-22 |  |  | FALSE | yes
| JD3RZ07C04WT26092 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z07 - C - 04 - WT | 1 | 2026-01-14 | 2026-01-15 |  |  | FALSE | yes
| JD3RZ07C04WT26093 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z07 - C - 04 - WT | 1 | 2026-01-17 | 2026-01-18 |  |  | FALSE | yes
| JD3RZ07C04WT26094 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z07 - C - 04 - WT | 1 | 2026-01-27 | 2026-01-28 |  |  | FALSE | yes
| JD3RZ07L52ST26544 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 52 - ST | 1 | 2024-12-02 | 2024-12-03 |  |  | FALSE | yes
| JD3RZ07L52ST26545 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 52 | 1 | 2024-12-04 | 2024-12-05 |  |  | FALSE | yes
| JD3RZ07L52ST26546 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 52 - ST | 1 | 2024-12-07 | 2024-12-08 |  |  | FALSE | yes
| JD3RZ07L52ST26547 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 52 - ST | 1 | 2024-12-09 | 2024-12-10 |  |  | FALSE | yes
| JD3RZ07L52ST26548 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 52 - ST | 1 | 2024-12-11 | 2024-12-12 |  |  | FALSE | yes
| JD3RZ07L52ST26552 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 52 - ST | 1 | 2024-12-09 | 2024-12-10 | 2025-08-20 |  | FALSE | FALSE
| JD3RZ07L52ST26553 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 52 - ST | 1 | 2024-12-11 | 2024-12-12 | 2025-08-23 |  | FALSE | FALSE
| JD3RZ07L52ST26557 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 52 - ST | 1 | 2024-12-14 | 2024-12-15 |  |  | FALSE | yes
| JD3RZ07L52ST26558 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 52 - ST | 1 | 2024-12-16 | 2024-12-17 |  |  | FALSE | yes
| JD3RZ07L52ST26578.R | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - Z07 - L - 52 - ST - Remaining | 1 | 2024-12-15 | 2024-12-16 |  |  | FALSE | yes
| JD3RZ07L52ST26584.R | Excavation Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - Z07 - L - 52 - ST - Remaining | 1 | 2024-12-17 | 2024-12-18 |  |  | FALSE | yes
| JD3RZ07L52ST26587 | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - Z07 - L - 52 - ST | 1 | 2024-12-24 | 2024-12-25 | 2025-08-18 |  | FALSE | FALSE
| JD3RZ07L52ST26588 | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - Z07 - L - 52 - ST | 1 | 2024-12-26 | 2024-12-28 | 2025-08-20 |  | FALSE | FALSE
| JD3RZ07L52ST26728.R | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - L - 52 - ST - Remainin | 1 | 2024-12-19 | 2024-12-21 |  |  | FALSE | yes
| JD3RZ07L52ST26729 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - L - 52 - ST | 1 | 2024-12-22 | 2024-12-23 | 2025-08-13 |  | FALSE | FALSE
| JD3RZ07L52ST26730 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - L - 52 - S | 1 | 2024-12-24 | 2024-12-25 |  |  | FALSE | yes
| JD3RZ07L52ST26731 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - L - 52 - ST | 1 | 2024-12-26 | 2024-12-28 |  |  | FALSE | yes
| JD3RZ07L52ST26737 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - L - 52 - ST | 1 | 2024-12-09 | 2024-12-10 |  |  | FALSE | yes
| JD3RZ07L52ST26738 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - L - 52 - ST | 1 | 2024-12-11 | 2024-12-12 |  |  | FALSE | yes
| JD3RZ07L52ST26739 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - L - 52 - ST | 1 | 2024-12-14 | 2024-12-15 |  |  | FALSE | yes
| JD3RZ07L52ST26740 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - L - 52 - S | 1 | 2024-12-16 | 2024-12-17 |  |  | FALSE | yes
| JD3RZ07L52ST26741 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - L - 52 - ST | 1 | 2024-12-18 | 2024-12-19 |  |  | FALSE | yes
| JD3RZ07L52ST26743 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - L - 52 - ST | 1 | 2024-12-14 | 2024-12-15 | 2025-08-13 |  | FALSE | FALSE
| JD3RZ07L52ST26744 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - L - 52 - ST | 1 | 2024-12-16 | 2024-12-17 | 2025-08-16 |  | FALSE | FALSE
| JD3RZ07L52ST26745 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - L - 52 - S | 1 | 2024-12-18 | 2024-12-19 |  |  | FALSE | yes
| JD3RZ07L52ST26746 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - L - 52 - ST | 1 | 2024-12-21 | 2024-12-22 |  |  | FALSE | yes
| JD3RZ07L52ST26762 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - Z07 - L - 52 - ST | 1 | 2024-12-14 | 2024-12-15 |  |  | FALSE | yes
| JD3RZ07L52ST26763 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - Z07 - L - 52 - ST | 1 | 2024-12-16 | 2024-12-17 |  |  | FALSE | yes
| JD3RZ07L52ST26764 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - Z07 - L - 52 - ST | 1 | 2024-12-18 | 2024-12-19 |  |  | FALSE | yes
| JD3RZ07L52ST26765 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - Z07 - L - 52 - ST | 1 | 2024-12-21 | 2024-12-22 |  |  | FALSE | yes
| JD3RZ07L52ST26766 | EXCAVATION Works for Catchbasine double - B6.33 05 39.10 - Z07 - L - 52 - ST | 1 | 2024-12-16 | 2024-12-17 |  |  | FALSE | yes
| JD3RZ07L52ST26767 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - Z07 - L - 52 - ST | 1 | 2024-12-18 | 2024-12-19 |  |  | FALSE | yes
| JD3RZ07L52ST26768 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z07 - L - 52 - ST | 1 | 2024-12-21 | 2024-12-22 |  |  | FALSE | yes
| JD3RZ07L52ST26769 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z07 - L - 52 - ST | 1 | 2024-12-23 | 2024-12-24 |  |  | FALSE | yes
| JD3RZ07L52TSE26820 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 52 - TSE | 1 | 2024-12-25 | 2024-12-26 |  |  | FALSE | yes
| JD3RZ07L52TSE26821 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 52 - T | 1 | 2024-12-28 | 2024-12-29 |  |  | FALSE | yes
| JD3RZ07L52TSE26822 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 52 - TSE | 1 | 2024-12-30 | 2024-12-31 |  |  | FALSE | yes
| JD3RZ07L52TSE26823 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 52 - TSE | 1 | 2025-01-01 | 2025-01-02 |  |  | FALSE | yes
| JD3RZ07L52TSE26824 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 52 - TSE | 1 | 2025-01-04 | 2025-01-05 |  |  | FALSE | yes
| JD3RZ07L52TSE26835 | Excavation Worksfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - Z07 - L - 52 - TSE | 1 | 2024-12-28 | 2024-12-29 |  |  | FALSE | yes
| JD3RZ07L52TSE26836 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - Z07 - L - 52 - TS | 1 | 2024-12-30 | 2024-12-31 |  |  | FALSE | yes
| JD3RZ07L52TSE26837 | Installing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - Z07 - L - 52 - TSE | 1 | 2025-01-01 | 2025-01-02 |  |  | FALSE | yes
| JD3RZ07L52TSE26838 | Testing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - Z07 - L - 52 - TSE | 1 | 2025-01-04 | 2025-01-05 |  |  | FALSE | yes
| JD3RZ07L52TSE26839 | Backfillingfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - Z07 - L - 52 - TSE | 1 | 2025-01-06 | 2025-01-07 |  |  | FALSE | yes
| JD3RZ07L52TSE26840 | Excavation Worksfor HDPE Pipes 315 mm - depth from 2.51 to 3.5 m - B4.33 31 00.05 - Z07 - L - 52 - TSE | 1 | 2024-12-30 | 2024-12-31 |  |  | FALSE | yes
| JD3RZ07L52TSE26841 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 2.51 to 3.5 m - B4.33 31 00.05 - Z07 - L - 52 - TS | 1 | 2025-01-01 | 2025-01-02 |  |  | FALSE | yes
| JD3RZ07L52TSE26842 | Installing for HDPE Pipes 315 mm - depth from 2.51 to 3.5 m - B4.33 31 00.05 - Z07 - L - 52 - TSE | 1 | 2025-01-04 | 2025-01-05 |  |  | FALSE | yes
| JD3RZ07L52TSE26843 | Testing for HDPE Pipes 315 mm - depth from 2.51 to 3.5 m - B4.33 31 00.05 - Z07 - L - 52 - TSE | 1 | 2025-01-06 | 2025-01-07 |  |  | FALSE | yes
| JD3RZ07L52TSE26844 | Backfillingfor HDPE Pipes 315 mm - depth from 2.51 to 3.5 m - B4.33 31 00.05 - Z07 - L - 52 - TSE | 1 | 2025-01-08 | 2025-01-09 |  |  | FALSE | yes
| JD3RZ07L52TSE26845 | Excavation Worksfor HDPE Pipes 315 mm - depth from 3.51 to 4.5 m - B4.33 31 00.06 - Z07 - L - 52 - TSE | 1 | 2025-01-01 | 2025-01-02 |  |  | FALSE | yes
| JD3RZ07L52TSE26846 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 3.51 to 4.5 m - B4.33 31 00.06 - Z07 - L - 52 - TS | 1 | 2025-01-04 | 2025-01-05 |  |  | FALSE | yes
| JD3RZ07L52TSE26847 | Installing for HDPE Pipes 315 mm - depth from 3.51 to 4.5 m - B4.33 31 00.06 - Z07 - L - 52 - TSE | 1 | 2025-01-06 | 2025-01-07 |  |  | FALSE | yes
| JD3RZ07L52TSE26848 | Testing for HDPE Pipes 315 mm - depth from 3.51 to 4.5 m - B4.33 31 00.06 - Z07 - L - 52 - TSE | 1 | 2025-01-08 | 2025-01-09 |  |  | FALSE | yes
| JD3RZ07L52TSE26849 | Backfillingfor HDPE Pipes 315 mm - depth from 3.51 to 4.5 m - B4.33 31 00.06 - Z07 - L - 52 - TSE | 1 | 2025-01-11 | 2025-01-12 |  |  | FALSE | yes
| JD3RZ07L52TSE26945 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z07 - L - 52 - TSE | 1 | 2025-01-08 | 2025-01-09 |  |  | FALSE | yes
| JD3RZ07L52TSE26946 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z07 - L - 52 - TSE | 1 | 2025-01-11 | 2025-01-12 |  |  | FALSE | yes
| JD3RZ07L52WT26770 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 52 - WT | 1 | 2025-01-13 | 2025-01-14 |  |  | FALSE | yes
| JD3RZ07L52WT26771 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 52 - WT | 1 | 2025-01-15 | 2025-01-16 |  |  | FALSE | yes
| JD3RZ07L52WT26772 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 52 - WT | 1 | 2025-01-18 | 2025-01-19 |  |  | FALSE | yes
| JD3RZ07L52WT26773 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 52 - WT | 1 | 2025-01-20 | 2025-01-21 |  |  | FALSE | yes
| JD3RZ07L52WT26774 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 52 - WT | 1 | 2025-01-22 | 2025-01-23 |  |  | FALSE | yes
| JD3RZ07L52WT26805 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z07 - L - 52 - WT | 1 | 2025-01-15 | 2025-01-16 |  |  | FALSE | yes
| JD3RZ07L52WT26806 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z07 - L - 52 - WT | 1 | 2025-01-18 | 2025-01-19 |  |  | FALSE | yes
| JD3RZ07L52WT26807 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z07 - L - 52 - WT | 1 | 2025-01-20 | 2025-01-21 |  |  | FALSE | yes
| JD3RZ07L63ST27261.R | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 63 - ST - Remaining | 1 | 2024-12-24 | 2024-12-25 |  |  | FALSE | yes
| JD3RZ07L63ST27262.R | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 63 - ST - Remaining | 1 | 2024-12-09 | 2024-12-10 |  |  | FALSE | yes
| JD3RZ07L63ST27263.R | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 63 | 1 | 2024-12-12 | 2024-12-14 |  |  | FALSE | yes
| JD3RZ07L63ST27264.R | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 63 - ST - Remaining | 1 | 2024-12-16 | 2024-12-17 | 2025-08-30 |  | FALSE | FALSE
| JD3RZ07L63ST27265 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 63 - ST | 1 | 2024-12-18 | 2024-12-21 |  |  | FALSE | yes
| JD3RZ07L63ST27266 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 63 - ST | 1 | 2025-01-04 | 2025-01-07 | 2025-09-16 |  | FALSE | FALSE
| JD3RZ07L63ST27270 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 63 - ST | 1 | 2024-12-18 | 2024-12-19 |  |  | FALSE | yes
| JD3RZ07L63ST27271 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 63 - ST | 1 | 2025-01-04 | 2025-01-05 |  |  | FALSE | yes
| JD3RZ07L63ST27275 | Primary Test for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m - B6.33 42 11.03 - Z07 - L - 63 - ST | 1 | 2024-12-21 | 2024-12-22 |  |  | FALSE | yes
| JD3RZ07L63ST27280 | Primary Test for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - Z07 - L - 63 - ST | 1 | 2024-12-23 | 2024-12-24 |  |  | FALSE | yes
| JD3RZ07L63ST27290 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - Z07 - L - 63 - ST | 1 | 2024-12-25 | 2024-12-28 |  |  | FALSE | yes
| JD3RZ07L63ST27291 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - Z07 - L - 63 - ST | 1 | 2025-01-04 | 2025-01-08 |  |  | FALSE | yes
| JD3RZ07L63ST27301 | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - Z07 - L - 63 - ST | 1 | 2025-01-04 | 2025-01-05 |  |  | FALSE | yes
| JD3RZ07L63ST27310.R | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - Z07 - L - 63 - ST - Remaining | 1 | 2024-12-28 | 2024-12-29 |  |  | FALSE | yes
| JD3RZ07L63ST27311 | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - Z07 - L - 63 - ST | 1 | 2025-01-04 | 2025-01-05 |  |  | FALSE | yes
| JD3RZ07L63ST27320 | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - Z07 - L - 63 - ST | 1 | 2024-12-30 | 2024-12-31 |  |  | FALSE | yes
| JD3RZ07L63ST27321 | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - Z07 - L - 63 - ST | 1 | 2025-01-04 | 2025-01-05 |  |  | FALSE | yes
| JD3RZ07L63ST27335 | Primary Test for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m - B6.33 42 11.15 - Z07 - L - 63 - ST | 1 | 2024-12-25 | 2024-12-26 |  |  | FALSE | yes
| JD3RZ07L63ST27336 | Backfilling Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m - B6.33 42 11.15 - Z07 - L - 63 - ST | 1 | 2025-01-04 | 2025-01-05 |  |  | FALSE | yes
| JD3RZ07L63ST27442 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - L - 63 - ST | 1 | 2024-12-26 | 2024-12-29 |  |  | FALSE | yes
| JD3RZ07L63ST27443 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - L - 63 - S | 1 | 2024-12-30 | 2024-12-31 |  |  | FALSE | yes
| JD3RZ07L63ST27444 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - L - 63 - ST | 1 | 2025-01-01 | 2025-01-02 |  |  | FALSE | yes
| JD3RZ07L63ST27452 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - L - 63 - ST | 1 | 2024-12-28 | 2024-12-29 |  |  | FALSE | yes
| JD3RZ07L63ST27453 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - L - 63 - S | 1 | 2024-12-30 | 2024-12-31 |  |  | FALSE | yes
| JD3RZ07L63ST27454 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - L - 63 - ST | 1 | 2025-01-01 | 2025-01-02 |  |  | FALSE | yes
| JD3RZ07L63ST27470 | Excavation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z07 - L - 63 - ST | 1 | 2024-12-23 | 2024-12-24 |  |  | FALSE | yes
| JD3RZ07L63ST27471 | Base Plain Concrete Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z07 - L - 63 - ST | 1 | 2024-12-25 | 2024-12-26 |  |  | FALSE | yes
| JD3RZ07L63ST27472 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z07 - L - 63 - ST | 1 | 2024-12-28 | 2024-12-29 |  |  | FALSE | yes
| JD3RZ07L63ST27473 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z07 - L - 63 - S | 1 | 2024-12-30 | 2024-12-31 |  |  | FALSE | yes
| JD3RZ07L63ST27474 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z07 - L - 63 - ST | 1 | 2025-01-01 | 2025-01-02 |  |  | FALSE | yes
| JD3RZ07L63ST27475 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - Z07 - L - 63 - ST | 1 | 2024-12-25 | 2024-12-28 | 2025-10-19 |  | FALSE | FALSE
| JD3RZ07L63ST27476 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - Z07 - L - 63 - ST | 1 | 2024-12-29 | 2025-01-01 | 2025-10-21 |  | FALSE | FALSE
| JD3RZ07L63ST27477 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - Z07 - L - 63 - ST | 1 | 2025-01-02 | 2025-01-06 |  |  | FALSE | yes
| JD3RZ07L63ST27478 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - Z07 - L - 63 - ST | 1 | 2025-01-07 | 2025-01-09 |  |  | FALSE | yes
| JD3RZ07L63ST27479 | EXCAVATION Works for Catchbasine double - B6.33 05 39.10 - Z07 - L - 63 - ST | 1 | 2024-12-29 | 2024-12-30 | 2025-10-20 |  | FALSE | FALSE
| JD3RZ07L63ST27480 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - Z07 - L - 63 - ST | 1 | 2024-12-31 | 2025-01-02 | 2025-10-21 |  | FALSE | FALSE
| JD3RZ07L63ST27481 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z07 - L - 63 - ST | 1 | 2025-01-04 | 2025-01-06 |  |  | FALSE | yes
| JD3RZ07L63ST27482 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z07 - L - 63 - ST | 1 | 2025-01-07 | 2025-01-08 |  |  | FALSE | yes
| JD3RZ07L63TSE27533 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 63 - TSE | 1 | 2025-01-11 | 2025-01-12 |  |  | FALSE | yes
| JD3RZ07L63TSE27534 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 63 - T | 1 | 2025-01-13 | 2025-01-14 |  |  | FALSE | yes
| JD3RZ07L63TSE27535 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 63 - TSE | 1 | 2025-01-15 | 2025-01-16 |  |  | FALSE | yes
| JD3RZ07L63TSE27536 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 63 - TSE | 1 | 2025-01-18 | 2025-01-19 |  |  | FALSE | yes
| JD3RZ07L63TSE27537 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 63 - TSE | 1 | 2025-01-20 | 2025-01-21 |  |  | FALSE | yes
| JD3RZ07L63TSE27658 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z07 - L - 63 - TSE | 1 | 2025-01-15 | 2025-01-16 |  |  | FALSE | yes
| JD3RZ07L63TSE27659 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z07 - L - 63 - TSE | 1 | 2025-01-18 | 2025-01-19 |  |  | FALSE | yes
| JD3RZ07L63TSE27662 | Installationfor butterfly valves 300 mm. - B4.33 14 19.03 - Z07 - L - 63 - TSE | 1 | 2025-02-17 | 2025-02-18 |  |  | FALSE | yes
| JD3RZ07L63TSE27663 | Testing And Commtionningfor butterfly valves 300 mm. - B4.33 14 19.03 - Z07 - L - 63 - TSE | 1 | 2025-02-19 | 2025-02-20 |  |  | FALSE | yes
| JD3RZ07L63TSE27670 | Installationfor Wash - Out valves 100 mm. - on pipes with diameter 110 - 400 mm - B4.33 14 19.07 - Z07 - L - 63 - TSE | 1 | 2025-01-15 | 2025-01-16 |  |  | FALSE | yes
| JD3RZ07L63TSE27671 | Testing And Commtionningfor Wash - Out valves 100 mm. - on pipes with diameter 110 - 400 mm - B4.33 14 19.07 - Z07 - L - | 1 | 2025-01-18 | 2025-01-19 |  |  | FALSE | yes
| JD3RZ07L63TSE27676 | Installationfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - Z07 - L - 63 - TSE | 1 | 2025-01-15 | 2025-01-16 |  |  | FALSE | yes
| JD3RZ07L63TSE27677 | Testing And Commtionningfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - Z07 - L - 63 | 1 | 2025-01-18 | 2025-01-19 |  |  | FALSE | yes
| JD3RZ07L63TSE27682 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - Z07 - L - 63 - TSE | 1 | 2025-01-15 | 2025-01-16 |  |  | FALSE | yes
| JD3RZ07L63TSE27683 | Plain Concrete Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - Z07 - L - 63 - TSE | 1 | 2025-01-18 | 2025-01-19 |  |  | FALSE | yes
| JD3RZ07L63TSE27684 | INSTALLATIONfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - Z07 - L - 63 - TSE | 1 | 2025-01-20 | 2025-01-21 |  |  | FALSE | yes
| JD3RZ07L63TSE27685 | Backfilling Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - Z07 - L - 63 - TSE | 1 | 2025-01-22 | 2025-01-23 |  |  | FALSE | yes
| JD3RZ07L63TSE27694 | EXCAVATION and Bedding Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - Z07 - L - 63 - TSE | 1 | 2025-01-18 | 2025-01-19 |  |  | FALSE | yes
| JD3RZ07L63TSE27695 | Plain Concrete Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - Z07 - L - 63 - TSE | 1 | 2025-01-20 | 2025-01-21 |  |  | FALSE | yes
| JD3RZ07L63TSE27696 | INSTALLATIONfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - Z07 - L - 63 - TSE | 1 | 2025-01-22 | 2025-01-23 |  |  | FALSE | yes
| JD3RZ07L63TSE27697 | Backfilling Worksfor Wash - out Valve Chamber - 110 to 400 MM - B4.33 14 13.06 - Z07 - L - 63 - TSE | 1 | 2025-01-25 | 2025-01-26 |  |  | FALSE | yes
| JD3RZ07L63TSE27706 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z07 - L - 63 - TSE | 1 | 2025-01-20 | 2025-01-21 |  |  | FALSE | yes
| JD3RZ07L63TSE27707 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z07 - L - 63 - TSE | 1 | 2025-01-22 | 2025-01-23 |  |  | FALSE | yes
| JD3RZ07L63TSE27708 | INSTALLATIONfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z07 - L - 63 - TSE | 1 | 2025-01-25 | 2025-01-26 |  |  | FALSE | yes
| JD3RZ07L63TSE27709 | Backfilling Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z07 - L - 63 - TSE | 1 | 2025-01-27 | 2025-01-28 |  |  | FALSE | yes
| JD3RZ07L63WT27483 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 63 - WT | 1 | 2025-02-01 | 2025-02-02 |  |  | FALSE | yes
| JD3RZ07L63WT27484 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 63 - WT | 1 | 2025-02-03 | 2025-02-04 |  |  | FALSE | yes
| JD3RZ07L63WT27485 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 63 - WT | 1 | 2025-02-05 | 2025-02-06 |  |  | FALSE | yes
| JD3RZ07L63WT27486 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 63 - WT | 1 | 2025-02-08 | 2025-02-09 |  |  | FALSE | yes
| JD3RZ07L63WT27487 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 63 - WT | 1 | 2025-02-12 | 2025-02-13 |  |  | FALSE | yes
| JD3RZ07L63WT27518 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z07 - L - 63 - WT | 1 | 2025-02-03 | 2025-02-04 |  |  | FALSE | yes
| JD3RZ07L63WT27519 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z07 - L - 63 - WT | 1 | 2025-02-08 | 2025-02-09 |  |  | FALSE | yes
| JD3RZ07L63WT27520 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z07 - L - 63 - WT | 1 | 2025-02-10 | 2025-02-11 |  |  | FALSE | yes
| JD3RZ07L64ST27970.R | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 64 - ST - Remaining | 1 | 2025-01-13 | 2025-01-14 |  |  | FALSE | yes
| JD3RZ07L64ST27971.R | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 64 | 1 | 2025-01-15 | 2025-01-16 |  |  | FALSE | yes
| JD3RZ07L64ST27972.R | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 64 - ST - Remaining | 1 | 2025-01-18 | 2025-01-19 |  |  | FALSE | yes
| JD3RZ07L64ST27973.R | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 64 - ST - Remaining | 1 | 2025-01-20 | 2025-01-21 |  |  | FALSE | yes
| JD3RZ07L64ST27974.R | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 64 - ST - Remaining | 1 | 2025-02-16 | 2025-02-17 |  |  | FALSE | yes
| JD3RZ07L64ST27975 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 64 - ST | 1 | 2025-01-15 | 2025-01-16 |  |  | FALSE | yes
| JD3RZ07L64ST27976 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 64 | 1 | 2025-01-18 | 2025-01-19 |  |  | FALSE | yes
| JD3RZ07L64ST27977 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 64 - ST | 1 | 2025-01-20 | 2025-01-21 |  |  | FALSE | yes
| JD3RZ07L64ST27978 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 64 - ST | 1 | 2025-01-22 | 2025-01-23 |  |  | FALSE | yes
| JD3RZ07L64ST27979 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 64 - ST | 1 | 2025-02-12 | 2025-02-13 |  |  | FALSE | yes
| JD3RZ07L64ST27980 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 64 - ST | 1 | 2025-01-18 | 2025-01-19 |  |  | FALSE | yes
| JD3RZ07L64ST27981 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 64 | 1 | 2025-01-20 | 2025-01-21 |  |  | FALSE | yes
| JD3RZ07L64ST27982 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 64 - ST | 1 | 2025-01-22 | 2025-01-23 |  |  | FALSE | yes
| JD3RZ07L64ST27983 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 64 - ST | 1 | 2025-01-25 | 2025-01-26 |  |  | FALSE | yes
| JD3RZ07L64ST27984 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 64 - ST | 1 | 2025-02-12 | 2025-02-13 |  |  | FALSE | yes
| JD3RZ07L64ST27994.R | Backfilling Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m - B6.33 42 11.04 - Z07 - L - 64 - ST - Remaining | 1 | 2025-02-12 | 2025-02-13 |  |  | FALSE | yes
| JD3RZ07L64ST28004.R | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - Z07 - L - 64 - ST - Remaining | 1 | 2025-02-12 | 2025-02-13 |  |  | FALSE | yes
| JD3RZ07L64ST28012.R | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - Z07 - L - 64 - ST - Remaining | 1 | 2025-01-27 | 2025-01-28 |  |  | FALSE | yes
| JD3RZ07L64ST28013.R | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - Z07 - L - 64 - ST - Remaining | 1 | 2025-01-29 | 2025-01-30 |  |  | FALSE | yes
| JD3RZ07L64ST28014.R | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - Z07 - L - 64 - ST - Remaining | 1 | 2025-02-12 | 2025-02-13 |  |  | FALSE | yes
| JD3RZ07L64ST28023.R | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - Z07 - L - 64 - ST - Remaining | 1 | 2025-02-06 | 2025-02-08 | 2025-09-20 |  | FALSE | FALSE
| JD3RZ07L64ST28024.R | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - Z07 - L - 64 - ST - Remaining | 1 | 2025-02-16 | 2025-02-17 | 2025-09-23 |  | FALSE | FALSE
| JD3RZ07L64ST28033.R | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - Z07 - L - 64 - ST - Remaining | 1 | 2025-02-19 | 2025-02-20 | 2025-09-21 |  | FALSE | FALSE
| JD3RZ07L64ST28034.R | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - Z07 - L - 64 - ST - Remaining | 1 | 2025-02-27 | 2025-03-01 | 2025-09-23 |  | FALSE | FALSE
| JD3RZ07L64ST28060 | Excavation Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m - B6.33 42 11.20 - Z07 - L - 64 - ST | 1 | 2025-01-20 | 2025-01-21 |  |  | FALSE | yes
| JD3RZ07L64ST28061 | Soil Replacement and Bedding Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m - B6.33 42 11.20 - Z07 - L - 64 | 1 | 2025-01-22 | 2025-01-23 |  |  | FALSE | yes
| JD3RZ07L64ST28062 | Installing for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m - B6.33 42 11.20 - Z07 - L - 64 - ST | 1 | 2025-01-25 | 2025-01-26 |  |  | FALSE | yes
| JD3RZ07L64ST28063 | Primary Test for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m - B6.33 42 11.20 - Z07 - L - 64 - ST | 1 | 2025-01-27 | 2025-01-28 |  |  | FALSE | yes
| JD3RZ07L64ST28064 | Backfilling Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m - B6.33 42 11.20 - Z07 - L - 64 - ST | 1 | 2025-02-13 | 2025-02-15 |  |  | FALSE | yes
| JD3RZ07L64ST28155 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - L - 64 - ST | 1 | 2025-01-27 | 2025-01-28 |  |  | FALSE | yes
| JD3RZ07L64ST28156 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - L - 64 - S | 1 | 2025-01-29 | 2025-01-30 |  |  | FALSE | yes
| JD3RZ07L64ST28157 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - L - 64 - ST | 1 | 2025-02-01 | 2025-02-02 |  |  | FALSE | yes
| JD3RZ07L64ST28164.R | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - L - 64 - ST - Remainin | 1 | 2025-02-06 | 2025-02-08 | 2025-10-23 |  | FALSE | FALSE
| JD3RZ07L64ST28165.R | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - L - 64 - ST - Remaini | 1 | 2025-02-10 | 2025-02-11 |  |  | FALSE | yes
| JD3RZ07L64ST28166 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - L - 64 - S | 1 | 2025-02-12 | 2025-02-13 |  |  | FALSE | yes
| JD3RZ07L64ST28167 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - L - 64 - ST | 1 | 2025-02-15 | 2025-02-16 |  |  | FALSE | yes
| JD3RZ07L64ST28168 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - L - 64 - ST | 1 | 2025-01-25 | 2025-01-26 | 2025-10-23 |  | FALSE | FALSE
| JD3RZ07L64ST28169 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - L - 64 - ST | 1 | 2025-01-27 | 2025-01-28 |  |  | FALSE | yes
| JD3RZ07L64ST28170 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - L - 64 - ST | 1 | 2025-01-29 | 2025-01-30 |  |  | FALSE | yes
| JD3RZ07L64ST28171 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - L - 64 - S | 1 | 2025-02-01 | 2025-02-02 |  |  | FALSE | yes
| JD3RZ07L64ST28172 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - L - 64 - ST | 1 | 2025-02-03 | 2025-02-04 |  |  | FALSE | yes
| JD3RZ07L64ST28178 | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - L - 64 - ST | 1 | 2025-01-27 | 2025-01-28 |  |  | FALSE | yes
| JD3RZ07L64ST28179 | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - L - 64 - ST | 1 | 2025-01-29 | 2025-01-30 |  |  | FALSE | yes
| JD3RZ07L64ST28180 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - L - 64 - ST | 1 | 2025-02-01 | 2025-02-02 |  |  | FALSE | yes
| JD3RZ07L64ST28181 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - L - 64 - S | 1 | 2025-02-03 | 2025-02-04 |  |  | FALSE | yes
| JD3RZ07L64ST28182 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - L - 64 - ST | 1 | 2025-02-05 | 2025-02-06 |  |  | FALSE | yes
| JD3RZ07L64ST28188 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - Z07 - L - 64 - ST | 1 | 2025-01-29 | 2025-01-30 | 2025-10-18 |  | FALSE | FALSE
| JD3RZ07L64ST28189 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - Z07 - L - 64 - ST | 1 | 2025-02-01 | 2025-02-03 | 2025-10-20 |  | FALSE | FALSE
| JD3RZ07L64ST28190 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - Z07 - L - 64 - ST | 1 | 2025-02-04 | 2025-02-06 |  |  | FALSE | yes
| JD3RZ07L64ST28191 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - Z07 - L - 64 - ST | 1 | 2025-02-08 | 2025-02-09 |  |  | FALSE | yes
| JD3RZ07L64ST28192 | EXCAVATION Works for Catchbasine double - B6.33 05 39.10 - Z07 - L - 64 - ST | 1 | 2025-02-01 | 2025-02-02 | 2025-10-08 |  | FALSE | FALSE
| JD3RZ07L64ST28193 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - Z07 - L - 64 - ST | 1 | 2025-02-04 | 2025-02-06 | 2025-10-11 |  | FALSE | FALSE
| JD3RZ07L64ST28194 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z07 - L - 64 - ST | 1 | 2025-02-08 | 2025-02-10 |  |  | FALSE | yes
| JD3RZ07L64ST28195 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z07 - L - 64 - ST | 1 | 2025-02-11 | 2025-02-12 |  |  | FALSE | yes
| JD3RZ07L64TSE28246.R | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 64 - TSE - Remaining | 1 | 2025-02-15 | 2025-02-16 | 2025-08-26 |  | FALSE | FALSE
| JD3RZ07L64TSE28247.R | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 64 - T | 1 | 2025-02-20 | 2025-02-22 | 2025-08-28 |  | FALSE | FALSE
| JD3RZ07L64TSE28248.R | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 64 - TSE - Remaining | 1 | 2025-03-02 | 2025-03-03 | 2025-08-31 |  | FALSE | FALSE
| JD3RZ07L64TSE28249 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 64 - TSE | 1 | 2025-03-04 | 2025-03-09 |  |  | FALSE | yes
| JD3RZ07L64TSE28250 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 64 - TSE | 1 | 2025-03-10 | 2025-03-15 |  |  | FALSE | yes
| JD3RZ07L64TSE28371 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z07 - L - 64 - TSE | 1 | 2025-03-04 | 2025-03-05 |  |  | FALSE | yes
| JD3RZ07L64TSE28372 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z07 - L - 64 - TSE | 1 | 2025-03-08 | 2025-03-09 |  |  | FALSE | yes
| JD3RZ07L64WT28196 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 64 - WT | 1 | 2025-03-16 | 2025-03-17 |  |  | FALSE | yes
| JD3RZ07L64WT28197 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 64 - WT | 1 | 2025-03-18 | 2025-03-19 |  |  | FALSE | yes
| JD3RZ07L64WT28198 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 64 - WT | 1 | 2025-03-20 | 2025-03-22 |  |  | FALSE | yes
| JD3RZ07L64WT28199 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 64 - WT | 1 | 2025-03-23 | 2025-03-24 |  |  | FALSE | yes
| JD3RZ07L64WT28200 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 64 - WT | 1 | 2025-03-25 | 2025-03-26 |  |  | FALSE | yes
| JD3RZ07L64WT28231 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z07 - L - 64 - WT | 1 | 2025-03-18 | 2025-03-19 |  |  | FALSE | yes
| JD3RZ07L64WT28232 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z07 - L - 64 - WT | 1 | 2025-03-20 | 2025-03-22 |  |  | FALSE | yes
| JD3RZ07L64WT28233 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z07 - L - 64 - WT | 1 | 2025-03-23 | 2025-03-24 |  |  | FALSE | yes
| JD3RZ07L65ST28683 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 65 - ST | 1 | 2024-12-10 | 2024-12-12 | 2025-10-23 |  | FALSE | FALSE
| JD3RZ07L65ST28684 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 65 | 1 | 2024-12-14 | 2024-12-16 | 2025-10-27 |  | FALSE | FALSE
| JD3RZ07L65ST28685 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 65 - ST | 1 | 2024-12-17 | 2024-12-21 |  |  | FALSE | yes
| JD3RZ07L65ST28686 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 65 - ST | 1 | 2024-12-22 | 2024-12-25 |  |  | FALSE | yes
| JD3RZ07L65ST28687 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 65 - ST | 1 | 2025-01-21 | 2025-01-26 |  |  | FALSE | yes
| JD3RZ07L65ST28688 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 65 - ST | 1 | 2024-12-14 | 2024-12-15 |  |  | FALSE | yes
| JD3RZ07L65ST28689 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 65 | 1 | 2024-12-16 | 2024-12-17 |  |  | FALSE | yes
| JD3RZ07L65ST28690 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 65 - ST | 1 | 2024-12-18 | 2024-12-19 |  |  | FALSE | yes
| JD3RZ07L65ST28691 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 65 - ST | 1 | 2024-12-21 | 2024-12-22 |  |  | FALSE | yes
| JD3RZ07L65ST28692 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 65 - ST | 1 | 2025-01-20 | 2025-01-21 |  |  | FALSE | yes
| JD3RZ07L65ST28693 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 65 - ST | 1 | 2024-12-16 | 2024-12-17 |  |  | FALSE | yes
| JD3RZ07L65ST28694 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 65 | 1 | 2024-12-18 | 2024-12-19 |  |  | FALSE | yes
| JD3RZ07L65ST28695 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 65 - ST | 1 | 2024-12-21 | 2024-12-22 |  |  | FALSE | yes
| JD3RZ07L65ST28696 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 65 - ST | 1 | 2024-12-23 | 2024-12-24 |  |  | FALSE | yes
| JD3RZ07L65ST28697 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 65 - ST | 1 | 2025-01-20 | 2025-01-21 |  |  | FALSE | yes
| JD3RZ07L65ST28701 | Primary Test for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m - B6.33 42 11.03 - Z07 - L - 65 - ST | 1 | 2024-12-25 | 2024-12-26 |  |  | FALSE | yes
| JD3RZ07L65ST28702 | Backfilling Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m - B6.33 42 11.03 - Z07 - L - 65 - ST | 1 | 2025-01-20 | 2025-01-21 |  |  | FALSE | yes
| JD3RZ07L65ST28711 | Primary Test for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m - B6.33 42 11.05 - Z07 - L - 65 - ST | 1 | 2024-12-28 | 2024-12-29 |  |  | FALSE | yes
| JD3RZ07L65ST28712 | Backfilling Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m - B6.33 42 11.05 - Z07 - L - 65 - ST | 1 | 2025-01-20 | 2025-01-21 |  |  | FALSE | yes
| JD3RZ07L65ST28726 | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - Z07 - L - 65 - ST | 1 | 2024-12-31 | 2025-01-01 |  |  | FALSE | yes
| JD3RZ07L65ST28727 | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - Z07 - L - 65 - ST | 1 | 2025-01-20 | 2025-01-22 |  |  | FALSE | yes
| JD3RZ07L65ST28736 | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - Z07 - L - 65 - ST | 1 | 2025-01-05 | 2025-01-06 |  |  | FALSE | yes
| JD3RZ07L65ST28737 | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - Z07 - L - 65 - ST | 1 | 2025-01-23 | 2025-01-26 |  |  | FALSE | yes
| JD3RZ07L65ST28746 | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - Z07 - L - 65 - ST | 1 | 2025-01-09 | 2025-01-12 |  |  | FALSE | yes
| JD3RZ07L65ST28747 | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - Z07 - L - 65 - ST | 1 | 2025-01-20 | 2025-01-23 |  |  | FALSE | yes
| JD3RZ07L65ST28759.R | Soil Replacement and Bedding Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m - B6.33 42 11.15 - Z07 - L - 65 | 1 | 2025-01-07 | 2025-01-08 |  |  | FALSE | yes
| JD3RZ07L65ST28760.R | Installing for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m - B6.33 42 11.15 - Z07 - L - 65 - ST - Remaining | 1 | 2025-01-11 | 2025-01-12 |  |  | FALSE | yes
| JD3RZ07L65ST28761 | Primary Test for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m - B6.33 42 11.15 - Z07 - L - 65 - ST | 1 | 2025-01-13 | 2025-01-15 |  |  | FALSE | yes
| JD3RZ07L65ST28762 | Backfilling Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m - B6.33 42 11.15 - Z07 - L - 65 - ST | 1 | 2025-01-20 | 2025-01-23 |  |  | FALSE | yes
| JD3RZ07L65ST28791 | Primary Test for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - Z07 - L - 65 - ST | 1 | 2025-01-01 | 2025-01-02 |  |  | FALSE | yes
| JD3RZ07L65ST28792 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - Z07 - L - 65 - ST | 1 | 2025-01-20 | 2025-01-21 |  |  | FALSE | yes
| JD3RZ07L65ST28866 | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - L - 65 - ST | 1 | 2024-12-28 | 2024-12-29 | 2025-08-05 |  | FALSE | FALSE
| JD3RZ07L65ST28867 | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - L - 65 - ST | 1 | 2024-12-30 | 2024-12-31 | 2025-08-07 |  | FALSE | FALSE
| JD3RZ07L65ST28868 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - L - 65 - ST | 1 | 2025-01-01 | 2025-01-02 |  |  | FALSE | yes
| JD3RZ07L65ST28869 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - L - 65 - S | 1 | 2025-01-04 | 2025-01-05 |  |  | FALSE | yes
| JD3RZ07L65ST28870 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - L - 65 - ST | 1 | 2025-01-06 | 2025-01-07 |  |  | FALSE | yes
| JD3RZ07L65ST28878.R | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - L - 65 - ST - Remaini | 1 | 2025-01-14 | 2025-01-15 |  |  | FALSE | yes
| JD3RZ07L65ST28879 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - L - 65 - S | 1 | 2025-01-16 | 2025-01-18 |  |  | FALSE | yes
| JD3RZ07L65ST28880 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - L - 65 - ST | 1 | 2025-01-19 | 2025-01-20 |  |  | FALSE | yes
| JD3RZ07L65ST28883 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - L - 65 - ST | 1 | 2025-01-04 | 2025-01-05 |  |  | FALSE | yes
| JD3RZ07L65ST28884 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - L - 65 - S | 1 | 2025-01-06 | 2025-01-07 |  |  | FALSE | yes
| JD3RZ07L65ST28885 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - L - 65 - ST | 1 | 2025-01-08 | 2025-01-09 |  |  | FALSE | yes
| JD3RZ07L65ST28893.R | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - L - 65 - ST - Remaini | 1 | 2025-01-16 | 2025-01-18 |  |  | FALSE | yes
| JD3RZ07L65ST28894 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - L - 65 - S | 1 | 2025-01-19 | 2025-01-20 |  |  | FALSE | yes
| JD3RZ07L65ST28895 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - L - 65 - ST | 1 | 2025-01-21 | 2025-01-22 |  |  | FALSE | yes
| JD3RZ07L65ST28898 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z07 - L - 65 - ST | 1 | 2025-01-06 | 2025-01-07 |  |  | FALSE | yes
| JD3RZ07L65ST28899 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z07 - L - 65 - S | 1 | 2025-01-08 | 2025-01-09 |  |  | FALSE | yes
| JD3RZ07L65ST28900 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z07 - L - 65 - ST | 1 | 2025-01-15 | 2025-01-16 |  |  | FALSE | yes
| JD3RZ07L65ST28901 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - Z07 - L - 65 - ST | 1 | 2025-01-04 | 2025-01-05 | 2025-10-23 |  | FALSE | FALSE
| JD3RZ07L65ST28902 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - Z07 - L - 65 - ST | 1 | 2025-01-06 | 2025-01-08 |  |  | FALSE | yes
| JD3RZ07L65ST28903 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - Z07 - L - 65 - ST | 1 | 2025-01-09 | 2025-01-12 |  |  | FALSE | yes
| JD3RZ07L65ST28904 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - Z07 - L - 65 - ST | 1 | 2025-01-13 | 2025-01-14 |  |  | FALSE | yes
| JD3RZ07L65ST28905 | EXCAVATION Works for Catchbasine double - B6.33 05 39.10 - Z07 - L - 65 - ST | 1 | 2025-01-06 | 2025-01-07 | 2025-10-26 |  | FALSE | FALSE
| JD3RZ07L65ST28906 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - Z07 - L - 65 - ST | 1 | 2025-01-08 | 2025-01-11 |  |  | FALSE | yes
| JD3RZ07L65ST28907 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z07 - L - 65 - ST | 1 | 2025-01-12 | 2025-01-14 |  |  | FALSE | yes
| JD3RZ07L65ST28908 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z07 - L - 65 - ST | 1 | 2025-01-15 | 2025-01-16 |  |  | FALSE | yes
| JD3RZ07L65TSE28959.R | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 65 - TSE - Remaining | 1 | 2025-01-18 | 2025-01-19 |  |  | FALSE | yes
| JD3RZ07L65TSE28960.R | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 65 - T | 1 | 2025-01-22 | 2025-01-23 |  |  | FALSE | yes
| JD3RZ07L65TSE28961.R | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 65 - TSE - Remaining | 1 | 2025-02-01 | 2025-02-02 |  |  | FALSE | yes
| JD3RZ07L65TSE28962.R | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 65 - TSE - Remaining | 1 | 2025-02-08 | 2025-02-09 |  |  | FALSE | yes
| JD3RZ07L65TSE28963 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 65 - TSE | 1 | 2025-02-10 | 2025-02-16 |  |  | FALSE | yes
| JD3RZ07L65TSE29004 | Excavation Worksfor HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - Z07 - L - 65 - TSE | 1 | 2025-01-27 | 2025-01-28 |  |  | FALSE | yes
| JD3RZ07L65TSE29005 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - Z07 - L - 65 - TS | 1 | 2025-01-29 | 2025-01-30 |  |  | FALSE | yes
| JD3RZ07L65TSE29006 | Installing for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - Z07 - L - 65 - TSE | 1 | 2025-02-01 | 2025-02-02 |  |  | FALSE | yes
| JD3RZ07L65TSE29007 | Testing for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - Z07 - L - 65 - TSE | 1 | 2025-02-03 | 2025-02-04 |  |  | FALSE | yes
| JD3RZ07L65TSE29008 | Backfillingfor HDPE Pipes 450 mm - depth from 1.51 to 2.5 m - B4.33 31 00.10 - Z07 - L - 65 - TSE | 1 | 2025-02-05 | 2025-02-06 |  |  | FALSE | yes
| JD3RZ07L65TSE29084 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z07 - L - 65 - TSE | 1 | 2025-02-03 | 2025-02-04 |  |  | FALSE | yes
| JD3RZ07L65TSE29085 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z07 - L - 65 - TSE | 1 | 2025-02-05 | 2025-02-06 |  |  | FALSE | yes
| JD3RZ07L65WT28909 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 65 - WT | 1 | 2025-01-27 | 2025-01-28 |  |  | FALSE | yes
| JD3RZ07L65WT28910 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 65 - WT | 1 | 2025-01-29 | 2025-01-30 |  |  | FALSE | yes
| JD3RZ07L65WT28911 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 65 - WT | 1 | 2025-02-01 | 2025-02-02 |  |  | FALSE | yes
| JD3RZ07L65WT28912 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 65 - WT | 1 | 2025-02-03 | 2025-02-04 |  |  | FALSE | yes
| JD3RZ07L65WT28913 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 65 - WT | 1 | 2025-02-15 | 2025-02-16 |  |  | FALSE | yes
| JD3RZ07L65WT28944 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z07 - L - 65 - WT | 1 | 2025-02-08 | 2025-02-09 |  |  | FALSE | yes
| JD3RZ07L65WT28945 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z07 - L - 65 - WT | 1 | 2025-02-10 | 2025-02-11 |  |  | FALSE | yes
| JD3RZ07L65WT28946 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z07 - L - 65 - WT | 1 | 2025-02-12 | 2025-02-13 |  |  | FALSE | yes
| JD3RZ07L66ST29396 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 66 - ST | 1 | 2025-01-13 | 2025-01-15 |  |  | FALSE | yes
| JD3RZ07L66ST29397 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 66 | 1 | 2025-01-16 | 2025-01-19 |  |  | FALSE | yes
| JD3RZ07L66ST29398 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 66 - ST | 1 | 2025-01-20 | 2025-01-23 |  |  | FALSE | yes
| JD3RZ07L66ST29399 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 66 - ST | 1 | 2025-01-25 | 2025-01-28 |  |  | FALSE | yes
| JD3RZ07L66ST29400 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 66 - ST | 1 | 2025-02-27 | 2025-03-04 |  |  | FALSE | yes
| JD3RZ07L66ST29401 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 66 - ST | 1 | 2025-01-16 | 2025-01-18 | 2025-08-16 |  | FALSE | FALSE
| JD3RZ07L66ST29402 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 66 | 1 | 2025-01-19 | 2025-01-20 | 2025-08-18 |  | FALSE | FALSE
| JD3RZ07L66ST29403 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 66 - ST | 1 | 2025-01-21 | 2025-01-22 | 2025-08-21 |  | FALSE | FALSE
| JD3RZ07L66ST29404 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 66 - ST | 1 | 2025-01-23 | 2025-01-25 |  |  | FALSE | yes
| JD3RZ07L66ST29405 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 66 - ST | 1 | 2025-03-05 | 2025-03-06 |  |  | FALSE | yes
| JD3RZ07L66ST29406 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 66 - ST | 1 | 2025-01-23 | 2025-01-25 |  |  | FALSE | yes
| JD3RZ07L66ST29407 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 66 | 1 | 2025-01-26 | 2025-01-27 |  |  | FALSE | yes
| JD3RZ07L66ST29408 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 66 - ST | 1 | 2025-01-28 | 2025-01-29 |  |  | FALSE | yes
| JD3RZ07L66ST29409 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 66 - ST | 1 | 2025-01-30 | 2025-02-01 |  |  | FALSE | yes
| JD3RZ07L66ST29410 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 66 - ST | 1 | 2025-03-08 | 2025-03-09 |  |  | FALSE | yes
| JD3RZ07L66ST29411.R | Excavation Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m - B6.33 42 11.03 - Z07 - L - 66 - ST - Remaining | 1 | 2025-01-28 | 2025-01-29 |  |  | FALSE | yes
| JD3RZ07L66ST29412.R | Soil Replacement and Bedding Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m - B6.33 42 11.03 - Z07 - L - 66 | 1 | 2025-01-30 | 2025-02-01 |  |  | FALSE | yes
| JD3RZ07L66ST29413.R | Installing for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m - B6.33 42 11.03 - Z07 - L - 66 - ST - Remaining | 1 | 2025-02-02 | 2025-02-03 |  |  | FALSE | yes
| JD3RZ07L66ST29414.R | Primary Test for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m - B6.33 42 11.03 - Z07 - L - 66 - ST - Remaining | 1 | 2025-02-04 | 2025-02-05 |  |  | FALSE | yes
| JD3RZ07L66ST29415 | Backfilling Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m - B6.33 42 11.03 - Z07 - L - 66 - ST | 1 | 2025-02-13 | 2025-02-15 |  |  | FALSE | yes
| JD3RZ07L66ST29424 | Primary Test for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m - B6.33 42 11.05 - Z07 - L - 66 - ST | 1 | 2025-02-06 | 2025-02-08 |  |  | FALSE | yes
| JD3RZ07L66ST29425 | Backfilling Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m - B6.33 42 11.05 - Z07 - L - 66 - ST | 1 | 2025-02-13 | 2025-02-15 |  |  | FALSE | yes
| JD3RZ07L66ST29435 | Backfilling Works for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m - B6.33 42 11.07 - Z07 - L - 66 - ST | 1 | 2025-02-13 | 2025-02-15 |  |  | FALSE | yes
| JD3RZ07L66ST29439.R | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - Z07 - L - 66 - ST - Remaining | 1 | 2025-02-08 | 2025-02-09 |  |  | FALSE | yes
| JD3RZ07L66ST29440.R | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m - B6.33 42 11.08 - Z07 - L - 66 - ST - Remaining | 1 | 2025-02-11 | 2025-02-12 |  |  | FALSE | yes
| JD3RZ07L66ST29444 | Primary Test for GRP Pipe Line 800 mm - depth from 0.00 to 1.50 m - B6.33 42 11.09 - Z07 - L - 66 - ST | 1 | 2025-02-10 | 2025-02-11 |  |  | FALSE | yes
| JD3RZ07L66ST29445 | Backfilling Works for GRP Pipe Line 800 mm - depth from 0.00 to 1.50 m - B6.33 42 11.09 - Z07 - L - 66 - ST | 1 | 2025-02-13 | 2025-02-15 |  |  | FALSE | yes
| JD3RZ07L66ST29449 | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - Z07 - L - 66 - ST | 1 | 2025-02-12 | 2025-02-15 |  |  | FALSE | yes
| JD3RZ07L66ST29450 | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - Z07 - L - 66 - ST | 1 | 2025-02-16 | 2025-02-19 |  |  | FALSE | yes
| JD3RZ07L66ST29454 | Primary Test for GRP Pipe Line 900 mm - depth from 0.00 to 1.50 m - B6.33 42 11.11 - Z07 - L - 66 - ST | 1 | 2025-02-02 | 2025-02-03 |  |  | FALSE | yes
| JD3RZ07L66ST29455 | Backfilling Works for GRP Pipe Line 900 mm - depth from 0.00 to 1.50 m - B6.33 42 11.11 - Z07 - L - 66 - ST | 1 | 2025-02-16 | 2025-02-17 |  |  | FALSE | yes
| JD3RZ07L66ST29468 | Installing for GRP Pipe Line 1000 mm - depth from 0.00 to 1.50 m - B6.33 42 11.14 - Z07 - L - 66 - ST | 1 | 2025-02-02 | 2025-02-03 |  |  | FALSE | yes
| JD3RZ07L66ST29469 | Primary Test for GRP Pipe Line 1000 mm - depth from 0.00 to 1.50 m - B6.33 42 11.14 - Z07 - L - 66 - ST | 1 | 2025-02-04 | 2025-02-05 |  |  | FALSE | yes
| JD3RZ07L66ST29470 | Backfilling Works for GRP Pipe Line 1000 mm - depth from 0.00 to 1.50 m - B6.33 42 11.14 - Z07 - L - 66 - ST | 1 | 2025-02-13 | 2025-02-15 |  |  | FALSE | yes
| JD3RZ07L66ST29473 | Installing for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m - B6.33 42 11.15 - Z07 - L - 66 - ST | 1 | 2025-02-04 | 2025-02-05 |  |  | FALSE | yes
| JD3RZ07L66ST29474 | Primary Test for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m - B6.33 42 11.15 - Z07 - L - 66 - ST | 1 | 2025-02-06 | 2025-02-08 |  |  | FALSE | yes
| JD3RZ07L66ST29475 | Backfilling Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m - B6.33 42 11.15 - Z07 - L - 66 - ST | 1 | 2025-02-20 | 2025-02-22 |  |  | FALSE | yes
| JD3RZ07L66ST29581 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - L - 66 - ST | 1 | 2025-02-06 | 2025-02-08 |  |  | FALSE | yes
| JD3RZ07L66ST29582 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - L - 66 - S | 1 | 2025-02-09 | 2025-02-10 |  |  | FALSE | yes
| JD3RZ07L66ST29583 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - L - 66 - ST | 1 | 2025-02-11 | 2025-02-12 |  |  | FALSE | yes
| JD3RZ07L66ST29589.R | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - L - 66 - ST - Remaining | 1 | 2025-02-05 | 2025-02-06 |  |  | FALSE | yes
| JD3RZ07L66ST29590.R | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - L - 66 - ST - Remainin | 1 | 2025-02-09 | 2025-02-10 |  |  | FALSE | yes
| JD3RZ07L66ST29591.R | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - L - 66 - ST - Remaini | 1 | 2025-02-12 | 2025-02-13 |  |  | FALSE | yes
| JD3RZ07L66ST29592 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - L - 66 - S | 1 | 2025-02-15 | 2025-02-16 |  |  | FALSE | yes
| JD3RZ07L66ST29593 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - L - 66 - ST | 1 | 2025-02-17 | 2025-02-18 |  |  | FALSE | yes
| JD3RZ07L66ST29604 | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - L - 66 - ST | 1 | 2025-02-02 | 2025-02-03 |  |  | FALSE | yes
| JD3RZ07L66ST29605 | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - L - 66 - ST | 1 | 2025-02-04 | 2025-02-05 |  |  | FALSE | yes
| JD3RZ07L66ST29606 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - L - 66 - ST | 1 | 2025-02-06 | 2025-02-08 |  |  | FALSE | yes
| JD3RZ07L66ST29607 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - L - 66 - S | 1 | 2025-02-09 | 2025-02-10 |  |  | FALSE | yes
| JD3RZ07L66ST29608 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - L - 66 - ST | 1 | 2025-02-23 | 2025-02-24 |  |  | FALSE | yes
| JD3RZ07L66ST29614 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - Z07 - L - 66 - ST | 1 | 2025-02-04 | 2025-02-05 |  |  | FALSE | yes
| JD3RZ07L66ST29615 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - Z07 - L - 66 - ST | 1 | 2025-02-06 | 2025-02-09 |  |  | FALSE | yes
| JD3RZ07L66ST29616 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - Z07 - L - 66 - ST | 1 | 2025-02-10 | 2025-02-12 |  |  | FALSE | yes
| JD3RZ07L66ST29617 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - Z07 - L - 66 - ST | 1 | 2025-02-25 | 2025-02-26 |  |  | FALSE | yes
| JD3RZ07L66ST29618 | EXCAVATION Works for Catchbasine double - B6.33 05 39.10 - Z07 - L - 66 - ST | 1 | 2025-02-06 | 2025-02-08 |  |  | FALSE | yes
| JD3RZ07L66ST29619 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - Z07 - L - 66 - ST | 1 | 2025-02-09 | 2025-02-11 |  |  | FALSE | yes
| JD3RZ07L66ST29620 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z07 - L - 66 - ST | 1 | 2025-02-12 | 2025-02-15 |  |  | FALSE | yes
| JD3RZ07L66ST29621 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z07 - L - 66 - ST | 1 | 2025-02-27 | 2025-03-01 |  |  | FALSE | yes
| JD3RZ07L66TSE29672 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 66 - TSE | 1 | 2025-02-09 | 2025-02-12 |  |  | FALSE | yes
| JD3RZ07L66TSE29673 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 66 - T | 1 | 2025-02-13 | 2025-02-18 |  |  | FALSE | yes
| JD3RZ07L66TSE29674 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 66 - TSE | 1 | 2025-02-19 | 2025-02-27 |  |  | FALSE | yes
| JD3RZ07L66TSE29675 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 66 - TSE | 1 | 2025-03-01 | 2025-03-06 |  |  | FALSE | yes
| JD3RZ07L66TSE29676 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 66 - TSE | 1 | 2025-03-08 | 2025-03-13 |  |  | FALSE | yes
| JD3RZ07L66TSE29687 | Excavation Worksfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - Z07 - L - 66 - TSE | 1 | 2025-02-13 | 2025-02-15 |  |  | FALSE | yes
| JD3RZ07L66TSE29688 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - Z07 - L - 66 - TS | 1 | 2025-02-16 | 2025-02-17 |  |  | FALSE | yes
| JD3RZ07L66TSE29689 | Installing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - Z07 - L - 66 - TSE | 1 | 2025-02-18 | 2025-02-19 |  |  | FALSE | yes
| JD3RZ07L66TSE29690 | Testing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - Z07 - L - 66 - TSE | 1 | 2025-02-20 | 2025-02-22 |  |  | FALSE | yes
| JD3RZ07L66TSE29691 | Backfillingfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m - B4.33 31 00.04 - Z07 - L - 66 - TSE | 1 | 2025-02-23 | 2025-02-24 |  |  | FALSE | yes
| JD3RZ07L66TSE29797 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z07 - L - 66 - TSE | 1 | 2025-03-01 | 2025-03-02 |  |  | FALSE | yes
| JD3RZ07L66TSE29798 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z07 - L - 66 - TSE | 1 | 2025-03-03 | 2025-03-04 |  |  | FALSE | yes
| JD3RZ07L66TSE29801 | Installationfor butterfly valves 300 mm. - B4.33 14 19.03 - Z07 - L - 66 - TSE | 1 | 2025-03-01 | 2025-03-02 |  |  | FALSE | yes
| JD3RZ07L66TSE29802 | Testing And Commtionningfor butterfly valves 300 mm. - B4.33 14 19.03 - Z07 - L - 66 - TSE | 1 | 2025-03-03 | 2025-03-04 |  |  | FALSE | yes
| JD3RZ07L66TSE29815 | Installationfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - Z07 - L - 66 - TSE | 1 | 2025-03-01 | 2025-03-02 |  |  | FALSE | yes
| JD3RZ07L66TSE29816 | Testing And Commtionningfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - Z07 - L - 66 | 1 | 2025-03-03 | 2025-03-04 |  |  | FALSE | yes
| JD3RZ07L66TSE29821 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - Z07 - L - 66 - TSE | 1 | 2025-02-13 | 2025-02-15 |  |  | FALSE | yes
| JD3RZ07L66TSE29822 | Plain Concrete Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - Z07 - L - 66 - TSE | 1 | 2025-02-16 | 2025-02-17 |  |  | FALSE | yes
| JD3RZ07L66TSE29823 | INSTALLATIONfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - Z07 - L - 66 - TSE | 1 | 2025-02-18 | 2025-02-19 |  |  | FALSE | yes
| JD3RZ07L66TSE29824 | Backfilling Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - Z07 - L - 66 - TSE | 1 | 2025-02-20 | 2025-02-22 |  |  | FALSE | yes
| JD3RZ07L66TSE29845 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z07 - L - 66 - TSE | 1 | 2025-02-13 | 2025-02-15 |  |  | FALSE | yes
| JD3RZ07L66TSE29846 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z07 - L - 66 - TSE | 1 | 2025-02-16 | 2025-02-17 |  |  | FALSE | yes
| JD3RZ07L66TSE29847 | INSTALLATIONfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z07 - L - 66 - TSE | 1 | 2025-02-18 | 2025-02-19 |  |  | FALSE | yes
| JD3RZ07L66TSE29848 | Backfilling Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z07 - L - 66 - TSE | 1 | 2025-02-20 | 2025-02-22 |  |  | FALSE | yes
| JD3RZ07L66WT29622 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 66 - WT | 1 | 2025-03-10 | 2025-03-11 |  |  | FALSE | yes
| JD3RZ07L66WT29623 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 66 - WT | 1 | 2025-03-12 | 2025-03-13 |  |  | FALSE | yes
| JD3RZ07L66WT29624 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 66 - WT | 1 | 2025-03-15 | 2025-03-16 |  |  | FALSE | yes
| JD3RZ07L66WT29625 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 66 - WT | 1 | 2025-03-17 | 2025-03-18 |  |  | FALSE | yes
| JD3RZ07L66WT29626 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 66 - WT | 1 | 2025-03-19 | 2025-03-20 |  |  | FALSE | yes
| JD3RZ07L66WT29657 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z07 - L - 66 - WT | 1 | 2025-03-12 | 2025-03-13 |  |  | FALSE | yes
| JD3RZ07L66WT29658 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z07 - L - 66 - WT | 1 | 2025-03-15 | 2025-03-16 |  |  | FALSE | yes
| JD3RZ07L66WT29659 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z07 - L - 66 - WT | 1 | 2025-03-17 | 2025-03-18 |  |  | FALSE | yes
| JD3RZ07L67ST30109 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 67 - ST | 1 | 2025-01-16 | 2025-01-18 |  |  | FALSE | yes
| JD3RZ07L67ST30110 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 67 | 1 | 2025-01-19 | 2025-01-20 |  |  | FALSE | yes
| JD3RZ07L67ST30111 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 67 - ST | 1 | 2025-01-21 | 2025-01-22 |  |  | FALSE | yes
| JD3RZ07L67ST30112 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 67 - ST | 1 | 2025-01-23 | 2025-01-25 |  |  | FALSE | yes
| JD3RZ07L67ST30113 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 67 - ST | 1 | 2025-01-26 | 2025-01-27 |  |  | FALSE | yes
| JD3RZ07L67ST30114.R | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 67 - ST - Remaining | 1 | 2025-01-21 | 2025-01-22 | 2025-10-15 |  | FALSE | FALSE
| JD3RZ07L67ST30115 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 67 | 1 | 2025-01-23 | 2025-01-25 | 2025-10-02 |  | FALSE | FALSE
| JD3RZ07L67ST30116 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 67 - ST | 1 | 2025-01-26 | 2025-01-27 | 2025-10-04 |  | FALSE | FALSE
| JD3RZ07L67ST30117 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 67 - ST | 1 | 2025-01-28 | 2025-01-29 |  |  | FALSE | yes
| JD3RZ07L67ST30118 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 67 - ST | 1 | 2025-01-30 | 2025-02-01 |  |  | FALSE | yes
| JD3RZ07L67ST30119 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 67 - ST | 1 | 2025-01-23 | 2025-01-25 |  |  | FALSE | yes
| JD3RZ07L67ST30120 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 67 | 1 | 2025-01-26 | 2025-01-27 |  |  | FALSE | yes
| JD3RZ07L67ST30121 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 67 - ST | 1 | 2025-01-28 | 2025-01-29 |  |  | FALSE | yes
| JD3RZ07L67ST30122 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 67 - ST | 1 | 2025-01-30 | 2025-02-01 |  |  | FALSE | yes
| JD3RZ07L67ST30123 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 67 - ST | 1 | 2025-02-02 | 2025-02-03 |  |  | FALSE | yes
| JD3RZ07L67ST30127 | Primary Test for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m - B6.33 42 11.03 - Z07 - L - 67 - ST | 1 | 2025-02-02 | 2025-02-03 |  |  | FALSE | yes
| JD3RZ07L67ST30128 | Backfilling Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m - B6.33 42 11.03 - Z07 - L - 67 - ST | 1 | 2025-02-04 | 2025-02-05 |  |  | FALSE | yes
| JD3RZ07L67ST30138 | Backfilling Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m - B6.33 42 11.05 - Z07 - L - 67 - ST | 1 | 2025-02-16 | 2025-02-17 | 2025-04-05 |  | FALSE | FALSE
| JD3RZ07L67ST30143 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m - B6.33 42 11.06 - Z07 - L - 67 - ST | 1 | 2025-02-18 | 2025-02-19 |  |  | FALSE | yes
| JD3RZ07L67ST30217 | Primary Test for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - Z07 - L - 67 - ST | 1 | 2025-02-04 | 2025-02-05 |  |  | FALSE | yes
| JD3RZ07L67ST30218 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m - B6.33 42 11.23 - Z07 - L - 67 - ST | 1 | 2025-02-06 | 2025-02-08 |  |  | FALSE | yes
| JD3RZ07L67ST30292.R | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - L - 67 - ST - Remaining | 1 | 2025-01-30 | 2025-02-01 |  |  | FALSE | yes
| JD3RZ07L67ST30293.R | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - L - 67 - ST - Remainin | 1 | 2025-02-02 | 2025-02-03 |  |  | FALSE | yes
| JD3RZ07L67ST30294.R | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - L - 67 - ST - Remaini | 1 | 2025-02-04 | 2025-02-05 | 2025-10-20 |  | FALSE | FALSE
| JD3RZ07L67ST30295 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - L - 67 - S | 1 | 2025-02-06 | 2025-02-08 |  |  | FALSE | yes
| JD3RZ07L67ST30296 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - L - 67 - ST | 1 | 2025-02-09 | 2025-02-10 |  |  | FALSE | yes
| JD3RZ07L67ST30322 | Excavation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z07 - L - 67 - ST | 1 | 2025-01-30 | 2025-02-01 |  |  | FALSE | yes
| JD3RZ07L67ST30323 | Base Plain Concrete Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z07 - L - 67 - ST | 1 | 2025-02-02 | 2025-02-03 |  |  | FALSE | yes
| JD3RZ07L67ST30324 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z07 - L - 67 - ST | 1 | 2025-02-04 | 2025-02-05 |  |  | FALSE | yes
| JD3RZ07L67ST30325 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z07 - L - 67 - S | 1 | 2025-02-06 | 2025-02-08 |  |  | FALSE | yes
| JD3RZ07L67ST30326 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - B6.33 05 39.08 - Z07 - L - 67 - ST | 1 | 2025-02-09 | 2025-02-10 |  |  | FALSE | yes
| JD3RZ07L67ST30327 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - Z07 - L - 67 - ST | 1 | 2025-02-02 | 2025-02-03 |  |  | FALSE | yes
| JD3RZ07L67ST30328 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - Z07 - L - 67 - ST | 1 | 2025-02-04 | 2025-02-05 |  |  | FALSE | yes
| JD3RZ07L67ST30329 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - Z07 - L - 67 - ST | 1 | 2025-02-06 | 2025-02-08 |  |  | FALSE | yes
| JD3RZ07L67ST30330 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - Z07 - L - 67 - ST | 1 | 2025-02-09 | 2025-02-10 |  |  | FALSE | yes
| JD3RZ07L67ST30331 | EXCAVATION Works for Catchbasine double - B6.33 05 39.10 - Z07 - L - 67 - ST | 1 | 2025-02-04 | 2025-02-05 |  |  | FALSE | yes
| JD3RZ07L67ST30332 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - Z07 - L - 67 - ST | 1 | 2025-02-06 | 2025-02-08 |  |  | FALSE | yes
| JD3RZ07L67ST30333 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z07 - L - 67 - ST | 1 | 2025-02-09 | 2025-02-10 |  |  | FALSE | yes
| JD3RZ07L67ST30334 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z07 - L - 67 - ST | 1 | 2025-02-11 | 2025-02-12 |  |  | FALSE | yes
| JD3RZ07L67TSE30385 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 67 - TSE | 1 | 2025-02-13 | 2025-02-15 |  |  | FALSE | yes
| JD3RZ07L67TSE30386 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 67 - T | 1 | 2025-02-16 | 2025-02-17 |  |  | FALSE | yes
| JD3RZ07L67TSE30387 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 67 - TSE | 1 | 2025-02-18 | 2025-02-19 |  |  | FALSE | yes
| JD3RZ07L67TSE30388 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 67 - TSE | 1 | 2025-02-20 | 2025-02-22 |  |  | FALSE | yes
| JD3RZ07L67TSE30389 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 67 - TSE | 1 | 2025-03-06 | 2025-03-08 |  |  | FALSE | yes
| JD3RZ07L67TSE30398 | Testing for HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - Z07 - L - 67 - TSE | 1 | 2025-02-23 | 2025-02-24 |  |  | FALSE | yes
| JD3RZ07L67TSE30399 | Backfillingfor HDPE Pipes 315 mm - depth from 0 to 1.5 m - B4.33 31 00.03 - Z07 - L - 67 - TSE | 1 | 2025-02-25 | 2025-02-26 | 2025-08-23 |  | FALSE | FALSE
| JD3RZ07L67TSE30510 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z07 - L - 67 - TSE | 1 | 2025-03-02 | 2025-03-03 |  |  | FALSE | yes
| JD3RZ07L67TSE30511 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z07 - L - 67 - TSE | 1 | 2025-03-04 | 2025-03-05 |  |  | FALSE | yes
| JD3RZ07L67TSE30514 | Installationfor butterfly valves 300 mm. - B4.33 14 19.03 - Z07 - L - 67 - TSE | 1 | 2025-02-20 | 2025-02-22 |  |  | FALSE | yes
| JD3RZ07L67TSE30515 | Testing And Commtionningfor butterfly valves 300 mm. - B4.33 14 19.03 - Z07 - L - 67 - TSE | 1 | 2025-02-23 | 2025-02-24 |  |  | FALSE | yes
| JD3RZ07L67TSE30534 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - Z07 - L - 67 - TSE | 1 | 2025-02-16 | 2025-02-17 |  |  | FALSE | yes
| JD3RZ07L67TSE30535 | Plain Concrete Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - Z07 - L - 67 - TSE | 1 | 2025-02-18 | 2025-02-19 |  |  | FALSE | yes
| JD3RZ07L67TSE30536 | INSTALLATIONfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - Z07 - L - 67 - TSE | 1 | 2025-02-20 | 2025-02-22 |  |  | FALSE | yes
| JD3RZ07L67TSE30537 | Backfilling Worksfor R.C Valve Chamber - 315 to 400 MM - B4.33 14 13.01 - Z07 - L - 67 - TSE | 1 | 2025-02-23 | 2025-02-24 |  |  | FALSE | yes
| JD3RZ07L67WT30335 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 67 - WT | 1 | 2025-03-09 | 2025-03-10 |  |  | FALSE | yes
| JD3RZ07L67WT30336 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 67 - WT | 1 | 2025-03-11 | 2025-03-12 |  |  | FALSE | yes
| JD3RZ07L67WT30337 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 67 - WT | 1 | 2025-03-13 | 2025-03-15 |  |  | FALSE | yes
| JD3RZ07L67WT30338 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 67 - WT | 1 | 2025-03-16 | 2025-03-17 |  |  | FALSE | yes
| JD3RZ07L67WT30339 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 67 - WT | 1 | 2025-03-18 | 2025-03-19 |  |  | FALSE | yes
| JD3RZ07L67WT30370 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z07 - L - 67 - WT | 1 | 2025-03-09 | 2025-03-10 |  |  | FALSE | yes
| JD3RZ07L67WT30371 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z07 - L - 67 - WT | 1 | 2025-03-11 | 2025-03-12 |  |  | FALSE | yes
| JD3RZ07L67WT30372 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z07 - L - 67 - WT | 1 | 2025-03-13 | 2025-03-15 |  |  | FALSE | yes
| JD3RZ07L68ST30822 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 68 - ST | 1 | 2025-01-25 | 2025-01-26 |  |  | FALSE | yes
| JD3RZ07L68ST30823 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 68 | 1 | 2025-01-27 | 2025-01-28 |  |  | FALSE | yes
| JD3RZ07L68ST30824 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 68 - ST | 1 | 2025-01-29 | 2025-01-30 |  |  | FALSE | yes
| JD3RZ07L68ST30825 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 68 - ST | 1 | 2025-02-01 | 2025-02-02 |  |  | FALSE | yes
| JD3RZ07L68ST30826 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m - B6.33 14 11.01 - Z07 - L - 68 - ST | 1 | 2025-02-03 | 2025-02-04 |  |  | FALSE | yes
| JD3RZ07L68ST30827 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 68 - ST | 1 | 2025-01-27 | 2025-01-28 |  |  | FALSE | yes
| JD3RZ07L68ST30828 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 68 | 1 | 2025-01-29 | 2025-01-30 |  |  | FALSE | yes
| JD3RZ07L68ST30829 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 68 - ST | 1 | 2025-02-01 | 2025-02-02 |  |  | FALSE | yes
| JD3RZ07L68ST30830 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 68 - ST | 1 | 2025-02-03 | 2025-02-04 |  |  | FALSE | yes
| JD3RZ07L68ST30831 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m - B6.33 42 11.01 - Z07 - L - 68 - ST | 1 | 2025-02-05 | 2025-02-06 |  |  | FALSE | yes
| JD3RZ07L68ST30832 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 68 - ST | 1 | 2025-01-29 | 2025-01-30 |  |  | FALSE | yes
| JD3RZ07L68ST30833 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 68 | 1 | 2025-02-01 | 2025-02-02 |  |  | FALSE | yes
| JD3RZ07L68ST30834 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 68 - ST | 1 | 2025-02-03 | 2025-02-04 |  |  | FALSE | yes
| JD3RZ07L68ST30835 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 68 - ST | 1 | 2025-02-05 | 2025-02-06 |  |  | FALSE | yes
| JD3RZ07L68ST30836 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m - B6.33 42 11.02 - Z07 - L - 68 - ST | 1 | 2025-02-08 | 2025-02-09 |  |  | FALSE | yes
| JD3RZ07L68ST30840 | Primary Test for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m - B6.33 42 11.03 - Z07 - L - 68 - ST | 1 | 2025-02-08 | 2025-02-09 |  |  | FALSE | yes
| JD3RZ07L68ST30841 | Backfilling Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m - B6.33 42 11.03 - Z07 - L - 68 - ST | 1 | 2025-02-10 | 2025-02-11 |  |  | FALSE | yes
| JD3RZ07L68ST30850 | Primary Test for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m - B6.33 42 11.05 - Z07 - L - 68 - ST | 1 | 2025-02-08 | 2025-02-09 |  |  | FALSE | yes
| JD3RZ07L68ST30851 | Backfilling Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m - B6.33 42 11.05 - Z07 - L - 68 - ST | 1 | 2025-02-10 | 2025-02-11 |  |  | FALSE | yes
| JD3RZ07L68ST30860 | Primary Test for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m - B6.33 42 11.07 - Z07 - L - 68 - ST | 1 | 2025-02-10 | 2025-02-11 |  |  | FALSE | yes
| JD3RZ07L68ST30861 | Backfilling Works for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m - B6.33 42 11.07 - Z07 - L - 68 - ST | 1 | 2025-02-12 | 2025-02-13 |  |  | FALSE | yes
| JD3RZ07L68ST30875 | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - Z07 - L - 68 - ST | 1 | 2025-02-12 | 2025-02-13 |  |  | FALSE | yes
| JD3RZ07L68ST30876 | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m - B6.33 42 11.10 - Z07 - L - 68 - ST | 1 | 2025-02-15 | 2025-02-16 |  |  | FALSE | yes
| JD3RZ07L68ST30885 | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - Z07 - L - 68 - ST | 1 | 2025-02-15 | 2025-02-16 |  |  | FALSE | yes
| JD3RZ07L68ST30886 | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m - B6.33 42 11.12 - Z07 - L - 68 - ST | 1 | 2025-02-17 | 2025-02-18 |  |  | FALSE | yes
| JD3RZ07L68ST30910 | Primary Test for GRP Pipe Line 1100 mm - depth from 0.00 to 1.50 m - B6.33 42 11.19 - Z07 - L - 68 - ST | 1 | 2025-02-10 | 2025-02-11 |  |  | FALSE | yes
| JD3RZ07L68ST30911 | Backfilling Works for GRP Pipe Line 1100 mm - depth from 0.00 to 1.50 m - B6.33 42 11.19 - Z07 - L - 68 - ST | 1 | 2025-02-12 | 2025-02-13 |  |  | FALSE | yes
| JD3RZ07L68ST30915 | Primary Test for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m - B6.33 42 11.20 - Z07 - L - 68 - ST | 1 | 2025-02-12 | 2025-02-13 |  |  | FALSE | yes
| JD3RZ07L68ST30916 | Backfilling Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m - B6.33 42 11.20 - Z07 - L - 68 - ST | 1 | 2025-02-15 | 2025-02-16 |  |  | FALSE | yes
| JD3RZ07L68ST31007 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - L - 68 - ST | 1 | 2025-02-12 | 2025-02-13 |  |  | FALSE | yes
| JD3RZ07L68ST31008 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - L - 68 - S | 1 | 2025-02-15 | 2025-02-16 |  |  | FALSE | yes
| JD3RZ07L68ST31009 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - B6.33 05 39.02 - Z07 - L - 68 - ST | 1 | 2025-02-17 | 2025-02-18 |  |  | FALSE | yes
| JD3RZ07L68ST31017.R | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - L - 68 - ST - Remaini | 1 | 2025-02-24 | 2025-02-25 |  |  | FALSE | yes
| JD3RZ07L68ST31018 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - L - 68 - S | 1 | 2025-02-26 | 2025-02-27 |  |  | FALSE | yes
| JD3RZ07L68ST31019 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - B6.33 05 39.04 - Z07 - L - 68 - ST | 1 | 2025-03-01 | 2025-03-02 |  |  | FALSE | yes
| JD3RZ07L68ST31022 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - L - 68 - ST | 1 | 2025-02-12 | 2025-02-13 |  |  | FALSE | yes
| JD3RZ07L68ST31023 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - L - 68 - S | 1 | 2025-02-15 | 2025-02-16 |  |  | FALSE | yes
| JD3RZ07L68ST31024 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - B6.33 05 39.05 - Z07 - L - 68 - ST | 1 | 2025-02-17 | 2025-02-18 |  |  | FALSE | yes
| JD3RZ07L68ST31031 | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - L - 68 - ST | 1 | 2025-02-12 | 2025-02-13 |  |  | FALSE | yes
| JD3RZ07L68ST31032 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - L - 68 - ST | 1 | 2025-02-15 | 2025-02-16 |  |  | FALSE | yes
| JD3RZ07L68ST31033 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - L - 68 - S | 1 | 2025-02-17 | 2025-02-18 |  |  | FALSE | yes
| JD3RZ07L68ST31034 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - B6.33 05 39.07 - Z07 - L - 68 - ST | 1 | 2025-02-19 | 2025-02-20 |  |  | FALSE | yes
| JD3RZ07L68ST31040 | EXCAVATION Works for Catchbasine single - B6.33 05 39.09 - Z07 - L - 68 - ST | 1 | 2025-02-12 | 2025-02-13 |  |  | FALSE | yes
| JD3RZ07L68ST31041 | Catchbasine Installation Works For Catchbasine single - B6.33 05 39.09 - Z07 - L - 68 - ST | 1 | 2025-02-15 | 2025-02-16 |  |  | FALSE | yes
| JD3RZ07L68ST31042 | FINISHING Works For Catchbasine single - B6.33 05 39.09 - Z07 - L - 68 - ST | 1 | 2025-02-17 | 2025-02-18 |  |  | FALSE | yes
| JD3RZ07L68ST31043 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - B6.33 05 39.09 - Z07 - L - 68 - ST | 1 | 2025-02-19 | 2025-02-20 |  |  | FALSE | yes
| JD3RZ07L68ST31044 | EXCAVATION Works for Catchbasine double - B6.33 05 39.10 - Z07 - L - 68 - ST | 1 | 2025-02-15 | 2025-02-16 |  |  | FALSE | yes
| JD3RZ07L68ST31045 | Catchbasine Installation Works For Catchbasine double - B6.33 05 39.10 - Z07 - L - 68 - ST | 1 | 2025-02-17 | 2025-02-18 |  |  | FALSE | yes
| JD3RZ07L68ST31046 | FINISHING Works For Catchbasine double - B6.33 05 39.10 - Z07 - L - 68 - ST | 1 | 2025-02-19 | 2025-02-20 |  |  | FALSE | yes
| JD3RZ07L68ST31047 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - B6.33 05 39.10 - Z07 - L - 68 - ST | 1 | 2025-02-22 | 2025-02-23 |  |  | FALSE | yes
| JD3RZ07L68TSE31098 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 68 - TSE | 1 | 2025-03-03 | 2025-03-04 |  |  | FALSE | yes
| JD3RZ07L68TSE31099 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 68 - T | 1 | 2025-03-05 | 2025-03-06 |  |  | FALSE | yes
| JD3RZ07L68TSE31100 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 68 - TSE | 1 | 2025-03-08 | 2025-03-09 |  |  | FALSE | yes
| JD3RZ07L68TSE31101 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 68 - TSE | 1 | 2025-03-10 | 2025-03-11 |  |  | FALSE | yes
| JD3RZ07L68TSE31102 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z07 - L - 68 - TSE | 1 | 2025-03-15 | 2025-03-16 |  |  | FALSE | yes
| JD3RZ07L68TSE31223 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z07 - L - 68 - TSE | 1 | 2025-03-10 | 2025-03-11 |  |  | FALSE | yes
| JD3RZ07L68TSE31224 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z07 - L - 68 - TSE | 1 | 2025-03-12 | 2025-03-13 |  |  | FALSE | yes
| JD3RZ07L68TSE31241 | Installationfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - Z07 - L - 68 - TSE | 1 | 2025-03-10 | 2025-03-11 |  |  | FALSE | yes
| JD3RZ07L68TSE31242 | Testing And Commtionningfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - Z07 - L - 68 | 1 | 2025-03-12 | 2025-03-13 |  |  | FALSE | yes
| JD3RZ07L68TSE31271 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z07 - L - 68 - TSE | 1 | 2025-03-03 | 2025-03-04 |  |  | FALSE | yes
| JD3RZ07L68TSE31272 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z07 - L - 68 - TSE | 1 | 2025-03-05 | 2025-03-06 |  |  | FALSE | yes
| JD3RZ07L68TSE31273 | INSTALLATIONfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z07 - L - 68 - TSE | 1 | 2025-03-08 | 2025-03-09 |  |  | FALSE | yes
| JD3RZ07L68TSE31274 | Backfilling Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z07 - L - 68 - TSE | 1 | 2025-03-15 | 2025-03-16 |  |  | FALSE | yes
| JD3RZ07L68WT31048 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 68 - WT | 1 | 2025-03-18 | 2025-03-19 |  |  | FALSE | yes
| JD3RZ07L68WT31049 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 68 - WT | 1 | 2025-03-20 | 2025-03-22 |  |  | FALSE | yes
| JD3RZ07L68WT31050 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 68 - WT | 1 | 2025-03-23 | 2025-03-24 |  |  | FALSE | yes
| JD3RZ07L68WT31051 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 68 - WT | 1 | 2025-03-25 | 2025-03-26 |  |  | FALSE | yes
| JD3RZ07L68WT31052 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m - B3.33 14 13.01 - Z07 - L - 68 - WT | 1 | 2025-03-27 | 2025-03-29 |  |  | FALSE | yes
| JD3RZ07L68WT31083 | EXCAVATION and Bedding Worksfor Fire Hydrant - B3.33 14 19.08 - Z07 - L - 68 - WT | 1 | 2025-03-20 | 2025-03-22 |  |  | FALSE | yes
| JD3RZ07L68WT31084 | INSTALLATIONfor Fire Hydrant - B3.33 14 19.08 - Z07 - L - 68 - WT | 1 | 2025-03-23 | 2025-03-24 |  |  | FALSE | yes
| JD3RZ07L68WT31085 | TESTING AND COMMITIONfor Fire Hydrant - B3.33 14 19.08 - Z07 - L - 68 - WT | 1 | 2025-03-25 | 2025-03-26 |  |  | FALSE | yes
| JD3RZ08L42SUR01 | Surveying Works L - 42 | 1 |  |  |  |  | yes | FALSE
| JD3RZ08L42TSE34663 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z08 - L - 42 - TSE | 1 | 2026-02-28 | 2026-03-02 |  |  | FALSE | yes
| JD3RZ08L42TSE34664 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z08 - L - 42 - T | 1 | 2026-03-03 | 2026-03-05 |  |  | FALSE | yes
| JD3RZ08L42TSE34665 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z08 - L - 42 - TSE | 1 | 2026-03-07 | 2026-03-12 |  |  | FALSE | yes
| JD3RZ08L42TSE34666 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z08 - L - 42 - TSE | 1 | 2026-03-14 | 2026-03-17 |  |  | FALSE | yes
| JD3RZ08L42TSE34667 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z08 - L - 42 - TSE | 1 | 2026-03-18 | 2026-03-22 |  |  | FALSE | yes
| JD3RZ08L42TSE34788 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z08 - L - 42 - TSE | 1 | 2026-03-14 | 2026-03-15 |  |  | FALSE | yes
| JD3RZ08L42TSE34789 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z08 - L - 42 - TSE | 1 | 2026-03-16 | 2026-03-17 |  |  | FALSE | yes
| JD3RZ08L43TSE35376 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z08 - L - 43 - TSE | 1 | 2026-01-04 | 2026-01-05 |  |  | FALSE | yes
| JD3RZ08L43TSE35377 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z08 - L - 43 - T | 1 | 2026-01-06 | 2026-01-07 |  |  | FALSE | yes
| JD3RZ08L43TSE35378 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z08 - L - 43 - TSE | 1 | 2026-01-08 | 2026-01-10 |  |  | FALSE | yes
| JD3RZ08L43TSE35379 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z08 - L - 43 - TSE | 1 | 2026-01-11 | 2026-01-12 |  |  | FALSE | yes
| JD3RZ08L43TSE35380 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z08 - L - 43 - TSE | 1 | 2026-01-15 | 2026-01-17 |  |  | FALSE | yes
| JD3RZ08L43TSE35382 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z08 - L - 43 - T | 1 | 2026-01-10 | 2026-01-12 | 2025-10-23 |  | FALSE | yes
| JD3RZ08L43TSE35383 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z08 - L - 43 - TSE | 1 | 2026-01-13 | 2026-01-19 | 2025-10-25 |  | FALSE | yes
| JD3RZ08L43TSE35384 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z08 - L - 43 - TSE | 1 | 2026-01-20 | 2026-01-24 |  |  | FALSE | yes
| JD3RZ08L43TSE35385 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m - B4.33 31 00.02 - Z08 - L - 43 - TSE | 1 | 2026-01-25 | 2026-01-28 |  |  | FALSE | yes
| JD3RZ08L43TSE35501 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z08 - L - 43 - TSE | 1 | 2026-01-11 | 2026-01-12 |  |  | FALSE | yes
| JD3RZ08L43TSE35502 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z08 - L - 43 - TSE | 1 | 2026-01-13 | 2026-01-14 |  |  | FALSE | yes
| JD3RZ08L43TSE35503 | Installationfor gate valves 250 mm - B4.33 14 19.02 - Z08 - L - 43 - TSE | 1 | 2026-01-20 | 2026-01-21 |  |  | FALSE | yes
| JD3RZ08L43TSE35504 | Testing And Commtionningfor gate valves 250 mm - B4.33 14 19.02 - Z08 - L - 43 - TSE | 1 | 2026-01-22 | 2026-01-24 |  |  | FALSE | yes
| JD3RZ08L43TSE35519 | Installationfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - Z08 - L - 43 - TSE | 1 | 2026-01-11 | 2026-01-12 |  |  | FALSE | yes
| JD3RZ08L43TSE35520 | Testing And Commtionningfor Air valves 50 mm. - on pipes with diameter less than 315 mm - B4.33 14 19.15 - Z08 - L - 43 | 1 | 2026-01-13 | 2026-01-14 |  |  | FALSE | yes
| JD3RZ08L43TSE35549 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z08 - L - 43 - TSE | 1 | 2026-01-10 | 2026-01-11 |  |  | FALSE | yes
| JD3RZ08L43TSE35550 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z08 - L - 43 - TSE | 1 | 2026-01-12 | 2026-01-13 |  |  | FALSE | yes
| JD3RZ08L43TSE35551 | INSTALLATIONfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z08 - L - 43 - TSE | 1 | 2026-01-14 | 2026-01-15 |  |  | FALSE | yes
| JD3RZ08L43TSE35552 | Backfilling Worksfor Air Valve Chamber - less than 315 mm - B4.33 14 13.10 - Z08 - L - 43 - TSE | 1 | 2026-01-17 | 2026-01-18 |  |  | FALSE | yes
| JD3RZ08L44SUR01 | Surveying Works L - 44 | 1 |  |  |  |  | yes | FALSE
| JD3RZ08L44TSE36089 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z08 - L - 44 - TSE | 1 | 2026-01-07 | 2026-01-08 |  |  | FALSE | yes
| JD3RZ08L44TSE36090 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z08 - L - 44 - T | 1 | 2026-01-10 | 2026-01-12 |  |  | FALSE | yes
| JD3RZ08L44TSE36091 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z08 - L - 44 - TSE | 1 | 2026-01-13 | 2026-01-17 |  |  | FALSE | yes
| JD3RZ08L44TSE36092 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z08 - L - 44 - TSE | 1 | 2026-01-18 | 2026-01-20 |  |  | FALSE | yes
| JD3RZ08L44TSE36093 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z08 - L - 44 - TSE | 1 | 2026-01-22 | 2026-01-25 |  |  | FALSE | yes
| JD3RZ08L44TSE36214 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z08 - L - 44 - TSE | 1 | 2026-01-18 | 2026-01-19 |  |  | FALSE | yes
| JD3RZ08L44TSE36215 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z08 - L - 44 - TSE | 1 | 2026-01-20 | 2026-01-21 |  |  | FALSE | yes
| JD3RZ08L45SUR01 | Surveying Works L - 45 | 1 |  |  |  |  | yes | FALSE
| JD3RZ08L45TSE36802 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z08 - L - 45 - TSE | 1 | 2026-02-16 | 2026-02-17 |  |  | FALSE | yes
| JD3RZ08L45TSE36803 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z08 - L - 45 - T | 1 | 2026-02-18 | 2026-02-19 |  |  | FALSE | yes
| JD3RZ08L45TSE36804 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z08 - L - 45 - TSE | 1 | 2026-02-21 | 2026-02-24 |  |  | FALSE | yes
| JD3RZ08L45TSE36805 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z08 - L - 45 - TSE | 1 | 2026-02-25 | 2026-02-28 |  |  | FALSE | yes
| JD3RZ08L45TSE36806 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z08 - L - 45 - TSE | 1 | 2026-03-02 | 2026-03-04 |  |  | FALSE | yes
| JD3RZ08L45TSE36927 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z08 - L - 45 - TSE | 1 | 2026-02-25 | 2026-02-26 |  |  | FALSE | yes
| JD3RZ08L45TSE36928 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z08 - L - 45 - TSE | 1 | 2026-02-28 | 2026-03-01 |  |  | FALSE | yes
| JD3RZ08L46SUR01 | Surveying Works L - 46 | 1 |  |  |  |  | yes | FALSE
| JD3RZ08L46TSE37515 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z08 - L - 46 - TSE | 1 | 2026-02-07 | 2026-02-08 |  |  | FALSE | yes
| JD3RZ08L46TSE37516 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z08 - L - 46 - T | 1 | 2026-02-09 | 2026-02-10 |  |  | FALSE | yes
| JD3RZ08L46TSE37517 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z08 - L - 46 - TSE | 1 | 2026-02-11 | 2026-02-12 |  |  | FALSE | yes
| JD3RZ08L46TSE37518 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z08 - L - 46 - TSE | 1 | 2026-02-14 | 2026-02-15 |  |  | FALSE | yes
| JD3RZ08L46TSE37519 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m - B4.33 31 00.01 - Z08 - L - 46 - TSE | 1 | 2026-02-18 | 2026-02-19 |  |  | FALSE | yes
| JD3RZ08L46TSE37640 | Installationfor gate valves 100 mm - B4.33 14 19.01 - Z08 - L - 46 - TSE | 1 | 2026-02-14 | 2026-02-15 |  |  | FALSE | yes
| JD3RZ08L46TSE37641 | Testing And Commtionningfor gate valves 100 mm - B4.33 14 19.01 - Z08 - L - 46 - TSE | 1 | 2026-02-16 | 2026-02-17 |  |  | FALSE | yes
| JD3RZ08RCBST21652 | Excavation Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z08 - RCB - ST | 1 | 2026-01-26 | 2026-01-29 |  |  | FALSE | yes
| JD3RZ08RCBST21653 | Soil Replacement and Bedding Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z08 - RCB | 1 | 2026-01-31 | 2026-02-04 |  |  | FALSE | yes
| JD3RZ08RCBST21654 | Installing for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z08 - RCB - ST | 1 | 2026-02-05 | 2026-02-11 |  |  | FALSE | yes
| JD3RZ08RCBST21655 | Primary Test for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z08 - RCB - ST | 1 | 2026-02-12 | 2026-02-18 |  |  | FALSE | yes
| JD3RZ08RCBST21656 | Backfilling Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z08 - RCB - ST | 1 | 2026-02-19 | 2026-02-28 |  |  | FALSE | yes
| JD3RZ08RCBST21662 | Excavation Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z08 - RCB - ST | 1 | 2026-01-31 | 2026-02-03 |  |  | FALSE | yes
| JD3RZ08RCBST21663 | Soil Replacement and Bedding Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z08 - RCB - | 1 | 2026-02-04 | 2026-02-08 |  |  | FALSE | yes
| JD3RZ08RCBST21664 | Installing for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z08 - RCB - ST | 1 | 2026-02-09 | 2026-02-14 |  |  | FALSE | yes
| JD3RZ08RCBST21665 | Primary Test for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z08 - RCB - ST | 1 | 2026-02-15 | 2026-02-18 |  |  | FALSE | yes
| JD3RZ08RCBST21666 | Backfilling Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z08 - RCB - ST | 1 | 2026-02-19 | 2026-02-25 |  |  | FALSE | yes
| JD3RZ08RCBST21870 | EXCAVATION Works for Catchbasine - B6.33 05 39.09 - single - Z08 - RCB - ST | 1 | 2026-02-04 | 2026-02-11 |  |  | FALSE | yes
| JD3RZ08RCBST21871 | Catchbasine Installation Works for Catchbasine - B6.33 05 39.09 - single - Z08 - RCB - ST | 1 | 2026-02-12 | 2026-02-23 |  |  | FALSE | yes
| JD3RZ08RCBST21872 | FINISHING Works for Catchbasine - B6.33 05 39.09 - single - Z08 - RCB - ST | 1 | 2026-02-24 | 2026-03-07 |  |  | FALSE | yes
| JD3RZ08RCBST21873 | TESTING AND COMMITIONING RELEASED for Catchbasine - B6.33 05 39.09 - single - Z08 - RCB - ST | 1 | 2026-03-08 | 2026-03-15 |  |  | FALSE | yes
| JD3RZ08RCBST21874 | EXCAVATION Works for Catchbasine - B6.33 05 39.10 - double - Z08 - RCB - ST | 1 | 2026-02-12 | 2026-02-16 |  |  | FALSE | yes
| JD3RZ08RCBST21875 | Catchbasine Installation Works for Catchbasine - B6.33 05 39.10 - double - Z08 - RCB - ST | 1 | 2026-02-17 | 2026-02-22 |  |  | FALSE | yes
| JD3RZ08RCBST21876 | FINISHING Works for Catchbasine - B6.33 05 39.10 - double - Z08 - RCB - ST | 1 | 2026-02-23 | 2026-02-28 |  |  | FALSE | yes
| JD3RZ08RCBST21877 | TESTING AND COMMITIONING RELEASED for Catchbasine - B6.33 05 39.10 - double - Z08 - RCB - ST | 1 | 2026-03-01 | 2026-03-04 |  |  | FALSE | yes
| JD3RZ09L18SS15718 | Trench excavation for GRP Pipe Line 200 mm - depth from 0.00 to 1.50 - B5.33 31 00.03 - Z09 - L - 18 - SS | 1 | 2026-03-24 | 2026-03-29 |  |  | FALSE | yes
| JD3RZ09L18SS15719 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - depth from 0.00 to 1.50 - B5.33 31 00.03 - Z09 - L - 18 - | 1 | 2026-03-30 | 2026-04-04 |  |  | FALSE | yes
| JD3RZ09L18SS15720 | Installing for GRP Pipe Line 200 mm - depth from 0.00 to 1.50 - B5.33 31 00.03 - Z09 - L - 18 - SS | 1 | 2026-04-05 | 2026-04-09 |  |  | FALSE | yes
| JD3RZ09L18SS15721 | Primary Test for GRP Pipe Line 200 mm - depth from 0.00 to 1.50 - B5.33 31 00.03 - Z09 - L - 18 - SS | 1 | 2026-04-11 | 2026-04-15 |  |  | FALSE | yes
| JD3RZ09L18SS15722 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - depth from 0.00 to 1.50 - B5.33 31 00.03 - Z09 - L - 18 - | 1 | 2026-04-16 | 2026-04-23 |  |  | FALSE | yes
| JD3RZ09L18SS15723 | Trench excavation for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z09 - L - 18 - SS | 1 | 2026-03-30 | 2026-04-07 |  |  | FALSE | yes
| JD3RZ09L18SS15724 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z09 - L - 18 - | 1 | 2026-04-08 | 2026-04-16 |  |  | FALSE | yes
| JD3RZ09L18SS15725 | Installing for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z09 - L - 18 - SS | 1 | 2026-04-18 | 2026-04-28 |  |  | FALSE | yes
| JD3RZ09L18SS15726 | Primary Test for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z09 - L - 18 - SS | 1 | 2026-04-29 | 2026-05-07 |  |  | FALSE | yes
| JD3RZ09L18SS15727 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z09 - L - 18 - | 1 | 2026-05-09 | 2026-05-21 |  |  | FALSE | yes
| JD3RZ09L18SS15728 | Trench excavation for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - Z09 - L - 18 - SS | 1 | 2026-04-08 | 2026-04-12 |  |  | FALSE | yes
| JD3RZ09L18SS15729 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - Z09 - L - 18 - | 1 | 2026-04-13 | 2026-04-16 |  |  | FALSE | yes
| JD3RZ09L18SS15730 | Installing for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - Z09 - L - 18 - SS | 1 | 2026-04-18 | 2026-04-21 |  |  | FALSE | yes
| JD3RZ09L18SS15731 | Primary Test for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - Z09 - L - 18 - SS | 1 | 2026-04-22 | 2026-04-26 |  |  | FALSE | yes
| JD3RZ09L18SS15732 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - Z09 - L - 18 - | 1 | 2026-04-27 | 2026-05-02 |  |  | FALSE | yes
| JD3RZ09L18SS15753 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 0.00 to 1.50 - B5.33 05 13.01 - Z09 - L - 18 - SS | 1 | 2026-04-13 | 2026-04-14 |  |  | FALSE | yes
| JD3RZ09L18SS15754 | Installation of Base Works for Manholes 1200 mm - Depth from 0.00 to 1.50 - B5.33 05 13.01 - Z09 - L - 18 - SS | 1 | 2026-04-15 | 2026-04-16 |  |  | FALSE | yes
| JD3RZ09L18SS15755 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 0.00 to 1.50 - B5.33 05 13.01 - Z09 | 1 | 2026-04-18 | 2026-04-19 |  |  | FALSE | yes
| JD3RZ09L18SS15756 | Backfilling Works for Manholes 1200 mm - Depth from 0.00 to 1.50 - B5.33 05 13.01 - Z09 - L - 18 - SS | 1 | 2026-04-20 | 2026-04-21 |  |  | FALSE | yes
| JD3RZ09L18SS15757 | Finishing, Benching Works for Manholes 1200 mm - Depth from 0.00 to 1.50 - B5.33 05 13.01 - Z09 - L - 18 - SS | 1 | 2026-04-22 | 2026-04-23 |  |  | FALSE | yes
| JD3RZ09L18SS15765 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z09 - L - 18 - SS | 1 | 2026-04-15 | 2026-04-18 |  |  | FALSE | yes
| JD3RZ09L18SS15766 | Installation of Base Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z09 - L - 18 - SS | 1 | 2026-04-19 | 2026-04-26 |  |  | FALSE | yes
| JD3RZ09L18SS15767 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z09 | 1 | 2026-04-27 | 2026-05-04 |  |  | FALSE | yes
| JD3RZ09L18SS15768 | Backfilling Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z09 - L - 18 - SS | 1 | 2026-05-05 | 2026-05-09 |  |  | FALSE | yes
| JD3RZ09L18SS15769 | Finishing, Benching Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z09 - L - 18 - SS | 1 | 2026-05-10 | 2026-05-13 |  |  | FALSE | yes
| JD3RZ09L18SS15777 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z09 - L - 18 - SS | 1 | 2026-04-19 | 2026-04-20 |  |  | FALSE | yes
| JD3RZ09L18SS15778 | Installation of Base Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z09 - L - 18 - SS | 1 | 2026-04-21 | 2026-04-25 |  |  | FALSE | yes
| JD3RZ09L18SS15779 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z09 | 1 | 2026-04-26 | 2026-04-29 |  |  | FALSE | yes
| JD3RZ09L18SS15780 | Backfilling Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z09 - L - 18 - SS | 1 | 2026-04-30 | 2026-05-02 |  |  | FALSE | yes
| JD3RZ09L18SS15781 | Finishing, Benching Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z09 - L - 18 - SS | 1 | 2026-05-03 | 2026-05-04 |  |  | FALSE | yes
| JD3RZ09L18SS15782 | Excavation and PC Blinding Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.06 - Z09 - L - 18 | 1 | 2026-04-21 | 2026-04-22 |  |  | FALSE | yes
| JD3RZ09L18SS15783 | Installation of Base Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.06 - Z09 - L - 18 - SS | 1 | 2026-04-23 | 2026-04-25 |  |  | FALSE | yes
| JD3RZ09L18SS15784 | Installation of Manhole Ring and Cover Slab Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13. | 1 | 2026-04-26 | 2026-04-27 |  |  | FALSE | yes
| JD3RZ09L18SS15785 | Installation of fitting Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.06 - Z09 - L - 18 - | 1 | 2026-04-28 | 2026-04-29 |  |  | FALSE | yes
| JD3RZ09L18SS15786 | Concrete Encasement Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.06 - Z09 - L - 18 - SS | 1 | 2026-04-30 | 2026-05-02 |  |  | FALSE | yes
| JD3RZ09L18SS15787 | Backfilling Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.06 - Z09 - L - 18 - SS | 1 | 2026-05-03 | 2026-05-04 |  |  | FALSE | yes
| JD3RZ09L18SS15788 | Finishing, Benching Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.06 - Z09 - L - 18 - SS | 1 | 2026-05-05 | 2026-05-06 |  |  | FALSE | yes
| JD3RZ09L18SUR01 | Surveying Works L - 18 | 1 |  |  |  |  | yes | FALSE
| JD3RZ09L19SS37821 | Trench excavation for GRP Pipe Line 200 mm - depth from 0.00 to 1.50 - B5.33 31 00.03 - Z09 - L - 19 - SS | 1 | 2026-05-23 | 2026-05-24 |  |  | FALSE | yes
| JD3RZ09L19SS37822 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - depth from 0.00 to 1.50 - B5.33 31 00.03 - Z09 - L - 19 - | 1 | 2026-05-25 | 2026-05-26 |  |  | FALSE | yes
| JD3RZ09L19SS37823 | Installing for GRP Pipe Line 200 mm - depth from 0.00 to 1.50 - B5.33 31 00.03 - Z09 - L - 19 - SS | 1 | 2026-05-27 | 2026-05-28 |  |  | FALSE | yes
| JD3RZ09L19SS37824 | Primary Test for GRP Pipe Line 200 mm - depth from 0.00 to 1.50 - B5.33 31 00.03 - Z09 - L - 19 - SS | 1 | 2026-05-30 | 2026-05-31 |  |  | FALSE | yes
| JD3RZ09L19SS37825 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - depth from 0.00 to 1.50 - B5.33 31 00.03 - Z09 - L - 19 - | 1 | 2026-06-01 | 2026-06-02 |  |  | FALSE | yes
| JD3RZ09L19SS37826 | Trench excavation for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z09 - L - 19 - SS | 1 | 2026-05-25 | 2026-06-01 |  |  | FALSE | yes
| JD3RZ09L19SS37827 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z09 - L - 19 - | 1 | 2026-06-02 | 2026-06-09 |  |  | FALSE | yes
| JD3RZ09L19SS37828 | Installing for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z09 - L - 19 - SS | 1 | 2026-06-10 | 2026-06-18 |  |  | FALSE | yes
| JD3RZ09L19SS37829 | Primary Test for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z09 - L - 19 - SS | 1 | 2026-06-20 | 2026-06-27 |  |  | FALSE | yes
| JD3RZ09L19SS37830 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z09 - L - 19 - | 1 | 2026-06-28 | 2026-07-08 |  |  | FALSE | yes
| JD3RZ09L19SS37831 | Trench excavation for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - Z09 - L - 19 - SS | 1 | 2026-06-02 | 2026-06-04 |  |  | FALSE | yes
| JD3RZ09L19SS37832 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - Z09 - L - 19 - | 1 | 2026-06-06 | 2026-06-08 |  |  | FALSE | yes
| JD3RZ09L19SS37833 | Installing for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - Z09 - L - 19 - SS | 1 | 2026-06-09 | 2026-06-13 |  |  | FALSE | yes
| JD3RZ09L19SS37834 | Primary Test for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - Z09 - L - 19 - SS | 1 | 2026-06-14 | 2026-06-16 |  |  | FALSE | yes
| JD3RZ09L19SS37835 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - Z09 - L - 19 - | 1 | 2026-06-17 | 2026-06-22 |  |  | FALSE | yes
| JD3RZ09L19SS37846 | Trench excavation for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50 - B5.33 31 00.12 - Z09 - L - 19 - SS | 1 | 2026-06-06 | 2026-06-07 |  |  | FALSE | yes
| JD3RZ09L19SS37847 | Soil Replacement and Bedding Works for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50 - B5.33 31 00.12 - Z09 - L - 19 - | 1 | 2026-06-08 | 2026-06-09 |  |  | FALSE | yes
| JD3RZ09L19SS37848 | Installing for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50 - B5.33 31 00.12 - Z09 - L - 19 - SS | 1 | 2026-06-10 | 2026-06-11 |  |  | FALSE | yes
| JD3RZ09L19SS37849 | Primary Test for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50 - B5.33 31 00.12 - Z09 - L - 19 - SS | 1 | 2026-06-13 | 2026-06-14 |  |  | FALSE | yes
| JD3RZ09L19SS37850 | Backfilling and warning tabe Works for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50 - B5.33 31 00.12 - Z09 - L - 19 - | 1 | 2026-06-15 | 2026-06-16 |  |  | FALSE | yes
| JD3RZ09L19SS37856 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 0.00 to 1.50 - B5.33 05 13.01 - Z09 - L - 19 - SS | 1 | 2026-06-08 | 2026-06-09 |  |  | FALSE | yes
| JD3RZ09L19SS37857 | Installation of Base Works for Manholes 1200 mm - Depth from 0.00 to 1.50 - B5.33 05 13.01 - Z09 - L - 19 - SS | 1 | 2026-06-10 | 2026-06-11 |  |  | FALSE | yes
| JD3RZ09L19SS37858 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 0.00 to 1.50 - B5.33 05 13.01 - Z09 | 1 | 2026-06-13 | 2026-06-14 |  |  | FALSE | yes
| JD3RZ09L19SS37859 | Backfilling Works for Manholes 1200 mm - Depth from 0.00 to 1.50 - B5.33 05 13.01 - Z09 - L - 19 - SS | 1 | 2026-06-15 | 2026-06-16 |  |  | FALSE | yes
| JD3RZ09L19SS37860 | Finishing, Benching Works for Manholes 1200 mm - Depth from 0.00 to 1.50 - B5.33 05 13.01 - Z09 - L - 19 - SS | 1 | 2026-06-17 | 2026-06-18 |  |  | FALSE | yes
| JD3RZ09L19SS37868 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z09 - L - 19 - SS | 1 | 2026-06-10 | 2026-06-11 |  |  | FALSE | yes
| JD3RZ09L19SS37869 | Installation of Base Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z09 - L - 19 - SS | 1 | 2026-06-13 | 2026-06-17 |  |  | FALSE | yes
| JD3RZ09L19SS37870 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z09 | 1 | 2026-06-18 | 2026-06-23 |  |  | FALSE | yes
| JD3RZ09L19SS37871 | Backfilling Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z09 - L - 19 - SS | 1 | 2026-06-24 | 2026-06-27 |  |  | FALSE | yes
| JD3RZ09L19SS37872 | Finishing, Benching Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z09 - L - 19 - SS | 1 | 2026-06-28 | 2026-06-30 |  |  | FALSE | yes
| JD3RZ09L19SS37880 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z09 - L - 19 - SS | 1 | 2026-06-13 | 2026-06-14 |  |  | FALSE | yes
| JD3RZ09L19SS37881 | Installation of Base Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z09 - L - 19 - SS | 1 | 2026-06-15 | 2026-06-16 |  |  | FALSE | yes
| JD3RZ09L19SS37882 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z09 | 1 | 2026-06-17 | 2026-06-18 |  |  | FALSE | yes
| JD3RZ09L19SS37883 | Backfilling Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z09 - L - 19 - SS | 1 | 2026-06-20 | 2026-06-21 |  |  | FALSE | yes
| JD3RZ09L19SS37884 | Finishing, Benching Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z09 - L - 19 - SS | 1 | 2026-06-22 | 2026-06-23 |  |  | FALSE | yes
| JD3RZ10L20SS38534 | Trench excavation for GRP Pipe Line 200 mm - depth from 0.00 to 1.50 - B5.33 31 00.03 - Z10 - L - 20 - SS | 1 | 2026-03-21 | 2026-03-22 |  |  | FALSE | yes
| JD3RZ10L20SS38535 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - depth from 0.00 to 1.50 - B5.33 31 00.03 - Z10 - L - 20 - | 1 | 2026-03-23 | 2026-03-24 |  |  | FALSE | yes
| JD3RZ10L20SS38536 | Installing for GRP Pipe Line 200 mm - depth from 0.00 to 1.50 - B5.33 31 00.03 - Z10 - L - 20 - SS | 1 | 2026-03-25 | 2026-03-26 |  |  | FALSE | yes
| JD3RZ10L20SS38537 | Primary Test for GRP Pipe Line 200 mm - depth from 0.00 to 1.50 - B5.33 31 00.03 - Z10 - L - 20 - SS | 1 | 2026-03-28 | 2026-03-29 |  |  | FALSE | yes
| JD3RZ10L20SS38538 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - depth from 0.00 to 1.50 - B5.33 31 00.03 - Z10 - L - 20 - | 1 | 2026-03-30 | 2026-03-31 |  |  | FALSE | yes
| JD3RZ10L20SS38539 | Trench excavation for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z10 - L - 20 - SS | 1 | 2026-03-23 | 2026-03-29 |  |  | FALSE | yes
| JD3RZ10L20SS38540 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z10 - L - 20 - | 1 | 2026-03-30 | 2026-04-05 |  |  | FALSE | yes
| JD3RZ10L20SS38541 | Installing for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z10 - L - 20 - SS | 1 | 2026-04-06 | 2026-04-13 |  |  | FALSE | yes
| JD3RZ10L20SS38542 | Primary Test for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z10 - L - 20 - SS | 1 | 2026-04-14 | 2026-04-20 |  |  | FALSE | yes
| JD3RZ10L20SS38543 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z10 - L - 20 - | 1 | 2026-04-21 | 2026-04-30 |  |  | FALSE | yes
| JD3RZ10L20SS38569 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 0.00 to 1.50 - B5.33 05 13.01 - Z10 - L - 20 - SS | 1 | 2026-03-30 | 2026-03-31 |  |  | FALSE | yes
| JD3RZ10L20SS38570 | Installation of Base Works for Manholes 1200 mm - Depth from 0.00 to 1.50 - B5.33 05 13.01 - Z10 - L - 20 - SS | 1 | 2026-04-01 | 2026-04-02 |  |  | FALSE | yes
| JD3RZ10L20SS38571 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 0.00 to 1.50 - B5.33 05 13.01 - Z10 | 1 | 2026-04-04 | 2026-04-05 |  |  | FALSE | yes
| JD3RZ10L20SS38572 | Backfilling Works for Manholes 1200 mm - Depth from 0.00 to 1.50 - B5.33 05 13.01 - Z10 - L - 20 - SS | 1 | 2026-04-06 | 2026-04-07 |  |  | FALSE | yes
| JD3RZ10L20SS38573 | Finishing, Benching Works for Manholes 1200 mm - Depth from 0.00 to 1.50 - B5.33 05 13.01 - Z10 - L - 20 - SS | 1 | 2026-04-08 | 2026-04-09 |  |  | FALSE | yes
| JD3RZ10L20SS38581 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z10 - L - 20 - SS | 1 | 2026-04-01 | 2026-04-02 |  |  | FALSE | yes
| JD3RZ10L20SS38582 | Installation of Base Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z10 - L - 20 - SS | 1 | 2026-04-04 | 2026-04-07 |  |  | FALSE | yes
| JD3RZ10L20SS38583 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z10 | 1 | 2026-04-08 | 2026-04-12 |  |  | FALSE | yes
| JD3RZ10L20SS38584 | Backfilling Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z10 - L - 20 - SS | 1 | 2026-04-13 | 2026-04-15 |  |  | FALSE | yes
| JD3RZ10L20SS38585 | Finishing, Benching Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z10 - L - 20 - SS | 1 | 2026-04-16 | 2026-04-18 |  |  | FALSE | yes
| JD3RZ10L23SS40678 | Trench excavation for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z10 - L - 23 - SS | 1 | 2026-03-21 | 2026-03-23 |  |  | FALSE | yes
| JD3RZ10L23SS40679 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z10 - L - 23 - | 1 | 2026-03-24 | 2026-03-26 |  |  | FALSE | yes
| JD3RZ10L23SS40680 | Installing for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z10 - L - 23 - SS | 1 | 2026-03-28 | 2026-03-30 |  |  | FALSE | yes
| JD3RZ10L23SS40681 | Primary Test for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z10 - L - 23 - SS | 1 | 2026-03-31 | 2026-04-02 |  |  | FALSE | yes
| JD3RZ10L23SS40682 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z10 - L - 23 - | 1 | 2026-04-04 | 2026-04-07 |  |  | FALSE | yes
| JD3RZ10L23SS40683 | Trench excavation for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - Z10 - L - 23 - SS | 1 | 2026-04-04 | 2026-04-13 |  |  | FALSE | yes
| JD3RZ10L23SS40684 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - Z10 - L - 23 - | 1 | 2026-04-14 | 2026-04-23 |  |  | FALSE | yes
| JD3RZ10L23SS40685 | Installing for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - Z10 - L - 23 - SS | 1 | 2026-04-25 | 2026-05-06 |  |  | FALSE | yes
| JD3RZ10L23SS40686 | Primary Test for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - Z10 - L - 23 - SS | 1 | 2026-05-07 | 2026-05-17 |  |  | FALSE | yes
| JD3RZ10L23SS40687 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - Z10 - L - 23 - | 1 | 2026-05-18 | 2026-06-02 |  |  | FALSE | yes
| JD3RZ10L23SS40720 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z10 - L - 23 - SS | 1 | 2026-04-14 | 2026-04-15 |  |  | FALSE | yes
| JD3RZ10L23SS40721 | Installation of Base Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z10 - L - 23 - SS | 1 | 2026-04-16 | 2026-04-19 |  |  | FALSE | yes
| JD3RZ10L23SS40722 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z10 | 1 | 2026-04-20 | 2026-04-22 |  |  | FALSE | yes
| JD3RZ10L23SS40723 | Backfilling Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z10 - L - 23 - SS | 1 | 2026-04-23 | 2026-04-25 |  |  | FALSE | yes
| JD3RZ10L23SS40724 | Finishing, Benching Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z10 - L - 23 - SS | 1 | 2026-04-26 | 2026-04-27 |  |  | FALSE | yes
| JD3RZ10L23SS40732 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z10 - L - 23 - SS | 1 | 2026-04-16 | 2026-04-19 |  |  | FALSE | yes
| JD3RZ10L23SS40733 | Installation of Base Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z10 - L - 23 - SS | 1 | 2026-04-20 | 2026-04-26 |  |  | FALSE | yes
| JD3RZ10L23SS40734 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z10 | 1 | 2026-04-27 | 2026-05-03 |  |  | FALSE | yes
| JD3RZ10L23SS40735 | Backfilling Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z10 - L - 23 - SS | 1 | 2026-05-04 | 2026-05-06 |  |  | FALSE | yes
| JD3RZ10L23SS40736 | Finishing, Benching Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z10 - L - 23 - SS | 1 | 2026-05-07 | 2026-05-10 |  |  | FALSE | yes
| JD3RZ10L24SS41391 | Trench excavation for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z10 - L - 24 - SS | 1 | 2026-05-02 | 2026-05-04 | 2025-10-25 |  | FALSE | yes
| JD3RZ10L24SS41392 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z10 - L - 24 - | 1 | 2026-05-05 | 2026-05-07 | 2025-10-27 |  | FALSE | yes
| JD3RZ10L24SS41393 | Installing for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z10 - L - 24 - SS | 1 | 2026-05-09 | 2026-05-12 | 2025-10-30 |  | FALSE | yes
| JD3RZ10L24SS41394 | Primary Test for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z10 - L - 24 - SS | 1 | 2026-05-13 | 2026-05-16 |  |  | FALSE | yes
| JD3RZ10L24SS41395 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z10 - L - 24 - | 1 | 2026-05-17 | 2026-05-20 |  |  | FALSE | yes
| JD3RZ10L24SS41424 | Backfilling Works for Manholes 1200 mm - Depth from 0.00 to 1.50 - B5.33 05 13.01 - Z10 - L - 24 - SS | 1 | 2026-05-12 | 2026-05-13 |  |  | FALSE | yes
| JD3RZ10L24SS41425 | Finishing, Benching Works for Manholes 1200 mm - Depth from 0.00 to 1.50 - B5.33 05 13.01 - Z10 - L - 24 - SS | 1 | 2026-05-14 | 2026-05-16 |  |  | FALSE | yes
| JD3RZ10L24SS41433 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z10 - L - 24 - SS | 1 | 2026-05-07 | 2026-05-09 |  |  | FALSE | yes
| JD3RZ10L24SS41434 | Installation of Base Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z10 - L - 24 - SS | 1 | 2026-05-10 | 2026-05-11 |  |  | FALSE | yes
| JD3RZ10L24SS41435 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z10 | 1 | 2026-05-12 | 2026-05-13 |  |  | FALSE | yes
| JD3RZ10L24SS41436 | Backfilling Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z10 - L - 24 - SS | 1 | 2026-05-14 | 2026-05-16 |  |  | FALSE | yes
| JD3RZ10L24SS41437 | Finishing, Benching Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z10 - L - 24 - SS | 1 | 2026-05-17 | 2026-05-18 |  |  | FALSE | yes
| JD3RZ10L25SS42104 | Trench excavation for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z10 - L - 25 - SS | 1 | 2026-05-21 | 2026-05-26 |  |  | FALSE | yes
| JD3RZ10L25SS42105 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z10 - L - 25 - | 1 | 2026-05-27 | 2026-06-01 |  |  | FALSE | yes
| JD3RZ10L25SS42106 | Installing for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z10 - L - 25 - SS | 1 | 2026-06-02 | 2026-06-08 |  |  | FALSE | yes
| JD3RZ10L25SS42107 | Primary Test for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z10 - L - 25 - SS | 1 | 2026-06-09 | 2026-06-14 |  |  | FALSE | yes
| JD3RZ10L25SS42108 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z10 - L - 25 - | 1 | 2026-06-15 | 2026-06-23 |  |  | FALSE | yes
| JD3RZ10L25SS42109 | Trench excavation for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - Z10 - L - 25 - SS | 1 | 2026-05-27 | 2026-06-01 |  |  | FALSE | yes
| JD3RZ10L25SS42110 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - Z10 - L - 25 - | 1 | 2026-06-02 | 2026-06-07 |  |  | FALSE | yes
| JD3RZ10L25SS42111 | Installing for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - Z10 - L - 25 - SS | 1 | 2026-06-08 | 2026-06-14 |  |  | FALSE | yes
| JD3RZ10L25SS42112 | Primary Test for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - Z10 - L - 25 - SS | 1 | 2026-06-15 | 2026-06-20 |  |  | FALSE | yes
| JD3RZ10L25SS42113 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - Z10 - L - 25 - | 1 | 2026-06-21 | 2026-06-28 |  |  | FALSE | yes
| JD3RZ10L25SS42146 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z10 - L - 25 - SS | 1 | 2026-06-02 | 2026-06-03 |  |  | FALSE | yes
| JD3RZ10L25SS42147 | Installation of Base Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z10 - L - 25 - SS | 1 | 2026-06-04 | 2026-06-08 |  |  | FALSE | yes
| JD3RZ10L25SS42148 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z10 | 1 | 2026-06-09 | 2026-06-13 |  |  | FALSE | yes
| JD3RZ10L25SS42149 | Backfilling Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z10 - L - 25 - SS | 1 | 2026-06-14 | 2026-06-16 |  |  | FALSE | yes
| JD3RZ10L25SS42150 | Finishing, Benching Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z10 - L - 25 - SS | 1 | 2026-06-17 | 2026-06-18 |  |  | FALSE | yes
| JD3RZ10L25SS42158 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z10 - L - 25 - SS | 1 | 2026-06-04 | 2026-06-06 |  |  | FALSE | yes
| JD3RZ10L25SS42159 | Installation of Base Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z10 - L - 25 - SS | 1 | 2026-06-07 | 2026-06-08 |  |  | FALSE | yes
| JD3RZ10L25SS42160 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z10 | 1 | 2026-06-09 | 2026-06-10 |  |  | FALSE | yes
| JD3RZ10L25SS42161 | Backfilling Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z10 - L - 25 - SS | 1 | 2026-06-11 | 2026-06-13 |  |  | FALSE | yes
| JD3RZ10L25SS42162 | Finishing, Benching Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z10 - L - 25 - SS | 1 | 2026-06-14 | 2026-06-15 |  |  | FALSE | yes
| JD3RZ10L26SS42817 | Trench excavation for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z10 - L - 26 - SS | 1 | 2026-03-21 | 2026-03-22 |  |  | FALSE | yes
| JD3RZ10L26SS42818 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z10 - L - 26 - | 1 | 2026-03-23 | 2026-03-24 |  |  | FALSE | yes
| JD3RZ10L26SS42819 | Installing for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z10 - L - 26 - SS | 1 | 2026-03-25 | 2026-03-26 |  |  | FALSE | yes
| JD3RZ10L26SS42820 | Primary Test for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z10 - L - 26 - SS | 1 | 2026-03-28 | 2026-03-29 |  |  | FALSE | yes
| JD3RZ10L26SS42821 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50 - B5.33 31 00.04 - Z10 - L - 26 - | 1 | 2026-03-30 | 2026-04-01 |  |  | FALSE | yes
| JD3RZ10L26SS42822 | Trench excavation for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - Z10 - L - 26 - SS | 1 | 2026-03-23 | 2026-03-26 |  |  | FALSE | yes
| JD3RZ10L26SS42823 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - Z10 - L - 26 - | 1 | 2026-03-28 | 2026-03-31 |  |  | FALSE | yes
| JD3RZ10L26SS42824 | Installing for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - Z10 - L - 26 - SS | 1 | 2026-04-01 | 2026-04-06 |  |  | FALSE | yes
| JD3RZ10L26SS42825 | Primary Test for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - Z10 - L - 26 - SS | 1 | 2026-04-07 | 2026-04-11 |  |  | FALSE | yes
| JD3RZ10L26SS42826 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50 - B5.33 31 00.05 - Z10 - L - 26 - | 1 | 2026-04-12 | 2026-04-18 |  |  | FALSE | yes
| JD3RZ10L26SS42832 | Trench excavation for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50 - B5.33 31 00.11 - Z10 - L - 26 - SS | 1 | 2026-04-19 | 2026-04-20 |  |  | FALSE | yes
| JD3RZ10L26SS42833 | Soil Replacement and Bedding Works for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50 - B5.33 31 00.11 - Z10 - L - 26 - | 1 | 2026-04-21 | 2026-04-22 |  |  | FALSE | yes
| JD3RZ10L26SS42834 | Installing for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50 - B5.33 31 00.11 - Z10 - L - 26 - SS | 1 | 2026-04-23 | 2026-04-25 |  |  | FALSE | yes
| JD3RZ10L26SS42835 | Primary Test for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50 - B5.33 31 00.11 - Z10 - L - 26 - SS | 1 | 2026-04-26 | 2026-04-27 |  |  | FALSE | yes
| JD3RZ10L26SS42836 | Backfilling and warning tabe Works for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50 - B5.33 31 00.11 - Z10 - L - 26 - | 1 | 2026-04-28 | 2026-04-29 |  |  | FALSE | yes
| JD3RZ10L26SS42837 | Trench excavation for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50 - B5.33 31 00.12 - Z10 - L - 26 - SS | 1 | 2026-04-30 | 2026-05-06 |  |  | FALSE | yes
| JD3RZ10L26SS42838 | Soil Replacement and Bedding Works for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50 - B5.33 31 00.12 - Z10 - L - 26 - | 1 | 2026-05-07 | 2026-05-13 |  |  | FALSE | yes
| JD3RZ10L26SS42839 | Installing for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50 - B5.33 31 00.12 - Z10 - L - 26 - SS | 1 | 2026-05-14 | 2026-05-21 |  |  | FALSE | yes
| JD3RZ10L26SS42840 | Primary Test for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50 - B5.33 31 00.12 - Z10 - L - 26 - SS | 1 | 2026-05-23 | 2026-05-28 |  |  | FALSE | yes
| JD3RZ10L26SS42841 | Backfilling and warning tabe Works for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50 - B5.33 31 00.12 - Z10 - L - 26 - | 1 | 2026-05-30 | 2026-06-08 |  |  | FALSE | yes
| JD3RZ10L26SS42859 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z10 - L - 26 - SS | 1 | 2026-05-07 | 2026-05-09 |  |  | FALSE | yes
| JD3RZ10L26SS42860 | Installation of Base Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z10 - L - 26 - SS | 1 | 2026-05-10 | 2026-05-11 |  |  | FALSE | yes
| JD3RZ10L26SS42861 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z10 | 1 | 2026-05-12 | 2026-05-13 |  |  | FALSE | yes
| JD3RZ10L26SS42862 | Backfilling Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z10 - L - 26 - SS | 1 | 2026-05-14 | 2026-05-16 |  |  | FALSE | yes
| JD3RZ10L26SS42863 | Finishing, Benching Works for Manholes 1200 mm - Depth from 1.51 to 2.50 - B5.33 05 13.03 - Z10 - L - 26 - SS | 1 | 2026-05-17 | 2026-05-18 |  |  | FALSE | yes
| JD3RZ10L26SS42871 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z10 - L - 26 - SS | 1 | 2026-05-10 | 2026-05-12 |  |  | FALSE | yes
| JD3RZ10L26SS42872 | Installation of Base Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z10 - L - 26 - SS | 1 | 2026-05-13 | 2026-05-21 |  |  | FALSE | yes
| JD3RZ10L26SS42873 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z10 | 1 | 2026-05-23 | 2026-05-31 |  |  | FALSE | yes
| JD3RZ10L26SS42874 | Backfilling Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z10 - L - 26 - SS | 1 | 2026-06-01 | 2026-06-04 |  |  | FALSE | yes
| JD3RZ10L26SS42875 | Finishing, Benching Works for Manholes 1200 mm - Depth from 2.51 to 3.50 - B5.33 05 13.05 - Z10 - L - 26 - SS | 1 | 2026-06-06 | 2026-06-08 |  |  | FALSE | yes
| JD3RZ11RCBST22104 | Excavation Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z11 - RCB - ST | 1 | 2026-02-15 | 2026-02-16 |  |  | FALSE | yes
| JD3RZ11RCBST22105 | Soil Replacement and Bedding Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z11 - RCB | 1 | 2026-02-17 | 2026-02-18 |  |  | FALSE | yes
| JD3RZ11RCBST22106 | Installing for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z11 - RCB - ST | 1 | 2026-02-19 | 2026-02-21 |  |  | FALSE | yes
| JD3RZ11RCBST22107 | Primary Test for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z11 - RCB - ST | 1 | 2026-02-22 | 2026-02-23 |  |  | FALSE | yes
| JD3RZ11RCBST22108 | Backfilling Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z11 - RCB - ST | 1 | 2026-02-24 | 2026-02-25 |  |  | FALSE | yes
| JD3RZ11RCBST22114 | Excavation Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z11 - RCB - ST | 1 | 2026-02-17 | 2026-02-18 |  |  | FALSE | yes
| JD3RZ11RCBST22115 | Soil Replacement and Bedding Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z11 - RCB - | 1 | 2026-02-19 | 2026-02-21 |  |  | FALSE | yes
| JD3RZ11RCBST22116 | Installing for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z11 - RCB - ST | 1 | 2026-02-22 | 2026-02-23 |  |  | FALSE | yes
| JD3RZ11RCBST22117 | Primary Test for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z11 - RCB - ST | 1 | 2026-02-24 | 2026-02-25 |  |  | FALSE | yes
| JD3RZ11RCBST22118 | Backfilling Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z11 - RCB - ST | 1 | 2026-02-26 | 2026-02-28 |  |  | FALSE | yes
| JD3RZ11RCBST22322 | EXCAVATION Works for Catchbasine - B6.33 05 39.09 - single - Z11 - RCB - ST | 1 | 2026-02-19 | 2026-02-21 |  |  | FALSE | yes
| JD3RZ11RCBST22323 | Catchbasine Installation Works for Catchbasine - B6.33 05 39.09 - single - Z11 - RCB - ST | 1 | 2026-02-22 | 2026-02-23 |  |  | FALSE | yes
| JD3RZ11RCBST22324 | FINISHING Works for Catchbasine - B6.33 05 39.09 - single - Z11 - RCB - ST | 1 | 2026-02-24 | 2026-02-25 |  |  | FALSE | yes
| JD3RZ11RCBST22325 | TESTING AND COMMITIONING RELEASED for Catchbasine - B6.33 05 39.09 - single - Z11 - RCB - ST | 1 | 2026-02-26 | 2026-02-28 |  |  | FALSE | yes
| JD3RZ11RCBST22326 | EXCAVATION Works for Catchbasine - B6.33 05 39.10 - double - Z11 - RCB - ST | 1 | 2026-02-22 | 2026-02-23 |  |  | FALSE | yes
| JD3RZ11RCBST22327 | Catchbasine Installation Works for Catchbasine - B6.33 05 39.10 - double - Z11 - RCB - ST | 1 | 2026-02-24 | 2026-02-25 |  |  | FALSE | yes
| JD3RZ11RCBST22328 | FINISHING Works for Catchbasine - B6.33 05 39.10 - double - Z11 - RCB - ST | 1 | 2026-02-26 | 2026-02-28 |  |  | FALSE | yes
| JD3RZ11RCBST22329 | TESTING AND COMMITIONING RELEASED for Catchbasine - B6.33 05 39.10 - double - Z11 - RCB - ST | 1 | 2026-03-01 | 2026-03-02 |  |  | FALSE | yes
| JD3RZ12RCBST22330 | Excavation Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z12 - RCB - ST | 1 | 2026-01-29 | 2026-01-31 |  |  | FALSE | yes
| JD3RZ12RCBST22331 | Soil Replacement and Bedding Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z12 - RCB | 1 | 2026-02-01 | 2026-02-02 |  |  | FALSE | yes
| JD3RZ12RCBST22332 | Installing for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z12 - RCB - ST | 1 | 2026-02-03 | 2026-02-04 |  |  | FALSE | yes
| JD3RZ12RCBST22333 | Primary Test for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z12 - RCB - ST | 1 | 2026-02-05 | 2026-02-07 |  |  | FALSE | yes
| JD3RZ12RCBST22334 | Backfilling Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z12 - RCB - ST | 1 | 2026-02-08 | 2026-02-10 |  |  | FALSE | yes
| JD3RZ12RCBST22340 | Excavation Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z12 - RCB - ST | 1 | 2026-02-01 | 2026-02-02 |  |  | FALSE | yes
| JD3RZ12RCBST22341 | Soil Replacement and Bedding Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z12 - RCB - | 1 | 2026-02-03 | 2026-02-04 |  |  | FALSE | yes
| JD3RZ12RCBST22342 | Installing for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z12 - RCB - ST | 1 | 2026-02-05 | 2026-02-07 |  |  | FALSE | yes
| JD3RZ12RCBST22343 | Primary Test for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z12 - RCB - ST | 1 | 2026-02-08 | 2026-02-09 |  |  | FALSE | yes
| JD3RZ12RCBST22344 | Backfilling Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z12 - RCB - ST | 1 | 2026-02-10 | 2026-02-11 |  |  | FALSE | yes
| JD3RZ12RCBST22548 | EXCAVATION Works for Catchbasine - B6.33 05 39.09 - single - Z12 - RCB - ST | 1 | 2026-02-03 | 2026-02-04 |  |  | FALSE | yes
| JD3RZ12RCBST22549 | Catchbasine Installation Works for Catchbasine - B6.33 05 39.09 - single - Z12 - RCB - ST | 1 | 2026-02-05 | 2026-02-08 |  |  | FALSE | yes
| JD3RZ12RCBST22550 | FINISHING Works for Catchbasine - B6.33 05 39.09 - single - Z12 - RCB - ST | 1 | 2026-02-09 | 2026-02-11 |  |  | FALSE | yes
| JD3RZ12RCBST22551 | TESTING AND COMMITIONING RELEASED for Catchbasine - B6.33 05 39.09 - single - Z12 - RCB - ST | 1 | 2026-02-12 | 2026-02-14 |  |  | FALSE | yes
| JD3RZ12RCBST22552 | EXCAVATION Works for Catchbasine - B6.33 05 39.10 - double - Z12 - RCB - ST | 1 | 2026-02-05 | 2026-02-07 |  |  | FALSE | yes
| JD3RZ12RCBST22553 | Catchbasine Installation Works for Catchbasine - B6.33 05 39.10 - double - Z12 - RCB - ST | 1 | 2026-02-08 | 2026-02-09 |  |  | FALSE | yes
| JD3RZ12RCBST22554 | FINISHING Works for Catchbasine - B6.33 05 39.10 - double - Z12 - RCB - ST | 1 | 2026-02-10 | 2026-02-11 |  |  | FALSE | yes
| JD3RZ12RCBST22555 | TESTING AND COMMITIONING RELEASED for Catchbasine - B6.33 05 39.10 - double - Z12 - RCB - ST | 1 | 2026-02-12 | 2026-02-14 |  |  | FALSE | yes
| JD3RZ13C10.CNST20061 | Excavation Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z13 - C10.CN - ST | 1 | 2026-02-28 | 2026-03-03 |  |  | FALSE | yes
| JD3RZ13C10.CNST20062 | Soil Replacement and Bedding Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z13 - C10. | 1 | 2026-03-04 | 2026-03-09 |  |  | FALSE | yes
| JD3RZ13C10.CNST20063 | Installing for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z13 - C10.CN - ST | 1 | 2026-03-10 | 2026-03-16 |  |  | FALSE | yes
| JD3RZ13C10.CNST20064 | Primary Test for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z13 - C10.CN - ST | 1 | 2026-03-17 | 2026-03-23 |  |  | FALSE | yes
| JD3RZ13C10.CNST20065 | Backfilling Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z13 - C10.CN - ST | 1 | 2026-03-24 | 2026-04-01 |  |  | FALSE | yes
| JD3RZ13C10.CNST200661 | Excavation Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z13 - C10.CN - ST | 1 | 2026-03-07 | 2026-03-08 | 2025-08-09 |  | FALSE | yes
| JD3RZ13C10.CNST200671 | Soil Replacement and Bedding Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z13 - C10.C | 1 | 2026-03-09 | 2026-03-10 | 2025-08-12 |  | FALSE | yes
| JD3RZ13C10.CNST200681 | Installing for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z13 - C10.CN - ST | 1 | 2026-03-11 | 2026-03-12 | 2025-08-14 |  | FALSE | yes
| JD3RZ13C10.CNST200691 | Primary Test for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z13 - C10.CN - ST | 1 | 2026-03-14 | 2026-03-15 | 2025-08-16 |  | FALSE | yes
| JD3RZ13C10.CNST200701 | Backfilling Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z13 - C10.CN - ST | 1 | 2026-03-16 | 2026-03-18 | 2025-08-19 |  | FALSE | yes
| JD3RZ13C10.CNST20076 | Excavation Works for GRP Pipe Line - B6.33 42 11.04 - 500 mm - depth from 1.51 to 2.50 m - Z13 - C10.CN - ST | 1 | 2026-03-09 | 2026-03-10 | 2025-08-12 |  | FALSE | yes
| JD3RZ13C10.CNST20077 | Soil Replacement and Bedding Works for GRP Pipe Line - B6.33 42 11.04 - 500 mm - depth from 1.51 to 2.50 m - Z13 - C10.C | 1 | 2026-03-11 | 2026-03-12 | 2025-08-14 |  | FALSE | yes
| JD3RZ13C10.CNST20078 | Installing for GRP Pipe Line - B6.33 42 11.04 - 500 mm - depth from 1.51 to 2.50 m - Z13 - C10.CN - ST | 1 | 2026-03-14 | 2026-03-15 | 2025-08-16 |  | FALSE | yes
| JD3RZ13C10.CNST20079 | Primary Test for GRP Pipe Line - B6.33 42 11.04 - 500 mm - depth from 1.51 to 2.50 m - Z13 - C10.CN - ST | 1 | 2026-03-16 | 2026-03-17 | 2025-08-19 |  | FALSE | yes
| JD3RZ13C10.CNST20080 | Backfilling Works for GRP Pipe Line - B6.33 42 11.04 - 500 mm - depth from 1.51 to 2.50 m - Z13 - C10.CN - ST | 1 | 2026-03-18 | 2026-03-19 | 2025-08-21 |  | FALSE | yes
| JD3RZ13C10.CNST20171 | Excavation Works for GRP Pipe Line - B6.33 42 11.24 - 1200 mm - depth from 2.51 to 3.50 m - Z13 - C10.CN - ST | 1 | 2026-04-23 | 2026-04-25 | 2025-08-31 |  | FALSE | yes
| JD3RZ13C10.CNST20172 | Soil Replacement and Bedding Works for GRP Pipe Line - B6.33 42 11.24 - 1200 mm - depth from 2.51 to 3.50 m - Z13 - C10. | 1 | 2026-04-26 | 2026-04-27 | 2025-09-03 |  | FALSE | yes
| JD3RZ13C10.CNST20173 | Installing for GRP Pipe Line - B6.33 42 11.24 - 1200 mm - depth from 2.51 to 3.50 m - Z13 - C10.CN - ST | 1 | 2026-04-28 | 2026-04-29 | 2025-09-09 |  | FALSE | yes
| JD3RZ13C10.CNST20174 | Primary Test for GRP Pipe Line - B6.33 42 11.24 - 1200 mm - depth from 2.51 to 3.50 m - Z13 - C10.CN - ST | 1 | 2026-04-30 | 2026-05-02 | 2025-09-15 |  | FALSE | yes
| JD3RZ13C10.CNST20175 | Backfilling Works for GRP Pipe Line - B6.33 42 11.24 - 1200 mm - depth from 2.51 to 3.50 m - Z13 - C10.CN - ST | 1 | 2026-05-03 | 2026-05-05 | 2025-09-20 |  | FALSE | yes
| JD3RZ13C10.CNST20244 | Excavation Works for Manholes - B6.33 05 39.02 - Diam 1200 depth from 1.51 to 2.50 - Z13 - C10.CN - ST | 1 | 2026-04-26 | 2026-04-27 |  |  | FALSE | yes
| JD3RZ13C10.CNST20245 | Base Plain Concrete Works for Manholes - B6.33 05 39.02 - Diam 1200 depth from 1.51 to 2.50 - Z13 - C10.CN - ST | 1 | 2026-04-28 | 2026-04-29 |  |  | FALSE | yes
| JD3RZ13C10.CNST20246 | Manhole Installation Works for Manholes - B6.33 05 39.02 - Diam 1200 depth from 1.51 to 2.50 - Z13 - C10.CN - ST | 1 | 2026-04-30 | 2026-05-02 |  |  | FALSE | yes
| JD3RZ13C10.CNST20247 | FINISHING Works and Backfilling Works for Manholes - B6.33 05 39.02 - Diam 1200 depth from 1.51 to 2.50 - Z13 - C10.CN - | 1 | 2026-05-03 | 2026-05-04 |  |  | FALSE | yes
| JD3RZ13C10.CNST20248 | TESTING AND COMMITIONING Works for Manholes - B6.33 05 39.02 - Diam 1200 depth from 1.51 to 2.50 - Z13 - C10.CN - ST | 1 | 2026-05-05 | 2026-05-06 |  |  | FALSE | yes
| JD3RZ13C10.CNST20271 | Manhole Installation Works for Manholes - B6.33 05 39.07 - Diam 2000 depth from 1.51 to 2.50 - Z13 - C10.CN - ST | 1 | 2026-05-09 | 2026-05-14 |  |  | FALSE | yes
| JD3RZ13C10.CNST20272 | FINISHING Works and Backfilling Works for Manholes - B6.33 05 39.07 - Diam 2000 depth from 1.51 to 2.50 - Z13 - C10.CN - | 1 | 2026-05-16 | 2026-05-19 |  |  | FALSE | yes
| JD3RZ13C10.CNST20273 | TESTING AND COMMITIONING Works for Manholes - B6.33 05 39.07 - Diam 2000 depth from 1.51 to 2.50 - Z13 - C10.CN - ST | 1 | 2026-05-20 | 2026-05-24 |  |  | FALSE | yes
| JD3RZ13C10.CNST20274 | Excavation Works for Manholes - B6.33 05 39.08 - Diam 2000 depth from 2.51 to 3.50 - Z13 - C10.CN - ST | 1 | 2026-05-02 | 2026-05-03 |  |  | FALSE | yes
| JD3RZ13C10.CNST20275 | Base Plain Concrete Works for Manholes - B6.33 05 39.08 - Diam 2000 depth from 2.51 to 3.50 - Z13 - C10.CN - ST | 1 | 2026-05-04 | 2026-05-07 |  |  | FALSE | yes
| JD3RZ13C10.CNST20276 | Manhole Installation Works for Manholes - B6.33 05 39.08 - Diam 2000 depth from 2.51 to 3.50 - Z13 - C10.CN - ST | 1 | 2026-05-09 | 2026-05-12 |  |  | FALSE | yes
| JD3RZ13C10.CNST20277 | FINISHING Works and Backfilling Works for Manholes - B6.33 05 39.08 - Diam 2000 depth from 2.51 to 3.50 - Z13 - C10.CN - | 1 | 2026-05-13 | 2026-05-16 |  |  | FALSE | yes
| JD3RZ13C10.CNST20278 | TESTING AND COMMITIONING Works for Manholes - B6.33 05 39.08 - Diam 2000 depth from 2.51 to 3.50 - Z13 - C10.CN - ST | 1 | 2026-05-17 | 2026-05-19 |  |  | FALSE | yes
| JD3RZ13C10.CNST20279 | EXCAVATION Works for Catchbasine - B6.33 05 39.09 - single - Z13 - C10.CN - ST | 1 | 2026-05-04 | 2026-05-06 |  |  | FALSE | yes
| JD3RZ13C10.CNST20280 | Catchbasine Installation Works for Catchbasine - B6.33 05 39.09 - single - Z13 - C10.CN - ST | 1 | 2026-05-07 | 2026-05-12 |  |  | FALSE | yes
| JD3RZ13C10.CNST20281 | FINISHING Works for Catchbasine - B6.33 05 39.09 - single - Z13 - C10.CN - ST | 1 | 2026-05-13 | 2026-05-18 |  |  | FALSE | yes
| JD3RZ13C10.CNST20282 | TESTING AND COMMITIONING RELEASED for Catchbasine - B6.33 05 39.09 - single - Z13 - C10.CN - ST | 1 | 2026-05-19 | 2026-05-21 |  |  | FALSE | yes
| JD3RZ13C10.CNST20283 | EXCAVATION Works for Catchbasine - B6.33 05 39.10 - double - Z13 - C10.CN - ST | 1 | 2026-05-07 | 2026-05-09 | 2025-10-25 |  | FALSE | yes
| JD3RZ13C10.CNST20284 | Catchbasine Installation Works for Catchbasine - B6.33 05 39.10 - double - Z13 - C10.CN - ST | 1 | 2026-05-10 | 2026-05-12 | 2025-10-26 |  | FALSE | yes
| JD3RZ13C10.CNST20285 | FINISHING Works for Catchbasine - B6.33 05 39.10 - double - Z13 - C10.CN - ST | 1 | 2026-05-13 | 2026-05-16 | 2025-10-27 |  | FALSE | yes
| JD3RZ13C10.CNST20286 | TESTING AND COMMITIONING RELEASED for Catchbasine - B6.33 05 39.10 - double - Z13 - C10.CN - ST | 1 | 2026-05-17 | 2026-05-18 | 2025-10-20 |  | FALSE | yes
| JD3RZ13C10.CNTSE20468 | Installation for butterfly valves - B4.33 14 19.04 - 400 mm. - Z13 - C10.CN - TSE | 1 | 2026-06-02 | 2026-06-03 |  |  | FALSE | yes
| JD3RZ13C10.CNTSE20469 | Testing And Commtionning for butterfly valves - B4.33 14 19.04 - 400 mm. - Z13 - C10.CN - TSE | 1 | 2026-06-04 | 2026-06-06 |  |  | FALSE | yes
| JD3RZ13C10.CNTSE20482 | Installation for Air valves - B4.33 14 19.16 - 65 mm. - on pipes with diameter 355 - 630 mm - Z13 - C10.CN - TSE | 1 | 2026-06-02 | 2026-06-03 |  |  | FALSE | yes
| JD3RZ13C10.CNTSE20483 | Testing And Commtionning for Air valves - B4.33 14 19.16 - 65 mm. - on pipes with diameter 355 - 630 mm - Z13 - C10.CN - | 1 | 2026-06-04 | 2026-06-06 |  |  | FALSE | yes
| JD3RZ13C10.CNTSE20514 | EXCAVATION and Bedding Works for Air Valve Chamber - B4.33 14 13.11 - on 355 - 630 mm - Z13 - C10.CN - TSE | 1 | 2026-05-07 | 2026-05-09 |  |  | FALSE | yes
| JD3RZ13C10.CNTSE205140 | EXCAVATION and Bedding Works for R.C Valve Chamber - B4.33 14 13.01 - 315 to 400 MM - Z13 - C10.CN - TSE | 1 | 2026-05-07 | 2026-05-09 |  |  | FALSE | yes
| JD3RZ13C10.CNTSE20515 | Plain Concrete Works for Air Valve Chamber - B4.33 14 13.11 - on 355 - 630 mm - Z13 - C10.CN - TSE | 1 | 2026-05-10 | 2026-05-11 |  |  | FALSE | yes
| JD3RZ13C10.CNTSE205150 | Plain Concrete Works for R.C Valve Chamber - B4.33 14 13.01 - 315 to 400 MM - Z13 - C10.CN - TSE | 1 | 2026-05-10 | 2026-05-11 |  |  | FALSE | yes
| JD3RZ13C10.CNTSE20516 | INSTALLATION for Air Valve Chamber - B4.33 14 13.11 - on 355 - 630 mm - Z13 - C10.CN - TSE | 1 | 2026-05-12 | 2026-05-13 |  |  | FALSE | yes
| JD3RZ13C10.CNTSE205160 | INSTALLATION for R.C Valve Chamber - B4.33 14 13.01 - 315 to 400 MM - Z13 - C10.CN - TSE | 1 | 2026-05-12 | 2026-05-13 |  |  | FALSE | yes
| JD3RZ13C10.CNTSE20517 | Backfilling Works for Air Valve Chamber - B4.33 14 13.11 - on 355 - 630 mm - Z13 - C10.CN - TSE | 1 | 2026-06-07 | 2026-06-08 |  |  | FALSE | yes
| JD3RZ13C10.CNTSE205170 | Backfilling Works for R.C Valve Chamber - B4.33 14 13.01 - 315 to 400 MM - Z13 - C10.CN - TSE | 1 | 2026-06-07 | 2026-06-08 |  |  | FALSE | yes
| JD3RZ13C10.CNWT20287 | Excavation Works for HDPE Pipes - B3.33 14 13.01 - 160 mm - depth from 0 to 1.5 m - Z13 - C10.CN - WT | 1 | 2026-05-05 | 2026-05-06 |  |  | FALSE | yes
| JD3RZ13C10.CNWT20288 | Soil Replacement and Bedding Works for HDPE Pipes - B3.33 14 13.01 - 160 mm - depth from 0 to 1.5 m - Z13 - C10.CN - WT | 1 | 2026-05-07 | 2026-05-09 |  |  | FALSE | yes
| JD3RZ13C10.CNWT20289 | Installing for HDPE Pipes - B3.33 14 13.01 - 160 mm - depth from 0 to 1.5 m - Z13 - C10.CN - WT | 1 | 2026-05-10 | 2026-05-11 |  |  | FALSE | yes
| JD3RZ13C10.CNWT20290 | Testing for HDPE Pipes - B3.33 14 13.01 - 160 mm - depth from 0 to 1.5 m - Z13 - C10.CN - WT | 1 | 2026-05-12 | 2026-05-13 |  |  | FALSE | yes
| JD3RZ13C10.CNWT20291 | Backfilling for HDPE Pipes - B3.33 14 13.01 - 160 mm - depth from 0 to 1.5 m - Z13 - C10.CN - WT | 1 | 2026-05-17 | 2026-05-18 |  |  | FALSE | yes
| JD3RZ13C10.CNWT20312 | INSTALLATION for gate valves - B3.33 14 19.01 - 150 mm - Z13 - C10.CN - WT | 1 | 2026-05-12 | 2026-05-13 |  |  | FALSE | yes
| JD3RZ13C10.CNWT20313 | TESTING AND COMMITION for gate valves - B3.33 14 19.01 - 150 mm - Z13 - C10.CN - WT | 1 | 2026-05-14 | 2026-05-16 |  |  | FALSE | yes
| JD3RZ13C10.CNWT20322 | EXCAVATION and Bedding Works for Fire Hydrant - B3.33 14 19.08 - Z13 - C10.CN - WT | 1 | 2026-06-09 | 2026-06-10 |  |  | FALSE | yes
| JD3RZ13C10.CNWT20323 | INSTALLATION for Fire Hydrant - B3.33 14 19.08 - Z13 - C10.CN - WT | 1 | 2026-06-11 | 2026-06-13 |  |  | FALSE | yes
| JD3RZ13C10.CNWT20324 | TESTING AND COMMITION for Fire Hydrant - B3.33 14 19.08 - Z13 - C10.CN - WT | 1 | 2026-06-14 | 2026-06-15 |  |  | FALSE | yes
| JD3RZ13C10.CNWT20325 | EXCAVATION and Bedding Works for R.C Valve Chamber - B3.33 14 13.011 - 315 to 400 MM - Z13 - C10.CN - WT | 1 | 2026-06-14 | 2026-06-15 |  |  | FALSE | yes
| JD3RZ13C10.CNWT203250 | INSTALLATION for Wash - Out Valve - B3.33 14 19.05 - 100 mm - Z13 - C10.CN - WT | 1 | 2026-05-12 | 2026-05-13 |  |  | FALSE | yes
| JD3RZ13C10.CNWT203251 | EXCAVATION and Bedding Works for Wash - out Valve Chamber - B3.33 14 13.06 - 110 to 400 MM - Z13 - C10.CN - WT | 1 | 2026-06-16 | 2026-06-17 |  |  | FALSE | yes
| JD3RZ13C10.CNWT20326 | Plain Concrete Works for R.C Valve Chamber - B3.33 14 13.011 - 315 to 400 MM - Z13 - C10.CN - WT | 1 | 2026-06-16 | 2026-06-17 |  |  | FALSE | yes
| JD3RZ13C10.CNWT203260 | TESTING AND COMMITION for Wash - Out Valve - B3.33 14 19.05 - 100 mm - Z13 - C10.CN - WT | 1 | 2026-05-14 | 2026-05-16 |  |  | FALSE | yes
| JD3RZ13C10.CNWT203261 | Plain Concrete Works for Wash - out Valve Chamber - B3.33 14 13.06 - 110 to 400 MM - Z13 - C10.CN - WT | 1 | 2026-06-18 | 2026-06-20 |  |  | FALSE | yes
| JD3RZ13C10.CNWT20327 | INSTALLATION for R.C Valve Chamber - B3.33 14 13.011 - 315 to 400 MM - Z13 - C10.CN - WT | 1 | 2026-06-18 | 2026-06-20 |  |  | FALSE | yes
| JD3RZ13C10.CNWT203271 | INSTALLATION for Wash - out Valve Chamber - B3.33 14 13.06 - 110 to 400 MM - Z13 - C10.CN - WT | 1 | 2026-06-21 | 2026-06-22 |  |  | FALSE | yes
| JD3RZ13C10.CNWT20328 | Backfilling Works for R.C Valve Chamber - B3.33 14 13.011 - 315 to 400 MM - Z13 - C10.CN - WT | 1 | 2026-06-21 | 2026-06-22 |  |  | FALSE | yes
| JD3RZ13C10.CNWT203281 | Backfilling Works for Wash - out Valve Chamber - B3.33 14 13.06 - 110 to 400 MM - Z13 - C10.CN - WT | 1 | 2026-06-23 | 2026-06-24 |  |  | FALSE | yes
| JD3RZ13RCBST22556.R | Excavation Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z13 - RCB - ST - Remaining | 1 | 2026-03-18 | 2026-03-19 |  |  | FALSE | yes
| JD3RZ13RCBST22557.R | Soil Replacement and Bedding Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z13 - RCB | 1 | 2026-03-21 | 2026-03-22 |  |  | FALSE | yes
| JD3RZ13RCBST22558.R | Installing for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z13 - RCB - ST - Remaining | 1 | 2026-03-23 | 2026-03-24 |  |  | FALSE | yes
| JD3RZ13RCBST22559 | Primary Test for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z13 - RCB - ST | 1 | 2026-03-25 | 2026-03-26 |  |  | FALSE | yes
| JD3RZ13RCBST22560 | Backfilling Works for UPVC Pipe Line - B6.33 14 11.01 - 300 mm - depth from 0.00 to 1.50 m - Z13 - RCB - ST | 1 | 2026-03-28 | 2026-03-29 |  |  | FALSE | yes
| JD3RZ13RCBST22566.R | Excavation Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z13 - RCB - ST - Remaining | 1 | 2026-03-04 | 2026-03-05 |  |  | FALSE | yes
| JD3RZ13RCBST22567.R | Soil Replacement and Bedding Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z13 - RCB - | 1 | 2026-03-07 | 2026-03-08 |  |  | FALSE | yes
| JD3RZ13RCBST22568.R | Installing for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z13 - RCB - ST - Remaining | 1 | 2026-03-09 | 2026-03-10 |  |  | FALSE | yes
| JD3RZ13RCBST22569 | Primary Test for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z13 - RCB - ST | 1 | 2026-03-11 | 2026-03-12 |  |  | FALSE | yes
| JD3RZ13RCBST22570 | Backfilling Works for GRP Pipe Line - B6.33 42 11.02 - 400 mm - depth from 1.51 to 2.50 m - Z13 - RCB - ST | 1 | 2026-03-14 | 2026-03-15 |  |  | FALSE | yes
| JD3RZ13RCBST22774.R | EXCAVATION Works for Catchbasine - B6.33 05 39.09 - single - Z13 - RCB - ST - Remaining | 1 | 2026-03-07 | 2026-03-08 | 2025-10-23 |  | FALSE | yes
| JD3RZ13RCBST22775.R | Catchbasine Installation Works for Catchbasine - B6.33 05 39.09 - single - Z13 - RCB - ST - Remaining | 1 | 2026-03-09 | 2026-03-10 | 2025-10-26 |  | FALSE | yes
| JD3RZ13RCBST22776.R | FINISHING Works for Catchbasine - B6.33 05 39.09 - single - Z13 - RCB - ST - Remaining | 1 | 2026-03-11 | 2026-03-12 | 2025-10-28 |  | FALSE | yes
| JD3RZ13RCBST22777 | TESTING AND COMMITIONING RELEASED for Catchbasine - B6.33 05 39.09 - single - Z13 - RCB - ST | 1 | 2026-03-14 | 2026-03-15 | 2025-10-28 |  | FALSE | yes
| JDH3-02-008RAS318 | Prepare and Submit Drawing for Genral layout - AS | 1 | 2026-05-04 | 2026-05-09 |  |  | FALSE | yes
| JDH3-02-008RAS321 | Prepare and Submit Drawing for Box Culverts - AS | 1 | 2026-05-10 | 2026-05-14 |  |  | FALSE | yes
| JDH3-02-008RAS446 | Review and Approval Drawing for Genral layout - AS | 1 | 2026-05-10 | 2026-05-16 |  |  | FALSE | yes
| JDH3-02-008RAS476 | Review and Approval Drawing for Box Culverts - AS | 1 | 2026-01-06 | 2026-01-12 |  |  | FALSE | yes
| JDH3-02-008RCCTVAS01 | Prepare and Submit Drawing for CCTV - AS | 1 |  |  |  |  | yes | FALSE
| JDH3-02-008RCCTVAS02 | Review and Approval Drawing for CCTV - AS | 1 |  |  |  |  | yes | FALSE
| JDH3-02-008RCCTVFT01 | Final Testing And Commissioning for CCTV - FT | 1 |  |  |  |  | yes | FALSE
| JDH3-02-008RELMI19 | Finish of ELECTRICAL Network - MI - EL - SL - TC | 1 |  | 2025-05-18 |  |  | yes | FALSE
| JDH3-02-008RMI102 | Complete all Works including Testing & Commissioning, Cleanup, Closeout Documentation and Ready for Initial Handover | 1 |  | 2026-07-09 |  |  | yes | FALSE
| JDH3-02-008RMI112 | Complete Demobilization | 1 |  | 2026-07-20 |  |  | yes | FALSE
| JDH3-02-008RMI42 | Complete Earthworks | 1 |  | 2026-07-05 |  |  | yes | FALSE
| JDH3-02-008RMI5 | Finishing Sewage, Storm and Electrical Networks - MI | 1 |  | 2026-07-08 |  |  | yes | FALSE
| JDH3-02-008RMI52 | Complete steel structure Erection for all blocks | 1 |  | 2026-04-05 |  |  | yes | FALSE
| JDH3-02-008RMI6 | Finishing Water Network (Potable - TSE) - MI | 1 |  | 2026-07-05 |  |  | yes | FALSE
| JDH3-02-008RMI7 | Finishing Road Kerbing and Pavement - MI | 1 |  | 2026-07-09 |  |  | yes | FALSE
| JDH3-02-008RMI72 | Complete all Civil Works | 1 |  | 2026-07-05 |  |  | yes | FALSE
| JDH3-02-008RMI8 | Project Finish - MI | 1 |  | 2026-07-28 |  |  | yes | FALSE
| JDH3-02-008RMI82 | Complete Mechanical Works | 1 |  | 2026-07-05 |  |  | yes | FALSE
| JDH3-02-008RMRAS422 | Prepare and Submit Drawing for Sewage Network for - MR - AS - SS | 1 | 2026-06-21 | 2026-06-27 |  |  | FALSE | yes
| JDH3-02-008RMRAS423 | Prepare and Submit Drawing for Storm Network - Pipes for - MR - AS - ST | 1 | 2026-06-21 | 2026-06-27 |  |  | FALSE | yes
| JDH3-02-008RMRAS425 | Prepare and Submit Drawing for Potable Water Network for - MR - AS - WT | 1 | 2026-07-11 | 2026-07-16 |  |  | FALSE | yes
| JDH3-02-008RMRAS427 | Prepare and Submit Drawing for TSE (IRRIGATION) Network for - MR - AS - TSE | 1 | 2026-07-09 | 2026-07-15 |  |  | FALSE | yes
| JDH3-02-008RMRAS430 | Prepare and Submit Drawing for Telecommunications Network for - MR - AS | 1 | 2026-07-12 | 2026-07-16 |  |  | FALSE | yes
| JDH3-02-008RMRAS557 | Review and Approval Drawing for Sewage Network for - MR - AS - SS | 1 | 2026-06-28 | 2026-07-04 |  |  | FALSE | yes
| JDH3-02-008RMRAS567 | Review and Approval Drawing for Storm Network - Pipes for - MR - AS - ST | 1 | 2026-06-28 | 2026-07-04 |  |  | FALSE | yes
| JDH3-02-008RMRAS587 | Review and Approval Drawing for Potable Water Network for - MR - AS - WT | 1 | 2026-07-05 | 2026-07-11 |  |  | FALSE | yes
| JDH3-02-008RMRAS597 | Review and Approval Drawing for TSE (IRRIGATION) Network for - MR - AS - TSE | 1 | 2026-07-05 | 2026-07-11 |  |  | FALSE | yes
| JDH3-02-008RMRAS627 | Review and Approval Drawing for Telecommunications Network for - MR - AS | 1 | 2026-07-05 | 2026-07-11 |  |  | FALSE | yes
| JDH3-02-008RMRAS637 | Review and Approval Drawing for Road Works( KERBING AND PAVEMENT ) for - MR - AS - RD | 1 | 2026-07-05 | 2026-07-11 |  |  | FALSE | yes
| JDH3-02-008RMRFT1406 | Final Testing And Commissioning for Sewage Network - FT - MR - SS | 1 | 2026-01-13 | 2026-01-17 |  |  | FALSE | yes
| JDH3-02-008RMRFT1407 | Final Testing And Commissioning for Storm Network - FT - MR - ST | 1 | 2026-06-16 | 2026-06-20 |  |  | FALSE | yes
| JDH3-02-008RMRFT1408 | Final Testing And Commissioning for Potable Water - FT - MR - WT | 1 | 2026-07-06 | 2026-07-09 |  |  | FALSE | yes
| JDH3-02-008RMRFT1409 | Final Testing And Commissioning for TSE (IRRIGATION) Network - FT - MR - TSE | 1 | 2026-07-05 | 2026-07-08 |  |  | FALSE | yes
| JDH3-02-008RMRFT1411 | Final Testing And Commissioning for Street Lighting Network - FT - MR - SL | 1 | 2026-07-09 | 2026-07-13 |  |  | FALSE | yes
| JDH3-02-008RMRFT1412 | Final Testing And Commissioning for Telecommunications Network - FT - MR - TC | 1 | 2026-07-09 | 2026-07-11 |  |  | FALSE | yes
| JDH3-02-008RMRFT1413 | Final Testing And Commissioning for Road Network - FT - MR - RD | 1 | 2026-07-09 | 2026-07-13 |  |  | FALSE | yes
| JDH3-02-008RMRFT1423 | Final Testing And Commissioning for Street Lighting Network - FT - HM - SL | 1 | 2026-04-02 | 2026-04-06 |  |  | FALSE | yes
| JDH3-02-008RMRFT1503 | Final Testing And Commissioning for Sewage Network - FT - PS - SS | 1 | 2026-03-18 | 2026-03-22 |  |  | FALSE | yes
| JDH3-02-008RMRMI28 | Finish for Main Roads - MI - MR | 1 |  | 2026-07-09 |  |  | yes | FALSE
| JDH3-02-008RPAS727 | Prepare and Submit Drawing for Storm Network - Collecting Lakes (PONDS) - ST | 1 | 2026-05-16 | 2026-05-20 |  |  | FALSE | yes
| JDH3-02-008RPAS797 | Review and Approval Drawing for Storm Network - Collecting Lakes (PONDS) - ST | 1 | 2026-05-21 | 2026-05-27 |  |  | FALSE | yes
| JDH3-02-008RRDMI25 | Finish for Road Works - RD - MI - RD | 1 |  | 2026-03-11 |  |  | yes | FALSE
| JDH3-02-008RSEPR1006 | Delivery for Precast Concrete - PR - TSE - Z05 | 1 | 2025-03-10 | 2025-03-19 |  |  | FALSE | yes
| JDH3-02-008RSEPR1008 | Delivery for Isolation Materials - PR - TSE - Z05 | 1 | 2025-04-01 | 2025-04-10 |  |  | FALSE | yes
| JDH3-02-008RSEPR1009 | Delivery for GRP pipes - PR - TSE - Z05 | 1 | 2025-05-22 | 2025-05-31 |  |  | FALSE | yes
| JDH3-02-008RSEPR1011 | Delivery for Concrete Pipes - PR - TSE - Z05 | 1 | 2025-06-13 | 2025-06-22 |  |  | FALSE | yes
| JDH3-02-008RSEPR1013 | Delivery for Metal Works (Stairs - Covers) - PR - TSE - Z05 | 1 | 2025-07-05 | 2025-07-14 |  |  | FALSE | yes
| JDH3-02-008RSEPR1042 | Delivery for Precast Concrete - PR - TSE - Z06 | 1 | 2025-04-23 | 2025-05-04 |  |  | FALSE | yes
| JDH3-02-008RSEPR1043 | Delivery for Backfilling Materials - PR - TSE - Z06 | 1 | 2025-05-05 | 2025-05-16 |  |  | FALSE | yes
| JDH3-02-008RSEPR1044 | Delivery for Isolation Materials - PR - TSE - Z06 | 1 | 2025-05-17 | 2025-05-28 |  |  | FALSE | yes
| JDH3-02-008RSEPR1045 | Delivery for GRP pipes - PR - TSE - Z06 | 1 | 2025-05-29 | 2025-06-09 |  |  | FALSE | yes
| JDH3-02-008RSEPR1047 | Delivery for Concrete Pipes - PR - TSE - Z06 | 1 | 2025-06-22 | 2025-07-03 |  |  | FALSE | yes
| JDH3-02-008RSEPR1049 | Delivery for Metal Works (Stairs - Covers) - PR - TSE - Z06 | 1 | 2025-07-16 | 2025-07-27 |  |  | FALSE | yes
| JDH3-02-008RSEPR1084 | Delivery for Concrete - PR - TSE - Z07 | 1 | 2024-09-01 | 2024-09-12 | 2025-10-30 |  | FALSE | FALSE
| JDH3-02-008RSEPR1085 | Delivery for Precast Concrete - PR - TSE - Z07 | 1 | 2024-09-13 | 2024-09-25 | 2025-11-01 |  | FALSE | FALSE
| JDH3-02-008RSEPR1086 | Delivery for Backfilling Materials - PR - TSE - Z07 | 1 | 2024-09-26 | 2024-10-07 | 2025-11-02 |  | FALSE | FALSE
| JDH3-02-008RSEPR1087 | Delivery for Isolation Materials - PR - TSE - Z07 | 1 | 2024-10-08 | 2024-10-19 | 2025-11-03 |  | FALSE | FALSE
| JDH3-02-008RSEPR1088 | Delivery for GRP pipes - PR - TSE - Z07 | 1 | 2024-10-20 | 2024-10-31 | 2025-11-04 |  | FALSE | FALSE
| JDH3-02-008RSEPR1092 | Delivery for Metal Works (Stairs - Covers) - PR - TSE - Z07 | 1 | 2024-12-07 | 2024-12-18 | 2025-11-05 |  | FALSE | FALSE
| JDH3-02-008RSEPR1147 | Delivery for Concrete - PR - TSE - Z07 - 1 | 1 | 2024-09-01 | 2024-09-12 | 2025-10-30 |  | FALSE | FALSE
| JDH3-02-008RSEPR1148 | Delivery for Precast Concrete - PR - TSE - Z07 - 1 | 1 | 2024-09-13 | 2024-09-25 | 2025-10-30 |  | FALSE | FALSE
| JDH3-02-008RSEPR1150 | Delivery for Isolation Materials - PR - TSE - Z07 - 1 | 1 | 2024-10-08 | 2024-10-19 | 2025-10-29 |  | FALSE | FALSE
| JDH3-02-008RSEPR1151 | Delivery for GRP pipes - PR - TSE - Z07 - 1 | 1 | 2024-10-20 | 2024-11-03 | 2025-11-01 |  | FALSE | FALSE
| JDH3-02-008RSEPR1153 | Delivery for Concrete Pipes - PR - TSE - Z07 - 1 | 1 | 2024-11-16 | 2024-11-27 | 2025-11-02 |  | FALSE | FALSE
| JDH3-02-008RSEPR1155 | Delivery for Metal Works (Stairs - Covers) - PR - TSE - Z07 - 1 | 1 | 2024-12-10 | 2024-12-21 | 2025-11-04 |  | FALSE | FALSE
| JDH3-02-008RSEPR1183 | Delivery for Concrete - PR - TSE - Z08 | 1 | 2025-11-23 | 2025-12-02 |  |  | FALSE | yes
| JDH3-02-008RSEPR1184 | Delivery for Precast Concrete - PR - TSE - Z08 | 1 | 2025-12-03 | 2025-12-12 |  |  | FALSE | yes
| JDH3-02-008RSEPR1186 | Delivery for Isolation Materials - PR - TSE - Z08 | 1 | 2025-12-26 | 2026-01-04 |  |  | FALSE | yes
| JDH3-02-008RSEPR1187 | Delivery for GRP pipes - PR - TSE - Z08 | 1 | 2025-11-23 | 2025-12-02 |  |  | FALSE | yes
| JDH3-02-008RSEPR1189 | Delivery for Concrete Pipes - PR - TSE - Z08 | 1 | 2025-12-15 | 2025-12-24 |  |  | FALSE | yes
| JDH3-02-008RSEPR1191 | Delivery for Metal Works (Stairs - Covers) - PR - TSE - Z08 | 1 | 2025-12-15 | 2025-12-24 |  |  | FALSE | yes
| JDH3-02-008RSEPR1398 | Delivery for Concrete - PR - TSE - Z13 | 1 | 2025-08-03 | 2025-08-14 | 2025-10-30 |  | FALSE | FALSE
| JDH3-02-008RSEPR1408 | Delivery for Precast Concrete - PR - TSE - Z13 | 1 | 2025-08-15 | 2025-08-26 | 2025-11-01 |  | FALSE | FALSE
| JDH3-02-008RSEPR1428 | Delivery for Isolation Materials - PR - TSE - Z13 | 1 | 2025-09-13 | 2025-09-24 | 2025-11-05 |  | FALSE | FALSE
| JDH3-02-008RSEPR1438 | Delivery for GRP pipes - PR - TSE - Z13 | 1 | 2025-09-25 | 2025-10-06 | 2025-11-02 |  | FALSE | FALSE
| JDH3-02-008RSEPR1458 | Delivery for Concrete Pipes - PR - TSE - Z13 | 1 | 2025-10-22 | 2025-11-02 | 2025-11-01 |  | FALSE | FALSE
| JDH3-02-008RSEPR1478 | Delivery for Metal Works (Stairs - Covers) - PR - TSE - Z13 | 1 | 2025-10-08 | 2025-10-19 | 2025-11-01 |  | FALSE | FALSE
| JDH3-02-008RSEPR1498 | Material Fabrication for Butterfly Valves (Importing) - PR - TSE | 1 | 2024-08-28 | 2024-10-27 |  |  | FALSE | yes
| JDH3-02-008RSEPR1508 | Delivery for Butterfly Valves (Importing) - PR - TSE - MR | 1 | 2024-12-19 | 2025-02-16 |  |  | FALSE | yes
| JDH3-02-008RSEPR769 | Delivery for Precast Concrete - PR - TSE - Z01 | 1 | 2025-11-18 | 2025-11-29 |  |  | FALSE | yes
| JDH3-02-008RSEPR771 | Delivery for Isolation Materials - PR - TSE - Z01 | 1 | 2025-12-12 | 2025-12-23 |  |  | FALSE | yes
| JDH3-02-008RSEPR772 | Delivery for GRP pipes - PR - TSE - Z01 | 1 | 2025-12-24 | 2026-01-04 |  |  | FALSE | yes
| JDH3-02-008RSEPR776 | Delivery for Metal Works (Stairs - Covers) - PR - TSE - Z01 | 1 | 2026-02-10 | 2026-02-21 |  |  | FALSE | yes
| JDH3-02-008RSEPR819 | Delivery for Metal Works (Stairs - Covers) - PR - TSE - Z02 | 1 | 2025-05-22 | 2025-06-02 |  |  | FALSE | yes
| JDH3-02-008RSEPR882 | Delivery for Metal Works (Stairs - Covers) - PR - TSE - Z02 - 1 | 1 | 2024-11-27 | 2024-12-06 |  |  | FALSE | yes
| JDH3-02-008RSEPR9440 | Delivery for Butterfly Valves (Importing) - PR - TSE - Z02 - 2 | 1 | 2024-12-07 | 2025-02-04 |  |  | FALSE | yes
| JDH3-02-008RSEPR9450 | Delivery for Butterfly Valves (Importing) - PR - TSE - Z07 | 1 | 2024-12-19 | 2025-02-16 |  |  | FALSE | yes
| JDH3-02-008RSEPR9460 | Delivery for Butterfly Valves (Importing) - PR - TSE - Z13 | 1 | 2025-11-03 | 2026-01-01 |  |  | FALSE | yes
| JDH3-02-008RSEPR981 | Delivery for Metal Works (Stairs - Covers) - PR - TSE - Z03 | 1 | 2025-11-01 | 2025-11-12 |  |  | FALSE | yes
| JDH3-02-008RSEPR990 | Delivery for Precast Concrete - PR - TSE - Z04 | 1 | 2025-12-07 | 2025-12-18 |  |  | FALSE | yes
| JDH3-02-008RSEPR992 | Delivery for Isolation Materials - PR - TSE - Z04 | 1 | 2025-12-31 | 2026-01-11 |  |  | FALSE | yes
| JDH3-02-008RSEPR993 | Delivery for GRP pipes - PR - TSE - Z04 | 1 | 2026-01-12 | 2026-01-23 |  |  | FALSE | yes
| JDH3-02-008RSEPR995 | Delivery for Concrete Pipes - PR - TSE - Z04 | 1 | 2026-02-05 | 2026-02-15 |  |  | FALSE | yes
| JDH3-02-008RSEPR997 | Delivery for Metal Works (Stairs - Covers) - PR - TSE - Z04 | 1 | 2026-02-28 | 2026-03-10 |  |  | FALSE | yes
| JDH3-02-008RSLPR1171 | Delivery for Steel Covers - PR - SL - Z07 - 1 | 1 | 2024-11-11 | 2024-11-22 |  |  | FALSE | yes
| JDH3-02-008RSLPR1314 | Delivery for Steel Covers - PR - SL - MR | 1 | 2025-07-09 | 2025-07-20 |  |  | FALSE | yes
| JDH3-02-008RSLPR898 | Delivery for Steel Covers - PR - SL - Z02 - 1 | 1 | 2024-11-11 | 2024-11-22 |  |  | FALSE | yes
| JDH3-02-008RSSMI11 | Finish for Sewage Network - SS - MI - SS | 1 |  | 2025-03-25 |  |  | yes | FALSE
| JDH3-02-008RSSPR1263 | Delivery for Concrete - PR - SS - MR | 1 | 2024-12-17 | 2024-12-28 |  |  | FALSE | yes
| JDH3-02-008RSSPR1265 | Delivery for Backfilling Materials - PR - SS - MR | 1 | 2024-12-29 | 2025-01-09 |  |  | FALSE | yes
| JDH3-02-008RSSPR1266 | Delivery for Isolation Materials - PR - SS - MR | 1 | 2025-01-10 | 2025-01-21 |  |  | FALSE | yes
| JDH3-02-008RSSPR1267 | Delivery for GRP pipes - PR - SS - MR | 1 | 2025-01-22 | 2025-02-02 |  |  | FALSE | yes
| JDH3-02-008RSSPR1268 | Delivery for Metal Works (Stairs - Covers) - PR - SS - MR | 1 | 2025-02-03 | 2025-02-14 |  |  | FALSE | yes
| JDH3-02-008RSSPR1338 | Delivery for Concrete - PR - SS - Z09 | 1 | 2026-01-25 | 2026-02-02 |  |  | FALSE | yes
| JDH3-02-008RSSPR1348 | Delivery for Precast Concrete - PR - SS - Z09 | 1 | 2026-02-03 | 2026-02-14 |  |  | FALSE | yes
| JDH3-02-008RSSPR1358 | Delivery for Backfilling Materials - PR - SS - Z09 | 1 | 2026-02-15 | 2026-02-26 | 2025-10-30 |  | FALSE | yes
| JDH3-02-008RSSPR1368 | Delivery for Isolation Materials - PR - SS - Z09 | 1 | 2026-01-25 | 2026-02-05 |  |  | FALSE | yes
| JDH3-02-008RSSPR1378 | Delivery for GRP pipes - PR - SS - Z09 | 1 | 2026-02-06 | 2026-02-17 | 2025-10-30 |  | FALSE | yes
| JDH3-02-008RSSPR1388 | Delivery for Metal Works (Stairs - Covers) - PR - SS - Z09 | 1 | 2026-02-18 | 2026-03-01 |  |  | FALSE | yes
| JDH3-02-008RSSPR1398 | Delivery for Concrete - PR - SS - Z10 | 1 | 2026-02-15 | 2026-02-25 |  |  | FALSE | yes
| JDH3-02-008RSSPR1408 | Delivery for Precast Concrete - PR - SS - Z10 | 1 | 2026-02-26 | 2026-03-08 | 2025-10-30 |  | FALSE | yes
| JDH3-02-008RSSPR1418 | Delivery for Backfilling Materials - PR - SS - Z10 | 1 | 2026-03-09 | 2026-03-19 |  |  | FALSE | yes
| JDH3-02-008RSSPR1428 | Delivery for Isolation Materials - PR - SS - Z10 | 1 | 2026-02-06 | 2026-02-16 |  |  | FALSE | yes
| JDH3-02-008RSSPR1438 | Delivery for GRP pipes - PR - SS - Z10 | 1 | 2026-02-17 | 2026-02-27 | 2025-10-30 |  | FALSE | yes
| JDH3-02-008RSSPR1448 | Delivery for Metal Works (Stairs - Covers) - PR - SS - Z10 | 1 | 2026-02-28 | 2026-03-10 |  |  | FALSE | yes
| JDH3-02-008RSTMI13 | Finish for Storm Network - ST - MI - ST | 1 |  | 2026-03-11 |  |  | yes | FALSE
| JDH3-02-008RSTPR1022 | Delivery for Precast Concrete - PR - ST - Z06 | 1 | 2024-10-21 | 2024-10-30 |  |  | FALSE | yes
| JDH3-02-008RSTPR1024 | Delivery for Isolation Materials - PR - ST - Z06 | 1 | 2024-11-14 | 2024-11-23 |  |  | FALSE | yes
| JDH3-02-008RSTPR1027 | Delivery for Catchbasine - PR - ST - Z06 | 1 | 2024-12-22 | 2024-12-31 |  |  | FALSE | yes
| JDH3-02-008RSTPR1028 | Delivery for Metal Works (Stairs - Covers) - PR - ST - Z06 | 1 | 2025-01-01 | 2025-01-10 |  |  | FALSE | yes
| JDH3-02-008RSTPR1067 | Delivery for Isolation Materials - PR - ST - Z07 | 1 | 2024-10-07 | 2024-10-18 |  |  | FALSE | yes
| JDH3-02-008RSTPR1071 | Delivery for Metal Works (Stairs - Covers) - PR - ST - Z07 | 1 | 2024-11-24 | 2024-12-05 |  |  | FALSE | yes
| JDH3-02-008RSTPR1130 | Delivery for Isolation Materials - PR - ST - Z07 - 1 | 1 | 2024-10-07 | 2024-10-18 |  |  | FALSE | yes
| JDH3-02-008RSTPR1133 | Delivery for Catchbasine - PR - ST - Z07 - 1 | 1 | 2024-11-12 | 2024-11-23 |  |  | FALSE | yes
| JDH3-02-008RSTPR1134 | Delivery for Metal Works (Stairs - Covers) - PR - ST - Z07 - 1 | 1 | 2024-11-24 | 2024-12-05 |  |  | FALSE | yes
| JDH3-02-008RSTPR1367 | Delivery for Concrete - PR - ST - Z02 | 1 | 2024-12-04 | 2024-12-13 |  |  | FALSE | yes
| JDH3-02-008RSTPR1377 | Delivery for Precast Concrete - PR - ST - Z02 | 1 | 2024-12-14 | 2024-12-23 |  |  | FALSE | yes
| JDH3-02-008RSTPR1397 | Delivery for Isolation Materials - PR - ST - Z02 | 1 | 2025-01-01 | 2025-01-04 |  |  | FALSE | yes
| JDH3-02-008RSTPR1417 | Delivery for UPVC pipes - PR - ST - Z02 | 1 | 2025-01-17 | 2025-01-26 |  |  | FALSE | yes
| JDH3-02-008RSTPR1437 | Delivery for Metal Works (Stairs - Covers) - PR - ST - Z02 | 1 | 2025-02-08 | 2025-02-19 |  |  | FALSE | yes
| JDH3-02-008RSTPR1447 | Delivery for Concrete - PR - ST - Z04 | 1 | 2025-11-13 | 2025-11-24 |  |  | FALSE | yes
| JDH3-02-008RSTPR1457 | Delivery for Precast Concrete - PR - ST - Z04 | 1 | 2025-11-25 | 2025-12-06 |  |  | FALSE | yes
| JDH3-02-008RSTPR1467 | Delivery for Backfilling Materials - PR - ST - Z04 | 1 | 2025-12-07 | 2025-12-18 |  |  | FALSE | yes
| JDH3-02-008RSTPR1477 | Delivery for Isolation Materials - PR - ST - Z04 | 1 | 2025-12-19 | 2025-12-30 |  |  | FALSE | yes
| JDH3-02-008RSTPR1517 | Delivery for Metal Works (Stairs - Covers) - PR - ST - Z04 | 1 | 2026-02-15 | 2026-02-26 |  |  | FALSE | yes
| JDH3-02-008RSTPR1537 | Delivery for Precast Concrete - PR - ST - Z05 | 1 | 2024-12-04 | 2024-12-13 |  |  | FALSE | yes
| JDH3-02-008RSTPR1547 | Delivery for Backfilling Materials - PR - ST - Z05 | 1 | 2024-12-14 | 2024-12-23 |  |  | FALSE | yes
| JDH3-02-008RSTPR1557 | Delivery for Isolation Materials - PR - ST - Z05 | 1 | 2024-12-24 | 2025-01-02 |  |  | FALSE | yes
| JDH3-02-008RSTPR1587 | Delivery for Catchbasine - PR - ST - Z05 | 1 | 2025-02-06 | 2025-02-15 |  |  | FALSE | yes
| JDH3-02-008RSTPR1597 | Delivery for Metal Works (Stairs - Covers) - PR - ST - Z05 | 1 | 2025-02-16 | 2025-02-25 |  |  | FALSE | yes
| JDH3-02-008RSTPR1637 | Delivery for Isolation Materials - PR - ST - Z08 | 1 | 2025-11-13 | 2025-11-22 |  |  | FALSE | yes
| JDH3-02-008RSTPR1657.R | Delivery for UPVC pipes - PR - ST - Z08 - Remaining | 1 | 2025-12-07 | 2025-12-16 |  |  | FALSE | yes
| JDH3-02-008RSTPR1667 | Delivery for Catchbasine - PR - ST - Z08 | 1 | 2025-12-17 | 2025-12-25 |  |  | FALSE | yes
| JDH3-02-008RSTPR1677 | Delivery for Metal Works (Stairs - Covers) - PR - ST - Z08 | 1 | 2025-11-13 | 2025-11-22 |  |  | FALSE | yes
| JDH3-02-008RSTPR1687.R | Delivery for Concrete - PR - ST - Z11 - Remaining | 1 | 2025-01-10 | 2025-01-19 |  |  | FALSE | yes
| JDH3-02-008RSTPR1717 | Delivery for Isolation Materials - PR - ST - Z11 | 1 | 2025-02-12 | 2025-02-24 |  |  | FALSE | yes
| JDH3-02-008RSTPR1737.R | Delivery for UPVC pipes - PR - ST - Z11 - Remaining | 1 | 2025-03-20 | 2025-03-28 |  |  | FALSE | yes
| JDH3-02-008RSTPR1747 | Delivery for Catchbasine - PR - ST - Z11 | 1 | 2025-03-28 | 2025-04-09 |  |  | FALSE | yes
| JDH3-02-008RSTPR1757 | Delivery for Metal Works (Stairs - Covers) - PR - ST - Z11 | 1 | 2025-04-09 | 2025-04-21 |  |  | FALSE | yes
| JDH3-02-008RSTPR1767.R | Delivery for Concrete - PR - ST - Z12 - Remaining | 1 | 2025-06-20 | 2025-07-02 |  |  | FALSE | yes
| JDH3-02-008RSTPR1797 | Delivery for Isolation Materials - PR - ST - Z12 | 1 | 2025-07-26 | 2025-08-07 |  |  | FALSE | yes
| JDH3-02-008RSTPR1817.R | Delivery for UPVC pipes - PR - ST - Z12 - Remaining | 1 | 2025-08-31 | 2025-09-12 |  |  | FALSE | yes
| JDH3-02-008RSTPR1827 | Delivery for Catchbasine - PR - ST - Z12 | 1 | 2025-09-12 | 2025-09-24 |  |  | FALSE | yes
| JDH3-02-008RSTPR1837 | Delivery for Metal Works (Stairs - Covers) - PR - ST - Z12 | 1 | 2025-09-24 | 2025-10-06 |  |  | FALSE | yes
| JDH3-02-008RSTPR1877 | Delivery for Isolation Materials - PR - ST - Z13 | 1 | 2026-02-04 | 2026-02-15 |  |  | FALSE | yes
| JDH3-02-008RSTPR1917 | Delivery for Metal Works (Stairs - Covers) - PR - ST - Z13 | 1 | 2026-03-24 | 2026-04-04 |  |  | FALSE | yes
| JDH3-02-008RSTPR749 | Delivery for Precast Concrete - PR - ST - Z01 | 1 | 2025-08-14 | 2025-08-25 |  |  | FALSE | yes
| JDH3-02-008RSTPR751 | Delivery for Isolation Materials - PR - ST - Z01 | 1 | 2025-09-07 | 2025-09-18 |  |  | FALSE | yes
| JDH3-02-008RSTPR754 | Delivery for Catchbasine - PR - ST - Z01 | 1 | 2025-10-13 | 2025-10-24 |  |  | FALSE | yes
| JDH3-02-008RSTPR755 | Delivery for Metal Works (Stairs - Covers) - PR - ST - Z01 | 1 | 2025-10-25 | 2025-11-05 |  |  | FALSE | yes
| JDH3-02-008RSTPR861 | Delivery for Metal Works (Stairs - Covers) - PR - ST - Z02 - 1 | 1 | 2024-11-24 | 2024-12-03 |  |  | FALSE | yes
| JDH3-02-008RTCPR1174 | Delivery for Manhole - PR - TC - Z07 - 1 | 1 | 2024-12-05 | 2024-12-16 |  |  | FALSE | yes
| JDH3-02-008RTCPR1175 | Delivery for Duct - PR - TC - Z07 - 1 | 1 | 2024-12-17 | 2024-12-28 |  |  | FALSE | yes
| JDH3-02-008RTCPR1317 | Delivery for Manhole - PR - TC - MR | 1 | 2025-05-10 | 2025-05-21 |  |  | FALSE | yes
| JDH3-02-008RTCPR1318 | Delivery for Duct - PR - TC - MR | 1 | 2025-05-22 | 2025-06-02 |  |  | FALSE | yes
| JDH3-02-008RTCPR1388 | Delivery for CCTV System - MR | 1 | 2026-04-05 | 2026-04-16 | 2025-10-30 |  | FALSE | yes
| JDH3-02-008RTCPR901 | Delivery for Manhole - PR - TC - Z02 - 1 | 1 | 2024-12-05 | 2024-12-16 |  |  | FALSE | yes
| JDH3-02-008RTCPR902 | Delivery for Duct - PR - TC - Z02 - 1 | 1 | 2024-12-17 | 2024-12-28 |  |  | FALSE | yes
| JDH3-02-008RTSEMI17 | Finish for TSE Network - TSE - MI - TSE | 1 |  | 2026-07-05 |  |  | yes | FALSE
| JDH3-02-008RWTMI15 | Finish for Potable Water Network - WT - MI - WT | 1 |  | 2026-04-14 |  |  | yes | FALSE
| JDH3-02-008RWTPR1039 | Delivery for Metal Works (Stairs - Covers) - PR - WT - Z06 | 1 | 2025-04-02 | 2025-04-10 |  |  | FALSE | yes
| JDH3-02-008RWTPR1082 | Delivery for Metal Works (Stairs - Covers) - PR - WT - Z07 | 1 | 2024-10-26 | 2024-10-31 |  |  | FALSE | yes
| JDH3-02-008RWTPR1145 | Delivery for Metal Works (Stairs - Covers) - PR - WT - Z07 - 1 | 1 | 2024-10-26 | 2024-10-31 |  |  | FALSE | yes
| JDH3-02-008RWTPR1288 | Delivery for Metal Works (Stairs - Covers) - PR - WT - MR | 1 | 2025-04-16 | 2025-04-27 |  |  | FALSE | yes
| JDH3-02-008RWTPR1488 | Delivery for Metal Works (Stairs - Covers) - PR - WT - Z01 | 1 | 2025-07-27 | 2025-08-01 |  |  | FALSE | yes
| JDH3-02-008RWTPR1588 | Delivery for Metal Works (Stairs - Covers) - PR - WT - Z13 | 1 | 2025-09-25 | 2025-09-30 |  |  | FALSE | yes
| JDH3-02-008RWTPR1608 | Material Fabrication for Butterfly Valves (Importing) - PR - WT | 1 | 2024-08-28 | 2024-10-27 |  |  | FALSE | yes
| JDH3-02-008RWTPR1618 | Delivery for Butterfly Valves (Importing) - PR - WT - MR | 1 | 2025-04-28 | 2025-06-26 |  |  | FALSE | yes
| JDH3-02-008RWTPR6970 | Material Purchase Order for Butterfly Valves (Importing) - PR - TSE | 1 | 2024-08-20 | 2024-08-27 |  |  | FALSE | yes
| JDH3-02-008RWTPR700 | Material Purchase Order for Butterfly Valves (Importing) - PR - WT | 1 | 2024-08-20 | 2024-08-27 |  |  | FALSE | yes
| JDH3-02-008RWTPR872 | Delivery for Metal Works (Stairs - Covers) - PR - WT - Z02 - 1 | 1 | 2024-10-26 | 2024-10-31 |  |  | FALSE | yes
| JDH3-02-008RZ01AS323 | Prepare and Submit Drawing for Storm Water Network for - Z01 - AS - ST | 1 | 2026-06-11 | 2026-06-16 |  |  | FALSE | yes
| JDH3-02-008RZ01AS325 | Prepare and Submit Drawing for TSE (IRRIGATION) Network for - Z01 - AS - TSE | 1 | 2026-07-08 | 2026-07-13 |  |  | FALSE | yes
| JDH3-02-008RZ01AS557 | Prepare and Submit Drawing for Potable Water Network for - Z01 - AS - WT | 1 | 2026-06-27 | 2026-07-01 |  |  | FALSE | yes
| JDH3-02-008RZ01AS567 | Review and Approval Drawing for Storm Water Network for - Z01 - AS - ST | 1 | 2026-06-17 | 2026-06-23 |  |  | FALSE | yes
| JDH3-02-008RZ01AS577 | Review and Approval Drawing for TSE (IRRIGATION) Network for - Z01 - AS - TSE | 1 | 2026-07-14 | 2026-07-20 |  |  | FALSE | yes
| JDH3-02-008RZ01AS587 | Review and Approval Drawing for Potable Water Network for - Z01 - AS - WT | 1 | 2026-07-21 | 2026-07-27 |  |  | FALSE | yes
| JDH3-02-008RZ01FT1325 | Final Testing and Commissioning for Storm Network - FT - Z01 - ST | 1 | 2026-06-07 | 2026-06-10 |  |  | FALSE | yes
| JDH3-02-008RZ01FT1327 | Final Testing And Commissioning for TSE (IRRIGATION) Network - FT - Z01 - TSE | 1 | 2026-07-06 | 2026-07-07 |  |  | FALSE | yes
| JDH3-02-008RZ01FT1328 | Final Testing And Commissioning for Potable Water - FT - Z01 - WT | 1 | 2026-06-23 | 2026-06-25 |  |  | FALSE | yes
| JDH3-02-008RZ01MI30 | Finish for Zone 01 - MI - Z01 | 1 |  | 2026-07-05 |  |  | yes | FALSE
| JDH3-02-008RZ02-1AS1 | Review and Approval Drawing for Sewage Network for - Z02 - 1 - AS - SS | 1 | 2026-02-05 | 2026-02-11 |  |  | FALSE | yes
| JDH3-02-008RZ02-1AS2 | Review and Approval Drawing for Storm Network - Pipes for - Z02 - 1 - AS - ST | 1 | 2026-02-12 | 2026-02-18 |  |  | FALSE | yes
| JDH3-02-008RZ02-1AS3 | Review and Approval Drawing for TSE (IRRIGATION) Network for - Z02 - 1 - AS - TSE | 1 | 2026-02-26 | 2026-03-04 |  |  | FALSE | yes
| JDH3-02-008RZ02-1AS339 | Prepare and Submit Drawing for Sewage Network for - Z02 - 1 - AS - SS | 1 | 2026-01-29 | 2026-02-04 |  |  | FALSE | yes
| JDH3-02-008RZ02-1AS340 | Prepare and Submit Drawing for Storm Network - Pipes for - Z02 - 1 - AS - ST | 1 | 2026-02-05 | 2026-02-11 |  |  | FALSE | yes
| JDH3-02-008RZ02-1AS341 | Prepare and Submit Drawing for Potable Water Network for - Z02 - 1 - AS - WT | 1 | 2026-02-12 | 2026-02-18 |  |  | FALSE | yes
| JDH3-02-008RZ02-1AS342 | Prepare and Submit Drawing for TSE (IRRIGATION) Network for - Z02 - 1 - AS - TSE | 1 | 2026-02-19 | 2026-02-25 |  |  | FALSE | yes
| JDH3-02-008RZ02-1AS345 | Prepare and Submit Drawing for Telecommunications Network for - Z02 - 1 - AS | 1 | 2026-03-05 | 2026-03-11 |  |  | FALSE | yes
| JDH3-02-008RZ02-1AS4 | Review and Approval Drawing for Potable Water Network for - Z02 - 1 - AS - WT | 1 | 2026-03-05 | 2026-03-11 |  |  | FALSE | yes
| JDH3-02-008RZ02-1AS5 | Review and Approval Drawing for Street Lighting Network for - Z02 - 1 - AS - SL | 1 | 2026-03-12 | 2026-03-18 |  |  | FALSE | yes
| JDH3-02-008RZ02-1AS6 | Review and Approval Drawing for Telecommunications Network for - Z02 - 1 - AS | 1 | 2026-03-19 | 2026-03-25 |  |  | FALSE | yes
| JDH3-02-008RZ02-1FT1339 | Final Testing And Commissioning for Sewage Network - FT - Z02 - 1 - SS | 1 | 2025-08-14 | 2025-08-18 |  |  | FALSE | yes
| JDH3-02-008RZ02-1FT1340 | Final Testing And Commissioning for Storm Network - FT - Z02 - 1 - ST | 1 | 2025-08-14 | 2025-08-18 |  |  | FALSE | yes
| JDH3-02-008RZ02-1FT1341 | Final Testing And Commissioning for Potable Water - FT - Z02 - 1 - WT | 1 | 2025-08-14 | 2025-08-18 |  |  | FALSE | yes
| JDH3-02-008RZ02-1FT1342 | Final Testing And Commissioning for TSE (IRRIGATION) Network - FT - Z02 - 1 - TSE | 1 | 2025-08-14 | 2025-08-18 |  |  | FALSE | yes
| JDH3-02-008RZ02-1FT1344 | Final Testing And Commissioning for Street Lighting Network - FT - Z02 - 1 - SL | 1 | 2025-08-14 | 2025-08-18 |  |  | FALSE | yes
| JDH3-02-008RZ02-1FT1345 | Final Testing And Commissioning for Telecommunications Network - FT - Z02 - 1 - TC | 1 | 2025-08-14 | 2025-08-18 |  |  | FALSE | yes
| JDH3-02-008RZ02-1MI34 | Finish for Zone 02 - 1 - MI - Z02 - 1 | 1 |  | 2025-05-11 |  |  | yes | FALSE
| JDH3-02-008RZ02-2AS1 | Review and Approval Drawing for Sewage Network for - Z02 - 2 - AS - SS | 1 | 2026-03-19 | 2026-03-25 |  |  | FALSE | yes
| JDH3-02-008RZ02-2AS2 | Review and Approval Drawing for Storm Network - Pipes for - Z02 - 2 - AS - ST | 1 | 2026-03-26 | 2026-04-01 |  |  | FALSE | yes
| JDH3-02-008RZ02-2AS3 | Review and Approval Drawing for TSE (IRRIGATION) Network for - Z02 - 2 - AS - TSE | 1 | 2026-04-09 | 2026-04-15 |  |  | FALSE | yes
| JDH3-02-008RZ02-2AS349 | Prepare and Submit Drawing for Sewage Network for - Z02 - 2 - AS - SS | 1 | 2026-03-12 | 2026-03-18 |  |  | FALSE | yes
| JDH3-02-008RZ02-2AS350 | Prepare and Submit Drawing for Storm Network - Pipes for - Z02 - 2 - AS - ST | 1 | 2026-03-19 | 2026-03-25 |  |  | FALSE | yes
| JDH3-02-008RZ02-2AS351 | Prepare and Submit Drawing for Potable Water Network for - Z02 - 2 - AS - WT | 1 | 2026-03-26 | 2026-04-01 |  |  | FALSE | yes
| JDH3-02-008RZ02-2AS352 | Prepare and Submit Drawing for TSE (IRRIGATION) Network for - Z02 - 2 - AS - TSE | 1 | 2026-04-02 | 2026-04-08 |  |  | FALSE | yes
| JDH3-02-008RZ02-2AS354 | Prepare and Submit Drawing for Street Lighting Network for - Z02 - 2 - AS - SL | 1 | 2026-04-09 | 2026-04-15 |  |  | FALSE | yes
| JDH3-02-008RZ02-2AS355 | Prepare and Submit Drawing for Telecommunications Network for - Z02 - 2 - AS | 1 | 2026-04-16 | 2026-04-22 |  |  | FALSE | yes
| JDH3-02-008RZ02-2AS4 | Review and Approval Drawing for Potable Water Network for - Z02 - 2 - AS - WT | 1 | 2026-04-16 | 2026-04-22 |  |  | FALSE | yes
| JDH3-02-008RZ02-2AS5 | Review and Approval Drawing for Street Lighting Network for - Z02 - 2 - AS - SL | 1 | 2026-04-23 | 2026-04-29 |  |  | FALSE | yes
| JDH3-02-008RZ02-2AS6 | Review and Approval Drawing for Telecommunications Network for - Z02 - 2 - AS | 1 | 2026-04-30 | 2026-05-06 |  |  | FALSE | yes
| JDH3-02-008RZ02-2AS7 | Review and Approval Drawing for Road Works( KERBING AND PAVEMENT ) for - Z02 - 2 - AS - RD | 1 | 2026-05-07 | 2026-05-13 |  |  | FALSE | yes
| JDH3-02-008RZ02-2FT1348 | Final Testing And Commissioning for Sewage Network - FT - Z02 - 2 - SS | 1 | 2025-08-14 | 2025-08-18 |  |  | FALSE | yes
| JDH3-02-008RZ02-2FT1349 | Final Testing And Commissioning for Storm Network - FT - Z02 - 2 - ST | 1 | 2025-08-19 | 2025-08-23 |  |  | FALSE | yes
| JDH3-02-008RZ02-2FT1350 | Final Testing And Commissioning for Potable Water - FT - Z02 - 2 - WT | 1 | 2025-08-24 | 2025-08-27 |  |  | FALSE | yes
| JDH3-02-008RZ02-2FT1351 | Final Testing And Commissioning for TSE (IRRIGATION) Network - FT - Z02 - 2 - TSE | 1 | 2025-08-28 | 2025-09-01 |  |  | FALSE | yes
| JDH3-02-008RZ02-2FT1353 | Final Testing And Commissioning for Street Lighting Network - FT - Z02 - 2 - SL | 1 | 2025-09-02 | 2025-09-06 |  |  | FALSE | yes
| JDH3-02-008RZ02-2FT1354 | Final Testing And Commissioning for Telecommunications Network - FT - Z02 - 2 - TC | 1 | 2025-09-07 | 2025-09-10 |  |  | FALSE | yes
| JDH3-02-008RZ02-2FT1355 | Final Testing And Commissioning for Road Network - FT - Z02 - 2 - RD | 1 | 2025-09-11 | 2025-09-15 |  |  | FALSE | yes
| JDH3-02-008RZ02-2MI36 | Finish for Zone 02 - 2 - MI - Z02 - 2 | 1 |  | 2025-06-14 |  |  | yes | FALSE
| JDH3-02-008RZ02AS332 | Prepare and Submit Drawing for TSE (IRRIGATION) Network for - Z02 - AS - TSE | 1 | 2026-07-02 | 2026-07-08 |  |  | FALSE | yes
| JDH3-02-008RZ02AS450 | Prepare and Submit Drawing for Storm Water Network for - Z02 - AS - ST | 1 | 2026-07-09 | 2026-07-15 |  |  | FALSE | yes
| JDH3-02-008RZ02AS460 | Review and Approval Drawing for TSE (IRRIGATION) Network for - Z02 - AS - TSE | 1 | 2026-07-09 | 2026-07-15 |  |  | FALSE | yes
| JDH3-02-008RZ02AS470 | Review and Approval Drawing for Storm Water Network for - Z02 - AS - ST | 1 | 2026-07-16 | 2026-07-22 |  |  | FALSE | yes
| JDH3-02-008RZ02FT1333 | Final Testing And Commissioning for TSE (IRRIGATION) Network - FT - Z02 - TSE | 1 | 2025-10-18 | 2025-10-21 |  |  | FALSE | yes
| JDH3-02-008RZ02FT1336 | Final Testing And Commissioning for Storm Network - FT - Z02 - ST | 1 | 2025-11-03 | 2025-11-06 |  |  | FALSE | yes
| JDH3-02-008RZ02MI32 | Finish for Zone 02 - MI - Z02 | 1 |  | 2025-11-02 |  |  | yes | FALSE
| JDH3-02-008RZ03AS359 | Prepare and Submit Drawing for TSE (IRRIGATION) Network for - Z03 - AS - TSE | 1 | 2026-01-29 | 2026-02-04 |  |  | FALSE | yes
| JDH3-02-008RZ03AS484 | Review and Approval Drawing for TSE (IRRIGATION) Network for - Z03 - AS - TSE | 1 | 2026-02-05 | 2026-02-11 |  |  | FALSE | yes
| JDH3-02-008RZ03FT1357 | Final Testing And Commissioning for TSE (IRRIGATION) Network - FT - Z03 - TSE | 1 | 2026-01-06 | 2026-01-10 |  |  | FALSE | yes
| JDH3-02-008RZ03MI38 | Finish for Zone 03 - MI - Z03 | 1 |  | 2026-01-05 |  |  | yes | FALSE
| JDH3-02-008RZ04AS363 | Prepare and Submit Drawing for TSE (IRRIGATION) Network for - Z04 - AS - TSE | 1 | 2026-06-23 | 2026-06-29 |  |  | FALSE | yes
| JDH3-02-008RZ04AS364 | Prepare and Submit Drawing for Storm Network - Pipes for - Z04 - AS - ST | 1 | 2026-06-30 | 2026-07-06 |  |  | FALSE | yes
| JDH3-02-008RZ04AS489 | Review and Approval Drawing for TSE (IRRIGATION) Network for - Z04 - AS - TSE | 1 | 2026-06-30 | 2026-07-06 |  |  | FALSE | yes
| JDH3-02-008RZ04AS499 | Review and Approval Drawing for Storm Network - Pipes for - Z04 - AS - ST | 1 | 2026-07-07 | 2026-07-13 |  |  | FALSE | yes
| JDH3-02-008RZ04FT1360 | Final Testing And Commissioning for TSE (IRRIGATION) Network - FT - Z04 - TSE | 1 | 2026-06-18 | 2026-06-22 |  |  | FALSE | yes
| JDH3-02-008RZ04FT1361 | Final Testing And Commissioning for Storm Network - FT - Z04 - ST | 1 | 2026-05-09 | 2026-05-12 |  |  | FALSE | yes
| JDH3-02-008RZ04MI40 | Finish for Zone 04 - MI - Z04 | 1 |  | 2026-06-17 |  |  | yes | FALSE
| JDH3-02-008RZ05AS367 | Prepare and Submit Drawing for TSE (IRRIGATION) Network for - Z05 - AS - TSE | 1 | 2026-01-29 | 2026-02-04 |  |  | FALSE | yes
| JDH3-02-008RZ05AS460 | Prepare and Submit Drawing for Storm Water Network for - Z05 - AS - ST | 1 | 2026-01-29 | 2026-02-04 |  |  | FALSE | yes
| JDH3-02-008RZ05AS492 | Review and Approval Drawing for TSE (IRRIGATION) Network for - Z05 - AS - TSE | 1 | 2026-02-05 | 2026-02-11 |  |  | FALSE | yes
| JDH3-02-008RZ05AS502 | Review and Approval Drawing for Storm Water Network for - Z05 - AS - ST | 1 | 2026-02-05 | 2026-02-11 |  |  | FALSE | yes
| JDH3-02-008RZ05FT1363 | Final Testing And Commissioning for TSE (IRRIGATION) Network - FT - Z05 - TSE | 1 | 2025-10-28 | 2025-11-01 |  |  | FALSE | yes
| JDH3-02-008RZ05FT1364 | Final Testing And Commissioning for Storm Network - FT - Z05 - ST | 1 | 2025-11-20 | 2025-11-24 |  |  | FALSE | yes
| JDH3-02-008RZ05MI42 | Finish for Zone 05 - MI - Z05 | 1 |  | 2025-11-19 |  |  | yes | FALSE
| JDH3-02-008RZ06AS371 | Prepare and Submit Drawing for Storm Network - Pipes for - Z06 - AS - ST | 1 | 2026-03-17 | 2026-03-23 |  |  | FALSE | yes
| JDH3-02-008RZ06AS373 | Prepare and Submit Drawing for TSE (IRRIGATION) Network for - Z06 - AS - TSE | 1 | 2026-03-24 | 2026-03-30 |  |  | FALSE | yes
| JDH3-02-008RZ06AS567 | Prepare and Submit Drawing for Potable Water Network for - Z06 - AS - WT | 1 | 2026-03-16 | 2026-03-22 |  |  | FALSE | yes
| JDH3-02-008RZ06AS577 | Review and Approval Drawing for Storm Network - Pipes for - Z06 - AS - ST | 1 | 2026-07-07 | 2026-07-13 |  |  | FALSE | yes
| JDH3-02-008RZ06AS587 | Review and Approval Drawing for TSE (IRRIGATION) Network for - Z06 - AS - TSE | 1 | 2026-07-14 | 2026-07-20 |  |  | FALSE | yes
| JDH3-02-008RZ06AS597 | Review and Approval Drawing for Potable Water Network for - Z06 - AS - WT | 1 | 2026-07-21 | 2026-07-27 |  |  | FALSE | yes
| JDH3-02-008RZ06FT1366 | Final Testing And Commissioning for Storm Network - FT - Z06 - ST | 1 | 2026-03-12 | 2026-03-16 |  |  | FALSE | yes
| JDH3-02-008RZ06FT1367 | Final Testing And Commissioning for Potable Water - FT - Z06 - WT | 1 | 2026-04-15 | 2026-04-19 |  |  | FALSE | yes
| JDH3-02-008RZ06FT1368 | Final Testing And Commissioning for TSE (IRRIGATION) Network - FT - Z06 - TSE | 1 | 2026-03-11 | 2026-03-15 |  |  | FALSE | yes
| JDH3-02-008RZ06MI44 | Finish for Zone 06 - MI - Z06 | 1 |  | 2026-04-14 |  |  | yes | FALSE
| JDH3-02-008RZ07-1AS389 | Prepare and Submit Drawing for Sewage Network for - Z07 - 1 - AS - SS | 1 | 2026-02-08 | 2026-02-14 |  |  | FALSE | yes
| JDH3-02-008RZ07-1AS390 | Prepare and Submit Drawing for Storm Network - Pipes for - Z07 - 1 - AS - ST | 1 | 2026-02-15 | 2026-02-21 |  |  | FALSE | yes
| JDH3-02-008RZ07-1AS392 | Prepare and Submit Drawing for Potable Water Network for - Z07 - 1 - AS - WT | 1 | 2026-02-22 | 2026-02-28 |  |  | FALSE | yes
| JDH3-02-008RZ07-1AS394 | Prepare and Submit Drawing for TSE (IRRIGATION) Network for - Z07 - 1 - AS - TSE | 1 | 2026-03-01 | 2026-03-07 |  |  | FALSE | yes
| JDH3-02-008RZ07-1AS396 | Prepare and Submit Drawing for Street Lighting Network for - Z07 - 1 - AS - SL | 1 | 2026-03-08 | 2026-03-14 |  |  | FALSE | yes
| JDH3-02-008RZ07-1AS397 | Prepare and Submit Drawing for Telecommunications Network for - Z07 - 1 - AS | 1 | 2026-03-15 | 2026-03-21 |  |  | FALSE | yes
| JDH3-02-008RZ07-1AS4 | Review and Approval Drawing for Sewage Network for - Z07 - 1 - AS - SS | 1 | 2026-02-15 | 2026-02-21 |  |  | FALSE | yes
| JDH3-02-008RZ07-1AS5 | Review and Approval Drawing for Storm Network - Pipes for - Z07 - 1 - AS - ST | 1 | 2026-02-22 | 2026-02-28 |  |  | FALSE | yes
| JDH3-02-008RZ07-1AS6 | Review and Approval Drawing for Street Lighting Network for - Z07 - 1 - AS - SL | 1 | 2026-03-15 | 2026-03-21 |  |  | FALSE | yes
| JDH3-02-008RZ07-1AS7 | Review and Approval Drawing for Telecommunications Network for - Z07 - 1 - AS | 1 | 2026-03-22 | 2026-03-28 |  |  | FALSE | yes
| JDH3-02-008RZ07-1AS8 | Review and Approval Drawing for TSE (IRRIGATION) Network for - Z07 - 1 - AS - TSE | 1 | 2026-03-29 | 2026-04-04 |  |  | FALSE | yes
| JDH3-02-008RZ07-1AS9 | Review and Approval Drawing for Potable Water Network for - Z07 - 1 - AS - WT | 1 | 2026-04-05 | 2026-04-11 |  |  | FALSE | yes
| JDH3-02-008RZ07-1FT1380 | Final Testing And Commissioning for Sewage Network - FT - Z07 - 1 - SS | 1 | 2025-08-14 | 2025-08-18 |  |  | FALSE | yes
| JDH3-02-008RZ07-1FT1381 | Final Testing And Commissioning for Storm Network - FT - Z07 - 1 - ST | 1 | 2025-08-14 | 2025-08-18 |  |  | FALSE | yes
| JDH3-02-008RZ07-1FT1382 | Final Testing And Commissioning for Potable Water - FT - Z07 - 1 - WT | 1 | 2025-08-14 | 2025-08-18 |  |  | FALSE | yes
| JDH3-02-008RZ07-1FT1383 | Final Testing And Commissioning for TSE (IRRIGATION) Network - FT - Z07 - 1 - TSE | 1 | 2025-08-14 | 2025-08-18 |  |  | FALSE | yes
| JDH3-02-008RZ07-1FT1385 | Final Testing And Commissioning for Street Lighting Network - FT - Z07 - 1 - SL | 1 | 2025-08-14 | 2025-08-18 |  |  | FALSE | yes
| JDH3-02-008RZ07-1FT1386 | Final Testing And Commissioning for Telecommunications Network - FT - Z07 - 1 - TC | 1 | 2025-08-14 | 2025-08-18 |  |  | FALSE | yes
| JDH3-02-008RZ07-1MI48 | Finish for Zone 07 - 1 - MI - Z07 - 1 | 1 |  | 2025-02-23 |  |  | yes | FALSE
| JDH3-02-008RZ07AS378 | Prepare and Submit Drawing for Storm Network - Pipes for - Z07 - AS - ST | 1 | 2026-01-29 | 2026-02-04 |  |  | FALSE | yes
| JDH3-02-008RZ07AS382 | Prepare and Submit Drawing for TSE (IRRIGATION) Network for - Z07 - AS - TSE | 1 | 2026-02-03 | 2026-02-09 |  |  | FALSE | yes
| JDH3-02-008RZ07AS577 | Prepare and Submit Drawing for Potable Water Network for - Z07 - AS - WT | 1 | 2026-02-01 | 2026-02-07 |  |  | FALSE | yes
| JDH3-02-008RZ07AS587 | Review and Approval Drawing for Storm Network - Pipes for - Z07 - AS - ST | 1 | 2026-02-05 | 2026-02-11 |  |  | FALSE | yes
| JDH3-02-008RZ07AS607 | Review and Approval Drawing for TSE (IRRIGATION) Network for - Z07 - AS - TSE | 1 | 2026-02-10 | 2026-02-16 |  |  | FALSE | yes
| JDH3-02-008RZ07AS617 | Review and Approval Drawing for Potable Water Network for - Z07 - AS - WT | 1 | 2026-02-08 | 2026-02-14 |  |  | FALSE | yes
| JDH3-02-008RZ07FT1372 | Final Testing And Commissioning for Storm Network - FT - Z07 - ST | 1 | 2026-01-10 | 2026-01-13 |  |  | FALSE | yes
| JDH3-02-008RZ07FT1373 | Final Testing And Commissioning for Potable Water - FT - Z07 - WT | 1 | 2026-01-29 | 2026-02-02 |  |  | FALSE | yes
| JDH3-02-008RZ07FT1374 | Final Testing And Commissioning for TSE (IRRIGATION) Network - FT - Z07 - TSE | 1 | 2026-01-27 | 2026-01-31 |  |  | FALSE | yes
| JDH3-02-008RZ07MI46 | Finish for Zone 07 - MI - Z07 | 1 |  | 2026-01-28 |  |  | yes | FALSE
| JDH3-02-008RZ08AS401 | Prepare and Submit Drawing for TSE (IRRIGATION) Network for - Z08 - AS - TSE | 1 | 2026-03-28 | 2026-04-02 |  |  | FALSE | yes
| JDH3-02-008RZ08AS507 | Prepare and Submit Drawing for Storm Network - Pipes for - Z08 - AS - ST | 1 | 2026-04-11 | 2026-04-16 |  |  | FALSE | yes
| JDH3-02-008RZ08AS528 | Review and Approval Drawing for TSE (IRRIGATION) Network for - Z08 - AS - TSE | 1 | 2026-04-04 | 2026-04-09 |  |  | FALSE | yes
| JDH3-02-008RZ08AS538 | Review and Approval Drawing for Road Works( KERBING AND PAVEMENT ) for - Z08 - AS - RD | 1 | 2026-04-11 | 2026-04-16 |  |  | FALSE | yes
| JDH3-02-008RZ08AS548 | Review and Approval Drawing for Storm Network - Pipes for - Z08 - AS - ST | 1 | 2026-04-18 | 2026-04-23 |  |  | FALSE | yes
| JDH3-02-008RZ08FT1389 | Final Testing And Commissioning for TSE (IRRIGATION) Network - FT - Z08 - TSE | 1 | 2026-03-23 | 2026-03-26 |  |  | FALSE | yes
| JDH3-02-008RZ08FT139 | Final Testing And Commissioning for Storm Network - FT - Z08 - ST | 1 | 2026-03-16 | 2026-03-19 |  |  | FALSE | yes
| JDH3-02-008RZ08FT1391 | Final Testing And Commissioning for Road Network - FT - Z08 - RD | 1 | 2026-02-08 | 2026-02-11 |  |  | FALSE | yes
| JDH3-02-008RZ08MI50 | Finish for Zone 08 - MI - Z08 | 1 |  | 2026-03-22 |  |  | yes | FALSE
| JDH3-02-008RZ09AS1 | Review and Approval Drawing for Sewage Network for - Z09 - AS - SS | 1 | 2026-07-21 | 2026-07-27 |  |  | FALSE | yes
| JDH3-02-008RZ09AS11 | Prepare and Submit Drawing for Sewage Network for - Z09 - AS - SS | 1 | 2026-07-14 | 2026-07-20 |  |  | FALSE | yes
| JDH3-02-008RZ09FT1 | Final Testing And Commissioning for Sewage Network - FT - Z09 - SS | 1 | 2026-07-09 | 2026-07-13 |  |  | FALSE | yes
| JDH3-02-008RZ09MI76 | Finish for Zone 09 - MI - Z09 | 1 |  | 2026-07-08 |  |  | yes | FALSE
| JDH3-02-008RZ10AS1 | Review and Approval Drawing for Sewage Network for - Z10 - AS - SS | 1 | 2026-07-11 | 2026-07-16 |  |  | FALSE | yes
| JDH3-02-008RZ10AS11 | Prepare and Submit Drawing for Sewage Network for - Z10 - AS - SS | 1 | 2026-07-04 | 2026-07-09 |  |  | FALSE | yes
| JDH3-02-008RZ10FT1 | Final Testing And Commissioning for Sewage Network - FT - Z10 - SS | 1 | 2026-06-29 | 2026-07-02 |  |  | FALSE | yes
| JDH3-02-008RZ10MI96 | Finish for Zone 10 - MI - Z10 | 1 |  | 2026-06-28 |  |  | yes | FALSE
| JDH3-02-008RZ11AS517 | Prepare and Submit Drawing for Storm Network - Pipes for - Z11 - AS - ST | 1 | 2026-03-24 | 2026-03-30 |  |  | FALSE | yes
| JDH3-02-008RZ11AS538 | Review and Approval Drawing for Road Works( KERBING AND PAVEMENT ) for - Z11 - AS - RD | 1 | 2026-03-24 | 2026-03-30 |  |  | FALSE | yes
| JDH3-02-008RZ11AS548 | Review and Approval Drawing for Storm Network - Pipes for - Z11 - AS - ST | 1 | 2026-03-31 | 2026-04-06 |  |  | FALSE | yes
| JDH3-02-008RZ11FT140 | Final Testing And Commissioning for Storm Network - FT - Z11 - ST | 1 | 2026-03-03 | 2026-03-07 |  |  | FALSE | yes
| JDH3-02-008RZ11FT1400 | Final Testing And Commissioning for Road Network - FT - Z11 - RD | 1 | 2026-03-12 | 2026-03-16 |  |  | FALSE | yes
| JDH3-02-008RZ11MI56 | Finish for Zone 11 - MI - Z11 | 1 |  | 2026-03-11 |  |  | yes | FALSE
| JDH3-02-008RZ12AS547 | Prepare and Submit Drawing for Storm Network - Pipes for - Z12 - AS - ST | 1 | 2026-03-31 | 2026-04-06 |  |  | FALSE | yes
| JDH3-02-008RZ12AS557 | Review and Approval Drawing for Storm Network - Pipes for - Z12 - AS - ST | 1 | 2026-04-07 | 2026-04-13 |  |  | FALSE | yes
| JDH3-02-008RZ12FT1402 | Final Testing And Commissioning for Storm Network - FT - Z12 - ST | 1 | 2026-02-15 | 2026-02-18 |  |  | FALSE | yes
| JDH3-02-008RZ12MI58 | Finish for Zone 12 - MI - Z12 | 1 |  | 2026-02-14 |  |  | yes | FALSE
| JDH3-02-008RZ13AS527 | Prepare and Submit Drawing for Storm Network - Pipes for - Z13 - AS - ST | 1 | 2026-07-01 | 2026-07-07 |  |  | FALSE | yes
| JDH3-02-008RZ13AS537 | Prepare and Submit Drawing for TSE (IRRIGATION) Network for - Z13 - AS - TSE | 1 | 2026-07-08 | 2026-07-14 |  |  | FALSE | yes
| JDH3-02-008RZ13AS587 | Prepare and Submit Drawing for Potable Water Network for - Z13 - AS - WT | 1 | 2026-07-15 | 2026-07-21 |  |  | FALSE | yes
| JDH3-02-008RZ13AS597 | Review and Approval Drawing for Storm Network - Pipes for - Z13 - AS - ST | 1 | 2026-07-08 | 2026-07-14 |  |  | FALSE | yes
| JDH3-02-008RZ13AS607 | Review and Approval Drawing for TSE (IRRIGATION) Network for - Z13 - AS - TSE | 1 | 2026-07-15 | 2026-07-21 |  |  | FALSE | yes
| JDH3-02-008RZ13AS617 | Review and Approval Drawing for Potable Water Network for - Z13 - AS - WT | 1 | 2026-07-22 | 2026-07-28 |  |  | FALSE | yes
| JDH3-02-008RZ13FT1404 | Final Testing And Commissioning for Storm Network - FT - Z13 - ST | 1 | 2026-06-27 | 2026-06-30 |  |  | FALSE | yes
| JDH3-02-008RZ13FT141 | Final Testing And Commissioning for Potable Water - FT - Z13 - WT | 1 | 2026-06-25 | 2026-06-29 |  |  | FALSE | yes
| JDH3-02-008RZ13FT142 | Final Testing And Commissioning for TSE (IRRIGATION) Network - FT - Z13 - TSE | 1 | 2026-06-14 | 2026-06-17 |  |  | FALSE | yes
| JDH3-02-008RZ13MI60 | Finish for Zone 13 - MI - Z13 | 1 |  | 2026-06-25 |  |  | yes | FALSE
| Activity ID | Activity Name | Activity Count | BL Project Start | BL Project Finish | Actual Start | Actual Finish
| A1000 | Start of Sewage network Z02-1 MI-SS | 1 | 2024-12-05
| A1010 | Finish of Sewage network Z02-1 MI-SS | 1 |  | 2025-03-25
| A1020 | Start of Sewage network Z02-2 MI-SS | 1 | 2024-12-07
| A1030 | Finish of Sewage network Z02-2 MI-SS | 1 |  | 2025-01-14
| A1040 | Start of Sewage network Z07-1 MI-SS | 1 | 2024-12-07
| A1050 | Finish of Sewage network Z07-1 MI-SS | 1 |  | 2024-12-07
| A1060 | Start of Sewage network MR MI-SS | 1 | 2025-02-17
| A1100 | Start of Storm Network Z02-1 MI-ST | 1 | 2024-11-24
| A1110 | Finish of Storm Network Z02-1 MI-ST | 1 |  | 2025-05-11
| A1120 | Start of Storm Network Z02-2 MI-ST | 1 | 2024-12-22
| A1130 | Finish of Storm Network Z02-2 MI-ST | 1 |  | 2025-03-12
| A1140 | Start of Storm Network Z06 MI-ST | 1 | 2025-08-02
| A1160 | Start of Storm Network Z07 MI-ST | 1 | 2024-11-24
| A1180 | Start of Storm Network Z07-1 MI-ST | 1 | 2024-12-07
| A1190 | Finish of Storm Network Z07-1 MI-ST | 1 |  | 2024-12-26
| A1200 | Start of Storm Network MR MI-ST | 1 | 2024-12-07
| A1240 | Start of TSE Network Z02 MI-TSE | 1 | 2025-09-11
| A1260 | Start of TSE Network Z02-1 MI-TSE | 1 | 2024-12-07
| A1270 | Finish of TSE Network Z02-1 MI-TSE | 1 |  | 2025-05-11
| A1280 | Start of TSE Network Z02-2 MI-TSE | 1 | 2024-11-13
| A1290 | Finish of TSE Network Z02-2 MI-TSE | 1 |  | 2025-01-20
| A1340 | Start of TSE Network Z05 MI-TSE | 1 | 2025-09-11
| A1360 | Start of TSE Network Z06 MI-TSE | 1 | 2025-08-02
| A1380 | Start of TSE Network Z07 MI-TSE | 1 | 2024-12-07
| A1400 | Start of TSE Network Z07-1 MI-TSE | 1 | 2024-12-22
| A1410 | Finish of TSE Network Z07-1 MI-TSE | 1 |  | 2024-12-22
| A1440 | Start of TSE Network MR MI-TSE | 1 | 2025-02-17
| A1460 | Start of PT-WT network Z02-1 MI-WT | 1 | 2024-12-07
| A1470 | Finish of PT-WT Network Z02-1 MI-WT | 1 |  | 2025-03-25
| A1480 | Start of PT-WT network Z02-2 MI-WT | 1 | 2025-02-23
| A1490 | Finish of PT-WT Network Z02-2 MI-WT | 1 |  | 2025-02-23
| A1500 | Start of PT-WT network Z07-1 MI-WT | 1 | 2024-11-02
| A1510 | Finish of PT-WT Network Z07-1 MI-WT | 1 |  | 2025-02-23
| A1520 | Start of PT-WT network Z07 MI-WT | 1 | 2024-10-14
| A1540 | Start of PT-WT network Z06 MI-WT | 1 | 2025-08-02
| A1580 | Start of PT-WT network MR MI-WT | 1 | 2025-06-28
| A1660 | Start of ELECTRICAL Network Z02-2 MI-EL-SL-TC | 1 | 2025-04-15
| A1670 | Finish of ELECTRICAL Network Z02-2 MI-EL-SL-TC | 1 |  | 2025-05-18
| A1800 | Start of Road Network Z02-2 MI-RD | 1 | 2024-10-17 |  | 2025-02-15
| A1810 | Finish of Road Network Z02-2 MI-RD | 1 |  | 2025-06-14
| A1860 | Start of Storm Network Z05 MI-ST | 1 | 2025-09-11
| A2140 | Prepare and Submit MOS for Earth Works -MOS | 1 | 2024-07-30 | 2024-08-01 | 2024-09-21 | 2024-10-21
| A2150 | Review and Approval MOS for Earth Works -MOS | 1 | 2024-08-04 | 2024-08-13 | 2024-10-10 | 2025-01-07
| A2160 | Prepare and Submit MOS for Concrete Works -MOS | 1 | 2024-08-03 | 2024-08-05 | 2024-11-14 | 2024-12-14
| A2170 | Review and Approval MOS for Concrete Works -MOS | 1 | 2024-08-14 | 2024-08-25 | 2024-11-16 | 2025-02-12
| A2180 | Prepare and Submit MOS for Underground Utilities and Foundation -MOS | 1 | 2024-07-30 | 2024-08-01 | 2024-10-31 | 2024-11-30
| A2190 | Review and Approval MOS for Underground Utilities and Foundation -MOS | 1 | 2024-08-04 | 2024-08-13 | 2024-11-02 | 2025-01-29
| A2200 | Prepare and Submit MOS for Storm Network -MOS | 1 | 2024-07-30 | 2024-08-01 | 2024-11-20 | 2024-12-19
| A2210 | Review and Approval MOS for Storm Network -MOS | 1 | 2024-08-04 | 2024-08-13 | 2024-11-29 | 2025-02-26
| A2220 | Prepare and Submit MOS for Asphalt Works -MOS | 1 | 2024-07-30 | 2024-08-01 | 2024-09-24 | 2024-10-23
| A2230 | Review and Approval MOS for Asphalt Works -MOS | 1 | 2024-08-04 | 2024-08-13 | 2024-09-29 | 2024-12-25
| A2240 | Prepare and Submit MOS for Sewage Network -MOS | 1 | 2024-07-30 | 2024-08-01 | 2024-12-01 | 2024-12-30
| A2250 | Review and Approval MOS for Sewage Network -MOS | 1 | 2024-08-04 | 2024-08-13 | 2024-12-11 | 2025-03-10
| A2260 | Prepare and Submit MOS for Potable Network -MOS | 1 | 2024-07-30 | 2024-08-01 | 2025-01-09 | 2025-02-08
| A2270 | Review and Approval MOS for Potable Network -MOS | 1 | 2024-08-04 | 2024-08-13 | 2025-01-13 | 2025-04-10
| A2280 | Prepare and Submit MOS for TSE Network -MOS | 1 | 2024-07-30 | 2024-08-01 | 2024-12-10 | 2025-01-08
| A2290 | Review and Approval MOS for TSE Network -MOS | 1 | 2024-08-04 | 2024-08-13 | 2024-12-17 | 2025-03-16
| A2300 | Prepare and Submit MOS for Street Lighting -MOS | 1 | 2024-07-30 | 2024-08-01 | 2025-03-05 | 2025-04-03
| A2310 | Review and Approval MOS for Street Lighting -MOS | 1 | 2024-08-04 | 2024-08-13 | 2025-03-12 | 2025-06-09
| A2320 | Prepare and Submit MOS for Precast Curbstone, Interlocking -MOS | 1 | 2024-07-30 | 2024-08-01 | 2024-11-02 | 2024-12-01
| A2330 | Review and Approval MOS for Precast Curbstone, Interlocking -MOS | 1 | 2024-08-04 | 2024-08-13 | 2024-11-06 | 2025-02-03
| A2340 | Prepare and Submit MOS for Waterproofing -MOS | 1 | 2024-07-30 | 2024-08-01 | 2025-02-10 | 2025-03-11
| A2350 | Review and Approval MOS for Waterproofing -MOS | 1 | 2024-08-04 | 2024-08-13 | 2025-02-18 | 2025-05-18
| A2360 | Prepare and Submit MOS for Precast Box Culvert -MOS | 1 | 2024-07-30 | 2024-08-01 | 2024-10-31 | 2024-11-30
| A2370 | Review and Approval MOS for Precast Box Culvert -MOS | 1 | 2024-08-04 | 2024-08-13 | 2024-11-05 | 2025-02-02
| A2430 | Surveying Works L-47 | 1 | 2025-09-11 | 2025-09-14 | 2025-07-16 | 2025-07-30
| A2440 | Surveying Works L-48 | 1 | 2025-09-11 | 2025-09-18 | 2025-07-12 | 2025-07-21
| A2450 | Surveying Works L-49 | 1 | 2025-09-11 | 2025-09-18 | 2025-07-23 | 2025-07-30
| A2460 | Surveying Works L-50 | 1 | 2025-09-11 | 2025-09-18 | 2025-07-01 | 2025-07-08
| A2470 | Surveying Works L-69 | 1 | 2024-08-27 | 2024-09-03 | 2025-04-01 | 2025-04-08
| A2480 | Surveying Works L-70 | 1 | 2024-08-27 | 2024-09-03 | 2025-07-01 | 2025-07-15
| A2490 | Surveying Works L-71 | 1 | 2024-08-27 | 2024-09-03 | 2025-04-01 | 2025-04-05
| A2500 | Surveying Works L-72 | 1 | 2024-12-05 | 2024-12-12 | 2025-04-01 | 2025-04-05
| A2510 | Surveying Works L-73 | 1 | 2024-12-05 | 2024-12-12 | 2025-06-10 | 2025-06-18
| A2520 | Surveying Works C-16 | 1 | 2024-08-27 | 2024-09-03 | 2025-02-10 | 2025-02-25
| A2530 | Surveying Works L-74 | 1 | 2024-12-07 | 2024-12-14 | 2025-02-10 | 2025-02-26
| A2540 | Surveying Works L-75 | 1 | 2024-12-07 | 2024-12-14 | 2025-02-10 | 2025-02-19
| A2590 | Surveying Works L-04 | 1 | 2025-09-11 | 2025-09-18 | 2025-07-08 | 2025-07-22
| A2660 | Surveying Works L-05 | 1 | 2025-09-11 | 2025-09-18 | 2025-07-01 | 2025-07-16
| A2670 | Surveying Works L-06 | 1 | 2025-09-11 | 2025-09-18 | 2025-07-19 | 2025-07-31
| A2680 | Surveying Works L-07 | 1 | 2025-09-11 | 2025-09-18 | 2025-07-07 | 2025-07-23
| A2690 | Surveying Works L-53 | 1 | 2025-08-02 | 2025-08-09 | 2025-07-22 | 2025-07-29
| A2700 | Surveying Works L-54 | 1 | 2025-08-10 | 2025-08-17 | 2025-04-01 | 2025-04-14
| A2710 | Surveying Works L-55 | 1 | 2025-08-18 | 2025-08-25 | 2025-02-04 | 2025-02-11
| A2720 | Surveying Works L-56 | 1 | 2025-08-26 | 2025-09-02 | 2024-11-04 | 2024-11-10
| A2730 | Surveying Works L-57 | 1 | 2025-09-03 | 2025-09-10 | 2024-11-03 | 2024-11-11
| A2740 | Surveying Works C-04 | 1 | 2025-01-22 | 2025-01-29 | 2024-12-17 | 2024-12-31
| A2750 | Surveying Works L-52 | 1 | 2024-11-24 | 2024-12-01 | 2024-11-06 | 2024-11-25
| A2760 | Surveying Works L-63 | 1 | 2024-11-24 | 2024-12-01 | 2024-11-12 | 2024-11-28
| A2770 | Surveying Works L-64 | 1 | 2024-11-24 | 2024-12-01 | 2024-11-02 | 2024-11-12
| A2780 | Surveying Works L-65 | 1 | 2024-12-02 | 2024-12-09 | 2025-01-01 | 2025-01-08
| A2790 | Surveying Works L-66 | 1 | 2024-12-10 | 2024-12-17 | 2025-03-17 | 2025-03-29
| A2800 | Surveying Works L-67 | 1 | 2024-12-18 | 2024-12-25 | 2024-11-12 | 2024-11-28
| A2810 | Surveying Works L-68 | 1 | 2024-12-26 | 2025-01-02 | 2025-02-11 | 2025-02-25
| A2820 | Surveying Works L-59 | 1 | 2024-08-27 | 2024-09-03 | 2024-11-02 | 2024-11-12
| A2830 | Surveying Works L-60 | 1 | 2024-08-27 | 2024-09-03 | 2024-10-14 | 2024-10-28
| A2850 | Surveying Works L-62 | 1 | 2024-08-27 | 2024-09-03 | 2024-11-05 | 2024-11-20
| A3090 | Surveying Works C-01 | 1 | 2024-08-27 | 2024-09-03 | 2025-04-28 | 2025-05-01
| A3100 | Surveying Works C-02 | 1 | 2024-12-14 | 2024-12-21 | 2025-06-12 | 2025-06-18
| A3110 | Surveying Works C-03 | 1 | 2025-05-05 | 2025-05-12 | 2025-01-08 | 2025-01-16
| A3120 | Surveying Works C-05 | 1 | 2025-08-27 | 2025-09-03 | 2025-04-01 | 2025-04-07
| A3150 | Surveying Works C-08 | 1 | 2025-08-02 | 2025-08-09 | 2025-04-08 | 2025-04-12
| A3160 | Surveying Works C-09 | 1 | 2024-08-27 | 2024-09-03 | 2025-04-07 | 2025-04-12
| A3170 | Surveying Works C-10 | 1 | 2024-12-14 | 2024-12-21 | 2025-04-01 | 2025-04-08
| A3180 | Surveying Works C-11 | 1 | 2025-08-10 | 2025-08-17 | 2025-06-09 | 2025-06-14
| A3200 | Surveying Works C-13 | 1 | 2025-08-18 | 2025-08-25 | 2025-04-09 | 2025-04-13
| A3240 | Surveying Works L-03 | 1 | 2025-08-26 | 2025-09-02 | 2024-11-05 | 2024-12-02
| A3270 | Surveying Works L-51 | 1 | 2025-09-11 | 2025-09-18 | 2024-12-01 | 2024-12-10
| A3280 | Surveying Works L-58 | 1 | 2025-09-20 | 2025-09-27 | 2024-10-08 | 2024-10-15
| A3400 | Start of PONDS -PS | 1 | 2024-09-11 |  | 2024-09-28
| A3640 | Start of ELECTRICAL Network MR MI-EL-SL-TC | 1 | 2025-08-02
| A3670 | Start of Storm Network Z02 MI-ST | 1 | 2025-09-11
| A3680 | Finish of ELECTRICAL Network Z02-1 MI-EL-SL-TC | 1 |  | 2025-05-11
| A3690 | Start of ELECTRICAL Network Z02-1 MI-EL-SL-TC | 1 | 2025-03-26
| A3700 | Finish of ELECTRICAL Network Z07-1 MI-EL-SL-TC | 1 |  | 2025-01-28
| A3710 | Start of ELECTRICAL Network Z07-1 MI-EL-SL-TC | 1 | 2024-12-29
| A3860 | Surveying Works L-17 | 1 | 2025-09-03 | 2025-09-10 | 2025-07-07 | 2025-07-15
| A3870 | start-FT-MI | 1 | 2025-08-10 | 2025-08-13
| JD3RMRC01ST100 | Channel excavation for Swales-B6.31 22 00.13-MR-C-01-ST | 1 | 2024-09-10 | 2024-09-25 | 2025-05-05 | 2025-07-31
| JD3RMRC01ST100.R | Channel excavation for Swales-B6.31 22 00.13-MR-C-01-ST -Remaining | 1 | 2024-09-26 | 2024-10-08 | 2025-08-02
| JD3RMRC01ST300 | Riprap with side slopes 1.5:1 for Swales-NB6.31 22 00.16-MR-C-01-ST | 1 | 2024-10-09 | 2024-10-30 | 2025-05-15 | 2025-07-31
| JD3RMRC01ST300.R | Riprap with side slopes 1.5:1 for Swales-NB6.31 22 00.16-MR-C-01-ST -Remaining | 1 | 2024-10-31 | 2024-11-17 | 2025-08-16
| JD3RMRC01ST50891 | Excavation Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-C-01-ST | 1 | 2024-11-18 | 2024-11-19 | 2025-08-12 | 2025-08-25
| JD3RMRC01ST50892 | Soil Replacement and Bedding Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-C-01-ST | 1 | 2024-11-20 | 2024-11-21 | 2025-08-15 | 2025-08-25
| JD3RMRC01ST50893 | Installing for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-C-01-ST | 1 | 2024-11-23 | 2024-11-25 | 2025-08-18 | 2025-08-27
| JD3RMRC01ST50894 | Primary Test for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-C-01-ST | 1 | 2024-11-26 | 2024-11-27 | 2025-08-21 | 2025-08-28
| JD3RMRC01ST50895 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-C-01-ST | 1 | 2024-11-28 | 2024-12-01 | 2025-08-23 | 2025-08-30
| JD3RMRC01ST50994 | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-MR-C-01-ST | 1 | 2024-11-18 | 2024-11-19 | 2025-08-12 | 2025-08-25
| JD3RMRC01ST50995 | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-MR-C-01-ST | 1 | 2024-11-20 | 2024-11-21 | 2025-08-18 | 2025-08-27
| JD3RMRC01ST50996 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-MR-C-01-ST | 1 | 2024-11-23 | 2024-11-24
| JD3RMRC01ST50997 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-MR-C-01-ST | 1 | 2024-11-25 | 2024-11-26
| JD3RMRC01ST50998 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-MR-C-01-ST | 1 | 2024-11-27 | 2024-11-28
| JD3RMRC01TSE51062 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-MR-C-01-TSE | 1 | 2024-12-02 | 2024-12-03
| JD3RMRC01TSE51063 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-MR-C-01-TSE | 1 | 2024-12-04 | 2024-12-05
| JD3RMRC01TSE51064 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-MR-C-01-TSE | 1 | 2024-12-07 | 2024-12-08
| JD3RMRC01TSE51065 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-MR-C-01-TSE | 1 | 2024-12-09 | 2024-12-10
| JD3RMRC01TSE51066 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-MR-C-01-TSE | 1 | 2024-12-14 | 2024-12-15
| JD3RMRC01TSE51072 | Excavation Worksfor HDPE Pipes 315 mm - depth from 0 to 1.5 m- B4.33 31 00.03-MR-C-01-TSE | 1 | 2024-12-04 | 2024-12-05 | 2025-01-11 | 2025-01-28
| JD3RMRC01TSE51073 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 0 to 1.5 m- B4.33 31 00.03-MR-C-01-TSE | 1 | 2024-12-07 | 2024-12-08 | 2025-01-15 | 2025-02-02
| JD3RMRC01TSE51074 | Installing for HDPE Pipes 315 mm - depth from 0 to 1.5 m- B4.33 31 00.03-MR-C-01-TSE | 1 | 2024-12-09 | 2024-12-10 | 2025-02-20 | 2025-03-10
| JD3RMRC01TSE51075 | Testing for HDPE Pipes 315 mm - depth from 0 to 1.5 m- B4.33 31 00.03-MR-C-01-TSE | 1 | 2024-12-11 | 2024-12-12 | 2025-03-26 | 2025-04-13
| JD3RMRC01TSE51076 | Backfillingfor HDPE Pipes 315 mm - depth from 0 to 1.5 m- B4.33 31 00.03-MR-C-01-TSE | 1 | 2024-12-14 | 2024-12-15 | 2025-04-20 | 2025-05-07
| JD3RMRC01TSE51187 | Installationfor gate valves 100 mm - - B4.33 14 19.01-MR-C-01-TSE | 1 | 2024-12-09 | 2024-12-10
| JD3RMRC01TSE51188 | Testing And Commtionningfor gate valves 100 mm - - B4.33 14 19.01-MR-C-01-TSE | 1 | 2024-12-11 | 2024-12-12
| JD3RMRC02ST100 | Channel excavation for Swales-B6.31 22 00.13-MR-C-02-ST | 1 | 2024-12-22 | 2024-12-23 | 2025-06-21 | 2025-07-08
| JD3RMRC02ST100.R | Channel excavation for Swales-B6.31 22 00.13-MR-C-02-ST -Remaining | 1 | 2024-12-25 | 2025-01-11 | 2025-08-06
| JD3RMRC02ST300 | Riprap with side slopes 1.5:1 for Swales-NB6.31 22 00.16-MR-C-02-ST | 1 | 2025-01-12 | 2025-01-28 | 2025-08-16
| JD3RMRC02ST51604 | Excavation Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-C-02-ST | 1 | 2025-01-29 | 2025-01-30 | 2025-08-04 | 2025-08-16
| JD3RMRC02ST51605 | Soil Replacement and Bedding Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-C-02-ST | 1 | 2025-02-01 | 2025-02-02 | 2025-08-06 | 2025-08-16
| JD3RMRC02ST51606 | Installing for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-C-02-ST | 1 | 2025-02-03 | 2025-02-04 | 2025-08-12 | 2025-08-18
| JD3RMRC02ST51607 | Primary Test for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-C-02-ST | 1 | 2025-02-05 | 2025-02-06 | 2025-08-14 | 2025-08-19
| JD3RMRC02ST51608 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-C-02-ST | 1 | 2025-02-08 | 2025-02-09 | 2025-08-16 | 2025-08-23
| JD3RMRC02ST51707 | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-MR-C-02-ST | 1 | 2025-02-01 | 2025-02-02 | 2025-08-04 | 2025-08-16
| JD3RMRC02ST51708 | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-MR-C-02-ST | 1 | 2025-02-03 | 2025-02-04 | 2025-08-12 | 2025-08-18
| JD3RMRC02ST51709 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-MR-C-02-ST | 1 | 2025-02-05 | 2025-02-06
| JD3RMRC02ST51710 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-MR-C-02-ST | 1 | 2025-02-08 | 2025-02-09
| JD3RMRC02ST51711 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-MR-C-02-ST | 1 | 2025-02-10 | 2025-02-11
| JD3RMRC02TSE51775 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-MR-C-02-TSE | 1 | 2025-02-12 | 2025-02-13
| JD3RMRC02TSE51776 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-MR-C-02-TSE | 1 | 2025-02-15 | 2025-02-16
| JD3RMRC02TSE51777 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-MR-C-02-TSE | 1 | 2025-02-17 | 2025-02-18
| JD3RMRC02TSE51778 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-MR-C-02-TSE | 1 | 2025-02-19 | 2025-02-20
| JD3RMRC02TSE51779 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-MR-C-02-TSE | 1 | 2025-03-03 | 2025-03-04
| JD3RMRC02TSE51780 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-MR-C-02-TSE | 1 | 2025-02-12 | 2025-02-13
| JD3RMRC02TSE51781 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-MR-C-02-TSE | 1 | 2025-02-15 | 2025-02-16
| JD3RMRC02TSE51782 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-MR-C-02-TSE | 1 | 2025-02-17 | 2025-02-18
| JD3RMRC02TSE51783 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-MR-C-02-TSE | 1 | 2025-02-19 | 2025-02-20
| JD3RMRC02TSE51784 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-MR-C-02-TSE | 1 | 2025-03-03 | 2025-03-04
| JD3RMRC02TSE51815 | Excavation Worksfor HDPE Pipes 450 mm - depth from 0 to 1.5 m- B4.33 31 00.09-MR-C-02-TSE | 1 | 2025-02-12 | 2025-02-15 | 2025-08-11
| JD3RMRC02TSE51816 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 0 to 1.5 m- B4.33 31 00.09-MR-C-02-TSE | 1 | 2025-02-16 | 2025-02-18 | 2025-08-16
| JD3RMRC02TSE51817 | Installing for HDPE Pipes 450 mm - depth from 0 to 1.5 m- B4.33 31 00.09-MR-C-02-TSE | 1 | 2025-02-19 | 2025-02-25 | 2025-08-18
| JD3RMRC02TSE51818 | Testing for HDPE Pipes 450 mm - depth from 0 to 1.5 m- B4.33 31 00.09-MR-C-02-TSE | 1 | 2025-02-26 | 2025-03-02 | 2025-09-16
| JD3RMRC02TSE51819 | Backfillingfor HDPE Pipes 450 mm - depth from 0 to 1.5 m- B4.33 31 00.09-MR-C-02-TSE | 1 | 2025-03-03 | 2025-03-06 | 2025-08-26
| JD3RMRC02TSE51850 | Excavation Worksfor HDPE Pipes 630 mm - depth from 1.51 to 2.5 m- B4.33 31 00.16-MR-C-02-TSE | 1 | 2025-02-12 | 2025-02-13
| JD3RMRC02TSE51851 | Soil Replacement and Bedding Works for HDPE Pipes 630 mm - depth from 1.51 to 2.5 m- B4.33 31 00.16-MR-C-02-TSE | 1 | 2025-02-15 | 2025-02-16
| JD3RMRC02TSE51852 | Installing for HDPE Pipes 630 mm - depth from 1.51 to 2.5 m- B4.33 31 00.16-MR-C-02-TSE | 1 | 2025-02-17 | 2025-02-18
| JD3RMRC02TSE51853 | Testing for HDPE Pipes 630 mm - depth from 1.51 to 2.5 m- B4.33 31 00.16-MR-C-02-TSE | 1 | 2025-02-19 | 2025-02-20
| JD3RMRC02TSE51854 | Backfillingfor HDPE Pipes 630 mm - depth from 1.51 to 2.5 m- B4.33 31 00.16-MR-C-02-TSE | 1 | 2025-03-03 | 2025-03-04
| JD3RMRC02TSE51855 | Excavation Worksfor HDPE Pipes 630 mm - depth from 2.51 to 3.5 m- B4.33 31 00.17-MR-C-02-TSE | 1 | 2025-02-12 | 2025-02-13
| JD3RMRC02TSE51856 | Soil Replacement and Bedding Works for HDPE Pipes 630 mm - depth from 2.51 to 3.5 m- B4.33 31 00.17-MR-C-02-TSE | 1 | 2025-02-15 | 2025-02-16
| JD3RMRC02TSE51857 | Installing for HDPE Pipes 630 mm - depth from 2.51 to 3.5 m- B4.33 31 00.17-MR-C-02-TSE | 1 | 2025-02-17 | 2025-02-18
| JD3RMRC02TSE51858 | Testing for HDPE Pipes 630 mm - depth from 2.51 to 3.5 m- B4.33 31 00.17-MR-C-02-TSE | 1 | 2025-02-19 | 2025-02-20
| JD3RMRC02TSE51859 | Backfillingfor HDPE Pipes 630 mm - depth from 2.51 to 3.5 m- B4.33 31 00.17-MR-C-02-TSE | 1 | 2025-03-03 | 2025-03-04
| JD3RMRC02TSE51900 | Installationfor gate valves 100 mm - - B4.33 14 19.01-MR-C-02-TSE | 1 | 2025-02-26 | 2025-02-27
| JD3RMRC02TSE51901 | Testing And Commtionningfor gate valves 100 mm - - B4.33 14 19.01-MR-C-02-TSE | 1 | 2025-03-01 | 2025-03-02
| JD3RMRC02TSE51902 | Installationfor gate valves 250 mm - - B4.33 14 19.02-MR-C-02-TSE | 1 | 2025-02-26 | 2025-02-27
| JD3RMRC02TSE51903 | Testing And Commtionningfor gate valves 250 mm - - B4.33 14 19.02-MR-C-02-TSE | 1 | 2025-03-01 | 2025-03-02
| JD3RMRC02TSE51906 | Installationfor butterfly valves 400 mm. - - B4.33 14 19.04-MR-C-02-TSE | 1 | 2025-02-26 | 2025-02-27
| JD3RMRC02TSE51907 | Testing And Commtionningfor butterfly valves 400 mm. - - B4.33 14 19.04-MR-C-02-TSE | 1 | 2025-03-01 | 2025-03-02
| JD3RMRC02TSE51920 | Installationfor Air valves 65 mm. - on pipes with diameter 355-630 mm- B4.33 14 19.16-MR-C-02-TSE | 1 | 2025-02-26 | 2025-02-27
| JD3RMRC02TSE51921 | Testing And Commtionningfor Air valves 65 mm. - on pipes with diameter 355-630 mm- B4.33 14 19.16-MR-C-02-TSE | 1 | 2025-03-01 | 2025-03-02
| JD3RMRC02TSE51924 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-MR-C-02-TSE | 1 | 2025-02-12 | 2025-02-13
| JD3RMRC02TSE51925 | Plain Concrete Worksfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-MR-C-02-TSE | 1 | 2025-02-15 | 2025-02-16
| JD3RMRC02TSE51926 | INSTALLATIONfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-MR-C-02-TSE | 1 | 2025-02-17 | 2025-02-18
| JD3RMRC02TSE51927 | Backfilling Worksfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-MR-C-02-TSE | 1 | 2025-02-19 | 2025-02-20
| JD3RMRC02TSE51952 | EXCAVATION and Bedding Worksfor Air Valve Chamber - on 355-630 mm - B4.33 14 13.11-MR-C-02-TSE | 1 | 2025-02-12 | 2025-02-13
| JD3RMRC02TSE51953 | Plain Concrete Worksfor Air Valve Chamber - on 355-630 mm - B4.33 14 13.11-MR-C-02-TSE | 1 | 2025-02-15 | 2025-02-16
| JD3RMRC02TSE51954 | INSTALLATIONfor Air Valve Chamber - on 355-630 mm - B4.33 14 13.11-MR-C-02-TSE | 1 | 2025-02-17 | 2025-02-18
| JD3RMRC02TSE51955 | Backfilling Worksfor Air Valve Chamber - on 355-630 mm - B4.33 14 13.11-MR-C-02-TSE | 1 | 2025-02-19 | 2025-02-20
| JD3RMRC03SS52086 | Trench excavation for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-MR-C-03-SS | 1 | 2025-05-13 | 2025-05-15 | 2025-01-18 | 2025-05-18
| JD3RMRC03SS52087 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-MR-C-03-SS | 1 | 2025-05-17 | 2025-05-19 | 2025-01-20 | 2025-06-17
| JD3RMRC03SS52088 | Installing for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-MR-C-03-SS | 1 | 2025-05-20 | 2025-05-24 | 2025-03-10 | 2025-06-29
| JD3RMRC03SS52089 | Primary Test for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-MR-C-03-SS | 1 | 2025-05-25 | 2025-05-27 | 2025-03-29 | 2025-07-17
| JD3RMRC03SS52090 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-MR-C-03-SS | 1 | 2025-05-28 | 2025-06-01 | 2025-04-02 | 2025-07-31
| JD3RMRC03SS52091 | Trench excavation for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-MR-C-03-SS | 1 | 2025-05-13 | 2025-05-14 | 2025-01-21 | 2025-03-08
| JD3RMRC03SS52092 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-MR-C-03-SS | 1 | 2025-05-15 | 2025-05-17 | 2025-01-23 | 2025-03-10
| JD3RMRC03SS52093 | Installing for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-MR-C-03-SS | 1 | 2025-05-18 | 2025-05-19 | 2025-01-25 | 2025-03-02
| JD3RMRC03SS52094 | Primary Test for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-MR-C-03-SS | 1 | 2025-05-20 | 2025-05-21 | 2025-01-27 | 2025-03-04
| JD3RMRC03SS52095 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-MR-C-03-SS | 1 | 2025-05-22 | 2025-05-24 | 2025-03-05 | 2025-04-20
| JD3RMRC03SS52140 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2025-05-13 | 2025-05-14 | 2025-01-21 | 2025-03-08
| JD3RMRC03SS521401 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2025-05-13 | 2025-05-14 | 2025-08-01 | 2025-08-03
| JD3RMRC03SS52141 | Installation of Base Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2025-05-15 | 2025-05-18 | 2025-01-22 | 2025-05-13
| JD3RMRC03SS521411 | Installation of Base Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2025-05-15 | 2025-05-17 | 2025-08-04 | 2025-08-05
| JD3RMRC03SS52142 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-MR-C-03 | 1 | 2025-05-19 | 2025-05-21 | 2025-04-13 | 2025-07-31
| JD3RMRC03SS521421 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03 | 1 | 2025-05-18 | 2025-05-19
| JD3RMRC03SS52143 | Backfilling Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2025-05-22 | 2025-05-24
| JD3RMRC03SS521431 | Backfilling Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2025-05-20 | 2025-05-21
| JD3RMRC03SS52144 | Finishing, Benching Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2025-05-25 | 2025-05-26
| JD3RMRC03SS521441 | Finishing, Benching Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2025-05-22 | 2025-05-24
| JD3RMRC03ST100 | Channel excavation for Swales-B6.31 22 00.13-MR-C-03-ST | 1 | 2025-05-25 | 2025-06-16 | 2025-04-08 | 2025-07-31
| JD3RMRC03ST100.R | Channel excavation for Swales-B6.31 22 00.13-MR-C-03-ST -Remaining | 1 | 2025-06-17 | 2025-07-02 | 2025-08-17
| JD3RMRC03ST100.R1 | Channel excavation for Swales-B6.31 22 00.13-MR-C-03-ST -Remaining | 1 | 2025-07-03 | 2025-07-19
| JD3RMRC03ST300 | Riprap with side slopes 1.5:1 for Swales-NB6.31 22 00.16-MR-C-03-ST | 1 | 2025-07-20 | 2025-08-06 | 2025-04-20 | 2025-07-31
| JD3RMRC03ST301 | Riprap with side slopes 1.5:1 for Swales-NB6.31 22 00.16-MR-C-03-ST | 1 | 2025-08-07 | 2025-08-30 | 2025-06-25 | 2025-07-31
| JD3RMRC03ST301.R | Riprap with side slopes 1.5:1 for Swales-NB6.31 22 00.16-MR-C-03-ST -Remaining | 1 | 2025-08-31 | 2025-09-14
| JD3RMRC03ST302 | Riprap with side slopes 1.5:1 for Swales-NB6.31 22 00.16-MR-C-03-ST | 1 | 2025-09-15 | 2025-10-02 | 2025-08-17
| JD3RMRC03ST52212 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-MR-C-03-ST | 1 | 2025-06-02 | 2025-06-03
| JD3RMRC03ST52213 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-MR-C-03-ST | 1 | 2025-06-04 | 2025-06-05
| JD3RMRC03ST52214 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-MR-C-03-ST | 1 | 2025-06-07 | 2025-06-08
| JD3RMRC03ST52215 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-MR-C-03-ST | 1 | 2025-06-09 | 2025-06-10
| JD3RMRC03ST52216 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-MR-C-03-ST | 1 | 2025-06-11 | 2025-06-12
| JD3RMRC03ST52242 | Excavation Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-MR-C-03-ST | 1 | 2025-06-02 | 2025-06-03
| JD3RMRC03ST52243 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-MR-C-03-ST | 1 | 2025-06-04 | 2025-06-05
| JD3RMRC03ST52244 | Installing for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-MR-C-03-ST | 1 | 2025-06-07 | 2025-06-08
| JD3RMRC03ST52245 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-MR-C-03-ST | 1 | 2025-06-09 | 2025-06-10
| JD3RMRC03ST52246 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-MR-C-03-ST | 1 | 2025-06-16 | 2025-06-17
| JD3RMRC03ST52317 | Excavation Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-C-03-ST | 1 | 2025-06-02 | 2025-06-03
| JD3RMRC03ST52318 | Soil Replacement and Bedding Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-C-03-ST | 1 | 2025-06-04 | 2025-06-05
| JD3RMRC03ST52319 | Installing for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-C-03-ST | 1 | 2025-06-07 | 2025-06-08
| JD3RMRC03ST52320 | Primary Test for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-C-03-ST | 1 | 2025-06-09 | 2025-06-10
| JD3RMRC03ST52321 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-C-03-ST | 1 | 2025-06-16 | 2025-06-17
| JD3RMRC03ST52405 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-MR-C-03-ST | 1 | 2025-06-02 | 2025-06-03
| JD3RMRC03ST52406 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-MR-C-03-ST | 1 | 2025-06-04 | 2025-06-05
| JD3RMRC03ST52407 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-MR-C-03-ST | 1 | 2025-06-07 | 2025-06-08
| JD3RMRC03ST52408 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-MR-C-03-ST | 1 | 2025-06-09 | 2025-06-10
| JD3RMRC03ST52409 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-MR-C-03-ST | 1 | 2025-06-11 | 2025-06-12
| JD3RMRC03ST52410 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-MR-C-03-ST | 1 | 2025-06-02 | 2025-06-03
| JD3RMRC03ST52411 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-MR-C-03-ST | 1 | 2025-06-04 | 2025-06-05
| JD3RMRC03ST52412 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-MR-C-03-ST | 1 | 2025-06-07 | 2025-06-08
| JD3RMRC03ST52413 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-MR-C-03-ST | 1 | 2025-06-09 | 2025-06-10
| JD3RMRC03ST52414 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-MR-C-03-ST | 1 | 2025-06-11 | 2025-06-12
| JD3RMRC03ST52420 | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-MR-C-03-ST | 1 | 2025-06-02 | 2025-06-03
| JD3RMRC03ST52421 | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-MR-C-03-ST | 1 | 2025-06-04 | 2025-06-05
| JD3RMRC03ST52422 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-MR-C-03-ST | 1 | 2025-06-07 | 2025-06-08
| JD3RMRC03ST52423 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-MR-C-03-ST | 1 | 2025-06-09 | 2025-06-10
| JD3RMRC03ST52424 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-MR-C-03-ST | 1 | 2025-06-11 | 2025-06-12
| JD3RMRC03ST52430 | EXCAVATION Works for Catchbasine single - - B6.33 05 39.09-MR-C-03-ST | 1 | 2025-06-02 | 2025-06-03
| JD3RMRC03ST52431 | Catchbasine Installation Works For Catchbasine single - - B6.33 05 39.09-MR-C-03-ST | 1 | 2025-06-04 | 2025-06-05
| JD3RMRC03ST52432 | FINISHING Works For Catchbasine single - - B6.33 05 39.09-MR-C-03-ST | 1 | 2025-06-07 | 2025-06-08
| JD3RMRC03ST52433 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - - B6.33 05 39.09-MR-C-03-ST | 1 | 2025-06-09 | 2025-06-10
| JD3RMRC03ST524341 | Concrete encasement for pipes- NNB6.33 42 11.25-MR-C-03-ST | 1 | 2025-06-09 | 2025-06-15
| JD3RMRC03TSE52488 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-MR-C-03-TSE | 1 | 2025-06-04 | 2025-06-09 | 2025-08-11
| JD3RMRC03TSE52489 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-MR-C-03-TSE | 1 | 2025-06-10 | 2025-06-16 | 2025-08-17
| JD3RMRC03TSE52490 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-MR-C-03-TSE | 1 | 2025-06-17 | 2025-06-28 | 2025-08-24
| JD3RMRC03TSE52491 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-MR-C-03-TSE | 1 | 2025-06-29 | 2025-07-06 | 2025-09-16
| JD3RMRC03TSE52492 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-MR-C-03-TSE | 1 | 2025-07-07 | 2025-07-14 | 2025-08-12
| JD3RMRC03TSE52493 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-MR-C-03-TSE | 1 | 2025-07-15 | 2025-07-31 | 2025-08-21
| JD3RMRC03TSE52494 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-MR-C-03-TSE | 1 | 2025-08-02 | 2025-08-19 | 2025-08-28
| JD3RMRC03TSE52495 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-MR-C-03-TSE | 1 | 2025-08-20 | 2025-09-06 | 2025-08-31
| JD3RMRC03TSE52496 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-MR-C-03-TSE | 1 | 2025-09-07 | 2025-09-28
| JD3RMRC03TSE52497 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-MR-C-03-TSE | 1 | 2025-09-29 | 2025-10-20 | 2025-09-02
| JD3RMRC03TSE52498 | Excavation Worksfor HDPE Pipes 315 mm - depth from 0 to 1.5 m- B4.33 31 00.03-MR-C-03-TSE | 1 | 2025-08-02 | 2025-08-03
| JD3RMRC03TSE52499 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 0 to 1.5 m- B4.33 31 00.03-MR-C-03-TSE | 1 | 2025-08-04 | 2025-08-05
| JD3RMRC03TSE52500 | Installing for HDPE Pipes 315 mm - depth from 0 to 1.5 m- B4.33 31 00.03-MR-C-03-TSE | 1 | 2025-08-06 | 2025-08-07
| JD3RMRC03TSE52501 | Testing for HDPE Pipes 315 mm - depth from 0 to 1.5 m- B4.33 31 00.03-MR-C-03-TSE | 1 | 2025-08-09 | 2025-08-10
| JD3RMRC03TSE52502 | Backfillingfor HDPE Pipes 315 mm - depth from 0 to 1.5 m- B4.33 31 00.03-MR-C-03-TSE | 1 | 2025-08-11 | 2025-08-12
| JD3RMRC03TSE52528 | Excavation Worksfor HDPE Pipes 450 mm - depth from 0 to 1.5 m- B4.33 31 00.09-MR-C-03-TSE | 1 | 2025-08-04 | 2025-08-05
| JD3RMRC03TSE52529 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 0 to 1.5 m- B4.33 31 00.09-MR-C-03-TSE | 1 | 2025-08-06 | 2025-08-07
| JD3RMRC03TSE52530 | Installing for HDPE Pipes 450 mm - depth from 0 to 1.5 m- B4.33 31 00.09-MR-C-03-TSE | 1 | 2025-08-09 | 2025-08-10
| JD3RMRC03TSE52531 | Testing for HDPE Pipes 450 mm - depth from 0 to 1.5 m- B4.33 31 00.09-MR-C-03-TSE | 1 | 2025-08-11 | 2025-08-12
| JD3RMRC03TSE52532 | Backfillingfor HDPE Pipes 450 mm - depth from 0 to 1.5 m- B4.33 31 00.09-MR-C-03-TSE | 1 | 2025-08-13 | 2025-08-14
| JD3RMRC03TSE52578 | Excavation Worksfor GRP Pipes 800 mm - depth from 0 to 1.5 m- B4.33 05 36.01-MR-C-03-TSE | 1 | 2025-08-06 | 2025-08-07
| JD3RMRC03TSE52579 | Soil Replacement and Bedding Works for GRP Pipes 800 mm - depth from 0 to 1.5 m- B4.33 05 36.01-MR-C-03-TSE | 1 | 2025-08-09 | 2025-08-10
| JD3RMRC03TSE52580 | Installing for GRP Pipes 800 mm - depth from 0 to 1.5 m- B4.33 05 36.01-MR-C-03-TSE | 1 | 2025-08-11 | 2025-08-12
| JD3RMRC03TSE52581 | Testing for GRP Pipes 800 mm - depth from 0 to 1.5 m- B4.33 05 36.01-MR-C-03-TSE | 1 | 2025-08-13 | 2025-08-14
| JD3RMRC03TSE52582 | Backfillingfor GRP Pipes 800 mm - depth from 0 to 1.5 m- B4.33 05 36.01-MR-C-03-TSE | 1 | 2025-08-23 | 2025-08-24
| JD3RMRC03TSE52583 | Excavation Worksfor GRP Pipes 800 mm - depth from 1.51 to 2.5 m- B4.33 05 36.02-MR-C-03-TSE | 1 | 2025-08-09 | 2025-08-10
| JD3RMRC03TSE52584 | Soil Replacement and Bedding Works for GRP Pipes 800 mm - depth from 1.51 to 2.5 m- B4.33 05 36.02-MR-C-03-TSE | 1 | 2025-08-11 | 2025-08-12
| JD3RMRC03TSE52585 | Installing for GRP Pipes 800 mm - depth from 1.51 to 2.5 m- B4.33 05 36.02-MR-C-03-TSE | 1 | 2025-08-13 | 2025-08-14
| JD3RMRC03TSE52586 | Testing for GRP Pipes 800 mm - depth from 1.51 to 2.5 m- B4.33 05 36.02-MR-C-03-TSE | 1 | 2025-08-16 | 2025-08-17
| JD3RMRC03TSE52587 | Backfillingfor GRP Pipes 800 mm - depth from 1.51 to 2.5 m- B4.33 05 36.02-MR-C-03-TSE | 1 | 2025-08-23 | 2025-08-24
| JD3RMRC03TSE52588 | Excavation Worksfor GRP Pipes 800 mm - depth from 2.51 to 3.5 m- B4.33 05 36.03-MR-C-03-TSE | 1 | 2025-08-11 | 2025-08-12
| JD3RMRC03TSE52589 | Soil Replacement and Bedding Works for GRP Pipes 800 mm - depth from 2.51 to 3.5 m- B4.33 05 36.03-MR-C-03-TSE | 1 | 2025-08-13 | 2025-08-14
| JD3RMRC03TSE52590 | Installing for GRP Pipes 800 mm - depth from 2.51 to 3.5 m- B4.33 05 36.03-MR-C-03-TSE | 1 | 2025-08-16 | 2025-08-17
| JD3RMRC03TSE52591 | Testing for GRP Pipes 800 mm - depth from 2.51 to 3.5 m- B4.33 05 36.03-MR-C-03-TSE | 1 | 2025-08-18 | 2025-08-19
| JD3RMRC03TSE52592 | Backfillingfor GRP Pipes 800 mm - depth from 2.51 to 3.5 m- B4.33 05 36.03-MR-C-03-TSE | 1 | 2025-08-23 | 2025-08-24
| JD3RMRC03TSE52613 | Installationfor gate valves 100 mm - - B4.33 14 19.01-MR-C-03-TSE | 1 | 2025-08-11 | 2025-08-16
| JD3RMRC03TSE52614 | Testing And Commtionningfor gate valves 100 mm - - B4.33 14 19.01-MR-C-03-TSE | 1 | 2025-08-17 | 2025-08-21
| JD3RMRC03TSE52615 | Installationfor gate valves 250 mm - - B4.33 14 19.02-MR-C-03-TSE | 1 | 2025-08-11 | 2025-08-13
| JD3RMRC03TSE52616 | Testing And Commtionningfor gate valves 250 mm - - B4.33 14 19.02-MR-C-03-TSE | 1 | 2025-08-14 | 2025-08-17
| JD3RMRC03TSE52623 | Installationfor butterfly valves 800 mm. - - B4.33 14 19.06-MR-C-03-TSE | 1 | 2025-08-11 | 2025-08-12
| JD3RMRC03TSE52624 | Testing And Commtionningfor butterfly valves 800 mm. - - B4.33 14 19.06-MR-C-03-TSE | 1 | 2025-08-13 | 2025-08-14
| JD3RMRC03TSE52629 | Installationfor Wash-Out valves 200 mm. - on pipes with diameter 700-1200 mm- B4.33 14 19.09-MR-C-03-TSE | 1 | 2025-08-11 | 2025-08-12
| JD3RMRC03TSE52630 | Testing And Commtionningfor Wash-Out valves 200 mm. - on pipes with diameter 700-1200 mm- B4.33 14 19.09-MR-C-03-TSE | 1 | 2025-08-13 | 2025-08-14
| JD3RMRC03TSE52631 | Installationfor Air valves 50 mm. - on pipes with diameter less than 315 mm- B4.33 14 19.15-MR-C-03-TSE | 1 | 2025-08-11 | 2025-08-12
| JD3RMRC03TSE52632 | Testing And Commtionningfor Air valves 50 mm. - on pipes with diameter less than 315 mm- B4.33 14 19.15-MR-C-03-TSE | 1 | 2025-08-13 | 2025-08-14
| JD3RMRC03TSE52645 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 700 to 1000 MM- B4.33 14 13.03-MR-C-03-TSE | 1 | 2025-08-13 | 2025-08-14
| JD3RMRC03TSE52646 | Plain Concrete Worksfor R.C Valve Chamber - 700 to 1000 MM- B4.33 14 13.03-MR-C-03-TSE | 1 | 2025-08-16 | 2025-08-17
| JD3RMRC03TSE52647 | INSTALLATIONfor R.C Valve Chamber - 700 to 1000 MM- B4.33 14 13.03-MR-C-03-TSE | 1 | 2025-08-18 | 2025-08-19
| JD3RMRC03TSE52648 | Backfilling Worksfor R.C Valve Chamber - 700 to 1000 MM- B4.33 14 13.03-MR-C-03-TSE | 1 | 2025-08-23 | 2025-08-24
| JD3RMRC03TSE52657 | EXCAVATION and Bedding Worksfor Wash-out Valve Chamber - 700 to 1200 MM- B4.33 14 13.08-MR-C-03-TSE | 1 | 2025-08-16 | 2025-08-17
| JD3RMRC03TSE52658 | Plain Concrete Worksfor Wash-out Valve Chamber - 700 to 1200 MM- B4.33 14 13.08-MR-C-03-TSE | 1 | 2025-08-18 | 2025-08-19
| JD3RMRC03TSE52659 | INSTALLATIONfor Wash-out Valve Chamber - 700 to 1200 MM- B4.33 14 13.08-MR-C-03-TSE | 1 | 2025-08-20 | 2025-08-21
| JD3RMRC03TSE52660 | Backfilling Worksfor Wash-out Valve Chamber - 700 to 1200 MM- B4.33 14 13.08-MR-C-03-TSE | 1 | 2025-08-23 | 2025-08-24
| JD3RMRC03TSE52661 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm- B4.33 14 13.10-MR-C-03-TSE | 1 | 2025-08-18 | 2025-08-19
| JD3RMRC03TSE52662 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm- B4.33 14 13.10-MR-C-03-TSE | 1 | 2025-08-20 | 2025-08-21
| JD3RMRC03TSE52663 | INSTALLATIONfor Air Valve Chamber - less than 315 mm- B4.33 14 13.10-MR-C-03-TSE | 1 | 2025-08-23 | 2025-08-24
| JD3RMRC03TSE52664 | Backfilling Worksfor Air Valve Chamber - less than 315 mm- B4.33 14 13.10-MR-C-03-TSE | 1 | 2025-08-25 | 2025-08-26
| JD3RMRC05ST100 | Channel excavation for Swales-B6.31 22 00.13-MR-C-05-ST | 1 | 2025-09-04 | 2025-09-23 | 2025-04-10
| JD3RMRC05ST100.R | Channel excavation for Swales-B6.31 22 00.13-MR-C-05-ST -Remaining | 1 | 2025-09-24 | 2025-10-06
| JD3RMRC05ST53040 | Excavation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.01-MR-C-05-ST | 1 | 2025-09-04 | 2025-09-06
| JD3RMRC05ST53041 | Plain Concrete Works For Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.01-MR-C-05-ST | 1 | 2025-09-07 | 2025-09-08
| JD3RMRC05ST53042 | Raft Foundation for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.01-MR-C-05-ST | 1 | 2025-09-09 | 2025-09-13
| JD3RMRC05ST53043 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.01-MR-C-05-ST | 1 | 2025-09-14 | 2025-09-20
| JD3RMRC05ST53044 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.01-MR-C-05-ST | 1 | 2025-09-21 | 2025-09-27
| JD3RMRC05ST53045 | Isolation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.01-MR-C-05-ST | 1 | 2025-09-28 | 2025-09-29
| JD3RMRC05ST53046 | Backfilling Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.01-MR-C-05-ST | 1 | 2025-09-30 | 2025-10-01
| JD3RMRC05ST53054 | Excavation Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - - B6.34 42 16.03-MR-C-05-ST | 1 | 2025-09-07 | 2025-09-09
| JD3RMRC05ST53055 | Plain Concrete Works For Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - - B6.34 42 16.03-MR-C-05-ST | 1 | 2025-09-10 | 2025-09-11
| JD3RMRC05ST53056 | Raft Foundation for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - - B6.34 42 16.03-MR-C-05-ST | 1 | 2025-09-13 | 2025-09-23
| JD3RMRC05ST53057 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.34 42 16.03-MR-C-05-ST | 1 | 2025-09-24 | 2025-10-11
| JD3RMRC05ST53061 | Excavation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-MR-C-05-ST | 1 | 2025-09-10 | 2025-09-13
| JD3RMRC05ST53062 | Plain Concrete Works For Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-MR-C-05-ST | 1 | 2025-09-14 | 2025-09-15
| JD3RMRC05ST53063 | Raft Foundation for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-MR-C-05-ST | 1 | 2025-09-16 | 2025-09-27
| JD3RMRC05ST53064 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-MR-C-05-ST | 1 | 2025-09-28 | 2025-10-14
| JD3RMRC05ST53068 | Excavation Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - - B6.34 42 16.05-MR-C-05-ST | 1 | 2025-09-14 | 2025-09-15
| JD3RMRC05ST53069 | Plain Concrete Works For Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - - B6.34 42 16.05-MR-C-05-ST | 1 | 2025-09-16 | 2025-09-17
| JD3RMRC05ST53070 | Raft Foundation for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - - B6.34 42 16.05-MR-C-05-ST | 1 | 2025-09-18 | 2025-09-20
| JD3RMRC05ST53071 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.34 42 16.05-MR-C-05-ST | 1 | 2025-09-21 | 2025-09-22
| JD3RMRC05ST53072 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.34 42 16.05-MR-C-05-ST | 1 | 2025-09-23 | 2025-09-24
| JD3RMRC05ST53073 | Isolation Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - - B6.34 42 16.05-MR-C-05-ST | 1 | 2025-09-25 | 2025-09-27
| JD3RMRC05ST53074 | Backfilling Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - - B6.34 42 16.05-MR-C-05-ST | 1 | 2025-09-28 | 2025-09-29
| JD3RMRC05ST53075 | Excavation Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - - B6.34 42 16.06-MR-C-05-ST | 1 | 2025-09-30 | 2025-10-01
| JD3RMRC08ST100 | Channel excavation for Swales-B6.31 22 00.13-MR-C-08-ST | 1 | 2025-08-10 | 2025-08-28 | 2025-04-15 | 2025-07-31
| JD3RMRC08ST100.R | Channel excavation for Swales-B6.31 22 00.13-MR-C-08-ST -Remaining | 1 | 2025-08-30 | 2025-09-11 | 2025-08-17
| JD3RMRC08ST300 | Riprap with side slopes 1.5:1 for Swales-NB6.31 22 00.16-MR-C-08-ST | 1899-12-31 | 2025-09-13 | 2025-09-30 | 2025-05-26 | 2025-07-31
| JD3RMRC09RD56346 | Supply and installation Precast Concrete Kerb, Type K1-Dfor ROADS - - B1.32 14 13.01-MR-C-09-RD | 1 | 2024-11-23 | 2024-12-08 | 2025-01-11 | 2025-05-20
| JD3RMRC09RD56346.R | Supply and installation Precast Concrete Kerb, Type K1-Dfor ROADS - - B1.32 14 13.01-MR-C-09-RD -Remaining | 1 | 2024-12-09 | 2024-12-10
| JD3RMRC09RD56348 | Supply and installation Depressed curbs Type K2for ROADS - - B1.32 14 13.03-MR-C-09-RD | 1 | 2024-12-11 | 2024-12-12
| JD3RMRC09ST100 | Channel excavation for Swales-B6.31 22 00.13-MR-C-09-ST | 1 | 2024-09-10 | 2024-10-02 | 2025-04-15
| JD3RMRC09ST100.R | Channel excavation for Swales-B6.31 22 00.13-MR-C-09-ST -Remaining | 1 | 2024-10-03 | 2024-10-14
| JD3RMRC09ST300 | Riprap with side slopes 1.5:1 for Swales-NB6.31 22 00.16-MR-C-09-ST | 1 | 2024-10-03 | 2024-10-16 | 2025-06-21 | 2025-07-31
| JD3RMRC09ST300.R | Riprap with side slopes 1.5:1 for Swales-NB6.31 22 00.16-MR-C-09-ST -Remaining | 1 | 2024-10-17 | 2024-11-10 | 2025-08-13
| JD3RMRC09ST55882 | Excavation Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-C-09-ST | 1 | 2024-11-11 | 2024-11-12
| JD3RMRC09ST55883 | Soil Replacement and Bedding Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-C-09-ST | 1 | 2024-11-13 | 2024-11-14
| JD3RMRC09ST55884 | Installing for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-C-09-ST | 1 | 2024-11-16 | 2024-11-17
| JD3RMRC09ST55885 | Primary Test for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-C-09-ST | 1 | 2024-11-18 | 2024-11-19
| JD3RMRC09ST55886 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-C-09-ST | 1 | 2024-11-20 | 2024-11-21
| JD3RMRC10ST100 | Channel excavation for Swales-B6.31 22 00.13-MR-C-10-ST | 1 | 2024-12-22 | 2025-01-09 | 2025-04-10
| JD3RMRC10ST100.R | Channel excavation for Swales-B6.31 22 00.13-MR-C-10-ST -Remaining | 1899-12-31 | 2025-01-11 | 2025-01-26
| JD3RMRC10ST300 | Riprap with side slopes 1.5:1 for Swales-NB6.31 22 00.16-MR-C-10-ST | 1 | 2025-01-11 | 2025-02-02 | 2025-04-15
| JD3RMRC10ST300.R | Riprap with side slopes 1.5:1 for Swales-NB6.31 22 00.16-MR-C-10-ST -Remaining | 1 | 2025-02-03 | 2025-02-20
| JD3RMRC10ST56595 | Excavation Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-C-10-ST | 1 | 2025-04-10 | 2025-04-14 | 2025-08-11
| JD3RMRC10ST56596 | Soil Replacement and Bedding Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-C-10-ST | 1 | 2025-04-15 | 2025-04-19 | 2025-08-13
| JD3RMRC10ST56597 | Installing for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-C-10-ST | 1 | 2025-04-20 | 2025-04-23 | 2025-08-15
| JD3RMRC10ST56598 | Primary Test for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-C-10-ST | 1 | 2025-04-24 | 2025-04-28
| JD3RMRC10ST56599 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-C-10-ST | 1 | 2025-04-29 | 2025-05-04
| JD3RMRC10ST56633 | Excavation Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - - B6.34 42 16.05-MR-C-10-ST | 1 | 2025-02-24 | 2025-02-25
| JD3RMRC10ST56634 | Plain Concrete Works For Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - - B6.34 42 16.05-MR-C-10-ST | 1 | 2025-02-26 | 2025-02-27
| JD3RMRC10ST56635 | Raft Foundation for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - - B6.34 42 16.05-MR-C-10-ST | 1 | 2025-03-01 | 2025-03-08
| JD3RMRC10ST56636 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.34 42 16.05-MR-C-10-ST | 1 | 2025-03-09 | 2025-03-19
| JD3RMRC10ST56637 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.34 42 16.05-MR-C-10-ST | 1 | 2025-03-20 | 2025-03-31
| JD3RMRC10ST56638 | Isolation Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - - B6.34 42 16.05-MR-C-10-ST | 1 | 2025-04-01 | 2025-04-05
| JD3RMRC10ST56639 | Backfilling Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - - B6.34 42 16.05-MR-C-10-ST | 1899-12-31 | 2025-04-06 | 2025-04-07
| JD3RMRC10ST56640 | Excavation Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - - B6.34 42 16.06-MR-C-10-ST | 1 | 2025-02-22 | 2025-02-23
| JD3RMRC10ST56641 | Plain Concrete Works For Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - - B6.34 42 16.06-MR-C-10-ST | 1 | 2025-02-24 | 2025-02-25
| JD3RMRC10ST56642 | Raft Foundation for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - - B6.34 42 16.06-MR-C-10-ST | 1 | 2025-02-26 | 2025-03-05
| JD3RMRC10ST56643 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.34 42 16.06-MR-C-10-ST | 1 | 2025-03-06 | 2025-03-17
| JD3RMRC10ST56644 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.34 42 16.06-MR-C-10-ST | 1 | 2025-03-18 | 2025-03-29
| JD3RMRC10ST56645 | Isolation Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - - B6.34 42 16.06-MR-C-10-ST | 1 | 2025-03-30 | 2025-04-02
| JD3RMRC10ST56646 | Backfilling Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - - B6.34 42 16.06-MR-C-10-ST | 1 | 2025-04-03 | 2025-04-05
| JD3RMRC10ST56688 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-MR-C-10-ST | 1 | 2025-04-08 | 2025-04-09
| JD3RMRC10ST56689 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-MR-C-10-ST | 1 | 2025-04-10 | 2025-04-12
| JD3RMRC10ST56690 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-MR-C-10-ST | 1 | 2025-04-13 | 2025-04-14
| JD3RMRC10ST56691 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-MR-C-10-ST | 1 | 2025-04-15 | 2025-04-16
| JD3RMRC10ST56692 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-MR-C-10-ST | 1 | 2025-04-17 | 2025-04-19
| JD3RMRC10ST56698 | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-MR-C-10-ST | 1 | 2025-04-10 | 2025-04-12 | 2025-08-11
| JD3RMRC10ST56699 | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-MR-C-10-ST | 1 | 2025-04-13 | 2025-04-14 | 2025-08-15
| JD3RMRC10ST56700 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-MR-C-10-ST | 1 | 2025-04-15 | 2025-04-16
| JD3RMRC10ST56701 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-MR-C-10-ST | 1 | 2025-04-17 | 2025-04-19
| JD3RMRC10ST56702 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-MR-C-10-ST | 1899-12-31 | 2025-04-20 | 2025-04-21
| JD3RMRC11ST100 | Channel excavation for Swales-B6.31 22 00.13-MR-C-11-ST | 1 | 2025-08-18 | 2025-09-08 | 2025-06-15 | 2025-07-31
| JD3RMRC11ST100.R | Channel excavation for Swales-B6.31 22 00.13-MR-C-11-ST -Remaining | 1 | 2025-09-09 | 2025-10-02 | 2025-08-19
| JD3RMRC13ST100 | Channel excavation for Swales-B6.31 22 00.13-MR-C-13-ST | 1 | 2025-08-26 | 2025-09-17 | 2025-04-15 | 2025-07-31
| JD3RMRC13ST100.R | Channel excavation for Swales-B6.31 22 00.13-MR-C-13-ST -Remaining | 1 | 2025-09-18 | 2025-10-06
| JD3RMRL03SS61350 | Trench excavation for GRP Pipe Line 200 mm - depth from 0.00 to 1.50- B5.33 31 00.03-MR-L-03-SS | 1 | 2025-09-03 | 2025-09-04
| JD3RMRL03SS61351 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - depth from 0.00 to 1.50- B5.33 31 00.03-MR-L-03-SS | 1899-12-31 | 2025-09-06 | 2025-09-07
| JD3RMRL03SS61352 | Installing for GRP Pipe Line 200 mm - depth from 0.00 to 1.50- B5.33 31 00.03-MR-L-03-SS | 1 | 2025-09-08 | 2025-09-09
| JD3RMRL03SS61353 | Primary Test for GRP Pipe Line 200 mm - depth from 0.00 to 1.50- B5.33 31 00.03-MR-L-03-SS | 1 | 2025-09-10 | 2025-09-11
| JD3RMRL03SS61354 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - depth from 0.00 to 1.50- B5.33 31 00.03-MR-L-03-SS | 1 | 2025-09-13 | 2025-09-14
| JD3RMRL03SS61355 | Trench excavation for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-MR-L-03-SS | 1 | 2025-09-06 | 2025-09-11
| JD3RMRL03SS61356 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-MR-L-03-SS | 1 | 2025-09-15 | 2025-09-21
| JD3RMRL03SS61357 | Installing for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-MR-L-03-SS | 1 | 2025-09-22 | 2025-09-29
| JD3RMRL03SS61358 | Primary Test for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-MR-L-03-SS | 1 | 2025-09-30 | 2025-10-06
| JD3RMRL03SS61360 | Trench excavation for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-MR-L-03-SS | 1 | 2025-09-13 | 2025-09-14
| JD3RMRL03SS61361 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-MR-L-03-SS | 1 | 2025-09-15 | 2025-09-16
| JD3RMRL03SS61362 | Installing for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-MR-L-03-SS | 1 | 2025-09-17 | 2025-09-20
| JD3RMRL03SS61363 | Primary Test for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-MR-L-03-SS | 1 | 2025-09-21 | 2025-09-22
| JD3RMRL03SS61364 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-MR-L-03-SS | 1 | 2025-09-23 | 2025-09-25
| JD3RMRL03SS61370 | Trench excavation for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50- B5.33 31 00.11-MR-L-03-SS | 1 | 2025-09-15 | 2025-09-17
| JD3RMRL03SS61371 | Soil Replacement and Bedding Works for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50- B5.33 31 00.11-MR-L-03-SS | 1 | 2025-09-18 | 2025-09-21
| JD3RMRL03SS61372 | Installing for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50- B5.33 31 00.11-MR-L-03-SS | 1 | 2025-09-22 | 2025-09-24
| JD3RMRL03SS61373 | Primary Test for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50- B5.33 31 00.11-MR-L-03-SS | 1 | 2025-09-25 | 2025-09-28
| JD3RMRL03SS61374 | Backfilling and warning tabe Works for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50- B5.33 31 00.11-MR-L-03-SS | 1899-12-31 | 2025-09-29 | 2025-10-02
| JD3RMRL03SS61375 | Trench excavation for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50- B5.33 31 00.12-MR-L-03-SS | 1 | 2025-09-18 | 2025-09-22
| JD3RMRL03SS61376 | Soil Replacement and Bedding Works for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50- B5.33 31 00.12-MR-L-03-SS | 1 | 2025-09-23 | 2025-09-27
| JD3RMRL03SS61377 | Installing for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50- B5.33 31 00.12-MR-L-03-SS | 1899-12-31 | 2025-09-28 | 2025-10-02
| JD3RMRL03SS613801 | Trench excavation for GRP Pipe Line 300 mm - Depth from 4.51 to 5.50- B5.33 31 00.13-MR-L-03-SS | 1 | 2025-09-23 | 2025-09-24
| JD3RMRL03SS613802 | Trench excavation for GRP Pipe Line 400 mm - Depth from 4.51 to 5.50- B5.33 31 00.13-MR-L-03-SS | 1 | 2025-09-25 | 2025-09-29
| JD3RMRL03SS613811 | Soil Replacement and Bedding Works for GRP Pipe Line 300 mm - Depth from 4.51 to 5.50- B5.33 31 00.13-MR-L-03-SS | 1 | 2025-09-25 | 2025-09-27
| JD3RMRL03SS613812 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - Depth from 4.51 to 5.50- B5.33 31 00.13-MR-L-03-SS | 1 | 2025-09-30 | 2025-10-04
| JD3RMRL03SS613821 | Installing for GRP Pipe Line 300 mm - Depth from 4.51 to 5.50- B5.33 31 00.13-MR-L-03-SS | 1 | 2025-09-28 | 2025-09-29
| JD3RMRL03SS613831 | Primary Test for GRP Pipe Line 300 mm - Depth from 4.51 to 5.50- B5.33 31 00.13-MR-L-03-SS | 1 | 2025-09-30 | 2025-10-01
| JD3RMRL03SS61397 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-MR-L-03-SS | 1 | 2025-09-30 | 2025-10-01
| JD3RMRL17SS62068 | Trench excavation for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-MR-L-17-SS | 1 | 2025-09-11 | 2025-10-01
| JD3RMRL51SS63489 | Trench excavation for GRP Pipe Line 200 mm - depth from 0.00 to 1.50- B5.33 31 00.03-MR-L-51-SS | 1899-12-31 | 2025-09-20 | 2025-09-21 | 2024-12-21 | 2025-01-26
| JD3RMRL51SS63490 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - depth from 0.00 to 1.50- B5.33 31 00.03-MR-L-51-SS | 1 | 2025-09-22 | 2025-09-23 | 2024-12-31 | 2025-02-24
| JD3RMRL51SS63491 | Installing for GRP Pipe Line 200 mm - depth from 0.00 to 1.50- B5.33 31 00.03-MR-L-51-SS | 1 | 2025-09-24 | 2025-09-25 | 2024-12-31 | 2025-02-05
| JD3RMRL51SS63492 | Primary Test for GRP Pipe Line 200 mm - depth from 0.00 to 1.50- B5.33 31 00.03-MR-L-51-SS | 1899-12-31 | 2025-09-27 | 2025-09-28 | 2025-01-06 | 2025-01-23
| JD3RMRL51SS63493 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - depth from 0.00 to 1.50- B5.33 31 00.03-MR-L-51-SS | 1 | 2025-09-29 | 2025-09-30 | 2025-04-01 | 2025-06-14
| JD3RMRL51SS63494 | Trench excavation for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-MR-L-51-SS | 1 | 2025-09-20 | 2025-09-21 | 2024-12-31 | 2025-01-18
| JD3RMRL51SS63495 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-MR-L-51-SS | 1 | 2025-09-22 | 2025-09-23 | 2025-01-06 | 2025-01-23
| JD3RMRL51SS63496 | Installing for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-MR-L-51-SS | 1 | 2025-09-24 | 2025-09-25 | 2025-01-21 | 2025-02-08
| JD3RMRL51SS63497 | Primary Test for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-MR-L-51-SS | 1899-12-31 | 2025-09-27 | 2025-09-28 | 2025-01-06 | 2025-01-23
| JD3RMRL51SS63498 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-MR-L-51-SS | 1 | 2025-09-29 | 2025-09-30 | 2025-08-17 | 2025-08-18
| JD3RMRL51SS63504 | Trench excavation for GRP Pipe Line 250 mm - Depth from 1.51 to 2.50- B5.33 31 00.10-MR-L-51-SS | 1 | 2025-09-20 | 2025-09-23 | 2024-12-16 | 2025-01-02
| JD3RMRL51SS63505 | Soil Replacement and Bedding Works for GRP Pipe Line 250 mm - Depth from 1.51 to 2.50- B5.33 31 00.10-MR-L-51-SS | 1 | 2025-09-24 | 2025-09-28 | 2024-12-19 | 2025-01-06
| JD3RMRL51SS63506 | Installing for GRP Pipe Line 250 mm - Depth from 1.51 to 2.50- B5.33 31 00.10-MR-L-51-SS | 1 | 2025-09-29 | 2025-10-02 | 2024-12-25 | 2025-01-12
| JD3RMRL51SS63509 | Trench excavation for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50- B5.33 31 00.11-MR-L-51-SS | 1 | 2025-09-20 | 2025-09-21 | 2024-12-19 | 2025-01-06
| JD3RMRL51SS63510 | Soil Replacement and Bedding Works for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50- B5.33 31 00.11-MR-L-51-SS | 1 | 2025-09-22 | 2025-09-23 | 2025-01-06 | 2025-01-23
| JD3RMRL51SS63511 | Installing for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50- B5.33 31 00.11-MR-L-51-SS | 1 | 2025-09-24 | 2025-09-25 | 2025-01-13 | 2025-01-30
| JD3RMRL51SS63512 | Primary Test for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50- B5.33 31 00.11-MR-L-51-SS | 1 | 2025-09-27 | 2025-09-28 | 2025-01-22 | 2025-02-09
| JD3RMRL51SS63536 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-MR-L-51-SS | 1899-12-31 | 2025-09-20 | 2025-09-21 | 2024-12-16 | 2025-01-12
| JD3RMRL51SS63537 | Installation of Base Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-MR-L-51-SS | 1 | 2025-09-22 | 2025-09-23 | 2024-12-30 | 2025-02-04
| JD3RMRL51SS63548 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-MR-L-51-SS | 1 | 2025-09-20 | 2025-09-21 | 2024-12-24 | 2025-01-11
| JD3RMRL51SS63549 | Installation of Base Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-MR-L-51-SS | 1 | 2025-09-22 | 2025-09-24 | 2025-01-08 | 2025-02-04
| JD3RMRL51SS63550 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-MR-L-51 | 1 | 2025-09-25 | 2025-09-28 | 2025-01-22 | 2025-02-18
| JD3RMRL51ST63675 | Excavation Works for GRP Pipe Line 900 mm - depth from 0.00 to 1.50 m- B6.33 42 11.11-MR-L-51-ST | 1 | 2025-09-20 | 2025-09-21 | 2025-04-05 | 2025-04-22
| JD3RMRL51ST63676 | Soil Replacement and Bedding Works for GRP Pipe Line 900 mm - depth from 0.00 to 1.50 m- B6.33 42 11.11-MR-L-51-ST | 1 | 2025-09-22 | 2025-09-23 | 2025-05-11 | 2025-05-28
| JD3RMRL51ST63677 | Installing for GRP Pipe Line 900 mm - depth from 0.00 to 1.50 m- B6.33 42 11.11-MR-L-51-ST | 1 | 2025-09-24 | 2025-09-25 | 2025-05-11 | 2025-05-28
| JD3RMRL51ST63725 | Excavation Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-L-51-ST | 1 | 2025-09-20 | 2025-09-23 | 2025-01-07 | 2025-01-25
| JD3RMRL51ST63726 | Soil Replacement and Bedding Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-L-51-ST | 1 | 2025-09-24 | 2025-09-28 | 2025-03-11 | 2025-04-07
| JD3RMRL51ST63727 | Installing for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-MR-L-51-ST | 1 | 2025-09-29 | 2025-10-02 | 2025-04-07 | 2025-05-04
| JD3RMRL58ST100 | Channel excavation for Swales-B6.31 22 00.13-MR-L-58-ST | 1 | 2025-09-28 | 2025-10-11
| JD3RMRMR1ST100 | Channel excavation for Swales-B6.31 22 00.13-MR-R1-ST | 1 | 2025-08-02 | 2025-08-24 | 2025-04-02 | 2025-07-31
| JD3RMRMR1ST101 | Channel excavation for Swales-B6.31 22 00.13-MR-R1-ST | 1 | 2025-08-25 | 2025-09-02 | 2025-07-01 | 2025-07-31
| JD3RMRMR1ST101.R | Channel excavation for Swales-B6.31 22 00.13-MR-R1-ST -Remaining | 1 | 2025-09-03 | 2025-09-22 | 2025-08-12 | 2025-08-31
| JD3RMRMR1ST101.R1 | Channel excavation for Swales-B6.31 22 00.13-MR-R1-ST -Remaining | 1 | 2025-09-23 | 2025-10-12 | 2025-08-02
| JD3RMRMR1ST200 | Riprap With side slopes 1:1 for Swales-NB6.31 22 00.15-MR-R1-ST | 1 | 2025-09-23 | 2025-09-30
| JD3RPS08 | Excavation Works -For Pond 2--B6.31 22 00.04---PS | 1 | 2025-02-13 | 2025-02-24 | 2024-10-08 | 2025-02-05
| JD3RPS09 | Filling with selected excavated material-For Pond 2--B6.31 22 00.05---PS | 1 | 2025-02-25 | 2025-02-26 | 2024-11-18 | 2024-12-05
| JD3RPS1 | Excavation Works -For Pond 1--B6.31 22 00.01--Pond
| 1-1-PS | 1 | 2024-09-11 | 2024-10-03 | 2024-09-28 | 2025-02-04
| JD3RPS1001 | Outfall structure size 3.0 × 1.5 m-For Pond 3--B6.33 05 13.03---PS | 1 | 2025-09-14 | 2025-09-15
| JD3RPS101 | Acess Entrace Ramp-For Pond 1--B6.03 30 00.02---PS | 1 | 2024-12-17 | 2024-12-21 | 2025-02-01 | 2025-02-18
| JD3RPS1011 | Acess Entrace Ramp-For Pond 3--B6.03 30 00.06---PS | 1 | 2025-09-16 | 2025-09-17 | 2025-02-03 | 2025-02-20
| JD3RPS1021 | Excavation Works -For Pond 4--B6.31 22 00.10---PS | 1899-12-31 | 2025-08-13 | 2025-08-20 | 2024-11-02 | 2025-02-11
| JD3RPS1031 | Filling with selected excavated material-For Pond 4--B6.31 22 00.11---PS | 1 | 2025-08-21 | 2025-08-23 | 2024-12-21 | 2025-01-07
| JD3RPS1051 | Riprap with thickness 300mm as shown in drawings.-For Pond 4--B6.03 30 00.07---PS | 1 | 2025-08-24 | 2025-08-31 | 2024-12-21 | 2025-04-29
| JD3RPS1071 | Outfall structure size 4.0 × 2.0 m-For Pond 4--B6.33 05 13.04---PS | 1 | 2025-09-01 | 2025-09-02
| JD3RPS1081 | Acess Entrace Ramp-For Pond 4--B6.03 30 00.08---PS | 1 | 2025-09-03 | 2025-09-04 | 2025-02-04 | 2025-02-22
| JD3RPS1091 | Excavation Works -For Pond 4--B6.31 22 00.01---PS | 1 | 2025-09-06 | 2025-09-13 | 2024-11-07 | 2025-02-17
| JD3RPS11 | Riprap with thickness 300mm as shown in drawings.-For Pond 2--B6.03 30 00.03---PS | 1 | 2025-02-27 | 2025-03-11 | 2024-11-18 | 2025-02-27
| JD3RPS1101 | Filling with selected excavated material-For Pond 4--B6.31 22 00.02---PS | 1 | 2025-09-14 | 2025-09-15 | 2024-11-10 | 2024-11-27
| JD3RPS111 | Excavation Works -For Pond 1--B6.31 22 00.01---PS | 1 | 2024-12-24 | 2025-01-14 | 2024-10-28 | 2025-03-06
| JD3RPS1121 | Riprap with thickness 300mm as shown in drawings.-For Pond 4--B6.03 30 00.01---PS | 1 | 2025-09-16 | 2025-09-23 | 2024-12-26 | 2025-05-05
| JD3RPS1141 | Outfall structure size 4.0 × 2.0 m-For Pond 4--B6.33 05 13.01---PS | 1 | 2025-09-24 | 2025-09-25
| JD3RPS1151 | Acess Entrace Ramp-For Pond 4--B6.03 30 00.02---PS | 1 | 2025-09-27 | 2025-09-28 | 2025-02-04 | 2025-02-22
| JD3RPS1161 | Excavation Works -For Pond 4--B6.31 22 00.01---PS | 1 | 2025-09-29 | 2025-10-06 | 2024-12-10 | 2025-03-22
| JD3RPS121 | Filling with selected excavated material-For Pond 1--B6.31 22 00.02---PS | 1 | 2025-01-15 | 2025-01-16 | 2024-10-28 | 2024-11-14
| JD3RPS13 | Outfall structure size 2.0 × 1.25 m-For Pond 2--B6.33 05 13.02---PS | 1 | 2025-03-12 | 2025-03-13
| JD3RPS1301 | Excavation Works -For Pond 4--B6.31 22 00.10---PS | 1 | 2025-07-29 | 2025-08-05 | 2024-12-12 | 2025-03-24
| JD3RPS1311 | Filling with selected excavated material-For Pond 4--B6.31 22 00.11---PS | 1 | 2025-08-06 | 2025-08-07 | 2024-12-15 | 2025-01-01
| JD3RPS1331 | Riprap with thickness 300mm as shown in drawings.-For Pond 4--B6.03 30 00.07---PS | 1 | 2025-08-09 | 2025-08-16 | 2025-01-15 | 2025-05-25
| JD3RPS1351 | Outfall structure size 3.0 × 1.5 m-For Pond 4--B6.33 05 13.04---PS | 1 | 2025-08-17 | 2025-08-18
| JD3RPS1361 | Acess Entrace Ramp-For Pond 4--B6.03 30 00.08---PS | 1 | 2025-08-19 | 2025-08-20 | 2025-02-04 | 2025-02-22
| JD3RPS1371 | Excavation Works -For Pond 4--B6.31 22 00.01---PS | 1 | 2025-08-21 | 2025-08-28 | 2024-12-15 | 2025-03-26
| JD3RPS1381 | Filling with selected excavated material-For Pond 4--B6.31 22 00.02---PS | 1 | 2025-08-30 | 2025-08-31 | 2024-12-17 | 2025-01-04
| JD3RPS14 | Acess Entrace Ramp-For Pond 2--B6.03 30 00.04---PS | 1 | 2025-03-15 | 2025-03-16 | 2025-02-01 | 2025-02-18
| JD3RPS1401 | Riprap with thickness 300mm as shown in drawings.-For Pond 4--B6.03 30 00.01---PS | 1899-12-31 | 2025-09-01 | 2025-09-08 | 2025-01-16 | 2025-05-26
| JD3RPS141 | Riprap with thickness 300mm as shown in drawings.-For Pond 1--B6.03 30 00.01---PS | 1 | 2025-01-18 | 2025-02-08 | 2024-10-28 | 2025-04-22
| JD3RPS1421 | Outfall structure size 4.0 × 2.0 m-For Pond 4--B6.33 05 13.01---PS | 1 | 2025-09-09 | 2025-09-10
| JD3RPS1431 | Acess Entrace Ramp-For Pond 4--B6.03 30 00.02---PS | 1 | 2025-09-11 | 2025-09-13 | 2025-02-04 | 2025-02-22
| JD3RPS1441 | Excavation Works -For Pond 4--B6.31 22 00.01---PS | 1 | 2025-09-14 | 2025-09-21 | 2024-12-16 | 2025-03-27
| JD3RPS1451 | Filling with selected excavated material-For Pond 4--B6.31 22 00.02---PS | 1 | 2025-09-22 | 2025-09-23 | 2024-12-18 | 2025-01-05
| JD3RPS1471 | Riprap with thickness 300mm as shown in drawings.-For Pond 4--B6.03 30 00.01---PS | 1 | 2025-09-24 | 2025-10-01 | 2025-01-18 | 2025-05-27
| JD3RPS15 | Excavation Works -For Pond 3--B6.31 22 00.07---PS | 1 | 2024-10-05 | 2024-10-28 | 2024-09-30 | 2025-02-25
| JD3RPS16 | Filling with selected excavated material-For Pond 3--B6.31 22 00.08---PS | 1 | 2024-10-29 | 2024-10-30 | 2024-11-23 | 2024-12-10
| JD3RPS161 | Outfall structure size 4.0 × 2.0 m-For Pond 1--B6.33 05 13.01---PS | 1 | 2025-02-13 | 2025-02-15
| JD3RPS171 | Acess Entrace Ramp-For Pond 1--B6.03 30 00.02---PS | 1 | 2025-02-09 | 2025-02-12 | 2025-02-01 | 2025-02-18
| JD3RPS18 | Riprap with thickness 300mm as shown in drawings.-For Pond 3--B6.03 30 00.05---PS | 1 | 2024-10-31 | 2024-11-11 | 2024-11-23 | 2025-04-20
| JD3RPS181 | Excavation Works -For Pond 2--B6.31 22 00.04---PS | 1 | 2025-03-17 | 2025-03-27 | 2024-10-19 | 2025-02-16
| JD3RPS191 | Filling with selected excavated material-For Pond 2--B6.31 22 00.05---PS | 1 | 2025-03-29 | 2025-03-30 | 2024-11-24 | 2024-12-11
| JD3RPS2 | Filling with selected excavated material-For Pond 1--B6.31 22 00.02--Pond
| 1-1-PS | 1 | 2024-10-05 | 2024-10-06 | 2024-11-20 | 2024-12-08
| JD3RPS20 | Outfall structure size 2.0 × 1.25 m-For Pond 3--B6.33 05 13.03---PS | 1 | 2024-11-12 | 2024-11-13
| JD3RPS21 | Acess Entrace Ramp-For Pond 3--B6.03 30 00.06---PS | 1 | 2024-11-14 | 2024-11-16 | 2025-02-03 | 2025-02-20
| JD3RPS211 | Riprap with thickness 300mm as shown in drawings.-For Pond 2--B6.03 30 00.03---PS | 1 | 2025-03-31 | 2025-04-12 | 2024-11-24 | 2025-03-05
| JD3RPS22 | Excavation Works -For Pond 4--B6.31 22 00.10---PS | 1 | 2025-07-21 | 2025-07-28 | 2024-10-23 | 2025-02-02
| JD3RPS23 | Filling with selected excavated material-For Pond 4--B6.31 22 00.11---PS | 1899-12-31 | 2025-07-29 | 2025-07-30 | 2024-12-04 | 2024-12-22
| JD3RPS231 | Outfall structure size 4.0 × 2.0 m-For Pond 2--B6.33 05 13.02---PS | 1 | 2025-04-13 | 2025-04-14
| JD3RPS241 | Acess Entrace Ramp-For Pond 2--B6.03 30 00.04---PS | 1 | 2025-04-15 | 2025-04-16 | 2025-02-01 | 2025-02-18
| JD3RPS25 | Riprap with thickness 300mm as shown in drawings.-For Pond 4--B6.03 30 00.07---PS | 1 | 2025-07-31 | 2025-08-07 | 2024-12-04 | 2025-04-13
| JD3RPS251 | Excavation Works -For Pond 2--B6.31 22 00.01---PS | 1 | 2025-04-17 | 2025-04-28 | 2024-10-26 | 2025-02-23
| JD3RPS261 | Filling with selected excavated material-For Pond 2--B6.31 22 00.02---PS | 1 | 2025-04-29 | 2025-04-30 | 2024-12-07 | 2024-12-24
| JD3RPS27 | Outfall structure size 4.0 × 1.5 m-For Pond 4--B6.33 05 13.04---PS | 1 | 2025-08-09 | 2025-08-10
| JD3RPS28 | Acess Entrace Ramp-For Pond 4--B6.03 30 00.08---PS | 1 | 2025-08-11 | 2025-08-12 | 2025-02-04 | 2025-02-22
| JD3RPS281 | Riprap with thickness 300mm as shown in drawings.-For Pond 2--B6.03 30 00.01---PS | 1 | 2025-05-01 | 2025-05-13 | 2024-12-07 | 2025-03-18
| JD3RPS301 | Outfall structure size 4.0 × 2.0 m-For Pond 2--B6.33 05 13.01---PS | 1899-12-31 | 2025-05-14 | 2025-05-15
| JD3RPS311 | Acess Entrace Ramp-For Pond 2--B6.03 30 00.02---PS | 1 | 2025-05-17 | 2025-05-18 | 2025-02-01 | 2025-02-18
| JD3RPS321 | Excavation Works -For Pond 2--B6.31 22 00.01---PS | 1 | 2025-05-19 | 2025-05-29 | 2024-11-09 | 2025-03-09
| JD3RPS331 | Filling with selected excavated material-For Pond 2--B6.31 22 00.02---PS | 1 | 2025-05-31 | 2025-06-01 | 2024-11-09 | 2024-11-26
| JD3RPS351 | Riprap with thickness 300mm as shown in drawings.-For Pond 2--B6.03 30 00.01---PS | 1 | 2025-06-02 | 2025-06-14 | 2024-11-09 | 2025-02-18
| JD3RPS371 | Outfall structure size 4.0 × 2.0 m-For Pond 2--B6.33 05 13.01---PS | 1 | 2025-06-15 | 2025-06-16
| JD3RPS381 | Acess Entrace Ramp-For Pond 2--B6.03 30 00.02---PS | 1 | 2025-06-17 | 2025-06-18 | 2025-02-01 | 2025-02-18
| JD3RPS391 | Excavation Works -For Pond 2--B6.31 22 00.01---PS | 1 | 2025-06-19 | 2025-06-30 | 2024-12-05 | 2025-03-26
| JD3RPS4 | Riprap with thickness 300mm as shown in drawings.-For Pond 1--B6.03 30 00.01--Pond
| 1-1-PS | 1 | 2024-10-07 | 2024-10-28 | 2024-11-20 | 2025-05-25
| JD3RPS401 | Filling with selected excavated material-For Pond 2--B6.31 22 00.02---PS | 1 | 2025-07-01 | 2025-07-02 | 2024-12-05 | 2024-12-23
| JD3RPS41 | Excavation Works -For Pond 1--B6.31 22 00.01---PS | 1 | 2024-11-03 | 2024-11-24 | 2024-10-21 | 2025-02-27
| JD3RPS421 | Riprap with thickness 300mm as shown in drawings.-For Pond 2--B6.03 30 00.01---PS | 1 | 2025-07-03 | 2025-07-15 | 2024-12-05 | 2025-03-17
| JD3RPS441 | Outfall structure size 4.0 × 2.0 m-For Pond 2--B6.33 05 13.01---PS | 1 | 2025-07-16 | 2025-07-17
| JD3RPS451 | Acess Entrace Ramp-For Pond 2--B6.03 30 00.02---PS | 1 | 2025-07-19 | 2025-07-20 | 2025-02-01 | 2025-02-18
| JD3RPS461 | Excavation Works -For Pond 3--B6.31 22 00.07---PS | 1 | 2024-11-17 | 2024-12-10 | 2024-10-13 | 2025-03-10
| JD3RPS471 | Filling with selected excavated material-For Pond 3--B6.31 22 00.08---PS | 1 | 2024-12-11 | 2024-12-12 | 2024-12-02 | 2024-12-19
| JD3RPS491 | Riprap with thickness 300mm as shown in drawings.-For Pond 3--B6.03 30 00.05---PS | 1 | 2024-12-14 | 2024-12-24 | 2024-12-02 | 2025-04-29
| JD3RPS51 | Filling with selected excavated material-For Pond 1--B6.31 22 00.02---PS | 1 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-12-15
| JD3RPS511 | Outfall structure size 4.0 × 2.0 m-For Pond 3--B6.33 05 13.03---PS | 1 | 2024-12-25 | 2024-12-26
| JD3RPS521 | Acess Entrace Ramp-For Pond 3--B6.03 30 00.06---PS | 1 | 2024-12-28 | 2024-12-29 | 2025-02-03 | 2025-02-20
| JD3RPS524371 | Filling with imported material-B6.31 22 00.12-Z02-2-L-74-ST | 1 | 2025-01-09 | 2025-01-28
| JD3RPS524372 | Filling with imported material-B6.31 22 00.12-Z02-2-L-75-ST | 1 | 2025-02-03 | 2025-02-25
| JD3RPS531 | Excavation Works -For Pond 3--B6.31 22 00.01---PS | 1 | 2024-12-30 | 2025-01-22 | 2024-10-21 | 2025-03-18
| JD3RPS541 | Filling with selected excavated material-For Pond 3--B6.31 22 00.02---PS | 1 | 2025-01-23 | 2025-01-25 | 2024-12-09 | 2024-12-26
| JD3RPS561 | Riprap with thickness 300mm as shown in drawings.-For Pond 3--B6.03 30 00.01---PS | 1 | 2025-01-26 | 2025-02-05 | 2024-12-09 | 2025-05-06
| JD3RPS581 | Outfall structure size 4.0 × 2.0 m-For Pond 3--B6.33 05 13.01---PS | 1 | 2025-02-06 | 2025-02-08
| JD3RPS591 | Acess Entrace Ramp-For Pond 3--B6.03 30 00.02---PS | 1 | 2025-02-09 | 2025-02-10 | 2025-02-03 | 2025-02-20
| JD3RPS6 | Outfall structure size 4.0 × 2.0 m-For Pond 1--B6.33 05 13.01--Pond
| 1-1-PS | 1 | 2024-11-03 | 2024-11-04 | 2025-09-08
| JD3RPS601 | Excavation Works -For Pond 3--B6.31 22 00.01---PS | 1 | 2025-02-11 | 2025-03-06 | 2024-10-26 | 2025-03-23
| JD3RPS611 | Filling with selected excavated material-For Pond 3--B6.31 22 00.02---PS | 1 | 2025-03-08 | 2025-03-09 | 2024-12-05 | 2024-12-23
| JD3RPS631 | Riprap with thickness 300mm as shown in drawings.-For Pond 3--B6.03 30 00.01---PS | 1 | 2025-03-10 | 2025-03-20 | 2024-12-05 | 2025-05-03
| JD3RPS651 | Outfall structure size 4.0 × 2.0 m-For Pond 3--B6.33 05 13.01---PS | 1 | 2025-03-22 | 2025-03-23
| JD3RPS661 | Acess Entrace Ramp-For Pond 3--B6.03 30 00.02---PS | 1 | 2025-03-24 | 2025-03-25 | 2025-02-03 | 2025-02-20
| JD3RPS671 | Excavation Works -For Pond 3--B6.31 22 00.01---PS | 1 | 2025-03-26 | 2025-04-19 | 2024-10-30 | 2025-03-27
| JD3RPS681 | Filling with selected excavated material-For Pond 3--B6.31 22 00.02---PS | 1 | 2025-04-20 | 2025-04-21 | 2024-12-10 | 2024-12-28
| JD3RPS7 | Acess Entrace Ramp-For Pond 1--B6.03 30 00.02--Pond
| 1-1-PS | 1 | 2024-10-29 | 2024-11-02 | 2025-02-01 | 2025-02-18
| JD3RPS701 | Riprap with thickness 300mm as shown in drawings.-For Pond 3--B6.03 30 00.01---PS | 1 | 2025-04-22 | 2025-05-03 | 2024-12-10 | 2025-05-07
| JD3RPS71 | Riprap with thickness 300mm as shown in drawings.-For Pond 1--B6.03 30 00.01---PS | 1 | 2024-11-25 | 2024-12-16 | 2024-11-27 | 2025-05-22
| JD3RPS721 | Outfall structure size 4.0 × 2.0 m-For Pond 3--B6.33 05 13.01---PS | 1 | 2025-05-04 | 2025-05-05
| JD3RPS731 | Acess Entrace Ramp-For Pond 3--B6.03 30 00.02---PS | 1 | 2025-05-06 | 2025-05-06 | 2025-02-03 | 2025-02-20
| JD3RPS741 | Excavation Works -For Pond 3--B6.31 22 00.07---PS | 1 | 2025-05-07 | 2025-05-31 | 2024-11-05 | 2025-04-02
| JD3RPS751 | Filling with selected excavated material-For Pond 3--B6.31 22 00.08---PS | 1 | 2025-06-01 | 2025-06-02 | 2024-11-10 | 2024-11-27
| JD3RPS771 | Riprap with thickness 300mm as shown in drawings.-For Pond 3--B6.03 30 00.05---PS | 1 | 2025-06-03 | 2025-06-14 | 2024-12-17 | 2025-05-14
| JD3RPS791 | Outfall structure size 3.0 × 1.5 m-For Pond 3--B6.33 05 13.03---PS | 1 | 2025-06-15 | 2025-06-16
| JD3RPS801 | Acess Entrace Ramp-For Pond 3--B6.03 30 00.06---PS | 1 | 2025-06-17 | 2025-06-18 | 2025-02-03 | 2025-02-20
| JD3RPS811 | Excavation Works -For Pond 3--B6.31 22 00.01---PS | 1 | 2025-06-19 | 2025-07-13 | 2024-11-12 | 2025-04-09
| JD3RPS821 | Filling with selected excavated material-For Pond 3--B6.31 22 00.02---PS | 1 | 2025-07-14 | 2025-07-15 | 2024-11-20 | 2024-12-08
| JD3RPS841 | Riprap with thickness 300mm as shown in drawings.-For Pond 3--B6.03 30 00.01---PS | 1 | 2025-07-16 | 2025-07-27 | 2024-12-26 | 2025-05-24
| JD3RPS861 | Outfall structure size 4.0 × 2.0 m-For Pond 3--B6.33 05 13.01---PS | 1 | 2025-07-28 | 2025-07-29
| JD3RPS871 | Acess Entrace Ramp-For Pond 3--B6.03 30 00.02---PS | 1 | 2025-07-30 | 2025-07-31 | 2025-02-03 | 2025-02-20
| JD3RPS881 | Excavation Works -For Pond 3--B6.31 22 00.01---PS | 1 | 2025-08-02 | 2025-08-25 | 2024-11-12 | 2025-04-09
| JD3RPS891 | Filling with selected excavated material-For Pond 3--B6.31 22 00.02---PS | 1 | 2025-08-26 | 2025-08-27 | 2024-11-20 | 2024-12-08
| JD3RPS91 | Outfall structure size 4.0 × 2.0 m-For Pond 1--B6.33 05 13.01---PS | 1 | 2024-12-22 | 2024-12-23 | 2025-09-08
| JD3RPS911 | Riprap with thickness 300mm as shown in drawings.-For Pond 3--B6.03 30 00.01---PS | 1 | 2025-08-28 | 2025-09-08 | 2025-01-05 | 2025-06-02
| JD3RPS931 | Outfall structure size 4.0 × 2.0 m-For Pond 3--B6.33 05 13.01---PS | 1 | 2025-09-09 | 2025-09-10
| JD3RPS941 | Acess Entrace Ramp-For Pond 3--B6.03 30 00.02---PS | 1 | 2025-09-11 | 2025-09-13 | 2025-02-03 | 2025-02-20
| JD3RPS951 | Excavation Works -For Pond 3--B6.31 22 00.07---PS | 1 | 2025-09-18 | 2025-10-12 | 2024-11-18 | 2025-02-27
| JD3RZ02-1L69SL7079 | Excavation Worksfor Copper Cables 4Cx25 mm² - - B2.26 05 19.04-Z02-1-L-69-SL | 1 | 2025-01-13 | 2025-01-15
| JD3RZ02-1L69SL7080 | Installationfor Copper Cables 4Cx25 mm² - - B2.26 05 19.04-Z02-1-L-69-SL | 1 | 2025-03-26 | 2025-03-29
| JD3RZ02-1L69SL7081 | Backfilling, Warning Tabe Worksfor Copper Cables 4Cx25 mm² - - B2.26 05 19.04-Z02-1-L-69-SL | 1 | 2025-03-30 | 2025-04-01
| JD3RZ02-1L69SL7082 | Testing and Commitioning for Copper Cables 4Cx25 mm² - - B2.26 05 19.04-Z02-1-L-69-SL | 1 | 2025-04-02 | 2025-04-05
| JD3RZ02-1L69SL7093 | INSTALLINGfor insulated copper conductor 16 mm² - - B2.26 05 19.08-Z02-1-L-69-SL | 1 | 2025-03-30 | 2025-04-01
| JD3RZ02-1L69SL7094 | TESTING AND COMMITIONINGfor insulated copper conductor 16 mm² - - B2.26 05 19.08-Z02-1-L-69-SL | 1 | 2025-04-02 | 2025-04-05
| JD3RZ02-1L69SL7100 | Excavation of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-1-L-69-SL | 1 | 2025-01-18 | 2025-01-19
| JD3RZ02-1L69SL7101 | Installation of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-1-L-69-SL | 1 | 2025-01-20 | 2025-01-21
| JD3RZ02-1L69SL7102 | Backfilling of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-1-L-69-SL | 1 | 2025-01-22 | 2025-01-23
| JD3RZ02-1L69SL7103 | Installation Worksfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-1-L-69-SL | 1 | 2025-01-25 | 2025-01-27
| JD3RZ02-1L69SL7104 | Testing and Commitioningfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-1-L-69-SL | 1 | 2025-04-06 | 2025-04-08
| JD3RZ02-1L69SL7105 | Installationfor Lighting( LED ) Luminaire 150 WATT - - B2.26.56.19.01-Z02-1-L-69-SL | 1 | 2025-01-25 | 2025-01-26
| JD3RZ02-1L69SL7108 | Supply, construct, connect and test earthing pitsfor Street Lighting EARTHING SYSTEM - - B2.26 05 26.01-Z02-1-L-69-SL | 1 | 2025-01-22 | 2025-01-23
| JD3RZ02-1L69SL7121 | Excavationfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z02-1-L-69-SL | 1 | 2025-01-20 | 2025-01-21
| JD3RZ02-1L69SL7122 | Installationfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z02-1-L-69-SL | 1 | 2025-01-22 | 2025-01-23
| JD3RZ02-1L69SL7123 | Backfillingfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z02-1-L-69-SL | 1 | 2025-01-25 | 2025-01-26
| JD3RZ02-1L69SS6454 | Trench excavation for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-69-SS | 1 | 2024-09-04 | 2024-09-07 | 2025-04-10 | 2025-04-28
| JD3RZ02-1L69SS6455 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-69-SS | 1 | 2024-09-08 | 2024-09-10 | 2025-04-20 | 2025-05-17
| JD3RZ02-1L69SS6456 | Installing for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-69-SS | 1 | 2024-09-11 | 2024-09-14 | 2025-04-22 | 2025-05-28
| JD3RZ02-1L69SS6457 | Primary Test for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-69-SS | 1 | 2024-09-15 | 2024-09-17 | 2025-06-10 | 2025-07-16
| JD3RZ02-1L69SS6458 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-69-SS | 1 | 2024-09-18 | 2024-09-22 | 2025-06-14 | 2025-07-20
| JD3RZ02-1L69SS6458.R | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-69-SS -Rem | 1 | 2024-09-24 | 2024-09-25
| JD3RZ02-1L69SS6464 | Trench excavation for GRP Pipe Line 250 mm - Depth from 1.51 to 2.50- B5.33 31 00.10-Z02-1-L-69-SS | 1 | 2024-09-04 | 2024-09-05 | 2025-08-02 | 2025-08-03
| JD3RZ02-1L69SS6465 | Soil Replacement and Bedding Works for GRP Pipe Line 250 mm - Depth from 1.51 to 2.50- B5.33 31 00.10-Z02-1-L-69-SS | 1 | 2024-09-07 | 2024-09-08 | 2025-08-04 | 2025-08-05
| JD3RZ02-1L69SS6466 | Installing for GRP Pipe Line 250 mm - Depth from 1.51 to 2.50- B5.33 31 00.10-Z02-1-L-69-SS | 1 | 2024-09-09 | 2024-09-10 | 2025-08-06 | 2025-08-07
| JD3RZ02-1L69SS6467 | Primary Test for GRP Pipe Line 250 mm - Depth from 1.51 to 2.50- B5.33 31 00.10-Z02-1-L-69-SS | 1 | 2024-09-11 | 2024-09-12 | 2025-08-09 | 2025-08-10
| JD3RZ02-1L69SS6468 | Backfilling and warning tabe Works for GRP Pipe Line 250 mm - Depth from 1.51 to 2.50- B5.33 31 00.10-Z02-1-L-69-SS | 1 | 2024-09-14 | 2024-09-15 | 2025-08-11 | 2025-08-12
| JD3RZ02-1L69SS6508 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-1-L-69-SS | 1 | 2024-09-24 | 2024-09-25 | 2025-04-10 | 2025-05-17
| JD3RZ02-1L69SS6508.R | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-1-L-69-SS -Remaining | 1 | 2024-09-26 | 2024-09-28 | 2025-08-02 | 2025-08-03
| JD3RZ02-1L69SS6509 | Installation of Base Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-1-L-69-SS | 1 | 2024-09-26 | 2024-09-29 | 2025-04-22 | 2025-07-31
| JD3RZ02-1L69SS6509.R | Installation of Base Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-1-L-69-SS -Remaining | 1 | 2024-09-30 | 2024-10-01 | 2025-08-04 | 2025-08-05
| JD3RZ02-1L69SS6510 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-1-L | 1 | 2024-10-02 | 2024-10-05 | 2025-08-06
| JD3RZ02-1L69SS6511 | Backfilling Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-1-L-69-SS | 1 | 2024-10-06 | 2024-10-07
| JD3RZ02-1L69SS6512 | Finishing, Benching Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-1-L-69-SS | 1 | 2024-10-08 | 2024-10-09
| JD3RZ02-1L69ST6580 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-1-L-69-ST | 1 | 2024-10-08 | 2024-10-09
| JD3RZ02-1L69ST6581 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-1-L-69-ST | 1 | 2024-10-10 | 2024-10-12
| JD3RZ02-1L69ST6582 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-1-L-69-ST | 1 | 2024-10-13 | 2024-10-15
| JD3RZ02-1L69ST6583 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-1-L-69-ST | 1 | 2024-10-16 | 2024-10-19
| JD3RZ02-1L69ST6584 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-1-L-69-ST | 1 | 2024-10-20 | 2024-10-22
| JD3RZ02-1L69ST6585 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-1-L-69-ST | 1 | 2024-09-26 | 2024-09-28 | 2025-04-28 | 2025-05-15
| JD3RZ02-1L69ST6585.R | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-1-L-69-ST -Remaining | 1 | 2024-10-10 | 2024-10-12
| JD3RZ02-1L69ST6586 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-1-L-69-ST | 1 | 2024-09-29 | 2024-09-30 | 2025-04-29 | 2025-05-17
| JD3RZ02-1L69ST6586.R | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-1-L-69-ST -R | 1 | 2024-10-13 | 2024-10-14
| JD3RZ02-1L69ST6587 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-1-L-69-ST | 1 | 2024-10-01 | 2024-10-03 | 2025-04-30 | 2025-05-18
| JD3RZ02-1L69ST6587.R | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-1-L-69-ST -Remaining | 1 | 2024-10-15 | 2024-10-16
| JD3RZ02-1L69ST6588 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-1-L-69-ST | 1 | 2024-10-17 | 2024-10-19 | 2025-09-06
| JD3RZ02-1L69ST6589 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-1-L-69-ST | 1 | 2024-10-20 | 2024-10-22
| JD3RZ02-1L69ST6590 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-1-L-69-ST | 1 | 2024-10-10 | 2024-10-12
| JD3RZ02-1L69ST6591 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-1-L-69-ST | 1 | 2024-10-13 | 2024-10-14
| JD3RZ02-1L69ST6592 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-1-L-69-ST | 1 | 2024-10-15 | 2024-10-16
| JD3RZ02-1L69ST6593 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-1-L-69-ST | 1 | 2024-10-17 | 2024-10-19
| JD3RZ02-1L69ST6594 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-1-L-69-ST | 1 | 2024-10-20 | 2024-10-21
| JD3RZ02-1L69ST6595 | Excavation Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z02-1-L-69-ST | 1 | 2024-10-13 | 2024-10-14 | 2025-08-17 | 2025-08-18
| JD3RZ02-1L69ST6596 | Soil Replacement and Bedding Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z02-1-L-69-ST | 1 | 2024-10-15 | 2024-10-16 | 2025-08-19 | 2025-08-20
| JD3RZ02-1L69ST6597 | Installing for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z02-1-L-69-ST | 1 | 2024-10-17 | 2024-10-19 | 2025-08-21 | 2025-08-23
| JD3RZ02-1L69ST6598 | Primary Test for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z02-1-L-69-ST | 1 | 2024-10-20 | 2024-10-21 | 2025-08-24 | 2025-08-25
| JD3RZ02-1L69ST6599 | Backfilling Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z02-1-L-69-ST | 1 | 2024-10-22 | 2024-10-23 | 2025-08-26 | 2025-08-27
| JD3RZ02-1L69ST6600 | Excavation Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z02-1-L-69-ST | 1 | 2024-10-10 | 2024-10-12 | 2025-08-14 | 2025-08-16
| JD3RZ02-1L69ST6601 | Soil Replacement and Bedding Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z02-1-L-69-ST | 1 | 2024-10-13 | 2024-10-14 | 2025-08-17 | 2025-08-18
| JD3RZ02-1L69ST6602 | Installing for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z02-1-L-69-ST | 1 | 2024-10-15 | 2024-10-16 | 2025-08-19 | 2025-08-20
| JD3RZ02-1L69ST6603 | Primary Test for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z02-1-L-69-ST | 1 | 2024-10-17 | 2024-10-19 | 2025-08-21 | 2025-08-23
| JD3RZ02-1L69ST6604 | Backfilling Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z02-1-L-69-ST | 1 | 2024-10-20 | 2024-10-21 | 2025-08-24 | 2025-08-25
| JD3RZ02-1L69ST6605 | Excavation Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z02-1-L-69-ST | 1 | 2024-10-13 | 2024-10-14 | 2025-08-17 | 2025-09-03
| JD3RZ02-1L69ST6606 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z02-1-L-69-ST | 1 | 2024-10-15 | 2024-10-16 | 2025-08-19 | 2025-09-06
| JD3RZ02-1L69ST6607 | Installing for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z02-1-L-69-ST | 1 | 2024-10-17 | 2024-10-19 | 2025-08-23 | 2025-09-09
| JD3RZ02-1L69ST6608 | Primary Test for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z02-1-L-69-ST | 1 | 2024-10-20 | 2024-10-21 | 2025-08-26
| JD3RZ02-1L69ST6609 | Backfilling Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z02-1-L-69-ST | 1 | 2024-10-22 | 2024-10-23 | 2025-08-30
| JD3RZ02-1L69ST6615 | Excavation Works for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m- B6.33 42 11.07-Z02-1-L-69-ST | 1 | 2024-10-15 | 2024-10-16 | 2025-08-20
| JD3RZ02-1L69ST6616 | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m- B6.33 42 11.07-Z02-1-L-69-ST | 1 | 2024-10-17 | 2024-10-19 | 2025-08-26
| JD3RZ02-1L69ST6617 | Installing for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m- B6.33 42 11.07-Z02-1-L-69-ST | 1 | 2024-10-20 | 2024-10-21 | 2025-08-28
| JD3RZ02-1L69ST6618 | Primary Test for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m- B6.33 42 11.07-Z02-1-L-69-ST | 1 | 2024-10-22 | 2024-10-23 | 2025-09-17
| JD3RZ02-1L69ST6619 | Backfilling Works for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m- B6.33 42 11.07-Z02-1-L-69-ST | 1 | 2024-10-24 | 2024-10-26 | 2025-09-20
| JD3RZ02-1L69ST6620 | Excavation Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-69-ST | 1 | 2024-10-01 | 2024-10-02 | 2025-06-30 | 2025-07-17
| JD3RZ02-1L69ST6620.R | Excavation Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-69-ST -Remaining | 1 | 2024-10-13 | 2024-10-14 | 2025-08-20 | 2025-08-25
| JD3RZ02-1L69ST6621 | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-69-ST | 1 | 2024-10-03 | 2024-10-05 | 2025-07-02 | 2025-07-20
| JD3RZ02-1L69ST6621.R | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-69-ST -R | 1 | 2024-10-15 | 2024-10-16 | 2025-08-26 | 2025-08-27
| JD3RZ02-1L69ST6622 | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-69-ST | 1 | 2024-10-06 | 2024-10-07 | 2025-07-05 | 2025-07-22
| JD3RZ02-1L69ST6622.R | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-69-ST -Remaining | 1 | 2024-10-17 | 2024-10-19 | 2025-08-28 | 2025-08-30
| JD3RZ02-1L69ST6623 | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-69-ST | 1 | 2024-10-20 | 2024-10-21 | 2025-08-30 | 2025-09-17
| JD3RZ02-1L69ST6624 | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-69-ST | 1 | 2024-10-22 | 2024-10-23 | 2025-08-31 | 2025-09-20
| JD3RZ02-1L69ST6630 | Excavation Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-1-L-69-ST | 1 | 2024-10-03 | 2024-10-05 | 2025-06-30 | 2025-07-17
| JD3RZ02-1L69ST6631 | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-1-L-69-ST | 1 | 2024-10-06 | 2024-10-07 | 2025-07-02 | 2025-07-20
| JD3RZ02-1L69ST6632 | Installing for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-1-L-69-ST | 1 | 2024-10-08 | 2024-10-09 | 2025-07-05 | 2025-07-22
| JD3RZ02-1L69ST6633 | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-1-L-69-ST | 1 | 2024-10-22 | 2024-10-23 | 2025-08-26 | 2025-08-27
| JD3RZ02-1L69ST6634 | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-1-L-69-ST | 1 | 2024-10-24 | 2024-10-26
| JD3RZ02-1L69ST6640 | Excavation Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z02-1-L-69-ST | 1 | 2024-10-06 | 2024-10-07 | 2025-05-10 | 2025-05-27
| JD3RZ02-1L69ST6641 | Soil Replacement and Bedding Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z02-1-L-69-ST | 1 | 2024-10-08 | 2024-10-09 | 2025-05-11 | 2025-05-28
| JD3RZ02-1L69ST6642 | Installing for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z02-1-L-69-ST | 1 | 2024-10-10 | 2024-10-12 | 2025-05-15 | 2025-06-02
| JD3RZ02-1L69ST6643 | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z02-1-L-69-ST | 1 | 2024-10-24 | 2024-10-26 | 2025-08-20 | 2025-08-21
| JD3RZ02-1L69ST6644 | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z02-1-L-69-ST | 1 | 2024-10-27 | 2024-10-28 | 2025-08-23 | 2025-08-24
| JD3RZ02-1L69ST6655 | Excavation Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z02-1-L-69-ST | 1 | 2024-10-08 | 2024-10-09 | 2025-05-10 | 2025-05-27
| JD3RZ02-1L69ST6656 | Soil Replacement and Bedding Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z02-1-L-69-ST | 1 | 2024-10-10 | 2024-10-12 | 2025-05-11 | 2025-05-28
| JD3RZ02-1L69ST6657 | Installing for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z02-1-L-69-ST | 1 | 2024-10-13 | 2024-10-14 | 2025-06-15 | 2025-07-02
| JD3RZ02-1L69ST6658 | Primary Test for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z02-1-L-69-ST | 1 | 2024-10-27 | 2024-10-28 | 2025-08-21 | 2025-08-23
| JD3RZ02-1L69ST6659 | Backfilling Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z02-1-L-69-ST | 1 | 2024-10-29 | 2024-10-30 | 2025-08-25 | 2025-08-26
| JD3RZ02-1L69ST6763 | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-1-L-69-ST | 1 | 2024-10-17 | 2024-10-19 | 2025-08-17
| JD3RZ02-1L69ST6764 | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-1-L-69-ST | 1 | 2024-10-20 | 2024-10-21 | 2025-08-19
| JD3RZ02-1L69ST6765 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-1-L-69-ST | 1 | 2024-10-22 | 2024-10-23 | 2025-09-17
| JD3RZ02-1L69ST6766 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-1-L-69-ST | 1 | 2024-10-24 | 2024-10-26
| JD3RZ02-1L69ST6767 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-1-L-69-ST | 1 | 2024-10-27 | 2024-10-28
| JD3RZ02-1L69ST6773 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-1-L-69-ST | 1 | 2024-10-03 | 2024-10-05 | 2025-05-10 | 2025-05-27
| JD3RZ02-1L69ST6773.R | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-1-L-69-ST -Remaining | 1 | 2024-10-20 | 2024-10-21 | 2025-09-03 | 2025-09-06
| JD3RZ02-1L69ST6774 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-1-L-69-ST | 1 | 2024-10-06 | 2024-10-07 | 2025-05-25 | 2025-06-11
| JD3RZ02-1L69ST6774.R | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-1-L-69-ST -Remaining | 1 | 2024-10-22 | 2024-10-23 | 2025-09-07 | 2025-09-10
| JD3RZ02-1L69ST6775 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-1-L-69-ST | 1 | 2024-10-08 | 2024-10-09 | 2025-06-16 | 2025-07-03
| JD3RZ02-1L69ST6775.R | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-1-L-69-ST -Remaining | 1 | 2024-10-24 | 2024-10-26 | 2025-09-11
| JD3RZ02-1L69ST6776 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-1-L-69-ST | 1 | 2024-10-27 | 2024-10-28
| JD3RZ02-1L69ST6777 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-1-L-69-ST | 1 | 2024-10-29 | 2024-10-30
| JD3RZ02-1L69ST6778 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-1-L-69-ST | 1 | 2024-10-20 | 2024-10-21 | 2025-09-16
| JD3RZ02-1L69ST6779 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-1-L-69-ST | 1 | 2024-10-22 | 2024-10-23 | 2025-09-18
| JD3RZ02-1L69ST6780 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-1-L-69-ST | 1 | 2024-10-24 | 2024-10-26
| JD3RZ02-1L69ST6781 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-1-L-69-ST | 1 | 2024-10-27 | 2024-10-28
| JD3RZ02-1L69ST6782 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-1-L-69-ST | 1 | 2024-10-29 | 2024-10-30
| JD3RZ02-1L69ST6788 | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z02-1-L-69-ST | 1 | 2024-10-22 | 2024-10-23 | 2025-05-10 | 2025-06-15
| JD3RZ02-1L69ST6789 | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z02-1-L-69-ST | 1 | 2024-10-24 | 2024-10-26 | 2025-05-12 | 2025-07-24
| JD3RZ02-1L69ST6790 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z02-1-L-69-ST | 1 | 2024-10-27 | 2024-10-28 | 2025-06-30 | 2025-07-31
| JD3RZ02-1L69ST6790.R | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z02-1-L-69-ST -Remaining | 1 | 2024-10-29 | 2024-10-30
| JD3RZ02-1L69ST6791 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z02-1-L-69-ST | 1 | 2024-10-31 | 2024-11-02
| JD3RZ02-1L69ST6792 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z02-1-L-69-ST | 1 | 2024-11-03 | 2024-11-04
| JD3RZ02-1L69ST6798 | EXCAVATION Works for Catchbasine single - - B6.33 05 39.09-Z02-1-L-69-ST | 1 | 2024-10-22 | 2024-10-23
| JD3RZ02-1L69ST6799 | Catchbasine Installation Works For Catchbasine single - - B6.33 05 39.09-Z02-1-L-69-ST | 1 | 2024-10-24 | 2024-10-27
| JD3RZ02-1L69ST6800 | FINISHING Works For Catchbasine single - - B6.33 05 39.09-Z02-1-L-69-ST | 1 | 2024-10-28 | 2024-10-30
| JD3RZ02-1L69ST6801 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - - B6.33 05 39.09-Z02-1-L-69-ST | 1 | 2024-10-31 | 2024-11-02
| JD3RZ02-1L69ST6802 | EXCAVATION Works for Catchbasine double - - B6.33 05 39.10-Z02-1-L-69-ST | 1 | 2024-10-24 | 2024-10-26
| JD3RZ02-1L69ST6803 | Catchbasine Installation Works For Catchbasine double - - B6.33 05 39.10-Z02-1-L-69-ST | 1 | 2024-10-27 | 2024-10-29
| JD3RZ02-1L69ST6804 | FINISHING Works For Catchbasine double - - B6.33 05 39.10-Z02-1-L-69-ST | 1 | 2024-10-30 | 2024-11-02
| JD3RZ02-1L69ST6805 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - - B6.33 05 39.10-Z02-1-L-69-ST | 1 | 2024-11-03 | 2024-11-04
| JD3RZ02-1L69TC7136 | Excavation Worksfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z02-1-L-69-TC | 1 | 2025-01-16 | 2025-01-18
| JD3RZ02-1L69TC7137 | Installationfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z02-1-L-69-TC | 1 | 2025-01-19 | 2025-01-22
| JD3RZ02-1L69TC7138 | Pouring Concrete Coverfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z02-1-L-69-TC | 1 | 2025-01-23 | 2025-01-27
| JD3RZ02-1L69TC7139 | Backfilling Worksfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z02-1-L-69-TC | 1 | 2025-04-09 | 2025-04-10
| JD3RZ02-1L69TC7140 | Excavation and Bedding Worksfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z02-1-L-69-TC | 1 | 2025-01-19 | 2025-01-20
| JD3RZ02-1L69TC7141 | Installationfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z02-1-L-69-TC | 1 | 2025-01-21 | 2025-01-22
| JD3RZ02-1L69TC7142 | Backfilling Worksfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z02-1-L-69-TC | 1 | 2025-01-23 | 2025-01-25
| JD3RZ02-1L69TSE6856 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-1-L-69-TSE | 1 | 2024-11-05 | 2024-11-06
| JD3RZ02-1L69TSE6857 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-1-L-69-TSE | 1 | 2024-11-07 | 2024-11-09
| JD3RZ02-1L69TSE6858 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-1-L-69-TSE | 1 | 2024-12-07 | 2024-12-08
| JD3RZ02-1L69TSE6859 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-1-L-69-TSE | 1 | 2024-12-09 | 2024-12-10
| JD3RZ02-1L69TSE6860 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-1-L-69-TSE | 1 | 2024-12-23 | 2024-12-24
| JD3RZ02-1L69TSE6861 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-1-L-69-TSE | 1 | 2024-11-07 | 2024-11-11 | 2025-08-16 | 2025-08-26
| JD3RZ02-1L69TSE6862 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-1-L-69-TSE | 1 | 2024-11-12 | 2024-11-17 | 2025-08-16 | 2025-08-26
| JD3RZ02-1L69TSE6863 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-1-L-69-TSE | 1 | 2024-12-07 | 2024-12-15 | 2025-09-03
| JD3RZ02-1L69TSE6864 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-1-L-69-TSE | 1 | 2024-12-16 | 2024-12-21 | 2025-09-06
| JD3RZ02-1L69TSE6865 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-1-L-69-TSE | 1 | 2024-12-25 | 2024-12-30 | 2025-09-09
| JD3RZ02-1L69TSE6981 | Installationfor gate valves 100 mm - - B4.33 14 19.01-Z02-1-L-69-TSE | 1 | 2024-12-16 | 2024-12-18
| JD3RZ02-1L69TSE6982 | Testing And Commtionningfor gate valves 100 mm - - B4.33 14 19.01-Z02-1-L-69-TSE | 1 | 2024-12-19 | 2024-12-22
| JD3RZ02-1L69TSE6983 | Installationfor gate valves 250 mm - - B4.33 14 19.02-Z02-1-L-69-TSE | 1 | 2024-12-16 | 2024-12-17
| JD3RZ02-1L69TSE6984 | Testing And Commtionningfor gate valves 250 mm - - B4.33 14 19.02-Z02-1-L-69-TSE | 1 | 2024-12-18 | 2024-12-19
| JD3RZ02-1L69WT6806 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-1-L-69-WT | 1 | 2024-11-12 | 2024-11-17 | 2025-08-20
| JD3RZ02-1L69WT6807 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-1-L-69-WT | 1 | 2024-11-18 | 2024-11-23 | 2025-08-26
| JD3RZ02-1L69WT6808 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-1-L-69-WT | 1 | 2024-11-24 | 2024-12-03 | 2025-09-03
| JD3RZ02-1L69WT6809 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-1-L-69-WT | 1 | 2024-12-04 | 2024-12-10
| JD3RZ02-1L69WT6810 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-1-L-69-WT | 1 | 2025-01-11 | 2025-01-16
| JD3RZ02-1L69WT6831 | INSTALLATIONfor gate valves 150 mm - - B3.33 14 19.01-Z02-1-L-69-WT | 1 | 2025-01-04 | 2025-01-06
| JD3RZ02-1L69WT6832 | TESTING AND COMMITIONfor gate valves 150 mm - - B3.33 14 19.01-Z02-1-L-69-WT | 1 | 2025-01-07 | 2025-01-09
| JD3RZ02-1L69WT6837 | INSTALLATIONfor Wash-Out Valve 100 mm - - B3.33 14 19.05-Z02-1-L-69-WT | 1 | 2025-01-04 | 2025-01-05
| JD3RZ02-1L69WT6838 | TESTING AND COMMITIONfor Wash-Out Valve 100 mm - - B3.33 14 19.05-Z02-1-L-69-WT | 1 | 2025-01-06 | 2025-01-07
| JD3RZ02-1L69WT6841 | EXCAVATION and Bedding Worksfor Fire Hydrant - - B3.33 14 19.08-Z02-1-L-69-WT | 1 | 2024-12-25 | 2024-12-26
| JD3RZ02-1L69WT6842 | INSTALLATIONfor Fire Hydrant - - B3.33 14 19.08-Z02-1-L-69-WT | 1 | 2024-12-28 | 2024-12-29
| JD3RZ02-1L69WT6843 | TESTING AND COMMITIONfor Fire Hydrant - - B3.33 14 19.08-Z02-1-L-69-WT | 1 | 2024-12-30 | 2024-12-31
| JD3RZ02-1L69WT6848 | EXCAVATION and Bedding Worksfor Wash-out Valve Chamber - 110 to 400 MM- B3.33 14 13.06-Z02-1-L-69-WT | 1 | 2024-12-28 | 2024-12-29
| JD3RZ02-1L69WT6849 | Plain Concrete Worksfor Wash-out Valve Chamber - 110 to 400 MM- B3.33 14 13.06-Z02-1-L-69-WT | 1 | 2024-12-30 | 2024-12-31
| JD3RZ02-1L69WT6850 | INSTALLATIONfor Wash-out Valve Chamber - 110 to 400 MM- B3.33 14 13.06-Z02-1-L-69-WT | 1 | 2025-01-01 | 2025-01-02
| JD3RZ02-1L69WT6851 | Backfilling Worksfor Wash-out Valve Chamber - 110 to 400 MM- B3.33 14 13.06-Z02-1-L-69-WT | 1 | 2025-01-11 | 2025-01-12
| JD3RZ02-1L70TSE7569 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-1-L-70-TSE | 1 | 2024-12-07 | 2024-12-10 | 2025-08-23
| JD3RZ02-1L70TSE7570 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-1-L-70-TSE | 1 | 2024-12-11 | 2024-12-15 | 2025-09-03
| JD3RZ02-1L70TSE7571 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-1-L-70-TSE | 1 | 2024-12-16 | 2024-12-23 | 2025-09-06
| JD3RZ02-1L70TSE7572 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-1-L-70-TSE | 1 | 2024-12-24 | 2024-12-29 | 2025-09-09
| JD3RZ02-1L70TSE7573 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-1-L-70-TSE | 1 | 2024-12-30 | 2025-01-04 | 2025-09-14
| JD3RZ02-1L70TSE7574 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-1-L-70-TSE | 1 | 2024-12-11 | 2024-12-12
| JD3RZ02-1L70TSE7575 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-1-L-70-TSE | 1 | 2024-12-14 | 2024-12-15
| JD3RZ02-1L70TSE7576 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-1-L-70-TSE | 1 | 2024-12-16 | 2024-12-17
| JD3RZ02-1L70TSE7577 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-1-L-70-TSE | 1 | 2024-12-18 | 2024-12-19
| JD3RZ02-1L70TSE7578 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-1-L-70-TSE | 1 | 2024-12-29 | 2024-12-30
| JD3RZ02-1L70TSE7694 | Installationfor gate valves 100 mm - - B4.33 14 19.01-Z02-1-L-70-TSE | 1 | 2024-12-24 | 2024-12-25
| JD3RZ02-1L70TSE7695 | Testing And Commtionningfor gate valves 100 mm - - B4.33 14 19.01-Z02-1-L-70-TSE | 1 | 2024-12-26 | 2024-12-28
| JD3RZ02-1L71SL8505 | Excavation Worksfor Copper Cables 4Cx25 mm² - - B2.26 05 19.04-Z02-1-L-71-SL | 1 | 2025-04-20 | 2025-04-22
| JD3RZ02-1L71SL8506 | Installationfor Copper Cables 4Cx25 mm² - - B2.26 05 19.04-Z02-1-L-71-SL | 1 | 2025-04-23 | 2025-04-26
| JD3RZ02-1L71SL8507 | Backfilling, Warning Tabe Worksfor Copper Cables 4Cx25 mm² - - B2.26 05 19.04-Z02-1-L-71-SL | 1 | 2025-04-27 | 2025-04-29
| JD3RZ02-1L71SL8508 | Testing and Commitioning for Copper Cables 4Cx25 mm² - - B2.26 05 19.04-Z02-1-L-71-SL | 1 | 2025-05-05 | 2025-05-07
| JD3RZ02-1L71SL8519 | INSTALLINGfor insulated copper conductor 16 mm² - - B2.26 05 19.08-Z02-1-L-71-SL | 1 | 2025-04-28 | 2025-04-30
| JD3RZ02-1L71SL8520 | TESTING AND COMMITIONINGfor insulated copper conductor 16 mm² - - B2.26 05 19.08-Z02-1-L-71-SL | 1 | 2025-05-01 | 2025-05-04
| JD3RZ02-1L71SL8526 | Excavation of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-1-L-71-SL | 1 | 2025-04-23 | 2025-04-24
| JD3RZ02-1L71SL8527 | Installation of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-1-L-71-SL | 1 | 2025-04-26 | 2025-04-27
| JD3RZ02-1L71SL8528 | Backfilling of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-1-L-71-SL | 1 | 2025-04-28 | 2025-04-29
| JD3RZ02-1L71SL8529 | Installation Worksfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-1-L-71-SL | 1 | 2025-04-30 | 2025-05-04
| JD3RZ02-1L71SL8530 | Testing and Commitioningfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-1-L-71-SL | 1 | 2025-05-07 | 2025-05-11
| JD3RZ02-1L71SL8531 | Installationfor Lighting( LED ) Luminaire 150 WATT - - B2.26.56.19.01-Z02-1-L-71-SL | 1 | 2025-05-05 | 2025-05-06
| JD3RZ02-1L71SL8535 | Excavation Worksfor PVC Pipes 2×150mm - - B2.33 71 19.01.SL-Z02-1-L-71-SL | 1 | 2025-04-26 | 2025-04-27
| JD3RZ02-1L71SL8536 | Installationfor PVC Pipes 2×150mm - - B2.33 71 19.01.SL-Z02-1-L-71-SL | 1 | 2025-04-28 | 2025-04-29
| JD3RZ02-1L71SL8537 | Pouring Concrete Coverfor PVC Pipes 2×150mm - - B2.33 71 19.01.SL-Z02-1-L-71-SL | 1 | 2025-04-30 | 2025-05-01
| JD3RZ02-1L71SL8538 | Testing and Backfilling Worksfor PVC Pipes 2×150mm - - B2.33 71 19.01.SL-Z02-1-L-71-SL | 1 | 2025-05-05 | 2025-05-06
| JD3RZ02-1L71SL8547 | Excavationfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z02-1-L-71-SL | 1 | 2025-04-28 | 2025-04-29
| JD3RZ02-1L71SL8548 | Installationfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z02-1-L-71-SL | 1 | 2025-04-30 | 2025-05-01
| JD3RZ02-1L71SL8549 | Backfillingfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z02-1-L-71-SL | 1 | 2025-05-05 | 2025-05-06
| JD3RZ02-1L71SL8550 | Excavationfor Drawpit 900x900x1200mm - - B2.33 71 19.13.02-Z02-1-L-71-SL | 1 | 2025-04-30 | 2025-05-01
| JD3RZ02-1L71SL8551 | Installationfor Drawpit 900x900x1200mm - - B2.33 71 19.13.02-Z02-1-L-71-SL | 1 | 2025-05-03 | 2025-05-04
| JD3RZ02-1L71SL8552 | Backfillingfor Drawpit 900x900x1200mm - - B2.33 71 19.13.02-Z02-1-L-71-SL | 1 | 2025-05-05 | 2025-05-06
| JD3RZ02-1L71SS521401 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2025-01-08 | 2025-01-09 | 2025-08-02
| JD3RZ02-1L71SS521411 | Installation of Base Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2025-01-11 | 2025-01-12 | 2025-08-04
| JD3RZ02-1L71SS521421 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03 | 1 | 2025-01-13 | 2025-01-14
| JD3RZ02-1L71SS521431 | Backfilling Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2025-01-15 | 2025-01-16
| JD3RZ02-1L71SS521441 | Finishing, Benching Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2025-01-18 | 2025-01-19
| JD3RZ02-1L71SS7880 | Trench excavation for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-71-SS | 1 | 2024-12-29 | 2024-12-30 | 2025-04-06 | 2025-07-31
| JD3RZ02-1L71SS7880.R | Trench excavation for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-71-SS -Remaining | 1 | 2024-12-31 | 2025-01-01 | 2025-08-02 | 2025-08-03
| JD3RZ02-1L71SS7881 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-71-SS | 1 | 2024-12-31 | 2025-01-01 | 2025-04-07 | 2025-07-31
| JD3RZ02-1L71SS7881.R | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-71-SS -Rem | 1 | 2025-01-02 | 2025-01-04 | 2025-08-04 | 2025-08-05
| JD3RZ02-1L71SS7882 | Installing for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-71-SS | 1 | 2025-01-02 | 2025-01-05 | 2025-04-08 | 2025-07-28
| JD3RZ02-1L71SS7882.R | Installing for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-71-SS -Remaining | 1 | 2025-01-06 | 2025-01-07 | 2025-08-06 | 2025-08-07
| JD3RZ02-1L71SS7883 | Primary Test for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-71-SS | 1 | 2025-01-06 | 2025-01-07 | 2025-04-16 | 2025-07-31
| JD3RZ02-1L71SS7883.R | Primary Test for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-71-SS -Remaining | 1 | 2025-01-08 | 2025-01-09 | 2025-08-09 | 2025-08-10
| JD3RZ02-1L71SS7884 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-71-SS | 1 | 2025-01-08 | 2025-01-11 | 2025-05-15 | 2025-07-31
| JD3RZ02-1L71SS7884.R | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-71-SS -Rem | 1 | 2025-01-12 | 2025-01-13 | 2025-08-11 | 2025-08-12
| JD3RZ02-1L71SS7885 | Trench excavation for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-1-L-71-SS | 1 | 2024-12-31 | 2025-01-02 | 2025-04-08 | 2025-05-14
| JD3RZ02-1L71SS7885.R | Trench excavation for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-1-L-71-SS -Remaining | 1 | 2025-01-04 | 2025-01-05 | 2025-08-04 | 2025-08-05
| JD3RZ02-1L71SS7886 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-1-L-71-SS | 1 | 2025-01-04 | 2025-01-06 | 2025-04-16 | 2025-06-01
| JD3RZ02-1L71SS7886.R | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-1-L-71-SS -Rem | 1 | 2025-01-07 | 2025-01-08 | 2025-08-06 | 2025-08-07
| JD3RZ02-1L71SS7887 | Installing for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-1-L-71-SS | 1 | 2025-01-07 | 2025-01-09 | 2025-04-17 | 2025-05-24
| JD3RZ02-1L71SS7887.R | Installing for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-1-L-71-SS -Remaining | 1 | 2025-01-11 | 2025-01-12 | 2025-08-09 | 2025-08-10
| JD3RZ02-1L71SS7888 | Primary Test for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-1-L-71-SS | 1 | 2025-01-11 | 2025-01-13 | 2025-04-20 | 2025-05-26
| JD3RZ02-1L71SS7888.R | Primary Test for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-1-L-71-SS -Remaining | 1 | 2025-01-14 | 2025-01-15 | 2025-08-11 | 2025-08-12
| JD3RZ02-1L71SS7889 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-1-L-71-SS | 1 | 2025-01-14 | 2025-01-18 | 2025-05-15 | 2025-06-21
| JD3RZ02-1L71SS7889.R | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-1-L-71-SS -Rem | 1 | 2025-01-19 | 2025-01-20 | 2025-08-13
| JD3RZ02-1L71SS7922 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z02-1-L-71-SS | 1 | 2025-01-04 | 2025-01-05 | 2025-04-06 | 2025-04-23
| JD3RZ02-1L71SS7923 | Installation of Base Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z02-1-L-71-SS | 1 | 2025-01-06 | 2025-01-07 | 2025-04-20 | 2025-05-07
| JD3RZ02-1L71SS7924 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z02-1-L | 1 | 2025-01-08 | 2025-01-09
| JD3RZ02-1L71SS7925 | Backfilling Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z02-1-L-71-SS | 1 | 2025-01-11 | 2025-01-12
| JD3RZ02-1L71SS7926 | Finishing, Benching Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z02-1-L-71-SS | 1 | 2025-01-13 | 2025-01-14
| JD3RZ02-1L71SS7934 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-1-L-71-SS | 1 | 2025-01-06 | 2025-01-07 | 2025-04-08 | 2025-04-26
| JD3RZ02-1L71SS7934.R | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-1-L-71-SS -Remaining | 1 | 2025-01-08 | 2025-01-09 | 2025-08-02 | 2025-08-03
| JD3RZ02-1L71SS7935 | Installation of Base Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-1-L-71-SS | 1 | 2025-01-08 | 2025-01-09 | 2025-04-20 | 2025-05-07
| JD3RZ02-1L71SS7935.R | Installation of Base Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-1-L-71-SS -Remaining | 1 | 2025-01-11 | 2025-01-12 | 2025-08-04 | 2025-08-05
| JD3RZ02-1L71SS7936 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-1-L | 1 | 2025-01-13 | 2025-01-14
| JD3RZ02-1L71SS7937 | Backfilling Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-1-L-71-SS | 1 | 2025-01-15 | 2025-01-16
| JD3RZ02-1L71SS7938 | Finishing, Benching Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-1-L-71-SS | 1 | 2025-01-18 | 2025-01-19
| JD3RZ02-1L71ST8006 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-1-L-71-ST | 1 | 2025-01-21 | 2025-01-23
| JD3RZ02-1L71ST8007 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-1-L-71-ST | 1 | 2025-01-25 | 2025-01-27
| JD3RZ02-1L71ST8008 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-1-L-71-ST | 1 | 2025-01-28 | 2025-02-01
| JD3RZ02-1L71ST8009 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-1-L-71-ST | 1 | 2025-02-02 | 2025-02-05
| JD3RZ02-1L71ST8010 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-1-L-71-ST | 1 | 2025-02-06 | 2025-02-11
| JD3RZ02-1L71ST8011 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-1-L-71-ST | 1 | 2025-01-25 | 2025-01-26
| JD3RZ02-1L71ST8012 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-1-L-71-ST | 1 | 2025-01-27 | 2025-01-28
| JD3RZ02-1L71ST8013 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-1-L-71-ST | 1 | 2025-01-29 | 2025-01-30
| JD3RZ02-1L71ST8014 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-1-L-71-ST | 1 | 2025-02-01 | 2025-02-02
| JD3RZ02-1L71ST8015 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-1-L-71-ST | 1 | 2025-02-03 | 2025-02-04
| JD3RZ02-1L71ST8016 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-1-L-71-ST | 1 | 2025-01-08 | 2025-01-09 | 2025-04-05 | 2025-04-22
| JD3RZ02-1L71ST8016.R | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-1-L-71-ST -Remaining | 1 | 2025-01-27 | 2025-01-28
| JD3RZ02-1L71ST8017 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-1-L-71-ST | 1 | 2025-01-11 | 2025-01-12 | 2025-04-07 | 2025-04-24
| JD3RZ02-1L71ST8017.R | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-1-L-71-ST -R | 1 | 2025-01-29 | 2025-01-30
| JD3RZ02-1L71ST8018 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-1-L-71-ST | 1 | 2025-01-13 | 2025-01-14 | 2025-04-09 | 2025-04-27
| JD3RZ02-1L71ST8018.R | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-1-L-71-ST -Remaining | 1 | 2025-02-01 | 2025-02-02
| JD3RZ02-1L71ST8019 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-1-L-71-ST | 1 | 2025-02-03 | 2025-02-04 | 2025-08-25
| JD3RZ02-1L71ST8020 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-1-L-71-ST | 1 | 2025-02-05 | 2025-02-06 | 2025-08-30
| JD3RZ02-1L71ST8026 | Excavation Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z02-1-L-71-ST | 1 | 2025-01-11 | 2025-01-12 | 2025-06-11 | 2025-06-29
| JD3RZ02-1L71ST8027 | Soil Replacement and Bedding Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z02-1-L-71-ST | 1 | 2025-01-13 | 2025-01-14 | 2025-06-12 | 2025-06-30
| JD3RZ02-1L71ST8028 | Installing for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z02-1-L-71-ST | 1 | 2025-01-15 | 2025-01-16 | 2025-06-14 | 2025-07-01
| JD3RZ02-1L71ST8029 | Primary Test for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z02-1-L-71-ST | 1 | 2025-01-18 | 2025-01-19 | 2025-06-16 | 2025-07-03
| JD3RZ02-1L71ST8030 | Backfilling Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z02-1-L-71-ST | 1 | 2025-01-20 | 2025-01-21 | 2025-06-17 | 2025-07-05
| JD3RZ02-1L71ST8036 | Excavation Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-1-L-71-ST | 1 | 2025-01-13 | 2025-01-14 | 2025-04-06 | 2025-04-23
| JD3RZ02-1L71ST8037 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-1-L-71-ST | 1 | 2025-01-15 | 2025-01-16 | 2025-04-07 | 2025-04-24
| JD3RZ02-1L71ST8038 | Installing for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-1-L-71-ST | 1 | 2025-01-18 | 2025-01-19 | 2025-04-08 | 2025-05-05
| JD3RZ02-1L71ST8039 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-1-L-71-ST | 1 | 2025-01-20 | 2025-01-21 | 2025-05-12 | 2025-06-08
| JD3RZ02-1L71ST8039.R | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-1-L-71-ST -Remaining | 1 | 2025-02-05 | 2025-02-06 | 2025-08-21 | 2025-08-23
| JD3RZ02-1L71ST8040 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-1-L-71-ST | 1 | 2025-02-08 | 2025-02-09 | 2025-08-24 | 2025-08-25
| JD3RZ02-1L71ST8046 | Excavation Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-71-ST | 1 | 2025-01-22 | 2025-01-23 | 2025-06-11 | 2025-06-29
| JD3RZ02-1L71ST8046.R | Excavation Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-71-ST -Remaining | 1 | 2025-01-29 | 2025-01-30
| JD3RZ02-1L71ST8047 | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-71-ST | 1 | 2025-01-25 | 2025-01-26 | 2025-06-12 | 2025-06-30
| JD3RZ02-1L71ST8047.R | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-71-ST -R | 1 | 2025-02-01 | 2025-02-02
| JD3RZ02-1L71ST8048 | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-71-ST | 1 | 2025-01-27 | 2025-01-28 | 2025-06-14 | 2025-07-01
| JD3RZ02-1L71ST8048.R | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-71-ST -Remaining | 1 | 2025-02-03 | 2025-02-04
| JD3RZ02-1L71ST8049 | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-71-ST | 1 | 2025-01-29 | 2025-01-30 | 2025-06-16 | 2025-07-03
| JD3RZ02-1L71ST8049.R | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-71-ST -Remaining | 1 | 2025-02-05 | 2025-02-06
| JD3RZ02-1L71ST8050 | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-71-ST | 1 | 2025-02-01 | 2025-02-02 | 2025-06-17 | 2025-07-05
| JD3RZ02-1L71ST8050.R | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-71-ST -Remaining | 1 | 2025-02-10 | 2025-02-11
| JD3RZ02-1L71ST8056 | Excavation Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-1-L-71-ST | 1 | 2025-01-25 | 2025-01-26 | 2025-04-06 | 2025-04-23
| JD3RZ02-1L71ST8057 | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-1-L-71-ST | 1 | 2025-01-27 | 2025-01-28 | 2025-04-07 | 2025-04-24
| JD3RZ02-1L71ST8058 | Installing for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-1-L-71-ST | 1 | 2025-01-29 | 2025-01-30 | 2025-04-15 | 2025-05-12
| JD3RZ02-1L71ST8059 | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-1-L-71-ST | 1 | 2025-02-01 | 2025-02-02 | 2025-05-18 | 2025-06-14
| JD3RZ02-1L71ST8060 | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-1-L-71-ST | 1 | 2025-02-03 | 2025-02-05 | 2025-05-19 | 2025-06-15
| JD3RZ02-1L71ST8060.R | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-1-L-71-ST -Remaining | 1 | 2025-02-06 | 2025-02-08 | 2025-08-26 | 2025-08-27
| JD3RZ02-1L71ST8066 | Excavation Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z02-1-L-71-ST | 1 | 2025-01-27 | 2025-01-28 | 2025-04-12 | 2025-04-29
| JD3RZ02-1L71ST8067 | Soil Replacement and Bedding Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z02-1-L-71-ST | 1 | 2025-01-29 | 2025-01-30 | 2025-04-14 | 2025-05-01
| JD3RZ02-1L71ST8068 | Installing for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z02-1-L-71-ST | 1 | 2025-02-01 | 2025-02-02 | 2025-04-15 | 2025-05-03
| JD3RZ02-1L71ST8069 | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z02-1-L-71-ST | 1 | 2025-02-03 | 2025-02-04 | 2025-05-11 | 2025-05-28
| JD3RZ02-1L71ST8070 | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z02-1-L-71-ST | 1 | 2025-02-05 | 2025-02-06 | 2025-05-12 | 2025-05-29
| JD3RZ02-1L71ST8081 | Excavation Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z02-1-L-71-ST | 1 | 2025-01-29 | 2025-01-30 | 2025-06-11 | 2025-06-29
| JD3RZ02-1L71ST8082 | Soil Replacement and Bedding Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z02-1-L-71-ST | 1 | 2025-02-01 | 2025-02-02 | 2025-06-12 | 2025-06-30
| JD3RZ02-1L71ST8083 | Installing for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z02-1-L-71-ST | 1 | 2025-02-03 | 2025-02-04 | 2025-06-14 | 2025-07-01
| JD3RZ02-1L71ST8084 | Primary Test for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z02-1-L-71-ST | 1 | 2025-02-05 | 2025-02-06 | 2025-06-16 | 2025-07-03
| JD3RZ02-1L71ST8085 | Backfilling Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z02-1-L-71-ST | 1 | 2025-02-08 | 2025-02-09 | 2025-06-17 | 2025-07-05
| JD3RZ02-1L71ST8096 | Excavation Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z02-1-L-71-ST | 1 | 2025-02-01 | 2025-02-02 | 2025-06-01 | 2025-06-18
| JD3RZ02-1L71ST8097 | Soil Replacement and Bedding Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z02-1-L-71-ST | 1 | 2025-02-03 | 2025-02-04 | 2025-06-02 | 2025-06-19
| JD3RZ02-1L71ST8098 | Installing for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z02-1-L-71-ST | 1 | 2025-02-05 | 2025-02-06 | 2025-06-03 | 2025-06-30
| JD3RZ02-1L71ST8099 | Primary Test for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z02-1-L-71-ST | 1 | 2025-02-08 | 2025-02-09 | 2025-06-16 | 2025-07-13
| JD3RZ02-1L71ST8100 | Backfilling Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z02-1-L-71-ST | 1 | 2025-02-10 | 2025-02-12 | 2025-06-17 | 2025-07-14
| JD3RZ02-1L71ST8189 | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-1-L-71-ST | 1 | 2025-02-06 | 2025-02-08 | 2025-04-15 | 2025-05-03
| JD3RZ02-1L71ST8189.R | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-1-L-71-ST -Remaining | 1 | 2025-02-09 | 2025-02-10
| JD3RZ02-1L71ST8190 | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-1-L-71-ST | 1 | 2025-02-09 | 2025-02-10 | 2025-05-11 | 2025-05-28
| JD3RZ02-1L71ST8190.R | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-1-L-71-ST -Remaining | 1 | 2025-02-11 | 2025-02-12
| JD3RZ02-1L71ST8191 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-1-L-71-ST | 1 | 2025-02-11 | 2025-02-12 | 2025-06-16 | 2025-07-03
| JD3RZ02-1L71ST8191.R | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-1-L-71-ST -Remaining | 1 | 2025-02-13 | 2025-02-15
| JD3RZ02-1L71ST8192 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-1-L-71-ST | 1 | 2025-02-16 | 2025-02-17
| JD3RZ02-1L71ST8193 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-1-L-71-ST | 1 | 2025-02-18 | 2025-02-19
| JD3RZ02-1L71ST8199 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-1-L-71-ST | 1 | 2025-02-09 | 2025-02-10 | 2025-04-15 | 2025-05-03
| JD3RZ02-1L71ST8200 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-1-L-71-ST | 1 | 2025-02-11 | 2025-02-12 | 2025-06-16 | 2025-07-03
| JD3RZ02-1L71ST8201 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-1-L-71-ST | 1 | 2025-02-13 | 2025-02-15 | 2025-06-30 | 2025-07-17
| JD3RZ02-1L71ST8201.R | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-1-L-71-ST -Remaining | 1 | 2025-02-16 | 2025-02-17
| JD3RZ02-1L71ST8202 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-1-L-71-ST | 1 | 2025-02-18 | 2025-02-19
| JD3RZ02-1L71ST8203 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-1-L-71-ST | 1 | 2025-02-20 | 2025-02-22
| JD3RZ02-1L71ST8204 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-1-L-71-ST | 1 | 2025-02-11 | 2025-02-12 | 2025-08-26 | 2025-08-27
| JD3RZ02-1L71ST8205 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-1-L-71-ST | 1 | 2025-02-13 | 2025-02-15 | 2025-08-28 | 2025-08-30
| JD3RZ02-1L71ST8206 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-1-L-71-ST | 1 | 2025-02-16 | 2025-02-17
| JD3RZ02-1L71ST8207 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-1-L-71-ST | 1 | 2025-02-18 | 2025-02-19
| JD3RZ02-1L71ST8208 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-1-L-71-ST | 1 | 2025-02-20 | 2025-02-22
| JD3RZ02-1L71ST8219 | Excavation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z02-1-L-71-ST | 1 | 2025-02-13 | 2025-02-15 | 2025-04-15 | 2025-05-03
| JD3RZ02-1L71ST8220 | Base Plain Concrete Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z02-1-L-71-ST | 1 | 2025-02-16 | 2025-02-17 | 2025-06-16 | 2025-07-03
| JD3RZ02-1L71ST8221 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z02-1-L-71-ST | 1 | 2025-02-18 | 2025-02-19 | 2025-06-30 | 2025-07-17
| JD3RZ02-1L71ST8221.R | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z02-1-L-71-ST -Remaining | 1 | 2025-02-20 | 2025-02-22 | 2025-08-20
| JD3RZ02-1L71ST8222 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z02-1-L-71-ST | 1 | 2025-02-23 | 2025-02-24
| JD3RZ02-1L71ST8223 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z02-1-L-71-ST | 1 | 2025-02-25 | 2025-02-26
| JD3RZ02-1L71ST8224 | EXCAVATION Works for Catchbasine single - - B6.33 05 39.09-Z02-1-L-71-ST | 1 | 2025-02-13 | 2025-02-15
| JD3RZ02-1L71ST8225 | Catchbasine Installation Works For Catchbasine single - - B6.33 05 39.09-Z02-1-L-71-ST | 1 | 2025-02-16 | 2025-02-18
| JD3RZ02-1L71ST8226 | FINISHING Works For Catchbasine single - - B6.33 05 39.09-Z02-1-L-71-ST | 1 | 2025-02-19 | 2025-02-22
| JD3RZ02-1L71ST8227 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - - B6.33 05 39.09-Z02-1-L-71-ST | 1 | 2025-02-23 | 2025-02-24
| JD3RZ02-1L71ST8228 | EXCAVATION Works for Catchbasine double - - B6.33 05 39.10-Z02-1-L-71-ST | 1 | 2025-02-16 | 2025-02-17
| JD3RZ02-1L71ST8229 | Catchbasine Installation Works For Catchbasine double - - B6.33 05 39.10-Z02-1-L-71-ST | 1 | 2025-02-18 | 2025-02-20
| JD3RZ02-1L71ST8230 | FINISHING Works For Catchbasine double - - B6.33 05 39.10-Z02-1-L-71-ST | 1 | 2025-02-22 | 2025-02-24
| JD3RZ02-1L71ST8231 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - - B6.33 05 39.10-Z02-1-L-71-ST | 1 | 2025-02-27 | 2025-03-01
| JD3RZ02-1L71TC8562 | Excavation Worksfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z02-1-L-71-TC | 1 | 2025-04-20 | 2025-04-21
| JD3RZ02-1L71TC8563 | Installationfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z02-1-L-71-TC | 1 | 2025-04-22 | 2025-04-26
| JD3RZ02-1L71TC8564 | Pouring Concrete Coverfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z02-1-L-71-TC | 1 | 2025-04-27 | 2025-04-30
| JD3RZ02-1L71TC8565 | Backfilling Worksfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z02-1-L-71-TC | 1 | 2025-05-01 | 2025-05-03
| JD3RZ02-1L71TC8566 | Excavation and Bedding Worksfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z02-1-L-71-TC | 1 | 2025-04-22 | 2025-04-23
| JD3RZ02-1L71TC8567 | Installationfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z02-1-L-71-TC | 1 | 2025-04-24 | 2025-04-26
| JD3RZ02-1L71TC8568 | Backfilling Worksfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z02-1-L-71-TC | 1 | 2025-04-27 | 2025-04-28
| JD3RZ02-1L71TSE8282 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-1-L-71-TSE | 1 | 2025-03-02 | 2025-03-05 | 2025-08-09
| JD3RZ02-1L71TSE8283 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-1-L-71-TSE | 1 | 2025-03-06 | 2025-03-10 | 2025-08-14
| JD3RZ02-1L71TSE8284 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-1-L-71-TSE | 1 | 2025-03-11 | 2025-03-18 | 2025-08-18
| JD3RZ02-1L71TSE8285 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-1-L-71-TSE | 1 | 2025-03-19 | 2025-03-24 | 2025-08-31
| JD3RZ02-1L71TSE8286 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-1-L-71-TSE | 1 | 2025-03-25 | 2025-03-30 | 2025-08-25
| JD3RZ02-1L71TSE8407 | Installationfor gate valves 100 mm - - B4.33 14 19.01-Z02-1-L-71-TSE | 1 | 2025-03-19 | 2025-03-20
| JD3RZ02-1L71TSE8408 | Testing And Commtionningfor gate valves 100 mm - - B4.33 14 19.01-Z02-1-L-71-TSE | 1 | 2025-03-22 | 2025-03-23
| JD3RZ02-1L71WT8232 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-1-L-71-WT | 1 | 2025-03-11 | 2025-03-15 | 2025-08-25 | 2025-09-02
| JD3RZ02-1L71WT8233 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-1-L-71-WT | 1 | 2025-03-16 | 2025-03-20 | 2025-09-03 | 2025-09-06
| JD3RZ02-1L71WT8234 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-1-L-71-WT | 1 | 2025-03-22 | 2025-03-30 | 2025-09-06 | 2025-09-15
| JD3RZ02-1L71WT8235 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-1-L-71-WT | 1 | 2025-03-31 | 2025-04-05
| JD3RZ02-1L71WT8236 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-1-L-71-WT | 1 | 2025-04-14 | 2025-04-19
| JD3RZ02-1L71WT8237 | Excavation Worksfor HDPE Pipes 225 mm - depth from 0 to 1.5 m- B3.33 14 13.02-Z02-1-L-71-WT | 1 | 2025-03-31 | 2025-04-01
| JD3RZ02-1L71WT8238 | Soil Replacement and Bedding Works for HDPE Pipes 225 mm - depth from 0 to 1.5 m- B3.33 14 13.02-Z02-1-L-71-WT | 1 | 2025-04-02 | 2025-04-03
| JD3RZ02-1L71WT8239 | Installing for HDPE Pipes 225 mm - depth from 0 to 1.5 m- B3.33 14 13.02-Z02-1-L-71-WT | 1 | 2025-04-05 | 2025-04-06
| JD3RZ02-1L71WT8240 | Testing for HDPE Pipes 225 mm - depth from 0 to 1.5 m- B3.33 14 13.02-Z02-1-L-71-WT | 1 | 2025-04-07 | 2025-04-08
| JD3RZ02-1L71WT8241 | Backfillingfor HDPE Pipes 225 mm - depth from 0 to 1.5 m- B3.33 14 13.02-Z02-1-L-71-WT | 1 | 2025-04-14 | 2025-04-15
| JD3RZ02-1L71WT8257 | INSTALLATIONfor gate valves 150 mm - - B3.33 14 19.01-Z02-1-L-71-WT | 1 | 2025-04-07 | 2025-04-08
| JD3RZ02-1L71WT8258 | TESTING AND COMMITIONfor gate valves 150 mm - - B3.33 14 19.01-Z02-1-L-71-WT | 1 | 2025-04-09 | 2025-04-10
| JD3RZ02-1L71WT8267 | EXCAVATION and Bedding Worksfor Fire Hydrant - - B3.33 14 19.08-Z02-1-L-71-WT | 1 | 2025-04-02 | 2025-04-03
| JD3RZ02-1L71WT8268 | INSTALLATIONfor Fire Hydrant - - B3.33 14 19.08-Z02-1-L-71-WT | 1 | 2025-04-05 | 2025-04-06
| JD3RZ02-1L71WT8269 | TESTING AND COMMITIONfor Fire Hydrant - - B3.33 14 19.08-Z02-1-L-71-WT | 1 | 2025-04-12 | 2025-04-13
| JD3RZ02-1L72SL9218 | Excavation Worksfor Copper Cables 4Cx25 mm² - - B2.26 05 19.04-Z02-1-L-72-SL | 1 | 2025-03-26 | 2025-03-29
| JD3RZ02-1L72SL9219 | Installationfor Copper Cables 4Cx25 mm² - - B2.26 05 19.04-Z02-1-L-72-SL | 1 | 2025-03-30 | 2025-04-01
| JD3RZ02-1L72SL9220 | Backfilling, Warning Tabe Worksfor Copper Cables 4Cx25 mm² - - B2.26 05 19.04-Z02-1-L-72-SL | 1 | 2025-04-02 | 2025-04-05
| JD3RZ02-1L72SL9221 | Testing and Commitioning for Copper Cables 4Cx25 mm² - - B2.26 05 19.04-Z02-1-L-72-SL | 1 | 2025-04-09 | 2025-04-12
| JD3RZ02-1L72SL9232 | INSTALLINGfor insulated copper conductor 16 mm² - - B2.26 05 19.08-Z02-1-L-72-SL | 1 | 2025-04-02 | 2025-04-05
| JD3RZ02-1L72SL9233 | TESTING AND COMMITIONINGfor insulated copper conductor 16 mm² - - B2.26 05 19.08-Z02-1-L-72-SL | 1 | 2025-04-06 | 2025-04-08
| JD3RZ02-1L72SL9239 | Excavation of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-1-L-72-SL | 1 | 2025-03-30 | 2025-03-31
| JD3RZ02-1L72SL9240 | Installation of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-1-L-72-SL | 1 | 2025-04-01 | 2025-04-02
| JD3RZ02-1L72SL9241 | Backfilling of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-1-L-72-SL | 1 | 2025-04-03 | 2025-04-05
| JD3RZ02-1L72SL9242 | Installation Worksfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-1-L-72-SL | 1 | 2025-04-06 | 2025-04-09
| JD3RZ02-1L72SL9243 | Testing and Commitioningfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-1-L-72-SL | 1 | 2025-04-10 | 2025-04-14
| JD3RZ02-1L72SL9244 | Installationfor Lighting( LED ) Luminaire 150 WATT - - B2.26.56.19.01-Z02-1-L-72-SL | 1 | 2025-04-10 | 2025-04-12
| JD3RZ02-1L72SL9247 | Supply, construct, connect and test earthing pitsfor Street Lighting EARTHING SYSTEM - - B2.26 05 26.01-Z02-1-L-72-SL | 1 | 2025-04-10 | 2025-04-12
| JD3RZ02-1L72SL9248 | Excavation Worksfor PVC Pipes 2×150mm - - B2.33 71 19.01.SL-Z02-1-L-72-SL | 1 | 2025-04-01 | 2025-04-02
| JD3RZ02-1L72SL9249 | Installationfor PVC Pipes 2×150mm - - B2.33 71 19.01.SL-Z02-1-L-72-SL | 1 | 2025-04-03 | 2025-04-05
| JD3RZ02-1L72SL9250 | Pouring Concrete Coverfor PVC Pipes 2×150mm - - B2.33 71 19.01.SL-Z02-1-L-72-SL | 1 | 2025-04-06 | 2025-04-07
| JD3RZ02-1L72SL9251 | Testing and Backfilling Worksfor PVC Pipes 2×150mm - - B2.33 71 19.01.SL-Z02-1-L-72-SL | 1 | 2025-04-08 | 2025-04-09
| JD3RZ02-1L72SL9260 | Excavationfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z02-1-L-72-SL | 1 | 2025-04-03 | 2025-04-05
| JD3RZ02-1L72SL9261 | Installationfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z02-1-L-72-SL | 1 | 2025-04-06 | 2025-04-07
| JD3RZ02-1L72SL9262 | Backfillingfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z02-1-L-72-SL | 1 | 2025-04-08 | 2025-04-09
| JD3RZ02-1L72SL9263 | Excavationfor Drawpit 900x900x1200mm - - B2.33 71 19.13.02-Z02-1-L-72-SL | 1 | 2025-04-06 | 2025-04-07
| JD3RZ02-1L72SL9264 | Installationfor Drawpit 900x900x1200mm - - B2.33 71 19.13.02-Z02-1-L-72-SL | 1 | 2025-04-08 | 2025-04-09
| JD3RZ02-1L72SL9265 | Backfillingfor Drawpit 900x900x1200mm - - B2.33 71 19.13.02-Z02-1-L-72-SL | 1 | 2025-04-13 | 2025-04-14
| JD3RZ02-1L72SS521401 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2024-12-29 | 2024-12-30
| JD3RZ02-1L72SS521411 | Installation of Base Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2024-12-31 | 2025-01-01
| JD3RZ02-1L72SS521421 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03 | 1 | 2025-01-02 | 2025-01-04
| JD3RZ02-1L72SS521431 | Backfilling Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2025-01-05 | 2025-01-06
| JD3RZ02-1L72SS521441 | Finishing, Benching Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2025-01-07 | 2025-01-08
| JD3RZ02-1L72SS8593 | Trench excavation for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-72-SS | 1 | 2024-12-14 | 2024-12-18 | 2025-04-08 | 2025-06-21
| JD3RZ02-1L72SS8593.R | Trench excavation for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-72-SS -Remaining | 1 | 2024-12-19 | 2024-12-21 | 2025-08-02 | 2025-08-03
| JD3RZ02-1L72SS8594 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-72-SS | 1 | 2024-12-19 | 2024-12-24 | 2025-04-15 | 2025-07-16
| JD3RZ02-1L72SS8594.R | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-72-SS -Rem | 1 | 2024-12-25 | 2024-12-26 | 2025-08-04 | 2025-08-05
| JD3RZ02-1L72SS8595 | Installing for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-72-SS | 1 | 2024-12-25 | 2024-12-30 | 2025-04-14 | 2025-06-26
| JD3RZ02-1L72SS8595.R | Installing for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-72-SS -Remaining | 1 | 2024-12-31 | 2025-01-01 | 2025-08-06 | 2025-08-07
| JD3RZ02-1L72SS8596 | Primary Test for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-72-SS | 1 | 2024-12-31 | 2025-01-05 | 2025-04-23 | 2025-07-06
| JD3RZ02-1L72SS8596.R | Primary Test for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-72-SS -Remaining | 1 | 2025-01-06 | 2025-01-07 | 2025-08-09 | 2025-08-10
| JD3RZ02-1L72SS8597 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-72-SS | 1 | 2025-01-06 | 2025-01-13 | 2025-06-10 | 2025-07-31
| JD3RZ02-1L72SS8597.R | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-72-SS -Rem | 1 | 2025-01-14 | 2025-01-15 | 2025-08-11 | 2025-08-12
| JD3RZ02-1L72SS8598 | Trench excavation for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-1-L-72-SS | 1 | 2024-12-19 | 2024-12-23 | 2025-04-08 | 2025-06-02
| JD3RZ02-1L72SS8598.R | Trench excavation for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-1-L-72-SS -Remaining | 1 | 2024-12-24 | 2024-12-25 | 2025-08-04 | 2025-08-05
| JD3RZ02-1L72SS8599 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-1-L-72-SS | 1 | 2024-12-24 | 2024-12-28 | 2025-04-14 | 2025-06-08
| JD3RZ02-1L72SS8599.R | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-1-L-72-SS -Rem | 1 | 2024-12-29 | 2024-12-30 | 2025-08-06 | 2025-08-07
| JD3RZ02-1L72SS8600 | Installing for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-1-L-72-SS | 1 | 2024-12-29 | 2025-01-02 | 2025-04-08 | 2025-05-14
| JD3RZ02-1L72SS8600.R | Installing for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-1-L-72-SS -Remaining | 1 | 2025-01-04 | 2025-01-05 | 2025-08-09 | 2025-08-10
| JD3RZ02-1L72SS8601 | Primary Test for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-1-L-72-SS | 1 | 2025-01-04 | 2025-01-07 | 2025-04-08 | 2025-05-14
| JD3RZ02-1L72SS8601.R | Primary Test for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-1-L-72-SS -Remaining | 1 | 2025-01-08 | 2025-01-09
| JD3RZ02-1L72SS8602 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-1-L-72-SS | 1 | 2025-01-11 | 2025-01-16 | 2025-08-13
| JD3RZ02-1L72SS8635 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z02-1-L-72-SS | 1 | 2024-12-14 | 2024-12-15 | 2025-04-08 | 2025-04-26
| JD3RZ02-1L72SS8636 | Installation of Base Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z02-1-L-72-SS | 1 | 2024-12-16 | 2024-12-17 | 2025-04-15 | 2025-05-03
| JD3RZ02-1L72SS8637 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z02-1-L | 1 | 2024-12-18 | 2024-12-19 | 2025-04-17 | 2025-05-05
| JD3RZ02-1L72SS8638 | Backfilling Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z02-1-L-72-SS | 1 | 2024-12-21 | 2024-12-22
| JD3RZ02-1L72SS8639 | Finishing, Benching Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z02-1-L-72-SS | 1 | 2024-12-23 | 2024-12-24
| JD3RZ02-1L72SS8647 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-1-L-72-SS | 1 | 2024-12-24 | 2024-12-25 | 2025-04-08 | 2025-04-26
| JD3RZ02-1L72SS8647.R | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-1-L-72-SS -Remaining | 1 | 2024-12-26 | 2024-12-28
| JD3RZ02-1L72SS8648 | Installation of Base Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-1-L-72-SS | 1 | 2024-12-26 | 2024-12-31 | 2025-04-15 | 2025-05-31
| JD3RZ02-1L72SS8648.R | Installation of Base Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-1-L-72-SS -Remaining | 1 | 2025-01-01 | 2025-01-02
| JD3RZ02-1L72SS8649 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-1-L | 1 | 2025-01-01 | 2025-01-06 | 2025-04-17 | 2025-06-02
| JD3RZ02-1L72SS8649.R | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-1-L | 1 | 2025-01-07 | 2025-01-08
| JD3RZ02-1L72SS8650 | Backfilling Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-1-L-72-SS | 1 | 2025-01-09 | 2025-01-12
| JD3RZ02-1L72SS8651 | Finishing, Benching Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-1-L-72-SS | 1 | 2025-01-13 | 2025-01-14
| JD3RZ02-1L72ST524363 | Concrete encasement for pipes- NNB6.33 42 11.25-Z02-1-L-72-ST | 1 | 2025-02-08 | 2025-02-10
| JD3RZ02-1L72ST8719 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-1-L-72-ST | 1 | 2025-01-18 | 2025-01-19
| JD3RZ02-1L72ST8720 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-1-L-72-ST | 1 | 2025-01-20 | 2025-01-22
| JD3RZ02-1L72ST8721 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-1-L-72-ST | 1 | 2025-01-23 | 2025-01-26
| JD3RZ02-1L72ST8722 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-1-L-72-ST | 1 | 2025-01-27 | 2025-01-29
| JD3RZ02-1L72ST8723 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-1-L-72-ST | 1 | 2025-02-11 | 2025-02-15
| JD3RZ02-1L72ST8724 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-1-L-72-ST | 1 | 2025-01-20 | 2025-01-21
| JD3RZ02-1L72ST8725 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-1-L-72-ST | 1 | 2025-01-22 | 2025-01-23
| JD3RZ02-1L72ST8726 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-1-L-72-ST | 1 | 2025-01-25 | 2025-01-26
| JD3RZ02-1L72ST8727 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-1-L-72-ST | 1 | 2025-01-27 | 2025-01-28
| JD3RZ02-1L72ST8728 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-1-L-72-ST | 1 | 2025-02-16 | 2025-02-17
| JD3RZ02-1L72ST8729 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-1-L-72-ST | 1 | 2025-01-22 | 2025-01-23
| JD3RZ02-1L72ST8730 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-1-L-72-ST | 1 | 2025-01-25 | 2025-01-26
| JD3RZ02-1L72ST8731 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-1-L-72-ST | 1 | 2025-01-27 | 2025-01-28
| JD3RZ02-1L72ST8732 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-1-L-72-ST | 1 | 2025-01-29 | 2025-01-30
| JD3RZ02-1L72ST8733 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-1-L-72-ST | 1 | 2025-02-18 | 2025-02-19
| JD3RZ02-1L72ST8734 | Excavation Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z02-1-L-72-ST | 1 | 2024-12-14 | 2024-12-15 | 2025-03-11 | 2025-03-29
| JD3RZ02-1L72ST8735 | Soil Replacement and Bedding Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z02-1-L-72-ST | 1 | 2024-12-16 | 2024-12-17 | 2025-03-17 | 2025-04-03
| JD3RZ02-1L72ST8736 | Installing for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z02-1-L-72-ST | 1 | 2024-12-18 | 2024-12-19 | 2025-03-18 | 2025-04-05
| JD3RZ02-1L72ST8737 | Primary Test for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z02-1-L-72-ST | 1 | 2024-12-26 | 2024-12-28 | 2025-05-12 | 2025-05-29
| JD3RZ02-1L72ST8737.R | Primary Test for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z02-1-L-72-ST -Remaining | 1 | 2025-02-01 | 2025-02-02 | 2025-08-20 | 2025-08-21
| JD3RZ02-1L72ST8738 | Backfilling Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z02-1-L-72-ST | 1 | 2025-02-03 | 2025-02-04 | 2025-08-23 | 2025-08-24
| JD3RZ02-1L72ST8749 | Excavation Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-1-L-72-ST | 1 | 2024-12-14 | 2024-12-15 | 2025-03-17 | 2025-04-03
| JD3RZ02-1L72ST8750 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-1-L-72-ST | 1 | 2024-12-16 | 2024-12-17 | 2025-03-29 | 2025-04-15
| JD3RZ02-1L72ST8751 | Installing for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-1-L-72-ST | 1 | 2024-12-18 | 2024-12-19 | 2025-04-03 | 2025-04-30
| JD3RZ02-1L72ST8752 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-1-L-72-ST | 1 | 2024-12-29 | 2024-12-30 | 2025-05-12 | 2025-06-08
| JD3RZ02-1L72ST8752.R | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-1-L-72-ST -Remaining | 1 | 2025-02-03 | 2025-02-04 | 2025-08-15 | 2025-08-17
| JD3RZ02-1L72ST8753 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-1-L-72-ST | 1 | 2025-02-05 | 2025-02-06 | 2025-08-17 | 2025-08-19
| JD3RZ02-1L72ST8759 | Excavation Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-72-ST | 1 | 2024-12-14 | 2024-12-15 | 2025-04-06 | 2025-04-23
| JD3RZ02-1L72ST8760 | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-72-ST | 1 | 2024-12-16 | 2024-12-17 | 2025-04-07 | 2025-04-24
| JD3RZ02-1L72ST8761 | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-72-ST | 1 | 2024-12-18 | 2024-12-19 | 2025-04-08 | 2025-04-26
| JD3RZ02-1L72ST8762 | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-72-ST | 1 | 2024-12-31 | 2025-01-01 | 2025-05-12 | 2025-05-29
| JD3RZ02-1L72ST8762.R | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-72-ST -Remaining | 1 | 2025-02-05 | 2025-02-06 | 2025-08-18 | 2025-08-19
| JD3RZ02-1L72ST8763 | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-72-ST | 1 | 2025-02-08 | 2025-02-09 | 2025-08-20 | 2025-08-21
| JD3RZ02-1L72ST8769 | Excavation Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-1-L-72-ST | 1 | 2025-01-02 | 2025-01-05 | 2025-03-18 | 2025-04-14
| JD3RZ02-1L72ST8769.R | Excavation Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-1-L-72-ST -Remaining | 1 | 2025-01-25 | 2025-01-26 | 2025-08-20 | 2025-08-21
| JD3RZ02-1L72ST8770 | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-1-L-72-ST | 1 | 2025-01-06 | 2025-01-08 | 2025-03-29 | 2025-04-24
| JD3RZ02-1L72ST8770.R | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-1-L-72-ST -R | 1 | 2025-01-27 | 2025-01-28 | 2025-08-23 | 2025-08-24
| JD3RZ02-1L72ST8771 | Installing for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-1-L-72-ST | 1 | 2025-01-09 | 2025-01-12 | 2025-04-03 | 2025-05-10
| JD3RZ02-1L72ST8771.R | Installing for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-1-L-72-ST -Remaining | 1 | 2025-01-29 | 2025-01-30 | 2025-08-25 | 2025-08-26
| JD3RZ02-1L72ST8772 | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-1-L-72-ST | 1 | 2025-01-13 | 2025-01-15 | 2025-05-13 | 2025-06-18
| JD3RZ02-1L72ST8772.R | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-1-L-72-ST -Remaining | 1 | 2025-02-01 | 2025-02-02 | 2025-09-03 | 2025-09-09
| JD3RZ02-1L72ST8773 | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-1-L-72-ST | 1 | 2025-02-10 | 2025-02-13 | 2025-08-31
| JD3RZ02-1L72ST8779 | Excavation Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z02-1-L-72-ST | 1 | 2024-12-14 | 2024-12-15 | 2025-04-05 | 2025-04-22
| JD3RZ02-1L72ST8780 | Soil Replacement and Bedding Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z02-1-L-72-ST | 1 | 2024-12-16 | 2024-12-17 | 2025-04-06 | 2025-05-03
| JD3RZ02-1L72ST8781 | Installing for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z02-1-L-72-ST | 1 | 2024-12-18 | 2024-12-19 | 2025-04-07 | 2025-05-04
| JD3RZ02-1L72ST8782 | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z02-1-L-72-ST | 1 | 2025-01-06 | 2025-01-07 | 2025-05-13 | 2025-06-09
| JD3RZ02-1L72ST8782.R | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z02-1-L-72-ST -Remaining | 1 | 2025-02-03 | 2025-02-04 | 2025-08-06 | 2025-08-07
| JD3RZ02-1L72ST8783 | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z02-1-L-72-ST | 1 | 2025-02-15 | 2025-02-16 | 2025-08-10 | 2025-08-11
| JD3RZ02-1L72ST8784 | Excavation Works for GRP Pipe Line 900 mm - depth from 2.51 to 3.50 m- B6.33 42 11.13-Z02-1-L-72-ST | 1 | 2025-01-27 | 2025-01-28 | 2025-08-20 | 2025-08-21
| JD3RZ02-1L72ST8785 | Soil Replacement and Bedding Works for GRP Pipe Line 900 mm - depth from 2.51 to 3.50 m- B6.33 42 11.13-Z02-1-L-72-ST | 1 | 2025-01-29 | 2025-01-30 | 2025-08-22 | 2025-08-24
| JD3RZ02-1L72ST8786 | Installing for GRP Pipe Line 900 mm - depth from 2.51 to 3.50 m- B6.33 42 11.13-Z02-1-L-72-ST | 1 | 2025-02-01 | 2025-02-02 | 2025-08-25 | 2025-08-26
| JD3RZ02-1L72ST8787 | Primary Test for GRP Pipe Line 900 mm - depth from 2.51 to 3.50 m- B6.33 42 11.13-Z02-1-L-72-ST | 1 | 2025-02-03 | 2025-02-04
| JD3RZ02-1L72ST8788 | Backfilling Works for GRP Pipe Line 900 mm - depth from 2.51 to 3.50 m- B6.33 42 11.13-Z02-1-L-72-ST | 1 | 2025-02-17 | 2025-02-18
| JD3RZ02-1L72ST8794 | Excavation Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z02-1-L-72-ST | 1 | 2024-12-14 | 2024-12-15 | 2025-06-15 | 2025-07-02
| JD3RZ02-1L72ST8795 | Soil Replacement and Bedding Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z02-1-L-72-ST | 1 | 2024-12-16 | 2024-12-17 | 2025-06-25 | 2025-07-13
| JD3RZ02-1L72ST8796 | Installing for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z02-1-L-72-ST | 1 | 2024-12-18 | 2024-12-19 | 2025-06-30 | 2025-07-17
| JD3RZ02-1L72ST8797 | Primary Test for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z02-1-L-72-ST | 1 | 2025-02-05 | 2025-02-06
| JD3RZ02-1L72ST8798 | Backfilling Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z02-1-L-72-ST | 1 | 2025-02-19 | 2025-02-20
| JD3RZ02-1L72ST8809 | Excavation Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z02-1-L-72-ST | 1 | 2025-01-08 | 2025-01-09 | 2025-05-12 | 2025-05-29
| JD3RZ02-1L72ST8809.R | Excavation Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z02-1-L-72-ST -Remaining | 1 | 2025-01-29 | 2025-01-30 | 2025-08-14 | 2025-08-16
| JD3RZ02-1L72ST8810 | Soil Replacement and Bedding Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z02-1-L-72-ST | 1 | 2025-02-01 | 2025-02-02 | 2025-08-17 | 2025-08-18
| JD3RZ02-1L72ST8811 | Installing for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z02-1-L-72-ST | 1 | 2025-02-03 | 2025-02-04 | 2025-08-20 | 2025-08-21
| JD3RZ02-1L72ST8812 | Primary Test for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z02-1-L-72-ST | 1 | 2025-02-05 | 2025-02-06
| JD3RZ02-1L72ST8813 | Backfilling Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z02-1-L-72-ST | 1 | 2025-02-22 | 2025-02-23
| JD3RZ02-1L72ST8814 | Excavation Works for GRP Pipe Line 1100 mm - depth from 2.51 to 3.50 m- B6.33 42 11.21-Z02-1-L-72-ST | 1 | 2025-02-01 | 2025-02-02
| JD3RZ02-1L72ST8815 | Soil Replacement and Bedding Works for GRP Pipe Line 1100 mm - depth from 2.51 to 3.50 m- B6.33 42 11.21-Z02-1-L-72-ST | 1 | 2025-02-03 | 2025-02-04
| JD3RZ02-1L72ST8816 | Installing for GRP Pipe Line 1100 mm - depth from 2.51 to 3.50 m- B6.33 42 11.21-Z02-1-L-72-ST | 1 | 2025-02-05 | 2025-02-06
| JD3RZ02-1L72ST8817 | Primary Test for GRP Pipe Line 1100 mm - depth from 2.51 to 3.50 m- B6.33 42 11.21-Z02-1-L-72-ST | 1 | 2025-02-08 | 2025-02-09
| JD3RZ02-1L72ST8818 | Backfilling Works for GRP Pipe Line 1100 mm - depth from 2.51 to 3.50 m- B6.33 42 11.21-Z02-1-L-72-ST | 1 | 2025-02-24 | 2025-02-25
| JD3RZ02-1L72ST8902 | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-1-L-72-ST | 1 | 2024-12-14 | 2024-12-15 | 2025-04-06 | 2025-04-23
| JD3RZ02-1L72ST8903 | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-1-L-72-ST | 1 | 2025-01-11 | 2025-01-12 | 2025-05-13 | 2025-05-31
| JD3RZ02-1L72ST8904 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-1-L-72-ST | 1 | 2025-01-13 | 2025-01-14 | 2025-06-16 | 2025-07-03
| JD3RZ02-1L72ST8904.R | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-1-L-72-ST -Remaining | 1 | 2025-02-08 | 2025-02-09
| JD3RZ02-1L72ST8905 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-1-L-72-ST | 1 | 2025-02-10 | 2025-02-11
| JD3RZ02-1L72ST8906 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-1-L-72-ST | 1 | 2025-02-26 | 2025-02-27
| JD3RZ02-1L72ST8912 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-1-L-72-ST | 1 | 2024-12-14 | 2024-12-15 | 2025-04-06 | 2025-04-23
| JD3RZ02-1L72ST8913 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-1-L-72-ST | 1 | 2025-01-13 | 2025-01-14 | 2025-05-13 | 2025-06-09
| JD3RZ02-1L72ST8913.R | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-1-L-72-ST -Remaining | 1 | 2025-02-10 | 2025-02-11
| JD3RZ02-1L72ST8914 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-1-L-72-ST | 1 | 2025-01-15 | 2025-01-16 | 2025-06-30 | 2025-07-27
| JD3RZ02-1L72ST8914.R | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-1-L-72-ST -Remaining | 1 | 2025-02-12 | 2025-02-13
| JD3RZ02-1L72ST8915 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-1-L-72-ST | 1 | 2025-02-15 | 2025-02-16
| JD3RZ02-1L72ST8916 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-1-L-72-ST | 1 | 2025-03-01 | 2025-03-02
| JD3RZ02-1L72ST8917 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-1-L-72-ST | 1 | 2024-12-14 | 2024-12-15 | 2025-04-06 | 2025-04-23
| JD3RZ02-1L72ST8918 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-1-L-72-ST | 1 | 2025-02-12 | 2025-02-13
| JD3RZ02-1L72ST8919 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-1-L-72-ST | 1 | 2025-02-15 | 2025-02-16
| JD3RZ02-1L72ST8920 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-1-L-72-ST | 1 | 2025-02-17 | 2025-02-18
| JD3RZ02-1L72ST8921 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-1-L-72-ST | 1 | 2025-03-03 | 2025-03-04
| JD3RZ02-1L72ST8932 | Excavation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z02-1-L-72-ST | 1 | 2025-01-15 | 2025-01-16 | 2025-04-06 | 2025-04-23
| JD3RZ02-1L72ST8932.R | Excavation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z02-1-L-72-ST -Remaining | 1 | 2025-02-15 | 2025-02-16
| JD3RZ02-1L72ST8933 | Base Plain Concrete Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z02-1-L-72-ST | 1 | 2025-01-18 | 2025-01-19 | 2025-05-13 | 2025-05-31
| JD3RZ02-1L72ST8933.R | Base Plain Concrete Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z02-1-L-72-ST -Remaining | 1 | 2025-02-17 | 2025-02-18
| JD3RZ02-1L72ST8934 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z02-1-L-72-ST | 1 | 2025-01-20 | 2025-01-21 | 2025-06-30 | 2025-07-17
| JD3RZ02-1L72ST8934.R | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z02-1-L-72-ST -Remaining | 1 | 2025-02-19 | 2025-02-20
| JD3RZ02-1L72ST8935 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z02-1-L-72-ST | 1 | 2025-02-22 | 2025-02-23
| JD3RZ02-1L72ST8936 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z02-1-L-72-ST | 1 | 2025-03-05 | 2025-03-06
| JD3RZ02-1L72ST8937 | EXCAVATION Works for Catchbasine single - - B6.33 05 39.09-Z02-1-L-72-ST | 1 | 2025-02-17 | 2025-02-18
| JD3RZ02-1L72ST8938 | Catchbasine Installation Works For Catchbasine single - - B6.33 05 39.09-Z02-1-L-72-ST | 1 | 2025-02-19 | 2025-02-22
| JD3RZ02-1L72ST8939 | FINISHING Works For Catchbasine single - - B6.33 05 39.09-Z02-1-L-72-ST | 1 | 2025-02-23 | 2025-02-25
| JD3RZ02-1L72ST8940 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - - B6.33 05 39.09-Z02-1-L-72-ST | 1 | 2025-03-08 | 2025-03-09
| JD3RZ02-1L72ST8941 | EXCAVATION Works for Catchbasine double - - B6.33 05 39.10-Z02-1-L-72-ST | 1 | 2025-02-19 | 2025-02-20
| JD3RZ02-1L72ST8942 | Catchbasine Installation Works For Catchbasine double - - B6.33 05 39.10-Z02-1-L-72-ST | 1 | 2025-02-22 | 2025-02-24
| JD3RZ02-1L72ST8943 | FINISHING Works For Catchbasine double - - B6.33 05 39.10-Z02-1-L-72-ST | 1 | 2025-02-25 | 2025-02-27
| JD3RZ02-1L72ST8944 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - - B6.33 05 39.10-Z02-1-L-72-ST | 1 | 2025-03-01 | 2025-03-02
| JD3RZ02-1L72TC9275 | Excavation Worksfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z02-1-L-72-TC | 1 | 2025-04-08 | 2025-04-09
| JD3RZ02-1L72TC9276 | Installationfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z02-1-L-72-TC | 1 | 2025-04-10 | 2025-04-14
| JD3RZ02-1L72TC9277 | Pouring Concrete Coverfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z02-1-L-72-TC | 1 | 2025-04-15 | 2025-04-19
| JD3RZ02-1L72TC9278 | Backfilling Worksfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z02-1-L-72-TC | 1 | 2025-04-20 | 2025-04-21
| JD3RZ02-1L72TC9279 | Excavation and Bedding Worksfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z02-1-L-72-TC | 1 | 2025-04-10 | 2025-04-12
| JD3RZ02-1L72TC9280 | Installationfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z02-1-L-72-TC | 1 | 2025-04-13 | 2025-04-14
| JD3RZ02-1L72TC9281 | Backfilling Worksfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z02-1-L-72-TC | 1 | 2025-04-15 | 2025-04-16
| JD3RZ02-1L72TSE8995 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-1-L-72-TSE | 1 | 2025-02-22 | 2025-02-24
| JD3RZ02-1L72TSE8996 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-1-L-72-TSE | 1 | 2025-02-25 | 2025-02-27
| JD3RZ02-1L72TSE8997 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-1-L-72-TSE | 1 | 2025-03-01 | 2025-03-06
| JD3RZ02-1L72TSE8998 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-1-L-72-TSE | 1 | 2025-03-10 | 2025-03-13
| JD3RZ02-1L72TSE8999 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-1-L-72-TSE | 1 | 2025-03-15 | 2025-03-18
| JD3RZ02-1L72TSE9120 | Installationfor gate valves 100 mm - - B4.33 14 19.01-Z02-1-L-72-TSE | 1 | 2025-03-08 | 2025-03-09
| JD3RZ02-1L72TSE9121 | Testing And Commtionningfor gate valves 100 mm - - B4.33 14 19.01-Z02-1-L-72-TSE | 1 | 2025-03-10 | 2025-03-11
| JD3RZ02-1L72WT8945 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-1-L-72-WT | 1 | 2025-02-25 | 2025-03-01 | 2025-08-16
| JD3RZ02-1L72WT8946 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-1-L-72-WT | 1 | 2025-03-02 | 2025-03-06 | 2025-08-20
| JD3RZ02-1L72WT8947 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-1-L-72-WT | 1 | 2025-03-08 | 2025-03-16 | 2025-08-23
| JD3RZ02-1L72WT8948 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-1-L-72-WT | 1 | 2025-03-17 | 2025-03-22 | 2025-09-16
| JD3RZ02-1L72WT8949 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-1-L-72-WT | 1 | 2025-03-26 | 2025-03-31 | 2025-08-27
| JD3RZ02-1L72WT8970 | INSTALLATIONfor gate valves 150 mm - - B3.33 14 19.01-Z02-1-L-72-WT | 1 | 2025-03-08 | 2025-03-09
| JD3RZ02-1L72WT8971 | TESTING AND COMMITIONfor gate valves 150 mm - - B3.33 14 19.01-Z02-1-L-72-WT | 1 | 2025-03-10 | 2025-03-11
| JD3RZ02-1L72WT8980 | EXCAVATION and Bedding Worksfor Fire Hydrant - - B3.33 14 19.08-Z02-1-L-72-WT | 1 | 2025-03-19 | 2025-03-20
| JD3RZ02-1L72WT8981 | INSTALLATIONfor Fire Hydrant - - B3.33 14 19.08-Z02-1-L-72-WT | 1 | 2025-03-22 | 2025-03-23
| JD3RZ02-1L72WT8982 | TESTING AND COMMITIONfor Fire Hydrant - - B3.33 14 19.08-Z02-1-L-72-WT | 1 | 2025-03-24 | 2025-03-25
| JD3RZ02-1L73SL9931 | Excavation Worksfor Copper Cables 4Cx25 mm² - - B2.26 05 19.04-Z02-1-L-73-SL | 1 | 2025-03-22 | 2025-03-24
| JD3RZ02-1L73SL9932 | Installationfor Copper Cables 4Cx25 mm² - - B2.26 05 19.04-Z02-1-L-73-SL | 1 | 2025-03-26 | 2025-03-29
| JD3RZ02-1L73SL9933 | Backfilling, Warning Tabe Worksfor Copper Cables 4Cx25 mm² - - B2.26 05 19.04-Z02-1-L-73-SL | 1 | 2025-03-30 | 2025-04-01
| JD3RZ02-1L73SL9934 | Testing and Commitioning for Copper Cables 4Cx25 mm² - - B2.26 05 19.04-Z02-1-L-73-SL | 1 | 2025-04-06 | 2025-04-08
| JD3RZ02-1L73SL9945 | INSTALLINGfor insulated copper conductor 16 mm² - - B2.26 05 19.08-Z02-1-L-73-SL | 1 | 2025-03-30 | 2025-04-01
| JD3RZ02-1L73SL9946 | TESTING AND COMMITIONINGfor insulated copper conductor 16 mm² - - B2.26 05 19.08-Z02-1-L-73-SL | 1 | 2025-04-02 | 2025-04-05
| JD3RZ02-1L73SL9952 | Excavation of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-1-L-73-SL | 1 | 2025-03-25 | 2025-03-26
| JD3RZ02-1L73SL9953 | Installation of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-1-L-73-SL | 1 | 2025-03-27 | 2025-03-29
| JD3RZ02-1L73SL9954 | Backfilling of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-1-L-73-SL | 1 | 2025-03-30 | 2025-03-31
| JD3RZ02-1L73SL9955 | Installation Worksfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-1-L-73-SL | 1 | 2025-04-01 | 2025-04-03
| JD3RZ02-1L73SL9956 | Testing and Commitioningfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-1-L-73-SL | 1 | 2025-04-05 | 2025-04-07
| JD3RZ02-1L73SL9957 | Installationfor Lighting( LED ) Luminaire 150 WATT - - B2.26.56.19.01-Z02-1-L-73-SL | 1 | 2025-03-30 | 2025-03-31
| JD3RZ02-1L73SL9960 | Supply, construct, connect and test earthing pitsfor Street Lighting EARTHING SYSTEM - - B2.26 05 26.01-Z02-1-L-73-SL | 1 | 2025-04-01 | 2025-04-02
| JD3RZ02-1L73SL9961 | Excavation Worksfor PVC Pipes 2×150mm - - B2.33 71 19.01.SL-Z02-1-L-73-SL | 1 | 2025-03-27 | 2025-03-29
| JD3RZ02-1L73SL9962 | Installationfor PVC Pipes 2×150mm - - B2.33 71 19.01.SL-Z02-1-L-73-SL | 1 | 2025-03-30 | 2025-03-31
| JD3RZ02-1L73SL9963 | Pouring Concrete Coverfor PVC Pipes 2×150mm - - B2.33 71 19.01.SL-Z02-1-L-73-SL | 1 | 2025-04-01 | 2025-04-02
| JD3RZ02-1L73SL9964 | Testing and Backfilling Worksfor PVC Pipes 2×150mm - - B2.33 71 19.01.SL-Z02-1-L-73-SL | 1 | 2025-04-03 | 2025-04-05
| JD3RZ02-1L73SL9973 | Excavationfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z02-1-L-73-SL | 1 | 2025-03-30 | 2025-03-31
| JD3RZ02-1L73SL9974 | Installationfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z02-1-L-73-SL | 1 | 2025-04-01 | 2025-04-02
| JD3RZ02-1L73SL9975 | Backfillingfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z02-1-L-73-SL | 1 | 2025-04-03 | 2025-04-05
| JD3RZ02-1L73SL9976 | Excavationfor Drawpit 900x900x1200mm - - B2.33 71 19.13.02-Z02-1-L-73-SL | 1 | 2025-04-01 | 2025-04-02
| JD3RZ02-1L73SL9977 | Installationfor Drawpit 900x900x1200mm - - B2.33 71 19.13.02-Z02-1-L-73-SL | 1 | 2025-04-03 | 2025-04-05
| JD3RZ02-1L73SL9978 | Backfillingfor Drawpit 900x900x1200mm - - B2.33 71 19.13.02-Z02-1-L-73-SL | 1 | 2025-04-06 | 2025-04-07
| JD3RZ02-1L73SL9982 | Excavationfor Street Lighting panels - - B2.26 24 16.01-Z02-1-L-73-SL | 1 | 2025-04-03 | 2025-04-05
| JD3RZ02-1L73SL9983 | Installationfor Street Lighting panels - - B2.26 24 16.01-Z02-1-L-73-SL | 1 | 2025-04-06 | 2025-04-07
| JD3RZ02-1L73SL9984 | Backfillingfor Street Lighting panels - - B2.26 24 16.01-Z02-1-L-73-SL | 1 | 2025-04-08 | 2025-04-09
| JD3RZ02-1L73SL9985 | Excavationfor KWH meter - - B2.26 24 16.02-Z02-1-L-73-SL | 1 | 2025-04-06 | 2025-04-07
| JD3RZ02-1L73SL99851 | Excavation for Drawpit-B2.33 71 19.13.03-Z02-1-L-73-SL | 1 | 2025-04-08 | 2025-04-09
| JD3RZ02-1L73SL9986 | Installationfor KWH meter - - B2.26 24 16.02-Z02-1-L-73-SL | 1 | 2025-04-08 | 2025-04-09
| JD3RZ02-1L73SL99861 | Installation for Drawpit-B2.33 71 19.13.03-Z02-1-L-73-SL | 1 | 2025-04-10 | 2025-04-12
| JD3RZ02-1L73SL9987 | Backfillingfor KWH meter - - B2.26 24 16.02-Z02-1-L-73-SL | 1 | 2025-04-10 | 2025-04-12
| JD3RZ02-1L73SL99871 | Backfilling for Drawpit-B2.33 71 19.13.03-Z02-1-L-73-SL | 1 | 2025-04-13 | 2025-04-14
| JD3RZ02-1L73SS521401 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2025-02-08 | 2025-02-09 | 2025-08-18
| JD3RZ02-1L73SS521411 | Installation of Base Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2025-02-10 | 2025-02-13 | 2025-08-21
| JD3RZ02-1L73SS521421 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03 | 1 | 2025-02-15 | 2025-02-18 | 2025-08-25
| JD3RZ02-1L73SS521431 | Backfilling Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2025-02-19 | 2025-02-20
| JD3RZ02-1L73SS521441 | Finishing, Benching Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2025-02-22 | 2025-02-23
| JD3RZ02-1L73SS9306 | Trench excavation for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-73-SS | 1 | 2025-01-27 | 2025-01-28
| JD3RZ02-1L73SS9307 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-73-SS | 1 | 2025-01-29 | 2025-01-30
| JD3RZ02-1L73SS9308 | Installing for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-73-SS | 1 | 2025-02-01 | 2025-02-02
| JD3RZ02-1L73SS9309 | Primary Test for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-73-SS | 1 | 2025-02-03 | 2025-02-04
| JD3RZ02-1L73SS9310 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-1-L-73-SS | 1 | 2025-02-05 | 2025-02-06
| JD3RZ02-1L73SS9311 | Trench excavation for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-1-L-73-SS | 1 | 2025-01-29 | 2025-02-02 | 2025-08-14
| JD3RZ02-1L73SS9312 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-1-L-73-SS | 1 | 2025-02-03 | 2025-02-06 | 2025-08-18
| JD3RZ02-1L73SS9313 | Installing for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-1-L-73-SS | 1 | 2025-02-08 | 2025-02-12 | 2025-08-24
| JD3RZ02-1L73SS9314 | Primary Test for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-1-L-73-SS | 1 | 2025-02-13 | 2025-02-17 | 2025-09-03
| JD3RZ02-1L73SS9315 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-1-L-73-SS | 1 | 2025-02-24 | 2025-03-02 | 2025-09-09
| JD3RZ02-1L73SS9348 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z02-1-L-73-SS | 1 | 2025-02-03 | 2025-02-04
| JD3RZ02-1L73SS9349 | Installation of Base Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z02-1-L-73-SS | 1 | 2025-02-05 | 2025-02-06
| JD3RZ02-1L73SS9350 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z02-1-L | 1 | 2025-02-08 | 2025-02-09
| JD3RZ02-1L73SS9351 | Backfilling Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z02-1-L-73-SS | 1 | 2025-02-10 | 2025-02-11
| JD3RZ02-1L73SS9352 | Finishing, Benching Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z02-1-L-73-SS | 1 | 2025-02-12 | 2025-02-13
| JD3RZ02-1L73SS9365 | Excavation and PC Blinding Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.06-Z02-1-L-73-SS | 1 | 2025-02-05 | 2025-02-06
| JD3RZ02-1L73SS9366 | Installation of Base Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.06-Z02-1-L-73-SS | 1 | 2025-02-08 | 2025-02-09
| JD3RZ02-1L73SS9367 | Installation of Manhole Ring and Cover Slab Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.0 | 1 | 2025-02-10 | 2025-02-11
| JD3RZ02-1L73SS9368 | Installation of fitting Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.06-Z02-1-L-73-SS | 1 | 2025-02-12 | 2025-02-13
| JD3RZ02-1L73SS9369 | Concrete Encasement Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.06-Z02-1-L-73-SS | 1 | 2025-02-15 | 2025-02-16
| JD3RZ02-1L73SS9370 | Backfilling Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.06-Z02-1-L-73-SS | 1 | 2025-02-17 | 2025-02-18
| JD3RZ02-1L73SS9371 | Finishing, Benching Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.06-Z02-1-L-73-SS | 1 | 2025-02-19 | 2025-02-20
| JD3RZ02-1L73ST9432 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-1-L-73-ST | 1 | 2025-03-23 | 2025-03-24
| JD3RZ02-1L73ST9433 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-1-L-73-ST | 1 | 2025-03-25 | 2025-03-27
| JD3RZ02-1L73ST9434 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-1-L-73-ST | 1 | 2025-03-29 | 2025-03-31
| JD3RZ02-1L73ST9435 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-1-L-73-ST | 1 | 2025-04-01 | 2025-04-03
| JD3RZ02-1L73ST9436 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-1-L-73-ST | 1 | 2025-04-05 | 2025-04-08
| JD3RZ02-1L73ST9437 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-1-L-73-ST | 1 | 2025-03-25 | 2025-03-26
| JD3RZ02-1L73ST9438 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-1-L-73-ST | 1 | 2025-03-27 | 2025-03-29
| JD3RZ02-1L73ST9439 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-1-L-73-ST | 1 | 2025-03-30 | 2025-03-31
| JD3RZ02-1L73ST9440 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-1-L-73-ST | 1 | 2025-04-01 | 2025-04-02
| JD3RZ02-1L73ST9441 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-1-L-73-ST | 1 | 2025-04-03 | 2025-04-05
| JD3RZ02-1L73ST9442 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-1-L-73-ST | 1 | 2025-03-27 | 2025-03-29
| JD3RZ02-1L73ST9443 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-1-L-73-ST | 1 | 2025-03-30 | 2025-03-31
| JD3RZ02-1L73ST9444 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-1-L-73-ST | 1 | 2025-04-01 | 2025-04-02
| JD3RZ02-1L73ST9445 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-1-L-73-ST | 1 | 2025-04-03 | 2025-04-05
| JD3RZ02-1L73ST9446 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-1-L-73-ST | 1 | 2025-04-06 | 2025-04-07
| JD3RZ02-1L73ST9447 | Excavation Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z02-1-L-73-ST | 1 | 2025-03-30 | 2025-03-31 | 2025-08-23
| JD3RZ02-1L73ST9448 | Soil Replacement and Bedding Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z02-1-L-73-ST | 1 | 2025-04-01 | 2025-04-02 | 2025-08-25
| JD3RZ02-1L73ST9449 | Installing for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z02-1-L-73-ST | 1 | 2025-04-03 | 2025-04-05 | 2025-08-27
| JD3RZ02-1L73ST9450 | Primary Test for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z02-1-L-73-ST | 1 | 2025-04-06 | 2025-04-07
| JD3RZ02-1L73ST9451 | Backfilling Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z02-1-L-73-ST | 1 | 2025-04-09 | 2025-04-10
| JD3RZ02-1L73ST9452 | Excavation Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z02-1-L-73-ST | 1 | 2025-04-01 | 2025-04-02
| JD3RZ02-1L73ST9453 | Soil Replacement and Bedding Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z02-1-L-73-ST | 1 | 2025-04-03 | 2025-04-05
| JD3RZ02-1L73ST9454 | Installing for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z02-1-L-73-ST | 1 | 2025-04-06 | 2025-04-07
| JD3RZ02-1L73ST9455 | Primary Test for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z02-1-L-73-ST | 1 | 2025-04-08 | 2025-04-09
| JD3RZ02-1L73ST9456 | Backfilling Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z02-1-L-73-ST | 1 | 2025-04-12 | 2025-04-13
| JD3RZ02-1L73ST9457 | Excavation Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z02-1-L-73-ST | 1 | 2025-04-03 | 2025-04-05
| JD3RZ02-1L73ST9458 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z02-1-L-73-ST | 1 | 2025-04-06 | 2025-04-07
| JD3RZ02-1L73ST9459 | Installing for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z02-1-L-73-ST | 1 | 2025-04-08 | 2025-04-09
| JD3RZ02-1L73ST9460 | Primary Test for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z02-1-L-73-ST | 1 | 2025-04-10 | 2025-04-12
| JD3RZ02-1L73ST9461 | Backfilling Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z02-1-L-73-ST | 1 | 2025-04-14 | 2025-04-15
| JD3RZ02-1L73ST9462 | Excavation Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-1-L-73-ST | 1 | 2025-04-06 | 2025-04-07 | 2025-08-23
| JD3RZ02-1L73ST9463 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-1-L-73-ST | 1 | 2025-04-08 | 2025-04-09 | 2025-08-25
| JD3RZ02-1L73ST9464 | Installing for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-1-L-73-ST | 1 | 2025-04-10 | 2025-04-12 | 2025-08-27
| JD3RZ02-1L73ST9465 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-1-L-73-ST | 1 | 2025-04-13 | 2025-04-14 | 2025-08-30
| JD3RZ02-1L73ST9466 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-1-L-73-ST | 1 | 2025-04-16 | 2025-04-17
| JD3RZ02-1L73ST9472 | Excavation Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-73-ST | 1 | 2025-04-08 | 2025-04-09 | 2025-08-23
| JD3RZ02-1L73ST9473 | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-73-ST | 1 | 2025-04-10 | 2025-04-12 | 2025-08-25
| JD3RZ02-1L73ST9474 | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-73-ST | 1 | 2025-04-13 | 2025-04-14 | 2025-08-27
| JD3RZ02-1L73ST9475 | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-73-ST | 1 | 2025-04-15 | 2025-04-16
| JD3RZ02-1L73ST9476 | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-1-L-73-ST | 1 | 2025-04-19 | 2025-04-20
| JD3RZ02-1L73ST9542 | Excavation Works for GRP Pipe Line 1200 mm - depth from 2.51 to 3.50 m- B6.33 42 11.24-Z02-1-L-73-ST | 1 | 2025-04-10 | 2025-04-12
| JD3RZ02-1L73ST9543 | Soil Replacement and Bedding Works for GRP Pipe Line 1200 mm - depth from 2.51 to 3.50 m- B6.33 42 11.24-Z02-1-L-73-ST | 1 | 2025-04-13 | 2025-04-14
| JD3RZ02-1L73ST9544 | Installing for GRP Pipe Line 1200 mm - depth from 2.51 to 3.50 m- B6.33 42 11.24-Z02-1-L-73-ST | 1 | 2025-04-15 | 2025-04-16
| JD3RZ02-1L73ST9545 | Primary Test for GRP Pipe Line 1200 mm - depth from 2.51 to 3.50 m- B6.33 42 11.24-Z02-1-L-73-ST | 1 | 2025-04-17 | 2025-04-19
| JD3RZ02-1L73ST9546 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 2.51 to 3.50 m- B6.33 42 11.24-Z02-1-L-73-ST | 1 | 2025-04-21 | 2025-04-22
| JD3RZ02-1L73ST9561 | Excavation Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - - B6.34 42 16.03-Z02-1-L-73-ST | 1 | 2025-02-23 | 2025-02-24 | 2025-09-14 | 2025-09-16
| JD3RZ02-1L73ST9562 | Plain Concrete Works For Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - - B6.34 42 16.03-Z02-1-L-73-ST | 1 | 2025-02-25 | 2025-02-26 | 2025-09-17 | 2025-09-18
| JD3RZ02-1L73ST9563 | Raft Foundation for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - - B6.34 42 16.03-Z02-1-L-73-ST | 1 | 2025-02-27 | 2025-03-03
| JD3RZ02-1L73ST9564 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.34 42 16.03-Z02-1-L-73-ST | 1 | 2025-03-04 | 2025-03-10
| JD3RZ02-1L73ST9565 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.34 42 16.03-Z02-1-L-73-ST | 1 | 2025-03-11 | 2025-03-17
| JD3RZ02-1L73ST9566 | Isolation Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - - B6.34 42 16.03-Z02-1-L-73-ST | 1 | 2025-03-18 | 2025-03-19
| JD3RZ02-1L73ST9567 | Backfilling Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - - B6.34 42 16.03-Z02-1-L-73-ST | 1 | 2025-03-20 | 2025-03-22
| JD3RZ02-1L73ST9568 | Excavation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-Z02-1-L-73-ST | 1 | 2024-12-14 | 2024-12-17 | 2025-07-01 | 2025-07-31
| JD3RZ02-1L73ST9568.R | Excavation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-Z02-1-L-73-ST | 1 | 2024-12-18 | 2024-12-19 | 2025-08-02 | 2025-08-04
| JD3RZ02-1L73ST9569 | Plain Concrete Works For Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-Z02-1-L-73-ST | 1 | 2024-12-18 | 2024-12-19 | 2025-07-05 | 2025-07-22
| JD3RZ02-1L73ST9569.R | Plain Concrete Works For Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-Z02-1-L-73-ST | 1 | 2024-12-21 | 2024-12-22 | 2025-08-03 | 2025-09-03
| JD3RZ02-1L73ST9570 | Raft Foundation for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-Z02-1-L-73-ST | 1 | 2024-12-21 | 2025-01-01 | 2025-07-05 | 2025-07-31
| JD3RZ02-1L73ST9570.R | Raft Foundation for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-Z02-1-L-73-ST | 1 | 2025-01-02 | 2025-01-04 | 2025-08-06
| JD3RZ02-1L73ST9571 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-Z02-1-L-73-ST | 1 | 2025-01-05 | 2025-01-23 | 2025-08-09
| JD3RZ02-1L73ST9572 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-Z02-1-L-73-ST | 1 | 2025-01-25 | 2025-02-12 | 2025-08-23
| JD3RZ02-1L73ST9573 | Isolation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-Z02-1-L-73-ST | 1 | 2025-02-13 | 2025-02-19 | 2025-08-28
| JD3RZ02-1L73ST9574 | Backfilling Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-Z02-1-L-73-ST | 1 | 2025-02-20 | 2025-02-22 | 2025-08-30
| JD3RZ02-1L73ST9615 | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-1-L-73-ST | 1 | 2025-02-25 | 2025-02-26 | 2025-08-09
| JD3RZ02-1L73ST9616 | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-1-L-73-ST | 1 | 2025-02-27 | 2025-03-01 | 2025-08-12
| JD3RZ02-1L73ST9617 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-1-L-73-ST | 1 | 2025-03-02 | 2025-03-03
| JD3RZ02-1L73ST9618 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-1-L-73-ST | 1 | 2025-03-04 | 2025-03-05
| JD3RZ02-1L73ST9619 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-1-L-73-ST | 1 | 2025-03-06 | 2025-03-08
| JD3RZ02-1L73ST9625 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-1-L-73-ST | 1 | 2025-03-03 | 2025-03-04 | 2025-08-16 | 2025-09-03
| JD3RZ02-1L73ST9626 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-1-L-73-ST | 1 | 2025-03-05 | 2025-03-06 | 2025-09-04 | 2025-09-07
| JD3RZ02-1L73ST9627 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-1-L-73-ST | 1 | 2025-03-08 | 2025-03-09
| JD3RZ02-1L73ST9628 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-1-L-73-ST | 1 | 2025-03-10 | 2025-03-11
| JD3RZ02-1L73ST9629 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-1-L-73-ST | 1 | 2025-03-12 | 2025-03-13
| JD3RZ02-1L73ST9630 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-1-L-73-ST | 1 | 2025-03-05 | 2025-03-06
| JD3RZ02-1L73ST9631 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-1-L-73-ST | 1 | 2025-03-08 | 2025-03-09
| JD3RZ02-1L73ST9632 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-1-L-73-ST | 1 | 2025-03-10 | 2025-03-11
| JD3RZ02-1L73ST9633 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-1-L-73-ST | 1 | 2025-03-12 | 2025-03-13
| JD3RZ02-1L73ST9634 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-1-L-73-ST | 1 | 2025-03-15 | 2025-03-16
| JD3RZ02-1L73ST9645 | Excavation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z02-1-L-73-ST | 1 | 2025-03-08 | 2025-03-09
| JD3RZ02-1L73ST9646 | Base Plain Concrete Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z02-1-L-73-ST | 1 | 2025-03-10 | 2025-03-11
| JD3RZ02-1L73ST9647 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z02-1-L-73-ST | 1 | 2025-03-12 | 2025-03-13
| JD3RZ02-1L73ST9648 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z02-1-L-73-ST | 1 | 2025-03-15 | 2025-03-16
| JD3RZ02-1L73ST9649 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z02-1-L-73-ST | 1 | 2025-03-17 | 2025-03-18
| JD3RZ02-1L73ST9650 | EXCAVATION Works for Catchbasine single - - B6.33 05 39.09-Z02-1-L-73-ST | 1 | 2025-03-10 | 2025-03-12
| JD3RZ02-1L73ST9651 | Catchbasine Installation Works For Catchbasine single - - B6.33 05 39.09-Z02-1-L-73-ST | 1 | 2025-03-13 | 2025-03-17
| JD3RZ02-1L73ST9652 | FINISHING Works For Catchbasine single - - B6.33 05 39.09-Z02-1-L-73-ST | 1 | 2025-03-18 | 2025-03-22
| JD3RZ02-1L73ST9653 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - - B6.33 05 39.09-Z02-1-L-73-ST | 1 | 2025-03-23 | 2025-03-25
| JD3RZ02-1L73ST9654 | EXCAVATION Works for Catchbasine double - - B6.33 05 39.10-Z02-1-L-73-ST | 1 | 2025-03-13 | 2025-03-15
| JD3RZ02-1L73ST9655 | Catchbasine Installation Works For Catchbasine double - - B6.33 05 39.10-Z02-1-L-73-ST | 1 | 2025-03-16 | 2025-03-18
| JD3RZ02-1L73ST9656 | FINISHING Works For Catchbasine double - - B6.33 05 39.10-Z02-1-L-73-ST | 1 | 2025-03-19 | 2025-03-22
| JD3RZ02-1L73ST9657 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - - B6.33 05 39.10-Z02-1-L-73-ST | 1 | 2025-03-23 | 2025-03-24
| JD3RZ02-1L73TC9988 | Excavation Worksfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z02-1-L-73-TC | 1 | 2025-04-09 | 2025-04-10
| JD3RZ02-1L73TC9989 | Installationfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z02-1-L-73-TC | 1 | 2025-04-12 | 2025-04-15
| JD3RZ02-1L73TC9990 | Pouring Concrete Coverfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z02-1-L-73-TC | 1 | 2025-04-16 | 2025-04-20
| JD3RZ02-1L73TC9991 | Backfilling Worksfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z02-1-L-73-TC | 1 | 2025-05-05 | 2025-05-06
| JD3RZ02-1L73TC9992 | Excavation and Bedding Worksfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z02-1-L-73-TC | 1 | 2025-04-24 | 2025-04-26
| JD3RZ02-1L73TC9993 | Installationfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z02-1-L-73-TC | 1 | 2025-04-27 | 2025-04-28
| JD3RZ02-1L73TC9994 | Backfilling Worksfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z02-1-L-73-TC | 1 | 2025-04-29 | 2025-04-30
| JD3RZ02-1L73TSE9708 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-1-L-73-TSE | 1 | 2025-03-13 | 2025-03-15
| JD3RZ02-1L73TSE9709 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-1-L-73-TSE | 1 | 2025-03-26 | 2025-03-27
| JD3RZ02-1L73TSE9710 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-1-L-73-TSE | 1 | 2025-03-29 | 2025-03-30
| JD3RZ02-1L73TSE9711 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-1-L-73-TSE | 1 | 2025-04-23 | 2025-04-24
| JD3RZ02-1L73TSE9712 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-1-L-73-TSE | 1 | 2025-04-26 | 2025-04-27
| JD3RZ02-1L73TSE9713 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-1-L-73-TSE | 1 | 2025-03-16 | 2025-03-19
| JD3RZ02-1L73TSE9714 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-1-L-73-TSE | 1 | 2025-03-20 | 2025-03-24
| JD3RZ02-1L73TSE9715 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-1-L-73-TSE | 1 | 2025-03-25 | 2025-04-01
| JD3RZ02-1L73TSE9716 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-1-L-73-TSE | 1 | 2025-04-23 | 2025-04-28
| JD3RZ02-1L73TSE9717 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-1-L-73-TSE | 1 | 2025-04-29 | 2025-05-04
| JD3RZ02-1L73TSE9833 | Installationfor gate valves 100 mm - - B4.33 14 19.01-Z02-1-L-73-TSE | 1 | 2025-04-02 | 2025-04-03
| JD3RZ02-1L73TSE9834 | Testing And Commtionningfor gate valves 100 mm - - B4.33 14 19.01-Z02-1-L-73-TSE | 1 | 2025-04-07 | 2025-04-08
| JD3RZ02-1L73TSE9835 | Installationfor gate valves 250 mm - - B4.33 14 19.02-Z02-1-L-73-TSE | 1 | 2025-04-02 | 2025-04-03
| JD3RZ02-1L73TSE9836 | Testing And Commtionningfor gate valves 250 mm - - B4.33 14 19.02-Z02-1-L-73-TSE | 1 | 2025-04-05 | 2025-04-06
| JD3RZ02-1L73TSE9845 | Installationfor Wash-Out valves 100 mm. - on pipes with diameter 110-400 mm- B4.33 14 19.07-Z02-1-L-73-TSE | 1 | 2025-04-02 | 2025-04-03
| JD3RZ02-1L73TSE9846 | Testing And Commtionningfor Wash-Out valves 100 mm. - on pipes with diameter 110-400 mm- B4.33 14 19.07-Z02-1-L-73-TSE | 1 | 2025-04-05 | 2025-04-06
| JD3RZ02-1L73TSE9869 | EXCAVATION and Bedding Worksfor Wash-out Valve Chamber - 110 to 400 MM- B4.33 14 13.06-Z02-1-L-73-TSE | 1 | 2025-03-20 | 2025-03-22
| JD3RZ02-1L73TSE9870 | Plain Concrete Worksfor Wash-out Valve Chamber - 110 to 400 MM- B4.33 14 13.06-Z02-1-L-73-TSE | 1 | 2025-03-23 | 2025-03-24
| JD3RZ02-1L73TSE9871 | INSTALLATIONfor Wash-out Valve Chamber - 110 to 400 MM- B4.33 14 13.06-Z02-1-L-73-TSE | 1 | 2025-03-25 | 2025-03-26
| JD3RZ02-1L73TSE9872 | Backfilling Worksfor Wash-out Valve Chamber - 110 to 400 MM- B4.33 14 13.06-Z02-1-L-73-TSE | 1 | 2025-03-27 | 2025-03-29
| JD3RZ02-1L73WT9658 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-1-L-73-WT | 1 | 2025-03-16 | 2025-03-17
| JD3RZ02-1L73WT9659 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-1-L-73-WT | 1 | 2025-03-18 | 2025-03-19
| JD3RZ02-1L73WT9660 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-1-L-73-WT | 1 | 2025-03-20 | 2025-03-22
| JD3RZ02-1L73WT9661 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-1-L-73-WT | 1 | 2025-03-23 | 2025-03-24
| JD3RZ02-1L73WT9662 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-1-L-73-WT | 1 | 2025-04-07 | 2025-04-08
| JD3RZ02-1L73WT9663 | Excavation Worksfor HDPE Pipes 225 mm - depth from 0 to 1.5 m- B3.33 14 13.02-Z02-1-L-73-WT | 1 | 2025-03-18 | 2025-03-20
| JD3RZ02-1L73WT9664 | Soil Replacement and Bedding Works for HDPE Pipes 225 mm - depth from 0 to 1.5 m- B3.33 14 13.02-Z02-1-L-73-WT | 1 | 2025-03-22 | 2025-03-25
| JD3RZ02-1L73WT9665 | Installing for HDPE Pipes 225 mm - depth from 0 to 1.5 m- B3.33 14 13.02-Z02-1-L-73-WT | 1 | 2025-03-26 | 2025-04-01
| JD3RZ02-1L73WT9666 | Testing for HDPE Pipes 225 mm - depth from 0 to 1.5 m- B3.33 14 13.02-Z02-1-L-73-WT | 1 | 2025-04-15 | 2025-04-19
| JD3RZ02-1L73WT9667 | Backfillingfor HDPE Pipes 225 mm - depth from 0 to 1.5 m- B3.33 14 13.02-Z02-1-L-73-WT | 1 | 2025-04-20 | 2025-04-23
| JD3RZ02-1L73WT9685 | INSTALLATIONfor gate valves 200 mm - - B3.33 14 19.02-Z02-1-L-73-WT | 1 | 2025-04-02 | 2025-04-03
| JD3RZ02-1L73WT9686 | TESTING AND COMMITIONfor gate valves 200 mm - - B3.33 14 19.02-Z02-1-L-73-WT | 1 | 2025-04-05 | 2025-04-06
| JD3RZ02-1L73WT9693 | EXCAVATION and Bedding Worksfor Fire Hydrant - - B3.33 14 19.08-Z02-1-L-73-WT | 1 | 2025-03-22 | 2025-03-23
| JD3RZ02-1L73WT9694 | INSTALLATIONfor Fire Hydrant - - B3.33 14 19.08-Z02-1-L-73-WT | 1 | 2025-03-24 | 2025-03-25
| JD3RZ02-1L73WT9695 | TESTING AND COMMITIONfor Fire Hydrant - - B3.33 14 19.08-Z02-1-L-73-WT | 1 | 2025-03-26 | 2025-03-27
| JD3RZ02-2C16SL10665 | Excavation of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-2-C-16-SL | 1 | 2025-04-20 | 2025-04-21 | 2025-08-04 | 2025-08-10
| JD3RZ02-2C16SL10666 | Installation of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-2-C-16-SL | 1 | 2025-04-22 | 2025-04-23 | 2025-08-10 | 2025-08-16
| JD3RZ02-2C16SL10667 | Backfilling of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-2-C-16-SL | 1 | 2025-04-24 | 2025-04-26 | 2025-08-17 | 2025-08-20
| JD3RZ02-2C16SL10668 | Installation Worksfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-2-C-16-SL | 1 | 2025-04-27 | 2025-04-29 | 2025-08-21 | 2025-08-24
| JD3RZ02-2C16SL10669 | Testing and Commitioningfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-2-C-16-SL | 1 | 2025-04-30 | 2025-05-03
| JD3RZ02-2C16SL10670 | Installationfor Lighting( LED ) Luminaire 150 WATT - - B2.26.56.19.01-Z02-2-C-16-SL | 1 | 2025-04-27 | 2025-04-28 | 2025-08-21 | 2025-08-24
| JD3RZ02-2C16SL10686 | Excavationfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z02-2-C-16-SL | 1 | 2025-04-22 | 2025-04-23 | 2025-08-04 | 2025-08-10
| JD3RZ02-2C16SL10687 | Installationfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z02-2-C-16-SL | 1 | 2025-04-24 | 2025-04-26 | 2025-08-10 | 2025-08-16
| JD3RZ02-2C16SL10688 | Backfillingfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z02-2-C-16-SL | 1 | 2025-04-27 | 2025-04-28 | 2025-08-17 | 2025-08-20
| JD3RZ02-2C16ST10145 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-2-C-16-ST | 1 | 2025-02-01 | 2025-02-03 | 2025-08-03
| JD3RZ02-2C16ST10146 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-2-C-16-ST | 1 | 2025-02-04 | 2025-02-06 | 2025-08-07
| JD3RZ02-2C16ST10147 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-2-C-16-ST | 1 | 2025-02-08 | 2025-02-11 | 2025-08-10
| JD3RZ02-2C16ST10148 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-2-C-16-ST | 1 | 2025-02-12 | 2025-02-16
| JD3RZ02-2C16ST10149 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-2-C-16-ST | 1 | 2025-03-08 | 2025-03-12
| JD3RZ02-2C16ST10150 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-2-C-16-ST | 1 | 2025-02-04 | 2025-02-05
| JD3RZ02-2C16ST10151 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-2-C-16-ST | 1 | 2025-02-06 | 2025-02-08
| JD3RZ02-2C16ST10152 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-2-C-16-ST | 1 | 2025-02-09 | 2025-02-10
| JD3RZ02-2C16ST10153 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-2-C-16-ST | 1 | 2025-02-11 | 2025-02-12
| JD3RZ02-2C16ST10154 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-2-C-16-ST | 1 | 2025-03-05 | 2025-03-06
| JD3RZ02-2C16ST10155 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-2-C-16-ST | 1 | 2024-09-04 | 2024-09-05 | 2025-07-05 | 2025-07-22
| JD3RZ02-2C16ST10155.R | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-2-C-16-ST -Remaining | 1 | 2025-02-06 | 2025-02-08 | 2025-08-09 | 2025-08-11
| JD3RZ02-2C16ST10156 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-2-C-16-ST | 1 | 2024-09-07 | 2024-09-08 | 2025-08-10 | 2025-08-11
| JD3RZ02-2C16ST10156.R | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-2-C-16-ST -R | 1 | 2025-02-09 | 2025-02-10 | 2025-08-11 | 2025-08-12
| JD3RZ02-2C16ST10157 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-2-C-16-ST | 1 | 2025-02-11 | 2025-02-12 | 2025-08-14 | 2025-08-15
| JD3RZ02-2C16ST10158 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-2-C-16-ST | 1 | 2025-02-13 | 2025-02-15 | 2025-08-16 | 2025-08-17
| JD3RZ02-2C16ST10159 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-2-C-16-ST | 1 | 2025-03-05 | 2025-03-06 | 2025-08-18 | 2025-08-20
| JD3RZ02-2C16ST10175 | Excavation Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-2-C-16-ST | 1 | 2024-09-07 | 2024-09-08 | 2025-06-30 | 2025-07-17
| JD3RZ02-2C16ST10176 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-2-C-16-ST | 1 | 2024-09-09 | 2024-09-10 | 2025-07-03 | 2025-07-21
| JD3RZ02-2C16ST10177 | Installing for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-2-C-16-ST | 1 | 2024-09-09 | 2024-09-10 | 2025-07-06 | 2025-07-31
| JD3RZ02-2C16ST10178 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-2-C-16-ST | 1 | 2024-09-11 | 2024-09-12 | 2025-07-07 | 2025-07-31
| JD3RZ02-2C16ST10178.R | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-2-C-16-ST -Remaining | 1 | 2025-02-16 | 2025-02-17 | 2025-08-18 | 2025-08-20
| JD3RZ02-2C16ST10179 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-2-C-16-ST | 1 | 2024-09-14 | 2024-09-15 | 2025-07-08 | 2025-07-31
| JD3RZ02-2C16ST10179.R | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-2-C-16-ST -Remaining | 1 | 2025-02-18 | 2025-02-19 | 2025-08-21 | 2025-08-23
| JD3RZ02-2C16ST10195 | Excavation Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-2-C-16-ST | 1 | 2024-09-14 | 2024-09-15 | 2025-07-05 | 2025-07-22
| JD3RZ02-2C16ST10195.R | Excavation Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-2-C-16-ST -Remaining | 1 | 2025-02-09 | 2025-02-10 | 2025-08-11 | 2025-08-12
| JD3RZ02-2C16ST10196 | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-2-C-16-ST | 1 | 2024-09-16 | 2024-09-17 | 2025-07-08 | 2025-07-31
| JD3RZ02-2C16ST10196.R | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-2-C-16-ST -R | 1 | 2025-02-11 | 2025-02-12 | 2025-08-14 | 2025-08-16
| JD3RZ02-2C16ST10197 | Installing for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-2-C-16-ST | 1 | 2025-02-13 | 2025-02-16 | 2025-08-16 | 2025-08-18
| JD3RZ02-2C16ST10198 | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-2-C-16-ST | 1 | 2025-02-17 | 2025-02-18 | 2025-08-20 | 2025-08-21
| JD3RZ02-2C16ST10199 | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z02-2-C-16-ST | 1 | 2025-03-08 | 2025-03-10 | 2025-08-22
| JD3RZ02-2C16ST10205 | Excavation Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z02-2-C-16-ST | 1 | 2024-09-04 | 2024-09-05 | 2025-01-27 | 2025-02-13
| JD3RZ02-2C16ST10206 | Soil Replacement and Bedding Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z02-2-C-16-ST | 1 | 2024-09-07 | 2024-09-08 | 2025-01-28 | 2025-02-15
| JD3RZ02-2C16ST10207 | Installing for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z02-2-C-16-ST | 1 | 2024-09-09 | 2024-09-10 | 2025-01-29 | 2025-02-16
| JD3RZ02-2C16ST10208 | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z02-2-C-16-ST | 1 | 2024-09-11 | 2024-09-12 | 2025-04-05 | 2025-04-22
| JD3RZ02-2C16ST10209 | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z02-2-C-16-ST | 1 | 2024-09-16 | 2024-09-17 | 2025-04-05 | 2025-04-22
| JD3RZ02-2C16ST10209.R | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z02-2-C-16-ST -Remaining | 1 | 2025-03-11 | 2025-03-12 | 2025-08-20
| JD3RZ02-2C16ST10215 | Excavation Works for GRP Pipe Line 1000 mm - depth from 0.00 to 1.50 m- B6.33 42 11.14-Z02-2-C-16-ST | 1 | 2024-09-04 | 2024-09-05 | 2025-06-12 | 2025-06-30
| JD3RZ02-2C16ST10216 | Soil Replacement and Bedding Works for GRP Pipe Line 1000 mm - depth from 0.00 to 1.50 m- B6.33 42 11.14-Z02-2-C-16-ST | 1 | 2024-09-07 | 2024-09-08 | 2025-06-14 | 2025-07-01
| JD3RZ02-2C16ST10217 | Installing for GRP Pipe Line 1000 mm - depth from 0.00 to 1.50 m- B6.33 42 11.14-Z02-2-C-16-ST | 1 | 2024-09-09 | 2024-09-10 | 2025-06-16 | 2025-07-03
| JD3RZ02-2C16ST10218 | Primary Test for GRP Pipe Line 1000 mm - depth from 0.00 to 1.50 m- B6.33 42 11.14-Z02-2-C-16-ST | 1 | 2025-02-19 | 2025-02-20 | 2025-08-11 | 2025-08-13
| JD3RZ02-2C16ST10219 | Backfilling Works for GRP Pipe Line 1000 mm - depth from 0.00 to 1.50 m- B6.33 42 11.14-Z02-2-C-16-ST | 1 | 2025-02-22 | 2025-02-23 | 2025-08-14 | 2025-08-15
| JD3RZ02-2C16ST10220 | Excavation Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z02-2-C-16-ST | 1 | 2024-09-04 | 2024-09-05 | 2025-06-12 | 2025-06-30
| JD3RZ02-2C16ST10221 | Soil Replacement and Bedding Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z02-2-C-16-ST | 1 | 2024-09-07 | 2024-09-08 | 2025-06-14 | 2025-07-10
| JD3RZ02-2C16ST10222 | Installing for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z02-2-C-16-ST | 1 | 2024-09-18 | 2024-09-19 | 2025-06-16 | 2025-07-13
| JD3RZ02-2C16ST10222.R | Installing for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z02-2-C-16-ST -Remaining | 1 | 2025-02-17 | 2025-02-18 | 2025-08-11 | 2025-08-13
| JD3RZ02-2C16ST10223 | Primary Test for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z02-2-C-16-ST | 1 | 2025-02-19 | 2025-02-20 | 2025-08-14 | 2025-08-15
| JD3RZ02-2C16ST10224 | Backfilling Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z02-2-C-16-ST | 1 | 2025-02-24 | 2025-02-26 | 2025-08-16
| JD3RZ02-2C16ST10250 | Excavation Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z02-2-C-16-ST | 1 | 2024-09-04 | 2024-09-07 | 2025-05-21 | 2025-06-17
| JD3RZ02-2C16ST10251 | Soil Replacement and Bedding Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z02-2-C-16-ST | 1 | 2024-09-08 | 2024-09-10 | 2025-05-22 | 2025-06-28
| JD3RZ02-2C16ST10252 | Installing for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z02-2-C-16-ST | 1 | 2024-09-11 | 2024-09-14 | 2025-06-12 | 2025-07-19
| JD3RZ02-2C16ST10253 | Primary Test for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z02-2-C-16-ST | 1 | 2025-02-22 | 2025-02-24 | 2025-08-16 | 2025-08-18
| JD3RZ02-2C16ST10254 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z02-2-C-16-ST | 1 | 2025-02-27 | 2025-03-03 | 2025-08-18 | 2025-08-20
| JD3RZ02-2C16ST10255 | Excavation Works for GRP Pipe Line 1200 mm - depth from 2.51 to 3.50 m- B6.33 42 11.24-Z02-2-C-16-ST | 1 | 2025-02-11 | 2025-02-12 | 2025-08-11 | 2025-08-13
| JD3RZ02-2C16ST10256 | Soil Replacement and Bedding Works for GRP Pipe Line 1200 mm - depth from 2.51 to 3.50 m- B6.33 42 11.24-Z02-2-C-16-ST | 1 | 2025-02-13 | 2025-02-15 | 2025-08-14 | 2025-08-15
| JD3RZ02-2C16ST10257 | Installing for GRP Pipe Line 1200 mm - depth from 2.51 to 3.50 m- B6.33 42 11.24-Z02-2-C-16-ST | 1 | 2025-02-16 | 2025-02-17 | 2025-08-16 | 2025-08-17
| JD3RZ02-2C16ST10258 | Primary Test for GRP Pipe Line 1200 mm - depth from 2.51 to 3.50 m- B6.33 42 11.24-Z02-2-C-16-ST | 1 | 2025-02-18 | 2025-02-19 | 2025-08-18 | 2025-08-20
| JD3RZ02-2C16ST10259 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 2.51 to 3.50 m- B6.33 42 11.24-Z02-2-C-16-ST | 1 | 2025-03-05 | 2025-03-06 | 2025-08-21 | 2025-08-23
| JD3RZ02-2C16ST10274 | Excavation Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - - B6.34 42 16.03-Z02-2-C-16-ST | 1 | 2024-09-21 | 2024-09-30 | 2025-01-05 | 2025-03-19
| JD3RZ02-2C16ST10275 | Plain Concrete Works For Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - - B6.34 42 16.03-Z02-2-C-16-ST | 1 | 2024-10-01 | 2024-10-03 | 2025-01-11 | 2025-02-06
| JD3RZ02-2C16ST10275.R | Plain Concrete Works For Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - - B6.34 42 16.03-Z02-2-C-16-ST | 1 | 2024-10-05 | 2024-10-06 | 2025-08-02 | 2025-08-03
| JD3RZ02-2C16ST10276 | Raft Foundation for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - - B6.34 42 16.03-Z02-2-C-16-ST | 1 | 2024-10-05 | 2024-10-19 | 2025-01-14 | 2025-05-14
| JD3RZ02-2C16ST10276.R | Raft Foundation for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - - B6.34 42 16.03-Z02-2-C-16-ST | 1 | 2024-10-20 | 2024-10-21 | 2025-08-04 | 2025-08-05
| JD3RZ02-2C16ST10277 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.34 42 16.03-Z02-2-C-16-ST | 1 | 2024-10-20 | 2024-11-11 | 2025-02-05 | 2025-07-31
| JD3RZ02-2C16ST10277.R | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.34 42 16.03-Z02-2-C-16-ST | 1 | 2024-11-12 | 2024-11-13 | 2025-08-06
| JD3RZ02-2C16ST10278 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.34 42 16.03-Z02-2-C-16-ST | 1 | 2024-11-12 | 2024-12-04 | 2025-03-05 | 2025-07-31
| JD3RZ02-2C16ST10278.R | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.34 42 16.03-Z02-2-C-16-ST | 1 | 2024-12-05 | 2024-12-07 | 2025-08-09
| JD3RZ02-2C16ST10279 | Isolation Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - - B6.34 42 16.03-Z02-2-C-16-ST | 1 | 2024-12-05 | 2024-12-19 | 2025-05-20 | 2025-07-31
| JD3RZ02-2C16ST10279.R | Isolation Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - - B6.34 42 16.03-Z02-2-C-16-ST | 1 | 2024-12-21 | 2024-12-22 | 2025-08-11
| JD3RZ02-2C16ST10280 | Backfilling Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - - B6.34 42 16.03-Z02-2-C-16-ST | 1 | 2024-12-21 | 2024-12-24 | 2025-05-25 | 2025-06-30
| JD3RZ02-2C16ST10280.R | Backfilling Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - - B6.34 42 16.03-Z02-2-C-16-ST | 1 | 2025-01-05 | 2025-01-06 | 2025-08-16
| JD3RZ02-2C16ST10281 | Excavation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-Z02-2-C-16-ST | 1 | 2024-10-07 | 2024-10-08 | 2025-09-03
| JD3RZ02-2C16ST10282 | Plain Concrete Works For Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-Z02-2-C-16-ST | 1 | 2024-10-09 | 2024-10-10
| JD3RZ02-2C16ST10283 | Raft Foundation for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-Z02-2-C-16-ST | 1 | 2024-10-12 | 2024-10-17
| JD3RZ02-2C16ST10284 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-Z02-2-C-16-ST | 1 | 2025-01-07 | 2025-01-15
| JD3RZ02-2C16ST10285 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-Z02-2-C-16-ST | 1 | 2025-01-16 | 2025-01-25
| JD3RZ02-2C16ST10286 | Isolation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-Z02-2-C-16-ST | 1 | 2025-01-26 | 2025-01-28
| JD3RZ02-2C16ST10287 | Backfilling Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-Z02-2-C-16-ST | 1 | 2025-01-29 | 2025-01-30
| JD3RZ02-2C16ST10328 | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-2-C-16-ST | 1 | 2024-10-01 | 2024-10-02 | 2025-05-25 | 2025-06-11
| JD3RZ02-2C16ST10328.R | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-2-C-16-ST -Remaining | 1 | 2025-02-13 | 2025-02-15 | 2025-08-09 | 2025-08-10
| JD3RZ02-2C16ST10329 | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-2-C-16-ST | 1 | 2025-02-16 | 2025-02-17 | 2025-08-11 | 2025-08-12
| JD3RZ02-2C16ST10330 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-2-C-16-ST | 1 | 2025-02-18 | 2025-02-19
| JD3RZ02-2C16ST10331 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-2-C-16-ST | 1 | 2025-02-20 | 2025-02-22
| JD3RZ02-2C16ST10332 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-2-C-16-ST | 1 | 2025-02-23 | 2025-02-24
| JD3RZ02-2C16ST10338 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-2-C-16-ST | 1 | 2024-10-03 | 2024-10-05 | 2025-05-25 | 2025-06-11
| JD3RZ02-2C16ST10338.R | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-2-C-16-ST -Remaining | 1 | 2025-02-16 | 2025-02-17 | 2025-08-11 | 2025-08-12
| JD3RZ02-2C16ST10339 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-2-C-16-ST | 1 | 2024-10-06 | 2024-10-07 | 2025-05-28 | 2025-06-15
| JD3RZ02-2C16ST10339.R | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-2-C-16-ST -Remaining | 1 | 2025-02-18 | 2025-02-19 | 2025-08-14 | 2025-08-16
| JD3RZ02-2C16ST10340 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-2-C-16-ST | 1 | 2024-10-08 | 2024-10-09 | 2025-06-01 | 2025-06-18
| JD3RZ02-2C16ST10340.R | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-2-C-16-ST -Remaining | 1 | 2025-02-20 | 2025-02-22
| JD3RZ02-2C16ST10341 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-2-C-16-ST | 1 | 2025-02-23 | 2025-02-24
| JD3RZ02-2C16ST10342 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z02-2-C-16-ST | 1 | 2025-02-25 | 2025-02-26
| JD3RZ02-2C16ST10343 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-2-C-16-ST | 1 | 2025-02-18 | 2025-02-19
| JD3RZ02-2C16ST10344 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-2-C-16-ST | 1 | 2025-02-20 | 2025-02-23
| JD3RZ02-2C16ST10345 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-2-C-16-ST | 1 | 2025-02-24 | 2025-02-26
| JD3RZ02-2C16ST10346 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-2-C-16-ST | 1 | 2025-02-27 | 2025-03-01
| JD3RZ02-2C16ST10347 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-2-C-16-ST | 1 | 2025-03-02 | 2025-03-03
| JD3RZ02-2C16ST10358 | Excavation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z02-2-C-16-ST | 1 | 2024-09-04 | 2024-09-05 | 2025-05-25 | 2025-06-11
| JD3RZ02-2C16ST10359 | Base Plain Concrete Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z02-2-C-16-ST | 1 | 2025-02-24 | 2025-02-26 | 2025-08-20 | 2025-08-21
| JD3RZ02-2C16ST10360 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z02-2-C-16-ST | 1 | 2025-02-27 | 2025-03-02 | 2025-08-23 | 2025-08-25
| JD3RZ02-2C16ST10361 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z02-2-C-16-ST | 1 | 2025-03-03 | 2025-03-04
| JD3RZ02-2C16ST10362 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z02-2-C-16-ST | 1 | 2025-03-05 | 2025-03-06
| JD3RZ02-2C16ST10363 | EXCAVATION Works for Catchbasine single - - B6.33 05 39.09-Z02-2-C-16-ST | 1 | 2025-02-20 | 2025-02-23 | 2025-08-16
| JD3RZ02-2C16ST10364 | Catchbasine Installation Works For Catchbasine single - - B6.33 05 39.09-Z02-2-C-16-ST | 1 | 2025-02-24 | 2025-02-27
| JD3RZ02-2C16ST10365 | FINISHING Works For Catchbasine single - - B6.33 05 39.09-Z02-2-C-16-ST | 1 | 2025-03-01 | 2025-03-04
| JD3RZ02-2C16ST10366 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - - B6.33 05 39.09-Z02-2-C-16-ST | 1 | 2025-03-08 | 2025-03-10
| JD3RZ02-2C16ST10367 | EXCAVATION Works for Catchbasine double - - B6.33 05 39.10-Z02-2-C-16-ST | 1 | 2025-02-24 | 2025-02-25
| JD3RZ02-2C16ST10368 | Catchbasine Installation Works For Catchbasine double - - B6.33 05 39.10-Z02-2-C-16-ST | 1 | 2025-02-26 | 2025-03-01
| JD3RZ02-2C16ST10369 | FINISHING Works For Catchbasine double - - B6.33 05 39.10-Z02-2-C-16-ST | 1 | 2025-03-02 | 2025-03-04
| JD3RZ02-2C16ST10370 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - - B6.33 05 39.10-Z02-2-C-16-ST | 1 | 2025-03-11 | 2025-03-12
| JD3RZ02-2C16ST524343 | Concrete encasement for pipes- NNB6.33 42 11.25-MR-C-16-ST | 1 | 2025-02-13 | 2025-03-04
| JD3RZ02-2C16TSE10421 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-2-C-16-TSE | 1 | 2025-03-13 | 2025-03-15
| JD3RZ02-2C16TSE10422 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-2-C-16-TSE | 1 | 2025-03-16 | 2025-03-17
| JD3RZ02-2C16TSE10423 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-2-C-16-TSE | 1 | 2025-03-18 | 2025-03-20
| JD3RZ02-2C16TSE10424 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-2-C-16-TSE | 1 | 2025-03-22 | 2025-03-23
| JD3RZ02-2C16TSE10425 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-2-C-16-TSE | 1 | 2025-04-08 | 2025-04-09
| JD3RZ02-2C16TSE10426 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-2-C-16-TSE | 1 | 2025-03-16 | 2025-03-17
| JD3RZ02-2C16TSE10427 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-2-C-16-TSE | 1 | 2025-03-18 | 2025-03-19
| JD3RZ02-2C16TSE10428 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-2-C-16-TSE | 1 | 2025-03-20 | 2025-03-22
| JD3RZ02-2C16TSE10429 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-2-C-16-TSE | 1 | 2025-03-23 | 2025-03-24
| JD3RZ02-2C16TSE10430 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-2-C-16-TSE | 1 | 2025-04-08 | 2025-04-09
| JD3RZ02-2C16TSE10431 | Excavation Worksfor HDPE Pipes 315 mm - depth from 0 to 1.5 m- B4.33 31 00.03-Z02-2-C-16-TSE | 1 | 2025-03-18 | 2025-03-19
| JD3RZ02-2C16TSE10432 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 0 to 1.5 m- B4.33 31 00.03-Z02-2-C-16-TSE | 1 | 2025-03-20 | 2025-03-22
| JD3RZ02-2C16TSE10433 | Installing for HDPE Pipes 315 mm - depth from 0 to 1.5 m- B4.33 31 00.03-Z02-2-C-16-TSE | 1 | 2025-03-23 | 2025-03-24
| JD3RZ02-2C16TSE10434 | Testing for HDPE Pipes 315 mm - depth from 0 to 1.5 m- B4.33 31 00.03-Z02-2-C-16-TSE | 1 | 2025-03-25 | 2025-03-26
| JD3RZ02-2C16TSE10435 | Backfillingfor HDPE Pipes 315 mm - depth from 0 to 1.5 m- B4.33 31 00.03-Z02-2-C-16-TSE | 1 | 2025-04-08 | 2025-04-09
| JD3RZ02-2C16TSE10461 | Excavation Worksfor HDPE Pipes 450 mm - depth from 0 to 1.5 m- B4.33 31 00.09-Z02-2-C-16-TSE | 1 | 2025-03-20 | 2025-03-22 | 2025-08-09 | 2025-08-10
| JD3RZ02-2C16TSE10462 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 0 to 1.5 m- B4.33 31 00.09-Z02-2-C-16-TSE | 1 | 2025-03-23 | 2025-03-24 | 2025-08-11 | 2025-08-12
| JD3RZ02-2C16TSE10463 | Installing for HDPE Pipes 450 mm - depth from 0 to 1.5 m- B4.33 31 00.09-Z02-2-C-16-TSE | 1 | 2025-03-25 | 2025-03-27 | 2025-08-13 | 2025-08-16
| JD3RZ02-2C16TSE10464 | Testing for HDPE Pipes 450 mm - depth from 0 to 1.5 m- B4.33 31 00.09-Z02-2-C-16-TSE | 1 | 2025-03-29 | 2025-03-30 | 2025-09-16 | 2025-09-20
| JD3RZ02-2C16TSE10465 | Backfillingfor HDPE Pipes 450 mm - depth from 0 to 1.5 m- B4.33 31 00.09-Z02-2-C-16-TSE | 1 | 2025-04-08 | 2025-04-09 | 2025-08-27 | 2025-08-28
| JD3RZ02-2C16TSE10466 | Excavation Worksfor HDPE Pipes 450 mm - depth from 1.51 to 2.5 m- B4.33 31 00.10-Z02-2-C-16-TSE | 1 | 2025-03-23 | 2025-03-24 | 2025-08-11 | 2025-09-02
| JD3RZ02-2C16TSE10467 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m- B4.33 31 00.10-Z02-2-C-16-TSE | 1 | 2025-03-25 | 2025-03-26 | 2025-08-13 | 2025-09-04
| JD3RZ02-2C16TSE10468 | Installing for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m- B4.33 31 00.10-Z02-2-C-16-TSE | 1 | 2025-03-27 | 2025-03-29 | 2025-08-16 | 2025-09-06
| JD3RZ02-2C16TSE10469 | Testing for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m- B4.33 31 00.10-Z02-2-C-16-TSE | 1 | 2025-03-30 | 2025-03-31 | 2025-09-16 | 2025-09-20
| JD3RZ02-2C16TSE10470 | Backfillingfor HDPE Pipes 450 mm - depth from 1.51 to 2.5 m- B4.33 31 00.10-Z02-2-C-16-TSE | 1 | 2025-04-01 | 2025-04-02 | 2025-08-20
| JD3RZ02-2C16TSE10471 | Excavation Worksfor HDPE Pipes 450 mm - depth from 2.51 to 3.5 m- B4.33 31 00.11-Z02-2-C-16-TSE | 1 | 2025-03-25 | 2025-03-26 | 2025-08-31 | 2025-09-02
| JD3RZ02-2C16TSE10472 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 2.51 to 3.5 m- B4.33 31 00.11-Z02-2-C-16-TSE | 1 | 2025-03-27 | 2025-03-29 | 2025-09-02 | 2025-09-04
| JD3RZ02-2C16TSE10473 | Installing for HDPE Pipes 450 mm - depth from 2.51 to 3.5 m- B4.33 31 00.11-Z02-2-C-16-TSE | 1 | 2025-03-30 | 2025-03-31 | 2025-09-04 | 2025-09-06
| JD3RZ02-2C16TSE10474 | Testing for HDPE Pipes 450 mm - depth from 2.51 to 3.5 m- B4.33 31 00.11-Z02-2-C-16-TSE | 1 | 2025-04-01 | 2025-04-02 | 2025-09-16 | 2025-09-20
| JD3RZ02-2C16TSE10475 | Backfillingfor HDPE Pipes 450 mm - depth from 2.51 to 3.5 m- B4.33 31 00.11-Z02-2-C-16-TSE | 1 | 2025-04-03 | 2025-04-05
| JD3RZ02-2C16TSE10476 | Excavation Worksfor HDPE Pipes 450 mm - depth from 3.51 to 4.5 m- B4.33 31 00.12-Z02-2-C-16-TSE | 1 | 2025-03-27 | 2025-03-29 | 2025-08-31 | 2025-09-02
| JD3RZ02-2C16TSE10477 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 3.51 to 4.5 m- B4.33 31 00.12-Z02-2-C-16-TSE | 1 | 2025-03-30 | 2025-03-31 | 2025-09-02 | 2025-09-04
| JD3RZ02-2C16TSE10478 | Installing for HDPE Pipes 450 mm - depth from 3.51 to 4.5 m- B4.33 31 00.12-Z02-2-C-16-TSE | 1 | 2025-04-01 | 2025-04-02 | 2025-09-04 | 2025-09-06
| JD3RZ02-2C16TSE10479 | Testing for HDPE Pipes 450 mm - depth from 3.51 to 4.5 m- B4.33 31 00.12-Z02-2-C-16-TSE | 1 | 2025-04-03 | 2025-04-05 | 2025-09-16 | 2025-09-20
| JD3RZ02-2C16TSE10480 | Backfillingfor HDPE Pipes 450 mm - depth from 3.51 to 4.5 m- B4.33 31 00.12-Z02-2-C-16-TSE | 1 | 2025-04-06 | 2025-04-07
| JD3RZ02-2C16TSE10481 | Excavation Worksfor HDPE Pipes 450 mm - depth from 4.51 to 5.5 m- B4.33 31 00.13-Z02-2-C-16-TSE | 1 | 2025-03-30 | 2025-03-31 | 2025-08-31 | 2025-09-02
| JD3RZ02-2C16TSE10482 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 4.51 to 5.5 m- B4.33 31 00.13-Z02-2-C-16-TSE | 1 | 2025-04-01 | 2025-04-02 | 2025-09-02 | 2025-09-04
| JD3RZ02-2C16TSE10483 | Installing for HDPE Pipes 450 mm - depth from 4.51 to 5.5 m- B4.33 31 00.13-Z02-2-C-16-TSE | 1 | 2025-04-03 | 2025-04-05 | 2025-09-04 | 2025-09-06
| JD3RZ02-2C16TSE10484 | Testing for HDPE Pipes 450 mm - depth from 4.51 to 5.5 m- B4.33 31 00.13-Z02-2-C-16-TSE | 1 | 2025-04-06 | 2025-04-07 | 2025-09-16 | 2025-09-20
| JD3RZ02-2C16TSE10485 | Backfillingfor HDPE Pipes 450 mm - depth from 4.51 to 5.5 m- B4.33 31 00.13-Z02-2-C-16-TSE | 1 | 2025-04-08 | 2025-04-09
| JD3RZ02-2C16TSE10511 | Excavation Worksfor GRP Pipes 800 mm - depth from 0 to 1.5 m- B4.33 05 36.01-Z02-2-C-16-TSE | 1 | 2025-04-01 | 2025-04-02 | 2025-08-20 | 2025-08-21
| JD3RZ02-2C16TSE10512 | Soil Replacement and Bedding Works for GRP Pipes 800 mm - depth from 0 to 1.5 m- B4.33 05 36.01-Z02-2-C-16-TSE | 1 | 2025-04-03 | 2025-04-05 | 2025-08-23 | 2025-08-24
| JD3RZ02-2C16TSE10513 | Installing for GRP Pipes 800 mm - depth from 0 to 1.5 m- B4.33 05 36.01-Z02-2-C-16-TSE | 1 | 2025-04-06 | 2025-04-07 | 2025-08-25 | 2025-08-26
| JD3RZ02-2C16TSE10514 | Testing for GRP Pipes 800 mm - depth from 0 to 1.5 m- B4.33 05 36.01-Z02-2-C-16-TSE | 1 | 2025-04-08 | 2025-04-09
| JD3RZ02-2C16TSE10515 | Backfillingfor GRP Pipes 800 mm - depth from 0 to 1.5 m- B4.33 05 36.01-Z02-2-C-16-TSE | 1 | 2025-04-10 | 2025-04-12
| JD3RZ02-2C16TSE10516 | Excavation Worksfor GRP Pipes 800 mm - depth from 1.51 to 2.5 m- B4.33 05 36.02-Z02-2-C-16-TSE | 1 | 2025-04-03 | 2025-04-05 | 2025-08-23 | 2025-08-24
| JD3RZ02-2C16TSE10517 | Soil Replacement and Bedding Works for GRP Pipes 800 mm - depth from 1.51 to 2.5 m- B4.33 05 36.02-Z02-2-C-16-TSE | 1 | 2025-04-06 | 2025-04-07 | 2025-08-25 | 2025-08-26
| JD3RZ02-2C16TSE10518 | Installing for GRP Pipes 800 mm - depth from 1.51 to 2.5 m- B4.33 05 36.02-Z02-2-C-16-TSE | 1 | 2025-04-08 | 2025-04-09 | 2025-08-27 | 2025-08-28
| JD3RZ02-2C16TSE10519 | Testing for GRP Pipes 800 mm - depth from 1.51 to 2.5 m- B4.33 05 36.02-Z02-2-C-16-TSE | 1 | 2025-04-10 | 2025-04-12 | 2025-08-30
| JD3RZ02-2C16TSE10520 | Backfillingfor GRP Pipes 800 mm - depth from 1.51 to 2.5 m- B4.33 05 36.02-Z02-2-C-16-TSE | 1 | 2025-04-13 | 2025-04-15
| JD3RZ02-2C16TSE10521 | Excavation Worksfor GRP Pipes 800 mm - depth from 2.51 to 3.5 m- B4.33 05 36.03-Z02-2-C-16-TSE | 1 | 2025-04-06 | 2025-04-07 | 2025-08-25 | 2025-08-26
| JD3RZ02-2C16TSE10522 | Soil Replacement and Bedding Works for GRP Pipes 800 mm - depth from 2.51 to 3.5 m- B4.33 05 36.03-Z02-2-C-16-TSE | 1 | 2025-04-08 | 2025-04-09 | 2025-08-27 | 2025-08-28
| JD3RZ02-2C16TSE10523 | Installing for GRP Pipes 800 mm - depth from 2.51 to 3.5 m- B4.33 05 36.03-Z02-2-C-16-TSE | 1 | 2025-04-10 | 2025-04-12 | 2025-08-30 | 2025-08-31
| JD3RZ02-2C16TSE10524 | Testing for GRP Pipes 800 mm - depth from 2.51 to 3.5 m- B4.33 05 36.03-Z02-2-C-16-TSE | 1 | 2025-04-13 | 2025-04-14
| JD3RZ02-2C16TSE10525 | Backfillingfor GRP Pipes 800 mm - depth from 2.51 to 3.5 m- B4.33 05 36.03-Z02-2-C-16-TSE | 1 | 2025-04-15 | 2025-04-16
| JD3RZ02-2C16TSE10526 | Excavation Worksfor GRP Pipes 800 mm - depth from 3.51 to 4.5 m- B4.33 05 36.04-Z02-2-C-16-TSE | 1 | 2025-04-08 | 2025-04-09 | 2025-08-20 | 2025-08-21
| JD3RZ02-2C16TSE10527 | Soil Replacement and Bedding Works for GRP Pipes 800 mm - depth from 3.51 to 4.5 m- B4.33 05 36.04-Z02-2-C-16-TSE | 1 | 2025-04-10 | 2025-04-12 | 2025-08-23 | 2025-08-24
| JD3RZ02-2C16TSE10528 | Installing for GRP Pipes 800 mm - depth from 3.51 to 4.5 m- B4.33 05 36.04-Z02-2-C-16-TSE | 1 | 2025-04-13 | 2025-04-14 | 2025-08-26 | 2025-08-27
| JD3RZ02-2C16TSE10529 | Testing for GRP Pipes 800 mm - depth from 3.51 to 4.5 m- B4.33 05 36.04-Z02-2-C-16-TSE | 1 | 2025-04-15 | 2025-04-16
| JD3RZ02-2C16TSE10530 | Backfillingfor GRP Pipes 800 mm - depth from 3.51 to 4.5 m- B4.33 05 36.04-Z02-2-C-16-TSE | 1 | 2025-04-17 | 2025-04-19
| JD3RZ02-2C16TSE10531 | Excavation Worksfor GRP Pipes 800 mm - depth from 4.51 to 5.5 m- B4.33 05 36.05-Z02-2-C-16-TSE | 1 | 2025-03-27 | 2025-03-29 | 2025-08-16 | 2025-08-17
| JD3RZ02-2C16TSE10532 | Soil Replacement and Bedding Works for GRP Pipes 800 mm - depth from 4.51 to 5.5 m- B4.33 05 36.05-Z02-2-C-16-TSE | 1 | 2025-03-30 | 2025-03-31 | 2025-08-18 | 2025-08-19
| JD3RZ02-2C16TSE10533 | Installing for GRP Pipes 800 mm - depth from 4.51 to 5.5 m- B4.33 05 36.05-Z02-2-C-16-TSE | 1 | 2025-04-01 | 2025-04-02 | 2025-08-20 | 2025-08-21
| JD3RZ02-2C16TSE10534 | Testing for GRP Pipes 800 mm - depth from 4.51 to 5.5 m- B4.33 05 36.05-Z02-2-C-16-TSE | 1 | 2025-04-03 | 2025-04-05
| JD3RZ02-2C16TSE10535 | Backfillingfor GRP Pipes 800 mm - depth from 4.51 to 5.5 m- B4.33 05 36.05-Z02-2-C-16-TSE | 1 | 2025-04-06 | 2025-04-07
| JD3RZ02-2C16TSE10546 | Installationfor gate valves 100 mm - - B4.33 14 19.01-Z02-2-C-16-TSE | 1 | 2025-04-03 | 2025-04-05
| JD3RZ02-2C16TSE10547 | Testing And Commtionningfor gate valves 100 mm - - B4.33 14 19.01-Z02-2-C-16-TSE | 1 | 2025-04-06 | 2025-04-07
| JD3RZ02-2C16TSE10552 | Installationfor butterfly valves 400 mm. - - B4.33 14 19.04-Z02-2-C-16-TSE | 1 | 2025-04-06 | 2025-04-07
| JD3RZ02-2C16TSE10553 | Testing And Commtionningfor butterfly valves 400 mm. - - B4.33 14 19.04-Z02-2-C-16-TSE | 1 | 2025-04-08 | 2025-04-09
| JD3RZ02-2C16TSE10560 | Installationfor Wash-Out valves 150 mm. - on pipes with diameter 450-630 mm- B4.33 14 19.08-Z02-2-C-16-TSE | 1 | 2025-03-29 | 2025-03-30
| JD3RZ02-2C16TSE10561 | Testing And Commtionningfor Wash-Out valves 150 mm. - on pipes with diameter 450-630 mm- B4.33 14 19.08-Z02-2-C-16-TSE | 1 | 2025-03-31 | 2025-04-01
| JD3RZ02-2C16TSE10570 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-Z02-2-C-16-TSE | 1 | 2025-03-30 | 2025-03-31
| JD3RZ02-2C16TSE10571 | Plain Concrete Worksfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-Z02-2-C-16-TSE | 1 | 2025-04-01 | 2025-04-02
| JD3RZ02-2C16TSE10572 | INSTALLATIONfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-Z02-2-C-16-TSE | 1 | 2025-04-03 | 2025-04-05
| JD3RZ02-2C16TSE10573 | Backfilling Worksfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-Z02-2-C-16-TSE | 1 | 2025-04-06 | 2025-04-07
| JD3RZ02-2C16TSE10586 | EXCAVATION and Bedding Worksfor Wash-out Valve Chamber - 450 to 630 MM- B4.33 14 13.07-Z02-2-C-16-TSE | 1 | 2025-04-01 | 2025-04-02
| JD3RZ02-2C16TSE10587 | Plain Concrete Worksfor Wash-out Valve Chamber - 450 to 630 MM- B4.33 14 13.07-Z02-2-C-16-TSE | 1 | 2025-04-03 | 2025-04-05
| JD3RZ02-2C16TSE10588 | INSTALLATIONfor Wash-out Valve Chamber - 450 to 630 MM- B4.33 14 13.07-Z02-2-C-16-TSE | 1 | 2025-04-06 | 2025-04-07
| JD3RZ02-2C16TSE10589 | Backfilling Worksfor Wash-out Valve Chamber - 450 to 630 MM- B4.33 14 13.07-Z02-2-C-16-TSE | 1 | 2025-04-08 | 2025-04-09
| JD3RZ02-2L74RD11421 | Supply, lay and compaction subgrade compacted thicknessfor ROADS thickness 300mm - - B1.31 22 00.01-Z02-2-L-74-RD | 1 | 2024-08-17 | 2024-08-21 | 2025-02-15 | 2025-04-01
| JD3RZ02-2L74RD11422 | Supply, lay and compaction Aggregate base course compacted thicknessfor ROADS thickness 300mm - - B1.32 11 23.01-Z02-2-L | 1 | 2024-10-17 | 2024-10-19 | 2025-02-20 | 2025-03-10
| JD3RZ02-2L74RD11423 | Supply and spreading of Prime coat MC1for ROADS - - B1.32 11 26.01-Z02-2-L-74-RD | 1 | 2025-01-05 | 2025-01-06 | 2025-06-25 | 2025-07-13
| JD3RZ02-2L74RD11423.R | Supply and spreading of Prime coat MC1for ROADS - - B1.32 11 26.01-Z02-2-L-74-RD -Remaining | 1 | 2025-04-19 | 2025-04-20 | 2025-08-20 | 2025-08-21
| JD3RZ02-2L74RD11424 | Supply, lay and compaction Asphaltic base coursefor ROADS - - B1.32 11 26.01-Z02-2-L-74-RD | 1 | 2025-01-07 | 2025-01-08 | 2025-06-28 | 2025-07-15
| JD3RZ02-2L74RD11424.R | Supply, lay and compaction Asphaltic base coursefor ROADS - - B1.32 11 26.01-Z02-2-L-74-RD -Remaining | 1 | 2025-04-21 | 2025-04-22 | 2025-08-23 | 2025-08-24
| JD3RZ02-2L74RD11425 | Supply and spreading of Tack coat RC2for ROADS - - B1.32 12 16.01-Z02-2-L-74-RD | 1 | 2025-04-23 | 2025-04-24 | 2025-09-20 | 2025-09-25
| JD3RZ02-2L74RD11426 | Supply, lay and compaction Asphaltic wearing coursefor ROADS - - B1.32 12 16.01-Z02-2-L-74-RD | 1 | 2025-04-26 | 2025-04-27 | 2025-09-22 | 2025-09-26
| JD3RZ02-2L74RD11427 | Supply and installation Precast Concrete Kerb, Type K1-Dfor ROADS - - B1.32 14 13.01-Z02-2-L-74-RD | 1 | 2025-04-28 | 2025-05-12 | 2025-08-16 | 2025-09-20
| JD3RZ02-2L74RD11429 | Supply and installation Depressed curbs Type K2for ROADS - - B1.32 14 13.03-Z02-2-L-74-RD | 1 | 2025-05-13 | 2025-05-14 | 2025-08-16 | 2025-09-20
| JD3RZ02-2L74RD11431 | Supply and installation Retroreflective Thermoplastic White Traffic linesfor ROADS - - B1.32 17 23.01-Z02-2-L-74-RD | 1 | 2025-05-15 | 2025-05-17
| JD3RZ02-2L74RD11432 | Supply and installation Retroreflective Thermoplastic Yellow, Traffic linesfor ROADS - - B1.32 17 23.02-Z02-2-L-74-RD | 1 | 2025-05-18 | 2025-05-19
| JD3RZ02-2L74RD11434 | Supply and install (Right/left ) Arrowfor ROADS - - B1.32 17 23.04-Z02-2-L-74-RD | 1 | 2025-05-20 | 2025-05-21
| JD3RZ02-2L74RD11436 | Supply and install Straight-Right Arrowfor ROADS - - B1.32 17 23.06-Z02-2-L-74-RD | 1 | 2025-05-22 | 2025-05-24
| JD3RZ02-2L74RD11437 | Supply and install Straight-Left Arrowfor ROADS - - B1.32 17 23.07-Z02-2-L-74-RD | 1 | 2025-05-25 | 2025-05-26
| JD3RZ02-2L74RD11438 | Supply and installation Traffic signs with Single postfor ROADS - - B1.10 14 53.01-Z02-2-L-74-RD | 1 | 2025-05-15 | 2025-05-17
| JD3RZ02-2L74RD11439 | Supply and installation Traffic signs with Double postfor ROADS - - B1.10 14 53.02-Z02-2-L-74-RD | 1 | 2025-05-18 | 2025-05-19
| JD3RZ02-2L74SL11357 | Excavation Worksfor Copper Cables 4Cx25 mm² - - B2.26 05 19.04-Z02-2-L-74-SL | 1 | 2025-04-15 | 2025-04-17 | 2025-08-06 | 2025-08-11
| JD3RZ02-2L74SL11358 | Installationfor Copper Cables 4Cx25 mm² - - B2.26 05 19.04-Z02-2-L-74-SL | 1 | 2025-04-19 | 2025-04-21 | 2025-08-20 | 2025-08-27
| JD3RZ02-2L74SL11359 | Backfilling, Warning Tabe Worksfor Copper Cables 4Cx25 mm² - - B2.26 05 19.04-Z02-2-L-74-SL | 1 | 2025-04-22 | 2025-04-24 | 2025-08-28 | 2025-09-02
| JD3RZ02-2L74SL11360 | Testing and Commitioning for Copper Cables 4Cx25 mm² - - B2.26 05 19.04-Z02-2-L-74-SL | 1 | 2025-04-29 | 2025-05-01
| JD3RZ02-2L74SL11371 | INSTALLINGfor insulated copper conductor 16 mm² - - B2.26 05 19.08-Z02-2-L-74-SL | 1 | 2025-04-22 | 2025-04-24
| JD3RZ02-2L74SL11372 | TESTING AND COMMITIONINGfor insulated copper conductor 16 mm² - - B2.26 05 19.08-Z02-2-L-74-SL | 1 | 2025-04-26 | 2025-04-28
| JD3RZ02-2L74SS10727 | Trench excavation for GRP Pipe Line 200 mm - depth from 0.00 to 1.50- B5.33 31 00.03-Z02-2-L-74-SS | 1 | 2024-12-15 | 2024-12-16 | 2025-01-05 | 2025-01-22
| JD3RZ02-2L74SS10728 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - depth from 0.00 to 1.50- B5.33 31 00.03-Z02-2-L-74-SS | 1 | 2024-12-17 | 2024-12-18 | 2025-01-13 | 2025-01-30
| JD3RZ02-2L74SS10729 | Installing for GRP Pipe Line 200 mm - depth from 0.00 to 1.50- B5.33 31 00.03-Z02-2-L-74-SS | 1 | 2024-12-19 | 2024-12-21 | 2025-01-14 | 2025-02-01
| JD3RZ02-2L74SS10730 | Primary Test for GRP Pipe Line 200 mm - depth from 0.00 to 1.50- B5.33 31 00.03-Z02-2-L-74-SS | 1 | 2024-12-22 | 2024-12-23 | 2025-01-18 | 2025-02-04
| JD3RZ02-2L74SS10731 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - depth from 0.00 to 1.50- B5.33 31 00.03-Z02-2-L-74-SS | 1 | 2024-12-24 | 2024-12-25 | 2025-01-28 | 2025-02-15
| JD3RZ02-2L74SS10732 | Trench excavation for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-2-L-74-SS | 1 | 2024-12-15 | 2024-12-17 | 2025-01-13 | 2025-01-30
| JD3RZ02-2L74SS10733 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-2-L-74-SS | 1 | 2024-12-18 | 2024-12-21 | 2025-01-15 | 2025-02-11
| JD3RZ02-2L74SS10734 | Installing for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-2-L-74-SS | 1 | 2024-12-22 | 2024-12-24 | 2025-01-21 | 2025-02-26
| JD3RZ02-2L74SS10735 | Primary Test for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-2-L-74-SS | 1 | 2024-12-25 | 2024-12-28 | 2025-01-28 | 2025-03-05
| JD3RZ02-2L74SS10736 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-2-L-74-SS | 1 | 2024-12-29 | 2025-01-01 | 2025-02-05 | 2025-03-13
| JD3RZ02-2L74SS10737 | Trench excavation for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-2-L-74-SS | 1 | 2024-12-15 | 2024-12-16 | 2025-01-16 | 2025-02-03
| JD3RZ02-2L74SS10738 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-2-L-74-SS | 1 | 2024-12-17 | 2024-12-18 | 2025-01-18 | 2025-02-04
| JD3RZ02-2L74SS10739 | Installing for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-2-L-74-SS | 1 | 2024-12-19 | 2024-12-22 | 2025-01-22 | 2025-02-18
| JD3RZ02-2L74SS10740 | Primary Test for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-2-L-74-SS | 1 | 2024-12-23 | 2024-12-24 | 2025-01-30 | 2025-02-26
| JD3RZ02-2L74SS10741 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-2-L-74-SS | 1 | 2024-12-25 | 2024-12-28 | 2025-02-05 | 2025-03-13
| JD3RZ02-2L74SS10762 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 0.00 to 1.50- B5.33 05 13.01-Z02-2-L-74-SS | 1 | 2024-12-15 | 2024-12-16 | 2025-01-22 | 2025-02-09
| JD3RZ02-2L74SS10763 | Installation of Base Works for Manholes 1200 mm - Depth from 0.00 to 1.50- B5.33 05 13.01-Z02-2-L-74-SS | 1 | 2024-12-17 | 2024-12-18 | 2025-01-25 | 2025-02-11
| JD3RZ02-2L74SS10764 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 0.00 to 1.50- B5.33 05 13.01-Z02-2-L | 1 | 2024-12-19 | 2024-12-21 | 2025-04-30 | 2025-05-18
| JD3RZ02-2L74SS10765 | Backfilling Works for Manholes 1200 mm - Depth from 0.00 to 1.50- B5.33 05 13.01-Z02-2-L-74-SS | 1 | 2024-12-22 | 2024-12-23 | 2025-05-05 | 2025-05-22
| JD3RZ02-2L74SS10766 | Finishing, Benching Works for Manholes 1200 mm - Depth from 0.00 to 1.50- B5.33 05 13.01-Z02-2-L-74-SS | 1 | 2024-12-24 | 2024-12-25 | 2025-06-10 | 2025-06-28
| JD3RZ02-2L74SS10774 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z02-2-L-74-SS | 1 | 2024-12-26 | 2024-12-28 | 2025-08-02 | 2025-08-03
| JD3RZ02-2L74SS10775 | Installation of Base Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z02-2-L-74-SS | 1 | 2024-12-29 | 2024-12-30 | 2025-08-04 | 2025-08-05
| JD3RZ02-2L74SS10776 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z02-2-L | 1 | 2024-12-31 | 2025-01-01 | 2025-08-06 | 2025-08-07
| JD3RZ02-2L74SS10777 | Backfilling Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z02-2-L-74-SS | 1 | 2025-01-02 | 2025-01-04
| JD3RZ02-2L74SS10778 | Finishing, Benching Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z02-2-L-74-SS | 1 | 2025-01-11 | 2025-01-12 | 2025-08-14 | 2025-08-16
| JD3RZ02-2L74SS10779 | Excavation and PC Blinding Works for Backdrop Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.04-Z02-2-L-74-SS | 1 | 2024-12-15 | 2024-12-16 | 2025-04-10 | 2025-04-28
| JD3RZ02-2L74SS10780 | Installation of Base Works for Backdrop Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.04-Z02-2-L-74-SS | 1 | 2024-12-17 | 2024-12-18 | 2025-04-15 | 2025-05-03
| JD3RZ02-2L74SS10781 | Installation of Manhole Ring and Cover Slab Works for Backdrop Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.0 | 1 | 2024-12-19 | 2024-12-21 | 2025-04-20 | 2025-05-07
| JD3RZ02-2L74SS10782 | Installation of fitting Works for Backdrop Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.04-Z02-2-L-74-SS | 1 | 2024-12-22 | 2024-12-23 | 2025-04-22 | 2025-05-10
| JD3RZ02-2L74SS10783 | Concrete Encasement Works for Backdrop Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.04-Z02-2-L-74-SS | 1 | 2024-12-24 | 2024-12-25 | 2025-04-30 | 2025-05-18
| JD3RZ02-2L74SS10784 | Backfilling Works for Backdrop Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.04-Z02-2-L-74-SS | 1 | 2024-12-26 | 2024-12-28 | 2025-05-05 | 2025-05-22
| JD3RZ02-2L74SS10785 | Finishing, Benching Works for Backdrop Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.04-Z02-2-L-74-SS | 1 | 2024-12-29 | 2024-12-30 | 2025-06-10 | 2025-06-28
| JD3RZ02-2L74SS10786 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-2-L-74-SS | 1 | 2024-12-15 | 2024-12-16 | 2025-04-20 | 2025-05-07
| JD3RZ02-2L74SS10787 | Installation of Base Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-2-L-74-SS | 1 | 2024-12-17 | 2024-12-18 | 2025-04-22 | 2025-05-10
| JD3RZ02-2L74SS10788 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-2-L | 1 | 2024-12-19 | 2024-12-21 | 2025-04-30 | 2025-05-18
| JD3RZ02-2L74SS10789 | Backfilling Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-2-L-74-SS | 1 | 2024-12-22 | 2024-12-23 | 2025-05-05 | 2025-05-22
| JD3RZ02-2L74SS10790 | Finishing, Benching Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-2-L-74-SS | 1 | 2024-12-24 | 2024-12-25 | 2025-06-10 | 2025-06-28
| JD3RZ02-2L74SS10791 | Excavation and PC Blinding Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.06-Z02-2-L-74-SS | 1 | 2024-12-15 | 2024-12-16 | 2025-04-10 | 2025-04-28
| JD3RZ02-2L74SS10792 | Installation of Base Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.06-Z02-2-L-74-SS | 1 | 2024-12-17 | 2024-12-18 | 2025-04-15 | 2025-05-03
| JD3RZ02-2L74SS10793 | Installation of Manhole Ring and Cover Slab Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.0 | 1 | 2024-12-19 | 2024-12-21 | 2025-04-20 | 2025-05-07
| JD3RZ02-2L74SS10794 | Installation of fitting Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.06-Z02-2-L-74-SS | 1 | 2024-12-22 | 2024-12-23 | 2025-04-22 | 2025-05-10
| JD3RZ02-2L74SS10795 | Concrete Encasement Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.06-Z02-2-L-74-SS | 1 | 2024-12-24 | 2024-12-25 | 2025-04-30 | 2025-05-18
| JD3RZ02-2L74SS10796 | Backfilling Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.06-Z02-2-L-74-SS | 1 | 2024-12-26 | 2024-12-28 | 2025-05-05 | 2025-05-22
| JD3RZ02-2L74SS10797 | Finishing, Benching Works for Backdrop Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.06-Z02-2-L-74-SS | 1 | 2024-12-29 | 2024-12-30 | 2025-06-10 | 2025-06-28
| JD3RZ02-2L74SS521401 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2024-12-29 | 2024-12-30 | 2025-08-04 | 2025-08-05
| JD3RZ02-2L74SS521411 | Installation of Base Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2024-12-31 | 2025-01-01 | 2025-08-06 | 2025-08-07
| JD3RZ02-2L74SS521421 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03 | 1 | 2025-01-02 | 2025-01-04 | 2025-08-09 | 2025-08-10
| JD3RZ02-2L74SS521431 | Backfilling Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2025-01-05 | 2025-01-06
| JD3RZ02-2L74SS521441 | Finishing, Benching Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2025-01-11 | 2025-01-12 | 2025-08-14 | 2025-08-16
| JD3RZ02-2L74ST10858 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-2-L-74-ST | 1 | 2024-12-15 | 2024-12-16 | 2025-03-05 | 2025-04-01
| JD3RZ02-2L74ST10858.R | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-2-L-74-ST -Remaining | 1 | 2024-12-31 | 2025-01-01 | 2025-08-06 | 2025-08-07
| JD3RZ02-2L74ST10859 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-2-L-74-ST | 1 | 2024-12-17 | 2024-12-19 | 2025-03-12 | 2025-04-17
| JD3RZ02-2L74ST10859.R | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-2-L-74-ST - | 1 | 2025-01-02 | 2025-01-04 | 2025-08-09 | 2025-08-10
| JD3RZ02-2L74ST10860 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-2-L-74-ST | 1 | 2024-12-21 | 2024-12-23 | 2025-03-15 | 2025-04-20
| JD3RZ02-2L74ST10860.R | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-2-L-74-ST -Remaining | 1 | 2025-01-05 | 2025-01-06 | 2025-08-11 | 2025-08-12
| JD3RZ02-2L74ST10861 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-2-L-74-ST | 1 | 2024-12-24 | 2024-12-26 | 2025-05-15 | 2025-06-21
| JD3RZ02-2L74ST10861.R | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-2-L-74-ST -Remaining | 1 | 2025-01-07 | 2025-01-08 | 2025-08-13 | 2025-08-14
| JD3RZ02-2L74ST10862 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-2-L-74-ST | 1 | 2024-12-28 | 2024-12-31 | 2025-06-15 | 2025-07-30
| JD3RZ02-2L74ST10862.R | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z02-2-L-74-ST -Remaining | 1 | 2025-01-09 | 2025-01-11 | 2025-08-16 | 2025-08-17
| JD3RZ02-2L74ST10863 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-2-L-74-ST | 1 | 2024-12-15 | 2024-12-16 | 2025-01-14 | 2025-02-01
| JD3RZ02-2L74ST10864 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-2-L-74-ST | 1 | 2024-12-17 | 2024-12-18 | 2025-01-15 | 2025-02-02
| JD3RZ02-2L74ST10865 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-2-L-74-ST | 1 | 2024-12-19 | 2024-12-21 | 2025-01-16 | 2025-02-12
| JD3RZ02-2L74ST10866 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-2-L-74-ST | 1 | 2024-12-22 | 2024-12-23 | 2025-01-22 | 2025-02-18
| JD3RZ02-2L74ST10867 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-2-L-74-ST | 1 | 2024-12-24 | 2024-12-26 | 2025-02-05 | 2025-03-13
| JD3RZ02-2L74ST10868 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-2-L-74-ST | 1 | 2024-12-15 | 2024-12-16 | 2025-01-14 | 2025-02-01
| JD3RZ02-2L74ST10869 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-2-L-74-ST | 1 | 2024-12-17 | 2024-12-18 | 2025-01-15 | 2025-02-02
| JD3RZ02-2L74ST10870 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-2-L-74-ST | 1 | 2024-12-19 | 2024-12-21 | 2025-01-16 | 2025-02-03
| JD3RZ02-2L74ST10871 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-2-L-74-ST | 1 | 2024-12-22 | 2024-12-23 | 2025-01-22 | 2025-02-09
| JD3RZ02-2L74ST10872 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z02-2-L-74-ST | 1 | 2024-12-24 | 2024-12-25 | 2025-02-05 | 2025-02-23
| JD3RZ02-2L74ST10878 | Excavation Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z02-2-L-74-ST | 1 | 2024-12-15 | 2024-12-16 | 2025-01-14 | 2025-02-01
| JD3RZ02-2L74ST10879 | Soil Replacement and Bedding Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z02-2-L-74-ST | 1 | 2024-12-17 | 2024-12-18 | 2025-01-15 | 2025-02-02
| JD3RZ02-2L74ST10880 | Installing for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z02-2-L-74-ST | 1 | 2024-12-19 | 2024-12-21 | 2025-01-16 | 2025-02-03
| JD3RZ02-2L74ST10881 | Primary Test for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z02-2-L-74-ST | 1 | 2024-12-22 | 2024-12-23 | 2025-01-22 | 2025-02-09
| JD3RZ02-2L74ST10882 | Backfilling Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z02-2-L-74-ST | 1 | 2024-12-24 | 2024-12-25 | 2025-02-05 | 2025-02-23
| JD3RZ02-2L74ST10888 | Excavation Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-2-L-74-ST | 1 | 2024-12-15 | 2024-12-18 | 2025-01-08 | 2025-01-26
| JD3RZ02-2L74ST10889 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-2-L-74-ST | 1 | 2024-12-19 | 2024-12-23 | 2025-01-09 | 2025-01-27
| JD3RZ02-2L74ST10890 | Installing for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-2-L-74-ST | 1 | 2024-12-24 | 2024-12-29 | 2025-01-15 | 2025-02-11
| JD3RZ02-2L74ST10891 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-2-L-74-ST | 1 | 2024-12-30 | 2025-01-02 | 2025-01-16 | 2025-02-12
| JD3RZ02-2L74ST10892 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-2-L-74-ST | 1 | 2025-01-04 | 2025-01-09 | 2025-02-05 | 2025-03-04
| JD3RZ02-2L74ST10898 | Excavation Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-2-L-74-ST | 1 | 2024-12-15 | 2024-12-16 | 2025-01-21 | 2025-02-08
| JD3RZ02-2L74ST10899 | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-2-L-74-ST | 1 | 2024-12-17 | 2024-12-18 | 2025-01-22 | 2025-02-09
| JD3RZ02-2L74ST10900 | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-2-L-74-ST | 1 | 2024-12-19 | 2024-12-21 | 2025-02-05 | 2025-03-04
| JD3RZ02-2L74ST10901 | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-2-L-74-ST | 1 | 2024-12-22 | 2024-12-23 | 2025-02-11 | 2025-03-10
| JD3RZ02-2L74ST10902 | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z02-2-L-74-ST | 1 | 2024-12-24 | 2024-12-25 | 2025-02-08 | 2025-03-06
| JD3RZ02-2L74ST10923 | Excavation Works for GRP Pipe Line 900 mm - depth from 2.51 to 3.50 m- B6.33 42 11.13-Z02-2-L-74-ST | 1 | 2024-12-15 | 2024-12-16 | 2025-01-14 | 2025-02-01
| JD3RZ02-2L74ST10924 | Soil Replacement and Bedding Works for GRP Pipe Line 900 mm - depth from 2.51 to 3.50 m- B6.33 42 11.13-Z02-2-L-74-ST | 1 | 2024-12-17 | 2024-12-18 | 2025-01-15 | 2025-02-02
| JD3RZ02-2L74ST10925 | Installing for GRP Pipe Line 900 mm - depth from 2.51 to 3.50 m- B6.33 42 11.13-Z02-2-L-74-ST | 1 | 2024-12-19 | 2024-12-21 | 2025-01-16 | 2025-02-03
| JD3RZ02-2L74ST10926 | Primary Test for GRP Pipe Line 900 mm - depth from 2.51 to 3.50 m- B6.33 42 11.13-Z02-2-L-74-ST | 1 | 2024-12-22 | 2024-12-23 | 2025-01-22 | 2025-02-09
| JD3RZ02-2L74ST10927 | Backfilling Works for GRP Pipe Line 900 mm - depth from 2.51 to 3.50 m- B6.33 42 11.13-Z02-2-L-74-ST | 1 | 2024-12-24 | 2024-12-25 | 2025-02-08 | 2025-02-25
| JD3RZ02-2L74ST11041 | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-2-L-74-ST | 1 | 2024-12-15 | 2024-12-16 | 2025-01-22 | 2025-02-09
| JD3RZ02-2L74ST11042 | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-2-L-74-ST | 1 | 2024-12-17 | 2024-12-21 | 2025-02-25 | 2025-04-02
| JD3RZ02-2L74ST11043 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-2-L-74-ST | 1 | 2024-12-22 | 2024-12-25 | 2025-05-10 | 2025-06-15
| JD3RZ02-2L74ST11044 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-2-L-74-ST | 1 | 2024-12-26 | 2024-12-28 | 2025-06-02 | 2025-06-19
| JD3RZ02-2L74ST11045 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-2-L-74-ST | 1 | 2025-01-09 | 2025-01-11
| JD3RZ02-2L74ST11056 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-2-L-74-ST | 1 | 2024-12-15 | 2024-12-16 | 2025-01-22 | 2025-02-09
| JD3RZ02-2L74ST11057 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-2-L-74-ST | 1 | 2024-12-17 | 2024-12-18 | 2025-02-25 | 2025-03-15
| JD3RZ02-2L74ST11058 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-2-L-74-ST | 1 | 2024-12-19 | 2024-12-21 | 2025-05-10 | 2025-05-27
| JD3RZ02-2L74ST11059 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-2-L-74-ST | 1 | 2024-12-22 | 2024-12-23 | 2025-06-02 | 2025-06-19
| JD3RZ02-2L74ST11060 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-2-L-74-ST | 1 | 2025-01-12 | 2025-01-13
| JD3RZ02-2L74ST11076 | EXCAVATION Works for Catchbasine single - - B6.33 05 39.09-Z02-2-L-74-ST | 1 | 2024-12-17 | 2024-12-19 | 2025-03-22 | 2025-04-17
| JD3RZ02-2L74ST11076.R | EXCAVATION Works for Catchbasine single - - B6.33 05 39.09-Z02-2-L-74-ST -Remaining | 1 | 2025-01-02 | 2025-01-04 | 2025-08-09 | 2025-08-10
| JD3RZ02-2L74ST11077 | Catchbasine Installation Works For Catchbasine single - - B6.33 05 39.09-Z02-2-L-74-ST | 1 | 2024-12-21 | 2024-12-24 | 2025-04-15 | 2025-05-21
| JD3RZ02-2L74ST11077.R | Catchbasine Installation Works For Catchbasine single - - B6.33 05 39.09-Z02-2-L-74-ST -Remaining | 1 | 2025-01-05 | 2025-01-06 | 2025-08-11 | 2025-08-12
| JD3RZ02-2L74ST11078 | FINISHING Works For Catchbasine single - - B6.33 05 39.09-Z02-2-L-74-ST | 1 | 2025-01-07 | 2025-01-11
| JD3RZ02-2L74ST11079 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - - B6.33 05 39.09-Z02-2-L-74-ST | 1 | 2025-01-12 | 2025-01-14
| JD3RZ02-2L74ST11080 | EXCAVATION Works for Catchbasine double - - B6.33 05 39.10-Z02-2-L-74-ST | 1 | 2024-12-21 | 2024-12-22 | 2025-05-10 | 2025-05-27
| JD3RZ02-2L74ST11080.R | EXCAVATION Works for Catchbasine double - - B6.33 05 39.10-Z02-2-L-74-ST -Remaining | 1 | 2025-01-05 | 2025-01-06 | 2025-08-11 | 2025-08-12
| JD3RZ02-2L74ST11081 | Catchbasine Installation Works For Catchbasine double - - B6.33 05 39.10-Z02-2-L-74-ST | 1 | 2024-12-23 | 2024-12-25 | 2025-05-15 | 2025-06-11
| JD3RZ02-2L74ST11081.R | Catchbasine Installation Works For Catchbasine double - - B6.33 05 39.10-Z02-2-L-74-ST -Remaining | 1 | 2025-01-07 | 2025-01-08 | 2025-08-13 | 2025-08-14
| JD3RZ02-2L74ST11082 | FINISHING Works For Catchbasine double - - B6.33 05 39.10-Z02-2-L-74-ST | 1 | 2025-01-09 | 2025-01-12
| JD3RZ02-2L74ST11083 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - - B6.33 05 39.10-Z02-2-L-74-ST | 1 | 2025-01-13 | 2025-01-14
| JD3RZ02-2L74ST524364 | Concrete encasement for pipes- NNB6.33 42 11.25-Z02-2-L-74-ST | 1 | 2025-01-07 | 2025-01-09
| JD3RZ02-2L74ST524369 | Excavation for cutting material, in all type of soil- NNB6.33 42 11.25-Z02-2-L-74-ST | 1 | 2024-12-31 | 2025-01-08
| JD3RZ02-2L74TC11414 | Excavation Worksfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z02-2-L-74-TC | 1 | 2025-05-03 | 2025-05-04 | 2025-08-10
| JD3RZ02-2L74TC11415 | Installationfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z02-2-L-74-TC | 1 | 2025-05-05 | 2025-05-10 | 2025-08-16
| JD3RZ02-2L74TC11416 | Pouring Concrete Coverfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z02-2-L-74-TC | 1 | 2025-05-11 | 2025-05-15 | 2025-08-20
| JD3RZ02-2L74TC11417 | Backfilling Worksfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z02-2-L-74-TC | 1 | 2025-05-17 | 2025-05-18
| JD3RZ02-2L74TC11418 | Excavation and Bedding Worksfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z02-2-L-74-TC | 1 | 2025-05-05 | 2025-05-07
| JD3RZ02-2L74TC11419 | Installationfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z02-2-L-74-TC | 1 | 2025-05-08 | 2025-05-11
| JD3RZ02-2L74TC11420 | Backfilling Worksfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z02-2-L-74-TC | 1 | 2025-05-12 | 2025-05-14
| JD3RZ02-2L74TSE11134 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-2-L-74-TSE | 1 | 2024-12-23 | 2024-12-24 | 2025-05-01 | 2025-05-19
| JD3RZ02-2L74TSE11134.R | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-2-L-74-TSE -Remaining | 1 | 2025-01-09 | 2025-01-11 | 2025-08-16 | 2025-08-17
| JD3RZ02-2L74TSE11135 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-2-L-74-TSE | 1 | 2024-12-25 | 2024-12-26 | 2025-05-10 | 2025-05-27
| JD3RZ02-2L74TSE11135.R | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-2-L-74-TSE -Rem | 1 | 2025-01-12 | 2025-01-13 | 2025-08-18 | 2025-08-19
| JD3RZ02-2L74TSE11136 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-2-L-74-TSE | 1 | 2024-12-28 | 2024-12-29 | 2025-05-17 | 2025-06-22
| JD3RZ02-2L74TSE11136.R | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-2-L-74-TSE -Remaining | 1 | 2025-01-14 | 2025-01-15 | 2025-08-20 | 2025-08-21
| JD3RZ02-2L74TSE11137 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-2-L-74-TSE | 1 | 2024-12-30 | 2024-12-31 | 2025-06-30 | 2025-07-31
| JD3RZ02-2L74TSE11137.R | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-2-L-74-TSE -Remaining | 1 | 2025-01-16 | 2025-01-18 | 2025-08-23 | 2025-08-24
| JD3RZ02-2L74TSE11138 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-2-L-74-TSE | 1 | 2025-01-01 | 2025-01-02 | 2025-05-25 | 2025-06-11
| JD3RZ02-2L74TSE11138.R | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-2-L-74-TSE -Remaining | 1 | 2025-01-19 | 2025-01-20 | 2025-08-25 | 2025-08-26
| JD3RZ02-2L74TSE11174 | Excavation Worksfor HDPE Pipes 450 mm - depth from 0 to 1.5 m- B4.33 31 00.09-Z02-2-L-74-TSE | 1 | 2024-11-13 | 2024-11-14 | 2025-05-01 | 2025-05-19
| JD3RZ02-2L74TSE11175 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 0 to 1.5 m- B4.33 31 00.09-Z02-2-L-74-TSE | 1 | 2024-11-16 | 2024-11-18 | 2025-05-10 | 2025-06-05
| JD3RZ02-2L74TSE11176 | Installing for HDPE Pipes 450 mm - depth from 0 to 1.5 m- B4.33 31 00.09-Z02-2-L-74-TSE | 1 | 2024-11-19 | 2024-11-23 | 2025-05-17 | 2025-07-31
| JD3RZ02-2L74TSE11177 | Testing for HDPE Pipes 450 mm - depth from 0 to 1.5 m- B4.33 31 00.09-Z02-2-L-74-TSE | 1 | 2024-11-24 | 2024-11-26 | 2025-06-30 | 2025-07-31
| JD3RZ02-2L74TSE11178 | Backfillingfor HDPE Pipes 450 mm - depth from 0 to 1.5 m- B4.33 31 00.09-Z02-2-L-74-TSE | 1 | 2024-11-27 | 2024-11-30 | 2025-05-25 | 2025-06-21
| JD3RZ02-2L74TSE11179 | Excavation Worksfor HDPE Pipes 450 mm - depth from 1.51 to 2.5 m- B4.33 31 00.10-Z02-2-L-74-TSE | 1 | 2024-11-13 | 2024-11-14 | 2025-05-01 | 2025-05-19
| JD3RZ02-2L74TSE11180 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m- B4.33 31 00.10-Z02-2-L-74-TSE | 1 | 2024-11-16 | 2024-11-17 | 2025-05-10 | 2025-05-27
| JD3RZ02-2L74TSE11181 | Installing for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m- B4.33 31 00.10-Z02-2-L-74-TSE | 1 | 2024-11-18 | 2024-11-19 | 2025-05-17 | 2025-06-22
| JD3RZ02-2L74TSE11182 | Testing for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m- B4.33 31 00.10-Z02-2-L-74-TSE | 1 | 2024-11-20 | 2024-11-21 | 2025-06-30 | 2025-07-31
| JD3RZ02-2L74TSE11183 | Backfillingfor HDPE Pipes 450 mm - depth from 1.51 to 2.5 m- B4.33 31 00.10-Z02-2-L-74-TSE | 1 | 2024-11-23 | 2024-11-24 | 2025-05-25 | 2025-06-11
| JD3RZ02-2L74TSE11184 | Excavation Worksfor HDPE Pipes 450 mm - depth from 2.51 to 3.5 m- B4.33 31 00.11-Z02-2-L-74-TSE | 1 | 2024-11-13 | 2024-11-14 | 2025-01-07 | 2025-01-25
| JD3RZ02-2L74TSE11185 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 2.51 to 3.5 m- B4.33 31 00.11-Z02-2-L-74-TSE | 1 | 2024-12-25 | 2024-12-26 | 2025-05-17 | 2025-06-03
| JD3RZ02-2L74TSE11186 | Installing for HDPE Pipes 450 mm - depth from 2.51 to 3.5 m- B4.33 31 00.11-Z02-2-L-74-TSE | 1 | 2024-12-25 | 2024-12-26 | 2025-05-17 | 2025-06-12
| JD3RZ02-2L74TSE11187 | Testing for HDPE Pipes 450 mm - depth from 2.51 to 3.5 m- B4.33 31 00.11-Z02-2-L-74-TSE | 1 | 2024-12-28 | 2024-12-29 | 2025-06-30 | 2025-07-31
| JD3RZ02-2L74TSE11188 | Backfillingfor HDPE Pipes 450 mm - depth from 2.51 to 3.5 m- B4.33 31 00.11-Z02-2-L-74-TSE | 1 | 2024-12-30 | 2024-12-31 | 2025-05-25 | 2025-06-11
| JD3RZ02-2L74TSE11219 | Excavation Worksfor HDPE Pipes 630 mm - depth from 3.51 to 4.5 m- B4.33 31 00.18-Z02-2-L-74-TSE | 1 | 2024-11-13 | 2024-11-14 | 2025-05-01 | 2025-05-19
| JD3RZ02-2L74TSE11220 | Soil Replacement and Bedding Works for HDPE Pipes 630 mm - depth from 3.51 to 4.5 m- B4.33 31 00.18-Z02-2-L-74-TSE | 1 | 2024-11-16 | 2024-11-17 | 2025-05-10 | 2025-05-27
| JD3RZ02-2L74TSE11221 | Installing for HDPE Pipes 630 mm - depth from 3.51 to 4.5 m- B4.33 31 00.18-Z02-2-L-74-TSE | 1 | 2024-11-18 | 2024-11-19 | 2025-05-17 | 2025-06-03
| JD3RZ02-2L74TSE11222 | Testing for HDPE Pipes 630 mm - depth from 3.51 to 4.5 m- B4.33 31 00.18-Z02-2-L-74-TSE | 1 | 2024-11-20 | 2024-11-21 | 2025-06-30 | 2025-07-17
| JD3RZ02-2L74TSE11223 | Backfillingfor HDPE Pipes 630 mm - depth from 3.51 to 4.5 m- B4.33 31 00.18-Z02-2-L-74-TSE | 1 | 2024-11-23 | 2024-11-24 | 2025-05-25 | 2025-06-11
| JD3RZ02-2L74TSE11259 | Installationfor gate valves 100 mm - - B4.33 14 19.01-Z02-2-L-74-TSE | 1 | 2024-12-28 | 2024-12-29 | 2025-06-15 | 2025-07-21
| JD3RZ02-2L74TSE11259.R | Installationfor gate valves 100 mm - - B4.33 14 19.01-Z02-2-L-74-TSE -Remaining | 1 | 2025-01-14 | 2025-01-15
| JD3RZ02-2L74TSE11260 | Testing And Commtionningfor gate valves 100 mm - - B4.33 14 19.01-Z02-2-L-74-TSE | 1 | 2024-12-30 | 2024-12-31 | 2025-06-25 | 2025-07-31
| JD3RZ02-2L74TSE11260.R | Testing And Commtionningfor gate valves 100 mm - - B4.33 14 19.01-Z02-2-L-74-TSE -Remaining | 1 | 2025-01-16 | 2025-01-18
| JD3RZ02-2L74TSE11265 | Installationfor butterfly valves 400 mm. - - B4.33 14 19.04-Z02-2-L-74-TSE | 1 | 2025-02-05 | 2025-02-06
| JD3RZ02-2L74TSE11266 | Testing And Commtionningfor butterfly valves 400 mm. - - B4.33 14 19.04-Z02-2-L-74-TSE | 1 | 2025-02-08 | 2025-02-09
| JD3RZ02-2L74TSE11267 | Installationfor butterfly valves 600 mm. - - B4.33 14 19.05-Z02-2-L-74-TSE | 1 | 2025-02-05 | 2025-02-06
| JD3RZ02-2L74TSE11268 | Testing And Commtionningfor butterfly valves 600 mm. - - B4.33 14 19.05-Z02-2-L-74-TSE | 1 | 2025-02-08 | 2025-02-09
| JD3RZ02-2L74TSE11283 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-Z02-2-L-74-TSE | 1 | 2025-01-09 | 2025-01-11
| JD3RZ02-2L74TSE11284 | Plain Concrete Worksfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-Z02-2-L-74-TSE | 1 | 2025-01-12 | 2025-01-13
| JD3RZ02-2L74TSE11285 | INSTALLATIONfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-Z02-2-L-74-TSE | 1 | 2025-01-14 | 2025-01-15
| JD3RZ02-2L74TSE11286 | Backfilling Worksfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-Z02-2-L-74-TSE | 1 | 2025-01-16 | 2025-01-18
| JD3RZ02-2L74TSE11287 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 500 to 630 MM- B4.33 14 13.02-Z02-2-L-74-TSE | 1 | 2025-01-12 | 2025-01-13
| JD3RZ02-2L74TSE11288 | Plain Concrete Worksfor R.C Valve Chamber - 500 to 630 MM- B4.33 14 13.02-Z02-2-L-74-TSE | 1 | 2025-01-14 | 2025-01-15
| JD3RZ02-2L74TSE11289 | INSTALLATIONfor R.C Valve Chamber - 500 to 630 MM- B4.33 14 13.02-Z02-2-L-74-TSE | 1 | 2025-01-16 | 2025-01-18
| JD3RZ02-2L74TSE11290 | Backfilling Worksfor R.C Valve Chamber - 500 to 630 MM- B4.33 14 13.02-Z02-2-L-74-TSE | 1 | 2025-01-19 | 2025-01-20
| JD3RZ02-2L74WT11084 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-2-L-74-WT | 1 | 2024-12-30 | 2025-01-04 | 2025-01-09 | 2025-03-24
| JD3RZ02-2L74WT11084.R | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-2-L-74-WT -Remaining | 1 | 2025-01-21 | 2025-01-22 | 2025-08-23 | 2025-08-24
| JD3RZ02-2L74WT11085 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-2-L-74-WT | 1 | 2025-01-05 | 2025-01-09 | 2025-01-15 | 2025-05-06
| JD3RZ02-2L74WT11085.R | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-2-L-74-WT -Remainin | 1 | 2025-01-23 | 2025-01-25 | 2025-08-25 | 2025-08-26
| JD3RZ02-2L74WT11086 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-2-L-74-WT | 1 | 2025-01-11 | 2025-01-20 | 2025-01-16 | 2025-06-14
| JD3RZ02-2L74WT11086.R | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-2-L-74-WT -Remaining | 1 | 2025-01-26 | 2025-01-27 | 2025-08-27 | 2025-08-28
| JD3RZ02-2L74WT11087 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-2-L-74-WT | 1 | 2025-01-21 | 2025-01-27 | 2025-01-21 | 2025-03-17
| JD3RZ02-2L74WT11087.R | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-2-L-74-WT -Remaining | 1 | 2025-01-28 | 2025-01-29 | 2025-08-28 | 2025-08-30
| JD3RZ02-2L74WT11088 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-2-L-74-WT | 1 | 2025-01-28 | 2025-02-03 | 2025-06-10 | 2025-07-31
| JD3RZ02-2L74WT11088.R | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-2-L-74-WT -Remaining | 1 | 2025-02-04 | 2025-02-05 | 2025-08-30 | 2025-08-31
| JD3RZ02-2L74WT11109 | INSTALLATIONfor gate valves 150 mm - - B3.33 14 19.01-Z02-2-L-74-WT | 1 | 2025-01-28 | 2025-01-30
| JD3RZ02-2L74WT11110 | TESTING AND COMMITIONfor gate valves 150 mm - - B3.33 14 19.01-Z02-2-L-74-WT | 1 | 2025-02-01 | 2025-02-03
| JD3RZ02-2L74WT11119 | EXCAVATION and Bedding Worksfor Fire Hydrant - - B3.33 14 19.08-Z02-2-L-74-WT | 1 | 2025-01-23 | 2025-01-25
| JD3RZ02-2L74WT11120 | INSTALLATIONfor Fire Hydrant - - B3.33 14 19.08-Z02-2-L-74-WT | 1 | 2025-01-26 | 2025-01-27
| JD3RZ02-2L74WT11121 | TESTING AND COMMITIONfor Fire Hydrant - - B3.33 14 19.08-Z02-2-L-74-WT | 1 | 2025-01-28 | 2025-01-29
| JD3RZ02-2L75EL12070 | Remove And Transfare An existing lighting pole - - NB2.26 24 16.01-Z02-2-L-75-SL | 1 | 2025-04-15 | 2025-04-16 | 2025-07-15 | 2025-07-16
| JD3RZ02-2L75EL12071 | Re-installing An existing lighting pole In New Place - - NB2.26 24 16.01-Z02-2-L-75-SL | 1 | 2025-04-17 | 2025-04-19 | 2025-07-19 | 2025-07-20
| JD3RZ02-2L75RD12134 | Supply, lay and compaction subgrade compacted thicknessfor ROADS thickness 300mm - - B1.31 22 00.01-Z02-2-L-75-RD | 1 | 2025-01-07 | 2025-01-11 | 2025-02-20 | 2025-03-29
| JD3RZ02-2L75RD12135 | Supply, lay and compaction Aggregate base course compacted thicknessfor ROADS thickness 300mm - - B1.32 11 23.01-Z02-2-L | 1 | 2025-01-12 | 2025-01-13 | 2025-02-20 | 2025-03-10
| JD3RZ02-2L75RD12136 | Supply and spreading of Prime coat MC1for ROADS - - B1.32 11 26.01-Z02-2-L-75-RD | 1 | 2025-01-25 | 2025-01-26 | 2025-06-25 | 2025-07-13
| JD3RZ02-2L75RD12136.R | Supply and spreading of Prime coat MC1for ROADS - - B1.32 11 26.01-Z02-2-L-75-RD -Remaining | 1 | 2025-05-04 | 2025-05-05 | 2025-08-16 | 2025-08-17
| JD3RZ02-2L75RD12137 | Supply, lay and compaction Asphaltic base coursefor ROADS - - B1.32 11 26.01-Z02-2-L-75-RD | 1 | 2025-01-27 | 2025-01-28 | 2025-06-28 | 2025-07-15
| JD3RZ02-2L75RD12137.R | Supply, lay and compaction Asphaltic base coursefor ROADS - - B1.32 11 26.01-Z02-2-L-75-RD -Remaining | 1 | 2025-05-06 | 2025-05-07 | 2025-08-19 | 2025-08-20
| JD3RZ02-2L75RD12138 | Supply and spreading of Tack coat RC2for ROADS - - B1.32 12 16.01-Z02-2-L-75-RD | 1 | 2025-05-08 | 2025-05-10 | 2025-09-28 | 2025-09-29
| JD3RZ02-2L75RD12139 | Supply, lay and compaction Asphaltic wearing coursefor ROADS - - B1.32 12 16.01-Z02-2-L-75-RD | 1 | 2025-05-11 | 2025-05-12 | 2025-09-29 | 2025-09-30
| JD3RZ02-2L75RD12140 | Supply and installation Precast Concrete Kerb, Type K1-Dfor ROADS - - B1.32 14 13.01-Z02-2-L-75-RD | 1 | 2025-05-13 | 2025-05-26 | 2025-08-16 | 2025-09-20
| JD3RZ02-2L75RD12142 | Supply and installation Depressed curbs Type K2for ROADS - - B1.32 14 13.03-Z02-2-L-75-RD | 1 | 2025-05-27 | 2025-05-28 | 2025-08-16 | 2025-09-20
| JD3RZ02-2L75RD12144 | Supply and installation Retroreflective Thermoplastic White Traffic linesfor ROADS - - B1.32 17 23.01-Z02-2-L-75-RD | 1 | 2025-05-29 | 2025-05-31
| JD3RZ02-2L75RD12148 | Supply and installation Right-left Arrowfor ROADS - - B1.32 17 23.05-Z02-2-L-75-RD | 1 | 2025-06-01 | 2025-06-02
| JD3RZ02-2L75RD12149 | Supply and install Straight-Right Arrowfor ROADS - - B1.32 17 23.06-Z02-2-L-75-RD | 1 | 2025-06-03 | 2025-06-07
| JD3RZ02-2L75RD12150 | Supply and install Straight-Left Arrowfor ROADS - - B1.32 17 23.07-Z02-2-L-75-RD | 1 | 2025-06-08 | 2025-06-11
| JD3RZ02-2L75RD12151 | Supply and installation Traffic signs with Single postfor ROADS - - B1.10 14 53.01-Z02-2-L-75-RD | 1 | 2025-06-12 | 2025-06-14
| JD3RZ02-2L75SL12070 | Excavation Worksfor Copper Cables 4Cx25 mm² - - B2.26 05 19.04-Z02-2-L-75-SL | 1 | 2025-02-22 | 2025-02-23 | 2025-08-06 | 2025-08-11
| JD3RZ02-2L75SL12071 | Installationfor Copper Cables 4Cx25 mm² - - B2.26 05 19.04-Z02-2-L-75-SL | 1 | 2025-02-24 | 2025-02-25 | 2025-08-20 | 2025-08-27
| JD3RZ02-2L75SL12072 | Backfilling, Warning Tabe Worksfor Copper Cables 4Cx25 mm² - - B2.26 05 19.04-Z02-2-L-75-SL | 1 | 2025-02-26 | 2025-02-27 | 2025-08-28 | 2025-09-02
| JD3RZ02-2L75SL12073 | Testing and Commitioning for Copper Cables 4Cx25 mm² - - B2.26 05 19.04-Z02-2-L-75-SL | 1 | 2025-03-01 | 2025-03-02
| JD3RZ02-2L75SL12084 | INSTALLINGfor insulated copper conductor 16 mm² - - B2.26 05 19.08-Z02-2-L-75-SL | 1 | 2025-02-26 | 2025-02-27
| JD3RZ02-2L75SL12085 | TESTING AND COMMITIONINGfor insulated copper conductor 16 mm² - - B2.26 05 19.08-Z02-2-L-75-SL | 1 | 2025-03-01 | 2025-03-02
| JD3RZ02-2L75SL12091 | Excavation of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-2-L-75-SL | 1 | 2025-02-24 | 2025-02-25 | 2025-08-04 | 2025-08-10
| JD3RZ02-2L75SL12092 | Installation of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-2-L-75-SL | 1 | 2025-02-26 | 2025-02-27 | 2025-08-10 | 2025-08-16
| JD3RZ02-2L75SL12093 | Backfilling of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-2-L-75-SL | 1 | 2025-03-01 | 2025-03-02 | 2025-08-17 | 2025-08-20
| JD3RZ02-2L75SL12094 | Installation Worksfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-2-L-75-SL | 1 | 2025-03-03 | 2025-03-05 | 2025-08-21 | 2025-08-24
| JD3RZ02-2L75SL12095 | Testing and Commitioningfor LIGHTING POLE one arm - - B2.26 56 19.02-Z02-2-L-75-SL | 1 | 2025-03-06 | 2025-03-09
| JD3RZ02-2L75SL12096 | Installationfor Lighting( LED ) Luminaire 150 WATT - - B2.26.56.19.01-Z02-2-L-75-SL | 1 | 2025-03-01 | 2025-03-02 | 2025-08-21 | 2025-08-24
| JD3RZ02-2L75SL12099 | Supply, construct, connect and test earthing pitsfor Street Lighting EARTHING SYSTEM - - B2.26 05 26.01-Z02-2-L-75-SL | 1 | 2025-03-01 | 2025-03-02
| JD3RZ02-2L75SL12112 | Excavationfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z02-2-L-75-SL | 1 | 2025-02-26 | 2025-03-01 | 2025-08-04
| JD3RZ02-2L75SL12113 | Installationfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z02-2-L-75-SL | 1 | 2025-03-02 | 2025-03-04 | 2025-08-10
| JD3RZ02-2L75SL12114 | Backfillingfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z02-2-L-75-SL | 1 | 2025-03-05 | 2025-03-08 | 2025-08-17
| JD3RZ02-2L75SS11440 | Trench excavation for GRP Pipe Line 200 mm - depth from 0.00 to 1.50- B5.33 31 00.03-Z02-2-L-75-SS | 1 | 2024-12-15 | 2024-12-16 | 2025-01-09 | 2025-01-27
| JD3RZ02-2L75SS11441 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - depth from 0.00 to 1.50- B5.33 31 00.03-Z02-2-L-75-SS | 1 | 2024-12-17 | 2024-12-18 | 2025-01-11 | 2025-01-28
| JD3RZ02-2L75SS11442 | Installing for GRP Pipe Line 200 mm - depth from 0.00 to 1.50- B5.33 31 00.03-Z02-2-L-75-SS | 1 | 2024-12-19 | 2024-12-21 | 2025-01-13 | 2025-01-30
| JD3RZ02-2L75SS11443 | Primary Test for GRP Pipe Line 200 mm - depth from 0.00 to 1.50- B5.33 31 00.03-Z02-2-L-75-SS | 1 | 2024-12-22 | 2024-12-23 | 2025-02-03 | 2025-02-20
| JD3RZ02-2L75SS11444 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - depth from 0.00 to 1.50- B5.33 31 00.03-Z02-2-L-75-SS | 1 | 2024-12-24 | 2024-12-25 | 2025-02-18 | 2025-03-08
| JD3RZ02-2L75SS11445 | Trench excavation for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-2-L-75-SS | 1 | 2024-12-15 | 2024-12-16 | 2025-01-14 | 2025-02-19
| JD3RZ02-2L75SS11446 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-2-L-75-SS | 1 | 2024-12-17 | 2024-12-18 | 2025-01-15 | 2025-02-20
| JD3RZ02-2L75SS11447 | Installing for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-2-L-75-SS | 1 | 2024-12-19 | 2024-12-21 | 2025-01-15 | 2025-02-20
| JD3RZ02-2L75SS11448 | Primary Test for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-2-L-75-SS | 1 | 2024-12-22 | 2024-12-23 | 2025-02-12 | 2025-03-20
| JD3RZ02-2L75SS11449 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z02-2-L-75-SS | 1 | 2024-12-24 | 2024-12-26 | 2025-04-23 | 2025-06-26
| JD3RZ02-2L75SS11450 | Trench excavation for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-2-L-75-SS | 1 | 2024-12-15 | 2024-12-16 | 2025-01-07 | 2025-02-12
| JD3RZ02-2L75SS11451 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-2-L-75-SS | 1 | 2024-12-17 | 2024-12-18 | 2025-01-07 | 2025-02-12
| JD3RZ02-2L75SS11452 | Installing for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-2-L-75-SS | 1 | 2024-12-19 | 2024-12-21 | 2025-01-15 | 2025-02-20
| JD3RZ02-2L75SS11453 | Primary Test for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-2-L-75-SS | 1 | 2024-12-22 | 2024-12-23 | 2025-01-22 | 2025-02-27
| JD3RZ02-2L75SS11454 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z02-2-L-75-SS | 1 | 2024-12-24 | 2024-12-25 | 2025-01-22 | 2025-04-06
| JD3RZ02-2L75SS11460 | Trench excavation for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50- B5.33 31 00.11-Z02-2-L-75-SS | 1 | 2024-12-15 | 2024-12-16 | 2025-01-07 | 2025-01-25
| JD3RZ02-2L75SS11461 | Soil Replacement and Bedding Works for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50- B5.33 31 00.11-Z02-2-L-75-SS | 1 | 2024-12-17 | 2024-12-18 | 2025-01-13 | 2025-01-30
| JD3RZ02-2L75SS11462 | Installing for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50- B5.33 31 00.11-Z02-2-L-75-SS | 1 | 2024-12-19 | 2024-12-21 | 2025-01-15 | 2025-02-02
| JD3RZ02-2L75SS11463 | Primary Test for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50- B5.33 31 00.11-Z02-2-L-75-SS | 1 | 2024-12-22 | 2024-12-23 | 2025-01-22 | 2025-02-09
| JD3RZ02-2L75SS11464 | Backfilling and warning tabe Works for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50- B5.33 31 00.11-Z02-2-L-75-SS | 1 | 2024-12-24 | 2024-12-25 | 2025-02-04 | 2025-02-22
| JD3RZ02-2L75SS11464.R | Backfilling and warning tabe Works for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50- B5.33 31 00.11-Z02-2-L-75-SS -Rem | 1 | 2024-12-26 | 2024-12-28 | 2025-08-02 | 2025-08-03
| JD3RZ02-2L75SS11465 | Trench excavation for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50- B5.33 31 00.12-Z02-2-L-75-SS | 1 | 2024-12-15 | 2024-12-16 | 2025-02-05 | 2025-02-23
| JD3RZ02-2L75SS11466 | Soil Replacement and Bedding Works for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50- B5.33 31 00.12-Z02-2-L-75-SS | 1 | 2024-12-17 | 2024-12-18 | 2025-02-09 | 2025-02-26
| JD3RZ02-2L75SS11467 | Installing for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50- B5.33 31 00.12-Z02-2-L-75-SS | 1 | 2024-12-19 | 2024-12-21 | 2025-02-11 | 2025-03-01
| JD3RZ02-2L75SS11468 | Primary Test for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50- B5.33 31 00.12-Z02-2-L-75-SS | 1 | 2024-12-22 | 2024-12-23 | 2025-02-18 | 2025-03-08
| JD3RZ02-2L75SS11469 | Backfilling and warning tabe Works for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50- B5.33 31 00.12-Z02-2-L-75-SS | 1 | 2024-12-24 | 2024-12-25 | 2025-02-25 | 2025-03-15
| JD3RZ02-2L75SS11487 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z02-2-L-75-SS | 1 | 2024-12-15 | 2024-12-16 | 2025-02-11 | 2025-03-01
| JD3RZ02-2L75SS11488 | Installation of Base Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z02-2-L-75-SS | 1 | 2024-12-17 | 2024-12-18 | 2025-02-13 | 2025-03-03
| JD3RZ02-2L75SS11489 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z02-2-L | 1 | 2024-12-19 | 2024-12-21 | 2025-02-17 | 2025-03-06
| JD3RZ02-2L75SS11490 | Backfilling Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z02-2-L-75-SS | 1 | 2024-12-22 | 2024-12-23 | 2025-06-10 | 2025-06-28
| JD3RZ02-2L75SS11491 | Finishing, Benching Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z02-2-L-75-SS | 1 | 2024-12-24 | 2024-12-25 | 2025-06-15 | 2025-07-02
| JD3RZ02-2L75SS11499 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-2-L-75-SS | 1 | 2024-12-15 | 2024-12-16 | 2025-02-11 | 2025-03-01
| JD3RZ02-2L75SS11500 | Installation of Base Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-2-L-75-SS | 1 | 2024-12-17 | 2024-12-21 | 2025-02-17 | 2025-03-25
| JD3RZ02-2L75SS11501 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-2-L | 1 | 2024-12-22 | 2024-12-25 | 2025-02-19 | 2025-03-27
| JD3RZ02-2L75SS11502 | Backfilling Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-2-L-75-SS | 1 | 2024-12-26 | 2024-12-28 | 2025-06-10 | 2025-06-28
| JD3RZ02-2L75SS11503 | Finishing, Benching Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z02-2-L-75-SS | 1 | 2024-12-29 | 2024-12-30 | 2025-06-15 | 2025-07-02
| JD3RZ02-2L75ST11576 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-2-L-75-ST | 1 | 2024-12-15 | 2024-12-16
| JD3RZ02-2L75ST11577 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-2-L-75-ST | 1 | 2024-12-17 | 2024-12-18
| JD3RZ02-2L75ST11578 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-2-L-75-ST | 1 | 2024-12-19 | 2024-12-21
| JD3RZ02-2L75ST11579 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-2-L-75-ST | 1 | 2024-12-22 | 2024-12-23
| JD3RZ02-2L75ST11580 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z02-2-L-75-ST | 1 | 2024-12-24 | 2024-12-25
| JD3RZ02-2L75ST11596 | Excavation Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z02-2-L-75-ST | 1 | 2024-12-15 | 2024-12-16 | 2025-06-25 | 2025-07-13
| JD3RZ02-2L75ST11597 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z02-2-L-75-ST | 1 | 2024-12-17 | 2024-12-18 | 2025-06-28 | 2025-07-15
| JD3RZ02-2L75ST11598 | Installing for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z02-2-L-75-ST | 1 | 2024-12-19 | 2024-12-21 | 2025-06-30 | 2025-07-17
| JD3RZ02-2L75ST11599 | Primary Test for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z02-2-L-75-ST | 1 | 2024-12-22 | 2024-12-23 | 2025-07-03 | 2025-07-21
| JD3RZ02-2L75ST11600 | Backfilling Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z02-2-L-75-ST | 1 | 2024-12-24 | 2024-12-25 | 2025-07-06 | 2025-07-23
| JD3RZ02-2L75ST11601 | Excavation Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-2-L-75-ST | 1 | 2024-12-15 | 2024-12-16 | 2025-06-25 | 2025-07-13
| JD3RZ02-2L75ST11602 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-2-L-75-ST | 1 | 2024-12-17 | 2024-12-18 | 2025-06-28 | 2025-07-15
| JD3RZ02-2L75ST11603 | Installing for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-2-L-75-ST | 1 | 2024-12-19 | 2024-12-21 | 2025-06-30 | 2025-07-17
| JD3RZ02-2L75ST11604 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-2-L-75-ST | 1 | 2024-12-22 | 2024-12-23 | 2025-07-03 | 2025-07-21
| JD3RZ02-2L75ST11605 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z02-2-L-75-ST | 1 | 2024-12-24 | 2024-12-25 | 2025-07-06 | 2025-07-23
| JD3RZ02-2L75ST11749 | Excavation Works For Manholes Diam 1200 depth from 0.00 to 1.50 - - B6.33 05 39.01-Z02-2-L-75-ST | 1 | 2024-12-29 | 2024-12-30 | 2025-08-04 | 2025-08-05
| JD3RZ02-2L75ST11750 | Base Plain Concrete Works For Manholes Diam 1200 depth from 0.00 to 1.50 - - B6.33 05 39.01-Z02-2-L-75-ST | 1 | 2024-12-31 | 2025-01-01 | 2025-08-06 | 2025-08-07
| JD3RZ02-2L75ST11751 | Manhole Installation Works For Manholes Diam 1200 depth from 0.00 to 1.50 - - B6.33 05 39.01-Z02-2-L-75-ST | 1 | 2025-01-02 | 2025-01-04 | 2025-08-09 | 2025-08-10
| JD3RZ02-2L75ST11752 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 0.00 to 1.50 - - B6.33 05 39.01-Z02-2-L-75-ST | 1 | 2025-01-05 | 2025-01-06 | 2025-08-11 | 2025-08-12
| JD3RZ02-2L75ST11753 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 0.00 to 1.50 - - B6.33 05 39.01-Z02-2-L-75-ST | 1 | 2025-01-07 | 2025-01-08
| JD3RZ02-2L75ST11754 | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-2-L-75-ST | 1 | 2024-12-31 | 2025-01-01 | 2025-08-06 | 2025-08-07
| JD3RZ02-2L75ST11755 | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-2-L-75-ST | 1 | 2025-01-02 | 2025-01-04 | 2025-08-09 | 2025-08-10
| JD3RZ02-2L75ST11756 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-2-L-75-ST | 1 | 2025-01-05 | 2025-01-06 | 2025-08-11 | 2025-08-12
| JD3RZ02-2L75ST11757 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-2-L-75-ST | 1 | 2025-01-07 | 2025-01-08 | 2025-08-13 | 2025-08-14
| JD3RZ02-2L75ST11758 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z02-2-L-75-ST | 1 | 2025-01-09 | 2025-01-11
| JD3RZ02-2L75ST11769 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-2-L-75-ST | 1 | 2025-01-02 | 2025-01-04
| JD3RZ02-2L75ST11770 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-2-L-75-ST | 1 | 2025-01-05 | 2025-01-06
| JD3RZ02-2L75ST11771 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-2-L-75-ST | 1 | 2025-01-07 | 2025-01-08
| JD3RZ02-2L75ST11772 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-2-L-75-ST | 1 | 2025-01-09 | 2025-01-11
| JD3RZ02-2L75ST11773 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z02-2-L-75-ST | 1 | 2025-01-12 | 2025-01-13
| JD3RZ02-2L75ST11793 | EXCAVATION Works for Catchbasine double - - B6.33 05 39.10-Z02-2-L-75-ST | 1 | 2025-01-05 | 2025-01-06
| JD3RZ02-2L75ST11794 | Catchbasine Installation Works For Catchbasine double - - B6.33 05 39.10-Z02-2-L-75-ST | 1 | 2025-01-07 | 2025-01-08
| JD3RZ02-2L75ST11795 | FINISHING Works For Catchbasine double - - B6.33 05 39.10-Z02-2-L-75-ST | 1 | 2025-01-09 | 2025-01-11
| JD3RZ02-2L75ST11796 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - - B6.33 05 39.10-Z02-2-L-75-ST | 1 | 2025-01-12 | 2025-01-13
| JD3RZ02-2L75ST524370 | Excavation for cutting material, in all type of soil- NNB6.33 42 11.25-Z02-2-L-75-ST | 1 | 2025-01-26 | 2025-02-02
| JD3RZ02-2L75TC12127 | Excavation Worksfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z02-2-L-75-TC | 1 | 2025-04-20 | 2025-04-22 | 2025-08-10
| JD3RZ02-2L75TC12128 | Installationfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z02-2-L-75-TC | 1 | 2025-04-23 | 2025-04-29 | 2025-08-16
| JD3RZ02-2L75TC12129 | Pouring Concrete Coverfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z02-2-L-75-TC | 1 | 2025-04-30 | 2025-05-06 | 2025-08-20
| JD3RZ02-2L75TC12130 | Backfilling Worksfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z02-2-L-75-TC | 1 | 2025-05-07 | 2025-05-10
| JD3RZ02-2L75TC12131 | Excavation and Bedding Worksfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z02-2-L-75-TC | 1 | 2025-04-23 | 2025-04-26 | 2025-08-10
| JD3RZ02-2L75TC12132 | Installationfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z02-2-L-75-TC | 1 | 2025-04-27 | 2025-04-29 | 2025-08-16
| JD3RZ02-2L75TC12133 | Backfilling Worksfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z02-2-L-75-TC | 1 | 2025-04-30 | 2025-05-03 | 2025-08-20
| JD3RZ02-2L75TSE11847 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-2-L-75-TSE | 1 | 2024-12-26 | 2024-12-28 | 2025-01-15 | 2025-02-02
| JD3RZ02-2L75TSE11848 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-2-L-75-TSE | 1 | 2024-12-29 | 2024-12-30 | 2025-01-16 | 2025-02-03
| JD3RZ02-2L75TSE11849 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-2-L-75-TSE | 1 | 2024-12-31 | 2025-01-01 | 2025-05-17 | 2025-06-12
| JD3RZ02-2L75TSE11850 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-2-L-75-TSE | 1 | 2025-01-02 | 2025-01-04 | 2025-06-30 | 2025-07-27
| JD3RZ02-2L75TSE11851 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-2-L-75-TSE | 1 | 2025-01-05 | 2025-01-06 | 2025-05-25 | 2025-06-11
| JD3RZ02-2L75TSE11852 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-2-L-75-TSE | 1 | 2025-01-14 | 2025-01-15
| JD3RZ02-2L75TSE11853 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-2-L-75-TSE | 1 | 2025-01-16 | 2025-01-18
| JD3RZ02-2L75TSE11854 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-2-L-75-TSE | 1 | 2025-01-19 | 2025-01-20
| JD3RZ02-2L75TSE11855 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-2-L-75-TSE | 1 | 2025-01-21 | 2025-01-22
| JD3RZ02-2L75TSE11856 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-2-L-75-TSE | 1 | 2025-01-23 | 2025-01-25
| JD3RZ02-2L75TSE11857 | Excavation Worksfor HDPE Pipes 315 mm - depth from 0 to 1.5 m- B4.33 31 00.03-Z02-2-L-75-TSE | 1 | 2024-12-26 | 2024-12-29 | 2025-01-11 | 2025-01-28
| JD3RZ02-2L75TSE11858 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 0 to 1.5 m- B4.33 31 00.03-Z02-2-L-75-TSE | 1 | 2024-12-30 | 2025-01-01 | 2025-01-15 | 2025-02-11
| JD3RZ02-2L75TSE11859 | Installing for HDPE Pipes 315 mm - depth from 0 to 1.5 m- B4.33 31 00.03-Z02-2-L-75-TSE | 1 | 2025-01-02 | 2025-01-07 | 2025-01-25 | 2025-04-27
| JD3RZ02-2L75TSE11860 | Testing for HDPE Pipes 315 mm - depth from 0 to 1.5 m- B4.33 31 00.03-Z02-2-L-75-TSE | 1 | 2025-01-08 | 2025-01-11 | 2025-06-30 | 2025-07-31
| JD3RZ02-2L75TSE11861 | Backfillingfor HDPE Pipes 315 mm - depth from 0 to 1.5 m- B4.33 31 00.03-Z02-2-L-75-TSE | 1 | 2025-01-12 | 2025-01-14 | 2025-06-10 | 2025-07-07
| JD3RZ02-2L75TSE11862 | Excavation Worksfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z02-2-L-75-TSE | 1 | 2024-12-26 | 2024-12-28 | 2025-01-07 | 2025-01-25
| JD3RZ02-2L75TSE11863 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z02-2-L-75-TSE | 1 | 2024-12-29 | 2024-12-30 | 2025-05-10 | 2025-05-27
| JD3RZ02-2L75TSE11864 | Installing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z02-2-L-75-TSE | 1 | 2024-12-31 | 2025-01-01 | 2025-05-17 | 2025-06-03
| JD3RZ02-2L75TSE11865 | Testing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z02-2-L-75-TSE | 1 | 2025-01-02 | 2025-01-04 | 2025-06-30 | 2025-07-17
| JD3RZ02-2L75TSE11866 | Backfillingfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z02-2-L-75-TSE | 1 | 2025-01-05 | 2025-01-06 | 2025-05-25 | 2025-06-11
| JD3RZ02-2L75TSE11867 | Excavation Worksfor HDPE Pipes 315 mm - depth from 2.51 to 3.5 m- B4.33 31 00.05-Z02-2-L-75-TSE | 1 | 2024-12-26 | 2024-12-28 | 2025-01-07 | 2025-01-25
| JD3RZ02-2L75TSE11868 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 2.51 to 3.5 m- B4.33 31 00.05-Z02-2-L-75-TSE | 1 | 2024-12-29 | 2024-12-30 | 2025-05-10 | 2025-05-27
| JD3RZ02-2L75TSE11869 | Installing for HDPE Pipes 315 mm - depth from 2.51 to 3.5 m- B4.33 31 00.05-Z02-2-L-75-TSE | 1 | 2024-12-31 | 2025-01-01 | 2025-05-17 | 2025-06-03
| JD3RZ02-2L75TSE11870 | Testing for HDPE Pipes 315 mm - depth from 2.51 to 3.5 m- B4.33 31 00.05-Z02-2-L-75-TSE | 1 | 2025-01-02 | 2025-01-04 | 2025-06-30 | 2025-07-17
| JD3RZ02-2L75TSE11871 | Backfillingfor HDPE Pipes 315 mm - depth from 2.51 to 3.5 m- B4.33 31 00.05-Z02-2-L-75-TSE | 1 | 2025-01-05 | 2025-01-06 | 2025-05-25 | 2025-06-11
| JD3RZ02-2L75TSE11892 | Excavation Worksfor HDPE Pipes 450 mm - depth from 1.51 to 2.5 m- B4.33 31 00.10-Z02-2-L-75-TSE | 1 | 2024-12-26 | 2024-12-28 | 2025-01-11 | 2025-01-28
| JD3RZ02-2L75TSE11893 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m- B4.33 31 00.10-Z02-2-L-75-TSE | 1 | 2024-12-29 | 2024-12-30 | 2025-01-15 | 2025-02-02
| JD3RZ02-2L75TSE11894 | Installing for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m- B4.33 31 00.10-Z02-2-L-75-TSE | 1 | 2024-12-31 | 2025-01-01 | 2025-01-25 | 2025-02-11
| JD3RZ02-2L75TSE11895 | Testing for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m- B4.33 31 00.10-Z02-2-L-75-TSE | 1 | 2025-01-02 | 2025-01-04 | 2025-06-30 | 2025-07-17
| JD3RZ02-2L75TSE11896 | Backfillingfor HDPE Pipes 450 mm - depth from 1.51 to 2.5 m- B4.33 31 00.10-Z02-2-L-75-TSE | 1 | 2025-01-15 | 2025-01-16 | 2025-06-10 | 2025-06-28
| JD3RZ02-2L75TSE11897 | Excavation Worksfor HDPE Pipes 450 mm - depth from 2.51 to 3.5 m- B4.33 31 00.11-Z02-2-L-75-TSE | 1 | 2025-01-16 | 2025-01-18
| JD3RZ02-2L75TSE11898 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 2.51 to 3.5 m- B4.33 31 00.11-Z02-2-L-75-TSE | 1 | 2025-01-19 | 2025-01-20
| JD3RZ02-2L75TSE11899 | Installing for HDPE Pipes 450 mm - depth from 2.51 to 3.5 m- B4.33 31 00.11-Z02-2-L-75-TSE | 1 | 2025-01-21 | 2025-01-22
| JD3RZ02-2L75TSE11900 | Testing for HDPE Pipes 450 mm - depth from 2.51 to 3.5 m- B4.33 31 00.11-Z02-2-L-75-TSE | 1 | 2025-01-23 | 2025-01-25
| JD3RZ02-2L75TSE11901 | Backfillingfor HDPE Pipes 450 mm - depth from 2.51 to 3.5 m- B4.33 31 00.11-Z02-2-L-75-TSE | 1 | 2025-01-28 | 2025-01-29
| JD3RZ02-2L75TSE11972 | Installationfor gate valves 100 mm - - B4.33 14 19.01-Z02-2-L-75-TSE | 1 | 2025-01-18 | 2025-01-19 | 2025-06-10 | 2025-06-28
| JD3RZ02-2L75TSE11972.R | Installationfor gate valves 100 mm - - B4.33 14 19.01-Z02-2-L-75-TSE -Remaining | 1 | 2025-01-23 | 2025-01-25
| JD3RZ02-2L75TSE11973 | Testing And Commtionningfor gate valves 100 mm - - B4.33 14 19.01-Z02-2-L-75-TSE | 1 | 2025-01-20 | 2025-01-21 | 2025-06-30 | 2025-07-17
| JD3RZ02-2L75TSE11973.R | Testing And Commtionningfor gate valves 100 mm - - B4.33 14 19.01-Z02-2-L-75-TSE -Remaining | 1 | 2025-01-26 | 2025-01-27
| JD3RZ02-2L75TSE11976 | Installationfor butterfly valves 300 mm. - - B4.33 14 19.03-Z02-2-L-75-TSE | 1 | 2025-01-26 | 2025-01-27
| JD3RZ02-2L75TSE11977 | Testing And Commtionningfor butterfly valves 300 mm. - - B4.33 14 19.03-Z02-2-L-75-TSE | 1 | 2025-01-28 | 2025-01-29
| JD3RZ02-2L75TSE11996 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-Z02-2-L-75-TSE | 1 | 2025-01-19 | 2025-01-20
| JD3RZ02-2L75TSE11997 | Plain Concrete Worksfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-Z02-2-L-75-TSE | 1 | 2025-01-21 | 2025-01-22
| JD3RZ02-2L75TSE11998 | INSTALLATIONfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-Z02-2-L-75-TSE | 1 | 2025-01-23 | 2025-01-25
| JD3RZ02-2L75TSE11999 | Backfilling Worksfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-Z02-2-L-75-TSE | 1 | 2025-01-30 | 2025-02-01
| JD3RZ02-2L75WT11797 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-2-L-75-WT | 1 | 2025-01-20 | 2025-01-23 | 2025-01-14 | 2025-04-07
| JD3RZ02-2L75WT11797.R | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-2-L-75-WT -Remaining | 1 | 2025-01-26 | 2025-01-27
| JD3RZ02-2L75WT11798 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-2-L-75-WT | 1 | 2025-01-25 | 2025-01-28 | 2025-01-15 | 2025-05-25
| JD3RZ02-2L75WT11798.R | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-2-L-75-WT -Remainin | 1 | 2025-01-29 | 2025-01-30
| JD3RZ02-2L75WT11799 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-2-L-75-WT | 1 | 2025-01-29 | 2025-02-06 | 2025-01-16 | 2025-05-26
| JD3RZ02-2L75WT11799.R | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-2-L-75-WT -Remaining | 1 | 2025-02-08 | 2025-02-09
| JD3RZ02-2L75WT11800 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-2-L-75-WT | 1 | 2025-02-08 | 2025-02-12 | 2025-01-21 | 2025-03-17
| JD3RZ02-2L75WT11800.R | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-2-L-75-WT -Remaining | 1 | 2025-02-13 | 2025-02-15
| JD3RZ02-2L75WT11801 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-2-L-75-WT | 1 | 2025-02-13 | 2025-02-18 | 2025-06-10 | 2025-07-31
| JD3RZ02-2L75WT11801.R | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z02-2-L-75-WT -Remaining | 1 | 2025-02-19 | 2025-02-20
| JD3RZ02-2L75WT11802 | Excavation Worksfor HDPE Pipes 225 mm - depth from 0 to 1.5 m- B3.33 14 13.02-Z02-2-L-75-WT | 1 | 2025-02-02 | 2025-02-03
| JD3RZ02-2L75WT11803 | Soil Replacement and Bedding Works for HDPE Pipes 225 mm - depth from 0 to 1.5 m- B3.33 14 13.02-Z02-2-L-75-WT | 1 | 2025-02-04 | 2025-02-05
| JD3RZ02-2L75WT11804 | Installing for HDPE Pipes 225 mm - depth from 0 to 1.5 m- B3.33 14 13.02-Z02-2-L-75-WT | 1 | 2025-02-06 | 2025-02-08
| JD3RZ02-2L75WT11805 | Testing for HDPE Pipes 225 mm - depth from 0 to 1.5 m- B3.33 14 13.02-Z02-2-L-75-WT | 1 | 2025-02-09 | 2025-02-10
| JD3RZ02-2L75WT11806 | Backfillingfor HDPE Pipes 225 mm - depth from 0 to 1.5 m- B3.33 14 13.02-Z02-2-L-75-WT | 1 | 2025-02-13 | 2025-02-15
| JD3RZ02-2L75WT11822 | INSTALLATIONfor gate valves 150 mm - - B3.33 14 19.01-Z02-2-L-75-WT | 1 | 2025-02-09 | 2025-02-10
| JD3RZ02-2L75WT11823 | TESTING AND COMMITIONfor gate valves 150 mm - - B3.33 14 19.01-Z02-2-L-75-WT | 1 | 2025-02-11 | 2025-02-12
| JD3RZ02-2L75WT11824 | INSTALLATIONfor gate valves 200 mm - - B3.33 14 19.02-Z02-2-L-75-WT | 1 | 2025-02-09 | 2025-02-10
| JD3RZ02-2L75WT11825 | TESTING AND COMMITIONfor gate valves 200 mm - - B3.33 14 19.02-Z02-2-L-75-WT | 1 | 2025-02-11 | 2025-02-12
| JD3RZ02-2L75WT11832 | EXCAVATION and Bedding Worksfor Fire Hydrant - - B3.33 14 19.08-Z02-2-L-75-WT | 1 | 2025-02-04 | 2025-02-05
| JD3RZ02-2L75WT11833 | INSTALLATIONfor Fire Hydrant - - B3.33 14 19.08-Z02-2-L-75-WT | 1 | 2025-02-06 | 2025-02-08
| JD3RZ02-2L75WT11834 | TESTING AND COMMITIONfor Fire Hydrant - - B3.33 14 19.08-Z02-2-L-75-WT | 1 | 2025-02-09 | 2025-02-10
| JD3RZ02-2RCBST21426 | Excavation Works for UPVC Pipe Line-B6.33 14 11.01-300 mm-depth from 0.00 to 1.50 m-Z02-2-RCB-ST | 1 | 2024-08-24 | 2024-08-25 | 2025-05-22 | 2025-06-09
| JD3RZ02-2RCBST21426.R | Excavation Works for UPVC Pipe Line-B6.33 14 11.01-300 mm-depth from 0.00 to 1.50 m-Z02-2-RCB-ST -Remaining | 1 | 2024-08-26 | 2024-08-27
| JD3RZ02-2RCBST21427 | Soil Replacement and Bedding Works for UPVC Pipe Line-B6.33 14 11.01-300 mm-depth from 0.00 to 1.50 m-Z02-2-RCB-ST | 1 | 2024-08-26 | 2024-08-27 | 2025-05-26 | 2025-06-12
| JD3RZ02-2RCBST21427.R | Soil Replacement and Bedding Works for UPVC Pipe Line-B6.33 14 11.01-300 mm-depth from 0.00 to 1.50 m-Z02-2-RCB-ST -Rem | 1 | 2024-08-28 | 2024-08-29
| JD3RZ02-2RCBST21428 | Installing for UPVC Pipe Line-B6.33 14 11.01-300 mm-depth from 0.00 to 1.50 m-Z02-2-RCB-ST | 1 | 2024-08-28 | 2024-08-29 | 2025-06-12 | 2025-06-30
| JD3RZ02-2RCBST21428.R | Installing for UPVC Pipe Line-B6.33 14 11.01-300 mm-depth from 0.00 to 1.50 m-Z02-2-RCB-ST -Remaining | 1 | 2024-08-31 | 2024-09-01
| JD3RZ02-2RCBST21429 | Primary Test for UPVC Pipe Line-B6.33 14 11.01-300 mm-depth from 0.00 to 1.50 m-Z02-2-RCB-ST | 1 | 2024-08-31 | 2024-09-01 | 2025-06-18 | 2025-07-06
| JD3RZ02-2RCBST21429.R | Primary Test for UPVC Pipe Line-B6.33 14 11.01-300 mm-depth from 0.00 to 1.50 m-Z02-2-RCB-ST -Remaining | 1 | 2024-09-02 | 2024-09-03
| JD3RZ02-2RCBST21430 | Backfilling Works for UPVC Pipe Line-B6.33 14 11.01-300 mm-depth from 0.00 to 1.50 m-Z02-2-RCB-ST | 1 | 2024-09-02 | 2024-09-03 | 2025-06-30 | 2025-07-17
| JD3RZ02-2RCBST21430.R | Backfilling Works for UPVC Pipe Line-B6.33 14 11.01-300 mm-depth from 0.00 to 1.50 m-Z02-2-RCB-ST -Remaining | 1 | 2024-09-04 | 2024-09-05
| JD3RZ02-2RCBST21436 | Excavation Works for GRP Pipe Line-B6.33 42 11.02-400 mm-depth from 1.51 to 2.50 m-Z02-2-RCB-ST | 1 | 2024-12-22 | 2024-12-23
| JD3RZ02-2RCBST21437 | Soil Replacement and Bedding Works for GRP Pipe Line-B6.33 42 11.02-400 mm-depth from 1.51 to 2.50 m-Z02-2-RCB-ST | 1 | 2024-12-24 | 2024-12-25
| JD3RZ02-2RCBST21438 | Installing for GRP Pipe Line-B6.33 42 11.02-400 mm-depth from 1.51 to 2.50 m-Z02-2-RCB-ST | 1 | 2024-12-26 | 2024-12-28
| JD3RZ02-2RCBST21439 | Primary Test for GRP Pipe Line-B6.33 42 11.02-400 mm-depth from 1.51 to 2.50 m-Z02-2-RCB-ST | 1 | 2024-12-29 | 2024-12-30
| JD3RZ02-2RCBST21440 | Backfilling Works for GRP Pipe Line-B6.33 42 11.02-400 mm-depth from 1.51 to 2.50 m-Z02-2-RCB-ST | 1 | 2025-01-02 | 2025-01-04
| JD3RZ02-2RCBST21644 | EXCAVATION Works for Catchbasine-B6.33 05 39.09-single-Z02-2-RCB-ST | 1 | 2024-12-24 | 2024-12-25
| JD3RZ02-2RCBST21645 | Catchbasine Installation Works for Catchbasine-B6.33 05 39.09-single-Z02-2-RCB-ST | 1 | 2024-12-26 | 2024-12-28
| JD3RZ02-2RCBST21646 | FINISHING Works for Catchbasine-B6.33 05 39.09-single-Z02-2-RCB-ST | 1 | 2024-12-29 | 2024-12-30
| JD3RZ02-2RCBST21647 | TESTING AND COMMITIONING RELEASED for Catchbasine-B6.33 05 39.09-single-Z02-2-RCB-ST | 1 | 2024-12-31 | 2025-01-01
| JD3RZ02-2RCBST21648 | EXCAVATION Works for Catchbasine-B6.33 05 39.10-double-Z02-2-RCB-ST | 1 | 2024-12-22 | 2024-12-23 | 2025-05-22 | 2025-06-09
| JD3RZ02-2RCBST21649 | Catchbasine Installation Works for Catchbasine-B6.33 05 39.10-double-Z02-2-RCB-ST | 1 | 2024-12-24 | 2024-12-25 | 2025-06-18 | 2025-07-06
| JD3RZ02-2RCBST21650 | FINISHING Works for Catchbasine-B6.33 05 39.10-double-Z02-2-RCB-ST | 1 | 2024-12-26 | 2024-12-28
| JD3RZ02-2RCBST21651 | TESTING AND COMMITIONING RELEASED for Catchbasine-B6.33 05 39.10-double-Z02-2-RCB-ST | 1 | 2024-12-29 | 2024-12-30
| JD3RZ02L47TSE4004 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-L-47-TSE | 1 | 2025-09-15 | 2025-09-17
| JD3RZ02L47TSE4005 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-L-47-TSE | 1 | 2025-09-18 | 2025-09-21
| JD3RZ02L47TSE4006 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-L-47-TSE | 1 | 2025-09-22 | 2025-09-27
| JD3RZ02L47TSE4007 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-L-47-TSE | 1 | 2025-09-28 | 2025-09-30
| JD3RZ02L47TSE4009 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-L-47-TSE | 1 | 2025-09-18 | 2025-09-22
| JD3RZ02L47TSE4010 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-L-47-TSE | 1 | 2025-09-23 | 2025-09-27
| JD3RZ02L47TSE4011 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-L-47-TSE | 1 | 2025-09-28 | 2025-10-05
| JD3RZ02L47TSE4177 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm- B4.33 14 13.10-Z02-L-47-TSE | 1 | 2025-09-23 | 2025-09-24
| JD3RZ02L47TSE4178 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm- B4.33 14 13.10-Z02-L-47-TSE | 1 | 2025-09-25 | 2025-09-27
| JD3RZ02L47TSE4179 | INSTALLATIONfor Air Valve Chamber - less than 315 mm- B4.33 14 13.10-Z02-L-47-TSE | 1 | 2025-09-28 | 2025-09-29
| JD3RZ02L48TSE4717 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-L-48-TSE | 1 | 2025-09-20 | 2025-09-21
| JD3RZ02L48TSE4718 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-L-48-TSE | 1 | 2025-09-22 | 2025-09-23
| JD3RZ02L48TSE4719 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-L-48-TSE | 1 | 2025-09-24 | 2025-09-27
| JD3RZ02L48TSE4720 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-L-48-TSE | 1 | 2025-09-28 | 2025-09-29
| JD3RZ02L48TSE4721 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-L-48-TSE | 1 | 2025-09-30 | 2025-10-01
| JD3RZ02L48TSE4842 | Installationfor gate valves 100 mm - - B4.33 14 19.01-Z02-L-48-TSE | 1 | 2025-09-24 | 2025-09-25
| JD3RZ02L48TSE4843 | Testing And Commtionningfor gate valves 100 mm - - B4.33 14 19.01-Z02-L-48-TSE | 1 | 2025-09-27 | 2025-09-28
| JD3RZ02L49TSE5430 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-L-49-TSE | 1 | 2025-09-20 | 2025-09-21 | 2025-08-20 | 2025-08-21
| JD3RZ02L49TSE5431 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-L-49-TSE | 1 | 2025-09-22 | 2025-09-24 | 2025-08-23 | 2025-08-25
| JD3RZ02L49TSE5432 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-L-49-TSE | 1 | 2025-09-25 | 2025-09-29 | 2025-08-26 | 2025-08-30
| JD3RZ02L49TSE5433 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-L-49-TSE | 1 | 2025-09-30 | 2025-10-02
| JD3RZ02L49TSE5555 | Installationfor gate valves 100 mm - - B4.33 14 19.01-Z02-L-49-TSE | 1 | 2025-09-25 | 2025-09-27
| JD3RZ02L49TSE5556 | Testing And Commtionningfor gate valves 100 mm - - B4.33 14 19.01-Z02-L-49-TSE | 1 | 2025-09-28 | 2025-09-29
| JD3RZ02L50TSE6143 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-L-50-TSE | 1 | 2025-09-20 | 2025-09-22
| JD3RZ02L50TSE6144 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-L-50-TSE | 1 | 2025-09-23 | 2025-09-25
| JD3RZ02L50TSE6145 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z02-L-50-TSE | 1 | 2025-09-27 | 2025-10-01
| JD3RZ02L50TSE6148 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-L-50-TSE | 1 | 2025-09-23 | 2025-09-24
| JD3RZ02L50TSE6149 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-L-50-TSE | 1 | 2025-09-25 | 2025-09-27
| JD3RZ02L50TSE6150 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-L-50-TSE | 1 | 2025-09-28 | 2025-09-29
| JD3RZ02L50TSE6151 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z02-L-50-TSE | 1 | 2025-09-30 | 2025-10-01
| JD3RZ02RCBST21200 | Excavation Works for UPVC Pipe Line-B6.33 14 11.01-300 mm-depth from 0.00 to 1.50 m-Z02-RCB-ST | 1 | 2025-09-11 | 2025-09-16
| JD3RZ02RCBST21201 | Soil Replacement and Bedding Works for UPVC Pipe Line-B6.33 14 11.01-300 mm-depth from 0.00 to 1.50 m-Z02-RCB-ST | 1 | 2025-09-17 | 2025-09-23
| JD3RZ02RCBST21202 | Installing for UPVC Pipe Line-B6.33 14 11.01-300 mm-depth from 0.00 to 1.50 m-Z02-RCB-ST | 1 | 2025-09-24 | 2025-10-01
| JD3RZ02RCBST21210 | Excavation Works for GRP Pipe Line-B6.33 42 11.02-400 mm-depth from 1.51 to 2.50 m-Z02-RCB-ST | 1 | 2025-09-17 | 2025-09-22
| JD3RZ02RCBST21211 | Soil Replacement and Bedding Works for GRP Pipe Line-B6.33 42 11.02-400 mm-depth from 1.51 to 2.50 m-Z02-RCB-ST | 1 | 2025-09-23 | 2025-09-28
| JD3RZ02RCBST21212 | Installing for GRP Pipe Line-B6.33 42 11.02-400 mm-depth from 1.51 to 2.50 m-Z02-RCB-ST | 1 | 2025-09-29 | 2025-10-05
| JD3RZ02RCBST21418 | EXCAVATION Works for Catchbasine-B6.33 05 39.09-single-Z02-RCB-ST | 1 | 2025-09-17 | 2025-09-25
| JD3RZ02RCBST21419 | Catchbasine Installation Works for Catchbasine-B6.33 05 39.09-single-Z02-RCB-ST | 1 | 2025-09-27 | 2025-10-09
| JD3RZ02RCBST21422 | EXCAVATION Works for Catchbasine-B6.33 05 39.10-double-Z02-RCB-ST | 1 | 2025-09-17 | 2025-09-21
| JD3RZ02RCBST21423 | Catchbasine Installation Works for Catchbasine-B6.33 05 39.10-double-Z02-RCB-ST | 1 | 2025-09-22 | 2025-09-28
| JD3RZ02RCBST21424 | FINISHING Works for Catchbasine-B6.33 05 39.10-double-Z02-RCB-ST | 1 | 2025-09-29 | 2025-10-05
| JD3RZ05L04TSE19690 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z05-L-04-TSE | 1 | 2025-09-20 | 2025-09-21
| JD3RZ05L04TSE19691 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z05-L-04-TSE | 1 | 2025-09-22 | 2025-09-23
| JD3RZ05L04TSE19692 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z05-L-04-TSE | 1 | 2025-09-24 | 2025-09-25
| JD3RZ05L04TSE19693 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z05-L-04-TSE | 1 | 2025-09-27 | 2025-09-28
| JD3RZ05L04TSE19695 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z05-L-04-TSE | 1 | 2025-09-22 | 2025-09-25 | 2025-09-02 | 2025-09-20
| JD3RZ05L04TSE19696 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z05-L-04-TSE | 1 | 2025-09-27 | 2025-09-30 | 2025-09-06 | 2025-09-23
| JD3RZ05L04TSE19817 | Installationfor gate valves 250 mm - - B4.33 14 19.02-Z05-L-04-TSE | 1 | 2025-09-27 | 2025-09-28
| JD3RZ05L04TSE19818 | Testing And Commtionningfor gate valves 250 mm - - B4.33 14 19.02-Z05-L-04-TSE | 1 | 2025-09-29 | 2025-09-30
| JD3RZ05L05TSE20403 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z05-L-05-TSE | 1 | 2025-09-20 | 2025-09-24
| JD3RZ05L05TSE20404 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z05-L-05-TSE | 1 | 2025-09-25 | 2025-09-30
| JD3RZ05L06TSE21116 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z05-L-06-TSE | 1 | 2025-09-20 | 2025-09-24
| JD3RZ05L06TSE21117 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z05-L-06-TSE | 1 | 2025-09-25 | 2025-09-30
| JD3RZ05L07TSE21829 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z05-L-07-TSE | 1 | 2025-09-20 | 2025-09-21
| JD3RZ05L07TSE21830 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z05-L-07-TSE | 1 | 2025-09-22 | 2025-09-23
| JD3RZ05L07TSE21831 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z05-L-07-TSE | 1 | 2025-09-24 | 2025-09-25
| JD3RZ05L07TSE21832 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z05-L-07-TSE | 1 | 2025-09-27 | 2025-09-28
| JD3RZ05L07TSE21834 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z05-L-07-TSE | 1 | 2025-09-22 | 2025-09-27
| JD3RZ05L07TSE21835 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z05-L-07-TSE | 1 | 2025-09-28 | 2025-10-02
| JD3RZ05L07TSE21956 | Installationfor gate valves 250 mm - - B4.33 14 19.02-Z05-L-07-TSE | 1 | 2025-09-27 | 2025-09-28
| JD3RZ05L07TSE21957 | Testing And Commtionningfor gate valves 250 mm - - B4.33 14 19.02-Z05-L-07-TSE | 1 | 2025-09-29 | 2025-09-30
| JD3RZ05L07TSE22002 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm- B4.33 14 13.10-Z05-L-07-TSE | 1 | 2025-09-28 | 2025-09-29
| JD3RZ05L07TSE22003 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm- B4.33 14 13.10-Z05-L-07-TSE | 1 | 2025-09-30 | 2025-10-01
| JD3RZ05RCBST20974 | Excavation Works for UPVC Pipe Line-B6.33 14 11.01-300 mm-depth from 0.00 to 1.50 m-Z05-RCB-ST | 1 | 2025-09-11 | 2025-09-17
| JD3RZ05RCBST20975 | Soil Replacement and Bedding Works for UPVC Pipe Line-B6.33 14 11.01-300 mm-depth from 0.00 to 1.50 m-Z05-RCB-ST | 1 | 2025-09-18 | 2025-09-25
| JD3RZ05RCBST20976 | Installing for UPVC Pipe Line-B6.33 14 11.01-300 mm-depth from 0.00 to 1.50 m-Z05-RCB-ST | 1 | 2025-09-27 | 2025-10-06
| JD3RZ05RCBST20984 | Excavation Works for GRP Pipe Line-B6.33 42 11.02-400 mm-depth from 1.51 to 2.50 m-Z05-RCB-ST | 1 | 2025-09-18 | 2025-09-24
| JD3RZ05RCBST20985 | Soil Replacement and Bedding Works for GRP Pipe Line-B6.33 42 11.02-400 mm-depth from 1.51 to 2.50 m-Z05-RCB-ST | 1 | 2025-09-25 | 2025-10-01
| JD3RZ05RCBST21192 | EXCAVATION Works for Catchbasine-B6.33 05 39.09-single-Z05-RCB-ST | 1 | 2025-09-25 | 2025-10-06
| JD3RZ06L53ST22266 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z06-L-53-ST | 1 | 2025-08-10 | 2025-08-12
| JD3RZ06L53ST22267 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z06-L-53-ST | 1 | 2025-08-13 | 2025-08-16
| JD3RZ06L53ST22268 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z06-L-53-ST | 1 | 2025-08-17 | 2025-08-20
| JD3RZ06L53ST22269 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z06-L-53-ST | 1 | 2025-08-21 | 2025-08-25
| JD3RZ06L53ST22270 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z06-L-53-ST | 1 | 2025-09-03 | 2025-09-08
| JD3RZ06L53ST22271 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z06-L-53-ST | 1 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-17
| JD3RZ06L53ST22272 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z06-L-53-ST | 1 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19
| JD3RZ06L53ST22273 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z06-L-53-ST | 1 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21
| JD3RZ06L53ST22274 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z06-L-53-ST | 1 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-24
| JD3RZ06L53ST22275 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z06-L-53-ST | 1 | 2025-09-03 | 2025-09-04 | 2025-08-25 | 2025-08-26
| JD3RZ06L53ST22276 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z06-L-53-ST | 1 | 2025-08-16 | 2025-08-17 | 2025-08-20
| JD3RZ06L53ST22277 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z06-L-53-ST | 1 | 2025-08-18 | 2025-08-19 | 2025-08-23
| JD3RZ06L53ST22278 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z06-L-53-ST | 1 | 2025-08-20 | 2025-08-21 | 2025-08-25
| JD3RZ06L53ST22279 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z06-L-53-ST | 1 | 2025-08-23 | 2025-08-24
| JD3RZ06L53ST22280 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z06-L-53-ST | 1 | 2025-09-03 | 2025-09-04
| JD3RZ06L53ST22306 | Excavation Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z06-L-53-ST | 1 | 2025-08-10 | 2025-08-11 | 2025-06-12 | 2025-06-30
| JD3RZ06L53ST22307 | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z06-L-53-ST | 1 | 2025-08-12 | 2025-08-13 | 2025-06-16 | 2025-07-03
| JD3RZ06L53ST22308 | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z06-L-53-ST | 1 | 2025-08-14 | 2025-08-16 | 2025-06-18 | 2025-07-06
| JD3RZ06L53ST22309 | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z06-L-53-ST | 1 | 2025-08-25 | 2025-08-26 | 2025-08-18 | 2025-08-21
| JD3RZ06L53ST22310 | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z06-L-53-ST | 1 | 2025-09-03 | 2025-09-04
| JD3RZ06L53ST22316 | Excavation Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-53-ST | 1 | 2025-08-10 | 2025-08-12 | 2025-06-12 | 2025-06-15
| JD3RZ06L53ST22316.R | Excavation Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-53-ST -Remaining | 1 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21
| JD3RZ06L53ST22317 | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-53-ST | 1 | 2025-08-13 | 2025-08-16 | 2025-06-16 | 2025-06-18
| JD3RZ06L53ST22317.R | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-53-ST -Rem | 1 | 2025-08-20 | 2025-08-21 | 2025-08-24 | 2025-08-24
| JD3RZ06L53ST22318 | Installing for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-53-ST | 1 | 2025-08-17 | 2025-08-19 | 2025-06-18 | 2025-06-22
| JD3RZ06L53ST22318.R | Installing for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-53-ST -Remaining | 1 | 2025-08-23 | 2025-08-24 | 2025-08-24 | 2025-09-20
| JD3RZ06L53ST22319 | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-53-ST | 1 | 2025-08-25 | 2025-08-27 | 2025-08-20
| JD3RZ06L53ST22320 | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-53-ST | 1 | 2025-09-03 | 2025-09-07
| JD3RZ06L53ST22326 | Excavation Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z06-L-53-ST | 1 | 2025-08-10 | 2025-08-13 | 2025-06-12 | 2025-07-19
| JD3RZ06L53ST22327 | Soil Replacement and Bedding Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z06-L-53-ST | 1 | 2025-08-14 | 2025-08-18 | 2025-06-16 | 2025-07-31
| JD3RZ06L53ST22328 | Installing for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z06-L-53-ST | 1 | 2025-08-19 | 2025-08-24 | 2025-06-18 | 2025-07-31
| JD3RZ06L53ST22328.R | Installing for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z06-L-53-ST -Remaining | 1 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28
| JD3RZ06L53ST22329 | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z06-L-53-ST | 1 | 2025-08-27 | 2025-08-31 | 2025-06-18
| JD3RZ06L53ST22330 | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z06-L-53-ST | 1 | 2025-09-03 | 2025-09-09
| JD3RZ06L53ST22341 | Excavation Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z06-L-53-ST | 1 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21
| JD3RZ06L53ST22342 | Soil Replacement and Bedding Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z06-L-53-ST | 1 | 2025-08-20 | 2025-08-21 | 2025-09-03 | 2025-09-06
| JD3RZ06L53ST22343 | Installing for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z06-L-53-ST | 1 | 2025-08-23 | 2025-08-24 | 2025-09-07 | 2025-09-09
| JD3RZ06L53ST22344 | Primary Test for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z06-L-53-ST | 1 | 2025-08-25 | 2025-08-26
| JD3RZ06L53ST22345 | Backfilling Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z06-L-53-ST | 1 | 2025-09-03 | 2025-09-04
| JD3RZ06L53ST22371 | Excavation Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z06-L-53-ST | 1 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-24
| JD3RZ06L53ST22372 | Soil Replacement and Bedding Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z06-L-53-ST | 1 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26
| JD3RZ06L53ST22373 | Installing for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z06-L-53-ST | 1 | 2025-08-25 | 2025-08-26 | 2025-08-25 | 2025-08-27
| JD3RZ06L53ST22374 | Primary Test for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z06-L-53-ST | 1 | 2025-08-27 | 2025-08-28
| JD3RZ06L53ST22375 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z06-L-53-ST | 1 | 2025-08-30 | 2025-08-31
| JD3RZ06L53ST22449 | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z06-L-53-ST | 1 | 2025-08-23 | 2025-08-24 | 2025-08-18 | 2025-08-19
| JD3RZ06L53ST22450 | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z06-L-53-ST | 1 | 2025-08-25 | 2025-08-26 | 2025-08-20 | 2025-08-21
| JD3RZ06L53ST22451 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z06-L-53-ST | 1 | 2025-08-27 | 2025-08-28
| JD3RZ06L53ST22452 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z06-L-53-ST | 1 | 2025-08-30 | 2025-08-31
| JD3RZ06L53ST22453 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z06-L-53-ST | 1 | 2025-09-01 | 2025-09-02
| JD3RZ06L53ST22459 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z06-L-53-ST | 1 | 2025-08-25 | 2025-08-26 | 2025-08-20 | 2025-08-21
| JD3RZ06L53ST22460 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z06-L-53-ST | 1 | 2025-08-27 | 2025-08-28 | 2025-08-22 | 2025-08-24
| JD3RZ06L53ST22461 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z06-L-53-ST | 1 | 2025-08-30 | 2025-08-31
| JD3RZ06L53ST22462 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z06-L-53-ST | 1 | 2025-09-01 | 2025-09-02
| JD3RZ06L53ST22463 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z06-L-53-ST | 1 | 2025-09-03 | 2025-09-04
| JD3RZ06L53ST22464 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z06-L-53-ST | 1 | 2025-08-10 | 2025-08-11 | 2025-06-12 | 2025-06-30
| JD3RZ06L53ST22465 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z06-L-53-ST | 1 | 2025-08-12 | 2025-08-14 | 2025-06-16 | 2025-07-13
| JD3RZ06L53ST22466 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z06-L-53-ST | 1 | 2025-08-25 | 2025-08-27 | 2025-06-18 | 2025-07-15
| JD3RZ06L53ST22466.R | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z06-L-53-ST -Remaining | 1 | 2025-09-01 | 2025-09-02
| JD3RZ06L53ST22467 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z06-L-53-ST | 1 | 2025-09-03 | 2025-09-04
| JD3RZ06L53ST22468 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z06-L-53-ST | 1 | 2025-09-06 | 2025-09-07
| JD3RZ06L53ST22479 | Excavation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z06-L-53-ST | 1 | 2025-08-27 | 2025-08-28 | 2025-08-22
| JD3RZ06L53ST22480 | Base Plain Concrete Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z06-L-53-ST | 1 | 2025-08-30 | 2025-08-31 | 2025-08-25
| JD3RZ06L53ST22481 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z06-L-53-ST | 1 | 2025-09-03 | 2025-09-04
| JD3RZ06L53ST22482 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z06-L-53-ST | 1 | 2025-09-06 | 2025-09-07
| JD3RZ06L53ST22483 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z06-L-53-ST | 1 | 2025-09-08 | 2025-09-09
| JD3RZ06L53ST22484 | EXCAVATION Works for Catchbasine single - - B6.33 05 39.09-Z06-L-53-ST | 1 | 2025-08-30 | 2025-08-31
| JD3RZ06L53ST22485 | Catchbasine Installation Works For Catchbasine single - - B6.33 05 39.09-Z06-L-53-ST | 1 | 2025-09-01 | 2025-09-03
| JD3RZ06L53ST22486 | FINISHING Works For Catchbasine single - - B6.33 05 39.09-Z06-L-53-ST | 1 | 2025-09-04 | 2025-09-07
| JD3RZ06L53ST22487 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - - B6.33 05 39.09-Z06-L-53-ST | 1 | 2025-09-08 | 2025-09-09
| JD3RZ06L53ST22488 | EXCAVATION Works for Catchbasine double - - B6.33 05 39.10-Z06-L-53-ST | 1 | 2025-09-01 | 2025-09-02
| JD3RZ06L53ST22489 | Catchbasine Installation Works For Catchbasine double - - B6.33 05 39.10-Z06-L-53-ST | 1 | 2025-09-03 | 2025-09-06
| JD3RZ06L53ST22490 | FINISHING Works For Catchbasine double - - B6.33 05 39.10-Z06-L-53-ST | 1 | 2025-09-07 | 2025-09-09
| JD3RZ06L53ST22491 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - - B6.33 05 39.10-Z06-L-53-ST | 1 | 2025-09-10 | 2025-09-11
| JD3RZ06L53ST524358 | Concrete encasement for pipes- NNB6.33 42 11.25-Z06-L-53-ST | 1 | 2025-08-27 | 2025-09-02
| JD3RZ06L53TSE22542 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z06-L-53-TSE | 1 | 2025-09-13 | 2025-09-16
| JD3RZ06L53TSE22543 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z06-L-53-TSE | 1 | 2025-09-17 | 2025-09-21
| JD3RZ06L53TSE22544 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z06-L-53-TSE | 1 | 2025-09-22 | 2025-09-29
| JD3RZ06L53TSE22545 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z06-L-53-TSE | 1 | 2025-09-30 | 2025-10-05
| JD3RZ06L53TSE22547 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z06-L-53-TSE | 1 | 2025-09-17 | 2025-09-18
| JD3RZ06L53TSE22548 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z06-L-53-TSE | 1 | 2025-09-20 | 2025-09-21
| JD3RZ06L53TSE22549 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z06-L-53-TSE | 1 | 2025-09-22 | 2025-09-23
| JD3RZ06L53TSE22550 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z06-L-53-TSE | 1 | 2025-09-24 | 2025-09-25
| JD3RZ06L53TSE22667 | Installationfor gate valves 100 mm - - B4.33 14 19.01-Z06-L-53-TSE | 1 | 2025-09-30 | 2025-10-01
| JD3RZ06L53TSE22669 | Installationfor gate valves 250 mm - - B4.33 14 19.02-Z06-L-53-TSE | 1 | 2025-09-30 | 2025-10-01
| JD3RZ06L54ST22979 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z06-L-54-ST | 1 | 2025-08-18 | 2025-08-20
| JD3RZ06L54ST22980 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z06-L-54-ST | 1 | 2025-08-21 | 2025-08-24
| JD3RZ06L54ST22981 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z06-L-54-ST | 1 | 2025-08-25 | 2025-08-28
| JD3RZ06L54ST22982 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z06-L-54-ST | 1 | 2025-08-30 | 2025-09-02
| JD3RZ06L54ST22983 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z06-L-54-ST | 1 | 2025-09-18 | 2025-09-23
| JD3RZ06L54ST22984 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z06-L-54-ST | 1 | 2025-08-21 | 2025-08-23 | 2025-08-02 | 2025-08-03
| JD3RZ06L54ST22985 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z06-L-54-ST | 1 | 2025-08-24 | 2025-08-25 | 2025-08-05 | 2025-08-06
| JD3RZ06L54ST22986 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z06-L-54-ST | 1 | 2025-08-26 | 2025-08-27 | 2025-08-07 | 2025-08-09
| JD3RZ06L54ST22987 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z06-L-54-ST | 1 | 2025-08-28 | 2025-08-30 | 2025-09-03 | 2025-09-09
| JD3RZ06L54ST22988 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z06-L-54-ST | 1 | 2025-08-31 | 2025-09-01
| JD3RZ06L54ST22989 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z06-L-54-ST | 1 | 2025-08-24 | 2025-08-25 | 2025-08-16
| JD3RZ06L54ST22990 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z06-L-54-ST | 1 | 2025-08-26 | 2025-08-27 | 2025-08-18
| JD3RZ06L54ST22991 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z06-L-54-ST | 1 | 2025-08-28 | 2025-08-30 | 2025-08-21
| JD3RZ06L54ST22992 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z06-L-54-ST | 1 | 2025-08-31 | 2025-09-01 | 2025-09-06
| JD3RZ06L54ST22993 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z06-L-54-ST | 1 | 2025-09-07 | 2025-09-08
| JD3RZ06L54ST23019 | Excavation Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z06-L-54-ST | 1 | 2025-08-18 | 2025-08-19 | 2025-04-20 | 2025-05-07
| JD3RZ06L54ST23019.R | Excavation Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z06-L-54-ST -Remaining | 1 | 2025-08-26 | 2025-08-27 | 2025-08-07 | 2025-08-09
| JD3RZ06L54ST23020 | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z06-L-54-ST | 1 | 2025-08-20 | 2025-08-21 | 2025-04-21 | 2025-05-08
| JD3RZ06L54ST23020.R | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z06-L-54-ST -Rem | 1 | 2025-08-28 | 2025-08-30 | 2025-08-09 | 2025-08-10
| JD3RZ06L54ST23021 | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z06-L-54-ST | 1 | 2025-08-23 | 2025-08-24 | 2025-04-22 | 2025-05-10
| JD3RZ06L54ST23021.R | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z06-L-54-ST -Remaining | 1 | 2025-08-31 | 2025-09-01 | 2025-08-12 | 2025-08-13
| JD3RZ06L54ST23022 | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z06-L-54-ST | 1 | 2025-08-25 | 2025-08-26 | 2025-07-06 | 2025-07-23
| JD3RZ06L54ST23022.R | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z06-L-54-ST -Remaining | 1 | 2025-09-02 | 2025-09-03 | 2025-09-03 | 2025-09-09
| JD3RZ06L54ST23023 | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z06-L-54-ST | 1 | 2025-08-27 | 2025-08-28 | 2025-07-08 | 2025-07-30
| JD3RZ06L54ST23023.R | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z06-L-54-ST -Remaining | 1 | 2025-09-04 | 2025-09-06
| JD3RZ06L54ST23029 | Excavation Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-54-ST | 1 | 2025-08-20 | 2025-08-23 | 2025-04-21 | 2025-05-18
| JD3RZ06L54ST23029.R | Excavation Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-54-ST -Remaining | 1 | 2025-08-28 | 2025-08-30 | 2025-08-09 | 2025-08-10
| JD3RZ06L54ST23030 | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-54-ST | 1 | 2025-08-24 | 2025-08-26 | 2025-05-11 | 2025-06-07
| JD3RZ06L54ST23030.R | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-54-ST -Rem | 1 | 2025-08-31 | 2025-09-01 | 2025-08-12 | 2025-08-13
| JD3RZ06L54ST23031 | Installing for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-54-ST | 1 | 2025-08-27 | 2025-08-30 | 2025-05-12 | 2025-06-17
| JD3RZ06L54ST23031.R | Installing for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-54-ST -Remaining | 1 | 2025-09-02 | 2025-09-03 | 2025-08-14 | 2025-08-16
| JD3RZ06L54ST23032 | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-54-ST | 1 | 2025-08-31 | 2025-09-02 | 2025-06-18 | 2025-07-24
| JD3RZ06L54ST23032.R | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-54-ST -Remaining | 1 | 2025-09-04 | 2025-09-06 | 2025-08-23 | 2025-09-10
| JD3RZ06L54ST23033 | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-54-ST | 1 | 2025-09-03 | 2025-09-07 | 2025-07-08 | 2025-07-31
| JD3RZ06L54ST23033.R | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-54-ST -Remaining | 1 | 2025-09-08 | 2025-09-09
| JD3RZ06L54ST23039 | Excavation Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z06-L-54-ST | 1 | 2025-08-18 | 2025-08-21 | 2025-06-09 | 2025-07-15
| JD3RZ06L54ST23040 | Soil Replacement and Bedding Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z06-L-54-ST | 1 | 2025-08-23 | 2025-08-26 | 2025-06-11 | 2025-07-17
| JD3RZ06L54ST23041 | Installing for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z06-L-54-ST | 1 | 2025-08-27 | 2025-09-01 | 2025-06-12 | 2025-07-31
| JD3RZ06L54ST23041.R | Installing for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z06-L-54-ST -Remaining | 1 | 2025-09-02 | 2025-09-03 | 2025-08-12 | 2025-08-13
| JD3RZ06L54ST23042 | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z06-L-54-ST | 1 | 2025-09-02 | 2025-09-06 | 2025-06-18 | 2025-07-31
| JD3RZ06L54ST23042.R | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z06-L-54-ST -Remaining | 1 | 2025-09-07 | 2025-09-08 | 2025-08-14 | 2025-08-16
| JD3RZ06L54ST23043 | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z06-L-54-ST | 1 | 2025-09-07 | 2025-09-13 | 2025-07-08 | 2025-07-31
| JD3RZ06L54ST23043.R | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z06-L-54-ST -Remaining | 1 | 2025-09-14 | 2025-09-15
| JD3RZ06L54ST23044 | Excavation Works for GRP Pipe Line 900 mm - depth from 2.51 to 3.50 m- B6.33 42 11.13-Z06-L-54-ST | 1 | 2025-09-02 | 2025-09-03 | 2025-06-25 | 2025-07-13
| JD3RZ06L54ST23045 | Soil Replacement and Bedding Works for GRP Pipe Line 900 mm - depth from 2.51 to 3.50 m- B6.33 42 11.13-Z06-L-54-ST | 1 | 2025-09-04 | 2025-09-06 | 2025-06-28 | 2025-07-15
| JD3RZ06L54ST23046 | Installing for GRP Pipe Line 900 mm - depth from 2.51 to 3.50 m- B6.33 42 11.13-Z06-L-54-ST | 1 | 2025-09-07 | 2025-09-08 | 2025-06-30 | 2025-07-17
| JD3RZ06L54ST23047 | Primary Test for GRP Pipe Line 900 mm - depth from 2.51 to 3.50 m- B6.33 42 11.13-Z06-L-54-ST | 1 | 2025-09-09 | 2025-09-10 | 2025-07-03 | 2025-07-21
| JD3RZ06L54ST23048 | Backfilling Works for GRP Pipe Line 900 mm - depth from 2.51 to 3.50 m- B6.33 42 11.13-Z06-L-54-ST | 1 | 2025-09-11 | 2025-09-13 | 2025-07-06 | 2025-07-23
| JD3RZ06L54ST23048.R | Backfilling Works for GRP Pipe Line 900 mm - depth from 2.51 to 3.50 m- B6.33 42 11.13-Z06-L-54-ST -Remaining | 1 | 2025-09-16 | 2025-09-17
| JD3RZ06L54ST23162 | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z06-L-54-ST | 1 | 2025-08-26 | 2025-08-27 | 2025-08-22 | 2025-08-24
| JD3RZ06L54ST23163 | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z06-L-54-ST | 1 | 2025-08-28 | 2025-08-30 | 2025-08-25 | 2025-08-26
| JD3RZ06L54ST23164 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z06-L-54-ST | 1 | 2025-08-31 | 2025-09-01
| JD3RZ06L54ST23165 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z06-L-54-ST | 1 | 2025-09-02 | 2025-09-03
| JD3RZ06L54ST23166 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z06-L-54-ST | 1 | 2025-09-04 | 2025-09-06
| JD3RZ06L54ST23172 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z06-L-54-ST | 1 | 2025-08-18 | 2025-08-19 | 2025-05-26 | 2025-06-12
| JD3RZ06L54ST23173 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z06-L-54-ST | 1 | 2025-08-20 | 2025-08-21 | 2025-05-29 | 2025-06-25
| JD3RZ06L54ST23174 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z06-L-54-ST | 1 | 2025-09-04 | 2025-09-06 | 2025-06-03 | 2025-06-30
| JD3RZ06L54ST23174.R | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z06-L-54-ST -Remaining | 1 | 2025-09-07 | 2025-09-08
| JD3RZ06L54ST23175 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z06-L-54-ST | 1 | 2025-09-09 | 2025-09-10
| JD3RZ06L54ST23176 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z06-L-54-ST | 1 | 2025-09-11 | 2025-09-13
| JD3RZ06L54ST23177 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z06-L-54-ST | 1 | 2025-08-28 | 2025-08-30 | 2025-08-22 | 2025-08-24
| JD3RZ06L54ST23178 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z06-L-54-ST | 1 | 2025-08-31 | 2025-09-02 | 2025-08-02 | 2025-08-04
| JD3RZ06L54ST23179 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z06-L-54-ST | 1 | 2025-09-03 | 2025-09-06
| JD3RZ06L54ST23180 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z06-L-54-ST | 1 | 2025-09-07 | 2025-09-08
| JD3RZ06L54ST23181 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z06-L-54-ST | 1 | 2025-09-14 | 2025-09-15
| JD3RZ06L54ST23197 | EXCAVATION Works for Catchbasine single - - B6.33 05 39.09-Z06-L-54-ST | 1 | 2025-08-31 | 2025-09-01
| JD3RZ06L54ST23198 | Catchbasine Installation Works For Catchbasine single - - B6.33 05 39.09-Z06-L-54-ST | 1 | 2025-09-02 | 2025-09-04
| JD3RZ06L54ST23199 | FINISHING Works For Catchbasine single - - B6.33 05 39.09-Z06-L-54-ST | 1 | 2025-09-06 | 2025-09-08
| JD3RZ06L54ST23200 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - - B6.33 05 39.09-Z06-L-54-ST | 1 | 2025-09-09 | 2025-09-10
| JD3RZ06L54ST23201 | EXCAVATION Works for Catchbasine double - - B6.33 05 39.10-Z06-L-54-ST | 1 | 2025-09-02 | 2025-09-03
| JD3RZ06L54ST23202 | Catchbasine Installation Works For Catchbasine double - - B6.33 05 39.10-Z06-L-54-ST | 1 | 2025-09-04 | 2025-09-07
| JD3RZ06L54ST23203 | FINISHING Works For Catchbasine double - - B6.33 05 39.10-Z06-L-54-ST | 1 | 2025-09-08 | 2025-09-10
| JD3RZ06L54ST23204 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - - B6.33 05 39.10-Z06-L-54-ST | 1 | 2025-09-16 | 2025-09-17
| JD3RZ06L54ST524351 | Concrete encasement for pipes- NNB6.33 42 11.25-Z06-L-54-ST | 1 | 2025-08-31 | 2025-09-06
| JD3RZ06L54TSE23255 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z06-L-54-TSE | 1 | 2025-09-24 | 2025-09-29
| JD3RZ06L54TSE23256 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z06-L-54-TSE | 1 | 2025-09-30 | 2025-10-05
| JD3RZ06L54TSE23260 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z06-L-54-TSE | 1 | 2025-09-24 | 2025-09-25
| JD3RZ06L54TSE23261 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z06-L-54-TSE | 1 | 2025-09-27 | 2025-09-28
| JD3RZ06L54TSE23262 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z06-L-54-TSE | 1 | 2025-09-29 | 2025-09-30
| JD3RZ06L55ST23732 | Excavation Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z06-L-55-ST | 1 | 2025-08-26 | 2025-08-27 | 2025-03-03 | 2025-03-20
| JD3RZ06L55ST23733 | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z06-L-55-ST | 1 | 2025-08-28 | 2025-08-30 | 2025-03-04 | 2025-03-22
| JD3RZ06L55ST23734 | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z06-L-55-ST | 1 | 2025-08-31 | 2025-09-01 | 2025-03-05 | 2025-03-23
| JD3RZ06L55ST23735 | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z06-L-55-ST | 1 | 2025-09-02 | 2025-09-03 | 2025-05-13 | 2025-05-31
| JD3RZ06L55ST23736 | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z06-L-55-ST | 1 | 2025-09-04 | 2025-09-06 | 2025-07-05 | 2025-07-31
| JD3RZ06L55ST23742 | Excavation Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-55-ST | 1 | 2025-08-26 | 2025-08-30 | 2025-03-10 | 2025-04-15
| JD3RZ06L55ST23743 | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-55-ST | 1 | 2025-08-31 | 2025-09-03 | 2025-03-11 | 2025-04-16
| JD3RZ06L55ST23744 | Installing for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-55-ST | 1 | 2025-09-04 | 2025-09-09 | 2025-03-12 | 2025-04-27
| JD3RZ06L55ST23745 | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-55-ST | 1 | 2025-09-10 | 2025-09-14 | 2025-05-13 | 2025-06-28
| JD3RZ06L55ST23746 | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-55-ST | 1 | 2025-09-15 | 2025-09-21 | 2025-07-05 | 2025-07-31
| JD3RZ06L55ST23752 | Excavation Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z06-L-55-ST | 1 | 2025-08-26 | 2025-08-28 | 2025-03-10 | 2025-04-15
| JD3RZ06L55ST23753 | Soil Replacement and Bedding Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z06-L-55-ST | 1 | 2025-08-30 | 2025-09-01 | 2025-03-11 | 2025-04-16
| JD3RZ06L55ST23754 | Installing for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z06-L-55-ST | 1 | 2025-09-02 | 2025-09-06 | 2025-04-03 | 2025-05-19
| JD3RZ06L55ST23755 | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z06-L-55-ST | 1 | 2025-09-07 | 2025-09-09 | 2025-04-06 | 2025-05-21
| JD3RZ06L55ST23756 | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z06-L-55-ST | 1 | 2025-09-22 | 2025-09-27 | 2025-04-23 | 2025-06-17
| JD3RZ06L55ST23782 | Excavation Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z06-L-55-ST | 1 | 2025-08-26 | 2025-08-27 | 2025-06-09 | 2025-06-26
| JD3RZ06L55ST23783 | Soil Replacement and Bedding Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z06-L-55-ST | 1 | 2025-08-28 | 2025-08-30 | 2025-06-14 | 2025-07-01
| JD3RZ06L55ST23784 | Installing for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z06-L-55-ST | 1 | 2025-08-31 | 2025-09-01 | 2025-06-19 | 2025-07-07
| JD3RZ06L55ST23875 | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z06-L-55-ST | 1 | 2025-08-26 | 2025-08-27 | 2025-05-25 | 2025-06-11
| JD3RZ06L55ST23876 | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z06-L-55-ST | 1 | 2025-08-28 | 2025-08-30 | 2025-05-28 | 2025-06-15
| JD3RZ06L55ST23877 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z06-L-55-ST | 1 | 2025-09-28 | 2025-09-29 | 2025-06-01 | 2025-06-18
| JD3RZ06L55ST23885 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z06-L-55-ST | 1 | 2025-08-26 | 2025-08-27 | 2025-05-25 | 2025-06-11
| JD3RZ06L55ST23886 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z06-L-55-ST | 1 | 2025-08-28 | 2025-08-30 | 2025-05-28 | 2025-06-15
| JD3RZ06L55ST23887 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z06-L-55-ST | 1 | 2025-09-30 | 2025-10-01 | 2025-06-01 | 2025-06-18
| JD3RZ06L55ST23890 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z06-L-55-ST | 1 | 2025-08-26 | 2025-08-27 | 2025-05-25 | 2025-06-11
| JD3RZ06L55ST23891 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z06-L-55-ST | 1 | 2025-08-28 | 2025-08-31 | 2025-05-28 | 2025-06-24
| JD3RZ06L56ST24415 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z06-L-56-ST | 1 | 2025-09-03 | 2025-09-06 | 2025-06-16 | 2025-07-13
| JD3RZ06L56ST24416 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z06-L-56-ST | 1 | 2025-09-07 | 2025-09-09 | 2025-06-19 | 2025-07-26
| JD3RZ06L56ST24417 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z06-L-56-ST | 1 | 2025-09-10 | 2025-09-14 | 2025-06-30 | 2025-07-31
| JD3RZ06L56ST24418 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z06-L-56-ST | 1 | 2025-09-15 | 2025-09-17 | 2025-07-05 | 2025-07-31
| JD3RZ06L56ST24425 | Excavation Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z06-L-56-ST | 1 | 2025-09-07 | 2025-09-10 | 2025-04-22 | 2025-05-10
| JD3RZ06L56ST24426 | Soil Replacement and Bedding Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z06-L-56-ST | 1 | 2025-09-11 | 2025-09-15 | 2025-04-23 | 2025-05-11
| JD3RZ06L56ST24427 | Installing for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z06-L-56-ST | 1 | 2025-09-16 | 2025-09-21 | 2025-04-24 | 2025-05-12
| JD3RZ06L56ST24428 | Primary Test for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z06-L-56-ST | 1 | 2025-09-22 | 2025-09-25 | 2025-07-05 | 2025-07-22
| JD3RZ06L56ST24429 | Backfilling Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z06-L-56-ST | 1 | 2025-09-27 | 2025-10-02 | 2025-06-21 | 2025-07-08
| JD3RZ06L56ST24435 | Excavation Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z06-L-56-ST | 1 | 2025-09-11 | 2025-09-14 | 2025-06-16 | 2025-07-13
| JD3RZ06L56ST24436 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z06-L-56-ST | 1 | 2025-09-15 | 2025-09-17 | 2025-06-19 | 2025-07-16
| JD3RZ06L56ST24437 | Installing for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z06-L-56-ST | 1 | 2025-09-18 | 2025-09-21 | 2025-06-21 | 2025-07-27
| JD3RZ06L56ST24445 | Excavation Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z06-L-56-ST | 1 | 2025-09-15 | 2025-09-16 | 2025-06-16 | 2025-07-03
| JD3RZ06L56ST24446 | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z06-L-56-ST | 1 | 2025-09-17 | 2025-09-18 | 2025-06-19 | 2025-07-16
| JD3RZ06L56ST24447 | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z06-L-56-ST | 1 | 2025-09-20 | 2025-09-22 | 2025-06-21 | 2025-07-17
| JD3RZ06L56ST24455 | Excavation Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-56-ST | 1 | 2025-09-17 | 2025-09-18 | 2025-02-11 | 2025-03-01
| JD3RZ06L56ST24456 | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-56-ST | 1 | 2025-09-20 | 2025-09-21 | 2025-02-12 | 2025-03-02
| JD3RZ06L56ST24457 | Installing for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-56-ST | 1 | 2025-09-22 | 2025-09-23 | 2025-07-01 | 2025-07-28
| JD3RZ06L56ST24465 | Excavation Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z06-L-56-ST | 1 | 2025-09-20 | 2025-09-27 | 2025-01-28 | 2025-03-24
| JD3RZ06L56ST24466 | Soil Replacement and Bedding Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z06-L-56-ST | 1 | 2025-09-28 | 2025-10-05 | 2025-02-04 | 2025-04-09
| JD3RZ06L56ST24534 | Excavation Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - - B6.34 42 16.03-Z06-L-56-ST | 1 | 2025-09-28 | 2025-09-30 | 2025-01-05 | 2025-02-01
| JD3RZ06L56ST24541 | Excavation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-Z06-L-56-ST | 1 | 2025-09-03 | 2025-09-04 | 2024-11-26 | 2024-12-14
| JD3RZ06L57ST25128 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z06-L-57-ST | 1 | 2025-09-11 | 2025-09-13 | 2025-06-09 | 2025-06-26
| JD3RZ06L57ST25129 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z06-L-57-ST | 1 | 2025-09-14 | 2025-09-15 | 2025-06-15 | 2025-07-02
| JD3RZ06L57ST25130 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z06-L-57-ST | 1 | 2025-09-16 | 2025-09-17 | 2025-06-21 | 2025-07-17
| JD3RZ06L57ST25133 | Excavation Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z06-L-57-ST | 1 | 2025-09-11 | 2025-09-13 | 2025-04-05 | 2025-04-22
| JD3RZ06L57ST25134 | Soil Replacement and Bedding Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z06-L-57-ST | 1 | 2025-09-14 | 2025-09-15 | 2025-04-07 | 2025-04-24
| JD3RZ06L57ST25135 | Installing for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z06-L-57-ST | 1 | 2025-09-16 | 2025-09-17 | 2025-04-09 | 2025-04-27
| JD3RZ06L57ST25136 | Primary Test for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z06-L-57-ST | 1 | 2025-09-18 | 2025-09-20 | 2025-04-15 | 2025-05-03
| JD3RZ06L57ST25137 | Backfilling Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z06-L-57-ST | 1 | 2025-09-14 | 2025-09-15 | 2025-04-20 | 2025-05-07
| JD3RZ06L57ST25148 | Excavation Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z06-L-57-ST | 1 | 2025-09-11 | 2025-09-13 | 2025-06-09 | 2025-06-26
| JD3RZ06L57ST25149 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z06-L-57-ST | 1 | 2025-09-14 | 2025-09-15 | 2025-06-15 | 2025-07-02
| JD3RZ06L57ST25150 | Installing for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z06-L-57-ST | 1 | 2025-09-16 | 2025-09-17 | 2025-06-21 | 2025-07-08
| JD3RZ06L57ST25158 | Excavation Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z06-L-57-ST | 1 | 2025-09-11 | 2025-09-13 | 2025-06-09 | 2025-06-26
| JD3RZ06L57ST25159 | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z06-L-57-ST | 1 | 2025-09-14 | 2025-09-15 | 2025-06-15 | 2025-07-02
| JD3RZ06L57ST25160 | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z06-L-57-ST | 1 | 2025-09-16 | 2025-09-17 | 2025-06-21 | 2025-07-08
| JD3RZ06L57ST25168 | Excavation Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-57-ST | 1 | 2025-09-16 | 2025-09-17 | 2025-06-09 | 2025-06-26
| JD3RZ06L57ST25169 | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-57-ST | 1 | 2025-09-18 | 2025-09-20 | 2025-06-15 | 2025-07-02
| JD3RZ06L57ST25170 | Installing for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z06-L-57-ST | 1 | 2025-09-21 | 2025-09-22 | 2025-06-21 | 2025-07-08
| JD3RZ06L57ST25247 | Excavation Works for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - - B6.34 42 16.03-Z06-L-57-ST | 1 | 2025-09-11 | 2025-09-13 | 2024-11-27 | 2025-01-02
| JD3RZ06L57ST25248 | Plain Concrete Works For Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - - B6.34 42 16.03-Z06-L-57-ST | 1 | 2025-09-14 | 2025-09-15 | 2025-05-24 | 2025-07-31
| JD3RZ06L57ST25249 | Raft Foundation for Box Culvert Dim (2000x1250) depth from 1.51 to 2.50 - - B6.34 42 16.03-Z06-L-57-ST | 1 | 2025-09-16 | 2025-09-23 | 2025-05-26 | 2025-07-31
| JD3RZ06L57ST25250 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.34 42 16.03-Z06-L-57-ST | 1 | 2025-09-24 | 2025-10-05 | 2025-05-29 | 2025-07-31
| JD3RZ06L57ST25311 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z06-L-57-ST | 1 | 2025-09-11 | 2025-09-13 | 2025-06-09 | 2025-06-26
| JD3RZ06L57ST25312 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z06-L-57-ST | 1 | 2025-09-14 | 2025-09-15 | 2025-06-15 | 2025-07-02
| JD3RZ07-1L59SL32030 | Excavation Worksfor Copper Cables 4Cx16 mm² - - B2.26 05 19.03-Z07-1-L-59-SL | 1 | 2024-12-29 | 2024-12-31
| JD3RZ07-1L59SL32031 | Installationfor Copper Cables 4Cx16 mm² - - B2.26 05 19.03-Z07-1-L-59-SL | 1 | 2025-01-01 | 2025-01-04
| JD3RZ07-1L59SL32032 | Backfilling, Warning Tabe Worksfor Copper Cables 4Cx16 mm² - - B2.26 05 19.03-Z07-1-L-59-SL | 1 | 2025-01-05 | 2025-01-07
| JD3RZ07-1L59SL32033 | Testing and Commitioning for Copper Cables 4Cx16 mm² - - B2.26 05 19.03-Z07-1-L-59-SL | 1 | 2025-01-12 | 2025-01-14
| JD3RZ07-1L59SL32046 | INSTALLINGfor insulated copper conductor 6 mm² - - B2.26 05 19.07-Z07-1-L-59-SL | 1 | 2025-01-05 | 2025-01-07
| JD3RZ07-1L59SL32047 | TESTING AND COMMITIONINGfor insulated copper conductor 6 mm² - - B2.26 05 19.07-Z07-1-L-59-SL | 1 | 2025-01-08 | 2025-01-11
| JD3RZ07-1L59SL32055 | Excavation of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z07-1-L-59-SL | 1 | 2025-01-01 | 2025-01-02
| JD3RZ07-1L59SL32056 | Installation of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z07-1-L-59-SL | 1 | 2025-01-04 | 2025-01-06
| JD3RZ07-1L59SL32057 | Backfilling of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z07-1-L-59-SL | 1 | 2025-01-07 | 2025-01-08
| JD3RZ07-1L59SL32058 | Installation Worksfor LIGHTING POLE one arm - - B2.26 56 19.02-Z07-1-L-59-SL | 1 | 2025-01-09 | 2025-01-14
| JD3RZ07-1L59SL32059 | Testing and Commitioningfor LIGHTING POLE one arm - - B2.26 56 19.02-Z07-1-L-59-SL | 1 | 2025-01-15 | 2025-01-20
| JD3RZ07-1L59SL32060 | Installationfor Lighting( LED ) Luminaire 150 WATT - - B2.26.56.19.01-Z07-1-L-59-SL | 1 | 2025-01-07 | 2025-01-08
| JD3RZ07-1L59SL32063 | Supply, construct, connect and test earthing pitsfor Street Lighting EARTHING SYSTEM - - B2.26 05 26.01-Z07-1-L-59-SL | 1 | 2025-01-09 | 2025-01-11
| JD3RZ07-1L59SL32064 | Excavation Worksfor PVC Pipes 2×150mm - - B2.33 71 19.01.SL-Z07-1-L-59-SL | 1 | 2025-01-04 | 2025-01-05
| JD3RZ07-1L59SL32065 | Installationfor PVC Pipes 2×150mm - - B2.33 71 19.01.SL-Z07-1-L-59-SL | 1 | 2025-01-06 | 2025-01-07
| JD3RZ07-1L59SL32066 | Pouring Concrete Coverfor PVC Pipes 2×150mm - - B2.33 71 19.01.SL-Z07-1-L-59-SL | 1 | 2025-01-08 | 2025-01-09
| JD3RZ07-1L59SL32067 | Testing and Backfilling Worksfor PVC Pipes 2×150mm - - B2.33 71 19.01.SL-Z07-1-L-59-SL | 1 | 2025-01-11 | 2025-01-12
| JD3RZ07-1L59SL32076 | Excavationfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z07-1-L-59-SL | 1 | 2025-01-06 | 2025-01-07
| JD3RZ07-1L59SL32077 | Installationfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z07-1-L-59-SL | 1 | 2025-01-08 | 2025-01-11
| JD3RZ07-1L59SL32078 | Backfillingfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z07-1-L-59-SL | 1 | 2025-01-12 | 2025-01-13
| JD3RZ07-1L59SL32079 | Excavationfor Drawpit 900x900x1200mm - - B2.33 71 19.13.02-Z07-1-L-59-SL | 1 | 2025-01-08 | 2025-01-09
| JD3RZ07-1L59SL32080 | Installationfor Drawpit 900x900x1200mm - - B2.33 71 19.13.02-Z07-1-L-59-SL | 1 | 2025-01-11 | 2025-01-12
| JD3RZ07-1L59SL32081 | Backfillingfor Drawpit 900x900x1200mm - - B2.33 71 19.13.02-Z07-1-L-59-SL | 1 | 2025-01-13 | 2025-01-14
| JD3RZ07-1L59SS31404 | Trench excavation for GRP Pipe Line 200 mm - depth from 0.00 to 1.50- B5.33 31 00.03-Z07-1-L-59-SS | 1 | 2024-09-04 | 2024-09-05 | 2024-11-26 | 2025-01-01
| JD3RZ07-1L59SS31405 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - depth from 0.00 to 1.50- B5.33 31 00.03-Z07-1-L-59-SS | 1 | 2024-09-08 | 2024-09-09 | 2025-01-01 | 2025-02-16
| JD3RZ07-1L59SS31406 | Installing for GRP Pipe Line 200 mm - depth from 0.00 to 1.50- B5.33 31 00.03-Z07-1-L-59-SS | 1 | 2024-09-18 | 2024-09-19 | 2025-01-02 | 2025-02-08
| JD3RZ07-1L59SS31407 | Primary Test for GRP Pipe Line 200 mm - depth from 0.00 to 1.50- B5.33 31 00.03-Z07-1-L-59-SS | 1 | 2024-09-28 | 2024-09-29 | 2025-01-12 | 2025-02-17
| JD3RZ07-1L59SS31408 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - depth from 0.00 to 1.50- B5.33 31 00.03-Z07-1-L-59-SS | 1 | 2024-09-30 | 2024-10-01 | 2025-01-20 | 2025-03-25
| JD3RZ07-1L59SS31408.R | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - depth from 0.00 to 1.50- B5.33 31 00.03-Z07-1-L-59-SS -Rem | 1 | 2024-10-02 | 2024-10-03 | 2025-08-04 | 2025-08-05
| JD3RZ07-1L59SS31409 | Trench excavation for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z07-1-L-59-SS | 1 | 2024-09-04 | 2024-09-10 | 2024-12-16 | 2025-02-27
| JD3RZ07-1L59SS31410 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z07-1-L-59-SS | 1 | 2024-09-11 | 2024-09-17 | 2025-01-01 | 2025-03-16
| JD3RZ07-1L59SS31411 | Installing for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z07-1-L-59-SS | 1 | 2024-09-18 | 2024-09-26 | 2025-01-01 | 2025-04-03
| JD3RZ07-1L59SS31412 | Primary Test for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z07-1-L-59-SS | 1 | 2024-09-28 | 2024-10-03 | 2025-01-08 | 2025-04-10
| JD3RZ07-1L59SS31413 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z07-1-L-59-SS | 1 | 2024-09-04 | 2024-09-14 | 2025-01-16 | 2025-06-04
| JD3RZ07-1L59SS31413.R | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z07-1-L-59-SS -Rem | 1 | 2024-09-15 | 2024-09-16 | 2025-08-02 | 2025-08-03
| JD3RZ07-1L59SS31414 | Trench excavation for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z07-1-L-59-SS | 1 | 2024-09-04 | 2024-09-07 | 2024-11-26 | 2025-01-01
| JD3RZ07-1L59SS31415 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z07-1-L-59-SS | 1 | 2024-09-08 | 2024-09-10 | 2024-12-16 | 2025-01-30
| JD3RZ07-1L59SS31416 | Installing for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z07-1-L-59-SS | 1 | 2024-09-11 | 2024-09-14 | 2024-12-18 | 2025-01-23
| JD3RZ07-1L59SS31417 | Primary Test for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z07-1-L-59-SS | 1 | 2024-09-15 | 2024-09-17 | 2025-01-01 | 2025-02-06
| JD3RZ07-1L59SS31418 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z07-1-L-59-SS | 1 | 2024-10-02 | 2024-10-06 | 2025-02-12 | 2025-04-08
| JD3RZ07-1L59SS31418.R | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z07-1-L-59-SS -Rem | 1 | 2024-10-07 | 2024-10-08 | 2025-09-16 | 2025-09-20
| JD3RZ07-1L59SS31451 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z07-1-L-59-SS | 1 | 2024-09-04 | 2024-09-05 | 2024-12-31 | 2025-01-27
| JD3RZ07-1L59SS31452 | Installation of Base Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z07-1-L-59-SS | 1 | 2024-09-07 | 2024-09-08 | 2025-01-01 | 2025-02-25
| JD3RZ07-1L59SS31453 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z07-1-L | 1 | 2024-09-09 | 2024-09-10 | 2025-01-16 | 2025-03-12
| JD3RZ07-1L59SS31454 | Backfilling Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z07-1-L-59-SS | 1 | 2024-09-11 | 2024-09-12 | 2025-05-01 | 2025-06-08
| JD3RZ07-1L59SS31455 | Finishing, Benching Works for Manholes 1200 mm - Depth from 1.51 to 2.50- B5.33 05 13.03-Z07-1-L-59-SS | 1 | 2024-09-11 | 2024-09-12 | 2025-05-06 | 2025-06-11
| JD3RZ07-1L59SS31463 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z07-1-L-59-SS | 1 | 2024-09-04 | 2024-09-05 | 2024-12-05 | 2025-02-08
| JD3RZ07-1L59SS31463.R | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z07-1-L-59-SS -Remaining | 1 | 2024-09-07 | 2024-09-08 | 2025-08-02 | 2025-08-03
| JD3RZ07-1L59SS31464 | Installation of Base Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z07-1-L-59-SS | 1 | 2024-09-07 | 2024-09-11 | 2024-12-24 | 2025-05-21
| JD3RZ07-1L59SS31464.R | Installation of Base Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z07-1-L-59-SS -Remaining | 1 | 2024-09-12 | 2024-09-14 | 2025-08-04 | 2025-08-05
| JD3RZ07-1L59SS31465 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z07-1-L | 1 | 2024-09-12 | 2024-09-17 | 2025-02-25 | 2025-07-23
| JD3RZ07-1L59SS31465.R | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z07-1-L | 1 | 2024-09-18 | 2024-09-19 | 2025-08-06 | 2025-08-07
| JD3RZ07-1L59SS31466 | Backfilling Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z07-1-L-59-SS | 1 | 2024-09-18 | 2024-09-21 | 2025-03-01 | 2025-05-13
| JD3RZ07-1L59SS31466.R | Backfilling Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z07-1-L-59-SS -Remaining | 1 | 2024-09-22 | 2024-09-24 | 2025-08-09 | 2025-08-10
| JD3RZ07-1L59SS31467 | Finishing, Benching Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z07-1-L-59-SS | 1 | 2024-09-22 | 2024-09-24 | 2025-03-15 | 2025-05-18
| JD3RZ07-1L59SS31467.R | Finishing, Benching Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z07-1-L-59-SS -Remaining | 1 | 2024-09-25 | 2024-09-26 | 2025-08-11
| JD3RZ07-1L59SS521401 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2024-09-04 | 2024-09-05
| JD3RZ07-1L59SS521411 | Installation of Base Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2024-09-09 | 2024-09-10
| JD3RZ07-1L59SS521421 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03 | 1 | 2024-09-11 | 2024-09-12
| JD3RZ07-1L59SS521431 | Backfilling Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2024-09-14 | 2024-09-15
| JD3RZ07-1L59SS521441 | Finishing, Benching Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2024-09-16 | 2024-09-17
| JD3RZ07-1L59ST31535 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-1-L-59-ST | 1 | 2024-09-07 | 2024-09-09
| JD3RZ07-1L59ST31536 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-1-L-59-ST | 1 | 2024-09-10 | 2024-09-12
| JD3RZ07-1L59ST31537 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-1-L-59-ST | 1 | 2024-09-14 | 2024-09-17
| JD3RZ07-1L59ST31538 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-1-L-59-ST | 1 | 2024-09-28 | 2024-10-01
| JD3RZ07-1L59ST31539 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-1-L-59-ST | 1 | 2024-10-26 | 2024-10-30
| JD3RZ07-1L59ST31540 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-1-L-59-ST | 1 | 2024-09-15 | 2024-09-16 | 2025-04-15 | 2025-05-03
| JD3RZ07-1L59ST31540.R | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-1-L-59-ST -Remaining | 1 | 2024-09-18 | 2024-09-19
| JD3RZ07-1L59ST31541 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-1-L-59-ST | 1 | 2024-09-17 | 2024-09-18 | 2025-05-12 | 2025-05-29
| JD3RZ07-1L59ST31541.R | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-1-L-59-ST -R | 1 | 2024-09-21 | 2024-09-22
| JD3RZ07-1L59ST31542 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-1-L-59-ST | 1 | 2024-09-19 | 2024-09-22 | 2025-05-14 | 2025-06-01
| JD3RZ07-1L59ST31542.R | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-1-L-59-ST -Remaining | 1 | 2024-09-24 | 2024-09-25
| JD3RZ07-1L59ST31543 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-1-L-59-ST | 1 | 2024-09-24 | 2024-09-25 | 2025-05-19 | 2025-06-05
| JD3RZ07-1L59ST31543.R | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-1-L-59-ST -Remaining | 1 | 2024-09-26 | 2024-09-28 | 2025-08-30
| JD3RZ07-1L59ST31544 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-1-L-59-ST | 1 | 2024-09-26 | 2024-09-29 | 2025-06-19 | 2025-07-07
| JD3RZ07-1L59ST31544.R | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-1-L-59-ST -Remaining | 1 | 2024-09-30 | 2024-10-01 | 2025-09-07
| JD3RZ07-1L59ST31545 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-1-L-59-ST | 1 | 2024-10-09 | 2024-10-10
| JD3RZ07-1L59ST31546 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-1-L-59-ST | 1 | 2024-10-12 | 2024-10-13
| JD3RZ07-1L59ST31547 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-1-L-59-ST | 1 | 2024-10-14 | 2024-10-15
| JD3RZ07-1L59ST31548 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-1-L-59-ST | 1 | 2024-10-16 | 2024-10-17
| JD3RZ07-1L59ST31549 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-1-L-59-ST | 1 | 2024-10-26 | 2024-10-27
| JD3RZ07-1L59ST31550 | Excavation Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-1-L-59-ST | 1 | 2024-09-04 | 2024-09-05 | 2025-04-10 | 2025-04-28
| JD3RZ07-1L59ST31551 | Soil Replacement and Bedding Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-1-L-59-ST | 1 | 2024-09-07 | 2024-09-08 | 2025-04-13 | 2025-04-30
| JD3RZ07-1L59ST31552 | Installing for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-1-L-59-ST | 1 | 2024-09-09 | 2024-09-10 | 2025-04-14 | 2025-05-11
| JD3RZ07-1L59ST31553 | Primary Test for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-1-L-59-ST | 1 | 2024-09-11 | 2024-09-12 | 2025-04-15 | 2025-05-12
| JD3RZ07-1L59ST31554 | Backfilling Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-1-L-59-ST | 1 | 2024-09-14 | 2024-09-15 | 2025-04-26 | 2025-05-22
| JD3RZ07-1L59ST31555 | Excavation Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z07-1-L-59-ST | 1 | 2024-09-04 | 2024-09-05 | 2025-04-10 | 2025-04-28
| JD3RZ07-1L59ST31556 | Soil Replacement and Bedding Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z07-1-L-59-ST | 1 | 2024-09-07 | 2024-09-08 | 2025-04-13 | 2025-04-30
| JD3RZ07-1L59ST31557 | Installing for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z07-1-L-59-ST | 1 | 2024-09-09 | 2024-09-10 | 2025-04-14 | 2025-05-01
| JD3RZ07-1L59ST31558 | Primary Test for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z07-1-L-59-ST | 1 | 2024-09-11 | 2024-09-12 | 2025-05-13 | 2025-05-31
| JD3RZ07-1L59ST31559 | Backfilling Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z07-1-L-59-ST | 1 | 2024-09-14 | 2024-09-15 | 2025-06-21 | 2025-07-08
| JD3RZ07-1L59ST31560 | Excavation Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z07-1-L-59-ST | 1 | 2024-09-04 | 2024-09-05 | 2025-06-12 | 2025-06-30
| JD3RZ07-1L59ST31561 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z07-1-L-59-ST | 1 | 2024-09-07 | 2024-09-08 | 2025-06-18 | 2025-07-06
| JD3RZ07-1L59ST31562 | Installing for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z07-1-L-59-ST | 1 | 2024-09-09 | 2024-09-10 | 2025-06-21 | 2025-07-08
| JD3RZ07-1L59ST31563 | Primary Test for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z07-1-L-59-ST | 1 | 2024-09-11 | 2024-09-12 | 2025-07-01 | 2025-07-19
| JD3RZ07-1L59ST31564 | Backfilling Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z07-1-L-59-ST | 1 | 2024-09-14 | 2024-09-15 | 2025-07-05 | 2025-07-22
| JD3RZ07-1L59ST31565 | Excavation Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-1-L-59-ST | 1 | 2024-09-04 | 2024-09-07 | 2025-04-06 | 2025-04-23
| JD3RZ07-1L59ST31566 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-1-L-59-ST | 1 | 2024-09-08 | 2024-09-10 | 2025-04-07 | 2025-05-04
| JD3RZ07-1L59ST31567 | Installing for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-1-L-59-ST | 1 | 2024-09-11 | 2024-09-14 | 2025-04-15 | 2025-05-21
| JD3RZ07-1L59ST31568 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-1-L-59-ST | 1 | 2024-09-17 | 2024-09-19 | 2025-06-29 | 2025-07-31
| JD3RZ07-1L59ST31568.R | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-1-L-59-ST -Remaining | 1 | 2024-10-19 | 2024-10-20 | 2025-08-18 | 2025-08-21
| JD3RZ07-1L59ST31569 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-1-L-59-ST | 1 | 2024-09-21 | 2024-09-25 | 2025-07-01 | 2025-07-31
| JD3RZ07-1L59ST31569.R | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-1-L-59-ST -Remaining | 1 | 2024-10-21 | 2024-10-22 | 2025-08-28
| JD3RZ07-1L59ST31570 | Excavation Works for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m- B6.33 42 11.07-Z07-1-L-59-ST | 1 | 2024-10-12 | 2024-10-13 | 2025-08-16 | 2025-08-17
| JD3RZ07-1L59ST31571 | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m- B6.33 42 11.07-Z07-1-L-59-ST | 1 | 2024-10-14 | 2024-10-15 | 2025-08-18 | 2025-08-19
| JD3RZ07-1L59ST31572 | Installing for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m- B6.33 42 11.07-Z07-1-L-59-ST | 1 | 2024-10-16 | 2024-10-17 | 2025-08-20 | 2025-08-21
| JD3RZ07-1L59ST31573 | Primary Test for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m- B6.33 42 11.07-Z07-1-L-59-ST | 1 | 2024-10-19 | 2024-10-20 | 2025-08-23 | 2025-08-24
| JD3RZ07-1L59ST31574 | Backfilling Works for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m- B6.33 42 11.07-Z07-1-L-59-ST | 1 | 2024-10-26 | 2024-10-27 | 2025-08-30 | 2025-08-31
| JD3RZ07-1L59ST31575 | Excavation Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-1-L-59-ST | 1 | 2024-09-04 | 2024-09-05 | 2025-04-06 | 2025-04-23
| JD3RZ07-1L59ST31576 | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-1-L-59-ST | 1 | 2024-09-07 | 2024-09-08 | 2025-04-07 | 2025-04-24
| JD3RZ07-1L59ST31577 | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-1-L-59-ST | 1 | 2024-09-09 | 2024-09-10 | 2025-04-08 | 2025-04-26
| JD3RZ07-1L59ST31578 | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-1-L-59-ST | 1 | 2024-10-19 | 2024-10-20 | 2025-08-23 | 2025-08-24
| JD3RZ07-1L59ST31579 | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-1-L-59-ST | 1 | 2024-10-21 | 2024-10-22 | 2025-08-30
| JD3RZ07-1L59ST31585 | Excavation Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-1-L-59-ST | 1 | 2024-09-04 | 2024-09-05 | 2025-04-10 | 2025-04-28
| JD3RZ07-1L59ST31586 | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-1-L-59-ST | 1 | 2024-09-07 | 2024-09-08 | 2025-04-13 | 2025-04-30
| JD3RZ07-1L59ST31587 | Installing for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-1-L-59-ST | 1 | 2024-09-09 | 2024-09-10 | 2025-04-14 | 2025-05-01
| JD3RZ07-1L59ST31588 | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-1-L-59-ST | 1 | 2024-10-19 | 2024-10-20 | 2025-08-23 | 2025-08-28
| JD3RZ07-1L59ST31589 | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-1-L-59-ST | 1 | 2024-10-21 | 2024-10-22 | 2025-08-30
| JD3RZ07-1L59ST31595 | Excavation Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-1-L-59-ST | 1 | 2024-09-04 | 2024-09-05 | 2025-04-10 | 2025-04-28
| JD3RZ07-1L59ST31596 | Soil Replacement and Bedding Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-1-L-59-ST | 1 | 2024-09-07 | 2024-09-08 | 2025-04-13 | 2025-04-30
| JD3RZ07-1L59ST31597 | Installing for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-1-L-59-ST | 1 | 2024-09-09 | 2024-09-10 | 2025-04-14 | 2025-05-01
| JD3RZ07-1L59ST31598 | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-1-L-59-ST | 1 | 2024-10-19 | 2024-10-20 | 2025-08-23 | 2025-08-24
| JD3RZ07-1L59ST31599 | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-1-L-59-ST | 1 | 2024-10-21 | 2024-10-22 | 2025-08-30
| JD3RZ07-1L59ST31610 | Excavation Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-1-L-59-ST | 1 | 2024-09-21 | 2024-09-22 | 2025-06-10 | 2025-06-28
| JD3RZ07-1L59ST31611 | Soil Replacement and Bedding Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-1-L-59-ST | 1 | 2024-09-24 | 2024-09-25 | 2025-06-15 | 2025-07-02
| JD3RZ07-1L59ST31612 | Installing for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-1-L-59-ST | 1 | 2024-09-26 | 2024-09-28 | 2025-07-05 | 2025-07-22
| JD3RZ07-1L59ST31612.R | Installing for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-1-L-59-ST -Remaining | 1 | 2024-09-29 | 2024-09-30 | 2025-08-16 | 2025-08-17
| JD3RZ07-1L59ST31613 | Primary Test for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-1-L-59-ST | 1 | 2024-10-01 | 2024-10-02 | 2025-08-18 | 2025-08-19
| JD3RZ07-1L59ST31614 | Backfilling Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-1-L-59-ST | 1 | 2024-10-03 | 2024-10-05 | 2025-08-30
| JD3RZ07-1L59ST31718 | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-1-L-59-ST | 1 | 2024-09-24 | 2024-09-25 | 2025-05-15 | 2025-06-02
| JD3RZ07-1L59ST31718.R | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-1-L-59-ST -Remaining | 1 | 2024-10-03 | 2024-10-05 | 2025-08-18 | 2025-08-19
| JD3RZ07-1L59ST31719 | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-1-L-59-ST | 1 | 2024-09-26 | 2024-09-29 | 2025-05-18 | 2025-06-14
| JD3RZ07-1L59ST31719.R | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-1-L-59-ST -Remaining | 1 | 2024-10-06 | 2024-10-07 | 2025-08-20 | 2025-08-21
| JD3RZ07-1L59ST31720 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-1-L-59-ST | 1 | 2024-09-30 | 2024-10-02 | 2025-05-25 | 2025-06-21
| JD3RZ07-1L59ST31720.R | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-1-L-59-ST -Remaining | 1 | 2024-10-08 | 2024-10-09
| JD3RZ07-1L59ST31721 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-1-L-59-ST | 1 | 2024-10-10 | 2024-10-12
| JD3RZ07-1L59ST31722 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-1-L-59-ST | 1 | 2024-10-13 | 2024-10-14
| JD3RZ07-1L59ST31728 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-1-L-59-ST | 1 | 2024-09-04 | 2024-09-05 | 2025-04-10 | 2025-04-28
| JD3RZ07-1L59ST31729 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-1-L-59-ST | 1 | 2024-09-07 | 2024-09-08 | 2025-06-15 | 2025-07-02
| JD3RZ07-1L59ST31730 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-1-L-59-ST | 1 | 2024-09-26 | 2024-09-28 | 2025-06-18 | 2025-07-06
| JD3RZ07-1L59ST31730.R | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-1-L-59-ST -Remaining | 1 | 2024-10-10 | 2024-10-12
| JD3RZ07-1L59ST31731 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-1-L-59-ST | 1 | 2024-10-13 | 2024-10-14
| JD3RZ07-1L59ST31732 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-1-L-59-ST | 1 | 2024-10-15 | 2024-10-16
| JD3RZ07-1L59ST31733 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-1-L-59-ST | 1 | 2024-10-14 | 2024-10-15 | 2025-08-16
| JD3RZ07-1L59ST31734 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-1-L-59-ST | 1 | 2024-10-16 | 2024-10-17 | 2025-08-18
| JD3RZ07-1L59ST31735 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-1-L-59-ST | 1 | 2024-10-19 | 2024-10-20
| JD3RZ07-1L59ST31736 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-1-L-59-ST | 1 | 2024-10-21 | 2024-10-22
| JD3RZ07-1L59ST31737 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-1-L-59-ST | 1 | 2024-10-23 | 2024-10-24
| JD3RZ07-1L59ST31743 | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-1-L-59-ST | 1 | 2024-09-29 | 2024-09-30 | 2025-06-18 | 2025-07-06
| JD3RZ07-1L59ST31743.R | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-1-L-59-ST -Remaining | 1 | 2024-10-01 | 2024-10-02 | 2025-08-16 | 2025-08-17
| JD3RZ07-1L59ST31744 | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-1-L-59-ST | 1 | 2024-10-03 | 2024-10-05 | 2025-08-18 | 2025-08-19
| JD3RZ07-1L59ST31745 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-1-L-59-ST | 1 | 2024-10-06 | 2024-10-07
| JD3RZ07-1L59ST31746 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-1-L-59-ST | 1 | 2024-10-08 | 2024-10-09
| JD3RZ07-1L59ST31747 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-1-L-59-ST | 1 | 2024-10-10 | 2024-10-12
| JD3RZ07-1L59ST31748 | Excavation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-1-L-59-ST | 1 | 2024-10-16 | 2024-10-17 | 2025-08-18 | 2025-08-19
| JD3RZ07-1L59ST31749 | Base Plain Concrete Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-1-L-59-ST | 1 | 2024-10-19 | 2024-10-20 | 2025-08-20 | 2025-08-21
| JD3RZ07-1L59ST31750 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-1-L-59-ST | 1 | 2024-10-21 | 2024-10-22
| JD3RZ07-1L59ST31751 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-1-L-59-ST | 1 | 2024-10-23 | 2024-10-24
| JD3RZ07-1L59ST31752 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-1-L-59-ST | 1 | 2024-10-26 | 2024-10-27
| JD3RZ07-1L59ST31753 | EXCAVATION Works for Catchbasine single - - B6.33 05 39.09-Z07-1-L-59-ST | 1 | 2024-10-19 | 2024-10-21
| JD3RZ07-1L59ST31754 | Catchbasine Installation Works For Catchbasine single - - B6.33 05 39.09-Z07-1-L-59-ST | 1 | 2024-10-22 | 2024-10-26
| JD3RZ07-1L59ST31755 | FINISHING Works For Catchbasine single - - B6.33 05 39.09-Z07-1-L-59-ST | 1 | 2024-10-27 | 2024-10-30
| JD3RZ07-1L59ST31756 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - - B6.33 05 39.09-Z07-1-L-59-ST | 1 | 2024-10-31 | 2024-11-03
| JD3RZ07-1L59ST31757 | EXCAVATION Works for Catchbasine double - - B6.33 05 39.10-Z07-1-L-59-ST | 1 | 2024-10-22 | 2024-10-24
| JD3RZ07-1L59ST31758 | Catchbasine Installation Works For Catchbasine double - - B6.33 05 39.10-Z07-1-L-59-ST | 1 | 2024-10-26 | 2024-10-29
| JD3RZ07-1L59ST31759 | FINISHING Works For Catchbasine double - - B6.33 05 39.10-Z07-1-L-59-ST | 1 | 2024-10-30 | 2024-11-03
| JD3RZ07-1L59ST31760 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - - B6.33 05 39.10-Z07-1-L-59-ST | 1 | 2024-11-04 | 2024-11-06
| JD3RZ07-1L59ST524359 | Concrete encasement for pipes- NNB6.33 42 11.25-Z07-1-L-59-ST | 1 | 2024-10-19 | 2024-10-24
| JD3RZ07-1L59TC32091 | Excavation Worksfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z07-1-L-59-TC | 1 | 2025-01-01 | 2025-01-02
| JD3RZ07-1L59TC32092 | Installationfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z07-1-L-59-TC | 1 | 2025-01-04 | 2025-01-07
| JD3RZ07-1L59TC32093 | Pouring Concrete Coverfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z07-1-L-59-TC | 1 | 2025-01-08 | 2025-01-12
| JD3RZ07-1L59TC32094 | Backfilling Worksfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z07-1-L-59-TC | 1 | 2025-01-13 | 2025-01-14
| JD3RZ07-1L59TC32095 | Excavation and Bedding Worksfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z07-1-L-59-TC | 1 | 2025-01-15 | 2025-01-16
| JD3RZ07-1L59TC32096 | Installationfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z07-1-L-59-TC | 1 | 2025-01-18 | 2025-01-19
| JD3RZ07-1L59TC32097 | Backfilling Worksfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z07-1-L-59-TC | 1 | 2025-01-21 | 2025-01-22
| JD3RZ07-1L59TSE31811 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-1-L-59-TSE | 1 | 2024-11-07 | 2024-11-12 | 2025-08-07
| JD3RZ07-1L59TSE31812 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-1-L-59-TSE | 1 | 2024-11-13 | 2024-11-18 | 2025-08-13
| JD3RZ07-1L59TSE31813 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-1-L-59-TSE | 1 | 2024-11-19 | 2024-11-28 | 2025-08-18
| JD3RZ07-1L59TSE31814 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-1-L-59-TSE | 1 | 2024-11-30 | 2024-12-05 | 2025-08-30
| JD3RZ07-1L59TSE31815 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-1-L-59-TSE | 1 | 2024-12-07 | 2024-12-12 | 2025-08-06
| JD3RZ07-1L59TSE31816 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z07-1-L-59-TSE | 1 | 2024-11-13 | 2024-11-14
| JD3RZ07-1L59TSE31817 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z07-1-L-59-TSE | 1 | 2024-11-16 | 2024-11-17
| JD3RZ07-1L59TSE31818 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z07-1-L-59-TSE | 1 | 2024-11-18 | 2024-11-19
| JD3RZ07-1L59TSE31819 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z07-1-L-59-TSE | 1 | 2024-11-20 | 2024-11-21
| JD3RZ07-1L59TSE31820 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z07-1-L-59-TSE | 1 | 2024-12-07 | 2024-12-08
| JD3RZ07-1L59TSE31936 | Installationfor gate valves 100 mm - - B4.33 14 19.01-Z07-1-L-59-TSE | 1 | 2024-11-30 | 2024-12-01
| JD3RZ07-1L59TSE31937 | Testing And Commtionningfor gate valves 100 mm - - B4.33 14 19.01-Z07-1-L-59-TSE | 1 | 2024-12-04 | 2024-12-05
| JD3RZ07-1L59WT31761 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-1-L-59-WT | 1 | 2024-11-13 | 2024-11-18 | 2025-08-13 | 2025-08-18
| JD3RZ07-1L59WT31762 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-1-L-59-WT | 1 | 2024-11-19 | 2024-11-24 | 2025-08-18 | 2025-08-23
| JD3RZ07-1L59WT31763 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-1-L-59-WT | 1 | 2024-11-25 | 2024-12-04 | 2025-08-24 | 2025-08-30
| JD3RZ07-1L59WT31764 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-1-L-59-WT | 1 | 2024-12-05 | 2024-12-11 | 2025-08-26 | 2025-08-31
| JD3RZ07-1L59WT31765 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-1-L-59-WT | 1 | 2024-12-21 | 2024-12-26 | 2025-08-30
| JD3RZ07-1L59WT31786 | INSTALLATIONfor gate valves 150 mm - - B3.33 14 19.01-Z07-1-L-59-WT | 1 | 2024-12-05 | 2024-12-07
| JD3RZ07-1L59WT31787 | TESTING AND COMMITIONfor gate valves 150 mm - - B3.33 14 19.01-Z07-1-L-59-WT | 1 | 2024-12-08 | 2024-12-09
| JD3RZ07-1L59WT31796 | EXCAVATION and Bedding Worksfor Fire Hydrant - - B3.33 14 19.08-Z07-1-L-59-WT | 1 | 2024-12-14 | 2024-12-15
| JD3RZ07-1L59WT31797 | INSTALLATIONfor Fire Hydrant - - B3.33 14 19.08-Z07-1-L-59-WT | 1 | 2024-12-16 | 2024-12-17
| JD3RZ07-1L59WT31798 | TESTING AND COMMITIONfor Fire Hydrant - - B3.33 14 19.08-Z07-1-L-59-WT | 1 | 2024-12-18 | 2024-12-19
| JD3RZ07-1L60SL32768 | Excavation of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z07-1-L-60-SL | 1 | 2024-12-30 | 2024-12-31
| JD3RZ07-1L60SL32769 | Installation of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z07-1-L-60-SL | 1 | 2025-01-01 | 2025-01-04
| JD3RZ07-1L60SL32770 | Backfilling of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z07-1-L-60-SL | 1 | 2025-01-05 | 2025-01-06
| JD3RZ07-1L60SL32771 | Installation Worksfor LIGHTING POLE one arm - - B2.26 56 19.02-Z07-1-L-60-SL | 1 | 2025-01-07 | 2025-01-12
| JD3RZ07-1L60SL32772 | Testing and Commitioningfor LIGHTING POLE one arm - - B2.26 56 19.02-Z07-1-L-60-SL | 1 | 2025-01-13 | 2025-01-18
| JD3RZ07-1L60SL32773 | Installationfor Lighting( LED ) Luminaire 150 WATT - - B2.26.56.19.01-Z07-1-L-60-SL | 1 | 2025-01-05 | 2025-01-06
| JD3RZ07-1L60SL32776 | Supply, construct, connect and test earthing pitsfor Street Lighting EARTHING SYSTEM - - B2.26 05 26.01-Z07-1-L-60-SL | 1 | 2025-01-07 | 2025-01-08
| JD3RZ07-1L60SL32777 | Excavation Worksfor PVC Pipes 2×150mm - - B2.33 71 19.01.SL-Z07-1-L-60-SL | 1 | 2025-01-01 | 2025-01-02
| JD3RZ07-1L60SL32778 | Installationfor PVC Pipes 2×150mm - - B2.33 71 19.01.SL-Z07-1-L-60-SL | 1 | 2025-01-04 | 2025-01-05
| JD3RZ07-1L60SL32779 | Pouring Concrete Coverfor PVC Pipes 2×150mm - - B2.33 71 19.01.SL-Z07-1-L-60-SL | 1 | 2025-01-06 | 2025-01-07
| JD3RZ07-1L60SL32780 | Testing and Backfilling Worksfor PVC Pipes 2×150mm - - B2.33 71 19.01.SL-Z07-1-L-60-SL | 1 | 2025-01-08 | 2025-01-09
| JD3RZ07-1L60SL32789 | Excavationfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z07-1-L-60-SL | 1 | 2025-01-04 | 2025-01-05
| JD3RZ07-1L60SL32790 | Installationfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z07-1-L-60-SL | 1 | 2025-01-06 | 2025-01-08
| JD3RZ07-1L60SL32791 | Backfillingfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z07-1-L-60-SL | 1 | 2025-01-09 | 2025-01-11
| JD3RZ07-1L60SL32792 | Excavationfor Drawpit 900x900x1200mm - - B2.33 71 19.13.02-Z07-1-L-60-SL | 1 | 2025-01-06 | 2025-01-07
| JD3RZ07-1L60SL32793 | Installationfor Drawpit 900x900x1200mm - - B2.33 71 19.13.02-Z07-1-L-60-SL | 1 | 2025-01-08 | 2025-01-09
| JD3RZ07-1L60SL32794 | Backfillingfor Drawpit 900x900x1200mm - - B2.33 71 19.13.02-Z07-1-L-60-SL | 1 | 2025-01-11 | 2025-01-12
| JD3RZ07-1L60SS32122 | Trench excavation for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z07-1-L-60-SS | 1 | 2024-09-04 | 2024-09-07 | 2024-12-28 | 2025-06-03
| JD3RZ07-1L60SS32123 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z07-1-L-60-SS | 1 | 2024-09-12 | 2024-09-15 | 2025-01-01 | 2025-05-11
| JD3RZ07-1L60SS32124 | Installing for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z07-1-L-60-SS | 1 | 2024-09-21 | 2024-09-24 | 2025-01-01 | 2025-05-29
| JD3RZ07-1L60SS32125 | Primary Test for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z07-1-L-60-SS | 1 | 2024-10-02 | 2024-10-05 | 2025-01-14 | 2025-03-29
| JD3RZ07-1L60SS32126 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z07-1-L-60-SS | 1 | 2024-10-06 | 2024-10-09 | 2025-01-15 | 2025-06-12
| JD3RZ07-1L60SS32126.R | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z07-1-L-60-SS -Rem | 1 | 2024-10-10 | 2024-10-12 | 2025-08-18 | 2025-09-15
| JD3RZ07-1L60SS32127 | Trench excavation for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z07-1-L-60-SS | 1 | 2024-09-04 | 2024-09-11 | 2024-11-26 | 2025-01-20
| JD3RZ07-1L60SS32128 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z07-1-L-60-SS | 1 | 2024-09-12 | 2024-09-19 | 2024-12-16 | 2025-01-21
| JD3RZ07-1L60SS32129 | Installing for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z07-1-L-60-SS | 1 | 2024-09-21 | 2024-10-01 | 2024-12-18 | 2025-02-02
| JD3RZ07-1L60SS32130 | Primary Test for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z07-1-L-60-SS | 1 | 2024-10-02 | 2024-10-09 | 2024-12-02 | 2025-01-16
| JD3RZ07-1L60SS32131 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z07-1-L-60-SS | 1 | 2024-10-10 | 2024-10-22 | 2025-01-15 | 2025-03-02
| JD3RZ07-1L60SS32131.R | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z07-1-L-60-SS -Rem | 1 | 2024-10-23 | 2024-10-24 | 2025-08-20
| JD3RZ07-1L60SS32176 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z07-1-L-60-SS | 1 | 2024-09-04 | 2024-09-05 | 2024-12-17 | 2025-01-04
| JD3RZ07-1L60SS32177 | Installation of Base Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z07-1-L-60-SS | 1 | 2024-09-07 | 2024-09-08 | 2025-01-08 | 2025-01-26
| JD3RZ07-1L60SS32178 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z07-1-L | 1 | 2024-09-09 | 2024-09-10 | 2025-01-15 | 2025-02-02
| JD3RZ07-1L60SS32179 | Backfilling Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z07-1-L-60-SS | 1 | 2024-10-26 | 2024-10-27
| JD3RZ07-1L60SS32180 | Finishing, Benching Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z07-1-L-60-SS | 1 | 2024-10-26 | 2024-10-27
| JD3RZ07-1L60SS521401 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2024-10-28 | 2024-10-29 | 2025-08-08
| JD3RZ07-1L60SS521411 | Installation of Base Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2024-10-30 | 2024-11-04 | 2025-08-14
| JD3RZ07-1L60SS521421 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03 | 1 | 2024-11-05 | 2024-11-10 | 2025-08-20
| JD3RZ07-1L60SS521431 | Backfilling Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2024-11-11 | 2024-11-13
| JD3RZ07-1L60SS521441 | Finishing, Benching Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2024-11-14 | 2024-11-16
| JD3RZ07-1L60ST32248 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-1-L-60-ST | 1 | 2024-10-26 | 2024-10-28 | 2025-09-03
| JD3RZ07-1L60ST32249 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-1-L-60-ST | 1 | 2024-10-29 | 2024-10-31 | 2025-09-09
| JD3RZ07-1L60ST32250 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-1-L-60-ST | 1 | 2024-11-02 | 2024-11-05 | 2025-09-13
| JD3RZ07-1L60ST32251 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-1-L-60-ST | 1 | 2024-11-06 | 2024-11-10
| JD3RZ07-1L60ST32252 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-1-L-60-ST | 1 | 2024-12-16 | 2024-12-21
| JD3RZ07-1L60ST32253 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-1-L-60-ST | 1 | 2024-10-23 | 2024-10-24 | 2025-04-14 | 2025-05-01
| JD3RZ07-1L60ST32253.R | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-1-L-60-ST -Remaining | 1 | 2024-10-29 | 2024-10-30 | 2025-08-02
| JD3RZ07-1L60ST32254 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-1-L-60-ST | 1 | 2024-10-26 | 2024-10-27 | 2025-04-15 | 2025-05-03
| JD3RZ07-1L60ST32254.R | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-1-L-60-ST -R | 1 | 2024-10-31 | 2024-11-02 | 2025-08-04
| JD3RZ07-1L60ST32255 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-1-L-60-ST | 1 | 2024-10-28 | 2024-10-29 | 2025-04-16 | 2025-05-04
| JD3RZ07-1L60ST32255.R | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-1-L-60-ST -Remaining | 1 | 2024-11-03 | 2024-11-04 | 2025-08-07
| JD3RZ07-1L60ST32256 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-1-L-60-ST | 1 | 2024-10-30 | 2024-10-31 | 2025-06-16 | 2025-07-03
| JD3RZ07-1L60ST32256.R | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-1-L-60-ST -Remaining | 1 | 2024-11-05 | 2024-11-06 | 2025-08-09
| JD3RZ07-1L60ST32257 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-1-L-60-ST | 1 | 2024-11-07 | 2024-11-09 | 2025-08-11
| JD3RZ07-1L60ST32268 | Excavation Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z07-1-L-60-ST | 1 | 2024-10-31 | 2024-11-02 | 2025-08-04 | 2025-08-05
| JD3RZ07-1L60ST32269 | Soil Replacement and Bedding Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z07-1-L-60-ST | 1 | 2024-11-03 | 2024-11-04 | 2025-08-07 | 2025-08-09
| JD3RZ07-1L60ST32270 | Installing for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z07-1-L-60-ST | 1 | 2024-11-05 | 2024-11-06 | 2025-08-09 | 2025-08-10
| JD3RZ07-1L60ST32271 | Primary Test for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z07-1-L-60-ST | 1 | 2024-11-07 | 2024-11-09 | 2025-08-11 | 2025-08-12
| JD3RZ07-1L60ST32272 | Backfilling Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z07-1-L-60-ST | 1 | 2024-12-16 | 2024-12-17 | 2025-08-15 | 2025-08-17
| JD3RZ07-1L60ST32278 | Excavation Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-1-L-60-ST | 1899-12-31 | 2024-09-04 | 2024-09-05 | 2025-03-11 | 2025-03-29
| JD3RZ07-1L60ST32279 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-1-L-60-ST | 1 | 2024-09-07 | 2024-09-08 | 2025-03-12 | 2025-03-30
| JD3RZ07-1L60ST32280 | Installing for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-1-L-60-ST | 1 | 2024-09-09 | 2024-09-10 | 2025-03-29 | 2025-04-24
| JD3RZ07-1L60ST32281 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-1-L-60-ST | 1 | 2024-09-11 | 2024-09-12 | 2025-04-08 | 2025-05-05
| JD3RZ07-1L60ST32282 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-1-L-60-ST | 1 | 2024-09-14 | 2024-09-15 | 2025-04-27 | 2025-05-24
| JD3RZ07-1L60ST32288 | Excavation Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-1-L-60-ST | 1 | 2024-09-04 | 2024-09-05 | 2025-02-24 | 2025-03-13
| JD3RZ07-1L60ST32289 | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-1-L-60-ST | 1 | 2024-09-07 | 2024-09-08 | 2025-02-25 | 2025-03-15
| JD3RZ07-1L60ST32290 | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-1-L-60-ST | 1 | 2024-09-09 | 2024-09-10 | 2025-02-26 | 2025-03-16
| JD3RZ07-1L60ST32291 | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-1-L-60-ST | 1 | 2024-10-26 | 2024-10-27 | 2025-03-05 | 2025-03-23
| JD3RZ07-1L60ST32291.R | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-1-L-60-ST -Remaining | 1 | 2024-11-10 | 2024-11-11 | 2025-08-14 | 2025-08-16
| JD3RZ07-1L60ST32292 | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-1-L-60-ST | 1 | 2024-10-28 | 2024-10-29 | 2025-04-27 | 2025-05-24
| JD3RZ07-1L60ST32292.R | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-1-L-60-ST -Remaining | 1 | 2024-11-12 | 2024-11-13 | 2025-08-16 | 2025-08-17
| JD3RZ07-1L60ST32298 | Excavation Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-1-L-60-ST | 1 | 2024-09-04 | 2024-09-05 | 2025-03-11 | 2025-03-29
| JD3RZ07-1L60ST32299 | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-1-L-60-ST | 1 | 2024-09-07 | 2024-09-08 | 2025-03-18 | 2025-04-05
| JD3RZ07-1L60ST32300 | Installing for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-1-L-60-ST | 1 | 2024-09-09 | 2024-09-10 | 2025-03-19 | 2025-04-06
| JD3RZ07-1L60ST32301 | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-1-L-60-ST | 1 | 2024-09-11 | 2024-09-12 | 2025-05-13 | 2025-05-31
| JD3RZ07-1L60ST32302 | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-1-L-60-ST | 1 | 2024-10-28 | 2024-10-29 | 2025-05-15 | 2025-06-11
| JD3RZ07-1L60ST32302.R | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-1-L-60-ST -Remaining | 1 | 2024-11-12 | 2024-11-13 | 2025-08-30
| JD3RZ07-1L60ST32308 | Excavation Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-1-L-60-ST | 1 | 2024-09-04 | 2024-09-05 | 2025-02-25 | 2025-03-24
| JD3RZ07-1L60ST32309 | Soil Replacement and Bedding Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-1-L-60-ST | 1 | 2024-09-07 | 2024-09-08 | 2025-02-25 | 2025-03-24
| JD3RZ07-1L60ST32310 | Installing for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-1-L-60-ST | 1 | 2024-09-09 | 2024-09-11 | 2025-02-26 | 2025-04-03
| JD3RZ07-1L60ST32311 | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-1-L-60-ST | 1 | 2024-09-12 | 2024-09-14 | 2025-05-13 | 2025-06-18
| JD3RZ07-1L60ST32312 | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-1-L-60-ST | 1 | 2024-10-30 | 2024-11-02 | 2025-05-15 | 2025-06-21
| JD3RZ07-1L60ST32312.R | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-1-L-60-ST -Remaining | 1 | 2024-11-14 | 2024-11-16 | 2025-08-18 | 2025-08-19
| JD3RZ07-1L60ST32323 | Excavation Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-1-L-60-ST | 1 | 2024-09-04 | 2024-09-07 | 2025-04-20 | 2025-05-26
| JD3RZ07-1L60ST32324 | Soil Replacement and Bedding Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-1-L-60-ST | 1 | 2024-09-08 | 2024-09-10 | 2025-04-28 | 2025-06-03
| JD3RZ07-1L60ST32325 | Installing for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-1-L-60-ST | 1 | 2024-09-11 | 2024-09-14 | 2025-05-10 | 2025-07-03
| JD3RZ07-1L60ST32326 | Primary Test for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-1-L-60-ST | 1 | 2024-11-03 | 2024-11-05 | 2025-06-10 | 2025-07-31
| JD3RZ07-1L60ST32326.R | Primary Test for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-1-L-60-ST -Remaining | 1 | 2024-11-17 | 2024-11-18 | 2025-08-21 | 2025-08-23
| JD3RZ07-1L60ST32327 | Backfilling Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-1-L-60-ST | 1 | 2024-11-06 | 2024-11-10 | 2025-07-05 | 2025-07-31
| JD3RZ07-1L60ST32327.R | Backfilling Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-1-L-60-ST -Remaining | 1 | 2024-11-19 | 2024-11-20 | 2025-08-23 | 2025-08-24
| JD3RZ07-1L60ST32338 | Excavation Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z07-1-L-60-ST | 1 | 2024-09-04 | 2024-09-05 | 2025-05-20 | 2025-06-07
| JD3RZ07-1L60ST32339 | Soil Replacement and Bedding Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z07-1-L-60-ST | 1 | 2024-09-07 | 2024-09-08 | 2025-05-21 | 2025-06-08
| JD3RZ07-1L60ST32340 | Installing for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z07-1-L-60-ST | 1 | 2024-12-07 | 2024-12-08 | 2025-08-23 | 2025-08-24
| JD3RZ07-1L60ST32341 | Primary Test for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z07-1-L-60-ST | 1 | 2024-12-09 | 2024-12-10 | 2025-08-25 | 2025-08-26
| JD3RZ07-1L60ST32342 | Backfilling Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z07-1-L-60-ST | 1 | 2024-12-11 | 2024-12-12 | 2025-08-30
| JD3RZ07-1L60ST32353 | Excavation Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z07-1-L-60-ST | 1 | 2024-09-04 | 2024-09-05 | 2025-05-15 | 2025-06-11
| JD3RZ07-1L60ST32354 | Soil Replacement and Bedding Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z07-1-L-60-ST | 1 | 2024-09-07 | 2024-09-08 | 2025-05-19 | 2025-06-15
| JD3RZ07-1L60ST32355 | Installing for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z07-1-L-60-ST | 1 | 2024-09-09 | 2024-09-10 | 2025-06-19 | 2025-07-26
| JD3RZ07-1L60ST32356 | Primary Test for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z07-1-L-60-ST | 1 | 2024-12-09 | 2024-12-10 | 2025-08-25 | 2025-08-26
| JD3RZ07-1L60ST32357 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z07-1-L-60-ST | 1 | 2024-12-11 | 2024-12-12 | 2025-08-30
| JD3RZ07-1L60ST32431 | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-1-L-60-ST | 1 | 2024-09-04 | 2024-09-05 | 2025-05-15 | 2025-06-02
| JD3RZ07-1L60ST32432 | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-1-L-60-ST | 1 | 2024-09-07 | 2024-09-08 | 2025-05-19 | 2025-06-05
| JD3RZ07-1L60ST32433 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-1-L-60-ST | 1 | 2024-11-06 | 2024-11-07 | 2025-06-01 | 2025-06-18
| JD3RZ07-1L60ST32433.R | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-1-L-60-ST -Remaining | 1 | 2024-12-11 | 2024-12-12 | 2025-08-18 | 2025-08-19
| JD3RZ07-1L60ST32434 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-1-L-60-ST | 1 | 2024-12-14 | 2024-12-15
| JD3RZ07-1L60ST32435 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-1-L-60-ST | 1 | 2024-12-16 | 2024-12-17
| JD3RZ07-1L60ST32441 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-1-L-60-ST | 1 | 2024-09-04 | 2024-09-05 | 2025-05-19 | 2025-06-05
| JD3RZ07-1L60ST32442 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-1-L-60-ST | 1 | 2024-09-07 | 2024-09-08 | 2025-05-21 | 2025-06-08
| JD3RZ07-1L60ST32443 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-1-L-60-ST | 1 | 2024-11-09 | 2024-11-10 | 2025-06-01 | 2025-06-18
| JD3RZ07-1L60ST32443.R | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-1-L-60-ST -Remaining | 1 | 2024-12-14 | 2024-12-15
| JD3RZ07-1L60ST32444 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-1-L-60-ST | 1 | 2024-12-16 | 2024-12-17
| JD3RZ07-1L60ST32445 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-1-L-60-ST | 1 | 2024-12-18 | 2024-12-19
| JD3RZ07-1L60ST32446 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-1-L-60-ST | 1 | 2024-09-04 | 2024-09-05 | 2025-05-15 | 2025-06-02
| JD3RZ07-1L60ST32447 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-1-L-60-ST | 1 | 2024-09-07 | 2024-09-08 | 2025-05-21 | 2025-06-08
| JD3RZ07-1L60ST32448 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-1-L-60-ST | 1 | 2024-11-11 | 2024-11-12 | 2025-06-01 | 2025-06-18
| JD3RZ07-1L60ST32448.R | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-1-L-60-ST -Remaining | 1 | 2024-12-16 | 2024-12-17 | 2025-08-23 | 2025-08-24
| JD3RZ07-1L60ST32449 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-1-L-60-ST | 1 | 2024-12-18 | 2024-12-19
| JD3RZ07-1L60ST32450 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-1-L-60-ST | 1 | 2024-12-21 | 2024-12-22
| JD3RZ07-1L60ST32456 | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-1-L-60-ST | 1 | 2024-09-04 | 2024-09-05 | 2025-05-19 | 2025-07-22
| JD3RZ07-1L60ST32457 | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-1-L-60-ST | 1 | 2024-09-07 | 2024-09-08 | 2025-05-21 | 2025-07-31
| JD3RZ07-1L60ST32458 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-1-L-60-ST | 1 | 2024-11-13 | 2024-11-14 | 2025-06-01 | 2025-07-31
| JD3RZ07-1L60ST32458.R | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-1-L-60-ST -Remaining | 1 | 2024-12-18 | 2024-12-19 | 2025-08-25 | 2025-08-26
| JD3RZ07-1L60ST32459 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-1-L-60-ST | 1 | 2024-12-21 | 2024-12-22
| JD3RZ07-1L60ST32460 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-1-L-60-ST | 1 | 2024-12-23 | 2024-12-24
| JD3RZ07-1L60ST32461 | Excavation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-1-L-60-ST | 1 | 2024-09-04 | 2024-09-05 | 2025-05-15 | 2025-06-02
| JD3RZ07-1L60ST32462 | Base Plain Concrete Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-1-L-60-ST | 1 | 2024-09-07 | 2024-09-08 | 2025-05-21 | 2025-06-08
| JD3RZ07-1L60ST32463 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-1-L-60-ST | 1 | 2024-11-16 | 2024-11-17 | 2025-06-01 | 2025-06-18
| JD3RZ07-1L60ST32463.R | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-1-L-60-ST -Remaining | 1 | 2024-12-21 | 2024-12-22 | 2025-08-28 | 2025-08-30
| JD3RZ07-1L60ST32464 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-1-L-60-ST | 1 | 2024-12-23 | 2024-12-24
| JD3RZ07-1L60ST32465 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-1-L-60-ST | 1 | 2024-12-25 | 2024-12-26
| JD3RZ07-1L60ST32466 | EXCAVATION Works for Catchbasine single - - B6.33 05 39.09-Z07-1-L-60-ST | 1 | 2024-11-17 | 2024-11-19
| JD3RZ07-1L60ST32467 | Catchbasine Installation Works For Catchbasine single - - B6.33 05 39.09-Z07-1-L-60-ST | 1 | 2024-11-20 | 2024-11-24
| JD3RZ07-1L60ST32468 | FINISHING Works For Catchbasine single - - B6.33 05 39.09-Z07-1-L-60-ST | 1 | 2024-11-25 | 2024-11-28
| JD3RZ07-1L60ST32469 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - - B6.33 05 39.09-Z07-1-L-60-ST | 1 | 2024-11-30 | 2024-12-02
| JD3RZ07-1L60ST32470 | EXCAVATION Works for Catchbasine double - - B6.33 05 39.10-Z07-1-L-60-ST | 1 | 2024-11-20 | 2024-11-21
| JD3RZ07-1L60ST32471 | Catchbasine Installation Works For Catchbasine double - - B6.33 05 39.10-Z07-1-L-60-ST | 1899-12-31 | 2024-11-23 | 2024-11-25
| JD3RZ07-1L60ST32472 | FINISHING Works For Catchbasine double - - B6.33 05 39.10-Z07-1-L-60-ST | 1 | 2024-11-26 | 2024-11-28
| JD3RZ07-1L60ST32473 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - - B6.33 05 39.10-Z07-1-L-60-ST | 1 | 2024-11-30 | 2024-12-01
| JD3RZ07-1L60ST524360 | Concrete encasement for pipes- NNB6.33 42 11.25-Z07-1-L-60-ST | 1 | 2024-12-09 | 2024-12-15
| JD3RZ07-1L60TC32804 | Excavation Worksfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z07-1-L-60-TC | 1 | 2025-01-01 | 2025-01-02
| JD3RZ07-1L60TC32805 | Installationfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z07-1-L-60-TC | 1 | 2025-01-04 | 2025-01-07
| JD3RZ07-1L60TC32806 | Pouring Concrete Coverfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z07-1-L-60-TC | 1 | 2025-01-08 | 2025-01-12
| JD3RZ07-1L60TC32807 | Backfilling Worksfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z07-1-L-60-TC | 1 | 2025-01-13 | 2025-01-14
| JD3RZ07-1L60TC32808 | Excavation and Bedding Worksfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z07-1-L-60-TC | 1 | 2025-01-13 | 2025-01-14
| JD3RZ07-1L60TC32809 | Installationfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z07-1-L-60-TC | 1 | 2025-01-15 | 2025-01-16
| JD3RZ07-1L60TC32810 | Backfilling Worksfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z07-1-L-60-TC | 1 | 2025-01-18 | 2025-01-19
| JD3RZ07-1L60TSE32524 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-1-L-60-TSE | 1 | 2024-11-20 | 2024-11-24 | 2025-08-02 | 2025-08-05
| JD3RZ07-1L60TSE32525 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-1-L-60-TSE | 1 | 2024-11-25 | 2024-11-30 | 2025-08-06 | 2025-08-11
| JD3RZ07-1L60TSE32526 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-1-L-60-TSE | 1 | 2024-12-01 | 2024-12-09 | 2025-08-12 | 2025-08-20
| JD3RZ07-1L60TSE32527 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-1-L-60-TSE | 1 | 2024-12-10 | 2024-12-15 | 2025-08-21 | 2025-08-26
| JD3RZ07-1L60TSE32528 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-1-L-60-TSE | 1 | 2024-12-16 | 2024-12-21 | 2025-08-27 | 2025-08-31
| JD3RZ07-1L60TSE32649 | Installationfor gate valves 100 mm - - B4.33 14 19.01-Z07-1-L-60-TSE | 1 | 2024-12-10 | 2024-12-11
| JD3RZ07-1L60TSE32650 | Testing And Commtionningfor gate valves 100 mm - - B4.33 14 19.01-Z07-1-L-60-TSE | 1 | 2024-12-12 | 2024-12-14
| JD3RZ07-1L60WT32474 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-1-L-60-WT | 1 | 2024-11-18 | 2024-11-24 | 2025-02-11 | 2025-04-16
| JD3RZ07-1L60WT32474.R | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-1-L-60-WT -Remaining | 1 | 2024-11-25 | 2024-11-26
| JD3RZ07-1L60WT32475 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-1-L-60-WT | 1 | 2024-11-25 | 2024-12-01 | 2025-02-12 | 2025-05-25
| JD3RZ07-1L60WT32475.R | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-1-L-60-WT -Remainin | 1 | 2024-12-02 | 2024-12-03
| JD3RZ07-1L60WT32476 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-1-L-60-WT | 1 | 2024-12-02 | 2024-12-14 | 2025-03-04 | 2025-07-30
| JD3RZ07-1L60WT32476.R | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-1-L-60-WT -Remaining | 1899-12-31 | 2024-12-15 | 2024-12-16
| JD3RZ07-1L60WT32477 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-1-L-60-WT | 1 | 2024-11-25 | 2024-12-02 | 2025-04-03 | 2025-05-28
| JD3RZ07-1L60WT32477.R | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-1-L-60-WT -Remaining | 1 | 2024-12-22 | 2024-12-23
| JD3RZ07-1L60WT32478 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-1-L-60-WT | 1 | 2024-12-03 | 2024-12-10 | 2025-04-21 | 2025-07-31
| JD3RZ07-1L60WT32478.R | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-1-L-60-WT -Remaining | 1 | 2024-12-24 | 2024-12-25
| JD3RZ07-1L60WT32499 | INSTALLATIONfor gate valves 150 mm - - B3.33 14 19.01-Z07-1-L-60-WT | 1 | 2024-12-17 | 2024-12-18
| JD3RZ07-1L60WT32500 | TESTING AND COMMITIONfor gate valves 150 mm - - B3.33 14 19.01-Z07-1-L-60-WT | 1 | 2024-12-19 | 2024-12-21
| JD3RZ07-1L60WT32509 | EXCAVATION and Bedding Worksfor Fire Hydrant - - B3.33 14 19.08-Z07-1-L-60-WT | 1 | 2024-12-22 | 2024-12-23
| JD3RZ07-1L60WT32510 | INSTALLATIONfor Fire Hydrant - - B3.33 14 19.08-Z07-1-L-60-WT | 1 | 2024-12-24 | 2024-12-26
| JD3RZ07-1L60WT32511 | TESTING AND COMMITIONfor Fire Hydrant - - B3.33 14 19.08-Z07-1-L-60-WT | 1 | 2024-12-28 | 2024-12-29
| JD3RZ07-1L62SL34161 | Excavation Worksfor Copper Cables 4Cx6 mm² - - B2.26 05 19.01-Z07-1-L-62-SL | 1 | 2024-12-29 | 2025-01-01
| JD3RZ07-1L62SL34162 | Installationfor Copper Cables 4Cx6 mm² - - B2.26 05 19.01-Z07-1-L-62-SL | 1 | 2025-01-02 | 2025-01-06
| JD3RZ07-1L62SL34163 | Backfilling, Warning Tabe Worksfor Copper Cables 4Cx6 mm² - - B2.26 05 19.01-Z07-1-L-62-SL | 1 | 2025-01-07 | 2025-01-11
| JD3RZ07-1L62SL34164 | Testing and Commitioning for Copper Cables 4Cx6 mm² - - B2.26 05 19.01-Z07-1-L-62-SL | 1 | 2025-01-16 | 2025-01-20
| JD3RZ07-1L62SL34185 | INSTALLINGfor insulated copper conductor 6 mm² - - B2.26 05 19.07-Z07-1-L-62-SL | 1 | 2025-01-07 | 2025-01-11
| JD3RZ07-1L62SL34186 | TESTING AND COMMITIONINGfor insulated copper conductor 6 mm² - - B2.26 05 19.07-Z07-1-L-62-SL | 1 | 2025-01-12 | 2025-01-15
| JD3RZ07-1L62SL34194 | Excavation of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z07-1-L-62-SL | 1 | 2025-01-02 | 2025-01-04
| JD3RZ07-1L62SL34195 | Installation of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z07-1-L-62-SL | 1 | 2025-01-05 | 2025-01-07
| JD3RZ07-1L62SL34196 | Backfilling of reinforced concrete foundationfor LIGHTING POLE one arm - - B2.26 56 19.02-Z07-1-L-62-SL | 1 | 2025-01-08 | 2025-01-09
| JD3RZ07-1L62SL34197 | Installation Worksfor LIGHTING POLE one arm - - B2.26 56 19.02-Z07-1-L-62-SL | 1 | 2025-01-11 | 2025-01-15
| JD3RZ07-1L62SL34198 | Testing and Commitioningfor LIGHTING POLE one arm - - B2.26 56 19.02-Z07-1-L-62-SL | 1899-12-31 | 2025-01-16 | 2025-01-21
| JD3RZ07-1L62SL34199 | Installationfor Lighting( LED ) Luminaire 150 WATT - - B2.26.56.19.01-Z07-1-L-62-SL | 1 | 2025-01-08 | 2025-01-09
| JD3RZ07-1L62SL34202 | Supply, construct, connect and test earthing pitsfor Street Lighting EARTHING SYSTEM - - B2.26 05 26.01-Z07-1-L-62-SL | 1 | 2025-01-11 | 2025-01-12
| JD3RZ07-1L62SL34215 | Excavationfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z07-1-L-62-SL | 1 | 2025-01-13 | 2025-01-14
| JD3RZ07-1L62SL34216 | Installationfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z07-1-L-62-SL | 1 | 2025-01-15 | 2025-01-18
| JD3RZ07-1L62SL34217 | Backfillingfor Drawpit 600x600x1000mm - - B2.33 71 19.13.01-Z07-1-L-62-SL | 1 | 2025-01-19 | 2025-01-20
| JD3RZ07-1L62SS33548 | Trench excavation for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z07-1-L-62-SS | 1 | 2024-09-04 | 2024-09-05 | 2024-11-26 | 2025-03-17
| JD3RZ07-1L62SS33548.R | Trench excavation for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z07-1-L-62-SS -Remaining | 1 | 2024-09-07 | 2024-09-08 | 2025-08-04 | 2025-08-05
| JD3RZ07-1L62SS33549 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z07-1-L-62-SS | 1 | 2024-09-07 | 2024-09-08 | 2025-01-04 | 2025-05-13
| JD3RZ07-1L62SS33549.R | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z07-1-L-62-SS -Rem | 1899-12-31 | 2024-09-09 | 2024-09-10 | 2025-08-06 | 2025-08-07
| JD3RZ07-1L62SS33550 | Installing for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z07-1-L-62-SS | 1 | 2024-09-09 | 2024-09-11 | 2025-02-04 | 2025-05-17
| JD3RZ07-1L62SS33550.R | Installing for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z07-1-L-62-SS -Remaining | 1 | 2024-09-12 | 2024-09-14 | 2025-08-09 | 2025-08-10
| JD3RZ07-1L62SS33551 | Primary Test for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z07-1-L-62-SS | 1 | 2024-09-12 | 2024-09-14 | 2025-02-03 | 2025-03-16
| JD3RZ07-1L62SS33551.R | Primary Test for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z07-1-L-62-SS -Remaining | 1 | 2024-09-15 | 2024-09-16 | 2025-08-11 | 2025-08-12
| JD3RZ07-1L62SS33552 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z07-1-L-62-SS | 1 | 2024-09-15 | 2024-09-17 | 2025-02-12 | 2025-07-10
| JD3RZ07-1L62SS33552.R | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 1.51 to 2.50- B5.33 31 00.04-Z07-1-L-62-SS -Rem | 1 | 2024-09-18 | 2024-09-19 | 2025-08-13 | 2025-08-14
| JD3RZ07-1L62SS33553 | Trench excavation for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z07-1-L-62-SS | 1 | 2024-09-07 | 2024-09-09 | 2024-11-26 | 2025-01-11
| JD3RZ07-1L62SS33553.R | Trench excavation for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z07-1-L-62-SS -Remaining | 1 | 2024-09-10 | 2024-09-11 | 2025-08-06 | 2025-08-07
| JD3RZ07-1L62SS33554 | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z07-1-L-62-SS | 1 | 2024-09-10 | 2024-09-12 | 2025-01-04 | 2025-02-18
| JD3RZ07-1L62SS33554.R | Soil Replacement and Bedding Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z07-1-L-62-SS -Rem | 1 | 2024-09-14 | 2024-09-15 | 2025-08-09 | 2025-08-10
| JD3RZ07-1L62SS33555 | Installing for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z07-1-L-62-SS | 1 | 2024-09-14 | 2024-09-17 | 2025-02-04 | 2025-03-12
| JD3RZ07-1L62SS33555.R | Installing for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z07-1-L-62-SS -Remaining | 1 | 2024-09-18 | 2024-09-19 | 2025-08-11 | 2025-08-12
| JD3RZ07-1L62SS33556 | Primary Test for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z07-1-L-62-SS | 1 | 2024-09-18 | 2024-09-21 | 2025-05-04 | 2025-06-09
| JD3RZ07-1L62SS33556.R | Primary Test for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z07-1-L-62-SS -Remaining | 1 | 2024-09-22 | 2024-09-24 | 2025-08-13 | 2025-08-14
| JD3RZ07-1L62SS33557 | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z07-1-L-62-SS | 1 | 2024-09-22 | 2024-09-28 | 2025-05-25 | 2025-07-28
| JD3RZ07-1L62SS33557.R | Backfilling and warning tabe Works for GRP Pipe Line 200 mm - Depth from 2.51 to 3.50- B5.33 31 00.05-Z07-1-L-62-SS -Rem | 1 | 2024-09-29 | 2024-09-30 | 2025-08-16 | 2025-09-16
| JD3RZ07-1L62SS33563 | Trench excavation for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50- B5.33 31 00.11-Z07-1-L-62-SS | 1 | 2024-09-10 | 2024-09-15 | 2025-02-04 | 2025-03-22
| JD3RZ07-1L62SS33563.R | Trench excavation for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50- B5.33 31 00.11-Z07-1-L-62-SS -Remaining | 1 | 2024-09-16 | 2024-09-17 | 2025-08-31 | 2025-09-02
| JD3RZ07-1L62SS33564 | Soil Replacement and Bedding Works for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50- B5.33 31 00.11-Z07-1-L-62-SS | 1 | 2024-09-16 | 2024-09-21 | 2025-02-10 | 2025-03-27
| JD3RZ07-1L62SS33564.R | Soil Replacement and Bedding Works for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50- B5.33 31 00.11-Z07-1-L-62-SS -Rem | 1 | 2024-09-22 | 2024-09-24 | 2025-09-02 | 2025-09-06
| JD3RZ07-1L62SS33565 | Installing for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50- B5.33 31 00.11-Z07-1-L-62-SS | 1 | 2024-09-22 | 2024-09-29 | 2025-02-19 | 2025-04-24
| JD3RZ07-1L62SS33565.R | Installing for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50- B5.33 31 00.11-Z07-1-L-62-SS -Remaining | 1 | 2024-09-30 | 2024-10-01 | 2025-09-02 | 2025-09-08
| JD3RZ07-1L62SS33566 | Primary Test for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50- B5.33 31 00.11-Z07-1-L-62-SS | 1 | 2024-09-30 | 2024-10-05 | 2025-02-24 | 2025-04-29
| JD3RZ07-1L62SS33566.R | Primary Test for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50- B5.33 31 00.11-Z07-1-L-62-SS -Remaining | 1 | 2024-10-06 | 2024-10-07 | 2025-09-09 | 2025-09-13
| JD3RZ07-1L62SS33567 | Backfilling and warning tabe Works for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50- B5.33 31 00.11-Z07-1-L-62-SS | 1 | 2024-10-06 | 2024-10-13 | 2025-03-10 | 2025-05-04
| JD3RZ07-1L62SS33567.R | Backfilling and warning tabe Works for GRP Pipe Line 250 mm - Depth from 2.51 to 3.50- B5.33 31 00.11-Z07-1-L-62-SS -Rem | 1 | 2024-10-14 | 2024-10-15 | 2025-09-14
| JD3RZ07-1L62SS33568 | Trench excavation for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50- B5.33 31 00.12-Z07-1-L-62-SS | 1 | 2024-09-04 | 2024-09-05 | 2025-08-02 | 2025-08-03
| JD3RZ07-1L62SS33569 | Soil Replacement and Bedding Works for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50- B5.33 31 00.12-Z07-1-L-62-SS | 1 | 2024-09-07 | 2024-09-08 | 2025-08-04 | 2025-08-05
| JD3RZ07-1L62SS33570 | Installing for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50- B5.33 31 00.12-Z07-1-L-62-SS | 1 | 2024-09-09 | 2024-09-10 | 2025-08-06 | 2025-08-07
| JD3RZ07-1L62SS33571 | Primary Test for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50- B5.33 31 00.12-Z07-1-L-62-SS | 1 | 2024-09-11 | 2024-09-12 | 2025-09-02 | 2025-09-06
| JD3RZ07-1L62SS33572 | Backfilling and warning tabe Works for GRP Pipe Line 250 mm - Depth from 3.51 to 4.50- B5.33 31 00.12-Z07-1-L-62-SS | 1 | 2024-09-14 | 2024-09-15
| JD3RZ07-1L62SS33602 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z07-1-L-62-SS | 1 | 2024-09-04 | 2024-09-05 | 2024-11-26 | 2025-01-01
| JD3RZ07-1L62SS33603 | Installation of Base Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z07-1-L-62-SS | 1 | 2024-09-07 | 2024-09-08 | 2024-12-24 | 2025-04-05
| JD3RZ07-1L62SS33604 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z07-1-L | 1 | 2024-09-16 | 2024-09-17 | 2025-01-22 | 2025-05-04
| JD3RZ07-1L62SS33604.R | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z07-1-L | 1 | 2024-09-18 | 2024-09-19
| JD3RZ07-1L62SS33605 | Backfilling Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z07-1-L-62-SS | 1 | 2024-09-21 | 2024-09-22
| JD3RZ07-1L62SS33606 | Finishing, Benching Works for Manholes 1200 mm - Depth from 2.51 to 3.50- B5.33 05 13.05-Z07-1-L-62-SS | 1 | 2024-09-24 | 2024-09-25
| JD3RZ07-1L62SS521401 | Excavation and PC Blinding Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2024-09-18 | 2024-09-21 | 2025-08-11 | 2025-08-13
| JD3RZ07-1L62SS521411 | Installation of Base Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2024-09-22 | 2024-09-29 | 2025-08-14 | 2025-08-20
| JD3RZ07-1L62SS521421 | Installation of Manhole Ring and Cover Slab Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03 | 1 | 2024-09-30 | 2024-10-06 | 2025-08-21 | 2025-08-27
| JD3RZ07-1L62SS521431 | Backfilling Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2024-10-07 | 2024-10-09
| JD3RZ07-1L62SS521441 | Finishing, Benching Works for Manholes 1200 mm - Depth from 3.51 to 4.50- B5.33 05 13.05-MR-C-03-SS | 1 | 2024-10-10 | 2024-10-13
| JD3RZ07-1L62ST33674 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-1-L-62-ST | 1 | 2024-09-07 | 2024-09-09 | 2025-09-03
| JD3RZ07-1L62ST33675 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-1-L-62-ST | 1 | 2024-09-10 | 2024-09-12 | 2025-09-09
| JD3RZ07-1L62ST33676 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-1-L-62-ST | 1 | 2024-09-14 | 2024-09-17 | 2025-09-10
| JD3RZ07-1L62ST33677 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-1-L-62-ST | 1 | 2024-09-18 | 2024-09-22
| JD3RZ07-1L62ST33678 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-1-L-62-ST | 1 | 2024-10-05 | 2024-10-09
| JD3RZ07-1L62ST33679 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-1-L-62-ST | 1 | 2024-09-10 | 2024-09-11 | 2025-08-07
| JD3RZ07-1L62ST33680 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-1-L-62-ST | 1 | 2024-09-12 | 2024-09-14 | 2025-08-10
| JD3RZ07-1L62ST33681 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-1-L-62-ST | 1 | 2024-09-15 | 2024-09-16 | 2025-08-12
| JD3RZ07-1L62ST33682 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-1-L-62-ST | 1 | 2024-09-17 | 2024-09-18 | 2025-08-14
| JD3RZ07-1L62ST33683 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-1-L-62-ST | 1 | 2024-10-05 | 2024-10-06 | 2025-08-28
| JD3RZ07-1L62ST33684 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-1-L-62-ST | 1 | 2024-09-12 | 2024-09-14 | 2025-08-07 | 2025-08-09
| JD3RZ07-1L62ST33685 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-1-L-62-ST | 1 | 2024-09-15 | 2024-09-16 | 2025-08-10 | 2025-08-11
| JD3RZ07-1L62ST33686 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-1-L-62-ST | 1 | 2024-09-17 | 2024-09-18 | 2025-08-12 | 2025-08-13
| JD3RZ07-1L62ST33687 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-1-L-62-ST | 1 | 2024-09-19 | 2024-09-21 | 2025-08-14 | 2025-08-16
| JD3RZ07-1L62ST33688 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-1-L-62-ST | 1 | 2024-10-05 | 2024-10-06 | 2025-08-28 | 2025-08-30
| JD3RZ07-1L62ST33694 | Excavation Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z07-1-L-62-ST | 1 | 2024-09-15 | 2024-09-16 | 2025-08-10 | 2025-08-11
| JD3RZ07-1L62ST33695 | Soil Replacement and Bedding Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z07-1-L-62-ST | 1 | 2024-09-17 | 2024-09-18 | 2025-08-12 | 2025-08-13
| JD3RZ07-1L62ST33696 | Installing for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z07-1-L-62-ST | 1 | 2024-09-19 | 2024-09-21 | 2025-08-14 | 2025-08-16
| JD3RZ07-1L62ST33697 | Primary Test for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z07-1-L-62-ST | 1 | 2024-09-22 | 2024-09-24 | 2025-08-17 | 2025-08-18
| JD3RZ07-1L62ST33698 | Backfilling Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z07-1-L-62-ST | 1 | 2024-10-05 | 2024-10-06 | 2025-09-03 | 2025-09-06
| JD3RZ07-1L62ST33704 | Excavation Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-1-L-62-ST | 1 | 2024-09-17 | 2024-09-18 | 2025-08-12 | 2025-08-13
| JD3RZ07-1L62ST33705 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-1-L-62-ST | 1 | 2024-09-19 | 2024-09-21 | 2025-08-14 | 2025-08-16
| JD3RZ07-1L62ST33706 | Installing for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-1-L-62-ST | 1 | 2024-09-22 | 2024-09-24 | 2025-08-17 | 2025-08-18
| JD3RZ07-1L62ST33707 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-1-L-62-ST | 1 | 2024-09-25 | 2024-09-26 | 2025-08-23 | 2025-08-26
| JD3RZ07-1L62ST33708 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-1-L-62-ST | 1 | 2024-10-05 | 2024-10-06 | 2025-08-30
| JD3RZ07-1L62ST33714 | Excavation Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-1-L-62-ST | 1 | 2024-09-19 | 2024-09-21 | 2025-08-14 | 2025-08-16
| JD3RZ07-1L62ST33715 | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-1-L-62-ST | 1 | 2024-09-22 | 2024-09-24 | 2025-08-17 | 2025-08-18
| JD3RZ07-1L62ST33716 | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-1-L-62-ST | 1 | 2024-09-25 | 2024-09-26 | 2025-08-19 | 2025-08-20
| JD3RZ07-1L62ST33717 | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-1-L-62-ST | 1 | 2024-09-28 | 2024-09-29 | 2025-08-23 | 2025-08-26
| JD3RZ07-1L62ST33718 | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-1-L-62-ST | 1 | 2024-10-05 | 2024-10-06 | 2025-08-27 | 2025-08-31
| JD3RZ07-1L62ST33719 | Excavation Works for GRP Pipe Line 800 mm - depth from 0.00 to 1.50 m- B6.33 42 11.09-Z07-1-L-62-ST | 1 | 2024-09-04 | 2024-09-05 | 2025-04-14 | 2025-05-01
| JD3RZ07-1L62ST33720 | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 0.00 to 1.50 m- B6.33 42 11.09-Z07-1-L-62-ST | 1 | 2024-09-07 | 2024-09-08 | 2025-04-15 | 2025-05-03
| JD3RZ07-1L62ST33721 | Installing for GRP Pipe Line 800 mm - depth from 0.00 to 1.50 m- B6.33 42 11.09-Z07-1-L-62-ST | 1 | 2024-09-09 | 2024-09-10 | 2025-05-11 | 2025-05-28
| JD3RZ07-1L62ST33722 | Primary Test for GRP Pipe Line 800 mm - depth from 0.00 to 1.50 m- B6.33 42 11.09-Z07-1-L-62-ST | 1 | 2024-09-11 | 2024-09-12 | 2025-06-16 | 2025-07-03
| JD3RZ07-1L62ST33723 | Backfilling Works for GRP Pipe Line 800 mm - depth from 0.00 to 1.50 m- B6.33 42 11.09-Z07-1-L-62-ST | 1 | 2024-09-18 | 2024-09-19 | 2025-07-05 | 2025-07-22
| JD3RZ07-1L62ST33724 | Excavation Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-1-L-62-ST | 1 | 2024-09-21 | 2024-09-24 | 2025-04-14 | 2025-05-20
| JD3RZ07-1L62ST33724.R | Excavation Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-1-L-62-ST -Remaining | 1 | 2024-09-25 | 2024-09-26 | 2025-08-02 | 2025-08-03
| JD3RZ07-1L62ST33725 | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-1-L-62-ST | 1 | 2024-09-25 | 2024-09-28 | 2025-04-15 | 2025-05-21
| JD3RZ07-1L62ST33725.R | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-1-L-62-ST -R | 1 | 2024-09-29 | 2024-09-30 | 2025-08-04 | 2025-08-05
| JD3RZ07-1L62ST33726 | Installing for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-1-L-62-ST | 1 | 2024-09-29 | 2024-10-02 | 2025-05-11 | 2025-06-25
| JD3RZ07-1L62ST33726.R | Installing for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-1-L-62-ST -Remaining | 1 | 2024-10-03 | 2024-10-05 | 2025-08-06 | 2025-08-07
| JD3RZ07-1L62ST33727 | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-1-L-62-ST | 1 | 2024-10-03 | 2024-10-06 | 2025-06-16 | 2025-07-03
| JD3RZ07-1L62ST33727.R | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-1-L-62-ST -Remaining | 1 | 2024-10-07 | 2024-10-08 | 2025-08-09 | 2025-08-10
| JD3RZ07-1L62ST33728 | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-1-L-62-ST | 1 | 2024-10-07 | 2024-10-12 | 2025-07-05 | 2025-07-31
| JD3RZ07-1L62ST33728.R | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-1-L-62-ST -Remaining | 1 | 2024-10-13 | 2024-10-14 | 2025-08-30
| JD3RZ07-1L62ST33734 | Excavation Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-1-L-62-ST | 1 | 2024-10-14 | 2024-10-15 | 2025-08-17 | 2025-08-18
| JD3RZ07-1L62ST33735 | Soil Replacement and Bedding Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-1-L-62-ST | 1 | 2024-10-16 | 2024-10-17 | 2025-08-19 | 2025-08-20
| JD3RZ07-1L62ST33736 | Installing for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-1-L-62-ST | 1 | 2024-10-19 | 2024-10-20 | 2025-08-21 | 2025-08-23
| JD3RZ07-1L62ST33737 | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-1-L-62-ST | 1 | 2024-10-21 | 2024-10-22 | 2025-08-24 | 2025-08-25
| JD3RZ07-1L62ST33738 | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-1-L-62-ST | 1 | 2024-10-23 | 2024-10-24 | 2025-08-24
| JD3RZ07-1L62ST33749 | Excavation Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-1-L-62-ST | 1 | 2024-10-16 | 2024-10-17 | 2025-08-20 | 2025-08-21
| JD3RZ07-1L62ST33750 | Soil Replacement and Bedding Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-1-L-62-ST | 1 | 2024-10-19 | 2024-10-20 | 2025-08-23 | 2025-08-24
| JD3RZ07-1L62ST33751 | Installing for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-1-L-62-ST | 1 | 2024-10-21 | 2024-10-22 | 2025-08-25 | 2025-08-26
| JD3RZ07-1L62ST33752 | Primary Test for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-1-L-62-ST | 1 | 2024-10-23 | 2024-10-24 | 2025-08-27 | 2025-08-28
| JD3RZ07-1L62ST33753 | Backfilling Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-1-L-62-ST | 1 | 2024-10-26 | 2024-10-27 | 2025-08-31
| JD3RZ07-1L62ST33779 | Excavation Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z07-1-L-62-ST | 1 | 2024-10-16 | 2024-10-17 | 2025-08-20 | 2025-08-21
| JD3RZ07-1L62ST33780 | Soil Replacement and Bedding Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z07-1-L-62-ST | 1 | 2024-10-19 | 2024-10-20 | 2025-08-21 | 2025-08-24
| JD3RZ07-1L62ST33781 | Installing for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z07-1-L-62-ST | 1 | 2024-10-21 | 2024-10-22 | 2025-09-07 | 2025-09-10
| JD3RZ07-1L62ST33782 | Primary Test for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z07-1-L-62-ST | 1 | 2024-10-23 | 2024-10-24 | 2025-09-10 | 2025-09-11
| JD3RZ07-1L62ST33783 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z07-1-L-62-ST | 1 | 2024-10-26 | 2024-10-27 | 2025-09-13 | 2025-09-15
| JD3RZ07-1L62ST33857 | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-1-L-62-ST | 1 | 2024-10-16 | 2024-10-17 | 2025-08-20 | 2025-08-21
| JD3RZ07-1L62ST33858 | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-1-L-62-ST | 1 | 2024-10-19 | 2024-10-20 | 2025-08-23 | 2025-08-24
| JD3RZ07-1L62ST33859 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-1-L-62-ST | 1 | 2024-10-21 | 2024-10-22
| JD3RZ07-1L62ST33860 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-1-L-62-ST | 1 | 2024-10-23 | 2024-10-24
| JD3RZ07-1L62ST33861 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-1-L-62-ST | 1 | 2024-10-26 | 2024-10-27
| JD3RZ07-1L62ST33867 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-1-L-62-ST | 1 | 2024-09-25 | 2024-09-26 | 2025-06-01 | 2025-06-18
| JD3RZ07-1L62ST33867.R | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-1-L-62-ST -Remaining | 1 | 2024-09-28 | 2024-09-29
| JD3RZ07-1L62ST33868 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-1-L-62-ST | 1 | 2024-09-28 | 2024-09-30 | 2025-06-02 | 2025-06-19
| JD3RZ07-1L62ST33868.R | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-1-L-62-ST -Remaining | 1 | 2024-10-01 | 2024-10-02
| JD3RZ07-1L62ST33869 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-1-L-62-ST | 1 | 2024-10-01 | 2024-10-03 | 2025-06-10 | 2025-06-28
| JD3RZ07-1L62ST33869.R | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-1-L-62-ST -Remaining | 1 | 2024-10-05 | 2024-10-06
| JD3RZ07-1L62ST33870 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-1-L-62-ST | 1 | 2024-10-07 | 2024-10-08
| JD3RZ07-1L62ST33871 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-1-L-62-ST | 1 | 2024-10-09 | 2024-10-10
| JD3RZ07-1L62ST33882 | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-1-L-62-ST | 1 | 2024-09-28 | 2024-09-29 | 2025-06-01 | 2025-06-18
| JD3RZ07-1L62ST33882.R | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-1-L-62-ST -Remaining | 1 | 2024-09-30 | 2024-10-01
| JD3RZ07-1L62ST33883 | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-1-L-62-ST | 1 | 2024-09-30 | 2024-10-01 | 2025-06-02 | 2025-06-19
| JD3RZ07-1L62ST33883.R | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-1-L-62-ST -Remaining | 1 | 2024-10-02 | 2024-10-03
| JD3RZ07-1L62ST33884 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-1-L-62-ST | 1 | 2024-10-02 | 2024-10-03 | 2025-06-10 | 2025-06-28
| JD3RZ07-1L62ST33884.R | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-1-L-62-ST -Remaining | 1 | 2024-10-05 | 2024-10-06
| JD3RZ07-1L62ST33885 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-1-L-62-ST | 1 | 2024-10-07 | 2024-10-08
| JD3RZ07-1L62ST33886 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-1-L-62-ST | 1 | 2024-10-09 | 2024-10-10
| JD3RZ07-1L62ST33887 | Excavation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-1-L-62-ST | 1 | 2024-10-19 | 2024-10-20
| JD3RZ07-1L62ST33888 | Base Plain Concrete Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-1-L-62-ST | 1 | 2024-10-21 | 2024-10-22
| JD3RZ07-1L62ST33889 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-1-L-62-ST | 1 | 2024-10-23 | 2024-10-24
| JD3RZ07-1L62ST33890 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-1-L-62-ST | 1 | 2024-10-26 | 2024-10-27
| JD3RZ07-1L62ST33891 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-1-L-62-ST | 1 | 2024-10-28 | 2024-10-29
| JD3RZ07-1L62ST33892 | EXCAVATION Works for Catchbasine single - - B6.33 05 39.09-Z07-1-L-62-ST | 1 | 2024-10-16 | 2024-10-19
| JD3RZ07-1L62ST33893 | Catchbasine Installation Works For Catchbasine single - - B6.33 05 39.09-Z07-1-L-62-ST | 1 | 2024-10-20 | 2024-10-23
| JD3RZ07-1L62ST33894 | FINISHING Works For Catchbasine single - - B6.33 05 39.09-Z07-1-L-62-ST | 1 | 2024-10-24 | 2024-10-28
| JD3RZ07-1L62ST33895 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - - B6.33 05 39.09-Z07-1-L-62-ST | 1 | 2024-10-29 | 2024-10-31
| JD3RZ07-1L62ST33896 | EXCAVATION Works for Catchbasine double - - B6.33 05 39.10-Z07-1-L-62-ST | 1 | 2024-10-16 | 2024-10-17
| JD3RZ07-1L62ST33897 | Catchbasine Installation Works For Catchbasine double - - B6.33 05 39.10-Z07-1-L-62-ST | 1 | 2024-10-19 | 2024-10-21
| JD3RZ07-1L62ST33898 | FINISHING Works For Catchbasine double - - B6.33 05 39.10-Z07-1-L-62-ST | 1 | 2024-10-22 | 2024-10-24
| JD3RZ07-1L62ST33899 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - - B6.33 05 39.10-Z07-1-L-62-ST | 1 | 2024-10-26 | 2024-10-27
| JD3RZ07-1L62ST524361 | Concrete encasement for pipes- NNB6.33 42 11.25-Z07-1-L-60-ST | 1 | 2024-09-28 | 2024-10-03
| JD3RZ07-1L62TC34230 | Excavation Worksfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z07-1-L-62-TC | 1 | 2025-01-02 | 2025-01-04
| JD3RZ07-1L62TC34231 | Installationfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z07-1-L-62-TC | 1 | 2025-01-05 | 2025-01-08
| JD3RZ07-1L62TC34232 | Pouring Concrete Coverfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z07-1-L-62-TC | 1 | 2025-01-09 | 2025-01-13
| JD3RZ07-1L62TC34233 | Backfilling Worksfor Trenches 6-ways ducts, 50mm - 1x110 MM & 5 x 32MM- B2.33 71 19.02.TEL-Z07-1-L-62-TC | 1 | 2025-01-14 | 2025-01-15
| JD3RZ07-1L62TC34234 | Excavation and Bedding Worksfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z07-1-L-62-TC | 1 | 2025-01-22 | 2025-01-23
| JD3RZ07-1L62TC34235 | Installationfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z07-1-L-62-TC | 1 | 2025-01-25 | 2025-01-26
| JD3RZ07-1L62TC34236 | Backfilling Worksfor Manhole Type 1 - 120x120x150 CM- B2.33.71.19.13.01-Z07-1-L-62-TC | 1 | 2025-01-27 | 2025-01-28
| JD3RZ07-1L62TSE33950 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-1-L-62-TSE | 1 | 2024-11-02 | 2024-11-03
| JD3RZ07-1L62TSE33951 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-1-L-62-TSE | 1 | 2024-11-04 | 2024-11-05
| JD3RZ07-1L62TSE33952 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-1-L-62-TSE | 1 | 2024-11-06 | 2024-11-07
| JD3RZ07-1L62TSE33953 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-1-L-62-TSE | 1 | 2024-11-09 | 2024-11-10
| JD3RZ07-1L62TSE33954 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-1-L-62-TSE | 1 | 2024-11-28 | 2024-11-30
| JD3RZ07-1L62TSE33955 | Excavation Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z07-1-L-62-TSE | 1 | 2024-11-04 | 2024-11-07 | 2025-08-02 | 2025-08-05
| JD3RZ07-1L62TSE33956 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z07-1-L-62-TSE | 1 | 2024-11-09 | 2024-11-12 | 2025-08-06 | 2025-08-10
| JD3RZ07-1L62TSE33957 | installationfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z07-1-L-62-TSE | 1 | 2024-11-13 | 2024-11-21 | 2025-08-10 | 2025-08-18
| JD3RZ07-1L62TSE33958 | Testingfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z07-1-L-62-TSE | 1 | 2024-11-23 | 2024-11-27 | 2025-09-03 | 2025-09-09
| JD3RZ07-1L62TSE33959 | Backfilling Worksfor HDPE Pipe Lines 250 mm - depth from 0 to 1.5 m- B4.33 31 00.02-Z07-1-L-62-TSE | 1 | 2024-11-28 | 2024-12-03 | 2025-08-25 | 2025-09-14
| JD3RZ07-1L62TSE34075 | Installationfor gate valves 100 mm - - B4.33 14 19.01-Z07-1-L-62-TSE | 1 | 2024-11-23 | 2024-11-24
| JD3RZ07-1L62TSE34076 | Testing And Commtionningfor gate valves 100 mm - - B4.33 14 19.01-Z07-1-L-62-TSE | 1 | 2024-11-25 | 2024-11-26
| JD3RZ07-1L62TSE34077 | Installationfor gate valves 250 mm - - B4.33 14 19.02-Z07-1-L-62-TSE | 1 | 2024-11-23 | 2024-11-24
| JD3RZ07-1L62TSE34078 | Testing And Commtionningfor gate valves 250 mm - - B4.33 14 19.02-Z07-1-L-62-TSE | 1 | 2024-11-26 | 2024-11-27
| JD3RZ07-1L62TSE34093 | Installationfor Air valves 50 mm. - on pipes with diameter less than 315 mm- B4.33 14 19.15-Z07-1-L-62-TSE | 1 | 2024-11-23 | 2024-11-24
| JD3RZ07-1L62TSE34094 | Testing And Commtionningfor Air valves 50 mm. - on pipes with diameter less than 315 mm- B4.33 14 19.15-Z07-1-L-62-TSE | 1 | 2024-11-25 | 2024-11-26
| JD3RZ07-1L62TSE34123 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm- B4.33 14 13.10-Z07-1-L-62-TSE | 1 | 2024-11-09 | 2024-11-10
| JD3RZ07-1L62TSE34124 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm- B4.33 14 13.10-Z07-1-L-62-TSE | 1 | 2024-11-11 | 2024-11-12
| JD3RZ07-1L62TSE34125 | INSTALLATIONfor Air Valve Chamber - less than 315 mm- B4.33 14 13.10-Z07-1-L-62-TSE | 1 | 2024-11-13 | 2024-11-14
| JD3RZ07-1L62TSE34126 | Backfilling Worksfor Air Valve Chamber - less than 315 mm- B4.33 14 13.10-Z07-1-L-62-TSE | 1 | 2024-11-16 | 2024-11-17
| JD3RZ07-1L62WT33900 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-1-L-62-WT | 1 | 2024-11-04 | 2024-11-09 | 2025-08-02
| JD3RZ07-1L62WT33901 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-1-L-62-WT | 1 | 2024-11-10 | 2024-11-14 | 2025-08-07
| JD3RZ07-1L62WT33902 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-1-L-62-WT | 1 | 2024-11-16 | 2024-11-25 | 2025-08-13
| JD3RZ07-1L62WT33903 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-1-L-62-WT | 1 | 2024-11-26 | 2024-12-02 | 2025-09-20
| JD3RZ07-1L62WT33904 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-1-L-62-WT | 1 | 2024-12-03 | 2024-12-09 | 2025-08-26
| JD3RZ07-1L62WT33905 | Excavation Worksfor HDPE Pipes 225 mm - depth from 0 to 1.5 m- B3.33 14 13.02-Z07-1-L-62-WT | 1 | 2024-11-10 | 2024-11-11
| JD3RZ07-1L62WT33906 | Soil Replacement and Bedding Works for HDPE Pipes 225 mm - depth from 0 to 1.5 m- B3.33 14 13.02-Z07-1-L-62-WT | 1 | 2024-11-13 | 2024-11-14
| JD3RZ07-1L62WT33907 | Installing for HDPE Pipes 225 mm - depth from 0 to 1.5 m- B3.33 14 13.02-Z07-1-L-62-WT | 1 | 2024-11-16 | 2024-11-17
| JD3RZ07-1L62WT33908 | Testing for HDPE Pipes 225 mm - depth from 0 to 1.5 m- B3.33 14 13.02-Z07-1-L-62-WT | 1 | 2024-11-18 | 2024-11-19
| JD3RZ07-1L62WT33909 | Backfillingfor HDPE Pipes 225 mm - depth from 0 to 1.5 m- B3.33 14 13.02-Z07-1-L-62-WT | 1 | 2024-12-03 | 2024-12-04
| JD3RZ07-1L62WT33925 | INSTALLATIONfor gate valves 150 mm - - B3.33 14 19.01-Z07-1-L-62-WT | 1 | 2024-11-26 | 2024-11-27
| JD3RZ07-1L62WT33926 | TESTING AND COMMITIONfor gate valves 150 mm - - B3.33 14 19.01-Z07-1-L-62-WT | 1 | 2024-12-01 | 2024-12-02
| JD3RZ07-1L62WT33935 | EXCAVATION and Bedding Worksfor Fire Hydrant - - B3.33 14 19.08-Z07-1-L-62-WT | 1 | 2024-11-12 | 2024-11-13
| JD3RZ07-1L62WT33936 | INSTALLATIONfor Fire Hydrant - - B3.33 14 19.08-Z07-1-L-62-WT | 1 | 2024-11-14 | 2024-11-16
| JD3RZ07-1L62WT33937 | TESTING AND COMMITIONfor Fire Hydrant - - B3.33 14 19.08-Z07-1-L-62-WT | 1 | 2024-11-17 | 2024-11-18
| JD3RZ07C04ST100 | Channel excavation for Swales-B6.31 22 00.13-Z07-C-04-ST | 1 | 2025-01-30 | 2025-02-03 | 2025-09-13 | 2025-09-16
| JD3RZ07C04ST259411 | Excavation Works for GRP Pipe Line 1400 mm - depth from 1.51 to 2.50 m- NNB6.33 42 11.25-Z07-C-04-ST | 1 | 2025-06-09 | 2025-06-11
| JD3RZ07C04ST259421 | Soil Replacement and Bedding Works for GRP Pipe Line 1400 mm - depth from 1.51 to 2.50 m- NNB6.33 42 11.25-Z07-C-04-ST | 1 | 2025-06-12 | 2025-06-15
| JD3RZ07C04ST259431 | Installing for GRP Pipe Line 1400 mm - depth from 1.51 to 2.50 m- NNB6.33 42 11.25-Z07-C-04-ST | 1 | 2025-06-16 | 2025-06-19
| JD3RZ07C04ST259441 | Primary Test for GRP Pipe Line 1400 mm - depth from 1.51 to 2.50 m- NNB6.33 42 11.25-Z07-C-04-ST | 1 | 2025-07-05 | 2025-07-07
| JD3RZ07C04ST259451 | Backfilling Works for GRP Pipe Line 1400 mm - depth from 1.51 to 2.50 m- NNB6.33 42 11.25-Z07-C-04-ST | 1 | 2025-07-08 | 2025-07-13
| JD3RZ07C04ST25946 | Excavation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.01-Z07-C-04-ST | 1 | 2025-01-30 | 2025-02-08 | 2025-01-05
| JD3RZ07C04ST25947 | Plain Concrete Works For Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.01-Z07-C-04-ST | 1 | 2025-02-09 | 2025-02-11 | 2025-01-15 | 2025-02-11
| JD3RZ07C04ST25947.R | Plain Concrete Works For Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.01-Z07-C-04-ST | 1 | 2025-02-12 | 2025-02-13 | 2025-08-02
| JD3RZ07C04ST25948 | Raft Foundation for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.01-Z07-C-04-ST | 1 | 2025-02-12 | 2025-02-26 | 2025-01-25 | 2025-05-25
| JD3RZ07C04ST25948.R | Raft Foundation for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.01-Z07-C-04-ST | 1 | 2025-02-27 | 2025-03-01 | 2025-08-04
| JD3RZ07C04ST25949 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.01-Z07-C-04-ST | 1 | 2025-02-27 | 2025-03-22 | 2025-01-30 | 2025-07-31
| JD3RZ07C04ST25949.R | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.01-Z07-C-04-ST | 1 | 2025-03-23 | 2025-03-24 | 2025-08-06
| JD3RZ07C04ST25950 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.01-Z07-C-04-ST | 1 | 2025-03-23 | 2025-04-14 | 2025-02-25 | 2025-07-31
| JD3RZ07C04ST25950.R | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.01-Z07-C-04-ST | 1 | 2025-04-15 | 2025-04-16 | 2025-08-09
| JD3RZ07C04ST25951 | Isolation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.01-Z07-C-04-ST | 1 | 2025-04-15 | 2025-04-29 | 2025-03-05 | 2025-07-03
| JD3RZ07C04ST25951.R | Isolation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.01-Z07-C-04-ST | 1 | 2025-04-30 | 2025-05-01 | 2025-08-11
| JD3RZ07C04ST25952 | Backfilling Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.01-Z07-C-04-ST | 1 | 2025-04-30 | 2025-05-04 | 2025-05-05 | 2025-06-10
| JD3RZ07C04ST25952.R | Backfilling Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.01-Z07-C-04-ST | 1 | 2025-05-05 | 2025-05-06 | 2025-08-13
| JD3RZ07C04ST25967 | Excavation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-Z07-C-04-ST | 1 | 2025-05-07 | 2025-05-08
| JD3RZ07C04ST25968 | Plain Concrete Works For Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-Z07-C-04-ST | 1 | 2025-05-10 | 2025-05-11
| JD3RZ07C04ST25969 | Raft Foundation for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-Z07-C-04-ST | 1 | 2025-05-12 | 2025-05-13
| JD3RZ07C04ST25970 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-Z07-C-04-ST | 1 | 2025-05-14 | 2025-05-17
| JD3RZ07C04ST25971 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-Z07-C-04-ST | 1 | 2025-05-18 | 2025-05-20
| JD3RZ07C04ST25972 | Isolation Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-Z07-C-04-ST | 1 | 2025-05-21 | 2025-05-22
| JD3RZ07C04ST25973 | Backfilling Works for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.35 42 16.04-Z07-C-04-ST | 1 | 2025-05-24 | 2025-05-25
| JD3RZ07C04ST25974 | Excavation Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - - B6.34 42 16.05-Z07-C-04-ST | 1 | 2025-05-26 | 2025-06-08
| JD3RZ07C04ST25975 | Plain Concrete Works For Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - - B6.34 42 16.05-Z07-C-04-ST | 1 | 2025-06-09 | 2025-06-17
| JD3RZ07C04ST25976 | Raft Foundation for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - - B6.34 42 16.05-Z07-C-04-ST | 1 | 2025-06-18 | 2025-07-07
| JD3RZ07C04ST25977 | Wing Wall for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.34 42 16.05-Z07-C-04-ST | 1 | 2025-07-08 | 2025-07-31
| JD3RZ07C04ST25978 | Slab for Box Culvert Dim (1000x1000) depth from 2.51 to 3.50 - - B6.34 42 16.05-Z07-C-04-ST | 1 | 2025-08-02 | 2025-08-25
| JD3RZ07C04ST25979 | Isolation Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - - B6.34 42 16.05-Z07-C-04-ST | 1 | 2025-08-26 | 2025-09-14
| JD3RZ07C04ST25980 | Backfilling Works for Box Culvert Dim (3000x1500) depth from 1.51 to 2.50 - - B6.34 42 16.05-Z07-C-04-ST | 1 | 2025-09-15 | 2025-09-20
| JD3RZ07C04ST25981 | Excavation Works for Box Culvert Dim (3000x1500) depth from 2.51 to 3.50 - - B6.34 42 16.06-Z07-C-04-ST | 1 | 2025-09-21 | 2025-10-01
| JD3RZ07C04ST26024 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-C-04-ST | 1 | 2025-06-12 | 2025-06-14
| JD3RZ07C04ST26025 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-C-04-ST | 1 | 2025-06-15 | 2025-06-16
| JD3RZ07C04ST26026 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-C-04-ST | 1 | 2025-06-17 | 2025-06-18
| JD3RZ07C04ST26027 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-C-04-ST | 1 | 2025-06-19 | 2025-06-21
| JD3RZ07C04ST26028 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-C-04-ST | 1 | 2025-06-22 | 2025-06-23
| JD3RZ07C04ST26029 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-C-04-ST | 1 | 2025-06-15 | 2025-06-17
| JD3RZ07C04ST26030 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-C-04-ST | 1 | 2025-06-18 | 2025-06-24
| JD3RZ07C04ST26031 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-C-04-ST | 1 | 2025-06-25 | 2025-07-01
| JD3RZ07C04ST26032 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-C-04-ST | 1 | 2025-07-02 | 2025-07-06
| JD3RZ07C04ST26033 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-C-04-ST | 1 | 2025-07-07 | 2025-07-10
| JD3RZ07C04ST26039 | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-C-04-ST | 1 | 2025-06-18 | 2025-06-19
| JD3RZ07C04ST26040 | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-C-04-ST | 1 | 2025-06-21 | 2025-06-24
| JD3RZ07C04ST26041 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-C-04-ST | 1 | 2025-06-25 | 2025-06-29
| JD3RZ07C04ST26042 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-C-04-ST | 1 | 2025-06-30 | 2025-07-01
| JD3RZ07C04ST26043 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-C-04-ST | 1 | 2025-07-02 | 2025-07-03
| JD3RZ07C04ST26044 | Excavation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-C-04-ST | 1 | 2025-06-21 | 2025-06-22
| JD3RZ07C04ST26045 | Base Plain Concrete Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-C-04-ST | 1 | 2025-06-23 | 2025-06-24
| JD3RZ07C04ST26046 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-C-04-ST | 1 | 2025-06-25 | 2025-06-26
| JD3RZ07C04ST26047 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-C-04-ST | 1 | 2025-06-28 | 2025-06-29
| JD3RZ07C04ST26048 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-C-04-ST | 1 | 2025-07-05 | 2025-07-06
| JD3RZ07C04ST300 | Riprap with side slopes 1.5:1 for Swales-NB6.31 22 00.16-Z07-C-04-ST | 1 | 2025-02-04 | 2025-02-09 | 2025-09-16 | 2025-09-21
| JD3RZ07C04ST524342 | Concrete encasement for pipes- NNB6.33 42 11.25-MR-C-03-ST | 1 | 2025-06-21 | 2025-07-03
| JD3RZ07L52ST26544 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-52-ST | 1 | 2024-12-02 | 2024-12-03
| JD3RZ07L52ST26545 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-52-ST | 1 | 2024-12-04 | 2024-12-05
| JD3RZ07L52ST26546 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-52-ST | 1 | 2024-12-07 | 2024-12-08
| JD3RZ07L52ST26547 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-52-ST | 1 | 2024-12-09 | 2024-12-10
| JD3RZ07L52ST26548 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-52-ST | 1 | 2024-12-11 | 2024-12-12
| JD3RZ07L52ST26549 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-52-ST | 1 | 2024-12-02 | 2024-12-03 | 2024-12-11 | 2024-12-29
| JD3RZ07L52ST26549.R | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-52-ST -Remaining | 1 | 2024-12-04 | 2024-12-05 | 2025-08-10 | 2025-09-20
| JD3RZ07L52ST26550 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-52-ST | 1 | 2024-12-07 | 2024-12-08 | 2025-08-12 | 2025-09-20
| JD3RZ07L52ST26551 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-52-ST | 1 | 2024-12-07 | 2024-12-08 | 2025-08-17 | 2025-09-22
| JD3RZ07L52ST26552 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-52-ST | 1 | 2024-12-09 | 2024-12-10 | 2025-08-20
| JD3RZ07L52ST26553 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-52-ST | 1 | 2024-12-11 | 2024-12-12 | 2025-08-23
| JD3RZ07L52ST26554 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-52-ST | 1 | 2024-12-07 | 2024-12-08
| JD3RZ07L52ST26555 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-52-ST | 1 | 2024-12-09 | 2024-12-10
| JD3RZ07L52ST26556 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-52-ST | 1 | 2024-12-11 | 2024-12-12
| JD3RZ07L52ST26557 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-52-ST | 1 | 2024-12-14 | 2024-12-15
| JD3RZ07L52ST26558 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-52-ST | 1 | 2024-12-16 | 2024-12-17
| JD3RZ07L52ST26574 | Excavation Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-L-52-ST | 1 | 2024-12-02 | 2024-12-03 | 2024-12-04 | 2024-12-22
| JD3RZ07L52ST26575 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-L-52-ST | 1 | 2024-12-04 | 2024-12-05 | 2024-12-18 | 2025-01-14
| JD3RZ07L52ST26576 | Installing for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-L-52-ST | 1 | 2024-12-07 | 2024-12-08 | 2024-12-22 | 2025-01-27
| JD3RZ07L52ST26577 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-L-52-ST | 1 | 2024-12-09 | 2024-12-10 | 2025-01-02 | 2025-02-08
| JD3RZ07L52ST26578 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-L-52-ST | 1 | 2024-12-11 | 2024-12-14 | 2025-04-16 | 2025-05-22
| JD3RZ07L52ST26578.R | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-L-52-ST -Remaining | 1 | 2024-12-15 | 2024-12-16
| JD3RZ07L52ST26584 | Excavation Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-52-ST | 1 | 2024-12-15 | 2024-12-16 | 2025-04-12 | 2025-04-29
| JD3RZ07L52ST26584.R | Excavation Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-52-ST -Remaining | 1 | 2024-12-17 | 2024-12-18
| JD3RZ07L52ST26585 | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-52-ST | 1 | 2024-12-19 | 2024-12-21 | 2025-08-11 | 2025-08-12
| JD3RZ07L52ST26586 | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-52-ST | 1 | 2024-12-22 | 2024-12-23 | 2025-08-13 | 2025-08-14
| JD3RZ07L52ST26587 | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-52-ST | 1 | 2024-12-24 | 2024-12-25 | 2025-08-18
| JD3RZ07L52ST26588 | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-52-ST | 1 | 2024-12-26 | 2024-12-28 | 2025-08-20
| JD3RZ07L52ST26727 | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-52-ST | 1 | 2024-12-02 | 2024-12-03 | 2024-12-24 | 2025-01-11
| JD3RZ07L52ST26728 | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-52-ST | 1 | 2024-12-17 | 2024-12-18 | 2025-05-21 | 2025-06-08
| JD3RZ07L52ST26728.R | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-52-ST -Remaining | 1 | 2024-12-19 | 2024-12-21
| JD3RZ07L52ST26729 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-52-ST | 1 | 2024-12-22 | 2024-12-23 | 2025-08-13
| JD3RZ07L52ST26730 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-52-ST | 1 | 2024-12-24 | 2024-12-25
| JD3RZ07L52ST26731 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-52-ST | 1 | 2024-12-26 | 2024-12-28
| JD3RZ07L52ST26737 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-52-ST | 1 | 2024-12-09 | 2024-12-10
| JD3RZ07L52ST26738 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-52-ST | 1 | 2024-12-11 | 2024-12-12
| JD3RZ07L52ST26739 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-52-ST | 1 | 2024-12-14 | 2024-12-15
| JD3RZ07L52ST26740 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-52-ST | 1 | 2024-12-16 | 2024-12-17
| JD3RZ07L52ST26741 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-52-ST | 1 | 2024-12-18 | 2024-12-19
| JD3RZ07L52ST26742 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-L-52-ST | 1 | 2024-12-11 | 2024-12-12 | 2025-08-11 | 2025-08-12
| JD3RZ07L52ST26743 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-L-52-ST | 1 | 2024-12-14 | 2024-12-15 | 2025-08-13
| JD3RZ07L52ST26744 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-L-52-ST | 1 | 2024-12-16 | 2024-12-17 | 2025-08-16
| JD3RZ07L52ST26745 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-L-52-ST | 1 | 2024-12-18 | 2024-12-19
| JD3RZ07L52ST26746 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-L-52-ST | 1 | 2024-12-21 | 2024-12-22
| JD3RZ07L52ST26762 | EXCAVATION Works for Catchbasine single - - B6.33 05 39.09-Z07-L-52-ST | 1 | 2024-12-14 | 2024-12-15
| JD3RZ07L52ST26763 | Catchbasine Installation Works For Catchbasine single - - B6.33 05 39.09-Z07-L-52-ST | 1 | 2024-12-16 | 2024-12-17
| JD3RZ07L52ST26764 | FINISHING Works For Catchbasine single - - B6.33 05 39.09-Z07-L-52-ST | 1 | 2024-12-18 | 2024-12-19
| JD3RZ07L52ST26765 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - - B6.33 05 39.09-Z07-L-52-ST | 1 | 2024-12-21 | 2024-12-22
| JD3RZ07L52ST26766 | EXCAVATION Works for Catchbasine double - - B6.33 05 39.10-Z07-L-52-ST | 1 | 2024-12-16 | 2024-12-17
| JD3RZ07L52ST26767 | Catchbasine Installation Works For Catchbasine double - - B6.33 05 39.10-Z07-L-52-ST | 1 | 2024-12-18 | 2024-12-19
| JD3RZ07L52ST26768 | FINISHING Works For Catchbasine double - - B6.33 05 39.10-Z07-L-52-ST | 1 | 2024-12-21 | 2024-12-22
| JD3RZ07L52ST26769 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - - B6.33 05 39.10-Z07-L-52-ST | 1 | 2024-12-23 | 2024-12-24
| JD3RZ07L52TSE26820 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-52-TSE | 1 | 2024-12-25 | 2024-12-26
| JD3RZ07L52TSE26821 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-52-TSE | 1 | 2024-12-28 | 2024-12-29
| JD3RZ07L52TSE26822 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-52-TSE | 1 | 2024-12-30 | 2024-12-31
| JD3RZ07L52TSE26823 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-52-TSE | 1 | 2025-01-01 | 2025-01-02
| JD3RZ07L52TSE26824 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-52-TSE | 1 | 2025-01-04 | 2025-01-05
| JD3RZ07L52TSE26835 | Excavation Worksfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-52-TSE | 1 | 2024-12-28 | 2024-12-29
| JD3RZ07L52TSE26836 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-52-TSE | 1 | 2024-12-30 | 2024-12-31
| JD3RZ07L52TSE26837 | Installing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-52-TSE | 1 | 2025-01-01 | 2025-01-02
| JD3RZ07L52TSE26838 | Testing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-52-TSE | 1 | 2025-01-04 | 2025-01-05
| JD3RZ07L52TSE26839 | Backfillingfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-52-TSE | 1 | 2025-01-06 | 2025-01-07
| JD3RZ07L52TSE26840 | Excavation Worksfor HDPE Pipes 315 mm - depth from 2.51 to 3.5 m- B4.33 31 00.05-Z07-L-52-TSE | 1 | 2024-12-30 | 2024-12-31
| JD3RZ07L52TSE26841 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 2.51 to 3.5 m- B4.33 31 00.05-Z07-L-52-TSE | 1 | 2025-01-01 | 2025-01-02
| JD3RZ07L52TSE26842 | Installing for HDPE Pipes 315 mm - depth from 2.51 to 3.5 m- B4.33 31 00.05-Z07-L-52-TSE | 1 | 2025-01-04 | 2025-01-05
| JD3RZ07L52TSE26843 | Testing for HDPE Pipes 315 mm - depth from 2.51 to 3.5 m- B4.33 31 00.05-Z07-L-52-TSE | 1 | 2025-01-06 | 2025-01-07
| JD3RZ07L52TSE26844 | Backfillingfor HDPE Pipes 315 mm - depth from 2.51 to 3.5 m- B4.33 31 00.05-Z07-L-52-TSE | 1 | 2025-01-08 | 2025-01-09
| JD3RZ07L52TSE26845 | Excavation Worksfor HDPE Pipes 315 mm - depth from 3.51 to 4.5 m- B4.33 31 00.06-Z07-L-52-TSE | 1 | 2025-01-01 | 2025-01-02
| JD3RZ07L52TSE26846 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 3.51 to 4.5 m- B4.33 31 00.06-Z07-L-52-TSE | 1 | 2025-01-04 | 2025-01-05
| JD3RZ07L52TSE26847 | Installing for HDPE Pipes 315 mm - depth from 3.51 to 4.5 m- B4.33 31 00.06-Z07-L-52-TSE | 1 | 2025-01-06 | 2025-01-07
| JD3RZ07L52TSE26848 | Testing for HDPE Pipes 315 mm - depth from 3.51 to 4.5 m- B4.33 31 00.06-Z07-L-52-TSE | 1 | 2025-01-08 | 2025-01-09
| JD3RZ07L52TSE26849 | Backfillingfor HDPE Pipes 315 mm - depth from 3.51 to 4.5 m- B4.33 31 00.06-Z07-L-52-TSE | 1 | 2025-01-11 | 2025-01-12
| JD3RZ07L52TSE26945 | Installationfor gate valves 100 mm - - B4.33 14 19.01-Z07-L-52-TSE | 1 | 2025-01-08 | 2025-01-09
| JD3RZ07L52TSE26946 | Testing And Commtionningfor gate valves 100 mm - - B4.33 14 19.01-Z07-L-52-TSE | 1 | 2025-01-11 | 2025-01-12
| JD3RZ07L52WT26770 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-52-WT | 1 | 2025-01-13 | 2025-01-14
| JD3RZ07L52WT26771 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-52-WT | 1 | 2025-01-15 | 2025-01-16
| JD3RZ07L52WT26772 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-52-WT | 1 | 2025-01-18 | 2025-01-19
| JD3RZ07L52WT26773 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-52-WT | 1 | 2025-01-20 | 2025-01-21
| JD3RZ07L52WT26774 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-52-WT | 1 | 2025-01-22 | 2025-01-23
| JD3RZ07L52WT26805 | EXCAVATION and Bedding Worksfor Fire Hydrant - - B3.33 14 19.08-Z07-L-52-WT | 1 | 2025-01-15 | 2025-01-16
| JD3RZ07L52WT26806 | INSTALLATIONfor Fire Hydrant - - B3.33 14 19.08-Z07-L-52-WT | 1 | 2025-01-18 | 2025-01-19
| JD3RZ07L52WT26807 | TESTING AND COMMITIONfor Fire Hydrant - - B3.33 14 19.08-Z07-L-52-WT | 1 | 2025-01-20 | 2025-01-21
| JD3RZ07L63ST27257 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-63-ST | 1 | 2024-12-02 | 2024-12-04 | 2024-12-28 | 2025-02-02
| JD3RZ07L63ST27257.R | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-63-ST -Remaining | 1 | 2024-12-05 | 2024-12-07 | 2025-08-02 | 2025-08-03
| JD3RZ07L63ST27258 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-63-ST | 1 | 2024-12-05 | 2024-12-08 | 2025-01-26 | 2025-03-03
| JD3RZ07L63ST27258.R | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-63-ST -Re | 1 | 2024-12-09 | 2024-12-10 | 2025-08-04 | 2025-08-05
| JD3RZ07L63ST27259 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-63-ST | 1 | 2024-12-09 | 2024-12-12 | 2025-01-28 | 2025-03-05
| JD3RZ07L63ST27259.R | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-63-ST -Remaining | 1 | 2024-12-14 | 2024-12-15 | 2025-08-06 | 2025-08-07
| JD3RZ07L63ST27260 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-63-ST | 1 | 2024-12-14 | 2024-12-17 | 2025-01-29 | 2025-03-06
| JD3RZ07L63ST27260.R | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-63-ST -Remaining | 1 | 2024-12-18 | 2024-12-19 | 2025-08-09 | 2025-08-10
| JD3RZ07L63ST27261 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-63-ST | 1 | 2024-12-18 | 2024-12-23 | 2025-04-05 | 2025-05-29
| JD3RZ07L63ST27261.R | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-63-ST -Remaining | 1 | 2024-12-24 | 2024-12-25
| JD3RZ07L63ST27262 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-63-ST | 1 | 2024-12-05 | 2024-12-08 | 2025-04-27 | 2025-05-14
| JD3RZ07L63ST27262.R | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-63-ST -Remaining | 1 | 2024-12-09 | 2024-12-10
| JD3RZ07L63ST27263 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-63-ST | 1 | 2024-12-09 | 2024-12-11 | 2025-04-15 | 2025-05-03
| JD3RZ07L63ST27263.R | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-63-ST -Rem | 1 | 2024-12-12 | 2024-12-14
| JD3RZ07L63ST27264 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-63-ST | 1 | 2024-12-12 | 2024-12-15 | 2025-04-22 | 2025-05-19
| JD3RZ07L63ST27264.R | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-63-ST -Remaining | 1 | 2024-12-16 | 2024-12-17 | 2025-08-30
| JD3RZ07L63ST27265 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-63-ST | 1 | 2024-12-18 | 2024-12-21
| JD3RZ07L63ST27266 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-63-ST | 1 | 2025-01-04 | 2025-01-07 | 2025-09-16
| JD3RZ07L63ST27267 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-63-ST | 1 | 2024-12-11 | 2024-12-12 | 2025-08-06 | 2025-08-07
| JD3RZ07L63ST27268 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-63-ST | 1 | 2024-12-14 | 2024-12-15 | 2025-08-09 | 2025-08-10
| JD3RZ07L63ST27269 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-63-ST | 1 | 2024-12-16 | 2024-12-17 | 2025-08-11 | 2025-08-12
| JD3RZ07L63ST27270 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-63-ST | 1 | 2024-12-18 | 2024-12-19
| JD3RZ07L63ST27271 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-63-ST | 1 | 2025-01-04 | 2025-01-05
| JD3RZ07L63ST27272 | Excavation Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-63-ST | 1 | 2024-12-14 | 2024-12-15 | 2025-08-09 | 2025-08-10
| JD3RZ07L63ST27273 | Soil Replacement and Bedding Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-63-ST | 1 | 2024-12-16 | 2024-12-17 | 2025-08-11 | 2025-08-12
| JD3RZ07L63ST27274 | Installing for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-63-ST | 1 | 2024-12-18 | 2024-12-19 | 2025-08-13 | 2025-08-14
| JD3RZ07L63ST27275 | Primary Test for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-63-ST | 1 | 2024-12-21 | 2024-12-22
| JD3RZ07L63ST27276 | Backfilling Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-63-ST | 1 | 2025-01-04 | 2025-01-05 | 2025-09-14 | 2025-09-18
| JD3RZ07L63ST27277 | Excavation Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z07-L-63-ST | 1 | 2024-12-16 | 2024-12-17 | 2025-08-11 | 2025-08-12
| JD3RZ07L63ST27278 | Soil Replacement and Bedding Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z07-L-63-ST | 1 | 2024-12-18 | 2024-12-19 | 2025-08-13 | 2025-08-14
| JD3RZ07L63ST27279 | Installing for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z07-L-63-ST | 1 | 2024-12-21 | 2024-12-22 | 2025-08-16 | 2025-08-17
| JD3RZ07L63ST27280 | Primary Test for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z07-L-63-ST | 1 | 2024-12-23 | 2024-12-24
| JD3RZ07L63ST27281 | Backfilling Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z07-L-63-ST | 1 | 2025-01-04 | 2025-01-05 | 2025-09-14 | 2025-09-18
| JD3RZ07L63ST27287 | Excavation Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-L-63-ST | 1 | 2024-12-09 | 2024-12-11 | 2025-04-14 | 2025-05-01
| JD3RZ07L63ST27287.R | Excavation Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-L-63-ST -Remaining | 1 | 2024-12-18 | 2024-12-19 | 2025-08-13 | 2025-08-14
| JD3RZ07L63ST27288 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-L-63-ST | 1 | 2024-12-12 | 2024-12-15 | 2025-04-15 | 2025-05-03
| JD3RZ07L63ST27288.R | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-L-63-ST -Rem | 1 | 2024-12-21 | 2024-12-22 | 2025-08-16 | 2025-08-17
| JD3RZ07L63ST27289 | Installing for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-L-63-ST | 1 | 2024-12-16 | 2024-12-19 | 2025-04-22 | 2025-05-10
| JD3RZ07L63ST27289.R | Installing for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-L-63-ST -Remaining | 1 | 2024-12-23 | 2024-12-24 | 2025-08-18 | 2025-08-19
| JD3RZ07L63ST27290 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-L-63-ST | 1 | 2024-12-25 | 2024-12-28
| JD3RZ07L63ST27291 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-L-63-ST | 1 | 2025-01-04 | 2025-01-08
| JD3RZ07L63ST27297 | Excavation Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-63-ST | 1 | 2024-12-02 | 2024-12-03 | 2025-04-15 | 2025-05-03
| JD3RZ07L63ST27298 | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-63-ST | 1 | 2024-12-04 | 2024-12-05 | 2025-04-16 | 2025-05-04
| JD3RZ07L63ST27299 | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-63-ST | 1 | 2024-12-07 | 2024-12-08 | 2025-04-22 | 2025-05-10
| JD3RZ07L63ST27300 | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-63-ST | 1 | 2024-12-09 | 2024-12-10 | 2025-05-19 | 2025-06-05
| JD3RZ07L63ST27301 | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-63-ST | 1 | 2025-01-04 | 2025-01-05
| JD3RZ07L63ST27307 | Excavation Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-63-ST | 1 | 2024-12-12 | 2024-12-14 | 2025-04-14 | 2025-05-01
| JD3RZ07L63ST27307.R | Excavation Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-63-ST -Remaining | 1 | 2024-12-21 | 2024-12-22
| JD3RZ07L63ST27308 | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-63-ST | 1 | 2024-12-15 | 2024-12-16 | 2025-04-15 | 2025-05-03
| JD3RZ07L63ST27308.R | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-63-ST -Rem | 1 | 2024-12-23 | 2024-12-24
| JD3RZ07L63ST27309 | Installing for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-63-ST | 1 | 2024-12-17 | 2024-12-18 | 2025-05-11 | 2025-05-28
| JD3RZ07L63ST27309.R | Installing for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-63-ST -Remaining | 1 | 2024-12-25 | 2024-12-26
| JD3RZ07L63ST27310 | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-63-ST | 1 | 2024-12-19 | 2024-12-21 | 2025-07-05 | 2025-07-22
| JD3RZ07L63ST27310.R | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-63-ST -Remaining | 1 | 2024-12-28 | 2024-12-29
| JD3RZ07L63ST27311 | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-63-ST | 1 | 2025-01-04 | 2025-01-05
| JD3RZ07L63ST27317 | Excavation Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-63-ST | 1 | 2024-12-02 | 2024-12-03 | 2025-04-14 | 2025-05-01
| JD3RZ07L63ST27318 | Soil Replacement and Bedding Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-63-ST | 1 | 2024-12-04 | 2024-12-05 | 2025-04-15 | 2025-05-03
| JD3RZ07L63ST27319 | Installing for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-63-ST | 1 | 2024-12-16 | 2024-12-17 | 2025-05-12 | 2025-05-29
| JD3RZ07L63ST27320 | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-63-ST | 1 | 2024-12-30 | 2024-12-31
| JD3RZ07L63ST27321 | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-63-ST | 1 | 2025-01-04 | 2025-01-05
| JD3RZ07L63ST27332 | Excavation Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-L-63-ST | 1 | 2024-12-18 | 2024-12-19 | 2025-08-13 | 2025-08-14
| JD3RZ07L63ST27333 | Soil Replacement and Bedding Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-L-63-ST | 1 | 2024-12-21 | 2024-12-22 | 2025-08-16 | 2025-08-17
| JD3RZ07L63ST27334 | Installing for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-L-63-ST | 1 | 2024-12-23 | 2024-12-24 | 2025-08-23 | 2025-08-30
| JD3RZ07L63ST27335 | Primary Test for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-L-63-ST | 1 | 2024-12-25 | 2024-12-26
| JD3RZ07L63ST27336 | Backfilling Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-L-63-ST | 1 | 2025-01-04 | 2025-01-05
| JD3RZ07L63ST27440 | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-63-ST | 1 | 2024-12-21 | 2024-12-22 | 2025-08-06 | 2025-08-07
| JD3RZ07L63ST27441 | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-63-ST | 1 | 2024-12-23 | 2024-12-25 | 2025-08-09 | 2025-08-11
| JD3RZ07L63ST27442 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-63-ST | 1 | 2024-12-26 | 2024-12-29
| JD3RZ07L63ST27443 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-63-ST | 1 | 2024-12-30 | 2024-12-31
| JD3RZ07L63ST27444 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-63-ST | 1 | 2025-01-01 | 2025-01-02
| JD3RZ07L63ST27450 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-63-ST | 1 | 2024-12-15 | 2024-12-16 | 2025-04-15 | 2025-05-03
| JD3RZ07L63ST27450.R | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-63-ST -Remaining | 1 | 2024-12-23 | 2024-12-24 | 2025-08-09 | 2025-08-10
| JD3RZ07L63ST27451 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-63-ST | 1 | 2024-12-17 | 2024-12-18 | 2025-05-20 | 2025-06-07
| JD3RZ07L63ST27451.R | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-63-ST -Remaining | 1 | 2024-12-25 | 2024-12-26 | 2025-08-11 | 2025-08-12
| JD3RZ07L63ST27452 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-63-ST | 1 | 2024-12-28 | 2024-12-29
| JD3RZ07L63ST27453 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-63-ST | 1 | 2024-12-30 | 2024-12-31
| JD3RZ07L63ST27454 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-63-ST | 1 | 2025-01-01 | 2025-01-02
| JD3RZ07L63ST27470 | Excavation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-L-63-ST | 1 | 2024-12-23 | 2024-12-24
| JD3RZ07L63ST27471 | Base Plain Concrete Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-L-63-ST | 1 | 2024-12-25 | 2024-12-26
| JD3RZ07L63ST27472 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-L-63-ST | 1 | 2024-12-28 | 2024-12-29
| JD3RZ07L63ST27473 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-L-63-ST | 1 | 2024-12-30 | 2024-12-31
| JD3RZ07L63ST27474 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-L-63-ST | 1 | 2025-01-01 | 2025-01-02
| JD3RZ07L63ST27475 | EXCAVATION Works for Catchbasine single - - B6.33 05 39.09-Z07-L-63-ST | 1 | 2024-12-25 | 2024-12-28
| JD3RZ07L63ST27476 | Catchbasine Installation Works For Catchbasine single - - B6.33 05 39.09-Z07-L-63-ST | 1 | 2024-12-29 | 2025-01-01
| JD3RZ07L63ST27477 | FINISHING Works For Catchbasine single - - B6.33 05 39.09-Z07-L-63-ST | 1 | 2025-01-02 | 2025-01-06
| JD3RZ07L63ST27478 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - - B6.33 05 39.09-Z07-L-63-ST | 1 | 2025-01-07 | 2025-01-09
| JD3RZ07L63ST27479 | EXCAVATION Works for Catchbasine double - - B6.33 05 39.10-Z07-L-63-ST | 1 | 2024-12-29 | 2024-12-30
| JD3RZ07L63ST27480 | Catchbasine Installation Works For Catchbasine double - - B6.33 05 39.10-Z07-L-63-ST | 1 | 2024-12-31 | 2025-01-02
| JD3RZ07L63ST27481 | FINISHING Works For Catchbasine double - - B6.33 05 39.10-Z07-L-63-ST | 1 | 2025-01-04 | 2025-01-06
| JD3RZ07L63ST27482 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - - B6.33 05 39.10-Z07-L-63-ST | 1 | 2025-01-07 | 2025-01-08
| JD3RZ07L63ST524365 | Concrete encasement for pipes- NNB6.33 42 11.25-Z07-L-63-ST | 1 | 2024-12-28 | 2025-01-02
| JD3RZ07L63TSE27533 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-63-TSE | 1 | 2025-01-11 | 2025-01-12
| JD3RZ07L63TSE27534 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-63-TSE | 1 | 2025-01-13 | 2025-01-14
| JD3RZ07L63TSE27535 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-63-TSE | 1 | 2025-01-15 | 2025-01-16
| JD3RZ07L63TSE27536 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-63-TSE | 1 | 2025-01-18 | 2025-01-19
| JD3RZ07L63TSE27537 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-63-TSE | 1 | 2025-01-20 | 2025-01-21
| JD3RZ07L63TSE27548 | Excavation Worksfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-63-TSE | 1 | 2024-12-17 | 2024-12-21 | 2025-05-01 | 2025-05-28
| JD3RZ07L63TSE27548.R | Excavation Worksfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-63-TSE -Remaining | 1 | 2025-01-13 | 2025-01-14 | 2025-08-05 | 2025-08-06
| JD3RZ07L63TSE27549 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-63-TSE | 1 | 2024-12-22 | 2024-12-25 | 2025-05-10 | 2025-06-15
| JD3RZ07L63TSE27549.R | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-63-TSE -Remai | 1 | 2025-01-15 | 2025-01-16 | 2025-08-08 | 2025-08-09
| JD3RZ07L63TSE27550 | Installing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-63-TSE | 1 | 2024-12-26 | 2025-01-04 | 2025-05-17 | 2025-07-31
| JD3RZ07L63TSE27550.R | Installing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-63-TSE -Remaining | 1 | 2025-01-18 | 2025-01-19 | 2025-08-11 | 2025-08-12
| JD3RZ07L63TSE27551 | Testing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-63-TSE | 1 | 2025-01-20 | 2025-01-25 | 2025-08-18 | 2025-08-20
| JD3RZ07L63TSE27552 | Backfillingfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-63-TSE | 1 | 2025-01-26 | 2025-01-30 | 2025-08-14 | 2025-08-19
| JD3RZ07L63TSE27658 | Installationfor gate valves 100 mm - - B4.33 14 19.01-Z07-L-63-TSE | 1 | 2025-01-15 | 2025-01-16
| JD3RZ07L63TSE27659 | Testing And Commtionningfor gate valves 100 mm - - B4.33 14 19.01-Z07-L-63-TSE | 1 | 2025-01-18 | 2025-01-19
| JD3RZ07L63TSE27662 | Installationfor butterfly valves 300 mm. - - B4.33 14 19.03-Z07-L-63-TSE | 1 | 2025-02-17 | 2025-02-18
| JD3RZ07L63TSE27663 | Testing And Commtionningfor butterfly valves 300 mm. - - B4.33 14 19.03-Z07-L-63-TSE | 1 | 2025-02-19 | 2025-02-20
| JD3RZ07L63TSE27670 | Installationfor Wash-Out valves 100 mm. - on pipes with diameter 110-400 mm- B4.33 14 19.07-Z07-L-63-TSE | 1 | 2025-01-15 | 2025-01-16
| JD3RZ07L63TSE27671 | Testing And Commtionningfor Wash-Out valves 100 mm. - on pipes with diameter 110-400 mm- B4.33 14 19.07-Z07-L-63-TSE | 1 | 2025-01-18 | 2025-01-19
| JD3RZ07L63TSE27676 | Installationfor Air valves 50 mm. - on pipes with diameter less than 315 mm- B4.33 14 19.15-Z07-L-63-TSE | 1 | 2025-01-15 | 2025-01-16
| JD3RZ07L63TSE27677 | Testing And Commtionningfor Air valves 50 mm. - on pipes with diameter less than 315 mm- B4.33 14 19.15-Z07-L-63-TSE | 1 | 2025-01-18 | 2025-01-19
| JD3RZ07L63TSE27682 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-Z07-L-63-TSE | 1 | 2025-01-15 | 2025-01-16
| JD3RZ07L63TSE27683 | Plain Concrete Worksfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-Z07-L-63-TSE | 1 | 2025-01-18 | 2025-01-19
| JD3RZ07L63TSE27684 | INSTALLATIONfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-Z07-L-63-TSE | 1 | 2025-01-20 | 2025-01-21
| JD3RZ07L63TSE27685 | Backfilling Worksfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-Z07-L-63-TSE | 1 | 2025-01-22 | 2025-01-23
| JD3RZ07L63TSE27694 | EXCAVATION and Bedding Worksfor Wash-out Valve Chamber - 110 to 400 MM- B4.33 14 13.06-Z07-L-63-TSE | 1 | 2025-01-18 | 2025-01-19
| JD3RZ07L63TSE27695 | Plain Concrete Worksfor Wash-out Valve Chamber - 110 to 400 MM- B4.33 14 13.06-Z07-L-63-TSE | 1 | 2025-01-20 | 2025-01-21
| JD3RZ07L63TSE27696 | INSTALLATIONfor Wash-out Valve Chamber - 110 to 400 MM- B4.33 14 13.06-Z07-L-63-TSE | 1 | 2025-01-22 | 2025-01-23
| JD3RZ07L63TSE27697 | Backfilling Worksfor Wash-out Valve Chamber - 110 to 400 MM- B4.33 14 13.06-Z07-L-63-TSE | 1 | 2025-01-25 | 2025-01-26
| JD3RZ07L63TSE27706 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm- B4.33 14 13.10-Z07-L-63-TSE | 1 | 2025-01-20 | 2025-01-21
| JD3RZ07L63TSE27707 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm- B4.33 14 13.10-Z07-L-63-TSE | 1 | 2025-01-22 | 2025-01-23
| JD3RZ07L63TSE27708 | INSTALLATIONfor Air Valve Chamber - less than 315 mm- B4.33 14 13.10-Z07-L-63-TSE | 1 | 2025-01-25 | 2025-01-26
| JD3RZ07L63TSE27709 | Backfilling Worksfor Air Valve Chamber - less than 315 mm- B4.33 14 13.10-Z07-L-63-TSE | 1 | 2025-01-27 | 2025-01-28
| JD3RZ07L63WT27483 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-63-WT | 1 | 2025-02-01 | 2025-02-02
| JD3RZ07L63WT27484 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-63-WT | 1 | 2025-02-03 | 2025-02-04
| JD3RZ07L63WT27485 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-63-WT | 1 | 2025-02-05 | 2025-02-06
| JD3RZ07L63WT27486 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-63-WT | 1 | 2025-02-08 | 2025-02-09
| JD3RZ07L63WT27487 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-63-WT | 1 | 2025-02-12 | 2025-02-13
| JD3RZ07L63WT27518 | EXCAVATION and Bedding Worksfor Fire Hydrant - - B3.33 14 19.08-Z07-L-63-WT | 1 | 2025-02-03 | 2025-02-04
| JD3RZ07L63WT27519 | INSTALLATIONfor Fire Hydrant - - B3.33 14 19.08-Z07-L-63-WT | 1 | 2025-02-08 | 2025-02-09
| JD3RZ07L63WT27520 | TESTING AND COMMITIONfor Fire Hydrant - - B3.33 14 19.08-Z07-L-63-WT | 1 | 2025-02-10 | 2025-02-11
| JD3RZ07L64ST27970 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-64-ST | 1 | 2024-12-02 | 2024-12-04 | 2024-11-24 | 2024-12-21
| JD3RZ07L64ST27970.R | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-64-ST -Remaining | 1 | 2025-01-13 | 2025-01-14
| JD3RZ07L64ST27971 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-64-ST | 1 | 2024-12-05 | 2024-12-08 | 2024-11-27 | 2025-01-02
| JD3RZ07L64ST27971.R | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-64-ST -Re | 1 | 2025-01-15 | 2025-01-16
| JD3RZ07L64ST27972 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-64-ST | 1 | 2024-12-09 | 2024-12-12 | 2024-12-01 | 2025-01-06
| JD3RZ07L64ST27972.R | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-64-ST -Remaining | 1 | 2025-01-18 | 2025-01-19
| JD3RZ07L64ST27973 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-64-ST | 1 | 2024-12-14 | 2024-12-17 | 2025-02-05 | 2025-03-13
| JD3RZ07L64ST27973.R | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-64-ST -Remaining | 1 | 2025-01-20 | 2025-01-21
| JD3RZ07L64ST27974 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-64-ST | 1 | 2025-02-10 | 2025-02-15 | 2025-04-05 | 2025-05-20
| JD3RZ07L64ST27974.R | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-64-ST -Remaining | 1 | 2025-02-16 | 2025-02-17
| JD3RZ07L64ST27975 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-64-ST | 1 | 2025-01-15 | 2025-01-16
| JD3RZ07L64ST27976 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-64-ST | 1 | 2025-01-18 | 2025-01-19
| JD3RZ07L64ST27977 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-64-ST | 1 | 2025-01-20 | 2025-01-21
| JD3RZ07L64ST27978 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-64-ST | 1 | 2025-01-22 | 2025-01-23
| JD3RZ07L64ST27979 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-64-ST | 1 | 2025-02-12 | 2025-02-13
| JD3RZ07L64ST27980 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-64-ST | 1 | 2025-01-18 | 2025-01-19
| JD3RZ07L64ST27981 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-64-ST | 1 | 2025-01-20 | 2025-01-21
| JD3RZ07L64ST27982 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-64-ST | 1 | 2025-01-22 | 2025-01-23
| JD3RZ07L64ST27983 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-64-ST | 1 | 2025-01-25 | 2025-01-26
| JD3RZ07L64ST27984 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-64-ST | 1 | 2025-02-12 | 2025-02-13
| JD3RZ07L64ST27990 | Excavation Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z07-L-64-ST | 1 | 2025-01-15 | 2025-01-16 | 2025-04-05 | 2025-04-22
| JD3RZ07L64ST27991 | Soil Replacement and Bedding Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z07-L-64-ST | 1 | 2025-01-18 | 2025-01-19 | 2025-04-08 | 2025-04-26
| JD3RZ07L64ST27992 | Installing for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z07-L-64-ST | 1 | 2025-01-20 | 2025-01-21 | 2025-04-13 | 2025-04-30
| JD3RZ07L64ST27993 | Primary Test for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z07-L-64-ST | 1 | 2025-01-22 | 2025-01-23 | 2025-04-15 | 2025-05-03
| JD3RZ07L64ST27994 | Backfilling Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z07-L-64-ST | 1 | 2025-02-10 | 2025-02-11 | 2025-04-20 | 2025-05-07
| JD3RZ07L64ST27994.R | Backfilling Works for GRP Pipe Line 500 mm - depth from 1.51 to 2.50 m- B6.33 42 11.04-Z07-L-64-ST -Remaining | 1 | 2025-02-12 | 2025-02-13
| JD3RZ07L64ST28000 | Excavation Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-L-64-ST | 1 | 2025-01-18 | 2025-01-19 | 2025-01-21 | 2025-02-08
| JD3RZ07L64ST28001 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-L-64-ST | 1 | 2025-01-20 | 2025-01-21 | 2025-04-08 | 2025-04-26
| JD3RZ07L64ST28002 | Installing for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-L-64-ST | 1 | 2025-01-22 | 2025-01-23 | 2025-04-13 | 2025-04-30
| JD3RZ07L64ST28003 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-L-64-ST | 1 | 2025-01-25 | 2025-01-26 | 2025-04-15 | 2025-05-03
| JD3RZ07L64ST28004 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-L-64-ST | 1 | 2025-02-10 | 2025-02-11 | 2025-04-20 | 2025-05-07
| JD3RZ07L64ST28004.R | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-L-64-ST -Remaining | 1 | 2025-02-12 | 2025-02-13
| JD3RZ07L64ST28010 | Excavation Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-64-ST | 1 | 2025-01-20 | 2025-01-21 | 2025-01-21 | 2025-02-08
| JD3RZ07L64ST28010.R | Excavation Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-64-ST -Remaining | 1 | 2025-01-22 | 2025-01-23
| JD3RZ07L64ST28011 | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-64-ST | 1 | 2025-01-22 | 2025-01-23 | 2025-03-04 | 2025-03-22
| JD3RZ07L64ST28011.R | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-64-ST -Rem | 1 | 2025-01-25 | 2025-01-26
| JD3RZ07L64ST28012 | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-64-ST | 1 | 2025-01-25 | 2025-01-26 | 2025-03-05 | 2025-03-23
| JD3RZ07L64ST28012.R | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-64-ST -Remaining | 1 | 2025-01-27 | 2025-01-28
| JD3RZ07L64ST28013 | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-64-ST | 1 | 2025-01-27 | 2025-01-28 | 2025-03-06 | 2025-03-24
| JD3RZ07L64ST28013.R | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-64-ST -Remaining | 1 | 2025-01-29 | 2025-01-30
| JD3RZ07L64ST28014 | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-64-ST | 1 | 2025-02-10 | 2025-02-11 | 2025-04-20 | 2025-05-07
| JD3RZ07L64ST28014.R | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-64-ST -Remaining | 1 | 2025-02-12 | 2025-02-13
| JD3RZ07L64ST28020 | Excavation Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-64-ST | 1 | 2025-01-22 | 2025-01-25 | 2025-01-22 | 2025-02-18
| JD3RZ07L64ST28020.R | Excavation Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-64-ST -Remaining | 1 | 2025-01-26 | 2025-01-27 | 2025-09-14
| JD3RZ07L64ST28021 | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-64-ST | 1 | 2025-01-26 | 2025-01-28 | 2025-01-28 | 2025-03-05
| JD3RZ07L64ST28021.R | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-64-ST -Rem | 1 | 2025-01-29 | 2025-01-30 | 2025-09-16
| JD3RZ07L64ST28022 | Installing for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-64-ST | 1 | 2025-01-29 | 2025-02-02 | 2025-04-15 | 2025-05-21
| JD3RZ07L64ST28022.R | Installing for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-64-ST -Remaining | 1 | 2025-02-03 | 2025-02-04 | 2025-09-18
| JD3RZ07L64ST28023 | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-64-ST | 1 | 2025-02-03 | 2025-02-05 | 2025-04-16 | 2025-05-22
| JD3RZ07L64ST28023.R | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-64-ST -Remaining | 1 | 2025-02-06 | 2025-02-08 | 2025-09-20
| JD3RZ07L64ST28024 | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-64-ST | 1 | 2025-02-10 | 2025-02-15 | 2025-04-20 | 2025-06-04
| JD3RZ07L64ST28024.R | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-64-ST -Remaining | 1 | 2025-02-16 | 2025-02-17 | 2025-09-23
| JD3RZ07L64ST28030 | Excavation Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-64-ST | 1 | 2025-01-26 | 2025-01-30 | 2025-01-28 | 2025-03-15
| JD3RZ07L64ST28030.R | Excavation Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-64-ST -Remaining | 1 | 2025-02-01 | 2025-02-02 | 2025-09-14
| JD3RZ07L64ST28031 | Soil Replacement and Bedding Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-64-ST | 1 | 2025-02-01 | 2025-02-05 | 2025-02-04 | 2025-04-09
| JD3RZ07L64ST28031.R | Soil Replacement and Bedding Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-64-ST -Rem | 1 | 2025-02-06 | 2025-02-08 | 2025-09-16
| JD3RZ07L64ST28032 | Installing for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-64-ST | 1 | 2025-02-06 | 2025-02-12 | 2025-02-05 | 2025-04-29
| JD3RZ07L64ST28032.R | Installing for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-64-ST -Remaining | 1 | 2025-02-13 | 2025-02-15 | 2025-09-18
| JD3RZ07L64ST28033 | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-64-ST | 1 | 2025-02-13 | 2025-02-18 | 2025-02-11 | 2025-05-05
| JD3RZ07L64ST28033.R | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-64-ST -Remaining | 1 | 2025-02-19 | 2025-02-20 | 2025-09-21
| JD3RZ07L64ST28034 | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-64-ST | 1 | 2025-02-19 | 2025-02-26 | 2025-04-20 | 2025-07-21
| JD3RZ07L64ST28034.R | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-64-ST -Remaining | 1 | 2025-02-27 | 2025-03-01 | 2025-09-23
| JD3RZ07L64ST28060 | Excavation Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z07-L-64-ST | 1 | 2025-01-20 | 2025-01-21
| JD3RZ07L64ST28061 | Soil Replacement and Bedding Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z07-L-64-ST | 1 | 2025-01-22 | 2025-01-23
| JD3RZ07L64ST28062 | Installing for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z07-L-64-ST | 1 | 2025-01-25 | 2025-01-26
| JD3RZ07L64ST28063 | Primary Test for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z07-L-64-ST | 1 | 2025-01-27 | 2025-01-28
| JD3RZ07L64ST28064 | Backfilling Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z07-L-64-ST | 1 | 2025-02-13 | 2025-02-15
| JD3RZ07L64ST28153 | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-64-ST | 1 | 2025-01-22 | 2025-01-23 | 2025-08-23 | 2025-08-24
| JD3RZ07L64ST28154 | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-64-ST | 1 | 2025-01-25 | 2025-01-26 | 2025-08-24 | 2025-08-25
| JD3RZ07L64ST28155 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-64-ST | 1 | 2025-01-27 | 2025-01-28
| JD3RZ07L64ST28156 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-64-ST | 1 | 2025-01-29 | 2025-01-30
| JD3RZ07L64ST28157 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-64-ST | 1 | 2025-02-01 | 2025-02-02
| JD3RZ07L64ST28163 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-64-ST | 1 | 2025-02-01 | 2025-02-02 | 2025-05-10 | 2025-05-27
| JD3RZ07L64ST28163.R | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-64-ST -Remaining | 1 | 2025-02-03 | 2025-02-04 | 2025-08-24 | 2025-08-25
| JD3RZ07L64ST28164 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-64-ST | 1 | 2025-02-03 | 2025-02-05 | 2025-05-15 | 2025-06-11
| JD3RZ07L64ST28164.R | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-64-ST -Remaining | 1 | 2025-02-06 | 2025-02-08
| JD3RZ07L64ST28165 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-64-ST | 1 | 2025-02-06 | 2025-02-09 | 2025-07-15 | 2025-07-31
| JD3RZ07L64ST28165.R | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-64-ST -Remaining | 1 | 2025-02-10 | 2025-02-11
| JD3RZ07L64ST28166 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-64-ST | 1 | 2025-02-12 | 2025-02-13
| JD3RZ07L64ST28167 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-64-ST | 1 | 2025-02-15 | 2025-02-16
| JD3RZ07L64ST28168 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-L-64-ST | 1 | 2025-01-25 | 2025-01-26
| JD3RZ07L64ST28169 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-L-64-ST | 1 | 2025-01-27 | 2025-01-28
| JD3RZ07L64ST28170 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-L-64-ST | 1 | 2025-01-29 | 2025-01-30
| JD3RZ07L64ST28171 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-L-64-ST | 1 | 2025-02-01 | 2025-02-02
| JD3RZ07L64ST28172 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-L-64-ST | 1 | 2025-02-03 | 2025-02-04
| JD3RZ07L64ST28178 | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-L-64-ST | 1 | 2025-01-27 | 2025-01-28
| JD3RZ07L64ST28179 | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-L-64-ST | 1 | 2025-01-29 | 2025-01-30
| JD3RZ07L64ST28180 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-L-64-ST | 1 | 2025-02-01 | 2025-02-02
| JD3RZ07L64ST28181 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-L-64-ST | 1 | 2025-02-03 | 2025-02-04
| JD3RZ07L64ST28182 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-L-64-ST | 1 | 2025-02-05 | 2025-02-06
| JD3RZ07L64ST28188 | EXCAVATION Works for Catchbasine single - - B6.33 05 39.09-Z07-L-64-ST | 1 | 2025-01-29 | 2025-01-30
| JD3RZ07L64ST28189 | Catchbasine Installation Works For Catchbasine single - - B6.33 05 39.09-Z07-L-64-ST | 1 | 2025-02-01 | 2025-02-03
| JD3RZ07L64ST28190 | FINISHING Works For Catchbasine single - - B6.33 05 39.09-Z07-L-64-ST | 1 | 2025-02-04 | 2025-02-06
| JD3RZ07L64ST28191 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - - B6.33 05 39.09-Z07-L-64-ST | 1 | 2025-02-08 | 2025-02-09
| JD3RZ07L64ST28192 | EXCAVATION Works for Catchbasine double - - B6.33 05 39.10-Z07-L-64-ST | 1 | 2025-02-01 | 2025-02-02
| JD3RZ07L64ST28193 | Catchbasine Installation Works For Catchbasine double - - B6.33 05 39.10-Z07-L-64-ST | 1 | 2025-02-04 | 2025-02-06
| JD3RZ07L64ST28194 | FINISHING Works For Catchbasine double - - B6.33 05 39.10-Z07-L-64-ST | 1 | 2025-02-08 | 2025-02-10
| JD3RZ07L64ST28195 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - - B6.33 05 39.10-Z07-L-64-ST | 1 | 2025-02-11 | 2025-02-12
| JD3RZ07L64ST524366 | Concrete encasement for pipes- NNB6.33 42 11.25-Z07-L-64-ST | 1 | 2025-02-03 | 2025-02-09 | 2025-04-21 | 2025-06-15
| JD3RZ07L64ST524366.R | Concrete encasement for pipes- NNB6.33 42 11.25-Z07-L-64-ST -Remaining | 1 | 2025-02-10 | 2025-02-11
| JD3RZ07L64TSE28246 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-64-TSE | 1 | 2025-02-10 | 2025-02-13 | 2024-12-24 | 2025-01-11
| JD3RZ07L64TSE28246.R | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-64-TSE -Remaining | 1 | 2025-02-15 | 2025-02-16 | 2025-08-26
| JD3RZ07L64TSE28247 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-64-TSE | 1 | 2025-02-15 | 2025-02-19 | 2025-01-01 | 2025-01-28
| JD3RZ07L64TSE28247.R | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-64-TSE -Remai | 1 | 2025-02-20 | 2025-02-22 | 2025-08-28
| JD3RZ07L64TSE28248 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-64-TSE | 1 | 2025-02-20 | 2025-03-01 | 2025-01-02 | 2025-01-29
| JD3RZ07L64TSE28248.R | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-64-TSE -Remaining | 1 | 2025-03-02 | 2025-03-03 | 2025-08-31
| JD3RZ07L64TSE28249 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-64-TSE | 1 | 2025-03-04 | 2025-03-09
| JD3RZ07L64TSE28250 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-64-TSE | 1 | 2025-03-10 | 2025-03-15
| JD3RZ07L64TSE28371 | Installationfor gate valves 100 mm - - B4.33 14 19.01-Z07-L-64-TSE | 1 | 2025-03-04 | 2025-03-05
| JD3RZ07L64TSE28372 | Testing And Commtionningfor gate valves 100 mm - - B4.33 14 19.01-Z07-L-64-TSE | 1 | 2025-03-08 | 2025-03-09
| JD3RZ07L64WT28196 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-64-WT | 1 | 2025-03-16 | 2025-03-17
| JD3RZ07L64WT28197 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-64-WT | 1 | 2025-03-18 | 2025-03-19
| JD3RZ07L64WT28198 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-64-WT | 1 | 2025-03-20 | 2025-03-22
| JD3RZ07L64WT28199 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-64-WT | 1 | 2025-03-23 | 2025-03-24
| JD3RZ07L64WT28200 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-64-WT | 1 | 2025-03-25 | 2025-03-26
| JD3RZ07L64WT28231 | EXCAVATION and Bedding Worksfor Fire Hydrant - - B3.33 14 19.08-Z07-L-64-WT | 1 | 2025-03-18 | 2025-03-19
| JD3RZ07L64WT28232 | INSTALLATIONfor Fire Hydrant - - B3.33 14 19.08-Z07-L-64-WT | 1 | 2025-03-20 | 2025-03-22
| JD3RZ07L64WT28233 | TESTING AND COMMITIONfor Fire Hydrant - - B3.33 14 19.08-Z07-L-64-WT | 1 | 2025-03-23 | 2025-03-24
| JD3RZ07L65ST28683 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-65-ST | 1 | 2024-12-10 | 2024-12-12
| JD3RZ07L65ST28684 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-65-ST | 1 | 2024-12-14 | 2024-12-16
| JD3RZ07L65ST28685 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-65-ST | 1 | 2024-12-17 | 2024-12-21
| JD3RZ07L65ST28686 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-65-ST | 1 | 2024-12-22 | 2024-12-25
| JD3RZ07L65ST28687 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-65-ST | 1 | 2025-01-21 | 2025-01-26
| JD3RZ07L65ST28688 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-65-ST | 1 | 2024-12-14 | 2024-12-15
| JD3RZ07L65ST28689 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-65-ST | 1 | 2024-12-16 | 2024-12-17
| JD3RZ07L65ST28690 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-65-ST | 1 | 2024-12-18 | 2024-12-19
| JD3RZ07L65ST28691 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-65-ST | 1 | 2024-12-21 | 2024-12-22
| JD3RZ07L65ST28692 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-65-ST | 1 | 2025-01-20 | 2025-01-21
| JD3RZ07L65ST28693 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-65-ST | 1 | 2024-12-16 | 2024-12-17
| JD3RZ07L65ST28694 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-65-ST | 1 | 2024-12-18 | 2024-12-19
| JD3RZ07L65ST28695 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-65-ST | 1 | 2024-12-21 | 2024-12-22
| JD3RZ07L65ST28696 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-65-ST | 1 | 2024-12-23 | 2024-12-24
| JD3RZ07L65ST28697 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-65-ST | 1 | 2025-01-20 | 2025-01-21
| JD3RZ07L65ST28698 | Excavation Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-65-ST | 1 | 2024-12-18 | 2024-12-19 | 2025-08-02 | 2025-08-03
| JD3RZ07L65ST28699 | Soil Replacement and Bedding Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-65-ST | 1 | 2024-12-21 | 2024-12-22 | 2025-08-05 | 2025-08-06
| JD3RZ07L65ST28700 | Installing for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-65-ST | 1 | 2024-12-23 | 2024-12-24 | 2025-08-07 | 2025-08-09
| JD3RZ07L65ST28701 | Primary Test for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-65-ST | 1 | 2024-12-25 | 2024-12-26
| JD3RZ07L65ST28702 | Backfilling Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-65-ST | 1 | 2025-01-20 | 2025-01-21
| JD3RZ07L65ST28708 | Excavation Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z07-L-65-ST | 1 | 2024-12-21 | 2024-12-22 | 2025-08-05 | 2025-08-06
| JD3RZ07L65ST28709 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z07-L-65-ST | 1 | 2024-12-23 | 2024-12-24 | 2025-08-07 | 2025-08-09
| JD3RZ07L65ST28710 | Installing for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z07-L-65-ST | 1 | 2024-12-25 | 2024-12-26 | 2025-08-09 | 2025-08-10
| JD3RZ07L65ST28711 | Primary Test for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z07-L-65-ST | 1 | 2024-12-28 | 2024-12-29
| JD3RZ07L65ST28712 | Backfilling Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z07-L-65-ST | 1 | 2025-01-20 | 2025-01-21
| JD3RZ07L65ST28723 | Excavation Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-65-ST | 1 | 2024-12-23 | 2024-12-24 | 2025-08-07 | 2025-08-09
| JD3RZ07L65ST28724 | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-65-ST | 1 | 2024-12-25 | 2024-12-26 | 2025-08-09 | 2025-08-10
| JD3RZ07L65ST28725 | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-65-ST | 1 | 2024-12-28 | 2024-12-30 | 2025-08-12 | 2025-08-13
| JD3RZ07L65ST28726 | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-65-ST | 1 | 2024-12-31 | 2025-01-01
| JD3RZ07L65ST28727 | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-65-ST | 1 | 2025-01-20 | 2025-01-22
| JD3RZ07L65ST28733 | Excavation Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-65-ST | 1 | 2024-12-25 | 2024-12-26 | 2025-06-28 | 2025-07-15
| JD3RZ07L65ST28733.R | Excavation Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-65-ST -Remaining | 1 | 2024-12-28 | 2024-12-29 | 2025-08-09 | 2025-08-10
| JD3RZ07L65ST28734 | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-65-ST | 1 | 2024-12-28 | 2024-12-29 | 2025-07-01 | 2025-07-28
| JD3RZ07L65ST28734.R | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-65-ST -Rem | 1 | 2024-12-30 | 2024-12-31 | 2025-08-12 | 2025-08-13
| JD3RZ07L65ST28735 | Installing for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-65-ST | 1 | 2024-12-30 | 2025-01-01 | 2025-07-05 | 2025-07-31
| JD3RZ07L65ST28735.R | Installing for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-65-ST -Remaining | 1 | 2025-01-02 | 2025-01-04 | 2025-08-14 | 2025-08-16
| JD3RZ07L65ST28736 | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-65-ST | 1 | 2025-01-05 | 2025-01-06
| JD3RZ07L65ST28737 | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-65-ST | 1 | 2025-01-23 | 2025-01-26
| JD3RZ07L65ST28743 | Excavation Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-65-ST | 1 | 2024-12-28 | 2024-12-30 | 2025-06-28 | 2025-07-24
| JD3RZ07L65ST28743.R | Excavation Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-65-ST -Remaining | 1 | 2024-12-31 | 2025-01-01 | 2025-08-12 | 2025-08-16
| JD3RZ07L65ST28744 | Soil Replacement and Bedding Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-65-ST | 1 | 2024-12-31 | 2025-01-02 | 2025-06-30 | 2025-07-27
| JD3RZ07L65ST28744.R | Soil Replacement and Bedding Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-65-ST -Rem | 1 | 2025-01-04 | 2025-01-05 | 2025-08-20 | 2025-08-23
| JD3RZ07L65ST28745 | Installing for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-65-ST | 1 | 2025-01-04 | 2025-01-06 | 2025-07-01 | 2025-07-31
| JD3RZ07L65ST28745.R | Installing for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-65-ST -Remaining | 1 | 2025-01-07 | 2025-01-08
| JD3RZ07L65ST28746 | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-65-ST | 1 | 2025-01-09 | 2025-01-12
| JD3RZ07L65ST28747 | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-65-ST | 1 | 2025-01-20 | 2025-01-23
| JD3RZ07L65ST28758 | Excavation Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-L-65-ST | 1 | 2024-12-31 | 2025-01-02 | 2025-06-10 | 2025-07-16
| JD3RZ07L65ST28759 | Soil Replacement and Bedding Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-L-65-ST | 1 | 2025-01-04 | 2025-01-06 | 2025-06-29 | 2025-07-31
| JD3RZ07L65ST28759.R | Soil Replacement and Bedding Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-L-65-ST -Re | 1 | 2025-01-07 | 2025-01-08
| JD3RZ07L65ST28760 | Installing for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-L-65-ST | 1 | 2025-01-07 | 2025-01-09 | 2025-06-30 | 2025-07-31
| JD3RZ07L65ST28760.R | Installing for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-L-65-ST -Remaining | 1 | 2025-01-11 | 2025-01-12
| JD3RZ07L65ST28761 | Primary Test for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-L-65-ST | 1 | 2025-01-13 | 2025-01-15
| JD3RZ07L65ST28762 | Backfilling Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-L-65-ST | 1 | 2025-01-20 | 2025-01-23
| JD3RZ07L65ST28788 | Excavation Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z07-L-65-ST | 1 | 2024-12-25 | 2024-12-26
| JD3RZ07L65ST28789 | Soil Replacement and Bedding Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z07-L-65-ST | 1 | 2024-12-28 | 2024-12-29
| JD3RZ07L65ST28790 | Installing for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z07-L-65-ST | 1 | 2024-12-30 | 2024-12-31
| JD3RZ07L65ST28791 | Primary Test for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z07-L-65-ST | 1 | 2025-01-01 | 2025-01-02
| JD3RZ07L65ST28792 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z07-L-65-ST | 1 | 2025-01-20 | 2025-01-21
| JD3RZ07L65ST28866 | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-65-ST | 1 | 2024-12-28 | 2024-12-29 | 2025-08-05
| JD3RZ07L65ST28867 | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-65-ST | 1 | 2024-12-30 | 2024-12-31 | 2025-08-07
| JD3RZ07L65ST28868 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-65-ST | 1 | 2025-01-01 | 2025-01-02
| JD3RZ07L65ST28869 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-65-ST | 1 | 2025-01-04 | 2025-01-05
| JD3RZ07L65ST28870 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-65-ST | 1 | 2025-01-06 | 2025-01-07
| JD3RZ07L65ST28876 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-65-ST | 1 | 2025-01-07 | 2025-01-08 | 2025-06-10 | 2025-06-28
| JD3RZ07L65ST28876.R | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-65-ST -Remaining | 1 | 2025-01-09 | 2025-01-11 | 2025-08-07
| JD3RZ07L65ST28877 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-65-ST | 1 | 2025-01-09 | 2025-01-11 | 2025-06-15 | 2025-07-02
| JD3RZ07L65ST28877.R | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-65-ST -Remaining | 1 | 2025-01-12 | 2025-01-13 | 2025-08-09
| JD3RZ07L65ST28878 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-65-ST | 1 | 2025-01-12 | 2025-01-13 | 2025-06-30 | 2025-07-17
| JD3RZ07L65ST28878.R | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-65-ST -Remaining | 1 | 2025-01-14 | 2025-01-15
| JD3RZ07L65ST28879 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-65-ST | 1 | 2025-01-16 | 2025-01-18
| JD3RZ07L65ST28880 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-65-ST | 1 | 2025-01-19 | 2025-01-20
| JD3RZ07L65ST28881 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-L-65-ST | 1 | 2024-12-30 | 2024-12-31
| JD3RZ07L65ST28882 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-L-65-ST | 1 | 2025-01-01 | 2025-01-02
| JD3RZ07L65ST28883 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-L-65-ST | 1 | 2025-01-04 | 2025-01-05
| JD3RZ07L65ST28884 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-L-65-ST | 1 | 2025-01-06 | 2025-01-07
| JD3RZ07L65ST28885 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-L-65-ST | 1 | 2025-01-08 | 2025-01-09
| JD3RZ07L65ST28891 | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-L-65-ST | 1 | 2025-01-09 | 2025-01-11 | 2025-06-10 | 2025-06-28
| JD3RZ07L65ST28891.R | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-L-65-ST -Remaining | 1 | 2025-01-12 | 2025-01-13 | 2025-08-09 | 2025-08-10
| JD3RZ07L65ST28892 | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-L-65-ST | 1 | 2025-01-12 | 2025-01-13 | 2025-06-15 | 2025-07-12
| JD3RZ07L65ST28892.R | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-L-65-ST -Remaining | 1 | 2025-01-14 | 2025-01-15 | 2025-08-12 | 2025-08-13
| JD3RZ07L65ST28893 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-L-65-ST | 1 | 2025-01-14 | 2025-01-15 | 2025-06-30 | 2025-07-27
| JD3RZ07L65ST28893.R | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-L-65-ST -Remaining | 1 | 2025-01-16 | 2025-01-18
| JD3RZ07L65ST28894 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-L-65-ST | 1 | 2025-01-19 | 2025-01-20
| JD3RZ07L65ST28895 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-L-65-ST | 1 | 2025-01-21 | 2025-01-22
| JD3RZ07L65ST28896 | Excavation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-L-65-ST | 1 | 2025-01-01 | 2025-01-02
| JD3RZ07L65ST28897 | Base Plain Concrete Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-L-65-ST | 1 | 2025-01-04 | 2025-01-05
| JD3RZ07L65ST28898 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-L-65-ST | 1 | 2025-01-06 | 2025-01-07
| JD3RZ07L65ST28899 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-L-65-ST | 1 | 2025-01-08 | 2025-01-09
| JD3RZ07L65ST28900 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-L-65-ST | 1 | 2025-01-15 | 2025-01-16
| JD3RZ07L65ST28901 | EXCAVATION Works for Catchbasine single - - B6.33 05 39.09-Z07-L-65-ST | 1 | 2025-01-04 | 2025-01-05
| JD3RZ07L65ST28902 | Catchbasine Installation Works For Catchbasine single - - B6.33 05 39.09-Z07-L-65-ST | 1 | 2025-01-06 | 2025-01-08
| JD3RZ07L65ST28903 | FINISHING Works For Catchbasine single - - B6.33 05 39.09-Z07-L-65-ST | 1 | 2025-01-09 | 2025-01-12
| JD3RZ07L65ST28904 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - - B6.33 05 39.09-Z07-L-65-ST | 1 | 2025-01-13 | 2025-01-14
| JD3RZ07L65ST28905 | EXCAVATION Works for Catchbasine double - - B6.33 05 39.10-Z07-L-65-ST | 1 | 2025-01-06 | 2025-01-07
| JD3RZ07L65ST28906 | Catchbasine Installation Works For Catchbasine double - - B6.33 05 39.10-Z07-L-65-ST | 1 | 2025-01-08 | 2025-01-11
| JD3RZ07L65ST28907 | FINISHING Works For Catchbasine double - - B6.33 05 39.10-Z07-L-65-ST | 1 | 2025-01-12 | 2025-01-14
| JD3RZ07L65ST28908 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - - B6.33 05 39.10-Z07-L-65-ST | 1 | 2025-01-15 | 2025-01-16
| JD3RZ07L65ST524367 | Concrete encasement for pipes- NNB6.33 42 11.25-Z07-L-65-ST | 1 | 2025-01-13 | 2025-01-19
| JD3RZ07L65TSE28959 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-65-TSE | 1 | 2025-01-12 | 2025-01-15 | 2025-01-20 | 2025-02-06
| JD3RZ07L65TSE28959.R | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-65-TSE -Remaining | 1 | 2025-01-18 | 2025-01-19
| JD3RZ07L65TSE28960 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-65-TSE | 1 | 2025-01-16 | 2025-01-21 | 2025-01-21 | 2025-02-17
| JD3RZ07L65TSE28960.R | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-65-TSE -Remai | 1 | 2025-01-22 | 2025-01-23
| JD3RZ07L65TSE28961 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-65-TSE | 1 | 2025-01-22 | 2025-01-30 | 2025-01-22 | 2025-02-18
| JD3RZ07L65TSE28961.R | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-65-TSE -Remaining | 1 | 2025-02-01 | 2025-02-02
| JD3RZ07L65TSE28962 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-65-TSE | 1 | 2025-02-01 | 2025-02-06
| JD3RZ07L65TSE28962.R | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-65-TSE -Remaining | 1 | 2025-02-08 | 2025-02-09
| JD3RZ07L65TSE28963 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-65-TSE | 1 | 2025-02-10 | 2025-02-16
| JD3RZ07L65TSE29004 | Excavation Worksfor HDPE Pipes 450 mm - depth from 1.51 to 2.5 m- B4.33 31 00.10-Z07-L-65-TSE | 1 | 2025-01-27 | 2025-01-28
| JD3RZ07L65TSE29005 | Soil Replacement and Bedding Works for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m- B4.33 31 00.10-Z07-L-65-TSE | 1 | 2025-01-29 | 2025-01-30
| JD3RZ07L65TSE29006 | Installing for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m- B4.33 31 00.10-Z07-L-65-TSE | 1 | 2025-02-01 | 2025-02-02
| JD3RZ07L65TSE29007 | Testing for HDPE Pipes 450 mm - depth from 1.51 to 2.5 m- B4.33 31 00.10-Z07-L-65-TSE | 1 | 2025-02-03 | 2025-02-04
| JD3RZ07L65TSE29008 | Backfillingfor HDPE Pipes 450 mm - depth from 1.51 to 2.5 m- B4.33 31 00.10-Z07-L-65-TSE | 1 | 2025-02-05 | 2025-02-06
| JD3RZ07L65TSE29084 | Installationfor gate valves 100 mm - - B4.33 14 19.01-Z07-L-65-TSE | 1 | 2025-02-03 | 2025-02-04
| JD3RZ07L65TSE29085 | Testing And Commtionningfor gate valves 100 mm - - B4.33 14 19.01-Z07-L-65-TSE | 1 | 2025-02-05 | 2025-02-06
| JD3RZ07L65WT28909 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-65-WT | 1 | 2025-01-27 | 2025-01-28
| JD3RZ07L65WT28910 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-65-WT | 1 | 2025-01-29 | 2025-01-30
| JD3RZ07L65WT28911 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-65-WT | 1 | 2025-02-01 | 2025-02-02
| JD3RZ07L65WT28912 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-65-WT | 1 | 2025-02-03 | 2025-02-04
| JD3RZ07L65WT28913 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-65-WT | 1 | 2025-02-15 | 2025-02-16
| JD3RZ07L65WT28944 | EXCAVATION and Bedding Worksfor Fire Hydrant - - B3.33 14 19.08-Z07-L-65-WT | 1 | 2025-02-08 | 2025-02-09
| JD3RZ07L65WT28945 | INSTALLATIONfor Fire Hydrant - - B3.33 14 19.08-Z07-L-65-WT | 1 | 2025-02-10 | 2025-02-11
| JD3RZ07L65WT28946 | TESTING AND COMMITIONfor Fire Hydrant - - B3.33 14 19.08-Z07-L-65-WT | 1 | 2025-02-12 | 2025-02-13
| JD3RZ07L66ST29396 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-66-ST | 1 | 2025-01-13 | 2025-01-15
| JD3RZ07L66ST29397 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-66-ST | 1 | 2025-01-16 | 2025-01-19
| JD3RZ07L66ST29398 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-66-ST | 1 | 2025-01-20 | 2025-01-23
| JD3RZ07L66ST29399 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-66-ST | 1 | 2025-01-25 | 2025-01-28
| JD3RZ07L66ST29400 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-66-ST | 1 | 2025-02-27 | 2025-03-04
| JD3RZ07L66ST29401 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-66-ST | 1 | 2025-01-16 | 2025-01-18 | 2025-08-16
| JD3RZ07L66ST29402 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-66-ST | 1 | 2025-01-19 | 2025-01-20 | 2025-08-18
| JD3RZ07L66ST29403 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-66-ST | 1 | 2025-01-21 | 2025-01-22 | 2025-08-21
| JD3RZ07L66ST29404 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-66-ST | 1 | 2025-01-23 | 2025-01-25
| JD3RZ07L66ST29405 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-66-ST | 1 | 2025-03-05 | 2025-03-06
| JD3RZ07L66ST29406 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-66-ST | 1 | 2025-01-23 | 2025-01-25
| JD3RZ07L66ST29407 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-66-ST | 1 | 2025-01-26 | 2025-01-27
| JD3RZ07L66ST29408 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-66-ST | 1 | 2025-01-28 | 2025-01-29
| JD3RZ07L66ST29409 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-66-ST | 1 | 2025-01-30 | 2025-02-01
| JD3RZ07L66ST29410 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-66-ST | 1 | 2025-03-08 | 2025-03-09
| JD3RZ07L66ST29411 | Excavation Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-66-ST | 1 | 2025-01-26 | 2025-01-27 | 2025-04-06 | 2025-04-23
| JD3RZ07L66ST29411.R | Excavation Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-66-ST -Remaining | 1 | 2025-01-28 | 2025-01-29
| JD3RZ07L66ST29412 | Soil Replacement and Bedding Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-66-ST | 1 | 2025-01-28 | 2025-01-29 | 2025-04-07 | 2025-04-24
| JD3RZ07L66ST29412.R | Soil Replacement and Bedding Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-66-ST -Rem | 1 | 2025-01-30 | 2025-02-01
| JD3RZ07L66ST29413 | Installing for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-66-ST | 1 | 2025-01-30 | 2025-02-01 | 2025-04-08 | 2025-04-26
| JD3RZ07L66ST29413.R | Installing for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-66-ST -Remaining | 1 | 2025-02-02 | 2025-02-03
| JD3RZ07L66ST29414 | Primary Test for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-66-ST | 1 | 2025-02-02 | 2025-02-03 | 2025-04-09 | 2025-04-27
| JD3RZ07L66ST29414.R | Primary Test for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-66-ST -Remaining | 1 | 2025-02-04 | 2025-02-05
| JD3RZ07L66ST29415 | Backfilling Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-66-ST | 1 | 2025-02-13 | 2025-02-15
| JD3RZ07L66ST29421 | Excavation Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z07-L-66-ST | 1 | 2025-01-28 | 2025-01-29 | 2025-04-05 | 2025-04-22
| JD3RZ07L66ST29422 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z07-L-66-ST | 1 | 2025-01-30 | 2025-02-01 | 2025-04-08 | 2025-04-26
| JD3RZ07L66ST29423 | Installing for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z07-L-66-ST | 1 | 2025-02-02 | 2025-02-03 | 2025-04-10 | 2025-04-28
| JD3RZ07L66ST29424 | Primary Test for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z07-L-66-ST | 1 | 2025-02-06 | 2025-02-08
| JD3RZ07L66ST29425 | Backfilling Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z07-L-66-ST | 1 | 2025-02-13 | 2025-02-15
| JD3RZ07L66ST29431 | Excavation Works for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m- B6.33 42 11.07-Z07-L-66-ST | 1 | 2025-01-30 | 2025-02-01
| JD3RZ07L66ST29432 | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m- B6.33 42 11.07-Z07-L-66-ST | 1 | 2025-02-02 | 2025-02-03
| JD3RZ07L66ST29433 | Installing for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m- B6.33 42 11.07-Z07-L-66-ST | 1 | 2025-02-04 | 2025-02-05
| JD3RZ07L66ST29434 | Primary Test for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m- B6.33 42 11.07-Z07-L-66-ST | 1 | 2025-02-06 | 2025-02-08
| JD3RZ07L66ST29435 | Backfilling Works for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m- B6.33 42 11.07-Z07-L-66-ST | 1 | 2025-02-13 | 2025-02-15
| JD3RZ07L66ST29436 | Excavation Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-66-ST | 1 | 2025-01-28 | 2025-01-29 | 2025-04-05 | 2025-05-01
| JD3RZ07L66ST29436.R | Excavation Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-66-ST -Remaining | 1 | 2025-01-30 | 2025-02-01
| JD3RZ07L66ST29437 | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-66-ST | 1 | 2025-01-30 | 2025-02-01 | 2025-04-08 | 2025-05-05
| JD3RZ07L66ST29437.R | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-66-ST -Rem | 1 | 2025-02-02 | 2025-02-03
| JD3RZ07L66ST29438 | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-66-ST | 1 | 2025-02-02 | 2025-02-04 | 2025-04-10 | 2025-05-17
| JD3RZ07L66ST29438.R | Installing for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-66-ST -Remaining | 1 | 2025-02-05 | 2025-02-06
| JD3RZ07L66ST29439 | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-66-ST | 1 | 2025-02-05 | 2025-02-06 | 2025-07-05 | 2025-07-31
| JD3RZ07L66ST29439.R | Primary Test for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-66-ST -Remaining | 1 | 2025-02-08 | 2025-02-09
| JD3RZ07L66ST29440 | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-66-ST | 1 | 2025-02-08 | 2025-02-10 | 2025-04-29 | 2025-06-04
| JD3RZ07L66ST29440.R | Backfilling Works for GRP Pipe Line 700 mm - depth from 1.51 to 2.50 m- B6.33 42 11.08-Z07-L-66-ST -Remaining | 1 | 2025-02-11 | 2025-02-12
| JD3RZ07L66ST29441 | Excavation Works for GRP Pipe Line 800 mm - depth from 0.00 to 1.50 m- B6.33 42 11.09-Z07-L-66-ST | 1 | 2025-01-30 | 2025-02-01
| JD3RZ07L66ST29442 | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 0.00 to 1.50 m- B6.33 42 11.09-Z07-L-66-ST | 1 | 2025-02-02 | 2025-02-03
| JD3RZ07L66ST29443 | Installing for GRP Pipe Line 800 mm - depth from 0.00 to 1.50 m- B6.33 42 11.09-Z07-L-66-ST | 1 | 2025-02-04 | 2025-02-05
| JD3RZ07L66ST29444 | Primary Test for GRP Pipe Line 800 mm - depth from 0.00 to 1.50 m- B6.33 42 11.09-Z07-L-66-ST | 1 | 2025-02-10 | 2025-02-11
| JD3RZ07L66ST29445 | Backfilling Works for GRP Pipe Line 800 mm - depth from 0.00 to 1.50 m- B6.33 42 11.09-Z07-L-66-ST | 1 | 2025-02-13 | 2025-02-15
| JD3RZ07L66ST29446 | Excavation Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-66-ST | 1 | 2025-01-30 | 2025-02-02 | 2025-04-05 | 2025-05-01
| JD3RZ07L66ST29446.R | Excavation Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-66-ST -Remaining | 1 | 2025-02-03 | 2025-02-04
| JD3RZ07L66ST29447 | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-66-ST | 1 | 2025-02-03 | 2025-02-05 | 2025-04-08 | 2025-05-14
| JD3RZ07L66ST29447.R | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-66-ST -Rem | 1 | 2025-02-06 | 2025-02-08
| JD3RZ07L66ST29448 | Installing for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-66-ST | 1 | 2025-02-06 | 2025-02-09 | 2025-05-13 | 2025-06-18
| JD3RZ07L66ST29448.R | Installing for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-66-ST -Remaining | 1 | 2025-02-10 | 2025-02-11
| JD3RZ07L66ST29449 | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-66-ST | 1 | 2025-02-12 | 2025-02-15
| JD3RZ07L66ST29450 | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-66-ST | 1 | 2025-02-16 | 2025-02-19
| JD3RZ07L66ST29451 | Excavation Works for GRP Pipe Line 900 mm - depth from 0.00 to 1.50 m- B6.33 42 11.11-Z07-L-66-ST | 1 | 2025-01-26 | 2025-01-27
| JD3RZ07L66ST29452 | Soil Replacement and Bedding Works for GRP Pipe Line 900 mm - depth from 0.00 to 1.50 m- B6.33 42 11.11-Z07-L-66-ST | 1 | 2025-01-28 | 2025-01-29
| JD3RZ07L66ST29453 | Installing for GRP Pipe Line 900 mm - depth from 0.00 to 1.50 m- B6.33 42 11.11-Z07-L-66-ST | 1 | 2025-01-30 | 2025-02-01
| JD3RZ07L66ST29454 | Primary Test for GRP Pipe Line 900 mm - depth from 0.00 to 1.50 m- B6.33 42 11.11-Z07-L-66-ST | 1 | 2025-02-02 | 2025-02-03
| JD3RZ07L66ST29455 | Backfilling Works for GRP Pipe Line 900 mm - depth from 0.00 to 1.50 m- B6.33 42 11.11-Z07-L-66-ST | 1 | 2025-02-16 | 2025-02-17
| JD3RZ07L66ST29466 | Excavation Works for GRP Pipe Line 1000 mm - depth from 0.00 to 1.50 m- B6.33 42 11.14-Z07-L-66-ST | 1 | 2025-01-28 | 2025-01-29
| JD3RZ07L66ST29467 | Soil Replacement and Bedding Works for GRP Pipe Line 1000 mm - depth from 0.00 to 1.50 m- B6.33 42 11.14-Z07-L-66-ST | 1 | 2025-01-30 | 2025-02-01
| JD3RZ07L66ST29468 | Installing for GRP Pipe Line 1000 mm - depth from 0.00 to 1.50 m- B6.33 42 11.14-Z07-L-66-ST | 1 | 2025-02-02 | 2025-02-03
| JD3RZ07L66ST29469 | Primary Test for GRP Pipe Line 1000 mm - depth from 0.00 to 1.50 m- B6.33 42 11.14-Z07-L-66-ST | 1 | 2025-02-04 | 2025-02-05
| JD3RZ07L66ST29470 | Backfilling Works for GRP Pipe Line 1000 mm - depth from 0.00 to 1.50 m- B6.33 42 11.14-Z07-L-66-ST | 1 | 2025-02-13 | 2025-02-15
| JD3RZ07L66ST29471 | Excavation Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-L-66-ST | 1 | 2025-01-30 | 2025-02-01
| JD3RZ07L66ST29472 | Soil Replacement and Bedding Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-L-66-ST | 1 | 2025-02-02 | 2025-02-03
| JD3RZ07L66ST29473 | Installing for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-L-66-ST | 1 | 2025-02-04 | 2025-02-05
| JD3RZ07L66ST29474 | Primary Test for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-L-66-ST | 1 | 2025-02-06 | 2025-02-08
| JD3RZ07L66ST29475 | Backfilling Works for GRP Pipe Line 1000 mm - depth from 1.51 to 2.50 m- B6.33 42 11.15-Z07-L-66-ST | 1 | 2025-02-20 | 2025-02-22
| JD3RZ07L66ST29579 | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-66-ST | 1 | 2025-02-02 | 2025-02-03 | 2025-05-10 | 2025-05-27
| JD3RZ07L66ST29580 | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-66-ST | 1 | 2025-02-04 | 2025-02-05 | 2025-05-13 | 2025-05-31
| JD3RZ07L66ST29581 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-66-ST | 1 | 2025-02-06 | 2025-02-08
| JD3RZ07L66ST29582 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-66-ST | 1 | 2025-02-09 | 2025-02-10
| JD3RZ07L66ST29583 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-66-ST | 1 | 2025-02-11 | 2025-02-12
| JD3RZ07L66ST29589 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-66-ST | 1 | 2025-02-03 | 2025-02-04 | 2025-05-15 | 2025-06-02
| JD3RZ07L66ST29589.R | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-66-ST -Remaining | 1 | 2025-02-05 | 2025-02-06
| JD3RZ07L66ST29590 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-66-ST | 1 | 2025-02-05 | 2025-02-08 | 2025-05-25 | 2025-06-21
| JD3RZ07L66ST29590.R | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-66-ST -Remaining | 1 | 2025-02-09 | 2025-02-10
| JD3RZ07L66ST29591 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-66-ST | 1 | 2025-02-09 | 2025-02-11 | 2025-06-30 | 2025-07-27
| JD3RZ07L66ST29591.R | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-66-ST -Remaining | 1 | 2025-02-12 | 2025-02-13
| JD3RZ07L66ST29592 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-66-ST | 1 | 2025-02-15 | 2025-02-16
| JD3RZ07L66ST29593 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-66-ST | 1 | 2025-02-17 | 2025-02-18
| JD3RZ07L66ST29604 | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-L-66-ST | 1 | 2025-02-02 | 2025-02-03
| JD3RZ07L66ST29605 | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-L-66-ST | 1 | 2025-02-04 | 2025-02-05
| JD3RZ07L66ST29606 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-L-66-ST | 1 | 2025-02-06 | 2025-02-08
| JD3RZ07L66ST29607 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-L-66-ST | 1 | 2025-02-09 | 2025-02-10
| JD3RZ07L66ST29608 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-L-66-ST | 1 | 2025-02-23 | 2025-02-24
| JD3RZ07L66ST29614 | EXCAVATION Works for Catchbasine single - - B6.33 05 39.09-Z07-L-66-ST | 1 | 2025-02-04 | 2025-02-05
| JD3RZ07L66ST29615 | Catchbasine Installation Works For Catchbasine single - - B6.33 05 39.09-Z07-L-66-ST | 1 | 2025-02-06 | 2025-02-09
| JD3RZ07L66ST29616 | FINISHING Works For Catchbasine single - - B6.33 05 39.09-Z07-L-66-ST | 1 | 2025-02-10 | 2025-02-12
| JD3RZ07L66ST29617 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - - B6.33 05 39.09-Z07-L-66-ST | 1 | 2025-02-25 | 2025-02-26
| JD3RZ07L66ST29618 | EXCAVATION Works for Catchbasine double - - B6.33 05 39.10-Z07-L-66-ST | 1 | 2025-02-06 | 2025-02-08
| JD3RZ07L66ST29619 | Catchbasine Installation Works For Catchbasine double - - B6.33 05 39.10-Z07-L-66-ST | 1 | 2025-02-09 | 2025-02-11
| JD3RZ07L66ST29620 | FINISHING Works For Catchbasine double - - B6.33 05 39.10-Z07-L-66-ST | 1 | 2025-02-12 | 2025-02-15
| JD3RZ07L66ST29621 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - - B6.33 05 39.10-Z07-L-66-ST | 1 | 2025-02-27 | 2025-03-01
| JD3RZ07L66ST524368 | Concrete encasement for pipes- NNB6.33 42 11.25-Z07-L-66-ST | 1 | 2025-02-06 | 2025-02-12
| JD3RZ07L66TSE29672 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-66-TSE | 1 | 2025-02-09 | 2025-02-12
| JD3RZ07L66TSE29673 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-66-TSE | 1 | 2025-02-13 | 2025-02-18
| JD3RZ07L66TSE29674 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-66-TSE | 1 | 2025-02-19 | 2025-02-27
| JD3RZ07L66TSE29675 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-66-TSE | 1 | 2025-03-01 | 2025-03-06
| JD3RZ07L66TSE29676 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-66-TSE | 1 | 2025-03-08 | 2025-03-13
| JD3RZ07L66TSE29687 | Excavation Worksfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-66-TSE | 1 | 2025-02-13 | 2025-02-15
| JD3RZ07L66TSE29688 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-66-TSE | 1 | 2025-02-16 | 2025-02-17
| JD3RZ07L66TSE29689 | Installing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-66-TSE | 1 | 2025-02-18 | 2025-02-19
| JD3RZ07L66TSE29690 | Testing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-66-TSE | 1 | 2025-02-20 | 2025-02-22
| JD3RZ07L66TSE29691 | Backfillingfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-66-TSE | 1 | 2025-02-23 | 2025-02-24
| JD3RZ07L66TSE29797 | Installationfor gate valves 100 mm - - B4.33 14 19.01-Z07-L-66-TSE | 1 | 2025-03-01 | 2025-03-02
| JD3RZ07L66TSE29798 | Testing And Commtionningfor gate valves 100 mm - - B4.33 14 19.01-Z07-L-66-TSE | 1 | 2025-03-03 | 2025-03-04
| JD3RZ07L66TSE29801 | Installationfor butterfly valves 300 mm. - - B4.33 14 19.03-Z07-L-66-TSE | 1 | 2025-03-01 | 2025-03-02
| JD3RZ07L66TSE29802 | Testing And Commtionningfor butterfly valves 300 mm. - - B4.33 14 19.03-Z07-L-66-TSE | 1 | 2025-03-03 | 2025-03-04
| JD3RZ07L66TSE29815 | Installationfor Air valves 50 mm. - on pipes with diameter less than 315 mm- B4.33 14 19.15-Z07-L-66-TSE | 1 | 2025-03-01 | 2025-03-02
| JD3RZ07L66TSE29816 | Testing And Commtionningfor Air valves 50 mm. - on pipes with diameter less than 315 mm- B4.33 14 19.15-Z07-L-66-TSE | 1 | 2025-03-03 | 2025-03-04
| JD3RZ07L66TSE29821 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-Z07-L-66-TSE | 1 | 2025-02-13 | 2025-02-15
| JD3RZ07L66TSE29822 | Plain Concrete Worksfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-Z07-L-66-TSE | 1 | 2025-02-16 | 2025-02-17
| JD3RZ07L66TSE29823 | INSTALLATIONfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-Z07-L-66-TSE | 1 | 2025-02-18 | 2025-02-19
| JD3RZ07L66TSE29824 | Backfilling Worksfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-Z07-L-66-TSE | 1 | 2025-02-20 | 2025-02-22
| JD3RZ07L66TSE29845 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm- B4.33 14 13.10-Z07-L-66-TSE | 1 | 2025-02-13 | 2025-02-15
| JD3RZ07L66TSE29846 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm- B4.33 14 13.10-Z07-L-66-TSE | 1 | 2025-02-16 | 2025-02-17
| JD3RZ07L66TSE29847 | INSTALLATIONfor Air Valve Chamber - less than 315 mm- B4.33 14 13.10-Z07-L-66-TSE | 1 | 2025-02-18 | 2025-02-19
| JD3RZ07L66TSE29848 | Backfilling Worksfor Air Valve Chamber - less than 315 mm- B4.33 14 13.10-Z07-L-66-TSE | 1 | 2025-02-20 | 2025-02-22
| JD3RZ07L66WT29622 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-66-WT | 1 | 2025-03-10 | 2025-03-11
| JD3RZ07L66WT29623 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-66-WT | 1 | 2025-03-12 | 2025-03-13
| JD3RZ07L66WT29624 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-66-WT | 1 | 2025-03-15 | 2025-03-16
| JD3RZ07L66WT29625 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-66-WT | 1 | 2025-03-17 | 2025-03-18
| JD3RZ07L66WT29626 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-66-WT | 1 | 2025-03-19 | 2025-03-20
| JD3RZ07L66WT29657 | EXCAVATION and Bedding Worksfor Fire Hydrant - - B3.33 14 19.08-Z07-L-66-WT | 1 | 2025-03-12 | 2025-03-13
| JD3RZ07L66WT29658 | INSTALLATIONfor Fire Hydrant - - B3.33 14 19.08-Z07-L-66-WT | 1 | 2025-03-15 | 2025-03-16
| JD3RZ07L66WT29659 | TESTING AND COMMITIONfor Fire Hydrant - - B3.33 14 19.08-Z07-L-66-WT | 1 | 2025-03-17 | 2025-03-18
| JD3RZ07L67ST30109 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-67-ST | 1 | 2025-01-16 | 2025-01-18
| JD3RZ07L67ST30110 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-67-ST | 1 | 2025-01-19 | 2025-01-20
| JD3RZ07L67ST30111 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-67-ST | 1 | 2025-01-21 | 2025-01-22
| JD3RZ07L67ST30112 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-67-ST | 1 | 2025-01-23 | 2025-01-25
| JD3RZ07L67ST30113 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-67-ST | 1 | 2025-01-26 | 2025-01-27
| JD3RZ07L67ST30114 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-67-ST | 1 | 2025-01-19 | 2025-01-20 | 2025-04-26 | 2025-05-13
| JD3RZ07L67ST30114.R | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-67-ST -Remaining | 1 | 2025-01-21 | 2025-01-22
| JD3RZ07L67ST30115 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-67-ST | 1 | 2025-01-23 | 2025-01-25
| JD3RZ07L67ST30116 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-67-ST | 1 | 2025-01-26 | 2025-01-27
| JD3RZ07L67ST30117 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-67-ST | 1 | 2025-01-28 | 2025-01-29
| JD3RZ07L67ST30118 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-67-ST | 1 | 2025-01-30 | 2025-02-01
| JD3RZ07L67ST30119 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-67-ST | 1 | 2025-01-23 | 2025-01-25
| JD3RZ07L67ST30120 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-67-ST | 1 | 2025-01-26 | 2025-01-27
| JD3RZ07L67ST30121 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-67-ST | 1 | 2025-01-28 | 2025-01-29
| JD3RZ07L67ST30122 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-67-ST | 1 | 2025-01-30 | 2025-02-01
| JD3RZ07L67ST30123 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-67-ST | 1 | 2025-02-02 | 2025-02-03
| JD3RZ07L67ST30124 | Excavation Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-67-ST | 1 | 2025-01-26 | 2025-01-27 | 2025-08-23
| JD3RZ07L67ST30125 | Soil Replacement and Bedding Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-67-ST | 1 | 2025-01-28 | 2025-01-29 | 2025-08-25
| JD3RZ07L67ST30126 | Installing for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-67-ST | 1 | 2025-01-30 | 2025-02-01 | 2025-08-28
| JD3RZ07L67ST30127 | Primary Test for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-67-ST | 1 | 2025-02-02 | 2025-02-03
| JD3RZ07L67ST30128 | Backfilling Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-67-ST | 1 | 2025-02-04 | 2025-02-05
| JD3RZ07L67ST30134 | Excavation Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z07-L-67-ST | 1 | 2025-02-06 | 2025-02-08 | 2025-01-05 | 2025-01-22
| JD3RZ07L67ST30135 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z07-L-67-ST | 1 | 2025-02-09 | 2025-02-10 | 2025-01-11 | 2025-01-28
| JD3RZ07L67ST30136 | Installing for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z07-L-67-ST | 1 | 2025-02-11 | 2025-02-12 | 2025-01-12 | 2025-01-29
| JD3RZ07L67ST30137 | Primary Test for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z07-L-67-ST | 1 | 2025-02-13 | 2025-02-15 | 2025-02-25 | 2025-03-15
| JD3RZ07L67ST30138 | Backfilling Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z07-L-67-ST | 1 | 2025-02-16 | 2025-02-17 | 2025-04-05
| JD3RZ07L67ST30139 | Excavation Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-L-67-ST | 1 | 2025-02-09 | 2025-02-10 | 2024-12-04 | 2024-12-22
| JD3RZ07L67ST30140 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-L-67-ST | 1 | 2025-02-11 | 2025-02-12 | 2025-03-10 | 2025-03-27
| JD3RZ07L67ST30141 | Installing for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-L-67-ST | 1 | 2025-02-13 | 2025-02-15 | 2025-03-12 | 2025-03-30
| JD3RZ07L67ST30142 | Primary Test for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-L-67-ST | 1 | 2025-02-16 | 2025-02-17 | 2025-05-17 | 2025-06-03
| JD3RZ07L67ST30143 | Backfilling Works for GRP Pipe Line 600 mm - depth from 1.51 to 2.50 m- B6.33 42 11.06-Z07-L-67-ST | 1 | 2025-02-18 | 2025-02-19
| JD3RZ07L67ST30214 | Excavation Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z07-L-67-ST | 1 | 2025-01-28 | 2025-01-29
| JD3RZ07L67ST30215 | Soil Replacement and Bedding Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z07-L-67-ST | 1 | 2025-01-30 | 2025-02-01
| JD3RZ07L67ST30216 | Installing for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z07-L-67-ST | 1 | 2025-02-02 | 2025-02-03
| JD3RZ07L67ST30217 | Primary Test for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z07-L-67-ST | 1 | 2025-02-04 | 2025-02-05
| JD3RZ07L67ST30218 | Backfilling Works for GRP Pipe Line 1200 mm - depth from 1.51 to 2.50 m- B6.33 42 11.23-Z07-L-67-ST | 1 | 2025-02-06 | 2025-02-08
| JD3RZ07L67ST30292 | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-67-ST | 1 | 2025-01-21 | 2025-01-22 | 2024-12-24 | 2025-01-11
| JD3RZ07L67ST30292.R | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-67-ST -Remaining | 1 | 2025-01-30 | 2025-02-01
| JD3RZ07L67ST30293 | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-67-ST | 1 | 2025-01-23 | 2025-01-25 | 2025-02-05 | 2025-02-23
| JD3RZ07L67ST30293.R | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-67-ST -Remaining | 1 | 2025-02-02 | 2025-02-03
| JD3RZ07L67ST30294 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-67-ST | 1 | 2025-01-26 | 2025-01-27 | 2025-07-05 | 2025-07-22
| JD3RZ07L67ST30294.R | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-67-ST -Remaining | 1 | 2025-02-04 | 2025-02-05
| JD3RZ07L67ST30295 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-67-ST | 1 | 2025-02-06 | 2025-02-08
| JD3RZ07L67ST30296 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-67-ST | 1 | 2025-02-09 | 2025-02-10
| JD3RZ07L67ST30322 | Excavation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-L-67-ST | 1 | 2025-01-30 | 2025-02-01
| JD3RZ07L67ST30323 | Base Plain Concrete Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-L-67-ST | 1 | 2025-02-02 | 2025-02-03
| JD3RZ07L67ST30324 | Manhole Installation Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-L-67-ST | 1 | 2025-02-04 | 2025-02-05
| JD3RZ07L67ST30325 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-L-67-ST | 1 | 2025-02-06 | 2025-02-08
| JD3RZ07L67ST30326 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 2.51 to 3.50 - - B6.33 05 39.08-Z07-L-67-ST | 1 | 2025-02-09 | 2025-02-10
| JD3RZ07L67ST30327 | EXCAVATION Works for Catchbasine single - - B6.33 05 39.09-Z07-L-67-ST | 1 | 2025-02-02 | 2025-02-03
| JD3RZ07L67ST30328 | Catchbasine Installation Works For Catchbasine single - - B6.33 05 39.09-Z07-L-67-ST | 1 | 2025-02-04 | 2025-02-05
| JD3RZ07L67ST30329 | FINISHING Works For Catchbasine single - - B6.33 05 39.09-Z07-L-67-ST | 1 | 2025-02-06 | 2025-02-08
| JD3RZ07L67ST30330 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - - B6.33 05 39.09-Z07-L-67-ST | 1 | 2025-02-09 | 2025-02-10
| JD3RZ07L67ST30331 | EXCAVATION Works for Catchbasine double - - B6.33 05 39.10-Z07-L-67-ST | 1 | 2025-02-04 | 2025-02-05
| JD3RZ07L67ST30332 | Catchbasine Installation Works For Catchbasine double - - B6.33 05 39.10-Z07-L-67-ST | 1 | 2025-02-06 | 2025-02-08
| JD3RZ07L67ST30333 | FINISHING Works For Catchbasine double - - B6.33 05 39.10-Z07-L-67-ST | 1 | 2025-02-09 | 2025-02-10
| JD3RZ07L67ST30334 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - - B6.33 05 39.10-Z07-L-67-ST | 1 | 2025-02-11 | 2025-02-12
| JD3RZ07L67TSE30385 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-67-TSE | 1 | 2025-02-13 | 2025-02-15
| JD3RZ07L67TSE30386 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-67-TSE | 1 | 2025-02-16 | 2025-02-17
| JD3RZ07L67TSE30387 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-67-TSE | 1 | 2025-02-18 | 2025-02-19
| JD3RZ07L67TSE30388 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-67-TSE | 1 | 2025-02-20 | 2025-02-22
| JD3RZ07L67TSE30389 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-67-TSE | 1 | 2025-03-06 | 2025-03-08
| JD3RZ07L67TSE30395 | Excavation Worksfor HDPE Pipes 315 mm - depth from 0 to 1.5 m- B4.33 31 00.03-Z07-L-67-TSE | 1 | 2025-02-16 | 2025-02-17 | 2025-04-05 | 2025-04-23
| JD3RZ07L67TSE30396 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 0 to 1.5 m- B4.33 31 00.03-Z07-L-67-TSE | 1 | 2025-02-18 | 2025-02-19 | 2025-04-10 | 2025-04-29
| JD3RZ07L67TSE30397 | Installing for HDPE Pipes 315 mm - depth from 0 to 1.5 m- B4.33 31 00.03-Z07-L-67-TSE | 1 | 2025-02-20 | 2025-02-22 | 2025-04-17 | 2025-05-05
| JD3RZ07L67TSE30398 | Testing for HDPE Pipes 315 mm - depth from 0 to 1.5 m- B4.33 31 00.03-Z07-L-67-TSE | 1 | 2025-02-23 | 2025-02-24
| JD3RZ07L67TSE30399 | Backfillingfor HDPE Pipes 315 mm - depth from 0 to 1.5 m- B4.33 31 00.03-Z07-L-67-TSE | 1 | 2025-02-25 | 2025-02-26 | 2025-08-23
| JD3RZ07L67TSE30400 | Excavation Worksfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-67-TSE | 1 | 2025-02-18 | 2025-02-19 | 2025-04-05 | 2025-04-22
| JD3RZ07L67TSE30401 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-67-TSE | 1 | 2025-02-20 | 2025-02-22 | 2025-04-10 | 2025-04-28
| JD3RZ07L67TSE30402 | Installing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-67-TSE | 1 | 2025-02-23 | 2025-02-24 | 2025-04-17 | 2025-05-14
| JD3RZ07L67TSE30403 | Testing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-67-TSE | 1 | 2025-02-25 | 2025-02-26
| JD3RZ07L67TSE30404 | Backfillingfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-67-TSE | 1 | 2025-02-27 | 2025-03-01 | 2025-06-10 | 2025-06-28
| JD3RZ07L67TSE30510 | Installationfor gate valves 100 mm - - B4.33 14 19.01-Z07-L-67-TSE | 1 | 2025-03-02 | 2025-03-03
| JD3RZ07L67TSE30511 | Testing And Commtionningfor gate valves 100 mm - - B4.33 14 19.01-Z07-L-67-TSE | 1 | 2025-03-04 | 2025-03-05
| JD3RZ07L67TSE30514 | Installationfor butterfly valves 300 mm. - - B4.33 14 19.03-Z07-L-67-TSE | 1 | 2025-02-20 | 2025-02-22
| JD3RZ07L67TSE30515 | Testing And Commtionningfor butterfly valves 300 mm. - - B4.33 14 19.03-Z07-L-67-TSE | 1 | 2025-02-23 | 2025-02-24
| JD3RZ07L67TSE30534 | EXCAVATION and Bedding Worksfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-Z07-L-67-TSE | 1 | 2025-02-16 | 2025-02-17
| JD3RZ07L67TSE30535 | Plain Concrete Worksfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-Z07-L-67-TSE | 1 | 2025-02-18 | 2025-02-19
| JD3RZ07L67TSE30536 | INSTALLATIONfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-Z07-L-67-TSE | 1 | 2025-02-20 | 2025-02-22
| JD3RZ07L67TSE30537 | Backfilling Worksfor R.C Valve Chamber - 315 to 400 MM- B4.33 14 13.01-Z07-L-67-TSE | 1 | 2025-02-23 | 2025-02-24
| JD3RZ07L67WT30335 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-67-WT | 1 | 2025-03-09 | 2025-03-10
| JD3RZ07L67WT30336 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-67-WT | 1 | 2025-03-11 | 2025-03-12
| JD3RZ07L67WT30337 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-67-WT | 1 | 2025-03-13 | 2025-03-15
| JD3RZ07L67WT30338 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-67-WT | 1 | 2025-03-16 | 2025-03-17
| JD3RZ07L67WT30339 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-67-WT | 1 | 2025-03-18 | 2025-03-19
| JD3RZ07L67WT30370 | EXCAVATION and Bedding Worksfor Fire Hydrant - - B3.33 14 19.08-Z07-L-67-WT | 1 | 2025-03-09 | 2025-03-10
| JD3RZ07L67WT30371 | INSTALLATIONfor Fire Hydrant - - B3.33 14 19.08-Z07-L-67-WT | 1 | 2025-03-11 | 2025-03-12
| JD3RZ07L67WT30372 | TESTING AND COMMITIONfor Fire Hydrant - - B3.33 14 19.08-Z07-L-67-WT | 1 | 2025-03-13 | 2025-03-15
| JD3RZ07L68ST30822 | Excavation Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-68-ST | 1 | 2025-01-25 | 2025-01-26
| JD3RZ07L68ST30823 | Soil Replacement and Bedding Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-68-ST | 1 | 2025-01-27 | 2025-01-28
| JD3RZ07L68ST30824 | Installing for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-68-ST | 1 | 2025-01-29 | 2025-01-30
| JD3RZ07L68ST30825 | Primary Test for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-68-ST | 1 | 2025-02-01 | 2025-02-02
| JD3RZ07L68ST30826 | Backfilling Works for UPVC Pipe Line 300 mm - depth from 0.00 to 1.50 m- B6.33 14 11.01-Z07-L-68-ST | 1 | 2025-02-03 | 2025-02-04
| JD3RZ07L68ST30827 | Excavation Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-68-ST | 1 | 2025-01-27 | 2025-01-28
| JD3RZ07L68ST30828 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-68-ST | 1 | 2025-01-29 | 2025-01-30
| JD3RZ07L68ST30829 | Installing for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-68-ST | 1 | 2025-02-01 | 2025-02-02
| JD3RZ07L68ST30830 | Primary Test for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-68-ST | 1 | 2025-02-03 | 2025-02-04
| JD3RZ07L68ST30831 | Backfilling Works for GRP Pipe Line 400 mm - depth from 0.00 to 1.50 m- B6.33 42 11.01-Z07-L-68-ST | 1 | 2025-02-05 | 2025-02-06
| JD3RZ07L68ST30832 | Excavation Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-68-ST | 1 | 2025-01-29 | 2025-01-30
| JD3RZ07L68ST30833 | Soil Replacement and Bedding Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-68-ST | 1 | 2025-02-01 | 2025-02-02
| JD3RZ07L68ST30834 | Installing for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-68-ST | 1 | 2025-02-03 | 2025-02-04
| JD3RZ07L68ST30835 | Primary Test for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-68-ST | 1 | 2025-02-05 | 2025-02-06
| JD3RZ07L68ST30836 | Backfilling Works for GRP Pipe Line 400 mm - depth from 1.51 to 2.50 m- B6.33 42 11.02-Z07-L-68-ST | 1 | 2025-02-08 | 2025-02-09
| JD3RZ07L68ST30837 | Excavation Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-68-ST | 1 | 2025-02-01 | 2025-02-02 | 2025-03-11 | 2025-03-29
| JD3RZ07L68ST30838 | Soil Replacement and Bedding Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-68-ST | 1 | 2025-02-03 | 2025-02-04 | 2025-03-12 | 2025-03-30
| JD3RZ07L68ST30839 | Installing for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-68-ST | 1 | 2025-02-05 | 2025-02-06 | 2025-03-19 | 2025-04-06
| JD3RZ07L68ST30840 | Primary Test for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-68-ST | 1 | 2025-02-08 | 2025-02-09
| JD3RZ07L68ST30841 | Backfilling Works for GRP Pipe Line 500 mm - depth from 0.00 to 1.50 m- B6.33 42 11.03-Z07-L-68-ST | 1 | 2025-02-10 | 2025-02-11
| JD3RZ07L68ST30847 | Excavation Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z07-L-68-ST | 1 | 2025-02-01 | 2025-02-02
| JD3RZ07L68ST30848 | Soil Replacement and Bedding Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z07-L-68-ST | 1 | 2025-02-03 | 2025-02-04
| JD3RZ07L68ST30849 | Installing for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z07-L-68-ST | 1 | 2025-02-05 | 2025-02-06
| JD3RZ07L68ST30850 | Primary Test for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z07-L-68-ST | 1 | 2025-02-08 | 2025-02-09
| JD3RZ07L68ST30851 | Backfilling Works for GRP Pipe Line 600 mm - depth from 0.00 to 1.50 m- B6.33 42 11.05-Z07-L-68-ST | 1 | 2025-02-10 | 2025-02-11
| JD3RZ07L68ST30857 | Excavation Works for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m- B6.33 42 11.07-Z07-L-68-ST | 1 | 2025-02-03 | 2025-02-04 | 2025-03-03 | 2025-03-20
| JD3RZ07L68ST30858 | Soil Replacement and Bedding Works for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m- B6.33 42 11.07-Z07-L-68-ST | 1 | 2025-02-05 | 2025-02-06 | 2025-03-05 | 2025-03-23
| JD3RZ07L68ST30859 | Installing for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m- B6.33 42 11.07-Z07-L-68-ST | 1 | 2025-02-08 | 2025-02-09 | 2025-03-06 | 2025-03-24
| JD3RZ07L68ST30860 | Primary Test for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m- B6.33 42 11.07-Z07-L-68-ST | 1 | 2025-02-10 | 2025-02-11
| JD3RZ07L68ST30861 | Backfilling Works for GRP Pipe Line 700 mm - depth from 0.00 to 1.50 m- B6.33 42 11.07-Z07-L-68-ST | 1 | 2025-02-12 | 2025-02-13
| JD3RZ07L68ST30872 | Excavation Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-68-ST | 1 | 2025-02-05 | 2025-02-06 | 2025-03-18 | 2025-04-05
| JD3RZ07L68ST30873 | Soil Replacement and Bedding Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-68-ST | 1 | 2025-02-08 | 2025-02-09 | 2025-03-19 | 2025-04-06
| JD3RZ07L68ST30874 | Installing for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-68-ST | 1 | 2025-02-10 | 2025-02-11 | 2025-03-20 | 2025-04-07
| JD3RZ07L68ST30875 | Primary Test for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-68-ST | 1 | 2025-02-12 | 2025-02-13
| JD3RZ07L68ST30876 | Backfilling Works for GRP Pipe Line 800 mm - depth from 1.51 to 2.50 m- B6.33 42 11.10-Z07-L-68-ST | 1 | 2025-02-15 | 2025-02-16
| JD3RZ07L68ST30882 | Excavation Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-68-ST | 1 | 2025-02-08 | 2025-02-09 | 2025-03-04 | 2025-03-22
| JD3RZ07L68ST30883 | Soil Replacement and Bedding Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-68-ST | 1 | 2025-02-10 | 2025-02-11 | 2025-03-05 | 2025-03-23
| JD3RZ07L68ST30884 | Installing for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-68-ST | 1 | 2025-02-12 | 2025-02-13 | 2025-03-06 | 2025-03-24
| JD3RZ07L68ST30885 | Primary Test for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-68-ST | 1 | 2025-02-15 | 2025-02-16
| JD3RZ07L68ST30886 | Backfilling Works for GRP Pipe Line 900 mm - depth from 1.51 to 2.50 m- B6.33 42 11.12-Z07-L-68-ST | 1 | 2025-02-17 | 2025-02-18
| JD3RZ07L68ST30907 | Excavation Works for GRP Pipe Line 1100 mm - depth from 0.00 to 1.50 m- B6.33 42 11.19-Z07-L-68-ST | 1 | 2025-02-03 | 2025-02-04
| JD3RZ07L68ST30908 | Soil Replacement and Bedding Works for GRP Pipe Line 1100 mm - depth from 0.00 to 1.50 m- B6.33 42 11.19-Z07-L-68-ST | 1 | 2025-02-05 | 2025-02-06
| JD3RZ07L68ST30909 | Installing for GRP Pipe Line 1100 mm - depth from 0.00 to 1.50 m- B6.33 42 11.19-Z07-L-68-ST | 1 | 2025-02-08 | 2025-02-09
| JD3RZ07L68ST30910 | Primary Test for GRP Pipe Line 1100 mm - depth from 0.00 to 1.50 m- B6.33 42 11.19-Z07-L-68-ST | 1 | 2025-02-10 | 2025-02-11
| JD3RZ07L68ST30911 | Backfilling Works for GRP Pipe Line 1100 mm - depth from 0.00 to 1.50 m- B6.33 42 11.19-Z07-L-68-ST | 1 | 2025-02-12 | 2025-02-13
| JD3RZ07L68ST30912 | Excavation Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z07-L-68-ST | 1 | 2025-02-05 | 2025-02-06
| JD3RZ07L68ST30913 | Soil Replacement and Bedding Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z07-L-68-ST | 1 | 2025-02-08 | 2025-02-09
| JD3RZ07L68ST30914 | Installing for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z07-L-68-ST | 1 | 2025-02-10 | 2025-02-11
| JD3RZ07L68ST30915 | Primary Test for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z07-L-68-ST | 1 | 2025-02-12 | 2025-02-13
| JD3RZ07L68ST30916 | Backfilling Works for GRP Pipe Line 1100 mm - depth from 1.51 to 2.50 m- B6.33 42 11.20-Z07-L-68-ST | 1 | 2025-02-15 | 2025-02-16
| JD3RZ07L68ST31005 | Excavation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-68-ST | 1 | 2025-02-08 | 2025-02-09 | 2025-03-05 | 2025-03-23
| JD3RZ07L68ST31006 | Base Plain Concrete Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-68-ST | 1 | 2025-02-10 | 2025-02-11 | 2025-05-20 | 2025-06-07
| JD3RZ07L68ST31007 | Manhole Installation Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-68-ST | 1 | 2025-02-12 | 2025-02-13
| JD3RZ07L68ST31008 | FINISHING Works and Backfilling Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-68-ST | 1 | 2025-02-15 | 2025-02-16
| JD3RZ07L68ST31009 | TESTING AND COMMITIONING Works For Manholes Diam 1200 depth from 1.51 to 2.50 - - B6.33 05 39.02-Z07-L-68-ST | 1 | 2025-02-17 | 2025-02-18
| JD3RZ07L68ST31015 | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-68-ST | 1 | 2025-02-10 | 2025-02-11 | 2025-03-05 | 2025-03-23
| JD3RZ07L68ST31015.R | Excavation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-68-ST -Remaining | 1 | 2025-02-19 | 2025-02-20 | 2025-08-02 | 2025-08-03
| JD3RZ07L68ST31016 | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-68-ST | 1 | 2025-02-12 | 2025-02-13 | 2025-05-20 | 2025-06-07
| JD3RZ07L68ST31016.R | Base Plain Concrete Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-68-ST -Remaining | 1 | 2025-02-22 | 2025-02-23 | 2025-08-03 | 2025-08-04
| JD3RZ07L68ST31017 | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-68-ST | 1 | 2025-02-15 | 2025-02-16 | 2025-06-30 | 2025-07-17
| JD3RZ07L68ST31017.R | Manhole Installation Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-68-ST -Remaining | 1 | 2025-02-24 | 2025-02-25
| JD3RZ07L68ST31018 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-68-ST | 1 | 2025-02-26 | 2025-02-27
| JD3RZ07L68ST31019 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 1.51 to 2.50 - - B6.33 05 39.04-Z07-L-68-ST | 1 | 2025-03-01 | 2025-03-02
| JD3RZ07L68ST31020 | Excavation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-L-68-ST | 1 | 2025-02-08 | 2025-02-09 | 2025-08-20 | 2025-08-21
| JD3RZ07L68ST31021 | Base Plain Concrete Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-L-68-ST | 1 | 2025-02-10 | 2025-02-11 | 2025-08-23 | 2025-08-24
| JD3RZ07L68ST31022 | Manhole Installation Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-L-68-ST | 1 | 2025-02-12 | 2025-02-13
| JD3RZ07L68ST31023 | FINISHING Works and Backfilling Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-L-68-ST | 1 | 2025-02-15 | 2025-02-16
| JD3RZ07L68ST31024 | TESTING AND COMMITIONING Works For Manholes Diam 1500 depth from 2.51 to 3.50 - - B6.33 05 39.05-Z07-L-68-ST | 1 | 2025-02-17 | 2025-02-18
| JD3RZ07L68ST31030 | Excavation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-L-68-ST | 1 | 2025-02-10 | 2025-02-11 | 2025-08-23 | 2025-08-24
| JD3RZ07L68ST31031 | Base Plain Concrete Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-L-68-ST | 1 | 2025-02-12 | 2025-02-13
| JD3RZ07L68ST31032 | Manhole Installation Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-L-68-ST | 1 | 2025-02-15 | 2025-02-16
| JD3RZ07L68ST31033 | FINISHING Works and Backfilling Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-L-68-ST | 1 | 2025-02-17 | 2025-02-18
| JD3RZ07L68ST31034 | TESTING AND COMMITIONING Works For Manholes Diam 2000 depth from 1.51 to 2.50 - - B6.33 05 39.07-Z07-L-68-ST | 1 | 2025-02-19 | 2025-02-20
| JD3RZ07L68ST31040 | EXCAVATION Works for Catchbasine single - - B6.33 05 39.09-Z07-L-68-ST | 1 | 2025-02-12 | 2025-02-13
| JD3RZ07L68ST31041 | Catchbasine Installation Works For Catchbasine single - - B6.33 05 39.09-Z07-L-68-ST | 1 | 2025-02-15 | 2025-02-16
| JD3RZ07L68ST31042 | FINISHING Works For Catchbasine single - - B6.33 05 39.09-Z07-L-68-ST | 1 | 2025-02-17 | 2025-02-18
| JD3RZ07L68ST31043 | TESTING AND COMMITIONING RELEASEDfor Catchbasine single - - B6.33 05 39.09-Z07-L-68-ST | 1 | 2025-02-19 | 2025-02-20
| JD3RZ07L68ST31044 | EXCAVATION Works for Catchbasine double - - B6.33 05 39.10-Z07-L-68-ST | 1 | 2025-02-15 | 2025-02-16
| JD3RZ07L68ST31045 | Catchbasine Installation Works For Catchbasine double - - B6.33 05 39.10-Z07-L-68-ST | 1 | 2025-02-17 | 2025-02-18
| JD3RZ07L68ST31046 | FINISHING Works For Catchbasine double - - B6.33 05 39.10-Z07-L-68-ST | 1 | 2025-02-19 | 2025-02-20
| JD3RZ07L68ST31047 | TESTING AND COMMITIONING RELEASEDfor Catchbasine double - - B6.33 05 39.10-Z07-L-68-ST | 1 | 2025-02-22 | 2025-02-23
| JD3RZ07L68TSE31098 | Excavation Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-68-TSE | 1 | 2025-03-03 | 2025-03-04
| JD3RZ07L68TSE31099 | Soil Replacement and Bedding Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-68-TSE | 1 | 2025-03-05 | 2025-03-06
| JD3RZ07L68TSE31100 | installationfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-68-TSE | 1 | 2025-03-08 | 2025-03-09
| JD3RZ07L68TSE31101 | Testingfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-68-TSE | 1 | 2025-03-10 | 2025-03-11
| JD3RZ07L68TSE31102 | Backfilling Worksfor HDPE Pipe Lines 125 mm - depth from 0 to 1.5 m- B4.33 31 00.01-Z07-L-68-TSE | 1 | 2025-03-15 | 2025-03-16
| JD3RZ07L68TSE31113 | Excavation Worksfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-68-TSE | 1 | 2025-03-05 | 2025-03-06 | 2025-04-05 | 2025-04-22
| JD3RZ07L68TSE31114 | Soil Replacement and Bedding Works for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-68-TSE | 1 | 2025-03-08 | 2025-03-09 | 2025-04-10 | 2025-04-28
| JD3RZ07L68TSE31115 | Installing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-68-TSE | 1 | 2025-03-10 | 2025-03-12 | 2025-04-26 | 2025-06-19
| JD3RZ07L68TSE31116 | Testing for HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-68-TSE | 1 | 2025-03-13 | 2025-03-15 | 2025-05-10 | 2025-07-03
| JD3RZ07L68TSE31117 | Backfillingfor HDPE Pipes 315 mm - depth from 1.51 to 2.5 m- B4.33 31 00.04-Z07-L-68-TSE | 1 | 2025-03-16 | 2025-03-17 | 2025-06-12 | 2025-06-30
| JD3RZ07L68TSE31223 | Installationfor gate valves 100 mm - - B4.33 14 19.01-Z07-L-68-TSE | 1 | 2025-03-10 | 2025-03-11
| JD3RZ07L68TSE31224 | Testing And Commtionningfor gate valves 100 mm - - B4.33 14 19.01-Z07-L-68-TSE | 1 | 2025-03-12 | 2025-03-13
| JD3RZ07L68TSE31241 | Installationfor Air valves 50 mm. - on pipes with diameter less than 315 mm- B4.33 14 19.15-Z07-L-68-TSE | 1 | 2025-03-10 | 2025-03-11
| JD3RZ07L68TSE31242 | Testing And Commtionningfor Air valves 50 mm. - on pipes with diameter less than 315 mm- B4.33 14 19.15-Z07-L-68-TSE | 1 | 2025-03-12 | 2025-03-13
| JD3RZ07L68TSE31271 | EXCAVATION and Bedding Worksfor Air Valve Chamber - less than 315 mm- B4.33 14 13.10-Z07-L-68-TSE | 1 | 2025-03-03 | 2025-03-04
| JD3RZ07L68TSE31272 | Plain Concrete Worksfor Air Valve Chamber - less than 315 mm- B4.33 14 13.10-Z07-L-68-TSE | 1 | 2025-03-05 | 2025-03-06
| JD3RZ07L68TSE31273 | INSTALLATIONfor Air Valve Chamber - less than 315 mm- B4.33 14 13.10-Z07-L-68-TSE | 1 | 2025-03-08 | 2025-03-09
| JD3RZ07L68TSE31274 | Backfilling Worksfor Air Valve Chamber - less than 315 mm- B4.33 14 13.10-Z07-L-68-TSE | 1 | 2025-03-15 | 2025-03-16
| JD3RZ07L68WT31048 | Excavation Worksfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-68-WT | 1 | 2025-03-18 | 2025-03-19
| JD3RZ07L68WT31049 | Soil Replacement and Bedding Works for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-68-WT | 1 | 2025-03-20 | 2025-03-22
| JD3RZ07L68WT31050 | Installing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-68-WT | 1 | 2025-03-23 | 2025-03-24
| JD3RZ07L68WT31051 | Testing for HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-68-WT | 1 | 2025-03-25 | 2025-03-26
| JD3RZ07L68WT31052 | Backfillingfor HDPE Pipes 160 mm - depth from 0 to 1.5 m- B3.33 14 13.01-Z07-L-68-WT | 1 | 2025-03-27 | 2025-03-29
| JD3RZ07L68WT31083 | EXCAVATION and Bedding Worksfor Fire Hydrant - - B3.33 14 19.08-Z07-L-68-WT | 1 | 2025-03-20 | 2025-03-22
| JD3RZ07L68WT31084 | INSTALLATIONfor Fire Hydrant - - B3.33 14 19.08-Z07-L-68-WT | 1 | 2025-03-23 | 2025-03-24
| JD3RZ07L68WT31085 | TESTING AND COMMITIONfor Fire Hydrant - - B3.33 14 19.08-Z07-L-68-WT | 1 | 2025-03-25 | 2025-03-26
| JDH3-02-008RAT86 | Electrical Network Authorities Permits & Approvall - AT | 1 | 2024-09-05 | 2024-09-10 | 2024-10-21 | 2024-12-03
| JDH3-02-008RELMI18 | Start of ELECTRICAL Network-MI-EL-SL-TC | 1 | 2024-07-30 |  | 2025-05-10
| JDH3-02-008RELMI19 | Finish of ELECTRICAL Network-MI-EL-SL-TC | 1 |  | 2025-05-18
| JDH3-02-008RMI1 | Project Start - MI | 1 | 2024-07-30 |  | 2024-07-29
| JDH3-02-008RMI12 | Site Handover Date - MI | 1 | 2024-07-30 |  | 2024-07-29
| JDH3-02-008RMI2 | Complete Mobilization - MI | 1 |  | 2024-09-04 |  | 2024-10-26
| JDH3-02-008RMI3 | Prepare and Submit Project Management Plan - MI | 1 |  | 2024-07-30 |  | 2024-10-21
| JDH3-02-008RMI4 | Prepare and Submit Shop Drawings and Material Submittals - MI | 1 |  | 2024-07-30 |  | 2025-07-26
| JDH3-02-008RMob61 | Installation Of Offices - Mob | 1 | 2024-07-30 | 2024-08-31 | 2024-09-01 | 2025-05-20
| JDH3-02-008RMob62 | Mobilization Of Equipment - Mob | 1 | 2024-07-30 | 2024-08-12 | 2024-08-21 | 2024-12-11
| JDH3-02-008RMob63 | Access Road works - Mob | 1 | 2024-07-30 | 2024-08-03 | 2024-09-18 | 2024-10-26
| JDH3-02-008RMob64 | Build up Project Store - Mob | 1 | 2024-07-30 | 2024-08-31 | 2024-09-07 | 2025-05-26
| JDH3-02-008RMob66 | Install of Project Signboard - Mob | 1 | 2024-07-30 | 2024-08-03 | 2024-09-07 | 2024-10-14
| JDH3-02-008RMob67 | Preparation Of Parking Area - Mob | 1 | 2024-07-30 | 2024-08-07 | 2024-09-22 | 2024-12-05
| JDH3-02-008RMRMI27 | Start of Main Roads - MI-MR | 1 | 2024-07-30 |  | 2024-11-23
| JDH3-02-008RMRSD192 | Prepare and Submit Drawing for Sewage Network for -MR-SD-SS | 1 | 2024-07-30 | 2024-08-05 | 2024-09-16 | 2024-11-11
| JDH3-02-008RMRSD193 | Prepare and Submit Drawing for Storm Network - Pipes for -MR-SD-ST | 1 | 2024-07-30 | 2024-08-12 | 2024-10-10 | 2025-01-29
| JDH3-02-008RMRSD194 | Prepare and Submit Drawing for Storm Network - Collecting Lakes (PONDS) for -MR-SD-ST | 1 | 2024-07-30 | 2024-08-05 | 2024-09-16 | 2024-11-11
| JDH3-02-008RMRSD195 | Prepare and Submit Drawing for Potable Water Network for -MR-SD-WT | 1 | 2024-07-30 | 2024-08-05 | 2024-09-25 | 2024-11-19
| JDH3-02-008RMRSD196 | Prepare and Submit Drawing for Fire Hydrant Network for -MR-SD-WT | 1 | 2024-07-30 | 2024-08-05 | 2024-09-25 | 2024-11-19
| JDH3-02-008RMRSD197 | Prepare and Submit Drawing for TSE (IRRIGATION) Network for -MR-SD-TSE | 1 | 2024-07-30 | 2024-08-05 | 2024-10-20 | 2024-12-14
| JDH3-02-008RMRSD199 | Prepare and Submit Drawing for Street Lighting Network for -MR-SD-SL | 1 | 2024-07-30 | 2024-08-05 | 2024-10-15 | 2024-12-09
| JDH3-02-008RMRSD200 | Prepare and Submit Drawing for Telecommunications Network for -MR-SD-TC | 1 | 2024-07-30 | 2024-08-05 | 2024-10-15 | 2024-12-09
| JDH3-02-008RMRSD201 | Prepare and Submit Drawing for Road Works( KERBING AND PAVEMENT ) for -MR-SD-RD | 1 | 2024-07-30 | 2024-08-05 | 2024-10-02 | 2024-11-26
| JDH3-02-008RMRSD202 | Prepare and Submit Drawing for Road Works ( TRAFFIC SIGN AND MARKING) for -MR-SD-RD | 1 | 2024-07-30 | 2024-08-05 | 2024-10-02 | 2024-11-26
| JDH3-02-008RMRSD307 | Review and Approval Drawing for Sewage Network for -MR-SD-SS | 1 | 2024-08-06 | 2024-08-19 | 2024-09-30 | 2025-01-19
| JDH3-02-008RMRSD308 | Review and Approval Drawing for Storm Network - Pipes for -MR-SD-ST | 1 | 2024-08-13 | 2024-08-26 | 2024-10-21 | 2025-02-09
| JDH3-02-008RMRSD309 | Review and Approval Drawing for Storm Network - Collecting Lakes (PONDS) for -MR-SD-ST | 1 | 2024-08-06 | 2024-08-19 | 2024-09-17 | 2025-01-07
| JDH3-02-008RMRSD310 | Review and Approval Drawing for Potable Water Network for -MR-SD-WT | 1 | 2024-08-06 | 2024-08-19 | 2024-10-21 | 2025-02-09
| JDH3-02-008RMRSD311 | Review and Approval Drawing for Fire Hydrant Network for -MR-SD-WT | 1 | 2024-08-06 | 2024-08-19 | 2024-10-21 | 2025-02-09
| JDH3-02-008RMRSD312 | Review and Approval Drawing for TSE (IRRIGATION) Network for -MR-SD-TSE | 1 | 2024-08-06 | 2024-08-19 | 2024-10-31 | 2025-02-19
| JDH3-02-008RMRSD314 | Review and Approval Drawing for Street Lighting Network for -MR-SD-SL | 1 | 2024-08-06 | 2024-08-19 | 2024-10-25 | 2025-02-13
| JDH3-02-008RMRSD315 | Review and Approval Drawing for Telecommunications Network for -MR-SD-TC | 1 | 2024-08-06 | 2024-08-19 | 2024-10-23 | 2025-02-11
| JDH3-02-008RMRSD316 | Review and Approval Drawing for Road Works( KERBING AND PAVEMENT ) for -MR-SD-RD | 1 | 2024-08-06 | 2024-08-19 | 2024-10-24 | 2025-02-12
| JDH3-02-008RMRSD317 | Review and Approval Drawing for Road Works ( TRAFFIC SIGN AND MARKING) for -MR-SD-RD | 1 | 2024-08-06 | 2024-08-19 | 2024-10-24 | 2025-02-12
| JDH3-02-008RPP68 | Prepare & Submit Soil Investigation - PP | 1 | 2024-07-30 | 2024-08-07 | 2024-08-20 | 2024-11-03
| JDH3-02-008RPP69 | Review & approval Soil Investigation - PP | 1 | 2024-08-08 | 2024-08-21 | 2024-08-26 | 2024-12-16
| JDH3-02-008RPP70 | Prepare & Submit Land surveying works - PP | 1 | 2024-07-30 | 2024-08-07 | 2024-08-07 | 2024-10-21
| JDH3-02-008RPP71 | Review & approval Land surveying works - PP | 1 | 2024-08-08 | 2024-08-21 | 2024-08-21 | 2024-12-11
| JDH3-02-008RPP72 | Prepare & Submit Shop Drawings Submission Plan - PP | 1 | 2024-07-30 | 2024-08-07 | 2024-08-28 | 2024-11-11
| JDH3-02-008RPP73 | Review & approval Shop Drawings Submission Plan - PP | 1 | 2024-08-08 | 2024-08-21 | 2024-09-04 | 2024-12-25
| JDH3-02-008RPP74 | Prepare & Submit Material submittal plan - PP | 1 | 2024-07-30 | 2024-08-07 | 2024-08-15 | 2024-10-29
| JDH3-02-008RPP75 | Review & approval Material submittal plan - PP | 1 | 2024-08-08 | 2024-08-21 | 2024-08-26 | 2024-12-16
| JDH3-02-008RPP76 | Prepare & Submit Project Schedule - PP | 1 | 2024-07-30 | 2024-08-18 | 2024-07-29 | 2025-01-04
| JDH3-02-008RPP77 | Review & approval Project Schedule - PP | 1 | 2024-08-19 | 2024-09-01 | 2024-09-12 | 2025-01-02
| JDH3-02-008RPP78 | Prepare & Submit HSE (Health, Safety & Environment) Plan - PP | 1 | 2024-07-30 | 2024-08-06 | 2024-09-18 | 2024-11-23
| JDH3-02-008RPP79 | Review & approval HSE (Health, Safety & Environment) Plan - PP | 1 | 2024-08-07 | 2024-08-20 | 2024-09-22 | 2025-01-12
| JDH3-02-008RPP80 | Prepare & Submit Logistic Plan-Site Mobilization Plan - PP | 1 | 2024-07-30 | 2024-08-06 | 2024-09-02 | 2024-11-06
| JDH3-02-008RPP81 | Review & approval Logistic Plan-Site Mobilization Plan - PP | 1 | 2024-08-07 | 2024-08-21 | 2024-09-25 | 2025-01-26
| JDH3-02-008RPP82 | Prepare & Submit Organization chart and Recruitment plan - PP | 1 | 2024-07-30 | 2024-08-05 | 2024-08-14 | 2024-10-09
| JDH3-02-008RPP83 | Review & approval Organization chart and Recruitment plan - PP | 1 | 2024-08-06 | 2024-08-19 | 2024-08-28 | 2024-12-18
| JDH3-02-008RPP84 | Prepare & Submit Project management plans - PP | 1 | 2024-07-30 | 2024-08-21 | 2024-07-29 | 2025-02-01
| JDH3-02-008RPP85 | Review & approval Project management plans - PP | 1 | 2024-08-22 | 2024-09-04 | 2024-09-04 | 2024-12-25
| JDH3-02-008RRDMI24 | Start of Road Works - RD - MI-RD | 1 | 2024-07-30 |  | 2024-11-21
| JDH3-02-008RRDPR1245 | Delivery for Concrete - PR-RD-Z11 | 1 | 2025-04-21 | 2025-05-03 | 2024-12-10 | 2025-03-15
| JDH3-02-008RRDPR1246 | Delivery for Backfilling Materials - PR-RD-Z11 | 1 | 2025-05-03 | 2025-05-15 | 2024-12-10 | 2024-12-26
| JDH3-02-008RRDPR1247 | Delivery for Kerbs and Interlock - PR-RD-Z11 | 1 | 2025-05-15 | 2025-05-27 | 2024-11-02 | 2025-02-05
| JDH3-02-008RRDPR1248 | Delivery for Pavement Materials - PR-RD-Z11 | 1 | 2025-05-27 | 2025-06-08 | 2025-04-16 | 2025-05-07
| JDH3-02-008RRDPR1320 | Delivery for Concrete - PR-RD-MR | 1 | 2025-05-10 | 2025-05-21 | 2024-12-04 | 2024-12-24
| JDH3-02-008RRDPR1321 | Delivery for Backfilling Materials - PR-RD-MR | 1 | 2025-05-22 | 2025-06-02 | 2024-12-10 | 2024-12-26
| JDH3-02-008RRDPR1322 | Delivery for Kerbs and Interlock - PR-RD-MR | 1 | 2025-05-22 | 2025-06-02 | 2024-12-29 | 2025-01-06
| JDH3-02-008RRDPR1323 | Delivery for Pavement Materials - PR-RD-MR | 1 | 2025-05-22 | 2025-06-02 | 2025-04-16 | 2025-05-07
| JDH3-02-008RRDPR1333 | Material Fabrication for Concrete - PR-RD | 1 | 2024-08-23 | 2024-08-28 | 2024-11-14 | 2024-12-31
| JDH3-02-008RRDPR1343 | Material Fabrication for Backfilling Materials - PR-RD | 1 | 2024-08-23 | 2024-09-04 | 2025-02-01 | 2025-05-15
| JDH3-02-008RRDPR1353 | Material Fabrication for Kerbs and Interlock - PR-RD | 1 | 2024-08-23 | 2024-08-25 | 2024-10-29 | 2024-11-21
| JDH3-02-008RRDPR1363 | Material Fabrication for Pavement Materials - PR-RD | 1 | 2024-08-16 | 2024-08-18 | 2025-07-10 | 2025-07-31
| JDH3-02-008RRDPR606 | Prepare Material Submittal for Concrete - PR-RD | 1 | 2024-07-30 | 2024-08-05 | 2024-09-21 | 2024-11-16
| JDH3-02-008RRDPR607 | Prepare Material Submittal for Backfilling Materials - PR-RD | 1 | 2024-07-30 | 2024-08-05 | 2024-11-07 | 2025-01-01
| JDH3-02-008RRDPR608 | Prepare Material Submittal for Kerbs and Interlock - PR-RD | 1 | 2024-07-30 | 2024-08-05 | 2024-10-05 | 2024-11-28
| JDH3-02-008RRDPR609 | Prepare Material Submittal for Pavement Materials - PR-RD | 1 | 2024-07-30 | 2024-08-05 | 2025-02-04 | 2025-03-31
| JDH3-02-008RRDPR668 | Review and Approval of Material Submittal for Concrete - PR-RD | 1 | 2024-08-06 | 2024-08-15 | 2024-10-02 | 2024-12-30
| JDH3-02-008RRDPR669 | Review and Approval of Material Submittal for Backfilling Materials - PR-RD | 1 | 2024-08-06 | 2024-08-15 | 2025-01-16 | 2025-04-15
| JDH3-02-008RRDPR670 | Review and Approval of Material Submittal for Kerbs and Interlock - PR-RD | 1 | 2024-08-06 | 2024-08-15 | 2024-10-06 | 2025-01-01
| JDH3-02-008RRDPR671 | Review and Approval of Material Submittal for Pavement Materials - PR-RD | 1 | 2024-07-30 | 2024-08-08 | 2025-05-01 | 2025-07-29
| JDH3-02-008RRDPR730 | Material Purchase Order for Concrete - PR-RD | 1 | 2024-08-16 | 2024-08-22 | 2024-11-14 | 2025-01-08
| JDH3-02-008RRDPR731 | Material Purchase Order for Backfilling Materials - PR-RD | 1 | 2024-08-16 | 2024-08-22 | 2025-02-01 | 2025-03-28
| JDH3-02-008RRDPR732 | Material Purchase Order for Kerbs and Interlock - PR-RD | 1 | 2024-08-16 | 2024-08-22 | 2024-10-29 | 2024-12-23
| JDH3-02-008RRDPR733 | Material Purchase Order for Pavement Materials - PR-RD | 1 | 2024-08-09 | 2024-08-15 | 2025-07-02 | 2025-07-31
| JDH3-02-008RRDPR967 | Delivery for Concrete - PR-RD-Z02-2 | 1 | 2024-08-29 | 2024-09-09 | 2025-05-07 | 2025-07-31
| JDH3-02-008RRDPR968 | Delivery for Backfilling Materials - PR-RD-Z02-2 | 1 | 2024-09-10 | 2024-09-21 | 2025-05-01 | 2025-07-31
| JDH3-02-008RRDPR969 | Delivery for Kerbs and Interlock - PR-RD-Z02-2 | 1 | 2024-09-22 | 2024-10-04 | 2025-05-01 | 2025-07-31
| JDH3-02-008RRDPR970 | Delivery for Pavement Materials - PR-RD-Z02-2 | 1 | 2024-10-05 | 2024-10-16 | 2025-05-01 | 2025-07-31
| JDH3-02-008RSD200 | Prepare and Submit Drawing for Swales for R1 | 1 | 2024-07-30 | 2024-08-18 | 2025-04-01 | 2025-07-31
| JDH3-02-008RSD203 | Review and Approval for General layout - SD | 1 | 2024-08-20 | 2024-09-02 | 2024-08-25 | 2024-12-15
| JDH3-02-008RSD204 | Review and Approval for Ponds - SD | 1 | 2024-08-06 | 2024-08-19 | 2024-09-15 | 2025-01-05
| JDH3-02-008RSD205 | Review and Approval for Swales - SD | 1 | 2024-08-06 | 2024-08-19 | 2024-10-28 | 2025-02-16
| JDH3-02-008RSD206 | Review and Approval for Box Culverts - SD | 1 | 2024-08-06 | 2024-08-19 | 2024-09-17 | 2025-01-07
| JDH3-02-008RSD216 | Prepare and Submit Drawing for Swales for R2 | 1 | 2024-07-30 | 2024-08-18 | 2025-04-01 | 2025-07-31
| JDH3-02-008RSD226 | Prepare and Submit Drawing for Swales for C-01 | 1 | 2024-07-30 | 2024-08-18 | 2025-04-01 | 2025-07-31
| JDH3-02-008RSD236 | Prepare and Submit Drawing for Swales for C-02 | 1 | 2024-07-30 | 2024-08-18 | 2025-04-01 | 2025-07-31
| JDH3-02-008RSD246 | Prepare and Submit Drawing for Swales for C-03 | 1 | 2024-07-30 | 2024-08-18 | 2025-04-01 | 2025-07-31
| JDH3-02-008RSD266 | Prepare and Submit Drawing for Swales for C-05 | 1 | 2024-07-30 | 2024-08-18 | 2025-04-01 | 2025-07-31
| JDH3-02-008RSD276 | Prepare and Submit Drawing for Swales for C-08 | 1 | 2024-07-30 | 2024-08-18 | 2025-04-01 | 2025-07-31
| JDH3-02-008RSD286 | Prepare and Submit Drawing for Swales for C-09 | 1 | 2024-07-30 | 2024-08-18 | 2025-04-01 | 2025-07-31
| JDH3-02-008RSD296 | Prepare and Submit Drawing for Swales for C-10 | 1 | 2024-07-30 | 2024-08-18 | 2025-04-01 | 2025-07-31
| JDH3-02-008RSD306 | Prepare and Submit Drawing for Swales for C-11 | 1 | 2024-07-30 | 2024-08-18 | 2025-04-01 | 2025-07-31
| JDH3-02-008RSD316 | Prepare and Submit Drawing for Swales for C-12 | 1 | 2024-07-30 | 2024-08-18 | 2025-04-01 | 2025-07-31
| JDH3-02-008RSD326 | Prepare and Submit Drawing for Swales for C-13 | 1 | 2024-07-30 | 2024-08-18 | 2025-04-01 | 2025-07-31
| JDH3-02-008RSD336 | Prepare and Submit Drawing for Swales for C-14 | 1 | 2024-07-30 | 2024-08-18 | 2025-04-01 | 2025-07-31
| JDH3-02-008RSD346 | Prepare and Submit Drawing for Swales for C-15 | 1 | 2024-07-30 | 2024-08-18 | 2025-04-01 | 2025-07-31
| JDH3-02-008RSD356 | Prepare and Submit Drawing for Swales for L-58 | 1 | 2024-07-30 | 2024-08-18 | 2025-04-01 | 2025-07-31
| JDH3-02-008RSD366 | Prepare and Submit Drawing for Pond 6 | 1 | 2024-07-30 | 2024-08-22 | 2025-03-01 | 2025-07-31
| JDH3-02-008RSD376 | Prepare and Submit Drawing for Pond 12 | 1 | 2024-07-30 | 2024-08-06 | 2025-03-01 | 2025-04-07
| JDH3-02-008RSD386 | Prepare and Submit Drawing for L-74 | 1 | 2024-07-30 | 2024-08-06 | 2025-01-04 | 2025-02-10
| JDH3-02-008RSD396 | Prepare and Submit Drawing for L-75 | 1 | 2024-07-30 | 2024-08-06 | 2025-01-04 | 2025-02-10
| JDH3-02-008RSD406 | Prepare and Submit Drawing for Tranfer Lighting Poles | 1 | 2024-07-30 | 2024-08-04 | 2025-04-15 | 2025-05-31
| JDH3-02-008RSD416 | Prepare and Submit Drawing for Potable Water for connection Z13-C10 | 1 | 2024-07-30 | 2024-08-10 | 2025-01-20 | 2025-04-22
| JDH3-02-008RSD426 | Prepare and Submit Drawing for Storm Water for connection Z13-C10 | 1 | 2024-07-30 | 2024-08-18 | 2025-03-01 | 2025-07-31
| JDH3-02-008RSD436 | Prepare and Submit Drawing for Roundabout Catchbasin for Z-02 | 1 | 2024-07-30 | 2024-08-14 | 2024-10-30 | 2025-03-09
| JDH3-02-008RSD446 | Prepare and Submit Drawing for Roundabout Catchbasin for Z-02-2 | 1 | 2024-07-30 | 2024-08-14 | 2024-10-30 | 2025-03-09
| JDH3-02-008RSD456 | Prepare and Submit Drawing for Roundabout Catchbasin for Z-04 | 1 | 2024-07-30 | 2024-08-14 | 2024-10-30 | 2025-03-09
| JDH3-02-008RSD466 | Prepare and Submit Drawing for Roundabout Catchbasin for Z-05 | 1 | 2024-07-30 | 2024-08-14 | 2024-10-30 | 2025-03-09
| JDH3-02-008RSD476 | Prepare and Submit Drawing for Roundabout Catchbasin for Z-08 | 1 | 2024-07-30 | 2024-08-14 | 2024-10-30 | 2025-03-09
| JDH3-02-008RSD486 | Prepare and Submit Drawing for Roundabout Catchbasin for Z11 | 1 | 2024-07-30 | 2024-08-12 | 2025-03-26 | 2025-07-15
| JDH3-02-008RSD496 | Prepare and Submit Drawing for Roundabout Catchbasin for Z12 | 1 | 2024-07-30 | 2024-08-12 | 2025-03-26 | 2025-07-15
| JDH3-02-008RSD506 | Prepare and Submit Drawing for Roundabout Catchbasin for Z13 | 1 | 2024-07-30 | 2024-08-12 | 2025-03-26 | 2025-07-15
| JDH3-02-008RSD516 | Prepare and Submit Drawing for Storm network for R1 | 1 | 2024-07-30 | 2024-08-18 | 2025-03-01 | 2025-07-31
| JDH3-02-008RSD526 | Prepare and Submit Drawing for Storm network for R2 | 1 | 2024-07-30 | 2024-08-18 | 2025-03-01 | 2025-07-31
| JDH3-02-008RSD536 | Prepare and Submit Drawing for Box Culvert for R1 | 1 | 2024-07-30 | 2024-08-11 | 2025-06-01 | 2025-07-31
| JDH3-02-008RSD546 | Prepare and Submit Drawing for Box Culvert for R2 | 1 | 2024-07-30 | 2024-08-11 | 2025-06-01 | 2025-07-31
| JDH3-02-008RSD556 | Review and Approval Drawing for Swales for R1 | 1 | 2024-08-19 | 2024-09-09 | 2025-04-09 | 2025-07-31
| JDH3-02-008RSD566 | Review and Approval Drawing for Swales for R2 | 1 | 2024-08-19 | 2024-09-09 | 2025-04-09 | 2025-07-31
| JDH3-02-008RSD576 | Review and Approval Drawing for Swales for C-01 | 1 | 2024-08-19 | 2024-09-09 | 2025-04-09 | 2025-07-31
| JDH3-02-008RSD586 | Review and Approval Drawing for Swales for C-02 | 1 | 2024-08-19 | 2024-09-09 | 2025-04-09 | 2025-07-31
| JDH3-02-008RSD596 | Review and Approval Drawing for Swales for C-03 | 1 | 2024-08-19 | 2024-09-09 | 2025-04-09 | 2025-07-31
| JDH3-02-008RSD616 | Review and Approval Drawing for Swales for C-05 | 1 | 2024-08-19 | 2024-09-09 | 2025-04-09 | 2025-07-31
| JDH3-02-008RSD626 | Review and Approval Drawing for Swales for C-08 | 1 | 2024-08-19 | 2024-09-09 | 2025-04-09 | 2025-07-31
| JDH3-02-008RSD636 | Review and Approval Drawing for Swales for C-09 | 1 | 2024-08-19 | 2024-09-09 | 2025-04-09 | 2025-07-31
| JDH3-02-008RSD646 | Review and Approval Drawing for Swales for C-10 | 1 | 2024-08-19 | 2024-09-09 | 2025-04-09 | 2025-07-31
| JDH3-02-008RSD656 | Review and Approval Drawing for Swales for C-11 | 1 | 2024-08-19 | 2024-09-09 | 2025-04-09 | 2025-07-31
| JDH3-02-008RSD666 | Review and Approval Drawing for Swales for C-12 | 1 | 2024-08-19 | 2024-09-09 | 2025-04-09 | 2025-07-31
| JDH3-02-008RSD676 | Review and Approval Drawing for Swales for C-13 | 1 | 2024-08-19 | 2024-09-09 | 2025-04-09 | 2025-07-31
| JDH3-02-008RSD686 | Review and Approval Drawing for Swales for C-14 | 1 | 2024-08-19 | 2024-09-09 | 2025-04-09 | 2025-07-31
| JDH3-02-008RSD696 | Review and Approval Drawing for Swales for C-15 | 1 | 2024-08-19 | 2024-09-09 | 2025-04-09 | 2025-07-31
| JDH3-02-008RSD706 | Review and Approval Drawing for Swales for L-58 | 1 | 2024-08-19 | 2024-09-09 | 2025-04-09 | 2025-07-31
| JDH3-02-008RSD716 | Review and Approval Drawing for Pond 6 | 1 | 2024-08-25 | 2024-09-10 | 2025-03-13 | 2025-07-31
| JDH3-02-008RSD726 | Review and Approval Drawing for Pond 12 | 1 | 2024-08-07 | 2024-08-15 | 2025-03-13 | 2025-07-31
| JDH3-02-008RSD736 | Review and Approval Drawing for L-74 | 1 | 2024-08-07 | 2024-08-15 | 2025-01-13 | 2025-07-31
| JDH3-02-008RSD746 | Review and Approval Drawing for L-75 | 1 | 2024-08-07 | 2024-08-15 | 2025-01-13 | 2025-07-31
| JDH3-02-008RSD756 | Review and Approval Drawing for Tranfer Lighting Poles | 1 | 2024-08-05 | 2024-08-07 | 2025-04-21 | 2025-05-22
| JDH3-02-008RSD766 | Review and Approval Drawing for Potable Water for connection Z13-C10 | 1 | 2024-08-11 | 2024-08-12 | 2025-02-01 | 2025-02-23
| JDH3-02-008RSD776 | Review and Approval Drawing for Storm Water for connection Z13-C10 | 1 | 2024-08-19 | 2024-08-25 | 2025-03-19 | 2025-05-13
| JDH3-02-008RSD786 | Review and Approval Drawing for Roundabout Catchbasin for Z-02 | 1 | 2024-08-15 | 2024-08-22 | 2024-11-16 | 2025-01-21
| JDH3-02-008RSD796 | Review and Approval Drawing for Roundabout Catchbasin for Z-02-2 | 1 | 2024-08-15 | 2024-08-22 | 2024-11-16 | 2025-01-21
| JDH3-02-008RSD806 | Review and Approval Drawing for Roundabout Catchbasin for Z-04 | 1 | 2024-08-15 | 2024-08-22 | 2024-11-16 | 2025-01-21
| JDH3-02-008RSD816 | Review and Approval Drawing for Roundabout Catchbasin for Z-05 | 1 | 2024-08-15 | 2024-08-22 | 2024-11-16 | 2025-01-21
| JDH3-02-008RSD826 | Review and Approval Drawing for Roundabout Catchbasin for Z-08 | 1 | 2024-08-15 | 2024-08-22 | 2024-11-16 | 2025-01-21
| JDH3-02-008RSD836 | Review and Approval Drawing for Roundabout Catchbasin for Z11 | 1 | 2024-08-13 | 2024-08-18 | 2025-04-09 | 2025-05-22
| JDH3-02-008RSD846 | Review and Approval Drawing for Roundabout Catchbasin for Z12 | 1 | 2024-08-13 | 2024-08-18 | 2025-04-09 | 2025-05-22
| JDH3-02-008RSD856 | Review and Approval Drawing for Roundabout Catchbasin for Z13 | 1 | 2024-08-13 | 2024-08-18 | 2025-04-09 | 2025-05-22
| JDH3-02-008RSD866 | Review and Approval Drawing for Storm network for R1 | 1 | 2024-08-19 | 2024-08-25 | 2025-03-19 | 2025-05-13
| JDH3-02-008RSD876 | Review and Approval Drawing for Storm network for R2 | 1 | 2024-08-19 | 2024-08-25 | 2025-03-19 | 2025-05-13
| JDH3-02-008RSD88 | Prepare and Submit Drawing for General layout - SD | 1 | 2024-07-30 | 2024-08-05 | 2024-08-05 | 2024-09-30
| JDH3-02-008RSD886 | Review and Approval Drawing for Box Culvert for R1 | 1 | 2024-08-12 | 2024-08-20 | 2025-06-14 | 2025-07-31
| JDH3-02-008RSD89 | Prepare and Submit Drawing for Ponds - SD-ST | 1 | 2024-07-30 | 2024-08-05 | 2024-09-18 | 2024-11-13
| JDH3-02-008RSD896 | Review and Approval Drawing for Box Culvert for R2 | 1 | 2024-08-12 | 2024-08-20 | 2025-06-14 | 2025-07-31
| JDH3-02-008RSD90 | Prepare and Submit Drawing for Swales - SD-ST | 1 | 2024-07-30 | 2024-08-05 | 2024-10-05 | 2024-11-28
| JDH3-02-008RSD906 | Prepare and Submit Drawing for CCTV System | 1 | 2024-07-30 | 2024-08-05 | 2025-05-02 | 2025-06-26
| JDH3-02-008RSD91 | Prepare and Submit Drawing for Box Culverts - SD-ST | 1 | 2024-07-30 | 2024-08-05 | 2024-09-16 | 2024-11-11
| JDH3-02-008RSD916 | Review and Approval Drawing for CCTV System | 1 | 2024-08-06 | 2024-08-19 | 2025-06-09 | 2025-07-31
| JDH3-02-008RSEPR1005 | Delivery for Concrete - PR-TSE-Z05 | 1 | 2025-02-26 | 2025-03-09 | 2025-03-04 | 2025-06-07
| JDH3-02-008RSEPR1006 | Delivery for Precast Concrete - PR-TSE-Z05 | 1 | 2025-03-10 | 2025-03-19
| JDH3-02-008RSEPR1007 | Delivery for Backfilling Materials - PR-TSE-Z05 | 1 | 2025-03-20 | 2025-03-31 | 2025-03-01 | 2025-06-04
| JDH3-02-008RSEPR1008 | Delivery for Isolation Materials - PR-TSE-Z05 | 1 | 2025-04-01 | 2025-04-10
| JDH3-02-008RSEPR1009 | Delivery for GRP pipes - PR-TSE-Z05 | 1 | 2025-05-22 | 2025-05-31
| JDH3-02-008RSEPR1010 | Delivery for HDPE pipes - PR-TSE-Z05 | 1 | 2025-06-01 | 2025-06-12 | 2024-12-29 | 2025-04-03
| JDH3-02-008RSEPR1011 | Delivery for Concrete Pipes - PR-TSE-Z05 | 1 | 2025-06-13 | 2025-06-22
| JDH3-02-008RSEPR1012 | Delivery for Valves (Aira & Gate) - PR-TSE-Z05 | 1 | 2025-06-23 | 2025-07-04 | 2025-03-01 | 2025-06-04
| JDH3-02-008RSEPR1013 | Delivery for Metal Works (Stairs - Covers) - PR-TSE-Z05 | 1 | 2025-07-05 | 2025-07-14
| JDH3-02-008RSEPR1041 | Delivery for Concrete - PR-TSE-Z06 | 1 | 2025-04-11 | 2025-04-22 | 2025-03-08 | 2025-06-11
| JDH3-02-008RSEPR1042 | Delivery for Precast Concrete - PR-TSE-Z06 | 1 | 2025-04-23 | 2025-05-04
| JDH3-02-008RSEPR1043 | Delivery for Backfilling Materials - PR-TSE-Z06 | 1 | 2025-05-05 | 2025-05-16
| JDH3-02-008RSEPR1044 | Delivery for Isolation Materials - PR-TSE-Z06 | 1 | 2025-05-17 | 2025-05-28
| JDH3-02-008RSEPR1045 | Delivery for GRP pipes - PR-TSE-Z06 | 1 | 2025-05-29 | 2025-06-09
| JDH3-02-008RSEPR1046 | Delivery for HDPE pipes - PR-TSE-Z06 | 1 | 2025-06-10 | 2025-06-21 | 2025-01-13 | 2025-04-18
| JDH3-02-008RSEPR1047 | Delivery for Concrete Pipes - PR-TSE-Z06 | 1 | 2025-06-22 | 2025-07-03
| JDH3-02-008RSEPR1048 | Delivery for Valves (Aira & Gate) - PR-TSE-Z06 | 1 | 2025-07-04 | 2025-07-15 | 2025-03-01 | 2025-06-04
| JDH3-02-008RSEPR1049 | Delivery for Metal Works (Stairs - Covers) - PR-TSE-Z06 | 1 | 2025-07-16 | 2025-07-27
| JDH3-02-008RSEPR1084 | Delivery for Concrete - PR-TSE-Z07 | 1 | 2024-09-01 | 2024-09-12
| JDH3-02-008RSEPR1085 | Delivery for Precast Concrete - PR-TSE-Z07 | 1 | 2024-09-13 | 2024-09-25
| JDH3-02-008RSEPR1086 | Delivery for Backfilling Materials - PR-TSE-Z07 | 1 | 2024-09-26 | 2024-10-07
| JDH3-02-008RSEPR1087 | Delivery for Isolation Materials - PR-TSE-Z07 | 1 | 2024-10-08 | 2024-10-19
| JDH3-02-008RSEPR1088 | Delivery for GRP pipes - PR-TSE-Z07 | 1 | 2024-10-20 | 2024-10-31
| JDH3-02-008RSEPR1089 | Delivery for HDPE pipes - PR-TSE-Z07 | 1 | 2024-11-01 | 2024-11-12 | 2024-12-12 | 2025-03-17
| JDH3-02-008RSEPR1090 | Delivery for Concrete Pipes - PR-TSE-Z07 | 1 | 2024-11-13 | 2024-11-24 | 2025-02-01 | 2025-05-07
| JDH3-02-008RSEPR1091 | Delivery for Valves (Aira & Gate) - PR-TSE-Z07 | 1 | 2024-11-25 | 2024-12-06 | 2025-02-20 | 2025-05-26
| JDH3-02-008RSEPR1092 | Delivery for Metal Works (Stairs - Covers) - PR-TSE-Z07 | 1 | 2024-12-07 | 2024-12-18
| JDH3-02-008RSEPR1147 | Delivery for Concrete - PR-TSE-Z07-1 | 1 | 2024-09-01 | 2024-09-12
| JDH3-02-008RSEPR1148 | Delivery for Precast Concrete - PR-TSE-Z07-1 | 1 | 2024-09-13 | 2024-09-25
| JDH3-02-008RSEPR1149 | Delivery for Backfilling Materials - PR-TSE-Z07-1 | 1 | 2024-09-26 | 2024-10-07 | 2025-02-05 | 2025-05-11
| JDH3-02-008RSEPR1150 | Delivery for Isolation Materials - PR-TSE-Z07-1 | 1 | 2024-10-08 | 2024-10-19
| JDH3-02-008RSEPR1151 | Delivery for GRP pipes - PR-TSE-Z07-1 | 1 | 2024-10-20 | 2024-11-03
| JDH3-02-008RSEPR1152 | Delivery for HDPE pipes - PR-TSE-Z07-1 | 1 | 2024-11-04 | 2024-11-15 | 2024-12-01 | 2025-03-06
| JDH3-02-008RSEPR1153 | Delivery for Concrete Pipes - PR-TSE-Z07-1 | 1 | 2024-11-16 | 2024-11-27
| JDH3-02-008RSEPR1154 | Delivery for Valves (Aira & Gate) - PR-TSE-Z07-1 | 1 | 2024-11-28 | 2024-12-09 | 2025-02-01 | 2025-05-07
| JDH3-02-008RSEPR1155 | Delivery for Metal Works (Stairs - Covers) - PR-TSE-Z07-1 | 1 | 2024-12-10 | 2024-12-21
| JDH3-02-008RSEPR1290 | Delivery for Concrete - PR-TSE-MR | 1 | 2024-09-01 | 2024-09-12 | 2025-02-19 | 2025-05-25
| JDH3-02-008RSEPR1291 | Delivery for Precast Concrete - PR-TSE-MR | 1 | 2024-09-13 | 2024-09-25 | 2024-11-19 | 2025-02-22
| JDH3-02-008RSEPR1292 | Delivery for Backfilling Materials - PR-TSE-MR | 1 | 2024-09-26 | 2024-10-07 | 2025-02-12 | 2025-05-18
| JDH3-02-008RSEPR1293 | Delivery for Isolation Materials - PR-TSE-MR | 1 | 2024-10-08 | 2024-10-19 | 2024-11-19 | 2025-02-22
| JDH3-02-008RSEPR1294 | Delivery for GRP pipes - PR-TSE-MR | 1 | 2024-10-20 | 2024-10-31 | 2024-11-12 | 2025-02-15
| JDH3-02-008RSEPR1295 | Delivery for HDPE pipes - PR-TSE-MR | 1 | 2024-11-01 | 2024-11-12 | 2024-12-10 | 2025-03-15
| JDH3-02-008RSEPR1296 | Delivery for Concrete Pipes - PR-TSE-MR | 1 | 2024-11-13 | 2024-11-24 | 2024-11-19 | 2025-02-22
| JDH3-02-008RSEPR1297 | Delivery for Valves (Aira & Gate) - PR-TSE-MR | 1 | 2024-11-25 | 2024-12-06 | 2025-02-10 | 2025-05-16
| JDH3-02-008RSEPR1298 | Delivery for Metal Works (Stairs - Covers) - PR-TSE-MR | 1 | 2024-12-07 | 2024-12-18 | 2024-11-19 | 2025-01-05
| JDH3-02-008RSEPR1308 | Material Fabrication for Concrete - PR-TSE | 1 | 2024-08-26 | 2024-08-31 | 2024-11-14 | 2024-12-31
| JDH3-02-008RSEPR1318 | Material Fabrication for Precast Concrete - PR-TSE | 1 | 2024-08-26 | 2024-08-31 | 2024-11-12 | 2024-12-29
| JDH3-02-008RSEPR1328 | Material Fabrication for Backfilling Materials - PR-TSE | 1 | 2024-08-26 | 2024-08-30 | 2024-12-26 | 2025-02-03
| JDH3-02-008RSEPR1338 | Material Fabrication for Isolation Materials - PR-TSE | 1 | 2024-08-26 | 2024-09-02 | 2024-11-20 | 2025-01-22
| JDH3-02-008RSEPR1348 | Material Fabrication for GRP pipes - PR-TSE | 1 | 2024-08-26 | 2024-08-31 | 2025-01-01 | 2025-02-17
| JDH3-02-008RSEPR1358 | Material Fabrication for HDPE pipes - PR-TSE | 1 | 2024-08-26 | 2024-08-30 | 2024-11-20 | 2024-12-29
| JDH3-02-008RSEPR1368 | Material Fabrication for Concrete Pipes - PR-TSE | 1 | 2024-08-26 | 2024-08-31 | 2025-01-25 | 2025-03-13
| JDH3-02-008RSEPR1378 | Material Fabrication for Valves (Aira & Gate) - PR-TSE | 1 | 2024-08-26 | 2024-09-02 | 2025-05-11 | 2025-07-13
| JDH3-02-008RSEPR1388 | Material Fabrication for Metal Works (Stairs - Covers) - PR-TSE | 1 | 2024-08-26 | 2024-09-06 | 2025-03-01 | 2025-07-31
| JDH3-02-008RSEPR1398 | Delivery for Concrete - PR-TSE-Z13 | 1 | 2025-08-03 | 2025-08-14
| JDH3-02-008RSEPR1408 | Delivery for Precast Concrete - PR-TSE-Z13 | 1 | 2025-08-15 | 2025-08-26
| JDH3-02-008RSEPR1418 | Delivery for Backfilling Materials - PR-TSE-Z13 | 1 | 2025-08-27 | 2025-09-12 | 2025-03-01 | 2025-07-14
| JDH3-02-008RSEPR1428 | Delivery for Isolation Materials - PR-TSE-Z13 | 1 | 2025-09-13 | 2025-09-24
| JDH3-02-008RSEPR1438 | Delivery for GRP pipes - PR-TSE-Z13 | 1 | 2025-09-25 | 2025-10-06
| JDH3-02-008RSEPR1468 | Delivery for Valves (Aira & Gate) - PR-TSE-Z13 | 1 | 2025-09-25 | 2025-10-07 | 2025-02-01 | 2025-05-15
| JDH3-02-008RSEPR1498 | Material Fabrication for Butterfly Valves (Importing) - PR-TSE | 1 | 2024-08-28 | 2024-10-27
| JDH3-02-008RSEPR1508 | Delivery for Butterfly Valves (Importing) - PR-TSE-MR | 1 | 2024-12-19 | 2025-02-16
| JDH3-02-008RSEPR576 | Prepare Material Submittal for Concrete - PR-TSE | 1 | 2024-07-30 | 2024-08-05 | 2024-09-21 | 2024-11-16
| JDH3-02-008RSEPR577 | Prepare Material Submittal for Precast Concrete - PR-TSE | 1 | 2024-07-30 | 2024-08-05 | 2024-11-19 | 2025-01-13
| JDH3-02-008RSEPR578 | Prepare Material Submittal for Backfilling Materials - PR-TSE | 1 | 2024-07-30 | 2024-08-05 | 2024-11-07 | 2025-01-01
| JDH3-02-008RSEPR579 | Prepare Material Submittal for Isolation Materials - PR-TSE | 1 | 2024-07-30 | 2024-08-05 | 2024-11-25 | 2025-01-19
| JDH3-02-008RSEPR580 | Prepare Material Submittal for GRP pipes - PR-TSE | 1 | 2024-07-30 | 2024-08-05 | 2024-09-18 | 2024-11-13
| JDH3-02-008RSEPR581 | Prepare Material Submittal for HDPE pipes - PR-TSE | 1 | 2024-07-30 | 2024-08-05 | 2024-09-18 | 2024-11-13
| JDH3-02-008RSEPR582 | Prepare Material Submittal for Concrete Pipes - PR-TSE | 1 | 2024-07-30 | 2024-08-05 | 2024-09-21 | 2024-11-16
| JDH3-02-008RSEPR583 | Prepare Material Submittal for Valves - PR-TSE | 1 | 2024-07-30 | 2024-08-05 | 2024-09-28 | 2024-11-21
| JDH3-02-008RSEPR584 | Prepare Material Submittal for Metal Works (Stairs - Covers) - PR-TSE | 1 | 2024-07-30 | 2024-08-05 | 2024-10-01 | 2024-11-25
| JDH3-02-008RSEPR638 | Review and Approval of Material Submittal for Concrete - PR-TSE | 1 | 2024-08-06 | 2024-08-19 | 2024-11-14 | 2025-03-05
| JDH3-02-008RSEPR639 | Review and Approval of Material Submittal for Precast Concrete - PR-TSE | 1 | 2024-08-06 | 2024-08-19 | 2024-11-24 | 2025-03-13
| JDH3-02-008RSEPR640 | Review and Approval of Material Submittal for Backfilling Materials - PR-TSE | 1 | 2024-08-06 | 2024-08-19 | 2024-11-11 | 2025-03-02
| JDH3-02-008RSEPR641 | Review and Approval of Material Submittal for Isolation Materials - PR-TSE | 1 | 2024-08-06 | 2024-08-19 | 2024-11-25 | 2025-03-16
| JDH3-02-008RSEPR642 | Review and Approval of Material Submittal for GRP pipes - PR-TSE | 1 | 2024-08-06 | 2024-08-19 | 2024-10-27 | 2025-02-13
| JDH3-02-008RSEPR643 | Review and Approval of Material Submittal for HDPE pipes - PR-TSE | 1 | 2024-08-06 | 2024-08-19 | 2024-09-30 | 2025-01-19
| JDH3-02-008RSEPR644 | Review and Approval of Material Submittal for Concrete Pipes - PR-TSE | 1 | 2024-08-06 | 2024-08-19 | 2024-11-14 | 2025-03-05
| JDH3-02-008RSEPR645 | Review and Approval of Material Submittal for Valves - PR-TSE | 1 | 2024-08-06 | 2024-08-19 | 2024-10-03 | 2025-01-22
| JDH3-02-008RSEPR646 | Review and Approval of Material Submittal for Metal Works (Stairs - Covers) - PR-TSE | 1 | 2024-08-06 | 2024-08-19 | 2024-10-08 | 2025-01-27
| JDH3-02-008RSEPR700 | Material Purchase Order for Concrete - PR-TSE | 1 | 2024-08-20 | 2024-08-25 | 2024-11-14 | 2024-12-31
| JDH3-02-008RSEPR701 | Material Purchase Order for Precast Concrete - PR-TSE | 1 | 2024-08-20 | 2024-08-25 | 2024-11-05 | 2024-12-22
| JDH3-02-008RSEPR702 | Material Purchase Order for Backfilling Materials - PR-TSE | 1 | 2024-08-20 | 2024-08-25 | 2024-12-26 | 2025-02-11
| JDH3-02-008RSEPR703 | Material Purchase Order for Isolation Materials - PR-TSE | 1 | 2024-08-20 | 2024-08-25 | 2024-11-20 | 2025-01-06
| JDH3-02-008RSEPR704 | Material Purchase Order for GRP pipes - PR-TSE | 1 | 2024-08-20 | 2024-08-25 | 2024-12-24 | 2025-02-09
| JDH3-02-008RSEPR705 | Material Purchase Order for HDPE pipes - PR-TSE | 1 | 2024-08-20 | 2024-08-25 | 2024-11-20 | 2025-01-06
| JDH3-02-008RSEPR706 | Material Purchase Order for Concrete Pipes - PR-TSE | 1 | 2024-08-20 | 2024-08-25 | 2025-01-18 | 2025-03-06
| JDH3-02-008RSEPR707 | Material Purchase Order for Valves (Aira & Gate) - PR-TSE | 1 | 2024-08-20 | 2024-08-25 | 2025-05-02 | 2025-06-18
| JDH3-02-008RSEPR708 | Material Purchase Order for Metal Works (Stairs - Covers) - PR-TSE | 1 | 2024-08-20 | 2024-08-25 | 2025-03-01 | 2025-04-17
| JDH3-02-008RSEPR811 | Delivery for Concrete - PR-TSE-Z02 | 1 | 2025-02-20 | 2025-03-02 | 2025-08-02 | 2025-08-14
| JDH3-02-008RSEPR812 | Delivery for Precast Concrete - PR-TSE-Z02 | 1 | 2025-03-03 | 2025-03-14 | 2025-08-05 | 2025-08-12
| JDH3-02-008RSEPR813 | Delivery for Backfilling Materials - PR-TSE-Z02 | 1 | 2025-03-15 | 2025-03-22 | 2025-03-04 | 2025-05-06
| JDH3-02-008RSEPR814 | Delivery for Isolation Materials - PR-TSE-Z02 | 1 | 2025-03-23 | 2025-04-03 | 2025-08-12 | 2025-08-27
| JDH3-02-008RSEPR815 | Delivery for GRP pipes - PR-TSE-Z02 | 1 | 2025-04-04 | 2025-04-15 | 2025-08-13 | 2025-08-27
| JDH3-02-008RSEPR816 | Delivery for HDPE pipes - PR-TSE-Z02 | 1 | 2025-04-16 | 2025-04-27 | 2025-01-01 | 2025-04-06
| JDH3-02-008RSEPR817 | Delivery for Concrete Pipes - PR-TSE-Z02 | 1 | 2025-04-28 | 2025-05-09 | 2025-03-13 | 2025-06-16
| JDH3-02-008RSEPR818 | Delivery for Valves (Aira & Gate) - PR-TSE-Z02 | 1 | 2025-05-10 | 2025-05-21 | 2025-02-10 | 2025-05-16
| JDH3-02-008RSEPR819 | Delivery for Metal Works (Stairs - Covers) - PR-TSE-Z02 | 1 | 2025-05-22 | 2025-06-02
| JDH3-02-008RSEPR874 | Delivery for Concrete - PR-TSE-Z02-1 | 1 | 2024-09-01 | 2024-09-10 | 2025-08-05 | 2025-08-14
| JDH3-02-008RSEPR875 | Delivery for Precast Concrete - PR-TSE-Z02-1 | 1 | 2024-09-11 | 2024-09-20 | 2025-08-05 | 2025-08-12
| JDH3-02-008RSEPR876 | Delivery for Backfilling Materials - PR-TSE-Z02-1 | 1 | 2024-09-21 | 2024-10-03 | 2025-03-11 | 2025-06-14
| JDH3-02-008RSEPR877 | Delivery for Isolation Materials - PR-TSE-Z02-1 | 1 | 2024-10-04 | 2024-10-13 | 2025-08-12 | 2025-08-27
| JDH3-02-008RSEPR878 | Delivery for GRP pipes - PR-TSE-Z02-1 | 1 | 2024-10-14 | 2024-10-23 | 2025-08-13 | 2025-08-27
| JDH3-02-008RSEPR879 | Delivery for HDPE pipes - PR-TSE-Z02-1 | 1 | 2024-10-24 | 2024-11-04 | 2025-03-01 | 2025-06-04
| JDH3-02-008RSEPR880 | Delivery for Concrete Pipes - PR-TSE-Z02-1 | 1 | 2024-11-05 | 2024-11-14 | 2025-08-23 | 2025-09-03
| JDH3-02-008RSEPR881 | Delivery for Valves (Aira & Gate) - PR-TSE-Z02-1 | 1 | 2024-11-15 | 2024-11-26 | 2025-03-02 | 2025-06-05
| JDH3-02-008RSEPR882 | Delivery for Metal Works (Stairs - Covers) - PR-TSE-Z02-1 | 1 | 2024-11-27 | 2024-12-06
| JDH3-02-008RSEPR937 | Delivery for Concrete - PR-TSE-Z02-2 | 1 | 2024-09-01 | 2024-09-12 | 2025-01-02 | 2025-04-07
| JDH3-02-008RSEPR938 | Delivery for Precast Concrete - PR-TSE-Z02-2 | 1 | 2024-09-13 | 2024-09-25 | 2025-01-02 | 2025-04-07
| JDH3-02-008RSEPR939 | Delivery for Backfilling Materials - PR-TSE-Z02-2 | 1 | 2024-09-26 | 2024-10-07 | 2025-01-02 | 2025-04-07
| JDH3-02-008RSEPR940 | Delivery for Isolation Materials - PR-TSE-Z02-2 | 1 | 2024-10-08 | 2024-10-19 | 2025-01-02 | 2025-04-07
| JDH3-02-008RSEPR941 | Delivery for GRP pipes - PR-TSE-Z02-2 | 1 | 2024-10-20 | 2024-10-31 | 2025-01-02 | 2025-04-07
| JDH3-02-008RSEPR942 | Delivery for HDPE pipes - PR-TSE-Z02-2 | 1 | 2024-11-01 | 2024-11-12 | 2025-01-02 | 2025-04-07
| JDH3-02-008RSEPR943 | Delivery for Concrete Pipes - PR-TSE-Z02-2 | 1 | 2024-11-13 | 2024-11-24 | 2025-01-02 | 2025-04-07
| JDH3-02-008RSEPR944 | Delivery for Valves (Aira & Gate) - PR-TSE-Z02-2 | 1 | 2024-11-25 | 2024-12-06 | 2025-01-02 | 2025-04-07
| JDH3-02-008RSEPR9440 | Delivery for Butterfly Valves (Importing) - PR-TSE-Z02-2 | 1 | 2024-12-07 | 2025-02-04
| JDH3-02-008RSEPR945 | Delivery for Metal Works (Stairs - Covers) - PR-TSE-Z02-2 | 1 | 2025-02-05 | 2025-02-16 | 2025-01-02 | 2025-04-07
| JDH3-02-008RSEPR9450 | Delivery for Butterfly Valves (Importing) - PR-TSE-Z07 | 1 | 2024-12-19 | 2025-02-16
| JDH3-02-008RSEPR973 | Delivery for Concrete - PR-TSE-Z03 | 1 | 2025-07-28 | 2025-08-08 | 2025-08-18 | 2025-09-03
| JDH3-02-008RSEPR974 | Delivery for Precast Concrete - PR-TSE-Z03 | 1 | 2025-08-09 | 2025-08-20 | 2025-08-06 | 2025-09-01
| JDH3-02-008RSEPR975 | Delivery for Backfilling Materials - PR-TSE-Z03 | 1 | 2025-08-21 | 2025-09-01 | 2025-02-01 | 2025-05-07
| JDH3-02-008RSEPR976 | Delivery for Isolation Materials - PR-TSE-Z03 | 1 | 2025-09-02 | 2025-09-13 | 2025-08-12 | 2025-08-27
| JDH3-02-008RSEPR977 | Delivery for GRP pipes - PR-TSE-Z03 | 1 | 2025-09-14 | 2025-09-25 | 2025-08-13 | 2025-08-27
| JDH3-02-008RSEPR978 | Delivery for HDPE pipes - PR-TSE-Z03 | 1 | 2025-09-26 | 2025-10-07 | 2024-12-04 | 2025-03-09
| JDH3-02-008RSLPR1164 | Delivery for Unit Stations - PR-SL-Z07-1 | 1 | 2024-08-30 | 2024-09-10 | 2025-07-15 | 2025-08-11
| JDH3-02-008RSLPR1165 | Delivery for Cables&Conductors - PR-SL-Z07-1 | 1 | 2024-09-11 | 2024-09-22 | 2025-05-01 | 2025-07-31
| JDH3-02-008RSLPR1166 | Delivery for Lighting Columns - PR-SL-Z07-1 | 1 | 2024-09-24 | 2024-10-05 | 2025-05-01 | 2025-07-31
| JDH3-02-008RSLPR1167 | Delivery for Earthing Materials - PR-SL-Z07-1 | 1 | 2024-10-06 | 2024-10-17 | 2025-08-05 | 2025-08-27
| JDH3-02-008RSLPR1168 | Delivery for Lighting Panels - PR-SL-Z07-1 | 1 | 2024-10-18 | 2024-10-29 | 2025-08-05 | 2025-08-27
| JDH3-02-008RSLPR1169 | Delivery for Electirical Accessories - PR-SL-Z07-1 | 1 | 2024-10-30 | 2024-11-10 | 2025-08-05 | 2025-08-27
| JDH3-02-008RSLPR1171 | Delivery for Steel Covers - PR-SL-Z07-1 | 1 | 2024-11-11 | 2024-11-22
| JDH3-02-008RSLPR1172 | Delivery for Ducts - PR-SL-Z07-1 | 1 | 2024-11-23 | 2024-12-04 | 2025-04-16 | 2025-05-13
| JDH3-02-008RSLPR1307 | Delivery for Unit Stations - PR-SL-MR | 1 | 2025-04-28 | 2025-05-09 | 2025-07-15 | 2025-08-11
| JDH3-02-008RSLPR1308 | Delivery for Cables&Conductors - PR-SL-MR | 1 | 2025-05-10 | 2025-05-21 | 2025-05-01 | 2025-07-31
| JDH3-02-008RSLPR1309 | Delivery for Lighting Columns - PR-SL-MR | 1 | 2025-05-22 | 2025-06-02 | 2025-08-05 | 2025-08-27
| JDH3-02-008RSLPR1310 | Delivery for Earthing Materials - PR-SL-MR | 1 | 2025-06-03 | 2025-06-14 | 2025-08-05 | 2025-08-27
| JDH3-02-008RSLPR1311 | Delivery for Lighting Panels - PR-SL-MR | 1 | 2025-06-15 | 2025-06-26 | 2025-08-05 | 2025-08-27
| JDH3-02-008RSLPR1312 | Delivery for Electirical Accessories - PR-SL-MR | 1 | 2025-06-27 | 2025-07-08 | 2025-08-05 | 2025-08-27
| JDH3-02-008RSLPR1314 | Delivery for Steel Covers - PR-SL-MR | 1 | 2025-07-09 | 2025-07-20
| JDH3-02-008RSLPR1315 | Delivery for Ducts - PR-SL-MR | 1 | 2025-07-21 | 2025-08-01 | 2025-08-17 | 2025-09-02
| JDH3-02-008RSLPR1415 | Material Fabrication for Cables&Conductors - PR-SL | 1 | 2024-08-26 | 2024-08-31 | 2025-04-23 | 2025-06-09
| JDH3-02-008RSLPR1425 | Material Fabrication for Earthing Materials - PR-SL | 1 | 2024-08-26 | 2024-08-31 | 2025-04-23 | 2025-06-09
| JDH3-02-008RSLPR1435 | Material Fabrication for Electirical Accessories - PR-SL | 1 | 2024-08-19 | 2024-08-24 | 2025-04-23 | 2025-06-09
| JDH3-02-008RSLPR593 | Prepare Material Submittal for Unit Stations - PR-SL | 1 | 2024-07-30 | 2024-08-05 | 2024-12-01 | 2025-01-25
| JDH3-02-008RSLPR594 | Prepare Material Submittal for Cables&Conductors - PR-SL | 1 | 2024-07-30 | 2024-08-05 | 2024-09-28 | 2024-11-21
| JDH3-02-008RSLPR595 | Prepare Material Submittal for Lighting Columns - PR-SL | 1 | 2024-07-30 | 2024-08-05 | 2025-02-01 | 2025-03-27
| JDH3-02-008RSLPR596 | Prepare Material Submittal for Earthing Materials - PR-SL | 1 | 2024-07-30 | 2024-08-05 | 2025-02-03 | 2025-03-30
| JDH3-02-008RSLPR597 | Prepare Material Submittal for Lighting Panels - PR-SL | 1 | 2024-07-30 | 2024-08-05 | 2025-05-20 | 2025-07-14
| JDH3-02-008RSLPR598 | Prepare Material Submittal for Electrical Accessories - PR-SL | 1 | 2024-07-30 | 2024-08-05 | 2025-04-19 | 2025-06-12
| JDH3-02-008RSLPR600 | Prepare Material Submittal for Steel Covers - PR-SL | 1 | 2024-07-30 | 2024-08-05 | 2025-02-01 | 2025-03-27
| JDH3-02-008RSLPR601 | Prepare Material Submittal for Ducts - PR-SL | 1 | 2024-07-30 | 2024-08-05 | 2025-02-10 | 2025-04-06
| JDH3-02-008RSLPR655 | Review and Approval of Material Submittal for Unit Stations - PR-SL | 1 | 2024-08-06 | 2024-08-19 | 2025-02-20 | 2025-06-11
| JDH3-02-008RSLPR656 | Review and Approval of Material Submittal for Cables&Conductors - PR-SL | 1 | 2024-08-06 | 2024-08-19 | 2025-01-16 | 2025-05-07
| JDH3-02-008RSLPR657 | Review and Approval of Material Submittal for Lighting Columns - PR-SL | 1 | 2024-08-06 | 2024-08-19 | 2025-01-16 | 2025-05-07
| JDH3-02-008RSLPR658 | Review and Approval of Material Submittal for Earthing Materials - PR-SL | 1 | 2024-08-06 | 2024-08-19 | 2025-02-10 | 2025-06-01
| JDH3-02-008RSLPR659 | Review and Approval of Material Submittal for Lighting Panels - PR-SL | 1 | 2024-08-06 | 2024-08-19 | 2025-05-26 | 2025-07-31
| JDH3-02-008RSLPR660 | Review and Approval of Material Submittal for Electirical Accessories - PR-SL | 1 | 2024-07-30 | 2024-08-12 | 2025-04-21 | 2025-07-31
| JDH3-02-008RSLPR662 | Review and Approval of Material Submittal for Steel Covers - PR-SL | 1 | 2024-08-06 | 2024-08-19 | 2025-02-14 | 2025-06-05
| JDH3-02-008RSLPR663 | Review and Approval of Material Submittal for Ducts - PR-SL | 1 | 2024-08-06 | 2024-08-19 | 2025-02-14 | 2025-06-05
| JDH3-02-008RSLPR717 | Material Purchase Order for Unit Stations - PR-SL | 1 | 2024-08-20 | 2024-08-25 | 2025-07-02 | 2025-07-31
| JDH3-02-008RSLPR718 | Material Purchase Order for Cables&Conductors - PR-SL | 1 | 2024-08-20 | 2024-08-25 | 2024-12-01 | 2025-01-17
| JDH3-02-008RSLPR719 | Material Purchase Order for Lighting Columns - PR-SL | 1 | 2024-08-20 | 2024-08-25 | 2025-04-27 | 2025-06-13
| JDH3-02-008RSLPR720 | Material Purchase Order for Earthing Materials - PR-SL | 1 | 2024-08-20 | 2024-08-25 | 2025-07-02 | 2025-07-31
| JDH3-02-008RSLPR721 | Material Purchase Order for Lighting Panels - PR-SL | 1 | 2024-08-20 | 2024-08-25 | 2025-07-02 | 2025-07-31
| JDH3-02-008RSLPR722 | Material Purchase Order for Electirical Accessories - PR-SL | 1 | 2024-08-13 | 2024-08-18 | 2025-07-02 | 2025-07-31
| JDH3-02-008RSLPR724 | Material Purchase Order for Steel Covers - PR-SL | 1 | 2024-08-20 | 2024-08-25 | 2025-07-02 | 2025-07-31
| JDH3-02-008RSLPR725 | Material Purchase Order for Ducts - PR-SL | 1 | 2024-08-20 | 2024-08-25 | 2025-05-01 | 2025-06-17
| JDH3-02-008RSLPR738 | Material Fabrication for Unit Stations - PR-SL | 1 | 2024-08-26 | 2024-08-29 | 2025-04-23 | 2025-05-24
| JDH3-02-008RSLPR739 | Material Fabrication for Lighting Columns - PR-SL | 1 | 2024-08-26 | 2024-08-29 | 2025-04-23 | 2025-05-24
| JDH3-02-008RSLPR740 | Material Fabrication for Lighting Panels - PR-SL | 1 | 2024-08-26 | 2024-08-29 | 2025-04-23 | 2025-05-24
| JDH3-02-008RSLPR742 | Material Fabrication for Steel Covers - PR-SL | 1 | 2024-08-26 | 2024-08-29 | 2025-04-23 | 2025-05-24
| JDH3-02-008RSLPR743 | Material Fabrication for Ducts - PR-SL | 1 | 2024-08-26 | 2024-08-29 | 2025-04-23 | 2025-05-24
| JDH3-02-008RSLPR891 | Delivery for Unit Stations - PR-SL-Z02-1 | 1 | 2024-08-30 | 2024-09-10 | 2025-07-15 | 2025-08-11
| JDH3-02-008RSLPR892 | Delivery for Cables&Conductors - PR-SL-Z02-1 | 1 | 2024-09-11 | 2024-09-22 | 2025-05-01 | 2025-07-31
| JDH3-02-008RSLPR893 | Delivery for Lighting Columns - PR-SL-Z02-1 | 1 | 2024-09-24 | 2024-10-05 | 2025-08-05 | 2025-08-27
| JDH3-02-008RSLPR894 | Delivery for Earthing Materials - PR-SL-Z02-1 | 1 | 2024-10-06 | 2024-10-17 | 2025-08-05 | 2025-08-27
| JDH3-02-008RSLPR895 | Delivery for Lighting Panels - PR-SL-Z02-1 | 1 | 2024-10-18 | 2024-10-29 | 2025-08-05 | 2025-08-27
| JDH3-02-008RSLPR896 | Delivery for Electirical Accessories - PR-SL-Z02-1 | 1 | 2024-10-30 | 2024-11-10 | 2025-08-05 | 2025-08-27
| JDH3-02-008RSLPR898 | Delivery for Steel Covers - PR-SL-Z02-1 | 1 | 2024-11-11 | 2024-11-22
| JDH3-02-008RSLPR899 | Delivery for Ducts - PR-SL-Z02-1 | 1 | 2024-11-23 | 2024-12-04 | 2025-08-12 | 2025-08-27
| JDH3-02-008RSLPR954 | Delivery for Unit Stations - PR-SL-Z02-2 | 1 | 2024-09-26 | 2024-10-07 | 2025-05-01 | 2025-07-31
| JDH3-02-008RSLPR955 | Delivery for Cables&Conductors - PR-SL-Z02-2 | 1 | 2024-10-08 | 2024-10-19 | 2025-05-01 | 2025-07-31
| JDH3-02-008RSLPR956 | Delivery for Lighting Columns - PR-SL-Z02-2 | 1 | 2024-10-20 | 2024-10-31 | 2025-05-01 | 2025-07-31
| JDH3-02-008RSLPR957 | Delivery for Earthing Materials - PR-SL-Z02-2 | 1 | 2025-02-14 | 2025-02-25 | 2025-05-01 | 2025-07-31
| JDH3-02-008RSLPR958 | Delivery for Lighting Panels - PR-SL-Z02-2 | 1 | 2025-02-26 | 2025-03-09 | 2025-05-01 | 2025-07-31
| JDH3-02-008RSLPR959 | Delivery for Electirical Accessories - PR-SL-Z02-2 | 1 | 2025-03-10 | 2025-03-21 | 2025-05-01 | 2025-07-31
| JDH3-02-008RSLPR961 | Delivery for Steel Covers - PR-SL-Z02-2 | 1 | 2025-03-22 | 2025-04-02 | 2025-05-01 | 2025-07-31
| JDH3-02-008RSLPR962 | Delivery for Ducts - PR-SL-Z02-2 | 1 | 2025-04-03 | 2025-04-14 | 2025-05-01 | 2025-07-31
| JDH3-02-008RSSMI10 | Start of Sewage Network - SS - MI-SS | 1 | 2024-07-30 |  | 2024-11-26
| JDH3-02-008RSSMI11 | Finish for Sewage Network - SS - MI-SS | 1 |  | 2025-03-25
| JDH3-02-008RSSPR1120 | Delivery for Concrete - PR-SS-Z07-1 | 1 | 2024-08-28 | 2024-09-08 | 2025-01-01 | 2025-04-06
| JDH3-02-008RSSPR1121 | Delivery for Precast Concrete - PR-SS-Z07-1 | 1 | 2024-10-08 | 2024-10-19 | 2024-11-30 | 2025-03-05
| JDH3-02-008RSSPR1122 | Delivery for Backfilling Materials - PR-SS-Z07-1 | 1 | 2024-10-20 | 2024-10-31 | 2024-12-12 | 2025-03-17
| JDH3-02-008RSSPR1123 | Delivery for Isolation Materials - PR-SS-Z07-1 | 1 | 2024-11-01 | 2024-11-12 | 2024-12-05 | 2025-03-10
| JDH3-02-008RSSPR1124 | Delivery for GRP pipes - PR-SS-Z07-1 | 1 | 2024-11-13 | 2024-11-24 | 2024-11-09 | 2025-02-12
| JDH3-02-008RSSPR1125 | Delivery for Metal Works (Stairs - Covers) - PR-SS-Z07-1 | 1 | 2024-11-25 | 2024-12-06
| JDH3-02-008RSSPR1263 | Delivery for Concrete - PR-SS-MR | 1 | 2024-12-17 | 2024-12-28
| JDH3-02-008RSSPR1264 | Delivery for Precast Concrete - PR-SS-MR | 1 | 2024-10-08 | 2024-10-19 | 2024-12-14 | 2025-03-19
| JDH3-02-008RSSPR1265 | Delivery for Backfilling Materials - PR-SS-MR | 1 | 2024-12-29 | 2025-01-09
| JDH3-02-008RSSPR1266 | Delivery for Isolation Materials - PR-SS-MR | 1 | 2025-01-10 | 2025-01-21
| JDH3-02-008RSSPR1267 | Delivery for GRP pipes - PR-SS-MR | 1 | 2025-01-22 | 2025-02-02
| JDH3-02-008RSSPR1268 | Delivery for Metal Works (Stairs - Covers) - PR-SS-MR | 1 | 2025-02-03 | 2025-02-14
| JDH3-02-008RSSPR1278 | Material Fabrication for Concrete - PR-SS | 1 | 2024-08-26 | 2024-08-27 | 2024-11-13 | 2024-11-28
| JDH3-02-008RSSPR1288 | Material Fabrication for Precast Concrete - PR-SS | 1 | 2024-10-01 | 2024-10-07 | 2024-11-05 | 2024-12-30
| JDH3-02-008RSSPR1298 | Material Fabrication for Backfilling Materials - PR-SS | 1 | 2024-08-22 | 2024-08-26 | 2024-12-26 | 2025-02-03
| JDH3-02-008RSSPR1308 | Material Fabrication for Isolation Materials - PR-SS | 1 | 2024-08-22 | 2024-08-28 | 2024-11-20 | 2025-01-14
| JDH3-02-008RSSPR1318 | Material Fabrication for GRP pipes - PR-SS | 1 | 2024-08-22 | 2024-08-27 | 2024-11-02 | 2024-12-19
| JDH3-02-008RSSPR1328 | Material Fabrication for Metal Works (Stairs - Covers) - PR-SS | 1 | 2024-10-01 | 2024-10-06 | 2025-03-01 | 2025-04-17
| JDH3-02-008RSSPR549 | Prepare Material Submittal for Concrete - PR-SS | 1 | 2024-07-30 | 2024-08-06 | 2024-09-21 | 2024-11-25
| JDH3-02-008RSSPR550 | Prepare Material Submittal for Precast Concrete - PR-SS | 1 | 2024-09-05 | 2024-09-12 | 2024-09-23 | 2024-11-27
| JDH3-02-008RSSPR551 | Prepare Material Submittal for Backfilling Materials - PR-SS | 1 | 2024-07-30 | 2024-08-06 | 2024-11-07 | 2025-01-11
| JDH3-02-008RSSPR552 | Prepare Material Submittal for Isolation Materials - PR-SS | 1 | 2024-07-30 | 2024-08-06 | 2024-11-18 | 2025-01-21
| JDH3-02-008RSSPR553 | Prepare Material Submittal for GRP pipes - PR-SS | 1 | 2024-07-30 | 2024-08-06 | 2024-09-18 | 2024-11-23
| JDH3-02-008RSSPR554 | Prepare Material Submittal for Metal Works (Stairs - Covers) - PR-SS | 1 | 2024-09-05 | 2024-09-12 | 2024-10-01 | 2024-12-04
| JDH3-02-008RSSPR611 | Review and Approval of Material Submittal for Concrete - PR-SS | 1 | 2024-08-07 | 2024-08-18 | 2024-11-14 | 2025-02-11
| JDH3-02-008RSSPR612 | Review and Approval of Material Submittal for Precast Concrete - PR-SS | 1 | 2024-09-15 | 2024-09-22 | 2024-09-29 | 2024-12-03
| JDH3-02-008RSSPR613 | Review and Approval of Material Submittal for Backfilling Materials - PR-SS | 1 | 2024-08-07 | 2024-08-14 | 2024-11-11 | 2025-01-15
| JDH3-02-008RSSPR614 | Review and Approval of Material Submittal for Isolation Materials - PR-SS | 1 | 2024-08-07 | 2024-08-14 | 2024-11-27 | 2025-02-02
| JDH3-02-008RSSPR615 | Review and Approval of Material Submittal for GRP pipes - PR-SS | 1 | 2024-08-07 | 2024-08-14 | 2024-09-22 | 2024-11-27
| JDH3-02-008RSSPR616 | Review and Approval of Material Submittal for Metal Works (Stairs - Covers) - PR-SS | 1 | 2024-09-15 | 2024-09-22 | 2024-10-08 | 2024-12-12
| JDH3-02-008RSSPR673 | Material Purchase Order for Concrete - PR-SS | 1 | 2024-08-19 | 2024-08-25 | 2024-11-13 | 2025-01-07
| JDH3-02-008RSSPR674 | Material Purchase Order for Precast Concrete - PR-SS | 1 | 2024-09-24 | 2024-09-30 | 2024-11-05 | 2024-12-30
| JDH3-02-008RSSPR675 | Material Purchase Order for Backfilling Materials - PR-SS | 1 | 2024-08-15 | 2024-08-21 | 2024-12-26 | 2025-02-19
| JDH3-02-008RSSPR676 | Material Purchase Order for Isolation Materials - PR-SS | 1 | 2024-08-15 | 2024-08-21 | 2024-11-20 | 2025-01-14
| JDH3-02-008RSSPR677 | Material Purchase Order for GRP pipes - PR-SS | 1 | 2024-08-15 | 2024-08-21 | 2024-11-02 | 2024-12-27
| JDH3-02-008RSSPR678 | Material Purchase Order for Metal Works (Stairs - Covers) - PR-SS | 1 | 2024-09-24 | 2024-09-30 | 2025-03-01 | 2025-04-25
| JDH3-02-008RSSPR847 | Delivery for Concrete - PR-SS-Z02-1 | 1 | 2024-08-28 | 2024-09-08 | 2025-06-04 | 2025-07-31
| JDH3-02-008RSSPR848 | Delivery for Precast Concrete - PR-SS-Z02-1 | 1 | 2024-10-08 | 2024-10-19 | 2024-12-04 | 2025-03-09
| JDH3-02-008RSSPR849 | Delivery for Backfilling Materials - PR-SS-Z02-1 | 1 | 2024-10-20 | 2024-10-31 | 2025-04-16 | 2025-07-20
| JDH3-02-008RSSPR850 | Delivery for Isolation Materials - PR-SS-Z02-1 | 1 | 2024-11-01 | 2024-11-10
| JDH3-02-008RSSPR851 | Delivery for GRP pipes - PR-SS-Z02-1 | 1 | 2024-11-11 | 2024-11-22 | 2025-03-06 | 2025-06-09
| JDH3-02-008RSSPR852 | Delivery for Metal Works (Stairs - Covers) - PR-SS-Z02-1 | 1 | 2024-11-23 | 2024-12-04 | 2025-04-24 | 2025-07-28
| JDH3-02-008RSSPR910 | Delivery for Concrete - PR-SS-Z02-2 | 1 | 2024-08-28 | 2024-09-08 | 2025-03-03 | 2025-06-06
| JDH3-02-008RSSPR911 | Delivery for Precast Concrete - PR-SS-Z02-2 | 1 | 2024-10-08 | 2024-10-19 | 2024-12-31 | 2025-04-05
| JDH3-02-008RSSPR912 | Delivery for Backfilling Materials - PR-SS-Z02-2 | 1 | 2024-10-20 | 2024-10-31 | 2025-01-15 | 2025-04-20
| JDH3-02-008RSSPR913 | Delivery for Isolation Materials - PR-SS-Z02-2 | 1 | 2024-11-01 | 2024-11-12 | 2025-04-02 | 2025-07-06
| JDH3-02-008RSSPR914 | Delivery for GRP pipes - PR-SS-Z02-2 | 1 | 2024-11-13 | 2024-11-24 | 2025-01-01 | 2025-04-06
| JDH3-02-008RSSPR915 | Delivery for Metal Works (Stairs - Covers) - PR-SS-Z02-2 | 1 | 2024-11-25 | 2024-12-06 | 2025-05-05 | 2025-07-31
| JDH3-02-008RSTMI12 | Start of Storm Network - ST - MI-ST | 1 | 2024-07-30 |  | 2024-11-23
| JDH3-02-008RSTPR1021 | Delivery for Concrete - PR-ST-Z06 | 1 | 2024-10-07 | 2024-10-20 | 2025-03-01 | 2025-06-20
| JDH3-02-008RSTPR1022 | Delivery for Precast Concrete - PR-ST-Z06 | 1 | 2024-10-21 | 2024-10-30
| JDH3-02-008RSTPR1023 | Delivery for Backfilling Materials - PR-ST-Z06 | 1 | 2024-10-31 | 2024-11-13 | 2025-03-05 | 2025-06-24
| JDH3-02-008RSTPR1024 | Delivery for Isolation Materials - PR-ST-Z06 | 1 | 2024-11-14 | 2024-11-23
| JDH3-02-008RSTPR1025 | Delivery for GRP pipes - PR-ST-Z06 | 1 | 2024-11-24 | 2024-12-07 | 2025-04-01 | 2025-07-21
| JDH3-02-008RSTPR1026 | Delivery for UPVC pipes - PR-ST-Z06 | 1 | 2024-12-08 | 2024-12-21 | 2024-11-10 | 2025-03-01
| JDH3-02-008RSTPR1027 | Delivery for Catchbasine - PR-ST-Z06 | 1 | 2024-12-22 | 2024-12-31
| JDH3-02-008RSTPR1028 | Delivery for Metal Works (Stairs - Covers) - PR-ST-Z06 | 1 | 2025-01-01 | 2025-01-10
| JDH3-02-008RSTPR1064 | Delivery for Concrete - PR-ST-Z07 | 1 | 2024-08-31 | 2024-09-11 | 2024-12-10 | 2025-03-15
| JDH3-02-008RSTPR1065 | Delivery for Precast Concrete - PR-ST-Z07 | 1 | 2024-09-12 | 2024-09-24 | 2024-12-01 | 2025-03-06
| JDH3-02-008RSTPR1066 | Delivery for Backfilling Materials - PR-ST-Z07 | 1 | 2024-09-25 | 2024-10-06 | 2024-12-07 | 2025-03-12
| JDH3-02-008RSTPR1067 | Delivery for Isolation Materials - PR-ST-Z07 | 1 | 2024-10-07 | 2024-10-18
| JDH3-02-008RSTPR1068 | Delivery for GRP pipes - PR-ST-Z07 | 1 | 2024-10-19 | 2024-10-30 | 2024-11-12 | 2025-02-15
| JDH3-02-008RSTPR1069 | Delivery for UPVC pipes - PR-ST-Z07 | 1 | 2024-10-31 | 2024-11-11 | 2024-11-10 | 2025-02-13
| JDH3-02-008RSTPR1070 | Delivery for Catchbasine - PR-ST-Z07 | 1 | 2024-11-12 | 2024-11-23 | 2025-02-09 | 2025-05-15
| JDH3-02-008RSTPR1071 | Delivery for Metal Works (Stairs - Covers) - PR-ST-Z07 | 1 | 2024-11-24 | 2024-12-05
| JDH3-02-008RSTPR1127 | Delivery for Concrete - PR-ST-Z07-1 | 1 | 2024-08-31 | 2024-09-11 | 2024-12-21 | 2025-03-26
| JDH3-02-008RSTPR1128 | Delivery for Precast Concrete - PR-ST-Z07-1 | 1 | 2024-09-12 | 2024-09-24 | 2025-03-19 | 2025-06-22
| JDH3-02-008RSTPR1129 | Delivery for Backfilling Materials - PR-ST-Z07-1 | 1 | 2024-09-25 | 2024-10-06 | 2024-12-19 | 2025-03-24
| JDH3-02-008RSTPR1130 | Delivery for Isolation Materials - PR-ST-Z07-1 | 1 | 2024-10-07 | 2024-10-18
| JDH3-02-008RSTPR1131 | Delivery for GRP pipes - PR-ST-Z07-1 | 1 | 2024-10-19 | 2024-10-30 | 2024-12-04 | 2025-03-09
| JDH3-02-008RSTPR1132 | Delivery for UPVC pipes - PR-ST-Z07-1 | 1 | 2024-10-31 | 2024-11-11 | 2025-04-01 | 2025-07-05
| JDH3-02-008RSTPR1133 | Delivery for Catchbasine - PR-ST-Z07-1 | 1 | 2024-11-12 | 2024-11-23
| JDH3-02-008RSTPR1134 | Delivery for Metal Works (Stairs - Covers) - PR-ST-Z07-1 | 1 | 2024-11-24 | 2024-12-05
| JDH3-02-008RSTPR1270 | Delivery for Concrete - PR-ST-MR | 1 | 2024-08-31 | 2024-09-11 | 2025-05-15 | 2025-07-31
| JDH3-02-008RSTPR1271 | Delivery for Precast Concrete - PR-ST-MR | 1 | 2024-09-12 | 2024-09-24 | 2025-05-15 | 2025-07-31
| JDH3-02-008RSTPR1272 | Delivery for Backfilling Materials - PR-ST-MR | 1 | 2024-09-25 | 2024-10-06 | 2025-04-02 | 2025-07-06
| JDH3-02-008RSTPR1273 | Delivery for Isolation Materials - PR-ST-MR | 1 | 2024-10-07 | 2024-10-18 | 2025-05-01 | 2025-06-01
| JDH3-02-008RSTPR1274 | Delivery for GRP pipes - PR-ST-MR | 1 | 2024-10-19 | 2024-10-30 | 2025-03-01 | 2025-06-04
| JDH3-02-008RSTPR1275 | Delivery for UPVC pipes - PR-ST-MR | 1 | 2024-10-31 | 2024-11-11 | 2025-05-01 | 2025-07-31
| JDH3-02-008RSTPR1276 | Delivery for Catchbasine - PR-ST-MR | 1 | 2024-11-12 | 2024-11-23 | 2025-03-01 | 2025-06-04
| JDH3-02-008RSTPR1277 | Delivery for Metal Works (Stairs - Covers) - PR-ST-MR | 1 | 2024-11-24 | 2024-12-05 | 2025-05-01 | 2025-07-31
| JDH3-02-008RSTPR1287 | Material Fabrication for Concrete - PR-ST | 1 | 2024-08-25 | 2024-08-30 | 2024-11-14 | 2024-12-31
| JDH3-02-008RSTPR1297 | Material Fabrication for Precast Concrete - PR-ST | 1 | 2024-09-01 | 2024-09-07 | 2024-12-05 | 2025-01-29
| JDH3-02-008RSTPR1307 | Material Fabrication for Backfilling Materials - PR-ST | 1 | 2024-08-25 | 2024-08-29 | 2024-12-26 | 2025-02-03
| JDH3-02-008RSTPR1317 | Material Fabrication for Isolation Materials - PR-ST | 1 | 2024-08-25 | 2024-09-01 | 2024-11-20 | 2025-01-22
| JDH3-02-008RSTPR1327 | Material Fabrication for GRP pipes - PR-ST | 1 | 2024-08-25 | 2024-08-29 | 2024-11-06 | 2024-12-15
| JDH3-02-008RSTPR1337 | Material Fabrication for UPVC pipes - PR-ST | 1 | 2024-08-27 | 2024-09-02 | 2024-10-10 | 2024-12-04
| JDH3-02-008RSTPR1347 | Material Fabrication for Catchbasine - PR-ST | 1 | 2024-08-25 | 2024-09-01 | 2025-01-15 | 2025-03-19
| JDH3-02-008RSTPR1357 | Material Fabrication for Metal Works (Stairs - Covers) - PR-ST | 1 | 2024-08-25 | 2024-08-30 | 2025-03-01 | 2025-04-17
| JDH3-02-008RSTPR1367 | Delivery for Concrete - PR-ST-Z02 | 1 | 2024-12-04 | 2024-12-13
| JDH3-02-008RSTPR1377 | Delivery for Precast Concrete - PR-ST-Z02 | 1 | 2024-12-14 | 2024-12-23
| JDH3-02-008RSTPR1387 | Delivery for Backfilling Materials - PR-ST-Z02 | 1 | 2024-12-24 | 2024-12-31 | 2025-04-02 | 2025-06-04
| JDH3-02-008RSTPR1397 | Delivery for Isolation Materials - PR-ST-Z02 | 1 | 2025-01-01 | 2025-01-04
| JDH3-02-008RSTPR1407 | Delivery for GRP pipes - PR-ST-Z02 | 1 | 2025-01-05 | 2025-01-16 | 2025-03-01 | 2025-07-31
| JDH3-02-008RSTPR1417 | Delivery for UPVC pipes - PR-ST-Z02 | 1 | 2025-01-17 | 2025-01-26
| JDH3-02-008RSTPR1427 | Delivery for Catchbasine - PR-ST-Z02 | 1 | 2025-01-27 | 2025-02-07
| JDH3-02-008RSTPR1437 | Delivery for Metal Works (Stairs - Covers) - PR-ST-Z02 | 1 | 2025-02-08 | 2025-02-19
| JDH3-02-008RSTPR1527 | Delivery for Concrete - PR-ST-Z05 | 1 | 2024-11-24 | 2024-12-03 | 2025-09-02 | 2025-09-10
| JDH3-02-008RSTPR1537 | Delivery for Precast Concrete - PR-ST-Z05 | 1 | 2024-12-04 | 2024-12-13
| JDH3-02-008RSTPR1547 | Delivery for Backfilling Materials - PR-ST-Z05 | 1 | 2024-12-14 | 2024-12-23
| JDH3-02-008RSTPR1557 | Delivery for Isolation Materials - PR-ST-Z05 | 1 | 2024-12-24 | 2025-01-02
| JDH3-02-008RSTPR1567 | Delivery for GRP pipes - PR-ST-Z05 | 1 | 2025-01-03 | 2025-01-22 | 2025-03-12 | 2025-07-31
| JDH3-02-008RSTPR1577 | Delivery for UPVC pipes - PR-ST-Z05 | 1 | 2025-01-23 | 2025-02-05 | 2025-04-01 | 2025-07-21
| JDH3-02-008RSTPR1587 | Delivery for Catchbasine - PR-ST-Z05 | 1 | 2025-02-06 | 2025-02-15
| JDH3-02-008RSTPR1597 | Delivery for Metal Works (Stairs - Covers) - PR-ST-Z05 | 1 | 2025-02-16 | 2025-02-25
| JDH3-02-008RSTPR1687 | Delivery for Concrete - PR-ST-Z11 | 1 | 2024-12-29 | 2025-01-09 | 2024-12-21 | 2025-07-31
| JDH3-02-008RSTPR1687.R | Delivery for Concrete - PR-ST-Z11 -Remaining | 1 | 2025-01-10 | 2025-01-19
| JDH3-02-008RSTPR1697 | Delivery for Precast Concrete - PR-ST-Z11 | 1 | 2025-01-19 | 2025-01-31 | 2025-03-19 | 2025-07-31
| JDH3-02-008RSTPR1707 | Delivery for Backfilling Materials - PR-ST-Z11 | 1 | 2025-01-31 | 2025-02-12 | 2024-12-19 | 2025-07-31
| JDH3-02-008RSTPR1717 | Delivery for Isolation Materials - PR-ST-Z11 | 1 | 2025-02-12 | 2025-02-24
| JDH3-02-008RSTPR1727 | Delivery for GRP pipes - PR-ST-Z11 | 1 | 2025-02-24 | 2025-03-08 | 2024-12-04 | 2025-07-31
| JDH3-02-008RSTPR1737 | Delivery for UPVC pipes - PR-ST-Z11 | 1 | 2025-03-08 | 2025-03-20 | 2024-12-28 | 2025-07-31
| JDH3-02-008RSTPR1737.R | Delivery for UPVC pipes - PR-ST-Z11 -Remaining | 1 | 2025-03-20 | 2025-03-28
| JDH3-02-008RSTPR1747 | Delivery for Catchbasine - PR-ST-Z11 | 1 | 2025-03-28 | 2025-04-09
| JDH3-02-008RSTPR1757 | Delivery for Metal Works (Stairs - Covers) - PR-ST-Z11 | 1 | 2025-04-09 | 2025-04-21
| JDH3-02-008RSTPR1767 | Delivery for Concrete - PR-ST-Z12 | 1 | 2025-06-08 | 2025-06-20 | 2024-12-21 | 2025-07-31
| JDH3-02-008RSTPR1767.R | Delivery for Concrete - PR-ST-Z12 -Remaining | 1 | 2025-06-20 | 2025-07-02
| JDH3-02-008RSTPR1777 | Delivery for Precast Concrete - PR-ST-Z12 | 1 | 2025-07-02 | 2025-07-14 | 2025-03-19 | 2025-07-31
| JDH3-02-008RSTPR1787 | Delivery for Backfilling Materials - PR-ST-Z12 | 1 | 2025-07-14 | 2025-07-26 | 2024-12-19 | 2025-07-31
| JDH3-02-008RSTPR1797 | Delivery for Isolation Materials - PR-ST-Z12 | 1 | 2025-07-26 | 2025-08-07
| JDH3-02-008RSTPR1807 | Delivery for GRP pipes - PR-ST-Z12 | 1 | 2025-08-07 | 2025-08-19 | 2024-12-04 | 2025-07-31
| JDH3-02-008RSTPR1817 | Delivery for UPVC pipes - PR-ST-Z12 | 1 | 2025-08-19 | 2025-08-31 | 2024-12-28 | 2025-07-31
| JDH3-02-008RSTPR1817.R | Delivery for UPVC pipes - PR-ST-Z12 -Remaining | 1 | 2025-08-31 | 2025-09-12
| JDH3-02-008RSTPR1827 | Delivery for Catchbasine - PR-ST-Z12 | 1 | 2025-09-12 | 2025-09-24
| JDH3-02-008RSTPR1837 | Delivery for Metal Works (Stairs - Covers) - PR-ST-Z12 | 1 | 2025-09-24 | 2025-10-06
| JDH3-02-008RSTPR556 | Prepare Material Submittal for Concrete - PR-ST | 1 | 2024-07-30 | 2024-08-06 | 2024-09-21 | 2024-11-25
| JDH3-02-008RSTPR557 | Prepare Material Submittal for Precast Concrete - PR-ST | 1 | 2024-07-30 | 2024-08-06 | 2024-11-19 | 2025-01-22
| JDH3-02-008RSTPR558 | Prepare Material Submittal for Backfilling Materials - PR-ST | 1 | 2024-07-30 | 2024-08-06 | 2024-11-07 | 2025-01-11
| JDH3-02-008RSTPR559 | Prepare Material Submittal for Isolation Materials - PR-ST | 1 | 2024-07-30 | 2024-08-06 | 2024-11-25 | 2025-01-28
| JDH3-02-008RSTPR560 | Prepare Material Submittal for GRP pipes - PR-ST | 1 | 2024-07-30 | 2024-08-06 | 2024-09-18 | 2024-11-23
| JDH3-02-008RSTPR561 | Prepare Material Submittal for UPVC pipes - PR-ST | 1 | 2024-07-30 | 2024-08-06 | 2024-09-15 | 2024-11-19
| JDH3-02-008RSTPR562 | Prepare Material Submittal for Catchbasine - PR-ST | 1 | 2024-07-30 | 2024-08-06 | 2024-09-26 | 2024-11-30
| JDH3-02-008RSTPR563 | Prepare Material Submittal for Metal Works (Stairs - Covers) - PR-ST | 1 | 2024-07-30 | 2024-08-06 | 2024-10-01 | 2024-12-04
| JDH3-02-008RSTPR618 | Review and Approval of Material Submittal for Concrete - PR-ST | 1 | 2024-08-07 | 2024-08-18 | 2024-11-14 | 2025-02-11
| JDH3-02-008RSTPR619 | Review and Approval of Material Submittal for Precast Concrete - PR-ST | 1 | 2024-08-07 | 2024-08-20 | 2024-11-24 | 2025-03-13
| JDH3-02-008RSTPR620 | Review and Approval of Material Submittal for Backfilling Materials - PR-ST | 1 | 2024-08-07 | 2024-08-18 | 2024-11-11 | 2025-02-06
| JDH3-02-008RSTPR621 | Review and Approval of Material Submittal for Isolation Materials - PR-ST | 1 | 2024-08-07 | 2024-08-18 | 2024-11-27 | 2025-02-24
| JDH3-02-008RSTPR622 | Review and Approval of Material Submittal for GRP pipes - PR-ST | 1 | 2024-08-07 | 2024-08-18 | 2024-09-22 | 2024-12-19
| JDH3-02-008RSTPR623 | Review and Approval of Material Submittal for UPVC pipes - PR-ST | 1 | 2024-08-07 | 2024-08-20 | 2024-09-24 | 2025-01-13
| JDH3-02-008RSTPR624 | Review and Approval of Material Submittal for Catchbasine - PR-ST | 1 | 2024-08-07 | 2024-08-18 | 2024-11-27 | 2025-02-24
| JDH3-02-008RSTPR625 | Review and Approval of Material Submittal for Metal Works (Stairs - Covers) - PR-ST | 1 | 2024-08-07 | 2024-08-18 | 2024-10-08 | 2025-01-05
| JDH3-02-008RSTPR680 | Material Purchase Order for Concrete - PR-ST | 1 | 2024-08-19 | 2024-08-24 | 2024-11-14 | 2024-12-31
| JDH3-02-008RSTPR681 | Material Purchase Order for Precast Concrete - PR-ST | 1 | 2024-08-26 | 2024-08-31 | 2024-12-05 | 2025-01-21
| JDH3-02-008RSTPR682 | Material Purchase Order for Backfilling Materials - PR-ST | 1 | 2024-08-19 | 2024-08-24 | 2024-12-26 | 2025-02-11
| JDH3-02-008RSTPR683 | Material Purchase Order for Isolation Materials - PR-ST | 1 | 2024-08-19 | 2024-08-24 | 2024-11-20 | 2025-01-06
| JDH3-02-008RSTPR684 | Material Purchase Order for GRP pipes - PR-ST | 1 | 2024-08-19 | 2024-08-24 | 2024-11-06 | 2024-12-23
| JDH3-02-008RSTPR685 | Material Purchase Order for UPVC pipes - PR-ST | 1 | 2024-08-21 | 2024-08-26 | 2024-10-10 | 2024-11-26
| JDH3-02-008RSTPR686 | Material Purchase Order for Catchbasine - PR-ST | 1 | 2024-08-19 | 2024-08-24 | 2025-01-15 | 2025-03-03
| JDH3-02-008RSTPR687 | Material Purchase Order for Metal Works (Stairs - Covers) - PR-ST | 1 | 2024-08-19 | 2024-08-24 | 2025-03-01 | 2025-04-17
| JDH3-02-008RSTPR748 | Delivery for Concrete - PR-ST-Z01 | 1 | 2025-08-02 | 2025-08-13 | 2025-03-07 | 2025-06-10
| JDH3-02-008RSTPR749 | Delivery for Precast Concrete - PR-ST-Z01 | 1 | 2025-08-14 | 2025-08-25
| JDH3-02-008RSTPR750 | Delivery for Backfilling Materials - PR-ST-Z01 | 1 | 2025-08-26 | 2025-09-06 | 2025-01-18 | 2025-04-23
| JDH3-02-008RSTPR751 | Delivery for Isolation Materials - PR-ST-Z01 | 1 | 2025-09-07 | 2025-09-18
| JDH3-02-008RSTPR752 | Delivery for GRP pipes - PR-ST-Z01 | 1 | 2025-09-19 | 2025-09-30 | 2025-01-12 | 2025-04-17
| JDH3-02-008RSTPR854 | Delivery for Concrete - PR-ST-Z02-1 | 1 | 2024-08-31 | 2024-09-11 | 2025-06-05 | 2025-07-31
| JDH3-02-008RSTPR855 | Delivery for Precast Concrete - PR-ST-Z02-1 | 1 | 2024-09-12 | 2024-09-24 | 2025-05-01 | 2025-07-31
| JDH3-02-008RSTPR856 | Delivery for Backfilling Materials - PR-ST-Z02-1 | 1 | 2024-09-25 | 2024-10-06 | 2025-06-01 | 2025-07-31
| JDH3-02-008RSTPR857 | Delivery for Isolation Materials - PR-ST-Z02-1 | 1 | 2024-10-07 | 2024-10-18 | 2025-06-05 | 2025-07-31
| JDH3-02-008RSTPR858 | Delivery for GRP pipes - PR-ST-Z02-1 | 1 | 2024-10-19 | 2024-10-30 | 2025-03-12 | 2025-06-15
| JDH3-02-008RSTPR859 | Delivery for UPVC pipes - PR-ST-Z02-1 | 1 | 2024-10-31 | 2024-11-11 | 2025-04-01 | 2025-07-05
| JDH3-02-008RSTPR860 | Delivery for Catchbasine - PR-ST-Z02-1 | 1 | 2024-11-12 | 2024-11-23 | 2025-05-07 | 2025-07-31
| JDH3-02-008RSTPR861 | Delivery for Metal Works (Stairs - Covers) - PR-ST-Z02-1 | 1 | 2024-11-24 | 2024-12-03
| JDH3-02-008RSTPR917 | Delivery for Concrete - PR-ST-Z02-2 | 1 | 2024-08-31 | 2024-09-13 | 2025-02-04 | 2025-05-26
| JDH3-02-008RSTPR918 | Delivery for Precast Concrete - PR-ST-Z02-2 | 1 | 2024-09-14 | 2024-09-28 | 2025-02-04 | 2025-05-26
| JDH3-02-008RSTPR919 | Delivery for Backfilling Materials - PR-ST-Z02-2 | 1 | 2024-09-29 | 2024-10-12 | 2025-01-12 | 2025-05-03
| JDH3-02-008RSTPR920 | Delivery for Isolation Materials - PR-ST-Z02-2 | 1 | 2024-10-13 | 2024-10-26 | 2025-05-06 | 2025-07-31
| JDH3-02-008RSTPR921 | Delivery for GRP pipes - PR-ST-Z02-2 | 1 | 2024-10-27 | 2024-11-09 | 2025-01-01 | 2025-04-22
| JDH3-02-008RSTPR922 | Delivery for UPVC pipes - PR-ST-Z02-2 | 1 | 2024-11-10 | 2024-11-23 | 2025-04-01 | 2025-07-21
| JDH3-02-008RSTPR923 | Delivery for Catchbasine - PR-ST-Z02-2 | 1 | 2024-11-24 | 2024-12-07 | 2025-05-04 | 2025-07-31
| JDH3-02-008RSTPR924 | Delivery for Metal Works (Stairs - Covers) - PR-ST-Z02-2 | 1 | 2024-12-08 | 2024-12-21 | 2025-05-06 | 2025-07-31
| JDH3-02-008RTCPR1174 | Delivery for Manhole - PR-TC-Z07-1 | 1 | 2024-12-05 | 2024-12-16
| JDH3-02-008RTCPR1175 | Delivery for Duct - PR-TC-Z07-1 | 1 | 2024-12-17 | 2024-12-28
| JDH3-02-008RTCPR1317 | Delivery for Manhole - PR-TC-MR | 1 | 2025-05-10 | 2025-05-21
| JDH3-02-008RTCPR1318 | Delivery for Duct - PR-TC-MR | 1 | 2025-05-22 | 2025-06-02
| JDH3-02-008RTCPR1328 | Prepare Material Submittal for CCTV System | 1 | 2024-07-30 | 2024-08-05 | 2025-07-02 | 2025-07-31
| JDH3-02-008RTCPR1348 | Review and Approval of Material Submittal for CCTV System | 1 | 2024-08-06 | 2024-08-19 | 2025-07-10 | 2025-07-31
| JDH3-02-008RTCPR1358 | Material Purchase Order for CCTV System | 1 | 2024-08-20 | 2024-08-25 | 2025-07-02 | 2025-07-31
| JDH3-02-008RTCPR1378 | Material Fabrication for CCTV System | 1 | 2024-08-26 | 2024-08-31 | 2025-07-09 | 2025-07-31
| JDH3-02-008RTCPR1398 | Material Fabrication for Duct - PR-TC | 1 | 2024-08-26 | 2024-08-31 | 2025-07-02 | 2025-07-31
| JDH3-02-008RTCPR603 | Prepare Material Submittal for Manhole - PR-TC | 1 | 2024-07-30 | 2024-08-05 | 2024-11-19 | 2025-01-13
| JDH3-02-008RTCPR604 | Prepare Material Submittal for Duct - PR-TC | 1 | 2024-07-30 | 2024-08-05 | 2024-09-21 | 2024-11-16
| JDH3-02-008RTCPR665 | Review and Approval of Material Submittal for Manhole - PR-TC | 1 | 2024-08-06 | 2024-08-19 | 2025-02-19 | 2025-06-10
| JDH3-02-008RTCPR666 | Review and Approval of Material Submittal for Duct - PR-TC | 1 | 2024-08-06 | 2024-08-19 | 2024-11-14 | 2025-03-05
| JDH3-02-008RTCPR727 | Material Purchase Order for Duct - PR-TC | 1 | 2024-08-20 | 2024-08-25 | 2025-04-01 | 2025-05-18
| JDH3-02-008RTCPR728 | Material Purchase Order for Manhole - PR-TC | 1 | 2024-08-20 | 2024-08-25 | 2025-04-01 | 2025-05-18
| JDH3-02-008RTCPR745 | Material Fabrication for Manhole - PR-TC | 1 | 2024-08-26 | 2024-08-31 | 2025-07-02 | 2025-07-31
| JDH3-02-008RTCPR901 | Delivery for Manhole - PR-TC-Z02-1 | 1 | 2024-12-05 | 2024-12-16
| JDH3-02-008RTCPR902 | Delivery for Duct - PR-TC-Z02-1 | 1 | 2024-12-17 | 2024-12-28
| JDH3-02-008RTCPR964 | Delivery for Manhole - PR-TC-Z02-2 | 1 | 2024-09-01 | 2024-09-12 | 2025-05-01 | 2025-07-31
| JDH3-02-008RTCPR965 | Delivery for Duct - PR-TC-Z02-2 | 1 | 2024-10-08 | 2024-10-19 | 2025-05-01 | 2025-07-31
| JDH3-02-008RTSEMI16 | Start of TSE Network - TSE - MI-TSE | 1 | 2024-07-30 |  | 2024-12-08
| JDH3-02-008RWTMI14 | Start of Potable Water Network - WT - MI-WT | 1 | 2024-07-30 |  | 2025-01-09
| JDH3-02-008RWTPR1030 | Delivery for Concrete - PR-WT-Z06 | 1 | 2025-01-11 | 2025-01-19 | 2025-08-04 | 2025-08-27
| JDH3-02-008RWTPR1031 | Delivery for Precast Concrete - PR-WT-Z06 | 1 | 2025-01-20 | 2025-01-28 | 2025-08-12 | 2025-08-28
| JDH3-02-008RWTPR1032 | Delivery for Backfilling Materials - PR-WT-Z06 | 1 | 2025-01-29 | 2025-02-06 | 2025-06-18 | 2025-07-07
| JDH3-02-008RWTPR1033 | Delivery for Isolation Materials - PR-WT-Z06 | 1 | 2025-02-07 | 2025-02-15 | 2025-08-04 | 2025-08-21
| JDH3-02-008RWTPR1034 | Delivery for GRP pipes - PR-WT-Z06 | 1 | 2025-02-16 | 2025-02-24 | 2025-08-12 | 2025-08-28
| JDH3-02-008RWTPR1035 | Delivery for HDPE pipes - PR-WT-Z06 | 1 | 2025-02-25 | 2025-03-05 | 2025-06-10 | 2025-07-27
| JDH3-02-008RWTPR1036 | Delivery for DI pipes - PR-WT-Z06 | 1 | 2025-03-06 | 2025-03-14 | 2025-06-17 | 2025-07-15
| JDH3-02-008RWTPR1037 | Delivery for Bolts and Rubber Gasket - PR-WT-Z06 | 1 | 2025-03-15 | 2025-03-23 | 2025-08-04 | 2025-08-20
| JDH3-02-008RWTPR1038 | Delivery for Valves (Aira & Gate) - PR-WT-Z06 | 1 | 2025-03-24 | 2025-04-01 | 2025-08-04 | 2025-08-20
| JDH3-02-008RWTPR1039 | Delivery for Metal Works (Stairs - Covers) - PR-WT-Z06 | 1 | 2025-04-02 | 2025-04-10
| JDH3-02-008RWTPR1073 | Delivery for Concrete - PR-WT-Z07 | 1 | 2024-09-01 | 2024-09-06 | 2025-08-04 | 2025-08-27
| JDH3-02-008RWTPR1074 | Delivery for Precast Concrete - PR-WT-Z07 | 1 | 2024-09-07 | 2024-09-12 | 2025-08-12 | 2025-08-28
| JDH3-02-008RWTPR1075 | Delivery for Backfilling Materials - PR-WT-Z07 | 1 | 2024-09-13 | 2024-09-18 | 2025-06-18 | 2025-07-07
| JDH3-02-008RWTPR1076 | Delivery for Isolation Materials - PR-WT-Z07 | 1 | 2024-09-19 | 2024-09-25 | 2025-08-04 | 2025-08-21
| JDH3-02-008RWTPR1077 | Delivery for GRP pipes - PR-WT-Z07 | 1 | 2024-09-26 | 2024-10-01 | 2025-08-12 | 2025-08-28
| JDH3-02-008RWTPR1078 | Delivery for HDPE pipes - PR-WT-Z07 | 1 | 2024-10-02 | 2024-10-07 | 2025-06-10 | 2025-07-27
| JDH3-02-008RWTPR1079 | Delivery for DI pipes - PR-WT-Z07 | 1 | 2024-10-08 | 2024-10-13 | 2025-06-17 | 2025-07-15
| JDH3-02-008RWTPR1080 | Delivery for Bolts and Rubber Gasket - PR-WT-Z07 | 1 | 2024-10-14 | 2024-10-19 | 2025-08-04 | 2025-08-20
| JDH3-02-008RWTPR1081 | Delivery for Valves (Aira & Gate) - PR-WT-Z07 | 1 | 2024-10-20 | 2024-10-25 | 2025-08-04 | 2025-08-20
| JDH3-02-008RWTPR1082 | Delivery for Metal Works (Stairs - Covers) - PR-WT-Z07 | 1 | 2024-10-26 | 2024-10-31
| JDH3-02-008RWTPR1136 | Delivery for Concrete - PR-WT-Z07-1 | 1 | 2024-09-01 | 2024-09-06 | 2025-06-28 | 2025-07-31
| JDH3-02-008RWTPR1137 | Delivery for Precast Concrete - PR-WT-Z07-1 | 1 | 2024-09-07 | 2024-09-12 | 2025-05-01 | 2025-07-11
| JDH3-02-008RWTPR1138 | Delivery for Backfilling Materials - PR-WT-Z07-1 | 1 | 2024-09-13 | 2024-09-18 | 2025-08-04 | 2025-08-21
| JDH3-02-008RWTPR1139 | Delivery for Isolation Materials - PR-WT-Z07-1 | 1 | 2024-09-19 | 2024-09-25 | 2025-06-18 | 2025-07-07
| JDH3-02-008RWTPR1140 | Delivery for GRP pipes - PR-WT-Z07-1 | 1 | 2024-09-26 | 2024-10-01 | 2025-06-10 | 2025-07-27
| JDH3-02-008RWTPR1141 | Delivery for HDPE pipes - PR-WT-Z07-1 | 1 | 2024-10-02 | 2024-10-07 | 2025-08-04 | 2025-08-20
| JDH3-02-008RWTPR1142 | Delivery for DI pipes - PR-WT-Z07-1 | 1 | 2024-10-08 | 2024-10-13 | 2025-08-04 | 2025-08-20
| JDH3-02-008RWTPR1143 | Delivery for Bolts and Rubber Gasket - PR-WT-Z07-1 | 1 | 2024-10-14 | 2024-10-19 | 2025-08-12 | 2025-08-28
| JDH3-02-008RWTPR1144 | Delivery for Valves (Aira & Gate) - PR-WT-Z07-1 | 1 | 2024-10-20 | 2024-10-25 | 2024-11-07 | 2024-12-24
| JDH3-02-008RWTPR1145 | Delivery for Metal Works (Stairs - Covers) - PR-WT-Z07-1 | 1 | 2024-10-26 | 2024-10-31
| JDH3-02-008RWTPR1279 | Delivery for Concrete - PR-WT-MR | 1 | 2024-12-29 | 2025-01-09 | 2025-08-04 | 2025-08-27
| JDH3-02-008RWTPR1280 | Delivery for Precast Concrete - PR-WT-MR | 1 | 2025-01-10 | 2025-01-21 | 2025-08-12 | 2025-08-28
| JDH3-02-008RWTPR1281 | Delivery for Backfilling Materials - PR-WT-MR | 1 | 2025-01-22 | 2025-02-02 | 2025-06-18 | 2025-07-07
| JDH3-02-008RWTPR1282 | Delivery for Isolation Materials - PR-WT-MR | 1 | 2025-02-03 | 2025-02-14 | 2025-08-04 | 2025-08-21
| JDH3-02-008RWTPR1283 | Delivery for GRP pipes - PR-WT-MR | 1 | 2025-02-15 | 2025-02-26 | 2025-08-12 | 2025-08-28
| JDH3-02-008RWTPR1284 | Delivery for HDPE pipes - PR-WT-MR | 1 | 2025-02-27 | 2025-03-10 | 2025-06-10 | 2025-07-27
| JDH3-02-008RWTPR1285 | Delivery for DI pipes - PR-WT-MR | 1 | 2025-03-11 | 2025-03-22 | 2025-06-17 | 2025-07-15
| JDH3-02-008RWTPR1286 | Delivery for Bolts and Rubber Gasket - PR-WT-MR | 1 | 2025-03-23 | 2025-04-03 | 2025-08-04 | 2025-08-20
| JDH3-02-008RWTPR1287 | Delivery for Valves (Aira & Gate) - PR-WT-MR | 1 | 2025-04-04 | 2025-04-15 | 2025-08-04 | 2025-08-20
| JDH3-02-008RWTPR1288 | Delivery for Metal Works (Stairs - Covers) - PR-WT-MR | 1 | 2025-04-16 | 2025-04-27
| JDH3-02-008RWTPR1298 | Material Fabrication for Concrete - PR-WT | 1 | 2024-08-26 | 2024-08-31 | 2024-11-14 | 2024-12-31
| JDH3-02-008RWTPR1308 | Material Fabrication for Precast Concrete - PR-WT | 1 | 2024-08-26 | 2024-08-31 | 2025-05-02 | 2025-06-18
| JDH3-02-008RWTPR1318 | Material Fabrication for Backfilling Materials - PR-WT | 1 | 2024-08-26 | 2024-08-30 | 2024-12-26 | 2025-02-03
| JDH3-02-008RWTPR1328 | Material Fabrication for Isolation Materials - PR-WT | 1 | 2024-08-26 | 2024-09-02 | 2024-11-20 | 2025-01-22
| JDH3-02-008RWTPR1338 | Material Fabrication for GRP pipes - PR-WT | 1 | 2024-08-26 | 2024-08-31 | 2025-05-02 | 2025-06-18
| JDH3-02-008RWTPR1348 | Material Fabrication for HDPE pipes - PR-WT | 1 | 2024-08-26 | 2024-09-01 | 2024-11-18 | 2025-01-12
| JDH3-02-008RWTPR1358 | Material Fabrication for DI pipes - PR-WT | 1 | 2024-08-26 | 2024-08-30 | 2025-05-02 | 2025-06-10
| JDH3-02-008RWTPR1368 | Material Fabrication for Bolts and Rubber Gasket - PR-WT | 1 | 2024-08-26 | 2024-09-02 | 2024-12-01 | 2025-02-02
| JDH3-02-008RWTPR1378 | Material Fabrication for Valves (Aira & Gate) - PR-WT | 1 | 2024-08-26 | 2024-08-31 | 2025-05-09 | 2025-06-25
| JDH3-02-008RWTPR1388 | Material Fabrication for Metal Works (Stairs - Covers) - PR-WT | 1 | 2024-08-26 | 2024-08-31 | 2025-03-01 | 2025-04-17
| JDH3-02-008RWTPR1398 | Delivery for Concrete - PR-WT-Z01 | 1 | 2025-06-03 | 2025-06-08 | 2025-08-04 | 2025-08-27
| JDH3-02-008RWTPR1408 | Delivery for Precast Concrete - PR-WT-Z01 | 1 | 2025-06-09 | 2025-06-14 | 2025-08-12 | 2025-08-28
| JDH3-02-008RWTPR1418 | Delivery for Backfilling Materials - PR-WT-Z01 | 1 | 2025-06-15 | 2025-06-20 | 2025-06-18 | 2025-07-07
| JDH3-02-008RWTPR1428 | Delivery for Isolation Materials - PR-WT-Z01 | 1 | 2025-06-21 | 2025-06-26 | 2025-08-04 | 2025-08-21
| JDH3-02-008RWTPR1438 | Delivery for GRP pipes - PR-WT-Z01 | 1 | 2025-06-27 | 2025-07-02 | 2025-08-12 | 2025-08-28
| JDH3-02-008RWTPR1448 | Delivery for HDPE pipes - PR-WT-Z01 | 1 | 2025-07-03 | 2025-07-08 | 2025-06-10 | 2025-07-27
| JDH3-02-008RWTPR1458 | Delivery for DI pipes - PR-WT-Z01 | 1 | 2025-07-09 | 2025-07-14 | 2025-06-17 | 2025-07-15
| JDH3-02-008RWTPR1468 | Delivery for Bolts and Rubber Gasket - PR-WT-Z01 | 1 | 2025-07-15 | 2025-07-20 | 2025-08-04 | 2025-08-20
| JDH3-02-008RWTPR1478 | Delivery for Valves (Aira & Gate) - PR-WT-Z01 | 1 | 2025-07-21 | 2025-07-26 | 2025-08-04 | 2025-08-20
| JDH3-02-008RWTPR1488 | Delivery for Metal Works (Stairs - Covers) - PR-WT-Z01 | 1 | 2025-07-27 | 2025-08-01
| JDH3-02-008RWTPR1498 | Delivery for Concrete - PR-WT-Z13 | 1 | 2025-07-28 | 2025-08-02 | 2025-05-27 | 2025-07-31
| JDH3-02-008RWTPR1508 | Delivery for Precast Concrete - PR-WT-Z13 | 1 | 2025-08-03 | 2025-08-08 | 2025-06-28 | 2025-07-31
| JDH3-02-008RWTPR1518 | Delivery for Backfilling Materials - PR-WT-Z13 | 1 | 2025-08-09 | 2025-08-15 | 2025-06-10 | 2025-07-31
| JDH3-02-008RWTPR1528 | Delivery for Isolation Materials - PR-WT-Z13 | 1 | 2025-08-16 | 2025-08-21 | 2025-01-01 | 2025-03-13
| JDH3-02-008RWTPR1538 | Delivery for GRP pipes - PR-WT-Z13 | 1 | 2025-08-22 | 2025-08-27 | 2025-05-01 | 2025-06-24
| JDH3-02-008RWTPR1548 | Delivery for HDPE pipes - PR-WT-Z13 | 1 | 2025-08-28 | 2025-09-06 | 2025-05-20 | 2025-07-31
| JDH3-02-008RWTPR1558 | Delivery for DI pipes - PR-WT-Z13 | 1 | 2025-09-07 | 2025-09-12 | 2025-06-08 | 2025-07-31
| JDH3-02-008RWTPR1568 | Delivery for Bolts and Rubber Gasket - PR-WT-Z13 | 1 | 2025-09-13 | 2025-09-18 | 2025-06-08 | 2025-07-31
| JDH3-02-008RWTPR1578 | Delivery for Valves (Aira & Gate) - PR-WT-Z13 | 1 | 2025-09-19 | 2025-09-24 | 2025-06-28 | 2025-07-31
| JDH3-02-008RWTPR1588 | Delivery for Metal Works (Stairs - Covers) - PR-WT-Z13 | 1 | 2025-09-25 | 2025-09-30
| JDH3-02-008RWTPR1608 | Material Fabrication for Butterfly Valves (Importing) - PR-WT | 1 | 2024-08-28 | 2024-10-27
| JDH3-02-008RWTPR1618 | Delivery for Butterfly Valves (Importing) - PR-WT-MR | 1 | 2025-04-28 | 2025-06-26
| JDH3-02-008RWTPR565 | Prepare Material Submittal for Concrete - PR-WT | 1 | 2024-07-30 | 2024-08-05 | 2024-09-21 | 2024-11-16
| JDH3-02-008RWTPR566 | Prepare Material Submittal for Precast Concrete - PR-WT | 1 | 2024-07-30 | 2024-08-05 | 2024-11-19 | 2025-01-13
| JDH3-02-008RWTPR567 | Prepare Material Submittal for Backfilling Materials - PR-WT | 1 | 2024-07-30 | 2024-08-05 | 2024-11-07 | 2025-01-01
| JDH3-02-008RWTPR568 | Prepare Material Submittal for Isolation Materials - PR-WT | 1 | 2024-07-30 | 2024-08-05 | 2024-11-25 | 2025-01-19
| JDH3-02-008RWTPR569 | Prepare Material Submittal for GRP pipes - PR-WT | 1 | 2024-07-30 | 2024-08-05 | 2024-09-21 | 2024-11-16
| JDH3-02-008RWTPR570 | Prepare Material Submittal for HDPE pipes - PR-WT | 1 | 2024-07-30 | 2024-08-05 | 2024-09-18 | 2024-11-13
| JDH3-02-008RWTPR571 | Prepare Material Submittal for DI pipes - PR-WT | 1 | 2024-07-30 | 2024-08-05 | 2024-09-28 | 2024-11-21
| JDH3-02-008RWTPR572 | Prepare Material Submittal for Bolts and Rubber Gasket - PR-WT | 1 | 2024-07-30 | 2024-08-05 | 2024-11-18 | 2025-01-12
| JDH3-02-008RWTPR573 | Prepare Material Submittal for Valves - PR-WT | 1 | 2024-07-30 | 2024-08-05 | 2024-09-28 | 2024-11-21
| JDH3-02-008RWTPR574 | Prepare Material Submittal for Metal Works (Stairs - Covers) - PR-WT | 1 | 2024-07-30 | 2024-08-05 | 2024-10-01 | 2024-11-25
| JDH3-02-008RWTPR627 | Review and Approval of Material Submittal for Concrete - PR-WT | 1 | 2024-08-06 | 2024-08-19 | 2024-11-14 | 2025-03-05
| JDH3-02-008RWTPR628 | Review and Approval of Material Submittal for Precast Concrete - PR-WT | 1 | 2024-08-06 | 2024-08-19 | 2024-11-24 | 2025-03-13
| JDH3-02-008RWTPR629 | Review and Approval of Material Submittal for Backfilling Materials - PR-WT | 1 | 2024-08-06 | 2024-08-19 | 2024-11-11 | 2025-03-02
| JDH3-02-008RWTPR630 | Review and Approval of Material Submittal for Isolation Materials - PR-WT | 1 | 2024-08-06 | 2024-08-19 | 2024-11-27 | 2025-03-18
| JDH3-02-008RWTPR631 | Review and Approval of Material Submittal for GRP pipes - PR-WT | 1 | 2024-08-06 | 2024-08-19 | 2024-10-28 | 2025-02-16
| JDH3-02-008RWTPR632 | Review and Approval of Material Submittal for HDPE pipes - PR-WT | 1 | 2024-08-06 | 2024-08-19 | 2024-09-30 | 2025-01-19
| JDH3-02-008RWTPR633 | Review and Approval of Material Submittal for DI pipes - PR-WT | 1 | 2024-08-06 | 2024-08-19 | 2024-10-03 | 2025-01-22
| JDH3-02-008RWTPR634 | Review and Approval of Material Submittal for Bolts and Rubber Gasket - PR-WT | 1 | 2024-08-06 | 2024-08-19 | 2024-11-24 | 2025-03-13
| JDH3-02-008RWTPR635 | Review and Approval of Material Submittal for Valves - PR-WT | 1 | 2024-08-06 | 2024-08-19 | 2024-10-03 | 2025-01-22
| JDH3-02-008RWTPR636 | Review and Approval of Material Submittal for Metal Works (Stairs - Covers) - PR-WT | 1 | 2024-08-06 | 2024-08-19 | 2024-10-08 | 2025-01-27
| JDH3-02-008RWTPR689 | Material Purchase Order for Concrete - PR-WT | 1 | 2024-08-20 | 2024-08-25 | 2024-11-14 | 2024-12-31
| JDH3-02-008RWTPR690 | Material Purchase Order for Precast Concrete - PR-WT | 1 | 2024-08-20 | 2024-08-25 | 2025-06-02 | 2025-07-19
| JDH3-02-008RWTPR691 | Material Purchase Order for Backfilling Materials - PR-WT | 1 | 2024-08-20 | 2024-08-25 | 2024-12-26 | 2025-02-11
| JDH3-02-008RWTPR692 | Material Purchase Order for Isolation Materials - PR-WT | 1 | 2024-08-20 | 2024-08-25 | 2024-11-20 | 2025-01-06
| JDH3-02-008RWTPR693 | Material Purchase Order for GRP pipes - PR-WT | 1 | 2024-08-20 | 2024-08-25 | 2025-04-06 | 2025-05-23
| JDH3-02-008RWTPR694 | Material Purchase Order for HDPE pipes - PR-WT | 1 | 2024-08-20 | 2024-08-25 | 2024-11-18 | 2025-01-04
| JDH3-02-008RWTPR695 | Material Purchase Order for DI pipes - PR-WT | 1 | 2024-08-20 | 2024-08-25 | 2025-06-02 | 2025-07-19
| JDH3-02-008RWTPR696 | Material Purchase Order for Bolts and Rubber Gasket - PR-WT | 1 | 2024-08-20 | 2024-08-25 | 2024-12-01 | 2025-01-17
| JDH3-02-008RWTPR697 | Material Purchase Order for Valves (Aira & Gate) - PR-WT | 1 | 2024-08-20 | 2024-08-25 | 2025-05-02 | 2025-06-18
| JDH3-02-008RWTPR6970 | Material Purchase Order for Butterfly Valves (Importing) - PR-TSE | 1 | 2024-08-20 | 2024-08-27
| JDH3-02-008RWTPR698 | Material Purchase Order for Metal Works (Stairs - Covers) - PR-WT | 1 | 2024-08-20 | 2024-08-25 | 2025-03-01 | 2025-04-17
| JDH3-02-008RWTPR700 | Material Purchase Order for Butterfly Valves (Importing) - PR-WT | 1 | 2024-08-20 | 2024-08-27
| JDH3-02-008RWTPR863 | Delivery for Concrete - PR-WT-Z02-1 | 1 | 2024-09-01 | 2024-09-06 | 2025-08-04 | 2025-08-27
| JDH3-02-008RWTPR864 | Delivery for Precast Concrete - PR-WT-Z02-1 | 1 | 2024-09-07 | 2024-09-12 | 2025-08-12 | 2025-08-28
| JDH3-02-008RWTPR865 | Delivery for Backfilling Materials - PR-WT-Z02-1 | 1 | 2024-09-13 | 2024-09-18 | 2025-06-18 | 2025-07-07
| JDH3-02-008RWTPR866 | Delivery for Isolation Materials - PR-WT-Z02-1 | 1 | 2024-09-19 | 2024-09-25 | 2025-08-04 | 2025-08-21
| JDH3-02-008RWTPR867 | Delivery for GRP pipes - PR-WT-Z02-1 | 1 | 2024-09-26 | 2024-10-01 | 2025-08-12 | 2025-08-28
| JDH3-02-008RWTPR868 | Delivery for HDPE pipes - PR-WT-Z02-1 | 1 | 2024-10-02 | 2024-10-07 | 2025-06-10 | 2025-07-27
| JDH3-02-008RWTPR869 | Delivery for DI pipes - PR-WT-Z02-1 | 1 | 2024-10-08 | 2024-10-13 | 2025-06-17 | 2025-07-15
| JDH3-02-008RWTPR870 | Delivery for Bolts and Rubber Gasket - PR-WT-Z02-1 | 1 | 2024-10-14 | 2024-10-19 | 2025-08-04 | 2025-08-20
| JDH3-02-008RWTPR871 | Delivery for Valves (Aira & Gate) - PR-WT-Z02-1 | 1 | 2024-10-20 | 2024-10-25 | 2025-08-04 | 2025-08-20
| JDH3-02-008RWTPR872 | Delivery for Metal Works (Stairs - Covers) - PR-WT-Z02-1 | 1 | 2024-10-26 | 2024-10-31
| JDH3-02-008RWTPR926 | Delivery for Concrete - PR-WT-Z02-2 | 1 | 2024-11-25 | 2024-12-03 | 2025-05-27 | 2025-07-31
| JDH3-02-008RWTPR927 | Delivery for Precast Concrete - PR-WT-Z02-2 | 1 | 2024-12-04 | 2024-12-12 | 2025-06-28 | 2025-07-31
| JDH3-02-008RWTPR928 | Delivery for Backfilling Materials - PR-WT-Z02-2 | 1 | 2024-12-13 | 2024-12-21 | 2025-01-07 | 2025-03-19
| JDH3-02-008RWTPR929 | Delivery for Isolation Materials - PR-WT-Z02-2 | 1 | 2024-12-22 | 2024-12-30 | 2025-06-28 | 2025-07-31
| JDH3-02-008RWTPR930 | Delivery for GRP pipes - PR-WT-Z02-2 | 1 | 2024-12-31 | 2025-01-08 | 2025-06-28 | 2025-07-31
| JDH3-02-008RWTPR931 | Delivery for HDPE pipes - PR-WT-Z02-2 | 1 | 2025-01-09 | 2025-01-17 | 2025-01-01 | 2025-03-13
| JDH3-02-008RWTPR932 | Delivery for DI pipes - PR-WT-Z02-2 | 1 | 2025-01-18 | 2025-01-26 | 2025-06-28 | 2025-07-31
| JDH3-02-008RWTPR933 | Delivery for Bolts and Rubber Gasket - PR-WT-Z02-2 | 1 | 2025-01-27 | 2025-02-04 | 2025-06-28 | 2025-07-31
| JDH3-02-008RWTPR934 | Delivery for Valves (Aira & Gate) - PR-WT-Z02-2 | 1 | 2025-02-05 | 2025-02-13 | 2025-05-01 | 2025-07-11
| JDH3-02-008RWTPR935 | Delivery for Metal Works (Stairs - Covers) - PR-WT-Z02-2 | 1 | 2025-02-14 | 2025-02-22 | 2025-06-28 | 2025-07-31
| JDH3-02-008RZ01MI29 | Start of Zone 01 - MI-Z01 | 1 | 2024-07-30 |  | 2024-12-05
| JDH3-02-008RZ01SD208 | Review and Approval for Storm Water Network for -Z01-SD-ST | 1 | 2024-08-13 | 2024-08-26 | 2024-10-21 | 2025-02-09
| JDH3-02-008RZ01SD210 | Review and Approval for TSE (IRRIGATION) Network for -Z01-SD-TSE | 1 | 2024-08-06 | 2024-08-19 | 2024-10-31 | 2025-02-19
| JDH3-02-008RZ01SD327 | Prepare and Submit Drawing for Potable Water Network for -Z01-SD-WT | 1 | 2024-07-30 | 2024-08-06 | 2024-09-25 | 2025-04-17
| JDH3-02-008RZ01SD337 | Review and Approva for Potable Water Network for -Z01-SD-WT | 1 | 2024-08-07 | 2024-08-15 | 2024-09-25 | 2025-07-31
| JDH3-02-008RZ01SD93 | Prepare and Submit Drawing for Storm Water Network for -Z01-SD-ST | 1 | 2024-07-30 | 2024-08-12 | 2024-10-10 | 2025-01-29
| JDH3-02-008RZ01SD95 | Prepare and Submit Drawing for TSE (IRRIGATION) Network for -Z01-SD-TSE | 1 | 2024-07-30 | 2024-08-05 | 2024-10-20 | 2024-12-14
| JDH3-02-008RZ02-1FT1339 | Final Testing And Commissioning for Sewage Network - FT-Z02-1-SS | 1 | 2025-08-14 | 2025-08-18
| JDH3-02-008RZ02-1FT1340 | Final Testing And Commissioning for Storm Network - FT-Z02-1-ST | 1 | 2025-08-14 | 2025-08-18
| JDH3-02-008RZ02-1FT1341 | Final Testing And Commissioning for Potable Water - FT-Z02-1-WT | 1 | 2025-08-14 | 2025-08-18
| JDH3-02-008RZ02-1FT1342 | Final Testing And Commissioning for TSE (IRRIGATION) Network - FT-Z02-1-TSE | 1 | 2025-08-14 | 2025-08-18
| JDH3-02-008RZ02-1FT1344 | Final Testing And Commissioning for Street Lighting Network - FT-Z02-1-SL | 1 | 2025-08-14 | 2025-08-18
| JDH3-02-008RZ02-1FT1345 | Final Testing And Commissioning for Telecommunications Network - FT-Z02-1-TC | 1 | 2025-08-14 | 2025-08-18
| JDH3-02-008RZ02-1MI33 | Start of Zone 02-1 - MI-Z02-1 | 1 | 2024-07-30 |  | 2025-03-09
| JDH3-02-008RZ02-1MI34 | Finish for Zone 02-1 - MI-Z02-1 | 1 |  | 2025-05-11
| JDH3-02-008RZ02-1SD109 | Prepare and Submit Drawing for Sewage Network for -Z02-1-SD-SS | 1 | 2024-07-30 | 2024-08-05 | 2024-09-16 | 2024-11-11
| JDH3-02-008RZ02-1SD110 | Prepare and Submit Drawing for Storm Network - Pipes for -Z02-1-SD-ST | 1 | 2024-07-30 | 2024-08-12 | 2024-10-10 | 2025-01-29
| JDH3-02-008RZ02-1SD111 | Prepare and Submit Drawing for Potable Water Network for -Z02-1-SD-WT | 1 | 2024-07-30 | 2024-08-05 | 2024-09-25 | 2024-11-19
| JDH3-02-008RZ02-1SD112 | Prepare and Submit Drawing for TSE (IRRIGATION) Network for -Z02-1-SD-TSE | 1 | 2024-07-30 | 2024-08-05 | 2024-10-20 | 2024-12-14
| JDH3-02-008RZ02-1SD114 | Prepare and Submit Drawing for Street Lighting Network for -Z02-1-SD-SL | 1 | 2024-07-30 | 2024-08-05 | 2024-10-15 | 2024-12-09
| JDH3-02-008RZ02-1SD115 | Prepare and Submit Drawing for Telecommunications Network for -Z02-1-SD-TC | 1 | 2024-07-30 | 2024-08-05 | 2024-10-15 | 2024-12-09
| JDH3-02-008RZ02-1SD224 | Review and Approval Drawing for Sewage Network for -Z02-1-SD-SS | 1 | 2024-08-06 | 2024-08-19 | 2024-09-30 | 2025-01-19
| JDH3-02-008RZ02-1SD225 | Review and Approval Drawing for Storm Network - Pipes for -Z02-1-SD-ST | 1 | 2024-08-13 | 2024-08-26 | 2024-10-21 | 2025-02-09
| JDH3-02-008RZ02-1SD226 | Review and Approval Drawing for Potable Water Network for -Z02-1-SD-WT | 1 | 2024-08-06 | 2024-08-19 | 2024-10-21 | 2025-02-09
| JDH3-02-008RZ02-1SD227 | Review and Approval Drawing for TSE (IRRIGATION) Network for -Z02-1-SD-TSE | 1 | 2024-08-06 | 2024-08-19 | 2024-10-31 | 2025-02-19
| JDH3-02-008RZ02-1SD229 | Review and Approval Drawing for Street Lighting Network for -Z02-1-SD-SL | 1 | 2024-08-06 | 2024-08-19 | 2024-10-25 | 2025-02-13
| JDH3-02-008RZ02-1SD230 | Review and Approval Drawing for Telecommunications Network for -Z02-1-SD-TC | 1 | 2024-08-06 | 2024-08-19 | 2024-10-23 | 2025-02-11
| JDH3-02-008RZ02-2FT1348 | Final Testing And Commissioning for Sewage Network - FT-Z02-2-SS | 1 | 2025-08-14 | 2025-08-18
| JDH3-02-008RZ02-2FT1349 | Final Testing And Commissioning for Storm Network - FT-Z02-2-ST | 1 | 2025-08-19 | 2025-08-23
| JDH3-02-008RZ02-2FT1350 | Final Testing And Commissioning for Potable Water - FT-Z02-2-WT | 1 | 2025-08-24 | 2025-08-27
| JDH3-02-008RZ02-2FT1351 | Final Testing And Commissioning for TSE (IRRIGATION) Network - FT-Z02-2-TSE | 1 | 2025-08-28 | 2025-09-01
| JDH3-02-008RZ02-2FT1353 | Final Testing And Commissioning for Street Lighting Network - FT-Z02-2-SL | 1 | 2025-09-02 | 2025-09-06
| JDH3-02-008RZ02-2FT1354 | Final Testing And Commissioning for Telecommunications Network - FT-Z02-2-TC | 1 | 2025-09-07 | 2025-09-10
| JDH3-02-008RZ02-2FT1355 | Final Testing And Commissioning for Road Network - FT-Z02-2-RD | 1 | 2025-09-11 | 2025-09-15
| JDH3-02-008RZ02-2MI35 | Start of Zone 02-2 - MI-Z02-2 | 1 | 2024-07-30 |  | 2025-01-01
| JDH3-02-008RZ02-2MI36 | Finish for Zone 02-2 - MI-Z02-2 | 1 |  | 2025-06-14
| JDH3-02-008RZ02-2SD119 | Prepare and Submit Drawing for Sewage Network for -Z02-2-SD-SS | 1 | 2024-07-30 | 2024-08-05 | 2024-11-01 | 2024-12-26
| JDH3-02-008RZ02-2SD120 | Prepare and Submit Drawing for Storm Network - Pipes for -Z02-2-SD-ST | 1 | 2024-07-30 | 2024-08-12 | 2024-10-30 | 2025-02-18
| JDH3-02-008RZ02-2SD121 | Prepare and Submit Drawing for Potable Water Network for -Z02-2-SD-WT | 1 | 2024-07-30 | 2024-08-05 | 2024-11-01 | 2024-12-26
| JDH3-02-008RZ02-2SD122 | Prepare and Submit Drawing for TSE (IRRIGATION) Network for -Z02-2-SD-TSE | 1 | 2024-07-30 | 2024-08-05 | 2024-10-30 | 2024-12-24
| JDH3-02-008RZ02-2SD124 | Prepare and Submit Drawing for Street Lighting Network for -Z02-2-SD-SL | 1 | 2024-07-30 | 2024-08-05 | 2024-11-01 | 2024-12-26
| JDH3-02-008RZ02-2SD125 | Prepare and Submit Drawing for Telecommunications Network for -Z02-2-SD-TC | 1 | 2024-07-30 | 2024-08-05 | 2024-11-01 | 2024-12-26
| JDH3-02-008RZ02-2SD126 | Prepare and Submit Drawing for Road Works( KERBING AND PAVEMENT ) for -Z02-2-SD-RD | 1 | 2024-07-30 | 2024-08-05 | 2024-11-01 | 2024-12-26
| JDH3-02-008RZ02-2SD127 | Prepare and Submit Drawing for Road Works ( TRAFFIC SIGN AND MARKING) for -Z02-2-SD-RD | 1 | 2024-07-30 | 2024-08-05 | 2024-11-01 | 2024-12-26
| JDH3-02-008RZ02-2SD234 | Review and Approval Drawing for Sewage Network for -Z02-2-SD-SS | 1 | 2024-08-06 | 2024-08-19 | 2024-11-28 | 2025-03-19
| JDH3-02-008RZ02-2SD235 | Review and Approval Drawing for Storm Network - Pipes for -Z02-2-SD-ST | 1 | 2024-08-13 | 2024-08-26 | 2024-11-06 | 2025-02-25
| JDH3-02-008RZ02-2SD236 | Review and Approval Drawing for Potable Water Network for -Z02-2-SD-WT | 1 | 2024-08-06 | 2024-08-19 | 2024-11-28 | 2025-03-19
| JDH3-02-008RZ02-2SD237 | Review and Approval Drawing for TSE (IRRIGATION) Network for -Z02-2-SD-TSE | 1 | 2024-08-06 | 2024-08-19 | 2024-11-12 | 2025-03-03
| JDH3-02-008RZ02-2SD239 | Review and Approval Drawing for Street Lighting Network for -Z02-2-SD-SL | 1 | 2024-08-06 | 2024-08-19 | 2024-11-28 | 2025-03-19
| JDH3-02-008RZ02-2SD240 | Review and Approval Drawing for Telecommunications Network for -Z02-2-SD-TC | 1 | 2024-08-06 | 2024-08-19 | 2024-11-28 | 2025-03-19
| JDH3-02-008RZ02-2SD241 | Review and Approval Drawing for Road Works( KERBING AND PAVEMENT ) for -Z02-2-SD-RD | 1 | 2024-08-06 | 2024-08-19 | 2024-11-28 | 2025-03-19
| JDH3-02-008RZ02-2SD242 | Review and Approval Drawing for Road Works ( TRAFFIC SIGN AND MARKING) for -Z02-2-SD-RD | 1 | 2024-08-06 | 2024-08-19 | 2024-11-28 | 2025-03-19
| JDH3-02-008RZ02MI31 | Start of Zone 02 - MI-Z02 | 1 | 2024-07-30 |  | 2025-01-08
| JDH3-02-008RZ02SD102 | Prepare and Submit Drawing for TSE (IRRIGATION) Network for -Z02-SD-TSE | 1 | 2024-07-30 | 2024-08-05 | 2024-10-20 | 2024-12-14
| JDH3-02-008RZ02SD217 | Review and Approval for TSE (IRRIGATION) Network for -Z02-SD-TSE | 1 | 2024-08-06 | 2024-08-19 | 2024-10-31 | 2025-02-19
| JDH3-02-008RZ02SD347 | Prepare and Submit Drawing for Storm Water Network for -Z02-SD-ST | 1 | 2024-07-30 | 2024-08-06 | 2024-10-10 | 2025-05-22
| JDH3-02-008RZ02SD357 | Review and Approval Drawing for Storm Water Network for -Z02-SD-ST | 1 | 2024-08-07 | 2024-08-15 | 2024-10-10 | 2025-07-31
| JDH3-02-008RZ03MI37 | Start of Zone 03 - MI-Z03 | 1 | 2024-07-30 |  | 2024-12-05
| JDH3-02-008RZ03SD129 | Prepare and Submit Drawing for TSE (IRRIGATION) Network for -Z03-SD-TSE | 1 | 2024-07-30 | 2024-08-05 | 2024-10-20 | 2024-12-14
| JDH3-02-008RZ03SD244 | Review and Approval for TSE (IRRIGATION) Network for -Z03-SD-TSE | 1 | 2024-08-06 | 2024-08-19 | 2024-10-31 | 2025-02-19
| JDH3-02-008RZ04MI39 | Start of Zone 04 - MI-Z04 | 1 | 2024-07-30 |  | 2025-04-20
| JDH3-02-008RZ04SD133 | Prepare and Submit Drawing for TSE (IRRIGATION) Network for -Z04-SD-TSE | 1 | 2024-07-30 | 2024-08-05 | 2024-10-20 | 2024-12-14
| JDH3-02-008RZ04SD134 | Prepare and Submit Drawing for Storm Network - Pipes for -Z04-SD-ST | 1 | 2024-07-30 | 2024-08-05 | 2024-10-02 | 2024-11-26
| JDH3-02-008RZ04SD248 | Review and Approval for TSE (IRRIGATION) Network for -Z04-SD-TSE | 1 | 2024-08-06 | 2024-08-19 | 2024-10-31 | 2025-02-19
| JDH3-02-008RZ04SD259 | Review and Approval for Storm Network - Pipes for -Z04-SD-ST | 1 | 2024-08-06 | 2024-08-14 | 2024-10-30 | 2025-07-31
| JDH3-02-008RZ05MI41 | Start of Zone 05 - MI-Z05 | 1 | 2024-07-30 |  | 2025-01-01
| JDH3-02-008RZ05SD137 | Prepare and Submit Drawing for TSE (IRRIGATION) Network for -Z05-SD-TSE | 1 | 2024-07-30 | 2024-08-05 | 2024-10-20 | 2024-12-14
| JDH3-02-008RZ05SD252 | Review and Approval for TSE (IRRIGATION) Network for -Z05-SD-TSE | 1 | 2024-08-06 | 2024-08-19 | 2024-10-31 | 2025-02-19
| JDH3-02-008RZ05SD269 | Prepare and Submit Drawing for Storm Network - Pipes for -Z05-SD-ST | 1 | 2024-07-30 | 2024-08-06 | 2024-10-30 | 2025-05-21
| JDH3-02-008RZ05SD279 | Review and Approval for Storm Network - Pipes for -Z05-SD-ST | 1 | 2024-08-07 | 2024-08-15 | 2024-10-30 | 2025-07-31
| JDH3-02-008RZ06MI43 | Start of Zone 06 - MI-Z06 | 1 | 2024-07-30 |  | 2024-11-26
| JDH3-02-008RZ06SD141 | Prepare and Submit Drawing for Storm Network - Pipes for -Z06-SD-ST | 1 | 2024-07-30 | 2024-08-12 | 2024-10-10 | 2025-01-29
| JDH3-02-008RZ06SD142 | Prepare and Submit Drawing for Fire Hydrant Network for -Z06-SD-WT | 1 | 2024-07-30 | 2024-08-05 | 2024-09-25 | 2024-11-19
| JDH3-02-008RZ06SD143 | Prepare and Submit Drawing for TSE (IRRIGATION) Network for -Z06-SD-TSE | 1 | 2024-07-30 | 2024-08-05 | 2024-10-20 | 2024-12-14
| JDH3-02-008RZ06SD256 | Review and Approval for Storm Network - Pipes for -Z06-SD-ST | 1 | 2024-08-13 | 2024-08-26 | 2024-10-21 | 2025-02-09
| JDH3-02-008RZ06SD257 | Review and Approval for Fire Hydrant Network for -Z06-SD-WT | 1 | 2024-08-06 | 2024-08-19 | 2024-10-21 | 2025-02-09
| JDH3-02-008RZ06SD258 | Review and Approval for TSE (IRRIGATION) Network for -Z06-SD-TSE | 1 | 2024-08-06 | 2024-08-19 | 2024-10-31 | 2025-02-19
| JDH3-02-008RZ07-1FT1380 | Final Testing And Commissioning for Sewage Network - FT-Z07-1-SS | 1 | 2025-08-14 | 2025-08-18
| JDH3-02-008RZ07-1FT1381 | Final Testing And Commissioning for Storm Network - FT-Z07-1-ST | 1 | 2025-08-14 | 2025-08-18
| JDH3-02-008RZ07-1FT1382 | Final Testing And Commissioning for Potable Water - FT-Z07-1-WT | 1 | 2025-08-14 | 2025-08-18
| JDH3-02-008RZ07-1FT1383 | Final Testing And Commissioning for TSE (IRRIGATION) Network - FT-Z07-1-TSE | 1 | 2025-08-14 | 2025-08-18
| JDH3-02-008RZ07-1FT1385 | Final Testing And Commissioning for Street Lighting Network - FT-Z07-1-SL | 1 | 2025-08-14 | 2025-08-18
| JDH3-02-008RZ07-1FT1386 | Final Testing And Commissioning for Telecommunications Network - FT-Z07-1-TC | 1 | 2025-08-14 | 2025-08-18
| JDH3-02-008RZ07-1MI47 | Start of Zone 07-1 - MI-Z07-1 | 1 | 2024-07-30 |  | 2024-11-26
| JDH3-02-008RZ07-1MI48 | Finish for Zone 07-1 - MI-Z07-1 | 1 |  | 2025-02-23
| JDH3-02-008RZ07-1SD159 | Prepare and Submit Drawing for Sewage Network for -Z07-1-SD-SS | 1 | 2024-07-30 | 2024-08-05 | 2024-09-16 | 2024-11-11
| JDH3-02-008RZ07-1SD160 | Prepare and Submit Drawing for Storm Network - Pipes for -Z07-1-SD-ST | 1 | 2024-07-30 | 2024-08-12 | 2024-10-10 | 2025-01-29
| JDH3-02-008RZ07-1SD161 | Prepare and Submit Drawing for Storm Network - Collecting Lakes (PONDS) for -Z07-1-SD-ST | 1 | 2024-07-30 | 2024-08-05 | 2024-09-16 | 2024-11-11
| JDH3-02-008RZ07-1SD162 | Prepare and Submit Drawing for Potable Water Network for -Z07-1-SD-WT | 1 | 2024-07-30 | 2024-08-05 | 2024-09-25 | 2024-11-19
| JDH3-02-008RZ07-1SD163 | Prepare and Submit Drawing for Fire Hydrant Network for -Z07-1-SD-WT | 1 | 2024-07-30 | 2024-08-05 | 2024-09-25 | 2024-11-19
| JDH3-02-008RZ07-1SD164 | Prepare and Submit Drawing for TSE (IRRIGATION) Network for -Z07-1-SD-TSE | 1 | 2024-07-30 | 2024-08-05 | 2024-10-20 | 2024-12-14
| JDH3-02-008RZ07-1SD166 | Prepare and Submit Drawing for Street Lighting Network for -Z07-1-SD-SL | 1 | 2024-07-30 | 2024-08-05 | 2024-10-15 | 2024-12-09
| JDH3-02-008RZ07-1SD167 | Prepare and Submit Drawing for Telecommunications Network for -Z07-1-SD-TC | 1 | 2024-07-30 | 2024-08-05 | 2024-10-15 | 2024-12-09
| JDH3-02-008RZ07-1SD274 | Review and Approval Drawing for Sewage Network for -Z07-1-SD-SS | 1 | 2024-08-06 | 2024-08-19 | 2024-09-30 | 2025-01-19
| JDH3-02-008RZ07-1SD275 | Review and Approval Drawing for Storm Network - Pipes for -Z07-1-SD-ST | 1 | 2024-08-13 | 2024-08-26 | 2024-10-21 | 2025-02-09
| JDH3-02-008RZ07-1SD276 | Review and Approval Drawing for Storm Network - Collecting Lakes (PONDS) for -Z07-1-SD-ST | 1 | 2024-08-06 | 2024-08-19 | 2024-09-17 | 2025-01-07
| JDH3-02-008RZ07-1SD277 | Review and Approval Drawing for Potable Water Network for -Z07-1-SD-WT | 1 | 2024-08-06 | 2024-08-19 | 2024-10-21 | 2025-02-09
| JDH3-02-008RZ07-1SD278 | Review and Approval Drawing for Fire Hydrant Network for -Z07-1-SD-WT | 1 | 2024-08-06 | 2024-08-19 | 2024-10-21 | 2025-02-09
| JDH3-02-008RZ07-1SD279 | Review and Approval Drawing for TSE (IRRIGATION) Network for -Z07-1-SD-TSE | 1 | 2024-08-06 | 2024-08-19 | 2024-10-31 | 2025-02-19
| JDH3-02-008RZ07-1SD281 | Review and Approval Drawing for Street Lighting Network for -Z07-1-SD-SL | 1 | 2024-08-06 | 2024-08-19 | 2024-10-25 | 2025-02-13
| JDH3-02-008RZ07-1SD282 | Review and Approval Drawing for Telecommunications Network for -Z07-1-SD-TC | 1 | 2024-08-06 | 2024-08-19 | 2024-10-23 | 2025-02-11
| JDH3-02-008RZ07MI45 | Start of Zone 07 - MI-Z07 | 1 | 2024-07-30 |  | 2024-11-23
| JDH3-02-008RZ07SD148 | Prepare and Submit Drawing for Storm Network - Pipes for -Z07-SD-ST | 1 | 2024-07-30 | 2024-08-12 | 2024-10-10 | 2025-01-29
| JDH3-02-008RZ07SD149 | Prepare and Submit Drawing for Storm Network - Collecting Lakes (PONDS) for -Z07-SD-ST | 1 | 2024-07-30 | 2024-08-05 | 2024-09-16 | 2024-11-11
| JDH3-02-008RZ07SD151 | Prepare and Submit Drawing for Fire Hydrant Network for -Z07-SD-WT | 1 | 2024-07-30 | 2024-08-05 | 2024-09-25 | 2024-11-19
| JDH3-02-008RZ07SD152 | Prepare and Submit Drawing for TSE (IRRIGATION) Network for -Z07-SD-TSE | 1 | 2024-07-30 | 2024-08-05 | 2024-10-20 | 2024-12-14
| JDH3-02-008RZ07SD263 | Review and Approval for Storm Network - Pipes for -Z07-SD-ST | 1 | 2024-08-13 | 2024-08-26 | 2024-10-21 | 2025-02-09
| JDH3-02-008RZ07SD264 | Review and Approval for Storm Network - Collecting Lakes (PONDS) for -Z07-SD-ST | 1 | 2024-08-06 | 2024-08-19 | 2024-09-17 | 2025-01-07
| JDH3-02-008RZ07SD266 | Review and Approval for Fire Hydrant Network for -Z07-SD-WT | 1 | 2024-08-06 | 2024-08-19 | 2024-10-21 | 2025-02-09
| JDH3-02-008RZ07SD267 | Review and Approval for TSE (IRRIGATION) Network for -Z07-SD-TSE | 1 | 2024-08-06 | 2024-08-19 | 2024-10-31 | 2025-02-19
| JDH3-02-008RZ08MI49 | Start of Zone 08 - MI-Z08 | 1 | 2024-07-30 |  | 2025-01-16
| JDH3-02-008RZ08SD171 | Prepare and Submit Drawing for TSE (IRRIGATION) Network for -Z08-SD-TSE | 1 | 2024-07-30 | 2024-08-05 | 2024-10-20 | 2024-12-14
| JDH3-02-008RZ08SD173 | Prepare and Submit Drawing for Road Works( KERBING AND PAVEMENT ) for -Z08-SD-RD | 1 | 2024-07-30 | 2024-08-05 | 2024-10-02 | 2024-11-26
| JDH3-02-008RZ08SD277 | Prepare and Submit Drawing for Storm Network - Pipes for -Z08-SD-ST | 1 | 2024-07-30 | 2024-08-06 | 2024-10-10 | 2025-05-22
| JDH3-02-008RZ08SD286 | Review and Approval for TSE (IRRIGATION) Network for -Z08-SD-TSE | 1 | 2024-08-06 | 2024-08-19 | 2024-10-31 | 2025-02-19
| JDH3-02-008RZ08SD288 | Review and Approval for Road Works( KERBING AND PAVEMENT ) for -Z08-SD-RD | 1 | 2024-08-06 | 2024-08-19 | 2024-10-24 | 2025-02-12
| JDH3-02-008RZ08SD298 | Review and Approval for Storm Network - Pipes for -Z08-SD-ST | 1 | 2024-08-07 | 2024-08-15 | 2024-10-10 | 2025-07-31
| JDH3-02-008RZ09MI66 | Start of Zone 09 - MI-Z09 | 1 | 2024-07-30 |  | 2024-11-23
| JDH3-02-008RZ09SD12 | Review and Approval Drawing for Sewage Network for -Z09-SD-SS | 1 | 2024-08-07 | 2024-08-15 | 2024-11-01 | 2025-07-16
| JDH3-02-008RZ09SD2 | Prepare and Submit Drawing for Sewage Network for -Z09-SD-SS | 1 | 2024-07-30 | 2024-08-06 | 2024-11-01 | 2025-06-03
| JDH3-02-008RZ10MI86 | Start of Zone 10 - MI-Z10 | 1 | 2024-07-30 |  | 2024-11-23
| JDH3-02-008RZ10SD12 | Prepare and Submit Drawing for Sewage Network for -Z10-SD-SS | 1 | 2024-07-30 | 2024-08-06 | 2024-11-01 | 2025-06-03
| JDH3-02-008RZ10SD22 | Review and Approval Drawing for Sewage Network for -Z10-SD-SS | 1 | 2024-08-07 | 2024-08-15 | 2024-11-01 | 2025-07-16
| JDH3-02-008RZ11MI55 | Start of Zone 11 - MI-Z11 | 1 | 2024-07-30 |  | 2024-11-23
| JDH3-02-008RZ11SD183 | Prepare and Submit Drawing for Road Works( KERBING AND PAVEMENT ) for -Z11-SD-RD | 1 | 2024-07-30 | 2024-08-05 | 2024-10-02 | 2024-11-26
| JDH3-02-008RZ11SD287 | Prepare and Submit Drawing for Storm Network - Pipes for -Z11-SD-ST | 1 | 2024-07-30 | 2024-08-06 | 2024-10-10 | 2025-05-22
| JDH3-02-008RZ11SD298 | Review and Approval for Road Works( KERBING AND PAVEMENT ) for -Z11-SD-RD | 1 | 2024-08-06 | 2024-08-19 | 2024-10-24 | 2025-02-12
| JDH3-02-008RZ11SD308 | Review and Approval for Storm Network - Pipes for -Z11-SD-ST | 1 | 2024-08-07 | 2024-08-15 | 2024-10-10 | 2025-07-31
| JDH3-02-008RZ12MI57 | Start of Zone 12 - MI-Z12 | 1 | 2024-07-30 |  | 2025-03-24
| JDH3-02-008RZ13MI59 | Start of Zone 13 - MI-Z13 | 1 | 2024-07-30 |  | 2025-03-24

## EV-Chart Data
| Baseline Plan |  |  | Revised / Recovery Plan |  |  | Earned Value |  |  | Gross Paid Value |  |  | Forecast |  |  | Actual/Fcst vs Plan
Month | Monthly | Cum | % | Monthly | Cum | % | Monthly | Cum | % | Monthly | Cum | % | Monthly | C um | % | Month | Cum | %
2024-07-29 | 17143.23 | 17143.23 | 0.005362% | 0 | 0 | 0% | 0 | 0 | 0% | [6 empty] | 0 | 0 |  |  | Actuals thru previous month
2024-08-31 | 10048903.47 | 10066046.7 | 3.148% | 0 | 0 | 0% | 0 | 0 | 0% | [6 empty] | 0 | 0
2024-09-30 | 13175096.08 | 23241142.78 | 7.269% | 78036.41 | 78036.41 | 0.02441% | 78036.41 | 78036.41 | 0.02441% | [6 empty] | 78036.41 | 78036.41
2024-10-31 | 15369360.74 | 38610503.52 | 12.08% | 3386825.39 | 3464861.8 | 1.084% | 3386825.39 | 3464861.8 | 1.084% | [6 empty] | 3386825.39 | 3464861.8
2024-11-30 | 12926062.37 | 51536565.89 | 16.12% | 9710131.68 | 13174993.48 | 4.12% | 9710131.68 | 13174993.48 | 4.12% | [6 empty] | 9710131.68 | 13174993.48 |  |  | Forecast current and future months
2024-12-31 | 14903825.44 | 66440391.33 | 20.78% | 7669459.73 | 20844453.21 | 6.519% | 7669459.73 | 20844453.21 | 6.519% | [6 empty] | 7669459.73 | 20844453.21
2025-01-31 | 14626087.63 | 81066478.96 | 25.35% | 8415792.79 | 29260246 | 9.151% | 8415792.79 | 29260246 | 9.151% | [6 empty] | 8415792.79 | 29260246
2025-02-28 | 13992449.16 | 95058928.12 | 29.73% | 8496722.51 | 37756968.51 | 11.81% | 8496722.51 | 37756968.51 | 11.81% | [6 empty] | 8496722.51 | 37756968.51
2025-03-31 | 6401983.26 | 101460911.38 | 31.73% | 6490740.32 | 44247708.83 | 13.84% | 6490740.32 | 44247708.83 | 13.84% | [6 empty] | 6490740.32 | 44247708.83
2025-04-30 | 5434721.77 | 106895633.15 | 33.43% | 9927868.47 | 54175577.3 | 16.94% | 9927868.47 | 54175577.3 | 16.94% | [6 empty] | 9927868.47 | 54175577.3
2025-05-31 | 3355341.08 | 110250974.23 | 34.48% | 11539503.2 | 65715080.5 | 20.55% | 11539503.2 | 65715080.5 | 20.55% | [6 empty] | 11539503.2 | 65715080.5
2025-06-30 | 4784714.31 | 115035688.54 | 35.98% | 10881441.23 | 76596521.73 | 23.96% | 10881441.23 | 76596521.73 | 23.96% | [6 empty] | 10881441.23 | 76596521.73
2025-07-31 | 4339315.41 | 119375003.95 | 37.33% | 27187886.92 | 103784408.65 | 32.46% | 27187886.92 | 103784408.65 | 32.46% | [6 empty] | 27187886.92 | 103784408.65
2025-08-31 | 11178223.68 | 130553227.63 | 40.83% | 15347030.35 | 119131439 | 37.26% | 15347030.35 | 119131439 | 37.26% | [6 empty] | 15347030.35 | 119131439
2025-09-30 | 14424559.49 | 144977787.12 | 45.34% | 24607873.83 | 143739312.83 | 44.95% | 24607873.83 | 143739312.83 | 44.95% | [6 empty] | 24607873.83 | 143739312.83
2025-10-31 | 16171720.47 | 161149507.59 | 50.4% | 13672987.56 | 157412300.39 | 49.23% | 13672987.56 | 157412300.39 | 49.23% | [6 empty] | 13672987.56 | 157412300.39
2025-11-30 | 15780657.43 | 176930165.02 | 55.33% | 19950189.44 | 177362489.83 | 55.47% | 19950189.44 | 177362489.83 | 55.47% | [6 empty] | 19950189.44 | 177362489.83
2025-12-31 | 15019903.34 | 191950068.36 | 60.03% | 22454226.56 | 199816716.39 | 62.49% | 22454226.56 | 199816716.39 | 62.49% | [6 empty] | 22454226.56 | 199816716.39
2026-01-31 | 19315349.74 | 211265418.1 | 66.07% | 21985204.1 | 221801920.49 | 69.37% | 21985204.1 | 221801920.49 | 69.37% | [6 empty] | 21985204.1 | 221654613.61 |  |  |  | Extended Duration
2026-02-28 | 28765308.42 | 240030726.52 | 75.07% | 13503824.01 | 235305744.5 | 73.59% | 13503824.01 | 235305744.5 | 73.59% | [6 empty] | 13503824.01 | 235305744.5
2026-03-31 | 25134977.14 | 265165703.66 | 82.93% | 6203650.47 | 241509394.97 | 75.53% | 6203650.47 | 241509394.97 | 75.53% | [6 empty] | 6203650.47 | 241509394.97
2026-04-30 | 23471727.98 | 288637431.64 | 90.27% | 8981865.09 | 250491260.06 | 78.34% | 8981865.09 | 250491260.06 | 78.34% | [6 empty] | 8981865.09 | 250491260.06
2026-05-31 | 14953248.95 | 303590680.59 | 94.95% | 6168786.64 | 256660046.7 | 80.27% | 6168786.64 | 256660046.7 | 80.27% | [6 empty] | 6168786.64 | 256660046.7
2026-06-30 | 7812194.82 | 311402875.41 | 97.39% | 11521220.255 | 268181266.955 | 83.87% | 6441833.18 | 263101879.88 | 82.28% | [6 empty] | 6441833.18 | 263101879.88
2026-07-31 | 8342000.32 | 319744875.73 | 100% | 13358030.575 | 281539297.53 | 88.05% | 12339087.93 | 275440967.81 | 86.14% | [6 empty] | 12339087.93 | 275440967.81
2026-08-31 |  |  |  | 17703814.355 | 299243111.885 | 93.59% | 9345756.11 | 284786723.92 | 89.07% | [6 empty] | 9345756.11 | 284786723.92
2026-09-30 |  |  |  | 20501763.845 | 319744875.73 | 100% | 29245947.85 | 314032671.77 | 98.21% | [6 empty] | 29245947.85 | 314032671.77 | 98.21%
2026-10-31 | [12 empty] | 5712203.96 | 319744875.73 | 100% | 5712203.96 | 319744875.73 | 100%
2026-11-30
2026-12-31
2027-01-31
2027-02-28
2027-03-31
2027-04-30
2027-05-31
UPDATE ONLY YELLOW PORTION FROM PRIMAVERA EXPORT, IF NEEDED, EXTEND YELLOW PORTION BASED ON SCHEDULE.
|  |  | Activity ID | Activity Name | BL Project Start | BL Project Finish | Start | Finish | Earned Value Cost | Actual Total Cost | Budgeted Total Cost | Spreadsheet Field | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01
|  |  | Completion of the Infrastructure development of the 1st phase in the 3rd industrial city in Jeddah |  | 2024-07-30 | 2026-07-28 | 29-Jul-24 A | 46305 | 143739312.69 | 143739312.83 | 319744875.73 | Planned Total Cost | 1946-12-07 05:31 | 9998379.03 | 11596467.97 | 11189647.33 | 9291041.79 | 9075586.43 | 7518899.3 | 5832117.3 | 2745968.99 | 2309640.74 | 1569642.12 | 1565118.54 | 2335919.79 | 5951376.65 | 8358224.9 | 51156026.88 | 33640960.19 | 28103127.95 | 26403454.82 | 20799571.67 | 24158908.96 | 11289522.53 | 8287559.5 | 6477805.57 | 15099783.65 | 2847805.2 | 1542335.23 | 241047.97 |  |  | 2026-12-09 23:17 | 295425.52
|  |  | Completion of the Infrastructure development of the 1st phase in the 3rd industrial city in Jeddah |  | 2024-07-30 | 2026-07-28 | 29-Jul-24 A | 2026-10-10 | 143739312.69 | 143739312.83 | 319744875.73 | Remaining Total Cost | [15 empty] | 45831851.12 | 27868631.88 | 20442574.68 | 17522229.39 | 11896365.35 | 16074372.96 | 6339545.26 | 4349704.95 | 5949315.35 | 15099783.65 | 2847805.2 | 1542335.23 | 241047.97
|  |  | Completion of the Infrastructure development of the 1st phase in the 3rd industrial city in Jeddah |  | 2024-07-30 | 2026-07-28 | 29-Jul-24 A | 2026-10-10 | 143739312.69 | 143739312.83 | 319744875.73 | Actual Total Cost |  |  | 168070.69 | 1511642.24 | 3450840.11 | 8556983.41 | 11550048.13 | 10397280.85 | 10894272.44 | 12625778.28 | 15059632.09 | 15505659.12 | 15522302.02 | 21969815.88 | 15991106.73 | 535880.85
|  |  | JDH3-02-008--Milestones - MI |  | 2024-07-30 | 2026-07-28 | 29-Jul-24 A | 2026-10-10 | 0 | 0 | 0 | Planned Total Cost
|  |  | JDH3-02-008--Milestones - MI |  | 2024-07-30 | 2026-07-28 | 29-Jul-24 A | 2026-10-10 | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Milestones - MI |  | 2024-07-30 | 2026-07-28 | 29-Jul-24 A | 2026-10-10 | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Contractual Milestones |  | 2024-07-30 | 2026-07-28 | 29-Jul-24 A | 2026-10-10 | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Contractual Milestones |  | 2024-07-30 | 2026-07-28 | 29-Jul-24 A | 2026-10-10 | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Contractual Milestones |  | 2024-07-30 | 2026-07-28 | 29-Jul-24 A | 2026-10-10 | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Control Milestones |  | 2024-07-30 | 2026-07-09 | 21-Oct-24 A | 2026-07-20 | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Control Milestones |  | 2024-07-30 | 2026-07-09 | 21-Oct-24 A | 2026-07-20 | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Control Milestones |  | 2024-07-30 | 2026-07-09 | 21-Oct-24 A | 2026-07-20 | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Network Milestones |  | 2024-07-30 | 2026-07-05 | 21-Nov-24 A | 2026-06-27 | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Network Milestones |  | 2024-07-30 | 2026-07-05 | 21-Nov-24 A | 2026-06-27 | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Network Milestones |  | 2024-07-30 | 2026-07-05 | 21-Nov-24 A | 2026-06-27 | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Zones Millestones |  | 2024-07-30 | 2026-07-09 | 23-Nov-24 A | 2026-07-20 | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Zones Millestones |  | 2024-07-30 | 2026-07-09 | 23-Nov-24 A | 2026-07-20 | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Zones Millestones |  | 2024-07-30 | 2026-07-09 | 23-Nov-24 A | 2026-07-20 | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Mobilization - Mob |  | 2024-07-30 | 2024-09-04 | 29-Jul-24 A | 26-May-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Mobilization - Mob |  | 2024-07-30 | 2024-09-04 | 29-Jul-24 A | 26-May-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Mobilization - Mob |  | 2024-07-30 | 2024-09-04 | 29-Jul-24 A | 26-May-25 A | 0 | 0 | 0% | Actual Total Cost | [33 empty] | 2026-10-01
|  |  | JDH3-02-008--Site Facilities and Offices |  | 2024-07-30 | 2024-08-31 | 21-Aug-24 A | 26-May-25 A | 0 | 0 | 0% | Planned Total Cost | [33 empty] | 855.09
|  |  | JDH3-02-008--Site Facilities and Offices |  | 2024-07-30 | 2024-08-31 | 21-Aug-24 A | 26-May-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Site Facilities and Offices |  | 2024-07-30 | 2024-08-31 | 21-Aug-24 A | 26-May-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Preliminaries - PP |  | 2024-07-30 | 2024-09-04 | 29-Jul-24 A | 01-Feb-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Preliminaries - PP |  | 2024-07-30 | 2024-09-04 | 29-Jul-24 A | 01-Feb-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Preliminaries - PP |  | 2024-07-30 | 2024-09-04 | 29-Jul-24 A | 01-Feb-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Soil Investigation |  | 2024-07-30 | 2024-08-21 | 20-Aug-24 A | 16-Dec-24 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Soil Investigation |  | 2024-07-30 | 2024-08-21 | 20-Aug-24 A | 16-Dec-24 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Soil Investigation |  | 2024-07-30 | 2024-08-21 | 20-Aug-24 A | 16-Dec-24 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Land Surveying Works |  | 2024-07-30 | 2024-08-21 | 07-Aug-24 A | 11-Dec-24 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Land Surveying Works |  | 2024-07-30 | 2024-08-21 | 07-Aug-24 A | 11-Dec-24 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Land Surveying Works |  | 2024-07-30 | 2024-08-21 | 07-Aug-24 A | 11-Dec-24 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Shop Drawings Submission Plan |  | 2024-07-30 | 2024-08-21 | 28-Aug-24 A | 25-Dec-24 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Shop Drawings Submission Plan |  | 2024-07-30 | 2024-08-21 | 28-Aug-24 A | 25-Dec-24 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Shop Drawings Submission Plan |  | 2024-07-30 | 2024-08-21 | 28-Aug-24 A | 25-Dec-24 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Material submittal plan |  | 2024-07-30 | 2024-08-21 | 15-Aug-24 A | 16-Dec-24 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Material submittal plan |  | 2024-07-30 | 2024-08-21 | 15-Aug-24 A | 16-Dec-24 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Material submittal plan |  | 2024-07-30 | 2024-08-21 | 15-Aug-24 A | 16-Dec-24 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Project Schedule |  | 2024-07-30 | 2024-09-01 | 29-Jul-24 A | 04-Jan-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Project Schedule |  | 2024-07-30 | 2024-09-01 | 29-Jul-24 A | 04-Jan-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Project Schedule |  | 2024-07-30 | 2024-09-01 | 29-Jul-24 A | 04-Jan-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--HSE (Health, Safety & Environment) Plan |  | 2024-07-30 | 2024-08-20 | 18-Sep-24 A | 12-Jan-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--HSE (Health, Safety & Environment) Plan |  | 2024-07-30 | 2024-08-20 | 18-Sep-24 A | 12-Jan-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--HSE (Health, Safety & Environment) Plan |  | 2024-07-30 | 2024-08-20 | 18-Sep-24 A | 12-Jan-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Logistic Plan-Site Mobilization Plan |  | 2024-07-30 | 2024-08-21 | 02-Sep-24 A | 26-Jan-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Logistic Plan-Site Mobilization Plan |  | 2024-07-30 | 2024-08-21 | 02-Sep-24 A | 26-Jan-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Logistic Plan-Site Mobilization Plan |  | 2024-07-30 | 2024-08-21 | 02-Sep-24 A | 26-Jan-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Organization chart and Recruitment plan |  | 2024-07-30 | 2024-08-19 | 14-Aug-24 A | 18-Dec-24 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Organization chart and Recruitment plan |  | 2024-07-30 | 2024-08-19 | 14-Aug-24 A | 18-Dec-24 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Organization chart and Recruitment plan |  | 2024-07-30 | 2024-08-19 | 14-Aug-24 A | 18-Dec-24 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Project management plans |  | 2024-07-30 | 2024-09-04 | 29-Jul-24 A | 01-Feb-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Project management plans |  | 2024-07-30 | 2024-09-04 | 29-Jul-24 A | 01-Feb-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Project management plans |  | 2024-07-30 | 2024-09-04 | 29-Jul-24 A | 01-Feb-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Authorities Permits & Approval - AT |  | 2024-09-05 | 2024-09-10 | 21-Oct-24 A | 03-Dec-24 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Authorities Permits & Approval - AT |  | 2024-09-05 | 2024-09-10 | 21-Oct-24 A | 03-Dec-24 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Authorities Permits & Approval - AT |  | 2024-09-05 | 2024-09-10 | 21-Oct-24 A | 03-Dec-24 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Engineering |  | 2024-07-30 | 2024-09-22 | 05-Aug-24 A | 31-Jul-25 A | 9592346.27 | 9592346.27 | 959234627% | Planned Total Cost | 1714323% | 9366048.29 | 209154.76
|  |  | JDH3-02-008--Engineering |  | 2024-07-30 | 2024-09-22 | 05-Aug-24 A | 31-Jul-25 A | 9592346.27 | 9592346.27 | 959234627% | Remaining Total Cost
|  |  | JDH3-02-008--Engineering |  | 2024-07-30 | 2024-09-22 | 05-Aug-24 A | 31-Jul-25 A | 9592346.27 | 9592346.27 | 959234627% | Actual Total Cost |  |  | 157563.09 | 110521905% | 165901981% | 287276817% | 2055965.35 | 1143616.22 | 257613.93 | 90911.25 | 85453.63 | 58513.39 | 105702.38
|  |  | JDH3-02-008--Shop Drawings - SD |  | 2024-07-30 | 2024-09-10 | 05-Aug-24 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Shop Drawings - SD |  | 2024-07-30 | 2024-09-10 | 05-Aug-24 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Shop Drawings - SD |  | 2024-07-30 | 2024-09-10 | 05-Aug-24 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Shop Drawing Submittals |  | 2024-07-30 | 2024-08-22 | 05-Aug-24 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Shop Drawing Submittals |  | 2024-07-30 | 2024-08-22 | 05-Aug-24 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Shop Drawing Submittals |  | 2024-07-30 | 2024-08-22 | 05-Aug-24 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-MR |  | 2024-07-30 | 2024-08-12 | 16-Sep-24 A | 29-Jan-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-MR |  | 2024-07-30 | 2024-08-12 | 16-Sep-24 A | 29-Jan-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-MR |  | 2024-07-30 | 2024-08-12 | 16-Sep-24 A | 29-Jan-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z01 |  | 2024-07-30 | 2024-08-12 | 25-Sep-24 A | 17-Apr-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z01 |  | 2024-07-30 | 2024-08-12 | 25-Sep-24 A | 17-Apr-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z01 |  | 2024-07-30 | 2024-08-12 | 25-Sep-24 A | 17-Apr-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z02 |  | 2024-07-30 | 2024-08-06 | 10-Oct-24 A | 22-May-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z02 |  | 2024-07-30 | 2024-08-06 | 10-Oct-24 A | 22-May-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z02 |  | 2024-07-30 | 2024-08-06 | 10-Oct-24 A | 22-May-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z02-1 |  | 2024-07-30 | 2024-08-12 | 16-Sep-24 A | 29-Jan-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z02-1 |  | 2024-07-30 | 2024-08-12 | 16-Sep-24 A | 29-Jan-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z02-1 |  | 2024-07-30 | 2024-08-12 | 16-Sep-24 A | 29-Jan-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z02-2 |  | 2024-07-30 | 2024-08-12 | 30-Oct-24 A | 18-Feb-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z02-2 |  | 2024-07-30 | 2024-08-12 | 30-Oct-24 A | 18-Feb-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z02-2 |  | 2024-07-30 | 2024-08-12 | 30-Oct-24 A | 18-Feb-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z03 |  | 2024-07-30 | 2024-08-05 | 20-Oct-24 A | 14-Dec-24 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z03 |  | 2024-07-30 | 2024-08-05 | 20-Oct-24 A | 14-Dec-24 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z03 |  | 2024-07-30 | 2024-08-05 | 20-Oct-24 A | 14-Dec-24 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z04 |  | 2024-07-30 | 2024-08-05 | 02-Oct-24 A | 14-Dec-24 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z04 |  | 2024-07-30 | 2024-08-05 | 02-Oct-24 A | 14-Dec-24 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z04 |  | 2024-07-30 | 2024-08-05 | 02-Oct-24 A | 14-Dec-24 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z05 |  | 2024-07-30 | 2024-08-06 | 20-Oct-24 A | 21-May-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z05 |  | 2024-07-30 | 2024-08-06 | 20-Oct-24 A | 21-May-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z05 |  | 2024-07-30 | 2024-08-06 | 20-Oct-24 A | 21-May-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z06 |  | 2024-07-30 | 2024-08-12 | 25-Sep-24 A | 29-Jan-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z06 |  | 2024-07-30 | 2024-08-12 | 25-Sep-24 A | 29-Jan-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z06 |  | 2024-07-30 | 2024-08-12 | 25-Sep-24 A | 29-Jan-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z07 |  | 2024-07-30 | 2024-08-12 | 25-Sep-24 A | 29-Jan-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z07 |  | 2024-07-30 | 2024-08-12 | 25-Sep-24 A | 29-Jan-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z07 |  | 2024-07-30 | 2024-08-12 | 25-Sep-24 A | 29-Jan-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z07-1 |  | 2024-07-30 | 2024-08-12 | 16-Sep-24 A | 29-Jan-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z07-1 |  | 2024-07-30 | 2024-08-12 | 16-Sep-24 A | 29-Jan-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z07-1 |  | 2024-07-30 | 2024-08-12 | 16-Sep-24 A | 29-Jan-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z08 |  | 2024-07-30 | 2024-08-06 | 02-Oct-24 A | 22-May-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z08 |  | 2024-07-30 | 2024-08-06 | 02-Oct-24 A | 22-May-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z08 |  | 2024-07-30 | 2024-08-06 | 02-Oct-24 A | 22-May-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z09 |  | 2024-07-30 | 2024-08-06 | 01-Nov-24 A | 03-Jun-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z09 |  | 2024-07-30 | 2024-08-06 | 01-Nov-24 A | 03-Jun-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z09 |  | 2024-07-30 | 2024-08-06 | 01-Nov-24 A | 03-Jun-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z10 |  | 2024-07-30 | 2024-08-06 | 01-Nov-24 A | 03-Jun-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z10 |  | 2024-07-30 | 2024-08-06 | 01-Nov-24 A | 03-Jun-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z10 |  | 2024-07-30 | 2024-08-06 | 01-Nov-24 A | 03-Jun-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z11 |  | 2024-07-30 | 2024-08-06 | 02-Oct-24 A | 22-May-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z11 |  | 2024-07-30 | 2024-08-06 | 02-Oct-24 A | 22-May-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z11 |  | 2024-07-30 | 2024-08-06 | 02-Oct-24 A | 22-May-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-New Scope |  | 2024-07-30 | 2024-08-22 | 30-Oct-24 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-New Scope |  | 2024-07-30 | 2024-08-22 | 30-Oct-24 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-New Scope |  | 2024-07-30 | 2024-08-22 | 30-Oct-24 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | Swales |  | 2024-07-30 | 2024-08-18 | 01-Apr-25 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | Swales |  | 2024-07-30 | 2024-08-18 | 01-Apr-25 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | Swales |  | 2024-07-30 | 2024-08-18 | 01-Apr-25 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | Ponds |  | 2024-07-30 | 2024-08-22 | 01-Mar-25 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | Ponds |  | 2024-07-30 | 2024-08-22 | 01-Mar-25 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | Ponds |  | 2024-07-30 | 2024-08-22 | 01-Mar-25 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | Road Works |  | 2024-07-30 | 2024-08-06 | 04-Jan-25 A | 10-Feb-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | Road Works |  | 2024-07-30 | 2024-08-06 | 04-Jan-25 A | 10-Feb-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | Road Works |  | 2024-07-30 | 2024-08-06 | 04-Jan-25 A | 10-Feb-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | Transfer Lighting poles |  | 2024-07-30 | 2024-08-04 | 15-Apr-25 A | 31-May-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | Transfer Lighting poles |  | 2024-07-30 | 2024-08-04 | 15-Apr-25 A | 31-May-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | Transfer Lighting poles |  | 2024-07-30 | 2024-08-04 | 15-Apr-25 A | 31-May-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | Connection Z13-C10 |  | 2024-07-30 | 2024-08-18 | 20-Jan-25 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | Connection Z13-C10 |  | 2024-07-30 | 2024-08-18 | 20-Jan-25 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | Connection Z13-C10 |  | 2024-07-30 | 2024-08-18 | 20-Jan-25 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | Roundabout Catchbasin |  | 2024-07-30 | 2024-08-14 | 30-Oct-24 A | 15-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | Roundabout Catchbasin |  | 2024-07-30 | 2024-08-14 | 30-Oct-24 A | 15-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | Roundabout Catchbasin |  | 2024-07-30 | 2024-08-14 | 30-Oct-24 A | 15-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | Storm network for New Roads (MR1-MR2) |  | 2024-07-30 | 2024-08-18 | 01-Mar-25 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | Storm network for New Roads (MR1-MR2) |  | 2024-07-30 | 2024-08-18 | 01-Mar-25 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | Storm network for New Roads (MR1-MR2) |  | 2024-07-30 | 2024-08-18 | 01-Mar-25 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | Box Culvert |  | 2024-07-30 | 2024-08-11 | 01-Jun-25 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | Box Culvert |  | 2024-07-30 | 2024-08-11 | 01-Jun-25 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | Box Culvert |  | 2024-07-30 | 2024-08-11 | 01-Jun-25 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | CCTV System |  | 2024-07-30 | 2024-08-05 | 02-May-25 A | 26-Jun-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | CCTV System |  | 2024-07-30 | 2024-08-05 | 02-May-25 A | 26-Jun-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | CCTV System |  | 2024-07-30 | 2024-08-05 | 02-May-25 A | 26-Jun-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Shop Drawing Approvals |  | 2024-08-05 | 2024-09-10 | 25-Aug-24 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Shop Drawing Approvals |  | 2024-08-05 | 2024-09-10 | 25-Aug-24 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Shop Drawing Approvals |  | 2024-08-05 | 2024-09-10 | 25-Aug-24 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z01 |  | 2024-08-06 | 2024-08-26 | 25-Sep-24 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z01 |  | 2024-08-06 | 2024-08-26 | 25-Sep-24 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z01 |  | 2024-08-06 | 2024-08-26 | 25-Sep-24 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z02 |  | 2024-08-06 | 2024-08-19 | 10-Oct-24 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z02 |  | 2024-08-06 | 2024-08-19 | 10-Oct-24 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z02 |  | 2024-08-06 | 2024-08-19 | 10-Oct-24 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-MR |  | 2024-08-06 | 2024-08-26 | 30-Sep-24 A | 19-Feb-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-MR |  | 2024-08-06 | 2024-08-26 | 30-Sep-24 A | 19-Feb-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-MR |  | 2024-08-06 | 2024-08-26 | 30-Sep-24 A | 19-Feb-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z02-1 |  | 2024-08-06 | 2024-08-26 | 30-Sep-24 A | 19-Feb-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z02-1 |  | 2024-08-06 | 2024-08-26 | 30-Sep-24 A | 19-Feb-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z02-1 |  | 2024-08-06 | 2024-08-26 | 30-Sep-24 A | 19-Feb-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z02-2 |  | 2024-08-06 | 2024-08-26 | 06-Nov-24 A | 19-Mar-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z02-2 |  | 2024-08-06 | 2024-08-26 | 06-Nov-24 A | 19-Mar-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z02-2 |  | 2024-08-06 | 2024-08-26 | 06-Nov-24 A | 19-Mar-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z03 |  | 2024-08-06 | 2024-08-19 | 31-Oct-24 A | 19-Feb-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z03 |  | 2024-08-06 | 2024-08-19 | 31-Oct-24 A | 19-Feb-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z03 |  | 2024-08-06 | 2024-08-19 | 31-Oct-24 A | 19-Feb-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z04 |  | 2024-08-06 | 2024-08-19 | 30-Oct-24 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z04 |  | 2024-08-06 | 2024-08-19 | 30-Oct-24 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z04 |  | 2024-08-06 | 2024-08-19 | 30-Oct-24 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z05 |  | 2024-08-06 | 2024-08-19 | 30-Oct-24 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z05 |  | 2024-08-06 | 2024-08-19 | 30-Oct-24 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z05 |  | 2024-08-06 | 2024-08-19 | 30-Oct-24 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z06 |  | 2024-08-06 | 2024-08-26 | 21-Oct-24 A | 19-Feb-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z06 |  | 2024-08-06 | 2024-08-26 | 21-Oct-24 A | 19-Feb-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z06 |  | 2024-08-06 | 2024-08-26 | 21-Oct-24 A | 19-Feb-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z07 |  | 2024-08-06 | 2024-08-26 | 21-Oct-24 A | 19-Feb-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z07 |  | 2024-08-06 | 2024-08-26 | 21-Oct-24 A | 19-Feb-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z07 |  | 2024-08-06 | 2024-08-26 | 21-Oct-24 A | 19-Feb-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z07-1 |  | 2024-08-06 | 2024-08-26 | 30-Sep-24 A | 19-Feb-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z07-1 |  | 2024-08-06 | 2024-08-26 | 30-Sep-24 A | 19-Feb-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z07-1 |  | 2024-08-06 | 2024-08-26 | 30-Sep-24 A | 19-Feb-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z08 |  | 2024-08-06 | 2024-08-19 | 10-Oct-24 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z08 |  | 2024-08-06 | 2024-08-19 | 10-Oct-24 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z08 |  | 2024-08-06 | 2024-08-19 | 10-Oct-24 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z09 |  | 2024-08-07 | 2024-08-15 | 01-Nov-24 A | 16-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z09 |  | 2024-08-07 | 2024-08-15 | 01-Nov-24 A | 16-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z09 |  | 2024-08-07 | 2024-08-15 | 01-Nov-24 A | 16-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z10 |  | 2024-08-07 | 2024-08-15 | 01-Nov-24 A | 16-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z10 |  | 2024-08-07 | 2024-08-15 | 01-Nov-24 A | 16-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-Z10 |  | 2024-08-07 | 2024-08-15 | 01-Nov-24 A | 16-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z11 |  | 2024-08-06 | 2024-08-19 | 10-Oct-24 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z11 |  | 2024-08-06 | 2024-08-19 | 10-Oct-24 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Approvals-Z11 |  | 2024-08-06 | 2024-08-19 | 10-Oct-24 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-New Scope |  | 2024-08-05 | 2024-09-10 | 16-Nov-24 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-New Scope |  | 2024-08-05 | 2024-09-10 | 16-Nov-24 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Shop Drawing Submittals-New Scope |  | 2024-08-05 | 2024-09-10 | 16-Nov-24 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | Swales |  | 2024-08-19 | 2024-09-09 | 09-Apr-25 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | Swales |  | 2024-08-19 | 2024-09-09 | 09-Apr-25 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | Swales |  | 2024-08-19 | 2024-09-09 | 09-Apr-25 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | Ponds |  | 2024-08-07 | 2024-09-10 | 13-Mar-25 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | Ponds |  | 2024-08-07 | 2024-09-10 | 13-Mar-25 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | Ponds |  | 2024-08-07 | 2024-09-10 | 13-Mar-25 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | Road Works |  | 2024-08-07 | 2024-08-15 | 13-Jan-25 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | Road Works |  | 2024-08-07 | 2024-08-15 | 13-Jan-25 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | Road Works |  | 2024-08-07 | 2024-08-15 | 13-Jan-25 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | Transfer Lighting poles |  | 2024-08-05 | 2024-08-07 | 21-Apr-25 A | 22-May-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | Transfer Lighting poles |  | 2024-08-05 | 2024-08-07 | 21-Apr-25 A | 22-May-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | Transfer Lighting poles |  | 2024-08-05 | 2024-08-07 | 21-Apr-25 A | 22-May-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | Connection Z13-C10 |  | 2024-08-11 | 2024-08-25 | 01-Feb-25 A | 13-May-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | Connection Z13-C10 |  | 2024-08-11 | 2024-08-25 | 01-Feb-25 A | 13-May-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | Connection Z13-C10 |  | 2024-08-11 | 2024-08-25 | 01-Feb-25 A | 13-May-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | Roundabout Catchbasin |  | 2024-08-13 | 2024-08-22 | 16-Nov-24 A | 22-May-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | Roundabout Catchbasin |  | 2024-08-13 | 2024-08-22 | 16-Nov-24 A | 22-May-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | Roundabout Catchbasin |  | 2024-08-13 | 2024-08-22 | 16-Nov-24 A | 22-May-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | Storm network for New Roads (MR1-MR2) |  | 2024-08-19 | 2024-08-25 | 19-Mar-25 A | 13-May-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | Storm network for New Roads (MR1-MR2) |  | 2024-08-19 | 2024-08-25 | 19-Mar-25 A | 13-May-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | Storm network for New Roads (MR1-MR2) |  | 2024-08-19 | 2024-08-25 | 19-Mar-25 A | 13-May-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | Box Culvert |  | 2024-08-12 | 2024-08-20 | 14-Jun-25 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | Box Culvert |  | 2024-08-12 | 2024-08-20 | 14-Jun-25 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | Box Culvert |  | 2024-08-12 | 2024-08-20 | 14-Jun-25 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | CCTV System |  | 2024-08-06 | 2024-08-19 | 09-Jun-25 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | CCTV System |  | 2024-08-06 | 2024-08-19 | 09-Jun-25 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | CCTV System |  | 2024-08-06 | 2024-08-19 | 09-Jun-25 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Prequalification and Material |  | 2024-07-30 | 2024-09-22 | 15-Sep-24 A | 31-Jul-25 A | 9592346.27 | 9592346.27 | 959234627% | Planned Total Cost | 1714323% | 9366048.29 | 209154.76
|  |  | JDH3-02-008--Prequalification and Material |  | 2024-07-30 | 2024-09-22 | 15-Sep-24 A | 31-Jul-25 A | 9592346.27 | 9592346.27 | 959234627% | Remaining Total Cost
|  |  | JDH3-02-008--Prequalification and Material |  | 2024-07-30 | 2024-09-22 | 15-Sep-24 A | 31-Jul-25 A | 9592346.27 | 9592346.27 | 959234627% | Actual Total Cost |  |  | 157563.09 | 110521905% | 165901981% | 287276817% | 2055965.35 | 1143616.22 | 257613.93 | 90911.25 | 85453.63 | 58513.39 | 105702.38
|  |  | JDH3-02-008--Submittals of Material and Prequalifications |  | 2024-07-30 | 2024-09-12 | 15-Sep-24 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Submittals of Material and Prequalifications |  | 2024-07-30 | 2024-09-12 | 15-Sep-24 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Submittals of Material and Prequalifications |  | 2024-07-30 | 2024-09-12 | 15-Sep-24 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Submittals of Material and Prequalifications-Sewage Network - SS |  | 2024-07-30 | 2024-09-12 | 18-Sep-24 A | 21-Jan-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Submittals of Material and Prequalifications-Sewage Network - SS |  | 2024-07-30 | 2024-09-12 | 18-Sep-24 A | 21-Jan-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Submittals of Material and Prequalifications-Sewage Network - SS |  | 2024-07-30 | 2024-09-12 | 18-Sep-24 A | 21-Jan-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Submittals of Material and Prequalifications-Storm Network - ST |  | 2024-07-30 | 2024-08-06 | 15-Sep-24 A | 28-Jan-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Submittals of Material and Prequalifications-Storm Network - ST |  | 2024-07-30 | 2024-08-06 | 15-Sep-24 A | 28-Jan-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Submittals of Material and Prequalifications-Storm Network - ST |  | 2024-07-30 | 2024-08-06 | 15-Sep-24 A | 28-Jan-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Submittals of Material and Prequalifications-TSE Network - TSE |  | 2024-07-30 | 2024-08-05 | 18-Sep-24 A | 19-Jan-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Submittals of Material and Prequalifications-TSE Network - TSE |  | 2024-07-30 | 2024-08-05 | 18-Sep-24 A | 19-Jan-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Submittals of Material and Prequalifications-TSE Network - TSE |  | 2024-07-30 | 2024-08-05 | 18-Sep-24 A | 19-Jan-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Submittals of Material and Prequalifications-Potable Water Network - WT |  | 2024-07-30 | 2024-08-05 | 18-Sep-24 A | 19-Jan-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Submittals of Material and Prequalifications-Potable Water Network - WT |  | 2024-07-30 | 2024-08-05 | 18-Sep-24 A | 19-Jan-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Submittals of Material and Prequalifications-Potable Water Network - WT |  | 2024-07-30 | 2024-08-05 | 18-Sep-24 A | 19-Jan-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Submittals of Material and Prequalifications-Street Lighting Network -SL |  | 2024-07-30 | 2024-08-05 | 28-Sep-24 A | 14-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Submittals of Material and Prequalifications-Street Lighting Network -SL |  | 2024-07-30 | 2024-08-05 | 28-Sep-24 A | 14-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Submittals of Material and Prequalifications-Street Lighting Network -SL |  | 2024-07-30 | 2024-08-05 | 28-Sep-24 A | 14-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Submittals of Material and Prequalifications-Telecommunications Network - TC |  | 2024-07-30 | 2024-08-05 | 21-Sep-24 A | 13-Jan-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Submittals of Material and Prequalifications-Telecommunications Network - TC |  | 2024-07-30 | 2024-08-05 | 21-Sep-24 A | 13-Jan-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Submittals of Material and Prequalifications-Telecommunications Network - TC |  | 2024-07-30 | 2024-08-05 | 21-Sep-24 A | 13-Jan-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Submittals of Material and Prequalifications-Road Works - RD |  | 2024-07-30 | 2024-08-05 | 21-Sep-24 A | 31-Mar-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Submittals of Material and Prequalifications-Road Works - RD |  | 2024-07-30 | 2024-08-05 | 21-Sep-24 A | 31-Mar-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Submittals of Material and Prequalifications-Road Works - RD |  | 2024-07-30 | 2024-08-05 | 21-Sep-24 A | 31-Mar-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Submittals of Material and Prequalifications-CCTV |  | 2024-07-30 | 2024-08-05 | 02-Jul-25 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Submittals of Material and Prequalifications-CCTV |  | 2024-07-30 | 2024-08-05 | 02-Jul-25 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Submittals of Material and Prequalifications-CCTV |  | 2024-07-30 | 2024-08-05 | 02-Jul-25 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Approval of Material and Prequalifications |  | 2024-07-30 | 2024-09-22 | 22-Sep-24 A | 31-Jul-25 A | 9592346.27 | 9592346.27 | 959234627% | Planned Total Cost | 1714323% | 9366048.29 | 209154.76
|  |  | JDH3-02-008--Approval of Material and Prequalifications |  | 2024-07-30 | 2024-09-22 | 22-Sep-24 A | 31-Jul-25 A | 9592346.27 | 9592346.27 | 959234627% | Remaining Total Cost
|  |  | JDH3-02-008--Approval of Material and Prequalifications |  | 2024-07-30 | 2024-09-22 | 22-Sep-24 A | 31-Jul-25 A | 9592346.27 | 9592346.27 | 959234627% | Actual Total Cost |  |  | 157563.09 | 110521905% | 165901981% | 287276817% | 2055965.35 | 1143616.22 | 257613.93 | 90911.25 | 85453.63 | 58513.39 | 105702.38
|  |  | JDH3-02-008-Approval of Material and Prequalifications-Sewage Network - SS |  | 2024-08-07 | 2024-09-22 | 22-Sep-24 A | 11-Feb-25 A | 627464.28 | 627464.28 | 62746428% | Planned Total Cost |  | 418309.52 | 209154.76
|  |  | JDH3-02-008-Approval of Material and Prequalifications-Sewage Network - SS |  | 2024-08-07 | 2024-09-22 | 22-Sep-24 A | 11-Feb-25 A | 627464.28 | 627464.28 | 62746428% | Remaining Total Cost
|  |  | JDH3-02-008-Approval of Material and Prequalifications-Sewage Network - SS |  | 2024-08-07 | 2024-09-22 | 22-Sep-24 A | 11-Feb-25 A | 627464.28 | 627464.28 | 62746428% | Actual Total Cost |  |  | 17429.56 | 13943651% | 18137639% | 16612553% | 107845.42 | 15250.87
|  |  | JDH3-02-008-Approval of Material and Prequalifications-Storm Network - ST |  | 2024-08-07 | 2024-08-20 | 22-Sep-24 A | 13-Mar-25 A | 7083648.88 | 7083648.88 | 708364888% | Planned Total Cost |  | 7083648.88
|  |  | JDH3-02-008-Approval of Material and Prequalifications-Storm Network - ST |  | 2024-08-07 | 2024-08-20 | 22-Sep-24 A | 13-Mar-25 A | 7083648.88 | 7083648.88 | 708364888% | Remaining Total Cost
|  |  | JDH3-02-008-Approval of Material and Prequalifications-Storm Network - ST |  | 2024-08-07 | 2024-08-20 | 22-Sep-24 A | 13-Mar-25 A | 7083648.88 | 7083648.88 | 708364888% | Actual Total Cost |  |  | 138352.52 | 82181395% | 123133740% | 230771999% | 1602122.15 | 871620.86 | 110682.01
|  |  | JDH3-02-008-Approval of Material and Prequalifications-TSE Network - TSE |  | 2024-08-06 | 2024-08-19 | 30-Sep-24 A | 16-Mar-25 A | 1131819.39 | 1131819.39 | 113181939% | Planned Total Cost |  | 1131819.39
|  |  | JDH3-02-008-Approval of Material and Prequalifications-TSE Network - TSE |  | 2024-08-06 | 2024-08-19 | 30-Sep-24 A | 16-Mar-25 A | 1131819.39 | 1131819.39 | 113181939% | Remaining Total Cost
|  |  | JDH3-02-008-Approval of Material and Prequalifications-TSE Network - TSE |  | 2024-08-06 | 2024-08-19 | 30-Sep-24 A | 16-Mar-25 A | 1131819.39 | 1131819.39 | 113181939% | Actual Total Cost |  |  | 1571.97 | 10532208% | 19649642% | 32539807% | 282954.85 | 172916.85 | 47159.14
|  |  | JDH3-02-008-Approval of Material and Prequalifications-Potable Water Network - WT |  | 2024-08-06 | 2024-08-19 | 30-Sep-24 A | 18-Mar-25 A | 2357-11-09 19:12 | 2357-11-09 19:12 | 16723080% | Planned Total Cost |  | 167230.8
|  |  | JDH3-02-008-Approval of Material and Prequalifications-Potable Water Network - WT |  | 2024-08-06 | 2024-08-19 | 30-Sep-24 A | 18-Mar-25 A | 2357-11-09 19:12 | 2357-11-09 19:12 | 16723080% | Remaining Total Cost
|  |  | JDH3-02-008-Approval of Material and Prequalifications-Potable Water Network - WT |  | 2024-08-06 | 2024-08-19 | 30-Sep-24 A | 18-Mar-25 A | 2357-11-09 19:12 | 2357-11-09 19:12 | 16723080% | Actual Total Cost |  |  | 209.04 | 1818635% | 2863827% | 4807886% | 40971.55 | 23203.27 | 7943.46
|  |  | JDH3-02-008-Approval of Material and Prequalifications-Street Lighting Network -SL |  | 2024-07-30 | 2024-08-19 | 16-Jan-25 A | 31-Jul-25 A | 373955.28 | 373955.28 | 37395528% | Planned Total Cost | 934888% | 364606.4
|  |  | JDH3-02-008-Approval of Material and Prequalifications-Street Lighting Network -SL |  | 2024-07-30 | 2024-08-19 | 16-Jan-25 A | 31-Jul-25 A | 373955.28 | 373955.28 | 37395528% | Remaining Total Cost
|  |  | JDH3-02-008-Approval of Material and Prequalifications-Street Lighting Network -SL |  | 2024-07-30 | 2024-08-19 | 16-Jan-25 A | 31-Jul-25 A | 373955.28 | 373955.28 | 37395528% | Actual Total Cost | [6 empty] | 12854.71 | 46744.41 | 77128.28 | 82181.73 | 72005.86 | 46570.38 | 36469.92
|  |  | JDH3-02-008-Approval of Material and Prequalifications-Telecommunications Network - TC |  | 2024-08-06 | 2024-08-19 | 14-Nov-24 A | 10-Jun-25 A | 1967-02-12 17:46 | 1967-02-12 17:46 | 2451574% | Planned Total Cost |  | 24515.74
|  |  | JDH3-02-008-Approval of Material and Prequalifications-Telecommunications Network - TC |  | 2024-08-06 | 2024-08-19 | 14-Nov-24 A | 10-Jun-25 A | 1967-02-12 17:46 | 1967-02-12 17:46 | 2451574% | Remaining Total Cost
|  |  | JDH3-02-008-Approval of Material and Prequalifications-Telecommunications Network - TC |  | 2024-08-06 | 2024-08-19 | 14-Nov-24 A | 10-Jun-25 A | 1967-02-12 17:46 | 1967-02-12 17:46 | 2451574% | Actual Total Cost |  |  |  |  | 168546% | 352414% | 3370.91 | 4137.03 | 3983.81 | 3370.91 | 3217.69 | 1225.79
|  |  | JDH3-02-008-Approval of Material and Prequalifications-Road Works - RD |  | 2024-07-30 | 2024-08-15 | 02-Oct-24 A | 29-Jul-25 A | 2241-06-09 12:29 | 2241-06-09 12:29 | 12470952% | Planned Total Cost | 779435% | 116915.18
|  |  | JDH3-02-008-Approval of Material and Prequalifications-Road Works - RD |  | 2024-07-30 | 2024-08-15 | 02-Oct-24 A | 29-Jul-25 A | 2241-06-09 12:29 | 2241-06-09 12:29 | 12470952% | Remaining Total Cost
|  |  | JDH3-02-008-Approval of Material and Prequalifications-Road Works - RD |  | 2024-07-30 | 2024-08-15 | 02-Oct-24 A | 29-Jul-25 A | 2241-06-09 12:29 | 2241-06-09 12:29 | 12470952% | Actual Total Cost |  |  |  | 2046016% | 1948586% | 2192160% | 5845.76 | 9742.93 | 10717.22 | 5358.61 | 10230.08 | 10717.22 | 10230.08
|  |  | JDH3-02-008-Approval of Material and Prequalifications-CCTV |  | 2024-08-06 | 2024-08-19 | 10-Jul-25 A | 31-Jul-25 A | 2061-07-15 09:07 | 2061-07-15 09:07 | 5900238% | Planned Total Cost |  | 59002.38
|  |  | JDH3-02-008-Approval of Material and Prequalifications-CCTV |  | 2024-08-06 | 2024-08-19 | 10-Jul-25 A | 31-Jul-25 A | 2061-07-15 09:07 | 2061-07-15 09:07 | 5900238% | Remaining Total Cost
|  |  | JDH3-02-008-Approval of Material and Prequalifications-CCTV |  | 2024-08-06 | 2024-08-19 | 10-Jul-25 A | 31-Jul-25 A | 2061-07-15 09:07 | 2061-07-15 09:07 | 5900238% | Actual Total Cost | [12 empty] | 59002.38
|  |  | JDH3-02-008--Method Statment |  | 2024-07-30 | 2024-08-25 | 21-Sep-24 A | 09-Jun-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Method Statment |  | 2024-07-30 | 2024-08-25 | 21-Sep-24 A | 09-Jun-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Method Statment |  | 2024-07-30 | 2024-08-25 | 21-Sep-24 A | 09-Jun-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Earth Works (Excavation, Backfilling) |  | 2024-07-30 | 2024-08-13 | 21-Sep-24 A | 07-Jan-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Earth Works (Excavation, Backfilling) |  | 2024-07-30 | 2024-08-13 | 21-Sep-24 A | 07-Jan-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Earth Works (Excavation, Backfilling) |  | 2024-07-30 | 2024-08-13 | 21-Sep-24 A | 07-Jan-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Concrete Works |  | 2024-08-03 | 2024-08-25 | 14-Nov-24 A | 12-Feb-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Concrete Works |  | 2024-08-03 | 2024-08-25 | 14-Nov-24 A | 12-Feb-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Concrete Works |  | 2024-08-03 | 2024-08-25 | 14-Nov-24 A | 12-Feb-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Underground Utilities and Foundation |  | 2024-07-30 | 2024-08-13 | 31-Oct-24 A | 29-Jan-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Underground Utilities and Foundation |  | 2024-07-30 | 2024-08-13 | 31-Oct-24 A | 29-Jan-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Underground Utilities and Foundation |  | 2024-07-30 | 2024-08-13 | 31-Oct-24 A | 29-Jan-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Asphalt Works |  | 2024-07-30 | 2024-08-13 | 24-Sep-24 A | 25-Dec-24 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Asphalt Works |  | 2024-07-30 | 2024-08-13 | 24-Sep-24 A | 25-Dec-24 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Asphalt Works |  | 2024-07-30 | 2024-08-13 | 24-Sep-24 A | 25-Dec-24 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Storm Network |  | 2024-07-30 | 2024-08-13 | 20-Nov-24 A | 26-Feb-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Storm Network |  | 2024-07-30 | 2024-08-13 | 20-Nov-24 A | 26-Feb-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Storm Network |  | 2024-07-30 | 2024-08-13 | 20-Nov-24 A | 26-Feb-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Sewage Network |  | 2024-07-30 | 2024-08-13 | 01-Dec-24 A | 10-Mar-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Sewage Network |  | 2024-07-30 | 2024-08-13 | 01-Dec-24 A | 10-Mar-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Sewage Network |  | 2024-07-30 | 2024-08-13 | 01-Dec-24 A | 10-Mar-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Potable Network |  | 2024-07-30 | 2024-08-13 | 09-Jan-25 A | 10-Apr-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Potable Network |  | 2024-07-30 | 2024-08-13 | 09-Jan-25 A | 10-Apr-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Potable Network |  | 2024-07-30 | 2024-08-13 | 09-Jan-25 A | 10-Apr-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--TSE Network |  | 2024-07-30 | 2024-08-13 | 10-Dec-24 A | 16-Mar-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--TSE Network |  | 2024-07-30 | 2024-08-13 | 10-Dec-24 A | 16-Mar-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--TSE Network |  | 2024-07-30 | 2024-08-13 | 10-Dec-24 A | 16-Mar-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Street Lighting |  | 2024-07-30 | 2024-08-13 | 05-Mar-25 A | 09-Jun-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Street Lighting |  | 2024-07-30 | 2024-08-13 | 05-Mar-25 A | 09-Jun-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Street Lighting |  | 2024-07-30 | 2024-08-13 | 05-Mar-25 A | 09-Jun-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Precast Concrete Curbstone, Interlocking |  | 2024-07-30 | 2024-08-13 | 02-Nov-24 A | 03-Feb-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Precast Concrete Curbstone, Interlocking |  | 2024-07-30 | 2024-08-13 | 02-Nov-24 A | 03-Feb-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Precast Concrete Curbstone, Interlocking |  | 2024-07-30 | 2024-08-13 | 02-Nov-24 A | 03-Feb-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--WaterProofing |  | 2024-07-30 | 2024-08-13 | 10-Feb-25 A | 18-May-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--WaterProofing |  | 2024-07-30 | 2024-08-13 | 10-Feb-25 A | 18-May-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--WaterProofing |  | 2024-07-30 | 2024-08-13 | 10-Feb-25 A | 18-May-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Precast Box Culvert |  | 2024-07-30 | 2024-08-13 | 31-Oct-24 A | 02-Feb-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Precast Box Culvert |  | 2024-07-30 | 2024-08-13 | 31-Oct-24 A | 02-Feb-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Precast Box Culvert |  | 2024-07-30 | 2024-08-13 | 31-Oct-24 A | 02-Feb-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Procurement |  | 2024-08-09 | 2026-04-16 | 10-Oct-24 A | 2026-02-06 | 40322209.1 | 40322209.15 | 6394897515% | Planned Total Cost |  | 357952.36 | 5948040.28 | 687478788% | 624884051% | 226945016% | 1756168.76 | 924845.78 | 856476.49 | 275834.72 | 254853.66 | 382799.23 | 929279.71 | 1362532.42 | 922032.59 | 21289216.71 | 6808137.9 | 2055249.13 | 2238935.09 | 935067.75 | 964525.97 | 86098.88 | 168877.44 | 38971.72
|  |  | JDH3-02-008--Procurement |  | 2024-08-09 | 2026-04-16 | 10-Oct-24 A | 2026-02-06 | 40322209.1 | 40322209.15 | 6394897515% | Remaining Total Cost | [15 empty] | 18278326.12 | 4215228.63 | 1049375.33 | 70240.94 | 13595.02
|  |  | JDH3-02-008--Procurement |  | 2024-08-09 | 2026-04-16 | 10-Oct-24 A | 2026-02-06 | 40322209.1 | 40322209.15 | 6394897515% | Actual Total Cost |  |  |  | 5709786% | 50400267% | 226526975% | 3414970.49 | 3364887 | 4356285.41 | 5053428.44 | 6638020.44 | 5931652.69 | 5354468.19 | 2487684.88 | 894441.33
|  |  | JDH3-02-008--Material Purchase Order |  | 2024-08-09 | 2024-09-30 | 10-Oct-24 A | 2025-10-09 | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Material Purchase Order |  | 2024-08-09 | 2024-09-30 | 10-Oct-24 A | 2025-10-09 | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Material Purchase Order |  | 2024-08-09 | 2024-09-30 | 10-Oct-24 A | 2025-10-09 | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Material Purchase Order-Sewage Network - SS |  | 2024-08-15 | 2024-09-30 | 02-Nov-24 A | 25-Apr-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Material Purchase Order-Sewage Network - SS |  | 2024-08-15 | 2024-09-30 | 02-Nov-24 A | 25-Apr-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Material Purchase Order-Sewage Network - SS |  | 2024-08-15 | 2024-09-30 | 02-Nov-24 A | 25-Apr-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Material Purchase Order-Storm Network - ST |  | 2024-08-19 | 2024-08-31 | 10-Oct-24 A | 17-Apr-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Material Purchase Order-Storm Network - ST |  | 2024-08-19 | 2024-08-31 | 10-Oct-24 A | 17-Apr-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Material Purchase Order-Storm Network - ST |  | 2024-08-19 | 2024-08-31 | 10-Oct-24 A | 17-Apr-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Material Purchase Order-TSE Network - TSE |  | 2024-08-20 | 2024-08-27 | 05-Nov-24 A | 2025-10-09 | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Material Purchase Order-TSE Network - TSE |  | 2024-08-20 | 2024-08-27 | 05-Nov-24 A | 2025-10-09 | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Material Purchase Order-TSE Network - TSE |  | 2024-08-20 | 2024-08-27 | 05-Nov-24 A | 2025-10-09 | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Material Purchase Order-Potable Water Network - WT |  | 2024-08-20 | 2024-08-27 | 14-Nov-24 A | 2025-10-09 | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Material Purchase Order-Potable Water Network - WT |  | 2024-08-20 | 2024-08-27 | 14-Nov-24 A | 2025-10-09 | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Material Purchase Order-Potable Water Network - WT |  | 2024-08-20 | 2024-08-27 | 14-Nov-24 A | 2025-10-09 | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Material Purchase Order-Street Lighting Network -SL |  | 2024-08-13 | 2024-08-25 | 01-Dec-24 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Material Purchase Order-Street Lighting Network -SL |  | 2024-08-13 | 2024-08-25 | 01-Dec-24 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Material Purchase Order-Street Lighting Network -SL |  | 2024-08-13 | 2024-08-25 | 01-Dec-24 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Material Purchase Order-Telecommunications Network - TC |  | 2024-08-20 | 2024-08-25 | 01-Apr-25 A | 18-May-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Material Purchase Order-Telecommunications Network - TC |  | 2024-08-20 | 2024-08-25 | 01-Apr-25 A | 18-May-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Material Purchase Order-Telecommunications Network - TC |  | 2024-08-20 | 2024-08-25 | 01-Apr-25 A | 18-May-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Material Purchase Order-Road Works - RD |  | 2024-08-09 | 2024-08-22 | 29-Oct-24 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Material Purchase Order-Road Works - RD |  | 2024-08-09 | 2024-08-22 | 29-Oct-24 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Material Purchase Order-Road Works - RD |  | 2024-08-09 | 2024-08-22 | 29-Oct-24 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Material Purchase Order-CCTV System |  | 2024-08-20 | 2024-08-25 | 02-Jul-25 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Material Purchase Order-CCTV System |  | 2024-08-20 | 2024-08-25 | 02-Jul-25 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Material Purchase Order-CCTV System |  | 2024-08-20 | 2024-08-25 | 02-Jul-25 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Material Fabrication |  | 2024-08-16 | 2024-10-27 | 10-Oct-24 A | 2025-12-08 | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008--Material Fabrication |  | 2024-08-16 | 2024-10-27 | 10-Oct-24 A | 2025-12-08 | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008--Material Fabrication |  | 2024-08-16 | 2024-10-27 | 10-Oct-24 A | 2025-12-08 | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Material Fabrication-Sewage Network - SS |  | 2024-08-22 | 2024-10-07 | 02-Nov-24 A | 17-Apr-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Material Fabrication-Sewage Network - SS |  | 2024-08-22 | 2024-10-07 | 02-Nov-24 A | 17-Apr-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Material Fabrication-Sewage Network - SS |  | 2024-08-22 | 2024-10-07 | 02-Nov-24 A | 17-Apr-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Material Fabrication-Storm Network - ST |  | 2024-08-25 | 2024-09-07 | 10-Oct-24 A | 17-Apr-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Material Fabrication-Storm Network - ST |  | 2024-08-25 | 2024-09-07 | 10-Oct-24 A | 17-Apr-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Material Fabrication-Storm Network - ST |  | 2024-08-25 | 2024-09-07 | 10-Oct-24 A | 17-Apr-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Material Fabrication-TSE Network - TSE |  | 2024-08-26 | 2024-10-27 | 12-Nov-24 A | 2025-12-08 | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Material Fabrication-TSE Network - TSE |  | 2024-08-26 | 2024-10-27 | 12-Nov-24 A | 2025-12-08 | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Material Fabrication-TSE Network - TSE |  | 2024-08-26 | 2024-10-27 | 12-Nov-24 A | 2025-12-08 | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Material Fabrication-Potable Water Network - WT |  | 2024-08-26 | 2024-10-27 | 14-Nov-24 A | 2025-12-08 | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Material Fabrication-Potable Water Network - WT |  | 2024-08-26 | 2024-10-27 | 14-Nov-24 A | 2025-12-08 | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Material Fabrication-Potable Water Network - WT |  | 2024-08-26 | 2024-10-27 | 14-Nov-24 A | 2025-12-08 | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Material Fabrication-Street Lighting Network -SL |  | 2024-08-19 | 2024-08-31 | 23-Apr-25 A | 09-Jun-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Material Fabrication-Street Lighting Network -SL |  | 2024-08-19 | 2024-08-31 | 23-Apr-25 A | 09-Jun-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Material Fabrication-Street Lighting Network -SL |  | 2024-08-19 | 2024-08-31 | 23-Apr-25 A | 09-Jun-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Material Fabrication-Telecommunications Network - TC |  | 2024-08-26 | 2024-08-31 | 02-Jul-25 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Material Fabrication-Telecommunications Network - TC |  | 2024-08-26 | 2024-08-31 | 02-Jul-25 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Material Fabrication-Telecommunications Network - TC |  | 2024-08-26 | 2024-08-31 | 02-Jul-25 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Material Fabrication-Road Works - RD |  | 2024-08-16 | 2024-09-04 | 29-Oct-24 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Material Fabrication-Road Works - RD |  | 2024-08-16 | 2024-09-04 | 29-Oct-24 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Material Fabrication-Road Works - RD |  | 2024-08-16 | 2024-09-04 | 29-Oct-24 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008-Material Fabrication-CCTV System |  | 2024-08-26 | 2024-08-31 | 09-Jul-25 A | 31-Jul-25 A | 0 | 0 | 0% | Planned Total Cost
|  |  | JDH3-02-008-Material Fabrication-CCTV System |  | 2024-08-26 | 2024-08-31 | 09-Jul-25 A | 31-Jul-25 A | 0 | 0 | 0% | Remaining Total Cost
|  |  | JDH3-02-008-Material Fabrication-CCTV System |  | 2024-08-26 | 2024-08-31 | 09-Jul-25 A | 31-Jul-25 A | 0 | 0 | 0% | Actual Total Cost
|  |  | JDH3-02-008--Material Delivery on Site |  | 2024-08-28 | 2026-04-16 | 19-Oct-24 A | 2026-02-06 | 40322209.1 | 40322209.15 | 6394897515% | Planned Total Cost |  | 357952.36 | 5948040.28 | 687478788% | 624884051% | 226945016% | 1756168.76 | 924845.78 | 856476.49 | 275834.72 | 254853.66 | 382799.23 | 929279.71 | 1362532.42 | 922032.59 | 21289216.71 | 6808137.9 | 2055249.13 | 2238935.09 | 935067.75 | 964525.97 | 86098.88 | 168877.44 | 38971.72
|  |  | JDH3-02-008--Material Delivery on Site |  | 2024-08-28 | 2026-04-16 | 19-Oct-24 A | 2026-02-06 | 40322209.1 | 40322209.15 | 6394897515% | Remaining Total Cost | [15 empty] | 18278326.12 | 4215228.63 | 1049375.33 | 70240.94 | 13595.02
|  |  | JDH3-02-008--Material Delivery on Site |  | 2024-08-28 | 2026-04-16 | 19-Oct-24 A | 2026-02-06 | 40322209.1 | 40322209.15 | 6394897515% | Actual Total Cost |  |  |  | 5709786% | 50400267% | 226526975% | 3414970.49 | 3364887 | 4356285.41 | 5053428.44 | 6638020.44 | 5931652.69 | 5354468.19 | 2487684.88 | 894441.33
|  |  | JDH3-02-008-Material Delivery on Site-MR |  | 2024-08-31 | 2025-08-01 | 12-Nov-24 A | 2026-02-06 | 4967292.24 | 4967292.24 | 602430665% | Planned Total Cost |  | 35137.15 | 1174830.84 | 143014930% | 119921947% | 25629965% |  |  |  |  | 77907.36 |  |  |  |  | 602534.56 | 552600.14 | 267234.85 | 128362.13 | 36438.45 | 36001.08 | 19742.53 | 168877.44 | 38971.72
|  |  | JDH3-02-008-Material Delivery on Site-MR |  | 2024-08-31 | 2025-08-01 | 12-Nov-24 A | 2026-02-06 | 4967292.24 | 4967292.24 | 602430665% | Remaining Total Cost | [15 empty] | 407766.16 | 435739.1 | 189327.49 | 20260.32 | 3921.35
|  |  | JDH3-02-008-Material Delivery on Site-MR |  | 2024-08-31 | 2025-08-01 | 12-Nov-24 A | 2026-02-06 | 4967292.24 | 4967292.24 | 602430665% | Actual Total Cost |  |  |  |  | 5307083% | 29365656% | 201768.62 | 148580.6 | 368948.8 | 476713.3 | 1361931.34 | 826694.69 | 739136.8 | 487625.14 | 9165.57
|  |  | JDH3-02-008-Material Delivery on Site-Sewage Network - SS-MR |  | 2024-10-08 | 2025-02-14 | 14-Dec-24 A | 2025-12-12 | 2377-03-14 15:22 | 2377-03-14 15:22 | 104577384% | Planned Total Cost |  |  |  | 17429564% | [11 empty] | 261443.46 | 435739.1 | 174295.64
|  |  | JDH3-02-008-Material Delivery on Site-Sewage Network - SS-MR |  | 2024-10-08 | 2025-02-14 | 14-Dec-24 A | 2025-12-12 | 2377-03-14 15:22 | 2377-03-14 15:22 | 104577384% | Remaining Total Cost | [15 empty] | 261443.46 | 435739.1 | 174295.64
|  |  | JDH3-02-008-Material Delivery on Site-Sewage Network - SS-MR |  | 2024-10-08 | 2025-02-14 | 14-Dec-24 A | 2025-12-12 | 2377-03-14 15:22 | 2377-03-14 15:22 | 104577384% | Actual Total Cost | [5 empty] | 3268043% | 56282.97 | 50836.23 | 34496.01
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-MR |  | 2024-08-31 | 2024-12-05 | 01-Mar-25 A | 31-Jul-25 A | 3373166.16 | 3373166.16 | 337316616% | Planned Total Cost |  | 35137.15 | 1018977.28 | 108925157% | 105411443% | 17568574%
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-MR |  | 2024-08-31 | 2024-12-05 | 01-Mar-25 A | 31-Jul-25 A | 3373166.16 | 3373166.16 | 337316616% | Remaining Total Cost
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-MR |  | 2024-08-31 | 2024-12-05 | 01-Mar-25 A | 31-Jul-25 A | 3373166.16 | 3373166.16 | 337316616% | Actual Total Cost | [8 empty] | 272312.89 | 390900.77 | 1284885.57 | 779407.15 | 645659.77
|  |  | JDH3-02-008-Material Delivery on Site-Potable Water Network - WT-MR |  | 2024-12-29 | 2025-06-26 | 10-Jun-25 A | 2026-02-06 | 2224-04-25 03:36 | 2224-04-25 03:36 | 13935900% | Planned Total Cost | [15 empty] | 13935.9 |  | 2671.05 | 33794.56 | 33213.89 | 36001.08 | 19742.53
|  |  | JDH3-02-008-Material Delivery on Site-Potable Water Network - WT-MR |  | 2024-12-29 | 2025-06-26 | 10-Jun-25 A | 2026-02-06 | 2224-04-25 03:36 | 2224-04-25 03:36 | 13935900% | Remaining Total Cost | [15 empty] | 13935.9 |  | 2671.05 | 3600.11 | 696.8
|  |  | JDH3-02-008-Material Delivery on Site-Potable Water Network - WT-MR |  | 2024-12-29 | 2025-06-26 | 10-Jun-25 A | 2026-02-06 | 2224-04-25 03:36 | 2224-04-25 03:36 | 13935900% | Actual Total Cost | [11 empty] | 21882.97 | 19924.73 | 76647.45
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-MR |  | 2024-09-01 | 2025-02-16 | 12-Nov-24 A | 2026-02-06 | 548174.61 | 548174.61 | 58042017% | Planned Total Cost |  |  | 155853.56 | 16660209% | 14510504% | 8061391% | [11 empty] | 12360.8 | 16660.21 | 3224.56
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-MR |  | 2024-09-01 | 2025-02-16 | 12-Nov-24 A | 2026-02-06 | 548174.61 | 548174.61 | 58042017% | Remaining Total Cost | [17 empty] | 12360.8 | 16660.21 | 3224.56
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-MR |  | 2024-09-01 | 2025-02-16 | 12-Nov-24 A | 2026-02-06 | 548174.61 | 548174.61 | 58042017% | Actual Total Cost |  |  |  |  | 5307083% | 13973078% | 110844.13 | 97744.37 | 62139.89 | 50383.7 | 34260.91
|  |  | JDH3-02-008-Material Delivery on Site-Street Lighting Network -SL-MR |  | 2025-04-28 | 2025-08-01 | 01-May-25 A | 2025-10-13 | 545351.52 | 545351.52 | 62325888% | Planned Total Cost | [10 empty] | 77907.36 |  |  |  |  | 272675.76 | 116861.04 | 77907.36 | 77907.36
|  |  | JDH3-02-008-Material Delivery on Site-Street Lighting Network -SL-MR |  | 2025-04-28 | 2025-08-01 | 01-May-25 A | 2025-10-13 | 545351.52 | 545351.52 | 62325888% | Remaining Total Cost | [15 empty] | 77907.36
|  |  | JDH3-02-008-Material Delivery on Site-Street Lighting Network -SL-MR |  | 2025-04-28 | 2025-08-01 | 01-May-25 A | 2025-10-13 | 545351.52 | 545351.52 | 62325888% | Actual Total Cost | [10 empty] | 26251.39 | 25404.57 | 73552.29 | 410977.69 | 9165.57
|  |  | JDH3-02-008-Material Delivery on Site-Telecommunications Network - TC-MR |  | 2025-05-10 | 2025-06-02 | 2025-10-02 | 2025-10-25 | 0 | 0 | 5447944% | Planned Total Cost | [15 empty] | 54479.44
|  |  | JDH3-02-008-Material Delivery on Site-Telecommunications Network - TC-MR |  | 2025-05-10 | 2025-06-02 | 2025-10-02 | 2025-10-25 | 0 | 0 | 5447944% | Remaining Total Cost | [15 empty] | 54479.44
|  |  | JDH3-02-008-Material Delivery on Site-Telecommunications Network - TC-MR |  | 2025-05-10 | 2025-06-02 | 2025-10-02 | 2025-10-25 | 0 | 0 | 5447944% | Actual Total Cost
|  |  | JDH3-02-008-Material Delivery on Site-Road Works - RD-MR |  | 2025-05-10 | 2025-06-02 | 04-Dec-24 A | 07-May-25 A | 207849.16 | 207849.16 | 20784916% | Planned Total Cost | [22 empty] | 168877.44 | 38971.72
|  |  | JDH3-02-008-Material Delivery on Site-Road Works - RD-MR |  | 2025-05-10 | 2025-06-02 | 04-Dec-24 A | 07-May-25 A | 207849.16 | 207849.16 | 20784916% | Remaining Total Cost
|  |  | JDH3-02-008-Material Delivery on Site-Road Works - RD-MR |  | 2025-05-10 | 2025-06-02 | 04-Dec-24 A | 07-May-25 A | 207849.16 | 207849.16 | 20784916% | Actual Total Cost | [5 empty] | 12124534% | 34641.53 |  |  | 35428.83 | 16533.46
|  |  | JDH3-02-008-Material Delivery on Site-Z01 |  | 2025-06-03 | 2026-02-21 | 19-Oct-24 A | 2025-12-18 | 2069970.7 | 2069970.7 | 409294533% | Planned Total Cost | [13 empty] | 632468.66 | 632468.66 | 2215714.07 | 166602.09 | 126795.38 | 80613.91 | 62304.25 | 109621.98 | 66356.35
|  |  | JDH3-02-008-Material Delivery on Site-Z01 |  | 2025-06-03 | 2026-02-21 | 19-Oct-24 A | 2025-12-18 | 2069970.7 | 2069970.7 | 409294533% | Remaining Total Cost | [15 empty] | 1794068.3 | 161227.83 | 67678.51
|  |  | JDH3-02-008-Material Delivery on Site-Z01 |  | 2025-06-03 | 2026-02-21 | 19-Oct-24 A | 2025-12-18 | 2069970.7 | 2069970.7 | 409294533% | Actual Total Cost |  |  |  | 5709786% | 13176430% | 14959210% | 266785.29 | 264769.95 | 427797.7 | 347757 | 177806.97 | 78568.27 | 19924.73 | 148106.53
|  |  | JDH3-02-008-Material Delivery on Site-Potable Water Network - WT-Z01 |  | 2025-06-03 | 2025-08-01 | 10-Jun-25 A | 2025-12-18 | 2243-05-24 02:24 | 2243-05-24 02:24 | 13935900% | Planned Total Cost | [17 empty] | 13935.9 |  | 13935.9 | 72002.15 | 39485.05
|  |  | JDH3-02-008-Material Delivery on Site-Potable Water Network - WT-Z01 |  | 2025-06-03 | 2025-08-01 | 10-Jun-25 A | 2025-12-18 | 2243-05-24 02:24 | 2243-05-24 02:24 | 13935900% | Remaining Total Cost | [17 empty] | 13935.9
|  |  | JDH3-02-008-Material Delivery on Site-Potable Water Network - WT-Z01 |  | 2025-06-03 | 2025-08-01 | 10-Jun-25 A | 2025-12-18 | 2243-05-24 02:24 | 2243-05-24 02:24 | 13935900% | Actual Total Cost | [11 empty] | 21882.97 | 19924.73 | 83615.4
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z01 |  | 2025-08-02 | 2025-11-05 | 19-Oct-24 A | 2025-10-25 | 1686583.08 | 1686583.08 | 337316616% | Planned Total Cost | [13 empty] | 632468.66 | 632468.66 | 2108228.85
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z01 |  | 2025-08-02 | 2025-11-05 | 19-Oct-24 A | 2025-10-25 | 1686583.08 | 1686583.08 | 337316616% | Remaining Total Cost | [15 empty] | 1686583.08
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z01 |  | 2025-08-02 | 2025-11-05 | 19-Oct-24 A | 2025-10-25 | 1686583.08 | 1686583.08 | 337316616% | Actual Total Cost |  |  |  | 5709786% | 13176430% | 13615645% | 245960.03 | 245960.03 | 382116.48 | 307450.04 | 136156.45 | 43921.43
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z01 |  | 2025-11-06 | 2026-02-21 | 12-Dec-24 A | 2025-12-10 | 257964.52 | 257964.52 | 58042017% | Planned Total Cost | [15 empty] | 107485.22 | 166602.09 | 112859.48 | 80613.91 | 48368.35 | 37619.83 | 26871.3
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z01 |  | 2025-11-06 | 2026-02-21 | 12-Dec-24 A | 2025-12-10 | 257964.52 | 257964.52 | 58042017% | Remaining Total Cost | [15 empty] | 107485.22 | 161227.83 | 53742.61
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z01 |  | 2025-11-06 | 2026-02-21 | 12-Dec-24 A | 2025-12-10 | 257964.52 | 257964.52 | 58042017% | Actual Total Cost | [5 empty] | 1343565% | 20825.26 | 18809.91 | 45681.22 | 40306.96 | 41650.52 | 12763.87 |  | 64491.13
|  |  | JDH3-02-008-Material Delivery on Site-Z02 |  | 2024-12-04 | 2025-06-02 | 01-Jan-25 A | 2025-11-14 | 1359220.58 | 1359220.58 | 395358633% | Planned Total Cost | [5 empty] | 42164577% | 421645.77 |  | 64491.13 | 80613.91 | 112859.48 |  |  |  |  | 2102445.69 | 620902.33 | 128982.26
|  |  | JDH3-02-008-Material Delivery on Site-Z02 |  | 2024-12-04 | 2025-06-02 | 01-Jan-25 A | 2025-11-14 | 1359220.58 | 1359220.58 | 395358633% | Remaining Total Cost | [15 empty] | 2102445.69 | 491920.07
|  |  | JDH3-02-008-Material Delivery on Site-Z02 |  | 2024-12-04 | 2025-06-02 | 01-Jan-25 A | 2025-11-14 | 1359220.58 | 1359220.58 | 395358633% | Actual Total Cost | [6 empty] | 20825.26 | 31573.78 | 168060.76 | 348301.75 | 327285.99 | 119777.02 | 85431.5 | 257964.52
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z02 |  | 2024-12-04 | 2025-02-19 | 01-Mar-25 A | 2025-11-14 | 843291.54 | 843291.54 | 337316616% | Planned Total Cost | [5 empty] | 42164577% | 421645.77 | [8 empty] | 2037954.56 | 491920.07
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z02 |  | 2024-12-04 | 2025-02-19 | 01-Mar-25 A | 2025-11-14 | 843291.54 | 843291.54 | 337316616% | Remaining Total Cost | [15 empty] | 2037954.56 | 491920.07
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z02 |  | 2024-12-04 | 2025-02-19 | 01-Mar-25 A | 2025-11-14 | 843291.54 | 843291.54 | 337316616% | Actual Total Cost | [8 empty] | 85431.5 | 273733.88 | 289666.17 | 109028.5 | 85431.5
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z02 |  | 2025-02-20 | 2025-06-02 | 01-Jan-25 A | 2025-10-19 | 515929.04 | 515929.04 | 58042017% | Planned Total Cost | [8 empty] | 64491.13 | 80613.91 | 112859.48 |  |  |  |  | 64491.13 | 128982.26 | 128982.26
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z02 |  | 2025-02-20 | 2025-06-02 | 01-Jan-25 A | 2025-10-19 | 515929.04 | 515929.04 | 58042017% | Remaining Total Cost | [15 empty] | 64491.13
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z02 |  | 2025-02-20 | 2025-06-02 | 01-Jan-25 A | 2025-10-19 | 515929.04 | 515929.04 | 58042017% | Actual Total Cost | [6 empty] | 20825.26 | 31573.78 | 82629.26 | 74567.87 | 37619.83 | 10748.52 |  | 257964.52
|  |  | JDH3-02-008-Material Delivery on Site-Z02-1 |  | 2024-08-28 | 2024-12-28 | 04-Dec-24 A | 2025-10-25 | 5009702.25 | 5009702.25 | 581645749% | Planned Total Cost |  | 93235.69 | 1261450.08 | 151089562% | 118463530% | 5809855% | [9 empty] | 1513373.85 | 116861.04 | 77907.36
|  |  | JDH3-02-008-Material Delivery on Site-Z02-1 |  | 2024-08-28 | 2024-12-28 | 04-Dec-24 A | 2025-10-25 | 5009702.25 | 5009702.25 | 581645749% | Remaining Total Cost | [15 empty] | 806755.24
|  |  | JDH3-02-008-Material Delivery on Site-Z02-1 |  | 2024-08-28 | 2024-12-28 | 04-Dec-24 A | 2025-10-25 | 5009702.25 | 5009702.25 | 581645749% | Actual Total Cost | [5 empty] | 5083623% | 56282.97 | 50836.23 | 206474.33 | 418399.18 | 794536.71 | 1343402.6 | 1262719.7 | 810091.53 | 16122.78
|  |  | JDH3-02-008-Material Delivery on Site-Sewage Network - SS-Z02-1 |  | 2024-08-28 | 2024-12-04 | 04-Dec-24 A | 2025-10-11 | 871478.2 | 871478.2 | 104577384% | Planned Total Cost |  | 58098.55 | 116197.09 | 34859128% | 29049273% | 5809855% | [9 empty] | 174295.64
|  |  | JDH3-02-008-Material Delivery on Site-Sewage Network - SS-Z02-1 |  | 2024-08-28 | 2024-12-04 | 04-Dec-24 A | 2025-10-11 | 871478.2 | 871478.2 | 104577384% | Remaining Total Cost | [15 empty] | 174295.64
|  |  | JDH3-02-008-Material Delivery on Site-Sewage Network - SS-Z02-1 |  | 2024-08-28 | 2024-12-04 | 04-Dec-24 A | 2025-10-11 | 871478.2 | 871478.2 | 104577384% | Actual Total Cost | [5 empty] | 5083623% | 56282.97 | 50836.23 | 63545.29 | 94410.14 | 168848.9 | 206412.62 | 180305.83
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z02-1 |  | 2024-08-31 | 2024-12-03 | 12-Mar-25 A | 2025-10-11 | 2951520.39 | 2951520.39 | 337316616% | Planned Total Cost |  | 35137.15 | 1018977.28 | 108925157% | 80815439% | [10 empty] | 421645.77
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z02-1 |  | 2024-08-31 | 2024-12-03 | 12-Mar-25 A | 2025-10-11 | 2951520.39 | 2951520.39 | 337316616% | Remaining Total Cost | [15 empty] | 421645.77
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z02-1 |  | 2024-08-31 | 2024-12-03 | 12-Mar-25 A | 2025-10-11 | 2951520.39 | 2951520.39 | 337316616% | Actual Total Cost | [8 empty] | 87842.87 | 263528.61 | 536960.63 | 1074251.45 | 988936.84
|  |  | JDH3-02-008-Material Delivery on Site-Potable Water Network - WT-Z02-1 |  | 2024-09-01 | 2024-10-31 | 10-Jun-25 A | 2025-10-07 | 2243-05-24 02:24 | 2243-05-24 02:24 | 13935900% | Planned Total Cost |  |  |  | 1393590% | [11 empty] | 125423.1
|  |  | JDH3-02-008-Material Delivery on Site-Potable Water Network - WT-Z02-1 |  | 2024-09-01 | 2024-10-31 | 10-Jun-25 A | 2025-10-07 | 2243-05-24 02:24 | 2243-05-24 02:24 | 13935900% | Remaining Total Cost | [15 empty] | 13935.9
|  |  | JDH3-02-008-Material Delivery on Site-Potable Water Network - WT-Z02-1 |  | 2024-09-01 | 2024-10-31 | 10-Jun-25 A | 2025-10-07 | 2243-05-24 02:24 | 2243-05-24 02:24 | 13935900% | Actual Total Cost | [11 empty] | 21882.97 | 19924.73 | 83615.4
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z02-1 |  | 2024-09-01 | 2024-12-06 | 01-Mar-25 A | 2025-10-11 | 515929.04 | 515929.04 | 58042017% | Planned Total Cost |  |  | 48368.35 | 5911687% | 8598817% | [10 empty] | 386946.78
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z02-1 |  | 2024-09-01 | 2024-12-06 | 01-Mar-25 A | 2025-10-11 | 515929.04 | 515929.04 | 58042017% | Remaining Total Cost | [15 empty] | 64491.13
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z02-1 |  | 2024-09-01 | 2024-12-06 | 01-Mar-25 A | 2025-10-11 | 515929.04 | 515929.04 | 58042017% | Actual Total Cost | [8 empty] | 55086.17 | 60460.43 | 62475.78 | 15451 |  | 306332.87 | 16122.78
|  |  | JDH3-02-008-Material Delivery on Site-Street Lighting Network -SL-Z02-1 |  | 2024-08-30 | 2024-12-04 | 01-May-25 A | 2025-10-13 | 545351.52 | 545351.52 | 62325888% | Planned Total Cost |  |  | 77907.36 | [12 empty] | 350583.12 | 116861.04 | 77907.36
|  |  | JDH3-02-008-Material Delivery on Site-Street Lighting Network -SL-Z02-1 |  | 2024-08-30 | 2024-12-04 | 01-May-25 A | 2025-10-13 | 545351.52 | 545351.52 | 62325888% | Remaining Total Cost | [15 empty] | 77907.36
|  |  | JDH3-02-008-Material Delivery on Site-Street Lighting Network -SL-Z02-1 |  | 2024-08-30 | 2024-12-04 | 01-May-25 A | 2025-10-13 | 545351.52 | 545351.52 | 62325888% | Actual Total Cost | [10 empty] | 26251.39 | 25404.57 | 73552.29 | 420143.26
|  |  | JDH3-02-008-Material Delivery on Site-Telecommunications Network - TC-Z02-1 |  | 2024-12-05 | 2024-12-28 | 2025-10-02 | 2025-10-25 | 0 | 0 | 5447944% | Planned Total Cost | [15 empty] | 54479.44
|  |  | JDH3-02-008-Material Delivery on Site-Telecommunications Network - TC-Z02-1 |  | 2024-12-05 | 2024-12-28 | 2025-10-02 | 2025-10-25 | 0 | 0 | 5447944% | Remaining Total Cost | [15 empty] | 54479.44
|  |  | JDH3-02-008-Material Delivery on Site-Telecommunications Network - TC-Z02-1 |  | 2024-12-05 | 2024-12-28 | 2025-10-02 | 2025-10-25 | 0 | 0 | 5447944% | Actual Total Cost
|  |  | JDH3-02-008-Material Delivery on Site-Z02-2 |  | 2024-08-28 | 2025-04-14 | 31-Dec-24 A | 2026-02-06 | 5992061.09 | 5992061.09 | 602430665% | Planned Total Cost |  | 101206.67 | 1330736.41 | 174662102% | 149366139% | 78374069% | 48001.43 | 195940.86 | 201260.68 | 90891.92 | [7 empty] | 12360.8 | 16660.21 | 3224.56
|  |  | JDH3-02-008-Material Delivery on Site-Z02-2 |  | 2024-08-28 | 2025-04-14 | 31-Dec-24 A | 2026-02-06 | 5992061.09 | 5992061.09 | 602430665% | Remaining Total Cost | [17 empty] | 12360.8 | 16660.21 | 3224.56
|  |  | JDH3-02-008-Material Delivery on Site-Z02-2 |  | 2024-08-28 | 2025-04-14 | 31-Dec-24 A | 2026-02-06 | 5992061.09 | 5992061.09 | 602430665% | Actual Total Cost | [5 empty] | 181558% | 517573.8 | 722289.58 | 871531.26 | 737959.83 | 1177534.18 | 980118.27 | 983238.59
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z02-2 |  | 2024-09-01 | 2025-02-16 | 02-Jan-25 A | 2026-02-06 | 548174.61 | 548174.61 | 58042017% | Planned Total Cost |  |  | 155853.56 | 16660209% | 14510504% | 1612278% |  | 64491.13 | [9 empty] | 12360.8 | 16660.21 | 3224.56
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z02-2 |  | 2024-09-01 | 2025-02-16 | 02-Jan-25 A | 2026-02-06 | 548174.61 | 548174.61 | 58042017% | Remaining Total Cost | [17 empty] | 12360.8 | 16660.21 | 3224.56
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z02-2 |  | 2024-09-01 | 2025-02-16 | 02-Jan-25 A | 2026-02-06 | 548174.61 | 548174.61 | 58042017% | Actual Total Cost | [6 empty] | 171304.57 | 159884.26 | 177014.72 | 39971.07
|  |  | JDH3-02-008-Material Delivery on Site-Sewage Network - SS-Z02-2 |  | 2024-08-28 | 2024-12-06 | 31-Dec-24 A | 31-Jul-25 A | 1045773.84 | 1045773.84 | 104577384% | Planned Total Cost |  | 58098.55 | 116197.09 | 34859128% | 43573910% | 8714782%
|  |  | JDH3-02-008-Material Delivery on Site-Sewage Network - SS-Z02-2 |  | 2024-08-28 | 2024-12-06 | 31-Dec-24 A | 31-Jul-25 A | 1045773.84 | 1045773.84 | 104577384% | Remaining Total Cost
|  |  | JDH3-02-008-Material Delivery on Site-Sewage Network - SS-Z02-2 |  | 2024-08-28 | 2024-12-06 | 31-Dec-24 A | 31-Jul-25 A | 1045773.84 | 1045773.84 | 104577384% | Actual Total Cost | [5 empty] | 181558% | 143430.79 | 152508.69 | 221500.71 | 163402.16 | 166043.01 | 124779.83 | 72293.08
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z02-2 |  | 2024-08-31 | 2024-12-21 | 01-Jan-25 A | 31-Jul-25 A | 3373166.16 | 3373166.16 | 337316616% | Planned Total Cost |  | 30117.56 | 873409.1 | 93364421% | 90352665% | 63246866%
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z02-2 |  | 2024-08-31 | 2024-12-21 | 01-Jan-25 A | 31-Jul-25 A | 3373166.16 | 3373166.16 | 337316616% | Remaining Total Cost
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z02-2 |  | 2024-08-31 | 2024-12-21 | 01-Jan-25 A | 31-Jul-25 A | 3373166.16 | 3373166.16 | 337316616% | Actual Total Cost | [6 empty] | 191999.41 | 399057.6 | 466822.1 | 534586.6 | 708434.48 | 545858.81 | 526407.15
|  |  | JDH3-02-008-Material Delivery on Site-Potable Water Network - WT-Z02-2 |  | 2024-11-25 | 2025-02-22 | 01-Jan-25 A | 31-Jul-25 A | 2281-07-19 | 2281-07-19 | 13935900% | Planned Total Cost |  |  |  |  | 929060% | 4800143% | 48001.43 | 34065.53
|  |  | JDH3-02-008-Material Delivery on Site-Potable Water Network - WT-Z02-2 |  | 2024-11-25 | 2025-02-22 | 01-Jan-25 A | 31-Jul-25 A | 2281-07-19 | 2281-07-19 | 13935900% | Remaining Total Cost
|  |  | JDH3-02-008-Material Delivery on Site-Potable Water Network - WT-Z02-2 |  | 2024-11-25 | 2025-02-22 | 01-Jan-25 A | 31-Jul-25 A | 2281-07-19 | 2281-07-19 | 13935900% | Actual Total Cost | [6 empty] | 10839.03 | 10839.03 | 6193.73 |  | 7055.93 | 19518.95 | 84912.32
|  |  | JDH3-02-008-Material Delivery on Site-Street Lighting Network -SL-Z02-2 |  | 2024-09-26 | 2025-04-14 | 01-May-25 A | 31-Jul-25 A | 623258.88 | 623258.88 | 62325888% | Planned Total Cost |  |  | 32461.4 | 20126068% |  |  |  | 97384.2 | 201260.68 | 90891.92
|  |  | JDH3-02-008-Material Delivery on Site-Street Lighting Network -SL-Z02-2 |  | 2024-09-26 | 2025-04-14 | 01-May-25 A | 31-Jul-25 A | 623258.88 | 623258.88 | 62325888% | Remaining Total Cost
|  |  | JDH3-02-008-Material Delivery on Site-Street Lighting Network -SL-Z02-2 |  | 2024-09-26 | 2025-04-14 | 01-May-25 A | 31-Jul-25 A | 623258.88 | 623258.88 | 62325888% | Actual Total Cost | [10 empty] | 210011.14 | 203236.59 | 210011.14
|  |  | JDH3-02-008-Material Delivery on Site-Telecommunications Network - TC-Z02-2 |  | 2024-09-01 | 2024-10-19 | 01-May-25 A | 31-Jul-25 A | 2049-02-25 10:34 | 2049-02-25 10:34 | 5447944% | Planned Total Cost |  |  | 27239.72 | 2723972%
|  |  | JDH3-02-008-Material Delivery on Site-Telecommunications Network - TC-Z02-2 |  | 2024-09-01 | 2024-10-19 | 01-May-25 A | 31-Jul-25 A | 2049-02-25 10:34 | 2049-02-25 10:34 | 5447944% | Remaining Total Cost
|  |  | JDH3-02-008-Material Delivery on Site-Telecommunications Network - TC-Z02-2 |  | 2024-09-01 | 2024-10-19 | 01-May-25 A | 31-Jul-25 A | 2049-02-25 10:34 | 2049-02-25 10:34 | 5447944% | Actual Total Cost | [10 empty] | 18357.2 | 17765.03 | 18357.2
|  |  | JDH3-02-008-Material Delivery on Site-Road Works - RD-Z02-2 |  | 2024-08-29 | 2024-10-16 | 01-May-25 A | 31-Jul-25 A | 207849.16 | 207849.16 | 20784916% | Planned Total Cost |  | 12990.57 | 125575.53 | 6928305%
|  |  | JDH3-02-008-Material Delivery on Site-Road Works - RD-Z02-2 |  | 2024-08-29 | 2024-10-16 | 01-May-25 A | 31-Jul-25 A | 207849.16 | 207849.16 | 20784916% | Remaining Total Cost
|  |  | JDH3-02-008-Material Delivery on Site-Road Works - RD-Z02-2 |  | 2024-08-29 | 2024-10-16 | 01-May-25 A | 31-Jul-25 A | 207849.16 | 207849.16 | 20784916% | Actual Total Cost | [10 empty] | 67632.41 | 68959.06 | 71257.69
|  |  | JDH3-02-008-Material Delivery on Site-Z03 |  | 2025-07-28 | 2025-11-12 | 04-Dec-24 A | 2025-10-23 | 515929.04 | 515929.04 | 58042017% | Planned Total Cost | [13 empty] | 59116.87 | 32245.57 | 338578.43 | 21497.04 |  |  | 118233.74 | 10748.52
|  |  | JDH3-02-008-Material Delivery on Site-Z03 |  | 2025-07-28 | 2025-11-12 | 04-Dec-24 A | 2025-10-23 | 515929.04 | 515929.04 | 58042017% | Remaining Total Cost | [15 empty] | 64491.13
|  |  | JDH3-02-008-Material Delivery on Site-Z03 |  | 2025-07-28 | 2025-11-12 | 04-Dec-24 A | 2025-10-23 | 515929.04 | 515929.04 | 58042017% | Actual Total Cost | [5 empty] | 1880991% | 20825.26 | 37619.83 | 46353 | 40306.96 | 25527.74 | 4030.7 |  | 296594.22 | 25861.43
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z03 |  | 2025-07-28 | 2025-11-12 | 04-Dec-24 A | 2025-10-23 | 515929.04 | 515929.04 | 58042017% | Planned Total Cost | [13 empty] | 59116.87 | 32245.57 | 338578.43 | 21497.04 |  |  | 118233.74 | 10748.52
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z03 |  | 2025-07-28 | 2025-11-12 | 04-Dec-24 A | 2025-10-23 | 515929.04 | 515929.04 | 58042017% | Remaining Total Cost | [15 empty] | 64491.13
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z03 |  | 2025-07-28 | 2025-11-12 | 04-Dec-24 A | 2025-10-23 | 515929.04 | 515929.04 | 58042017% | Actual Total Cost | [5 empty] | 1880991% | 20825.26 | 37619.83 | 46353 | 40306.96 | 25527.74 | 4030.7 |  | 296594.22 | 25861.43
|  |  | JDH3-02-008-Material Delivery on Site-Z04 |  | 2025-11-13 | 2026-03-10 | 11-Jan-25 A | 2025-12-12 | 1522901.83 | 1522901.83 | 395358633% | Planned Total Cost | [14 empty] | 105411.44 | 1162207.71 | 1195310.91 | 539464.75 | 804968.23 | 146223.28
|  |  | JDH3-02-008-Material Delivery on Site-Z04 |  | 2025-11-13 | 2026-03-10 | 11-Jan-25 A | 2025-12-12 | 1522901.83 | 1522901.83 | 395358633% | Remaining Total Cost | [15 empty] | 845973.38 | 1163065.35 | 421645.77
|  |  | JDH3-02-008-Material Delivery on Site-Z04 |  | 2025-11-13 | 2026-03-10 | 11-Jan-25 A | 2025-12-12 | 1522901.83 | 1522901.83 | 395358633% | Actual Total Cost | [6 empty] | 14107.43 | 18809.91 | 111785.77 | 253076.4 | 266329.21 | 241357.53 | 195789.8 |  | 421645.77
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z04 |  | 2025-11-13 | 2026-02-26 | 12-Mar-25 A | 2025-12-12 | 1264937.31 | 1264937.31 | 337316616% | Planned Total Cost | [14 empty] | 105411.44 | 948702.98 | 1054114.43 | 442728.06 | 761974.14 | 60235.11
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z04 |  | 2025-11-13 | 2026-02-26 | 12-Mar-25 A | 2025-12-12 | 1264937.31 | 1264937.31 | 337316616% | Remaining Total Cost | [15 empty] | 632468.66 | 1054114.43 | 421645.77
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z04 |  | 2025-11-13 | 2026-02-26 | 12-Mar-25 A | 2025-12-12 | 1264937.31 | 1264937.31 | 337316616% | Actual Total Cost | [8 empty] | 59386.73 | 202020.92 | 208754.95 | 202020.92 | 171108.01 |  | 421645.77
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z04 |  | 2025-11-25 | 2026-03-10 | 11-Jan-25 A | 2025-11-17 | 257964.52 | 257964.52 | 58042017% | Planned Total Cost | [15 empty] | 213504.73 | 141196.49 | 96736.7 | 42994.09 | 85988.17
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z04 |  | 2025-11-25 | 2026-03-10 | 11-Jan-25 A | 2025-11-17 | 257964.52 | 257964.52 | 58042017% | Remaining Total Cost | [15 empty] | 213504.73 | 108950.92
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z04 |  | 2025-11-25 | 2026-03-10 | 11-Jan-25 A | 2025-11-17 | 257964.52 | 257964.52 | 58042017% | Actual Total Cost | [6 empty] | 14107.43 | 18809.91 | 52399.04 | 51055.48 | 57574.26 | 39336.6 | 24681.79
|  |  | JDH3-02-008-Material Delivery on Site-Z05 |  | 2024-11-24 | 2025-07-14 | 29-Dec-24 A | 2025-10-31 | 1522901.83 | 1522901.83 | 395358633% | Planned Total Cost | [6 empty] | 692703.77 | 166710.56 | 112859.48 |  |  | 107485.22 | 21497.04 |  |  | 2852330.27
|  |  | JDH3-02-008-Material Delivery on Site-Z05 |  | 2024-11-24 | 2025-07-14 | 29-Dec-24 A | 2025-10-31 | 1522901.83 | 1522901.83 | 395358633% | Remaining Total Cost | [15 empty] | 2430684.5
|  |  | JDH3-02-008-Material Delivery on Site-Z05 |  | 2024-11-24 | 2025-07-14 | 29-Dec-24 A | 2025-10-31 | 1522901.83 | 1522901.83 | 395358633% | Actual Total Cost | [5 empty] | 201535% | 20825.26 | 18809.91 | 140672.42 | 264496.71 | 271230.74 | 212097.66 | 171108.01 |  | 421645.77
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z05 |  | 2024-11-24 | 2025-02-25 | 12-Mar-25 A | 2025-10-31 | 1264937.31 | 1264937.31 | 337316616% | Planned Total Cost | [6 empty] | 692703.77 | 150587.78 | [7 empty] | 2529874.62
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z05 |  | 2024-11-24 | 2025-02-25 | 12-Mar-25 A | 2025-10-31 | 1264937.31 | 1264937.31 | 337316616% | Remaining Total Cost | [15 empty] | 2108228.85
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z05 |  | 2024-11-24 | 2025-02-25 | 12-Mar-25 A | 2025-10-31 | 1264937.31 | 1264937.31 | 337316616% | Actual Total Cost | [8 empty] | 59386.73 | 202020.92 | 208754.95 | 202020.92 | 171108.01 |  | 421645.77
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z05 |  | 2025-02-26 | 2025-07-14 | 29-Dec-24 A | 2025-10-21 | 257964.52 | 257964.52 | 58042017% | Planned Total Cost | [7 empty] | 16122.78 | 112859.48 |  |  | 107485.22 | 21497.04 |  |  | 322455.65
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z05 |  | 2025-02-26 | 2025-07-14 | 29-Dec-24 A | 2025-10-21 | 257964.52 | 257964.52 | 58042017% | Remaining Total Cost | [15 empty] | 322455.65
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z05 |  | 2025-02-26 | 2025-07-14 | 29-Dec-24 A | 2025-10-21 | 257964.52 | 257964.52 | 58042017% | Actual Total Cost | [5 empty] | 201535% | 20825.26 | 18809.91 | 81285.7 | 62475.78 | 62475.78 | 10076.74
|  |  | JDH3-02-008-Material Delivery on Site-Z06 |  | 2024-10-07 | 2025-07-27 | 10-Nov-24 A | 2025-11-24 | 2005479.57 | 2005479.57 | 409294533% | Planned Total Cost |  |  |  | 45176333% | 60235110% | 63246866% |  |  |  | 64491.13 |  | 64491.13 | 64491.13 |  |  | 1973967.83 | 175435.26 | 48001.43 | 15484.33
|  |  | JDH3-02-008-Material Delivery on Site-Z06 |  | 2024-10-07 | 2025-07-27 | 10-Nov-24 A | 2025-11-24 | 2005479.57 | 2005479.57 | 409294533% | Remaining Total Cost | [15 empty] | 1958483.5 | 128982.26
|  |  | JDH3-02-008-Material Delivery on Site-Z06 |  | 2024-10-07 | 2025-07-27 | 10-Nov-24 A | 2025-11-24 | 2005479.57 | 2005479.57 | 409294533% | Actual Total Cost |  |  |  |  | 7905858% | 11670553% | 129469.4 | 124221.36 | 279890.27 | 391221.54 | 391767.1 | 310547.09 | 98983.31 | 83615.4
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z06 |  | 2024-10-07 | 2025-01-10 | 10-Nov-24 A | 2025-10-21 | 1686583.08 | 1686583.08 | 337316616% | Planned Total Cost |  |  |  | 45176333% | 60235110% | 63246866% | [9 empty] | 1686583.08
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z06 |  | 2024-10-07 | 2025-01-10 | 10-Nov-24 A | 2025-10-21 | 1686583.08 | 1686583.08 | 337316616% | Remaining Total Cost | [15 empty] | 1686583.08
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z06 |  | 2024-10-07 | 2025-01-10 | 10-Nov-24 A | 2025-10-21 | 1686583.08 | 1686583.08 | 337316616% | Actual Total Cost |  |  |  |  | 7905858% | 11670553% | 116705.53 | 105411.44 | 222116.97 | 338822.49 | 350116.58 | 278587.38 | 79058.58
|  |  | JDH3-02-008-Material Delivery on Site-Potable Water Network - WT-Z06 |  | 2025-01-11 | 2025-04-10 | 10-Jun-25 A | 2025-10-16 | 2243-05-24 02:24 | 2243-05-24 02:24 | 13935900% | Planned Total Cost | [15 empty] | 29420.23 | 46453 | 48001.43 | 15484.33
|  |  | JDH3-02-008-Material Delivery on Site-Potable Water Network - WT-Z06 |  | 2025-01-11 | 2025-04-10 | 10-Jun-25 A | 2025-10-16 | 2243-05-24 02:24 | 2243-05-24 02:24 | 13935900% | Remaining Total Cost | [15 empty] | 13935.9
|  |  | JDH3-02-008-Material Delivery on Site-Potable Water Network - WT-Z06 |  | 2025-01-11 | 2025-04-10 | 10-Jun-25 A | 2025-10-16 | 2243-05-24 02:24 | 2243-05-24 02:24 | 13935900% | Actual Total Cost | [11 empty] | 21882.97 | 19924.73 | 83615.4
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z06 |  | 2025-04-11 | 2025-07-27 | 13-Jan-25 A | 2025-11-24 | 2429-09-15 09:22 | 2429-09-15 09:22 | 58042017% | Planned Total Cost | [9 empty] | 64491.13 |  | 64491.13 | 64491.13 |  |  | 257964.52 | 128982.26
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z06 |  | 2025-04-11 | 2025-07-27 | 13-Jan-25 A | 2025-11-24 | 2429-09-15 09:22 | 2429-09-15 09:22 | 58042017% | Remaining Total Cost | [15 empty] | 257964.52 | 128982.26
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z06 |  | 2025-04-11 | 2025-07-27 | 13-Jan-25 A | 2025-11-24 | 2429-09-15 09:22 | 2429-09-15 09:22 | 58042017% | Actual Total Cost | [6 empty] | 12763.87 | 18809.91 | 57773.3 | 52399.04 | 41650.52 | 10076.74
|  |  | JDH3-02-008-Material Delivery on Site-Z07 |  | 2024-08-31 | 2025-02-16 | 10-Nov-24 A | 2026-02-06 | 2816525.55 | 2816525.55 | 409294533% | Planned Total Cost |  | 35137.15 | 1018977.28 | 66760580% | 95325944% | 1612278% | [9 empty] | 1217117.02 | 152480.3 | 12360.8 | 16660.21 | 3224.56
|  |  | JDH3-02-008-Material Delivery on Site-Z07 |  | 2024-08-31 | 2025-02-16 | 10-Nov-24 A | 2026-02-06 | 2816525.55 | 2816525.55 | 409294533% | Remaining Total Cost | [15 empty] | 1147437.52 | 96736.7 | 12360.8 | 16660.21 | 3224.56
|  |  | JDH3-02-008-Material Delivery on Site-Z07 |  | 2024-08-31 | 2025-02-16 | 10-Nov-24 A | 2026-02-06 | 2816525.55 | 2816525.55 | 409294533% | Actual Total Cost |  |  |  |  | 17568574% | 62833573% | 701607.49 | 620405.78 | 323755.38 | 161994.52 | 79317.81 | 21882.97 | 19924.73 | 83615.4
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z07 |  | 2024-08-31 | 2024-12-05 | 10-Nov-24 A | 2025-10-25 | 2529874.62 | 2529874.62 | 337316616% | Planned Total Cost |  | 35137.15 | 1018977.28 | 66760580% | 80815439% | [10 empty] | 843291.54
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z07 |  | 2024-08-31 | 2024-12-05 | 10-Nov-24 A | 2025-10-25 | 2529874.62 | 2529874.62 | 337316616% | Remaining Total Cost | [15 empty] | 843291.54
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z07 |  | 2024-08-31 | 2024-12-05 | 10-Nov-24 A | 2025-10-25 | 2529874.62 | 2529874.62 | 337316616% | Actual Total Cost |  |  |  |  | 17568574% | 61490008% | 680782.23 | 579762.93 | 281097.18 | 131764.3 | 65882.15
|  |  | JDH3-02-008-Material Delivery on Site-Potable Water Network - WT-Z07 |  | 2024-09-01 | 2024-10-31 | 10-Jun-25 A | 2025-10-07 | 2243-05-24 02:24 | 2243-05-24 02:24 | 13935900% | Planned Total Cost | [15 empty] | 83615.4 | 55743.6
|  |  | JDH3-02-008-Material Delivery on Site-Potable Water Network - WT-Z07 |  | 2024-09-01 | 2024-10-31 | 10-Jun-25 A | 2025-10-07 | 2243-05-24 02:24 | 2243-05-24 02:24 | 13935900% | Remaining Total Cost | [15 empty] | 13935.9
|  |  | JDH3-02-008-Material Delivery on Site-Potable Water Network - WT-Z07 |  | 2024-09-01 | 2024-10-31 | 10-Jun-25 A | 2025-10-07 | 2243-05-24 02:24 | 2243-05-24 02:24 | 13935900% | Actual Total Cost | [11 empty] | 21882.97 | 19924.73 | 83615.4
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z07 |  | 2024-09-01 | 2025-02-16 | 12-Dec-24 A | 2026-02-06 | 2341-06-03 19:55 | 2341-06-03 19:55 | 58042017% | Planned Total Cost |  |  |  |  | 14510504% | 1612278% | [9 empty] | 290210.09 | 96736.7 | 12360.8 | 16660.21 | 3224.56
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z07 |  | 2024-09-01 | 2025-02-16 | 12-Dec-24 A | 2026-02-06 | 2341-06-03 19:55 | 2341-06-03 19:55 | 58042017% | Remaining Total Cost | [15 empty] | 290210.09 | 96736.7 | 12360.8 | 16660.21 | 3224.56
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z07 |  | 2024-09-01 | 2025-02-16 | 12-Dec-24 A | 2026-02-06 | 2341-06-03 19:55 | 2341-06-03 19:55 | 58042017% | Actual Total Cost | [5 empty] | 1343565% | 20825.26 | 40642.85 | 42658.2 | 30230.22 | 13435.65
|  |  | JDH3-02-008-Material Delivery on Site-Z07-1 |  | 2024-08-28 | 2024-12-28 | 07-Nov-24 A | 2025-10-28 | 3843955.06 | 3843955.06 | 581645749% | Planned Total Cost |  | 93235.69 | 1162045.68 | 106775281% | 81571382% | 4836835% | [9 empty] | 2314857.69 | 236576.1 | 77907.36
|  |  | JDH3-02-008-Material Delivery on Site-Z07-1 |  | 2024-08-28 | 2024-12-28 | 07-Nov-24 A | 2025-10-28 | 3843955.06 | 3843955.06 | 581645749% | Remaining Total Cost | [15 empty] | 1972502.43
|  |  | JDH3-02-008-Material Delivery on Site-Z07-1 |  | 2024-08-28 | 2024-12-28 | 07-Nov-24 A | 2025-10-28 | 3843955.06 | 3843955.06 | 581645749% | Actual Total Cost |  |  |  |  | 4872628% | 45408284% | 710709.44 | 647814.53 | 476297.06 | 356465.13 | 379079.22 | 301392.16 | 149316.27 | 320072.14
|  |  | JDH3-02-008-Material Delivery on Site-Sewage Network - SS-Z07-1 |  | 2024-08-28 | 2024-12-06 | 09-Nov-24 A | 2025-10-13 | 871478.2 | 871478.2 | 104577384% | Planned Total Cost |  | 58098.55 | 116197.09 | 34859128% | 34859128% | [10 empty] | 174295.64
|  |  | JDH3-02-008-Material Delivery on Site-Sewage Network - SS-Z07-1 |  | 2024-08-28 | 2024-12-06 | 09-Nov-24 A | 2025-10-13 | 871478.2 | 871478.2 | 104577384% | Remaining Total Cost | [15 empty] | 174295.64
|  |  | JDH3-02-008-Material Delivery on Site-Sewage Network - SS-Z07-1 |  | 2024-08-28 | 2024-12-06 | 09-Nov-24 A | 2025-10-13 | 871478.2 | 871478.2 | 104577384% | Actual Total Cost |  |  |  |  | 4175833% | 19789817% | 281414.84 | 225131.87 | 114381.51 | 10893.48
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z07-1 |  | 2024-08-31 | 2024-12-05 | 04-Dec-24 A | 2025-10-25 | 2108228.85 | 2108228.85 | 337316616% | Planned Total Cost |  | 35137.15 | 1018977.28 | 66760580% | 38650862% | [10 empty] | 1264937.31
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z07-1 |  | 2024-08-31 | 2024-12-05 | 04-Dec-24 A | 2025-10-25 | 2108228.85 | 2108228.85 | 337316616% | Remaining Total Cost | [15 empty] | 1264937.31
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z07-1 |  | 2024-08-31 | 2024-12-05 | 04-Dec-24 A | 2025-10-25 | 2108228.85 | 2108228.85 | 337316616% | Actual Total Cost | [5 empty] | 22839146% | 408469.34 | 368940.05 | 316234.33 | 263528.61 | 272312.89 | 228391.46 | 21960.72
|  |  | JDH3-02-008-Material Delivery on Site-Potable Water Network - WT-Z07-1 |  | 2024-09-01 | 2024-10-31 | 07-Nov-24 A | 2025-10-07 | 2243-05-24 02:24 | 2243-05-24 02:24 | 13935900% | Planned Total Cost |  |  |  | 1393590% | [11 empty] | 83615.4 | 41807.7
|  |  | JDH3-02-008-Material Delivery on Site-Potable Water Network - WT-Z07-1 |  | 2024-09-01 | 2024-10-31 | 07-Nov-24 A | 2025-10-07 | 2243-05-24 02:24 | 2243-05-24 02:24 | 13935900% | Remaining Total Cost | [15 empty] | 13935.9
|  |  | JDH3-02-008-Material Delivery on Site-Potable Water Network - WT-Z07-1 |  | 2024-09-01 | 2024-10-31 | 07-Nov-24 A | 2025-10-07 | 2243-05-24 02:24 | 2243-05-24 02:24 | 13935900% | Actual Total Cost |  |  |  |  | 696795% | 696795% |  |  |  |  | 6000.18 | 22191.55 | 27551.87 | 55743.6
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z07-1 |  | 2024-09-01 | 2024-12-21 | 01-Dec-24 A | 2025-10-28 | 2429-09-15 09:22 | 2429-09-15 09:22 | 58042017% | Planned Total Cost |  |  | 26871.3 | 3761983% | 8061391% | 4836835% | [9 empty] | 386946.78
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z07-1 |  | 2024-09-01 | 2024-12-21 | 01-Dec-24 A | 2025-10-28 | 2429-09-15 09:22 | 2429-09-15 09:22 | 58042017% | Remaining Total Cost | [15 empty] | 386946.78
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z07-1 |  | 2024-09-01 | 2024-12-21 | 01-Dec-24 A | 2025-10-28 | 2429-09-15 09:22 | 2429-09-15 09:22 | 58042017% | Actual Total Cost | [5 empty] | 2082526% | 20825.26 | 53742.61 | 45681.22 | 40306.96 | 12092.09
|  |  | JDH3-02-008-Material Delivery on Site-Street Lighting Network -SL-Z07-1 |  | 2024-08-30 | 2024-12-04 | 16-Apr-25 A | 2025-10-13 | 545351.52 | 545351.52 | 62325888% | Planned Total Cost | [15 empty] | 350583.12 | 194768.4 | 77907.36
|  |  | JDH3-02-008-Material Delivery on Site-Street Lighting Network -SL-Z07-1 |  | 2024-08-30 | 2024-12-04 | 16-Apr-25 A | 2025-10-13 | 545351.52 | 545351.52 | 62325888% | Remaining Total Cost | [15 empty] | 77907.36
|  |  | JDH3-02-008-Material Delivery on Site-Street Lighting Network -SL-Z07-1 |  | 2024-08-30 | 2024-12-04 | 16-Apr-25 A | 2025-10-13 | 545351.52 | 545351.52 | 62325888% | Actual Total Cost | [9 empty] | 41736.09 | 88674.06 | 50809.15 | 99803.68 | 264328.54
|  |  | JDH3-02-008-Material Delivery on Site-Telecommunications Network - TC-Z07-1 |  | 2024-12-05 | 2024-12-28 | 2025-10-02 | 2025-10-25 | 0 | 0 | 5447944% | Planned Total Cost | [15 empty] | 54479.44
|  |  | JDH3-02-008-Material Delivery on Site-Telecommunications Network - TC-Z07-1 |  | 2024-12-05 | 2024-12-28 | 2025-10-02 | 2025-10-25 | 0 | 0 | 5447944% | Remaining Total Cost | [15 empty] | 54479.44
|  |  | JDH3-02-008-Material Delivery on Site-Telecommunications Network - TC-Z07-1 |  | 2024-12-05 | 2024-12-28 | 2025-10-02 | 2025-10-25 | 0 | 0 | 5447944% | Actual Total Cost
|  |  | JDH3-02-008-Material Delivery on Site-Z08 |  | 2025-11-01 | 2026-01-24 | 04-Dec-24 A | 2025-10-31 | 2298728.52 | 2298728.52 | 416143549% | Planned Total Cost | [14 empty] | 31177.37 | 1935454.18 | 1790507.66 | 404296.28
|  |  | JDH3-02-008-Material Delivery on Site-Z08 |  | 2025-11-01 | 2026-01-24 | 04-Dec-24 A | 2025-10-31 | 2298728.52 | 2298728.52 | 416143549% | Remaining Total Cost | [15 empty] | 1862706.98
|  |  | JDH3-02-008-Material Delivery on Site-Z08 |  | 2025-11-01 | 2026-01-24 | 04-Dec-24 A | 2025-10-31 | 2298728.52 | 2298728.52 | 416143549% | Actual Total Cost | [5 empty] | 21950190% | 248161.03 | 219554.27 | 304506.13 | 377128.48 | 340310.98 | 291315.95 | 298249.78
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z08 |  | 2025-11-01 | 2025-12-25 | 04-Dec-24 A | 2025-10-20 | 1897405.97 | 1897405.97 | 337316616% | Planned Total Cost | [15 empty] | 1475760.2 | 1686583.08 | 210822.89
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z08 |  | 2025-11-01 | 2025-12-25 | 04-Dec-24 A | 2025-10-20 | 1897405.97 | 1897405.97 | 337316616% | Remaining Total Cost | [15 empty] | 1475760.2
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z08 |  | 2025-11-01 | 2025-12-25 | 04-Dec-24 A | 2025-10-20 | 1897405.97 | 1897405.97 | 337316616% | Actual Total Cost | [5 empty] | 9825656% | 201427.42 | 181934.44 | 242030.35 | 288628.82 | 298249.78 | 288628.82 | 298249.78
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z08 |  | 2025-11-23 | 2026-01-04 | 14-Jan-25 A | 2025-10-31 | 2429-09-15 09:22 | 2429-09-15 09:22 | 58042017% | Planned Total Cost | [15 empty] | 386946.78 |  | 193473.39
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z08 |  | 2025-11-23 | 2026-01-04 | 14-Jan-25 A | 2025-10-31 | 2429-09-15 09:22 | 2429-09-15 09:22 | 58042017% | Remaining Total Cost | [15 empty] | 386946.78
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z08 |  | 2025-11-23 | 2026-01-04 | 14-Jan-25 A | 2025-10-31 | 2429-09-15 09:22 | 2429-09-15 09:22 | 58042017% | Actual Total Cost | [6 empty] | 12092.09 | 37619.83 | 62475.78 | 53070.83 | 25527.74 | 2687.13
|  |  | JDH3-02-008-Material Delivery on Site-Road Works - RD-Z08 |  | 2025-12-15 | 2026-01-24 | 04-Dec-24 A | 07-May-25 A | 207849.16 | 207849.16 | 20784916% | Planned Total Cost | [14 empty] | 31177.37 | 72747.21 | 103924.58
|  |  | JDH3-02-008-Material Delivery on Site-Road Works - RD-Z08 |  | 2025-12-15 | 2026-01-24 | 04-Dec-24 A | 07-May-25 A | 207849.16 | 207849.16 | 20784916% | Remaining Total Cost
|  |  | JDH3-02-008-Material Delivery on Site-Road Works - RD-Z08 |  | 2025-12-15 | 2026-01-24 | 04-Dec-24 A | 07-May-25 A | 207849.16 | 207849.16 | 20784916% | Actual Total Cost | [5 empty] | 12124534% | 34641.53 |  |  | 35428.83 | 16533.46
|  |  | JDH3-02-008-Material Delivery on Site-Z09 |  | 2026-01-25 | 2026-03-01 | 2025-10-14 | 2025-12-24 | 0 | 0 | 15581485% | Planned Total Cost | [15 empty] | 51938.28 | 51938.28 | 51938.28
|  |  | JDH3-02-008-Material Delivery on Site-Z09 |  | 2026-01-25 | 2026-03-01 | 2025-10-14 | 2025-12-24 | 0 | 0 | 15581485% | Remaining Total Cost | [15 empty] | 51938.28 | 51938.28 | 51938.28
|  |  | JDH3-02-008-Material Delivery on Site-Z09 |  | 2026-01-25 | 2026-03-01 | 2025-10-14 | 2025-12-24 | 0 | 0 | 15581485% | Actual Total Cost
|  |  | JDH3-02-008-Material Delivery on Site-Sewage Network - SS-Z09 |  | 2026-01-25 | 2026-03-01 | 2025-10-14 | 2025-12-24 | 0 | 0 | 15581485% | Planned Total Cost | [15 empty] | 51938.28 | 51938.28 | 51938.28
|  |  | JDH3-02-008-Material Delivery on Site-Sewage Network - SS-Z09 |  | 2026-01-25 | 2026-03-01 | 2025-10-14 | 2025-12-24 | 0 | 0 | 15581485% | Remaining Total Cost | [15 empty] | 51938.28 | 51938.28 | 51938.28
|  |  | JDH3-02-008-Material Delivery on Site-Sewage Network - SS-Z09 |  | 2026-01-25 | 2026-03-01 | 2025-10-14 | 2025-12-24 | 0 | 0 | 15581485% | Actual Total Cost
|  |  | JDH3-02-008-Material Delivery on Site-Z10 |  | 2026-02-06 | 2026-03-19 | 2025-11-04 | 2026-01-02 | 0 | 0 | 15581485% | Planned Total Cost | [16 empty] | 77907.43 | 77907.43
|  |  | JDH3-02-008-Material Delivery on Site-Z10 |  | 2026-02-06 | 2026-03-19 | 2025-11-04 | 2026-01-02 | 0 | 0 | 15581485% | Remaining Total Cost | [16 empty] | 77907.43 | 77907.43
|  |  | JDH3-02-008-Material Delivery on Site-Z10 |  | 2026-02-06 | 2026-03-19 | 2025-11-04 | 2026-01-02 | 0 | 0 | 15581485% | Actual Total Cost
|  |  | JDH3-02-008-Material Delivery on Site-Sewage Network - SS-Z10 |  | 2026-02-06 | 2026-03-19 | 2025-11-04 | 2026-01-02 | 0 | 0 | 15581485% | Planned Total Cost | [16 empty] | 77907.43 | 77907.43
|  |  | JDH3-02-008-Material Delivery on Site-Sewage Network - SS-Z10 |  | 2026-02-06 | 2026-03-19 | 2025-11-04 | 2026-01-02 | 0 | 0 | 15581485% | Remaining Total Cost | [16 empty] | 77907.43 | 77907.43
|  |  | JDH3-02-008-Material Delivery on Site-Sewage Network - SS-Z10 |  | 2026-02-06 | 2026-03-19 | 2025-11-04 | 2026-01-02 | 0 | 0 | 15581485% | Actual Total Cost
|  |  | JDH3-02-008-Material Delivery on Site-Z11 |  | 2024-12-29 | 2025-06-08 | 02-Nov-24 A | 2025-12-06 | 1894432.24 | 1894432.25 | 358101532% | Planned Total Cost | [5 empty] | 5270572% | 593817.79 | 562194.36 | 477865.21 | 39837.76 | 64086.82 |  |  |  | 51962.29 | 605372.36 | 929377.55 | 203795.46
|  |  | JDH3-02-008-Material Delivery on Site-Z11 |  | 2024-12-29 | 2025-06-08 | 02-Nov-24 A | 2025-12-06 | 1894432.24 | 1894432.25 | 358101532% | Remaining Total Cost | [15 empty] | 553410.07 | 929377.55 | 203795.46
|  |  | JDH3-02-008-Material Delivery on Site-Z11 |  | 2024-12-29 | 2025-06-08 | 02-Nov-24 A | 2025-12-06 | 1894432.24 | 1894432.25 | 358101532% | Actual Total Cost |  |  |  |  | 1569694% | 16850703% | 205679.18 | 173325.45 | 220842.24 | 295695.83 | 285476.02 | 260267 | 268942.56
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z11 |  | 2024-12-29 | 2025-04-21 | 04-Dec-24 A | 2025-12-06 | 1686583.08 | 1686583.09 | 337316616% | Planned Total Cost | [5 empty] | 5270572% | 593817.79 | 562194.36 | 477865.21 | [6 empty] | 553410.07 | 929377.55 | 203795.46
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z11 |  | 2024-12-29 | 2025-04-21 | 04-Dec-24 A | 2025-12-06 | 1686583.08 | 1686583.09 | 337316616% | Remaining Total Cost | [15 empty] | 553410.07 | 929377.55 | 203795.46
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z11 |  | 2024-12-29 | 2025-04-21 | 04-Dec-24 A | 2025-12-06 | 1686583.08 | 1686583.09 | 337316616% | Actual Total Cost | [5 empty] | 8785723% | 172120.2 | 155463.41 | 212723.13 | 260267 | 268942.56 | 260267 | 268942.56
|  |  | JDH3-02-008-Material Delivery on Site-Road Works - RD-Z11 |  | 2025-04-21 | 2025-06-08 | 02-Nov-24 A | 07-May-25 A | 207849.16 | 207849.16 | 20784916% | Planned Total Cost | [9 empty] | 39837.76 | 64086.82 |  |  |  | 51962.29 | 51962.29
|  |  | JDH3-02-008-Material Delivery on Site-Road Works - RD-Z11 |  | 2025-04-21 | 2025-06-08 | 02-Nov-24 A | 07-May-25 A | 207849.16 | 207849.16 | 20784916% | Remaining Total Cost
|  |  | JDH3-02-008-Material Delivery on Site-Road Works - RD-Z11 |  | 2025-04-21 | 2025-06-08 | 02-Nov-24 A | 07-May-25 A | 207849.16 | 207849.16 | 20784916% | Actual Total Cost |  |  |  |  | 1569694% | 8064980% | 33558.98 | 17862.04 | 8119.11 | 35428.83 | 16533.46
|  |  | JDH3-02-008-Material Delivery on Site-Z12 |  | 2025-06-08 | 2025-10-06 | 04-Dec-24 A | 2025-11-18 | 1686583.08 | 1686583.09 | 337316616% | Planned Total Cost | [11 empty] | 210822.89 | 843291.54 | 632468.66 |  | 1054114.43 | 632468.66
|  |  | JDH3-02-008-Material Delivery on Site-Z12 |  | 2025-06-08 | 2025-10-06 | 04-Dec-24 A | 2025-11-18 | 1686583.08 | 1686583.09 | 337316616% | Remaining Total Cost | [15 empty] | 1054114.43 | 632468.66
|  |  | JDH3-02-008-Material Delivery on Site-Z12 |  | 2025-06-08 | 2025-10-06 | 04-Dec-24 A | 2025-11-18 | 1686583.08 | 1686583.09 | 337316616% | Actual Total Cost | [5 empty] | 8785723% | 172120.2 | 155463.41 | 212723.13 | 260267 | 268942.56 | 260267 | 268942.56
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z12 |  | 2025-06-08 | 2025-10-06 | 04-Dec-24 A | 2025-11-18 | 1686583.08 | 1686583.09 | 337316616% | Planned Total Cost | [11 empty] | 210822.89 | 843291.54 | 632468.66 |  | 1054114.43 | 632468.66
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z12 |  | 2025-06-08 | 2025-10-06 | 04-Dec-24 A | 2025-11-18 | 1686583.08 | 1686583.09 | 337316616% | Remaining Total Cost | [15 empty] | 1054114.43 | 632468.66
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z12 |  | 2025-06-08 | 2025-10-06 | 04-Dec-24 A | 2025-11-18 | 1686583.08 | 1686583.09 | 337316616% | Actual Total Cost | [5 empty] | 8785723% | 172120.2 | 155463.41 | 212723.13 | 260267 | 268942.56 | 260267 | 268942.56
|  |  | JDH3-02-008-Material Delivery on Site-Z13 |  | 2025-07-28 | 2026-04-04 | 04-Dec-24 A | 2026-02-06 | 2816525.55 | 2816525.55 | 409294533% | Planned Total Cost | [13 empty] | 38478.24 | 68767.26 | 1335590.48 | 74053.27 | 26296.7 | 1176186.08 | 565418.92 | 808154.39
|  |  | JDH3-02-008-Material Delivery on Site-Z13 |  | 2025-07-28 | 2026-04-04 | 04-Dec-24 A | 2026-02-06 | 2816525.55 | 2816525.55 | 409294533% | Remaining Total Cost | [15 empty] | 1211928.66 | 32245.57 | 12360.8 | 16660.21 | 3224.56
|  |  | JDH3-02-008-Material Delivery on Site-Z13 |  | 2025-07-28 | 2026-04-04 | 04-Dec-24 A | 2026-02-06 | 2816525.55 | 2816525.55 | 409294533% | Actual Total Cost | [5 empty] | 7355376% | 128229.84 | 130812.43 | 196647.18 | 323644.83 | 490943.9 | 679933.77 | 792759.84
|  |  | JDH3-02-008-Material Delivery on Site-Potable Water Network - WT-Z13 |  | 2025-07-28 | 2025-09-30 | 01-Jan-25 A | 2025-10-07 | 2243-05-24 02:24 | 2243-05-24 02:24 | 13935900% | Planned Total Cost | [13 empty] | 19510.26 | 8361.54 | 55743.6 | 41807.7 | 13935.9
|  |  | JDH3-02-008-Material Delivery on Site-Potable Water Network - WT-Z13 |  | 2025-07-28 | 2025-09-30 | 01-Jan-25 A | 2025-10-07 | 2243-05-24 02:24 | 2243-05-24 02:24 | 13935900% | Remaining Total Cost | [15 empty] | 13935.9
|  |  | JDH3-02-008-Material Delivery on Site-Potable Water Network - WT-Z13 |  | 2025-07-28 | 2025-09-30 | 01-Jan-25 A | 2025-10-07 | 2243-05-24 02:24 | 2243-05-24 02:24 | 13935900% | Actual Total Cost | [6 empty] | 6000.18 | 5419.52 | 2516.2 |  | 11201.36 | 38101.26 | 62184.58
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z13 |  | 2025-08-03 | 2026-01-01 | 14-Jan-25 A | 2026-02-06 | 2341-06-03 19:55 | 2341-06-03 19:55 | 58042017% | Planned Total Cost | [13 empty] | 18967.98 | 60405.72 | 436555.34 | 32245.57 | 12360.8 | 16660.21 | 3224.56
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z13 |  | 2025-08-03 | 2026-01-01 | 14-Jan-25 A | 2026-02-06 | 2341-06-03 19:55 | 2341-06-03 19:55 | 58042017% | Remaining Total Cost | [15 empty] | 354701.22 | 32245.57 | 12360.8 | 16660.21 | 3224.56
|  |  | JDH3-02-008-Material Delivery on Site-TSE Network - TSE-Z13 |  | 2025-08-03 | 2026-01-01 | 14-Jan-25 A | 2026-02-06 | 2341-06-03 19:55 | 2341-06-03 19:55 | 58042017% | Actual Total Cost | [6 empty] | 9673.67 | 23729.43 | 40972.05 | 39650.37 | 26337.53 | 14225.98 | 6638.79
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z13 |  | 2026-01-02 | 2026-04-04 | 04-Dec-24 A | 2025-10-13 | 2529874.62 | 2529874.62 | 337316616% | Planned Total Cost | [15 empty] | 843291.54 |  |  | 1159525.87 | 562194.36 | 808154.39
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z13 |  | 2026-01-02 | 2026-04-04 | 04-Dec-24 A | 2025-10-13 | 2529874.62 | 2529874.62 | 337316616% | Remaining Total Cost | [15 empty] | 843291.54
|  |  | JDH3-02-008-Material Delivery on Site-Storm Network - ST-Z13 |  | 2026-01-02 | 2026-04-04 | 04-Dec-24 A | 2025-10-13 | 2529874.62 | 2529874.62 | 337316616% | Actual Total Cost | [5 empty] | 7355376% | 112556 | 101663.48 | 153158.92 | 283994.45 | 453405.01 | 627606.53 | 723936.47
|  |  | JDH3-02-008-Material Delivery on Site-CCTV System |  | 2026-04-05 | 2026-04-16 | 2025-10-26 | 2025-11-06 | 0 | 0 | 2723972% | Planned Total Cost | [15 empty] | 13619.86 | 13619.86
|  |  | JDH3-02-008-Material Delivery on Site-CCTV System |  | 2026-04-05 | 2026-04-16 | 2025-10-26 | 2025-11-06 | 0 | 0 | 2723972% | Remaining Total Cost | [15 empty] | 13619.86 | 13619.86
|  |  | JDH3-02-008-Material Delivery on Site-CCTV System |  | 2026-04-05 | 2026-04-16 | 2025-10-26 | 2025-11-06 | 0 | 0 | 2723972% | Actual Total Cost
|  |  | JDH3-02-008--Construction |  | 2024-08-17 | 2026-07-09 | 28-Sep-24 A | 2026-07-20 | 93824757.31 | 93824757.41 | 21422906676% | Planned Total Cost |  | 274378.38 | 5439272.93 | 431485945% | 304220128% | 680613627% | 5762730.54 | 4907271.52 | 1889492.5 | 2033806.02 | 1314788.46 | 1182319.31 | 1406640.07 | 4588844.23 | 7436192.31 | 29866810.17 | 26801839.26 | 22399626.96 | 23438631.58 | 18639567.67 | 22577378.07 | 10187180.25 | 7029849.84 | 2350943.16 | 196515.06 | [5 empty] | 46365.97 | 295425.52
|  |  | JDH3-02-008--Construction |  | 2024-08-17 | 2026-07-09 | 28-Sep-24 A | 2026-07-20 | 93824757.31 | 93824757.41 | 21422906676% | Remaining Total Cost | [15 empty] | 27553525 | 23622420.21 | 15744947.49 | 16726100.3 | 10657834.08 | 15457368.04 | 5323301.86 | 3260872.73 | 1861424.65 | 196515.06
|  |  | JDH3-02-008--Construction |  | 2024-08-17 | 2026-07-09 | 28-Sep-24 A | 2026-07-20 | 93824757.31 | 93824757.41 | 21422906676% | Actual Total Cost |  |  | 10507.6 | 34932533% | 128781762% | 341894549% | 6079112.29 | 5888777.62 | 6280373.1 | 7481438.59 | 8336158.02 | 9515493.04 | 10062131.45 | 19482131 | 15096665.4 | 535880.85
|  |  | Pond and Swales - PS |  | 2024-09-11 | 2026-03-17 | 28-Sep-24 A | 2025-10-06 | 22001604.02 | 22001604.09 | 2311340010% | Planned Total Cost |  |  | 250484.44 | 91907410% | 83822678% | 91985100% | 898551.16 | 767565.52 | 828994.06 | 827006.33 | 806447.53 | 812597.48 | 857174 | 1164267.61 | 1206799.41 | 2068838.64 | 951597.41 | 1472008.91 | 3477668.91 | 2641314.54 | 1404932.27
|  |  | Pond and Swales - PS |  | 2024-09-11 | 2026-03-17 | 28-Sep-24 A | 2025-10-06 | 22001604.02 | 22001604.09 | 2311340010% | Remaining Total Cost | [15 empty] | 1111796.08
|  |  | Pond and Swales - PS |  | 2024-09-11 | 2026-03-17 | 28-Sep-24 A | 2025-10-06 | 22001604.02 | 22001604.09 | 2311340010% | Actual Total Cost |  |  | 10507.6 | 34932533% | 122524882% | 226136870% | 2547603.75 | 2842101.05 | 1922216.82 | 1956242.32 | 2622524.9 | 3063086.54 | 3201378.27
|  |  | JDH3-02-008--(ST)- Pond 1 |  | 2024-09-11 | 2025-02-15 | 28-Sep-24 A | 2025-10-06 | 2501264.91 | 2501264.94 | 266591447% | Planned Total Cost |  |  | 250484.44 | 56892369% | 44279442% | 51489434% | 492820.64 | 231347.39 | [6 empty] | 109766.37 | 54883.18
|  |  | JDH3-02-008--(ST)- Pond 1 |  | 2024-09-11 | 2025-02-15 | 28-Sep-24 A | 2025-10-06 | 2501264.91 | 2501264.94 | 266591447% | Remaining Total Cost | [15 empty] | 164649.55
|  |  | JDH3-02-008--(ST)- Pond 1 |  | 2024-09-11 | 2025-02-15 | 28-Sep-24 A | 2025-10-06 | 2501264.91 | 2501264.94 | 266591447% | Actual Total Cost |  |  | 7967.42 | 12299880% | 32283565% | 47097253% | 445415.96 | 530199.21 | 263361.89 | 216518.09 | 120995.4
|  |  | Stage (1) - Pond 1 |  | 2024-09-11 | 2024-11-04 | 28-Sep-24 A | 2025-10-04 | 833754.97 | 833754.98 | 88863816% | Planned Total Cost |  |  | 250484.44 | 56892369% | 1434684% | [9 empty] | 54883.18
|  |  | Stage (1) - Pond 1 |  | 2024-09-11 | 2024-11-04 | 28-Sep-24 A | 2025-10-04 | 833754.97 | 833754.98 | 88863816% | Remaining Total Cost | [15 empty] | 54883.18
|  |  | Stage (1) - Pond 1 |  | 2024-09-11 | 2024-11-04 | 28-Sep-24 A | 2025-10-04 | 833754.97 | 833754.98 | 88863816% | Actual Total Cost |  |  | 7967.42 | 7170676% | 9674645% | 15433548% | 145779.75 | 138837.18 | 79679.9 | 76728.79 | 61973.25
|  |  | Stage (2) - Pond 1 |  | 2024-11-03 | 2024-12-23 | 21-Oct-24 A | 2025-10-04 | 833754.97 | 833754.98 | 88863816% | Planned Total Cost |  |  |  |  | 42844757% | 40530740% | [8 empty] | 54883.18
|  |  | Stage (2) - Pond 1 |  | 2024-11-03 | 2024-12-23 | 21-Oct-24 A | 2025-10-04 | 833754.97 | 833754.98 | 88863816% | Remaining Total Cost | [15 empty] | 54883.18
|  |  | Stage (2) - Pond 1 |  | 2024-11-03 | 2024-12-23 | 21-Oct-24 A | 2025-10-04 | 833754.97 | 833754.98 | 88863816% | Actual Total Cost |  |  |  | 2655806% | 7697821% | 16105671% | 149818.1 | 195681.02 | 83873.58 | 80767.15 | 59022.15
|  |  | Stage (3) - Pond 1 |  | 2024-12-24 | 2025-02-15 | 28-Oct-24 A | 2025-10-06 | 833754.97 | 833754.98 | 88863816% | Planned Total Cost | [5 empty] | 10958694% | 492820.64 | 231347.39 | [7 empty] | 54883.18
|  |  | Stage (3) - Pond 1 |  | 2024-12-24 | 2025-02-15 | 28-Oct-24 A | 2025-10-06 | 833754.97 | 833754.98 | 88863816% | Remaining Total Cost | [15 empty] | 54883.18
|  |  | Stage (3) - Pond 1 |  | 2024-12-24 | 2025-02-15 | 28-Oct-24 A | 2025-10-06 | 833754.97 | 833754.98 | 88863816% | Actual Total Cost |  |  |  | 2473398% | 14911098% | 15558034% | 149818.1 | 195681.02 | 99808.41 | 59022.15
|  |  | JDH3-02-008--(ST)- Pond 2 |  | 2025-02-13 | 2025-07-20 | 08-Oct-24 A | 2025-10-04 | 2120187.02 | 2120187 | 228665834% | Planned Total Cost | [7 empty] | 180882.87 | 424037.4 | 402815.23 | 423123.83 | 423123.83 | 266203.85 |  |  | 166471.32
|  |  | JDH3-02-008--(ST)- Pond 2 |  | 2025-02-13 | 2025-07-20 | 08-Oct-24 A | 2025-10-04 | 2120187.02 | 2120187 | 228665834% | Remaining Total Cost | [15 empty] | 166471.32
|  |  | JDH3-02-008--(ST)- Pond 2 |  | 2025-02-13 | 2025-07-20 | 08-Oct-24 A | 2025-10-04 | 2120187.02 | 2120187 | 228665834% | Actual Total Cost |  |  |  | 5918758% | 24192552% | 54133482% | 545440.43 | 586843.55 | 145455.1
|  |  | Stage (1) - Pond 2 |  | 2025-02-13 | 2025-03-16 | 08-Oct-24 A | 2025-10-04 | 424037.4 | 424037.4 | 45733167% | Planned Total Cost | [7 empty] | 180882.87 | 243154.53 | [6 empty] | 33294.26
|  |  | Stage (1) - Pond 2 |  | 2025-02-13 | 2025-03-16 | 08-Oct-24 A | 2025-10-04 | 424037.4 | 424037.4 | 45733167% | Remaining Total Cost | [15 empty] | 33294.26
|  |  | Stage (1) - Pond 2 |  | 2025-02-13 | 2025-03-16 | 08-Oct-24 A | 2025-10-04 | 424037.4 | 424037.4 | 45733167% | Actual Total Cost |  |  |  | 3187024% | 6837741% | 11317183% | 108430.45 | 102187.48
|  |  | Stage (2) - Pond 2 |  | 2025-03-17 | 2025-04-16 | 19-Oct-24 A | 2025-10-04 | 424037.4 | 424037.4 | 45733167% | Planned Total Cost | [8 empty] | 180882.87 | 243154.53 | [5 empty] | 33294.26
|  |  | Stage (2) - Pond 2 |  | 2025-03-17 | 2025-04-16 | 19-Oct-24 A | 2025-10-04 | 424037.4 | 424037.4 | 45733167% | Remaining Total Cost | [15 empty] | 33294.26
|  |  | Stage (2) - Pond 2 |  | 2025-03-17 | 2025-04-16 | 19-Oct-24 A | 2025-10-04 | 424037.4 | 424037.4 | 45733167% | Actual Total Cost |  |  |  | 1821156% | 5454257% | 11374282% | 108430.45 | 115846.15 | 13263.86
|  |  | Stage (3) - Pond 2 |  | 2025-04-17 | 2025-05-18 | 26-Oct-24 A | 2025-10-04 | 424037.4 | 424037.4 | 45733167% | Planned Total Cost | [9 empty] | 159660.7 | 264376.71 |  |  |  |  | 33294.26
|  |  | Stage (3) - Pond 2 |  | 2025-04-17 | 2025-05-18 | 26-Oct-24 A | 2025-10-04 | 424037.4 | 424037.4 | 45733167% | Remaining Total Cost | [15 empty] | 33294.26
|  |  | Stage (3) - Pond 2 |  | 2025-04-17 | 2025-05-18 | 26-Oct-24 A | 2025-10-04 | 424037.4 | 424037.4 | 45733167% | Actual Total Cost |  |  |  | 910578% | 3794076% | 10116414% | 108430.45 | 124951.93 | 42444.34
|  |  | Stage (4) - Pond 2 |  | 2025-05-19 | 2025-06-18 | 09-Nov-24 A | 2025-10-04 | 424037.4 | 424037.4 | 45733167% | Planned Total Cost | [10 empty] | 158747.12 | 265290.28 |  |  |  | 33294.26
|  |  | Stage (4) - Pond 2 |  | 2025-05-19 | 2025-06-18 | 09-Nov-24 A | 2025-10-04 | 424037.4 | 424037.4 | 45733167% | Remaining Total Cost | [15 empty] | 33294.26
|  |  | Stage (4) - Pond 2 |  | 2025-05-19 | 2025-06-18 | 09-Nov-24 A | 2025-10-04 | 424037.4 | 424037.4 | 45733167% | Actual Total Cost |  |  |  |  | 8106478% | 11260085% | 108430.45 | 109800.28 | 12141.04
|  |  | Stage (5) - Pond 2 |  | 2025-06-19 | 2025-07-20 | 05-Dec-24 A | 2025-10-04 | 424037.4 | 424037.4 | 45733167% | Planned Total Cost | [11 empty] | 157833.55 | 266203.85 |  |  | 33294.26
|  |  | Stage (5) - Pond 2 |  | 2025-06-19 | 2025-07-20 | 05-Dec-24 A | 2025-10-04 | 424037.4 | 424037.4 | 45733167% | Remaining Total Cost | [15 empty] | 33294.26
|  |  | Stage (5) - Pond 2 |  | 2025-06-19 | 2025-07-20 | 05-Dec-24 A | 2025-10-04 | 424037.4 | 424037.4 | 45733167% | Actual Total Cost | [5 empty] | 10065518% | 111718.64 | 134057.71 | 77605.86
|  |  | JDH3-02-008--(ST)- Pond 3 |  | 2024-10-05 | 2025-10-26 | 30-Sep-24 A | 2025-10-04 | 5038080.4 | 5038080.39 | 556940159% | Planned Total Cost |  |  |  | 35015041% | 39543236% | 40495666% | 405730.52 | 355335.26 | 404956.66 | 424191.09 | 383323.7 | 389473.65 | 404956.66 | 393423.47 | 351583.83 | 905887.31
|  |  | JDH3-02-008--(ST)- Pond 3 |  | 2024-10-05 | 2025-10-26 | 30-Sep-24 A | 2025-10-04 | 5038080.4 | 5038080.39 | 556940159% | Remaining Total Cost | [15 empty] | 531321.19
|  |  | JDH3-02-008--(ST)- Pond 3 |  | 2024-10-05 | 2025-10-26 | 30-Sep-24 A | 2025-10-04 | 5038080.4 | 5038080.39 | 556940159% | Actual Total Cost |  |  | 2540.18 | 15749119% | 51685865% | 89390185% | 1001596.87 | 1073298.48 | 794825.72 | 427292.47 | 166894.28 | 3380.71
|  |  | Stage (1) - Pond 3 |  | 2024-10-05 | 2024-11-16 | 30-Sep-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Planned Total Cost |  |  |  | 35015041% | 20963630% | [10 empty] | 59035.69
|  |  | Stage (1) - Pond 3 |  | 2024-10-05 | 2024-11-16 | 30-Sep-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Remaining Total Cost | [15 empty] | 59035.69
|  |  | Stage (1) - Pond 3 |  | 2024-10-05 | 2024-11-16 | 30-Sep-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Actual Total Cost |  |  | 2540.18 | 6858487% | 7681170% | 11612049% | 109993.9 | 111360 | 45639.56 | 28736.02
|  |  | Stage (2) - Pond 3 |  | 2024-11-17 | 2024-12-29 | 13-Oct-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Planned Total Cost |  |  |  |  | 18579606% | 37399065% | [9 empty] | 59035.69
|  |  | Stage (2) - Pond 3 |  | 2024-11-17 | 2024-12-29 | 13-Oct-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Remaining Total Cost | [15 empty] | 59035.69
|  |  | Stage (2) - Pond 3 |  | 2024-11-17 | 2024-12-29 | 13-Oct-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Actual Total Cost |  |  |  | 4318307% | 6350451% | 11590485% | 109993.9 | 116440.36 | 68501.18 | 42258.85
|  |  | Stage (3) - Pond 3 |  | 2024-12-30 | 2025-02-10 | 21-Oct-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Planned Total Cost | [5 empty] | 3096601% | 405730.52 | 123090.18 | [7 empty] | 59035.69
|  |  | Stage (3) - Pond 3 |  | 2024-12-30 | 2025-02-10 | 21-Oct-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Remaining Total Cost | [15 empty] | 59035.69
|  |  | Stage (3) - Pond 3 |  | 2024-12-30 | 2025-02-10 | 21-Oct-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Actual Total Cost |  |  |  | 2540181% | 6350451% | 10576272% | 109993.9 | 116440.36 | 86282.44 | 43949.2 | 8451.77
|  |  | Stage (4) - Pond 3 |  | 2025-02-11 | 2025-03-25 | 26-Oct-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Planned Total Cost | [7 empty] | 232245.08 | 327541.63 | [6 empty] | 59035.69
|  |  | Stage (4) - Pond 3 |  | 2025-02-11 | 2025-03-25 | 26-Oct-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Remaining Total Cost | [15 empty] | 59035.69
|  |  | Stage (4) - Pond 3 |  | 2025-02-11 | 2025-03-25 | 26-Oct-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Actual Total Cost |  |  |  | 1524108% | 6350451% | 11083378% | 109993.9 | 116440.36 | 96443.17 | 43949.2 | 3380.71
|  |  | Stage (5) - Pond 3 |  | 2025-03-26 | 2025-05-06 | 30-Oct-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Planned Total Cost | [8 empty] | 77415.03 | 424191.09 | 58180.59 |  |  |  |  | 59035.69
|  |  | Stage (5) - Pond 3 |  | 2025-03-26 | 2025-05-06 | 30-Oct-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Remaining Total Cost | [15 empty] | 59035.69
|  |  | Stage (5) - Pond 3 |  | 2025-03-26 | 2025-05-06 | 30-Oct-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Actual Total Cost |  |  |  | 508036% | 6350451% | 10407237% | 109993.9 | 116440.36 | 106603.89 | 43949.2 | 10142.12
|  |  | Stage (6) - Pond 3 |  | 2025-05-07 | 2025-06-18 | 05-Nov-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Planned Total Cost | [10 empty] | 325143.11 | 234643.6 |  |  |  | 59035.69
|  |  | Stage (6) - Pond 3 |  | 2025-05-07 | 2025-06-18 | 05-Nov-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Remaining Total Cost | [15 empty] | 59035.69
|  |  | Stage (6) - Pond 3 |  | 2025-05-07 | 2025-06-18 | 05-Nov-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Actual Total Cost |  |  |  |  | 5925474% | 9055948% | 109993.9 | 116440.36 | 114224.43 | 49029.56 | 20284.25
|  |  | Stage (7) - Pond 3 |  | 2025-06-19 | 2025-07-31 | 12-Nov-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Planned Total Cost | [11 empty] | 154830.05 | 404956.66 |  |  | 59035.69
|  |  | Stage (7) - Pond 3 |  | 2025-06-19 | 2025-07-31 | 12-Nov-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Remaining Total Cost | [15 empty] | 59035.69
|  |  | Stage (7) - Pond 3 |  | 2025-06-19 | 2025-07-31 | 12-Nov-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Actual Total Cost |  |  |  |  | 4253895% | 7851136% | 109993.9 | 116440.36 | 114224.43 | 64270.65 | 33807.08
|  |  | Stage (8) - Pond 3 |  | 2025-08-02 | 2025-09-13 | 12-Nov-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Planned Total Cost | [13 empty] | 393423.47 | 166363.24 | 59035.69
|  |  | Stage (8) - Pond 3 |  | 2025-08-02 | 2025-09-13 | 12-Nov-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Remaining Total Cost | [15 empty] | 59035.69
|  |  | Stage (8) - Pond 3 |  | 2025-08-02 | 2025-09-13 | 12-Nov-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Actual Total Cost |  |  |  |  | 4253895% | 7005959% | 104922.83 | 116440.36 | 114224.43 | 64270.65 | 43949.2 | 3380.71
|  |  | Stage (9) - Pond 3 |  | 2025-09-14 | 2025-10-26 | 18-Nov-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Planned Total Cost | [14 empty] | 185220.59 | 433601.81
|  |  | Stage (9) - Pond 3 |  | 2025-09-14 | 2025-10-26 | 18-Nov-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Remaining Total Cost | [15 empty] | 59035.69
|  |  | Stage (9) - Pond 3 |  | 2025-09-14 | 2025-10-26 | 18-Nov-24 A | 2025-10-04 | 559786.71 | 559786.71 | 61882240% | Actual Total Cost |  |  |  |  | 4169625% | 10207722% | 126716.76 | 146855.98 | 48682.19 | 46879.15 | 46879.15
|  |  | JDH3-02-008--(ST)- Pond 4 |  | 2025-07-21 | 2025-11-13 | 23-Oct-24 A | 2025-10-04 | 2566976.59 | 2566976.67 | 281633061% | Planned Total Cost | [12 empty] | 186013.48 | 770844.14 | 745449.21 | 941596.83 | 172426.95
|  |  | JDH3-02-008--(ST)- Pond 4 |  | 2025-07-21 | 2025-11-13 | 23-Oct-24 A | 2025-10-04 | 2566976.59 | 2566976.67 | 281633061% | Remaining Total Cost | [15 empty] | 249354.02
|  |  | JDH3-02-008--(ST)- Pond 4 |  | 2025-07-21 | 2025-11-13 | 23-Oct-24 A | 2025-10-04 | 2566976.59 | 2566976.67 | 281633061% | Actual Total Cost |  |  |  | 964776% | 14362901% | 35515950% | 555150.5 | 651759.81 | 424938.26 | 287095.12 | 139596.71
|  |  | Stage (1) - Pond 4 |  | 2025-07-21 | 2025-08-12 | 23-Oct-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Planned Total Cost | [12 empty] | 140531.19 | 144688.43 |  | 27706
|  |  | Stage (1) - Pond 4 |  | 2025-07-21 | 2025-08-12 | 23-Oct-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Remaining Total Cost | [15 empty] | 27706
|  |  | Stage (1) - Pond 4 |  | 2025-07-21 | 2025-08-12 | 23-Oct-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Actual Total Cost |  |  |  | 964776% | 3014925% | 7750262% | 65595.92 | 52279.97 | 35557.65 | 14486.45
|  |  | Stage (2) - Pond 4 |  | 2025-08-13 | 2025-09-04 | 02-Nov-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Planned Total Cost | [13 empty] | 266958.4 | 18261.23 | 27706
|  |  | Stage (2) - Pond 4 |  | 2025-08-13 | 2025-09-04 | 02-Nov-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Remaining Total Cost | [15 empty] | 27706
|  |  | Stage (2) - Pond 4 |  | 2025-08-13 | 2025-09-04 | 02-Nov-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Actual Total Cost |  |  |  |  | 3014925% | 5406483% | 70596.41 | 61927.73 | 35557.65 | 32923.75
|  |  | Stage (3) - Pond 4 |  | 2025-09-06 | 2025-09-28 | 07-Nov-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Planned Total Cost | [14 empty] | 285219.62 | 27706
|  |  | Stage (3) - Pond 4 |  | 2025-09-06 | 2025-09-28 | 07-Nov-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Remaining Total Cost | [15 empty] | 27706
|  |  | Stage (3) - Pond 4 |  | 2025-09-06 | 2025-09-28 | 07-Nov-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Actual Total Cost |  |  |  |  | 3745403% | 3914594% | 65595.92 | 67957.58 | 35557.65 | 34240.7 | 5267.8
|  |  | Stage (4) - Pond 4 |  | 2025-09-29 | 2025-10-21 | 12-Nov-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Planned Total Cost | [14 empty] | 30321.53 | 282604.09
|  |  | Stage (4) - Pond 4 |  | 2025-09-29 | 2025-10-21 | 12-Nov-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Remaining Total Cost | [15 empty] | 27706
|  |  | Stage (4) - Pond 4 |  | 2025-09-29 | 2025-10-21 | 12-Nov-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Actual Total Cost |  |  |  |  | 1333463% | 2291343% | 62962.02 | 78811.31 | 58471.08 | 34240.7 | 14486.45
|  |  | Stage (5) - Pond 4 |  | 2025-10-22 | 2025-11-13 | 10-Nov-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Planned Total Cost | [15 empty] | 140498.68 | 172426.95
|  |  | Stage (5) - Pond 4 |  | 2025-10-22 | 2025-11-13 | 10-Nov-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Remaining Total Cost | [15 empty] | 27706
|  |  | Stage (5) - Pond 4 |  | 2025-10-22 | 2025-11-13 | 10-Nov-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Actual Total Cost |  |  |  |  | 3254185% | 4164618% | 65595.92 | 70369.52 | 35557.65 | 34240.7 | 5267.8
|  |  | Stage (6) - Pond 4 |  | 2025-07-29 | 2025-08-20 | 12-Dec-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Planned Total Cost | [12 empty] | 45482.3 | 239737.32 |  | 27706
|  |  | Stage (6) - Pond 4 |  | 2025-07-29 | 2025-08-20 | 12-Dec-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Remaining Total Cost | [15 empty] | 27706
|  |  | Stage (6) - Pond 4 |  | 2025-07-29 | 2025-08-20 | 12-Dec-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Actual Total Cost | [5 empty] | 3300271% | 50625.94 | 78811.31 | 60883.02 | 34240.7 | 27655.95
|  |  | Stage (7) - Pond 4 |  | 2025-08-21 | 2025-09-13 | 15-Dec-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Planned Total Cost | [13 empty] | 119459.99 | 165759.64 | 27706
|  |  | Stage (7) - Pond 4 |  | 2025-08-21 | 2025-09-13 | 15-Dec-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Remaining Total Cost | [15 empty] | 27706
|  |  | Stage (7) - Pond 4 |  | 2025-08-21 | 2025-09-13 | 15-Dec-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Actual Total Cost | [5 empty] | 2892394% | 50975.81 | 78811.31 | 63294.96 | 34240.7 | 28972.9
|  |  | Stage (8) - Pond 4 |  | 2025-09-14 | 2025-10-06 | 16-Dec-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Planned Total Cost | [14 empty] | 245887.19 | 67038.43
|  |  | Stage (8) - Pond 4 |  | 2025-09-14 | 2025-10-06 | 16-Dec-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Remaining Total Cost | [15 empty] | 27706
|  |  | Stage (8) - Pond 4 |  | 2025-09-14 | 2025-10-06 | 16-Dec-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Actual Total Cost | [5 empty] | 2688455% | 50492.28 | 78811.31 | 64500.93 | 34240.7 | 30289.85
|  |  | Stage (9) - Pond 4 |  | 2025-10-07 | 2025-10-29 | 18-Dec-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Planned Total Cost | [15 empty] | 312925.62
|  |  | Stage (9) - Pond 4 |  | 2025-10-07 | 2025-10-29 | 18-Dec-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Remaining Total Cost | [15 empty] | 27706
|  |  | Stage (9) - Pond 4 |  | 2025-10-07 | 2025-10-29 | 18-Dec-24 A | 2025-10-04 | 285219.62 | 285219.63 | 31292562% | Actual Total Cost | [5 empty] | 3107529% | 72710.28 | 83979.76 | 35557.65 | 34240.7 | 27655.95
|  |  | JDH3-02-008--(ST)- Pond 6 |  | 2025-11-15 | 2026-02-01 | 20-Mar-25 A | 31-Jul-25 A | 3500856.14 | 3500856.15 | 350085614% | Planned Total Cost | [16 empty] | 779170.46 | 1472008.91 | 1248959.79 | 716.99
|  |  | JDH3-02-008--(ST)- Pond 6 |  | 2025-11-15 | 2026-02-01 | 20-Mar-25 A | 31-Jul-25 A | 3500856.14 | 3500856.15 | 350085614% | Remaining Total Cost
|  |  | JDH3-02-008--(ST)- Pond 6 |  | 2025-11-15 | 2026-02-01 | 20-Mar-25 A | 31-Jul-25 A | 3500856.14 | 3500856.15 | 350085614% | Actual Total Cost | [8 empty] | 114553.92 | 392094.62 | 807852.19 | 1103837.4 | 1082518.02
|  |  | Stage (1) - Pond 6 |  | 2025-11-17 | 2025-12-11 | 20-Mar-25 A | 31-Jul-25 A | 1158242.05 | 1158242.05 | 115824205% | Planned Total Cost | [16 empty] | 753040.46 | 405201.59
|  |  | Stage (1) - Pond 6 |  | 2025-11-17 | 2025-12-11 | 20-Mar-25 A | 31-Jul-25 A | 1158242.05 | 1158242.05 | 115824205% | Remaining Total Cost
|  |  | Stage (1) - Pond 6 |  | 2025-11-17 | 2025-12-11 | 20-Mar-25 A | 31-Jul-25 A | 1158242.05 | 1158242.05 | 115824205% | Actual Total Cost | [8 empty] | 98222.67 | 255378.94 | 255378.94 | 284060.3 | 265201.21
|  |  | Stage (2) - Pond 6 |  | 2025-12-13 | 2026-01-06 | 20-Apr-25 A | 31-Jul-25 A | 1158242.05 | 1158242.05 | 115824205% | Planned Total Cost | [17 empty] | 1066807.32 | 91434.73
|  |  | Stage (2) - Pond 6 |  | 2025-12-13 | 2026-01-06 | 20-Apr-25 A | 31-Jul-25 A | 1158242.05 | 1158242.05 | 115824205% | Remaining Total Cost
|  |  | Stage (2) - Pond 6 |  | 2025-12-13 | 2026-01-06 | 20-Apr-25 A | 31-Jul-25 A | 1158242.05 | 1158242.05 | 115824205% | Actual Total Cost | [9 empty] | 126916.93 | 329984.02 | 358665.38 | 342675.71
|  |  | Stage (3) - Pond 6 |  | 2026-01-07 | 2026-02-01 | 17-May-25 A | 31-Jul-25 A | 1158242.05 | 1158242.05 | 115824205% | Planned Total Cost | [18 empty] | 1157525.06 | 716.99
|  |  | Stage (3) - Pond 6 |  | 2026-01-07 | 2026-02-01 | 17-May-25 A | 31-Jul-25 A | 1158242.05 | 1158242.05 | 115824205% | Remaining Total Cost
|  |  | Stage (3) - Pond 6 |  | 2026-01-07 | 2026-02-01 | 17-May-25 A | 31-Jul-25 A | 1158242.05 | 1158242.05 | 115824205% | Actual Total Cost | [10 empty] | 222489.23 | 461111.72 | 474641.1
|  |  | JDH3-02-008--(ST)- Pond 12 |  | 2026-01-07 | 2026-03-17 | 20-Mar-25 A | 31-Jul-25 A | 6274238.95 | 6274238.94 | 627423895% | Planned Total Cost | [18 empty] | 2228709.13 | 2640597.55 | 1404932.27
|  |  | JDH3-02-008--(ST)- Pond 12 |  | 2026-01-07 | 2026-03-17 | 20-Mar-25 A | 31-Jul-25 A | 6274238.95 | 6274238.94 | 627423895% | Remaining Total Cost
|  |  | JDH3-02-008--(ST)- Pond 12 |  | 2026-01-07 | 2026-03-17 | 20-Mar-25 A | 31-Jul-25 A | 6274238.95 | 6274238.94 | 627423895% | Actual Total Cost | [8 empty] | 179081.93 | 633242.02 | 1387186.33 | 1955868.43 | 2118860.24
|  |  | Stage (1) - Pond 12 |  | 2026-01-07 | 2026-01-29 | 20-Mar-25 A | 31-Jul-25 A | 2091412.98 | 2091412.98 | 209141298% | Planned Total Cost | [18 empty] | 2091412.98
|  |  | Stage (1) - Pond 12 |  | 2026-01-07 | 2026-01-29 | 20-Mar-25 A | 31-Jul-25 A | 2091412.98 | 2091412.98 | 209141298% | Remaining Total Cost
|  |  | Stage (1) - Pond 12 |  | 2026-01-07 | 2026-01-29 | 20-Mar-25 A | 31-Jul-25 A | 2091412.98 | 2091412.98 | 209141298% | Actual Total Cost | [8 empty] | 179081.93 | 465613.01 | 465613.01 | 469609.36 | 511495.68
|  |  | Stage (2) - Pond 12 |  | 2026-01-31 | 2026-02-22 | 23-Apr-25 A | 31-Jul-25 A | 2091412.98 | 2091412.98 | 209141298% | Planned Total Cost | [18 empty] | 137296.14 | 1954116.84
|  |  | Stage (2) - Pond 12 |  | 2026-01-31 | 2026-02-22 | 23-Apr-25 A | 31-Jul-25 A | 2091412.98 | 2091412.98 | 209141298% | Remaining Total Cost
|  |  | Stage (2) - Pond 12 |  | 2026-01-31 | 2026-02-22 | 23-Apr-25 A | 31-Jul-25 A | 2091412.98 | 2091412.98 | 209141298% | Actual Total Cost | [9 empty] | 167629.01 | 622622.04 | 622622.04 | 678539.88
|  |  | Stage (3) - Pond 12 |  | 2026-02-23 | 2026-03-17 | 21-May-25 A | 31-Jul-25 A | 2091412.98 | 2091412.98 | 209141298% | Planned Total Cost | [19 empty] | 686480.71 | 1404932.27
|  |  | Stage (3) - Pond 12 |  | 2026-02-23 | 2026-03-17 | 21-May-25 A | 31-Jul-25 A | 2091412.98 | 2091412.98 | 209141298% | Remaining Total Cost
|  |  | Stage (3) - Pond 12 |  | 2026-02-23 | 2026-03-17 | 21-May-25 A | 31-Jul-25 A | 2091412.98 | 2091412.98 | 209141298% | Actual Total Cost | [10 empty] | 298951.28 | 863637.03 | 928824.68
|  |  | High Mast |  | 2026-01-06 | 2026-04-01 | 20-Aug-25 A | 2025-12-15 | 540852.78 | 540852.79 | 211504855% | Planned Total Cost | [15 empty] | 1228872.91 | 431065.27 | 113318.88 | [12 empty] | 46365.97 | 295425.52
|  |  | High Mast |  | 2026-01-06 | 2026-04-01 | 20-Aug-25 A | 2025-12-15 | 540852.78 | 540852.79 | 211504855% | Remaining Total Cost | [15 empty] | 1417761.21 | 122045.11 | 34389.43
|  |  | High Mast |  | 2026-01-06 | 2026-04-01 | 20-Aug-25 A | 2025-12-15 | 540852.78 | 540852.79 | 211504855% | Actual Total Cost | [13 empty] | 98211.88 | 421827.55 | 20813.35
|  |  | JDH3-02-008-H&M-Street Lighting - SL |  | 2026-01-06 | 2026-04-01 | 20-Aug-25 A | 2025-12-15 | 540852.78 | 540852.79 | 211504855% | Planned Total Cost | [15 empty] | 1228872.91 | 431065.27 | 113318.88 | [12 empty] | 46365.97 | 295425.52
|  |  | JDH3-02-008-H&M-Street Lighting - SL |  | 2026-01-06 | 2026-04-01 | 20-Aug-25 A | 2025-12-15 | 540852.78 | 540852.79 | 211504855% | Remaining Total Cost | [15 empty] | 1417761.21 | 122045.11 | 34389.43
|  |  | JDH3-02-008-H&M-Street Lighting - SL |  | 2026-01-06 | 2026-04-01 | 20-Aug-25 A | 2025-12-15 | 540852.78 | 540852.79 | 211504855% | Actual Total Cost | [13 empty] | 98211.88 | 421827.55 | 20813.35
|  |  | JDH3-02-008-H&M-(SL)- Supply and install single core PVC insulated copper conductor for circuit |  | 2026-01-06 | 2026-01-17 | 2025-10-02 | 2025-10-13 | 0 | 0 | 6030000% | Planned Total Cost | [15 empty] | 60300
|  |  | JDH3-02-008-H&M-(SL)- Supply and install single core PVC insulated copper conductor for circuit |  | 2026-01-06 | 2026-01-17 | 2025-10-02 | 2025-10-13 | 0 | 0 | 6030000% | Remaining Total Cost | [15 empty] | 60300
|  |  | JDH3-02-008-H&M-(SL)- Supply and install single core PVC insulated copper conductor for circuit |  | 2026-01-06 | 2026-01-17 | 2025-10-02 | 2025-10-13 | 0 | 0 | 6030000% | Actual Total Cost
|  |  | JDH3-02-008-H&M-(SL)- Stranded armored Cables, Copper, 4Cx150 mm² XLPE /PVC/SWA |  | 2026-01-12 | 2026-01-22 | 2025-10-08 | 2025-10-19 | 0 | 0 | 33544890% | Planned Total Cost | [15 empty] | 335448.9
|  |  | JDH3-02-008-H&M-(SL)- Stranded armored Cables, Copper, 4Cx150 mm² XLPE /PVC/SWA |  | 2026-01-12 | 2026-01-22 | 2025-10-08 | 2025-10-19 | 0 | 0 | 33544890% | Remaining Total Cost | [15 empty] | 335448.9
|  |  | JDH3-02-008-H&M-(SL)- Stranded armored Cables, Copper, 4Cx150 mm² XLPE /PVC/SWA |  | 2026-01-12 | 2026-01-22 | 2025-10-08 | 2025-10-19 | 0 | 0 | 33544890% | Actual Total Cost
|  |  | JDH3-02-008-H&M-(SL)- Supply,install,Light fixtures LED 342 wats including cables , fuse box and ris |  | 2026-01-18 | 2026-01-21 | 16-Sep-25 A | 2025-10-04 | 2222-11-07 | 2222-11-07 | 14740000% | Planned Total Cost | [15 empty] | 147400
|  |  | JDH3-02-008-H&M-(SL)- Supply,install,Light fixtures LED 342 wats including cables , fuse box and ris |  | 2026-01-18 | 2026-01-21 | 16-Sep-25 A | 2025-10-04 | 2222-11-07 | 2222-11-07 | 14740000% | Remaining Total Cost | [15 empty] | 29480
|  |  | JDH3-02-008-H&M-(SL)- Supply,install,Light fixtures LED 342 wats including cables , fuse box and ris |  | 2026-01-18 | 2026-01-21 | 16-Sep-25 A | 2025-10-04 | 2222-11-07 | 2222-11-07 | 14740000% | Actual Total Cost | [14 empty] | 117920
|  |  | JDH3-02-008-H&M-(SL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx10 mm² |  | 2026-01-06 | 2026-01-24 | 2025-10-02 | 2025-10-20 | 0 | 0 | 4036901% | Planned Total Cost | [15 empty] | 40369.01
|  |  | JDH3-02-008-H&M-(SL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx10 mm² |  | 2026-01-06 | 2026-01-24 | 2025-10-02 | 2025-10-20 | 0 | 0 | 4036901% | Remaining Total Cost | [15 empty] | 40369.01
|  |  | JDH3-02-008-H&M-(SL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx10 mm² |  | 2026-01-06 | 2026-01-24 | 2025-10-02 | 2025-10-20 | 0 | 0 | 4036901% | Actual Total Cost
|  |  | JDH3-02-008-H&M-(SL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx25 mm² |  | 2026-01-11 | 2026-02-07 | 2025-10-07 | 2025-11-03 | 0 | 0 | 10515357% | Planned Total Cost | [15 empty] | 99895.89 | 5257.68
|  |  | JDH3-02-008-H&M-(SL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx25 mm² |  | 2026-01-11 | 2026-02-07 | 2025-10-07 | 2025-11-03 | 0 | 0 | 10515357% | Remaining Total Cost | [15 empty] | 99895.89 | 5257.68
|  |  | JDH3-02-008-H&M-(SL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx25 mm² |  | 2026-01-11 | 2026-02-07 | 2025-10-07 | 2025-11-03 | 0 | 0 | 10515357% | Actual Total Cost
|  |  | JDH3-02-008-H&M-(SL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx35 mm² |  | 2026-01-06 | 2026-03-25 | 16-Sep-25 A | 2025-10-19 | 2267-08-11 | 2267-08-11 | 78929444% | Planned Total Cost | [15 empty] | 348218.13 | 362146.86 | 78929.44
|  |  | JDH3-02-008-H&M-(SL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx35 mm² |  | 2026-01-06 | 2026-03-25 | 16-Sep-25 A | 2025-10-19 | 2267-08-11 | 2267-08-11 | 78929444% | Remaining Total Cost | [15 empty] | 655026.44
|  |  | JDH3-02-008-H&M-(SL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx35 mm² |  | 2026-01-06 | 2026-03-25 | 16-Sep-25 A | 2025-10-19 | 2267-08-11 | 2267-08-11 | 78929444% | Actual Total Cost | [14 empty] | 120008.56 | 14259.44
|  |  | JDH3-02-008-H&M-(SL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx50 mm² |  | 2026-01-06 | 2026-01-19 | 2025-10-02 | 2025-10-15 | 0 | 0 | 6622280% | Planned Total Cost | [15 empty] | 66222.8
|  |  | JDH3-02-008-H&M-(SL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx50 mm² |  | 2026-01-06 | 2026-01-19 | 2025-10-02 | 2025-10-15 | 0 | 0 | 6622280% | Remaining Total Cost | [15 empty] | 66222.8
|  |  | JDH3-02-008-H&M-(SL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx50 mm² |  | 2026-01-06 | 2026-01-19 | 2025-10-02 | 2025-10-15 | 0 | 0 | 6622280% | Actual Total Cost
|  |  | JDH3-02-008-H&M-(SL)- Supply,install,connect and test single core PVC insulated copper 6 mm² |  | 2026-01-06 | 2026-01-10 | 2025-10-02 | 2025-10-06 | 0 | 0 | 169322% | Planned Total Cost | [15 empty] | 1693.22
|  |  | JDH3-02-008-H&M-(SL)- Supply,install,connect and test single core PVC insulated copper 6 mm² |  | 2026-01-06 | 2026-01-10 | 2025-10-02 | 2025-10-06 | 0 | 0 | 169322% | Remaining Total Cost | [15 empty] | 1693.22
|  |  | JDH3-02-008-H&M-(SL)- Supply,install,connect and test single core PVC insulated copper 6 mm² |  | 2026-01-06 | 2026-01-10 | 2025-10-02 | 2025-10-06 | 0 | 0 | 169322% | Actual Total Cost
|  |  | JDH3-02-008-H&M-(SL)- Supply,install,connect and test single core PVC insulated copper 16 mm² |  | 2026-01-06 | 2026-02-23 | 2025-10-02 | 2025-11-19 | 0 | 0 | 11377281% | Planned Total Cost | [15 empty] | 95352.45 | 18420.36
|  |  | JDH3-02-008-H&M-(SL)- Supply,install,connect and test single core PVC insulated copper 16 mm² |  | 2026-01-06 | 2026-02-23 | 2025-10-02 | 2025-11-19 | 0 | 0 | 11377281% | Remaining Total Cost | [15 empty] | 95352.45 | 18420.36
|  |  | JDH3-02-008-H&M-(SL)- Supply,install,connect and test single core PVC insulated copper 16 mm² |  | 2026-01-06 | 2026-02-23 | 2025-10-02 | 2025-11-19 | 0 | 0 | 11377281% | Actual Total Cost
|  |  | JDH3-02-008-H&M-(SL)-ROAD CROSSING DUCTS FOR CABLES PVC-4 × 150 mm |  | 2026-02-24 | 2026-03-11 | 2025-11-20 | 2025-12-06 | 0 | 0 | 1613327% | Planned Total Cost | [16 empty] | 14721.61 | 1411.66
|  |  | JDH3-02-008-H&M-(SL)-ROAD CROSSING DUCTS FOR CABLES PVC-4 × 150 mm |  | 2026-02-24 | 2026-03-11 | 2025-11-20 | 2025-12-06 | 0 | 0 | 1613327% | Remaining Total Cost | [16 empty] | 14721.61 | 1411.66
|  |  | JDH3-02-008-H&M-(SL)-ROAD CROSSING DUCTS FOR CABLES PVC-4 × 150 mm |  | 2026-02-24 | 2026-03-11 | 2025-11-20 | 2025-12-06 | 0 | 0 | 1613327% | Actual Total Cost
|  |  | JDH3-02-008-H&M-(SL)-ROAD CROSSING DUCTS FOR CABLES PVC-6 × 150 mm |  | 2026-02-26 | 2026-03-07 | 2025-11-23 | 2025-12-01 | 0 | 0 | 265280% | Planned Total Cost | [16 empty] | 2586.48 | 66.32
|  |  | JDH3-02-008-H&M-(SL)-ROAD CROSSING DUCTS FOR CABLES PVC-6 × 150 mm |  | 2026-02-26 | 2026-03-07 | 2025-11-23 | 2025-12-01 | 0 | 0 | 265280% | Remaining Total Cost | [16 empty] | 2586.48 | 66.32
|  |  | JDH3-02-008-H&M-(SL)-ROAD CROSSING DUCTS FOR CABLES PVC-6 × 150 mm |  | 2026-02-26 | 2026-03-07 | 2025-11-23 | 2025-12-01 | 0 | 0 | 265280% | Actual Total Cost
|  |  | JDH3-02-008-H&M-(SL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2026-02-26 | 2026-03-31 | 20-Aug-25 A | 2025-11-22 | 207681.88 | 207681.89 | 26080860% | Planned Total Cost | [30 empty] | 46365.97 | 214442.62
|  |  | JDH3-02-008-H&M-(SL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2026-02-26 | 2026-03-31 | 20-Aug-25 A | 2025-11-22 | 207681.88 | 207681.89 | 26080860% | Remaining Total Cost | [16 empty] | 53126.71
|  |  | JDH3-02-008-H&M-(SL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2026-02-26 | 2026-03-31 | 20-Aug-25 A | 2025-11-22 | 207681.88 | 207681.89 | 26080860% | Actual Total Cost | [13 empty] | 30726.13 | 170401.84 | 6553.92
|  |  | JDH3-02-008-H&M-(SL)- Street Lighting panels |  | 2026-03-01 | 2026-03-07 | 2025-11-25 | 2025-12-01 | 0 | 0 | 2940240% | Planned Total Cost | [16 empty] | 27932.28 | 1470.12
|  |  | JDH3-02-008-H&M-(SL)- Street Lighting panels |  | 2026-03-01 | 2026-03-07 | 2025-11-25 | 2025-12-01 | 0 | 0 | 2940240% | Remaining Total Cost | [16 empty] | 27932.28 | 1470.12
|  |  | JDH3-02-008-H&M-(SL)- Street Lighting panels |  | 2026-03-01 | 2026-03-07 | 2025-11-25 | 2025-12-01 | 0 | 0 | 2940240% | Actual Total Cost
|  |  | JDH3-02-008-H&M-(SL)-Supply and installation of KWH meter mounting frame |  | 2026-03-08 | 2026-03-14 | 2025-12-02 | 2025-12-08 | 0 | 0 | 296566% | Planned Total Cost | [17 empty] | 2965.66
|  |  | JDH3-02-008-H&M-(SL)-Supply and installation of KWH meter mounting frame |  | 2026-03-08 | 2026-03-14 | 2025-12-02 | 2025-12-08 | 0 | 0 | 296566% | Remaining Total Cost | [17 empty] | 2965.66
|  |  | JDH3-02-008-H&M-(SL)-Supply and installation of KWH meter mounting frame |  | 2026-03-08 | 2026-03-14 | 2025-12-02 | 2025-12-08 | 0 | 0 | 296566% | Actual Total Cost
|  |  | JDH3-02-008-H&M-(SL)-Substation protection room including Protection poles |  | 2026-03-15 | 2026-03-21 | 2025-12-09 | 2025-12-15 | 0 | 0 | 2847567% | Planned Total Cost | [17 empty] | 28475.67
|  |  | JDH3-02-008-H&M-(SL)-Substation protection room including Protection poles |  | 2026-03-15 | 2026-03-21 | 2025-12-09 | 2025-12-15 | 0 | 0 | 2847567% | Remaining Total Cost | [17 empty] | 28475.67
|  |  | JDH3-02-008-H&M-(SL)-Substation protection room including Protection poles |  | 2026-03-15 | 2026-03-21 | 2025-12-09 | 2025-12-15 | 0 | 0 | 2847567% | Actual Total Cost
|  |  | JDH3-02-008-H&M-(SL)- Supply,install,Light fixtures LED 208 wats including cables , fuse box and ris |  | 2026-03-22 | 2026-03-25 | 20-Aug-25 A | 2025-10-04 | 2121-09-19 21:36 | 2121-09-19 21:36 | 10122863% | Planned Total Cost | [15 empty] | 20245.73 | [15 empty] | 80982.9
|  |  | JDH3-02-008-H&M-(SL)- Supply,install,Light fixtures LED 208 wats including cables , fuse box and ris |  | 2026-03-22 | 2026-03-25 | 20-Aug-25 A | 2025-10-04 | 2121-09-19 21:36 | 2121-09-19 21:36 | 10122863% | Remaining Total Cost | [15 empty] | 20245.73
|  |  | JDH3-02-008-H&M-(SL)- Supply,install,Light fixtures LED 208 wats including cables , fuse box and ris |  | 2026-03-22 | 2026-03-25 | 20-Aug-25 A | 2025-10-04 | 2121-09-19 21:36 | 2121-09-19 21:36 | 10122863% | Actual Total Cost | [13 empty] | 67485.75 | 13497.15
|  |  | JDH3-02-008-H&M-(SL)- Drawpit with medium duty steel cover,size 900x1800x1200mm |  | 2026-03-26 | 2026-04-01 | 2025-10-05 | 2025-10-11 | 0 | 0 | 1372677% | Planned Total Cost | [15 empty] | 13726.77
|  |  | JDH3-02-008-H&M-(SL)- Drawpit with medium duty steel cover,size 900x1800x1200mm |  | 2026-03-26 | 2026-04-01 | 2025-10-05 | 2025-10-11 | 0 | 0 | 1372677% | Remaining Total Cost | [15 empty] | 13726.77
|  |  | JDH3-02-008-H&M-(SL)- Drawpit with medium duty steel cover,size 900x1800x1200mm |  | 2026-03-26 | 2026-04-01 | 2025-10-05 | 2025-10-11 | 0 | 0 | 1372677% | Actual Total Cost
|  |  | MR |  | 2024-08-27 | 2026-07-09 | 08-Oct-24 A | 2026-07-20 | 30747489.89 | 30747489.98 | 8512403124% | Planned Total Cost |  |  | 262196.91 | 82353393% | 63270726% | 21618183% | 900496.35 | 475688.66 | 40027.22 | 477803.38 | 322292.05 | 369721.82 | 549466.08 | 1565135.15 | 2414782.49 | 5820477.48 | 13198275.62 | 15448058.67 | 10322945.59 | 10118764.37 | 9850799.47 | 6064963.27 | 4154928.79 | 898269.76 | 196515.06
|  |  | MR |  | 2024-08-27 | 2026-07-09 | 08-Oct-24 A | 2026-07-20 | 30747489.89 | 30747489.98 | 8512403124% | Remaining Total Cost | [15 empty] | 4746064.6 | 12900418.73 | 11524529.8 | 7752098.52 | 5634485.43 | 5876121.8 | 2851397.67 | 2119830.56 | 775079.19 | 196515.06
|  |  | MR |  | 2024-08-27 | 2026-07-09 | 08-Oct-24 A | 2026-07-20 | 30747489.89 | 30747489.98 | 8512403124% | Actual Total Cost |  |  |  |  | 2956212% | 61874051% | 1650158.23 | 826988.65 | 1160279.46 | 1994882.32 | 2497335.25 | 3009229.76 | 3617670.32 | 8398599.15 | 6704326.71 | 239717.49
|  |  | R1 |  | 2025-08-02 | 2026-06-15 | 02-Apr-25 A | 2026-04-16 | 4073764.63 | 4073764.64 | 1258072482% | Planned Total Cost | [13 empty] | 547388.62 | 219264.41 | 893922.38 | 1266473.32 | 2119152.12 | 2792772.18 | 1325713.16 | 1304146.64 | 1637558.99 | 458820.3 | 15512.68
|  |  | R1 |  | 2025-08-02 | 2026-06-15 | 02-Apr-25 A | 2026-04-16 | 4073764.63 | 4073764.64 | 1258072482% | Remaining Total Cost | [16 empty] | 736145.14 | 1594052.99 | 2756996.4 | 1325713.16 | 1680751.69 | 413300.81
|  |  | R1 |  | 2025-08-02 | 2026-06-15 | 02-Apr-25 A | 2026-04-16 | 4073764.63 | 4073764.64 | 1258072482% | Actual Total Cost | [9 empty] | 242996.17 | 504607.51 | 596978.93 | 713104.45 | 1364348.54 | 631525.37 | 20203.67
|  |  | JDH3-02-008-R1-Storm Network - ST |  | 2025-08-02 | 2026-06-15 | 02-Apr-25 A | 2026-04-16 | 4073764.63 | 4073764.64 | 1258072482% | Planned Total Cost | [13 empty] | 547388.62 | 219264.41 | 893922.38 | 1266473.32 | 2119152.12 | 2792772.18 | 1325713.16 | 1304146.64 | 1637558.99 | 458820.3 | 15512.68
|  |  | JDH3-02-008-R1-Storm Network - ST |  | 2025-08-02 | 2026-06-15 | 02-Apr-25 A | 2026-04-16 | 4073764.63 | 4073764.64 | 1258072482% | Remaining Total Cost | [16 empty] | 736145.14 | 1594052.99 | 2756996.4 | 1325713.16 | 1680751.69 | 413300.81
|  |  | JDH3-02-008-R1-Storm Network - ST |  | 2025-08-02 | 2026-06-15 | 02-Apr-25 A | 2026-04-16 | 4073764.63 | 4073764.64 | 1258072482% | Actual Total Cost | [9 empty] | 242996.17 | 504607.51 | 596978.93 | 713104.45 | 1364348.54 | 631525.37 | 20203.67
|  |  | JDH3-02-008-R1-(ST)-Swales |  | 2025-08-02 | 2026-04-13 | 02-Apr-25 A | 2026-03-26 | 3128082.4 | 3128082.41 | 664172669% | Planned Total Cost | [13 empty] | 547388.62 | 219264.41 | 893922.38 | 1266473.32 | 1468825.78 | 718376.19 | 371921.74 | 402645.32 | 752908.93
|  |  | JDH3-02-008-R1-(ST)-Swales |  | 2025-08-02 | 2026-04-13 | 02-Apr-25 A | 2026-03-26 | 3128082.4 | 3128082.41 | 664172669% | Remaining Total Cost | [16 empty] | 736145.14 | 943726.65 | 682600.4 | 371921.74 | 779250.37
|  |  | JDH3-02-008-R1-(ST)-Swales |  | 2025-08-02 | 2026-04-13 | 02-Apr-25 A | 2026-03-26 | 3128082.4 | 3128082.41 | 664172669% | Actual Total Cost | [9 empty] | 198527.42 | 329697.13 | 329697.13 | 409209.99 | 1209221.7 | 631525.37 | 20203.67
|  |  | JDH3-02-008-R1-Box Culvert |  | 2026-02-21 | 2026-06-15 | 2025-12-15 | 2026-04-09 | 0 | 0 | 452597995% | Planned Total Cost | [17 empty] | 650326.34 | 2074395.99 | 953791.42 | 623231.09 | 224235.1
|  |  | JDH3-02-008-R1-Box Culvert |  | 2026-02-21 | 2026-06-15 | 2025-12-15 | 2026-04-09 | 0 | 0 | 452597995% | Remaining Total Cost | [17 empty] | 650326.34 | 2074395.99 | 953791.42 | 623231.09 | 224235.1
|  |  | JDH3-02-008-R1-Box Culvert |  | 2026-02-21 | 2026-06-15 | 2025-12-15 | 2026-04-09 | 0 | 0 | 452597995% | Actual Total Cost
|  |  | JDH3-02-008-R1-(ST)- Concrete Box Culvert With Dim (1000x1000) depth from 2.51 to 3.50 |  | 2026-02-21 | 2026-04-15 | 2025-12-15 | 2026-02-08 | 0 | 0 | 36437357% | Planned Total Cost | [17 empty] | 183132.76 | 127076.69 | 54164.13
|  |  | JDH3-02-008-R1-(ST)- Concrete Box Culvert With Dim (1000x1000) depth from 2.51 to 3.50 |  | 2026-02-21 | 2026-04-15 | 2025-12-15 | 2026-02-08 | 0 | 0 | 36437357% | Remaining Total Cost | [17 empty] | 183132.76 | 127076.69 | 54164.13
|  |  | JDH3-02-008-R1-(ST)- Concrete Box Culvert With Dim (1000x1000) depth from 2.51 to 3.50 |  | 2026-02-21 | 2026-04-15 | 2025-12-15 | 2026-02-08 | 0 | 0 | 36437357% | Actual Total Cost
|  |  | JDH3-02-008-R1-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2026-02-24 | 2026-06-04 | 2025-12-18 | 2026-03-30 | 0 | 0 | 212739839% | Planned Total Cost | [17 empty] | 394809.68 | 950896.43 | 393036.85 | 388655.43
|  |  | JDH3-02-008-R1-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2026-02-24 | 2026-06-04 | 2025-12-18 | 2026-03-30 | 0 | 0 | 212739839% | Remaining Total Cost | [17 empty] | 394809.68 | 950896.43 | 393036.85 | 388655.43
|  |  | JDH3-02-008-R1-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2026-02-24 | 2026-06-04 | 2025-12-18 | 2026-03-30 | 0 | 0 | 212739839% | Actual Total Cost
|  |  | JDH3-02-008-R1-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2026-03-07 | 2026-06-15 | 2025-12-29 | 2026-04-09 | 0 | 0 | 203420798% | Planned Total Cost | [17 empty] | 72383.9 | 996422.88 | 506590.44 | 234575.66 | 224235.1
|  |  | JDH3-02-008-R1-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2026-03-07 | 2026-06-15 | 2025-12-29 | 2026-04-09 | 0 | 0 | 203420798% | Remaining Total Cost | [17 empty] | 72383.9 | 996422.88 | 506590.44 | 234575.66 | 224235.1
|  |  | JDH3-02-008-R1-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2026-03-07 | 2026-06-15 | 2025-12-29 | 2026-04-09 | 0 | 0 | 203420798% | Actual Total Cost
|  |  | JDH3-02-008-R1-NetWork |  | 2026-04-14 | 2026-06-14 | 20-Apr-25 A | 2026-04-16 | 945682.23 | 945682.23 | 141301817% | Planned Total Cost | [20 empty] | 278270.24 | 660414.95 | 458820.3 | 15512.68
|  |  | JDH3-02-008-R1-NetWork |  | 2026-04-14 | 2026-06-14 | 20-Apr-25 A | 2026-04-16 | 945682.23 | 945682.23 | 141301817% | Remaining Total Cost | [20 empty] | 278270.24 | 189065.71
|  |  | JDH3-02-008-R1-NetWork |  | 2026-04-14 | 2026-06-14 | 20-Apr-25 A | 2026-04-16 | 945682.23 | 945682.23 | 141301817% | Actual Total Cost | [9 empty] | 44468.74 | 174910.38 | 267281.8 | 303894.46 | 155126.84
|  |  | JDH3-02-008-R1-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-04-14 | 2026-05-19 | 20-Apr-25 A | 31-Jul-25 A | 790555.38 | 790555.39 | 79055538% | Planned Total Cost | [21 empty] | 471349.24 | 319206.14
|  |  | JDH3-02-008-R1-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-04-14 | 2026-05-19 | 20-Apr-25 A | 31-Jul-25 A | 790555.38 | 790555.39 | 79055538% | Remaining Total Cost
|  |  | JDH3-02-008-R1-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-04-14 | 2026-05-19 | 20-Apr-25 A | 31-Jul-25 A | 790555.38 | 790555.39 | 79055538% | Actual Total Cost | [9 empty] | 44468.74 | 174910.38 | 267281.8 | 303894.46
|  |  | JDH3-02-008-R1-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-05-20 | 2026-05-31 | 2026-03-23 | 2026-04-04 | 0 | 0 | 4106299% | Planned Total Cost | [20 empty] | 36142.28 | 4920.72
|  |  | JDH3-02-008-R1-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-05-20 | 2026-05-31 | 2026-03-23 | 2026-04-04 | 0 | 0 | 4106299% | Remaining Total Cost | [20 empty] | 36142.28 | 4920.72
|  |  | JDH3-02-008-R1-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-05-20 | 2026-05-31 | 2026-03-23 | 2026-04-04 | 0 | 0 | 4106299% | Actual Total Cost
|  |  | JDH3-02-008-R1-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-05-23 | 2026-06-09 | 2026-03-25 | 2026-04-13 | 0 | 0 | 27114611% | Planned Total Cost | [20 empty] | 122128.73 | 149017.38
|  |  | JDH3-02-008-R1-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-05-23 | 2026-06-09 | 2026-03-25 | 2026-04-13 | 0 | 0 | 27114611% | Remaining Total Cost | [20 empty] | 122128.73 | 149017.38
|  |  | JDH3-02-008-R1-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-05-23 | 2026-06-09 | 2026-03-25 | 2026-04-13 | 0 | 0 | 27114611% | Actual Total Cost
|  |  | JDH3-02-008-R1-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2026-05-25 | 2026-06-14 | 08-Aug-25 A | 2026-04-16 | 2324-09-19 20:24 | 2324-09-19 20:10 | 31025369% | Planned Total Cost | [20 empty] | 119999.23 | 35127.61 | 139614.16 | 15512.68
|  |  | JDH3-02-008-R1-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2026-05-25 | 2026-06-14 | 08-Aug-25 A | 2026-04-16 | 2324-09-19 20:24 | 2324-09-19 20:10 | 31025369% | Remaining Total Cost | [20 empty] | 119999.23 | 35127.61
|  |  | JDH3-02-008-R1-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2026-05-25 | 2026-06-14 | 08-Aug-25 A | 2026-04-16 | 2324-09-19 20:24 | 2324-09-19 20:10 | 31025369% | Actual Total Cost | [13 empty] | 155126.84
|  |  | R2 |  | 2026-01-11 | 2026-06-09 | 08-Apr-25 A | 2026-05-25 | 1530483.32 | 1530483.32 | 385901937% | Planned Total Cost | [15 empty] | 26639.08 |  |  | 296971.29 | 435275.91 | 2185181.48 | 558204.14 | 356747.48
|  |  | R2 |  | 2026-01-11 | 2026-06-09 | 08-Apr-25 A | 2026-05-25 | 1530483.32 | 1530483.32 | 385901937% | Remaining Total Cost | [15 empty] | 26639.08 |  |  |  | 457789.07 | 929156.28 | 558204.14 | 356747.48
|  |  | R2 |  | 2026-01-11 | 2026-06-09 | 08-Apr-25 A | 2026-05-25 | 1530483.32 | 1530483.32 | 385901937% | Actual Total Cost | [9 empty] | 106540.98 | 222878.75 | 222878.75 | 231451.01 | 515282.84 | 222878.75 | 8572.26
|  |  | JDH3-02-008-R2-Storm Network - ST |  | 2026-01-11 | 2026-06-09 | 08-Apr-25 A | 2026-05-25 | 1530483.32 | 1530483.32 | 385901937% | Planned Total Cost | [15 empty] | 26639.08 |  |  | 296971.29 | 435275.91 | 2185181.48 | 558204.14 | 356747.48
|  |  | JDH3-02-008-R2-Storm Network - ST |  | 2026-01-11 | 2026-06-09 | 08-Apr-25 A | 2026-05-25 | 1530483.32 | 1530483.32 | 385901937% | Remaining Total Cost | [15 empty] | 26639.08 |  |  |  | 457789.07 | 929156.28 | 558204.14 | 356747.48
|  |  | JDH3-02-008-R2-Storm Network - ST |  | 2026-01-11 | 2026-06-09 | 08-Apr-25 A | 2026-05-25 | 1530483.32 | 1530483.32 | 385901937% | Actual Total Cost | [9 empty] | 106540.98 | 222878.75 | 222878.75 | 231451.01 | 515282.84 | 222878.75 | 8572.26
|  |  | JDH3-02-008-R2-(ST)-Swales |  | 2026-01-11 | 2026-06-09 | 08-Apr-25 A | 2026-05-25 | 1238079.23 | 1238079.23 | 294211384% | Planned Total Cost | [18 empty] | 296971.29 | 319319.81 | 1512044.75 | 457030.52 | 356747.48
|  |  | JDH3-02-008-R2-(ST)-Swales |  | 2026-01-11 | 2026-06-09 | 08-Apr-25 A | 2026-05-25 | 1238079.23 | 1238079.23 | 294211384% | Remaining Total Cost | [19 empty] | 341832.98 | 548423.64 | 457030.52 | 356747.48
|  |  | JDH3-02-008-R2-(ST)-Swales |  | 2026-01-11 | 2026-06-09 | 08-Apr-25 A | 2026-05-25 | 1238079.23 | 1238079.23 | 294211384% | Actual Total Cost | [9 empty] | 106540.98 | 222878.75 | 222878.75 | 231451.01 | 222878.75 | 222878.75 | 8572.26
|  |  | JDH3-02-008-R2-Box Culvert |  | 2026-02-03 | 2026-03-07 | 2025-10-02 | 2026-03-10 | 0 | 0 | 17759384% | Planned Total Cost | [15 empty] | 26639.08 |  |  |  | 115956.09 | 34998.67
|  |  | JDH3-02-008-R2-Box Culvert |  | 2026-02-03 | 2026-03-07 | 2025-10-02 | 2026-03-10 | 0 | 0 | 17759384% | Remaining Total Cost | [15 empty] | 26639.08 |  |  |  | 115956.09 | 34998.67
|  |  | JDH3-02-008-R2-Box Culvert |  | 2026-02-03 | 2026-03-07 | 2025-10-02 | 2026-03-10 | 0 | 0 | 17759384% | Actual Total Cost
|  |  | JDH3-02-008-R2-(ST)- Concrete Box Culvert With Dim (1000x1000) depth from 2.51 to 3.50 |  | 2026-02-03 | 2026-03-07 | 2025-10-02 | 2026-03-10 | 0 | 0 | 17759384% | Planned Total Cost | [15 empty] | 26639.08 |  |  |  | 115956.09 | 34998.67
|  |  | JDH3-02-008-R2-(ST)- Concrete Box Culvert With Dim (1000x1000) depth from 2.51 to 3.50 |  | 2026-02-03 | 2026-03-07 | 2025-10-02 | 2026-03-10 | 0 | 0 | 17759384% | Remaining Total Cost | [15 empty] | 26639.08 |  |  |  | 115956.09 | 34998.67
|  |  | JDH3-02-008-R2-(ST)- Concrete Box Culvert With Dim (1000x1000) depth from 2.51 to 3.50 |  | 2026-02-03 | 2026-03-07 | 2025-10-02 | 2026-03-10 | 0 | 0 | 17759384% | Actual Total Cost
|  |  | JDH3-02-008-R2-NetWork |  | 2026-03-08 | 2026-03-28 | 08-Aug-25 A | 2026-04-11 | 292404.1 | 292404.09 | 73931168% | Planned Total Cost | [20 empty] | 638138.06 | 101173.62
|  |  | JDH3-02-008-R2-NetWork |  | 2026-03-08 | 2026-03-28 | 08-Aug-25 A | 2026-04-11 | 292404.1 | 292404.09 | 73931168% | Remaining Total Cost | [20 empty] | 345733.97 | 101173.62
|  |  | JDH3-02-008-R2-NetWork |  | 2026-03-08 | 2026-03-28 | 08-Aug-25 A | 2026-04-11 | 292404.1 | 292404.09 | 73931168% | Actual Total Cost | [13 empty] | 292404.09
|  |  | JDH3-02-008-R2-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-03-08 | 2026-03-21 | 08-Aug-25 A | 31-Aug-25 A | 292404.1 | 292404.09 | 29240410% | Planned Total Cost | [20 empty] | 292404.1
|  |  | JDH3-02-008-R2-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-03-08 | 2026-03-21 | 08-Aug-25 A | 31-Aug-25 A | 292404.1 | 292404.09 | 29240410% | Remaining Total Cost
|  |  | JDH3-02-008-R2-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-03-08 | 2026-03-21 | 08-Aug-25 A | 31-Aug-25 A | 292404.1 | 292404.09 | 29240410% | Actual Total Cost | [13 empty] | 292404.09
|  |  | JDH3-02-008-R2-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-03-10 | 2026-03-22 | 2026-03-23 | 2026-04-05 | 0 | 0 | 12318989% | Planned Total Cost | [20 empty] | 105984.36 | 17205.52
|  |  | JDH3-02-008-R2-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-03-10 | 2026-03-22 | 2026-03-23 | 2026-04-05 | 0 | 0 | 12318989% | Remaining Total Cost | [20 empty] | 105984.36 | 17205.52
|  |  | JDH3-02-008-R2-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-03-10 | 2026-03-22 | 2026-03-23 | 2026-04-05 | 0 | 0 | 12318989% | Actual Total Cost
|  |  | JDH3-02-008-R2-(ST)- Supply and install UPVC pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-03-10 | 2026-03-25 | 2026-03-23 | 2026-04-08 | 0 | 0 | 22660045% | Planned Total Cost | [20 empty] | 182841.38 | 43759.06
|  |  | JDH3-02-008-R2-(ST)- Supply and install UPVC pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-03-10 | 2026-03-25 | 2026-03-23 | 2026-04-08 | 0 | 0 | 22660045% | Remaining Total Cost | [20 empty] | 182841.38 | 43759.06
|  |  | JDH3-02-008-R2-(ST)- Supply and install UPVC pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-03-10 | 2026-03-25 | 2026-03-23 | 2026-04-08 | 0 | 0 | 22660045% | Actual Total Cost
|  |  | JDH3-02-008-R2-(ST)- Single Catchbasine Works |  | 2026-03-12 | 2026-03-23 | 2026-03-25 | 2026-04-06 | 0 | 0 | 4692916% | Planned Total Cost | [20 empty] | 40213.07 | 6716.08
|  |  | JDH3-02-008-R2-(ST)- Single Catchbasine Works |  | 2026-03-12 | 2026-03-23 | 2026-03-25 | 2026-04-06 | 0 | 0 | 4692916% | Remaining Total Cost | [20 empty] | 40213.07 | 6716.08
|  |  | JDH3-02-008-R2-(ST)- Single Catchbasine Works |  | 2026-03-12 | 2026-03-23 | 2026-03-25 | 2026-04-06 | 0 | 0 | 4692916% | Actual Total Cost
|  |  | JDH3-02-008-R2-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-03-17 | 2026-03-28 | 2026-03-30 | 2026-04-11 | 0 | 0 | 1368766% | Planned Total Cost | [20 empty] | 2064.56 | 11623.11
|  |  | JDH3-02-008-R2-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-03-17 | 2026-03-28 | 2026-03-30 | 2026-04-11 | 0 | 0 | 1368766% | Remaining Total Cost | [20 empty] | 2064.56 | 11623.11
|  |  | JDH3-02-008-R2-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-03-17 | 2026-03-28 | 2026-03-30 | 2026-04-11 | 0 | 0 | 1368766% | Actual Total Cost
|  |  | JDH3-02-008-R2-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2026-03-15 | 2026-03-25 | 2026-03-28 | 2026-04-08 | 0 | 0 | 3650043% | Planned Total Cost | [20 empty] | 14630.59 | 21869.84
|  |  | JDH3-02-008-R2-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2026-03-15 | 2026-03-25 | 2026-03-28 | 2026-04-08 | 0 | 0 | 3650043% | Remaining Total Cost | [20 empty] | 14630.59 | 21869.84
|  |  | JDH3-02-008-R2-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2026-03-15 | 2026-03-25 | 2026-03-28 | 2026-04-08 | 0 | 0 | 3650043% | Actual Total Cost
|  |  | C-01 |  | 2024-08-27 | 2024-12-15 | 11-Jan-25 A | 2025-10-22 | 888462.12 | 888462.12 | 102106637% | Planned Total Cost |  |  | 121965.23 | 36723181% | 44652294% | 2907077% | [9 empty] | 56275.63
|  |  | C-01 |  | 2024-08-27 | 2024-12-15 | 11-Jan-25 A | 2025-10-22 | 888462.12 | 888462.12 | 102106637% | Remaining Total Cost | [15 empty] | 132604.26
|  |  | C-01 |  | 2024-08-27 | 2024-12-15 | 11-Jan-25 A | 2025-10-22 | 888462.12 | 888462.12 | 102106637% | Actual Total Cost | [6 empty] | 4700.1 | 4760.36 | 6568.1 | 2530.83 | 101640.07 | 164163.11 | 170477.07 | 367675.83 | 63504.17 | 2442.47
|  |  | JDH3-02-008-C-01-Storm Network - ST |  | 2024-09-10 | 2024-12-01 | 05-May-25 A | 2025-10-11 | 869179.63 | 869179.63 | 98200869% | Planned Total Cost |  |  | 121965.23 | 36723181% | 44652294% | 978828% | [9 empty] | 36500.43
|  |  | JDH3-02-008-C-01-Storm Network - ST |  | 2024-09-10 | 2024-12-01 | 05-May-25 A | 2025-10-11 | 869179.63 | 869179.63 | 98200869% | Remaining Total Cost | [15 empty] | 112829.06
|  |  | JDH3-02-008-C-01-Storm Network - ST |  | 2024-09-10 | 2024-12-01 | 05-May-25 A | 2025-10-11 | 869179.63 | 869179.63 | 98200869% | Actual Total Cost | [10 empty] | 100916.98 | 164163.11 | 170477.07 | 367675.83 | 63504.17 | 2442.47
|  |  | JDH3-02-008-C-01-(ST)-Swales |  | 2024-09-10 | 2024-11-17 | 05-May-25 A | 2025-10-11 | 539030.82 | 539030.82 | 61535945% | Planned Total Cost |  |  | 121965.23 | 36723181% | 12616242%
|  |  | JDH3-02-008-C-01-(ST)-Swales |  | 2024-09-10 | 2024-11-17 | 05-May-25 A | 2025-10-11 | 539030.82 | 539030.82 | 61535945% | Remaining Total Cost | [15 empty] | 76328.63
|  |  | JDH3-02-008-C-01-(ST)-Swales |  | 2024-09-10 | 2024-11-17 | 05-May-25 A | 2025-10-11 | 539030.82 | 539030.82 | 61535945% | Actual Total Cost | [10 empty] | 100916.98 | 164163.11 | 170477.07 | 37527.02 | 63504.17 | 2442.47
|  |  | JDH3-02-008-C-01-(ST)-Network |  | 2024-11-18 | 2024-12-01 | 12-Aug-25 A | 2025-10-08 | 330148.8 | 330148.81 | 36664924% | Planned Total Cost |  |  |  |  | 32036052% | 978828% | [9 empty] | 36500.43
|  |  | JDH3-02-008-C-01-(ST)-Network |  | 2024-11-18 | 2024-12-01 | 12-Aug-25 A | 2025-10-08 | 330148.8 | 330148.81 | 36664924% | Remaining Total Cost | [15 empty] | 36500.43
|  |  | JDH3-02-008-C-01-(ST)-Network |  | 2024-11-18 | 2024-12-01 | 12-Aug-25 A | 2025-10-08 | 330148.8 | 330148.81 | 36664924% | Actual Total Cost | [13 empty] | 330148.81
|  |  | JDH3-02-008-C-01-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2024-11-18 | 2024-12-01 | 12-Aug-25 A | 30-Aug-25 A | 293648.37 | 293648.37 | 29364837% | Planned Total Cost |  |  |  |  | 28386009% | 978828%
|  |  | JDH3-02-008-C-01-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2024-11-18 | 2024-12-01 | 12-Aug-25 A | 30-Aug-25 A | 293648.37 | 293648.37 | 29364837% | Remaining Total Cost
|  |  | JDH3-02-008-C-01-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2024-11-18 | 2024-12-01 | 12-Aug-25 A | 30-Aug-25 A | 293648.37 | 293648.37 | 29364837% | Actual Total Cost | [13 empty] | 293648.37
|  |  | JDH3-02-008-C-01-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2024-11-18 | 2024-11-28 | 12-Aug-25 A | 2025-10-08 | 1999-12-06 10:19 | 1999-12-06 10:34 | 7300087% | Planned Total Cost |  |  |  |  | 3650043% | [10 empty] | 36500.43
|  |  | JDH3-02-008-C-01-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2024-11-18 | 2024-11-28 | 12-Aug-25 A | 2025-10-08 | 1999-12-06 10:19 | 1999-12-06 10:34 | 7300087% | Remaining Total Cost | [15 empty] | 36500.43
|  |  | JDH3-02-008-C-01-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2024-11-18 | 2024-11-28 | 12-Aug-25 A | 2025-10-08 | 1999-12-06 10:19 | 1999-12-06 10:34 | 7300087% | Actual Total Cost | [13 empty] | 36500.44
|  |  | JDH3-02-008-C-01-TSE Network - TSE |  | 2024-12-02 | 2024-12-15 | 11-Jan-25 A | 2025-10-22 | 1952-10-15 11:46 | 1952-10-15 11:46 | 3905769% | Planned Total Cost | [5 empty] | 1928249% | [9 empty] | 19775.2
|  |  | JDH3-02-008-C-01-TSE Network - TSE |  | 2024-12-02 | 2024-12-15 | 11-Jan-25 A | 2025-10-22 | 1952-10-15 11:46 | 1952-10-15 11:46 | 3905769% | Remaining Total Cost | [15 empty] | 19775.2
|  |  | JDH3-02-008-C-01-TSE Network - TSE |  | 2024-12-02 | 2024-12-15 | 11-Jan-25 A | 2025-10-22 | 1952-10-15 11:46 | 1952-10-15 11:46 | 3905769% | Actual Total Cost | [6 empty] | 4700.1 | 4760.36 | 6568.1 | 2530.83 | 723.09
|  |  | JDH3-02-008-C-01-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-12-02 | 2024-12-15 | 2025-10-09 | 2025-10-22 | 0 | 0 | 1201623% | Planned Total Cost | [15 empty] | 12016.23
|  |  | JDH3-02-008-C-01-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-12-02 | 2024-12-15 | 2025-10-09 | 2025-10-22 | 0 | 0 | 1201623% | Remaining Total Cost | [15 empty] | 12016.23
|  |  | JDH3-02-008-C-01-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-12-02 | 2024-12-15 | 2025-10-09 | 2025-10-22 | 0 | 0 | 1201623% | Actual Total Cost
|  |  | JDH3-02-008-C-01-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2024-12-04 | 2024-12-15 | 11-Jan-25 A | 07-May-25 A | 1952-10-15 11:46 | 1952-10-15 11:46 | 1928249% | Planned Total Cost | [5 empty] | 1928249%
|  |  | JDH3-02-008-C-01-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2024-12-04 | 2024-12-15 | 11-Jan-25 A | 07-May-25 A | 1952-10-15 11:46 | 1952-10-15 11:46 | 1928249% | Remaining Total Cost
|  |  | JDH3-02-008-C-01-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2024-12-04 | 2024-12-15 | 11-Jan-25 A | 07-May-25 A | 1952-10-15 11:46 | 1952-10-15 11:46 | 1928249% | Actual Total Cost | [6 empty] | 4700.1 | 4760.36 | 6568.1 | 2530.83 | 723.09
|  |  | JDH3-02-008-C-01-(TSE)-Supply and install gate valves-100 mm |  | 2024-12-09 | 2024-12-12 | 2025-10-16 | 2025-10-20 | 0 | 0 | 775896% | Planned Total Cost | [15 empty] | 7758.96
|  |  | JDH3-02-008-C-01-(TSE)-Supply and install gate valves-100 mm |  | 2024-12-09 | 2024-12-12 | 2025-10-16 | 2025-10-20 | 0 | 0 | 775896% | Remaining Total Cost | [15 empty] | 7758.96
|  |  | JDH3-02-008-C-01-(TSE)-Supply and install gate valves-100 mm |  | 2024-12-09 | 2024-12-12 | 2025-10-16 | 2025-10-20 | 0 | 0 | 775896% | Actual Total Cost
|  |  | C-02 |  | 2024-12-14 | 2025-03-06 | 12-Jun-25 A | 2025-11-05 | 524034.69 | 524034.68 | 140042835% | Planned Total Cost | [5 empty] | 6733562% | 510061.61 | 439834.3 | 40027.22 | [6 empty] | 270013.44 | 73156.16
|  |  | C-02 |  | 2024-12-14 | 2025-03-06 | 12-Jun-25 A | 2025-11-05 | 524034.69 | 524034.68 | 140042835% | Remaining Total Cost | [15 empty] | 787062.49 | 89331.16
|  |  | C-02 |  | 2024-12-14 | 2025-03-06 | 12-Jun-25 A | 2025-11-05 | 524034.69 | 524034.68 | 140042835% | Actual Total Cost | [11 empty] | 9629.58 | 7489.67 | 257535.75 | 239323.08 | 10056.6
|  |  | JDH3-02-008-C-02-Storm Network - ST |  | 2024-12-22 | 2025-02-11 | 21-Jun-25 A | 2025-10-22 | 285512.48 | 285512.47 | 70613886% | Planned Total Cost | [5 empty] | 6733562% | 510061.61 | 119616.53 | [7 empty] | 9125.11
|  |  | JDH3-02-008-C-02-Storm Network - ST |  | 2024-12-22 | 2025-02-11 | 21-Jun-25 A | 2025-10-22 | 285512.48 | 285512.47 | 70613886% | Remaining Total Cost | [15 empty] | 420626.38
|  |  | JDH3-02-008-C-02-Storm Network - ST |  | 2024-12-22 | 2025-02-11 | 21-Jun-25 A | 2025-10-22 | 285512.48 | 285512.47 | 70613886% | Actual Total Cost | [11 empty] | 9629.58 | 7489.67 | 190289.44 | 75211.05 | 2892.73
|  |  | JDH3-02-008-C-02-(ST)-Swales |  | 2024-12-22 | 2025-01-28 | 21-Jun-25 A | 2025-10-22 | 2278-07-29 02:10 | 2278-07-29 02:24 | 54977437% | Planned Total Cost | [5 empty] | 6733562% | 482438.75
|  |  | JDH3-02-008-C-02-(ST)-Swales |  | 2024-12-22 | 2025-01-28 | 21-Jun-25 A | 2025-10-22 | 2278-07-29 02:10 | 2278-07-29 02:24 | 54977437% | Remaining Total Cost | [15 empty] | 411501.27
|  |  | JDH3-02-008-C-02-(ST)-Swales |  | 2024-12-22 | 2025-01-28 | 21-Jun-25 A | 2025-10-22 | 2278-07-29 02:10 | 2278-07-29 02:24 | 54977437% | Actual Total Cost | [11 empty] | 9629.58 | 7489.67 | 43050.07 | 75211.05 | 2892.73
|  |  | JDH3-02-008-C-02-(ST)-Network |  | 2025-01-29 | 2025-02-11 | 04-Aug-25 A | 2025-10-16 | 2303-02-15 09:07 | 2303-02-15 08:53 | 15636449% | Planned Total Cost | [6 empty] | 27622.85 | 119616.53 | [7 empty] | 9125.11
|  |  | JDH3-02-008-C-02-(ST)-Network |  | 2025-01-29 | 2025-02-11 | 04-Aug-25 A | 2025-10-16 | 2303-02-15 09:07 | 2303-02-15 08:53 | 15636449% | Remaining Total Cost | [15 empty] | 9125.11
|  |  | JDH3-02-008-C-02-(ST)-Network |  | 2025-01-29 | 2025-02-11 | 04-Aug-25 A | 2025-10-16 | 2303-02-15 09:07 | 2303-02-15 08:53 | 15636449% | Actual Total Cost | [13 empty] | 147239.37
|  |  | JDH3-02-008-C-02-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-01-29 | 2025-02-09 | 04-Aug-25 A | 23-Aug-25 A | 2278-02-20 06:29 | 2278-02-20 06:29 | 13811427% | Planned Total Cost | [6 empty] | 27622.85 | 110491.42
|  |  | JDH3-02-008-C-02-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-01-29 | 2025-02-09 | 04-Aug-25 A | 23-Aug-25 A | 2278-02-20 06:29 | 2278-02-20 06:29 | 13811427% | Remaining Total Cost
|  |  | JDH3-02-008-C-02-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-01-29 | 2025-02-09 | 04-Aug-25 A | 23-Aug-25 A | 2278-02-20 06:29 | 2278-02-20 06:29 | 13811427% | Actual Total Cost | [13 empty] | 138114.27
|  |  | JDH3-02-008-C-02-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-02-01 | 2025-02-11 | 04-Aug-25 A | 2025-10-16 | 1924-12-24 02:38 | 1924-12-24 02:24 | 1825022% | Planned Total Cost | [7 empty] | 9125.11 | [7 empty] | 9125.11
|  |  | JDH3-02-008-C-02-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-02-01 | 2025-02-11 | 04-Aug-25 A | 2025-10-16 | 1924-12-24 02:38 | 1924-12-24 02:24 | 1825022% | Remaining Total Cost | [15 empty] | 9125.11
|  |  | JDH3-02-008-C-02-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-02-01 | 2025-02-11 | 04-Aug-25 A | 2025-10-16 | 1924-12-24 02:38 | 1924-12-24 02:24 | 1825022% | Actual Total Cost | [13 empty] | 9125.1
|  |  | JDH3-02-008-C-02-TSE Network - TSE |  | 2025-02-12 | 2025-03-06 | 11-Aug-25 A | 2025-11-05 | 238522.21 | 238522.21 | 69428949% | Planned Total Cost | [7 empty] | 320217.77 | 40027.22 | [6 empty] | 260888.33 | 73156.16
|  |  | JDH3-02-008-C-02-TSE Network - TSE |  | 2025-02-12 | 2025-03-06 | 11-Aug-25 A | 2025-11-05 | 238522.21 | 238522.21 | 69428949% | Remaining Total Cost | [15 empty] | 366436.11 | 89331.16
|  |  | JDH3-02-008-C-02-TSE Network - TSE |  | 2025-02-12 | 2025-03-06 | 11-Aug-25 A | 2025-11-05 | 238522.21 | 238522.21 | 69428949% | Actual Total Cost | [13 empty] | 67246.31 | 164112.03 | 7163.87
|  |  | JDH3-02-008-C-02-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-02-12 | 2025-03-04 | 2025-10-23 | 2025-11-05 | 0 | 0 | 700043% | Planned Total Cost | [15 empty] | 5950.36 | 1050.06
|  |  | JDH3-02-008-C-02-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-02-12 | 2025-03-04 | 2025-10-23 | 2025-11-05 | 0 | 0 | 700043% | Remaining Total Cost | [15 empty] | 5950.36 | 1050.06
|  |  | JDH3-02-008-C-02-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-02-12 | 2025-03-04 | 2025-10-23 | 2025-11-05 | 0 | 0 | 700043% | Actual Total Cost
|  |  | JDH3-02-008-C-02-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-02-12 | 2025-03-04 | 2025-10-23 | 2025-11-05 | 0 | 0 | 89791% | Planned Total Cost | [15 empty] | 763.23 | 134.69
|  |  | JDH3-02-008-C-02-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-02-12 | 2025-03-04 | 2025-10-23 | 2025-11-05 | 0 | 0 | 89791% | Remaining Total Cost | [15 empty] | 763.23 | 134.69
|  |  | JDH3-02-008-C-02-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-02-12 | 2025-03-04 | 2025-10-23 | 2025-11-05 | 0 | 0 | 89791% | Actual Total Cost
|  |  | JDH3-02-008-C-02-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2025-02-12 | 2025-03-06 | 11-Aug-25 A | 2025-11-03 | 238522.21 | 238522.21 | 40027222% | Planned Total Cost | [7 empty] | 320217.77 | 40027.22 | [6 empty] | 40027.22
|  |  | JDH3-02-008-C-02-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2025-02-12 | 2025-03-06 | 11-Aug-25 A | 2025-11-03 | 238522.21 | 238522.21 | 40027222% | Remaining Total Cost | [15 empty] | 145575 | 16175
|  |  | JDH3-02-008-C-02-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2025-02-12 | 2025-03-06 | 11-Aug-25 A | 2025-11-03 | 238522.21 | 238522.21 | 40027222% | Actual Total Cost | [13 empty] | 67246.31 | 164112.03 | 7163.87
|  |  | JDH3-02-008-C-02-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 1.51 to 2.5 m |  | 2025-02-12 | 2025-03-04 | 2025-10-23 | 2025-11-05 | 0 | 0 | 10300521% | Planned Total Cost | [15 empty] | 87554.43 | 15450.78
|  |  | JDH3-02-008-C-02-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 1.51 to 2.5 m |  | 2025-02-12 | 2025-03-04 | 2025-10-23 | 2025-11-05 | 0 | 0 | 10300521% | Remaining Total Cost | [15 empty] | 87554.43 | 15450.78
|  |  | JDH3-02-008-C-02-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 1.51 to 2.5 m |  | 2025-02-12 | 2025-03-04 | 2025-10-23 | 2025-11-05 | 0 | 0 | 10300521% | Actual Total Cost
|  |  | JDH3-02-008-C-02-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 2.51 to 3.5 m |  | 2025-02-12 | 2025-03-04 | 2025-10-23 | 2025-11-05 | 0 | 0 | 7467676% | Planned Total Cost | [15 empty] | 63475.25 | 11201.51
|  |  | JDH3-02-008-C-02-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 2.51 to 3.5 m |  | 2025-02-12 | 2025-03-04 | 2025-10-23 | 2025-11-05 | 0 | 0 | 7467676% | Remaining Total Cost | [15 empty] | 63475.25 | 11201.51
|  |  | JDH3-02-008-C-02-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 2.51 to 3.5 m |  | 2025-02-12 | 2025-03-04 | 2025-10-23 | 2025-11-05 | 0 | 0 | 7467676% | Actual Total Cost
|  |  | JDH3-02-008-C-02-(TSE)-Supply and install gate valves-100 mm |  | 2025-02-26 | 2025-03-02 | 2025-10-30 | 2025-11-03 | 0 | 0 | 517264% | Planned Total Cost | [15 empty] | 2327.69 | 2844.95
|  |  | JDH3-02-008-C-02-(TSE)-Supply and install gate valves-100 mm |  | 2025-02-26 | 2025-03-02 | 2025-10-30 | 2025-11-03 | 0 | 0 | 517264% | Remaining Total Cost | [15 empty] | 2327.69 | 2844.95
|  |  | JDH3-02-008-C-02-(TSE)-Supply and install gate valves-100 mm |  | 2025-02-26 | 2025-03-02 | 2025-10-30 | 2025-11-03 | 0 | 0 | 517264% | Actual Total Cost
|  |  | JDH3-02-008-C-02-(TSE)-Supply and install gate valves-250 mm |  | 2025-02-26 | 2025-03-02 | 2025-10-30 | 2025-11-03 | 0 | 0 | 256611% | Planned Total Cost | [15 empty] | 1154.75 | 1411.36
|  |  | JDH3-02-008-C-02-(TSE)-Supply and install gate valves-250 mm |  | 2025-02-26 | 2025-03-02 | 2025-10-30 | 2025-11-03 | 0 | 0 | 256611% | Remaining Total Cost | [15 empty] | 1154.75 | 1411.36
|  |  | JDH3-02-008-C-02-(TSE)-Supply and install gate valves-250 mm |  | 2025-02-26 | 2025-03-02 | 2025-10-30 | 2025-11-03 | 0 | 0 | 256611% | Actual Total Cost
|  |  | JDH3-02-008-C-02-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2025-02-26 | 2025-03-02 | 2025-10-30 | 2025-11-03 | 0 | 0 | 4731630% | Planned Total Cost | [15 empty] | 21292.33 | 26023.96
|  |  | JDH3-02-008-C-02-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2025-02-26 | 2025-03-02 | 2025-10-30 | 2025-11-03 | 0 | 0 | 4731630% | Remaining Total Cost | [15 empty] | 21292.33 | 26023.96
|  |  | JDH3-02-008-C-02-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2025-02-26 | 2025-03-02 | 2025-10-30 | 2025-11-03 | 0 | 0 | 4731630% | Actual Total Cost
|  |  | JDH3-02-008-C-02-(TSE)-Supply and install of Air valves-65 mm. |  | 2025-02-26 | 2025-03-02 | 2025-10-30 | 2025-11-03 | 0 | 0 | 2473948% | Planned Total Cost | [15 empty] | 11132.77 | 13606.72
|  |  | JDH3-02-008-C-02-(TSE)-Supply and install of Air valves-65 mm. |  | 2025-02-26 | 2025-03-02 | 2025-10-30 | 2025-11-03 | 0 | 0 | 2473948% | Remaining Total Cost | [15 empty] | 11132.77 | 13606.72
|  |  | JDH3-02-008-C-02-(TSE)-Supply and install of Air valves-65 mm. |  | 2025-02-26 | 2025-03-02 | 2025-10-30 | 2025-11-03 | 0 | 0 | 2473948% | Actual Total Cost
|  |  | JDH3-02-008-C-02-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2025-02-12 | 2025-02-20 | 2025-10-23 | 2025-11-01 | 0 | 0 | 1820460% | Planned Total Cost | [15 empty] | 17294.37 | 910.23
|  |  | JDH3-02-008-C-02-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2025-02-12 | 2025-02-20 | 2025-10-23 | 2025-11-01 | 0 | 0 | 1820460% | Remaining Total Cost | [15 empty] | 17294.37 | 910.23
|  |  | JDH3-02-008-C-02-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2025-02-12 | 2025-02-20 | 2025-10-23 | 2025-11-01 | 0 | 0 | 1820460% | Actual Total Cost
|  |  | JDH3-02-008-C-02-(TSE)- Supply and Construct Air Valves Chamber on 355-630 mm Diameter pipelines |  | 2025-02-12 | 2025-02-20 | 2025-10-23 | 2025-11-01 | 0 | 0 | 1043783% | Planned Total Cost | [15 empty] | 9915.94 | 521.89
|  |  | JDH3-02-008-C-02-(TSE)- Supply and Construct Air Valves Chamber on 355-630 mm Diameter pipelines |  | 2025-02-12 | 2025-02-20 | 2025-10-23 | 2025-11-01 | 0 | 0 | 1043783% | Remaining Total Cost | [15 empty] | 9915.94 | 521.89
|  |  | JDH3-02-008-C-02-(TSE)- Supply and Construct Air Valves Chamber on 355-630 mm Diameter pipelines |  | 2025-02-12 | 2025-02-20 | 2025-10-23 | 2025-11-01 | 0 | 0 | 1043783% | Actual Total Cost
|  |  | C-03 |  | 2025-05-05 | 2026-01-11 | 08-Jan-25 A | 2026-03-03 | 2257288.21 | 2257288.22 | 647233076% | Planned Total Cost | [10 empty] | 322292.05 | 369721.82 | 549466.08 | 789044.12 | 366816.41 | 111283.75 | 1249426.95 | 1126701.53 | 914785.15 | 572114.69 | 100678.2
|  |  | C-03 |  | 2025-05-05 | 2026-01-11 | 08-Jan-25 A | 2026-03-03 | 2257288.21 | 2257288.22 | 647233076% | Remaining Total Cost | [15 empty] | 76445.96 | 1473105.51 | 1077913.03 | 914785.15 | 572114.69 | 100678.2
|  |  | C-03 |  | 2025-05-05 | 2026-01-11 | 08-Jan-25 A | 2026-03-03 | 2257288.21 | 2257288.22 | 647233076% | Actual Total Cost | [6 empty] | 18129.11 | 57340.29 | 36260.05 | 157705.35 | 272661.57 | 320963.75 | 553511.15 | 195448.66 | 621002.26 | 24266.04
|  |  | JDH3-02-008-C-03-Sewage Network - SS |  | 2025-05-13 | 2025-06-01 | 18-Jan-25 A | 2025-11-10 | 248086.78 | 248086.78 | 27731307% | Planned Total Cost | [10 empty] | 245302.51 | 2784.27 |  |  |  | 18080.62 | 11145.67
|  |  | JDH3-02-008-C-03-Sewage Network - SS |  | 2025-05-13 | 2025-06-01 | 18-Jan-25 A | 2025-11-10 | 248086.78 | 248086.78 | 27731307% | Remaining Total Cost | [15 empty] | 18080.62 | 11145.67
|  |  | JDH3-02-008-C-03-Sewage Network - SS |  | 2025-05-13 | 2025-06-01 | 18-Jan-25 A | 2025-11-10 | 248086.78 | 248086.78 | 27731307% | Actual Total Cost | [6 empty] | 18129.11 | 57340.29 | 36260.05 | 40751.57 | 35980 | 29522.26 | 12022.87 | 18080.62
|  |  | JDH3-02-008-C-03-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2025-05-13 | 2025-06-01 | 18-Jan-25 A | 31-Jul-25 A | 2204-12-01 19:41 | 2204-12-01 19:26 | 11137082% | Planned Total Cost | [10 empty] | 108586.55 | 2784.27
|  |  | JDH3-02-008-C-03-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2025-05-13 | 2025-06-01 | 18-Jan-25 A | 31-Jul-25 A | 2204-12-01 19:41 | 2204-12-01 19:26 | 11137082% | Remaining Total Cost
|  |  | JDH3-02-008-C-03-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2025-05-13 | 2025-06-01 | 18-Jan-25 A | 31-Jul-25 A | 2204-12-01 19:41 | 2204-12-01 19:26 | 11137082% | Actual Total Cost | [6 empty] | 3005.14 | 6184.29 | 19428.54 | 28982.74 | 26733.9 | 22404.68 | 4631.53
|  |  | JDH3-02-008-C-03-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2025-05-13 | 2025-05-24 | 21-Jan-25 A | 20-Apr-25 A | 2051-11-19 12:58 | 2051-11-19 12:58 | 5547654% | Planned Total Cost | [10 empty] | 55476.54
|  |  | JDH3-02-008-C-03-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2025-05-13 | 2025-05-24 | 21-Jan-25 A | 20-Apr-25 A | 2051-11-19 12:58 | 2051-11-19 12:58 | 5547654% | Remaining Total Cost
|  |  | JDH3-02-008-C-03-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2025-05-13 | 2025-05-24 | 21-Jan-25 A | 20-Apr-25 A | 2051-11-19 12:58 | 2051-11-19 12:58 | 5547654% | Actual Total Cost | [6 empty] | 9396.34 | 35366.3 | 8356.15 | 2357.75
|  |  | JDH3-02-008-C-03-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2025-05-13 | 2025-05-26 | 21-Jan-25 A | 2025-11-10 | 2072-11-30 19:12 | 2072-11-30 19:26 | 7430447% | Planned Total Cost | [10 empty] | 63158.8 | [5 empty] | 11145.67
|  |  | JDH3-02-008-C-03-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2025-05-13 | 2025-05-26 | 21-Jan-25 A | 2025-11-10 | 2072-11-30 19:12 | 2072-11-30 19:26 | 7430447% | Remaining Total Cost | [16 empty] | 11145.67
|  |  | JDH3-02-008-C-03-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2025-05-13 | 2025-05-26 | 21-Jan-25 A | 2025-11-10 | 2072-11-30 19:12 | 2072-11-30 19:26 | 7430447% | Actual Total Cost | [6 empty] | 5727.64 | 15789.7 | 8475.35 | 9411.09 | 9246.1 | 7117.59 | 7391.34
|  |  | JDH3-02-008-C-03-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2025-05-13 | 2025-05-24 | 01-Aug-25 A | 2025-10-08 | 1949-07-01 14:53 | 1949-07-01 14:53 | 3616124% | Planned Total Cost | [10 empty] | 18080.62 |  |  |  |  | 18080.62
|  |  | JDH3-02-008-C-03-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2025-05-13 | 2025-05-24 | 01-Aug-25 A | 2025-10-08 | 1949-07-01 14:53 | 1949-07-01 14:53 | 3616124% | Remaining Total Cost | [15 empty] | 18080.62
|  |  | JDH3-02-008-C-03-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2025-05-13 | 2025-05-24 | 01-Aug-25 A | 2025-10-08 | 1949-07-01 14:53 | 1949-07-01 14:53 | 3616124% | Actual Total Cost | [13 empty] | 18080.62
|  |  | JDH3-02-008-C-03-Storm Network - ST |  | 2025-05-25 | 2026-01-11 | 08-Apr-25 A | 2026-03-03 | 1573421.63 | 1573421.63 | 499034181% | Planned Total Cost | [10 empty] | 76989.54 | 277333.01 | 414667.28 | 531547.81 | 253518.04 | 93203.13 | 887801.34 | 998003.66 | 914785.15 | 441814.66 | 100678.2
|  |  | JDH3-02-008-C-03-Storm Network - ST |  | 2025-05-25 | 2026-01-11 | 08-Apr-25 A | 2026-03-03 | 1573421.63 | 1573421.63 | 499034181% | Remaining Total Cost | [15 empty] | 58365.34 | 903273.18 | 998003.66 | 914785.15 | 441814.66 | 100678.2
|  |  | JDH3-02-008-C-03-Storm Network - ST |  | 2025-05-25 | 2026-01-11 | 08-Apr-25 A | 2026-03-03 | 1573421.63 | 1573421.63 | 499034181% | Actual Total Cost | [9 empty] | 116953.77 | 236681.56 | 291441.48 | 541488.28 | 125728.37 | 251456.74 | 9671.41
|  |  | JDH3-02-008-C-03-(ST)-Swales |  | 2025-05-25 | 2025-10-21 | 08-Apr-25 A | 2025-12-11 | 1573421.63 | 1573421.63 | 222298628% | Planned Total Cost | [10 empty] | 76989.54 | 277333.01 | 414667.28 | 531547.81 | 253518.04 | 93203.13 | 394643.16 | 181084.31
|  |  | JDH3-02-008-C-03-(ST)-Swales |  | 2025-05-25 | 2025-10-21 | 08-Apr-25 A | 2025-12-11 | 1573421.63 | 1573421.63 | 222298628% | Remaining Total Cost | [15 empty] | 58365.34 | 410115 | 181084.31
|  |  | JDH3-02-008-C-03-(ST)-Swales |  | 2025-05-25 | 2025-10-21 | 08-Apr-25 A | 2025-12-11 | 1573421.63 | 1573421.63 | 222298628% | Actual Total Cost | [9 empty] | 116953.77 | 236681.56 | 291441.48 | 541488.28 | 125728.37 | 251456.74 | 9671.41
|  |  | JDH3-02-008-C-03-(ST)-Box Culvert |  | 2025-10-22 | 2026-01-11 | 2025-12-13 | 2026-03-03 | 0 | 0 | 227419735% | Planned Total Cost | [17 empty] | 816919.34 | 914785.15 | 441814.66 | 100678.2
|  |  | JDH3-02-008-C-03-(ST)-Box Culvert |  | 2025-10-22 | 2026-01-11 | 2025-12-13 | 2026-03-03 | 0 | 0 | 227419735% | Remaining Total Cost | [17 empty] | 816919.34 | 914785.15 | 441814.66 | 100678.2
|  |  | JDH3-02-008-C-03-(ST)-Box Culvert |  | 2025-10-22 | 2026-01-11 | 2025-12-13 | 2026-03-03 | 0 | 0 | 227419735% | Actual Total Cost
|  |  | JDH3-02-008-C-03-(ST)- Concrete Box Culvert With Dim (1000x1000) depth from 2.51 to 3.50 |  | 2025-10-22 | 2025-12-29 | 2025-12-13 | 2026-02-18 | 0 | 0 | 45623246% | Planned Total Cost | [17 empty] | 228116.23 | 138211.6 | 89904.63
|  |  | JDH3-02-008-C-03-(ST)- Concrete Box Culvert With Dim (1000x1000) depth from 2.51 to 3.50 |  | 2025-10-22 | 2025-12-29 | 2025-12-13 | 2026-02-18 | 0 | 0 | 45623246% | Remaining Total Cost | [17 empty] | 228116.23 | 138211.6 | 89904.63
|  |  | JDH3-02-008-C-03-(ST)- Concrete Box Culvert With Dim (1000x1000) depth from 2.51 to 3.50 |  | 2025-10-22 | 2025-12-29 | 2025-12-13 | 2026-02-18 | 0 | 0 | 45623246% | Actual Total Cost
|  |  | JDH3-02-008-C-03-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2025-10-27 | 2026-01-06 | 2025-12-17 | 2026-02-26 | 0 | 0 | 88862770% | Planned Total Cost | [17 empty] | 333235.39 | 348045.85 | 207346.46
|  |  | JDH3-02-008-C-03-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2025-10-27 | 2026-01-06 | 2025-12-17 | 2026-02-26 | 0 | 0 | 88862770% | Remaining Total Cost | [17 empty] | 333235.39 | 348045.85 | 207346.46
|  |  | JDH3-02-008-C-03-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2025-10-27 | 2026-01-06 | 2025-12-17 | 2026-02-26 | 0 | 0 | 88862770% | Actual Total Cost
|  |  | JDH3-02-008-C-03-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2025-11-01 | 2026-01-11 | 2025-12-22 | 2026-03-03 | 0 | 0 | 92933719% | Planned Total Cost | [17 empty] | 255567.73 | 428527.71 | 144563.56 | 100678.2
|  |  | JDH3-02-008-C-03-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2025-11-01 | 2026-01-11 | 2025-12-22 | 2026-03-03 | 0 | 0 | 92933719% | Remaining Total Cost | [17 empty] | 255567.73 | 428527.71 | 144563.56 | 100678.2
|  |  | JDH3-02-008-C-03-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2025-11-01 | 2026-01-11 | 2025-12-22 | 2026-03-03 | 0 | 0 | 92933719% | Actual Total Cost
|  |  | JDH3-02-008-C-03-(ST)-NetWork |  | 2025-06-02 | 2025-06-17 | 2025-11-11 | 2025-11-26 | 0 | 0 | 49315818% | Planned Total Cost | [16 empty] | 493158.18
|  |  | JDH3-02-008-C-03-(ST)-NetWork |  | 2025-06-02 | 2025-06-17 | 2025-11-11 | 2025-11-26 | 0 | 0 | 49315818% | Remaining Total Cost | [16 empty] | 493158.18
|  |  | JDH3-02-008-C-03-(ST)-NetWork |  | 2025-06-02 | 2025-06-17 | 2025-11-11 | 2025-11-26 | 0 | 0 | 49315818% | Actual Total Cost
|  |  | JDH3-02-008-C-03-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-06-02 | 2025-06-12 | 2025-11-11 | 2025-11-22 | 0 | 0 | 4927595% | Planned Total Cost | [16 empty] | 49275.95
|  |  | JDH3-02-008-C-03-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-06-02 | 2025-06-12 | 2025-11-11 | 2025-11-22 | 0 | 0 | 4927595% | Remaining Total Cost | [16 empty] | 49275.95
|  |  | JDH3-02-008-C-03-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-06-02 | 2025-06-12 | 2025-11-11 | 2025-11-22 | 0 | 0 | 4927595% | Actual Total Cost
|  |  | JDH3-02-008-C-03-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-06-02 | 2025-06-17 | 2025-11-11 | 2025-11-26 | 0 | 0 | 7114200% | Planned Total Cost | [16 empty] | 71142
|  |  | JDH3-02-008-C-03-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-06-02 | 2025-06-17 | 2025-11-11 | 2025-11-26 | 0 | 0 | 7114200% | Remaining Total Cost | [16 empty] | 71142
|  |  | JDH3-02-008-C-03-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-06-02 | 2025-06-17 | 2025-11-11 | 2025-11-26 | 0 | 0 | 7114200% | Actual Total Cost
|  |  | JDH3-02-008-C-03-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-06-02 | 2025-06-17 | 2025-11-11 | 2025-11-26 | 0 | 0 | 12442727% | Planned Total Cost | [16 empty] | 124427.27
|  |  | JDH3-02-008-C-03-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-06-02 | 2025-06-17 | 2025-11-11 | 2025-11-26 | 0 | 0 | 12442727% | Remaining Total Cost | [16 empty] | 124427.27
|  |  | JDH3-02-008-C-03-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-06-02 | 2025-06-17 | 2025-11-11 | 2025-11-26 | 0 | 0 | 12442727% | Actual Total Cost
|  |  | JDH3-02-008-C-03-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-06-02 | 2025-06-12 | 2025-11-11 | 2025-11-22 | 0 | 0 | 4106299% | Planned Total Cost | [16 empty] | 41062.99
|  |  | JDH3-02-008-C-03-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-06-02 | 2025-06-12 | 2025-11-11 | 2025-11-22 | 0 | 0 | 4106299% | Remaining Total Cost | [16 empty] | 41062.99
|  |  | JDH3-02-008-C-03-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-06-02 | 2025-06-12 | 2025-11-11 | 2025-11-22 | 0 | 0 | 4106299% | Actual Total Cost
|  |  | JDH3-02-008-C-03-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-06-02 | 2025-06-12 | 2025-11-11 | 2025-11-22 | 0 | 0 | 11862642% | Planned Total Cost | [16 empty] | 118626.42
|  |  | JDH3-02-008-C-03-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-06-02 | 2025-06-12 | 2025-11-11 | 2025-11-22 | 0 | 0 | 11862642% | Remaining Total Cost | [16 empty] | 118626.42
|  |  | JDH3-02-008-C-03-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-06-02 | 2025-06-12 | 2025-11-11 | 2025-11-22 | 0 | 0 | 11862642% | Actual Total Cost
|  |  | JDH3-02-008-C-03-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-06-02 | 2025-06-12 | 2025-11-11 | 2025-11-22 | 0 | 0 | 3650043% | Planned Total Cost | [16 empty] | 36500.43
|  |  | JDH3-02-008-C-03-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-06-02 | 2025-06-12 | 2025-11-11 | 2025-11-22 | 0 | 0 | 3650043% | Remaining Total Cost | [16 empty] | 36500.43
|  |  | JDH3-02-008-C-03-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-06-02 | 2025-06-12 | 2025-11-11 | 2025-11-22 | 0 | 0 | 3650043% | Actual Total Cost
|  |  | JDH3-02-008-C-03-(ST)- Single Catchbasine Works |  | 2025-06-02 | 2025-06-10 | 2025-11-11 | 2025-11-19 | 0 | 0 | 3128611% | Planned Total Cost | [16 empty] | 31286.11
|  |  | JDH3-02-008-C-03-(ST)- Single Catchbasine Works |  | 2025-06-02 | 2025-06-10 | 2025-11-11 | 2025-11-19 | 0 | 0 | 3128611% | Remaining Total Cost | [16 empty] | 31286.11
|  |  | JDH3-02-008-C-03-(ST)- Single Catchbasine Works |  | 2025-06-02 | 2025-06-10 | 2025-11-11 | 2025-11-19 | 0 | 0 | 3128611% | Actual Total Cost
|  |  | JDH3-02-008-C-03-(ST)-PIPES ENCASEMENT |  | 2025-06-09 | 2025-06-15 | 2025-11-18 | 2025-11-24 | 0 | 0 | 2083700% | Planned Total Cost | [16 empty] | 20837
|  |  | JDH3-02-008-C-03-(ST)-PIPES ENCASEMENT |  | 2025-06-09 | 2025-06-15 | 2025-11-18 | 2025-11-24 | 0 | 0 | 2083700% | Remaining Total Cost | [16 empty] | 20837
|  |  | JDH3-02-008-C-03-(ST)-PIPES ENCASEMENT |  | 2025-06-09 | 2025-06-15 | 2025-11-18 | 2025-11-24 | 0 | 0 | 2083700% | Actual Total Cost
|  |  | JDH3-02-008-C-03-TSE Network - TSE |  | 2025-06-04 | 2025-10-20 | 11-Aug-25 A | 2026-02-10 | 435779.8 | 435779.81 | 120429783% | Planned Total Cost | [11 empty] | 89604.55 | 134798.8 | 257496.31 | 113298.38 |  | 350479.94 | 128697.88 |  | 129921.99
|  |  | JDH3-02-008-C-03-TSE Network - TSE |  | 2025-06-04 | 2025-10-20 | 11-Aug-25 A | 2026-02-10 | 435779.8 | 435779.81 | 120429783% | Remaining Total Cost | [16 empty] | 558686.66 | 79909.37 |  | 129921.99
|  |  | JDH3-02-008-C-03-TSE Network - TSE |  | 2025-06-04 | 2025-10-20 | 11-Aug-25 A | 2026-02-10 | 435779.8 | 435779.81 | 120429783% | Actual Total Cost | [13 empty] | 51639.67 | 369545.52 | 14594.62
|  |  | JDH3-02-008-C-03-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-06-04 | 2025-07-14 | 11-Aug-25 A | 2025-11-12 | 2152-05-06 11:31 | 2152-05-06 11:31 | 11200568% | Planned Total Cost | [11 empty] | 89604.55 | 11200.57 |  |  |  | 11200.57
|  |  | JDH3-02-008-C-03-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-06-04 | 2025-07-14 | 11-Aug-25 A | 2025-11-12 | 2152-05-06 11:31 | 2152-05-06 11:31 | 11200568% | Remaining Total Cost | [16 empty] | 19836.2
|  |  | JDH3-02-008-C-03-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-06-04 | 2025-07-14 | 11-Aug-25 A | 2025-11-12 | 2152-05-06 11:31 | 2152-05-06 11:31 | 11200568% | Actual Total Cost | [13 empty] | 22869.24 | 66416.58 | 2883.66
|  |  | JDH3-02-008-C-03-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-07-15 | 2025-10-20 | 21-Aug-25 A | 2025-12-04 | 343610.33 | 343610.33 | 61799114% | Planned Total Cost | [12 empty] | 123598.23 | 257496.31 | 113298.38 |  | 48788.77 | 74809.45
|  |  | JDH3-02-008-C-03-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-07-15 | 2025-10-20 | 21-Aug-25 A | 2025-12-04 | 343610.33 | 343610.33 | 61799114% | Remaining Total Cost | [16 empty] | 248359.86 | 26020.95
|  |  | JDH3-02-008-C-03-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-07-15 | 2025-10-20 | 21-Aug-25 A | 2025-12-04 | 343610.33 | 343610.33 | 61799114% | Actual Total Cost | [13 empty] | 28770.42 | 303128.94 | 11710.96
|  |  | JDH3-02-008-C-03-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2025-08-02 | 2025-08-12 | 2025-11-13 | 2025-11-24 | 0 | 0 | 8100361% | Planned Total Cost | [16 empty] | 81003.61
|  |  | JDH3-02-008-C-03-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2025-08-02 | 2025-08-12 | 2025-11-13 | 2025-11-24 | 0 | 0 | 8100361% | Remaining Total Cost | [16 empty] | 81003.61
|  |  | JDH3-02-008-C-03-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2025-08-02 | 2025-08-12 | 2025-11-13 | 2025-11-24 | 0 | 0 | 8100361% | Actual Total Cost
|  |  | JDH3-02-008-C-03-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2025-08-04 | 2025-08-14 | 2025-11-16 | 2025-11-26 | 0 | 0 | 467522% | Planned Total Cost | [16 empty] | 4675.22
|  |  | JDH3-02-008-C-03-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2025-08-04 | 2025-08-14 | 2025-11-16 | 2025-11-26 | 0 | 0 | 467522% | Remaining Total Cost | [16 empty] | 4675.22
|  |  | JDH3-02-008-C-03-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2025-08-04 | 2025-08-14 | 2025-11-16 | 2025-11-26 | 0 | 0 | 467522% | Actual Total Cost
|  |  | JDH3-02-008-C-03-(TSE)- Supply and install GRP Pipes - 800 mm depth from 0 to 1.5 m |  | 2025-08-06 | 2025-08-24 | 2025-11-18 | 2025-12-06 | 0 | 0 | 1435516% | Planned Total Cost | [16 empty] | 12919.65 | 1435.52
|  |  | JDH3-02-008-C-03-(TSE)- Supply and install GRP Pipes - 800 mm depth from 0 to 1.5 m |  | 2025-08-06 | 2025-08-24 | 2025-11-18 | 2025-12-06 | 0 | 0 | 1435516% | Remaining Total Cost | [16 empty] | 12919.65 | 1435.52
|  |  | JDH3-02-008-C-03-(TSE)- Supply and install GRP Pipes - 800 mm depth from 0 to 1.5 m |  | 2025-08-06 | 2025-08-24 | 2025-11-18 | 2025-12-06 | 0 | 0 | 1435516% | Actual Total Cost
|  |  | JDH3-02-008-C-03-(TSE)- Supply and install GRP Pipes - 800 mm depth from 1.51 to 2.5 m |  | 2025-08-09 | 2025-08-24 | 2025-11-20 | 2025-12-06 | 0 | 0 | 6155205% | Planned Total Cost | [16 empty] | 55396.84 | 6155.2
|  |  | JDH3-02-008-C-03-(TSE)- Supply and install GRP Pipes - 800 mm depth from 1.51 to 2.5 m |  | 2025-08-09 | 2025-08-24 | 2025-11-20 | 2025-12-06 | 0 | 0 | 6155205% | Remaining Total Cost | [16 empty] | 55396.84 | 6155.2
|  |  | JDH3-02-008-C-03-(TSE)- Supply and install GRP Pipes - 800 mm depth from 1.51 to 2.5 m |  | 2025-08-09 | 2025-08-24 | 2025-11-20 | 2025-12-06 | 0 | 0 | 6155205% | Actual Total Cost
|  |  | JDH3-02-008-C-03-(TSE)- Supply and install GRP Pipes - 800 mm depth from 2.51 to 3.5 m |  | 2025-08-11 | 2025-08-24 | 2025-11-23 | 2025-12-06 | 0 | 0 | 455931% | Planned Total Cost | [16 empty] | 3875.41 | 683.9
|  |  | JDH3-02-008-C-03-(TSE)- Supply and install GRP Pipes - 800 mm depth from 2.51 to 3.5 m |  | 2025-08-11 | 2025-08-24 | 2025-11-23 | 2025-12-06 | 0 | 0 | 455931% | Remaining Total Cost | [16 empty] | 3875.41 | 683.9
|  |  | JDH3-02-008-C-03-(TSE)- Supply and install GRP Pipes - 800 mm depth from 2.51 to 3.5 m |  | 2025-08-11 | 2025-08-24 | 2025-11-23 | 2025-12-06 | 0 | 0 | 455931% | Actual Total Cost
|  |  | JDH3-02-008-C-03-(TSE)-Supply and install gate valves-100 mm |  | 2025-08-11 | 2025-08-21 | 2025-11-23 | 2025-12-03 | 0 | 0 | 2327689% | Planned Total Cost | [16 empty] | 21880.27 | 1396.61
|  |  | JDH3-02-008-C-03-(TSE)-Supply and install gate valves-100 mm |  | 2025-08-11 | 2025-08-21 | 2025-11-23 | 2025-12-03 | 0 | 0 | 2327689% | Remaining Total Cost | [16 empty] | 21880.27 | 1396.61
|  |  | JDH3-02-008-C-03-(TSE)-Supply and install gate valves-100 mm |  | 2025-08-11 | 2025-08-21 | 2025-11-23 | 2025-12-03 | 0 | 0 | 2327689% | Actual Total Cost
|  |  | JDH3-02-008-C-03-(TSE)-Supply and install gate valves-250 mm |  | 2025-08-11 | 2025-08-17 | 2025-11-23 | 2025-11-29 | 0 | 0 | 2566113% | Planned Total Cost | [16 empty] | 25661.13
|  |  | JDH3-02-008-C-03-(TSE)-Supply and install gate valves-250 mm |  | 2025-08-11 | 2025-08-17 | 2025-11-23 | 2025-11-29 | 0 | 0 | 2566113% | Remaining Total Cost | [16 empty] | 25661.13
|  |  | JDH3-02-008-C-03-(TSE)-Supply and install gate valves-250 mm |  | 2025-08-11 | 2025-08-17 | 2025-11-23 | 2025-11-29 | 0 | 0 | 2566113% | Actual Total Cost
|  |  | JDH3-02-008-C-03-(TSE)-Supply and install of butterfly valves-800 mm. |  | 2025-08-11 | 2025-08-14 | 2026-02-07 | 2026-02-10 | 0 | 0 | 12992199% | Planned Total Cost | [19 empty] | 129921.99
|  |  | JDH3-02-008-C-03-(TSE)-Supply and install of butterfly valves-800 mm. |  | 2025-08-11 | 2025-08-14 | 2026-02-07 | 2026-02-10 | 0 | 0 | 12992199% | Remaining Total Cost | [19 empty] | 129921.99
|  |  | JDH3-02-008-C-03-(TSE)-Supply and install of butterfly valves-800 mm. |  | 2025-08-11 | 2025-08-14 | 2026-02-07 | 2026-02-10 | 0 | 0 | 12992199% | Actual Total Cost
|  |  | JDH3-02-008-C-03-(TSE)-Supply and install of Wash-out valves-200 mm. |  | 2025-08-11 | 2025-08-14 | 2025-11-23 | 2025-11-26 | 0 | 0 | 2427539% | Planned Total Cost | [16 empty] | 24275.39
|  |  | JDH3-02-008-C-03-(TSE)-Supply and install of Wash-out valves-200 mm. |  | 2025-08-11 | 2025-08-14 | 2025-11-23 | 2025-11-26 | 0 | 0 | 2427539% | Remaining Total Cost | [16 empty] | 24275.39
|  |  | JDH3-02-008-C-03-(TSE)-Supply and install of Wash-out valves-200 mm. |  | 2025-08-11 | 2025-08-14 | 2025-11-23 | 2025-11-26 | 0 | 0 | 2427539% | Actual Total Cost
|  |  | JDH3-02-008-C-03-(TSE)-Supply and install of Air valves-50 mm. |  | 2025-08-11 | 2025-08-14 | 2025-11-23 | 2025-11-26 | 0 | 0 | 2977654% | Planned Total Cost | [16 empty] | 29776.54
|  |  | JDH3-02-008-C-03-(TSE)-Supply and install of Air valves-50 mm. |  | 2025-08-11 | 2025-08-14 | 2025-11-23 | 2025-11-26 | 0 | 0 | 2977654% | Remaining Total Cost | [16 empty] | 29776.54
|  |  | JDH3-02-008-C-03-(TSE)-Supply and install of Air valves-50 mm. |  | 2025-08-11 | 2025-08-14 | 2025-11-23 | 2025-11-26 | 0 | 0 | 2977654% | Actual Total Cost
|  |  | JDH3-02-008-C-03-(TSE)- Supply and Construct R.C Valves Chamber on 700-1000 mm Diameter pipelines |  | 2025-08-13 | 2025-08-24 | 2025-11-25 | 2025-12-06 | 0 | 0 | 4086615% | Planned Total Cost | [16 empty] | 24519.69 | 16346.46
|  |  | JDH3-02-008-C-03-(TSE)- Supply and Construct R.C Valves Chamber on 700-1000 mm Diameter pipelines |  | 2025-08-13 | 2025-08-24 | 2025-11-25 | 2025-12-06 | 0 | 0 | 4086615% | Remaining Total Cost | [16 empty] | 24519.69 | 16346.46
|  |  | JDH3-02-008-C-03-(TSE)- Supply and Construct R.C Valves Chamber on 700-1000 mm Diameter pipelines |  | 2025-08-13 | 2025-08-24 | 2025-11-25 | 2025-12-06 | 0 | 0 | 4086615% | Actual Total Cost
|  |  | JDH3-02-008-C-03-(TSE)- Supply and Construct Wash-out Valves Chamber on 700-1200 mm Diameter pipelin |  | 2025-08-16 | 2025-08-24 | 2025-11-27 | 2025-12-06 | 0 | 0 | 2046045% | Planned Total Cost | [16 empty] | 5115.11 | 15345.34
|  |  | JDH3-02-008-C-03-(TSE)- Supply and Construct Wash-out Valves Chamber on 700-1200 mm Diameter pipelin |  | 2025-08-16 | 2025-08-24 | 2025-11-27 | 2025-12-06 | 0 | 0 | 2046045% | Remaining Total Cost | [16 empty] | 5115.11 | 15345.34
|  |  | JDH3-02-008-C-03-(TSE)- Supply and Construct Wash-out Valves Chamber on 700-1200 mm Diameter pipelin |  | 2025-08-16 | 2025-08-24 | 2025-11-27 | 2025-12-06 | 0 | 0 | 2046045% | Actual Total Cost
|  |  | JDH3-02-008-C-03-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2025-08-18 | 2025-08-26 | 2025-11-30 | 2025-12-08 | 0 | 0 | 1391711% | Planned Total Cost | [16 empty] | 1391.71 | 12525.4
|  |  | JDH3-02-008-C-03-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2025-08-18 | 2025-08-26 | 2025-11-30 | 2025-12-08 | 0 | 0 | 1391711% | Remaining Total Cost | [16 empty] | 1391.71 | 12525.4
|  |  | JDH3-02-008-C-03-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2025-08-18 | 2025-08-26 | 2025-11-30 | 2025-12-08 | 0 | 0 | 1391711% | Actual Total Cost
|  |  | JDH3-02-008-C-03-Street Lighting Network -SL |  | 2025-10-21 | 2025-10-22 | 2026-02-07 | 2026-02-08 | 0 | 0 | 37804% | Planned Total Cost | [19 empty] | 378.04
|  |  | JDH3-02-008-C-03-Street Lighting Network -SL |  | 2025-10-21 | 2025-10-22 | 2026-02-07 | 2026-02-08 | 0 | 0 | 37804% | Remaining Total Cost | [19 empty] | 378.04
|  |  | JDH3-02-008-C-03-Street Lighting Network -SL |  | 2025-10-21 | 2025-10-22 | 2026-02-07 | 2026-02-08 | 0 | 0 | 37804% | Actual Total Cost
|  |  | JDH3-02-008-C-03-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2025-10-21 | 2025-10-22 | 2026-02-07 | 2026-02-08 | 0 | 0 | 37804% | Planned Total Cost | [19 empty] | 378.04
|  |  | JDH3-02-008-C-03-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2025-10-21 | 2025-10-22 | 2026-02-07 | 2026-02-08 | 0 | 0 | 37804% | Remaining Total Cost | [19 empty] | 378.04
|  |  | JDH3-02-008-C-03-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2025-10-21 | 2025-10-22 | 2026-02-07 | 2026-02-08 | 0 | 0 | 37804% | Actual Total Cost
|  |  | C-05 |  | 2025-08-27 | 2025-12-25 | 04-Dec-24 A | 2026-04-13 | 530040.28 | 530040.28 | 347522068% | Planned Total Cost | [14 empty] | 389958.62 | 652502.81 | 92672.41 | 236903.15 | 907113.17 | 358348.27 | 629493.14 | 208229.11
|  |  | C-05 |  | 2025-08-27 | 2025-12-25 | 04-Dec-24 A | 2026-04-13 | 530040.28 | 530040.28 | 347522068% | Remaining Total Cost | [15 empty] | 771178.29 | 70818.43 |  | 907113.17 | 358348.27 | 629493.14 | 208229.11
|  |  | C-05 |  | 2025-08-27 | 2025-12-25 | 04-Dec-24 A | 2026-04-13 | 530040.28 | 530040.28 | 347522068% | Actual Total Cost | [5 empty] | 6063518% | 88245.31 | 50641.88 | 28510.77 | 26021.05 | 64456.09 | 64456.09 | 45681.72 | 36826.6 | 63149.18 | 1416.41
|  |  | JDH3-02-008-C-05-Storm Network - ST |  | 2025-09-04 | 2025-11-25 | 10-Apr-25 A | 2026-03-26 | 266814.55 | 266814.55 | 267548956% | Planned Total Cost | [14 empty] | 363636.05 | 652502.81 | 92672.41 |  | 907113.17 | 358348.27 | 301216.86
|  |  | JDH3-02-008-C-05-Storm Network - ST |  | 2025-09-04 | 2025-11-25 | 10-Apr-25 A | 2026-03-26 | 266814.55 | 266814.55 | 267548956% | Remaining Total Cost | [15 empty] | 771178.29 | 70818.43 |  | 907113.17 | 358348.27 | 301216.86
|  |  | JDH3-02-008-C-05-Storm Network - ST |  | 2025-09-04 | 2025-11-25 | 10-Apr-25 A | 2026-03-26 | 266814.55 | 266814.55 | 267548956% | Actual Total Cost | [9 empty] | 17151.03 | 64456.09 | 64456.09 | 45681.72 | 36826.6 | 36826.6 | 1416.41
|  |  | JDH3-02-008-C-05-(ST)-Swales |  | 2025-09-04 | 2025-11-25 | 10-Apr-25 A | 2025-11-08 | 266814.55 | 266814.55 | 110881126% | Planned Total Cost | [14 empty] | 363636.05 | 652502.81 | 92672.41
|  |  | JDH3-02-008-C-05-(ST)-Swales |  | 2025-09-04 | 2025-11-25 | 10-Apr-25 A | 2025-11-08 | 266814.55 | 266814.55 | 110881126% | Remaining Total Cost | [15 empty] | 771178.29 | 70818.43
|  |  | JDH3-02-008-C-05-(ST)-Swales |  | 2025-09-04 | 2025-11-25 | 10-Apr-25 A | 2025-11-08 | 266814.55 | 266814.55 | 110881126% | Actual Total Cost | [9 empty] | 17151.03 | 64456.09 | 64456.09 | 45681.72 | 36826.6 | 36826.6 | 1416.41
|  |  | JDH3-02-008-C-05-(ST)-Box Culvert |  | 2025-09-04 | 2025-11-10 | 2026-01-04 | 2026-03-12 | 0 | 0 | 145131084% | Planned Total Cost | [18 empty] | 907113.17 | 358348.27 | 185849.4
|  |  | JDH3-02-008-C-05-(ST)-Box Culvert |  | 2025-09-04 | 2025-11-10 | 2026-01-04 | 2026-03-12 | 0 | 0 | 145131084% | Remaining Total Cost | [18 empty] | 907113.17 | 358348.27 | 185849.4
|  |  | JDH3-02-008-C-05-(ST)-Box Culvert |  | 2025-09-04 | 2025-11-10 | 2026-01-04 | 2026-03-12 | 0 | 0 | 145131084% | Actual Total Cost
|  |  | JDH3-02-008-C-05-(ST)- Concrete Box Culvert With Dim (1000x1000) depth from 2.51 to 3.50 |  | 2025-09-04 | 2025-10-01 | 2026-01-04 | 2026-02-01 | 0 | 0 | 15922207% | Planned Total Cost | [18 empty] | 156037.62 | 3184.44
|  |  | JDH3-02-008-C-05-(ST)- Concrete Box Culvert With Dim (1000x1000) depth from 2.51 to 3.50 |  | 2025-09-04 | 2025-10-01 | 2026-01-04 | 2026-02-01 | 0 | 0 | 15922207% | Remaining Total Cost | [18 empty] | 156037.62 | 3184.44
|  |  | JDH3-02-008-C-05-(ST)- Concrete Box Culvert With Dim (1000x1000) depth from 2.51 to 3.50 |  | 2025-09-04 | 2025-10-01 | 2026-01-04 | 2026-02-01 | 0 | 0 | 15922207% | Actual Total Cost
|  |  | JDH3-02-008-C-05-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2025-09-07 | 2025-11-05 | 2026-01-06 | 2026-03-08 | 0 | 0 | 57385562% | Planned Total Cost | [18 empty] | 350051.93 | 141168.48 | 82635.21
|  |  | JDH3-02-008-C-05-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2025-09-07 | 2025-11-05 | 2026-01-06 | 2026-03-08 | 0 | 0 | 57385562% | Remaining Total Cost | [18 empty] | 350051.93 | 141168.48 | 82635.21
|  |  | JDH3-02-008-C-05-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2025-09-07 | 2025-11-05 | 2026-01-06 | 2026-03-08 | 0 | 0 | 57385562% | Actual Total Cost
|  |  | JDH3-02-008-C-05-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2025-09-10 | 2025-11-10 | 2026-01-10 | 2026-03-12 | 0 | 0 | 59776561% | Planned Total Cost | [18 empty] | 334748.74 | 159802.67 | 103214.2
|  |  | JDH3-02-008-C-05-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2025-09-10 | 2025-11-10 | 2026-01-10 | 2026-03-12 | 0 | 0 | 59776561% | Remaining Total Cost | [18 empty] | 334748.74 | 159802.67 | 103214.2
|  |  | JDH3-02-008-C-05-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2025-09-10 | 2025-11-10 | 2026-01-10 | 2026-03-12 | 0 | 0 | 59776561% | Actual Total Cost
|  |  | JDH3-02-008-C-05-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2025-09-14 | 2025-09-29 | 2026-01-13 | 2026-01-29 | 0 | 0 | 5888497% | Planned Total Cost | [18 empty] | 58884.97
|  |  | JDH3-02-008-C-05-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2025-09-14 | 2025-09-29 | 2026-01-13 | 2026-01-29 | 0 | 0 | 5888497% | Remaining Total Cost | [18 empty] | 58884.97
|  |  | JDH3-02-008-C-05-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2025-09-14 | 2025-09-29 | 2026-01-13 | 2026-01-29 | 0 | 0 | 5888497% | Actual Total Cost
|  |  | JDH3-02-008-C-05-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2025-09-30 | 2025-10-15 | 2026-01-29 | 2026-02-15 | 0 | 0 | 6158259% | Planned Total Cost | [18 empty] | 7389.91 | 54192.67
|  |  | JDH3-02-008-C-05-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2025-09-30 | 2025-10-15 | 2026-01-29 | 2026-02-15 | 0 | 0 | 6158259% | Remaining Total Cost | [18 empty] | 7389.91 | 54192.67
|  |  | JDH3-02-008-C-05-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2025-09-30 | 2025-10-15 | 2026-01-29 | 2026-02-15 | 0 | 0 | 6158259% | Actual Total Cost
|  |  | JDH3-02-008-C-05-(ST)-NetWork |  | 2025-11-11 | 2025-11-24 | 2026-03-12 | 2026-03-26 | 0 | 0 | 11536745% | Planned Total Cost | [20 empty] | 115367.45
|  |  | JDH3-02-008-C-05-(ST)-NetWork |  | 2025-11-11 | 2025-11-24 | 2026-03-12 | 2026-03-26 | 0 | 0 | 11536745% | Remaining Total Cost | [20 empty] | 115367.45
|  |  | JDH3-02-008-C-05-(ST)-NetWork |  | 2025-11-11 | 2025-11-24 | 2026-03-12 | 2026-03-26 | 0 | 0 | 11536745% | Actual Total Cost
|  |  | JDH3-02-008-C-05-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-11-11 | 2025-11-22 | 2026-03-12 | 2026-03-24 | 0 | 0 | 1368766% | Planned Total Cost | [20 empty] | 13687.66
|  |  | JDH3-02-008-C-05-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-11-11 | 2025-11-22 | 2026-03-12 | 2026-03-24 | 0 | 0 | 1368766% | Remaining Total Cost | [20 empty] | 13687.66
|  |  | JDH3-02-008-C-05-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-11-11 | 2025-11-22 | 2026-03-12 | 2026-03-24 | 0 | 0 | 1368766% | Actual Total Cost
|  |  | JDH3-02-008-C-05-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-11-13 | 2025-11-24 | 2026-03-15 | 2026-03-26 | 0 | 0 | 10167979% | Planned Total Cost | [20 empty] | 101679.79
|  |  | JDH3-02-008-C-05-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-11-13 | 2025-11-24 | 2026-03-15 | 2026-03-26 | 0 | 0 | 10167979% | Remaining Total Cost | [20 empty] | 101679.79
|  |  | JDH3-02-008-C-05-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-11-13 | 2025-11-24 | 2026-03-15 | 2026-03-26 | 0 | 0 | 10167979% | Actual Total Cost
|  |  | JDH3-02-008-C-05-TSE Network - TSE |  | 2025-11-26 | 2025-12-25 | 04-Dec-24 A | 2026-04-13 | 263225.72 | 263225.73 | 79973112% | Planned Total Cost | [14 empty] | 26322.58 |  |  | 236903.15 |  |  | 328276.28 | 208229.11
|  |  | JDH3-02-008-C-05-TSE Network - TSE |  | 2025-11-26 | 2025-12-25 | 04-Dec-24 A | 2026-04-13 | 263225.72 | 263225.73 | 79973112% | Remaining Total Cost | [20 empty] | 328276.28 | 208229.11
|  |  | JDH3-02-008-C-05-TSE Network - TSE |  | 2025-11-26 | 2025-12-25 | 04-Dec-24 A | 2026-04-13 | 263225.72 | 263225.73 | 79973112% | Actual Total Cost | [5 empty] | 6063518% | 88245.31 | 50641.88 | 28510.77 | 8870.02 |  |  |  |  | 26322.58
|  |  | JDH3-02-008-C-05-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-11-26 | 2025-12-21 | 2026-03-12 | 2026-04-09 | 0 | 0 | 1202090% | Planned Total Cost | [20 empty] | 10818.81 | 1202.09
|  |  | JDH3-02-008-C-05-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-11-26 | 2025-12-21 | 2026-03-12 | 2026-04-09 | 0 | 0 | 1202090% | Remaining Total Cost | [20 empty] | 10818.81 | 1202.09
|  |  | JDH3-02-008-C-05-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-11-26 | 2025-12-21 | 2026-03-12 | 2026-04-09 | 0 | 0 | 1202090% | Actual Total Cost
|  |  | JDH3-02-008-C-05-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2025-11-26 | 2025-12-25 | 2026-03-12 | 2026-04-13 | 0 | 0 | 34018086% | Planned Total Cost | [20 empty] | 276226.86 | 63954
|  |  | JDH3-02-008-C-05-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2025-11-26 | 2025-12-25 | 2026-03-12 | 2026-04-13 | 0 | 0 | 34018086% | Remaining Total Cost | [20 empty] | 276226.86 | 63954
|  |  | JDH3-02-008-C-05-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2025-11-26 | 2025-12-25 | 2026-03-12 | 2026-04-13 | 0 | 0 | 34018086% | Actual Total Cost
|  |  | JDH3-02-008-C-05-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2025-12-01 | 2025-12-13 | 10-Dec-24 A | 18-Sep-25 A | 2232-02-13 11:17 | 2232-02-13 11:17 | 12130547% | Planned Total Cost | [14 empty] | 12130.55 |  |  | 109174.92
|  |  | JDH3-02-008-C-05-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2025-12-01 | 2025-12-13 | 10-Dec-24 A | 18-Sep-25 A | 2232-02-13 11:17 | 2232-02-13 11:17 | 12130547% | Remaining Total Cost
|  |  | JDH3-02-008-C-05-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2025-12-01 | 2025-12-13 | 10-Dec-24 A | 18-Sep-25 A | 2232-02-13 11:17 | 2232-02-13 11:17 | 12130547% | Actual Total Cost | [5 empty] | 3831230% | 50695.58 | 20167.04 | [6 empty] | 12130.55
|  |  | JDH3-02-008-C-05-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 2.51 to 3.5 m |  | 2025-12-03 | 2025-12-18 | 04-Dec-24 A | 18-Sep-25 A | 2288-07-23 06:00 | 2288-07-23 06:14 | 14192025% | Planned Total Cost | [14 empty] | 14192.03 |  |  | 127728.23
|  |  | JDH3-02-008-C-05-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 2.51 to 3.5 m |  | 2025-12-03 | 2025-12-18 | 04-Dec-24 A | 18-Sep-25 A | 2288-07-23 06:00 | 2288-07-23 06:14 | 14192025% | Remaining Total Cost
|  |  | JDH3-02-008-C-05-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 2.51 to 3.5 m |  | 2025-12-03 | 2025-12-18 | 04-Dec-24 A | 18-Sep-25 A | 2288-07-23 06:00 | 2288-07-23 06:14 | 14192025% | Actual Total Cost | [5 empty] | 2232287% | 37549.73 | 30474.84 | 28510.77 | 8870.02 |  |  |  |  | 14192.03
|  |  | JDH3-02-008-C-05-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 2.51 to 3.5 m |  | 2025-12-06 | 2025-12-22 | 2026-03-26 | 2026-04-09 | 0 | 0 | 3068958% | Planned Total Cost | [20 empty] | 12736.17 | 17953.4
|  |  | JDH3-02-008-C-05-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 2.51 to 3.5 m |  | 2025-12-06 | 2025-12-22 | 2026-03-26 | 2026-04-09 | 0 | 0 | 3068958% | Remaining Total Cost | [20 empty] | 12736.17 | 17953.4
|  |  | JDH3-02-008-C-05-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 2.51 to 3.5 m |  | 2025-12-06 | 2025-12-22 | 2026-03-26 | 2026-04-09 | 0 | 0 | 3068958% | Actual Total Cost
|  |  | JDH3-02-008-C-05-(TSE)-Supply and install gate valves-100 mm |  | 2025-12-15 | 2025-12-18 | 2026-04-02 | 2026-04-07 | 0 | 0 | 775896% | Planned Total Cost | [21 empty] | 7758.96
|  |  | JDH3-02-008-C-05-(TSE)-Supply and install gate valves-100 mm |  | 2025-12-15 | 2025-12-18 | 2026-04-02 | 2026-04-07 | 0 | 0 | 775896% | Remaining Total Cost | [21 empty] | 7758.96
|  |  | JDH3-02-008-C-05-(TSE)-Supply and install gate valves-100 mm |  | 2025-12-15 | 2025-12-18 | 2026-04-02 | 2026-04-07 | 0 | 0 | 775896% | Actual Total Cost
|  |  | JDH3-02-008-C-05-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2025-12-15 | 2025-12-18 | 2026-04-02 | 2026-04-07 | 0 | 0 | 7669979% | Planned Total Cost | [21 empty] | 76699.79
|  |  | JDH3-02-008-C-05-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2025-12-15 | 2025-12-18 | 2026-04-02 | 2026-04-07 | 0 | 0 | 7669979% | Remaining Total Cost | [21 empty] | 76699.79
|  |  | JDH3-02-008-C-05-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2025-12-15 | 2025-12-18 | 2026-04-02 | 2026-04-07 | 0 | 0 | 7669979% | Actual Total Cost
|  |  | JDH3-02-008-C-05-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2025-12-15 | 2025-12-18 | 2026-04-02 | 2026-04-07 | 0 | 0 | 979190% | Planned Total Cost | [21 empty] | 9791.9
|  |  | JDH3-02-008-C-05-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2025-12-15 | 2025-12-18 | 2026-04-02 | 2026-04-07 | 0 | 0 | 979190% | Remaining Total Cost | [21 empty] | 9791.9
|  |  | JDH3-02-008-C-05-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2025-12-15 | 2025-12-18 | 2026-04-02 | 2026-04-07 | 0 | 0 | 979190% | Actual Total Cost
|  |  | JDH3-02-008-C-05-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2025-11-26 | 2025-12-04 | 2026-03-26 | 2026-04-05 | 0 | 0 | 4551149% | Planned Total Cost | [20 empty] | 21845.52 | 23665.98
|  |  | JDH3-02-008-C-05-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2025-11-26 | 2025-12-04 | 2026-03-26 | 2026-04-05 | 0 | 0 | 4551149% | Remaining Total Cost | [20 empty] | 21845.52 | 23665.98
|  |  | JDH3-02-008-C-05-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2025-11-26 | 2025-12-04 | 2026-03-26 | 2026-04-05 | 0 | 0 | 4551149% | Actual Total Cost
|  |  | JDH3-02-008-C-05-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2025-11-26 | 2025-12-04 | 2026-03-26 | 2026-04-05 | 0 | 0 | 1385192% | Planned Total Cost | [20 empty] | 6648.92 | 7203
|  |  | JDH3-02-008-C-05-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2025-11-26 | 2025-12-04 | 2026-03-26 | 2026-04-05 | 0 | 0 | 1385192% | Remaining Total Cost | [20 empty] | 6648.92 | 7203
|  |  | JDH3-02-008-C-05-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2025-11-26 | 2025-12-04 | 2026-03-26 | 2026-04-05 | 0 | 0 | 1385192% | Actual Total Cost
|  |  | C-06 |  | 2025-12-27 | 2026-04-04 | 01-Jul-25 A | 2026-04-20 | 327791.63 | 327791.63 | 221491710% | Planned Total Cost | [15 empty] | 801793.95 | 486054.48 | 85615.77 |  |  | 553793.4 | 287659.5
|  |  | C-06 |  | 2025-12-27 | 2026-04-04 | 01-Jul-25 A | 2026-04-20 | 327791.63 | 327791.63 | 221491710% | Remaining Total Cost | [15 empty] | 801793.95 | 486054.48 | 85615.77 |  |  | 237593.4 | 276067.87
|  |  | C-06 |  | 2025-12-27 | 2026-04-04 | 01-Jul-25 A | 2026-04-20 | 327791.63 | 327791.63 | 221491710% | Actual Total Cost | [13 empty] | 106430.72 | 212737.44 | 8623.47
|  |  | JDH3-02-008-C-06-Sewage Network - SS |  | 2026-01-04 | 2026-02-19 | 2025-10-02 | 2025-11-18 | 0 | 0 | 101644110% | Planned Total Cost | [15 empty] | 801793.95 | 214647.14
|  |  | JDH3-02-008-C-06-Sewage Network - SS |  | 2026-01-04 | 2026-02-19 | 2025-10-02 | 2025-11-18 | 0 | 0 | 101644110% | Remaining Total Cost | [15 empty] | 801793.95 | 214647.14
|  |  | JDH3-02-008-C-06-Sewage Network - SS |  | 2026-01-04 | 2026-02-19 | 2025-10-02 | 2025-11-18 | 0 | 0 | 101644110% | Actual Total Cost
|  |  | JDH3-02-008-C-06-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2026-01-04 | 2026-01-14 | 2025-10-02 | 2025-10-13 | 0 | 0 | 925772% | Planned Total Cost | [15 empty] | 9257.72
|  |  | JDH3-02-008-C-06-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2026-01-04 | 2026-01-14 | 2025-10-02 | 2025-10-13 | 0 | 0 | 925772% | Remaining Total Cost | [15 empty] | 9257.72
|  |  | JDH3-02-008-C-06-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2026-01-04 | 2026-01-14 | 2025-10-02 | 2025-10-13 | 0 | 0 | 925772% | Actual Total Cost
|  |  | JDH3-02-008-C-06-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 3.51 to 4.5 m. |  | 2026-01-06 | 2026-02-19 | 2025-10-05 | 2025-11-18 | 0 | 0 | 80903811% | Planned Total Cost | [15 empty] | 658788.17 | 150249.93
|  |  | JDH3-02-008-C-06-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 3.51 to 4.5 m. |  | 2026-01-06 | 2026-02-19 | 2025-10-05 | 2025-11-18 | 0 | 0 | 80903811% | Remaining Total Cost | [15 empty] | 658788.17 | 150249.93
|  |  | JDH3-02-008-C-06-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 3.51 to 4.5 m. |  | 2026-01-06 | 2026-02-19 | 2025-10-05 | 2025-11-18 | 0 | 0 | 80903811% | Actual Total Cost
|  |  | JDH3-02-008-C-06-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2026-01-14 | 2026-02-15 | 2025-10-13 | 2025-11-13 | 0 | 0 | 19814526% | Planned Total Cost | [15 empty] | 133748.05 | 64397.21
|  |  | JDH3-02-008-C-06-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2026-01-14 | 2026-02-15 | 2025-10-13 | 2025-11-13 | 0 | 0 | 19814526% | Remaining Total Cost | [15 empty] | 133748.05 | 64397.21
|  |  | JDH3-02-008-C-06-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2026-01-14 | 2026-02-15 | 2025-10-13 | 2025-11-13 | 0 | 0 | 19814526% | Actual Total Cost
|  |  | JDH3-02-008-C-06-Storm Network - ST |  | 2026-01-04 | 2026-03-03 | 2025-11-08 | 2026-04-02 | 0 | 0 | 60343401% | Planned Total Cost | [16 empty] | 271407.34 | 85615.77 |  |  | 237593.4 | 8817.51
|  |  | JDH3-02-008-C-06-Storm Network - ST |  | 2026-01-04 | 2026-03-03 | 2025-11-08 | 2026-04-02 | 0 | 0 | 60343401% | Remaining Total Cost | [16 empty] | 271407.34 | 85615.77 |  |  | 237593.4 | 8817.51
|  |  | JDH3-02-008-C-06-Storm Network - ST |  | 2026-01-04 | 2026-03-03 | 2025-11-08 | 2026-04-02 | 0 | 0 | 60343401% | Actual Total Cost
|  |  | JDH3-02-008-C-06-(ST)-Swales |  | 2026-01-04 | 2026-02-05 | 2025-11-08 | 2025-12-11 | 0 | 0 | 20135726% | Planned Total Cost | [16 empty] | 115741.5 | 85615.77
|  |  | JDH3-02-008-C-06-(ST)-Swales |  | 2026-01-04 | 2026-02-05 | 2025-11-08 | 2025-12-11 | 0 | 0 | 20135726% | Remaining Total Cost | [16 empty] | 115741.5 | 85615.77
|  |  | JDH3-02-008-C-06-(ST)-Swales |  | 2026-01-04 | 2026-02-05 | 2025-11-08 | 2025-12-11 | 0 | 0 | 20135726% | Actual Total Cost
|  |  | JDH3-02-008-C-06-(ST)-Box Culvert |  | 2026-02-07 | 2026-02-26 | 2026-03-12 | 2026-04-02 | 0 | 0 | 24641090% | Planned Total Cost | [20 empty] | 237593.4 | 8817.51
|  |  | JDH3-02-008-C-06-(ST)-Box Culvert |  | 2026-02-07 | 2026-02-26 | 2026-03-12 | 2026-04-02 | 0 | 0 | 24641090% | Remaining Total Cost | [20 empty] | 237593.4 | 8817.51
|  |  | JDH3-02-008-C-06-(ST)-Box Culvert |  | 2026-02-07 | 2026-02-26 | 2026-03-12 | 2026-04-02 | 0 | 0 | 24641090% | Actual Total Cost
|  |  | JDH3-02-008-C-06-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2026-02-07 | 2026-02-24 | 2026-03-12 | 2026-03-31 | 0 | 0 | 12044653% | Planned Total Cost | [20 empty] | 120446.53
|  |  | JDH3-02-008-C-06-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2026-02-07 | 2026-02-24 | 2026-03-12 | 2026-03-31 | 0 | 0 | 12044653% | Remaining Total Cost | [20 empty] | 120446.53
|  |  | JDH3-02-008-C-06-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2026-02-07 | 2026-02-24 | 2026-03-12 | 2026-03-31 | 0 | 0 | 12044653% | Actual Total Cost
|  |  | JDH3-02-008-C-06-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2026-02-09 | 2026-02-26 | 2026-03-15 | 2026-04-02 | 0 | 0 | 12596438% | Planned Total Cost | [20 empty] | 117146.87 | 8817.51
|  |  | JDH3-02-008-C-06-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2026-02-09 | 2026-02-26 | 2026-03-15 | 2026-04-02 | 0 | 0 | 12596438% | Remaining Total Cost | [20 empty] | 117146.87 | 8817.51
|  |  | JDH3-02-008-C-06-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2026-02-09 | 2026-02-26 | 2026-03-15 | 2026-04-02 | 0 | 0 | 12596438% | Actual Total Cost
|  |  | JDH3-02-008-C-06-(ST)-NetWork |  | 2026-02-21 | 2026-03-03 | 2025-11-19 | 2025-11-30 | 0 | 0 | 15566584% | Planned Total Cost | [16 empty] | 155665.84
|  |  | JDH3-02-008-C-06-(ST)-NetWork |  | 2026-02-21 | 2026-03-03 | 2025-11-19 | 2025-11-30 | 0 | 0 | 15566584% | Remaining Total Cost | [16 empty] | 155665.84
|  |  | JDH3-02-008-C-06-(ST)-NetWork |  | 2026-02-21 | 2026-03-03 | 2025-11-19 | 2025-11-30 | 0 | 0 | 15566584% | Actual Total Cost
|  |  | JDH3-02-008-C-06-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-02-21 | 2026-03-03 | 2025-11-19 | 2025-11-30 | 0 | 0 | 6159494% | Planned Total Cost | [16 empty] | 61594.94
|  |  | JDH3-02-008-C-06-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-02-21 | 2026-03-03 | 2025-11-19 | 2025-11-30 | 0 | 0 | 6159494% | Remaining Total Cost | [16 empty] | 61594.94
|  |  | JDH3-02-008-C-06-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-02-21 | 2026-03-03 | 2025-11-19 | 2025-11-30 | 0 | 0 | 6159494% | Actual Total Cost
|  |  | JDH3-02-008-C-06-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-02-21 | 2026-03-03 | 2025-11-19 | 2025-11-30 | 0 | 0 | 3161867% | Planned Total Cost | [16 empty] | 31618.67
|  |  | JDH3-02-008-C-06-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-02-21 | 2026-03-03 | 2025-11-19 | 2025-11-30 | 0 | 0 | 3161867% | Remaining Total Cost | [16 empty] | 31618.67
|  |  | JDH3-02-008-C-06-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-02-21 | 2026-03-03 | 2025-11-19 | 2025-11-30 | 0 | 0 | 3161867% | Actual Total Cost
|  |  | JDH3-02-008-C-06-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-02-21 | 2026-03-03 | 2025-11-19 | 2025-11-30 | 0 | 0 | 2986255% | Planned Total Cost | [16 empty] | 29862.55
|  |  | JDH3-02-008-C-06-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-02-21 | 2026-03-03 | 2025-11-19 | 2025-11-30 | 0 | 0 | 2986255% | Remaining Total Cost | [16 empty] | 29862.55
|  |  | JDH3-02-008-C-06-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-02-21 | 2026-03-03 | 2025-11-19 | 2025-11-30 | 0 | 0 | 2986255% | Actual Total Cost
|  |  | JDH3-02-008-C-06-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-02-21 | 2026-03-03 | 2025-11-19 | 2025-11-30 | 0 | 0 | 1694663% | Planned Total Cost | [16 empty] | 16946.63
|  |  | JDH3-02-008-C-06-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-02-21 | 2026-03-03 | 2025-11-19 | 2025-11-30 | 0 | 0 | 1694663% | Remaining Total Cost | [16 empty] | 16946.63
|  |  | JDH3-02-008-C-06-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-02-21 | 2026-03-03 | 2025-11-19 | 2025-11-30 | 0 | 0 | 1694663% | Actual Total Cost
|  |  | JDH3-02-008-C-06-(ST)- Single Catchbasine Works |  | 2026-02-21 | 2026-03-01 | 2025-11-19 | 2025-11-27 | 0 | 0 | 1564305% | Planned Total Cost | [16 empty] | 15643.05
|  |  | JDH3-02-008-C-06-(ST)- Single Catchbasine Works |  | 2026-02-21 | 2026-03-01 | 2025-11-19 | 2025-11-27 | 0 | 0 | 1564305% | Remaining Total Cost | [16 empty] | 15643.05
|  |  | JDH3-02-008-C-06-(ST)- Single Catchbasine Works |  | 2026-02-21 | 2026-03-01 | 2025-11-19 | 2025-11-27 | 0 | 0 | 1564305% | Actual Total Cost
|  |  | JDH3-02-008-C-06-TSE Network - TSE |  | 2026-03-04 | 2026-04-04 | 04-Aug-25 A | 2026-04-20 | 327791.63 | 327791.63 | 59504200% | Planned Total Cost | [20 empty] | 316200 | 278842
|  |  | JDH3-02-008-C-06-TSE Network - TSE |  | 2026-03-04 | 2026-04-04 | 04-Aug-25 A | 2026-04-20 | 327791.63 | 327791.63 | 59504200% | Remaining Total Cost | [21 empty] | 267250.37
|  |  | JDH3-02-008-C-06-TSE Network - TSE |  | 2026-03-04 | 2026-04-04 | 04-Aug-25 A | 2026-04-20 | 327791.63 | 327791.63 | 59504200% | Actual Total Cost | [13 empty] | 106430.72 | 212737.44 | 8623.47
|  |  | JDH3-02-008-C-06-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-03-04 | 2026-03-30 | 2026-04-02 | 2026-04-19 | 0 | 0 | 1400086% | Planned Total Cost | [21 empty] | 14000.86
|  |  | JDH3-02-008-C-06-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-03-04 | 2026-03-30 | 2026-04-02 | 2026-04-19 | 0 | 0 | 1400086% | Remaining Total Cost | [21 empty] | 14000.86
|  |  | JDH3-02-008-C-06-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-03-04 | 2026-03-30 | 2026-04-02 | 2026-04-19 | 0 | 0 | 1400086% | Actual Total Cost
|  |  | JDH3-02-008-C-06-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-03-04 | 2026-03-31 | 2026-04-02 | 2026-04-20 | 0 | 0 | 7275714% | Planned Total Cost | [21 empty] | 72757.14
|  |  | JDH3-02-008-C-06-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-03-04 | 2026-03-31 | 2026-04-02 | 2026-04-20 | 0 | 0 | 7275714% | Remaining Total Cost | [21 empty] | 72757.14
|  |  | JDH3-02-008-C-06-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-03-04 | 2026-03-31 | 2026-04-02 | 2026-04-20 | 0 | 0 | 7275714% | Actual Total Cost
|  |  | JDH3-02-008-C-06-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2026-03-04 | 2026-04-04 | 04-Aug-25 A | 2026-04-16 | 327791.63 | 327791.63 | 35448430% | Planned Total Cost | [20 empty] | 316200 | 38284.3
|  |  | JDH3-02-008-C-06-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2026-03-04 | 2026-04-04 | 04-Aug-25 A | 2026-04-16 | 327791.63 | 327791.63 | 35448430% | Remaining Total Cost | [21 empty] | 26692.67
|  |  | JDH3-02-008-C-06-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2026-03-04 | 2026-04-04 | 04-Aug-25 A | 2026-04-16 | 327791.63 | 327791.63 | 35448430% | Actual Total Cost | [13 empty] | 106430.72 | 212737.44 | 8623.47
|  |  | JDH3-02-008-C-06-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-03-04 | 2026-03-30 | 2026-04-02 | 2026-04-19 | 0 | 0 | 2472574% | Planned Total Cost | [21 empty] | 24725.74
|  |  | JDH3-02-008-C-06-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-03-04 | 2026-03-30 | 2026-04-02 | 2026-04-19 | 0 | 0 | 2472574% | Remaining Total Cost | [21 empty] | 24725.74
|  |  | JDH3-02-008-C-06-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-03-04 | 2026-03-30 | 2026-04-02 | 2026-04-19 | 0 | 0 | 2472574% | Actual Total Cost
|  |  | JDH3-02-008-C-06-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-03-04 | 2026-03-30 | 2026-04-02 | 2026-04-19 | 0 | 0 | 6553058% | Planned Total Cost | [21 empty] | 65530.58
|  |  | JDH3-02-008-C-06-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-03-04 | 2026-03-30 | 2026-04-02 | 2026-04-19 | 0 | 0 | 6553058% | Remaining Total Cost | [21 empty] | 65530.58
|  |  | JDH3-02-008-C-06-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-03-04 | 2026-03-30 | 2026-04-02 | 2026-04-19 | 0 | 0 | 6553058% | Actual Total Cost
|  |  | JDH3-02-008-C-06-(TSE)-Supply and install gate valves-100 mm |  | 2026-03-24 | 2026-03-28 | 2026-04-12 | 2026-04-16 | 0 | 0 | 775896% | Planned Total Cost | [21 empty] | 7758.96
|  |  | JDH3-02-008-C-06-(TSE)-Supply and install gate valves-100 mm |  | 2026-03-24 | 2026-03-28 | 2026-04-12 | 2026-04-16 | 0 | 0 | 775896% | Remaining Total Cost | [21 empty] | 7758.96
|  |  | JDH3-02-008-C-06-(TSE)-Supply and install gate valves-100 mm |  | 2026-03-24 | 2026-03-28 | 2026-04-12 | 2026-04-16 | 0 | 0 | 775896% | Actual Total Cost
|  |  | JDH3-02-008-C-06-(TSE)-Supply and install gate valves-250 mm |  | 2026-03-24 | 2026-03-28 | 2026-04-12 | 2026-04-16 | 0 | 0 | 769834% | Planned Total Cost | [21 empty] | 7698.34
|  |  | JDH3-02-008-C-06-(TSE)-Supply and install gate valves-250 mm |  | 2026-03-24 | 2026-03-28 | 2026-04-12 | 2026-04-16 | 0 | 0 | 769834% | Remaining Total Cost | [21 empty] | 7698.34
|  |  | JDH3-02-008-C-06-(TSE)-Supply and install gate valves-250 mm |  | 2026-03-24 | 2026-03-28 | 2026-04-12 | 2026-04-16 | 0 | 0 | 769834% | Actual Total Cost
|  |  | JDH3-02-008-C-06-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2026-03-24 | 2026-03-28 | 2026-04-12 | 2026-04-16 | 0 | 0 | 1533996% | Planned Total Cost | [21 empty] | 15339.96
|  |  | JDH3-02-008-C-06-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2026-03-24 | 2026-03-28 | 2026-04-12 | 2026-04-16 | 0 | 0 | 1533996% | Remaining Total Cost | [21 empty] | 15339.96
|  |  | JDH3-02-008-C-06-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2026-03-24 | 2026-03-28 | 2026-04-12 | 2026-04-16 | 0 | 0 | 1533996% | Actual Total Cost
|  |  | JDH3-02-008-C-06-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-03-24 | 2026-03-28 | 2026-04-12 | 2026-04-16 | 0 | 0 | 979190% | Planned Total Cost | [21 empty] | 9791.9
|  |  | JDH3-02-008-C-06-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-03-24 | 2026-03-28 | 2026-04-12 | 2026-04-16 | 0 | 0 | 979190% | Remaining Total Cost | [21 empty] | 9791.9
|  |  | JDH3-02-008-C-06-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-03-24 | 2026-03-28 | 2026-04-12 | 2026-04-16 | 0 | 0 | 979190% | Actual Total Cost
|  |  | JDH3-02-008-C-06-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-03-04 | 2026-03-12 | 2026-04-02 | 2026-04-12 | 0 | 0 | 910230% | Planned Total Cost | [21 empty] | 9102.3
|  |  | JDH3-02-008-C-06-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-03-04 | 2026-03-12 | 2026-04-02 | 2026-04-12 | 0 | 0 | 910230% | Remaining Total Cost | [21 empty] | 9102.3
|  |  | JDH3-02-008-C-06-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-03-04 | 2026-03-12 | 2026-04-02 | 2026-04-12 | 0 | 0 | 910230% | Actual Total Cost
|  |  | JDH3-02-008-C-06-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-03-04 | 2026-03-25 | 2026-04-02 | 2026-04-14 | 0 | 0 | 1385192% | Planned Total Cost | [21 empty] | 13851.92
|  |  | JDH3-02-008-C-06-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-03-04 | 2026-03-25 | 2026-04-02 | 2026-04-14 | 0 | 0 | 1385192% | Remaining Total Cost | [21 empty] | 13851.92
|  |  | JDH3-02-008-C-06-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-03-04 | 2026-03-25 | 2026-04-02 | 2026-04-14 | 0 | 0 | 1385192% | Actual Total Cost
|  |  | C-07 |  | 2026-04-05 | 2026-06-08 | 14-Jul-25 A | 2026-06-13 | 0 | 0 | 102285908% | Planned Total Cost | [21 empty] | 574173.89 | 391879.73 | 56805.45
|  |  | C-07 |  | 2026-04-05 | 2026-06-08 | 14-Jul-25 A | 2026-06-13 | 0 | 0 | 102285908% | Remaining Total Cost | [21 empty] | 574173.89 | 391879.73 | 56805.45
|  |  | C-07 |  | 2026-04-05 | 2026-06-08 | 14-Jul-25 A | 2026-06-13 | 0 | 0 | 102285908% | Actual Total Cost
|  |  | JDH3-02-008-C-07-Storm Network - ST |  | 2026-04-13 | 2026-05-17 | 2026-04-16 | 2026-05-21 | 0 | 0 | 87956733% | Planned Total Cost | [21 empty] | 574173.89 | 305393.43
|  |  | JDH3-02-008-C-07-Storm Network - ST |  | 2026-04-13 | 2026-05-17 | 2026-04-16 | 2026-05-21 | 0 | 0 | 87956733% | Remaining Total Cost | [21 empty] | 574173.89 | 305393.43
|  |  | JDH3-02-008-C-07-Storm Network - ST |  | 2026-04-13 | 2026-05-17 | 2026-04-16 | 2026-05-21 | 0 | 0 | 87956733% | Actual Total Cost
|  |  | JDH3-02-008-C-07-(ST)-Swales |  | 2026-04-13 | 2026-04-26 | 2026-04-16 | 2026-04-30 | 0 | 0 | 7101427% | Planned Total Cost | [21 empty] | 71014.27
|  |  | JDH3-02-008-C-07-(ST)-Swales |  | 2026-04-13 | 2026-04-26 | 2026-04-16 | 2026-04-30 | 0 | 0 | 7101427% | Remaining Total Cost | [21 empty] | 71014.27
|  |  | JDH3-02-008-C-07-(ST)-Swales |  | 2026-04-13 | 2026-04-26 | 2026-04-16 | 2026-04-30 | 0 | 0 | 7101427% | Actual Total Cost
|  |  | JDH3-02-008-C-07-(ST)-Box Culvert |  | 2026-04-13 | 2026-05-17 | 2026-04-16 | 2026-05-21 | 0 | 0 | 75771316% | Planned Total Cost | [21 empty] | 469050.28 | 288662.87
|  |  | JDH3-02-008-C-07-(ST)-Box Culvert |  | 2026-04-13 | 2026-05-17 | 2026-04-16 | 2026-05-21 | 0 | 0 | 75771316% | Remaining Total Cost | [21 empty] | 469050.28 | 288662.87
|  |  | JDH3-02-008-C-07-(ST)-Box Culvert |  | 2026-04-13 | 2026-05-17 | 2026-04-16 | 2026-05-21 | 0 | 0 | 75771316% | Actual Total Cost
|  |  | JDH3-02-008-C-07-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2026-04-13 | 2026-05-10 | 2026-04-16 | 2026-05-14 | 0 | 0 | 21020352% | Planned Total Cost | [21 empty] | 148689.8 | 61513.73
|  |  | JDH3-02-008-C-07-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2026-04-13 | 2026-05-10 | 2026-04-16 | 2026-05-14 | 0 | 0 | 21020352% | Remaining Total Cost | [21 empty] | 148689.8 | 61513.73
|  |  | JDH3-02-008-C-07-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2026-04-13 | 2026-05-10 | 2026-04-16 | 2026-05-14 | 0 | 0 | 21020352% | Actual Total Cost
|  |  | JDH3-02-008-C-07-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2026-04-15 | 2026-05-12 | 2026-04-19 | 2026-05-17 | 0 | 0 | 21896176% | Planned Total Cost | [21 empty] | 136638.22 | 82323.54
|  |  | JDH3-02-008-C-07-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2026-04-15 | 2026-05-12 | 2026-04-19 | 2026-05-17 | 0 | 0 | 21896176% | Remaining Total Cost | [21 empty] | 136638.22 | 82323.54
|  |  | JDH3-02-008-C-07-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2026-04-15 | 2026-05-12 | 2026-04-19 | 2026-05-17 | 0 | 0 | 21896176% | Actual Total Cost
|  |  | JDH3-02-008-C-07-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2026-04-18 | 2026-05-14 | 2026-04-21 | 2026-05-19 | 0 | 0 | 16059537% | Planned Total Cost | [21 empty] | 100137.9 | 60457.46
|  |  | JDH3-02-008-C-07-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2026-04-18 | 2026-05-14 | 2026-04-21 | 2026-05-19 | 0 | 0 | 16059537% | Remaining Total Cost | [21 empty] | 100137.9 | 60457.46
|  |  | JDH3-02-008-C-07-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2026-04-18 | 2026-05-14 | 2026-04-21 | 2026-05-19 | 0 | 0 | 16059537% | Actual Total Cost
|  |  | JDH3-02-008-C-07-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2026-04-20 | 2026-05-17 | 2026-04-23 | 2026-05-21 | 0 | 0 | 16795250% | Planned Total Cost | [21 empty] | 83584.36 | 84368.14
|  |  | JDH3-02-008-C-07-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2026-04-20 | 2026-05-17 | 2026-04-23 | 2026-05-21 | 0 | 0 | 16795250% | Remaining Total Cost | [21 empty] | 83584.36 | 84368.14
|  |  | JDH3-02-008-C-07-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2026-04-20 | 2026-05-17 | 2026-04-23 | 2026-05-21 | 0 | 0 | 16795250% | Actual Total Cost
|  |  | JDH3-02-008-C-07-(ST)-NetWork |  | 2026-04-22 | 2026-05-03 | 2026-04-26 | 2026-05-07 | 0 | 0 | 5083989% | Planned Total Cost | [21 empty] | 34109.33 | 16730.56
|  |  | JDH3-02-008-C-07-(ST)-NetWork |  | 2026-04-22 | 2026-05-03 | 2026-04-26 | 2026-05-07 | 0 | 0 | 5083989% | Remaining Total Cost | [21 empty] | 34109.33 | 16730.56
|  |  | JDH3-02-008-C-07-(ST)-NetWork |  | 2026-04-22 | 2026-05-03 | 2026-04-26 | 2026-05-07 | 0 | 0 | 5083989% | Actual Total Cost
|  |  | JDH3-02-008-C-07-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-04-22 | 2026-05-03 | 2026-04-26 | 2026-05-07 | 0 | 0 | 5083989% | Planned Total Cost | [21 empty] | 34109.33 | 16730.56
|  |  | JDH3-02-008-C-07-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-04-22 | 2026-05-03 | 2026-04-26 | 2026-05-07 | 0 | 0 | 5083989% | Remaining Total Cost | [21 empty] | 34109.33 | 16730.56
|  |  | JDH3-02-008-C-07-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-04-22 | 2026-05-03 | 2026-04-26 | 2026-05-07 | 0 | 0 | 5083989% | Actual Total Cost
|  |  | JDH3-02-008-C-07-TSE Network - TSE |  | 2026-05-18 | 2026-06-08 | 2026-05-21 | 2026-06-13 | 0 | 0 | 14329175% | Planned Total Cost | [22 empty] | 86486.3 | 56805.45
|  |  | JDH3-02-008-C-07-TSE Network - TSE |  | 2026-05-18 | 2026-06-08 | 2026-05-21 | 2026-06-13 | 0 | 0 | 14329175% | Remaining Total Cost | [22 empty] | 86486.3 | 56805.45
|  |  | JDH3-02-008-C-07-TSE Network - TSE |  | 2026-05-18 | 2026-06-08 | 2026-05-21 | 2026-06-13 | 0 | 0 | 14329175% | Actual Total Cost
|  |  | JDH3-02-008-C-07-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-05-18 | 2026-06-06 | 2026-05-21 | 2026-06-10 | 0 | 0 | 51336% | Planned Total Cost | [22 empty] | 462.03 | 51.34
|  |  | JDH3-02-008-C-07-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-05-18 | 2026-06-06 | 2026-05-21 | 2026-06-10 | 0 | 0 | 51336% | Remaining Total Cost | [22 empty] | 462.03 | 51.34
|  |  | JDH3-02-008-C-07-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-05-18 | 2026-06-06 | 2026-05-21 | 2026-06-10 | 0 | 0 | 51336% | Actual Total Cost
|  |  | JDH3-02-008-C-07-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-05-18 | 2026-06-08 | 2026-05-21 | 2026-06-13 | 0 | 0 | 10630401% | Planned Total Cost | [22 empty] | 61383.48 | 44920.53
|  |  | JDH3-02-008-C-07-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-05-18 | 2026-06-08 | 2026-05-21 | 2026-06-13 | 0 | 0 | 10630401% | Remaining Total Cost | [22 empty] | 61383.48 | 44920.53
|  |  | JDH3-02-008-C-07-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-05-18 | 2026-06-08 | 2026-05-21 | 2026-06-13 | 0 | 0 | 10630401% | Actual Total Cost
|  |  | JDH3-02-008-C-07-(TSE)-Supply and install gate valves-250 mm |  | 2026-05-25 | 2026-05-28 | 2026-05-28 | 2026-06-02 | 0 | 0 | 1283057% | Planned Total Cost | [22 empty] | 12174.07 | 656.5
|  |  | JDH3-02-008-C-07-(TSE)-Supply and install gate valves-250 mm |  | 2026-05-25 | 2026-05-28 | 2026-05-28 | 2026-06-02 | 0 | 0 | 1283057% | Remaining Total Cost | [22 empty] | 12174.07 | 656.5
|  |  | JDH3-02-008-C-07-(TSE)-Supply and install gate valves-250 mm |  | 2026-05-25 | 2026-05-28 | 2026-05-28 | 2026-06-02 | 0 | 0 | 1283057% | Actual Total Cost
|  |  | JDH3-02-008-C-07-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-05-31 | 2026-06-03 | 2026-06-03 | 2026-06-08 | 0 | 0 | 979190% | Planned Total Cost | [23 empty] | 9791.9
|  |  | JDH3-02-008-C-07-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-05-31 | 2026-06-03 | 2026-06-03 | 2026-06-08 | 0 | 0 | 979190% | Remaining Total Cost | [23 empty] | 9791.9
|  |  | JDH3-02-008-C-07-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-05-31 | 2026-06-03 | 2026-06-03 | 2026-06-08 | 0 | 0 | 979190% | Actual Total Cost
|  |  | JDH3-02-008-C-07-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-05-18 | 2026-06-06 | 2026-05-21 | 2026-06-10 | 0 | 0 | 1385192% | Planned Total Cost | [22 empty] | 12466.72 | 1385.19
|  |  | JDH3-02-008-C-07-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-05-18 | 2026-06-06 | 2026-05-21 | 2026-06-10 | 0 | 0 | 1385192% | Remaining Total Cost | [22 empty] | 12466.72 | 1385.19
|  |  | JDH3-02-008-C-07-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-05-18 | 2026-06-06 | 2026-05-21 | 2026-06-10 | 0 | 0 | 1385192% | Actual Total Cost
|  |  | C-08 |  | 2025-08-02 | 2025-11-26 | 08-Apr-25 A | 2025-11-29 | 1094305.25 | 1094305.26 | 160257268% | Planned Total Cost | [13 empty] | 89212.81 | 507404.91 | 490779.22 | 515175.74
|  |  | C-08 |  | 2025-08-02 | 2025-11-26 | 08-Apr-25 A | 2025-11-29 | 1094305.25 | 1094305.26 | 160257268% | Remaining Total Cost | [16 empty] | 508267.42
|  |  | C-08 |  | 2025-08-02 | 2025-11-26 | 08-Apr-25 A | 2025-11-29 | 1094305.25 | 1094305.26 | 160257268% | Actual Total Cost | [9 empty] | 10936.41 | 56912.73 | 210642.16 | 218743.78 | 519663.61 | 74539.65 | 2866.91
|  |  | JDH3-02-008-C-08-Storm Network - ST |  | 2025-08-10 | 2025-11-26 | 15-Apr-25 A | 2025-11-29 | 1094305.25 | 1094305.26 | 160257268% | Planned Total Cost | [13 empty] | 89212.81 | 507404.91 | 490779.22 | 515175.74
|  |  | JDH3-02-008-C-08-Storm Network - ST |  | 2025-08-10 | 2025-11-26 | 15-Apr-25 A | 2025-11-29 | 1094305.25 | 1094305.26 | 160257268% | Remaining Total Cost | [16 empty] | 508267.42
|  |  | JDH3-02-008-C-08-Storm Network - ST |  | 2025-08-10 | 2025-11-26 | 15-Apr-25 A | 2025-11-29 | 1094305.25 | 1094305.26 | 160257268% | Actual Total Cost | [9 empty] | 10936.41 | 56912.73 | 210642.16 | 218743.78 | 519663.61 | 74539.65 | 2866.91
|  |  | JDH3-02-008-C-08-(ST)-Swales |  | 2025-08-10 | 2025-10-20 | 15-Apr-25 A | 2025-11-23 | 600765.18 | 600765.18 | 90106035% | Planned Total Cost | [13 empty] | 89212.81 | 507404.91 | 304442.63
|  |  | JDH3-02-008-C-08-(ST)-Swales |  | 2025-08-10 | 2025-10-20 | 15-Apr-25 A | 2025-11-23 | 600765.18 | 600765.18 | 90106035% | Remaining Total Cost | [16 empty] | 300295.17
|  |  | JDH3-02-008-C-08-(ST)-Swales |  | 2025-08-10 | 2025-10-20 | 15-Apr-25 A | 2025-11-23 | 600765.18 | 600765.18 | 90106035% | Actual Total Cost | [9 empty] | 10936.41 | 56912.73 | 210642.16 | 218743.78 | 26123.53 | 74539.65 | 2866.91
|  |  | JDH3-02-008-C-08-(ST)-Box Culvert |  | 2025-10-21 | 2025-11-26 | 02-Aug-25 A | 2025-11-29 | 493540.08 | 493540.08 | 57927504% | Planned Total Cost | [15 empty] | 186336.59 | 392938.44
|  |  | JDH3-02-008-C-08-(ST)-Box Culvert |  | 2025-10-21 | 2025-11-26 | 02-Aug-25 A | 2025-11-29 | 493540.08 | 493540.08 | 57927504% | Remaining Total Cost | [16 empty] | 85734.96
|  |  | JDH3-02-008-C-08-(ST)-Box Culvert |  | 2025-10-21 | 2025-11-26 | 02-Aug-25 A | 2025-11-29 | 493540.08 | 493540.08 | 57927504% | Actual Total Cost | [13 empty] | 493540.08
|  |  | JDH3-02-008-C-08-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2025-10-21 | 2025-11-22 | 02-Aug-25 A | 21-Aug-25 A | 241734.05 | 241734.06 | 24173405% | Planned Total Cost | [15 empty] | 120867.03 | 120867.03
|  |  | JDH3-02-008-C-08-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2025-10-21 | 2025-11-22 | 02-Aug-25 A | 21-Aug-25 A | 241734.05 | 241734.06 | 24173405% | Remaining Total Cost
|  |  | JDH3-02-008-C-08-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2025-10-21 | 2025-11-22 | 02-Aug-25 A | 21-Aug-25 A | 241734.05 | 241734.06 | 24173405% | Actual Total Cost | [13 empty] | 241734.06
|  |  | JDH3-02-008-C-08-(ST)- Concrete Box Culvert With Dim (1000x1000) depth from 2.51 to 3.50 |  | 2025-10-23 | 2025-11-13 | 2025-11-06 | 2025-11-29 | 0 | 0 | 8573496% | Planned Total Cost | [16 empty] | 85734.96
|  |  | JDH3-02-008-C-08-(ST)- Concrete Box Culvert With Dim (1000x1000) depth from 2.51 to 3.50 |  | 2025-10-23 | 2025-11-13 | 2025-11-06 | 2025-11-29 | 0 | 0 | 8573496% | Remaining Total Cost | [16 empty] | 85734.96
|  |  | JDH3-02-008-C-08-(ST)- Concrete Box Culvert With Dim (1000x1000) depth from 2.51 to 3.50 |  | 2025-10-23 | 2025-11-13 | 2025-11-06 | 2025-11-29 | 0 | 0 | 8573496% | Actual Total Cost
|  |  | JDH3-02-008-C-08-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2025-10-26 | 2025-11-26 | 02-Aug-25 A | 30-Aug-25 A | 251806.03 | 251806.02 | 25180603% | Planned Total Cost | [15 empty] | 65469.57 | 186336.46
|  |  | JDH3-02-008-C-08-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2025-10-26 | 2025-11-26 | 02-Aug-25 A | 30-Aug-25 A | 251806.03 | 251806.02 | 25180603% | Remaining Total Cost
|  |  | JDH3-02-008-C-08-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2025-10-26 | 2025-11-26 | 02-Aug-25 A | 30-Aug-25 A | 251806.03 | 251806.02 | 25180603% | Actual Total Cost | [13 empty] | 251806.02
|  |  | JDH3-02-008-C-08-(ST)-NetWork |  | 2025-10-28 | 2025-11-10 | 2025-11-06 | 2025-11-25 | 0 | 0 | 12223729% | Planned Total Cost | [16 empty] | 122237.29
|  |  | JDH3-02-008-C-08-(ST)-NetWork |  | 2025-10-28 | 2025-11-10 | 2025-11-06 | 2025-11-25 | 0 | 0 | 12223729% | Remaining Total Cost | [16 empty] | 122237.29
|  |  | JDH3-02-008-C-08-(ST)-NetWork |  | 2025-10-28 | 2025-11-10 | 2025-11-06 | 2025-11-25 | 0 | 0 | 12223729% | Actual Total Cost
|  |  | JDH3-02-008-C-08-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-10-28 | 2025-11-08 | 2025-11-06 | 2025-11-18 | 0 | 0 | 1368766% | Planned Total Cost | [16 empty] | 13687.66
|  |  | JDH3-02-008-C-08-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-10-28 | 2025-11-08 | 2025-11-06 | 2025-11-18 | 0 | 0 | 1368766% | Remaining Total Cost | [16 empty] | 13687.66
|  |  | JDH3-02-008-C-08-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-10-28 | 2025-11-08 | 2025-11-06 | 2025-11-18 | 0 | 0 | 1368766% | Actual Total Cost
|  |  | JDH3-02-008-C-08-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-10-30 | 2025-11-10 | 2025-11-13 | 2025-11-25 | 0 | 0 | 7465636% | Planned Total Cost | [16 empty] | 74656.36
|  |  | JDH3-02-008-C-08-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-10-30 | 2025-11-10 | 2025-11-13 | 2025-11-25 | 0 | 0 | 7465636% | Remaining Total Cost | [16 empty] | 74656.36
|  |  | JDH3-02-008-C-08-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-10-30 | 2025-11-10 | 2025-11-13 | 2025-11-25 | 0 | 0 | 7465636% | Actual Total Cost
|  |  | JDH3-02-008-C-08-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-10-30 | 2025-11-10 | 2025-11-09 | 2025-11-20 | 0 | 0 | 3389326% | Planned Total Cost | [16 empty] | 33893.26
|  |  | JDH3-02-008-C-08-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-10-30 | 2025-11-10 | 2025-11-09 | 2025-11-20 | 0 | 0 | 3389326% | Remaining Total Cost | [16 empty] | 33893.26
|  |  | JDH3-02-008-C-08-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-10-30 | 2025-11-10 | 2025-11-09 | 2025-11-20 | 0 | 0 | 3389326% | Actual Total Cost
|  |  | C-09 |  | 2024-08-27 | 2024-12-12 | 11-Jan-25 A | 2025-11-06 | 643925.87 | 643925.87 | 92334176% | Planned Total Cost |  |  | 140231.68 | 45630213% | 18618432% | 4356175% | [9 empty] | 80079.93 | 16981.95
|  |  | C-09 |  | 2024-08-27 | 2024-12-12 | 11-Jan-25 A | 2025-11-06 | 643925.87 | 643925.87 | 92334176% | Remaining Total Cost | [15 empty] | 262433.94 | 16981.95
|  |  | C-09 |  | 2024-08-27 | 2024-12-12 | 11-Jan-25 A | 2025-11-06 | 643925.87 | 643925.87 | 92334176% | Actual Total Cost | [6 empty] | 14001.99 | 18669.32 | 21002.99 | 30078.02 | 31522.38 | 70308.93 | 175034.01 | 109836.1 | 167047.24 | 6424.89
|  |  | JDH3-02-008-C-09-Storm Network - ST |  | 2024-09-10 | 2024-11-21 | 15-Apr-25 A | 2025-11-02 | 556802.37 | 556802.37 | 82269290% | Planned Total Cost |  |  | 140231.68 | 45630213% | 14262257% | [10 empty] | 80079.93 | 3456.59
|  |  | JDH3-02-008-C-09-Storm Network - ST |  | 2024-09-10 | 2024-11-21 | 15-Apr-25 A | 2025-11-02 | 556802.37 | 556802.37 | 82269290% | Remaining Total Cost | [15 empty] | 262433.94 | 3456.59
|  |  | JDH3-02-008-C-09-Storm Network - ST |  | 2024-09-10 | 2024-11-21 | 15-Apr-25 A | 2025-11-02 | 556802.37 | 556802.37 | 82269290% | Actual Total Cost | [9 empty] | 9852.92 | 18298.28 | 70308.93 | 175034.01 | 109836.1 | 167047.24 | 6424.89
|  |  | JDH3-02-008-C-09-(ST)-Swales |  | 2024-09-10 | 2024-11-10 | 15-Apr-25 A | 2025-10-21 | 556802.37 | 556802.37 | 77789908% | Planned Total Cost |  |  | 140231.68 | 45630213% | 14262257% | [10 empty] | 38742.7
|  |  | JDH3-02-008-C-09-(ST)-Swales |  | 2024-09-10 | 2024-11-10 | 15-Apr-25 A | 2025-10-21 | 556802.37 | 556802.37 | 77789908% | Remaining Total Cost | [15 empty] | 221096.71
|  |  | JDH3-02-008-C-09-(ST)-Swales |  | 2024-09-10 | 2024-11-10 | 15-Apr-25 A | 2025-10-21 | 556802.37 | 556802.37 | 77789908% | Actual Total Cost | [9 empty] | 9852.92 | 18298.28 | 70308.93 | 175034.01 | 109836.1 | 167047.24 | 6424.89
|  |  | JDH3-02-008-C-09-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2024-11-11 | 2024-11-21 | 2025-10-21 | 2025-11-02 | 0 | 0 | 4479382% | Planned Total Cost | [15 empty] | 41337.23 | 3456.59
|  |  | JDH3-02-008-C-09-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2024-11-11 | 2024-11-21 | 2025-10-21 | 2025-11-02 | 0 | 0 | 4479382% | Remaining Total Cost | [15 empty] | 41337.23 | 3456.59
|  |  | JDH3-02-008-C-09-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2024-11-11 | 2024-11-21 | 2025-10-21 | 2025-11-02 | 0 | 0 | 4479382% | Actual Total Cost
|  |  | JDH3-02-008-C-09-Road Works - RD |  | 2024-11-23 | 2024-12-12 | 11-Jan-25 A | 2025-11-06 | 2138-07-13 12:00 | 2138-07-13 12:00 | 10064886% | Planned Total Cost |  |  |  |  | 4356175% | 4356175% | [10 empty] | 13525.36
|  |  | JDH3-02-008-C-09-Road Works - RD |  | 2024-11-23 | 2024-12-12 | 11-Jan-25 A | 2025-11-06 | 2138-07-13 12:00 | 2138-07-13 12:00 | 10064886% | Remaining Total Cost | [16 empty] | 13525.36
|  |  | JDH3-02-008-C-09-Road Works - RD |  | 2024-11-23 | 2024-12-12 | 11-Jan-25 A | 2025-11-06 | 2138-07-13 12:00 | 2138-07-13 12:00 | 10064886% | Actual Total Cost | [6 empty] | 14001.99 | 18669.32 | 21002.99 | 20225.1 | 13224.1
|  |  | JDH3-02-008-C-09-(RD)-Precast Concrete Curb |  | 2024-11-23 | 2024-12-12 | 11-Jan-25 A | 2025-11-06 | 2138-07-13 12:00 | 2138-07-13 12:00 | 10064886% | Planned Total Cost |  |  |  |  | 4356175% | 4356175% | [10 empty] | 13525.36
|  |  | JDH3-02-008-C-09-(RD)-Precast Concrete Curb |  | 2024-11-23 | 2024-12-12 | 11-Jan-25 A | 2025-11-06 | 2138-07-13 12:00 | 2138-07-13 12:00 | 10064886% | Remaining Total Cost | [16 empty] | 13525.36
|  |  | JDH3-02-008-C-09-(RD)-Precast Concrete Curb |  | 2024-11-23 | 2024-12-12 | 11-Jan-25 A | 2025-11-06 | 2138-07-13 12:00 | 2138-07-13 12:00 | 10064886% | Actual Total Cost | [6 empty] | 14001.99 | 18669.32 | 21002.99 | 20225.1 | 13224.1
|  |  | C-10 |  | 2024-12-14 | 2025-05-04 | 01-Apr-25 A | 2026-01-22 | 544538.18 | 544538.17 | 233683196% | Planned Total Cost | [5 empty] | 7621369% | 390434.74 | 35854.36 |  | 477803.38 | [5 empty] | 34559.69 | 340714.39 | 609012.41 | 372239.29
|  |  | C-10 |  | 2024-12-14 | 2025-05-04 | 01-Apr-25 A | 2026-01-22 | 544538.18 | 544538.17 | 233683196% | Remaining Total Cost | [15 empty] | 94443.75 | 340714.39 | 609012.41 | 748123.24
|  |  | C-10 |  | 2024-12-14 | 2025-05-04 | 01-Apr-25 A | 2026-01-22 | 544538.18 | 544538.17 | 233683196% | Actual Total Cost | [9 empty] | 45132.07 | 78292.83 | 78292.83 | 81304.09 | 115423.1 | 140682.39 | 5410.86
|  |  | JDH3-02-008-C-10-Storm Network - ST |  | 2024-12-22 | 2025-05-04 | 10-Apr-25 A | 2026-01-22 | 544538.18 | 544538.17 | 233683196% | Planned Total Cost | [5 empty] | 7621369% | 390434.74 | 35854.36 |  | 477803.38 | [5 empty] | 34559.69 | 340714.39 | 609012.41 | 372239.29
|  |  | JDH3-02-008-C-10-Storm Network - ST |  | 2024-12-22 | 2025-05-04 | 10-Apr-25 A | 2026-01-22 | 544538.18 | 544538.17 | 233683196% | Remaining Total Cost | [15 empty] | 94443.75 | 340714.39 | 609012.41 | 748123.24
|  |  | JDH3-02-008-C-10-Storm Network - ST |  | 2024-12-22 | 2025-05-04 | 10-Apr-25 A | 2026-01-22 | 544538.18 | 544538.17 | 233683196% | Actual Total Cost | [9 empty] | 45132.07 | 78292.83 | 78292.83 | 81304.09 | 115423.1 | 140682.39 | 5410.86
|  |  | JDH3-02-008-C-10-(ST)-Swales |  | 2024-12-22 | 2025-02-20 | 10-Apr-25 A | 2025-11-25 | 442618.74 | 442618.74 | 69984258% | Planned Total Cost | [5 empty] | 7621369% | 390434.74 | 35854.36 | [7 empty] | 34559.69 | 162780.09
|  |  | JDH3-02-008-C-10-(ST)-Swales |  | 2024-12-22 | 2025-02-20 | 10-Apr-25 A | 2025-11-25 | 442618.74 | 442618.74 | 69984258% | Remaining Total Cost | [15 empty] | 94443.75 | 162780.09
|  |  | JDH3-02-008-C-10-(ST)-Swales |  | 2024-12-22 | 2025-02-20 | 10-Apr-25 A | 2025-11-25 | 442618.74 | 442618.74 | 69984258% | Actual Total Cost | [9 empty] | 45132.07 | 78292.83 | 78292.83 | 81304.09 | 78292.83 | 78292.83 | 3011.26
|  |  | JDH3-02-008-C-10-(ST)-Box Culvert |  | 2025-02-22 | 2025-04-07 | 2025-11-25 | 2026-01-10 | 0 | 0 | 93088564% | Planned Total Cost | [16 empty] | 177934.3 | 609012.41 | 143938.93
|  |  | JDH3-02-008-C-10-(ST)-Box Culvert |  | 2025-02-22 | 2025-04-07 | 2025-11-25 | 2026-01-10 | 0 | 0 | 93088564% | Remaining Total Cost | [16 empty] | 177934.3 | 609012.41 | 143938.93
|  |  | JDH3-02-008-C-10-(ST)-Box Culvert |  | 2025-02-22 | 2025-04-07 | 2025-11-25 | 2026-01-10 | 0 | 0 | 93088564% | Actual Total Cost
|  |  | JDH3-02-008-C-10-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2025-02-22 | 2025-04-05 | 2025-11-25 | 2026-01-07 | 0 | 0 | 47586543% | Planned Total Cost | [16 empty] | 104486.45 | 302715.56 | 68663.42
|  |  | JDH3-02-008-C-10-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2025-02-22 | 2025-04-05 | 2025-11-25 | 2026-01-07 | 0 | 0 | 47586543% | Remaining Total Cost | [16 empty] | 104486.45 | 302715.56 | 68663.42
|  |  | JDH3-02-008-C-10-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2025-02-22 | 2025-04-05 | 2025-11-25 | 2026-01-07 | 0 | 0 | 47586543% | Actual Total Cost
|  |  | JDH3-02-008-C-10-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2025-02-24 | 2025-04-07 | 2025-11-27 | 2026-01-10 | 0 | 0 | 45502021% | Planned Total Cost | [16 empty] | 73447.84 | 306296.85 | 75275.51
|  |  | JDH3-02-008-C-10-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2025-02-24 | 2025-04-07 | 2025-11-27 | 2026-01-10 | 0 | 0 | 45502021% | Remaining Total Cost | [16 empty] | 73447.84 | 306296.85 | 75275.51
|  |  | JDH3-02-008-C-10-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2025-02-24 | 2025-04-07 | 2025-11-27 | 2026-01-10 | 0 | 0 | 45502021% | Actual Total Cost
|  |  | JDH3-02-008-C-10-(ST)-NetWork |  | 2025-04-08 | 2025-05-04 | 11-Aug-25 A | 2026-01-22 | 2179-01-15 10:19 | 2179-01-15 10:19 | 70610375% | Planned Total Cost | [9 empty] | 477803.38 | [8 empty] | 228300.36
|  |  | JDH3-02-008-C-10-(ST)-NetWork |  | 2025-04-08 | 2025-05-04 | 11-Aug-25 A | 2026-01-22 | 2179-01-15 10:19 | 2179-01-15 10:19 | 70610375% | Remaining Total Cost | [18 empty] | 604184.32
|  |  | JDH3-02-008-C-10-(ST)-NetWork |  | 2025-04-08 | 2025-05-04 | 11-Aug-25 A | 2026-01-22 | 2179-01-15 10:19 | 2179-01-15 10:19 | 70610375% | Actual Total Cost | [13 empty] | 37130.27 | 62389.56 | 2399.6
|  |  | JDH3-02-008-C-10-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-04-08 | 2025-04-19 | 2026-01-10 | 2026-01-21 | 0 | 0 | 6778653% | Planned Total Cost | [18 empty] | 67786.53
|  |  | JDH3-02-008-C-10-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-04-08 | 2025-04-19 | 2026-01-10 | 2026-01-21 | 0 | 0 | 6778653% | Remaining Total Cost | [18 empty] | 67786.53
|  |  | JDH3-02-008-C-10-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-04-08 | 2025-04-19 | 2026-01-10 | 2026-01-21 | 0 | 0 | 6778653% | Actual Total Cost
|  |  | JDH3-02-008-C-10-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-04-10 | 2025-05-04 | 11-Aug-25 A | 2026-01-22 | 2079-02-06 04:05 | 2079-02-06 04:05 | 52881592% | Planned Total Cost | [9 empty] | 423052.73 | [8 empty] | 105763.18
|  |  | JDH3-02-008-C-10-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-04-10 | 2025-05-04 | 11-Aug-25 A | 2026-01-22 | 2079-02-06 04:05 | 2079-02-06 04:05 | 52881592% | Remaining Total Cost | [18 empty] | 463398.75
|  |  | JDH3-02-008-C-10-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-04-10 | 2025-05-04 | 11-Aug-25 A | 2026-01-22 | 2079-02-06 04:05 | 2079-02-06 04:05 | 52881592% | Actual Total Cost | [13 empty] | 23597.73 | 40270.57 | 1548.87
|  |  | JDH3-02-008-C-10-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-04-10 | 2025-04-21 | 11-Aug-25 A | 2026-01-19 | 1999-12-08 06:14 | 1999-12-08 06:14 | 10950130% | Planned Total Cost | [9 empty] | 54750.65 | [8 empty] | 54750.65
|  |  | JDH3-02-008-C-10-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-04-10 | 2025-04-21 | 11-Aug-25 A | 2026-01-19 | 1999-12-08 06:14 | 1999-12-08 06:14 | 10950130% | Remaining Total Cost | [18 empty] | 72999.04
|  |  | JDH3-02-008-C-10-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-04-10 | 2025-04-21 | 11-Aug-25 A | 2026-01-19 | 1999-12-08 06:14 | 1999-12-08 06:14 | 10950130% | Actual Total Cost | [13 empty] | 13532.55 | 22118.98 | 850.73
|  |  | C-11 |  | 2025-08-10 | 2026-03-14 | 22-Nov-24 A | 2026-03-07 | 1952165.1 | 1952165.1 | 468707608% | Planned Total Cost | [13 empty] | 98408.26 | 223162.66 | 441058.29 | 1235482.19 | 1066084.52 | 517796.21 | 954792.8 | 150291.14
|  |  | C-11 |  | 2025-08-10 | 2026-03-14 | 22-Nov-24 A | 2026-03-07 | 1952165.1 | 1952165.1 | 468707608% | Remaining Total Cost | [16 empty] | 710611.87 | 981473.97 | 328010.29 | 629376.98 | 85437.85
|  |  | C-11 |  | 2025-08-10 | 2026-03-14 | 22-Nov-24 A | 2026-03-07 | 1952165.1 | 1952165.1 | 468707608% | Actual Total Cost |  |  |  |  | 2289522% | 8831014% | 91497.63 | 109684.44 | 84369.3 | 27662.43 | 71572.99 | 110682.43 | 293966.99 | 551627.36 | 486217.27 | 13678.89
|  |  | JDH3-02-008-C-11-Storm Network - ST |  | 2025-08-18 | 2026-01-01 | 15-Jun-25 A | 2026-02-16 | 1208227.41 | 1208227.42 | 344949990% | Planned Total Cost | [13 empty] | 98408.26 | 223162.66 | 441058.29 | 1042048.11 | 1066084.52 | 328010.29 | 250727.76
|  |  | JDH3-02-008-C-11-Storm Network - ST |  | 2025-08-18 | 2026-01-01 | 15-Jun-25 A | 2026-02-16 | 1208227.41 | 1208227.42 | 344949990% | Remaining Total Cost | [16 empty] | 681060.46 | 981473.97 | 328010.29 | 250727.76
|  |  | JDH3-02-008-C-11-Storm Network - ST |  | 2025-08-18 | 2026-01-01 | 15-Jun-25 A | 2026-02-16 | 1208227.41 | 1208227.42 | 344949990% | Actual Total Cost | [11 empty] | 87222.79 | 286307.59 | 539932.14 | 283893.77 | 10871.13
|  |  | JDH3-02-008-C-11-(ST)-Swales |  | 2025-08-18 | 2025-11-27 | 15-Jun-25 A | 2025-11-17 | 1102464.23 | 1102464.23 | 135781663% | Planned Total Cost | [13 empty] | 98408.26 | 223162.66 | 441058.29 | 595187.42
|  |  | JDH3-02-008-C-11-(ST)-Swales |  | 2025-08-18 | 2025-11-27 | 15-Jun-25 A | 2025-11-17 | 1102464.23 | 1102464.23 | 135781663% | Remaining Total Cost | [16 empty] | 255352.4
|  |  | JDH3-02-008-C-11-(ST)-Swales |  | 2025-08-18 | 2025-11-27 | 15-Jun-25 A | 2025-11-17 | 1102464.23 | 1102464.23 | 135781663% | Actual Total Cost | [11 empty] | 87222.79 | 286307.59 | 435413.22 | 282649.49 | 10871.13
|  |  | JDH3-02-008-C-11-(ST)-Box Culvert |  | 2025-10-04 | 2026-01-01 | 2025-11-17 | 2026-02-16 | 0 | 0 | 183340040% | Planned Total Cost | [16 empty] | 425708.05 | 828954.29 | 328010.29 | 250727.76
|  |  | JDH3-02-008-C-11-(ST)-Box Culvert |  | 2025-10-04 | 2026-01-01 | 2025-11-17 | 2026-02-16 | 0 | 0 | 183340040% | Remaining Total Cost | [16 empty] | 425708.05 | 828954.29 | 328010.29 | 250727.76
|  |  | JDH3-02-008-C-11-(ST)-Box Culvert |  | 2025-10-04 | 2026-01-01 | 2025-11-17 | 2026-02-16 | 0 | 0 | 183340040% | Actual Total Cost
|  |  | JDH3-02-008-C-11-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2025-10-04 | 2025-12-24 | 2025-11-17 | 2026-02-08 | 0 | 0 | 87444665% | Planned Total Cost | [16 empty] | 261197.21 | 370878.14 | 138175.52 | 104195.78
|  |  | JDH3-02-008-C-11-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2025-10-04 | 2025-12-24 | 2025-11-17 | 2026-02-08 | 0 | 0 | 87444665% | Remaining Total Cost | [16 empty] | 261197.21 | 370878.14 | 138175.52 | 104195.78
|  |  | JDH3-02-008-C-11-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2025-10-04 | 2025-12-24 | 2025-11-17 | 2026-02-08 | 0 | 0 | 87444665% | Actual Total Cost
|  |  | JDH3-02-008-C-11-(ST)- Concrete Box Culvert With Dim (1000x1000) depth from 2.51 to 3.50 |  | 2025-10-09 | 2025-10-25 | 2025-11-23 | 2025-12-09 | 0 | 0 | 4807282% | Planned Total Cost | [16 empty] | 29654.92 | 18417.9
|  |  | JDH3-02-008-C-11-(ST)- Concrete Box Culvert With Dim (1000x1000) depth from 2.51 to 3.50 |  | 2025-10-09 | 2025-10-25 | 2025-11-23 | 2025-12-09 | 0 | 0 | 4807282% | Remaining Total Cost | [16 empty] | 29654.92 | 18417.9
|  |  | JDH3-02-008-C-11-(ST)- Concrete Box Culvert With Dim (1000x1000) depth from 2.51 to 3.50 |  | 2025-10-09 | 2025-10-25 | 2025-11-23 | 2025-12-09 | 0 | 0 | 4807282% | Actual Total Cost
|  |  | JDH3-02-008-C-11-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2025-10-12 | 2026-01-01 | 2025-11-25 | 2026-02-16 | 0 | 0 | 91088093% | Planned Total Cost | [16 empty] | 134855.92 | 439658.25 | 189834.78 | 146531.98
|  |  | JDH3-02-008-C-11-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2025-10-12 | 2026-01-01 | 2025-11-25 | 2026-02-16 | 0 | 0 | 91088093% | Remaining Total Cost | [16 empty] | 134855.92 | 439658.25 | 189834.78 | 146531.98
|  |  | JDH3-02-008-C-11-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2025-10-12 | 2026-01-01 | 2025-11-25 | 2026-02-16 | 0 | 0 | 91088093% | Actual Total Cost
|  |  | JDH3-02-008-C-11-(ST)-NetWork |  | 2025-11-29 | 2025-12-11 | 04-Aug-25 A | 2025-12-15 | 2189-07-25 04:19 | 2189-07-25 04:34 | 25828287% | Planned Total Cost | [16 empty] | 21152.64 | 237130.23
|  |  | JDH3-02-008-C-11-(ST)-NetWork |  | 2025-11-29 | 2025-12-11 | 04-Aug-25 A | 2025-12-15 | 2189-07-25 04:19 | 2189-07-25 04:34 | 25828287% | Remaining Total Cost | [17 empty] | 152519.68
|  |  | JDH3-02-008-C-11-(ST)-NetWork |  | 2025-11-29 | 2025-12-11 | 04-Aug-25 A | 2025-12-15 | 2189-07-25 04:19 | 2189-07-25 04:34 | 25828287% | Actual Total Cost | [13 empty] | 104518.92 | 1244.27
|  |  | JDH3-02-008-C-11-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-11-29 | 2025-12-09 | 04-Aug-25 A | 02-Sep-25 A | 2189-07-25 04:19 | 2189-07-25 04:34 | 10576318% | Planned Total Cost | [16 empty] | 21152.64 | 84610.55
|  |  | JDH3-02-008-C-11-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-11-29 | 2025-12-09 | 04-Aug-25 A | 02-Sep-25 A | 2189-07-25 04:19 | 2189-07-25 04:34 | 10576318% | Remaining Total Cost
|  |  | JDH3-02-008-C-11-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-11-29 | 2025-12-09 | 04-Aug-25 A | 02-Sep-25 A | 2189-07-25 04:19 | 2189-07-25 04:34 | 10576318% | Actual Total Cost | [13 empty] | 104518.92 | 1244.27
|  |  | JDH3-02-008-C-11-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-11-29 | 2025-12-11 | 2025-12-01 | 2025-12-15 | 0 | 0 | 15251968% | Planned Total Cost | [17 empty] | 152519.68
|  |  | JDH3-02-008-C-11-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-11-29 | 2025-12-11 | 2025-12-01 | 2025-12-15 | 0 | 0 | 15251968% | Remaining Total Cost | [17 empty] | 152519.68
|  |  | JDH3-02-008-C-11-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-11-29 | 2025-12-11 | 2025-12-01 | 2025-12-15 | 0 | 0 | 15251968% | Actual Total Cost
|  |  | JDH3-02-008-C-11-TSE Network - TSE |  | 2026-01-03 | 2026-03-14 | 21-Jan-25 A | 2026-03-07 | 429946.08 | 429946.07 | 90557882% | Planned Total Cost | [16 empty] | 175428.33 |  | 147920.37 | 431938.97 | 150291.14
|  |  | JDH3-02-008-C-11-TSE Network - TSE |  | 2026-01-03 | 2026-03-14 | 21-Jan-25 A | 2026-03-07 | 429946.08 | 429946.07 | 90557882% | Remaining Total Cost | [16 empty] | 11545.66 |  |  | 378649.22 | 85437.85
|  |  | JDH3-02-008-C-11-TSE Network - TSE |  | 2026-01-03 | 2026-03-14 | 21-Jan-25 A | 2026-03-07 | 429946.08 | 429946.07 | 90557882% | Actual Total Cost | [6 empty] | 6458.24 | 31186.54 | 45120.35 | 27662.43 | 71572.99 | 23459.64 | 7659.41 | 11695.22 | 202323.51 | 2807.75
|  |  | JDH3-02-008-C-11-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-01-03 | 2026-02-23 | 2026-02-16 | 2026-03-07 | 0 | 0 | 528532% | Planned Total Cost | [19 empty] | 4756.79 | 528.53
|  |  | JDH3-02-008-C-11-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-01-03 | 2026-02-23 | 2026-02-16 | 2026-03-07 | 0 | 0 | 528532% | Remaining Total Cost | [19 empty] | 4756.79 | 528.53
|  |  | JDH3-02-008-C-11-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-01-03 | 2026-02-23 | 2026-02-16 | 2026-03-07 | 0 | 0 | 528532% | Actual Total Cost
|  |  | JDH3-02-008-C-11-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-01-05 | 2026-03-14 | 21-Jan-25 A | 2026-02-23 | 207587.3 | 207587.3 | 35456570% | Planned Total Cost | [18 empty] | 89444.26 | 200268.14 | 64853.29
|  |  | JDH3-02-008-C-11-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-01-05 | 2026-03-14 | 21-Jan-25 A | 2026-02-23 | 207587.3 | 207587.3 | 35456570% | Remaining Total Cost | [19 empty] | 146978.4
|  |  | JDH3-02-008-C-11-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-01-05 | 2026-03-14 | 21-Jan-25 A | 2026-02-23 | 207587.3 | 207587.3 | 35456570% | Actual Total Cost | [6 empty] | 6458.24 | 31186.54 | 45120.35 | 27662.43 | 24792.1 | 23459.64 | 7659.41 |  | 39286.9 | 1961.7
|  |  | JDH3-02-008-C-11-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-01-18 | 2026-01-28 | 2026-02-21 | 2026-03-04 | 0 | 0 | 9935037% | Planned Total Cost | [19 empty] | 84124.92 | 15225.44
|  |  | JDH3-02-008-C-11-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-01-18 | 2026-01-28 | 2026-02-21 | 2026-03-04 | 0 | 0 | 9935037% | Remaining Total Cost | [19 empty] | 84124.92 | 15225.44
|  |  | JDH3-02-008-C-11-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-01-18 | 2026-01-28 | 2026-02-21 | 2026-03-04 | 0 | 0 | 9935037% | Actual Total Cost
|  |  | JDH3-02-008-C-11-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-01-15 | 2026-02-05 | 01-May-25 A | 2025-11-06 | 222358.77 | 222358.77 | 23390444% | Planned Total Cost | [16 empty] | 175428.33 |  | 58476.11
|  |  | JDH3-02-008-C-11-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-01-15 | 2026-02-05 | 01-May-25 A | 2025-11-06 | 222358.77 | 222358.77 | 23390444% | Remaining Total Cost | [16 empty] | 11545.66
|  |  | JDH3-02-008-C-11-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-01-15 | 2026-02-05 | 01-May-25 A | 2025-11-06 | 222358.77 | 222358.77 | 23390444% | Actual Total Cost | [10 empty] | 46780.89 |  |  | 11695.22 | 163036.6 | 846.06
|  |  | JDH3-02-008-C-11-(TSE)-Supply and install gate valves-100 mm |  | 2026-02-17 | 2026-02-21 | 2026-02-28 | 2026-03-04 | 0 | 0 | 129316% | Planned Total Cost | [19 empty] | 544.1 | 749.06
|  |  | JDH3-02-008-C-11-(TSE)-Supply and install gate valves-100 mm |  | 2026-02-17 | 2026-02-21 | 2026-02-28 | 2026-03-04 | 0 | 0 | 129316% | Remaining Total Cost | [19 empty] | 544.1 | 749.06
|  |  | JDH3-02-008-C-11-(TSE)-Supply and install gate valves-100 mm |  | 2026-02-17 | 2026-02-21 | 2026-02-28 | 2026-03-04 | 0 | 0 | 129316% | Actual Total Cost
|  |  | JDH3-02-008-C-11-(TSE)-Supply and install gate valves-250 mm |  | 2026-02-17 | 2026-02-21 | 2026-02-28 | 2026-03-04 | 0 | 0 | 2052891% | Planned Total Cost | [19 empty] | 8637.54 | 11891.37
|  |  | JDH3-02-008-C-11-(TSE)-Supply and install gate valves-250 mm |  | 2026-02-17 | 2026-02-21 | 2026-02-28 | 2026-03-04 | 0 | 0 | 2052891% | Remaining Total Cost | [19 empty] | 8637.54 | 11891.37
|  |  | JDH3-02-008-C-11-(TSE)-Supply and install gate valves-250 mm |  | 2026-02-17 | 2026-02-21 | 2026-02-28 | 2026-03-04 | 0 | 0 | 2052891% | Actual Total Cost
|  |  | JDH3-02-008-C-11-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2026-02-17 | 2026-02-21 | 2026-02-28 | 2026-03-04 | 0 | 0 | 2365815% | Planned Total Cost | [19 empty] | 9954.17 | 13703.98
|  |  | JDH3-02-008-C-11-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2026-02-17 | 2026-02-21 | 2026-02-28 | 2026-03-04 | 0 | 0 | 2365815% | Remaining Total Cost | [19 empty] | 9954.17 | 13703.98
|  |  | JDH3-02-008-C-11-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2026-02-17 | 2026-02-21 | 2026-02-28 | 2026-03-04 | 0 | 0 | 2365815% | Actual Total Cost
|  |  | JDH3-02-008-C-11-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-02-17 | 2026-02-21 | 2026-02-28 | 2026-03-04 | 0 | 0 | 3916758% | Planned Total Cost | [19 empty] | 16479.76 | 22687.82
|  |  | JDH3-02-008-C-11-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-02-17 | 2026-02-21 | 2026-02-28 | 2026-03-04 | 0 | 0 | 3916758% | Remaining Total Cost | [19 empty] | 16479.76 | 22687.82
|  |  | JDH3-02-008-C-11-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-02-17 | 2026-02-21 | 2026-02-28 | 2026-03-04 | 0 | 0 | 3916758% | Actual Total Cost
|  |  | JDH3-02-008-C-11-(TSE)-Supply and install of Wash-out valves-150 mm. |  | 2026-02-17 | 2026-02-21 | 2026-02-28 | 2026-03-04 | 0 | 0 | 1174858% | Planned Total Cost | [19 empty] | 4943.21 | 6805.36
|  |  | JDH3-02-008-C-11-(TSE)-Supply and install of Wash-out valves-150 mm. |  | 2026-02-17 | 2026-02-21 | 2026-02-28 | 2026-03-04 | 0 | 0 | 1174858% | Remaining Total Cost | [19 empty] | 4943.21 | 6805.36
|  |  | JDH3-02-008-C-11-(TSE)-Supply and install of Wash-out valves-150 mm. |  | 2026-02-17 | 2026-02-21 | 2026-02-28 | 2026-03-04 | 0 | 0 | 1174858% | Actual Total Cost
|  |  | JDH3-02-008-C-11-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-02-17 | 2026-02-21 | 2026-02-28 | 2026-03-04 | 0 | 0 | 2233241% | Planned Total Cost | [19 empty] | 9396.36 | 12936.05
|  |  | JDH3-02-008-C-11-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-02-17 | 2026-02-21 | 2026-02-28 | 2026-03-04 | 0 | 0 | 2233241% | Remaining Total Cost | [19 empty] | 9396.36 | 12936.05
|  |  | JDH3-02-008-C-11-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-02-17 | 2026-02-21 | 2026-02-28 | 2026-03-04 | 0 | 0 | 2233241% | Actual Total Cost
|  |  | JDH3-02-008-C-11-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-01-26 | 2026-02-23 | 2026-02-16 | 2026-03-07 | 0 | 0 | 910230% | Planned Total Cost | [19 empty] | 8192.07 | 910.23
|  |  | JDH3-02-008-C-11-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-01-26 | 2026-02-23 | 2026-02-16 | 2026-03-07 | 0 | 0 | 910230% | Remaining Total Cost | [19 empty] | 8192.07 | 910.23
|  |  | JDH3-02-008-C-11-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-01-26 | 2026-02-23 | 2026-02-16 | 2026-03-07 | 0 | 0 | 910230% | Actual Total Cost
|  |  | JDH3-02-008-C-11-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-01-28 | 2026-02-05 | 2026-02-18 | 2026-02-28 | 0 | 0 | 5540766% | Planned Total Cost | [19 empty] | 55407.66
|  |  | JDH3-02-008-C-11-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-01-28 | 2026-02-05 | 2026-02-18 | 2026-02-28 | 0 | 0 | 5540766% | Remaining Total Cost | [19 empty] | 55407.66
|  |  | JDH3-02-008-C-11-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-01-28 | 2026-02-05 | 2026-02-18 | 2026-02-28 | 0 | 0 | 5540766% | Actual Total Cost
|  |  | JDH3-02-008-C-11-(TSE)- Supply and Construct Wash-out Valves Chamber on 450-630 mm Diameter pipeline |  | 2026-01-03 | 2026-01-11 | 2026-02-16 | 2026-02-25 | 0 | 0 | 1879642% | Planned Total Cost | [19 empty] | 18796.42
|  |  | JDH3-02-008-C-11-(TSE)- Supply and Construct Wash-out Valves Chamber on 450-630 mm Diameter pipeline |  | 2026-01-03 | 2026-01-11 | 2026-02-16 | 2026-02-25 | 0 | 0 | 1879642% | Remaining Total Cost | [19 empty] | 18796.42
|  |  | JDH3-02-008-C-11-(TSE)- Supply and Construct Wash-out Valves Chamber on 450-630 mm Diameter pipeline |  | 2026-01-03 | 2026-01-11 | 2026-02-16 | 2026-02-25 | 0 | 0 | 1879642% | Actual Total Cost
|  |  | JDH3-02-008-C-11-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-01-03 | 2026-01-11 | 2026-02-16 | 2026-02-25 | 0 | 0 | 1043783% | Planned Total Cost | [19 empty] | 10437.83
|  |  | JDH3-02-008-C-11-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-01-03 | 2026-01-11 | 2026-02-16 | 2026-02-25 | 0 | 0 | 1043783% | Remaining Total Cost | [19 empty] | 10437.83
|  |  | JDH3-02-008-C-11-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-01-03 | 2026-01-11 | 2026-02-16 | 2026-02-25 | 0 | 0 | 1043783% | Actual Total Cost
|  |  | JDH3-02-008-C-11-Road Works - RD |  | 2026-01-29 | 2026-02-17 | 22-Nov-24 A | 2025-11-09 | 313991.61 | 313991.61 | 33199736% | Planned Total Cost | [16 empty] | 18005.75 |  | 41865.55 | 272126.07
|  |  | JDH3-02-008-C-11-Road Works - RD |  | 2026-01-29 | 2026-02-17 | 22-Nov-24 A | 2025-11-09 | 313991.61 | 313991.61 | 33199736% | Remaining Total Cost | [16 empty] | 18005.75
|  |  | JDH3-02-008-C-11-Road Works - RD |  | 2026-01-29 | 2026-02-17 | 22-Nov-24 A | 2025-11-09 | 313991.61 | 313991.61 | 33199736% | Actual Total Cost |  |  |  |  | 2289522% | 8831014% | 85039.39 | 78497.9 | 39248.95
|  |  | JDH3-02-008-C-11-(RD)-Precast Concrete Curb |  | 2026-01-29 | 2026-02-17 | 22-Nov-24 A | 2025-11-09 | 313991.61 | 313991.61 | 33199736% | Planned Total Cost | [16 empty] | 18005.75 |  | 41865.55 | 272126.07
|  |  | JDH3-02-008-C-11-(RD)-Precast Concrete Curb |  | 2026-01-29 | 2026-02-17 | 22-Nov-24 A | 2025-11-09 | 313991.61 | 313991.61 | 33199736% | Remaining Total Cost | [16 empty] | 18005.75
|  |  | JDH3-02-008-C-11-(RD)-Precast Concrete Curb |  | 2026-01-29 | 2026-02-17 | 22-Nov-24 A | 2025-11-09 | 313991.61 | 313991.61 | 33199736% | Actual Total Cost |  |  |  |  | 2289522% | 8831014% | 85039.39 | 78497.9 | 39248.95
|  |  | C-12 |  | 2026-03-15 | 2026-06-21 | 04-Mar-25 A | 2025-11-04 | 265202.73 | 265202.72 | 70821597% | Planned Total Cost | [14 empty] | 12488.61 | 97597.57 | 488.65 |  |  |  | 64966.87 | 389789.17 | 110771.29 | 32113.8
|  |  | C-12 |  | 2026-03-15 | 2026-06-21 | 04-Mar-25 A | 2025-11-04 | 265202.73 | 265202.72 | 70821597% | Remaining Total Cost | [15 empty] | 414674.65 | 28338.59
|  |  | C-12 |  | 2026-03-15 | 2026-06-21 | 04-Mar-25 A | 2025-11-04 | 265202.73 | 265202.72 | 70821597% | Actual Total Cost | [8 empty] | 36939.72 | 36476.52 | 29299.44 | 34889.44 | 22895.69 | 52096.31 | 50657.25 | 1948.36
|  |  | JDH3-02-008-C-12-Storm Network - ST |  | 2026-03-23 | 2026-05-13 | 14-Jun-25 A | 2025-11-02 | 2284-03-03 10:05 | 2284-03-03 10:19 | 48524445% | Planned Total Cost | [20 empty] | 64966.87 | 389789.17 | 30488.41
|  |  | JDH3-02-008-C-12-Storm Network - ST |  | 2026-03-23 | 2026-05-13 | 14-Jun-25 A | 2025-11-02 | 2284-03-03 10:05 | 2284-03-03 10:19 | 48524445% | Remaining Total Cost | [15 empty] | 317077.08 | 27849.94
|  |  | JDH3-02-008-C-12-Storm Network - ST |  | 2026-03-23 | 2026-05-13 | 14-Jun-25 A | 2025-11-02 | 2284-03-03 10:05 | 2284-03-03 10:19 | 48524445% | Actual Total Cost | [11 empty] | 12719.83 | 22895.69 | 52096.31 | 50657.25 | 1948.36
|  |  | JDH3-02-008-C-12-(ST)-Swales |  | 2026-03-23 | 2026-05-02 | 14-Jun-25 A | 2025-11-02 | 2250-02-07 16:48 | 2250-02-07 16:48 | 47280172% | Planned Total Cost | [20 empty] | 64966.87 | 389789.17 | 18045.68
|  |  | JDH3-02-008-C-12-(ST)-Swales |  | 2026-03-23 | 2026-05-02 | 14-Jun-25 A | 2025-11-02 | 2250-02-07 16:48 | 2250-02-07 16:48 | 47280172% | Remaining Total Cost | [15 empty] | 317077.08 | 27849.94
|  |  | JDH3-02-008-C-12-(ST)-Swales |  | 2026-03-23 | 2026-05-02 | 14-Jun-25 A | 2025-11-02 | 2250-02-07 16:48 | 2250-02-07 16:48 | 47280172% | Actual Total Cost | [11 empty] | 12719.83 | 22895.69 | 39653.58 | 50657.25 | 1948.36
|  |  | JDH3-02-008-C-12-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-05-03 | 2026-05-13 | 04-Aug-25 A | 31-Aug-25 A | 1934-01-23 17:31 | 1934-01-23 17:31 | 1244273% | Planned Total Cost | [22 empty] | 12442.73
|  |  | JDH3-02-008-C-12-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-05-03 | 2026-05-13 | 04-Aug-25 A | 31-Aug-25 A | 1934-01-23 17:31 | 1934-01-23 17:31 | 1244273% | Remaining Total Cost
|  |  | JDH3-02-008-C-12-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-05-03 | 2026-05-13 | 04-Aug-25 A | 31-Aug-25 A | 1934-01-23 17:31 | 1934-01-23 17:31 | 1244273% | Actual Total Cost | [13 empty] | 12442.73
|  |  | JDH3-02-008-C-12-TSE Network - TSE |  | 2026-05-14 | 2026-06-21 | 04-Mar-25 A | 2025-11-04 | 2241-12-02 07:12 | 2241-12-02 06:58 | 22297152% | Planned Total Cost | [14 empty] | 12488.61 | 97597.57 | 488.65 | [5 empty] | 80282.88 | 32113.8
|  |  | JDH3-02-008-C-12-TSE Network - TSE |  | 2026-05-14 | 2026-06-21 | 04-Mar-25 A | 2025-11-04 | 2241-12-02 07:12 | 2241-12-02 06:58 | 22297152% | Remaining Total Cost | [15 empty] | 97597.57 | 488.65
|  |  | JDH3-02-008-C-12-TSE Network - TSE |  | 2026-05-14 | 2026-06-21 | 04-Mar-25 A | 2025-11-04 | 2241-12-02 07:12 | 2241-12-02 06:58 | 22297152% | Actual Total Cost | [8 empty] | 36939.72 | 36476.52 | 29299.44 | 22169.61
|  |  | JDH3-02-008-C-12-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-05-14 | 2026-05-27 | 2025-10-14 | 2025-10-28 | 0 | 0 | 700043% | Planned Total Cost | [15 empty] | 7000.43
|  |  | JDH3-02-008-C-12-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-05-14 | 2026-05-27 | 2025-10-14 | 2025-10-28 | 0 | 0 | 700043% | Remaining Total Cost | [15 empty] | 7000.43
|  |  | JDH3-02-008-C-12-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-05-14 | 2026-05-27 | 2025-10-14 | 2025-10-28 | 0 | 0 | 700043% | Actual Total Cost
|  |  | JDH3-02-008-C-12-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-05-17 | 2026-06-16 | 04-Mar-25 A | 2025-10-30 | 2241-12-02 07:12 | 2241-12-02 06:58 | 14898986% | Planned Total Cost | [14 empty] | 12488.61 | 24104.56 | [6 empty] | 80282.88 | 32113.8
|  |  | JDH3-02-008-C-12-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-05-17 | 2026-06-16 | 04-Mar-25 A | 2025-10-30 | 2241-12-02 07:12 | 2241-12-02 06:58 | 14898986% | Remaining Total Cost | [15 empty] | 24104.56
|  |  | JDH3-02-008-C-12-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-05-17 | 2026-06-16 | 04-Mar-25 A | 2025-10-30 | 2241-12-02 07:12 | 2241-12-02 06:58 | 14898986% | Actual Total Cost | [8 empty] | 36939.72 | 36476.52 | 29299.44 | 22169.61
|  |  | JDH3-02-008-C-12-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-05-14 | 2026-06-18 | 2025-10-14 | 2025-11-02 | 0 | 0 | 241591% | Planned Total Cost | [15 empty] | 2275.18 | 140.73
|  |  | JDH3-02-008-C-12-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-05-14 | 2026-06-18 | 2025-10-14 | 2025-11-02 | 0 | 0 | 241591% | Remaining Total Cost | [15 empty] | 2275.18 | 140.73
|  |  | JDH3-02-008-C-12-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-05-14 | 2026-06-18 | 2025-10-14 | 2025-11-02 | 0 | 0 | 241591% | Actual Total Cost
|  |  | JDH3-02-008-C-12-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 0 to 1.5 m |  | 2026-05-14 | 2026-05-27 | 2025-10-14 | 2025-10-28 | 0 | 0 | 4848948% | Planned Total Cost | [15 empty] | 48489.48
|  |  | JDH3-02-008-C-12-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 0 to 1.5 m |  | 2026-05-14 | 2026-05-27 | 2025-10-14 | 2025-10-28 | 0 | 0 | 4848948% | Remaining Total Cost | [15 empty] | 48489.48
|  |  | JDH3-02-008-C-12-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 0 to 1.5 m |  | 2026-05-14 | 2026-05-27 | 2025-10-14 | 2025-10-28 | 0 | 0 | 4848948% | Actual Total Cost
|  |  | JDH3-02-008-C-12-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-21 | 2026-05-25 | 2025-10-21 | 2025-10-26 | 0 | 0 | 258632% | Planned Total Cost | [15 empty] | 2586.32
|  |  | JDH3-02-008-C-12-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-21 | 2026-05-25 | 2025-10-21 | 2025-10-26 | 0 | 0 | 258632% | Remaining Total Cost | [15 empty] | 2586.32
|  |  | JDH3-02-008-C-12-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-21 | 2026-05-25 | 2025-10-21 | 2025-10-26 | 0 | 0 | 258632% | Actual Total Cost
|  |  | JDH3-02-008-C-12-(TSE)-Supply and install gate valves-250 mm |  | 2026-05-21 | 2026-05-25 | 2025-10-21 | 2025-10-26 | 0 | 0 | 256611% | Planned Total Cost | [15 empty] | 2566.11
|  |  | JDH3-02-008-C-12-(TSE)-Supply and install gate valves-250 mm |  | 2026-05-21 | 2026-05-25 | 2025-10-21 | 2025-10-26 | 0 | 0 | 256611% | Remaining Total Cost | [15 empty] | 2566.11
|  |  | JDH3-02-008-C-12-(TSE)-Supply and install gate valves-250 mm |  | 2026-05-21 | 2026-05-25 | 2025-10-21 | 2025-10-26 | 0 | 0 | 256611% | Actual Total Cost
|  |  | JDH3-02-008-C-12-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-05-21 | 2026-05-25 | 2025-10-21 | 2025-10-26 | 0 | 0 | 744414% | Planned Total Cost | [15 empty] | 7444.14
|  |  | JDH3-02-008-C-12-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-05-21 | 2026-05-25 | 2025-10-21 | 2025-10-26 | 0 | 0 | 744414% | Remaining Total Cost | [15 empty] | 7444.14
|  |  | JDH3-02-008-C-12-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-05-21 | 2026-05-25 | 2025-10-21 | 2025-10-26 | 0 | 0 | 744414% | Actual Total Cost
|  |  | JDH3-02-008-C-12-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-05-14 | 2026-06-21 | 2025-10-14 | 2025-11-04 | 0 | 0 | 347928% | Planned Total Cost | [15 empty] | 3131.35 | 347.93
|  |  | JDH3-02-008-C-12-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-05-14 | 2026-06-21 | 2025-10-14 | 2025-11-04 | 0 | 0 | 347928% | Remaining Total Cost | [15 empty] | 3131.35 | 347.93
|  |  | JDH3-02-008-C-12-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-05-14 | 2026-06-21 | 2025-10-14 | 2025-11-04 | 0 | 0 | 347928% | Actual Total Cost
|  |  | C-13 |  | 2025-08-18 | 2026-03-18 | 05-Apr-25 A | 2026-03-14 | 1151405.48 | 1151405.5 | 255278608% | Planned Total Cost | [13 empty] | 41081.34 | 123244.02 | 467156.41 | 318863.19 | 250563.44 | 296960.46 | 1015521.94 | 39395.27
|  |  | C-13 |  | 2025-08-18 | 2026-03-18 | 05-Apr-25 A | 2026-03-14 | 1151405.48 | 1151405.5 | 255278608% | Remaining Total Cost | [16 empty] | 302408.03 | 250563.44 | 235244.53 | 595765.73 | 17398.87
|  |  | C-13 |  | 2025-08-18 | 2026-03-18 | 05-Apr-25 A | 2026-03-14 | 1151405.48 | 1151405.5 | 255278608% | Actual Total Cost | [9 empty] | 209871.51 | 252949.52 | 270229.68 | 220092.74 | 88640.98 | 108036.35 | 1584.72
|  |  | JDH3-02-008-C-13-Storm Network - ST |  | 2025-08-26 | 2026-02-10 | 15-Apr-25 A | 2026-02-21 | 678554.26 | 678554.26 | 176736431% | Planned Total Cost | [13 empty] | 41081.34 | 123244.02 | 467156.41 | 236713.81 | 250563.44 | 296960.46 | 351644.83
|  |  | JDH3-02-008-C-13-Storm Network - ST |  | 2025-08-26 | 2026-02-10 | 15-Apr-25 A | 2026-02-21 | 678554.26 | 678554.26 | 176736431% | Remaining Total Cost | [16 empty] | 266786.23 | 250563.44 | 235244.53 | 336215.84
|  |  | JDH3-02-008-C-13-Storm Network - ST |  | 2025-08-26 | 2026-02-10 | 15-Apr-25 A | 2026-02-21 | 678554.26 | 678554.26 | 176736431% | Actual Total Cost | [9 empty] | 24737.15 | 134356.54 | 210141.77 | 218224.15 | 82335.51 | 8434.73 | 324.41
|  |  | JDH3-02-008-C-13-(ST)-Swales |  | 2025-08-26 | 2025-11-13 | 15-Apr-25 A | 2025-11-25 | 601409.35 | 601409.35 | 80260312% | Planned Total Cost | [13 empty] | 41081.34 | 123244.02 | 467156.41 | 171121.35
|  |  | JDH3-02-008-C-13-(ST)-Swales |  | 2025-08-26 | 2025-11-13 | 15-Apr-25 A | 2025-11-25 | 601409.35 | 601409.35 | 80260312% | Remaining Total Cost | [16 empty] | 201193.77
|  |  | JDH3-02-008-C-13-(ST)-Swales |  | 2025-08-26 | 2025-11-13 | 15-Apr-25 A | 2025-11-25 | 601409.35 | 601409.35 | 80260312% | Actual Total Cost | [9 empty] | 24737.15 | 134356.54 | 210141.77 | 218224.15 | 5190.6 | 8434.73 | 324.41
|  |  | JDH3-02-008-C-13-(ST)-Box Culvert |  | 2025-11-15 | 2026-02-10 | 2025-11-24 | 2026-02-21 | 0 | 0 | 69659651% | Planned Total Cost | [16 empty] | 51628.99 | 231854.28 | 235244.53 | 177868.7
|  |  | JDH3-02-008-C-13-(ST)-Box Culvert |  | 2025-11-15 | 2026-02-10 | 2025-11-24 | 2026-02-21 | 0 | 0 | 69659651% | Remaining Total Cost | [16 empty] | 51628.99 | 231854.28 | 235244.53 | 177868.7
|  |  | JDH3-02-008-C-13-(ST)-Box Culvert |  | 2025-11-15 | 2026-02-10 | 2025-11-24 | 2026-02-21 | 0 | 0 | 69659651% | Actual Total Cost
|  |  | JDH3-02-008-C-13-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2025-11-15 | 2025-12-06 | 2025-11-24 | 2025-12-16 | 0 | 0 | 15984209% | Planned Total Cost | [16 empty] | 51628.99 | 108213.09
|  |  | JDH3-02-008-C-13-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2025-11-15 | 2025-12-06 | 2025-11-24 | 2025-12-16 | 0 | 0 | 15984209% | Remaining Total Cost | [16 empty] | 51628.99 | 108213.09
|  |  | JDH3-02-008-C-13-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2025-11-15 | 2025-12-06 | 2025-11-24 | 2025-12-16 | 0 | 0 | 15984209% | Actual Total Cost
|  |  | JDH3-02-008-C-13-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2025-12-07 | 2025-12-28 | 2025-12-16 | 2026-01-07 | 0 | 0 | 15344857% | Planned Total Cost | [17 empty] | 123641.19 | 29807.38
|  |  | JDH3-02-008-C-13-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2025-12-07 | 2025-12-28 | 2025-12-16 | 2026-01-07 | 0 | 0 | 15344857% | Remaining Total Cost | [17 empty] | 123641.19 | 29807.38
|  |  | JDH3-02-008-C-13-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2025-12-07 | 2025-12-28 | 2025-12-16 | 2026-01-07 | 0 | 0 | 15344857% | Actual Total Cost
|  |  | JDH3-02-008-C-13-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2025-12-29 | 2026-01-19 | 2026-01-07 | 2026-01-29 | 0 | 0 | 18736126% | Planned Total Cost | [18 empty] | 187361.26
|  |  | JDH3-02-008-C-13-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2025-12-29 | 2026-01-19 | 2026-01-07 | 2026-01-29 | 0 | 0 | 18736126% | Remaining Total Cost | [18 empty] | 187361.26
|  |  | JDH3-02-008-C-13-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2025-12-29 | 2026-01-19 | 2026-01-07 | 2026-01-29 | 0 | 0 | 18736126% | Actual Total Cost
|  |  | JDH3-02-008-C-13-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2026-01-20 | 2026-02-10 | 2026-01-29 | 2026-02-21 | 0 | 0 | 19594459% | Planned Total Cost | [18 empty] | 18075.89 | 177868.7
|  |  | JDH3-02-008-C-13-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2026-01-20 | 2026-02-10 | 2026-01-29 | 2026-02-21 | 0 | 0 | 19594459% | Remaining Total Cost | [18 empty] | 18075.89 | 177868.7
|  |  | JDH3-02-008-C-13-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2026-01-20 | 2026-02-10 | 2026-01-29 | 2026-02-21 | 0 | 0 | 19594459% | Actual Total Cost
|  |  | JDH3-02-008-C-13-(ST)-NetWork |  | 2026-01-22 | 2026-02-09 | 12-Aug-25 A | 2026-02-15 | 2111-03-18 21:50 | 2111-03-18 21:50 | 26816468% | Planned Total Cost | [16 empty] | 13963.46 | 18709.16 | 61715.93 | 173776.13
|  |  | JDH3-02-008-C-13-(ST)-NetWork |  | 2026-01-22 | 2026-02-09 | 12-Aug-25 A | 2026-02-15 | 2111-03-18 21:50 | 2111-03-18 21:50 | 26816468% | Remaining Total Cost | [16 empty] | 13963.46 | 18709.16 |  | 158347.14
|  |  | JDH3-02-008-C-13-(ST)-NetWork |  | 2026-01-22 | 2026-02-09 | 12-Aug-25 A | 2026-02-15 | 2111-03-18 21:50 | 2111-03-18 21:50 | 26816468% | Actual Total Cost | [13 empty] | 77144.91
|  |  | JDH3-02-008-C-13-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-01-22 | 2026-02-02 | 2026-02-01 | 2026-02-12 | 0 | 0 | 5666735% | Planned Total Cost | [19 empty] | 56667.35
|  |  | JDH3-02-008-C-13-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-01-22 | 2026-02-02 | 2026-02-01 | 2026-02-12 | 0 | 0 | 5666735% | Remaining Total Cost | [19 empty] | 56667.35
|  |  | JDH3-02-008-C-13-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-01-22 | 2026-02-02 | 2026-02-01 | 2026-02-12 | 0 | 0 | 5666735% | Actual Total Cost
|  |  | JDH3-02-008-C-13-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-01-25 | 2026-02-04 | 12-Aug-25 A | 30-Aug-25 A | 2111-03-18 21:50 | 2111-03-18 21:50 | 7714491% | Planned Total Cost | [18 empty] | 61715.93 | 15428.98
|  |  | JDH3-02-008-C-13-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-01-25 | 2026-02-04 | 12-Aug-25 A | 30-Aug-25 A | 2111-03-18 21:50 | 2111-03-18 21:50 | 7714491% | Remaining Total Cost
|  |  | JDH3-02-008-C-13-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-01-25 | 2026-02-04 | 12-Aug-25 A | 30-Aug-25 A | 2111-03-18 21:50 | 2111-03-18 21:50 | 7714491% | Actual Total Cost | [13 empty] | 77144.91
|  |  | JDH3-02-008-C-13-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-01-27 | 2026-02-07 | 2025-11-25 | 2025-12-07 | 0 | 0 | 3267262% | Planned Total Cost | [16 empty] | 13963.46 | 18709.16
|  |  | JDH3-02-008-C-13-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-01-27 | 2026-02-07 | 2025-11-25 | 2025-12-07 | 0 | 0 | 3267262% | Remaining Total Cost | [16 empty] | 13963.46 | 18709.16
|  |  | JDH3-02-008-C-13-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-01-27 | 2026-02-07 | 2025-11-25 | 2025-12-07 | 0 | 0 | 3267262% | Actual Total Cost
|  |  | JDH3-02-008-C-13-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2026-01-29 | 2026-02-09 | 2026-02-03 | 2026-02-15 | 0 | 0 | 1825022% | Planned Total Cost | [19 empty] | 18250.22
|  |  | JDH3-02-008-C-13-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2026-01-29 | 2026-02-09 | 2026-02-03 | 2026-02-15 | 0 | 0 | 1825022% | Remaining Total Cost | [19 empty] | 18250.22
|  |  | JDH3-02-008-C-13-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2026-01-29 | 2026-02-09 | 2026-02-03 | 2026-02-15 | 0 | 0 | 1825022% | Actual Total Cost
|  |  | JDH3-02-008-C-13-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-01-22 | 2026-02-02 | 2026-02-01 | 2026-02-12 | 0 | 0 | 6778653% | Planned Total Cost | [19 empty] | 67786.53
|  |  | JDH3-02-008-C-13-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-01-22 | 2026-02-02 | 2026-02-01 | 2026-02-12 | 0 | 0 | 6778653% | Remaining Total Cost | [19 empty] | 67786.53
|  |  | JDH3-02-008-C-13-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-01-22 | 2026-02-02 | 2026-02-01 | 2026-02-12 | 0 | 0 | 6778653% | Actual Total Cost
|  |  | JDH3-02-008-C-13-(ST)- Single Catchbasine Works |  | 2026-02-01 | 2026-02-09 | 2026-02-05 | 2026-02-15 | 0 | 0 | 1564305% | Planned Total Cost | [19 empty] | 15643.05
|  |  | JDH3-02-008-C-13-(ST)- Single Catchbasine Works |  | 2026-02-01 | 2026-02-09 | 2026-02-05 | 2026-02-15 | 0 | 0 | 1564305% | Remaining Total Cost | [19 empty] | 15643.05
|  |  | JDH3-02-008-C-13-(ST)- Single Catchbasine Works |  | 2026-02-01 | 2026-02-09 | 2026-02-05 | 2026-02-15 | 0 | 0 | 1564305% | Actual Total Cost
|  |  | JDH3-02-008-C-13-TSE Network - TSE |  | 2026-02-11 | 2026-03-09 | 05-Apr-25 A | 2026-03-04 | 472851.21 | 472851.24 | 77486069% | Planned Total Cost | [16 empty] | 82149.38 |  |  | 663877.12 | 28834.19
|  |  | JDH3-02-008-C-13-TSE Network - TSE |  | 2026-02-11 | 2026-03-09 | 05-Apr-25 A | 2026-03-04 | 472851.21 | 472851.24 | 77486069% | Remaining Total Cost | [16 empty] | 35621.8 |  |  | 259549.89 | 6837.79
|  |  | JDH3-02-008-C-13-TSE Network - TSE |  | 2026-02-11 | 2026-03-09 | 05-Apr-25 A | 2026-03-04 | 472851.21 | 472851.24 | 77486069% | Actual Total Cost | [9 empty] | 185134.36 | 118592.99 | 60087.9 | 1868.59 | 6305.47 | 99601.62 | 1260.31
|  |  | JDH3-02-008-C-13-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-02-11 | 2026-03-07 | 2026-02-21 | 2026-03-04 | 0 | 0 | 418742% | Planned Total Cost | [19 empty] | 3398.09 | 789.33
|  |  | JDH3-02-008-C-13-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-02-11 | 2026-03-07 | 2026-02-21 | 2026-03-04 | 0 | 0 | 418742% | Remaining Total Cost | [19 empty] | 3398.09 | 789.33
|  |  | JDH3-02-008-C-13-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-02-11 | 2026-03-07 | 2026-02-21 | 2026-03-04 | 0 | 0 | 418742% | Actual Total Cost
|  |  | JDH3-02-008-C-13-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-02-14 | 2026-03-02 | 05-Apr-25 A | 20-Sep-25 A | 228578.92 | 228578.93 | 22857892% | Planned Total Cost | [16 empty] | 22857.89 |  |  | 205494.16 | 226.87
|  |  | JDH3-02-008-C-13-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-02-14 | 2026-03-02 | 05-Apr-25 A | 20-Sep-25 A | 228578.92 | 228578.93 | 22857892% | Remaining Total Cost
|  |  | JDH3-02-008-C-13-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-02-14 | 2026-03-02 | 05-Apr-25 A | 20-Sep-25 A | 228578.92 | 228578.93 | 22857892% | Actual Total Cost | [9 empty] | 108254.25 | 70994.22 | 24450.79 | 497.93 | 1523.85 | 22857.89
|  |  | JDH3-02-008-C-13-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-02-16 | 2026-03-09 | 05-Apr-25 A | 2025-11-09 | 2417-06-01 11:46 | 2417-06-01 12:00 | 21769532% | Planned Total Cost | [16 empty] | 52380.52 |  |  | 143545.27 | 21769.53
|  |  | JDH3-02-008-C-13-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-02-16 | 2026-03-09 | 05-Apr-25 A | 2025-11-09 | 2417-06-01 11:46 | 2417-06-01 12:00 | 21769532% | Remaining Total Cost | [16 empty] | 28710.82
|  |  | JDH3-02-008-C-13-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-02-16 | 2026-03-09 | 05-Apr-25 A | 2025-11-09 | 2417-06-01 11:46 | 2417-06-01 12:00 | 21769532% | Actual Total Cost | [9 empty] | 76880.11 | 47598.77 | 35637.11 | 1370.66 | 174.3 | 26063.24 | 1260.31
|  |  | JDH3-02-008-C-13-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 0 to 1.5 m |  | 2026-02-11 | 2026-03-07 | 31-Aug-25 A | 2026-02-12 | 1910-12-24 13:12 | 1910-12-24 13:12 | 501444% | Planned Total Cost | [16 empty] | 501.44 |  |  | 4512.99
|  |  | JDH3-02-008-C-13-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 0 to 1.5 m |  | 2026-02-11 | 2026-03-07 | 31-Aug-25 A | 2026-02-12 | 1910-12-24 13:12 | 1910-12-24 13:12 | 501444% | Remaining Total Cost | [16 empty] | 501.44 |  |  | 501.44
|  |  | JDH3-02-008-C-13-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 0 to 1.5 m |  | 2026-02-11 | 2026-03-07 | 31-Aug-25 A | 2026-02-12 | 1910-12-24 13:12 | 1910-12-24 13:12 | 501444% | Actual Total Cost | [13 empty] | 334.3 | 3677.25
|  |  | JDH3-02-008-C-13-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 1.51 to 2.5 m |  | 2026-02-11 | 2026-03-07 | 31-Aug-25 A | 2026-02-12 | 2040-05-20 06:14 | 2040-05-20 06:14 | 6409532% | Planned Total Cost | [16 empty] | 6409.53 |  |  | 57685.79
|  |  | JDH3-02-008-C-13-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 1.51 to 2.5 m |  | 2026-02-11 | 2026-03-07 | 31-Aug-25 A | 2026-02-12 | 2040-05-20 06:14 | 2040-05-20 06:14 | 6409532% | Remaining Total Cost | [16 empty] | 6409.53 |  |  | 6409.53
|  |  | JDH3-02-008-C-13-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 1.51 to 2.5 m |  | 2026-02-11 | 2026-03-07 | 31-Aug-25 A | 2026-02-12 | 2040-05-20 06:14 | 2040-05-20 06:14 | 6409532% | Actual Total Cost | [13 empty] | 4273.02 | 47003.24
|  |  | JDH3-02-008-C-13-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2026-03-01 | 2026-03-04 | 2026-02-07 | 2026-02-10 | 0 | 0 | 14194889% | Planned Total Cost | [19 empty] | 141948.89
|  |  | JDH3-02-008-C-13-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2026-03-01 | 2026-03-04 | 2026-02-07 | 2026-02-10 | 0 | 0 | 14194889% | Remaining Total Cost | [19 empty] | 141948.89
|  |  | JDH3-02-008-C-13-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2026-03-01 | 2026-03-04 | 2026-02-07 | 2026-02-10 | 0 | 0 | 14194889% | Actual Total Cost
|  |  | JDH3-02-008-C-13-(TSE)-Supply and install of butterfly valves-600 mm. |  | 2026-03-01 | 2026-03-04 | 2026-02-07 | 2026-02-10 | 0 | 0 | 4657520% | Planned Total Cost | [19 empty] | 46575.2
|  |  | JDH3-02-008-C-13-(TSE)-Supply and install of butterfly valves-600 mm. |  | 2026-03-01 | 2026-03-04 | 2026-02-07 | 2026-02-10 | 0 | 0 | 4657520% | Remaining Total Cost | [19 empty] | 46575.2
|  |  | JDH3-02-008-C-13-(TSE)-Supply and install of butterfly valves-600 mm. |  | 2026-03-01 | 2026-03-04 | 2026-02-07 | 2026-02-10 | 0 | 0 | 4657520% | Actual Total Cost
|  |  | JDH3-02-008-C-13-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-02-11 | 2026-02-19 | 2026-02-21 | 2026-03-02 | 0 | 0 | 5461379% | Planned Total Cost | [19 empty] | 49780.47 | 4833.32
|  |  | JDH3-02-008-C-13-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-02-11 | 2026-02-19 | 2026-02-21 | 2026-03-02 | 0 | 0 | 5461379% | Remaining Total Cost | [19 empty] | 49780.47 | 4833.32
|  |  | JDH3-02-008-C-13-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-02-11 | 2026-02-19 | 2026-02-21 | 2026-03-02 | 0 | 0 | 5461379% | Actual Total Cost
|  |  | JDH3-02-008-C-13-(TSE)- Supply and Construct R.C Valves Chamber on 500-630 mm Diameter pipelines |  | 2026-02-11 | 2026-02-22 | 2026-02-21 | 2026-03-04 | 0 | 0 | 1215139% | Planned Total Cost | [19 empty] | 10936.25 | 1215.14
|  |  | JDH3-02-008-C-13-(TSE)- Supply and Construct R.C Valves Chamber on 500-630 mm Diameter pipelines |  | 2026-02-11 | 2026-02-22 | 2026-02-21 | 2026-03-04 | 0 | 0 | 1215139% | Remaining Total Cost | [19 empty] | 10936.25 | 1215.14
|  |  | JDH3-02-008-C-13-(TSE)- Supply and Construct R.C Valves Chamber on 500-630 mm Diameter pipelines |  | 2026-02-11 | 2026-02-22 | 2026-02-21 | 2026-03-04 | 0 | 0 | 1215139% | Actual Total Cost
|  |  | JDH3-02-008-C-13-Street Lighting Network -SL |  | 2026-03-10 | 2026-03-18 | 2026-03-04 | 2026-03-14 | 0 | 0 | 1056108% | Planned Total Cost | [20 empty] | 10561.08
|  |  | JDH3-02-008-C-13-Street Lighting Network -SL |  | 2026-03-10 | 2026-03-18 | 2026-03-04 | 2026-03-14 | 0 | 0 | 1056108% | Remaining Total Cost | [20 empty] | 10561.08
|  |  | JDH3-02-008-C-13-Street Lighting Network -SL |  | 2026-03-10 | 2026-03-18 | 2026-03-04 | 2026-03-14 | 0 | 0 | 1056108% | Actual Total Cost
|  |  | JDH3-02-008-C-13-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-2 × 150 mm |  | 2026-03-10 | 2026-03-18 | 2026-03-04 | 2026-03-14 | 0 | 0 | 229960% | Planned Total Cost | [20 empty] | 2299.6
|  |  | JDH3-02-008-C-13-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-2 × 150 mm |  | 2026-03-10 | 2026-03-18 | 2026-03-04 | 2026-03-14 | 0 | 0 | 229960% | Remaining Total Cost | [20 empty] | 2299.6
|  |  | JDH3-02-008-C-13-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-2 × 150 mm |  | 2026-03-10 | 2026-03-18 | 2026-03-04 | 2026-03-14 | 0 | 0 | 229960% | Actual Total Cost
|  |  | JDH3-02-008-C-13-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2026-03-10 | 2026-03-16 | 2026-03-04 | 2026-03-11 | 0 | 0 | 826148% | Planned Total Cost | [20 empty] | 8261.48
|  |  | JDH3-02-008-C-13-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2026-03-10 | 2026-03-16 | 2026-03-04 | 2026-03-11 | 0 | 0 | 826148% | Remaining Total Cost | [20 empty] | 8261.48
|  |  | JDH3-02-008-C-13-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2026-03-10 | 2026-03-16 | 2026-03-04 | 2026-03-11 | 0 | 0 | 826148% | Actual Total Cost
|  |  | C-14 |  | 2026-01-12 | 2026-05-25 | 05-Apr-25 A | 2026-02-10 | 1527867.45 | 1527867.46 | 285043844% | Planned Total Cost | [16 empty] | 188044.36 | 619781.77 | 141176.68 | 577459.84 | 594950.62 | 213621.77 | 515403.39
|  |  | C-14 |  | 2026-01-12 | 2026-05-25 | 05-Apr-25 A | 2026-02-10 | 1527867.45 | 1527867.46 | 285043844% | Remaining Total Cost | [16 empty] | 504234.57 | 619781.77 | 58829.02 | 139725.61
|  |  | C-14 |  | 2026-01-12 | 2026-05-25 | 05-Apr-25 A | 2026-02-10 | 1527867.45 | 1527867.46 | 285043844% | Actual Total Cost | [9 empty] | 191168.93 | 178875.72 | 228216.82 | 336691.49 | 432458.08 | 154571.83 | 5884.59
|  |  | JDH3-02-008-C-14-Storm Network - ST |  | 2026-01-20 | 2026-04-28 | 19-Apr-25 A | 2025-12-29 | 996975.54 | 996975.55 | 211027936% | Planned Total Cost | [16 empty] | 186471.84 | 609069.24 | 82347.65 | 437734.23 | 594950.62 | 199705.78
|  |  | JDH3-02-008-C-14-Storm Network - ST |  | 2026-01-20 | 2026-04-28 | 19-Apr-25 A | 2025-12-29 | 996975.54 | 996975.55 | 211027936% | Remaining Total Cost | [16 empty] | 504234.57 | 609069.24
|  |  | JDH3-02-008-C-14-Storm Network - ST |  | 2026-01-20 | 2026-04-28 | 19-Apr-25 A | 2025-12-29 | 996975.54 | 996975.55 | 211027936% | Actual Total Cost | [9 empty] | 19122.95 | 45199.71 | 123627.72 | 282222.2 | 367919.06 | 152999.31 | 5884.59
|  |  | JDH3-02-008-C-14-(ST)-Swales |  | 2026-01-20 | 2026-03-24 | 19-Apr-25 A | 2025-11-24 | 730701.18 | 730701.18 | 104846391% | Planned Total Cost | [18 empty] | 82347.65 | 437734.23 | 528382.03
|  |  | JDH3-02-008-C-14-(ST)-Swales |  | 2026-01-20 | 2026-03-24 | 19-Apr-25 A | 2025-11-24 | 730701.18 | 730701.18 | 104846391% | Remaining Total Cost | [16 empty] | 317762.73
|  |  | JDH3-02-008-C-14-(ST)-Swales |  | 2026-01-20 | 2026-03-24 | 19-Apr-25 A | 2025-11-24 | 730701.18 | 730701.18 | 104846391% | Actual Total Cost | [9 empty] | 19122.95 | 45199.71 | 123627.72 | 282222.2 | 101644.69 | 152999.31 | 5884.59
|  |  | JDH3-02-008-C-14-(ST)-Box Culvert |  | 2026-03-25 | 2026-04-28 | 2025-11-24 | 2025-12-29 | 0 | 0 | 68995053% | Planned Total Cost | [16 empty] | 157527.32 | 532423.21
|  |  | JDH3-02-008-C-14-(ST)-Box Culvert |  | 2026-03-25 | 2026-04-28 | 2025-11-24 | 2025-12-29 | 0 | 0 | 68995053% | Remaining Total Cost | [16 empty] | 157527.32 | 532423.21
|  |  | JDH3-02-008-C-14-(ST)-Box Culvert |  | 2026-03-25 | 2026-04-28 | 2025-11-24 | 2025-12-29 | 0 | 0 | 68995053% | Actual Total Cost
|  |  | JDH3-02-008-C-14-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2026-03-25 | 2026-04-26 | 2025-11-24 | 2025-12-27 | 0 | 0 | 35270026% | Planned Total Cost | [16 empty] | 96569.33 | 256130.93
|  |  | JDH3-02-008-C-14-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2026-03-25 | 2026-04-26 | 2025-11-24 | 2025-12-27 | 0 | 0 | 35270026% | Remaining Total Cost | [16 empty] | 96569.33 | 256130.93
|  |  | JDH3-02-008-C-14-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2026-03-25 | 2026-04-26 | 2025-11-24 | 2025-12-27 | 0 | 0 | 35270026% | Actual Total Cost
|  |  | JDH3-02-008-C-14-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2026-03-28 | 2026-04-28 | 2025-11-26 | 2025-12-29 | 0 | 0 | 33725027% | Planned Total Cost | [16 empty] | 60957.99 | 276292.28
|  |  | JDH3-02-008-C-14-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2026-03-28 | 2026-04-28 | 2025-11-26 | 2025-12-29 | 0 | 0 | 33725027% | Remaining Total Cost | [16 empty] | 60957.99 | 276292.28
|  |  | JDH3-02-008-C-14-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2026-03-28 | 2026-04-28 | 2025-11-26 | 2025-12-29 | 0 | 0 | 33725027% | Actual Total Cost
|  |  | JDH3-02-008-C-14-(ST)-NetWork |  | 2026-03-28 | 2026-04-22 | 11-Aug-25 A | 2025-12-10 | 266274.37 | 266274.37 | 37186491% | Planned Total Cost | [16 empty] | 28944.52 | 76646.03 |  |  | 66568.59 | 199705.78
|  |  | JDH3-02-008-C-14-(ST)-NetWork |  | 2026-03-28 | 2026-04-22 | 11-Aug-25 A | 2025-12-10 | 266274.37 | 266274.37 | 37186491% | Remaining Total Cost | [16 empty] | 28944.52 | 76646.03
|  |  | JDH3-02-008-C-14-(ST)-NetWork |  | 2026-03-28 | 2026-04-22 | 11-Aug-25 A | 2025-12-10 | 266274.37 | 266274.37 | 37186491% | Actual Total Cost | [13 empty] | 266274.37
|  |  | JDH3-02-008-C-14-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-03-28 | 2026-04-08 | 11-Aug-25 A | 30-Aug-25 A | 266274.37 | 266274.37 | 26627437% | Planned Total Cost | [20 empty] | 66568.59 | 199705.78
|  |  | JDH3-02-008-C-14-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-03-28 | 2026-04-08 | 11-Aug-25 A | 30-Aug-25 A | 266274.37 | 266274.37 | 26627437% | Remaining Total Cost
|  |  | JDH3-02-008-C-14-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-03-28 | 2026-04-08 | 11-Aug-25 A | 30-Aug-25 A | 266274.37 | 266274.37 | 26627437% | Actual Total Cost | [13 empty] | 266274.37
|  |  | JDH3-02-008-C-14-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-04-09 | 2026-04-20 | 2025-11-26 | 2025-12-08 | 0 | 0 | 5083989% | Planned Total Cost | [16 empty] | 20526.61 | 30313.29
|  |  | JDH3-02-008-C-14-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-04-09 | 2026-04-20 | 2025-11-26 | 2025-12-08 | 0 | 0 | 5083989% | Remaining Total Cost | [16 empty] | 20526.61 | 30313.29
|  |  | JDH3-02-008-C-14-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-04-09 | 2026-04-20 | 2025-11-26 | 2025-12-08 | 0 | 0 | 5083989% | Actual Total Cost
|  |  | JDH3-02-008-C-14-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2026-04-12 | 2026-04-22 | 2025-11-29 | 2025-12-10 | 0 | 0 | 5475065% | Planned Total Cost | [16 empty] | 8417.91 | 46332.74
|  |  | JDH3-02-008-C-14-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2026-04-12 | 2026-04-22 | 2025-11-29 | 2025-12-10 | 0 | 0 | 5475065% | Remaining Total Cost | [16 empty] | 8417.91 | 46332.74
|  |  | JDH3-02-008-C-14-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2026-04-12 | 2026-04-22 | 2025-11-29 | 2025-12-10 | 0 | 0 | 5475065% | Actual Total Cost
|  |  | JDH3-02-008-C-14-TSE Network - TSE |  | 2026-04-29 | 2026-05-25 | 05-Apr-25 A | 2026-02-10 | 530891.91 | 530891.91 | 74015908% | Planned Total Cost | [16 empty] | 1572.52 | 10712.53 | 58829.02 | 139725.61 |  | 13916 | 515403.39
|  |  | JDH3-02-008-C-14-TSE Network - TSE |  | 2026-04-29 | 2026-05-25 | 05-Apr-25 A | 2026-02-10 | 530891.91 | 530891.91 | 74015908% | Remaining Total Cost | [17 empty] | 10712.53 | 58829.02 | 139725.61
|  |  | JDH3-02-008-C-14-TSE Network - TSE |  | 2026-04-29 | 2026-05-25 | 05-Apr-25 A | 2026-02-10 | 530891.91 | 530891.91 | 74015908% | Actual Total Cost | [9 empty] | 172045.97 | 133676.01 | 104589.1 | 54469.29 | 64539.02 | 1572.52
|  |  | JDH3-02-008-C-14-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-04-29 | 2026-05-20 | 2025-12-29 | 2026-01-12 | 0 | 0 | 1101634% | Planned Total Cost | [17 empty] | 2266.61 | 8749.73
|  |  | JDH3-02-008-C-14-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-04-29 | 2026-05-20 | 2025-12-29 | 2026-01-12 | 0 | 0 | 1101634% | Remaining Total Cost | [17 empty] | 2266.61 | 8749.73
|  |  | JDH3-02-008-C-14-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-04-29 | 2026-05-20 | 2025-12-29 | 2026-01-12 | 0 | 0 | 1101634% | Actual Total Cost
|  |  | JDH3-02-008-C-14-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 0 to 1.5 m |  | 2026-04-29 | 2026-05-23 | 29-Jul-25 A | 13-Aug-25 A | 2090-06-30 23:31 | 2090-06-30 23:46 | 6957998% | Planned Total Cost | [21 empty] | 13916 | 55663.98
|  |  | JDH3-02-008-C-14-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 0 to 1.5 m |  | 2026-04-29 | 2026-05-23 | 29-Jul-25 A | 13-Aug-25 A | 2090-06-30 23:31 | 2090-06-30 23:46 | 6957998% | Remaining Total Cost
|  |  | JDH3-02-008-C-14-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 0 to 1.5 m |  | 2026-04-29 | 2026-05-23 | 29-Jul-25 A | 13-Aug-25 A | 2090-06-30 23:31 | 2090-06-30 23:46 | 6957998% | Actual Total Cost | [12 empty] | 15655.5 | 53924.49
|  |  | JDH3-02-008-C-14-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 1.51 to 2.5 m |  | 2026-05-02 | 2026-05-20 | 05-Apr-25 A | 28-Jul-25 A | 445586.7 | 445586.69 | 44558670% | Planned Total Cost | [22 empty] | 445586.7
|  |  | JDH3-02-008-C-14-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 1.51 to 2.5 m |  | 2026-05-02 | 2026-05-20 | 05-Apr-25 A | 28-Jul-25 A | 445586.7 | 445586.69 | 44558670% | Remaining Total Cost
|  |  | JDH3-02-008-C-14-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 1.51 to 2.5 m |  | 2026-05-02 | 2026-05-20 | 05-Apr-25 A | 28-Jul-25 A | 445586.7 | 445586.69 | 44558670% | Actual Total Cost | [9 empty] | 172045.97 | 133676.01 | 104589.1 | 35275.61
|  |  | JDH3-02-008-C-14-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 2.51 to 3.5 m |  | 2026-05-05 | 2026-05-20 | 29-Jul-25 A | 09-Sep-25 A | 1943-01-19 05:46 | 1943-01-19 05:31 | 1572524% | Planned Total Cost | [16 empty] | 1572.52 | [5 empty] | 14152.71
|  |  | JDH3-02-008-C-14-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 2.51 to 3.5 m |  | 2026-05-05 | 2026-05-20 | 29-Jul-25 A | 09-Sep-25 A | 1943-01-19 05:46 | 1943-01-19 05:31 | 1572524% | Remaining Total Cost
|  |  | JDH3-02-008-C-14-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 2.51 to 3.5 m |  | 2026-05-05 | 2026-05-20 | 29-Jul-25 A | 09-Sep-25 A | 1943-01-19 05:46 | 1943-01-19 05:31 | 1572524% | Actual Total Cost | [12 empty] | 3538.18 | 10614.53 | 1572.52
|  |  | JDH3-02-008-C-14-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-14 | 2026-05-18 | 2026-01-05 | 2026-01-10 | 0 | 0 | 1034528% | Planned Total Cost | [18 empty] | 10345.28
|  |  | JDH3-02-008-C-14-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-14 | 2026-05-18 | 2026-01-05 | 2026-01-10 | 0 | 0 | 1034528% | Remaining Total Cost | [18 empty] | 10345.28
|  |  | JDH3-02-008-C-14-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-14 | 2026-05-18 | 2026-01-05 | 2026-01-10 | 0 | 0 | 1034528% | Actual Total Cost
|  |  | JDH3-02-008-C-14-(TSE)-Supply and install of butterfly valves-600 mm. |  | 2026-05-14 | 2026-05-18 | 2026-02-07 | 2026-02-10 | 0 | 0 | 13972561% | Planned Total Cost | [19 empty] | 139725.61
|  |  | JDH3-02-008-C-14-(TSE)-Supply and install of butterfly valves-600 mm. |  | 2026-05-14 | 2026-05-18 | 2026-02-07 | 2026-02-10 | 0 | 0 | 13972561% | Remaining Total Cost | [19 empty] | 139725.61
|  |  | JDH3-02-008-C-14-(TSE)-Supply and install of butterfly valves-600 mm. |  | 2026-05-14 | 2026-05-18 | 2026-02-07 | 2026-02-10 | 0 | 0 | 13972561% | Actual Total Cost
|  |  | JDH3-02-008-C-14-(TSE)-Supply and install of Air valves-65 mm. |  | 2026-05-14 | 2026-05-18 | 2026-01-05 | 2026-01-10 | 0 | 0 | 824649% | Planned Total Cost | [18 empty] | 8246.49
|  |  | JDH3-02-008-C-14-(TSE)-Supply and install of Air valves-65 mm. |  | 2026-05-14 | 2026-05-18 | 2026-01-05 | 2026-01-10 | 0 | 0 | 824649% | Remaining Total Cost | [18 empty] | 8246.49
|  |  | JDH3-02-008-C-14-(TSE)-Supply and install of Air valves-65 mm. |  | 2026-05-14 | 2026-05-18 | 2026-01-05 | 2026-01-10 | 0 | 0 | 824649% | Actual Total Cost
|  |  | JDH3-02-008-C-14-(TSE)- Supply and Construct R.C Valves Chamber on 500-630 mm Diameter pipelines |  | 2026-04-29 | 2026-05-07 | 2025-12-29 | 2026-01-07 | 0 | 0 | 3645416% | Planned Total Cost | [17 empty] | 7710.06 | 28744.11
|  |  | JDH3-02-008-C-14-(TSE)- Supply and Construct R.C Valves Chamber on 500-630 mm Diameter pipelines |  | 2026-04-29 | 2026-05-07 | 2025-12-29 | 2026-01-07 | 0 | 0 | 3645416% | Remaining Total Cost | [17 empty] | 7710.06 | 28744.11
|  |  | JDH3-02-008-C-14-(TSE)- Supply and Construct R.C Valves Chamber on 500-630 mm Diameter pipelines |  | 2026-04-29 | 2026-05-07 | 2025-12-29 | 2026-01-07 | 0 | 0 | 3645416% | Actual Total Cost
|  |  | JDH3-02-008-C-14-(TSE)- Supply and Construct Air Valves Chamber on 355-630 mm Diameter pipelines |  | 2026-04-29 | 2026-05-25 | 2025-12-29 | 2026-01-10 | 0 | 0 | 347928% | Planned Total Cost | [17 empty] | 735.87 | 2743.41
|  |  | JDH3-02-008-C-14-(TSE)- Supply and Construct Air Valves Chamber on 355-630 mm Diameter pipelines |  | 2026-04-29 | 2026-05-25 | 2025-12-29 | 2026-01-10 | 0 | 0 | 347928% | Remaining Total Cost | [17 empty] | 735.87 | 2743.41
|  |  | JDH3-02-008-C-14-(TSE)- Supply and Construct Air Valves Chamber on 355-630 mm Diameter pipelines |  | 2026-04-29 | 2026-05-25 | 2025-12-29 | 2026-01-10 | 0 | 0 | 347928% | Actual Total Cost
|  |  | C-15 |  | 2026-02-25 | 2026-07-05 | 01-Jul-25 A | 2026-03-05 | 793600.63 | 793600.65 | 141876650% | Planned Total Cost | [16 empty] | 407048.66 | 203945.83 |  | 241564.39 | 60843.3 | 353435.67 | 138595.98 | 13332.68
|  |  | C-15 |  | 2026-02-25 | 2026-07-05 | 01-Jul-25 A | 2026-03-05 | 793600.63 | 793600.65 | 141876650% | Remaining Total Cost | [16 empty] | 326920.23 | 172729.96 |  | 108984.77 | 16530.9
|  |  | C-15 |  | 2026-02-25 | 2026-07-05 | 01-Jul-25 A | 2026-03-05 | 793600.63 | 793600.65 | 141876650% | Actual Total Cost | [12 empty] | 72193 | 404536.99 | 301904.86 | 14965.79
|  |  | JDH3-02-008-C-15-Storm Network - ST |  | 2026-03-09 | 2026-05-04 | 22-Jul-25 A | 2025-12-02 | 538758.51 | 538758.51 | 79249117% | Planned Total Cost | [16 empty] | 341506.83 | 34634.39 |  |  | 44312.4 | 353435.67 | 18601.88
|  |  | JDH3-02-008-C-15-Storm Network - ST |  | 2026-03-09 | 2026-05-04 | 22-Jul-25 A | 2025-12-02 | 538758.51 | 538758.51 | 79249117% | Remaining Total Cost | [16 empty] | 250314.14 | 3418.52
|  |  | JDH3-02-008-C-15-Storm Network - ST |  | 2026-03-09 | 2026-05-04 | 22-Jul-25 A | 2025-12-02 | 538758.51 | 538758.51 | 79249117% | Actual Total Cost | [12 empty] | 72193 | 271210.2 | 184393.72 | 10961.58
|  |  | JDH3-02-008-C-15-(ST)-Swales |  | 2026-03-09 | 2026-04-12 | 10-Aug-25 A | 2025-11-17 | 2438-10-14 00:43 | 2438-10-14 00:43 | 20853063% | Planned Total Cost | [16 empty] | 133002.36 | 31215.87 |  |  | 44312.4
|  |  | JDH3-02-008-C-15-(ST)-Swales |  | 2026-03-09 | 2026-04-12 | 10-Aug-25 A | 2025-11-17 | 2438-10-14 00:43 | 2438-10-14 00:43 | 20853063% | Remaining Total Cost | [16 empty] | 11741.6
|  |  | JDH3-02-008-C-15-(ST)-Swales |  | 2026-03-09 | 2026-04-12 | 10-Aug-25 A | 2025-11-17 | 2438-10-14 00:43 | 2438-10-14 00:43 | 20853063% | Actual Total Cost | [13 empty] | 40092.17 | 147167.07 | 9529.79
|  |  | JDH3-02-008-C-15-(ST)-Network |  | 2026-04-13 | 2026-05-04 | 22-Jul-25 A | 2025-12-02 | 341969.48 | 341969.48 | 58396054% | Planned Total Cost | [16 empty] | 208504.47 | 3418.52 |  |  |  | 353435.67 | 18601.88
|  |  | JDH3-02-008-C-15-(ST)-Network |  | 2026-04-13 | 2026-05-04 | 22-Jul-25 A | 2025-12-02 | 341969.48 | 341969.48 | 58396054% | Remaining Total Cost | [16 empty] | 238572.54 | 3418.52
|  |  | JDH3-02-008-C-15-(ST)-Network |  | 2026-04-13 | 2026-05-04 | 22-Jul-25 A | 2025-12-02 | 341969.48 | 341969.48 | 58396054% | Actual Total Cost | [12 empty] | 72193 | 231118.03 | 37226.65 | 1431.79
|  |  | JDH3-02-008-C-15-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-04-23 | 2026-05-04 | 2025-11-20 | 2025-12-02 | 0 | 0 | 6159494% | Planned Total Cost | [16 empty] | 58176.42 | 3418.52
|  |  | JDH3-02-008-C-15-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-04-23 | 2026-05-04 | 2025-11-20 | 2025-12-02 | 0 | 0 | 6159494% | Remaining Total Cost | [16 empty] | 58176.42 | 3418.52
|  |  | JDH3-02-008-C-15-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-04-23 | 2026-05-04 | 2025-11-20 | 2025-12-02 | 0 | 0 | 6159494% | Actual Total Cost
|  |  | JDH3-02-008-C-15-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-04-13 | 2026-04-23 | 2025-11-17 | 2025-11-29 | 0 | 0 | 6429129% | Planned Total Cost | [16 empty] | 64291.29
|  |  | JDH3-02-008-C-15-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-04-13 | 2026-04-23 | 2025-11-17 | 2025-11-29 | 0 | 0 | 6429129% | Remaining Total Cost | [16 empty] | 64291.29
|  |  | JDH3-02-008-C-15-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-04-13 | 2026-04-23 | 2025-11-17 | 2025-11-29 | 0 | 0 | 6429129% | Actual Total Cost
|  |  | JDH3-02-008-C-15-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-04-15 | 2026-05-03 | 22-Jul-25 A | 2025-11-17 | 341969.48 | 341969.48 | 37203755% | Planned Total Cost | [21 empty] | 353435.67 | 18601.88
|  |  | JDH3-02-008-C-15-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-04-15 | 2026-05-03 | 22-Jul-25 A | 2025-11-17 | 341969.48 | 341969.48 | 37203755% | Remaining Total Cost | [16 empty] | 30068.07
|  |  | JDH3-02-008-C-15-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-04-15 | 2026-05-03 | 22-Jul-25 A | 2025-11-17 | 341969.48 | 341969.48 | 37203755% | Actual Total Cost | [12 empty] | 72193 | 231118.03 | 37226.65 | 1431.79
|  |  | JDH3-02-008-C-15-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2026-04-19 | 2026-04-29 | 2025-11-16 | 2025-11-27 | 0 | 0 | 5475065% | Planned Total Cost | [16 empty] | 54750.65
|  |  | JDH3-02-008-C-15-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2026-04-19 | 2026-04-29 | 2025-11-16 | 2025-11-27 | 0 | 0 | 5475065% | Remaining Total Cost | [16 empty] | 54750.65
|  |  | JDH3-02-008-C-15-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2026-04-19 | 2026-04-29 | 2025-11-16 | 2025-11-27 | 0 | 0 | 5475065% | Actual Total Cost
|  |  | JDH3-02-008-C-15-(ST)- Single Catchbasine Works |  | 2026-04-21 | 2026-04-29 | 2025-11-18 | 2025-11-27 | 0 | 0 | 3128611% | Planned Total Cost | [16 empty] | 31286.11
|  |  | JDH3-02-008-C-15-(ST)- Single Catchbasine Works |  | 2026-04-21 | 2026-04-29 | 2025-11-18 | 2025-11-27 | 0 | 0 | 3128611% | Remaining Total Cost | [16 empty] | 31286.11
|  |  | JDH3-02-008-C-15-(ST)- Single Catchbasine Works |  | 2026-04-21 | 2026-04-29 | 2025-11-18 | 2025-11-27 | 0 | 0 | 3128611% | Actual Total Cost
|  |  | JDH3-02-008-C-15-TSE Network - TSE |  | 2026-05-05 | 2026-06-06 | 02-Aug-25 A | 2026-02-15 | 2265-01-11 18:43 | 2265-01-11 18:58 | 38394028% | Planned Total Cost | [17 empty] | 169311.44 |  | 81302.07 |  |  | 119994.1 | 13332.68
|  |  | JDH3-02-008-C-15-TSE Network - TSE |  | 2026-05-05 | 2026-06-06 | 02-Aug-25 A | 2026-02-15 | 2265-01-11 18:43 | 2265-01-11 18:58 | 38394028% | Remaining Total Cost | [17 empty] | 169311.44 |  | 81302.07
|  |  | JDH3-02-008-C-15-TSE Network - TSE |  | 2026-05-05 | 2026-06-06 | 02-Aug-25 A | 2026-02-15 | 2265-01-11 18:43 | 2265-01-11 18:58 | 38394028% | Actual Total Cost | [13 empty] | 133326.79
|  |  | JDH3-02-008-C-15-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-05-05 | 2026-06-06 | 02-Aug-25 A | 31-Aug-25 A | 2265-01-11 18:43 | 2265-01-11 18:58 | 13332678% | Planned Total Cost | [22 empty] | 119994.1 | 13332.68
|  |  | JDH3-02-008-C-15-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-05-05 | 2026-06-06 | 02-Aug-25 A | 31-Aug-25 A | 2265-01-11 18:43 | 2265-01-11 18:58 | 13332678% | Remaining Total Cost
|  |  | JDH3-02-008-C-15-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-05-05 | 2026-06-06 | 02-Aug-25 A | 31-Aug-25 A | 2265-01-11 18:43 | 2265-01-11 18:58 | 13332678% | Actual Total Cost | [13 empty] | 133326.79
|  |  | JDH3-02-008-C-15-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-05-10 | 2026-05-31 | 2025-12-02 | 2026-02-12 | 0 | 0 | 4330733% | Planned Total Cost | [17 empty] | 38976.6 |  | 4330.73
|  |  | JDH3-02-008-C-15-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-05-10 | 2026-05-31 | 2025-12-02 | 2026-02-12 | 0 | 0 | 4330733% | Remaining Total Cost | [17 empty] | 38976.6 |  | 4330.73
|  |  | JDH3-02-008-C-15-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-05-10 | 2026-05-31 | 2025-12-02 | 2026-02-12 | 0 | 0 | 4330733% | Actual Total Cost
|  |  | JDH3-02-008-C-15-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-05-12 | 2026-05-28 | 2025-12-04 | 2026-02-15 | 0 | 0 | 5648961% | Planned Total Cost | [17 empty] | 50840.65 |  | 5648.96
|  |  | JDH3-02-008-C-15-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-05-12 | 2026-05-28 | 2025-12-04 | 2026-02-15 | 0 | 0 | 5648961% | Remaining Total Cost | [17 empty] | 50840.65 |  | 5648.96
|  |  | JDH3-02-008-C-15-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-05-12 | 2026-05-28 | 2025-12-04 | 2026-02-15 | 0 | 0 | 5648961% | Actual Total Cost
|  |  | JDH3-02-008-C-15-(TSE)-Supply and install gate valves-250 mm |  | 2026-05-23 | 2026-05-26 | 2025-12-11 | 2025-12-16 | 0 | 0 | 1026445% | Planned Total Cost | [17 empty] | 10264.45
|  |  | JDH3-02-008-C-15-(TSE)-Supply and install gate valves-250 mm |  | 2026-05-23 | 2026-05-26 | 2025-12-11 | 2025-12-16 | 0 | 0 | 1026445% | Remaining Total Cost | [17 empty] | 10264.45
|  |  | JDH3-02-008-C-15-(TSE)-Supply and install gate valves-250 mm |  | 2026-05-23 | 2026-05-26 | 2025-12-11 | 2025-12-16 | 0 | 0 | 1026445% | Actual Total Cost
|  |  | JDH3-02-008-C-15-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2026-05-23 | 2026-05-26 | 2026-02-07 | 2026-02-10 | 0 | 0 | 7097445% | Planned Total Cost | [19 empty] | 70974.45
|  |  | JDH3-02-008-C-15-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2026-05-23 | 2026-05-26 | 2026-02-07 | 2026-02-10 | 0 | 0 | 7097445% | Remaining Total Cost | [19 empty] | 70974.45
|  |  | JDH3-02-008-C-15-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2026-05-23 | 2026-05-26 | 2026-02-07 | 2026-02-10 | 0 | 0 | 7097445% | Actual Total Cost
|  |  | JDH3-02-008-C-15-(TSE)-Supply and install of Wash-out valves-150 mm. |  | 2026-05-23 | 2026-05-26 | 2025-12-11 | 2025-12-16 | 0 | 0 | 1174858% | Planned Total Cost | [17 empty] | 11748.58
|  |  | JDH3-02-008-C-15-(TSE)-Supply and install of Wash-out valves-150 mm. |  | 2026-05-23 | 2026-05-26 | 2025-12-11 | 2025-12-16 | 0 | 0 | 1174858% | Remaining Total Cost | [17 empty] | 11748.58
|  |  | JDH3-02-008-C-15-(TSE)-Supply and install of Wash-out valves-150 mm. |  | 2026-05-23 | 2026-05-26 | 2025-12-11 | 2025-12-16 | 0 | 0 | 1174858% | Actual Total Cost
|  |  | JDH3-02-008-C-15-(TSE)-Supply and install of Air valves-65 mm. |  | 2026-05-23 | 2026-05-26 | 2025-12-11 | 2025-12-16 | 0 | 0 | 824649% | Planned Total Cost | [17 empty] | 8246.49
|  |  | JDH3-02-008-C-15-(TSE)-Supply and install of Air valves-65 mm. |  | 2026-05-23 | 2026-05-26 | 2025-12-11 | 2025-12-16 | 0 | 0 | 824649% | Remaining Total Cost | [17 empty] | 8246.49
|  |  | JDH3-02-008-C-15-(TSE)-Supply and install of Air valves-65 mm. |  | 2026-05-23 | 2026-05-26 | 2025-12-11 | 2025-12-16 | 0 | 0 | 824649% | Actual Total Cost
|  |  | JDH3-02-008-C-15-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-05-14 | 2026-05-23 | 2025-12-07 | 2025-12-16 | 0 | 0 | 2730690% | Planned Total Cost | [17 empty] | 27306.9
|  |  | JDH3-02-008-C-15-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-05-14 | 2026-05-23 | 2025-12-07 | 2025-12-16 | 0 | 0 | 2730690% | Remaining Total Cost | [17 empty] | 27306.9
|  |  | JDH3-02-008-C-15-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-05-14 | 2026-05-23 | 2025-12-07 | 2025-12-16 | 0 | 0 | 2730690% | Actual Total Cost
|  |  | JDH3-02-008-C-15-(TSE)- Supply and Construct Wash-out Valves Chamber on 450-630 mm Diameter pipeline |  | 2026-05-17 | 2026-05-25 | 2025-12-09 | 2025-12-18 | 0 | 0 | 1879642% | Planned Total Cost | [17 empty] | 18796.42
|  |  | JDH3-02-008-C-15-(TSE)- Supply and Construct Wash-out Valves Chamber on 450-630 mm Diameter pipeline |  | 2026-05-17 | 2026-05-25 | 2025-12-09 | 2025-12-18 | 0 | 0 | 1879642% | Remaining Total Cost | [17 empty] | 18796.42
|  |  | JDH3-02-008-C-15-(TSE)- Supply and Construct Wash-out Valves Chamber on 450-630 mm Diameter pipeline |  | 2026-05-17 | 2026-05-25 | 2025-12-09 | 2025-12-18 | 0 | 0 | 1879642% | Actual Total Cost
|  |  | JDH3-02-008-C-15-(TSE)- Supply and Construct Air Valves Chamber on 355-630 mm Diameter pipelines |  | 2026-05-19 | 2026-05-27 | 2025-12-11 | 2026-02-15 | 0 | 0 | 347928% | Planned Total Cost | [17 empty] | 3131.35 |  | 347.93
|  |  | JDH3-02-008-C-15-(TSE)- Supply and Construct Air Valves Chamber on 355-630 mm Diameter pipelines |  | 2026-05-19 | 2026-05-27 | 2025-12-11 | 2026-02-15 | 0 | 0 | 347928% | Remaining Total Cost | [17 empty] | 3131.35 |  | 347.93
|  |  | JDH3-02-008-C-15-(TSE)- Supply and Construct Air Valves Chamber on 355-630 mm Diameter pipelines |  | 2026-05-19 | 2026-05-27 | 2025-12-11 | 2026-02-15 | 0 | 0 | 347928% | Actual Total Cost
|  |  | JDH3-02-008-C-15-Potable Water Network - WT |  | 2026-05-28 | 2026-07-05 | 03-Sep-25 A | 2026-03-05 | 2232-09-10 08:24 | 2232-09-10 08:24 | 24233505% | Planned Total Cost | [16 empty] | 65541.83 |  |  | 160262.32 | 16530.9
|  |  | JDH3-02-008-C-15-Potable Water Network - WT |  | 2026-05-28 | 2026-07-05 | 03-Sep-25 A | 2026-03-05 | 2232-09-10 08:24 | 2232-09-10 08:24 | 24233505% | Remaining Total Cost | [16 empty] | 76606.09 |  |  | 27682.7 | 16530.9
|  |  | JDH3-02-008-C-15-Potable Water Network - WT |  | 2026-05-28 | 2026-07-05 | 03-Sep-25 A | 2026-03-05 | 2232-09-10 08:24 | 2232-09-10 08:24 | 24233505% | Actual Total Cost | [14 empty] | 117511.14 | 4004.21
|  |  | JDH3-02-008-C-15-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-05-28 | 2026-06-08 | 2026-02-16 | 2026-02-26 | 0 | 0 | 1359905% | Planned Total Cost | [19 empty] | 13599.05
|  |  | JDH3-02-008-C-15-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-05-28 | 2026-06-08 | 2026-02-16 | 2026-02-26 | 0 | 0 | 1359905% | Remaining Total Cost | [19 empty] | 13599.05
|  |  | JDH3-02-008-C-15-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-05-28 | 2026-06-08 | 2026-02-16 | 2026-02-26 | 0 | 0 | 1359905% | Actual Total Cost
|  |  | JDH3-02-008-C-15-(WT)- Supply and install HDPE Pipes -225 mm depth from 0 to 1.5 m |  | 2026-05-31 | 2026-07-05 | 03-Sep-25 A | 2026-03-05 | 2232-09-10 08:24 | 2232-09-10 08:24 | 16572452% | Planned Total Cost | [16 empty] | 16572.45 |  |  | 135341.69 | 13810.38
|  |  | JDH3-02-008-C-15-(WT)- Supply and install HDPE Pipes -225 mm depth from 0 to 1.5 m |  | 2026-05-31 | 2026-07-05 | 03-Sep-25 A | 2026-03-05 | 2232-09-10 08:24 | 2232-09-10 08:24 | 16572452% | Remaining Total Cost | [16 empty] | 27636.72 |  |  | 2762.08 | 13810.38
|  |  | JDH3-02-008-C-15-(WT)- Supply and install HDPE Pipes -225 mm depth from 0 to 1.5 m |  | 2026-05-31 | 2026-07-05 | 03-Sep-25 A | 2026-03-05 | 2232-09-10 08:24 | 2232-09-10 08:24 | 16572452% | Actual Total Cost | [14 empty] | 117511.14 | 4004.21
|  |  | JDH3-02-008-C-15-(WT)- Supply and install gate valves -Diameter 200 mm |  | 2026-06-22 | 2026-06-25 | 2026-02-23 | 2026-02-26 | 0 | 0 | 860106% | Planned Total Cost | [19 empty] | 8601.06
|  |  | JDH3-02-008-C-15-(WT)- Supply and install gate valves -Diameter 200 mm |  | 2026-06-22 | 2026-06-25 | 2026-02-23 | 2026-02-26 | 0 | 0 | 860106% | Remaining Total Cost | [19 empty] | 8601.06
|  |  | JDH3-02-008-C-15-(WT)- Supply and install gate valves -Diameter 200 mm |  | 2026-06-22 | 2026-06-25 | 2026-02-23 | 2026-02-26 | 0 | 0 | 860106% | Actual Total Cost
|  |  | JDH3-02-008-C-15-(WT)- Supply and install 3-out fire hydrant |  | 2026-06-06 | 2026-06-28 | 2025-11-16 | 2026-03-01 | 0 | 0 | 5441042% | Planned Total Cost | [16 empty] | 48969.38 |  |  | 2720.52 | 2720.52
|  |  | JDH3-02-008-C-15-(WT)- Supply and install 3-out fire hydrant |  | 2026-06-06 | 2026-06-28 | 2025-11-16 | 2026-03-01 | 0 | 0 | 5441042% | Remaining Total Cost | [16 empty] | 48969.38 |  |  | 2720.52 | 2720.52
|  |  | JDH3-02-008-C-15-(WT)- Supply and install 3-out fire hydrant |  | 2026-06-06 | 2026-06-28 | 2025-11-16 | 2026-03-01 | 0 | 0 | 5441042% | Actual Total Cost
|  |  | L-01 |  | 2025-11-15 | 2026-06-23 | 07-Jan-25 A | 2026-03-24 | 922945.66 | 922945.64 | 501041025% | Planned Total Cost | [16 empty] | 1343026.26 | 2016204.11 | 631642.78 | 486729.6 | 469642.68 | 3996.48 | 59168.34
|  |  | L-01 |  | 2025-11-15 | 2026-06-23 | 07-Jan-25 A | 2026-03-24 | 922945.66 | 922945.64 | 501041025% | Remaining Total Cost | [16 empty] | 1740850.13 | 1319353 | 576207.74 | 358311.08 | 92742.67
|  |  | L-01 |  | 2025-11-15 | 2026-06-23 | 07-Jan-25 A | 2026-03-24 | 922945.66 | 922945.64 | 501041025% | Actual Total Cost | [7 empty] | 10764.09 | 20056.33 | 17732 | 13013.94 | 12657.24 | 24928.79 | 287497.62 | 516089.77 | 20205.87
|  |  | JDH3-02-008-L-01-Storm Network - ST |  | 2025-11-23 | 2026-01-28 | 02-Jul-25 A | 2025-12-17 | 697637.14 | 697637.12 | 262002089% | Planned Total Cost | [16 empty] | 1260693.78 | 1303892.06 | 55435.04
|  |  | JDH3-02-008-L-01-Storm Network - ST |  | 2025-11-23 | 2026-01-28 | 02-Jul-25 A | 2025-12-17 | 697637.14 | 697637.12 | 262002089% | Remaining Total Cost | [16 empty] | 1658517.66 | 263866.11
|  |  | JDH3-02-008-L-01-Storm Network - ST |  | 2025-11-23 | 2026-01-28 | 02-Jul-25 A | 2025-12-17 | 697637.14 | 697637.12 | 262002089% | Actual Total Cost | [12 empty] | 19224.49 | 259840.83 | 402726.07 | 15845.73
|  |  | JDH3-02-008-L-01-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-11-23 | 2026-01-07 | 2025-11-06 | 2025-12-17 | 0 | 0 | 33292164% | Planned Total Cost | [16 empty] | 299629.48 | 33292.16
|  |  | JDH3-02-008-L-01-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-11-23 | 2026-01-07 | 2025-11-06 | 2025-12-17 | 0 | 0 | 33292164% | Remaining Total Cost | [16 empty] | 299629.48 | 33292.16
|  |  | JDH3-02-008-L-01-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-11-23 | 2026-01-07 | 2025-11-06 | 2025-12-17 | 0 | 0 | 33292164% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-11-26 | 2026-01-03 | 2025-11-10 | 2025-12-13 | 0 | 0 | 4414977% | Planned Total Cost | [16 empty] | 39734.79 | 4414.98
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-11-26 | 2026-01-03 | 2025-11-10 | 2025-12-13 | 0 | 0 | 4414977% | Remaining Total Cost | [16 empty] | 39734.79 | 4414.98
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-11-26 | 2026-01-03 | 2025-11-10 | 2025-12-13 | 0 | 0 | 4414977% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-11-26 | 2026-01-06 | 05-Aug-25 A | 2025-12-10 | 2097-11-08 20:24 | 2097-11-08 20:10 | 18387361% | Planned Total Cost | [16 empty] | 55162.08 | 128711.53
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-11-26 | 2026-01-06 | 05-Aug-25 A | 2025-12-10 | 2097-11-08 20:24 | 2097-11-08 20:10 | 18387361% | Remaining Total Cost | [16 empty] | 101248.17 | 10357.6
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-11-26 | 2026-01-06 | 05-Aug-25 A | 2025-12-10 | 2097-11-08 20:24 | 2097-11-08 20:10 | 18387361% | Actual Total Cost | [13 empty] | 24125.98 | 45926.25 | 2215.61
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2025-11-23 | 2026-01-03 | 02-Jul-25 A | 2025-11-10 | 1986-11-08 05:46 | 1986-11-08 06:00 | 3524916% | Planned Total Cost | [16 empty] | 12337.21 | 22911.95
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2025-11-23 | 2026-01-03 | 02-Jul-25 A | 2025-11-10 | 1986-11-08 05:46 | 1986-11-08 06:00 | 3524916% | Remaining Total Cost | [16 empty] | 3524.92
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2025-11-23 | 2026-01-03 | 02-Jul-25 A | 2025-11-10 | 1986-11-08 05:46 | 1986-11-08 06:00 | 3524916% | Actual Total Cost | [12 empty] | 8812.29 | 19387.04 | 3524.92
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2025-12-03 | 2026-01-03 | 15-Aug-25 A | 2025-12-10 | 1921-01-30 01:26 | 1921-01-30 01:41 | 5513362% | Planned Total Cost | [16 empty] | 5513.36 | 49620.26
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2025-12-03 | 2026-01-03 | 15-Aug-25 A | 2025-12-10 | 1921-01-30 01:26 | 1921-01-30 01:41 | 5513362% | Remaining Total Cost | [16 empty] | 42774.86 | 4657.69
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2025-12-03 | 2026-01-03 | 15-Aug-25 A | 2025-12-10 | 1921-01-30 01:26 | 1921-01-30 01:41 | 5513362% | Actual Total Cost | [13 empty] | 1899.96 | 5540.15 | 260.95
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-11-23 | 2026-01-03 | 02-Jul-25 A | 2025-11-12 | 2095-11-29 13:26 | 2095-11-29 13:26 | 7950840% | Planned Total Cost | [16 empty] | 18363.04 | 61145.36
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-11-23 | 2026-01-03 | 02-Jul-25 A | 2025-11-12 | 2095-11-29 13:26 | 2095-11-29 13:26 | 7950840% | Remaining Total Cost | [16 empty] | 7950.84
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-11-23 | 2026-01-03 | 02-Jul-25 A | 2025-11-12 | 2095-11-29 13:26 | 2095-11-29 13:26 | 7950840% | Actual Total Cost | [12 empty] | 10412.2 | 53194.52 | 7950.84
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-12-08 | 2025-12-25 | 17-Aug-25 A | 2025-11-18 | 2254-10-26 01:12 | 2254-10-26 00:58 | 21214649% | Planned Total Cost | [16 empty] | 42429.3 | 169717.19
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-12-08 | 2025-12-25 | 17-Aug-25 A | 2025-11-18 | 2254-10-26 01:12 | 2254-10-26 00:58 | 21214649% | Remaining Total Cost | [16 empty] | 82550.45
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-12-08 | 2025-12-25 | 17-Aug-25 A | 2025-11-18 | 2254-10-26 01:12 | 2254-10-26 00:58 | 21214649% | Actual Total Cost | [13 empty] | 30898.17 | 95042.39 | 3655.48
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-12-11 | 2025-12-24 | 17-Aug-25 A | 2025-11-16 | 2147-10-11 20:53 | 2147-10-11 20:53 | 20681186% | Planned Total Cost | [16 empty] | 41362.37 | 165449.49
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-12-11 | 2025-12-24 | 17-Aug-25 A | 2025-11-16 | 2147-10-11 20:53 | 2147-10-11 20:53 | 20681186% | Remaining Total Cost | [16 empty] | 116310.99
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-12-11 | 2025-12-24 | 17-Aug-25 A | 2025-11-16 | 2147-10-11 20:53 | 2147-10-11 20:53 | 20681186% | Actual Total Cost | [13 empty] | 21577.14 | 66371 | 2552.73
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2025-12-14 | 2025-12-24 | 15-Aug-25 A | 2025-11-12 | 2071-02-08 19:26 | 2071-02-08 19:26 | 13894578% | Planned Total Cost | [16 empty] | 27789.16 | 111156.62
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2025-12-14 | 2025-12-24 | 15-Aug-25 A | 2025-11-12 | 2071-02-08 19:26 | 2071-02-08 19:26 | 13894578% | Remaining Total Cost | [16 empty] | 76447.97
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2025-12-14 | 2025-12-24 | 15-Aug-25 A | 2025-11-12 | 2071-02-08 19:26 | 2071-02-08 19:26 | 13894578% | Actual Total Cost | [13 empty] | 16934.24 | 43600.04 | 1963.53
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2025-12-16 | 2025-12-27 | 17-Aug-25 A | 2025-11-15 | 2093-08-14 20:53 | 2093-08-14 20:53 | 7857875% | Planned Total Cost | [16 empty] | 15715.75 | 62863
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2025-12-16 | 2025-12-27 | 17-Aug-25 A | 2025-11-15 | 2093-08-14 20:53 | 2093-08-14 20:53 | 7857875% | Remaining Total Cost | [16 empty] | 7857.87
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2025-12-16 | 2025-12-27 | 17-Aug-25 A | 2025-11-15 | 2093-08-14 20:53 | 2093-08-14 20:53 | 7857875% | Actual Total Cost | [13 empty] | 62863 | 7857.87
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 2.51 to 3.50 m |  | 2025-12-18 | 2025-12-29 | 2025-11-09 | 2025-11-20 | 0 | 0 | 3220570% | Planned Total Cost | [16 empty] | 32205.7
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 2.51 to 3.50 m |  | 2025-12-18 | 2025-12-29 | 2025-11-09 | 2025-11-20 | 0 | 0 | 3220570% | Remaining Total Cost | [16 empty] | 32205.7
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 2.51 to 3.50 m |  | 2025-12-18 | 2025-12-29 | 2025-11-09 | 2025-11-20 | 0 | 0 | 3220570% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2025-12-21 | 2026-01-01 | 22-Aug-25 A | 2025-11-13 | 2118-02-21 00:58 | 2118-02-21 00:58 | 22209968% | Planned Total Cost | [16 empty] | 44419.94 | 177679.75
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2025-12-21 | 2026-01-01 | 22-Aug-25 A | 2025-11-13 | 2118-02-21 00:58 | 2118-02-21 00:58 | 22209968% | Remaining Total Cost | [16 empty] | 142423.64
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2025-12-21 | 2026-01-01 | 22-Aug-25 A | 2025-11-13 | 2118-02-21 00:58 | 2118-02-21 00:58 | 22209968% | Actual Total Cost | [13 empty] | 12566.32 | 64319.71 | 2790.01
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2025-12-23 | 2026-01-03 | 2025-11-11 | 2025-11-23 | 0 | 0 | 6114595% | Planned Total Cost | [16 empty] | 61145.95
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2025-12-23 | 2026-01-03 | 2025-11-11 | 2025-11-23 | 0 | 0 | 6114595% | Remaining Total Cost | [16 empty] | 61145.95
|  |  | JDH3-02-008-L-01-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2025-12-23 | 2026-01-03 | 2025-11-11 | 2025-11-23 | 0 | 0 | 6114595% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-12-25 | 2026-01-07 | 22-Aug-25 A | 2025-11-18 | 1996-05-14 16:05 | 1996-05-14 15:50 | 9385828% | Planned Total Cost | [16 empty] | 14078.74 | 57879.27 | 21900.26
|  |  | JDH3-02-008-L-01-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-12-25 | 2026-01-07 | 22-Aug-25 A | 2025-11-18 | 1996-05-14 16:05 | 1996-05-14 15:50 | 9385828% | Remaining Total Cost | [16 empty] | 58658.62
|  |  | JDH3-02-008-L-01-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-12-25 | 2026-01-07 | 22-Aug-25 A | 2025-11-18 | 1996-05-14 16:05 | 1996-05-14 15:50 | 9385828% | Actual Total Cost | [13 empty] | 7089.85 | 27068.71 | 1041.1
|  |  | JDH3-02-008-L-01-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-12-28 | 2026-01-07 | 22-Aug-25 A | 2025-11-18 | 2026-06-22 02:38 | 2026-06-22 02:38 | 9581365% | Planned Total Cost | [16 empty] | 14372.05 | 47906.83 | 33534.78
|  |  | JDH3-02-008-L-01-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-12-28 | 2026-01-07 | 22-Aug-25 A | 2025-11-18 | 2026-06-22 02:38 | 2026-06-22 02:38 | 9581365% | Remaining Total Cost | [16 empty] | 49618.54
|  |  | JDH3-02-008-L-01-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-12-28 | 2026-01-07 | 22-Aug-25 A | 2025-11-18 | 2026-06-22 02:38 | 2026-06-22 02:38 | 9581365% | Actual Total Cost | [13 empty] | 9304.61 | 35524.19 | 1366.31
|  |  | JDH3-02-008-L-01-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-12-30 | 2026-01-10 | 2025-11-13 | 2025-11-25 | 0 | 0 | 5083989% | Planned Total Cost | [16 empty] | 50839.89
|  |  | JDH3-02-008-L-01-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-12-30 | 2026-01-10 | 2025-11-13 | 2025-11-25 | 0 | 0 | 5083989% | Remaining Total Cost | [16 empty] | 50839.89
|  |  | JDH3-02-008-L-01-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-12-30 | 2026-01-10 | 2025-11-13 | 2025-11-25 | 0 | 0 | 5083989% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-01-01 | 2026-01-12 | 2025-11-16 | 2025-11-27 | 0 | 0 | 17207347% | Planned Total Cost | [16 empty] | 172073.47
|  |  | JDH3-02-008-L-01-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-01-01 | 2026-01-12 | 2025-11-16 | 2025-11-27 | 0 | 0 | 17207347% | Remaining Total Cost | [16 empty] | 172073.47
|  |  | JDH3-02-008-L-01-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-01-01 | 2026-01-12 | 2025-11-16 | 2025-11-27 | 0 | 0 | 17207347% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(ST)- Single Catchbasine Works |  | 2026-01-04 | 2026-01-26 | 2025-11-18 | 2025-12-11 | 0 | 0 | 12123366% | Planned Total Cost | [16 empty] | 104351.87 | 16881.79
|  |  | JDH3-02-008-L-01-(ST)- Single Catchbasine Works |  | 2026-01-04 | 2026-01-26 | 2025-11-18 | 2025-12-11 | 0 | 0 | 12123366% | Remaining Total Cost | [16 empty] | 104351.87 | 16881.79
|  |  | JDH3-02-008-L-01-(ST)- Single Catchbasine Works |  | 2026-01-04 | 2026-01-26 | 2025-11-18 | 2025-12-11 | 0 | 0 | 12123366% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(ST)- Double Catchbasine Works |  | 2026-01-08 | 2026-01-28 | 2025-11-23 | 2025-12-14 | 0 | 0 | 34092052% | Planned Total Cost | [16 empty] | 177380.95 | 163539.57
|  |  | JDH3-02-008-L-01-(ST)- Double Catchbasine Works |  | 2026-01-08 | 2026-01-28 | 2025-11-23 | 2025-12-14 | 0 | 0 | 34092052% | Remaining Total Cost | [16 empty] | 177380.95 | 163539.57
|  |  | JDH3-02-008-L-01-(ST)- Double Catchbasine Works |  | 2026-01-08 | 2026-01-28 | 2025-11-23 | 2025-12-14 | 0 | 0 | 34092052% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(ST)-PIPES ENCASEMENT |  | 2025-12-13 | 2025-12-31 | 2025-11-20 | 2025-12-10 | 0 | 0 | 6251100% | Planned Total Cost | [16 empty] | 31788.68 | 30722.32
|  |  | JDH3-02-008-L-01-(ST)-PIPES ENCASEMENT |  | 2025-12-13 | 2025-12-31 | 2025-11-20 | 2025-12-10 | 0 | 0 | 6251100% | Remaining Total Cost | [16 empty] | 31788.68 | 30722.32
|  |  | JDH3-02-008-L-01-(ST)-PIPES ENCASEMENT |  | 2025-12-13 | 2025-12-31 | 2025-11-20 | 2025-12-10 | 0 | 0 | 6251100% | Actual Total Cost
|  |  | JDH3-02-008-L-01-TSE Network - TSE |  | 2026-01-29 | 2026-05-16 | 05-Feb-25 A | 2026-02-14 | 225308.52 | 225308.52 | 206801496% | Planned Total Cost | [16 empty] | 82332.47 | 712312.05 | 576207.74 | 257097.87 | 376900.01 | 3996.48 | 59168.34
|  |  | JDH3-02-008-L-01-TSE Network - TSE |  | 2026-01-29 | 2026-05-16 | 05-Feb-25 A | 2026-02-14 | 225308.52 | 225308.52 | 206801496% | Remaining Total Cost | [16 empty] | 82332.47 | 1055486.88 | 576207.74 | 128679.35
|  |  | JDH3-02-008-L-01-TSE Network - TSE |  | 2026-01-29 | 2026-05-16 | 05-Feb-25 A | 2026-02-14 | 225308.52 | 225308.52 | 206801496% | Actual Total Cost | [7 empty] | 10764.09 | 20056.33 | 17732 | 13013.94 | 12657.24 | 5704.3 | 27656.79 | 113363.69 | 4360.14
|  |  | JDH3-02-008-L-01-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-01-29 | 2026-02-21 | 2025-12-17 | 2026-01-10 | 0 | 0 | 6300385% | Planned Total Cost | [17 empty] | 51419.02 | 11584.83
|  |  | JDH3-02-008-L-01-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-01-29 | 2026-02-21 | 2025-12-17 | 2026-01-10 | 0 | 0 | 6300385% | Remaining Total Cost | [17 empty] | 51419.02 | 11584.83
|  |  | JDH3-02-008-L-01-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-01-29 | 2026-02-21 | 2025-12-17 | 2026-01-10 | 0 | 0 | 6300385% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-02-02 | 2026-05-16 | 05-Feb-25 A | 2025-12-27 | 225308.52 | 225308.52 | 63164816% | Planned Total Cost | [16 empty] | 44215.37 | 18949.45 |  | 128418.52 | 376900.01 | 3996.48 | 59168.34
|  |  | JDH3-02-008-L-01-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-02-02 | 2026-05-16 | 05-Feb-25 A | 2025-12-27 | 225308.52 | 225308.52 | 63164816% | Remaining Total Cost | [16 empty] | 44215.37 | 362124.28
|  |  | JDH3-02-008-L-01-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-02-02 | 2026-05-16 | 05-Feb-25 A | 2025-12-27 | 225308.52 | 225308.52 | 63164816% | Actual Total Cost | [7 empty] | 10764.09 | 20056.33 | 17732 | 13013.94 | 12657.24 | 5704.3 | 27656.79 | 113363.69 | 4360.14
|  |  | JDH3-02-008-L-01-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2026-02-19 | 2026-04-13 | 2025-11-06 | 2026-02-12 | 0 | 0 | 12437611% | Planned Total Cost | [16 empty] | 38117.11 | 73821.39 |  | 12437.61
|  |  | JDH3-02-008-L-01-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2026-02-19 | 2026-04-13 | 2025-11-06 | 2026-02-12 | 0 | 0 | 12437611% | Remaining Total Cost | [16 empty] | 38117.11 | 73821.39 |  | 12437.61
|  |  | JDH3-02-008-L-01-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2026-02-19 | 2026-04-13 | 2025-11-06 | 2026-02-12 | 0 | 0 | 12437611% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2026-02-24 | 2026-04-13 | 2025-12-23 | 2026-02-12 | 0 | 0 | 316434% | Planned Total Cost | [17 empty] | 2791.74 | 56.17 | 316.43
|  |  | JDH3-02-008-L-01-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2026-02-24 | 2026-04-13 | 2025-12-23 | 2026-02-12 | 0 | 0 | 316434% | Remaining Total Cost | [17 empty] | 2791.74 | 56.17 | 316.43
|  |  | JDH3-02-008-L-01-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2026-02-24 | 2026-04-13 | 2025-12-23 | 2026-02-12 | 0 | 0 | 316434% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-01-29 | 2026-04-14 | 2025-12-17 | 2026-02-14 | 0 | 0 | 26815800% | Planned Total Cost | [17 empty] | 241342.2 |  | 26815.8
|  |  | JDH3-02-008-L-01-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-01-29 | 2026-04-14 | 2025-12-17 | 2026-02-14 | 0 | 0 | 26815800% | Remaining Total Cost | [17 empty] | 241342.2 |  | 26815.8
|  |  | JDH3-02-008-L-01-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-01-29 | 2026-04-14 | 2025-12-17 | 2026-02-14 | 0 | 0 | 26815800% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-01-29 | 2026-03-15 | 2025-12-17 | 2026-02-01 | 0 | 0 | 62988219% | Planned Total Cost | [17 empty] | 177784.25 | 449302.84 | 2795.1
|  |  | JDH3-02-008-L-01-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-01-29 | 2026-03-15 | 2025-12-17 | 2026-02-01 | 0 | 0 | 62988219% | Remaining Total Cost | [17 empty] | 177784.25 | 449302.84 | 2795.1
|  |  | JDH3-02-008-L-01-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-01-29 | 2026-03-15 | 2025-12-17 | 2026-02-01 | 0 | 0 | 62988219% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 0 to 1.5 m |  | 2026-01-29 | 2026-02-09 | 2025-12-17 | 2025-12-29 | 0 | 0 | 7506724% | Planned Total Cost | [17 empty] | 75067.24
|  |  | JDH3-02-008-L-01-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 0 to 1.5 m |  | 2026-01-29 | 2026-02-09 | 2025-12-17 | 2025-12-29 | 0 | 0 | 7506724% | Remaining Total Cost | [17 empty] | 75067.24
|  |  | JDH3-02-008-L-01-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 0 to 1.5 m |  | 2026-01-29 | 2026-02-09 | 2025-12-17 | 2025-12-29 | 0 | 0 | 7506724% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(TSE)-Supply and install gate valves-100 mm |  | 2026-03-31 | 2026-04-11 | 2026-01-13 | 2026-01-25 | 0 | 0 | 2327689% | Planned Total Cost | [18 empty] | 23276.89
|  |  | JDH3-02-008-L-01-(TSE)-Supply and install gate valves-100 mm |  | 2026-03-31 | 2026-04-11 | 2026-01-13 | 2026-01-25 | 0 | 0 | 2327689% | Remaining Total Cost | [18 empty] | 23276.89
|  |  | JDH3-02-008-L-01-(TSE)-Supply and install gate valves-100 mm |  | 2026-03-31 | 2026-04-11 | 2026-01-13 | 2026-01-25 | 0 | 0 | 2327689% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(TSE)-Supply and install gate valves-250 mm |  | 2026-03-31 | 2026-04-08 | 2026-01-13 | 2026-01-22 | 0 | 0 | 3592559% | Planned Total Cost | [18 empty] | 35925.59
|  |  | JDH3-02-008-L-01-(TSE)-Supply and install gate valves-250 mm |  | 2026-03-31 | 2026-04-08 | 2026-01-13 | 2026-01-22 | 0 | 0 | 3592559% | Remaining Total Cost | [18 empty] | 35925.59
|  |  | JDH3-02-008-L-01-(TSE)-Supply and install gate valves-250 mm |  | 2026-03-31 | 2026-04-08 | 2026-01-13 | 2026-01-22 | 0 | 0 | 3592559% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2026-03-31 | 2026-04-04 | 2026-02-07 | 2026-02-10 | 0 | 0 | 1533996% | Planned Total Cost | [19 empty] | 15339.96
|  |  | JDH3-02-008-L-01-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2026-03-31 | 2026-04-04 | 2026-02-07 | 2026-02-10 | 0 | 0 | 1533996% | Remaining Total Cost | [19 empty] | 15339.96
|  |  | JDH3-02-008-L-01-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2026-03-31 | 2026-04-04 | 2026-02-07 | 2026-02-10 | 0 | 0 | 1533996% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2026-03-31 | 2026-04-04 | 2026-02-07 | 2026-02-10 | 0 | 0 | 7097445% | Planned Total Cost | [19 empty] | 70974.45
|  |  | JDH3-02-008-L-01-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2026-03-31 | 2026-04-04 | 2026-02-07 | 2026-02-10 | 0 | 0 | 7097445% | Remaining Total Cost | [19 empty] | 70974.45
|  |  | JDH3-02-008-L-01-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2026-03-31 | 2026-04-04 | 2026-02-07 | 2026-02-10 | 0 | 0 | 7097445% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-03-31 | 2026-04-04 | 2026-01-13 | 2026-01-18 | 0 | 0 | 979190% | Planned Total Cost | [18 empty] | 9791.9
|  |  | JDH3-02-008-L-01-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-03-31 | 2026-04-04 | 2026-01-13 | 2026-01-18 | 0 | 0 | 979190% | Remaining Total Cost | [18 empty] | 9791.9
|  |  | JDH3-02-008-L-01-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-03-31 | 2026-04-04 | 2026-01-13 | 2026-01-18 | 0 | 0 | 979190% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-03-31 | 2026-04-04 | 2026-01-13 | 2026-01-18 | 0 | 0 | 2977654% | Planned Total Cost | [18 empty] | 29776.54
|  |  | JDH3-02-008-L-01-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-03-31 | 2026-04-04 | 2026-01-13 | 2026-01-18 | 0 | 0 | 2977654% | Remaining Total Cost | [18 empty] | 29776.54
|  |  | JDH3-02-008-L-01-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-03-31 | 2026-04-04 | 2026-01-13 | 2026-01-18 | 0 | 0 | 2977654% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(TSE)-Supply and install of Air valves-65 mm. |  | 2026-03-31 | 2026-04-04 | 2026-01-13 | 2026-01-18 | 0 | 0 | 1649299% | Planned Total Cost | [18 empty] | 16492.99
|  |  | JDH3-02-008-L-01-(TSE)-Supply and install of Air valves-65 mm. |  | 2026-03-31 | 2026-04-04 | 2026-01-13 | 2026-01-18 | 0 | 0 | 1649299% | Remaining Total Cost | [18 empty] | 16492.99
|  |  | JDH3-02-008-L-01-(TSE)-Supply and install of Air valves-65 mm. |  | 2026-03-31 | 2026-04-04 | 2026-01-13 | 2026-01-18 | 0 | 0 | 1649299% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-01-29 | 2026-02-07 | 2025-12-17 | 2025-12-27 | 0 | 0 | 3640919% | Planned Total Cost | [17 empty] | 36409.19
|  |  | JDH3-02-008-L-01-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-01-29 | 2026-02-07 | 2025-12-17 | 2025-12-27 | 0 | 0 | 3640919% | Remaining Total Cost | [17 empty] | 36409.19
|  |  | JDH3-02-008-L-01-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-01-29 | 2026-02-07 | 2025-12-17 | 2025-12-27 | 0 | 0 | 3640919% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-01-29 | 2026-02-07 | 2025-12-17 | 2025-12-27 | 0 | 0 | 1385192% | Planned Total Cost | [17 empty] | 13851.92
|  |  | JDH3-02-008-L-01-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-01-29 | 2026-02-07 | 2025-12-17 | 2025-12-27 | 0 | 0 | 1385192% | Remaining Total Cost | [17 empty] | 13851.92
|  |  | JDH3-02-008-L-01-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-01-29 | 2026-02-07 | 2025-12-17 | 2025-12-27 | 0 | 0 | 1385192% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-01-29 | 2026-02-07 | 2025-12-17 | 2025-12-27 | 0 | 0 | 1391711% | Planned Total Cost | [17 empty] | 13917.11
|  |  | JDH3-02-008-L-01-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-01-29 | 2026-02-07 | 2025-12-17 | 2025-12-27 | 0 | 0 | 1391711% | Remaining Total Cost | [17 empty] | 13917.11
|  |  | JDH3-02-008-L-01-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-01-29 | 2026-02-07 | 2025-12-17 | 2025-12-27 | 0 | 0 | 1391711% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(TSE)- Supply and Construct Air Valves Chamber on 355-630 mm Diameter pipelines |  | 2026-01-29 | 2026-02-07 | 2025-12-17 | 2025-12-27 | 0 | 0 | 695855% | Planned Total Cost | [17 empty] | 6958.55
|  |  | JDH3-02-008-L-01-(TSE)- Supply and Construct Air Valves Chamber on 355-630 mm Diameter pipelines |  | 2026-01-29 | 2026-02-07 | 2025-12-17 | 2025-12-27 | 0 | 0 | 695855% | Remaining Total Cost | [17 empty] | 6958.55
|  |  | JDH3-02-008-L-01-(TSE)- Supply and Construct Air Valves Chamber on 355-630 mm Diameter pipelines |  | 2026-01-29 | 2026-02-07 | 2025-12-17 | 2025-12-27 | 0 | 0 | 695855% | Actual Total Cost
|  |  | JDH3-02-008-L-01-Street Lighting Network -SL |  | 2026-05-17 | 2026-06-23 | 2026-02-15 | 2026-03-24 | 0 | 0 | 32237440% | Planned Total Cost | [19 empty] | 229631.73 | 92742.67
|  |  | JDH3-02-008-L-01-Street Lighting Network -SL |  | 2026-05-17 | 2026-06-23 | 2026-02-15 | 2026-03-24 | 0 | 0 | 32237440% | Remaining Total Cost | [19 empty] | 229631.73 | 92742.67
|  |  | JDH3-02-008-L-01-Street Lighting Network -SL |  | 2026-05-17 | 2026-06-23 | 2026-02-15 | 2026-03-24 | 0 | 0 | 32237440% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2026-05-17 | 2026-06-23 | 2026-02-15 | 2026-03-24 | 0 | 0 | 16827406% | Planned Total Cost | [19 empty] | 86240.45 | 82033.6
|  |  | JDH3-02-008-L-01-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2026-05-17 | 2026-06-23 | 2026-02-15 | 2026-03-24 | 0 | 0 | 16827406% | Remaining Total Cost | [19 empty] | 86240.45 | 82033.6
|  |  | JDH3-02-008-L-01-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2026-05-17 | 2026-06-23 | 2026-02-15 | 2026-03-24 | 0 | 0 | 16827406% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2026-05-27 | 2026-05-31 | 2026-02-25 | 2026-03-01 | 0 | 0 | 2588604% | Planned Total Cost | [19 empty] | 19414.53 | 6471.51
|  |  | JDH3-02-008-L-01-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2026-05-27 | 2026-05-31 | 2026-02-25 | 2026-03-01 | 0 | 0 | 2588604% | Remaining Total Cost | [19 empty] | 19414.53 | 6471.51
|  |  | JDH3-02-008-L-01-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2026-05-27 | 2026-05-31 | 2026-02-25 | 2026-03-01 | 0 | 0 | 2588604% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2026-06-01 | 2026-06-02 | 2026-03-02 | 2026-03-03 | 0 | 0 | 113412% | Planned Total Cost | [20 empty] | 1134.12
|  |  | JDH3-02-008-L-01-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2026-06-01 | 2026-06-02 | 2026-03-02 | 2026-03-03 | 0 | 0 | 113412% | Remaining Total Cost | [20 empty] | 1134.12
|  |  | JDH3-02-008-L-01-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2026-06-01 | 2026-06-02 | 2026-03-02 | 2026-03-03 | 0 | 0 | 113412% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-4 × 150 mm |  | 2026-05-17 | 2026-06-04 | 2026-02-15 | 2026-03-05 | 0 | 0 | 531866% | Planned Total Cost | [19 empty] | 5052.73 | 265.93
|  |  | JDH3-02-008-L-01-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-4 × 150 mm |  | 2026-05-17 | 2026-06-04 | 2026-02-15 | 2026-03-05 | 0 | 0 | 531866% | Remaining Total Cost | [19 empty] | 5052.73 | 265.93
|  |  | JDH3-02-008-L-01-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-4 × 150 mm |  | 2026-05-17 | 2026-06-04 | 2026-02-15 | 2026-03-05 | 0 | 0 | 531866% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2026-05-17 | 2026-05-31 | 2026-02-15 | 2026-03-01 | 0 | 0 | 11350004% | Planned Total Cost | [19 empty] | 110662.54 | 2837.5
|  |  | JDH3-02-008-L-01-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2026-05-17 | 2026-05-31 | 2026-02-15 | 2026-03-01 | 0 | 0 | 11350004% | Remaining Total Cost | [19 empty] | 110662.54 | 2837.5
|  |  | JDH3-02-008-L-01-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2026-05-17 | 2026-05-31 | 2026-02-15 | 2026-03-01 | 0 | 0 | 11350004% | Actual Total Cost
|  |  | JDH3-02-008-L-01-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2026-05-17 | 2026-05-23 | 2026-02-15 | 2026-02-21 | 0 | 0 | 826148% | Planned Total Cost | [19 empty] | 8261.48
|  |  | JDH3-02-008-L-01-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2026-05-17 | 2026-05-23 | 2026-02-15 | 2026-02-21 | 0 | 0 | 826148% | Remaining Total Cost | [19 empty] | 8261.48
|  |  | JDH3-02-008-L-01-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2026-05-17 | 2026-05-23 | 2026-02-15 | 2026-02-21 | 0 | 0 | 826148% | Actual Total Cost
|  |  | L-03 |  | 2025-08-26 | 2026-07-04 | 05-Nov-24 A | 2026-03-23 | 1771798.45 | 1771798.44 | 659004068% | Planned Total Cost | [16 empty] | 2397393.26 | 1881243.7 | 651086.76 | 955897.59 | 613429.37 | 38395.08 | 45080.78 | 7514.14
|  |  | L-03 |  | 2025-08-26 | 2026-07-04 | 05-Nov-24 A | 2026-03-23 | 1771798.45 | 1771798.44 | 659004068% | Remaining Total Cost | [16 empty] | 2404210.15 | 1764628.49 | 208879.55 | 347610.38 | 92913.66
|  |  | L-03 |  | 2025-08-26 | 2026-07-04 | 05-Nov-24 A | 2026-03-23 | 1771798.45 | 1771798.44 | 659004068% | Actual Total Cost | [5 empty] | 1502828% | 28292.67 | 35907.56 | 167598.65 | 16848.24 | 47109.75 | 9744.23 | 51562.81 | 928861.01 | 469153.51 | 1691.73
|  |  | JDH3-02-008-L-03-Sewage Network - SS |  | 2025-09-03 | 2026-01-03 | 2025-11-06 | 2026-03-09 | 0 | 0 | 192132039% | Planned Total Cost | [16 empty] | 527134.6 | 999141.41 | 203728.94 | 150327.24 | 40988.21
|  |  | JDH3-02-008-L-03-Sewage Network - SS |  | 2025-09-03 | 2026-01-03 | 2025-11-06 | 2026-03-09 | 0 | 0 | 192132039% | Remaining Total Cost | [16 empty] | 527134.6 | 999141.41 | 203728.94 | 150327.24 | 40988.21
|  |  | JDH3-02-008-L-03-Sewage Network - SS |  | 2025-09-03 | 2026-01-03 | 2025-11-06 | 2026-03-09 | 0 | 0 | 192132039% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 0 to 1.5 m. |  | 2025-09-03 | 2025-09-14 | 2025-11-06 | 2025-11-18 | 0 | 0 | 1865923% | Planned Total Cost | [16 empty] | 18659.23
|  |  | JDH3-02-008-L-03-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 0 to 1.5 m. |  | 2025-09-03 | 2025-09-14 | 2025-11-06 | 2025-11-18 | 0 | 0 | 1865923% | Remaining Total Cost | [16 empty] | 18659.23
|  |  | JDH3-02-008-L-03-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 0 to 1.5 m. |  | 2025-09-03 | 2025-09-14 | 2025-11-06 | 2025-11-18 | 0 | 0 | 1865923% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2025-09-06 | 2025-10-16 | 2025-11-09 | 2025-12-21 | 0 | 0 | 23253195% | Planned Total Cost | [16 empty] | 142998.85 | 89533.11
|  |  | JDH3-02-008-L-03-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2025-09-06 | 2025-10-16 | 2025-11-09 | 2025-12-21 | 0 | 0 | 23253195% | Remaining Total Cost | [16 empty] | 142998.85 | 89533.11
|  |  | JDH3-02-008-L-03-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2025-09-06 | 2025-10-16 | 2025-11-09 | 2025-12-21 | 0 | 0 | 23253195% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2025-09-13 | 2025-09-25 | 2025-11-16 | 2025-11-30 | 0 | 0 | 9907593% | Planned Total Cost | [16 empty] | 99075.93
|  |  | JDH3-02-008-L-03-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2025-09-13 | 2025-09-25 | 2025-11-16 | 2025-11-30 | 0 | 0 | 9907593% | Remaining Total Cost | [16 empty] | 99075.93
|  |  | JDH3-02-008-L-03-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2025-09-13 | 2025-09-25 | 2025-11-16 | 2025-11-30 | 0 | 0 | 9907593% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 2.51 to 3.5 m. |  | 2025-09-15 | 2025-10-02 | 2025-11-18 | 2025-12-07 | 0 | 0 | 12815785% | Planned Total Cost | [16 empty] | 109553.6 | 18604.25
|  |  | JDH3-02-008-L-03-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 2.51 to 3.5 m. |  | 2025-09-15 | 2025-10-02 | 2025-11-18 | 2025-12-07 | 0 | 0 | 12815785% | Remaining Total Cost | [16 empty] | 109553.6 | 18604.25
|  |  | JDH3-02-008-L-03-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 2.51 to 3.5 m. |  | 2025-09-15 | 2025-10-02 | 2025-11-18 | 2025-12-07 | 0 | 0 | 12815785% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 3.51 to 4.5 m. |  | 2025-09-18 | 2025-10-14 | 2025-11-22 | 2025-12-18 | 0 | 0 | 43042613% | Planned Total Cost | [16 empty] | 105696.52 | 324729.62
|  |  | JDH3-02-008-L-03-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 3.51 to 4.5 m. |  | 2025-09-18 | 2025-10-14 | 2025-11-22 | 2025-12-18 | 0 | 0 | 43042613% | Remaining Total Cost | [16 empty] | 105696.52 | 324729.62
|  |  | JDH3-02-008-L-03-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 3.51 to 4.5 m. |  | 2025-09-18 | 2025-10-14 | 2025-11-22 | 2025-12-18 | 0 | 0 | 43042613% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(SS)-Glass Reinforced Plastic (GRP)-300mm diameter depth from 4.51 to 5.5 m. |  | 2025-09-23 | 2025-10-05 | 2025-11-26 | 2025-12-09 | 0 | 0 | 10418741% | Planned Total Cost | [16 empty] | 25122.19 | 79065.22
|  |  | JDH3-02-008-L-03-(SS)-Glass Reinforced Plastic (GRP)-300mm diameter depth from 4.51 to 5.5 m. |  | 2025-09-23 | 2025-10-05 | 2025-11-26 | 2025-12-09 | 0 | 0 | 10418741% | Remaining Total Cost | [16 empty] | 25122.19 | 79065.22
|  |  | JDH3-02-008-L-03-(SS)-Glass Reinforced Plastic (GRP)-300mm diameter depth from 4.51 to 5.5 m. |  | 2025-09-23 | 2025-10-05 | 2025-11-26 | 2025-12-09 | 0 | 0 | 10418741% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(SS)-Glass Reinforced Plastic (GRP)-400mm diameter depth from 4.51 to 5.5 m. |  | 2025-09-25 | 2025-10-23 | 2025-11-29 | 2025-12-28 | 0 | 0 | 31645327% | Planned Total Cost | [16 empty] | 26028.28 | 290424.99
|  |  | JDH3-02-008-L-03-(SS)-Glass Reinforced Plastic (GRP)-400mm diameter depth from 4.51 to 5.5 m. |  | 2025-09-25 | 2025-10-23 | 2025-11-29 | 2025-12-28 | 0 | 0 | 31645327% | Remaining Total Cost | [16 empty] | 26028.28 | 290424.99
|  |  | JDH3-02-008-L-03-(SS)-Glass Reinforced Plastic (GRP)-400mm diameter depth from 4.51 to 5.5 m. |  | 2025-09-25 | 2025-10-23 | 2025-11-29 | 2025-12-28 | 0 | 0 | 31645327% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2025-09-30 | 2025-10-20 | 2025-12-03 | 2025-12-24 | 0 | 0 | 14600176% | Planned Total Cost | [17 empty] | 146001.76
|  |  | JDH3-02-008-L-03-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2025-09-30 | 2025-10-20 | 2025-12-03 | 2025-12-24 | 0 | 0 | 14600176% | Remaining Total Cost | [17 empty] | 146001.76
|  |  | JDH3-02-008-L-03-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2025-09-30 | 2025-10-20 | 2025-12-03 | 2025-12-24 | 0 | 0 | 14600176% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2025-10-25 | 2026-01-03 | 2025-12-28 | 2026-03-09 | 0 | 0 | 44582684% | Planned Total Cost | [17 empty] | 50782.46 | 203728.94 | 150327.24 | 40988.21
|  |  | JDH3-02-008-L-03-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2025-10-25 | 2026-01-03 | 2025-12-28 | 2026-03-09 | 0 | 0 | 44582684% | Remaining Total Cost | [17 empty] | 50782.46 | 203728.94 | 150327.24 | 40988.21
|  |  | JDH3-02-008-L-03-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2025-10-25 | 2026-01-03 | 2025-12-28 | 2026-03-09 | 0 | 0 | 44582684% | Actual Total Cost
|  |  | JDH3-02-008-L-03-Storm Network - ST |  | 2026-01-04 | 2026-04-23 | 25-Feb-25 A | 2026-03-23 | 1666478.56 | 1666478.55 | 309705070% | Planned Total Cost | [16 empty] | 1332354.21 | 118394.11 | 442207.21 | 608287.21 | 572441.17 | 23366.8
|  |  | JDH3-02-008-L-03-Storm Network - ST |  | 2026-01-04 | 2026-04-23 | 25-Feb-25 A | 2026-03-23 | 1666478.56 | 1666478.55 | 309705070% | Remaining Total Cost | [16 empty] | 1339171.09 | 39475.58 |  |  | 51925.45
|  |  | JDH3-02-008-L-03-Storm Network - ST |  | 2026-01-04 | 2026-04-23 | 25-Feb-25 A | 2026-03-23 | 1666478.56 | 1666478.55 | 309705070% | Actual Total Cost | [7 empty] | 14423.11 | 164780.84 | 16848.24 | 47109.75 | 9744.23 | 51562.81 | 928861.01 | 431456.82 | 1691.73
|  |  | JDH3-02-008-L-03-(ST)-Box Culvert |  | 2026-01-04 | 2026-02-22 | 12-Aug-25 A | 2025-11-25 | 577496.22 | 577496.22 | 66609936% | Planned Total Cost | [16 empty] | 88603.13 |  | 421091 | 156405.23
|  |  | JDH3-02-008-L-03-(ST)-Box Culvert |  | 2026-01-04 | 2026-02-22 | 12-Aug-25 A | 2025-11-25 | 577496.22 | 577496.22 | 66609936% | Remaining Total Cost | [16 empty] | 88603.13
|  |  | JDH3-02-008-L-03-(ST)-Box Culvert |  | 2026-01-04 | 2026-02-22 | 12-Aug-25 A | 2025-11-25 | 577496.22 | 577496.22 | 66609936% | Actual Total Cost | [13 empty] | 341280.5 | 236215.72
|  |  | JDH3-02-008-L-03-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2026-01-04 | 2026-02-22 | 12-Aug-25 A | 21-Sep-25 A | 577496.22 | 577496.22 | 57749622% | Planned Total Cost | [18 empty] | 421091 | 156405.23
|  |  | JDH3-02-008-L-03-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2026-01-04 | 2026-02-22 | 12-Aug-25 A | 21-Sep-25 A | 577496.22 | 577496.22 | 57749622% | Remaining Total Cost
|  |  | JDH3-02-008-L-03-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2026-01-04 | 2026-02-22 | 12-Aug-25 A | 21-Sep-25 A | 577496.22 | 577496.22 | 57749622% | Actual Total Cost | [13 empty] | 341280.5 | 236215.72
|  |  | JDH3-02-008-L-03-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2026-01-07 | 2026-01-25 | 2025-11-06 | 2025-11-25 | 0 | 0 | 8860313% | Planned Total Cost | [16 empty] | 88603.13
|  |  | JDH3-02-008-L-03-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2026-01-07 | 2026-01-25 | 2025-11-06 | 2025-11-25 | 0 | 0 | 8860313% | Remaining Total Cost | [16 empty] | 88603.13
|  |  | JDH3-02-008-L-03-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2026-01-07 | 2026-01-25 | 2025-11-06 | 2025-11-25 | 0 | 0 | 8860313% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(ST)-Network |  | 2026-01-26 | 2026-04-23 | 25-Feb-25 A | 2026-03-23 | 1088982.34 | 1088982.33 | 243095134% | Planned Total Cost | [16 empty] | 1243751.07 | 118394.11 | 21116.21 | 451881.98 | 572441.17 | 23366.8
|  |  | JDH3-02-008-L-03-(ST)-Network |  | 2026-01-26 | 2026-04-23 | 25-Feb-25 A | 2026-03-23 | 1088982.34 | 1088982.33 | 243095134% | Remaining Total Cost | [16 empty] | 1250567.96 | 39475.58 |  |  | 51925.45
|  |  | JDH3-02-008-L-03-(ST)-Network |  | 2026-01-26 | 2026-04-23 | 25-Feb-25 A | 2026-03-23 | 1088982.34 | 1088982.33 | 243095134% | Actual Total Cost | [7 empty] | 14423.11 | 164780.84 | 16848.24 | 47109.75 | 9744.23 | 51562.81 | 587580.51 | 195241.1 | 1691.73
|  |  | JDH3-02-008-L-03-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2026-01-26 | 2026-02-05 | 17-Aug-25 A | 2025-11-11 | 1988-02-04 01:55 | 1988-02-04 01:55 | 4022135% | Planned Total Cost | [16 empty] | 8044.27 |  | 21116.21 | 11060.87
|  |  | JDH3-02-008-L-03-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2026-01-26 | 2026-02-05 | 17-Aug-25 A | 2025-11-11 | 1988-02-04 01:55 | 1988-02-04 01:55 | 4022135% | Remaining Total Cost | [16 empty] | 8044.27
|  |  | JDH3-02-008-L-03-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2026-01-26 | 2026-02-05 | 17-Aug-25 A | 2025-11-11 | 1988-02-04 01:55 | 1988-02-04 01:55 | 4022135% | Actual Total Cost | [13 empty] | 32177.08
|  |  | JDH3-02-008-L-03-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-01-28 | 2026-03-07 | 2025-11-06 | 2025-12-03 | 0 | 0 | 34100133% | Planned Total Cost | [16 empty] | 327617.03 | 13384.3
|  |  | JDH3-02-008-L-03-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-01-28 | 2026-03-07 | 2025-11-06 | 2025-12-03 | 0 | 0 | 34100133% | Remaining Total Cost | [16 empty] | 327617.03 | 13384.3
|  |  | JDH3-02-008-L-03-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-01-28 | 2026-03-07 | 2025-11-06 | 2025-12-03 | 0 | 0 | 34100133% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-02-01 | 2026-02-12 | 2025-11-10 | 2025-11-23 | 0 | 0 | 9593559% | Planned Total Cost | [16 empty] | 95935.59
|  |  | JDH3-02-008-L-03-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-02-01 | 2026-02-12 | 2025-11-10 | 2025-11-23 | 0 | 0 | 9593559% | Remaining Total Cost | [16 empty] | 95935.59
|  |  | JDH3-02-008-L-03-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-02-01 | 2026-02-12 | 2025-11-10 | 2025-11-23 | 0 | 0 | 9593559% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2026-02-03 | 2026-02-16 | 2025-11-12 | 2025-11-26 | 0 | 0 | 6981622% | Planned Total Cost | [16 empty] | 69816.22
|  |  | JDH3-02-008-L-03-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2026-02-03 | 2026-02-16 | 2025-11-12 | 2025-11-26 | 0 | 0 | 6981622% | Remaining Total Cost | [16 empty] | 69816.22
|  |  | JDH3-02-008-L-03-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2026-02-03 | 2026-02-16 | 2025-11-12 | 2025-11-26 | 0 | 0 | 6981622% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2026-02-05 | 2026-02-18 | 30-Jun-25 A | 2025-11-29 | 2029-09-15 00:58 | 2029-09-15 00:43 | 5093544% | Planned Total Cost | [16 empty] | 8652.95 |  |  | 42282.49
|  |  | JDH3-02-008-L-03-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2026-02-05 | 2026-02-18 | 30-Jun-25 A | 2025-11-29 | 2029-09-15 00:58 | 2029-09-15 00:43 | 5093544% | Remaining Total Cost | [16 empty] | 3559.4
|  |  | JDH3-02-008-L-03-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2026-02-05 | 2026-02-18 | 30-Jun-25 A | 2025-11-29 | 2029-09-15 00:58 | 2029-09-15 00:43 | 5093544% | Actual Total Cost | [11 empty] | 636.69 | 41645.8 |  | 5093.54
|  |  | JDH3-02-008-L-03-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-02-08 | 2026-02-21 | 2025-11-17 | 2025-12-01 | 0 | 0 | 4135521% | Planned Total Cost | [16 empty] | 40621.15 | 734.05
|  |  | JDH3-02-008-L-03-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-02-08 | 2026-02-21 | 2025-11-17 | 2025-12-01 | 0 | 0 | 4135521% | Remaining Total Cost | [16 empty] | 40621.15 | 734.05
|  |  | JDH3-02-008-L-03-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-02-08 | 2026-02-21 | 2025-11-17 | 2025-12-01 | 0 | 0 | 4135521% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 0.00 to 1.50 m |  | 2026-02-10 | 2026-03-02 | 25-Feb-25 A | 2025-12-03 | 227920.61 | 227920.61 | 24506523% | Planned Total Cost | [17 empty] | 17144.62 |  | 227920.61
|  |  | JDH3-02-008-L-03-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 0.00 to 1.50 m |  | 2026-02-10 | 2026-03-02 | 25-Feb-25 A | 2025-12-03 | 227920.61 | 227920.61 | 24506523% | Remaining Total Cost | [17 empty] | 17144.62
|  |  | JDH3-02-008-L-03-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 0.00 to 1.50 m |  | 2026-02-10 | 2026-03-02 | 25-Feb-25 A | 2025-12-03 | 227920.61 | 227920.61 | 24506523% | Actual Total Cost | [7 empty] | 14423.11 | 164780.84 | 16848.24 | 3068.85 | 5114.75 | 7361.9 | 7617.36 | 8705.56
|  |  | JDH3-02-008-L-03-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-02-14 | 2026-03-14 | 01-Aug-25 A | 15-Sep-25 A | 386838.99 | 386838.99 | 38683899% | Planned Total Cost | [16 empty] | 34106.3 | 43261.49 |  | 96709.75 | 212761.44
|  |  | JDH3-02-008-L-03-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-02-14 | 2026-03-14 | 01-Aug-25 A | 15-Sep-25 A | 386838.99 | 386838.99 | 38683899% | Remaining Total Cost
|  |  | JDH3-02-008-L-03-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-02-14 | 2026-03-14 | 01-Aug-25 A | 15-Sep-25 A | 386838.99 | 386838.99 | 38683899% | Actual Total Cost | [13 empty] | 234415.53 | 152423.46
|  |  | JDH3-02-008-L-03-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2026-02-24 | 2026-03-25 | 18-May-25 A | 2025-11-09 | 312762.1 | 312762.1 | 35657033% | Planned Total Cost | [16 empty] | 35657.03 | 35657.03 |  | 71314.07 | 213942.2
|  |  | JDH3-02-008-L-03-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2026-02-24 | 2026-03-25 | 18-May-25 A | 2025-11-09 | 312762.1 | 312762.1 | 35657033% | Remaining Total Cost | [16 empty] | 43808.23
|  |  | JDH3-02-008-L-03-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2026-02-24 | 2026-03-25 | 18-May-25 A | 2025-11-09 | 312762.1 | 312762.1 | 35657033% | Actual Total Cost | [10 empty] | 17338.06 |  |  | 267918.2 | 25932.79 | 1573.05
|  |  | JDH3-02-008-L-03-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2026-02-26 | 2026-04-06 | 15-May-25 A | 2025-11-18 | 1907-01-27 06:00 | 1907-01-27 06:00 | 7300088% | Planned Total Cost | [16 empty] | 42132.45 |  |  | 2594.2 | 15499.08 | 12775.15
|  |  | JDH3-02-008-L-03-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2026-02-26 | 2026-04-06 | 15-May-25 A | 2025-11-18 | 1907-01-27 06:00 | 1907-01-27 06:00 | 7300088% | Remaining Total Cost | [16 empty] | 70416.63
|  |  | JDH3-02-008-L-03-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2026-02-26 | 2026-04-06 | 15-May-25 A | 2025-11-18 | 1907-01-27 06:00 | 1907-01-27 06:00 | 7300088% | Actual Total Cost | [10 empty] | 64.1 | 170.68 | 362.77 | 974.61 | 974.61 | 37.48
|  |  | JDH3-02-008-L-03-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-03-01 | 2026-04-01 | 10-May-25 A | 2025-12-08 | 2001-03-06 16:34 | 2001-03-06 16:34 | 5475066% | Planned Total Cost | [17 empty] | 8212.6 |  |  | 46538.06
|  |  | JDH3-02-008-L-03-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-03-01 | 2026-04-01 | 10-May-25 A | 2025-12-08 | 2001-03-06 16:34 | 2001-03-06 16:34 | 5475066% | Remaining Total Cost | [16 empty] | 9581.36 | 8212.6
|  |  | JDH3-02-008-L-03-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-03-01 | 2026-04-01 | 10-May-25 A | 2025-12-08 | 2001-03-06 16:34 | 2001-03-06 16:34 | 5475066% | Actual Total Cost | [10 empty] | 26638.74 | 3822.11 | 2192.35 | 2111.15 | 2111.15 | 81.2
|  |  | JDH3-02-008-L-03-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-03-29 | 2026-04-08 | 16-Aug-25 A | 2026-03-14 | 2015-12-28 13:55 | 2015-12-28 13:55 | 8473316% | Planned Total Cost | [16 empty] | 29656.61 |  |  |  | 44484.91 | 10591.64
|  |  | JDH3-02-008-L-03-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-03-29 | 2026-04-08 | 16-Aug-25 A | 2026-03-14 | 2015-12-28 13:55 | 2015-12-28 13:55 | 8473316% | Remaining Total Cost | [16 empty] | 29656.61 |  |  |  | 12709.97
|  |  | JDH3-02-008-L-03-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-03-29 | 2026-04-08 | 16-Aug-25 A | 2026-03-14 | 2015-12-28 13:55 | 2015-12-28 13:55 | 8473316% | Actual Total Cost | [13 empty] | 42366.58
|  |  | JDH3-02-008-L-03-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-03-31 | 2026-04-13 | 2025-11-06 | 2026-03-16 | 0 | 0 | 19358266% | Planned Total Cost | [16 empty] | 174224.39 |  |  |  | 19358.27
|  |  | JDH3-02-008-L-03-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-03-31 | 2026-04-13 | 2025-11-06 | 2026-03-16 | 0 | 0 | 19358266% | Remaining Total Cost | [16 empty] | 174224.39 |  |  |  | 19358.27
|  |  | JDH3-02-008-L-03-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-03-31 | 2026-04-13 | 2025-11-06 | 2026-03-16 | 0 | 0 | 19358266% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(ST)- Single Catchbasine Works |  | 2026-04-02 | 2026-04-20 | 2025-11-09 | 2026-03-19 | 0 | 0 | 10167984% | Planned Total Cost | [16 empty] | 96595.85 |  |  |  | 5083.99
|  |  | JDH3-02-008-L-03-(ST)- Single Catchbasine Works |  | 2026-04-02 | 2026-04-20 | 2025-11-09 | 2026-03-19 | 0 | 0 | 10167984% | Remaining Total Cost | [16 empty] | 96595.85 |  |  |  | 5083.99
|  |  | JDH3-02-008-L-03-(ST)- Single Catchbasine Works |  | 2026-04-02 | 2026-04-20 | 2025-11-09 | 2026-03-19 | 0 | 0 | 10167984% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(ST)- Double Catchbasine Works |  | 2026-04-06 | 2026-04-23 | 2025-11-12 | 2026-03-23 | 0 | 0 | 29546445% | Planned Total Cost | [16 empty] | 280691.23 |  |  |  | 14773.22
|  |  | JDH3-02-008-L-03-(ST)- Double Catchbasine Works |  | 2026-04-06 | 2026-04-23 | 2025-11-12 | 2026-03-23 | 0 | 0 | 29546445% | Remaining Total Cost | [16 empty] | 280691.23 |  |  |  | 14773.22
|  |  | JDH3-02-008-L-03-(ST)- Double Catchbasine Works |  | 2026-04-06 | 2026-04-23 | 2025-11-12 | 2026-03-23 | 0 | 0 | 29546445% | Actual Total Cost
|  |  | JDH3-02-008-L-03-TSE Network - TSE |  | 2026-04-25 | 2026-07-04 | 05-Dec-24 A | 2026-02-19 | 2188-05-07 21:07 | 2188-05-07 21:22 | 157166959% | Planned Total Cost | [16 empty] | 537904.46 | 763708.18 | 5150.62 | 197283.14 |  | 15028.28 | 45080.78 | 7514.14
|  |  | JDH3-02-008-L-03-TSE Network - TSE |  | 2026-04-25 | 2026-07-04 | 05-Dec-24 A | 2026-02-19 | 2188-05-07 21:07 | 2188-05-07 21:22 | 157166959% | Remaining Total Cost | [16 empty] | 537904.46 | 726011.5 | 5150.62 | 197283.14
|  |  | JDH3-02-008-L-03-TSE Network - TSE |  | 2026-04-25 | 2026-07-04 | 05-Dec-24 A | 2026-02-19 | 2188-05-07 21:07 | 2188-05-07 21:22 | 157166959% | Actual Total Cost | [5 empty] | 1502828% | 28292.67 | 21484.45 | 2817.8 | [5 empty] | 37696.69
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-04-25 | 2026-06-13 | 05-Dec-24 A | 2025-12-15 | 2085-02-20 04:48 | 2085-02-20 04:48 | 12876937% | Planned Total Cost | [16 empty] | 9013.86 | 52132.32 |  |  |  | 15028.28 | 45080.78 | 7514.14
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-04-25 | 2026-06-13 | 05-Dec-24 A | 2025-12-15 | 2085-02-20 04:48 | 2085-02-20 04:48 | 12876937% | Remaining Total Cost | [16 empty] | 9013.86 | 52132.32
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-04-25 | 2026-06-13 | 05-Dec-24 A | 2025-12-15 | 2085-02-20 04:48 | 2085-02-20 04:48 | 12876937% | Actual Total Cost | [5 empty] | 1502828% | 28292.67 | 21484.45 | 2817.8
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-05-04 | 2026-07-01 | 2025-12-06 | 2026-02-14 | 0 | 0 | 43166348% | Planned Total Cost | [17 empty] | 388497.13 |  | 43166.35
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-05-04 | 2026-07-01 | 2025-12-06 | 2026-02-14 | 0 | 0 | 43166348% | Remaining Total Cost | [17 empty] | 388497.13 |  | 43166.35
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-05-04 | 2026-07-01 | 2025-12-06 | 2026-02-14 | 0 | 0 | 43166348% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2026-05-11 | 2026-06-14 | 2025-12-13 | 2026-02-12 | 0 | 0 | 3896521% | Planned Total Cost | [17 empty] | 35068.69 |  | 3896.52
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2026-05-11 | 2026-06-14 | 2025-12-13 | 2026-02-12 | 0 | 0 | 3896521% | Remaining Total Cost | [17 empty] | 35068.69 |  | 3896.52
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2026-05-11 | 2026-06-14 | 2025-12-13 | 2026-02-12 | 0 | 0 | 3896521% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2026-05-13 | 2026-06-16 | 2025-12-15 | 2026-02-15 | 0 | 0 | 9411494% | Planned Total Cost | [17 empty] | 84703.45 |  | 9411.49
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2026-05-13 | 2026-06-16 | 2025-12-15 | 2026-02-15 | 0 | 0 | 9411494% | Remaining Total Cost | [17 empty] | 84703.45 |  | 9411.49
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2026-05-13 | 2026-06-16 | 2025-12-15 | 2026-02-15 | 0 | 0 | 9411494% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 2.51 to 3.5 m |  | 2026-05-16 | 2026-06-18 | 2025-12-17 | 2026-02-17 | 0 | 0 | 5367484% | Planned Total Cost | [17 empty] | 48307.36 |  | 5367.48
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 2.51 to 3.5 m |  | 2026-05-16 | 2026-06-18 | 2025-12-17 | 2026-02-17 | 0 | 0 | 5367484% | Remaining Total Cost | [17 empty] | 48307.36 |  | 5367.48
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 2.51 to 3.5 m |  | 2026-05-16 | 2026-06-18 | 2025-12-17 | 2026-02-17 | 0 | 0 | 5367484% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-05-18 | 2026-06-21 | 02-Sep-25 A | 2026-02-19 | 1977-02-01 14:24 | 1977-02-01 14:24 | 11263039% | Planned Total Cost | [16 empty] | 73209.75 | 28157.6 |  | 11263.04
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-05-18 | 2026-06-21 | 02-Sep-25 A | 2026-02-19 | 1977-02-01 14:24 | 1977-02-01 14:24 | 11263039% | Remaining Total Cost | [16 empty] | 73209.75 |  |  | 11263.04
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-05-18 | 2026-06-21 | 02-Sep-25 A | 2026-02-19 | 1977-02-01 14:24 | 1977-02-01 14:24 | 11263039% | Actual Total Cost | [14 empty] | 28157.6
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-05-20 | 2026-05-31 | 02-Sep-25 A | 2025-11-13 | 1926-02-11 02:10 | 1926-02-11 02:10 | 3815636% | Planned Total Cost | [16 empty] | 28617.27 | 9539.09
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-05-20 | 2026-05-31 | 02-Sep-25 A | 2025-11-13 | 1926-02-11 02:10 | 1926-02-11 02:10 | 3815636% | Remaining Total Cost | [16 empty] | 28617.27
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-05-20 | 2026-05-31 | 02-Sep-25 A | 2025-11-13 | 1926-02-11 02:10 | 1926-02-11 02:10 | 3815636% | Actual Total Cost | [14 empty] | 9539.09
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 0 to 1.5 m |  | 2026-05-23 | 2026-06-02 | 2025-11-06 | 2025-11-18 | 0 | 0 | 20299137% | Planned Total Cost | [16 empty] | 202991.37
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 0 to 1.5 m |  | 2026-05-23 | 2026-06-02 | 2025-11-06 | 2025-11-18 | 0 | 0 | 20299137% | Remaining Total Cost | [16 empty] | 202991.37
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 0 to 1.5 m |  | 2026-05-23 | 2026-06-02 | 2025-11-06 | 2025-11-18 | 0 | 0 | 20299137% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 1.51 to 2.5 m |  | 2026-05-25 | 2026-06-04 | 2025-11-09 | 2025-11-20 | 0 | 0 | 8214801% | Planned Total Cost | [16 empty] | 82148.01
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 1.51 to 2.5 m |  | 2026-05-25 | 2026-06-04 | 2025-11-09 | 2025-11-20 | 0 | 0 | 8214801% | Remaining Total Cost | [16 empty] | 82148.01
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 1.51 to 2.5 m |  | 2026-05-25 | 2026-06-04 | 2025-11-09 | 2025-11-20 | 0 | 0 | 8214801% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 2.51 to 3.5 m |  | 2026-05-27 | 2026-06-07 | 2025-11-11 | 2025-11-23 | 0 | 0 | 4258616% | Planned Total Cost | [16 empty] | 42586.16
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 2.51 to 3.5 m |  | 2026-05-27 | 2026-06-07 | 2025-11-11 | 2025-11-23 | 0 | 0 | 4258616% | Remaining Total Cost | [16 empty] | 42586.16
|  |  | JDH3-02-008-L-03-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 2.51 to 3.5 m |  | 2026-05-27 | 2026-06-07 | 2025-11-11 | 2025-11-23 | 0 | 0 | 4258616% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(TSE)-Supply and install gate valves-100 mm |  | 2026-06-03 | 2026-06-11 | 2025-12-24 | 2026-01-03 | 0 | 0 | 2069056% | Planned Total Cost | [17 empty] | 19989.67 | 700.89
|  |  | JDH3-02-008-L-03-(TSE)-Supply and install gate valves-100 mm |  | 2026-06-03 | 2026-06-11 | 2025-12-24 | 2026-01-03 | 0 | 0 | 2069056% | Remaining Total Cost | [17 empty] | 19989.67 | 700.89
|  |  | JDH3-02-008-L-03-(TSE)-Supply and install gate valves-100 mm |  | 2026-06-03 | 2026-06-11 | 2025-12-24 | 2026-01-03 | 0 | 0 | 2069056% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(TSE)-Supply and install gate valves-250 mm |  | 2026-06-03 | 2026-06-09 | 2025-12-24 | 2025-12-31 | 0 | 0 | 3079336% | Planned Total Cost | [17 empty] | 30793.36
|  |  | JDH3-02-008-L-03-(TSE)-Supply and install gate valves-250 mm |  | 2026-06-03 | 2026-06-09 | 2025-12-24 | 2025-12-31 | 0 | 0 | 3079336% | Remaining Total Cost | [17 empty] | 30793.36
|  |  | JDH3-02-008-L-03-(TSE)-Supply and install gate valves-250 mm |  | 2026-06-03 | 2026-06-09 | 2025-12-24 | 2025-12-31 | 0 | 0 | 3079336% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2026-06-03 | 2026-06-07 | 2026-02-07 | 2026-02-10 | 0 | 0 | 3067992% | Planned Total Cost | [19 empty] | 30679.92
|  |  | JDH3-02-008-L-03-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2026-06-03 | 2026-06-07 | 2026-02-07 | 2026-02-10 | 0 | 0 | 3067992% | Remaining Total Cost | [19 empty] | 30679.92
|  |  | JDH3-02-008-L-03-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2026-06-03 | 2026-06-07 | 2026-02-07 | 2026-02-10 | 0 | 0 | 3067992% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(TSE)-Supply and install of butterfly valves-600 mm. |  | 2026-06-03 | 2026-06-07 | 2026-02-07 | 2026-02-10 | 0 | 0 | 9315041% | Planned Total Cost | [19 empty] | 93150.41
|  |  | JDH3-02-008-L-03-(TSE)-Supply and install of butterfly valves-600 mm. |  | 2026-06-03 | 2026-06-07 | 2026-02-07 | 2026-02-10 | 0 | 0 | 9315041% | Remaining Total Cost | [19 empty] | 93150.41
|  |  | JDH3-02-008-L-03-(TSE)-Supply and install of butterfly valves-600 mm. |  | 2026-06-03 | 2026-06-07 | 2026-02-07 | 2026-02-10 | 0 | 0 | 9315041% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-06-03 | 2026-06-07 | 2025-12-24 | 2025-12-29 | 0 | 0 | 3916758% | Planned Total Cost | [17 empty] | 39167.58
|  |  | JDH3-02-008-L-03-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-06-03 | 2026-06-07 | 2025-12-24 | 2025-12-29 | 0 | 0 | 3916758% | Remaining Total Cost | [17 empty] | 39167.58
|  |  | JDH3-02-008-L-03-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-06-03 | 2026-06-07 | 2025-12-24 | 2025-12-29 | 0 | 0 | 3916758% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-06-03 | 2026-06-07 | 2025-12-24 | 2025-12-29 | 0 | 0 | 1488827% | Planned Total Cost | [17 empty] | 14888.27
|  |  | JDH3-02-008-L-03-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-06-03 | 2026-06-07 | 2025-12-24 | 2025-12-29 | 0 | 0 | 1488827% | Remaining Total Cost | [17 empty] | 14888.27
|  |  | JDH3-02-008-L-03-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-06-03 | 2026-06-07 | 2025-12-24 | 2025-12-29 | 0 | 0 | 1488827% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(TSE)-Supply and install of Air valves-65 mm. |  | 2026-06-03 | 2026-06-07 | 2025-12-24 | 2025-12-29 | 0 | 0 | 824649% | Planned Total Cost | [17 empty] | 8246.49
|  |  | JDH3-02-008-L-03-(TSE)-Supply and install of Air valves-65 mm. |  | 2026-06-03 | 2026-06-07 | 2025-12-24 | 2025-12-29 | 0 | 0 | 824649% | Remaining Total Cost | [17 empty] | 8246.49
|  |  | JDH3-02-008-L-03-(TSE)-Supply and install of Air valves-65 mm. |  | 2026-06-03 | 2026-06-07 | 2025-12-24 | 2025-12-29 | 0 | 0 | 824649% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-05-30 | 2026-06-07 | 2025-11-13 | 2025-11-23 | 0 | 0 | 1820460% | Planned Total Cost | [16 empty] | 18204.6
|  |  | JDH3-02-008-L-03-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-05-30 | 2026-06-07 | 2025-11-13 | 2025-11-23 | 0 | 0 | 1820460% | Remaining Total Cost | [16 empty] | 18204.6
|  |  | JDH3-02-008-L-03-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-05-30 | 2026-06-07 | 2025-11-13 | 2025-11-23 | 0 | 0 | 1820460% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(TSE)- Supply and Construct R.C Valves Chamber on 500-630 mm Diameter pipelines |  | 2026-06-01 | 2026-06-09 | 2025-11-16 | 2025-12-31 | 0 | 0 | 2430278% | Planned Total Cost | [16 empty] | 21872.5 | 2430.28
|  |  | JDH3-02-008-L-03-(TSE)- Supply and Construct R.C Valves Chamber on 500-630 mm Diameter pipelines |  | 2026-06-01 | 2026-06-09 | 2025-11-16 | 2025-12-31 | 0 | 0 | 2430278% | Remaining Total Cost | [16 empty] | 21872.5 | 2430.28
|  |  | JDH3-02-008-L-03-(TSE)- Supply and Construct R.C Valves Chamber on 500-630 mm Diameter pipelines |  | 2026-06-01 | 2026-06-09 | 2025-11-16 | 2025-12-31 | 0 | 0 | 2430278% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-06-03 | 2026-06-11 | 2025-11-18 | 2026-01-03 | 0 | 0 | 5540766% | Planned Total Cost | [16 empty] | 49866.89 | 1786.9 | 3753.87
|  |  | JDH3-02-008-L-03-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-06-03 | 2026-06-11 | 2025-11-18 | 2026-01-03 | 0 | 0 | 5540766% | Remaining Total Cost | [16 empty] | 49866.89 | 1786.9 | 3753.87
|  |  | JDH3-02-008-L-03-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-06-03 | 2026-06-11 | 2025-11-18 | 2026-01-03 | 0 | 0 | 5540766% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-06-06 | 2026-06-14 | 2025-11-20 | 2026-01-05 | 0 | 0 | 695855% | Planned Total Cost | [16 empty] | 6262.7 |  | 695.86
|  |  | JDH3-02-008-L-03-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-06-06 | 2026-06-14 | 2025-11-20 | 2026-01-05 | 0 | 0 | 695855% | Remaining Total Cost | [16 empty] | 6262.7 |  | 695.86
|  |  | JDH3-02-008-L-03-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-06-06 | 2026-06-14 | 2025-11-20 | 2026-01-05 | 0 | 0 | 695855% | Actual Total Cost
|  |  | JDH3-02-008-L-03-(TSE)- Supply and Construct Air Valves Chamber on 355-630 mm Diameter pipelines |  | 2026-06-08 | 2026-07-04 | 2025-11-23 | 2026-02-16 | 0 | 0 | 347928% | Planned Total Cost | [16 empty] | 3131.35 |  |  | 347.93
|  |  | JDH3-02-008-L-03-(TSE)- Supply and Construct Air Valves Chamber on 355-630 mm Diameter pipelines |  | 2026-06-08 | 2026-07-04 | 2025-11-23 | 2026-02-16 | 0 | 0 | 347928% | Remaining Total Cost | [16 empty] | 3131.35 |  |  | 347.93
|  |  | JDH3-02-008-L-03-(TSE)- Supply and Construct Air Valves Chamber on 355-630 mm Diameter pipelines |  | 2026-06-08 | 2026-07-04 | 2025-11-23 | 2026-02-16 | 0 | 0 | 347928% | Actual Total Cost
|  |  | L-17 |  | 2025-09-03 | 2026-01-12 | 07-Jul-25 A | 2026-03-10 | 0 | 0 | 149897547% | Planned Total Cost | [16 empty] | 178822.76 | 680904.45 | 516021.01 | 93164.8 | 30062.45
|  |  | L-17 |  | 2025-09-03 | 2026-01-12 | 07-Jul-25 A | 2026-03-10 | 0 | 0 | 149897547% | Remaining Total Cost | [16 empty] | 178822.76 | 680904.45 | 516021.01 | 93164.8 | 30062.45
|  |  | L-17 |  | 2025-09-03 | 2026-01-12 | 07-Jul-25 A | 2026-03-10 | 0 | 0 | 149897547% | Actual Total Cost
|  |  | JDH3-02-008-L-17-Sewage Network - SS |  | 2025-09-11 | 2026-01-12 | 2025-11-06 | 2026-03-10 | 0 | 0 | 149897547% | Planned Total Cost | [16 empty] | 178822.76 | 680904.45 | 516021.01 | 93164.8 | 30062.45
|  |  | JDH3-02-008-L-17-Sewage Network - SS |  | 2025-09-11 | 2026-01-12 | 2025-11-06 | 2026-03-10 | 0 | 0 | 149897547% | Remaining Total Cost | [16 empty] | 178822.76 | 680904.45 | 516021.01 | 93164.8 | 30062.45
|  |  | JDH3-02-008-L-17-Sewage Network - SS |  | 2025-09-11 | 2026-01-12 | 2025-11-06 | 2026-03-10 | 0 | 0 | 149897547% | Actual Total Cost
|  |  | JDH3-02-008-L-17-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2025-09-11 | 2026-01-12 | 2025-11-06 | 2026-03-10 | 0 | 0 | 75560905% | Planned Total Cost | [16 empty] | 156673.44 | 64782.98 | 410925.39 | 93164.8 | 30062.45
|  |  | JDH3-02-008-L-17-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2025-09-11 | 2026-01-12 | 2025-11-06 | 2026-03-10 | 0 | 0 | 75560905% | Remaining Total Cost | [16 empty] | 156673.44 | 64782.98 | 410925.39 | 93164.8 | 30062.45
|  |  | JDH3-02-008-L-17-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2025-09-11 | 2026-01-12 | 2025-11-06 | 2026-03-10 | 0 | 0 | 75560905% | Actual Total Cost
|  |  | JDH3-02-008-L-17-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2025-10-02 | 2025-11-03 | 2025-11-27 | 2025-12-30 | 0 | 0 | 20935089% | Planned Total Cost | [16 empty] | 22149.32 | 187201.56
|  |  | JDH3-02-008-L-17-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2025-10-02 | 2025-11-03 | 2025-11-27 | 2025-12-30 | 0 | 0 | 20935089% | Remaining Total Cost | [16 empty] | 22149.32 | 187201.56
|  |  | JDH3-02-008-L-17-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2025-10-02 | 2025-11-03 | 2025-11-27 | 2025-12-30 | 0 | 0 | 20935089% | Actual Total Cost
|  |  | JDH3-02-008-L-17-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 2.51 to 3.5 m. |  | 2025-10-08 | 2025-10-20 | 2025-12-03 | 2025-12-16 | 0 | 0 | 7189387% | Planned Total Cost | [17 empty] | 71893.87
|  |  | JDH3-02-008-L-17-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 2.51 to 3.5 m. |  | 2025-10-08 | 2025-10-20 | 2025-12-03 | 2025-12-16 | 0 | 0 | 7189387% | Remaining Total Cost | [17 empty] | 71893.87
|  |  | JDH3-02-008-L-17-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 2.51 to 3.5 m. |  | 2025-10-08 | 2025-10-20 | 2025-12-03 | 2025-12-16 | 0 | 0 | 7189387% | Actual Total Cost
|  |  | JDH3-02-008-L-17-(SS)-MH WORKS from 0.00 to 1.50 @ 1200 mm |  | 2025-10-11 | 2025-10-21 | 2025-12-06 | 2025-12-17 | 0 | 0 | 912511% | Planned Total Cost | [17 empty] | 9125.11
|  |  | JDH3-02-008-L-17-(SS)-MH WORKS from 0.00 to 1.50 @ 1200 mm |  | 2025-10-11 | 2025-10-21 | 2025-12-06 | 2025-12-17 | 0 | 0 | 912511% | Remaining Total Cost | [17 empty] | 9125.11
|  |  | JDH3-02-008-L-17-(SS)-MH WORKS from 0.00 to 1.50 @ 1200 mm |  | 2025-10-11 | 2025-10-21 | 2025-12-06 | 2025-12-17 | 0 | 0 | 912511% | Actual Total Cost
|  |  | JDH3-02-008-L-17-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2025-10-13 | 2025-11-22 | 2025-12-08 | 2026-01-18 | 0 | 0 | 29200353% | Planned Total Cost | [17 empty] | 213914.48 | 78089.04
|  |  | JDH3-02-008-L-17-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2025-10-13 | 2025-11-22 | 2025-12-08 | 2026-01-18 | 0 | 0 | 29200353% | Remaining Total Cost | [17 empty] | 213914.48 | 78089.04
|  |  | JDH3-02-008-L-17-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2025-10-13 | 2025-11-22 | 2025-12-08 | 2026-01-18 | 0 | 0 | 29200353% | Actual Total Cost
|  |  | JDH3-02-008-L-17-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2025-10-18 | 2025-11-13 | 2025-12-13 | 2026-01-10 | 0 | 0 | 16099303% | Planned Total Cost | [17 empty] | 133986.45 | 27006.58
|  |  | JDH3-02-008-L-17-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2025-10-18 | 2025-11-13 | 2025-12-13 | 2026-01-10 | 0 | 0 | 16099303% | Remaining Total Cost | [17 empty] | 133986.45 | 27006.58
|  |  | JDH3-02-008-L-17-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2025-10-18 | 2025-11-13 | 2025-12-13 | 2026-01-10 | 0 | 0 | 16099303% | Actual Total Cost
|  |  | L-34 |  | 2026-01-13 | 2026-05-05 | 18-Nov-24 A | 2026-02-19 | 557328.53 | 557328.54 | 210501070% | Planned Total Cost | [15 empty] | 1097049.03 | 27721.31 |  | 8782.14 | 356244.1 | 99904.57 | 442147.35 | 73162.21
|  |  | L-34 |  | 2026-01-13 | 2026-05-05 | 18-Nov-24 A | 2026-02-19 | 557328.53 | 557328.54 | 210501070% | Remaining Total Cost | [15 empty] | 1378788.23 | 27721.31 |  |  | 141172.62
|  |  | L-34 |  | 2026-01-13 | 2026-05-05 | 18-Nov-24 A | 2026-02-19 | 557328.53 | 557328.54 | 210501070% | Actual Total Cost | [5 empty] | 1184097% | 16203.44 | 14957.02 | 29344.13 | 24622.6 | 30227.79 | 30227.79 | 31390.4 | 57965.92 | 297201.28 | 13347.21
|  |  | JDH3-02-008-L-34-TSE Network - TSE |  | 2026-01-21 | 2026-05-05 | 11-Mar-25 A | 2026-02-19 | 497500.47 | 497500.47 | 202042669% | Planned Total Cost | [15 empty] | 1097049.03 | 2965.36 |  | 8782.14 | 296416.03 | 99904.57 | 442147.35 | 73162.21
|  |  | JDH3-02-008-L-34-TSE Network - TSE |  | 2026-01-21 | 2026-05-05 | 11-Mar-25 A | 2026-02-19 | 497500.47 | 497500.47 | 202042669% | Remaining Total Cost | [15 empty] | 1378788.23 | 2965.36 |  |  | 141172.62
|  |  | JDH3-02-008-L-34-TSE Network - TSE |  | 2026-01-21 | 2026-05-05 | 11-Mar-25 A | 2026-02-19 | 497500.47 | 497500.47 | 202042669% | Actual Total Cost | [8 empty] | 12517.49 | 24622.6 | 30227.79 | 30227.79 | 31390.4 | 57965.92 | 297201.28 | 13347.21
|  |  | JDH3-02-008-L-34-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-01-21 | 2026-02-11 | 2025-10-02 | 2025-10-23 | 0 | 0 | 5482735% | Planned Total Cost | [15 empty] | 54827.35
|  |  | JDH3-02-008-L-34-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-01-21 | 2026-02-11 | 2025-10-02 | 2025-10-23 | 0 | 0 | 5482735% | Remaining Total Cost | [15 empty] | 54827.35
|  |  | JDH3-02-008-L-34-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-01-21 | 2026-02-11 | 2025-10-02 | 2025-10-23 | 0 | 0 | 5482735% | Actual Total Cost
|  |  | JDH3-02-008-L-34-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-01-25 | 2026-05-05 | 11-Mar-25 A | 2025-10-13 | 443841.56 | 443841.56 | 80333987% | Planned Total Cost | [15 empty] | 24100.19 |  |  | 8782.14 | 155243.41 | 99904.57 | 442147.35 | 73162.21
|  |  | JDH3-02-008-L-34-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-01-25 | 2026-05-05 | 11-Mar-25 A | 2025-10-13 | 443841.56 | 443841.56 | 80333987% | Remaining Total Cost | [15 empty] | 359498.31
|  |  | JDH3-02-008-L-34-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-01-25 | 2026-05-05 | 11-Mar-25 A | 2025-10-13 | 443841.56 | 443841.56 | 80333987% | Actual Total Cost | [8 empty] | 12517.49 | 24622.6 | 30227.79 | 30227.79 | 31390.4 | 57965.92 | 247375.15 | 9514.43
|  |  | JDH3-02-008-L-34-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2026-01-25 | 2026-02-05 | 2025-10-06 | 2025-10-18 | 0 | 0 | 11482778% | Planned Total Cost | [15 empty] | 114827.78
|  |  | JDH3-02-008-L-34-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2026-01-25 | 2026-02-05 | 2025-10-06 | 2025-10-18 | 0 | 0 | 11482778% | Remaining Total Cost | [15 empty] | 114827.78
|  |  | JDH3-02-008-L-34-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2026-01-25 | 2026-02-05 | 2025-10-06 | 2025-10-18 | 0 | 0 | 11482778% | Actual Total Cost
|  |  | JDH3-02-008-L-34-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2026-01-27 | 2026-02-07 | 2025-10-08 | 2025-10-19 | 0 | 0 | 237671% | Planned Total Cost | [15 empty] | 2376.71
|  |  | JDH3-02-008-L-34-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2026-01-27 | 2026-02-07 | 2025-10-08 | 2025-10-19 | 0 | 0 | 237671% | Remaining Total Cost | [15 empty] | 2376.71
|  |  | JDH3-02-008-L-34-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2026-01-27 | 2026-02-07 | 2025-10-08 | 2025-10-19 | 0 | 0 | 237671% | Actual Total Cost
|  |  | JDH3-02-008-L-34-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-01-29 | 2026-02-19 | 16-Sep-25 A | 2025-10-28 | 2046-11-27 21:50 | 2046-11-27 21:50 | 35325155% | Planned Total Cost | [15 empty] | 353251.55
|  |  | JDH3-02-008-L-34-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-01-29 | 2026-02-19 | 16-Sep-25 A | 2025-10-28 | 2046-11-27 21:50 | 2046-11-27 21:50 | 35325155% | Remaining Total Cost | [15 empty] | 299592.64
|  |  | JDH3-02-008-L-34-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-01-29 | 2026-02-19 | 16-Sep-25 A | 2025-10-28 | 2046-11-27 21:50 | 2046-11-27 21:50 | 35325155% | Actual Total Cost | [14 empty] | 49826.13 | 3832.78
|  |  | JDH3-02-008-L-34-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-02-02 | 2026-02-14 | 2025-10-11 | 2025-10-22 | 0 | 0 | 14007820% | Planned Total Cost | [15 empty] | 140078.2
|  |  | JDH3-02-008-L-34-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-02-02 | 2026-02-14 | 2025-10-11 | 2025-10-22 | 0 | 0 | 14007820% | Remaining Total Cost | [15 empty] | 140078.2
|  |  | JDH3-02-008-L-34-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-02-02 | 2026-02-14 | 2025-10-11 | 2025-10-22 | 0 | 0 | 14007820% | Actual Total Cost
|  |  | JDH3-02-008-L-34-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 0 to 1.5 m |  | 2026-02-04 | 2026-02-15 | 2025-10-13 | 2025-10-23 | 0 | 0 | 24695168% | Planned Total Cost | [15 empty] | 246951.68
|  |  | JDH3-02-008-L-34-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 0 to 1.5 m |  | 2026-02-04 | 2026-02-15 | 2025-10-13 | 2025-10-23 | 0 | 0 | 24695168% | Remaining Total Cost | [15 empty] | 246951.68
|  |  | JDH3-02-008-L-34-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 0 to 1.5 m |  | 2026-02-04 | 2026-02-15 | 2025-10-13 | 2025-10-23 | 0 | 0 | 24695168% | Actual Total Cost
|  |  | JDH3-02-008-L-34-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 1.51 to 2.5 m |  | 2026-02-07 | 2026-02-17 | 2025-10-15 | 2025-10-26 | 0 | 0 | 827001% | Planned Total Cost | [15 empty] | 8270.01
|  |  | JDH3-02-008-L-34-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 1.51 to 2.5 m |  | 2026-02-07 | 2026-02-17 | 2025-10-15 | 2025-10-26 | 0 | 0 | 827001% | Remaining Total Cost | [15 empty] | 8270.01
|  |  | JDH3-02-008-L-34-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 1.51 to 2.5 m |  | 2026-02-07 | 2026-02-17 | 2025-10-15 | 2025-10-26 | 0 | 0 | 827001% | Actual Total Cost
|  |  | JDH3-02-008-L-34-(TSE)-Supply and install gate valves-100 mm |  | 2026-02-14 | 2026-02-19 | 2025-10-22 | 2025-10-28 | 0 | 0 | 1293160% | Planned Total Cost | [15 empty] | 12931.6
|  |  | JDH3-02-008-L-34-(TSE)-Supply and install gate valves-100 mm |  | 2026-02-14 | 2026-02-19 | 2025-10-22 | 2025-10-28 | 0 | 0 | 1293160% | Remaining Total Cost | [15 empty] | 12931.6
|  |  | JDH3-02-008-L-34-(TSE)-Supply and install gate valves-100 mm |  | 2026-02-14 | 2026-02-19 | 2025-10-22 | 2025-10-28 | 0 | 0 | 1293160% | Actual Total Cost
|  |  | JDH3-02-008-L-34-(TSE)-Supply and install gate valves-250 mm |  | 2026-02-14 | 2026-02-25 | 2025-10-22 | 2025-11-03 | 0 | 0 | 4362393% | Planned Total Cost | [15 empty] | 41006.49 | 2617.44
|  |  | JDH3-02-008-L-34-(TSE)-Supply and install gate valves-250 mm |  | 2026-02-14 | 2026-02-25 | 2025-10-22 | 2025-11-03 | 0 | 0 | 4362393% | Remaining Total Cost | [15 empty] | 41006.49 | 2617.44
|  |  | JDH3-02-008-L-34-(TSE)-Supply and install gate valves-250 mm |  | 2026-02-14 | 2026-02-25 | 2025-10-22 | 2025-11-03 | 0 | 0 | 4362393% | Actual Total Cost
|  |  | JDH3-02-008-L-34-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2026-02-19 | 2026-02-23 | 2026-02-07 | 2026-02-10 | 0 | 0 | 1533996% | Planned Total Cost | [19 empty] | 15339.96
|  |  | JDH3-02-008-L-34-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2026-02-19 | 2026-02-23 | 2026-02-07 | 2026-02-10 | 0 | 0 | 1533996% | Remaining Total Cost | [19 empty] | 15339.96
|  |  | JDH3-02-008-L-34-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2026-02-19 | 2026-02-23 | 2026-02-07 | 2026-02-10 | 0 | 0 | 1533996% | Actual Total Cost
|  |  | JDH3-02-008-L-34-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2026-02-22 | 2026-02-28 | 2026-02-09 | 2026-02-12 | 0 | 0 | 7097445% | Planned Total Cost | [19 empty] | 70974.45
|  |  | JDH3-02-008-L-34-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2026-02-22 | 2026-02-28 | 2026-02-09 | 2026-02-12 | 0 | 0 | 7097445% | Remaining Total Cost | [19 empty] | 70974.45
|  |  | JDH3-02-008-L-34-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2026-02-22 | 2026-02-28 | 2026-02-09 | 2026-02-12 | 0 | 0 | 7097445% | Actual Total Cost
|  |  | JDH3-02-008-L-34-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-02-24 | 2026-02-28 | 2026-02-11 | 2026-02-15 | 0 | 0 | 3916758% | Planned Total Cost | [19 empty] | 39167.58
|  |  | JDH3-02-008-L-34-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-02-24 | 2026-02-28 | 2026-02-11 | 2026-02-15 | 0 | 0 | 3916758% | Remaining Total Cost | [19 empty] | 39167.58
|  |  | JDH3-02-008-L-34-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-02-24 | 2026-02-28 | 2026-02-11 | 2026-02-15 | 0 | 0 | 3916758% | Actual Total Cost
|  |  | JDH3-02-008-L-34-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-02-26 | 2026-03-02 | 2026-02-14 | 2026-02-17 | 0 | 0 | 744414% | Planned Total Cost | [19 empty] | 7444.14
|  |  | JDH3-02-008-L-34-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-02-26 | 2026-03-02 | 2026-02-14 | 2026-02-17 | 0 | 0 | 744414% | Remaining Total Cost | [19 empty] | 7444.14
|  |  | JDH3-02-008-L-34-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-02-26 | 2026-03-02 | 2026-02-14 | 2026-02-17 | 0 | 0 | 744414% | Actual Total Cost
|  |  | JDH3-02-008-L-34-(TSE)-Supply and install of Air valves-65 mm. |  | 2026-03-01 | 2026-03-04 | 2026-02-16 | 2026-02-19 | 0 | 0 | 824649% | Planned Total Cost | [19 empty] | 8246.49
|  |  | JDH3-02-008-L-34-(TSE)-Supply and install of Air valves-65 mm. |  | 2026-03-01 | 2026-03-04 | 2026-02-16 | 2026-02-19 | 0 | 0 | 824649% | Remaining Total Cost | [19 empty] | 8246.49
|  |  | JDH3-02-008-L-34-(TSE)-Supply and install of Air valves-65 mm. |  | 2026-03-01 | 2026-03-04 | 2026-02-16 | 2026-02-19 | 0 | 0 | 824649% | Actual Total Cost
|  |  | JDH3-02-008-L-34-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-02-09 | 2026-02-17 | 2025-10-18 | 2025-10-26 | 0 | 0 | 3640919% | Planned Total Cost | [15 empty] | 36409.19
|  |  | JDH3-02-008-L-34-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-02-09 | 2026-02-17 | 2025-10-18 | 2025-10-26 | 0 | 0 | 3640919% | Remaining Total Cost | [15 empty] | 36409.19
|  |  | JDH3-02-008-L-34-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-02-09 | 2026-02-17 | 2025-10-18 | 2025-10-26 | 0 | 0 | 3640919% | Actual Total Cost
|  |  | JDH3-02-008-L-34-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-02-11 | 2026-02-19 | 2025-10-20 | 2025-10-28 | 0 | 0 | 5540766% | Planned Total Cost | [15 empty] | 55407.66
|  |  | JDH3-02-008-L-34-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-02-11 | 2026-02-19 | 2025-10-20 | 2025-10-28 | 0 | 0 | 5540766% | Remaining Total Cost | [15 empty] | 55407.66
|  |  | JDH3-02-008-L-34-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-02-11 | 2026-02-19 | 2025-10-20 | 2025-10-28 | 0 | 0 | 5540766% | Actual Total Cost
|  |  | JDH3-02-008-L-34-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-02-14 | 2026-02-22 | 2025-10-22 | 2025-10-30 | 0 | 0 | 347928% | Planned Total Cost | [15 empty] | 3479.28
|  |  | JDH3-02-008-L-34-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-02-14 | 2026-02-22 | 2025-10-22 | 2025-10-30 | 0 | 0 | 347928% | Remaining Total Cost | [15 empty] | 3479.28
|  |  | JDH3-02-008-L-34-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-02-14 | 2026-02-22 | 2025-10-22 | 2025-10-30 | 0 | 0 | 347928% | Actual Total Cost
|  |  | JDH3-02-008-L-34-(TSE)- Supply and Construct Air Valves Chamber on 355-630 mm Diameter pipelines |  | 2026-02-16 | 2026-02-24 | 2025-10-25 | 2025-11-02 | 0 | 0 | 347928% | Planned Total Cost | [15 empty] | 3131.35 | 347.93
|  |  | JDH3-02-008-L-34-(TSE)- Supply and Construct Air Valves Chamber on 355-630 mm Diameter pipelines |  | 2026-02-16 | 2026-02-24 | 2025-10-25 | 2025-11-02 | 0 | 0 | 347928% | Remaining Total Cost | [15 empty] | 3131.35 | 347.93
|  |  | JDH3-02-008-L-34-(TSE)- Supply and Construct Air Valves Chamber on 355-630 mm Diameter pipelines |  | 2026-02-16 | 2026-02-24 | 2025-10-25 | 2025-11-02 | 0 | 0 | 347928% | Actual Total Cost
|  |  | JDH3-02-008-L-34-Road Works - RD |  | 2026-02-16 | 2026-03-01 | 10-Dec-24 A | 2025-11-06 | 2063-10-19 01:41 | 2063-10-19 01:41 | 8458402% | Planned Total Cost | [16 empty] | 24755.95 |  |  | 59828.07
|  |  | JDH3-02-008-L-34-Road Works - RD |  | 2026-02-16 | 2026-03-01 | 10-Dec-24 A | 2025-11-06 | 2063-10-19 01:41 | 2063-10-19 01:41 | 8458402% | Remaining Total Cost | [16 empty] | 24755.95
|  |  | JDH3-02-008-L-34-Road Works - RD |  | 2026-02-16 | 2026-03-01 | 10-Dec-24 A | 2025-11-06 | 2063-10-19 01:41 | 2063-10-19 01:41 | 8458402% | Actual Total Cost | [5 empty] | 1184097% | 16203.44 | 14957.02 | 16826.64
|  |  | JDH3-02-008-L-34-(RD)-Precast Concrete Curb |  | 2026-02-16 | 2026-03-01 | 10-Dec-24 A | 2025-11-06 | 2063-10-19 01:41 | 2063-10-19 01:41 | 8458402% | Planned Total Cost | [16 empty] | 24755.95 |  |  | 59828.07
|  |  | JDH3-02-008-L-34-(RD)-Precast Concrete Curb |  | 2026-02-16 | 2026-03-01 | 10-Dec-24 A | 2025-11-06 | 2063-10-19 01:41 | 2063-10-19 01:41 | 8458402% | Remaining Total Cost | [16 empty] | 24755.95
|  |  | JDH3-02-008-L-34-(RD)-Precast Concrete Curb |  | 2026-02-16 | 2026-03-01 | 10-Dec-24 A | 2025-11-06 | 2063-10-19 01:41 | 2063-10-19 01:41 | 8458402% | Actual Total Cost | [5 empty] | 1184097% | 16203.44 | 14957.02 | 16826.64
|  |  | L-51 |  | 2025-09-11 | 2026-07-08 | 01-Dec-24 A | 2026-07-20 | 3473881.21 | 3473881.25 | 927165193% | Planned Total Cost | [14 empty] | 572442.83 | 264002.09 | 1484749.84 | 560799.64 | 214926.55 | 1627734 | 1250507.09 | 768568.14 | 1604088.86 | 727317.83 | 196515.06
|  |  | L-51 |  | 2025-09-11 | 2026-07-08 | 01-Dec-24 A | 2026-07-20 | 3473881.21 | 3473881.25 | 927165193% | Remaining Total Cost | [16 empty] | 1720564.45 | 560799.64 | 48549.16 |  | 601676.98 | 582542.97 | 1368848.72 | 718273.73 | 196515.06
|  |  | L-51 |  | 2025-09-11 | 2026-07-08 | 01-Dec-24 A | 2026-07-20 | 3473881.21 | 3473881.25 | 927165193% | Actual Total Cost | [5 empty] | 11142857% | 684061.79 | 189811.35 | 167847.42 | 445834.02 | 286256.44 | 299145.05 | 316203.98 | 360751.21 | 572666.5 | 39874.93
|  |  | JDH3-02-008-L-51-Sewage Network - SS |  | 2025-09-20 | 2025-10-16 | 16-Dec-24 A | 2025-11-11 | 357749.91 | 357749.91 | 37901268% | Planned Total Cost | [14 empty] | 238371.8 | 119378.11 | 21262.77
|  |  | JDH3-02-008-L-51-Sewage Network - SS |  | 2025-09-20 | 2025-10-16 | 16-Dec-24 A | 2025-11-11 | 357749.91 | 357749.91 | 37901268% | Remaining Total Cost | [16 empty] | 21262.77
|  |  | JDH3-02-008-L-51-Sewage Network - SS |  | 2025-09-20 | 2025-10-16 | 16-Dec-24 A | 2025-11-11 | 357749.91 | 357749.91 | 37901268% | Actual Total Cost | [5 empty] | 7994286% | 179787.79 | 38620.46 |  | 1652.3 | 1652.3 | 762.6 |  | 55331.61
|  |  | JDH3-02-008-L-51-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 0 to 1.5 m. |  | 2025-09-20 | 2025-09-30 | 21-Dec-24 A | 14-Jun-25 A | 2011-05-08 22:34 | 2011-05-08 22:34 | 4067194% | Planned Total Cost | [14 empty] | 40671.94
|  |  | JDH3-02-008-L-51-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 0 to 1.5 m. |  | 2025-09-20 | 2025-09-30 | 21-Dec-24 A | 14-Jun-25 A | 2011-05-08 22:34 | 2011-05-08 22:34 | 4067194% | Remaining Total Cost
|  |  | JDH3-02-008-L-51-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 0 to 1.5 m. |  | 2025-09-20 | 2025-09-30 | 21-Dec-24 A | 14-Jun-25 A | 2011-05-08 22:34 | 2011-05-08 22:34 | 4067194% | Actual Total Cost | [5 empty] | 328341% | 28936.39 | 4384.95 |  | 1652.3 | 1652.3 | 762.6
|  |  | JDH3-02-008-L-51-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2025-09-20 | 2025-09-30 | 31-Dec-24 A | 18-Aug-25 A | 1943-04-19 08:10 | 1943-04-19 08:10 | 1581534% | Planned Total Cost | [14 empty] | 15815.34
|  |  | JDH3-02-008-L-51-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2025-09-20 | 2025-09-30 | 31-Dec-24 A | 18-Aug-25 A | 1943-04-19 08:10 | 1943-04-19 08:10 | 1581534% | Remaining Total Cost
|  |  | JDH3-02-008-L-51-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2025-09-20 | 2025-09-30 | 31-Dec-24 A | 18-Aug-25 A | 1943-04-19 08:10 | 1943-04-19 08:10 | 1581534% | Actual Total Cost | [5 empty] | 19769% | 10230.55 | 3805.57 | [5 empty] | 1581.53
|  |  | JDH3-02-008-L-51-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 1.51 to 2.5 m. |  | 2025-09-20 | 2025-10-13 | 16-Dec-24 A | 16-Feb-25 A | 2278-04-11 06:00 | 2278-04-11 06:14 | 13816425% | Planned Total Cost | [14 empty] | 72536.23 | 65628.02
|  |  | JDH3-02-008-L-51-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 1.51 to 2.5 m. |  | 2025-09-20 | 2025-10-13 | 16-Dec-24 A | 16-Feb-25 A | 2278-04-11 06:00 | 2278-04-11 06:14 | 13816425% | Remaining Total Cost
|  |  | JDH3-02-008-L-51-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 1.51 to 2.5 m. |  | 2025-09-20 | 2025-10-13 | 16-Dec-24 A | 16-Feb-25 A | 2278-04-11 06:00 | 2278-04-11 06:14 | 13816425% | Actual Total Cost | [5 empty] | 5742452% | 68650.37 | 12089.38
|  |  | JDH3-02-008-L-51-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 2.51 to 3.5 m. |  | 2025-09-20 | 2025-10-02 | 19-Dec-24 A | 19-Aug-25 A | 2016-08-27 08:24 | 2016-08-27 08:10 | 4260935% | Planned Total Cost | [14 empty] | 38348.41 | 4260.93
|  |  | JDH3-02-008-L-51-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 2.51 to 3.5 m. |  | 2025-09-20 | 2025-10-02 | 19-Dec-24 A | 19-Aug-25 A | 2016-08-27 08:24 | 2016-08-27 08:10 | 4260935% | Remaining Total Cost
|  |  | JDH3-02-008-L-51-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 2.51 to 3.5 m. |  | 2025-09-20 | 2025-10-02 | 19-Dec-24 A | 19-Aug-25 A | 2016-08-27 08:24 | 2016-08-27 08:10 | 4260935% | Actual Total Cost | [5 empty] | 585879% | 30359.16 | 2130.47 | [5 empty] | 4260.93
|  |  | JDH3-02-008-L-51-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2025-09-20 | 2025-10-09 | 16-Dec-24 A | 2025-11-11 | 1972-10-21 04:19 | 1972-10-21 04:05 | 3128609% | Planned Total Cost | [14 empty] | 15643.05 | 10950.13 | 4692.91
|  |  | JDH3-02-008-L-51-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2025-09-20 | 2025-10-09 | 16-Dec-24 A | 2025-11-11 | 1972-10-21 04:19 | 1972-10-21 04:05 | 3128609% | Remaining Total Cost | [16 empty] | 4692.91
|  |  | JDH3-02-008-L-51-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2025-09-20 | 2025-10-09 | 16-Dec-24 A | 2025-11-11 | 1972-10-21 04:19 | 1972-10-21 04:05 | 3128609% | Actual Total Cost | [5 empty] | 505140% | 9613.95 | 977.69 | [5 empty] | 10950.13
|  |  | JDH3-02-008-L-51-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2025-09-20 | 2025-10-12 | 24-Dec-24 A | 2025-11-11 | 2072-11-30 19:12 | 2072-11-30 19:26 | 7430447% | Planned Total Cost | [14 empty] | 55356.84 | 7801.97 | 11145.67
|  |  | JDH3-02-008-L-51-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2025-09-20 | 2025-10-12 | 24-Dec-24 A | 2025-11-11 | 2072-11-30 19:12 | 2072-11-30 19:26 | 7430447% | Remaining Total Cost | [16 empty] | 11145.67
|  |  | JDH3-02-008-L-51-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2025-09-20 | 2025-10-12 | 24-Dec-24 A | 2025-11-11 | 2072-11-30 19:12 | 2072-11-30 19:26 | 7430447% | Actual Total Cost | [5 empty] | 812705% | 31997.37 | 15232.42 | [5 empty] | 7801.97
|  |  | JDH3-02-008-L-51-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2025-10-06 | 2025-10-16 | 24-Aug-25 A | 2025-11-11 | 1984-02-25 01:12 | 1984-02-25 01:12 | 3616124% | Planned Total Cost | [15 empty] | 30737.05 | 5424.19
|  |  | JDH3-02-008-L-51-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2025-10-06 | 2025-10-16 | 24-Aug-25 A | 2025-11-11 | 1984-02-25 01:12 | 1984-02-25 01:12 | 3616124% | Remaining Total Cost | [16 empty] | 5424.19
|  |  | JDH3-02-008-L-51-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2025-10-06 | 2025-10-16 | 24-Aug-25 A | 2025-11-11 | 1984-02-25 01:12 | 1984-02-25 01:12 | 3616124% | Actual Total Cost | [13 empty] | 30737.05
|  |  | JDH3-02-008-L-51-Storm Network - ST |  | 2025-09-20 | 2026-03-25 | 15-Dec-24 A | 2026-05-04 | 2668807.22 | 2668807.26 | 612394748% | Planned Total Cost | [14 empty] | 334071.03 | 144623.99 | 1432888.76 | 560799.64 | 214926.55 | 1627734 | 1233492.42 | 545018.62 | 30392.48
|  |  | JDH3-02-008-L-51-Storm Network - ST |  | 2025-09-20 | 2026-03-25 | 15-Dec-24 A | 2026-05-04 | 2668807.22 | 2668807.26 | 612394748% | Remaining Total Cost | [16 empty] | 1668703.38 | 560799.64 | 48549.16 |  | 601676.98 | 545018.62 | 30392.48
|  |  | JDH3-02-008-L-51-Storm Network - ST |  | 2025-09-20 | 2026-03-25 | 15-Dec-24 A | 2026-05-04 | 2668807.22 | 2668807.26 | 612394748% | Actual Total Cost | [5 empty] | 1327542% | 383195.13 | 83968.51 | 145828.89 | 444181.72 | 284604.14 | 298382.45 | 316203.98 | 290683.33 | 383367.28 | 25116.41
|  |  | JDH3-02-008-L-51-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-01-25 | 2026-03-25 | 2025-11-11 | 2026-01-11 | 0 | 0 | 81351080% | Planned Total Cost | [16 empty] | 229613.42 | 535348.22 | 48549.16
|  |  | JDH3-02-008-L-51-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-01-25 | 2026-03-25 | 2025-11-11 | 2026-01-11 | 0 | 0 | 81351080% | Remaining Total Cost | [16 empty] | 229613.42 | 535348.22 | 48549.16
|  |  | JDH3-02-008-L-51-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-01-25 | 2026-03-25 | 2025-11-11 | 2026-01-11 | 0 | 0 | 81351080% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2026-01-13 | 2026-02-23 | 15-Dec-24 A | 2025-12-01 | 2290-11-01 11:31 | 2290-11-01 11:31 | 39744990% | Planned Total Cost | [16 empty] | 74873.44 | 1567.72 | 39228.57 | 281780.18
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2026-01-13 | 2026-02-23 | 15-Dec-24 A | 2025-12-01 | 2290-11-01 11:31 | 2290-11-01 11:31 | 39744990% | Remaining Total Cost | [16 empty] | 253130.71 | 1567.72
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2026-01-13 | 2026-02-23 | 15-Dec-24 A | 2025-12-01 | 2290-11-01 11:31 | 2290-11-01 11:31 | 39744990% | Actual Total Cost | [5 empty] | 868806% | 5212.84 |  |  |  | 20965.86 | 22177.57 | 1619.69 | 25213.09 | 56622.02 | 2252.35
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-10-18 | 2026-03-11 | 2025-11-11 | 2025-12-28 | 0 | 0 | 7746884% | Planned Total Cost | [16 empty] | 69721.96 | 7746.88
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-10-18 | 2026-03-11 | 2025-11-11 | 2025-12-28 | 0 | 0 | 7746884% | Remaining Total Cost | [16 empty] | 69721.96 | 7746.88
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-10-18 | 2026-03-11 | 2025-11-11 | 2025-12-28 | 0 | 0 | 7746884% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2026-01-20 | 2026-03-08 | 25-Jun-25 A | 2025-12-06 | 2000-07-14 18:14 | 2000-07-14 18:14 | 7958294% | Planned Total Cost | [16 empty] | 53797.99 | 7958.29 | 17826.66
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2026-01-20 | 2026-03-08 | 25-Jun-25 A | 2025-12-06 | 2000-07-14 18:14 | 2000-07-14 18:14 | 7958294% | Remaining Total Cost | [16 empty] | 34902.89 | 7958.29
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2026-01-20 | 2026-03-08 | 25-Jun-25 A | 2025-12-06 | 2000-07-14 18:14 | 2000-07-14 18:14 | 7958294% | Actual Total Cost | [11 empty] | 735.4 | 17091.26 |  | 16915.64 | 1979.46
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2026-01-22 | 2026-02-17 | 09-Jan-25 A | 2025-11-10 | 2238-06-11 19:26 | 2238-06-11 19:55 | 16191312% | Planned Total Cost | [16 empty] | 5909.47 |  | 68445.43 | 87558.23
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2026-01-22 | 2026-02-17 | 09-Jan-25 A | 2025-11-10 | 2238-06-11 19:26 | 2238-06-11 19:55 | 16191312% | Remaining Total Cost | [16 empty] | 38297.3
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2026-01-22 | 2026-02-17 | 09-Jan-25 A | 2025-11-10 | 2238-06-11 19:26 | 2238-06-11 19:55 | 16191312% | Actual Total Cost | [6 empty] | 96800.5 | [5 empty] | 13133.71 | 3378.93 | 9921.11 | 381.58
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-01-26 | 2026-02-23 | 09-Jun-25 A | 2025-11-08 | 2359-02-03 18:58 | 2359-02-03 18:58 | 18326280% | Planned Total Cost | [16 empty] | 34236.26 |  | 32774.75 | 116251.8
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-01-26 | 2026-02-23 | 09-Jun-25 A | 2025-11-08 | 2359-02-03 18:58 | 2359-02-03 18:58 | 18326280% | Remaining Total Cost | [16 empty] | 15581.01
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-01-26 | 2026-02-23 | 09-Jun-25 A | 2025-11-08 | 2359-02-03 18:58 | 2359-02-03 18:58 | 18326280% | Actual Total Cost | [11 empty] | 34238.57 | 78135.41 | 5402.1 | 49325.36 | 580.35
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 0.00 to 1.50 m |  | 2026-01-29 | 2026-02-22 | 10-Feb-25 A | 2025-11-11 | 208454.64 | 208454.66 | 24539332% | Planned Total Cost | [16 empty] | 36938.67 |  | 8101.99 | 200352.66
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 0.00 to 1.50 m |  | 2026-01-29 | 2026-02-22 | 10-Feb-25 A | 2025-11-11 | 208454.64 | 208454.66 | 24539332% | Remaining Total Cost | [16 empty] | 36938.67
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 0.00 to 1.50 m |  | 2026-01-29 | 2026-02-22 | 10-Feb-25 A | 2025-11-11 | 208454.64 | 208454.66 | 24539332% | Actual Total Cost | [7 empty] | 31128.28 | 27891.69 | 1707.45 |  |  |  | 147727.24
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2026-02-02 | 2026-02-24 | 10-Feb-25 A | 2025-11-11 | 2164-11-18 17:17 | 2164-11-18 17:31 | 11080017% | Planned Total Cost | [16 empty] | 14051.45 |  |  | 96748.72
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2026-02-02 | 2026-02-24 | 10-Feb-25 A | 2025-11-11 | 2164-11-18 17:17 | 2164-11-18 17:31 | 11080017% | Remaining Total Cost | [16 empty] | 14051.45
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2026-02-02 | 2026-02-24 | 10-Feb-25 A | 2025-11-11 | 2164-11-18 17:17 | 2164-11-18 17:31 | 11080017% | Actual Total Cost | [7 empty] | 17075.7 | 26160.92 |  |  |  | 8108.59 | 45403.52
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2026-02-04 | 2026-02-26 | 30-Dec-24 A | 2025-11-11 | 2308-01-09 10:48 | 2308-01-09 10:48 | 17564432% | Planned Total Cost | [16 empty] | 74209.44 |  |  | 101434.88
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2026-02-04 | 2026-02-26 | 30-Dec-24 A | 2025-11-11 | 2308-01-09 10:48 | 2308-01-09 10:48 | 17564432% | Remaining Total Cost | [16 empty] | 26615.87
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2026-02-04 | 2026-02-26 | 30-Dec-24 A | 2025-11-11 | 2308-01-09 10:48 | 2308-01-09 10:48 | 17564432% | Actual Total Cost | [5 empty] | 290417% | 20329.17 |  | 33876.7 | 35811.85 |  |  | 8513 |  | 47593.56
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 0.00 to 1.50 m |  | 2025-09-20 | 2026-02-22 | 05-Apr-25 A | 2025-11-11 | 2058-09-17 16:48 | 2058-09-17 16:34 | 7246337% | Planned Total Cost | [14 empty] | 57970.7 |  | 14492.67
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 0.00 to 1.50 m |  | 2025-09-20 | 2026-02-22 | 05-Apr-25 A | 2025-11-11 | 2058-09-17 16:48 | 2058-09-17 16:34 | 7246337% | Remaining Total Cost | [16 empty] | 14492.67
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 0.00 to 1.50 m |  | 2025-09-20 | 2026-02-22 | 05-Apr-25 A | 2025-11-11 | 2058-09-17 16:48 | 2058-09-17 16:34 | 7246337% | Actual Total Cost | [9 empty] | 14492.67 | 43478.02
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2026-02-07 | 2026-03-03 | 31-Dec-24 A | 2025-11-16 | 2434-09-25 12:29 | 2434-09-25 12:29 | 34008881% | Planned Total Cost | [16 empty] | 161997.57 |  |  | 178091.24
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2026-02-07 | 2026-03-03 | 31-Dec-24 A | 2025-11-16 | 2434-09-25 12:29 | 2434-09-25 12:29 | 34008881% | Remaining Total Cost | [16 empty] | 144779.29
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2026-02-07 | 2026-03-03 | 31-Dec-24 A | 2025-11-16 | 2434-09-25 12:29 | 2434-09-25 12:29 | 34008881% | Actual Total Cost | [5 empty] | 168319% | 44600.94 | 4205.44 | 38178.13 | 72885.53 | 4961.4 | 8269.01 | 3307.6 |  | 15535.42 | 1682.86
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2026-02-10 | 2026-03-08 | 01-Jan-25 A | 2025-11-13 | 215407.56 | 215407.56 | 45798728% | Planned Total Cost | [16 empty] | 305359.89 |  |  | 148883.77 | 3743.62
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2026-02-10 | 2026-03-08 | 01-Jan-25 A | 2025-11-13 | 215407.56 | 215407.56 | 45798728% | Remaining Total Cost | [16 empty] | 242579.72
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2026-02-10 | 2026-03-08 | 01-Jan-25 A | 2025-11-13 | 215407.56 | 215407.56 | 45798728% | Actual Total Cost | [6 empty] | 50633.85 | 6418.38 |  | 16867.02 | 54817.81 | 12650.26 | 11240.07 |  | 54751.36 | 8028.81
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2026-02-15 | 2026-03-15 | 02-Jan-25 A | 2025-11-09 | 393758.59 | 393758.6 | 60735613% | Planned Total Cost | [19 empty] | 295832.34 | 311523.79
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2026-02-15 | 2026-03-15 | 02-Jan-25 A | 2025-11-09 | 393758.59 | 393758.6 | 60735613% | Remaining Total Cost | [16 empty] | 213597.53
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2026-02-15 | 2026-03-15 | 02-Jan-25 A | 2025-11-09 | 393758.59 | 393758.6 | 60735613% | Actual Total Cost | [6 empty] | 60436.75 | 25140.71 |  |  |  | 61187.89 | 139765.59 | 34511.55 | 70022.92 | 2693.19
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-09-20 | 2026-03-03 | 07-Jan-25 A | 2025-11-10 | 505931.62 | 505931.62 | 52590540% | Planned Total Cost | [14 empty] | 276100.34 | 144623.99 |  |  |  | 68481.58 | 36699.5
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-09-20 | 2026-03-03 | 07-Jan-25 A | 2025-11-10 | 505931.62 | 505931.62 | 52590540% | Remaining Total Cost | [16 empty] | 19973.79
|  |  | JDH3-02-008-L-51-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-09-20 | 2026-03-03 | 07-Jan-25 A | 2025-11-10 | 505931.62 | 505931.62 | 52590540% | Actual Total Cost | [6 empty] | 105181.08 |  | 19721.45 | 302417.2 | 59319.02 |  |  | 17776.7 | 1460.02 | 56.15
|  |  | JDH3-02-008-L-51-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2026-02-24 | 2026-03-19 | 15-May-25 A | 2025-11-19 | 2151-06-20 13:41 | 2151-06-20 13:55 | 20857395% | Planned Total Cost | [16 empty] | 123419.21 |  |  | 44827.84 | 40326.89
|  |  | JDH3-02-008-L-51-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2026-02-24 | 2026-03-19 | 15-May-25 A | 2025-11-19 | 2151-06-20 13:41 | 2151-06-20 13:55 | 20857395% | Remaining Total Cost | [16 empty] | 116725.37
|  |  | JDH3-02-008-L-51-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2026-02-24 | 2026-03-19 | 15-May-25 A | 2025-11-19 | 2151-06-20 13:41 | 2151-06-20 13:55 | 20857395% | Actual Total Cost | [10 empty] | 32064.36 | 46634.06 | 6456.32 |  | 6215.71 | 478.13
|  |  | JDH3-02-008-L-51-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-02-28 | 2026-03-15 | 19-May-25 A | 2026-03-28 | 2033-12-15 06:58 | 2033-12-15 06:43 | 8212599% | Planned Total Cost | [16 empty] | 24985.1 |  |  | 7490.76 | 49650.13
|  |  | JDH3-02-008-L-51-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-02-28 | 2026-03-15 | 19-May-25 A | 2026-03-28 | 2033-12-15 06:58 | 2033-12-15 06:43 | 8212599% | Remaining Total Cost | [16 empty] | 24985.1 |  |  |  | 8212.6
|  |  | JDH3-02-008-L-51-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-02-28 | 2026-03-15 | 19-May-25 A | 2026-03-28 | 2033-12-15 06:58 | 2033-12-15 06:43 | 8212599% | Actual Total Cost | [10 empty] | 13385.47 | 24272.61 |  | 11270.2
|  |  | JDH3-02-008-L-51-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-01-13 | 2026-01-31 | 16-Sep-25 A | 2026-03-25 | 1969-08-07 01:41 | 1969-08-07 01:41 | 25419947% | Planned Total Cost | [20 empty] | 254199.47
|  |  | JDH3-02-008-L-51-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-01-13 | 2026-01-31 | 16-Sep-25 A | 2026-03-25 | 1969-08-07 01:41 | 1969-08-07 01:41 | 25419947% | Remaining Total Cost | [20 empty] | 228777.4
|  |  | JDH3-02-008-L-51-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-01-13 | 2026-01-31 | 16-Sep-25 A | 2026-03-25 | 1969-08-07 01:41 | 1969-08-07 01:41 | 25419947% | Actual Total Cost | [14 empty] | 23269.97 | 2152.11
|  |  | JDH3-02-008-L-51-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2026-01-15 | 2026-01-26 | 2026-03-10 | 2026-03-22 | 0 | 0 | 1825022% | Planned Total Cost | [20 empty] | 18250.22
|  |  | JDH3-02-008-L-51-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2026-01-15 | 2026-01-26 | 2026-03-10 | 2026-03-22 | 0 | 0 | 1825022% | Remaining Total Cost | [20 empty] | 18250.22
|  |  | JDH3-02-008-L-51-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2026-01-15 | 2026-01-26 | 2026-03-10 | 2026-03-22 | 0 | 0 | 1825022% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-03-02 | 2026-03-24 | 19-May-25 A | 2026-05-04 | 209227.64 | 209227.64 | 38716532% | Planned Total Cost | [16 empty] | 175786.76 |  |  |  | 172662.03 | 8324.05 | 30392.48
|  |  | JDH3-02-008-L-51-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-03-02 | 2026-03-24 | 19-May-25 A | 2026-05-04 | 209227.64 | 209227.64 | 38716532% | Remaining Total Cost | [16 empty] | 139221.15 |  |  |  |  | 8324.05 | 30392.48
|  |  | JDH3-02-008-L-51-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-03-02 | 2026-03-24 | 19-May-25 A | 2026-05-04 | 209227.64 | 209227.64 | 38716532% | Actual Total Cost | [10 empty] | 55612.21 | 88217.08 | 28832.74 |  | 31734.19 | 4831.42
|  |  | JDH3-02-008-L-51-(ST)- Single Catchbasine Works |  | 2026-01-18 | 2026-03-02 | 2026-03-12 | 2026-04-26 | 0 | 0 | 25811037% | Planned Total Cost | [20 empty] | 180712.46 | 77397.91
|  |  | JDH3-02-008-L-51-(ST)- Single Catchbasine Works |  | 2026-01-18 | 2026-03-02 | 2026-03-12 | 2026-04-26 | 0 | 0 | 25811037% | Remaining Total Cost | [20 empty] | 180712.46 | 77397.91
|  |  | JDH3-02-008-L-51-(ST)- Single Catchbasine Works |  | 2026-01-18 | 2026-03-02 | 2026-03-12 | 2026-04-26 | 0 | 0 | 25811037% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(ST)- Double Catchbasine Works |  | 2026-01-27 | 2026-03-07 | 2026-03-22 | 2026-04-30 | 0 | 0 | 62502096% | Planned Total Cost | [20 empty] | 165724.31 | 459296.65
|  |  | JDH3-02-008-L-51-(ST)- Double Catchbasine Works |  | 2026-01-27 | 2026-03-07 | 2026-03-22 | 2026-04-30 | 0 | 0 | 62502096% | Remaining Total Cost | [20 empty] | 165724.31 | 459296.65
|  |  | JDH3-02-008-L-51-(ST)- Double Catchbasine Works |  | 2026-01-27 | 2026-03-07 | 2026-03-22 | 2026-04-30 | 0 | 0 | 62502096% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(ST)-PIPES ENCASEMENT |  | 2026-02-21 | 2026-03-05 | 2025-11-19 | 2025-12-03 | 0 | 0 | 4167400% | Planned Total Cost | [16 empty] | 33495.48 | 8178.52
|  |  | JDH3-02-008-L-51-(ST)-PIPES ENCASEMENT |  | 2026-02-21 | 2026-03-05 | 2025-11-19 | 2025-12-03 | 0 | 0 | 4167400% | Remaining Total Cost | [16 empty] | 33495.48 | 8178.52
|  |  | JDH3-02-008-L-51-(ST)-PIPES ENCASEMENT |  | 2026-02-21 | 2026-03-05 | 2025-11-19 | 2025-12-03 | 0 | 0 | 4167400% | Actual Total Cost
|  |  | JDH3-02-008-L-51-TSE Network - TSE |  | 2026-03-25 | 2026-05-24 | 24-Dec-24 A | 2026-06-04 | 382514.64 | 382514.63 | 173437927% | Planned Total Cost | [16 empty] | 30598.31 |  |  |  | 17014.67 | 223549.52 | 1436555.07 | 26661.7
|  |  | JDH3-02-008-L-51-TSE Network - TSE |  | 2026-03-25 | 2026-05-24 | 24-Dec-24 A | 2026-06-04 | 382514.64 | 382514.63 | 173437927% | Remaining Total Cost | [16 empty] | 30598.31 |  |  |  |  | 37524.35 | 1257080.28 | 26661.7
|  |  | JDH3-02-008-L-51-TSE Network - TSE |  | 2026-03-25 | 2026-05-24 | 24-Dec-24 A | 2026-06-04 | 382514.64 | 382514.63 | 173437927% | Actual Total Cost | [5 empty] | 1821029% | 121078.87 | 67222.38 | 22018.53 | [5 empty] | 144613.5 | 9371.06
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-03-25 | 2026-05-09 | 2026-05-04 | 2026-05-23 | 0 | 0 | 2810672% | Planned Total Cost | [22 empty] | 28106.72
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-03-25 | 2026-05-09 | 2026-05-04 | 2026-05-23 | 0 | 0 | 2810672% | Remaining Total Cost | [22 empty] | 28106.72
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-03-25 | 2026-05-09 | 2026-05-04 | 2026-05-23 | 0 | 0 | 2810672% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-03-28 | 2026-05-16 | 24-Dec-24 A | 2026-05-18 | 2179-07-06 00:43 | 2179-07-06 00:43 | 25481863% | Planned Total Cost | [16 empty] | 30598.31 |  |  |  | 17014.67 | 85076.36 | 122129.3
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-03-28 | 2026-05-16 | 24-Dec-24 A | 2026-05-18 | 2179-07-06 00:43 | 2179-07-06 00:43 | 25481863% | Remaining Total Cost | [16 empty] | 30598.31 | [5 empty] | 122129.3
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-03-28 | 2026-05-16 | 24-Dec-24 A | 2026-05-18 | 2179-07-06 00:43 | 2179-07-06 00:43 | 25481863% | Actual Total Cost | [5 empty] | 694549% | 51909.26 | 28979.24 | 14257.05
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2026-04-04 | 2026-05-09 | 2026-05-04 | 2026-05-23 | 0 | 0 | 4456842% | Planned Total Cost | [22 empty] | 44568.42
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2026-04-04 | 2026-05-09 | 2026-05-04 | 2026-05-23 | 0 | 0 | 4456842% | Remaining Total Cost | [22 empty] | 44568.42
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2026-04-04 | 2026-05-09 | 2026-05-04 | 2026-05-23 | 0 | 0 | 4456842% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2026-04-06 | 2026-05-24 | 24-Dec-24 A | 2026-06-01 | 2246-03-05 00:58 | 2246-03-05 00:58 | 32008201% | Planned Total Cost | [21 empty] | 126439.04 | 192019.69 | 1623.27
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2026-04-06 | 2026-05-24 | 24-Dec-24 A | 2026-06-01 | 2246-03-05 00:58 | 2246-03-05 00:58 | 32008201% | Remaining Total Cost | [22 empty] | 192019.69 | 1623.27
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2026-04-06 | 2026-05-24 | 24-Dec-24 A | 2026-06-01 | 2246-03-05 00:58 | 2246-03-05 00:58 | 32008201% | Actual Total Cost | [5 empty] | 1126480% | 69169.62 | 38243.14 | 7761.48
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 2.51 to 3.5 m |  | 2026-04-06 | 2026-04-16 | 2026-05-06 | 2026-05-18 | 0 | 0 | 4697145% | Planned Total Cost | [22 empty] | 46971.45
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 2.51 to 3.5 m |  | 2026-04-06 | 2026-04-16 | 2026-05-06 | 2026-05-18 | 0 | 0 | 4697145% | Remaining Total Cost | [22 empty] | 46971.45
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 2.51 to 3.5 m |  | 2026-04-06 | 2026-04-16 | 2026-05-06 | 2026-05-18 | 0 | 0 | 4697145% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-04-08 | 2026-05-09 | 2026-05-09 | 2026-05-23 | 0 | 0 | 2991547% | Planned Total Cost | [22 empty] | 29915.47
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-04-08 | 2026-05-09 | 2026-05-09 | 2026-05-23 | 0 | 0 | 2991547% | Remaining Total Cost | [22 empty] | 29915.47
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-04-08 | 2026-05-09 | 2026-05-09 | 2026-05-23 | 0 | 0 | 2991547% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-04-12 | 2026-05-21 | 03-Sep-25 A | 2026-06-04 | 2321-08-04 13:26 | 2321-08-04 13:26 | 37315094% | Planned Total Cost | [21 empty] | 12034.12 | 336078.39 | 25038.43
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-04-12 | 2026-05-21 | 03-Sep-25 A | 2026-06-04 | 2321-08-04 13:26 | 2321-08-04 13:26 | 37315094% | Remaining Total Cost | [21 empty] | 37524.35 | 156603.6 | 25038.43
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-04-12 | 2026-05-21 | 03-Sep-25 A | 2026-06-04 | 2321-08-04 13:26 | 2321-08-04 13:26 | 37315094% | Actual Total Cost | [14 empty] | 144613.5 | 9371.06
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 2.51 to 3.5 m |  | 2026-03-25 | 2026-05-09 | 2026-05-04 | 2026-05-23 | 0 | 0 | 11180474% | Planned Total Cost | [22 empty] | 111804.74
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 2.51 to 3.5 m |  | 2026-03-25 | 2026-05-09 | 2026-05-04 | 2026-05-23 | 0 | 0 | 11180474% | Remaining Total Cost | [22 empty] | 111804.74
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 2.51 to 3.5 m |  | 2026-03-25 | 2026-05-09 | 2026-05-04 | 2026-05-23 | 0 | 0 | 11180474% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 0 to 1.5 m |  | 2026-03-25 | 2026-05-09 | 2026-05-04 | 2026-05-23 | 0 | 0 | 5366567% | Planned Total Cost | [22 empty] | 53665.67
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 0 to 1.5 m |  | 2026-03-25 | 2026-05-09 | 2026-05-04 | 2026-05-23 | 0 | 0 | 5366567% | Remaining Total Cost | [22 empty] | 53665.67
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 0 to 1.5 m |  | 2026-03-25 | 2026-05-09 | 2026-05-04 | 2026-05-23 | 0 | 0 | 5366567% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 1.51 to 2.5 m |  | 2026-03-25 | 2026-05-09 | 2026-05-04 | 2026-05-23 | 0 | 0 | 9864386% | Planned Total Cost | [22 empty] | 98643.86
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 1.51 to 2.5 m |  | 2026-03-25 | 2026-05-09 | 2026-05-04 | 2026-05-23 | 0 | 0 | 9864386% | Remaining Total Cost | [22 empty] | 98643.86
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 1.51 to 2.5 m |  | 2026-03-25 | 2026-05-09 | 2026-05-04 | 2026-05-23 | 0 | 0 | 9864386% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 2.51 to 3.5 m |  | 2026-03-25 | 2026-04-05 | 2026-05-04 | 2026-05-16 | 0 | 0 | 11186417% | Planned Total Cost | [22 empty] | 111864.17
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 2.51 to 3.5 m |  | 2026-03-25 | 2026-04-05 | 2026-05-04 | 2026-05-16 | 0 | 0 | 11186417% | Remaining Total Cost | [22 empty] | 111864.17
|  |  | JDH3-02-008-L-51-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 2.51 to 3.5 m |  | 2026-03-25 | 2026-04-05 | 2026-05-04 | 2026-05-16 | 0 | 0 | 11186417% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-10 | 2026-05-16 | 2026-05-23 | 2026-05-30 | 0 | 0 | 1163844% | Planned Total Cost | [22 empty] | 11638.44
|  |  | JDH3-02-008-L-51-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-10 | 2026-05-16 | 2026-05-23 | 2026-05-30 | 0 | 0 | 1163844% | Remaining Total Cost | [22 empty] | 11638.44
|  |  | JDH3-02-008-L-51-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-10 | 2026-05-16 | 2026-05-23 | 2026-05-30 | 0 | 0 | 1163844% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(TSE)-Supply and install gate valves-250 mm |  | 2026-05-03 | 2026-05-06 | 2026-05-16 | 2026-05-20 | 0 | 0 | 1539668% | Planned Total Cost | [22 empty] | 15396.68
|  |  | JDH3-02-008-L-51-(TSE)-Supply and install gate valves-250 mm |  | 2026-05-03 | 2026-05-06 | 2026-05-16 | 2026-05-20 | 0 | 0 | 1539668% | Remaining Total Cost | [22 empty] | 15396.68
|  |  | JDH3-02-008-L-51-(TSE)-Supply and install gate valves-250 mm |  | 2026-05-03 | 2026-05-06 | 2026-05-16 | 2026-05-20 | 0 | 0 | 1539668% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2026-05-03 | 2026-05-11 | 2026-05-16 | 2026-05-25 | 0 | 0 | 6135983% | Planned Total Cost | [22 empty] | 61359.83
|  |  | JDH3-02-008-L-51-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2026-05-03 | 2026-05-11 | 2026-05-16 | 2026-05-25 | 0 | 0 | 6135983% | Remaining Total Cost | [22 empty] | 61359.83
|  |  | JDH3-02-008-L-51-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2026-05-03 | 2026-05-11 | 2026-05-16 | 2026-05-25 | 0 | 0 | 6135983% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2026-05-03 | 2026-05-09 | 2026-05-16 | 2026-05-23 | 0 | 0 | 2365815% | Planned Total Cost | [22 empty] | 23658.15
|  |  | JDH3-02-008-L-51-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2026-05-03 | 2026-05-09 | 2026-05-16 | 2026-05-23 | 0 | 0 | 2365815% | Remaining Total Cost | [22 empty] | 23658.15
|  |  | JDH3-02-008-L-51-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2026-05-03 | 2026-05-09 | 2026-05-16 | 2026-05-23 | 0 | 0 | 2365815% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(TSE)-Supply and install of butterfly valves-600 mm. |  | 2026-05-03 | 2026-05-06 | 2026-05-16 | 2026-05-20 | 0 | 0 | 4657520% | Planned Total Cost | [22 empty] | 46575.2
|  |  | JDH3-02-008-L-51-(TSE)-Supply and install of butterfly valves-600 mm. |  | 2026-05-03 | 2026-05-06 | 2026-05-16 | 2026-05-20 | 0 | 0 | 4657520% | Remaining Total Cost | [22 empty] | 46575.2
|  |  | JDH3-02-008-L-51-(TSE)-Supply and install of butterfly valves-600 mm. |  | 2026-05-03 | 2026-05-06 | 2026-05-16 | 2026-05-20 | 0 | 0 | 4657520% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-05-03 | 2026-05-06 | 2026-05-16 | 2026-05-20 | 0 | 0 | 2233241% | Planned Total Cost | [22 empty] | 22332.41
|  |  | JDH3-02-008-L-51-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-05-03 | 2026-05-06 | 2026-05-16 | 2026-05-20 | 0 | 0 | 2233241% | Remaining Total Cost | [22 empty] | 22332.41
|  |  | JDH3-02-008-L-51-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-05-03 | 2026-05-06 | 2026-05-16 | 2026-05-20 | 0 | 0 | 2233241% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(TSE)-Supply and install of Air valves-65 mm. |  | 2026-05-03 | 2026-05-06 | 2026-05-16 | 2026-05-20 | 0 | 0 | 824649% | Planned Total Cost | [22 empty] | 8246.49
|  |  | JDH3-02-008-L-51-(TSE)-Supply and install of Air valves-65 mm. |  | 2026-05-03 | 2026-05-06 | 2026-05-16 | 2026-05-20 | 0 | 0 | 824649% | Remaining Total Cost | [22 empty] | 8246.49
|  |  | JDH3-02-008-L-51-(TSE)-Supply and install of Air valves-65 mm. |  | 2026-05-03 | 2026-05-06 | 2026-05-16 | 2026-05-20 | 0 | 0 | 824649% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-03-25 | 2026-04-02 | 2026-05-04 | 2026-05-13 | 0 | 0 | 4551149% | Planned Total Cost | [22 empty] | 45511.49
|  |  | JDH3-02-008-L-51-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-03-25 | 2026-04-02 | 2026-05-04 | 2026-05-13 | 0 | 0 | 4551149% | Remaining Total Cost | [22 empty] | 45511.49
|  |  | JDH3-02-008-L-51-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-03-25 | 2026-04-02 | 2026-05-04 | 2026-05-13 | 0 | 0 | 4551149% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(TSE)- Supply and Construct R.C Valves Chamber on 500-630 mm Diameter pipelines |  | 2026-03-25 | 2026-04-02 | 2026-05-04 | 2026-05-13 | 0 | 0 | 1215139% | Planned Total Cost | [22 empty] | 12151.39
|  |  | JDH3-02-008-L-51-(TSE)- Supply and Construct R.C Valves Chamber on 500-630 mm Diameter pipelines |  | 2026-03-25 | 2026-04-02 | 2026-05-04 | 2026-05-13 | 0 | 0 | 1215139% | Remaining Total Cost | [22 empty] | 12151.39
|  |  | JDH3-02-008-L-51-(TSE)- Supply and Construct R.C Valves Chamber on 500-630 mm Diameter pipelines |  | 2026-03-25 | 2026-04-02 | 2026-05-04 | 2026-05-13 | 0 | 0 | 1215139% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-03-25 | 2026-04-02 | 2026-05-04 | 2026-05-13 | 0 | 0 | 1043783% | Planned Total Cost | [22 empty] | 10437.83
|  |  | JDH3-02-008-L-51-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-03-25 | 2026-04-02 | 2026-05-04 | 2026-05-13 | 0 | 0 | 1043783% | Remaining Total Cost | [22 empty] | 10437.83
|  |  | JDH3-02-008-L-51-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-03-25 | 2026-04-02 | 2026-05-04 | 2026-05-13 | 0 | 0 | 1043783% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(TSE)- Supply and Construct Air Valves Chamber on 355-630 mm Diameter pipelines |  | 2026-03-25 | 2026-04-02 | 2026-05-04 | 2026-05-13 | 0 | 0 | 347928% | Planned Total Cost | [22 empty] | 3479.28
|  |  | JDH3-02-008-L-51-(TSE)- Supply and Construct Air Valves Chamber on 355-630 mm Diameter pipelines |  | 2026-03-25 | 2026-04-02 | 2026-05-04 | 2026-05-13 | 0 | 0 | 347928% | Remaining Total Cost | [22 empty] | 3479.28
|  |  | JDH3-02-008-L-51-(TSE)- Supply and Construct Air Valves Chamber on 355-630 mm Diameter pipelines |  | 2026-03-25 | 2026-04-02 | 2026-05-04 | 2026-05-13 | 0 | 0 | 347928% | Actual Total Cost
|  |  | JDH3-02-008-L-51-Potable Water Network - WT |  | 2026-05-07 | 2026-06-11 | 07-Aug-25 A | 2026-06-23 | 2077-06-08 10:34 | 2077-06-08 10:48 | 59046052% | Planned Total Cost | [22 empty] | 137141.31 | 453319.21
|  |  | JDH3-02-008-L-51-Potable Water Network - WT |  | 2026-05-07 | 2026-06-11 | 07-Aug-25 A | 2026-06-23 | 2077-06-08 10:34 | 2077-06-08 10:48 | 59046052% | Remaining Total Cost | [22 empty] | 81375.96 | 444275.11
|  |  | JDH3-02-008-L-51-Potable Water Network - WT |  | 2026-05-07 | 2026-06-11 | 07-Aug-25 A | 2026-06-23 | 2077-06-08 10:34 | 2077-06-08 10:48 | 59046052% | Actual Total Cost | [13 empty] | 14736.27 | 44685.72 | 5387.46
|  |  | JDH3-02-008-L-51-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-05-07 | 2026-06-10 | 20-Sep-25 A | 2026-06-22 | 1973-10-31 03:07 | 1973-10-31 03:07 | 6067829% | Planned Total Cost | [22 empty] | 45566.36 | 15111.93
|  |  | JDH3-02-008-L-51-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-05-07 | 2026-06-10 | 20-Sep-25 A | 2026-06-22 | 1973-10-31 03:07 | 1973-10-31 03:07 | 6067829% | Remaining Total Cost | [22 empty] | 27642.33 | 6067.83
|  |  | JDH3-02-008-L-51-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-05-07 | 2026-06-10 | 20-Sep-25 A | 2026-06-22 | 1973-10-31 03:07 | 1973-10-31 03:07 | 6067829% | Actual Total Cost | [14 empty] | 22436.41 | 4531.72
|  |  | JDH3-02-008-L-51-(WT)- Supply and install HDPE Pipes -225 mm depth from 0 to 1.5 m |  | 2026-05-11 | 2026-06-11 | 07-Aug-25 A | 2026-06-23 | 2003-08-08 07:26 | 2003-08-08 07:41 | 10174995% | Planned Total Cost | [22 empty] | 91574.95 | 10174.99
|  |  | JDH3-02-008-L-51-(WT)- Supply and install HDPE Pipes -225 mm depth from 0 to 1.5 m |  | 2026-05-11 | 2026-06-11 | 07-Aug-25 A | 2026-06-23 | 2003-08-08 07:26 | 2003-08-08 07:41 | 10174995% | Remaining Total Cost | [22 empty] | 53733.63 | 10174.99
|  |  | JDH3-02-008-L-51-(WT)- Supply and install HDPE Pipes -225 mm depth from 0 to 1.5 m |  | 2026-05-11 | 2026-06-11 | 07-Aug-25 A | 2026-06-23 | 2003-08-08 07:26 | 2003-08-08 07:41 | 10174995% | Actual Total Cost | [13 empty] | 14736.27 | 22249.31 | 855.74
|  |  | JDH3-02-008-L-51-(WT)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-05-25 | 2026-06-09 | 2026-06-04 | 2026-06-21 | 0 | 0 | 9743795% | Planned Total Cost | [23 empty] | 97437.95
|  |  | JDH3-02-008-L-51-(WT)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-05-25 | 2026-06-09 | 2026-06-04 | 2026-06-21 | 0 | 0 | 9743795% | Remaining Total Cost | [23 empty] | 97437.95
|  |  | JDH3-02-008-L-51-(WT)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-05-25 | 2026-06-09 | 2026-06-04 | 2026-06-21 | 0 | 0 | 9743795% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(WT)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-05-27 | 2026-06-09 | 2026-06-07 | 2026-06-21 | 0 | 0 | 132654% | Planned Total Cost | [23 empty] | 1326.54
|  |  | JDH3-02-008-L-51-(WT)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-05-27 | 2026-06-09 | 2026-06-07 | 2026-06-21 | 0 | 0 | 132654% | Remaining Total Cost | [23 empty] | 1326.54
|  |  | JDH3-02-008-L-51-(WT)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-05-27 | 2026-06-09 | 2026-06-07 | 2026-06-21 | 0 | 0 | 132654% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2026-06-03 | 2026-06-07 | 2026-06-14 | 2026-06-18 | 0 | 0 | 1218591% | Planned Total Cost | [23 empty] | 12185.91
|  |  | JDH3-02-008-L-51-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2026-06-03 | 2026-06-07 | 2026-06-14 | 2026-06-18 | 0 | 0 | 1218591% | Remaining Total Cost | [23 empty] | 12185.91
|  |  | JDH3-02-008-L-51-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2026-06-03 | 2026-06-07 | 2026-06-14 | 2026-06-18 | 0 | 0 | 1218591% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(WT)- Supply and install gate valves -Diameter 200 mm |  | 2026-06-03 | 2026-06-07 | 2026-06-14 | 2026-06-18 | 0 | 0 | 430053% | Planned Total Cost | [23 empty] | 4300.53
|  |  | JDH3-02-008-L-51-(WT)- Supply and install gate valves -Diameter 200 mm |  | 2026-06-03 | 2026-06-07 | 2026-06-14 | 2026-06-18 | 0 | 0 | 430053% | Remaining Total Cost | [23 empty] | 4300.53
|  |  | JDH3-02-008-L-51-(WT)- Supply and install gate valves -Diameter 200 mm |  | 2026-06-03 | 2026-06-07 | 2026-06-14 | 2026-06-18 | 0 | 0 | 430053% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(WT)- Supply and install Butterfly Valves -Diameter 300 mm. |  | 2026-06-03 | 2026-06-07 | 2026-06-14 | 2026-06-18 | 0 | 0 | 3067992% | Planned Total Cost | [23 empty] | 30679.92
|  |  | JDH3-02-008-L-51-(WT)- Supply and install Butterfly Valves -Diameter 300 mm. |  | 2026-06-03 | 2026-06-07 | 2026-06-14 | 2026-06-18 | 0 | 0 | 3067992% | Remaining Total Cost | [23 empty] | 30679.92
|  |  | JDH3-02-008-L-51-(WT)- Supply and install Butterfly Valves -Diameter 300 mm. |  | 2026-06-03 | 2026-06-07 | 2026-06-14 | 2026-06-18 | 0 | 0 | 3067992% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(WT)- Supply and install Wash-Out Valves -Diameter 100 mm. |  | 2026-06-03 | 2026-06-07 | 2026-06-14 | 2026-06-18 | 0 | 0 | 1298112% | Planned Total Cost | [23 empty] | 12981.12
|  |  | JDH3-02-008-L-51-(WT)- Supply and install Wash-Out Valves -Diameter 100 mm. |  | 2026-06-03 | 2026-06-07 | 2026-06-14 | 2026-06-18 | 0 | 0 | 1298112% | Remaining Total Cost | [23 empty] | 12981.12
|  |  | JDH3-02-008-L-51-(WT)- Supply and install Wash-Out Valves -Diameter 100 mm. |  | 2026-06-03 | 2026-06-07 | 2026-06-14 | 2026-06-18 | 0 | 0 | 1298112% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(WT)- Supply and install Air Valves -Diameter 50 mm. |  | 2026-06-03 | 2026-06-07 | 2026-06-14 | 2026-06-18 | 0 | 0 | 687512% | Planned Total Cost | [23 empty] | 6875.12
|  |  | JDH3-02-008-L-51-(WT)- Supply and install Air Valves -Diameter 50 mm. |  | 2026-06-03 | 2026-06-07 | 2026-06-14 | 2026-06-18 | 0 | 0 | 687512% | Remaining Total Cost | [23 empty] | 6875.12
|  |  | JDH3-02-008-L-51-(WT)- Supply and install Air Valves -Diameter 50 mm. |  | 2026-06-03 | 2026-06-07 | 2026-06-14 | 2026-06-18 | 0 | 0 | 687512% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(WT)- Supply and install 3-out fire hydrant |  | 2026-05-25 | 2026-06-07 | 2026-06-04 | 2026-06-18 | 0 | 0 | 22671008% | Planned Total Cost | [23 empty] | 226710.08
|  |  | JDH3-02-008-L-51-(WT)- Supply and install 3-out fire hydrant |  | 2026-05-25 | 2026-06-07 | 2026-06-04 | 2026-06-18 | 0 | 0 | 22671008% | Remaining Total Cost | [23 empty] | 226710.08
|  |  | JDH3-02-008-L-51-(WT)- Supply and install 3-out fire hydrant |  | 2026-05-25 | 2026-06-07 | 2026-06-04 | 2026-06-18 | 0 | 0 | 22671008% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(WT)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-05-25 | 2026-06-09 | 2026-06-04 | 2026-06-21 | 0 | 0 | 1820460% | Planned Total Cost | [23 empty] | 18204.6
|  |  | JDH3-02-008-L-51-(WT)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-05-25 | 2026-06-09 | 2026-06-04 | 2026-06-21 | 0 | 0 | 1820460% | Remaining Total Cost | [23 empty] | 18204.6
|  |  | JDH3-02-008-L-51-(WT)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-05-25 | 2026-06-09 | 2026-06-04 | 2026-06-21 | 0 | 0 | 1820460% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(WT)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipelines |  | 2026-05-25 | 2026-06-09 | 2026-06-04 | 2026-06-21 | 0 | 0 | 1385127% | Planned Total Cost | [23 empty] | 13851.27
|  |  | JDH3-02-008-L-51-(WT)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipelines |  | 2026-05-25 | 2026-06-09 | 2026-06-04 | 2026-06-21 | 0 | 0 | 1385127% | Remaining Total Cost | [23 empty] | 13851.27
|  |  | JDH3-02-008-L-51-(WT)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipelines |  | 2026-05-25 | 2026-06-09 | 2026-06-04 | 2026-06-21 | 0 | 0 | 1385127% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(WT)- Supply and Construct Air Valves Chamber on less than 450 mm Diameter pipeline |  | 2026-05-25 | 2026-06-09 | 2026-06-04 | 2026-06-21 | 0 | 0 | 347928% | Planned Total Cost | [23 empty] | 3479.28 | [9 empty] | 855.09
|  |  | JDH3-02-008-L-51-(WT)- Supply and Construct Air Valves Chamber on less than 450 mm Diameter pipeline |  | 2026-05-25 | 2026-06-09 | 2026-06-04 | 2026-06-21 | 0 | 0 | 347928% | Remaining Total Cost | [23 empty] | 3479.28 | [9 empty] | 855.09
|  |  | JDH3-02-008-L-51-(WT)- Supply and Construct Air Valves Chamber on less than 450 mm Diameter pipeline |  | 2026-05-25 | 2026-06-09 | 2026-06-04 | 2026-06-21 | 0 | 0 | 347928% | Actual Total Cost
|  |  | JDH3-02-008-L-51-Street Lighting Network -SL |  | 2026-06-13 | 2026-07-02 | 2026-06-23 | 2026-07-14 | 0 | 0 | 31244763% | Planned Total Cost | [23 empty] | 223354.33 | 89093.29
|  |  | JDH3-02-008-L-51-Street Lighting Network -SL |  | 2026-06-13 | 2026-07-02 | 2026-06-23 | 2026-07-14 | 0 | 0 | 31244763% | Remaining Total Cost | [23 empty] | 223354.33 | 89093.29
|  |  | JDH3-02-008-L-51-Street Lighting Network -SL |  | 2026-06-13 | 2026-07-02 | 2026-06-23 | 2026-07-14 | 0 | 0 | 31244763% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx10 mm² |  | 2026-06-13 | 2026-06-25 | 2026-06-23 | 2026-07-07 | 0 | 0 | 3463274% | Planned Total Cost | [23 empty] | 23013.46 | 11619.29
|  |  | JDH3-02-008-L-51-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx10 mm² |  | 2026-06-13 | 2026-06-25 | 2026-06-23 | 2026-07-07 | 0 | 0 | 3463274% | Remaining Total Cost | [23 empty] | 23013.46 | 11619.29
|  |  | JDH3-02-008-L-51-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx10 mm² |  | 2026-06-13 | 2026-06-25 | 2026-06-23 | 2026-07-07 | 0 | 0 | 3463274% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx25 mm² |  | 2026-06-13 | 2026-06-29 | 2026-06-23 | 2026-07-11 | 0 | 0 | 5124713% | Planned Total Cost | [23 empty] | 34053.72 | 17193.41
|  |  | JDH3-02-008-L-51-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx25 mm² |  | 2026-06-13 | 2026-06-29 | 2026-06-23 | 2026-07-11 | 0 | 0 | 5124713% | Remaining Total Cost | [23 empty] | 34053.72 | 17193.41
|  |  | JDH3-02-008-L-51-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx25 mm² |  | 2026-06-13 | 2026-06-29 | 2026-06-23 | 2026-07-11 | 0 | 0 | 5124713% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(STL)- Supply,install,connect and test single core PVC insulated copper 6mm2 |  | 2026-06-20 | 2026-06-25 | 2026-06-30 | 2026-07-07 | 0 | 0 | 314549% | Planned Total Cost | [23 empty] | 541.02 | 2604.47
|  |  | JDH3-02-008-L-51-(STL)- Supply,install,connect and test single core PVC insulated copper 6mm2 |  | 2026-06-20 | 2026-06-25 | 2026-06-30 | 2026-07-07 | 0 | 0 | 314549% | Remaining Total Cost | [23 empty] | 541.02 | 2604.47
|  |  | JDH3-02-008-L-51-(STL)- Supply,install,connect and test single core PVC insulated copper 6mm2 |  | 2026-06-20 | 2026-06-25 | 2026-06-30 | 2026-07-07 | 0 | 0 | 314549% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(STL)- Supply,install,connect and test single core PVC insulated copper 16mm2 |  | 2026-06-20 | 2026-06-25 | 2026-06-30 | 2026-07-07 | 0 | 0 | 723248% | Planned Total Cost | [23 empty] | 1243.99 | 5988.5
|  |  | JDH3-02-008-L-51-(STL)- Supply,install,connect and test single core PVC insulated copper 16mm2 |  | 2026-06-20 | 2026-06-25 | 2026-06-30 | 2026-07-07 | 0 | 0 | 723248% | Remaining Total Cost | [23 empty] | 1243.99 | 5988.5
|  |  | JDH3-02-008-L-51-(STL)- Supply,install,connect and test single core PVC insulated copper 16mm2 |  | 2026-06-20 | 2026-06-25 | 2026-06-30 | 2026-07-07 | 0 | 0 | 723248% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(STL)-LIGHTING POLE 12 m Column with two arms. |  | 2026-06-13 | 2026-06-23 | 2026-06-23 | 2026-07-05 | 0 | 0 | 3690454% | Planned Total Cost | [23 empty] | 24463.1 | 12441.44
|  |  | JDH3-02-008-L-51-(STL)-LIGHTING POLE 12 m Column with two arms. |  | 2026-06-13 | 2026-06-23 | 2026-06-23 | 2026-07-05 | 0 | 0 | 3690454% | Remaining Total Cost | [23 empty] | 24463.1 | 12441.44
|  |  | JDH3-02-008-L-51-(STL)-LIGHTING POLE 12 m Column with two arms. |  | 2026-06-13 | 2026-06-23 | 2026-06-23 | 2026-07-05 | 0 | 0 | 3690454% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2026-06-13 | 2026-06-28 | 2026-06-23 | 2026-07-09 | 0 | 0 | 6802568% | Planned Total Cost | [23 empty] | 41253.33 | 26772.36
|  |  | JDH3-02-008-L-51-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2026-06-13 | 2026-06-28 | 2026-06-23 | 2026-07-09 | 0 | 0 | 6802568% | Remaining Total Cost | [23 empty] | 41253.33 | 26772.36
|  |  | JDH3-02-008-L-51-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2026-06-13 | 2026-06-28 | 2026-06-23 | 2026-07-09 | 0 | 0 | 6802568% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2026-06-17 | 2026-06-21 | 2026-06-28 | 2026-07-02 | 0 | 0 | 2147991% | Planned Total Cost | [23 empty] | 14203.59 | 7276.32
|  |  | JDH3-02-008-L-51-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2026-06-17 | 2026-06-21 | 2026-06-28 | 2026-07-02 | 0 | 0 | 2147991% | Remaining Total Cost | [23 empty] | 14203.59 | 7276.32
|  |  | JDH3-02-008-L-51-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2026-06-17 | 2026-06-21 | 2026-06-28 | 2026-07-02 | 0 | 0 | 2147991% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2026-06-22 | 2026-06-23 | 2026-07-02 | 2026-07-05 | 0 | 0 | 151216% | Planned Total Cost | [24 empty] | 1512.16
|  |  | JDH3-02-008-L-51-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2026-06-22 | 2026-06-23 | 2026-07-02 | 2026-07-05 | 0 | 0 | 151216% | Remaining Total Cost | [24 empty] | 1512.16
|  |  | JDH3-02-008-L-51-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2026-06-22 | 2026-06-23 | 2026-07-02 | 2026-07-05 | 0 | 0 | 151216% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-2 × 150 mm |  | 2026-06-13 | 2026-07-02 | 2026-06-23 | 2026-07-14 | 0 | 0 | 996494% | Planned Total Cost | [23 empty] | 6351.65 | 3613.29
|  |  | JDH3-02-008-L-51-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-2 × 150 mm |  | 2026-06-13 | 2026-07-02 | 2026-06-23 | 2026-07-14 | 0 | 0 | 996494% | Remaining Total Cost | [23 empty] | 6351.65 | 3613.29
|  |  | JDH3-02-008-L-51-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-2 × 150 mm |  | 2026-06-13 | 2026-07-02 | 2026-06-23 | 2026-07-14 | 0 | 0 | 996494% | Actual Total Cost
|  |  | JDH3-02-008-L-51-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-4 × 150 mm |  | 2026-06-13 | 2026-06-21 | 2026-06-23 | 2026-07-02 | 0 | 0 | 2127.46 | Planned Total Cost | [23 empty] | 2055.4 | 72.07
|  |  | JDH3-02-008-L-51-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-4 × 150 mm |  | 2026-06-13 | 2026-06-21 | 2026-06-23 | 2026-07-02 | 0 | 0 | 2127.46 | Remaining Total Cost | [23 empty] | 2055.4 | 72.07
|  |  | JDH3-02-008-L-51-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-4 × 150 mm |  | 2026-06-13 | 2026-06-21 | 2026-06-23 | 2026-07-02 | 0 | 0 | 2127.46 | Actual Total Cost
|  |  | JDH3-02-008-L-51-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2026-06-13 | 2026-06-18 | 2026-06-23 | 2026-06-30 | 0 | 0 | 45882.99 | Planned Total Cost | [23 empty] | 45882.99
|  |  | JDH3-02-008-L-51-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2026-06-13 | 2026-06-18 | 2026-06-23 | 2026-06-30 | 0 | 0 | 45882.99 | Remaining Total Cost | [23 empty] | 45882.99
|  |  | JDH3-02-008-L-51-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2026-06-13 | 2026-06-18 | 2026-06-23 | 2026-06-30 | 0 | 0 | 45882.99 | Actual Total Cost
|  |  | JDH3-02-008-L-51-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2026-06-13 | 2026-06-18 | 2026-06-23 | 2026-06-30 | 0 | 0 | 30292.1 | Planned Total Cost | [23 empty] | 30292.1
|  |  | JDH3-02-008-L-51-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2026-06-13 | 2026-06-18 | 2026-06-23 | 2026-06-30 | 0 | 0 | 30292.1 | Remaining Total Cost | [23 empty] | 30292.1 | [9 empty] | 855.09
|  |  | JDH3-02-008-L-51-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2026-06-13 | 2026-06-18 | 2026-06-23 | 2026-06-30 | 0 | 0 | 30292.1 | Actual Total Cost
|  |  | JDH3-02-008-L-51-Telecommunications Network - TC |  | 2026-06-16 | 2026-07-08 | 2026-06-27 | 2026-07-20 | 0 | 0 | 131404.35 | Planned Total Cost | [23 empty] | 23982.59 | 107421.76
|  |  | JDH3-02-008-L-51-Telecommunications Network - TC |  | 2026-06-16 | 2026-07-08 | 2026-06-27 | 2026-07-20 | 0 | 0 | 131404.35 | Remaining Total Cost | [23 empty] | 23982.59 | 107421.76
|  |  | JDH3-02-008-L-51-Telecommunications Network - TC |  | 2026-06-16 | 2026-07-08 | 2026-06-27 | 2026-07-20 | 0 | 0 | 131404.35 | Actual Total Cost
|  |  | JDH3-02-008-L-51-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2026-06-16 | 2026-07-08 | 2026-06-27 | 2026-07-20 | 0 | 0 | 86919.44 | Planned Total Cost | [23 empty] | 22189.29 | 64730.15
|  |  | JDH3-02-008-L-51-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2026-06-16 | 2026-07-08 | 2026-06-27 | 2026-07-20 | 0 | 0 | 86919.44 | Remaining Total Cost | [23 empty] | 22189.29 | 64730.15
|  |  | JDH3-02-008-L-51-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2026-06-16 | 2026-07-08 | 2026-06-27 | 2026-07-20 | 0 | 0 | 86919.44 | Actual Total Cost
|  |  | JDH3-02-008-L-51-(TEL)-Manhole for feeder pathway Type 1 |  | 2026-06-20 | 2026-07-02 | 2026-06-30 | 2026-07-14 | 0 | 0 | 44484.92 | Planned Total Cost | [23 empty] | 1793.3 | 42691.62
|  |  | JDH3-02-008-L-51-(TEL)-Manhole for feeder pathway Type 1 |  | 2026-06-20 | 2026-07-02 | 2026-06-30 | 2026-07-14 | 0 | 0 | 44484.92 | Remaining Total Cost | [23 empty] | 1793.3 | 42691.62
|  |  | JDH3-02-008-L-51-(TEL)-Manhole for feeder pathway Type 1 |  | 2026-06-20 | 2026-07-02 | 2026-06-30 | 2026-07-14 | 0 | 0 | 44484.92 | Actual Total Cost
|  |  | L-58 |  | 2025-09-20 | 2026-06-30 | 08-Oct-24 A | 2026-05-05 | 5916660.47 | 5916660.49 | 11521346.23 | Planned Total Cost | [15 empty] | 35764.21 | 1575979.74 | 3991146.21 | 2060671.92 | 1118203.29 | 1703513.27 | 589183.98 | 401210.43 | 45673.17
|  |  | L-58 |  | 2025-09-20 | 2026-06-30 | 08-Oct-24 A | 2026-05-05 | 5916660.47 | 5916660.49 | 11521346.23 | Remaining Total Cost | [16 empty] | 1234318.16 | 1807700.88 | 453339.25 | 506408.26 | 1361685.71 | 238878.87 | 2354.63
|  |  | L-58 |  | 2025-09-20 | 2026-06-30 | 08-Oct-24 A | 2026-05-05 | 5916660.47 | 5916660.49 | 11521346.23 | Actual Total Cost |  |  |  |  | 6666.9 | 331497.37 | 705026.18 | 334452.34 | 561782.02 | 402725.21 | 255057.73 | 275122.95 | 50947.48 | 1645691.92 | 1311438.56 | 36251.83
|  |  | JDH3-02-008-L-58-Storm Network - ST |  | 2025-09-28 | 2026-04-08 | 30-Nov-24 A | 2026-03-08 | 5376817.2 | 5376817.2 | 9404437.31 | Planned Total Cost | [15 empty] | 35764.21 | 1575979.74 | 3969025.83 | 2060671.92 | 1118203.29 | 576770.95 | 68021.38
|  |  | JDH3-02-008-L-58-Storm Network - ST |  | 2025-09-28 | 2026-04-08 | 30-Nov-24 A | 2026-03-08 | 5376817.2 | 5376817.2 | 9404437.31 | Remaining Total Cost | [16 empty] | 1234318.16 | 1801463.42 | 453339.25 | 506408.26 | 32091.04
|  |  | JDH3-02-008-L-58-Storm Network - ST |  | 2025-09-28 | 2026-04-08 | 30-Nov-24 A | 2026-03-08 | 5376817.2 | 5376817.2 | 9404437.31 | Actual Total Cost |  |  |  |  | 6666.9 | 331497.37 | 705026.18 | 334452.34 | 561782.02 | 402725.21 | 255057.73 | 275122.95 | 50947.48 | 1234224.95 | 1184626.28 | 34687.79
|  |  | JDH3-02-008-L-58-(ST)-Swales |  | 2025-09-28 | 2025-10-26 | 2025-11-06 | 2025-12-06 | 0 | 0 | 334640.72 | Planned Total Cost | [16 empty] | 255991.42 | 78649.3
|  |  | JDH3-02-008-L-58-(ST)-Swales |  | 2025-09-28 | 2025-10-26 | 2025-11-06 | 2025-12-06 | 0 | 0 | 334640.72 | Remaining Total Cost | [16 empty] | 255991.42 | 78649.3
|  |  | JDH3-02-008-L-58-(ST)-Swales |  | 2025-09-28 | 2025-10-26 | 2025-11-06 | 2025-12-06 | 0 | 0 | 334640.72 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(ST)-Box Culvert |  | 2025-10-27 | 2026-04-08 | 30-Nov-24 A | 2025-11-20 | 4166805.49 | 4166805.5 | 4550330.23 | Planned Total Cost | [15 empty] | 35764.21 | 508004.25 | 1533097.09 | 1248968.37 | 611795.02 | 544679.91 | 68021.38
|  |  | JDH3-02-008-L-58-(ST)-Box Culvert |  | 2025-10-27 | 2026-04-08 | 30-Nov-24 A | 2025-11-20 | 4166805.49 | 4166805.5 | 4550330.23 | Remaining Total Cost | [16 empty] | 383524.74
|  |  | JDH3-02-008-L-58-(ST)-Box Culvert |  | 2025-10-27 | 2026-04-08 | 30-Nov-24 A | 2025-11-20 | 4166805.49 | 4166805.5 | 4550330.23 | Actual Total Cost |  |  |  |  | 6666.9 | 324547.1 | 625578.6 | 316916.29 | 379459.4 | 302517.2 | 181621.37 | 180843.94 | 42707.65 | 901318.06 | 881691.13 | 22937.86
|  |  | JDH3-02-008-L-58-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2025-10-27 | 2025-11-17 | 01-Dec-24 A | 09-Jun-25 A | 2389-08-04 01:41 | 2389-08-04 01:41 | 178821.07 | Planned Total Cost | [15 empty] | 35764.21 | 143056.86
|  |  | JDH3-02-008-L-58-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2025-10-27 | 2025-11-17 | 01-Dec-24 A | 09-Jun-25 A | 2389-08-04 01:41 | 2389-08-04 01:41 | 178821.07 | Remaining Total Cost
|  |  | JDH3-02-008-L-58-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2025-10-27 | 2025-11-17 | 01-Dec-24 A | 09-Jun-25 A | 2389-08-04 01:41 | 2389-08-04 01:41 | 178821.07 | Actual Total Cost | [5 empty] | 69851.98 | 80357.72 | 10729.27 |  |  | 8941.06 | 8941.06
|  |  | JDH3-02-008-L-58-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2025-11-18 | 2026-03-26 | 30-Nov-24 A | 01-Sep-25 A | 2423969.25 | 2423969.24 | 2423969.25 | Planned Total Cost | [16 empty] | 270778.83 | 725833.03 | 853685.16 | 238347.19 | 335325.04
|  |  | JDH3-02-008-L-58-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2025-11-18 | 2026-03-26 | 30-Nov-24 A | 01-Sep-25 A | 2423969.25 | 2423969.24 | 2423969.25 | Remaining Total Cost
|  |  | JDH3-02-008-L-58-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2025-11-18 | 2026-03-26 | 30-Nov-24 A | 01-Sep-25 A | 2423969.25 | 2423969.24 | 2423969.25 | Actual Total Cost |  |  |  |  | 6666.9 | 254695.13 | 389959.9 | 245447.3 | 339736.48 | 287104 | 147943.96 | 135170.32 |  | 591774.06 | 25471.2
|  |  | JDH3-02-008-L-58-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2025-12-03 | 2026-02-22 | 05-Jan-25 A | 2025-11-08 | 1254459.04 | 1254459.05 | 1575995.1 | Planned Total Cost | [17 empty] | 807264.06 | 395283.21 | 373447.84
|  |  | JDH3-02-008-L-58-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2025-12-03 | 2026-02-22 | 05-Jan-25 A | 2025-11-08 | 1254459.04 | 1254459.05 | 1575995.1 | Remaining Total Cost | [16 empty] | 321536.07
|  |  | JDH3-02-008-L-58-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2025-12-03 | 2026-02-22 | 05-Jan-25 A | 2025-11-08 | 1254459.04 | 1254459.05 | 1575995.1 | Actual Total Cost | [6 empty] | 62685.98 | 55143.25 | 39722.92 | 15413.21 | 19761.71 | 31757.93 | 42707.65 | 244650.59 | 719677.96 | 22937.86
|  |  | JDH3-02-008-L-58-(ST)- Concrete Box Culvert With Dim (4000x2000) depth from 3.51 to 4.50 |  | 2026-02-23 | 2026-03-10 | 14-Sep-25 A | 2025-11-20 | 1929-12-12 04:19 | 1929-12-12 04:19 | 72927.86 | Planned Total Cost | [16 empty] | 72927.86
|  |  | JDH3-02-008-L-58-(ST)- Concrete Box Culvert With Dim (4000x2000) depth from 3.51 to 4.50 |  | 2026-02-23 | 2026-03-10 | 14-Sep-25 A | 2025-11-20 | 1929-12-12 04:19 | 1929-12-12 04:19 | 72927.86 | Remaining Total Cost | [16 empty] | 61988.68
|  |  | JDH3-02-008-L-58-(ST)- Concrete Box Culvert With Dim (4000x2000) depth from 3.51 to 4.50 |  | 2026-02-23 | 2026-03-10 | 14-Sep-25 A | 2025-11-20 | 1929-12-12 04:19 | 1929-12-12 04:19 | 72927.86 | Actual Total Cost | [14 empty] | 10939.18
|  |  | JDH3-02-008-L-58-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2026-03-11 | 2026-04-08 | 05-Jan-25 A | 20-Sep-25 A | 298616.95 | 298616.96 | 298616.95 | Planned Total Cost | [16 empty] | 21240.71 |  |  |  | 209354.86 | 68021.38
|  |  | JDH3-02-008-L-58-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2026-03-11 | 2026-04-08 | 05-Jan-25 A | 20-Sep-25 A | 298616.95 | 298616.96 | 298616.95 | Remaining Total Cost
|  |  | JDH3-02-008-L-58-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2026-03-11 | 2026-04-08 | 05-Jan-25 A | 20-Sep-25 A | 298616.95 | 298616.96 | 298616.95 | Actual Total Cost | [6 empty] | 92575.01 | 5596.47 |  |  | 4974.64 | 4974.64 |  | 64893.41 | 125602.79
|  |  | JDH3-02-008-L-58-(ST)-NetWork |  | 2025-10-12 | 2026-03-03 | 23-Dec-24 A | 2026-03-08 | 1210011.71 | 1210011.7 | 4519466.36 | Planned Total Cost | [16 empty] | 811984.07 | 2357279.44 | 811703.55 | 506408.26 | 32091.04
|  |  | JDH3-02-008-L-58-(ST)-NetWork |  | 2025-10-12 | 2026-03-03 | 23-Dec-24 A | 2026-03-08 | 1210011.71 | 1210011.7 | 4519466.36 | Remaining Total Cost | [16 empty] | 594802 | 1722814.12 | 453339.25 | 506408.26 | 32091.04
|  |  | JDH3-02-008-L-58-(ST)-NetWork |  | 2025-10-12 | 2026-03-03 | 23-Dec-24 A | 2026-03-08 | 1210011.71 | 1210011.7 | 4519466.36 | Actual Total Cost | [5 empty] | 6950.27 | 79447.58 | 17536.05 | 182322.61 | 100208.01 | 73436.36 | 94279.01 | 8239.83 | 332906.9 | 302935.15 | 11749.93
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-10-12 | 2025-11-04 | 2025-11-20 | 2025-12-15 | 0 | 0 | 233738.36 | Planned Total Cost | [16 empty] | 79164.26 | 154574.1
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-10-12 | 2025-11-04 | 2025-11-20 | 2025-12-15 | 0 | 0 | 233738.36 | Remaining Total Cost | [16 empty] | 79164.26 | 154574.1
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-10-12 | 2025-11-04 | 2025-11-20 | 2025-12-15 | 0 | 0 | 233738.36 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-10-16 | 2025-12-30 | 03-Sep-25 A | 2026-01-08 | 1912-01-29 05:17 | 1912-01-29 05:17 | 606074.68 | Planned Total Cost | [16 empty] | 324063.26 | 246207.1 | 35804.32
|  |  | JDH3-02-008-L-58-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-10-16 | 2025-12-30 | 03-Sep-25 A | 2026-01-08 | 1912-01-29 05:17 | 1912-01-29 05:17 | 606074.68 | Remaining Total Cost | [16 empty] | 515637.74 | 50220.4 | 35804.32
|  |  | JDH3-02-008-L-58-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-10-16 | 2025-12-30 | 03-Sep-25 A | 2026-01-08 | 1912-01-29 05:17 | 1912-01-29 05:17 | 606074.68 | Actual Total Cost | [14 empty] | 4153.88 | 258.34
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-11-05 | 2025-12-03 | 02-Mar-25 A | 2025-12-20 | 2140-03-16 18:00 | 2140-03-16 18:00 | 197479.25 | Planned Total Cost | [16 empty] | 126801.69 | 70677.56
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-11-05 | 2025-12-03 | 02-Mar-25 A | 2025-12-20 | 2140-03-16 18:00 | 2140-03-16 18:00 | 197479.25 | Remaining Total Cost | [17 empty] | 109743.5
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-11-05 | 2025-12-03 | 02-Mar-25 A | 2025-12-20 | 2140-03-16 18:00 | 2140-03-16 18:00 | 197479.25 | Actual Total Cost | [8 empty] | 87735.75
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2025-11-12 | 2025-11-25 | 05-Jan-25 A | 2025-12-27 | 2043-04-19 06:43 | 2043-04-19 06:43 | 90849.62 | Planned Total Cost | [16 empty] | 52340.28 | 38509.34
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2025-11-12 | 2025-11-25 | 05-Jan-25 A | 2025-12-27 | 2043-04-19 06:43 | 2043-04-19 06:43 | 90849.62 | Remaining Total Cost | [17 empty] | 38509.34
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2025-11-12 | 2025-11-25 | 05-Jan-25 A | 2025-12-27 | 2043-04-19 06:43 | 2043-04-19 06:43 | 90849.62 | Actual Total Cost | [6 empty] | 30795.68 | 17536.05 | 3188.52 | 820.03
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2025-11-15 | 2025-11-25 | 23-Dec-24 A | 2025-12-22 | 2052-03-24 03:50 | 2052-03-24 04:05 | 69502.7 | Planned Total Cost | [16 empty] | 55602.16 | 13900.54
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2025-11-15 | 2025-11-25 | 23-Dec-24 A | 2025-12-22 | 2052-03-24 03:50 | 2052-03-24 04:05 | 69502.7 | Remaining Total Cost | [17 empty] | 13900.54
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2025-11-15 | 2025-11-25 | 23-Dec-24 A | 2025-12-22 | 2052-03-24 03:50 | 2052-03-24 04:05 | 69502.7 | Actual Total Cost | [5 empty] | 6950.27 | 48651.9
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-11-17 | 2025-12-07 | 08-Mar-25 A | 2025-12-20 | 2381-08-31 13:12 | 2381-08-31 12:58 | 200783.55 | Planned Total Cost | [16 empty] | 174012.41 | 26771.14
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-11-17 | 2025-12-07 | 08-Mar-25 A | 2025-12-20 | 2381-08-31 13:12 | 2381-08-31 12:58 | 200783.55 | Remaining Total Cost | [17 empty] | 24857.01
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-11-17 | 2025-12-07 | 08-Mar-25 A | 2025-12-20 | 2381-08-31 13:12 | 2381-08-31 12:58 | 200783.55 | Actual Total Cost | [8 empty] | 91398.35 | 69228.49 |  |  |  | 3642.5 | 11225.46 | 431.75
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-12-02 | 2025-12-13 | 08-Aug-25 A | 2025-12-22 | 44458.35 | 2021-09-19 08:38 | 55572.94 | Planned Total Cost | [17 empty] | 55572.94
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-12-02 | 2025-12-13 | 08-Aug-25 A | 2025-12-22 | 44458.35 | 2021-09-19 08:38 | 55572.94 | Remaining Total Cost | [17 empty] | 11114.59
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-12-02 | 2025-12-13 | 08-Aug-25 A | 2025-12-22 | 44458.35 | 2021-09-19 08:38 | 55572.94 | Actual Total Cost | [13 empty] | 44458.36
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 0.00 to 1.50 m |  | 2025-12-04 | 2025-12-15 | 10-Aug-25 A | 2025-12-22 | 2044-05-26 07:55 | 2044-05-26 07:55 | 65929.16 | Planned Total Cost | [17 empty] | 65929.16
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 0.00 to 1.50 m |  | 2025-12-04 | 2025-12-15 | 10-Aug-25 A | 2025-12-22 | 2044-05-26 07:55 | 2044-05-26 07:55 | 65929.16 | Remaining Total Cost | [17 empty] | 13185.83
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 0.00 to 1.50 m |  | 2025-12-04 | 2025-12-15 | 10-Aug-25 A | 2025-12-22 | 2044-05-26 07:55 | 2044-05-26 07:55 | 65929.16 | Actual Total Cost | [13 empty] | 52743.33
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-12-07 | 2025-12-20 | 14-Apr-25 A | 2025-12-27 | 1910-08-28 07:55 | 1910-08-28 07:55 | 15573.31 | Planned Total Cost | [17 empty] | 15573.31
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-12-07 | 2025-12-20 | 14-Apr-25 A | 2025-12-27 | 1910-08-28 07:55 | 1910-08-28 07:55 | 15573.31 | Remaining Total Cost | [17 empty] | 11679.98
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-12-07 | 2025-12-20 | 14-Apr-25 A | 2025-12-27 | 1910-08-28 07:55 | 1910-08-28 07:55 | 15573.31 | Actual Total Cost | [9 empty] | 3601.33 | 292
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2025-12-07 | 2025-12-17 | 12-Aug-25 A | 2025-12-17 | 2310-01-26 22:05 | 2310-01-26 22:05 | 152905.36 | Planned Total Cost | [17 empty] | 152905.36
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2025-12-07 | 2025-12-17 | 12-Aug-25 A | 2025-12-17 | 2310-01-26 22:05 | 2310-01-26 22:05 | 152905.36 | Remaining Total Cost | [17 empty] | 3128.45
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2025-12-07 | 2025-12-17 | 12-Aug-25 A | 2025-12-17 | 2310-01-26 22:05 | 2310-01-26 22:05 | 152905.36 | Actual Total Cost | [13 empty] | 140394.74 | 9034.7 | 347.49
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-12-09 | 2026-01-22 | 15-Aug-25 A | 2025-12-21 | 380901.44 | 380901.44 | 1061820.16 | Planned Total Cost | [17 empty] | 703455.86 | 358364.31
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-12-09 | 2026-01-22 | 15-Aug-25 A | 2025-12-21 | 380901.44 | 380901.44 | 1061820.16 | Remaining Total Cost | [17 empty] | 680918.72
|  |  | JDH3-02-008-L-58-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-12-09 | 2026-01-22 | 15-Aug-25 A | 2025-12-21 | 380901.44 | 380901.44 | 1061820.16 | Actual Total Cost | [13 empty] | 91667.98 | 278521.11 | 10712.35
|  |  | JDH3-02-008-L-58-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-12-09 | 2026-01-04 | 15-Apr-25 A | 2026-01-04 | 2159-06-03 06:43 | 2159-06-03 06:43 | 219002.65 | Planned Total Cost | [17 empty] | 198513.73 | 20488.91
|  |  | JDH3-02-008-L-58-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-12-09 | 2026-01-04 | 15-Apr-25 A | 2026-01-04 | 2159-06-03 06:43 | 2159-06-03 06:43 | 219002.65 | Remaining Total Cost | [17 empty] | 103760.45 | 20488.91
|  |  | JDH3-02-008-L-58-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-12-09 | 2026-01-04 | 15-Apr-25 A | 2026-01-04 | 2159-06-03 06:43 | 2159-06-03 06:43 | 219002.65 | Actual Total Cost | [9 empty] | 26558.16 | 22764.13 | 45430.99
|  |  | JDH3-02-008-L-58-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-12-13 | 2025-12-30 | 20-May-25 A | 2026-01-04 | 1916-10-10 19:12 | 1916-10-10 19:12 | 82125.99 | Planned Total Cost | [17 empty] | 72257.18 | 9868.81
|  |  | JDH3-02-008-L-58-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-12-13 | 2025-12-30 | 20-May-25 A | 2026-01-04 | 1916-10-10 19:12 | 1916-10-10 19:12 | 82125.99 | Remaining Total Cost | [17 empty] | 66128.38 | 9868.81
|  |  | JDH3-02-008-L-58-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-12-13 | 2025-12-30 | 20-May-25 A | 2026-01-04 | 1916-10-10 19:12 | 1916-10-10 19:12 | 82125.99 | Actual Total Cost | [10 empty] | 3830.5 | 2298.3
|  |  | JDH3-02-008-L-58-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-12-17 | 2026-01-06 | 2025-12-21 | 2026-01-11 | 0 | 0 | 305039.37 | Planned Total Cost | [17 empty] | 199353.4 | 105685.97
|  |  | JDH3-02-008-L-58-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-12-17 | 2026-01-06 | 2025-12-21 | 2026-01-11 | 0 | 0 | 305039.37 | Remaining Total Cost | [17 empty] | 199353.4 | 105685.97
|  |  | JDH3-02-008-L-58-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-12-17 | 2026-01-06 | 2025-12-21 | 2026-01-11 | 0 | 0 | 305039.37 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-12-20 | 2025-12-30 | 2025-12-23 | 2026-01-04 | 0 | 0 | 109501.3 | Planned Total Cost | [17 empty] | 96342.9 | 13158.41
|  |  | JDH3-02-008-L-58-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-12-20 | 2025-12-30 | 2025-12-23 | 2026-01-04 | 0 | 0 | 109501.3 | Remaining Total Cost | [17 empty] | 96342.9 | 13158.41
|  |  | JDH3-02-008-L-58-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-12-20 | 2025-12-30 | 2025-12-23 | 2026-01-04 | 0 | 0 | 109501.3 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-12-15 | 2026-01-01 | 20-May-25 A | 2026-01-06 | 2177-06-14 06:58 | 2177-06-14 06:43 | 279619.39 | Planned Total Cost | [17 empty] | 201526.95 | 78092.45
|  |  | JDH3-02-008-L-58-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-12-15 | 2026-01-01 | 20-May-25 A | 2026-01-06 | 2177-06-14 06:58 | 2177-06-14 06:43 | 279619.39 | Remaining Total Cost | [17 empty] | 100187.66 | 78092.45
|  |  | JDH3-02-008-L-58-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-12-15 | 2026-01-01 | 20-May-25 A | 2026-01-06 | 2177-06-14 06:58 | 2177-06-14 06:43 | 279619.39 | Actual Total Cost | [10 empty] | 46549.73 | 46549.72 | 8239.83
|  |  | JDH3-02-008-L-58-(ST)- Single Catchbasine Works |  | 2025-12-22 | 2026-01-29 | 2025-12-25 | 2026-02-03 | 0 | 0 | 219002.74 | Planned Total Cost | [17 empty] | 24371.88 | 190240.38 | 4390.48
|  |  | JDH3-02-008-L-58-(ST)- Single Catchbasine Works |  | 2025-12-22 | 2026-01-29 | 2025-12-25 | 2026-02-03 | 0 | 0 | 219002.74 | Remaining Total Cost | [17 empty] | 24371.88 | 190240.38 | 4390.48
|  |  | JDH3-02-008-L-58-(ST)- Single Catchbasine Works |  | 2025-12-22 | 2026-01-29 | 2025-12-25 | 2026-02-03 | 0 | 0 | 219002.74 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(ST)- Double Catchbasine Works |  | 2026-01-31 | 2026-03-03 | 2026-02-03 | 2026-03-08 | 0 | 0 | 534108.82 | Planned Total Cost | [19 empty] | 502017.78 | 32091.04
|  |  | JDH3-02-008-L-58-(ST)- Double Catchbasine Works |  | 2026-01-31 | 2026-03-03 | 2026-02-03 | 2026-03-08 | 0 | 0 | 534108.82 | Remaining Total Cost | [19 empty] | 502017.78 | 32091.04
|  |  | JDH3-02-008-L-58-(ST)- Double Catchbasine Works |  | 2026-01-31 | 2026-03-03 | 2026-02-03 | 2026-03-08 | 0 | 0 | 534108.82 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(ST)-PIPES ENCASEMENT |  | 2025-12-11 | 2025-12-17 | 2025-12-20 | 2025-12-27 | 0 | 0 | 20837 | Planned Total Cost | [17 empty] | 20837
|  |  | JDH3-02-008-L-58-(ST)-PIPES ENCASEMENT |  | 2025-12-11 | 2025-12-17 | 2025-12-20 | 2025-12-27 | 0 | 0 | 20837 | Remaining Total Cost | [17 empty] | 20837
|  |  | JDH3-02-008-L-58-(ST)-PIPES ENCASEMENT |  | 2025-12-11 | 2025-12-17 | 2025-12-20 | 2025-12-27 | 0 | 0 | 20837 | Actual Total Cost
|  |  | JDH3-02-008-L-58-TSE Network - TSE |  | 2026-04-09 | 2026-06-06 | 02-Aug-25 A | 2026-04-11 | 539843.27 | 539843.29 | 1986638.43 | Planned Total Cost | [17 empty] | 22120.39 |  |  | 1126742.32 | 393246.75 | 398855.8 | 45673.17
|  |  | JDH3-02-008-L-58-TSE Network - TSE |  | 2026-04-09 | 2026-06-06 | 02-Aug-25 A | 2026-04-11 | 539843.27 | 539843.29 | 1986638.43 | Remaining Total Cost | [17 empty] | 6237.46 |  |  | 1329594.67 | 110963.02
|  |  | JDH3-02-008-L-58-TSE Network - TSE |  | 2026-04-09 | 2026-06-06 | 02-Aug-25 A | 2026-04-11 | 539843.27 | 539843.29 | 1986638.43 | Actual Total Cost | [13 empty] | 411466.96 | 126812.29 | 1564.04
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-04-09 | 2026-06-02 | 2026-03-08 | 2026-04-11 | 0 | 0 | 30192.85 | Planned Total Cost | [20 empty] | 27173.56 | 3019.28
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-04-09 | 2026-06-02 | 2026-03-08 | 2026-04-11 | 0 | 0 | 30192.85 | Remaining Total Cost | [20 empty] | 27173.56 | 3019.28
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-04-09 | 2026-06-02 | 2026-03-08 | 2026-04-11 | 0 | 0 | 30192.85 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-04-12 | 2026-06-06 | 02-Aug-25 A | 27-Sep-25 A | 221203.88 | 221203.88 | 221203.88 | Planned Total Cost | [17 empty] | 22120.39 |  |  |  | 110601.94 | 72681.27 | 15800.28
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-04-12 | 2026-06-06 | 02-Aug-25 A | 27-Sep-25 A | 221203.88 | 221203.88 | 221203.88 | Remaining Total Cost
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-04-12 | 2026-06-06 | 02-Aug-25 A | 27-Sep-25 A | 221203.88 | 221203.88 | 221203.88 | Actual Total Cost | [13 empty] | 152934.67 | 68269.21
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2026-04-19 | 2026-06-02 | 2026-03-08 | 2026-04-11 | 0 | 0 | 11016.46 | Planned Total Cost | [20 empty] | 9914.82 | 1101.65
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2026-04-19 | 2026-06-02 | 2026-03-08 | 2026-04-11 | 0 | 0 | 11016.46 | Remaining Total Cost | [20 empty] | 9914.82 | 1101.65
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2026-04-19 | 2026-06-02 | 2026-03-08 | 2026-04-11 | 0 | 0 | 11016.46 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-04-21 | 2026-06-02 | 2026-03-10 | 2026-04-11 | 0 | 0 | 2483.01 | Planned Total Cost | [20 empty] | 2234.71 | 248.3
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-04-21 | 2026-06-02 | 2026-03-10 | 2026-04-11 | 0 | 0 | 2483.01 | Remaining Total Cost | [20 empty] | 2234.71 | 248.3
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2026-04-21 | 2026-06-02 | 2026-03-10 | 2026-04-11 | 0 | 0 | 2483.01 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-04-23 | 2026-06-04 | 16-Aug-25 A | 2025-12-18 | 292491.51 | 292491.53 | 298728.98 | Planned Total Cost | [21 empty] | 107542.43 | 161313.65 | 29872.9
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-04-23 | 2026-06-04 | 16-Aug-25 A | 2025-12-18 | 292491.51 | 292491.53 | 298728.98 | Remaining Total Cost | [17 empty] | 6237.46
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-04-23 | 2026-06-04 | 16-Aug-25 A | 2025-12-18 | 292491.51 | 292491.53 | 298728.98 | Actual Total Cost | [13 empty] | 255875.15 | 35941.08 | 675.3
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 2.51 to 3.5 m |  | 2026-04-27 | 2026-06-03 | 23-Aug-25 A | 2026-04-08 | 1971-08-02 21:07 | 1971-08-02 21:07 | 282618.64 | Planned Total Cost | [20 empty] | 28261.86 | 89495.9 | 164860.88
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 2.51 to 3.5 m |  | 2026-04-27 | 2026-06-03 | 23-Aug-25 A | 2026-04-08 | 1971-08-02 21:07 | 1971-08-02 21:07 | 282618.64 | Remaining Total Cost | [20 empty] | 231114.22 | 25356.54
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 2.51 to 3.5 m |  | 2026-04-27 | 2026-06-03 | 23-Aug-25 A | 2026-04-08 | 1971-08-02 21:07 | 1971-08-02 21:07 | 282618.64 | Actual Total Cost | [13 empty] | 2657.14 | 22602 | 888.74
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 0 to 1.5 m |  | 2026-04-30 | 2026-05-11 | 2026-03-08 | 2026-03-19 | 0 | 0 | 174908.03 | Planned Total Cost | [20 empty] | 174908.03
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 0 to 1.5 m |  | 2026-04-30 | 2026-05-11 | 2026-03-08 | 2026-03-19 | 0 | 0 | 174908.03 | Remaining Total Cost | [20 empty] | 174908.03
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 0 to 1.5 m |  | 2026-04-30 | 2026-05-11 | 2026-03-08 | 2026-03-19 | 0 | 0 | 174908.03 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 1.51 to 2.5 m |  | 2026-05-03 | 2026-05-24 | 2026-03-10 | 2026-04-01 | 0 | 0 | 503962.57 | Planned Total Cost | [20 empty] | 493799.33 | 10163.25
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 1.51 to 2.5 m |  | 2026-05-03 | 2026-05-24 | 2026-03-10 | 2026-04-01 | 0 | 0 | 503962.57 | Remaining Total Cost | [20 empty] | 493799.33 | 10163.25
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 1.51 to 2.5 m |  | 2026-05-03 | 2026-05-24 | 2026-03-10 | 2026-04-01 | 0 | 0 | 503962.57 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 2.51 to 3.5 m |  | 2026-05-06 | 2026-05-17 | 2026-03-14 | 2026-03-25 | 0 | 0 | 46487.28 | Planned Total Cost | [20 empty] | 46487.28
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 2.51 to 3.5 m |  | 2026-05-06 | 2026-05-17 | 2026-03-14 | 2026-03-25 | 0 | 0 | 46487.28 | Remaining Total Cost | [20 empty] | 46487.28
|  |  | JDH3-02-008-L-58-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 2.51 to 3.5 m |  | 2026-05-06 | 2026-05-17 | 2026-03-14 | 2026-03-25 | 0 | 0 | 46487.28 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-16 | 2026-05-19 | 2026-03-23 | 2026-03-28 | 0 | 0 | 6465.8 | Planned Total Cost | [20 empty] | 6465.8
|  |  | JDH3-02-008-L-58-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-16 | 2026-05-19 | 2026-03-23 | 2026-03-28 | 0 | 0 | 6465.8 | Remaining Total Cost | [20 empty] | 6465.8
|  |  | JDH3-02-008-L-58-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-16 | 2026-05-19 | 2026-03-23 | 2026-03-28 | 0 | 0 | 6465.8 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(TSE)-Supply and install gate valves-250 mm |  | 2026-05-18 | 2026-05-21 | 2026-03-25 | 2026-03-30 | 0 | 0 | 17962.79 | Planned Total Cost | [20 empty] | 17962.79
|  |  | JDH3-02-008-L-58-(TSE)-Supply and install gate valves-250 mm |  | 2026-05-18 | 2026-05-21 | 2026-03-25 | 2026-03-30 | 0 | 0 | 17962.79 | Remaining Total Cost | [20 empty] | 17962.79
|  |  | JDH3-02-008-L-58-(TSE)-Supply and install gate valves-250 mm |  | 2026-05-18 | 2026-05-21 | 2026-03-25 | 2026-03-30 | 0 | 0 | 17962.79 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2026-05-20 | 2026-05-24 | 2026-03-28 | 2026-04-01 | 0 | 0 | 165607.04 | Planned Total Cost | [20 empty] | 158927.56 | 6679.48
|  |  | JDH3-02-008-L-58-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2026-05-20 | 2026-05-24 | 2026-03-28 | 2026-04-01 | 0 | 0 | 165607.04 | Remaining Total Cost | [20 empty] | 158927.56 | 6679.48
|  |  | JDH3-02-008-L-58-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2026-05-20 | 2026-05-24 | 2026-03-28 | 2026-04-01 | 0 | 0 | 165607.04 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(TSE)-Supply and install of butterfly valves-600 mm. |  | 2026-05-23 | 2026-05-26 | 2026-03-30 | 2026-04-04 | 0 | 0 | 46575.2 | Planned Total Cost | [20 empty] | 25010.88 | 21564.32
|  |  | JDH3-02-008-L-58-(TSE)-Supply and install of butterfly valves-600 mm. |  | 2026-05-23 | 2026-05-26 | 2026-03-30 | 2026-04-04 | 0 | 0 | 46575.2 | Remaining Total Cost | [20 empty] | 25010.88 | 21564.32
|  |  | JDH3-02-008-L-58-(TSE)-Supply and install of butterfly valves-600 mm. |  | 2026-05-23 | 2026-05-26 | 2026-03-30 | 2026-04-04 | 0 | 0 | 46575.2 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(TSE)-Supply and install of Wash-out valves-150 mm. |  | 2026-05-25 | 2026-05-28 | 2026-04-01 | 2026-04-06 | 0 | 0 | 35245.73 | Planned Total Cost | [21 empty] | 35245.73
|  |  | JDH3-02-008-L-58-(TSE)-Supply and install of Wash-out valves-150 mm. |  | 2026-05-25 | 2026-05-28 | 2026-04-01 | 2026-04-06 | 0 | 0 | 35245.73 | Remaining Total Cost | [21 empty] | 35245.73
|  |  | JDH3-02-008-L-58-(TSE)-Supply and install of Wash-out valves-150 mm. |  | 2026-05-25 | 2026-05-28 | 2026-04-01 | 2026-04-06 | 0 | 0 | 35245.73 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-05-27 | 2026-05-31 | 2026-04-04 | 2026-04-08 | 0 | 0 | 7444.14 | Planned Total Cost | [21 empty] | 7444.14
|  |  | JDH3-02-008-L-58-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-05-27 | 2026-05-31 | 2026-04-04 | 2026-04-08 | 0 | 0 | 7444.14 | Remaining Total Cost | [21 empty] | 7444.14
|  |  | JDH3-02-008-L-58-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-05-27 | 2026-05-31 | 2026-04-04 | 2026-04-08 | 0 | 0 | 7444.14 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-05-09 | 2026-05-19 | 2026-03-16 | 2026-03-28 | 0 | 0 | 63716.09 | Planned Total Cost | [20 empty] | 63716.09
|  |  | JDH3-02-008-L-58-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-05-09 | 2026-05-19 | 2026-03-16 | 2026-03-28 | 0 | 0 | 63716.09 | Remaining Total Cost | [20 empty] | 63716.09
|  |  | JDH3-02-008-L-58-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-05-09 | 2026-05-19 | 2026-03-16 | 2026-03-28 | 0 | 0 | 63716.09 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(TSE)- Supply and Construct R.C Valves Chamber on 500-630 mm Diameter pipelines |  | 2026-05-11 | 2026-05-19 | 2026-03-18 | 2026-03-28 | 0 | 0 | 12151.39 | Planned Total Cost | [20 empty] | 12151.39
|  |  | JDH3-02-008-L-58-(TSE)- Supply and Construct R.C Valves Chamber on 500-630 mm Diameter pipelines |  | 2026-05-11 | 2026-05-19 | 2026-03-18 | 2026-03-28 | 0 | 0 | 12151.39 | Remaining Total Cost | [20 empty] | 12151.39
|  |  | JDH3-02-008-L-58-(TSE)- Supply and Construct R.C Valves Chamber on 500-630 mm Diameter pipelines |  | 2026-05-11 | 2026-05-19 | 2026-03-18 | 2026-03-28 | 0 | 0 | 12151.39 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(TSE)- Supply and Construct Wash-out Valves Chamber on 450-630 mm Diameter pipeline |  | 2026-05-13 | 2026-05-21 | 2026-03-21 | 2026-03-30 | 0 | 0 | 56389.26 | Planned Total Cost | [20 empty] | 56389.26
|  |  | JDH3-02-008-L-58-(TSE)- Supply and Construct Wash-out Valves Chamber on 450-630 mm Diameter pipeline |  | 2026-05-13 | 2026-05-21 | 2026-03-21 | 2026-03-30 | 0 | 0 | 56389.26 | Remaining Total Cost | [20 empty] | 56389.26
|  |  | JDH3-02-008-L-58-(TSE)- Supply and Construct Wash-out Valves Chamber on 450-630 mm Diameter pipeline |  | 2026-05-13 | 2026-05-21 | 2026-03-21 | 2026-03-30 | 0 | 0 | 56389.26 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-05-16 | 2026-05-24 | 2026-03-23 | 2026-04-01 | 0 | 0 | 3479.28 | Planned Total Cost | [20 empty] | 3338.95 | 140.33
|  |  | JDH3-02-008-L-58-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-05-16 | 2026-05-24 | 2026-03-23 | 2026-04-01 | 0 | 0 | 3479.28 | Remaining Total Cost | [20 empty] | 3338.95 | 140.33
|  |  | JDH3-02-008-L-58-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-05-16 | 2026-05-24 | 2026-03-23 | 2026-04-01 | 0 | 0 | 3479.28 | Actual Total Cost
|  |  | JDH3-02-008-L-58-Potable Water Network - WT |  | 2026-05-25 | 2026-06-13 | 2026-04-01 | 2026-04-18 | 0 | 0 | 80475.39 | Planned Total Cost | [21 empty] | 80475.39
|  |  | JDH3-02-008-L-58-Potable Water Network - WT |  | 2026-05-25 | 2026-06-13 | 2026-04-01 | 2026-04-18 | 0 | 0 | 80475.39 | Remaining Total Cost | [21 empty] | 80475.39
|  |  | JDH3-02-008-L-58-Potable Water Network - WT |  | 2026-05-25 | 2026-06-13 | 2026-04-01 | 2026-04-18 | 0 | 0 | 80475.39 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-05-25 | 2026-06-04 | 2026-04-01 | 2026-04-13 | 0 | 0 | 7928.17 | Planned Total Cost | [21 empty] | 7928.17
|  |  | JDH3-02-008-L-58-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-05-25 | 2026-06-04 | 2026-04-01 | 2026-04-13 | 0 | 0 | 7928.17 | Remaining Total Cost | [21 empty] | 7928.17
|  |  | JDH3-02-008-L-58-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-05-25 | 2026-06-04 | 2026-04-01 | 2026-04-13 | 0 | 0 | 7928.17 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(WT)- Supply and install 3-out fire hydrant |  | 2026-06-07 | 2026-06-13 | 2026-04-11 | 2026-04-18 | 0 | 0 | 72547.22 | Planned Total Cost | [21 empty] | 72547.22
|  |  | JDH3-02-008-L-58-(WT)- Supply and install 3-out fire hydrant |  | 2026-06-07 | 2026-06-13 | 2026-04-11 | 2026-04-18 | 0 | 0 | 72547.22 | Remaining Total Cost | [21 empty] | 72547.22
|  |  | JDH3-02-008-L-58-(WT)- Supply and install 3-out fire hydrant |  | 2026-06-07 | 2026-06-13 | 2026-04-11 | 2026-04-18 | 0 | 0 | 72547.22 | Actual Total Cost
|  |  | JDH3-02-008-L-58-Street Lighting Network -SL |  | 2026-06-14 | 2026-06-30 | 2026-04-18 | 2026-05-05 | 0 | 0 | 49795.09 | Planned Total Cost | [21 empty] | 47440.46 | 2354.63
|  |  | JDH3-02-008-L-58-Street Lighting Network -SL |  | 2026-06-14 | 2026-06-30 | 2026-04-18 | 2026-05-05 | 0 | 0 | 49795.09 | Remaining Total Cost | [21 empty] | 47440.46 | 2354.63
|  |  | JDH3-02-008-L-58-Street Lighting Network -SL |  | 2026-06-14 | 2026-06-30 | 2026-04-18 | 2026-05-05 | 0 | 0 | 49795.09 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx6 mm² |  | 2026-06-14 | 2026-06-30 | 2026-04-18 | 2026-05-05 | 0 | 0 | 22247.02 | Planned Total Cost | [21 empty] | 20022.31 | 2224.7
|  |  | JDH3-02-008-L-58-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx6 mm² |  | 2026-06-14 | 2026-06-30 | 2026-04-18 | 2026-05-05 | 0 | 0 | 22247.02 | Remaining Total Cost | [21 empty] | 20022.31 | 2224.7
|  |  | JDH3-02-008-L-58-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx6 mm² |  | 2026-06-14 | 2026-06-30 | 2026-04-18 | 2026-05-05 | 0 | 0 | 22247.02 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(STL)- Supply,install,connect and test single core PVC insulated copper 6mm2 |  | 2026-06-21 | 2026-06-27 | 2026-04-25 | 2026-05-02 | 0 | 0 | 2416.1 | Planned Total Cost | [21 empty] | 2286.17 | 129.93
|  |  | JDH3-02-008-L-58-(STL)- Supply,install,connect and test single core PVC insulated copper 6mm2 |  | 2026-06-21 | 2026-06-27 | 2026-04-25 | 2026-05-02 | 0 | 0 | 2416.1 | Remaining Total Cost | [21 empty] | 2286.17 | 129.93
|  |  | JDH3-02-008-L-58-(STL)- Supply,install,connect and test single core PVC insulated copper 6mm2 |  | 2026-06-21 | 2026-06-27 | 2026-04-25 | 2026-05-02 | 0 | 0 | 2416.1 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2026-06-24 | 2026-06-25 | 2026-04-28 | 2026-04-30 | 0 | 0 | 756.08 | Planned Total Cost | [21 empty] | 756.08
|  |  | JDH3-02-008-L-58-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2026-06-24 | 2026-06-25 | 2026-04-28 | 2026-04-30 | 0 | 0 | 756.08 | Remaining Total Cost | [21 empty] | 756.08
|  |  | JDH3-02-008-L-58-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2026-06-24 | 2026-06-25 | 2026-04-28 | 2026-04-30 | 0 | 0 | 756.08 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-2 × 150 mm |  | 2026-06-14 | 2026-06-22 | 2026-04-18 | 2026-04-27 | 0 | 0 | 3066.13 | Planned Total Cost | [21 empty] | 3066.13
|  |  | JDH3-02-008-L-58-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-2 × 150 mm |  | 2026-06-14 | 2026-06-22 | 2026-04-18 | 2026-04-27 | 0 | 0 | 3066.13 | Remaining Total Cost | [21 empty] | 3066.13
|  |  | JDH3-02-008-L-58-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-2 × 150 mm |  | 2026-06-14 | 2026-06-22 | 2026-04-18 | 2026-04-27 | 0 | 0 | 3066.13 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-4 × 150 mm |  | 2026-06-14 | 2026-06-22 | 2026-04-18 | 2026-04-27 | 0 | 0 | 4786.79 | Planned Total Cost | [21 empty] | 4786.79
|  |  | JDH3-02-008-L-58-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-4 × 150 mm |  | 2026-06-14 | 2026-06-22 | 2026-04-18 | 2026-04-27 | 0 | 0 | 4786.79 | Remaining Total Cost | [21 empty] | 4786.79
|  |  | JDH3-02-008-L-58-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-4 × 150 mm |  | 2026-06-14 | 2026-06-22 | 2026-04-18 | 2026-04-27 | 0 | 0 | 4786.79 | Actual Total Cost
|  |  | JDH3-02-008-L-58-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2026-06-14 | 2026-06-20 | 2026-04-18 | 2026-04-25 | 0 | 0 | 16522.96 | Planned Total Cost | [21 empty] | 16522.96
|  |  | JDH3-02-008-L-58-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2026-06-14 | 2026-06-20 | 2026-04-18 | 2026-04-25 | 0 | 0 | 16522.96 | Remaining Total Cost | [21 empty] | 16522.96
|  |  | JDH3-02-008-L-58-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2026-06-14 | 2026-06-20 | 2026-04-18 | 2026-04-25 | 0 | 0 | 16522.96 | Actual Total Cost
|  |  | Z01 |  | 2025-12-24 | 2026-07-05 | 12-Nov-24 A | 2026-06-03 | 3916461.34 | 3916461.39 | 13509025.98 | Planned Total Cost | [14 empty] | 166670.21 | 3044470.53 | 170437.08 | 1270308.52 | 927461.9 | 1793527.31 | 3376453.52 | 2114053.7 | 643931.79 | 1711.42
|  |  | Z01 |  | 2025-12-24 | 2026-07-05 | 12-Nov-24 A | 2026-06-03 | 3916461.34 | 3916461.39 | 13509025.98 | Remaining Total Cost | [15 empty] | 3029175.32 | 170437.08 | 832112.48 | 196355.16 | 1658216.75 | 2488666.49 | 1021167.35 | 194722.58 | 1711.42
|  |  | Z01 |  | 2025-12-24 | 2026-07-05 | 12-Nov-24 A | 2026-06-03 | 3916461.34 | 3916461.39 | 13509025.98 | Actual Total Cost | [5 empty] | 1313.32 | 17768.52 | 109579.44 | 323499.24 | 312320.62 | 108241.21 | 37475.58 | 38448.87 | 521037.98 | 2353664.94 | 93111.68
|  |  | L-02 |  | 2025-12-24 | 2026-04-18 | 06-Jul-25 A | 2026-03-10 | 686388.69 | 686388.68 | 2251948.05 | Planned Total Cost | [15 empty] | 306720.99 |  | 1264652.32 | 463368.35 | 169304.59 | 47901.81
|  |  | L-02 |  | 2025-12-24 | 2026-04-18 | 06-Jul-25 A | 2026-03-10 | 686388.69 | 686388.68 | 2251948.05 | Remaining Total Cost | [15 empty] | 325541.52 |  | 826456.28 | 196355.16 | 169304.59 | 47901.81
|  |  | L-02 |  | 2025-12-24 | 2026-04-18 | 06-Jul-25 A | 2026-03-10 | 686388.69 | 686388.68 | 2251948.05 | Actual Total Cost | [13 empty] | 157825.83 | 516161.78 | 12401.07
|  |  | JDH3-02-008-L-02-Storm Network - ST |  | 2025-12-28 | 2026-02-26 | 12-Aug-25 A | 2026-01-19 | 686388.69 | 686388.68 | 1976764.61 | Planned Total Cost | [15 empty] | 306720.99 |  | 1264652.32 | 405391.31
|  |  | JDH3-02-008-L-02-Storm Network - ST |  | 2025-12-28 | 2026-02-26 | 12-Aug-25 A | 2026-01-19 | 686388.69 | 686388.68 | 1976764.61 | Remaining Total Cost | [15 empty] | 325541.52 |  | 826456.28 | 138378.12
|  |  | JDH3-02-008-L-02-Storm Network - ST |  | 2025-12-28 | 2026-02-26 | 12-Aug-25 A | 2026-01-19 | 686388.69 | 686388.68 | 1976764.61 | Actual Total Cost | [13 empty] | 157825.83 | 516161.78 | 12401.07
|  |  | JDH3-02-008-L-02-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-12-28 | 2026-02-26 | 2025-12-10 | 2026-01-19 | 0 | 0 | 259641.26 | Planned Total Cost | [17 empty] | 233677.13 | 25964.13
|  |  | JDH3-02-008-L-02-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-12-28 | 2026-02-26 | 2025-12-10 | 2026-01-19 | 0 | 0 | 259641.26 | Remaining Total Cost | [17 empty] | 233677.13 | 25964.13
|  |  | JDH3-02-008-L-02-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-12-28 | 2026-02-26 | 2025-12-10 | 2026-01-19 | 0 | 0 | 259641.26 | Actual Total Cost
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-12-31 | 2026-02-21 | 2025-12-14 | 2026-01-15 | 0 | 0 | 43746.73 | Planned Total Cost | [17 empty] | 39372.06 | 4374.67
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-12-31 | 2026-02-21 | 2025-12-14 | 2026-01-15 | 0 | 0 | 43746.73 | Remaining Total Cost | [17 empty] | 39372.06 | 4374.67
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-12-31 | 2026-02-21 | 2025-12-14 | 2026-01-15 | 0 | 0 | 43746.73 | Actual Total Cost
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-01-03 | 2026-02-24 | 03-Sep-25 A | 2026-01-13 | 1929-09-10 06:14 | 1929-09-10 06:14 | 172903.85 | Planned Total Cost | [17 empty] | 155613.46 | 17290.38
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-01-03 | 2026-02-24 | 03-Sep-25 A | 2026-01-13 | 1929-09-10 06:14 | 1929-09-10 06:14 | 172903.85 | Remaining Total Cost | [17 empty] | 145972.34 | 16085.24
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-01-03 | 2026-02-24 | 03-Sep-25 A | 2026-01-13 | 1929-09-10 06:14 | 1929-09-10 06:14 | 172903.85 | Actual Total Cost | [14 empty] | 10265.24 | 581.02
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2026-01-06 | 2026-02-21 | 03-Sep-25 A | 2026-01-15 | 1920-02-13 12:43 | 1920-02-13 12:58 | 67473.33 | Planned Total Cost | [17 empty] | 60726 | 6747.33
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2026-01-06 | 2026-02-21 | 03-Sep-25 A | 2026-01-15 | 1920-02-13 12:43 | 1920-02-13 12:58 | 67473.33 | Remaining Total Cost | [17 empty] | 53376.46 | 6747.33
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2026-01-06 | 2026-02-21 | 03-Sep-25 A | 2026-01-15 | 1920-02-13 12:43 | 1920-02-13 12:58 | 67473.33 | Actual Total Cost | [14 empty] | 7050.45 | 299.09
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-01-08 | 2026-02-21 | 03-Sep-25 A | 2026-01-13 | 2006-01-31 11:17 | 2006-01-31 11:17 | 88497.14 | Planned Total Cost | [17 empty] | 79647.42 | 8849.71
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-01-08 | 2026-02-21 | 03-Sep-25 A | 2026-01-13 | 2006-01-31 11:17 | 2006-01-31 11:17 | 88497.14 | Remaining Total Cost | [17 empty] | 45204.34 | 4544.32
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-01-08 | 2026-02-21 | 03-Sep-25 A | 2026-01-13 | 2006-01-31 11:17 | 2006-01-31 11:17 | 88497.14 | Actual Total Cost | [14 empty] | 36810.89 | 1937.58
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2026-01-11 | 2026-02-21 | 03-Sep-25 A | 2025-12-16 | 2038-06-04 03:22 | 2038-06-04 03:22 | 56177.93 | Planned Total Cost | [17 empty] | 50560.14 | 5617.79
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2026-01-11 | 2026-02-21 | 03-Sep-25 A | 2025-12-16 | 2038-06-04 03:22 | 2038-06-04 03:22 | 56177.93 | Remaining Total Cost | [17 empty] | 5617.79
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2026-01-11 | 2026-02-21 | 03-Sep-25 A | 2025-12-16 | 2038-06-04 03:22 | 2038-06-04 03:22 | 56177.93 | Actual Total Cost | [14 empty] | 50560.14
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2026-01-13 | 2026-02-21 | 03-Sep-25 A | 2025-12-18 | 2189-12-22 20:10 | 2189-12-22 19:55 | 117682.04 | Planned Total Cost | [17 empty] | 105913.84 | 11768.2
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2026-01-13 | 2026-02-21 | 03-Sep-25 A | 2025-12-18 | 2189-12-22 20:10 | 2189-12-22 19:55 | 117682.04 | Remaining Total Cost | [17 empty] | 11768.2
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2026-01-13 | 2026-02-21 | 03-Sep-25 A | 2025-12-18 | 2189-12-22 20:10 | 2189-12-22 19:55 | 117682.04 | Actual Total Cost | [14 empty] | 105913.83
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2026-01-15 | 2026-02-22 | 15-Aug-25 A | 2026-01-13 | 2333-01-17 21:50 | 2333-01-17 21:50 | 262813.27 | Planned Total Cost | [17 empty] | 170828.62 | 91984.64
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2026-01-15 | 2026-02-22 | 15-Aug-25 A | 2026-01-13 | 2333-01-17 21:50 | 2333-01-17 21:50 | 262813.27 | Remaining Total Cost | [17 empty] | 95937.35 | 8707.01
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2026-01-15 | 2026-02-22 | 15-Aug-25 A | 2026-01-13 | 2333-01-17 21:50 | 2333-01-17 21:50 | 262813.27 | Actual Total Cost | [13 empty] | 14857.81 | 136433.92 | 6877.18
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-01-18 | 2026-02-21 | 12-Aug-25 A | 23-Sep-25 A | 2389-04-15 00:43 | 2389-04-15 00:29 | 178710.03 | Planned Total Cost | [17 empty] | 17871 | 160839.02
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-01-18 | 2026-02-21 | 12-Aug-25 A | 23-Sep-25 A | 2389-04-15 00:43 | 2389-04-15 00:29 | 178710.03 | Remaining Total Cost
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-01-18 | 2026-02-21 | 12-Aug-25 A | 23-Sep-25 A | 2389-04-15 00:43 | 2389-04-15 00:29 | 178710.03 | Actual Total Cost | [13 empty] | 142968.02 | 35742
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2026-01-20 | 2026-02-21 | 20-Sep-25 A | 2026-01-15 | 1978-09-06 19:41 | 1978-09-06 19:41 | 31933.13 | Planned Total Cost | [17 empty] | 28739.82 | 3193.31
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2026-01-20 | 2026-02-21 | 20-Sep-25 A | 2026-01-15 | 1978-09-06 19:41 | 1978-09-06 19:41 | 31933.13 | Remaining Total Cost | [18 empty] | 3193.31
|  |  | JDH3-02-008-L-02-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2026-01-20 | 2026-02-21 | 20-Sep-25 A | 2026-01-15 | 1978-09-06 19:41 | 1978-09-06 19:41 | 31933.13 | Actual Total Cost | [14 empty] | 28739.82
|  |  | JDH3-02-008-L-02-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2026-01-22 | 2026-02-04 | 16-Sep-25 A | 2025-12-18 | 1919-04-10 16:05 | 1919-04-10 16:05 | 114715.67 | Planned Total Cost | [17 empty] | 114715.67
|  |  | JDH3-02-008-L-02-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2026-01-22 | 2026-02-04 | 16-Sep-25 A | 2025-12-18 | 1919-04-10 16:05 | 1919-04-10 16:05 | 114715.67 | Remaining Total Cost | [17 empty] | 107675
|  |  | JDH3-02-008-L-02-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2026-01-22 | 2026-02-04 | 16-Sep-25 A | 2025-12-18 | 1919-04-10 16:05 | 1919-04-10 16:05 | 114715.67 | Actual Total Cost | [14 empty] | 6501.69 | 538.98
|  |  | JDH3-02-008-L-02-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-01-25 | 2026-02-04 | 16-Sep-25 A | 2025-12-17 | 1975-11-19 12:29 | 1975-11-19 12:29 | 41062.99 | Planned Total Cost | [17 empty] | 41062.99
|  |  | JDH3-02-008-L-02-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-01-25 | 2026-02-04 | 16-Sep-25 A | 2025-12-17 | 1975-11-19 12:29 | 1975-11-19 12:29 | 41062.99 | Remaining Total Cost | [17 empty] | 13345.48
|  |  | JDH3-02-008-L-02-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-01-25 | 2026-02-04 | 16-Sep-25 A | 2025-12-17 | 1975-11-19 12:29 | 1975-11-19 12:29 | 41062.99 | Actual Total Cost | [14 empty] | 27118.69 | 598.84
|  |  | JDH3-02-008-L-02-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2026-01-27 | 2026-02-07 | 2025-12-11 | 2025-12-23 | 0 | 0 | 18250.22 | Planned Total Cost | [17 empty] | 18250.22
|  |  | JDH3-02-008-L-02-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2026-01-27 | 2026-02-07 | 2025-12-11 | 2025-12-23 | 0 | 0 | 18250.22 | Remaining Total Cost | [17 empty] | 18250.22
|  |  | JDH3-02-008-L-02-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2026-01-27 | 2026-02-07 | 2025-12-11 | 2025-12-23 | 0 | 0 | 18250.22 | Actual Total Cost
|  |  | JDH3-02-008-L-02-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-01-29 | 2026-02-09 | 16-Sep-25 A | 2025-10-07 | 2098-09-30 12:00 | 2098-09-30 12:00 | 107545.92 | Planned Total Cost | [15 empty] | 16131.89 |  | 91414.03
|  |  | JDH3-02-008-L-02-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-01-29 | 2026-02-09 | 16-Sep-25 A | 2025-10-07 | 2098-09-30 12:00 | 2098-09-30 12:00 | 107545.92 | Remaining Total Cost | [15 empty] | 34952.42
|  |  | JDH3-02-008-L-02-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-01-29 | 2026-02-09 | 16-Sep-25 A | 2025-10-07 | 2098-09-30 12:00 | 2098-09-30 12:00 | 107545.92 | Actual Total Cost | [14 empty] | 71025.12 | 1568.38
|  |  | JDH3-02-008-L-02-(ST)- Single Catchbasine Works |  | 2026-02-01 | 2026-02-16 | 2025-10-02 | 2025-10-18 | 0 | 0 | 86036.79 | Planned Total Cost | [15 empty] | 86036.79
|  |  | JDH3-02-008-L-02-(ST)- Single Catchbasine Works |  | 2026-02-01 | 2026-02-16 | 2025-10-02 | 2025-10-18 | 0 | 0 | 86036.79 | Remaining Total Cost | [15 empty] | 86036.79
|  |  | JDH3-02-008-L-02-(ST)- Single Catchbasine Works |  | 2026-02-01 | 2026-02-16 | 2025-10-02 | 2025-10-18 | 0 | 0 | 86036.79 | Actual Total Cost
|  |  | JDH3-02-008-L-02-(ST)- Double Catchbasine Works |  | 2026-02-04 | 2026-02-15 | 2025-10-06 | 2025-10-16 | 0 | 0 | 204552.31 | Planned Total Cost | [15 empty] | 204552.31
|  |  | JDH3-02-008-L-02-(ST)- Double Catchbasine Works |  | 2026-02-04 | 2026-02-15 | 2025-10-06 | 2025-10-16 | 0 | 0 | 204552.31 | Remaining Total Cost | [15 empty] | 204552.31
|  |  | JDH3-02-008-L-02-(ST)- Double Catchbasine Works |  | 2026-02-04 | 2026-02-15 | 2025-10-06 | 2025-10-16 | 0 | 0 | 204552.31 | Actual Total Cost
|  |  | JDH3-02-008-L-02-(ST)-PIPES ENCASEMENT |  | 2026-01-27 | 2026-02-18 | 2025-12-22 | 2026-01-13 | 0 | 0 | 125022 | Planned Total Cost | [17 empty] | 56259.9 | 68762.1
|  |  | JDH3-02-008-L-02-(ST)-PIPES ENCASEMENT |  | 2026-01-27 | 2026-02-18 | 2025-12-22 | 2026-01-13 | 0 | 0 | 125022 | Remaining Total Cost | [17 empty] | 56259.9 | 68762.1
|  |  | JDH3-02-008-L-02-(ST)-PIPES ENCASEMENT |  | 2026-01-27 | 2026-02-18 | 2025-12-22 | 2026-01-13 | 0 | 0 | 125022 | Actual Total Cost
|  |  | JDH3-02-008-L-02-TSE Network - TSE |  | 2026-02-28 | 2026-04-06 | 2026-01-20 | 2026-02-26 | 0 | 0 | 226997.21 | Planned Total Cost | [18 empty] | 57977.04 | 169020.17
|  |  | JDH3-02-008-L-02-TSE Network - TSE |  | 2026-02-28 | 2026-04-06 | 2026-01-20 | 2026-02-26 | 0 | 0 | 226997.21 | Remaining Total Cost | [18 empty] | 57977.04 | 169020.17
|  |  | JDH3-02-008-L-02-TSE Network - TSE |  | 2026-02-28 | 2026-04-06 | 2026-01-20 | 2026-02-26 | 0 | 0 | 226997.21 | Actual Total Cost
|  |  | JDH3-02-008-L-02-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-02-28 | 2026-03-30 | 2026-01-20 | 2026-02-19 | 0 | 0 | 16796.36 | Planned Total Cost | [18 empty] | 15116.72 | 1679.64
|  |  | JDH3-02-008-L-02-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-02-28 | 2026-03-30 | 2026-01-20 | 2026-02-19 | 0 | 0 | 16796.36 | Remaining Total Cost | [18 empty] | 15116.72 | 1679.64
|  |  | JDH3-02-008-L-02-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-02-28 | 2026-03-30 | 2026-01-20 | 2026-02-19 | 0 | 0 | 16796.36 | Actual Total Cost
|  |  | JDH3-02-008-L-02-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-03-02 | 2026-04-06 | 2026-01-22 | 2026-02-26 | 0 | 0 | 182567.39 | Planned Total Cost | [18 empty] | 41990.5 | 140576.89
|  |  | JDH3-02-008-L-02-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-03-02 | 2026-04-06 | 2026-01-22 | 2026-02-26 | 0 | 0 | 182567.39 | Remaining Total Cost | [18 empty] | 41990.5 | 140576.89
|  |  | JDH3-02-008-L-02-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-03-02 | 2026-04-06 | 2026-01-22 | 2026-02-26 | 0 | 0 | 182567.39 | Actual Total Cost
|  |  | JDH3-02-008-L-02-(TSE)-Supply and install gate valves-100 mm |  | 2026-03-24 | 2026-03-28 | 2026-02-14 | 2026-02-17 | 0 | 0 | 3879.48 | Planned Total Cost | [19 empty] | 3879.48
|  |  | JDH3-02-008-L-02-(TSE)-Supply and install gate valves-100 mm |  | 2026-03-24 | 2026-03-28 | 2026-02-14 | 2026-02-17 | 0 | 0 | 3879.48 | Remaining Total Cost | [19 empty] | 3879.48
|  |  | JDH3-02-008-L-02-(TSE)-Supply and install gate valves-100 mm |  | 2026-03-24 | 2026-03-28 | 2026-02-14 | 2026-02-17 | 0 | 0 | 3879.48 | Actual Total Cost
|  |  | JDH3-02-008-L-02-(TSE)-Supply and install gate valves-250 mm |  | 2026-03-24 | 2026-03-28 | 2026-02-14 | 2026-02-17 | 0 | 0 | 12830.57 | Planned Total Cost | [19 empty] | 12830.57
|  |  | JDH3-02-008-L-02-(TSE)-Supply and install gate valves-250 mm |  | 2026-03-24 | 2026-03-28 | 2026-02-14 | 2026-02-17 | 0 | 0 | 12830.57 | Remaining Total Cost | [19 empty] | 12830.57
|  |  | JDH3-02-008-L-02-(TSE)-Supply and install gate valves-250 mm |  | 2026-03-24 | 2026-03-28 | 2026-02-14 | 2026-02-17 | 0 | 0 | 12830.57 | Actual Total Cost
|  |  | JDH3-02-008-L-02-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-03-24 | 2026-03-28 | 2026-02-14 | 2026-02-17 | 0 | 0 | 7444.14 | Planned Total Cost | [19 empty] | 7444.14
|  |  | JDH3-02-008-L-02-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-03-24 | 2026-03-28 | 2026-02-14 | 2026-02-17 | 0 | 0 | 7444.14 | Remaining Total Cost | [19 empty] | 7444.14
|  |  | JDH3-02-008-L-02-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-03-24 | 2026-03-28 | 2026-02-14 | 2026-02-17 | 0 | 0 | 7444.14 | Actual Total Cost
|  |  | JDH3-02-008-L-02-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-03-08 | 2026-03-30 | 2026-01-28 | 2026-02-19 | 0 | 0 | 3479.28 | Planned Total Cost | [18 empty] | 869.82 | 2609.46
|  |  | JDH3-02-008-L-02-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-03-08 | 2026-03-30 | 2026-01-28 | 2026-02-19 | 0 | 0 | 3479.28 | Remaining Total Cost | [18 empty] | 869.82 | 2609.46
|  |  | JDH3-02-008-L-02-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-03-08 | 2026-03-30 | 2026-01-28 | 2026-02-19 | 0 | 0 | 3479.28 | Actual Total Cost
|  |  | JDH3-02-008-L-02-Potable Water Network - WT |  | 2026-04-07 | 2026-04-18 | 2026-02-28 | 2026-03-10 | 0 | 0 | 48186.23 | Planned Total Cost | [19 empty] | 284.42 | 47901.81
|  |  | JDH3-02-008-L-02-Potable Water Network - WT |  | 2026-04-07 | 2026-04-18 | 2026-02-28 | 2026-03-10 | 0 | 0 | 48186.23 | Remaining Total Cost | [19 empty] | 284.42 | 47901.81
|  |  | JDH3-02-008-L-02-Potable Water Network - WT |  | 2026-04-07 | 2026-04-18 | 2026-02-28 | 2026-03-10 | 0 | 0 | 48186.23 | Actual Total Cost
|  |  | JDH3-02-008-L-02-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-04-07 | 2026-04-18 | 2026-02-28 | 2026-03-10 | 0 | 0 | 2844.21 | Planned Total Cost | [19 empty] | 284.42 | 2559.79
|  |  | JDH3-02-008-L-02-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-04-07 | 2026-04-18 | 2026-02-28 | 2026-03-10 | 0 | 0 | 2844.21 | Remaining Total Cost | [19 empty] | 284.42 | 2559.79
|  |  | JDH3-02-008-L-02-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-04-07 | 2026-04-18 | 2026-02-28 | 2026-03-10 | 0 | 0 | 2844.21 | Actual Total Cost
|  |  | JDH3-02-008-L-02-(WT)- Supply and install 3-out fire hydrant |  | 2026-04-09 | 2026-04-15 | 2026-03-02 | 2026-03-08 | 0 | 0 | 45342.02 | Planned Total Cost | [20 empty] | 45342.02
|  |  | JDH3-02-008-L-02-(WT)- Supply and install 3-out fire hydrant |  | 2026-04-09 | 2026-04-15 | 2026-03-02 | 2026-03-08 | 0 | 0 | 45342.02 | Remaining Total Cost | [20 empty] | 45342.02
|  |  | JDH3-02-008-L-02-(WT)- Supply and install 3-out fire hydrant |  | 2026-04-09 | 2026-04-15 | 2026-03-02 | 2026-03-08 | 0 | 0 | 45342.02 | Actual Total Cost
|  |  | L-08 |  | 2026-01-27 | 2026-05-24 | 12-Nov-24 A | 2026-06-03 | 1668327.71 | 1668327.71 | 5501458.26 | Planned Total Cost | [19 empty] | 1441663.45 | 2450773.04 | 1363346.8 | 243963.55 | 1711.42
|  |  | L-08 |  | 2026-01-27 | 2026-05-24 | 12-Nov-24 A | 2026-06-03 | 1668327.71 | 1668327.71 | 5501458.26 | Remaining Total Cost | [19 empty] | 1375875.5 | 1556962.33 | 704848.31 | 193732.99 | 1711.42
|  |  | L-08 |  | 2026-01-27 | 2026-05-24 | 12-Nov-24 A | 2026-06-03 | 1668327.71 | 1668327.71 | 5501458.26 | Actual Total Cost | [5 empty] | 1313.32 | 2276.41 | 612.88 |  | 31.27 | 162.6 | 3200.34 | 5536.35 | 274844.87 | 1327522.19 | 52827.48
|  |  | JDH3-02-008-L-08-Storm Network - ST |  | 2026-02-04 | 2026-04-23 | 15-Dec-24 A | 2026-04-21 | 1668327.71 | 1668327.71 | 5267357.08 | Planned Total Cost | [19 empty] | 1441663.45 | 2450773.04 | 1324690.03 | 50230.56
|  |  | JDH3-02-008-L-08-Storm Network - ST |  | 2026-02-04 | 2026-04-23 | 15-Dec-24 A | 2026-04-21 | 1668327.71 | 1668327.71 | 5267357.08 | Remaining Total Cost | [19 empty] | 1375875.5 | 1556962.33 | 666191.54
|  |  | JDH3-02-008-L-08-Storm Network - ST |  | 2026-02-04 | 2026-04-23 | 15-Dec-24 A | 2026-04-21 | 1668327.71 | 1668327.71 | 5267357.08 | Actual Total Cost | [5 empty] | 1313.32 | 2276.41 | 612.88 |  | 31.27 | 162.6 | 3200.34 | 5536.35 | 274844.87 | 1327522.19 | 52827.48
|  |  | JDH3-02-008-L-08-(ST)-Box Culvert |  | 2026-02-04 | 2026-04-23 | 15-Dec-24 A | 2026-03-10 | 1668327.71 | 1668327.71 | 3609543.65 | Planned Total Cost | [19 empty] | 1392543.65 | 1508270.94 | 658498.49 | 50230.56
|  |  | JDH3-02-008-L-08-(ST)-Box Culvert |  | 2026-02-04 | 2026-04-23 | 15-Dec-24 A | 2026-03-10 | 1668327.71 | 1668327.71 | 3609543.65 | Remaining Total Cost | [19 empty] | 1326755.71 | 614460.23
|  |  | JDH3-02-008-L-08-(ST)-Box Culvert |  | 2026-02-04 | 2026-04-23 | 15-Dec-24 A | 2026-03-10 | 1668327.71 | 1668327.71 | 3609543.65 | Actual Total Cost | [5 empty] | 1313.32 | 2276.41 | 612.88 |  | 31.27 | 162.6 | 3200.34 | 5536.35 | 274844.87 | 1327522.19 | 52827.48
|  |  | JDH3-02-008-L-08-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2026-02-04 | 2026-02-24 | 15-Dec-24 A | 2026-03-10 | 1935-12-15 04:05 | 1935-12-15 04:05 | 104886.67 | Planned Total Cost | [19 empty] | 52033.8 | 52852.87
|  |  | JDH3-02-008-L-08-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2026-02-04 | 2026-02-24 | 15-Dec-24 A | 2026-03-10 | 1935-12-15 04:05 | 1935-12-15 04:05 | 104886.67 | Remaining Total Cost | [19 empty] | 38900.63 | 52852.87
|  |  | JDH3-02-008-L-08-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2026-02-04 | 2026-02-24 | 15-Dec-24 A | 2026-03-10 | 1935-12-15 04:05 | 1935-12-15 04:05 | 104886.67 | Actual Total Cost | [5 empty] | 1313.32 | 2276.41 | 612.88 |  | 31.27 | 162.6 | 3200.34 | 5536.35
|  |  | JDH3-02-008-L-08-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2026-02-09 | 2026-04-21 | 20-Aug-25 A | 2026-03-10 | 602625.76 | 602625.75 | 993129.08 | Planned Total Cost | [19 empty] | 273110.5 | 471736.31 | 248282.27
|  |  | JDH3-02-008-L-08-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2026-02-09 | 2026-04-21 | 20-Aug-25 A | 2026-03-10 | 602625.76 | 602625.75 | 993129.08 | Remaining Total Cost | [19 empty] | 47675.17 | 342828.16
|  |  | JDH3-02-008-L-08-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2026-02-09 | 2026-04-21 | 20-Aug-25 A | 2026-03-10 | 602625.76 | 602625.75 | 993129.08 | Actual Total Cost | [13 empty] | 112841.1 | 471644.48 | 18140.17
|  |  | JDH3-02-008-L-08-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2026-02-09 | 2026-04-23 | 20-Aug-25 A | 2026-03-10 | 1052568.79 | 1052568.79 | 2511527.9 | Planned Total Cost | [19 empty] | 1067399.36 | 983681.76 | 410216.22 | 50230.56
|  |  | JDH3-02-008-L-08-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2026-02-09 | 2026-04-23 | 20-Aug-25 A | 2026-03-10 | 1052568.79 | 1052568.79 | 2511527.9 | Remaining Total Cost | [19 empty] | 1240179.91 | 218779.2
|  |  | JDH3-02-008-L-08-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2026-02-09 | 2026-04-23 | 20-Aug-25 A | 2026-03-10 | 1052568.79 | 1052568.79 | 2511527.9 | Actual Total Cost | [13 empty] | 162003.77 | 855877.71 | 34687.31
|  |  | JDH3-02-008-L-08-(ST)-NetWork |  | 2026-02-16 | 2026-04-11 | 2026-02-25 | 2026-04-21 | 0 | 0 | 1657813.43 | Planned Total Cost | [19 empty] | 49119.79 | 942502.1 | 666191.54
|  |  | JDH3-02-008-L-08-(ST)-NetWork |  | 2026-02-16 | 2026-04-11 | 2026-02-25 | 2026-04-21 | 0 | 0 | 1657813.43 | Remaining Total Cost | [19 empty] | 49119.79 | 942502.1 | 666191.54
|  |  | JDH3-02-008-L-08-(ST)-NetWork |  | 2026-02-16 | 2026-04-11 | 2026-02-25 | 2026-04-21 | 0 | 0 | 1657813.43 | Actual Total Cost
|  |  | JDH3-02-008-L-08-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-02-16 | 2026-03-29 | 2026-02-25 | 2026-04-08 | 0 | 0 | 287063.72 | Planned Total Cost | [19 empty] | 49119.79 | 209237.55 | 28706.37
|  |  | JDH3-02-008-L-08-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-02-16 | 2026-03-29 | 2026-02-25 | 2026-04-08 | 0 | 0 | 287063.72 | Remaining Total Cost | [19 empty] | 49119.79 | 209237.55 | 28706.37
|  |  | JDH3-02-008-L-08-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-02-16 | 2026-03-29 | 2026-02-25 | 2026-04-08 | 0 | 0 | 287063.72 | Actual Total Cost
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2026-02-19 | 2026-03-25 | 2026-03-01 | 2026-04-05 | 0 | 0 | 43193.16 | Planned Total Cost | [20 empty] | 38873.84 | 4319.32
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2026-02-19 | 2026-03-25 | 2026-03-01 | 2026-04-05 | 0 | 0 | 43193.16 | Remaining Total Cost | [20 empty] | 38873.84 | 4319.32
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2026-02-19 | 2026-03-25 | 2026-03-01 | 2026-04-05 | 0 | 0 | 43193.16 | Actual Total Cost
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-02-22 | 2026-03-26 | 2026-03-03 | 2026-04-06 | 0 | 0 | 95775.25 | Planned Total Cost | [20 empty] | 86197.72 | 9577.52
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-02-22 | 2026-03-26 | 2026-03-03 | 2026-04-06 | 0 | 0 | 95775.25 | Remaining Total Cost | [20 empty] | 86197.72 | 9577.52
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-02-22 | 2026-03-26 | 2026-03-03 | 2026-04-06 | 0 | 0 | 95775.25 | Actual Total Cost
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2026-02-24 | 2026-03-25 | 2026-03-05 | 2026-04-05 | 0 | 0 | 40700.07 | Planned Total Cost | [20 empty] | 36630.07 | 4070.01
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2026-02-24 | 2026-03-25 | 2026-03-05 | 2026-04-05 | 0 | 0 | 40700.07 | Remaining Total Cost | [20 empty] | 36630.07 | 4070.01
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2026-02-24 | 2026-03-25 | 2026-03-05 | 2026-04-05 | 0 | 0 | 40700.07 | Actual Total Cost
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2026-02-26 | 2026-03-25 | 2026-03-08 | 2026-04-05 | 0 | 0 | 80640.93 | Planned Total Cost | [20 empty] | 72576.84 | 8064.09
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2026-02-26 | 2026-03-25 | 2026-03-08 | 2026-04-05 | 0 | 0 | 80640.93 | Remaining Total Cost | [20 empty] | 72576.84 | 8064.09
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2026-02-26 | 2026-03-25 | 2026-03-08 | 2026-04-05 | 0 | 0 | 80640.93 | Actual Total Cost
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2026-03-01 | 2026-03-25 | 2026-03-10 | 2026-04-05 | 0 | 0 | 49296.97 | Planned Total Cost | [20 empty] | 44367.27 | 4929.7
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2026-03-01 | 2026-03-25 | 2026-03-10 | 2026-04-05 | 0 | 0 | 49296.97 | Remaining Total Cost | [20 empty] | 44367.27 | 4929.7
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2026-03-01 | 2026-03-25 | 2026-03-10 | 2026-04-05 | 0 | 0 | 49296.97 | Actual Total Cost
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2026-03-03 | 2026-03-25 | 2026-03-12 | 2026-04-05 | 0 | 0 | 53652.24 | Planned Total Cost | [20 empty] | 48287.02 | 5365.22
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2026-03-03 | 2026-03-25 | 2026-03-12 | 2026-04-05 | 0 | 0 | 53652.24 | Remaining Total Cost | [20 empty] | 48287.02 | 5365.22
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2026-03-03 | 2026-03-25 | 2026-03-12 | 2026-04-05 | 0 | 0 | 53652.24 | Actual Total Cost
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2026-03-05 | 2026-03-26 | 2026-03-15 | 2026-04-06 | 0 | 0 | 165155.97 | Planned Total Cost | [20 empty] | 148640.37 | 16515.6
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2026-03-05 | 2026-03-26 | 2026-03-15 | 2026-04-06 | 0 | 0 | 165155.97 | Remaining Total Cost | [20 empty] | 148640.37 | 16515.6
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2026-03-05 | 2026-03-26 | 2026-03-15 | 2026-04-06 | 0 | 0 | 165155.97 | Actual Total Cost
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 2.51 to 3.50 m |  | 2026-03-08 | 2026-03-25 | 2026-03-17 | 2026-04-05 | 0 | 0 | 32209.08 | Planned Total Cost | [20 empty] | 28988.17 | 3220.91
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 2.51 to 3.50 m |  | 2026-03-08 | 2026-03-25 | 2026-03-17 | 2026-04-05 | 0 | 0 | 32209.08 | Remaining Total Cost | [20 empty] | 28988.17 | 3220.91
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 2.51 to 3.50 m |  | 2026-03-08 | 2026-03-25 | 2026-03-17 | 2026-04-05 | 0 | 0 | 32209.08 | Actual Total Cost
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2026-03-10 | 2026-03-25 | 2026-03-19 | 2026-04-05 | 0 | 0 | 36663.06 | Planned Total Cost | [20 empty] | 32996.76 | 3666.31
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2026-03-10 | 2026-03-25 | 2026-03-19 | 2026-04-05 | 0 | 0 | 36663.06 | Remaining Total Cost | [20 empty] | 32996.76 | 3666.31
|  |  | JDH3-02-008-L-08-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2026-03-10 | 2026-03-25 | 2026-03-19 | 2026-04-05 | 0 | 0 | 36663.06 | Actual Total Cost
|  |  | JDH3-02-008-L-08-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2026-03-12 | 2026-03-23 | 2026-03-22 | 2026-04-02 | 0 | 0 | 62572.18 | Planned Total Cost | [20 empty] | 58087.84 | 4484.34
|  |  | JDH3-02-008-L-08-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2026-03-12 | 2026-03-23 | 2026-03-22 | 2026-04-02 | 0 | 0 | 62572.18 | Remaining Total Cost | [20 empty] | 58087.84 | 4484.34
|  |  | JDH3-02-008-L-08-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2026-03-12 | 2026-03-23 | 2026-03-22 | 2026-04-02 | 0 | 0 | 62572.18 | Actual Total Cost
|  |  | JDH3-02-008-L-08-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-03-15 | 2026-03-25 | 2026-03-24 | 2026-04-05 | 0 | 0 | 13687.66 | Planned Total Cost | [20 empty] | 11828.42 | 1859.24
|  |  | JDH3-02-008-L-08-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-03-15 | 2026-03-25 | 2026-03-24 | 2026-04-05 | 0 | 0 | 13687.66 | Remaining Total Cost | [20 empty] | 11828.42 | 1859.24
|  |  | JDH3-02-008-L-08-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-03-15 | 2026-03-25 | 2026-03-24 | 2026-04-05 | 0 | 0 | 13687.66 | Actual Total Cost
|  |  | JDH3-02-008-L-08-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-03-17 | 2026-04-07 | 2026-03-26 | 2026-04-18 | 0 | 0 | 321986 | Planned Total Cost | [20 empty] | 105718.74 | 216267.26
|  |  | JDH3-02-008-L-08-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-03-17 | 2026-04-07 | 2026-03-26 | 2026-04-18 | 0 | 0 | 321986 | Remaining Total Cost | [20 empty] | 105718.74 | 216267.26
|  |  | JDH3-02-008-L-08-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-03-17 | 2026-04-07 | 2026-03-26 | 2026-04-18 | 0 | 0 | 321986 | Actual Total Cost
|  |  | JDH3-02-008-L-08-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-03-21 | 2026-03-31 | 2026-03-30 | 2026-04-11 | 0 | 0 | 21509.18 | Planned Total Cost | [20 empty] | 4212.22 | 17296.97
|  |  | JDH3-02-008-L-08-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-03-21 | 2026-03-31 | 2026-03-30 | 2026-04-11 | 0 | 0 | 21509.18 | Remaining Total Cost | [20 empty] | 4212.22 | 17296.97
|  |  | JDH3-02-008-L-08-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-03-21 | 2026-03-31 | 2026-03-30 | 2026-04-11 | 0 | 0 | 21509.18 | Actual Total Cost
|  |  | JDH3-02-008-L-08-(ST)- Single Catchbasine Works |  | 2026-03-23 | 2026-04-09 | 2026-04-01 | 2026-04-20 | 0 | 0 | 105590.61 | Planned Total Cost | [21 empty] | 105590.61
|  |  | JDH3-02-008-L-08-(ST)- Single Catchbasine Works |  | 2026-03-23 | 2026-04-09 | 2026-04-01 | 2026-04-20 | 0 | 0 | 105590.61 | Remaining Total Cost | [21 empty] | 105590.61
|  |  | JDH3-02-008-L-08-(ST)- Single Catchbasine Works |  | 2026-03-23 | 2026-04-09 | 2026-04-01 | 2026-04-20 | 0 | 0 | 105590.61 | Actual Total Cost
|  |  | JDH3-02-008-L-08-(ST)- Double Catchbasine Works |  | 2026-03-26 | 2026-04-11 | 2026-04-05 | 2026-04-21 | 0 | 0 | 227280.35 | Planned Total Cost | [21 empty] | 227280.35
|  |  | JDH3-02-008-L-08-(ST)- Double Catchbasine Works |  | 2026-03-26 | 2026-04-11 | 2026-04-05 | 2026-04-21 | 0 | 0 | 227280.35 | Remaining Total Cost | [21 empty] | 227280.35
|  |  | JDH3-02-008-L-08-(ST)- Double Catchbasine Works |  | 2026-03-26 | 2026-04-11 | 2026-04-05 | 2026-04-21 | 0 | 0 | 227280.35 | Actual Total Cost
|  |  | JDH3-02-008-L-08-(ST)-PIPES ENCASEMENT |  | 2026-03-17 | 2026-03-23 | 2026-03-26 | 2026-04-02 | 0 | 0 | 20837 | Planned Total Cost | [20 empty] | 15859.27 | 4977.73
|  |  | JDH3-02-008-L-08-(ST)-PIPES ENCASEMENT |  | 2026-03-17 | 2026-03-23 | 2026-03-26 | 2026-04-02 | 0 | 0 | 20837 | Remaining Total Cost | [20 empty] | 15859.27 | 4977.73
|  |  | JDH3-02-008-L-08-(ST)-PIPES ENCASEMENT |  | 2026-03-17 | 2026-03-23 | 2026-03-26 | 2026-04-02 | 0 | 0 | 20837 | Actual Total Cost
|  |  | JDH3-02-008-L-08-TSE Network - TSE |  | 2026-04-12 | 2026-05-12 | 2026-04-21 | 2026-05-23 | 0 | 0 | 175313.81 | Planned Total Cost | [21 empty] | 38656.77 | 136657.04
|  |  | JDH3-02-008-L-08-TSE Network - TSE |  | 2026-04-12 | 2026-05-12 | 2026-04-21 | 2026-05-23 | 0 | 0 | 175313.81 | Remaining Total Cost | [21 empty] | 38656.77 | 136657.04
|  |  | JDH3-02-008-L-08-TSE Network - TSE |  | 2026-04-12 | 2026-05-12 | 2026-04-21 | 2026-05-23 | 0 | 0 | 175313.81 | Actual Total Cost
|  |  | JDH3-02-008-L-08-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-04-12 | 2026-05-07 | 2026-04-21 | 2026-05-18 | 0 | 0 | 4013.58 | Planned Total Cost | [21 empty] | 3612.22 | 401.36
|  |  | JDH3-02-008-L-08-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-04-12 | 2026-05-07 | 2026-04-21 | 2026-05-18 | 0 | 0 | 4013.58 | Remaining Total Cost | [21 empty] | 3612.22 | 401.36
|  |  | JDH3-02-008-L-08-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-04-12 | 2026-05-07 | 2026-04-21 | 2026-05-18 | 0 | 0 | 4013.58 | Actual Total Cost
|  |  | JDH3-02-008-L-08-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-04-14 | 2026-05-12 | 2026-04-23 | 2026-05-23 | 0 | 0 | 137371.76 | Planned Total Cost | [21 empty] | 31881.7 | 105490.06
|  |  | JDH3-02-008-L-08-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-04-14 | 2026-05-12 | 2026-04-23 | 2026-05-23 | 0 | 0 | 137371.76 | Remaining Total Cost | [21 empty] | 31881.7 | 105490.06
|  |  | JDH3-02-008-L-08-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-04-14 | 2026-05-12 | 2026-04-23 | 2026-05-23 | 0 | 0 | 137371.76 | Actual Total Cost
|  |  | JDH3-02-008-L-08-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-02 | 2026-05-05 | 2026-05-11 | 2026-05-16 | 0 | 0 | 2586.32 | Planned Total Cost | [22 empty] | 2586.32
|  |  | JDH3-02-008-L-08-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-02 | 2026-05-05 | 2026-05-11 | 2026-05-16 | 0 | 0 | 2586.32 | Remaining Total Cost | [22 empty] | 2586.32
|  |  | JDH3-02-008-L-08-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-02 | 2026-05-05 | 2026-05-11 | 2026-05-16 | 0 | 0 | 2586.32 | Actual Total Cost
|  |  | JDH3-02-008-L-08-(TSE)-Supply and install gate valves-250 mm |  | 2026-05-02 | 2026-05-05 | 2026-05-11 | 2026-05-16 | 0 | 0 | 7698.34 | Planned Total Cost | [22 empty] | 7698.34
|  |  | JDH3-02-008-L-08-(TSE)-Supply and install gate valves-250 mm |  | 2026-05-02 | 2026-05-05 | 2026-05-11 | 2026-05-16 | 0 | 0 | 7698.34 | Remaining Total Cost | [22 empty] | 7698.34
|  |  | JDH3-02-008-L-08-(TSE)-Supply and install gate valves-250 mm |  | 2026-05-02 | 2026-05-05 | 2026-05-11 | 2026-05-16 | 0 | 0 | 7698.34 | Actual Total Cost
|  |  | JDH3-02-008-L-08-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-05-02 | 2026-05-05 | 2026-05-11 | 2026-05-16 | 0 | 0 | 9791.9 | Planned Total Cost | [22 empty] | 9791.9
|  |  | JDH3-02-008-L-08-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-05-02 | 2026-05-05 | 2026-05-11 | 2026-05-16 | 0 | 0 | 9791.9 | Remaining Total Cost | [22 empty] | 9791.9
|  |  | JDH3-02-008-L-08-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-05-02 | 2026-05-05 | 2026-05-11 | 2026-05-16 | 0 | 0 | 9791.9 | Actual Total Cost
|  |  | JDH3-02-008-L-08-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-04-19 | 2026-05-07 | 2026-04-28 | 2026-05-18 | 0 | 0 | 13851.92 | Planned Total Cost | [21 empty] | 3162.85 | 10689.06
|  |  | JDH3-02-008-L-08-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-04-19 | 2026-05-07 | 2026-04-28 | 2026-05-18 | 0 | 0 | 13851.92 | Remaining Total Cost | [21 empty] | 3162.85 | 10689.06
|  |  | JDH3-02-008-L-08-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-04-19 | 2026-05-07 | 2026-04-28 | 2026-05-18 | 0 | 0 | 13851.92 | Actual Total Cost
|  |  | JDH3-02-008-L-08-Potable Water Network - WT |  | 2026-05-13 | 2026-05-24 | 2026-05-23 | 2026-06-03 | 0 | 0 | 58787.37 | Planned Total Cost | [22 empty] | 57075.95 | 1711.42
|  |  | JDH3-02-008-L-08-Potable Water Network - WT |  | 2026-05-13 | 2026-05-24 | 2026-05-23 | 2026-06-03 | 0 | 0 | 58787.37 | Remaining Total Cost | [22 empty] | 57075.95 | 1711.42
|  |  | JDH3-02-008-L-08-Potable Water Network - WT |  | 2026-05-13 | 2026-05-24 | 2026-05-23 | 2026-06-03 | 0 | 0 | 58787.37 | Actual Total Cost
|  |  | JDH3-02-008-L-08-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-05-13 | 2026-05-24 | 2026-05-23 | 2026-06-03 | 0 | 0 | 4376.95 | Planned Total Cost | [22 empty] | 3844.42 | 532.53
|  |  | JDH3-02-008-L-08-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-05-13 | 2026-05-24 | 2026-05-23 | 2026-06-03 | 0 | 0 | 4376.95 | Remaining Total Cost | [22 empty] | 3844.42 | 532.53
|  |  | JDH3-02-008-L-08-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-05-13 | 2026-05-24 | 2026-05-23 | 2026-06-03 | 0 | 0 | 4376.95 | Actual Total Cost
|  |  | JDH3-02-008-L-08-(WT)- Supply and install 3-out fire hydrant |  | 2026-05-16 | 2026-05-21 | 2026-05-25 | 2026-06-01 | 0 | 0 | 54410.42 | Planned Total Cost | [22 empty] | 53231.53 | 1178.89
|  |  | JDH3-02-008-L-08-(WT)- Supply and install 3-out fire hydrant |  | 2026-05-16 | 2026-05-21 | 2026-05-25 | 2026-06-01 | 0 | 0 | 54410.42 | Remaining Total Cost | [22 empty] | 53231.53 | 1178.89
|  |  | JDH3-02-008-L-08-(WT)- Supply and install 3-out fire hydrant |  | 2026-05-16 | 2026-05-21 | 2026-05-25 | 2026-06-01 | 0 | 0 | 54410.42 | Actual Total Cost
|  |  | L-09 |  | 2025-12-24 | 2026-04-25 | 13-Jan-25 A | 2026-05-04 | 739634.13 | 739634.18 | 1901769.2 | Planned Total Cost | [14 empty] | 52041.86 | 534012.98 |  |  | 464093.55 | 120508.21 | 317929.81 | 412193.19 | 989.59
|  |  | L-09 |  | 2025-12-24 | 2026-04-25 | 13-Jan-25 A | 2026-05-04 | 739634.13 | 739634.18 | 1901769.2 | Remaining Total Cost | [15 empty] | 617537.55 |  |  |  | 50985.59 | 323953.5 | 168668.83 | 989.59
|  |  | L-09 |  | 2025-12-24 | 2026-04-25 | 13-Jan-25 A | 2026-05-04 | 739634.13 | 739634.18 | 1901769.2 | Actual Total Cost | [7 empty] | 6067.23 | 173399.27 | 187469.58 | 67701.25 | 19419.96 | 25511.98 | 72639.58 | 183904.12 | 3521.23
|  |  | JDH3-02-008-L-09-Storm Network - ST |  | 2026-01-01 | 2026-03-14 | 25-Feb-25 A | 2026-03-22 | 739634.13 | 739634.18 | 1702513.47 | Planned Total Cost | [14 empty] | 52041.86 | 534012.98 |  |  | 464093.55 | 120508.21 | 288332.51 | 243524.36
|  |  | JDH3-02-008-L-09-Storm Network - ST |  | 2026-01-01 | 2026-03-14 | 25-Feb-25 A | 2026-03-22 | 739634.13 | 739634.18 | 1702513.47 | Remaining Total Cost | [15 empty] | 617537.55 |  |  |  | 50985.59 | 294356.19
|  |  | JDH3-02-008-L-09-Storm Network - ST |  | 2026-01-01 | 2026-03-14 | 25-Feb-25 A | 2026-03-22 | 739634.13 | 739634.18 | 1702513.47 | Actual Total Cost | [7 empty] | 6067.23 | 173399.27 | 187469.58 | 67701.25 | 19419.96 | 25511.98 | 72639.58 | 183904.12 | 3521.23
|  |  | JDH3-02-008-L-09-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-02-09 | 2026-03-12 | 2026-02-24 | 2026-03-22 | 0 | 0 | 241706.38 | Planned Total Cost | [19 empty] | 50758.34 | 190948.04
|  |  | JDH3-02-008-L-09-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-02-09 | 2026-03-12 | 2026-02-24 | 2026-03-22 | 0 | 0 | 241706.38 | Remaining Total Cost | [19 empty] | 50758.34 | 190948.04
|  |  | JDH3-02-008-L-09-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-02-09 | 2026-03-12 | 2026-02-24 | 2026-03-22 | 0 | 0 | 241706.38 | Actual Total Cost
|  |  | JDH3-02-008-L-09-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2026-02-12 | 2026-03-09 | 2026-02-28 | 2026-03-18 | 0 | 0 | 3787.6 | Planned Total Cost | [19 empty] | 227.26 | 3560.34
|  |  | JDH3-02-008-L-09-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2026-02-12 | 2026-03-09 | 2026-02-28 | 2026-03-18 | 0 | 0 | 3787.6 | Remaining Total Cost | [19 empty] | 227.26 | 3560.34
|  |  | JDH3-02-008-L-09-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2026-02-12 | 2026-03-09 | 2026-02-28 | 2026-03-18 | 0 | 0 | 3787.6 | Actual Total Cost
|  |  | JDH3-02-008-L-09-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-02-15 | 2026-03-09 | 2026-03-02 | 2026-03-18 | 0 | 0 | 42443.8 | Planned Total Cost | [20 empty] | 42443.8
|  |  | JDH3-02-008-L-09-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-02-15 | 2026-03-09 | 2026-03-02 | 2026-03-18 | 0 | 0 | 42443.8 | Remaining Total Cost | [20 empty] | 42443.8
|  |  | JDH3-02-008-L-09-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-02-15 | 2026-03-09 | 2026-03-02 | 2026-03-18 | 0 | 0 | 42443.8 | Actual Total Cost
|  |  | JDH3-02-008-L-09-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2026-02-17 | 2026-03-09 | 06-Aug-25 A | 2026-03-18 | 1984-03-24 01:26 | 1984-03-24 01:41 | 38456.33 | Planned Total Cost | [15 empty] | 3845.63 |  |  |  | 30765.06 | 3845.63
|  |  | JDH3-02-008-L-09-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2026-02-17 | 2026-03-09 | 06-Aug-25 A | 2026-03-18 | 1984-03-24 01:26 | 1984-03-24 01:41 | 38456.33 | Remaining Total Cost | [15 empty] | 3845.63 |  |  |  |  | 3845.63
|  |  | JDH3-02-008-L-09-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2026-02-17 | 2026-03-09 | 06-Aug-25 A | 2026-03-18 | 1984-03-24 01:26 | 1984-03-24 01:41 | 38456.33 | Actual Total Cost | [13 empty] | 30765.07
|  |  | JDH3-02-008-L-09-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-02-19 | 2026-03-09 | 31-Aug-25 A | 2026-03-18 | 1999-07-11 10:19 | 1999-07-11 10:34 | 45440.54 | Planned Total Cost | [14 empty] | 36352.43 | 4544.05 |  |  |  |  | 4544.05
|  |  | JDH3-02-008-L-09-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-02-19 | 2026-03-09 | 31-Aug-25 A | 2026-03-18 | 1999-07-11 10:19 | 1999-07-11 10:34 | 45440.54 | Remaining Total Cost | [15 empty] | 4544.05 |  |  |  |  | 4544.05
|  |  | JDH3-02-008-L-09-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-02-19 | 2026-03-09 | 31-Aug-25 A | 2026-03-18 | 1999-07-11 10:19 | 1999-07-11 10:34 | 45440.54 | Actual Total Cost | [13 empty] | 3483.78 | 32868.66
|  |  | JDH3-02-008-L-09-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2026-01-01 | 2026-03-10 | 04-Apr-25 A | 2026-03-16 | 2361-06-25 11:02 | 2361-06-25 11:17 | 180620.36 | Planned Total Cost | [15 empty] | 6042.21 |  |  | 108167.78 |  |  | 66410.36
|  |  | JDH3-02-008-L-09-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2026-01-01 | 2026-03-10 | 04-Apr-25 A | 2026-03-16 | 2361-06-25 11:02 | 2361-06-25 11:17 | 180620.36 | Remaining Total Cost | [15 empty] | 6042.21 |  |  |  |  | 6023.69
|  |  | JDH3-02-008-L-09-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2026-01-01 | 2026-03-10 | 04-Apr-25 A | 2026-03-16 | 2361-06-25 11:02 | 2361-06-25 11:17 | 180620.36 | Actual Total Cost | [9 empty] | 77306.31 | 29197.69 | 16772.66 |  |  | 44644.22 | 633.6
|  |  | JDH3-02-008-L-09-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2026-01-04 | 2026-03-10 | 18-Mar-25 A | 2026-03-19 | 2348-10-13 06:14 | 2348-10-13 06:14 | 189125.38 | Planned Total Cost | [14 empty] | 15689.43 | 40836.21 |  |  | 113687.2 |  | 18912.54
|  |  | JDH3-02-008-L-09-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2026-01-04 | 2026-03-10 | 18-Mar-25 A | 2026-03-19 | 2348-10-13 06:14 | 2348-10-13 06:14 | 189125.38 | Remaining Total Cost | [15 empty] | 6296.59 |  |  |  |  | 18912.54
|  |  | JDH3-02-008-L-09-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2026-01-04 | 2026-03-10 | 18-Mar-25 A | 2026-03-19 | 2348-10-13 06:14 | 2348-10-13 06:14 | 189125.38 | Actual Total Cost | [8 empty] | 43563.37 | 57507.88 |  |  | 12615.95 |  | 50229.06
|  |  | JDH3-02-008-L-09-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2026-01-06 | 2026-02-28 | 25-Feb-25 A | 2025-10-08 | 248543.76 | 248543.75 | 437116.21 | Planned Total Cost | [15 empty] | 70508.27 |  |  | 189127.11 | 366.84 |  | 177113.99
|  |  | JDH3-02-008-L-09-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2026-01-06 | 2026-02-28 | 25-Feb-25 A | 2025-10-08 | 248543.76 | 248543.75 | 437116.21 | Remaining Total Cost | [15 empty] | 188572.46
|  |  | JDH3-02-008-L-09-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2026-01-06 | 2026-02-28 | 25-Feb-25 A | 2025-10-08 | 248543.76 | 248543.75 | 437116.21 | Actual Total Cost | [7 empty] | 6067.23 | 129835.9 | 52655.39 | 935.43 |  |  |  | 56162.17 | 2887.63
|  |  | JDH3-02-008-L-09-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2026-02-22 | 2026-03-09 | 11-Aug-25 A | 2026-03-18 | 1970-12-26 19:41 | 1970-12-26 19:55 | 32411.03 | Planned Total Cost | [15 empty] | 3241.1 |  |  |  | 25928.82 | 3241.1
|  |  | JDH3-02-008-L-09-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2026-02-22 | 2026-03-09 | 11-Aug-25 A | 2026-03-18 | 1970-12-26 19:41 | 1970-12-26 19:55 | 32411.03 | Remaining Total Cost | [15 empty] | 3241.1 |  |  |  |  | 3241.1
|  |  | JDH3-02-008-L-09-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2026-02-22 | 2026-03-09 | 11-Aug-25 A | 2026-03-18 | 1970-12-26 19:41 | 1970-12-26 19:55 | 32411.03 | Actual Total Cost | [13 empty] | 25928.83
|  |  | JDH3-02-008-L-09-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2026-02-24 | 2026-03-07 | 2025-10-02 | 2025-10-13 | 0 | 0 | 20857.39 | Planned Total Cost | [15 empty] | 20857.39
|  |  | JDH3-02-008-L-09-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2026-02-24 | 2026-03-07 | 2025-10-02 | 2025-10-13 | 0 | 0 | 20857.39 | Remaining Total Cost | [15 empty] | 20857.39
|  |  | JDH3-02-008-L-09-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2026-02-24 | 2026-03-07 | 2025-10-02 | 2025-10-13 | 0 | 0 | 20857.39 | Actual Total Cost
|  |  | JDH3-02-008-L-09-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-01-11 | 2026-03-02 | 05-May-25 A | 2025-10-08 | 2039-10-30 08:53 | 2039-10-30 09:07 | 82125.99 | Planned Total Cost | [15 empty] | 31052.61 |  |  | 38611.48 | 12461.9
|  |  | JDH3-02-008-L-09-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-01-11 | 2026-03-02 | 05-May-25 A | 2025-10-08 | 2039-10-30 08:53 | 2039-10-30 09:07 | 82125.99 | Remaining Total Cost | [15 empty] | 31052.61
|  |  | JDH3-02-008-L-09-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-01-11 | 2026-03-02 | 05-May-25 A | 2025-10-08 | 2039-10-30 08:53 | 2039-10-30 09:07 | 82125.99 | Actual Total Cost | [10 empty] | 26813.53 | 2413.22 | 9384.73 | 12461.9
|  |  | JDH3-02-008-L-09-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-02-26 | 2026-03-09 | 2025-10-05 | 2025-10-15 | 0 | 0 | 101679.79 | Planned Total Cost | [15 empty] | 101679.79
|  |  | JDH3-02-008-L-09-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-02-26 | 2026-03-09 | 2025-10-05 | 2025-10-15 | 0 | 0 | 101679.79 | Remaining Total Cost | [15 empty] | 101679.79
|  |  | JDH3-02-008-L-09-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-02-26 | 2026-03-09 | 2025-10-05 | 2025-10-15 | 0 | 0 | 101679.79 | Actual Total Cost
|  |  | JDH3-02-008-L-09-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-01-01 | 2026-03-04 | 05-May-25 A | 2025-10-11 | 1939-09-11 23:17 | 1939-09-11 23:31 | 21509.18 | Planned Total Cost | [15 empty] | 7009.21 |  |  | 14499.97
|  |  | JDH3-02-008-L-09-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-01-01 | 2026-03-04 | 05-May-25 A | 2025-10-11 | 1939-09-11 23:17 | 1939-09-11 23:31 | 21509.18 | Remaining Total Cost | [15 empty] | 7009.21
|  |  | JDH3-02-008-L-09-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-01-01 | 2026-03-04 | 05-May-25 A | 2025-10-11 | 1939-09-11 23:17 | 1939-09-11 23:31 | 21509.18 | Actual Total Cost | [10 empty] | 10754.6 | 234.09 | 3511.29
|  |  | JDH3-02-008-L-09-(ST)- Single Catchbasine Works |  | 2026-03-01 | 2026-03-11 | 2025-10-07 | 2025-10-18 | 0 | 0 | 62572.21 | Planned Total Cost | [15 empty] | 62572.21
|  |  | JDH3-02-008-L-09-(ST)- Single Catchbasine Works |  | 2026-03-01 | 2026-03-11 | 2025-10-07 | 2025-10-18 | 0 | 0 | 62572.21 | Remaining Total Cost | [15 empty] | 62572.21
|  |  | JDH3-02-008-L-09-(ST)- Single Catchbasine Works |  | 2026-03-01 | 2026-03-11 | 2025-10-07 | 2025-10-18 | 0 | 0 | 62572.21 | Actual Total Cost
|  |  | JDH3-02-008-L-09-(ST)- Double Catchbasine Works |  | 2026-03-03 | 2026-03-14 | 2025-10-09 | 2025-10-20 | 0 | 0 | 181824.28 | Planned Total Cost | [15 empty] | 181824.28
|  |  | JDH3-02-008-L-09-(ST)- Double Catchbasine Works |  | 2026-03-03 | 2026-03-14 | 2025-10-09 | 2025-10-20 | 0 | 0 | 181824.28 | Remaining Total Cost | [15 empty] | 181824.28
|  |  | JDH3-02-008-L-09-(ST)- Double Catchbasine Works |  | 2026-03-03 | 2026-03-14 | 2025-10-09 | 2025-10-20 | 0 | 0 | 181824.28 | Actual Total Cost
|  |  | JDH3-02-008-L-09-(ST)-PIPES ENCASEMENT |  | 2026-03-01 | 2026-03-07 | 2026-03-09 | 2026-03-16 | 0 | 0 | 20837 | Planned Total Cost | [20 empty] | 20837
|  |  | JDH3-02-008-L-09-(ST)-PIPES ENCASEMENT |  | 2026-03-01 | 2026-03-07 | 2026-03-09 | 2026-03-16 | 0 | 0 | 20837 | Remaining Total Cost | [20 empty] | 20837
|  |  | JDH3-02-008-L-09-(ST)-PIPES ENCASEMENT |  | 2026-03-01 | 2026-03-07 | 2026-03-09 | 2026-03-16 | 0 | 0 | 20837 | Actual Total Cost
|  |  | JDH3-02-008-L-09-TSE Network - TSE |  | 2026-03-14 | 2026-04-13 | 2026-03-22 | 2026-04-22 | 0 | 0 | 127530.31 | Planned Total Cost | [20 empty] | 29597.3 | 97933.01
|  |  | JDH3-02-008-L-09-TSE Network - TSE |  | 2026-03-14 | 2026-04-13 | 2026-03-22 | 2026-04-22 | 0 | 0 | 127530.31 | Remaining Total Cost | [20 empty] | 29597.3 | 97933.01
|  |  | JDH3-02-008-L-09-TSE Network - TSE |  | 2026-03-14 | 2026-04-13 | 2026-03-22 | 2026-04-22 | 0 | 0 | 127530.31 | Actual Total Cost
|  |  | JDH3-02-008-L-09-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-03-14 | 2026-04-13 | 2026-03-22 | 2026-04-22 | 0 | 0 | 86497.29 | Planned Total Cost | [20 empty] | 21278.33 | 65218.96
|  |  | JDH3-02-008-L-09-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-03-14 | 2026-04-13 | 2026-03-22 | 2026-04-22 | 0 | 0 | 86497.29 | Remaining Total Cost | [20 empty] | 21278.33 | 65218.96
|  |  | JDH3-02-008-L-09-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-03-14 | 2026-04-13 | 2026-03-22 | 2026-04-22 | 0 | 0 | 86497.29 | Actual Total Cost
|  |  | JDH3-02-008-L-09-(TSE)-Supply and install gate valves-100 mm |  | 2026-04-02 | 2026-04-06 | 2026-04-11 | 2026-04-15 | 0 | 0 | 6465.8 | Planned Total Cost | [21 empty] | 6465.8
|  |  | JDH3-02-008-L-09-(TSE)-Supply and install gate valves-100 mm |  | 2026-04-02 | 2026-04-06 | 2026-04-11 | 2026-04-15 | 0 | 0 | 6465.8 | Remaining Total Cost | [21 empty] | 6465.8
|  |  | JDH3-02-008-L-09-(TSE)-Supply and install gate valves-100 mm |  | 2026-04-02 | 2026-04-06 | 2026-04-11 | 2026-04-15 | 0 | 0 | 6465.8 | Actual Total Cost
|  |  | JDH3-02-008-L-09-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-04-02 | 2026-04-06 | 2026-04-11 | 2026-04-15 | 0 | 0 | 9791.9 | Planned Total Cost | [21 empty] | 9791.9
|  |  | JDH3-02-008-L-09-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-04-02 | 2026-04-06 | 2026-04-11 | 2026-04-15 | 0 | 0 | 9791.9 | Remaining Total Cost | [21 empty] | 9791.9
|  |  | JDH3-02-008-L-09-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-04-02 | 2026-04-06 | 2026-04-11 | 2026-04-15 | 0 | 0 | 9791.9 | Actual Total Cost
|  |  | JDH3-02-008-L-09-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-04-02 | 2026-04-06 | 2026-04-11 | 2026-04-15 | 0 | 0 | 7444.14 | Planned Total Cost | [21 empty] | 7444.14
|  |  | JDH3-02-008-L-09-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-04-02 | 2026-04-06 | 2026-04-11 | 2026-04-15 | 0 | 0 | 7444.14 | Remaining Total Cost | [21 empty] | 7444.14
|  |  | JDH3-02-008-L-09-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-04-02 | 2026-04-06 | 2026-04-11 | 2026-04-15 | 0 | 0 | 7444.14 | Actual Total Cost
|  |  | JDH3-02-008-L-09-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-03-18 | 2026-04-08 | 2026-03-26 | 2026-04-18 | 0 | 0 | 13851.92 | Planned Total Cost | [20 empty] | 6648.92 | 7203
|  |  | JDH3-02-008-L-09-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-03-18 | 2026-04-08 | 2026-03-26 | 2026-04-18 | 0 | 0 | 13851.92 | Remaining Total Cost | [20 empty] | 6648.92 | 7203
|  |  | JDH3-02-008-L-09-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-03-18 | 2026-04-08 | 2026-03-26 | 2026-04-18 | 0 | 0 | 13851.92 | Actual Total Cost
|  |  | JDH3-02-008-L-09-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-03-18 | 2026-04-08 | 2026-03-26 | 2026-04-18 | 0 | 0 | 3479.28 | Planned Total Cost | [20 empty] | 1670.05 | 1809.22
|  |  | JDH3-02-008-L-09-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-03-18 | 2026-04-08 | 2026-03-26 | 2026-04-18 | 0 | 0 | 3479.28 | Remaining Total Cost | [20 empty] | 1670.05 | 1809.22
|  |  | JDH3-02-008-L-09-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-03-18 | 2026-04-08 | 2026-03-26 | 2026-04-18 | 0 | 0 | 3479.28 | Actual Total Cost
|  |  | JDH3-02-008-L-09-Potable Water Network - WT |  | 2026-04-14 | 2026-04-25 | 2026-04-22 | 2026-05-04 | 0 | 0 | 71725.41 | Planned Total Cost | [21 empty] | 70735.82 | 989.59
|  |  | JDH3-02-008-L-09-Potable Water Network - WT |  | 2026-04-14 | 2026-04-25 | 2026-04-22 | 2026-05-04 | 0 | 0 | 71725.41 | Remaining Total Cost | [21 empty] | 70735.82 | 989.59
|  |  | JDH3-02-008-L-09-Potable Water Network - WT |  | 2026-04-14 | 2026-04-25 | 2026-04-22 | 2026-05-04 | 0 | 0 | 71725.41 | Actual Total Cost
|  |  | JDH3-02-008-L-09-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-04-14 | 2026-04-25 | 2026-04-22 | 2026-05-04 | 0 | 0 | 8246.59 | Planned Total Cost | [21 empty] | 7257 | 989.59
|  |  | JDH3-02-008-L-09-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-04-14 | 2026-04-25 | 2026-04-22 | 2026-05-04 | 0 | 0 | 8246.59 | Remaining Total Cost | [21 empty] | 7257 | 989.59
|  |  | JDH3-02-008-L-09-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-04-14 | 2026-04-25 | 2026-04-22 | 2026-05-04 | 0 | 0 | 8246.59 | Actual Total Cost
|  |  | JDH3-02-008-L-09-(WT)- Supply and install 3-out fire hydrant |  | 2026-04-14 | 2026-04-20 | 2026-04-22 | 2026-04-29 | 0 | 0 | 63478.82 | Planned Total Cost | [21 empty] | 63478.82
|  |  | JDH3-02-008-L-09-(WT)- Supply and install 3-out fire hydrant |  | 2026-04-14 | 2026-04-20 | 2026-04-22 | 2026-04-29 | 0 | 0 | 63478.82 | Remaining Total Cost | [21 empty] | 63478.82
|  |  | JDH3-02-008-L-09-(WT)- Supply and install 3-out fire hydrant |  | 2026-04-14 | 2026-04-20 | 2026-04-22 | 2026-04-29 | 0 | 0 | 63478.82 | Actual Total Cost
|  |  | L-10 |  | 2026-04-16 | 2026-07-05 | 20-Nov-24 A | 2026-04-21 | 624900.12 | 624900.12 | 1858666.02 | Planned Total Cost | [15 empty] | 499273.74 |  |  |  | 62051.07 | 559848.86 | 338513.71 | 398978.65
|  |  | L-10 |  | 2026-04-16 | 2026-07-05 | 20-Nov-24 A | 2026-04-21 | 624900.12 | 624900.12 | 1858666.02 | Remaining Total Cost | [15 empty] | 464215.77 |  |  |  | 62051.07 | 559848.86 | 147650.21
|  |  | L-10 |  | 2026-04-16 | 2026-07-05 | 20-Nov-24 A | 2026-04-21 | 624900.12 | 624900.12 | 1858666.02 | Actual Total Cost | [6 empty] | 15492.1 | 102899.33 | 150099.97 | 124819.77 | 40377.36 | 14855.28 | 7400.54 | 15727.71 | 145350.26 | 7877.8
|  |  | JDH3-02-008-L-10-Storm Network - ST |  | 2026-04-25 | 2026-06-09 | 21-Jan-25 A | 2026-03-26 | 624900.12 | 624900.12 | 1677155.58 | Planned Total Cost | [15 empty] | 499273.74 |  |  |  | 62051.07 | 525988.62 | 190863.5 | 398978.65
|  |  | JDH3-02-008-L-10-Storm Network - ST |  | 2026-04-25 | 2026-06-09 | 21-Jan-25 A | 2026-03-26 | 624900.12 | 624900.12 | 1677155.58 | Remaining Total Cost | [15 empty] | 464215.77 |  |  |  | 62051.07 | 525988.62
|  |  | JDH3-02-008-L-10-Storm Network - ST |  | 2026-04-25 | 2026-06-09 | 21-Jan-25 A | 2026-03-26 | 624900.12 | 624900.12 | 1677155.58 | Actual Total Cost | [6 empty] | 15492.1 | 102899.33 | 150099.97 | 124819.77 | 40377.36 | 14855.28 | 7400.54 | 15727.71 | 145350.26 | 7877.8
|  |  | JDH3-02-008-L-10-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-04-25 | 2026-06-09 | 2026-02-22 | 2026-03-26 | 0 | 0 | 245714.94 | Planned Total Cost | [19 empty] | 59790.63 | 185924.3
|  |  | JDH3-02-008-L-10-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-04-25 | 2026-06-09 | 2026-02-22 | 2026-03-26 | 0 | 0 | 245714.94 | Remaining Total Cost | [19 empty] | 59790.63 | 185924.3
|  |  | JDH3-02-008-L-10-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-04-25 | 2026-06-09 | 2026-02-22 | 2026-03-26 | 0 | 0 | 245714.94 | Actual Total Cost
|  |  | JDH3-02-008-L-10-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2026-04-28 | 2026-06-06 | 2026-02-25 | 2026-03-23 | 0 | 0 | 8012.22 | Planned Total Cost | [19 empty] | 1722.63 | 6289.59
|  |  | JDH3-02-008-L-10-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2026-04-28 | 2026-06-06 | 2026-02-25 | 2026-03-23 | 0 | 0 | 8012.22 | Remaining Total Cost | [19 empty] | 1722.63 | 6289.59
|  |  | JDH3-02-008-L-10-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2026-04-28 | 2026-06-06 | 2026-02-25 | 2026-03-23 | 0 | 0 | 8012.22 | Actual Total Cost
|  |  | JDH3-02-008-L-10-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-05-21 | 2026-06-06 | 2026-03-07 | 2026-03-23 | 0 | 0 | 38259.26 | Planned Total Cost | [20 empty] | 38259.26
|  |  | JDH3-02-008-L-10-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-05-21 | 2026-06-06 | 2026-03-07 | 2026-03-23 | 0 | 0 | 38259.26 | Remaining Total Cost | [20 empty] | 38259.26
|  |  | JDH3-02-008-L-10-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-05-21 | 2026-06-06 | 2026-03-07 | 2026-03-23 | 0 | 0 | 38259.26 | Actual Total Cost
|  |  | JDH3-02-008-L-10-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2026-04-25 | 2026-05-11 | 05-Apr-25 A | 2026-03-11 | 2005-11-21 22:19 | 2005-11-21 22:19 | 47662.63 | Planned Total Cost | [19 empty] | 537.8 | 8446.89 | 30945.46 | 7732.47
|  |  | JDH3-02-008-L-10-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2026-04-25 | 2026-05-11 | 05-Apr-25 A | 2026-03-11 | 2005-11-21 22:19 | 2005-11-21 22:19 | 47662.63 | Remaining Total Cost | [19 empty] | 537.8 | 8446.89
|  |  | JDH3-02-008-L-10-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2026-04-25 | 2026-05-11 | 05-Apr-25 A | 2026-03-11 | 2005-11-21 22:19 | 2005-11-21 22:19 | 47662.63 | Actual Total Cost | [9 empty] | 38677.93
|  |  | JDH3-02-008-L-10-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-04-25 | 2026-05-05 | 11-Mar-25 A | 17-May-25 A | 2029-10-06 21:22 | 2029-10-06 21:22 | 47397.89 | Planned Total Cost | [21 empty] | 37918.31 | 9479.58
|  |  | JDH3-02-008-L-10-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-04-25 | 2026-05-05 | 11-Mar-25 A | 17-May-25 A | 2029-10-06 21:22 | 2029-10-06 21:22 | 47397.89 | Remaining Total Cost
|  |  | JDH3-02-008-L-10-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-04-25 | 2026-05-05 | 11-Mar-25 A | 17-May-25 A | 2029-10-06 21:22 | 2029-10-06 21:22 | 47397.89 | Actual Total Cost | [8 empty] | 9479.58 | 23402.71 | 14515.61
|  |  | JDH3-02-008-L-10-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2026-04-27 | 2026-05-13 | 04-Mar-25 A | 2025-10-06 | 2316-05-01 18:14 | 2316-05-01 18:14 | 175720.58 | Planned Total Cost | [15 empty] | 23656.82 | [5 empty] | 108988.23 | 43075.53
|  |  | JDH3-02-008-L-10-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2026-04-27 | 2026-05-13 | 04-Mar-25 A | 2025-10-06 | 2316-05-01 18:14 | 2316-05-01 18:14 | 175720.58 | Remaining Total Cost | [15 empty] | 23656.82
|  |  | JDH3-02-008-L-10-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2026-04-27 | 2026-05-13 | 04-Mar-25 A | 2025-10-06 | 2316-05-01 18:14 | 2316-05-01 18:14 | 175720.58 | Actual Total Cost | [8 empty] | 32007.19 | 13939.34 |  | 5205.02 | 6282.27 |  | 94629.94
|  |  | JDH3-02-008-L-10-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2026-04-29 | 2026-05-16 | 10-Mar-25 A | 2025-10-07 | 115544.31 | 2216-05-06 07:26 | 191161.84 | Planned Total Cost | [15 empty] | 126067.55 | [5 empty] | 13011.5 | 52082.78
|  |  | JDH3-02-008-L-10-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2026-04-29 | 2026-05-16 | 10-Mar-25 A | 2025-10-07 | 115544.31 | 2216-05-06 07:26 | 191161.84 | Remaining Total Cost | [15 empty] | 75617.52
|  |  | JDH3-02-008-L-10-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2026-04-29 | 2026-05-16 | 10-Mar-25 A | 2025-10-07 | 115544.31 | 2216-05-06 07:26 | 191161.84 | Actual Total Cost | [8 empty] | 27558.59 | 30414.5 | 3662.25 | 3458.94 |  |  | 42874.01 | 7576.02
|  |  | JDH3-02-008-L-10-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2026-05-02 | 2026-05-30 | 21-Jan-25 A | 2025-10-14 | 218188.62 | 218188.62 | 439641.91 | Planned Total Cost | [15 empty] | 221453.29 | [6 empty] | 218188.62
|  |  | JDH3-02-008-L-10-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2026-05-02 | 2026-05-30 | 21-Jan-25 A | 2025-10-14 | 218188.62 | 218188.62 | 439641.91 | Remaining Total Cost | [15 empty] | 221453.29
|  |  | JDH3-02-008-L-10-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2026-05-02 | 2026-05-30 | 21-Jan-25 A | 2025-10-14 | 218188.62 | 218188.62 | 439641.91 | Actual Total Cost | [6 empty] | 15349.3 | 98688 | 72199.09 | 17972.73 | 8865.05 | 5114.45
|  |  | JDH3-02-008-L-10-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2026-05-06 | 2026-06-06 | 21-Jan-25 A | 2026-03-23 | 1918-09-13 17:46 | 1918-09-13 17:46 | 31286.09 | Planned Total Cost | [15 empty] | 17910.38 |  |  |  |  | 3128.61 |  | 10247.1
|  |  | JDH3-02-008-L-10-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2026-05-06 | 2026-06-06 | 21-Jan-25 A | 2026-03-23 | 1918-09-13 17:46 | 1918-09-13 17:46 | 31286.09 | Remaining Total Cost | [15 empty] | 21325.74 |  |  |  |  | 3128.61
|  |  | JDH3-02-008-L-10-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2026-05-06 | 2026-06-06 | 21-Jan-25 A | 2026-03-23 | 1918-09-13 17:46 | 1918-09-13 17:46 | 31286.09 | Actual Total Cost | [6 empty] | 142.81 | 380.82 | 428.42 | 412.55 | 1076.86 | 1076.86 | 1118.28 | 1076.86 | 1076.86 | 41.42
|  |  | JDH3-02-008-L-10-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-05-09 | 2026-06-06 | 23-Feb-25 A | 2026-03-23 | 2026-06-22 20:53 | 2026-06-22 20:53 | 68438.32 | Planned Total Cost | [15 empty] | 3421.92 |  |  |  |  | 6843.83 |  | 58172.57
|  |  | JDH3-02-008-L-10-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-05-09 | 2026-06-06 | 23-Feb-25 A | 2026-03-23 | 2026-06-22 20:53 | 2026-06-22 20:53 | 68438.32 | Remaining Total Cost | [15 empty] | 15398.62 |  |  |  |  | 6843.83
|  |  | JDH3-02-008-L-10-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-05-09 | 2026-06-06 | 23-Feb-25 A | 2026-03-23 | 2026-06-22 20:53 | 2026-06-22 20:53 | 68438.32 | Actual Total Cost | [7 empty] | 3830.5 | 8427.11 |  | 12257.6 |  |  | 14650.85 | 6769.44 | 260.36
|  |  | JDH3-02-008-L-10-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-05-14 | 2026-06-06 | 2025-10-02 | 2026-03-23 | 0 | 0 | 118626.42 | Planned Total Cost | [15 empty] | 106763.78 |  |  |  |  | 11862.64
|  |  | JDH3-02-008-L-10-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-05-14 | 2026-06-06 | 2025-10-02 | 2026-03-23 | 0 | 0 | 118626.42 | Remaining Total Cost | [15 empty] | 106763.78 |  |  |  |  | 11862.64
|  |  | JDH3-02-008-L-10-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-05-14 | 2026-06-06 | 2025-10-02 | 2026-03-23 | 0 | 0 | 118626.42 | Actual Total Cost
|  |  | JDH3-02-008-L-10-(ST)- Single Catchbasine Works |  | 2026-05-17 | 2026-06-06 | 2026-03-02 | 2026-03-23 | 0 | 0 | 62572.21 | Planned Total Cost | [20 empty] | 62572.21
|  |  | JDH3-02-008-L-10-(ST)- Single Catchbasine Works |  | 2026-05-17 | 2026-06-06 | 2026-03-02 | 2026-03-23 | 0 | 0 | 62572.21 | Remaining Total Cost | [20 empty] | 62572.21
|  |  | JDH3-02-008-L-10-(ST)- Single Catchbasine Works |  | 2026-05-17 | 2026-06-06 | 2026-03-02 | 2026-03-23 | 0 | 0 | 62572.21 | Actual Total Cost
|  |  | JDH3-02-008-L-10-(ST)- Double Catchbasine Works |  | 2026-05-19 | 2026-06-06 | 2026-03-04 | 2026-03-23 | 0 | 0 | 181824.28 | Planned Total Cost | [20 empty] | 181824.28
|  |  | JDH3-02-008-L-10-(ST)- Double Catchbasine Works |  | 2026-05-19 | 2026-06-06 | 2026-03-04 | 2026-03-23 | 0 | 0 | 181824.28 | Remaining Total Cost | [20 empty] | 181824.28
|  |  | JDH3-02-008-L-10-(ST)- Double Catchbasine Works |  | 2026-05-19 | 2026-06-06 | 2026-03-04 | 2026-03-23 | 0 | 0 | 181824.28 | Actual Total Cost
|  |  | JDH3-02-008-L-10-(ST)-PIPES ENCASEMENT |  | 2026-05-28 | 2026-06-03 | 2026-03-14 | 2026-03-21 | 0 | 0 | 20837 | Planned Total Cost | [20 empty] | 20837
|  |  | JDH3-02-008-L-10-(ST)-PIPES ENCASEMENT |  | 2026-05-28 | 2026-06-03 | 2026-03-14 | 2026-03-21 | 0 | 0 | 20837 | Remaining Total Cost | [20 empty] | 20837
|  |  | JDH3-02-008-L-10-(ST)-PIPES ENCASEMENT |  | 2026-05-28 | 2026-06-03 | 2026-03-14 | 2026-03-21 | 0 | 0 | 20837 | Actual Total Cost
|  |  | JDH3-02-008-L-10-TSE Network - TSE |  | 2026-06-07 | 2026-07-05 | 2026-03-23 | 2026-04-21 | 0 | 0 | 111228.72 | Planned Total Cost | [20 empty] | 22070.93 | 89157.79
|  |  | JDH3-02-008-L-10-TSE Network - TSE |  | 2026-06-07 | 2026-07-05 | 2026-03-23 | 2026-04-21 | 0 | 0 | 111228.72 | Remaining Total Cost | [20 empty] | 22070.93 | 89157.79
|  |  | JDH3-02-008-L-10-TSE Network - TSE |  | 2026-06-07 | 2026-07-05 | 2026-03-23 | 2026-04-21 | 0 | 0 | 111228.72 | Actual Total Cost
|  |  | JDH3-02-008-L-10-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-06-07 | 2026-07-05 | 2026-03-23 | 2026-04-21 | 0 | 0 | 77207.72 | Planned Total Cost | [20 empty] | 18915.89 | 58291.83
|  |  | JDH3-02-008-L-10-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-06-07 | 2026-07-05 | 2026-03-23 | 2026-04-21 | 0 | 0 | 77207.72 | Remaining Total Cost | [20 empty] | 18915.89 | 58291.83
|  |  | JDH3-02-008-L-10-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-06-07 | 2026-07-05 | 2026-03-23 | 2026-04-21 | 0 | 0 | 77207.72 | Actual Total Cost
|  |  | JDH3-02-008-L-10-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-06-11 | 2026-06-30 | 2026-03-28 | 2026-04-16 | 0 | 0 | 3911.39 | Planned Total Cost | [20 empty] | 938.73 | 2972.66
|  |  | JDH3-02-008-L-10-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-06-11 | 2026-06-30 | 2026-03-28 | 2026-04-16 | 0 | 0 | 3911.39 | Remaining Total Cost | [20 empty] | 938.73 | 2972.66
|  |  | JDH3-02-008-L-10-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-06-11 | 2026-06-30 | 2026-03-28 | 2026-04-16 | 0 | 0 | 3911.39 | Actual Total Cost
|  |  | JDH3-02-008-L-10-(TSE)-Supply and install gate valves-100 mm |  | 2026-06-24 | 2026-06-28 | 2026-04-09 | 2026-04-14 | 0 | 0 | 6465.8 | Planned Total Cost | [21 empty] | 6465.8
|  |  | JDH3-02-008-L-10-(TSE)-Supply and install gate valves-100 mm |  | 2026-06-24 | 2026-06-28 | 2026-04-09 | 2026-04-14 | 0 | 0 | 6465.8 | Remaining Total Cost | [21 empty] | 6465.8
|  |  | JDH3-02-008-L-10-(TSE)-Supply and install gate valves-100 mm |  | 2026-06-24 | 2026-06-28 | 2026-04-09 | 2026-04-14 | 0 | 0 | 6465.8 | Actual Total Cost
|  |  | JDH3-02-008-L-10-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-06-24 | 2026-06-28 | 2026-04-09 | 2026-04-14 | 0 | 0 | 9791.9 | Planned Total Cost | [21 empty] | 9791.9
|  |  | JDH3-02-008-L-10-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-06-24 | 2026-06-28 | 2026-04-09 | 2026-04-14 | 0 | 0 | 9791.9 | Remaining Total Cost | [21 empty] | 9791.9
|  |  | JDH3-02-008-L-10-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-06-24 | 2026-06-28 | 2026-04-09 | 2026-04-14 | 0 | 0 | 9791.9 | Actual Total Cost
|  |  | JDH3-02-008-L-10-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-06-14 | 2026-07-02 | 2026-03-30 | 2026-04-19 | 0 | 0 | 13851.92 | Planned Total Cost | [20 empty] | 2216.31 | 11635.61
|  |  | JDH3-02-008-L-10-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-06-14 | 2026-07-02 | 2026-03-30 | 2026-04-19 | 0 | 0 | 13851.92 | Remaining Total Cost | [20 empty] | 2216.31 | 11635.61
|  |  | JDH3-02-008-L-10-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-06-14 | 2026-07-02 | 2026-03-30 | 2026-04-19 | 0 | 0 | 13851.92 | Actual Total Cost
|  |  | JDH3-02-008-L-10-Potable Water Network - WT |  | 2026-06-11 | 2026-06-22 | 2026-03-28 | 2026-04-08 | 0 | 0 | 70281.72 | Planned Total Cost | [20 empty] | 11789.31 | 58492.41
|  |  | JDH3-02-008-L-10-Potable Water Network - WT |  | 2026-06-11 | 2026-06-22 | 2026-03-28 | 2026-04-08 | 0 | 0 | 70281.72 | Remaining Total Cost | [20 empty] | 11789.31 | 58492.41
|  |  | JDH3-02-008-L-10-Potable Water Network - WT |  | 2026-06-11 | 2026-06-22 | 2026-03-28 | 2026-04-08 | 0 | 0 | 70281.72 | Actual Total Cost
|  |  | JDH3-02-008-L-10-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-06-11 | 2026-06-22 | 2026-03-28 | 2026-04-08 | 0 | 0 | 6802.9 | Planned Total Cost | [20 empty] | 1632.7 | 5170.2
|  |  | JDH3-02-008-L-10-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-06-11 | 2026-06-22 | 2026-03-28 | 2026-04-08 | 0 | 0 | 6802.9 | Remaining Total Cost | [20 empty] | 1632.7 | 5170.2
|  |  | JDH3-02-008-L-10-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-06-11 | 2026-06-22 | 2026-03-28 | 2026-04-08 | 0 | 0 | 6802.9 | Actual Total Cost
|  |  | JDH3-02-008-L-10-(WT)- Supply and install 3-out fire hydrant |  | 2026-06-14 | 2026-06-20 | 2026-03-30 | 2026-04-06 | 0 | 0 | 63478.82 | Planned Total Cost | [20 empty] | 10156.61 | 53322.21
|  |  | JDH3-02-008-L-10-(WT)- Supply and install 3-out fire hydrant |  | 2026-06-14 | 2026-06-20 | 2026-03-30 | 2026-04-06 | 0 | 0 | 63478.82 | Remaining Total Cost | [20 empty] | 10156.61 | 53322.21
|  |  | JDH3-02-008-L-10-(WT)- Supply and install 3-out fire hydrant |  | 2026-06-14 | 2026-06-20 | 2026-03-30 | 2026-04-06 | 0 | 0 | 63478.82 | Actual Total Cost
|  |  | L-11 |  | 2026-03-15 | 2026-06-11 | 08-Jul-25 A | 2025-12-04 | 2439-12-09 16:34 | 2439-12-09 16:48 | 1995184.45 | Planned Total Cost | [14 empty] | 114628.35 | 1704462.82 | 170437.08 | 5656.2
|  |  | L-11 |  | 2026-03-15 | 2026-06-11 | 08-Jul-25 A | 2025-12-04 | 2439-12-09 16:34 | 2439-12-09 16:48 | 1995184.45 | Remaining Total Cost | [15 empty] | 1621880.47 | 170437.08 | 5656.2
|  |  | L-11 |  | 2026-03-15 | 2026-06-11 | 08-Jul-25 A | 2025-12-04 | 2439-12-09 16:34 | 2439-12-09 16:48 | 1995184.45 | Actual Total Cost | [14 empty] | 180726.6 | 16484.1
|  |  | JDH3-02-008-L-11-Storm Network - ST |  | 2026-03-23 | 2026-05-10 | 03-Sep-25 A | 2025-11-02 | 2439-12-09 16:34 | 2439-12-09 16:48 | 1820250.51 | Planned Total Cost | [14 empty] | 114628.35 | 1699013.51 | 6608.65
|  |  | JDH3-02-008-L-11-Storm Network - ST |  | 2026-03-23 | 2026-05-10 | 03-Sep-25 A | 2025-11-02 | 2439-12-09 16:34 | 2439-12-09 16:48 | 1820250.51 | Remaining Total Cost | [15 empty] | 1616431.17 | 6608.65
|  |  | JDH3-02-008-L-11-Storm Network - ST |  | 2026-03-23 | 2026-05-10 | 03-Sep-25 A | 2025-11-02 | 2439-12-09 16:34 | 2439-12-09 16:48 | 1820250.51 | Actual Total Cost | [14 empty] | 180726.6 | 16484.1
|  |  | JDH3-02-008-L-11-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-03-23 | 2026-05-02 | 2025-10-02 | 2025-10-25 | 0 | 0 | 248906.14 | Planned Total Cost | [15 empty] | 248906.14
|  |  | JDH3-02-008-L-11-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-03-23 | 2026-05-02 | 2025-10-02 | 2025-10-25 | 0 | 0 | 248906.14 | Remaining Total Cost | [15 empty] | 248906.14
|  |  | JDH3-02-008-L-11-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-03-23 | 2026-05-02 | 2025-10-02 | 2025-10-25 | 0 | 0 | 248906.14 | Actual Total Cost
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2026-03-26 | 2026-04-30 | 2025-10-06 | 2025-10-23 | 0 | 0 | 9255.33 | Planned Total Cost | [15 empty] | 9255.33
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2026-03-26 | 2026-04-30 | 2025-10-06 | 2025-10-23 | 0 | 0 | 9255.33 | Remaining Total Cost | [15 empty] | 9255.33
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2026-03-26 | 2026-04-30 | 2025-10-06 | 2025-10-23 | 0 | 0 | 9255.33 | Actual Total Cost
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-03-29 | 2026-04-30 | 2025-10-08 | 2025-10-23 | 0 | 0 | 40590.09 | Planned Total Cost | [15 empty] | 40590.09
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-03-29 | 2026-04-30 | 2025-10-08 | 2025-10-23 | 0 | 0 | 40590.09 | Remaining Total Cost | [15 empty] | 40590.09
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-03-29 | 2026-04-30 | 2025-10-08 | 2025-10-23 | 0 | 0 | 40590.09 | Actual Total Cost
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2026-03-31 | 2026-04-30 | 03-Sep-25 A | 2025-10-23 | 1984-07-13 21:50 | 1984-07-13 22:05 | 38596.14 | Planned Total Cost | [14 empty] | 30876.91 | 7719.23
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2026-03-31 | 2026-04-30 | 03-Sep-25 A | 2025-10-23 | 1984-07-13 21:50 | 1984-07-13 22:05 | 38596.14 | Remaining Total Cost | [15 empty] | 7719.23
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2026-03-31 | 2026-04-30 | 03-Sep-25 A | 2025-10-23 | 1984-07-13 21:50 | 1984-07-13 22:05 | 38596.14 | Actual Total Cost | [14 empty] | 30876.92
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-04-02 | 2026-04-30 | 17-Sep-25 A | 2025-10-23 | 1999-11-14 04:34 | 1999-11-14 04:34 | 55955 | Planned Total Cost | [14 empty] | 29376.38 | 26578.63
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-04-02 | 2026-04-30 | 17-Sep-25 A | 2025-10-23 | 1999-11-14 04:34 | 1999-11-14 04:34 | 55955 | Remaining Total Cost | [15 empty] | 19476.81
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2026-04-02 | 2026-04-30 | 17-Sep-25 A | 2025-10-23 | 1999-11-14 04:34 | 1999-11-14 04:34 | 55955 | Actual Total Cost | [14 empty] | 33306.81 | 3171.38
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2026-04-05 | 2026-05-02 | 17-Sep-25 A | 2025-10-25 | 2067-04-28 18:00 | 2067-04-28 18:00 | 164824.06 | Planned Total Cost | [14 empty] | 37085.41 | 127738.65
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2026-04-05 | 2026-05-02 | 17-Sep-25 A | 2025-10-25 | 2067-04-28 18:00 | 2067-04-28 18:00 | 164824.06 | Remaining Total Cost | [15 empty] | 103708.31
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2026-04-05 | 2026-05-02 | 17-Sep-25 A | 2025-10-25 | 2067-04-28 18:00 | 2067-04-28 18:00 | 164824.06 | Actual Total Cost | [14 empty] | 55916.75 | 5199
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2026-04-07 | 2026-05-02 | 18-Sep-25 A | 2025-10-25 | 2037-11-18 12:29 | 2037-11-18 12:29 | 172896.5 | Planned Total Cost | [14 empty] | 17289.65 | 155606.85
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2026-04-07 | 2026-05-02 | 18-Sep-25 A | 2025-10-25 | 2037-11-18 12:29 | 2037-11-18 12:29 | 172896.5 | Remaining Total Cost | [15 empty] | 122533.98
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2026-04-07 | 2026-05-02 | 18-Sep-25 A | 2025-10-25 | 2037-11-18 12:29 | 2037-11-18 12:29 | 172896.5 | Actual Total Cost | [14 empty] | 44699.11 | 5663.41
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2026-04-09 | 2026-04-30 | 23-Sep-25 A | 2025-10-23 | 1950-04-24 07:41 | 1950-04-24 07:41 | 349230.2 | Planned Total Cost | [15 empty] | 349230.2
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2026-04-09 | 2026-04-30 | 23-Sep-25 A | 2025-10-23 | 1950-04-24 07:41 | 1950-04-24 07:41 | 349230.2 | Remaining Total Cost | [15 empty] | 330852.88
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2026-04-09 | 2026-04-30 | 23-Sep-25 A | 2025-10-23 | 1950-04-24 07:41 | 1950-04-24 07:41 | 349230.2 | Actual Total Cost | [14 empty] | 15927.01 | 2450.31
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2026-04-13 | 2026-04-30 | 2025-10-05 | 2025-10-23 | 0 | 0 | 144949.56 | Planned Total Cost | [15 empty] | 144949.56
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2026-04-13 | 2026-04-30 | 2025-10-05 | 2025-10-23 | 0 | 0 | 144949.56 | Remaining Total Cost | [15 empty] | 144949.56
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2026-04-13 | 2026-04-30 | 2025-10-05 | 2025-10-23 | 0 | 0 | 144949.56 | Actual Total Cost
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-04-15 | 2026-04-30 | 2025-10-07 | 2025-10-23 | 0 | 0 | 28401.88 | Planned Total Cost | [15 empty] | 28401.88
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-04-15 | 2026-04-30 | 2025-10-07 | 2025-10-23 | 0 | 0 | 28401.88 | Remaining Total Cost | [15 empty] | 28401.88
|  |  | JDH3-02-008-L-11-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-04-15 | 2026-04-30 | 2025-10-07 | 2025-10-23 | 0 | 0 | 28401.88 | Actual Total Cost
|  |  | JDH3-02-008-L-11-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2026-04-18 | 2026-04-28 | 2025-10-09 | 2025-10-21 | 0 | 0 | 31286.09 | Planned Total Cost | [15 empty] | 31286.09
|  |  | JDH3-02-008-L-11-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2026-04-18 | 2026-04-28 | 2025-10-09 | 2025-10-21 | 0 | 0 | 31286.09 | Remaining Total Cost | [15 empty] | 31286.09
|  |  | JDH3-02-008-L-11-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2026-04-18 | 2026-04-28 | 2025-10-09 | 2025-10-21 | 0 | 0 | 31286.09 | Actual Total Cost
|  |  | JDH3-02-008-L-11-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-04-20 | 2026-04-30 | 2025-10-12 | 2025-10-23 | 0 | 0 | 54750.66 | Planned Total Cost | [15 empty] | 54750.66
|  |  | JDH3-02-008-L-11-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-04-20 | 2026-04-30 | 2025-10-12 | 2025-10-23 | 0 | 0 | 54750.66 | Remaining Total Cost | [15 empty] | 54750.66
|  |  | JDH3-02-008-L-11-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2026-04-20 | 2026-04-30 | 2025-10-12 | 2025-10-23 | 0 | 0 | 54750.66 | Actual Total Cost
|  |  | JDH3-02-008-L-11-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-04-22 | 2026-05-03 | 2025-10-14 | 2025-10-26 | 0 | 0 | 135573.05 | Planned Total Cost | [15 empty] | 135573.05
|  |  | JDH3-02-008-L-11-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-04-22 | 2026-05-03 | 2025-10-14 | 2025-10-26 | 0 | 0 | 135573.05 | Remaining Total Cost | [15 empty] | 135573.05
|  |  | JDH3-02-008-L-11-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2026-04-22 | 2026-05-03 | 2025-10-14 | 2025-10-26 | 0 | 0 | 135573.05 | Actual Total Cost
|  |  | JDH3-02-008-L-11-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-04-25 | 2026-05-05 | 2025-10-16 | 2025-10-28 | 0 | 0 | 64527.55 | Planned Total Cost | [15 empty] | 64527.55
|  |  | JDH3-02-008-L-11-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-04-25 | 2026-05-05 | 2025-10-16 | 2025-10-28 | 0 | 0 | 64527.55 | Remaining Total Cost | [15 empty] | 64527.55
|  |  | JDH3-02-008-L-11-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-04-25 | 2026-05-05 | 2025-10-16 | 2025-10-28 | 0 | 0 | 64527.55 | Actual Total Cost
|  |  | JDH3-02-008-L-11-(ST)- Single Catchbasine Works |  | 2026-04-27 | 2026-05-07 | 2025-10-19 | 2025-10-30 | 0 | 0 | 66482.97 | Planned Total Cost | [15 empty] | 66482.97
|  |  | JDH3-02-008-L-11-(ST)- Single Catchbasine Works |  | 2026-04-27 | 2026-05-07 | 2025-10-19 | 2025-10-30 | 0 | 0 | 66482.97 | Remaining Total Cost | [15 empty] | 66482.97
|  |  | JDH3-02-008-L-11-(ST)- Single Catchbasine Works |  | 2026-04-27 | 2026-05-07 | 2025-10-19 | 2025-10-30 | 0 | 0 | 66482.97 | Actual Total Cost
|  |  | JDH3-02-008-L-11-(ST)- Double Catchbasine Works |  | 2026-04-29 | 2026-05-10 | 2025-10-21 | 2025-11-02 | 0 | 0 | 193188.3 | Planned Total Cost | [15 empty] | 186579.65 | 6608.65
|  |  | JDH3-02-008-L-11-(ST)- Double Catchbasine Works |  | 2026-04-29 | 2026-05-10 | 2025-10-21 | 2025-11-02 | 0 | 0 | 193188.3 | Remaining Total Cost | [15 empty] | 186579.65 | 6608.65
|  |  | JDH3-02-008-L-11-(ST)- Double Catchbasine Works |  | 2026-04-29 | 2026-05-10 | 2025-10-21 | 2025-11-02 | 0 | 0 | 193188.3 | Actual Total Cost
|  |  | JDH3-02-008-L-11-(ST)-PIPES ENCASEMENT |  | 2026-04-22 | 2026-04-28 | 2025-10-15 | 2025-10-21 | 0 | 0 | 20837 | Planned Total Cost | [15 empty] | 20837
|  |  | JDH3-02-008-L-11-(ST)-PIPES ENCASEMENT |  | 2026-04-22 | 2026-04-28 | 2025-10-15 | 2025-10-21 | 0 | 0 | 20837 | Remaining Total Cost | [15 empty] | 20837
|  |  | JDH3-02-008-L-11-(ST)-PIPES ENCASEMENT |  | 2026-04-22 | 2026-04-28 | 2025-10-15 | 2025-10-21 | 0 | 0 | 20837 | Actual Total Cost
|  |  | JDH3-02-008-L-11-TSE Network - TSE |  | 2026-05-09 | 2026-05-31 | 2025-10-30 | 2025-11-23 | 0 | 0 | 103657.82 | Planned Total Cost | [15 empty] | 5449.3 | 98208.52
|  |  | JDH3-02-008-L-11-TSE Network - TSE |  | 2026-05-09 | 2026-05-31 | 2025-10-30 | 2025-11-23 | 0 | 0 | 103657.82 | Remaining Total Cost | [15 empty] | 5449.3 | 98208.52
|  |  | JDH3-02-008-L-11-TSE Network - TSE |  | 2026-05-09 | 2026-05-31 | 2025-10-30 | 2025-11-23 | 0 | 0 | 103657.82 | Actual Total Cost
|  |  | JDH3-02-008-L-11-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-05-09 | 2026-05-31 | 2025-10-30 | 2025-11-23 | 0 | 0 | 86268.61 | Planned Total Cost | [15 empty] | 5449.3 | 80819.31
|  |  | JDH3-02-008-L-11-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-05-09 | 2026-05-31 | 2025-10-30 | 2025-11-23 | 0 | 0 | 86268.61 | Remaining Total Cost | [15 empty] | 5449.3 | 80819.31
|  |  | JDH3-02-008-L-11-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-05-09 | 2026-05-31 | 2025-10-30 | 2025-11-23 | 0 | 0 | 86268.61 | Actual Total Cost
|  |  | JDH3-02-008-L-11-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-25 | 2026-05-28 | 2025-11-16 | 2025-11-20 | 0 | 0 | 6465.8 | Planned Total Cost | [16 empty] | 6465.8
|  |  | JDH3-02-008-L-11-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-25 | 2026-05-28 | 2025-11-16 | 2025-11-20 | 0 | 0 | 6465.8 | Remaining Total Cost | [16 empty] | 6465.8
|  |  | JDH3-02-008-L-11-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-25 | 2026-05-28 | 2025-11-16 | 2025-11-20 | 0 | 0 | 6465.8 | Actual Total Cost
|  |  | JDH3-02-008-L-11-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-05-25 | 2026-05-28 | 2025-11-16 | 2025-11-20 | 0 | 0 | 7444.14 | Planned Total Cost | [16 empty] | 7444.14
|  |  | JDH3-02-008-L-11-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-05-25 | 2026-05-28 | 2025-11-16 | 2025-11-20 | 0 | 0 | 7444.14 | Remaining Total Cost | [16 empty] | 7444.14
|  |  | JDH3-02-008-L-11-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-05-25 | 2026-05-28 | 2025-11-16 | 2025-11-20 | 0 | 0 | 7444.14 | Actual Total Cost
|  |  | JDH3-02-008-L-11-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-05-18 | 2026-05-31 | 2025-11-09 | 2025-11-23 | 0 | 0 | 3479.28 | Planned Total Cost | [16 empty] | 3479.28
|  |  | JDH3-02-008-L-11-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-05-18 | 2026-05-31 | 2025-11-09 | 2025-11-23 | 0 | 0 | 3479.28 | Remaining Total Cost | [16 empty] | 3479.28
|  |  | JDH3-02-008-L-11-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-05-18 | 2026-05-31 | 2025-11-09 | 2025-11-23 | 0 | 0 | 3479.28 | Actual Total Cost
|  |  | JDH3-02-008-L-11-Potable Water Network - WT |  | 2026-06-01 | 2026-06-11 | 2025-11-23 | 2025-12-04 | 0 | 0 | 71276.11 | Planned Total Cost | [16 empty] | 65619.91 | 5656.2
|  |  | JDH3-02-008-L-11-Potable Water Network - WT |  | 2026-06-01 | 2026-06-11 | 2025-11-23 | 2025-12-04 | 0 | 0 | 71276.11 | Remaining Total Cost | [16 empty] | 65619.91 | 5656.2
|  |  | JDH3-02-008-L-11-Potable Water Network - WT |  | 2026-06-01 | 2026-06-11 | 2025-11-23 | 2025-12-04 | 0 | 0 | 71276.11 | Actual Total Cost
|  |  | JDH3-02-008-L-11-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-06-01 | 2026-06-11 | 2025-11-23 | 2025-12-04 | 0 | 0 | 7797.29 | Planned Total Cost | [16 empty] | 6484.1 | 1313.19
|  |  | JDH3-02-008-L-11-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-06-01 | 2026-06-11 | 2025-11-23 | 2025-12-04 | 0 | 0 | 7797.29 | Remaining Total Cost | [16 empty] | 6484.1 | 1313.19
|  |  | JDH3-02-008-L-11-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-06-01 | 2026-06-11 | 2025-11-23 | 2025-12-04 | 0 | 0 | 7797.29 | Actual Total Cost
|  |  | JDH3-02-008-L-11-(WT)- Supply and install 3-out fire hydrant |  | 2026-06-03 | 2026-06-09 | 2025-11-25 | 2025-12-02 | 0 | 0 | 63478.82 | Planned Total Cost | [16 empty] | 59135.81 | 4343.01
|  |  | JDH3-02-008-L-11-(WT)- Supply and install 3-out fire hydrant |  | 2026-06-03 | 2026-06-09 | 2025-11-25 | 2025-12-02 | 0 | 0 | 63478.82 | Remaining Total Cost | [16 empty] | 59135.81 | 4343.01
|  |  | JDH3-02-008-L-11-(WT)- Supply and install 3-out fire hydrant |  | 2026-06-03 | 2026-06-09 | 2025-11-25 | 2025-12-02 | 0 | 0 | 63478.82 | Actual Total Cost
|  |  | Z02 |  | 2025-09-11 | 2025-11-02 | 01-Jul-25 A | 2026-04-15 | 1993-06-04 18:00 | 1993-06-04 18:14 | 1822795.54 | Planned Total Cost | [14 empty] | 34124.75 | 139012.81 |  |  |  | 155944.59 | 1461424.6 | 32288.79
|  |  | Z02 |  | 2025-09-11 | 2025-11-02 | 01-Jul-25 A | 2026-04-15 | 1993-06-04 18:00 | 1993-06-04 18:14 | 1822795.54 | Remaining Total Cost | [15 empty] | 139012.81 |  |  |  | 155944.59 | 1461424.6 | 32288.79
|  |  | Z02 |  | 2025-09-11 | 2025-11-02 | 01-Jul-25 A | 2026-04-15 | 1993-06-04 18:00 | 1993-06-04 18:14 | 1822795.54 | Actual Total Cost | [13 empty] | 34124.76
|  |  | RCB |  | 2025-09-11 | 2025-11-02 | 2026-02-22 | 2026-04-15 | 0 | 0 | 1426434.4 | Planned Total Cost | [19 empty] | 124721.05 | 1269424.56 | 32288.79
|  |  | RCB |  | 2025-09-11 | 2025-11-02 | 2026-02-22 | 2026-04-15 | 0 | 0 | 1426434.4 | Remaining Total Cost | [19 empty] | 124721.05 | 1269424.56 | 32288.79
|  |  | RCB |  | 2025-09-11 | 2025-11-02 | 2026-02-22 | 2026-04-15 | 0 | 0 | 1426434.4 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z02-Storm Network - ST |  | 2025-09-11 | 2025-11-02 | 2026-02-22 | 2026-04-15 | 0 | 0 | 1426434.4 | Planned Total Cost | [19 empty] | 124721.05 | 1269424.56 | 32288.79
|  |  | JDH3-02-008-RCB-Z02-Storm Network - ST |  | 2025-09-11 | 2025-11-02 | 2026-02-22 | 2026-04-15 | 0 | 0 | 1426434.4 | Remaining Total Cost | [19 empty] | 124721.05 | 1269424.56 | 32288.79
|  |  | JDH3-02-008-RCB-Z02-Storm Network - ST |  | 2025-09-11 | 2025-11-02 | 2026-02-22 | 2026-04-15 | 0 | 0 | 1426434.4 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z02-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-09-11 | 2025-10-20 | 2026-02-22 | 2026-04-02 | 0 | 0 | 521503.85 | Planned Total Cost | [19 empty] | 106908.29 | 406483.28 | 8112.28
|  |  | JDH3-02-008-RCB-Z02-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-09-11 | 2025-10-20 | 2026-02-22 | 2026-04-02 | 0 | 0 | 521503.85 | Remaining Total Cost | [19 empty] | 106908.29 | 406483.28 | 8112.28
|  |  | JDH3-02-008-RCB-Z02-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-09-11 | 2025-10-20 | 2026-02-22 | 2026-04-02 | 0 | 0 | 521503.85 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z02-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-09-17 | 2025-10-19 | 2026-02-28 | 2026-04-01 | 0 | 0 | 263240.01 | Planned Total Cost | [19 empty] | 6317.76 | 255418.03 | 1504.23
|  |  | JDH3-02-008-RCB-Z02-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-09-17 | 2025-10-19 | 2026-02-28 | 2026-04-01 | 0 | 0 | 263240.01 | Remaining Total Cost | [19 empty] | 6317.76 | 255418.03 | 1504.23
|  |  | JDH3-02-008-RCB-Z02-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-09-17 | 2025-10-19 | 2026-02-28 | 2026-04-01 | 0 | 0 | 263240.01 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z02-(ST)- Single Catchbasine Works |  | 2025-09-17 | 2025-11-02 | 2026-02-28 | 2026-04-15 | 0 | 0 | 261603.19 | Planned Total Cost | [19 empty] | 2943.04 | 235987.88 | 22672.28
|  |  | JDH3-02-008-RCB-Z02-(ST)- Single Catchbasine Works |  | 2025-09-17 | 2025-11-02 | 2026-02-28 | 2026-04-15 | 0 | 0 | 261603.19 | Remaining Total Cost | [19 empty] | 2943.04 | 235987.88 | 22672.28
|  |  | JDH3-02-008-RCB-Z02-(ST)- Single Catchbasine Works |  | 2025-09-17 | 2025-11-02 | 2026-02-28 | 2026-04-15 | 0 | 0 | 261603.19 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z02-(ST)- Double Catchbasine Works |  | 2025-09-17 | 2025-10-09 | 2026-02-28 | 2026-03-23 | 0 | 0 | 380087.35 | Planned Total Cost | [19 empty] | 8551.97 | 371535.38
|  |  | JDH3-02-008-RCB-Z02-(ST)- Double Catchbasine Works |  | 2025-09-17 | 2025-10-09 | 2026-02-28 | 2026-03-23 | 0 | 0 | 380087.35 | Remaining Total Cost | [19 empty] | 8551.97 | 371535.38
|  |  | JDH3-02-008-RCB-Z02-(ST)- Double Catchbasine Works |  | 2025-09-17 | 2025-10-09 | 2026-02-28 | 2026-03-23 | 0 | 0 | 380087.35 | Actual Total Cost
|  |  | L-48 |  | 2025-09-11 | 2025-10-01 | 12-Jul-25 A | 2025-10-14 | 0 | 0 | 29672.97 | Planned Total Cost | [15 empty] | 29672.97
|  |  | L-48 |  | 2025-09-11 | 2025-10-01 | 12-Jul-25 A | 2025-10-14 | 0 | 0 | 29672.97 | Remaining Total Cost | [15 empty] | 29672.97
|  |  | L-48 |  | 2025-09-11 | 2025-10-01 | 12-Jul-25 A | 2025-10-14 | 0 | 0 | 29672.97 | Actual Total Cost
|  |  | JDH3-02-008-L-48-TSE Network - TSE |  | 2025-09-20 | 2025-10-01 | 2025-10-02 | 2025-10-14 | 0 | 0 | 29672.97 | Planned Total Cost | [15 empty] | 29672.97
|  |  | JDH3-02-008-L-48-TSE Network - TSE |  | 2025-09-20 | 2025-10-01 | 2025-10-02 | 2025-10-14 | 0 | 0 | 29672.97 | Remaining Total Cost | [15 empty] | 29672.97
|  |  | JDH3-02-008-L-48-TSE Network - TSE |  | 2025-09-20 | 2025-10-01 | 2025-10-02 | 2025-10-14 | 0 | 0 | 29672.97 | Actual Total Cost
|  |  | JDH3-02-008-L-48-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-20 | 2025-10-01 | 2025-10-02 | 2025-10-14 | 0 | 0 | 24500.33 | Planned Total Cost | [15 empty] | 24500.33
|  |  | JDH3-02-008-L-48-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-20 | 2025-10-01 | 2025-10-02 | 2025-10-14 | 0 | 0 | 24500.33 | Remaining Total Cost | [15 empty] | 24500.33
|  |  | JDH3-02-008-L-48-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-20 | 2025-10-01 | 2025-10-02 | 2025-10-14 | 0 | 0 | 24500.33 | Actual Total Cost
|  |  | JDH3-02-008-L-48-(TSE)-Supply and install gate valves-100 mm |  | 2025-09-24 | 2025-09-28 | 2025-10-07 | 2025-10-11 | 0 | 0 | 5172.64 | Planned Total Cost | [15 empty] | 5172.64
|  |  | JDH3-02-008-L-48-(TSE)-Supply and install gate valves-100 mm |  | 2025-09-24 | 2025-09-28 | 2025-10-07 | 2025-10-11 | 0 | 0 | 5172.64 | Remaining Total Cost | [15 empty] | 5172.64
|  |  | JDH3-02-008-L-48-(TSE)-Supply and install gate valves-100 mm |  | 2025-09-24 | 2025-09-28 | 2025-10-07 | 2025-10-11 | 0 | 0 | 5172.64 | Actual Total Cost
|  |  | L-49 |  | 2025-09-11 | 2025-10-06 | 23-Jul-25 A | 2025-10-09 | 1993-06-04 18:00 | 1993-06-04 18:14 | 49121.74 | Planned Total Cost | [14 empty] | 34124.75 | 14996.99
|  |  | L-49 |  | 2025-09-11 | 2025-10-06 | 23-Jul-25 A | 2025-10-09 | 1993-06-04 18:00 | 1993-06-04 18:14 | 49121.74 | Remaining Total Cost | [15 empty] | 14996.99
|  |  | L-49 |  | 2025-09-11 | 2025-10-06 | 23-Jul-25 A | 2025-10-09 | 1993-06-04 18:00 | 1993-06-04 18:14 | 49121.74 | Actual Total Cost | [13 empty] | 34124.76
|  |  | JDH3-02-008-L-49-TSE Network - TSE |  | 2025-09-20 | 2025-10-06 | 20-Aug-25 A | 2025-10-09 | 1993-06-04 18:00 | 1993-06-04 18:14 | 49121.74 | Planned Total Cost | [14 empty] | 34124.75 | 14996.99
|  |  | JDH3-02-008-L-49-TSE Network - TSE |  | 2025-09-20 | 2025-10-06 | 20-Aug-25 A | 2025-10-09 | 1993-06-04 18:00 | 1993-06-04 18:14 | 49121.74 | Remaining Total Cost | [15 empty] | 14996.99
|  |  | JDH3-02-008-L-49-TSE Network - TSE |  | 2025-09-20 | 2025-10-06 | 20-Aug-25 A | 2025-10-09 | 1993-06-04 18:00 | 1993-06-04 18:14 | 49121.74 | Actual Total Cost | [13 empty] | 34124.76
|  |  | JDH3-02-008-L-49-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-20 | 2025-10-06 | 20-Aug-25 A | 2025-10-09 | 1993-06-04 18:00 | 1993-06-04 18:14 | 42655.94 | Planned Total Cost | [14 empty] | 34124.75 | 8531.19
|  |  | JDH3-02-008-L-49-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-20 | 2025-10-06 | 20-Aug-25 A | 2025-10-09 | 1993-06-04 18:00 | 1993-06-04 18:14 | 42655.94 | Remaining Total Cost | [15 empty] | 8531.19
|  |  | JDH3-02-008-L-49-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-20 | 2025-10-06 | 20-Aug-25 A | 2025-10-09 | 1993-06-04 18:00 | 1993-06-04 18:14 | 42655.94 | Actual Total Cost | [13 empty] | 34124.76
|  |  | JDH3-02-008-L-49-(TSE)-Supply and install gate valves-100 mm |  | 2025-09-25 | 2025-09-29 | 2025-10-02 | 2025-10-06 | 0 | 0 | 6465.8 | Planned Total Cost | [15 empty] | 6465.8
|  |  | JDH3-02-008-L-49-(TSE)-Supply and install gate valves-100 mm |  | 2025-09-25 | 2025-09-29 | 2025-10-02 | 2025-10-06 | 0 | 0 | 6465.8 | Remaining Total Cost | [15 empty] | 6465.8
|  |  | JDH3-02-008-L-49-(TSE)-Supply and install gate valves-100 mm |  | 2025-09-25 | 2025-09-29 | 2025-10-02 | 2025-10-06 | 0 | 0 | 6465.8 | Actual Total Cost
|  |  | L-50 |  | 2025-09-11 | 2025-10-09 | 01-Jul-25 A | 2025-10-22 | 0 | 0 | 94342.85 | Planned Total Cost | [15 empty] | 94342.85
|  |  | L-50 |  | 2025-09-11 | 2025-10-09 | 01-Jul-25 A | 2025-10-22 | 0 | 0 | 94342.85 | Remaining Total Cost | [15 empty] | 94342.85
|  |  | L-50 |  | 2025-09-11 | 2025-10-09 | 01-Jul-25 A | 2025-10-22 | 0 | 0 | 94342.85 | Actual Total Cost
|  |  | JDH3-02-008-L-50-TSE Network - TSE |  | 2025-09-20 | 2025-10-09 | 2025-10-02 | 2025-10-22 | 0 | 0 | 94342.85 | Planned Total Cost | [15 empty] | 94342.85
|  |  | JDH3-02-008-L-50-TSE Network - TSE |  | 2025-09-20 | 2025-10-09 | 2025-10-02 | 2025-10-22 | 0 | 0 | 94342.85 | Remaining Total Cost | [15 empty] | 94342.85
|  |  | JDH3-02-008-L-50-TSE Network - TSE |  | 2025-09-20 | 2025-10-09 | 2025-10-02 | 2025-10-22 | 0 | 0 | 94342.85 | Actual Total Cost
|  |  | JDH3-02-008-L-50-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-20 | 2025-10-09 | 2025-10-02 | 2025-10-22 | 0 | 0 | 48385.79 | Planned Total Cost | [15 empty] | 48385.79
|  |  | JDH3-02-008-L-50-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-20 | 2025-10-09 | 2025-10-02 | 2025-10-22 | 0 | 0 | 48385.79 | Remaining Total Cost | [15 empty] | 48385.79
|  |  | JDH3-02-008-L-50-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-20 | 2025-10-09 | 2025-10-02 | 2025-10-22 | 0 | 0 | 48385.79 | Actual Total Cost
|  |  | JDH3-02-008-L-50-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-09-23 | 2025-10-08 | 2025-10-06 | 2025-10-21 | 0 | 0 | 40804.62 | Planned Total Cost | [15 empty] | 40804.62
|  |  | JDH3-02-008-L-50-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-09-23 | 2025-10-08 | 2025-10-06 | 2025-10-21 | 0 | 0 | 40804.62 | Remaining Total Cost | [15 empty] | 40804.62
|  |  | JDH3-02-008-L-50-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-09-23 | 2025-10-08 | 2025-10-06 | 2025-10-21 | 0 | 0 | 40804.62 | Actual Total Cost
|  |  | JDH3-02-008-L-50-(TSE)-Supply and install gate valves-100 mm |  | 2025-10-02 | 2025-10-06 | 2025-10-15 | 2025-10-19 | 0 | 0 | 2586.32 | Planned Total Cost | [15 empty] | 2586.32
|  |  | JDH3-02-008-L-50-(TSE)-Supply and install gate valves-100 mm |  | 2025-10-02 | 2025-10-06 | 2025-10-15 | 2025-10-19 | 0 | 0 | 2586.32 | Remaining Total Cost | [15 empty] | 2586.32
|  |  | JDH3-02-008-L-50-(TSE)-Supply and install gate valves-100 mm |  | 2025-10-02 | 2025-10-06 | 2025-10-15 | 2025-10-19 | 0 | 0 | 2586.32 | Actual Total Cost
|  |  | JDH3-02-008-L-50-(TSE)-Supply and install gate valves-250 mm |  | 2025-10-02 | 2025-10-06 | 2025-10-15 | 2025-10-19 | 0 | 0 | 2566.11 | Planned Total Cost | [15 empty] | 2566.11
|  |  | JDH3-02-008-L-50-(TSE)-Supply and install gate valves-250 mm |  | 2025-10-02 | 2025-10-06 | 2025-10-15 | 2025-10-19 | 0 | 0 | 2566.11 | Remaining Total Cost | [15 empty] | 2566.11
|  |  | JDH3-02-008-L-50-(TSE)-Supply and install gate valves-250 mm |  | 2025-10-02 | 2025-10-06 | 2025-10-15 | 2025-10-19 | 0 | 0 | 2566.11 | Actual Total Cost
|  |  | L-47 |  | 2025-09-11 | 2025-10-16 | 16-Jul-25 A | 2026-03-26 | 0 | 0 | 223223.58 | Planned Total Cost | [19 empty] | 31223.54 | 192000.04
|  |  | L-47 |  | 2025-09-11 | 2025-10-16 | 16-Jul-25 A | 2026-03-26 | 0 | 0 | 223223.58 | Remaining Total Cost | [19 empty] | 31223.54 | 192000.04
|  |  | L-47 |  | 2025-09-11 | 2025-10-16 | 16-Jul-25 A | 2026-03-26 | 0 | 0 | 223223.58 | Actual Total Cost
|  |  | JDH3-02-008-L-47-TSE Network - TSE |  | 2025-09-15 | 2025-10-16 | 2026-02-22 | 2026-03-26 | 0 | 0 | 223223.58 | Planned Total Cost | [19 empty] | 31223.54 | 192000.04
|  |  | JDH3-02-008-L-47-TSE Network - TSE |  | 2025-09-15 | 2025-10-16 | 2026-02-22 | 2026-03-26 | 0 | 0 | 223223.58 | Remaining Total Cost | [19 empty] | 31223.54 | 192000.04
|  |  | JDH3-02-008-L-47-TSE Network - TSE |  | 2025-09-15 | 2025-10-16 | 2026-02-22 | 2026-03-26 | 0 | 0 | 223223.58 | Actual Total Cost
|  |  | JDH3-02-008-L-47-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-15 | 2025-10-13 | 2026-02-22 | 2026-03-23 | 0 | 0 | 48204.95 | Planned Total Cost | [19 empty] | 11729.87 | 36475.08
|  |  | JDH3-02-008-L-47-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-15 | 2025-10-13 | 2026-02-22 | 2026-03-23 | 0 | 0 | 48204.95 | Remaining Total Cost | [19 empty] | 11729.87 | 36475.08
|  |  | JDH3-02-008-L-47-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-15 | 2025-10-13 | 2026-02-22 | 2026-03-23 | 0 | 0 | 48204.95 | Actual Total Cost
|  |  | JDH3-02-008-L-47-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-09-18 | 2025-10-16 | 2026-02-25 | 2026-03-26 | 0 | 0 | 149951.29 | Planned Total Cost | [19 empty] | 19493.67 | 130457.62
|  |  | JDH3-02-008-L-47-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-09-18 | 2025-10-16 | 2026-02-25 | 2026-03-26 | 0 | 0 | 149951.29 | Remaining Total Cost | [19 empty] | 19493.67 | 130457.62
|  |  | JDH3-02-008-L-47-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-09-18 | 2025-10-16 | 2026-02-25 | 2026-03-26 | 0 | 0 | 149951.29 | Actual Total Cost
|  |  | JDH3-02-008-L-47-(TSE)-Supply and install gate valves-100 mm |  | 2025-10-06 | 2025-10-09 | 2026-03-15 | 2026-03-19 | 0 | 0 | 3879.48 | Planned Total Cost | [20 empty] | 3879.48
|  |  | JDH3-02-008-L-47-(TSE)-Supply and install gate valves-100 mm |  | 2025-10-06 | 2025-10-09 | 2026-03-15 | 2026-03-19 | 0 | 0 | 3879.48 | Remaining Total Cost | [20 empty] | 3879.48
|  |  | JDH3-02-008-L-47-(TSE)-Supply and install gate valves-100 mm |  | 2025-10-06 | 2025-10-09 | 2026-03-15 | 2026-03-19 | 0 | 0 | 3879.48 | Actual Total Cost
|  |  | JDH3-02-008-L-47-(TSE)-Supply and install gate valves-250 mm |  | 2025-10-06 | 2025-10-09 | 2026-03-15 | 2026-03-19 | 0 | 0 | 10264.45 | Planned Total Cost | [20 empty] | 10264.45
|  |  | JDH3-02-008-L-47-(TSE)-Supply and install gate valves-250 mm |  | 2025-10-06 | 2025-10-09 | 2026-03-15 | 2026-03-19 | 0 | 0 | 10264.45 | Remaining Total Cost | [20 empty] | 10264.45
|  |  | JDH3-02-008-L-47-(TSE)-Supply and install gate valves-250 mm |  | 2025-10-06 | 2025-10-09 | 2026-03-15 | 2026-03-19 | 0 | 0 | 10264.45 | Actual Total Cost
|  |  | JDH3-02-008-L-47-(TSE)-Supply and install of Air valves-50 mm. |  | 2025-10-06 | 2025-10-09 | 2026-03-15 | 2026-03-19 | 0 | 0 | 7444.14 | Planned Total Cost | [20 empty] | 7444.14
|  |  | JDH3-02-008-L-47-(TSE)-Supply and install of Air valves-50 mm. |  | 2025-10-06 | 2025-10-09 | 2026-03-15 | 2026-03-19 | 0 | 0 | 7444.14 | Remaining Total Cost | [20 empty] | 7444.14
|  |  | JDH3-02-008-L-47-(TSE)-Supply and install of Air valves-50 mm. |  | 2025-10-06 | 2025-10-09 | 2026-03-15 | 2026-03-19 | 0 | 0 | 7444.14 | Actual Total Cost
|  |  | JDH3-02-008-L-47-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2025-09-23 | 2025-10-12 | 2026-03-02 | 2026-03-22 | 0 | 0 | 3479.28 | Planned Total Cost | [20 empty] | 3479.28
|  |  | JDH3-02-008-L-47-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2025-09-23 | 2025-10-12 | 2026-03-02 | 2026-03-22 | 0 | 0 | 3479.28 | Remaining Total Cost | [20 empty] | 3479.28
|  |  | JDH3-02-008-L-47-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2025-09-23 | 2025-10-12 | 2026-03-02 | 2026-03-22 | 0 | 0 | 3479.28 | Actual Total Cost
|  |  | Z02-1 |  | 2024-08-27 | 2025-05-11 | 11-Mar-25 A | 2026-02-22 | 4698000.66 | 4698000.55 | 10537672.95 | Planned Total Cost |  |  | 215538.47 | 722974.32 | 68065.48 | 856394.51 | 1381958.74 | 1181753.33 | 183147.83 | 182910.86 |  |  |  |  | 131225.56 | 2168579.17 | 813156.7 | 548915.98 | 1798494.88 | 284557.12
|  |  | Z02-1 |  | 2024-08-27 | 2025-05-11 | 11-Mar-25 A | 2026-02-22 | 4698000.66 | 4698000.55 | 10537672.95 | Remaining Total Cost | [15 empty] | 2255485.37 | 765572.47 | 624578.19 | 1909479.14 | 284557.12
|  |  | Z02-1 |  | 2024-08-27 | 2025-05-11 | 11-Mar-25 A | 2026-02-22 | 4698000.66 | 4698000.55 | 10537672.95 | Actual Total Cost | [8 empty] | 54072.25 | 827114.9 | 628538.25 | 607787.44 | 412625.87 | 1059826.2 | 1071092.99 | 36942.66
|  |  | L-69 |  | 2024-08-27 | 2025-04-10 | 01-Apr-25 A | 2026-01-20 | 1106032.32 | 1106032.31 | 2160800.32 | Planned Total Cost |  |  | 215538.47 | 722974.32 | 68065.48 | [9 empty] | 94126.41 | 727611.13 | 133041.6 | 156314.85 | 43128.06
|  |  | L-69 |  | 2024-08-27 | 2025-04-10 | 01-Apr-25 A | 2026-01-20 | 1106032.32 | 1106032.31 | 2160800.32 | Remaining Total Cost | [15 empty] | 718283.74 | 137041.35 | 156314.85 | 43128.06
|  |  | L-69 |  | 2024-08-27 | 2025-04-10 | 01-Apr-25 A | 2026-01-20 | 1106032.32 | 1106032.31 | 2160800.32 | Actual Total Cost | [9 empty] | 52725.65 | 261889.38 | 79354.41 | 112343.82 | 324070.83 | 265944.89 | 9703.33
|  |  | JDH3-02-008-L-69-Sewage Network - SS |  | 2024-09-04 | 2024-10-09 | 10-Apr-25 A | 2025-10-09 | 2444-08-15 08:53 | 2444-08-15 08:53 | 233082.4 | Planned Total Cost |  |  | 192172.05 | 27554.58 | [11 empty] | 13355.77
|  |  | JDH3-02-008-L-69-Sewage Network - SS |  | 2024-09-04 | 2024-10-09 | 10-Apr-25 A | 2025-10-09 | 2444-08-15 08:53 | 2444-08-15 08:53 | 233082.4 | Remaining Total Cost | [15 empty] | 34161.03
|  |  | JDH3-02-008-L-69-Sewage Network - SS |  | 2024-09-04 | 2024-10-09 | 10-Apr-25 A | 2025-10-09 | 2444-08-15 08:53 | 2444-08-15 08:53 | 233082.4 | Actual Total Cost | [9 empty] | 45423.64 | 54918.7 | 13759.6 | 13183.08 | 68770.32 | 2759.88 | 106.15
|  |  | JDH3-02-008-L-69-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2024-09-04 | 2024-09-25 | 10-Apr-25 A | 2025-10-04 | 2163-12-07 20:10 | 2163-12-07 20:10 | 98611.94 | Planned Total Cost |  |  | 96401.84 | [12 empty] | 2210.1
|  |  | JDH3-02-008-L-69-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2024-09-04 | 2024-09-25 | 10-Apr-25 A | 2025-10-04 | 2163-12-07 20:10 | 2163-12-07 20:10 | 98611.94 | Remaining Total Cost | [15 empty] | 2210.1
|  |  | JDH3-02-008-L-69-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2024-09-04 | 2024-09-25 | 10-Apr-25 A | 2025-10-04 | 2163-12-07 20:10 | 2163-12-07 20:10 | 98611.94 | Actual Total Cost | [9 empty] | 35335.95 | 43553.61 | 9133.37 | 8378.91
|  |  | JDH3-02-008-L-69-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 1.51 to 2.5 m. |  | 2024-09-04 | 2024-09-15 | 02-Aug-25 A | 12-Aug-25 A | 2064-09-20 23:31 | 2064-09-20 23:46 | 60165.98 | Planned Total Cost |  |  | 60165.98
|  |  | JDH3-02-008-L-69-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 1.51 to 2.5 m. |  | 2024-09-04 | 2024-09-15 | 02-Aug-25 A | 12-Aug-25 A | 2064-09-20 23:31 | 2064-09-20 23:46 | 60165.98 | Remaining Total Cost
|  |  | JDH3-02-008-L-69-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 1.51 to 2.5 m. |  | 2024-09-04 | 2024-09-15 | 02-Aug-25 A | 12-Aug-25 A | 2064-09-20 23:31 | 2064-09-20 23:46 | 60165.98 | Actual Total Cost | [13 empty] | 60165.99
|  |  | JDH3-02-008-L-69-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2024-09-24 | 2024-10-09 | 10-Apr-25 A | 2025-10-09 | 2015-12-15 13:12 | 2015-12-15 12:58 | 74304.47 | Planned Total Cost |  |  | 35604.23 | 27554.58 | [11 empty] | 11145.67
|  |  | JDH3-02-008-L-69-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2024-09-24 | 2024-10-09 | 10-Apr-25 A | 2025-10-09 | 2015-12-15 13:12 | 2015-12-15 12:58 | 74304.47 | Remaining Total Cost | [15 empty] | 31950.93
|  |  | JDH3-02-008-L-69-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2024-09-24 | 2024-10-09 | 10-Apr-25 A | 2025-10-09 | 2015-12-15 13:12 | 2015-12-15 12:58 | 74304.47 | Actual Total Cost | [9 empty] | 10087.69 | 11365.08 | 4626.24 | 4804.17 | 8604.33 | 2759.88 | 106.15
|  |  | JDH3-02-008-L-69-Storm Network - ST |  | 2024-09-26 | 2024-11-04 | 28-Apr-25 A | 2025-10-23 | 754136.32 | 754136.3 | 1329971.33 | Planned Total Cost |  |  | 23366.42 | 695419.74 | [10 empty] | 32979.32 | 578205.84
|  |  | JDH3-02-008-L-69-Storm Network - ST |  | 2024-09-26 | 2024-11-04 | 28-Apr-25 A | 2025-10-23 | 754136.32 | 754136.3 | 1329971.33 | Remaining Total Cost | [15 empty] | 575835.02
|  |  | JDH3-02-008-L-69-Storm Network - ST |  | 2024-09-26 | 2024-11-04 | 28-Apr-25 A | 2025-10-23 | 754136.32 | 754136.3 | 1329971.33 | Actual Total Cost | [9 empty] | 7302.01 | 206970.68 | 65594.81 | 99160.74 | 208851.93 | 160923.32 | 5332.81
|  |  | JDH3-02-008-L-69-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-10-08 | 2024-10-22 | 2025-10-07 | 2025-10-22 | 0 | 0 | 171589.82 | Planned Total Cost | [15 empty] | 171589.82
|  |  | JDH3-02-008-L-69-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-10-08 | 2024-10-22 | 2025-10-07 | 2025-10-22 | 0 | 0 | 171589.82 | Remaining Total Cost | [15 empty] | 171589.82
|  |  | JDH3-02-008-L-69-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-10-08 | 2024-10-22 | 2025-10-07 | 2025-10-22 | 0 | 0 | 171589.82 | Actual Total Cost
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-09-26 | 2024-10-22 | 28-Apr-25 A | 2025-10-20 | 2112-08-29 00:14 | 2112-08-29 00:14 | 133522.46 | Planned Total Cost |  |  | 23366.42 | 51406.15 | [11 empty] | 58749.89
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-09-26 | 2024-10-22 | 28-Apr-25 A | 2025-10-20 | 2112-08-29 00:14 | 2112-08-29 00:14 | 133522.46 | Remaining Total Cost | [15 empty] | 55848.45
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-09-26 | 2024-10-22 | 28-Apr-25 A | 2025-10-20 | 2112-08-29 00:14 | 2112-08-29 00:14 | 133522.46 | Actual Total Cost | [9 empty] | 7302.01 | 67470.56 |  |  |  | 2775.29 | 126.15
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-10-10 | 2024-10-21 | 2025-10-09 | 2025-10-21 | 0 | 0 | 7571.29 | Planned Total Cost | [15 empty] | 7571.29
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-10-10 | 2024-10-21 | 2025-10-09 | 2025-10-21 | 0 | 0 | 7571.29 | Remaining Total Cost | [15 empty] | 7571.29
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-10-10 | 2024-10-21 | 2025-10-09 | 2025-10-21 | 0 | 0 | 7571.29 | Actual Total Cost
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2024-10-13 | 2024-10-23 | 17-Aug-25 A | 27-Aug-25 A | 1977-03-20 02:38 | 1977-03-20 02:38 | 28204.11 | Planned Total Cost |  |  |  | 28204.11
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2024-10-13 | 2024-10-23 | 17-Aug-25 A | 27-Aug-25 A | 1977-03-20 02:38 | 1977-03-20 02:38 | 28204.11 | Remaining Total Cost
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2024-10-13 | 2024-10-23 | 17-Aug-25 A | 27-Aug-25 A | 1977-03-20 02:38 | 1977-03-20 02:38 | 28204.11 | Actual Total Cost | [13 empty] | 28204.11
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2024-10-10 | 2024-10-21 | 14-Aug-25 A | 25-Aug-25 A | 1995-05-02 06:14 | 1995-05-02 06:14 | 34821.26 | Planned Total Cost |  |  |  | 34821.26
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2024-10-10 | 2024-10-21 | 14-Aug-25 A | 25-Aug-25 A | 1995-05-02 06:14 | 1995-05-02 06:14 | 34821.26 | Remaining Total Cost
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2024-10-10 | 2024-10-21 | 14-Aug-25 A | 25-Aug-25 A | 1995-05-02 06:14 | 1995-05-02 06:14 | 34821.26 | Actual Total Cost | [13 empty] | 34821.26
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2024-10-13 | 2024-10-23 | 17-Aug-25 A | 2025-10-02 | 2077-03-19 20:38 | 2077-03-19 20:38 | 67969.65 | Planned Total Cost |  |  |  | 67969.65
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2024-10-13 | 2024-10-23 | 17-Aug-25 A | 2025-10-02 | 2077-03-19 20:38 | 2077-03-19 20:38 | 67969.65 | Remaining Total Cost | [15 empty] | 3240.79
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2024-10-13 | 2024-10-23 | 17-Aug-25 A | 2025-10-02 | 2077-03-19 20:38 | 2077-03-19 20:38 | 67969.65 | Actual Total Cost | [13 empty] | 33239.02 | 31149.57 | 340.27
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 0.00 to 1.50 m |  | 2024-10-15 | 2024-10-26 | 20-Aug-25 A | 2025-10-02 | 2042-08-31 15:22 | 2042-08-31 15:07 | 64237.72 | Planned Total Cost |  |  |  | 51390.18 | [10 empty] | 12847.54
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 0.00 to 1.50 m |  | 2024-10-15 | 2024-10-26 | 20-Aug-25 A | 2025-10-02 | 2042-08-31 15:22 | 2042-08-31 15:07 | 64237.72 | Remaining Total Cost | [15 empty] | 12128.09
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 0.00 to 1.50 m |  | 2024-10-15 | 2024-10-26 | 20-Aug-25 A | 2025-10-02 | 2042-08-31 15:22 | 2042-08-31 15:07 | 64237.72 | Actual Total Cost | [13 empty] | 6089.87 | 43826.75 | 2193.01
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-10-01 | 2024-10-23 | 30-Jun-25 A | 20-Sep-25 A | 2205-05-11 11:31 | 2205-05-11 11:31 | 111531.48 | Planned Total Cost |  |  |  | 111531.48
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-10-01 | 2024-10-23 | 30-Jun-25 A | 20-Sep-25 A | 2205-05-11 11:31 | 2205-05-11 11:31 | 111531.48 | Remaining Total Cost
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-10-01 | 2024-10-23 | 30-Jun-25 A | 20-Sep-25 A | 2205-05-11 11:31 | 2205-05-11 11:31 | 111531.48 | Actual Total Cost | [11 empty] | 680.95 | 42915.87 | 47560.11 | 20374.55
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2024-10-03 | 2024-10-26 | 30-Jun-25 A | 2025-10-04 | 2041-01-31 02:24 | 2041-01-31 02:24 | 57257.89 | Planned Total Cost |  |  |  | 51532.1 | [11 empty] | 5725.79
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2024-10-03 | 2024-10-26 | 30-Jun-25 A | 2025-10-04 | 2041-01-31 02:24 | 2041-01-31 02:24 | 57257.89 | Remaining Total Cost | [15 empty] | 5725.79
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2024-10-03 | 2024-10-26 | 30-Jun-25 A | 2025-10-04 | 2041-01-31 02:24 | 2041-01-31 02:24 | 57257.89 | Actual Total Cost | [11 empty] | 715.72 | 45090.59 | 5725.79
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2024-10-06 | 2024-10-28 | 10-May-25 A | 24-Aug-25 A | 2265-10-04 22:19 | 2265-10-04 22:19 | 133592.93 | Planned Total Cost |  |  |  | 133592.93
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2024-10-06 | 2024-10-28 | 10-May-25 A | 24-Aug-25 A | 2265-10-04 22:19 | 2265-10-04 22:19 | 133592.93 | Remaining Total Cost
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2024-10-06 | 2024-10-28 | 10-May-25 A | 24-Aug-25 A | 2265-10-04 22:19 | 2265-10-04 22:19 | 133592.93 | Actual Total Cost | [10 empty] | 97689.84 | 9184.51 |  | 26718.58
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2024-10-08 | 2024-10-30 | 10-May-25 A | 26-Aug-25 A | 2109-02-26 11:02 | 2109-02-26 11:02 | 76394.46 | Planned Total Cost |  |  |  | 76394.46
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2024-10-08 | 2024-10-30 | 10-May-25 A | 26-Aug-25 A | 2109-02-26 11:02 | 2109-02-26 11:02 | 76394.46 | Remaining Total Cost
|  |  | JDH3-02-008-L-69-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2024-10-08 | 2024-10-30 | 10-May-25 A | 26-Aug-25 A | 2109-02-26 11:02 | 2109-02-26 11:02 | 76394.46 | Actual Total Cost | [10 empty] | 19098.61 | 36764.83 | 5252.12 | 15278.9
|  |  | JDH3-02-008-L-69-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-10-17 | 2024-10-28 | 17-Aug-25 A | 2025-10-14 | 2009-12-03 11:31 | 2009-12-03 11:31 | 83429.58 | Planned Total Cost |  |  |  | 41714.79 | [11 empty] | 41714.79
|  |  | JDH3-02-008-L-69-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-10-17 | 2024-10-28 | 17-Aug-25 A | 2025-10-14 | 2009-12-03 11:31 | 2009-12-03 11:31 | 83429.58 | Remaining Total Cost | [15 empty] | 43279.1
|  |  | JDH3-02-008-L-69-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-10-17 | 2024-10-28 | 17-Aug-25 A | 2025-10-14 | 2009-12-03 11:31 | 2009-12-03 11:31 | 83429.58 | Actual Total Cost | [13 empty] | 11214.28 | 27718.9 | 1217.3
|  |  | JDH3-02-008-L-69-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2024-10-03 | 2024-10-30 | 10-May-25 A | 2025-10-14 | 2071-06-11 15:50 | 2071-06-11 15:50 | 82125.99 | Planned Total Cost |  |  |  | 34559.64 | [10 empty] | 20131.78 | 27434.57
|  |  | JDH3-02-008-L-69-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2024-10-03 | 2024-10-30 | 10-May-25 A | 2025-10-14 | 2071-06-11 15:50 | 2071-06-11 15:50 | 82125.99 | Remaining Total Cost | [15 empty] | 19505.32
|  |  | JDH3-02-008-L-69-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2024-10-03 | 2024-10-30 | 10-May-25 A | 2025-10-14 | 2071-06-11 15:50 | 2071-06-11 15:50 | 82125.99 | Actual Total Cost | [10 empty] | 18790.74 | 14428.22 | 1340.68 |  | 27260.62 | 800.41
|  |  | JDH3-02-008-L-69-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2024-10-20 | 2024-10-30 | 16-Sep-25 A | 2025-10-16 | 1923-03-13 07:41 | 1923-03-13 07:41 | 33893.26 | Planned Total Cost | [15 empty] | 33893.26
|  |  | JDH3-02-008-L-69-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2024-10-20 | 2024-10-30 | 16-Sep-25 A | 2025-10-16 | 1923-03-13 07:41 | 1923-03-13 07:41 | 33893.26 | Remaining Total Cost | [15 empty] | 25419.94
|  |  | JDH3-02-008-L-69-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2024-10-20 | 2024-10-30 | 16-Sep-25 A | 2025-10-16 | 1923-03-13 07:41 | 1923-03-13 07:41 | 33893.26 | Actual Total Cost | [14 empty] | 7817.65 | 655.67
|  |  | JDH3-02-008-L-69-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2024-10-22 | 2024-11-04 | 10-May-25 A | 2025-10-19 | 1933-09-06 00:14 | 1933-09-06 | 18250.22 | Planned Total Cost |  |  |  | 12303.01 | [11 empty] | 5947.21
|  |  | JDH3-02-008-L-69-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2024-10-22 | 2024-11-04 | 10-May-25 A | 2025-10-19 | 1933-09-06 00:14 | 1933-09-06 | 18250.22 | Remaining Total Cost | [15 empty] | 5947.21
|  |  | JDH3-02-008-L-69-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2024-10-22 | 2024-11-04 | 10-May-25 A | 2025-10-19 | 1933-09-06 00:14 | 1933-09-06 | 18250.22 | Actual Total Cost | [10 empty] | 3920.94 | 3820.57 | 4561.49
|  |  | JDH3-02-008-L-69-(ST)- Single Catchbasine Works |  | 2024-10-22 | 2024-11-02 | 2025-10-09 | 2025-10-21 | 0 | 0 | 66482.97 | Planned Total Cost | [15 empty] | 66482.97
|  |  | JDH3-02-008-L-69-(ST)- Single Catchbasine Works |  | 2024-10-22 | 2024-11-02 | 2025-10-09 | 2025-10-21 | 0 | 0 | 66482.97 | Remaining Total Cost | [15 empty] | 66482.97
|  |  | JDH3-02-008-L-69-(ST)- Single Catchbasine Works |  | 2024-10-22 | 2024-11-02 | 2025-10-09 | 2025-10-21 | 0 | 0 | 66482.97 | Actual Total Cost
|  |  | JDH3-02-008-L-69-(ST)- Double Catchbasine Works |  | 2024-10-24 | 2024-11-04 | 2025-10-12 | 2025-10-23 | 0 | 0 | 159096.24 | Planned Total Cost | [15 empty] | 159096.24
|  |  | JDH3-02-008-L-69-(ST)- Double Catchbasine Works |  | 2024-10-24 | 2024-11-04 | 2025-10-12 | 2025-10-23 | 0 | 0 | 159096.24 | Remaining Total Cost | [15 empty] | 159096.24
|  |  | JDH3-02-008-L-69-(ST)- Double Catchbasine Works |  | 2024-10-24 | 2024-11-04 | 2025-10-12 | 2025-10-23 | 0 | 0 | 159096.24 | Actual Total Cost
|  |  | JDH3-02-008-L-69-TSE Network - TSE |  | 2024-11-05 | 2024-12-30 | 16-Aug-25 A | 2025-11-09 | 2100-02-15 12:29 | 2100-02-15 12:43 | 189670.91 | Planned Total Cost |  |  |  |  | 40271.35 | [10 empty] | 124931.87 | 24467.69
|  |  | JDH3-02-008-L-69-TSE Network - TSE |  | 2024-11-05 | 2024-12-30 | 16-Aug-25 A | 2025-11-09 | 2100-02-15 12:29 | 2100-02-15 12:43 | 189670.91 | Remaining Total Cost | [15 empty] | 88106.93 | 28467.45
|  |  | JDH3-02-008-L-69-TSE Network - TSE |  | 2024-11-05 | 2024-12-30 | 16-Aug-25 A | 2025-11-09 | 2100-02-15 12:29 | 2100-02-15 12:43 | 189670.91 | Actual Total Cost | [13 empty] | 40271.35 | 31453.18 | 1372
|  |  | JDH3-02-008-L-69-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-11-05 | 2024-12-24 | 2025-10-23 | 2025-11-09 | 0 | 0 | 9248.73 | Planned Total Cost | [15 empty] | 7676.45 | 1572.28
|  |  | JDH3-02-008-L-69-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-11-05 | 2024-12-24 | 2025-10-23 | 2025-11-09 | 0 | 0 | 9248.73 | Remaining Total Cost | [15 empty] | 7676.45 | 1572.28
|  |  | JDH3-02-008-L-69-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-11-05 | 2024-12-24 | 2025-10-23 | 2025-11-09 | 0 | 0 | 9248.73 | Actual Total Cost
|  |  | JDH3-02-008-L-69-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2024-11-07 | 2024-12-30 | 16-Aug-25 A | 2025-11-09 | 2100-02-15 12:29 | 2100-02-15 12:43 | 161085.39 | Planned Total Cost |  |  |  |  | 40271.35 | [10 empty] | 113081.95 | 7732.1
|  |  | JDH3-02-008-L-69-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2024-11-07 | 2024-12-30 | 16-Aug-25 A | 2025-11-09 | 2100-02-15 12:29 | 2100-02-15 12:43 | 161085.39 | Remaining Total Cost | [15 empty] | 76257.02 | 11731.85
|  |  | JDH3-02-008-L-69-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2024-11-07 | 2024-12-30 | 16-Aug-25 A | 2025-11-09 | 2100-02-15 12:29 | 2100-02-15 12:43 | 161085.39 | Actual Total Cost | [13 empty] | 40271.35 | 31453.18 | 1372
|  |  | JDH3-02-008-L-69-(TSE)-Supply and install gate valves-100 mm |  | 2024-12-16 | 2024-12-22 | 2025-10-30 | 2025-11-06 | 0 | 0 | 11638.44 | Planned Total Cost | [15 empty] | 2094.92 | 9543.52
|  |  | JDH3-02-008-L-69-(TSE)-Supply and install gate valves-100 mm |  | 2024-12-16 | 2024-12-22 | 2025-10-30 | 2025-11-06 | 0 | 0 | 11638.44 | Remaining Total Cost | [15 empty] | 2094.92 | 9543.52
|  |  | JDH3-02-008-L-69-(TSE)-Supply and install gate valves-100 mm |  | 2024-12-16 | 2024-12-22 | 2025-10-30 | 2025-11-06 | 0 | 0 | 11638.44 | Actual Total Cost
|  |  | JDH3-02-008-L-69-(TSE)-Supply and install gate valves-250 mm |  | 2024-12-16 | 2024-12-19 | 2025-10-30 | 2025-11-04 | 0 | 0 | 7698.34 | Planned Total Cost | [15 empty] | 2078.55 | 5619.79
|  |  | JDH3-02-008-L-69-(TSE)-Supply and install gate valves-250 mm |  | 2024-12-16 | 2024-12-19 | 2025-10-30 | 2025-11-04 | 0 | 0 | 7698.34 | Remaining Total Cost | [15 empty] | 2078.55 | 5619.79
|  |  | JDH3-02-008-L-69-(TSE)-Supply and install gate valves-250 mm |  | 2024-12-16 | 2024-12-19 | 2025-10-30 | 2025-11-04 | 0 | 0 | 7698.34 | Actual Total Cost
|  |  | JDH3-02-008-L-69-Potable Water Network - WT |  | 2024-11-12 | 2025-01-16 | 20-Aug-25 A | 2025-12-02 | 2118-09-11 02:38 | 2118-09-11 02:38 | 200106.54 | Planned Total Cost |  |  |  |  | 27794.13 | [9 empty] | 61147.09 | 11117.65 | 97453.55 | 2594.12
|  |  | JDH3-02-008-L-69-Potable Water Network - WT |  | 2024-11-12 | 2025-01-16 | 20-Aug-25 A | 2025-12-02 | 2118-09-11 02:38 | 2118-09-11 02:38 | 200106.54 | Remaining Total Cost | [15 empty] | 20180.76 | 97453.55 | 2594.12
|  |  | JDH3-02-008-L-69-Potable Water Network - WT |  | 2024-11-12 | 2025-01-16 | 20-Aug-25 A | 2025-12-02 | 2118-09-11 02:38 | 2118-09-11 02:38 | 200106.54 | Actual Total Cost | [13 empty] | 6177.23 | 70808.5 | 2892.38
|  |  | JDH3-02-008-L-69-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2024-11-12 | 2025-01-16 | 20-Aug-25 A | 2025-12-02 | 2118-09-11 02:38 | 2118-09-11 02:38 | 111176.52 | Planned Total Cost |  |  |  |  | 27794.13 | [9 empty] | 61147.09 | 11117.65 | 8523.53 | 2594.12
|  |  | JDH3-02-008-L-69-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2024-11-12 | 2025-01-16 | 20-Aug-25 A | 2025-12-02 | 2118-09-11 02:38 | 2118-09-11 02:38 | 111176.52 | Remaining Total Cost | [15 empty] | 20180.76 | 8523.53 | 2594.12
|  |  | JDH3-02-008-L-69-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2024-11-12 | 2025-01-16 | 20-Aug-25 A | 2025-12-02 | 2118-09-11 02:38 | 2118-09-11 02:38 | 111176.52 | Actual Total Cost | [13 empty] | 6177.23 | 70808.5 | 2892.38
|  |  | JDH3-02-008-L-69-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2025-01-04 | 2025-01-09 | 2025-11-18 | 2025-11-25 | 0 | 0 | 16755.62 | Planned Total Cost | [16 empty] | 16755.62
|  |  | JDH3-02-008-L-69-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2025-01-04 | 2025-01-09 | 2025-11-18 | 2025-11-25 | 0 | 0 | 16755.62 | Remaining Total Cost | [16 empty] | 16755.62
|  |  | JDH3-02-008-L-69-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2025-01-04 | 2025-01-09 | 2025-11-18 | 2025-11-25 | 0 | 0 | 16755.62 | Actual Total Cost
|  |  | JDH3-02-008-L-69-(WT)- Supply and install Wash-Out Valves -Diameter 100 mm. |  | 2025-01-04 | 2025-01-07 | 2025-11-18 | 2025-11-23 | 0 | 0 | 12981.12 | Planned Total Cost | [16 empty] | 12981.12
|  |  | JDH3-02-008-L-69-(WT)- Supply and install Wash-Out Valves -Diameter 100 mm. |  | 2025-01-04 | 2025-01-07 | 2025-11-18 | 2025-11-23 | 0 | 0 | 12981.12 | Remaining Total Cost | [16 empty] | 12981.12
|  |  | JDH3-02-008-L-69-(WT)- Supply and install Wash-Out Valves -Diameter 100 mm. |  | 2025-01-04 | 2025-01-07 | 2025-11-18 | 2025-11-23 | 0 | 0 | 12981.12 | Actual Total Cost
|  |  | JDH3-02-008-L-69-(WT)- Supply and install 3-out fire hydrant |  | 2024-12-25 | 2024-12-31 | 2025-11-09 | 2025-11-16 | 0 | 0 | 45342.02 | Planned Total Cost | [16 empty] | 45342.02
|  |  | JDH3-02-008-L-69-(WT)- Supply and install 3-out fire hydrant |  | 2024-12-25 | 2024-12-31 | 2025-11-09 | 2025-11-16 | 0 | 0 | 45342.02 | Remaining Total Cost | [16 empty] | 45342.02
|  |  | JDH3-02-008-L-69-(WT)- Supply and install 3-out fire hydrant |  | 2024-12-25 | 2024-12-31 | 2025-11-09 | 2025-11-16 | 0 | 0 | 45342.02 | Actual Total Cost
|  |  | JDH3-02-008-L-69-(WT)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipelines |  | 2024-12-28 | 2025-01-12 | 2025-11-11 | 2025-11-27 | 0 | 0 | 13851.27 | Planned Total Cost | [16 empty] | 13851.27
|  |  | JDH3-02-008-L-69-(WT)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipelines |  | 2024-12-28 | 2025-01-12 | 2025-11-11 | 2025-11-27 | 0 | 0 | 13851.27 | Remaining Total Cost | [16 empty] | 13851.27
|  |  | JDH3-02-008-L-69-(WT)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipelines |  | 2024-12-28 | 2025-01-12 | 2025-11-11 | 2025-11-27 | 0 | 0 | 13851.27 | Actual Total Cost
|  |  | JDH3-02-008-L-69-Street Lighting Network -SL |  | 2025-01-13 | 2025-04-08 | 2025-11-27 | 2026-01-18 | 0 | 0 | 134282.29 | Planned Total Cost | [16 empty] | 11120.35 | 82531.96 | 40629.98
|  |  | JDH3-02-008-L-69-Street Lighting Network -SL |  | 2025-01-13 | 2025-04-08 | 2025-11-27 | 2026-01-18 | 0 | 0 | 134282.29 | Remaining Total Cost | [16 empty] | 11120.35 | 82531.96 | 40629.98
|  |  | JDH3-02-008-L-69-Street Lighting Network -SL |  | 2025-01-13 | 2025-04-08 | 2025-11-27 | 2026-01-18 | 0 | 0 | 134282.29 | Actual Total Cost
|  |  | JDH3-02-008-L-69-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx25 mm² |  | 2025-01-13 | 2025-04-05 | 2025-11-27 | 2026-01-14 | 0 | 0 | 42770.58 | Planned Total Cost | [16 empty] | 11120.35 | 1710.82 | 29939.4
|  |  | JDH3-02-008-L-69-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx25 mm² |  | 2025-01-13 | 2025-04-05 | 2025-11-27 | 2026-01-14 | 0 | 0 | 42770.58 | Remaining Total Cost | [16 empty] | 11120.35 | 1710.82 | 29939.4
|  |  | JDH3-02-008-L-69-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx25 mm² |  | 2025-01-13 | 2025-04-05 | 2025-11-27 | 2026-01-14 | 0 | 0 | 42770.58 | Actual Total Cost
|  |  | JDH3-02-008-L-69-(STL)- Supply,install,connect and test single core PVC insulated copper 16mm2 |  | 2025-03-30 | 2025-04-05 | 2026-01-07 | 2026-01-14 | 0 | 0 | 6036.19 | Planned Total Cost | [18 empty] | 6036.19
|  |  | JDH3-02-008-L-69-(STL)- Supply,install,connect and test single core PVC insulated copper 16mm2 |  | 2025-03-30 | 2025-04-05 | 2026-01-07 | 2026-01-14 | 0 | 0 | 6036.19 | Remaining Total Cost | [18 empty] | 6036.19
|  |  | JDH3-02-008-L-69-(STL)- Supply,install,connect and test single core PVC insulated copper 16mm2 |  | 2025-03-30 | 2025-04-05 | 2026-01-07 | 2026-01-14 | 0 | 0 | 6036.19 | Actual Total Cost
|  |  | JDH3-02-008-L-69-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2025-01-18 | 2025-04-08 | 2025-12-02 | 2026-01-18 | 0 | 0 | 46543.89 | Planned Total Cost | [17 empty] | 41889.5 | 4654.39
|  |  | JDH3-02-008-L-69-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2025-01-18 | 2025-04-08 | 2025-12-02 | 2026-01-18 | 0 | 0 | 46543.89 | Remaining Total Cost | [17 empty] | 41889.5 | 4654.39
|  |  | JDH3-02-008-L-69-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2025-01-18 | 2025-04-08 | 2025-12-02 | 2026-01-18 | 0 | 0 | 46543.89 | Actual Total Cost
|  |  | JDH3-02-008-L-69-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-01-25 | 2025-01-26 | 2025-12-09 | 2025-12-11 | 0 | 0 | 7159.97 | Planned Total Cost | [17 empty] | 7159.97
|  |  | JDH3-02-008-L-69-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-01-25 | 2025-01-26 | 2025-12-09 | 2025-12-11 | 0 | 0 | 7159.97 | Remaining Total Cost | [17 empty] | 7159.97
|  |  | JDH3-02-008-L-69-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-01-25 | 2025-01-26 | 2025-12-09 | 2025-12-11 | 0 | 0 | 7159.97 | Actual Total Cost
|  |  | JDH3-02-008-L-69-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2025-01-22 | 2025-01-23 | 2025-12-07 | 2025-12-09 | 0 | 0 | 378.04 | Planned Total Cost | [17 empty] | 378.04
|  |  | JDH3-02-008-L-69-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2025-01-22 | 2025-01-23 | 2025-12-07 | 2025-12-09 | 0 | 0 | 378.04 | Remaining Total Cost | [17 empty] | 378.04
|  |  | JDH3-02-008-L-69-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2025-01-22 | 2025-01-23 | 2025-12-07 | 2025-12-09 | 0 | 0 | 378.04 | Actual Total Cost
|  |  | JDH3-02-008-L-69-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-01-20 | 2025-01-26 | 2025-12-04 | 2025-12-11 | 0 | 0 | 31393.63 | Planned Total Cost | [17 empty] | 31393.63
|  |  | JDH3-02-008-L-69-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-01-20 | 2025-01-26 | 2025-12-04 | 2025-12-11 | 0 | 0 | 31393.63 | Remaining Total Cost | [17 empty] | 31393.63
|  |  | JDH3-02-008-L-69-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-01-20 | 2025-01-26 | 2025-12-04 | 2025-12-11 | 0 | 0 | 31393.63 | Actual Total Cost
|  |  | JDH3-02-008-L-69-Telecommunications Network - TC |  | 2025-01-16 | 2025-04-10 | 2025-12-01 | 2026-01-20 | 0 | 0 | 73686.85 | Planned Total Cost | [17 empty] | 71188.78 | 2498.08
|  |  | JDH3-02-008-L-69-Telecommunications Network - TC |  | 2025-01-16 | 2025-04-10 | 2025-12-01 | 2026-01-20 | 0 | 0 | 73686.85 | Remaining Total Cost | [17 empty] | 71188.78 | 2498.08
|  |  | JDH3-02-008-L-69-Telecommunications Network - TC |  | 2025-01-16 | 2025-04-10 | 2025-12-01 | 2026-01-20 | 0 | 0 | 73686.85 | Actual Total Cost
|  |  | JDH3-02-008-L-69-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-01-16 | 2025-04-10 | 2025-12-01 | 2026-01-20 | 0 | 0 | 49961.57 | Planned Total Cost | [17 empty] | 47463.49 | 2498.08
|  |  | JDH3-02-008-L-69-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-01-16 | 2025-04-10 | 2025-12-01 | 2026-01-20 | 0 | 0 | 49961.57 | Remaining Total Cost | [17 empty] | 47463.49 | 2498.08
|  |  | JDH3-02-008-L-69-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-01-16 | 2025-04-10 | 2025-12-01 | 2026-01-20 | 0 | 0 | 49961.57 | Actual Total Cost
|  |  | JDH3-02-008-L-69-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-01-19 | 2025-01-25 | 2025-12-03 | 2025-12-10 | 0 | 0 | 23725.29 | Planned Total Cost | [17 empty] | 23725.29
|  |  | JDH3-02-008-L-69-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-01-19 | 2025-01-25 | 2025-12-03 | 2025-12-10 | 0 | 0 | 23725.29 | Remaining Total Cost | [17 empty] | 23725.29
|  |  | JDH3-02-008-L-69-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-01-19 | 2025-01-25 | 2025-12-03 | 2025-12-10 | 0 | 0 | 23725.29 | Actual Total Cost
|  |  | L-70 |  | 2024-08-27 | 2025-01-04 | 01-Jul-25 A | 2025-10-16 | 2087-01-25 15:36 | 2087-01-25 15:50 | 78488.46 | Planned Total Cost | [5 empty] | 14365.11 | [8 empty] | 31253.52 | 32869.83
|  |  | L-70 |  | 2024-08-27 | 2025-01-04 | 01-Jul-25 A | 2025-10-16 | 2087-01-25 15:36 | 2087-01-25 15:50 | 78488.46 | Remaining Total Cost | [15 empty] | 10160.8
|  |  | L-70 |  | 2024-08-27 | 2025-01-04 | 01-Jul-25 A | 2025-10-16 | 2087-01-25 15:36 | 2087-01-25 15:50 | 78488.46 | Actual Total Cost | [13 empty] | 3123.55 | 62274.4 | 2929.71
|  |  | JDH3-02-008-L-70-TSE Network - TSE |  | 2024-12-07 | 2025-01-04 | 23-Aug-25 A | 2025-10-16 | 2087-01-25 15:36 | 2087-01-25 15:50 | 78488.46 | Planned Total Cost | [5 empty] | 14365.11 | [8 empty] | 31253.52 | 32869.83
|  |  | JDH3-02-008-L-70-TSE Network - TSE |  | 2024-12-07 | 2025-01-04 | 23-Aug-25 A | 2025-10-16 | 2087-01-25 15:36 | 2087-01-25 15:50 | 78488.46 | Remaining Total Cost | [15 empty] | 10160.8
|  |  | JDH3-02-008-L-70-TSE Network - TSE |  | 2024-12-07 | 2025-01-04 | 23-Aug-25 A | 2025-10-16 | 2087-01-25 15:36 | 2087-01-25 15:50 | 78488.46 | Actual Total Cost | [13 empty] | 3123.55 | 62274.4 | 2929.71
|  |  | JDH3-02-008-L-70-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-12-07 | 2025-01-04 | 23-Aug-25 A | 2025-10-14 | 2087-01-25 15:36 | 2087-01-25 15:50 | 71825.56 | Planned Total Cost | [5 empty] | 14365.11 | [8 empty] | 31253.52 | 26206.92
|  |  | JDH3-02-008-L-70-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-12-07 | 2025-01-04 | 23-Aug-25 A | 2025-10-14 | 2087-01-25 15:36 | 2087-01-25 15:50 | 71825.56 | Remaining Total Cost | [15 empty] | 3497.9
|  |  | JDH3-02-008-L-70-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-12-07 | 2025-01-04 | 23-Aug-25 A | 2025-10-14 | 2087-01-25 15:36 | 2087-01-25 15:50 | 71825.56 | Actual Total Cost | [13 empty] | 3123.55 | 62274.4 | 2929.71
|  |  | JDH3-02-008-L-70-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2024-12-11 | 2024-12-30 | 2025-10-02 | 2025-10-16 | 0 | 0 | 197.1 | Planned Total Cost | [15 empty] | 197.1
|  |  | JDH3-02-008-L-70-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2024-12-11 | 2024-12-30 | 2025-10-02 | 2025-10-16 | 0 | 0 | 197.1 | Remaining Total Cost | [15 empty] | 197.1
|  |  | JDH3-02-008-L-70-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2024-12-11 | 2024-12-30 | 2025-10-02 | 2025-10-16 | 0 | 0 | 197.1 | Actual Total Cost
|  |  | JDH3-02-008-L-70-(TSE)-Supply and install gate valves-100 mm |  | 2024-12-24 | 2024-12-28 | 2025-10-09 | 2025-10-14 | 0 | 0 | 6465.8 | Planned Total Cost | [15 empty] | 6465.8
|  |  | JDH3-02-008-L-70-(TSE)-Supply and install gate valves-100 mm |  | 2024-12-24 | 2024-12-28 | 2025-10-09 | 2025-10-14 | 0 | 0 | 6465.8 | Remaining Total Cost | [15 empty] | 6465.8
|  |  | JDH3-02-008-L-70-(TSE)-Supply and install gate valves-100 mm |  | 2024-12-24 | 2024-12-28 | 2025-10-09 | 2025-10-14 | 0 | 0 | 6465.8 | Actual Total Cost
|  |  | L-71 |  | 2024-08-27 | 2025-05-11 | 01-Apr-25 A | 2026-02-01 | 1284272.91 | 1284272.86 | 2367985.18 | Planned Total Cost | [5 empty] | 15755.09 | 559793.42 | 592837.71 | 76542.68 | [6 empty] | 664449.69 | 201887 | 238789.47 | 17285.67 | 644.45
|  |  | L-71 |  | 2024-08-27 | 2025-05-11 | 01-Apr-25 A | 2026-02-01 | 1284272.91 | 1284272.86 | 2367985.18 | Remaining Total Cost | [15 empty] | 686453.74 | 140538.93 | 238789.47 | 17285.67 | 644.45
|  |  | L-71 |  | 2024-08-27 | 2025-05-11 | 01-Apr-25 A | 2026-02-01 | 1284272.91 | 1284272.86 | 2367985.18 | Actual Total Cost | [9 empty] | 316311.14 | 143639.95 | 421845.55 | 75612.9 | 191718.87 | 132560.23 | 2584.22
|  |  | JDH3-02-008-L-71-Sewage Network - SS |  | 2024-12-29 | 2025-01-20 | 06-Apr-25 A | 2025-10-11 | 235147.66 | 235147.64 | 328529.46 | Planned Total Cost | [5 empty] | 15755.09 | 246630.63 | [8 empty] | 66143.75
|  |  | JDH3-02-008-L-71-Sewage Network - SS |  | 2024-12-29 | 2025-01-20 | 06-Apr-25 A | 2025-10-11 | 235147.66 | 235147.64 | 328529.46 | Remaining Total Cost | [15 empty] | 93381.79
|  |  | JDH3-02-008-L-71-Sewage Network - SS |  | 2024-12-29 | 2025-01-20 | 06-Apr-25 A | 2025-10-11 | 235147.66 | 235147.64 | 328529.46 | Actual Total Cost | [9 empty] | 43695.96 | 42650.48 | 10042.79 | 9090 | 118042 | 11195.81 | 430.61
|  |  | JDH3-02-008-L-71-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2024-12-29 | 2025-01-13 | 06-Apr-25 A | 12-Aug-25 A | 2101-07-08 12:58 | 2101-07-08 12:43 | 73604.54 | Planned Total Cost | [5 empty] | 11835.58 | 61768.96
|  |  | JDH3-02-008-L-71-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2024-12-29 | 2025-01-13 | 06-Apr-25 A | 12-Aug-25 A | 2101-07-08 12:58 | 2101-07-08 12:43 | 73604.54 | Remaining Total Cost
|  |  | JDH3-02-008-L-71-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2024-12-29 | 2025-01-13 | 06-Apr-25 A | 12-Aug-25 A | 2101-07-08 12:58 | 2101-07-08 12:43 | 73604.54 | Actual Total Cost | [9 empty] | 6541.88 | 9025.01 | 9345.62 | 9090 | 39602.03
|  |  | JDH3-02-008-L-71-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2024-12-31 | 2025-01-20 | 08-Apr-25 A | 2025-10-02 | 2235-06-12 07:12 | 2235-06-12 06:58 | 122637.42 | Planned Total Cost | [5 empty] | 3919.51 | 118717.92
|  |  | JDH3-02-008-L-71-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2024-12-31 | 2025-01-20 | 08-Apr-25 A | 2025-10-02 | 2235-06-12 07:12 | 2235-06-12 06:58 | 122637.42 | Remaining Total Cost | [15 empty] | 117.13
|  |  | JDH3-02-008-L-71-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2024-12-31 | 2025-01-20 | 08-Apr-25 A | 2025-10-02 | 2235-06-12 07:12 | 2235-06-12 06:58 | 122637.42 | Actual Total Cost | [9 empty] | 21807.96 | 30048.51 | 697.17 |  | 63035.98 | 6673.98 | 256.69
|  |  | JDH3-02-008-L-71-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2025-01-04 | 2025-01-14 | 06-Apr-25 A | 2025-10-08 | 1914-04-10 08:24 | 1914-04-10 08:10 | 10428.7 | Planned Total Cost | [6 empty] | 5214.35 | [8 empty] | 5214.35
|  |  | JDH3-02-008-L-71-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2025-01-04 | 2025-01-14 | 06-Apr-25 A | 2025-10-08 | 1914-04-10 08:24 | 1914-04-10 08:10 | 10428.7 | Remaining Total Cost | [15 empty] | 5214.35
|  |  | JDH3-02-008-L-71-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2025-01-04 | 2025-01-14 | 06-Apr-25 A | 2025-10-08 | 1914-04-10 08:24 | 1914-04-10 08:10 | 10428.7 | Actual Total Cost | [9 empty] | 4236.65 | 977.69
|  |  | JDH3-02-008-L-71-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2025-01-06 | 2025-01-19 | 08-Apr-25 A | 2025-10-08 | 1967-10-23 03:50 | 1967-10-23 03:50 | 49536.32 | Planned Total Cost | [6 empty] | 24768.16 | [8 empty] | 24768.16
|  |  | JDH3-02-008-L-71-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2025-01-06 | 2025-01-19 | 08-Apr-25 A | 2025-10-08 | 1967-10-23 03:50 | 1967-10-23 03:50 | 49536.32 | Remaining Total Cost | [15 empty] | 24768.16
|  |  | JDH3-02-008-L-71-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2025-01-06 | 2025-01-19 | 08-Apr-25 A | 2025-10-08 | 1967-10-23 03:50 | 1967-10-23 03:50 | 49536.32 | Actual Total Cost | [9 empty] | 11109.47 | 2599.27 |  |  | 11059.42
|  |  | JDH3-02-008-L-71-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2025-01-08 | 2025-01-19 | 02-Aug-25 A | 2025-10-11 | 1924-09-30 07:26 | 1924-09-30 07:41 | 72322.48 | Planned Total Cost | [6 empty] | 36161.24 | [8 empty] | 36161.24
|  |  | JDH3-02-008-L-71-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2025-01-08 | 2025-01-19 | 02-Aug-25 A | 2025-10-11 | 1924-09-30 07:26 | 1924-09-30 07:41 | 72322.48 | Remaining Total Cost | [15 empty] | 63282.16
|  |  | JDH3-02-008-L-71-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2025-01-08 | 2025-01-19 | 02-Aug-25 A | 2025-10-11 | 1924-09-30 07:26 | 1924-09-30 07:41 | 72322.48 | Actual Total Cost | [13 empty] | 4344.57 | 4521.83 | 173.92
|  |  | JDH3-02-008-L-71-Storm Network - ST |  | 2025-01-08 | 2025-03-01 | 05-Apr-25 A | 2025-11-11 | 898663.24 | 898663.22 | 1532146.72 | Planned Total Cost | [6 empty] | 313162.79 | 592837.71 | [7 empty] | 585734.68 | 40411.54
|  |  | JDH3-02-008-L-71-Storm Network - ST |  | 2025-01-08 | 2025-03-01 | 05-Apr-25 A | 2025-11-11 | 898663.24 | 898663.22 | 1532146.72 | Remaining Total Cost | [15 empty] | 593071.95 | 40411.54
|  |  | JDH3-02-008-L-71-Storm Network - ST |  | 2025-01-08 | 2025-03-01 | 05-Apr-25 A | 2025-11-11 | 898663.24 | 898663.22 | 1532146.72 | Actual Total Cost | [9 empty] | 272615.19 | 100989.47 | 411802.76 | 66522.9 | 38013.29 | 8396.66 | 322.95
|  |  | JDH3-02-008-L-71-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-01-21 | 2025-02-11 | 2025-10-11 | 2025-11-02 | 0 | 0 | 237416.24 | Planned Total Cost | [15 empty] | 230293.75 | 7122.49
|  |  | JDH3-02-008-L-71-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-01-21 | 2025-02-11 | 2025-10-11 | 2025-11-02 | 0 | 0 | 237416.24 | Remaining Total Cost | [15 empty] | 230293.75 | 7122.49
|  |  | JDH3-02-008-L-71-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-01-21 | 2025-02-11 | 2025-10-11 | 2025-11-02 | 0 | 0 | 237416.24 | Actual Total Cost
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-01-25 | 2025-02-04 | 2025-10-14 | 2025-10-26 | 0 | 0 | 5273.5 | Planned Total Cost | [15 empty] | 5273.5
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-01-25 | 2025-02-04 | 2025-10-14 | 2025-10-26 | 0 | 0 | 5273.5 | Remaining Total Cost | [15 empty] | 5273.5
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-01-25 | 2025-02-04 | 2025-10-14 | 2025-10-26 | 0 | 0 | 5273.5 | Actual Total Cost
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-01-08 | 2025-02-06 | 05-Apr-25 A | 2025-10-26 | 1978-12-10 11:46 | 1978-12-10 11:46 | 40331.98 | Planned Total Cost | [6 empty] | 23067.82 | 8066.4 | [7 empty] | 9197.76
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-01-08 | 2025-02-06 | 05-Apr-25 A | 2025-10-26 | 1978-12-10 11:46 | 1978-12-10 11:46 | 40331.98 | Remaining Total Cost | [15 empty] | 11497.49
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-01-08 | 2025-02-06 | 05-Apr-25 A | 2025-10-26 | 1978-12-10 11:46 | 1978-12-10 11:46 | 40331.98 | Actual Total Cost | [9 empty] | 23067.83 |  |  |  | 723.09 | 4856.77 | 186.8
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2025-01-11 | 2025-01-21 | 11-Jun-25 A | 05-Jul-25 A | 1985-12-21 06:14 | 1985-12-21 06:14 | 31402.26 | Planned Total Cost | [6 empty] | 31402.26
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2025-01-11 | 2025-01-21 | 11-Jun-25 A | 05-Jul-25 A | 1985-12-21 06:14 | 1985-12-21 06:14 | 31402.26 | Remaining Total Cost
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2025-01-11 | 2025-01-21 | 11-Jun-25 A | 05-Jul-25 A | 1985-12-21 06:14 | 1985-12-21 06:14 | 31402.26 | Actual Total Cost | [11 empty] | 28948.96 | 2453.3
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-01-13 | 2025-02-09 | 06-Apr-25 A | 25-Aug-25 A | 2007-03-31 00:14 | 2007-03-31 00:14 | 39172.01 | Planned Total Cost | [6 empty] | 34079.65 | 5092.36
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-01-13 | 2025-02-09 | 06-Apr-25 A | 25-Aug-25 A | 2007-03-31 00:14 | 2007-03-31 00:14 | 39172.01 | Remaining Total Cost
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-01-13 | 2025-02-09 | 06-Apr-25 A | 25-Aug-25 A | 2007-03-31 00:14 | 2007-03-31 00:14 | 39172.01 | Actual Total Cost | [9 empty] | 27746.84 | 5533.05 | 799.76 |  | 5092.36
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-01-22 | 2025-02-11 | 11-Jun-25 A | 2025-10-30 | 2045-10-31 05:46 | 2045-10-31 06:00 | 103686.51 | Planned Total Cost | [6 empty] | 47937.7 | 5328.55 | [7 empty] | 50420.27
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-01-22 | 2025-02-11 | 11-Jun-25 A | 2025-10-30 | 2045-10-31 05:46 | 2045-10-31 06:00 | 103686.51 | Remaining Total Cost | [15 empty] | 50420.27
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-01-22 | 2025-02-11 | 11-Jun-25 A | 2025-10-30 | 2045-10-31 05:46 | 2045-10-31 06:00 | 103686.51 | Actual Total Cost | [11 empty] | 49104.63 | 4161.62
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-01-25 | 2025-02-08 | 06-Apr-25 A | 27-Aug-25 A | 2345-09-06 23:02 | 2345-09-06 23:17 | 162783.96 | Planned Total Cost | [6 empty] | 130227.17 | 32556.79
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-01-25 | 2025-02-08 | 06-Apr-25 A | 27-Aug-25 A | 2345-09-06 23:02 | 2345-09-06 23:17 | 162783.96 | Remaining Total Cost
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-01-25 | 2025-02-08 | 06-Apr-25 A | 27-Aug-25 A | 2345-09-06 23:02 | 2345-09-06 23:17 | 162783.96 | Actual Total Cost | [9 empty] | 92922.51 | 50422.27 | 14022.78 |  | 5416.4
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2025-01-27 | 2025-02-06 | 12-Apr-25 A | 29-May-25 A | 2251-09-24 05:17 | 2251-09-24 05:02 | 128468.22 | Planned Total Cost | [6 empty] | 32117.05 | 96351.16
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2025-01-27 | 2025-02-06 | 12-Apr-25 A | 29-May-25 A | 2251-09-24 05:17 | 2251-09-24 05:02 | 128468.22 | Remaining Total Cost
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2025-01-27 | 2025-02-06 | 12-Apr-25 A | 29-May-25 A | 2251-09-24 05:17 | 2251-09-24 05:02 | 128468.22 | Actual Total Cost | [9 empty] | 93540.92 | 34927.29
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2025-01-29 | 2025-02-09 | 11-Jun-25 A | 05-Jul-25 A | 2096-03-06 16:05 | 2096-03-06 16:05 | 71655.67 | Planned Total Cost | [6 empty] | 14331.13 | 57324.54
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2025-01-29 | 2025-02-09 | 11-Jun-25 A | 05-Jul-25 A | 2096-03-06 16:05 | 2096-03-06 16:05 | 71655.67 | Remaining Total Cost
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2025-01-29 | 2025-02-09 | 11-Jun-25 A | 05-Jul-25 A | 2096-03-06 16:05 | 2096-03-06 16:05 | 71655.67 | Actual Total Cost | [11 empty] | 66057.57 | 5598.1
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2025-02-01 | 2025-02-12 | 01-Jun-25 A | 14-Jul-25 A | 244646.5 | 244646.49 | 244646.5 | Planned Total Cost | [7 empty] | 244646.5
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2025-02-01 | 2025-02-12 | 01-Jun-25 A | 14-Jul-25 A | 244646.5 | 244646.49 | 244646.5 | Remaining Total Cost
|  |  | JDH3-02-008-L-71-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2025-02-01 | 2025-02-12 | 01-Jun-25 A | 14-Jul-25 A | 244646.5 | 244646.49 | 244646.5 | Actual Total Cost | [11 empty] | 221201.2 | 23445.29
|  |  | JDH3-02-008-L-71-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-02-06 | 2025-02-19 | 15-Apr-25 A | 2025-11-04 | 1933-01-09 00:58 | 1933-01-09 00:58 | 31286.09 | Planned Total Cost | [7 empty] | 12063.04 | [7 empty] | 16094.44 | 3128.61
|  |  | JDH3-02-008-L-71-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-02-06 | 2025-02-19 | 15-Apr-25 A | 2025-11-04 | 1933-01-09 00:58 | 1933-01-09 00:58 | 31286.09 | Remaining Total Cost | [15 empty] | 16094.44 | 3128.61
|  |  | JDH3-02-008-L-71-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-02-06 | 2025-02-19 | 15-Apr-25 A | 2025-11-04 | 1933-01-09 00:58 | 1933-01-09 00:58 | 31286.09 | Actual Total Cost | [9 empty] | 4539.85 | 5707.25 | 1475.45 | 340.49
|  |  | JDH3-02-008-L-71-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-02-09 | 2025-02-22 | 15-Apr-25 A | 2025-11-06 | 1989-12-15 04:48 | 1989-12-15 04:48 | 54750.66 | Planned Total Cost | [7 empty] | 32857.2 | [7 empty] | 16418.39 | 5475.07
|  |  | JDH3-02-008-L-71-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-02-09 | 2025-02-22 | 15-Apr-25 A | 2025-11-06 | 1989-12-15 04:48 | 1989-12-15 04:48 | 54750.66 | Remaining Total Cost | [15 empty] | 16418.39 | 5475.07
|  |  | JDH3-02-008-L-71-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-02-09 | 2025-02-22 | 15-Apr-25 A | 2025-11-06 | 1989-12-15 04:48 | 1989-12-15 04:48 | 54750.66 | Actual Total Cost | [9 empty] | 11976.7 | 1710.96 | 11463.84 | 7705.7
|  |  | JDH3-02-008-L-71-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-02-11 | 2025-02-22 | 26-Aug-25 A | 2025-11-04 | 1969-08-04 22:48 | 1969-08-04 22:34 | 50839.89 | Planned Total Cost | [7 empty] | 25419.95 | [7 empty] | 18429.46 | 6990.49
|  |  | JDH3-02-008-L-71-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-02-11 | 2025-02-22 | 26-Aug-25 A | 2025-11-04 | 1969-08-04 22:48 | 1969-08-04 22:34 | 50839.89 | Remaining Total Cost | [15 empty] | 18429.46 | 6990.49
|  |  | JDH3-02-008-L-71-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-02-11 | 2025-02-22 | 26-Aug-25 A | 2025-11-04 | 1969-08-04 22:48 | 1969-08-04 22:34 | 50839.89 | Actual Total Cost | [13 empty] | 25419.94
|  |  | JDH3-02-008-L-71-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-02-13 | 2025-02-26 | 15-Apr-25 A | 2025-11-09 | 2086-06-05 16:34 | 2086-06-05 16:34 | 86036.74 | Planned Total Cost | [7 empty] | 73131.23 | [7 empty] | 4301.84 | 8603.67
|  |  | JDH3-02-008-L-71-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-02-13 | 2025-02-26 | 15-Apr-25 A | 2025-11-09 | 2086-06-05 16:34 | 2086-06-05 16:34 | 86036.74 | Remaining Total Cost | [15 empty] | 9339.37 | 8603.67
|  |  | JDH3-02-008-L-71-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-02-13 | 2025-02-26 | 15-Apr-25 A | 2025-11-09 | 2086-06-05 16:34 | 2086-06-05 16:34 | 86036.74 | Actual Total Cost | [9 empty] | 18820.53 | 2688.65 | 18728.57 | 22818.4 | 1361.5 | 3539.89 | 136.15
|  |  | JDH3-02-008-L-71-(ST)- Single Catchbasine Works |  | 2025-02-13 | 2025-02-24 | 2025-10-11 | 2025-10-22 | 0 | 0 | 62572.21 | Planned Total Cost | [15 empty] | 62572.21
|  |  | JDH3-02-008-L-71-(ST)- Single Catchbasine Works |  | 2025-02-13 | 2025-02-24 | 2025-10-11 | 2025-10-22 | 0 | 0 | 62572.21 | Remaining Total Cost | [15 empty] | 62572.21
|  |  | JDH3-02-008-L-71-(ST)- Single Catchbasine Works |  | 2025-02-13 | 2025-02-24 | 2025-10-11 | 2025-10-22 | 0 | 0 | 62572.21 | Actual Total Cost
|  |  | JDH3-02-008-L-71-(ST)- Double Catchbasine Works |  | 2025-02-16 | 2025-03-01 | 2025-10-13 | 2025-11-11 | 0 | 0 | 181824.28 | Planned Total Cost | [15 empty] | 172733.06 | 9091.21
|  |  | JDH3-02-008-L-71-(ST)- Double Catchbasine Works |  | 2025-02-16 | 2025-03-01 | 2025-10-13 | 2025-11-11 | 0 | 0 | 181824.28 | Remaining Total Cost | [15 empty] | 172733.06 | 9091.21
|  |  | JDH3-02-008-L-71-(ST)- Double Catchbasine Works |  | 2025-02-16 | 2025-03-01 | 2025-10-13 | 2025-11-11 | 0 | 0 | 181824.28 | Actual Total Cost
|  |  | JDH3-02-008-L-71-TSE Network - TSE |  | 2025-03-02 | 2025-03-30 | 09-Aug-25 A | 2025-11-16 | 70005.94 | 2091-08-30 22:19 | 84301.64 | Planned Total Cost | [8 empty] | 76542.68 | [7 empty] | 7758.96
|  |  | JDH3-02-008-L-71-TSE Network - TSE |  | 2025-03-02 | 2025-03-30 | 09-Aug-25 A | 2025-11-16 | 70005.94 | 2091-08-30 22:19 | 84301.64 | Remaining Total Cost | [16 empty] | 14295.71
|  |  | JDH3-02-008-L-71-TSE Network - TSE |  | 2025-03-02 | 2025-03-30 | 09-Aug-25 A | 2025-11-16 | 70005.94 | 2091-08-30 22:19 | 84301.64 | Actual Total Cost | [13 empty] | 20578.07 | 47597.2 | 1830.66
|  |  | JDH3-02-008-L-71-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-03-02 | 2025-03-30 | 09-Aug-25 A | 2025-11-16 | 2091-08-30 22:34 | 2091-08-30 22:19 | 76542.68 | Planned Total Cost | [8 empty] | 76542.68
|  |  | JDH3-02-008-L-71-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-03-02 | 2025-03-30 | 09-Aug-25 A | 2025-11-16 | 2091-08-30 22:34 | 2091-08-30 22:19 | 76542.68 | Remaining Total Cost | [16 empty] | 6536.75
|  |  | JDH3-02-008-L-71-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-03-02 | 2025-03-30 | 09-Aug-25 A | 2025-11-16 | 2091-08-30 22:34 | 2091-08-30 22:19 | 76542.68 | Actual Total Cost | [13 empty] | 20578.07 | 47597.2 | 1830.66
|  |  | JDH3-02-008-L-71-(TSE)-Supply and install gate valves-100 mm |  | 2025-03-19 | 2025-03-23 | 2025-11-11 | 2025-11-16 | 0 | 0 | 7758.96 | Planned Total Cost | [16 empty] | 7758.96
|  |  | JDH3-02-008-L-71-(TSE)-Supply and install gate valves-100 mm |  | 2025-03-19 | 2025-03-23 | 2025-11-11 | 2025-11-16 | 0 | 0 | 7758.96 | Remaining Total Cost | [16 empty] | 7758.96
|  |  | JDH3-02-008-L-71-(TSE)-Supply and install gate valves-100 mm |  | 2025-03-19 | 2025-03-23 | 2025-11-11 | 2025-11-16 | 0 | 0 | 7758.96 | Actual Total Cost
|  |  | JDH3-02-008-L-71-Potable Water Network - WT |  | 2025-03-11 | 2025-04-19 | 25-Aug-25 A | 2025-12-06 | 2120-04-11 01:55 | 2120-04-11 01:41 | 175389.95 | Planned Total Cost | [15 empty] | 12571.26 | 153716.5 | 9102.19
|  |  | JDH3-02-008-L-71-Potable Water Network - WT |  | 2025-03-11 | 2025-04-19 | 25-Aug-25 A | 2025-12-06 | 2120-04-11 01:55 | 2120-04-11 01:41 | 175389.95 | Remaining Total Cost | [16 empty] | 85831.68 | 9102.19
|  |  | JDH3-02-008-L-71-Potable Water Network - WT |  | 2025-03-11 | 2025-04-19 | 25-Aug-25 A | 2025-12-06 | 2120-04-11 01:55 | 2120-04-11 01:41 | 175389.95 | Actual Total Cost | [13 empty] | 15085.52 | 65370.56
|  |  | JDH3-02-008-L-71-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-03-11 | 2025-04-19 | 25-Aug-25 A | 2025-12-06 | 2120-04-11 01:55 | 2120-04-11 01:41 | 100570.1 | Planned Total Cost | [15 empty] | 12571.26 | 78947.53 | 9051.31
|  |  | JDH3-02-008-L-71-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-03-11 | 2025-04-19 | 25-Aug-25 A | 2025-12-06 | 2120-04-11 01:55 | 2120-04-11 01:41 | 100570.1 | Remaining Total Cost | [16 empty] | 11062.71 | 9051.31
|  |  | JDH3-02-008-L-71-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-03-11 | 2025-04-19 | 25-Aug-25 A | 2025-12-06 | 2120-04-11 01:55 | 2120-04-11 01:41 | 100570.1 | Actual Total Cost | [13 empty] | 15085.52 | 65370.56
|  |  | JDH3-02-008-L-71-(WT)- Supply and install HDPE Pipes -225 mm depth from 0 to 1.5 m |  | 2025-03-31 | 2025-04-15 | 2025-11-16 | 2025-12-02 | 0 | 0 | 678.36 | Planned Total Cost | [16 empty] | 627.48 | 50.88
|  |  | JDH3-02-008-L-71-(WT)- Supply and install HDPE Pipes -225 mm depth from 0 to 1.5 m |  | 2025-03-31 | 2025-04-15 | 2025-11-16 | 2025-12-02 | 0 | 0 | 678.36 | Remaining Total Cost | [16 empty] | 627.48 | 50.88
|  |  | JDH3-02-008-L-71-(WT)- Supply and install HDPE Pipes -225 mm depth from 0 to 1.5 m |  | 2025-03-31 | 2025-04-15 | 2025-11-16 | 2025-12-02 | 0 | 0 | 678.36 | Actual Total Cost
|  |  | JDH3-02-008-L-71-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2025-04-07 | 2025-04-10 | 2025-11-23 | 2025-11-27 | 0 | 0 | 10662.67 | Planned Total Cost | [16 empty] | 10662.67
|  |  | JDH3-02-008-L-71-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2025-04-07 | 2025-04-10 | 2025-11-23 | 2025-11-27 | 0 | 0 | 10662.67 | Remaining Total Cost | [16 empty] | 10662.67
|  |  | JDH3-02-008-L-71-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2025-04-07 | 2025-04-10 | 2025-11-23 | 2025-11-27 | 0 | 0 | 10662.67 | Actual Total Cost
|  |  | JDH3-02-008-L-71-(WT)- Supply and install 3-out fire hydrant |  | 2025-04-02 | 2025-04-13 | 2025-11-18 | 2025-11-30 | 0 | 0 | 63478.82 | Planned Total Cost | [16 empty] | 63478.82
|  |  | JDH3-02-008-L-71-(WT)- Supply and install 3-out fire hydrant |  | 2025-04-02 | 2025-04-13 | 2025-11-18 | 2025-11-30 | 0 | 0 | 63478.82 | Remaining Total Cost | [16 empty] | 63478.82
|  |  | JDH3-02-008-L-71-(WT)- Supply and install 3-out fire hydrant |  | 2025-04-02 | 2025-04-13 | 2025-11-18 | 2025-11-30 | 0 | 0 | 63478.82 | Actual Total Cost
|  |  | JDH3-02-008-L-71-Street Lighting Network -SL |  | 2025-04-20 | 2025-05-11 | 2025-12-06 | 2026-02-01 | 0 | 0 | 183740.26 | Planned Total Cost | [17 empty] | 165810.14 | 17285.67 | 644.45
|  |  | JDH3-02-008-L-71-Street Lighting Network -SL |  | 2025-04-20 | 2025-05-11 | 2025-12-06 | 2026-02-01 | 0 | 0 | 183740.26 | Remaining Total Cost | [17 empty] | 165810.14 | 17285.67 | 644.45
|  |  | JDH3-02-008-L-71-Street Lighting Network -SL |  | 2025-04-20 | 2025-05-11 | 2025-12-06 | 2026-02-01 | 0 | 0 | 183740.26 | Actual Total Cost
|  |  | JDH3-02-008-L-71-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx25 mm² |  | 2025-04-20 | 2025-05-07 | 2025-12-06 | 2026-01-31 | 0 | 0 | 46260.92 | Planned Total Cost | [17 empty] | 41634.83 | 4626.09
|  |  | JDH3-02-008-L-71-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx25 mm² |  | 2025-04-20 | 2025-05-07 | 2025-12-06 | 2026-01-31 | 0 | 0 | 46260.92 | Remaining Total Cost | [17 empty] | 41634.83 | 4626.09
|  |  | JDH3-02-008-L-71-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx25 mm² |  | 2025-04-20 | 2025-05-07 | 2025-12-06 | 2026-01-31 | 0 | 0 | 46260.92 | Actual Total Cost
|  |  | JDH3-02-008-L-71-(STL)- Supply,install,connect and test single core PVC insulated copper 16mm2 |  | 2025-04-28 | 2025-05-04 | 2025-12-14 | 2026-01-27 | 0 | 0 | 6528.78 | Planned Total Cost | [17 empty] | 5223.03 | 1305.76
|  |  | JDH3-02-008-L-71-(STL)- Supply,install,connect and test single core PVC insulated copper 16mm2 |  | 2025-04-28 | 2025-05-04 | 2025-12-14 | 2026-01-27 | 0 | 0 | 6528.78 | Remaining Total Cost | [17 empty] | 5223.03 | 1305.76
|  |  | JDH3-02-008-L-71-(STL)- Supply,install,connect and test single core PVC insulated copper 16mm2 |  | 2025-04-28 | 2025-05-04 | 2025-12-14 | 2026-01-27 | 0 | 0 | 6528.78 | Actual Total Cost
|  |  | JDH3-02-008-L-71-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2025-04-23 | 2025-05-11 | 2025-12-09 | 2026-02-01 | 0 | 0 | 64445.38 | Planned Total Cost | [17 empty] | 58000.85 | 5800.08 | 644.45
|  |  | JDH3-02-008-L-71-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2025-04-23 | 2025-05-11 | 2025-12-09 | 2026-02-01 | 0 | 0 | 64445.38 | Remaining Total Cost | [17 empty] | 58000.85 | 5800.08 | 644.45
|  |  | JDH3-02-008-L-71-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2025-04-23 | 2025-05-11 | 2025-12-09 | 2026-02-01 | 0 | 0 | 64445.38 | Actual Total Cost
|  |  | JDH3-02-008-L-71-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-05-05 | 2025-05-06 | 2025-12-21 | 2025-12-23 | 0 | 0 | 9913.8 | Planned Total Cost | [17 empty] | 9913.8
|  |  | JDH3-02-008-L-71-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-05-05 | 2025-05-06 | 2025-12-21 | 2025-12-23 | 0 | 0 | 9913.8 | Remaining Total Cost | [17 empty] | 9913.8
|  |  | JDH3-02-008-L-71-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-05-05 | 2025-05-06 | 2025-12-21 | 2025-12-23 | 0 | 0 | 9913.8 | Actual Total Cost
|  |  | JDH3-02-008-L-71-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-2 × 150 mm |  | 2025-04-26 | 2025-05-06 | 2025-12-11 | 2026-01-29 | 0 | 0 | 2107.97 | Planned Total Cost | [17 empty] | 2002.57 | 105.4
|  |  | JDH3-02-008-L-71-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-2 × 150 mm |  | 2025-04-26 | 2025-05-06 | 2025-12-11 | 2026-01-29 | 0 | 0 | 2107.97 | Remaining Total Cost | [17 empty] | 2002.57 | 105.4
|  |  | JDH3-02-008-L-71-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-2 × 150 mm |  | 2025-04-26 | 2025-05-06 | 2025-12-11 | 2026-01-29 | 0 | 0 | 2107.97 | Actual Total Cost
|  |  | JDH3-02-008-L-71-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-04-28 | 2025-05-06 | 2025-12-14 | 2026-01-29 | 0 | 0 | 43468.1 | Planned Total Cost | [17 empty] | 39121.29 | 4346.81
|  |  | JDH3-02-008-L-71-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-04-28 | 2025-05-06 | 2025-12-14 | 2026-01-29 | 0 | 0 | 43468.1 | Remaining Total Cost | [17 empty] | 39121.29 | 4346.81
|  |  | JDH3-02-008-L-71-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-04-28 | 2025-05-06 | 2025-12-14 | 2026-01-29 | 0 | 0 | 43468.1 | Actual Total Cost
|  |  | JDH3-02-008-L-71-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2025-04-30 | 2025-05-06 | 2025-12-16 | 2026-01-29 | 0 | 0 | 11015.31 | Planned Total Cost | [17 empty] | 9913.78 | 1101.53
|  |  | JDH3-02-008-L-71-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2025-04-30 | 2025-05-06 | 2025-12-16 | 2026-01-29 | 0 | 0 | 11015.31 | Remaining Total Cost | [17 empty] | 9913.78 | 1101.53
|  |  | JDH3-02-008-L-71-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2025-04-30 | 2025-05-06 | 2025-12-16 | 2026-01-29 | 0 | 0 | 11015.31 | Actual Total Cost
|  |  | JDH3-02-008-L-71-Telecommunications Network - TC |  | 2025-04-20 | 2025-05-03 | 2025-12-06 | 2025-12-20 | 0 | 0 | 63877.14 | Planned Total Cost | [17 empty] | 63877.14
|  |  | JDH3-02-008-L-71-Telecommunications Network - TC |  | 2025-04-20 | 2025-05-03 | 2025-12-06 | 2025-12-20 | 0 | 0 | 63877.14 | Remaining Total Cost | [17 empty] | 63877.14
|  |  | JDH3-02-008-L-71-Telecommunications Network - TC |  | 2025-04-20 | 2025-05-03 | 2025-12-06 | 2025-12-20 | 0 | 0 | 63877.14 | Actual Total Cost
|  |  | JDH3-02-008-L-71-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-04-20 | 2025-05-03 | 2025-12-06 | 2025-12-20 | 0 | 0 | 43117.52 | Planned Total Cost | [17 empty] | 43117.52
|  |  | JDH3-02-008-L-71-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-04-20 | 2025-05-03 | 2025-12-06 | 2025-12-20 | 0 | 0 | 43117.52 | Remaining Total Cost | [17 empty] | 43117.52
|  |  | JDH3-02-008-L-71-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-04-20 | 2025-05-03 | 2025-12-06 | 2025-12-20 | 0 | 0 | 43117.52 | Actual Total Cost
|  |  | JDH3-02-008-L-71-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-04-22 | 2025-04-28 | 2025-12-08 | 2025-12-15 | 0 | 0 | 20759.63 | Planned Total Cost | [17 empty] | 20759.63
|  |  | JDH3-02-008-L-71-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-04-22 | 2025-04-28 | 2025-12-08 | 2025-12-15 | 0 | 0 | 20759.63 | Remaining Total Cost | [17 empty] | 20759.63
|  |  | JDH3-02-008-L-71-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-04-22 | 2025-04-28 | 2025-12-08 | 2025-12-15 | 0 | 0 | 20759.63 | Actual Total Cost
|  |  | L-72 |  | 2024-12-05 | 2025-04-21 | 11-Mar-25 A | 2026-01-31 | 1322566.98 | 1322566.95 | 2685510.96 | Planned Total Cost | [5 empty] | 659278.07 | 446977.72 | 170622.84 | 75139.17 | [5 empty] | 5845.63 | 542322.43 | 478228.11 | 66624.87 | 240472.13
|  |  | L-72 |  | 2024-12-05 | 2025-04-21 | 11-Mar-25 A | 2026-01-31 | 1322566.98 | 1322566.95 | 2685510.96 | Remaining Total Cost | [15 empty] | 561746.47 | 487992.19 | 72733.19 | 240472.13
|  |  | L-72 |  | 2024-12-05 | 2025-04-21 | 11-Mar-25 A | 2026-01-31 | 1322566.98 | 1322566.95 | 2685510.96 | Actual Total Cost | [8 empty] | 54072.25 | 458078.1 | 223008.92 | 106587.47 | 103436.84 | 297987.95 | 76402.38 | 2993.02
|  |  | JDH3-02-008-L-72-Sewage Network - SS |  | 2024-12-14 | 2025-01-16 | 08-Apr-25 A | 2025-10-15 | 425152.93 | 425152.91 | 568007.94 | Planned Total Cost | [5 empty] | 281817.44 | 145193.71 | [8 empty] | 140996.79
|  |  | JDH3-02-008-L-72-Sewage Network - SS |  | 2024-12-14 | 2025-01-16 | 08-Apr-25 A | 2025-10-15 | 425152.93 | 425152.91 | 568007.94 | Remaining Total Cost | [15 empty] | 142855.01
|  |  | JDH3-02-008-L-72-Sewage Network - SS |  | 2024-12-14 | 2025-01-16 | 08-Apr-25 A | 2025-10-15 | 425152.93 | 425152.91 | 568007.94 | Actual Total Cost | [9 empty] | 140736.67 | 131694.45 | 56190.49 | 8350.1 | 77680.07 | 10112.21 | 388.93
|  |  | JDH3-02-008-L-72-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2024-12-14 | 2025-01-15 | 08-Apr-25 A | 12-Aug-25 A | 2380-10-02 08:10 | 2380-10-02 07:55 | 175593.34 | Planned Total Cost | [5 empty] | 139646.14 | 35947.2
|  |  | JDH3-02-008-L-72-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2024-12-14 | 2025-01-15 | 08-Apr-25 A | 12-Aug-25 A | 2380-10-02 08:10 | 2380-10-02 07:55 | 175593.34 | Remaining Total Cost
|  |  | JDH3-02-008-L-72-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2024-12-14 | 2025-01-15 | 08-Apr-25 A | 12-Aug-25 A | 2380-10-02 08:10 | 2380-10-02 07:55 | 175593.34 | Actual Total Cost | [9 empty] | 34043.44 | 57776.11 | 53421.42 | 8350.1 | 22002.26
|  |  | JDH3-02-008-L-72-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2024-12-19 | 2025-01-16 | 08-Apr-25 A | 2025-10-04 | 2388-05-29 17:31 | 2388-05-29 17:31 | 185822.64 | Planned Total Cost | [5 empty] | 83940.03 | 96307.93 | [8 empty] | 5574.68
|  |  | JDH3-02-008-L-72-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2024-12-19 | 2025-01-16 | 08-Apr-25 A | 2025-10-04 | 2388-05-29 17:31 | 2388-05-29 17:31 | 185822.64 | Remaining Total Cost | [15 empty] | 7432.91
|  |  | JDH3-02-008-L-72-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2024-12-19 | 2025-01-16 | 08-Apr-25 A | 2025-10-04 | 2388-05-29 17:31 | 2388-05-29 17:31 | 185822.64 | Actual Total Cost | [9 empty] | 61888.06 | 48200.58 | 2122.14 |  | 55677.81 | 10112.21 | 388.93
|  |  | JDH3-02-008-L-72-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2024-12-14 | 2024-12-24 | 08-Apr-25 A | 2025-10-06 | 1924-04-07 09:22 | 1924-04-07 09:07 | 10428.7 | Planned Total Cost | [5 empty] | 8864.39 | [9 empty] | 1564.3
|  |  | JDH3-02-008-L-72-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2024-12-14 | 2024-12-24 | 08-Apr-25 A | 2025-10-06 | 1924-04-07 09:22 | 1924-04-07 09:07 | 10428.7 | Remaining Total Cost | [15 empty] | 1564.3
|  |  | JDH3-02-008-L-72-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2024-12-14 | 2024-12-24 | 08-Apr-25 A | 2025-10-06 | 1924-04-07 09:22 | 1924-04-07 09:07 | 10428.7 | Actual Total Cost | [9 empty] | 7625.97 | 1238.41
|  |  | JDH3-02-008-L-72-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2024-12-24 | 2025-01-14 | 08-Apr-25 A | 2025-10-14 | 2070-07-31 11:17 | 2070-07-31 11:17 | 123840.79 | Planned Total Cost | [5 empty] | 49366.88 | 12938.59 | [8 empty] | 61535.32
|  |  | JDH3-02-008-L-72-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2024-12-24 | 2025-01-14 | 08-Apr-25 A | 2025-10-14 | 2070-07-31 11:17 | 2070-07-31 11:17 | 123840.79 | Remaining Total Cost | [15 empty] | 61535.32
|  |  | JDH3-02-008-L-72-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2024-12-24 | 2025-01-14 | 08-Apr-25 A | 2025-10-14 | 2070-07-31 11:17 | 2070-07-31 11:17 | 123840.79 | Actual Total Cost | [9 empty] | 37179.19 | 24479.35 | 646.93
|  |  | JDH3-02-008-L-72-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2024-12-29 | 2025-01-08 | 2025-10-05 | 2025-10-15 | 0 | 0 | 72322.48 | Planned Total Cost | [15 empty] | 72322.48
|  |  | JDH3-02-008-L-72-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2024-12-29 | 2025-01-08 | 2025-10-05 | 2025-10-15 | 0 | 0 | 72322.48 | Remaining Total Cost | [15 empty] | 72322.48
|  |  | JDH3-02-008-L-72-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2024-12-29 | 2025-01-08 | 2025-10-05 | 2025-10-15 | 0 | 0 | 72322.48 | Actual Total Cost
|  |  | JDH3-02-008-L-72-Storm Network - ST |  | 2024-12-14 | 2025-03-09 | 11-Mar-25 A | 2025-11-20 | 823119.45 | 823119.43 | 1633317.03 | Planned Total Cost | [5 empty] | 377460.63 | 301784.01 | 155595 | [6 empty] | 5845.63 | 401325.64 | 391306.12
|  |  | JDH3-02-008-L-72-Storm Network - ST |  | 2024-12-14 | 2025-03-09 | 11-Mar-25 A | 2025-11-20 | 823119.45 | 823119.43 | 1633317.03 | Remaining Total Cost | [15 empty] | 418891.46 | 391306.12
|  |  | JDH3-02-008-L-72-Storm Network - ST |  | 2024-12-14 | 2025-03-09 | 11-Mar-25 A | 2025-11-20 | 823119.45 | 823119.43 | 1633317.03 | Actual Total Cost | [8 empty] | 54072.25 | 317341.44 | 91314.47 | 50396.98 | 95086.75 | 203574.23 | 11130.07 | 203.25
|  |  | JDH3-02-008-L-72-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-01-18 | 2025-02-15 | 2025-10-16 | 2025-11-04 | 0 | 0 | 219583.04 | Planned Total Cost | [15 empty] | 197624.73 | 21958.3
|  |  | JDH3-02-008-L-72-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-01-18 | 2025-02-15 | 2025-10-16 | 2025-11-04 | 0 | 0 | 219583.04 | Remaining Total Cost | [15 empty] | 197624.73 | 21958.3
|  |  | JDH3-02-008-L-72-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-01-18 | 2025-02-15 | 2025-10-16 | 2025-11-04 | 0 | 0 | 219583.04 | Actual Total Cost
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-01-20 | 2025-02-17 | 2025-10-19 | 2025-11-06 | 0 | 0 | 13159.47 | Planned Total Cost | [15 empty] | 11843.52 | 1315.95
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-01-20 | 2025-02-17 | 2025-10-19 | 2025-11-06 | 0 | 0 | 13159.47 | Remaining Total Cost | [15 empty] | 11843.52 | 1315.95
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-01-20 | 2025-02-17 | 2025-10-19 | 2025-11-06 | 0 | 0 | 13159.47 | Actual Total Cost
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-01-22 | 2025-02-19 | 2025-10-21 | 2025-11-09 | 0 | 0 | 10609.97 | Planned Total Cost | [15 empty] | 9548.98 | 1061
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-01-22 | 2025-02-19 | 2025-10-21 | 2025-11-09 | 0 | 0 | 10609.97 | Remaining Total Cost | [15 empty] | 9548.98 | 1061
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-01-22 | 2025-02-19 | 2025-10-21 | 2025-11-09 | 0 | 0 | 10609.97 | Actual Total Cost
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2024-12-14 | 2025-02-04 | 11-Mar-25 A | 24-Aug-25 A | 2019-08-16 02:53 | 2019-08-16 02:53 | 43693.12 | Planned Total Cost | [5 empty] | 38013.01 |  | 5680.1
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2024-12-14 | 2025-02-04 | 11-Mar-25 A | 24-Aug-25 A | 2019-08-16 02:53 | 2019-08-16 02:53 | 43693.12 | Remaining Total Cost
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2024-12-14 | 2025-02-04 | 11-Mar-25 A | 24-Aug-25 A | 2019-08-16 02:53 | 2019-08-16 02:53 | 43693.12 | Actual Total Cost | [8 empty] | 28537.07 | 6417.43 | 3058.52 |  |  | 5680.1
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-12-14 | 2025-02-06 | 17-Mar-25 A | 19-Aug-25 A | 40978.8 | 2012-03-10 19:12 | 40978.8 | Planned Total Cost | [5 empty] | 35651.55 |  | 5327.25
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-12-14 | 2025-02-06 | 17-Mar-25 A | 19-Aug-25 A | 40978.8 | 2012-03-10 19:12 | 40978.8 | Remaining Total Cost
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-12-14 | 2025-02-06 | 17-Mar-25 A | 19-Aug-25 A | 40978.8 | 2012-03-10 19:12 | 40978.8 | Actual Total Cost | [8 empty] | 7043.23 | 25739.81 | 2031.86 | 836.65 |  | 5327.25
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-12-14 | 2025-02-09 | 06-Apr-25 A | 21-Aug-25 A | 2034-03-28 00:58 | 2034-03-28 00:43 | 49031.04 | Planned Total Cost | [5 empty] | 40940.91 | 1716.09 | 6374.04
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-12-14 | 2025-02-09 | 06-Apr-25 A | 21-Aug-25 A | 2034-03-28 00:58 | 2034-03-28 00:43 | 49031.04 | Remaining Total Cost
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-12-14 | 2025-02-09 | 06-Apr-25 A | 21-Aug-25 A | 2034-03-28 00:58 | 2034-03-28 00:43 | 49031.04 | Actual Total Cost | [9 empty] | 39224.83 | 3432.17 |  |  | 6374.03
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-01-02 | 2025-02-13 | 18-Mar-25 A | 2025-10-06 | 215001.63 | 215001.64 | 232567.45 | Planned Total Cost | [6 empty] | 203465.08 | 23256.74 | [6 empty] | 5845.63
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-01-02 | 2025-02-13 | 18-Mar-25 A | 2025-10-06 | 215001.63 | 215001.64 | 232567.45 | Remaining Total Cost | [15 empty] | 17565.81
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-01-02 | 2025-02-13 | 18-Mar-25 A | 2025-10-06 | 215001.63 | 215001.64 | 232567.45 | Actual Total Cost | [8 empty] | 18491.95 | 96827.95 | 32642.04 | 8705.56 |  | 47000.84 | 11130.07 | 203.25
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2024-12-14 | 2025-02-16 | 05-Apr-25 A | 11-Aug-25 A | 2263-01-23 02:24 | 2263-01-23 02:10 | 132607.1 | Planned Total Cost | [5 empty] | 106085.68 | 4434.45 | 22086.97
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2024-12-14 | 2025-02-16 | 05-Apr-25 A | 11-Aug-25 A | 2263-01-23 02:24 | 2263-01-23 02:10 | 132607.1 | Remaining Total Cost
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2024-12-14 | 2025-02-16 | 05-Apr-25 A | 11-Aug-25 A | 2263-01-23 02:24 | 2263-01-23 02:10 | 132607.1 | Actual Total Cost | [9 empty] | 96416.4 | 12625.57 | 1478.15 |  | 22086.97
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 2.51 to 3.50 m |  | 2025-01-27 | 2025-02-18 | 20-Aug-25 A | 2025-11-02 | 2067-11-24 18:43 | 2067-11-24 18:29 | 76657.22 | Planned Total Cost | [6 empty] | 19164.31 | 42161.47 | [7 empty] | 7665.72 | 7665.72
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 2.51 to 3.50 m |  | 2025-01-27 | 2025-02-18 | 20-Aug-25 A | 2025-11-02 | 2067-11-24 18:43 | 2067-11-24 18:29 | 76657.22 | Remaining Total Cost | [15 empty] | 7665.72 | 7665.72
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 2.51 to 3.50 m |  | 2025-01-27 | 2025-02-18 | 20-Aug-25 A | 2025-11-02 | 2067-11-24 18:43 | 2067-11-24 18:29 | 76657.22 | Actual Total Cost | [13 empty] | 61325.77
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2024-12-14 | 2025-02-20 | 15-Jun-25 A | 2025-11-04 | 2228-11-01 01:55 | 2228-11-01 01:55 | 150132.61 | Planned Total Cost | [5 empty] | 120106.08 | [9 empty] | 15013.26 | 15013.26
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2024-12-14 | 2025-02-20 | 15-Jun-25 A | 2025-11-04 | 2228-11-01 01:55 | 2228-11-01 01:55 | 150132.61 | Remaining Total Cost | [15 empty] | 15013.26 | 15013.26
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2024-12-14 | 2025-02-20 | 15-Jun-25 A | 2025-11-04 | 2228-11-01 01:55 | 2228-11-01 01:55 | 150132.61 | Actual Total Cost | [11 empty] | 33779.84 | 86326.25
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2025-01-08 | 2025-02-23 | 12-May-25 A | 2025-11-06 | 2085-02-08 05:46 | 2085-02-08 05:46 | 84514.06 | Planned Total Cost | [6 empty] | 16902.81 | 50708.43 | [7 empty] | 8451.41 | 8451.41
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2025-01-08 | 2025-02-23 | 12-May-25 A | 2025-11-06 | 2085-02-08 05:46 | 2085-02-08 05:46 | 84514.06 | Remaining Total Cost | [15 empty] | 8451.41 | 8451.41
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2025-01-08 | 2025-02-23 | 12-May-25 A | 2025-11-06 | 2085-02-08 05:46 | 2085-02-08 05:46 | 84514.06 | Actual Total Cost | [10 empty] | 11831.97 |  |  | 55779.27
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 2.51 to 3.50 m |  | 2025-02-01 | 2025-02-25 | 2025-10-16 | 2025-11-09 | 0 | 0 | 92277.9 | Planned Total Cost | [15 empty] | 83050.11 | 9227.79
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 2.51 to 3.50 m |  | 2025-02-01 | 2025-02-25 | 2025-10-16 | 2025-11-09 | 0 | 0 | 92277.9 | Remaining Total Cost | [15 empty] | 83050.11 | 9227.79
|  |  | JDH3-02-008-L-72-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 2.51 to 3.50 m |  | 2025-02-01 | 2025-02-25 | 2025-10-16 | 2025-11-09 | 0 | 0 | 92277.9 | Actual Total Cost
|  |  | JDH3-02-008-L-72-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-12-14 | 2025-02-27 | 06-Apr-25 A | 2025-11-11 | 1938-06-29 13:55 | 1938-06-29 13:55 | 20857.39 | Planned Total Cost | [5 empty] | 5214.35 | 8846.23 | [8 empty] | 4711.07 | 2085.74
|  |  | JDH3-02-008-L-72-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-12-14 | 2025-02-27 | 06-Apr-25 A | 2025-11-11 | 1938-06-29 13:55 | 1938-06-29 13:55 | 20857.39 | Remaining Total Cost | [15 empty] | 4711.07 | 2085.74
|  |  | JDH3-02-008-L-72-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-12-14 | 2025-02-27 | 06-Apr-25 A | 2025-11-11 | 1938-06-29 13:55 | 1938-06-29 13:55 | 20857.39 | Actual Total Cost | [9 empty] | 5214.35 | 5214.35 | 2950.9 | 680.98
|  |  | JDH3-02-008-L-72-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2024-12-14 | 2025-03-02 | 06-Apr-25 A | 2025-11-13 | 1959-05-02 03:22 | 1959-05-02 03:36 | 41062.99 | Planned Total Cost | [5 empty] | 10265.75 | 11406.4 | [8 empty] | 14257.97 | 5132.87
|  |  | JDH3-02-008-L-72-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2024-12-14 | 2025-03-02 | 06-Apr-25 A | 2025-11-13 | 1959-05-02 03:22 | 1959-05-02 03:36 | 41062.99 | Remaining Total Cost | [15 empty] | 14257.97 | 5132.87
|  |  | JDH3-02-008-L-72-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2024-12-14 | 2025-03-02 | 06-Apr-25 A | 2025-11-13 | 1959-05-02 03:22 | 1959-05-02 03:36 | 41062.99 | Actual Total Cost | [9 empty] | 10265.75 | 4426.37 | 2411.8 | 4568.23
|  |  | JDH3-02-008-L-72-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2024-12-14 | 2025-03-04 | 06-Apr-25 A | 2025-11-16 | 1957-12-29 06:58 | 1957-12-29 06:58 | 84733.16 | Planned Total Cost | [5 empty] | 21183.29 | [9 empty] | 36011.59 | 27538.28
|  |  | JDH3-02-008-L-72-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2024-12-14 | 2025-03-04 | 06-Apr-25 A | 2025-11-16 | 1957-12-29 06:58 | 1957-12-29 06:58 | 84733.16 | Remaining Total Cost | [15 empty] | 36011.59 | 27538.28
|  |  | JDH3-02-008-L-72-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2024-12-14 | 2025-03-04 | 06-Apr-25 A | 2025-11-16 | 1957-12-29 06:58 | 1957-12-29 06:58 | 84733.16 | Actual Total Cost | [9 empty] | 21183.29
|  |  | JDH3-02-008-L-72-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-01-15 | 2025-03-06 | 06-Apr-25 A | 2025-11-18 | 1998-02-22 15:36 | 1998-02-22 15:22 | 86036.74 | Planned Total Cost | [6 empty] | 35848.65 | [8 empty] | 2728.78 | 47459.32
|  |  | JDH3-02-008-L-72-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-01-15 | 2025-03-06 | 06-Apr-25 A | 2025-11-18 | 1998-02-22 15:36 | 1998-02-22 15:22 | 86036.74 | Remaining Total Cost | [15 empty] | 2728.78 | 47459.32
|  |  | JDH3-02-008-L-72-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-01-15 | 2025-03-06 | 06-Apr-25 A | 2025-11-18 | 1998-02-22 15:36 | 1998-02-22 15:22 | 86036.74 | Actual Total Cost | [9 empty] | 16051.63 | 16051.63 | 234.09 | 3511.29
|  |  | JDH3-02-008-L-72-(ST)- Single Catchbasine Works |  | 2025-02-17 | 2025-03-09 | 2025-11-02 | 2025-11-20 | 0 | 0 | 62572.21 | Planned Total Cost | [16 empty] | 62572.21
|  |  | JDH3-02-008-L-72-(ST)- Single Catchbasine Works |  | 2025-02-17 | 2025-03-09 | 2025-11-02 | 2025-11-20 | 0 | 0 | 62572.21 | Remaining Total Cost | [16 empty] | 62572.21
|  |  | JDH3-02-008-L-72-(ST)- Single Catchbasine Works |  | 2025-02-17 | 2025-03-09 | 2025-11-02 | 2025-11-20 | 0 | 0 | 62572.21 | Actual Total Cost
|  |  | JDH3-02-008-L-72-(ST)- Double Catchbasine Works |  | 2025-02-19 | 2025-03-02 | 2025-11-04 | 2025-11-15 | 0 | 0 | 181824.28 | Planned Total Cost | [16 empty] | 181824.28
|  |  | JDH3-02-008-L-72-(ST)- Double Catchbasine Works |  | 2025-02-19 | 2025-03-02 | 2025-11-04 | 2025-11-15 | 0 | 0 | 181824.28 | Remaining Total Cost | [16 empty] | 181824.28
|  |  | JDH3-02-008-L-72-(ST)- Double Catchbasine Works |  | 2025-02-19 | 2025-03-02 | 2025-11-04 | 2025-11-15 | 0 | 0 | 181824.28 | Actual Total Cost
|  |  | JDH3-02-008-L-72-(ST)-PIPES ENCASEMENT |  | 2025-02-08 | 2025-02-10 | 2025-10-28 | 2025-10-30 | 0 | 0 | 10418.5 | Planned Total Cost | [15 empty] | 10418.5
|  |  | JDH3-02-008-L-72-(ST)-PIPES ENCASEMENT |  | 2025-02-08 | 2025-02-10 | 2025-10-28 | 2025-10-30 | 0 | 0 | 10418.5 | Remaining Total Cost | [15 empty] | 10418.5
|  |  | JDH3-02-008-L-72-(ST)-PIPES ENCASEMENT |  | 2025-02-08 | 2025-02-10 | 2025-10-28 | 2025-10-30 | 0 | 0 | 10418.5 | Actual Total Cost
|  |  | JDH3-02-008-L-72-TSE Network - TSE |  | 2025-02-22 | 2025-03-18 | 2025-11-10 | 2025-12-02 | 0 | 0 | 69386.82 | Planned Total Cost | [16 empty] | 66240.76 | 3146.05
|  |  | JDH3-02-008-L-72-TSE Network - TSE |  | 2025-02-22 | 2025-03-18 | 2025-11-10 | 2025-12-02 | 0 | 0 | 69386.82 | Remaining Total Cost | [16 empty] | 66240.76 | 3146.05
|  |  | JDH3-02-008-L-72-TSE Network - TSE |  | 2025-02-22 | 2025-03-18 | 2025-11-10 | 2025-12-02 | 0 | 0 | 69386.82 | Actual Total Cost
|  |  | JDH3-02-008-L-72-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-02-22 | 2025-03-18 | 2025-11-10 | 2025-12-02 | 0 | 0 | 62921.01 | Planned Total Cost | [16 empty] | 59774.96 | 3146.05
|  |  | JDH3-02-008-L-72-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-02-22 | 2025-03-18 | 2025-11-10 | 2025-12-02 | 0 | 0 | 62921.01 | Remaining Total Cost | [16 empty] | 59774.96 | 3146.05
|  |  | JDH3-02-008-L-72-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-02-22 | 2025-03-18 | 2025-11-10 | 2025-12-02 | 0 | 0 | 62921.01 | Actual Total Cost
|  |  | JDH3-02-008-L-72-(TSE)-Supply and install gate valves-100 mm |  | 2025-03-08 | 2025-03-11 | 2025-11-24 | 2025-11-27 | 0 | 0 | 6465.8 | Planned Total Cost | [16 empty] | 6465.8
|  |  | JDH3-02-008-L-72-(TSE)-Supply and install gate valves-100 mm |  | 2025-03-08 | 2025-03-11 | 2025-11-24 | 2025-11-27 | 0 | 0 | 6465.8 | Remaining Total Cost | [16 empty] | 6465.8
|  |  | JDH3-02-008-L-72-(TSE)-Supply and install gate valves-100 mm |  | 2025-03-08 | 2025-03-11 | 2025-11-24 | 2025-11-27 | 0 | 0 | 6465.8 | Actual Total Cost
|  |  | JDH3-02-008-L-72-Potable Water Network - WT |  | 2025-02-25 | 2025-03-31 | 16-Aug-25 A | 2025-12-09 | 2103-05-29 14:38 | 2103-05-29 14:38 | 174327.05 | Planned Total Cost | [7 empty] | 15027.83 | 75139.17 | [7 empty] | 20681.22 | 63478.82
|  |  | JDH3-02-008-L-72-Potable Water Network - WT |  | 2025-02-25 | 2025-03-31 | 16-Aug-25 A | 2025-12-09 | 2103-05-29 14:38 | 2103-05-29 14:38 | 174327.05 | Remaining Total Cost | [16 empty] | 30445.31 | 69587.14
|  |  | JDH3-02-008-L-72-Potable Water Network - WT |  | 2025-02-25 | 2025-03-31 | 16-Aug-25 A | 2025-12-09 | 2103-05-29 14:38 | 2103-05-29 14:38 | 174327.05 | Actual Total Cost | [13 empty] | 16733.66 | 55160.11 | 2400.85
|  |  | JDH3-02-008-L-72-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-02-25 | 2025-03-31 | 16-Aug-25 A | 2025-12-09 | 2103-05-29 14:38 | 2103-05-29 14:38 | 100185.56 | Planned Total Cost | [7 empty] | 15027.83 | 75139.17 | [7 empty] | 10018.56
|  |  | JDH3-02-008-L-72-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-02-25 | 2025-03-31 | 16-Aug-25 A | 2025-12-09 | 2103-05-29 14:38 | 2103-05-29 14:38 | 100185.56 | Remaining Total Cost | [16 empty] | 19782.64 | 6108.32
|  |  | JDH3-02-008-L-72-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-02-25 | 2025-03-31 | 16-Aug-25 A | 2025-12-09 | 2103-05-29 14:38 | 2103-05-29 14:38 | 100185.56 | Actual Total Cost | [13 empty] | 16733.66 | 55160.11 | 2400.85
|  |  | JDH3-02-008-L-72-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2025-03-08 | 2025-03-11 | 2025-11-11 | 2025-11-16 | 0 | 0 | 10662.67 | Planned Total Cost | [16 empty] | 10662.67
|  |  | JDH3-02-008-L-72-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2025-03-08 | 2025-03-11 | 2025-11-11 | 2025-11-16 | 0 | 0 | 10662.67 | Remaining Total Cost | [16 empty] | 10662.67
|  |  | JDH3-02-008-L-72-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2025-03-08 | 2025-03-11 | 2025-11-11 | 2025-11-16 | 0 | 0 | 10662.67 | Actual Total Cost
|  |  | JDH3-02-008-L-72-(WT)- Supply and install 3-out fire hydrant |  | 2025-03-19 | 2025-03-25 | 2025-12-03 | 2025-12-09 | 0 | 0 | 63478.82 | Planned Total Cost | [17 empty] | 63478.82
|  |  | JDH3-02-008-L-72-(WT)- Supply and install 3-out fire hydrant |  | 2025-03-19 | 2025-03-25 | 2025-12-03 | 2025-12-09 | 0 | 0 | 63478.82 | Remaining Total Cost | [17 empty] | 63478.82
|  |  | JDH3-02-008-L-72-(WT)- Supply and install 3-out fire hydrant |  | 2025-03-19 | 2025-03-25 | 2025-12-03 | 2025-12-09 | 0 | 0 | 63478.82 | Actual Total Cost
|  |  | JDH3-02-008-L-72-Street Lighting Network -SL |  | 2025-03-26 | 2025-04-14 | 2026-01-04 | 2026-01-24 | 0 | 0 | 176594.98 | Planned Total Cost | [18 empty] | 176594.98
|  |  | JDH3-02-008-L-72-Street Lighting Network -SL |  | 2025-03-26 | 2025-04-14 | 2026-01-04 | 2026-01-24 | 0 | 0 | 176594.98 | Remaining Total Cost | [18 empty] | 176594.98
|  |  | JDH3-02-008-L-72-Street Lighting Network -SL |  | 2025-03-26 | 2025-04-14 | 2026-01-04 | 2026-01-24 | 0 | 0 | 176594.98 | Actual Total Cost
|  |  | JDH3-02-008-L-72-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx25 mm² |  | 2025-03-26 | 2025-04-12 | 2026-01-04 | 2026-01-21 | 0 | 0 | 39668.05 | Planned Total Cost | [18 empty] | 39668.05
|  |  | JDH3-02-008-L-72-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx25 mm² |  | 2025-03-26 | 2025-04-12 | 2026-01-04 | 2026-01-21 | 0 | 0 | 39668.05 | Remaining Total Cost | [18 empty] | 39668.05
|  |  | JDH3-02-008-L-72-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx25 mm² |  | 2025-03-26 | 2025-04-12 | 2026-01-04 | 2026-01-21 | 0 | 0 | 39668.05 | Actual Total Cost
|  |  | JDH3-02-008-L-72-(STL)- Supply,install,connect and test single core PVC insulated copper 16mm2 |  | 2025-04-02 | 2025-04-08 | 2026-01-11 | 2026-01-18 | 0 | 0 | 5598.33 | Planned Total Cost | [18 empty] | 5598.33
|  |  | JDH3-02-008-L-72-(STL)- Supply,install,connect and test single core PVC insulated copper 16mm2 |  | 2025-04-02 | 2025-04-08 | 2026-01-11 | 2026-01-18 | 0 | 0 | 5598.33 | Remaining Total Cost | [18 empty] | 5598.33
|  |  | JDH3-02-008-L-72-(STL)- Supply,install,connect and test single core PVC insulated copper 16mm2 |  | 2025-04-02 | 2025-04-08 | 2026-01-11 | 2026-01-18 | 0 | 0 | 5598.33 | Actual Total Cost
|  |  | JDH3-02-008-L-72-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2025-03-30 | 2025-04-14 | 2026-01-07 | 2026-01-24 | 0 | 0 | 64445.38 | Planned Total Cost | [18 empty] | 64445.38
|  |  | JDH3-02-008-L-72-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2025-03-30 | 2025-04-14 | 2026-01-07 | 2026-01-24 | 0 | 0 | 64445.38 | Remaining Total Cost | [18 empty] | 64445.38
|  |  | JDH3-02-008-L-72-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2025-03-30 | 2025-04-14 | 2026-01-07 | 2026-01-24 | 0 | 0 | 64445.38 | Actual Total Cost
|  |  | JDH3-02-008-L-72-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-04-10 | 2025-04-12 | 2026-01-19 | 2026-01-21 | 0 | 0 | 9913.8 | Planned Total Cost | [18 empty] | 9913.8
|  |  | JDH3-02-008-L-72-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-04-10 | 2025-04-12 | 2026-01-19 | 2026-01-21 | 0 | 0 | 9913.8 | Remaining Total Cost | [18 empty] | 9913.8
|  |  | JDH3-02-008-L-72-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-04-10 | 2025-04-12 | 2026-01-19 | 2026-01-21 | 0 | 0 | 9913.8 | Actual Total Cost
|  |  | JDH3-02-008-L-72-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2025-04-10 | 2025-04-12 | 2026-01-19 | 2026-01-21 | 0 | 0 | 378.04 | Planned Total Cost | [18 empty] | 378.04
|  |  | JDH3-02-008-L-72-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2025-04-10 | 2025-04-12 | 2026-01-19 | 2026-01-21 | 0 | 0 | 378.04 | Remaining Total Cost | [18 empty] | 378.04
|  |  | JDH3-02-008-L-72-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2025-04-10 | 2025-04-12 | 2026-01-19 | 2026-01-21 | 0 | 0 | 378.04 | Actual Total Cost
|  |  | JDH3-02-008-L-72-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-2 × 150 mm |  | 2025-04-01 | 2025-04-09 | 2026-01-10 | 2026-01-19 | 0 | 0 | 2107.97 | Planned Total Cost | [18 empty] | 2107.97
|  |  | JDH3-02-008-L-72-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-2 × 150 mm |  | 2025-04-01 | 2025-04-09 | 2026-01-10 | 2026-01-19 | 0 | 0 | 2107.97 | Remaining Total Cost | [18 empty] | 2107.97
|  |  | JDH3-02-008-L-72-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-2 × 150 mm |  | 2025-04-01 | 2025-04-09 | 2026-01-10 | 2026-01-19 | 0 | 0 | 2107.97 | Actual Total Cost
|  |  | JDH3-02-008-L-72-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-04-03 | 2025-04-09 | 2026-01-12 | 2026-01-19 | 0 | 0 | 43468.1 | Planned Total Cost | [18 empty] | 43468.1
|  |  | JDH3-02-008-L-72-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-04-03 | 2025-04-09 | 2026-01-12 | 2026-01-19 | 0 | 0 | 43468.1 | Remaining Total Cost | [18 empty] | 43468.1
|  |  | JDH3-02-008-L-72-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-04-03 | 2025-04-09 | 2026-01-12 | 2026-01-19 | 0 | 0 | 43468.1 | Actual Total Cost
|  |  | JDH3-02-008-L-72-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2025-04-06 | 2025-04-14 | 2026-01-14 | 2026-01-24 | 0 | 0 | 11015.31 | Planned Total Cost | [18 empty] | 11015.31
|  |  | JDH3-02-008-L-72-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2025-04-06 | 2025-04-14 | 2026-01-14 | 2026-01-24 | 0 | 0 | 11015.31 | Remaining Total Cost | [18 empty] | 11015.31
|  |  | JDH3-02-008-L-72-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2025-04-06 | 2025-04-14 | 2026-01-14 | 2026-01-24 | 0 | 0 | 11015.31 | Actual Total Cost
|  |  | JDH3-02-008-L-72-Telecommunications Network - TC |  | 2025-04-08 | 2025-04-21 | 2026-01-17 | 2026-01-31 | 0 | 0 | 63877.14 | Planned Total Cost | [18 empty] | 63877.14
|  |  | JDH3-02-008-L-72-Telecommunications Network - TC |  | 2025-04-08 | 2025-04-21 | 2026-01-17 | 2026-01-31 | 0 | 0 | 63877.14 | Remaining Total Cost | [18 empty] | 63877.14
|  |  | JDH3-02-008-L-72-Telecommunications Network - TC |  | 2025-04-08 | 2025-04-21 | 2026-01-17 | 2026-01-31 | 0 | 0 | 63877.14 | Actual Total Cost
|  |  | JDH3-02-008-L-72-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-04-08 | 2025-04-21 | 2026-01-17 | 2026-01-31 | 0 | 0 | 43117.52 | Planned Total Cost | [18 empty] | 43117.52
|  |  | JDH3-02-008-L-72-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-04-08 | 2025-04-21 | 2026-01-17 | 2026-01-31 | 0 | 0 | 43117.52 | Remaining Total Cost | [18 empty] | 43117.52
|  |  | JDH3-02-008-L-72-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-04-08 | 2025-04-21 | 2026-01-17 | 2026-01-31 | 0 | 0 | 43117.52 | Actual Total Cost
|  |  | JDH3-02-008-L-72-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-04-10 | 2025-04-16 | 2026-01-19 | 2026-01-26 | 0 | 0 | 20759.63 | Planned Total Cost | [18 empty] | 20759.63
|  |  | JDH3-02-008-L-72-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-04-10 | 2025-04-16 | 2026-01-19 | 2026-01-26 | 0 | 0 | 20759.63 | Remaining Total Cost | [18 empty] | 20759.63
|  |  | JDH3-02-008-L-72-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-04-10 | 2025-04-16 | 2026-01-19 | 2026-01-26 | 0 | 0 | 20759.63 | Actual Total Cost
|  |  | L-73 |  | 2024-12-05 | 2025-05-06 | 10-Jun-25 A | 2026-02-22 | 916800.79 | 916800.77 | 3244888.02 | Planned Total Cost | [5 empty] | 166996.24 | 375187.6 | 418292.78 | 31465.98 | 182910.86 | [5 empty] | 201326.09 |  | 87186.78 | 1497609.02 | 283912.67
|  |  | L-73 |  | 2024-12-05 | 2025-05-06 | 10-Jun-25 A | 2026-02-22 | 916800.79 | 916800.77 | 3244888.02 | Remaining Total Cost | [15 empty] | 278840.62 |  | 156740.68 | 1608593.28 | 283912.67
|  |  | L-73 |  | 2024-12-05 | 2025-05-06 | 10-Jun-25 A | 2026-02-22 | 916800.79 | 916800.77 | 3244888.02 | Actual Total Cost | [12 empty] | 121232.31 | 242924.99 | 533911.09 | 18732.38
|  |  | JDH3-02-008-L-73-Sewage Network - SS |  | 2025-01-27 | 2025-03-02 | 14-Aug-25 A | 2026-01-04 | 2389-06-22 12:14 | 2389-06-22 12:29 | 357301.57 | Planned Total Cost | [6 empty] | 17218.37 | 243476.81 | [9 empty] | 81711.72 | 14894.68
|  |  | JDH3-02-008-L-73-Sewage Network - SS |  | 2025-01-27 | 2025-03-02 | 14-Aug-25 A | 2026-01-04 | 2389-06-22 12:14 | 2389-06-22 12:29 | 357301.57 | Remaining Total Cost | [17 empty] | 156740.68 | 21782.38
|  |  | JDH3-02-008-L-73-Sewage Network - SS |  | 2025-01-27 | 2025-03-02 | 14-Aug-25 A | 2026-01-04 | 2389-06-22 12:14 | 2389-06-22 12:29 | 357301.57 | Actual Total Cost | [13 empty] | 38643.34 | 134782.87 | 5352.32
|  |  | JDH3-02-008-L-73-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2025-01-27 | 2025-02-06 | 2025-12-11 | 2025-12-23 | 0 | 0 | 15704.76 | Planned Total Cost | [17 empty] | 15704.76
|  |  | JDH3-02-008-L-73-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2025-01-27 | 2025-02-06 | 2025-12-11 | 2025-12-23 | 0 | 0 | 15704.76 | Remaining Total Cost | [17 empty] | 15704.76
|  |  | JDH3-02-008-L-73-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2025-01-27 | 2025-02-06 | 2025-12-11 | 2025-12-23 | 0 | 0 | 15704.76 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2025-01-29 | 2025-03-02 | 14-Aug-25 A | 2026-01-04 | 129599.23 | 2254-10-29 05:31 | 172183.7 | Planned Total Cost | [6 empty] | 17218.37 | 120528.59 | [9 empty] | 34436.74
|  |  | JDH3-02-008-L-73-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2025-01-29 | 2025-03-02 | 14-Aug-25 A | 2026-01-04 | 129599.23 | 2254-10-29 05:31 | 172183.7 | Remaining Total Cost | [17 empty] | 35696.77 | 6887.7
|  |  | JDH3-02-008-L-73-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2025-01-29 | 2025-03-02 | 14-Aug-25 A | 2026-01-04 | 129599.23 | 2254-10-29 05:31 | 172183.7 | Actual Total Cost | [13 empty] | 26894.73 | 98738.51 | 3965.99
|  |  | JDH3-02-008-L-73-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2025-02-03 | 2025-02-13 | 2025-12-14 | 2025-12-25 | 0 | 0 | 10428.7 | Planned Total Cost | [17 empty] | 10428.7
|  |  | JDH3-02-008-L-73-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2025-02-03 | 2025-02-13 | 2025-12-14 | 2025-12-25 | 0 | 0 | 10428.7 | Remaining Total Cost | [17 empty] | 10428.7
|  |  | JDH3-02-008-L-73-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2025-02-03 | 2025-02-13 | 2025-12-14 | 2025-12-25 | 0 | 0 | 10428.7 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm with back drop |  | 2025-02-05 | 2025-02-20 | 2025-12-16 | 2026-01-01 | 0 | 0 | 14339.45 | Planned Total Cost | [17 empty] | 13909.27 | 430.18
|  |  | JDH3-02-008-L-73-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm with back drop |  | 2025-02-05 | 2025-02-20 | 2025-12-16 | 2026-01-01 | 0 | 0 | 14339.45 | Remaining Total Cost | [17 empty] | 13909.27 | 430.18
|  |  | JDH3-02-008-L-73-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm with back drop |  | 2025-02-05 | 2025-02-20 | 2025-12-16 | 2026-01-01 | 0 | 0 | 14339.45 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2025-02-08 | 2025-02-23 | 18-Aug-25 A | 2026-01-04 | 2034-08-23 06:58 | 2034-08-23 06:58 | 144644.96 | Planned Total Cost | [7 empty] | 122948.22 | [9 empty] | 7232.25 | 14464.5
|  |  | JDH3-02-008-L-73-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2025-02-08 | 2025-02-23 | 18-Aug-25 A | 2026-01-04 | 2034-08-23 06:58 | 2034-08-23 06:58 | 144644.96 | Remaining Total Cost | [17 empty] | 81001.17 | 14464.5
|  |  | JDH3-02-008-L-73-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2025-02-08 | 2025-02-23 | 18-Aug-25 A | 2026-01-04 | 2034-08-23 06:58 | 2034-08-23 06:58 | 144644.96 | Actual Total Cost | [13 empty] | 11748.61 | 36044.36 | 1386.32
|  |  | JDH3-02-008-L-73-Storm Network - ST |  | 2024-12-14 | 2025-04-22 | 01-Jul-25 A | 2026-02-04 | 738022.28 | 738022.25 | 2279228.47 | Planned Total Cost | [5 empty] | 166996.24 | 357969.23 | 174815.98 | 31465.98 | 182910.86 | [5 empty] | 201326.09 |  | 5475.07 | 1126988.73 | 31280.29
|  |  | JDH3-02-008-L-73-Storm Network - ST |  | 2024-12-14 | 2025-04-22 | 01-Jul-25 A | 2026-02-04 | 738022.28 | 738022.25 | 2279228.47 | Remaining Total Cost | [15 empty] | 278840.62 |  |  | 1231085.3 | 31280.29
|  |  | JDH3-02-008-L-73-Storm Network - ST |  | 2024-12-14 | 2025-04-22 | 01-Jul-25 A | 2026-02-04 | 738022.28 | 738022.25 | 2279228.47 | Actual Total Cost | [12 empty] | 121232.31 | 204281.65 | 399128.22 | 13380.06
|  |  | JDH3-02-008-L-73-(ST)-Box Culvert |  | 2024-12-14 | 2025-03-22 | 01-Jul-25 A | 2025-10-29 | 590980.84 | 590980.82 | 869821.44 | Planned Total Cost | [5 empty] | 166996.24 | 357969.23 | 143529.88 | [7 empty] | 201326.09
|  |  | JDH3-02-008-L-73-(ST)-Box Culvert |  | 2024-12-14 | 2025-03-22 | 01-Jul-25 A | 2025-10-29 | 590980.84 | 590980.82 | 869821.44 | Remaining Total Cost | [15 empty] | 278840.62
|  |  | JDH3-02-008-L-73-(ST)-Box Culvert |  | 2024-12-14 | 2025-03-22 | 01-Jul-25 A | 2025-10-29 | 590980.84 | 590980.82 | 869821.44 | Actual Total Cost | [12 empty] | 121232.31 | 176063.59 | 284407.52 | 9277.4
|  |  | JDH3-02-008-L-73-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2024-12-14 | 2025-02-22 | 01-Jul-25 A | 2025-10-07 | 550715.62 | 550715.61 | 668495.35 | Planned Total Cost | [5 empty] | 166996.24 | 357969.23 | 143529.88
|  |  | JDH3-02-008-L-73-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2024-12-14 | 2025-02-22 | 01-Jul-25 A | 2025-10-07 | 550715.62 | 550715.61 | 668495.35 | Remaining Total Cost | [15 empty] | 117779.75
|  |  | JDH3-02-008-L-73-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2024-12-14 | 2025-02-22 | 01-Jul-25 A | 2025-10-07 | 550715.62 | 550715.61 | 668495.35 | Actual Total Cost | [12 empty] | 121232.31 | 176063.59 | 244142.31 | 9277.4
|  |  | JDH3-02-008-L-73-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2025-02-23 | 2025-03-22 | 14-Sep-25 A | 2025-10-29 | 2010-03-28 05:17 | 2010-03-28 05:02 | 201326.09 | Planned Total Cost | [15 empty] | 201326.09
|  |  | JDH3-02-008-L-73-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2025-02-23 | 2025-03-22 | 14-Sep-25 A | 2025-10-29 | 2010-03-28 05:17 | 2010-03-28 05:02 | 201326.09 | Remaining Total Cost | [15 empty] | 161060.87
|  |  | JDH3-02-008-L-73-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2025-02-23 | 2025-03-22 | 14-Sep-25 A | 2025-10-29 | 2010-03-28 05:17 | 2010-03-28 05:02 | 201326.09 | Actual Total Cost | [14 empty] | 40265.21
|  |  | JDH3-02-008-L-73-(ST)-NetWork |  | 2025-02-25 | 2025-04-22 | 09-Aug-25 A | 2026-02-04 | 2302-08-01 10:34 | 2302-08-01 10:19 | 1409407.03 | Planned Total Cost | [7 empty] | 31286.09 | 31465.98 | 182910.86 | [7 empty] | 5475.07 | 1126988.73 | 31280.29
|  |  | JDH3-02-008-L-73-(ST)-NetWork |  | 2025-02-25 | 2025-04-22 | 09-Aug-25 A | 2026-02-04 | 2302-08-01 10:34 | 2302-08-01 10:19 | 1409407.03 | Remaining Total Cost | [18 empty] | 1231085.3 | 31280.29
|  |  | JDH3-02-008-L-73-(ST)-NetWork |  | 2025-02-25 | 2025-04-22 | 09-Aug-25 A | 2026-02-04 | 2302-08-01 10:34 | 2302-08-01 10:19 | 1409407.03 | Actual Total Cost | [13 empty] | 28218.06 | 114720.71 | 4102.66
|  |  | JDH3-02-008-L-73-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-03-23 | 2025-04-08 | 2026-01-04 | 2026-01-21 | 0 | 0 | 203439.3 | Planned Total Cost | [18 empty] | 203439.3
|  |  | JDH3-02-008-L-73-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-03-23 | 2025-04-08 | 2026-01-04 | 2026-01-21 | 0 | 0 | 203439.3 | Remaining Total Cost | [18 empty] | 203439.3
|  |  | JDH3-02-008-L-73-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-03-23 | 2025-04-08 | 2026-01-04 | 2026-01-21 | 0 | 0 | 203439.3 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-03-25 | 2025-04-05 | 2026-01-06 | 2026-01-18 | 0 | 0 | 76383.18 | Planned Total Cost | [18 empty] | 76383.18
|  |  | JDH3-02-008-L-73-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-03-25 | 2025-04-05 | 2026-01-06 | 2026-01-18 | 0 | 0 | 76383.18 | Remaining Total Cost | [18 empty] | 76383.18
|  |  | JDH3-02-008-L-73-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-03-25 | 2025-04-05 | 2026-01-06 | 2026-01-18 | 0 | 0 | 76383.18 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-03-27 | 2025-04-07 | 2026-01-08 | 2026-01-20 | 0 | 0 | 30179.57 | Planned Total Cost | [18 empty] | 30179.57
|  |  | JDH3-02-008-L-73-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-03-27 | 2025-04-07 | 2026-01-08 | 2026-01-20 | 0 | 0 | 30179.57 | Remaining Total Cost | [18 empty] | 30179.57
|  |  | JDH3-02-008-L-73-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-03-27 | 2025-04-07 | 2026-01-08 | 2026-01-20 | 0 | 0 | 30179.57 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2025-03-30 | 2025-04-10 | 23-Aug-25 A | 2026-01-24 | 1950-04-19 | 1950-04-19 | 70967.25 | Planned Total Cost | [8 empty] | 14193.45 | 42580.35 | [8 empty] | 14193.45
|  |  | JDH3-02-008-L-73-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2025-03-30 | 2025-04-10 | 23-Aug-25 A | 2026-01-24 | 1950-04-19 | 1950-04-19 | 70967.25 | Remaining Total Cost | [18 empty] | 52595.25
|  |  | JDH3-02-008-L-73-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2025-03-30 | 2025-04-10 | 23-Aug-25 A | 2026-01-24 | 1950-04-19 | 1950-04-19 | 70967.25 | Actual Total Cost | [13 empty] | 2888.38 | 14910.16 | 573.47
|  |  | JDH3-02-008-L-73-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2025-04-01 | 2025-04-13 | 2026-01-11 | 2026-01-26 | 0 | 0 | 9130.04 | Planned Total Cost | [18 empty] | 9130.04
|  |  | JDH3-02-008-L-73-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2025-04-01 | 2025-04-13 | 2026-01-11 | 2026-01-26 | 0 | 0 | 9130.04 | Remaining Total Cost | [18 empty] | 9130.04
|  |  | JDH3-02-008-L-73-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2025-04-01 | 2025-04-13 | 2026-01-11 | 2026-01-26 | 0 | 0 | 9130.04 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2025-04-03 | 2025-04-15 | 2026-01-13 | 2026-01-28 | 0 | 0 | 29740.2 | Planned Total Cost | [18 empty] | 29740.2
|  |  | JDH3-02-008-L-73-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2025-04-03 | 2025-04-15 | 2026-01-13 | 2026-01-28 | 0 | 0 | 29740.2 | Remaining Total Cost | [18 empty] | 29740.2
|  |  | JDH3-02-008-L-73-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2025-04-03 | 2025-04-15 | 2026-01-13 | 2026-01-28 | 0 | 0 | 29740.2 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-04-06 | 2025-04-17 | 23-Aug-25 A | 2026-01-31 | 2006-01-28 00:43 | 2006-01-28 00:43 | 54715.35 | Planned Total Cost | [9 empty] | 49243.82 | [8 empty] | 5471.54
|  |  | JDH3-02-008-L-73-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-04-06 | 2025-04-17 | 23-Aug-25 A | 2026-01-31 | 2006-01-28 00:43 | 2006-01-28 00:43 | 54715.35 | Remaining Total Cost | [18 empty] | 15970.32
|  |  | JDH3-02-008-L-73-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-04-06 | 2025-04-17 | 23-Aug-25 A | 2026-01-31 | 2006-01-28 00:43 | 2006-01-28 00:43 | 54715.35 | Actual Total Cost | [13 empty] | 5711.43 | 31810.14 | 1223.47
|  |  | JDH3-02-008-L-73-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-04-08 | 2025-04-20 | 23-Aug-25 A | 2026-02-02 | 2087-04-23 05:17 | 2087-04-23 05:17 | 113858.37 | Planned Total Cost | [9 empty] | 91086.7 | [8 empty] | 14801.59 | 7970.09
|  |  | JDH3-02-008-L-73-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-04-08 | 2025-04-20 | 23-Aug-25 A | 2026-02-02 | 2087-04-23 05:17 | 2087-04-23 05:17 | 113858.37 | Remaining Total Cost | [18 empty] | 37473.07 | 7970.09
|  |  | JDH3-02-008-L-73-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-04-08 | 2025-04-20 | 23-Aug-25 A | 2026-02-02 | 2087-04-23 05:17 | 2087-04-23 05:17 | 113858.37 | Actual Total Cost | [13 empty] | 10755.98 | 55523.71 | 2135.53
|  |  | JDH3-02-008-L-73-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2025-04-10 | 2025-04-22 | 2026-01-15 | 2026-02-04 | 0 | 0 | 233102.08 | Planned Total Cost | [18 empty] | 209791.87 | 23310.21
|  |  | JDH3-02-008-L-73-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2025-04-10 | 2025-04-22 | 2026-01-15 | 2026-02-04 | 0 | 0 | 233102.08 | Remaining Total Cost | [18 empty] | 209791.87 | 23310.21
|  |  | JDH3-02-008-L-73-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2025-04-10 | 2025-04-22 | 2026-01-15 | 2026-02-04 | 0 | 0 | 233102.08 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-02-25 | 2025-03-08 | 09-Aug-25 A | 2026-01-11 | 1921-05-30 12:29 | 1921-05-30 12:29 | 83429.58 | Planned Total Cost | [7 empty] | 31286.09 | 10428.7 | [9 empty] | 41714.79
|  |  | JDH3-02-008-L-73-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-02-25 | 2025-03-08 | 09-Aug-25 A | 2026-01-11 | 1921-05-30 12:29 | 1921-05-30 12:29 | 83429.58 | Remaining Total Cost | [18 empty] | 75608.06
|  |  | JDH3-02-008-L-73-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-02-25 | 2025-03-08 | 09-Aug-25 A | 2026-01-11 | 1921-05-30 12:29 | 1921-05-30 12:29 | 83429.58 | Actual Total Cost | [13 empty] | 3226.19 | 4425.13 | 170.2
|  |  | JDH3-02-008-L-73-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-03-03 | 2025-03-13 | 16-Aug-25 A | 2026-01-13 | 1937-06-21 15:50 | 1937-06-21 15:50 | 27375.33 | Planned Total Cost | [8 empty] | 6843.83 | [8 empty] | 5475.07 | 15056.43
|  |  | JDH3-02-008-L-73-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-03-03 | 2025-03-13 | 16-Aug-25 A | 2026-01-13 | 1937-06-21 15:50 | 1937-06-21 15:50 | 27375.33 | Remaining Total Cost | [18 empty] | 13687.66
|  |  | JDH3-02-008-L-73-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-03-03 | 2025-03-13 | 16-Aug-25 A | 2026-01-13 | 1937-06-21 15:50 | 1937-06-21 15:50 | 27375.33 | Actual Total Cost | [13 empty] | 5636.1 | 8051.56
|  |  | JDH3-02-008-L-73-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-03-05 | 2025-03-16 | 2026-01-04 | 2026-01-15 | 0 | 0 | 101679.79 | Planned Total Cost | [18 empty] | 101679.79
|  |  | JDH3-02-008-L-73-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-03-05 | 2025-03-16 | 2026-01-04 | 2026-01-15 | 0 | 0 | 101679.79 | Remaining Total Cost | [18 empty] | 101679.79
|  |  | JDH3-02-008-L-73-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-03-05 | 2025-03-16 | 2026-01-04 | 2026-01-15 | 0 | 0 | 101679.79 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-03-08 | 2025-03-18 | 2026-01-06 | 2026-01-18 | 0 | 0 | 107545.92 | Planned Total Cost | [18 empty] | 107545.92
|  |  | JDH3-02-008-L-73-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-03-08 | 2025-03-18 | 2026-01-06 | 2026-01-18 | 0 | 0 | 107545.92 | Remaining Total Cost | [18 empty] | 107545.92
|  |  | JDH3-02-008-L-73-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-03-08 | 2025-03-18 | 2026-01-06 | 2026-01-18 | 0 | 0 | 107545.92 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(ST)- Single Catchbasine Works |  | 2025-03-10 | 2025-03-25 | 2026-01-08 | 2026-01-25 | 0 | 0 | 86036.79 | Planned Total Cost | [18 empty] | 86036.79
|  |  | JDH3-02-008-L-73-(ST)- Single Catchbasine Works |  | 2025-03-10 | 2025-03-25 | 2026-01-08 | 2026-01-25 | 0 | 0 | 86036.79 | Remaining Total Cost | [18 empty] | 86036.79
|  |  | JDH3-02-008-L-73-(ST)- Single Catchbasine Works |  | 2025-03-10 | 2025-03-25 | 2026-01-08 | 2026-01-25 | 0 | 0 | 86036.79 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(ST)- Double Catchbasine Works |  | 2025-03-13 | 2025-03-24 | 2026-01-12 | 2026-01-24 | 0 | 0 | 181824.28 | Planned Total Cost | [18 empty] | 181824.28
|  |  | JDH3-02-008-L-73-(ST)- Double Catchbasine Works |  | 2025-03-13 | 2025-03-24 | 2026-01-12 | 2026-01-24 | 0 | 0 | 181824.28 | Remaining Total Cost | [18 empty] | 181824.28
|  |  | JDH3-02-008-L-73-(ST)- Double Catchbasine Works |  | 2025-03-13 | 2025-03-24 | 2026-01-12 | 2026-01-24 | 0 | 0 | 181824.28 | Actual Total Cost
|  |  | JDH3-02-008-L-73-TSE Network - TSE |  | 2025-03-13 | 2025-05-04 | 2026-01-12 | 2026-02-19 | 0 | 0 | 199568.52 | Planned Total Cost | [18 empty] | 140590.09 | 58978.43
|  |  | JDH3-02-008-L-73-TSE Network - TSE |  | 2025-03-13 | 2025-05-04 | 2026-01-12 | 2026-02-19 | 0 | 0 | 199568.52 | Remaining Total Cost | [18 empty] | 140590.09 | 58978.43
|  |  | JDH3-02-008-L-73-TSE Network - TSE |  | 2025-03-13 | 2025-05-04 | 2026-01-12 | 2026-02-19 | 0 | 0 | 199568.52 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-03-13 | 2025-04-27 | 2026-01-12 | 2026-02-10 | 0 | 0 | 13055.8 | Planned Total Cost | [18 empty] | 10444.64 | 2611.16
|  |  | JDH3-02-008-L-73-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-03-13 | 2025-04-27 | 2026-01-12 | 2026-02-10 | 0 | 0 | 13055.8 | Remaining Total Cost | [18 empty] | 10444.64 | 2611.16
|  |  | JDH3-02-008-L-73-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-03-13 | 2025-04-27 | 2026-01-12 | 2026-02-10 | 0 | 0 | 13055.8 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-03-16 | 2025-05-04 | 2026-01-14 | 2026-02-19 | 0 | 0 | 151311.29 | Planned Total Cost | [18 empty] | 116293.54 | 35017.76
|  |  | JDH3-02-008-L-73-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-03-16 | 2025-05-04 | 2026-01-14 | 2026-02-19 | 0 | 0 | 151311.29 | Remaining Total Cost | [18 empty] | 116293.54 | 35017.76
|  |  | JDH3-02-008-L-73-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-03-16 | 2025-05-04 | 2026-01-14 | 2026-02-19 | 0 | 0 | 151311.29 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(TSE)-Supply and install gate valves-100 mm |  | 2025-04-02 | 2025-04-08 | 2026-02-01 | 2026-02-08 | 0 | 0 | 1293.16 | Planned Total Cost | [19 empty] | 1293.16
|  |  | JDH3-02-008-L-73-(TSE)-Supply and install gate valves-100 mm |  | 2025-04-02 | 2025-04-08 | 2026-02-01 | 2026-02-08 | 0 | 0 | 1293.16 | Remaining Total Cost | [19 empty] | 1293.16
|  |  | JDH3-02-008-L-73-(TSE)-Supply and install gate valves-100 mm |  | 2025-04-02 | 2025-04-08 | 2026-02-01 | 2026-02-08 | 0 | 0 | 1293.16 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(TSE)-Supply and install gate valves-250 mm |  | 2025-04-02 | 2025-04-06 | 2026-02-01 | 2026-02-05 | 0 | 0 | 10264.45 | Planned Total Cost | [19 empty] | 10264.45
|  |  | JDH3-02-008-L-73-(TSE)-Supply and install gate valves-250 mm |  | 2025-04-02 | 2025-04-06 | 2026-02-01 | 2026-02-05 | 0 | 0 | 10264.45 | Remaining Total Cost | [19 empty] | 10264.45
|  |  | JDH3-02-008-L-73-(TSE)-Supply and install gate valves-250 mm |  | 2025-04-02 | 2025-04-06 | 2026-02-01 | 2026-02-05 | 0 | 0 | 10264.45 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2025-04-02 | 2025-04-06 | 2026-02-01 | 2026-02-05 | 0 | 0 | 9791.9 | Planned Total Cost | [19 empty] | 9791.9
|  |  | JDH3-02-008-L-73-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2025-04-02 | 2025-04-06 | 2026-02-01 | 2026-02-05 | 0 | 0 | 9791.9 | Remaining Total Cost | [19 empty] | 9791.9
|  |  | JDH3-02-008-L-73-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2025-04-02 | 2025-04-06 | 2026-02-01 | 2026-02-05 | 0 | 0 | 9791.9 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2025-03-20 | 2025-03-29 | 2026-01-19 | 2026-01-28 | 0 | 0 | 13851.92 | Planned Total Cost | [18 empty] | 13851.92
|  |  | JDH3-02-008-L-73-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2025-03-20 | 2025-03-29 | 2026-01-19 | 2026-01-28 | 0 | 0 | 13851.92 | Remaining Total Cost | [18 empty] | 13851.92
|  |  | JDH3-02-008-L-73-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2025-03-20 | 2025-03-29 | 2026-01-19 | 2026-01-28 | 0 | 0 | 13851.92 | Actual Total Cost
|  |  | JDH3-02-008-L-73-Potable Water Network - WT |  | 2025-03-16 | 2025-04-23 | 2026-01-14 | 2026-02-10 | 0 | 0 | 156545.05 | Planned Total Cost | [18 empty] | 125516.48 | 31028.57
|  |  | JDH3-02-008-L-73-Potable Water Network - WT |  | 2025-03-16 | 2025-04-23 | 2026-01-14 | 2026-02-10 | 0 | 0 | 156545.05 | Remaining Total Cost | [18 empty] | 125516.48 | 31028.57
|  |  | JDH3-02-008-L-73-Potable Water Network - WT |  | 2025-03-16 | 2025-04-23 | 2026-01-14 | 2026-02-10 | 0 | 0 | 156545.05 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-03-16 | 2025-04-08 | 2026-01-14 | 2026-02-08 | 0 | 0 | 5256.66 | Planned Total Cost | [18 empty] | 4731 | 525.67
|  |  | JDH3-02-008-L-73-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-03-16 | 2025-04-08 | 2026-01-14 | 2026-02-08 | 0 | 0 | 5256.66 | Remaining Total Cost | [18 empty] | 4731 | 525.67
|  |  | JDH3-02-008-L-73-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-03-16 | 2025-04-08 | 2026-01-14 | 2026-02-08 | 0 | 0 | 5256.66 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(WT)- Supply and install HDPE Pipes -225 mm depth from 0 to 1.5 m |  | 2025-03-18 | 2025-04-23 | 2026-01-17 | 2026-02-10 | 0 | 0 | 110714.24 | Planned Total Cost | [18 empty] | 84511.87 | 26202.37
|  |  | JDH3-02-008-L-73-(WT)- Supply and install HDPE Pipes -225 mm depth from 0 to 1.5 m |  | 2025-03-18 | 2025-04-23 | 2026-01-17 | 2026-02-10 | 0 | 0 | 110714.24 | Remaining Total Cost | [18 empty] | 84511.87 | 26202.37
|  |  | JDH3-02-008-L-73-(WT)- Supply and install HDPE Pipes -225 mm depth from 0 to 1.5 m |  | 2025-03-18 | 2025-04-23 | 2026-01-17 | 2026-02-10 | 0 | 0 | 110714.24 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(WT)- Supply and install gate valves -Diameter 200 mm |  | 2025-04-02 | 2025-04-06 | 2026-02-01 | 2026-02-05 | 0 | 0 | 4300.53 | Planned Total Cost | [19 empty] | 4300.53
|  |  | JDH3-02-008-L-73-(WT)- Supply and install gate valves -Diameter 200 mm |  | 2025-04-02 | 2025-04-06 | 2026-02-01 | 2026-02-05 | 0 | 0 | 4300.53 | Remaining Total Cost | [19 empty] | 4300.53
|  |  | JDH3-02-008-L-73-(WT)- Supply and install gate valves -Diameter 200 mm |  | 2025-04-02 | 2025-04-06 | 2026-02-01 | 2026-02-05 | 0 | 0 | 4300.53 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(WT)- Supply and install 3-out fire hydrant |  | 2025-03-22 | 2025-03-27 | 2026-01-20 | 2026-01-27 | 0 | 0 | 36273.61 | Planned Total Cost | [18 empty] | 36273.61
|  |  | JDH3-02-008-L-73-(WT)- Supply and install 3-out fire hydrant |  | 2025-03-22 | 2025-03-27 | 2026-01-20 | 2026-01-27 | 0 | 0 | 36273.61 | Remaining Total Cost | [18 empty] | 36273.61
|  |  | JDH3-02-008-L-73-(WT)- Supply and install 3-out fire hydrant |  | 2025-03-22 | 2025-03-27 | 2026-01-20 | 2026-01-27 | 0 | 0 | 36273.61 | Actual Total Cost
|  |  | JDH3-02-008-L-73-Street Lighting Network -SL |  | 2025-03-22 | 2025-04-14 | 2026-01-20 | 2026-02-14 | 0 | 0 | 178557.57 | Planned Total Cost | [18 empty] | 89619.04 | 88938.53
|  |  | JDH3-02-008-L-73-Street Lighting Network -SL |  | 2025-03-22 | 2025-04-14 | 2026-01-20 | 2026-02-14 | 0 | 0 | 178557.57 | Remaining Total Cost | [18 empty] | 89619.04 | 88938.53
|  |  | JDH3-02-008-L-73-Street Lighting Network -SL |  | 2025-03-22 | 2025-04-14 | 2026-01-20 | 2026-02-14 | 0 | 0 | 178557.57 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(STL)-Substation protection room including Protection poles |  | 2025-04-08 | 2025-04-14 | 2026-02-07 | 2026-02-14 | 0 | 0 | 28475.67 | Planned Total Cost | [19 empty] | 28475.67
|  |  | JDH3-02-008-L-73-(STL)-Substation protection room including Protection poles |  | 2025-04-08 | 2025-04-14 | 2026-02-07 | 2026-02-14 | 0 | 0 | 28475.67 | Remaining Total Cost | [19 empty] | 28475.67
|  |  | JDH3-02-008-L-73-(STL)-Substation protection room including Protection poles |  | 2025-04-08 | 2025-04-14 | 2026-02-07 | 2026-02-14 | 0 | 0 | 28475.67 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx25 mm² |  | 2025-03-22 | 2025-04-08 | 2026-01-20 | 2026-02-07 | 0 | 0 | 41496.32 | Planned Total Cost | [18 empty] | 37346.69 | 4149.63
|  |  | JDH3-02-008-L-73-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx25 mm² |  | 2025-03-22 | 2025-04-08 | 2026-01-20 | 2026-02-07 | 0 | 0 | 41496.32 | Remaining Total Cost | [18 empty] | 37346.69 | 4149.63
|  |  | JDH3-02-008-L-73-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx25 mm² |  | 2025-03-22 | 2025-04-08 | 2026-01-20 | 2026-02-07 | 0 | 0 | 41496.32 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(STL)- Supply,install,connect and test single core PVC insulated copper 16mm2 |  | 2025-03-30 | 2025-04-05 | 2026-01-27 | 2026-02-03 | 0 | 0 | 5856.36 | Planned Total Cost | [18 empty] | 4919.34 | 937.02
|  |  | JDH3-02-008-L-73-(STL)- Supply,install,connect and test single core PVC insulated copper 16mm2 |  | 2025-03-30 | 2025-04-05 | 2026-01-27 | 2026-02-03 | 0 | 0 | 5856.36 | Remaining Total Cost | [18 empty] | 4919.34 | 937.02
|  |  | JDH3-02-008-L-73-(STL)- Supply,install,connect and test single core PVC insulated copper 16mm2 |  | 2025-03-30 | 2025-04-05 | 2026-01-27 | 2026-02-03 | 0 | 0 | 5856.36 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2025-03-25 | 2025-04-07 | 2026-01-24 | 2026-02-07 | 0 | 0 | 42963.59 | Planned Total Cost | [18 empty] | 26637.43 | 16326.16
|  |  | JDH3-02-008-L-73-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2025-03-25 | 2025-04-07 | 2026-01-24 | 2026-02-07 | 0 | 0 | 42963.59 | Remaining Total Cost | [18 empty] | 26637.43 | 16326.16
|  |  | JDH3-02-008-L-73-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2025-03-25 | 2025-04-07 | 2026-01-24 | 2026-02-07 | 0 | 0 | 42963.59 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-03-30 | 2025-03-31 | 2026-01-28 | 2026-01-31 | 0 | 0 | 6609.2 | Planned Total Cost | [18 empty] | 6609.2
|  |  | JDH3-02-008-L-73-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-03-30 | 2025-03-31 | 2026-01-28 | 2026-01-31 | 0 | 0 | 6609.2 | Remaining Total Cost | [18 empty] | 6609.2
|  |  | JDH3-02-008-L-73-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-03-30 | 2025-03-31 | 2026-01-28 | 2026-01-31 | 0 | 0 | 6609.2 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2025-04-01 | 2025-04-02 | 2026-01-31 | 2026-02-02 | 0 | 0 | 378.04 | Planned Total Cost | [18 empty] | 113.41 | 264.63
|  |  | JDH3-02-008-L-73-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2025-04-01 | 2025-04-02 | 2026-01-31 | 2026-02-02 | 0 | 0 | 378.04 | Remaining Total Cost | [18 empty] | 113.41 | 264.63
|  |  | JDH3-02-008-L-73-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2025-04-01 | 2025-04-02 | 2026-01-31 | 2026-02-02 | 0 | 0 | 378.04 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-2 × 150 mm |  | 2025-03-27 | 2025-04-05 | 2026-01-26 | 2026-02-04 | 0 | 0 | 2107.97 | Planned Total Cost | [18 empty] | 1781.23 | 326.73
|  |  | JDH3-02-008-L-73-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-2 × 150 mm |  | 2025-03-27 | 2025-04-05 | 2026-01-26 | 2026-02-04 | 0 | 0 | 2107.97 | Remaining Total Cost | [18 empty] | 1781.23 | 326.73
|  |  | JDH3-02-008-L-73-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-2 × 150 mm |  | 2025-03-27 | 2025-04-05 | 2026-01-26 | 2026-02-04 | 0 | 0 | 2107.97 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-03-30 | 2025-04-05 | 2026-01-28 | 2026-02-04 | 0 | 0 | 28978.73 | Planned Total Cost | [18 empty] | 11881.28 | 17097.45
|  |  | JDH3-02-008-L-73-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-03-30 | 2025-04-05 | 2026-01-28 | 2026-02-04 | 0 | 0 | 28978.73 | Remaining Total Cost | [18 empty] | 11881.28 | 17097.45
|  |  | JDH3-02-008-L-73-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-03-30 | 2025-04-05 | 2026-01-28 | 2026-02-04 | 0 | 0 | 28978.73 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2025-04-01 | 2025-04-07 | 2026-01-31 | 2026-02-07 | 0 | 0 | 5507.65 | Planned Total Cost | [18 empty] | 330.46 | 5177.2
|  |  | JDH3-02-008-L-73-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2025-04-01 | 2025-04-07 | 2026-01-31 | 2026-02-07 | 0 | 0 | 5507.65 | Remaining Total Cost | [18 empty] | 330.46 | 5177.2
|  |  | JDH3-02-008-L-73-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2025-04-01 | 2025-04-07 | 2026-01-31 | 2026-02-07 | 0 | 0 | 5507.65 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(STL)- Street Lighting panels |  | 2025-04-03 | 2025-04-09 | 2026-02-02 | 2026-02-09 | 0 | 0 | 14701.2 | Planned Total Cost | [19 empty] | 14701.2
|  |  | JDH3-02-008-L-73-(STL)- Street Lighting panels |  | 2025-04-03 | 2025-04-09 | 2026-02-02 | 2026-02-09 | 0 | 0 | 14701.2 | Remaining Total Cost | [19 empty] | 14701.2
|  |  | JDH3-02-008-L-73-(STL)- Street Lighting panels |  | 2025-04-03 | 2025-04-09 | 2026-02-02 | 2026-02-09 | 0 | 0 | 14701.2 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(STL)-Supply and installation of KWH meter mounting frame |  | 2025-04-06 | 2025-04-12 | 2026-02-04 | 2026-02-11 | 0 | 0 | 1482.83 | Planned Total Cost | [19 empty] | 1482.83
|  |  | JDH3-02-008-L-73-(STL)-Supply and installation of KWH meter mounting frame |  | 2025-04-06 | 2025-04-12 | 2026-02-04 | 2026-02-11 | 0 | 0 | 1482.83 | Remaining Total Cost | [19 empty] | 1482.83
|  |  | JDH3-02-008-L-73-(STL)-Supply and installation of KWH meter mounting frame |  | 2025-04-06 | 2025-04-12 | 2026-02-04 | 2026-02-11 | 0 | 0 | 1482.83 | Actual Total Cost
|  |  | JDH3-02-008-L-73-Telecommunications Network - TC |  | 2025-04-09 | 2025-05-06 | 2026-02-08 | 2026-02-22 | 0 | 0 | 73686.85 | Planned Total Cost | [19 empty] | 73686.85
|  |  | JDH3-02-008-L-73-Telecommunications Network - TC |  | 2025-04-09 | 2025-05-06 | 2026-02-08 | 2026-02-22 | 0 | 0 | 73686.85 | Remaining Total Cost | [19 empty] | 73686.85
|  |  | JDH3-02-008-L-73-Telecommunications Network - TC |  | 2025-04-09 | 2025-05-06 | 2026-02-08 | 2026-02-22 | 0 | 0 | 73686.85 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-04-09 | 2025-05-06 | 2026-02-08 | 2026-02-22 | 0 | 0 | 49961.57 | Planned Total Cost | [19 empty] | 49961.57
|  |  | JDH3-02-008-L-73-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-04-09 | 2025-05-06 | 2026-02-08 | 2026-02-22 | 0 | 0 | 49961.57 | Remaining Total Cost | [19 empty] | 49961.57
|  |  | JDH3-02-008-L-73-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-04-09 | 2025-05-06 | 2026-02-08 | 2026-02-22 | 0 | 0 | 49961.57 | Actual Total Cost
|  |  | JDH3-02-008-L-73-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-04-24 | 2025-04-30 | 2026-02-10 | 2026-02-17 | 0 | 0 | 23725.29 | Planned Total Cost | [19 empty] | 23725.29
|  |  | JDH3-02-008-L-73-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-04-24 | 2025-04-30 | 2026-02-10 | 2026-02-17 | 0 | 0 | 23725.29 | Remaining Total Cost | [19 empty] | 23725.29
|  |  | JDH3-02-008-L-73-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-04-24 | 2025-04-30 | 2026-02-10 | 2026-02-17 | 0 | 0 | 23725.29 | Actual Total Cost
|  |  | Z02-2 |  | 2024-08-17 | 2025-06-14 | 05-Jan-25 A | 2026-02-22 | 9071204.82 | 9071204.78 | 12159362.48 | Planned Total Cost |  | 274378.38 | 852715.86 | 795419.13 | 806777.06 | 2359908.32 | 1428554.96 | 802594.83 | 359619.78 | 403819.22 | 69817.31 |  |  |  | 278131.31 | 2113541.09 | 1196057.33 | 268837.71 | 7982.38 | 141207.8
|  |  | Z02-2 |  | 2024-08-17 | 2025-06-14 | 05-Jan-25 A | 2026-02-22 | 9071204.82 | 9071204.78 | 12159362.48 | Remaining Total Cost | [15 empty] | 2043174.9 | 780109.52 | 115683.07 | 7982.38 | 141207.8
|  |  | Z02-2 |  | 2024-08-17 | 2025-06-14 | 05-Jan-25 A | 2026-02-22 | 9071204.82 | 9071204.78 | 12159362.48 | Actual Total Cost | [6 empty] | 853649.54 | 1093579.25 | 1027146.15 | 346385.23 | 686809.08 | 927349.48 | 1063652.95 | 2062228.38 | 997944.36 | 12460.36
|  |  | RCB |  | 2024-08-24 | 2025-01-04 | 22-May-25 A | 2025-10-15 | 2061-06-10 05:31 | 2061-06-10 05:46 | 178585.09 | Planned Total Cost |  | 15743.86 | 2775.5 |  |  | 40447.88 | [9 empty] | 119617.86
|  |  | RCB |  | 2024-08-24 | 2025-01-04 | 22-May-25 A | 2025-10-15 | 2061-06-10 05:31 | 2061-06-10 05:46 | 178585.09 | Remaining Total Cost | [15 empty] | 119617.86
|  |  | RCB |  | 2024-08-24 | 2025-01-04 | 22-May-25 A | 2025-10-15 | 2061-06-10 05:31 | 2061-06-10 05:46 | 178585.09 | Actual Total Cost | [10 empty] | 5708.38 | 40536.57 | 12722.29
|  |  | JDH3-02-008-RCB-Z02-2-Storm Network - ST |  | 2024-08-24 | 2025-01-04 | 22-May-25 A | 2025-10-15 | 2061-06-10 05:31 | 2061-06-10 05:46 | 178585.09 | Planned Total Cost |  | 15743.86 | 2775.5 |  |  | 40447.88 | [9 empty] | 119617.86
|  |  | JDH3-02-008-RCB-Z02-2-Storm Network - ST |  | 2024-08-24 | 2025-01-04 | 22-May-25 A | 2025-10-15 | 2061-06-10 05:31 | 2061-06-10 05:46 | 178585.09 | Remaining Total Cost | [15 empty] | 119617.86
|  |  | JDH3-02-008-RCB-Z02-2-Storm Network - ST |  | 2024-08-24 | 2025-01-04 | 22-May-25 A | 2025-10-15 | 2061-06-10 05:31 | 2061-06-10 05:46 | 178585.09 | Actual Total Cost | [10 empty] | 5708.38 | 40536.57 | 12722.29
|  |  | JDH3-02-008-RCB-Z02-2-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-08-24 | 2024-09-05 | 22-May-25 A | 2025-10-13 | 1950-09-13 08:38 | 1950-09-13 08:38 | 65290.64 | Planned Total Cost |  | 15743.86 | 2775.5 | [12 empty] | 46771.28
|  |  | JDH3-02-008-RCB-Z02-2-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-08-24 | 2024-09-05 | 22-May-25 A | 2025-10-13 | 1950-09-13 08:38 | 1950-09-13 08:38 | 65290.64 | Remaining Total Cost | [15 empty] | 46771.28
|  |  | JDH3-02-008-RCB-Z02-2-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-08-24 | 2024-09-05 | 22-May-25 A | 2025-10-13 | 1950-09-13 08:38 | 1950-09-13 08:38 | 65290.64 | Actual Total Cost | [10 empty] | 2139.45 | 14067 | 2312.91
|  |  | JDH3-02-008-RCB-Z02-2-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-12-22 | 2025-01-04 | 2025-10-02 | 2025-10-15 | 0 | 0 | 32956.82 | Planned Total Cost | [15 empty] | 32956.82
|  |  | JDH3-02-008-RCB-Z02-2-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-12-22 | 2025-01-04 | 2025-10-02 | 2025-10-15 | 0 | 0 | 32956.82 | Remaining Total Cost | [15 empty] | 32956.82
|  |  | JDH3-02-008-RCB-Z02-2-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-12-22 | 2025-01-04 | 2025-10-02 | 2025-10-15 | 0 | 0 | 32956.82 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z02-2-(ST)- Single Catchbasine Works |  | 2024-12-24 | 2025-01-01 | 2025-10-05 | 2025-10-13 | 0 | 0 | 32751.9 | Planned Total Cost | [15 empty] | 32751.9
|  |  | JDH3-02-008-RCB-Z02-2-(ST)- Single Catchbasine Works |  | 2024-12-24 | 2025-01-01 | 2025-10-05 | 2025-10-13 | 0 | 0 | 32751.9 | Remaining Total Cost | [15 empty] | 32751.9
|  |  | JDH3-02-008-RCB-Z02-2-(ST)- Single Catchbasine Works |  | 2024-12-24 | 2025-01-01 | 2025-10-05 | 2025-10-13 | 0 | 0 | 32751.9 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z02-2-(ST)- Double Catchbasine Works |  | 2024-12-22 | 2024-12-30 | 22-May-25 A | 2025-10-06 | 2010-09-26 21:07 | 2010-09-26 21:07 | 47585.74 | Planned Total Cost | [5 empty] | 40447.88 | [9 empty] | 7137.86
|  |  | JDH3-02-008-RCB-Z02-2-(ST)- Double Catchbasine Works |  | 2024-12-22 | 2024-12-30 | 22-May-25 A | 2025-10-06 | 2010-09-26 21:07 | 2010-09-26 21:07 | 47585.74 | Remaining Total Cost | [15 empty] | 7137.86
|  |  | JDH3-02-008-RCB-Z02-2-(ST)- Double Catchbasine Works |  | 2024-12-22 | 2024-12-30 | 22-May-25 A | 2025-10-06 | 2010-09-26 21:07 | 2010-09-26 21:07 | 47585.74 | Actual Total Cost | [10 empty] | 3568.93 | 26469.57 | 10409.38
|  |  | C-16 |  | 2024-08-27 | 2025-05-03 | 05-Jan-25 A | 2026-02-10 | 3634341.11 | 3634341.11 | 4954286.26 | Planned Total Cost |  |  | 849940.36 | 686642.81 | 318851.58 | 202767.73 | 92693.2 | 751192.2 | 359619.78 | 322581.89 |  |  |  |  | 50125.22 | 816766.33 | 275338.46 | 196126.16 | 7982.38 | 23658.15
|  |  | C-16 |  | 2024-08-27 | 2025-05-03 | 05-Jan-25 A | 2026-02-10 | 3634341.11 | 3634341.11 | 4954286.26 | Remaining Total Cost | [15 empty] | 897246.12 | 275375.41 | 115683.07 | 7982.38 | 23658.15
|  |  | C-16 |  | 2024-08-27 | 2025-05-03 | 05-Jan-25 A | 2026-02-10 | 3634341.11 | 3634341.11 | 4954286.26 | Actual Total Cost | [6 empty] | 192009.77 | 240608.54 | 215095.16 | 156585.7 | 178197.23 | 445018.73 | 331821.82 | 1504400.12 | 360205.3 | 10398.74
|  |  | JDH3-02-008-C-16-Storm Network - ST |  | 2024-09-04 | 2025-03-12 | 05-Jan-25 A | 2025-11-26 | 2911218.3 | 2911218.31 | 4036949.49 | Planned Total Cost |  |  | 849940.36 | 686642.81 | 318851.58 | 202767.73 | 92693.2 | 751192.2 | 109549.17 | [5 empty] | 50125.22 | 816766.33 | 158420.89
|  |  | JDH3-02-008-C-16-Storm Network - ST |  | 2024-09-04 | 2025-03-12 | 05-Jan-25 A | 2025-11-26 | 2911218.3 | 2911218.31 | 4036949.49 | Remaining Total Cost | [15 empty] | 897246.12 | 228485.06
|  |  | JDH3-02-008-C-16-Storm Network - ST |  | 2024-09-04 | 2025-03-12 | 05-Jan-25 A | 2025-11-26 | 2911218.3 | 2911218.31 | 4036949.49 | Actual Total Cost | [6 empty] | 192009.77 | 240608.54 | 215095.16 | 156585.7 | 178197.23 | 445018.73 | 331821.82 | 886835.21 | 255164.39 | 9881.77
|  |  | JDH3-02-008-C-16-(ST)-Box Culvert |  | 2024-09-21 | 2025-01-30 | 05-Jan-25 A | 2025-11-09 | 1493817.93 | 1493817.94 | 1837908.44 | Planned Total Cost |  |  | 227119.53 | 672698.15 | 318851.58 | 202767.73 | 92693.2 | [7 empty] | 48566.74 | 214503.09 | 60708.42
|  |  | JDH3-02-008-C-16-(ST)-Box Culvert |  | 2024-09-21 | 2025-01-30 | 05-Jan-25 A | 2025-11-09 | 1493817.93 | 1493817.94 | 1837908.44 | Remaining Total Cost | [15 empty] | 283382.07 | 60708.42
|  |  | JDH3-02-008-C-16-(ST)-Box Culvert |  | 2024-09-21 | 2025-01-30 | 05-Jan-25 A | 2025-11-09 | 1493817.93 | 1493817.94 | 1837908.44 | Actual Total Cost | [6 empty] | 187701.66 | 218017.19 | 215095.16 | 152159.24 | 124737.29 | 134614.15 | 90246.77 | 205645.59 | 159402.29 | 6198.61
|  |  | JDH3-02-008-C-16-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2024-09-21 | 2025-01-06 | 05-Jan-25 A | 2025-10-15 | 1471797.77 | 1471797.78 | 1514130.19 | Planned Total Cost |  |  | 227119.53 | 672698.15 | 318851.58 | 202767.73 | 92693.2
|  |  | JDH3-02-008-C-16-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2024-09-21 | 2025-01-06 | 05-Jan-25 A | 2025-10-15 | 1471797.77 | 1471797.78 | 1514130.19 | Remaining Total Cost | [15 empty] | 42332.41
|  |  | JDH3-02-008-C-16-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2024-09-21 | 2025-01-06 | 05-Jan-25 A | 2025-10-15 | 1471797.77 | 1471797.78 | 1514130.19 | Actual Total Cost | [6 empty] | 187701.66 | 218017.19 | 215095.16 | 152159.24 | 124737.29 | 134614.15 | 90246.77 | 205645.59 | 138262.93 | 5317.81
|  |  | JDH3-02-008-C-16-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2024-10-07 | 2025-01-30 | 03-Sep-25 A | 2025-11-09 | 1960-04-14 03:50 | 1960-04-14 03:50 | 323778.25 | Planned Total Cost | [14 empty] | 48566.74 | 214503.09 | 60708.42
|  |  | JDH3-02-008-C-16-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2024-10-07 | 2025-01-30 | 03-Sep-25 A | 2025-11-09 | 1960-04-14 03:50 | 1960-04-14 03:50 | 323778.25 | Remaining Total Cost | [15 empty] | 241049.67 | 60708.42
|  |  | JDH3-02-008-C-16-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2024-10-07 | 2025-01-30 | 03-Sep-25 A | 2025-11-09 | 1960-04-14 03:50 | 1960-04-14 03:50 | 323778.25 | Actual Total Cost | [14 empty] | 21139.35 | 880.81
|  |  | JDH3-02-008-C-16-(ST)-NetWork |  | 2024-09-04 | 2025-03-12 | 27-Jan-25 A | 2025-11-26 | 1417400.36 | 1417400.37 | 2199041.05 | Planned Total Cost |  |  | 622820.83 | 13944.66 |  |  |  | 751192.2 | 109549.17 | [5 empty] | 1558.48 | 602263.25 | 97712.46
|  |  | JDH3-02-008-C-16-(ST)-NetWork |  | 2024-09-04 | 2025-03-12 | 27-Jan-25 A | 2025-11-26 | 1417400.36 | 1417400.37 | 2199041.05 | Remaining Total Cost | [15 empty] | 613864.05 | 167776.63
|  |  | JDH3-02-008-C-16-(ST)-NetWork |  | 2024-09-04 | 2025-03-12 | 27-Jan-25 A | 2025-11-26 | 1417400.36 | 1417400.37 | 2199041.05 | Actual Total Cost | [6 empty] | 4308.12 | 22591.34 |  | 4426.46 | 53459.94 | 310404.58 | 241575.05 | 681189.62 | 95762.1 | 3683.16
|  |  | JDH3-02-008-C-16-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-02-01 | 2025-03-12 | 03-Aug-25 A | 2025-11-26 | 2247-09-30 17:46 | 2247-09-30 17:46 | 239649.3 | Planned Total Cost | [7 empty] | 191719.44 | [8 empty] | 47929.86
|  |  | JDH3-02-008-C-16-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-02-01 | 2025-03-12 | 03-Aug-25 A | 2025-11-26 | 2247-09-30 17:46 | 2247-09-30 17:46 | 239649.3 | Remaining Total Cost | [16 empty] | 112635.56
|  |  | JDH3-02-008-C-16-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-02-01 | 2025-03-12 | 03-Aug-25 A | 2025-11-26 | 2247-09-30 17:46 | 2247-09-30 17:46 | 239649.3 | Actual Total Cost | [13 empty] | 55495.69 | 68869.23 | 2648.82
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-02-04 | 2025-03-06 | 2025-11-10 | 2025-11-20 | 0 | 0 | 49782.6 | Planned Total Cost | [16 empty] | 49782.6
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-02-04 | 2025-03-06 | 2025-11-10 | 2025-11-20 | 0 | 0 | 49782.6 | Remaining Total Cost | [16 empty] | 49782.6
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-02-04 | 2025-03-06 | 2025-11-10 | 2025-11-20 | 0 | 0 | 49782.6 | Actual Total Cost
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2025-03-06 | 05-Jul-25 A | 20-Aug-25 A | 2017-03-29 03:36 | 2017-03-29 03:50 | 42823.15 | Planned Total Cost |  |  | 6222.23 |  |  |  |  | 30760.12 | 4282.32 | [5 empty] | 1558.48
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2025-03-06 | 05-Jul-25 A | 20-Aug-25 A | 2017-03-29 03:36 | 2017-03-29 03:50 | 42823.15 | Remaining Total Cost
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2025-03-06 | 05-Jul-25 A | 20-Aug-25 A | 2017-03-29 03:36 | 2017-03-29 03:50 | 42823.15 | Actual Total Cost | [12 empty] | 6222.23 | 36600.93
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-09-07 | 2025-02-19 | 30-Jun-25 A | 23-Aug-25 A | 2127-11-22 09:36 | 2127-11-22 09:22 | 83237.4 | Planned Total Cost |  |  | 74970.87 |  |  |  |  | 8266.52
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-09-07 | 2025-02-19 | 30-Jun-25 A | 23-Aug-25 A | 2127-11-22 09:36 | 2127-11-22 09:22 | 83237.4 | Remaining Total Cost
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-09-07 | 2025-02-19 | 30-Jun-25 A | 23-Aug-25 A | 2127-11-22 09:36 | 2127-11-22 09:22 | 83237.4 | Actual Total Cost | [11 empty] | 1040.47 | 73930.4 | 8266.52
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2024-09-14 | 2025-03-10 | 05-Jul-25 A | 2025-11-20 | 2446-07-16 23:46 | 2446-07-16 23:46 | 203987.32 | Planned Total Cost |  |  | 22973.1 |  |  |  |  | 160615.49 | 20398.73
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2024-09-14 | 2025-03-10 | 05-Jul-25 A | 2025-11-20 | 2446-07-16 23:46 | 2446-07-16 23:46 | 203987.32 | Remaining Total Cost | [16 empty] | 4365.33
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2024-09-14 | 2025-03-10 | 05-Jul-25 A | 2025-11-20 | 2446-07-16 23:46 | 2446-07-16 23:46 | 203987.32 | Actual Total Cost | [12 empty] | 22973.1 | 164280.27 | 11910.53 | 458.1
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2025-03-12 | 27-Jan-25 A | 2025-11-20 | 1989-05-03 04:19 | 1989-05-03 04:34 | 33624.32 | Planned Total Cost |  |  | 31325.92 | [5 empty] | 2298.41
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2025-03-12 | 27-Jan-25 A | 2025-11-20 | 1989-05-03 04:19 | 1989-05-03 04:34 | 33624.32 | Remaining Total Cost | [16 empty] | 993.14
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2025-03-12 | 27-Jan-25 A | 2025-11-20 | 1989-05-03 04:19 | 1989-05-03 04:34 | 33624.32 | Actual Total Cost | [6 empty] | 4308.12 | 22591.34 |  | 4426.46 |  |  |  | 352.78 | 917.22 | 35.28
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 0.00 to 1.50 m |  | 2024-09-04 | 2025-02-23 | 12-Jun-25 A | 15-Aug-25 A | 1996-01-13 05:17 | 1996-01-13 05:02 | 35077.22 | Planned Total Cost |  |  | 28061.77 |  |  |  |  | 7015.44
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 0.00 to 1.50 m |  | 2024-09-04 | 2025-02-23 | 12-Jun-25 A | 15-Aug-25 A | 1996-01-13 05:17 | 1996-01-13 05:02 | 35077.22 | Remaining Total Cost
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 0.00 to 1.50 m |  | 2024-09-04 | 2025-02-23 | 12-Jun-25 A | 15-Aug-25 A | 1996-01-13 05:17 | 1996-01-13 05:02 | 35077.22 | Actual Total Cost | [11 empty] | 24334.82 | 3726.95 | 7015.44
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2025-02-26 | 12-Jun-25 A | 2025-10-02 | 212992.81 | 212992.82 | 214615.31 | Planned Total Cost |  |  | 122641.44 |  |  |  |  | 91973.87
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2025-02-26 | 12-Jun-25 A | 2025-10-02 | 212992.81 | 212992.82 | 214615.31 | Remaining Total Cost | [15 empty] | 1622.49
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2025-02-26 | 12-Jun-25 A | 2025-10-02 | 212992.81 | 212992.82 | 214615.31 | Actual Total Cost | [11 empty] | 86998.08 | 35643.36 | 77286.65 | 12580.85 | 483.88
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2025-03-03 | 21-May-25 A | 20-Aug-25 A | 360287.29 | 360287.29 | 360287.29 | Planned Total Cost |  |  | 288229.83 |  |  |  |  | 45035.91 | 27021.55
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2025-03-03 | 21-May-25 A | 20-Aug-25 A | 360287.29 | 360287.29 | 360287.29 | Remaining Total Cost
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2025-03-03 | 21-May-25 A | 20-Aug-25 A | 360287.29 | 360287.29 | 360287.29 | Actual Total Cost | [10 empty] | 31525.14 | 157625.69 | 99079.01 | 72057.46
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2025-02-11 | 2025-03-06 | 11-Aug-25 A | 23-Aug-25 A | 2184-02-27 19:26 | 2184-02-27 19:26 | 103788.81 | Planned Total Cost | [7 empty] | 93409.93 | 10378.88
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2025-02-11 | 2025-03-06 | 11-Aug-25 A | 23-Aug-25 A | 2184-02-27 19:26 | 2184-02-27 19:26 | 103788.81 | Remaining Total Cost
|  |  | JDH3-02-008-C-16-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2025-02-11 | 2025-03-06 | 11-Aug-25 A | 23-Aug-25 A | 2184-02-27 19:26 | 2184-02-27 19:26 | 103788.81 | Actual Total Cost | [13 empty] | 103788.81
|  |  | JDH3-02-008-C-16-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-10-01 | 2025-02-24 | 25-May-25 A | 2025-10-08 | 1928-07-19 16:48 | 1928-07-19 16:48 | 20857.39 | Planned Total Cost |  |  |  | 3372.47 |  |  |  | 7056.23 | [7 empty] | 10428.7
|  |  | JDH3-02-008-C-16-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-10-01 | 2025-02-24 | 25-May-25 A | 2025-10-08 | 1928-07-19 16:48 | 1928-07-19 16:48 | 20857.39 | Remaining Total Cost | [15 empty] | 10428.7
|  |  | JDH3-02-008-C-16-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-10-01 | 2025-02-24 | 25-May-25 A | 2025-10-08 | 1928-07-19 16:48 | 1928-07-19 16:48 | 20857.39 | Actual Total Cost | [10 empty] | 1264.68 | 2107.79 |  | 7056.23
|  |  | JDH3-02-008-C-16-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2024-10-03 | 2025-02-26 | 25-May-25 A | 2025-10-11 | 2016-08-30 05:17 | 2016-08-30 05:31 | 82125.99 | Planned Total Cost |  |  |  | 10572.19 |  |  |  | 32040.03 | [7 empty] | 39513.77
|  |  | JDH3-02-008-C-16-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2024-10-03 | 2025-02-26 | 25-May-25 A | 2025-10-11 | 2016-08-30 05:17 | 2016-08-30 05:31 | 82125.99 | Remaining Total Cost | [15 empty] | 39513.77
|  |  | JDH3-02-008-C-16-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2024-10-03 | 2025-02-26 | 25-May-25 A | 2025-10-11 | 2016-08-30 05:17 | 2016-08-30 05:31 | 82125.99 | Actual Total Cost | [10 empty] | 2521.75 | 8050.45 |  | 32040.03
|  |  | JDH3-02-008-C-16-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-02-18 | 2025-03-03 | 2025-10-04 | 2025-10-18 | 0 | 0 | 186412.95 | Planned Total Cost | [15 empty] | 186412.95
|  |  | JDH3-02-008-C-16-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-02-18 | 2025-03-03 | 2025-10-04 | 2025-10-18 | 0 | 0 | 186412.95 | Remaining Total Cost | [15 empty] | 186412.95
|  |  | JDH3-02-008-C-16-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-02-18 | 2025-03-03 | 2025-10-04 | 2025-10-18 | 0 | 0 | 186412.95 | Actual Total Cost
|  |  | JDH3-02-008-C-16-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2024-09-04 | 2025-03-06 | 25-May-25 A | 2025-10-20 | 2350-07-04 06:14 | 2350-07-04 06:00 | 193582.66 | Planned Total Cost |  |  | 48395.66 |  |  |  |  | 70980.31 | 45169.29 | [6 empty] | 29037.4
|  |  | JDH3-02-008-C-16-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2024-09-04 | 2025-03-06 | 25-May-25 A | 2025-10-20 | 2350-07-04 06:14 | 2350-07-04 06:00 | 193582.66 | Remaining Total Cost | [15 empty] | 29037.4
|  |  | JDH3-02-008-C-16-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2024-09-04 | 2025-03-06 | 25-May-25 A | 2025-10-20 | 2350-07-04 06:14 | 2350-07-04 06:00 | 193582.66 | Actual Total Cost | [10 empty] | 18148.37 | 30247.29 |  | 116149.59
|  |  | JDH3-02-008-C-16-(ST)- Single Catchbasine Works |  | 2025-02-20 | 2025-03-10 | 16-Aug-25 A | 2025-10-23 | 1906-05-28 14:10 | 1906-05-28 14:10 | 82126.03 | Planned Total Cost | [7 empty] | 12318.9 | [7 empty] | 69807.12
|  |  | JDH3-02-008-C-16-(ST)- Single Catchbasine Works |  | 2025-02-20 | 2025-03-10 | 16-Aug-25 A | 2025-10-23 | 1906-05-28 14:10 | 1906-05-28 14:10 | 82126.03 | Remaining Total Cost | [15 empty] | 79785.44
|  |  | JDH3-02-008-C-16-(ST)- Single Catchbasine Works |  | 2025-02-20 | 2025-03-10 | 16-Aug-25 A | 2025-10-23 | 1906-05-28 14:10 | 1906-05-28 14:10 | 82126.03 | Actual Total Cost | [13 empty] | 799.23 | 1484.28 | 57.09
|  |  | JDH3-02-008-C-16-(ST)- Double Catchbasine Works |  | 2025-02-24 | 2025-03-12 | 2025-10-06 | 2025-10-26 | 0 | 0 | 204552.31 | Planned Total Cost | [15 empty] | 204552.31
|  |  | JDH3-02-008-C-16-(ST)- Double Catchbasine Works |  | 2025-02-24 | 2025-03-12 | 2025-10-06 | 2025-10-26 | 0 | 0 | 204552.31 | Remaining Total Cost | [15 empty] | 204552.31
|  |  | JDH3-02-008-C-16-(ST)- Double Catchbasine Works |  | 2025-02-24 | 2025-03-12 | 2025-10-06 | 2025-10-26 | 0 | 0 | 204552.31 | Actual Total Cost
|  |  | JDH3-02-008-C-16-(ST)-PIPES ENCASEMENT |  | 2025-02-13 | 2025-03-04 | 2025-10-02 | 2025-10-21 | 0 | 0 | 62511 | Planned Total Cost | [15 empty] | 62511
|  |  | JDH3-02-008-C-16-(ST)-PIPES ENCASEMENT |  | 2025-02-13 | 2025-03-04 | 2025-10-02 | 2025-10-21 | 0 | 0 | 62511 | Remaining Total Cost | [15 empty] | 62511
|  |  | JDH3-02-008-C-16-(ST)-PIPES ENCASEMENT |  | 2025-02-13 | 2025-03-04 | 2025-10-02 | 2025-10-21 | 0 | 0 | 62511 | Actual Total Cost
|  |  | JDH3-02-008-C-16-TSE Network - TSE |  | 2025-03-13 | 2025-04-19 | 09-Aug-25 A | 2026-02-10 | 642679.72 | 642679.7 | 832239.29 | Planned Total Cost | [8 empty] | 250070.61 | 322581.89 | [6 empty] | 112263.19 | 115683.07 | 7982.38 | 23658.15
|  |  | JDH3-02-008-C-16-TSE Network - TSE |  | 2025-03-13 | 2025-04-19 | 09-Aug-25 A | 2026-02-10 | 642679.72 | 642679.7 | 832239.29 | Remaining Total Cost | [16 empty] | 42235.96 | 115683.07 | 7982.38 | 23658.15
|  |  | JDH3-02-008-C-16-TSE Network - TSE |  | 2025-03-13 | 2025-04-19 | 09-Aug-25 A | 2026-02-10 | 642679.72 | 642679.7 | 832239.29 | Actual Total Cost | [13 empty] | 537121.81 | 105040.91 | 516.97
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-03-13 | 2025-04-09 | 2025-11-27 | 2025-12-15 | 0 | 0 | 24373.16 | Planned Total Cost | [16 empty] | 5483.96 | 18889.2
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-03-13 | 2025-04-09 | 2025-11-27 | 2025-12-15 | 0 | 0 | 24373.16 | Remaining Total Cost | [16 empty] | 5483.96 | 18889.2
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-03-13 | 2025-04-09 | 2025-11-27 | 2025-12-15 | 0 | 0 | 24373.16 | Actual Total Cost
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-03-16 | 2025-04-09 | 2025-11-30 | 2025-12-17 | 0 | 0 | 212.43 | Planned Total Cost | [16 empty] | 21.24 | 191.19
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-03-16 | 2025-04-09 | 2025-11-30 | 2025-12-17 | 0 | 0 | 212.43 | Remaining Total Cost | [16 empty] | 21.24 | 191.19
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-03-16 | 2025-04-09 | 2025-11-30 | 2025-12-17 | 0 | 0 | 212.43 | Actual Total Cost
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2025-03-18 | 2025-04-09 | 2025-12-02 | 2025-12-20 | 0 | 0 | 21502.81 | Planned Total Cost | [17 empty] | 21502.81
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2025-03-18 | 2025-04-09 | 2025-12-02 | 2025-12-20 | 0 | 0 | 21502.81 | Remaining Total Cost | [17 empty] | 21502.81
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2025-03-18 | 2025-04-09 | 2025-12-02 | 2025-12-20 | 0 | 0 | 21502.81 | Actual Total Cost
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2025-03-20 | 2025-04-09 | 09-Aug-25 A | 20-Sep-25 A | 202950.94 | 202950.93 | 202950.94 | Planned Total Cost | [8 empty] | 162360.75 | 20295.09 | [6 empty] | 20295.09
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2025-03-20 | 2025-04-09 | 09-Aug-25 A | 20-Sep-25 A | 202950.94 | 202950.93 | 202950.94 | Remaining Total Cost
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2025-03-20 | 2025-04-09 | 09-Aug-25 A | 20-Sep-25 A | 202950.94 | 202950.93 | 202950.94 | Actual Total Cost | [13 empty] | 182655.84 | 20295.09
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2025-03-23 | 2025-04-02 | 11-Aug-25 A | 2025-11-20 | 2174-02-10 06:14 | 2174-02-10 06:14 | 102747.55 | Planned Total Cost | [8 empty] | 82198.04 | 10274.75 | [6 empty] | 10274.75
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2025-03-23 | 2025-04-02 | 11-Aug-25 A | 2025-11-20 | 2174-02-10 06:14 | 2174-02-10 06:14 | 102747.55 | Remaining Total Cost | [16 empty] | 2628.28
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2025-03-23 | 2025-04-02 | 11-Aug-25 A | 2025-11-20 | 2174-02-10 06:14 | 2174-02-10 06:14 | 102747.55 | Actual Total Cost | [13 empty] | 66310.87 | 33601.73 | 206.66
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 2.51 to 3.5 m |  | 2025-03-25 | 2025-04-05 | 31-Aug-25 A | 2025-11-23 | 1984-08-23 11:17 | 1984-08-23 11:17 | 34352.75 | Planned Total Cost | [16 empty] | 34352.75
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 2.51 to 3.5 m |  | 2025-03-25 | 2025-04-05 | 31-Aug-25 A | 2025-11-23 | 1984-08-23 11:17 | 1984-08-23 11:17 | 34352.75 | Remaining Total Cost | [16 empty] | 3435.27
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 2.51 to 3.5 m |  | 2025-03-25 | 2025-04-05 | 31-Aug-25 A | 2025-11-23 | 1984-08-23 11:17 | 1984-08-23 11:17 | 34352.75 | Actual Total Cost | [13 empty] | 2290.18 | 28627.29
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 3.51 to 4.5 m |  | 2025-03-27 | 2025-04-07 | 31-Aug-25 A | 2025-12-20 | 1927-06-23 20:24 | 1927-06-23 20:24 | 11152.06 | Planned Total Cost | [16 empty] | 10036.85 | 1115.21
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 3.51 to 4.5 m |  | 2025-03-27 | 2025-04-07 | 31-Aug-25 A | 2025-12-20 | 1927-06-23 20:24 | 1927-06-23 20:24 | 11152.06 | Remaining Total Cost | [17 empty] | 1115.21
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 3.51 to 4.5 m |  | 2025-03-27 | 2025-04-07 | 31-Aug-25 A | 2025-12-20 | 1927-06-23 20:24 | 1927-06-23 20:24 | 11152.06 | Actual Total Cost | [13 empty] | 743.47 | 9293.38
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 4.51 to 5.5 m |  | 2025-03-30 | 2025-04-09 | 31-Aug-25 A | 2025-12-22 | 1915-03-29 17:17 | 1915-03-29 17:17 | 6186.35 | Planned Total Cost | [16 empty] | 5567.72 | 618.64
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 4.51 to 5.5 m |  | 2025-03-30 | 2025-04-09 | 31-Aug-25 A | 2025-12-22 | 1915-03-29 17:17 | 1915-03-29 17:17 | 6186.35 | Remaining Total Cost | [17 empty] | 618.64
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 4.51 to 5.5 m |  | 2025-03-30 | 2025-04-09 | 31-Aug-25 A | 2025-12-22 | 1915-03-29 17:17 | 1915-03-29 17:17 | 6186.35 | Actual Total Cost | [13 empty] | 412.42 | 5155.3
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install GRP Pipes - 800 mm depth from 0 to 1.5 m |  | 2025-04-01 | 2025-04-12 | 20-Aug-25 A | 2025-12-24 | 1967-08-28 09:36 | 1967-08-28 09:36 | 30890.5 | Planned Total Cost | [9 empty] | 24712.4 | [6 empty] | 3089.05 | 3089.05
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install GRP Pipes - 800 mm depth from 0 to 1.5 m |  | 2025-04-01 | 2025-04-12 | 20-Aug-25 A | 2025-12-24 | 1967-08-28 09:36 | 1967-08-28 09:36 | 30890.5 | Remaining Total Cost | [16 empty] | 3089.05 | 3089.05
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install GRP Pipes - 800 mm depth from 0 to 1.5 m |  | 2025-04-01 | 2025-04-12 | 20-Aug-25 A | 2025-12-24 | 1967-08-28 09:36 | 1967-08-28 09:36 | 30890.5 | Actual Total Cost | [13 empty] | 24712.4
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install GRP Pipes - 800 mm depth from 1.51 to 2.5 m |  | 2025-04-03 | 2025-04-15 | 23-Aug-25 A | 2025-12-28 | 2218-11-30 16:34 | 2218-11-30 16:48 | 134354.53 | Planned Total Cost | [9 empty] | 120919.08 | [7 empty] | 13435.45
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install GRP Pipes - 800 mm depth from 1.51 to 2.5 m |  | 2025-04-03 | 2025-04-15 | 23-Aug-25 A | 2025-12-28 | 2218-11-30 16:34 | 2218-11-30 16:48 | 134354.53 | Remaining Total Cost | [16 empty] | 4436.38 | 13435.45
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install GRP Pipes - 800 mm depth from 1.51 to 2.5 m |  | 2025-04-03 | 2025-04-15 | 23-Aug-25 A | 2025-12-28 | 2218-11-30 16:34 | 2218-11-30 16:48 | 134354.53 | Actual Total Cost | [13 empty] | 108104.26 | 8068.13 | 310.31
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install GRP Pipes - 800 mm depth from 2.51 to 3.5 m |  | 2025-04-06 | 2025-04-16 | 25-Aug-25 A | 2025-12-30 | 2054-05-06 18:00 | 2054-05-06 18:00 | 70469.69 | Planned Total Cost | [9 empty] | 56375.75 | [6 empty] | 7046.97 | 7046.97
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install GRP Pipes - 800 mm depth from 2.51 to 3.5 m |  | 2025-04-06 | 2025-04-16 | 25-Aug-25 A | 2025-12-30 | 2054-05-06 18:00 | 2054-05-06 18:00 | 70469.69 | Remaining Total Cost | [16 empty] | 7046.97 | 7046.97
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install GRP Pipes - 800 mm depth from 2.51 to 3.5 m |  | 2025-04-06 | 2025-04-16 | 25-Aug-25 A | 2025-12-30 | 2054-05-06 18:00 | 2054-05-06 18:00 | 70469.69 | Actual Total Cost | [13 empty] | 56375.75
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install GRP Pipes - 800 mm depth from 3.51 to 4.5 m |  | 2025-04-08 | 2025-04-19 | 20-Aug-25 A | 2026-01-01 | 2113-03-21 19:12 | 2113-03-21 18:58 | 97348.5 | Planned Total Cost | [9 empty] | 77878.8 | [6 empty] | 9734.85 | 4867.42 | 4867.42
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install GRP Pipes - 800 mm depth from 3.51 to 4.5 m |  | 2025-04-08 | 2025-04-19 | 20-Aug-25 A | 2026-01-01 | 2113-03-21 19:12 | 2113-03-21 18:58 | 97348.5 | Remaining Total Cost | [16 empty] | 9734.85 | 4867.42 | 4867.42
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install GRP Pipes - 800 mm depth from 3.51 to 4.5 m |  | 2025-04-08 | 2025-04-19 | 20-Aug-25 A | 2026-01-01 | 2113-03-21 19:12 | 2113-03-21 18:58 | 97348.5 | Actual Total Cost | [13 empty] | 77878.79
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install GRP Pipes - 800 mm depth from 4.51 to 5.5 m |  | 2025-03-27 | 2025-04-07 | 16-Aug-25 A | 2026-01-04 | 1948-04-14 20:10 | 1948-04-14 19:55 | 22047.3 | Planned Total Cost | [8 empty] | 5511.82 | 12126.01 | [6 empty] | 2204.73 |  | 2204.73
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install GRP Pipes - 800 mm depth from 4.51 to 5.5 m |  | 2025-03-27 | 2025-04-07 | 16-Aug-25 A | 2026-01-04 | 1948-04-14 20:10 | 1948-04-14 19:55 | 22047.3 | Remaining Total Cost | [16 empty] | 2204.73 |  | 2204.73
|  |  | JDH3-02-008-C-16-(TSE)- Supply and install GRP Pipes - 800 mm depth from 4.51 to 5.5 m |  | 2025-03-27 | 2025-04-07 | 16-Aug-25 A | 2026-01-04 | 1948-04-14 20:10 | 1948-04-14 19:55 | 22047.3 | Actual Total Cost | [13 empty] | 17637.83
|  |  | JDH3-02-008-C-16-(TSE)-Supply and install gate valves-100 mm |  | 2025-04-03 | 2025-04-07 | 2025-12-07 | 2025-12-10 | 0 | 0 | 10345.28 | Planned Total Cost | [17 empty] | 10345.28
|  |  | JDH3-02-008-C-16-(TSE)-Supply and install gate valves-100 mm |  | 2025-04-03 | 2025-04-07 | 2025-12-07 | 2025-12-10 | 0 | 0 | 10345.28 | Remaining Total Cost | [17 empty] | 10345.28
|  |  | JDH3-02-008-C-16-(TSE)-Supply and install gate valves-100 mm |  | 2025-04-03 | 2025-04-07 | 2025-12-07 | 2025-12-10 | 0 | 0 | 10345.28 | Actual Total Cost
|  |  | JDH3-02-008-C-16-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2025-04-06 | 2025-04-09 | 2026-02-07 | 2026-02-10 | 0 | 0 | 23658.15 | Planned Total Cost | [19 empty] | 23658.15
|  |  | JDH3-02-008-C-16-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2025-04-06 | 2025-04-09 | 2026-02-07 | 2026-02-10 | 0 | 0 | 23658.15 | Remaining Total Cost | [19 empty] | 23658.15
|  |  | JDH3-02-008-C-16-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2025-04-06 | 2025-04-09 | 2026-02-07 | 2026-02-10 | 0 | 0 | 23658.15 | Actual Total Cost
|  |  | JDH3-02-008-C-16-(TSE)-Supply and install of Wash-out valves-150 mm. |  | 2025-03-29 | 2025-04-01 | 2025-12-09 | 2025-12-13 | 0 | 0 | 11748.58 | Planned Total Cost | [17 empty] | 11748.58
|  |  | JDH3-02-008-C-16-(TSE)-Supply and install of Wash-out valves-150 mm. |  | 2025-03-29 | 2025-04-01 | 2025-12-09 | 2025-12-13 | 0 | 0 | 11748.58 | Remaining Total Cost | [17 empty] | 11748.58
|  |  | JDH3-02-008-C-16-(TSE)-Supply and install of Wash-out valves-150 mm. |  | 2025-03-29 | 2025-04-01 | 2025-12-09 | 2025-12-13 | 0 | 0 | 11748.58 | Actual Total Cost
|  |  | JDH3-02-008-C-16-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2025-03-30 | 2025-04-07 | 2025-11-27 | 2026-01-06 | 0 | 0 | 9102.3 | Planned Total Cost | [16 empty] | 2275.57 | 5916.49 | 910.23
|  |  | JDH3-02-008-C-16-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2025-03-30 | 2025-04-07 | 2025-11-27 | 2026-01-06 | 0 | 0 | 9102.3 | Remaining Total Cost | [16 empty] | 2275.57 | 5916.49 | 910.23
|  |  | JDH3-02-008-C-16-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2025-03-30 | 2025-04-07 | 2025-11-27 | 2026-01-06 | 0 | 0 | 9102.3 | Actual Total Cost
|  |  | JDH3-02-008-C-16-(TSE)- Supply and Construct Wash-out Valves Chamber on 450-630 mm Diameter pipeline |  | 2025-04-01 | 2025-04-09 | 2025-11-30 | 2025-12-08 | 0 | 0 | 18796.42 | Planned Total Cost | [16 empty] | 1879.64 | 16916.78
|  |  | JDH3-02-008-C-16-(TSE)- Supply and Construct Wash-out Valves Chamber on 450-630 mm Diameter pipeline |  | 2025-04-01 | 2025-04-09 | 2025-11-30 | 2025-12-08 | 0 | 0 | 18796.42 | Remaining Total Cost | [16 empty] | 1879.64 | 16916.78
|  |  | JDH3-02-008-C-16-(TSE)- Supply and Construct Wash-out Valves Chamber on 450-630 mm Diameter pipeline |  | 2025-04-01 | 2025-04-09 | 2025-11-30 | 2025-12-08 | 0 | 0 | 18796.42 | Actual Total Cost
|  |  | JDH3-02-008-C-16-Street Lighting Network -SL |  | 2025-04-20 | 2025-05-03 | 04-Aug-25 A | 2025-11-24 | 80443.1 | 2120-03-29 02:24 | 85097.48 | Planned Total Cost | [16 empty] | 4654.39 | 80443.1
|  |  | JDH3-02-008-C-16-Street Lighting Network -SL |  | 2025-04-20 | 2025-05-03 | 04-Aug-25 A | 2025-11-24 | 80443.1 | 2120-03-29 02:24 | 85097.48 | Remaining Total Cost | [16 empty] | 4654.39
|  |  | JDH3-02-008-C-16-Street Lighting Network -SL |  | 2025-04-20 | 2025-05-03 | 04-Aug-25 A | 2025-11-24 | 80443.1 | 2120-03-29 02:24 | 85097.48 | Actual Total Cost | [13 empty] | 80443.1
|  |  | JDH3-02-008-C-16-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2025-04-20 | 2025-05-03 | 04-Aug-25 A | 2025-11-24 | 2014-09-07 12:00 | 2014-09-07 12:00 | 46543.89 | Planned Total Cost | [16 empty] | 4654.39 | 41889.5
|  |  | JDH3-02-008-C-16-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2025-04-20 | 2025-05-03 | 04-Aug-25 A | 2025-11-24 | 2014-09-07 12:00 | 2014-09-07 12:00 | 46543.89 | Remaining Total Cost | [16 empty] | 4654.39
|  |  | JDH3-02-008-C-16-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2025-04-20 | 2025-05-03 | 04-Aug-25 A | 2025-11-24 | 2014-09-07 12:00 | 2014-09-07 12:00 | 46543.89 | Actual Total Cost | [13 empty] | 41889.5
|  |  | JDH3-02-008-C-16-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-04-27 | 2025-04-28 | 21-Aug-25 A | 24-Aug-25 A | 1919-08-07 23:17 | 1919-08-07 23:17 | 7159.97 | Planned Total Cost | [17 empty] | 7159.97
|  |  | JDH3-02-008-C-16-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-04-27 | 2025-04-28 | 21-Aug-25 A | 24-Aug-25 A | 1919-08-07 23:17 | 1919-08-07 23:17 | 7159.97 | Remaining Total Cost
|  |  | JDH3-02-008-C-16-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-04-27 | 2025-04-28 | 21-Aug-25 A | 24-Aug-25 A | 1919-08-07 23:17 | 1919-08-07 23:17 | 7159.97 | Actual Total Cost | [13 empty] | 7159.97
|  |  | JDH3-02-008-C-16-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-04-22 | 2025-04-28 | 04-Aug-25 A | 20-Aug-25 A | 1985-12-12 15:07 | 1985-12-12 15:07 | 31393.63 | Planned Total Cost | [17 empty] | 31393.63
|  |  | JDH3-02-008-C-16-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-04-22 | 2025-04-28 | 04-Aug-25 A | 20-Aug-25 A | 1985-12-12 15:07 | 1985-12-12 15:07 | 31393.63 | Remaining Total Cost
|  |  | JDH3-02-008-C-16-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-04-22 | 2025-04-28 | 04-Aug-25 A | 20-Aug-25 A | 1985-12-12 15:07 | 1985-12-12 15:07 | 31393.63 | Actual Total Cost | [13 empty] | 31393.63
|  |  | L-74 |  | 2024-08-17 | 2025-05-26 | 05-Jan-25 A | 2026-02-10 | 3383045.29 | 3383045.24 | 4235108.12 | Planned Total Cost |  | 258634.52 |  | 108776.32 | 487925.48 | 1623094.95 | 464934.33 | 7734.69 |  | 61137.33 |  |  |  |  | 228006.1 | 877314.75 |  |  |  | 117549.65
|  |  | L-74 |  | 2024-08-17 | 2025-05-26 | 05-Jan-25 A | 2026-02-10 | 3383045.29 | 3383045.24 | 4235108.12 | Remaining Total Cost | [15 empty] | 734513.19 |  |  |  | 117549.65
|  |  | L-74 |  | 2024-08-17 | 2025-05-26 | 05-Jan-25 A | 2026-02-10 | 3383045.29 | 3383045.24 | 4235108.12 | Actual Total Cost | [6 empty] | 522745.47 | 555393.21 | 440953.04 | 147054.62 | 477931.09 | 321304.51 | 330472.6 | 301523.84 | 285493.47 | 173.4
|  |  | JDH3-02-008-L-74-Sewage Network - SS |  | 2024-12-15 | 2025-01-12 | 05-Jan-25 A | 2025-10-06 | 371179.58 | 371179.59 | 375317.14 | Planned Total Cost | [5 empty] | 324411.16 | 46768.42 | [8 empty] | 4137.56
|  |  | JDH3-02-008-L-74-Sewage Network - SS |  | 2024-12-15 | 2025-01-12 | 05-Jan-25 A | 2025-10-06 | 371179.58 | 371179.59 | 375317.14 | Remaining Total Cost | [15 empty] | 4137.56
|  |  | JDH3-02-008-L-74-Sewage Network - SS |  | 2024-12-15 | 2025-01-12 | 05-Jan-25 A | 2025-10-06 | 371179.58 | 371179.59 | 375317.14 | Actual Total Cost | [6 empty] | 95683.98 | 112877.71 | 8396.21 | 28634.11 | 36414.9 | 10559.06 |  | 78613.61
|  |  | JDH3-02-008-L-74-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 0 to 1.5 m. |  | 2024-12-15 | 2024-12-25 | 05-Jan-25 A | 15-Feb-25 A | 1961-08-25 15:50 | 1961-08-25 15:50 | 22518.66 | Planned Total Cost | [5 empty] | 22518.66
|  |  | JDH3-02-008-L-74-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 0 to 1.5 m. |  | 2024-12-15 | 2024-12-25 | 05-Jan-25 A | 15-Feb-25 A | 1961-08-25 15:50 | 1961-08-25 15:50 | 22518.66 | Remaining Total Cost
|  |  | JDH3-02-008-L-74-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 0 to 1.5 m. |  | 2024-12-15 | 2024-12-25 | 05-Jan-25 A | 15-Feb-25 A | 1961-08-25 15:50 | 1961-08-25 15:50 | 22518.66 | Actual Total Cost | [6 empty] | 19351.97 | 3166.69
|  |  | JDH3-02-008-L-74-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2024-12-15 | 2025-01-01 | 13-Jan-25 A | 13-Mar-25 A | 2153-07-14 22:19 | 2153-07-14 22:19 | 92603.93 | Planned Total Cost | [5 empty] | 90288.83 | 2315.1
|  |  | JDH3-02-008-L-74-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2024-12-15 | 2025-01-01 | 13-Jan-25 A | 13-Mar-25 A | 2153-07-14 22:19 | 2153-07-14 22:19 | 92603.93 | Remaining Total Cost
|  |  | JDH3-02-008-L-74-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2024-12-15 | 2025-01-01 | 13-Jan-25 A | 13-Mar-25 A | 2153-07-14 22:19 | 2153-07-14 22:19 | 92603.93 | Actual Total Cost | [6 empty] | 36414.57 | 51269.78 | 4919.58
|  |  | JDH3-02-008-L-74-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2024-12-15 | 2024-12-28 | 16-Jan-25 A | 13-Mar-25 A | 2153-10-29 05:02 | 2153-10-29 04:48 | 92710.21 | Planned Total Cost | [5 empty] | 92710.21
|  |  | JDH3-02-008-L-74-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2024-12-15 | 2024-12-28 | 16-Jan-25 A | 13-Mar-25 A | 2153-10-29 05:02 | 2153-10-29 04:48 | 92710.21 | Remaining Total Cost
|  |  | JDH3-02-008-L-74-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2024-12-15 | 2024-12-28 | 16-Jan-25 A | 13-Mar-25 A | 2153-10-29 05:02 | 2153-10-29 04:48 | 92710.21 | Actual Total Cost | [6 empty] | 35925.2 | 53308.37 | 3476.63
|  |  | JDH3-02-008-L-74-(SS)-MH WORKS from 0.00 to 1.50 @ 1200 mm |  | 2024-12-15 | 2024-12-25 | 22-Jan-25 A | 28-Jun-25 A | 1949-12-18 05:17 | 1949-12-18 05:31 | 18250.22 | Planned Total Cost | [5 empty] | 18250.22
|  |  | JDH3-02-008-L-74-(SS)-MH WORKS from 0.00 to 1.50 @ 1200 mm |  | 2024-12-15 | 2024-12-25 | 22-Jan-25 A | 28-Jun-25 A | 1949-12-18 05:17 | 1949-12-18 05:31 | 18250.22 | Remaining Total Cost
|  |  | JDH3-02-008-L-74-(SS)-MH WORKS from 0.00 to 1.50 @ 1200 mm |  | 2024-12-15 | 2024-12-25 | 22-Jan-25 A | 28-Jun-25 A | 1949-12-18 05:17 | 1949-12-18 05:31 | 18250.22 | Actual Total Cost | [6 empty] | 3992.24 | 5132.88 |  | 399.22 | 6900.87 | 1825.02
|  |  | JDH3-02-008-L-74-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2024-12-26 | 2025-01-12 | 02-Aug-25 A | 2025-10-04 | 1927-02-14 06:14 | 1927-02-14 06:00 | 10428.7 | Planned Total Cost | [5 empty] | 7039.37 | 2867.89 | [8 empty] | 521.43
|  |  | JDH3-02-008-L-74-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2024-12-26 | 2025-01-12 | 02-Aug-25 A | 2025-10-04 | 1927-02-14 06:14 | 1927-02-14 06:00 | 10428.7 | Remaining Total Cost | [15 empty] | 521.43
|  |  | JDH3-02-008-L-74-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2024-12-26 | 2025-01-12 | 02-Aug-25 A | 2025-10-04 | 1927-02-14 06:14 | 1927-02-14 06:00 | 10428.7 | Actual Total Cost | [13 empty] | 9907.25
|  |  | JDH3-02-008-L-74-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm with back drop |  | 2024-12-15 | 2024-12-30 | 10-Apr-25 A | 28-Jun-25 A | 1935-09-08 20:53 | 1935-09-08 20:53 | 13035.87 | Planned Total Cost | [5 empty] | 13035.87
|  |  | JDH3-02-008-L-74-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm with back drop |  | 2024-12-15 | 2024-12-30 | 10-Apr-25 A | 28-Jun-25 A | 1935-09-08 20:53 | 1935-09-08 20:53 | 13035.87 | Remaining Total Cost
|  |  | JDH3-02-008-L-74-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm with back drop |  | 2024-12-15 | 2024-12-30 | 10-Apr-25 A | 28-Jun-25 A | 1935-09-08 20:53 | 1935-09-08 20:53 | 13035.87 | Actual Total Cost | [9 empty] | 6477.2 | 4603.29 | 1955.38
|  |  | JDH3-02-008-L-74-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2024-12-15 | 2024-12-25 | 20-Apr-25 A | 28-Jun-25 A | 1967-10-23 03:50 | 1967-10-23 04:05 | 24768.16 | Planned Total Cost | [5 empty] | 24768.16
|  |  | JDH3-02-008-L-74-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2024-12-15 | 2024-12-25 | 20-Apr-25 A | 28-Jun-25 A | 1967-10-23 03:50 | 1967-10-23 04:05 | 24768.16 | Remaining Total Cost
|  |  | JDH3-02-008-L-74-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2024-12-15 | 2024-12-25 | 20-Apr-25 A | 28-Jun-25 A | 1967-10-23 03:50 | 1967-10-23 04:05 | 24768.16 | Actual Total Cost | [9 empty] | 7507.85 | 14783.5 | 2476.82
|  |  | JDH3-02-008-L-74-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm with back drop |  | 2024-12-15 | 2024-12-30 | 10-Apr-25 A | 28-Jun-25 A | 1978-07-07 21:50 | 1978-07-07 22:05 | 28678.91 | Planned Total Cost | [5 empty] | 28678.91
|  |  | JDH3-02-008-L-74-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm with back drop |  | 2024-12-15 | 2024-12-30 | 10-Apr-25 A | 28-Jun-25 A | 1978-07-07 21:50 | 1978-07-07 22:05 | 28678.91 | Remaining Total Cost
|  |  | JDH3-02-008-L-74-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm with back drop |  | 2024-12-15 | 2024-12-30 | 10-Apr-25 A | 28-Jun-25 A | 1978-07-07 21:50 | 1978-07-07 22:05 | 28678.91 | Actual Total Cost | [9 empty] | 14249.84 | 10127.24 | 4301.84
|  |  | JDH3-02-008-L-74-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2024-12-29 | 2025-01-12 | 04-Aug-25 A | 2025-10-06 | 2088-02-08 08:38 | 2088-02-08 08:38 | 72322.48 | Planned Total Cost | [5 empty] | 27120.93 | 41585.43 | [8 empty] | 3616.12
|  |  | JDH3-02-008-L-74-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2024-12-29 | 2025-01-12 | 04-Aug-25 A | 2025-10-06 | 2088-02-08 08:38 | 2088-02-08 08:38 | 72322.48 | Remaining Total Cost | [15 empty] | 3616.12
|  |  | JDH3-02-008-L-74-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2024-12-29 | 2025-01-12 | 04-Aug-25 A | 2025-10-06 | 2088-02-08 08:38 | 2088-02-08 08:38 | 72322.48 | Actual Total Cost | [13 empty] | 68706.36
|  |  | JDH3-02-008-L-74-Storm Network - ST |  | 2024-12-15 | 2025-01-28 | 08-Jan-25 A | 2025-10-30 | 1306745.49 | 1306745.49 | 1757725.22 | Planned Total Cost | [5 empty] | 1237089.36 | 69656.13 | [8 empty] | 450979.73
|  |  | JDH3-02-008-L-74-Storm Network - ST |  | 2024-12-15 | 2025-01-28 | 08-Jan-25 A | 2025-10-30 | 1306745.49 | 1306745.49 | 1757725.22 | Remaining Total Cost | [15 empty] | 450979.73
|  |  | JDH3-02-008-L-74-Storm Network - ST |  | 2024-12-15 | 2025-01-28 | 08-Jan-25 A | 2025-10-30 | 1306745.49 | 1306745.49 | 1757725.22 | Actual Total Cost | [6 empty] | 407103.26 | 300449.74 | 181000.57 | 103385.46 | 180236.72 | 90640.13 | 14041.78 | 29887.84
|  |  | JDH3-02-008-L-74-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-12-15 | 2025-01-11 | 05-Mar-25 A | 17-Aug-25 A | 220044.51 | 220044.51 | 220044.51 | Planned Total Cost | [5 empty] | 216423.75 | 3620.76
|  |  | JDH3-02-008-L-74-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-12-15 | 2025-01-11 | 05-Mar-25 A | 17-Aug-25 A | 220044.51 | 220044.51 | 220044.51 | Remaining Total Cost
|  |  | JDH3-02-008-L-74-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-12-15 | 2025-01-11 | 05-Mar-25 A | 17-Aug-25 A | 220044.51 | 220044.51 | 220044.51 | Actual Total Cost | [8 empty] | 102835.53 | 69981.02 | 9451.2 | 19712.5 | 14041.78 | 4022.48
|  |  | JDH3-02-008-L-74-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-12-15 | 2024-12-26 | 14-Jan-25 A | 13-Mar-25 A | 2172-05-19 12:29 | 2172-05-19 12:14 | 99487.52 | Planned Total Cost | [5 empty] | 99487.52
|  |  | JDH3-02-008-L-74-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-12-15 | 2024-12-26 | 14-Jan-25 A | 13-Mar-25 A | 2172-05-19 12:29 | 2172-05-19 12:14 | 99487.52 | Remaining Total Cost
|  |  | JDH3-02-008-L-74-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-12-15 | 2024-12-26 | 14-Jan-25 A | 13-Mar-25 A | 2172-05-19 12:29 | 2172-05-19 12:14 | 99487.52 | Actual Total Cost | [6 empty] | 55961.73 | 39795 | 3730.78
|  |  | JDH3-02-008-L-74-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-12-15 | 2024-12-25 | 14-Jan-25 A | 23-Feb-25 A | 2012-04-29 02:24 | 2012-04-29 02:10 | 41028.1 | Planned Total Cost | [5 empty] | 41028.1
|  |  | JDH3-02-008-L-74-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-12-15 | 2024-12-25 | 14-Jan-25 A | 23-Feb-25 A | 2012-04-29 02:24 | 2012-04-29 02:10 | 41028.1 | Remaining Total Cost
|  |  | JDH3-02-008-L-74-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-12-15 | 2024-12-25 | 14-Jan-25 A | 23-Feb-25 A | 2012-04-29 02:24 | 2012-04-29 02:10 | 41028.1 | Actual Total Cost | [6 empty] | 29873.58 | 11154.51
|  |  | JDH3-02-008-L-74-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2024-12-15 | 2024-12-25 | 14-Jan-25 A | 23-Feb-25 A | 2073-01-13 18:14 | 2073-01-13 18:29 | 63202.76 | Planned Total Cost | [5 empty] | 63202.76
|  |  | JDH3-02-008-L-74-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2024-12-15 | 2024-12-25 | 14-Jan-25 A | 23-Feb-25 A | 2073-01-13 18:14 | 2073-01-13 18:29 | 63202.76 | Remaining Total Cost
|  |  | JDH3-02-008-L-74-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2024-12-15 | 2024-12-25 | 14-Jan-25 A | 23-Feb-25 A | 2073-01-13 18:14 | 2073-01-13 18:29 | 63202.76 | Actual Total Cost | [6 empty] | 46019.51 | 17183.26
|  |  | JDH3-02-008-L-74-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-12-15 | 2025-01-09 | 08-Jan-25 A | 04-Mar-25 A | 267800.07 | 267800.07 | 267800.07 | Planned Total Cost | [5 empty] | 227630.06 | 40170.01
|  |  | JDH3-02-008-L-74-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-12-15 | 2025-01-09 | 08-Jan-25 A | 04-Mar-25 A | 267800.07 | 267800.07 | 267800.07 | Remaining Total Cost
|  |  | JDH3-02-008-L-74-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-12-15 | 2025-01-09 | 08-Jan-25 A | 04-Mar-25 A | 267800.07 | 267800.07 | 267800.07 | Actual Total Cost | [6 empty] | 167375.04 | 95961.7 | 4463.34
|  |  | JDH3-02-008-L-74-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-12-15 | 2024-12-25 | 21-Jan-25 A | 10-Mar-25 A | 2189-10-30 12:00 | 2189-10-30 11:46 | 105860.5 | Planned Total Cost | [5 empty] | 105860.5
|  |  | JDH3-02-008-L-74-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-12-15 | 2024-12-25 | 21-Jan-25 A | 10-Mar-25 A | 2189-10-30 12:00 | 2189-10-30 11:46 | 105860.5 | Remaining Total Cost
|  |  | JDH3-02-008-L-74-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-12-15 | 2024-12-25 | 21-Jan-25 A | 10-Mar-25 A | 2189-10-30 12:00 | 2189-10-30 11:46 | 105860.5 | Actual Total Cost | [6 empty] | 14555.82 | 74984.51 | 16320.16
|  |  | JDH3-02-008-L-74-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 2.51 to 3.50 m |  | 2024-12-15 | 2024-12-25 | 14-Jan-25 A | 25-Feb-25 A | 2139-05-17 09:22 | 2139-05-17 09:22 | 87431.39 | Planned Total Cost | [5 empty] | 87431.39
|  |  | JDH3-02-008-L-74-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 2.51 to 3.50 m |  | 2024-12-15 | 2024-12-25 | 14-Jan-25 A | 25-Feb-25 A | 2139-05-17 09:22 | 2139-05-17 09:22 | 87431.39 | Remaining Total Cost
|  |  | JDH3-02-008-L-74-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 2.51 to 3.50 m |  | 2024-12-15 | 2024-12-25 | 14-Jan-25 A | 25-Feb-25 A | 2139-05-17 09:22 | 2139-05-17 09:22 | 87431.39 | Actual Total Cost | [6 empty] | 63660.98 | 23770.41
|  |  | JDH3-02-008-L-74-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-12-15 | 2025-01-11 | 22-Jan-25 A | 2025-10-04 | 2234-01-23 18:14 | 2234-01-23 18:14 | 135573.07 | Planned Total Cost | [5 empty] | 122015.76 | [9 empty] | 13557.31
|  |  | JDH3-02-008-L-74-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-12-15 | 2025-01-11 | 22-Jan-25 A | 2025-10-04 | 2234-01-23 18:14 | 2234-01-23 18:14 | 135573.07 | Remaining Total Cost | [15 empty] | 13557.31
|  |  | JDH3-02-008-L-74-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-12-15 | 2025-01-11 | 22-Jan-25 A | 2025-10-04 | 2234-01-23 18:14 | 2234-01-23 18:14 | 135573.07 | Actual Total Cost | [6 empty] | 16946.63 | 20124.13 | 28597.45 | 2118.33 | 28173.78 | 26055.44
|  |  | JDH3-02-008-L-74-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2024-12-15 | 2025-01-13 | 22-Jan-25 A | 2025-10-06 | 2150-07-18 19:26 | 2150-07-18 19:41 | 101679.79 | Planned Total Cost | [5 empty] | 91511.81 | [9 empty] | 10167.98
|  |  | JDH3-02-008-L-74-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2024-12-15 | 2025-01-13 | 22-Jan-25 A | 2025-10-06 | 2150-07-18 19:26 | 2150-07-18 19:41 | 101679.79 | Remaining Total Cost | [15 empty] | 10167.98
|  |  | JDH3-02-008-L-74-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2024-12-15 | 2025-01-13 | 22-Jan-25 A | 2025-10-06 | 2150-07-18 19:26 | 2150-07-18 19:41 | 101679.79 | Actual Total Cost | [6 empty] | 12709.98 | 17476.22 | 20653.71 |  | 35587.93 | 5083.99
|  |  | JDH3-02-008-L-74-(ST)- Single Catchbasine Works |  | 2024-12-17 | 2025-01-14 | 22-Mar-25 A | 2025-10-09 | 2100-03-22 06:29 | 2100-03-22 06:29 | 86036.79 | Planned Total Cost | [5 empty] | 66482.97 | 6648.3 | [8 empty] | 12905.52
|  |  | JDH3-02-008-L-74-(ST)- Single Catchbasine Works |  | 2024-12-17 | 2025-01-14 | 22-Mar-25 A | 2025-10-09 | 2100-03-22 06:29 | 2100-03-22 06:29 | 86036.79 | Remaining Total Cost | [15 empty] | 12905.52
|  |  | JDH3-02-008-L-74-(ST)- Single Catchbasine Works |  | 2024-12-17 | 2025-01-14 | 22-Mar-25 A | 2025-10-09 | 2100-03-22 06:29 | 2100-03-22 06:29 | 86036.79 | Actual Total Cost | [8 empty] | 4399.61 | 31286.1 | 30797.26 |  |  | 6648.3
|  |  | JDH3-02-008-L-74-(ST)- Double Catchbasine Works |  | 2024-12-21 | 2025-01-14 | 10-May-25 A | 2025-10-07 | 2270-03-31 19:26 | 2270-03-31 19:26 | 159096.24 | Planned Total Cost | [5 empty] | 116014.75 | 19217.06 | [8 empty] | 23864.44
|  |  | JDH3-02-008-L-74-(ST)- Double Catchbasine Works |  | 2024-12-21 | 2025-01-14 | 10-May-25 A | 2025-10-07 | 2270-03-31 19:26 | 2270-03-31 19:26 | 159096.24 | Remaining Total Cost | [15 empty] | 23864.44
|  |  | JDH3-02-008-L-74-(ST)- Double Catchbasine Works |  | 2024-12-21 | 2025-01-14 | 10-May-25 A | 2025-10-07 | 2270-03-31 19:26 | 2270-03-31 19:26 | 159096.24 | Actual Total Cost | [10 empty] | 76226.55 | 39788.2 |  | 19217.06
|  |  | JDH3-02-008-L-74-(ST)-PIPES ENCASEMENT |  | 2025-01-07 | 2025-01-09 | 2025-10-02 | 2025-10-05 | 0 | 0 | 10418.5 | Planned Total Cost | [15 empty] | 10418.5
|  |  | JDH3-02-008-L-74-(ST)-PIPES ENCASEMENT |  | 2025-01-07 | 2025-01-09 | 2025-10-02 | 2025-10-05 | 0 | 0 | 10418.5 | Remaining Total Cost | [15 empty] | 10418.5
|  |  | JDH3-02-008-L-74-(ST)-PIPES ENCASEMENT |  | 2025-01-07 | 2025-01-09 | 2025-10-02 | 2025-10-05 | 0 | 0 | 10418.5 | Actual Total Cost
|  |  | JDH3-02-008-L-74-(ST)-Excavation for cutting material |  | 2024-12-31 | 2025-01-08 | 2025-10-02 | 2025-10-11 | 0 | 0 | 137309.08 | Planned Total Cost | [15 empty] | 137309.08
|  |  | JDH3-02-008-L-74-(ST)-Excavation for cutting material |  | 2024-12-31 | 2025-01-08 | 2025-10-02 | 2025-10-11 | 0 | 0 | 137309.08 | Remaining Total Cost | [15 empty] | 137309.08
|  |  | JDH3-02-008-L-74-(ST)-Excavation for cutting material |  | 2024-12-31 | 2025-01-08 | 2025-10-02 | 2025-10-11 | 0 | 0 | 137309.08 | Actual Total Cost
|  |  | JDH3-02-008-L-74-(ST)-Filling with imported material |  | 2025-01-09 | 2025-01-28 | 2025-10-12 | 2025-10-30 | 0 | 0 | 242756.91 | Planned Total Cost | [15 empty] | 242756.91
|  |  | JDH3-02-008-L-74-(ST)-Filling with imported material |  | 2025-01-09 | 2025-01-28 | 2025-10-12 | 2025-10-30 | 0 | 0 | 242756.91 | Remaining Total Cost | [15 empty] | 242756.91
|  |  | JDH3-02-008-L-74-(ST)-Filling with imported material |  | 2025-01-09 | 2025-01-28 | 2025-10-12 | 2025-10-30 | 0 | 0 | 242756.91 | Actual Total Cost
|  |  | JDH3-02-008-L-74-TSE Network - TSE |  | 2024-11-13 | 2025-02-09 | 07-Jan-25 A | 2026-02-10 | 551355.42 | 551355.38 | 711470.8 | Planned Total Cost |  |  |  |  | 487925.48 | 56121.73 | 7308.21 | [8 empty] | 42565.72 |  |  |  | 117549.65
|  |  | JDH3-02-008-L-74-TSE Network - TSE |  | 2024-11-13 | 2025-02-09 | 07-Jan-25 A | 2026-02-10 | 551355.42 | 551355.38 | 711470.8 | Remaining Total Cost | [15 empty] | 42565.72 |  |  |  | 117549.65
|  |  | JDH3-02-008-L-74-TSE Network - TSE |  | 2024-11-13 | 2025-02-09 | 07-Jan-25 A | 2026-02-10 | 551355.42 | 551355.38 | 711470.8 | Actual Total Cost | [6 empty] | 10134.32 |  |  |  | 253458.73 | 165066.82 | 116890.13 | 5805.38
|  |  | JDH3-02-008-L-74-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-12-23 | 2025-01-20 | 01-May-25 A | 26-Aug-25 A | 1957-01-07 10:34 | 1957-01-07 10:19 | 20827.44 | Planned Total Cost | [5 empty] | 13519.23 | 7308.21
|  |  | JDH3-02-008-L-74-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-12-23 | 2025-01-20 | 01-May-25 A | 26-Aug-25 A | 1957-01-07 10:34 | 1957-01-07 10:19 | 20827.44 | Remaining Total Cost
|  |  | JDH3-02-008-L-74-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-12-23 | 2025-01-20 | 01-May-25 A | 26-Aug-25 A | 1957-01-07 10:34 | 1957-01-07 10:19 | 20827.44 | Actual Total Cost | [10 empty] | 7675.71 | 5897.75 | 1448.59 | 5805.38
|  |  | JDH3-02-008-L-74-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2024-11-13 | 2024-11-30 | 01-May-25 A | 31-Jul-25 A | 282310.43 | 282310.43 | 282310.43 | Planned Total Cost |  |  |  |  | 282310.43
|  |  | JDH3-02-008-L-74-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2024-11-13 | 2024-11-30 | 01-May-25 A | 31-Jul-25 A | 282310.43 | 282310.43 | 282310.43 | Remaining Total Cost
|  |  | JDH3-02-008-L-74-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 0 to 1.5 m |  | 2024-11-13 | 2024-11-30 | 01-May-25 A | 31-Jul-25 A | 282310.43 | 282310.43 | 282310.43 | Actual Total Cost | [10 empty] | 105278.27 | 86289.53 | 90742.64
|  |  | JDH3-02-008-L-74-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2024-11-13 | 2024-11-24 | 01-May-25 A | 31-Jul-25 A | 2170-11-15 02:24 | 2170-11-15 02:10 | 98936.1 | Planned Total Cost |  |  |  |  | 98936.1
|  |  | JDH3-02-008-L-74-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2024-11-13 | 2024-11-24 | 01-May-25 A | 31-Jul-25 A | 2170-11-15 02:24 | 2170-11-15 02:10 | 98936.1 | Remaining Total Cost
|  |  | JDH3-02-008-L-74-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2024-11-13 | 2024-11-24 | 01-May-25 A | 31-Jul-25 A | 2170-11-15 02:24 | 2170-11-15 02:10 | 98936.1 | Actual Total Cost | [10 empty] | 50550.16 | 38845.67 | 9540.27
|  |  | JDH3-02-008-L-74-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 2.51 to 3.5 m |  | 2024-11-13 | 2024-12-31 | 07-Jan-25 A | 31-Jul-25 A | 2038-09-23 14:53 | 2038-09-23 14:38 | 50671.62 | Planned Total Cost |  |  |  |  | 10134.32 | 40537.3
|  |  | JDH3-02-008-L-74-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 2.51 to 3.5 m |  | 2024-11-13 | 2024-12-31 | 07-Jan-25 A | 31-Jul-25 A | 2038-09-23 14:53 | 2038-09-23 14:38 | 50671.62 | Remaining Total Cost
|  |  | JDH3-02-008-L-74-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 2.51 to 3.5 m |  | 2024-11-13 | 2024-12-31 | 07-Jan-25 A | 31-Jul-25 A | 2038-09-23 14:53 | 2038-09-23 14:38 | 50671.62 | Actual Total Cost | [6 empty] | 10134.32 |  |  |  | 19054.64 | 16596.46 | 4886.19
|  |  | JDH3-02-008-L-74-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 3.51 to 4.5 m |  | 2024-11-13 | 2024-11-24 | 01-May-25 A | 17-Jul-25 A | 2164-04-28 15:07 | 2164-04-28 14:53 | 96544.63 | Planned Total Cost |  |  |  |  | 96544.63
|  |  | JDH3-02-008-L-74-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 3.51 to 4.5 m |  | 2024-11-13 | 2024-11-24 | 01-May-25 A | 17-Jul-25 A | 2164-04-28 15:07 | 2164-04-28 14:53 | 96544.63 | Remaining Total Cost
|  |  | JDH3-02-008-L-74-(TSE)- Supply and install HDPE Pipes - 630 mm depth from 3.51 to 4.5 m |  | 2024-11-13 | 2024-11-24 | 01-May-25 A | 17-Jul-25 A | 2164-04-28 15:07 | 2164-04-28 14:53 | 96544.63 | Actual Total Cost | [10 empty] | 70899.96 | 16593.61 | 9051.06
|  |  | JDH3-02-008-L-74-(TSE)-Supply and install gate valves-100 mm |  | 2024-12-28 | 2025-01-18 | 15-Jun-25 A | 2025-10-06 | 1905-08-26 04:48 | 1905-08-26 04:48 | 5172.64 | Planned Total Cost | [5 empty] | 2065.2 | [9 empty] | 3107.44
|  |  | JDH3-02-008-L-74-(TSE)-Supply and install gate valves-100 mm |  | 2024-12-28 | 2025-01-18 | 15-Jun-25 A | 2025-10-06 | 1905-08-26 04:48 | 1905-08-26 04:48 | 5172.64 | Remaining Total Cost | [15 empty] | 3107.44
|  |  | JDH3-02-008-L-74-(TSE)-Supply and install gate valves-100 mm |  | 2024-12-28 | 2025-01-18 | 15-Jun-25 A | 2025-10-06 | 1905-08-26 04:48 | 1905-08-26 04:48 | 5172.64 | Actual Total Cost | [11 empty] | 843.81 | 1221.39
|  |  | JDH3-02-008-L-74-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2025-02-05 | 2025-02-09 | 2026-02-07 | 2026-02-10 | 0 | 0 | 70974.45 | Planned Total Cost | [19 empty] | 70974.45
|  |  | JDH3-02-008-L-74-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2025-02-05 | 2025-02-09 | 2026-02-07 | 2026-02-10 | 0 | 0 | 70974.45 | Remaining Total Cost | [19 empty] | 70974.45
|  |  | JDH3-02-008-L-74-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2025-02-05 | 2025-02-09 | 2026-02-07 | 2026-02-10 | 0 | 0 | 70974.45 | Actual Total Cost
|  |  | JDH3-02-008-L-74-(TSE)-Supply and install of butterfly valves-600 mm. |  | 2025-02-05 | 2025-02-09 | 2026-02-07 | 2026-02-10 | 0 | 0 | 46575.2 | Planned Total Cost | [19 empty] | 46575.2
|  |  | JDH3-02-008-L-74-(TSE)-Supply and install of butterfly valves-600 mm. |  | 2025-02-05 | 2025-02-09 | 2026-02-07 | 2026-02-10 | 0 | 0 | 46575.2 | Remaining Total Cost | [19 empty] | 46575.2
|  |  | JDH3-02-008-L-74-(TSE)-Supply and install of butterfly valves-600 mm. |  | 2025-02-05 | 2025-02-09 | 2026-02-07 | 2026-02-10 | 0 | 0 | 46575.2 | Actual Total Cost
|  |  | JDH3-02-008-L-74-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2025-01-09 | 2025-01-18 | 2025-10-12 | 2025-10-20 | 0 | 0 | 27306.9 | Planned Total Cost | [15 empty] | 27306.9
|  |  | JDH3-02-008-L-74-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2025-01-09 | 2025-01-18 | 2025-10-12 | 2025-10-20 | 0 | 0 | 27306.9 | Remaining Total Cost | [15 empty] | 27306.9
|  |  | JDH3-02-008-L-74-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2025-01-09 | 2025-01-18 | 2025-10-12 | 2025-10-20 | 0 | 0 | 27306.9 | Actual Total Cost
|  |  | JDH3-02-008-L-74-(TSE)- Supply and Construct R.C Valves Chamber on 500-630 mm Diameter pipelines |  | 2025-01-12 | 2025-01-20 | 2025-10-14 | 2025-10-22 | 0 | 0 | 12151.39 | Planned Total Cost | [15 empty] | 12151.39
|  |  | JDH3-02-008-L-74-(TSE)- Supply and Construct R.C Valves Chamber on 500-630 mm Diameter pipelines |  | 2025-01-12 | 2025-01-20 | 2025-10-14 | 2025-10-22 | 0 | 0 | 12151.39 | Remaining Total Cost | [15 empty] | 12151.39
|  |  | JDH3-02-008-L-74-(TSE)- Supply and Construct R.C Valves Chamber on 500-630 mm Diameter pipelines |  | 2025-01-12 | 2025-01-20 | 2025-10-14 | 2025-10-22 | 0 | 0 | 12151.39 | Actual Total Cost
|  |  | JDH3-02-008-L-74-Potable Water Network - WT |  | 2024-12-30 | 2025-02-05 | 09-Jan-25 A | 2025-10-22 | 2200-10-12 15:50 | 2200-10-12 15:36 | 205184.43 | Planned Total Cost | [5 empty] | 5472.7 | 96652.27 | 7734.69 | [7 empty] | 95324.77
|  |  | JDH3-02-008-L-74-Potable Water Network - WT |  | 2024-12-30 | 2025-02-05 | 09-Jan-25 A | 2025-10-22 | 2200-10-12 15:50 | 2200-10-12 15:36 | 205184.43 | Remaining Total Cost | [15 empty] | 95324.77
|  |  | JDH3-02-008-L-74-Potable Water Network - WT |  | 2024-12-30 | 2025-02-05 | 09-Jan-25 A | 2025-10-22 | 2200-10-12 15:50 | 2200-10-12 15:36 | 205184.43 | Actual Total Cost | [6 empty] | 9823.91 | 16885.76 | 15791.27 | 8569.19 | 7820.74 | 6128.35 | 3901.54 | 40938.89
|  |  | JDH3-02-008-L-74-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2024-12-30 | 2025-02-05 | 09-Jan-25 A | 31-Aug-25 A | 2200-10-12 15:50 | 2200-10-12 15:36 | 109859.66 | Planned Total Cost | [5 empty] | 5472.7 | 96652.27 | 7734.69
|  |  | JDH3-02-008-L-74-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2024-12-30 | 2025-02-05 | 09-Jan-25 A | 31-Aug-25 A | 2200-10-12 15:50 | 2200-10-12 15:36 | 109859.66 | Remaining Total Cost
|  |  | JDH3-02-008-L-74-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2024-12-30 | 2025-02-05 | 09-Jan-25 A | 31-Aug-25 A | 2200-10-12 15:50 | 2200-10-12 15:36 | 109859.66 | Actual Total Cost | [6 empty] | 9823.91 | 16885.76 | 15791.27 | 8569.19 | 7820.74 | 6128.35 | 3901.54 | 40938.89
|  |  | JDH3-02-008-L-74-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2025-01-28 | 2025-02-03 | 2025-10-02 | 2025-10-08 | 0 | 0 | 13709.14 | Planned Total Cost | [15 empty] | 13709.14
|  |  | JDH3-02-008-L-74-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2025-01-28 | 2025-02-03 | 2025-10-02 | 2025-10-08 | 0 | 0 | 13709.14 | Remaining Total Cost | [15 empty] | 13709.14
|  |  | JDH3-02-008-L-74-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2025-01-28 | 2025-02-03 | 2025-10-02 | 2025-10-08 | 0 | 0 | 13709.14 | Actual Total Cost
|  |  | JDH3-02-008-L-74-(WT)- Supply and install 3-out fire hydrant |  | 2025-01-23 | 2025-01-29 | 2025-10-16 | 2025-10-22 | 0 | 0 | 81615.63 | Planned Total Cost | [15 empty] | 81615.63
|  |  | JDH3-02-008-L-74-(WT)- Supply and install 3-out fire hydrant |  | 2025-01-23 | 2025-01-29 | 2025-10-16 | 2025-10-22 | 0 | 0 | 81615.63 | Remaining Total Cost | [15 empty] | 81615.63
|  |  | JDH3-02-008-L-74-(WT)- Supply and install 3-out fire hydrant |  | 2025-01-23 | 2025-01-29 | 2025-10-16 | 2025-10-22 | 0 | 0 | 81615.63 | Actual Total Cost
|  |  | JDH3-02-008-L-74-Street Lighting Network -SL |  | 2025-04-15 | 2025-05-01 | 06-Aug-25 A | 2025-10-12 | 2038-10-31 17:31 | 2038-10-31 17:17 | 64295.96 | Planned Total Cost | [15 empty] | 64295.96
|  |  | JDH3-02-008-L-74-Street Lighting Network -SL |  | 2025-04-15 | 2025-05-01 | 06-Aug-25 A | 2025-10-12 | 2038-10-31 17:31 | 2038-10-31 17:17 | 64295.96 | Remaining Total Cost | [15 empty] | 13586.24
|  |  | JDH3-02-008-L-74-Street Lighting Network -SL |  | 2025-04-15 | 2025-05-01 | 06-Aug-25 A | 2025-10-12 | 2038-10-31 17:31 | 2038-10-31 17:17 | 64295.96 | Actual Total Cost | [13 empty] | 43948.42 | 6761.3
|  |  | JDH3-02-008-L-74-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx25 mm² |  | 2025-04-15 | 2025-05-01 | 06-Aug-25 A | 2025-10-12 | 2038-10-31 17:31 | 2038-10-31 17:17 | 56344.14 | Planned Total Cost | [15 empty] | 56344.14
|  |  | JDH3-02-008-L-74-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx25 mm² |  | 2025-04-15 | 2025-05-01 | 06-Aug-25 A | 2025-10-12 | 2038-10-31 17:31 | 2038-10-31 17:17 | 56344.14 | Remaining Total Cost | [15 empty] | 5634.41
|  |  | JDH3-02-008-L-74-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx25 mm² |  | 2025-04-15 | 2025-05-01 | 06-Aug-25 A | 2025-10-12 | 2038-10-31 17:31 | 2038-10-31 17:17 | 56344.14 | Actual Total Cost | [13 empty] | 43948.42 | 6761.3
|  |  | JDH3-02-008-L-74-(STL)- Supply,install,connect and test single core PVC insulated copper 16mm2 |  | 2025-04-22 | 2025-04-28 | 2025-10-02 | 2025-10-08 | 0 | 0 | 7951.82 | Planned Total Cost | [15 empty] | 7951.82
|  |  | JDH3-02-008-L-74-(STL)- Supply,install,connect and test single core PVC insulated copper 16mm2 |  | 2025-04-22 | 2025-04-28 | 2025-10-02 | 2025-10-08 | 0 | 0 | 7951.82 | Remaining Total Cost | [15 empty] | 7951.82
|  |  | JDH3-02-008-L-74-(STL)- Supply,install,connect and test single core PVC insulated copper 16mm2 |  | 2025-04-22 | 2025-04-28 | 2025-10-02 | 2025-10-08 | 0 | 0 | 7951.82 | Actual Total Cost
|  |  | JDH3-02-008-L-74-Telecommunications Network - TC |  | 2025-05-03 | 2025-05-18 | 10-Aug-25 A | 2025-10-22 | 1919-07-29 22:19 | 1919-07-29 22:05 | 92279.67 | Planned Total Cost | [15 empty] | 92279.67
|  |  | JDH3-02-008-L-74-Telecommunications Network - TC |  | 2025-05-03 | 2025-05-18 | 10-Aug-25 A | 2025-10-22 | 1919-07-29 22:19 | 1919-07-29 22:05 | 92279.67 | Remaining Total Cost | [15 empty] | 85128.75
|  |  | JDH3-02-008-L-74-Telecommunications Network - TC |  | 2025-05-03 | 2025-05-18 | 10-Aug-25 A | 2025-10-22 | 1919-07-29 22:19 | 1919-07-29 22:05 | 92279.67 | Actual Total Cost | [13 empty] | 2469.16 | 4508.37 | 173.4
|  |  | JDH3-02-008-L-74-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-05-03 | 2025-05-18 | 10-Aug-25 A | 2025-10-14 | 1919-07-29 22:19 | 1919-07-29 22:05 | 62623.06 | Planned Total Cost | [15 empty] | 62623.06
|  |  | JDH3-02-008-L-74-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-05-03 | 2025-05-18 | 10-Aug-25 A | 2025-10-14 | 1919-07-29 22:19 | 1919-07-29 22:05 | 62623.06 | Remaining Total Cost | [15 empty] | 55472.14
|  |  | JDH3-02-008-L-74-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-05-03 | 2025-05-18 | 10-Aug-25 A | 2025-10-14 | 1919-07-29 22:19 | 1919-07-29 22:05 | 62623.06 | Actual Total Cost | [13 empty] | 2469.16 | 4508.37 | 173.4
|  |  | JDH3-02-008-L-74-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-05-05 | 2025-05-14 | 2025-10-13 | 2025-10-22 | 0 | 0 | 29656.61 | Planned Total Cost | [15 empty] | 29656.61
|  |  | JDH3-02-008-L-74-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-05-05 | 2025-05-14 | 2025-10-13 | 2025-10-22 | 0 | 0 | 29656.61 | Remaining Total Cost | [15 empty] | 29656.61
|  |  | JDH3-02-008-L-74-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-05-05 | 2025-05-14 | 2025-10-13 | 2025-10-22 | 0 | 0 | 29656.61 | Actual Total Cost
|  |  | JDH3-02-008-L-74-Road Works - RD |  | 2024-08-17 | 2025-05-26 | 15-Feb-25 A | 2025-10-13 | 986044.49 | 986044.49 | 1028834.91 | Planned Total Cost |  | 258634.52 |  | 108776.32 |  |  | 244549.3 |  |  | 61137.33 |  |  |  |  | 228006.1 | 127731.34
|  |  | JDH3-02-008-L-74-Road Works - RD |  | 2024-08-17 | 2025-05-26 | 15-Feb-25 A | 2025-10-13 | 986044.49 | 986044.49 | 1028834.91 | Remaining Total Cost | [15 empty] | 42790.42
|  |  | JDH3-02-008-L-74-Road Works - RD |  | 2024-08-17 | 2025-05-26 | 15-Feb-25 A | 2025-10-13 | 986044.49 | 986044.49 | 1028834.91 | Actual Total Cost | [7 empty] | 125180 | 235764.98 | 6465.86 |  | 48910.14 | 195639.16 | 99860.54 | 274223.81
|  |  | JDH3-02-008-L-74-(RD)-Subgrade |  | 2024-08-17 | 2024-08-21 | 15-Feb-25 A | 01-Apr-25 A | 258634.52 | 258634.52 | 258634.52 | Planned Total Cost |  | 258634.52
|  |  | JDH3-02-008-L-74-(RD)-Subgrade |  | 2024-08-17 | 2024-08-21 | 15-Feb-25 A | 01-Apr-25 A | 258634.52 | 258634.52 | 258634.52 | Remaining Total Cost
|  |  | JDH3-02-008-L-74-(RD)-Subgrade |  | 2024-08-17 | 2024-08-21 | 15-Feb-25 A | 01-Apr-25 A | 258634.52 | 258634.52 | 258634.52 | Actual Total Cost | [7 empty] | 77590.36 | 174578.3 | 6465.86
|  |  | JDH3-02-008-L-74-(RD)-AGGREGATE BASE COURSE |  | 2024-10-17 | 2024-10-19 | 20-Feb-25 A | 10-Mar-25 A | 2197-10-24 07:41 | 2197-10-24 07:41 | 108776.32 | Planned Total Cost |  |  |  | 108776.32
|  |  | JDH3-02-008-L-74-(RD)-AGGREGATE BASE COURSE |  | 2024-10-17 | 2024-10-19 | 20-Feb-25 A | 10-Mar-25 A | 2197-10-24 07:41 | 2197-10-24 07:41 | 108776.32 | Remaining Total Cost
|  |  | JDH3-02-008-L-74-(RD)-AGGREGATE BASE COURSE |  | 2024-10-17 | 2024-10-19 | 20-Feb-25 A | 10-Mar-25 A | 2197-10-24 07:41 | 2197-10-24 07:41 | 108776.32 | Actual Total Cost | [7 empty] | 47589.64 | 61186.68
|  |  | JDH3-02-008-L-74-(RD)-Bituminous base course (Grading I - Class A), including Prime Coat (MC1) |  | 2025-01-05 | 2025-04-22 | 25-Jun-25 A | 24-Aug-25 A | 305686.63 | 305686.63 | 305686.63 | Planned Total Cost | [6 empty] | 244549.3 |  |  | 61137.33
|  |  | JDH3-02-008-L-74-(RD)-Bituminous base course (Grading I - Class A), including Prime Coat (MC1) |  | 2025-01-05 | 2025-04-22 | 25-Jun-25 A | 24-Aug-25 A | 305686.63 | 305686.63 | 305686.63 | Remaining Total Cost
|  |  | JDH3-02-008-L-74-(RD)-Bituminous base course (Grading I - Class A), including Prime Coat (MC1) |  | 2025-01-05 | 2025-04-22 | 25-Jun-25 A | 24-Aug-25 A | 305686.63 | 305686.63 | 305686.63 | Actual Total Cost | [11 empty] | 48910.14 | 195639.16 | 61137.33
|  |  | JDH3-02-008-L-74-(RD)-Bituminous concrete wearing course, (Grading I - Class A), including tack coat |  | 2025-04-23 | 2025-04-27 | 20-Sep-25 A | 26-Sep-25 A | 227202.76 | 227202.77 | 227202.76 | Planned Total Cost | [14 empty] | 227202.76
|  |  | JDH3-02-008-L-74-(RD)-Bituminous concrete wearing course, (Grading I - Class A), including tack coat |  | 2025-04-23 | 2025-04-27 | 20-Sep-25 A | 26-Sep-25 A | 227202.76 | 227202.77 | 227202.76 | Remaining Total Cost
|  |  | JDH3-02-008-L-74-(RD)-Bituminous concrete wearing course, (Grading I - Class A), including tack coat |  | 2025-04-23 | 2025-04-27 | 20-Sep-25 A | 26-Sep-25 A | 227202.76 | 227202.77 | 227202.76 | Actual Total Cost | [14 empty] | 227202.77
|  |  | JDH3-02-008-L-74-(RD)-Precast Concrete Curb |  | 2025-04-28 | 2025-05-14 | 16-Aug-25 A | 20-Sep-25 A | 2134-10-03 06:14 | 2134-10-03 06:00 | 85744.26 | Planned Total Cost | [14 empty] | 803.33 | 84940.92
|  |  | JDH3-02-008-L-74-(RD)-Precast Concrete Curb |  | 2025-04-28 | 2025-05-14 | 16-Aug-25 A | 20-Sep-25 A | 2134-10-03 06:14 | 2134-10-03 06:00 | 85744.26 | Remaining Total Cost
|  |  | JDH3-02-008-L-74-(RD)-Precast Concrete Curb |  | 2025-04-28 | 2025-05-14 | 16-Aug-25 A | 20-Sep-25 A | 2134-10-03 06:14 | 2134-10-03 06:00 | 85744.26 | Actual Total Cost | [13 empty] | 38723.21 | 47021.04
|  |  | JDH3-02-008-L-74-(RD)-Pavement Marking |  | 2025-05-15 | 2025-05-26 | 2025-10-02 | 2025-10-13 | 0 | 0 | 8388.8 | Planned Total Cost | [15 empty] | 8388.8
|  |  | JDH3-02-008-L-74-(RD)-Pavement Marking |  | 2025-05-15 | 2025-05-26 | 2025-10-02 | 2025-10-13 | 0 | 0 | 8388.8 | Remaining Total Cost | [15 empty] | 8388.8
|  |  | JDH3-02-008-L-74-(RD)-Pavement Marking |  | 2025-05-15 | 2025-05-26 | 2025-10-02 | 2025-10-13 | 0 | 0 | 8388.8 | Actual Total Cost
|  |  | JDH3-02-008-L-74-(RD)-Traffic Signage |  | 2025-05-15 | 2025-05-19 | 2025-10-02 | 2025-10-06 | 0 | 0 | 34401.62 | Planned Total Cost | [15 empty] | 34401.62
|  |  | JDH3-02-008-L-74-(RD)-Traffic Signage |  | 2025-05-15 | 2025-05-19 | 2025-10-02 | 2025-10-06 | 0 | 0 | 34401.62 | Remaining Total Cost | [15 empty] | 34401.62
|  |  | JDH3-02-008-L-74-(RD)-Traffic Signage |  | 2025-05-15 | 2025-05-19 | 2025-10-02 | 2025-10-06 | 0 | 0 | 34401.62 | Actual Total Cost
|  |  | L-75 |  | 2024-12-07 | 2025-06-14 | 07-Jan-25 A | 2025-11-30 | 1994851.18 | 1994851.19 | 2791383.01 | Planned Total Cost | [5 empty] | 493597.76 | 870927.43 | 43667.95 |  | 20100 | 69817.31 |  |  |  |  | 299842.14 | 920718.87 | 72711.55
|  |  | L-75 |  | 2024-12-07 | 2025-06-14 | 07-Jan-25 A | 2025-11-30 | 1994851.18 | 1994851.19 | 2791383.01 | Remaining Total Cost | [15 empty] | 291797.73 | 504734.12
|  |  | L-75 |  | 2024-12-07 | 2025-06-14 | 07-Jan-25 A | 2025-11-30 | 1994851.18 | 1994851.19 | 2791383.01 | Actual Total Cost | [6 empty] | 138894.29 | 297577.51 | 371097.96 | 42744.91 | 24972.4 | 120489.68 | 388636.24 | 256304.42 | 352245.58 | 1888.21
|  |  | JDH3-02-008-L-75-Sewage Network - SS |  | 2024-12-15 | 2024-12-30 | 07-Jan-25 A | 03-Aug-25 A | 288078.55 | 288078.57 | 288078.55 | Planned Total Cost | [5 empty] | 288078.55
|  |  | JDH3-02-008-L-75-Sewage Network - SS |  | 2024-12-15 | 2024-12-30 | 07-Jan-25 A | 03-Aug-25 A | 288078.55 | 288078.57 | 288078.55 | Remaining Total Cost
|  |  | JDH3-02-008-L-75-Sewage Network - SS |  | 2024-12-15 | 2024-12-30 | 07-Jan-25 A | 03-Aug-25 A | 288078.55 | 288078.57 | 288078.55 | Actual Total Cost | [6 empty] | 64779.29 | 133153.53 | 62813.07 | 767.65 | 2640.42 | 21694.02 | 1759.84 | 470.74
|  |  | JDH3-02-008-L-75-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 0 to 1.5 m. |  | 2024-12-15 | 2024-12-25 | 09-Jan-25 A | 08-Mar-25 A | 2004-07-10 19:55 | 2004-07-10 19:41 | 38178.83 | Planned Total Cost | [5 empty] | 38178.83
|  |  | JDH3-02-008-L-75-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 0 to 1.5 m. |  | 2024-12-15 | 2024-12-25 | 09-Jan-25 A | 08-Mar-25 A | 2004-07-10 19:55 | 2004-07-10 19:41 | 38178.83 | Remaining Total Cost
|  |  | JDH3-02-008-L-75-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 0 to 1.5 m. |  | 2024-12-15 | 2024-12-25 | 09-Jan-25 A | 08-Mar-25 A | 2004-07-10 19:55 | 2004-07-10 19:41 | 38178.83 | Actual Total Cost | [6 empty] | 30543.06 | 5965.44 | 1670.32
|  |  | JDH3-02-008-L-75-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2024-12-15 | 2024-12-26 | 14-Jan-25 A | 26-Jun-25 A | 2055-09-13 13:41 | 2055-09-13 13:41 | 56870.57 | Planned Total Cost | [5 empty] | 56870.57
|  |  | JDH3-02-008-L-75-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2024-12-15 | 2024-12-26 | 14-Jan-25 A | 26-Jun-25 A | 2055-09-13 13:41 | 2055-09-13 13:41 | 56870.57 | Remaining Total Cost
|  |  | JDH3-02-008-L-75-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2024-12-15 | 2024-12-26 | 14-Jan-25 A | 26-Jun-25 A | 2055-09-13 13:41 | 2055-09-13 13:41 | 56870.57 | Actual Total Cost | [6 empty] | 20260.14 | 27724.4 | 3198.97 | 710.88 | 2640.42 | 2335.76
|  |  | JDH3-02-008-L-75-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2024-12-15 | 2024-12-25 | 07-Jan-25 A | 06-Apr-25 A | 1919-11-22 13:41 | 1919-11-22 13:41 | 7266.57 | Planned Total Cost | [5 empty] | 7266.57
|  |  | JDH3-02-008-L-75-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2024-12-15 | 2024-12-25 | 07-Jan-25 A | 06-Apr-25 A | 1919-11-22 13:41 | 1919-11-22 13:41 | 7266.57 | Remaining Total Cost
|  |  | JDH3-02-008-L-75-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2024-12-15 | 2024-12-25 | 07-Jan-25 A | 06-Apr-25 A | 1919-11-22 13:41 | 1919-11-22 13:41 | 7266.57 | Actual Total Cost | [6 empty] | 3213.18 | 3690.06 | 306.56 | 56.77
|  |  | JDH3-02-008-L-75-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 2.51 to 3.5 m. |  | 2024-12-15 | 2024-12-28 | 07-Jan-25 A | 03-Aug-25 A | 1937-09-18 12:29 | 1937-09-18 12:29 | 13776.52 | Planned Total Cost | [5 empty] | 13776.52
|  |  | JDH3-02-008-L-75-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 2.51 to 3.5 m. |  | 2024-12-15 | 2024-12-28 | 07-Jan-25 A | 03-Aug-25 A | 1937-09-18 12:29 | 1937-09-18 12:29 | 13776.52 | Remaining Total Cost
|  |  | JDH3-02-008-L-75-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 2.51 to 3.5 m. |  | 2024-12-15 | 2024-12-28 | 07-Jan-25 A | 03-Aug-25 A | 1937-09-18 12:29 | 1937-09-18 12:29 | 13776.52 | Actual Total Cost | [6 empty] | 10762.91 | 2542.87 | [5 empty] | 470.74
|  |  | JDH3-02-008-L-75-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 3.51 to 4.5 m. |  | 2024-12-15 | 2024-12-25 | 05-Feb-25 A | 15-Mar-25 A | 1985-05-31 15:36 | 1985-05-31 15:50 | 31198.65 | Planned Total Cost | [5 empty] | 31198.65
|  |  | JDH3-02-008-L-75-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 3.51 to 4.5 m. |  | 2024-12-15 | 2024-12-25 | 05-Feb-25 A | 15-Mar-25 A | 1985-05-31 15:36 | 1985-05-31 15:50 | 31198.65 | Remaining Total Cost
|  |  | JDH3-02-008-L-75-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 3.51 to 4.5 m. |  | 2024-12-15 | 2024-12-25 | 05-Feb-25 A | 15-Mar-25 A | 1985-05-31 15:36 | 1985-05-31 15:50 | 31198.65 | Actual Total Cost | [7 empty] | 26226.37 | 4972.29
|  |  | JDH3-02-008-L-75-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2024-12-15 | 2024-12-25 | 11-Feb-25 A | 02-Jul-25 A | 2014-03-16 18:58 | 2014-03-16 19:12 | 41714.79 | Planned Total Cost | [5 empty] | 41714.79
|  |  | JDH3-02-008-L-75-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2024-12-15 | 2024-12-25 | 11-Feb-25 A | 02-Jul-25 A | 2014-03-16 18:58 | 2014-03-16 19:12 | 41714.79 | Remaining Total Cost
|  |  | JDH3-02-008-L-75-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2024-12-15 | 2024-12-25 | 11-Feb-25 A | 02-Jul-25 A | 2014-03-16 18:58 | 2014-03-16 19:12 | 41714.79 | Actual Total Cost | [7 empty] | 27375.34 | 8082.24 |  |  | 5735.79 | 521.44
|  |  | JDH3-02-008-L-75-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2024-12-15 | 2024-12-30 | 11-Feb-25 A | 02-Jul-25 A | 99072.63 | 2171-03-31 15:07 | 99072.63 | Planned Total Cost | [5 empty] | 99072.63
|  |  | JDH3-02-008-L-75-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2024-12-15 | 2024-12-30 | 11-Feb-25 A | 02-Jul-25 A | 99072.63 | 2171-03-31 15:07 | 99072.63 | Remaining Total Cost
|  |  | JDH3-02-008-L-75-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2024-12-15 | 2024-12-30 | 11-Feb-25 A | 02-Jul-25 A | 99072.63 | 2171-03-31 15:07 | 99072.63 | Actual Total Cost | [7 empty] | 39629.06 | 44582.69 |  |  | 13622.48 | 1238.41
|  |  | JDH3-02-008-L-75-Storm Network - ST |  | 2024-12-15 | 2025-02-25 | 25-Jun-25 A | 2025-11-25 | 2358-11-08 02:53 | 2358-11-08 03:22 | 659291.8 | Planned Total Cost | [5 empty] | 137057.59 | 30536.53 | [8 empty] | 171849.67 | 319848.01
|  |  | JDH3-02-008-L-75-Storm Network - ST |  | 2024-12-15 | 2025-02-25 | 25-Jun-25 A | 2025-11-25 | 2358-11-08 02:53 | 2358-11-08 03:22 | 659291.8 | Remaining Total Cost | [15 empty] | 171849.67 | 319848.01
|  |  | JDH3-02-008-L-75-Storm Network - ST |  | 2024-12-15 | 2025-02-25 | 25-Jun-25 A | 2025-11-25 | 2358-11-08 02:53 | 2358-11-08 03:22 | 659291.8 | Actual Total Cost | [11 empty] | 13194.62 | 110990.06 | 43409.46
|  |  | JDH3-02-008-L-75-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-12-15 | 2024-12-25 | 2025-10-02 | 2025-10-13 | 0 | 0 | 18491.24 | Planned Total Cost | [15 empty] | 18491.24
|  |  | JDH3-02-008-L-75-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-12-15 | 2024-12-25 | 2025-10-02 | 2025-10-13 | 0 | 0 | 18491.24 | Remaining Total Cost | [15 empty] | 18491.24
|  |  | JDH3-02-008-L-75-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-12-15 | 2024-12-25 | 2025-10-02 | 2025-10-13 | 0 | 0 | 18491.24 | Actual Total Cost
|  |  | JDH3-02-008-L-75-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2024-12-15 | 2024-12-25 | 25-Jun-25 A | 23-Jul-25 A | 2185-12-10 13:41 | 2185-12-10 13:41 | 104440.57 | Planned Total Cost | [5 empty] | 104440.57
|  |  | JDH3-02-008-L-75-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2024-12-15 | 2024-12-25 | 25-Jun-25 A | 23-Jul-25 A | 2185-12-10 13:41 | 2185-12-10 13:41 | 104440.57 | Remaining Total Cost
|  |  | JDH3-02-008-L-75-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2024-12-15 | 2024-12-25 | 25-Jun-25 A | 23-Jul-25 A | 2185-12-10 13:41 | 2185-12-10 13:41 | 104440.57 | Actual Total Cost | [11 empty] | 11096.81 | 93343.76
|  |  | JDH3-02-008-L-75-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-12-15 | 2024-12-25 | 25-Jun-25 A | 23-Jul-25 A | 1954-01-20 02:24 | 1954-01-20 02:38 | 19744.1 | Planned Total Cost | [5 empty] | 19744.1
|  |  | JDH3-02-008-L-75-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-12-15 | 2024-12-25 | 25-Jun-25 A | 23-Jul-25 A | 1954-01-20 02:24 | 1954-01-20 02:38 | 19744.1 | Remaining Total Cost
|  |  | JDH3-02-008-L-75-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-12-15 | 2024-12-25 | 25-Jun-25 A | 23-Jul-25 A | 1954-01-20 02:24 | 1954-01-20 02:38 | 19744.1 | Actual Total Cost | [11 empty] | 2097.81 | 17646.3
|  |  | JDH3-02-008-L-75-(ST)- MH WORKS With (1200) diameter depth from 0.00 to 1.50 |  | 2024-12-29 | 2025-01-08 | 04-Aug-25 A | 2025-10-04 | 1967-06-14 19:12 | 1967-06-14 19:12 | 27375.34 | Planned Total Cost | [5 empty] | 10265.75 | 14372.05 | [8 empty] | 2737.53
|  |  | JDH3-02-008-L-75-(ST)- MH WORKS With (1200) diameter depth from 0.00 to 1.50 |  | 2024-12-29 | 2025-01-08 | 04-Aug-25 A | 2025-10-04 | 1967-06-14 19:12 | 1967-06-14 19:12 | 27375.34 | Remaining Total Cost | [15 empty] | 2737.53
|  |  | JDH3-02-008-L-75-(ST)- MH WORKS With (1200) diameter depth from 0.00 to 1.50 |  | 2024-12-29 | 2025-01-08 | 04-Aug-25 A | 2025-10-04 | 1967-06-14 19:12 | 1967-06-14 19:12 | 27375.34 | Actual Total Cost | [13 empty] | 24637.8
|  |  | JDH3-02-008-L-75-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-12-31 | 2025-01-11 | 06-Aug-25 A | 2025-10-04 | 1951-05-23 15:50 | 1951-05-23 15:50 | 20857.39 | Planned Total Cost | [5 empty] | 2607.17 | 16164.48 | [8 empty] | 2085.74
|  |  | JDH3-02-008-L-75-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-12-31 | 2025-01-11 | 06-Aug-25 A | 2025-10-04 | 1951-05-23 15:50 | 1951-05-23 15:50 | 20857.39 | Remaining Total Cost | [15 empty] | 2085.74
|  |  | JDH3-02-008-L-75-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-12-31 | 2025-01-11 | 06-Aug-25 A | 2025-10-04 | 1951-05-23 15:50 | 1951-05-23 15:50 | 20857.39 | Actual Total Cost | [13 empty] | 18771.66
|  |  | JDH3-02-008-L-75-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-01-02 | 2025-01-13 | 2025-10-02 | 2025-10-13 | 0 | 0 | 16946.63 | Planned Total Cost | [15 empty] | 16946.63
|  |  | JDH3-02-008-L-75-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-01-02 | 2025-01-13 | 2025-10-02 | 2025-10-13 | 0 | 0 | 16946.63 | Remaining Total Cost | [15 empty] | 16946.63
|  |  | JDH3-02-008-L-75-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-01-02 | 2025-01-13 | 2025-10-02 | 2025-10-13 | 0 | 0 | 16946.63 | Actual Total Cost
|  |  | JDH3-02-008-L-75-(ST)- Double Catchbasine Works |  | 2025-01-05 | 2025-01-13 | 2025-10-05 | 2025-10-13 | 0 | 0 | 45456.07 | Planned Total Cost | [15 empty] | 45456.07
|  |  | JDH3-02-008-L-75-(ST)- Double Catchbasine Works |  | 2025-01-05 | 2025-01-13 | 2025-10-05 | 2025-10-13 | 0 | 0 | 45456.07 | Remaining Total Cost | [15 empty] | 45456.07
|  |  | JDH3-02-008-L-75-(ST)- Double Catchbasine Works |  | 2025-01-05 | 2025-01-13 | 2025-10-05 | 2025-10-13 | 0 | 0 | 45456.07 | Actual Total Cost
|  |  | JDH3-02-008-L-75-(ST)-Excavation for cutting material |  | 2025-01-26 | 2025-02-02 | 2025-10-26 | 2025-11-02 | 0 | 0 | 120585.45 | Planned Total Cost | [15 empty] | 86132.46 | 34452.99
|  |  | JDH3-02-008-L-75-(ST)-Excavation for cutting material |  | 2025-01-26 | 2025-02-02 | 2025-10-26 | 2025-11-02 | 0 | 0 | 120585.45 | Remaining Total Cost | [15 empty] | 86132.46 | 34452.99
|  |  | JDH3-02-008-L-75-(ST)-Excavation for cutting material |  | 2025-01-26 | 2025-02-02 | 2025-10-26 | 2025-11-02 | 0 | 0 | 120585.45 | Actual Total Cost
|  |  | JDH3-02-008-L-75-(ST)-Filling with imported material |  | 2025-02-03 | 2025-02-25 | 2025-11-03 | 2025-11-25 | 0 | 0 | 285395.02 | Planned Total Cost | [16 empty] | 285395.02
|  |  | JDH3-02-008-L-75-(ST)-Filling with imported material |  | 2025-02-03 | 2025-02-25 | 2025-11-03 | 2025-11-25 | 0 | 0 | 285395.02 | Remaining Total Cost | [16 empty] | 285395.02
|  |  | JDH3-02-008-L-75-(ST)-Filling with imported material |  | 2025-02-03 | 2025-02-25 | 2025-11-03 | 2025-11-25 | 0 | 0 | 285395.02 | Actual Total Cost
|  |  | JDH3-02-008-L-75-TSE Network - TSE |  | 2024-12-26 | 2025-02-01 | 07-Jan-25 A | 2025-11-01 | 241450.74 | 241450.75 | 337863.15 | Planned Total Cost | [5 empty] | 68461.61 | 172989.13 | [8 empty] | 95502.18 | 910.23
|  |  | JDH3-02-008-L-75-TSE Network - TSE |  | 2024-12-26 | 2025-02-01 | 07-Jan-25 A | 2025-11-01 | 241450.74 | 241450.75 | 337863.15 | Remaining Total Cost | [15 empty] | 95502.18 | 910.23
|  |  | JDH3-02-008-L-75-TSE Network - TSE |  | 2024-12-26 | 2025-02-01 | 07-Jan-25 A | 2025-11-01 | 241450.74 | 241450.75 | 337863.15 | Actual Total Cost | [6 empty] | 64796.55 | 41105.77 | 36065.53 | 30722.49 | 13858.77 | 26860.6 | 28041.05
|  |  | JDH3-02-008-L-75-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-12-26 | 2025-01-06 | 15-Jan-25 A | 27-Jul-25 A | 1938-04-07 12:29 | 1938-04-07 12:29 | 13977.52 | Planned Total Cost | [5 empty] | 7338.2 | 6639.32
|  |  | JDH3-02-008-L-75-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-12-26 | 2025-01-06 | 15-Jan-25 A | 27-Jul-25 A | 1938-04-07 12:29 | 1938-04-07 12:29 | 13977.52 | Remaining Total Cost
|  |  | JDH3-02-008-L-75-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-12-26 | 2025-01-06 | 15-Jan-25 A | 27-Jul-25 A | 1938-04-07 12:29 | 1938-04-07 12:29 | 13977.52 | Actual Total Cost | [6 empty] | 3013.9 | 480.48 |  |  | 4688.29 | 4455.34 | 1339.51
|  |  | JDH3-02-008-L-75-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-01-14 | 2025-01-25 | 2025-10-14 | 2025-10-25 | 0 | 0 | 35990.94 | Planned Total Cost | [15 empty] | 35990.94
|  |  | JDH3-02-008-L-75-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-01-14 | 2025-01-25 | 2025-10-14 | 2025-10-25 | 0 | 0 | 35990.94 | Remaining Total Cost | [15 empty] | 35990.94
|  |  | JDH3-02-008-L-75-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-01-14 | 2025-01-25 | 2025-10-14 | 2025-10-25 | 0 | 0 | 35990.94 | Actual Total Cost
|  |  | JDH3-02-008-L-75-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2024-12-26 | 2025-01-14 | 11-Jan-25 A | 31-Jul-25 A | 2431-12-13 09:50 | 2431-12-13 09:36 | 194292.41 | Planned Total Cost | [5 empty] | 45334.9 | 148957.51
|  |  | JDH3-02-008-L-75-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2024-12-26 | 2025-01-14 | 11-Jan-25 A | 31-Jul-25 A | 2431-12-13 09:50 | 2431-12-13 09:36 | 194292.41 | Remaining Total Cost
|  |  | JDH3-02-008-L-75-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2024-12-26 | 2025-01-14 | 11-Jan-25 A | 31-Jul-25 A | 2431-12-13 09:50 | 2431-12-13 09:36 | 194292.41 | Actual Total Cost | [6 empty] | 52539.9 | 36106 | 36065.53 | 30722.49 |  | 15265.83 | 23592.65
|  |  | JDH3-02-008-L-75-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2024-12-26 | 2025-01-06 | 07-Jan-25 A | 17-Jul-25 A | 1941-05-17 12:43 | 1941-05-17 12:43 | 15113.53 | Planned Total Cost | [5 empty] | 7934.6 | 7178.92
|  |  | JDH3-02-008-L-75-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2024-12-26 | 2025-01-06 | 07-Jan-25 A | 17-Jul-25 A | 1941-05-17 12:43 | 1941-05-17 12:43 | 15113.53 | Remaining Total Cost
|  |  | JDH3-02-008-L-75-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2024-12-26 | 2025-01-06 | 07-Jan-25 A | 17-Jul-25 A | 1941-05-17 12:43 | 1941-05-17 12:43 | 15113.53 | Actual Total Cost | [6 empty] | 3022.71 |  |  |  | 8076.29 | 2597.64 | 1416.89
|  |  | JDH3-02-008-L-75-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 2.51 to 3.5 m |  | 2024-12-26 | 2025-01-06 | 07-Jan-25 A | 17-Jul-25 A | 1905-08-08 14:24 | 1905-08-08 14:24 | 2047.6 | Planned Total Cost | [5 empty] | 1074.99 | 972.61
|  |  | JDH3-02-008-L-75-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 2.51 to 3.5 m |  | 2024-12-26 | 2025-01-06 | 07-Jan-25 A | 17-Jul-25 A | 1905-08-08 14:24 | 1905-08-08 14:24 | 2047.6 | Remaining Total Cost
|  |  | JDH3-02-008-L-75-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 2.51 to 3.5 m |  | 2024-12-26 | 2025-01-06 | 07-Jan-25 A | 17-Jul-25 A | 1905-08-08 14:24 | 1905-08-08 14:24 | 2047.6 | Actual Total Cost | [6 empty] | 409.52 |  |  |  | 1094.19 | 351.93 | 191.96
|  |  | JDH3-02-008-L-75-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2024-12-26 | 2025-01-16 | 11-Jan-25 A | 17-Jul-25 A | 1935-05-08 06:00 | 1935-05-08 06:14 | 12912.25 | Planned Total Cost | [5 empty] | 6778.93 | 6133.32
|  |  | JDH3-02-008-L-75-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2024-12-26 | 2025-01-16 | 11-Jan-25 A | 17-Jul-25 A | 1935-05-08 06:00 | 1935-05-08 06:14 | 12912.25 | Remaining Total Cost
|  |  | JDH3-02-008-L-75-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2024-12-26 | 2025-01-16 | 11-Jan-25 A | 17-Jul-25 A | 1935-05-08 06:00 | 1935-05-08 06:14 | 12912.25 | Actual Total Cost | [6 empty] | 5810.51 | 4519.29 |  |  |  | 1371.93 | 1210.53
|  |  | JDH3-02-008-L-75-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 2.51 to 3.5 m |  | 2025-01-16 | 2025-01-29 | 2025-10-16 | 2025-10-29 | 0 | 0 | 10764.92 | Planned Total Cost | [15 empty] | 10764.92
|  |  | JDH3-02-008-L-75-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 2.51 to 3.5 m |  | 2025-01-16 | 2025-01-29 | 2025-10-16 | 2025-10-29 | 0 | 0 | 10764.92 | Remaining Total Cost | [15 empty] | 10764.92
|  |  | JDH3-02-008-L-75-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 2.51 to 3.5 m |  | 2025-01-16 | 2025-01-29 | 2025-10-16 | 2025-10-29 | 0 | 0 | 10764.92 | Actual Total Cost
|  |  | JDH3-02-008-L-75-(TSE)-Supply and install gate valves-100 mm |  | 2025-01-18 | 2025-01-27 | 10-Jun-25 A | 2025-10-27 | 1908-07-03 10:34 | 1908-07-03 10:34 | 3879.48 | Planned Total Cost | [6 empty] | 3107.44 | [8 empty] | 772.04
|  |  | JDH3-02-008-L-75-(TSE)-Supply and install gate valves-100 mm |  | 2025-01-18 | 2025-01-27 | 10-Jun-25 A | 2025-10-27 | 1908-07-03 10:34 | 1908-07-03 10:34 | 3879.48 | Remaining Total Cost | [15 empty] | 772.04
|  |  | JDH3-02-008-L-75-(TSE)-Supply and install gate valves-100 mm |  | 2025-01-18 | 2025-01-27 | 10-Jun-25 A | 2025-10-27 | 1908-07-03 10:34 | 1908-07-03 10:34 | 3879.48 | Actual Total Cost | [11 empty] | 2817.93 | 289.51
|  |  | JDH3-02-008-L-75-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2025-01-26 | 2025-01-29 | 2025-10-26 | 2025-10-29 | 0 | 0 | 30679.92 | Planned Total Cost | [15 empty] | 30679.92
|  |  | JDH3-02-008-L-75-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2025-01-26 | 2025-01-29 | 2025-10-26 | 2025-10-29 | 0 | 0 | 30679.92 | Remaining Total Cost | [15 empty] | 30679.92
|  |  | JDH3-02-008-L-75-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2025-01-26 | 2025-01-29 | 2025-10-26 | 2025-10-29 | 0 | 0 | 30679.92 | Actual Total Cost
|  |  | JDH3-02-008-L-75-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2025-01-19 | 2025-02-01 | 2025-10-19 | 2025-11-01 | 0 | 0 | 18204.6 | Planned Total Cost | [15 empty] | 17294.37 | 910.23
|  |  | JDH3-02-008-L-75-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2025-01-19 | 2025-02-01 | 2025-10-19 | 2025-11-01 | 0 | 0 | 18204.6 | Remaining Total Cost | [15 empty] | 17294.37 | 910.23
|  |  | JDH3-02-008-L-75-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2025-01-19 | 2025-02-01 | 2025-10-19 | 2025-11-01 | 0 | 0 | 18204.6 | Actual Total Cost
|  |  | JDH3-02-008-L-75-Potable Water Network - WT |  | 2025-01-20 | 2025-02-20 | 14-Jan-25 A | 2025-11-15 | 2096-02-14 12:00 | 2096-02-14 12:00 | 152052.98 | Planned Total Cost | [6 empty] | 27966.55 | 43667.95 | [7 empty] | 12231.57 | 68186.92
|  |  | JDH3-02-008-L-75-Potable Water Network - WT |  | 2025-01-20 | 2025-02-20 | 14-Jan-25 A | 2025-11-15 | 2096-02-14 12:00 | 2096-02-14 12:00 | 152052.98 | Remaining Total Cost | [15 empty] | 12231.57 | 68186.92
|  |  | JDH3-02-008-L-75-Potable Water Network - WT |  | 2025-01-20 | 2025-02-20 | 14-Jan-25 A | 2025-11-15 | 2096-02-14 12:00 | 2096-02-14 12:00 | 152052.98 | Actual Total Cost | [6 empty] | 9318.45 | 17431.68 | 17939.94 | 11254.77 | 8473.2 | 2886.58 | 4329.87
|  |  | JDH3-02-008-L-75-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-01-20 | 2025-02-20 | 14-Jan-25 A | 2025-11-05 | 2096-02-14 12:00 | 2096-02-14 12:00 | 95468.6 | Planned Total Cost | [6 empty] | 27966.55 | 43667.95 | [7 empty] | 12231.57 | 11602.54
|  |  | JDH3-02-008-L-75-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-01-20 | 2025-02-20 | 14-Jan-25 A | 2025-11-05 | 2096-02-14 12:00 | 2096-02-14 12:00 | 95468.6 | Remaining Total Cost | [15 empty] | 12231.57 | 11602.54
|  |  | JDH3-02-008-L-75-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-01-20 | 2025-02-20 | 14-Jan-25 A | 2025-11-05 | 2096-02-14 12:00 | 2096-02-14 12:00 | 95468.6 | Actual Total Cost | [6 empty] | 9318.45 | 17431.68 | 17939.94 | 11254.77 | 8473.2 | 2886.58 | 4329.87
|  |  | JDH3-02-008-L-75-(WT)- Supply and install HDPE Pipes -225 mm depth from 0 to 1.5 m |  | 2025-02-02 | 2025-02-15 | 2025-11-02 | 2025-11-15 | 0 | 0 | 4522.39 | Planned Total Cost | [16 empty] | 4522.39
|  |  | JDH3-02-008-L-75-(WT)- Supply and install HDPE Pipes -225 mm depth from 0 to 1.5 m |  | 2025-02-02 | 2025-02-15 | 2025-11-02 | 2025-11-15 | 0 | 0 | 4522.39 | Remaining Total Cost | [16 empty] | 4522.39
|  |  | JDH3-02-008-L-75-(WT)- Supply and install HDPE Pipes -225 mm depth from 0 to 1.5 m |  | 2025-02-02 | 2025-02-15 | 2025-11-02 | 2025-11-15 | 0 | 0 | 4522.39 | Actual Total Cost
|  |  | JDH3-02-008-L-75-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2025-02-09 | 2025-02-12 | 2025-11-09 | 2025-11-12 | 0 | 0 | 4569.71 | Planned Total Cost | [16 empty] | 4569.71
|  |  | JDH3-02-008-L-75-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2025-02-09 | 2025-02-12 | 2025-11-09 | 2025-11-12 | 0 | 0 | 4569.71 | Remaining Total Cost | [16 empty] | 4569.71
|  |  | JDH3-02-008-L-75-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2025-02-09 | 2025-02-12 | 2025-11-09 | 2025-11-12 | 0 | 0 | 4569.71 | Actual Total Cost
|  |  | JDH3-02-008-L-75-(WT)- Supply and install gate valves -Diameter 200 mm |  | 2025-02-09 | 2025-02-12 | 2025-11-09 | 2025-11-12 | 0 | 0 | 2150.26 | Planned Total Cost | [16 empty] | 2150.26
|  |  | JDH3-02-008-L-75-(WT)- Supply and install gate valves -Diameter 200 mm |  | 2025-02-09 | 2025-02-12 | 2025-11-09 | 2025-11-12 | 0 | 0 | 2150.26 | Remaining Total Cost | [16 empty] | 2150.26
|  |  | JDH3-02-008-L-75-(WT)- Supply and install gate valves -Diameter 200 mm |  | 2025-02-09 | 2025-02-12 | 2025-11-09 | 2025-11-12 | 0 | 0 | 2150.26 | Actual Total Cost
|  |  | JDH3-02-008-L-75-(WT)- Supply and install 3-out fire hydrant |  | 2025-02-04 | 2025-02-10 | 2025-11-04 | 2025-11-10 | 0 | 0 | 45342.02 | Planned Total Cost | [16 empty] | 45342.02
|  |  | JDH3-02-008-L-75-(WT)- Supply and install 3-out fire hydrant |  | 2025-02-04 | 2025-02-10 | 2025-11-04 | 2025-11-10 | 0 | 0 | 45342.02 | Remaining Total Cost | [16 empty] | 45342.02
|  |  | JDH3-02-008-L-75-(WT)- Supply and install 3-out fire hydrant |  | 2025-02-04 | 2025-02-10 | 2025-11-04 | 2025-11-10 | 0 | 0 | 45342.02 | Actual Total Cost
|  |  | JDH3-02-008-L-75-Street Lighting Network -SL |  | 2025-02-22 | 2025-04-19 | 15-Jul-25 A | 2025-11-15 | 2276-01-09 23:46 | 2276-01-09 23:17 | 178245.24 | Planned Total Cost | [9 empty] | 20100 | [5 empty] | 20258.72 | 137886.52
|  |  | JDH3-02-008-L-75-Street Lighting Network -SL |  | 2025-02-22 | 2025-04-19 | 15-Jul-25 A | 2025-11-15 | 2276-01-09 23:46 | 2276-01-09 23:17 | 178245.24 | Remaining Total Cost | [15 empty] | 12214.31 | 28688.95
|  |  | JDH3-02-008-L-75-Street Lighting Network -SL |  | 2025-02-22 | 2025-04-19 | 15-Jul-25 A | 2025-11-15 | 2276-01-09 23:46 | 2276-01-09 23:17 | 178245.24 | Actual Total Cost | [12 empty] | 20100 | 92691.3 | 23760.56 | 790.11
|  |  | JDH3-02-008-L-75-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx25 mm² |  | 2025-02-22 | 2025-03-02 | 06-Aug-25 A | 2025-10-04 | 1966-01-26 05:46 | 1966-01-26 05:31 | 26814.71 | Planned Total Cost | [15 empty] | 10725.89 | 16088.83
|  |  | JDH3-02-008-L-75-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx25 mm² |  | 2025-02-22 | 2025-03-02 | 06-Aug-25 A | 2025-10-04 | 1966-01-26 05:46 | 1966-01-26 05:31 | 26814.71 | Remaining Total Cost | [15 empty] | 2681.47
|  |  | JDH3-02-008-L-75-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx25 mm² |  | 2025-02-22 | 2025-03-02 | 06-Aug-25 A | 2025-10-04 | 1966-01-26 05:46 | 1966-01-26 05:31 | 26814.71 | Actual Total Cost | [13 empty] | 20915.47 | 3217.76
|  |  | JDH3-02-008-L-75-(STL)- Supply,install,connect and test single core PVC insulated copper 16mm2 |  | 2025-02-26 | 2025-03-02 | 2025-10-02 | 2025-10-06 | 0 | 0 | 3784.35 | Planned Total Cost | [15 empty] | 3784.35
|  |  | JDH3-02-008-L-75-(STL)- Supply,install,connect and test single core PVC insulated copper 16mm2 |  | 2025-02-26 | 2025-03-02 | 2025-10-02 | 2025-10-06 | 0 | 0 | 3784.35 | Remaining Total Cost | [15 empty] | 3784.35
|  |  | JDH3-02-008-L-75-(STL)- Supply,install,connect and test single core PVC insulated copper 16mm2 |  | 2025-02-26 | 2025-03-02 | 2025-10-02 | 2025-10-06 | 0 | 0 | 3784.35 | Actual Total Cost
|  |  | JDH3-02-008-L-75-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2025-02-24 | 2025-03-09 | 04-Aug-25 A | 2025-10-05 | 2032-04-30 00:58 | 2032-04-30 00:58 | 53704.49 | Planned Total Cost | [15 empty] | 5370.45 | 48334.04
|  |  | JDH3-02-008-L-75-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2025-02-24 | 2025-03-09 | 04-Aug-25 A | 2025-10-05 | 2032-04-30 00:58 | 2032-04-30 00:58 | 53704.49 | Remaining Total Cost | [15 empty] | 5370.45
|  |  | JDH3-02-008-L-75-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2025-02-24 | 2025-03-09 | 04-Aug-25 A | 2025-10-05 | 2032-04-30 00:58 | 2032-04-30 00:58 | 53704.49 | Actual Total Cost | [13 empty] | 48334.04
|  |  | JDH3-02-008-L-75-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-03-01 | 2025-03-02 | 21-Aug-25 A | 24-Aug-25 A | 1922-08-13 12:00 | 1922-08-13 12:00 | 8261.5 | Planned Total Cost | [16 empty] | 8261.5
|  |  | JDH3-02-008-L-75-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-03-01 | 2025-03-02 | 21-Aug-25 A | 24-Aug-25 A | 1922-08-13 12:00 | 1922-08-13 12:00 | 8261.5 | Remaining Total Cost
|  |  | JDH3-02-008-L-75-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-03-01 | 2025-03-02 | 21-Aug-25 A | 24-Aug-25 A | 1922-08-13 12:00 | 1922-08-13 12:00 | 8261.5 | Actual Total Cost | [13 empty] | 8261.5
|  |  | JDH3-02-008-L-75-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2025-03-01 | 2025-03-02 | 2025-10-02 | 2025-10-04 | 0 | 0 | 378.04 | Planned Total Cost | [15 empty] | 378.04
|  |  | JDH3-02-008-L-75-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2025-03-01 | 2025-03-02 | 2025-10-02 | 2025-10-04 | 0 | 0 | 378.04 | Remaining Total Cost | [15 empty] | 378.04
|  |  | JDH3-02-008-L-75-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2025-03-01 | 2025-03-02 | 2025-10-02 | 2025-10-04 | 0 | 0 | 378.04 | Actual Total Cost
|  |  | JDH3-02-008-L-75-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-02-26 | 2025-03-08 | 04-Aug-25 A | 2025-11-15 | 1999-12-19 04:48 | 1999-12-19 04:48 | 65202.15 | Planned Total Cost | [16 empty] | 65202.15
|  |  | JDH3-02-008-L-75-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-02-26 | 2025-03-08 | 04-Aug-25 A | 2025-11-15 | 1999-12-19 04:48 | 1999-12-19 04:48 | 65202.15 | Remaining Total Cost | [16 empty] | 28688.95
|  |  | JDH3-02-008-L-75-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-02-26 | 2025-03-08 | 04-Aug-25 A | 2025-11-15 | 1999-12-19 04:48 | 1999-12-19 04:48 | 65202.15 | Actual Total Cost | [13 empty] | 15180.29 | 20542.8 | 790.11
|  |  | JDH3-02-008-L-75-(STL)-Transfer existing lighting poles |  | 2025-04-15 | 2025-04-19 | 15-Jul-25 A | 20-Jul-25 A | 1955-01-11 | 1955-01-11 | 20100 | Planned Total Cost | [9 empty] | 20100
|  |  | JDH3-02-008-L-75-(STL)-Transfer existing lighting poles |  | 2025-04-15 | 2025-04-19 | 15-Jul-25 A | 20-Jul-25 A | 1955-01-11 | 1955-01-11 | 20100 | Remaining Total Cost
|  |  | JDH3-02-008-L-75-(STL)-Transfer existing lighting poles |  | 2025-04-15 | 2025-04-19 | 15-Jul-25 A | 20-Jul-25 A | 1955-01-11 | 1955-01-11 | 20100 | Actual Total Cost | [12 empty] | 20100
|  |  | JDH3-02-008-L-75-Telecommunications Network - TC |  | 2025-04-20 | 2025-05-10 | 10-Aug-25 A | 2025-11-18 | 2024-07-03 00:14 | 2024-07-03 | 110872.48 | Planned Total Cost | [16 empty] | 110872.48
|  |  | JDH3-02-008-L-75-Telecommunications Network - TC |  | 2025-04-20 | 2025-05-10 | 10-Aug-25 A | 2025-11-18 | 2024-07-03 00:14 | 2024-07-03 | 110872.48 | Remaining Total Cost | [16 empty] | 65396.48
|  |  | JDH3-02-008-L-75-Telecommunications Network - TC |  | 2025-04-20 | 2025-05-10 | 10-Aug-25 A | 2025-11-18 | 2024-07-03 00:14 | 2024-07-03 | 110872.48 | Actual Total Cost | [13 empty] | 15827.12 | 28550.77 | 1098.11
|  |  | JDH3-02-008-L-75-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-04-20 | 2025-05-10 | 10-Aug-25 A | 2025-11-18 | 1992-01-11 13:12 | 1992-01-11 13:12 | 75284.55 | Planned Total Cost | [16 empty] | 75284.55
|  |  | JDH3-02-008-L-75-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-04-20 | 2025-05-10 | 10-Aug-25 A | 2025-11-18 | 1992-01-11 13:12 | 1992-01-11 13:12 | 75284.55 | Remaining Total Cost | [16 empty] | 41670
|  |  | JDH3-02-008-L-75-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-04-20 | 2025-05-10 | 10-Aug-25 A | 2025-11-18 | 1992-01-11 13:12 | 1992-01-11 13:12 | 75284.55 | Actual Total Cost | [13 empty] | 11606.83 | 21192.62 | 815.1
|  |  | JDH3-02-008-L-75-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-04-23 | 2025-05-03 | 10-Aug-25 A | 2025-11-15 | 1932-06-21 11:02 | 1932-06-21 10:48 | 35587.93 | Planned Total Cost | [16 empty] | 35587.93
|  |  | JDH3-02-008-L-75-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-04-23 | 2025-05-03 | 10-Aug-25 A | 2025-11-15 | 1932-06-21 11:02 | 1932-06-21 10:48 | 35587.93 | Remaining Total Cost | [16 empty] | 23726.48
|  |  | JDH3-02-008-L-75-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-04-23 | 2025-05-03 | 10-Aug-25 A | 2025-11-15 | 1932-06-21 11:02 | 1932-06-21 10:48 | 35587.93 | Actual Total Cost | [13 empty] | 4220.29 | 7358.15 | 283.01
|  |  | JDH3-02-008-L-75-Road Works - RD |  | 2025-01-07 | 2025-06-14 | 20-Feb-25 A | 2025-11-30 | 1043275.27 | 1043275.26 | 1064978.79 | Planned Total Cost | [6 empty] | 639435.22 |  |  |  | 69817.31 | [5 empty] | 283014.71 | 72711.55
|  |  | JDH3-02-008-L-75-Road Works - RD |  | 2025-01-07 | 2025-06-14 | 20-Feb-25 A | 2025-11-30 | 1043275.27 | 1043275.26 | 1064978.79 | Remaining Total Cost | [16 empty] | 21703.52
|  |  | JDH3-02-008-L-75-Road Works - RD |  | 2025-01-07 | 2025-06-14 | 20-Feb-25 A | 2025-11-30 | 1043275.27 | 1043275.26 | 1064978.79 | Actual Total Cost | [7 empty] | 105886.53 | 254279.41 |  |  | 55853.85 | 223415.42 | 103905.8 | 299934.25
|  |  | JDH3-02-008-L-75-(RD)-Subgrade |  | 2025-01-07 | 2025-01-11 | 20-Feb-25 A | 29-Mar-25 A | 236279.19 | 236279.19 | 236279.19 | Planned Total Cost | [6 empty] | 236279.19
|  |  | JDH3-02-008-L-75-(RD)-Subgrade |  | 2025-01-07 | 2025-01-11 | 20-Feb-25 A | 29-Mar-25 A | 236279.19 | 236279.19 | 236279.19 | Remaining Total Cost
|  |  | JDH3-02-008-L-75-(RD)-Subgrade |  | 2025-01-07 | 2025-01-11 | 20-Feb-25 A | 29-Mar-25 A | 236279.19 | 236279.19 | 236279.19 | Actual Total Cost | [7 empty] | 51686.07 | 184593.12
|  |  | JDH3-02-008-L-75-(RD)-AGGREGATE BASE COURSE |  | 2025-01-12 | 2025-01-13 | 20-Feb-25 A | 10-Mar-25 A | 2239-03-09 18:00 | 2239-03-09 18:00 | 123886.75 | Planned Total Cost | [6 empty] | 123886.75
|  |  | JDH3-02-008-L-75-(RD)-AGGREGATE BASE COURSE |  | 2025-01-12 | 2025-01-13 | 20-Feb-25 A | 10-Mar-25 A | 2239-03-09 18:00 | 2239-03-09 18:00 | 123886.75 | Remaining Total Cost
|  |  | JDH3-02-008-L-75-(RD)-AGGREGATE BASE COURSE |  | 2025-01-12 | 2025-01-13 | 20-Feb-25 A | 10-Mar-25 A | 2239-03-09 18:00 | 2239-03-09 18:00 | 123886.75 | Actual Total Cost | [7 empty] | 54200.45 | 69686.3
|  |  | JDH3-02-008-L-75-(RD)-Bituminous base course (Grading I - Class A), including Prime Coat (MC1) |  | 2025-01-25 | 2025-05-07 | 25-Jun-25 A | 20-Aug-25 A | 349086.58 | 349086.58 | 349086.58 | Planned Total Cost | [6 empty] | 279269.27 |  |  |  | 69817.31
|  |  | JDH3-02-008-L-75-(RD)-Bituminous base course (Grading I - Class A), including Prime Coat (MC1) |  | 2025-01-25 | 2025-05-07 | 25-Jun-25 A | 20-Aug-25 A | 349086.58 | 349086.58 | 349086.58 | Remaining Total Cost
|  |  | JDH3-02-008-L-75-(RD)-Bituminous base course (Grading I - Class A), including Prime Coat (MC1) |  | 2025-01-25 | 2025-05-07 | 25-Jun-25 A | 20-Aug-25 A | 349086.58 | 349086.58 | 349086.58 | Actual Total Cost | [11 empty] | 55853.85 | 223415.42 | 69817.31
|  |  | JDH3-02-008-L-75-(RD)-Bituminous concrete wearing course, (Grading I - Class A), including tack coat |  | 2025-05-08 | 2025-05-12 | 28-Sep-25 A | 30-Sep-25 A | 258541.07 | 258541.08 | 258541.07 | Planned Total Cost | [16 empty] | 258541.07
|  |  | JDH3-02-008-L-75-(RD)-Bituminous concrete wearing course, (Grading I - Class A), including tack coat |  | 2025-05-08 | 2025-05-12 | 28-Sep-25 A | 30-Sep-25 A | 258541.07 | 258541.08 | 258541.07 | Remaining Total Cost
|  |  | JDH3-02-008-L-75-(RD)-Bituminous concrete wearing course, (Grading I - Class A), including tack coat |  | 2025-05-08 | 2025-05-12 | 28-Sep-25 A | 30-Sep-25 A | 258541.07 | 258541.08 | 258541.07 | Actual Total Cost | [14 empty] | 258541.08
|  |  | JDH3-02-008-L-75-(RD)-Precast Concrete Curb |  | 2025-05-13 | 2025-05-28 | 16-Aug-25 A | 20-Sep-25 A | 2106-08-28 15:50 | 2106-08-28 15:50 | 75481.66 | Planned Total Cost | [16 empty] | 2770.11 | 72711.55
|  |  | JDH3-02-008-L-75-(RD)-Precast Concrete Curb |  | 2025-05-13 | 2025-05-28 | 16-Aug-25 A | 20-Sep-25 A | 2106-08-28 15:50 | 2106-08-28 15:50 | 75481.66 | Remaining Total Cost
|  |  | JDH3-02-008-L-75-(RD)-Precast Concrete Curb |  | 2025-05-13 | 2025-05-28 | 16-Aug-25 A | 20-Sep-25 A | 2106-08-28 15:50 | 2106-08-28 15:50 | 75481.66 | Actual Total Cost | [13 empty] | 34088.49 | 41393.17
|  |  | JDH3-02-008-L-75-(RD)-Pavement Marking |  | 2025-05-29 | 2025-06-11 | 2025-11-13 | 2025-11-27 | 0 | 0 | 7468.38 | Planned Total Cost | [16 empty] | 7468.38
|  |  | JDH3-02-008-L-75-(RD)-Pavement Marking |  | 2025-05-29 | 2025-06-11 | 2025-11-13 | 2025-11-27 | 0 | 0 | 7468.38 | Remaining Total Cost | [16 empty] | 7468.38
|  |  | JDH3-02-008-L-75-(RD)-Pavement Marking |  | 2025-05-29 | 2025-06-11 | 2025-11-13 | 2025-11-27 | 0 | 0 | 7468.38 | Actual Total Cost
|  |  | JDH3-02-008-L-75-(RD)-Traffic Signage |  | 2025-06-12 | 2025-06-14 | 2025-11-27 | 2025-11-30 | 0 | 0 | 14235.14 | Planned Total Cost | [16 empty] | 14235.14
|  |  | JDH3-02-008-L-75-(RD)-Traffic Signage |  | 2025-06-12 | 2025-06-14 | 2025-11-27 | 2025-11-30 | 0 | 0 | 14235.14 | Remaining Total Cost | [16 empty] | 14235.14
|  |  | JDH3-02-008-L-75-(RD)-Traffic Signage |  | 2025-06-12 | 2025-06-14 | 2025-11-27 | 2025-11-30 | 0 | 0 | 14235.14 | Actual Total Cost
|  |  | Z03 |  | 2025-11-20 | 2026-01-05 | 08-Dec-24 A | 2025-11-29 | 281432.31 | 281432.31 | 717195.4 | Planned Total Cost | [14 empty] | 7460.47 | 230857.17 | 175382.19 | 296865.99 | 6629.56
|  |  | Z03 |  | 2025-11-20 | 2026-01-05 | 08-Dec-24 A | 2025-11-29 | 281432.31 | 281432.31 | 717195.4 | Remaining Total Cost | [15 empty] | 274491.43 | 161271.66
|  |  | Z03 |  | 2025-11-20 | 2026-01-05 | 08-Dec-24 A | 2025-11-29 | 281432.31 | 281432.31 | 717195.4 | Actual Total Cost | [6 empty] | 45031.9 | 25619.98 | 12126.38 | 5775.52 | 2284.74 | 429.18 |  | 47220.91 | 140637.49 | 2306.19
|  |  | L-12 |  | 2025-11-20 | 2025-12-31 | 02-Jul-25 A | 2025-11-29 | 0 | 0 | 211976.95 | Planned Total Cost | [15 empty] | 50705.29 | 161271.66
|  |  | L-12 |  | 2025-11-20 | 2025-12-31 | 02-Jul-25 A | 2025-11-29 | 0 | 0 | 211976.95 | Remaining Total Cost | [15 empty] | 50705.29 | 161271.66
|  |  | L-12 |  | 2025-11-20 | 2025-12-31 | 02-Jul-25 A | 2025-11-29 | 0 | 0 | 211976.95 | Actual Total Cost
|  |  | JDH3-02-008-L-12-TSE Network - TSE |  | 2025-11-26 | 2025-12-31 | 2025-10-25 | 2025-11-29 | 0 | 0 | 211976.95 | Planned Total Cost | [15 empty] | 50705.29 | 161271.66
|  |  | JDH3-02-008-L-12-TSE Network - TSE |  | 2025-11-26 | 2025-12-31 | 2025-10-25 | 2025-11-29 | 0 | 0 | 211976.95 | Remaining Total Cost | [15 empty] | 50705.29 | 161271.66
|  |  | JDH3-02-008-L-12-TSE Network - TSE |  | 2025-11-26 | 2025-12-31 | 2025-10-25 | 2025-11-29 | 0 | 0 | 211976.95 | Actual Total Cost
|  |  | JDH3-02-008-L-12-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-11-26 | 2025-12-24 | 2025-10-25 | 2025-11-22 | 0 | 0 | 22212.36 | Planned Total Cost | [15 empty] | 17769.89 | 4442.47
|  |  | JDH3-02-008-L-12-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-11-26 | 2025-12-24 | 2025-10-25 | 2025-11-22 | 0 | 0 | 22212.36 | Remaining Total Cost | [15 empty] | 17769.89 | 4442.47
|  |  | JDH3-02-008-L-12-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-11-26 | 2025-12-24 | 2025-10-25 | 2025-11-22 | 0 | 0 | 22212.36 | Actual Total Cost
|  |  | JDH3-02-008-L-12-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-11-29 | 2025-12-31 | 2025-10-27 | 2025-11-29 | 0 | 0 | 164677.04 | Planned Total Cost | [15 empty] | 32935.41 | 131741.63
|  |  | JDH3-02-008-L-12-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-11-29 | 2025-12-31 | 2025-10-27 | 2025-11-29 | 0 | 0 | 164677.04 | Remaining Total Cost | [15 empty] | 32935.41 | 131741.63
|  |  | JDH3-02-008-L-12-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-11-29 | 2025-12-31 | 2025-10-27 | 2025-11-29 | 0 | 0 | 164677.04 | Actual Total Cost
|  |  | JDH3-02-008-L-12-(TSE)-Supply and install gate valves-100 mm |  | 2025-12-18 | 2025-12-22 | 2025-11-16 | 2025-11-19 | 0 | 0 | 6465.8 | Planned Total Cost | [16 empty] | 6465.8
|  |  | JDH3-02-008-L-12-(TSE)-Supply and install gate valves-100 mm |  | 2025-12-18 | 2025-12-22 | 2025-11-16 | 2025-11-19 | 0 | 0 | 6465.8 | Remaining Total Cost | [16 empty] | 6465.8
|  |  | JDH3-02-008-L-12-(TSE)-Supply and install gate valves-100 mm |  | 2025-12-18 | 2025-12-22 | 2025-11-16 | 2025-11-19 | 0 | 0 | 6465.8 | Actual Total Cost
|  |  | JDH3-02-008-L-12-(TSE)-Supply and install gate valves-250 mm |  | 2025-12-18 | 2025-12-22 | 2025-11-16 | 2025-11-19 | 0 | 0 | 7698.34 | Planned Total Cost | [16 empty] | 7698.34
|  |  | JDH3-02-008-L-12-(TSE)-Supply and install gate valves-250 mm |  | 2025-12-18 | 2025-12-22 | 2025-11-16 | 2025-11-19 | 0 | 0 | 7698.34 | Remaining Total Cost | [16 empty] | 7698.34
|  |  | JDH3-02-008-L-12-(TSE)-Supply and install gate valves-250 mm |  | 2025-12-18 | 2025-12-22 | 2025-11-16 | 2025-11-19 | 0 | 0 | 7698.34 | Actual Total Cost
|  |  | JDH3-02-008-L-12-(TSE)-Supply and install of Air valves-50 mm. |  | 2025-12-18 | 2025-12-22 | 2025-11-16 | 2025-11-19 | 0 | 0 | 7444.14 | Planned Total Cost | [16 empty] | 7444.14
|  |  | JDH3-02-008-L-12-(TSE)-Supply and install of Air valves-50 mm. |  | 2025-12-18 | 2025-12-22 | 2025-11-16 | 2025-11-19 | 0 | 0 | 7444.14 | Remaining Total Cost | [16 empty] | 7444.14
|  |  | JDH3-02-008-L-12-(TSE)-Supply and install of Air valves-50 mm. |  | 2025-12-18 | 2025-12-22 | 2025-11-16 | 2025-11-19 | 0 | 0 | 7444.14 | Actual Total Cost
|  |  | JDH3-02-008-L-12-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2025-12-03 | 2025-12-24 | 2025-11-01 | 2025-11-22 | 0 | 0 | 3479.28 | Planned Total Cost | [16 empty] | 3479.28
|  |  | JDH3-02-008-L-12-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2025-12-03 | 2025-12-24 | 2025-11-01 | 2025-11-22 | 0 | 0 | 3479.28 | Remaining Total Cost | [16 empty] | 3479.28
|  |  | JDH3-02-008-L-12-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2025-12-03 | 2025-12-24 | 2025-11-01 | 2025-11-22 | 0 | 0 | 3479.28 | Actual Total Cost
|  |  | L-13 |  | 2025-11-20 | 2026-01-05 | 18-Feb-25 A | 2025-10-16 | 2079-10-02 18:14 | 2079-10-02 18:00 | 174461.5 | Planned Total Cost | [15 empty] | 84962.43 | 1650.85 | 81218.66 | 6629.56
|  |  | L-13 |  | 2025-11-20 | 2026-01-05 | 18-Feb-25 A | 2025-10-16 | 2079-10-02 18:14 | 2079-10-02 18:00 | 174461.5 | Remaining Total Cost | [15 empty] | 108805.75
|  |  | L-13 |  | 2025-11-20 | 2026-01-05 | 18-Feb-25 A | 2025-10-16 | 2079-10-02 18:14 | 2079-10-02 18:00 | 174461.5 | Actual Total Cost | [8 empty] | 5158.03 |  |  |  |  | 12652.9 | 46072.79 | 1772.03
|  |  | JDH3-02-008-L-13-TSE Network - TSE |  | 2025-11-29 | 2026-01-05 | 05-Mar-25 A | 2025-10-16 | 2079-10-02 18:14 | 2079-10-02 18:00 | 174461.5 | Planned Total Cost | [15 empty] | 84962.43 | 1650.85 | 81218.66 | 6629.56
|  |  | JDH3-02-008-L-13-TSE Network - TSE |  | 2025-11-29 | 2026-01-05 | 05-Mar-25 A | 2025-10-16 | 2079-10-02 18:14 | 2079-10-02 18:00 | 174461.5 | Remaining Total Cost | [15 empty] | 108805.75
|  |  | JDH3-02-008-L-13-TSE Network - TSE |  | 2025-11-29 | 2026-01-05 | 05-Mar-25 A | 2025-10-16 | 2079-10-02 18:14 | 2079-10-02 18:00 | 174461.5 | Actual Total Cost | [8 empty] | 5158.03 |  |  |  |  | 12652.9 | 46072.79 | 1772.03
|  |  | JDH3-02-008-L-13-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-11-29 | 2026-01-05 | 05-Mar-25 A | 2025-10-14 | 2079-10-02 18:14 | 2079-10-02 18:00 | 99443.41 | Planned Total Cost | [15 empty] | 9944.34 | 1650.85 | 81218.66 | 6629.56
|  |  | JDH3-02-008-L-13-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-11-29 | 2026-01-05 | 05-Mar-25 A | 2025-10-14 | 2079-10-02 18:14 | 2079-10-02 18:00 | 99443.41 | Remaining Total Cost | [15 empty] | 33787.66
|  |  | JDH3-02-008-L-13-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-11-29 | 2026-01-05 | 05-Mar-25 A | 2025-10-14 | 2079-10-02 18:14 | 2079-10-02 18:00 | 99443.41 | Actual Total Cost | [8 empty] | 5158.03 |  |  |  |  | 12652.9 | 46072.79 | 1772.03
|  |  | JDH3-02-008-L-13-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-12-07 | 2025-12-29 | 2025-10-02 | 2025-10-16 | 0 | 0 | 232.14 | Planned Total Cost | [15 empty] | 232.14
|  |  | JDH3-02-008-L-13-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-12-07 | 2025-12-29 | 2025-10-02 | 2025-10-16 | 0 | 0 | 232.14 | Remaining Total Cost | [15 empty] | 232.14
|  |  | JDH3-02-008-L-13-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-12-07 | 2025-12-29 | 2025-10-02 | 2025-10-16 | 0 | 0 | 232.14 | Actual Total Cost
|  |  | JDH3-02-008-L-13-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2025-12-09 | 2025-12-20 | 2025-10-05 | 2025-10-16 | 0 | 0 | 68320.14 | Planned Total Cost | [15 empty] | 68320.14
|  |  | JDH3-02-008-L-13-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2025-12-09 | 2025-12-20 | 2025-10-05 | 2025-10-16 | 0 | 0 | 68320.14 | Remaining Total Cost | [15 empty] | 68320.14
|  |  | JDH3-02-008-L-13-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2025-12-09 | 2025-12-20 | 2025-10-05 | 2025-10-16 | 0 | 0 | 68320.14 | Actual Total Cost
|  |  | JDH3-02-008-L-13-(TSE)-Supply and install gate valves-100 mm |  | 2025-12-23 | 2025-12-27 | 2025-10-09 | 2025-10-14 | 0 | 0 | 6465.8 | Planned Total Cost | [15 empty] | 6465.8
|  |  | JDH3-02-008-L-13-(TSE)-Supply and install gate valves-100 mm |  | 2025-12-23 | 2025-12-27 | 2025-10-09 | 2025-10-14 | 0 | 0 | 6465.8 | Remaining Total Cost | [15 empty] | 6465.8
|  |  | JDH3-02-008-L-13-(TSE)-Supply and install gate valves-100 mm |  | 2025-12-23 | 2025-12-27 | 2025-10-09 | 2025-10-14 | 0 | 0 | 6465.8 | Actual Total Cost
|  |  | L-14 |  | 2025-11-20 | 2026-01-04 | 17-Dec-24 A | 2025-10-06 | 2043-09-29 15:36 | 2043-09-29 15:36 | 79777.37 | Planned Total Cost | [14 empty] | 7460.47 | 5172.64 |  | 67144.26
|  |  | L-14 |  | 2025-11-20 | 2026-01-04 | 17-Dec-24 A | 2025-10-06 | 2043-09-29 15:36 | 2043-09-29 15:36 | 79777.37 | Remaining Total Cost | [15 empty] | 27273.72
|  |  | L-14 |  | 2025-11-20 | 2026-01-04 | 17-Dec-24 A | 2025-10-06 | 2043-09-29 15:36 | 2043-09-29 15:36 | 79777.37 | Actual Total Cost | [6 empty] | 33994.55 | 5683.1 | [5 empty] | 356.76 | 11935.07 | 534.16
|  |  | JDH3-02-008-L-14-TSE Network - TSE |  | 2025-12-04 | 2026-01-04 | 02-Jan-25 A | 2025-10-06 | 52503.65 | 2043-09-29 15:36 | 79777.37 | Planned Total Cost | [14 empty] | 7460.47 | 5172.64 |  | 67144.26
|  |  | JDH3-02-008-L-14-TSE Network - TSE |  | 2025-12-04 | 2026-01-04 | 02-Jan-25 A | 2025-10-06 | 52503.65 | 2043-09-29 15:36 | 79777.37 | Remaining Total Cost | [15 empty] | 27273.72
|  |  | JDH3-02-008-L-14-TSE Network - TSE |  | 2025-12-04 | 2026-01-04 | 02-Jan-25 A | 2025-10-06 | 52503.65 | 2043-09-29 15:36 | 79777.37 | Actual Total Cost | [6 empty] | 33994.55 | 5683.1 | [5 empty] | 356.76 | 11935.07 | 534.16
|  |  | JDH3-02-008-L-14-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-12-04 | 2026-01-04 | 02-Jan-25 A | 2025-10-04 | 2043-09-29 15:36 | 2043-09-29 15:36 | 74604.73 | Planned Total Cost | [14 empty] | 7460.47 |  |  | 67144.26
|  |  | JDH3-02-008-L-14-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-12-04 | 2026-01-04 | 02-Jan-25 A | 2025-10-04 | 2043-09-29 15:36 | 2043-09-29 15:36 | 74604.73 | Remaining Total Cost | [15 empty] | 22101.08
|  |  | JDH3-02-008-L-14-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-12-04 | 2026-01-04 | 02-Jan-25 A | 2025-10-04 | 2043-09-29 15:36 | 2043-09-29 15:36 | 74604.73 | Actual Total Cost | [6 empty] | 33994.55 | 5683.1 | [5 empty] | 356.76 | 11935.07 | 534.16
|  |  | JDH3-02-008-L-14-(TSE)-Supply and install gate valves-100 mm |  | 2025-12-24 | 2025-12-25 | 2025-10-04 | 2025-10-06 | 0 | 0 | 5172.64 | Planned Total Cost | [15 empty] | 5172.64
|  |  | JDH3-02-008-L-14-(TSE)-Supply and install gate valves-100 mm |  | 2025-12-24 | 2025-12-25 | 2025-10-04 | 2025-10-06 | 0 | 0 | 5172.64 | Remaining Total Cost | [15 empty] | 5172.64
|  |  | JDH3-02-008-L-14-(TSE)-Supply and install gate valves-100 mm |  | 2025-12-24 | 2025-12-25 | 2025-10-04 | 2025-10-06 | 0 | 0 | 5172.64 | Actual Total Cost
|  |  | L-15 |  | 2025-11-20 | 2025-12-24 | 08-Dec-24 A | 2025-10-06 | 1963-03-31 09:50 | 1963-03-31 09:50 | 28274.05 | Planned Total Cost | [15 empty] | 7482.78 |  | 20791.27
|  |  | L-15 |  | 2025-11-20 | 2025-12-24 | 08-Dec-24 A | 2025-10-06 | 1963-03-31 09:50 | 1963-03-31 09:50 | 28274.05 | Remaining Total Cost | [15 empty] | 5172.64
|  |  | L-15 |  | 2025-11-20 | 2025-12-24 | 08-Dec-24 A | 2025-10-06 | 1963-03-31 09:50 | 1963-03-31 09:50 | 28274.05 | Actual Total Cost | [6 empty] | 6607.39 | 9867.57 |  |  | 1630.9 | 429.18 |  | 2256.23 | 2310.14
|  |  | JDH3-02-008-L-15-TSE Network - TSE |  | 2025-12-09 | 2025-12-24 | 21-Jan-25 A | 2025-10-06 | 1963-03-31 09:50 | 1963-03-31 09:50 | 28274.05 | Planned Total Cost | [15 empty] | 7482.78 |  | 20791.27
|  |  | JDH3-02-008-L-15-TSE Network - TSE |  | 2025-12-09 | 2025-12-24 | 21-Jan-25 A | 2025-10-06 | 1963-03-31 09:50 | 1963-03-31 09:50 | 28274.05 | Remaining Total Cost | [15 empty] | 5172.64
|  |  | JDH3-02-008-L-15-TSE Network - TSE |  | 2025-12-09 | 2025-12-24 | 21-Jan-25 A | 2025-10-06 | 1963-03-31 09:50 | 1963-03-31 09:50 | 28274.05 | Actual Total Cost | [6 empty] | 6607.39 | 9867.57 |  |  | 1630.9 | 429.18 |  | 2256.23 | 2310.14
|  |  | JDH3-02-008-L-15-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-12-09 | 2025-12-24 | 21-Jan-25 A | 27-Sep-25 A | 1963-03-31 09:50 | 1963-03-31 09:50 | 23101.41 | Planned Total Cost | [15 empty] | 2310.14 |  | 20791.27
|  |  | JDH3-02-008-L-15-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-12-09 | 2025-12-24 | 21-Jan-25 A | 27-Sep-25 A | 1963-03-31 09:50 | 1963-03-31 09:50 | 23101.41 | Remaining Total Cost
|  |  | JDH3-02-008-L-15-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-12-09 | 2025-12-24 | 21-Jan-25 A | 27-Sep-25 A | 1963-03-31 09:50 | 1963-03-31 09:50 | 23101.41 | Actual Total Cost | [6 empty] | 6607.39 | 9867.57 |  |  | 1630.9 | 429.18 |  | 2256.23 | 2310.14
|  |  | JDH3-02-008-L-15-(TSE)-Supply and install gate valves-100 mm |  | 2025-12-18 | 2025-12-22 | 2025-10-02 | 2025-10-06 | 0 | 0 | 5172.64 | Planned Total Cost | [15 empty] | 5172.64
|  |  | JDH3-02-008-L-15-(TSE)-Supply and install gate valves-100 mm |  | 2025-12-18 | 2025-12-22 | 2025-10-02 | 2025-10-06 | 0 | 0 | 5172.64 | Remaining Total Cost | [15 empty] | 5172.64
|  |  | JDH3-02-008-L-15-(TSE)-Supply and install gate valves-100 mm |  | 2025-12-18 | 2025-12-22 | 2025-10-02 | 2025-10-06 | 0 | 0 | 5172.64 | Actual Total Cost
|  |  | L-16 |  | 2025-11-20 | 2026-01-03 | 01-Jan-25 A | 2025-10-23 | 2283-10-09 11:46 | 2283-10-09 12:00 | 222705.52 | Planned Total Cost | [15 empty] | 82534.03 | 12459.69 | 127711.8
|  |  | L-16 |  | 2025-11-20 | 2026-01-03 | 01-Jan-25 A | 2025-10-23 | 2283-10-09 11:46 | 2283-10-09 12:00 | 222705.52 | Remaining Total Cost | [15 empty] | 82534.03
|  |  | L-16 |  | 2025-11-20 | 2026-01-03 | 01-Jan-25 A | 2025-10-23 | 2283-10-09 11:46 | 2283-10-09 12:00 | 222705.52 | Actual Total Cost | [6 empty] | 4429.97 | 10069.31 | 6968.35 | 5775.52 | 653.84 |  |  | 31955.02 | 80319.49
|  |  | JDH3-02-008-L-16-TSE Network - TSE |  | 2025-11-29 | 2026-01-03 | 15-Jan-25 A | 2025-10-23 | 2283-10-09 11:46 | 2283-10-09 12:00 | 222705.52 | Planned Total Cost | [15 empty] | 82534.03 | 12459.69 | 127711.8
|  |  | JDH3-02-008-L-16-TSE Network - TSE |  | 2025-11-29 | 2026-01-03 | 15-Jan-25 A | 2025-10-23 | 2283-10-09 11:46 | 2283-10-09 12:00 | 222705.52 | Remaining Total Cost | [15 empty] | 82534.03
|  |  | JDH3-02-008-L-16-TSE Network - TSE |  | 2025-11-29 | 2026-01-03 | 15-Jan-25 A | 2025-10-23 | 2283-10-09 11:46 | 2283-10-09 12:00 | 222705.52 | Actual Total Cost | [6 empty] | 4429.97 | 10069.31 | 6968.35 | 5775.52 | 653.84 |  |  | 31955.02 | 80319.49
|  |  | JDH3-02-008-L-16-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-11-29 | 2025-12-31 | 2025-10-02 | 2025-10-23 | 0 | 0 | 54108.64 | Planned Total Cost | [15 empty] | 54108.64
|  |  | JDH3-02-008-L-16-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-11-29 | 2025-12-31 | 2025-10-02 | 2025-10-23 | 0 | 0 | 54108.64 | Remaining Total Cost | [15 empty] | 54108.64
|  |  | JDH3-02-008-L-16-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-11-29 | 2025-12-31 | 2025-10-02 | 2025-10-23 | 0 | 0 | 54108.64 | Actual Total Cost
|  |  | JDH3-02-008-L-16-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-12-02 | 2026-01-03 | 15-Jan-25 A | 2025-10-07 | 2283-10-09 11:46 | 2283-10-09 12:00 | 155746.1 | Planned Total Cost | [15 empty] | 15574.61 | 12459.69 | 127711.8
|  |  | JDH3-02-008-L-16-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-12-02 | 2026-01-03 | 15-Jan-25 A | 2025-10-07 | 2283-10-09 11:46 | 2283-10-09 12:00 | 155746.1 | Remaining Total Cost | [15 empty] | 15574.61
|  |  | JDH3-02-008-L-16-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-12-02 | 2026-01-03 | 15-Jan-25 A | 2025-10-07 | 2283-10-09 11:46 | 2283-10-09 12:00 | 155746.1 | Actual Total Cost | [6 empty] | 4429.97 | 10069.31 | 6968.35 | 5775.52 | 653.84 |  |  | 31955.02 | 80319.49
|  |  | JDH3-02-008-L-16-(TSE)-Supply and install gate valves-100 mm |  | 2025-12-23 | 2025-12-27 | 2025-10-02 | 2025-10-06 | 0 | 0 | 2586.32 | Planned Total Cost | [15 empty] | 2586.32
|  |  | JDH3-02-008-L-16-(TSE)-Supply and install gate valves-100 mm |  | 2025-12-23 | 2025-12-27 | 2025-10-02 | 2025-10-06 | 0 | 0 | 2586.32 | Remaining Total Cost | [15 empty] | 2586.32
|  |  | JDH3-02-008-L-16-(TSE)-Supply and install gate valves-100 mm |  | 2025-12-23 | 2025-12-27 | 2025-10-02 | 2025-10-06 | 0 | 0 | 2586.32 | Actual Total Cost
|  |  | JDH3-02-008-L-16-(TSE)-Supply and install gate valves-250 mm |  | 2025-12-23 | 2025-12-27 | 2025-10-02 | 2025-10-06 | 0 | 0 | 10264.45 | Planned Total Cost | [15 empty] | 10264.45
|  |  | JDH3-02-008-L-16-(TSE)-Supply and install gate valves-250 mm |  | 2025-12-23 | 2025-12-27 | 2025-10-02 | 2025-10-06 | 0 | 0 | 10264.45 | Remaining Total Cost | [15 empty] | 10264.45
|  |  | JDH3-02-008-L-16-(TSE)-Supply and install gate valves-250 mm |  | 2025-12-23 | 2025-12-27 | 2025-10-02 | 2025-10-06 | 0 | 0 | 10264.45 | Actual Total Cost
|  |  | Z04 |  | 2026-04-15 | 2026-06-17 | 10-Feb-25 A | 2026-06-18 | 225708.28 | 225708.29 | 863854.94 | Planned Total Cost | [15 empty] | 83798.4 | 1966.95 |  |  |  |  | 17389.98 | 212977.01 | 547722.6
|  |  | Z04 |  | 2026-04-15 | 2026-06-17 | 10-Feb-25 A | 2026-06-18 | 225708.28 | 225708.29 | 863854.94 | Remaining Total Cost | [15 empty] | 101547.61 | 1966.95 | [5 empty] | 78102.76 | 456529.35
|  |  | Z04 |  | 2026-04-15 | 2026-06-17 | 10-Feb-25 A | 2026-06-18 | 225708.28 | 225708.29 | 863854.94 | Actual Total Cost | [8 empty] | 25258.08 | 7424.98 | 2451.2 | 7033.63 |  | 121916.93 | 60761.39 | 862.08
|  |  | RCB |  | 2026-04-15 | 2026-05-07 | 2026-05-26 | 2026-06-18 | 0 | 0 | 534632.1 | Planned Total Cost | [22 empty] | 78102.76 | 456529.35
|  |  | RCB |  | 2026-04-15 | 2026-05-07 | 2026-05-26 | 2026-06-18 | 0 | 0 | 534632.1 | Remaining Total Cost | [22 empty] | 78102.76 | 456529.35
|  |  | RCB |  | 2026-04-15 | 2026-05-07 | 2026-05-26 | 2026-06-18 | 0 | 0 | 534632.1 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z04-Storm Network - ST |  | 2026-04-15 | 2026-05-07 | 2026-05-26 | 2026-06-18 | 0 | 0 | 534632.1 | Planned Total Cost | [22 empty] | 78102.76 | 456529.35
|  |  | JDH3-02-008-RCB-Z04-Storm Network - ST |  | 2026-04-15 | 2026-05-07 | 2026-05-26 | 2026-06-18 | 0 | 0 | 534632.1 | Remaining Total Cost | [22 empty] | 78102.76 | 456529.35
|  |  | JDH3-02-008-RCB-Z04-Storm Network - ST |  | 2026-04-15 | 2026-05-07 | 2026-05-26 | 2026-06-18 | 0 | 0 | 534632.1 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z04-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-04-15 | 2026-04-30 | 2026-05-26 | 2026-06-11 | 0 | 0 | 195461.28 | Planned Total Cost | [22 empty] | 56748.93 | 138712.36
|  |  | JDH3-02-008-RCB-Z04-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-04-15 | 2026-04-30 | 2026-05-26 | 2026-06-11 | 0 | 0 | 195461.28 | Remaining Total Cost | [22 empty] | 56748.93 | 138712.36
|  |  | JDH3-02-008-RCB-Z04-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-04-15 | 2026-04-30 | 2026-05-26 | 2026-06-11 | 0 | 0 | 195461.28 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z04-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-04-18 | 2026-04-30 | 2026-05-28 | 2026-06-11 | 0 | 0 | 98663.19 | Planned Total Cost | [22 empty] | 20275.28 | 78387.9
|  |  | JDH3-02-008-RCB-Z04-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-04-18 | 2026-04-30 | 2026-05-28 | 2026-06-11 | 0 | 0 | 98663.19 | Remaining Total Cost | [22 empty] | 20275.28 | 78387.9
|  |  | JDH3-02-008-RCB-Z04-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-04-18 | 2026-04-30 | 2026-05-28 | 2026-06-11 | 0 | 0 | 98663.19 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z04-(ST)- Single Catchbasine Works |  | 2026-04-20 | 2026-05-07 | 2026-05-31 | 2026-06-18 | 0 | 0 | 98049.7 | Planned Total Cost | [22 empty] | 1078.55 | 96971.15
|  |  | JDH3-02-008-RCB-Z04-(ST)- Single Catchbasine Works |  | 2026-04-20 | 2026-05-07 | 2026-05-31 | 2026-06-18 | 0 | 0 | 98049.7 | Remaining Total Cost | [22 empty] | 1078.55 | 96971.15
|  |  | JDH3-02-008-RCB-Z04-(ST)- Single Catchbasine Works |  | 2026-04-20 | 2026-05-07 | 2026-05-31 | 2026-06-18 | 0 | 0 | 98049.7 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z04-(ST)- Double Catchbasine Works |  | 2026-04-23 | 2026-05-04 | 2026-06-03 | 2026-06-15 | 0 | 0 | 142457.93 | Planned Total Cost | [23 empty] | 142457.93
|  |  | JDH3-02-008-RCB-Z04-(ST)- Double Catchbasine Works |  | 2026-04-23 | 2026-05-04 | 2026-06-03 | 2026-06-15 | 0 | 0 | 142457.93 | Remaining Total Cost | [23 empty] | 142457.93
|  |  | JDH3-02-008-RCB-Z04-(ST)- Double Catchbasine Works |  | 2026-04-23 | 2026-05-04 | 2026-06-03 | 2026-06-15 | 0 | 0 | 142457.93 | Actual Total Cost
|  |  | L-39 |  | 2026-04-15 | 2026-05-21 | 17-Jun-25 A | 2025-10-06 | 2100-06-19 23:31 | 2100-06-19 23:46 | 75807.3 | Planned Total Cost | [15 empty] | 2586.32 | [5 empty] | 17389.98 | 55830.99
|  |  | L-39 |  | 2026-04-15 | 2026-05-21 | 17-Jun-25 A | 2025-10-06 | 2100-06-19 23:31 | 2100-06-19 23:46 | 75807.3 | Remaining Total Cost | [15 empty] | 2586.32
|  |  | L-39 |  | 2026-04-15 | 2026-05-21 | 17-Jun-25 A | 2025-10-06 | 2100-06-19 23:31 | 2100-06-19 23:46 | 75807.3 | Actual Total Cost | [13 empty] | 73220.99
|  |  | JDH3-02-008-L-39-TSE Network - TSE |  | 2026-04-23 | 2026-05-21 | 02-Aug-25 A | 2025-10-06 | 2100-06-19 23:31 | 2100-06-19 23:46 | 75807.3 | Planned Total Cost | [15 empty] | 2586.32 | [5 empty] | 17389.98 | 55830.99
|  |  | JDH3-02-008-L-39-TSE Network - TSE |  | 2026-04-23 | 2026-05-21 | 02-Aug-25 A | 2025-10-06 | 2100-06-19 23:31 | 2100-06-19 23:46 | 75807.3 | Remaining Total Cost | [15 empty] | 2586.32
|  |  | JDH3-02-008-L-39-TSE Network - TSE |  | 2026-04-23 | 2026-05-21 | 02-Aug-25 A | 2025-10-06 | 2100-06-19 23:31 | 2100-06-19 23:46 | 75807.3 | Actual Total Cost | [13 empty] | 73220.99
|  |  | JDH3-02-008-L-39-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-04-23 | 2026-05-21 | 02-Aug-25 A | 18-Aug-25 A | 2100-06-19 23:31 | 2100-06-19 23:46 | 73220.98 | Planned Total Cost | [21 empty] | 17389.98 | 55830.99
|  |  | JDH3-02-008-L-39-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-04-23 | 2026-05-21 | 02-Aug-25 A | 18-Aug-25 A | 2100-06-19 23:31 | 2100-06-19 23:46 | 73220.98 | Remaining Total Cost
|  |  | JDH3-02-008-L-39-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-04-23 | 2026-05-21 | 02-Aug-25 A | 18-Aug-25 A | 2100-06-19 23:31 | 2100-06-19 23:46 | 73220.98 | Actual Total Cost | [13 empty] | 73220.99
|  |  | JDH3-02-008-L-39-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-11 | 2026-05-14 | 2025-10-02 | 2025-10-06 | 0 | 0 | 2586.32 | Planned Total Cost | [15 empty] | 2586.32
|  |  | JDH3-02-008-L-39-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-11 | 2026-05-14 | 2025-10-02 | 2025-10-06 | 0 | 0 | 2586.32 | Remaining Total Cost | [15 empty] | 2586.32
|  |  | JDH3-02-008-L-39-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-11 | 2026-05-14 | 2025-10-02 | 2025-10-06 | 0 | 0 | 2586.32 | Actual Total Cost
|  |  | L-40 |  | 2026-04-23 | 2026-05-25 | 14-Jul-25 A | 2025-10-26 | 0 | 0 | 69409.66 | Planned Total Cost | [15 empty] | 69409.66
|  |  | L-40 |  | 2026-04-23 | 2026-05-25 | 14-Jul-25 A | 2025-10-26 | 0 | 0 | 69409.66 | Remaining Total Cost | [15 empty] | 69409.66
|  |  | L-40 |  | 2026-04-23 | 2026-05-25 | 14-Jul-25 A | 2025-10-26 | 0 | 0 | 69409.66 | Actual Total Cost
|  |  | JDH3-02-008-L-40-TSE Network - TSE |  | 2026-05-02 | 2026-05-25 | 2025-10-02 | 2025-10-26 | 0 | 0 | 69409.66 | Planned Total Cost | [15 empty] | 69409.66
|  |  | JDH3-02-008-L-40-TSE Network - TSE |  | 2026-05-02 | 2026-05-25 | 2025-10-02 | 2025-10-26 | 0 | 0 | 69409.66 | Remaining Total Cost | [15 empty] | 69409.66
|  |  | JDH3-02-008-L-40-TSE Network - TSE |  | 2026-05-02 | 2026-05-25 | 2025-10-02 | 2025-10-26 | 0 | 0 | 69409.66 | Actual Total Cost
|  |  | JDH3-02-008-L-40-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-05-02 | 2026-05-25 | 2025-10-02 | 2025-10-26 | 0 | 0 | 68116.5 | Planned Total Cost | [15 empty] | 68116.5
|  |  | JDH3-02-008-L-40-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-05-02 | 2026-05-25 | 2025-10-02 | 2025-10-26 | 0 | 0 | 68116.5 | Remaining Total Cost | [15 empty] | 68116.5
|  |  | JDH3-02-008-L-40-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-05-02 | 2026-05-25 | 2025-10-02 | 2025-10-26 | 0 | 0 | 68116.5 | Actual Total Cost
|  |  | JDH3-02-008-L-40-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-17 | 2026-05-20 | 2025-10-18 | 2025-10-21 | 0 | 0 | 1293.16 | Planned Total Cost | [15 empty] | 1293.16
|  |  | JDH3-02-008-L-40-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-17 | 2026-05-20 | 2025-10-18 | 2025-10-21 | 0 | 0 | 1293.16 | Remaining Total Cost | [15 empty] | 1293.16
|  |  | JDH3-02-008-L-40-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-17 | 2026-05-20 | 2025-10-18 | 2025-10-21 | 0 | 0 | 1293.16 | Actual Total Cost
|  |  | L-41 |  | 2026-05-02 | 2026-06-04 | 17-Mar-25 A | 2025-10-26 | 2005-01-28 05:17 | 2005-01-28 05:17 | 60008.91 | Planned Total Cost | [15 empty] | 3879.48 | [6 empty] | 50516.49 | 5612.94
|  |  | L-41 |  | 2026-05-02 | 2026-06-04 | 17-Mar-25 A | 2025-10-26 | 2005-01-28 05:17 | 2005-01-28 05:17 | 60008.91 | Remaining Total Cost | [15 empty] | 21628.69
|  |  | L-41 |  | 2026-05-02 | 2026-06-04 | 17-Mar-25 A | 2025-10-26 | 2005-01-28 05:17 | 2005-01-28 05:17 | 60008.91 | Actual Total Cost | [9 empty] | 4156.29 | 2451.2 | 7033.63 |  | 1462.83 | 22414.19 | 862.08
|  |  | JDH3-02-008-L-41-TSE Network - TSE |  | 2026-05-10 | 2026-06-04 | 05-Apr-25 A | 2025-10-26 | 2005-01-28 05:17 | 2005-01-28 05:17 | 60008.91 | Planned Total Cost | [15 empty] | 3879.48 | [6 empty] | 50516.49 | 5612.94
|  |  | JDH3-02-008-L-41-TSE Network - TSE |  | 2026-05-10 | 2026-06-04 | 05-Apr-25 A | 2025-10-26 | 2005-01-28 05:17 | 2005-01-28 05:17 | 60008.91 | Remaining Total Cost | [15 empty] | 21628.69
|  |  | JDH3-02-008-L-41-TSE Network - TSE |  | 2026-05-10 | 2026-06-04 | 05-Apr-25 A | 2025-10-26 | 2005-01-28 05:17 | 2005-01-28 05:17 | 60008.91 | Actual Total Cost | [9 empty] | 4156.29 | 2451.2 | 7033.63 |  | 1462.83 | 22414.19 | 862.08
|  |  | JDH3-02-008-L-41-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-05-10 | 2026-06-04 | 05-Apr-25 A | 2025-10-26 | 2005-01-28 05:17 | 2005-01-28 05:17 | 56129.43 | Planned Total Cost | [22 empty] | 50516.49 | 5612.94
|  |  | JDH3-02-008-L-41-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-05-10 | 2026-06-04 | 05-Apr-25 A | 2025-10-26 | 2005-01-28 05:17 | 2005-01-28 05:17 | 56129.43 | Remaining Total Cost | [15 empty] | 17749.21
|  |  | JDH3-02-008-L-41-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-05-10 | 2026-06-04 | 05-Apr-25 A | 2025-10-26 | 2005-01-28 05:17 | 2005-01-28 05:17 | 56129.43 | Actual Total Cost | [9 empty] | 4156.29 | 2451.2 | 7033.63 |  | 1462.83 | 22414.19 | 862.08
|  |  | JDH3-02-008-L-41-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-25 | 2026-05-28 | 2025-10-02 | 2025-10-07 | 0 | 0 | 3879.48 | Planned Total Cost | [15 empty] | 3879.48
|  |  | JDH3-02-008-L-41-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-25 | 2026-05-28 | 2025-10-02 | 2025-10-07 | 0 | 0 | 3879.48 | Remaining Total Cost | [15 empty] | 3879.48
|  |  | JDH3-02-008-L-41-(TSE)-Supply and install gate valves-100 mm |  | 2026-05-25 | 2026-05-28 | 2025-10-02 | 2025-10-07 | 0 | 0 | 3879.48 | Actual Total Cost
|  |  | L-38 |  | 2026-05-10 | 2026-06-17 | 10-Feb-25 A | 2025-11-09 | 2212-05-30 01:55 | 2212-05-30 01:55 | 123996.97 | Planned Total Cost | [15 empty] | 7922.94 | 1966.95 | [5 empty] | 28526.77 | 85580.31
|  |  | L-38 |  | 2026-05-10 | 2026-06-17 | 10-Feb-25 A | 2025-11-09 | 2212-05-30 01:55 | 2212-05-30 01:55 | 123996.97 | Remaining Total Cost | [15 empty] | 7922.94 | 1966.95
|  |  | L-38 |  | 2026-05-10 | 2026-06-17 | 10-Feb-25 A | 2025-11-09 | 2212-05-30 01:55 | 2212-05-30 01:55 | 123996.97 | Actual Total Cost | [8 empty] | 25258.08 | 3268.69 |  |  |  | 47233.11 | 38347.2
|  |  | JDH3-02-008-L-38-TSE Network - TSE |  | 2026-05-18 | 2026-06-17 | 05-Mar-25 A | 2025-11-09 | 2212-05-30 01:55 | 2212-05-30 01:55 | 123996.97 | Planned Total Cost | [15 empty] | 7922.94 | 1966.95 | [5 empty] | 28526.77 | 85580.31
|  |  | JDH3-02-008-L-38-TSE Network - TSE |  | 2026-05-18 | 2026-06-17 | 05-Mar-25 A | 2025-11-09 | 2212-05-30 01:55 | 2212-05-30 01:55 | 123996.97 | Remaining Total Cost | [15 empty] | 7922.94 | 1966.95
|  |  | JDH3-02-008-L-38-TSE Network - TSE |  | 2026-05-18 | 2026-06-17 | 05-Mar-25 A | 2025-11-09 | 2212-05-30 01:55 | 2212-05-30 01:55 | 123996.97 | Actual Total Cost | [8 empty] | 25258.08 | 3268.69 |  |  |  | 47233.11 | 38347.2
|  |  | JDH3-02-008-L-38-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-05-26 | 2026-06-15 | 2025-10-27 | 2025-11-09 | 0 | 0 | 898.39 | Planned Total Cost | [15 empty] | 224.6 | 673.79
|  |  | JDH3-02-008-L-38-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-05-26 | 2026-06-15 | 2025-10-27 | 2025-11-09 | 0 | 0 | 898.39 | Remaining Total Cost | [15 empty] | 224.6 | 673.79
|  |  | JDH3-02-008-L-38-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-05-26 | 2026-06-15 | 2025-10-27 | 2025-11-09 | 0 | 0 | 898.39 | Actual Total Cost
|  |  | JDH3-02-008-L-38-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-05-18 | 2026-06-17 | 05-Mar-25 A | 27-Sep-25 A | 2212-05-30 01:55 | 2212-05-30 01:55 | 114107.08 | Planned Total Cost | [22 empty] | 28526.77 | 85580.31
|  |  | JDH3-02-008-L-38-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-05-18 | 2026-06-17 | 05-Mar-25 A | 27-Sep-25 A | 2212-05-30 01:55 | 2212-05-30 01:55 | 114107.08 | Remaining Total Cost
|  |  | JDH3-02-008-L-38-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-05-18 | 2026-06-17 | 05-Mar-25 A | 27-Sep-25 A | 2212-05-30 01:55 | 2212-05-30 01:55 | 114107.08 | Actual Total Cost | [8 empty] | 25258.08 | 3268.69 |  |  |  | 47233.11 | 38347.2
|  |  | JDH3-02-008-L-38-(TSE)-Supply and install gate valves-100 mm |  | 2026-06-09 | 2026-06-13 | 2025-11-03 | 2025-11-06 | 0 | 0 | 1293.16 | Planned Total Cost | [16 empty] | 1293.16
|  |  | JDH3-02-008-L-38-(TSE)-Supply and install gate valves-100 mm |  | 2026-06-09 | 2026-06-13 | 2025-11-03 | 2025-11-06 | 0 | 0 | 1293.16 | Remaining Total Cost | [16 empty] | 1293.16
|  |  | JDH3-02-008-L-38-(TSE)-Supply and install gate valves-100 mm |  | 2026-06-09 | 2026-06-13 | 2025-11-03 | 2025-11-06 | 0 | 0 | 1293.16 | Actual Total Cost
|  |  | JDH3-02-008-L-38-(TSE)-Supply and install gate valves-250 mm |  | 2026-06-09 | 2026-06-13 | 2025-10-02 | 2025-10-06 | 0 | 0 | 7698.34 | Planned Total Cost | [15 empty] | 7698.34
|  |  | JDH3-02-008-L-38-(TSE)-Supply and install gate valves-250 mm |  | 2026-06-09 | 2026-06-13 | 2025-10-02 | 2025-10-06 | 0 | 0 | 7698.34 | Remaining Total Cost | [15 empty] | 7698.34
|  |  | JDH3-02-008-L-38-(TSE)-Supply and install gate valves-250 mm |  | 2026-06-09 | 2026-06-13 | 2025-10-02 | 2025-10-06 | 0 | 0 | 7698.34 | Actual Total Cost
|  |  | Z05 |  | 2025-09-11 | 2025-11-19 | 01-Jul-25 A | 2026-05-03 | 2226-02-27 19:41 | 2226-02-27 19:26 | 2365244.76 | Planned Total Cost | [15 empty] | 299874.79 | 34516.71 |  |  | 180270.46 | 1524711.06 | 323583.44 | 2288.31
|  |  | Z05 |  | 2025-09-11 | 2025-11-19 | 01-Jul-25 A | 2026-05-03 | 2226-02-27 19:41 | 2226-02-27 19:26 | 2365244.76 | Remaining Total Cost | [15 empty] | 299874.79 | 34516.71 |  |  | 143787.26 | 1442065.44 | 323583.44 | 2288.31
|  |  | Z05 |  | 2025-09-11 | 2025-11-19 | 01-Jul-25 A | 2026-05-03 | 2226-02-27 19:41 | 2226-02-27 19:26 | 2365244.76 | Actual Total Cost | [14 empty] | 119128.81
|  |  | RCB |  | 2025-09-11 | 2025-11-19 | 2026-02-22 | 2026-05-03 | 0 | 0 | 1782481.41 | Planned Total Cost | [19 empty] | 121645.91 | 1334963.76 | 323583.44 | 2288.31
|  |  | RCB |  | 2025-09-11 | 2025-11-19 | 2026-02-22 | 2026-05-03 | 0 | 0 | 1782481.41 | Remaining Total Cost | [19 empty] | 121645.91 | 1334963.76 | 323583.44 | 2288.31
|  |  | RCB |  | 2025-09-11 | 2025-11-19 | 2026-02-22 | 2026-05-03 | 0 | 0 | 1782481.41 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z05-Storm Network - ST |  | 2025-09-11 | 2025-11-19 | 2026-02-22 | 2026-05-03 | 0 | 0 | 1782481.41 | Planned Total Cost | [19 empty] | 121645.91 | 1334963.76 | 323583.44 | 2288.31
|  |  | JDH3-02-008-RCB-Z05-Storm Network - ST |  | 2025-09-11 | 2025-11-19 | 2026-02-22 | 2026-05-03 | 0 | 0 | 1782481.41 | Remaining Total Cost | [19 empty] | 121645.91 | 1334963.76 | 323583.44 | 2288.31
|  |  | JDH3-02-008-RCB-Z05-Storm Network - ST |  | 2025-09-11 | 2025-11-19 | 2026-02-22 | 2026-05-03 | 0 | 0 | 1782481.41 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z05-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-09-11 | 2025-10-30 | 2026-02-22 | 2026-04-13 | 0 | 0 | 651674.49 | Planned Total Cost | [19 empty] | 121645.91 | 473550.13 | 56478.46
|  |  | JDH3-02-008-RCB-Z05-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-09-11 | 2025-10-30 | 2026-02-22 | 2026-04-13 | 0 | 0 | 651674.49 | Remaining Total Cost | [19 empty] | 121645.91 | 473550.13 | 56478.46
|  |  | JDH3-02-008-RCB-Z05-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-09-11 | 2025-10-30 | 2026-02-22 | 2026-04-13 | 0 | 0 | 651674.49 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z05-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-09-18 | 2025-10-27 | 2026-03-01 | 2026-04-09 | 0 | 0 | 328946.38 | Planned Total Cost | [20 empty] | 301899.68 | 27046.7
|  |  | JDH3-02-008-RCB-Z05-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-09-18 | 2025-10-27 | 2026-03-01 | 2026-04-09 | 0 | 0 | 328946.38 | Remaining Total Cost | [20 empty] | 301899.68 | 27046.7
|  |  | JDH3-02-008-RCB-Z05-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-09-18 | 2025-10-27 | 2026-03-01 | 2026-04-09 | 0 | 0 | 328946.38 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z05-(ST)- Single Catchbasine Works |  | 2025-09-25 | 2025-11-19 | 2026-03-08 | 2026-05-03 | 0 | 0 | 326900.99 | Planned Total Cost | [20 empty] | 222292.68 | 102320.01 | 2288.31
|  |  | JDH3-02-008-RCB-Z05-(ST)- Single Catchbasine Works |  | 2025-09-25 | 2025-11-19 | 2026-03-08 | 2026-05-03 | 0 | 0 | 326900.99 | Remaining Total Cost | [20 empty] | 222292.68 | 102320.01 | 2288.31
|  |  | JDH3-02-008-RCB-Z05-(ST)- Single Catchbasine Works |  | 2025-09-25 | 2025-11-19 | 2026-03-08 | 2026-05-03 | 0 | 0 | 326900.99 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z05-(ST)- Double Catchbasine Works |  | 2025-10-07 | 2025-11-03 | 2026-03-19 | 2026-04-16 | 0 | 0 | 474959.54 | Planned Total Cost | [20 empty] | 337221.27 | 137738.27
|  |  | JDH3-02-008-RCB-Z05-(ST)- Double Catchbasine Works |  | 2025-10-07 | 2025-11-03 | 2026-03-19 | 2026-04-16 | 0 | 0 | 474959.54 | Remaining Total Cost | [20 empty] | 337221.27 | 137738.27
|  |  | JDH3-02-008-RCB-Z05-(ST)- Double Catchbasine Works |  | 2025-10-07 | 2025-11-03 | 2026-03-19 | 2026-04-16 | 0 | 0 | 474959.54 | Actual Total Cost
|  |  | L-05 |  | 2025-09-11 | 2025-10-25 | 01-Jul-25 A | 2026-03-30 | 0 | 0 | 103548.9 | Planned Total Cost | [19 empty] | 19999.12 | 83549.78
|  |  | L-05 |  | 2025-09-11 | 2025-10-25 | 01-Jul-25 A | 2026-03-30 | 0 | 0 | 103548.9 | Remaining Total Cost | [19 empty] | 19999.12 | 83549.78
|  |  | L-05 |  | 2025-09-11 | 2025-10-25 | 01-Jul-25 A | 2026-03-30 | 0 | 0 | 103548.9 | Actual Total Cost
|  |  | JDH3-02-008-L-05-TSE Network - TSE |  | 2025-09-20 | 2025-10-25 | 2026-02-22 | 2026-03-30 | 0 | 0 | 103548.9 | Planned Total Cost | [19 empty] | 19999.12 | 83549.78
|  |  | JDH3-02-008-L-05-TSE Network - TSE |  | 2025-09-20 | 2025-10-25 | 2026-02-22 | 2026-03-30 | 0 | 0 | 103548.9 | Remaining Total Cost | [19 empty] | 19999.12 | 83549.78
|  |  | JDH3-02-008-L-05-TSE Network - TSE |  | 2025-09-20 | 2025-10-25 | 2026-02-22 | 2026-03-30 | 0 | 0 | 103548.9 | Actual Total Cost
|  |  | JDH3-02-008-L-05-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-20 | 2025-10-25 | 2026-02-22 | 2026-03-30 | 0 | 0 | 97083.1 | Planned Total Cost | [19 empty] | 19999.12 | 77083.98
|  |  | JDH3-02-008-L-05-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-20 | 2025-10-25 | 2026-02-22 | 2026-03-30 | 0 | 0 | 97083.1 | Remaining Total Cost | [19 empty] | 19999.12 | 77083.98
|  |  | JDH3-02-008-L-05-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-20 | 2025-10-25 | 2026-02-22 | 2026-03-30 | 0 | 0 | 97083.1 | Actual Total Cost
|  |  | JDH3-02-008-L-05-(TSE)-Supply and install gate valves-100 mm |  | 2025-10-12 | 2025-10-15 | 2026-03-16 | 2026-03-21 | 0 | 0 | 6465.8 | Planned Total Cost | [20 empty] | 6465.8
|  |  | JDH3-02-008-L-05-(TSE)-Supply and install gate valves-100 mm |  | 2025-10-12 | 2025-10-15 | 2026-03-16 | 2026-03-21 | 0 | 0 | 6465.8 | Remaining Total Cost | [20 empty] | 6465.8
|  |  | JDH3-02-008-L-05-(TSE)-Supply and install gate valves-100 mm |  | 2025-10-12 | 2025-10-15 | 2026-03-16 | 2026-03-21 | 0 | 0 | 6465.8 | Actual Total Cost
|  |  | L-06 |  | 2025-09-11 | 2025-10-25 | 19-Jul-25 A | 2025-11-06 | 0 | 0 | 103579.24 | Planned Total Cost | [15 empty] | 93867.9 | 9711.34
|  |  | L-06 |  | 2025-09-11 | 2025-10-25 | 19-Jul-25 A | 2025-11-06 | 0 | 0 | 103579.24 | Remaining Total Cost | [15 empty] | 93867.9 | 9711.34
|  |  | L-06 |  | 2025-09-11 | 2025-10-25 | 19-Jul-25 A | 2025-11-06 | 0 | 0 | 103579.24 | Actual Total Cost
|  |  | JDH3-02-008-L-06-TSE Network - TSE |  | 2025-09-20 | 2025-10-25 | 2025-10-02 | 2025-11-06 | 0 | 0 | 103579.24 | Planned Total Cost | [15 empty] | 93867.9 | 9711.34
|  |  | JDH3-02-008-L-06-TSE Network - TSE |  | 2025-09-20 | 2025-10-25 | 2025-10-02 | 2025-11-06 | 0 | 0 | 103579.24 | Remaining Total Cost | [15 empty] | 93867.9 | 9711.34
|  |  | JDH3-02-008-L-06-TSE Network - TSE |  | 2025-09-20 | 2025-10-25 | 2025-10-02 | 2025-11-06 | 0 | 0 | 103579.24 | Actual Total Cost
|  |  | JDH3-02-008-L-06-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-20 | 2025-10-25 | 2025-10-02 | 2025-11-06 | 0 | 0 | 97113.44 | Planned Total Cost | [15 empty] | 87402.09 | 9711.34
|  |  | JDH3-02-008-L-06-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-20 | 2025-10-25 | 2025-10-02 | 2025-11-06 | 0 | 0 | 97113.44 | Remaining Total Cost | [15 empty] | 87402.09 | 9711.34
|  |  | JDH3-02-008-L-06-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-20 | 2025-10-25 | 2025-10-02 | 2025-11-06 | 0 | 0 | 97113.44 | Actual Total Cost
|  |  | JDH3-02-008-L-06-(TSE)-Supply and install gate valves-100 mm |  | 2025-10-12 | 2025-10-15 | 2025-10-25 | 2025-10-28 | 0 | 0 | 6465.8 | Planned Total Cost | [15 empty] | 6465.8
|  |  | JDH3-02-008-L-06-(TSE)-Supply and install gate valves-100 mm |  | 2025-10-12 | 2025-10-15 | 2025-10-25 | 2025-10-28 | 0 | 0 | 6465.8 | Remaining Total Cost | [15 empty] | 6465.8
|  |  | JDH3-02-008-L-06-(TSE)-Supply and install gate valves-100 mm |  | 2025-10-12 | 2025-10-15 | 2025-10-25 | 2025-10-28 | 0 | 0 | 6465.8 | Actual Total Cost
|  |  | L-07 |  | 2025-09-11 | 2025-10-27 | 07-Jul-25 A | 2025-11-09 | 0 | 0 | 213334.83 | Planned Total Cost | [15 empty] | 188529.47 | 24805.36
|  |  | L-07 |  | 2025-09-11 | 2025-10-27 | 07-Jul-25 A | 2025-11-09 | 0 | 0 | 213334.83 | Remaining Total Cost | [15 empty] | 188529.47 | 24805.36
|  |  | L-07 |  | 2025-09-11 | 2025-10-27 | 07-Jul-25 A | 2025-11-09 | 0 | 0 | 213334.83 | Actual Total Cost
|  |  | JDH3-02-008-L-07-TSE Network - TSE |  | 2025-09-20 | 2025-10-27 | 2025-10-02 | 2025-11-09 | 0 | 0 | 213334.83 | Planned Total Cost | [15 empty] | 188529.47 | 24805.36
|  |  | JDH3-02-008-L-07-TSE Network - TSE |  | 2025-09-20 | 2025-10-27 | 2025-10-02 | 2025-11-09 | 0 | 0 | 213334.83 | Remaining Total Cost | [15 empty] | 188529.47 | 24805.36
|  |  | JDH3-02-008-L-07-TSE Network - TSE |  | 2025-09-20 | 2025-10-27 | 2025-10-02 | 2025-11-09 | 0 | 0 | 213334.83 | Actual Total Cost
|  |  | JDH3-02-008-L-07-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-20 | 2025-10-20 | 2025-10-02 | 2025-11-02 | 0 | 0 | 14000.86 | Planned Total Cost | [15 empty] | 12600.77 | 1400.09
|  |  | JDH3-02-008-L-07-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-20 | 2025-10-20 | 2025-10-02 | 2025-11-02 | 0 | 0 | 14000.86 | Remaining Total Cost | [15 empty] | 12600.77 | 1400.09
|  |  | JDH3-02-008-L-07-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-20 | 2025-10-20 | 2025-10-02 | 2025-11-02 | 0 | 0 | 14000.86 | Actual Total Cost
|  |  | JDH3-02-008-L-07-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-09-22 | 2025-10-27 | 2025-10-05 | 2025-11-09 | 0 | 0 | 175539.58 | Planned Total Cost | [15 empty] | 152134.31 | 23405.28
|  |  | JDH3-02-008-L-07-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-09-22 | 2025-10-27 | 2025-10-05 | 2025-11-09 | 0 | 0 | 175539.58 | Remaining Total Cost | [15 empty] | 152134.31 | 23405.28
|  |  | JDH3-02-008-L-07-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-09-22 | 2025-10-27 | 2025-10-05 | 2025-11-09 | 0 | 0 | 175539.58 | Actual Total Cost
|  |  | JDH3-02-008-L-07-(TSE)-Supply and install gate valves-100 mm |  | 2025-10-14 | 2025-10-18 | 2025-10-27 | 2025-10-30 | 0 | 0 | 5172.64 | Planned Total Cost | [15 empty] | 5172.64
|  |  | JDH3-02-008-L-07-(TSE)-Supply and install gate valves-100 mm |  | 2025-10-14 | 2025-10-18 | 2025-10-27 | 2025-10-30 | 0 | 0 | 5172.64 | Remaining Total Cost | [15 empty] | 5172.64
|  |  | JDH3-02-008-L-07-(TSE)-Supply and install gate valves-100 mm |  | 2025-10-14 | 2025-10-18 | 2025-10-27 | 2025-10-30 | 0 | 0 | 5172.64 | Actual Total Cost
|  |  | JDH3-02-008-L-07-(TSE)-Supply and install gate valves-250 mm |  | 2025-09-27 | 2025-09-30 | 2025-10-09 | 2025-10-13 | 0 | 0 | 7698.34 | Planned Total Cost | [15 empty] | 7698.34
|  |  | JDH3-02-008-L-07-(TSE)-Supply and install gate valves-250 mm |  | 2025-09-27 | 2025-09-30 | 2025-10-09 | 2025-10-13 | 0 | 0 | 7698.34 | Remaining Total Cost | [15 empty] | 7698.34
|  |  | JDH3-02-008-L-07-(TSE)-Supply and install gate valves-250 mm |  | 2025-09-27 | 2025-09-30 | 2025-10-09 | 2025-10-13 | 0 | 0 | 7698.34 | Actual Total Cost
|  |  | JDH3-02-008-L-07-(TSE)-Supply and install of Air valves-50 mm. |  | 2025-10-14 | 2025-10-18 | 2025-10-27 | 2025-10-30 | 0 | 0 | 7444.14 | Planned Total Cost | [15 empty] | 7444.14
|  |  | JDH3-02-008-L-07-(TSE)-Supply and install of Air valves-50 mm. |  | 2025-10-14 | 2025-10-18 | 2025-10-27 | 2025-10-30 | 0 | 0 | 7444.14 | Remaining Total Cost | [15 empty] | 7444.14
|  |  | JDH3-02-008-L-07-(TSE)-Supply and install of Air valves-50 mm. |  | 2025-10-14 | 2025-10-18 | 2025-10-27 | 2025-10-30 | 0 | 0 | 7444.14 | Actual Total Cost
|  |  | JDH3-02-008-L-07-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2025-09-28 | 2025-10-06 | 2025-10-11 | 2025-10-19 | 0 | 0 | 3479.28 | Planned Total Cost | [15 empty] | 3479.28
|  |  | JDH3-02-008-L-07-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2025-09-28 | 2025-10-06 | 2025-10-11 | 2025-10-19 | 0 | 0 | 3479.28 | Remaining Total Cost | [15 empty] | 3479.28
|  |  | JDH3-02-008-L-07-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2025-09-28 | 2025-10-06 | 2025-10-11 | 2025-10-19 | 0 | 0 | 3479.28 | Actual Total Cost
|  |  | L-04 |  | 2025-09-11 | 2025-10-20 | 08-Jul-25 A | 2026-03-11 | 2226-02-27 19:41 | 2226-02-27 19:26 | 162300.37 | Planned Total Cost | [15 empty] | 17477.42 |  |  |  | 38625.44 | 106197.51
|  |  | L-04 |  | 2025-09-11 | 2025-10-20 | 08-Jul-25 A | 2026-03-11 | 2226-02-27 19:41 | 2226-02-27 19:26 | 162300.37 | Remaining Total Cost | [15 empty] | 17477.42 |  |  |  | 2142.24 | 23551.9
|  |  | L-04 |  | 2025-09-11 | 2025-10-20 | 08-Jul-25 A | 2026-03-11 | 2226-02-27 19:41 | 2226-02-27 19:26 | 162300.37 | Actual Total Cost | [14 empty] | 119128.81
|  |  | JDH3-02-008-L-04-TSE Network - TSE |  | 2025-09-20 | 2025-10-20 | 02-Sep-25 A | 2026-03-11 | 2226-02-27 19:41 | 2226-02-27 19:26 | 162300.37 | Planned Total Cost | [15 empty] | 17477.42 |  |  |  | 38625.44 | 106197.51
|  |  | JDH3-02-008-L-04-TSE Network - TSE |  | 2025-09-20 | 2025-10-20 | 02-Sep-25 A | 2026-03-11 | 2226-02-27 19:41 | 2226-02-27 19:26 | 162300.37 | Remaining Total Cost | [15 empty] | 17477.42 |  |  |  | 2142.24 | 23551.9
|  |  | JDH3-02-008-L-04-TSE Network - TSE |  | 2025-09-20 | 2025-10-20 | 02-Sep-25 A | 2026-03-11 | 2226-02-27 19:41 | 2226-02-27 19:26 | 162300.37 | Actual Total Cost | [14 empty] | 119128.81
|  |  | JDH3-02-008-L-04-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-20 | 2025-10-15 | 2026-02-22 | 2026-03-08 | 0 | 0 | 3104.69 | Planned Total Cost | [19 empty] | 2142.24 | 962.45
|  |  | JDH3-02-008-L-04-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-20 | 2025-10-15 | 2026-02-22 | 2026-03-08 | 0 | 0 | 3104.69 | Remaining Total Cost | [19 empty] | 2142.24 | 962.45
|  |  | JDH3-02-008-L-04-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-20 | 2025-10-15 | 2026-02-22 | 2026-03-08 | 0 | 0 | 3104.69 | Actual Total Cost
|  |  | JDH3-02-008-L-04-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-09-22 | 2025-10-20 | 02-Sep-25 A | 2026-03-11 | 2226-02-27 19:41 | 2226-02-27 19:26 | 148911.02 | Planned Total Cost | [15 empty] | 14891.1 |  |  |  | 36483.2 | 97536.72
|  |  | JDH3-02-008-L-04-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-09-22 | 2025-10-20 | 02-Sep-25 A | 2026-03-11 | 2226-02-27 19:41 | 2226-02-27 19:26 | 148911.02 | Remaining Total Cost | [15 empty] | 14891.1 |  |  |  |  | 14891.1
|  |  | JDH3-02-008-L-04-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-09-22 | 2025-10-20 | 02-Sep-25 A | 2026-03-11 | 2226-02-27 19:41 | 2226-02-27 19:26 | 148911.02 | Actual Total Cost | [14 empty] | 119128.81
|  |  | JDH3-02-008-L-04-(TSE)-Supply and install gate valves-100 mm |  | 2025-10-09 | 2025-10-13 | 2025-10-02 | 2025-10-06 | 0 | 0 | 2586.32 | Planned Total Cost | [15 empty] | 2586.32
|  |  | JDH3-02-008-L-04-(TSE)-Supply and install gate valves-100 mm |  | 2025-10-09 | 2025-10-13 | 2025-10-02 | 2025-10-06 | 0 | 0 | 2586.32 | Remaining Total Cost | [15 empty] | 2586.32
|  |  | JDH3-02-008-L-04-(TSE)-Supply and install gate valves-100 mm |  | 2025-10-09 | 2025-10-13 | 2025-10-02 | 2025-10-06 | 0 | 0 | 2586.32 | Actual Total Cost
|  |  | JDH3-02-008-L-04-(TSE)-Supply and install gate valves-250 mm |  | 2025-09-27 | 2025-09-30 | 2026-03-01 | 2026-03-05 | 0 | 0 | 7698.34 | Planned Total Cost | [20 empty] | 7698.34
|  |  | JDH3-02-008-L-04-(TSE)-Supply and install gate valves-250 mm |  | 2025-09-27 | 2025-09-30 | 2026-03-01 | 2026-03-05 | 0 | 0 | 7698.34 | Remaining Total Cost | [20 empty] | 7698.34
|  |  | JDH3-02-008-L-04-(TSE)-Supply and install gate valves-250 mm |  | 2025-09-27 | 2025-09-30 | 2026-03-01 | 2026-03-05 | 0 | 0 | 7698.34 | Actual Total Cost
|  |  | Z06 |  | 2025-08-02 | 2026-04-14 | 03-Nov-24 A | 2026-06-24 | 7470193.65 | 7470193.65 | 15580161.78 | Planned Total Cost | [13 empty] | 1859441.47 | 2724869.56 | 4372513.2 | 1716533.65 | 647947.52 | 691742.27 | 1166320.92 | 1883369.85 | 439941.37 | 77481.96
|  |  | Z06 |  | 2025-08-02 | 2026-04-14 | 03-Nov-24 A | 2026-06-24 | 7470193.65 | 7470193.65 | 15580161.78 | Remaining Total Cost | [15 empty] | 3422734.83 | 687939.8 | 278251.42 | 662843.9 | 565829.74 | 1974945.09 | 439941.37 | 77481.96
|  |  | Z06 |  | 2025-08-02 | 2026-04-14 | 03-Nov-24 A | 2026-06-24 | 7470193.65 | 7470193.65 | 15580161.78 | Actual Total Cost |  |  |  |  | 7626.48 | 52698.87 | 122025.31 | 283886.97 | 606568.81 | 655296.84 | 459718.59 | 1078395.02 | 965073.98 | 1397092.4 | 1778309.85 | 63500.52
|  |  | L-53 |  | 2025-08-02 | 2025-10-25 | 12-Jun-25 A | 2026-02-23 | 915335.07 | 915335.09 | 1923290.65 | Planned Total Cost | [13 empty] | 941082.88 | 49118.04 | 391605.04 |  | 65412.58 | 392093.42 | 83978.69
|  |  | L-53 |  | 2025-08-02 | 2025-10-25 | 12-Jun-25 A | 2026-02-23 | 915335.07 | 915335.09 | 1923290.65 | Remaining Total Cost | [15 empty] | 466470.88 |  | 65412.58 | 392093.42 | 83978.69
|  |  | L-53 |  | 2025-08-02 | 2025-10-25 | 12-Jun-25 A | 2026-02-23 | 915335.07 | 915335.09 | 1923290.65 | Actual Total Cost | [11 empty] | 298768.1 | 217757.22 | 243756.81 | 153661.9 | 1391.06
|  |  | JDH3-02-008-L-53-Storm Network - ST |  | 2025-08-10 | 2025-09-11 | 12-Jun-25 A | 2026-01-22 | 915335.07 | 915335.09 | 1756877.38 | Planned Total Cost | [13 empty] | 941082.88 | 49118.04 | 391605.04 |  | 53425.07 | 321646.34
|  |  | JDH3-02-008-L-53-Storm Network - ST |  | 2025-08-10 | 2025-09-11 | 12-Jun-25 A | 2026-01-22 | 915335.07 | 915335.09 | 1756877.38 | Remaining Total Cost | [15 empty] | 466470.88 |  | 53425.07 | 321646.34
|  |  | JDH3-02-008-L-53-Storm Network - ST |  | 2025-08-10 | 2025-09-11 | 12-Jun-25 A | 2026-01-22 | 915335.07 | 915335.09 | 1756877.38 | Actual Total Cost | [11 empty] | 298768.1 | 217757.22 | 243756.81 | 153661.9 | 1391.06
|  |  | JDH3-02-008-L-53-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-08-10 | 2025-09-08 | 2025-12-28 | 2026-01-21 | 0 | 0 | 262316.24 | Planned Total Cost | [17 empty] | 53425.07 | 208891.17
|  |  | JDH3-02-008-L-53-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-08-10 | 2025-09-08 | 2025-12-28 | 2026-01-21 | 0 | 0 | 262316.24 | Remaining Total Cost | [17 empty] | 53425.07 | 208891.17
|  |  | JDH3-02-008-L-53-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-08-10 | 2025-09-08 | 2025-12-28 | 2026-01-21 | 0 | 0 | 262316.24 | Actual Total Cost
|  |  | JDH3-02-008-L-53-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-08-13 | 2025-09-04 | 15-Aug-25 A | 26-Aug-25 A | 1945-09-29 02:53 | 1945-09-29 02:53 | 16709.12 | Planned Total Cost | [13 empty] | 15038.21 | 1670.91
|  |  | JDH3-02-008-L-53-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-08-13 | 2025-09-04 | 15-Aug-25 A | 26-Aug-25 A | 1945-09-29 02:53 | 1945-09-29 02:53 | 16709.12 | Remaining Total Cost
|  |  | JDH3-02-008-L-53-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-08-13 | 2025-09-04 | 15-Aug-25 A | 26-Aug-25 A | 1945-09-29 02:53 | 1945-09-29 02:53 | 16709.12 | Actual Total Cost | [13 empty] | 16709.12
|  |  | JDH3-02-008-L-53-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-08-16 | 2025-09-04 | 20-Aug-25 A | 2026-01-18 | 1941-05-16 02:53 | 1941-05-16 02:53 | 66467.79 | Planned Total Cost | [13 empty] | 53174.23 |  | 6646.78 |  |  | 6646.78
|  |  | JDH3-02-008-L-53-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-08-16 | 2025-09-04 | 20-Aug-25 A | 2026-01-18 | 1941-05-16 02:53 | 1941-05-16 02:53 | 66467.79 | Remaining Total Cost | [15 empty] | 44708.89 |  |  | 6646.78
|  |  | JDH3-02-008-L-53-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-08-16 | 2025-09-04 | 20-Aug-25 A | 2026-01-18 | 1941-05-16 02:53 | 1941-05-16 02:53 | 66467.79 | Actual Total Cost | [13 empty] | 3125.99 | 11542.2 | 443.93
|  |  | JDH3-02-008-L-53-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-08-10 | 2025-09-04 | 12-Jun-25 A | 2026-01-18 | 2180-11-30 04:05 | 2180-11-30 04:05 | 114004.64 | Planned Total Cost | [13 empty] | 102604.17 |  |  |  |  | 11400.46
|  |  | JDH3-02-008-L-53-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-08-10 | 2025-09-04 | 12-Jun-25 A | 2026-01-18 | 2180-11-30 04:05 | 2180-11-30 04:05 | 114004.64 | Remaining Total Cost | [18 empty] | 11400.46
|  |  | JDH3-02-008-L-53-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-08-10 | 2025-09-04 | 12-Jun-25 A | 2026-01-18 | 2180-11-30 04:05 | 2180-11-30 04:05 | 114004.64 | Actual Total Cost | [11 empty] | 70540.37 | 20663.34 | 11400.46
|  |  | JDH3-02-008-L-53-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-08-10 | 2025-09-07 | 12-Jun-25 A | 2026-01-20 | 203673.06 | 203673.06 | 239632.28 | Planned Total Cost | [13 empty] | 215669.05 |  |  |  |  | 23963.23
|  |  | JDH3-02-008-L-53-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-08-10 | 2025-09-07 | 12-Jun-25 A | 2026-01-20 | 203673.06 | 203673.06 | 239632.28 | Remaining Total Cost | [15 empty] | 11995.99 |  |  | 23963.23
|  |  | JDH3-02-008-L-53-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-08-10 | 2025-09-07 | 12-Jun-25 A | 2026-01-20 | 203673.06 | 203673.06 | 239632.28 | Actual Total Cost | [11 empty] | 62834.09 |  | 62058.96 | 78456.57 | 323.44
|  |  | JDH3-02-008-L-53-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2025-08-10 | 2025-09-09 | 12-Jun-25 A | 2026-01-22 | 363945.52 | 363945.52 | 419998.52 | Planned Total Cost | [13 empty] | 377998.67 |  |  |  |  | 41999.85
|  |  | JDH3-02-008-L-53-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2025-08-10 | 2025-09-09 | 12-Jun-25 A | 2026-01-22 | 363945.52 | 363945.52 | 419998.52 | Remaining Total Cost | [15 empty] | 14053.15 |  |  | 41999.85
|  |  | JDH3-02-008-L-53-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2025-08-10 | 2025-09-09 | 12-Jun-25 A | 2026-01-22 | 363945.52 | 363945.52 | 419998.52 | Actual Total Cost | [11 empty] | 96697.25 | 173679.84 | 85276.55 | 7984.77 | 307.11
|  |  | JDH3-02-008-L-53-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2025-08-18 | 2025-09-04 | 20-Aug-25 A | 2026-01-18 | 2073-03-14 19:55 | 2073-03-14 20:10 | 79078.54 | Planned Total Cost | [13 empty] | 15815.71 | 47447.12 | 7907.85 |  |  | 7907.85
|  |  | JDH3-02-008-L-53-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2025-08-18 | 2025-09-04 | 20-Aug-25 A | 2026-01-18 | 2073-03-14 19:55 | 2073-03-14 20:10 | 79078.54 | Remaining Total Cost | [15 empty] | 7907.85 |  |  | 7907.85
|  |  | JDH3-02-008-L-53-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2025-08-18 | 2025-09-04 | 20-Aug-25 A | 2026-01-18 | 2073-03-14 19:55 | 2073-03-14 20:10 | 79078.54 | Actual Total Cost | [13 empty] | 15815.71 | 47447.13
|  |  | JDH3-02-008-L-53-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-08-20 | 2025-08-31 | 22-Aug-25 A | 2025-10-06 | 1977-05-16 05:17 | 1977-05-16 05:31 | 35326.53 | Planned Total Cost | [13 empty] | 28261.22 |  | 7065.31
|  |  | JDH3-02-008-L-53-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-08-20 | 2025-08-31 | 22-Aug-25 A | 2025-10-06 | 1977-05-16 05:17 | 1977-05-16 05:31 | 35326.53 | Remaining Total Cost | [15 empty] | 7065.31
|  |  | JDH3-02-008-L-53-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-08-20 | 2025-08-31 | 22-Aug-25 A | 2025-10-06 | 1977-05-16 05:17 | 1977-05-16 05:31 | 35326.53 | Actual Total Cost | [13 empty] | 28261.23
|  |  | JDH3-02-008-L-53-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-08-23 | 2025-09-02 | 18-Aug-25 A | 2025-10-08 | 1914-04-10 08:24 | 1914-04-10 08:10 | 10428.7 | Planned Total Cost | [13 empty] | 5214.35 |  | 5214.35
|  |  | JDH3-02-008-L-53-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-08-23 | 2025-09-02 | 18-Aug-25 A | 2025-10-08 | 1914-04-10 08:24 | 1914-04-10 08:10 | 10428.7 | Remaining Total Cost | [15 empty] | 5214.35
|  |  | JDH3-02-008-L-53-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-08-23 | 2025-09-02 | 18-Aug-25 A | 2025-10-08 | 1914-04-10 08:24 | 1914-04-10 08:10 | 10428.7 | Actual Total Cost | [13 empty] | 5214.34
|  |  | JDH3-02-008-L-53-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-08-25 | 2025-09-04 | 20-Aug-25 A | 2025-10-08 | 1937-06-21 15:50 | 1937-06-21 15:50 | 27375.33 | Planned Total Cost | [13 empty] | 13687.66 |  | 13687.66
|  |  | JDH3-02-008-L-53-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-08-25 | 2025-09-04 | 20-Aug-25 A | 2025-10-08 | 1937-06-21 15:50 | 1937-06-21 15:50 | 27375.33 | Remaining Total Cost | [15 empty] | 13687.66
|  |  | JDH3-02-008-L-53-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-08-25 | 2025-09-04 | 20-Aug-25 A | 2025-10-08 | 1937-06-21 15:50 | 1937-06-21 15:50 | 27375.33 | Actual Total Cost | [13 empty] | 13687.66
|  |  | JDH3-02-008-L-53-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-08-10 | 2025-09-07 | 12-Jun-25 A | 2025-10-11 | 2152-03-08 10:05 | 2152-03-08 10:19 | 169466.32 | Planned Total Cost | [13 empty] | 92110.42 |  | 77355.89
|  |  | JDH3-02-008-L-53-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-08-10 | 2025-09-07 | 12-Jun-25 A | 2025-10-11 | 2152-03-08 10:05 | 2152-03-08 10:19 | 169466.32 | Remaining Total Cost | [15 empty] | 77355.89
|  |  | JDH3-02-008-L-53-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-08-10 | 2025-09-07 | 12-Jun-25 A | 2025-10-11 | 2152-03-08 10:05 | 2152-03-08 10:19 | 169466.32 | Actual Total Cost | [11 empty] | 68696.39 | 23414.04
|  |  | JDH3-02-008-L-53-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-08-27 | 2025-09-09 | 22-Aug-25 A | 2025-10-13 | 1929-06-10 14:10 | 1929-06-10 14:24 | 43018.37 | Planned Total Cost | [13 empty] | 21509.18 |  | 21509.18
|  |  | JDH3-02-008-L-53-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-08-27 | 2025-09-09 | 22-Aug-25 A | 2025-10-13 | 1929-06-10 14:10 | 1929-06-10 14:24 | 43018.37 | Remaining Total Cost | [15 empty] | 32263.77
|  |  | JDH3-02-008-L-53-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-08-27 | 2025-09-09 | 22-Aug-25 A | 2025-10-13 | 1929-06-10 14:10 | 1929-06-10 14:24 | 43018.37 | Actual Total Cost | [13 empty] | 2206.79 | 8231.23 | 316.59
|  |  | JDH3-02-008-L-53-(ST)- Single Catchbasine Works |  | 2025-08-30 | 2025-09-09 | 2025-10-04 | 2025-10-14 | 0 | 0 | 70393.74 | Planned Total Cost | [15 empty] | 70393.74
|  |  | JDH3-02-008-L-53-(ST)- Single Catchbasine Works |  | 2025-08-30 | 2025-09-09 | 2025-10-04 | 2025-10-14 | 0 | 0 | 70393.74 | Remaining Total Cost | [15 empty] | 70393.74
|  |  | JDH3-02-008-L-53-(ST)- Single Catchbasine Works |  | 2025-08-30 | 2025-09-09 | 2025-10-04 | 2025-10-14 | 0 | 0 | 70393.74 | Actual Total Cost
|  |  | JDH3-02-008-L-53-(ST)- Double Catchbasine Works |  | 2025-09-01 | 2025-09-11 | 2025-10-06 | 2025-10-16 | 0 | 0 | 181824.28 | Planned Total Cost | [15 empty] | 181824.28
|  |  | JDH3-02-008-L-53-(ST)- Double Catchbasine Works |  | 2025-09-01 | 2025-09-11 | 2025-10-06 | 2025-10-16 | 0 | 0 | 181824.28 | Remaining Total Cost | [15 empty] | 181824.28
|  |  | JDH3-02-008-L-53-(ST)- Double Catchbasine Works |  | 2025-09-01 | 2025-09-11 | 2025-10-06 | 2025-10-16 | 0 | 0 | 181824.28 | Actual Total Cost
|  |  | JDH3-02-008-L-53-(ST)-PIPES ENCASEMENT |  | 2025-08-27 | 2025-09-02 | 2026-01-08 | 2026-01-15 | 0 | 0 | 20837 | Planned Total Cost | [18 empty] | 20837
|  |  | JDH3-02-008-L-53-(ST)-PIPES ENCASEMENT |  | 2025-08-27 | 2025-09-02 | 2026-01-08 | 2026-01-15 | 0 | 0 | 20837 | Remaining Total Cost | [18 empty] | 20837
|  |  | JDH3-02-008-L-53-(ST)-PIPES ENCASEMENT |  | 2025-08-27 | 2025-09-02 | 2026-01-08 | 2026-01-15 | 0 | 0 | 20837 | Actual Total Cost
|  |  | JDH3-02-008-L-53-TSE Network - TSE |  | 2025-09-13 | 2025-10-13 | 2025-12-28 | 2026-02-11 | 0 | 0 | 95643.13 | Planned Total Cost | [17 empty] | 11987.5 | 70447.08 | 13208.55
|  |  | JDH3-02-008-L-53-TSE Network - TSE |  | 2025-09-13 | 2025-10-13 | 2025-12-28 | 2026-02-11 | 0 | 0 | 95643.13 | Remaining Total Cost | [17 empty] | 11987.5 | 70447.08 | 13208.55
|  |  | JDH3-02-008-L-53-TSE Network - TSE |  | 2025-09-13 | 2025-10-13 | 2025-12-28 | 2026-02-11 | 0 | 0 | 95643.13 | Actual Total Cost
|  |  | JDH3-02-008-L-53-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-13 | 2025-10-11 | 2025-12-28 | 2026-02-09 | 0 | 0 | 74456.55 | Planned Total Cost | [17 empty] | 11987.5 | 55023.39 | 7445.66
|  |  | JDH3-02-008-L-53-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-13 | 2025-10-11 | 2025-12-28 | 2026-02-09 | 0 | 0 | 74456.55 | Remaining Total Cost | [17 empty] | 11987.5 | 55023.39 | 7445.66
|  |  | JDH3-02-008-L-53-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-13 | 2025-10-11 | 2025-12-28 | 2026-02-09 | 0 | 0 | 74456.55 | Actual Total Cost
|  |  | JDH3-02-008-L-53-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-09-17 | 2025-10-13 | 2026-01-22 | 2026-02-11 | 0 | 0 | 12154.66 | Planned Total Cost | [18 empty] | 10465.16 | 1689.5
|  |  | JDH3-02-008-L-53-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-09-17 | 2025-10-13 | 2026-01-22 | 2026-02-11 | 0 | 0 | 12154.66 | Remaining Total Cost | [18 empty] | 10465.16 | 1689.5
|  |  | JDH3-02-008-L-53-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-09-17 | 2025-10-13 | 2026-01-22 | 2026-02-11 | 0 | 0 | 12154.66 | Actual Total Cost
|  |  | JDH3-02-008-L-53-(TSE)-Supply and install gate valves-100 mm |  | 2025-09-30 | 2025-10-04 | 2026-01-29 | 2026-02-03 | 0 | 0 | 6465.8 | Planned Total Cost | [18 empty] | 3549.73 | 2916.08
|  |  | JDH3-02-008-L-53-(TSE)-Supply and install gate valves-100 mm |  | 2025-09-30 | 2025-10-04 | 2026-01-29 | 2026-02-03 | 0 | 0 | 6465.8 | Remaining Total Cost | [18 empty] | 3549.73 | 2916.08
|  |  | JDH3-02-008-L-53-(TSE)-Supply and install gate valves-100 mm |  | 2025-09-30 | 2025-10-04 | 2026-01-29 | 2026-02-03 | 0 | 0 | 6465.8 | Actual Total Cost
|  |  | JDH3-02-008-L-53-(TSE)-Supply and install gate valves-250 mm |  | 2025-09-30 | 2025-10-04 | 2026-01-29 | 2026-02-03 | 0 | 0 | 2566.11 | Planned Total Cost | [18 empty] | 1408.8 | 1157.32
|  |  | JDH3-02-008-L-53-(TSE)-Supply and install gate valves-250 mm |  | 2025-09-30 | 2025-10-04 | 2026-01-29 | 2026-02-03 | 0 | 0 | 2566.11 | Remaining Total Cost | [18 empty] | 1408.8 | 1157.32
|  |  | JDH3-02-008-L-53-(TSE)-Supply and install gate valves-250 mm |  | 2025-09-30 | 2025-10-04 | 2026-01-29 | 2026-02-03 | 0 | 0 | 2566.11 | Actual Total Cost
|  |  | JDH3-02-008-L-53-Potable Water Network - WT |  | 2025-10-14 | 2025-10-25 | 2026-02-11 | 2026-02-23 | 0 | 0 | 70770.15 | Planned Total Cost | [19 empty] | 70770.15
|  |  | JDH3-02-008-L-53-Potable Water Network - WT |  | 2025-10-14 | 2025-10-25 | 2026-02-11 | 2026-02-23 | 0 | 0 | 70770.15 | Remaining Total Cost | [19 empty] | 70770.15
|  |  | JDH3-02-008-L-53-Potable Water Network - WT |  | 2025-10-14 | 2025-10-25 | 2026-02-11 | 2026-02-23 | 0 | 0 | 70770.15 | Actual Total Cost
|  |  | JDH3-02-008-L-53-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-10-14 | 2025-10-25 | 2026-02-11 | 2026-02-23 | 0 | 0 | 7291.33 | Planned Total Cost | [19 empty] | 7291.33
|  |  | JDH3-02-008-L-53-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-10-14 | 2025-10-25 | 2026-02-11 | 2026-02-23 | 0 | 0 | 7291.33 | Remaining Total Cost | [19 empty] | 7291.33
|  |  | JDH3-02-008-L-53-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-10-14 | 2025-10-25 | 2026-02-11 | 2026-02-23 | 0 | 0 | 7291.33 | Actual Total Cost
|  |  | JDH3-02-008-L-53-(WT)- Supply and install 3-out fire hydrant |  | 2025-10-16 | 2025-10-22 | 2026-02-14 | 2026-02-21 | 0 | 0 | 63478.82 | Planned Total Cost | [19 empty] | 63478.82
|  |  | JDH3-02-008-L-53-(WT)- Supply and install 3-out fire hydrant |  | 2025-10-16 | 2025-10-22 | 2026-02-14 | 2026-02-21 | 0 | 0 | 63478.82 | Remaining Total Cost | [19 empty] | 63478.82
|  |  | JDH3-02-008-L-53-(WT)- Supply and install 3-out fire hydrant |  | 2025-10-16 | 2025-10-22 | 2026-02-14 | 2026-02-21 | 0 | 0 | 63478.82 | Actual Total Cost
|  |  | L-54 |  | 2025-08-10 | 2025-11-10 | 01-Apr-25 A | 2026-03-10 | 917536.38 | 917536.36 | 1869213.6 | Planned Total Cost | [13 empty] | 577805.57 | 403181.66 | 415466.04 |  | 53578.8 | 265668.65 | 91262.97 | 62249.91
|  |  | L-54 |  | 2025-08-10 | 2025-11-10 | 01-Apr-25 A | 2026-03-10 | 917536.38 | 917536.36 | 1869213.6 | Remaining Total Cost | [15 empty] | 478916.89 |  | 53578.8 | 265668.65 | 91262.97 | 62249.91
|  |  | L-54 |  | 2025-08-10 | 2025-11-10 | 01-Apr-25 A | 2026-03-10 | 917536.38 | 917536.36 | 1869213.6 | Actual Total Cost | [9 empty] | 28607.83 | 50861.91 | 181430.44 | 285883.06 | 352139.54 | 18496.4 | 117.18
|  |  | JDH3-02-008-L-54-Storm Network - ST |  | 2025-08-18 | 2025-09-23 | 20-Apr-25 A | 2026-01-21 | 917536.38 | 917536.36 | 1687710.84 | Planned Total Cost | [13 empty] | 577805.57 | 403181.66 | 415466.04 |  | 53578.8 | 237678.77
|  |  | JDH3-02-008-L-54-Storm Network - ST |  | 2025-08-18 | 2025-09-23 | 20-Apr-25 A | 2026-01-21 | 917536.38 | 917536.36 | 1687710.84 | Remaining Total Cost | [15 empty] | 478916.89 |  | 53578.8 | 237678.77
|  |  | JDH3-02-008-L-54-Storm Network - ST |  | 2025-08-18 | 2025-09-23 | 20-Apr-25 A | 2026-01-21 | 917536.38 | 917536.36 | 1687710.84 | Actual Total Cost | [9 empty] | 28607.83 | 50861.91 | 181430.44 | 285883.06 | 352139.54 | 18496.4 | 117.18
|  |  | JDH3-02-008-L-54-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-08-18 | 2025-09-23 | 2025-12-28 | 2026-01-21 | 0 | 0 | 263071.02 | Planned Total Cost | [17 empty] | 53578.8 | 209492.22
|  |  | JDH3-02-008-L-54-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-08-18 | 2025-09-23 | 2025-12-28 | 2026-01-21 | 0 | 0 | 263071.02 | Remaining Total Cost | [17 empty] | 53578.8 | 209492.22
|  |  | JDH3-02-008-L-54-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-08-18 | 2025-09-23 | 2025-12-28 | 2026-01-21 | 0 | 0 | 263071.02 | Actual Total Cost
|  |  | JDH3-02-008-L-54-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-08-21 | 2025-09-01 | 02-Aug-25 A | 2025-10-04 | 7294.04 | 1919-12-20 00:58 | 8104.48 | Planned Total Cost | [13 empty] | 6483.59 | 810.45 | 810.45
|  |  | JDH3-02-008-L-54-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-08-21 | 2025-09-01 | 02-Aug-25 A | 2025-10-04 | 7294.04 | 1919-12-20 00:58 | 8104.48 | Remaining Total Cost | [15 empty] | 810.45
|  |  | JDH3-02-008-L-54-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-08-21 | 2025-09-01 | 02-Aug-25 A | 2025-10-04 | 7294.04 | 1919-12-20 00:58 | 8104.48 | Actual Total Cost | [13 empty] | 6483.59 | 810.45
|  |  | JDH3-02-008-L-54-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-08-24 | 2025-09-08 | 16-Aug-25 A | 2026-01-18 | 1907-05-18 01:55 | 1907-05-18 01:55 | 73495.48 | Planned Total Cost | [13 empty] | 58796.38 | 7349.55 |  |  |  | 7349.55
|  |  | JDH3-02-008-L-54-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-08-24 | 2025-09-08 | 16-Aug-25 A | 2026-01-18 | 1907-05-18 01:55 | 1907-05-18 01:55 | 73495.48 | Remaining Total Cost | [15 empty] | 63450.85 |  |  | 7349.55
|  |  | JDH3-02-008-L-54-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-08-24 | 2025-09-08 | 16-Aug-25 A | 2026-01-18 | 1907-05-18 01:55 | 1907-05-18 01:55 | 73495.48 | Actual Total Cost | [14 empty] | 2577.9 | 117.18
|  |  | JDH3-02-008-L-54-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-08-18 | 2025-09-06 | 20-Apr-25 A | 2025-10-04 | 2191-11-28 19:55 | 2191-11-28 19:55 | 112209.6 | Planned Total Cost | [13 empty] | 85659.27 | 20960.57 | 5589.77
|  |  | JDH3-02-008-L-54-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-08-18 | 2025-09-06 | 20-Apr-25 A | 2025-10-04 | 2191-11-28 19:55 | 2191-11-28 19:55 | 112209.6 | Remaining Total Cost | [15 empty] | 5589.77
|  |  | JDH3-02-008-L-54-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-08-18 | 2025-09-06 | 20-Apr-25 A | 2025-10-04 | 2191-11-28 19:55 | 2191-11-28 19:55 | 112209.6 | Actual Total Cost | [9 empty] | 24118.86 | 20948.52 |  | 11260.72 | 44700.3 | 5591.43
|  |  | JDH3-02-008-L-54-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-08-20 | 2025-09-09 | 21-Apr-25 A | 2025-10-04 | 221598.92 | 221598.91 | 239576.48 | Planned Total Cost | [13 empty] | 90300.01 | 131298.9 | 17977.56
|  |  | JDH3-02-008-L-54-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-08-20 | 2025-09-09 | 21-Apr-25 A | 2025-10-04 | 221598.92 | 221598.91 | 239576.48 | Remaining Total Cost | [15 empty] | 17977.56
|  |  | JDH3-02-008-L-54-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-08-20 | 2025-09-09 | 21-Apr-25 A | 2025-10-04 | 221598.92 | 221598.91 | 239576.48 | Actual Total Cost | [9 empty] | 4488.97 | 27204.38 | 18228.57 | 9905.65 | 152254.73 | 9516.62
|  |  | JDH3-02-008-L-54-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2025-08-18 | 2025-09-15 | 09-Jun-25 A | 2025-10-04 | 385323.37 | 385323.35 | 412788.07 | Planned Total Cost | [13 empty] | 255526.66 | 129796.7 | 27464.71
|  |  | JDH3-02-008-L-54-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2025-08-18 | 2025-09-15 | 09-Jun-25 A | 2025-10-04 | 385323.37 | 385323.35 | 412788.07 | Remaining Total Cost | [15 empty] | 27464.71
|  |  | JDH3-02-008-L-54-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2025-08-18 | 2025-09-15 | 09-Jun-25 A | 2025-10-04 | 385323.37 | 385323.35 | 412788.07 | Actual Total Cost | [11 empty] | 138829.55 | 196213.7 | 50280.1
|  |  | JDH3-02-008-L-54-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 2.51 to 3.50 m |  | 2025-09-02 | 2025-09-17 | 25-Jun-25 A | 2025-10-06 | 2111-03-03 19:41 | 2111-03-03 19:41 | 81193.71 | Planned Total Cost | [14 empty] | 77129.82 | 4063.9
|  |  | JDH3-02-008-L-54-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 2.51 to 3.50 m |  | 2025-09-02 | 2025-09-17 | 25-Jun-25 A | 2025-10-06 | 2111-03-03 19:41 | 2111-03-03 19:41 | 81193.71 | Remaining Total Cost | [15 empty] | 4063.9
|  |  | JDH3-02-008-L-54-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 2.51 to 3.50 m |  | 2025-09-02 | 2025-09-17 | 25-Jun-25 A | 2025-10-06 | 2111-03-03 19:41 | 2111-03-03 19:41 | 81193.71 | Actual Total Cost | [11 empty] | 8626.83 | 68502.99
|  |  | JDH3-02-008-L-54-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-08-26 | 2025-09-06 | 22-Aug-25 A | 2025-10-08 | 1914-04-10 08:24 | 1914-04-10 08:10 | 10428.7 | Planned Total Cost | [13 empty] | 5214.35 |  | 5214.35
|  |  | JDH3-02-008-L-54-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-08-26 | 2025-09-06 | 22-Aug-25 A | 2025-10-08 | 1914-04-10 08:24 | 1914-04-10 08:10 | 10428.7 | Remaining Total Cost | [15 empty] | 5214.35
|  |  | JDH3-02-008-L-54-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-08-26 | 2025-09-06 | 22-Aug-25 A | 2025-10-08 | 1914-04-10 08:24 | 1914-04-10 08:10 | 10428.7 | Actual Total Cost | [13 empty] | 5214.34
|  |  | JDH3-02-008-L-54-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-08-18 | 2025-09-13 | 26-May-25 A | 2025-10-11 | 1950-07-10 12:14 | 1950-07-10 12:14 | 27375.33 | Planned Total Cost | [13 empty] | 13687.66 | 4766.85 | 8920.82
|  |  | JDH3-02-008-L-54-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-08-18 | 2025-09-13 | 26-May-25 A | 2025-10-11 | 1950-07-10 12:14 | 1950-07-10 12:14 | 27375.33 | Remaining Total Cost | [15 empty] | 8920.82
|  |  | JDH3-02-008-L-54-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-08-18 | 2025-09-13 | 26-May-25 A | 2025-10-11 | 1950-07-10 12:14 | 1950-07-10 12:14 | 27375.33 | Actual Total Cost | [10 empty] | 2709.02 | 15745.49
|  |  | JDH3-02-008-L-54-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-08-28 | 2025-09-15 | 02-Aug-25 A | 2025-10-13 | 2155-03-09 11:17 | 2155-03-09 11:31 | 186412.95 | Planned Total Cost | [13 empty] | 62137.65 | 31068.82 | 93206.47
|  |  | JDH3-02-008-L-54-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-08-28 | 2025-09-15 | 02-Aug-25 A | 2025-10-13 | 2155-03-09 11:17 | 2155-03-09 11:31 | 186412.95 | Remaining Total Cost | [15 empty] | 93206.47
|  |  | JDH3-02-008-L-54-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-08-28 | 2025-09-15 | 02-Aug-25 A | 2025-10-13 | 2155-03-09 11:17 | 2155-03-09 11:31 | 186412.95 | Actual Total Cost | [13 empty] | 93206.48
|  |  | JDH3-02-008-L-54-(ST)- Single Catchbasine Works |  | 2025-08-31 | 2025-09-10 | 2025-10-02 | 2025-10-13 | 0 | 0 | 70393.74 | Planned Total Cost | [15 empty] | 70393.74
|  |  | JDH3-02-008-L-54-(ST)- Single Catchbasine Works |  | 2025-08-31 | 2025-09-10 | 2025-10-02 | 2025-10-13 | 0 | 0 | 70393.74 | Remaining Total Cost | [15 empty] | 70393.74
|  |  | JDH3-02-008-L-54-(ST)- Single Catchbasine Works |  | 2025-08-31 | 2025-09-10 | 2025-10-02 | 2025-10-13 | 0 | 0 | 70393.74 | Actual Total Cost
|  |  | JDH3-02-008-L-54-(ST)- Double Catchbasine Works |  | 2025-09-02 | 2025-09-17 | 2025-10-05 | 2025-10-15 | 0 | 0 | 181824.28 | Planned Total Cost | [15 empty] | 181824.28
|  |  | JDH3-02-008-L-54-(ST)- Double Catchbasine Works |  | 2025-09-02 | 2025-09-17 | 2025-10-05 | 2025-10-15 | 0 | 0 | 181824.28 | Remaining Total Cost | [15 empty] | 181824.28
|  |  | JDH3-02-008-L-54-(ST)- Double Catchbasine Works |  | 2025-09-02 | 2025-09-17 | 2025-10-05 | 2025-10-15 | 0 | 0 | 181824.28 | Actual Total Cost
|  |  | JDH3-02-008-L-54-(ST)-PIPES ENCASEMENT |  | 2025-08-31 | 2025-09-06 | 2026-01-08 | 2026-01-15 | 0 | 0 | 20837 | Planned Total Cost | [18 empty] | 20837
|  |  | JDH3-02-008-L-54-(ST)-PIPES ENCASEMENT |  | 2025-08-31 | 2025-09-06 | 2026-01-08 | 2026-01-15 | 0 | 0 | 20837 | Remaining Total Cost | [18 empty] | 20837
|  |  | JDH3-02-008-L-54-(ST)-PIPES ENCASEMENT |  | 2025-08-31 | 2025-09-06 | 2026-01-08 | 2026-01-15 | 0 | 0 | 20837 | Actual Total Cost
|  |  | JDH3-02-008-L-54-TSE Network - TSE |  | 2025-09-24 | 2025-10-29 | 2026-01-21 | 2026-02-26 | 0 | 0 | 110603.09 | Planned Total Cost | [18 empty] | 27989.88 | 82613.21
|  |  | JDH3-02-008-L-54-TSE Network - TSE |  | 2025-09-24 | 2025-10-29 | 2026-01-21 | 2026-02-26 | 0 | 0 | 110603.09 | Remaining Total Cost | [18 empty] | 27989.88 | 82613.21
|  |  | JDH3-02-008-L-54-TSE Network - TSE |  | 2025-09-24 | 2025-10-29 | 2026-01-21 | 2026-02-26 | 0 | 0 | 110603.09 | Actual Total Cost
|  |  | JDH3-02-008-L-54-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-24 | 2025-10-29 | 2026-01-21 | 2026-02-26 | 0 | 0 | 94974.81 | Planned Total Cost | [18 empty] | 22053.15 | 72921.66
|  |  | JDH3-02-008-L-54-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-24 | 2025-10-29 | 2026-01-21 | 2026-02-26 | 0 | 0 | 94974.81 | Remaining Total Cost | [18 empty] | 22053.15 | 72921.66
|  |  | JDH3-02-008-L-54-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-09-24 | 2025-10-29 | 2026-01-21 | 2026-02-26 | 0 | 0 | 94974.81 | Actual Total Cost
|  |  | JDH3-02-008-L-54-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-09-24 | 2025-10-22 | 2026-01-21 | 2026-02-19 | 0 | 0 | 6596.37 | Planned Total Cost | [18 empty] | 5936.73 | 659.64
|  |  | JDH3-02-008-L-54-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-09-24 | 2025-10-22 | 2026-01-21 | 2026-02-19 | 0 | 0 | 6596.37 | Remaining Total Cost | [18 empty] | 5936.73 | 659.64
|  |  | JDH3-02-008-L-54-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-09-24 | 2025-10-22 | 2026-01-21 | 2026-02-19 | 0 | 0 | 6596.37 | Actual Total Cost
|  |  | JDH3-02-008-L-54-(TSE)-Supply and install gate valves-100 mm |  | 2025-10-16 | 2025-10-20 | 2026-02-12 | 2026-02-17 | 0 | 0 | 6465.8 | Planned Total Cost | [19 empty] | 6465.8
|  |  | JDH3-02-008-L-54-(TSE)-Supply and install gate valves-100 mm |  | 2025-10-16 | 2025-10-20 | 2026-02-12 | 2026-02-17 | 0 | 0 | 6465.8 | Remaining Total Cost | [19 empty] | 6465.8
|  |  | JDH3-02-008-L-54-(TSE)-Supply and install gate valves-100 mm |  | 2025-10-16 | 2025-10-20 | 2026-02-12 | 2026-02-17 | 0 | 0 | 6465.8 | Actual Total Cost
|  |  | JDH3-02-008-L-54-(TSE)-Supply and install gate valves-250 mm |  | 2025-10-16 | 2025-10-20 | 2026-02-12 | 2026-02-17 | 0 | 0 | 2566.11 | Planned Total Cost | [19 empty] | 2566.11
|  |  | JDH3-02-008-L-54-(TSE)-Supply and install gate valves-250 mm |  | 2025-10-16 | 2025-10-20 | 2026-02-12 | 2026-02-17 | 0 | 0 | 2566.11 | Remaining Total Cost | [19 empty] | 2566.11
|  |  | JDH3-02-008-L-54-(TSE)-Supply and install gate valves-250 mm |  | 2025-10-16 | 2025-10-20 | 2026-02-12 | 2026-02-17 | 0 | 0 | 2566.11 | Actual Total Cost
|  |  | JDH3-02-008-L-54-Potable Water Network - WT |  | 2025-10-30 | 2025-11-10 | 2026-02-26 | 2026-03-10 | 0 | 0 | 70899.67 | Planned Total Cost | [19 empty] | 8649.76 | 62249.91
|  |  | JDH3-02-008-L-54-Potable Water Network - WT |  | 2025-10-30 | 2025-11-10 | 2026-02-26 | 2026-03-10 | 0 | 0 | 70899.67 | Remaining Total Cost | [19 empty] | 8649.76 | 62249.91
|  |  | JDH3-02-008-L-54-Potable Water Network - WT |  | 2025-10-30 | 2025-11-10 | 2026-02-26 | 2026-03-10 | 0 | 0 | 70899.67 | Actual Total Cost
|  |  | JDH3-02-008-L-54-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-10-30 | 2025-11-10 | 2026-02-26 | 2026-03-10 | 0 | 0 | 7420.85 | Planned Total Cost | [19 empty] | 905.34 | 6515.51
|  |  | JDH3-02-008-L-54-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-10-30 | 2025-11-10 | 2026-02-26 | 2026-03-10 | 0 | 0 | 7420.85 | Remaining Total Cost | [19 empty] | 905.34 | 6515.51
|  |  | JDH3-02-008-L-54-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-10-30 | 2025-11-10 | 2026-02-26 | 2026-03-10 | 0 | 0 | 7420.85 | Actual Total Cost
|  |  | JDH3-02-008-L-54-(WT)- Supply and install 3-out fire hydrant |  | 2025-10-30 | 2025-11-05 | 2026-02-26 | 2026-03-05 | 0 | 0 | 63478.82 | Planned Total Cost | [19 empty] | 7744.42 | 55734.41
|  |  | JDH3-02-008-L-54-(WT)- Supply and install 3-out fire hydrant |  | 2025-10-30 | 2025-11-05 | 2026-02-26 | 2026-03-05 | 0 | 0 | 63478.82 | Remaining Total Cost | [19 empty] | 7744.42 | 55734.41
|  |  | JDH3-02-008-L-54-(WT)- Supply and install 3-out fire hydrant |  | 2025-10-30 | 2025-11-05 | 2026-02-26 | 2026-03-05 | 0 | 0 | 63478.82 | Actual Total Cost
|  |  | L-55 |  | 2025-08-18 | 2025-12-18 | 04-Feb-25 A | 2026-04-15 | 991737.61 | 991737.59 | 1829279.9 | Planned Total Cost | [13 empty] | 340553.02 | 576799.79 | 376021.14 |  |  | 15127.11 | 299871.8 | 145210.7 | 75696.34
|  |  | L-55 |  | 2025-08-18 | 2025-12-18 | 04-Feb-25 A | 2026-04-15 | 991737.61 | 991737.59 | 1829279.9 | Remaining Total Cost | [15 empty] | 311685.61 |  |  | 5077.84 | 299871.8 | 145210.7 | 75696.34
|  |  | L-55 |  | 2025-08-18 | 2025-12-18 | 04-Feb-25 A | 2026-04-15 | 991737.61 | 991737.59 | 1829279.9 | Actual Total Cost | [8 empty] | 278517.87 | 323138.25 | 155805.6 | 161975 | 29388.61 | 10754.6 | 32157.65
|  |  | JDH3-02-008-L-55-Storm Network - ST |  | 2025-08-26 | 2025-11-13 | 03-Mar-25 A | 2026-03-11 | 991737.61 | 991737.59 | 1681427.68 | Planned Total Cost | [13 empty] | 340553.02 | 576799.79 | 376021.14 |  |  | 15127.11 | 299871.8 | 73054.82
|  |  | JDH3-02-008-L-55-Storm Network - ST |  | 2025-08-26 | 2025-11-13 | 03-Mar-25 A | 2026-03-11 | 991737.61 | 991737.59 | 1681427.68 | Remaining Total Cost | [15 empty] | 311685.61 |  |  | 5077.84 | 299871.8 | 73054.82
|  |  | JDH3-02-008-L-55-Storm Network - ST |  | 2025-08-26 | 2025-11-13 | 03-Mar-25 A | 2026-03-11 | 991737.61 | 991737.59 | 1681427.68 | Actual Total Cost | [8 empty] | 278517.87 | 323138.25 | 155805.6 | 161975 | 29388.61 | 10754.6 | 32157.65
|  |  | JDH3-02-008-L-55-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-10-04 | 2025-10-26 | 2026-01-31 | 2026-02-21 | 0 | 0 | 230810.92 | Planned Total Cost | [18 empty] | 5077.84 | 225733.07
|  |  | JDH3-02-008-L-55-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-10-04 | 2025-10-26 | 2026-01-31 | 2026-02-21 | 0 | 0 | 230810.92 | Remaining Total Cost | [18 empty] | 5077.84 | 225733.07
|  |  | JDH3-02-008-L-55-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-10-04 | 2025-10-26 | 2026-01-31 | 2026-02-21 | 0 | 0 | 230810.92 | Actual Total Cost
|  |  | JDH3-02-008-L-55-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-10-06 | 2025-10-23 | 16-Sep-25 A | 2026-02-18 | 32157.66 | 1988-01-15 15:36 | 40197.07 | Planned Total Cost | [15 empty] | 26128.1 |  |  | 10049.27 | 4019.71
|  |  | JDH3-02-008-L-55-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-10-06 | 2025-10-23 | 16-Sep-25 A | 2026-02-18 | 32157.66 | 1988-01-15 15:36 | 40197.07 | Remaining Total Cost | [15 empty] | 4019.71 |  |  |  | 4019.71
|  |  | JDH3-02-008-L-55-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-10-06 | 2025-10-23 | 16-Sep-25 A | 2026-02-18 | 32157.66 | 1988-01-15 15:36 | 40197.07 | Actual Total Cost | [14 empty] | 32157.65
|  |  | JDH3-02-008-L-55-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-10-08 | 2025-10-23 | 2025-10-02 | 2026-02-18 | 0 | 0 | 49659.21 | Planned Total Cost | [15 empty] | 44693.29 |  |  |  | 4965.92
|  |  | JDH3-02-008-L-55-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-10-08 | 2025-10-23 | 2025-10-02 | 2026-02-18 | 0 | 0 | 49659.21 | Remaining Total Cost | [15 empty] | 44693.29 |  |  |  | 4965.92
|  |  | JDH3-02-008-L-55-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-10-08 | 2025-10-23 | 2025-10-02 | 2026-02-18 | 0 | 0 | 49659.21 | Actual Total Cost
|  |  | JDH3-02-008-L-55-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-08-26 | 2025-10-26 | 03-Mar-25 A | 2026-02-21 | 2195-04-25 05:17 | 2195-04-25 05:17 | 113552.55 | Planned Total Cost | [13 empty] | 59615.09 | 48248.13 |  |  |  |  | 5689.34
|  |  | JDH3-02-008-L-55-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-08-26 | 2025-10-26 | 03-Mar-25 A | 2026-02-21 | 2195-04-25 05:17 | 2195-04-25 05:17 | 113552.55 | Remaining Total Cost | [19 empty] | 5689.34
|  |  | JDH3-02-008-L-55-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-08-26 | 2025-10-26 | 03-Mar-25 A | 2026-02-21 | 2195-04-25 05:17 | 2195-04-25 05:17 | 113552.55 | Actual Total Cost | [8 empty] | 90842.04 |  | 11355.26 |  | 5665.92
|  |  | JDH3-02-008-L-55-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-08-26 | 2025-10-28 | 10-Mar-25 A | 2026-02-23 | 340560.95 | 340560.95 | 358479 | Planned Total Cost | [13 empty] | 76176.79 | 264384.16 |  |  |  |  | 17918.06
|  |  | JDH3-02-008-L-55-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-08-26 | 2025-10-28 | 10-Mar-25 A | 2026-02-23 | 340560.95 | 340560.95 | 358479 | Remaining Total Cost | [19 empty] | 17918.06
|  |  | JDH3-02-008-L-55-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-08-26 | 2025-10-28 | 10-Mar-25 A | 2026-02-23 | 340560.95 | 340560.95 | 358479 | Actual Total Cost | [8 empty] | 136446.07 | 150337.13 | 14339.16 | 21508.74 | 17929.85
|  |  | JDH3-02-008-L-55-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2025-08-26 | 2025-10-30 | 10-Mar-25 A | 2026-02-25 | 331362.49 | 331362.5 | 348798.38 | Planned Total Cost | [13 empty] | 81386.29 | 249976.21 |  |  |  |  | 17435.89
|  |  | JDH3-02-008-L-55-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2025-08-26 | 2025-10-30 | 10-Mar-25 A | 2026-02-25 | 331362.49 | 331362.5 | 348798.38 | Remaining Total Cost | [19 empty] | 17435.89
|  |  | JDH3-02-008-L-55-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2025-08-26 | 2025-10-30 | 10-Mar-25 A | 2026-02-25 | 331362.49 | 331362.5 | 348798.38 | Actual Total Cost | [8 empty] | 51229.77 | 172801.12 | 101880.38 | 5451.23
|  |  | JDH3-02-008-L-55-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2025-08-26 | 2025-11-04 | 09-Jun-25 A | 2026-03-02 | 1960-08-05 20:10 | 1960-08-05 19:55 | 27667.3 | Planned Total Cost | [13 empty] | 14525.33 | 7608.51 |  |  |  |  | 3071.07 | 2462.39
|  |  | JDH3-02-008-L-55-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2025-08-26 | 2025-11-04 | 09-Jun-25 A | 2026-03-02 | 1960-08-05 20:10 | 1960-08-05 19:55 | 27667.3 | Remaining Total Cost | [19 empty] | 3071.07 | 2462.39
|  |  | JDH3-02-008-L-55-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2025-08-26 | 2025-11-04 | 09-Jun-25 A | 2026-03-02 | 1960-08-05 20:10 | 1960-08-05 19:55 | 27667.3 | Actual Total Cost | [11 empty] | 16340.99 | 5792.84
|  |  | JDH3-02-008-L-55-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-08-26 | 2025-11-09 | 25-May-25 A | 2026-03-07 | 1919-03-31 06:58 | 1919-03-31 06:43 | 10428.7 | Planned Total Cost | [13 empty] | 5214.35 | 1815.94 |  |  |  |  | 201.75 | 3196.66
|  |  | JDH3-02-008-L-55-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-08-26 | 2025-11-09 | 25-May-25 A | 2026-03-07 | 1919-03-31 06:58 | 1919-03-31 06:43 | 10428.7 | Remaining Total Cost | [19 empty] | 201.75 | 3196.66
|  |  | JDH3-02-008-L-55-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-08-26 | 2025-11-09 | 25-May-25 A | 2026-03-07 | 1919-03-31 06:58 | 1919-03-31 06:43 | 10428.7 | Actual Total Cost | [10 empty] | 1466.53 | 5563.75
|  |  | JDH3-02-008-L-55-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-08-26 | 2025-11-11 | 25-May-25 A | 2026-03-09 | 2001-01-18 00:43 | 2001-01-18 00:29 | 54750.66 | Planned Total Cost | [13 empty] | 27375.33 | 4766.85 | 4766.85 |  |  |  |  | 17841.63
|  |  | JDH3-02-008-L-55-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-08-26 | 2025-11-11 | 25-May-25 A | 2026-03-09 | 2001-01-18 00:43 | 2001-01-18 00:29 | 54750.66 | Remaining Total Cost | [20 empty] | 17841.63
|  |  | JDH3-02-008-L-55-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-08-26 | 2025-11-11 | 25-May-25 A | 2026-03-09 | 2001-01-18 00:43 | 2001-01-18 00:29 | 54750.66 | Actual Total Cost | [10 empty] | 7699.31 | 29209.71
|  |  | JDH3-02-008-L-55-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-08-26 | 2025-11-13 | 25-May-25 A | 2026-03-11 | 2181-11-26 12:58 | 2181-11-26 12:58 | 152519.68 | Planned Total Cost | [13 empty] | 76259.84 |  | 26705.7 |  |  |  |  | 49554.14
|  |  | JDH3-02-008-L-55-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-08-26 | 2025-11-13 | 25-May-25 A | 2026-03-11 | 2181-11-26 12:58 | 2181-11-26 12:58 | 152519.68 | Remaining Total Cost | [20 empty] | 49554.14
|  |  | JDH3-02-008-L-55-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-08-26 | 2025-11-13 | 25-May-25 A | 2026-03-11 | 2181-11-26 12:58 | 2181-11-26 12:58 | 152519.68 | Actual Total Cost | [10 empty] | 19064.96 | 83900.58
|  |  | JDH3-02-008-L-55-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-10-11 | 2025-10-21 | 09-Aug-25 A | 2025-10-08 | 1929-06-10 14:10 | 1929-06-10 14:24 | 21509.18 | Planned Total Cost | [15 empty] | 21509.18
|  |  | JDH3-02-008-L-55-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-10-11 | 2025-10-21 | 09-Aug-25 A | 2025-10-08 | 1929-06-10 14:10 | 1929-06-10 14:24 | 21509.18 | Remaining Total Cost | [15 empty] | 10754.59
|  |  | JDH3-02-008-L-55-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-10-11 | 2025-10-21 | 09-Aug-25 A | 2025-10-08 | 1929-06-10 14:10 | 1929-06-10 14:24 | 21509.18 | Actual Total Cost | [13 empty] | 10754.6
|  |  | JDH3-02-008-L-55-(ST)- Single Catchbasine Works |  | 2025-10-13 | 2025-10-23 | 2025-10-02 | 2025-10-13 | 0 | 0 | 70393.74 | Planned Total Cost | [15 empty] | 70393.74
|  |  | JDH3-02-008-L-55-(ST)- Single Catchbasine Works |  | 2025-10-13 | 2025-10-23 | 2025-10-02 | 2025-10-13 | 0 | 0 | 70393.74 | Remaining Total Cost | [15 empty] | 70393.74
|  |  | JDH3-02-008-L-55-(ST)- Single Catchbasine Works |  | 2025-10-13 | 2025-10-23 | 2025-10-02 | 2025-10-13 | 0 | 0 | 70393.74 | Actual Total Cost
|  |  | JDH3-02-008-L-55-(ST)- Double Catchbasine Works |  | 2025-10-15 | 2025-10-26 | 2025-10-05 | 2025-10-15 | 0 | 0 | 181824.28 | Planned Total Cost | [15 empty] | 181824.28
|  |  | JDH3-02-008-L-55-(ST)- Double Catchbasine Works |  | 2025-10-15 | 2025-10-26 | 2025-10-05 | 2025-10-15 | 0 | 0 | 181824.28 | Remaining Total Cost | [15 empty] | 181824.28
|  |  | JDH3-02-008-L-55-(ST)- Double Catchbasine Works |  | 2025-10-15 | 2025-10-26 | 2025-10-05 | 2025-10-15 | 0 | 0 | 181824.28 | Actual Total Cost
|  |  | JDH3-02-008-L-55-(ST)-PIPES ENCASEMENT |  | 2025-10-15 | 2025-10-21 | 2026-02-09 | 2026-02-16 | 0 | 0 | 20837 | Planned Total Cost | [19 empty] | 20837
|  |  | JDH3-02-008-L-55-(ST)-PIPES ENCASEMENT |  | 2025-10-15 | 2025-10-21 | 2026-02-09 | 2026-02-16 | 0 | 0 | 20837 | Remaining Total Cost | [19 empty] | 20837
|  |  | JDH3-02-008-L-55-(ST)-PIPES ENCASEMENT |  | 2025-10-15 | 2025-10-21 | 2026-02-09 | 2026-02-16 | 0 | 0 | 20837 | Actual Total Cost
|  |  | JDH3-02-008-L-55-TSE Network - TSE |  | 2025-11-15 | 2025-12-07 | 2026-03-11 | 2026-04-04 | 0 | 0 | 76817.62 | Planned Total Cost | [20 empty] | 72155.88 | 4661.74
|  |  | JDH3-02-008-L-55-TSE Network - TSE |  | 2025-11-15 | 2025-12-07 | 2026-03-11 | 2026-04-04 | 0 | 0 | 76817.62 | Remaining Total Cost | [20 empty] | 72155.88 | 4661.74
|  |  | JDH3-02-008-L-55-TSE Network - TSE |  | 2025-11-15 | 2025-12-07 | 2026-03-11 | 2026-04-04 | 0 | 0 | 76817.62 | Actual Total Cost
|  |  | JDH3-02-008-L-55-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-11-15 | 2025-12-07 | 2026-03-11 | 2026-04-04 | 0 | 0 | 62886.01 | Planned Total Cost | [20 empty] | 58515.43 | 4370.58
|  |  | JDH3-02-008-L-55-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-11-15 | 2025-12-07 | 2026-03-11 | 2026-04-04 | 0 | 0 | 62886.01 | Remaining Total Cost | [20 empty] | 58515.43 | 4370.58
|  |  | JDH3-02-008-L-55-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-11-15 | 2025-12-07 | 2026-03-11 | 2026-04-04 | 0 | 0 | 62886.01 | Actual Total Cost
|  |  | JDH3-02-008-L-55-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-11-15 | 2025-12-04 | 2026-03-11 | 2026-04-01 | 0 | 0 | 7465.81 | Planned Total Cost | [20 empty] | 7174.64 | 291.17
|  |  | JDH3-02-008-L-55-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-11-15 | 2025-12-04 | 2026-03-11 | 2026-04-01 | 0 | 0 | 7465.81 | Remaining Total Cost | [20 empty] | 7174.64 | 291.17
|  |  | JDH3-02-008-L-55-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-11-15 | 2025-12-04 | 2026-03-11 | 2026-04-01 | 0 | 0 | 7465.81 | Actual Total Cost
|  |  | JDH3-02-008-L-55-(TSE)-Supply and install gate valves-100 mm |  | 2025-11-29 | 2025-12-02 | 2026-03-25 | 2026-03-30 | 0 | 0 | 6465.8 | Planned Total Cost | [20 empty] | 6465.8
|  |  | JDH3-02-008-L-55-(TSE)-Supply and install gate valves-100 mm |  | 2025-11-29 | 2025-12-02 | 2026-03-25 | 2026-03-30 | 0 | 0 | 6465.8 | Remaining Total Cost | [20 empty] | 6465.8
|  |  | JDH3-02-008-L-55-(TSE)-Supply and install gate valves-100 mm |  | 2025-11-29 | 2025-12-02 | 2026-03-25 | 2026-03-30 | 0 | 0 | 6465.8 | Actual Total Cost
|  |  | JDH3-02-008-L-55-Potable Water Network - WT |  | 2025-12-08 | 2025-12-18 | 2026-04-04 | 2026-04-15 | 0 | 0 | 71034.6 | Planned Total Cost | [21 empty] | 71034.6
|  |  | JDH3-02-008-L-55-Potable Water Network - WT |  | 2025-12-08 | 2025-12-18 | 2026-04-04 | 2026-04-15 | 0 | 0 | 71034.6 | Remaining Total Cost | [21 empty] | 71034.6
|  |  | JDH3-02-008-L-55-Potable Water Network - WT |  | 2025-12-08 | 2025-12-18 | 2026-04-04 | 2026-04-15 | 0 | 0 | 71034.6 | Actual Total Cost
|  |  | JDH3-02-008-L-55-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-12-08 | 2025-12-18 | 2026-04-04 | 2026-04-15 | 0 | 0 | 7555.78 | Planned Total Cost | [21 empty] | 7555.78
|  |  | JDH3-02-008-L-55-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-12-08 | 2025-12-18 | 2026-04-04 | 2026-04-15 | 0 | 0 | 7555.78 | Remaining Total Cost | [21 empty] | 7555.78
|  |  | JDH3-02-008-L-55-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-12-08 | 2025-12-18 | 2026-04-04 | 2026-04-15 | 0 | 0 | 7555.78 | Actual Total Cost
|  |  | JDH3-02-008-L-55-(WT)- Supply and install 3-out fire hydrant |  | 2025-12-08 | 2025-12-14 | 2026-04-04 | 2026-04-11 | 0 | 0 | 63478.82 | Planned Total Cost | [21 empty] | 63478.82
|  |  | JDH3-02-008-L-55-(WT)- Supply and install 3-out fire hydrant |  | 2025-12-08 | 2025-12-14 | 2026-04-04 | 2026-04-11 | 0 | 0 | 63478.82 | Remaining Total Cost | [21 empty] | 63478.82
|  |  | JDH3-02-008-L-55-(WT)- Supply and install 3-out fire hydrant |  | 2025-12-08 | 2025-12-14 | 2026-04-04 | 2026-04-11 | 0 | 0 | 63478.82 | Actual Total Cost
|  |  | L-56 |  | 2025-08-26 | 2026-03-22 | 04-Nov-24 A | 2026-05-26 | 2186383.4 | 2186383.42 | 4774752.92 | Planned Total Cost | [14 empty] | 745230.42 | 1186550.81 | 512613.64 | 25211.13 |  | 205325.12 | 1658094.81 | 364245.03 | 77481.96
|  |  | L-56 |  | 2025-08-26 | 2026-03-22 | 04-Nov-24 A | 2026-05-26 | 2186383.4 | 2186383.42 | 4774752.92 | Remaining Total Cost | [15 empty] | 271530.16 | 16911.6 |  |  | 90716.27 | 1767484.48 | 364245.03 | 77481.96
|  |  | L-56 |  | 2025-08-26 | 2026-03-22 | 04-Nov-24 A | 2026-05-26 | 2186383.4 | 2186383.42 | 4774752.92 | Actual Total Cost |  |  |  |  | 2656.57 | 7969.7 | 118712.04 | 283886.97 | 328050.94 | 267558.02 | 238204.05 | 220063.97 | 248602.79 | 80341.77 | 379322.65 | 11013.96
|  |  | JDH3-02-008-L-56-Storm Network - ST |  | 2025-09-03 | 2026-01-31 | 26-Nov-24 A | 2026-04-18 | 2186383.4 | 2186383.42 | 4207508.84 | Planned Total Cost | [14 empty] | 745230.42 | 1186550.81 | 512613.64 | 25211.13 |  | 205325.12 | 1444727.36 | 87850.36
|  |  | JDH3-02-008-L-56-Storm Network - ST |  | 2025-09-03 | 2026-01-31 | 26-Nov-24 A | 2026-04-18 | 2186383.4 | 2186383.42 | 4207508.84 | Remaining Total Cost | [15 empty] | 271530.16 | 16911.6 |  |  | 90716.27 | 1554117.03 | 87850.36
|  |  | JDH3-02-008-L-56-Storm Network - ST |  | 2025-09-03 | 2026-01-31 | 26-Nov-24 A | 2026-04-18 | 2186383.4 | 2186383.42 | 4207508.84 | Actual Total Cost |  |  |  |  | 2656.57 | 7969.7 | 118712.04 | 283886.97 | 328050.94 | 267558.02 | 238204.05 | 220063.97 | 248602.79 | 80341.77 | 379322.65 | 11013.96
|  |  | JDH3-02-008-L-56-(ST)-Box Culvert |  | 2025-09-03 | 2025-12-25 | 26-Nov-24 A | 2025-11-03 | 492275.86 | 492275.86 | 687784.19 | Planned Total Cost | [14 empty] | 137910.93 | 450247.44 | 99625.82
|  |  | JDH3-02-008-L-56-(ST)-Box Culvert |  | 2025-09-03 | 2025-12-25 | 26-Nov-24 A | 2025-11-03 | 492275.86 | 492275.86 | 687784.19 | Remaining Total Cost | [15 empty] | 178596.73 | 16911.6
|  |  | JDH3-02-008-L-56-(ST)-Box Culvert |  | 2025-09-03 | 2025-12-25 | 26-Nov-24 A | 2025-11-03 | 492275.86 | 492275.86 | 687784.19 | Actual Total Cost |  |  |  |  | 2656.57 | 7969.7 | 109842.62 | 66432.07 | 83582.46 | 45534.61 | 58476.24 | 1694.96 |  | 6318.97 | 109767.65
|  |  | JDH3-02-008-L-56-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2025-09-28 | 2025-11-23 | 05-Jan-25 A | 23-Sep-25 A | 481649.6 | 481649.59 | 481649.6 | Planned Total Cost | [14 empty] | 127284.66 | 271650.72 | 82714.22
|  |  | JDH3-02-008-L-56-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2025-09-28 | 2025-11-23 | 05-Jan-25 A | 23-Sep-25 A | 481649.6 | 481649.59 | 481649.6 | Remaining Total Cost
|  |  | JDH3-02-008-L-56-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2025-09-28 | 2025-11-23 | 05-Jan-25 A | 23-Sep-25 A | 481649.6 | 481649.59 | 481649.6 | Actual Total Cost | [6 empty] | 109842.62 | 66432.07 | 83582.46 | 45534.61 | 58476.24 | 1694.96 |  | 6318.97 | 109767.65
|  |  | JDH3-02-008-L-56-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2025-09-03 | 2025-12-07 | 26-Nov-24 A | 2025-10-15 | 1929-02-02 06:29 | 1929-02-02 06:29 | 70841.77 | Planned Total Cost | [14 empty] | 10626.27 | 60215.5
|  |  | JDH3-02-008-L-56-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2025-09-03 | 2025-12-07 | 26-Nov-24 A | 2025-10-15 | 1929-02-02 06:29 | 1929-02-02 06:29 | 70841.77 | Remaining Total Cost | [15 empty] | 60215.5
|  |  | JDH3-02-008-L-56-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2025-09-03 | 2025-12-07 | 26-Nov-24 A | 2025-10-15 | 1929-02-02 06:29 | 1929-02-02 06:29 | 70841.77 | Actual Total Cost |  |  |  |  | 2656.57 | 7969.7
|  |  | JDH3-02-008-L-56-(ST)- Concrete Box Culvert With Dim (4000x1500) depth from 3.51 to 4.50 |  | 2025-12-08 | 2025-12-25 | 2025-10-16 | 2025-11-03 | 0 | 0 | 135292.83 | Planned Total Cost | [15 empty] | 118381.22 | 16911.6
|  |  | JDH3-02-008-L-56-(ST)- Concrete Box Culvert With Dim (4000x1500) depth from 3.51 to 4.50 |  | 2025-12-08 | 2025-12-25 | 2025-10-16 | 2025-11-03 | 0 | 0 | 135292.83 | Remaining Total Cost | [15 empty] | 118381.22 | 16911.6
|  |  | JDH3-02-008-L-56-(ST)- Concrete Box Culvert With Dim (4000x1500) depth from 3.51 to 4.50 |  | 2025-12-08 | 2025-12-25 | 2025-10-16 | 2025-11-03 | 0 | 0 | 135292.83 | Actual Total Cost
|  |  | JDH3-02-008-L-56-(ST)-NetWork |  | 2025-09-03 | 2026-01-31 | 28-Jan-25 A | 2026-04-18 | 1694107.54 | 1694107.56 | 3519724.65 | Planned Total Cost | [14 empty] | 607319.5 | 736303.37 | 412987.82 | 25211.13 |  | 205325.12 | 1444727.36 | 87850.36
|  |  | JDH3-02-008-L-56-(ST)-NetWork |  | 2025-09-03 | 2026-01-31 | 28-Jan-25 A | 2026-04-18 | 1694107.54 | 1694107.56 | 3519724.65 | Remaining Total Cost | [15 empty] | 92933.44 |  |  |  | 90716.27 | 1554117.03 | 87850.36
|  |  | JDH3-02-008-L-56-(ST)-NetWork |  | 2025-09-03 | 2026-01-31 | 28-Jan-25 A | 2026-04-18 | 1694107.54 | 1694107.56 | 3519724.65 | Actual Total Cost | [6 empty] | 8869.42 | 217454.9 | 244468.47 | 222023.41 | 179727.81 | 218369 | 248602.79 | 74022.8 | 269555 | 11013.96
|  |  | JDH3-02-008-L-56-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-10-26 | 2026-01-03 | 2026-02-23 | 2026-04-04 | 0 | 0 | 524343.08 | Planned Total Cost | [19 empty] | 88509.11 | 419637.59 | 16196.38
|  |  | JDH3-02-008-L-56-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-10-26 | 2026-01-03 | 2026-02-23 | 2026-04-04 | 0 | 0 | 524343.08 | Remaining Total Cost | [19 empty] | 88509.11 | 419637.59 | 16196.38
|  |  | JDH3-02-008-L-56-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-10-26 | 2026-01-03 | 2026-02-23 | 2026-04-04 | 0 | 0 | 524343.08 | Actual Total Cost
|  |  | JDH3-02-008-L-56-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-11-01 | 2025-12-25 | 2026-03-01 | 2026-03-25 | 0 | 0 | 89775.73 | Planned Total Cost | [20 empty] | 89775.73
|  |  | JDH3-02-008-L-56-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-11-01 | 2025-12-25 | 2026-03-01 | 2026-03-25 | 0 | 0 | 89775.73 | Remaining Total Cost | [20 empty] | 89775.73
|  |  | JDH3-02-008-L-56-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-11-01 | 2025-12-25 | 2026-03-01 | 2026-03-25 | 0 | 0 | 89775.73 | Actual Total Cost
|  |  | JDH3-02-008-L-56-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-09-03 | 2026-01-31 | 16-Jun-25 A | 2026-04-18 | 2225-04-29 04:48 | 2225-04-29 04:34 | 175336.36 | Planned Total Cost | [14 empty] | 118824.2 | [5 empty] | 38978.52 | 17533.64
|  |  | JDH3-02-008-L-56-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-09-03 | 2026-01-31 | 16-Jun-25 A | 2026-04-18 | 2225-04-29 04:48 | 2225-04-29 04:34 | 175336.36 | Remaining Total Cost | [20 empty] | 38978.52 | 17533.64
|  |  | JDH3-02-008-L-56-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-09-03 | 2026-01-31 | 16-Jun-25 A | 2026-04-18 | 2225-04-29 04:48 | 2225-04-29 04:34 | 175336.36 | Actual Total Cost | [11 empty] | 19118.2 | 99705.99
|  |  | JDH3-02-008-L-56-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2025-09-07 | 2025-11-13 | 22-Apr-25 A | 2026-03-03 | 2396-01-29 23:02 | 2396-01-29 23:02 | 216172.26 | Planned Total Cost | [14 empty] | 153448.04 | 872.63 | 18999.34 |  |  | 9947.9 | 32904.35
|  |  | JDH3-02-008-L-56-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2025-09-07 | 2025-11-13 | 22-Apr-25 A | 2026-03-03 | 2396-01-29 23:02 | 2396-01-29 23:02 | 216172.26 | Remaining Total Cost | [20 empty] | 34981.29
|  |  | JDH3-02-008-L-56-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2025-09-07 | 2025-11-13 | 22-Apr-25 A | 2026-03-03 | 2396-01-29 23:02 | 2396-01-29 23:02 | 216172.26 | Actual Total Cost | [9 empty] | 56671.18 | 81499.53 | 1472.56 | 14677.4 |  | 25111.34 | 1758.95
|  |  | JDH3-02-008-L-56-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-09-11 | 2025-11-19 | 16-Jun-25 A | 2026-03-03 | 2263-11-12 02:24 | 2263-11-12 02:53 | 155358.07 | Planned Total Cost | [14 empty] | 68867.43 |  | 31071.61 |  |  | 55419.03
|  |  | JDH3-02-008-L-56-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-09-11 | 2025-11-19 | 16-Jun-25 A | 2026-03-03 | 2263-11-12 02:24 | 2263-11-12 02:53 | 155358.07 | Remaining Total Cost | [19 empty] | 2207.16 | 20250.79
|  |  | JDH3-02-008-L-56-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-09-11 | 2025-11-19 | 16-Jun-25 A | 2026-03-03 | 2263-11-12 02:24 | 2263-11-12 02:53 | 155358.07 | Actual Total Cost | [11 empty] | 24435.01 | 44432.42 | 2631.9 | 58231.3 | 3169.49
|  |  | JDH3-02-008-L-56-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-09-15 | 2025-11-19 | 16-Jun-25 A | 2026-03-03 | 2310-03-18 10:19 | 2310-03-18 10:19 | 174111.7 | Planned Total Cost | [14 empty] | 76990.02 |  | 34822.34 |  |  | 35813.52 | 26485.82
|  |  | JDH3-02-008-L-56-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-09-15 | 2025-11-19 | 16-Jun-25 A | 2026-03-03 | 2310-03-18 10:19 | 2310-03-18 10:19 | 174111.7 | Remaining Total Cost | [20 empty] | 24284.28
|  |  | JDH3-02-008-L-56-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-09-15 | 2025-11-19 | 16-Jun-25 A | 2026-03-03 | 2310-03-18 10:19 | 2310-03-18 10:19 | 174111.7 | Actual Total Cost | [11 empty] | 37493.76 | 39496.27 | 4452.79 | 65727.19 | 2657.42
|  |  | JDH3-02-008-L-56-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-09-17 | 2025-11-22 | 11-Feb-25 A | 2026-03-05 | 2082-11-13 03:36 | 2082-11-13 03:36 | 154896.18 | Planned Total Cost | [14 empty] | 32076.99 |  | 30979.24 |  |  | 13242.66 | 78597.29
|  |  | JDH3-02-008-L-56-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-09-17 | 2025-11-22 | 11-Feb-25 A | 2026-03-05 | 2082-11-13 03:36 | 2082-11-13 03:36 | 154896.18 | Remaining Total Cost | [20 empty] | 88103.03
|  |  | JDH3-02-008-L-56-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-09-17 | 2025-11-22 | 11-Feb-25 A | 2026-03-05 | 2082-11-13 03:36 | 2082-11-13 03:36 | 154896.18 | Actual Total Cost | [7 empty] | 9272 | 752.06 |  |  |  | 22052.93 | 1542.35 | 33008.12 | 165.7
|  |  | JDH3-02-008-L-56-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2025-09-20 | 2025-11-23 | 28-Jan-25 A | 2026-03-03 | 681679.53 | 681679.53 | 776390.28 | Planned Total Cost | [14 empty] | 157112.81 | 493000.34 | 126277.13
|  |  | JDH3-02-008-L-56-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2025-09-20 | 2025-11-23 | 28-Jan-25 A | 2026-03-03 | 681679.53 | 681679.53 | 776390.28 | Remaining Total Cost | [20 empty] | 94710.76
|  |  | JDH3-02-008-L-56-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2025-09-20 | 2025-11-23 | 28-Jan-25 A | 2026-03-03 | 681679.53 | 681679.53 | 776390.28 | Actual Total Cost | [6 empty] | 8869.42 | 208182.9 | 243716.41 | 165352.23 | 17039.85 | 14346.11 | 7173.06 | 7578.33 | 9072.28 | 348.93
|  |  | JDH3-02-008-L-56-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-12-10 | 2025-12-21 | 02-Aug-25 A | 2026-03-05 | 1969-01-08 03:07 | 1969-01-08 03:07 | 28012.37 | Planned Total Cost | [17 empty] | 25211.13 |  |  | 2801.24
|  |  | JDH3-02-008-L-56-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-12-10 | 2025-12-21 | 02-Aug-25 A | 2026-03-05 | 1969-01-08 03:07 | 1969-01-08 03:07 | 28012.37 | Remaining Total Cost | [20 empty] | 2801.24
|  |  | JDH3-02-008-L-56-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-12-10 | 2025-12-21 | 02-Aug-25 A | 2026-03-05 | 1969-01-08 03:07 | 1969-01-08 03:07 | 28012.37 | Actual Total Cost | [13 empty] | 25211.13
|  |  | JDH3-02-008-L-56-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-10-01 | 2025-12-24 | 15-May-25 A | 2026-03-15 | 2118-12-07 20:38 | 2118-12-07 20:24 | 198145.25 | Planned Total Cost | [15 empty] | 77138.64 |  |  |  |  | 121006.61
|  |  | JDH3-02-008-L-56-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-10-01 | 2025-12-24 | 15-May-25 A | 2026-03-15 | 2118-12-07 20:38 | 2118-12-07 20:24 | 198145.25 | Remaining Total Cost | [20 empty] | 118179.39
|  |  | JDH3-02-008-L-56-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-10-01 | 2025-12-24 | 15-May-25 A | 2026-03-15 | 2118-12-07 20:38 | 2118-12-07 20:24 | 198145.25 | Actual Total Cost | [10 empty] | 27466.13 | 49672.5 |  |  | 2625.28 | 201.94
|  |  | JDH3-02-008-L-56-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-10-05 | 2025-12-27 | 15-May-25 A | 2026-03-17 | 2059-04-07 13:41 | 2059-04-07 13:41 | 68438.32 | Planned Total Cost | [15 empty] | 39275.43 | 22319.06 |  |  |  | 6843.83
|  |  | JDH3-02-008-L-56-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-10-05 | 2025-12-27 | 15-May-25 A | 2026-03-17 | 2059-04-07 13:41 | 2059-04-07 13:41 | 68438.32 | Remaining Total Cost | [15 empty] | 3421.92 |  |  |  |  | 6843.83
|  |  | JDH3-02-008-L-56-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-10-05 | 2025-12-27 | 15-May-25 A | 2026-03-17 | 2059-04-07 13:41 | 2059-04-07 13:41 | 68438.32 | Actual Total Cost | [10 empty] | 13832.38 | 22021.13 |  | 22319.06
|  |  | JDH3-02-008-L-56-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-10-07 | 2026-01-25 | 15-May-25 A | 2026-04-12 | 2406-07-28 21:50 | 2406-07-28 22:05 | 305039.37 | Planned Total Cost | [15 empty] | 126016.33 | 148519.1 |  |  |  |  | 30503.94
|  |  | JDH3-02-008-L-56-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-10-07 | 2026-01-25 | 15-May-25 A | 2026-04-12 | 2406-07-28 21:50 | 2406-07-28 22:05 | 305039.37 | Remaining Total Cost | [15 empty] | 89511.52 | [5 empty] | 30503.94
|  |  | JDH3-02-008-L-56-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-10-07 | 2026-01-25 | 15-May-25 A | 2026-04-12 | 2406-07-28 21:50 | 2406-07-28 22:05 | 305039.37 | Actual Total Cost | [10 empty] | 39889.93 | 49809.71 | 21064.73 | 10287.23 | 61602.97 | 2369.35
|  |  | JDH3-02-008-L-56-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-12-13 | 2026-01-21 | 16-Sep-25 A | 2026-04-08 | 1939-09-30 16:48 | 1939-09-30 17:02 | 21509.18 | Planned Total Cost | [19 empty] | 2392.9 | 16965.37 | 2150.92
|  |  | JDH3-02-008-L-56-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-12-13 | 2026-01-21 | 16-Sep-25 A | 2026-04-08 | 1939-09-30 16:48 | 1939-09-30 17:02 | 21509.18 | Remaining Total Cost | [20 empty] | 4839.56 | 2150.92
|  |  | JDH3-02-008-L-56-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-12-13 | 2026-01-21 | 16-Sep-25 A | 2026-04-08 | 1939-09-30 16:48 | 1939-09-30 17:02 | 21509.18 | Actual Total Cost | [14 empty] | 14176.52 | 342.19
|  |  | JDH3-02-008-L-56-(ST)- Single Catchbasine Works |  | 2025-12-15 | 2026-01-13 | 2026-03-01 | 2026-03-31 | 0 | 0 | 168162.82 | Planned Total Cost | [20 empty] | 168162.82
|  |  | JDH3-02-008-L-56-(ST)- Single Catchbasine Works |  | 2025-12-15 | 2026-01-13 | 2026-03-01 | 2026-03-31 | 0 | 0 | 168162.82 | Remaining Total Cost | [20 empty] | 168162.82
|  |  | JDH3-02-008-L-56-(ST)- Single Catchbasine Works |  | 2025-12-15 | 2026-01-13 | 2026-03-01 | 2026-03-31 | 0 | 0 | 168162.82 | Actual Total Cost
|  |  | JDH3-02-008-L-56-(ST)- Double Catchbasine Works |  | 2025-12-21 | 2026-01-19 | 2026-03-07 | 2026-04-06 | 0 | 0 | 443196.68 | Planned Total Cost | [20 empty] | 421731.19 | 21465.49
|  |  | JDH3-02-008-L-56-(ST)- Double Catchbasine Works |  | 2025-12-21 | 2026-01-19 | 2026-03-07 | 2026-04-06 | 0 | 0 | 443196.68 | Remaining Total Cost | [20 empty] | 421731.19 | 21465.49
|  |  | JDH3-02-008-L-56-(ST)- Double Catchbasine Works |  | 2025-12-21 | 2026-01-19 | 2026-03-07 | 2026-04-06 | 0 | 0 | 443196.68 | Actual Total Cost
|  |  | JDH3-02-008-L-56-(ST)-PIPES ENCASEMENT |  | 2025-12-17 | 2025-12-23 | 2026-03-16 | 2026-03-23 | 0 | 0 | 20837 | Planned Total Cost | [20 empty] | 20837
|  |  | JDH3-02-008-L-56-(ST)-PIPES ENCASEMENT |  | 2025-12-17 | 2025-12-23 | 2026-03-16 | 2026-03-23 | 0 | 0 | 20837 | Remaining Total Cost | [20 empty] | 20837
|  |  | JDH3-02-008-L-56-(ST)-PIPES ENCASEMENT |  | 2025-12-17 | 2025-12-23 | 2026-03-16 | 2026-03-23 | 0 | 0 | 20837 | Actual Total Cost
|  |  | JDH3-02-008-L-56-TSE Network - TSE |  | 2025-12-27 | 2026-03-10 | 2026-03-01 | 2026-05-14 | 0 | 0 | 528116.81 | Planned Total Cost | [20 empty] | 213367.45 | 276394.67 | 38354.69
|  |  | JDH3-02-008-L-56-TSE Network - TSE |  | 2025-12-27 | 2026-03-10 | 2026-03-01 | 2026-05-14 | 0 | 0 | 528116.81 | Remaining Total Cost | [20 empty] | 213367.45 | 276394.67 | 38354.69
|  |  | JDH3-02-008-L-56-TSE Network - TSE |  | 2025-12-27 | 2026-03-10 | 2026-03-01 | 2026-05-14 | 0 | 0 | 528116.81 | Actual Total Cost
|  |  | JDH3-02-008-L-56-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-12-27 | 2026-02-23 | 2026-03-01 | 2026-04-29 | 0 | 0 | 49444.02 | Planned Total Cost | [20 empty] | 44499.62 | 4944.4
|  |  | JDH3-02-008-L-56-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-12-27 | 2026-02-23 | 2026-03-01 | 2026-04-29 | 0 | 0 | 49444.02 | Remaining Total Cost | [20 empty] | 44499.62 | 4944.4
|  |  | JDH3-02-008-L-56-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-12-27 | 2026-02-23 | 2026-03-01 | 2026-04-29 | 0 | 0 | 49444.02 | Actual Total Cost
|  |  | JDH3-02-008-L-56-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-12-30 | 2026-03-10 | 2026-03-04 | 2026-05-14 | 0 | 0 | 390709.93 | Planned Total Cost | [20 empty] | 148057.36 | 204297.88 | 38354.69
|  |  | JDH3-02-008-L-56-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-12-30 | 2026-03-10 | 2026-03-04 | 2026-05-14 | 0 | 0 | 390709.93 | Remaining Total Cost | [20 empty] | 148057.36 | 204297.88 | 38354.69
|  |  | JDH3-02-008-L-56-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2025-12-30 | 2026-03-10 | 2026-03-04 | 2026-05-14 | 0 | 0 | 390709.93 | Actual Total Cost
|  |  | JDH3-02-008-L-56-(TSE)-Supply and install gate valves-100 mm |  | 2026-02-11 | 2026-02-19 | 2026-04-16 | 2026-04-26 | 0 | 0 | 16811.08 | Planned Total Cost | [21 empty] | 16811.08
|  |  | JDH3-02-008-L-56-(TSE)-Supply and install gate valves-100 mm |  | 2026-02-11 | 2026-02-19 | 2026-04-16 | 2026-04-26 | 0 | 0 | 16811.08 | Remaining Total Cost | [21 empty] | 16811.08
|  |  | JDH3-02-008-L-56-(TSE)-Supply and install gate valves-100 mm |  | 2026-02-11 | 2026-02-19 | 2026-04-16 | 2026-04-26 | 0 | 0 | 16811.08 | Actual Total Cost
|  |  | JDH3-02-008-L-56-(TSE)-Supply and install gate valves-250 mm |  | 2026-02-11 | 2026-02-17 | 2026-04-16 | 2026-04-23 | 0 | 0 | 25661.13 | Planned Total Cost | [21 empty] | 25661.13
|  |  | JDH3-02-008-L-56-(TSE)-Supply and install gate valves-250 mm |  | 2026-02-11 | 2026-02-17 | 2026-04-16 | 2026-04-23 | 0 | 0 | 25661.13 | Remaining Total Cost | [21 empty] | 25661.13
|  |  | JDH3-02-008-L-56-(TSE)-Supply and install gate valves-250 mm |  | 2026-02-11 | 2026-02-17 | 2026-04-16 | 2026-04-23 | 0 | 0 | 25661.13 | Actual Total Cost
|  |  | JDH3-02-008-L-56-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-02-11 | 2026-02-15 | 2026-04-16 | 2026-04-21 | 0 | 0 | 9791.9 | Planned Total Cost | [21 empty] | 9791.9
|  |  | JDH3-02-008-L-56-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-02-11 | 2026-02-15 | 2026-04-16 | 2026-04-21 | 0 | 0 | 9791.9 | Remaining Total Cost | [21 empty] | 9791.9
|  |  | JDH3-02-008-L-56-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2026-02-11 | 2026-02-15 | 2026-04-16 | 2026-04-21 | 0 | 0 | 9791.9 | Actual Total Cost
|  |  | JDH3-02-008-L-56-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-02-11 | 2026-02-15 | 2026-04-16 | 2026-04-21 | 0 | 0 | 14888.27 | Planned Total Cost | [21 empty] | 14888.27
|  |  | JDH3-02-008-L-56-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-02-11 | 2026-02-15 | 2026-04-16 | 2026-04-21 | 0 | 0 | 14888.27 | Remaining Total Cost | [21 empty] | 14888.27
|  |  | JDH3-02-008-L-56-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-02-11 | 2026-02-15 | 2026-04-16 | 2026-04-21 | 0 | 0 | 14888.27 | Actual Total Cost
|  |  | JDH3-02-008-L-56-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-01-10 | 2026-01-18 | 2026-03-15 | 2026-03-24 | 0 | 0 | 13851.92 | Planned Total Cost | [20 empty] | 13851.92
|  |  | JDH3-02-008-L-56-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-01-10 | 2026-01-18 | 2026-03-15 | 2026-03-24 | 0 | 0 | 13851.92 | Remaining Total Cost | [20 empty] | 13851.92
|  |  | JDH3-02-008-L-56-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2026-01-10 | 2026-01-18 | 2026-03-15 | 2026-03-24 | 0 | 0 | 13851.92 | Actual Total Cost
|  |  | JDH3-02-008-L-56-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-01-12 | 2026-01-20 | 2026-03-17 | 2026-03-26 | 0 | 0 | 6958.55 | Planned Total Cost | [20 empty] | 6958.55
|  |  | JDH3-02-008-L-56-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-01-12 | 2026-01-20 | 2026-03-17 | 2026-03-26 | 0 | 0 | 6958.55 | Remaining Total Cost | [20 empty] | 6958.55
|  |  | JDH3-02-008-L-56-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-01-12 | 2026-01-20 | 2026-03-17 | 2026-03-26 | 0 | 0 | 6958.55 | Actual Total Cost
|  |  | JDH3-02-008-L-56-Potable Water Network - WT |  | 2026-03-11 | 2026-03-22 | 2026-05-14 | 2026-05-26 | 0 | 0 | 39127.27 | Planned Total Cost | [22 empty] | 39127.27
|  |  | JDH3-02-008-L-56-Potable Water Network - WT |  | 2026-03-11 | 2026-03-22 | 2026-05-14 | 2026-05-26 | 0 | 0 | 39127.27 | Remaining Total Cost | [22 empty] | 39127.27
|  |  | JDH3-02-008-L-56-Potable Water Network - WT |  | 2026-03-11 | 2026-03-22 | 2026-05-14 | 2026-05-26 | 0 | 0 | 39127.27 | Actual Total Cost
|  |  | JDH3-02-008-L-56-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-03-11 | 2026-03-22 | 2026-05-14 | 2026-05-26 | 0 | 0 | 2853.66 | Planned Total Cost | [22 empty] | 2853.66
|  |  | JDH3-02-008-L-56-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-03-11 | 2026-03-22 | 2026-05-14 | 2026-05-26 | 0 | 0 | 2853.66 | Remaining Total Cost | [22 empty] | 2853.66
|  |  | JDH3-02-008-L-56-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-03-11 | 2026-03-22 | 2026-05-14 | 2026-05-26 | 0 | 0 | 2853.66 | Actual Total Cost
|  |  | JDH3-02-008-L-56-(WT)- Supply and install 3-out fire hydrant |  | 2026-03-14 | 2026-03-19 | 2026-05-17 | 2026-05-24 | 0 | 0 | 36273.61 | Planned Total Cost | [22 empty] | 36273.61
|  |  | JDH3-02-008-L-56-(WT)- Supply and install 3-out fire hydrant |  | 2026-03-14 | 2026-03-19 | 2026-05-17 | 2026-05-24 | 0 | 0 | 36273.61 | Remaining Total Cost | [22 empty] | 36273.61
|  |  | JDH3-02-008-L-56-(WT)- Supply and install 3-out fire hydrant |  | 2026-03-14 | 2026-03-19 | 2026-05-17 | 2026-05-24 | 0 | 0 | 36273.61 | Actual Total Cost
|  |  | L-57 |  | 2025-09-03 | 2026-04-14 | 03-Nov-24 A | 2026-01-01 | 2459201.19 | 2459201.19 | 5183624.7 | Planned Total Cost | [14 empty] | 950539.65 | 2002870.17 | 1203920.01 | 503745.01 | 18853.09 | 485882.34 | 17814.43
|  |  | L-57 |  | 2025-09-03 | 2026-04-14 | 03-Nov-24 A | 2026-01-01 | 2459201.19 | 2459201.19 | 5183624.7 | Remaining Total Cost | [15 empty] | 1894131.29 | 671028.2 | 159260.04 | 3.99
|  |  | L-57 |  | 2025-09-03 | 2026-04-14 | 03-Nov-24 A | 2026-01-01 | 2459201.19 | 2459201.19 | 5183624.7 | Actual Total Cost |  |  |  |  | 4969.91 | 44729.17 | 3313.27 |  |  | 35992.74 | 14847.03 | 216157.5 | 183442.31 | 710099.67 | 1194671.26 | 50978.32
|  |  | JDH3-02-008-L-57-Storm Network - ST |  | 2025-09-11 | 2026-03-11 | 27-Nov-24 A | 2025-11-29 | 2459201.19 | 2459201.19 | 5004968.65 | Planned Total Cost | [14 empty] | 950539.65 | 2002870.17 | 1184527.99 | 344484.97 | 18849.11 | 485882.34 | 17814.43
|  |  | JDH3-02-008-L-57-Storm Network - ST |  | 2025-09-11 | 2026-03-11 | 27-Nov-24 A | 2025-11-29 | 2459201.19 | 2459201.19 | 5004968.65 | Remaining Total Cost | [15 empty] | 1894131.29 | 651636.18
|  |  | JDH3-02-008-L-57-Storm Network - ST |  | 2025-09-11 | 2026-03-11 | 27-Nov-24 A | 2025-11-29 | 2459201.19 | 2459201.19 | 5004968.65 | Actual Total Cost |  |  |  |  | 4969.91 | 44729.17 | 3313.27 |  |  | 35992.74 | 14847.03 | 216157.5 | 183442.31 | 710099.67 | 1194671.26 | 50978.32
|  |  | JDH3-02-008-L-57-(ST)-Box Culvert |  | 2025-09-11 | 2026-02-04 | 27-Nov-24 A | 2025-11-01 | 1763341.36 | 1763341.37 | 3230972.32 | Planned Total Cost | [14 empty] | 729188.98 | 1618104.58 | 539193.79 | 344484.97
|  |  | JDH3-02-008-L-57-(ST)-Box Culvert |  | 2025-09-11 | 2026-02-04 | 27-Nov-24 A | 2025-11-01 | 1763341.36 | 1763341.37 | 3230972.32 | Remaining Total Cost | [15 empty] | 1466826.63 | 804.34
|  |  | JDH3-02-008-L-57-(ST)-Box Culvert |  | 2025-09-11 | 2026-02-04 | 27-Nov-24 A | 2025-11-01 | 1763341.36 | 1763341.37 | 3230972.32 | Actual Total Cost |  |  |  |  | 4969.91 | 44729.17 | 3313.27 |  |  |  | 13345.41 | 94622.68 | 133633.99 | 334289.93 | 1086579.4 | 47857.62
|  |  | JDH3-02-008-L-57-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2025-09-11 | 2025-10-26 | 27-Nov-24 A | 19-Aug-25 A | 353415.67 | 353415.66 | 353415.67 | Planned Total Cost | [14 empty] | 212079.82 | 141335.85
|  |  | JDH3-02-008-L-57-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2025-09-11 | 2025-10-26 | 27-Nov-24 A | 19-Aug-25 A | 353415.67 | 353415.66 | 353415.67 | Remaining Total Cost
|  |  | JDH3-02-008-L-57-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 1.51 to 2.50 |  | 2025-09-11 | 2025-10-26 | 27-Nov-24 A | 19-Aug-25 A | 353415.67 | 353415.66 | 353415.67 | Actual Total Cost |  |  |  |  | 4969.91 | 44729.17 | 3313.27 |  |  |  | 13345.41 | 94622.68 | 133633.99 | 58801.23
|  |  | JDH3-02-008-L-57-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2025-10-27 | 2025-12-03 | 20-Aug-25 A | 2025-11-01 | 2275-04-16 07:26 | 2275-04-16 07:41 | 344717.1 | Planned Total Cost | [14 empty] | 120650.99 | 223261.78 | 804.34
|  |  | JDH3-02-008-L-57-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2025-10-27 | 2025-12-03 | 20-Aug-25 A | 2025-11-01 | 2275-04-16 07:26 | 2275-04-16 07:41 | 344717.1 | Remaining Total Cost | [15 empty] | 206839.45 | 804.34
|  |  | JDH3-02-008-L-57-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2025-10-27 | 2025-12-03 | 20-Aug-25 A | 2025-11-01 | 2275-04-16 07:26 | 2275-04-16 07:41 | 344717.1 | Actual Total Cost | [13 empty] | 24652.5 | 109695.63 | 2725.2
|  |  | JDH3-02-008-L-57-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2025-10-29 | 2025-12-07 | 02-Aug-25 A | 18-Sep-25 A | 370340.39 | 370340.4 | 370340.39 | Planned Total Cost | [15 empty] | 55551.06 | 259238.27 | 55551.06
|  |  | JDH3-02-008-L-57-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2025-10-29 | 2025-12-07 | 02-Aug-25 A | 18-Sep-25 A | 370340.39 | 370340.4 | 370340.39 | Remaining Total Cost
|  |  | JDH3-02-008-L-57-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2025-10-29 | 2025-12-07 | 02-Aug-25 A | 18-Sep-25 A | 370340.39 | 370340.4 | 370340.39 | Actual Total Cost | [13 empty] | 250836.2 | 119504.2
|  |  | JDH3-02-008-L-57-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2025-11-01 | 2026-02-04 | 03-Sep-25 A | 2025-10-29 | 902511.99 | 902511.99 | 2162499.16 | Planned Total Cost | [14 empty] | 396458.18 | 1197955.89 | 279151.18 | 288933.92
|  |  | JDH3-02-008-L-57-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2025-11-01 | 2026-02-04 | 03-Sep-25 A | 2025-10-29 | 902511.99 | 902511.99 | 2162499.16 | Remaining Total Cost | [15 empty] | 1259987.17
|  |  | JDH3-02-008-L-57-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2025-11-01 | 2026-02-04 | 03-Sep-25 A | 2025-10-29 | 902511.99 | 902511.99 | 2162499.16 | Actual Total Cost | [14 empty] | 857379.57 | 45132.42
|  |  | JDH3-02-008-L-57-(ST)-NetWork |  | 2025-09-11 | 2026-03-11 | 05-Apr-25 A | 2025-11-29 | 695859.83 | 695859.82 | 1773996.33 | Planned Total Cost | [14 empty] | 221350.67 | 384765.59 | 645334.2 |  | 18849.11 | 485882.34 | 17814.43
|  |  | JDH3-02-008-L-57-(ST)-NetWork |  | 2025-09-11 | 2026-03-11 | 05-Apr-25 A | 2025-11-29 | 695859.83 | 695859.82 | 1773996.33 | Remaining Total Cost | [15 empty] | 427304.67 | 650831.84
|  |  | JDH3-02-008-L-57-(ST)-NetWork |  | 2025-09-11 | 2026-03-11 | 05-Apr-25 A | 2025-11-29 | 695859.83 | 695859.82 | 1773996.33 | Actual Total Cost | [9 empty] | 35992.74 | 1501.62 | 121534.82 | 49808.32 | 375809.75 | 108091.86 | 3120.71
|  |  | JDH3-02-008-L-57-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-02-05 | 2026-03-02 | 2025-10-29 | 2025-11-24 | 0 | 0 | 247740.72 | Planned Total Cost | [15 empty] | 32261.35 | 215479.38
|  |  | JDH3-02-008-L-57-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-02-05 | 2026-03-02 | 2025-10-29 | 2025-11-24 | 0 | 0 | 247740.72 | Remaining Total Cost | [15 empty] | 32261.35 | 215479.38
|  |  | JDH3-02-008-L-57-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-02-05 | 2026-03-02 | 2025-10-29 | 2025-11-24 | 0 | 0 | 247740.72 | Actual Total Cost
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2026-02-09 | 2026-02-26 | 2025-11-02 | 2025-11-20 | 0 | 0 | 46009.58 | Planned Total Cost | [16 empty] | 46009.58
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2026-02-09 | 2026-02-26 | 2025-11-02 | 2025-11-20 | 0 | 0 | 46009.58 | Remaining Total Cost | [16 empty] | 46009.58
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2026-02-09 | 2026-02-26 | 2025-11-02 | 2025-11-20 | 0 | 0 | 46009.58 | Actual Total Cost
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-09-11 | 2026-02-26 | 09-Jun-25 A | 2025-11-20 | 1964-08-08 06:00 | 1964-08-08 06:00 | 78118.03 | Planned Total Cost | [14 empty] | 23597.25 |  | 54520.78
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-09-11 | 2026-02-26 | 09-Jun-25 A | 2025-11-20 | 1964-08-08 06:00 | 1964-08-08 06:00 | 78118.03 | Remaining Total Cost | [16 empty] | 54520.78
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-09-11 | 2026-02-26 | 09-Jun-25 A | 2025-11-20 | 1964-08-08 06:00 | 1964-08-08 06:00 | 78118.03 | Actual Total Cost | [11 empty] | 13271.96 | 10325.29
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2025-09-11 | 2026-03-01 | 05-Apr-25 A | 2025-11-23 | 2002-08-26 08:24 | 2002-08-26 08:38 | 38642.35 | Planned Total Cost | [14 empty] | 37494.35 |  | 1148
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2025-09-11 | 2026-03-01 | 05-Apr-25 A | 2025-11-23 | 2002-08-26 08:24 | 2002-08-26 08:38 | 38642.35 | Remaining Total Cost | [16 empty] | 1148
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2025-09-11 | 2026-03-01 | 05-Apr-25 A | 2025-11-23 | 2002-08-26 08:24 | 2002-08-26 08:38 | 38642.35 | Actual Total Cost | [9 empty] | 35992.74 | 1501.62
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-09-11 | 2026-03-05 | 09-Jun-25 A | 2025-11-18 | 1996-06-07 05:46 | 1996-06-07 05:31 | 37867.12 | Planned Total Cost | [14 empty] | 30293.69 | [5 empty] | 7573.42
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-09-11 | 2026-03-05 | 09-Jun-25 A | 2025-11-18 | 1996-06-07 05:46 | 1996-06-07 05:31 | 37867.12 | Remaining Total Cost | [16 empty] | 2643.88
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-09-11 | 2026-03-05 | 09-Jun-25 A | 2025-11-18 | 1996-06-07 05:46 | 1996-06-07 05:31 | 37867.12 | Actual Total Cost | [11 empty] | 20945.25 | 9348.44 | 3900.99 | 990.45 | 38.09
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-09-11 | 2026-03-08 | 09-Jun-25 A | 2025-10-04 | 2030-04-13 21:07 | 2030-04-13 20:53 | 51205.02 | Planned Total Cost | [14 empty] | 40964.02 | [5 empty] | 10241
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-09-11 | 2026-03-08 | 09-Jun-25 A | 2025-10-04 | 2030-04-13 21:07 | 2030-04-13 20:53 | 51205.02 | Remaining Total Cost | [15 empty] | 3618.14
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-09-11 | 2026-03-08 | 09-Jun-25 A | 2025-10-04 | 2030-04-13 21:07 | 2030-04-13 20:53 | 51205.02 | Actual Total Cost | [11 empty] | 28322.77 | 12641.24 | 5174.16 | 1395.05 | 53.66
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-09-16 | 2026-02-25 | 09-Jun-25 A | 2025-10-04 | 2164-12-03 18:58 | 2164-12-03 18:58 | 104005.71 | Planned Total Cost | [14 empty] | 41625.35 |  |  |  |  | 62380.36
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-09-16 | 2026-02-25 | 09-Jun-25 A | 2025-10-04 | 2164-12-03 18:58 | 2164-12-03 18:58 | 104005.71 | Remaining Total Cost | [15 empty] | 7241.92
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-09-16 | 2026-02-25 | 09-Jun-25 A | 2025-10-04 | 2164-12-03 18:58 | 2164-12-03 18:58 | 104005.71 | Actual Total Cost | [11 empty] | 28781.5 | 12843.85 | 52092.6 | 2933.03 | 112.81
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 2.51 to 3.50 m |  | 2026-02-11 | 2026-02-23 | 2025-11-04 | 2025-11-17 | 0 | 0 | 28123.59 | Planned Total Cost | [16 empty] | 28123.59
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 2.51 to 3.50 m |  | 2026-02-11 | 2026-02-23 | 2025-11-04 | 2025-11-17 | 0 | 0 | 28123.59 | Remaining Total Cost | [16 empty] | 28123.59
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 2.51 to 3.50 m |  | 2026-02-11 | 2026-02-23 | 2025-11-04 | 2025-11-17 | 0 | 0 | 28123.59 | Actual Total Cost
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-02-14 | 2026-02-25 | 09-Aug-25 A | 2025-11-17 | 2408-04-02 08:10 | 2408-04-02 07:55 | 188491.09 | Planned Total Cost | [14 empty] | 18849.11 |  |  |  | 18849.11 | 150792.87
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-02-14 | 2026-02-25 | 09-Aug-25 A | 2025-11-17 | 2408-04-02 08:10 | 2408-04-02 07:55 | 188491.09 | Remaining Total Cost | [16 empty] | 2853.76
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-02-14 | 2026-02-25 | 09-Aug-25 A | 2025-11-17 | 2408-04-02 08:10 | 2408-04-02 07:55 | 188491.09 | Actual Total Cost | [13 empty] | 150792.87 | 34002.6 | 841.86
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2026-02-16 | 2026-02-28 | 12-Aug-25 A | 2025-11-19 | 2265-08-26 00:58 | 2265-08-26 00:58 | 148392.27 | Planned Total Cost | [14 empty] | 14839.23 |  | 14839.23 |  |  | 118713.82
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2026-02-16 | 2026-02-28 | 12-Aug-25 A | 2025-11-19 | 2265-08-26 00:58 | 2265-08-26 00:58 | 148392.27 | Remaining Total Cost | [16 empty] | 14839.23
|  |  | JDH3-02-008-L-57-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2026-02-16 | 2026-02-28 | 12-Aug-25 A | 2025-11-19 | 2265-08-26 00:58 | 2265-08-26 00:58 | 148392.27 | Actual Total Cost | [13 empty] | 118713.81 | 14839.23
|  |  | JDH3-02-008-L-57-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-10-06 | 2026-03-01 | 01-Jun-25 A | 2025-10-11 | 1970-01-30 07:12 | 1970-01-30 07:12 | 52143.49 | Planned Total Cost | [15 empty] | 35709.21 |  |  |  | 16434.28
|  |  | JDH3-02-008-L-57-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-10-06 | 2026-03-01 | 01-Jun-25 A | 2025-10-11 | 1970-01-30 07:12 | 1970-01-30 07:12 | 52143.49 | Remaining Total Cost | [15 empty] | 26545.19
|  |  | JDH3-02-008-L-57-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-10-06 | 2026-03-01 | 01-Jun-25 A | 2025-10-11 | 1970-01-30 07:12 | 1970-01-30 07:12 | 52143.49 | Actual Total Cost | [11 empty] | 17381.16 |  | 2934.69 | 5086.8 | 195.65
|  |  | JDH3-02-008-L-57-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-09-11 | 2026-03-03 | 09-Jun-25 A | 2025-10-09 | 1963-09-15 00:43 | 1963-09-15 00:43 | 27375.33 | Planned Total Cost | [14 empty] | 13687.66 | 4106.3 |  |  |  | 9581.37
|  |  | JDH3-02-008-L-57-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-09-11 | 2026-03-03 | 09-Jun-25 A | 2025-10-09 | 1963-09-15 00:43 | 1963-09-15 00:43 | 27375.33 | Remaining Total Cost | [15 empty] | 4106.3
|  |  | JDH3-02-008-L-57-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-09-11 | 2026-03-03 | 09-Jun-25 A | 2025-10-09 | 1963-09-15 00:43 | 1963-09-15 00:43 | 27375.33 | Actual Total Cost | [11 empty] | 12832.18 | 855.48 | 9581.37
|  |  | JDH3-02-008-L-57-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-10-08 | 2026-03-01 | 15-Jul-25 A | 2025-11-23 | 1910-05-21 00:29 | 1910-05-21 00:29 | 237252.84 | Planned Total Cost | [15 empty] | 3794.02 | 233458.83
|  |  | JDH3-02-008-L-57-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-10-08 | 2026-03-01 | 15-Jul-25 A | 2025-11-23 | 1910-05-21 00:29 | 1910-05-21 00:29 | 237252.84 | Remaining Total Cost | [16 empty] | 233458.83
|  |  | JDH3-02-008-L-57-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-10-08 | 2026-03-01 | 15-Jul-25 A | 2025-11-23 | 1910-05-21 00:29 | 1910-05-21 00:29 | 237252.84 | Actual Total Cost | [12 empty] | 3794.02
|  |  | JDH3-02-008-L-57-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-02-18 | 2026-03-02 | 09-Aug-25 A | 2025-11-22 | 2128-03-06 14:24 | 2128-03-06 14:24 | 150564.29 | Planned Total Cost | [15 empty] | 7528.21 | 15056.43 |  |  | 127979.65
|  |  | JDH3-02-008-L-57-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-02-18 | 2026-03-02 | 09-Aug-25 A | 2025-11-22 | 2128-03-06 14:24 | 2128-03-06 14:24 | 150564.29 | Remaining Total Cost | [15 empty] | 52165.26 | 15056.43
|  |  | JDH3-02-008-L-57-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-02-18 | 2026-03-02 | 09-Aug-25 A | 2025-11-22 | 2128-03-06 14:24 | 2128-03-06 14:24 | 150564.29 | Actual Total Cost | [13 empty] | 32619.26 | 48844.7 | 1878.64
|  |  | JDH3-02-008-L-57-(ST)- Single Catchbasine Works |  | 2026-02-21 | 2026-03-08 | 2025-10-02 | 2025-11-25 | 0 | 0 | 89947.55 | Planned Total Cost | [15 empty] | 85450.18 | 4497.38
|  |  | JDH3-02-008-L-57-(ST)- Single Catchbasine Works |  | 2026-02-21 | 2026-03-08 | 2025-10-02 | 2025-11-25 | 0 | 0 | 89947.55 | Remaining Total Cost | [15 empty] | 85450.18 | 4497.38
|  |  | JDH3-02-008-L-57-(ST)- Single Catchbasine Works |  | 2026-02-21 | 2026-03-08 | 2025-10-02 | 2025-11-25 | 0 | 0 | 89947.55 | Actual Total Cost
|  |  | JDH3-02-008-L-57-(ST)- Double Catchbasine Works |  | 2026-02-24 | 2026-03-11 | 2025-10-06 | 2025-11-29 | 0 | 0 | 227280.35 | Planned Total Cost | [15 empty] | 215916.33 | 11364.02
|  |  | JDH3-02-008-L-57-(ST)- Double Catchbasine Works |  | 2026-02-24 | 2026-03-11 | 2025-10-06 | 2025-11-29 | 0 | 0 | 227280.35 | Remaining Total Cost | [15 empty] | 215916.33 | 11364.02
|  |  | JDH3-02-008-L-57-(ST)- Double Catchbasine Works |  | 2026-02-24 | 2026-03-11 | 2025-10-06 | 2025-11-29 | 0 | 0 | 227280.35 | Actual Total Cost
|  |  | JDH3-02-008-L-57-(ST)-PIPES ENCASEMENT |  | 2026-02-18 | 2026-02-24 | 2025-11-11 | 2025-11-18 | 0 | 0 | 20837 | Planned Total Cost | [16 empty] | 20837
|  |  | JDH3-02-008-L-57-(ST)-PIPES ENCASEMENT |  | 2026-02-18 | 2026-02-24 | 2025-11-11 | 2025-11-18 | 0 | 0 | 20837 | Remaining Total Cost | [16 empty] | 20837
|  |  | JDH3-02-008-L-57-(ST)-PIPES ENCASEMENT |  | 2026-02-18 | 2026-02-24 | 2025-11-11 | 2025-11-18 | 0 | 0 | 20837 | Actual Total Cost
|  |  | JDH3-02-008-L-57-TSE Network - TSE |  | 2026-03-12 | 2026-04-02 | 2025-11-29 | 2025-12-21 | 0 | 0 | 149742.69 | Planned Total Cost | [16 empty] | 19392.02 | 130350.67
|  |  | JDH3-02-008-L-57-TSE Network - TSE |  | 2026-03-12 | 2026-04-02 | 2025-11-29 | 2025-12-21 | 0 | 0 | 149742.69 | Remaining Total Cost | [16 empty] | 19392.02 | 130350.67
|  |  | JDH3-02-008-L-57-TSE Network - TSE |  | 2026-03-12 | 2026-04-02 | 2025-11-29 | 2025-12-21 | 0 | 0 | 149742.69 | Actual Total Cost
|  |  | JDH3-02-008-L-57-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-03-12 | 2026-03-31 | 2025-11-29 | 2025-12-18 | 0 | 0 | 18994.49 | Planned Total Cost | [16 empty] | 3710.26 | 15284.24
|  |  | JDH3-02-008-L-57-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-03-12 | 2026-03-31 | 2025-11-29 | 2025-12-18 | 0 | 0 | 18994.49 | Remaining Total Cost | [16 empty] | 3710.26 | 15284.24
|  |  | JDH3-02-008-L-57-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-03-12 | 2026-03-31 | 2025-11-29 | 2025-12-18 | 0 | 0 | 18994.49 | Actual Total Cost
|  |  | JDH3-02-008-L-57-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-03-12 | 2026-04-02 | 2025-11-29 | 2025-12-21 | 0 | 0 | 120423.12 | Planned Total Cost | [16 empty] | 15681.77 | 104741.36
|  |  | JDH3-02-008-L-57-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-03-12 | 2026-04-02 | 2025-11-29 | 2025-12-21 | 0 | 0 | 120423.12 | Remaining Total Cost | [16 empty] | 15681.77 | 104741.36
|  |  | JDH3-02-008-L-57-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-03-12 | 2026-04-02 | 2025-11-29 | 2025-12-21 | 0 | 0 | 120423.12 | Actual Total Cost
|  |  | JDH3-02-008-L-57-(TSE)-Supply and install gate valves-100 mm |  | 2026-03-25 | 2026-03-29 | 2025-12-11 | 2025-12-16 | 0 | 0 | 7758.96 | Planned Total Cost | [17 empty] | 7758.96
|  |  | JDH3-02-008-L-57-(TSE)-Supply and install gate valves-100 mm |  | 2026-03-25 | 2026-03-29 | 2025-12-11 | 2025-12-16 | 0 | 0 | 7758.96 | Remaining Total Cost | [17 empty] | 7758.96
|  |  | JDH3-02-008-L-57-(TSE)-Supply and install gate valves-100 mm |  | 2026-03-25 | 2026-03-29 | 2025-12-11 | 2025-12-16 | 0 | 0 | 7758.96 | Actual Total Cost
|  |  | JDH3-02-008-L-57-(TSE)-Supply and install gate valves-250 mm |  | 2026-03-25 | 2026-03-29 | 2025-12-11 | 2025-12-16 | 0 | 0 | 2566.11 | Planned Total Cost | [17 empty] | 2566.11
|  |  | JDH3-02-008-L-57-(TSE)-Supply and install gate valves-250 mm |  | 2026-03-25 | 2026-03-29 | 2025-12-11 | 2025-12-16 | 0 | 0 | 2566.11 | Remaining Total Cost | [17 empty] | 2566.11
|  |  | JDH3-02-008-L-57-(TSE)-Supply and install gate valves-250 mm |  | 2026-03-25 | 2026-03-29 | 2025-12-11 | 2025-12-16 | 0 | 0 | 2566.11 | Actual Total Cost
|  |  | JDH3-02-008-L-57-Potable Water Network - WT |  | 2026-04-04 | 2026-04-14 | 2025-12-21 | 2026-01-01 | 0 | 0 | 28913.35 | Planned Total Cost | [17 empty] | 28909.37 | 3.99
|  |  | JDH3-02-008-L-57-Potable Water Network - WT |  | 2026-04-04 | 2026-04-14 | 2025-12-21 | 2026-01-01 | 0 | 0 | 28913.35 | Remaining Total Cost | [17 empty] | 28909.37 | 3.99
|  |  | JDH3-02-008-L-57-Potable Water Network - WT |  | 2026-04-04 | 2026-04-14 | 2025-12-21 | 2026-01-01 | 0 | 0 | 28913.35 | Actual Total Cost
|  |  | JDH3-02-008-L-57-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-04-04 | 2026-04-14 | 2025-12-21 | 2026-01-01 | 0 | 0 | 1708.15 | Planned Total Cost | [17 empty] | 1704.16 | 3.99
|  |  | JDH3-02-008-L-57-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-04-04 | 2026-04-14 | 2025-12-21 | 2026-01-01 | 0 | 0 | 1708.15 | Remaining Total Cost | [17 empty] | 1704.16 | 3.99
|  |  | JDH3-02-008-L-57-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-04-04 | 2026-04-14 | 2025-12-21 | 2026-01-01 | 0 | 0 | 1708.15 | Actual Total Cost
|  |  | JDH3-02-008-L-57-(WT)- Supply and install 3-out fire hydrant |  | 2026-04-04 | 2026-04-09 | 2025-12-21 | 2025-12-28 | 0 | 0 | 27205.21 | Planned Total Cost | [17 empty] | 27205.21
|  |  | JDH3-02-008-L-57-(WT)- Supply and install 3-out fire hydrant |  | 2026-04-04 | 2026-04-09 | 2025-12-21 | 2025-12-28 | 0 | 0 | 27205.21 | Remaining Total Cost | [17 empty] | 27205.21
|  |  | JDH3-02-008-L-57-(WT)- Supply and install 3-out fire hydrant |  | 2026-04-04 | 2026-04-09 | 2025-12-21 | 2025-12-28 | 0 | 0 | 27205.21 | Actual Total Cost
|  |  | Z07 |  | 2024-10-14 | 2026-01-28 | 02-Nov-24 A | 2026-06-27 | 5511569.17 | 5511569.22 | 19046811.66 | Planned Total Cost | [5 empty] | 2063009.02 | 1153169.34 | 1679669.17 | 477703.6 | 142266.22 | 116231.56 |  |  |  | 23953.34 | 3620938.96 | 4937301.21 | 1366011.02 | 268989.31 | 766097 | 1087314.45 | 592002.45 | 243317.5 | 508837.51
|  |  | Z07 |  | 2024-10-14 | 2026-01-28 | 02-Nov-24 A | 2026-06-27 | 5511569.17 | 5511569.22 | 19046811.66 | Remaining Total Cost | [15 empty] | 3902626 | 4798008.94 | 1368049.33 | 268989.31 | 766097 | 1087314.45 | 592002.45 | 243317.5 | 508837.51
|  |  | Z07 |  | 2024-10-14 | 2026-01-28 | 02-Nov-24 A | 2026-06-27 | 5511569.17 | 5511569.22 | 19046811.66 | Actual Total Cost |  |  |  |  | 12165.13 | 215809.88 | 304151.33 | 406623.88 | 569001.01 | 693275.49 | 617961.7 | 264670.22 | 494322.57 | 1304343.5 | 599310.39 | 29934.12
|  |  | C-04 |  | 2025-01-22 | 2026-01-28 | 17-Dec-24 A | 2026-06-27 | 930179.6 | 930179.61 | 7941441.97 | Planned Total Cost | [6 empty] | 20686.94 | 448951.8 | 375167.01 | 142266.22 | 116231.56 |  |  |  | 23953.34 | 409678.65 | 2054890.49 | 944802.1 | 268604.78 | 704737.17 | 1087314.45 | 592002.45 | 243317.5 | 508837.51
|  |  | C-04 |  | 2025-01-22 | 2026-01-28 | 17-Dec-24 A | 2026-06-27 | 930179.6 | 930179.61 | 7941441.97 | Remaining Total Cost | [15 empty] | 606755.91 | 2054890.49 | 944802.1 | 268604.78 | 704737.17 | 1087314.45 | 592002.45 | 243317.5 | 508837.51
|  |  | C-04 |  | 2025-01-22 | 2026-01-28 | 17-Dec-24 A | 2026-06-27 | 930179.6 | 930179.61 | 7941441.97 | Actual Total Cost | [6 empty] | 38489.01 | 78600.97 | 88606.28 | 86127.58 | 109788.24 | 59290.5 | 43902.67 | 164381.98 | 253474.73 | 7517.66
|  |  | JDH3-02-008-C-04-Storm Network - ST |  | 2025-01-30 | 2026-01-08 | 05-Jan-25 A | 2026-06-07 | 930179.6 | 930179.61 | 7696612.29 | Planned Total Cost | [6 empty] | 20686.94 | 448951.8 | 375167.01 | 142266.22 | 116231.56 |  |  |  | 23953.34 | 409678.65 | 2054890.49 | 944802.1 | 268604.78 | 704737.17 | 1087314.45 | 592002.45 | 243317.5 | 264007.84
|  |  | JDH3-02-008-C-04-Storm Network - ST |  | 2025-01-30 | 2026-01-08 | 05-Jan-25 A | 2026-06-07 | 930179.6 | 930179.61 | 7696612.29 | Remaining Total Cost | [15 empty] | 606755.91 | 2054890.49 | 944802.1 | 268604.78 | 704737.17 | 1087314.45 | 592002.45 | 243317.5 | 264007.84
|  |  | JDH3-02-008-C-04-Storm Network - ST |  | 2025-01-30 | 2026-01-08 | 05-Jan-25 A | 2026-06-07 | 930179.6 | 930179.61 | 7696612.29 | Actual Total Cost | [6 empty] | 38489.01 | 78600.97 | 88606.28 | 86127.58 | 109788.24 | 59290.5 | 43902.67 | 164381.98 | 253474.73 | 7517.66
|  |  | JDH3-02-008-C-04-(ST)-Swales |  | 2025-01-30 | 2025-02-09 | 13-Sep-25 A | 21-Sep-25 A | 2058-11-01 16:19 | 2058-11-01 16:19 | 58015.68 | Planned Total Cost | [14 empty] | 23953.34 | 34062.34
|  |  | JDH3-02-008-C-04-(ST)-Swales |  | 2025-01-30 | 2025-02-09 | 13-Sep-25 A | 21-Sep-25 A | 2058-11-01 16:19 | 2058-11-01 16:19 | 58015.68 | Remaining Total Cost
|  |  | JDH3-02-008-C-04-(ST)-Swales |  | 2025-01-30 | 2025-02-09 | 13-Sep-25 A | 21-Sep-25 A | 2058-11-01 16:19 | 2058-11-01 16:19 | 58015.68 | Actual Total Cost | [14 empty] | 58015.68
|  |  | JDH3-02-008-C-04-(ST)-Box Culvert |  | 2025-01-30 | 2026-01-08 | 05-Jan-25 A | 2026-06-07 | 872163.92 | 872163.93 | 6274037.42 | Planned Total Cost | [6 empty] | 20686.94 | 448951.8 | 375167.01 | 142266.22 | 116231.56 |  |  |  |  | 375616.31 | 859271.57 | 775861.83 | 268604.78 | 704737.17 | 1087314.45 | 592002.45 | 243317.5 | 264007.84
|  |  | JDH3-02-008-C-04-(ST)-Box Culvert |  | 2025-01-30 | 2026-01-08 | 05-Jan-25 A | 2026-06-07 | 872163.92 | 872163.93 | 6274037.42 | Remaining Total Cost | [15 empty] | 606755.91 | 859271.57 | 775861.83 | 268604.78 | 704737.17 | 1087314.45 | 592002.45 | 243317.5 | 264007.84
|  |  | JDH3-02-008-C-04-(ST)-Box Culvert |  | 2025-01-30 | 2026-01-08 | 05-Jan-25 A | 2026-06-07 | 872163.92 | 872163.93 | 6274037.42 | Actual Total Cost | [6 empty] | 38489.01 | 78600.97 | 88606.28 | 86127.58 | 109788.24 | 59290.5 | 43902.67 | 164381.98 | 195459.05 | 7517.66
|  |  | JDH3-02-008-C-04-(ST)- Concrete Box Culvert With Dim (1000x1000) depth from 2.51 to 3.50 |  | 2025-01-30 | 2025-05-06 | 05-Jan-25 A | 2025-10-04 | 872163.92 | 872163.93 | 1103303.53 | Planned Total Cost | [6 empty] | 20686.94 | 448951.8 | 375167.01 | 142266.22 | 116231.56
|  |  | JDH3-02-008-C-04-(ST)- Concrete Box Culvert With Dim (1000x1000) depth from 2.51 to 3.50 |  | 2025-01-30 | 2025-05-06 | 05-Jan-25 A | 2025-10-04 | 872163.92 | 872163.93 | 1103303.53 | Remaining Total Cost | [15 empty] | 231139.6
|  |  | JDH3-02-008-C-04-(ST)- Concrete Box Culvert With Dim (1000x1000) depth from 2.51 to 3.50 |  | 2025-01-30 | 2025-05-06 | 05-Jan-25 A | 2025-10-04 | 872163.92 | 872163.93 | 1103303.53 | Actual Total Cost | [6 empty] | 38489.01 | 78600.97 | 88606.28 | 86127.58 | 109788.24 | 59290.5 | 43902.67 | 164381.98 | 195459.05 | 7517.66
|  |  | JDH3-02-008-C-04-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2025-05-07 | 2025-05-25 | 2025-10-02 | 2025-10-21 | 0 | 0 | 122048.27 | Planned Total Cost | [15 empty] | 122048.27
|  |  | JDH3-02-008-C-04-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2025-05-07 | 2025-05-25 | 2025-10-02 | 2025-10-21 | 0 | 0 | 122048.27 | Remaining Total Cost | [15 empty] | 122048.27
|  |  | JDH3-02-008-C-04-(ST)- Concrete Box Culvert With Dim (2000x1250) depth from 2.51 to 3.50 |  | 2025-05-07 | 2025-05-25 | 2025-10-02 | 2025-10-21 | 0 | 0 | 122048.27 | Actual Total Cost
|  |  | JDH3-02-008-C-04-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2025-05-26 | 2025-09-20 | 2025-10-21 | 2026-02-16 | 0 | 0 | 2467815.47 | Planned Total Cost | [15 empty] | 253568.04 | 859271.57 | 775861.83 | 268604.78 | 310509.25
|  |  | JDH3-02-008-C-04-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2025-05-26 | 2025-09-20 | 2025-10-21 | 2026-02-16 | 0 | 0 | 2467815.47 | Remaining Total Cost | [15 empty] | 253568.04 | 859271.57 | 775861.83 | 268604.78 | 310509.25
|  |  | JDH3-02-008-C-04-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 1.51 to 2.50 |  | 2025-05-26 | 2025-09-20 | 2025-10-21 | 2026-02-16 | 0 | 0 | 2467815.47 | Actual Total Cost
|  |  | JDH3-02-008-C-04-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2025-09-21 | 2026-01-08 | 2026-02-16 | 2026-06-07 | 0 | 0 | 2580870.15 | Planned Total Cost | [19 empty] | 394227.92 | 1087314.45 | 592002.45 | 243317.5 | 264007.84
|  |  | JDH3-02-008-C-04-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2025-09-21 | 2026-01-08 | 2026-02-16 | 2026-06-07 | 0 | 0 | 2580870.15 | Remaining Total Cost | [19 empty] | 394227.92 | 1087314.45 | 592002.45 | 243317.5 | 264007.84
|  |  | JDH3-02-008-C-04-(ST)- Concrete Box Culvert With Dim (3000x1500) depth from 2.51 to 3.50 |  | 2025-09-21 | 2026-01-08 | 2026-02-16 | 2026-06-07 | 0 | 0 | 2580870.15 | Actual Total Cost
|  |  | JDH3-02-008-C-04-(ST)-NetWork |  | 2025-06-09 | 2025-07-13 | 2025-11-04 | 2025-12-09 | 0 | 0 | 1364559.19 | Planned Total Cost | [16 empty] | 1195618.92 | 168940.28
|  |  | JDH3-02-008-C-04-(ST)-NetWork |  | 2025-06-09 | 2025-07-13 | 2025-11-04 | 2025-12-09 | 0 | 0 | 1364559.19 | Remaining Total Cost | [16 empty] | 1195618.92 | 168940.28
|  |  | JDH3-02-008-C-04-(ST)-NetWork |  | 2025-06-09 | 2025-07-13 | 2025-11-04 | 2025-12-09 | 0 | 0 | 1364559.19 | Actual Total Cost
|  |  | JDH3-02-008-C-04-(ST)- Supply and install GRP pipe Diameter 1400 mm depth from 1.51 to 2.50 m |  | 2025-06-09 | 2025-07-13 | 2025-11-04 | 2025-12-09 | 0 | 0 | 619600 | Planned Total Cost | [16 empty] | 500223.73 | 119376.27
|  |  | JDH3-02-008-C-04-(ST)- Supply and install GRP pipe Diameter 1400 mm depth from 1.51 to 2.50 m |  | 2025-06-09 | 2025-07-13 | 2025-11-04 | 2025-12-09 | 0 | 0 | 619600 | Remaining Total Cost | [16 empty] | 500223.73 | 119376.27
|  |  | JDH3-02-008-C-04-(ST)- Supply and install GRP pipe Diameter 1400 mm depth from 1.51 to 2.50 m |  | 2025-06-09 | 2025-07-13 | 2025-11-04 | 2025-12-09 | 0 | 0 | 619600 | Actual Total Cost
|  |  | JDH3-02-008-C-04-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-06-12 | 2025-06-23 | 2025-11-08 | 2025-11-19 | 0 | 0 | 54750.66 | Planned Total Cost | [16 empty] | 54750.66
|  |  | JDH3-02-008-C-04-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-06-12 | 2025-06-23 | 2025-11-08 | 2025-11-19 | 0 | 0 | 54750.66 | Remaining Total Cost | [16 empty] | 54750.66
|  |  | JDH3-02-008-C-04-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-06-12 | 2025-06-23 | 2025-11-08 | 2025-11-19 | 0 | 0 | 54750.66 | Actual Total Cost
|  |  | JDH3-02-008-C-04-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-06-15 | 2025-07-10 | 2025-11-10 | 2025-12-07 | 0 | 0 | 389772.53 | Planned Total Cost | [16 empty] | 342122.84 | 47649.69
|  |  | JDH3-02-008-C-04-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-06-15 | 2025-07-10 | 2025-11-10 | 2025-12-07 | 0 | 0 | 389772.53 | Remaining Total Cost | [16 empty] | 342122.84 | 47649.69
|  |  | JDH3-02-008-C-04-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-06-15 | 2025-07-10 | 2025-11-10 | 2025-12-07 | 0 | 0 | 389772.53 | Actual Total Cost
|  |  | JDH3-02-008-C-04-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-06-18 | 2025-07-03 | 2025-11-13 | 2025-11-30 | 0 | 0 | 237252.82 | Planned Total Cost | [16 empty] | 237252.82
|  |  | JDH3-02-008-C-04-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-06-18 | 2025-07-03 | 2025-11-13 | 2025-11-30 | 0 | 0 | 237252.82 | Remaining Total Cost | [16 empty] | 237252.82
|  |  | JDH3-02-008-C-04-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-06-18 | 2025-07-03 | 2025-11-13 | 2025-11-30 | 0 | 0 | 237252.82 | Actual Total Cost
|  |  | JDH3-02-008-C-04-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-06-21 | 2025-07-06 | 2025-11-16 | 2025-12-02 | 0 | 0 | 21509.18 | Planned Total Cost | [16 empty] | 19594.87 | 1914.32
|  |  | JDH3-02-008-C-04-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-06-21 | 2025-07-06 | 2025-11-16 | 2025-12-02 | 0 | 0 | 21509.18 | Remaining Total Cost | [16 empty] | 19594.87 | 1914.32
|  |  | JDH3-02-008-C-04-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-06-21 | 2025-07-06 | 2025-11-16 | 2025-12-02 | 0 | 0 | 21509.18 | Actual Total Cost
|  |  | JDH3-02-008-C-04-(ST)-PIPES ENCASEMENT |  | 2025-06-21 | 2025-07-03 | 2025-11-16 | 2025-11-30 | 0 | 0 | 41674 | Planned Total Cost | [16 empty] | 41674
|  |  | JDH3-02-008-C-04-(ST)-PIPES ENCASEMENT |  | 2025-06-21 | 2025-07-03 | 2025-11-16 | 2025-11-30 | 0 | 0 | 41674 | Remaining Total Cost | [16 empty] | 41674
|  |  | JDH3-02-008-C-04-(ST)-PIPES ENCASEMENT |  | 2025-06-21 | 2025-07-03 | 2025-11-16 | 2025-11-30 | 0 | 0 | 41674 | Actual Total Cost
|  |  | JDH3-02-008-C-04-TSE Network - TSE |  | 2026-01-10 | 2026-01-26 | 2026-06-07 | 2026-06-24 | 0 | 0 | 215349.64 | Planned Total Cost | [23 empty] | 215349.64
|  |  | JDH3-02-008-C-04-TSE Network - TSE |  | 2026-01-10 | 2026-01-26 | 2026-06-07 | 2026-06-24 | 0 | 0 | 215349.64 | Remaining Total Cost | [23 empty] | 215349.64
|  |  | JDH3-02-008-C-04-TSE Network - TSE |  | 2026-01-10 | 2026-01-26 | 2026-06-07 | 2026-06-24 | 0 | 0 | 215349.64 | Actual Total Cost
|  |  | JDH3-02-008-C-04-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2026-01-10 | 2026-01-26 | 2026-06-07 | 2026-06-24 | 0 | 0 | 170240.52 | Planned Total Cost | [23 empty] | 170240.52
|  |  | JDH3-02-008-C-04-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2026-01-10 | 2026-01-26 | 2026-06-07 | 2026-06-24 | 0 | 0 | 170240.52 | Remaining Total Cost | [23 empty] | 170240.52
|  |  | JDH3-02-008-C-04-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2026-01-10 | 2026-01-26 | 2026-06-07 | 2026-06-24 | 0 | 0 | 170240.52 | Actual Total Cost
|  |  | JDH3-02-008-C-04-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2026-01-12 | 2026-01-22 | 2026-06-09 | 2026-06-21 | 0 | 0 | 45109.12 | Planned Total Cost | [23 empty] | 45109.12
|  |  | JDH3-02-008-C-04-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2026-01-12 | 2026-01-22 | 2026-06-09 | 2026-06-21 | 0 | 0 | 45109.12 | Remaining Total Cost | [23 empty] | 45109.12
|  |  | JDH3-02-008-C-04-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2026-01-12 | 2026-01-22 | 2026-06-09 | 2026-06-21 | 0 | 0 | 45109.12 | Actual Total Cost
|  |  | JDH3-02-008-C-04-Potable Water Network - WT |  | 2026-01-12 | 2026-01-28 | 2026-06-09 | 2026-06-27 | 0 | 0 | 29480.04 | Planned Total Cost | [23 empty] | 29480.04
|  |  | JDH3-02-008-C-04-Potable Water Network - WT |  | 2026-01-12 | 2026-01-28 | 2026-06-09 | 2026-06-27 | 0 | 0 | 29480.04 | Remaining Total Cost | [23 empty] | 29480.04
|  |  | JDH3-02-008-C-04-Potable Water Network - WT |  | 2026-01-12 | 2026-01-28 | 2026-06-09 | 2026-06-27 | 0 | 0 | 29480.04 | Actual Total Cost
|  |  | JDH3-02-008-C-04-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-01-12 | 2026-01-22 | 2026-06-09 | 2026-06-21 | 0 | 0 | 2274.83 | Planned Total Cost | [23 empty] | 2274.83
|  |  | JDH3-02-008-C-04-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-01-12 | 2026-01-22 | 2026-06-09 | 2026-06-21 | 0 | 0 | 2274.83 | Remaining Total Cost | [23 empty] | 2274.83
|  |  | JDH3-02-008-C-04-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-01-12 | 2026-01-22 | 2026-06-09 | 2026-06-21 | 0 | 0 | 2274.83 | Actual Total Cost
|  |  | JDH3-02-008-C-04-(WT)- Supply and install 3-out fire hydrant |  | 2026-01-14 | 2026-01-28 | 2026-06-11 | 2026-06-27 | 0 | 0 | 27205.21 | Planned Total Cost | [23 empty] | 27205.21
|  |  | JDH3-02-008-C-04-(WT)- Supply and install 3-out fire hydrant |  | 2026-01-14 | 2026-01-28 | 2026-06-11 | 2026-06-27 | 0 | 0 | 27205.21 | Remaining Total Cost | [23 empty] | 27205.21
|  |  | JDH3-02-008-C-04-(WT)- Supply and install 3-out fire hydrant |  | 2026-01-14 | 2026-01-28 | 2026-06-11 | 2026-06-27 | 0 | 0 | 27205.21 | Actual Total Cost
|  |  | L-52 |  | 2024-11-24 | 2025-01-23 | 06-Nov-24 A | 2025-11-12 | 268980.97 | 268980.97 | 790836.33 | Planned Total Cost | [5 empty] | 310728.93 | [9 empty] | 457714.9 | 22392.5
|  |  | L-52 |  | 2024-11-24 | 2025-01-23 | 06-Nov-24 A | 2025-11-12 | 268980.97 | 268980.97 | 790836.33 | Remaining Total Cost | [15 empty] | 499462.86 | 22392.5
|  |  | L-52 |  | 2024-11-24 | 2025-01-23 | 06-Nov-24 A | 2025-11-12 | 268980.97 | 268980.97 | 790836.33 | Actual Total Cost | [5 empty] | 50537.66 | 59593.72 | 2229.23 |  | 10787.34 | 9037.88 | 5618.07 |  | 80813.55 | 49641.54 | 721.98
|  |  | JDH3-02-008-L-52-Storm Network - ST |  | 2024-12-02 | 2024-12-28 | 04-Dec-24 A | 2025-10-18 | 268980.97 | 268980.97 | 678276.02 | Planned Total Cost | [5 empty] | 310728.93 | [9 empty] | 367547.1
|  |  | JDH3-02-008-L-52-Storm Network - ST |  | 2024-12-02 | 2024-12-28 | 04-Dec-24 A | 2025-10-18 | 268980.97 | 268980.97 | 678276.02 | Remaining Total Cost | [15 empty] | 409295.06
|  |  | JDH3-02-008-L-52-Storm Network - ST |  | 2024-12-02 | 2024-12-28 | 04-Dec-24 A | 2025-10-18 | 268980.97 | 268980.97 | 678276.02 | Actual Total Cost | [5 empty] | 50537.66 | 59593.72 | 2229.23 |  | 10787.34 | 9037.88 | 5618.07 |  | 80813.55 | 49641.54 | 721.98
|  |  | JDH3-02-008-L-52-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-12-02 | 2024-12-12 | 2025-10-02 | 2025-10-13 | 0 | 0 | 98739.63 | Planned Total Cost | [15 empty] | 98739.63
|  |  | JDH3-02-008-L-52-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-12-02 | 2024-12-12 | 2025-10-02 | 2025-10-13 | 0 | 0 | 98739.63 | Remaining Total Cost | [15 empty] | 98739.63
|  |  | JDH3-02-008-L-52-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-12-02 | 2024-12-12 | 2025-10-02 | 2025-10-13 | 0 | 0 | 98739.63 | Actual Total Cost
|  |  | JDH3-02-008-L-52-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-12-02 | 2024-12-12 | 11-Dec-24 A | 2025-10-02 | 2083-09-15 15:36 | 2083-09-15 15:22 | 74508.81 | Planned Total Cost | [5 empty] | 74508.81
|  |  | JDH3-02-008-L-52-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-12-02 | 2024-12-12 | 11-Dec-24 A | 2025-10-02 | 2083-09-15 15:36 | 2083-09-15 15:22 | 74508.81 | Remaining Total Cost | [15 empty] | 7409.16
|  |  | JDH3-02-008-L-52-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-12-02 | 2024-12-12 | 11-Dec-24 A | 2025-10-02 | 2083-09-15 15:36 | 2083-09-15 15:22 | 74508.81 | Actual Total Cost | [5 empty] | 5000.84 | [7 empty] | 25605.08 | 36285.44 | 208.29
|  |  | JDH3-02-008-L-52-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-12-07 | 2024-12-17 | 2025-10-05 | 2025-10-15 | 0 | 0 | 47695.99 | Planned Total Cost | [15 empty] | 47695.99
|  |  | JDH3-02-008-L-52-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-12-07 | 2024-12-17 | 2025-10-05 | 2025-10-15 | 0 | 0 | 47695.99 | Remaining Total Cost | [15 empty] | 47695.99
|  |  | JDH3-02-008-L-52-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-12-07 | 2024-12-17 | 2025-10-05 | 2025-10-15 | 0 | 0 | 47695.99 | Actual Total Cost
|  |  | JDH3-02-008-L-52-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-12-02 | 2024-12-16 | 04-Dec-24 A | 2025-10-04 | 2159-06-22 23:02 | 2159-06-22 23:17 | 101907.46 | Planned Total Cost | [5 empty] | 94772.96 | [9 empty] | 7134.5
|  |  | JDH3-02-008-L-52-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-12-02 | 2024-12-16 | 04-Dec-24 A | 2025-10-04 | 2159-06-22 23:02 | 2159-06-22 23:17 | 101907.46 | Remaining Total Cost | [15 empty] | 7134.5
|  |  | JDH3-02-008-L-52-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-12-02 | 2024-12-16 | 04-Dec-24 A | 2025-10-04 | 2159-06-22 23:02 | 2159-06-22 23:17 | 101907.46 | Actual Total Cost | [5 empty] | 38692.99 | 50794.51 | 2229.23 |  | 1241.6 | 1814.65
|  |  | JDH3-02-008-L-52-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-12-15 | 2024-12-28 | 12-Apr-25 A | 2025-10-08 | 2052-05-10 00:29 | 2052-05-10 00:14 | 65884.42 | Planned Total Cost | [5 empty] | 62253.27 | [9 empty] | 3631.14
|  |  | JDH3-02-008-L-52-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-12-15 | 2024-12-28 | 12-Apr-25 A | 2025-10-08 | 2052-05-10 00:29 | 2052-05-10 00:14 | 65884.42 | Remaining Total Cost | [15 empty] | 10235.4
|  |  | JDH3-02-008-L-52-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-12-15 | 2024-12-28 | 12-Apr-25 A | 2025-10-08 | 2052-05-10 00:29 | 2052-05-10 00:14 | 65884.42 | Actual Total Cost | [9 empty] | 9545.74 |  |  |  | 41430.01 | 4500.17 | 173.08
|  |  | JDH3-02-008-L-52-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-12-02 | 2024-12-28 | 24-Dec-24 A | 2025-10-15 | 1997-12-19 16:48 | 1997-12-19 17:02 | 62572.18 | Planned Total Cost | [5 empty] | 50384.61 | [9 empty] | 12187.58
|  |  | JDH3-02-008-L-52-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-12-02 | 2024-12-28 | 24-Dec-24 A | 2025-10-15 | 1997-12-19 16:48 | 1997-12-19 17:02 | 62572.18 | Remaining Total Cost | [15 empty] | 26788.48
|  |  | JDH3-02-008-L-52-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-12-02 | 2024-12-28 | 24-Dec-24 A | 2025-10-15 | 1997-12-19 16:48 | 1997-12-19 17:02 | 62572.18 | Actual Total Cost | [5 empty] | 6843.83 | 8799.22 |  |  |  | 7223.23 | 5618.07 |  | 2716.04 | 4413.57 | 169.75
|  |  | JDH3-02-008-L-52-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2024-12-09 | 2024-12-19 | 2025-10-07 | 2025-10-18 | 0 | 0 | 13687.66 | Planned Total Cost | [15 empty] | 13687.66
|  |  | JDH3-02-008-L-52-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2024-12-09 | 2024-12-19 | 2025-10-07 | 2025-10-18 | 0 | 0 | 13687.66 | Remaining Total Cost | [15 empty] | 13687.66
|  |  | JDH3-02-008-L-52-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2024-12-09 | 2024-12-19 | 2025-10-07 | 2025-10-18 | 0 | 0 | 13687.66 | Actual Total Cost
|  |  | JDH3-02-008-L-52-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2024-12-11 | 2024-12-22 | 11-Aug-25 A | 2025-10-08 | 1942-11-30 15:07 | 1942-11-30 15:22 | 33893.26 | Planned Total Cost | [5 empty] | 28809.27 | [9 empty] | 5083.99
|  |  | JDH3-02-008-L-52-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2024-12-11 | 2024-12-22 | 11-Aug-25 A | 2025-10-08 | 1942-11-30 15:07 | 1942-11-30 15:22 | 33893.26 | Remaining Total Cost | [15 empty] | 18217.63
|  |  | JDH3-02-008-L-52-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2024-12-11 | 2024-12-22 | 11-Aug-25 A | 2025-10-08 | 1942-11-30 15:07 | 1942-11-30 15:22 | 33893.26 | Actual Total Cost | [13 empty] | 11062.42 | 4442.36 | 170.86
|  |  | JDH3-02-008-L-52-(ST)- Single Catchbasine Works |  | 2024-12-14 | 2024-12-22 | 2025-10-02 | 2025-10-11 | 0 | 0 | 43018.4 | Planned Total Cost | [15 empty] | 43018.4
|  |  | JDH3-02-008-L-52-(ST)- Single Catchbasine Works |  | 2024-12-14 | 2024-12-22 | 2025-10-02 | 2025-10-11 | 0 | 0 | 43018.4 | Remaining Total Cost | [15 empty] | 43018.4
|  |  | JDH3-02-008-L-52-(ST)- Single Catchbasine Works |  | 2024-12-14 | 2024-12-22 | 2025-10-02 | 2025-10-11 | 0 | 0 | 43018.4 | Actual Total Cost
|  |  | JDH3-02-008-L-52-(ST)- Double Catchbasine Works |  | 2024-12-16 | 2024-12-24 | 2025-10-05 | 2025-10-13 | 0 | 0 | 136368.21 | Planned Total Cost | [15 empty] | 136368.21
|  |  | JDH3-02-008-L-52-(ST)- Double Catchbasine Works |  | 2024-12-16 | 2024-12-24 | 2025-10-05 | 2025-10-13 | 0 | 0 | 136368.21 | Remaining Total Cost | [15 empty] | 136368.21
|  |  | JDH3-02-008-L-52-(ST)- Double Catchbasine Works |  | 2024-12-16 | 2024-12-24 | 2025-10-05 | 2025-10-13 | 0 | 0 | 136368.21 | Actual Total Cost
|  |  | JDH3-02-008-L-52-TSE Network - TSE |  | 2024-12-25 | 2025-01-12 | 2025-10-14 | 2025-11-01 | 0 | 0 | 90529.57 | Planned Total Cost | [15 empty] | 90167.8 | 361.77
|  |  | JDH3-02-008-L-52-TSE Network - TSE |  | 2024-12-25 | 2025-01-12 | 2025-10-14 | 2025-11-01 | 0 | 0 | 90529.57 | Remaining Total Cost | [15 empty] | 90167.8 | 361.77
|  |  | JDH3-02-008-L-52-TSE Network - TSE |  | 2024-12-25 | 2025-01-12 | 2025-10-14 | 2025-11-01 | 0 | 0 | 90529.57 | Actual Total Cost
|  |  | JDH3-02-008-L-52-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-12-25 | 2025-01-05 | 2025-10-14 | 2025-10-25 | 0 | 0 | 6358.72 | Planned Total Cost | [15 empty] | 6358.72
|  |  | JDH3-02-008-L-52-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-12-25 | 2025-01-05 | 2025-10-14 | 2025-10-25 | 0 | 0 | 6358.72 | Remaining Total Cost | [15 empty] | 6358.72
|  |  | JDH3-02-008-L-52-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-12-25 | 2025-01-05 | 2025-10-14 | 2025-10-25 | 0 | 0 | 6358.72 | Actual Total Cost
|  |  | JDH3-02-008-L-52-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2024-12-28 | 2025-01-07 | 2025-10-16 | 2025-10-27 | 0 | 0 | 27649.98 | Planned Total Cost | [15 empty] | 27649.98
|  |  | JDH3-02-008-L-52-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2024-12-28 | 2025-01-07 | 2025-10-16 | 2025-10-27 | 0 | 0 | 27649.98 | Remaining Total Cost | [15 empty] | 27649.98
|  |  | JDH3-02-008-L-52-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2024-12-28 | 2025-01-07 | 2025-10-16 | 2025-10-27 | 0 | 0 | 27649.98 | Actual Total Cost
|  |  | JDH3-02-008-L-52-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 2.51 to 3.5 m |  | 2024-12-30 | 2025-01-09 | 2025-10-19 | 2025-10-29 | 0 | 0 | 49285.43 | Planned Total Cost | [15 empty] | 49285.43
|  |  | JDH3-02-008-L-52-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 2.51 to 3.5 m |  | 2024-12-30 | 2025-01-09 | 2025-10-19 | 2025-10-29 | 0 | 0 | 49285.43 | Remaining Total Cost | [15 empty] | 49285.43
|  |  | JDH3-02-008-L-52-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 2.51 to 3.5 m |  | 2024-12-30 | 2025-01-09 | 2025-10-19 | 2025-10-29 | 0 | 0 | 49285.43 | Actual Total Cost
|  |  | JDH3-02-008-L-52-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 3.51 to 4.5 m |  | 2025-01-01 | 2025-01-12 | 2025-10-21 | 2025-11-01 | 0 | 0 | 4649.12 | Planned Total Cost | [15 empty] | 4416.67 | 232.46
|  |  | JDH3-02-008-L-52-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 3.51 to 4.5 m |  | 2025-01-01 | 2025-01-12 | 2025-10-21 | 2025-11-01 | 0 | 0 | 4649.12 | Remaining Total Cost | [15 empty] | 4416.67 | 232.46
|  |  | JDH3-02-008-L-52-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 3.51 to 4.5 m |  | 2025-01-01 | 2025-01-12 | 2025-10-21 | 2025-11-01 | 0 | 0 | 4649.12 | Actual Total Cost
|  |  | JDH3-02-008-L-52-(TSE)-Supply and install gate valves-100 mm |  | 2025-01-08 | 2025-01-12 | 2025-10-28 | 2025-11-01 | 0 | 0 | 2586.32 | Planned Total Cost | [15 empty] | 2457 | 129.32
|  |  | JDH3-02-008-L-52-(TSE)-Supply and install gate valves-100 mm |  | 2025-01-08 | 2025-01-12 | 2025-10-28 | 2025-11-01 | 0 | 0 | 2586.32 | Remaining Total Cost | [15 empty] | 2457 | 129.32
|  |  | JDH3-02-008-L-52-(TSE)-Supply and install gate valves-100 mm |  | 2025-01-08 | 2025-01-12 | 2025-10-28 | 2025-11-01 | 0 | 0 | 2586.32 | Actual Total Cost
|  |  | JDH3-02-008-L-52-Potable Water Network - WT |  | 2025-01-13 | 2025-01-23 | 2025-11-02 | 2025-11-12 | 0 | 0 | 22030.73 | Planned Total Cost | [16 empty] | 22030.73
|  |  | JDH3-02-008-L-52-Potable Water Network - WT |  | 2025-01-13 | 2025-01-23 | 2025-11-02 | 2025-11-12 | 0 | 0 | 22030.73 | Remaining Total Cost | [16 empty] | 22030.73
|  |  | JDH3-02-008-L-52-Potable Water Network - WT |  | 2025-01-13 | 2025-01-23 | 2025-11-02 | 2025-11-12 | 0 | 0 | 22030.73 | Actual Total Cost
|  |  | JDH3-02-008-L-52-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-01-13 | 2025-01-23 | 2025-11-02 | 2025-11-12 | 0 | 0 | 3893.92 | Planned Total Cost | [16 empty] | 3893.92
|  |  | JDH3-02-008-L-52-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-01-13 | 2025-01-23 | 2025-11-02 | 2025-11-12 | 0 | 0 | 3893.92 | Remaining Total Cost | [16 empty] | 3893.92
|  |  | JDH3-02-008-L-52-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-01-13 | 2025-01-23 | 2025-11-02 | 2025-11-12 | 0 | 0 | 3893.92 | Actual Total Cost
|  |  | JDH3-02-008-L-52-(WT)- Supply and install 3-out fire hydrant |  | 2025-01-15 | 2025-01-21 | 2025-11-04 | 2025-11-10 | 0 | 0 | 18136.81 | Planned Total Cost | [16 empty] | 18136.81
|  |  | JDH3-02-008-L-52-(WT)- Supply and install 3-out fire hydrant |  | 2025-01-15 | 2025-01-21 | 2025-11-04 | 2025-11-10 | 0 | 0 | 18136.81 | Remaining Total Cost | [16 empty] | 18136.81
|  |  | JDH3-02-008-L-52-(WT)- Supply and install 3-out fire hydrant |  | 2025-01-15 | 2025-01-21 | 2025-11-04 | 2025-11-10 | 0 | 0 | 18136.81 | Actual Total Cost
|  |  | L-63 |  | 2024-11-24 | 2025-02-20 | 12-Nov-24 A | 2026-02-10 | 1323563.35 | 1323563.35 | 2160909.19 | Planned Total Cost | [5 empty] | 1151979.91 | 183923.4 | [8 empty] | 715171.78 | 79154.19 |  |  | 30679.92
|  |  | L-63 |  | 2024-11-24 | 2025-02-20 | 12-Nov-24 A | 2026-02-10 | 1323563.35 | 1323563.35 | 2160909.19 | Remaining Total Cost | [15 empty] | 727511.73 | 79154.19 |  |  | 30679.92
|  |  | L-63 |  | 2024-11-24 | 2025-02-20 | 12-Nov-24 A | 2026-02-10 | 1323563.35 | 1323563.35 | 2160909.19 | Actual Total Cost | [5 empty] | 5565.58 | 50784.9 | 119651.93 | 24347.74 | 126879.47 | 228411.31 | 27966.58 | 29434.19 | 670243.42 | 39079.76 | 1198.48
|  |  | JDH3-02-008-L-63-Storm Network - ST |  | 2024-12-02 | 2025-01-09 | 28-Dec-24 A | 2025-10-21 | 1077929.71 | 1077929.71 | 1751284.77 | Planned Total Cost | [5 empty] | 1090269.66 | [9 empty] | 661015.1
|  |  | JDH3-02-008-L-63-Storm Network - ST |  | 2024-12-02 | 2025-01-09 | 28-Dec-24 A | 2025-10-21 | 1077929.71 | 1077929.71 | 1751284.77 | Remaining Total Cost | [15 empty] | 673355.06
|  |  | JDH3-02-008-L-63-Storm Network - ST |  | 2024-12-02 | 2025-01-09 | 28-Dec-24 A | 2025-10-21 | 1077929.71 | 1077929.71 | 1751284.77 | Actual Total Cost | [5 empty] | 5565.58 | 50784.9 | 119651.93 | 24347.74 | 126879.47 | 193277.97 | 3338.25 | 6051.21 | 507754.42 | 39079.76 | 1198.48
|  |  | JDH3-02-008-L-63-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-12-02 | 2024-12-25 | 28-Dec-24 A | 2025-10-04 | 262019.59 | 262019.58 | 278745.47 | Planned Total Cost | [5 empty] | 262019.59 | [9 empty] | 16725.88
|  |  | JDH3-02-008-L-63-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-12-02 | 2024-12-25 | 28-Dec-24 A | 2025-10-04 | 262019.59 | 262019.58 | 278745.47 | Remaining Total Cost | [15 empty] | 16725.88
|  |  | JDH3-02-008-L-63-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-12-02 | 2024-12-25 | 28-Dec-24 A | 2025-10-04 | 262019.59 | 262019.58 | 278745.47 | Actual Total Cost | [5 empty] | 5565.58 | 50784.9 | 119651.93 | 24347.74 | 5342.07 | 5806.6 |  |  | 50520.76
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-12-05 | 2025-01-07 | 15-Apr-25 A | 2025-10-15 | 2126-10-29 23:46 | 2126-10-29 23:46 | 152756.65 | Planned Total Cost | [5 empty] | 108150.65 | [9 empty] | 44606
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-12-05 | 2025-01-07 | 15-Apr-25 A | 2025-10-15 | 2126-10-29 23:46 | 2126-10-29 23:46 | 152756.65 | Remaining Total Cost | [15 empty] | 69907.66
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-12-05 | 2025-01-07 | 15-Apr-25 A | 2025-10-15 | 2126-10-29 23:46 | 2126-10-29 23:46 | 152756.65 | Actual Total Cost | [9 empty] | 18976.03 | 34935.24 |  |  | 1621.2 | 26118.05 | 1198.48
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-12-11 | 2025-01-05 | 06-Aug-25 A | 2025-10-18 | 1905-01-03 06:00 | 1905-01-03 06:00 | 2287.81 | Planned Total Cost | [5 empty] | 1830.25 | [9 empty] | 457.56
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-12-11 | 2025-01-05 | 06-Aug-25 A | 2025-10-18 | 1905-01-03 06:00 | 1905-01-03 06:00 | 2287.81 | Remaining Total Cost | [15 empty] | 457.56
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-12-11 | 2025-01-05 | 06-Aug-25 A | 2025-10-18 | 1905-01-03 06:00 | 1905-01-03 06:00 | 2287.81 | Actual Total Cost | [13 empty] | 1830.25
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2024-12-14 | 2025-01-05 | 09-Aug-25 A | 2025-10-04 | 2128-11-30 18:58 | 2128-11-30 19:12 | 92901.99 | Planned Total Cost | [5 empty] | 74321.59 | [9 empty] | 18580.4
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2024-12-14 | 2025-01-05 | 09-Aug-25 A | 2025-10-04 | 2128-11-30 18:58 | 2128-11-30 19:12 | 92901.99 | Remaining Total Cost | [15 empty] | 9290.2
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2024-12-14 | 2025-01-05 | 09-Aug-25 A | 2025-10-04 | 2128-11-30 18:58 | 2128-11-30 19:12 | 92901.99 | Actual Total Cost | [13 empty] | 74321.6 | 9290.2
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2024-12-16 | 2025-01-05 | 11-Aug-25 A | 2025-10-06 | 1990-06-19 13:12 | 1990-06-19 13:12 | 36715.05 | Planned Total Cost | [5 empty] | 29372.04 | [9 empty] | 7343.01
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2024-12-16 | 2025-01-05 | 11-Aug-25 A | 2025-10-06 | 1990-06-19 13:12 | 1990-06-19 13:12 | 36715.05 | Remaining Total Cost | [15 empty] | 3671.51
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2024-12-16 | 2025-01-05 | 11-Aug-25 A | 2025-10-06 | 1990-06-19 13:12 | 1990-06-19 13:12 | 36715.05 | Actual Total Cost | [13 empty] | 29372.04 | 3671.51
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-12-09 | 2025-01-08 | 14-Apr-25 A | 2025-10-21 | 2378-09-26 06:00 | 2378-09-26 06:00 | 218570.31 | Planned Total Cost | [5 empty] | 174856.25 | [9 empty] | 43714.06
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-12-09 | 2025-01-08 | 14-Apr-25 A | 2025-10-21 | 2378-09-26 06:00 | 2378-09-26 06:00 | 218570.31 | Remaining Total Cost | [15 empty] | 43714.06
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-12-09 | 2025-01-08 | 14-Apr-25 A | 2025-10-21 | 2378-09-26 06:00 | 2378-09-26 06:00 | 218570.31 | Actual Total Cost | [9 empty] | 21945.41 | 12731.74 |  |  | 140179.1
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-12-02 | 2025-01-05 | 15-Apr-25 A | 2025-10-18 | 2042-05-28 02:53 | 2042-05-28 02:38 | 57793.46 | Planned Total Cost | [5 empty] | 52014.12 | [9 empty] | 5779.35
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-12-02 | 2025-01-05 | 15-Apr-25 A | 2025-10-18 | 2042-05-28 02:53 | 2042-05-28 02:38 | 57793.46 | Remaining Total Cost | [15 empty] | 5779.35
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-12-02 | 2025-01-05 | 15-Apr-25 A | 2025-10-18 | 2042-05-28 02:53 | 2042-05-28 02:38 | 57793.46 | Actual Total Cost | [9 empty] | 28354.91 | 21853.15 | 1806.05
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2024-12-12 | 2025-01-05 | 14-Apr-25 A | 2025-10-18 | 2049-03-11 12:43 | 2049-03-11 12:43 | 79693.77 | Planned Total Cost | [5 empty] | 54493.53 | [9 empty] | 25200.24
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2024-12-12 | 2025-01-05 | 14-Apr-25 A | 2025-10-18 | 2049-03-11 12:43 | 2049-03-11 12:43 | 79693.77 | Remaining Total Cost | [15 empty] | 25200.24
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2024-12-12 | 2025-01-05 | 14-Apr-25 A | 2025-10-18 | 2049-03-11 12:43 | 2049-03-11 12:43 | 79693.77 | Actual Total Cost | [9 empty] | 14009.48 | 34432.84 |  | 6051.21
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2024-12-02 | 2025-01-05 | 14-Apr-25 A | 2025-10-18 | 2208-09-07 23:46 | 2208-09-08 | 140933.74 | Planned Total Cost | [5 empty] | 112746.99 | [9 empty] | 28186.75
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2024-12-02 | 2025-01-05 | 14-Apr-25 A | 2025-10-18 | 2208-09-07 23:46 | 2208-09-08 | 140933.74 | Remaining Total Cost | [15 empty] | 28186.75
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2024-12-02 | 2025-01-05 | 14-Apr-25 A | 2025-10-18 | 2208-09-07 23:46 | 2208-09-08 | 140933.74 | Actual Total Cost | [9 empty] | 32590.93 | 80156.07
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2024-12-18 | 2025-01-05 | 13-Aug-25 A | 2025-10-18 | 2252-11-16 15:36 | 2252-11-16 15:36 | 161109.57 | Planned Total Cost | [5 empty] | 128887.65 | [9 empty] | 32221.91
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2024-12-18 | 2025-01-05 | 13-Aug-25 A | 2025-10-18 | 2252-11-16 15:36 | 2252-11-16 15:36 | 161109.57 | Remaining Total Cost | [15 empty] | 32221.91
|  |  | JDH3-02-008-L-63-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2024-12-18 | 2025-01-05 | 13-Aug-25 A | 2025-10-18 | 2252-11-16 15:36 | 2252-11-16 15:36 | 161109.57 | Actual Total Cost | [13 empty] | 128887.65
|  |  | JDH3-02-008-L-63-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-12-21 | 2025-01-02 | 06-Aug-25 A | 2025-10-09 | 2057-01-12 20:10 | 2057-01-12 20:10 | 114715.67 | Planned Total Cost | [5 empty] | 57357.84 | [9 empty] | 57357.84
|  |  | JDH3-02-008-L-63-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-12-21 | 2025-01-02 | 06-Aug-25 A | 2025-10-09 | 2057-01-12 20:10 | 2057-01-12 20:10 | 114715.67 | Remaining Total Cost | [15 empty] | 57357.84
|  |  | JDH3-02-008-L-63-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-12-21 | 2025-01-02 | 06-Aug-25 A | 2025-10-09 | 2057-01-12 20:10 | 2057-01-12 20:10 | 114715.67 | Actual Total Cost | [13 empty] | 57357.84
|  |  | JDH3-02-008-L-63-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2024-12-15 | 2025-01-02 | 15-Apr-25 A | 2025-10-08 | 1993-09-07 03:50 | 1993-09-07 03:50 | 68438.32 | Planned Total Cost | [5 empty] | 34219.16 | [9 empty] | 34219.16
|  |  | JDH3-02-008-L-63-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2024-12-15 | 2025-01-02 | 15-Apr-25 A | 2025-10-08 | 1993-09-07 03:50 | 1993-09-07 03:50 | 68438.32 | Remaining Total Cost | [15 empty] | 34219.16
|  |  | JDH3-02-008-L-63-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2024-12-15 | 2025-01-02 | 15-Apr-25 A | 2025-10-08 | 1993-09-07 03:50 | 1993-09-07 03:50 | 68438.32 | Actual Total Cost | [9 empty] | 5660.64 | 3362.34 | 1532.21 |  | 23663.98
|  |  | JDH3-02-008-L-63-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2024-12-23 | 2025-01-02 | 2025-10-02 | 2025-10-13 | 0 | 0 | 43018.37 | Planned Total Cost | [15 empty] | 43018.37
|  |  | JDH3-02-008-L-63-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2024-12-23 | 2025-01-02 | 2025-10-02 | 2025-10-13 | 0 | 0 | 43018.37 | Remaining Total Cost | [15 empty] | 43018.37
|  |  | JDH3-02-008-L-63-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2024-12-23 | 2025-01-02 | 2025-10-02 | 2025-10-13 | 0 | 0 | 43018.37 | Actual Total Cost
|  |  | JDH3-02-008-L-63-(ST)- Single Catchbasine Works |  | 2024-12-25 | 2025-01-09 | 2025-10-05 | 2025-10-20 | 0 | 0 | 78215.26 | Planned Total Cost | [15 empty] | 78215.26
|  |  | JDH3-02-008-L-63-(ST)- Single Catchbasine Works |  | 2024-12-25 | 2025-01-09 | 2025-10-05 | 2025-10-20 | 0 | 0 | 78215.26 | Remaining Total Cost | [15 empty] | 78215.26
|  |  | JDH3-02-008-L-63-(ST)- Single Catchbasine Works |  | 2024-12-25 | 2025-01-09 | 2025-10-05 | 2025-10-20 | 0 | 0 | 78215.26 | Actual Total Cost
|  |  | JDH3-02-008-L-63-(ST)- Double Catchbasine Works |  | 2024-12-29 | 2025-01-08 | 2025-10-08 | 2025-10-19 | 0 | 0 | 204552.31 | Planned Total Cost | [15 empty] | 204552.31
|  |  | JDH3-02-008-L-63-(ST)- Double Catchbasine Works |  | 2024-12-29 | 2025-01-08 | 2025-10-08 | 2025-10-19 | 0 | 0 | 204552.31 | Remaining Total Cost | [15 empty] | 204552.31
|  |  | JDH3-02-008-L-63-(ST)- Double Catchbasine Works |  | 2024-12-29 | 2025-01-08 | 2025-10-08 | 2025-10-19 | 0 | 0 | 204552.31 | Actual Total Cost
|  |  | JDH3-02-008-L-63-(ST)-PIPES ENCASEMENT |  | 2024-12-28 | 2025-01-02 | 2025-10-09 | 2025-10-15 | 0 | 0 | 20837 | Planned Total Cost | [15 empty] | 20837
|  |  | JDH3-02-008-L-63-(ST)-PIPES ENCASEMENT |  | 2024-12-28 | 2025-01-02 | 2025-10-09 | 2025-10-15 | 0 | 0 | 20837 | Remaining Total Cost | [15 empty] | 20837
|  |  | JDH3-02-008-L-63-(ST)-PIPES ENCASEMENT |  | 2024-12-28 | 2025-01-02 | 2025-10-09 | 2025-10-15 | 0 | 0 | 20837 | Actual Total Cost
|  |  | JDH3-02-008-L-63-TSE Network - TSE |  | 2024-12-17 | 2025-02-20 | 01-May-25 A | 2026-02-10 | 245633.64 | 245633.64 | 339808.2 | Planned Total Cost | [5 empty] | 61710.25 | 183923.4 | [8 empty] | 54156.67 | 9337.96 |  |  | 30679.92
|  |  | JDH3-02-008-L-63-TSE Network - TSE |  | 2024-12-17 | 2025-02-20 | 01-May-25 A | 2026-02-10 | 245633.64 | 245633.64 | 339808.2 | Remaining Total Cost | [15 empty] | 54156.67 | 9337.96 |  |  | 30679.92
|  |  | JDH3-02-008-L-63-TSE Network - TSE |  | 2024-12-17 | 2025-02-20 | 01-May-25 A | 2026-02-10 | 245633.64 | 245633.64 | 339808.2 | Actual Total Cost | [10 empty] | 35133.34 | 24628.32 | 23382.98 | 162489
|  |  | JDH3-02-008-L-63-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-01-11 | 2025-01-21 | 2025-10-21 | 2025-11-01 | 0 | 0 | 5550.17 | Planned Total Cost | [15 empty] | 5272.66 | 277.51
|  |  | JDH3-02-008-L-63-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-01-11 | 2025-01-21 | 2025-10-21 | 2025-11-01 | 0 | 0 | 5550.17 | Remaining Total Cost | [15 empty] | 5272.66 | 277.51
|  |  | JDH3-02-008-L-63-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-01-11 | 2025-01-21 | 2025-10-21 | 2025-11-01 | 0 | 0 | 5550.17 | Actual Total Cost
|  |  | JDH3-02-008-L-63-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2024-12-17 | 2025-01-30 | 01-May-25 A | 20-Aug-25 A | 245633.64 | 245633.64 | 245633.64 | Planned Total Cost | [5 empty] | 61710.25 | 183923.4
|  |  | JDH3-02-008-L-63-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2024-12-17 | 2025-01-30 | 01-May-25 A | 20-Aug-25 A | 245633.64 | 245633.64 | 245633.64 | Remaining Total Cost
|  |  | JDH3-02-008-L-63-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2024-12-17 | 2025-01-30 | 01-May-25 A | 20-Aug-25 A | 245633.64 | 245633.64 | 245633.64 | Actual Total Cost | [10 empty] | 35133.34 | 24628.32 | 23382.98 | 162489
|  |  | JDH3-02-008-L-63-(TSE)-Supply and install gate valves-100 mm |  | 2025-01-15 | 2025-01-19 | 2025-10-26 | 2025-10-29 | 0 | 0 | 5172.64 | Planned Total Cost | [15 empty] | 5172.64
|  |  | JDH3-02-008-L-63-(TSE)-Supply and install gate valves-100 mm |  | 2025-01-15 | 2025-01-19 | 2025-10-26 | 2025-10-29 | 0 | 0 | 5172.64 | Remaining Total Cost | [15 empty] | 5172.64
|  |  | JDH3-02-008-L-63-(TSE)-Supply and install gate valves-100 mm |  | 2025-01-15 | 2025-01-19 | 2025-10-26 | 2025-10-29 | 0 | 0 | 5172.64 | Actual Total Cost
|  |  | JDH3-02-008-L-63-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2025-02-17 | 2025-02-20 | 2026-02-07 | 2026-02-10 | 0 | 0 | 30679.92 | Planned Total Cost | [19 empty] | 30679.92
|  |  | JDH3-02-008-L-63-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2025-02-17 | 2025-02-20 | 2026-02-07 | 2026-02-10 | 0 | 0 | 30679.92 | Remaining Total Cost | [19 empty] | 30679.92
|  |  | JDH3-02-008-L-63-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2025-02-17 | 2025-02-20 | 2026-02-07 | 2026-02-10 | 0 | 0 | 30679.92 | Actual Total Cost
|  |  | JDH3-02-008-L-63-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2025-01-15 | 2025-01-19 | 2025-10-26 | 2025-10-29 | 0 | 0 | 9791.9 | Planned Total Cost | [15 empty] | 9791.9
|  |  | JDH3-02-008-L-63-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2025-01-15 | 2025-01-19 | 2025-10-26 | 2025-10-29 | 0 | 0 | 9791.9 | Remaining Total Cost | [15 empty] | 9791.9
|  |  | JDH3-02-008-L-63-(TSE)-Supply and install of Wash-out valves-100 mm. |  | 2025-01-15 | 2025-01-19 | 2025-10-26 | 2025-10-29 | 0 | 0 | 9791.9 | Actual Total Cost
|  |  | JDH3-02-008-L-63-(TSE)-Supply and install of Air valves-50 mm. |  | 2025-01-15 | 2025-01-19 | 2025-10-26 | 2025-10-29 | 0 | 0 | 7444.14 | Planned Total Cost | [15 empty] | 7444.14
|  |  | JDH3-02-008-L-63-(TSE)-Supply and install of Air valves-50 mm. |  | 2025-01-15 | 2025-01-19 | 2025-10-26 | 2025-10-29 | 0 | 0 | 7444.14 | Remaining Total Cost | [15 empty] | 7444.14
|  |  | JDH3-02-008-L-63-(TSE)-Supply and install of Air valves-50 mm. |  | 2025-01-15 | 2025-01-19 | 2025-10-26 | 2025-10-29 | 0 | 0 | 7444.14 | Actual Total Cost
|  |  | JDH3-02-008-L-63-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2025-01-15 | 2025-01-23 | 2025-10-23 | 2025-11-01 | 0 | 0 | 18204.6 | Planned Total Cost | [15 empty] | 17294.37 | 910.23
|  |  | JDH3-02-008-L-63-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2025-01-15 | 2025-01-23 | 2025-10-23 | 2025-11-01 | 0 | 0 | 18204.6 | Remaining Total Cost | [15 empty] | 17294.37 | 910.23
|  |  | JDH3-02-008-L-63-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2025-01-15 | 2025-01-23 | 2025-10-23 | 2025-11-01 | 0 | 0 | 18204.6 | Actual Total Cost
|  |  | JDH3-02-008-L-63-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2025-01-18 | 2025-01-26 | 2025-10-26 | 2025-11-03 | 0 | 0 | 13851.92 | Planned Total Cost | [15 empty] | 8311.15 | 5540.77
|  |  | JDH3-02-008-L-63-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2025-01-18 | 2025-01-26 | 2025-10-26 | 2025-11-03 | 0 | 0 | 13851.92 | Remaining Total Cost | [15 empty] | 8311.15 | 5540.77
|  |  | JDH3-02-008-L-63-(TSE)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipeline |  | 2025-01-18 | 2025-01-26 | 2025-10-26 | 2025-11-03 | 0 | 0 | 13851.92 | Actual Total Cost
|  |  | JDH3-02-008-L-63-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2025-01-20 | 2025-01-28 | 2025-10-28 | 2025-11-05 | 0 | 0 | 3479.28 | Planned Total Cost | [15 empty] | 869.82 | 2609.46
|  |  | JDH3-02-008-L-63-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2025-01-20 | 2025-01-28 | 2025-10-28 | 2025-11-05 | 0 | 0 | 3479.28 | Remaining Total Cost | [15 empty] | 869.82 | 2609.46
|  |  | JDH3-02-008-L-63-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2025-01-20 | 2025-01-28 | 2025-10-28 | 2025-11-05 | 0 | 0 | 3479.28 | Actual Total Cost
|  |  | JDH3-02-008-L-63-Potable Water Network - WT |  | 2025-02-01 | 2025-02-13 | 2025-11-06 | 2025-11-19 | 0 | 0 | 69816.23 | Planned Total Cost | [16 empty] | 69816.23
|  |  | JDH3-02-008-L-63-Potable Water Network - WT |  | 2025-02-01 | 2025-02-13 | 2025-11-06 | 2025-11-19 | 0 | 0 | 69816.23 | Remaining Total Cost | [16 empty] | 69816.23
|  |  | JDH3-02-008-L-63-Potable Water Network - WT |  | 2025-02-01 | 2025-02-13 | 2025-11-06 | 2025-11-19 | 0 | 0 | 69816.23 | Actual Total Cost
|  |  | JDH3-02-008-L-63-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-02-01 | 2025-02-13 | 2025-11-06 | 2025-11-19 | 0 | 0 | 6337.41 | Planned Total Cost | [16 empty] | 6337.41
|  |  | JDH3-02-008-L-63-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-02-01 | 2025-02-13 | 2025-11-06 | 2025-11-19 | 0 | 0 | 6337.41 | Remaining Total Cost | [16 empty] | 6337.41
|  |  | JDH3-02-008-L-63-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-02-01 | 2025-02-13 | 2025-11-06 | 2025-11-19 | 0 | 0 | 6337.41 | Actual Total Cost
|  |  | JDH3-02-008-L-63-(WT)- Supply and install 3-out fire hydrant |  | 2025-02-03 | 2025-02-11 | 2025-11-09 | 2025-11-17 | 0 | 0 | 63478.82 | Planned Total Cost | [16 empty] | 63478.82
|  |  | JDH3-02-008-L-63-(WT)- Supply and install 3-out fire hydrant |  | 2025-02-03 | 2025-02-11 | 2025-11-09 | 2025-11-17 | 0 | 0 | 63478.82 | Remaining Total Cost | [16 empty] | 63478.82
|  |  | JDH3-02-008-L-63-(WT)- Supply and install 3-out fire hydrant |  | 2025-02-03 | 2025-02-11 | 2025-11-09 | 2025-11-17 | 0 | 0 | 63478.82 | Actual Total Cost
|  |  | L-64 |  | 2024-11-24 | 2025-03-26 | 02-Nov-24 A | 2025-12-01 | 1182892.35 | 1182892.33 | 2103669.73 | Planned Total Cost | [5 empty] | 200192.57 | 282580.4 | 492899.91 | 12818.57 | [6 empty] | 493090.75 | 621644.91 | 442.62
|  |  | L-64 |  | 2024-11-24 | 2025-03-26 | 02-Nov-24 A | 2025-12-01 | 1182892.35 | 1182892.33 | 2103669.73 | Remaining Total Cost | [15 empty] | 504506.52 | 415828.25 | 442.62
|  |  | L-64 |  | 2024-11-24 | 2025-03-26 | 02-Nov-24 A | 2025-12-01 | 1182892.35 | 1182892.33 | 2103669.73 | Actual Total Cost |  |  |  |  | 12165.13 | 152299.02 | 97646.21 | 175448.51 | 190318.65 | 208002.76 | 99192.46 | 13960.76 | 11331.45 | 16710.73 | 187979.69 | 17836.97
|  |  | JDH3-02-008-L-64-Storm Network - ST |  | 2024-12-02 | 2025-03-01 | 24-Nov-24 A | 2025-11-19 | 1125046.82 | 1125046.8 | 1929227.67 | Planned Total Cost | [5 empty] | 200192.57 | 282580.4 | 436457.18 | [7 empty] | 472772.69 | 537224.84
|  |  | JDH3-02-008-L-64-Storm Network - ST |  | 2024-12-02 | 2025-03-01 | 24-Nov-24 A | 2025-11-19 | 1125046.82 | 1125046.8 | 1929227.67 | Remaining Total Cost | [15 empty] | 472772.69 | 331408.18
|  |  | JDH3-02-008-L-64-Storm Network - ST |  | 2024-12-02 | 2025-03-01 | 24-Nov-24 A | 2025-11-19 | 1125046.82 | 1125046.8 | 1929227.67 | Actual Total Cost |  |  |  |  | 12165.13 | 145972.52 | 46127.19 | 175448.51 | 190318.65 | 208002.76 | 99192.46 | 13960.76 | 11331.45 | 16710.73 | 187979.69 | 17836.97
|  |  | JDH3-02-008-L-64-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-12-02 | 2025-02-17 | 24-Nov-24 A | 2025-11-19 | 208807.98 | 208807.98 | 283133.37 | Planned Total Cost | [5 empty] | 200192.57 |  | 8615.41 | [8 empty] | 74325.39
|  |  | JDH3-02-008-L-64-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-12-02 | 2025-02-17 | 24-Nov-24 A | 2025-11-19 | 208807.98 | 208807.98 | 283133.37 | Remaining Total Cost | [16 empty] | 74325.39
|  |  | JDH3-02-008-L-64-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-12-02 | 2025-02-17 | 24-Nov-24 A | 2025-11-19 | 208807.98 | 208807.98 | 283133.37 | Actual Total Cost |  |  |  |  | 12165.13 | 145972.52 | 19810.11 | 13903.01 | 8341.8 | 4953.86 | 3661.55
|  |  | JDH3-02-008-L-64-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-01-15 | 2025-02-13 | 2025-11-04 | 2025-11-19 | 0 | 0 | 33427.96 | Planned Total Cost | [16 empty] | 33427.96
|  |  | JDH3-02-008-L-64-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-01-15 | 2025-02-13 | 2025-11-04 | 2025-11-19 | 0 | 0 | 33427.96 | Remaining Total Cost | [16 empty] | 33427.96
|  |  | JDH3-02-008-L-64-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-01-15 | 2025-02-13 | 2025-11-04 | 2025-11-19 | 0 | 0 | 33427.96 | Actual Total Cost
|  |  | JDH3-02-008-L-64-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-01-18 | 2025-02-13 | 2025-11-06 | 2025-11-19 | 0 | 0 | 8169.64 | Planned Total Cost | [16 empty] | 8169.64
|  |  | JDH3-02-008-L-64-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-01-18 | 2025-02-13 | 2025-11-06 | 2025-11-19 | 0 | 0 | 8169.64 | Remaining Total Cost | [16 empty] | 8169.64
|  |  | JDH3-02-008-L-64-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-01-18 | 2025-02-13 | 2025-11-06 | 2025-11-19 | 0 | 0 | 8169.64 | Actual Total Cost
|  |  | JDH3-02-008-L-64-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2025-01-15 | 2025-02-13 | 05-Apr-25 A | 2025-11-19 | 1994-04-15 22:19 | 1994-04-15 22:05 | 37037.04 | Planned Total Cost | [6 empty] | 33333.34 | 1106.59 | [8 empty] | 2597.11
|  |  | JDH3-02-008-L-64-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2025-01-15 | 2025-02-13 | 05-Apr-25 A | 2025-11-19 | 1994-04-15 22:19 | 1994-04-15 22:05 | 37037.04 | Remaining Total Cost | [16 empty] | 2597.11
|  |  | JDH3-02-008-L-64-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2025-01-15 | 2025-02-13 | 05-Apr-25 A | 2025-11-19 | 1994-04-15 22:19 | 1994-04-15 22:05 | 37037.04 | Actual Total Cost | [9 empty] | 33561.99 | 877.93
|  |  | JDH3-02-008-L-64-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-01-18 | 2025-02-13 | 21-Jan-25 A | 2025-11-19 | 40479.7 | 2010-10-28 16:48 | 43533.38 | Planned Total Cost | [6 empty] | 39180.05 | 1299.65 | [8 empty] | 3053.68
|  |  | JDH3-02-008-L-64-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-01-18 | 2025-02-13 | 21-Jan-25 A | 2025-11-19 | 40479.7 | 2010-10-28 16:48 | 43533.38 | Remaining Total Cost | [16 empty] | 3053.68
|  |  | JDH3-02-008-L-64-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-01-18 | 2025-02-13 | 21-Jan-25 A | 2025-11-19 | 40479.7 | 2010-10-28 16:48 | 43533.38 | Actual Total Cost | [6 empty] | 4897.51 | 3809.17 |  | 30741.48 | 1031.54
|  |  | JDH3-02-008-L-64-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-01-20 | 2025-02-13 | 21-Jan-25 A | 2025-11-19 | 2047-11-29 23:31 | 2047-11-29 23:46 | 75737.16 | Planned Total Cost | [6 empty] | 51768.55 | 2257.44 | [8 empty] | 21711.18
|  |  | JDH3-02-008-L-64-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-01-20 | 2025-02-13 | 21-Jan-25 A | 2025-11-19 | 2047-11-29 23:31 | 2047-11-29 23:46 | 75737.16 | Remaining Total Cost | [16 empty] | 21711.18
|  |  | JDH3-02-008-L-64-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-01-20 | 2025-02-13 | 21-Jan-25 A | 2025-11-19 | 2047-11-29 23:31 | 2047-11-29 23:46 | 75737.16 | Actual Total Cost | [6 empty] | 6474.62 | 5035.81 | 40258.12 | 1410.9 | 846.54
|  |  | JDH3-02-008-L-64-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-01-22 | 2025-02-17 | 22-Jan-25 A | 2025-11-17 | 236554.35 | 236554.34 | 302385.8 | Planned Total Cost | [6 empty] | 63282.73 | 48756.69 | [8 empty] | 190346.38
|  |  | JDH3-02-008-L-64-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-01-22 | 2025-02-17 | 22-Jan-25 A | 2025-11-17 | 236554.35 | 236554.34 | 302385.8 | Remaining Total Cost | [16 empty] | 65831.46
|  |  | JDH3-02-008-L-64-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-01-22 | 2025-02-17 | 22-Jan-25 A | 2025-11-17 | 236554.35 | 236554.34 | 302385.8 | Actual Total Cost | [6 empty] | 8600.92 | 20592 | 941.71 | 34790.15 | 46759.17 | 355.47 |  |  | 113968.83 | 10546.09
|  |  | JDH3-02-008-L-64-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2025-01-26 | 2025-03-01 | 28-Jan-25 A | 2025-11-17 | 474170.63 | 474170.63 | 563914.21 | Planned Total Cost | [6 empty] | 84587.04 | 308281.85 | [8 empty] | 171045.32
|  |  | JDH3-02-008-L-64-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2025-01-26 | 2025-03-01 | 28-Jan-25 A | 2025-11-17 | 474170.63 | 474170.63 | 563914.21 | Remaining Total Cost | [16 empty] | 89743.58
|  |  | JDH3-02-008-L-64-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2025-01-26 | 2025-03-01 | 28-Jan-25 A | 2025-11-17 | 474170.63 | 474170.63 | 563914.21 | Actual Total Cost | [6 empty] | 6344.03 | 132108.52 | 140777.01 | 100590.91 | 6323.47 | 3973.83 | 2751.12 |  | 74010.86 | 7290.88
|  |  | JDH3-02-008-L-64-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2025-01-20 | 2025-02-15 | 2025-11-09 | 2025-11-19 | 0 | 0 | 22129.67 | Planned Total Cost | [16 empty] | 22129.67
|  |  | JDH3-02-008-L-64-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2025-01-20 | 2025-02-15 | 2025-11-09 | 2025-11-19 | 0 | 0 | 22129.67 | Remaining Total Cost | [16 empty] | 22129.67
|  |  | JDH3-02-008-L-64-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2025-01-20 | 2025-02-15 | 2025-11-09 | 2025-11-19 | 0 | 0 | 22129.67 | Actual Total Cost
|  |  | JDH3-02-008-L-64-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-01-22 | 2025-02-02 | 23-Aug-25 A | 2025-10-08 | 1928-07-19 16:48 | 1928-07-19 16:48 | 20857.39 | Planned Total Cost | [6 empty] | 10428.7 | [8 empty] | 10428.7
|  |  | JDH3-02-008-L-64-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-01-22 | 2025-02-02 | 23-Aug-25 A | 2025-10-08 | 1928-07-19 16:48 | 1928-07-19 16:48 | 20857.39 | Remaining Total Cost | [15 empty] | 10428.7
|  |  | JDH3-02-008-L-64-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-01-22 | 2025-02-02 | 23-Aug-25 A | 2025-10-08 | 1928-07-19 16:48 | 1928-07-19 16:48 | 20857.39 | Actual Total Cost | [13 empty] | 10428.7
|  |  | JDH3-02-008-L-64-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-02-01 | 2025-02-16 | 10-May-25 A | 2025-10-11 | 2052-07-21 00:58 | 2052-07-21 00:58 | 123188.98 | Planned Total Cost | [7 empty] | 55721.04 | [7 empty] | 67467.94
|  |  | JDH3-02-008-L-64-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-02-01 | 2025-02-16 | 10-May-25 A | 2025-10-11 | 2052-07-21 00:58 | 2052-07-21 00:58 | 123188.98 | Remaining Total Cost | [15 empty] | 67467.94
|  |  | JDH3-02-008-L-64-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-02-01 | 2025-02-16 | 10-May-25 A | 2025-10-11 | 2052-07-21 00:58 | 2052-07-21 00:58 | 123188.98 | Actual Total Cost | [10 empty] | 34048.9 | 6809.78 | 8580.33 | 6282.03
|  |  | JDH3-02-008-L-64-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-01-25 | 2025-02-04 | 2025-10-02 | 2025-10-13 | 0 | 0 | 101679.79 | Planned Total Cost | [15 empty] | 101679.79
|  |  | JDH3-02-008-L-64-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-01-25 | 2025-02-04 | 2025-10-02 | 2025-10-13 | 0 | 0 | 101679.79 | Remaining Total Cost | [15 empty] | 101679.79
|  |  | JDH3-02-008-L-64-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-01-25 | 2025-02-04 | 2025-10-02 | 2025-10-13 | 0 | 0 | 101679.79 | Actual Total Cost
|  |  | JDH3-02-008-L-64-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-01-27 | 2025-02-06 | 2025-10-05 | 2025-10-15 | 0 | 0 | 18250.22 | Planned Total Cost | [15 empty] | 18250.22
|  |  | JDH3-02-008-L-64-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-01-27 | 2025-02-06 | 2025-10-05 | 2025-10-15 | 0 | 0 | 18250.22 | Remaining Total Cost | [15 empty] | 18250.22
|  |  | JDH3-02-008-L-64-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-01-27 | 2025-02-06 | 2025-10-05 | 2025-10-15 | 0 | 0 | 18250.22 | Actual Total Cost
|  |  | JDH3-02-008-L-64-(ST)- Single Catchbasine Works |  | 2025-01-29 | 2025-02-09 | 2025-10-07 | 2025-10-18 | 0 | 0 | 70393.74 | Planned Total Cost | [15 empty] | 70393.74
|  |  | JDH3-02-008-L-64-(ST)- Single Catchbasine Works |  | 2025-01-29 | 2025-02-09 | 2025-10-07 | 2025-10-18 | 0 | 0 | 70393.74 | Remaining Total Cost | [15 empty] | 70393.74
|  |  | JDH3-02-008-L-64-(ST)- Single Catchbasine Works |  | 2025-01-29 | 2025-02-09 | 2025-10-07 | 2025-10-18 | 0 | 0 | 70393.74 | Actual Total Cost
|  |  | JDH3-02-008-L-64-(ST)- Double Catchbasine Works |  | 2025-02-01 | 2025-02-12 | 2025-10-09 | 2025-10-21 | 0 | 0 | 204552.31 | Planned Total Cost | [15 empty] | 204552.31
|  |  | JDH3-02-008-L-64-(ST)- Double Catchbasine Works |  | 2025-02-01 | 2025-02-12 | 2025-10-09 | 2025-10-21 | 0 | 0 | 204552.31 | Remaining Total Cost | [15 empty] | 204552.31
|  |  | JDH3-02-008-L-64-(ST)- Double Catchbasine Works |  | 2025-02-01 | 2025-02-12 | 2025-10-09 | 2025-10-21 | 0 | 0 | 204552.31 | Actual Total Cost
|  |  | JDH3-02-008-L-64-(ST)-PIPES ENCASEMENT |  | 2025-02-03 | 2025-02-11 | 21-Apr-25 A | 2025-11-17 | 1928-07-09 12:00 | 1928-07-09 12:00 | 20837 | Planned Total Cost | [7 empty] | 10418.5 | [8 empty] | 10418.5
|  |  | JDH3-02-008-L-64-(ST)-PIPES ENCASEMENT |  | 2025-02-03 | 2025-02-11 | 21-Apr-25 A | 2025-11-17 | 1928-07-09 12:00 | 1928-07-09 12:00 | 20837 | Remaining Total Cost | [16 empty] | 10418.5
|  |  | JDH3-02-008-L-64-(ST)-PIPES ENCASEMENT |  | 2025-02-03 | 2025-02-11 | 21-Apr-25 A | 2025-11-17 | 1928-07-09 12:00 | 1928-07-09 12:00 | 20837 | Actual Total Cost | [9 empty] | 1953.47 | 5643.35 | 2821.68
|  |  | JDH3-02-008-L-64-TSE Network - TSE |  | 2025-02-10 | 2025-03-15 | 24-Dec-24 A | 2025-11-02 | 2058-05-15 12:58 | 2058-05-15 12:43 | 93042.43 | Planned Total Cost | [7 empty] | 56442.73 | 12818.57 | [6 empty] | 20318.06 | 3463.07
|  |  | JDH3-02-008-L-64-TSE Network - TSE |  | 2025-02-10 | 2025-03-15 | 24-Dec-24 A | 2025-11-02 | 2058-05-15 12:58 | 2058-05-15 12:43 | 93042.43 | Remaining Total Cost | [15 empty] | 31733.83 | 3463.07
|  |  | JDH3-02-008-L-64-TSE Network - TSE |  | 2025-02-10 | 2025-03-15 | 24-Dec-24 A | 2025-11-02 | 2058-05-15 12:58 | 2058-05-15 12:43 | 93042.43 | Actual Total Cost | [5 empty] | 6326.5 | 51519.03
|  |  | JDH3-02-008-L-64-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-02-10 | 2025-03-15 | 24-Dec-24 A | 2025-11-02 | 2058-05-15 12:58 | 2058-05-15 12:43 | 86576.63 | Planned Total Cost | [7 empty] | 56442.73 | 12818.57 | [6 empty] | 13852.26 | 3463.07
|  |  | JDH3-02-008-L-64-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-02-10 | 2025-03-15 | 24-Dec-24 A | 2025-11-02 | 2058-05-15 12:58 | 2058-05-15 12:43 | 86576.63 | Remaining Total Cost | [15 empty] | 25268.03 | 3463.07
|  |  | JDH3-02-008-L-64-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-02-10 | 2025-03-15 | 24-Dec-24 A | 2025-11-02 | 2058-05-15 12:58 | 2058-05-15 12:43 | 86576.63 | Actual Total Cost | [5 empty] | 6326.5 | 51519.03
|  |  | JDH3-02-008-L-64-(TSE)-Supply and install gate valves-100 mm |  | 2025-03-04 | 2025-03-09 | 2025-10-12 | 2025-10-27 | 0 | 0 | 6465.8 | Planned Total Cost | [15 empty] | 6465.8
|  |  | JDH3-02-008-L-64-(TSE)-Supply and install gate valves-100 mm |  | 2025-03-04 | 2025-03-09 | 2025-10-12 | 2025-10-27 | 0 | 0 | 6465.8 | Remaining Total Cost | [15 empty] | 6465.8
|  |  | JDH3-02-008-L-64-(TSE)-Supply and install gate valves-100 mm |  | 2025-03-04 | 2025-03-09 | 2025-10-12 | 2025-10-27 | 0 | 0 | 6465.8 | Actual Total Cost
|  |  | JDH3-02-008-L-64-Potable Water Network - WT |  | 2025-03-16 | 2025-03-26 | 2025-11-20 | 2025-12-01 | 0 | 0 | 81399.63 | Planned Total Cost | [16 empty] | 80957.01 | 442.62
|  |  | JDH3-02-008-L-64-Potable Water Network - WT |  | 2025-03-16 | 2025-03-26 | 2025-11-20 | 2025-12-01 | 0 | 0 | 81399.63 | Remaining Total Cost | [16 empty] | 80957.01 | 442.62
|  |  | JDH3-02-008-L-64-Potable Water Network - WT |  | 2025-03-16 | 2025-03-26 | 2025-11-20 | 2025-12-01 | 0 | 0 | 81399.63 | Actual Total Cost
|  |  | JDH3-02-008-L-64-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-03-16 | 2025-03-26 | 2025-11-20 | 2025-12-01 | 0 | 0 | 8852.4 | Planned Total Cost | [16 empty] | 8409.78 | 442.62
|  |  | JDH3-02-008-L-64-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-03-16 | 2025-03-26 | 2025-11-20 | 2025-12-01 | 0 | 0 | 8852.4 | Remaining Total Cost | [16 empty] | 8409.78 | 442.62
|  |  | JDH3-02-008-L-64-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-03-16 | 2025-03-26 | 2025-11-20 | 2025-12-01 | 0 | 0 | 8852.4 | Actual Total Cost
|  |  | JDH3-02-008-L-64-(WT)- Supply and install 3-out fire hydrant |  | 2025-03-18 | 2025-03-24 | 2025-11-23 | 2025-11-29 | 0 | 0 | 72547.22 | Planned Total Cost | [16 empty] | 72547.22
|  |  | JDH3-02-008-L-64-(WT)- Supply and install 3-out fire hydrant |  | 2025-03-18 | 2025-03-24 | 2025-11-23 | 2025-11-29 | 0 | 0 | 72547.22 | Remaining Total Cost | [16 empty] | 72547.22
|  |  | JDH3-02-008-L-64-(WT)- Supply and install 3-out fire hydrant |  | 2025-03-18 | 2025-03-24 | 2025-11-23 | 2025-11-29 | 0 | 0 | 72547.22 | Actual Total Cost
|  |  | L-65 |  | 2024-12-02 | 2025-02-16 | 01-Jan-25 A | 2025-11-18 | 832297.89 | 832297.92 | 2202624.17 | Planned Total Cost | [5 empty] | 400107.61 | 447997.34 | [8 empty] | 1252143.65 | 102375.56
|  |  | L-65 |  | 2024-12-02 | 2025-02-16 | 01-Jan-25 A | 2025-11-18 | 832297.89 | 832297.92 | 2202624.17 | Remaining Total Cost | [15 empty] | 1267950.7 | 102375.56
|  |  | L-65 |  | 2024-12-02 | 2025-02-16 | 01-Jan-25 A | 2025-11-18 | 832297.89 | 832297.92 | 2202624.17 | Actual Total Cost | [6 empty] | 14054.05 | 19302.04 |  |  |  | 69878.31 | 383359.12 | 328438.79 | 16626.14 | 639.47
|  |  | JDH3-02-008-L-65-Storm Network - ST |  | 2024-12-10 | 2025-01-26 | 10-Jun-25 A | 2025-10-28 | 798941.81 | 798941.83 | 2017718.58 | Planned Total Cost | [5 empty] | 400107.61 | 414641.26 | [8 empty] | 1202969.71
|  |  | JDH3-02-008-L-65-Storm Network - ST |  | 2024-12-10 | 2025-01-26 | 10-Jun-25 A | 2025-10-28 | 798941.81 | 798941.83 | 2017718.58 | Remaining Total Cost | [15 empty] | 1218776.76
|  |  | JDH3-02-008-L-65-Storm Network - ST |  | 2024-12-10 | 2025-01-26 | 10-Jun-25 A | 2025-10-28 | 798941.81 | 798941.83 | 2017718.58 | Actual Total Cost | [11 empty] | 69878.31 | 383359.12 | 328438.79 | 16626.14 | 639.47
|  |  | JDH3-02-008-L-65-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-12-10 | 2025-01-26 | 2025-10-02 | 2025-10-27 | 0 | 0 | 272718.94 | Planned Total Cost | [15 empty] | 272718.94
|  |  | JDH3-02-008-L-65-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-12-10 | 2025-01-26 | 2025-10-02 | 2025-10-27 | 0 | 0 | 272718.94 | Remaining Total Cost | [15 empty] | 272718.94
|  |  | JDH3-02-008-L-65-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-12-10 | 2025-01-26 | 2025-10-02 | 2025-10-27 | 0 | 0 | 272718.94 | Actual Total Cost
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-12-14 | 2025-01-21 | 2025-10-06 | 2025-10-23 | 0 | 0 | 49607.79 | Planned Total Cost | [15 empty] | 49607.79
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-12-14 | 2025-01-21 | 2025-10-06 | 2025-10-23 | 0 | 0 | 49607.79 | Remaining Total Cost | [15 empty] | 49607.79
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-12-14 | 2025-01-21 | 2025-10-06 | 2025-10-23 | 0 | 0 | 49607.79 | Actual Total Cost
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-12-16 | 2025-01-21 | 2025-10-08 | 2025-10-23 | 0 | 0 | 15725.29 | Planned Total Cost | [15 empty] | 15725.29
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-12-16 | 2025-01-21 | 2025-10-08 | 2025-10-23 | 0 | 0 | 15725.29 | Remaining Total Cost | [15 empty] | 15725.29
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-12-16 | 2025-01-21 | 2025-10-08 | 2025-10-23 | 0 | 0 | 15725.29 | Actual Total Cost
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2024-12-18 | 2025-01-21 | 02-Aug-25 A | 2025-10-23 | 2019-07-01 03:36 | 2019-07-01 03:50 | 54558.94 | Planned Total Cost | [5 empty] | 43647.15 | [9 empty] | 10911.79
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2024-12-18 | 2025-01-21 | 02-Aug-25 A | 2025-10-23 | 2019-07-01 03:36 | 2019-07-01 03:50 | 54558.94 | Remaining Total Cost | [15 empty] | 10911.79
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2024-12-18 | 2025-01-21 | 02-Aug-25 A | 2025-10-23 | 2019-07-01 03:36 | 2019-07-01 03:50 | 54558.94 | Actual Total Cost | [13 empty] | 43647.16
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2024-12-21 | 2025-01-21 | 05-Aug-25 A | 2025-10-23 | 2017-08-25 12:29 | 2017-08-25 12:29 | 53715.65 | Planned Total Cost | [5 empty] | 42972.52 | [9 empty] | 10743.13
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2024-12-21 | 2025-01-21 | 05-Aug-25 A | 2025-10-23 | 2017-08-25 12:29 | 2017-08-25 12:29 | 53715.65 | Remaining Total Cost | [15 empty] | 10743.13
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2024-12-21 | 2025-01-21 | 05-Aug-25 A | 2025-10-23 | 2017-08-25 12:29 | 2017-08-25 12:29 | 53715.65 | Actual Total Cost | [13 empty] | 42972.52
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-12-23 | 2025-01-22 | 07-Aug-25 A | 2025-10-25 | 2279-02-21 22:19 | 2279-02-21 22:19 | 173101.16 | Planned Total Cost | [5 empty] | 138480.93 | [9 empty] | 34620.23
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-12-23 | 2025-01-22 | 07-Aug-25 A | 2025-10-25 | 2279-02-21 22:19 | 2279-02-21 22:19 | 173101.16 | Remaining Total Cost | [15 empty] | 34620.23
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-12-23 | 2025-01-22 | 07-Aug-25 A | 2025-10-25 | 2279-02-21 22:19 | 2279-02-21 22:19 | 173101.16 | Actual Total Cost | [13 empty] | 138480.93
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2024-12-25 | 2025-01-26 | 28-Jun-25 A | 2025-10-28 | 2310-02-01 17:31 | 2310-02-01 17:17 | 187228.41 | Planned Total Cost | [5 empty] | 93248.79 | 56533.94 | [8 empty] | 37445.68
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2024-12-25 | 2025-01-26 | 28-Jun-25 A | 2025-10-28 | 2310-02-01 17:31 | 2310-02-01 17:17 | 187228.41 | Remaining Total Cost | [15 empty] | 37445.68
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2024-12-25 | 2025-01-26 | 28-Jun-25 A | 2025-10-28 | 2310-02-01 17:31 | 2310-02-01 17:17 | 187228.41 | Actual Total Cost | [11 empty] | 4750.5 | 96576.82 | 48455.4
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2024-12-28 | 2025-01-23 | 28-Jun-25 A | 2025-10-26 | 2304-12-17 20:53 | 2304-12-17 21:07 | 281794.16 | Planned Total Cost | [5 empty] | 44607.98 | 103302.89 | [8 empty] | 133883.29
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2024-12-28 | 2025-01-23 | 28-Jun-25 A | 2025-10-26 | 2304-12-17 20:53 | 2304-12-17 21:07 | 281794.16 | Remaining Total Cost | [15 empty] | 133883.29
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2024-12-28 | 2025-01-23 | 28-Jun-25 A | 2025-10-26 | 2304-12-17 20:53 | 2304-12-17 21:07 | 281794.16 | Actual Total Cost | [11 empty] | 3813.77 | 108852.63 | 35244.48
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2024-12-31 | 2025-01-23 | 10-Jun-25 A | 2025-10-26 | 209133.11 | 209133.1 | 322607.86 | Planned Total Cost | [5 empty] | 21507.19 | 187625.92 | [8 empty] | 113474.76
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2024-12-31 | 2025-01-23 | 10-Jun-25 A | 2025-10-26 | 209133.11 | 209133.1 | 322607.86 | Remaining Total Cost | [15 empty] | 113474.76
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2024-12-31 | 2025-01-23 | 10-Jun-25 A | 2025-10-26 | 209133.11 | 209133.1 | 322607.86 | Actual Total Cost | [11 empty] | 41858.62 | 167274.48
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2024-12-25 | 2025-01-21 | 2025-10-02 | 2025-10-23 | 0 | 0 | 28650.73 | Planned Total Cost | [15 empty] | 28650.73
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2024-12-25 | 2025-01-21 | 2025-10-02 | 2025-10-23 | 0 | 0 | 28650.73 | Remaining Total Cost | [15 empty] | 28650.73
|  |  | JDH3-02-008-L-65-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2024-12-25 | 2025-01-21 | 2025-10-02 | 2025-10-23 | 0 | 0 | 28650.73 | Actual Total Cost
|  |  | JDH3-02-008-L-65-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-12-28 | 2025-01-07 | 05-Aug-25 A | 2025-10-11 | 1928-04-06 09:50 | 1928-04-06 10:05 | 31286.09 | Planned Total Cost | [5 empty] | 15643.05 | [9 empty] | 15643.05
|  |  | JDH3-02-008-L-65-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-12-28 | 2025-01-07 | 05-Aug-25 A | 2025-10-11 | 1928-04-06 09:50 | 1928-04-06 10:05 | 31286.09 | Remaining Total Cost | [15 empty] | 20961.67
|  |  | JDH3-02-008-L-65-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-12-28 | 2025-01-07 | 05-Aug-25 A | 2025-10-11 | 1928-04-06 09:50 | 1928-04-06 10:05 | 31286.09 | Actual Total Cost | [13 empty] | 4633.08 | 5480.55 | 210.79
|  |  | JDH3-02-008-L-65-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-01-07 | 2025-01-20 | 10-Jun-25 A | 2025-10-11 | 1993-06-29 17:02 | 1993-06-29 17:02 | 82125.99 | Planned Total Cost | [6 empty] | 44638.13 | [8 empty] | 37487.85
|  |  | JDH3-02-008-L-65-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-01-07 | 2025-01-20 | 10-Jun-25 A | 2025-10-11 | 1993-06-29 17:02 | 1993-06-29 17:02 | 82125.99 | Remaining Total Cost | [15 empty] | 47976.28
|  |  | JDH3-02-008-L-65-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-01-07 | 2025-01-20 | 10-Jun-25 A | 2025-10-11 | 1993-06-29 17:02 | 1993-06-29 17:02 | 82125.99 | Actual Total Cost | [11 empty] | 9799.71 | 3990.11 | 8785.62 | 11145.6 | 428.68
|  |  | JDH3-02-008-L-65-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2024-12-30 | 2025-01-09 | 2025-10-05 | 2025-10-15 | 0 | 0 | 67786.53 | Planned Total Cost | [15 empty] | 67786.53
|  |  | JDH3-02-008-L-65-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2024-12-30 | 2025-01-09 | 2025-10-05 | 2025-10-15 | 0 | 0 | 67786.53 | Remaining Total Cost | [15 empty] | 67786.53
|  |  | JDH3-02-008-L-65-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2024-12-30 | 2025-01-09 | 2025-10-05 | 2025-10-15 | 0 | 0 | 67786.53 | Actual Total Cost
|  |  | JDH3-02-008-L-65-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-01-09 | 2025-01-22 | 10-Jun-25 A | 2025-10-25 | 1961-09-16 09:07 | 1961-09-16 09:22 | 36500.43 | Planned Total Cost | [6 empty] | 22540.38 | [8 empty] | 13960.05
|  |  | JDH3-02-008-L-65-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-01-09 | 2025-01-22 | 10-Jun-25 A | 2025-10-25 | 1961-09-16 09:07 | 1961-09-16 09:22 | 36500.43 | Remaining Total Cost | [15 empty] | 13960.05
|  |  | JDH3-02-008-L-65-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-01-09 | 2025-01-22 | 10-Jun-25 A | 2025-10-25 | 1961-09-16 09:07 | 1961-09-16 09:22 | 36500.43 | Actual Total Cost | [11 empty] | 9655.71 | 6665.08 | 6219.6
|  |  | JDH3-02-008-L-65-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-01-01 | 2025-01-16 | 2025-10-07 | 2025-10-22 | 0 | 0 | 64527.55 | Planned Total Cost | [15 empty] | 64527.55
|  |  | JDH3-02-008-L-65-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-01-01 | 2025-01-16 | 2025-10-07 | 2025-10-22 | 0 | 0 | 64527.55 | Remaining Total Cost | [15 empty] | 64527.55
|  |  | JDH3-02-008-L-65-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-01-01 | 2025-01-16 | 2025-10-07 | 2025-10-22 | 0 | 0 | 64527.55 | Actual Total Cost
|  |  | JDH3-02-008-L-65-(ST)- Single Catchbasine Works |  | 2025-01-04 | 2025-01-14 | 2025-10-09 | 2025-10-20 | 0 | 0 | 70393.74 | Planned Total Cost | [15 empty] | 70393.74
|  |  | JDH3-02-008-L-65-(ST)- Single Catchbasine Works |  | 2025-01-04 | 2025-01-14 | 2025-10-09 | 2025-10-20 | 0 | 0 | 70393.74 | Remaining Total Cost | [15 empty] | 70393.74
|  |  | JDH3-02-008-L-65-(ST)- Single Catchbasine Works |  | 2025-01-04 | 2025-01-14 | 2025-10-09 | 2025-10-20 | 0 | 0 | 70393.74 | Actual Total Cost
|  |  | JDH3-02-008-L-65-(ST)- Double Catchbasine Works |  | 2025-01-06 | 2025-01-16 | 2025-10-12 | 2025-10-22 | 0 | 0 | 204552.31 | Planned Total Cost | [15 empty] | 204552.31
|  |  | JDH3-02-008-L-65-(ST)- Double Catchbasine Works |  | 2025-01-06 | 2025-01-16 | 2025-10-12 | 2025-10-22 | 0 | 0 | 204552.31 | Remaining Total Cost | [15 empty] | 204552.31
|  |  | JDH3-02-008-L-65-(ST)- Double Catchbasine Works |  | 2025-01-06 | 2025-01-16 | 2025-10-12 | 2025-10-22 | 0 | 0 | 204552.31 | Actual Total Cost
|  |  | JDH3-02-008-L-65-(ST)-PIPES ENCASEMENT |  | 2025-01-13 | 2025-01-19 | 2025-10-15 | 2025-10-21 | 0 | 0 | 20837 | Planned Total Cost | [15 empty] | 20837
|  |  | JDH3-02-008-L-65-(ST)-PIPES ENCASEMENT |  | 2025-01-13 | 2025-01-19 | 2025-10-15 | 2025-10-21 | 0 | 0 | 20837 | Remaining Total Cost | [15 empty] | 20837
|  |  | JDH3-02-008-L-65-(ST)-PIPES ENCASEMENT |  | 2025-01-13 | 2025-01-19 | 2025-10-15 | 2025-10-21 | 0 | 0 | 20837 | Actual Total Cost
|  |  | JDH3-02-008-L-65-TSE Network - TSE |  | 2025-01-12 | 2025-02-16 | 20-Jan-25 A | 2025-11-18 | 1991-04-28 01:55 | 1991-04-28 02:10 | 115089.36 | Planned Total Cost | [6 empty] | 33356.08 | [8 empty] | 47906.46 | 33826.81
|  |  | JDH3-02-008-L-65-TSE Network - TSE |  | 2025-01-12 | 2025-02-16 | 20-Jan-25 A | 2025-11-18 | 1991-04-28 01:55 | 1991-04-28 02:10 | 115089.36 | Remaining Total Cost | [15 empty] | 47906.46 | 33826.81
|  |  | JDH3-02-008-L-65-TSE Network - TSE |  | 2025-01-12 | 2025-02-16 | 20-Jan-25 A | 2025-11-18 | 1991-04-28 01:55 | 1991-04-28 02:10 | 115089.36 | Actual Total Cost | [6 empty] | 14054.05 | 19302.04
|  |  | JDH3-02-008-L-65-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-01-12 | 2025-02-16 | 20-Jan-25 A | 2025-11-18 | 1991-04-28 01:55 | 1991-04-28 02:10 | 89248.46 | Planned Total Cost | [6 empty] | 33356.08 | [8 empty] | 44290.07 | 11602.3
|  |  | JDH3-02-008-L-65-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-01-12 | 2025-02-16 | 20-Jan-25 A | 2025-11-18 | 1991-04-28 01:55 | 1991-04-28 02:10 | 89248.46 | Remaining Total Cost | [15 empty] | 44290.07 | 11602.3
|  |  | JDH3-02-008-L-65-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-01-12 | 2025-02-16 | 20-Jan-25 A | 2025-11-18 | 1991-04-28 01:55 | 1991-04-28 02:10 | 89248.46 | Actual Total Cost | [6 empty] | 14054.05 | 19302.04
|  |  | JDH3-02-008-L-65-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2025-01-27 | 2025-02-06 | 2025-10-29 | 2025-11-09 | 0 | 0 | 18081.94 | Planned Total Cost | [15 empty] | 3616.39 | 14465.55
|  |  | JDH3-02-008-L-65-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2025-01-27 | 2025-02-06 | 2025-10-29 | 2025-11-09 | 0 | 0 | 18081.94 | Remaining Total Cost | [15 empty] | 3616.39 | 14465.55
|  |  | JDH3-02-008-L-65-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2025-01-27 | 2025-02-06 | 2025-10-29 | 2025-11-09 | 0 | 0 | 18081.94 | Actual Total Cost
|  |  | JDH3-02-008-L-65-(TSE)-Supply and install gate valves-100 mm |  | 2025-02-03 | 2025-02-06 | 2025-11-05 | 2025-11-09 | 0 | 0 | 7758.96 | Planned Total Cost | [16 empty] | 7758.96
|  |  | JDH3-02-008-L-65-(TSE)-Supply and install gate valves-100 mm |  | 2025-02-03 | 2025-02-06 | 2025-11-05 | 2025-11-09 | 0 | 0 | 7758.96 | Remaining Total Cost | [16 empty] | 7758.96
|  |  | JDH3-02-008-L-65-(TSE)-Supply and install gate valves-100 mm |  | 2025-02-03 | 2025-02-06 | 2025-11-05 | 2025-11-09 | 0 | 0 | 7758.96 | Actual Total Cost
|  |  | JDH3-02-008-L-65-Potable Water Network - WT |  | 2025-01-27 | 2025-02-16 | 2025-10-29 | 2025-11-18 | 0 | 0 | 69816.23 | Planned Total Cost | [15 empty] | 1267.48 | 68548.75
|  |  | JDH3-02-008-L-65-Potable Water Network - WT |  | 2025-01-27 | 2025-02-16 | 2025-10-29 | 2025-11-18 | 0 | 0 | 69816.23 | Remaining Total Cost | [15 empty] | 1267.48 | 68548.75
|  |  | JDH3-02-008-L-65-Potable Water Network - WT |  | 2025-01-27 | 2025-02-16 | 2025-10-29 | 2025-11-18 | 0 | 0 | 69816.23 | Actual Total Cost
|  |  | JDH3-02-008-L-65-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-01-27 | 2025-02-16 | 2025-10-29 | 2025-11-18 | 0 | 0 | 6337.41 | Planned Total Cost | [15 empty] | 1267.48 | 5069.93
|  |  | JDH3-02-008-L-65-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-01-27 | 2025-02-16 | 2025-10-29 | 2025-11-18 | 0 | 0 | 6337.41 | Remaining Total Cost | [15 empty] | 1267.48 | 5069.93
|  |  | JDH3-02-008-L-65-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-01-27 | 2025-02-16 | 2025-10-29 | 2025-11-18 | 0 | 0 | 6337.41 | Actual Total Cost
|  |  | JDH3-02-008-L-65-(WT)- Supply and install 3-out fire hydrant |  | 2025-02-08 | 2025-02-13 | 2025-11-10 | 2025-11-16 | 0 | 0 | 63478.82 | Planned Total Cost | [16 empty] | 63478.82
|  |  | JDH3-02-008-L-65-(WT)- Supply and install 3-out fire hydrant |  | 2025-02-08 | 2025-02-13 | 2025-11-10 | 2025-11-16 | 0 | 0 | 63478.82 | Remaining Total Cost | [16 empty] | 63478.82
|  |  | JDH3-02-008-L-65-(WT)- Supply and install 3-out fire hydrant |  | 2025-02-08 | 2025-02-13 | 2025-11-10 | 2025-11-16 | 0 | 0 | 63478.82 | Actual Total Cost
|  |  | L-66 |  | 2024-12-10 | 2025-03-20 | 17-Mar-25 A | 2026-02-10 | 383076.39 | 383076.41 | 2108236.03 | Planned Total Cost | [6 empty] | 138273.63 | 278718.26 | [7 empty] | 113213.03 | 1305326.16 | 257365 |  | 15339.96
|  |  | L-66 |  | 2024-12-10 | 2025-03-20 | 17-Mar-25 A | 2026-02-10 | 383076.39 | 383076.41 | 2108236.03 | Remaining Total Cost | [15 empty] | 113213.03 | 1339241.65 | 257365 |  | 15339.96
|  |  | L-66 |  | 2024-12-10 | 2025-03-20 | 17-Mar-25 A | 2026-02-10 | 383076.39 | 383076.41 | 2108236.03 | Actual Total Cost | [9 empty] | 174941.62 | 112153.7 | 47180.53 | 14885.07 | 9376.67 | 23629.97 | 908.85
|  |  | JDH3-02-008-L-66-Storm Network - ST |  | 2025-01-13 | 2025-03-09 | 05-Apr-25 A | 2025-12-20 | 383076.39 | 383076.41 | 1880476.49 | Planned Total Cost | [6 empty] | 138273.63 | 278718.26 | [7 empty] | 113213.03 | 1276084.32 | 74187.26
|  |  | JDH3-02-008-L-66-Storm Network - ST |  | 2025-01-13 | 2025-03-09 | 05-Apr-25 A | 2025-12-20 | 383076.39 | 383076.41 | 1880476.49 | Remaining Total Cost | [15 empty] | 113213.03 | 1309999.81 | 74187.26
|  |  | JDH3-02-008-L-66-Storm Network - ST |  | 2025-01-13 | 2025-03-09 | 05-Apr-25 A | 2025-12-20 | 383076.39 | 383076.41 | 1880476.49 | Actual Total Cost | [9 empty] | 174941.62 | 112153.7 | 47180.53 | 14885.07 | 9376.67 | 23629.97 | 908.85
|  |  | JDH3-02-008-L-66-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-01-13 | 2025-03-04 | 2025-11-02 | 2025-12-15 | 0 | 0 | 274736.91 | Planned Total Cost | [16 empty] | 247263.22 | 27473.69
|  |  | JDH3-02-008-L-66-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-01-13 | 2025-03-04 | 2025-11-02 | 2025-12-15 | 0 | 0 | 274736.91 | Remaining Total Cost | [16 empty] | 247263.22 | 27473.69
|  |  | JDH3-02-008-L-66-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-01-13 | 2025-03-04 | 2025-11-02 | 2025-12-15 | 0 | 0 | 274736.91 | Actual Total Cost
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-01-16 | 2025-03-06 | 16-Aug-25 A | 2025-12-17 | 1992-11-07 11:46 | 1992-11-07 11:46 | 84788.73 | Planned Total Cost | [6 empty] | 67830.98 | [9 empty] | 8478.87 | 8478.87
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-01-16 | 2025-03-06 | 16-Aug-25 A | 2025-12-17 | 1992-11-07 11:46 | 1992-11-07 11:46 | 84788.73 | Remaining Total Cost | [16 empty] | 42394.37 | 8478.87
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-01-16 | 2025-03-06 | 16-Aug-25 A | 2025-12-17 | 1992-11-07 11:46 | 1992-11-07 11:46 | 84788.73 | Actual Total Cost | [13 empty] | 9376.67 | 23629.97 | 908.85
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-01-23 | 2025-03-09 | 2025-11-05 | 2025-12-20 | 0 | 0 | 7371.84 | Planned Total Cost | [16 empty] | 6634.66 | 737.18
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-01-23 | 2025-03-09 | 2025-11-05 | 2025-12-20 | 0 | 0 | 7371.84 | Remaining Total Cost | [16 empty] | 6634.66 | 737.18
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-01-23 | 2025-03-09 | 2025-11-05 | 2025-12-20 | 0 | 0 | 7371.84 | Actual Total Cost
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2025-01-26 | 2025-02-15 | 06-Apr-25 A | 2025-11-27 | 2014-08-29 13:41 | 2014-08-29 13:41 | 61031.4 | Planned Total Cost | [6 empty] | 24428.98 | 17451.59 | [8 empty] | 19150.84
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2025-01-26 | 2025-02-15 | 06-Apr-25 A | 2025-11-27 | 2014-08-29 13:41 | 2014-08-29 13:41 | 61031.4 | Remaining Total Cost | [16 empty] | 19150.84
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2025-01-26 | 2025-02-15 | 06-Apr-25 A | 2025-11-27 | 2014-08-29 13:41 | 2014-08-29 13:41 | 61031.4 | Actual Total Cost | [9 empty] | 41880.57
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2025-01-28 | 2025-02-15 | 05-Apr-25 A | 2025-11-27 | 2017-08-15 14:38 | 2017-08-15 14:38 | 53703.27 | Planned Total Cost | [6 empty] | 12083.24 | 30879.38 | [8 empty] | 10740.65
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2025-01-28 | 2025-02-15 | 05-Apr-25 A | 2025-11-27 | 2017-08-15 14:38 | 2017-08-15 14:38 | 53703.27 | Remaining Total Cost | [16 empty] | 10740.65
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2025-01-28 | 2025-02-15 | 05-Apr-25 A | 2025-11-27 | 2017-08-15 14:38 | 2017-08-15 14:38 | 53703.27 | Actual Total Cost | [9 empty] | 42962.61
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 0.00 to 1.50 m |  | 2025-01-30 | 2025-02-15 | 2025-10-02 | 2025-11-27 | 0 | 0 | 64573.26 | Planned Total Cost | [15 empty] | 58115.94 | 6457.33
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 0.00 to 1.50 m |  | 2025-01-30 | 2025-02-15 | 2025-10-02 | 2025-11-27 | 0 | 0 | 64573.26 | Remaining Total Cost | [15 empty] | 58115.94 | 6457.33
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 0.00 to 1.50 m |  | 2025-01-30 | 2025-02-15 | 2025-10-02 | 2025-11-27 | 0 | 0 | 64573.26 | Actual Total Cost
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-01-28 | 2025-02-12 | 05-Apr-25 A | 2025-11-20 | 2200-10-17 17:17 | 2200-10-17 17:31 | 173254.07 | Planned Total Cost | [6 empty] | 25873.71 | 83991.01 | [8 empty] | 63389.35
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-01-28 | 2025-02-12 | 05-Apr-25 A | 2025-11-20 | 2200-10-17 17:17 | 2200-10-17 17:31 | 173254.07 | Remaining Total Cost | [16 empty] | 63389.35
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2025-01-28 | 2025-02-12 | 05-Apr-25 A | 2025-11-20 | 2200-10-17 17:17 | 2200-10-17 17:31 | 173254.07 | Actual Total Cost | [9 empty] | 63162.03 | 39438.12 | 1515.97 | 5748.61
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 0.00 to 1.50 m |  | 2025-01-30 | 2025-02-15 | 2025-10-02 | 2025-11-27 | 0 | 0 | 68871.36 | Planned Total Cost | [15 empty] | 55097.09 | 13774.27
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 0.00 to 1.50 m |  | 2025-01-30 | 2025-02-15 | 2025-10-02 | 2025-11-27 | 0 | 0 | 68871.36 | Remaining Total Cost | [15 empty] | 55097.09 | 13774.27
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 0.00 to 1.50 m |  | 2025-01-30 | 2025-02-15 | 2025-10-02 | 2025-11-27 | 0 | 0 | 68871.36 | Actual Total Cost
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-01-30 | 2025-02-19 | 05-Apr-25 A | 2025-12-02 | 2164-08-14 12:58 | 2164-08-14 13:12 | 241717.55 | Planned Total Cost | [6 empty] | 8056.72 | 88595.82 | [8 empty] | 132979.13 | 12085.88
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-01-30 | 2025-02-19 | 05-Apr-25 A | 2025-12-02 | 2164-08-14 12:58 | 2164-08-14 13:12 | 241717.55 | Remaining Total Cost | [16 empty] | 132979.13 | 12085.88
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-01-30 | 2025-02-19 | 05-Apr-25 A | 2025-12-02 | 2164-08-14 12:58 | 2164-08-14 13:12 | 241717.55 | Actual Total Cost | [9 empty] | 26936.41 | 36493.62 | 33222.53
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 0.00 to 1.50 m |  | 2025-01-26 | 2025-02-17 | 2025-11-08 | 2025-11-30 | 0 | 0 | 152454.36 | Planned Total Cost | [16 empty] | 152454.36
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 0.00 to 1.50 m |  | 2025-01-26 | 2025-02-17 | 2025-11-08 | 2025-11-30 | 0 | 0 | 152454.36 | Remaining Total Cost | [16 empty] | 152454.36
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 0.00 to 1.50 m |  | 2025-01-26 | 2025-02-17 | 2025-11-08 | 2025-11-30 | 0 | 0 | 152454.36 | Actual Total Cost
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 0.00 to 1.50 m |  | 2025-01-28 | 2025-02-15 | 2025-11-10 | 2025-11-27 | 0 | 0 | 93268.23 | Planned Total Cost | [16 empty] | 93268.23
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 0.00 to 1.50 m |  | 2025-01-28 | 2025-02-15 | 2025-11-10 | 2025-11-27 | 0 | 0 | 93268.23 | Remaining Total Cost | [16 empty] | 93268.23
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 0.00 to 1.50 m |  | 2025-01-28 | 2025-02-15 | 2025-11-10 | 2025-11-27 | 0 | 0 | 93268.23 | Actual Total Cost
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2025-01-30 | 2025-02-22 | 2025-11-12 | 2025-12-04 | 0 | 0 | 80142.92 | Planned Total Cost | [16 empty] | 72128.62 | 8014.29
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2025-01-30 | 2025-02-22 | 2025-11-12 | 2025-12-04 | 0 | 0 | 80142.92 | Remaining Total Cost | [16 empty] | 72128.62 | 8014.29
|  |  | JDH3-02-008-L-66-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2025-01-30 | 2025-02-22 | 2025-11-12 | 2025-12-04 | 0 | 0 | 80142.92 | Actual Total Cost
|  |  | JDH3-02-008-L-66-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-02-02 | 2025-02-12 | 10-May-25 A | 2025-11-25 | 1957-02-06 09:22 | 1957-02-06 09:36 | 41714.79 | Planned Total Cost | [7 empty] | 20857.39 | [8 empty] | 20857.39
|  |  | JDH3-02-008-L-66-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-02-02 | 2025-02-12 | 10-May-25 A | 2025-11-25 | 1957-02-06 09:22 | 1957-02-06 09:36 | 41714.79 | Remaining Total Cost | [16 empty] | 20857.39
|  |  | JDH3-02-008-L-66-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-02-02 | 2025-02-12 | 10-May-25 A | 2025-11-25 | 1957-02-06 09:22 | 1957-02-06 09:36 | 41714.79 | Actual Total Cost | [10 empty] | 20857.4
|  |  | JDH3-02-008-L-66-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-02-03 | 2025-02-18 | 15-May-25 A | 2025-11-27 | 2001-02-21 01:26 | 2001-02-21 01:26 | 150564.31 | Planned Total Cost | [7 empty] | 36943.06 | [8 empty] | 113621.25
|  |  | JDH3-02-008-L-66-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-02-03 | 2025-02-18 | 15-May-25 A | 2025-11-27 | 2001-02-21 01:26 | 2001-02-21 01:26 | 150564.31 | Remaining Total Cost | [16 empty] | 113621.25
|  |  | JDH3-02-008-L-66-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-02-03 | 2025-02-18 | 15-May-25 A | 2025-11-27 | 2001-02-21 01:26 | 2001-02-21 01:26 | 150564.31 | Actual Total Cost | [10 empty] | 15364.57 | 12442.03 | 9136.46
|  |  | JDH3-02-008-L-66-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-02-02 | 2025-02-24 | 2025-11-15 | 2025-12-07 | 0 | 0 | 36500.43 | Planned Total Cost | [16 empty] | 32850.39 | 3650.04
|  |  | JDH3-02-008-L-66-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-02-02 | 2025-02-24 | 2025-11-15 | 2025-12-07 | 0 | 0 | 36500.43 | Remaining Total Cost | [16 empty] | 32850.39 | 3650.04
|  |  | JDH3-02-008-L-66-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-02-02 | 2025-02-24 | 2025-11-15 | 2025-12-07 | 0 | 0 | 36500.43 | Actual Total Cost
|  |  | JDH3-02-008-L-66-(ST)- Single Catchbasine Works |  | 2025-02-04 | 2025-02-26 | 2025-11-17 | 2025-12-09 | 0 | 0 | 70393.74 | Planned Total Cost | [16 empty] | 66874.05 | 3519.69
|  |  | JDH3-02-008-L-66-(ST)- Single Catchbasine Works |  | 2025-02-04 | 2025-02-26 | 2025-11-17 | 2025-12-09 | 0 | 0 | 70393.74 | Remaining Total Cost | [16 empty] | 66874.05 | 3519.69
|  |  | JDH3-02-008-L-66-(ST)- Single Catchbasine Works |  | 2025-02-04 | 2025-02-26 | 2025-11-17 | 2025-12-09 | 0 | 0 | 70393.74 | Actual Total Cost
|  |  | JDH3-02-008-L-66-(ST)- Double Catchbasine Works |  | 2025-02-06 | 2025-03-01 | 2025-11-19 | 2025-12-11 | 0 | 0 | 204552.31 | Planned Total Cost | [16 empty] | 194324.7 | 10227.62
|  |  | JDH3-02-008-L-66-(ST)- Double Catchbasine Works |  | 2025-02-06 | 2025-03-01 | 2025-11-19 | 2025-12-11 | 0 | 0 | 204552.31 | Remaining Total Cost | [16 empty] | 194324.7 | 10227.62
|  |  | JDH3-02-008-L-66-(ST)- Double Catchbasine Works |  | 2025-02-06 | 2025-03-01 | 2025-11-19 | 2025-12-11 | 0 | 0 | 204552.31 | Actual Total Cost
|  |  | JDH3-02-008-L-66-(ST)-PIPES ENCASEMENT |  | 2025-02-06 | 2025-02-12 | 2025-11-19 | 2025-11-25 | 0 | 0 | 20837 | Planned Total Cost | [16 empty] | 20837
|  |  | JDH3-02-008-L-66-(ST)-PIPES ENCASEMENT |  | 2025-02-06 | 2025-02-12 | 2025-11-19 | 2025-11-25 | 0 | 0 | 20837 | Remaining Total Cost | [16 empty] | 20837
|  |  | JDH3-02-008-L-66-(ST)-PIPES ENCASEMENT |  | 2025-02-06 | 2025-02-12 | 2025-11-19 | 2025-11-25 | 0 | 0 | 20837 | Actual Total Cost
|  |  | JDH3-02-008-L-66-TSE Network - TSE |  | 2025-02-09 | 2025-03-13 | 2025-11-22 | 2026-02-10 | 0 | 0 | 157943.31 | Planned Total Cost | [16 empty] | 29241.84 | 113361.51 |  | 15339.96
|  |  | JDH3-02-008-L-66-TSE Network - TSE |  | 2025-02-09 | 2025-03-13 | 2025-11-22 | 2026-02-10 | 0 | 0 | 157943.31 | Remaining Total Cost | [16 empty] | 29241.84 | 113361.51 |  | 15339.96
|  |  | JDH3-02-008-L-66-TSE Network - TSE |  | 2025-02-09 | 2025-03-13 | 2025-11-22 | 2026-02-10 | 0 | 0 | 157943.31 | Actual Total Cost
|  |  | JDH3-02-008-L-66-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-02-09 | 2025-03-13 | 2025-11-22 | 2025-12-24 | 0 | 0 | 90365.02 | Planned Total Cost | [16 empty] | 21687.61 | 68677.42
|  |  | JDH3-02-008-L-66-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-02-09 | 2025-03-13 | 2025-11-22 | 2025-12-24 | 0 | 0 | 90365.02 | Remaining Total Cost | [16 empty] | 21687.61 | 68677.42
|  |  | JDH3-02-008-L-66-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-02-09 | 2025-03-13 | 2025-11-22 | 2025-12-24 | 0 | 0 | 90365.02 | Actual Total Cost
|  |  | JDH3-02-008-L-66-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2025-02-13 | 2025-02-24 | 2025-11-26 | 2025-12-07 | 0 | 0 | 10943.92 | Planned Total Cost | [16 empty] | 2735.98 | 8207.94
|  |  | JDH3-02-008-L-66-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2025-02-13 | 2025-02-24 | 2025-11-26 | 2025-12-07 | 0 | 0 | 10943.92 | Remaining Total Cost | [16 empty] | 2735.98 | 8207.94
|  |  | JDH3-02-008-L-66-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2025-02-13 | 2025-02-24 | 2025-11-26 | 2025-12-07 | 0 | 0 | 10943.92 | Actual Total Cost
|  |  | JDH3-02-008-L-66-(TSE)-Supply and install gate valves-100 mm |  | 2025-03-01 | 2025-03-04 | 2025-12-11 | 2025-12-15 | 0 | 0 | 10345.28 | Planned Total Cost | [17 empty] | 10345.28
|  |  | JDH3-02-008-L-66-(TSE)-Supply and install gate valves-100 mm |  | 2025-03-01 | 2025-03-04 | 2025-12-11 | 2025-12-15 | 0 | 0 | 10345.28 | Remaining Total Cost | [17 empty] | 10345.28
|  |  | JDH3-02-008-L-66-(TSE)-Supply and install gate valves-100 mm |  | 2025-03-01 | 2025-03-04 | 2025-12-11 | 2025-12-15 | 0 | 0 | 10345.28 | Actual Total Cost
|  |  | JDH3-02-008-L-66-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2025-03-01 | 2025-03-04 | 2026-02-07 | 2026-02-10 | 0 | 0 | 15339.96 | Planned Total Cost | [19 empty] | 15339.96
|  |  | JDH3-02-008-L-66-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2025-03-01 | 2025-03-04 | 2026-02-07 | 2026-02-10 | 0 | 0 | 15339.96 | Remaining Total Cost | [19 empty] | 15339.96
|  |  | JDH3-02-008-L-66-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2025-03-01 | 2025-03-04 | 2026-02-07 | 2026-02-10 | 0 | 0 | 15339.96 | Actual Total Cost
|  |  | JDH3-02-008-L-66-(TSE)-Supply and install of Air valves-50 mm. |  | 2025-03-01 | 2025-03-04 | 2025-12-11 | 2025-12-15 | 0 | 0 | 14888.27 | Planned Total Cost | [17 empty] | 14888.27
|  |  | JDH3-02-008-L-66-(TSE)-Supply and install of Air valves-50 mm. |  | 2025-03-01 | 2025-03-04 | 2025-12-11 | 2025-12-15 | 0 | 0 | 14888.27 | Remaining Total Cost | [17 empty] | 14888.27
|  |  | JDH3-02-008-L-66-(TSE)-Supply and install of Air valves-50 mm. |  | 2025-03-01 | 2025-03-04 | 2025-12-11 | 2025-12-15 | 0 | 0 | 14888.27 | Actual Total Cost
|  |  | JDH3-02-008-L-66-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2025-02-13 | 2025-02-22 | 2025-11-26 | 2025-12-04 | 0 | 0 | 9102.3 | Planned Total Cost | [16 empty] | 2730.69 | 6371.61
|  |  | JDH3-02-008-L-66-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2025-02-13 | 2025-02-22 | 2025-11-26 | 2025-12-04 | 0 | 0 | 9102.3 | Remaining Total Cost | [16 empty] | 2730.69 | 6371.61
|  |  | JDH3-02-008-L-66-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2025-02-13 | 2025-02-22 | 2025-11-26 | 2025-12-04 | 0 | 0 | 9102.3 | Actual Total Cost
|  |  | JDH3-02-008-L-66-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2025-02-13 | 2025-02-22 | 2025-11-26 | 2025-12-04 | 0 | 0 | 6958.55 | Planned Total Cost | [16 empty] | 2087.57 | 4870.99
|  |  | JDH3-02-008-L-66-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2025-02-13 | 2025-02-22 | 2025-11-26 | 2025-12-04 | 0 | 0 | 6958.55 | Remaining Total Cost | [16 empty] | 2087.57 | 4870.99
|  |  | JDH3-02-008-L-66-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2025-02-13 | 2025-02-22 | 2025-11-26 | 2025-12-04 | 0 | 0 | 6958.55 | Actual Total Cost
|  |  | JDH3-02-008-L-66-Potable Water Network - WT |  | 2025-03-10 | 2025-03-20 | 2025-12-21 | 2025-12-31 | 0 | 0 | 69816.23 | Planned Total Cost | [17 empty] | 69816.23
|  |  | JDH3-02-008-L-66-Potable Water Network - WT |  | 2025-03-10 | 2025-03-20 | 2025-12-21 | 2025-12-31 | 0 | 0 | 69816.23 | Remaining Total Cost | [17 empty] | 69816.23
|  |  | JDH3-02-008-L-66-Potable Water Network - WT |  | 2025-03-10 | 2025-03-20 | 2025-12-21 | 2025-12-31 | 0 | 0 | 69816.23 | Actual Total Cost
|  |  | JDH3-02-008-L-66-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-03-10 | 2025-03-20 | 2025-12-21 | 2025-12-31 | 0 | 0 | 6337.41 | Planned Total Cost | [17 empty] | 6337.41
|  |  | JDH3-02-008-L-66-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-03-10 | 2025-03-20 | 2025-12-21 | 2025-12-31 | 0 | 0 | 6337.41 | Remaining Total Cost | [17 empty] | 6337.41
|  |  | JDH3-02-008-L-66-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-03-10 | 2025-03-20 | 2025-12-21 | 2025-12-31 | 0 | 0 | 6337.41 | Actual Total Cost
|  |  | JDH3-02-008-L-66-(WT)- Supply and install 3-out fire hydrant |  | 2025-03-12 | 2025-03-18 | 2025-12-23 | 2025-12-29 | 0 | 0 | 63478.82 | Planned Total Cost | [17 empty] | 63478.82
|  |  | JDH3-02-008-L-66-(WT)- Supply and install 3-out fire hydrant |  | 2025-03-12 | 2025-03-18 | 2025-12-23 | 2025-12-29 | 0 | 0 | 63478.82 | Remaining Total Cost | [17 empty] | 63478.82
|  |  | JDH3-02-008-L-66-(WT)- Supply and install 3-out fire hydrant |  | 2025-03-12 | 2025-03-18 | 2025-12-23 | 2025-12-29 | 0 | 0 | 63478.82 | Actual Total Cost
|  |  | L-67 |  | 2024-12-18 | 2025-03-19 | 12-Nov-24 A | 2026-02-10 | 2397-06-16 09:36 | 2397-06-16 09:50 | 843744.36 | Planned Total Cost | [6 empty] | 79707.63 | 137797.44 | 2135.58 | [6 empty] | 4271.17 | 566973.61 | 37518.97 |  | 15339.96
|  |  | L-67 |  | 2024-12-18 | 2025-03-19 | 12-Nov-24 A | 2026-02-10 | 2397-06-16 09:36 | 2397-06-16 09:50 | 843744.36 | Remaining Total Cost | [15 empty] | 7570.21 | 599582.51 | 39557.28 |  | 15339.96
|  |  | L-67 |  | 2024-12-18 | 2025-03-19 | 12-Nov-24 A | 2026-02-10 | 2397-06-16 09:36 | 2397-06-16 09:50 | 843744.36 | Actual Total Cost | [5 empty] | 7407.62 | 43583.43 | 11391.2 | 12436.92 | 38493.53 | 21133.52 | 4778.09 | 7511 | 4969.82 | 28878.56 | 1110.71
|  |  | JDH3-02-008-L-67-Storm Network - ST |  | 2025-01-16 | 2025-02-19 | 04-Dec-24 A | 2025-11-27 | 2247-07-26 09:22 | 2247-07-26 09:22 | 729388.62 | Planned Total Cost | [6 empty] | 79707.63 | 83147.7 | [8 empty] | 566533.29
|  |  | JDH3-02-008-L-67-Storm Network - ST |  | 2025-01-16 | 2025-02-19 | 04-Dec-24 A | 2025-11-27 | 2247-07-26 09:22 | 2247-07-26 09:22 | 729388.62 | Remaining Total Cost | [15 empty] | 3299.04 | 599142.19
|  |  | JDH3-02-008-L-67-Storm Network - ST |  | 2025-01-16 | 2025-02-19 | 04-Dec-24 A | 2025-11-27 | 2247-07-26 09:22 | 2247-07-26 09:22 | 729388.62 | Actual Total Cost | [5 empty] | 7407.62 | 43583.43 | 11391.2 | 12436.92 | 2566.07 | 6585.13 | 506.92 | 7511 | 4969.82 | 28878.56 | 1110.71
|  |  | JDH3-02-008-L-67-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-01-16 | 2025-01-27 | 2025-11-05 | 2025-11-16 | 0 | 0 | 100417.35 | Planned Total Cost | [16 empty] | 100417.35
|  |  | JDH3-02-008-L-67-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-01-16 | 2025-01-27 | 2025-11-05 | 2025-11-16 | 0 | 0 | 100417.35 | Remaining Total Cost | [16 empty] | 100417.35
|  |  | JDH3-02-008-L-67-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-01-16 | 2025-01-27 | 2025-11-05 | 2025-11-16 | 0 | 0 | 100417.35 | Actual Total Cost
|  |  | JDH3-02-008-L-67-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-01-19 | 2025-02-01 | 26-Apr-25 A | 2025-11-18 | 1920-08-19 12:00 | 1920-08-19 12:00 | 84929.55 | Planned Total Cost | [6 empty] | 7537.5 | [9 empty] | 77392.06
|  |  | JDH3-02-008-L-67-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-01-19 | 2025-02-01 | 26-Apr-25 A | 2025-11-18 | 1920-08-19 12:00 | 1920-08-19 12:00 | 84929.55 | Remaining Total Cost | [16 empty] | 77392.06
|  |  | JDH3-02-008-L-67-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-01-19 | 2025-02-01 | 26-Apr-25 A | 2025-11-18 | 1920-08-19 12:00 | 1920-08-19 12:00 | 84929.55 | Actual Total Cost | [9 empty] | 2355.47 | 5182.03
|  |  | JDH3-02-008-L-67-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-01-23 | 2025-02-03 | 2025-11-10 | 2025-11-20 | 0 | 0 | 6441.07 | Planned Total Cost | [16 empty] | 6441.07
|  |  | JDH3-02-008-L-67-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-01-23 | 2025-02-03 | 2025-11-10 | 2025-11-20 | 0 | 0 | 6441.07 | Remaining Total Cost | [16 empty] | 6441.07
|  |  | JDH3-02-008-L-67-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-01-23 | 2025-02-03 | 2025-11-10 | 2025-11-20 | 0 | 0 | 6441.07 | Actual Total Cost
|  |  | JDH3-02-008-L-67-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2025-01-26 | 2025-02-05 | 23-Aug-25 A | 2025-11-16 | 1994-05-19 19:12 | 1994-05-19 19:12 | 83853.37 | Planned Total Cost | [6 empty] | 44023.02 | 23059.68 | [8 empty] | 16770.68
|  |  | JDH3-02-008-L-67-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2025-01-26 | 2025-02-05 | 23-Aug-25 A | 2025-11-16 | 1994-05-19 19:12 | 1994-05-19 19:12 | 83853.37 | Remaining Total Cost | [16 empty] | 49379.57
|  |  | JDH3-02-008-L-67-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2025-01-26 | 2025-02-05 | 23-Aug-25 A | 2025-11-16 | 1994-05-19 19:12 | 1994-05-19 19:12 | 83853.37 | Actual Total Cost | [13 empty] | 4731.75 | 28640.49 | 1101.56
|  |  | JDH3-02-008-L-67-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2025-02-06 | 2025-02-17 | 05-Jan-25 A | 2025-10-04 | 2020-02-23 00:58 | 2020-02-23 01:12 | 47183.09 | Planned Total Cost | [7 empty] | 47183.09
|  |  | JDH3-02-008-L-67-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2025-02-06 | 2025-02-17 | 05-Jan-25 A | 2025-10-04 | 2020-02-23 00:58 | 2020-02-23 01:12 | 47183.09 | Remaining Total Cost | [15 empty] | 3299.04
|  |  | JDH3-02-008-L-67-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2025-02-06 | 2025-02-17 | 05-Jan-25 A | 2025-10-04 | 2020-02-23 00:58 | 2020-02-23 01:12 | 47183.09 | Actual Total Cost | [6 empty] | 37746.47 | 884.68 | 3833.63 | 210.6 | 238.07 | 238.07 | 247.23 | 238.07 | 238.07 | 9.16
|  |  | JDH3-02-008-L-67-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-02-09 | 2025-02-19 | 04-Dec-24 A | 2025-11-18 | 1935-04-30 22:19 | 1935-04-30 22:19 | 14338.81 | Planned Total Cost | [7 empty] | 12904.93 | [8 empty] | 1433.88
|  |  | JDH3-02-008-L-67-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-02-09 | 2025-02-19 | 04-Dec-24 A | 2025-11-18 | 1935-04-30 22:19 | 1935-04-30 22:19 | 14338.81 | Remaining Total Cost | [16 empty] | 1433.88
|  |  | JDH3-02-008-L-67-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2025-02-09 | 2025-02-19 | 04-Dec-24 A | 2025-11-18 | 1935-04-30 22:19 | 1935-04-30 22:19 | 14338.81 | Actual Total Cost | [5 empty] | 2867.76 |  |  | 8603.29 |  | 1165.03 | 268.85
|  |  | JDH3-02-008-L-67-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-01-28 | 2025-02-08 | 2025-11-12 | 2025-11-23 | 0 | 0 | 125498.43 | Planned Total Cost | [16 empty] | 125498.43
|  |  | JDH3-02-008-L-67-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-01-28 | 2025-02-08 | 2025-11-12 | 2025-11-23 | 0 | 0 | 125498.43 | Remaining Total Cost | [16 empty] | 125498.43
|  |  | JDH3-02-008-L-67-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2025-01-28 | 2025-02-08 | 2025-11-12 | 2025-11-23 | 0 | 0 | 125498.43 | Actual Total Cost
|  |  | JDH3-02-008-L-67-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-01-21 | 2025-02-10 | 24-Dec-24 A | 2025-11-25 | 1977-01-22 02:53 | 1977-01-22 02:38 | 52143.49 | Planned Total Cost | [6 empty] | 28147.12 | [9 empty] | 23996.37
|  |  | JDH3-02-008-L-67-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-01-21 | 2025-02-10 | 24-Dec-24 A | 2025-11-25 | 1977-01-22 02:53 | 1977-01-22 02:38 | 52143.49 | Remaining Total Cost | [16 empty] | 23996.37
|  |  | JDH3-02-008-L-67-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-01-21 | 2025-02-10 | 24-Dec-24 A | 2025-11-25 | 1977-01-22 02:53 | 1977-01-22 02:38 | 52143.49 | Actual Total Cost | [5 empty] | 4539.86 | 5836.96 | 10506.52 |  |  |  |  | 7263.77
|  |  | JDH3-02-008-L-67-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-01-30 | 2025-02-10 | 2025-11-15 | 2025-11-25 | 0 | 0 | 43018.37 | Planned Total Cost | [16 empty] | 43018.37
|  |  | JDH3-02-008-L-67-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-01-30 | 2025-02-10 | 2025-11-15 | 2025-11-25 | 0 | 0 | 43018.37 | Remaining Total Cost | [16 empty] | 43018.37
|  |  | JDH3-02-008-L-67-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2025-01-30 | 2025-02-10 | 2025-11-15 | 2025-11-25 | 0 | 0 | 43018.37 | Actual Total Cost
|  |  | JDH3-02-008-L-67-(ST)- Single Catchbasine Works |  | 2025-02-02 | 2025-02-10 | 2025-11-17 | 2025-11-25 | 0 | 0 | 35196.87 | Planned Total Cost | [16 empty] | 35196.87
|  |  | JDH3-02-008-L-67-(ST)- Single Catchbasine Works |  | 2025-02-02 | 2025-02-10 | 2025-11-17 | 2025-11-25 | 0 | 0 | 35196.87 | Remaining Total Cost | [16 empty] | 35196.87
|  |  | JDH3-02-008-L-67-(ST)- Single Catchbasine Works |  | 2025-02-02 | 2025-02-10 | 2025-11-17 | 2025-11-25 | 0 | 0 | 35196.87 | Actual Total Cost
|  |  | JDH3-02-008-L-67-(ST)- Double Catchbasine Works |  | 2025-02-04 | 2025-02-12 | 2025-11-19 | 2025-11-27 | 0 | 0 | 136368.21 | Planned Total Cost | [16 empty] | 136368.21
|  |  | JDH3-02-008-L-67-(ST)- Double Catchbasine Works |  | 2025-02-04 | 2025-02-12 | 2025-11-19 | 2025-11-27 | 0 | 0 | 136368.21 | Remaining Total Cost | [16 empty] | 136368.21
|  |  | JDH3-02-008-L-67-(ST)- Double Catchbasine Works |  | 2025-02-04 | 2025-02-12 | 2025-11-19 | 2025-11-27 | 0 | 0 | 136368.21 | Actual Total Cost
|  |  | JDH3-02-008-L-67-TSE Network - TSE |  | 2025-02-13 | 2025-03-08 | 05-Apr-25 A | 2026-02-10 | 2049-11-20 00:14 | 2049-11-20 00:29 | 92325.02 | Planned Total Cost | [7 empty] | 54649.74 | 2135.58 | [6 empty] | 4271.17 | 440.33 | 15488.24 |  | 15339.96
|  |  | JDH3-02-008-L-67-TSE Network - TSE |  | 2025-02-13 | 2025-03-08 | 05-Apr-25 A | 2026-02-10 | 2049-11-20 00:14 | 2049-11-20 00:29 | 92325.02 | Remaining Total Cost | [15 empty] | 4271.17 | 440.33 | 17526.55 |  | 15339.96
|  |  | JDH3-02-008-L-67-TSE Network - TSE |  | 2025-02-13 | 2025-03-08 | 05-Apr-25 A | 2026-02-10 | 2049-11-20 00:14 | 2049-11-20 00:29 | 92325.02 | Actual Total Cost | [9 empty] | 35927.46 | 14548.4 | 4271.17
|  |  | JDH3-02-008-L-67-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-02-13 | 2025-03-08 | 2025-11-29 | 2025-12-11 | 0 | 0 | 2201.63 | Planned Total Cost | [16 empty] | 440.33 | 1761.31
|  |  | JDH3-02-008-L-67-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-02-13 | 2025-03-08 | 2025-11-29 | 2025-12-11 | 0 | 0 | 2201.63 | Remaining Total Cost | [16 empty] | 440.33 | 1761.31
|  |  | JDH3-02-008-L-67-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-02-13 | 2025-03-08 | 2025-11-29 | 2025-12-11 | 0 | 0 | 2201.63 | Actual Total Cost
|  |  | JDH3-02-008-L-67-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2025-02-16 | 2025-02-26 | 05-Apr-25 A | 2025-12-09 | 1944-08-22 12:00 | 1944-08-22 12:00 | 20383.12 | Planned Total Cost | [7 empty] | 18344.81 | [9 empty] | 2038.31
|  |  | JDH3-02-008-L-67-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2025-02-16 | 2025-02-26 | 05-Apr-25 A | 2025-12-09 | 1944-08-22 12:00 | 1944-08-22 12:00 | 20383.12 | Remaining Total Cost | [17 empty] | 4076.62
|  |  | JDH3-02-008-L-67-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 0 to 1.5 m |  | 2025-02-16 | 2025-02-26 | 05-Apr-25 A | 2025-12-09 | 1944-08-22 12:00 | 1944-08-22 12:00 | 20383.12 | Actual Total Cost | [9 empty] | 13503.82 | 2802.68
|  |  | JDH3-02-008-L-67-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2025-02-18 | 2025-03-01 | 05-Apr-25 A | 2025-10-04 | 2005-03-29 12:29 | 2005-03-29 12:29 | 42711.69 | Planned Total Cost | [7 empty] | 36304.93 | 2135.58 | [6 empty] | 4271.17
|  |  | JDH3-02-008-L-67-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2025-02-18 | 2025-03-01 | 05-Apr-25 A | 2025-10-04 | 2005-03-29 12:29 | 2005-03-29 12:29 | 42711.69 | Remaining Total Cost | [15 empty] | 4271.17
|  |  | JDH3-02-008-L-67-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2025-02-18 | 2025-03-01 | 05-Apr-25 A | 2025-10-04 | 2005-03-29 12:29 | 2005-03-29 12:29 | 42711.69 | Actual Total Cost | [9 empty] | 22423.63 | 11745.72 | 4271.17
|  |  | JDH3-02-008-L-67-(TSE)-Supply and install gate valves-100 mm |  | 2025-03-02 | 2025-03-05 | 2025-12-06 | 2025-12-09 | 0 | 0 | 2586.32 | Planned Total Cost | [17 empty] | 2586.32
|  |  | JDH3-02-008-L-67-(TSE)-Supply and install gate valves-100 mm |  | 2025-03-02 | 2025-03-05 | 2025-12-06 | 2025-12-09 | 0 | 0 | 2586.32 | Remaining Total Cost | [17 empty] | 2586.32
|  |  | JDH3-02-008-L-67-(TSE)-Supply and install gate valves-100 mm |  | 2025-03-02 | 2025-03-05 | 2025-12-06 | 2025-12-09 | 0 | 0 | 2586.32 | Actual Total Cost
|  |  | JDH3-02-008-L-67-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2025-02-20 | 2025-02-24 | 2026-02-07 | 2026-02-10 | 0 | 0 | 15339.96 | Planned Total Cost | [19 empty] | 15339.96
|  |  | JDH3-02-008-L-67-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2025-02-20 | 2025-02-24 | 2026-02-07 | 2026-02-10 | 0 | 0 | 15339.96 | Remaining Total Cost | [19 empty] | 15339.96
|  |  | JDH3-02-008-L-67-(TSE)-Supply and install of butterfly valves-300 mm. |  | 2025-02-20 | 2025-02-24 | 2026-02-07 | 2026-02-10 | 0 | 0 | 15339.96 | Actual Total Cost
|  |  | JDH3-02-008-L-67-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2025-02-16 | 2025-02-24 | 2025-12-01 | 2025-12-09 | 0 | 0 | 9102.3 | Planned Total Cost | [17 empty] | 9102.3
|  |  | JDH3-02-008-L-67-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2025-02-16 | 2025-02-24 | 2025-12-01 | 2025-12-09 | 0 | 0 | 9102.3 | Remaining Total Cost | [17 empty] | 9102.3
|  |  | JDH3-02-008-L-67-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2025-02-16 | 2025-02-24 | 2025-12-01 | 2025-12-09 | 0 | 0 | 9102.3 | Actual Total Cost
|  |  | JDH3-02-008-L-67-Potable Water Network - WT |  | 2025-03-09 | 2025-03-19 | 2025-12-13 | 2025-12-23 | 0 | 0 | 22030.73 | Planned Total Cost | [17 empty] | 22030.73
|  |  | JDH3-02-008-L-67-Potable Water Network - WT |  | 2025-03-09 | 2025-03-19 | 2025-12-13 | 2025-12-23 | 0 | 0 | 22030.73 | Remaining Total Cost | [17 empty] | 22030.73
|  |  | JDH3-02-008-L-67-Potable Water Network - WT |  | 2025-03-09 | 2025-03-19 | 2025-12-13 | 2025-12-23 | 0 | 0 | 22030.73 | Actual Total Cost
|  |  | JDH3-02-008-L-67-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-03-09 | 2025-03-19 | 2025-12-13 | 2025-12-23 | 0 | 0 | 3893.92 | Planned Total Cost | [17 empty] | 3893.92
|  |  | JDH3-02-008-L-67-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-03-09 | 2025-03-19 | 2025-12-13 | 2025-12-23 | 0 | 0 | 3893.92 | Remaining Total Cost | [17 empty] | 3893.92
|  |  | JDH3-02-008-L-67-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-03-09 | 2025-03-19 | 2025-12-13 | 2025-12-23 | 0 | 0 | 3893.92 | Actual Total Cost
|  |  | JDH3-02-008-L-67-(WT)- Supply and install 3-out fire hydrant |  | 2025-03-09 | 2025-03-15 | 2025-12-13 | 2025-12-18 | 0 | 0 | 18136.81 | Planned Total Cost | [17 empty] | 18136.81
|  |  | JDH3-02-008-L-67-(WT)- Supply and install 3-out fire hydrant |  | 2025-03-09 | 2025-03-15 | 2025-12-13 | 2025-12-18 | 0 | 0 | 18136.81 | Remaining Total Cost | [17 empty] | 18136.81
|  |  | JDH3-02-008-L-67-(WT)- Supply and install 3-out fire hydrant |  | 2025-03-09 | 2025-03-15 | 2025-12-13 | 2025-12-18 | 0 | 0 | 18136.81 | Actual Total Cost
|  |  | L-68 |  | 2024-12-26 | 2025-03-29 | 11-Feb-25 A | 2026-01-03 | 408884.21 | 408884.22 | 895349.88 | Planned Total Cost | [7 empty] | 321301.77 | 87582.45 | [6 empty] | 175655.03 | 184543.78 | 125882.32 | 384.54
|  |  | L-68 |  | 2024-12-26 | 2025-03-29 | 11-Feb-25 A | 2026-01-03 | 408884.21 | 408884.22 | 895349.88 | Remaining Total Cost | [15 empty] | 175655.03 | 184543.78 | 125882.32 | 384.54
|  |  | L-68 |  | 2024-12-26 | 2025-03-29 | 11-Feb-25 A | 2026-01-03 | 408884.21 | 408884.22 | 895349.88 | Actual Total Cost | [8 empty] | 253291.43 | 48043.21 | 38244.59 | 35997.37 | 3899.08 | 29408.54
|  |  | JDH3-02-008-L-68-Storm Network - ST |  | 2025-01-25 | 2025-03-02 | 03-Mar-25 A | 2025-12-08 | 321301.77 | 321301.78 | 760955.34 | Planned Total Cost | [7 empty] | 321301.77 | [7 empty] | 175655.03 | 184543.78 | 79454.76
|  |  | JDH3-02-008-L-68-Storm Network - ST |  | 2025-01-25 | 2025-03-02 | 03-Mar-25 A | 2025-12-08 | 321301.77 | 321301.78 | 760955.34 | Remaining Total Cost | [15 empty] | 175655.03 | 184543.78 | 79454.76
|  |  | JDH3-02-008-L-68-Storm Network - ST |  | 2025-01-25 | 2025-03-02 | 03-Mar-25 A | 2025-12-08 | 321301.77 | 321301.78 | 760955.34 | Actual Total Cost | [8 empty] | 253291.43 | 21129.85 | 8685.51 | 5434.75 | 3351.69 | 29408.54
|  |  | JDH3-02-008-L-68-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-01-25 | 2025-02-04 | 2025-11-13 | 2025-11-24 | 0 | 0 | 90542.61 | Planned Total Cost | [16 empty] | 90542.61
|  |  | JDH3-02-008-L-68-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-01-25 | 2025-02-04 | 2025-11-13 | 2025-11-24 | 0 | 0 | 90542.61 | Remaining Total Cost | [16 empty] | 90542.61
|  |  | JDH3-02-008-L-68-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2025-01-25 | 2025-02-04 | 2025-11-13 | 2025-11-24 | 0 | 0 | 90542.61 | Actual Total Cost
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-01-27 | 2025-02-06 | 2025-11-16 | 2025-11-26 | 0 | 0 | 30456.15 | Planned Total Cost | [16 empty] | 30456.15
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-01-27 | 2025-02-06 | 2025-11-16 | 2025-11-26 | 0 | 0 | 30456.15 | Remaining Total Cost | [16 empty] | 30456.15
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2025-01-27 | 2025-02-06 | 2025-11-16 | 2025-11-26 | 0 | 0 | 30456.15 | Actual Total Cost
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-01-29 | 2025-02-09 | 2025-11-18 | 2025-11-29 | 0 | 0 | 2976.11 | Planned Total Cost | [16 empty] | 2976.11
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-01-29 | 2025-02-09 | 2025-11-18 | 2025-11-29 | 0 | 0 | 2976.11 | Remaining Total Cost | [16 empty] | 2976.11
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2025-01-29 | 2025-02-09 | 2025-11-18 | 2025-11-29 | 0 | 0 | 2976.11 | Actual Total Cost
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2025-02-01 | 2025-02-11 | 11-Mar-25 A | 2025-12-01 | 1987-12-30 00:43 | 1987-12-30 00:43 | 40176.29 | Planned Total Cost | [7 empty] | 32141.03 | [8 empty] | 6026.44 | 2008.81
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2025-02-01 | 2025-02-11 | 11-Mar-25 A | 2025-12-01 | 1987-12-30 00:43 | 1987-12-30 00:43 | 40176.29 | Remaining Total Cost | [16 empty] | 6026.44 | 2008.81
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2025-02-01 | 2025-02-11 | 11-Mar-25 A | 2025-12-01 | 1987-12-30 00:43 | 1987-12-30 00:43 | 40176.29 | Actual Total Cost | [8 empty] | 25235.73 | 6905.3
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2025-02-01 | 2025-02-11 | 2025-11-20 | 2025-12-01 | 0 | 0 | 13158.01 | Planned Total Cost | [16 empty] | 12500.11 | 657.9
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2025-02-01 | 2025-02-11 | 2025-11-20 | 2025-12-01 | 0 | 0 | 13158.01 | Remaining Total Cost | [16 empty] | 12500.11 | 657.9
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2025-02-01 | 2025-02-11 | 2025-11-20 | 2025-12-01 | 0 | 0 | 13158.01 | Actual Total Cost
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 0.00 to 1.50 m |  | 2025-02-03 | 2025-02-13 | 03-Mar-25 A | 2025-12-03 | 2144-04-04 12:00 | 2144-04-04 11:46 | 111519.37 | Planned Total Cost | [7 empty] | 89215.5 | [8 empty] | 5575.97 | 16727.91
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 0.00 to 1.50 m |  | 2025-02-03 | 2025-02-13 | 03-Mar-25 A | 2025-12-03 | 2144-04-04 12:00 | 2144-04-04 11:46 | 111519.37 | Remaining Total Cost | [16 empty] | 5575.97 | 16727.91
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 0.00 to 1.50 m |  | 2025-02-03 | 2025-02-13 | 03-Mar-25 A | 2025-12-03 | 2144-04-04 12:00 | 2144-04-04 11:46 | 111519.37 | Actual Total Cost | [8 empty] | 89215.49
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-02-05 | 2025-02-16 | 18-Mar-25 A | 2025-12-06 | 2014-08-05 03:22 | 2014-08-05 03:36 | 52320.18 | Planned Total Cost | [7 empty] | 41856.14 | [9 empty] | 10464.04
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-02-05 | 2025-02-16 | 18-Mar-25 A | 2025-12-06 | 2014-08-05 03:22 | 2014-08-05 03:36 | 52320.18 | Remaining Total Cost | [17 empty] | 10464.04
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2025-02-05 | 2025-02-16 | 18-Mar-25 A | 2025-12-06 | 2014-08-05 03:22 | 2014-08-05 03:36 | 52320.18 | Actual Total Cost | [8 empty] | 27631.6 | 14224.55
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2025-02-08 | 2025-02-18 | 04-Mar-25 A | 2025-12-08 | 2166-11-22 00:29 | 2166-11-22 00:43 | 121852.53 | Planned Total Cost | [7 empty] | 97482.02 | [9 empty] | 24370.51
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2025-02-08 | 2025-02-18 | 04-Mar-25 A | 2025-12-08 | 2166-11-22 00:29 | 2166-11-22 00:43 | 121852.53 | Remaining Total Cost | [17 empty] | 24370.51
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2025-02-08 | 2025-02-18 | 04-Mar-25 A | 2025-12-08 | 2166-11-22 00:29 | 2166-11-22 00:43 | 121852.53 | Actual Total Cost | [8 empty] | 97482.03
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 0.00 to 1.50 m |  | 2025-02-03 | 2025-02-13 | 2025-11-23 | 2025-12-03 | 0 | 0 | 29394.33 | Planned Total Cost | [16 empty] | 24985.18 | 4409.15
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 0.00 to 1.50 m |  | 2025-02-03 | 2025-02-13 | 2025-11-23 | 2025-12-03 | 0 | 0 | 29394.33 | Remaining Total Cost | [16 empty] | 24985.18 | 4409.15
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 0.00 to 1.50 m |  | 2025-02-03 | 2025-02-13 | 2025-11-23 | 2025-12-03 | 0 | 0 | 29394.33 | Actual Total Cost
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2025-02-05 | 2025-02-16 | 2025-11-25 | 2025-12-06 | 0 | 0 | 21868.95 | Planned Total Cost | [16 empty] | 11481.2 | 10387.75
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2025-02-05 | 2025-02-16 | 2025-11-25 | 2025-12-06 | 0 | 0 | 21868.95 | Remaining Total Cost | [16 empty] | 11481.2 | 10387.75
|  |  | JDH3-02-008-L-68-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2025-02-05 | 2025-02-16 | 2025-11-25 | 2025-12-06 | 0 | 0 | 21868.95 | Actual Total Cost
|  |  | JDH3-02-008-L-68-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-02-08 | 2025-02-18 | 05-Mar-25 A | 2025-12-08 | 1928-07-19 16:48 | 1928-07-19 16:48 | 20857.39 | Planned Total Cost | [7 empty] | 10428.7 | [9 empty] | 10428.7
|  |  | JDH3-02-008-L-68-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-02-08 | 2025-02-18 | 05-Mar-25 A | 2025-12-08 | 1928-07-19 16:48 | 1928-07-19 16:48 | 20857.39 | Remaining Total Cost | [17 empty] | 10428.7
|  |  | JDH3-02-008-L-68-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2025-02-08 | 2025-02-18 | 05-Mar-25 A | 2025-12-08 | 1928-07-19 16:48 | 1928-07-19 16:48 | 20857.39 | Actual Total Cost | [8 empty] | 5214.35 |  | 3258.97 | 1955.38
|  |  | JDH3-02-008-L-68-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-02-10 | 2025-03-02 | 05-Mar-25 A | 2025-10-08 | 24106.64 | 1965-12-30 15:07 | 41062.99 | Planned Total Cost | [7 empty] | 24106.64 | [7 empty] | 16956.36
|  |  | JDH3-02-008-L-68-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-02-10 | 2025-03-02 | 05-Mar-25 A | 2025-10-08 | 24106.64 | 1965-12-30 15:07 | 41062.99 | Remaining Total Cost | [15 empty] | 16956.36
|  |  | JDH3-02-008-L-68-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2025-02-10 | 2025-03-02 | 05-Mar-25 A | 2025-10-08 | 24106.64 | 1965-12-30 15:07 | 41062.99 | Actual Total Cost | [8 empty] | 8512.23 |  | 5426.54 | 3479.37 | 3351.69 | 3336.79
|  |  | JDH3-02-008-L-68-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-02-08 | 2025-02-18 | 20-Aug-25 A | 2025-10-08 | 1946-05-24 15:07 | 1946-05-24 15:22 | 33893.26 | Planned Total Cost | [7 empty] | 16946.63 | [7 empty] | 16946.63
|  |  | JDH3-02-008-L-68-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-02-08 | 2025-02-18 | 20-Aug-25 A | 2025-10-08 | 1946-05-24 15:07 | 1946-05-24 15:22 | 33893.26 | Remaining Total Cost | [15 empty] | 16946.63
|  |  | JDH3-02-008-L-68-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2025-02-08 | 2025-02-18 | 20-Aug-25 A | 2025-10-08 | 1946-05-24 15:07 | 1946-05-24 15:22 | 33893.26 | Actual Total Cost | [13 empty] | 16946.64
|  |  | JDH3-02-008-L-68-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-02-10 | 2025-02-20 | 23-Aug-25 A | 2025-10-11 | 1924-12-24 02:38 | 1924-12-24 02:38 | 36500.43 | Planned Total Cost | [7 empty] | 9125.11 | [7 empty] | 27375.33
|  |  | JDH3-02-008-L-68-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-02-10 | 2025-02-20 | 23-Aug-25 A | 2025-10-11 | 1924-12-24 02:38 | 1924-12-24 02:38 | 36500.43 | Remaining Total Cost | [15 empty] | 27375.33
|  |  | JDH3-02-008-L-68-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2025-02-10 | 2025-02-20 | 23-Aug-25 A | 2025-10-11 | 1924-12-24 02:38 | 1924-12-24 02:38 | 36500.43 | Actual Total Cost | [13 empty] | 9125.11
|  |  | JDH3-02-008-L-68-(ST)- Single Catchbasine Works |  | 2025-02-12 | 2025-02-20 | 2025-10-02 | 2025-10-11 | 0 | 0 | 23464.58 | Planned Total Cost | [15 empty] | 23464.58
|  |  | JDH3-02-008-L-68-(ST)- Single Catchbasine Works |  | 2025-02-12 | 2025-02-20 | 2025-10-02 | 2025-10-11 | 0 | 0 | 23464.58 | Remaining Total Cost | [15 empty] | 23464.58
|  |  | JDH3-02-008-L-68-(ST)- Single Catchbasine Works |  | 2025-02-12 | 2025-02-20 | 2025-10-02 | 2025-10-11 | 0 | 0 | 23464.58 | Actual Total Cost
|  |  | JDH3-02-008-L-68-(ST)- Double Catchbasine Works |  | 2025-02-15 | 2025-02-23 | 2025-10-05 | 2025-10-13 | 0 | 0 | 90912.14 | Planned Total Cost | [15 empty] | 90912.14
|  |  | JDH3-02-008-L-68-(ST)- Double Catchbasine Works |  | 2025-02-15 | 2025-02-23 | 2025-10-05 | 2025-10-13 | 0 | 0 | 90912.14 | Remaining Total Cost | [15 empty] | 90912.14
|  |  | JDH3-02-008-L-68-(ST)- Double Catchbasine Works |  | 2025-02-15 | 2025-02-23 | 2025-10-05 | 2025-10-13 | 0 | 0 | 90912.14 | Actual Total Cost
|  |  | JDH3-02-008-L-68-TSE Network - TSE |  | 2025-03-03 | 2025-03-17 | 05-Apr-25 A | 2025-12-22 | 2139-10-15 10:48 | 2139-10-15 10:34 | 103343.98 | Planned Total Cost | [8 empty] | 87582.45 | [8 empty] | 15761.54
|  |  | JDH3-02-008-L-68-TSE Network - TSE |  | 2025-03-03 | 2025-03-17 | 05-Apr-25 A | 2025-12-22 | 2139-10-15 10:48 | 2139-10-15 10:34 | 103343.98 | Remaining Total Cost | [17 empty] | 15761.54
|  |  | JDH3-02-008-L-68-TSE Network - TSE |  | 2025-03-03 | 2025-03-17 | 05-Apr-25 A | 2025-12-22 | 2139-10-15 10:48 | 2139-10-15 10:34 | 103343.98 | Actual Total Cost | [9 empty] | 26913.35 | 29559.08 | 30562.62 | 547.39
|  |  | JDH3-02-008-L-68-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-03-03 | 2025-03-16 | 2025-12-09 | 2025-12-22 | 0 | 0 | 2251.8 | Planned Total Cost | [17 empty] | 2251.8
|  |  | JDH3-02-008-L-68-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-03-03 | 2025-03-16 | 2025-12-09 | 2025-12-22 | 0 | 0 | 2251.8 | Remaining Total Cost | [17 empty] | 2251.8
|  |  | JDH3-02-008-L-68-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2025-03-03 | 2025-03-16 | 2025-12-09 | 2025-12-22 | 0 | 0 | 2251.8 | Actual Total Cost
|  |  | JDH3-02-008-L-68-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2025-03-05 | 2025-03-17 | 05-Apr-25 A | 03-Jul-25 A | 2139-10-15 10:48 | 2139-10-15 10:34 | 87582.45 | Planned Total Cost | [8 empty] | 87582.45
|  |  | JDH3-02-008-L-68-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2025-03-05 | 2025-03-17 | 05-Apr-25 A | 03-Jul-25 A | 2139-10-15 10:48 | 2139-10-15 10:34 | 87582.45 | Remaining Total Cost
|  |  | JDH3-02-008-L-68-(TSE)- Supply and install HDPE Pipes - 315 mm depth from 1.51 to 2.5 m |  | 2025-03-05 | 2025-03-17 | 05-Apr-25 A | 03-Jul-25 A | 2139-10-15 10:48 | 2139-10-15 10:34 | 87582.45 | Actual Total Cost | [9 empty] | 26913.35 | 29559.08 | 30562.62 | 547.39
|  |  | JDH3-02-008-L-68-(TSE)-Supply and install gate valves-100 mm |  | 2025-03-10 | 2025-03-13 | 2025-12-16 | 2025-12-20 | 0 | 0 | 2586.32 | Planned Total Cost | [17 empty] | 2586.32
|  |  | JDH3-02-008-L-68-(TSE)-Supply and install gate valves-100 mm |  | 2025-03-10 | 2025-03-13 | 2025-12-16 | 2025-12-20 | 0 | 0 | 2586.32 | Remaining Total Cost | [17 empty] | 2586.32
|  |  | JDH3-02-008-L-68-(TSE)-Supply and install gate valves-100 mm |  | 2025-03-10 | 2025-03-13 | 2025-12-16 | 2025-12-20 | 0 | 0 | 2586.32 | Actual Total Cost
|  |  | JDH3-02-008-L-68-(TSE)-Supply and install of Air valves-50 mm. |  | 2025-03-10 | 2025-03-13 | 2025-12-16 | 2025-12-20 | 0 | 0 | 7444.14 | Planned Total Cost | [17 empty] | 7444.14
|  |  | JDH3-02-008-L-68-(TSE)-Supply and install of Air valves-50 mm. |  | 2025-03-10 | 2025-03-13 | 2025-12-16 | 2025-12-20 | 0 | 0 | 7444.14 | Remaining Total Cost | [17 empty] | 7444.14
|  |  | JDH3-02-008-L-68-(TSE)-Supply and install of Air valves-50 mm. |  | 2025-03-10 | 2025-03-13 | 2025-12-16 | 2025-12-20 | 0 | 0 | 7444.14 | Actual Total Cost
|  |  | JDH3-02-008-L-68-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2025-03-03 | 2025-03-16 | 2025-12-09 | 2025-12-22 | 0 | 0 | 3479.28 | Planned Total Cost | [17 empty] | 3479.28
|  |  | JDH3-02-008-L-68-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2025-03-03 | 2025-03-16 | 2025-12-09 | 2025-12-22 | 0 | 0 | 3479.28 | Remaining Total Cost | [17 empty] | 3479.28
|  |  | JDH3-02-008-L-68-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2025-03-03 | 2025-03-16 | 2025-12-09 | 2025-12-22 | 0 | 0 | 3479.28 | Actual Total Cost
|  |  | JDH3-02-008-L-68-Potable Water Network - WT |  | 2025-03-18 | 2025-03-29 | 2025-12-23 | 2026-01-03 | 0 | 0 | 31050.56 | Planned Total Cost | [17 empty] | 30666.03 | 384.54
|  |  | JDH3-02-008-L-68-Potable Water Network - WT |  | 2025-03-18 | 2025-03-29 | 2025-12-23 | 2026-01-03 | 0 | 0 | 31050.56 | Remaining Total Cost | [17 empty] | 30666.03 | 384.54
|  |  | JDH3-02-008-L-68-Potable Water Network - WT |  | 2025-03-18 | 2025-03-29 | 2025-12-23 | 2026-01-03 | 0 | 0 | 31050.56 | Actual Total Cost
|  |  | JDH3-02-008-L-68-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-03-18 | 2025-03-29 | 2025-12-23 | 2026-01-03 | 0 | 0 | 3845.35 | Planned Total Cost | [17 empty] | 3460.82 | 384.54
|  |  | JDH3-02-008-L-68-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-03-18 | 2025-03-29 | 2025-12-23 | 2026-01-03 | 0 | 0 | 3845.35 | Remaining Total Cost | [17 empty] | 3460.82 | 384.54
|  |  | JDH3-02-008-L-68-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2025-03-18 | 2025-03-29 | 2025-12-23 | 2026-01-03 | 0 | 0 | 3845.35 | Actual Total Cost
|  |  | JDH3-02-008-L-68-(WT)- Supply and install 3-out fire hydrant |  | 2025-03-20 | 2025-03-26 | 2025-12-25 | 2025-12-31 | 0 | 0 | 27205.21 | Planned Total Cost | [17 empty] | 27205.21
|  |  | JDH3-02-008-L-68-(WT)- Supply and install 3-out fire hydrant |  | 2025-03-20 | 2025-03-26 | 2025-12-25 | 2025-12-31 | 0 | 0 | 27205.21 | Remaining Total Cost | [17 empty] | 27205.21
|  |  | JDH3-02-008-L-68-(WT)- Supply and install 3-out fire hydrant |  | 2025-03-20 | 2025-03-26 | 2025-12-25 | 2025-12-31 | 0 | 0 | 27205.21 | Actual Total Cost
|  |  | Z07-1 |  | 2024-08-27 | 2025-02-23 | 14-Oct-24 A | 2025-12-18 | 6194687.4 | 6194687.36 | 9475826.12 | Planned Total Cost |  |  | 3858337.25 | 1053857.97 | 696424.69 | 390791.6 | [8 empty] | 316706.53 | 2240409.92 | 668545.62 | 250752.54
|  |  | Z07-1 |  | 2024-08-27 | 2025-02-23 | 14-Oct-24 A | 2025-12-18 | 6194687.4 | 6194687.36 | 9475826.12 | Remaining Total Cost | [15 empty] | 2337256.41 | 693129.73 | 250752.54
|  |  | Z07-1 |  | 2024-08-27 | 2025-02-23 | 14-Oct-24 A | 2025-12-18 | 6194687.4 | 6194687.36 | 9475826.12 | Actual Total Cost |  |  |  |  | 13215.07 | 231893.4 | 424231.11 | 289942.32 | 573931.26 | 675390.38 | 646146.79 | 499562.78 | 268958.61 | 1859217.32 | 684367.16 | 27831.15
|  |  | L-59 |  | 2024-08-27 | 2025-01-22 | 02-Nov-24 A | 2025-12-18 | 1726563.45 | 1726563.44 | 2900329.38 | Planned Total Cost |  |  | 1374029.93 | 192759.48 | 143899.3 | 69421.29 | [8 empty] | 4210.25 | 733954.83 | 177418.13 | 204636.17
|  |  | L-59 |  | 2024-08-27 | 2025-01-22 | 02-Nov-24 A | 2025-12-18 | 1726563.45 | 1726563.44 | 2900329.38 | Remaining Total Cost | [15 empty] | 771676.02 | 197453.73 | 204636.17
|  |  | L-59 |  | 2024-08-27 | 2025-01-22 | 02-Nov-24 A | 2025-12-18 | 1726563.45 | 1726563.44 | 2900329.38 | Actual Total Cost |  |  |  |  | 3787.58 | 72290.26 | 185215.75 | 106859.84 | 83482.66 | 432531.84 | 199742.59 | 126457.8 | 108788.93 | 308809.78 | 95053.27 | 3543.13
|  |  | JDH3-02-008-L-59-Sewage Network - SS |  | 2024-09-04 | 2024-10-08 | 26-Nov-24 A | 2025-10-13 | 548349.03 | 548349.03 | 567544.11 | Planned Total Cost |  |  | 523535.71 | 21717.52 | [10 empty] | 4210.25 | 18080.62
|  |  | JDH3-02-008-L-59-Sewage Network - SS |  | 2024-09-04 | 2024-10-08 | 26-Nov-24 A | 2025-10-13 | 548349.03 | 548349.03 | 567544.11 | Remaining Total Cost | [15 empty] | 19195.08
|  |  | JDH3-02-008-L-59-Sewage Network - SS |  | 2024-09-04 | 2024-10-08 | 26-Nov-24 A | 2025-10-13 | 548349.03 | 548349.03 | 567544.11 | Actual Total Cost |  |  |  |  | 3787.58 | 72290.26 | 185215.75 | 106859.84 | 83482.66 | 28561.54 | 20333.16 | 9084.21 | 5323.69 | 27862.55 | 5498.26 | 49.54
|  |  | JDH3-02-008-L-59-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 0 to 1.5 m. |  | 2024-09-04 | 2024-10-03 | 26-Nov-24 A | 05-Aug-25 A | 2018-01-16 03:50 | 2018-01-16 04:05 | 43116.16 | Planned Total Cost |  |  | 40266.52 | 2849.64
|  |  | JDH3-02-008-L-59-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 0 to 1.5 m. |  | 2024-09-04 | 2024-10-03 | 26-Nov-24 A | 05-Aug-25 A | 2018-01-16 03:50 | 2018-01-16 04:05 | 43116.16 | Remaining Total Cost
|  |  | JDH3-02-008-L-59-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 0 to 1.5 m. |  | 2024-09-04 | 2024-10-03 | 26-Nov-24 A | 05-Aug-25 A | 2018-01-16 03:50 | 2018-01-16 04:05 | 43116.16 | Actual Total Cost |  |  |  |  | 1077.9 | 7275.85 | 23009.91 | 9216.14 | 1148.69 |  |  |  |  | 1387.67
|  |  | JDH3-02-008-L-59-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2024-09-04 | 2024-10-08 | 26-Nov-24 A | 20-Sep-25 A | 2196-09-29 20:10 | 2196-09-29 19:55 | 108386.84 | Planned Total Cost |  |  | 97548.16 | 6628.43 | [10 empty] | 4210.25
|  |  | JDH3-02-008-L-59-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2024-09-04 | 2024-10-08 | 26-Nov-24 A | 20-Sep-25 A | 2196-09-29 20:10 | 2196-09-29 19:55 | 108386.84 | Remaining Total Cost
|  |  | JDH3-02-008-L-59-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2024-09-04 | 2024-10-08 | 26-Nov-24 A | 20-Sep-25 A | 2196-09-29 20:10 | 2196-09-29 19:55 | 108386.84 | Actual Total Cost |  |  |  |  | 2709.67 | 42541.83 | 50264.39 | 3965.54 | 3728.49 | 966.65 |  |  |  |  | 4210.25
|  |  | JDH3-02-008-L-59-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2024-09-04 | 2024-09-12 | 31-Dec-24 A | 11-Jun-25 A | 2014-03-16 18:58 | 2014-03-16 19:12 | 41714.79 | Planned Total Cost |  |  | 41714.79
|  |  | JDH3-02-008-L-59-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2024-09-04 | 2024-09-12 | 31-Dec-24 A | 11-Jun-25 A | 2014-03-16 18:58 | 2014-03-16 19:12 | 41714.79 | Remaining Total Cost
|  |  | JDH3-02-008-L-59-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2024-09-04 | 2024-09-12 | 31-Dec-24 A | 11-Jun-25 A | 2014-03-16 18:58 | 2014-03-16 19:12 | 41714.79 | Actual Total Cost | [5 empty] | 434.53 | 19597.27 | 12079.91 | 3345.87 |  | 4511.2 | 1746.02
|  |  | JDH3-02-008-L-59-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2024-09-04 | 2024-09-26 | 05-Dec-24 A | 2025-10-02 | 2202-02-07 06:14 | 2202-02-07 06:00 | 111456.71 | Planned Total Cost |  |  | 111456.71
|  |  | JDH3-02-008-L-59-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2024-09-04 | 2024-09-26 | 05-Dec-24 A | 2025-10-02 | 2202-02-07 06:14 | 2202-02-07 06:00 | 111456.71 | Remaining Total Cost | [15 empty] | 1114.46
|  |  | JDH3-02-008-L-59-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2024-09-04 | 2024-09-26 | 05-Dec-24 A | 2025-10-02 | 2202-02-07 06:14 | 2202-02-07 06:00 | 111456.71 | Actual Total Cost | [5 empty] | 11328.52 | 16250.51 | 8411.05 | 16064.21 | 17079.17 | 13108.88 | 6920.8 | 5323.69 | 14517.88 | 1288.01 | 49.54
|  |  | JDH3-02-008-L-59-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2024-09-04 | 2024-09-17 | 2025-10-02 | 2025-10-13 | 0 | 0 | 18080.62 | Planned Total Cost | [15 empty] | 18080.62
|  |  | JDH3-02-008-L-59-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2024-09-04 | 2024-09-17 | 2025-10-02 | 2025-10-13 | 0 | 0 | 18080.62 | Remaining Total Cost | [15 empty] | 18080.62
|  |  | JDH3-02-008-L-59-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2024-09-04 | 2024-09-17 | 2025-10-02 | 2025-10-13 | 0 | 0 | 18080.62 | Actual Total Cost
|  |  | JDH3-02-008-L-59-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2024-09-04 | 2024-10-03 | 16-Dec-24 A | 03-Aug-25 A | 244788.98 | 244788.98 | 244788.98 | Planned Total Cost |  |  | 232549.53 | 12239.45
|  |  | JDH3-02-008-L-59-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2024-09-04 | 2024-10-03 | 16-Dec-24 A | 03-Aug-25 A | 244788.98 | 244788.98 | 244788.98 | Remaining Total Cost
|  |  | JDH3-02-008-L-59-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2024-09-04 | 2024-10-03 | 16-Dec-24 A | 03-Aug-25 A | 244788.98 | 244788.98 | 244788.98 | Actual Total Cost | [5 empty] | 10709.52 | 76093.68 | 73187.2 | 59195.39 | 10515.73 | 2713.08 | 417.4 |  | 11957
|  |  | JDH3-02-008-L-59-Storm Network - ST |  | 2024-09-04 | 2024-11-06 | 06-Apr-25 A | 2025-11-02 | 984929.44 | 984929.42 | 1755600.04 | Planned Total Cost |  |  | 850494.21 | 171041.96 | [11 empty] | 715874.21 | 18189.66
|  |  | JDH3-02-008-L-59-Storm Network - ST |  | 2024-09-04 | 2024-11-06 | 06-Apr-25 A | 2025-11-02 | 984929.44 | 984929.42 | 1755600.04 | Remaining Total Cost | [15 empty] | 752480.94 | 18189.66
|  |  | JDH3-02-008-L-59-Storm Network - ST |  | 2024-09-04 | 2024-11-06 | 06-Apr-25 A | 2025-11-02 | 984929.44 | 984929.42 | 1755600.04 | Actual Total Cost | [9 empty] | 403970.3 | 179409.43 | 117373.58 | 103465.24 | 149412.16 | 30092.14 | 1206.56
|  |  | JDH3-02-008-L-59-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-09-07 | 2024-10-30 | 2025-10-02 | 2025-11-02 | 0 | 0 | 274811.21 | Planned Total Cost | [15 empty] | 263818.76 | 10992.45
|  |  | JDH3-02-008-L-59-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-09-07 | 2024-10-30 | 2025-10-02 | 2025-11-02 | 0 | 0 | 274811.21 | Remaining Total Cost | [15 empty] | 263818.76 | 10992.45
|  |  | JDH3-02-008-L-59-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-09-07 | 2024-10-30 | 2025-10-02 | 2025-11-02 | 0 | 0 | 274811.21 | Actual Total Cost
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-09-15 | 2024-10-01 | 15-Apr-25 A | 2025-10-20 | 2137-05-16 04:19 | 2137-05-16 04:34 | 130550.66 | Planned Total Cost |  |  | 84312 | [12 empty] | 46238.65
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-09-15 | 2024-10-01 | 15-Apr-25 A | 2025-10-20 | 2137-05-16 04:19 | 2137-05-16 04:34 | 130550.66 | Remaining Total Cost | [15 empty] | 43850.47
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-09-15 | 2024-10-01 | 15-Apr-25 A | 2025-10-20 | 2137-05-16 04:19 | 2137-05-16 04:34 | 130550.66 | Actual Total Cost | [9 empty] | 14674.56 | 52391.47 | 6812.58 | 1572.28 | 387.86 | 10411.81 | 449.63
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-10-09 | 2024-10-27 | 2025-10-14 | 2025-10-29 | 0 | 0 | 735.23 | Planned Total Cost | [15 empty] | 735.23
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-10-09 | 2024-10-27 | 2025-10-14 | 2025-10-29 | 0 | 0 | 735.23 | Remaining Total Cost | [15 empty] | 735.23
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-10-09 | 2024-10-27 | 2025-10-14 | 2025-10-29 | 0 | 0 | 735.23 | Actual Total Cost
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2024-09-04 | 2024-09-15 | 10-Apr-25 A | 22-May-25 A | 2154-04-17 14:38 | 2154-04-17 14:38 | 92880.61 | Planned Total Cost |  |  | 92880.61
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2024-09-04 | 2024-09-15 | 10-Apr-25 A | 22-May-25 A | 2154-04-17 14:38 | 2154-04-17 14:38 | 92880.61 | Remaining Total Cost
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 0.00 to 1.50 m |  | 2024-09-04 | 2024-09-15 | 10-Apr-25 A | 22-May-25 A | 2154-04-17 14:38 | 2154-04-17 14:38 | 92880.61 | Actual Total Cost | [9 empty] | 62500.91 | 30379.7
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-09-15 | 10-Apr-25 A | 08-Jul-25 A | 2000-11-29 02:24 | 2000-11-29 02:10 | 36859.1 | Planned Total Cost |  |  | 36859.1
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-09-15 | 10-Apr-25 A | 08-Jul-25 A | 2000-11-29 02:24 | 2000-11-29 02:10 | 36859.1 | Remaining Total Cost
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-09-15 | 10-Apr-25 A | 08-Jul-25 A | 2000-11-29 02:24 | 2000-11-29 02:10 | 36859.1 | Actual Total Cost | [9 empty] | 28220.24 | 4952.94 | 2073.32 | 1612.59
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2024-09-04 | 2024-09-15 | 12-Jun-25 A | 22-Jul-25 A | 2049-08-15 15:22 | 2049-08-15 15:07 | 54650.64 | Planned Total Cost |  |  | 54650.64
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2024-09-04 | 2024-09-15 | 12-Jun-25 A | 22-Jul-25 A | 2049-08-15 15:22 | 2049-08-15 15:07 | 54650.64 | Remaining Total Cost
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 0.00 to 1.50 m |  | 2024-09-04 | 2024-09-15 | 12-Jun-25 A | 22-Jul-25 A | 2049-08-15 15:22 | 2049-08-15 15:07 | 54650.64 | Actual Total Cost | [11 empty] | 29716.29 | 24934.35
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-10-22 | 06-Apr-25 A | 2025-10-04 | 2365-01-14 07:41 | 2365-01-14 07:41 | 174193.76 | Planned Total Cost |  |  | 165512.89 | 8680.87
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-10-22 | 06-Apr-25 A | 2025-10-04 | 2365-01-14 07:41 | 2365-01-14 07:41 | 174193.76 | Remaining Total Cost | [15 empty] | 4340.44
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-10-22 | 06-Apr-25 A | 2025-10-04 | 2365-01-14 07:41 | 2365-01-14 07:41 | 174193.76 | Actual Total Cost | [9 empty] | 84375.1 | 54979.91 | 902 | 25255.88 | 4340.43
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 0.00 to 1.50 m |  | 2024-10-12 | 2024-10-27 | 16-Aug-25 A | 31-Aug-25 A | 1946-03-27 23:17 | 1946-03-27 23:17 | 16888.97 | Planned Total Cost |  |  |  | 16888.97
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 0.00 to 1.50 m |  | 2024-10-12 | 2024-10-27 | 16-Aug-25 A | 31-Aug-25 A | 1946-03-27 23:17 | 1946-03-27 23:17 | 16888.97 | Remaining Total Cost
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 0.00 to 1.50 m |  | 2024-10-12 | 2024-10-27 | 16-Aug-25 A | 31-Aug-25 A | 1946-03-27 23:17 | 1946-03-27 23:17 | 16888.97 | Actual Total Cost | [13 empty] | 16888.97
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-10-22 | 06-Apr-25 A | 2025-10-04 | 2047-01-12 08:24 | 2047-01-12 08:24 | 57780.17 | Planned Total Cost |  |  | 46224.13 | 11556.03
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-10-22 | 06-Apr-25 A | 2025-10-04 | 2047-01-12 08:24 | 2047-01-12 08:24 | 57780.17 | Remaining Total Cost | [15 empty] | 4075.82
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-10-22 | 06-Apr-25 A | 2025-10-04 | 2047-01-12 08:24 | 2047-01-12 08:24 | 57780.17 | Actual Total Cost | [9 empty] | 46224.13 |  |  |  | 5895.41 | 1526.11 | 58.7
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-10-22 | 10-Apr-25 A | 2025-10-04 | 2053-08-12 04:34 | 2053-08-12 04:34 | 60340.47 | Planned Total Cost |  |  | 48272.37 | 12068.09
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-10-22 | 10-Apr-25 A | 2025-10-04 | 2053-08-12 04:34 | 2053-08-12 04:34 | 60340.47 | Remaining Total Cost | [15 empty] | 4232.28
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-10-22 | 10-Apr-25 A | 2025-10-04 | 2053-08-12 04:34 | 2053-08-12 04:34 | 60340.47 | Actual Total Cost | [9 empty] | 46198.17 | 2074.2 |  |  | 6158.31 | 1615.38 | 62.13
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-10-22 | 10-Apr-25 A | 2025-10-04 | 2259-06-20 06:43 | 2259-06-20 06:43 | 141178.16 | Planned Total Cost |  |  | 112942.53 | 28235.63
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-10-22 | 10-Apr-25 A | 2025-10-04 | 2259-06-20 06:43 | 2259-06-20 06:43 | 141178.16 | Remaining Total Cost | [15 empty] | 9883.89
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-10-22 | 10-Apr-25 A | 2025-10-04 | 2259-06-20 06:43 | 2259-06-20 06:43 | 141178.16 | Actual Total Cost | [9 empty] | 108089.53 | 4853 |  |  | 14409.82 | 3795.94 | 146
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2024-09-21 | 2024-10-05 | 10-Jun-25 A | 2025-10-02 | 2317-09-15 01:26 | 2317-09-15 01:12 | 160554.24 | Planned Total Cost |  |  | 128443.39 | 32110.85
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2024-09-21 | 2024-10-05 | 10-Jun-25 A | 2025-10-02 | 2317-09-15 01:26 | 2317-09-15 01:12 | 160554.24 | Remaining Total Cost | [15 empty] | 7989.18
|  |  | JDH3-02-008-L-59-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2024-09-21 | 2024-10-05 | 10-Jun-25 A | 2025-10-02 | 2317-09-15 01:26 | 2317-09-15 01:12 | 160554.24 | Actual Total Cost | [11 empty] | 39135.1 | 44690.55 | 61229.45 | 7231.8 | 278.15
|  |  | JDH3-02-008-L-59-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-09-24 | 2024-10-14 | 15-May-25 A | 2025-10-08 | 2086-08-13 16:34 | 2086-08-13 16:34 | 114715.67 | Planned Total Cost |  |  | 41217.57 | 26945.12 | [11 empty] | 46552.98
|  |  | JDH3-02-008-L-59-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-09-24 | 2024-10-14 | 15-May-25 A | 2025-10-08 | 2086-08-13 16:34 | 2086-08-13 16:34 | 114715.67 | Remaining Total Cost | [15 empty] | 46552.98
|  |  | JDH3-02-008-L-59-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-09-24 | 2024-10-14 | 15-May-25 A | 2025-10-08 | 2086-08-13 16:34 | 2086-08-13 16:34 | 114715.67 | Actual Total Cost | [10 empty] | 29778.21 | 18642.6 |  | 19741.88
|  |  | JDH3-02-008-L-59-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2024-09-04 | 2024-10-16 | 10-Apr-25 A | 2025-10-11 | 2001-01-18 00:43 | 2001-01-18 00:29 | 54750.66 | Planned Total Cost |  |  | 36909.03 | [12 empty] | 17841.63
|  |  | JDH3-02-008-L-59-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2024-09-04 | 2024-10-16 | 10-Apr-25 A | 2025-10-11 | 2001-01-18 00:43 | 2001-01-18 00:29 | 54750.66 | Remaining Total Cost | [15 empty] | 17841.63
|  |  | JDH3-02-008-L-59-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2024-09-04 | 2024-10-16 | 10-Apr-25 A | 2025-10-11 | 2001-01-18 00:43 | 2001-01-18 00:29 | 54750.66 | Actual Total Cost | [9 empty] | 13687.66 |  | 18531.12 | 4690.24
|  |  | JDH3-02-008-L-59-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2024-10-14 | 2024-10-24 | 16-Aug-25 A | 2025-10-20 | 1923-03-13 07:41 | 1923-03-13 07:41 | 33893.26 | Planned Total Cost |  |  |  | 16946.63 | [11 empty] | 16946.63
|  |  | JDH3-02-008-L-59-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2024-10-14 | 2024-10-24 | 16-Aug-25 A | 2025-10-20 | 1923-03-13 07:41 | 1923-03-13 07:41 | 33893.26 | Remaining Total Cost | [15 empty] | 25419.94
|  |  | JDH3-02-008-L-59-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2024-10-14 | 2024-10-24 | 16-Aug-25 A | 2025-10-20 | 1923-03-13 07:41 | 1923-03-13 07:41 | 33893.26 | Actual Total Cost | [13 empty] | 2750.25 | 5511.1 | 211.97
|  |  | JDH3-02-008-L-59-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2024-09-29 | 2024-10-12 | 18-Jun-25 A | 2025-10-08 | 1924-12-24 02:38 | 1924-12-24 02:38 | 18250.22 | Planned Total Cost |  |  | 2269.94 | 6855.17 | [11 empty] | 9125.11
|  |  | JDH3-02-008-L-59-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2024-09-29 | 2024-10-12 | 18-Jun-25 A | 2025-10-08 | 1924-12-24 02:38 | 1924-12-24 02:38 | 18250.22 | Remaining Total Cost | [15 empty] | 9125.11
|  |  | JDH3-02-008-L-59-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2024-09-29 | 2024-10-12 | 18-Jun-25 A | 2025-10-08 | 1924-12-24 02:38 | 1924-12-24 02:38 | 18250.22 | Actual Total Cost | [11 empty] | 1560.58 | 709.36 | 6855.17
|  |  | JDH3-02-008-L-59-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2024-10-16 | 2024-10-27 | 18-Aug-25 A | 2025-10-19 | 1929-06-10 14:10 | 1929-06-10 14:24 | 21509.18 | Planned Total Cost |  |  |  | 10754.59 | [11 empty] | 10754.59
|  |  | JDH3-02-008-L-59-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2024-10-16 | 2024-10-27 | 18-Aug-25 A | 2025-10-19 | 1929-06-10 14:10 | 1929-06-10 14:24 | 21509.18 | Remaining Total Cost | [15 empty] | 10754.59
|  |  | JDH3-02-008-L-59-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2024-10-16 | 2024-10-27 | 18-Aug-25 A | 2025-10-19 | 1929-06-10 14:10 | 1929-06-10 14:24 | 21509.18 | Actual Total Cost | [13 empty] | 10754.6
|  |  | JDH3-02-008-L-59-(ST)- Single Catchbasine Works |  | 2024-10-19 | 2024-11-03 | 2025-10-14 | 2025-10-29 | 0 | 0 | 74304.5 | Planned Total Cost | [15 empty] | 74304.5
|  |  | JDH3-02-008-L-59-(ST)- Single Catchbasine Works |  | 2024-10-19 | 2024-11-03 | 2025-10-14 | 2025-10-29 | 0 | 0 | 74304.5 | Remaining Total Cost | [15 empty] | 74304.5
|  |  | JDH3-02-008-L-59-(ST)- Single Catchbasine Works |  | 2024-10-19 | 2024-11-03 | 2025-10-14 | 2025-10-29 | 0 | 0 | 74304.5 | Actual Total Cost
|  |  | JDH3-02-008-L-59-(ST)- Double Catchbasine Works |  | 2024-10-22 | 2024-11-06 | 2025-10-18 | 2025-11-02 | 0 | 0 | 215916.33 | Planned Total Cost | [15 empty] | 208719.12 | 7197.21
|  |  | JDH3-02-008-L-59-(ST)- Double Catchbasine Works |  | 2024-10-22 | 2024-11-06 | 2025-10-18 | 2025-11-02 | 0 | 0 | 215916.33 | Remaining Total Cost | [15 empty] | 208719.12 | 7197.21
|  |  | JDH3-02-008-L-59-(ST)- Double Catchbasine Works |  | 2024-10-22 | 2024-11-06 | 2025-10-18 | 2025-11-02 | 0 | 0 | 215916.33 | Actual Total Cost
|  |  | JDH3-02-008-L-59-(ST)-PIPES ENCASEMENT |  | 2024-10-19 | 2024-10-24 | 2025-10-21 | 2025-10-27 | 0 | 0 | 20837 | Planned Total Cost | [15 empty] | 20837
|  |  | JDH3-02-008-L-59-(ST)-PIPES ENCASEMENT |  | 2024-10-19 | 2024-10-24 | 2025-10-21 | 2025-10-27 | 0 | 0 | 20837 | Remaining Total Cost | [15 empty] | 20837
|  |  | JDH3-02-008-L-59-(ST)-PIPES ENCASEMENT |  | 2024-10-19 | 2024-10-24 | 2025-10-21 | 2025-10-27 | 0 | 0 | 20837 | Actual Total Cost
|  |  | JDH3-02-008-L-59-TSE Network - TSE |  | 2024-11-07 | 2024-12-12 | 06-Aug-25 A | 2025-11-16 | 2127-08-10 16:34 | 2127-08-10 16:48 | 111495.65 | Planned Total Cost |  |  |  |  | 79404.59 | 17825.52 | [10 empty] | 14265.54
|  |  | JDH3-02-008-L-59-TSE Network - TSE |  | 2024-11-07 | 2024-12-12 | 06-Aug-25 A | 2025-11-16 | 2127-08-10 16:34 | 2127-08-10 16:48 | 111495.65 | Remaining Total Cost | [16 empty] | 28361.95
|  |  | JDH3-02-008-L-59-TSE Network - TSE |  | 2024-11-07 | 2024-12-12 | 06-Aug-25 A | 2025-11-16 | 2127-08-10 16:34 | 2127-08-10 16:48 | 111495.65 | Actual Total Cost | [13 empty] | 26662.62 | 54379.56 | 2091.52
|  |  | JDH3-02-008-L-59-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-11-07 | 2024-12-12 | 06-Aug-25 A | 2025-11-13 | 2127-08-10 16:34 | 2127-08-10 16:48 | 97230.11 | Planned Total Cost |  |  |  |  | 79404.59 | 17825.52
|  |  | JDH3-02-008-L-59-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-11-07 | 2024-12-12 | 06-Aug-25 A | 2025-11-13 | 2127-08-10 16:34 | 2127-08-10 16:48 | 97230.11 | Remaining Total Cost | [16 empty] | 14096.41
|  |  | JDH3-02-008-L-59-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-11-07 | 2024-12-12 | 06-Aug-25 A | 2025-11-13 | 2127-08-10 16:34 | 2127-08-10 16:48 | 97230.11 | Actual Total Cost | [13 empty] | 26662.62 | 54379.56 | 2091.52
|  |  | JDH3-02-008-L-59-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2024-11-13 | 2024-12-08 | 2025-11-03 | 2025-11-16 | 0 | 0 | 6506.58 | Planned Total Cost | [16 empty] | 6506.58
|  |  | JDH3-02-008-L-59-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2024-11-13 | 2024-12-08 | 2025-11-03 | 2025-11-16 | 0 | 0 | 6506.58 | Remaining Total Cost | [16 empty] | 6506.58
|  |  | JDH3-02-008-L-59-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2024-11-13 | 2024-12-08 | 2025-11-03 | 2025-11-16 | 0 | 0 | 6506.58 | Actual Total Cost
|  |  | JDH3-02-008-L-59-(TSE)-Supply and install gate valves-100 mm |  | 2024-11-30 | 2024-12-05 | 2025-11-10 | 2025-11-13 | 0 | 0 | 7758.96 | Planned Total Cost | [16 empty] | 7758.96
|  |  | JDH3-02-008-L-59-(TSE)-Supply and install gate valves-100 mm |  | 2024-11-30 | 2024-12-05 | 2025-11-10 | 2025-11-13 | 0 | 0 | 7758.96 | Remaining Total Cost | [16 empty] | 7758.96
|  |  | JDH3-02-008-L-59-(TSE)-Supply and install gate valves-100 mm |  | 2024-11-30 | 2024-12-05 | 2025-11-10 | 2025-11-13 | 0 | 0 | 7758.96 | Actual Total Cost
|  |  | JDH3-02-008-L-59-Potable Water Network - WT |  | 2024-11-13 | 2024-12-26 | 13-Aug-25 A | 2025-11-23 | 2201-07-31 06:58 | 2201-07-31 06:58 | 199300.37 | Planned Total Cost |  |  |  |  | 64494.71 | 51595.77 | [10 empty] | 83209.89
|  |  | JDH3-02-008-L-59-Potable Water Network - WT |  | 2024-11-13 | 2024-12-26 | 13-Aug-25 A | 2025-11-23 | 2201-07-31 06:58 | 2201-07-31 06:58 | 199300.37 | Remaining Total Cost | [16 empty] | 89149.08
|  |  | JDH3-02-008-L-59-Potable Water Network - WT |  | 2024-11-13 | 2024-12-26 | 13-Aug-25 A | 2025-11-23 | 2201-07-31 06:58 | 2201-07-31 06:58 | 199300.37 | Actual Total Cost | [13 empty] | 104872.45 | 5083.32 | 195.51
|  |  | JDH3-02-008-L-59-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2024-11-13 | 2024-12-26 | 13-Aug-25 A | 2025-11-23 | 2201-07-31 06:58 | 2201-07-31 06:58 | 116090.48 | Planned Total Cost |  |  |  |  | 64494.71 | 51595.77
|  |  | JDH3-02-008-L-59-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2024-11-13 | 2024-12-26 | 13-Aug-25 A | 2025-11-23 | 2201-07-31 06:58 | 2201-07-31 06:58 | 116090.48 | Remaining Total Cost | [16 empty] | 5939.19
|  |  | JDH3-02-008-L-59-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2024-11-13 | 2024-12-26 | 13-Aug-25 A | 2025-11-23 | 2201-07-31 06:58 | 2201-07-31 06:58 | 116090.48 | Actual Total Cost | [13 empty] | 104872.45 | 5083.32 | 195.51
|  |  | JDH3-02-008-L-59-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2024-12-05 | 2024-12-09 | 2025-11-02 | 2025-11-06 | 0 | 0 | 10662.67 | Planned Total Cost | [16 empty] | 10662.67
|  |  | JDH3-02-008-L-59-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2024-12-05 | 2024-12-09 | 2025-11-02 | 2025-11-06 | 0 | 0 | 10662.67 | Remaining Total Cost | [16 empty] | 10662.67
|  |  | JDH3-02-008-L-59-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2024-12-05 | 2024-12-09 | 2025-11-02 | 2025-11-06 | 0 | 0 | 10662.67 | Actual Total Cost
|  |  | JDH3-02-008-L-59-(WT)- Supply and install 3-out fire hydrant |  | 2024-12-14 | 2024-12-19 | 2025-11-17 | 2025-11-23 | 0 | 0 | 72547.22 | Planned Total Cost | [16 empty] | 72547.22
|  |  | JDH3-02-008-L-59-(WT)- Supply and install 3-out fire hydrant |  | 2024-12-14 | 2024-12-19 | 2025-11-17 | 2025-11-23 | 0 | 0 | 72547.22 | Remaining Total Cost | [16 empty] | 72547.22
|  |  | JDH3-02-008-L-59-(WT)- Supply and install 3-out fire hydrant |  | 2024-12-14 | 2024-12-19 | 2025-11-17 | 2025-11-23 | 0 | 0 | 72547.22 | Actual Total Cost
|  |  | JDH3-02-008-L-59-Street Lighting Network -SL |  | 2024-12-29 | 2025-01-20 | 2025-11-24 | 2025-12-16 | 0 | 0 | 192702.36 | Planned Total Cost | [16 empty] | 44266.49 | 148435.87
|  |  | JDH3-02-008-L-59-Street Lighting Network -SL |  | 2024-12-29 | 2025-01-20 | 2025-11-24 | 2025-12-16 | 0 | 0 | 192702.36 | Remaining Total Cost | [16 empty] | 44266.49 | 148435.87
|  |  | JDH3-02-008-L-59-Street Lighting Network -SL |  | 2024-12-29 | 2025-01-20 | 2025-11-24 | 2025-12-16 | 0 | 0 | 192702.36 | Actual Total Cost
|  |  | JDH3-02-008-L-59-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx16 mm² |  | 2024-12-29 | 2025-01-14 | 2025-11-24 | 2025-12-10 | 0 | 0 | 38546.55 | Planned Total Cost | [16 empty] | 23127.93 | 15418.62
|  |  | JDH3-02-008-L-59-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx16 mm² |  | 2024-12-29 | 2025-01-14 | 2025-11-24 | 2025-12-10 | 0 | 0 | 38546.55 | Remaining Total Cost | [16 empty] | 23127.93 | 15418.62
|  |  | JDH3-02-008-L-59-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx16 mm² |  | 2024-12-29 | 2025-01-14 | 2025-11-24 | 2025-12-10 | 0 | 0 | 38546.55 | Actual Total Cost
|  |  | JDH3-02-008-L-59-(STL)- Supply,install,connect and test single core PVC insulated copper 6mm2 |  | 2025-01-05 | 2025-01-11 | 2025-12-01 | 2025-12-07 | 0 | 0 | 2917.56 | Planned Total Cost | [17 empty] | 2917.56
|  |  | JDH3-02-008-L-59-(STL)- Supply,install,connect and test single core PVC insulated copper 6mm2 |  | 2025-01-05 | 2025-01-11 | 2025-12-01 | 2025-12-07 | 0 | 0 | 2917.56 | Remaining Total Cost | [17 empty] | 2917.56
|  |  | JDH3-02-008-L-59-(STL)- Supply,install,connect and test single core PVC insulated copper 6mm2 |  | 2025-01-05 | 2025-01-11 | 2025-12-01 | 2025-12-07 | 0 | 0 | 2917.56 | Actual Total Cost
|  |  | JDH3-02-008-L-59-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2025-01-01 | 2025-01-20 | 2025-11-27 | 2025-12-16 | 0 | 0 | 78766.58 | Planned Total Cost | [16 empty] | 21004.42 | 57762.16
|  |  | JDH3-02-008-L-59-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2025-01-01 | 2025-01-20 | 2025-11-27 | 2025-12-16 | 0 | 0 | 78766.58 | Remaining Total Cost | [16 empty] | 21004.42 | 57762.16
|  |  | JDH3-02-008-L-59-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2025-01-01 | 2025-01-20 | 2025-11-27 | 2025-12-16 | 0 | 0 | 78766.58 | Actual Total Cost
|  |  | JDH3-02-008-L-59-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-01-07 | 2025-01-08 | 2025-12-03 | 2025-12-04 | 0 | 0 | 12116.87 | Planned Total Cost | [17 empty] | 12116.87
|  |  | JDH3-02-008-L-59-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-01-07 | 2025-01-08 | 2025-12-03 | 2025-12-04 | 0 | 0 | 12116.87 | Remaining Total Cost | [17 empty] | 12116.87
|  |  | JDH3-02-008-L-59-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-01-07 | 2025-01-08 | 2025-12-03 | 2025-12-04 | 0 | 0 | 12116.87 | Actual Total Cost
|  |  | JDH3-02-008-L-59-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2025-01-09 | 2025-01-11 | 2025-12-06 | 2025-12-07 | 0 | 0 | 378.04 | Planned Total Cost | [17 empty] | 378.04
|  |  | JDH3-02-008-L-59-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2025-01-09 | 2025-01-11 | 2025-12-06 | 2025-12-07 | 0 | 0 | 378.04 | Remaining Total Cost | [17 empty] | 378.04
|  |  | JDH3-02-008-L-59-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2025-01-09 | 2025-01-11 | 2025-12-06 | 2025-12-07 | 0 | 0 | 378.04 | Actual Total Cost
|  |  | JDH3-02-008-L-59-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-2 × 150 mm |  | 2025-01-04 | 2025-01-12 | 2025-11-30 | 2025-12-08 | 0 | 0 | 1341.43 | Planned Total Cost | [16 empty] | 134.14 | 1207.29
|  |  | JDH3-02-008-L-59-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-2 × 150 mm |  | 2025-01-04 | 2025-01-12 | 2025-11-30 | 2025-12-08 | 0 | 0 | 1341.43 | Remaining Total Cost | [16 empty] | 134.14 | 1207.29
|  |  | JDH3-02-008-L-59-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-2 × 150 mm |  | 2025-01-04 | 2025-01-12 | 2025-11-30 | 2025-12-08 | 0 | 0 | 1341.43 | Actual Total Cost
|  |  | JDH3-02-008-L-59-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-01-06 | 2025-01-13 | 2025-12-02 | 2025-12-09 | 0 | 0 | 53127.68 | Planned Total Cost | [17 empty] | 53127.68
|  |  | JDH3-02-008-L-59-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-01-06 | 2025-01-13 | 2025-12-02 | 2025-12-09 | 0 | 0 | 53127.68 | Remaining Total Cost | [17 empty] | 53127.68
|  |  | JDH3-02-008-L-59-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-01-06 | 2025-01-13 | 2025-12-02 | 2025-12-09 | 0 | 0 | 53127.68 | Actual Total Cost
|  |  | JDH3-02-008-L-59-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2025-01-08 | 2025-01-14 | 2025-12-04 | 2025-12-10 | 0 | 0 | 5507.65 | Planned Total Cost | [17 empty] | 5507.65
|  |  | JDH3-02-008-L-59-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2025-01-08 | 2025-01-14 | 2025-12-04 | 2025-12-10 | 0 | 0 | 5507.65 | Remaining Total Cost | [17 empty] | 5507.65
|  |  | JDH3-02-008-L-59-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2025-01-08 | 2025-01-14 | 2025-12-04 | 2025-12-10 | 0 | 0 | 5507.65 | Actual Total Cost
|  |  | JDH3-02-008-L-59-Telecommunications Network - TC |  | 2025-01-01 | 2025-01-22 | 2025-11-27 | 2025-12-18 | 0 | 0 | 73686.85 | Planned Total Cost | [16 empty] | 17486.55 | 56200.31
|  |  | JDH3-02-008-L-59-Telecommunications Network - TC |  | 2025-01-01 | 2025-01-22 | 2025-11-27 | 2025-12-18 | 0 | 0 | 73686.85 | Remaining Total Cost | [16 empty] | 17486.55 | 56200.31
|  |  | JDH3-02-008-L-59-Telecommunications Network - TC |  | 2025-01-01 | 2025-01-22 | 2025-11-27 | 2025-12-18 | 0 | 0 | 73686.85 | Actual Total Cost
|  |  | JDH3-02-008-L-59-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-01-01 | 2025-01-14 | 2025-11-27 | 2025-12-10 | 0 | 0 | 49961.57 | Planned Total Cost | [16 empty] | 17486.55 | 32475.02
|  |  | JDH3-02-008-L-59-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-01-01 | 2025-01-14 | 2025-11-27 | 2025-12-10 | 0 | 0 | 49961.57 | Remaining Total Cost | [16 empty] | 17486.55 | 32475.02
|  |  | JDH3-02-008-L-59-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-01-01 | 2025-01-14 | 2025-11-27 | 2025-12-10 | 0 | 0 | 49961.57 | Actual Total Cost
|  |  | JDH3-02-008-L-59-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-01-15 | 2025-01-22 | 2025-12-11 | 2025-12-18 | 0 | 0 | 23725.29 | Planned Total Cost | [17 empty] | 23725.29
|  |  | JDH3-02-008-L-59-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-01-15 | 2025-01-22 | 2025-12-11 | 2025-12-18 | 0 | 0 | 23725.29 | Remaining Total Cost | [17 empty] | 23725.29
|  |  | JDH3-02-008-L-59-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-01-15 | 2025-01-22 | 2025-12-11 | 2025-12-18 | 0 | 0 | 23725.29 | Actual Total Cost
|  |  | L-60 |  | 2024-08-27 | 2025-01-19 | 14-Oct-24 A | 2025-11-15 | 2404111.64 | 2404111.64 | 3311453.52 | Planned Total Cost |  |  | 1408812.57 | 221414.29 | 326595.47 | 300177.06 | [8 empty] | 12840.09 | 843597.91 | 198016.12
|  |  | L-60 |  | 2024-08-27 | 2025-01-19 | 14-Oct-24 A | 2025-11-15 | 2404111.64 | 2404111.64 | 3311453.52 | Remaining Total Cost | [15 empty] | 709325.73 | 198016.12
|  |  | L-60 |  | 2024-08-27 | 2025-01-19 | 14-Oct-24 A | 2025-11-15 | 2404111.64 | 2404111.64 | 3311453.52 | Actual Total Cost |  |  |  |  | 5578.07 | 132634.4 | 222925.1 | 81873.47 | 363890.53 | 150190.14 | 359882.02 | 310838.8 | 140539.99 | 320460.21 | 300245.1 | 15053.83
|  |  | JDH3-02-008-L-60-Sewage Network - SS |  | 2024-09-04 | 2024-11-16 | 26-Nov-24 A | 2025-10-11 | 603828 | 603827.99 | 670729.75 | Planned Total Cost |  |  | 373962.73 | 158972.44 | 90403.1 | [9 empty] | 12840.09 | 34551.38
|  |  | JDH3-02-008-L-60-Sewage Network - SS |  | 2024-09-04 | 2024-11-16 | 26-Nov-24 A | 2025-10-11 | 603828 | 603827.99 | 670729.75 | Remaining Total Cost | [15 empty] | 66901.74
|  |  | JDH3-02-008-L-60-Sewage Network - SS |  | 2024-09-04 | 2024-11-16 | 26-Nov-24 A | 2025-10-11 | 603828 | 603827.99 | 670729.75 | Actual Total Cost |  |  |  |  | 5578.07 | 132634.4 | 222925.1 | 46544.89 | 24700.27 | 18689.23 | 17432.82 | 1148.22 |  | 45572.17 | 85372.01 | 3230.83
|  |  | JDH3-02-008-L-60-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2024-09-04 | 2024-10-12 | 28-Dec-24 A | 15-Sep-25 A | 2189-05-26 00:58 | 2189-05-26 00:43 | 105703.04 | Planned Total Cost |  |  | 84562.43 | 18504.93 | [10 empty] | 2635.68
|  |  | JDH3-02-008-L-60-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2024-09-04 | 2024-10-12 | 28-Dec-24 A | 15-Sep-25 A | 2189-05-26 00:58 | 2189-05-26 00:43 | 105703.04 | Remaining Total Cost
|  |  | JDH3-02-008-L-60-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2024-09-04 | 2024-10-12 | 28-Dec-24 A | 15-Sep-25 A | 2189-05-26 00:58 | 2189-05-26 00:43 | 105703.04 | Actual Total Cost | [5 empty] | 621.78 | 20422.77 | 21215.46 | 23537.07 | 18689.23 | 17432.82 | 1148.22 |  | 1265.13 | 1370.55
|  |  | JDH3-02-008-L-60-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2024-09-04 | 2024-10-24 | 26-Nov-24 A | 2025-10-02 | 333070.87 | 333070.87 | 334684.19 | Planned Total Cost |  |  | 247294.43 | 77185.35 | [10 empty] | 10204.41
|  |  | JDH3-02-008-L-60-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2024-09-04 | 2024-10-24 | 26-Nov-24 A | 2025-10-02 | 333070.87 | 333070.87 | 334684.19 | Remaining Total Cost | [15 empty] | 1613.31
|  |  | JDH3-02-008-L-60-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2024-09-04 | 2024-10-24 | 26-Nov-24 A | 2025-10-02 | 333070.87 | 333070.87 | 334684.19 | Actual Total Cost |  |  |  |  | 5578.07 | 121950.55 | 172625.73 | 23162.21 | 1163.2 |  |  |  |  | 2321.92 | 6036.99 | 232.19
|  |  | JDH3-02-008-L-60-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2024-09-04 | 2024-10-27 | 17-Dec-24 A | 2025-10-05 | 2015-04-11 20:53 | 2015-04-11 20:53 | 49536.32 | Planned Total Cost |  |  | 42105.87 | [12 empty] | 7430.45
|  |  | JDH3-02-008-L-60-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2024-09-04 | 2024-10-27 | 17-Dec-24 A | 2025-10-05 | 2015-04-11 20:53 | 2015-04-11 20:53 | 49536.32 | Remaining Total Cost | [15 empty] | 7430.45
|  |  | JDH3-02-008-L-60-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2024-09-04 | 2024-10-27 | 17-Dec-24 A | 2025-10-05 | 2015-04-11 20:53 | 2015-04-11 20:53 | 49536.32 | Actual Total Cost | [5 empty] | 10062.07 | 29876.59 | 2167.21
|  |  | JDH3-02-008-L-60-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2024-10-28 | 2024-11-16 | 08-Aug-25 A | 2025-10-11 | 2236-08-13 05:17 | 2236-08-13 05:17 | 180806.2 | Planned Total Cost |  |  |  | 63282.17 | 90403.1 | [10 empty] | 27120.93
|  |  | JDH3-02-008-L-60-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2024-10-28 | 2024-11-16 | 08-Aug-25 A | 2025-10-11 | 2236-08-13 05:17 | 2236-08-13 05:17 | 180806.2 | Remaining Total Cost | [15 empty] | 57857.98
|  |  | JDH3-02-008-L-60-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2024-10-28 | 2024-11-16 | 08-Aug-25 A | 2025-10-11 | 2236-08-13 05:17 | 2236-08-13 05:17 | 180806.2 | Actual Total Cost | [13 empty] | 41985.12 | 77964.46 | 2998.63
|  |  | JDH3-02-008-L-60-Storm Network - ST |  | 2024-09-04 | 2024-12-26 | 24-Feb-25 A | 2025-11-04 | 1608287.22 | 1608287.22 | 2050728.69 | Planned Total Cost |  |  | 1034849.84 | 62441.85 | 181945.09 | 162427.92 | [9 empty] | 581182.72 | 27881.27
|  |  | JDH3-02-008-L-60-Storm Network - ST |  | 2024-09-04 | 2024-12-26 | 24-Feb-25 A | 2025-11-04 | 1608287.22 | 1608287.22 | 2050728.69 | Remaining Total Cost | [15 empty] | 414560.19 | 27881.27
|  |  | JDH3-02-008-L-60-Storm Network - ST |  | 2024-09-04 | 2024-12-26 | 24-Feb-25 A | 2025-11-04 | 1608287.22 | 1608287.22 | 2050728.69 | Actual Total Cost | [7 empty] | 28634.05 | 315807.4 | 106406.85 | 321002.45 | 294319.05 | 125044.8 | 190376.53 | 214873.09 | 11823.01
|  |  | JDH3-02-008-L-60-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-10-26 | 2024-12-21 | 03-Sep-25 A | 2025-11-02 | 207324.05 | 207324.06 | 278459.98 | Planned Total Cost | [15 empty] | 267321.58 | 11138.4
|  |  | JDH3-02-008-L-60-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-10-26 | 2024-12-21 | 03-Sep-25 A | 2025-11-02 | 207324.05 | 207324.06 | 278459.98 | Remaining Total Cost | [15 empty] | 59997.52 | 11138.4
|  |  | JDH3-02-008-L-60-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-10-26 | 2024-12-21 | 03-Sep-25 A | 2025-11-02 | 207324.05 | 207324.06 | 278459.98 | Actual Total Cost | [14 empty] | 196218.53 | 11105.53
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-10-23 | 2024-11-09 | 14-Apr-25 A | 2025-10-20 | 2016-02-22 18:00 | 2016-02-22 18:14 | 58717.45 | Planned Total Cost |  |  |  | 38499.52 | 20217.93
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-10-23 | 2024-11-09 | 14-Apr-25 A | 2025-10-20 | 2016-02-22 18:00 | 2016-02-22 18:14 | 58717.45 | Remaining Total Cost | [15 empty] | 16294.69
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-10-23 | 2024-11-09 | 14-Apr-25 A | 2025-10-20 | 2016-02-22 18:00 | 2016-02-22 18:14 | 58717.45 | Actual Total Cost | [9 empty] | 25406.25 | 4566.22 | 3042.48 | 702.11 | 3704.58 | 4815.89 | 185.23
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2024-10-31 | 2024-12-17 | 04-Aug-25 A | 17-Aug-25 A | 1931-08-26 21:22 | 1931-08-26 21:22 | 11561.89 | Planned Total Cost |  |  |  | 1156.19 | 9249.52 | 1156.19
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2024-10-31 | 2024-12-17 | 04-Aug-25 A | 17-Aug-25 A | 1931-08-26 21:22 | 1931-08-26 21:22 | 11561.89 | Remaining Total Cost
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2024-10-31 | 2024-12-17 | 04-Aug-25 A | 17-Aug-25 A | 1931-08-26 21:22 | 1931-08-26 21:22 | 11561.89 | Actual Total Cost | [13 empty] | 11561.89
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-09-15 | 11-Mar-25 A | 24-May-25 A | 2019-12-10 10:05 | 2019-12-10 09:50 | 43809.42 | Planned Total Cost |  |  | 43809.42
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-09-15 | 11-Mar-25 A | 24-May-25 A | 2019-12-10 10:05 | 2019-12-10 09:50 | 43809.42 | Remaining Total Cost
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-09-15 | 11-Mar-25 A | 24-May-25 A | 2019-12-10 10:05 | 2019-12-10 09:50 | 43809.42 | Actual Total Cost | [8 empty] | 13964.25 | 25464.22 | 4380.94
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-11-13 | 24-Feb-25 A | 17-Aug-25 A | 2215-07-28 03:50 | 2215-07-28 04:05 | 115261.16 | Planned Total Cost |  |  | 92208.93 | 11561.72 | 11490.51
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-11-13 | 24-Feb-25 A | 17-Aug-25 A | 2215-07-28 03:50 | 2215-07-28 04:05 | 115261.16 | Remaining Total Cost
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-11-13 | 24-Feb-25 A | 17-Aug-25 A | 2215-07-28 03:50 | 2215-07-28 04:05 | 115261.16 | Actual Total Cost | [7 empty] | 14767.84 | 83222.78 | 963.34 | 4816.69 |  |  | 11490.52
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-11-13 | 11-Mar-25 A | 2025-10-21 | 2202-07-19 13:41 | 2202-07-19 13:26 | 120764.62 | Planned Total Cost |  |  | 108688.16 | 1816.41 | 10260.06
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-11-13 | 11-Mar-25 A | 2025-10-21 | 2202-07-19 13:41 | 2202-07-19 13:26 | 120764.62 | Remaining Total Cost | [15 empty] | 10260.06
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-11-13 | 11-Mar-25 A | 2025-10-21 | 2202-07-19 13:41 | 2202-07-19 13:26 | 120764.62 | Actual Total Cost | [8 empty] | 74345.71 | 22265.98 | 13136.03 | 756.84
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-11-16 | 25-Feb-25 A | 19-Aug-25 A | 211294.7 | 211294.69 | 211294.7 | Planned Total Cost |  |  | 190165.23 | 9408.02 | 11721.45
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-11-16 | 25-Feb-25 A | 19-Aug-25 A | 211294.7 | 211294.69 | 211294.7 | Remaining Total Cost
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-11-16 | 25-Feb-25 A | 19-Aug-25 A | 211294.7 | 211294.69 | 211294.7 | Actual Total Cost | [7 empty] | 13866.21 | 144274.65 | 10894.88 | 16738.75 | 18502.75 |  | 7017.44
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-11-20 | 20-Apr-25 A | 24-Aug-25 A | 318692.81 | 318692.81 | 318692.81 | Planned Total Cost |  |  | 254954.25 |  | 63738.56
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-11-20 | 20-Apr-25 A | 24-Aug-25 A | 318692.81 | 318692.81 | 318692.81 | Remaining Total Cost
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-11-20 | 20-Apr-25 A | 24-Aug-25 A | 318692.81 | 318692.81 | 318692.81 | Actual Total Cost | [9 empty] | 21412.17 | 126149.23 | 106011.86 | 41271.49 | 23848.05
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-12-12 | 20-May-25 A | 2025-10-20 | 2128-07-20 07:12 | 2128-07-20 07:26 | 89759.68 | Planned Total Cost |  |  | 22439.92 |  |  | 67319.76
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-12-12 | 20-May-25 A | 2025-10-20 | 2128-07-20 07:12 | 2128-07-20 07:26 | 89759.68 | Remaining Total Cost | [15 empty] | 6281.38
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 1100 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-12-12 | 20-May-25 A | 2025-10-20 | 2128-07-20 07:12 | 2128-07-20 07:26 | 89759.68 | Actual Total Cost | [10 empty] | 13744.45 | 8695.47 |  | 58529.63 | 2415.84 | 92.92
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-12-12 | 15-May-25 A | 2025-10-20 | 2442-08-21 23:46 | 2442-08-21 23:46 | 206062.39 | Planned Total Cost |  |  | 164849.91 |  |  | 41212.48
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-12-12 | 15-May-25 A | 2025-10-20 | 2442-08-21 23:46 | 2442-08-21 23:46 | 206062.39 | Remaining Total Cost | [15 empty] | 7865.4
|  |  | JDH3-02-008-L-60-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2024-09-04 | 2024-12-12 | 15-May-25 A | 2025-10-20 | 2442-08-21 23:46 | 2442-08-21 23:46 | 206062.39 | Actual Total Cost | [10 empty] | 28762.88 | 58169.7 | 77917.34 | 21484.92 | 11422.82 | 439.34
|  |  | JDH3-02-008-L-60-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-09-04 | 2024-12-17 | 15-May-25 A | 2025-10-23 | 1972-10-21 04:19 | 1972-10-21 04:05 | 31286.09 | Planned Total Cost |  |  | 15643.05 |  | 5447.82 | 5502.31 | [9 empty] | 4692.91
|  |  | JDH3-02-008-L-60-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-09-04 | 2024-12-17 | 15-May-25 A | 2025-10-23 | 1972-10-21 04:19 | 1972-10-21 04:05 | 31286.09 | Remaining Total Cost | [15 empty] | 4692.91
|  |  | JDH3-02-008-L-60-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-09-04 | 2024-12-17 | 15-May-25 A | 2025-10-23 | 1972-10-21 04:19 | 1972-10-21 04:05 | 31286.09 | Actual Total Cost | [10 empty] | 12221.13 | 8869.74 |  | 5502.31
|  |  | JDH3-02-008-L-60-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2024-09-04 | 2024-12-19 | 19-May-25 A | 2025-10-26 | 1925-04-05 06:14 | 1925-04-05 06:14 | 13687.66 | Planned Total Cost |  |  | 6843.83 |  | 2383.42 | [10 empty] | 4460.41
|  |  | JDH3-02-008-L-60-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2024-09-04 | 2024-12-19 | 19-May-25 A | 2025-10-26 | 1925-04-05 06:14 | 1925-04-05 06:14 | 13687.66 | Remaining Total Cost | [15 empty] | 4460.41
|  |  | JDH3-02-008-L-60-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2024-09-04 | 2024-12-19 | 19-May-25 A | 2025-10-26 | 1925-04-05 06:14 | 1925-04-05 06:14 | 13687.66 | Actual Total Cost | [10 empty] | 4277.4 | 4949.86
|  |  | JDH3-02-008-L-60-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2024-09-04 | 2024-12-22 | 15-May-25 A | 2025-10-06 | 2136-08-16 19:41 | 2136-08-16 19:41 | 101679.79 | Planned Total Cost |  |  | 50839.89 |  | 17852.98 | 17734.94 | [9 empty] | 15251.97
|  |  | JDH3-02-008-L-60-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2024-09-04 | 2024-12-22 | 15-May-25 A | 2025-10-06 | 2136-08-16 19:41 | 2136-08-16 19:41 | 101679.79 | Remaining Total Cost | [15 empty] | 15251.97
|  |  | JDH3-02-008-L-60-(ST)- MH WORKS With (1500) diameter depth from 2.51 to 3.50 |  | 2024-09-04 | 2024-12-22 | 15-May-25 A | 2025-10-06 | 2136-08-16 19:41 | 2136-08-16 19:41 | 101679.79 | Actual Total Cost | [10 empty] | 36541.18 | 32151.7 |  | 17734.94
|  |  | JDH3-02-008-L-60-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2024-09-04 | 2024-12-24 | 19-May-25 A | 2025-10-06 | 1942-06-20 16:19 | 1942-06-20 16:19 | 18250.22 | Planned Total Cost |  |  | 9125.11 |  | 3177.9 | 3209.68 | [9 empty] | 2737.53
|  |  | JDH3-02-008-L-60-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2024-09-04 | 2024-12-24 | 19-May-25 A | 2025-10-06 | 1942-06-20 16:19 | 1942-06-20 16:19 | 18250.22 | Remaining Total Cost | [15 empty] | 2737.53
|  |  | JDH3-02-008-L-60-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2024-09-04 | 2024-12-24 | 19-May-25 A | 2025-10-06 | 1942-06-20 16:19 | 1942-06-20 16:19 | 18250.22 | Actual Total Cost | [10 empty] | 1558.52 | 5590.62 | 5153.86 | 3209.68
|  |  | JDH3-02-008-L-60-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2024-09-04 | 2024-12-26 | 15-May-25 A | 2025-10-06 | 2250-05-23 15:36 | 2250-05-23 15:22 | 150564.29 | Planned Total Cost |  |  | 75282.14 |  | 26404.93 | 26292.57 | [9 empty] | 22584.64
|  |  | JDH3-02-008-L-60-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2024-09-04 | 2024-12-26 | 15-May-25 A | 2025-10-06 | 2250-05-23 15:36 | 2250-05-23 15:22 | 150564.29 | Remaining Total Cost | [15 empty] | 22584.64
|  |  | JDH3-02-008-L-60-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2024-09-04 | 2024-12-26 | 15-May-25 A | 2025-10-06 | 2250-05-23 15:36 | 2250-05-23 15:22 | 150564.29 | Actual Total Cost | [10 empty] | 54109.04 | 47578.03 |  | 26292.57
|  |  | JDH3-02-008-L-60-(ST)- Single Catchbasine Works |  | 2024-11-17 | 2024-12-02 | 2025-10-19 | 2025-11-04 | 0 | 0 | 78215.26 | Planned Total Cost | [15 empty] | 73391.99 | 4823.27
|  |  | JDH3-02-008-L-60-(ST)- Single Catchbasine Works |  | 2024-11-17 | 2024-12-02 | 2025-10-19 | 2025-11-04 | 0 | 0 | 78215.26 | Remaining Total Cost | [15 empty] | 73391.99 | 4823.27
|  |  | JDH3-02-008-L-60-(ST)- Single Catchbasine Works |  | 2024-11-17 | 2024-12-02 | 2025-10-19 | 2025-11-04 | 0 | 0 | 78215.26 | Actual Total Cost
|  |  | JDH3-02-008-L-60-(ST)- Double Catchbasine Works |  | 2024-11-20 | 2024-12-01 | 2025-10-22 | 2025-11-03 | 0 | 0 | 181824.28 | Planned Total Cost | [15 empty] | 169904.69 | 11919.59
|  |  | JDH3-02-008-L-60-(ST)- Double Catchbasine Works |  | 2024-11-20 | 2024-12-01 | 2025-10-22 | 2025-11-03 | 0 | 0 | 181824.28 | Remaining Total Cost | [15 empty] | 169904.69 | 11919.59
|  |  | JDH3-02-008-L-60-(ST)- Double Catchbasine Works |  | 2024-11-20 | 2024-12-01 | 2025-10-22 | 2025-11-03 | 0 | 0 | 181824.28 | Actual Total Cost
|  |  | JDH3-02-008-L-60-(ST)-PIPES ENCASEMENT |  | 2024-12-09 | 2024-12-15 | 2025-10-21 | 2025-10-27 | 0 | 0 | 20837 | Planned Total Cost | [15 empty] | 20837
|  |  | JDH3-02-008-L-60-(ST)-PIPES ENCASEMENT |  | 2024-12-09 | 2024-12-15 | 2025-10-21 | 2025-10-27 | 0 | 0 | 20837 | Remaining Total Cost | [15 empty] | 20837
|  |  | JDH3-02-008-L-60-(ST)-PIPES ENCASEMENT |  | 2024-12-09 | 2024-12-15 | 2025-10-21 | 2025-10-27 | 0 | 0 | 20837 | Actual Total Cost
|  |  | JDH3-02-008-L-60-TSE Network - TSE |  | 2024-11-20 | 2024-12-21 | 02-Aug-25 A | 2025-10-06 | 2131-05-19 12:00 | 2131-05-19 12:14 | 90977.3 | Planned Total Cost |  |  |  |  | 21127.88 | 63383.63 | [9 empty] | 6465.8
|  |  | JDH3-02-008-L-60-TSE Network - TSE |  | 2024-11-20 | 2024-12-21 | 02-Aug-25 A | 2025-10-06 | 2131-05-19 12:00 | 2131-05-19 12:14 | 90977.3 | Remaining Total Cost | [15 empty] | 6465.8
|  |  | JDH3-02-008-L-60-TSE Network - TSE |  | 2024-11-20 | 2024-12-21 | 02-Aug-25 A | 2025-10-06 | 2131-05-19 12:00 | 2131-05-19 12:14 | 90977.3 | Actual Total Cost | [13 empty] | 84511.51
|  |  | JDH3-02-008-L-60-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-11-20 | 2024-12-21 | 02-Aug-25 A | 31-Aug-25 A | 2131-05-19 12:00 | 2131-05-19 12:14 | 84511.5 | Planned Total Cost |  |  |  |  | 21127.88 | 63383.63
|  |  | JDH3-02-008-L-60-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-11-20 | 2024-12-21 | 02-Aug-25 A | 31-Aug-25 A | 2131-05-19 12:00 | 2131-05-19 12:14 | 84511.5 | Remaining Total Cost
|  |  | JDH3-02-008-L-60-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-11-20 | 2024-12-21 | 02-Aug-25 A | 31-Aug-25 A | 2131-05-19 12:00 | 2131-05-19 12:14 | 84511.5 | Actual Total Cost | [13 empty] | 84511.51
|  |  | JDH3-02-008-L-60-(TSE)-Supply and install gate valves-100 mm |  | 2024-12-10 | 2024-12-14 | 2025-10-02 | 2025-10-06 | 0 | 0 | 6465.8 | Planned Total Cost | [15 empty] | 6465.8
|  |  | JDH3-02-008-L-60-(TSE)-Supply and install gate valves-100 mm |  | 2024-12-10 | 2024-12-14 | 2025-10-02 | 2025-10-06 | 0 | 0 | 6465.8 | Remaining Total Cost | [15 empty] | 6465.8
|  |  | JDH3-02-008-L-60-(TSE)-Supply and install gate valves-100 mm |  | 2024-12-10 | 2024-12-14 | 2025-10-02 | 2025-10-06 | 0 | 0 | 6465.8 | Actual Total Cost
|  |  | JDH3-02-008-L-60-Potable Water Network - WT |  | 2024-11-18 | 2024-12-29 | 11-Feb-25 A | 2025-10-18 | 2194-04-11 22:05 | 2194-04-11 22:05 | 274097.89 | Planned Total Cost |  |  |  |  | 33119.41 | 74365.52 | [9 empty] | 166612.97
|  |  | JDH3-02-008-L-60-Potable Water Network - WT |  | 2024-11-18 | 2024-12-29 | 11-Feb-25 A | 2025-10-18 | 2194-04-11 22:05 | 2194-04-11 22:05 | 274097.89 | Remaining Total Cost | [15 empty] | 166612.97
|  |  | JDH3-02-008-L-60-Potable Water Network - WT |  | 2024-11-18 | 2024-12-29 | 11-Feb-25 A | 2025-10-18 | 2194-04-11 22:05 | 2194-04-11 22:05 | 274097.89 | Actual Total Cost | [7 empty] | 6694.53 | 23382.86 | 25094.06 | 21446.74 | 15371.53 | 15495.19
|  |  | JDH3-02-008-L-60-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2024-11-18 | 2024-12-25 | 11-Feb-25 A | 2025-10-18 | 2194-04-11 22:05 | 2194-04-11 22:05 | 136477.58 | Planned Total Cost |  |  |  |  | 33119.41 | 74365.52 | [9 empty] | 28992.66
|  |  | JDH3-02-008-L-60-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2024-11-18 | 2024-12-25 | 11-Feb-25 A | 2025-10-18 | 2194-04-11 22:05 | 2194-04-11 22:05 | 136477.58 | Remaining Total Cost | [15 empty] | 28992.66
|  |  | JDH3-02-008-L-60-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2024-11-18 | 2024-12-25 | 11-Feb-25 A | 2025-10-18 | 2194-04-11 22:05 | 2194-04-11 22:05 | 136477.58 | Actual Total Cost | [7 empty] | 6694.53 | 23382.86 | 25094.06 | 21446.74 | 15371.53 | 15495.19
|  |  | JDH3-02-008-L-60-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2024-12-17 | 2024-12-21 | 2025-10-09 | 2025-10-13 | 0 | 0 | 10662.67 | Planned Total Cost | [15 empty] | 10662.67
|  |  | JDH3-02-008-L-60-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2024-12-17 | 2024-12-21 | 2025-10-09 | 2025-10-13 | 0 | 0 | 10662.67 | Remaining Total Cost | [15 empty] | 10662.67
|  |  | JDH3-02-008-L-60-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2024-12-17 | 2024-12-21 | 2025-10-09 | 2025-10-13 | 0 | 0 | 10662.67 | Actual Total Cost
|  |  | JDH3-02-008-L-60-(WT)- Supply and install 3-out fire hydrant |  | 2024-12-22 | 2024-12-29 | 2025-10-02 | 2025-10-09 | 0 | 0 | 126957.64 | Planned Total Cost | [15 empty] | 126957.64
|  |  | JDH3-02-008-L-60-(WT)- Supply and install 3-out fire hydrant |  | 2024-12-22 | 2024-12-29 | 2025-10-02 | 2025-10-09 | 0 | 0 | 126957.64 | Remaining Total Cost | [15 empty] | 126957.64
|  |  | JDH3-02-008-L-60-(WT)- Supply and install 3-out fire hydrant |  | 2024-12-22 | 2024-12-29 | 2025-10-02 | 2025-10-09 | 0 | 0 | 126957.64 | Actual Total Cost
|  |  | JDH3-02-008-L-60-Street Lighting Network -SL |  | 2024-12-30 | 2025-01-18 | 2025-10-26 | 2025-11-13 | 0 | 0 | 151233.03 | Planned Total Cost | [15 empty] | 37298.48 | 113934.55
|  |  | JDH3-02-008-L-60-Street Lighting Network -SL |  | 2024-12-30 | 2025-01-18 | 2025-10-26 | 2025-11-13 | 0 | 0 | 151233.03 | Remaining Total Cost | [15 empty] | 37298.48 | 113934.55
|  |  | JDH3-02-008-L-60-Street Lighting Network -SL |  | 2024-12-30 | 2025-01-18 | 2025-10-26 | 2025-11-13 | 0 | 0 | 151233.03 | Actual Total Cost
|  |  | JDH3-02-008-L-60-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2024-12-30 | 2025-01-18 | 2025-10-26 | 2025-11-13 | 0 | 0 | 78766.58 | Planned Total Cost | [15 empty] | 31506.63 | 47259.95
|  |  | JDH3-02-008-L-60-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2024-12-30 | 2025-01-18 | 2025-10-26 | 2025-11-13 | 0 | 0 | 78766.58 | Remaining Total Cost | [15 empty] | 31506.63 | 47259.95
|  |  | JDH3-02-008-L-60-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2024-12-30 | 2025-01-18 | 2025-10-26 | 2025-11-13 | 0 | 0 | 78766.58 | Actual Total Cost
|  |  | JDH3-02-008-L-60-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-01-05 | 2025-01-06 | 2025-11-01 | 2025-11-02 | 0 | 0 | 12116.87 | Planned Total Cost | [16 empty] | 12116.87
|  |  | JDH3-02-008-L-60-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-01-05 | 2025-01-06 | 2025-11-01 | 2025-11-02 | 0 | 0 | 12116.87 | Remaining Total Cost | [16 empty] | 12116.87
|  |  | JDH3-02-008-L-60-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-01-05 | 2025-01-06 | 2025-11-01 | 2025-11-02 | 0 | 0 | 12116.87 | Actual Total Cost
|  |  | JDH3-02-008-L-60-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2025-01-07 | 2025-01-08 | 2025-11-03 | 2025-11-04 | 0 | 0 | 756.08 | Planned Total Cost | [16 empty] | 756.08
|  |  | JDH3-02-008-L-60-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2025-01-07 | 2025-01-08 | 2025-11-03 | 2025-11-04 | 0 | 0 | 756.08 | Remaining Total Cost | [16 empty] | 756.08
|  |  | JDH3-02-008-L-60-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2025-01-07 | 2025-01-08 | 2025-11-03 | 2025-11-04 | 0 | 0 | 756.08 | Actual Total Cost
|  |  | JDH3-02-008-L-60-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-2 × 150 mm |  | 2025-01-01 | 2025-01-09 | 2025-10-28 | 2025-11-05 | 0 | 0 | 958.17 | Planned Total Cost | [15 empty] | 479.08 | 479.08
|  |  | JDH3-02-008-L-60-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-2 × 150 mm |  | 2025-01-01 | 2025-01-09 | 2025-10-28 | 2025-11-05 | 0 | 0 | 958.17 | Remaining Total Cost | [15 empty] | 479.08 | 479.08
|  |  | JDH3-02-008-L-60-(STL)-ROAD CROSSING DUCTS FOR CABLES PVC-2 × 150 mm |  | 2025-01-01 | 2025-01-09 | 2025-10-28 | 2025-11-05 | 0 | 0 | 958.17 | Actual Total Cost
|  |  | JDH3-02-008-L-60-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-01-04 | 2025-01-11 | 2025-10-30 | 2025-11-06 | 0 | 0 | 53127.68 | Planned Total Cost | [15 empty] | 5312.77 | 47814.91
|  |  | JDH3-02-008-L-60-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-01-04 | 2025-01-11 | 2025-10-30 | 2025-11-06 | 0 | 0 | 53127.68 | Remaining Total Cost | [15 empty] | 5312.77 | 47814.91
|  |  | JDH3-02-008-L-60-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-01-04 | 2025-01-11 | 2025-10-30 | 2025-11-06 | 0 | 0 | 53127.68 | Actual Total Cost
|  |  | JDH3-02-008-L-60-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2025-01-06 | 2025-01-12 | 2025-11-02 | 2025-11-08 | 0 | 0 | 5507.65 | Planned Total Cost | [16 empty] | 5507.65
|  |  | JDH3-02-008-L-60-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2025-01-06 | 2025-01-12 | 2025-11-02 | 2025-11-08 | 0 | 0 | 5507.65 | Remaining Total Cost | [16 empty] | 5507.65
|  |  | JDH3-02-008-L-60-(STL)-Drawpit with medium duty steel cover, size 900x900x1200mm |  | 2025-01-06 | 2025-01-12 | 2025-11-02 | 2025-11-08 | 0 | 0 | 5507.65 | Actual Total Cost
|  |  | JDH3-02-008-L-60-Telecommunications Network - TC |  | 2025-01-01 | 2025-01-19 | 2025-10-28 | 2025-11-15 | 0 | 0 | 73686.85 | Planned Total Cost | [15 empty] | 17486.55 | 56200.31
|  |  | JDH3-02-008-L-60-Telecommunications Network - TC |  | 2025-01-01 | 2025-01-19 | 2025-10-28 | 2025-11-15 | 0 | 0 | 73686.85 | Remaining Total Cost | [15 empty] | 17486.55 | 56200.31
|  |  | JDH3-02-008-L-60-Telecommunications Network - TC |  | 2025-01-01 | 2025-01-19 | 2025-10-28 | 2025-11-15 | 0 | 0 | 73686.85 | Actual Total Cost
|  |  | JDH3-02-008-L-60-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-01-01 | 2025-01-14 | 2025-10-28 | 2025-11-10 | 0 | 0 | 49961.57 | Planned Total Cost | [15 empty] | 17486.55 | 32475.02
|  |  | JDH3-02-008-L-60-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-01-01 | 2025-01-14 | 2025-10-28 | 2025-11-10 | 0 | 0 | 49961.57 | Remaining Total Cost | [15 empty] | 17486.55 | 32475.02
|  |  | JDH3-02-008-L-60-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-01-01 | 2025-01-14 | 2025-10-28 | 2025-11-10 | 0 | 0 | 49961.57 | Actual Total Cost
|  |  | JDH3-02-008-L-60-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-01-13 | 2025-01-19 | 2025-11-09 | 2025-11-15 | 0 | 0 | 23725.29 | Planned Total Cost | [16 empty] | 23725.29
|  |  | JDH3-02-008-L-60-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-01-13 | 2025-01-19 | 2025-11-09 | 2025-11-15 | 0 | 0 | 23725.29 | Remaining Total Cost | [16 empty] | 23725.29
|  |  | JDH3-02-008-L-60-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-01-13 | 2025-01-19 | 2025-11-09 | 2025-11-15 | 0 | 0 | 23725.29 | Actual Total Cost
|  |  | L-62 |  | 2024-08-27 | 2025-01-28 | 05-Nov-24 A | 2025-12-11 | 2064012.31 | 2064012.28 | 3264043.22 | Planned Total Cost |  |  | 1075494.75 | 639684.2 | 225929.92 | 21193.24 | [8 empty] | 299656.18 | 662857.18 | 293111.37 | 46116.37
|  |  | L-62 |  | 2024-08-27 | 2025-01-28 | 05-Nov-24 A | 2025-12-11 | 2064012.31 | 2064012.28 | 3264043.22 | Remaining Total Cost | [15 empty] | 856254.66 | 297659.88 | 46116.37
|  |  | L-62 |  | 2024-08-27 | 2025-01-28 | 05-Nov-24 A | 2025-12-11 | 2064012.31 | 2064012.28 | 3264043.22 | Actual Total Cost |  |  |  |  | 3849.43 | 26968.75 | 16090.27 | 101209.01 | 126558.07 | 92668.4 | 86522.18 | 62266.18 | 19629.69 | 1229947.33 | 289068.79 | 9234.18
|  |  | JDH3-02-008-L-62-Sewage Network - SS |  | 2024-09-04 | 2024-10-15 | 26-Nov-24 A | 2025-10-08 | 737236.16 | 737236.13 | 795059.19 | Planned Total Cost |  |  | 604345.02 | 65138.73 | [10 empty] | 74028.77 | 51546.68
|  |  | JDH3-02-008-L-62-Sewage Network - SS |  | 2024-09-04 | 2024-10-15 | 26-Nov-24 A | 2025-10-08 | 737236.16 | 737236.13 | 795059.19 | Remaining Total Cost | [15 empty] | 57823.03
|  |  | JDH3-02-008-L-62-Sewage Network - SS |  | 2024-09-04 | 2024-10-15 | 26-Nov-24 A | 2025-10-08 | 737236.16 | 737236.13 | 795059.19 | Actual Total Cost |  |  |  |  | 3849.43 | 26968.75 | 16090.27 | 101209.01 | 126558.07 | 62370.49 | 15170.14 | 7168.08 | 4066.11 | 309395.01 | 63493.95 | 896.82
|  |  | JDH3-02-008-L-62-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2024-09-04 | 2024-09-19 | 26-Nov-24 A | 14-Aug-25 A | 2113-06-19 01:55 | 2113-06-19 01:41 | 77968.08 | Planned Total Cost |  |  | 77968.08
|  |  | JDH3-02-008-L-62-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2024-09-04 | 2024-09-19 | 26-Nov-24 A | 14-Aug-25 A | 2113-06-19 01:55 | 2113-06-19 01:41 | 77968.08 | Remaining Total Cost
|  |  | JDH3-02-008-L-62-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2024-09-04 | 2024-09-19 | 26-Nov-24 A | 14-Aug-25 A | 2113-06-19 01:55 | 2113-06-19 01:41 | 77968.08 | Actual Total Cost |  |  |  |  | 554.01 | 3739.59 | 4313.84 | 17326.56 | 17648.63 | 12504.74 | 7071.7 | 926.2 | 320.61 | 13562.19
|  |  | JDH3-02-008-L-62-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2024-09-07 | 2024-09-30 | 26-Nov-24 A | 16-Sep-25 A | 2274-02-25 15:22 | 2274-02-25 14:53 | 136658.64 | Planned Total Cost |  |  | 131732.28 | [11 empty] | 4926.36
|  |  | JDH3-02-008-L-62-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2024-09-07 | 2024-09-30 | 26-Nov-24 A | 16-Sep-25 A | 2274-02-25 15:22 | 2274-02-25 14:53 | 136658.64 | Remaining Total Cost
|  |  | JDH3-02-008-L-62-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2024-09-07 | 2024-09-30 | 26-Nov-24 A | 16-Sep-25 A | 2274-02-25 15:22 | 2274-02-25 14:53 | 136658.64 | Actual Total Cost |  |  |  |  | 1747.41 | 11794.99 | 6554.26 | 33291.73 | 16522.7 |  | 7489.15 | 6241.88 | 3745.5 | 46807.82 | 2463.18
|  |  | JDH3-02-008-L-62-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 2.51 to 3.5 m. |  | 2024-09-10 | 2024-10-15 | 04-Feb-25 A | 2025-10-02 | 226892.07 | 226892.06 | 233168.42 | Planned Total Cost |  |  | 166820.03 | 7130.08 | [10 empty] | 59218.31
|  |  | JDH3-02-008-L-62-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 2.51 to 3.5 m. |  | 2024-09-10 | 2024-10-15 | 04-Feb-25 A | 2025-10-02 | 226892.07 | 226892.06 | 233168.42 | Remaining Total Cost | [15 empty] | 6276.35
|  |  | JDH3-02-008-L-62-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 2.51 to 3.5 m. |  | 2024-09-10 | 2024-10-15 | 04-Feb-25 A | 2025-10-02 | 226892.07 | 226892.06 | 233168.42 | Actual Total Cost | [7 empty] | 43684.54 | 84617.28 | 45480.08 | 168.21 |  |  | 898.46 | 51146.68 | 896.82
|  |  | JDH3-02-008-L-62-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 3.51 to 4.5 m. |  | 2024-09-04 | 2024-09-15 | 02-Aug-25 A | 2025-10-04 | 2143-07-20 19:41 | 2143-07-20 19:41 | 98840.92 | Planned Total Cost |  |  | 79072.73 | [11 empty] | 9884.09 | 9884.09
|  |  | JDH3-02-008-L-62-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 3.51 to 4.5 m. |  | 2024-09-04 | 2024-09-15 | 02-Aug-25 A | 2025-10-04 | 2143-07-20 19:41 | 2143-07-20 19:41 | 98840.92 | Remaining Total Cost | [15 empty] | 9884.09
|  |  | JDH3-02-008-L-62-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 3.51 to 4.5 m. |  | 2024-09-04 | 2024-09-15 | 02-Aug-25 A | 2025-10-04 | 2143-07-20 19:41 | 2143-07-20 19:41 | 98840.92 | Actual Total Cost | [13 empty] | 79072.73 | 9884.09
|  |  | JDH3-02-008-L-62-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2024-09-04 | 2024-09-25 | 26-Nov-24 A | 2025-10-08 | 2003-03-26 18:00 | 2003-03-26 18:00 | 49536.32 | Planned Total Cost |  |  | 37706.75 | [12 empty] | 11829.56
|  |  | JDH3-02-008-L-62-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2024-09-04 | 2024-09-25 | 26-Nov-24 A | 2025-10-08 | 2003-03-26 18:00 | 2003-03-26 18:00 | 49536.32 | Remaining Total Cost | [15 empty] | 11829.56
|  |  | JDH3-02-008-L-62-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2024-09-04 | 2024-09-25 | 26-Nov-24 A | 2025-10-08 | 2003-03-26 18:00 | 2003-03-26 18:00 | 49536.32 | Actual Total Cost |  |  |  |  | 1548.01 | 11434.16 | 5222.17 | 6906.18 | 7769.46 | 4385.68 | 441.09
|  |  | JDH3-02-008-L-62-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2024-09-18 | 2024-10-13 | 11-Aug-25 A | 2025-10-08 | 2362-11-06 19:12 | 2362-11-06 19:26 | 198886.82 | Planned Total Cost |  |  | 111045.14 | 58008.66 | [11 empty] | 29833.02
|  |  | JDH3-02-008-L-62-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2024-09-18 | 2024-10-13 | 11-Aug-25 A | 2025-10-08 | 2362-11-06 19:12 | 2362-11-06 19:26 | 198886.82 | Remaining Total Cost | [15 empty] | 29833.02
|  |  | JDH3-02-008-L-62-(SS)-MH WORKS from 3.51 to 4.50 @ 1200 mm |  | 2024-09-18 | 2024-10-13 | 11-Aug-25 A | 2025-10-08 | 2362-11-06 19:12 | 2362-11-06 19:26 | 198886.82 | Actual Total Cost | [13 empty] | 169053.81
|  |  | JDH3-02-008-L-62-Storm Network - ST |  | 2024-09-04 | 2024-10-31 | 14-Apr-25 A | 2025-10-25 | 1071632.97 | 1071632.98 | 1842748.41 | Planned Total Cost |  |  | 471149.74 | 574545.47 | [10 empty] | 225627.41 | 571425.8
|  |  | JDH3-02-008-L-62-Storm Network - ST |  | 2024-09-04 | 2024-10-31 | 14-Apr-25 A | 2025-10-25 | 1071632.97 | 1071632.98 | 1842748.41 | Remaining Total Cost | [15 empty] | 771115.44
|  |  | JDH3-02-008-L-62-Storm Network - ST |  | 2024-09-04 | 2024-10-31 | 14-Apr-25 A | 2025-10-25 | 1071632.97 | 1071632.98 | 1842748.41 | Actual Total Cost | [9 empty] | 30297.91 | 71352.04 | 55098.09 | 15563.59 | 754772.37 | 139136.24 | 5412.74
|  |  | JDH3-02-008-L-62-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-09-07 | 2024-10-09 | 03-Sep-25 A | 2025-10-18 | 2120-06-26 21:22 | 2120-06-26 21:22 | 278467.8 | Planned Total Cost | [14 empty] | 222774.24 | 55693.56
|  |  | JDH3-02-008-L-62-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-09-07 | 2024-10-09 | 03-Sep-25 A | 2025-10-18 | 2120-06-26 21:22 | 2120-06-26 21:22 | 278467.8 | Remaining Total Cost | [15 empty] | 197934.91
|  |  | JDH3-02-008-L-62-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2024-09-07 | 2024-10-09 | 03-Sep-25 A | 2025-10-18 | 2120-06-26 21:22 | 2120-06-26 21:22 | 278467.8 | Actual Total Cost | [14 empty] | 76561.88 | 3971.01
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-09-10 | 2024-10-06 | 07-Aug-25 A | 2025-10-12 | 0 | 0 | 65010.68 | Planned Total Cost |  |  | 58509.61 | 6501.07
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-09-10 | 2024-10-06 | 07-Aug-25 A | 2025-10-12 | 0 | 0 | 65010.68 | Remaining Total Cost | [15 empty] | 65010.68
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2024-09-10 | 2024-10-06 | 07-Aug-25 A | 2025-10-12 | 0 | 0 | 65010.68 | Actual Total Cost
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-09-12 | 2024-10-06 | 07-Aug-25 A | 30-Aug-25 A | 1914-04-24 17:31 | 1914-04-24 17:31 | 5228.73 | Planned Total Cost |  |  | 4705.85 | 522.87
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-09-12 | 2024-10-06 | 07-Aug-25 A | 30-Aug-25 A | 1914-04-24 17:31 | 1914-04-24 17:31 | 5228.73 | Remaining Total Cost
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2024-09-12 | 2024-10-06 | 07-Aug-25 A | 30-Aug-25 A | 1914-04-24 17:31 | 1914-04-24 17:31 | 5228.73 | Actual Total Cost | [13 empty] | 5228.73
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2024-09-15 | 2024-10-06 | 10-Aug-25 A | 06-Sep-25 A | 2001-01-14 16:48 | 2001-01-14 17:02 | 36905.7 | Planned Total Cost |  |  | 33215.13 | [12 empty] | 3690.57
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2024-09-15 | 2024-10-06 | 10-Aug-25 A | 06-Sep-25 A | 2001-01-14 16:48 | 2001-01-14 17:02 | 36905.7 | Remaining Total Cost
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2024-09-15 | 2024-10-06 | 10-Aug-25 A | 06-Sep-25 A | 2001-01-14 16:48 | 2001-01-14 17:02 | 36905.7 | Actual Total Cost | [13 empty] | 33215.14 | 3690.57
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-09-17 | 2024-10-06 | 12-Aug-25 A | 2025-10-12 | 2172-08-26 14:38 | 2172-08-26 14:38 | 100246.23 | Planned Total Cost |  |  | 90221.61 | 10024.62
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-09-17 | 2024-10-06 | 12-Aug-25 A | 2025-10-12 | 2172-08-26 14:38 | 2172-08-26 14:38 | 100246.23 | Remaining Total Cost | [15 empty] | 659.62
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 600 mm depth from 1.51 to 2.50 m |  | 2024-09-17 | 2024-10-06 | 12-Aug-25 A | 2025-10-12 | 2172-08-26 14:38 | 2172-08-26 14:38 | 100246.23 | Actual Total Cost | [13 empty] | 90867.47 | 8396.21 | 322.93
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-09-19 | 2024-10-06 | 14-Aug-25 A | 31-Aug-25 A | 2215-08-17 02:38 | 2215-08-17 02:38 | 115281.11 | Planned Total Cost |  |  | 103753 | 11528.11
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-09-19 | 2024-10-06 | 14-Aug-25 A | 31-Aug-25 A | 2215-08-17 02:38 | 2215-08-17 02:38 | 115281.11 | Remaining Total Cost
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 700 mm depth from 1.51 to 2.50 m |  | 2024-09-19 | 2024-10-06 | 14-Aug-25 A | 31-Aug-25 A | 2215-08-17 02:38 | 2215-08-17 02:38 | 115281.11 | Actual Total Cost | [13 empty] | 115281.11
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 0.00 to 1.50 m |  | 2024-09-04 | 2024-09-19 | 14-Apr-25 A | 22-Jul-25 A | 2093-05-30 15:22 | 2093-05-30 15:07 | 70644.64 | Planned Total Cost |  |  | 70644.64
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 0.00 to 1.50 m |  | 2024-09-04 | 2024-09-19 | 14-Apr-25 A | 22-Jul-25 A | 2093-05-30 15:22 | 2093-05-30 15:07 | 70644.64 | Remaining Total Cost
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 0.00 to 1.50 m |  | 2024-09-04 | 2024-09-19 | 14-Apr-25 A | 22-Jul-25 A | 2093-05-30 15:22 | 2093-05-30 15:07 | 70644.64 | Actual Total Cost | [9 empty] | 16336.57 | 40179.14 | 5739.87 | 8389.05
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2024-09-21 | 2024-10-14 | 14-Apr-25 A | 2025-10-02 | 295962.36 | 295962.36 | 302009.2 | Planned Total Cost |  |  | 92110.7 | 209898.5
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2024-09-21 | 2024-10-14 | 14-Apr-25 A | 2025-10-02 | 295962.36 | 295962.36 | 302009.2 | Remaining Total Cost | [15 empty] | 6046.84
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 800 mm depth from 1.51 to 2.50 m |  | 2024-09-21 | 2024-10-14 | 14-Apr-25 A | 2025-10-02 | 295962.36 | 295962.36 | 302009.2 | Actual Total Cost | [9 empty] | 13961.34 | 31172.9 | 23174.57 | 7174.54 | 203616.54 | 16237.93 | 624.54
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2024-10-14 | 2024-10-24 | 17-Aug-25 A | 2025-10-04 | 2266-02-28 06:58 | 2266-02-28 06:58 | 140787.09 | Planned Total Cost |  |  |  | 140787.09
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2024-10-14 | 2024-10-24 | 17-Aug-25 A | 2025-10-04 | 2266-02-28 06:58 | 2266-02-28 06:58 | 140787.09 | Remaining Total Cost | [15 empty] | 7047.8
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 900 mm depth from 1.51 to 2.50 m |  | 2024-10-14 | 2024-10-24 | 17-Aug-25 A | 2025-10-04 | 2266-02-28 06:58 | 2266-02-28 06:58 | 140787.09 | Actual Total Cost | [13 empty] | 128155.92 | 5376.58 | 206.79
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2024-10-16 | 2024-10-27 | 20-Aug-25 A | 2025-10-02 | 2318-10-19 13:12 | 2318-10-19 13:12 | 161017.01 | Planned Total Cost |  |  |  | 161017.01
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2024-10-16 | 2024-10-27 | 20-Aug-25 A | 2025-10-02 | 2318-10-19 13:12 | 2318-10-19 13:12 | 161017.01 | Remaining Total Cost | [15 empty] | 8052.46
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 1000 mm depth from 1.51 to 2.50 m |  | 2024-10-16 | 2024-10-27 | 20-Aug-25 A | 2025-10-02 | 2318-10-19 13:12 | 2318-10-19 13:12 | 161017.01 | Actual Total Cost | [13 empty] | 145202.78 | 7474.29 | 287.47
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2024-10-16 | 2024-10-27 | 20-Aug-25 A | 15-Sep-25 A | 1978-02-10 17:17 | 1978-02-10 17:02 | 28531.72 | Planned Total Cost | [14 empty] | 2853.17 | 25678.54
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2024-10-16 | 2024-10-27 | 20-Aug-25 A | 15-Sep-25 A | 1978-02-10 17:17 | 1978-02-10 17:02 | 28531.72 | Remaining Total Cost
|  |  | JDH3-02-008-L-62-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2024-10-16 | 2024-10-27 | 20-Aug-25 A | 15-Sep-25 A | 1978-02-10 17:17 | 1978-02-10 17:02 | 28531.72 | Actual Total Cost | [13 empty] | 7132.93 | 21398.78
|  |  | JDH3-02-008-L-62-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-10-16 | 2024-10-27 | 20-Aug-25 A | 2025-10-08 | 1971-05-18 17:46 | 1971-05-18 17:46 | 52143.49 | Planned Total Cost |  |  |  | 26071.74 | [11 empty] | 26071.74
|  |  | JDH3-02-008-L-62-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-10-16 | 2024-10-27 | 20-Aug-25 A | 2025-10-08 | 1971-05-18 17:46 | 1971-05-18 17:46 | 52143.49 | Remaining Total Cost | [15 empty] | 26071.74
|  |  | JDH3-02-008-L-62-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2024-10-16 | 2024-10-27 | 20-Aug-25 A | 2025-10-08 | 1971-05-18 17:46 | 1971-05-18 17:46 | 52143.49 | Actual Total Cost | [13 empty] | 26071.74
|  |  | JDH3-02-008-L-62-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2024-09-25 | 2024-10-10 | 01-Jun-25 A | 2025-10-13 | 1949-11-14 04:19 | 1949-11-14 04:19 | 136876.65 | Planned Total Cost |  |  | 13449.33 | 4766.85 | [11 empty] | 118660.46
|  |  | JDH3-02-008-L-62-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2024-09-25 | 2024-10-10 | 01-Jun-25 A | 2025-10-13 | 1949-11-14 04:19 | 1949-11-14 04:19 | 136876.65 | Remaining Total Cost | [15 empty] | 118660.46
|  |  | JDH3-02-008-L-62-(ST)- MH WORKS With (1500) diameter depth from 1.51 to 2.50 |  | 2024-09-25 | 2024-10-10 | 01-Jun-25 A | 2025-10-13 | 1949-11-14 04:19 | 1949-11-14 04:19 | 136876.65 | Actual Total Cost | [11 empty] | 18216.18
|  |  | JDH3-02-008-L-62-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2024-09-28 | 2024-10-10 | 01-Jun-25 A | 2025-10-15 | 1921-10-23 11:17 | 1921-10-23 11:17 | 18250.22 | Planned Total Cost |  |  | 4539.87 | 3427.6 | [11 empty] | 10282.75
|  |  | JDH3-02-008-L-62-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2024-09-28 | 2024-10-10 | 01-Jun-25 A | 2025-10-15 | 1921-10-23 11:17 | 1921-10-23 11:17 | 18250.22 | Remaining Total Cost | [15 empty] | 10282.75
|  |  | JDH3-02-008-L-62-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2024-09-28 | 2024-10-10 | 01-Jun-25 A | 2025-10-15 | 1921-10-23 11:17 | 1921-10-23 11:17 | 18250.22 | Actual Total Cost | [11 empty] | 7967.47
|  |  | JDH3-02-008-L-62-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2024-10-19 | 2024-10-29 | 2025-10-09 | 2025-10-20 | 0 | 0 | 43018.37 | Planned Total Cost | [15 empty] | 43018.37
|  |  | JDH3-02-008-L-62-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2024-10-19 | 2024-10-29 | 2025-10-09 | 2025-10-20 | 0 | 0 | 43018.37 | Remaining Total Cost | [15 empty] | 43018.37
|  |  | JDH3-02-008-L-62-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2024-10-19 | 2024-10-29 | 2025-10-09 | 2025-10-20 | 0 | 0 | 43018.37 | Actual Total Cost
|  |  | JDH3-02-008-L-62-(ST)- Single Catchbasine Works |  | 2024-10-16 | 2024-10-31 | 2025-10-09 | 2025-10-25 | 0 | 0 | 74304.5 | Planned Total Cost | [15 empty] | 74304.5
|  |  | JDH3-02-008-L-62-(ST)- Single Catchbasine Works |  | 2024-10-16 | 2024-10-31 | 2025-10-09 | 2025-10-25 | 0 | 0 | 74304.5 | Remaining Total Cost | [15 empty] | 74304.5
|  |  | JDH3-02-008-L-62-(ST)- Single Catchbasine Works |  | 2024-10-16 | 2024-10-31 | 2025-10-09 | 2025-10-25 | 0 | 0 | 74304.5 | Actual Total Cost
|  |  | JDH3-02-008-L-62-(ST)- Double Catchbasine Works |  | 2024-10-16 | 2024-10-27 | 2025-10-09 | 2025-10-20 | 0 | 0 | 193188.3 | Planned Total Cost | [15 empty] | 193188.3
|  |  | JDH3-02-008-L-62-(ST)- Double Catchbasine Works |  | 2024-10-16 | 2024-10-27 | 2025-10-09 | 2025-10-20 | 0 | 0 | 193188.3 | Remaining Total Cost | [15 empty] | 193188.3
|  |  | JDH3-02-008-L-62-(ST)- Double Catchbasine Works |  | 2024-10-16 | 2024-10-27 | 2025-10-09 | 2025-10-20 | 0 | 0 | 193188.3 | Actual Total Cost
|  |  | JDH3-02-008-L-62-(ST)-PIPES ENCASEMENT |  | 2024-09-28 | 2024-10-03 | 2025-10-05 | 2025-10-12 | 0 | 0 | 20837 | Planned Total Cost | [15 empty] | 20837
|  |  | JDH3-02-008-L-62-(ST)-PIPES ENCASEMENT |  | 2024-09-28 | 2024-10-03 | 2025-10-05 | 2025-10-12 | 0 | 0 | 20837 | Remaining Total Cost | [15 empty] | 20837
|  |  | JDH3-02-008-L-62-(ST)-PIPES ENCASEMENT |  | 2024-09-28 | 2024-10-03 | 2025-10-05 | 2025-10-12 | 0 | 0 | 20837 | Actual Total Cost
|  |  | JDH3-02-008-L-62-TSE Network - TSE |  | 2024-11-02 | 2024-12-03 | 02-Aug-25 A | 2025-11-08 | 2328-10-24 02:38 | 2328-10-24 02:38 | 196630.58 | Planned Total Cost |  |  |  |  | 131562.58 | 9397.33 | [9 empty] | 27598.77 | 28071.91
|  |  | JDH3-02-008-L-62-TSE Network - TSE |  | 2024-11-02 | 2024-12-03 | 02-Aug-25 A | 2025-11-08 | 2328-10-24 02:38 | 2328-10-24 02:38 | 196630.58 | Remaining Total Cost | [15 empty] | 11936.56 | 28071.91
|  |  | JDH3-02-008-L-62-TSE Network - TSE |  | 2024-11-02 | 2024-12-03 | 02-Aug-25 A | 2025-11-08 | 2328-10-24 02:38 | 2328-10-24 02:38 | 196630.58 | Actual Total Cost | [13 empty] | 130518.43 | 26103.68
|  |  | JDH3-02-008-L-62-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-11-02 | 2024-11-30 | 2025-10-26 | 2025-11-08 | 0 | 0 | 18759.98 | Planned Total Cost | [15 empty] | 9848.99 | 8910.99
|  |  | JDH3-02-008-L-62-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-11-02 | 2024-11-30 | 2025-10-26 | 2025-11-08 | 0 | 0 | 18759.98 | Remaining Total Cost | [15 empty] | 9848.99 | 8910.99
|  |  | JDH3-02-008-L-62-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2024-11-02 | 2024-11-30 | 2025-10-26 | 2025-11-08 | 0 | 0 | 18759.98 | Actual Total Cost
|  |  | JDH3-02-008-L-62-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2024-11-04 | 2024-12-03 | 02-Aug-25 A | 14-Sep-25 A | 2328-10-24 02:38 | 2328-10-24 02:38 | 156622.11 | Planned Total Cost |  |  |  |  | 131562.58 | 9397.33 | [9 empty] | 15662.21
|  |  | JDH3-02-008-L-62-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2024-11-04 | 2024-12-03 | 02-Aug-25 A | 14-Sep-25 A | 2328-10-24 02:38 | 2328-10-24 02:38 | 156622.11 | Remaining Total Cost
|  |  | JDH3-02-008-L-62-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2024-11-04 | 2024-12-03 | 02-Aug-25 A | 14-Sep-25 A | 2328-10-24 02:38 | 2328-10-24 02:38 | 156622.11 | Actual Total Cost | [13 empty] | 130518.43 | 26103.68
|  |  | JDH3-02-008-L-62-(TSE)-Supply and install gate valves-100 mm |  | 2024-11-23 | 2024-11-26 | 2025-11-02 | 2025-11-05 | 0 | 0 | 7758.96 | Planned Total Cost | [16 empty] | 7758.96
|  |  | JDH3-02-008-L-62-(TSE)-Supply and install gate valves-100 mm |  | 2024-11-23 | 2024-11-26 | 2025-11-02 | 2025-11-05 | 0 | 0 | 7758.96 | Remaining Total Cost | [16 empty] | 7758.96
|  |  | JDH3-02-008-L-62-(TSE)-Supply and install gate valves-100 mm |  | 2024-11-23 | 2024-11-26 | 2025-11-02 | 2025-11-05 | 0 | 0 | 7758.96 | Actual Total Cost
|  |  | JDH3-02-008-L-62-(TSE)-Supply and install gate valves-250 mm |  | 2024-11-23 | 2024-11-27 | 2025-11-02 | 2025-11-05 | 0 | 0 | 2566.11 | Planned Total Cost | [16 empty] | 2566.11
|  |  | JDH3-02-008-L-62-(TSE)-Supply and install gate valves-250 mm |  | 2024-11-23 | 2024-11-27 | 2025-11-02 | 2025-11-05 | 0 | 0 | 2566.11 | Remaining Total Cost | [16 empty] | 2566.11
|  |  | JDH3-02-008-L-62-(TSE)-Supply and install gate valves-250 mm |  | 2024-11-23 | 2024-11-27 | 2025-11-02 | 2025-11-05 | 0 | 0 | 2566.11 | Actual Total Cost
|  |  | JDH3-02-008-L-62-(TSE)-Supply and install of Air valves-50 mm. |  | 2024-11-23 | 2024-11-26 | 2025-11-02 | 2025-11-05 | 0 | 0 | 7444.14 | Planned Total Cost | [16 empty] | 7444.14
|  |  | JDH3-02-008-L-62-(TSE)-Supply and install of Air valves-50 mm. |  | 2024-11-23 | 2024-11-26 | 2025-11-02 | 2025-11-05 | 0 | 0 | 7444.14 | Remaining Total Cost | [16 empty] | 7444.14
|  |  | JDH3-02-008-L-62-(TSE)-Supply and install of Air valves-50 mm. |  | 2024-11-23 | 2024-11-26 | 2025-11-02 | 2025-11-05 | 0 | 0 | 7444.14 | Actual Total Cost
|  |  | JDH3-02-008-L-62-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2024-11-09 | 2024-11-17 | 2025-10-26 | 2025-11-03 | 0 | 0 | 3479.28 | Planned Total Cost | [15 empty] | 2087.57 | 1391.71
|  |  | JDH3-02-008-L-62-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2024-11-09 | 2024-11-17 | 2025-10-26 | 2025-11-03 | 0 | 0 | 3479.28 | Remaining Total Cost | [15 empty] | 2087.57 | 1391.71
|  |  | JDH3-02-008-L-62-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2024-11-09 | 2024-11-17 | 2025-10-26 | 2025-11-03 | 0 | 0 | 3479.28 | Actual Total Cost
|  |  | JDH3-02-008-L-62-Potable Water Network - WT |  | 2024-11-04 | 2024-12-09 | 02-Aug-25 A | 2025-11-10 | 2169-09-26 01:26 | 2169-09-26 01:26 | 190755.65 | Planned Total Cost |  |  |  |  | 94367.34 | 11795.92 | [9 empty] | 12285.94 | 72306.44
|  |  | JDH3-02-008-L-62-Potable Water Network - WT |  | 2024-11-04 | 2024-12-09 | 02-Aug-25 A | 2025-11-10 | 2169-09-26 01:26 | 2169-09-26 01:26 | 190755.65 | Remaining Total Cost | [15 empty] | 15379.63 | 76854.95
|  |  | JDH3-02-008-L-62-Potable Water Network - WT |  | 2024-11-04 | 2024-12-09 | 02-Aug-25 A | 2025-11-10 | 2169-09-26 01:26 | 2169-09-26 01:26 | 190755.65 | Actual Total Cost | [13 empty] | 35261.53 | 60334.92 | 2924.61
|  |  | JDH3-02-008-L-62-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2024-11-04 | 2024-12-09 | 02-Aug-25 A | 2025-11-08 | 2169-09-26 01:26 | 2169-09-26 01:26 | 117959.18 | Planned Total Cost |  |  |  |  | 94367.34 | 11795.92 | [9 empty] | 5897.96 | 5897.96
|  |  | JDH3-02-008-L-62-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2024-11-04 | 2024-12-09 | 02-Aug-25 A | 2025-11-08 | 2169-09-26 01:26 | 2169-09-26 01:26 | 117959.18 | Remaining Total Cost | [15 empty] | 8991.65 | 10446.47
|  |  | JDH3-02-008-L-62-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2024-11-04 | 2024-12-09 | 02-Aug-25 A | 2025-11-08 | 2169-09-26 01:26 | 2169-09-26 01:26 | 117959.18 | Actual Total Cost | [13 empty] | 35261.53 | 60334.92 | 2924.61
|  |  | JDH3-02-008-L-62-(WT)- Supply and install HDPE Pipes -225 mm depth from 0 to 1.5 m |  | 2024-11-10 | 2024-12-04 | 2025-10-28 | 2025-11-10 | 0 | 0 | 178.21 | Planned Total Cost | [15 empty] | 40.1 | 138.12
|  |  | JDH3-02-008-L-62-(WT)- Supply and install HDPE Pipes -225 mm depth from 0 to 1.5 m |  | 2024-11-10 | 2024-12-04 | 2025-10-28 | 2025-11-10 | 0 | 0 | 178.21 | Remaining Total Cost | [15 empty] | 40.1 | 138.12
|  |  | JDH3-02-008-L-62-(WT)- Supply and install HDPE Pipes -225 mm depth from 0 to 1.5 m |  | 2024-11-10 | 2024-12-04 | 2025-10-28 | 2025-11-10 | 0 | 0 | 178.21 | Actual Total Cost
|  |  | JDH3-02-008-L-62-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2024-11-26 | 2024-12-02 | 2025-11-04 | 2025-11-08 | 0 | 0 | 9139.43 | Planned Total Cost | [16 empty] | 9139.43
|  |  | JDH3-02-008-L-62-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2024-11-26 | 2024-12-02 | 2025-11-04 | 2025-11-08 | 0 | 0 | 9139.43 | Remaining Total Cost | [16 empty] | 9139.43
|  |  | JDH3-02-008-L-62-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2024-11-26 | 2024-12-02 | 2025-11-04 | 2025-11-08 | 0 | 0 | 9139.43 | Actual Total Cost
|  |  | JDH3-02-008-L-62-(WT)- Supply and install 3-out fire hydrant |  | 2024-11-12 | 2024-11-18 | 2025-10-30 | 2025-11-05 | 0 | 0 | 63478.82 | Planned Total Cost | [15 empty] | 6347.88 | 57130.94
|  |  | JDH3-02-008-L-62-(WT)- Supply and install 3-out fire hydrant |  | 2024-11-12 | 2024-11-18 | 2025-10-30 | 2025-11-05 | 0 | 0 | 63478.82 | Remaining Total Cost | [15 empty] | 6347.88 | 57130.94
|  |  | JDH3-02-008-L-62-(WT)- Supply and install 3-out fire hydrant |  | 2024-11-12 | 2024-11-18 | 2025-10-30 | 2025-11-05 | 0 | 0 | 63478.82 | Actual Total Cost
|  |  | JDH3-02-008-L-62-Street Lighting Network -SL |  | 2024-12-29 | 2025-01-21 | 2025-11-11 | 2025-12-04 | 0 | 0 | 174630.04 | Planned Total Cost | [16 empty] | 149273.3 | 25356.74
|  |  | JDH3-02-008-L-62-Street Lighting Network -SL |  | 2024-12-29 | 2025-01-21 | 2025-11-11 | 2025-12-04 | 0 | 0 | 174630.04 | Remaining Total Cost | [16 empty] | 149273.3 | 25356.74
|  |  | JDH3-02-008-L-62-Street Lighting Network -SL |  | 2024-12-29 | 2025-01-21 | 2025-11-11 | 2025-12-04 | 0 | 0 | 174630.04 | Actual Total Cost
|  |  | JDH3-02-008-L-62-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx6 mm² |  | 2024-12-29 | 2025-01-20 | 2025-11-11 | 2025-12-03 | 0 | 0 | 32501.03 | Planned Total Cost | [16 empty] | 30063.45 | 2437.58
|  |  | JDH3-02-008-L-62-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx6 mm² |  | 2024-12-29 | 2025-01-20 | 2025-11-11 | 2025-12-03 | 0 | 0 | 32501.03 | Remaining Total Cost | [16 empty] | 30063.45 | 2437.58
|  |  | JDH3-02-008-L-62-(STL)- Insulated Stranded armored Cables Copper- XLPE /PVC/SWA 4Cx6 mm² |  | 2024-12-29 | 2025-01-20 | 2025-11-11 | 2025-12-03 | 0 | 0 | 32501.03 | Actual Total Cost
|  |  | JDH3-02-008-L-62-(STL)- Supply,install,connect and test single core PVC insulated copper 6mm2 |  | 2025-01-07 | 2025-01-15 | 2025-11-20 | 2025-11-29 | 0 | 0 | 3529.72 | Planned Total Cost | [16 empty] | 3529.72
|  |  | JDH3-02-008-L-62-(STL)- Supply,install,connect and test single core PVC insulated copper 6mm2 |  | 2025-01-07 | 2025-01-15 | 2025-11-20 | 2025-11-29 | 0 | 0 | 3529.72 | Remaining Total Cost | [16 empty] | 3529.72
|  |  | JDH3-02-008-L-62-(STL)- Supply,install,connect and test single core PVC insulated copper 6mm2 |  | 2025-01-07 | 2025-01-15 | 2025-11-20 | 2025-11-29 | 0 | 0 | 3529.72 | Actual Total Cost
|  |  | JDH3-02-008-L-62-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2025-01-02 | 2025-01-21 | 2025-11-16 | 2025-12-04 | 0 | 0 | 75186.28 | Planned Total Cost | [16 empty] | 69171.38 | 6014.9
|  |  | JDH3-02-008-L-62-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2025-01-02 | 2025-01-21 | 2025-11-16 | 2025-12-04 | 0 | 0 | 75186.28 | Remaining Total Cost | [16 empty] | 69171.38 | 6014.9
|  |  | JDH3-02-008-L-62-(STL)-LIGHTING POLE 12 m Column with one arm. |  | 2025-01-02 | 2025-01-21 | 2025-11-16 | 2025-12-04 | 0 | 0 | 75186.28 | Actual Total Cost
|  |  | JDH3-02-008-L-62-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-01-08 | 2025-01-09 | 2025-11-22 | 2025-11-23 | 0 | 0 | 11566.1 | Planned Total Cost | [16 empty] | 11566.1
|  |  | JDH3-02-008-L-62-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-01-08 | 2025-01-09 | 2025-11-22 | 2025-11-23 | 0 | 0 | 11566.1 | Remaining Total Cost | [16 empty] | 11566.1
|  |  | JDH3-02-008-L-62-(STL)-Street Lighting( LED ) Luminaire complete with control gear and lamp, (150) W |  | 2025-01-08 | 2025-01-09 | 2025-11-22 | 2025-11-23 | 0 | 0 | 11566.1 | Actual Total Cost
|  |  | JDH3-02-008-L-62-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2025-01-11 | 2025-01-12 | 2025-11-24 | 2025-11-25 | 0 | 0 | 1134.12 | Planned Total Cost | [16 empty] | 1134.12
|  |  | JDH3-02-008-L-62-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2025-01-11 | 2025-01-12 | 2025-11-24 | 2025-11-25 | 0 | 0 | 1134.12 | Remaining Total Cost | [16 empty] | 1134.12
|  |  | JDH3-02-008-L-62-(STL)-LIGHTING POLE EARTHING SYSTEM |  | 2025-01-11 | 2025-01-12 | 2025-11-24 | 2025-11-25 | 0 | 0 | 1134.12 | Actual Total Cost
|  |  | JDH3-02-008-L-62-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-01-13 | 2025-01-20 | 2025-11-26 | 2025-12-03 | 0 | 0 | 50712.78 | Planned Total Cost | [16 empty] | 33808.52 | 16904.26
|  |  | JDH3-02-008-L-62-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-01-13 | 2025-01-20 | 2025-11-26 | 2025-12-03 | 0 | 0 | 50712.78 | Remaining Total Cost | [16 empty] | 33808.52 | 16904.26
|  |  | JDH3-02-008-L-62-(STL)-Drawpit with medium duty steel cover, size 600x600x1000mm |  | 2025-01-13 | 2025-01-20 | 2025-11-26 | 2025-12-03 | 0 | 0 | 50712.78 | Actual Total Cost
|  |  | JDH3-02-008-L-62-Telecommunications Network - TC |  | 2025-01-02 | 2025-01-28 | 2025-11-16 | 2025-12-11 | 0 | 0 | 64219.35 | Planned Total Cost | [16 empty] | 43459.72 | 20759.63
|  |  | JDH3-02-008-L-62-Telecommunications Network - TC |  | 2025-01-02 | 2025-01-28 | 2025-11-16 | 2025-12-11 | 0 | 0 | 64219.35 | Remaining Total Cost | [16 empty] | 43459.72 | 20759.63
|  |  | JDH3-02-008-L-62-Telecommunications Network - TC |  | 2025-01-02 | 2025-01-28 | 2025-11-16 | 2025-12-11 | 0 | 0 | 64219.35 | Actual Total Cost
|  |  | JDH3-02-008-L-62-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-01-02 | 2025-01-15 | 2025-11-16 | 2025-11-29 | 0 | 0 | 43459.72 | Planned Total Cost | [16 empty] | 43459.72
|  |  | JDH3-02-008-L-62-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-01-02 | 2025-01-15 | 2025-11-16 | 2025-11-29 | 0 | 0 | 43459.72 | Remaining Total Cost | [16 empty] | 43459.72
|  |  | JDH3-02-008-L-62-(TEL)-Trenches 6-ways ducts, 50mm diameter |  | 2025-01-02 | 2025-01-15 | 2025-11-16 | 2025-11-29 | 0 | 0 | 43459.72 | Actual Total Cost
|  |  | JDH3-02-008-L-62-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-01-22 | 2025-01-28 | 2025-12-06 | 2025-12-11 | 0 | 0 | 20759.63 | Planned Total Cost | [17 empty] | 20759.63
|  |  | JDH3-02-008-L-62-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-01-22 | 2025-01-28 | 2025-12-06 | 2025-12-11 | 0 | 0 | 20759.63 | Remaining Total Cost | [17 empty] | 20759.63
|  |  | JDH3-02-008-L-62-(TEL)-Manhole for feeder pathway Type 1 |  | 2025-01-22 | 2025-01-28 | 2025-12-06 | 2025-12-11 | 0 | 0 | 20759.63 | Actual Total Cost
|  |  | Z08 |  | 2025-12-25 | 2026-03-22 | 13-Jan-25 A | 2026-05-03 | 1945-10-19 18:00 | 1945-10-19 18:00 | 1581784.4 | Planned Total Cost | [15 empty] | 399242.21 | 1154359.57 | 11452.86 | 8364.88 | 8364.88
|  |  | Z08 |  | 2025-12-25 | 2026-03-22 | 13-Jan-25 A | 2026-05-03 | 1945-10-19 18:00 | 1945-10-19 18:00 | 1581784.4 | Remaining Total Cost | [15 empty] | 399242.21 | 1154359.57 | 11452.86
|  |  | Z08 |  | 2025-12-25 | 2026-03-22 | 13-Jan-25 A | 2026-05-03 | 1945-10-19 18:00 | 1945-10-19 18:00 | 1581784.4 | Actual Total Cost | [7 empty] | 10456.09 | 6273.66
|  |  | RCB |  | 2026-01-26 | 2026-03-15 | 2025-10-21 | 2025-12-08 | 0 | 0 | 1248972.48 | Planned Total Cost | [15 empty] | 168043.56 | 1069476.06 | 11452.86
|  |  | RCB |  | 2026-01-26 | 2026-03-15 | 2025-10-21 | 2025-12-08 | 0 | 0 | 1248972.48 | Remaining Total Cost | [15 empty] | 168043.56 | 1069476.06 | 11452.86
|  |  | RCB |  | 2026-01-26 | 2026-03-15 | 2025-10-21 | 2025-12-08 | 0 | 0 | 1248972.48 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z08-Storm Network - ST |  | 2026-01-26 | 2026-03-15 | 2025-10-21 | 2025-12-08 | 0 | 0 | 1248972.48 | Planned Total Cost | [15 empty] | 168043.56 | 1069476.06 | 11452.86
|  |  | JDH3-02-008-RCB-Z08-Storm Network - ST |  | 2026-01-26 | 2026-03-15 | 2025-10-21 | 2025-12-08 | 0 | 0 | 1248972.48 | Remaining Total Cost | [15 empty] | 168043.56 | 1069476.06 | 11452.86
|  |  | JDH3-02-008-RCB-Z08-Storm Network - ST |  | 2026-01-26 | 2026-03-15 | 2025-10-21 | 2025-12-08 | 0 | 0 | 1248972.48 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z08-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-01-26 | 2026-02-28 | 2025-10-21 | 2025-11-23 | 0 | 0 | 456623.84 | Planned Total Cost | [15 empty] | 114155.96 | 342467.88
|  |  | JDH3-02-008-RCB-Z08-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-01-26 | 2026-02-28 | 2025-10-21 | 2025-11-23 | 0 | 0 | 456623.84 | Remaining Total Cost | [15 empty] | 114155.96 | 342467.88
|  |  | JDH3-02-008-RCB-Z08-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-01-26 | 2026-02-28 | 2025-10-21 | 2025-11-23 | 0 | 0 | 456623.84 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z08-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-01-31 | 2026-02-25 | 2025-10-26 | 2025-11-20 | 0 | 0 | 230490.47 | Planned Total Cost | [15 empty] | 48979.22 | 181511.24
|  |  | JDH3-02-008-RCB-Z08-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-01-31 | 2026-02-25 | 2025-10-26 | 2025-11-20 | 0 | 0 | 230490.47 | Remaining Total Cost | [15 empty] | 48979.22 | 181511.24
|  |  | JDH3-02-008-RCB-Z08-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-01-31 | 2026-02-25 | 2025-10-26 | 2025-11-20 | 0 | 0 | 230490.47 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z08-(ST)- Single Catchbasine Works |  | 2026-02-04 | 2026-03-15 | 2025-10-30 | 2025-12-08 | 0 | 0 | 229057.28 | Planned Total Cost | [15 empty] | 4908.37 | 212696.05 | 11452.86
|  |  | JDH3-02-008-RCB-Z08-(ST)- Single Catchbasine Works |  | 2026-02-04 | 2026-03-15 | 2025-10-30 | 2025-12-08 | 0 | 0 | 229057.28 | Remaining Total Cost | [15 empty] | 4908.37 | 212696.05 | 11452.86
|  |  | JDH3-02-008-RCB-Z08-(ST)- Single Catchbasine Works |  | 2026-02-04 | 2026-03-15 | 2025-10-30 | 2025-12-08 | 0 | 0 | 229057.28 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z08-(ST)- Double Catchbasine Works |  | 2026-02-12 | 2026-03-04 | 2025-11-08 | 2025-11-27 | 0 | 0 | 332800.89 | Planned Total Cost | [16 empty] | 332800.89
|  |  | JDH3-02-008-RCB-Z08-(ST)- Double Catchbasine Works |  | 2026-02-12 | 2026-03-04 | 2025-11-08 | 2025-11-27 | 0 | 0 | 332800.89 | Remaining Total Cost | [16 empty] | 332800.89
|  |  | JDH3-02-008-RCB-Z08-(ST)- Double Catchbasine Works |  | 2026-02-12 | 2026-03-04 | 2025-11-08 | 2025-11-27 | 0 | 0 | 332800.89 | Actual Total Cost
|  |  | L-43 |  | 2025-12-27 | 2026-02-07 | 13-Jan-25 A | 2025-11-15 | 1945-10-19 18:00 | 1945-10-19 18:00 | 167138.47 | Planned Total Cost | [15 empty] | 65525.2 | 84883.51 |  | 8364.88 | 8364.88
|  |  | L-43 |  | 2025-12-27 | 2026-02-07 | 13-Jan-25 A | 2025-11-15 | 1945-10-19 18:00 | 1945-10-19 18:00 | 167138.47 | Remaining Total Cost | [15 empty] | 65525.2 | 84883.51
|  |  | L-43 |  | 2025-12-27 | 2026-02-07 | 13-Jan-25 A | 2025-11-15 | 1945-10-19 18:00 | 1945-10-19 18:00 | 167138.47 | Actual Total Cost | [7 empty] | 10456.09 | 6273.66
|  |  | JDH3-02-008-L-43-TSE Network - TSE |  | 2026-01-04 | 2026-01-28 | 2025-10-21 | 2025-11-15 | 0 | 0 | 144616.84 | Planned Total Cost | [15 empty] | 59733.32 | 84883.51
|  |  | JDH3-02-008-L-43-TSE Network - TSE |  | 2026-01-04 | 2026-01-28 | 2025-10-21 | 2025-11-15 | 0 | 0 | 144616.84 | Remaining Total Cost | [15 empty] | 59733.32 | 84883.51
|  |  | JDH3-02-008-L-43-TSE Network - TSE |  | 2026-01-04 | 2026-01-28 | 2025-10-21 | 2025-11-15 | 0 | 0 | 144616.84 | Actual Total Cost
|  |  | JDH3-02-008-L-43-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-01-04 | 2026-01-17 | 2025-10-21 | 2025-11-03 | 0 | 0 | 13939.02 | Planned Total Cost | [15 empty] | 12545.12 | 1393.9
|  |  | JDH3-02-008-L-43-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-01-04 | 2026-01-17 | 2025-10-21 | 2025-11-03 | 0 | 0 | 13939.02 | Remaining Total Cost | [15 empty] | 12545.12 | 1393.9
|  |  | JDH3-02-008-L-43-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-01-04 | 2026-01-17 | 2025-10-21 | 2025-11-03 | 0 | 0 | 13939.02 | Actual Total Cost
|  |  | JDH3-02-008-L-43-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-01-06 | 2026-01-28 | 2025-10-23 | 2025-11-15 | 0 | 0 | 110762.91 | Planned Total Cost | [15 empty] | 37843.99 | 72918.91
|  |  | JDH3-02-008-L-43-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-01-06 | 2026-01-28 | 2025-10-23 | 2025-11-15 | 0 | 0 | 110762.91 | Remaining Total Cost | [15 empty] | 37843.99 | 72918.91
|  |  | JDH3-02-008-L-43-(TSE)- Supply and install HDPE Pipes - 250 mm depth from 0 to 1.5 m |  | 2026-01-06 | 2026-01-28 | 2025-10-23 | 2025-11-15 | 0 | 0 | 110762.91 | Actual Total Cost
|  |  | JDH3-02-008-L-43-(TSE)-Supply and install gate valves-100 mm |  | 2026-01-11 | 2026-01-14 | 2025-10-28 | 2025-11-01 | 0 | 0 | 1293.16 | Planned Total Cost | [15 empty] | 1228.5 | 64.66
|  |  | JDH3-02-008-L-43-(TSE)-Supply and install gate valves-100 mm |  | 2026-01-11 | 2026-01-14 | 2025-10-28 | 2025-11-01 | 0 | 0 | 1293.16 | Remaining Total Cost | [15 empty] | 1228.5 | 64.66
|  |  | JDH3-02-008-L-43-(TSE)-Supply and install gate valves-100 mm |  | 2026-01-11 | 2026-01-14 | 2025-10-28 | 2025-11-01 | 0 | 0 | 1293.16 | Actual Total Cost
|  |  | JDH3-02-008-L-43-(TSE)-Supply and install gate valves-250 mm |  | 2026-01-20 | 2026-01-24 | 2025-11-06 | 2025-11-10 | 0 | 0 | 7698.34 | Planned Total Cost | [16 empty] | 7698.34
|  |  | JDH3-02-008-L-43-(TSE)-Supply and install gate valves-250 mm |  | 2026-01-20 | 2026-01-24 | 2025-11-06 | 2025-11-10 | 0 | 0 | 7698.34 | Remaining Total Cost | [16 empty] | 7698.34
|  |  | JDH3-02-008-L-43-(TSE)-Supply and install gate valves-250 mm |  | 2026-01-20 | 2026-01-24 | 2025-11-06 | 2025-11-10 | 0 | 0 | 7698.34 | Actual Total Cost
|  |  | JDH3-02-008-L-43-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-01-11 | 2026-01-14 | 2025-10-28 | 2025-11-01 | 0 | 0 | 7444.14 | Planned Total Cost | [15 empty] | 7071.93 | 372.21
|  |  | JDH3-02-008-L-43-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-01-11 | 2026-01-14 | 2025-10-28 | 2025-11-01 | 0 | 0 | 7444.14 | Remaining Total Cost | [15 empty] | 7071.93 | 372.21
|  |  | JDH3-02-008-L-43-(TSE)-Supply and install of Air valves-50 mm. |  | 2026-01-11 | 2026-01-14 | 2025-10-28 | 2025-11-01 | 0 | 0 | 7444.14 | Actual Total Cost
|  |  | JDH3-02-008-L-43-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-01-10 | 2026-01-18 | 2025-10-27 | 2025-11-04 | 0 | 0 | 3479.28 | Planned Total Cost | [15 empty] | 1043.78 | 2435.49
|  |  | JDH3-02-008-L-43-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-01-10 | 2026-01-18 | 2025-10-27 | 2025-11-04 | 0 | 0 | 3479.28 | Remaining Total Cost | [15 empty] | 1043.78 | 2435.49
|  |  | JDH3-02-008-L-43-(TSE)- Supply and Construct Air Valves Chamber on less than 315 mm Diameter pipelin |  | 2026-01-10 | 2026-01-18 | 2025-10-27 | 2025-11-04 | 0 | 0 | 3479.28 | Actual Total Cost
|  |  | JDH3-02-008-L-43-Road Works - RD |  | 2026-01-29 | 2026-02-07 | 05-Feb-25 A | 2025-10-06 | 1945-10-19 18:00 | 1945-10-19 18:00 | 22521.63 | Planned Total Cost | [15 empty] | 5791.88 |  |  | 8364.88 | 8364.88
|  |  | JDH3-02-008-L-43-Road Works - RD |  | 2026-01-29 | 2026-02-07 | 05-Feb-25 A | 2025-10-06 | 1945-10-19 18:00 | 1945-10-19 18:00 | 22521.63 | Remaining Total Cost | [15 empty] | 5791.88
|  |  | JDH3-02-008-L-43-Road Works - RD |  | 2026-01-29 | 2026-02-07 | 05-Feb-25 A | 2025-10-06 | 1945-10-19 18:00 | 1945-10-19 18:00 | 22521.63 | Actual Total Cost | [7 empty] | 10456.09 | 6273.66
|  |  | JDH3-02-008-L-43-(RD)-Precast Concrete Curb |  | 2026-01-29 | 2026-02-07 | 05-Feb-25 A | 2025-10-06 | 1945-10-19 18:00 | 1945-10-19 18:00 | 22521.63 | Planned Total Cost | [15 empty] | 5791.88 |  |  | 8364.88 | 8364.88
|  |  | JDH3-02-008-L-43-(RD)-Precast Concrete Curb |  | 2026-01-29 | 2026-02-07 | 05-Feb-25 A | 2025-10-06 | 1945-10-19 18:00 | 1945-10-19 18:00 | 22521.63 | Remaining Total Cost | [15 empty] | 5791.88
|  |  | JDH3-02-008-L-43-(RD)-Precast Concrete Curb |  | 2026-01-29 | 2026-02-07 | 05-Feb-25 A | 2025-10-06 | 1945-10-19 18:00 | 1945-10-19 18:00 | 22521.63 | Actual Total Cost | [7 empty] | 10456.09 | 6273.66
|  |  | L-44 |  | 2026-01-05 | 2026-01-25 | 01-Jul-25 A | 2025-10-20 | 0 | 0 | 47130.04 | Planned Total Cost | [15 empty] | 47130.04
|  |  | L-44 |  | 2026-01-05 | 2026-01-25 | 01-Jul-25 A | 2025-10-20 | 0 | 0 | 47130.04 | Remaining Total Cost | [15 empty] | 47130.04
|  |  | L-44 |  | 2026-01-05 | 2026-01-25 | 01-Jul-25 A | 2025-10-20 | 0 | 0 | 47130.04 | Actual Total Cost
|  |  | JDH3-02-008-L-44-TSE Network - TSE |  | 2026-01-07 | 2026-01-25 | 2025-10-02 | 2025-10-20 | 0 | 0 | 47130.04 | Planned Total Cost | [15 empty] | 47130.04
|  |  | JDH3-02-008-L-44-TSE Network - TSE |  | 2026-01-07 | 2026-01-25 | 2025-10-02 | 2025-10-20 | 0 | 0 | 47130.04 | Remaining Total Cost | [15 empty] | 47130.04
|  |  | JDH3-02-008-L-44-TSE Network - TSE |  | 2026-01-07 | 2026-01-25 | 2025-10-02 | 2025-10-20 | 0 | 0 | 47130.04 | Actual Total Cost
|  |  | JDH3-02-008-L-44-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-01-07 | 2026-01-25 | 2025-10-02 | 2025-10-20 | 0 | 0 | 44543.72 | Planned Total Cost | [15 empty] | 44543.72
|  |  | JDH3-02-008-L-44-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-01-07 | 2026-01-25 | 2025-10-02 | 2025-10-20 | 0 | 0 | 44543.72 | Remaining Total Cost | [15 empty] | 44543.72
|  |  | JDH3-02-008-L-44-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-01-07 | 2026-01-25 | 2025-10-02 | 2025-10-20 | 0 | 0 | 44543.72 | Actual Total Cost
|  |  | JDH3-02-008-L-44-(TSE)-Supply and install gate valves-100 mm |  | 2026-01-18 | 2026-01-21 | 2025-10-13 | 2025-10-16 | 0 | 0 | 2586.32 | Planned Total Cost | [15 empty] | 2586.32
|  |  | JDH3-02-008-L-44-(TSE)-Supply and install gate valves-100 mm |  | 2026-01-18 | 2026-01-21 | 2025-10-13 | 2025-10-16 | 0 | 0 | 2586.32 | Remaining Total Cost | [15 empty] | 2586.32
|  |  | JDH3-02-008-L-44-(TSE)-Supply and install gate valves-100 mm |  | 2026-01-18 | 2026-01-21 | 2025-10-13 | 2025-10-16 | 0 | 0 | 2586.32 | Actual Total Cost
|  |  | L-45 |  | 2026-02-08 | 2026-03-04 | 02-Jul-25 A | 2025-10-19 | 0 | 0 | 37647.55 | Planned Total Cost | [15 empty] | 37647.55
|  |  | L-45 |  | 2026-02-08 | 2026-03-04 | 02-Jul-25 A | 2025-10-19 | 0 | 0 | 37647.55 | Remaining Total Cost | [15 empty] | 37647.55
|  |  | L-45 |  | 2026-02-08 | 2026-03-04 | 02-Jul-25 A | 2025-10-19 | 0 | 0 | 37647.55 | Actual Total Cost
|  |  | JDH3-02-008-L-45-TSE Network - TSE |  | 2026-02-16 | 2026-03-04 | 2025-10-02 | 2025-10-19 | 0 | 0 | 37647.55 | Planned Total Cost | [15 empty] | 37647.55
|  |  | JDH3-02-008-L-45-TSE Network - TSE |  | 2026-02-16 | 2026-03-04 | 2025-10-02 | 2025-10-19 | 0 | 0 | 37647.55 | Remaining Total Cost | [15 empty] | 37647.55
|  |  | JDH3-02-008-L-45-TSE Network - TSE |  | 2026-02-16 | 2026-03-04 | 2025-10-02 | 2025-10-19 | 0 | 0 | 37647.55 | Actual Total Cost
|  |  | JDH3-02-008-L-45-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-02-16 | 2026-03-04 | 2025-10-02 | 2025-10-19 | 0 | 0 | 36354.39 | Planned Total Cost | [15 empty] | 36354.39
|  |  | JDH3-02-008-L-45-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-02-16 | 2026-03-04 | 2025-10-02 | 2025-10-19 | 0 | 0 | 36354.39 | Remaining Total Cost | [15 empty] | 36354.39
|  |  | JDH3-02-008-L-45-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-02-16 | 2026-03-04 | 2025-10-02 | 2025-10-19 | 0 | 0 | 36354.39 | Actual Total Cost
|  |  | JDH3-02-008-L-45-(TSE)-Supply and install gate valves-100 mm |  | 2026-02-25 | 2026-03-01 | 2025-10-12 | 2025-10-15 | 0 | 0 | 1293.16 | Planned Total Cost | [15 empty] | 1293.16
|  |  | JDH3-02-008-L-45-(TSE)-Supply and install gate valves-100 mm |  | 2026-02-25 | 2026-03-01 | 2025-10-12 | 2025-10-15 | 0 | 0 | 1293.16 | Remaining Total Cost | [15 empty] | 1293.16
|  |  | JDH3-02-008-L-45-(TSE)-Supply and install gate valves-100 mm |  | 2026-02-25 | 2026-03-01 | 2025-10-12 | 2025-10-15 | 0 | 0 | 1293.16 | Actual Total Cost
|  |  | L-46 |  | 2026-01-29 | 2026-02-19 | 05-Jul-25 A | 2025-10-18 | 0 | 0 | 17709.16 | Planned Total Cost | [15 empty] | 17709.16
|  |  | L-46 |  | 2026-01-29 | 2026-02-19 | 05-Jul-25 A | 2025-10-18 | 0 | 0 | 17709.16 | Remaining Total Cost | [15 empty] | 17709.16
|  |  | L-46 |  | 2026-01-29 | 2026-02-19 | 05-Jul-25 A | 2025-10-18 | 0 | 0 | 17709.16 | Actual Total Cost
|  |  | JDH3-02-008-L-46-TSE Network - TSE |  | 2026-02-07 | 2026-02-19 | 2025-10-05 | 2025-10-18 | 0 | 0 | 17709.16 | Planned Total Cost | [15 empty] | 17709.16
|  |  | JDH3-02-008-L-46-TSE Network - TSE |  | 2026-02-07 | 2026-02-19 | 2025-10-05 | 2025-10-18 | 0 | 0 | 17709.16 | Remaining Total Cost | [15 empty] | 17709.16
|  |  | JDH3-02-008-L-46-TSE Network - TSE |  | 2026-02-07 | 2026-02-19 | 2025-10-05 | 2025-10-18 | 0 | 0 | 17709.16 | Actual Total Cost
|  |  | JDH3-02-008-L-46-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-02-07 | 2026-02-19 | 2025-10-05 | 2025-10-18 | 0 | 0 | 16416 | Planned Total Cost | [15 empty] | 16416
|  |  | JDH3-02-008-L-46-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-02-07 | 2026-02-19 | 2025-10-05 | 2025-10-18 | 0 | 0 | 16416 | Remaining Total Cost | [15 empty] | 16416
|  |  | JDH3-02-008-L-46-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-02-07 | 2026-02-19 | 2025-10-05 | 2025-10-18 | 0 | 0 | 16416 | Actual Total Cost
|  |  | JDH3-02-008-L-46-(TSE)-Supply and install gate valves-100 mm |  | 2026-02-14 | 2026-02-17 | 2025-10-12 | 2025-10-15 | 0 | 0 | 1293.16 | Planned Total Cost | [15 empty] | 1293.16
|  |  | JDH3-02-008-L-46-(TSE)-Supply and install gate valves-100 mm |  | 2026-02-14 | 2026-02-17 | 2025-10-12 | 2025-10-15 | 0 | 0 | 1293.16 | Remaining Total Cost | [15 empty] | 1293.16
|  |  | JDH3-02-008-L-46-(TSE)-Supply and install gate valves-100 mm |  | 2026-02-14 | 2026-02-17 | 2025-10-12 | 2025-10-15 | 0 | 0 | 1293.16 | Actual Total Cost
|  |  | L-42 |  | 2026-02-21 | 2026-03-22 | 05-Jul-25 A | 2025-10-25 | 0 | 0 | 63186.69 | Planned Total Cost | [15 empty] | 63186.69
|  |  | L-42 |  | 2026-02-21 | 2026-03-22 | 05-Jul-25 A | 2025-10-25 | 0 | 0 | 63186.69 | Remaining Total Cost | [15 empty] | 63186.69
|  |  | L-42 |  | 2026-02-21 | 2026-03-22 | 05-Jul-25 A | 2025-10-25 | 0 | 0 | 63186.69 | Actual Total Cost
|  |  | JDH3-02-008-L-42-TSE Network - TSE |  | 2026-02-28 | 2026-03-22 | 2025-10-02 | 2025-10-25 | 0 | 0 | 63186.69 | Planned Total Cost | [15 empty] | 63186.69
|  |  | JDH3-02-008-L-42-TSE Network - TSE |  | 2026-02-28 | 2026-03-22 | 2025-10-02 | 2025-10-25 | 0 | 0 | 63186.69 | Remaining Total Cost | [15 empty] | 63186.69
|  |  | JDH3-02-008-L-42-TSE Network - TSE |  | 2026-02-28 | 2026-03-22 | 2025-10-02 | 2025-10-25 | 0 | 0 | 63186.69 | Actual Total Cost
|  |  | JDH3-02-008-L-42-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-02-28 | 2026-03-22 | 2025-10-02 | 2025-10-25 | 0 | 0 | 60600.37 | Planned Total Cost | [15 empty] | 60600.37
|  |  | JDH3-02-008-L-42-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-02-28 | 2026-03-22 | 2025-10-02 | 2025-10-25 | 0 | 0 | 60600.37 | Remaining Total Cost | [15 empty] | 60600.37
|  |  | JDH3-02-008-L-42-(TSE)- Supply and install HDPE Pipes - 125 mm depth from 0 to 1.5 m |  | 2026-02-28 | 2026-03-22 | 2025-10-02 | 2025-10-25 | 0 | 0 | 60600.37 | Actual Total Cost
|  |  | JDH3-02-008-L-42-(TSE)-Supply and install gate valves-100 mm |  | 2026-03-14 | 2026-03-17 | 2025-10-16 | 2025-10-20 | 0 | 0 | 2586.32 | Planned Total Cost | [15 empty] | 2586.32
|  |  | JDH3-02-008-L-42-(TSE)-Supply and install gate valves-100 mm |  | 2026-03-14 | 2026-03-17 | 2025-10-16 | 2025-10-20 | 0 | 0 | 2586.32 | Remaining Total Cost | [15 empty] | 2586.32
|  |  | JDH3-02-008-L-42-(TSE)-Supply and install gate valves-100 mm |  | 2026-03-14 | 2026-03-17 | 2025-10-16 | 2025-10-20 | 0 | 0 | 2586.32 | Actual Total Cost
|  |  | Z09 |  | 2026-03-16 | 2026-07-08 | 08-Jul-25 A | 2026-06-20 | 0 | 0 | 1632098.65 | Planned Total Cost | [15 empty] | 30385.65 | 751719.3 | 185597.45 |  |  |  |  | 545129.06 | 119267.19
|  |  | Z09 |  | 2026-03-16 | 2026-07-08 | 08-Jul-25 A | 2026-06-20 | 0 | 0 | 1632098.65 | Remaining Total Cost | [15 empty] | 30385.65 | 751719.3 | 185597.45 |  |  |  |  | 545129.06 | 119267.19
|  |  | Z09 |  | 2026-03-16 | 2026-07-08 | 08-Jul-25 A | 2026-06-20 | 0 | 0 | 1632098.65 | Actual Total Cost
|  |  | L-18 |  | 2026-03-16 | 2026-05-21 | 08-Jul-25 A | 2025-12-23 | 0 | 0 | 967702.4 | Planned Total Cost | [15 empty] | 30385.65 | 751719.3 | 185597.45
|  |  | L-18 |  | 2026-03-16 | 2026-05-21 | 08-Jul-25 A | 2025-12-23 | 0 | 0 | 967702.4 | Remaining Total Cost | [15 empty] | 30385.65 | 751719.3 | 185597.45
|  |  | L-18 |  | 2026-03-16 | 2026-05-21 | 08-Jul-25 A | 2025-12-23 | 0 | 0 | 967702.4 | Actual Total Cost
|  |  | JDH3-02-008-L-18-Sewage Network - SS |  | 2026-03-24 | 2026-05-21 | 2025-10-26 | 2025-12-23 | 0 | 0 | 967702.4 | Planned Total Cost | [15 empty] | 30385.65 | 751719.3 | 185597.45
|  |  | JDH3-02-008-L-18-Sewage Network - SS |  | 2026-03-24 | 2026-05-21 | 2025-10-26 | 2025-12-23 | 0 | 0 | 967702.4 | Remaining Total Cost | [15 empty] | 30385.65 | 751719.3 | 185597.45
|  |  | JDH3-02-008-L-18-Sewage Network - SS |  | 2026-03-24 | 2026-05-21 | 2025-10-26 | 2025-12-23 | 0 | 0 | 967702.4 | Actual Total Cost
|  |  | JDH3-02-008-L-18-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 0 to 1.5 m. |  | 2026-03-24 | 2026-04-23 | 2025-10-26 | 2025-11-25 | 0 | 0 | 151928.26 | Planned Total Cost | [15 empty] | 30385.65 | 121542.61
|  |  | JDH3-02-008-L-18-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 0 to 1.5 m. |  | 2026-03-24 | 2026-04-23 | 2025-10-26 | 2025-11-25 | 0 | 0 | 151928.26 | Remaining Total Cost | [15 empty] | 30385.65 | 121542.61
|  |  | JDH3-02-008-L-18-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 0 to 1.5 m. |  | 2026-03-24 | 2026-04-23 | 2025-10-26 | 2025-11-25 | 0 | 0 | 151928.26 | Actual Total Cost
|  |  | JDH3-02-008-L-18-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2026-03-30 | 2026-05-21 | 2025-11-01 | 2025-12-23 | 0 | 0 | 327509.03 | Planned Total Cost | [16 empty] | 262007.23 | 65501.81
|  |  | JDH3-02-008-L-18-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2026-03-30 | 2026-05-21 | 2025-11-01 | 2025-12-23 | 0 | 0 | 327509.03 | Remaining Total Cost | [16 empty] | 262007.23 | 65501.81
|  |  | JDH3-02-008-L-18-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2026-03-30 | 2026-05-21 | 2025-11-01 | 2025-12-23 | 0 | 0 | 327509.03 | Actual Total Cost
|  |  | JDH3-02-008-L-18-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2026-04-08 | 2026-05-02 | 2025-11-10 | 2025-12-03 | 0 | 0 | 160412.93 | Planned Total Cost | [16 empty] | 150788.15 | 9624.78
|  |  | JDH3-02-008-L-18-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2026-04-08 | 2026-05-02 | 2025-11-10 | 2025-12-03 | 0 | 0 | 160412.93 | Remaining Total Cost | [16 empty] | 150788.15 | 9624.78
|  |  | JDH3-02-008-L-18-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2026-04-08 | 2026-05-02 | 2025-11-10 | 2025-12-03 | 0 | 0 | 160412.93 | Actual Total Cost
|  |  | JDH3-02-008-L-18-(SS)-MH WORKS from 0.00 to 1.50 @ 1200 mm |  | 2026-04-13 | 2026-04-23 | 2025-11-15 | 2025-11-25 | 0 | 0 | 18250.22 | Planned Total Cost | [16 empty] | 18250.22
|  |  | JDH3-02-008-L-18-(SS)-MH WORKS from 0.00 to 1.50 @ 1200 mm |  | 2026-04-13 | 2026-04-23 | 2025-11-15 | 2025-11-25 | 0 | 0 | 18250.22 | Remaining Total Cost | [16 empty] | 18250.22
|  |  | JDH3-02-008-L-18-(SS)-MH WORKS from 0.00 to 1.50 @ 1200 mm |  | 2026-04-13 | 2026-04-23 | 2025-11-15 | 2025-11-25 | 0 | 0 | 18250.22 | Actual Total Cost
|  |  | JDH3-02-008-L-18-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2026-04-15 | 2026-05-13 | 2025-11-17 | 2025-12-15 | 0 | 0 | 208573.95 | Planned Total Cost | [16 empty] | 125144.37 | 83429.58
|  |  | JDH3-02-008-L-18-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2026-04-15 | 2026-05-13 | 2025-11-17 | 2025-12-15 | 0 | 0 | 208573.95 | Remaining Total Cost | [16 empty] | 125144.37 | 83429.58
|  |  | JDH3-02-008-L-18-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2026-04-15 | 2026-05-13 | 2025-11-17 | 2025-12-15 | 0 | 0 | 208573.95 | Actual Total Cost
|  |  | JDH3-02-008-L-18-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2026-04-19 | 2026-05-04 | 2025-11-20 | 2025-12-06 | 0 | 0 | 86688.55 | Planned Total Cost | [16 empty] | 66100.02 | 20588.53
|  |  | JDH3-02-008-L-18-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2026-04-19 | 2026-05-04 | 2025-11-20 | 2025-12-06 | 0 | 0 | 86688.55 | Remaining Total Cost | [16 empty] | 66100.02 | 20588.53
|  |  | JDH3-02-008-L-18-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2026-04-19 | 2026-05-04 | 2025-11-20 | 2025-12-06 | 0 | 0 | 86688.55 | Actual Total Cost
|  |  | JDH3-02-008-L-18-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm with back drop |  | 2026-04-21 | 2026-05-06 | 2025-11-23 | 2025-12-08 | 0 | 0 | 14339.45 | Planned Total Cost | [16 empty] | 7886.7 | 6452.75
|  |  | JDH3-02-008-L-18-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm with back drop |  | 2026-04-21 | 2026-05-06 | 2025-11-23 | 2025-12-08 | 0 | 0 | 14339.45 | Remaining Total Cost | [16 empty] | 7886.7 | 6452.75
|  |  | JDH3-02-008-L-18-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm with back drop |  | 2026-04-21 | 2026-05-06 | 2025-11-23 | 2025-12-08 | 0 | 0 | 14339.45 | Actual Total Cost
|  |  | L-19 |  | 2026-05-23 | 2026-07-08 | 2026-05-03 | 2026-06-20 | 0 | 0 | 664396.25 | Planned Total Cost | [22 empty] | 545129.06 | 119267.19
|  |  | L-19 |  | 2026-05-23 | 2026-07-08 | 2026-05-03 | 2026-06-20 | 0 | 0 | 664396.25 | Remaining Total Cost | [22 empty] | 545129.06 | 119267.19
|  |  | L-19 |  | 2026-05-23 | 2026-07-08 | 2026-05-03 | 2026-06-20 | 0 | 0 | 664396.25 | Actual Total Cost
|  |  | JDH3-02-008-L-19-Sewage Network - SS |  | 2026-05-23 | 2026-07-08 | 2026-05-03 | 2026-06-20 | 0 | 0 | 664396.25 | Planned Total Cost | [22 empty] | 545129.06 | 119267.19
|  |  | JDH3-02-008-L-19-Sewage Network - SS |  | 2026-05-23 | 2026-07-08 | 2026-05-03 | 2026-06-20 | 0 | 0 | 664396.25 | Remaining Total Cost | [22 empty] | 545129.06 | 119267.19
|  |  | JDH3-02-008-L-19-Sewage Network - SS |  | 2026-05-23 | 2026-07-08 | 2026-05-03 | 2026-06-20 | 0 | 0 | 664396.25 | Actual Total Cost
|  |  | JDH3-02-008-L-19-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 0 to 1.5 m. |  | 2026-05-23 | 2026-06-02 | 2026-05-03 | 2026-05-14 | 0 | 0 | 24002.31 | Planned Total Cost | [22 empty] | 24002.31
|  |  | JDH3-02-008-L-19-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 0 to 1.5 m. |  | 2026-05-23 | 2026-06-02 | 2026-05-03 | 2026-05-14 | 0 | 0 | 24002.31 | Remaining Total Cost | [22 empty] | 24002.31
|  |  | JDH3-02-008-L-19-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 0 to 1.5 m. |  | 2026-05-23 | 2026-06-02 | 2026-05-03 | 2026-05-14 | 0 | 0 | 24002.31 | Actual Total Cost
|  |  | JDH3-02-008-L-19-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2026-05-25 | 2026-07-08 | 2026-05-05 | 2026-06-20 | 0 | 0 | 272756.44 | Planned Total Cost | [22 empty] | 220543.06 | 52213.38
|  |  | JDH3-02-008-L-19-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2026-05-25 | 2026-07-08 | 2026-05-05 | 2026-06-20 | 0 | 0 | 272756.44 | Remaining Total Cost | [22 empty] | 220543.06 | 52213.38
|  |  | JDH3-02-008-L-19-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2026-05-25 | 2026-07-08 | 2026-05-05 | 2026-06-20 | 0 | 0 | 272756.44 | Actual Total Cost
|  |  | JDH3-02-008-L-19-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2026-06-02 | 2026-06-22 | 2026-05-13 | 2026-06-03 | 0 | 0 | 147113.05 | Planned Total Cost | [22 empty] | 140051.62 | 7061.43
|  |  | JDH3-02-008-L-19-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2026-06-02 | 2026-06-22 | 2026-05-13 | 2026-06-03 | 0 | 0 | 147113.05 | Remaining Total Cost | [22 empty] | 140051.62 | 7061.43
|  |  | JDH3-02-008-L-19-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2026-06-02 | 2026-06-22 | 2026-05-13 | 2026-06-03 | 0 | 0 | 147113.05 | Actual Total Cost
|  |  | JDH3-02-008-L-19-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 3.51 to 4.5 m. |  | 2026-06-06 | 2026-06-16 | 2026-05-17 | 2026-05-28 | 0 | 0 | 40629.42 | Planned Total Cost | [22 empty] | 40629.42
|  |  | JDH3-02-008-L-19-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 3.51 to 4.5 m. |  | 2026-06-06 | 2026-06-16 | 2026-05-17 | 2026-05-28 | 0 | 0 | 40629.42 | Remaining Total Cost | [22 empty] | 40629.42
|  |  | JDH3-02-008-L-19-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 3.51 to 4.5 m. |  | 2026-06-06 | 2026-06-16 | 2026-05-17 | 2026-05-28 | 0 | 0 | 40629.42 | Actual Total Cost
|  |  | JDH3-02-008-L-19-(SS)-MH WORKS from 0.00 to 1.50 @ 1200 mm |  | 2026-06-08 | 2026-06-18 | 2026-05-19 | 2026-05-31 | 0 | 0 | 9125.11 | Planned Total Cost | [22 empty] | 9125.11
|  |  | JDH3-02-008-L-19-(SS)-MH WORKS from 0.00 to 1.50 @ 1200 mm |  | 2026-06-08 | 2026-06-18 | 2026-05-19 | 2026-05-31 | 0 | 0 | 9125.11 | Remaining Total Cost | [22 empty] | 9125.11
|  |  | JDH3-02-008-L-19-(SS)-MH WORKS from 0.00 to 1.50 @ 1200 mm |  | 2026-06-08 | 2026-06-18 | 2026-05-19 | 2026-05-31 | 0 | 0 | 9125.11 | Actual Total Cost
|  |  | JDH3-02-008-L-19-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2026-06-10 | 2026-06-30 | 2026-05-21 | 2026-06-11 | 0 | 0 | 146001.76 | Planned Total Cost | [22 empty] | 89353.08 | 56648.68
|  |  | JDH3-02-008-L-19-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2026-06-10 | 2026-06-30 | 2026-05-21 | 2026-06-11 | 0 | 0 | 146001.76 | Remaining Total Cost | [22 empty] | 89353.08 | 56648.68
|  |  | JDH3-02-008-L-19-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2026-06-10 | 2026-06-30 | 2026-05-21 | 2026-06-11 | 0 | 0 | 146001.76 | Actual Total Cost
|  |  | JDH3-02-008-L-19-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2026-06-13 | 2026-06-23 | 2026-05-24 | 2026-06-04 | 0 | 0 | 24768.16 | Planned Total Cost | [22 empty] | 21424.46 | 3343.7
|  |  | JDH3-02-008-L-19-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2026-06-13 | 2026-06-23 | 2026-05-24 | 2026-06-04 | 0 | 0 | 24768.16 | Remaining Total Cost | [22 empty] | 21424.46 | 3343.7
|  |  | JDH3-02-008-L-19-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2026-06-13 | 2026-06-23 | 2026-05-24 | 2026-06-04 | 0 | 0 | 24768.16 | Actual Total Cost
|  |  | Z10 |  | 2026-03-21 | 2026-06-28 | 2026-01-03 | 2026-04-12 | 0 | 0 | 3104558.11 | Planned Total Cost | [18 empty] | 862708.63 | 1052098.53 | 1126830.16 | 62920.79
|  |  | Z10 |  | 2026-03-21 | 2026-06-28 | 2026-01-03 | 2026-04-12 | 0 | 0 | 3104558.11 | Remaining Total Cost | [18 empty] | 862708.63 | 1052098.53 | 1126830.16 | 62920.79
|  |  | Z10 |  | 2026-03-21 | 2026-06-28 | 2026-01-03 | 2026-04-12 | 0 | 0 | 3104558.11 | Actual Total Cost
|  |  | L-20 |  | 2026-03-21 | 2026-04-30 | 2026-01-03 | 2026-02-12 | 0 | 0 | 400276.82 | Planned Total Cost | [18 empty] | 367922.58 | 32354.24
|  |  | L-20 |  | 2026-03-21 | 2026-04-30 | 2026-01-03 | 2026-02-12 | 0 | 0 | 400276.82 | Remaining Total Cost | [18 empty] | 367922.58 | 32354.24
|  |  | L-20 |  | 2026-03-21 | 2026-04-30 | 2026-01-03 | 2026-02-12 | 0 | 0 | 400276.82 | Actual Total Cost
|  |  | JDH3-02-008-L-20-Sewage Network - SS |  | 2026-03-21 | 2026-04-30 | 2026-01-03 | 2026-02-12 | 0 | 0 | 400276.82 | Planned Total Cost | [18 empty] | 367922.58 | 32354.24
|  |  | JDH3-02-008-L-20-Sewage Network - SS |  | 2026-03-21 | 2026-04-30 | 2026-01-03 | 2026-02-12 | 0 | 0 | 400276.82 | Remaining Total Cost | [18 empty] | 367922.58 | 32354.24
|  |  | JDH3-02-008-L-20-Sewage Network - SS |  | 2026-03-21 | 2026-04-30 | 2026-01-03 | 2026-02-12 | 0 | 0 | 400276.82 | Actual Total Cost
|  |  | JDH3-02-008-L-20-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 0 to 1.5 m. |  | 2026-03-21 | 2026-03-31 | 2026-01-03 | 2026-01-13 | 0 | 0 | 14225.4 | Planned Total Cost | [18 empty] | 14225.4
|  |  | JDH3-02-008-L-20-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 0 to 1.5 m. |  | 2026-03-21 | 2026-03-31 | 2026-01-03 | 2026-01-13 | 0 | 0 | 14225.4 | Remaining Total Cost | [18 empty] | 14225.4
|  |  | JDH3-02-008-L-20-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 0 to 1.5 m. |  | 2026-03-21 | 2026-03-31 | 2026-01-03 | 2026-01-13 | 0 | 0 | 14225.4 | Actual Total Cost
|  |  | JDH3-02-008-L-20-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2026-03-23 | 2026-04-30 | 2026-01-05 | 2026-02-12 | 0 | 0 | 242656.83 | Planned Total Cost | [18 empty] | 210302.58 | 32354.24
|  |  | JDH3-02-008-L-20-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2026-03-23 | 2026-04-30 | 2026-01-05 | 2026-02-12 | 0 | 0 | 242656.83 | Remaining Total Cost | [18 empty] | 210302.58 | 32354.24
|  |  | JDH3-02-008-L-20-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2026-03-23 | 2026-04-30 | 2026-01-05 | 2026-02-12 | 0 | 0 | 242656.83 | Actual Total Cost
|  |  | JDH3-02-008-L-20-(SS)-MH WORKS from 0.00 to 1.50 @ 1200 mm |  | 2026-03-30 | 2026-04-09 | 2026-01-12 | 2026-01-22 | 0 | 0 | 18250.22 | Planned Total Cost | [18 empty] | 18250.22
|  |  | JDH3-02-008-L-20-(SS)-MH WORKS from 0.00 to 1.50 @ 1200 mm |  | 2026-03-30 | 2026-04-09 | 2026-01-12 | 2026-01-22 | 0 | 0 | 18250.22 | Remaining Total Cost | [18 empty] | 18250.22
|  |  | JDH3-02-008-L-20-(SS)-MH WORKS from 0.00 to 1.50 @ 1200 mm |  | 2026-03-30 | 2026-04-09 | 2026-01-12 | 2026-01-22 | 0 | 0 | 18250.22 | Actual Total Cost
|  |  | JDH3-02-008-L-20-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2026-04-01 | 2026-04-18 | 2026-01-14 | 2026-01-31 | 0 | 0 | 125144.37 | Planned Total Cost | [18 empty] | 125144.37
|  |  | JDH3-02-008-L-20-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2026-04-01 | 2026-04-18 | 2026-01-14 | 2026-01-31 | 0 | 0 | 125144.37 | Remaining Total Cost | [18 empty] | 125144.37
|  |  | JDH3-02-008-L-20-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2026-04-01 | 2026-04-18 | 2026-01-14 | 2026-01-31 | 0 | 0 | 125144.37 | Actual Total Cost
|  |  | L-23 |  | 2026-03-21 | 2026-06-02 | 2026-01-03 | 2026-03-17 | 0 | 0 | 769483.52 | Planned Total Cost | [18 empty] | 259481.51 | 461183.35 | 48818.66
|  |  | L-23 |  | 2026-03-21 | 2026-06-02 | 2026-01-03 | 2026-03-17 | 0 | 0 | 769483.52 | Remaining Total Cost | [18 empty] | 259481.51 | 461183.35 | 48818.66
|  |  | L-23 |  | 2026-03-21 | 2026-06-02 | 2026-01-03 | 2026-03-17 | 0 | 0 | 769483.52 | Actual Total Cost
|  |  | JDH3-02-008-L-23-Sewage Network - SS |  | 2026-03-21 | 2026-06-02 | 2026-01-03 | 2026-03-17 | 0 | 0 | 769483.52 | Planned Total Cost | [18 empty] | 259481.51 | 461183.35 | 48818.66
|  |  | JDH3-02-008-L-23-Sewage Network - SS |  | 2026-03-21 | 2026-06-02 | 2026-01-03 | 2026-03-17 | 0 | 0 | 769483.52 | Remaining Total Cost | [18 empty] | 259481.51 | 461183.35 | 48818.66
|  |  | JDH3-02-008-L-23-Sewage Network - SS |  | 2026-03-21 | 2026-06-02 | 2026-01-03 | 2026-03-17 | 0 | 0 | 769483.52 | Actual Total Cost
|  |  | JDH3-02-008-L-23-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2026-03-21 | 2026-04-07 | 2026-01-03 | 2026-01-20 | 0 | 0 | 100032.43 | Planned Total Cost | [18 empty] | 100032.43
|  |  | JDH3-02-008-L-23-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2026-03-21 | 2026-04-07 | 2026-01-03 | 2026-01-20 | 0 | 0 | 100032.43 | Remaining Total Cost | [18 empty] | 100032.43
|  |  | JDH3-02-008-L-23-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2026-03-21 | 2026-04-07 | 2026-01-03 | 2026-01-20 | 0 | 0 | 100032.43 | Actual Total Cost
|  |  | JDH3-02-008-L-23-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2026-04-04 | 2026-06-02 | 2026-01-17 | 2026-03-17 | 0 | 0 | 439367.94 | Planned Total Cost | [18 empty] | 97637.32 | 292911.96 | 48818.66
|  |  | JDH3-02-008-L-23-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2026-04-04 | 2026-06-02 | 2026-01-17 | 2026-03-17 | 0 | 0 | 439367.94 | Remaining Total Cost | [18 empty] | 97637.32 | 292911.96 | 48818.66
|  |  | JDH3-02-008-L-23-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2026-04-04 | 2026-06-02 | 2026-01-17 | 2026-03-17 | 0 | 0 | 439367.94 | Actual Total Cost
|  |  | JDH3-02-008-L-23-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2026-04-14 | 2026-04-27 | 2026-01-27 | 2026-02-09 | 0 | 0 | 93858.28 | Planned Total Cost | [18 empty] | 39107.62 | 54750.66
|  |  | JDH3-02-008-L-23-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2026-04-14 | 2026-04-27 | 2026-01-27 | 2026-02-09 | 0 | 0 | 93858.28 | Remaining Total Cost | [18 empty] | 39107.62 | 54750.66
|  |  | JDH3-02-008-L-23-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2026-04-14 | 2026-04-27 | 2026-01-27 | 2026-02-09 | 0 | 0 | 93858.28 | Actual Total Cost
|  |  | JDH3-02-008-L-23-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2026-04-16 | 2026-05-10 | 2026-01-29 | 2026-02-22 | 0 | 0 | 136224.87 | Planned Total Cost | [18 empty] | 22704.14 | 113520.72
|  |  | JDH3-02-008-L-23-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2026-04-16 | 2026-05-10 | 2026-01-29 | 2026-02-22 | 0 | 0 | 136224.87 | Remaining Total Cost | [18 empty] | 22704.14 | 113520.72
|  |  | JDH3-02-008-L-23-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2026-04-16 | 2026-05-10 | 2026-01-29 | 2026-02-22 | 0 | 0 | 136224.87 | Actual Total Cost
|  |  | L-24 |  | 2026-05-02 | 2026-05-20 | 2026-02-14 | 2026-03-04 | 0 | 0 | 159712.82 | Planned Total Cost | [19 empty] | 144654.05 | 15058.77
|  |  | L-24 |  | 2026-05-02 | 2026-05-20 | 2026-02-14 | 2026-03-04 | 0 | 0 | 159712.82 | Remaining Total Cost | [19 empty] | 144654.05 | 15058.77
|  |  | L-24 |  | 2026-05-02 | 2026-05-20 | 2026-02-14 | 2026-03-04 | 0 | 0 | 159712.82 | Actual Total Cost
|  |  | JDH3-02-008-L-24-Sewage Network - SS |  | 2026-05-02 | 2026-05-20 | 2026-02-14 | 2026-03-04 | 0 | 0 | 159712.82 | Planned Total Cost | [19 empty] | 144654.05 | 15058.77
|  |  | JDH3-02-008-L-24-Sewage Network - SS |  | 2026-05-02 | 2026-05-20 | 2026-02-14 | 2026-03-04 | 0 | 0 | 159712.82 | Remaining Total Cost | [19 empty] | 144654.05 | 15058.77
|  |  | JDH3-02-008-L-24-Sewage Network - SS |  | 2026-05-02 | 2026-05-20 | 2026-02-14 | 2026-03-04 | 0 | 0 | 159712.82 | Actual Total Cost
|  |  | JDH3-02-008-L-24-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2026-05-02 | 2026-05-20 | 2026-02-14 | 2026-03-04 | 0 | 0 | 108872.92 | Planned Total Cost | [19 empty] | 97985.62 | 10887.29
|  |  | JDH3-02-008-L-24-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2026-05-02 | 2026-05-20 | 2026-02-14 | 2026-03-04 | 0 | 0 | 108872.92 | Remaining Total Cost | [19 empty] | 97985.62 | 10887.29
|  |  | JDH3-02-008-L-24-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2026-05-02 | 2026-05-20 | 2026-02-14 | 2026-03-04 | 0 | 0 | 108872.92 | Actual Total Cost
|  |  | JDH3-02-008-L-24-(SS)-MH WORKS from 0.00 to 1.50 @ 1200 mm |  | 2026-05-05 | 2026-05-16 | 2026-02-17 | 2026-02-28 | 0 | 0 | 9125.11 | Planned Total Cost | [19 empty] | 9125.11
|  |  | JDH3-02-008-L-24-(SS)-MH WORKS from 0.00 to 1.50 @ 1200 mm |  | 2026-05-05 | 2026-05-16 | 2026-02-17 | 2026-02-28 | 0 | 0 | 9125.11 | Remaining Total Cost | [19 empty] | 9125.11
|  |  | JDH3-02-008-L-24-(SS)-MH WORKS from 0.00 to 1.50 @ 1200 mm |  | 2026-05-05 | 2026-05-16 | 2026-02-17 | 2026-02-28 | 0 | 0 | 9125.11 | Actual Total Cost
|  |  | JDH3-02-008-L-24-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2026-05-07 | 2026-05-18 | 2026-02-19 | 2026-03-02 | 0 | 0 | 41714.79 | Planned Total Cost | [19 empty] | 37543.31 | 4171.48
|  |  | JDH3-02-008-L-24-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2026-05-07 | 2026-05-18 | 2026-02-19 | 2026-03-02 | 0 | 0 | 41714.79 | Remaining Total Cost | [19 empty] | 37543.31 | 4171.48
|  |  | JDH3-02-008-L-24-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2026-05-07 | 2026-05-18 | 2026-02-19 | 2026-03-02 | 0 | 0 | 41714.79 | Actual Total Cost
|  |  | L-25 |  | 2026-05-21 | 2026-06-28 | 2026-03-05 | 2026-04-12 | 0 | 0 | 596006.33 | Planned Total Cost | [20 empty] | 533085.55 | 62920.79
|  |  | L-25 |  | 2026-05-21 | 2026-06-28 | 2026-03-05 | 2026-04-12 | 0 | 0 | 596006.33 | Remaining Total Cost | [20 empty] | 533085.55 | 62920.79
|  |  | L-25 |  | 2026-05-21 | 2026-06-28 | 2026-03-05 | 2026-04-12 | 0 | 0 | 596006.33 | Actual Total Cost
|  |  | JDH3-02-008-L-25-Sewage Network - SS |  | 2026-05-21 | 2026-06-28 | 2026-03-05 | 2026-04-12 | 0 | 0 | 596006.33 | Planned Total Cost | [20 empty] | 533085.55 | 62920.79
|  |  | JDH3-02-008-L-25-Sewage Network - SS |  | 2026-05-21 | 2026-06-28 | 2026-03-05 | 2026-04-12 | 0 | 0 | 596006.33 | Remaining Total Cost | [20 empty] | 533085.55 | 62920.79
|  |  | JDH3-02-008-L-25-Sewage Network - SS |  | 2026-05-21 | 2026-06-28 | 2026-03-05 | 2026-04-12 | 0 | 0 | 596006.33 | Actual Total Cost
|  |  | JDH3-02-008-L-25-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2026-05-21 | 2026-06-23 | 2026-03-05 | 2026-04-07 | 0 | 0 | 200067.7 | Planned Total Cost | [20 empty] | 185062.62 | 15005.08
|  |  | JDH3-02-008-L-25-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2026-05-21 | 2026-06-23 | 2026-03-05 | 2026-04-07 | 0 | 0 | 200067.7 | Remaining Total Cost | [20 empty] | 185062.62 | 15005.08
|  |  | JDH3-02-008-L-25-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2026-05-21 | 2026-06-23 | 2026-03-05 | 2026-04-07 | 0 | 0 | 200067.7 | Actual Total Cost
|  |  | JDH3-02-008-L-25-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2026-05-27 | 2026-06-28 | 2026-03-11 | 2026-04-12 | 0 | 0 | 221257.95 | Planned Total Cost | [20 empty] | 185856.68 | 35401.27
|  |  | JDH3-02-008-L-25-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2026-05-27 | 2026-06-28 | 2026-03-11 | 2026-04-12 | 0 | 0 | 221257.95 | Remaining Total Cost | [20 empty] | 185856.68 | 35401.27
|  |  | JDH3-02-008-L-25-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2026-05-27 | 2026-06-28 | 2026-03-11 | 2026-04-12 | 0 | 0 | 221257.95 | Actual Total Cost
|  |  | JDH3-02-008-L-25-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2026-06-02 | 2026-06-18 | 2026-03-17 | 2026-04-02 | 0 | 0 | 125144.37 | Planned Total Cost | [20 empty] | 112629.93 | 12514.44
|  |  | JDH3-02-008-L-25-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2026-06-02 | 2026-06-18 | 2026-03-17 | 2026-04-02 | 0 | 0 | 125144.37 | Remaining Total Cost | [20 empty] | 112629.93 | 12514.44
|  |  | JDH3-02-008-L-25-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2026-06-02 | 2026-06-18 | 2026-03-17 | 2026-04-02 | 0 | 0 | 125144.37 | Actual Total Cost
|  |  | JDH3-02-008-L-25-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2026-06-04 | 2026-06-15 | 2026-03-19 | 2026-03-30 | 0 | 0 | 49536.32 | Planned Total Cost | [20 empty] | 49536.32
|  |  | JDH3-02-008-L-25-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2026-06-04 | 2026-06-15 | 2026-03-19 | 2026-03-30 | 0 | 0 | 49536.32 | Remaining Total Cost | [20 empty] | 49536.32
|  |  | JDH3-02-008-L-25-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2026-06-04 | 2026-06-15 | 2026-03-19 | 2026-03-30 | 0 | 0 | 49536.32 | Actual Total Cost
|  |  | L-26 |  | 2026-03-21 | 2026-06-08 | 2026-01-03 | 2026-03-23 | 0 | 0 | 1179078.62 | Planned Total Cost | [18 empty] | 235304.54 | 413906.9 | 529867.18
|  |  | L-26 |  | 2026-03-21 | 2026-06-08 | 2026-01-03 | 2026-03-23 | 0 | 0 | 1179078.62 | Remaining Total Cost | [18 empty] | 235304.54 | 413906.9 | 529867.18
|  |  | L-26 |  | 2026-03-21 | 2026-06-08 | 2026-01-03 | 2026-03-23 | 0 | 0 | 1179078.62 | Actual Total Cost
|  |  | JDH3-02-008-L-26-Sewage Network - SS |  | 2026-03-21 | 2026-06-08 | 2026-01-03 | 2026-03-23 | 0 | 0 | 1179078.62 | Planned Total Cost | [18 empty] | 235304.54 | 413906.9 | 529867.18
|  |  | JDH3-02-008-L-26-Sewage Network - SS |  | 2026-03-21 | 2026-06-08 | 2026-01-03 | 2026-03-23 | 0 | 0 | 1179078.62 | Remaining Total Cost | [18 empty] | 235304.54 | 413906.9 | 529867.18
|  |  | JDH3-02-008-L-26-Sewage Network - SS |  | 2026-03-21 | 2026-06-08 | 2026-01-03 | 2026-03-23 | 0 | 0 | 1179078.62 | Actual Total Cost
|  |  | JDH3-02-008-L-26-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2026-03-21 | 2026-04-01 | 2026-01-03 | 2026-01-14 | 0 | 0 | 59391.15 | Planned Total Cost | [18 empty] | 59391.15
|  |  | JDH3-02-008-L-26-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2026-03-21 | 2026-04-01 | 2026-01-03 | 2026-01-14 | 0 | 0 | 59391.15 | Remaining Total Cost | [18 empty] | 59391.15
|  |  | JDH3-02-008-L-26-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 1.51 to 2.5 m. |  | 2026-03-21 | 2026-04-01 | 2026-01-03 | 2026-01-14 | 0 | 0 | 59391.15 | Actual Total Cost
|  |  | JDH3-02-008-L-26-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2026-03-23 | 2026-04-18 | 2026-01-05 | 2026-01-31 | 0 | 0 | 175913.38 | Planned Total Cost | [18 empty] | 175913.38
|  |  | JDH3-02-008-L-26-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2026-03-23 | 2026-04-18 | 2026-01-05 | 2026-01-31 | 0 | 0 | 175913.38 | Remaining Total Cost | [18 empty] | 175913.38
|  |  | JDH3-02-008-L-26-(SS)-Glass Reinforced Plastic (GRP)-200mm diameter depth from 2.51 to 3.5 m. |  | 2026-03-23 | 2026-04-18 | 2026-01-05 | 2026-01-31 | 0 | 0 | 175913.38 | Actual Total Cost
|  |  | JDH3-02-008-L-26-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 2.51 to 3.5 m. |  | 2026-04-19 | 2026-04-29 | 2026-02-01 | 2026-02-11 | 0 | 0 | 35206.66 | Planned Total Cost | [19 empty] | 35206.66
|  |  | JDH3-02-008-L-26-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 2.51 to 3.5 m. |  | 2026-04-19 | 2026-04-29 | 2026-02-01 | 2026-02-11 | 0 | 0 | 35206.66 | Remaining Total Cost | [19 empty] | 35206.66
|  |  | JDH3-02-008-L-26-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 2.51 to 3.5 m. |  | 2026-04-19 | 2026-04-29 | 2026-02-01 | 2026-02-11 | 0 | 0 | 35206.66 | Actual Total Cost
|  |  | JDH3-02-008-L-26-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 3.51 to 4.5 m. |  | 2026-04-30 | 2026-06-08 | 2026-02-12 | 2026-03-23 | 0 | 0 | 681091.44 | Planned Total Cost | [19 empty] | 277301.52 | 403789.93
|  |  | JDH3-02-008-L-26-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 3.51 to 4.5 m. |  | 2026-04-30 | 2026-06-08 | 2026-02-12 | 2026-03-23 | 0 | 0 | 681091.44 | Remaining Total Cost | [19 empty] | 277301.52 | 403789.93
|  |  | JDH3-02-008-L-26-(SS)-Glass Reinforced Plastic (GRP)-250mm diameter depth from 3.51 to 4.5 m. |  | 2026-04-30 | 2026-06-08 | 2026-02-12 | 2026-03-23 | 0 | 0 | 681091.44 | Actual Total Cost
|  |  | JDH3-02-008-L-26-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2026-05-07 | 2026-05-18 | 2026-02-19 | 2026-03-02 | 0 | 0 | 41714.79 | Planned Total Cost | [19 empty] | 37543.31 | 4171.48
|  |  | JDH3-02-008-L-26-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2026-05-07 | 2026-05-18 | 2026-02-19 | 2026-03-02 | 0 | 0 | 41714.79 | Remaining Total Cost | [19 empty] | 37543.31 | 4171.48
|  |  | JDH3-02-008-L-26-(SS)-MH WORKS from 1.51 to 2.50 @ 1200 mm |  | 2026-05-07 | 2026-05-18 | 2026-02-19 | 2026-03-02 | 0 | 0 | 41714.79 | Actual Total Cost
|  |  | JDH3-02-008-L-26-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2026-05-10 | 2026-06-08 | 2026-02-22 | 2026-03-23 | 0 | 0 | 185761.19 | Planned Total Cost | [19 empty] | 63855.41 | 121905.78
|  |  | JDH3-02-008-L-26-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2026-05-10 | 2026-06-08 | 2026-02-22 | 2026-03-23 | 0 | 0 | 185761.19 | Remaining Total Cost | [19 empty] | 63855.41 | 121905.78
|  |  | JDH3-02-008-L-26-(SS)-MH WORKS from 2.51 to 3.50 @ 1200 mm |  | 2026-05-10 | 2026-06-08 | 2026-02-22 | 2026-03-23 | 0 | 0 | 185761.19 | Actual Total Cost
|  |  | Z11 |  | 2026-02-15 | 2026-03-11 | 02-Nov-24 A | 2025-12-10 | 2315-02-06 09:36 | 2315-02-06 09:36 | 330198.49 | Planned Total Cost | [15 empty] | 173672.31 |  | 4912.78 |  | 70277.84 | 81335.56
|  |  | Z11 |  | 2026-02-15 | 2026-03-11 | 02-Nov-24 A | 2025-12-10 | 2315-02-06 09:36 | 2315-02-06 09:36 | 330198.49 | Remaining Total Cost | [15 empty] | 173672.31 |  | 4912.78
|  |  | Z11 |  | 2026-02-15 | 2026-03-11 | 02-Nov-24 A | 2025-12-10 | 2315-02-06 09:36 | 2315-02-06 09:36 | 330198.49 | Actual Total Cost | [5 empty] | 37120.81 | 114492.59
|  |  | RCB |  | 2026-02-15 | 2026-03-02 | 2025-10-02 | 2025-12-10 | 0 | 0 | 178585.09 | Planned Total Cost | [15 empty] | 173672.31 |  | 4912.78
|  |  | RCB |  | 2026-02-15 | 2026-03-02 | 2025-10-02 | 2025-12-10 | 0 | 0 | 178585.09 | Remaining Total Cost | [15 empty] | 173672.31 |  | 4912.78
|  |  | RCB |  | 2026-02-15 | 2026-03-02 | 2025-10-02 | 2025-12-10 | 0 | 0 | 178585.09 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z11-Storm Network - ST |  | 2026-02-15 | 2026-03-02 | 2025-10-02 | 2025-12-10 | 0 | 0 | 178585.09 | Planned Total Cost | [15 empty] | 173672.31 |  | 4912.78
|  |  | JDH3-02-008-RCB-Z11-Storm Network - ST |  | 2026-02-15 | 2026-03-02 | 2025-10-02 | 2025-12-10 | 0 | 0 | 178585.09 | Remaining Total Cost | [15 empty] | 173672.31 |  | 4912.78
|  |  | JDH3-02-008-RCB-Z11-Storm Network - ST |  | 2026-02-15 | 2026-03-02 | 2025-10-02 | 2025-12-10 | 0 | 0 | 178585.09 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z11-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-02-15 | 2026-02-25 | 2025-10-02 | 2025-10-13 | 0 | 0 | 65290.64 | Planned Total Cost | [15 empty] | 65290.64
|  |  | JDH3-02-008-RCB-Z11-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-02-15 | 2026-02-25 | 2025-10-02 | 2025-10-13 | 0 | 0 | 65290.64 | Remaining Total Cost | [15 empty] | 65290.64
|  |  | JDH3-02-008-RCB-Z11-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-02-15 | 2026-02-25 | 2025-10-02 | 2025-10-13 | 0 | 0 | 65290.64 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z11-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-02-17 | 2026-02-28 | 2025-10-05 | 2025-10-15 | 0 | 0 | 32956.82 | Planned Total Cost | [15 empty] | 32956.82
|  |  | JDH3-02-008-RCB-Z11-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-02-17 | 2026-02-28 | 2025-10-05 | 2025-10-15 | 0 | 0 | 32956.82 | Remaining Total Cost | [15 empty] | 32956.82
|  |  | JDH3-02-008-RCB-Z11-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-02-17 | 2026-02-28 | 2025-10-05 | 2025-10-15 | 0 | 0 | 32956.82 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z11-(ST)- Single Catchbasine Works |  | 2026-02-19 | 2026-02-28 | 2025-10-07 | 2025-12-10 | 0 | 0 | 32751.9 | Planned Total Cost | [15 empty] | 27839.11 |  | 4912.78
|  |  | JDH3-02-008-RCB-Z11-(ST)- Single Catchbasine Works |  | 2026-02-19 | 2026-02-28 | 2025-10-07 | 2025-12-10 | 0 | 0 | 32751.9 | Remaining Total Cost | [15 empty] | 27839.11 |  | 4912.78
|  |  | JDH3-02-008-RCB-Z11-(ST)- Single Catchbasine Works |  | 2026-02-19 | 2026-02-28 | 2025-10-07 | 2025-12-10 | 0 | 0 | 32751.9 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z11-(ST)- Double Catchbasine Works |  | 2026-02-22 | 2026-03-02 | 2025-10-09 | 2025-10-18 | 0 | 0 | 47585.74 | Planned Total Cost | [15 empty] | 47585.74
|  |  | JDH3-02-008-RCB-Z11-(ST)- Double Catchbasine Works |  | 2026-02-22 | 2026-03-02 | 2025-10-09 | 2025-10-18 | 0 | 0 | 47585.74 | Remaining Total Cost | [15 empty] | 47585.74
|  |  | JDH3-02-008-RCB-Z11-(ST)- Double Catchbasine Works |  | 2026-02-22 | 2026-03-02 | 2025-10-09 | 2025-10-18 | 0 | 0 | 47585.74 | Actual Total Cost
|  |  | L-36 |  | 2026-02-15 | 2026-03-11 | 05-Nov-24 A | 27-Jan-25 A | 2167-07-08 11:31 | 2167-07-08 11:31 | 97710.48 | Planned Total Cost | [19 empty] | 34167.85 | 63542.63
|  |  | L-36 |  | 2026-02-15 | 2026-03-11 | 05-Nov-24 A | 27-Jan-25 A | 2167-07-08 11:31 | 2167-07-08 11:31 | 97710.48 | Remaining Total Cost
|  |  | L-36 |  | 2026-02-15 | 2026-03-11 | 05-Nov-24 A | 27-Jan-25 A | 2167-07-08 11:31 | 2167-07-08 11:31 | 97710.48 | Actual Total Cost | [5 empty] | 23917.49 | 73792.99
|  |  | JDH3-02-008-L-36-Road Works - RD |  | 2026-02-23 | 2026-03-11 | 24-Dec-24 A | 27-Jan-25 A | 2167-07-08 11:31 | 2167-07-08 11:31 | 97710.48 | Planned Total Cost | [19 empty] | 34167.85 | 63542.63
|  |  | JDH3-02-008-L-36-Road Works - RD |  | 2026-02-23 | 2026-03-11 | 24-Dec-24 A | 27-Jan-25 A | 2167-07-08 11:31 | 2167-07-08 11:31 | 97710.48 | Remaining Total Cost
|  |  | JDH3-02-008-L-36-Road Works - RD |  | 2026-02-23 | 2026-03-11 | 24-Dec-24 A | 27-Jan-25 A | 2167-07-08 11:31 | 2167-07-08 11:31 | 97710.48 | Actual Total Cost | [5 empty] | 23917.49 | 73792.99
|  |  | JDH3-02-008-L-36-(RD)-Precast Concrete Curb |  | 2026-02-23 | 2026-03-03 | 24-Dec-24 A | 11-Jan-25 A | 2049-09-02 13:12 | 2049-09-02 13:12 | 54668.55 | Planned Total Cost | [19 empty] | 34167.85 | 20500.71
|  |  | JDH3-02-008-L-36-(RD)-Precast Concrete Curb |  | 2026-02-23 | 2026-03-03 | 24-Dec-24 A | 11-Jan-25 A | 2049-09-02 13:12 | 2049-09-02 13:12 | 54668.55 | Remaining Total Cost
|  |  | JDH3-02-008-L-36-(RD)-Precast Concrete Curb |  | 2026-02-23 | 2026-03-03 | 24-Dec-24 A | 11-Jan-25 A | 2049-09-02 13:12 | 2049-09-02 13:12 | 54668.55 | Actual Total Cost | [5 empty] | 23917.49 | 30751.06
|  |  | JDH3-02-008-L-36-(RD)-Precast Interlocking Block Pavers |  | 2026-03-04 | 2026-03-11 | 09-Jan-25 A | 27-Jan-25 A | 2017-11-02 22:19 | 2017-11-02 22:19 | 43041.93 | Planned Total Cost | [20 empty] | 43041.93
|  |  | JDH3-02-008-L-36-(RD)-Precast Interlocking Block Pavers |  | 2026-03-04 | 2026-03-11 | 09-Jan-25 A | 27-Jan-25 A | 2017-11-02 22:19 | 2017-11-02 22:19 | 43041.93 | Remaining Total Cost
|  |  | JDH3-02-008-L-36-(RD)-Precast Interlocking Block Pavers |  | 2026-03-04 | 2026-03-11 | 09-Jan-25 A | 27-Jan-25 A | 2017-11-02 22:19 | 2017-11-02 22:19 | 43041.93 | Actual Total Cost | [6 empty] | 43041.93
|  |  | L-37 |  | 2026-02-15 | 2026-03-03 | 05-Nov-24 A | 28-Jan-25 A | 2047-07-29 22:05 | 2047-07-29 22:05 | 53902.92 | Planned Total Cost | [19 empty] | 36110 | 17792.92
|  |  | L-37 |  | 2026-02-15 | 2026-03-03 | 05-Nov-24 A | 28-Jan-25 A | 2047-07-29 22:05 | 2047-07-29 22:05 | 53902.92 | Remaining Total Cost
|  |  | L-37 |  | 2026-02-15 | 2026-03-03 | 05-Nov-24 A | 28-Jan-25 A | 2047-07-29 22:05 | 2047-07-29 22:05 | 53902.92 | Actual Total Cost | [5 empty] | 13203.32 | 40699.6
|  |  | JDH3-02-008-L-37-Road Works - RD |  | 2026-02-23 | 2026-03-03 | 24-Dec-24 A | 28-Jan-25 A | 2047-07-29 22:05 | 2047-07-29 22:05 | 53902.92 | Planned Total Cost | [19 empty] | 36110 | 17792.92
|  |  | JDH3-02-008-L-37-Road Works - RD |  | 2026-02-23 | 2026-03-03 | 24-Dec-24 A | 28-Jan-25 A | 2047-07-29 22:05 | 2047-07-29 22:05 | 53902.92 | Remaining Total Cost
|  |  | JDH3-02-008-L-37-Road Works - RD |  | 2026-02-23 | 2026-03-03 | 24-Dec-24 A | 28-Jan-25 A | 2047-07-29 22:05 | 2047-07-29 22:05 | 53902.92 | Actual Total Cost | [5 empty] | 13203.32 | 40699.6
|  |  | JDH3-02-008-L-37-(RD)-Precast Concrete Curb |  | 2026-02-23 | 2026-02-26 | 24-Dec-24 A | 11-Jan-25 A | 1982-08-16 00:29 | 1982-08-16 00:29 | 30179.02 | Planned Total Cost | [19 empty] | 30179.02
|  |  | JDH3-02-008-L-37-(RD)-Precast Concrete Curb |  | 2026-02-23 | 2026-02-26 | 24-Dec-24 A | 11-Jan-25 A | 1982-08-16 00:29 | 1982-08-16 00:29 | 30179.02 | Remaining Total Cost
|  |  | JDH3-02-008-L-37-(RD)-Precast Concrete Curb |  | 2026-02-23 | 2026-02-26 | 24-Dec-24 A | 11-Jan-25 A | 1982-08-16 00:29 | 1982-08-16 00:29 | 30179.02 | Actual Total Cost | [5 empty] | 13203.32 | 16975.7
|  |  | JDH3-02-008-L-37-(RD)-Precast Interlocking Block Pavers |  | 2026-02-28 | 2026-03-03 | 11-Jan-25 A | 28-Jan-25 A | 1964-12-12 21:36 | 1964-12-12 21:36 | 23723.9 | Planned Total Cost | [19 empty] | 5930.97 | 17792.92
|  |  | JDH3-02-008-L-37-(RD)-Precast Interlocking Block Pavers |  | 2026-02-28 | 2026-03-03 | 11-Jan-25 A | 28-Jan-25 A | 1964-12-12 21:36 | 1964-12-12 21:36 | 23723.9 | Remaining Total Cost
|  |  | JDH3-02-008-L-37-(RD)-Precast Interlocking Block Pavers |  | 2026-02-28 | 2026-03-03 | 11-Jan-25 A | 28-Jan-25 A | 1964-12-12 21:36 | 1964-12-12 21:36 | 23723.9 | Actual Total Cost | [6 empty] | 23723.9
|  |  | Z12 |  | 2026-01-29 | 2026-02-14 | 28-Apr-25 A | 2025-11-24 | 0 | 0 | 357170.19 | Planned Total Cost | [15 empty] | 347344.62 | 9825.57
|  |  | Z12 |  | 2026-01-29 | 2026-02-14 | 28-Apr-25 A | 2025-11-24 | 0 | 0 | 357170.19 | Remaining Total Cost | [15 empty] | 347344.62 | 9825.57
|  |  | Z12 |  | 2026-01-29 | 2026-02-14 | 28-Apr-25 A | 2025-11-24 | 0 | 0 | 357170.19 | Actual Total Cost
|  |  | RCB |  | 2026-01-29 | 2026-02-14 | 2025-10-02 | 2025-11-24 | 0 | 0 | 357170.19 | Planned Total Cost | [15 empty] | 347344.62 | 9825.57
|  |  | RCB |  | 2026-01-29 | 2026-02-14 | 2025-10-02 | 2025-11-24 | 0 | 0 | 357170.19 | Remaining Total Cost | [15 empty] | 347344.62 | 9825.57
|  |  | RCB |  | 2026-01-29 | 2026-02-14 | 2025-10-02 | 2025-11-24 | 0 | 0 | 357170.19 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z12-Storm Network - ST |  | 2026-01-29 | 2026-02-14 | 2025-10-02 | 2025-11-24 | 0 | 0 | 357170.19 | Planned Total Cost | [15 empty] | 347344.62 | 9825.57
|  |  | JDH3-02-008-RCB-Z12-Storm Network - ST |  | 2026-01-29 | 2026-02-14 | 2025-10-02 | 2025-11-24 | 0 | 0 | 357170.19 | Remaining Total Cost | [15 empty] | 347344.62 | 9825.57
|  |  | JDH3-02-008-RCB-Z12-Storm Network - ST |  | 2026-01-29 | 2026-02-14 | 2025-10-02 | 2025-11-24 | 0 | 0 | 357170.19 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z12-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-01-29 | 2026-02-10 | 2025-10-02 | 2025-10-21 | 0 | 0 | 130581.28 | Planned Total Cost | [15 empty] | 130581.28
|  |  | JDH3-02-008-RCB-Z12-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-01-29 | 2026-02-10 | 2025-10-02 | 2025-10-21 | 0 | 0 | 130581.28 | Remaining Total Cost | [15 empty] | 130581.28
|  |  | JDH3-02-008-RCB-Z12-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-01-29 | 2026-02-10 | 2025-10-02 | 2025-10-21 | 0 | 0 | 130581.28 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z12-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-02-01 | 2026-02-11 | 2025-10-05 | 2025-10-15 | 0 | 0 | 65913.64 | Planned Total Cost | [15 empty] | 65913.64
|  |  | JDH3-02-008-RCB-Z12-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-02-01 | 2026-02-11 | 2025-10-05 | 2025-10-15 | 0 | 0 | 65913.64 | Remaining Total Cost | [15 empty] | 65913.64
|  |  | JDH3-02-008-RCB-Z12-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-02-01 | 2026-02-11 | 2025-10-05 | 2025-10-15 | 0 | 0 | 65913.64 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z12-(ST)- Single Catchbasine Works |  | 2026-02-03 | 2026-02-14 | 2025-10-07 | 2025-11-24 | 0 | 0 | 65503.79 | Planned Total Cost | [15 empty] | 55678.22 | 9825.57
|  |  | JDH3-02-008-RCB-Z12-(ST)- Single Catchbasine Works |  | 2026-02-03 | 2026-02-14 | 2025-10-07 | 2025-11-24 | 0 | 0 | 65503.79 | Remaining Total Cost | [15 empty] | 55678.22 | 9825.57
|  |  | JDH3-02-008-RCB-Z12-(ST)- Single Catchbasine Works |  | 2026-02-03 | 2026-02-14 | 2025-10-07 | 2025-11-24 | 0 | 0 | 65503.79 | Actual Total Cost
|  |  | JDH3-02-008-RCB-Z12-(ST)- Double Catchbasine Works |  | 2026-02-05 | 2026-02-14 | 2025-10-09 | 2025-10-18 | 0 | 0 | 95171.48 | Planned Total Cost | [15 empty] | 95171.48
|  |  | JDH3-02-008-RCB-Z12-(ST)- Double Catchbasine Works |  | 2026-02-05 | 2026-02-14 | 2025-10-09 | 2025-10-18 | 0 | 0 | 95171.48 | Remaining Total Cost | [15 empty] | 95171.48
|  |  | JDH3-02-008-RCB-Z12-(ST)- Double Catchbasine Works |  | 2026-02-05 | 2026-02-14 | 2025-10-09 | 2025-10-18 | 0 | 0 | 95171.48 | Actual Total Cost
|  |  | Z13 |  | 2026-02-28 | 2026-06-25 | 20-Apr-25 A | 2026-02-28 | 2843956.27 | 2843956.28 | 5727182.19 | Planned Total Cost | [14 empty] | 131468.69 | 1483980.32 | 591099.06 | 514638.14 |  | 260822.3 | 780207.13 | 540036.45 | 1149795.42 | 275134.67
|  |  | Z13 |  | 2026-02-28 | 2026-06-25 | 20-Apr-25 A | 2026-02-28 | 2843956.27 | 2843956.28 | 5727182.19 | Remaining Total Cost | [15 empty] | 1521878.86 | 591099.06 | 514638.14 |  | 255609.86
|  |  | Z13 |  | 2026-02-28 | 2026-06-25 | 20-Apr-25 A | 2026-02-28 | 2843956.27 | 2843956.28 | 5727182.19 | Actual Total Cost | [9 empty] | 7330 | 64146.29 | 20473.42 |  | 2578311.57 | 165293.75 | 8401.25
|  |  | RCB |  | 2026-02-28 | 2026-03-29 | 20-Apr-25 A | 2025-10-13 | 2151-09-29 17:02 | 2151-09-29 17:02 | 178585.09 | Planned Total Cost | [15 empty] | 86635.38 |  |  |  | 5212.44 | 86737.27
|  |  | RCB |  | 2026-02-28 | 2026-03-29 | 20-Apr-25 A | 2025-10-13 | 2151-09-29 17:02 | 2151-09-29 17:02 | 178585.09 | Remaining Total Cost | [15 empty] | 86635.38
|  |  | RCB |  | 2026-02-28 | 2026-03-29 | 20-Apr-25 A | 2025-10-13 | 2151-09-29 17:02 | 2151-09-29 17:02 | 178585.09 | Actual Total Cost | [9 empty] | 7330 | 64146.29 | 20473.42
|  |  | JDH3-02-008-RCB-Z13-Storm Network - ST |  | 2026-02-28 | 2026-03-29 | 20-Apr-25 A | 2025-10-13 | 2151-09-29 17:02 | 2151-09-29 17:02 | 178585.09 | Planned Total Cost | [15 empty] | 86635.38 |  |  |  | 5212.44 | 86737.27
|  |  | JDH3-02-008-RCB-Z13-Storm Network - ST |  | 2026-02-28 | 2026-03-29 | 20-Apr-25 A | 2025-10-13 | 2151-09-29 17:02 | 2151-09-29 17:02 | 178585.09 | Remaining Total Cost | [15 empty] | 86635.38
|  |  | JDH3-02-008-RCB-Z13-Storm Network - ST |  | 2026-02-28 | 2026-03-29 | 20-Apr-25 A | 2025-10-13 | 2151-09-29 17:02 | 2151-09-29 17:02 | 178585.09 | Actual Total Cost | [9 empty] | 7330 | 64146.29 | 20473.42
|  |  | JDH3-02-008-RCB-Z13-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-02-28 | 2026-03-29 | 20-Apr-25 A | 2025-10-13 | 2014-03-12 05:46 | 2014-03-12 05:46 | 65290.64 | Planned Total Cost | [15 empty] | 23580.4 |  |  |  | 5212.44 | 36497.79
|  |  | JDH3-02-008-RCB-Z13-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-02-28 | 2026-03-29 | 20-Apr-25 A | 2025-10-13 | 2014-03-12 05:46 | 2014-03-12 05:46 | 65290.64 | Remaining Total Cost | [15 empty] | 23580.4
|  |  | JDH3-02-008-RCB-Z13-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-02-28 | 2026-03-29 | 20-Apr-25 A | 2025-10-13 | 2014-03-12 05:46 | 2014-03-12 05:46 | 65290.64 | Actual Total Cost | [9 empty] | 7330 | 30795.35 | 3584.89
|  |  | JDH3-02-008-RCB-Z13-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-03-02 | 2026-03-15 | 10-May-25 A | 2025-10-13 | 1953-03-20 09:07 | 1953-03-20 08:53 | 32956.82 | Planned Total Cost | [15 empty] | 13518.44 |  |  |  |  | 19438.38
|  |  | JDH3-02-008-RCB-Z13-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-03-02 | 2026-03-15 | 10-May-25 A | 2025-10-13 | 1953-03-20 09:07 | 1953-03-20 08:53 | 32956.82 | Remaining Total Cost | [15 empty] | 13518.44
|  |  | JDH3-02-008-RCB-Z13-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-03-02 | 2026-03-15 | 10-May-25 A | 2025-10-13 | 1953-03-20 09:07 | 1953-03-20 08:53 | 32956.82 | Actual Total Cost | [10 empty] | 14273.65 | 5164.72
|  |  | JDH3-02-008-RCB-Z13-(ST)- Single Catchbasine Works |  | 2026-03-04 | 2026-03-15 | 15-May-25 A | 2025-10-11 | 1953-03-19 01:55 | 1953-03-19 01:55 | 32751.9 | Planned Total Cost | [15 empty] | 13314.82 |  |  |  |  | 19437.08
|  |  | JDH3-02-008-RCB-Z13-(ST)- Single Catchbasine Works |  | 2026-03-04 | 2026-03-15 | 15-May-25 A | 2025-10-11 | 1953-03-19 01:55 | 1953-03-19 01:55 | 32751.9 | Remaining Total Cost | [15 empty] | 13314.82
|  |  | JDH3-02-008-RCB-Z13-(ST)- Single Catchbasine Works |  | 2026-03-04 | 2026-03-15 | 15-May-25 A | 2025-10-11 | 1953-03-19 01:55 | 1953-03-19 01:55 | 32751.9 | Actual Total Cost | [10 empty] | 12027.79 | 7409.29
|  |  | JDH3-02-008-RCB-Z13-(ST)- Double Catchbasine Works |  | 2026-03-07 | 2026-03-17 | 15-May-25 A | 2025-10-11 | 1931-02-10 00:29 | 1931-02-10 00:29 | 47585.74 | Planned Total Cost | [15 empty] | 36221.72 |  |  |  |  | 11364.02
|  |  | JDH3-02-008-RCB-Z13-(ST)- Double Catchbasine Works |  | 2026-03-07 | 2026-03-17 | 15-May-25 A | 2025-10-11 | 1931-02-10 00:29 | 1931-02-10 00:29 | 47585.74 | Remaining Total Cost | [15 empty] | 36221.72
|  |  | JDH3-02-008-RCB-Z13-(ST)- Double Catchbasine Works |  | 2026-03-07 | 2026-03-17 | 15-May-25 A | 2025-10-11 | 1931-02-10 00:29 | 1931-02-10 00:29 | 47585.74 | Actual Total Cost | [10 empty] | 7049.51 | 4314.51
|  |  | C10.CN |  | 2026-02-28 | 2026-06-25 | 03-Aug-25 A | 2026-02-28 | 2752006.55 | 2752006.57 | 5548597.09 | Planned Total Cost | [14 empty] | 131468.69 | 1397344.94 | 591099.06 | 514638.14 |  | 255609.86 | 693469.86 | 540036.45 | 1149795.42 | 275134.67
|  |  | C10.CN |  | 2026-02-28 | 2026-06-25 | 03-Aug-25 A | 2026-02-28 | 2752006.55 | 2752006.57 | 5548597.09 | Remaining Total Cost | [15 empty] | 1435243.48 | 591099.06 | 514638.14 |  | 255609.86
|  |  | C10.CN |  | 2026-02-28 | 2026-06-25 | 03-Aug-25 A | 2026-02-28 | 2752006.55 | 2752006.57 | 5548597.09 | Actual Total Cost | [13 empty] | 2578311.57 | 165293.75 | 8401.25
|  |  | JDH3-02-008-C10.CN-Storm Network - ST |  | 2026-02-28 | 2026-06-25 | 03-Aug-25 A | 2025-11-04 | 2752006.55 | 2752006.57 | 4209306.65 | Planned Total Cost | [14 empty] | 131468.69 | 1397344.94 | 22056.62 |  |  |  | 693469.86 | 540036.45 | 1149795.42 | 275134.67
|  |  | JDH3-02-008-C10.CN-Storm Network - ST |  | 2026-02-28 | 2026-06-25 | 03-Aug-25 A | 2025-11-04 | 2752006.55 | 2752006.57 | 4209306.65 | Remaining Total Cost | [15 empty] | 1435243.48 | 22056.62
|  |  | JDH3-02-008-C10.CN-Storm Network - ST |  | 2026-02-28 | 2026-06-25 | 03-Aug-25 A | 2025-11-04 | 2752006.55 | 2752006.57 | 4209306.65 | Actual Total Cost | [13 empty] | 2578311.57 | 165293.75 | 8401.25
|  |  | JDH3-02-008-C10.CN-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-02-28 | 2026-04-01 | 2025-10-02 | 2025-11-04 | 0 | 0 | 441132.42 | Planned Total Cost | [15 empty] | 419075.8 | 22056.62
|  |  | JDH3-02-008-C10.CN-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-02-28 | 2026-04-01 | 2025-10-02 | 2025-11-04 | 0 | 0 | 441132.42 | Remaining Total Cost | [15 empty] | 419075.8 | 22056.62
|  |  | JDH3-02-008-C10.CN-(ST)- Supply and install UPVC pipe Diameter 300 mm depth from 0.00 to 1.50 m |  | 2026-02-28 | 2026-04-01 | 2025-10-02 | 2025-11-04 | 0 | 0 | 441132.42 | Actual Total Cost
|  |  | JDH3-02-008-C10.CN-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2026-03-04 | 2026-03-15 | 07-Aug-25 A | 20-Aug-25 A | 1938-07-31 18:29 | 1938-07-31 18:29 | 14092.77 | Planned Total Cost | [20 empty] | 14092.77
|  |  | JDH3-02-008-C10.CN-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2026-03-04 | 2026-03-15 | 07-Aug-25 A | 20-Aug-25 A | 1938-07-31 18:29 | 1938-07-31 18:29 | 14092.77 | Remaining Total Cost
|  |  | JDH3-02-008-C10.CN-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 0.00 to 1.50 m |  | 2026-03-04 | 2026-03-15 | 07-Aug-25 A | 20-Aug-25 A | 1938-07-31 18:29 | 1938-07-31 18:29 | 14092.77 | Actual Total Cost | [13 empty] | 14092.77
|  |  | JDH3-02-008-C10.CN-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-03-07 | 2026-03-18 | 09-Aug-25 A | 2025-10-04 | 2075-02-26 22:34 | 2075-02-26 22:19 | 83923.99 | Planned Total Cost | [20 empty] | 83923.99
|  |  | JDH3-02-008-C10.CN-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-03-07 | 2026-03-18 | 09-Aug-25 A | 2025-10-04 | 2075-02-26 22:34 | 2075-02-26 22:19 | 83923.99 | Remaining Total Cost | [15 empty] | 19947.06
|  |  | JDH3-02-008-C10.CN-(ST)- Supply and install GRP pipe Diameter 400 mm depth from 1.51 to 2.50 m |  | 2026-03-07 | 2026-03-18 | 09-Aug-25 A | 2025-10-04 | 2075-02-26 22:34 | 2075-02-26 22:19 | 83923.99 | Actual Total Cost | [13 empty] | 23551.01 | 38928.66 | 1497.26
|  |  | JDH3-02-008-C10.CN-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2026-03-09 | 2026-03-19 | 12-Aug-25 A | 2025-10-02 | 1933-12-29 06:43 | 1933-12-29 06:43 | 24834.56 | Planned Total Cost | [20 empty] | 24834.56
|  |  | JDH3-02-008-C10.CN-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2026-03-09 | 2026-03-19 | 12-Aug-25 A | 2025-10-02 | 1933-12-29 06:43 | 1933-12-29 06:43 | 24834.56 | Remaining Total Cost | [15 empty] | 12417.28
|  |  | JDH3-02-008-C10.CN-(ST)- Supply and install GRP pipe Diameter 500 mm depth from 1.51 to 2.50 m |  | 2026-03-09 | 2026-03-19 | 12-Aug-25 A | 2025-10-02 | 1933-12-29 06:43 | 1933-12-29 06:43 | 24834.56 | Actual Total Cost | [13 empty] | 4183.16 | 7929.15 | 304.97
|  |  | JDH3-02-008-C10.CN-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 0.00 to 1.50 m |  | 2026-03-11 | 2026-04-06 | 03-Aug-25 A | 14-Aug-25 A | 622492.96 | 622492.97 | 622492.96 | Planned Total Cost | [20 empty] | 570618.54 | 51874.41
|  |  | JDH3-02-008-C10.CN-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 0.00 to 1.50 m |  | 2026-03-11 | 2026-04-06 | 03-Aug-25 A | 14-Aug-25 A | 622492.96 | 622492.97 | 622492.96 | Remaining Total Cost
|  |  | JDH3-02-008-C10.CN-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 0.00 to 1.50 m |  | 2026-03-11 | 2026-04-06 | 03-Aug-25 A | 14-Aug-25 A | 622492.96 | 622492.97 | 622492.96 | Actual Total Cost | [13 empty] | 622492.97
|  |  | JDH3-02-008-C10.CN-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-04-07 | 2026-06-25 | 06-Aug-25 A | 27-Aug-25 A | 1703214.63 | 1703214.63 | 1703214.63 | Planned Total Cost | [21 empty] | 383223.29 | 1044856.67 | 275134.67
|  |  | JDH3-02-008-C10.CN-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-04-07 | 2026-06-25 | 06-Aug-25 A | 27-Aug-25 A | 1703214.63 | 1703214.63 | 1703214.63 | Remaining Total Cost
|  |  | JDH3-02-008-C10.CN-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 1.51 to 2.50 m |  | 2026-04-07 | 2026-06-25 | 06-Aug-25 A | 27-Aug-25 A | 1703214.63 | 1703214.63 | 1703214.63 | Actual Total Cost | [13 empty] | 1703214.63
|  |  | JDH3-02-008-C10.CN-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2026-04-23 | 2026-05-05 | 31-Aug-25 A | 2025-10-04 | 2244-10-16 11:31 | 2244-10-16 11:46 | 250416.55 | Planned Total Cost | [14 empty] | 131468.69 | 118947.86
|  |  | JDH3-02-008-C10.CN-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2026-04-23 | 2026-05-05 | 31-Aug-25 A | 2025-10-04 | 2244-10-16 11:31 | 2244-10-16 11:46 | 250416.55 | Remaining Total Cost | [15 empty] | 124482.06
|  |  | JDH3-02-008-C10.CN-(ST)- Supply and install GRP pipe Diameter 1200 mm depth from 2.51 to 3.50 m |  | 2026-04-23 | 2026-05-05 | 31-Aug-25 A | 2025-10-04 | 2244-10-16 11:31 | 2244-10-16 11:46 | 250416.55 | Actual Total Cost | [13 empty] | 899.53 | 118435.94 | 6599.02
|  |  | JDH3-02-008-C10.CN-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2026-04-26 | 2026-05-06 | 2025-10-02 | 2025-10-14 | 0 | 0 | 10428.7 | Planned Total Cost | [15 empty] | 10428.7
|  |  | JDH3-02-008-C10.CN-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2026-04-26 | 2026-05-06 | 2025-10-02 | 2025-10-14 | 0 | 0 | 10428.7 | Remaining Total Cost | [15 empty] | 10428.7
|  |  | JDH3-02-008-C10.CN-(ST)- MH WORKS With (1200) diameter depth from 1.51 to 2.50 |  | 2026-04-26 | 2026-05-06 | 2025-10-02 | 2025-10-14 | 0 | 0 | 10428.7 | Actual Total Cost
|  |  | JDH3-02-008-C10.CN-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2026-04-28 | 2026-05-24 | 18-Aug-25 A | 2025-10-18 | 209877.5 | 209877.5 | 419754.99 | Planned Total Cost | [15 empty] | 209877.5 | [5 empty] | 104938.75 | 104938.75
|  |  | JDH3-02-008-C10.CN-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2026-04-28 | 2026-05-24 | 18-Aug-25 A | 2025-10-18 | 209877.5 | 209877.5 | 419754.99 | Remaining Total Cost | [15 empty] | 209877.5
|  |  | JDH3-02-008-C10.CN-(ST)- MH WORKS With (2000) diameter depth from 1.51 to 2.50 |  | 2026-04-28 | 2026-05-24 | 18-Aug-25 A | 2025-10-18 | 209877.5 | 209877.5 | 419754.99 | Actual Total Cost | [13 empty] | 209877.5
|  |  | JDH3-02-008-C10.CN-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-05-02 | 2026-05-19 | 2025-10-02 | 2025-10-20 | 0 | 0 | 344146.95 | Planned Total Cost | [15 empty] | 344146.95
|  |  | JDH3-02-008-C10.CN-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-05-02 | 2026-05-19 | 2025-10-02 | 2025-10-20 | 0 | 0 | 344146.95 | Remaining Total Cost | [15 empty] | 344146.95
|  |  | JDH3-02-008-C10.CN-(ST)- MH WORKS With (2000) diameter depth from 2.51 to 3.50 |  | 2026-05-02 | 2026-05-19 | 2025-10-02 | 2025-10-20 | 0 | 0 | 344146.95 | Actual Total Cost
|  |  | JDH3-02-008-C10.CN-(ST)- Single Catchbasine Works |  | 2026-05-04 | 2026-05-21 | 2025-10-05 | 2025-10-22 | 0 | 0 | 101679.84 | Planned Total Cost | [15 empty] | 101679.84
|  |  | JDH3-02-008-C10.CN-(ST)- Single Catchbasine Works |  | 2026-05-04 | 2026-05-21 | 2025-10-05 | 2025-10-22 | 0 | 0 | 101679.84 | Remaining Total Cost | [15 empty] | 101679.84
|  |  | JDH3-02-008-C10.CN-(ST)- Single Catchbasine Works |  | 2026-05-04 | 2026-05-21 | 2025-10-05 | 2025-10-22 | 0 | 0 | 101679.84 | Actual Total Cost
|  |  | JDH3-02-008-C10.CN-(ST)- Double Catchbasine Works |  | 2026-05-07 | 2026-05-18 | 2025-10-08 | 2025-10-19 | 0 | 0 | 193188.3 | Planned Total Cost | [15 empty] | 193188.3
|  |  | JDH3-02-008-C10.CN-(ST)- Double Catchbasine Works |  | 2026-05-07 | 2026-05-18 | 2025-10-08 | 2025-10-19 | 0 | 0 | 193188.3 | Remaining Total Cost | [15 empty] | 193188.3
|  |  | JDH3-02-008-C10.CN-(ST)- Double Catchbasine Works |  | 2026-05-07 | 2026-05-18 | 2025-10-08 | 2025-10-19 | 0 | 0 | 193188.3 | Actual Total Cost
|  |  | JDH3-02-008-C10.CN-TSE Network - TSE |  | 2026-04-23 | 2026-06-13 | 2025-11-05 | 2026-02-16 | 0 | 0 | 1241941.38 | Planned Total Cost | [16 empty] | 540056.75 | 514638.14 |  | 187246.49
|  |  | JDH3-02-008-C10.CN-TSE Network - TSE |  | 2026-04-23 | 2026-06-13 | 2025-11-05 | 2026-02-16 | 0 | 0 | 1241941.38 | Remaining Total Cost | [16 empty] | 540056.75 | 514638.14 |  | 187246.49
|  |  | JDH3-02-008-C10.CN-TSE Network - TSE |  | 2026-04-23 | 2026-06-13 | 2025-11-05 | 2026-02-16 | 0 | 0 | 1241941.38 | Actual Total Cost
|  |  | JDH3-02-008-C10.CN-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-04-23 | 2026-06-13 | 2025-11-05 | 2026-02-16 | 0 | 0 | 1131934.27 | Planned Total Cost | [16 empty] | 512349.19 | 506391.65 |  | 113193.43
|  |  | JDH3-02-008-C10.CN-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-04-23 | 2026-06-13 | 2025-11-05 | 2026-02-16 | 0 | 0 | 1131934.27 | Remaining Total Cost | [16 empty] | 512349.19 | 506391.65 |  | 113193.43
|  |  | JDH3-02-008-C10.CN-(TSE)- Supply and install HDPE Pipes - 450 mm depth from 1.51 to 2.5 m |  | 2026-04-23 | 2026-06-13 | 2025-11-05 | 2026-02-16 | 0 | 0 | 1131934.27 | Actual Total Cost
|  |  | JDH3-02-008-C10.CN-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2026-06-02 | 2026-06-06 | 2026-02-07 | 2026-02-10 | 0 | 0 | 70974.45 | Planned Total Cost | [19 empty] | 70974.45
|  |  | JDH3-02-008-C10.CN-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2026-06-02 | 2026-06-06 | 2026-02-07 | 2026-02-10 | 0 | 0 | 70974.45 | Remaining Total Cost | [19 empty] | 70974.45
|  |  | JDH3-02-008-C10.CN-(TSE)-Supply and install of butterfly valves-400 mm. |  | 2026-06-02 | 2026-06-06 | 2026-02-07 | 2026-02-10 | 0 | 0 | 70974.45 | Actual Total Cost
|  |  | JDH3-02-008-C10.CN-(TSE)-Supply and install of Air valves-65 mm. |  | 2026-06-02 | 2026-06-06 | 2025-12-15 | 2025-12-18 | 0 | 0 | 8246.49 | Planned Total Cost | [17 empty] | 8246.49
|  |  | JDH3-02-008-C10.CN-(TSE)-Supply and install of Air valves-65 mm. |  | 2026-06-02 | 2026-06-06 | 2025-12-15 | 2025-12-18 | 0 | 0 | 8246.49 | Remaining Total Cost | [17 empty] | 8246.49
|  |  | JDH3-02-008-C10.CN-(TSE)-Supply and install of Air valves-65 mm. |  | 2026-06-02 | 2026-06-06 | 2025-12-15 | 2025-12-18 | 0 | 0 | 8246.49 | Actual Total Cost
|  |  | JDH3-02-008-C10.CN-(TSE)- Supply and Construct Air Valves Chamber on 355-630 mm Diameter pipelines |  | 2026-05-07 | 2026-06-08 | 2025-11-17 | 2026-02-12 | 0 | 0 | 3479.28 | Planned Total Cost | [16 empty] | 3131.35 |  |  | 347.93
|  |  | JDH3-02-008-C10.CN-(TSE)- Supply and Construct Air Valves Chamber on 355-630 mm Diameter pipelines |  | 2026-05-07 | 2026-06-08 | 2025-11-17 | 2026-02-12 | 0 | 0 | 3479.28 | Remaining Total Cost | [16 empty] | 3131.35 |  |  | 347.93
|  |  | JDH3-02-008-C10.CN-(TSE)- Supply and Construct Air Valves Chamber on 355-630 mm Diameter pipelines |  | 2026-05-07 | 2026-06-08 | 2025-11-17 | 2026-02-12 | 0 | 0 | 3479.28 | Actual Total Cost
|  |  | JDH3-02-008-C10.CN-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-05-07 | 2026-06-08 | 2025-11-05 | 2026-02-12 | 0 | 0 | 27306.9 | Planned Total Cost | [16 empty] | 24576.21 |  |  | 2730.69
|  |  | JDH3-02-008-C10.CN-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-05-07 | 2026-06-08 | 2025-11-05 | 2026-02-12 | 0 | 0 | 27306.9 | Remaining Total Cost | [16 empty] | 24576.21 |  |  | 2730.69
|  |  | JDH3-02-008-C10.CN-(TSE)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-05-07 | 2026-06-08 | 2025-11-05 | 2026-02-12 | 0 | 0 | 27306.9 | Actual Total Cost
|  |  | JDH3-02-008-C10.CN-Potable Water Network - WT |  | 2026-05-05 | 2026-06-24 | 2025-11-17 | 2026-02-28 | 0 | 0 | 97349.06 | Planned Total Cost | [16 empty] | 28985.69 |  |  | 68363.37
|  |  | JDH3-02-008-C10.CN-Potable Water Network - WT |  | 2026-05-05 | 2026-06-24 | 2025-11-17 | 2026-02-28 | 0 | 0 | 97349.06 | Remaining Total Cost | [16 empty] | 28985.69 |  |  | 68363.37
|  |  | JDH3-02-008-C10.CN-Potable Water Network - WT |  | 2026-05-05 | 2026-06-24 | 2025-11-17 | 2026-02-28 | 0 | 0 | 97349.06 | Actual Total Cost
|  |  | JDH3-02-008-C10.CN-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-05-05 | 2026-05-18 | 2025-11-17 | 2025-11-30 | 0 | 0 | 11434.86 | Planned Total Cost | [16 empty] | 11434.86
|  |  | JDH3-02-008-C10.CN-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-05-05 | 2026-05-18 | 2025-11-17 | 2025-11-30 | 0 | 0 | 11434.86 | Remaining Total Cost | [16 empty] | 11434.86
|  |  | JDH3-02-008-C10.CN-(WT)- Supply and install HDPE Pipes -160 mm depth from 0 to 1.5 m |  | 2026-05-05 | 2026-05-18 | 2025-11-17 | 2025-11-30 | 0 | 0 | 11434.86 | Actual Total Cost
|  |  | JDH3-02-008-C10.CN-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2026-05-12 | 2026-05-16 | 2025-11-24 | 2025-11-27 | 0 | 0 | 4569.71 | Planned Total Cost | [16 empty] | 4569.71
|  |  | JDH3-02-008-C10.CN-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2026-05-12 | 2026-05-16 | 2025-11-24 | 2025-11-27 | 0 | 0 | 4569.71 | Remaining Total Cost | [16 empty] | 4569.71
|  |  | JDH3-02-008-C10.CN-(WT)- Supply and install gate valves -Diameter 150 mm |  | 2026-05-12 | 2026-05-16 | 2025-11-24 | 2025-11-27 | 0 | 0 | 4569.71 | Actual Total Cost
|  |  | JDH3-02-008-C10.CN-(WT)- Supply and install 3-out fire hydrant |  | 2026-06-09 | 2026-06-15 | 2026-02-14 | 2026-02-19 | 0 | 0 | 27205.21 | Planned Total Cost | [19 empty] | 27205.21
|  |  | JDH3-02-008-C10.CN-(WT)- Supply and install 3-out fire hydrant |  | 2026-06-09 | 2026-06-15 | 2026-02-14 | 2026-02-19 | 0 | 0 | 27205.21 | Remaining Total Cost | [19 empty] | 27205.21
|  |  | JDH3-02-008-C10.CN-(WT)- Supply and install 3-out fire hydrant |  | 2026-06-09 | 2026-06-15 | 2026-02-14 | 2026-02-19 | 0 | 0 | 27205.21 | Actual Total Cost
|  |  | JDH3-02-008-C10.CN-(WT)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-06-14 | 2026-06-22 | 2026-02-17 | 2026-02-25 | 0 | 0 | 27306.9 | Planned Total Cost | [19 empty] | 27306.9
|  |  | JDH3-02-008-C10.CN-(WT)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-06-14 | 2026-06-22 | 2026-02-17 | 2026-02-25 | 0 | 0 | 27306.9 | Remaining Total Cost | [19 empty] | 27306.9
|  |  | JDH3-02-008-C10.CN-(WT)- Supply and Construct R.C Valves Chamber on 315-400 mm Diameter pipelines |  | 2026-06-14 | 2026-06-22 | 2026-02-17 | 2026-02-25 | 0 | 0 | 27306.9 | Actual Total Cost
|  |  | JDH3-02-008-C10.CN-(WT)- Supply and install Wash-Out Valves -Diameter 100 mm. |  | 2026-05-12 | 2026-05-16 | 2025-11-24 | 2025-11-27 | 0 | 0 | 12981.12 | Planned Total Cost | [16 empty] | 12981.12
|  |  | JDH3-02-008-C10.CN-(WT)- Supply and install Wash-Out Valves -Diameter 100 mm. |  | 2026-05-12 | 2026-05-16 | 2025-11-24 | 2025-11-27 | 0 | 0 | 12981.12 | Remaining Total Cost | [16 empty] | 12981.12
|  |  | JDH3-02-008-C10.CN-(WT)- Supply and install Wash-Out Valves -Diameter 100 mm. |  | 2026-05-12 | 2026-05-16 | 2025-11-24 | 2025-11-27 | 0 | 0 | 12981.12 | Actual Total Cost
|  |  | JDH3-02-008-C10.CN-(WT)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipe |  | 2026-06-16 | 2026-06-24 | 2026-02-19 | 2026-02-28 | 0 | 0 | 13851.27 | Planned Total Cost | [19 empty] | 13851.27
|  |  | JDH3-02-008-C10.CN-(WT)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipe |  | 2026-06-16 | 2026-06-24 | 2026-02-19 | 2026-02-28 | 0 | 0 | 13851.27 | Remaining Total Cost | [19 empty] | 13851.27
|  |  | JDH3-02-008-C10.CN-(WT)- Supply and Construct Wash-out Valves Chamber on 110-400 mm Diameter pipe |  | 2026-06-16 | 2026-06-24 | 2026-02-19 | 2026-02-28 | 0 | 0 | 13851.27 | Actual Total Cost
|  |  | CCTV |  | 2026-04-18 | 2026-04-23 | 2026-01-24 | 2026-01-29 | 0 | 0 | 5065643.26 | Planned Total Cost | [18 empty] | 5065643.26
|  |  | CCTV |  | 2026-04-18 | 2026-04-23 | 2026-01-24 | 2026-01-29 | 0 | 0 | 5065643.26 | Remaining Total Cost | [18 empty] | 5065643.26
|  |  | CCTV |  | 2026-04-18 | 2026-04-23 | 2026-01-24 | 2026-01-29 | 0 | 0 | 5065643.26 | Actual Total Cost
|  |  | JDH3-02-008--Close Out |  | 2025-08-10 | 2026-07-28 | 2025-10-02 | 2026-10-10 | 0 | 0 | 31974487.55 | Planned Total Cost | [16 empty] | 30983.03 | 3648251.86 | 725888.15 | 1224936.25 | 617004.93 | 1016243.41 | 1088832.22 | 4087890.7 | 14903268.6 | 2847805.2 | 1542335.23 | 241047.97
|  |  | JDH3-02-008--Close Out |  | 2025-08-10 | 2026-07-28 | 2025-10-02 | 2026-10-10 | 0 | 0 | 31974487.55 | Remaining Total Cost | [16 empty] | 30983.03 | 3648251.86 | 725888.15 | 1224936.25 | 617004.93 | 1016243.41 | 1088832.22 | 4087890.7 | 14903268.6 | 2847805.2 | 1542335.23 | 241047.97
|  |  | JDH3-02-008--Close Out |  | 2025-08-10 | 2026-07-28 | 2025-10-02 | 2026-10-10 | 0 | 0 | 31974487.55 | Actual Total Cost
|  |  | JDH3-02-008--Final Testing and Commissioning - FT |  | 2025-08-10 | 2026-07-13 | 2025-10-02 | 2026-07-25 | 0 | 0 | 10162434.07 | Planned Total Cost | [17 empty] | 3493336.71 | 725888.15 | 1224936.25 | 617004.93 | 1016243.41 | 1088832.22 | 1416389.25 | 579803.16
|  |  | JDH3-02-008--Final Testing and Commissioning - FT |  | 2025-08-10 | 2026-07-13 | 2025-10-02 | 2026-07-25 | 0 | 0 | 10162434.07 | Remaining Total Cost | [17 empty] | 3493336.71 | 725888.15 | 1224936.25 | 617004.93 | 1016243.41 | 1088832.22 | 1416389.25 | 579803.16
|  |  | JDH3-02-008--Final Testing and Commissioning - FT |  | 2025-08-10 | 2026-07-13 | 2025-10-02 | 2026-07-25 | 0 | 0 | 10162434.07 | Actual Total Cost
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-PS |  | 2026-03-18 | 2026-03-22 | 2025-12-17 | 2025-12-21 | 0 | 0 | 181472.04 | Planned Total Cost | [17 empty] | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-PS |  | 2026-03-18 | 2026-03-22 | 2025-12-17 | 2025-12-21 | 0 | 0 | 181472.04 | Remaining Total Cost | [17 empty] | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-PS |  | 2026-03-18 | 2026-03-22 | 2025-12-17 | 2025-12-21 | 0 | 0 | 181472.04 | Actual Total Cost
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-HM |  | 2026-04-02 | 2026-04-06 | 2025-12-17 | 2025-12-21 | 0 | 0 | 181472.04 | Planned Total Cost | [17 empty] | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-HM |  | 2026-04-02 | 2026-04-06 | 2025-12-17 | 2025-12-21 | 0 | 0 | 181472.04 | Remaining Total Cost | [17 empty] | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-HM |  | 2026-04-02 | 2026-04-06 | 2025-12-17 | 2025-12-21 | 0 | 0 | 181472.04 | Actual Total Cost
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-MR |  | 2026-01-13 | 2026-07-13 | 2026-03-10 | 2026-07-25 | 0 | 0 | 1270304.26 | Planned Total Cost | [20 empty] | 181472.04 | 181472.04 | 181472.04 | 181472.04 | 544416.11
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-MR |  | 2026-01-13 | 2026-07-13 | 2026-03-10 | 2026-07-25 | 0 | 0 | 1270304.26 | Remaining Total Cost | [20 empty] | 181472.04 | 181472.04 | 181472.04 | 181472.04 | 544416.11
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-MR |  | 2026-01-13 | 2026-07-13 | 2026-03-10 | 2026-07-25 | 0 | 0 | 1270304.26 | Actual Total Cost
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z01 |  | 2026-06-07 | 2026-07-07 | 2026-04-20 | 2026-06-07 | 0 | 0 | 544416.11 | Planned Total Cost | [21 empty] | 362944.07 |  | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z01 |  | 2026-06-07 | 2026-07-07 | 2026-04-20 | 2026-06-07 | 0 | 0 | 544416.11 | Remaining Total Cost | [21 empty] | 362944.07 |  | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z01 |  | 2026-06-07 | 2026-07-07 | 2026-04-20 | 2026-06-07 | 0 | 0 | 544416.11 | Actual Total Cost
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z02 |  | 2025-10-18 | 2025-11-06 | 2026-03-26 | 2026-04-20 | 0 | 0 | 362944.07 | Planned Total Cost | [20 empty] | 181472.04 | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z02 |  | 2025-10-18 | 2025-11-06 | 2026-03-26 | 2026-04-20 | 0 | 0 | 362944.07 | Remaining Total Cost | [20 empty] | 181472.04 | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z02 |  | 2025-10-18 | 2025-11-06 | 2026-03-26 | 2026-04-20 | 0 | 0 | 362944.07 | Actual Total Cost
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z02-1 |  | 2025-08-14 | 2025-08-18 | 2025-12-17 | 2026-02-26 | 0 | 0 | 1088832.22 | Planned Total Cost | [17 empty] | 181472.04 | 181472.04 | 725888.15
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z02-1 |  | 2025-08-14 | 2025-08-18 | 2025-12-17 | 2026-02-26 | 0 | 0 | 1088832.22 | Remaining Total Cost | [17 empty] | 181472.04 | 181472.04 | 725888.15
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z02-1 |  | 2025-08-14 | 2025-08-18 | 2025-12-17 | 2026-02-26 | 0 | 0 | 1088832.22 | Actual Total Cost
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z02-2 |  | 2025-08-14 | 2025-09-15 | 2025-12-17 | 2026-02-26 | 0 | 0 | 1270304.26 | Planned Total Cost | [17 empty] | 589784.12 | 499048.1 | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z02-2 |  | 2025-08-14 | 2025-09-15 | 2025-12-17 | 2026-02-26 | 0 | 0 | 1270304.26 | Remaining Total Cost | [17 empty] | 589784.12 | 499048.1 | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z02-2 |  | 2025-08-14 | 2025-09-15 | 2025-12-17 | 2026-02-26 | 0 | 0 | 1270304.26 | Actual Total Cost
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z03 |  | 2026-01-06 | 2026-01-10 | 2025-12-17 | 2025-12-21 | 0 | 0 | 181472.04 | Planned Total Cost | [17 empty] | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z03 |  | 2026-01-06 | 2026-01-10 | 2025-12-17 | 2025-12-21 | 0 | 0 | 181472.04 | Remaining Total Cost | [17 empty] | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z03 |  | 2026-01-06 | 2026-01-10 | 2025-12-17 | 2025-12-21 | 0 | 0 | 181472.04 | Actual Total Cost
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z04 |  | 2026-05-09 | 2026-06-22 | 2026-05-26 | 2026-06-23 | 0 | 0 | 362944.07 | Planned Total Cost | [22 empty] | 181472.04 | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z04 |  | 2026-05-09 | 2026-06-22 | 2026-05-26 | 2026-06-23 | 0 | 0 | 362944.07 | Remaining Total Cost | [22 empty] | 181472.04 | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z04 |  | 2026-05-09 | 2026-06-22 | 2026-05-26 | 2026-06-23 | 0 | 0 | 362944.07 | Actual Total Cost
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z05 |  | 2025-10-28 | 2025-11-24 | 2026-03-30 | 2026-05-07 | 0 | 0 | 362944.07 | Planned Total Cost | [20 empty] | 72588.81 | 108883.22 | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z05 |  | 2025-10-28 | 2025-11-24 | 2026-03-30 | 2026-05-07 | 0 | 0 | 362944.07 | Remaining Total Cost | [20 empty] | 72588.81 | 108883.22 | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z05 |  | 2025-10-28 | 2025-11-24 | 2026-03-30 | 2026-05-07 | 0 | 0 | 362944.07 | Actual Total Cost
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z06 |  | 2026-03-11 | 2026-04-19 | 2026-05-14 | 2026-06-29 | 0 | 0 | 544416.11 | Planned Total Cost | [22 empty] | 362944.07 | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z06 |  | 2026-03-11 | 2026-04-19 | 2026-05-14 | 2026-06-29 | 0 | 0 | 544416.11 | Remaining Total Cost | [22 empty] | 362944.07 | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z06 |  | 2026-03-11 | 2026-04-19 | 2026-05-14 | 2026-06-29 | 0 | 0 | 544416.11 | Actual Total Cost
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z07 |  | 2026-01-10 | 2026-02-02 | 2026-06-07 | 2026-07-01 | 0 | 0 | 544416.11 | Planned Total Cost | [23 empty] | 509029.06 | 35387.05
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z07 |  | 2026-01-10 | 2026-02-02 | 2026-06-07 | 2026-07-01 | 0 | 0 | 544416.11 | Remaining Total Cost | [23 empty] | 509029.06 | 35387.05
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z07 |  | 2026-01-10 | 2026-02-02 | 2026-06-07 | 2026-07-01 | 0 | 0 | 544416.11 | Actual Total Cost
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z07-1 |  | 2025-08-14 | 2025-08-18 | 2025-12-17 | 2025-12-21 | 0 | 0 | 1088832.22 | Planned Total Cost | [17 empty] | 1088832.22
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z07-1 |  | 2025-08-14 | 2025-08-18 | 2025-12-17 | 2025-12-21 | 0 | 0 | 1088832.22 | Remaining Total Cost | [17 empty] | 1088832.22
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z07-1 |  | 2025-08-14 | 2025-08-18 | 2025-12-17 | 2025-12-21 | 0 | 0 | 1088832.22 | Actual Total Cost
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z08 |  | 2026-02-08 | 2026-03-26 | 2025-12-17 | 2026-05-07 | 0 | 0 | 544416.11 | Planned Total Cost | [17 empty] | 362944.07 |  |  |  |  | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z08 |  | 2026-02-08 | 2026-03-26 | 2025-12-17 | 2026-05-07 | 0 | 0 | 544416.11 | Remaining Total Cost | [17 empty] | 362944.07 |  |  |  |  | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z08 |  | 2026-02-08 | 2026-03-26 | 2025-12-17 | 2026-05-07 | 0 | 0 | 544416.11 | Actual Total Cost
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z09 |  | 2026-07-09 | 2026-07-13 | 2026-06-20 | 2026-06-24 | 0 | 0 | 181472.04 | Planned Total Cost | [23 empty] | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z09 |  | 2026-07-09 | 2026-07-13 | 2026-06-20 | 2026-06-24 | 0 | 0 | 181472.04 | Remaining Total Cost | [23 empty] | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z09 |  | 2026-07-09 | 2026-07-13 | 2026-06-20 | 2026-06-24 | 0 | 0 | 181472.04 | Actual Total Cost
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z10 |  | 2026-06-29 | 2026-07-02 | 2026-04-13 | 2026-04-16 | 0 | 0 | 181472.04 | Planned Total Cost | [21 empty] | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z10 |  | 2026-06-29 | 2026-07-02 | 2026-04-13 | 2026-04-16 | 0 | 0 | 181472.04 | Remaining Total Cost | [21 empty] | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z10 |  | 2026-06-29 | 2026-07-02 | 2026-04-13 | 2026-04-16 | 0 | 0 | 181472.04 | Actual Total Cost
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z11 |  | 2026-03-03 | 2026-03-16 | 2025-12-17 | 2025-12-21 | 0 | 0 | 362944.07 | Planned Total Cost | [17 empty] | 362944.07
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z11 |  | 2026-03-03 | 2026-03-16 | 2025-12-17 | 2025-12-21 | 0 | 0 | 362944.07 | Remaining Total Cost | [17 empty] | 362944.07
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z11 |  | 2026-03-03 | 2026-03-16 | 2025-12-17 | 2025-12-21 | 0 | 0 | 362944.07 | Actual Total Cost
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z12 |  | 2026-02-15 | 2026-02-18 | 2025-12-17 | 2025-12-21 | 0 | 0 | 181472.04 | Planned Total Cost | [17 empty] | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z12 |  | 2026-02-15 | 2026-02-18 | 2025-12-17 | 2025-12-21 | 0 | 0 | 181472.04 | Remaining Total Cost | [17 empty] | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z12 |  | 2026-02-15 | 2026-02-18 | 2025-12-17 | 2025-12-21 | 0 | 0 | 181472.04 | Actual Total Cost
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z13 |  | 2026-06-14 | 2026-06-30 | 2025-12-17 | 2026-03-04 | 0 | 0 | 544416.11 | Planned Total Cost | [17 empty] | 181472.04 |  | 181472.04 | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z13 |  | 2026-06-14 | 2026-06-30 | 2025-12-17 | 2026-03-04 | 0 | 0 | 544416.11 | Remaining Total Cost | [17 empty] | 181472.04 |  | 181472.04 | 181472.04
|  |  | JDH3-02-008-Final Testing and Commissioning - FT-Z13 |  | 2026-06-14 | 2026-06-30 | 2025-12-17 | 2026-03-04 | 0 | 0 | 544416.11 | Actual Total Cost
|  |  | JDH3-02-008--Engineering |  | 2026-01-06 | 2026-07-28 | 2025-11-30 | 2026-10-10 | 0 | 0 | 21440257.23 | Planned Total Cost | [16 empty] | 30983.03 | 154915.15 | [5 empty] | 2299705.2 | 14323465.44 | 2847805.2 | 1542335.23 | 241047.97
|  |  | JDH3-02-008--Engineering |  | 2026-01-06 | 2026-07-28 | 2025-11-30 | 2026-10-10 | 0 | 0 | 21440257.23 | Remaining Total Cost | [16 empty] | 30983.03 | 154915.15 | [5 empty] | 2299705.2 | 14323465.44 | 2847805.2 | 1542335.23 | 241047.97
|  |  | JDH3-02-008--Engineering |  | 2026-01-06 | 2026-07-28 | 2025-11-30 | 2026-10-10 | 0 | 0 | 21440257.23 | Actual Total Cost
|  |  | JDH3-02-008--As Built Drawings |  | 2026-01-06 | 2026-07-28 | 2025-11-30 | 2026-10-10 | 0 | 0 | 21068460.87 | Planned Total Cost | [16 empty] | 30983.03 | 154915.15 | [5 empty] | 1927908.84 | 14323465.44 | 2847805.2 | 1542335.23 | 241047.97
|  |  | JDH3-02-008--As Built Drawings |  | 2026-01-06 | 2026-07-28 | 2025-11-30 | 2026-10-10 | 0 | 0 | 21068460.87 | Remaining Total Cost | [16 empty] | 30983.03 | 154915.15 | [5 empty] | 1927908.84 | 14323465.44 | 2847805.2 | 1542335.23 | 241047.97
|  |  | JDH3-02-008--As Built Drawings |  | 2026-01-06 | 2026-07-28 | 2025-11-30 | 2026-10-10 | 0 | 0 | 21068460.87 | Actual Total Cost
|  |  | JDH3-02-008--As Built Drawing Submittals |  | 2026-01-29 | 2026-07-21 | 2026-06-27 | 2026-09-26 | 0 | 0 | 10534230.43 | Planned Total Cost | [23 empty] | 1927908.84 | 6626041.23 | 1305469.97 | 674810.39
|  |  | JDH3-02-008--As Built Drawing Submittals |  | 2026-01-29 | 2026-07-21 | 2026-06-27 | 2026-09-26 | 0 | 0 | 10534230.43 | Remaining Total Cost | [23 empty] | 1927908.84 | 6626041.23 | 1305469.97 | 674810.39
|  |  | JDH3-02-008--As Built Drawing Submittals |  | 2026-01-29 | 2026-07-21 | 2026-06-27 | 2026-09-26 | 0 | 0 | 10534230.43 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Submittals-MR |  | 2026-06-21 | 2026-07-20 | 2026-06-27 | 2026-08-01 | 0 | 0 | 1301287.26 | Planned Total Cost | [23 empty] | 299296.07 | 990992.21 | 10998.98
|  |  | JDH3-02-008-As Built Drawing Submittals-MR |  | 2026-06-21 | 2026-07-20 | 2026-06-27 | 2026-08-01 | 0 | 0 | 1301287.26 | Remaining Total Cost | [23 empty] | 299296.07 | 990992.21 | 10998.98
|  |  | JDH3-02-008-As Built Drawing Submittals-MR |  | 2026-06-21 | 2026-07-20 | 2026-06-27 | 2026-08-01 | 0 | 0 | 1301287.26 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Submittals-Z01 |  | 2026-06-11 | 2026-07-13 | 2026-06-27 | 2026-07-08 | 0 | 0 | 557694.54 | Planned Total Cost | [23 empty] | 239436.86 | 318257.68
|  |  | JDH3-02-008-As Built Drawing Submittals-Z01 |  | 2026-06-11 | 2026-07-13 | 2026-06-27 | 2026-07-08 | 0 | 0 | 557694.54 | Remaining Total Cost | [23 empty] | 239436.86 | 318257.68
|  |  | JDH3-02-008-As Built Drawing Submittals-Z01 |  | 2026-06-11 | 2026-07-13 | 2026-06-27 | 2026-07-08 | 0 | 0 | 557694.54 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Submittals-Z02 |  | 2026-07-02 | 2026-07-15 | 2026-07-02 | 2026-07-16 | 0 | 0 | 371796.36 | Planned Total Cost | [24 empty] | 371796.36
|  |  | JDH3-02-008-As Built Drawing Submittals-Z02 |  | 2026-07-02 | 2026-07-15 | 2026-07-02 | 2026-07-16 | 0 | 0 | 371796.36 | Remaining Total Cost | [24 empty] | 371796.36
|  |  | JDH3-02-008-As Built Drawing Submittals-Z02 |  | 2026-07-02 | 2026-07-15 | 2026-07-02 | 2026-07-16 | 0 | 0 | 371796.36 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Submittals-Z02-1 |  | 2026-01-29 | 2026-03-11 | 2026-06-27 | 2026-08-08 | 0 | 0 | 1115389.08 | Planned Total Cost | [23 empty] | 99765.36 | 805558.78 | 210064.94
|  |  | JDH3-02-008-As Built Drawing Submittals-Z02-1 |  | 2026-01-29 | 2026-03-11 | 2026-06-27 | 2026-08-08 | 0 | 0 | 1115389.08 | Remaining Total Cost | [23 empty] | 99765.36 | 805558.78 | 210064.94
|  |  | JDH3-02-008-As Built Drawing Submittals-Z02-1 |  | 2026-01-29 | 2026-03-11 | 2026-06-27 | 2026-08-08 | 0 | 0 | 1115389.08 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Submittals-Z02-2 |  | 2026-03-12 | 2026-04-29 | 2026-08-08 | 2026-09-26 | 0 | 0 | 1301287.26 | Planned Total Cost | [25 empty] | 626476.87 | 674810.39
|  |  | JDH3-02-008-As Built Drawing Submittals-Z02-2 |  | 2026-03-12 | 2026-04-29 | 2026-08-08 | 2026-09-26 | 0 | 0 | 1301287.26 | Remaining Total Cost | [25 empty] | 626476.87 | 674810.39
|  |  | JDH3-02-008-As Built Drawing Submittals-Z02-2 |  | 2026-03-12 | 2026-04-29 | 2026-08-08 | 2026-09-26 | 0 | 0 | 1301287.26 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Submittals-Z03 |  | 2026-01-29 | 2026-02-04 | 2026-06-27 | 2026-07-04 | 0 | 0 | 185898.18 | Planned Total Cost | [23 empty] | 99765.36 | 86132.82
|  |  | JDH3-02-008-As Built Drawing Submittals-Z03 |  | 2026-01-29 | 2026-02-04 | 2026-06-27 | 2026-07-04 | 0 | 0 | 185898.18 | Remaining Total Cost | [23 empty] | 99765.36 | 86132.82
|  |  | JDH3-02-008-As Built Drawing Submittals-Z03 |  | 2026-01-29 | 2026-02-04 | 2026-06-27 | 2026-07-04 | 0 | 0 | 185898.18 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Submittals-Z04 |  | 2026-06-23 | 2026-07-06 | 2026-06-27 | 2026-07-11 | 0 | 0 | 371796.36 | Planned Total Cost | [23 empty] | 99765.36 | 272031
|  |  | JDH3-02-008-As Built Drawing Submittals-Z04 |  | 2026-06-23 | 2026-07-06 | 2026-06-27 | 2026-07-11 | 0 | 0 | 371796.36 | Remaining Total Cost | [23 empty] | 99765.36 | 272031
|  |  | JDH3-02-008-As Built Drawing Submittals-Z04 |  | 2026-06-23 | 2026-07-06 | 2026-06-27 | 2026-07-11 | 0 | 0 | 371796.36 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Submittals-Z05 |  | 2026-01-29 | 2026-02-04 | 2026-06-27 | 2026-07-04 | 0 | 0 | 371796.36 | Planned Total Cost | [23 empty] | 199530.71 | 172265.65
|  |  | JDH3-02-008-As Built Drawing Submittals-Z05 |  | 2026-01-29 | 2026-02-04 | 2026-06-27 | 2026-07-04 | 0 | 0 | 371796.36 | Remaining Total Cost | [23 empty] | 199530.71 | 172265.65
|  |  | JDH3-02-008-As Built Drawing Submittals-Z05 |  | 2026-01-29 | 2026-02-04 | 2026-06-27 | 2026-07-04 | 0 | 0 | 371796.36 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Submittals-Z06 |  | 2026-03-16 | 2026-03-30 | 2026-06-27 | 2026-07-13 | 0 | 0 | 557694.54 | Planned Total Cost | [23 empty] | 137564.65 | 420129.89
|  |  | JDH3-02-008-As Built Drawing Submittals-Z06 |  | 2026-03-16 | 2026-03-30 | 2026-06-27 | 2026-07-13 | 0 | 0 | 557694.54 | Remaining Total Cost | [23 empty] | 137564.65 | 420129.89
|  |  | JDH3-02-008-As Built Drawing Submittals-Z06 |  | 2026-03-16 | 2026-03-30 | 2026-06-27 | 2026-07-13 | 0 | 0 | 557694.54 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Submittals-Z07 |  | 2026-01-29 | 2026-02-09 | 2026-06-27 | 2026-07-08 | 0 | 0 | 557694.54 | Planned Total Cost | [23 empty] | 137564.65 | 420129.89
|  |  | JDH3-02-008-As Built Drawing Submittals-Z07 |  | 2026-01-29 | 2026-02-09 | 2026-06-27 | 2026-07-08 | 0 | 0 | 557694.54 | Remaining Total Cost | [23 empty] | 137564.65 | 420129.89
|  |  | JDH3-02-008-As Built Drawing Submittals-Z07 |  | 2026-01-29 | 2026-02-09 | 2026-06-27 | 2026-07-08 | 0 | 0 | 557694.54 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Submittals-Z07-1 |  | 2026-02-08 | 2026-03-21 | 2026-07-06 | 2026-08-17 | 0 | 0 | 1115389.08 | Planned Total Cost | [24 empty] | 657459.9 | 457929.18
|  |  | JDH3-02-008-As Built Drawing Submittals-Z07-1 |  | 2026-02-08 | 2026-03-21 | 2026-07-06 | 2026-08-17 | 0 | 0 | 1115389.08 | Remaining Total Cost | [24 empty] | 657459.9 | 457929.18
|  |  | JDH3-02-008-As Built Drawing Submittals-Z07-1 |  | 2026-02-08 | 2026-03-21 | 2026-07-06 | 2026-08-17 | 0 | 0 | 1115389.08 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Submittals-Z08 |  | 2026-03-28 | 2026-04-16 | 2026-06-27 | 2026-07-18 | 0 | 0 | 557694.54 | Planned Total Cost | [23 empty] | 99765.36 | 457929.18
|  |  | JDH3-02-008-As Built Drawing Submittals-Z08 |  | 2026-03-28 | 2026-04-16 | 2026-06-27 | 2026-07-18 | 0 | 0 | 557694.54 | Remaining Total Cost | [23 empty] | 99765.36 | 457929.18
|  |  | JDH3-02-008-As Built Drawing Submittals-Z08 |  | 2026-03-28 | 2026-04-16 | 2026-06-27 | 2026-07-18 | 0 | 0 | 557694.54 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Submittals-Z09 |  | 2026-07-14 | 2026-07-20 | 2026-06-27 | 2026-07-04 | 0 | 0 | 154915.27 | Planned Total Cost | [23 empty] | 83137.86 | 71777.41
|  |  | JDH3-02-008-As Built Drawing Submittals-Z09 |  | 2026-07-14 | 2026-07-20 | 2026-06-27 | 2026-07-04 | 0 | 0 | 154915.27 | Remaining Total Cost | [23 empty] | 83137.86 | 71777.41
|  |  | JDH3-02-008-As Built Drawing Submittals-Z09 |  | 2026-07-14 | 2026-07-20 | 2026-06-27 | 2026-07-04 | 0 | 0 | 154915.27 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Submittals-Z10 |  | 2026-07-04 | 2026-07-09 | 2026-06-27 | 2026-07-04 | 0 | 0 | 154915.27 | Planned Total Cost | [23 empty] | 83137.86 | 71777.41
|  |  | JDH3-02-008-As Built Drawing Submittals-Z10 |  | 2026-07-04 | 2026-07-09 | 2026-06-27 | 2026-07-04 | 0 | 0 | 154915.27 | Remaining Total Cost | [23 empty] | 83137.86 | 71777.41
|  |  | JDH3-02-008-As Built Drawing Submittals-Z10 |  | 2026-07-04 | 2026-07-09 | 2026-06-27 | 2026-07-04 | 0 | 0 | 154915.27 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Submittals-Z11 |  | 2026-03-17 | 2026-03-30 | 2026-06-27 | 2026-07-11 | 0 | 0 | 371796.36 | Planned Total Cost | [23 empty] | 99765.36 | 272031
|  |  | JDH3-02-008-As Built Drawing Submittals-Z11 |  | 2026-03-17 | 2026-03-30 | 2026-06-27 | 2026-07-11 | 0 | 0 | 371796.36 | Remaining Total Cost | [23 empty] | 99765.36 | 272031
|  |  | JDH3-02-008-As Built Drawing Submittals-Z11 |  | 2026-03-17 | 2026-03-30 | 2026-06-27 | 2026-07-11 | 0 | 0 | 371796.36 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Submittals-Z12 |  | 2026-03-31 | 2026-04-06 | 2026-07-11 | 2026-07-18 | 0 | 0 | 185898.18 | Planned Total Cost | [24 empty] | 185898.18
|  |  | JDH3-02-008-As Built Drawing Submittals-Z12 |  | 2026-03-31 | 2026-04-06 | 2026-07-11 | 2026-07-18 | 0 | 0 | 185898.18 | Remaining Total Cost | [24 empty] | 185898.18
|  |  | JDH3-02-008-As Built Drawing Submittals-Z12 |  | 2026-03-31 | 2026-04-06 | 2026-07-11 | 2026-07-18 | 0 | 0 | 185898.18 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Submittals-Z13 |  | 2026-07-01 | 2026-07-21 | 2026-06-27 | 2026-07-18 | 0 | 0 | 557694.54 | Planned Total Cost | [23 empty] | 99765.36 | 457929.18
|  |  | JDH3-02-008-As Built Drawing Submittals-Z13 |  | 2026-07-01 | 2026-07-21 | 2026-06-27 | 2026-07-18 | 0 | 0 | 557694.54 | Remaining Total Cost | [23 empty] | 99765.36 | 457929.18
|  |  | JDH3-02-008-As Built Drawing Submittals-Z13 |  | 2026-07-01 | 2026-07-21 | 2026-06-27 | 2026-07-18 | 0 | 0 | 557694.54 | Actual Total Cost
|  |  | JDH3-02-008--As Built Drawing Approvals |  | 2026-01-06 | 2026-07-28 | 2025-11-30 | 2026-10-10 | 0 | 0 | 10534230.43 | Planned Total Cost | [16 empty] | 30983.03 | 154915.15 | [6 empty] | 7697424.21 | 1542335.23 | 867524.84 | 241047.97
|  |  | JDH3-02-008--As Built Drawing Approvals |  | 2026-01-06 | 2026-07-28 | 2025-11-30 | 2026-10-10 | 0 | 0 | 10534230.43 | Remaining Total Cost | [16 empty] | 30983.03 | 154915.15 | [6 empty] | 7697424.21 | 1542335.23 | 867524.84 | 241047.97
|  |  | JDH3-02-008--As Built Drawing Approvals |  | 2026-01-06 | 2026-07-28 | 2025-11-30 | 2026-10-10 | 0 | 0 | 10534230.43 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Approvals-MR |  | 2026-06-28 | 2026-07-11 | 2026-07-04 | 2026-07-18 | 0 | 0 | 1301287.26 | Planned Total Cost | [24 empty] | 1301287.26
|  |  | JDH3-02-008-As Built Drawing Approvals-MR |  | 2026-06-28 | 2026-07-11 | 2026-07-04 | 2026-07-18 | 0 | 0 | 1301287.26 | Remaining Total Cost | [24 empty] | 1301287.26
|  |  | JDH3-02-008-As Built Drawing Approvals-MR |  | 2026-06-28 | 2026-07-11 | 2026-07-04 | 2026-07-18 | 0 | 0 | 1301287.26 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Approvals-Z01 |  | 2026-06-17 | 2026-07-27 | 2026-07-02 | 2026-07-23 | 0 | 0 | 557694.54 | Planned Total Cost | [24 empty] | 557694.54
|  |  | JDH3-02-008-As Built Drawing Approvals-Z01 |  | 2026-06-17 | 2026-07-27 | 2026-07-02 | 2026-07-23 | 0 | 0 | 557694.54 | Remaining Total Cost | [24 empty] | 557694.54
|  |  | JDH3-02-008-As Built Drawing Approvals-Z01 |  | 2026-06-17 | 2026-07-27 | 2026-07-02 | 2026-07-23 | 0 | 0 | 557694.54 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Approvals-Z02 |  | 2026-07-09 | 2026-07-22 | 2026-07-09 | 2026-07-23 | 0 | 0 | 371796.36 | Planned Total Cost | [24 empty] | 371796.36
|  |  | JDH3-02-008-As Built Drawing Approvals-Z02 |  | 2026-07-09 | 2026-07-22 | 2026-07-09 | 2026-07-23 | 0 | 0 | 371796.36 | Remaining Total Cost | [24 empty] | 371796.36
|  |  | JDH3-02-008-As Built Drawing Approvals-Z02 |  | 2026-07-09 | 2026-07-22 | 2026-07-09 | 2026-07-23 | 0 | 0 | 371796.36 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Approvals-Z02-1 |  | 2026-02-05 | 2026-03-25 | 2026-07-04 | 2026-08-22 | 0 | 0 | 1115389.08 | Planned Total Cost | [24 empty] | 533527.78 | 581861.3
|  |  | JDH3-02-008-As Built Drawing Approvals-Z02-1 |  | 2026-02-05 | 2026-03-25 | 2026-07-04 | 2026-08-22 | 0 | 0 | 1115389.08 | Remaining Total Cost | [24 empty] | 533527.78 | 581861.3
|  |  | JDH3-02-008-As Built Drawing Approvals-Z02-1 |  | 2026-02-05 | 2026-03-25 | 2026-07-04 | 2026-08-22 | 0 | 0 | 1115389.08 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Approvals-Z02-2 |  | 2026-03-19 | 2026-05-13 | 2026-08-15 | 2026-10-10 | 0 | 0 | 1301287.26 | Planned Total Cost | [25 empty] | 371796.36 | 688442.93 | 241047.97
|  |  | JDH3-02-008-As Built Drawing Approvals-Z02-2 |  | 2026-03-19 | 2026-05-13 | 2026-08-15 | 2026-10-10 | 0 | 0 | 1301287.26 | Remaining Total Cost | [25 empty] | 371796.36 | 688442.93 | 241047.97
|  |  | JDH3-02-008-As Built Drawing Approvals-Z02-2 |  | 2026-03-19 | 2026-05-13 | 2026-08-15 | 2026-10-10 | 0 | 0 | 1301287.26 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Approvals-Z03 |  | 2026-02-05 | 2026-02-11 | 2026-07-04 | 2026-07-11 | 0 | 0 | 185898.18 | Planned Total Cost | [24 empty] | 185898.18
|  |  | JDH3-02-008-As Built Drawing Approvals-Z03 |  | 2026-02-05 | 2026-02-11 | 2026-07-04 | 2026-07-11 | 0 | 0 | 185898.18 | Remaining Total Cost | [24 empty] | 185898.18
|  |  | JDH3-02-008-As Built Drawing Approvals-Z03 |  | 2026-02-05 | 2026-02-11 | 2026-07-04 | 2026-07-11 | 0 | 0 | 185898.18 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Approvals-Z04 |  | 2026-06-30 | 2026-07-13 | 2026-07-04 | 2026-07-18 | 0 | 0 | 371796.36 | Planned Total Cost | [24 empty] | 371796.36
|  |  | JDH3-02-008-As Built Drawing Approvals-Z04 |  | 2026-06-30 | 2026-07-13 | 2026-07-04 | 2026-07-18 | 0 | 0 | 371796.36 | Remaining Total Cost | [24 empty] | 371796.36
|  |  | JDH3-02-008-As Built Drawing Approvals-Z04 |  | 2026-06-30 | 2026-07-13 | 2026-07-04 | 2026-07-18 | 0 | 0 | 371796.36 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Approvals-Z05 |  | 2026-02-05 | 2026-02-11 | 2026-07-04 | 2026-07-11 | 0 | 0 | 371796.36 | Planned Total Cost | [24 empty] | 371796.36
|  |  | JDH3-02-008-As Built Drawing Approvals-Z05 |  | 2026-02-05 | 2026-02-11 | 2026-07-04 | 2026-07-11 | 0 | 0 | 371796.36 | Remaining Total Cost | [24 empty] | 371796.36
|  |  | JDH3-02-008-As Built Drawing Approvals-Z05 |  | 2026-02-05 | 2026-02-11 | 2026-07-04 | 2026-07-11 | 0 | 0 | 371796.36 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Approvals-Z06 |  | 2026-07-07 | 2026-07-27 | 2026-07-11 | 2026-08-01 | 0 | 0 | 557694.54 | Planned Total Cost | [24 empty] | 533527.78 | 24166.76
|  |  | JDH3-02-008-As Built Drawing Approvals-Z06 |  | 2026-07-07 | 2026-07-27 | 2026-07-11 | 2026-08-01 | 0 | 0 | 557694.54 | Remaining Total Cost | [24 empty] | 533527.78 | 24166.76
|  |  | JDH3-02-008-As Built Drawing Approvals-Z06 |  | 2026-07-07 | 2026-07-27 | 2026-07-11 | 2026-08-01 | 0 | 0 | 557694.54 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Approvals-Z07 |  | 2026-02-05 | 2026-02-16 | 2026-07-04 | 2026-07-15 | 0 | 0 | 557694.54 | Planned Total Cost | [24 empty] | 557694.54
|  |  | JDH3-02-008-As Built Drawing Approvals-Z07 |  | 2026-02-05 | 2026-02-16 | 2026-07-04 | 2026-07-15 | 0 | 0 | 557694.54 | Remaining Total Cost | [24 empty] | 557694.54
|  |  | JDH3-02-008-As Built Drawing Approvals-Z07 |  | 2026-02-05 | 2026-02-16 | 2026-07-04 | 2026-07-15 | 0 | 0 | 557694.54 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Approvals-Z07-1 |  | 2026-02-15 | 2026-04-11 | 2026-07-13 | 2026-09-07 | 0 | 0 | 1115389.08 | Planned Total Cost | [24 empty] | 371796.36 | 564510.81 | 179081.91
|  |  | JDH3-02-008-As Built Drawing Approvals-Z07-1 |  | 2026-02-15 | 2026-04-11 | 2026-07-13 | 2026-09-07 | 0 | 0 | 1115389.08 | Remaining Total Cost | [24 empty] | 371796.36 | 564510.81 | 179081.91
|  |  | JDH3-02-008-As Built Drawing Approvals-Z07-1 |  | 2026-02-15 | 2026-04-11 | 2026-07-13 | 2026-09-07 | 0 | 0 | 1115389.08 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Approvals-Z08 |  | 2026-04-04 | 2026-04-23 | 2026-07-04 | 2026-07-25 | 0 | 0 | 557694.54 | Planned Total Cost | [24 empty] | 557694.54
|  |  | JDH3-02-008-As Built Drawing Approvals-Z08 |  | 2026-04-04 | 2026-04-23 | 2026-07-04 | 2026-07-25 | 0 | 0 | 557694.54 | Remaining Total Cost | [24 empty] | 557694.54
|  |  | JDH3-02-008-As Built Drawing Approvals-Z08 |  | 2026-04-04 | 2026-04-23 | 2026-07-04 | 2026-07-25 | 0 | 0 | 557694.54 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Submittals-Z09 |  | 2026-07-21 | 2026-07-27 | 2026-07-04 | 2026-07-11 | 0 | 0 | 154915.27 | Planned Total Cost | [24 empty] | 154915.27
|  |  | JDH3-02-008-As Built Drawing Submittals-Z09 |  | 2026-07-21 | 2026-07-27 | 2026-07-04 | 2026-07-11 | 0 | 0 | 154915.27 | Remaining Total Cost | [24 empty] | 154915.27
|  |  | JDH3-02-008-As Built Drawing Submittals-Z09 |  | 2026-07-21 | 2026-07-27 | 2026-07-04 | 2026-07-11 | 0 | 0 | 154915.27 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Submittals-Z10 |  | 2026-07-11 | 2026-07-16 | 2026-07-04 | 2026-07-11 | 0 | 0 | 154915.27 | Planned Total Cost | [24 empty] | 154915.27
|  |  | JDH3-02-008-As Built Drawing Submittals-Z10 |  | 2026-07-11 | 2026-07-16 | 2026-07-04 | 2026-07-11 | 0 | 0 | 154915.27 | Remaining Total Cost | [24 empty] | 154915.27
|  |  | JDH3-02-008-As Built Drawing Submittals-Z10 |  | 2026-07-11 | 2026-07-16 | 2026-07-04 | 2026-07-11 | 0 | 0 | 154915.27 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Approvals-Z11 |  | 2026-03-24 | 2026-04-06 | 2026-07-04 | 2026-07-18 | 0 | 0 | 371796.36 | Planned Total Cost | [24 empty] | 371796.36
|  |  | JDH3-02-008-As Built Drawing Approvals-Z11 |  | 2026-03-24 | 2026-04-06 | 2026-07-04 | 2026-07-18 | 0 | 0 | 371796.36 | Remaining Total Cost | [24 empty] | 371796.36
|  |  | JDH3-02-008-As Built Drawing Approvals-Z11 |  | 2026-03-24 | 2026-04-06 | 2026-07-04 | 2026-07-18 | 0 | 0 | 371796.36 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Approvals-Z12 |  | 2026-04-07 | 2026-04-13 | 2026-07-18 | 2026-07-25 | 0 | 0 | 185898.18 | Planned Total Cost | [24 empty] | 185898.18
|  |  | JDH3-02-008-As Built Drawing Approvals-Z12 |  | 2026-04-07 | 2026-04-13 | 2026-07-18 | 2026-07-25 | 0 | 0 | 185898.18 | Remaining Total Cost | [24 empty] | 185898.18
|  |  | JDH3-02-008-As Built Drawing Approvals-Z12 |  | 2026-04-07 | 2026-04-13 | 2026-07-18 | 2026-07-25 | 0 | 0 | 185898.18 | Actual Total Cost
|  |  | JDH3-02-008-As Built Drawing Approvals-Z13 |  | 2026-07-08 | 2026-07-28 | 2026-07-04 | 2026-07-25 | 0 | 0 | 557694.54 | Planned Total Cost | [24 empty] | 557694.54
|  |  | JDH3-02-008-As Built Drawing Approvals-Z13 |  | 2026-07-08 | 2026-07-28 | 2026-07-04 | 2026-07-25 | 0 | 0 | 557694.54 | Remaining Total Cost | [24 empty] | 557694.54
|  |  | JDH3-02-008-As Built Drawing Approvals-Z13 |  | 2026-07-08 | 2026-07-28 | 2026-07-04 | 2026-07-25 | 0 | 0 | 557694.54 | Actual Total Cost
|  |  | JDH3-02-008--Operational Spares |  | 2026-07-09 | 2026-07-14 | 2026-06-15 | 2026-06-21 | 0 | 0 | 185898.18 | Planned Total Cost | [23 empty] | 185898.18
|  |  | JDH3-02-008--Operational Spares |  | 2026-07-09 | 2026-07-14 | 2026-06-15 | 2026-06-21 | 0 | 0 | 185898.18 | Remaining Total Cost | [23 empty] | 185898.18
|  |  | JDH3-02-008--Operational Spares |  | 2026-07-09 | 2026-07-14 | 2026-06-15 | 2026-06-21 | 0 | 0 | 185898.18 | Actual Total Cost
|  |  | JDH3-02-008--Warranties and Guarantees |  | 2026-07-15 | 2026-07-22 | 2026-06-21 | 2026-06-29 | 0 | 0 | 185898.18 | Planned Total Cost | [23 empty] | 185898.18
|  |  | JDH3-02-008--Warranties and Guarantees |  | 2026-07-15 | 2026-07-22 | 2026-06-21 | 2026-06-29 | 0 | 0 | 185898.18 | Remaining Total Cost | [23 empty] | 185898.18
|  |  | JDH3-02-008--Warranties and Guarantees |  | 2026-07-15 | 2026-07-22 | 2026-06-21 | 2026-06-29 | 0 | 0 | 185898.18 | Actual Total Cost
|  |  | JDH3-02-008--Training and Manuals |  | 2026-07-15 | 2026-07-22 | 2026-06-21 | 2026-06-29 | 0 | 0 | 371796.25 | Planned Total Cost | [23 empty] | 371796.25
|  |  | JDH3-02-008--Training and Manuals |  | 2026-07-15 | 2026-07-22 | 2026-06-21 | 2026-06-29 | 0 | 0 | 371796.25 | Remaining Total Cost | [23 empty] | 371796.25
|  |  | JDH3-02-008--Training and Manuals |  | 2026-07-15 | 2026-07-22 | 2026-06-21 | 2026-06-29 | 0 | 0 | 371796.25 | Actual Total Cost
|  |  | JDH3-02-008--Training |  | 2026-07-15 | 2026-07-22 | 2026-06-21 | 2026-06-29 | 0 | 0 | 185898.18 | Planned Total Cost | [23 empty] | 185898.18
|  |  | JDH3-02-008--Training |  | 2026-07-15 | 2026-07-22 | 2026-06-21 | 2026-06-29 | 0 | 0 | 185898.18 | Remaining Total Cost | [23 empty] | 185898.18
|  |  | JDH3-02-008--Training |  | 2026-07-15 | 2026-07-22 | 2026-06-21 | 2026-06-29 | 0 | 0 | 185898.18 | Actual Total Cost
|  |  | JDH3-02-008--Manuals |  | 2026-07-15 | 2026-07-22 | 2026-06-21 | 2026-06-29 | 0 | 0 | 185898.07 | Planned Total Cost | [23 empty] | 185898.07
|  |  | JDH3-02-008--Manuals |  | 2026-07-15 | 2026-07-22 | 2026-06-21 | 2026-06-29 | 0 | 0 | 185898.07 | Remaining Total Cost | [23 empty] | 185898.07
|  |  | JDH3-02-008--Manuals |  | 2026-07-15 | 2026-07-22 | 2026-06-21 | 2026-06-29 | 0 | 0 | 185898.07 | Actual Total Cost
|  |  | JDH3-02-008--Demobilization |  | 2026-07-15 | 2026-07-20 | 2026-06-21 | 2026-06-27 | 0 | 0 | 0 | Planned Total Cost
|  |  | JDH3-02-008--Demobilization |  | 2026-07-15 | 2026-07-20 | 2026-06-21 | 2026-06-27 | 0 | 0 | 0 | Remaining Total Cost
|  |  | JDH3-02-008--Demobilization |  | 2026-07-15 | 2026-07-20 | 2026-06-21 | 2026-06-27 | 0 | 0 | 0 | Actual Total Cost
|  |  | JDH3-02-008--Demobilization of Manpoer |  | 2026-07-15 | 2026-07-18 | 2026-06-21 | 2026-06-24 | 0 | 0 | 0 | Planned Total Cost
|  |  | JDH3-02-008--Demobilization of Manpoer |  | 2026-07-15 | 2026-07-18 | 2026-06-21 | 2026-06-24 | 0 | 0 | 0 | Remaining Total Cost
|  |  | JDH3-02-008--Demobilization of Manpoer |  | 2026-07-15 | 2026-07-18 | 2026-06-21 | 2026-06-24 | 0 | 0 | 0 | Actual Total Cost
|  |  | JDH3-02-008--Removal of Euipment from the Site |  | 2026-07-15 | 2026-07-19 | 2026-06-21 | 2026-06-25 | 0 | 0 | 0 | Planned Total Cost
|  |  | JDH3-02-008--Removal of Euipment from the Site |  | 2026-07-15 | 2026-07-19 | 2026-06-21 | 2026-06-25 | 0 | 0 | 0 | Remaining Total Cost
|  |  | JDH3-02-008--Removal of Euipment from the Site |  | 2026-07-15 | 2026-07-19 | 2026-06-21 | 2026-06-25 | 0 | 0 | 0 | Actual Total Cost
|  |  | JDH3-02-008--Site Clean - up |  | 2026-07-15 | 2026-07-19 | 2026-06-21 | 2026-06-25 | 0 | 0 | 0 | Planned Total Cost
|  |  | JDH3-02-008--Site Clean - up |  | 2026-07-15 | 2026-07-19 | 2026-06-21 | 2026-06-25 | 0 | 0 | 0 | Remaining Total Cost
|  |  | JDH3-02-008--Site Clean - up |  | 2026-07-15 | 2026-07-19 | 2026-06-21 | 2026-06-25 | 0 | 0 | 0 | Actual Total Cost
|  |  | JDH3-02-008--Removal of Site Offices and Structure |  | 2026-07-15 | 2026-07-20 | 2026-06-21 | 2026-06-27 | 0 | 0 | 0 | Planned Total Cost
|  |  | JDH3-02-008--Removal of Site Offices and Structure |  | 2026-07-15 | 2026-07-20 | 2026-06-21 | 2026-06-27 | 0 | 0 | 0 | Remaining Total Cost
|  |  | JDH3-02-008--Removal of Site Offices and Structure |  | 2026-07-15 | 2026-07-20 | 2026-06-21 | 2026-06-27 | 0 | 0 | 0 | Actual Total Cost
|  |  | JDH3-02-008--Restoration of Ground Surfaces |  | 2026-07-15 | 2026-07-20 | 2026-06-21 | 2026-06-27 | 0 | 0 | 0 | Planned Total Cost
|  |  | JDH3-02-008--Restoration of Ground Surfaces |  | 2026-07-15 | 2026-07-20 | 2026-06-21 | 2026-06-27 | 0 | 0 | 0 | Remaining Total Cost
|  |  | JDH3-02-008--Restoration of Ground Surfaces |  | 2026-07-15 | 2026-07-20 | 2026-06-21 | 2026-06-27 | 0 | 0 | 0 | Actual Total Cost

## Physical-Chart Data
| Baseline Plan |  |  | Revised / Recovery Plan |  |  | Earned Effort % |  |  | Forecast |  |  | Achieved/Fcst vs Plan
Week | Monthly Effort | Cum Effort | Plan Wt.% | Monthly Effort | Cum Effort | Plan Wt.% | Monthly Effort | Cum Effort | Achieved Wt.% | Monthly Effort | Cum Effort | Wt.% | Monthly Effort | Cum Effort | Wt.%
2024-07-29 |  |  | 0% |  |  | 0% |  | 0 | 0% |  |  |  | 0 | 0 |  |  | Actuals thru previous month
2024-08-31 | 4.02 | 4.02 | 0.005794% | 2.3317 | 2.3317 | 0.004853% | 2.3317 | 2.3317 | 0.004853% |  |  |  | 2.3317 | 2.3317 | [9 empty] | 3
2024-09-30 | 131.65 | 135.67 | 0.1955% | 1.7488 | 4.0805 | 0.008493% | 1.7488 | 4.0805 | 0.008493% |  |  |  | 1.7488 | 4.0805 | [9 empty] | 100
2024-10-31 | 466.88 | 602.55 | 0.8684% | 58.2929 | 62.3734 | 0.1298% | 58.2929 | 62.3734 | 0.1298% |  |  |  | 58.2929 | 62.3734 | [9 empty] | 359
2024-11-30 | 1347.95 | 1950.5 | 2.811% | 209.2715 | 271.6449 | 0.5654% | 209.2715 | 271.6449 | 0.5654% |  |  |  | 209.2715 | 271.6449 |  |  | Forecast current and future months | [6 empty] | 945
2024-12-31 | 2684.6 | 4635.1 | 6.68% | 550.8678 | 822.5127 | 1.712% | 550.8678 | 822.5127 | 1.712% |  |  |  | 550.8678 | 822.5127 | [9 empty] | 1981
2025-01-31 | 2611.78 | 7246.88 | 10.44% | 1154.7822 | 1977.2948 | 4.116% | 1154.7822 | 1977.2948 | 4.116% |  |  |  | 1154.7822 | 1977.2948 | [9 empty] | 2123
2025-02-28 | 2680.2 | 9927.08 | 14.31% | 1237.5581 | 3214.8529 | 6.691% | 1237.5581 | 3214.8529 | 6.691% |  |  |  | 1237.5581 | 3214.8529 | [9 empty] | 2613
2025-03-31 | 4168.9 | 14095.98 | 20.32% | 1523.1932 | 4738.0461 | 9.862% | 1523.1932 | 4738.0461 | 9.862% |  |  |  | 1523.1932 | 4738.0461 | [9 empty] | 2272
2025-04-30 | 3794.72 | 17890.7 | 25.78% | 1324.4145 | 6062.4606 | 12.62% | 1324.4145 | 6062.4606 | 12.62% |  |  |  | 1324.4145 | 6062.4606 | [9 empty] | 2937
2025-05-31 | 4328.67 | 22219.37 | 32.02% | 1712.0622 | 7774.5227 | 16.18% | 1712.0622 | 7774.5227 | 16.18% |  |  |  | 1712.0622 | 7774.5227 | [9 empty] | 2959
2025-06-30 | 4661.68 | 26881.05 | 38.74% | 1724.8866 | 9499.4094 | 19.77% | 1724.8866 | 9499.4094 | 19.77% |  |  |  | 1724.8866 | 9499.4094 | [9 empty] | 3683
2025-07-31 | 5844.81 | 32725.86 | 47.17% | 2146.9271 | 11646.3365 | 24.24% | 2146.9271 | 11646.3365 | 24.24% |  |  |  | 2146.9271 | 11646.3365 | [9 empty] | 2704
2025-08-31 | 4234.17 | 36960.03 | 53.27% | 1576.2397 | 13222.5763 | 27.52% | 1576.2397 | 13222.5763 | 27.52% |  |  |  | 1576.2397 | 13222.5763 | [9 empty] | 3055
2025-09-30 | 4243.23 | 41203.26 | 59.38% | 1780.8478 | 15003.424 | 31.23% | 1780.8478 | 15003.424 | 31.23% |  |  |  | 1780.8478 | 15003.424 | [9 empty] | 2782
2025-10-31 | 4653.6 | 45856.86 | 66.09% | 1621.7082 | 16625.1322 | 34.6% | 1621.7082 | 16625.1322 | 34.6% |  |  |  | 1621.7082 | 16625.1322 | [9 empty] | 2920
2025-11-30 | 5774.55 | 51631.41 | 74.41% | 1702.1524 | 18327.2846 | 38.15% | 1702.1524 | 18327.2846 | 38.15% |  |  |  | 1702.1524 | 18327.2846 | [9 empty] | 5479
2025-12-31 | 3021.68 | 54653.09 | 78.77% | 3193.8674 | 21521.1521 | 44.79% | 3193.8674 | 21521.1521 | 44.79% |  |  |  | 3193.8674 | 21521.1521 | [9 empty] | 7265
2026-01-31 | 1657.76 | 56310.85 | 81.16% | 4234.9785 | 25756.1306 | 53.61% | 4234.9785 | 25756.1306 | 53.61% |  |  |  | 4234.9785 | 25756.1306 |  |  |  | Extended Duration | [5 empty] | 2641
2026-02-28 | 1470.56 | 57781.41 | 83.28% | 1539.5152 | 27295.6458 | 56.81% | 1539.5152 | 27295.6458 | 56.81% |  |  |  | 1539.5152 | 27295.6458 | [9 empty] | 2619
2026-03-31 | 4979.21 | 62760.62 | 90.45% | 1526.6908 | 28822.3366 | 59.99% | 1526.6908 | 28822.3366 | 59.99% |  |  |  | 1526.6908 | 28822.3366 | [9 empty] | 3491
2026-04-30 | 2547.84 | 65308.46 | 94.13% | 2035.0048 | 30857.3414 | 64.23% | 2035.0048 | 30857.3414 | 64.23% |  |  |  | 2035.0048 | 30857.3414 | [9 empty] | 3925
2026-05-31 | 2116.96 | 67425.42 | 97.18% | 2287.9959 | 33145.3373 | 68.99% | 2287.9959 | 33145.3373 | 68.99% |  |  |  | 2287.9959 | 33145.3373 | [9 empty] | 5223
2026-06-30 | 1859.6 | 69285.02 | 99.86% | 3044.6376 | 36189.9749 | 75.33% | 1988.3872 | 35133.7245 | 73.13% |  |  |  | 1988.3872 | 35133.7245 | [9 empty] | 9040
2026-07-31 | 99.48 | 69384.5 | 100% | 5269.6773 | 41459.6522 | 86.29% | 2979.2755 | 38113 | 79.33% |  |  |  | 2979.2755 | 38113 | [9 empty] | 9140
2026-08-31 |  |  |  | 5327.9702 | 46787.6224 | 97.38% | 2780 | 40893 | 85.11% |  |  |  | 2780 | 40893 | [9 empty] | 2157
2026-09-30 |  |  |  | 1257.3776 | 48045 | 100% | 7152 | 48045 | 100% |  |  |  | 7152 | 48045 | 100%
2026-10-31
2026-11-30
2026-12-31
2027-01-31
2027-02-28
2027-03-31
2027-04-30
2027-05-31
UPDATE ONLY YELLOW PORTION FROM PRIMAVERA EXPORT, IF NEEDED, EXTEND YELLOW PORTION BASED ON SCHEDULE.
|  |  |  | Activity ID | Activity Name | Resource ID Name | Earned Value Units | Actual Units | Start | Finish | Spreadsheet Field | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01
|  |  |  | Total |  |  | 34794 | 34795 | 28-Sep-24 A | 2026-07-20 | Actual Units | 3 | 87 | 352 | 1158 | 2762 | 2643 | 2837 | 3206 | 3712 | 4013 | 4448 | 4750 | 4649 | 173
|  |  |  | Total |  |  | 34794 | 1995-04-06 | 28-Sep-24 A | 2026-07-20 | Remaining Early Units | 2025-10-01: 8962; 2025-11-01: 7865; 2025-12-01: 5948; 2026-01-01: 5166; 2026-02-01: 4396; 2026-03-01: 4900; 2026-04-01: 2336; 2026-05-01: 1327; 2026-06-01: 722; 2026-07-01: 269
|  |  |  | Unskilled Labor |  | MD-JDH3-LR-01.Unskilled Labor | 13549 | 1937-02-03 | 28-Oct-24 A | 2026-07-20 | Actual Units | 2024-10-01: 2; 2024-11-01: 42; 2024-12-01: 316; 2025-01-01: 1032; 2025-02-01: 1043; 2025-03-01: 1125; 2025-04-01: 1218; 2025-05-01: 1333; 2025-06-01: 1477; 2025-07-01: 1597; 2025-08-01: 2211; 2025-09-01: 2073; 2025-10-01: 79
|  |  |  | Unskilled Labor |  | MD-JDH3-LR-01.Unskilled Labor | 13549 | 1937-02-03 | 28-Oct-24 A | 2026-07-20 | Remaining Early Units | 2025-10-01: 4371; 2025-11-01: 3751; 2025-12-01: 2704; 2026-01-01: 2262; 2026-02-01: 1860; 2026-03-01: 2424; 2026-04-01: 1209; 2026-05-01: 646; 2026-06-01: 343; 2026-07-01: 130
|  |  |  | Electrician |  | MD-JDH3-LR-02.Electrician | 44 | 1900-02-12 | 19-Jul-25 A | 2026-07-11 | Actual Units | 2025-07-01: 1; 2025-08-01: 16; 2025-09-01: 25; 2025-10-01: 3
|  |  |  | Electrician |  | MD-JDH3-LR-02.Electrician | 44 | 1900-02-12 | 19-Jul-25 A | 2026-07-11 | Remaining Early Units | 2025-10-01: 260; 2025-11-01: 87; 2025-12-01: 47; 2026-01-01: 55; 2026-02-01: 22; 2026-03-01: 10; 2026-04-01: 15; 2026-05-01: 3; 2026-06-01: 22; 2026-07-01: 32
|  |  |  | Equipment Opreator |  | MD-JDH3-LR-04.Equipment Opreator | 13154 | 1936-01-05 | 28-Sep-24 A | 2026-07-20 | Actual Units | 2 | 74 | 256 | 598 | 960 | 849 | 869 | 1146 | 1505 | 1705 | 1971 | 1668 | 1496 | 53
|  |  |  | Equipment Opreator |  | MD-JDH3-LR-04.Equipment Opreator | 13154 | 1936-01-05 | 28-Sep-24 A | 2026-07-20 | Remaining Early Units | 2025-10-01: 2530; 2025-11-01: 2742; 2025-12-01: 1642; 2026-01-01: 1160; 2026-02-01: 1068; 2026-03-01: 1312; 2026-04-01: 549; 2026-05-01: 352; 2026-06-01: 263; 2026-07-01: 82
|  |  |  | Mason |  | MD-JDH3-LR-03.Mason | 1378 | 1903-10-09 | 28-Oct-24 A | 2026-05-25 | Actual Units | 2024-10-01: 1; 2024-11-01: 18; 2024-12-01: 72; 2025-01-01: 101; 2025-02-01: 98; 2025-03-01: 90; 2025-04-01: 101; 2025-05-01: 129; 2025-06-01: 149; 2025-07-01: 223; 2025-08-01: 218; 2025-09-01: 172; 2025-10-01: 6
|  |  |  | Mason |  | MD-JDH3-LR-03.Mason | 1378 | 1903-10-09 | 28-Oct-24 A | 2026-05-25 | Remaining Early Units | 2025-10-01: 129; 2025-11-01: 242; 2025-12-01: 117; 2026-01-01: 51; 2026-02-01: 63; 2026-03-01: 104; 2026-04-01: 56; 2026-05-01: 39
|  |  |  | Carpenter |  | MD-JDH3-LR-05.Carpenter | 2402 | 1906-07-29 | 03-Dec-24 A | 2026-06-09 | Actual Units | 2024-12-01: 29; 2025-01-01: 236; 2025-02-01: 254; 2025-03-01: 305; 2025-04-01: 290; 2025-05-01: 283; 2025-06-01: 239; 2025-07-01: 220; 2025-08-01: 211; 2025-09-01: 322; 2025-10-01: 11
|  |  |  | Carpenter |  | MD-JDH3-LR-05.Carpenter | 2402 | 1906-07-29 | 03-Dec-24 A | 2026-06-09 | Remaining Early Units | 2025-10-01: 371; 2025-11-01: 172; 2025-12-01: 530; 2026-01-01: 688; 2026-02-01: 584; 2026-03-01: 305; 2026-04-01: 151; 2026-05-01: 99; 2026-06-01: 1
|  |  |  | Steel Fixer |  | MD-JDH3-LR-06.Steel Fixer | 2177 | 1905-12-16 | 11-Dec-24 A | 2026-05-12 | Actual Units | 2024-12-01: 25; 2025-01-01: 212; 2025-02-01: 239; 2025-03-01: 292; 2025-04-01: 280; 2025-05-01: 251; 2025-06-01: 193; 2025-07-01: 211; 2025-08-01: 164; 2025-09-01: 299; 2025-10-01: 11
|  |  |  | Steel Fixer |  | MD-JDH3-LR-06.Steel Fixer | 2177 | 1905-12-16 | 11-Dec-24 A | 2026-05-12 | Remaining Early Units | 2025-10-01: 323; 2025-11-01: 113; 2025-12-01: 472; 2026-01-01: 647; 2026-02-01: 560; 2026-03-01: 269; 2026-04-01: 143; 2026-05-01: 90
|  |  |  | Skilled labor |  | MD-JDH3-LR-07.Skilled labor | 878 | 1902-05-27 | 28-Sep-24 A | 2026-07-11 | Actual Units | 0 | 10 | 36 | 102 | 137 | 76 | 57 | 49 | 89 | 106 | 100 | 52 | 61 | 2
|  |  |  | Skilled labor |  | MD-JDH3-LR-07.Skilled labor | 878 | 1902-05-27 | 28-Sep-24 A | 2026-07-11 | Remaining Early Units | 2025-10-01: 338; 2025-11-01: 216; 2025-12-01: 113; 2026-01-01: 96; 2026-02-01: 57; 2026-03-01: 106; 2026-04-01: 17; 2026-05-01: 6; 2026-06-01: 32; 2026-07-01: 25
|  |  |  | Plumber |  | MD-JDH3-LR-08.Plumber | 1212 | 1903-04-26 | 01-Dec-24 A | 2026-06-27 | Actual Units | 2024-12-01: 14; 2025-01-01: 85; 2025-02-01: 84; 2025-03-01: 98; 2025-04-01: 122; 2025-05-01: 122; 2025-06-01: 143; 2025-07-01: 125; 2025-08-01: 211; 2025-09-01: 201; 2025-10-01: 7
|  |  |  | Plumber |  | MD-JDH3-LR-08.Plumber | 1212 | 1903-04-26 | 01-Dec-24 A | 2026-06-27 | Remaining Early Units | 2025-10-01: 641; 2025-11-01: 541; 2025-12-01: 323; 2026-01-01: 207; 2026-02-01: 183; 2026-03-01: 369; 2026-04-01: 197; 2026-05-01: 93; 2026-06-01: 61
|  |  |  | Activity ID | Activity Name | Resource ID Name | Earned Value Units | Actual Units | Start | Finish | Spreadsheet Field | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-07-01
|  |  |  | Total |  |  | 0 | 0 | 2024-08-17 | 2026-07-08 | Budgeted Units | 48 | 1704 | 2144 | 1610 | 2965 | 3838 | 2917 | 2283 | 1652 | 893 | 1007 | 1019 | 2119 | 4111 | 6018 | 4475 | 4721 | 6625 | 7941 | 6756 | 5020 | 4130 | 2550 | 143 | 1270
|  |  |  | Total |  |  | 0 | 0 | 2024-08-17 | 2026-07-08 | Cum Budgeted Units | 1900-02-16 | 1904-10-17 | 1910-08-31 | 1915-01-27 | 8471 | 1230900% | 1522600% | 17510 | 19161 | 20054 | 2106100% | 22079 | 24199 | 28309 | 34327 | 38802 | 43523 | 50147 | 58088 | 64844 | 69864 | 73994 | 76543 | 76686 | 6
|  |  |  | Modon |  |  | 0 | 0 | 2024-08-17 | 2026-07-08 | Budgeted Units | 1900-02-16 | 1904-08-30 | 1905-11-13 | 1904-05-28 | 2965 | 383800% | 291700% | 2283 | 1652 | 893 | 100700% | 1019 | 2119 | 4111 | 6018 | 4475 | 4721 | 6625 | 7941 | 6756 | 5020 | 4130 | 2550 | 143
|  |  |  | Modon |  |  | 0 | 0 | 2024-08-17 | 2026-07-08 | Cum Budgeted Units | 1900-02-16 | 1904-10-17 | 1910-08-31 | 1915-01-27 | 8471 | 1230900% | 1522600% | 17510 | 19161 | 20054 | 2106100% | 22079 | 24199 | 28309 | 34327 | 38802 | 43523 | 50147 | 58088 | 64844 | 69864 | 73994 | 76543 | 76686
|  |  |  | Unskilled Labor |  | MD-JDH3-LR-01.Unskilled Labor | 0 | 0 | 2024-08-17 | 2026-07-08 | Budgeted Units | 1900-01-16 | 1901-12-18 | 1902-09-19 | 1901-12-20 | 1351 | 169700% | 140300% | 989 | 716 | 290 | 37500% | 360 | 762 | 1625 | 2884 | 1843 | 1921 | 2353 | 3413 | 3118 | 2350 | 2059 | 1241 | 49 | 4
|  |  |  | Unskilled Labor |  | MD-JDH3-LR-01.Unskilled Labor | 0 | 0 | 2024-08-17 | 2026-07-08 | Cum Budgeted Units | 1900-01-16 | 1902-01-04 | 1904-09-24 | 1906-09-13 | 3799 | 549600% | 689900% | 7888 | 8604 | 8894 | 926900% | 9630 | 10392 | 12017 | 14901 | 16744 | 18665 | 21019 | 24432 | 27550 | 29900 | 31959 | 33200 | 33249 | 4
|  |  |  | Electrician |  | MD-JDH3-LR-02.Electrician | 0 | 0 | 2025-01-01 | 2026-06-30 | Budgeted Units | 2025-01-01: 7600%; 2025-02-01: 700%; 2025-03-01: 28; 2025-04-01: 76; 2025-05-01: 12; 2025-10-01: 2; 2026-01-01: 163; 2026-02-01: 93; 2026-03-01: 48; 2026-04-01: 0; 2026-05-01: 11; 2026-06-01: 80; 2026-07-01: 0
|  |  |  | Electrician |  | MD-JDH3-LR-02.Electrician | 0 | 0 | 2025-01-01 | 2026-06-30 | Cum Budgeted Units | [5 empty] | 7600% | 8300% | 111 | 187 | 199 | 19900% | 199 | 199 | 199 | 201 | 201 | 201 | 364 | 457 | 505 | 505 | 516 | 596 | 596
|  |  |  | Equipment Opreator |  | MD-JDH3-LR-04.Equipment Opreator | 0 | 0 | 2024-08-17 | 2026-07-08 | Budgeted Units | 1900-01-27 | 808 | 1901-11-10 | 1901-05-05 | 1120 | 145900% | 98500% | 585 | 579 | 424 | 41400% | 343 | 951 | 1836 | 1666 | 948 | 1331 | 2168 | 2485 | 1956 | 1359 | 1242 | 903 | 94 | 1257
|  |  |  | Equipment Opreator |  | MD-JDH3-LR-04.Equipment Opreator | 0 | 0 | 2024-08-17 | 2026-07-08 | Cum Budgeted Units | 1900-01-27 | 836 | 1904-02-24 | 1905-06-30 | 3128 | 458700% | 557200% | 6157 | 6736 | 7160 | 757400% | 7917 | 8868 | 10704 | 12370 | 13318 | 14648 | 16816 | 19301 | 21256 | 22616 | 23858 | 24760 | 24854
|  |  |  | Mason |  | MD-JDH3-LR-03.Mason | 0 | 0 | 2024-10-03 | 2026-06-09 | Budgeted Units |  |  | 124 | 56 | 46 | 11300% | 4900% | 39 | 33 | 24 | 3900% | 84 | 100 | 152 | 379 | 161 | 53 | 69 | 152 | 312 | 124 | 52 | 15
|  |  |  | Mason |  | MD-JDH3-LR-03.Mason | 0 | 0 | 2024-10-03 | 2026-06-09 | Cum Budgeted Units |  |  | 124 | 180 | 226 | 33900% | 38800% | 427 | 460 | 484 | 52300% | 607 | 708 | 860 | 1239 | 1400 | 1453 | 1522 | 1674 | 1986 | 2110 | 2163 | 2178 | 2178
|  |  |  | Carpenter |  | MD-JDH3-LR-05.Carpenter | 0 | 0 | 2024-09-07 | 2026-06-20 | Budgeted Units |  | 30 | 122 | 103 | 68 | 9800% | 12000% | 231 | 50 | 22 | 6400% | 108 | 94 | 143 | 415 | 690 | 582 | 730 | 519 | 450 | 457 | 192 | 17
|  |  |  | Carpenter |  | MD-JDH3-LR-05.Carpenter | 0 | 0 | 2024-09-07 | 2026-06-20 | Cum Budgeted Units |  | 30 | 151 | 255 | 323 | 42000% | 54000% | 1902-02-09 | 1902-03-31 | 1902-04-22 | 1902-06-26 | 1902-10-11 | 1903-01-14 | 1903-06-06 | 1904-07-25 | 1906-06-15 | 1908-01-18 | 1910-01-17 | 1911-06-20 | 1912-09-11 | 1913-12-12 | 1914-06-22 | 1914-07-08 | 1914-07-08
|  |  |  | Steel Fixer |  | MD-JDH3-LR-06.Steel Fixer | 0 | 0 | 2024-10-05 | 2026-05-24 | Budgeted Units |  |  | 1900-04-14 | 1900-04-08 | 38 | 7800% | 8400% | 226 | 47 | 18 | 44 | 108 | 83 | 130 | 361 | 656 | 537 | 703 | 490 | 416 | 420 | 151
|  |  |  | Steel Fixer |  | MD-JDH3-LR-06.Steel Fixer | 0 | 0 | 2024-10-05 | 2026-05-24 | Cum Budgeted Units |  |  | 1900-04-14 | 1900-07-22 | 241 | 32000% | 40400% | 630 | 677 | 695 | 739 | 847 | 930 | 1060 | 1421 | 2077 | 2614 | 3317 | 3807 | 4223 | 4643 | 4794 | 4794 | 4794
|  |  |  | Skilled labor |  | MD-JDH3-LR-07.Skilled labor | 0 | 0 | 2024-08-26 | 2026-06-30 | Budgeted Units | 1 | 31 | 38 | 38 | 77 | 130 | 59 | 39 | 96 | 92 | 37 | 11 | 32 | 39 | 56 | 57 | 89 | 255 | 390 | 147 | 36 | 46 | 89
|  |  |  | Skilled labor |  | MD-JDH3-LR-07.Skilled labor | 0 | 0 | 2024-08-26 | 2026-06-30 | Cum Budgeted Units | 1 | 32 | 70 | 108 | 185 | 315 | 374 | 413 | 509 | 601 | 638 | 650 | 682 | 721 | 777 | 834 | 923 | 1178 | 1568 | 1715 | 1751 | 1796 | 1885 | 1885
|  |  |  | Plumber |  | MD-JDH3-LR-08.Plumber | 0 | 0 | 2024-08-28 | 2026-06-29 | Budgeted Units | 2 | 117 | 82 | 103 | 266 | 188 | 210 | 147 | 53 | 10 | 33 | 5 | 95 | 186 | 254 | 120 | 208 | 184 | 399 | 309 | 274 | 377 | 204
|  |  |  | Plumber |  | MD-JDH3-LR-08.Plumber | 0 | 0 | 2024-08-28 | 2026-06-29 | Cum Budgeted Units | 2 | 119 | 200 | 303 | 569 | 757 | 967 | 1114 | 1167 | 1177 | 1210 | 1215 | 1310 | 1496 | 1750 | 1870 | 2078 | 2262 | 2661 | 2970 | 3244 | 3622 | 3826 | 3826
692
| 692 | 8289
| 8289 | 17069
| 17069 | 12673
| 12673 | 22378
| 22378 | 19279
| 19279 | 26857
| 26857 | 29321
| 29321 | 29694
| 29694 | 40143
| 40143 | 39622
| 39622 | 47317
| 47317 | 33503
| 33503 | 21239
| 21239 | 30047
| 30047 | 22959
| 22959 | 11248
| 11248 | 11259
| 11259 | 8709
| 8709 | 5699
| 5699 | 4174
| 4174 | 2426
| 2426 | 1331
| 1331 | 1543
| 1543 | 228
| 228 | 44864
| 44864 | 31640
| 31640 | 21322
| 21322 | 31188
| 31188 | 19066
| 19066 | 10621
| 10621 | 11135
| 11135 | 9894
| 9894 | 7184
| 7184 | 4261
| 4261 | 2523
| 2523 | 1305
| 1305 | 1496
| 1496 | 102
102

## Testing (hidden)
Testing and Commissioning
Item | Planned Start Date | Planned Finish Date | Forecast Start Date | Forecast Finish Date | Actual Start Date | Actual Finish Date | % Completed | Open Comments | Closed Comments
Mechanical System | 2025-01-27 | 2025-12-02 | 2025-03-22 | 2026-01-25 |  |  | 0% | 0 | 0
Electrical System | 2025-03-13 | 2025-08-06 | 2025-04-13 | 2025-09-29 |  |  | 0% | 0 | 0
Fire System | [6 empty] | 0% | 0 | 0
Other Testing (Manhole Testing) | [6 empty] | 0% | 0 | 0
Total | [6 empty] | 0% | 0 | 0

## Codes (hidden)
Status List
| Approved |  | Y
| Pending |  | N | [5 empty] | (Manhours)
| Potential | [7 empty] | (Mandays)
| Phase | Stage |  | Stage |  | Status |  | Score
[8 empty] | Low | Contractor | Active
| Launch | LOA |  | LOA |  | Active |  | Medium | CM | Expired
| Launch | Kick-off Meeting |  | Kick-off Meeting |  | On Hold |  | High | PgM | Occurred
| Launch | Site Handover |  |  |  | Terminated |  |  | Modon | Pending
| Launch | Mobilization |  | Mobilization | Initial staff and equipment in place, ready to start production | Terminated, Closed |  |  | Other
| Execution | Construction |  | Execution | Tender Documents Issued | Substantial Complete | Initial Handover done at site
| Execution | T&C |  |  | Responses to the OCS completed | Complete | Initial Handover Signed
| Execution | Initial Handover |  | Closeout | Design close-out process complete | Closed | Final Handover done at Site
Warranty Period
Final Handover
Project Status Score
Elements |  |  | Max | Score | Planned | Actual | Remarks
SPI (Physical Effort) |  |  | 100% | 98.98% | No Entry Required
SPI (Cost) |  |  | 100% | 98.76% | No Entry Required
On Schedule -Active |  |  | 100% | 12127% | No Entry Required |  |  |  | 0.6
Manpower Availability |  |  | 100% | 64.62% | No Entry Required
Major Equipment Availability |  |  | 100% | 80.84% | No Entry Required
Billing % Compared to Planned |  |  | 100% | 0% | No Entry Required
Safety Score |  |  | 100% | #DIV/0! | No Entry Required
Quality Score |  |  | 100% | #DIV/0! | No Entry Required

## SOURCE (hidden)
تحديث مستهدفات حتى نهاية شهر يناير
# | القطاع | المبادرة | Project ID | اسم المشروع | مدير المشروع | المقاول | بداية المشروع | نهاية المشروع التعاقدية | مدة المشروع (أشهر) | قيمة المشروع | نسبة المدة المنقضية | قيمة الدفعة المقدمة | Mobilization المخطط | Mobilization المنفذ | Procurement (Long Lead Items) توريد المواد طويلة الأجل (المخطط) | Procurement (Long Lead Items) توريد المواد طويلة الأجل (المنفذ) | Civil Work الأعمال المدنيه (المخطط) | Civil Work الأعمال المدنيه (المنفذ) | Mechnical Work أعمال الميكانيكل (المخطط) | Mechnical Work أعمال الميكانيكل (المنفذ) | Electrical Work أعمال الكهرباء (المخطط) | Electrical Work أعمال الكهرباء (المنفذ) | تأثير التأخير (إن وجد) على المبادرات في الربع الاول 2025 | نسبة الانجاز المستهدفة بنهاية Q2 2025 | نسبة الانجاز المحققة بنهاية Q2 2025 | مجموع المبالغ المفوترة المستهدفة بنهاية Q2 2025 | مجموع المبالغ المفوترة المحققة بنهاية Q2 2025 | نهاية المشروع المتوقعة | قيمة الوفر | اسباب الوفر | مقترحات استخدام الوفر | 2026-10-11
1 | القطاع الأوسط | NIS | SUD1-02-010 | تطوير شبكات البنية التحتية بالمنطقة الصناعية بسدير بمساحة 3.6كم مربع | زياد الشباط | شركة الأومير للتجارة والمقاولات | 2024-02-21 | 2026-02-20 | 24.3333 | 299993709 | 100% | 29999370.9 | تم الأنتهاء |  | توريد حنفيات الحريق للمنطقة ( D ) توريد الكمية المتبقى من كوابل الجهد المتوسط ( 13,500 م ط ) و كذلك محطات الجهد المتوسط أستكمال توريد كاميرات المراقبة للمنطقة ( F , D ) توريد قطع السايفون لأحواض التبخير أستكمال توريد أعمدة الأنارة للمشروع (435) عمود لزونات ( F,D ) توريد كنترولر شبكة الرى أستكمال توريد كوابل إنارة الشوارع للمنطقة ( D ) توفير الكميات المتبقية من قطع شبكتي المياة والري |  | الأنتهاء من أعمال ردميات الطرق بالكامل للمنطقتين ( D,F ) الأنتهاء من أعمال الأسفلت للطبقة الأولى للمنطقتين ( B,F ) أعمال أسفلت الطبقة الثانية للمنطقة ( B ) أعمال دهانات الطرق و لوحات الطرق إنهاء كافة الأعمال المدنية الخاصة بأحواض التبخير أنهاء أعمال التشطيبات الداخلية لكافة مناهل الصرف الصحى و صرف السيول و كافة المناهل الخاصة بالأعمال الكهربية و أحواض تجميع مياة الأمطار للمنطقة ( B ) |  | الأنتهاء من أعمال شبكات الصرف الصحي و صرف الامطار للمناطق ( F,D ) شامل أحواض تجميع مياة الأمطار إنهاء أعمال شبكتي المياة والرى للمنطقتان ( B,F ) إنهاء أعمال الربط على الشبكات القائمة لكافة نقاط الربط للمنطقة ( B ) |  | الأنتهاء من أعمال الجهد المتوسط و إنارة الشوارع و شبكات الأتصالات و أنظمة المراقبة للمنطقة ( B ) الأنتهاء من شبكة الجهد المتوسط للمنطقة و إنارة الشوارع و أعمال إنارة الشوارع شبكات الأتصالات و أنظمة المراقبة للمنطقة ( F ) |  | لا يوجد | 60% |  | 179996225.4 |  | 2025-12-30 | 13000000 | الحصر الفعلي للمشروع | مقترح تطوير البحيرة أو تطوير مساحت اضافية
2 | القطاع الأوسط | مدن | SUD1-03-010 | مشروع تأهيل الطريق الرابط في مدينة سدير للصناعة والأعمال | زياد الشباط | Construction Era Contracting | 2024-04-09 | 2024-12-03 | 3 | 5999425 | 100% | 0 | سيتم الانتهاء من أعمال تجهيز الموقع |  | توريد فواصل التمدد وعيون القطط و توريد أحواض تجميع مياة الأمطار |  | إنهاء أعمال فواصل التمدد وكذلك عيون القطط الأنتهاء من معالجة كافة أماكن الهبوطات تركيب أحواض تجميع مياة الأمطار شامل توصيلاتها أعمال دهانات الطرق الأنتهاء من تركيب صبات الحواجز الخرسانية |  | إنهاء أعمال تصريف مياة الأمطارالموجودة داخل نطاق العمل |  | لا يوجد |  | لا يوجد | 100% |  | 4766997 |  | 2025-02-15 | 0 | - | -
3 | القطاع الأوسط | NIS | SUD1-05-016 | انشاء 40 مصنع جاهز 900م2 في المدينة الصناعية بسدير | زياد الشباط | شركة لبنة البناء للتجارة و المقاولات | 2024-10-24 | 2025-12-23 | 14 | 87953031 | 100% | 8795303.1 | تم الأنتهاء |  | توريد 75 % من الهيكل المعدني للمصانع توريد نسبة 50 % من بند جدران السيبوريكس توريد أبواب المصانع التعاقد و البدء بإجراءات توريد مضخات الحريق توريد أعمدة الأنارة التعاقد والبدء بتوريد وحدات التكيفات توريد نسبة 50% من مراوح الشفط للمصانع |  | الأنتهاء من أعمال الردم لكامل المشروع حتى المناسيب التصميمة الأنتهاء من القواعد المسلحة ورقابي الأعمدة لكافة المصانع الأنتهاء من أعمال الردم داخل المبانى الانتهاء من أعمال الميد و الأرضيات الخرسانية البدء فى تركيب الهيكل المعدني بنسبة 25% من المشروع البدء بأعمال السيبوركس للجدران |  | الأنتهاء من أعمال التأسيس لكافة الأعمال الميكانيكية للمصانع بمرحلة القواعد و أسفل صبة الأرضيات بالمصانع بدء أعمال البنية التحتية للشبكات الميكانيكية بالموقع العام |  | الأنتهاء من أعمال التأسيس لكافة الأعمال الكهربية للمصانع بمرحلة القواعد و أسفل صبة الأرضيات بالمصانع |  | لا يوجد | 45% |  | 39578863.95 |  | 2025-08-23 | 10000000 | الكميات الفعلية لأعمال الردم أقل من جدول الكميات المعتمد | سيتم تنفيذ 4 مصانع تقريبا اضافية
4 | القطاع الأوسط | NIS | HAL1-02-005 | مشروع تنفيذ البنية تحتية للتوسعة الشرقية لمدينة حائل الصناعية | عبدالعزيز المسلم | شركة شبه الجزيرة للمقاولات | 2024-01-07 | 2026-01-06 | 24.3333 | 45093675 | 100% | 4509367.5 | تم الأنتهاء |  | لايوجد |  | إنهاء أعمال المصبات الخرسانية يتم الانتهاء من كامل أعمال شبكة الصرف الصحي في المشروع يتم الانتهاء من كامل أعمال شبكة تصريف مياه الامطار في المشروع الانتهاء من تمديد شبكة مياه الشرب لكامل المشروع الانتهاء من تمديد شبكة المياه المعالجة لكامل المشروع الانتهاء من أعمال البردورات لكامل المشروع الانتهاء من اعمال الطبقة الاسفلتية السطحية لكامل المشروع الانتهاء من اعمال دهانات الطرق لكامل المشروع |  | إنهاء أعمال غرف المحابس |  | الانتهاء من اعمال الكهرباء لكامل المشروع |  | لا يوجد | 100% |  | 44239137.5 |  | 2025-03-30 | 4000000 | الحصر الفعلي للمشروع | سيتم تنفيذ طبقة سطح اسفلتية BWC داخل المدينة الصناعية بالتنسيق مع مدير المدينة والتشغيل
5 | القطاع الأوسط | برنامج ندلب | MLTX-04-001 | مشروع تأهيل الخندق بالرياض الثانية وتنفيذ الطريق الرابط بالمدينة الصناعية الثالثة بالرياض | عبدالعزيز المسلم | اساس | 2024-10-09 | 2025-01-08 | 3 | 22997121.7 | 100% | 0 | تم الأنتهاء |  | تم التوريد |  | الانتهاء من كافة الأعمال المتبقية وهي أعمال الخرسانة والأسفلت |  | لايوجد |  | الانتهاء من كافة الأعمال |  | - | 100% |  | 20724262.95 |  | 2025-01-07 | 2500000 | تغيير في التصاميم | لايوجد مقترح
6 | القطاع الأوسط | NIS | KHJ1-05-010 | إنشاء 40 مصنع جاهز بمساحة 900 م2 في المدينة الصناعية بالخرج | عبدالعزيز المسلم | حمزه محمد الديري | 2024-12-10 | 2026-02-09 | 14 | 87312629 | 100% | 0 | سيتم الانتهاء من أعمال تجهيز الموقع |  | الانتهاء من اعتماد جميع المواد الانتهاء من امر الشراء لجميع البنود توريد قواطع خفيفة معالجة (autoclaved aerated panels) للبلاطات و الحوائط الداخلية و الخارجية و الدروة للاسطح توريد لوحات الكهرباء توريد خزانات (GRP Water Tanks) |  | الانتهاء من اعمال الحفر الانتهاء من اعمال خرسانة القاوعد المسلحة الانتهاء من اعمال خرسانة رقاب الاعمدة الانتهاء من اعمال العزل للقواعد الانتهاء من اعمال الردم بنسبة 70% الانتهاء من اعمال خرسانة الميد بنسبة 70% |  | البدء باعمال تأسيس الصرف البدء باعمال تأسيس المياه |  | البدء باعمال تأسيس الكهرباء (مواسير) |  | ترسية تنفيذ 40 مصنع جاهز بالخرج ( 900 متر مربع) - 2025-03-31 | 30% |  | 26000000 |  | 2025-09-11 | 0 | - | -
7 | القطاع الأوسط | NIS | KHJ1-05-011 | إنشاء بوابات وسور بالمدينة الصناعية بالخرج | عبدالعزيز المسلم | حمزه محمد الديري | 2024-09-03 | 2025-02-09 | 12 | 21144020 | 100% | 0 | تم الأنتهاء |  | سيتم توريد جميع المشروع بالكامل |  | السور نوع 2 الانتهاء من حفر القواعد بنسبة 100% الانتهاء من صب قواعد ة تركيب بوستات بنسبة 100% تم تركيب شبك بنسبة 100% تم تركيب زوايا بنسبة 100% ------------------------------------------------------ السور نوع 1 حفر قواعد بنسبة 100% انهاء صبة نظافة بنسبة 100% انهاء قواعد مسلحة بنسبة100% انهاء صب مسلحة لرقاب الأعمدة بنسبة 100% الانتهاء من الميدات بنسبه 100% غرفة الحارس الانتهاء من تنفيذ غرف الحراسة |  | الانتهاء من أعمال السباكة بغرف الحراسة |  | السور نوع 1 الانتهاء من اعمال نظام كاشف التسلل ------------------------------------------------------ السور نوع 2 الانتهاء من اعمال نظام كاسف التسلل ----------------------- غرفة الحارس الانتهاء من اعمال التاسيسات الخاصه باعمال الكهرباءا |  | لا يوجد | 100% |  | 19520749 |  | 2025-04-03 | 0 | - | -
8 | القطاع الأوسط | برنامج ندلب | RDH2-05-005 | مشروع إنشاء عدد 17 وحدة مساندة للمدينة الصناعية الثانية في الرياض | راكان | مجموعة جمال الجارودي | 2024-08-08 | 2025-09-07 | 13.1667 | 11524240.1 | 100% | 1094651.7383 | تم الإنتهاء |  | توريد وتركيب خزان GRP توريد وتركيب مضخات الحريق توريد وتركيب مضخة المياه |  | الإنتهاء من أعمال اللياسة والبدء بأعمال الدهانات توريد وتركيب الشبابيك توريد وتركيب shutter door الإنتهاء من أعمال البنية التحتية للموقع العام الإنتهاء من أعمال قواعد الخزان وغرفة المضخات الإنتهاء من أعمال عزل الأسطح ل 3 بلوكات |  | الإنتهاء من تركيب الخزان والمضخات |  | الإنتهاء من أعمال لوحات الكهرباء للبلوكات |  | إنهاء 10% من تنفيذ 17 وحدة مساندة بالرياض الثانية 31-12-2024 إنهاء 30% من تنفيذ 17 وحدة مساندة بالرياض الثانية - 31-03-2024 | 40% |  | 2500000 |  | 2025-04-01 | 0 | - | -
9 | القطاع الأوسط | مدن | RDH4-05-001 | مشروع الأعمال التمكينية لإستكمال وتوسعة المدينة الصناعية بالرياض الثانية من الجهة الجنوبية (الرياض 4) | راكان | شركة الإنشاء المتقدم للمقاولات | 2024-08-20 | 2025-10-19 | 14 | 8988580 | 100% | 0 | تم الإنتهاء |  | توريد كاشف التسلل توريد كيبل فايبر الأوبتك |  | الإنتهاء من أعمال سور الشبك الإنتهاء من أعمال العظم للسور الخرساني وبدأ أعمال التشطيبات الإنتهاء من تركيب التيوبات الحديد للسور الخرساني الإنتهاء من أعمال الخرسانة لغرفة الحارس |  | لا يوجد |  | الإنتهاء من أعمال كاشف التسلل وفايبر أوبتك |  | - | 75% |  | 4000000 |  | 2025-03-15 | 0 | - | -
10 | القطاع الغربي | NIS | MKH2-02-002 | تطويرشبكات البنية التحتية للمرحلة الأولى بالمدينة الصناعية الثانية بمكة المكرمة | محمد الشنيفي | شركة الانجاز للتجارة والمقاولات | 2024-07-29 | 2026-01-28 | 18 | 219997081 | 100% | 0 | تم الانتهاء |  | • توريد المواد المتعلقة بالشبكات (مياه شرب، وري، وصرف وتصريف مياه الأمطار) بنسبة 50% |  | الإنتهاء من أعمال الطرق بالكامل (مع تركيب البردورة واللوحات المرورية) في الطرق المحلية 3 و 6 الإنتهاء من أعمال الطرق بالكامل (مع تركيب البردورة وبدون اللوحات المرورية) في الطرق المحلية 9 والطرق التجميعية رقم 2 الإنتهاء من حفر وتسوية وتدبيش القناة في المناطق 6، 5. الإنتهاء من حفر وتسوية القناة في المناطق 4،3،2،1. العبارة: الإنتهاء من 75% من أعمال العبارة. محطة الضخ: إكمال الردميات والوصول لمرحلة BSG المبنى الإداري: الوصول لمرحلة خرسانة النظافة وتسليح الأساسات |  | شبكة الصرف: الإنتهاء من شبكات الصرف في الطرق المحلية رقم 19، 23 - وفي الطرق المحلية 22، 18، 10، 24، 34 تصل نسبة الإكمال إلى 95% شبكة التصريف: الإنتهاء من تركيب مواسير التصريف والمناهيل والـcatch basin بعد اعتماده في الطريق المحلي رقم 22 و18 ، وفي الطريق 10، 19 يتم تركيب المواسير بنسبة 80% و90% على التوالي شبكة الري: الإنتهاء من شبكة الري في الطرق المحلية رقم 18 و19 و24 و 23، وتتجاوز نسبة الإكمال 90 في الطريق المحلي 22 وتتجاوز 60% في باقي الطرق (10و34) شبكة مياه الشرب: الإنتهاء من 35% من إجمالي أعمال الشبكة |  | • الإنتهاء من حفر وتركيب القنوات duct bank لكيابل الجهد المتوسط والجهد المنخفض في الطريق المحلي رقم 3 و 6 و9 والطريق التجميعي رقم 2 |  | الانتهاء من 15% من المشروع - 2024-12-31 الانتهاء من20% من المشروع - 2025-03-31 | 51.9% |  | 75000000 |  | 2025-12-30 | 28000000 | الحصر الفعلي للمشروع | تنفيذ طرق اضافية
11 | القطاع الغربي | NIDLP | JDH3-03-011 | مشروع ربط الخدمات والمرافق بين المدينة الصناعية الثانية والثالثة بجدة | محمد الشنيفي | شركة عبدالعالي العجمي | 2022-10-26 | 2025-11-15 | 37.2 | 125646775.6483 | 100% | 0 | تم الانتهاء |  | _ توريد للوحات الكهرباء الخاصة بمحطة ضخ المياه المعالجة ومحطة الصرف بجدة الثالثة ومحطة الصرف بجدة الاولي . _ توريد كابل الفايبر الخاص بممر الخدمات _الانتهاء من توريد اغطية الغرف لزوم الخطوط _ توريد رينجات واغطية المناهيل المتبقية _توريد خط DI قطر 200مم الرابط من محطة المعالجة ومحطة تعبئة السيارات _الانتهاء من توريد محابس الغرف _ الانتهاء من توريد محابس محطة الصرف الرئيسية بجدة التالثة _ توريد الUPS الخاص بمحطة ضخ المياه المعالجة _توريد منظومة التخلص من الروائح لزوم محطة الصرف الرئيسية بجدة الثالثة ومحطة الصرف بجدة الاولي |  | الانتهاء من اعمال اللياسة لزوم محطة ضخ المياه المعالجة . الانتهاء من اعمال عزل سطح محطة ضخ المياه المعالجة تركيب الزوايا الخاصة بأغطية الترنشات بمحطة ضخ المياه المعالجة صب طبقة السكريد بمحطة ضخ المياة المعالجة الانتهاء من اعمال المباني لزوم محطة الصرف الرئيسية الانتهاء من اعمال اللياسة الداخلية والخارجية لزوم محطة الصرف الرئيسية الانتهاء من اعمال عزل السطح لزوم محطة الصرف الرئيسية العمل في اعمال الخرسانات لزوم السور لمحطتي المعالجة والصرف الانتهاء من اعمال الخرسانات لزوم الغرف البدء في الاعمال المعدنية لمحطة المعالجة ومحطة الصرف الرئيسية |  | تركيب المضخات وتركيب خط الطرد وخط السحب لزوم محطة ضخ المياه المعالجة تركيب خط ال400&800 الواصل من الخزان الي محطة ضخ المياة المعالجة تركيب نظام الكلور بمحطة ضخ المياة المعالجة تركيب المضخات والمحابس والقطع الخاصة بمحطة الصرف الرئيسية بجدة 3 الربط خط ال900 الناقل لمياه الصرف علي محطة الرفع الرئيسية الانتهاء من اعمال الربط علي محطة ال CMZ الانتهاء من اعمال الخطوط الربط علي المحطات |  | تركيب حوامل الكابلات وتمديد الكابلات لزوم محطة ضخ المياه المعالجة . حفر وتركيب مواسيروالهاندهول لزوم خط ممر الخدمات اعمال تمديد كابلات الفايبر لزوم خط ممر الخدمات الانتهاء من تركيب الUPS الخاص بمحطة ضخ المياه المعالجة تركيب حوامل وتمديد الكابلات لزوم محطة ضخ الصرف بجدة التالته الانتهاء من اعمال تأسيس الكهرباء بمحطة الصرف الرئيسية |  | لا يوجد | 81.22% |  | 88767986.76 |  | 2025-05-25 | 0 | - | -
12 | القطاع الغربي | NIDLP | JDH3-02-006 | تنفيذ البنية التحتية للتجمع الغذائي بالمدينة الصناعية الثالثة بجدة | محمد الغانمي | شركة تطوير التقنية للمقاولات | 2024-06-12 | 2025-12-11 | 18.2333 | 66910337.0957 | 100% | 0 | تم الانتهاء |  | الانتهاء من توريدها مواسير GRP متبقي 16% الانتهاء من توريد أعمدة الإنارة الانتهاء من توريد جميع المناهيل |  | مستهدف الانتهاء من أعمال طبقة ABC وطبقةBBC للطرق بطول 6 كم تركيب جميع قواعد أعمدة الانارة |  | الانتهاء من أعمال شبكة السيول حيث متبقي 44% الانتهاء من أعمال شبكة الصرف الصحي حيت متبقي 80% الانتهاء من 60% من شبكة المياه |  | أعمال التأسيس وبانتظار اعتماد شبكة الجهد المتوسط تركيب 80% من أعمدة الانارة |  | لا يوجد | 53% |  | 29916230 |  | 2025-07-31 | 0 | - | -
13 | القطاع الغربي | NIDLP | MLTX-05-045 | تنفيذ المنتجات الجاهزة للتجمع الغذائية المدينة الصناعية الثانية و الثالثة بجدة | محمد الغانمي | شركة تطوير التقنية للمقاولات | 2024-08-18 | 2026-08-17 | 24 | 153739066 | 100% | 0 | تم الانتهاء |  | توريد ملحقات الهيكل المعدني وهي ألواح سيبوركس وساندويش بانل توريد خزان GRP |  | الانتهاء من تركيب الهيكل المعدني فقط دون ملحقاته |  | الانتهاء من أعمال الميكانيكا بالكامل لمبنى مختبر الجودة |  | الانتهاء من أعمال الكهرباء بالكامل لمبنى مختبر الجودة |  | لا يوجد | 29% |  | 40125896 |  | 2025-10-25 | 0 | - | -
14 | القطاع الغربي | NIS | JDH2-05-007 | تنفيذ المبنى الإداري بالمدينة الصناعية الثانية بجدة | يزيد | شركة كاب فرانس بات السعودية | 2024-05-28 | 2025-05-27 | 12.1333 | 11776481.6435 | 100% | 0 | تم الانتهاء |  | توريد جميع المواد طويلة الأجل المعمارية والكهربية والميكانيكية |  | الانتهاء من أعمال التشطيب بالكامل للمبنى |  | الانتهاء من أعمال الميكانيكا بالكامل للمبنى |  | الانتهاء من أعمال الكهرباء بالكامل للمبنى |  | لا يوجد | 100% |  | 13542953.89 |  | 2025-03-31 | 0 | - | -
15 | القطاع الغربي | NIDLP | TAF1-05-002 | تنفيذ أسوار ومبنى إداري في المدينة الصناعية بالطائف | يزيد | شركة اضواء الخليل للمقاولات | 2024-05-15 | 2025-05-15 | 12.1667 | 14999475.1826 | 100% | 0 | تم الانتهاء |  | توريد مواد الجهد المنخفض LV |  | الانتهاء من أعمال التشطيب بالكامل للمبنى الانتهاء من أعمال السور بالكامل |  | الانتهاء من أعمال الميكانيكا بالكامل للمبنى |  | الانتهاء من أعمال الكهرباء بالكامل للمبنى |  | لا يوجد | 100% |  | 17249396.46 |  | 2025-02-01 | 0 | - | -
16 | القطاع الغربي | NIS | JDH3-05-007 | انشاء 40 مصنع جاهز 900م2 في المدينة الصناعية الثالثة بجدة | يزيد | ركة لبنة البناء للمقاولات | 2024-11-27 | 2026-01-26 | 14 | 86682500 | 100% | 0 | تم الانتهاء |  | اعتماد جميع مواد طويلة الأجل |  | الانتهاء من أعمال الحفر الانتهاء من أعمال الردم الانتهاء من أعمال القواعد ورقاب الأعمدة الانتهاء من أعمال S.O.G بالكامل |  | الانتهاء من أعمال الميكانيكا أسفل منسوب S.O.G |  | الانتهاء من أعمال HG;IVFHX أسفل منسوب S.O.G |  | لا يوجد | 21.7% |  | 18830843 |  | 2025-10-27 | 0 | - | -
17 | القطاع الغربي | NIDLP | ASR2-02-001 | مشروع تنفيذ البنية التحتية في المدينة الصناعية الثانية بعسير | احمد الكتبي | شركة عبدالعالي العجمي | 2023-01-10 | 2026-01-08 | 36.4667 | 168555198 | 100% | 0 | تم الانتهاء |  | توريد محطات الكهرباء ووحدات الربط الحلقي |  | الإنتهاء من الحفر والردم للطرق والأكتاف الإنتهاء من طبقة الأسفلت BBC |  | تصريف مياه الأمطار الإنتهاء من خطوط أنابيب شبكة تصريف مياه الأمطار. الإنتهاء من مناهيل صرف الأمطار للطريق MC02-04 -31 الإنتهاء من مصائد الأمطار للطريق MC02-04-31 مياه الشرب الانتهاء من خطوط أنابيب مياه الشرب الانتهاء من تركيب فوهات الحريق الإنتهاء من تركيب محابس الفراشة إستكمال تشطيب الغرف عدد 25 |  | تركيب عدد 40 عمود تمديد كيبل جهد منخفض بطول 5000 متر إستكمال تركيب مناهيل الإتصالات |  | انهاء 70% من مشروع شبكات البنية التحتية بمساحة 1.2 كم مربع 30-01-2025 انهاء 80% من مشروع شبكات البنية التحتية 25-03-2025 انهاء 90% من مشروع شبكات البنية التحتية 30-03-2025 | 85% |  | 143271918.181 |  | 2025-09-30 | 1500000 | الحصر مبدئي جاري اعداد جدول كميات معدل للحصر الفعلي | يوجد أكثر من مقترح تعديل على العبارات اضافة عدد من المانهول وتمديد اضافي كيابل الجهد المتوسط وربطها مع المحطة
18 | القطاع الغربي | MOF | NJR1-05-004 | تنفيذ المبنى الإداري في المدينة الصناعية بنجران | احمد الكتبي | شركة حمزة الديري | 2024-08-13 | 2025-08-12 | 12 | 4275395 | 100% | 0 | تم الانتهاء |  | الانتهء من توريد جميع مواد طويلة الاجل |  | الإنتهاء من جميع الأعمال المدنية المتبقية وهي أعمال الموقع العام |  | الإنتهاء من جميع الأعمال المتبقية وهي أعمال التكيف |  | الإنتهاء من جميع الأعمال المتبقية وهي أعمال تمديد الأسلاك الانظمة والتشطيب النهائي |  | - | 100% |  | 4275394 |  | 2025-03-31 | 0 | - | -
19 | القطاع الغربي | NIDLP | ASR2-03-003 | تنفيذ الطريق الرابط للمدينة الصناعية بعسير | احمد الكتبي | شركة شبه الجزيرة للمقاولات | 2024-12-01 | 2026-01-31 | 14 | 24275950.71 | 100% | 0 | سيتم الإنتهاء من تجهيز موقع المختبر وتجهيزات السلامة للمكاتب وأعمال التشجير لموقع المكاتب |  | سيتم تقديم جدول التوريدات لأعمدة الكهرباء 17 عمود |  | الإنتهاء من أعمال القطع والردم الإنتهاء من طبقة القاعدة بنسبة 30% |  | لايوجد |  | سيتم إعتماد المخططات والمواد |  | لا يوجد | 20% |  | 4855190.142 |  | 2025-12-30 | 0 | - | -
20 | القطاع الغربي | MODON | JDH1-05-005 | انشاء 14 مصنع جاهز 900م2 في المدينة الصناعية الأولى بجدة | الهانوف | لبنة البناء | 2024-10-24 | 2025-12-23 | 14 | 35034628.45 | 100% | 0 | تم الانتهاء |  | جاري تقديم جدول التوريدات للمواد طويلة الأجل والاعتماد من قبل الإستشاري |  | جاري أعمال القواعد الخرسانية والعزل للبلوكات A/B/C/D |  | جاري اعتماد المواد والمخططات |  | جاري اعتماد المواد والمخططات |  | - | 30% |  | 12086946.7 |  | 2025-08-24 | 0 | - | -
21 | القطاع الغربي | NIS | MAD1-02-006 | تنفيذ البنية التحتية للقطاع رقم 3 و 4 في المدينة الصناعية بالمدينة المنورة | عبدالله الجليفي | شركة شبه الجزيرة للمقاولات | 2024-01-03 | 2026-01-02 | 24.3333 | 61984927 | 100% | 6198492.7 | تم الانتهاء |  | تم الانتهاء |  | استكمال اعمال طبقة ألأساس والأسطحية البتومينية لطرق المحلية والتجميعية استكمال اعمال تركيب بردورات والأرصفة لطرق المحلية والتجميعية استكمال اعمال اللوحات الارشادية لطرق المحلية والتجميعية |  | استكمال اعمال تركيب فوهات الحريق لشبكة المياه الشرب استكمال اعمال تركيب اغطية معدنية شديدة لغرف مانهولات استكمال اعمال تركيب توصيلات المنزلية لشبكة المياه الشرب |  | لا يوجد |  | لا يوجد | 100% |  | 30290576 |  | 2025-03-01 | 0 | - | -
22 | القطاع الغربي | NIS | MAD1-02-007 | تنفيذ البنية التحتية للقطاع رقم 5 في المدينة الصناعية بالمدينة المنورة | عبدالله الجليفي | شركة الإنجاز للتجارة والمقاولات | 2024-01-03 | 2026-01-02 | 24.3333 | 145002346 | 100% | 14500234.6 | تم الانتهاء |  | الانتهاء من توريد جميع مواد المشروع |  | إستكمال الأعمال الترابية لطرق Zone5 (R6 , R6A , R7). أعمال طبقات الأسفلت Zone6 (R4) & Zone5 (R6 , R6A , R7). أعمال الأرصفة Zone6 (R4 , R5) & Zone5 (R6 , R6A , R7). |  | إستكمال أعمال شبكة صرف مياه الأمطار Zone2 & Zone4 & Zone5. إستكمال أعمال شبكة الصرف الصحي Zone5. إستكمال أعمال شبكة مياه الشرب Zone2 & Zone5. إستكمال أعمال الربراب Zone1 & Zone6. |  | إستكمال أعمال إنارة الطرق. إستكمال أعمال شبكة الاتصالات Zone1 & Zone5. أعمال شبكة الجهد المتوسط. |  | لا يوجد | 100% |  | 145002346 |  | 2025-03-01 | 0 | - | -
23 | القطاع الغربي | NIS | MAD1-02-008 | مشروع تطوير البنية بالمدينة الصناعية بالمدينة المنورة مرحلة A-1 | عبدالله الجليفي | شركة الانجاز للتجارة والمقاولات | 2024-11-20 | 2026-07-19 | 20 | 113188837 | 100% | 11318883.7 | تم الانتهاء |  | الانتهاء من توريد جميع المواد طويلة الأجل خلال شهر يناير |  | استكمال اعمال القطع في الطرق المحلية (1&2&3&4&5) استكمال اعمال القطع في الطريق التجميعي (1) اعمال ال SG في الطرق المحلية (1&2&3&4&5) اعمال القطع والردم في القناه المفتوحة رقم 1 مع اعمال تهذيب القناه واعمال التكسية بالحجارة اعمال صب العبارة 10 فتحات |  | أعمال شبكة صرف مياه الأمطار في زون 2 (Line 1&1-1&1-2&1-3&3&2&2-1&2-2). أعمال شبكة الصرف الصحي زون 2 في Line 1&1-2. |  | اعمال شبكة الاتصالات في زون 2 اعمال شبكة الانارة في زون 2 اعمال شبكة الجهد المتوسط في زون 1 |  | لا يوجد | 20% |  | 22637767.4 |  | 2025-12-31 | 0 | - | -
24 | القطاع الغربي | NIS |  | إنشاء 20 مصنع جاهز 900م2 بالمدينة المنورة | عيسى ال علي | تحت الطرح | 2025-01-15 | 2026-03-14 | 14 | 44000000 | 100% | 0 | تم الانتهاء |  | اعتماد المواد واصدار اوامر الشراء |  | الانتهاء من اعمال الحفر واختبارات التربة |  | اعتماد مخططات والمواد |  | اعتماد المخططات والمواد |  | لا يوجد | 3% |  | 700000 |  | 2026-03-14 | 0 | - | -
25 | القطاع الشرقي | MODON | DAM2-05-014 | انشاء 23 مصنع جاهز 900م2 في المدينة الصناعية الثانية بالدمام | عفات العنزي | السعودي زاس | 2024-10-16 | 2025-12-12 | 14 | 54373752 | 100% | 0 | مستهدف الانتهاء 100% |  | الانتهاء من جميع مواد طويلة الأمد ( خزان GRP - المضخات - المواد الانشائية - STEEL STRUCTURE ) |  | الانتهاء من كامل أعمال الحفر الانتهاء من صب القواعد الانتهاء من صب الميد |  | الأنتهاء من أعمال التأسيس للأساسات |  | الأنتهاء من أعمال التأسيس للأساسات |  | - | 25% |  | 15000000 |  | 2025-10-30 | 0 | - | -
26 | القطاع الشرقي | MODON | DAM1-05-003 | انشاء 14 مصنع جاهز 900م2 في المدينة الصناعية الأولى بالدمام | عفات العنزي | السعودي زاس | 2024-10-16 | 2025-12-16 | 14 | 34953794 | 100% | 0 | مستهدف الانتهاء 100% |  | الانتهاء من جميع مواد طويلة الأمد ( خزان GRP - المضخات - المواد الانشائية - STEEL STRUCTURE ) توريد أعمال الحديد وتركيبها |  | الانتهاء من كامل أعمال الحفر الانتهاء من صب القواعد الانتهاء من صب الميد |  | الأنتهاء من أعمال التأسيس للأساسات |  | الأنتهاء من أعمال التأسيس للأساسات |  | - | 30% |  | 10000000 |  | 2025-09-30 | 0 | - | -
27 | القطاع الشرقي | NIS | HSA3-05-007 | إنشاء عدد (24) مصنع جاهز بواحة الاحساء 225م² | محمد العيسى | شركة بناء الجزيرة للمقاولات | 2024-01-10 | 2025-07-09 | 18.2 | 19595638.7652 | 100% | 0 | تم الانتهاء |  | مضخة المياه اعمدة الانارة خزان المياه GRP الواجهات الزجاجية والالمنيوم |  | الانتهاء من اعمال اللياسة الداخلية والخارجية الانتهاء من اعمال العزل الاسطح الانتهاء من اعمال السيراميك بنسبة 100% الانتهاء من تاسيس الدهانات بنسبة 100% الانتهاء من الدهانات والخارجية بنسبة 70% الانتهاء الانترلوك والبردوره 50% |  | الانتهاء من اعمال تاسيس الصرف والمياة داخل المصانع الانتهاء من شبكة الحريق الخارجية الانتهاء من شبكة المياة الانتهاء من شبكة الصرف الانتهاء شبكة الامطار الانتهاء من اعمال شبكة الحريق الداخلي 60% |  | انتهاء من تاسيس الكهرباء وتركيب العلب وسحب الاسلاك وتركيب وحدات الانارة الداخلية البدء بتركيب لوحات الكهرباء |  | لا يوجد | 80% |  | 10200000 |  | 2025-07-09 | 0 | - | -
28 | القطاع الشرقي | NIS | HSA3-05-008 | إنشاء 40 وحدة مساندة بواحة الأحساء | محمد العيسى | مؤسسة استشارات لتكنولوجيا البناء للمقاولات | 2024-01-21 | 2025-07-20 | 18.2 | 22075162.4174 | 100% | 1103758.1209 | تم الانتهاء |  | تم التوريد |  | الانتهاء من اعمال التشطيبات الداخلية واخارجية الانتهاء من اعمال الاسفلت تسليم المستندات واجراء الاختبارات وانتهاء المشروع |  | الانتهاء من تركيب الاجهزة الصحية الانتهاء من من الشبكات وتركيب اغطية المناهل وربط المضخات بالخزان والشبكات المياه والحريق تسليم المستندات واجراء الاختبارات وانتهاء المشروع |  | الانتهاء من تركيب وحدات الاضاءه واعمدة الانارة تسليم المستندات واجراء الاختبارات وانتهاء المشروع |  | لا يوجد | 100% |  | 22075162.4174 |  | 2025-01-13 | 0 | - | -
29 | القطاع الشرقي | NIS | HSA3-02-005 | مشروع توسعة واحة الأحساء (يشمل مشروع ربط واحة الأحساء بالطرق الخارجية والبوابات والأسوار) | محمد العيسى | الانجاز | 2024-10-08 | 2026-04-01 | 18 | 87783025 | 100% | 8778302.5 | تم الانتهاء |  | مواسير GRP شبكات الصرف الصحي وتصريف توريد حديد وبوابات سور للنوع الاول توريد محابس شبكات المياه والري توريد مناهل شبكات الصرف الصحي وصرف المطر والري والمياه |  | الانتهاء من اعمال السور النوع الثاني والانتهاء من قواعد ورقاب الاعمدة وميدات النوع الاول من السور بنسبة 50% الانتهاء العظم الخرسانة والبلوك وشبكات الموقع العام للمبني الاداري الانتهاء من اعمال العظم خرسانة وبلوك واعمال عزل لغرف الحراسة رقم 2&3 الانتهاء من اعمال التسوية والقطع للطريق الربط الخارجي بنسبة 50% |  | الانتهاء تاسيس اعمال السباكة بالمبني الاداري الانتهاء من تركيب المضخات وخزان المياة والشبكات الخارجية للمبني الاداري الانتهاء بنسبة 60% من تركيب محابس شبكات المياه والري |  | الانتهاء من تاسيس اعمال الكهرباء بالمبني الاداري وغرف الحراسة الانتهاء بنسبة 70% من اعمال خنادق كابلات شبكتي الكهرباء والاتصالات العمل علي ازالة اعمدة الانارة والكيابل من الطريق الخارجي |  | لا يوجد | 30% |  | 21300000 |  | 2025-10-07 | 0 | - | -
30 | القطاع الشرقي | NIDLP | DAM2-05-015 | استكمال إنشاء عدد 84 مصنع جاهز بالمدينة الصناعية الثانية بالدمام | محمد العيسى | شركة جمال عبد الفتاح الجارودي للمقاولات | 2024-11-17 | 2025-03-16 | 4 | 15327411.16 | 100% | 0 | تم الانتهاء |  | توريد باقي ابواب الشتر توريد الواجهات وجميع انواع الابواب توريد اعمدة الانارة ولوحات الانذار والمعلومات |  | الانتهاء من اعمال التشطيبات الداخلية واخارجية الانتهاء من اعمال الاسفلت تسليم المستندات واجراء الاختبارات وانتهاء المشروع |  | الانتهاء من تركيب الاجهزة الصحية الانتهاء من شبكات الحريق الداخلية والخارجية الانتهاء من اعمال الشبكات الخارجية والمناهل والتوصيلات تسليم المستندات واجراء الاختبارات وانتهاء المشروع |  | الانتهاء من تركيب وحدات الاضاءه واعمدة الانارة تسليم المستندات واجراء الاختبارات وانتهاء المشروع |  | لا يوجد | 100% |  | 15327411.16 |  | 2025-03-16 | 0 | - | -
31 | القطاع الشرقي | وزارة المالية | DAM1-05-004 | مشروع انشاء محطة الدفاع المدني بالمنطقة الصناعية الأولى بالدمام | محمدعسيري | شركة بروفاست المحدودة | 2024-07-25 | 2025-07-24 | 12 | 10724195.487 | 100% | 1072419.549 | تم الانتهاء |  | توريد جميع اعمال الكهرباء طويلة الاجل- المولد-ال UPS-كشافات الانارة - اللوحات العموميه والفرعية -انذار الحريق-الصوتيات-الداتا-التليفون-التحكم في الأبواب-كاميرات المراقبة - وتوريد الهيكل المعدني وتركيبه - توريد مضخات المياه - توريد GRP tank - توريد Fuel tank |  | الانتهاء من جميع الأعمال الخرسانية بالموقع - تركيب الهيكل المعدني - البدء بأعمال التشطيبات |  | الانتهاء من تأسيس أعمال الصحي ( صرف + تغذية ) - تمديد مواسير التكييف - البدء بأعمال شبكة الحريق |  | الانتهاء من اعمال ال FIRST FIX واعمال SECOND FIX والبدء باعمال ال THIRD FIX |  | - | 54% |  | 5000000 |  | 2025-03-31 | 0 | - | -
32 | القطاع الشرقي | NIS | DAM3-02-006 | مشروع تطوير شبكات البنية التحتية بالمنطقة الصناعية للمدينة الصناعية الثالثة بالدمام | محمدعسيري | شركة انساب للمقاولات العامة | 2024-08-06 | 2026-08-05 | 24 | 225574543 | 100% | 22557454.3 | تم الانتهاء |  | * RMU / تم إستلام إعتماد مبدئي *Generator./جاري التقديم للإعتماد *Pumps for Pump Station/تم التقديم جاري الإعتماد *Odor control system- MCC(pump station)/تم التقديم جاري الإعتماد *Penstock(Pump station)/تم التقديم جاري الإعتماد *CCTV system /تم تقديم العرض الفني للرسومات التنفيذية تحت المراجعة *Flow Metar/جاري التقديم للإعتماد *Fire alarm system /جاري التقديم للإعتماد *LV cable /تم الإعتماد *Street lighting Poles/تم التوريد بالموقع عدد 296 عمود إنارة *Street lighting Fixtures *MV cable /تم التوريد بالموقع كمية 4,997 متر طولي كابلات *Local Control Panel ( SCADA) /جاري التقديم للإعتماد *إستكمال أعمال توريد مواسير شبكة المياة والري والهاتف إستكمال توريد كابلات الجهد المتوسط وأعمدة الإنارة * استكمال توريد كيابل الكهرباء |  | * الإنتهاء من أعمال تجهيزات الموقع *الإنتهاء من أعمال تركيب المختبر ومعايرة الأجهزة *الإنتهاء من أعمال القطع الترابي والردم بالطرق الرئيسية والفرعية *استكمال أعمال طبقة التطويق وطبقة الأساس بالمشروع بالطرق الرئيسية والفرعية أعمال الشبكات *استكمال أعمال الحفر والتمديد بشبكة الصرف الصحي *استكمال أعمال الحفر بشبكة تصريف السيول |  | .استكمال أعمال شبكة تصريف مياة الأمطار .استكمال أعمال شبكة الصرف الصحي .استكمال أعمال شبكة الري .استكمال أعمال شبكة المياة |  | تنفيذ 10% من شبكة الجهد المتوسط. تنفيذ 10% منشبكة الإنارة. تنفيذ 10% من شبكة الهاتف. |  | لا يوجد | 21.68% |  | 30167373 |  | 2025-06-01 | 6000000 | كمية القطع والردم في الBOQ اعلى من الطبيعي ووجود محابس وعبارات خرسانية في الBOQ ولايلزم تنفيذها في k&L | لايوجد مقترح
33 | القطاع الشرقي | وزارة المالية | TAB1-05-003 | انشاء المبنى الإداري في المدينة الصناعية بتبوك | محمد الدريهم | شركة حمزة الديري | 2024-07-24 | 2025-07-24 | 12 | 4590676 | 100% | 0 | تم الانتهاء |  | تم التوريد |  | - تركيب قواعد اللوحات الارشادية والمرورية - اعمال الردم والدمك للموقع العام - أعمال الاسفت للموقع العام - تركيب حجر الواجهات الخارجي - الاسقف المستعارة - الدهانات الداخلية الطبقات النهائية والتشطيبات الداخلية - اعمال الانترلوك |  | تمديدات الصرف الخارجية المدفونة GRP - التمديدات الخارجية من الخزان الي المبني HDPE - تركيب اغطية المناهيل والاغطية - تركيب دكت التكييف - تركيب الادوات الصحية - تركيب التكييفات - تركيب المضخة |  | - تركيب مناهيل الطاقة والبيانات في الموقع العام وتاسيس خطوط الربط - عمل تغليفات للكوابل الخارجية المرتبطة باعمال الطرق الخارجية - تمديدات التيار الخفيف: أسلاك وانظمة اطفاء الحريق / التلفون / البيانات/ كاميرات المراقبة (داخلية + خارجية)/HDMI - تمديدات لوحات الطاقة - تركيب الافياش / اراكات / المفاتيح - تركيب الكشافات ومراوح التهوية |  | - | 100% |  | 4590676 |  | 2025-02-28 | 200000 | عدم الحاجة لتركيب مواسير الGRP+عدم الحاجة لتنفيذ الUPS+عدم تنفيذ بند انقطاع التيار المؤقت | لايوجد مقترح
34 | القطاع الشرقي | وعد الشمال | WAS1-05-004 | إنشاء 20 مصنع جاهز و 12 وحدة مساندة - الجزء الثاني من المرحلة الأولى - مدينة وعد الشمال | محمد الحربي | شركة زاس | 2023-08-29 | 2025-08-28 | 24.3333 | 48948728.4 | 100% | 0 | تم الانتهاء | [9 empty] | لا يوجد |  |  |  |  | 2024-12-25 | 3667707 | الحصر الفعلي للمشروع | لايوجد مقترح
35 | المشاريع النوعية | NIS | JDH3-02-008 | استكمال تطوير البنية التحتية للمرحلة الأولى في المدينة الصناعية الثالثة بجدة | شعيب الشعيبي | شركة الرواف | 2024-07-29 | 2026-07-28 | 24 | 319744875.7217 | 46.91% | 31974487.5722 | Completed |  | Completion of the following: HDPE pipes - 77,772 m, GRP pipe - 74,009 m, UPVC pipe - 24,958 m, Sewage Manhole - 359 Nr, Storm Manhole - 602 Nr, Catchbasins- 927 Nr, Kerbstone - 35,483 m, Interlock - 14,400 m2 Asphalt - 10,654 m3 50% of Electrical materials ( LOW VOLTAGE CABLES , Lighting panels ..etc) | HDPE Pipes - 79,271 m, GRP pipe - 63,503 m, UPVC Pipe - 28,564 m, Sewage Manhole - 107 No, Storm Manhole - 124 No, Kerbstone- 15084 m, Interlock - 4088.25 m2 , Catchbasins- 67 Nr, LV Cables- 46,842 m | Completion of the following: - Interlock - 14,400 m2, - Kerbstone - 35,483 L.m - Ponds finished100% - Road works to execute 10,654 m3 Asphalt | Kerbstone - 12,755 Lm, Interlock - 1,353 m2, Pond (1,2,3&4) -89%, Pond excavation at Zone 6&12 - 705,349 m3 Road Works Subgrade layer - 9,584 m3, Asphalt- 930 m | Completion of the following: - Sewage pipe - 30,112 L.m, - Sewage Manhole - 359 Nr, - Irrigation pipe - 61,381 L.m, - Storm Manhole - 602 Nr, - Storm pipe - 42,989 L.m, - Catchbasins- 927 Nr, - Catchbasin pipes - 24,958 L.m, - Box Culvert - 3600 L.m - Potable water pipe - 17,389 L.m, | Sewage pipe - 8,425 L.m, Sewage Manhole - 91 Nr, Storm pipe - 20,331 L.m, Storm Manhole - 171 Nr, Potable water pipe - 2,663 L.m, Irrigation pipe - 10,331 L.m, Catchbasin pipes - 1,757 L.m, Box Culvert - 1,126 L.m | Street lighting system ( LV Cables , Light LUMINAIRE …. ) | Relocation 12 Foundations, 12 Drawpits, 4Telecommunication Manholes, Telecome duct -144m | لا يوجد | 59.59% | 26.13% | 51759007 | 41751208.322 | 2026-07-28 | 105000000 | الحصر الفعلي للمشروع | تطوير شبكات اضافية ومساحات تطويرية اضافية
36 | المشاريع النوعية | NIS |  | تطوير المرحلة الثانية من المدينة الصناعية الثالثة بجدة | محمد الناصر | جاري التعاقد |  |  | 36 | 560000000 | 0% | 0 | [10 empty] | لا يوجد | [5 empty] | 0 | - | -
37 | إيصال خدمات | وعد الشمال | WAS1-03-001 | إنشاء محطة التحويل الأولى بمدينة وعد الشمال جهد 132 ك.ف | هارون الحميضي | شركة الطوخي | 2019-05-06 | 2023-01-31 | 45.5333 | 102900000 | 100% | 0 | تم الانتهاء |  | توريد مضخة منع الحرائق توريد نهايات كوابل الجهد المتوسط |  | اكمال تشطيبات غرفة المضخات بنسبة 100% اكمال تشطيبات غرفة الأمن بنسبة 100% |  | إكمال أعمال تركيبات انظمة منع الحرائق بنسبة 100% إكتمال تركيب ممرات التكييف بنسبة 100% |  | ربط كوابل الجهد المتوسط والعالي إكمال أعمال الإختبارات بنسبة 60% |  | لا يوجد | 98% |  | 92610000 |  | 2025-06-30 | 0 | - | -
38 | إيصال خدمات | برنامج ندلب | ASR2-03-001 | مشروع انشاء محطة تحويل جهد 33/132 ك.ف في المدينة الصناعية الثانية بعسير | هارون الحميضي | شركة نسما | 2023-08-23 | 2026-02-23 | 30.5 | 109481000 | 100% | 0 | تم الانتهاء |  | كبائن الحماية والتحكم أنظمة الأمن السبراني لوحات التيار المتردد والمستمر الشواحن البطاريات الأمن السيبراني كوابل التحكم كوابل الجهد المنخفض كوابل الجهد المتوسط الإنارة وملحقاتها محول التوزيع |  | إكتمال المباني بنسبة 100% أكتمال قواعد المحولات بنسبة 100% اكتمال ممرات الكوابل الخرسانية بنسبة 100% إكتمال السور الخارجي بنسبة 100% |  | لا يوجد |  | تركيب المفاتييح الغازية جهد 132 ك.ف بنسبة 100% تركيب حوامل الكوابل بنسبة 100% تركيب محول التوزيع بنسبة 100% تمديدات كوابل التحكم والجهد المنخفض بنسبة 80% تمديدات كوابل الجهد المتوسط بنسبة 50% تركيب كبائن الحماية والتحكم بنسبة 50% تركيب الإنارة بنسبة 50% |  | لا يوجد | 55% |  | 46700000 |  | 2025-12-31 | 0 | - | -
39 | إيصال خدمات | برنامج ندلب |  | إنشاء خطوط هوائية بعسير | هارون الحميضي | شركة الشريف للمقاولات والتنمية التجارية | 45603 | 46210 | 20 | 139300000 | 100% | 0 | تم الانتهاء |  | إعتماد المسار بنسبة 100% اعتماد المسار التفصيلي بنسبة 100% اعتماد المواد بنسبة 100% بدء اعمال التصنيع للمواد بنسبة 100% توريد 40% من ارجل قواعد الأبراج توريد 40% من مواد التأريض |  | اكمال 50% من اعمال طريق الصيانة إكمال 30% من تجهيز ارضية قواعد الابراج إكمال 10% من إختبارات التربة لقواعد الأبراج |  | لا يوجد |  | لا يوجد |  | لا يوجد | 25% |  | 25000000 |  | 2026-07-07 | 0 | - | -
40 | إيصال خدمات | NIDLP | HFR1-03-002 | إنشاء محطة تحويل جهد 115 ك.ف بسعة 100 م.ف.أ في المدينة الصناعية بحفر الباطن | ابراهيم العبودي | شركة نسما | 2023-08-16 | 2026-02-15 | 30.4667 | 96699999 | 100% | 9669999.9 | تم الانتهاء |  | المفاتيح الغازية كبائن الحماية والتحكم الشواحن البطاريات الأمن السيبراني الاتصالات |  | اكتمال المبنى 100 % - اكتمال قواعد المحولات 100 % اكتمال الأعمال الخاريجة بنسبة 40 % |  | تركيب الرافعة تركيب المفاتيح الغازية 50 % تركيب الاتصالات 30 % تركيب كبائن الحماية والتحكم 30 % |  |  |  | انهاء تنفيذ 40% من محطة الكهرباء بالمدينة الصناعية بحفر الباطن 30-03-2025 | 55% |  | 38000000 |  | 2026-02-15 | 0 | - | -
41 | إيصال خدمات | برنامج ندلب | HFR1-03-003 | إنشاء خطوط هوائية جهد 115 ك.ف. لإيصال الخدمة الكهربائية للمدينة الصناعية بحفر الباطن | ابراهيم العبودي | الحيدر للتجارة والمقاولات | 2024-02-18 | 2026-05-17 | 27.3 | 93600000 | 100% | 9360000 | تم الانتهاء |  | مكتمل وصول العوازل وصول الموصلات وصول الأبراج |  | اكتمال اعتماد تقارير التربة وتصاميم قواعد الأبراج - اكتمال صب قواعد 60 برج. |  | اكتمال تركيب 25 برج |  |  |  | - | 61% |  | 57300000 |  | 2026-05-17 | 0 | - | -
42 | إيصال خدمات | برنامج ندلب | TAB1-03-003 | إنشاء محطة تحويل جهد 132 / 13.8 ك.ف. بسعة 134 م.ف.أ في المدينة الصناعية بتبوك | ابراهيم العبودي | شركة الفنار | 2024-02-14 | 2026-08-13 | 30.3667 | 108569000 | 100% | 10856900 | تم الانتهاء |  | اعتماد جميع المواد ، وبدء التصنيع 100 % |  | اكتمال المبنى لاستقبال المواد بنسبة 80 %. | [5 empty] | - | 30% |  | 21000000 |  | 2026-08-13 | 0 | - | -
43 | إيصال خدمات | برنامج ندلب | TAB1-03-004 | إنشاء خطوط هوائية جهد 132 ك.ف. لإيصال الخدمة الكهربائية للمدينة الصناعية بتبوك | ابراهيم العبودي | شركة الشريف للمقاولات والتنمية التجارية | 2024-07-11 | 2026-01-10 | 17.8667 | 64480000 | 100% | 6448000 | تم الانتهاء |  | وصول الموصلات وصول العوازل وصول الأبراج |  | اكتمال اعتماد تقارير التربة وتصاميم قواعد الأبراج - اكتمال صب قواعد 22 برج. | [5 empty] | - | 52% |  | 17000000 |  | 2026-01-10 | 0 | - | -
44 | إيصال خدمات | NIS | DAM2-03-009 | التخلص من المياه المعالجة ومياة الأمطار في مدينة الدمام الثانية في البحر | محمد الغشام | الهيئة السعودية للمياه | 2024-03-19 | 2025-09-18 | 18 | 61381000 | 100% | 0 | تم الانتهاء |  | توريد المواسير اصدار امر الشراء لتوريد |  | الانتهاء من الاساسات للمحطات و الردم الانتهاء من تصاريح المسار و اعتماد المخططات و تنفيذ 10% من الخط |  | اعتماد المحابس و بدأ بالتركيب |  | اعتماد المخططات و التصاميم |  | لا يوجد | 28% |  | 16879775 |  | 2025-09-18 | 0 | - | -
45 | إيصال خدمات | NIS | JDH2-03-010 | توفير مصدر مياه للمدينة الصناعية الثانية بجدة | صالح الوطبان | شركة نقل وتقنيات المياه | 2024-03-10 | 2025-09-09 | 16 | 29976549 | 100% | 0 | تم الانتهاء |  | اعتماد التوريدات و ابدأ بالتصنيع |  | اكتمال الاعمال المدنية 30% |  | اكتمال الاعمال المكانكية 40% |  | اكتمال الاعمال الكهربائية 20% |  | لا يوجد | 60% |  | 0 |  | 2025-06-20 | 0 | - | -
46 | إيصال خدمات | NIS | KHJ1-03-011 | اتفاقية لتصميم و انشاء و تركيب محطة تنقية وتحلية بالمدينة الصناعية بالخرج | خالد اليامي | الهيئة السعودية للمياه | 2024-01-10 | 2024-06-09 | 6 | 22000000 | 100% | 0 | تم الانتهاء |  | اكتمال التوريد بنسبة 100% |  | اكتمال الاعمال المدنية 100% |  | اكتمال الاعمال المكانكية 100% |  | اكتمال الاعمال الكهربائية 100% |  | لا يوجد | 100% |  | 3960000 |  | 2025-03-25 | 0 | - | -
47 | إيصال خدمات | NIDLP | JDH4-03-008 | اتفاقية إنشاء أنظمة نقل المياه لمشروع امداد المياه لواحة جدة | خالد اليامي | شركة نقل وتقنيات المياه | 2023-11-08 | 2025-02-07 | 16 | 26550668 | 100% | 0 | تم الانتهاء |  | اكتمال التوريد بنسبة 100% |  | اكتمال الاعمال المدنية 100% |  | اكتمال الاعمال المكانكية 100% |  | اكتمال الاعمال الكهربائية 100% |  | - | 100% |  | 2655067 |  | 2025-02-07 | 0 | - | -
48 | إيصال خدمات | MOF | DAM2-03-010 | اتفاقية انشاء انظمة نقل المياه لمشروع امداد المياه للمدينة الصناعية الثانية بالدمام | محمد الغشام | شركة نقل وتقنيات المياه | 2024-06-06 | 2025-09-07 | 16 | 65987460 | 100% | 0 | تم الانتهاء |  | توريد المواسير اصدار امر الشراء لتوريد |  | الانتهاء من اساسات المباني الخدمية تنفيذ 15% من خط المياه |  | البدأ اعمال لحام المواسير تركيب المحابس و غرف المحابس |  | اعتماد المخططات و التصاميم |  | - | 40% |  | 26394984 |  | 2025-09-05 | 0 | - | -
49 | إيصال خدمات | MOF | DAM3-03-010 | اتفاقية انشاء انظمة نقل المياه لمشروع امداد المياه للمدينة الصناعية الثالثة بالدمام | محمد الحربي | شركة نقل وتقنيات المياه | 2024-10-17 | 2026-01-18 | 16 | 39577020 | 100% | 0 | تحت التجهيز | [9 empty] | - |  |  |  |  | 2026-01-18 | 0 | - | -
50 | إيصال خدمات | NIS | TAF1-03-002 | تنفيذ خزانات ومحطة ضخ المياه بالمدينة الصناعية بالطائف | خالد اليامي | شركة مشروعات المياه | 2024-07-18 | 2025-11-18 | 16 | 19950000 | 100% | 0 | تم الانتهاء |  | اكتمال التوريد بنسبة 90% |  | اكتمال الاعمال المدنية 100% |  | اكتمال الاعمال الميكانيكية 90% |  | اكتمال الاعمال الكهربائية بنسبة 70% |  | لا يوجد | 75% |  | 7758738 |  | 2025-11-18 | 0 | - | -
51 | إيصال خدمات | MOF | ASR1-03-001 | تنفيذ الخط الناقل للمياه و محطة المياه وشبكة مياه داخلية بعسير 1 | صالح الوطبان | شركة مشروعات المياه | 2024-07-14 | 2026-01-13 | 18 | 22399770 | 100% | 0 | تم الانتهاء |  | اكتمال التوريد بنسبة 90% |  | اكتمال الاعمال المدنية 100% |  | اكتمال الاعمال الميكانيكية 85% |  | اكتمال الاعمال الكهربائية بنسبة 80% |  | - | 70% |  | 6431052 |  | 2026-01-13 | 0 | - | -
52 | إيصال خدمات | NIDLP | RDH3-03-006 | توفير مصدر مياه للمدينة الصناعية الثالثة بالرياض | محمد الغشام | سواعد العربية | 2024-08-13 | 2025-02-12 | 6 | 1212660 | 100% | 0 | تم الانتهاء |  |  |  | اكتمال المشروع 100% |  | اكتمال المشروع 100% |  | اكتمال المشروع 100% |  | - | 100% |  | 1212660 |  | 2025-01-27 | 0 | - | -
53 | إيصال خدمات | NIS | RDH3-03-007 | تصميم و تنفيذ محطة معالجة مياه صرف صحي بالمدينة الصناعية الثالثة بالرياض | محمد الغشام | اساس | 2024-11-27 | 2025-09-26 | 10 | 17105524 | 100% | 0 | سيتم الانتهاء من أعمال تجهيز الموقع |  | اعتماد التوريدات و البدأ بالتصنيع |  | اعتماد التصاميم و المخططات البدأ بالاعمال النشائية الانتهاء من الأساسات |  | اعتماد التصاميم اصدار امر الشراء |  | اعتماد التصاميم اصدار امر الشراء |  | لا يوجد | 15% |  | 3078994.32 |  | 2025-09-26 | 0 | - | -
54 | إيصال خدمات | NIS | HAL1-03-006 | تصميم و تنفيذ محطة معالجة مياه صرف صحي بالمدينة الصناعية الثالثة حائل | محمد الغشام | اساس | 2024-11-28 | 2025-09-27 | 10 | 17105524 | 100% | 0 | سيتم الانتهاء من أعمال تجهيز الموقع |  | اعتماد التوريدات و البدأ بالتصنيع |  |  |  | اعتماد التصاميم اصدار امر الشراء |  | اعتماد التصاميم اصدار امر الشراء |  | لا يوجد | 15% |  | 3078994.32 |  | 2025-09-27 | 0 | - | -
2025-07-06

## Conclusion (hidden)
استكمال تطوير البنية التحتية للمرحلة الاولي في المدينة الصناعية الثالثة بجدة
معلومات المشروع |  |  |  | نطاق المشروع |  |  |  |  | موقع المشروع
المقاول | شركة الرواف للمقاولات | الاستشاري | شركة إيجيس للاستشارات الهندسية | البند | الكمية الكلية | الكمية المنفذة | الكمية المتبقية | نسبة المنفذ |  | Scope
تاريخ استلام الموقع | 2024-07-29 | مدة التنفيذ | 24 شهرًا ميلاديًا | أعمال الطرق m3 | 63689 | 836 | 62853 | 1.313% |  | Road Works
بداية العقد | 2024-07-29 | قيمة العقد (شامل ضريبة القيمة المضافة) | 367,706,607.08 ريال | إنارة الطرق وشبكة الإتصالات m | 65175 | 144 | 65031 | 0.2209% |  | Street Lighting and telecommunication Network
نسبة الإنجاز المخطط له | 59.9% | نسبة الإنجاز الفعلي | 26.13% | شبكة مياه الشرب m | 23742 | 2663 | 21079 | 11.22% |  | Potable Water Network
|  |  |  | شبكة المياه المعالجة m | 70983 | 10331 | 60652 | 14.55% |  | TSE
ملخص جدول الكميات |  |  |  | شبكة الصرف الصحي m | 29561 | 8425 | 21136 | 28.5% |  | Sewage
مكونات المشروع |  | التكلفة (غير شامل ضريبة القيمة المضافة) | النسبة الاجمالية | شبكة تصريف السيول والأمطار m | 73040 | 22088.75 | 50951.25 | 30.24% |  | Storm water
تنفيذ أعمال الطرق والرصف، وتنفيذ العلامات الأرضية واللوحات الإرشادية |  | 67012836.61 | 20.96% | البردورات مسبقة الصب - متر طولي | 313864 | 12755 | 301109 | 4.064% |  | Kerbstone
شبكة الأعمال الكهربائية |  | 13120143.99 | 4.103% | انترلوك - متر مربع | 59537.28 | 1353 | 58184.28 | 2.273% |  | Interlock
شبكة مياه الشرب |  | 9302202.18 | 2.909% | ملخص التوريدات |  |  |  |  | تقدم أعمال layout
شبكة المياه المعالجة |  | 49057169.92 | 15.34% | البند | الكمية الكلية (م.ط) | الكمية المورده (م.ط) | الكمية المتبقية (م.ط) | نسبة التوريد |  | Material delivery
شبكة الصرف الصناعي |  | 19706040.6 | 6.163% | شبكة تصريف مياة السيول | 73040 | 82309 | -9269 | 112.7% |  | Storm water
شبكة مياه الأمطار |  | 161546482.43 | 50.52% | شبكة الصرف الصحي | 29561 | 9759 | 19802 | 33.01% |  | Sewage
|  | 319744875.73 |  | شبكة المياة | 23742 | 11493 | 12249 | 48.41% |  | Potable Water Network
|  |  |  | شبكة الري | 70983 | 67778 | 3205 | 95.48% |  | TSE
معالم البرنامج الزمني |  |  |  | إنارة الطرق وشبكة الإتصالات m | 65175 | 46842 | 65175 | 71.87% |  | Street Lighting and telecommunication Network
البند |  | التاريخ حسب الجدول الزمني | ملاحظة | البردورات مسبقة الصب - متر طولي | 313864 | 15084 | 298780 | 4.806% |  | Kerbstone
استلام الموقع |  | 2024-07-29 | تم الإنتهاء | انترلوك - متر مربع | 59537.28 | 4088.24 | 55449.04 | 6.867% |  | Interlock
تجهيزات الموقع |  | 2024-08-29 | تم الإنتهاء | التحديات والعوائق
تقديم خطة العمل والبرنامج الزمني |  | 2024-08-29 | تم الإنتهاء | 1-
تقديم واعتماد المخططات والمواد |  | 2024-10-29 | جاري أعمال التنفيذ | 2-
الانتهاء من نطاق أعمال الشبكات العميقة والكهرباء |  | 2025-07-29 | جاري أعمال التوريد | 3-
الانتهاء من نطاق أعمال شبكات المياة |  | 2025-09-29 | جاري أعمال التوريد | 4-
الانتهاء من نطاق أعمال الطرق |  | 2025-11-29 | جاري أعمال التوريد | 5-
الانتهاء من نطاق كامل أعمال المشروع |  | 2026-07-28 | جاري أعمال التنفيذ | 6-
الانتهاء من نطاق كامل أعمال المشروع |  | 2026-07-28 | جاري أعمال التنفيذ | 7-
[7 empty] | 0.45148 | 0.19309