## Failed Start Activities
As of: 11-Oct-2026 | Playgrounds Initiative - Qassim, Hail & Tabuk Project
Activity ID | Activity Name | BL Project Start | Start | Remarks
PLAYGROUNDS INITIATIVE - QASSIM, HAIL & TABUK - 11-Oct-2026 |  | 2026-06-25 | 2026-10-10
QASSIM |  | 2026-06-25 | 2026-10-10
PROCUREMENT |  | 2026-06-25 | 2026-10-10
LONG LEAD ITEMS |  | 2026-06-25 | 2026-10-10
MANUFACTURE / FABRICATION |  | 2026-06-25 | 2026-10-10
METAL WORK |  | 2026-06-25 | 2026-10-10
PG-Q-PR-LL-MT-MF-20_R | Curtain Wall(Remaining) | 2026-06-25 | 2026-10-10
DELIVERY TO SITE |  | 2026-07-25 | 2026-11-08
METAL WORK |  | 2026-07-25 | 2026-11-08
PG-Q-PR-LL-MT-DL-20_R | Curtain Wall(Remaining) | 2026-07-25 | 2026-11-08
CONSTRUCTION STAGE |  | 2026-07-19 | 2026-10-10
PLAYGROUND AND LANDSCAPING WORKS |  | 2026-07-19 | 2026-10-10
PLAYGROUND WORKS |  | 2026-09-20 | 2026-10-20
PADEL PLAYGROUND WORKS |  | 2026-09-20 | 2026-10-20
PG-Q-CON-EX-PD-50 | Tempered Glass Installation | 2026-09-20 | 2026-10-20
GENERAL SITE WORKS |  | 2026-07-19 | 2026-10-12
FENCE WORKS |  | 2026-09-02 | 2026-10-21
PG-Q-CON-EX-GN-FN-50 | Installation of Gates | 2026-09-02 | 2026-10-21
MECHANICAL WORK |  | 2026-07-19 | 2026-10-12
STORM WATER AND UTILITY WORK |  | 2026-07-19 | 2026-10-12
PG-Q-CON-EX-GN-M-50 | Concrete Encasement | 2026-07-19 | 2026-10-12
PG-Q-CON-EX-GN-M-60 | Backfilling & Compaction | 2026-07-27 | 2026-10-20
PG-Q-CON-EX-GN-M-70 | Surface Reinstatement & Civil Works | 2026-08-10 | 2026-10-29
FIRE PROTECTION SYSTEM |  | 2026-08-17 | 2026-11-05
PG-Q-CON-EX-GN-M-110 | Fire Extinguisher Installation | 2026-08-17 | 2026-11-05
ELECTRICAL WORK |  | 2026-09-01 | 2026-11-08
POWER, LIGHTING & GROUNDING |  | 2026-09-01 | 2026-11-08
PG-Q-CON-EX-GN-E-40 | KWH Meter and MDB Installation | 2026-09-01 | 2026-11-08
PG-Q-CON-EX-GN-E-50 | Power Panels and Distribution Boards | 2026-09-03 | 2026-11-10
PG-Q-CON-EX-GN-E-70 | Wiring Works | 2026-09-13 | 2026-11-17
PG-Q-CON-EX-GN-E-80 | Lighting Fixtures with outlets Installation | 2026-09-16 | 2026-11-21
ELV SYSTEMS (TELECOM, DATA, AV & CCTV) |  | 2026-09-21 | 2026-11-25
PG-Q-CON-EX-GN-E-100 | Fiber Optic Pull Box Installation | 2026-09-26 | 2026-11-29
PG-Q-CON-EX-GN-E-110 | Telephone and Data Outlet Installation | 2026-09-29 | 2026-12-02
PG-Q-CON-EX-GN-E-120 | Telecom Equipment and AV HDMI Installation | 2026-10-04 | 2026-12-07
PG-Q-CON-EX-GN-E-130 | CCTV Rack / Cabinet Installation | 2026-10-08 | 2026-12-12
PG-Q-CON-EX-GN-E-90 | ELV Containment & Cabling Works | 2026-09-21 | 2026-11-25
FIRE ALARM SYSTEM |  | 2026-09-26 | 2026-11-29
PG-Q-CON-EX-GN-E-160 | Fire Alarm Containment & Cabling | 2026-09-26 | 2026-11-29
PG-Q-CON-EX-GN-E-170 | Fire Alarm Control Panel (FACP) Installation | 2026-10-05 | 2026-12-08
TANK WORKS |  | 2026-08-11 | 2026-10-10
WATER STORAGE TANK |  | 2026-08-11 | 2026-10-10
PG-Q-CON-EX-TW-IR-40 | GRP Water Tank Installation | 2026-08-11 | 2026-10-10
AIR DOME CONSTRUCTION |  | 2026-08-22 | 2026-10-11
CIVIL WORK |  | 2026-08-22 | 2026-10-11
PG-Q-CON-EX-AD-CL-70 | Installation of Steel Cable Structural System | 2026-08-22 | 2026-10-11
PG-Q-CON-EX-AD-CL-80 | Installation of Membrane System | 2026-09-02 | 2026-10-22
MECHANICAL WORK |  | 2026-09-12 | 2026-11-01
PG-Q-CON-EX-AD-ME-10 | Installation of Main Air Package Units | 2026-09-12 | 2026-11-01
PG-Q-CON-EX-AD-ME-20 | Installation of Backup Air Package Unit | 2026-09-17 | 2026-11-07
PG-Q-CON-EX-AD-ME-30 | Installation of Complete HVAC System | 2026-09-24 | 2026-11-12
ELECTRICAL WORK |  | 2026-08-31 | 2026-10-15
PG-Q-CON-EX-AD-EL-20 | Installation of Lighting System | 2026-08-31 | 2026-10-15
PG-Q-CON-EX-AD-EL-30 | Electrical Connections to Main Power Source (Excluding kWh Meter) | 2026-10-01 | 2026-11-19
PG-Q-CON-EX-AD-EL-40 | Installation of Backup Generator | 2026-10-07 | 2026-11-25
HAIL |  | 2026-06-25 | 2026-10-10
PROCUREMENT |  | 2026-06-25 | 2026-10-10
LONG LEAD ITEMS |  | 2026-06-25 | 2026-10-10
MANUFACTURE / FABRICATION |  | 2026-06-25 | 2026-10-10
METAL WORK |  | 2026-06-25 | 2026-10-10
PG-H-PR-LL-MT-MF-20_R | Curtain Wall(Remaining) | 2026-06-25 | 2026-10-10
CONSTRUCTION STAGE |  | 2026-07-13 | 2026-10-11
PLAYGROUND AND LANDSCAPING WORKS |  | 2026-07-13 | 2026-10-12
GENERAL SITE WORKS |  | 2026-07-13 | 2026-10-12
FENCE WORKS |  | 2026-08-12 | 2026-10-12
PG-H-CON-EX-GN-FN-50 | Installation of Gates | 2026-08-12 | 2026-10-12
MECHANICAL WORK |  | 2026-07-13 | 2026-10-12
STORM WATER AND UTILITY WORK |  | 2026-07-13 | 2026-10-12
PG-H-CON-EX-GN-M-40 | 150 mm uPVC pipe laying & jointing | 2026-07-13 | 2026-10-12
PG-H-CON-EX-GN-M-50 | Concrete Encasement | 2026-07-18 | 2026-10-17
PG-H-CON-EX-GN-M-60 | Backfilling & Compaction | 2026-07-21 | 2026-10-20
PG-H-CON-EX-GN-M-70 | Surface Reinstatement & Civil Works | 2026-08-01 | 2026-10-28
IRRIGATION SYSTEM WORKS |  | 2026-07-28 | 2026-10-25
PG-H-CON-EX-GN-M-100 | Installation of Bubblers and Sprinklers | 2026-07-28 | 2026-10-25
FIRE PROTECTION SYSTEM |  | 2026-08-05 | 2026-11-02
PG-H-CON-EX-GN-M-110 | Fire Extinguisher Installation | 2026-08-05 | 2026-11-02
ELECTRICAL WORK |  | 2026-08-17 | 2026-11-04
POWER, LIGHTING & GROUNDING |  | 2026-08-17 | 2026-11-04
PG-H-CON-EX-GN-E-30 | Lightning Protection System (LPS) | 2026-08-17 | 2026-11-04
PG-H-CON-EX-GN-E-40 | KWH Meter and MDB Installation | 2026-08-20 | 2026-11-08
PG-H-CON-EX-GN-E-50 | Power Panels and Distribution Boards | 2026-08-23 | 2026-11-10
PG-H-CON-EX-GN-E-60 | Site Lighting Poles Installation | 2026-08-29 | 2026-11-16
PG-H-CON-EX-GN-E-70 | Wiring Works | 2026-09-01 | 2026-11-19
PG-H-CON-EX-GN-E-80 | Lighting Fixtures with outlets Installation | 2026-09-05 | 2026-11-23
ELV SYSTEMS (TELECOM, DATA, AV & CCTV) |  | 2026-09-09 | 2026-11-28
PG-H-CON-EX-GN-E-100 | Fiber Optic Pull Box Installation | 2026-09-13 | 2026-12-01
PG-H-CON-EX-GN-E-110 | Telephone and Data Outlet Installation | 2026-09-16 | 2026-12-05
PG-H-CON-EX-GN-E-120 | Telecom Equipment and AV HDMI Installation | 2026-09-21 | 2026-12-09
PG-H-CON-EX-GN-E-130 | CCTV Rack / Cabinet Installation | 2026-09-27 | 2026-12-14
PG-H-CON-EX-GN-E-140 | NVR and CCTV Monitor Installation | 2026-10-01 | 2026-12-19
PG-H-CON-EX-GN-E-150 | IP Camera Installation | 2026-10-06 | 2026-12-23
PG-H-CON-EX-GN-E-90 | ELV Containment & Cabling Works | 2026-09-09 | 2026-11-28
FIRE ALARM SYSTEM |  | 2026-09-13 | 2026-12-01
PG-H-CON-EX-GN-E-160 | Fire Alarm Containment & Cabling | 2026-09-13 | 2026-12-01
PG-H-CON-EX-GN-E-170 | Fire Alarm Control Panel (FACP) Installation | 2026-09-22 | 2026-12-10
PG-H-CON-EX-GN-E-180 | Initiating Devices (Detectors & Manual Pull Station) | 2026-10-03 | 2026-12-20
LANDSCAPING WORKS |  | 2026-10-06 | 2026-11-11
SOFTSCAPE WORK |  | 2026-10-06 | 2026-11-11
PG-H-CON-EX-LS-SS-10 | Planting Trees | 2026-10-06 | 2026-11-11
TANK WORKS |  | 2026-08-17 | 2026-10-17
SEPTIC TANK |  | 2026-08-17 | 2026-10-17
PG-H-CON-EX-TW-ST-60 | Finishing Work | 2026-08-17 | 2026-10-17
PG-H-CON-EX-TW-ST-70 | Backfilling | 2026-08-25 | 2026-10-25
WATER STORAGE TANK |  | 2026-09-14 | 2026-11-01
PG-H-CON-EX-TW-IR-40 | GRP Water Tank Installation | 2026-09-14 | 2026-11-01
TOILET BUILDING WORKS |  | 2026-08-22 | 2026-10-11
CIVIL WORK |  | 2026-10-04 | 2026-11-12
ARCHITECTURAL WORK |  | 2026-10-04 | 2026-11-12
ROOF FINISHES |  | 2026-10-04 | 2026-11-12
PG-H-CON-B-AR-RF-30 | Steel ladder and Steel roof scupper Installation | 2026-10-04 | 2026-11-12
MEP WORK |  | 2026-08-22 | 2026-10-11
MECANICAL WORKS |  | 2026-08-22 | 2026-10-11
FIRE FIGHTING SYSTEM |  | 2026-10-06 | 2026-11-15
PG-H-CON-B-GF-FF-10 | Fire Extinguisher Installation | 2026-10-06 | 2026-11-15
SEWER AND DRAINAGE SYSTEM |  | 2026-08-22 | 2026-10-11
PG-H-CON-B-GF-DR-30 | Sanitaryware Installation (Final Fix) | 2026-08-22 | 2026-10-11
TABUK |  | 2026-07-12 | 2026-10-11
CONSTRUCTION STAGE |  | 2026-07-12 | 2026-10-11
PLAYGROUND AND LANDSCAPING WORKS |  | 2026-07-12 | 2026-10-11
PLAYGROUND WORKS |  | 2026-09-21 | 2026-10-17
PADEL PLAYGROUND WORKS |  | 2026-09-21 | 2026-10-17
PG-T-CON-EX-PD-50 | Tempered Glass Installation | 2026-09-21 | 2026-10-17
GENERAL SITE WORKS |  | 2026-07-12 | 2026-10-11
FENCE WORKS |  | 2026-08-11 | 2026-10-11
PG-T-CON-EX-GN-FN-50 | Installation of Gates | 2026-08-11 | 2026-10-11
MECHANICAL WORK |  | 2026-07-12 | 2026-10-12
STORM WATER AND UTILITY WORK |  | 2026-07-12 | 2026-10-12
PG-T-CON-EX-GN-M-50 | Concrete Encasement | 2026-07-12 | 2026-10-12
PG-T-CON-EX-GN-M-60 | Backfilling & Compaction | 2026-07-15 | 2026-10-15
PG-T-CON-EX-GN-M-70 | Surface Reinstatement & Civil Works | 2026-08-01 | 2026-10-21
FIRE PROTECTION SYSTEM |  | 2026-08-05 | 2026-10-26
PG-T-CON-EX-GN-M-110 | Fire Extinguisher Installation | 2026-08-05 | 2026-10-26
ELECTRICAL WORK |  | 2026-09-20 | 2026-11-15
POWER, LIGHTING & GROUNDING |  | 2026-09-20 | 2026-11-15
PG-T-CON-EX-GN-E-80 | Lighting Fixtures with outlets Installation | 2026-09-20 | 2026-11-15
FIRE ALARM SYSTEM |  | 2026-10-01 | 2026-11-24
PG-T-CON-EX-GN-E-160 | Fire Alarm Containment & Cabling | 2026-10-01 | 2026-11-24
TANK WORKS |  | 2026-07-18 | 2026-10-13
SEPTIC TANK |  | 2026-07-18 | 2026-10-13
PG-T-CON-EX-TW-ST-50 | RCC Slab | 2026-07-18 | 2026-10-13
PG-T-CON-EX-TW-ST-60 | Finishing Work | 2026-08-18 | 2026-10-28
WATER STORAGE TANK |  | 2026-09-21 | 2026-11-07
PG-T-CON-EX-TW-IR-40 | GRP Water Tank Installation | 2026-09-21 | 2026-11-07
AIR DOME CONSTRUCTION |  | 2026-08-26 | 2026-10-21
CIVIL WORK |  | 2026-08-26 | 2026-10-21
PG-T-CON-EX-AD-CL-70 | Installation of Steel Cable Structural System | 2026-08-26 | 2026-10-21
PG-T-CON-EX-AD-CL-80 | Installation of Membrane System | 2026-09-06 | 2026-11-01
MECHANICAL WORK |  | 2026-09-15 | 2026-11-10
PG-T-CON-EX-AD-ME-10 | Installation of Main Air Package Units | 2026-09-15 | 2026-11-10
PG-T-CON-EX-AD-ME-20 | Installation of Backup Air Package Unit | 2026-09-21 | 2026-11-16
PG-T-CON-EX-AD-ME-30 | Installation of Complete HVAC System | 2026-10-06 | 2026-11-30
ELECTRICAL WORK |  | 2026-09-28 | 2026-11-22
PG-T-CON-EX-AD-EL-10 | Installation of Electrical Boxes & MDBs | 2026-09-28 | 2026-11-22
PG-T-CON-EX-AD-EL-20 | Installation of Lighting System | 2026-10-06 | 2026-11-30