## Tracking Progress
ActivityID | Activity ID | Activity Name | BL Project Total Cost | Previous Percentage ( % ) | Progress Variance ( % ) | Total Progress % | Cumulative Amount | Curent Amount
Infrastructure Development for Madinah Industrial city Phase 1-A | JDH4-02-007 - Land Development of Jeddah Oasis |  | 57304347.86 | 91.11% | 2.2% | 93.31% | 53468556.35 | 1260695.6529
Key Milestones | Key Milestones |  | 0 |  | 0%
General Milestone | General Milestone |  | 0 |  | 0%
JDH4-02-007-MS-1000 | JDH4-02-007-MS-1000 | Project Commencement Date | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MS-1010 | JDH4-02-007-MS-1010 | Project Completion Date | 0 | 0% | 0% | 0% | 0 | 0
Contractual Milestone | Contractual Milestone |  | 0 |  | 0%
Engineering & Mobilization | Engineering & Mobilization |  | 0 |  | 0%
JDH4-02-007-MS-1020 | JDH4-02-007-MS-1020 | Completion of Mobilization | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MS-1030 | JDH4-02-007-MS-1030 | Submission of the Work Plan (Baseline Programme) | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MS-1040 | JDH4-02-007-MS-1040 | Submission and Approval of Drawings and Materials | 0 |  | 0%
Construction | Construction |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MS-1050 | JDH4-02-007-MS-1050 | Completion of Earthworks & Site Grading For Plots | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MS-1060 | JDH4-02-007-MS-1060 | Completion of Sewerage networks | 0 |  | 0%
JDH4-02-007-MS-1070 | JDH4-02-007-MS-1070 | Completion of Road Works | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MS-1080 | JDH4-02-007-MS-1080 | Completion of Potable Water Network | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MS-1090 | JDH4-02-007-MS-1090 | Completion of TSE Network | 0 |  | 0%
JDH4-02-007-MS-1100 | JDH4-02-007-MS-1100 | Completion of Electrical Networks | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MS-1110 | JDH4-02-007-MS-1110 | Completion of Entire Project | 0 | 0% | 0% | 0% | 0 | 0
Monitoring & Controlling Milestone | Monitoring & Controlling Milestone |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MS-1130 | JDH4-02-007-MS-1130 | Approval of Electrical Network Materials By SEC | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MS-1120 | JDH4-02-007-MS-1120 | Approval of Electrical Network Shop DWGs By SEC | 0 | 100% | 0% | 100% | 0 | 0
Mobilization | Mobilization |  | 0 | 0% | 0% | 0% | 0 | 0
Site Facilities & Offices | Site Facilities & Offices |  | 0 |  | 0%
JDH4-02-007-MB-1000 | JDH4-02-007-MB-1000 | Site Layout Plan | 0 |  | 0%
JDH4-02-007-MB-1010 | JDH4-02-007-MB-1010 | Clear & Grub for Offices & Access Road | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MB-1020 | JDH4-02-007-MB-1020 | Construct Site Access Roads | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MB-1040 | JDH4-02-007-MB-1040 | Construct Site Offices & Storage | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MB-1030 | JDH4-02-007-MB-1030 | Construct Temporary Fence | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MB-1060 | JDH4-02-007-MB-1060 | Install Site Facilities | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MB-1070 | JDH4-02-007-MB-1070 | Electrical Works & Connections | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MB-1090 | JDH4-02-007-MB-1090 | Mobilization of Equipment | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MB-1100 | JDH4-02-007-MB-1100 | Mobilization of Manpower | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MB-1080 | JDH4-02-007-MB-1080 | Construct Parking Sheds | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MB-1050 | JDH4-02-007-MB-1050 | Install Project Signs | 0 | 100% | 0% | 100% | 0 | 0
Topographic Survey | Topographic Survey |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-TP-1000 | JDH4-02-007-TP-1000 | Site Survey Works | 0 |  | 0%
Permit's and Authority Approvals | Permit's and Authority Approvals |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PA-1000 | JDH4-02-007-PA-1000 | Excavation & Backfilling Permit Permit | 0 |  | 0%
JDH4-02-007-PA-1010 | JDH4-02-007-PA-1010 | Saudi Electricity Company Permit | 0 | 100% | 0% | 100% | 0 | 0
Preliminary Submittals | Preliminary Submittals |  | 0 |  | 0%
Preparation and Submittal by Contractor's | Preparation and Submittal by Contractor's |  | 0 |  | 0%
JDH4-02-007-PS-1020 | JDH4-02-007-PS-1020 | Preparation and Submittal of Quality Management Plan | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PS-1030 | JDH4-02-007-PS-1030 | Preparation and Submittal of Safety Management Plan | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PS-1040 | JDH4-02-007-PS-1040 | Preparation and Submittal of Organization Chart | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PS-1050 | JDH4-02-007-PS-1050 | Preparation and Submittal of Communication Plan | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PS-1000 | JDH4-02-007-PS-1000 | Preparation and Submittal of Detailed Work Order Programme (baseline schedule) | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PS-1010 | JDH4-02-007-PS-1010 | Preparation and Submittal of Project Execution Plan | 0 | 100% | 0% | 100% | 0 | 0
Approval by the Employer's | Approval by the Employer's |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PS-1100 | JDH4-02-007-PS-1100 | Approval of Organization Chart | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PS-1110 | JDH4-02-007-PS-1110 | Approval of Comminumcation Plan | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PS-1060 | JDH4-02-007-PS-1060 | Approval of Detailed Work Order Programme (baseline schedule) | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PS-1080 | JDH4-02-007-PS-1080 | Approval of Quality Management Plan | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PS-1090 | JDH4-02-007-PS-1090 | Approval of Safety Management Plan | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PS-1070 | JDH4-02-007-PS-1070 | Approval of Project Execution Plan | 0 | 100% | 0% | 100% | 0 | 0
Engineering | Engineering |  | 1719130.43 | 100% | 0% | 100% | 1719130.43 | 0
Shop Drawings | Shop Drawings |  | 0 | 0% | 0% | 0% | 0 | 0
Shop Drawings Submittal | Shop Drawings Submittal |  | 0 | 0% | 0% | 0% | 0 | 0
Shop Drawings Submittal for Road Works | Shop Drawings Submittal for Road Works |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-EN-1040 | JDH4-02-007-EN-1040 | Shop DWG Submittal for Topographic Survey | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1050 | JDH4-02-007-EN-1050 | Shop DWG Submittal for Road Layout Plan | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1070 | JDH4-02-007-EN-1070 | Shop DWG Submittal for Road Setting Out | 0 |  | 0%
JDH4-02-007-EN-1080 | JDH4-02-007-EN-1080 | Shop DWG Submittal for Road Profiles | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1090 | JDH4-02-007-EN-1090 | Shop DWG Submittal for Grading Layout Plan | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1100 | JDH4-02-007-EN-1100 | Shop DWG Submittal for Curb Setting Out Points | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1120 | JDH4-02-007-EN-1120 | Shop DWG Submittal for Standards Details | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1060 | JDH4-02-007-EN-1060 | Shop DWG Submittal for Typical Cross Section | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1110 | JDH4-02-007-EN-1110 | Shop DWG Submittal for Signing & Marking Layout Plan | 0 | 100% | 0% | 100% | 0 | 0
Shop Drawings Submittal for Stormwater Network | Shop Drawings Submittal for Stormwater Network |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-EN-1250 | JDH4-02-007-EN-1250 | Shop DWG Submittal for Stormwater Plans | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1260 | JDH4-02-007-EN-1260 | Shop DWG Submittal for Stormwater Profiles | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1270 | JDH4-02-007-EN-1270 | Shop DWG Submittal for Stormwater Standard Details | 0 | 100% | 0% | 100% | 0 | 0
Shop Drawings Submittal for Sanitary Sewerage | Shop Drawings Submittal for Sanitary Sewerage |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-EN-1220 | JDH4-02-007-EN-1220 | Shop DWG Submittal for Sanitary Sewerage Plans | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1230 | JDH4-02-007-EN-1230 | Shop DWG Submittal for Sanitary Sewerage Profiles | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1240 | JDH4-02-007-EN-1240 | Shop DWG Submittal for Sanitary Sewerage Standard Details | 0 | 100% | 0% | 100% | 0 | 0
Shop Drawings Submittal for TSE Network | Shop Drawings Submittal for TSE Network |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-EN-1190 | JDH4-02-007-EN-1190 | Shop DWG Submittal for TSE Network Plans | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1200 | JDH4-02-007-EN-1200 | Shop DWG Submittal for TSE Profiles | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1210 | JDH4-02-007-EN-1210 | Shop DWG Submittal for TSE Standard Details | 0 | 100% | 0% | 100% | 0 | 0
Shop Drawings Submittal for Potable Water Network | Shop Drawings Submittal for Potable Water Network |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-EN-1160 | JDH4-02-007-EN-1160 | Shop DWG Submittal for Potable Water Plans | 0 |  | 0%
JDH4-02-007-EN-1170 | JDH4-02-007-EN-1170 | Shop DWG Submittal for Potable Water Profiles | 0 |  | 0%
JDH4-02-007-EN-1180 | JDH4-02-007-EN-1180 | Shop DWG Submittal for Potable Water Standard Details | 0 |  | 0%
Shop Drawings Submittal for Electrical Network | Shop Drawings Submittal for Electrical Network |  | 0 |  | 0%
JDH4-02-007-EN-1130 | JDH4-02-007-EN-1130 | Shop DWG Submittal for Medium Voltage Network | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1140 | JDH4-02-007-EN-1140 | Shop DWG Submittal for Street Lighting | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1150 | JDH4-02-007-EN-1150 | Shop DWG Submittal for Low Voltage Network | 0 | 100% | 0% | 100% | 0 | 0
Shop Drawings Submittal for Telecommunications | Shop Drawings Submittal for Telecommunications |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-EN-1600 | JDH4-02-007-EN-1600 | Shop DWG Submittal for Telecommunications Works | 0 | 100% | 0% | 100% | 0 | 0
Shop Drawings Submittal for Earthing System | Shop Drawings Submittal for Earthing System |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-EN-1610 | JDH4-02-007-EN-1610 | Shop DWG Submittal for Earthing System | 0 | 100% | 0% | 100% | 0 | 0
Shop Drawings Submittal for Road Lighting | Shop Drawings Submittal for Road Lighting |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-EN-1000 | JDH4-02-007-EN-1000 | Shop DWG Submittal for Street Lighting General Arrangement | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1010 | JDH4-02-007-EN-1010 | Shop DWG Submittal for Street Lighting Network Layout | 0 |  | 0%
JDH4-02-007-EN-1020 | JDH4-02-007-EN-1020 | Shop DWG Submittal for Street Lighting Details | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1030 | JDH4-02-007-EN-1030 | Shop DWG Submittal for Street Lighting Single Line Diagram | 0 | 100% | 0% | 100% | 0 | 0
Shop Drawings Submittal for Sewage Lift Station | Shop Drawings Submittal for Sewage Lift Station |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-EN-1280 | JDH4-02-007-EN-1280 | Shop DWG Submittal for the Sewage Lift Station - Civil Works | 0 |  | 0%
JDH4-02-007-EN-1290 | JDH4-02-007-EN-1290 | Shop DWG Submittal for the Sewage Lift Station - Mechanical Works | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1310 | JDH4-02-007-EN-1310 | Shop DWG Submittal for the Sewage Lift Station - Finishing Works | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1300 | JDH4-02-007-EN-1300 | Shop DWG Submittal for the Sewage Lift Station - Electrical Works | 0 | 100% | 0% | 100% | 0 | 0
Shop Drawings Approval | Shop Drawings Approval |  | 0 |  | 0%
Shop Drawings Approval for Road Works | Shop Drawings Approval for Road Works |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-EN-1320 | JDH4-02-007-EN-1320 | Shop DWG Approval for Topographic Survey | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1330 | JDH4-02-007-EN-1330 | Shop DWG Approval for Road Layout Plan | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1350 | JDH4-02-007-EN-1350 | Shop DWG Approval for Road Setting Out | 0 |  | 0%
JDH4-02-007-EN-1360 | JDH4-02-007-EN-1360 | Shop DWG Approval for Road Profiles | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1370 | JDH4-02-007-EN-1370 | Shop DWG Approval for Grading Layout Plan | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1380 | JDH4-02-007-EN-1380 | Shop DWG Approval for Curb Setting Out Points | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1340 | JDH4-02-007-EN-1340 | Shop DWG Approval for Typical Cross Section | 0 |  | 0%
JDH4-02-007-EN-1390 | JDH4-02-007-EN-1390 | Shop DWG Approval for Signing & Marking Layout Plan | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1400 | JDH4-02-007-EN-1400 | Shop DWG Approval for Standards Details | 0 | 100% | 0% | 100% | 0 | 0
Shop Drawings Approval for Storm Network | Shop Drawings Approval for Storm Network |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-EN-1530 | JDH4-02-007-EN-1530 | Shop DWG Approval for Stormwater Plans | 0 |  | 0%
JDH4-02-007-EN-1540 | JDH4-02-007-EN-1540 | Shop DWG Approval for Stormwater Profiles | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1550 | JDH4-02-007-EN-1550 | Shop DWG Approval for Stormwater Standard Details | 0 | 100% | 0% | 100% | 0 | 0
Shop Drawings Approval for Sanitary Sewerage | Shop Drawings Approval for Sanitary Sewerage |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-EN-1510 | JDH4-02-007-EN-1510 | Shop DWG Approval for Sanitary Sewerage Profiles | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1520 | JDH4-02-007-EN-1520 | Shop DWG Approval for Sanitary Sewerage Standard Details | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1500 | JDH4-02-007-EN-1500 | Shop DWG Approval for Sanitary Sewerage Plans | 0 | 100% | 0% | 100% | 0 | 0
Shop Drawings Approval for TSE Network | Shop Drawings Approval for TSE Network |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-EN-1470 | JDH4-02-007-EN-1470 | Shop DWG Approval for TSE Network Plans | 0 |  | 0%
JDH4-02-007-EN-1480 | JDH4-02-007-EN-1480 | Shop DWG Approval for TSE Profiles | 0 |  | 0%
JDH4-02-007-EN-1490 | JDH4-02-007-EN-1490 | Shop DWG Approval for TSE Standard Details | 0 | 100% | 0% | 100% | 0 | 0
Shop Drawings Approval for Potable Water Network | Shop Drawings Approval for Potable Water Network |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-EN-1440 | JDH4-02-007-EN-1440 | Shop DWG Approval for Potable Water Plans | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1450 | JDH4-02-007-EN-1450 | Shop DWG Approval for Potable Water Profiles | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1460 | JDH4-02-007-EN-1460 | Shop DWG Approval for Potable Water Standard Details | 0 | 100% | 0% | 100% | 0 | 0
Shop Drawings Approval for Electrical Network | Shop Drawings Approval for Electrical Network |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-EN-1410 | JDH4-02-007-EN-1410 | Shop DWG Approval for Medium Voltage Network By SEC | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1420 | JDH4-02-007-EN-1420 | Shop DWG Approval for Street Lighting by By SEC | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1430 | JDH4-02-007-EN-1430 | Shop DWG Approval for Low Voltage Network By SEC | 0 | 100% | 0% | 100% | 0 | 0
Shop Drawings Approval for Telecommunications | Shop Drawings Approval for Telecommunications |  | 0 |  | 0%
JDH4-02-007-EN-1620 | JDH4-02-007-EN-1620 | Shop DWG Approval for Telecommunications Works | 0 | 100% | 0% | 100% | 0 | 0
Shop Drawings Approval for Earthing System | Shop Drawings Approval for Earthing System |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-EN-1630 | JDH4-02-007-EN-1630 | Shop DWG Approval for Earthing System By SEC | 0 | 100% | 0% | 100% | 0 | 0
Shop Drawings Approval for Road Lighting | Shop Drawings Approval for Road Lighting |  | 0 |  | 0%
JDH4-02-007-EN-1640 | JDH4-02-007-EN-1640 | Shop DWG Approval for Street Lighting General Arrangement By SEC | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1650 | JDH4-02-007-EN-1650 | Shop DWG Approval for Street Lighting Network Layout By SEC | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1660 | JDH4-02-007-EN-1660 | Shop DWG Approval for Street Lighting Details By SEC | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1670 | JDH4-02-007-EN-1670 | Shop DWG Approval for Street Lighting Single Line Diagram By SEC | 0 |  | 0%
Shop Drawings Approval for Sewage Lift Station | Shop Drawings Approval for Sewage Lift Station |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-EN-1700 | JDH4-02-007-EN-1700 | Shop DWG Approval for the Sewage Lift Station - Electrical Works | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1680 | JDH4-02-007-EN-1680 | Shop DWG Approval for the Sewage Lift Station - Civil Works | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1690 | JDH4-02-007-EN-1690 | Shop DWG Approval for the Sewage Lift Station - Mechanical Works | 0 |  | 0%
JDH4-02-007-EN-1710 | JDH4-02-007-EN-1710 | Shop DWG Approval for the Sewage Lift Station - Finishing Works | 0 | 100% | 0% | 100% | 0 | 0
Method Statements | Method Statements |  | 0 | 0% | 0% | 0% | 0 | 0
Method Statements Submittal | Method Statements Submittal |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-EN-1560 | JDH4-02-007-EN-1560 | Preparation & Submission of Method Statement for Earthworks | 0 |  | 0%
JDH4-02-007-EN-1570 | JDH4-02-007-EN-1570 | Preparation & Submission of Method Statement for Concrete Works | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1580 | JDH4-02-007-EN-1580 | Preparation & Submission of Method Statement for Waterproofing Works | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1590 | JDH4-02-007-EN-1590 | Preparation & Submission of Method Statement for Asphalt | 0 | 100% | 0% | 100% | 0 | 0
Method Statements Approval | Method Statements Approval |  | 0 |  | 0%
JDH4-02-007-EN-1720 | JDH4-02-007-EN-1720 | Approval of Method Statement for Earthworks | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1730 | JDH4-02-007-EN-1730 | Approval of Method Statement for Concrete Works | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1740 | JDH4-02-007-EN-1740 | Approval of Method Statement for Waterproofing Works | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1750 | JDH4-02-007-EN-1750 | Approval of Method Statement for Asphalt | 0 | 100% | 0% | 100% | 0 | 0
Method Statements Staging Time | Method Statements Staging Time |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-EN-1760 | JDH4-02-007-EN-1760 | Staging Time of Method Statement for Earthworks | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1770 | JDH4-02-007-EN-1770 | Staging Time of Method Statement for Concrete Works | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-EN-1780 | JDH4-02-007-EN-1780 | Staging Time of Method Statement for Waterproofing Works | 0 |  | 0%
JDH4-02-007-EN-1790 | JDH4-02-007-EN-1790 | Staging Time of Method Statement for Asphalt | 0 |  | 0%
Pre-qualification and Material | Pre-qualification and Material |  | 1719130.43 | 100% | 0% | 100% | 1719130.43 | 0
Pre-qualification | Pre-qualification |  | 0 | 0% | 0% | 0% | 0 | 0
Road Works - Civil | Road Works - Civil |  | 0 | 0% | 0% | 0% | 0 | 0
Steel Reinforcement | Steel Reinforcement |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1580 | JDH4-02-007-SB-1580 | Pre-Qualification Submittal for Steel Reinforcement | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1590 | JDH4-02-007-SB-1590 | Pre-Qualification Approval for Steel Reinforcement | 0 | 100% | 0% | 100% | 0 | 0
Ready Mixed Concrete | Ready Mixed Concrete |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1600 | JDH4-02-007-SB-1600 | Pre-Qualification Submittal for Ready Mixed Concrete | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1610 | JDH4-02-007-SB-1610 | Pre-Qualification Approval for Ready Mixed Concrete | 0 | 100% | 0% | 100% | 0 | 0
Water Proofing | Water Proofing |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1620 | JDH4-02-007-SB-1620 | Pre-Qualification Submittal for Water Proofing | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1630 | JDH4-02-007-SB-1630 | Pre-Qualification Approval for Water Proofing | 0 | 100% | 0% | 100% | 0 | 0
Aggregate Base Course | Aggregate Base Course |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1000 | JDH4-02-007-SB-1000 | Pre-Qualification Submittal for Aggregate Base Cource | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1010 | JDH4-02-007-SB-1010 | Pre-Qualification Approval for Aggregate Base Cource | 0 | 100% | 0% | 100% | 0 | 0
Bituminous Base & Wearing Course | Bituminous Base & Wearing Course |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1020 | JDH4-02-007-SB-1020 | Pre-Qualification Submittal for Bituminous Base & Wearing Cource | 0 |  | 0%
JDH4-02-007-SB-1030 | JDH4-02-007-SB-1030 | Pre-Qualification Approval for Bituminous & Wearing Cource | 0 | 100% | 0% | 100% | 0 | 0
Precast Concrete Kerb | Precast Concrete Kerb |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1050 | JDH4-02-007-SB-1050 | Pre-Qualification Approval for Precast Concrete Kerb | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1040 | JDH4-02-007-SB-1040 | Pre-Qualification Submittal for Precast Concrete Kerb | 0 | 100% | 0% | 100% | 0 | 0
Interlocking Block Pavers | Interlocking Block Pavers |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1060 | JDH4-02-007-SB-1060 | Pre-Qualification Submittal for Interlocking Block Pavers | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1070 | JDH4-02-007-SB-1070 | Pre-Qualification Approval for Interlocking Block Pavers | 0 | 100% | 0% | 100% | 0 | 0
Pavement Markings | Pavement Markings |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1080 | JDH4-02-007-SB-1080 | Pre-Qualification Submittal for Pavement Markings | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1090 | JDH4-02-007-SB-1090 | Pre-Qualification Approval for Pavement Markings | 0 | 100% | 0% | 100% | 0 | 0
Traffic Signs | Traffic Signs |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1100 | JDH4-02-007-SB-1100 | Pre-Qualification Submittal for Traffic Signs | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1110 | JDH4-02-007-SB-1110 | Pre-Qualification Approval for Traffic Signs | 0 | 100% | 0% | 100% | 0 | 0
Storm Network | Storm Network |  | 0 | 0% | 0% | 0% | 0 | 0
GRP Pipes | GRP Pipes |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1260 | JDH4-02-007-SB-1260 | Pre-Qualification Submittal for GRP Pipe | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1270 | JDH4-02-007-SB-1270 | Pre-Qualification Approval for GRP Pipe | 0 |  | 0%
Catch Basin | Catch Basin |  | 0 |  | 0%
JDH4-02-007-SB-1640 | JDH4-02-007-SB-1640 | Pre-Qualification Submittal for Catch Basin | 0 |  | 0%
JDH4-02-007-SB-1650 | JDH4-02-007-SB-1650 | Pre-Qualification Approval for Catch Basin | 0 | 100% | 0% | 100% | 0 | 0
Inlet Manholes | Inlet Manholes |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1280 | JDH4-02-007-SB-1280 | Pre-Qualification Submittal for Inlet Manholes | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1290 | JDH4-02-007-SB-1290 | Pre-Qualification Approval for Inlet Manholes | 0 | 100% | 0% | 100% | 0 | 0
Sanitary Sewerage | Sanitary Sewerage |  | 0 | 0% | 0% | 0% | 0 | 0
GRP Pipes | GRP Pipes |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1220 | JDH4-02-007-SB-1220 | Pre-Qualification Submittal for GRP Pipe | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1230 | JDH4-02-007-SB-1230 | Pre-Qualification Approval for GRP Pipe | 0 | 100% | 0% | 100% | 0 | 0
Manholes | Manholes |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1240 | JDH4-02-007-SB-1240 | Pre-Qualification Submittal for Manholes | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1250 | JDH4-02-007-SB-1250 | Pre-Qualification Approval for Manholes | 0 | 100% | 0% | 100% | 0 | 0
TSE Network | TSE Network |  | 0 | 0% | 0% | 0% | 0 | 0
HDPE Pipe (PN 16) | HDPE Pipe (PN 16) |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1200 | JDH4-02-007-SB-1200 | Pre-Qualification Submittal for HDPE Pipe (PN 16) | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1210 | JDH4-02-007-SB-1210 | Pre-Qualification Approval for HDPE Pipe (PN 16) | 0 | 100% | 0% | 100% | 0 | 0
Valves / Chambers | Valves / Chambers |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1440 | JDH4-02-007-SB-1440 | Pre-Qualification Submittal for Valves / Chambers | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1450 | JDH4-02-007-SB-1450 | Pre-Qualification Approval for Valves / Chambers | 0 | 100% | 0% | 100% | 0 | 0
Risers | Risers |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1460 | JDH4-02-007-SB-1460 | Pre-Qualification Submittal for Risers | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1470 | JDH4-02-007-SB-1470 | Pre-Qualification Approval for Risers | 0 | 100% | 0% | 100% | 0 | 0
Potable Water Network | Potable Water Network |  | 0 | 0% | 0% | 0% | 0 | 0
HDPE Pipe (PN 16) | HDPE Pipe (PN 16) |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1180 | JDH4-02-007-SB-1180 | Pre-Qualification Submittal for HDPE Pipe (PN 16) | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1190 | JDH4-02-007-SB-1190 | Pre-Qualification Approval for HDPE Pipe (PN 16) | 0 | 100% | 0% | 100% | 0 | 0
Valves / Chambers | Valves / Chambers |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1420 | JDH4-02-007-SB-1420 | Pre-Qualification Submittal for Valves / Chambers | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1430 | JDH4-02-007-SB-1430 | Pre-Qualification Approval for Valves / Chambers | 0 | 100% | 0% | 100% | 0 | 0
Fire Hydrant | Fire Hydrant |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1660 | JDH4-02-007-SB-1660 | Pre-Qualification Submittal for Fire Hydrant | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1670 | JDH4-02-007-SB-1670 | Pre-Qualification Approval for Fire Hydrant | 0 |  | 0%
Electrical Network | Electrical Network |  | 0 | 0% | 0% | 0% | 0 | 0
Pipe for the Duct | Pipe for the Duct |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1120 | JDH4-02-007-SB-1120 | Pre-Qualification Submittal for Pipe for the Duct | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1130 | JDH4-02-007-SB-1130 | Pre-Qualification Approval for Pipe for the Duct | 0 | 100% | 0% | 100% | 0 | 0
Low Voltage Cables | Low Voltage Cables |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1320 | JDH4-02-007-SB-1320 | Pre-Qualification Submittal for Low Voltage Cables | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1330 | JDH4-02-007-SB-1330 | Pre-Qualification Approval for Low Voltage Cables | 0 | 100% | 0% | 100% | 0 | 0
Earthing System | Earthing System |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1160 | JDH4-02-007-SB-1160 | Pre-Qualification Submittal for Earthing System | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1170 | JDH4-02-007-SB-1170 | Pre-Qualification Approval for Earthing System | 0 | 100% | 0% | 100% | 0 | 0
Medium Voltage Cable | Medium Voltage Cable |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1300 | JDH4-02-007-SB-1300 | Pre-Qualification Submittal for Medium Voltage Cable | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1310 | JDH4-02-007-SB-1310 | Pre-Qualification Approval for Medium Voltage Cable | 0 | 100% | 0% | 100% | 0 | 0
Low Voltage Distribution Panel | Low Voltage Distribution Panel |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1140 | JDH4-02-007-SB-1140 | Pre-Qualification Submittal for Low Voltage Distribution Panel | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1150 | JDH4-02-007-SB-1150 | Pre-Qualification Approval for Low Voltage Distribution Panel | 0 | 100% | 0% | 100% | 0 | 0
Unit Sub Station | Unit Sub Station |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1380 | JDH4-02-007-SB-1380 | Pre-Qualification Submittal for Unit Sub Station | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1390 | JDH4-02-007-SB-1390 | Pre-Qualification Approval for Unit Sub Station | 0 | 100% | 0% | 100% | 0 | 0
Ring Main Unit (RMU) | Ring Main Unit (RMU) |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1400 | JDH4-02-007-SB-1400 | Pre-Qualification Submittal for Ring main Unit (RMU) | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1410 | JDH4-02-007-SB-1410 | Pre-Qualification Approval for Ring main Unit (RMU) | 0 | 100% | 0% | 100% | 0 | 0
Lighting poles | Lighting poles |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1340 | JDH4-02-007-SB-1340 | Pre-Qualification Submittal for Lighting poles | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1350 | JDH4-02-007-SB-1350 | Pre-Qualification Approval for Lighting poles | 0 | 100% | 0% | 100% | 0 | 0
Lighting panels/Feeder Pillers | Lighting panels/Feeder Pillers |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1520 | JDH4-02-007-SB-1520 | Pre-Qualification Submittal for Lighting panels/Feeder Pillers | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1530 | JDH4-02-007-SB-1530 | Pre-Qualification Approval for Lighting panels/Feeder Pillers | 0 | 100% | 0% | 100% | 0 | 0
Street Lighting Luminaire | Street Lighting Luminaire |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1360 | JDH4-02-007-SB-1360 | Pre-Qualification Submittal for Street Lighting Luminaire | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1370 | JDH4-02-007-SB-1370 | Pre-Qualification Approval for Street Lighting Luminaire | 0 | 100% | 0% | 100% | 0 | 0
Telecommunications | Telecommunications |  | 0 | 0% | 0% | 0% | 0 | 0
Pipe for the Duct | Pipe for the Duct |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1550 | JDH4-02-007-SB-1550 | Pre-Qualification Approval for Pipe for the Duct | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1540 | JDH4-02-007-SB-1540 | Pre-Qualification Submittal for Pipe for the Duct | 0 | 100% | 0% | 100% | 0 | 0
Sewage Lift Station | Sewage Lift Station |  | 0 | 0% | 0% | 0% | 0 | 0
Thermal & Moisture Protection | Thermal & Moisture Protection |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1490 | JDH4-02-007-SB-1490 | Pre-Qualification Submittal for Thermal & Moisture Protection | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1510 | JDH4-02-007-SB-1510 | Pre-Qualification Approval for Thermal & Moisture Protection | 0 | 100% | 0% | 100% | 0 | 0
Metals | Metals |  | 0 |  | 0%
JDH4-02-007-SB-1480 | JDH4-02-007-SB-1480 | Pre-Qualification Submittal for Metal | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1500 | JDH4-02-007-SB-1500 | Pre-Qualification Approval for Metal | 0 | 100% | 0% | 100% | 0 | 0
Pumps | Pumps |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1560 | JDH4-02-007-SB-1560 | Pre-Qualification Submittal for pumps | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1570 | JDH4-02-007-SB-1570 | Pre-Qualification Approval for pumps | 0 | 100% | 0% | 100% | 0 | 0
Pipes,Fittings & Valves | Pipes,Fittings & Valves |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1680 | JDH4-02-007-SB-1680 | Pre-Qualification Submittal for Pipes,Fittings & Valves | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1700 | JDH4-02-007-SB-1700 | Pre-Qualification Approval for Pipes,Fittings & Valves | 0 | 100% | 0% | 100% | 0 | 0
Odours scrubbing system | Odours scrubbing system |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1690 | JDH4-02-007-SB-1690 | Pre-Qualification Submittal for Odours Scrubbing System | 0 |  | 0%
JDH4-02-007-SB-1710 | JDH4-02-007-SB-1710 | Pre-Qualification Approval for Odours Scrubbing System | 0 | 100% | 0% | 100% | 0 | 0
Crane | Crane |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1720 | JDH4-02-007-SB-1720 | Pre-Qualification Submittal for Crane | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1730 | JDH4-02-007-SB-1730 | Pre-Qualification Approval for Crane | 0 | 100% | 0% | 100% | 0 | 0
Air Vents | Air Vents |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1800 | JDH4-02-007-SB-1800 | Pre-Qualification Submittal for Air Vents | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1820 | JDH4-02-007-SB-1820 | Pre-Qualification Approval for Air Vents | 0 | 100% | 0% | 100% | 0 | 0
Screening Container | Screening Container |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1740 | JDH4-02-007-SB-1740 | Pre-Qualification Submittal for Screening Container | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1760 | JDH4-02-007-SB-1760 | Pre-Qualification Approval for Screening Container | 0 |  | 0%
Baffle Plates | Baffle Plates |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1810 | JDH4-02-007-SB-1810 | Pre-Qualification Submittal for Baffle plates | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1830 | JDH4-02-007-SB-1830 | Pre-Qualification Approval for Baffle plates | 0 | 100% | 0% | 100% | 0 | 0
Anti-Water Hammer Equipment | Anti-Water Hammer Equipment |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1840 | JDH4-02-007-SB-1840 | Pre-Qualification Submittal for Anti-Water Hammer Equipment | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1850 | JDH4-02-007-SB-1850 | Pre-Qualification Approval for Anti-Water Hammer Equipment | 0 | 100% | 0% | 100% | 0 | 0
Air Conditioning and Ventilation | Air Conditioning and Ventilation |  | 0 |  | 0%
JDH4-02-007-SB-1750 | JDH4-02-007-SB-1750 | Pre-Qualification Submittal for Air Conditioning and Ventilation | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1770 | JDH4-02-007-SB-1770 | Pre-Qualification Approval for Air Conditioning and Ventilation | 0 | 100% | 0% | 100% | 0 | 0
Fuel System | Fuel System |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1780 | JDH4-02-007-SB-1780 | Pre-Qualification Submittal for Fuel System | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1790 | JDH4-02-007-SB-1790 | Pre-Qualification Approval for Fuel System | 0 | 100% | 0% | 100% | 0 | 0
Fire Fighting System | Fire Fighting System |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1920 | JDH4-02-007-SB-1920 | Pre-Qualification Submittal for Fire Fighting System | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1930 | JDH4-02-007-SB-1930 | Pre-Qualification Approval for Fire Fighting System | 0 | 100% | 0% | 100% | 0 | 0
Main Distribution Board /MCC panels | Main Distribution Board /MCC panels |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1860 | JDH4-02-007-SB-1860 | Pre-Qualification Submittal for Main Distribution Board/MCC Panels | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1870 | JDH4-02-007-SB-1870 | Pre-Qualification Approval for Main Distribution Board/MCC Panels | 0 | 100% | 0% | 100% | 0 | 0
Final Panel boards | Final Panel boards |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1880 | JDH4-02-007-SB-1880 | Pre-Qualification Submittal for Final Panel Boards | 0 |  | 0%
JDH4-02-007-SB-1890 | JDH4-02-007-SB-1890 | Pre-Qualification Approval for Final Panel Boards | 0 | 100% | 0% | 100% | 0 | 0
Local Control Panel/ Monitoring Control Panel | Local Control Panel/ Monitoring Control Panel |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1900 | JDH4-02-007-SB-1900 | Pre-Qualification Submittal for Local Control Panel / Monitoring Control Panel | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1910 | JDH4-02-007-SB-1910 | Pre-Qualification Approval for Local Control Panel / Monitoring Control Panel | 0 | 100% | 0% | 100% | 0 | 0
Engine Generators | Engine Generators |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-2060 | JDH4-02-007-SB-2060 | Pre-Qualification Submittal for Engine Generators | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-2070 | JDH4-02-007-SB-2070 | Pre-Qualification Approval for Engine Generators | 0 | 100% | 0% | 100% | 0 | 0
Standby Diesel Generator | Standby Diesel Generator |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-2040 | JDH4-02-007-SB-2040 | Pre-Qualification Submittal for Standby Diesel Generator | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-2050 | JDH4-02-007-SB-2050 | Pre-Qualification Approval for Standby Diesel Generator | 0 | 100% | 0% | 100% | 0 | 0
Power Factor Correction Capacitor Bank | Power Factor Correction Capacitor Bank |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-2000 | JDH4-02-007-SB-2000 | Pre-Qualification Submittal for Power Factor correction Capacitor Bank | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-2010 | JDH4-02-007-SB-2010 | Pre-Qualification Approval for Power Factor correction Capacitor Bank | 0 | 100% | 0% | 100% | 0 | 0
Low-Voltage Electrical Power Conductors and Cables | Low-Voltage Electrical Power Conductors and Cables |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-2020 | JDH4-02-007-SB-2020 | Pre-Qualification Submittal for Low Voltage Electrical Power Conductors & Cables | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-2030 | JDH4-02-007-SB-2030 | Pre-Qualification Approval for Low Voltage Electrical Power Conductors & Cables | 0 | 100% | 0% | 100% | 0 | 0
Low Voltage Feeder Cable | Low Voltage Feeder Cable |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1980 | JDH4-02-007-SB-1980 | Pre-Qualification Submittal for Low Voltage Feeder Cable | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1990 | JDH4-02-007-SB-1990 | Pre-Qualification Approval for Low Voltage Feeder Cable | 0 | 100% | 0% | 100% | 0 | 0
Wiring Devices | Wiring Devices |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1940 | JDH4-02-007-SB-1940 | Pre-Qualification Submittal for Wiring Devices | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1950 | JDH4-02-007-SB-1950 | Pre-Qualification Approval for Wiring Devices | 0 | 100% | 0% | 100% | 0 | 0
Enclosed Switches and Circuit Breakers | Enclosed Switches and Circuit Breakers |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-1960 | JDH4-02-007-SB-1960 | Pre-Qualification Submittal for Enclosed Switches and Circuit Breakers | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-1970 | JDH4-02-007-SB-1970 | Pre-Qualification Approval for Enclosed Switches and Circuit Breakers | 0 | 100% | 0% | 100% | 0 | 0
Raceways for Electrical Systems | Raceways for Electrical Systems |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-2100 | JDH4-02-007-SB-2100 | Pre-Qualification Submittal for Raceways for Electrical System | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-2110 | JDH4-02-007-SB-2110 | Pre-Qualification Approval for Raceways for Electrical System | 0 | 100% | 0% | 100% | 0 | 0
Electrical Manholes | Electrical Manholes |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-2140 | JDH4-02-007-SB-2140 | Pre-Qualification Submittal for Electrical Manholes | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-2150 | JDH4-02-007-SB-2150 | Pre-Qualification Approval for Electrical Manholes | 0 | 100% | 0% | 100% | 0 | 0
Security System (CCTV System) | Security System (CCTV System) |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-2080 | JDH4-02-007-SB-2080 | Pre-Qualification Submittal for Security System (CCTV System) | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-2090 | JDH4-02-007-SB-2090 | Pre-Qualification Approval for Security System (CCTV System) | 0 | 100% | 0% | 100% | 0 | 0
ICT (Data& telephone System) | ICT (Data& telephone System) |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-2120 | JDH4-02-007-SB-2120 | Pre-Qualification Submittal for ICT (Data & Telephone System) | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-2130 | JDH4-02-007-SB-2130 | Pre-Qualification Approval for ICT (Data & Telephone System) | 0 | 100% | 0% | 100% | 0 | 0
Programmable Logic Controllers | Programmable Logic Controllers |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-2200 | JDH4-02-007-SB-2200 | Pre-Qualification Submittal for Programmable Logic Controllers | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-2210 | JDH4-02-007-SB-2210 | Pre-Qualification Approval for Programmable Logic Controllers | 0 | 100% | 0% | 100% | 0 | 0
Process Control Wiring | Process Control Wiring |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-2180 | JDH4-02-007-SB-2180 | Pre-Qualification Submittal for Process Control Wiring | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-2190 | JDH4-02-007-SB-2190 | Pre-Qualification Approval for Process Control Wiring | 0 | 100% | 0% | 100% | 0 | 0
Instrumentation for Process Systems | Instrumentation for Process Systems |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-SB-2160 | JDH4-02-007-SB-2160 | Pre-Qualification Submittal for Instrumentation Control Wiring | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-SB-2170 | JDH4-02-007-SB-2170 | Pre-Qualification Approval for Instrumentation Control Wiring | 0 | 100% | 0% | 100% | 0 | 0
Material Submittal | Material Submittal |  | 1719130.43 | #N/A | #N/A | #N/A | #N/A | #N/A
Road Works - Civil | Road Works - Civil |  | 253642.19 | 100% | 0% | 100% | 253642.19 | 0
Steel Reinforcement | Steel Reinforcement |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1580 | JDH4-02-007-MA-1580 | Material Submittal for Steel Reinforcement | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1590 | JDH4-02-007-MA-1590 | Material Approval for Steel Reinforcement | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Ready Mixed Concrete | Ready Mixed Concrete |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1600 | JDH4-02-007-MA-1600 | Material Submittal for Ready Mixed Concrete | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1610 | JDH4-02-007-MA-1610 | Material Approval for Ready Mixed Concrete | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Water Proofing | Water Proofing |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1620 | JDH4-02-007-MA-1620 | Material Submittal for Water Proofing | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1630 | JDH4-02-007-MA-1630 | Material Approval for Water Proofing | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Aggregate Base Course | Aggregate Base Course |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1000 | JDH4-02-007-MA-1000 | Material Submittal for Aggregate Base Cource | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1010 | JDH4-02-007-MA-1010 | Material Approval for Aggregate Base Cource | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Bituminous Base & Wearing Course | Bituminous Base & Wearing Course |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1020 | JDH4-02-007-MA-1020 | Material Submittal for Bituminous Base & Wearing Cource | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1030 | JDH4-02-007-MA-1030 | Material Approval for Bituminous & Wearing Cource | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Precast Concrete Kerb | Precast Concrete Kerb |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1040 | JDH4-02-007-MA-1040 | Material Submittal for Precast Concrete Kerb | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1050 | JDH4-02-007-MA-1050 | Material Approval for Precast Concrete Kerb | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Interlocking Block Pavers | Interlocking Block Pavers |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1060 | JDH4-02-007-MA-1060 | Material Submittal for Interlocking Block Pavers | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1070 | JDH4-02-007-MA-1070 | Material Approval for Interlocking Block Pavers | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Pavement Markings | Pavement Markings |  | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
JDH4-02-007-MA-1080 | JDH4-02-007-MA-1080 | Material Submittal for Pavement Markings | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1090 | JDH4-02-007-MA-1090 | Material Approval for Pavement Markings | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Traffic Signs | Traffic Signs |  | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
JDH4-02-007-MA-1100 | JDH4-02-007-MA-1100 | Material Submittal for Traffic Signs | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1110 | JDH4-02-007-MA-1110 | Material Approval for Traffic Signs | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Storm Network | Storm Network |  | 84547.4 |  | 0%
GRP Pipes | GRP Pipes |  | 28182.47 |  | 0%
JDH4-02-007-MA-1250 | JDH4-02-007-MA-1250 | Material Submittal for GRP Pipe | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1270 | JDH4-02-007-MA-1270 | Material Approval for GRP Pipe | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Catch Basin | Catch Basin |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1640 | JDH4-02-007-MA-1640 | Material Submittal for Catch Basin | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1650 | JDH4-02-007-MA-1650 | Material Approval for Catch Basin | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Inlet Manholes | Inlet Manholes |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1280 | JDH4-02-007-MA-1280 | Material Submittal for Inlet Manholes | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1290 | JDH4-02-007-MA-1290 | Material Approval for Inlet Manholes | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Sanitary Sewerage | Sanitary Sewerage |  | 56364.93 | 0% | 0% | 0% | 0 | 0
GRP Pipes | GRP Pipes |  | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
JDH4-02-007-MA-1220 | JDH4-02-007-MA-1220 | Material Submittal for GRP Pipe | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1230 | JDH4-02-007-MA-1230 | Material Approval for GRP Pipe | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Manholes | Manholes |  | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
JDH4-02-007-MA-1240 | JDH4-02-007-MA-1240 | Material Submittal for Manholes | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1260 | JDH4-02-007-MA-1260 | Material Approval for Manholes | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
TSE Network | TSE Network |  | 84547.4 | 100% | 0% | 100% | 84547.4 | 0
HDPE Pipe (PN 16) | HDPE Pipe (PN 16) |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1200 | JDH4-02-007-MA-1200 | Material Submittal for HDPE Pipe (PN 16) | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1210 | JDH4-02-007-MA-1210 | Material Approval for HDPE Pipe (PN 16) | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Valves / Chambers | Valves / Chambers |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1440 | JDH4-02-007-MA-1440 | Material Submittal for Valves / Chambers | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1450 | JDH4-02-007-MA-1450 | Material Approval for Valves / Chambers | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Risers | Risers |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1460 | JDH4-02-007-MA-1460 | Material Submittal for Risers | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1470 | JDH4-02-007-MA-1470 | Material Approval for Risers | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Potable Water Network | Potable Water Network |  | 84547.4 | 0% | 0% | 0% | 0 | 0
HDPE Pipe (PN 16) | HDPE Pipe (PN 16) |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1180 | JDH4-02-007-MA-1180 | Material Submittal for HDPE Pipe (PN 16) | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1190 | JDH4-02-007-MA-1190 | Material Approval for HDPE Pipe (PN 16) | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Valves / Chambers | Valves / Chambers |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1420 | JDH4-02-007-MA-1420 | Material Submittal for Valves / Chambers | 0 |  | 0%
JDH4-02-007-MA-1430 | JDH4-02-007-MA-1430 | Material Approval for Valves / Chambers | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Fire Hydrant | Fire Hydrant |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1660 | JDH4-02-007-MA-1660 | Material Submittal for Fire Hydrant | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1670 | JDH4-02-007-MA-1670 | Material Approval for Fire Hydrant | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Electrical Network | Electrical Network |  | 281824.66 | 0% | 0% | 0% | 0 | 0
Pipe for the Duct | Pipe for the Duct |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1120 | JDH4-02-007-MA-1120 | Material Submittal for Pipe for the Duct | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1130 | JDH4-02-007-MA-1130 | Material Approval for Pipe for the Duct By SEC | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Low Voltage Cables | Low Voltage Cables |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1320 | JDH4-02-007-MA-1320 | Material Submittal for Low Voltage Cables | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1330 | JDH4-02-007-MA-1330 | Material Approval for Low Voltage Cables By SEC | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Earthing System | Earthing System |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1160 | JDH4-02-007-MA-1160 | Material Submittal for Earthing System | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1170 | JDH4-02-007-MA-1170 | Material Approval for Earthing System By SEC | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Medium Voltage Cable | Medium Voltage Cable |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1300 | JDH4-02-007-MA-1300 | Material Submittal for Medium Voltage Cable | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1310 | JDH4-02-007-MA-1310 | Material Approval for Medium Voltage Cable By SEC | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Low Voltage Distribution Panel | Low Voltage Distribution Panel |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1140 | JDH4-02-007-MA-1140 | Material Submittal for Low Voltage Distribution Panel | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1150 | JDH4-02-007-MA-1150 | Material Approval for Low Voltage Distribution Panel By SEC | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Unit Sub Station | Unit Sub Station |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1380 | JDH4-02-007-MA-1380 | Material Submittal for Unit Sub Station | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1390 | JDH4-02-007-MA-1390 | Material Approval for Unit Sub Station By SEC | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Ring Main Unit (RMU) | Ring Main Unit (RMU) |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1400 | JDH4-02-007-MA-1400 | Material Submittal for Ring main Unit (RMU) | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1410 | JDH4-02-007-MA-1410 | Material Approval for Ring main Unit (RMU) By SEC | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Lighting poles | Lighting poles |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1340 | JDH4-02-007-MA-1340 | Material Submittal for Lighting poles | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1350 | JDH4-02-007-MA-1350 | Material Approval for Lighting poles By SEC | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Lighting panels/Feeder Pillers | Lighting panels/Feeder Pillers |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1515 | JDH4-02-007-MA-1515 | Material Submittal for Lighting panels/Feeder Pillers By SEC | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1520 | JDH4-02-007-MA-1520 | Material Approval for Lighting panels/Feeder Pillers | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Street Lighting Luminaire | Street Lighting Luminaire |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1360 | JDH4-02-007-MA-1360 | Material Submittal for Street Lighting Luminaire | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1370 | JDH4-02-007-MA-1370 | Material Approval for Street Lighting Luminaire By SEC | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Telecommunications | Telecommunications |  | 28182.47 | 0% | 0% | 0% | 0 | 0
Pipe for the Duct | Pipe for the Duct |  | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
JDH4-02-007-MA-1540 | JDH4-02-007-MA-1540 | Material Submittal for Pipe for the Duct | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1550 | JDH4-02-007-MA-1550 | Material Approval for Pipe for the Duct | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Sewage Lift Station | Sewage Lift Station |  | 845473.98 |  | 0%
Thermal & Moisture Protection | Thermal & Moisture Protection |  | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
JDH4-02-007-MA-1490 | JDH4-02-007-MA-1490 | Material Submittal for Thermal & Moisture Protection | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1510 | JDH4-02-007-MA-1510 | Material Approval for Thermal & Moisture Protection | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Metals | Metals |  | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
JDH4-02-007-MA-1480 | JDH4-02-007-MA-1480 | Material Submittal for Metal | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1500 | JDH4-02-007-MA-1500 | Material Approval for Metal | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Pumps | Pumps |  | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
JDH4-02-007-MA-1560 | JDH4-02-007-MA-1560 | Material Submittal for pumps | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1570 | JDH4-02-007-MA-1570 | Material Approval for pumps | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Pipes,Fittings & Valves | Pipes,Fittings & Valves |  | 28182.47 |  | 0%
JDH4-02-007-MA-1680 | JDH4-02-007-MA-1680 | Material Submittal for Pipes,Fittings & Valves | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1700 | JDH4-02-007-MA-1700 | Material Approval for Pipes,Fittings & Valves | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Odours scrubbing system | Odours scrubbing system |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1690 | JDH4-02-007-MA-1690 | Material Submittal for Odours Scrubbing System | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1710 | JDH4-02-007-MA-1710 | Material Approval for Odours Scrubbing System | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Crane | Crane |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1720 | JDH4-02-007-MA-1720 | Material Submittal for Crane | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1730 | JDH4-02-007-MA-1730 | Material Approval for Crane | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Air Vents | Air Vents |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1800 | JDH4-02-007-MA-1800 | Material Submittal for Air Vents | 0 |  | 0%
JDH4-02-007-MA-1820 | JDH4-02-007-MA-1820 | Material Approval for Air Vents | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Screening Container | Screening Container |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1740 | JDH4-02-007-MA-1740 | Material Submittal for Screening Container | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1760 | JDH4-02-007-MA-1760 | Material Approval for Screening Container | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Baffle Plates | Baffle Plates |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1810 | JDH4-02-007-MA-1810 | Material Submittal for Baffle plates | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1830 | JDH4-02-007-MA-1830 | Material Approval for Baffle plates | 28182.47 |  | 0%
Anti-Water Hammer Equipment | Anti-Water Hammer Equipment |  | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
JDH4-02-007-MA-1840 | JDH4-02-007-MA-1840 | Material Submittal for Anti-Water Hammer Equipment | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1850 | JDH4-02-007-MA-1850 | Material Approval for Anti-Water Hammer Equipment | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Air Conditioning and Ventilation | Air Conditioning and Ventilation |  | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
JDH4-02-007-MA-1750 | JDH4-02-007-MA-1750 | Material Submittal for Air Conditioning and Ventilation | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1770 | JDH4-02-007-MA-1770 | Material Approval for Air Conditioning and Ventilation | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Fuel System | Fuel System |  | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
JDH4-02-007-MA-1780 | JDH4-02-007-MA-1780 | Material Submittal for Fuel System | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1790 | JDH4-02-007-MA-1790 | Material Approval for Fuel System | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Fire Fighting System | Fire Fighting System |  | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
JDH4-02-007-MA-1920 | JDH4-02-007-MA-1920 | Material Submittal for Fire Fighting System | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1930 | JDH4-02-007-MA-1930 | Material Approval for Fire Fighting System | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Main Distribution Board /MCC panels | Main Distribution Board /MCC panels |  | 28182.47 |  | 0%
JDH4-02-007-MA-1860 | JDH4-02-007-MA-1860 | Material Submittal for Main Distribution Board/MCC Panels | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1870 | JDH4-02-007-MA-1870 | Material Approval for Main Distribution Board/MCC Panels | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Final Panel boards | Final Panel boards |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1880 | JDH4-02-007-MA-1880 | Material Submittal for Final Panel Boards | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1890 | JDH4-02-007-MA-1890 | Material Approval for Final Panel Boards | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Local Control Panel/ Monitoring Control Panel | Local Control Panel/ Monitoring Control Panel |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-1900 | JDH4-02-007-MA-1900 | Material Submittal for Local Control Panel / Monitoring Control Panel | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1910 | JDH4-02-007-MA-1910 | Material Approval for Local Control Panel / Monitoring Control Panel | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Engine Generators | Engine Generators |  | 28182.47 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-MA-2060 | JDH4-02-007-MA-2060 | Material Submittal for Engine Generators | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-2070 | JDH4-02-007-MA-2070 | Material Approval for Engine Generators | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Standby Diesel Generator | Standby Diesel Generator |  | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
JDH4-02-007-MA-2040 | JDH4-02-007-MA-2040 | Material Submittal for Standby Diesel Generator | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-2050 | JDH4-02-007-MA-2050 | Material Approval for Standby Diesel Generator | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Power Factor Correction Capacitor Bank | Power Factor Correction Capacitor Bank |  | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
JDH4-02-007-MA-2000 | JDH4-02-007-MA-2000 | Material Submittal for Power Factor correction Capacitor Bank | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-2010 | JDH4-02-007-MA-2010 | Material Approval for Power Factor correction Capacitor Bank | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Low-Voltage Electrical Power Conductors and Cables | Low-Voltage Electrical Power Conductors and Cables |  | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
JDH4-02-007-MA-2020 | JDH4-02-007-MA-2020 | Material Submittal for Low Voltage Electrical Power Conductors & Cables | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-2030 | JDH4-02-007-MA-2030 | Material Approval for Low Voltage Electrical Power Conductors & Cables | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Low Voltage Feeder Cable | Low Voltage Feeder Cable |  | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
JDH4-02-007-MA-1980 | JDH4-02-007-MA-1980 | Material Submittal for Low Voltage Feeder Cable | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1990 | JDH4-02-007-MA-1990 | Material Approval for Low Voltage Feeder Cable | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Wiring Devices | Wiring Devices |  | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
JDH4-02-007-MA-1940 | JDH4-02-007-MA-1940 | Material Submittal for Wiring Devices | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1950 | JDH4-02-007-MA-1950 | Material Approval for Wiring Devices | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Enclosed Switches and Circuit Breakers | Enclosed Switches and Circuit Breakers |  | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
JDH4-02-007-MA-1960 | JDH4-02-007-MA-1960 | Material Submittal for Enclosed Switches and Circuit Breakers | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-1970 | JDH4-02-007-MA-1970 | Material Approval for Enclosed Switches and Circuit Breakers | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Raceways for Electrical Systems | Raceways for Electrical Systems |  | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
JDH4-02-007-MA-2100 | JDH4-02-007-MA-2100 | Material Submittal for Raceways for Electrical System | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-2110 | JDH4-02-007-MA-2110 | Material Approval for Raceways for Electrical System | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Electrical Manholes | Electrical Manholes |  | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
JDH4-02-007-MA-2140 | JDH4-02-007-MA-2140 | Material Submittal for Electrical Manholes | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-2150 | JDH4-02-007-MA-2150 | Material Approval for Electrical Manholes | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Security System (CCTV System) | Security System (CCTV System) |  | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
JDH4-02-007-MA-2080 | JDH4-02-007-MA-2080 | Material Submittal for Security System (CCTV System) | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-2090 | JDH4-02-007-MA-2090 | Material Approval for Security System (CCTV System) | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
ICT (Data& telephone System) | ICT (Data& telephone System) |  | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
JDH4-02-007-MA-2120 | JDH4-02-007-MA-2120 | Material Submittal for ICT (Data & Telephone System) | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-2130 | JDH4-02-007-MA-2130 | Material Approval for ICT (Data & Telephone System) | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Programmable Logic Controllers | Programmable Logic Controllers |  | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
JDH4-02-007-MA-2200 | JDH4-02-007-MA-2200 | Material Submittal for Programmable Logic Controllers | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-2210 | JDH4-02-007-MA-2210 | Material Approval for Programmable Logic Controllers | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Process Control Wiring | Process Control Wiring |  | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
JDH4-02-007-MA-2180 | JDH4-02-007-MA-2180 | Material Submittal for Process Control Wiring | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-2190 | JDH4-02-007-MA-2190 | Material Approval for Process Control Wiring | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Instrumentation for Process Systems | Instrumentation for Process Systems |  | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
JDH4-02-007-MA-2160 | JDH4-02-007-MA-2160 | Material Submittal for Instrumentation Control Wiring | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-MA-2170 | JDH4-02-007-MA-2170 | Material Approval for Instrumentation Control Wiring | 28182.47 | 100% | 0% | 100% | 28182.47 | 0
Procurement | Procurement |  | 11460869.58 | 100% | 0% | 100% | 11460869.58 | 0
Short Lead Item | Short Lead Item |  | 5193206.54 | 100% | 0% | 100% | 5193206.54 | 0
Road Works - Civil | Road Works - Civil |  | 1611684.79 | 0% | 0% | 0% | 0 | 0
Steel Reinforcement | Steel Reinforcement |  | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-1300 | JDH4-02-007-PR-1300 | PO for Steel Reinforcement | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1310 | JDH4-02-007-PR-1310 | Material Fabrication for Steel Reinforcement | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1319 | JDH4-02-007-PR-1319 | Material Delivery for Steel Reinforcement - Stage 1 | 89538.05 | 100% | 0% | 100% | 89538.05 | 0
JDH4-02-007-PR-1320 | JDH4-02-007-PR-1320 | Material Delivery for Steel Reinforcement - Stage 2 | 89538.05 | 100% | 0% | 100% | 89538.05 | 0
Ready Mixed Concrete | Ready Mixed Concrete |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-1330 | JDH4-02-007-PR-1330 | PO for Ready Mixed Concrete | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1340 | JDH4-02-007-PR-1340 | Material Delivery for Ready Mixed Concrete | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
Water Proofing | Water Proofing |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-1350 | JDH4-02-007-PR-1350 | PO for Water Proofing | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1360 | JDH4-02-007-PR-1360 | Material Fabrication for Water Proofing | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1370 | JDH4-02-007-PR-1370 | Material Delivery for Water Proofing | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
Aggregate Base Course | Aggregate Base Course |  | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-1380 | JDH4-02-007-PR-1380 | PO for Aggregate Base Course | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1389 | JDH4-02-007-PR-1389 | Material Delivery for Aggregate Base Course - Stage 1 | 89538.05 | 100% | 0% | 100% | 89538.05 | 0
JDH4-02-007-PR-1390 | JDH4-02-007-PR-1390 | Material Delivery for Aggregate Base Course - Stage 2 | 89538.05 | 100% | 0% | 100% | 89538.05 | 0
Bituminous Base & Wearing Course | Bituminous Base & Wearing Course |  | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-1400 | JDH4-02-007-PR-1400 | PO for Bituminous Base & Wearing Cource | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1410 | JDH4-02-007-PR-1410 | Material Delivery to the Site | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
Precast Concrete Kerb | Precast Concrete Kerb |  | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-1420 | JDH4-02-007-PR-1420 | PO for Precast Concrete Kerb | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1430 | JDH4-02-007-PR-1430 | Material Fabrication for Precast Concrete Kerb | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1440 | JDH4-02-007-PR-1440 | Material Delivery for Precast Concrete Kerb | 179076.09 |  | 0%
Interlocking Block Pavers | Interlocking Block Pavers |  | 179076.09 |  | 0%
JDH4-02-007-PR-1450 | JDH4-02-007-PR-1450 | PO for Interlocking Block Pavers | 0 |  | 0%
JDH4-02-007-PR-1460 | JDH4-02-007-PR-1460 | Material Fabrication for Interlocking Block Pavers | 0 |  | 0%
JDH4-02-007-PR-1470 | JDH4-02-007-PR-1470 | Material Delivery for Interlocking Block Pavers | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
Pavement Markings | Pavement Markings |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-1480 | JDH4-02-007-PR-1480 | PO for Pavement Markings | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1490 | JDH4-02-007-PR-1490 | Material Fabrication for Pavement Markings | 0 |  | 0%
JDH4-02-007-PR-1500 | JDH4-02-007-PR-1500 | Material Delivery for Pavement Markings | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
Traffic Signs | Traffic Signs |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-1510 | JDH4-02-007-PR-1510 | PO for Traffic Signs | 0 |  | 0%
JDH4-02-007-PR-1520 | JDH4-02-007-PR-1520 | Material Fabrication for Traffic Signs | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1530 | JDH4-02-007-PR-1530 | Material Delivery for Traffic Signs | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
Stormwater Utilities | Stormwater Utilities |  | 716304.35 |  | 0%
Catch Basins | Catch Basins |  | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-1720 | JDH4-02-007-PR-1720 | PO for Catch Basins | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1729 | JDH4-02-007-PR-1729 | Material Fabrication for Catch Basins - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1730 | JDH4-02-007-PR-1730 | Material Fabrication for Catch Basins - Stage 2 | 0 |  | 0%
JDH4-02-007-PR-1740 | JDH4-02-007-PR-1740 | Material Delivery for Catch Basins | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-1830 | JDH4-02-007-PR-1830 | Staging Time for Catch Basins | 0 | 100% | 0% | 100% | 0 | 0
GRP Pipes | GRP Pipes |  | 358152.18 |  | 0%
JDH4-02-007-PR-1660 | JDH4-02-007-PR-1660 | PO for GRP Pipes | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1670 | JDH4-02-007-PR-1670 | Material Fabrication for GRP Pipes | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1680 | JDH4-02-007-PR-1680 | Material Delivery for GRP Pipes | 358152.18 |  | 0%
Inlet Manholes | Inlet Manholes |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-1690 | JDH4-02-007-PR-1690 | PO for Inlet Manholes | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1700 | JDH4-02-007-PR-1700 | Material Fabrication for Inlet Manholes | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1710 | JDH4-02-007-PR-1710 | Material Delivery for Inlet Manholes | 179076.09 |  | 0%
Sanitary Sewerage | Sanitary Sewerage |  | 716304.35 | 0% | 0% | 0% | 0 | 0
GRP Pipes | GRP Pipes |  | 358152.18 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-1600 | JDH4-02-007-PR-1600 | PO for GRP Pipes | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1610 | JDH4-02-007-PR-1610 | Material Fabrication for GRP Pipes | 0 |  | 0%
JDH4-02-007-PR-1620 | JDH4-02-007-PR-1620 | Material Delivery for GRP Pipes | 358152.18 | 100% | 0% | 100% | 358152.18 | 0
Manholes | Manholes |  | 358152.17 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-1630 | JDH4-02-007-PR-1630 | PO for Manholes | 0 |  | 0%
JDH4-02-007-PR-1638 | JDH4-02-007-PR-1638 | Material Fabrication for Manholes - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1639 | JDH4-02-007-PR-1639 | Material Fabrication for Manholes - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1640 | JDH4-02-007-PR-1640 | Material Fabrication for Manholes - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1650 | JDH4-02-007-PR-1650 | Material Delivery for Manholes | 358152.17 |  | 0%
TSE Network | TSE Network |  | 179076.09 |  | 0%
HDPE Pipe (PN 16) | HDPE Pipe (PN 16) |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-1570 | JDH4-02-007-PR-1570 | PO for HDPE Pipe (PN 16) | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1580 | JDH4-02-007-PR-1580 | Material Fabrication for HDPE Pipe (PN 16) | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1590 | JDH4-02-007-PR-1590 | Material Delivery for HDPE Pipe (PN 16) | 179076.09 |  | 0%
Potable Water Network | Potable Water Network |  | 179076.09 | 0% | 0% | 0% | 0 | 0
HDPE Pipe (PN 16) | HDPE Pipe (PN 16) |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-1540 | JDH4-02-007-PR-1540 | PO for HDPE Pipe (PN 16) | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1550 | JDH4-02-007-PR-1550 | Material Fabrication for HDPE Pipe (PN 16) | 0 |  | 0%
JDH4-02-007-PR-1560 | JDH4-02-007-PR-1560 | Material Delivery for HDPE Pipe (PN 16) | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
Electrical Network | Electrical Network |  | 358152.17 | 0% | 0% | 0% | 0 | 0
Pipe for the Duct | Pipe for the Duct |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-1190 | JDH4-02-007-PR-1190 | PO for Pipe for Duct | 0 |  | 0%
JDH4-02-007-PR-1210 | JDH4-02-007-PR-1210 | Material Fabrication for Pipe for Duct | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1230 | JDH4-02-007-PR-1230 | Material Delivery for Pipe for Duct | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
Earthing System | Earthing System |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-1180 | JDH4-02-007-PR-1180 | PO for Earthing System | 0 |  | 0%
JDH4-02-007-PR-1200 | JDH4-02-007-PR-1200 | Material Fabrication for Earthing System | 0 |  | 0%
JDH4-02-007-PR-1220 | JDH4-02-007-PR-1220 | Material Delivery for Earthing System | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
Telecommunications | Telecommunications |  | 179076.09 | 0% | 0% | 0% | 0 | 0
Pipe for the Duct | Pipe for the Duct |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-2260 | JDH4-02-007-PR-2260 | PO for Pipe for Duct | 0 |  | 0%
JDH4-02-007-PR-2270 | JDH4-02-007-PR-2270 | Material Fabrication for Pipe for Duct | 0 |  | 0%
JDH4-02-007-PR-2280 | JDH4-02-007-PR-2280 | Material Delivery for Pipe for Duct | 179076.09 |  | 0%
Sewage Lift Station | Sewage Lift Station |  | 1253532.61 | 0% | 0% | 0% | 0 | 0
Thermal & Moisture Protection | Thermal & Moisture Protection |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-2350 | JDH4-02-007-PR-2350 | PO for Thermal & Moisture Protection | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2358 | JDH4-02-007-PR-2358 | Material Fabrication for Thermal & Moisture Protection - Stage 1 | 0 |  | 0%
JDH4-02-007-PR-2359 | JDH4-02-007-PR-2359 | Material Fabrication for Thermal & Moisture Protection - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2360 | JDH4-02-007-PR-2360 | Material Fabrication for Thermal & Moisture Protection - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2369 | JDH4-02-007-PR-2369 | Material Delivery for Thermal & Moisture Protection - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2370 | JDH4-02-007-PR-2370 | Material Delivery for Thermal & Moisture Protection - Stage 2 | 179076.09 |  | 0%
Metals | Metals |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-1840 | JDH4-02-007-PR-1840 | PO for Metal | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1848 | JDH4-02-007-PR-1848 | Material Fabrication for Metal - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1849 | JDH4-02-007-PR-1849 | Material Fabrication for Metal - Stage 2 | 0 |  | 0%
JDH4-02-007-PR-1850 | JDH4-02-007-PR-1850 | Material Fabrication for Metal - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1859 | JDH4-02-007-PR-1859 | Material Delivery for Metal - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1860 | JDH4-02-007-PR-1860 | Material Delivery for Metal - Stage 2 | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
Pipes | Pipes |  | 179076.09 |  | 0%
JDH4-02-007-PR-2290 | JDH4-02-007-PR-2290 | PO for Pipes | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2300 | JDH4-02-007-PR-2300 | Material Fabrication for Pipes | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2310 | JDH4-02-007-PR-2310 | Material Delivery for Pipes | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
Air Conditioning and Ventilation | Air Conditioning and Ventilation |  | 179076.09 |  | 0%
JDH4-02-007-PR-2380 | JDH4-02-007-PR-2380 | PO for Air Conditioning and Ventilation | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2390 | JDH4-02-007-PR-2390 | Material Fabrication for Air Conditioning and Ventilation | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2400 | JDH4-02-007-PR-2400 | Material Delivery for Air Conditioning and Ventilation | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
Fuel System | Fuel System |  | 179076.09 |  | 0%
JDH4-02-007-PR-1870 | JDH4-02-007-PR-1870 | PO for Fuel System | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1880 | JDH4-02-007-PR-1880 | Material Fabrication for Fuel System | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1890 | JDH4-02-007-PR-1890 | Material Delivery for Fuel System | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
Fire Fighting System | Fire Fighting System |  | 179076.09 |  | 0%
JDH4-02-007-PR-2320 | JDH4-02-007-PR-2320 | PO for Fire Fighting System | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2330 | JDH4-02-007-PR-2330 | Material Fabrication for Fire Fighting System | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2340 | JDH4-02-007-PR-2340 | Material Delivery for Fire Fighting System | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
Security System (CCTV System) | Security System (CCTV System) |  | 179076.09 |  | 0%
JDH4-02-007-PR-2410 | JDH4-02-007-PR-2410 | PO for Security System (CCTV System) | 0 |  | 0%
JDH4-02-007-PR-2420 | JDH4-02-007-PR-2420 | Material Fabrication for Security System (CCTV System) | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2430 | JDH4-02-007-PR-2430 | Material Delivery for Security System (CCTV System) | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
Long Lead Item | Long Lead Item |  | 6267663.05 | 100% | 0% | 100% | 6267663.05 | 0
TSE Network | TSE Network |  | 358152.17 |  | 0%
Valves / Chambers | Valves / Chambers |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-1270 | JDH4-02-007-PR-1270 | PO for Valves / Chambers | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1277 | JDH4-02-007-PR-1277 | Material Fabrication for Valves / Chambers - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1278 | JDH4-02-007-PR-1278 | Material Fabrication for Valves / Chambers - Stage 2 | 0 |  | 0%
JDH4-02-007-PR-1279 | JDH4-02-007-PR-1279 | Material Fabrication for Valves / Chambers - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1280 | JDH4-02-007-PR-1280 | Material Fabrication for Valves / Chambers - Stage 4 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1290 | JDH4-02-007-PR-1290 | Material Delivery for Valves / Chambers | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-1820 | JDH4-02-007-PR-1820 | Staging Time for Valves / Chambers | 0 |  | 0%
Risers | Risers |  | 179076.09 |  | 0%
JDH4-02-007-PR-1900 | JDH4-02-007-PR-1900 | PO for Risers | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1907 | JDH4-02-007-PR-1907 | Material Fabrication for Risers - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1908 | JDH4-02-007-PR-1908 | Material Fabrication for Risers - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1909 | JDH4-02-007-PR-1909 | Material Fabrication for Risers - Stage 3 | 0 |  | 0%
JDH4-02-007-PR-1910 | JDH4-02-007-PR-1910 | Material Fabrication for Risers - Stage 4 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1920 | JDH4-02-007-PR-1920 | Material Delivery for Risers | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-1930 | JDH4-02-007-PR-1930 | Staging Time for Risers | 0 | 100% | 0% | 100% | 0 | 0
Potable Water Network | Potable Water Network |  | 358152.17 |  | 0%
Valves / Chambers | Valves / Chambers |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-1240 | JDH4-02-007-PR-1240 | PO for Valves / Chambers | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1248 | JDH4-02-007-PR-1248 | Material Fabrication for Valves / Chambers - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1249 | JDH4-02-007-PR-1249 | Material Fabrication for Valves / Chambers - Stage 2 | 0 |  | 0%
JDH4-02-007-PR-1250 | JDH4-02-007-PR-1250 | Material Fabrication for Valves / Chambers - Stage 3 | 0 |  | 0%
JDH4-02-007-PR-1260 | JDH4-02-007-PR-1260 | Material Delivery for Valves / Chambers | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-1810 | JDH4-02-007-PR-1810 | Staging Time for Valves / Chambers | 0 | 100% | 0% | 100% | 0 | 0
Fire Hydrants | Fire Hydrants |  | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-2440 | JDH4-02-007-PR-2440 | PO for Fire Hydrant | 0 |  | 0%
JDH4-02-007-PR-2447 | JDH4-02-007-PR-2447 | Material Fabrication for Fire Hydrant - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2448 | JDH4-02-007-PR-2448 | Material Fabrication for Fire Hydrant - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2449 | JDH4-02-007-PR-2449 | Material Fabrication for Fire Hydrant - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2450 | JDH4-02-007-PR-2450 | Material Fabrication for Fire Hydrant - Stage 4 | 0 |  | 0%
JDH4-02-007-PR-2460 | JDH4-02-007-PR-2460 | Material Delivery for Fire Hydrant | 179076.09 |  | 0%
JDH4-02-007-PR-2470 | JDH4-02-007-PR-2470 | Staging Time for Fire Hydrant | 0 | 100% | 0% | 100% | 0 | 0
Electrical Network | Electrical Network |  | 1432608.7 | 0% | 0% | 0% | 0 | 0
Medium Voltage Cable | Medium Voltage Cable |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-1000 | JDH4-02-007-PR-1000 | PO for Medium Voltage Cable | 0 |  | 0%
JDH4-02-007-PR-1059 | JDH4-02-007-PR-1059 | Material Fabrication for Medium Voltage Cable - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1060 | JDH4-02-007-PR-1060 | Material Fabrication for Medium Voltage Cable - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1120 | JDH4-02-007-PR-1120 | Material Delivery for Medium Voltage Cable | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-1750 | JDH4-02-007-PR-1750 | Staging Time for Medium Voltage Cable | 0 |  | 0%
Unit Sub Station | Unit Sub Station |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-1010 | JDH4-02-007-PR-1010 | PO for Unit Sub-station | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1067 | JDH4-02-007-PR-1067 | Material Fabrication for Unit Sub-station - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1068 | JDH4-02-007-PR-1068 | Material Fabrication for Unit Sub-station - Stage 2 | 0 |  | 0%
JDH4-02-007-PR-1069 | JDH4-02-007-PR-1069 | Material Fabrication for Unit Sub-station - Stage 3 | 0 |  | 0%
JDH4-02-007-PR-1070 | JDH4-02-007-PR-1070 | Material Fabrication for Unit Sub-station - Stage 4 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1130 | JDH4-02-007-PR-1130 | Material Delivery for Unit Sub-station | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-1760 | JDH4-02-007-PR-1760 | Staging Time for Unit Sub-station | 0 | 100% | 0% | 100% | 0 | 0
Low Voltage Cables | Low Voltage Cables |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-1020 | JDH4-02-007-PR-1020 | PO for Low Voltage Cables | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1078 | JDH4-02-007-PR-1078 | Material Fabrication for Low Voltage Cables - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1079 | JDH4-02-007-PR-1079 | Material Fabrication for Low Voltage Cables - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1080 | JDH4-02-007-PR-1080 | Material Fabrication for Low Voltage Cables - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1140 | JDH4-02-007-PR-1140 | Material Delivery for Low Voltage Cables | 179076.09 |  | 0%
JDH4-02-007-PR-1770 | JDH4-02-007-PR-1770 | Staging Time for Low Voltage Cables | 0 | 100% | 0% | 100% | 0 | 0
Ring Main Unit | Ring Main Unit |  | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-1940 | JDH4-02-007-PR-1940 | PO for Ring Main Unit | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1948 | JDH4-02-007-PR-1948 | Material Fabrication for Ring Main Unit - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1949 | JDH4-02-007-PR-1949 | Material Fabrication for Ring Main Unit - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1950 | JDH4-02-007-PR-1950 | Material Fabrication for Ring Main Unit - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1960 | JDH4-02-007-PR-1960 | Material Delivery for Ring Main Unit | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-1970 | JDH4-02-007-PR-1970 | Staging Time for Ring Main Unit | 0 | 100% | 0% | 100% | 0 | 0
Lighting poles | Lighting poles |  | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-1030 | JDH4-02-007-PR-1030 | PO for Lighting poles | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1088 | JDH4-02-007-PR-1088 | Material Fabrication for Lighting poles - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1089 | JDH4-02-007-PR-1089 | Material Fabrication for Lighting poles - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1090 | JDH4-02-007-PR-1090 | Material Fabrication for Lighting poles - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1150 | JDH4-02-007-PR-1150 | Material Delivery for Lighting poles | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-1780 | JDH4-02-007-PR-1780 | Staging Time for Lighting poles | 0 | 100% | 0% | 100% | 0 | 0
Street Lighting Luminaire | Street Lighting Luminaire |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-1040 | JDH4-02-007-PR-1040 | PO for Street Lighting Luminaire | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1098 | JDH4-02-007-PR-1098 | Material Fabrication for Street Lighting Luminaire - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1099 | JDH4-02-007-PR-1099 | Material Fabrication for Street Lighting Luminaire - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1100 | JDH4-02-007-PR-1100 | Material Fabrication for Street Lighting Luminaire - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1160 | JDH4-02-007-PR-1160 | Material Delivery for Street Lighting Luminaire | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-1790 | JDH4-02-007-PR-1790 | Staging Time for Street Lighting Luminaire | 0 | 100% | 0% | 100% | 0 | 0
Lighting panels/Feeder Pillers | Lighting panels/Feeder Pillers |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-1050 | JDH4-02-007-PR-1050 | PO for Lighting Panels/Feeder Pillers | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1108 | JDH4-02-007-PR-1108 | Material Fabrication for Lighting Panels/Feeder Pillers - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1109 | JDH4-02-007-PR-1109 | Material Fabrication for Lighting Panels/Feeder Pillers - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1110 | JDH4-02-007-PR-1110 | Material Fabrication for Lighting Panels/Feeder Pillers - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-1170 | JDH4-02-007-PR-1170 | Material Delivery for Lighting Panels/Feeder Pillers | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-1800 | JDH4-02-007-PR-1800 | Staging Time for Lighting Panels/Feeder Pillers | 0 | 100% | 0% | 100% | 0 | 0
Low Voltage Distribution Panels | Low Voltage Distribution Panels |  | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-2480 | JDH4-02-007-PR-2480 | PO for Low Voltage Distribution Panels | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2488 | JDH4-02-007-PR-2488 | Material Fabrication for Low Voltage Distribution Panels - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2489 | JDH4-02-007-PR-2489 | Material Fabrication for Low Voltage Distribution Panels - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2490 | JDH4-02-007-PR-2490 | Material Fabrication for Low Voltage Distribution Panels - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2500 | JDH4-02-007-PR-2500 | Material Delivery for Low Voltage Distribution Panels | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-2510 | JDH4-02-007-PR-2510 | Staging Time for Low Voltage Distribution Panels | 0 | 100% | 0% | 100% | 0 | 0
Sewage Lift Station | Sewage Lift Station |  | 4118750 | 100% | 0% | 100% | 4118750 | 0
Odours scrubbing system | Odours scrubbing system |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-1990 | JDH4-02-007-PR-1990 | PO for Odours scrubbing system | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2037 | JDH4-02-007-PR-2037 | Material Fabrication for Odours scrubbing system - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2038 | JDH4-02-007-PR-2038 | Material Fabrication for Odours scrubbing system - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2039 | JDH4-02-007-PR-2039 | Material Fabrication for Odours scrubbing system - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2040 | JDH4-02-007-PR-2040 | Material Fabrication for Odours scrubbing system - Stage 4 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2090 | JDH4-02-007-PR-2090 | Material Delivery for Odours scrubbing system | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-2140 | JDH4-02-007-PR-2140 | Staging Time for Odours scrubbing system | 0 | 100% | 0% | 100% | 0 | 0
Crane | Crane |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-2180 | JDH4-02-007-PR-2180 | PO for Crane | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2187 | JDH4-02-007-PR-2187 | Material Fabrication for Crane - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2188 | JDH4-02-007-PR-2188 | Material Fabrication for Crane - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2189 | JDH4-02-007-PR-2189 | Material Fabrication for Crane - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2190 | JDH4-02-007-PR-2190 | Material Fabrication for Crane - Stage 4 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2200 | JDH4-02-007-PR-2200 | Material Delivery for Crane | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-2210 | JDH4-02-007-PR-2210 | Staging Time for Crane | 0 | 100% | 0% | 100% | 0 | 0
Air Vents | Air Vents |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-2000 | JDH4-02-007-PR-2000 | PO for Air Vents | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2045 | JDH4-02-007-PR-2045 | Material Fabrication for Air Vents - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2046 | JDH4-02-007-PR-2046 | Material Fabrication for Air Vents - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2047 | JDH4-02-007-PR-2047 | Material Fabrication for Air Vents - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2048 | JDH4-02-007-PR-2048 | Material Fabrication for Air Vents - Stage 4 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2049 | JDH4-02-007-PR-2049 | Material Fabrication for Air Vents - Stage 5 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2050 | JDH4-02-007-PR-2050 | Material Fabrication for Air Vents - Stage 6 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2100 | JDH4-02-007-PR-2100 | Material Delivery for Air Vents | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-2150 | JDH4-02-007-PR-2150 | Staging Time for Air Vents | 0 | 100% | 0% | 100% | 0 | 0
Screening Container | Screening Container |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-2220 | JDH4-02-007-PR-2220 | PO for Screening Container | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2225 | JDH4-02-007-PR-2225 | Material Fabrication for Screening Container - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2226 | JDH4-02-007-PR-2226 | Material Fabrication for Screening Container - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2227 | JDH4-02-007-PR-2227 | Material Fabrication for Screening Container - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2228 | JDH4-02-007-PR-2228 | Material Fabrication for Screening Container - Stage 4 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2229 | JDH4-02-007-PR-2229 | Material Fabrication for Screening Container - Stage 5 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2230 | JDH4-02-007-PR-2230 | Material Fabrication for Screening Container - Stage 6 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2240 | JDH4-02-007-PR-2240 | Material Delivery for Screening Container | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-2250 | JDH4-02-007-PR-2250 | Staging Time for Screening Container | 0 | 100% | 0% | 100% | 0 | 0
Baffle Plates | Baffle Plates |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-2010 | JDH4-02-007-PR-2010 | PO for Baffle Plates | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2057 | JDH4-02-007-PR-2057 | Material Fabrication for Baffle Plates - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2058 | JDH4-02-007-PR-2058 | Material Fabrication for Baffle Plates - Stage 2 | 0 |  | 0%
JDH4-02-007-PR-2059 | JDH4-02-007-PR-2059 | Material Fabrication for Baffle Plates - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2060 | JDH4-02-007-PR-2060 | Material Fabrication for Baffle Plates - Stage 4 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2110 | JDH4-02-007-PR-2110 | Material Delivery for Baffle Plates | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-2160 | JDH4-02-007-PR-2160 | Staging Time for Baffle Plates | 0 | 100% | 0% | 100% | 0 | 0
Anti-Water Hammer Equipment | Anti-Water Hammer Equipment |  | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-2020 | JDH4-02-007-PR-2020 | PO for Anti-Water Hammer Equipment | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2065 | JDH4-02-007-PR-2065 | Material Fabrication for Anti-Water Hammer Equipment - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2066 | JDH4-02-007-PR-2066 | Material Fabrication for Anti-Water Hammer Equipment - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2067 | JDH4-02-007-PR-2067 | Material Fabrication for Anti-Water Hammer Equipment - Stage 3 | 0 |  | 0%
JDH4-02-007-PR-2068 | JDH4-02-007-PR-2068 | Material Fabrication for Anti-Water Hammer Equipment - Stage 4 | 0 |  | 0%
JDH4-02-007-PR-2069 | JDH4-02-007-PR-2069 | Material Fabrication for Anti-Water Hammer Equipment - Stage 5 | 0 |  | 0%
JDH4-02-007-PR-2070 | JDH4-02-007-PR-2070 | Material Fabrication for Anti-Water Hammer Equipment - Stage 6 | 0 |  | 0%
JDH4-02-007-PR-2120 | JDH4-02-007-PR-2120 | Material Delivery for Anti-Water Hammer Equipment | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-2170 | JDH4-02-007-PR-2170 | Staging Time for Anti-Water Hammer Equipment | 0 | 100% | 0% | 100% | 0 | 0
Pumps | Pumps |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-1980 | JDH4-02-007-PR-1980 | PO for Pumps | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2026 | JDH4-02-007-PR-2026 | Material Fabrication for Pumps - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2027 | JDH4-02-007-PR-2027 | Material Fabrication for Pumps - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2028 | JDH4-02-007-PR-2028 | Material Fabrication for Pumps - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2029 | JDH4-02-007-PR-2029 | Material Fabrication for Pumps - Stage 4 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2030 | JDH4-02-007-PR-2030 | Material Fabrication for Pumps - Stage 5 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2080 | JDH4-02-007-PR-2080 | Material Delivery for Pumps | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-2130 | JDH4-02-007-PR-2130 | Staging Time for Pumps | 0 | 100% | 0% | 100% | 0 | 0
Main Distribution Board /MCC panels | Main Distribution Board /MCC panels |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-2530 | JDH4-02-007-PR-2530 | PO for Main Distribution Board / MCC panels | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2567 | JDH4-02-007-PR-2567 | Material Fabrication for Main Distribution Board / MCC panels - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2568 | JDH4-02-007-PR-2568 | Material Fabrication for Main Distribution Board / MCC panels - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2569 | JDH4-02-007-PR-2569 | Material Fabrication for Main Distribution Board / MCC panels - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2570 | JDH4-02-007-PR-2570 | Material Fabrication for Main Distribution Board / MCC panels - Stage 4 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2610 | JDH4-02-007-PR-2610 | Material Delivery for Main Distribution Board / MCC panels | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-2650 | JDH4-02-007-PR-2650 | Staging Time for Main Distribution Board / MCC panels | 0 | 100% | 0% | 100% | 0 | 0
Final Panel boards | Final Panel boards |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-2680 | JDH4-02-007-PR-2680 | PO for Final Panel Boards | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2687 | JDH4-02-007-PR-2687 | Material Fabrication for Final Panel Boards - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2688 | JDH4-02-007-PR-2688 | Material Fabrication for Final Panel Boards - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2689 | JDH4-02-007-PR-2689 | Material Fabrication for Final Panel Boards - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2690 | JDH4-02-007-PR-2690 | Material Fabrication for Final Panel Boards - Stage 4 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2700 | JDH4-02-007-PR-2700 | Material Delivery for Final Panel Boards | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-2710 | JDH4-02-007-PR-2710 | Staging Time for Final Panel Boards | 0 | 100% | 0% | 100% | 0 | 0
Local Control Panel/ Monitoring Control Panel | Local Control Panel/ Monitoring Control Panel |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-2540 | JDH4-02-007-PR-2540 | PO for Local Control Panel/ Monitoring Control Panel | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2576 | JDH4-02-007-PR-2576 | Material Fabrication for Local Control Panel/ Monitoring Control Panel - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2577 | JDH4-02-007-PR-2577 | Material Fabrication for Local Control Panel/ Monitoring Control Panel - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2578 | JDH4-02-007-PR-2578 | Material Fabrication for Local Control Panel/ Monitoring Control Panel - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2579 | JDH4-02-007-PR-2579 | Material Fabrication for Local Control Panel/ Monitoring Control Panel - Stage 4 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2580 | JDH4-02-007-PR-2580 | Material Fabrication for Local Control Panel/ Monitoring Control Panel - Stage 5 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2620 | JDH4-02-007-PR-2620 | Material Delivery for Local Control Panel/ Monitoring Control Panel | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-2660 | JDH4-02-007-PR-2660 | Staging Time for Local Control Panel/ Monitoring Control Panel | 0 | 100% | 0% | 100% | 0 | 0
Engine Generators | Engine Generators |  | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-2720 | JDH4-02-007-PR-2720 | PO for Engine Generators | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2726 | JDH4-02-007-PR-2726 | Material Fabrication for Engine Generators - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2727 | JDH4-02-007-PR-2727 | Material Fabrication for Engine Generators - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2728 | JDH4-02-007-PR-2728 | Material Fabrication for Engine Generators - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2729 | JDH4-02-007-PR-2729 | Material Fabrication for Engine Generators - Stage 4 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2730 | JDH4-02-007-PR-2730 | Material Fabrication for Engine Generators - Stage 5 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2740 | JDH4-02-007-PR-2740 | Material Delivery for Engine Generators | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-2750 | JDH4-02-007-PR-2750 | Staging Time for Engine Generators | 0 | 100% | 0% | 100% | 0 | 0
Standby Diesel Generator | Standby Diesel Generator |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-2550 | JDH4-02-007-PR-2550 | PO for Standby Diesel Generator | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2587 | JDH4-02-007-PR-2587 | Material Fabrication for Standby Diesel Generator - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2588 | JDH4-02-007-PR-2588 | Material Fabrication for Standby Diesel Generator - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2589 | JDH4-02-007-PR-2589 | Material Fabrication for Standby Diesel Generator - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2590 | JDH4-02-007-PR-2590 | Material Fabrication for Standby Diesel Generator - Stage 4 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2630 | JDH4-02-007-PR-2630 | Material Delivery for Standby Diesel Generator | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-2670 | JDH4-02-007-PR-2670 | Staging Time for Standby Diesel Generator | 0 | 100% | 0% | 100% | 0 | 0
Power Factor Correction Capacitor Bank | Power Factor Correction Capacitor Bank |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-2760 | JDH4-02-007-PR-2760 | PO for Power Factor Correction Capacitor Bank | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2795 | JDH4-02-007-PR-2795 | Material Fabrication for Power Factor Correction Capacitor Bank - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2796 | JDH4-02-007-PR-2796 | Material Fabrication for Power Factor Correction Capacitor Bank - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2797 | JDH4-02-007-PR-2797 | Material Fabrication for Power Factor Correction Capacitor Bank - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2798 | JDH4-02-007-PR-2798 | Material Fabrication for Power Factor Correction Capacitor Bank - Stage 4 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2799 | JDH4-02-007-PR-2799 | Material Fabrication for Power Factor Correction Capacitor Bank - Stage 5 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2800 | JDH4-02-007-PR-2800 | Material Fabrication for Power Factor Correction Capacitor Bank - Stage 6 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2840 | JDH4-02-007-PR-2840 | Material Delivery for Power Factor Correction Capacitor Bank | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-2880 | JDH4-02-007-PR-2880 | Staging Time for Power Factor Correction Capacitor Bank | 0 | 100% | 0% | 100% | 0 | 0
Low-Voltage Electrical Power Conductors and Cables | Low-Voltage Electrical Power Conductors and Cables |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-2770 | JDH4-02-007-PR-2770 | PO for Low-Voltage Electrical Power Conductors and Cables | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2807 | JDH4-02-007-PR-2807 | Material Fabrication for Low-Voltage Electrical Power Conductors and Cables - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2808 | JDH4-02-007-PR-2808 | Material Fabrication for Low-Voltage Electrical Power Conductors and Cables - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2809 | JDH4-02-007-PR-2809 | Material Fabrication for Low-Voltage Electrical Power Conductors and Cables - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2810 | JDH4-02-007-PR-2810 | Material Fabrication for Low-Voltage Electrical Power Conductors and Cables - Stage 4 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2850 | JDH4-02-007-PR-2850 | Material Delivery for Low-Voltage Electrical Power Conductors and Cables | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-2890 | JDH4-02-007-PR-2890 | Staging Time for Low-Voltage Electrical Power Conductors and Cables | 0 | 100% | 0% | 100% | 0 | 0
Low Voltage Feeder Cable | Low Voltage Feeder Cable |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-2920 | JDH4-02-007-PR-2920 | PO for Low Voltage Feeder Cable | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2927 | JDH4-02-007-PR-2927 | Material Fabrication for Low Voltage Feeder Cable - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2928 | JDH4-02-007-PR-2928 | Material Fabrication for Low Voltage Feeder Cable - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2929 | JDH4-02-007-PR-2929 | Material Fabrication for Low Voltage Feeder Cable - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2930 | JDH4-02-007-PR-2930 | Material Fabrication for Low Voltage Feeder Cable - Stage 4 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2940 | JDH4-02-007-PR-2940 | Material Delivery for Low Voltage Feeder Cable | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-2950 | JDH4-02-007-PR-2950 | Staging Time for Low Voltage Feeder Cable | 0 | 100% | 0% | 100% | 0 | 0
Wiring Devices | Wiring Devices |  | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-2780 | JDH4-02-007-PR-2780 | PO for Wiring Devices | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2815 | JDH4-02-007-PR-2815 | Material Fabrication for Wiring Devices - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2816 | JDH4-02-007-PR-2816 | Material Fabrication for Wiring Devices - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2817 | JDH4-02-007-PR-2817 | Material Fabrication for Wiring Devices - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2818 | JDH4-02-007-PR-2818 | Material Fabrication for Wiring Devices - Stage 4 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2819 | JDH4-02-007-PR-2819 | Material Fabrication for Wiring Devices - Stage 5 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2820 | JDH4-02-007-PR-2820 | Material Fabrication for Wiring Devices - Stage 6 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2860 | JDH4-02-007-PR-2860 | Material Delivery for Wiring Devices | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-2900 | JDH4-02-007-PR-2900 | Staging Time for Wiring Devices | 0 | 100% | 0% | 100% | 0 | 0
Enclosed Switches and Circuit Breakers | Enclosed Switches and Circuit Breakers |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-2960 | JDH4-02-007-PR-2960 | PO for Enclosed Switches and Circuit Breakers | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2965 | JDH4-02-007-PR-2965 | Material Fabrication for Enclosed Switches and Circuit Breakers - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2966 | JDH4-02-007-PR-2966 | Material Fabrication for Enclosed Switches and Circuit Breakers - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2967 | JDH4-02-007-PR-2967 | Material Fabrication for Enclosed Switches and Circuit Breakers - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2968 | JDH4-02-007-PR-2968 | Material Fabrication for Enclosed Switches and Circuit Breakers - Stage 4 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2969 | JDH4-02-007-PR-2969 | Material Fabrication for Enclosed Switches and Circuit Breakers - Stage 5 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2970 | JDH4-02-007-PR-2970 | Material Fabrication for Enclosed Switches and Circuit Breakers - Stage 6 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2980 | JDH4-02-007-PR-2980 | Material Delivery for Enclosed Switches and Circuit Breakers | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-2990 | JDH4-02-007-PR-2990 | Staging Time for Enclosed Switches and Circuit Breakers | 0 |  | 0%
Raceways for Electrical Systems | Raceways for Electrical Systems |  | 179076.09 |  | 0%
JDH4-02-007-PR-2790 | JDH4-02-007-PR-2790 | PO for Raceways for Electrical Systems | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2827 | JDH4-02-007-PR-2827 | Material Fabrication for Raceways for Electrical Systems - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2828 | JDH4-02-007-PR-2828 | Material Fabrication for Raceways for Electrical Systems - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2829 | JDH4-02-007-PR-2829 | Material Fabrication for Raceways for Electrical Systems - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2830 | JDH4-02-007-PR-2830 | Material Fabrication for Raceways for Electrical Systems - Stage 4 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2870 | JDH4-02-007-PR-2870 | Material Delivery for Raceways for Electrical Systems | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-2910 | JDH4-02-007-PR-2910 | Staging Time for Raceways for Electrical Systems | 0 | 100% | 0% | 100% | 0 | 0
Electrical Manholes | Electrical Manholes |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-2520 | JDH4-02-007-PR-2520 | PO for Electrical Manholes | 0 |  | 0%
JDH4-02-007-PR-2555 | JDH4-02-007-PR-2555 | Material Fabrication for Electrical Manholes - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2556 | JDH4-02-007-PR-2556 | Material Fabrication for Electrical Manholes - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2557 | JDH4-02-007-PR-2557 | Material Fabrication for Electrical Manholes - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2558 | JDH4-02-007-PR-2558 | Material Fabrication for Electrical Manholes - Stage 4 | 0 |  | 0%
JDH4-02-007-PR-2559 | JDH4-02-007-PR-2559 | Material Fabrication for Electrical Manholes - Stage 5 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2560 | JDH4-02-007-PR-2560 | Material Fabrication for Electrical Manholes - Stage 6 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-2600 | JDH4-02-007-PR-2600 | Material Delivery for Electrical Manholes | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-2640 | JDH4-02-007-PR-2640 | Staging Time for Electrical Manholes | 0 |  | 0%
ICT (Data& telephone System) | ICT (Data& telephone System) |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-3040 | JDH4-02-007-PR-3040 | PO for ICT (Data& telephone System) | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-3055 | JDH4-02-007-PR-3055 | Material Fabrication for ICT (Data& telephone System) - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-3056 | JDH4-02-007-PR-3056 | Material Fabrication for ICT (Data& telephone System) - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-3057 | JDH4-02-007-PR-3057 | Material Fabrication for ICT (Data& telephone System) - Stage 3 | 0 |  | 0%
JDH4-02-007-PR-3058 | JDH4-02-007-PR-3058 | Material Fabrication for ICT (Data& telephone System) - Stage 4 | 0 |  | 0%
JDH4-02-007-PR-3059 | JDH4-02-007-PR-3059 | Material Fabrication for ICT (Data& telephone System) - Stage 5 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-3060 | JDH4-02-007-PR-3060 | Material Fabrication for ICT (Data& telephone System) - Stage 6 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-3080 | JDH4-02-007-PR-3080 | Material Delivery for ICT (Data& telephone System) | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-3100 | JDH4-02-007-PR-3100 | Staging Time for ICT (Data& telephone System) | 0 | 100% | 0% | 100% | 0 | 0
Programmable Logic Controllers | Programmable Logic Controllers |  | 179076.09 |  | 0%
JDH4-02-007-PR-3120 | JDH4-02-007-PR-3120 | PO for Programmable Logic Controllers | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-3125 | JDH4-02-007-PR-3125 | Material Fabrication for Programmable Logic Controllers - Stage 1 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-3126 | JDH4-02-007-PR-3126 | Material Fabrication for Programmable Logic Controllers - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-3127 | JDH4-02-007-PR-3127 | Material Fabrication for Programmable Logic Controllers - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-3128 | JDH4-02-007-PR-3128 | Material Fabrication for Programmable Logic Controllers - Stage 4 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-3129 | JDH4-02-007-PR-3129 | Material Fabrication for Programmable Logic Controllers - Stage 5 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-3130 | JDH4-02-007-PR-3130 | Material Fabrication for Programmable Logic Controllers - Stage 6 | 0 |  | 0%
JDH4-02-007-PR-3140 | JDH4-02-007-PR-3140 | Material Delivery for Programmable Logic Controllers | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-3150 | JDH4-02-007-PR-3150 | Staging Time for Programmable Logic Controllers | 0 | 100% | 0% | 100% | 0 | 0
Process Control Wiring | Process Control Wiring |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-3050 | JDH4-02-007-PR-3050 | PO for Process Control Wiring | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-3067 | JDH4-02-007-PR-3067 | Material Fabrication for Process Control Wiring - Stage 1 | 0 |  | 0%
JDH4-02-007-PR-3068 | JDH4-02-007-PR-3068 | Material Fabrication for Process Control Wiring - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-3069 | JDH4-02-007-PR-3069 | Material Fabrication for Process Control Wiring - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-3070 | JDH4-02-007-PR-3070 | Material Fabrication for Process Control Wiring - Stage 4 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-3090 | JDH4-02-007-PR-3090 | Material Delivery for Process Control Wiring | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-3110 | JDH4-02-007-PR-3110 | Staging Time for Process Control Wiring | 0 |  | 0%
Instrumentation for Process Systems | Instrumentation for Process Systems |  | 179076.09 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-PR-3000 | JDH4-02-007-PR-3000 | PO for Instrumentation for Process Systems | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-3005 | JDH4-02-007-PR-3005 | Material Fabrication for Instrumentation for Process Systems - Stage 1 | 0 |  | 0%
JDH4-02-007-PR-3006 | JDH4-02-007-PR-3006 | Material Fabrication for Instrumentation for Process Systems - Stage 2 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-3007 | JDH4-02-007-PR-3007 | Material Fabrication for Instrumentation for Process Systems - Stage 3 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-3008 | JDH4-02-007-PR-3008 | Material Fabrication for Instrumentation for Process Systems - Stage 4 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-3009 | JDH4-02-007-PR-3009 | Material Fabrication for Instrumentation for Process Systems - Stage 5 | 0 |  | 0%
JDH4-02-007-PR-3010 | JDH4-02-007-PR-3010 | Material Fabrication for Instrumentation for Process Systems - Stage 6 | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-PR-3020 | JDH4-02-007-PR-3020 | Material Delivery for Instrumentation for Process Systems | 179076.09 | 100% | 0% | 100% | 179076.09 | 0
JDH4-02-007-PR-3030 | JDH4-02-007-PR-3030 | Staging Time for Instrumentation for Process Systems | 0 | 100% | 0% | 100% | 0 | 0
Construction | Construction |  | 38393913.06 |  | 0%
Demolition Works | Demolition Works |  | 506619.53 | 100% | 0% | 100% | 506619.53 | 0
Demolition in Road network | Demolition in Road network |  | 127411.78 | 100% | 0% | 100% | 127411.78 | 0
JDH4-02-007-CN-1000 | JDH4-02-007-CN-1000 | Concrete demolition works at the existing Underpass [Demolition Works ] | 26491.56 | 100% | 0% | 100% | 26491.56 | 0
JDH4-02-007-CN-1080 | JDH4-02-007-CN-1080 | Removal of the existing asphalt layers (up to base course layer) [Demolition Works ] | 37845.08 |  | 0%
JDH4-02-007-CN-1110 | JDH4-02-007-CN-1110 | Milling of the existing asphalt layer [Demolition Works ] | 25230.06 | 100% | 0% | 100% | 25230.06 | 0
JDH4-02-007-CN-1170 | JDH4-02-007-CN-1170 | Re-use and compaction of the existing aggregate base course layer | 37845.08 | 100% | 0% | 100% | 37845.08 | 0
Demolition in TSE network | Demolition in TSE network |  | 92720.46 | 100% | 0% | 100% | 92720.46 | 0
JDH4-02-007-CN-1480 | JDH4-02-007-CN-1480 | Pipe with diameter 63 mm pipe [Demolition Works ] | 1892.25 |  | 0%
JDH4-02-007-CN-1560 | JDH4-02-007-CN-1560 | Pipe with diameter 200 mm pipe [Demolition Works ] | 47937.11 | 100% | 0% | 100% | 47937.11 | 0
JDH4-02-007-CN-1590 | JDH4-02-007-CN-1590 | Pipe with diameter 250 mm pipe [Demolition Works ] | 18922.54 | 100% | 0% | 100% | 18922.54 | 0
JDH4-02-007-CN-1610 | JDH4-02-007-CN-1610 | Wash out valve with chamber; on 200 mm dia pipeline Depth 1.5 - 4.0m [Demolition Works ] | 20184.04 | 100% | 0% | 100% | 20184.04 | 0
JDH4-02-007-CN-1620 | JDH4-02-007-CN-1620 | Gate valves on 200 mm pipeline [Demolition Works ] | 3784.51 |  | 0%
Demolition in Storm water network | Demolition in Storm water network |  | 56073.8 |  | 0%
JDH4-02-007-CN-1670 | JDH4-02-007-CN-1670 | Manhole [Demolition Works ] | 8830.52 | 100% | 0% | 100% | 8830.52 | 0
JDH4-02-007-CN-1680 | JDH4-02-007-CN-1680 | Baffle box with dimentions 3.04x7.80m [Demolition Works ] | 18922.54 | 100% | 0% | 100% | 18922.54 | 0
JDH4-02-007-CN-1690 | JDH4-02-007-CN-1690 | Pipe with diameter 600 mm pipe [Demolition Works ] | 14128.83 | 100% | 0% | 100% | 14128.83 | 0
JDH4-02-007-CN-1700 | JDH4-02-007-CN-1700 | Pipe with diameter 800 mm pipe [Demolition Works ] | 14191.91 |  | 0%
Demolition in Sewerage network | Demolition in Sewerage network |  | 93225.06 | 100% | 0% | 100% | 93225.06 | 0
JDH4-02-007-CN-1630 | JDH4-02-007-CN-1630 | Pipe with diameter 200 mm pipe with depth 2.50 - 3.50m [Demolition Works ] | 26491.56 | 100% | 0% | 100% | 26491.56 | 0
JDH4-02-007-CN-1640 | JDH4-02-007-CN-1640 | Pipe with diameter 250 mm pipe with depth 3.50 - 4.50m [Demolition Works ] | 38349.69 | 100% | 0% | 100% | 38349.69 | 0
JDH4-02-007-CN-1650 | JDH4-02-007-CN-1650 | Manhole with depth 1.50m - 2.50m [Demolition Works ] | 12615.03 |  | 0%
JDH4-02-007-CN-1660 | JDH4-02-007-CN-1660 | Manhole with depth 4.50m - 5.50m [Demolition Works ] | 15768.79 | 100% | 0% | 100% | 15768.79 | 0
Demolition in Potable water network | Demolition in Potable water network |  | 46990.98 | 100% | 0% | 100% | 46990.98 | 0
JDH4-02-007-CN-1340 | JDH4-02-007-CN-1340 | Single house connection dia 63 mm [Demolition Works ] | 15768.79 |  | 0%
JDH4-02-007-CN-1400 | JDH4-02-007-CN-1400 | Pipe with diameter 200 mm [Demolition Works ] | 15453.41 | 100% | 0% | 100% | 15453.41 | 0
JDH4-02-007-CN-1430 | JDH4-02-007-CN-1430 | Wash out valve with chamber; on 200 mm dia pipeline [Demolition Works ] | 15768.79 | 100% | 0% | 100% | 15768.79 | 0
Demolition in Electrical works | Demolition in Electrical works |  | 90197.45 |  | 0%
JDH4-02-007-CN-1250 | JDH4-02-007-CN-1250 | Demolishing of existing Lighting Pole [Demolition Works ] | 20814.8 |  | 0%
JDH4-02-007-CN-3020 | JDH4-02-007-CN-3020 | Relocating of existing Lighting Pole [Road 02 ] | 42575.72 | 100% | 0% | 100% | 42575.72 | 0
JDH4-02-007-CN-3030 | JDH4-02-007-CN-3030 | Relocating of existing Lighting Pole [Road 08 ] | 4730.64 | 100% | 0% | 100% | 4730.64 | 0
JDH4-02-007-CN-3040 | JDH4-02-007-CN-3040 | Relocating of existing Lighting Pole [Road 04-R ] | 12615.03 | 100% | 0% | 100% | 12615.03 | 0
JDH4-02-007-CN-3050 | JDH4-02-007-CN-3050 | Relocating of existing Lighting Pole [Road 10 ] | 9461.27 | 100% | 0% | 100% | 9461.27 | 0
Plots | Plots |  | 7378530.38 | 100% | 0% | 100% | 7378530.38 | 0
Excavation | Excavation |  | 282577.06 | 100% | 0% | 100% | 282577.06 | 0
JDH4-02-007-CN-1760 | JDH4-02-007-CN-1760 | Plots excavation [Plots ] | 282577.06 |  | 0%
Backfilling | Backfilling |  | 7095953.32 | 100% | 0% | 100% | 7095953.32 | 0
JDH4-02-007-CN-1820 | JDH4-02-007-CN-1820 | Plots backfilling Stage 1 [Plots ] | 1013707.62 | 100% | 0% | 100% | 1013707.62 | 0
JDH4-02-007-CN-1830 | JDH4-02-007-CN-1830 | Plots backfilling Stage 2 [Plots ] | 1013707.62 | 100% | 0% | 100% | 1013707.62 | 0
JDH4-02-007-CN-1840 | JDH4-02-007-CN-1840 | Plots backfilling Stage 3 [Plots ] | 1013707.62 | 100% | 0% | 100% | 1013707.62 | 0
JDH4-02-007-CN-1850 | JDH4-02-007-CN-1850 | Plots backfilling Stage 4 [Plots ] | 1013707.62 | 100% | 0% | 100% | 1013707.62 | 0
JDH4-02-007-CN-1860 | JDH4-02-007-CN-1860 | Plots backfilling Stage 5 [Plots ] | 1013707.62 | 100% | 0% | 100% | 1013707.62 | 0
JDH4-02-007-CN-1870 | JDH4-02-007-CN-1870 | Plots backfilling Stage 6 [Plots ] | 1013707.62 |  | 0%
JDH4-02-007-CN-1880 | JDH4-02-007-CN-1880 | Plots backfilling Stage 7 [Plots ] | 1013707.62 | 60% | 0% | 60% | 608224.572 | 0
Roads | Roads |  | 27459419.74 | 98.67% | 1.09% | 99.76% | 27393517.1326 | 299307.6752
Road 04-R | Road 04-R |  | 5771861.74 | 100% | 0% | 100% | 5771861.74 | 0
Box Culvert | Box Culvert |  | 499321.73 | 100% | 0% | 100% | 499321.73 | 0
JDH4-02-007-CN-5580 | JDH4-02-007-CN-5580 | Excavation For Box Culvert [Road 04-R ] | 47552.35 | 100% | 0% | 100% | 47552.35 | 0
JDH4-02-007-CN-5590 | JDH4-02-007-CN-5590 | Backfilling For Box Culvert [Road 04-R ] | 30578.83 | 100% | 0% | 100% | 30578.83 | 0
JDH4-02-007-CN-5600 | JDH4-02-007-CN-5600 | Plain Concrete for box culvert [Road 04-R ] | 19679.44 |  | 0%
JDH4-02-007-CN-5610 | JDH4-02-007-CN-5610 | Steel Reinforcement for box culverts [Road 04-R ] | 169041.38 | 100% | 0% | 100% | 169041.38 | 0
JDH4-02-007-CN-5620 | JDH4-02-007-CN-5620 | Reinforced Concrete for box culvert [Road 04-R ] | 232469.74 |  | 0%
Road Works + Roundabout | Road Works + Roundabout |  | 3655858.23 | 100% | 0% | 100% | 3655858.23 | 0
Eartworks & Site grading | Eartworks & Site grading |  | 1552909.29 |  | 0%
JDH4-02-007-CN-1750 | JDH4-02-007-CN-1750 | Road excavation [Road 04-R ] | 35021.89 | 100% | 0% | 100% | 35021.89 | 0
JDH4-02-007-CN-1810 | JDH4-02-007-CN-1810 | Road backfilling [Road 04-R ] | 1378806.79 |  | 0%
JDH4-02-007-CN-1930 | JDH4-02-007-CN-1930 | Subgrade [Road 04-R ] | 139080.6 | 100% | 0% | 100% | 139080.6 | 0
Asphalt Works | Asphalt Works |  | 931597.74 |  | 0%
JDH4-02-007-CN-1990 | JDH4-02-007-CN-1990 | Aggregate base course [Road 04-R ] | 141644.69 | 100% | 0% | 100% | 141644.69 | 0
JDH4-02-007-CN-2040 | JDH4-02-007-CN-2040 | Prime Coat (MC1) [Road 04-R ] | 78995.31 |  | 0%
JDH4-02-007-CN-2090 | JDH4-02-007-CN-2090 | Bituminous base course [Road 04-R ] | 710957.75 | 100% | 0% | 100% | 710957.75 | 0
Finishing Works | Finishing Works |  | 1171351.21 |  | 0%
Asphalt Wearing Course | Asphalt Wearing Course |  | 418188.18 | 100% | 0% | 100% | 418188.18 | 0
JDH4-02-007-CN-2140 | JDH4-02-007-CN-2140 | Tack Coat (RC2) [Road 04-R ] | 41818.82 |  | 0%
JDH4-02-007-CN-2190 | JDH4-02-007-CN-2190 | Bituminous concrete wearing course [Road 04-R ] | 376369.36 | 100% | 0% | 100% | 376369.36 | 0
Precast Concrete Curb | Precast Concrete Curb |  | 260761.75 |  | 0%
JDH4-02-007-CN-2240 | JDH4-02-007-CN-2240 | Installation of Precast Concrete curb [Road 04-R ] | 260761.75 | 100% | 0% | 100% | 260761.75 | 0
Precast Interlocking block pavers | Precast Interlocking block pavers |  | 247979.91 |  | 0%
JDH4-02-007-CN-2290 | JDH4-02-007-CN-2290 | Installation of Interlocking block pavers for sidewalk/footpath [Road 04-R ] | 247979.91 |  | 0%
Pavement Markings | Pavement Markings |  | 70108.71 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-2340 | JDH4-02-007-CN-2340 | Pavement markings [Road 04-R ] | 70108.71 | 100% | 0% | 100% | 70108.71 | 0
Traffic Signage | Traffic Signage |  | 119121.91 | 100% | 0% | 100% | 119121.91 | 0
JDH4-02-007-CN-2390 | JDH4-02-007-CN-2390 | Installation of Traffic Signs [Road 04-R ] | 119121.91 | 100% | 0% | 100% | 119121.91 | 0
Guardrail | Guardrail |  | 55190.75 | 100% | 0% | 100% | 55190.75 | 0
JDH4-02-007-CN-2400 | JDH4-02-007-CN-2400 | Installation of Guard rails [Road 04-R ] | 55190.75 | 100% | 0% | 100% | 55190.75 | 0
Storm Water Drainage | Storm Water Drainage |  | 615872.64 |  | 0%
Pipe Works | Pipe Works |  | 372595.5 | 100% | 0% | 100% | 372595.5 | 0
JDH4-02-007-CN-5370 | JDH4-02-007-CN-5370 | Excavation and Compaction (FDT) [Road 04-R ] | 37259.53 | 100% | 0% | 100% | 37259.53 | 0
JDH4-02-007-CN-5420 | JDH4-02-007-CN-5420 | Sand Bedding [Road 04-R ] | 18629.79 | 100% | 0% | 100% | 18629.79 | 0
JDH4-02-007-CN-5470 | JDH4-02-007-CN-5470 | Installation of GRP Pipe [Road 04-R ] | 260816.86 | 100% | 0% | 100% | 260816.86 | 0
JDH4-02-007-CN-5520 | JDH4-02-007-CN-5520 | Sand Cover & Warning Tape [Road 04-R ] | 18629.79 | 100% | 0% | 100% | 18629.79 | 0
JDH4-02-007-CN-5570 | JDH4-02-007-CN-5570 | Backfilling & Compaction [Road 04-R ] | 37259.53 | 100% | 0% | 100% | 37259.53 | 0
Pipe Encasement | Pipe Encasement |  | 13406.24 |  | 0%
JDH4-02-007-CN-5840 | JDH4-02-007-CN-5840 | Pipe Encasement Works [Road 04-R ] | 13406.24 | 100% | 0% | 100% | 13406.24 | 0
Manholes | Manholes |  | 130842.93 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-5670 | JDH4-02-007-CN-5670 | Installation of Precast Manhole Ring [Road 04-R ] | 130842.93 | 100% | 0% | 100% | 130842.93 | 0
Precast Acces Openinig | Precast Acces Openinig |  | 7569.02 | 100% | 0% | 100% | 7569.02 | 0
JDH4-02-007-CN-5720 | JDH4-02-007-CN-5720 | Installation of Precast Access Opening [Road 04-R ] | 7569.02 | 100% | 0% | 100% | 7569.02 | 0
Catch Basins | Catch Basins |  | 40998.84 | 100% | 0% | 100% | 40998.84 | 0
JDH4-02-007-CN-5760 | JDH4-02-007-CN-5760 | Construction of Catch basins [Road 04-R ] | 40998.84 |  | 0%
Concrete Outfalls | Concrete Outfalls |  | 50460.11 | 100% | 0% | 100% | 50460.11 | 0
JDH4-02-007-CN-5790 | JDH4-02-007-CN-5790 | Construction of Concrete outfall structure [Road 04-R ] | 50460.11 |  | 0%
Sewerage Network | Sewerage Network |  | 233849.27 | 100% | 0% | 100% | 233849.27 | 0
Pipe Works | Pipe Works |  | 151984.62 |  | 0%
JDH4-02-007-CN-4820 | JDH4-02-007-CN-4820 | Excavation & Compaction (FDT) [Road 04-R ] | 15198.47 | 100% | 0% | 100% | 15198.47 | 0
JDH4-02-007-CN-4890 | JDH4-02-007-CN-4890 | Sand Bedding [Road 04-R ] | 7599.22 |  | 0%
JDH4-02-007-CN-4960 | JDH4-02-007-CN-4960 | Installation of GRP Pipe [Road 04-R ] | 75992.31 | 100% | 0% | 100% | 75992.31 | 0
JDH4-02-007-CN-5030 | JDH4-02-007-CN-5030 | Gravity Test [Road 04-R ] | 30396.93 |  | 0%
JDH4-02-007-CN-5100 | JDH4-02-007-CN-5100 | Sand Cover & Warning Tape [Road 04-R ] | 7599.22 | 100% | 0% | 100% | 7599.22 | 0
JDH4-02-007-CN-5170 | JDH4-02-007-CN-5170 | Backfilling & Compaction [Road 04-R ] | 15198.47 |  | 0%
Pipe Encasement | Pipe Encasement |  | 760.54 | 100% | 0% | 100% | 760.54 | 0
JDH4-02-007-CN-5310 | JDH4-02-007-CN-5310 | Pipe Encasement Works [Road 04-R ] | 760.54 |  | 0%
Manholes | Manholes |  | 81104.12 |  | 0%
JDH4-02-007-CN-5240 | JDH4-02-007-CN-5240 | Installation of Manholes [Road 04-R ] | 81104.12 | 100% | 0% | 100% | 81104.12 | 0
TSE Network | TSE Network |  | 186231.53 | 0% | 0% | 0% | 0 | 0
Pipe Works | Pipe Works |  | 160003.07 | 100% | 0% | 100% | 160003.07 | 0
JDH4-02-007-CN-4040 | JDH4-02-007-CN-4040 | Excavation and Compaction (FDT) [Road 04-R ] | 15169.19 | 100% | 0% | 100% | 15169.19 | 0
JDH4-02-007-CN-4110 | JDH4-02-007-CN-4110 | Sand Bedding [Road 04-R ] | 7584.62 | 100% | 0% | 100% | 7584.62 | 0
JDH4-02-007-CN-4180 | JDH4-02-007-CN-4180 | Installation of HDPE Pipe [Road 04-R ] | 75846 | 100% | 0% | 100% | 75846 | 0
JDH4-02-007-CN-4250 | JDH4-02-007-CN-4250 | Initial Pressure Test [Road 04-R ] | 30338.38 | 100% | 0% | 100% | 30338.38 | 0
JDH4-02-007-CN-4700 | JDH4-02-007-CN-4700 | Point of Connection [Road 04-R ] | 8311.08 | 100% | 0% | 100% | 8311.08 | 0
JDH4-02-007-CN-4320 | JDH4-02-007-CN-4320 | Sand Cover & Warning [Road 04-R ] | 7584.62 | 100% | 0% | 100% | 7584.62 | 0
JDH4-02-007-CN-4390 | JDH4-02-007-CN-4390 | Backfilling & Compaction [Road 04-R ] | 15169.19 | 100% | 0% | 100% | 15169.19 | 0
Pipe Encasement | Pipe Encasement |  | 7554.9 | 100% | 0% | 100% | 7554.9 | 0
JDH4-02-007-CN-4460 | JDH4-02-007-CN-4460 | Encasement for Pipes [Road 04-R ] | 7554.9 | 100% | 0% | 100% | 7554.9 | 0
Valves | Valves |  | 18673.56 | 100% | 0% | 100% | 18673.56 | 0
JDH4-02-007-CN-4530 | JDH4-02-007-CN-4530 | Installation of Gate Valves [Road 04-R ] | 18673.56 | 100% | 0% | 100% | 18673.56 | 0
Potable Network | Potable Network |  | 193744.81 | 100% | 0% | 100% | 193744.81 | 0
Pipe Works | Pipe Works |  | 124027.27 | 100% | 0% | 100% | 124027.27 | 0
JDH4-02-007-CN-3360 | JDH4-02-007-CN-3360 | Excavation and Compaction (FDT) [Road 04-R ] | 12402.74 | 100% | 0% | 100% | 12402.74 | 0
JDH4-02-007-CN-3430 | JDH4-02-007-CN-3430 | Sand Bedding [Road 04-R ] | 6201.37 | 100% | 0% | 100% | 6201.37 | 0
JDH4-02-007-CN-3500 | JDH4-02-007-CN-3500 | Installation of HDPE Pipe [Road 04-R ] | 62013.62 | 100% | 0% | 100% | 62013.62 | 0
JDH4-02-007-CN-3570 | JDH4-02-007-CN-3570 | Initial Pressure Test [Road 04-R ] | 24805.44 | 100% | 0% | 100% | 24805.44 | 0
JDH4-02-007-CN-3640 | JDH4-02-007-CN-3640 | Sand Cover & Warning Tape [Road 04-R ] | 6201.37 | 100% | 0% | 100% | 6201.37 | 0
JDH4-02-007-CN-3710 | JDH4-02-007-CN-3710 | Backfilling [Road 04-R ] | 12402.74 | 100% | 0% | 100% | 12402.74 | 0
Pipe Encasement | Pipe Encasement |  | 9796.16 | 100% | 0% | 100% | 9796.16 | 0
JDH4-02-007-CN-3780 | JDH4-02-007-CN-3780 | Encasement for Pipes [Road 04-R ] | 9796.16 | 100% | 0% | 100% | 9796.16 | 0
Valves | Valves |  | 15768.79 | 100% | 0% | 100% | 15768.79 | 0
JDH4-02-007-CN-3850 | JDH4-02-007-CN-3850 | Installation of Gate Valves [Road 04-R ] | 15768.79 | 100% | 0% | 100% | 15768.79 | 0
Fire Hydrant | Fire Hydrant |  | 44152.6 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-3940 | JDH4-02-007-CN-3940 | Installation of 3-outlet fire hydrant [Road 04-R ] | 44152.6 | 100% | 0% | 100% | 44152.6 | 0
Electrical Works | Electrical Works |  | 386983.51 | 100% | 0% | 100% | 386983.51 | 0
Street Lighting | Street Lighting |  | 173158.78 | 100% | 0% | 100% | 173158.78 | 0
JDH4-02-007-CN-2820 | JDH4-02-007-CN-2820 | Excavation for Low Voltage Cable [Road 04-R ] | 9991.1 | 100% | 0% | 100% | 9991.1 | 0
JDH4-02-007-CN-2830 | JDH4-02-007-CN-2830 | Installation of Road Crossing Ducts [Road 04-R ] | 17941.62 | 100% | 0% | 100% | 17941.62 | 0
JDH4-02-007-CN-2880 | JDH4-02-007-CN-2880 | Installation of Low Voltage Cables [Road 04-R ] | 50825.95 | 100% | 0% | 100% | 50825.95 | 0
JDH4-02-007-CN-2920 | JDH4-02-007-CN-2920 | Installation of Lighting Poles [Road 04-R ] | 73193.61 | 100% | 0% | 100% | 73193.61 | 0
JDH4-02-007-CN-2960 | JDH4-02-007-CN-2960 | Installation of Lighting Luminaires [Road 04-R ] | 17422 | 100% | 0% | 100% | 17422 | 0
JDH4-02-007-CN-2990 | JDH4-02-007-CN-2990 | Installation of Earthing System [Road 04-R ] | 3784.51 |  | 0%
Telecommunication | Telecommunication |  | 213824.72 |  | 0%
JDH4-02-007-CN-3110 | JDH4-02-007-CN-3110 | Installation Road Crossing R/F 6 way 50mm HDPE Pipe [Road 04-R ] | 182034.85 | 100% | 0% | 100% | 182034.85 | 0
JDH4-02-007-CN-3180 | JDH4-02-007-CN-3180 | Installation Road Crossing Un R/F 6 way 50mm HDPE Pipe [Road 04-R ] | 3406.06 | 100% | 0% | 100% | 3406.06 | 0
JDH4-02-007-CN-3290 | JDH4-02-007-CN-3290 | Installation of Manholes [Road 04-R ] | 28383.81 | 100% | 0% | 100% | 28383.81 | 0
Road 08 | Road 08 |  | 5862192.51 | 100% | 0% | 100% | 5862192.51 | 0
Road Works + Roundabout | Road Works + Roundabout |  | 3190841.54 | 100% | 0% | 100% | 3190841.54 | 0
Eartworks & Site grading | Eartworks & Site grading |  | 1378550.68 | 100% | 0% | 100% | 1378550.68 | 0
JDH4-02-007-CN-1770 | JDH4-02-007-CN-1770 | Road backfilling [Road 08 ] | 1224367.31 |  | 0%
JDH4-02-007-CN-1710 | JDH4-02-007-CN-1710 | Road excavation [Road 08 ] | 31065.82 |  | 0%
JDH4-02-007-CN-1890 | JDH4-02-007-CN-1890 | Subgrade [Road 08 ] | 123117.55 | 100% | 0% | 100% | 123117.55 | 0
Asphalt Works | Asphalt Works |  | 825025.98 | 100% | 0% | 100% | 825025.98 | 0
JDH4-02-007-CN-1950 | JDH4-02-007-CN-1950 | Aggregate base course [Road 08 ] | 125409.15 | 100% | 0% | 100% | 125409.15 | 0
JDH4-02-007-CN-2000 | JDH4-02-007-CN-2000 | Prime Coat (MC1) [Road 08 ] | 70000.79 | 100% | 0% | 100% | 70000.79 | 0
JDH4-02-007-CN-2050 | JDH4-02-007-CN-2050 | Bituminous base course [Road 08 ] | 629616.05 | 100% | 0% | 100% | 629616.05 | 0
Finishing Works | Finishing Works |  | 987264.88 | 100% | 0% | 100% | 987264.88 | 0
Asphalt Wearing Course | Asphalt Wearing Course |  | 370629.52 | 100% | 0% | 100% | 370629.52 | 0
JDH4-02-007-CN-2100 | JDH4-02-007-CN-2100 | Tack Coat (RC2) [Road 08 ] | 36898.96 | 100% | 0% | 100% | 36898.96 | 0
JDH4-02-007-CN-2150 | JDH4-02-007-CN-2150 | Bituminous concrete wearing course [Road 08 ] | 333730.57 |  | 0%
Precast Concrete Curb | Precast Concrete Curb |  | 231115.34 | 100% | 0% | 100% | 231115.34 | 0
JDH4-02-007-CN-2200 | JDH4-02-007-CN-2200 | Installation of Precast Concrete curb [Road 08 ] | 231115.34 | 100% | 0% | 100% | 231115.34 | 0
Precast Interlocking block pavers | Precast Interlocking block pavers |  | 219785.33 | 100% | 0% | 100% | 219785.33 | 0
JDH4-02-007-CN-2250 | JDH4-02-007-CN-2250 | Installation of Interlocking block pavers for sidewalk/footpath [Road 08 ] | 219785.33 | 100% | 0% | 100% | 219785.33 | 0
Pavement Markings | Pavement Markings |  | 62150.42 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-2300 | JDH4-02-007-CN-2300 | Pavement markings [Road 08 ] | 62150.42 | 100% | 0% | 100% | 62150.42 | 0
Traffic Signage | Traffic Signage |  | 103584.27 | 100% | 0% | 100% | 103584.27 | 0
JDH4-02-007-CN-2350 | JDH4-02-007-CN-2350 | Installation of Traffic Signs [Road 08 ] | 103584.27 | 100% | 0% | 100% | 103584.27 | 0
Storm Water Drainage | Storm Water Drainage |  | 873381.08 |  | 0%
Pipe Works | Pipe Works |  | 547196.15 | 100% | 0% | 100% | 547196.15 | 0
JDH4-02-007-CN-5330 | JDH4-02-007-CN-5330 | Excavation and Compaction (FDT) [Road 08 ] | 54719.59 | 100% | 0% | 100% | 54719.59 | 0
JDH4-02-007-CN-5380 | JDH4-02-007-CN-5380 | Sand Bedding [Road 08 ] | 27359.83 | 100% | 0% | 100% | 27359.83 | 0
JDH4-02-007-CN-5430 | JDH4-02-007-CN-5430 | Installation of GRP Pipe [Road 08 ] | 383037.32 | 100% | 0% | 100% | 383037.32 | 0
JDH4-02-007-CN-5480 | JDH4-02-007-CN-5480 | Sand Cover & Warning Tape [Road 08 ] | 27359.83 | 100% | 0% | 100% | 27359.83 | 0
JDH4-02-007-CN-5530 | JDH4-02-007-CN-5530 | Backfilling & Compaction [Road 08 ] | 54719.59 | 100% | 0% | 100% | 54719.59 | 0
Pipe Encasement | Pipe Encasement |  | 20926.82 | 100% | 0% | 100% | 20926.82 | 0
JDH4-02-007-CN-5800 | JDH4-02-007-CN-5800 | Pipe Encasement Works [Road 08 ] | 20926.82 | 100% | 0% | 100% | 20926.82 | 0
Manholes | Manholes |  | 224206.55 |  | 0%
JDH4-02-007-CN-5630 | JDH4-02-007-CN-5630 | Installation of Precast Manhole Ring [Road 08 ] | 224206.55 | 100% | 0% | 100% | 224206.55 | 0
Precast Acces Openinig | Precast Acces Openinig |  | 11353.53 | 100% | 0% | 100% | 11353.53 | 0
JDH4-02-007-CN-5680 | JDH4-02-007-CN-5680 | Installation of Precast Access Opening [Road 08 ] | 11353.53 | 100% | 0% | 100% | 11353.53 | 0
Catch Basins | Catch Basins |  | 69698.03 | 100% | 0% | 100% | 69698.03 | 0
JDH4-02-007-CN-5730 | JDH4-02-007-CN-5730 | Construction of Catch basins [Road 08 ] | 69698.03 | 100% | 0% | 100% | 69698.03 | 0
Sewerage Network | Sewerage Network |  | 558310.65 | 100% | 0% | 100% | 558310.65 | 0
Pipe Works | Pipe Works |  | 329545.93 | 100% | 0% | 100% | 329545.93 | 0
JDH4-02-007-CN-4780 | JDH4-02-007-CN-4780 | Excavation & Compaction (FDT) [Road 08 ] | 32954.6 | 100% | 0% | 100% | 32954.6 | 0
JDH4-02-007-CN-4850 | JDH4-02-007-CN-4850 | Sand Bedding [Road 08 ] | 16477.28 |  | 0%
JDH4-02-007-CN-4920 | JDH4-02-007-CN-4920 | Installation of GRP Pipe [Road 08 ] | 164772.96 | 100% | 0% | 100% | 164772.96 | 0
JDH4-02-007-CN-4990 | JDH4-02-007-CN-4990 | Gravity Test [Road 08 ] | 65909.2 | 100% | 0% | 100% | 65909.2 | 0
JDH4-02-007-CN-5060 | JDH4-02-007-CN-5060 | Sand Cover & Warning Tape [Road 08 ] | 16477.28 | 100% | 0% | 100% | 16477.28 | 0
JDH4-02-007-CN-5130 | JDH4-02-007-CN-5130 | Backfilling & Compaction [Road 08 ] | 32954.6 | 100% | 0% | 100% | 32954.6 | 0
Pipe Encasement | Pipe Encasement |  | 1673.19 | 100% | 0% | 100% | 1673.19 | 0
JDH4-02-007-CN-5270 | JDH4-02-007-CN-5270 | Pipe Encasement Works [Road 08 ] | 1673.19 | 100% | 0% | 100% | 1673.19 | 0
Manholes | Manholes |  | 227091.53 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-5200 | JDH4-02-007-CN-5200 | Installation of Manholes [Road 08 ] | 227091.53 | 100% | 0% | 100% | 227091.53 | 0
TSE Network | TSE Network |  | 229231.81 |  | 0%
Pipe Works | Pipe Works |  | 195413.82 |  | 0%
JDH4-02-007-CN-4000 | JDH4-02-007-CN-4000 | Excavation and Compaction (FDT) [Road 08 ] | 18710.26 |  | 0%
JDH4-02-007-CN-4070 | JDH4-02-007-CN-4070 | Sand Bedding [Road 08 ] | 9355.16 | 100% | 0% | 100% | 9355.16 | 0
JDH4-02-007-CN-4140 | JDH4-02-007-CN-4140 | Installation of HDPE Pipe [Road 08 ] | 93551.37 | 100% | 0% | 100% | 93551.37 | 0
JDH4-02-007-CN-4210 | JDH4-02-007-CN-4210 | Initial Pressure Test [Road 08 ] | 37420.53 | 100% | 0% | 100% | 37420.53 | 0
JDH4-02-007-CN-4660 | JDH4-02-007-CN-4660 | Point of Connection [Road 08 ] | 8311.08 | 100% | 0% | 100% | 8311.08 | 0
JDH4-02-007-CN-4280 | JDH4-02-007-CN-4280 | Sand Cover & Warning [Road 08 ] | 9355.16 | 100% | 0% | 100% | 9355.16 | 0
JDH4-02-007-CN-4350 | JDH4-02-007-CN-4350 | Backfilling & Compaction [Road 08 ] | 18710.26 | 100% | 0% | 100% | 18710.26 | 0
Pipe Encasement | Pipe Encasement |  | 9368.07 | 100% | 0% | 100% | 9368.07 | 0
JDH4-02-007-CN-4420 | JDH4-02-007-CN-4420 | Encasement for Pipes [Road 08 ] | 9368.07 | 100% | 0% | 100% | 9368.07 | 0
Valves | Valves |  | 11204.14 | 100% | 0% | 100% | 11204.14 | 0
JDH4-02-007-CN-4490 | JDH4-02-007-CN-4490 | Installation of Gate Valves [Road 08 ] | 11204.14 | 100% | 0% | 100% | 11204.14 | 0
Risers | Risers |  | 13245.78 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-4730 | JDH4-02-007-CN-4730 | Installation of Irrigation Riser with [Road 08 ] | 13245.78 | 100% | 0% | 100% | 13245.78 | 0
Potable Network | Potable Network |  | 199289.74 | 100% | 0% | 100% | 199289.74 | 0
Pipe Works | Pipe Works |  | 125752.87 | 100% | 0% | 100% | 125752.87 | 0
JDH4-02-007-CN-3320 | JDH4-02-007-CN-3320 | Excavation and Compaction (FDT) [Road 08 ] | 12575.3 | 100% | 0% | 100% | 12575.3 | 0
JDH4-02-007-CN-3390 | JDH4-02-007-CN-3390 | Sand Bedding [Road 08 ] | 6287.65 | 100% | 0% | 100% | 6287.65 | 0
JDH4-02-007-CN-3460 | JDH4-02-007-CN-3460 | Installation of HDPE Pipe [Road 08 ] | 62876.41 | 100% | 0% | 100% | 62876.41 | 0
JDH4-02-007-CN-3530 | JDH4-02-007-CN-3530 | Initial Pressure Test [Road 08 ] | 25150.56 | 100% | 0% | 100% | 25150.56 | 0
JDH4-02-007-CN-3600 | JDH4-02-007-CN-3600 | Sand Cover & Warning Tape [Road 08 ] | 6287.65 | 100% | 0% | 100% | 6287.65 | 0
JDH4-02-007-CN-3670 | JDH4-02-007-CN-3670 | Backfilling [Road 08 ] | 12575.3 | 100% | 0% | 100% | 12575.3 | 0
Pipe Encasement | Pipe Encasement |  | 9936.1 | 100% | 0% | 100% | 9936.1 | 0
JDH4-02-007-CN-3740 | JDH4-02-007-CN-3740 | Encasement for Pipes [Road 08 ] | 9936.1 | 100% | 0% | 100% | 9936.1 | 0
Valves | Valves |  | 13140.65 | 100% | 0% | 100% | 13140.65 | 0
JDH4-02-007-CN-3810 | JDH4-02-007-CN-3810 | Installation of Gate Valves [Road 08 ] | 13140.65 | 100% | 0% | 100% | 13140.65 | 0
Fire Hydrant | Fire Hydrant |  | 50460.11 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-3900 | JDH4-02-007-CN-3900 | Installation of 3-outlet fire hydrant [Road 08 ] | 50460.11 | 100% | 0% | 100% | 50460.11 | 0
Electrical Works | Electrical Works |  | 811137.69 | 100% | 0% | 100% | 811137.69 | 0
MV & LV Cables | MV & LV Cables |  | 361241.37 | 0% | 100% | 100% | 361241.37 | 361241.37
Medium Voltage Cable | Medium Voltage Cable |  | 165937.27 |  | 0%
JDH4-02-007-CN-2420 | JDH4-02-007-CN-2420 | Excavation for Trench [Road 08 ] | 7545 | 100% | 0% | 100% | 7545 | 0
JDH4-02-007-CN-2480 | JDH4-02-007-CN-2480 | Installation of Duct banks [Road 08 ] | 31916.02 | 100% | 0% | 100% | 31916.02 | 0
JDH4-02-007-CN-2540 | JDH4-02-007-CN-2540 | Installation of Medium Voltage Cables [Road 08 ] | 126476.25 | 100% | 0% | 100% | 126476.25 | 0
Low Voltage Cable | Low Voltage Cable |  | 195304.09 | 100% | 0% | 100% | 195304.09 | 0
JDH4-02-007-CN-2595 | JDH4-02-007-CN-2595 | Excavation for Low Voltage Cable [Road 08 ] | 10823.69 | 100% | 0% | 100% | 10823.69 | 0
JDH4-02-007-CN-2600 | JDH4-02-007-CN-2600 | Installation of Low Voltage Cables [Road 08 ] | 29946.31 | 100% | 0% | 100% | 29946.31 | 0
JDH4-02-007-CN-2710 | JDH4-02-007-CN-2710 | Installation of Low Voltage Distribution Panel (Main: 100A, MCCB, 5-50A, MCCB) [Road 08 ] | 15768.79 | 100% | 0% | 100% | 15768.79 | 0
JDH4-02-007-CN-2730 | JDH4-02-007-CN-2730 | Installation of Unit Substation , 13.8/0.4 kV, 500kVA with RMU [Road 08 ] | 75690.17 | 100% | 0% | 100% | 75690.17 | 0
JDH4-02-007-CN-2740 | JDH4-02-007-CN-2740 | Installation of Ring Main Unit (RMU) 3-way, 13.8kV [Road 08 ] | 63075.14 | 100% | 0% | 100% | 63075.14 | 0
Street Lighting | Street Lighting |  | 175355.47 | 100% | 0% | 100% | 175355.47 | 0
JDH4-02-007-CN-2750 | JDH4-02-007-CN-2750 | Excavation for Low Voltage Cable [Road 08 ] | 8325.92 | 100% | 0% | 100% | 8325.92 | 0
JDH4-02-007-CN-2760 | JDH4-02-007-CN-2760 | Installation of Road Crossing Ducts [Road 08 ] | 17695.84 | 100% | 0% | 100% | 17695.84 | 0
JDH4-02-007-CN-2840 | JDH4-02-007-CN-2840 | Installation of Low Voltage Cables [Road 08 ] | 42386.49 | 100% | 0% | 100% | 42386.49 | 0
JDH4-02-007-CN-2890 | JDH4-02-007-CN-2890 | Installation of Lighting Poles [Road 08 ] | 79467.35 | 100% | 0% | 100% | 79467.35 | 0
JDH4-02-007-CN-2930 | JDH4-02-007-CN-2930 | Installation of Lighting Luminaires [Road 08 ] | 19910.85 | 100% | 0% | 100% | 19910.85 | 0
JDH4-02-007-CN-2970 | JDH4-02-007-CN-2970 | Installation of Earthing System [Road 08 ] | 7569.02 | 100% | 0% | 100% | 7569.02 | 0
Telecommunication | Telecommunication |  | 274540.85 | 100% | 0% | 100% | 274540.85 | 0
JDH4-02-007-CN-3070 | JDH4-02-007-CN-3070 | Installation Road Crossing R/F 6 way 50mm HDPE Pipe [Road 08 ] | 126781.03 | 100% | 0% | 100% | 126781.03 | 0
JDH4-02-007-CN-3140 | JDH4-02-007-CN-3140 | Installation Road Crossing Un R/F 6 way 50mm HDPE Pipe [Road 08 ] | 3973.73 | 100% | 0% | 100% | 3973.73 | 0
JDH4-02-007-CN-3200 | JDH4-02-007-CN-3200 | Installation of 2 x 32 mm diameter HDPE ducts [Road 08 ] | 98371.99 | 100% | 0% | 100% | 98371.99 | 0
JDH4-02-007-CN-3250 | JDH4-02-007-CN-3250 | Installation of Manholes [Road 08 ] | 45414.1 | 100% | 0% | 100% | 45414.1 | 0
Road 01 | Road 01 |  | 3665687.82 | 92.5% | 5.93% | 98.43% | 3608136.5212 | 217375.2877
Road Works (Roundabout) | Road Works (Roundabout) |  | 826699.01 | 69.16% | 24.37% | 93.53% | 773211.5841 | 201466.5487
Eartworks & Site grading | Eartworks & Site grading |  | 357790.57 | 100% | 0% | 100% | 357790.57 | 0
JDH4-02-007-CN-1720 | JDH4-02-007-CN-1720 | Road excavation [Road 01 ] | 8053.45 | 100% | 0% | 100% | 8053.45 | 0
JDH4-02-007-CN-1780 | JDH4-02-007-CN-1780 | Road backfilling [Road 01 ] | 317788.32 |  | 0%
JDH4-02-007-CN-1900 | JDH4-02-007-CN-1900 | Subgrade [Road 01 ] | 31948.8 | 100% | 0% | 100% | 31948.8 | 0
Asphalt Works | Asphalt Works |  | 213995.03 | 100% | 0% | 100% | 213995.03 | 0
JDH4-02-007-CN-1960 | JDH4-02-007-CN-1960 | Aggregate base course [Road 01 ] | 32540.46 | 100% | 0% | 100% | 32540.46 | 0
JDH4-02-007-CN-2010 | JDH4-02-007-CN-2010 | Prime Coat (MC1) [Road 01 ] | 17989.03 | 100% | 0% | 100% | 17989.03 | 0
JDH4-02-007-CN-2060 | JDH4-02-007-CN-2060 | Bituminous base course [Road 01 ] | 163465.53 | 100% | 0% | 100% | 163465.53 | 0
Finishing Works | Finishing Works |  | 254913.42 | 100% | 0% | 100% | 254913.42 | 0
Asphalt Wearing Course | Asphalt Wearing Course |  | 95937.29 | 100% | 0% | 100% | 95937.29 | 0
JDH4-02-007-CN-2110 | JDH4-02-007-CN-2110 | Tack Coat (RC2) [Road 01 ] | 9429.73 | 0% | 100% | 100% | 9429.73 | 9429.73
JDH4-02-007-CN-2160 | JDH4-02-007-CN-2160 | Bituminous concrete wearing course [Road 01 ] | 86507.55 | 0% | 100% | 100% | 86507.55 | 86507.55
Precast Concrete Curb | Precast Concrete Curb |  | 59926.12 | 100% | 0% | 100% | 59926.12 | 0
JDH4-02-007-CN-2210 | JDH4-02-007-CN-2210 | Installation of Precast Concrete curb [Road 01 ] | 59926.12 | 0% | 100% | 100% | 59926.12 | 59926.12
Precast Interlocking block pavers | Precast Interlocking block pavers |  | 57004.16 | 100% | 0% | 100% | 57004.16 | 0
JDH4-02-007-CN-2260 | JDH4-02-007-CN-2260 | Installation of Interlocking block pavers for sidewalk/footpath [Road 01 ] | 57004.16 | 0% | 80% | 80% | 45603.328 | 45603.328
Pavement Markings | Pavement Markings |  | 16149.78 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-2310 | JDH4-02-007-CN-2310 | Pavement markings [Road 01 ] | 16149.78 | 100% | 0% | 100% | 16149.78 | 0
Traffic Signage | Traffic Signage |  | 25896.07 | 100% | 0% | 100% | 25896.07 | 0
JDH4-02-007-CN-2360 | JDH4-02-007-CN-2360 | Installation of Traffic Signs [Road 01 ] | 25896.07 | 0% | 0% | 0% | 0 | 0
Storm Water Drainage | Storm Water Drainage |  | 131305.16 | 100% | 0% | 100% | 131305.16 | 0
Pipe Works | Pipe Works |  | 26247.16 | 100% | 0% | 100% | 26247.16 | 0
JDH4-02-007-CN-5340 | JDH4-02-007-CN-5340 | Excavation and Compaction (FDT) [Road 01 ] | 2624.71 | 100% | 0% | 100% | 2624.71 | 0
JDH4-02-007-CN-5390 | JDH4-02-007-CN-5390 | Sand Bedding [Road 01 ] | 1312.36 | 100% | 0% | 100% | 1312.36 | 0
JDH4-02-007-CN-5440 | JDH4-02-007-CN-5440 | Installation of GRP Pipe [Road 01 ] | 18373.01 | 100% | 0% | 100% | 18373.01 | 0
JDH4-02-007-CN-5490 | JDH4-02-007-CN-5490 | Sand Cover & Warning Tape [Road 01 ] | 1312.36 | 100% | 0% | 100% | 1312.36 | 0
JDH4-02-007-CN-5540 | JDH4-02-007-CN-5540 | Backfilling & Compaction [Road 01 ] | 2624.71 | 100% | 0% | 100% | 2624.71 | 0
Pipe Encasement | Pipe Encasement |  | 1307.93 | 100% | 0% | 100% | 1307.93 | 0
JDH4-02-007-CN-5810 | JDH4-02-007-CN-5810 | Pipe Encasement Works [Road 01 ] | 1307.93 |  | 0%
Manholes | Manholes |  | 74735.52 | 100% | 0% | 100% | 74735.52 | 0
JDH4-02-007-CN-5640 | JDH4-02-007-CN-5640 | Installation of Precast Manhole Ring [Road 01 ] | 74735.52 | 100% | 0% | 100% | 74735.52 | 0
Precast Acces Openinig | Precast Acces Openinig |  | 3784.51 | 100% | 0% | 100% | 3784.51 | 0
JDH4-02-007-CN-5690 | JDH4-02-007-CN-5690 | Installation of Precast Access Opening [Road 01 ] | 3784.51 | 100% | 0% | 100% | 3784.51 | 0
Concrete Outfalls | Concrete Outfalls |  | 25230.06 | 100% | 0% | 100% | 25230.06 | 0
JDH4-02-007-CN-5780 | JDH4-02-007-CN-5780 | Construction of Concrete outfall structure [Road 01 ] | 25230.06 | 100% | 0% | 100% | 25230.06 | 0
Sewerage Network | Sewerage Network |  | 134037.31 | 100% | 0% | 100% | 134037.31 | 0
Pipe Works | Pipe Works |  | 52628.98 | 100% | 0% | 100% | 52628.98 | 0
JDH4-02-007-CN-4790 | JDH4-02-007-CN-4790 | Excavation & Compaction (FDT) [Road 01 ] | 5262.9 | 100% | 0% | 100% | 5262.9 | 0
JDH4-02-007-CN-4860 | JDH4-02-007-CN-4860 | Sand Bedding [Road 01 ] | 2631.45 | 100% | 0% | 100% | 2631.45 | 0
JDH4-02-007-CN-4930 | JDH4-02-007-CN-4930 | Installation of GRP Pipe [Road 01 ] | 26314.49 | 100% | 0% | 100% | 26314.49 | 0
JDH4-02-007-CN-5000 | JDH4-02-007-CN-5000 | Gravity Test [Road 01 ] | 10525.8 | 100% | 0% | 100% | 10525.8 | 0
JDH4-02-007-CN-5070 | JDH4-02-007-CN-5070 | Sand Cover & Warning Tape [Road 01 ] | 2631.45 | 100% | 0% | 100% | 2631.45 | 0
JDH4-02-007-CN-5140 | JDH4-02-007-CN-5140 | Backfilling & Compaction [Road 01 ] | 5262.9 | 100% | 0% | 100% | 5262.9 | 0
Pipe Encasement | Pipe Encasement |  | 304.22 | 100% | 0% | 100% | 304.22 | 0
JDH4-02-007-CN-5280 | JDH4-02-007-CN-5280 | Pipe Encasement Works [Road 01 ] | 304.22 | 100% | 0% | 100% | 304.22 | 0
Manholes | Manholes |  | 81104.12 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-5210 | JDH4-02-007-CN-5210 | Installation of Manholes [Road 01 ] | 81104.12 | 100% | 0% | 100% | 81104.12 | 0
TSE Network | TSE Network |  | 315401.48 | 0% | 0% | 0% | 0 | 0
Pipe Works | Pipe Works |  | 199896.71 | 100% | 0% | 100% | 199896.71 | 0
JDH4-02-007-CN-4010 | JDH4-02-007-CN-4010 | Excavation and Compaction (FDT) [Road 01 ] | 18327.45 | 100% | 0% | 100% | 18327.45 | 0
JDH4-02-007-CN-4080 | JDH4-02-007-CN-4080 | Sand Bedding [Road 01 ] | 9163.75 | 100% | 0% | 100% | 9163.75 | 0
JDH4-02-007-CN-4150 | JDH4-02-007-CN-4150 | Installation of HDPE Pipe [Road 01 ] | 91637.28 | 100% | 0% | 100% | 91637.28 | 0
JDH4-02-007-CN-4220 | JDH4-02-007-CN-4220 | Initial Pressure Test [Road 01 ] | 36654.89 | 100% | 0% | 100% | 36654.89 | 0
JDH4-02-007-CN-4290 | JDH4-02-007-CN-4290 | Sand Cover & Warning [Road 01 ] | 9163.75 | 100% | 0% | 100% | 9163.75 | 0
JDH4-02-007-CN-4360 | JDH4-02-007-CN-4360 | Backfilling & Compaction [Road 01 ] | 18327.45 | 100% | 0% | 100% | 18327.45 | 0
JDH4-02-007-CN-4670 | JDH4-02-007-CN-4670 | Point of Connection [Road 01 ] | 16622.15 | 100% | 0% | 100% | 16622.15 | 0
Pipe Encasement | Pipe Encasement |  | 9065.88 | 100% | 0% | 100% | 9065.88 | 0
JDH4-02-007-CN-4430 | JDH4-02-007-CN-4430 | Encasement for Pipes [Road 01 ] | 9065.88 | 100% | 0% | 100% | 9065.88 | 0
Valves | Valves |  | 93193.11 | 100% | 0% | 100% | 93193.11 | 0
JDH4-02-007-CN-4500 | JDH4-02-007-CN-4500 | Installation of Gate Valves [Road 01 ] | 11204.14 | 100% | 0% | 100% | 11204.14 | 0
JDH4-02-007-CN-4550 | JDH4-02-007-CN-4550 | Installation of Butterfly Valves [Road 01 ] | 44152.6 | 100% | 0% | 100% | 44152.6 | 0
JDH4-02-007-CN-4560 | JDH4-02-007-CN-4560 | Installation of Washout Valves [Road 01 ] | 23329.09 | 100% | 0% | 100% | 23329.09 | 0
JDH4-02-007-CN-4580 | JDH4-02-007-CN-4580 | Installation of Air Valves [Road 01 ] | 14507.28 | 100% | 0% | 100% | 14507.28 | 0
Risers | Risers |  | 13245.78 | 100% | 0% | 100% | 13245.78 | 0
JDH4-02-007-CN-4740 | JDH4-02-007-CN-4740 | Installation of Irrigation Riser with [Road 01 ] | 13245.78 | 100% | 0% | 100% | 13245.78 | 0
Potable Network | Potable Network |  | 1242733.03 | 100% | 0% | 100% | 1242733.03 | 0
Pipe Works | Pipe Works |  | 176873.67 | 100% | 0% | 100% | 176873.67 | 0
JDH4-02-007-CN-3330 | JDH4-02-007-CN-3330 | Excavation and Compaction (FDT) [Road 01 ] | 17687.38 | 100% | 0% | 100% | 17687.38 | 0
JDH4-02-007-CN-3400 | JDH4-02-007-CN-3400 | Sand Bedding [Road 01 ] | 8843.69 | 100% | 0% | 100% | 8843.69 | 0
JDH4-02-007-CN-3470 | JDH4-02-007-CN-3470 | Installation of HDPE Pipe [Road 01 ] | 88436.81 | 100% | 0% | 100% | 88436.81 | 0
JDH4-02-007-CN-3540 | JDH4-02-007-CN-3540 | Initial Pressure Test [Road 01 ] | 35374.71 | 100% | 0% | 100% | 35374.71 | 0
JDH4-02-007-CN-3610 | JDH4-02-007-CN-3610 | Sand Cover & Warning Tape [Road 01 ] | 8843.69 | 100% | 0% | 100% | 8843.69 | 0
JDH4-02-007-CN-3680 | JDH4-02-007-CN-3680 | Backfilling [Road 01 ] | 17687.38 | 100% | 0% | 100% | 17687.38 | 0
Pipe Encasement | Pipe Encasement |  | 13294.79 | 100% | 0% | 100% | 13294.79 | 0
JDH4-02-007-CN-3750 | JDH4-02-007-CN-3750 | Encasement for Pipes [Road 01 ] | 13294.79 | 100% | 0% | 100% | 13294.79 | 0
Valves | Valves |  | 141183.19 | 100% | 0% | 100% | 141183.19 | 0
JDH4-02-007-CN-3820 | JDH4-02-007-CN-3820 | Installation of Gate Valves [Road 01 ] | 13140.65 | 100% | 0% | 100% | 13140.65 | 0
JDH4-02-007-CN-3870 | JDH4-02-007-CN-3870 | Installation of Butterfly valves [Road 01 ] | 37845.08 | 92.5% | 5.93% | 98.43% | 37250.9122 | 2244.2132
JDH4-02-007-CN-3880 | JDH4-02-007-CN-3880 | Installation of Washout valves [Road 01 ] | 29645.32 | 100% | 0% | 100% | 29645.32 | 0
JDH4-02-007-CN-3890 | JDH4-02-007-CN-3890 | Installation of Air valves [Road 01 ] | 60552.14 |  | 0%
Fire Hydrant | Fire Hydrant |  | 75690.17 |  | 0%
JDH4-02-007-CN-3910 | JDH4-02-007-CN-3910 | Installation of 3-outlet fire hydrant [Road 01 ] | 75690.17 | 100% | 0% | 100% | 75690.17 | 0
Valve Chambers | Valve Chambers |  | 829383.7 | 100% | 0% | 100% | 829383.7 | 0
JDH4-02-007-CN-3950 | JDH4-02-007-CN-3950 | Construction of Valve Chambers [Road 01 ] | 104035.15 | 100% | 0% | 100% | 104035.15 | 0
JDH4-02-007-CN-3960 | JDH4-02-007-CN-3960 | Construction of Wash out Chambers [Road 01 ] | 261848.65 | 100% | 0% | 100% | 261848.65 | 0
JDH4-02-007-CN-3970 | JDH4-02-007-CN-3970 | Construction of Air Valve Chambers [Road 01 ] | 274274.48 | 100% | 0% | 100% | 274274.48 | 0
JDH4-02-007-CN-4600 | JDH4-02-007-CN-4600 | Construction of Valve Chambers [Road 01 ] | 75690.17 | 100% | 0% | 100% | 75690.17 | 0
JDH4-02-007-CN-4610 | JDH4-02-007-CN-4610 | Construction of Wash Out Valve Chambers [Road 01 ] | 37845.08 |  | 0%
JDH4-02-007-CN-4630 | JDH4-02-007-CN-4630 | Construction of Air Valve Chambers [Road 01 ] | 75690.17 | 100% | 0% | 100% | 75690.17 | 0
Road Crossings | Road Crossings |  | 6307.51 | 100% | 0% | 100% | 6307.51 | 0
JDH4-02-007-CN-3980 | JDH4-02-007-CN-3980 | Installation of HDPE road croosing [Road 01 ] | 6307.51 | 100% | 0% | 100% | 6307.51 | 0
Electrical Works | Electrical Works |  | 625707.07 |  | 0%
MV & LV Cables | MV & LV Cables |  | 336867.08 |  | 0%
Medium Voltage Cable | Medium Voltage Cable |  | 264999.32 |  | 0%
JDH4-02-007-CN-2430 | JDH4-02-007-CN-2430 | Excavation for Trench [Road 01 ] | 13372.86 |  | 0%
JDH4-02-007-CN-2490 | JDH4-02-007-CN-2490 | Installation of Duct banks [Road 01 ] | 27290.51 | 100% | 0% | 100% | 27290.51 | 0
JDH4-02-007-CN-2550 | JDH4-02-007-CN-2550 | Installation of Medium Voltage Cables [Road 01 ] | 224335.95 | 100% | 0% | 100% | 224335.95 | 0
Low Voltage Cable | Low Voltage Cable |  | 71867.76 | 100% | 0% | 100% | 71867.76 | 0
JDH4-02-007-CN-2610 | JDH4-02-007-CN-2610 | Excavation for Low Voltage Cable [Road 01 ] | 19225.3 | 100% | 0% | 100% | 19225.3 | 0
JDH4-02-007-CN-2620 | JDH4-02-007-CN-2620 | Installation of Low Voltage Cables [Road 01 ] | 52642.45 |  | 0%
Street Lighting | Street Lighting |  | 20045.28 | 100% | 0% | 100% | 20045.28 | 0
JDH4-02-007-CN-2770 | JDH4-02-007-CN-2770 | Excavation for Low Voltage Cable [Road 01 ] | 3279.91 | 100% | 0% | 100% | 3279.91 | 0
JDH4-02-007-CN-2850 | JDH4-02-007-CN-2850 | Installation of Low Voltage Cables [Road 01 ] | 16765.37 | 100% | 0% | 100% | 16765.37 | 0
Telecommunication | Telecommunication |  | 268794.71 | 100% | 0% | 100% | 268794.71 | 0
JDH4-02-007-CN-3080 | JDH4-02-007-CN-3080 | Installation Road Crossing R/F 6 way 50mm HDPE Pipe [Road 01 ] | 206634.16 | 100% | 0% | 100% | 206634.16 | 0
JDH4-02-007-CN-3150 | JDH4-02-007-CN-3150 | Installation Road Crossing Un R/F 6 way 50mm HDPE Pipe [Road 01 ] | 5392.92 |  | 0%
JDH4-02-007-CN-3260 | JDH4-02-007-CN-3260 | Installation of Manholes [Road 01 ] | 56767.63 | 100% | 0% | 100% | 56767.63 | 0
Open Drain Channel | Open Drain Channel |  | 389804.75 | 100% | 0% | 100% | 389804.75 | 0
JDH4-02-007-CN-5850 | JDH4-02-007-CN-5850 | Channel excavation [Road 01 ] | 164626.5 | 100% | 0% | 100% | 164626.5 | 0
JDH4-02-007-CN-5860 | JDH4-02-007-CN-5860 | Backfill of the existing channel [Road 01 ] | 50460.11 |  | 0%
JDH4-02-007-CN-5870 | JDH4-02-007-CN-5870 | Compaction [Road 01 ] | 18922.54 | 100% | 0% | 100% | 18922.54 | 0
JDH4-02-007-CN-5880 | JDH4-02-007-CN-5880 | Finished grouted riprap for side ditches [Road 01 ] | 155795.6 | 100% | 0% | 100% | 155795.6 | 0
Road 02 | Road 02 |  | 658318.98 | 100% | 0% | 100% | 658318.98 | 0
Under Pass | Under Pass |  | 112526.05 | 100% | 0% | 100% | 112526.05 | 0
JDH4-02-007-CN-1940 | JDH4-02-007-CN-1940 | Compacted structural backfill for closing the underpass [Road 02 ] | 16651.84 |  | 0%
JDH4-02-007-CN-2410 | JDH4-02-007-CN-2410 | RC wall and the foundation at face of underpass [Road 02 ] | 95874.21 | 100% | 0% | 100% | 95874.21 | 0
Sewerage Network | Sewerage Network |  | 89801.58 |  | 0%
Pipe Works | Pipe Works |  | 57055.71 |  | 0%
JDH4-02-007-CN-4770 | JDH4-02-007-CN-4770 | Excavation & Compaction (FDT) [Road 02 ] | 5705.57 | 100% | 0% | 100% | 5705.57 | 0
JDH4-02-007-CN-4840 | JDH4-02-007-CN-4840 | Sand Bedding [Road 02 ] | 2852.78 | 100% | 0% | 100% | 2852.78 | 0
JDH4-02-007-CN-4910 | JDH4-02-007-CN-4910 | Installation of GRP Pipe [Road 02 ] | 28527.86 | 100% | 0% | 100% | 28527.86 | 0
JDH4-02-007-CN-4980 | JDH4-02-007-CN-4980 | Gravity Test [Road 02 ] | 11411.15 |  | 0%
JDH4-02-007-CN-5050 | JDH4-02-007-CN-5050 | Sand Cover & Warning Tape [Road 02 ] | 2852.78 | 100% | 0% | 100% | 2852.78 | 0
JDH4-02-007-CN-5120 | JDH4-02-007-CN-5120 | Backfilling & Compaction [Road 02 ] | 5705.57 |  | 0%
Pipe Encasement | Pipe Encasement |  | 304.22 | 100% | 0% | 100% | 304.22 | 0
JDH4-02-007-CN-5260 | JDH4-02-007-CN-5260 | Pipe Encasement Works [Road 02 ] | 304.22 | 100% | 0% | 100% | 304.22 | 0
Manholes | Manholes |  | 32441.65 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-5190 | JDH4-02-007-CN-5190 | Installation of Manholes [Road 02 ] | 32441.65 |  | 0%
TSE Network | TSE Network |  | 145684.48 |  | 0%
Pipe Works | Pipe Works |  | 113107.76 |  | 0%
JDH4-02-007-CN-3990 | JDH4-02-007-CN-3990 | Excavation and Compaction (FDT) [Road 02 ] | 10479.66 | 100% | 0% | 100% | 10479.66 | 0
JDH4-02-007-CN-4060 | JDH4-02-007-CN-4060 | Sand Bedding [Road 02 ] | 5239.85 | 100% | 0% | 100% | 5239.85 | 0
JDH4-02-007-CN-4130 | JDH4-02-007-CN-4130 | Installation of HDPE Pipe [Road 02 ] | 52398.34 | 100% | 0% | 100% | 52398.34 | 0
JDH4-02-007-CN-4200 | JDH4-02-007-CN-4200 | Initial Pressure Test [Road 02 ] | 20959.32 |  | 0%
JDH4-02-007-CN-4270 | JDH4-02-007-CN-4270 | Sand Cover & Warning [Road 02 ] | 5239.85 | 100% | 0% | 100% | 5239.85 | 0
JDH4-02-007-CN-4340 | JDH4-02-007-CN-4340 | Backfilling & Compaction [Road 02 ] | 10479.66 | 100% | 0% | 100% | 10479.66 | 0
JDH4-02-007-CN-4650 | JDH4-02-007-CN-4650 | Point of Connection [Road 02 ] | 8311.08 | 100% | 0% | 100% | 8311.08 | 0
Pipe Encasement | Pipe Encasement |  | 5288.43 |  | 0%
JDH4-02-007-CN-4410 | JDH4-02-007-CN-4410 | Encasement for Pipes [Road 02 ] | 5288.43 | 100% | 0% | 100% | 5288.43 | 0
Valves | Valves |  | 18457.78 | 100% | 0% | 100% | 18457.78 | 0
JDH4-02-007-CN-4480 | JDH4-02-007-CN-4480 | Installation of Gate Valves [Road 02 ] | 11204.14 |  | 0%
JDH4-02-007-CN-4570 | JDH4-02-007-CN-4570 | Installation of Air Valves [Road 02 ] | 7253.64 | 100% | 0% | 100% | 7253.64 | 0
Risers | Risers |  | 8830.52 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-4720 | JDH4-02-007-CN-4720 | Installation of Irrigation Riser with [Road 02 ] | 8830.52 |  | 0%
Potable Network | Potable Network |  | 139057.87 |  | 0%
Pipe Works | Pipe Works |  | 84122.84 | 100% | 0% | 100% | 84122.84 | 0
JDH4-02-007-CN-3310 | JDH4-02-007-CN-3310 | Excavation and Compaction (FDT) [Road 02 ] | 8412.29 | 100% | 0% | 100% | 8412.29 | 0
JDH4-02-007-CN-3380 | JDH4-02-007-CN-3380 | Sand Bedding [Road 02 ] | 4206.15 | 100% | 0% | 100% | 4206.15 | 0
JDH4-02-007-CN-3450 | JDH4-02-007-CN-3450 | Installation of HDPE Pipe [Road 02 ] | 42061.41 | 100% | 0% | 100% | 42061.41 | 0
JDH4-02-007-CN-3520 | JDH4-02-007-CN-3520 | Initial Pressure Test [Road 02 ] | 16824.56 | 100% | 0% | 100% | 16824.56 | 0
JDH4-02-007-CN-3590 | JDH4-02-007-CN-3590 | Sand Cover & Warning Tape [Road 02 ] | 4206.15 | 100% | 0% | 100% | 4206.15 | 0
JDH4-02-007-CN-3660 | JDH4-02-007-CN-3660 | Backfilling [Road 02 ] | 8412.29 |  | 0%
Pipe Encasement | Pipe Encasement |  | 6577.42 | 100% | 0% | 100% | 6577.42 | 0
JDH4-02-007-CN-3730 | JDH4-02-007-CN-3730 | Encasement for Pipes [Road 02 ] | 6577.42 | 100% | 0% | 100% | 6577.42 | 0
Valves | Valves |  | 10512.52 | 100% | 0% | 100% | 10512.52 | 0
JDH4-02-007-CN-3800 | JDH4-02-007-CN-3800 | Installation of Gate Valves [Road 02 ] | 10512.52 | 100% | 0% | 100% | 10512.52 | 0
Valve Chambers | Valve Chambers |  | 37845.08 | 100% | 0% | 100% | 37845.08 | 0
JDH4-02-007-CN-4620 | JDH4-02-007-CN-4620 | Construction of Air Valve Chambers [Road 02 ] | 37845.08 | 100% | 0% | 100% | 37845.08 | 0
Electrical Works | Electrical Works |  | 171249.01 |  | 0%
Telecommunication | Telecommunication |  | 171249.01 | 100% | 0% | 100% | 171249.01 | 0
JDH4-02-007-CN-3060 | JDH4-02-007-CN-3060 | Installation Road Crossing R/F 6 way 50mm HDPE Pipe [Road 02 ] | 133214.7 | 100% | 0% | 100% | 133214.7 | 0
JDH4-02-007-CN-3130 | JDH4-02-007-CN-3130 | Installation Road Crossing Un R/F 6 way 50mm HDPE Pipe [Road 02 ] | 3973.73 | 100% | 0% | 100% | 3973.73 | 0
JDH4-02-007-CN-3240 | JDH4-02-007-CN-3240 | Installation of Manholes [Road 02 ] | 34060.58 | 100% | 0% | 100% | 34060.58 | 0
Road 07-N | Road 07-N |  | 5641570.83 | 100% | 0% | 100% | 5641570.83 | 0
Road Works | Road Works |  | 3118321.42 | 100% | 0% | 100% | 3118321.42 | 0
Eartworks & Site grading | Eartworks & Site grading |  | 1345969.85 |  | 0%
JDH4-02-007-CN-1790 | JDH4-02-007-CN-1790 | Road backfilling [Road 07-N ] | 1195447.36 | 100% | 0% | 100% | 1195447.36 | 0
JDH4-02-007-CN-1730 | JDH4-02-007-CN-1730 | Road excavation [Road 07-N ] | 30288.73 | 100% | 0% | 100% | 30288.73 | 0
JDH4-02-007-CN-1910 | JDH4-02-007-CN-1910 | Subgrade [Road 07-N ] | 120233.76 | 100% | 0% | 100% | 120233.76 | 0
Asphalt Works | Asphalt Works |  | 805652.46 | 100% | 0% | 100% | 805652.46 | 0
JDH4-02-007-CN-1970 | JDH4-02-007-CN-1970 | Aggregate base course [Road 07-N ] | 122460.38 | 100% | 0% | 100% | 122460.38 | 0
JDH4-02-007-CN-2020 | JDH4-02-007-CN-2020 | Prime Coat (MC1) [Road 07-N ] | 68436.53 | 100% | 0% | 100% | 68436.53 | 0
JDH4-02-007-CN-2070 | JDH4-02-007-CN-2070 | Bituminous base course [Road 07-N ] | 614755.54 |  | 0%
Finishing Works | Finishing Works |  | 966699.12 | 100% | 0% | 100% | 966699.12 | 0
Asphalt Wearing Course | Asphalt Wearing Course |  | 362429.75 | 100% | 0% | 100% | 362429.75 | 0
JDH4-02-007-CN-2120 | JDH4-02-007-CN-2120 | Tack Coat (RC2) [Road 07-N ] | 36078.98 | 100% | 0% | 100% | 36078.98 | 0
JDH4-02-007-CN-2170 | JDH4-02-007-CN-2170 | Bituminous concrete wearing course [Road 07-N ] | 326350.77 | 100% | 0% | 100% | 326350.77 | 0
Precast Concrete Curb | Precast Concrete Curb |  | 225534.37 | 100% | 0% | 100% | 225534.37 | 0
JDH4-02-007-CN-2220 | JDH4-02-007-CN-2220 | Installation of Precast Concrete curb [Road 07-N ] | 225534.37 | 100% | 0% | 100% | 225534.37 | 0
Precast Interlocking block pavers | Precast Interlocking block pavers |  | 214487.01 |  | 0%
JDH4-02-007-CN-2270 | JDH4-02-007-CN-2270 | Installation of Interlocking block pavers for sidewalk/footpath [Road 07-N ] | 214487.01 | 100% | 0% | 100% | 214487.01 | 0
Pavement Markings | Pavement Markings |  | 60663.71 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-2320 | JDH4-02-007-CN-2320 | Pavement markings [Road 07-N ] | 60663.71 | 100% | 0% | 100% | 60663.71 | 0
Traffic Signage | Traffic Signage |  | 103584.27 | 100% | 0% | 100% | 103584.27 | 0
JDH4-02-007-CN-2370 | JDH4-02-007-CN-2370 | Installation of Traffic Signs [Road 07-N ] | 103584.27 | 100% | 0% | 100% | 103584.27 | 0
Storm Water Drainage | Storm Water Drainage |  | 936796.62 | 100% | 0% | 100% | 936796.62 | 0
Pipe Works | Pipe Works |  | 649331.83 |  | 0%
JDH4-02-007-CN-5350 | JDH4-02-007-CN-5350 | Excavation and Compaction (FDT) [Road 07-N ] | 64933.15 | 100% | 0% | 100% | 64933.15 | 0
JDH4-02-007-CN-5400 | JDH4-02-007-CN-5400 | Sand Bedding [Road 07-N ] | 32466.61 | 100% | 0% | 100% | 32466.61 | 0
JDH4-02-007-CN-5450 | JDH4-02-007-CN-5450 | Installation of GRP Pipe [Road 07-N ] | 454532.29 |  | 0%
JDH4-02-007-CN-5500 | JDH4-02-007-CN-5500 | Sand Cover & Warning Tape [Road 07-N ] | 32466.61 | 100% | 0% | 100% | 32466.61 | 0
JDH4-02-007-CN-5550 | JDH4-02-007-CN-5550 | Backfilling & Compaction [Road 07-N ] | 64933.15 |  | 0%
Pipe Encasement | Pipe Encasement |  | 24850.59 | 100% | 0% | 100% | 24850.59 | 0
JDH4-02-007-CN-5820 | JDH4-02-007-CN-5820 | Pipe Encasement Works [Road 07-N ] | 24850.59 | 100% | 0% | 100% | 24850.59 | 0
Manholes | Manholes |  | 130787.16 |  | 0%
JDH4-02-007-CN-5650 | JDH4-02-007-CN-5650 | Installation of Precast Manhole Ring [Road 07-N ] | 130787.16 |  | 0%
Precast Acces Openinig | Precast Acces Openinig |  | 7569.02 | 100% | 0% | 100% | 7569.02 | 0
JDH4-02-007-CN-5700 | JDH4-02-007-CN-5700 | Installation of Precast Access Opening [Road 07-N ] | 7569.02 | 100% | 0% | 100% | 7569.02 | 0
Catch Basins | Catch Basins |  | 73797.91 | 100% | 0% | 100% | 73797.91 | 0
JDH4-02-007-CN-5740 | JDH4-02-007-CN-5740 | Construction of Catch basins [Road 07-N ] | 73797.91 | 100% | 0% | 100% | 73797.91 | 0
Concrete Outfalls | Concrete Outfalls |  | 50460.11 | 100% | 0% | 100% | 50460.11 | 0
JDH4-02-007-CN-5770 | JDH4-02-007-CN-5770 | Construction of Concrete outfall structure [Road 07-N ] | 50460.11 | 100% | 0% | 100% | 50460.11 | 0
Sewerage Network | Sewerage Network |  | 489984.34 |  | 0%
Pipe Works | Pipe Works |  | 326102.91 | 100% | 0% | 100% | 326102.91 | 0
JDH4-02-007-CN-4800 | JDH4-02-007-CN-4800 | Excavation & Compaction (FDT) [Road 07-N ] | 32610.3 | 100% | 0% | 100% | 32610.3 | 0
JDH4-02-007-CN-4870 | JDH4-02-007-CN-4870 | Sand Bedding [Road 07-N ] | 16305.13 | 100% | 0% | 100% | 16305.13 | 0
JDH4-02-007-CN-4940 | JDH4-02-007-CN-4940 | Installation of GRP Pipe [Road 07-N ] | 163051.46 | 100% | 0% | 100% | 163051.46 | 0
JDH4-02-007-CN-5010 | JDH4-02-007-CN-5010 | Gravity Test [Road 07-N ] | 65220.6 | 100% | 0% | 100% | 65220.6 | 0
JDH4-02-007-CN-5080 | JDH4-02-007-CN-5080 | Sand Cover & Warning Tape [Road 07-N ] | 16305.13 | 100% | 0% | 100% | 16305.13 | 0
JDH4-02-007-CN-5150 | JDH4-02-007-CN-5150 | Backfilling & Compaction [Road 07-N ] | 32610.3 |  | 0%
Pipe Encasement | Pipe Encasement |  | 1673.19 | 100% | 0% | 100% | 1673.19 | 0
JDH4-02-007-CN-5290 | JDH4-02-007-CN-5290 | Pipe Encasement Works [Road 07-N ] | 1673.19 | 100% | 0% | 100% | 1673.19 | 0
Manholes | Manholes |  | 162208.24 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-5220 | JDH4-02-007-CN-5220 | Installation of Manholes [Road 07-N ] | 162208.24 | 100% | 0% | 100% | 162208.24 | 0
TSE Network | TSE Network |  | 244612.82 | 0% | 0% | 0% | 0 | 0
Pipe Works | Pipe Works |  | 214076.25 | 100% | 0% | 100% | 214076.25 | 0
JDH4-02-007-CN-4020 | JDH4-02-007-CN-4020 | Excavation and Compaction (FDT) [Road 07-N ] | 20576.51 |  | 0%
JDH4-02-007-CN-4090 | JDH4-02-007-CN-4090 | Sand Bedding [Road 07-N ] | 10288.28 | 100% | 0% | 100% | 10288.28 | 0
JDH4-02-007-CN-4160 | JDH4-02-007-CN-4160 | Installation of HDPE Pipe [Road 07-N ] | 102882.58 | 100% | 0% | 100% | 102882.58 | 0
JDH4-02-007-CN-4230 | JDH4-02-007-CN-4230 | Initial Pressure Test [Road 07-N ] | 41153.01 | 100% | 0% | 100% | 41153.01 | 0
JDH4-02-007-CN-4300 | JDH4-02-007-CN-4300 | Sand Cover & Warning [Road 07-N ] | 10288.28 | 100% | 0% | 100% | 10288.28 | 0
JDH4-02-007-CN-4370 | JDH4-02-007-CN-4370 | Backfilling & Compaction [Road 07-N ] | 20576.51 | 100% | 0% | 100% | 20576.51 | 0
JDH4-02-007-CN-4680 | JDH4-02-007-CN-4680 | Point of Connection [Road 07-N ] | 8311.08 | 100% | 0% | 100% | 8311.08 | 0
Pipe Encasement | Pipe Encasement |  | 9821.37 |  | 0%
JDH4-02-007-CN-4440 | JDH4-02-007-CN-4440 | Encasement for Pipes [Road 07-N ] | 9821.37 | 100% | 0% | 100% | 9821.37 | 0
Valves | Valves |  | 7469.42 | 100% | 0% | 100% | 7469.42 | 0
JDH4-02-007-CN-4510 | JDH4-02-007-CN-4510 | Installation of Gate Valves [Road 07-N ] | 7469.42 | 100% | 0% | 100% | 7469.42 | 0
Risers | Risers |  | 13245.78 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-4750 | JDH4-02-007-CN-4750 | Installation of Irrigation Riser with [Road 07-N ] | 13245.78 | 100% | 0% | 100% | 13245.78 | 0
Potable Network | Potable Network |  | 167864.19 | 100% | 0% | 100% | 167864.19 | 0
Pipe Works | Pipe Works |  | 98143.32 |  | 0%
JDH4-02-007-CN-3340 | JDH4-02-007-CN-3340 | Excavation and Compaction (FDT) [Road 07-N ] | 9814.34 | 100% | 0% | 100% | 9814.34 | 0
JDH4-02-007-CN-3410 | JDH4-02-007-CN-3410 | Sand Bedding [Road 07-N ] | 4907.17 | 100% | 0% | 100% | 4907.17 | 0
JDH4-02-007-CN-3480 | JDH4-02-007-CN-3480 | Installation of HDPE Pipe [Road 07-N ] | 49071.64 | 100% | 0% | 100% | 49071.64 | 0
JDH4-02-007-CN-3550 | JDH4-02-007-CN-3550 | Initial Pressure Test [Road 07-N ] | 19628.65 | 100% | 0% | 100% | 19628.65 | 0
JDH4-02-007-CN-3620 | JDH4-02-007-CN-3620 | Sand Cover & Warning Tape [Road 07-N ] | 4907.17 | 100% | 0% | 100% | 4907.17 | 0
JDH4-02-007-CN-3690 | JDH4-02-007-CN-3690 | Backfilling [Road 07-N ] | 9814.34 | 100% | 0% | 100% | 9814.34 | 0
Pipe Encasement | Pipe Encasement |  | 7696.98 |  | 0%
JDH4-02-007-CN-3760 | JDH4-02-007-CN-3760 | Encasement for Pipes [Road 07-N ] | 7696.98 | 100% | 0% | 100% | 7696.98 | 0
Valves | Valves |  | 5256.26 | 100% | 0% | 100% | 5256.26 | 0
JDH4-02-007-CN-3830 | JDH4-02-007-CN-3830 | Installation of Gate Valves [Road 07-N ] | 5256.26 | 100% | 0% | 100% | 5256.26 | 0
Fire Hydrant | Fire Hydrant |  | 56767.63 |  | 0%
JDH4-02-007-CN-3920 | JDH4-02-007-CN-3920 | Installation of 3-outlet fire hydrant [Road 07-N ] | 56767.63 | 100% | 0% | 100% | 56767.63 | 0
Electrical Works | Electrical Works |  | 683991.44 | 100% | 0% | 100% | 683991.44 | 0
MV & LV Cables | MV & LV Cables |  | 165204.7 | 0% | 100% | 100% | 165204.7 | 165204.7
Medium Voltage Cable | Medium Voltage Cable |  | 130128.34 |  | 0%
JDH4-02-007-CN-2440 | JDH4-02-007-CN-2440 | Excavation for Trench [Road 07-N ] | 6530.33 |  | 0%
JDH4-02-007-CN-2500 | JDH4-02-007-CN-2500 | Installation of Duct banks [Road 07-N ] | 13876.53 | 100% | 0% | 100% | 13876.53 | 0
JDH4-02-007-CN-2560 | JDH4-02-007-CN-2560 | Installation of Medium Voltage Cables [Road 07-N ] | 109721.48 | 100% | 0% | 100% | 109721.48 | 0
Low Voltage Cable | Low Voltage Cable |  | 35076.36 | 100% | 0% | 100% | 35076.36 | 0
JDH4-02-007-CN-2630 | JDH4-02-007-CN-2630 | Excavation for Low Voltage Cable [Road 07-N ] | 9385.58 | 100% | 0% | 100% | 9385.58 | 0
JDH4-02-007-CN-2640 | JDH4-02-007-CN-2640 | Installation of Low Voltage Cables [Road 07-N ] | 25690.78 | 100% | 0% | 100% | 25690.78 | 0
Street Lighting | Street Lighting |  | 267583.69 | 100% | 0% | 100% | 267583.69 | 0
JDH4-02-007-CN-2780 | JDH4-02-007-CN-2780 | Excavation for Low Voltage Cable [Road 07-N ] | 17282.59 | 100% | 0% | 100% | 17282.59 | 0
JDH4-02-007-CN-2790 | JDH4-02-007-CN-2790 | Installation of Road Crossing Ducts [Road 07-N ] | 17204.29 | 100% | 0% | 100% | 17204.29 | 0
JDH4-02-007-CN-2860 | JDH4-02-007-CN-2860 | Installation of Low Voltage Cables [Road 07-N ] | 88141.2 | 100% | 0% | 100% | 88141.2 | 0
JDH4-02-007-CN-2900 | JDH4-02-007-CN-2900 | Installation of Lighting Poles [Road 07-N ] | 96197.32 | 100% | 0% | 100% | 96197.32 | 0
JDH4-02-007-CN-2940 | JDH4-02-007-CN-2940 | Installation of Lighting Luminaires [Road 07-N ] | 22897.48 | 100% | 0% | 100% | 22897.48 | 0
JDH4-02-007-CN-3000 | JDH4-02-007-CN-3000 | Installation of Street Lighting Feeder pillars [Road 07-N ] | 22076.3 | 100% | 0% | 100% | 22076.3 | 0
JDH4-02-007-CN-3010 | JDH4-02-007-CN-3010 | Installation of Earthing System [Road 07-N ] | 3784.51 | 100% | 0% | 100% | 3784.51 | 0
Telecommunication | Telecommunication |  | 251203.05 | 100% | 0% | 100% | 251203.05 | 0
JDH4-02-007-CN-3090 | JDH4-02-007-CN-3090 | Installation Road Crossing R/F 6 way 50mm HDPE Pipe [Road 07-N ] | 145325.12 | 100% | 0% | 100% | 145325.12 | 0
JDH4-02-007-CN-3160 | JDH4-02-007-CN-3160 | Installation Road Crossing Un R/F 6 way 50mm HDPE Pipe [Road 07-N ] | 3973.73 | 100% | 0% | 100% | 3973.73 | 0
JDH4-02-007-CN-3210 | JDH4-02-007-CN-3210 | Installation of 2 x 32 mm diameter HDPE ducts [Road 07-N ] | 62166.86 | 100% | 0% | 100% | 62166.86 | 0
JDH4-02-007-CN-3270 | JDH4-02-007-CN-3270 | Installation of Manholes [Road 07-N ] | 39737.34 | 100% | 0% | 100% | 39737.34 | 0
Road 06 | Road 06 |  | 4574877.17 | #N/A | #N/A | #N/A | #N/A | #N/A
Road Works | Road Works |  | 2010437.54 | 100% | 0% | 100% | 2010437.54 | 0
Eartworks & Site grading | Eartworks & Site grading |  | 852975.19 | 100% | 0% | 100% | 852975.19 | 0
JDH4-02-007-CN-1740 | JDH4-02-007-CN-1740 | Road excavation [Road 06 ] | 19197.58 | 0% | 100% | 100% | 19197.58 | 19197.58
JDH4-02-007-CN-1800 | JDH4-02-007-CN-1800 | Road backfilling [Road 06 ] | 757595.51 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-1920 | JDH4-02-007-CN-1920 | Subgrade [Road 06 ] | 76182.11 | #N/A | #N/A | #N/A | #N/A | #N/A
Asphalt Works | Asphalt Works |  | 511296.55 | 100% | 0% | 100% | 511296.55 | 0
JDH4-02-007-CN-1980 | JDH4-02-007-CN-1980 | Aggregate base course [Road 06 ] | 77604.5 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-2030 | JDH4-02-007-CN-2030 | Prime Coat (MC1) [Road 06 ] | 43408.31 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-2080 | JDH4-02-007-CN-2080 | Bituminous base course [Road 06 ] | 390283.74 | #N/A | #N/A | #N/A | #N/A | #N/A
Finishing Works | Finishing Works |  | 646165.8 | 100% | 0% | 100% | 646165.8 | 0
Asphalt Wearing Course | Asphalt Wearing Course |  | 229183.52 | 100% | 0% | 100% | 229183.52 | 0
JDH4-02-007-CN-2130 | JDH4-02-007-CN-2130 | Tack Coat (RC2) [Road 06 ] | 22959.35 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-2180 | JDH4-02-007-CN-2180 | Bituminous concrete wearing course [Road 06 ] | 206224.17 | #N/A | #N/A | #N/A | #N/A | #N/A
Precast Concrete Curb | Precast Concrete Curb |  | 142928.15 | 100% | 0% | 100% | 142928.15 | 0
JDH4-02-007-CN-2230 | JDH4-02-007-CN-2230 | Installation of Precast Concrete curb [Road 06 ] | 142928.15 | #N/A | #N/A | #N/A | #N/A | #N/A
Precast Interlocking block pavers | Precast Interlocking block pavers |  | 135911.16 | 100% | 0% | 100% | 135911.16 | 0
JDH4-02-007-CN-2280 | JDH4-02-007-CN-2280 | Installation of Interlocking block pavers for sidewalk/footpath [Road 06 ] | 135911.16 | 100% | 0% | 100% | 135911.16 | 0
Pavement Markings | Pavement Markings |  | 73402.8 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-2330 | JDH4-02-007-CN-2330 | Pavement markings [Road 06 ] | 73402.8 | #N/A | #N/A | #N/A | #N/A | #N/A
Traffic Signage | Traffic Signage |  | 64740.17 | 100% | 0% | 100% | 64740.17 | 0
JDH4-02-007-CN-2380 | JDH4-02-007-CN-2380 | Installation of Traffic Signs [Road 06 ] | 64740.17 | #N/A | #N/A | #N/A | #N/A | #N/A
Storm Water Drainage | Storm Water Drainage |  | 778965.12 | 100% | 0% | 100% | 778965.12 | 0
Pipe Works | Pipe Works |  | 559749.14 | 100% | 0% | 100% | 559749.14 | 0
JDH4-02-007-CN-5360 | JDH4-02-007-CN-5360 | Excavation and Compaction (FDT) [Road 06 ] | 55974.89 | 100% | 0% | 100% | 55974.89 | 0
JDH4-02-007-CN-5410 | JDH4-02-007-CN-5410 | Sand Bedding [Road 06 ] | 27987.48 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-5460 | JDH4-02-007-CN-5460 | Installation of GRP Pipe [Road 06 ] | 391824.41 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-5510 | JDH4-02-007-CN-5510 | Sand Cover & Warning Tape [Road 06 ] | 27987.48 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-5560 | JDH4-02-007-CN-5560 | Backfilling & Compaction [Road 06 ] | 55974.89 | #N/A | #N/A | #N/A | #N/A | #N/A
Pipe Encasement | Pipe Encasement |  | 21253.8 | 100% | 0% | 100% | 21253.8 | 0
JDH4-02-007-CN-5830 | JDH4-02-007-CN-5830 | Pipe Encasement Works [Road 06 ] | 21253.8 | #N/A | #N/A | #N/A | #N/A | #N/A
Manholes | Manholes |  | 130787.16 | 100% | 0% | 100% | 130787.16 | 0
JDH4-02-007-CN-5660 | JDH4-02-007-CN-5660 | Installation of Precast Manhole Ring [Road 06 ] | 130787.16 | #N/A | #N/A | #N/A | #N/A | #N/A
Precast Acces Openinig | Precast Acces Openinig |  | 5676.76 | 100% | 0% | 100% | 5676.76 | 0
JDH4-02-007-CN-5710 | JDH4-02-007-CN-5710 | Installation of Precast Access Opening [Road 06 ] | 5676.76 | #N/A | #N/A | #N/A | #N/A | #N/A
Catch Basins | Catch Basins |  | 61498.26 | 100% | 0% | 100% | 61498.26 | 0
JDH4-02-007-CN-5750 | JDH4-02-007-CN-5750 | Construction of Catch basins [Road 06 ] | 61498.26 | #N/A | #N/A | #N/A | #N/A | #N/A
Sewerage Network | Sewerage Network |  | 650267.31 | 100% | 0% | 100% | 650267.31 | 0
Pipe Works | Pipe Works |  | 389060.94 | 100% | 0% | 100% | 389060.94 | 0
JDH4-02-007-CN-4810 | JDH4-02-007-CN-4810 | Excavation & Compaction (FDT) [Road 06 ] | 38906.1 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-4880 | JDH4-02-007-CN-4880 | Sand Bedding [Road 06 ] | 19453.03 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-4950 | JDH4-02-007-CN-4950 | Installation of GRP Pipe [Road 06 ] | 194530.47 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-5020 | JDH4-02-007-CN-5020 | Gravity Test [Road 06 ] | 77812.21 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-5090 | JDH4-02-007-CN-5090 | Sand Cover & Warning Tape [Road 06 ] | 19453.03 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-5160 | JDH4-02-007-CN-5160 | Backfilling & Compaction [Road 06 ] | 38906.1 | #N/A | #N/A | #N/A | #N/A | #N/A
Pipe Encasement | Pipe Encasement |  | 1673.19 | 100% | 0% | 100% | 1673.19 | 0
JDH4-02-007-CN-5300 | JDH4-02-007-CN-5300 | Pipe Encasement Works [Road 06 ] | 1673.19 | #N/A | #N/A | #N/A | #N/A | #N/A
Manholes | Manholes |  | 259533.18 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-5230 | JDH4-02-007-CN-5230 | Installation of Manholes [Road 06 ] | 259533.18 | #N/A | #N/A | #N/A | #N/A | #N/A
TSE Network | TSE Network |  | 246262.42 | 0% | 0% | 0% | 0 | 0
Pipe Works | Pipe Works |  | 215272.56 | 100% | 0% | 100% | 215272.56 | 0
JDH4-02-007-CN-4030 | JDH4-02-007-CN-4030 | Excavation and Compaction (FDT) [Road 06 ] | 20696.14 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-4100 | JDH4-02-007-CN-4100 | Sand Bedding [Road 06 ] | 10348.1 | 100% | 0% | 100% | 10348.1 | 0
JDH4-02-007-CN-4170 | JDH4-02-007-CN-4170 | Installation of HDPE Pipe [Road 06 ] | 103480.74 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-4240 | JDH4-02-007-CN-4240 | Initial Pressure Test [Road 06 ] | 41392.27 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-4690 | JDH4-02-007-CN-4690 | Point of Connection [Road 06 ] | 8311.08 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-4310 | JDH4-02-007-CN-4310 | Sand Cover & Warning [Road 06 ] | 10348.1 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-4380 | JDH4-02-007-CN-4380 | Backfilling & Compaction [Road 06 ] | 20696.14 | #N/A | #N/A | #N/A | #N/A | #N/A
Pipe Encasement | Pipe Encasement |  | 10274.66 | 100% | 0% | 100% | 10274.66 | 0
JDH4-02-007-CN-4450 | JDH4-02-007-CN-4450 | Encasement for Pipes [Road 06 ] | 10274.66 | 15% | 0% | 15% | 1541.199 | 0
Valves | Valves |  | 7469.42 | 100% | 0% | 100% | 7469.42 | 0
JDH4-02-007-CN-4520 | JDH4-02-007-CN-4520 | Installation of Gate Valves [Road 06 ] | 7469.42 | #N/A | #N/A | #N/A | #N/A | #N/A
Risers | Risers |  | 13245.78 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-4760 | JDH4-02-007-CN-4760 | Installation of Irrigation Riser with [Road 06 ] | 13245.78 | #N/A | #N/A | #N/A | #N/A | #N/A
Potable Network | Potable Network |  | 195291.25 | 100% | 0% | 100% | 195291.25 | 0
Pipe Works | Pipe Works |  | 118634.78 | 100% | 0% | 100% | 118634.78 | 0
JDH4-02-007-CN-3350 | JDH4-02-007-CN-3350 | Excavation and Compaction (FDT) [Road 06 ] | 11863.49 | 0% | 50% | 50% | 5931.745 | 5931.745
JDH4-02-007-CN-3420 | JDH4-02-007-CN-3420 | Sand Bedding [Road 06 ] | 5931.74 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-3490 | JDH4-02-007-CN-3490 | Installation of HDPE Pipe [Road 06 ] | 59317.37 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-3560 | JDH4-02-007-CN-3560 | Initial Pressure Test [Road 06 ] | 23726.94 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-3630 | JDH4-02-007-CN-3630 | Sand Cover & Warning Tape [Road 06 ] | 5931.74 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-3700 | JDH4-02-007-CN-3700 | Backfilling [Road 06 ] | 11863.49 | #N/A | #N/A | #N/A | #N/A | #N/A
Pipe Encasement | Pipe Encasement |  | 9376.32 | 100% | 0% | 100% | 9376.32 | 0
JDH4-02-007-CN-3770 | JDH4-02-007-CN-3770 | Encasement for Pipes [Road 06 ] | 9376.32 | 0% | 50% | 50% | 4688.16 | 4688.16
Valves | Valves |  | 10512.52 | 100% | 0% | 100% | 10512.52 | 0
JDH4-02-007-CN-3840 | JDH4-02-007-CN-3840 | Installation of Gate Valves [Road 06 ] | 10512.52 | #N/A | #N/A | #N/A | #N/A | #N/A
Fire Hydrant | Fire Hydrant |  | 56767.63 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-3930 | JDH4-02-007-CN-3930 | Installation of 3-outlet fire hydrant [Road 06 ] | 56767.63 | #N/A | #N/A | #N/A | #N/A | #N/A
Electrical Works | Electrical Works |  | 693653.53 | 100% | 0% | 100% | 693653.53 | 0
MV & LV Cables | MV & LV Cables |  | 161966.84 | 0% | 100% | 100% | 161966.84 | 161966.84
Medium Voltage Cable | Medium Voltage Cable |  | 126890.48 | 100% | 0% | 100% | 126890.48 | 0
JDH4-02-007-CN-2450 | JDH4-02-007-CN-2450 | Excavation for Trench [Road 06 ] | 6530.33 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-2510 | JDH4-02-007-CN-2510 | Installation of Duct banks [Road 06 ] | 10638.67 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-2570 | JDH4-02-007-CN-2570 | Installation of Medium Voltage Cables [Road 06 ] | 109721.48 | #N/A | #N/A | #N/A | #N/A | #N/A
Low Voltage Cable | Low Voltage Cable |  | 35076.36 | 100% | 0% | 100% | 35076.36 | 0
JDH4-02-007-CN-2650 | JDH4-02-007-CN-2650 | Excavation for Low Voltage Cable [Road 06 ] | 9385.58 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-2660 | JDH4-02-007-CN-2660 | Installation of Low Voltage Cables [Road 06 ] | 25690.78 | #N/A | #N/A | #N/A | #N/A | #N/A
Street Lighting | Street Lighting |  | 170726.59 | 0% | 50% | 50% | 85363.295 | 85363.295
JDH4-02-007-CN-2800 | JDH4-02-007-CN-2800 | Excavation for Low Voltage Cable [Road 06 ] | 9057.59 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-2810 | JDH4-02-007-CN-2810 | Installation of Road Crossing Ducts [Road 06 ] | 18433.17 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-2870 | JDH4-02-007-CN-2870 | Installation of Low Voltage Cables [Road 06 ] | 46246.69 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-2910 | JDH4-02-007-CN-2910 | Installation of Lighting Poles [Road 06 ] | 75284.86 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-2950 | JDH4-02-007-CN-2950 | Installation of Lighting Luminaires [Road 06 ] | 17919.77 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-2980 | JDH4-02-007-CN-2980 | Installation of Earthing System [Road 06 ] | 3784.51 | #N/A | #N/A | #N/A | #N/A | #N/A
Telecommunication | Telecommunication |  | 360960.1 | 100% | 0% | 100% | 360960.1 | 0
JDH4-02-007-CN-3100 | JDH4-02-007-CN-3100 | Installation Road Crossing R/F 6 way 50mm HDPE Pipe [Road 06 ] | 242586.99 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-3170 | JDH4-02-007-CN-3170 | Installation Road Crossing Un R/F 6 way 50mm HDPE Pipe [Road 06 ] | 4257.57 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-3220 | JDH4-02-007-CN-3220 | Installation of 2 x 32 mm diameter HDPE ducts [Road 06 ] | 68701.44 | #N/A | #N/A | #N/A | #N/A | #N/A
JDH4-02-007-CN-3280 | JDH4-02-007-CN-3280 | Installation of Manholes [Road 06 ] | 45414.1 | #N/A | #N/A | #N/A | #N/A | #N/A
Road 10 | Road 10 |  | 1039115.97 | 95.97% | 4.03% | 100% | 1039115.97 | 41876.3736
Sewerage Network | Sewerage Network |  | 419517.39 | 100% | 0% | 100% | 419517.39 | 0
Pipe Works | Pipe Works |  | 288229.72 | 28% | 2% | 30% | 86468.916 | 5764.5944
JDH4-02-007-CN-4830 | JDH4-02-007-CN-4830 | Excavation & Compaction (FDT) [Road 10 ] | 28822.98 | 100% | 0% | 100% | 28822.98 | 0
JDH4-02-007-CN-4900 | JDH4-02-007-CN-4900 | Sand Bedding [Road 10 ] | 14411.47 | 100% | 0% | 100% | 14411.47 | 0
JDH4-02-007-CN-4970 | JDH4-02-007-CN-4970 | Installation of GRP Pipe [Road 10 ] | 144114.86 | 100% | 0% | 100% | 144114.86 | 0
JDH4-02-007-CN-5040 | JDH4-02-007-CN-5040 | Gravity Test [Road 10 ] | 57645.96 | 100% | 0% | 100% | 57645.96 | 0
JDH4-02-007-CN-5110 | JDH4-02-007-CN-5110 | Sand Cover & Warning Tape [Road 10 ] | 14411.47 | 100% | 0% | 100% | 14411.47 | 0
JDH4-02-007-CN-5180 | JDH4-02-007-CN-5180 | Backfilling & Compaction [Road 10 ] | 28822.98 | 100% | 0% | 100% | 28822.98 | 0
Pipe Encasement | Pipe Encasement |  | 1521.08 | 100% | 0% | 100% | 1521.08 | 0
JDH4-02-007-CN-5320 | JDH4-02-007-CN-5320 | Pipe Encasement Works [Road 10 ] | 1521.08 | 100% | 0% | 100% | 1521.08 | 0
Manholes | Manholes |  | 129766.59 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-5250 | JDH4-02-007-CN-5250 | Installation of Manholes [Road 10 ] | 129766.59 | 100% | 0% | 100% | 129766.59 | 0
TSE Network | TSE Network |  | 221839.88 | 0% | 0% | 0% | 0 | 0
Pipe Works | Pipe Works |  | 201483.46 | 100% | 0% | 100% | 201483.46 | 0
JDH4-02-007-CN-4050 | JDH4-02-007-CN-4050 | Excavation and Compaction (FDT) [Road 10 ] | 18901.67 | 100% | 0% | 100% | 18901.67 | 0
JDH4-02-007-CN-4120 | JDH4-02-007-CN-4120 | Sand Bedding [Road 10 ] | 9450.86 | 100% | 0% | 100% | 9450.86 | 0
JDH4-02-007-CN-4190 | JDH4-02-007-CN-4190 | Installation of HDPE Pipe [Road 10 ] | 94508.42 | 100% | 0% | 100% | 94508.42 | 0
JDH4-02-007-CN-4260 | JDH4-02-007-CN-4260 | Initial Pressure Test [Road 10 ] | 37803.35 | 100% | 0% | 100% | 37803.35 | 0
JDH4-02-007-CN-4710 | JDH4-02-007-CN-4710 | Point of Connection [Road 10 ] | 12466.62 | 100% | 0% | 100% | 12466.62 | 0
JDH4-02-007-CN-4330 | JDH4-02-007-CN-4330 | Sand Cover & Warning [Road 10 ] | 9450.86 | 100% | 0% | 100% | 9450.86 | 0
JDH4-02-007-CN-4400 | JDH4-02-007-CN-4400 | Backfilling & Compaction [Road 10 ] | 18901.67 | 100% | 0% | 100% | 18901.67 | 0
Pipe Encasement | Pipe Encasement |  | 9368.07 | 100% | 0% | 100% | 9368.07 | 0
JDH4-02-007-CN-4470 | JDH4-02-007-CN-4470 | Encasement for Pipes [Road 10 ] | 9368.07 |  | 0%
Valves | Valves |  | 10988.35 | 90% | 10% | 100% | 10988.35 | 1098.835
JDH4-02-007-CN-4540 | JDH4-02-007-CN-4540 | Installation of Gate Valves [Road 10 ] | 3734.71 | 60% | 0% | 60% | 2240.826 | 0
JDH4-02-007-CN-4590 | JDH4-02-007-CN-4590 | Installation of Air Valves [Road 10 ] | 7253.64 | 100% | 0% | 100% | 7253.64 | 0
Potable Network | Potable Network |  | 62644.02 | 100% | 0% | 100% | 62644.02 | 0
Pipe Works | Pipe Works |  | 20491.46 | 100% | 0% | 100% | 20491.46 | 0
JDH4-02-007-CN-3370 | JDH4-02-007-CN-3370 | Excavation and Compaction (FDT) [Road 10 ] | 2049.15 | 100% | 0% | 100% | 2049.15 | 0
JDH4-02-007-CN-3440 | JDH4-02-007-CN-3440 | Sand Bedding [Road 10 ] | 1024.57 | 100% | 0% | 100% | 1024.57 | 0
JDH4-02-007-CN-3510 | JDH4-02-007-CN-3510 | Installation of HDPE Pipe [Road 10 ] | 10245.73 | 100% | 0% | 100% | 10245.73 | 0
JDH4-02-007-CN-3580 | JDH4-02-007-CN-3580 | Initial Pressure Test [Road 10 ] | 4098.29 | 100% | 0% | 100% | 4098.29 | 0
JDH4-02-007-CN-3650 | JDH4-02-007-CN-3650 | Sand Cover & Warning Tape [Road 10 ] | 1024.57 | 100% | 0% | 100% | 1024.57 | 0
JDH4-02-007-CN-3720 | JDH4-02-007-CN-3720 | Backfilling [Road 10 ] | 2049.15 | 100% | 0% | 100% | 2049.15 | 0
Pipe Encasement | Pipe Encasement |  | 1679.34 | 100% | 0% | 100% | 1679.34 | 0
JDH4-02-007-CN-3790 | JDH4-02-007-CN-3790 | Encasement for Pipes [Road 10 ] | 1679.34 | 100% | 0% | 100% | 1679.34 | 0
Valves | Valves |  | 2628.13 | 100% | 0% | 100% | 2628.13 | 0
JDH4-02-007-CN-3860 | JDH4-02-007-CN-3860 | Installation of Gate Valves [Road 10 ] | 2628.13 | 100% | 0% | 100% | 2628.13 | 0
Valve Chambers | Valve Chambers |  | 37845.08 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-4640 | JDH4-02-007-CN-4640 | Construction of Air Valve Chambers [Road 10 ] | 37845.08 | 100% | 0% | 100% | 37845.08 | 0
Electrical Works | Electrical Works |  | 335114.68 | 100% | 0% | 100% | 335114.68 | 0
MV & LV Cables | MV & LV Cables |  | 167612.33 | 0% | 100% | 100% | 167612.33 | 167612.33
Medium Voltage Cable | Medium Voltage Cable |  | 130978.55 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-2460 | JDH4-02-007-CN-2460 | Excavation for Trench [Road 10 ] | 6816.52 | 100% | 0% | 100% | 6816.52 | 0
JDH4-02-007-CN-2520 | JDH4-02-007-CN-2520 | Installation of Duct banks [Road 10 ] | 9251.02 | 100% | 0% | 100% | 9251.02 | 0
JDH4-02-007-CN-2580 | JDH4-02-007-CN-2580 | Installation of Medium Voltage Cables [Road 10 ] | 114911.01 | 100% | 0% | 100% | 114911.01 | 0
Low Voltage Cable | Low Voltage Cable |  | 36633.79 | 100% | 0% | 100% | 36633.79 | 0
JDH4-02-007-CN-2670 | JDH4-02-007-CN-2670 | Excavation for Low Voltage Cable [Road 10 ] | 9839.72 | 0% | 100% | 100% | 9839.72 | 9839.72
JDH4-02-007-CN-2680 | JDH4-02-007-CN-2680 | Installation of Low Voltage Cables [Road 10 ] | 26794.06 | 0% | 0% | 0% | 0 | 0
Telecommunication | Telecommunication |  | 167502.34 | 100% | 0% | 100% | 167502.34 | 0
JDH4-02-007-CN-3120 | JDH4-02-007-CN-3120 | Installation Road Crossing R/F 6 way 50mm HDPE Pipe [Road 10 ] | 76068.62 | 100% | 0% | 100% | 76068.62 | 0
JDH4-02-007-CN-3190 | JDH4-02-007-CN-3190 | Installation Road Crossing Un R/F 6 way 50mm HDPE Pipe [Road 10 ] | 3406.06 | 100% | 0% | 100% | 3406.06 | 0
JDH4-02-007-CN-3230 | JDH4-02-007-CN-3230 | Installation of 2 x 32 mm diameter HDPE ducts [Road 10 ] | 70997.38 | 100% | 0% | 100% | 70997.38 | 0
JDH4-02-007-CN-3300 | JDH4-02-007-CN-3300 | Installation of Manholes [Road 10 ] | 17030.29 | 0% | 0% | 0% | 0 | 0
Out of Zone | Out of Zone |  | 245794.71 | 100% | 0% | 100% | 245794.71 | 0
Electrical Works | Electrical Works |  | 245794.71 | 100% | 0% | 100% | 245794.71 | 0
MV & LV Cables | MV & LV Cables |  | 245794.71 | 0% | 100% | 100% | 245794.71 | 245794.71
Medium Voltage Cable | Medium Voltage Cable |  | 196298.14 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-2470 | JDH4-02-007-CN-2470 | Excavation for Trench [Out of Zone ] | 9236.12 | 90% | 10% | 100% | 9236.12 | 923.612
JDH4-02-007-CN-2530 | JDH4-02-007-CN-2530 | Installation of Duct banks [Out of Zone ] | 33303.68 | 90% | 10% | 100% | 33303.68 | 3330.368
JDH4-02-007-CN-2590 | JDH4-02-007-CN-2590 | Installation of Medium Voltage Cables [Out of Zone ] | 153758.35 | 0% | 0% | 0% | 0 | 0
Low Voltage Cable | Low Voltage Cable |  | 49496.57 | 100% | 0% | 100% | 49496.57 | 0
JDH4-02-007-CN-2690 | JDH4-02-007-CN-2690 | Excavation for Low Voltage Cable [Out of Zone ] | 13245.78 | 100% | 0% | 100% | 13245.78 | 0
JDH4-02-007-CN-2700 | JDH4-02-007-CN-2700 | Installation of Low Voltage Cables [Out of Zone ] | 36250.79 | 100% | 0% | 100% | 36250.79 | 0
Sewage Lift Station | Sewage Lift Station |  | 3049343.42 | 0% | 0% | 0% | 0 | 0
Site Works | Site Works |  | 10249.71 | 100% | 0% | 100% | 10249.71 | 0
JDH4-02-007-CN-5910 | JDH4-02-007-CN-5910 | Excavation [Sewage Lift Station ] | 3942.2 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-5920 | JDH4-02-007-CN-5920 | Backfilling [Sewage Lift Station ] | 1576.88 | 100% | 0% | 100% | 1576.88 | 0
JDH4-02-007-CN-5930 | JDH4-02-007-CN-5930 | Install gravel beddings [Sewage Lift Station ] | 4730.64 | 100% | 0% | 100% | 4730.64 | 0
Concrete Works | Concrete Works |  | 67679.63 | 100% | 0% | 100% | 67679.63 | 0
JDH4-02-007-CN-1010 | JDH4-02-007-CN-1010 | Lean concrete under the foundations [Sewage Lift Station ] | 2081.48 | 100% | 0% | 100% | 2081.48 | 0
JDH4-02-007-CN-1020 | JDH4-02-007-CN-1020 | Footings For Sewage Lift Station [Sewage Lift Station ] | 25230.06 | 100% | 0% | 100% | 25230.06 | 0
JDH4-02-007-CN-1030 | JDH4-02-007-CN-1030 | Cast concrete for trench Including Mastic sealant [Sewage Lift Station ] | 40368.09 | 0% | 0% | 0% | 0 | 0
Thermal & Moisture Protection | Thermal & Moisture Protection |  | 7001.34 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-1050 | JDH4-02-007-CN-1050 | Install 250 micron polyethylene sheet under slab on grade and footings [Sewage Lift Station ] | 2270.71 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-1060 | JDH4-02-007-CN-1060 | Applying 2 Coats of Bituminous Paint [Sewage Lift Station ] | 4730.64 | 0% | 0% | 0% | 0 | 0
Metals | Metals |  | 10092.02 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-1040 | JDH4-02-007-CN-1040 | Install Stainless steel [Sewage Lift Station ] | 10092.02 | 100% | 0% | 100% | 10092.02 | 0
Mechanical Works | Mechanical Works |  | 1705863.66 | 43.26% | 24.4% | 67.66% | 1154187.3524 | 416230.733
Pipes & Fittings | Pipes & Fittings |  | 256712.31 | 100% | 0% | 100% | 256712.31 | 0
JDH4-02-007-CN-1090 | JDH4-02-007-CN-1090 | Installation of Pipes & Fittings [Sewage Lift Station ] | 30587.93 | 100% | 0% | 100% | 30587.93 | 0
JDH4-02-007-CN-1100 | JDH4-02-007-CN-1100 | Installation of Gate Valves [Sewage Lift Station ] | 29014.56 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-1120 | JDH4-02-007-CN-1120 | Installation of Dismantling Joints [Sewage Lift Station ] | 13876.53 | 100% | 0% | 100% | 13876.53 | 0
JDH4-02-007-CN-1130 | JDH4-02-007-CN-1130 | Installation of Non Return Valve DN250 [Sewage Lift Station ] | 9461.27 | 100% | 0% | 100% | 9461.27 | 0
JDH4-02-007-CN-1140 | JDH4-02-007-CN-1140 | Installation of Air Valve DN60 [Sewage Lift Station ] | 11353.53 | 100% | 0% | 100% | 11353.53 | 0
JDH4-02-007-CN-1150 | JDH4-02-007-CN-1150 | Installation of Bauer Coupling DN150 [Sewage Lift Station ] | 4730.64 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-1160 | JDH4-02-007-CN-1160 | Installation of Odors scrubbing system [Sewage Lift Station ] | 157687.85 | 100% | 0% | 100% | 157687.85 | 0
Control Equipment | Control Equipment |  | 118265.89 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-1180 | JDH4-02-007-CN-1180 | Installation of Manually operated davit crane (portable) [Sewage Lift Station ] | 94612.71 | 100% | 0% | 100% | 94612.71 | 0
JDH4-02-007-CN-1190 | JDH4-02-007-CN-1190 | Installation of Air Vents [Sewage Lift Station ] | 4730.64 | 100% | 0% | 100% | 4730.64 | 0
JDH4-02-007-CN-1200 | JDH4-02-007-CN-1200 | Installation of Screening Container [Sewage Lift Station ] | 9461.27 | 100% | 0% | 100% | 9461.27 | 0
JDH4-02-007-CN-1210 | JDH4-02-007-CN-1210 | Installation of Baffle Plates [Sewage Lift Station ] | 9461.27 | 0% | 0% | 0% | 0 | 0
Interface Works | Interface Works |  | 63075.14 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-1220 | JDH4-02-007-CN-1220 | Interfacing Works [Sewage Lift Station ] | 63075.14 | 0% | 100% | 100% | 63075.14 | 63075.14
Anti Water Hammer Equipment | Anti Water Hammer Equipment |  | 883051.97 | 20% | 40% | 60% | 529831.182 | 353220.788
JDH4-02-007-CN-1230 | JDH4-02-007-CN-1230 | Installation of Anti-Water Hammer Equipment [Sewage Lift Station ] | 883051.97 | 20% | 40% | 60% | 529831.182 | 353220.788
Air Conditioning & Ventilation | Air Conditioning & Ventilation |  | 18922.54 | 100% | 0% | 100% | 18922.54 | 0
JDH4-02-007-CN-1240 | JDH4-02-007-CN-1240 | Installation of Air Conditioning [Sewage Lift Station ] | 18922.54 | 100% | 0% | 100% | 18922.54 | 0
Fuel System | Fuel System |  | 75690.17 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-1260 | JDH4-02-007-CN-1260 | Installation of Bulk Fuel storage tank, 2500 Liter (7 Days of storage) [Sewage Lift Station ] | 18922.54 | 100% | 0% | 100% | 18922.54 | 0
JDH4-02-007-CN-1270 | JDH4-02-007-CN-1270 | Installation of Fuel pump set , 1 duty and 1 standby, Capacity 100 L/h, Head 1 Bar [Sewage Lift Station ] | 47306.36 | 100% | 0% | 100% | 47306.36 | 0
JDH4-02-007-CN-1280 | JDH4-02-007-CN-1280 | Pipes and Fitting Works [Sewage Lift Station ] | 9461.27 | 100% | 0% | 100% | 9461.27 | 0
Fire Fighting | Fire Fighting |  | 56767.63 | 100% | 0% | 100% | 56767.63 | 0
JDH4-02-007-CN-1290 | JDH4-02-007-CN-1290 | Installation of Fire fighting for electrical room which has a volume of about 62 m3 [Sewage Lift Station ] | 47306.36 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-1300 | JDH4-02-007-CN-1300 | Installation of Foam type - wheeled type 20 Gallon capacity-ref. FE-01 [Sewage Lift Station ] | 9461.27 | 100% | 0% | 100% | 9461.27 | 0
Pumps | Pumps |  | 233378.02 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-1070 | JDH4-02-007-CN-1070 | Installation of Submersible pump [Sewage Lift Station ] | 233378.02 | 15% | 0% | 15% | 35006.703 | 0
Electrical Works | Electrical Works |  | 1230213.96 | 100% | 0% | 100% | 1230213.96 | 0
Main Distribution Board | Main Distribution Board |  | 104073.98 | 0% | 50% | 50% | 52036.99 | 52036.99
JDH4-02-007-CN-1310 | JDH4-02-007-CN-1310 | Installation of Main Distribution Board/MCC Panel [Sewage Lift Station ] | 75690.17 | #REF! | #REF! | #REF! | #REF! | #REF!
JDH4-02-007-CN-1320 | JDH4-02-007-CN-1320 | Installation of Panel Board [Sewage Lift Station ] | 28383.81 | 0% | 50% | 50% | 14191.905 | 14191.905
Local Control Panel | Local Control Panel |  | 107227.74 | 0% | 50% | 50% | 53613.87 | 53613.87
JDH4-02-007-CN-1330 | JDH4-02-007-CN-1330 | Installation of MCP-LP-01 [Sewage Lift Station ] | 25230.06 | #REF! | #REF! | #REF! | #REF! | #REF!
JDH4-02-007-CN-1350 | JDH4-02-007-CN-1350 | Installation of MCP-LP-02 [Sewage Lift Station ] | 25230.06 | 0% | 50% | 50% | 12615.03 | 12615.03
JDH4-02-007-CN-1360 | JDH4-02-007-CN-1360 | Installation of OD-CP [Sewage Lift Station ] | 28383.81 | 0% | 50% | 50% | 14191.905 | 14191.905
JDH4-02-007-CN-1370 | JDH4-02-007-CN-1370 | Installation of FP-CP [Sewage Lift Station ] | 28383.81 | 0% | 50% | 50% | 14191.905 | 14191.905
Diesel Generator | Diesel Generator |  | 75690.17 | #REF! | #REF! | #REF! | #REF! | #REF!
JDH4-02-007-CN-1380 | JDH4-02-007-CN-1380 | Installation of Standby Diesel Generator [Sewage Lift Station ] | 75690.17 | 100% | 0% | 100% | 75690.17 | 0
Power Factor Correction Capacitor Bank | Power Factor Correction Capacitor Bank |  | 22076.3 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-1390 | JDH4-02-007-CN-1390 | Installation of Power Factor Correction Capacitor Bank [Sewage Lift Station ] | 22076.3 | 0% | 50% | 50% | 11038.15 | 11038.15
Low-Voltage Electrical Power Conductors and Cables | Low-Voltage Electrical Power Conductors and Cables |  | 17535.21 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-1410 | JDH4-02-007-CN-1410 | Installation of Low Voltage Cables [Sewage Lift Station ] | 17535.21 | 0% | 30% | 30% | 5260.563 | 5260.563
Wiring Devices | Wiring Devices |  | 5044.13 | #REF! | #REF! | #REF! | #REF! | #REF!
JDH4-02-007-CN-1420 | JDH4-02-007-CN-1420 | Installation of Wiring Devices [Sewage Lift Station ] | 5044.13 | 100% | 0% | 100% | 5044.13 | 0
Enclosed Switches and Circuit Breakers | Enclosed Switches and Circuit Breakers |  | 8830.52 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-1440 | JDH4-02-007-CN-1440 | Installation of Enclosed Switches and Circuit Breakers [Sewage Lift Station ] | 8830.52 | 0% | 0% | 0% | 0 | 0
Lighting | Lighting |  | 16399.54 | #REF! | #REF! | #REF! | #REF! | #REF!
JDH4-02-007-CN-1450 | JDH4-02-007-CN-1450 | Installation of Lightings [Sewage Lift Station ] | 16399.54 | 100% | 0% | 100% | 16399.54 | 0
Grounding and Bonding for Electrical Systems | Grounding and Bonding for Electrical Systems |  | 18607.17 | #REF! | #REF! | #REF! | #REF! | #REF!
JDH4-02-007-CN-1460 | JDH4-02-007-CN-1460 | Installation of Grounding Links [Sewage Lift Station ] | 18607.17 | 0% | 0% | 0% | 0 | 0
Electrical Manholes | Electrical Manholes |  | 10723.16 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-1470 | JDH4-02-007-CN-1470 | Installation of Electrical Manholes [Sewage Lift Station ] | 10723.16 | 100% | 0% | 100% | 10723.16 | 0
ICT (Data& telephone System) | ICT (Data& telephone System) |  | 44152.6 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-1490 | JDH4-02-007-CN-1490 | Installation of IDF Cabinet 9U (for data &Telephone) [Sewage Lift Station ] | 22076.3 | 0% | 50% | 50% | 11038.15 | 11038.15
JDH4-02-007-CN-1500 | JDH4-02-007-CN-1500 | Installationof Single data/Telephone outlet [Sewage Lift Station ] | 1261.5 |  | 0%
JDH4-02-007-CN-1510 | JDH4-02-007-CN-1510 | Installation of Data Switch (24 Port) [Sewage Lift Station ] | 18922.54 |  | 0%
JDH4-02-007-CN-1520 | JDH4-02-007-CN-1520 | Installation of Fiber optic cable (12 Core single mode). [Sewage Lift Station ] | 1892.25 | 0% | 0% | 0% | 0 | 0
Security System (CCTV System) | Security System (CCTV System) |  | 198686.69 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-1530 | JDH4-02-007-CN-1530 | Installation of 5.0 Megapixel, Fixed bullet IP CCTV camera [Sewage Lift Station ] | 198686.69 | 100% | 0% | 100% | 198686.69 | 0
Duct Bank and Handhole For Telecom Network | Duct Bank and Handhole For Telecom Network |  | 8199.77 | 100% | 0% | 100% | 8199.77 | 0
JDH4-02-007-CN-1540 | JDH4-02-007-CN-1540 | Installation of 2 x 50mm HDPE ducts Bank [Sewage Lift Station ] | 5046.01 | 100% | 0% | 100% | 5046.01 | 0
JDH4-02-007-CN-1550 | JDH4-02-007-CN-1550 | Installation of Handholes (800x800x800 mm) [Sewage Lift Station ] | 3153.76 | 100% | 0% | 100% | 3153.76 | 0
Programmable Logic Controllers | Programmable Logic Controllers |  | 252300.56 |  | 0%
JDH4-02-007-CN-1570 | JDH4-02-007-CN-1570 | Installation of Programmable Logic Controller [Sewage Lift Station ] | 252300.56 | 0% | 30% | 30% | 75690.168 | 75690.168
Process Control Wiring | Process Control Wiring |  | 157687.85 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-1580 | JDH4-02-007-CN-1580 | Installation of Process Control Wiring [Sewage Lift Station ] | 157687.85 | 0% | 0% | 0% | 0 | 0
Instrumentation for Process Systems | Instrumentation for Process Systems |  | 182978.58 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-CN-1600 | JDH4-02-007-CN-1600 | Installation of Process System [Sewage Lift Station ] | 182978.58 | 28% | 2% | 30% | 54893.574 | 3659.5716
Fence Work | Fence Work |  | 18243.11 | 100% | 0% | 100% | 18243.11 | 0
JDH4-02-007-CN-5890 | JDH4-02-007-CN-5890 | Installation of Chain Link Fence [Sewage Lift Station ] | 11984.28 |  | 0%
JDH4-02-007-CN-5900 | JDH4-02-007-CN-5900 | Installation of Pedestrian Gate [Sewage Lift Station ] | 6258.83 | 100% | 0% | 100% | 6258.83 | 0
Testing & Commissioning | Testing & Commissioning |  | 5730434.78 | 67.86% | 2.85% | 70.71% | 4051990.4329 | 163317.3912
JDH4-02-007-TC-1020 | JDH4-02-007-TC-1020 | Test for Sanitary Sewerage | 818633.54 | 100% | 0% | 100% | 818633.54 | 0
JDH4-02-007-TC-1030 | JDH4-02-007-TC-1030 | Test for Stormwater Utilities | 818633.54 | 100% | 0% | 100% | 818633.54 | 0
JDH4-02-007-TC-1000 | JDH4-02-007-TC-1000 | Test for Potable Water Network | 818633.54 | 100% | 0% | 100% | 818633.54 | 0
JDH4-02-007-TC-1010 | JDH4-02-007-TC-1010 | Test for TSE Network | 818633.54 | 100% | 0% | 100% | 818633.54 | 0
JDH4-02-007-TC-1040 | JDH4-02-007-TC-1040 | Test for Electrical Network | 818633.54 |  | 0%
JDH4-02-007-TC-1050 | JDH4-02-007-TC-1050 | Test for Sewage Lift Station | 818633.54 | 15% | 5% | 20% | 163726.708 | 40931.677
JDH4-02-007-TC-1060 | JDH4-02-007-TC-1060 | Test for Road Works | 818633.54 | 40% | 15% | 55% | 450248.447 | 122795.031
Project Hand Over & Close-out | Project Hand Over & Close-out |  | 0 | 0% | 0% | 0% | 0 | 0
As-Built DWGs | As-Built DWGs |  | 0 | 0% | 0% | 0% | 0 | 0
As-Built DWGs Submittal | As-Built DWGs Submittal |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-AB-1020 | JDH4-02-007-AB-1020 | As-Built DWGs Submittal for Sanitary Sewerage | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-AB-1030 | JDH4-02-007-AB-1030 | As-Built DWGs Submittal for Stormwater Utilities | 0 |  | 0%
JDH4-02-007-AB-1000 | JDH4-02-007-AB-1000 | As-Built DWGs Submittal for Potable Water Network | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-AB-1010 | JDH4-02-007-AB-1010 | As-Built DWGs Submittal for TSE Network | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-AB-1040 | JDH4-02-007-AB-1040 | As-Built DWGs Submittal for Electrical Network | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-AB-1050 | JDH4-02-007-AB-1050 | As-Built DWGs Submittal for Sewage Lift Station | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-AB-1060 | JDH4-02-007-AB-1060 | As-Built DWGs Submittal for Road Works | 0 | 0% | 0% | 0% | 0 | 0
As-Built DWGs Approval | As-Built DWGs Approval |  | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-AB-1090 | JDH4-02-007-AB-1090 | As- Built DWGs Approval for Sanitary Sewerage | 0 |  | 0%
JDH4-02-007-AB-1100 | JDH4-02-007-AB-1100 | As- Built DWGs Approval for Stormwater Utilities | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-AB-1070 | JDH4-02-007-AB-1070 | As- Built DWGs Approval for Potable Water Network | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-AB-1080 | JDH4-02-007-AB-1080 | As- Built DWGs Approval for TSE Network | 0 | 100% | 0% | 100% | 0 | 0
JDH4-02-007-AB-1110 | JDH4-02-007-AB-1110 | As- Built DWGs Approval for Electrical Network | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-AB-1120 | JDH4-02-007-AB-1120 | As- Built DWGs Approval for Sewage Lift Station | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-AB-1130 | JDH4-02-007-AB-1130 | As- Built DWGs Approval for Road Works | 0 | 0% | 0% | 0% | 0 | 0
Demobilization | Demobilization |  | 0 |  | 0%
JDH4-02-007-DM-1000 | JDH4-02-007-DM-1000 | Demobilization of Manpower | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-DM-1010 | JDH4-02-007-DM-1010 | Removal of Equipment from Site | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-DM-1020 | JDH4-02-007-DM-1020 | Site Clean Up | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-DM-1030 | JDH4-02-007-DM-1030 | Removal of Site Offices and Structures | 0 | 0% | 0% | 0% | 0 | 0
JDH4-02-007-DM-1040 | JDH4-02-007-DM-1040 | Restoration of Ground Surfaces | 0 | 0% | 0% | 0% | 0 | 0

## Current week
Activity ID | Activity ID | Activity Name | Budgeted Total Cost | Activity % Complete | Performance % Complete | Earned Value Cost
Infrastructure Development for Madinah Industrial city Phase 1-A | JDH4-02-007-R-UP-Land Development of Jeddah Oasis- 13 Oct 2026 |  | 57304347.86 |  | 93.31% | 53468556.35
Key Milestones | Key Milestones |  | 0 |  | 0% | 0
General Milestone | General Milestone |  | 0 |  | 0% | 0
JDH4-02-007-MS-1000 | JDH4-02-007-MS-1000 | Project Commencement Date | 0 | 100% | 100% | 0
JDH4-02-007-MS-1010 | JDH4-02-007-MS-1010 | Project Completion Date | 0 | 0% | 0% | 0
Contractual Milestone | Contractual Milestone |  | 0 |  | 0% | 0
Engineering & Mobilization | Engineering & Mobilization |  | 0 |  | 0% | 0
JDH4-02-007-MS-1020 | JDH4-02-007-MS-1020 | Completion of Mobilization | 0 | 100% | 100% | 0
JDH4-02-007-MS-1030 | JDH4-02-007-MS-1030 | Submission of the Work Plan (Baseline Programme) | 0 | 100% | 100% | 0
JDH4-02-007-MS-1040 | JDH4-02-007-MS-1040 | Submission and Approval of Drawings and Materials | 0 | 100% | 100% | 0
Construction | Construction |  | 0 |  | 0% | 0
JDH4-02-007-MS-1060 | JDH4-02-007-MS-1060 | Completion of Sewerage networks | 0 | 100% | 100% | 0
JDH4-02-007-MS-1090 | JDH4-02-007-MS-1090 | Completion of TSE Network | 0 | 100% | 100% | 0
JDH4-02-007-MS-1080 | JDH4-02-007-MS-1080 | Completion of Potable Water Network | 0 | 100% | 100% | 0
JDH4-02-007-MS-1050 | JDH4-02-007-MS-1050 | Completion of Earthworks & Site Grading For Plots | 0 | 0% | 0% | 0
JDH4-02-007-MS-1070 | JDH4-02-007-MS-1070 | Completion of Road Works | 0 | 0% | 0% | 0
JDH4-02-007-MS-1100 | JDH4-02-007-MS-1100 | Completion of Electrical Networks | 0 | 0% | 0% | 0
JDH4-02-007-MS-1110 | JDH4-02-007-MS-1110 | Completion of Entire Project | 0 | 0% | 0% | 0
Monitoring & Controlling Milestone | Monitoring & Controlling Milestone |  | 0 |  | 0% | 0
JDH4-02-007-MS-1120 | JDH4-02-007-MS-1120 | Approval of Electrical Network Shop DWGs By SEC | 0 | 100% | 100% | 0
JDH4-02-007-MS-1130 | JDH4-02-007-MS-1130 | Approval of Electrical Network Materials By SEC | 0 | 100% | 100% | 0
Mobilization | Mobilization |  | 0 |  | 0% | 0
Site Facilities & Offices | Site Facilities & Offices |  | 0 |  | 0% | 0
JDH4-02-007-MB-1000 | JDH4-02-007-MB-1000 | Site Layout Plan | 0 | 100% | 100% | 0
JDH4-02-007-MB-1010 | JDH4-02-007-MB-1010 | Clear & Grub for Offices & Access Road | 0 | 100% | 100% | 0
JDH4-02-007-MB-1020 | JDH4-02-007-MB-1020 | Construct Site Access Roads | 0 | 100% | 100% | 0
JDH4-02-007-MB-1040 | JDH4-02-007-MB-1040 | Construct Site Offices & Storage | 0 | 100% | 100% | 0
JDH4-02-007-MB-1030 | JDH4-02-007-MB-1030 | Construct Temporary Fence | 0 | 100% | 100% | 0
JDH4-02-007-MB-1060 | JDH4-02-007-MB-1060 | Install Site Facilities | 0 | 100% | 100% | 0
JDH4-02-007-MB-1070 | JDH4-02-007-MB-1070 | Electrical Works & Connections | 0 | 100% | 100% | 0
JDH4-02-007-MB-1090 | JDH4-02-007-MB-1090 | Mobilization of Equipment | 0 | 100% | 100% | 0
JDH4-02-007-MB-1100 | JDH4-02-007-MB-1100 | Mobilization of Manpower | 0 | 100% | 100% | 0
JDH4-02-007-MB-1050 | JDH4-02-007-MB-1050 | Install Project Signs | 0 | 100% | 100% | 0
JDH4-02-007-MB-1080 | JDH4-02-007-MB-1080 | Construct Parking Sheds | 0 | 100% | 100% | 0
Topographic Survey | Topographic Survey |  | 0 |  | 0% | 0
JDH4-02-007-TP-1000 | JDH4-02-007-TP-1000 | Site Survey Works | 0 | 100% | 100% | 0
Permit's and Authority Approvals | Permit's and Authority Approvals |  | 0 |  | 0% | 0
JDH4-02-007-PA-1000 | JDH4-02-007-PA-1000 | Excavation & Backfilling Permit Permit | 0 | 100% | 100% | 0
JDH4-02-007-PA-1010 | JDH4-02-007-PA-1010 | Saudi Electricity Company Permit | 0 | 100% | 100% | 0
Preliminary Submittals | Preliminary Submittals |  | 0 |  | 0% | 0
Preparation and Submittal by Contractor's | Preparation and Submittal by Contractor's |  | 0 |  | 0% | 0
JDH4-02-007-PS-1000 | JDH4-02-007-PS-1000 | Preparation and Submittal of Detailed Work Order Programme (baseline schedule) | 0 | 100% | 100% | 0
JDH4-02-007-PS-1020 | JDH4-02-007-PS-1020 | Preparation and Submittal of Quality Management Plan | 0 | 100% | 100% | 0
JDH4-02-007-PS-1030 | JDH4-02-007-PS-1030 | Preparation and Submittal of Safety Management Plan | 0 | 100% | 100% | 0
JDH4-02-007-PS-1040 | JDH4-02-007-PS-1040 | Preparation and Submittal of Organization Chart | 0 | 100% | 100% | 0
JDH4-02-007-PS-1050 | JDH4-02-007-PS-1050 | Preparation and Submittal of Communication Plan | 0 | 100% | 100% | 0
JDH4-02-007-PS-1010 | JDH4-02-007-PS-1010 | Preparation and Submittal of Project Execution Plan | 0 | 100% | 100% | 0
Approval by the Employer's | Approval by the Employer's |  | 0 |  | 0% | 0
JDH4-02-007-PS-1100 | JDH4-02-007-PS-1100 | Approval of Organization Chart | 0 | 100% | 100% | 0
JDH4-02-007-PS-1110 | JDH4-02-007-PS-1110 | Approval of Comminumcation Plan | 0 | 100% | 100% | 0
JDH4-02-007-PS-1060 | JDH4-02-007-PS-1060 | Approval of Detailed Work Order Programme (baseline schedule) | 0 | 100% | 100% | 0
JDH4-02-007-PS-1090 | JDH4-02-007-PS-1090 | Approval of Safety Management Plan | 0 | 100% | 100% | 0
JDH4-02-007-PS-1080 | JDH4-02-007-PS-1080 | Approval of Quality Management Plan | 0 | 100% | 100% | 0
JDH4-02-007-PS-1070 | JDH4-02-007-PS-1070 | Approval of Project Execution Plan | 0 | 100% | 100% | 0
Engineering | Engineering |  | 1719130.43 |  | 100% | 1719130.43
Shop Drawings | Shop Drawings |  | 0 |  | 0% | 0
Shop Drawings Submittal | Shop Drawings Submittal |  | 0 |  | 0% | 0
Shop Drawings Submittal for Road Works | Shop Drawings Submittal for Road Works |  | 0 |  | 0% | 0
JDH4-02-007-EN-1040 | JDH4-02-007-EN-1040 | Shop DWG Submittal for Topographic Survey | 0 | 100% | 100% | 0
JDH4-02-007-EN-1050 | JDH4-02-007-EN-1050 | Shop DWG Submittal for Road Layout Plan | 0 | 100% | 100% | 0
JDH4-02-007-EN-1070 | JDH4-02-007-EN-1070 | Shop DWG Submittal for Road Setting Out | 0 | 100% | 100% | 0
JDH4-02-007-EN-1080 | JDH4-02-007-EN-1080 | Shop DWG Submittal for Road Profiles | 0 | 100% | 100% | 0
JDH4-02-007-EN-1090 | JDH4-02-007-EN-1090 | Shop DWG Submittal for Grading Layout Plan | 0 | 100% | 100% | 0
JDH4-02-007-EN-1100 | JDH4-02-007-EN-1100 | Shop DWG Submittal for Curb Setting Out Points | 0 | 100% | 100% | 0
JDH4-02-007-EN-1120 | JDH4-02-007-EN-1120 | Shop DWG Submittal for Standards Details | 0 | 100% | 100% | 0
JDH4-02-007-EN-1060 | JDH4-02-007-EN-1060 | Shop DWG Submittal for Typical Cross Section | 0 | 100% | 100% | 0
JDH4-02-007-EN-1110 | JDH4-02-007-EN-1110 | Shop DWG Submittal for Signing & Marking Layout Plan | 0 | 100% | 100% | 0
Shop Drawings Submittal for Stormwater Network | Shop Drawings Submittal for Stormwater Network |  | 0 |  | 0% | 0
JDH4-02-007-EN-1250 | JDH4-02-007-EN-1250 | Shop DWG Submittal for Stormwater Plans | 0 | 100% | 100% | 0
JDH4-02-007-EN-1260 | JDH4-02-007-EN-1260 | Shop DWG Submittal for Stormwater Profiles | 0 | 100% | 100% | 0
JDH4-02-007-EN-1270 | JDH4-02-007-EN-1270 | Shop DWG Submittal for Stormwater Standard Details | 0 | 100% | 100% | 0
Shop Drawings Submittal for Sanitary Sewerage | Shop Drawings Submittal for Sanitary Sewerage |  | 0 |  | 0% | 0
JDH4-02-007-EN-1220 | JDH4-02-007-EN-1220 | Shop DWG Submittal for Sanitary Sewerage Plans | 0 | 100% | 100% | 0
JDH4-02-007-EN-1230 | JDH4-02-007-EN-1230 | Shop DWG Submittal for Sanitary Sewerage Profiles | 0 | 100% | 100% | 0
JDH4-02-007-EN-1240 | JDH4-02-007-EN-1240 | Shop DWG Submittal for Sanitary Sewerage Standard Details | 0 | 100% | 100% | 0
Shop Drawings Submittal for TSE Network | Shop Drawings Submittal for TSE Network |  | 0 |  | 0% | 0
JDH4-02-007-EN-1190 | JDH4-02-007-EN-1190 | Shop DWG Submittal for TSE Network Plans | 0 | 100% | 100% | 0
JDH4-02-007-EN-1200 | JDH4-02-007-EN-1200 | Shop DWG Submittal for TSE Profiles | 0 | 100% | 100% | 0
JDH4-02-007-EN-1210 | JDH4-02-007-EN-1210 | Shop DWG Submittal for TSE Standard Details | 0 | 100% | 100% | 0
Shop Drawings Submittal for Potable Water Network | Shop Drawings Submittal for Potable Water Network |  | 0 |  | 0% | 0
JDH4-02-007-EN-1160 | JDH4-02-007-EN-1160 | Shop DWG Submittal for Potable Water Plans | 0 | 100% | 100% | 0
JDH4-02-007-EN-1170 | JDH4-02-007-EN-1170 | Shop DWG Submittal for Potable Water Profiles | 0 | 100% | 100% | 0
JDH4-02-007-EN-1180 | JDH4-02-007-EN-1180 | Shop DWG Submittal for Potable Water Standard Details | 0 | 100% | 100% | 0
Shop Drawings Submittal for Electrical Network | Shop Drawings Submittal for Electrical Network |  | 0 |  | 0% | 0
JDH4-02-007-EN-1140 | JDH4-02-007-EN-1140 | Shop DWG Submittal for Street Lighting | 0 | 100% | 100% | 0
JDH4-02-007-EN-1150 | JDH4-02-007-EN-1150 | Shop DWG Submittal for Low Voltage Network | 0 | 100% | 100% | 0
JDH4-02-007-EN-1130 | JDH4-02-007-EN-1130 | Shop DWG Submittal for Medium Voltage Network | 0 | 100% | 100% | 0
Shop Drawings Submittal for Telecommunications | Shop Drawings Submittal for Telecommunications |  | 0 |  | 0% | 0
JDH4-02-007-EN-1600 | JDH4-02-007-EN-1600 | Shop DWG Submittal for Telecommunications Works | 0 | 100% | 100% | 0
Shop Drawings Submittal for Earthing System | Shop Drawings Submittal for Earthing System |  | 0 |  | 0% | 0
JDH4-02-007-EN-1610 | JDH4-02-007-EN-1610 | Shop DWG Submittal for Earthing System | 0 | 100% | 100% | 0
Shop Drawings Submittal for Road Lighting | Shop Drawings Submittal for Road Lighting |  | 0 |  | 0% | 0
JDH4-02-007-EN-1000 | JDH4-02-007-EN-1000 | Shop DWG Submittal for Street Lighting General Arrangement | 0 | 100% | 100% | 0
JDH4-02-007-EN-1010 | JDH4-02-007-EN-1010 | Shop DWG Submittal for Street Lighting Network Layout | 0 | 100% | 100% | 0
JDH4-02-007-EN-1020 | JDH4-02-007-EN-1020 | Shop DWG Submittal for Street Lighting Details | 0 | 100% | 100% | 0
JDH4-02-007-EN-1030 | JDH4-02-007-EN-1030 | Shop DWG Submittal for Street Lighting Single Line Diagram | 0 | 100% | 100% | 0
Shop Drawings Submittal for Sewage Lift Station | Shop Drawings Submittal for Sewage Lift Station |  | 0 |  | 0% | 0
JDH4-02-007-EN-1280 | JDH4-02-007-EN-1280 | Shop DWG Submittal for the Sewage Lift Station - Civil Works | 0 | 100% | 100% | 0
JDH4-02-007-EN-1290 | JDH4-02-007-EN-1290 | Shop DWG Submittal for the Sewage Lift Station - Mechanical Works | 0 | 100% | 100% | 0
JDH4-02-007-EN-1310 | JDH4-02-007-EN-1310 | Shop DWG Submittal for the Sewage Lift Station - Finishing Works | 0 | 100% | 100% | 0
JDH4-02-007-EN-1300 | JDH4-02-007-EN-1300 | Shop DWG Submittal for the Sewage Lift Station - Electrical Works | 0 | 100% | 100% | 0
Shop Drawings Approval | Shop Drawings Approval |  | 0 |  | 0% | 0
Shop Drawings Approval for Road Works | Shop Drawings Approval for Road Works |  | 0 |  | 0% | 0
JDH4-02-007-EN-1320 | JDH4-02-007-EN-1320 | Shop DWG Approval for Topographic Survey | 0 | 100% | 100% | 0
JDH4-02-007-EN-1330 | JDH4-02-007-EN-1330 | Shop DWG Approval for Road Layout Plan | 0 | 100% | 100% | 0
JDH4-02-007-EN-1340 | JDH4-02-007-EN-1340 | Shop DWG Approval for Typical Cross Section | 0 | 100% | 100% | 0
JDH4-02-007-EN-1350 | JDH4-02-007-EN-1350 | Shop DWG Approval for Road Setting Out | 0 | 100% | 100% | 0
JDH4-02-007-EN-1360 | JDH4-02-007-EN-1360 | Shop DWG Approval for Road Profiles | 0 | 100% | 100% | 0
JDH4-02-007-EN-1370 | JDH4-02-007-EN-1370 | Shop DWG Approval for Grading Layout Plan | 0 | 100% | 100% | 0
JDH4-02-007-EN-1380 | JDH4-02-007-EN-1380 | Shop DWG Approval for Curb Setting Out Points | 0 | 100% | 100% | 0
JDH4-02-007-EN-1400 | JDH4-02-007-EN-1400 | Shop DWG Approval for Standards Details | 0 | 100% | 100% | 0
JDH4-02-007-EN-1390 | JDH4-02-007-EN-1390 | Shop DWG Approval for Signing & Marking Layout Plan | 0 | 100% | 100% | 0
Shop Drawings Approval for Storm Network | Shop Drawings Approval for Storm Network |  | 0 |  | 0% | 0
JDH4-02-007-EN-1530 | JDH4-02-007-EN-1530 | Shop DWG Approval for Stormwater Plans | 0 | 100% | 100% | 0
JDH4-02-007-EN-1540 | JDH4-02-007-EN-1540 | Shop DWG Approval for Stormwater Profiles | 0 | 100% | 100% | 0
JDH4-02-007-EN-1550 | JDH4-02-007-EN-1550 | Shop DWG Approval for Stormwater Standard Details | 0 | 100% | 100% | 0
Shop Drawings Approval for Sanitary Sewerage | Shop Drawings Approval for Sanitary Sewerage |  | 0 |  | 0% | 0
JDH4-02-007-EN-1500 | JDH4-02-007-EN-1500 | Shop DWG Approval for Sanitary Sewerage Plans | 0 | 100% | 100% | 0
JDH4-02-007-EN-1510 | JDH4-02-007-EN-1510 | Shop DWG Approval for Sanitary Sewerage Profiles | 0 | 100% | 100% | 0
JDH4-02-007-EN-1520 | JDH4-02-007-EN-1520 | Shop DWG Approval for Sanitary Sewerage Standard Details | 0 | 100% | 100% | 0
Shop Drawings Approval for TSE Network | Shop Drawings Approval for TSE Network |  | 0 |  | 0% | 0
JDH4-02-007-EN-1470 | JDH4-02-007-EN-1470 | Shop DWG Approval for TSE Network Plans | 0 | 100% | 100% | 0
JDH4-02-007-EN-1480 | JDH4-02-007-EN-1480 | Shop DWG Approval for TSE Profiles | 0 | 100% | 100% | 0
JDH4-02-007-EN-1490 | JDH4-02-007-EN-1490 | Shop DWG Approval for TSE Standard Details | 0 | 100% | 100% | 0
Shop Drawings Approval for Potable Water Network | Shop Drawings Approval for Potable Water Network |  | 0 |  | 0% | 0
JDH4-02-007-EN-1440 | JDH4-02-007-EN-1440 | Shop DWG Approval for Potable Water Plans | 0 | 100% | 100% | 0
JDH4-02-007-EN-1450 | JDH4-02-007-EN-1450 | Shop DWG Approval for Potable Water Profiles | 0 | 100% | 100% | 0
JDH4-02-007-EN-1460 | JDH4-02-007-EN-1460 | Shop DWG Approval for Potable Water Standard Details | 0 | 100% | 100% | 0
Shop Drawings Approval for Electrical Network | Shop Drawings Approval for Electrical Network |  | 0 |  | 0% | 0
JDH4-02-007-EN-1420 | JDH4-02-007-EN-1420 | Shop DWG Approval for Street Lighting by By SEC | 0 | 100% | 100% | 0
JDH4-02-007-EN-1430 | JDH4-02-007-EN-1430 | Shop DWG Approval for Low Voltage Network By SEC | 0 | 100% | 100% | 0
JDH4-02-007-EN-1410 | JDH4-02-007-EN-1410 | Shop DWG Approval for Medium Voltage Network By SEC | 0 | 100% | 100% | 0
Shop Drawings Approval for Telecommunications | Shop Drawings Approval for Telecommunications |  | 0 |  | 0% | 0
JDH4-02-007-EN-1620 | JDH4-02-007-EN-1620 | Shop DWG Approval for Telecommunications Works | 0 | 100% | 100% | 0
Shop Drawings Approval for Earthing System | Shop Drawings Approval for Earthing System |  | 0 |  | 0% | 0
JDH4-02-007-EN-1630 | JDH4-02-007-EN-1630 | Shop DWG Approval for Earthing System By SEC | 0 | 100% | 100% | 0
Shop Drawings Approval for Road Lighting | Shop Drawings Approval for Road Lighting |  | 0 |  | 0% | 0
JDH4-02-007-EN-1640 | JDH4-02-007-EN-1640 | Shop DWG Approval for Street Lighting General Arrangement By SEC | 0 | 100% | 100% | 0
JDH4-02-007-EN-1650 | JDH4-02-007-EN-1650 | Shop DWG Approval for Street Lighting Network Layout By SEC | 0 | 100% | 100% | 0
JDH4-02-007-EN-1660 | JDH4-02-007-EN-1660 | Shop DWG Approval for Street Lighting Details By SEC | 0 | 100% | 100% | 0
JDH4-02-007-EN-1670 | JDH4-02-007-EN-1670 | Shop DWG Approval for Street Lighting Single Line Diagram By SEC | 0 | 100% | 100% | 0
Shop Drawings Approval for Sewage Lift Station | Shop Drawings Approval for Sewage Lift Station |  | 0 |  | 0% | 0
JDH4-02-007-EN-1680 | JDH4-02-007-EN-1680 | Shop DWG Approval for the Sewage Lift Station - Civil Works | 0 | 100% | 100% | 0
JDH4-02-007-EN-1690 | JDH4-02-007-EN-1690 | Shop DWG Approval for the Sewage Lift Station - Mechanical Works | 0 | 100% | 100% | 0
JDH4-02-007-EN-1710 | JDH4-02-007-EN-1710 | Shop DWG Approval for the Sewage Lift Station - Finishing Works | 0 | 100% | 100% | 0
JDH4-02-007-EN-1700 | JDH4-02-007-EN-1700 | Shop DWG Approval for the Sewage Lift Station - Electrical Works | 0 | 100% | 100% | 0
Method Statements | Method Statements |  | 0 |  | 0% | 0
Method Statements Submittal | Method Statements Submittal |  | 0 |  | 0% | 0
JDH4-02-007-EN-1560 | JDH4-02-007-EN-1560 | Preparation & Submission of Method Statement for Earthworks | 0 | 100% | 100% | 0
JDH4-02-007-EN-1570 | JDH4-02-007-EN-1570 | Preparation & Submission of Method Statement for Concrete Works | 0 | 100% | 100% | 0
JDH4-02-007-EN-1580 | JDH4-02-007-EN-1580 | Preparation & Submission of Method Statement for Waterproofing Works | 0 | 100% | 100% | 0
JDH4-02-007-EN-1590 | JDH4-02-007-EN-1590 | Preparation & Submission of Method Statement for Asphalt | 0 | 100% | 100% | 0
Method Statements Approval | Method Statements Approval |  | 0 |  | 0% | 0
JDH4-02-007-EN-1720 | JDH4-02-007-EN-1720 | Approval of Method Statement for Earthworks | 0 | 100% | 100% | 0
JDH4-02-007-EN-1730 | JDH4-02-007-EN-1730 | Approval of Method Statement for Concrete Works | 0 | 100% | 100% | 0
JDH4-02-007-EN-1740 | JDH4-02-007-EN-1740 | Approval of Method Statement for Waterproofing Works | 0 | 100% | 100% | 0
JDH4-02-007-EN-1750 | JDH4-02-007-EN-1750 | Approval of Method Statement for Asphalt | 0 | 100% | 100% | 0
Method Statements Staging Time | Method Statements Staging Time |  | 0 |  | 0% | 0
JDH4-02-007-EN-1760 | JDH4-02-007-EN-1760 | Staging Time of Method Statement for Earthworks | 0 | 100% | 100% | 0
JDH4-02-007-EN-1770 | JDH4-02-007-EN-1770 | Staging Time of Method Statement for Concrete Works | 0 | 100% | 100% | 0
JDH4-02-007-EN-1780 | JDH4-02-007-EN-1780 | Staging Time of Method Statement for Waterproofing Works | 0 | 100% | 100% | 0
JDH4-02-007-EN-1790 | JDH4-02-007-EN-1790 | Staging Time of Method Statement for Asphalt | 0 | 100% | 100% | 0
Pre-qualification and Material | Pre-qualification and Material |  | 1719130.43 |  | 100% | 1719130.43
Pre-qualification | Pre-qualification |  | 0 |  | 0% | 0
Road Works - Civil | Road Works - Civil |  | 0 |  | 0% | 0
Steel Reinforcement | Steel Reinforcement |  | 0 |  | 0% | 0
JDH4-02-007-SB-1580 | JDH4-02-007-SB-1580 | Pre-Qualification Submittal for Steel Reinforcement | 0 | 100% | 100% | 0
JDH4-02-007-SB-1590 | JDH4-02-007-SB-1590 | Pre-Qualification Approval for Steel Reinforcement | 0 | 100% | 100% | 0
Ready Mixed Concrete | Ready Mixed Concrete |  | 0 |  | 0% | 0
JDH4-02-007-SB-1600 | JDH4-02-007-SB-1600 | Pre-Qualification Submittal for Ready Mixed Concrete | 0 | 100% | 100% | 0
JDH4-02-007-SB-1610 | JDH4-02-007-SB-1610 | Pre-Qualification Approval for Ready Mixed Concrete | 0 | 100% | 100% | 0
Water Proofing | Water Proofing |  | 0 |  | 0% | 0
JDH4-02-007-SB-1620 | JDH4-02-007-SB-1620 | Pre-Qualification Submittal for Water Proofing | 0 | 100% | 100% | 0
JDH4-02-007-SB-1630 | JDH4-02-007-SB-1630 | Pre-Qualification Approval for Water Proofing | 0 | 100% | 100% | 0
Aggregate Base Course | Aggregate Base Course |  | 0 |  | 0% | 0
JDH4-02-007-SB-1000 | JDH4-02-007-SB-1000 | Pre-Qualification Submittal for Aggregate Base Cource | 0 | 100% | 100% | 0
JDH4-02-007-SB-1010 | JDH4-02-007-SB-1010 | Pre-Qualification Approval for Aggregate Base Cource | 0 | 100% | 100% | 0
Bituminous Base & Wearing Course | Bituminous Base & Wearing Course |  | 0 |  | 0% | 0
JDH4-02-007-SB-1020 | JDH4-02-007-SB-1020 | Pre-Qualification Submittal for Bituminous Base & Wearing Cource | 0 | 100% | 100% | 0
JDH4-02-007-SB-1030 | JDH4-02-007-SB-1030 | Pre-Qualification Approval for Bituminous & Wearing Cource | 0 | 100% | 100% | 0
Precast Concrete Kerb | Precast Concrete Kerb |  | 0 |  | 0% | 0
JDH4-02-007-SB-1050 | JDH4-02-007-SB-1050 | Pre-Qualification Approval for Precast Concrete Kerb | 0 | 100% | 100% | 0
JDH4-02-007-SB-1040 | JDH4-02-007-SB-1040 | Pre-Qualification Submittal for Precast Concrete Kerb | 0 | 100% | 100% | 0
Interlocking Block Pavers | Interlocking Block Pavers |  | 0 |  | 0% | 0
JDH4-02-007-SB-1070 | JDH4-02-007-SB-1070 | Pre-Qualification Approval for Interlocking Block Pavers | 0 | 100% | 100% | 0
JDH4-02-007-SB-1060 | JDH4-02-007-SB-1060 | Pre-Qualification Submittal for Interlocking Block Pavers | 0 | 100% | 100% | 0
Pavement Markings | Pavement Markings |  | 0 |  | 0% | 0
JDH4-02-007-SB-1080 | JDH4-02-007-SB-1080 | Pre-Qualification Submittal for Pavement Markings | 0 | 100% | 100% | 0
JDH4-02-007-SB-1090 | JDH4-02-007-SB-1090 | Pre-Qualification Approval for Pavement Markings | 0 | 100% | 100% | 0
Traffic Signs | Traffic Signs |  | 0 |  | 0% | 0
JDH4-02-007-SB-1100 | JDH4-02-007-SB-1100 | Pre-Qualification Submittal for Traffic Signs | 0 | 100% | 100% | 0
JDH4-02-007-SB-1110 | JDH4-02-007-SB-1110 | Pre-Qualification Approval for Traffic Signs | 0 | 100% | 100% | 0
Storm Network | Storm Network |  | 0 |  | 0% | 0
GRP Pipes | GRP Pipes |  | 0 |  | 0% | 0
JDH4-02-007-SB-1260 | JDH4-02-007-SB-1260 | Pre-Qualification Submittal for GRP Pipe | 0 | 100% | 100% | 0
JDH4-02-007-SB-1270 | JDH4-02-007-SB-1270 | Pre-Qualification Approval for GRP Pipe | 0 | 100% | 100% | 0
Catch Basin | Catch Basin |  | 0 |  | 0% | 0
JDH4-02-007-SB-1640 | JDH4-02-007-SB-1640 | Pre-Qualification Submittal for Catch Basin | 0 | 100% | 100% | 0
JDH4-02-007-SB-1650 | JDH4-02-007-SB-1650 | Pre-Qualification Approval for Catch Basin | 0 | 100% | 100% | 0
Inlet Manholes | Inlet Manholes |  | 0 |  | 0% | 0
JDH4-02-007-SB-1280 | JDH4-02-007-SB-1280 | Pre-Qualification Submittal for Inlet Manholes | 0 | 100% | 100% | 0
JDH4-02-007-SB-1290 | JDH4-02-007-SB-1290 | Pre-Qualification Approval for Inlet Manholes | 0 | 100% | 100% | 0
Sanitary Sewerage | Sanitary Sewerage |  | 0 |  | 0% | 0
GRP Pipes | GRP Pipes |  | 0 |  | 0% | 0
JDH4-02-007-SB-1220 | JDH4-02-007-SB-1220 | Pre-Qualification Submittal for GRP Pipe | 0 | 100% | 100% | 0
JDH4-02-007-SB-1230 | JDH4-02-007-SB-1230 | Pre-Qualification Approval for GRP Pipe | 0 | 100% | 100% | 0
Manholes | Manholes |  | 0 |  | 0% | 0
JDH4-02-007-SB-1240 | JDH4-02-007-SB-1240 | Pre-Qualification Submittal for Manholes | 0 | 100% | 100% | 0
JDH4-02-007-SB-1250 | JDH4-02-007-SB-1250 | Pre-Qualification Approval for Manholes | 0 | 100% | 100% | 0
TSE Network | TSE Network |  | 0 |  | 0% | 0
HDPE Pipe (PN 16) | HDPE Pipe (PN 16) |  | 0 |  | 0% | 0
JDH4-02-007-SB-1200 | JDH4-02-007-SB-1200 | Pre-Qualification Submittal for HDPE Pipe (PN 16) | 0 | 100% | 100% | 0
JDH4-02-007-SB-1210 | JDH4-02-007-SB-1210 | Pre-Qualification Approval for HDPE Pipe (PN 16) | 0 | 100% | 100% | 0
Valves / Chambers | Valves / Chambers |  | 0 |  | 0% | 0
JDH4-02-007-SB-1440 | JDH4-02-007-SB-1440 | Pre-Qualification Submittal for Valves / Chambers | 0 | 100% | 100% | 0
JDH4-02-007-SB-1450 | JDH4-02-007-SB-1450 | Pre-Qualification Approval for Valves / Chambers | 0 | 100% | 100% | 0
Risers | Risers |  | 0 |  | 0% | 0
JDH4-02-007-SB-1460 | JDH4-02-007-SB-1460 | Pre-Qualification Submittal for Risers | 0 | 100% | 100% | 0
JDH4-02-007-SB-1470 | JDH4-02-007-SB-1470 | Pre-Qualification Approval for Risers | 0 | 100% | 100% | 0
Potable Water Network | Potable Water Network |  | 0 |  | 0% | 0
HDPE Pipe (PN 16) | HDPE Pipe (PN 16) |  | 0 |  | 0% | 0
JDH4-02-007-SB-1180 | JDH4-02-007-SB-1180 | Pre-Qualification Submittal for HDPE Pipe (PN 16) | 0 | 100% | 100% | 0
JDH4-02-007-SB-1190 | JDH4-02-007-SB-1190 | Pre-Qualification Approval for HDPE Pipe (PN 16) | 0 | 100% | 100% | 0
Valves / Chambers | Valves / Chambers |  | 0 |  | 0% | 0
JDH4-02-007-SB-1420 | JDH4-02-007-SB-1420 | Pre-Qualification Submittal for Valves / Chambers | 0 | 100% | 100% | 0
JDH4-02-007-SB-1430 | JDH4-02-007-SB-1430 | Pre-Qualification Approval for Valves / Chambers | 0 | 100% | 100% | 0
Fire Hydrant | Fire Hydrant |  | 0 |  | 0% | 0
JDH4-02-007-SB-1660 | JDH4-02-007-SB-1660 | Pre-Qualification Submittal for Fire Hydrant | 0 | 100% | 100% | 0
JDH4-02-007-SB-1670 | JDH4-02-007-SB-1670 | Pre-Qualification Approval for Fire Hydrant | 0 | 100% | 100% | 0
Electrical Network | Electrical Network |  | 0 |  | 0% | 0
Pipe for the Duct | Pipe for the Duct |  | 0 |  | 0% | 0
JDH4-02-007-SB-1120 | JDH4-02-007-SB-1120 | Pre-Qualification Submittal for Pipe for the Duct | 0 | 100% | 100% | 0
JDH4-02-007-SB-1130 | JDH4-02-007-SB-1130 | Pre-Qualification Approval for Pipe for the Duct | 0 | 100% | 100% | 0
Low Voltage Cables | Low Voltage Cables |  | 0 |  | 0% | 0
JDH4-02-007-SB-1320 | JDH4-02-007-SB-1320 | Pre-Qualification Submittal for Low Voltage Cables | 0 | 100% | 100% | 0
JDH4-02-007-SB-1330 | JDH4-02-007-SB-1330 | Pre-Qualification Approval for Low Voltage Cables | 0 | 100% | 100% | 0
Earthing System | Earthing System |  | 0 |  | 0% | 0
JDH4-02-007-SB-1160 | JDH4-02-007-SB-1160 | Pre-Qualification Submittal for Earthing System | 0 | 100% | 100% | 0
JDH4-02-007-SB-1170 | JDH4-02-007-SB-1170 | Pre-Qualification Approval for Earthing System | 0 | 100% | 100% | 0
Medium Voltage Cable | Medium Voltage Cable |  | 0 |  | 0% | 0
JDH4-02-007-SB-1300 | JDH4-02-007-SB-1300 | Pre-Qualification Submittal for Medium Voltage Cable | 0 | 100% | 100% | 0
JDH4-02-007-SB-1310 | JDH4-02-007-SB-1310 | Pre-Qualification Approval for Medium Voltage Cable | 0 | 100% | 100% | 0
Low Voltage Distribution Panel | Low Voltage Distribution Panel |  | 0 |  | 0% | 0
JDH4-02-007-SB-1140 | JDH4-02-007-SB-1140 | Pre-Qualification Submittal for Low Voltage Distribution Panel | 0 | 100% | 100% | 0
JDH4-02-007-SB-1150 | JDH4-02-007-SB-1150 | Pre-Qualification Approval for Low Voltage Distribution Panel | 0 | 100% | 100% | 0
Unit Sub Station | Unit Sub Station |  | 0 |  | 0% | 0
JDH4-02-007-SB-1380 | JDH4-02-007-SB-1380 | Pre-Qualification Submittal for Unit Sub Station | 0 | 100% | 100% | 0
JDH4-02-007-SB-1390 | JDH4-02-007-SB-1390 | Pre-Qualification Approval for Unit Sub Station | 0 | 100% | 100% | 0
Ring Main Unit (RMU) | Ring Main Unit (RMU) |  | 0 |  | 0% | 0
JDH4-02-007-SB-1400 | JDH4-02-007-SB-1400 | Pre-Qualification Submittal for Ring main Unit (RMU) | 0 | 100% | 100% | 0
JDH4-02-007-SB-1410 | JDH4-02-007-SB-1410 | Pre-Qualification Approval for Ring main Unit (RMU) | 0 | 100% | 100% | 0
Lighting poles | Lighting poles |  | 0 |  | 0% | 0
JDH4-02-007-SB-1340 | JDH4-02-007-SB-1340 | Pre-Qualification Submittal for Lighting poles | 0 | 100% | 100% | 0
JDH4-02-007-SB-1350 | JDH4-02-007-SB-1350 | Pre-Qualification Approval for Lighting poles | 0 | 100% | 100% | 0
Lighting panels/Feeder Pillers | Lighting panels/Feeder Pillers |  | 0 |  | 0% | 0
JDH4-02-007-SB-1520 | JDH4-02-007-SB-1520 | Pre-Qualification Submittal for Lighting panels/Feeder Pillers | 0 | 100% | 100% | 0
JDH4-02-007-SB-1530 | JDH4-02-007-SB-1530 | Pre-Qualification Approval for Lighting panels/Feeder Pillers | 0 | 100% | 100% | 0
Street Lighting Luminaire | Street Lighting Luminaire |  | 0 |  | 0% | 0
JDH4-02-007-SB-1360 | JDH4-02-007-SB-1360 | Pre-Qualification Submittal for Street Lighting Luminaire | 0 | 100% | 100% | 0
JDH4-02-007-SB-1370 | JDH4-02-007-SB-1370 | Pre-Qualification Approval for Street Lighting Luminaire | 0 | 100% | 100% | 0
Telecommunications | Telecommunications |  | 0 |  | 0% | 0
Pipe for the Duct | Pipe for the Duct |  | 0 |  | 0% | 0
JDH4-02-007-SB-1550 | JDH4-02-007-SB-1550 | Pre-Qualification Approval for Pipe for the Duct | 0 | 100% | 100% | 0
JDH4-02-007-SB-1540 | JDH4-02-007-SB-1540 | Pre-Qualification Submittal for Pipe for the Duct | 0 | 100% | 100% | 0
Sewage Lift Station | Sewage Lift Station |  | 0 |  | 0% | 0
Thermal & Moisture Protection | Thermal & Moisture Protection |  | 0 |  | 0% | 0
JDH4-02-007-SB-1490 | JDH4-02-007-SB-1490 | Pre-Qualification Submittal for Thermal & Moisture Protection | 0 | 100% | 100% | 0
JDH4-02-007-SB-1510 | JDH4-02-007-SB-1510 | Pre-Qualification Approval for Thermal & Moisture Protection | 0 | 100% | 100% | 0
Metals | Metals |  | 0 |  | 0% | 0
JDH4-02-007-SB-1480 | JDH4-02-007-SB-1480 | Pre-Qualification Submittal for Metal | 0 | 100% | 100% | 0
JDH4-02-007-SB-1500 | JDH4-02-007-SB-1500 | Pre-Qualification Approval for Metal | 0 | 100% | 100% | 0
Pumps | Pumps |  | 0 |  | 0% | 0
JDH4-02-007-SB-1560 | JDH4-02-007-SB-1560 | Pre-Qualification Submittal for pumps | 0 | 100% | 100% | 0
JDH4-02-007-SB-1570 | JDH4-02-007-SB-1570 | Pre-Qualification Approval for pumps | 0 | 100% | 100% | 0
Pipes,Fittings & Valves | Pipes,Fittings & Valves |  | 0 |  | 0% | 0
JDH4-02-007-SB-1680 | JDH4-02-007-SB-1680 | Pre-Qualification Submittal for Pipes,Fittings & Valves | 0 | 100% | 100% | 0
JDH4-02-007-SB-1700 | JDH4-02-007-SB-1700 | Pre-Qualification Approval for Pipes,Fittings & Valves | 0 | 100% | 100% | 0
Odours scrubbing system | Odours scrubbing system |  | 0 |  | 0% | 0
JDH4-02-007-SB-1690 | JDH4-02-007-SB-1690 | Pre-Qualification Submittal for Odours Scrubbing System | 0 | 100% | 100% | 0
JDH4-02-007-SB-1710 | JDH4-02-007-SB-1710 | Pre-Qualification Approval for Odours Scrubbing System | 0 | 100% | 100% | 0
Crane | Crane |  | 0 |  | 0% | 0
JDH4-02-007-SB-1720 | JDH4-02-007-SB-1720 | Pre-Qualification Submittal for Crane | 0 | 100% | 100% | 0
JDH4-02-007-SB-1730 | JDH4-02-007-SB-1730 | Pre-Qualification Approval for Crane | 0 | 100% | 100% | 0
Air Vents | Air Vents |  | 0 |  | 0% | 0
JDH4-02-007-SB-1800 | JDH4-02-007-SB-1800 | Pre-Qualification Submittal for Air Vents | 0 | 100% | 100% | 0
JDH4-02-007-SB-1820 | JDH4-02-007-SB-1820 | Pre-Qualification Approval for Air Vents | 0 | 100% | 100% | 0
Screening Container | Screening Container |  | 0 |  | 0% | 0
JDH4-02-007-SB-1740 | JDH4-02-007-SB-1740 | Pre-Qualification Submittal for Screening Container | 0 | 100% | 100% | 0
JDH4-02-007-SB-1760 | JDH4-02-007-SB-1760 | Pre-Qualification Approval for Screening Container | 0 | 100% | 100% | 0
Baffle Plates | Baffle Plates |  | 0 |  | 0% | 0
JDH4-02-007-SB-1810 | JDH4-02-007-SB-1810 | Pre-Qualification Submittal for Baffle plates | 0 | 100% | 100% | 0
JDH4-02-007-SB-1830 | JDH4-02-007-SB-1830 | Pre-Qualification Approval for Baffle plates | 0 | 100% | 100% | 0
Anti-Water Hammer Equipment | Anti-Water Hammer Equipment |  | 0 |  | 0% | 0
JDH4-02-007-SB-1840 | JDH4-02-007-SB-1840 | Pre-Qualification Submittal for Anti-Water Hammer Equipment | 0 | 100% | 100% | 0
JDH4-02-007-SB-1850 | JDH4-02-007-SB-1850 | Pre-Qualification Approval for Anti-Water Hammer Equipment | 0 | 100% | 100% | 0
Air Conditioning and Ventilation | Air Conditioning and Ventilation |  | 0 |  | 0% | 0
JDH4-02-007-SB-1750 | JDH4-02-007-SB-1750 | Pre-Qualification Submittal for Air Conditioning and Ventilation | 0 | 100% | 100% | 0
JDH4-02-007-SB-1770 | JDH4-02-007-SB-1770 | Pre-Qualification Approval for Air Conditioning and Ventilation | 0 | 100% | 100% | 0
Fuel System | Fuel System |  | 0 |  | 0% | 0
JDH4-02-007-SB-1780 | JDH4-02-007-SB-1780 | Pre-Qualification Submittal for Fuel System | 0 | 100% | 100% | 0
JDH4-02-007-SB-1790 | JDH4-02-007-SB-1790 | Pre-Qualification Approval for Fuel System | 0 | 100% | 100% | 0
Fire Fighting System | Fire Fighting System |  | 0 |  | 0% | 0
JDH4-02-007-SB-1920 | JDH4-02-007-SB-1920 | Pre-Qualification Submittal for Fire Fighting System | 0 | 100% | 100% | 0
JDH4-02-007-SB-1930 | JDH4-02-007-SB-1930 | Pre-Qualification Approval for Fire Fighting System | 0 | 100% | 100% | 0
Main Distribution Board /MCC panels | Main Distribution Board /MCC panels |  | 0 |  | 0% | 0
JDH4-02-007-SB-1860 | JDH4-02-007-SB-1860 | Pre-Qualification Submittal for Main Distribution Board/MCC Panels | 0 | 100% | 100% | 0
JDH4-02-007-SB-1870 | JDH4-02-007-SB-1870 | Pre-Qualification Approval for Main Distribution Board/MCC Panels | 0 | 100% | 100% | 0
Final Panel boards | Final Panel boards |  | 0 |  | 0% | 0
JDH4-02-007-SB-1880 | JDH4-02-007-SB-1880 | Pre-Qualification Submittal for Final Panel Boards | 0 | 100% | 100% | 0
JDH4-02-007-SB-1890 | JDH4-02-007-SB-1890 | Pre-Qualification Approval for Final Panel Boards | 0 | 100% | 100% | 0
Local Control Panel/ Monitoring Control Panel | Local Control Panel/ Monitoring Control Panel |  | 0 |  | 0% | 0
JDH4-02-007-SB-1900 | JDH4-02-007-SB-1900 | Pre-Qualification Submittal for Local Control Panel / Monitoring Control Panel | 0 | 100% | 100% | 0
JDH4-02-007-SB-1910 | JDH4-02-007-SB-1910 | Pre-Qualification Approval for Local Control Panel / Monitoring Control Panel | 0 | 100% | 100% | 0
Engine Generators | Engine Generators |  | 0 |  | 0% | 0
JDH4-02-007-SB-2060 | JDH4-02-007-SB-2060 | Pre-Qualification Submittal for Engine Generators | 0 | 100% | 100% | 0
JDH4-02-007-SB-2070 | JDH4-02-007-SB-2070 | Pre-Qualification Approval for Engine Generators | 0 | 100% | 100% | 0
Standby Diesel Generator | Standby Diesel Generator |  | 0 |  | 0% | 0
JDH4-02-007-SB-2040 | JDH4-02-007-SB-2040 | Pre-Qualification Submittal for Standby Diesel Generator | 0 | 100% | 100% | 0
JDH4-02-007-SB-2050 | JDH4-02-007-SB-2050 | Pre-Qualification Approval for Standby Diesel Generator | 0 | 100% | 100% | 0
Power Factor Correction Capacitor Bank | Power Factor Correction Capacitor Bank |  | 0 |  | 0% | 0
JDH4-02-007-SB-2000 | JDH4-02-007-SB-2000 | Pre-Qualification Submittal for Power Factor correction Capacitor Bank | 0 | 100% | 100% | 0
JDH4-02-007-SB-2010 | JDH4-02-007-SB-2010 | Pre-Qualification Approval for Power Factor correction Capacitor Bank | 0 | 100% | 100% | 0
Low-Voltage Electrical Power Conductors and Cables | Low-Voltage Electrical Power Conductors and Cables |  | 0 |  | 0% | 0
JDH4-02-007-SB-2020 | JDH4-02-007-SB-2020 | Pre-Qualification Submittal for Low Voltage Electrical Power Conductors & Cables | 0 | 100% | 100% | 0
JDH4-02-007-SB-2030 | JDH4-02-007-SB-2030 | Pre-Qualification Approval for Low Voltage Electrical Power Conductors & Cables | 0 | 100% | 100% | 0
Low Voltage Feeder Cable | Low Voltage Feeder Cable |  | 0 |  | 0% | 0
JDH4-02-007-SB-1980 | JDH4-02-007-SB-1980 | Pre-Qualification Submittal for Low Voltage Feeder Cable | 0 | 100% | 100% | 0
JDH4-02-007-SB-1990 | JDH4-02-007-SB-1990 | Pre-Qualification Approval for Low Voltage Feeder Cable | 0 | 100% | 100% | 0
Wiring Devices | Wiring Devices |  | 0 |  | 0% | 0
JDH4-02-007-SB-1940 | JDH4-02-007-SB-1940 | Pre-Qualification Submittal for Wiring Devices | 0 | 100% | 100% | 0
JDH4-02-007-SB-1950 | JDH4-02-007-SB-1950 | Pre-Qualification Approval for Wiring Devices | 0 | 100% | 100% | 0
Enclosed Switches and Circuit Breakers | Enclosed Switches and Circuit Breakers |  | 0 |  | 0% | 0
JDH4-02-007-SB-1960 | JDH4-02-007-SB-1960 | Pre-Qualification Submittal for Enclosed Switches and Circuit Breakers | 0 | 100% | 100% | 0
JDH4-02-007-SB-1970 | JDH4-02-007-SB-1970 | Pre-Qualification Approval for Enclosed Switches and Circuit Breakers | 0 | 100% | 100% | 0
Raceways for Electrical Systems | Raceways for Electrical Systems |  | 0 |  | 0% | 0
JDH4-02-007-SB-2100 | JDH4-02-007-SB-2100 | Pre-Qualification Submittal for Raceways for Electrical System | 0 | 100% | 100% | 0
JDH4-02-007-SB-2110 | JDH4-02-007-SB-2110 | Pre-Qualification Approval for Raceways for Electrical System | 0 | 100% | 100% | 0
Electrical Manholes | Electrical Manholes |  | 0 |  | 0% | 0
JDH4-02-007-SB-2140 | JDH4-02-007-SB-2140 | Pre-Qualification Submittal for Electrical Manholes | 0 | 100% | 100% | 0
JDH4-02-007-SB-2150 | JDH4-02-007-SB-2150 | Pre-Qualification Approval for Electrical Manholes | 0 | 100% | 100% | 0
Security System (CCTV System) | Security System (CCTV System) |  | 0 |  | 0% | 0
JDH4-02-007-SB-2080 | JDH4-02-007-SB-2080 | Pre-Qualification Submittal for Security System (CCTV System) | 0 | 100% | 100% | 0
JDH4-02-007-SB-2090 | JDH4-02-007-SB-2090 | Pre-Qualification Approval for Security System (CCTV System) | 0 | 100% | 100% | 0
ICT (Data& telephone System) | ICT (Data& telephone System) |  | 0 |  | 0% | 0
JDH4-02-007-SB-2120 | JDH4-02-007-SB-2120 | Pre-Qualification Submittal for ICT (Data & Telephone System) | 0 | 100% | 100% | 0
JDH4-02-007-SB-2130 | JDH4-02-007-SB-2130 | Pre-Qualification Approval for ICT (Data & Telephone System) | 0 | 100% | 100% | 0
Programmable Logic Controllers | Programmable Logic Controllers |  | 0 |  | 0% | 0
JDH4-02-007-SB-2200 | JDH4-02-007-SB-2200 | Pre-Qualification Submittal for Programmable Logic Controllers | 0 | 100% | 100% | 0
JDH4-02-007-SB-2210 | JDH4-02-007-SB-2210 | Pre-Qualification Approval for Programmable Logic Controllers | 0 | 100% | 100% | 0
Process Control Wiring | Process Control Wiring |  | 0 |  | 0% | 0
JDH4-02-007-SB-2180 | JDH4-02-007-SB-2180 | Pre-Qualification Submittal for Process Control Wiring | 0 | 100% | 100% | 0
JDH4-02-007-SB-2190 | JDH4-02-007-SB-2190 | Pre-Qualification Approval for Process Control Wiring | 0 | 100% | 100% | 0
Instrumentation for Process Systems | Instrumentation for Process Systems |  | 0 |  | 0% | 0
JDH4-02-007-SB-2160 | JDH4-02-007-SB-2160 | Pre-Qualification Submittal for Instrumentation Control Wiring | 0 | 100% | 100% | 0
JDH4-02-007-SB-2170 | JDH4-02-007-SB-2170 | Pre-Qualification Approval for Instrumentation Control Wiring | 0 | 100% | 100% | 0
Material Submittal & Approval | Material Submittal & Approval |  | 1719130.43 |  | 100% | 1719130.43
Road Works - Civil | Road Works - Civil |  | 253642.23 |  | 100% | 253642.23
Steel Reinforcement | Steel Reinforcement |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1590 | JDH4-02-007-MA-1590 | Material Approval for Steel Reinforcement | 28182.47 | 100% | 100% | 28182.47
JDH4-02-007-MA-1580 | JDH4-02-007-MA-1580 | Material Submittal for Steel Reinforcement | 0 | 100% | 100% | 0
Ready Mixed Concrete | Ready Mixed Concrete |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1610 | JDH4-02-007-MA-1610 | Material Approval for Ready Mixed Concrete | 28182.47 | 100% | 100% | 28182.47
JDH4-02-007-MA-1600 | JDH4-02-007-MA-1600 | Material Submittal for Ready Mixed Concrete | 0 | 100% | 100% | 0
Water Proofing | Water Proofing |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1630 | JDH4-02-007-MA-1630 | Material Approval for Water Proofing | 28182.47 | 100% | 100% | 28182.47
JDH4-02-007-MA-1620 | JDH4-02-007-MA-1620 | Material Submittal for Water Proofing | 0 | 100% | 100% | 0
Aggregate Base Course | Aggregate Base Course |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1010 | JDH4-02-007-MA-1010 | Material Approval for Aggregate Base Cource | 28182.47 | 100% | 100% | 28182.47
JDH4-02-007-MA-1000 | JDH4-02-007-MA-1000 | Material Submittal for Aggregate Base Cource | 0 | 100% | 100% | 0
Bituminous Base & Wearing Course | Bituminous Base & Wearing Course |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1030 | JDH4-02-007-MA-1030 | Material Approval for Bituminous & Wearing Cource | 28182.47 | 100% | 100% | 28182.47
JDH4-02-007-MA-1020 | JDH4-02-007-MA-1020 | Material Submittal for Bituminous Base & Wearing Cource | 0 | 100% | 100% | 0
Precast Concrete Kerb | Precast Concrete Kerb |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1040 | JDH4-02-007-MA-1040 | Material Submittal for Precast Concrete Kerb | 0 | 100% | 100% | 0
JDH4-02-007-MA-1050 | JDH4-02-007-MA-1050 | Material Approval for Precast Concrete Kerb | 28182.47 | 100% | 100% | 28182.47
Interlocking Block Pavers | Interlocking Block Pavers |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1060 | JDH4-02-007-MA-1060 | Material Submittal for Interlocking Block Pavers | 0 | 100% | 100% | 0
JDH4-02-007-MA-1070 | JDH4-02-007-MA-1070 | Material Approval for Interlocking Block Pavers | 28182.47 | 100% | 100% | 28182.47
Pavement Markings | Pavement Markings |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1080 | JDH4-02-007-MA-1080 | Material Submittal for Pavement Markings | 0 | 100% | 100% | 0
JDH4-02-007-MA-1090 | JDH4-02-007-MA-1090 | Material Approval for Pavement Markings | 28182.47 | 100% | 100% | 28182.47
Traffic Signs | Traffic Signs |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1100 | JDH4-02-007-MA-1100 | Material Submittal for Traffic Signs | 0 | 100% | 100% | 0
JDH4-02-007-MA-1110 | JDH4-02-007-MA-1110 | Material Approval for Traffic Signs | 28182.47 | 100% | 100% | 28182.47
Storm Network | Storm Network |  | 84547.41 |  | 100% | 84547.41
GRP Pipes | GRP Pipes |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1270 | JDH4-02-007-MA-1270 | Material Approval for GRP Pipe | 28182.47 | 100% | 100% | 28182.47
JDH4-02-007-MA-1250 | JDH4-02-007-MA-1250 | Material Submittal for GRP Pipe | 0 | 100% | 100% | 0
Catch Basin | Catch Basin |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1650 | JDH4-02-007-MA-1650 | Material Approval for Catch Basin | 28182.47 | 100% | 100% | 28182.47
JDH4-02-007-MA-1640 | JDH4-02-007-MA-1640 | Material Submittal for Catch Basin | 0 | 100% | 100% | 0
Inlet Manholes | Inlet Manholes |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1290 | JDH4-02-007-MA-1290 | Material Approval for Inlet Manholes | 28182.47 | 100% | 100% | 28182.47
JDH4-02-007-MA-1280 | JDH4-02-007-MA-1280 | Material Submittal for Inlet Manholes | 0 | 100% | 100% | 0
Sanitary Sewerage | Sanitary Sewerage |  | 56364.94 |  | 100% | 56364.94
GRP Pipes | GRP Pipes |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1230 | JDH4-02-007-MA-1230 | Material Approval for GRP Pipe | 28182.47 | 100% | 100% | 28182.47
JDH4-02-007-MA-1220 | JDH4-02-007-MA-1220 | Material Submittal for GRP Pipe | 0 | 100% | 100% | 0
Manholes | Manholes |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1260 | JDH4-02-007-MA-1260 | Material Approval for Manholes | 28182.47 | 100% | 100% | 28182.47
JDH4-02-007-MA-1240 | JDH4-02-007-MA-1240 | Material Submittal for Manholes | 0 | 100% | 100% | 0
TSE Network | TSE Network |  | 84547.41 |  | 100% | 84547.41
HDPE Pipe (PN 16) | HDPE Pipe (PN 16) |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1200 | JDH4-02-007-MA-1200 | Material Submittal for HDPE Pipe (PN 16) | 0 | 100% | 100% | 0
JDH4-02-007-MA-1210 | JDH4-02-007-MA-1210 | Material Approval for HDPE Pipe (PN 16) | 28182.47 | 100% | 100% | 28182.47
Valves / Chambers | Valves / Chambers |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1440 | JDH4-02-007-MA-1440 | Material Submittal for Valves / Chambers | 0 | 100% | 100% | 0
JDH4-02-007-MA-1450 | JDH4-02-007-MA-1450 | Material Approval for Valves / Chambers | 28182.47 | 100% | 100% | 28182.47
Risers | Risers |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1460 | JDH4-02-007-MA-1460 | Material Submittal for Risers | 0 | 100% | 100% | 0
JDH4-02-007-MA-1470 | JDH4-02-007-MA-1470 | Material Approval for Risers | 28182.47 | 100% | 100% | 28182.47
Potable Water Network | Potable Water Network |  | 84547.41 |  | 100% | 84547.41
HDPE Pipe (PN 16) | HDPE Pipe (PN 16) |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1180 | JDH4-02-007-MA-1180 | Material Submittal for HDPE Pipe (PN 16) | 0 | 100% | 100% | 0
JDH4-02-007-MA-1190 | JDH4-02-007-MA-1190 | Material Approval for HDPE Pipe (PN 16) | 28182.47 | 100% | 100% | 28182.47
Valves / Chambers | Valves / Chambers |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1420 | JDH4-02-007-MA-1420 | Material Submittal for Valves / Chambers | 0 | 100% | 100% | 0
JDH4-02-007-MA-1430 | JDH4-02-007-MA-1430 | Material Approval for Valves / Chambers | 28182.47 | 100% | 100% | 28182.47
Fire Hydrant | Fire Hydrant |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1660 | JDH4-02-007-MA-1660 | Material Submittal for Fire Hydrant | 0 | 100% | 100% | 0
JDH4-02-007-MA-1670 | JDH4-02-007-MA-1670 | Material Approval for Fire Hydrant | 28182.47 | 100% | 100% | 28182.47
Electrical Network | Electrical Network |  | 281824.7 |  | 100% | 281824.7
Pipe for the Duct | Pipe for the Duct |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1120 | JDH4-02-007-MA-1120 | Material Submittal for Pipe for the Duct | 0 | 100% | 100% | 0
JDH4-02-007-MA-1130 | JDH4-02-007-MA-1130 | Material Approval for Pipe for the Duct By SEC | 28182.47 | 100% | 100% | 28182.47
Low Voltage Cables | Low Voltage Cables |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1330 | JDH4-02-007-MA-1330 | Material Approval for Low Voltage Cables By SEC | 28182.47 | 100% | 100% | 28182.47
JDH4-02-007-MA-1320 | JDH4-02-007-MA-1320 | Material Submittal for Low Voltage Cables | 0 | 100% | 100% | 0
Earthing System | Earthing System |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1160 | JDH4-02-007-MA-1160 | Material Submittal for Earthing System | 0 | 100% | 100% | 0
JDH4-02-007-MA-1170 | JDH4-02-007-MA-1170 | Material Approval for Earthing System By SEC | 28182.47 | 100% | 100% | 28182.47
Medium Voltage Cable | Medium Voltage Cable |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1300 | JDH4-02-007-MA-1300 | Material Submittal for Medium Voltage Cable | 0 | 100% | 100% | 0
JDH4-02-007-MA-1310 | JDH4-02-007-MA-1310 | Material Approval for Medium Voltage Cable By SEC | 28182.47 | 100% | 100% | 28182.47
Low Voltage Distribution Panel | Low Voltage Distribution Panel |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1140 | JDH4-02-007-MA-1140 | Material Submittal for Low Voltage Distribution Panel | 0 | 100% | 100% | 0
JDH4-02-007-MA-1150 | JDH4-02-007-MA-1150 | Material Approval for Low Voltage Distribution Panel By SEC | 28182.47 | 100% | 100% | 28182.47
Unit Sub Station | Unit Sub Station |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1380 | JDH4-02-007-MA-1380 | Material Submittal for Unit Sub Station | 0 | 100% | 100% | 0
JDH4-02-007-MA-1390 | JDH4-02-007-MA-1390 | Material Approval for Unit Sub Station By SEC | 28182.47 | 100% | 100% | 28182.47
Ring Main Unit (RMU) | Ring Main Unit (RMU) |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1400 | JDH4-02-007-MA-1400 | Material Submittal for Ring main Unit (RMU) | 0 | 100% | 100% | 0
JDH4-02-007-MA-1410 | JDH4-02-007-MA-1410 | Material Approval for Ring main Unit (RMU) By SEC | 28182.47 | 100% | 100% | 28182.47
Lighting poles | Lighting poles |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1340 | JDH4-02-007-MA-1340 | Material Submittal for Lighting poles | 0 | 100% | 100% | 0
JDH4-02-007-MA-1350 | JDH4-02-007-MA-1350 | Material Approval for Lighting poles By SEC | 28182.47 | 100% | 100% | 28182.47
Lighting panels/Feeder Pillers | Lighting panels/Feeder Pillers |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1515 | JDH4-02-007-MA-1515 | Material Submittal for Lighting panels/Feeder Pillers By SEC | 0 | 100% | 100% | 0
JDH4-02-007-MA-1520 | JDH4-02-007-MA-1520 | Material Approval for Lighting panels/Feeder Pillers | 28182.47 | 100% | 100% | 28182.47
Street Lighting Luminaire | Street Lighting Luminaire |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1360 | JDH4-02-007-MA-1360 | Material Submittal for Street Lighting Luminaire | 0 | 100% | 100% | 0
JDH4-02-007-MA-1370 | JDH4-02-007-MA-1370 | Material Approval for Street Lighting Luminaire By SEC | 28182.47 | 100% | 100% | 28182.47
Telecommunications | Telecommunications |  | 28182.47 |  | 100% | 28182.47
Pipe for the Duct | Pipe for the Duct |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1550 | JDH4-02-007-MA-1550 | Material Approval for Pipe for the Duct | 28182.47 | 100% | 100% | 28182.47
JDH4-02-007-MA-1540 | JDH4-02-007-MA-1540 | Material Submittal for Pipe for the Duct | 0 | 100% | 100% | 0
Sewage Lift Station | Sewage Lift Station |  | 845473.86 |  | 100% | 845473.86
Thermal & Moisture Protection | Thermal & Moisture Protection |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1490 | JDH4-02-007-MA-1490 | Material Submittal for Thermal & Moisture Protection | 0 | 100% | 100% | 0
JDH4-02-007-MA-1510 | JDH4-02-007-MA-1510 | Material Approval for Thermal & Moisture Protection | 28182.47 | 100% | 100% | 28182.47
Metals | Metals |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1480 | JDH4-02-007-MA-1480 | Material Submittal for Metal | 0 | 100% | 100% | 0
JDH4-02-007-MA-1500 | JDH4-02-007-MA-1500 | Material Approval for Metal | 28182.47 | 100% | 100% | 28182.47
Pumps | Pumps |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1560 | JDH4-02-007-MA-1560 | Material Submittal for pumps | 0 | 100% | 100% | 0
JDH4-02-007-MA-1570 | JDH4-02-007-MA-1570 | Material Approval for pumps | 28182.47 | 100% | 100% | 28182.47
Pipes,Fittings & Valves | Pipes,Fittings & Valves |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1680 | JDH4-02-007-MA-1680 | Material Submittal for Pipes,Fittings & Valves | 0 | 100% | 100% | 0
JDH4-02-007-MA-1700 | JDH4-02-007-MA-1700 | Material Approval for Pipes,Fittings & Valves | 28182.47 | 100% | 100% | 28182.47
Odours scrubbing system | Odours scrubbing system |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1690 | JDH4-02-007-MA-1690 | Material Submittal for Odours Scrubbing System | 0 | 100% | 100% | 0
JDH4-02-007-MA-1710 | JDH4-02-007-MA-1710 | Material Approval for Odours Scrubbing System | 28182.47 | 100% | 100% | 28182.47
Crane | Crane |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1720 | JDH4-02-007-MA-1720 | Material Submittal for Crane | 0 | 100% | 100% | 0
JDH4-02-007-MA-1730 | JDH4-02-007-MA-1730 | Material Approval for Crane | 28182.47 | 100% | 100% | 28182.47
Air Vents | Air Vents |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1800 | JDH4-02-007-MA-1800 | Material Submittal for Air Vents | 0 | 100% | 100% | 0
JDH4-02-007-MA-1820 | JDH4-02-007-MA-1820 | Material Approval for Air Vents | 28182.47 | 100% | 100% | 28182.47
Screening Container | Screening Container |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1740 | JDH4-02-007-MA-1740 | Material Submittal for Screening Container | 0 | 100% | 100% | 0
JDH4-02-007-MA-1760 | JDH4-02-007-MA-1760 | Material Approval for Screening Container | 28182.47 | 100% | 100% | 28182.47
Baffle Plates | Baffle Plates |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1810 | JDH4-02-007-MA-1810 | Material Submittal for Baffle plates | 0 | 100% | 100% | 0
JDH4-02-007-MA-1830 | JDH4-02-007-MA-1830 | Material Approval for Baffle plates | 28182.47 | 100% | 100% | 28182.47
Anti-Water Hammer Equipment | Anti-Water Hammer Equipment |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1840 | JDH4-02-007-MA-1840 | Material Submittal for Anti-Water Hammer Equipment | 0 | 100% | 100% | 0
JDH4-02-007-MA-1850 | JDH4-02-007-MA-1850 | Material Approval for Anti-Water Hammer Equipment | 28182.47 | 100% | 100% | 28182.47
Air Conditioning and Ventilation | Air Conditioning and Ventilation |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1750 | JDH4-02-007-MA-1750 | Material Submittal for Air Conditioning and Ventilation | 0 | 100% | 100% | 0
JDH4-02-007-MA-1770 | JDH4-02-007-MA-1770 | Material Approval for Air Conditioning and Ventilation | 28182.47 | 100% | 100% | 28182.47
Fuel System | Fuel System |  | 28182.23 |  | 100% | 28182.23
JDH4-02-007-MA-1780 | JDH4-02-007-MA-1780 | Material Submittal for Fuel System | 0 | 100% | 100% | 0
JDH4-02-007-MA-1790 | JDH4-02-007-MA-1790 | Material Approval for Fuel System(Completed) | 14091.23 | 100% | 100% | 14091.23
JDH4-02-007-MA-1790R | JDH4-02-007-MA-1790R | Material Approval for Fuel System | 14091 | 100% | 100% | 14091
Fire Fighting System | Fire Fighting System |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1920 | JDH4-02-007-MA-1920 | Material Submittal for Fire Fighting System | 0 | 100% | 100% | 0
JDH4-02-007-MA-1930 | JDH4-02-007-MA-1930 | Material Approval for Fire Fighting System | 28182.47 | 100% | 100% | 28182.47
Main Distribution Board /MCC panels | Main Distribution Board /MCC panels |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1860 | JDH4-02-007-MA-1860 | Material Submittal for Main Distribution Board/MCC Panels | 0 | 100% | 100% | 0
JDH4-02-007-MA-1870 | JDH4-02-007-MA-1870 | Material Approval for Main Distribution Board/MCC Panels | 28182.47 | 100% | 100% | 28182.47
Final Panel boards | Final Panel boards |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1880 | JDH4-02-007-MA-1880 | Material Submittal for Final Panel Boards | 0 | 100% | 100% | 0
JDH4-02-007-MA-1890 | JDH4-02-007-MA-1890 | Material Approval for Final Panel Boards | 28182.47 | 100% | 100% | 28182.47
Local Control Panel/ Monitoring Control Panel | Local Control Panel/ Monitoring Control Panel |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1900 | JDH4-02-007-MA-1900 | Material Submittal for Local Control Panel / Monitoring Control Panel | 0 | 100% | 100% | 0
JDH4-02-007-MA-1910 | JDH4-02-007-MA-1910 | Material Approval for Local Control Panel / Monitoring Control Panel | 28182.47 | 100% | 100% | 28182.47
Engine Generators | Engine Generators |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-2060 | JDH4-02-007-MA-2060 | Material Submittal for Engine Generators | 0 | 100% | 100% | 0
JDH4-02-007-MA-2070 | JDH4-02-007-MA-2070 | Material Approval for Engine Generators | 28182.47 | 100% | 100% | 28182.47
Standby Diesel Generator | Standby Diesel Generator |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-2040 | JDH4-02-007-MA-2040 | Material Submittal for Standby Diesel Generator | 0 | 100% | 100% | 0
JDH4-02-007-MA-2050 | JDH4-02-007-MA-2050 | Material Approval for Standby Diesel Generator | 28182.47 | 100% | 100% | 28182.47
Power Factor Correction Capacitor Bank | Power Factor Correction Capacitor Bank |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-2000 | JDH4-02-007-MA-2000 | Material Submittal for Power Factor correction Capacitor Bank | 0 | 100% | 100% | 0
JDH4-02-007-MA-2010 | JDH4-02-007-MA-2010 | Material Approval for Power Factor correction Capacitor Bank | 28182.47 | 100% | 100% | 28182.47
Low-Voltage Electrical Power Conductors and Cables | Low-Voltage Electrical Power Conductors and Cables |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-2020 | JDH4-02-007-MA-2020 | Material Submittal for Low Voltage Electrical Power Conductors & Cables | 0 | 100% | 100% | 0
JDH4-02-007-MA-2030 | JDH4-02-007-MA-2030 | Material Approval for Low Voltage Electrical Power Conductors & Cables | 28182.47 | 100% | 100% | 28182.47
Low Voltage Feeder Cable | Low Voltage Feeder Cable |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1980 | JDH4-02-007-MA-1980 | Material Submittal for Low Voltage Feeder Cable | 0 | 100% | 100% | 0
JDH4-02-007-MA-1990 | JDH4-02-007-MA-1990 | Material Approval for Low Voltage Feeder Cable | 28182.47 | 100% | 100% | 28182.47
Wiring Devices | Wiring Devices |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1940 | JDH4-02-007-MA-1940 | Material Submittal for Wiring Devices | 0 | 100% | 100% | 0
JDH4-02-007-MA-1950 | JDH4-02-007-MA-1950 | Material Approval for Wiring Devices | 28182.47 | 100% | 100% | 28182.47
Enclosed Switches and Circuit Breakers | Enclosed Switches and Circuit Breakers |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1960 | JDH4-02-007-MA-1960 | Material Submittal for Enclosed Switches and Circuit Breakers | 0 | 100% | 100% | 0
JDH4-02-007-MA-1970 | JDH4-02-007-MA-1970 | Material Approval for Enclosed Switches and Circuit Breakers | 28182.47 | 100% | 100% | 28182.47
Raceways for Electrical Systems | Raceways for Electrical Systems |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-2100 | JDH4-02-007-MA-2100 | Material Submittal for Raceways for Electrical System | 0 | 100% | 100% | 0
JDH4-02-007-MA-2110 | JDH4-02-007-MA-2110 | Material Approval for Raceways for Electrical System | 28182.47 | 100% | 100% | 28182.47
Electrical Manholes | Electrical Manholes |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-2140 | JDH4-02-007-MA-2140 | Material Submittal for Electrical Manholes | 0 | 100% | 100% | 0
JDH4-02-007-MA-2150 | JDH4-02-007-MA-2150 | Material Approval for Electrical Manholes | 28182.47 | 100% | 100% | 28182.47
Security System (CCTV System) | Security System (CCTV System) |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-2080 | JDH4-02-007-MA-2080 | Material Submittal for Security System (CCTV System) | 0 | 100% | 100% | 0
JDH4-02-007-MA-2090 | JDH4-02-007-MA-2090 | Material Approval for Security System (CCTV System) | 28182.47 | 100% | 100% | 28182.47
ICT (Data& telephone System) | ICT (Data& telephone System) |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-2120 | JDH4-02-007-MA-2120 | Material Submittal for ICT (Data & Telephone System) | 0 | 100% | 100% | 0
JDH4-02-007-MA-2130 | JDH4-02-007-MA-2130 | Material Approval for ICT (Data & Telephone System) | 28182.47 | 100% | 100% | 28182.47
Programmable Logic Controllers | Programmable Logic Controllers |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-2200 | JDH4-02-007-MA-2200 | Material Submittal for Programmable Logic Controllers | 0 | 100% | 100% | 0
JDH4-02-007-MA-2210 | JDH4-02-007-MA-2210 | Material Approval for Programmable Logic Controllers | 28182.47 | 100% | 100% | 28182.47
Process Control Wiring | Process Control Wiring |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-2180 | JDH4-02-007-MA-2180 | Material Submittal for Process Control Wiring | 0 | 100% | 100% | 0
JDH4-02-007-MA-2190 | JDH4-02-007-MA-2190 | Material Approval for Process Control Wiring | 28182.47 | 100% | 100% | 28182.47
Instrumentation for Process Systems | Instrumentation for Process Systems |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-2160 | JDH4-02-007-MA-2160 | Material Submittal for Instrumentation Control Wiring | 0 | 100% | 100% | 0
JDH4-02-007-MA-2170 | JDH4-02-007-MA-2170 | Material Approval for Instrumentation Control Wiring | 28182.47 | 100% | 100% | 28182.47
Procurement | Procurement |  | 11460869.58 |  | 100% | 11460869.58
Short Lead Item | Short Lead Item |  | 5193206.43 |  | 100% | 5193206.43
Road Works - Civil | Road Works - Civil |  | 1611684.79 |  | 100% | 1611684.79
Steel Reinforcement | Steel Reinforcement |  | 179076.06 |  | 100% | 179076.06
JDH4-02-007-PR-1300 | JDH4-02-007-PR-1300 | PO for Steel Reinforcement | 0 | 100% | 100% | 0
JDH4-02-007-PR-1310 | JDH4-02-007-PR-1310 | Material Fabrication for Steel Reinforcement | 0 | 100% | 100% | 0
JDH4-02-007-PR-1319 | JDH4-02-007-PR-1319 | Material Delivery for Steel Reinforcement - Stage 1(Completed) | 35815.22 | 100% | 100% | 35815.22
JDH4-02-007-PR-1319R | JDH4-02-007-PR-1319R | Material Delivery for Steel Reinforcement - Stage 1 | 53722.79 | 100% | 100% | 53722.79
JDH4-02-007-PR-1320 | JDH4-02-007-PR-1320 | Material Delivery for Steel Reinforcement - Stage 2 | 89538.05 | 100% | 100% | 89538.05
Ready Mixed Concrete | Ready Mixed Concrete |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1330 | JDH4-02-007-PR-1330 | PO for Ready Mixed Concrete | 0 | 100% | 100% | 0
JDH4-02-007-PR-1340 | JDH4-02-007-PR-1340 | Material Delivery for Ready Mixed Concrete | 179076.09 | 100% | 100% | 179076.09
Water Proofing | Water Proofing |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1350 | JDH4-02-007-PR-1350 | PO for Water Proofing | 0 | 100% | 100% | 0
JDH4-02-007-PR-1360 | JDH4-02-007-PR-1360 | Material Fabrication for Water Proofing | 0 | 100% | 100% | 0
JDH4-02-007-PR-1370 | JDH4-02-007-PR-1370 | Material Delivery for Water Proofing | 179076.09 | 100% | 100% | 179076.09
Aggregate Base Course | Aggregate Base Course |  | 179076.1 |  | 100% | 179076.1
JDH4-02-007-PR-1380 | JDH4-02-007-PR-1380 | PO for Aggregate Base Course | 0 | 100% | 100% | 0
JDH4-02-007-PR-1389 | JDH4-02-007-PR-1389 | Material Delivery for Aggregate Base Course - Stage 1 | 89538.05 | 100% | 100% | 89538.05
JDH4-02-007-PR-1390 | JDH4-02-007-PR-1390 | Material Delivery for Aggregate Base Course - Stage 2 | 89538.05 | 100% | 100% | 89538.05
Bituminous Base & Wearing Course | Bituminous Base & Wearing Course |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1400 | JDH4-02-007-PR-1400 | PO for Bituminous Base & Wearing Cource | 0 | 100% | 100% | 0
JDH4-02-007-PR-1410 | JDH4-02-007-PR-1410 | Material Delivery to the Site | 179076.09 | 100% | 100% | 179076.09
Precast Concrete Kerb | Precast Concrete Kerb |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1420 | JDH4-02-007-PR-1420 | PO for Precast Concrete Kerb | 0 | 100% | 100% | 0
JDH4-02-007-PR-1430 | JDH4-02-007-PR-1430 | Material Fabrication for Precast Concrete Kerb | 0 | 100% | 100% | 0
JDH4-02-007-PR-1440 | JDH4-02-007-PR-1440 | Material Delivery for Precast Concrete Kerb | 179076.09 | 100% | 100% | 179076.09
Interlocking Block Pavers | Interlocking Block Pavers |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1450 | JDH4-02-007-PR-1450 | PO for Interlocking Block Pavers | 0 | 100% | 100% | 0
JDH4-02-007-PR-1460 | JDH4-02-007-PR-1460 | Material Fabrication for Interlocking Block Pavers | 0 | 100% | 100% | 0
JDH4-02-007-PR-1470 | JDH4-02-007-PR-1470 | Material Delivery for Interlocking Block Pavers | 179076.09 | 100% | 100% | 179076.09
Pavement Markings | Pavement Markings |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1480 | JDH4-02-007-PR-1480 | PO for Pavement Markings | 0 | 100% | 100% | 0
JDH4-02-007-PR-1500 | JDH4-02-007-PR-1500 | Material Delivery for Pavement Markings | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-1490 | JDH4-02-007-PR-1490 | Material Fabrication for Pavement Markings | 0 | 100% | 100% | 0
Traffic Signs | Traffic Signs |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1510 | JDH4-02-007-PR-1510 | PO for Traffic Signs | 0 | 100% | 100% | 0
JDH4-02-007-PR-1520 | JDH4-02-007-PR-1520 | Material Fabrication for Traffic Signs | 0 | 100% | 100% | 0
JDH4-02-007-PR-1530 | JDH4-02-007-PR-1530 | Material Delivery for Traffic Signs | 179076.09 | 100% | 100% | 179076.09
Stormwater Utilities | Stormwater Utilities |  | 716304.35 |  | 100% | 716304.35
Catch Basins | Catch Basins |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1720 | JDH4-02-007-PR-1720 | PO for Catch Basins | 0 | 100% | 100% | 0
JDH4-02-007-PR-1729 | JDH4-02-007-PR-1729 | Material Fabrication for Catch Basins - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1740 | JDH4-02-007-PR-1740 | Material Delivery for Catch Basins(Completed) | 53722.83 | 100% | 100% | 53722.83
JDH4-02-007-PR-1740R | JDH4-02-007-PR-1740R | Material Delivery for Catch Basins | 125353.26 | 100% | 100% | 125353.26
JDH4-02-007-PR-1729R | JDH4-02-007-PR-1729R | Material Fabrication for Catch Basins - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1730 | JDH4-02-007-PR-1730 | Material Fabrication for Catch Basins - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1830 | JDH4-02-007-PR-1830 | Staging Time for Catch Basins | 0 | 100% | 100% | 0
GRP Pipes | GRP Pipes |  | 358152.18 |  | 100% | 358152.18
JDH4-02-007-PR-1660 | JDH4-02-007-PR-1660 | PO for GRP Pipes | 0 | 100% | 100% | 0
JDH4-02-007-PR-1670 | JDH4-02-007-PR-1670 | Material Fabrication for GRP Pipes | 0 | 100% | 100% | 0
JDH4-02-007-PR-1680 | JDH4-02-007-PR-1680 | Material Delivery for GRP Pipes(Completed) | 196983.7 | 100% | 100% | 196983.7
JDH4-02-007-PR-1670R | JDH4-02-007-PR-1670R | Material Fabrication for GRP Pipes | 0 | 100% | 100% | 0
JDH4-02-007-PR-1680R | JDH4-02-007-PR-1680R | Material Delivery for GRP Pipes | 161168.48 | 100% | 100% | 161168.48
Inlet Manholes | Inlet Manholes |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1690 | JDH4-02-007-PR-1690 | PO for Inlet Manholes | 0 | 100% | 100% | 0
JDH4-02-007-PR-1700 | JDH4-02-007-PR-1700 | Material Fabrication for Inlet Manholes | 0 | 100% | 100% | 0
JDH4-02-007-PR-1710 | JDH4-02-007-PR-1710 | Material Delivery for Inlet Manholes(Completed) | 71630.44 | 100% | 100% | 71630.44
JDH4-02-007-PR-1700R | JDH4-02-007-PR-1700R | Material Fabrication for Inlet Manholes | 0 | 100% | 100% | 0
JDH4-02-007-PR-1710R | JDH4-02-007-PR-1710R | Material Delivery for Inlet Manholes | 107445.65 | 100% | 100% | 107445.65
Sanitary Sewerage | Sanitary Sewerage |  | 716304.35 |  | 100% | 716304.35
GRP Pipes | GRP Pipes |  | 358152.18 |  | 100% | 358152.18
JDH4-02-007-PR-1600 | JDH4-02-007-PR-1600 | PO for GRP Pipes | 0 | 100% | 100% | 0
JDH4-02-007-PR-1610 | JDH4-02-007-PR-1610 | Material Fabrication for GRP Pipes | 0 | 100% | 100% | 0
JDH4-02-007-PR-1620 | JDH4-02-007-PR-1620 | Material Delivery for GRP Pipes(Completed) | 17907.61 | 100% | 100% | 17907.61
JDH4-02-007-PR-1610R | JDH4-02-007-PR-1610R | Material Fabrication for GRP Pipes | 0 | 100% | 100% | 0
JDH4-02-007-PR-1620R | JDH4-02-007-PR-1620R | Material Delivery for GRP Pipes | 340244.57 | 100% | 100% | 340244.57
Manholes | Manholes |  | 358152.17 |  | 100% | 358152.17
JDH4-02-007-PR-1630 | JDH4-02-007-PR-1630 | PO for Manholes | 0 | 100% | 100% | 0
JDH4-02-007-PR-1638 | JDH4-02-007-PR-1638 | Material Fabrication for Manholes - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1650 | JDH4-02-007-PR-1650 | Material Delivery for Manholes(Completed) | 161168.48 | 100% | 100% | 161168.48
JDH4-02-007-PR-1650R | JDH4-02-007-PR-1650R | Material Delivery for Manholes | 196983.69 | 100% | 100% | 196983.69
JDH4-02-007-PR-1639 | JDH4-02-007-PR-1639 | Material Fabrication for Manholes - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1640 | JDH4-02-007-PR-1640 | Material Fabrication for Manholes - Stage 3 | 0 | 100% | 100% | 0
TSE Network | TSE Network |  | 179076.09 |  | 100% | 179076.09
HDPE Pipe (PN 16) | HDPE Pipe (PN 16) |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1570 | JDH4-02-007-PR-1570 | PO for HDPE Pipe (PN 16) | 0 | 100% | 100% | 0
JDH4-02-007-PR-1580 | JDH4-02-007-PR-1580 | Material Fabrication for HDPE Pipe (PN 16) | 0 | 100% | 100% | 0
JDH4-02-007-PR-1590 | JDH4-02-007-PR-1590 | Material Delivery for HDPE Pipe (PN 16)(Completed) | 164750 | 100% | 100% | 164750
JDH4-02-007-PR-1580R | JDH4-02-007-PR-1580R | Material Fabrication for HDPE Pipe (PN 16) | 0 | 100% | 100% | 0
JDH4-02-007-PR-1590R | JDH4-02-007-PR-1590R | Material Delivery for HDPE Pipe (PN 16) | 14326.09 | 100% | 100% | 14326.09
Potable Water Network | Potable Water Network |  | 179076.09 |  | 100% | 179076.09
HDPE Pipe (PN 16) | HDPE Pipe (PN 16) |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1540 | JDH4-02-007-PR-1540 | PO for HDPE Pipe (PN 16) | 0 | 100% | 100% | 0
JDH4-02-007-PR-1550 | JDH4-02-007-PR-1550 | Material Fabrication for HDPE Pipe (PN 16) | 0 | 100% | 100% | 0
JDH4-02-007-PR-1560 | JDH4-02-007-PR-1560 | Material Delivery for HDPE Pipe (PN 16)(Completed) | 148633.15 | 100% | 100% | 148633.15
JDH4-02-007-PR-1550R | JDH4-02-007-PR-1550R | Material Fabrication for HDPE Pipe (PN 16) | 0 | 100% | 100% | 0
JDH4-02-007-PR-1560R | JDH4-02-007-PR-1560R | Material Delivery for HDPE Pipe (PN 16) | 30442.94 | 100% | 100% | 30442.94
Electrical Network | Electrical Network |  | 358152.04 |  | 100% | 358152.04
Pipe for the Duct | Pipe for the Duct |  | 179075.95 |  | 100% | 179075.95
JDH4-02-007-PR-1190 | JDH4-02-007-PR-1190 | PO for Pipe for Duct | 0 | 100% | 100% | 0
JDH4-02-007-PR-1210 | JDH4-02-007-PR-1210 | Material Fabrication for Pipe for Duct | 0 | 100% | 100% | 0
JDH4-02-007-PR-1230 | JDH4-02-007-PR-1230 | Material Delivery for Pipe for Duct | 179075.95 | 100% | 100% | 179075.95
Earthing System | Earthing System |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1180 | JDH4-02-007-PR-1180 | PO for Earthing System | 0 | 100% | 100% | 0
JDH4-02-007-PR-1200 | JDH4-02-007-PR-1200 | Material Fabrication for Earthing System | 0 | 100% | 100% | 0
JDH4-02-007-PR-1220 | JDH4-02-007-PR-1220 | Material Delivery for Earthing System | 179076.09 | 100% | 100% | 179076.09
Telecommunications | Telecommunications |  | 179076.09 |  | 100% | 179076.09
Pipe for the Duct | Pipe for the Duct |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2260 | JDH4-02-007-PR-2260 | PO for Pipe for Duct | 0 | 100% | 100% | 0
JDH4-02-007-PR-2270 | JDH4-02-007-PR-2270 | Material Fabrication for Pipe for Duct | 0 | 100% | 100% | 0
JDH4-02-007-PR-2280 | JDH4-02-007-PR-2280 | Material Delivery for Pipe for Duct(Completed) | 71630.44 | 100% | 100% | 71630.44
JDH4-02-007-PR-2270R | JDH4-02-007-PR-2270R | Material Fabrication for Pipe for Duct | 0 | 100% | 100% | 0
JDH4-02-007-PR-2280R | JDH4-02-007-PR-2280R | Material Delivery for Pipe for Duct | 107445.65 | 100% | 100% | 107445.65
Sewage Lift Station | Sewage Lift Station |  | 1253532.63 |  | 100% | 1253532.63
Thermal & Moisture Protection | Thermal & Moisture Protection |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2350 | JDH4-02-007-PR-2350 | PO for Thermal & Moisture Protection | 0 | 100% | 100% | 0
JDH4-02-007-PR-2358 | JDH4-02-007-PR-2358 | Material Fabrication for Thermal & Moisture Protection - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2359 | JDH4-02-007-PR-2359 | Material Fabrication for Thermal & Moisture Protection - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2360 | JDH4-02-007-PR-2360 | Material Fabrication for Thermal & Moisture Protection - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2369 | JDH4-02-007-PR-2369 | Material Delivery for Thermal & Moisture Protection - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2370 | JDH4-02-007-PR-2370 | Material Delivery for Thermal & Moisture Protection - Stage 2 | 179076.09 | 100% | 100% | 179076.09
Metals | Metals |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1840 | JDH4-02-007-PR-1840 | PO for Metal | 0 | 100% | 100% | 0
JDH4-02-007-PR-1848 | JDH4-02-007-PR-1848 | Material Fabrication for Metal - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1849 | JDH4-02-007-PR-1849 | Material Fabrication for Metal - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1850 | JDH4-02-007-PR-1850 | Material Fabrication for Metal - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1860 | JDH4-02-007-PR-1860 | Material Delivery for Metal - Stage 2 | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-1859 | JDH4-02-007-PR-1859 | Material Delivery for Metal - Stage 1 | 0 | 100% | 100% | 0
Pipes | Pipes |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2290 | JDH4-02-007-PR-2290 | PO for Pipes | 0 | 100% | 100% | 0
JDH4-02-007-PR-2300 | JDH4-02-007-PR-2300 | Material Fabrication for Pipes | 0 | 100% | 100% | 0
JDH4-02-007-PR-2310 | JDH4-02-007-PR-2310 | Material Delivery for Pipes | 179076.09 | 100% | 100% | 179076.09
Air Conditioning and Ventilation | Air Conditioning and Ventilation |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2380 | JDH4-02-007-PR-2380 | PO for Air Conditioning and Ventilation | 0 | 100% | 100% | 0
JDH4-02-007-PR-2390 | JDH4-02-007-PR-2390 | Material Fabrication for Air Conditioning and Ventilation | 0 | 100% | 100% | 0
JDH4-02-007-PR-2400 | JDH4-02-007-PR-2400 | Material Delivery for Air Conditioning and Ventilation | 179076.09 | 100% | 100% | 179076.09
Fuel System | Fuel System |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1870 | JDH4-02-007-PR-1870 | PO forFabrication for Fuel System | 0 | 100% | 100% | 0
JDH4-02-007-PR-1880 | JDH4-02-007-PR-1880 | Material Fabrication for Fuel System | 0 | 100% | 100% | 0
JDH4-02-007-PR-1890 | JDH4-02-007-PR-1890 | Material Delivery for Fuel System | 179076.09 | 100% | 100% | 179076.09
Fire Fighting System | Fire Fighting System |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2320 | JDH4-02-007-PR-2320 | PO for Fire Fighting System | 0 | 100% | 100% | 0
JDH4-02-007-PR-2330 | JDH4-02-007-PR-2330 | Material Fabrication for Fire Fighting System | 0 | 100% | 100% | 0
JDH4-02-007-PR-2340 | JDH4-02-007-PR-2340 | Material Delivery for Fire Fighting System | 179076.09 | 100% | 100% | 179076.09
Security System (CCTV System) | Security System (CCTV System) |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2410 | JDH4-02-007-PR-2410 | PO for Security System (CCTV System) | 0 | 100% | 100% | 0
JDH4-02-007-PR-2420 | JDH4-02-007-PR-2420 | Material Fabrication for Security System (CCTV System) | 0 | 100% | 100% | 0
JDH4-02-007-PR-2430 | JDH4-02-007-PR-2430 | Material Delivery for Security System (CCTV System) | 179076.09 | 100% | 100% | 179076.09
Long Lead Item | Long Lead Item |  | 6267663.15 |  | 100% | 6267663.15
TSE Network | TSE Network |  | 358152.18 |  | 100% | 358152.18
Valves / Chambers | Valves / Chambers |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1270 | JDH4-02-007-PR-1270 | PO for Valves / Chambers | 0 | 100% | 100% | 0
JDH4-02-007-PR-1277 | JDH4-02-007-PR-1277 | Material Fabrication for Valves / Chambers - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1278 | JDH4-02-007-PR-1278 | Material Fabrication for Valves / Chambers - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1279 | JDH4-02-007-PR-1279 | Material Fabrication for Valves / Chambers - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1280 | JDH4-02-007-PR-1280 | Material Fabrication for Valves / Chambers - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1290 | JDH4-02-007-PR-1290 | Material Delivery for Valves / Chambers | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-1820 | JDH4-02-007-PR-1820 | Staging Time for Valves / Chambers | 0 | 100% | 100% | 0
Risers | Risers |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1900 | JDH4-02-007-PR-1900 | PO for Risers | 0 | 100% | 100% | 0
JDH4-02-007-PR-1907 | JDH4-02-007-PR-1907 | Material Fabrication for Risers - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1908 | JDH4-02-007-PR-1908 | Material Fabrication for Risers - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1909 | JDH4-02-007-PR-1909 | Material Fabrication for Risers - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1910 | JDH4-02-007-PR-1910 | Material Fabrication for Risers - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1920 | JDH4-02-007-PR-1920 | Material Delivery for Risers | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-1930 | JDH4-02-007-PR-1930 | Staging Time for Risers | 0 | 100% | 100% | 0
Potable Water Network | Potable Water Network |  | 358152.18 |  | 100% | 358152.18
Valves / Chambers | Valves / Chambers |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1240 | JDH4-02-007-PR-1240 | PO for Valves / Chambers | 0 | 100% | 100% | 0
JDH4-02-007-PR-1249 | JDH4-02-007-PR-1249 | Material Fabrication for Valves / Chambers - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1248 | JDH4-02-007-PR-1248 | Material Fabrication for Valves / Chambers - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1250 | JDH4-02-007-PR-1250 | Material Fabrication for Valves / Chambers - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1260 | JDH4-02-007-PR-1260 | Material Delivery for Valves / Chambers | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-1810 | JDH4-02-007-PR-1810 | Staging Time for Valves / Chambers | 0 | 100% | 100% | 0
Fire Hydrants | Fire Hydrants |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2440 | JDH4-02-007-PR-2440 | PO for Fire Hydrant | 0 | 100% | 100% | 0
JDH4-02-007-PR-2447 | JDH4-02-007-PR-2447 | Material Fabrication for Fire Hydrant - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2448 | JDH4-02-007-PR-2448 | Material Fabrication for Fire Hydrant - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2449 | JDH4-02-007-PR-2449 | Material Fabrication for Fire Hydrant - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2450 | JDH4-02-007-PR-2450 | Material Fabrication for Fire Hydrant - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2460 | JDH4-02-007-PR-2460 | Material Delivery for Fire Hydrant | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2470 | JDH4-02-007-PR-2470 | Staging Time for Fire Hydrant | 0 | 100% | 100% | 0
Electrical Network | Electrical Network |  | 1432608.72 |  | 100% | 1432608.72
Medium Voltage Cable | Medium Voltage Cable |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1000 | JDH4-02-007-PR-1000 | PO for Medium Voltage Cable | 0 | 100% | 100% | 0
JDH4-02-007-PR-1060 | JDH4-02-007-PR-1060 | Material Fabrication for Medium Voltage Cable - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1059 | JDH4-02-007-PR-1059 | Material Fabrication for Medium Voltage Cable - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1120 | JDH4-02-007-PR-1120 | Material Delivery for Medium Voltage Cable | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-1750 | JDH4-02-007-PR-1750 | Staging Time for Medium Voltage Cable | 0 | 100% | 100% | 0
Unit Sub Station | Unit Sub Station |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1010 | JDH4-02-007-PR-1010 | PO for Unit Sub-station | 0 | 100% | 100% | 0
JDH4-02-007-PR-1067 | JDH4-02-007-PR-1067 | Material Fabrication for Unit Sub-station - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1068 | JDH4-02-007-PR-1068 | Material Fabrication for Unit Sub-station - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1069 | JDH4-02-007-PR-1069 | Material Fabrication for Unit Sub-station - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1070 | JDH4-02-007-PR-1070 | Material Fabrication for Unit Sub-station - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1130 | JDH4-02-007-PR-1130 | Material Delivery for Unit Sub-station | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-1760 | JDH4-02-007-PR-1760 | Staging Time for Unit Sub-station | 0 | 100% | 100% | 0
Low Voltage Cables | Low Voltage Cables |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1020 | JDH4-02-007-PR-1020 | PO for Low Voltage Cables | 0 | 100% | 100% | 0
JDH4-02-007-PR-1078 | JDH4-02-007-PR-1078 | Material Fabrication for Low Voltage Cables - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1079 | JDH4-02-007-PR-1079 | Material Fabrication for Low Voltage Cables - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1080 | JDH4-02-007-PR-1080 | Material Fabrication for Low Voltage Cables - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1140 | JDH4-02-007-PR-1140 | Material Delivery for Low Voltage Cables | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-1770 | JDH4-02-007-PR-1770 | Staging Time for Low Voltage Cables | 0 | 100% | 100% | 0
Ring Main Unit | Ring Main Unit |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1940 | JDH4-02-007-PR-1940 | PO for Ring Main Unit | 0 | 100% | 100% | 0
JDH4-02-007-PR-1948 | JDH4-02-007-PR-1948 | Material Fabrication for Ring Main Unit - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1949 | JDH4-02-007-PR-1949 | Material Fabrication for Ring Main Unit - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1950 | JDH4-02-007-PR-1950 | Material Fabrication for Ring Main Unit - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1960 | JDH4-02-007-PR-1960 | Material Delivery for Ring Main Unit | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-1970 | JDH4-02-007-PR-1970 | Staging Time for Ring Main Unit | 0 | 100% | 100% | 0
Lighting poles | Lighting poles |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1030 | JDH4-02-007-PR-1030 | PO for Lighting poles | 0 | 100% | 100% | 0
JDH4-02-007-PR-1088 | JDH4-02-007-PR-1088 | Material Fabrication for Lighting poles - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1090 | JDH4-02-007-PR-1090 | Material Fabrication for Lighting poles - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1089 | JDH4-02-007-PR-1089 | Material Fabrication for Lighting poles - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1150 | JDH4-02-007-PR-1150 | Material Delivery for Lighting poles | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-1780 | JDH4-02-007-PR-1780 | Staging Time for Lighting poles | 0 | 100% | 100% | 0
Street Lighting Luminaire | Street Lighting Luminaire |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1040 | JDH4-02-007-PR-1040 | PO for Street Lighting Luminaire | 0 | 100% | 100% | 0
JDH4-02-007-PR-1098 | JDH4-02-007-PR-1098 | Material Fabrication for Street Lighting Luminaire - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1099 | JDH4-02-007-PR-1099 | Material Fabrication for Street Lighting Luminaire - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1100 | JDH4-02-007-PR-1100 | Material Fabrication for Street Lighting Luminaire - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1160 | JDH4-02-007-PR-1160 | Material Delivery for Street Lighting Luminaire | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-1790 | JDH4-02-007-PR-1790 | Staging Time for Street Lighting Luminaire | 0 | 100% | 100% | 0
Lighting panels/Feeder Pillers | Lighting panels/Feeder Pillers |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1050 | JDH4-02-007-PR-1050 | PO for Lighting Panels/Feeder Pillers | 0 | 100% | 100% | 0
JDH4-02-007-PR-1108 | JDH4-02-007-PR-1108 | Material Fabrication for Lighting Panels/Feeder Pillers - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1110 | JDH4-02-007-PR-1110 | Material Fabrication for Lighting Panels/Feeder Pillers - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1170 | JDH4-02-007-PR-1170 | Material Delivery for Lighting Panels/Feeder Pillers | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-1109 | JDH4-02-007-PR-1109 | Material Fabrication for Lighting Panels/Feeder Pillers - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1800 | JDH4-02-007-PR-1800 | Staging Time for Lighting Panels/Feeder Pillers | 0 | 100% | 100% | 0
Low Voltage Distribution Panels | Low Voltage Distribution Panels |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2480 | JDH4-02-007-PR-2480 | PO for Low Voltage Distribution Panels | 0 | 100% | 100% | 0
JDH4-02-007-PR-2488 | JDH4-02-007-PR-2488 | Material Fabrication for Low Voltage Distribution Panels - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2489 | JDH4-02-007-PR-2489 | Material Fabrication for Low Voltage Distribution Panels - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2490 | JDH4-02-007-PR-2490 | Material Fabrication for Low Voltage Distribution Panels - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2500 | JDH4-02-007-PR-2500 | Material Delivery for Low Voltage Distribution Panels | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2510 | JDH4-02-007-PR-2510 | Staging Time for Low Voltage Distribution Panels | 0 | 100% | 100% | 0
Sewage Lift Station | Sewage Lift Station |  | 4118750.07 |  | 100% | 4118750.07
Odours scrubbing system | Odours scrubbing system |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1990 | JDH4-02-007-PR-1990 | PO for Odours scrubbing system | 0 | 100% | 100% | 0
JDH4-02-007-PR-2037 | JDH4-02-007-PR-2037 | Material Fabrication for Odours scrubbing system - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2038 | JDH4-02-007-PR-2038 | Material Fabrication for Odours scrubbing system - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2039 | JDH4-02-007-PR-2039 | Material Fabrication for Odours scrubbing system - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2040 | JDH4-02-007-PR-2040 | Material Fabrication for Odours scrubbing system - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2090 | JDH4-02-007-PR-2090 | Material Delivery for Odours scrubbing system | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2140 | JDH4-02-007-PR-2140 | Staging Time for Odours scrubbing system | 0 | 100% | 100% | 0
Crane | Crane |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2180 | JDH4-02-007-PR-2180 | PO for Crane | 0 | 100% | 100% | 0
JDH4-02-007-PR-2187 | JDH4-02-007-PR-2187 | Material Fabrication for Crane - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2188 | JDH4-02-007-PR-2188 | Material Fabrication for Crane - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2189 | JDH4-02-007-PR-2189 | Material Fabrication for Crane - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2190 | JDH4-02-007-PR-2190 | Material Fabrication for Crane - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2200 | JDH4-02-007-PR-2200 | Material Delivery for Crane | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2210 | JDH4-02-007-PR-2210 | Staging Time for Crane | 0 | 100% | 100% | 0
Air Vents | Air Vents |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2000 | JDH4-02-007-PR-2000 | PO for Air Vents | 0 | 100% | 100% | 0
JDH4-02-007-PR-2045 | JDH4-02-007-PR-2045 | Material Fabrication for Air Vents - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2046 | JDH4-02-007-PR-2046 | Material Fabrication for Air Vents - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2047 | JDH4-02-007-PR-2047 | Material Fabrication for Air Vents - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2048 | JDH4-02-007-PR-2048 | Material Fabrication for Air Vents - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2049 | JDH4-02-007-PR-2049 | Material Fabrication for Air Vents - Stage 5 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2050 | JDH4-02-007-PR-2050 | Material Fabrication for Air Vents - Stage 6 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2100 | JDH4-02-007-PR-2100 | Material Delivery for Air Vents | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2150 | JDH4-02-007-PR-2150 | Staging Time for Air Vents | 0 | 100% | 100% | 0
Screening Container | Screening Container |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2220 | JDH4-02-007-PR-2220 | PO for Screening Container | 0 | 100% | 100% | 0
JDH4-02-007-PR-2225 | JDH4-02-007-PR-2225 | Material Fabrication for Screening Container - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2226 | JDH4-02-007-PR-2226 | Material Fabrication for Screening Container - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2227 | JDH4-02-007-PR-2227 | Material Fabrication for Screening Container - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2230 | JDH4-02-007-PR-2230 | Material Fabrication for Screening Container - Stage 6 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2229 | JDH4-02-007-PR-2229 | Material Fabrication for Screening Container - Stage 5 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2228 | JDH4-02-007-PR-2228 | Material Fabrication for Screening Container - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2240 | JDH4-02-007-PR-2240 | Material Delivery for Screening Container | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2250 | JDH4-02-007-PR-2250 | Staging Time for Screening Container | 0 | 100% | 100% | 0
Baffle Plates | Baffle Plates |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2010 | JDH4-02-007-PR-2010 | PO for Baffle Plates | 0 | 100% | 100% | 0
JDH4-02-007-PR-2057 | JDH4-02-007-PR-2057 | Material Fabrication for Baffle Plates - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2058 | JDH4-02-007-PR-2058 | Material Fabrication for Baffle Plates - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2059 | JDH4-02-007-PR-2059 | Material Fabrication for Baffle Plates - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2060 | JDH4-02-007-PR-2060 | Material Fabrication for Baffle Plates - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2110 | JDH4-02-007-PR-2110 | Material Delivery for Baffle Plates | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2160 | JDH4-02-007-PR-2160 | Staging Time for Baffle Plates | 0 | 100% | 100% | 0
Anti-Water Hammer Equipment | Anti-Water Hammer Equipment |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2020 | JDH4-02-007-PR-2020 | PO for Anti-Water Hammer Equipment | 0 | 100% | 100% | 0
JDH4-02-007-PR-2120 | JDH4-02-007-PR-2120 | Material Delivery for Anti-Water Hammer Equipment | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2067 | JDH4-02-007-PR-2067 | Material Fabrication for Anti-Water Hammer Equipment - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2066 | JDH4-02-007-PR-2066 | Material Fabrication for Anti-Water Hammer Equipment - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2065 | JDH4-02-007-PR-2065 | Material Fabrication for Anti-Water Hammer Equipment - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2070 | JDH4-02-007-PR-2070 | Material Fabrication for Anti-Water Hammer Equipment - Stage 6 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2069 | JDH4-02-007-PR-2069 | Material Fabrication for Anti-Water Hammer Equipment - Stage 5 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2068 | JDH4-02-007-PR-2068 | Material Fabrication for Anti-Water Hammer Equipment - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2170 | JDH4-02-007-PR-2170 | Staging Time for Anti-Water Hammer Equipment | 0 | 100% | 100% | 0
Pumps | Pumps |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1980 | JDH4-02-007-PR-1980 | PO for Pumps | 0 | 100% | 100% | 0
JDH4-02-007-PR-2026 | JDH4-02-007-PR-2026 | Material Fabrication for Pumps - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2027 | JDH4-02-007-PR-2027 | Material Fabrication for Pumps - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2028 | JDH4-02-007-PR-2028 | Material Fabrication for Pumps - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2029 | JDH4-02-007-PR-2029 | Material Fabrication for Pumps - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2030 | JDH4-02-007-PR-2030 | Material Fabrication for Pumps - Stage 5 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2080 | JDH4-02-007-PR-2080 | Material Delivery for Pumps | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2130 | JDH4-02-007-PR-2130 | Staging Time for Pumps | 0 | 100% | 100% | 0
Main Distribution Board /MCC panels | Main Distribution Board /MCC panels |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2530 | JDH4-02-007-PR-2530 | PO for Main Distribution Board / MCC panels | 0 | 100% | 100% | 0
JDH4-02-007-PR-2567 | JDH4-02-007-PR-2567 | Material Fabrication for Main Distribution Board / MCC panels - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2568 | JDH4-02-007-PR-2568 | Material Fabrication for Main Distribution Board / MCC panels - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2570 | JDH4-02-007-PR-2570 | Material Fabrication for Main Distribution Board / MCC panels - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2569 | JDH4-02-007-PR-2569 | Material Fabrication for Main Distribution Board / MCC panels - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2610 | JDH4-02-007-PR-2610 | Material Delivery for Main Distribution Board / MCC panels | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2650 | JDH4-02-007-PR-2650 | Staging Time for Main Distribution Board / MCC panels | 0 | 100% | 100% | 0
Final Panel boards | Final Panel boards |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2680 | JDH4-02-007-PR-2680 | PO for Final Panel Boards | 0 | 100% | 100% | 0
JDH4-02-007-PR-2687 | JDH4-02-007-PR-2687 | Material Fabrication for Final Panel Boards - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2688 | JDH4-02-007-PR-2688 | Material Fabrication for Final Panel Boards - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2690 | JDH4-02-007-PR-2690 | Material Fabrication for Final Panel Boards - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2689 | JDH4-02-007-PR-2689 | Material Fabrication for Final Panel Boards - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2700 | JDH4-02-007-PR-2700 | Material Delivery for Final Panel Boards | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2710 | JDH4-02-007-PR-2710 | Staging Time for Final Panel Boards | 0 | 100% | 100% | 0
Local Control Panel/ Monitoring Control Panel | Local Control Panel/ Monitoring Control Panel |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2540 | JDH4-02-007-PR-2540 | PO for Local Control Panel/ Monitoring Control Panel | 0 | 100% | 100% | 0
JDH4-02-007-PR-2576 | JDH4-02-007-PR-2576 | Material Fabrication for Local Control Panel/ Monitoring Control Panel - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2577 | JDH4-02-007-PR-2577 | Material Fabrication for Local Control Panel/ Monitoring Control Panel - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2578 | JDH4-02-007-PR-2578 | Material Fabrication for Local Control Panel/ Monitoring Control Panel - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2580 | JDH4-02-007-PR-2580 | Material Fabrication for Local Control Panel/ Monitoring Control Panel - Stage 5 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2579 | JDH4-02-007-PR-2579 | Material Fabrication for Local Control Panel/ Monitoring Control Panel - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2620 | JDH4-02-007-PR-2620 | Material Delivery for Local Control Panel/ Monitoring Control Panel | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2660 | JDH4-02-007-PR-2660 | Staging Time for Local Control Panel/ Monitoring Control Panel | 0 | 100% | 100% | 0
Engine Generators | Engine Generators |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2720 | JDH4-02-007-PR-2720 | PO for Engine Generators | 0 | 100% | 100% | 0
JDH4-02-007-PR-2726 | JDH4-02-007-PR-2726 | Material Fabrication for Engine Generators - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2727 | JDH4-02-007-PR-2727 | Material Fabrication for Engine Generators - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2728 | JDH4-02-007-PR-2728 | Material Fabrication for Engine Generators - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2729 | JDH4-02-007-PR-2729 | Material Fabrication for Engine Generators - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2730 | JDH4-02-007-PR-2730 | Material Fabrication for Engine Generators - Stage 5 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2740 | JDH4-02-007-PR-2740 | Material Delivery for Engine Generators | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2750 | JDH4-02-007-PR-2750 | Staging Time for Engine Generators | 0 | 100% | 100% | 0
Standby Diesel Generator | Standby Diesel Generator |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2550 | JDH4-02-007-PR-2550 | PO for Standby Diesel Generator | 0 | 100% | 100% | 0
JDH4-02-007-PR-2587 | JDH4-02-007-PR-2587 | Material Fabrication for Standby Diesel Generator - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2588 | JDH4-02-007-PR-2588 | Material Fabrication for Standby Diesel Generator - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2589 | JDH4-02-007-PR-2589 | Material Fabrication for Standby Diesel Generator - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2590 | JDH4-02-007-PR-2590 | Material Fabrication for Standby Diesel Generator - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2630 | JDH4-02-007-PR-2630 | Material Delivery for Standby Diesel Generator | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2670 | JDH4-02-007-PR-2670 | Staging Time for Standby Diesel Generator | 0 | 100% | 100% | 0
Power Factor Correction Capacitor Bank | Power Factor Correction Capacitor Bank |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2760 | JDH4-02-007-PR-2760 | PO for Power Factor Correction Capacitor Bank | 0 | 100% | 100% | 0
JDH4-02-007-PR-2795 | JDH4-02-007-PR-2795 | Material Fabrication for Power Factor Correction Capacitor Bank - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2796 | JDH4-02-007-PR-2796 | Material Fabrication for Power Factor Correction Capacitor Bank - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2797 | JDH4-02-007-PR-2797 | Material Fabrication for Power Factor Correction Capacitor Bank - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2798 | JDH4-02-007-PR-2798 | Material Fabrication for Power Factor Correction Capacitor Bank - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2800 | JDH4-02-007-PR-2800 | Material Fabrication for Power Factor Correction Capacitor Bank - Stage 6 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2799 | JDH4-02-007-PR-2799 | Material Fabrication for Power Factor Correction Capacitor Bank - Stage 5 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2840 | JDH4-02-007-PR-2840 | Material Delivery for Power Factor Correction Capacitor Bank | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2880 | JDH4-02-007-PR-2880 | Staging Time for Power Factor Correction Capacitor Bank | 0 | 100% | 100% | 0
Low-Voltage Electrical Power Conductors and Cables | Low-Voltage Electrical Power Conductors and Cables |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2770 | JDH4-02-007-PR-2770 | PO for Low-Voltage Electrical Power Conductors and Cables | 0 | 100% | 100% | 0
JDH4-02-007-PR-2807 | JDH4-02-007-PR-2807 | Material Fabrication for Low-Voltage Electrical Power Conductors and Cables - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2808 | JDH4-02-007-PR-2808 | Material Fabrication for Low-Voltage Electrical Power Conductors and Cables - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2809 | JDH4-02-007-PR-2809 | Material Fabrication for Low-Voltage Electrical Power Conductors and Cables - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2810 | JDH4-02-007-PR-2810 | Material Fabrication for Low-Voltage Electrical Power Conductors and Cables - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2850 | JDH4-02-007-PR-2850 | Material Delivery for Low-Voltage Electrical Power Conductors and Cables | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2890 | JDH4-02-007-PR-2890 | Staging Time for Low-Voltage Electrical Power Conductors and Cables | 0 | 100% | 100% | 0
Low Voltage Feeder Cable | Low Voltage Feeder Cable |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2920 | JDH4-02-007-PR-2920 | PO for Low Voltage Feeder Cable | 0 | 100% | 100% | 0
JDH4-02-007-PR-2927 | JDH4-02-007-PR-2927 | Material Fabrication for Low Voltage Feeder Cable - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2928 | JDH4-02-007-PR-2928 | Material Fabrication for Low Voltage Feeder Cable - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2929 | JDH4-02-007-PR-2929 | Material Fabrication for Low Voltage Feeder Cable - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2930 | JDH4-02-007-PR-2930 | Material Fabrication for Low Voltage Feeder Cable - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2940 | JDH4-02-007-PR-2940 | Material Delivery for Low Voltage Feeder Cable | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2950 | JDH4-02-007-PR-2950 | Staging Time for Low Voltage Feeder Cable | 0 | 100% | 100% | 0
Wiring Devices | Wiring Devices |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2780 | JDH4-02-007-PR-2780 | PO for Wiring Devices | 0 | 100% | 100% | 0
JDH4-02-007-PR-2815 | JDH4-02-007-PR-2815 | Material Fabrication for Wiring Devices - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2816 | JDH4-02-007-PR-2816 | Material Fabrication for Wiring Devices - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2817 | JDH4-02-007-PR-2817 | Material Fabrication for Wiring Devices - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2818 | JDH4-02-007-PR-2818 | Material Fabrication for Wiring Devices - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2819 | JDH4-02-007-PR-2819 | Material Fabrication for Wiring Devices - Stage 5 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2820 | JDH4-02-007-PR-2820 | Material Fabrication for Wiring Devices - Stage 6 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2860 | JDH4-02-007-PR-2860 | Material Delivery for Wiring Devices | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2900 | JDH4-02-007-PR-2900 | Staging Time for Wiring Devices | 0 | 100% | 100% | 0
Enclosed Switches and Circuit Breakers | Enclosed Switches and Circuit Breakers |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2960 | JDH4-02-007-PR-2960 | PO for Enclosed Switches and Circuit Breakers | 0 | 100% | 100% | 0
JDH4-02-007-PR-2965 | JDH4-02-007-PR-2965 | Material Fabrication for Enclosed Switches and Circuit Breakers - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2966 | JDH4-02-007-PR-2966 | Material Fabrication for Enclosed Switches and Circuit Breakers - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2967 | JDH4-02-007-PR-2967 | Material Fabrication for Enclosed Switches and Circuit Breakers - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2970 | JDH4-02-007-PR-2970 | Material Fabrication for Enclosed Switches and Circuit Breakers - Stage 6 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2969 | JDH4-02-007-PR-2969 | Material Fabrication for Enclosed Switches and Circuit Breakers - Stage 5 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2968 | JDH4-02-007-PR-2968 | Material Fabrication for Enclosed Switches and Circuit Breakers - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2980 | JDH4-02-007-PR-2980 | Material Delivery for Enclosed Switches and Circuit Breakers | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2990 | JDH4-02-007-PR-2990 | Staging Time for Enclosed Switches and Circuit Breakers | 0 | 100% | 100% | 0
Raceways for Electrical Systems | Raceways for Electrical Systems |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2790 | JDH4-02-007-PR-2790 | PO for Raceways for Electrical Systems | 0 | 100% | 100% | 0
JDH4-02-007-PR-2827 | JDH4-02-007-PR-2827 | Material Fabrication for Raceways for Electrical Systems - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2828 | JDH4-02-007-PR-2828 | Material Fabrication for Raceways for Electrical Systems - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2829 | JDH4-02-007-PR-2829 | Material Fabrication for Raceways for Electrical Systems - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2830 | JDH4-02-007-PR-2830 | Material Fabrication for Raceways for Electrical Systems - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2870 | JDH4-02-007-PR-2870 | Material Delivery for Raceways for Electrical Systems | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2910 | JDH4-02-007-PR-2910 | Staging Time for Raceways for Electrical Systems | 0 | 100% | 100% | 0
Electrical Manholes | Electrical Manholes |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2520 | JDH4-02-007-PR-2520 | PO for Electrical Manholes | 0 | 100% | 100% | 0
JDH4-02-007-PR-2555 | JDH4-02-007-PR-2555 | Material Fabrication for Electrical Manholes - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2557 | JDH4-02-007-PR-2557 | Material Fabrication for Electrical Manholes - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2556 | JDH4-02-007-PR-2556 | Material Fabrication for Electrical Manholes - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2558 | JDH4-02-007-PR-2558 | Material Fabrication for Electrical Manholes - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2559 | JDH4-02-007-PR-2559 | Material Fabrication for Electrical Manholes - Stage 5 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2560 | JDH4-02-007-PR-2560 | Material Fabrication for Electrical Manholes - Stage 6 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2600 | JDH4-02-007-PR-2600 | Material Delivery for Electrical Manholes | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2640 | JDH4-02-007-PR-2640 | Staging Time for Electrical Manholes | 0 | 100% | 100% | 0
ICT (Data& telephone System) | ICT (Data& telephone System) |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-3040 | JDH4-02-007-PR-3040 | PO for ICT (Data& telephone System) | 0 | 100% | 100% | 0
JDH4-02-007-PR-3055 | JDH4-02-007-PR-3055 | Material Fabrication for ICT (Data& telephone System) - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3056 | JDH4-02-007-PR-3056 | Material Fabrication for ICT (Data& telephone System) - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3057 | JDH4-02-007-PR-3057 | Material Fabrication for ICT (Data& telephone System) - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3058 | JDH4-02-007-PR-3058 | Material Fabrication for ICT (Data& telephone System) - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3059 | JDH4-02-007-PR-3059 | Material Fabrication for ICT (Data& telephone System) - Stage 5 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3060 | JDH4-02-007-PR-3060 | Material Fabrication for ICT (Data& telephone System) - Stage 6 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3080 | JDH4-02-007-PR-3080 | Material Delivery for ICT (Data& telephone System) | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-3100 | JDH4-02-007-PR-3100 | Staging Time for ICT (Data& telephone System) | 0 | 100% | 100% | 0
Programmable Logic Controllers | Programmable Logic Controllers |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-3120 | JDH4-02-007-PR-3120 | PO for Programmable Logic Controllers | 0 | 100% | 100% | 0
JDH4-02-007-PR-3125 | JDH4-02-007-PR-3125 | Material Fabrication for Programmable Logic Controllers - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3126 | JDH4-02-007-PR-3126 | Material Fabrication for Programmable Logic Controllers - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3127 | JDH4-02-007-PR-3127 | Material Fabrication for Programmable Logic Controllers - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3130 | JDH4-02-007-PR-3130 | Material Fabrication for Programmable Logic Controllers - Stage 6 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3129 | JDH4-02-007-PR-3129 | Material Fabrication for Programmable Logic Controllers - Stage 5 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3128 | JDH4-02-007-PR-3128 | Material Fabrication for Programmable Logic Controllers - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3140 | JDH4-02-007-PR-3140 | Material Delivery for Programmable Logic Controllers | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-3150 | JDH4-02-007-PR-3150 | Staging Time for Programmable Logic Controllers | 0 | 100% | 100% | 0
Process Control Wiring | Process Control Wiring |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-3050 | JDH4-02-007-PR-3050 | PO for Process Control Wiring | 0 | 100% | 100% | 0
JDH4-02-007-PR-3067 | JDH4-02-007-PR-3067 | Material Fabrication for Process Control Wiring - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3068 | JDH4-02-007-PR-3068 | Material Fabrication for Process Control Wiring - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3069 | JDH4-02-007-PR-3069 | Material Fabrication for Process Control Wiring - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3070 | JDH4-02-007-PR-3070 | Material Fabrication for Process Control Wiring - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3090 | JDH4-02-007-PR-3090 | Material Delivery for Process Control Wiring | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-3110 | JDH4-02-007-PR-3110 | Staging Time for Process Control Wiring | 0 | 100% | 100% | 0
Instrumentation for Process Systems | Instrumentation for Process Systems |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-3000 | JDH4-02-007-PR-3000 | PO for Instrumentation for Process Systems | 0 | 100% | 100% | 0
JDH4-02-007-PR-3005 | JDH4-02-007-PR-3005 | Material Fabrication for Instrumentation for Process Systems - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3006 | JDH4-02-007-PR-3006 | Material Fabrication for Instrumentation for Process Systems - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3007 | JDH4-02-007-PR-3007 | Material Fabrication for Instrumentation for Process Systems - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3010 | JDH4-02-007-PR-3010 | Material Fabrication for Instrumentation for Process Systems - Stage 6 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3009 | JDH4-02-007-PR-3009 | Material Fabrication for Instrumentation for Process Systems - Stage 5 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3008 | JDH4-02-007-PR-3008 | Material Fabrication for Instrumentation for Process Systems - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3020 | JDH4-02-007-PR-3020 | Material Delivery for Instrumentation for Process Systems | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-3030 | JDH4-02-007-PR-3030 | Staging Time for Instrumentation for Process Systems | 0 | 100% | 100% | 0
Construction | Construction |  | 38393913.07 |  | 94.38% | 36236320.31
Demolition Works | Demolition Works |  | 505616.54 |  | 100% | 505616.54
Demolition in Road network | Demolition in Road network |  | 127411.78 |  | 100% | 127411.78
JDH4-02-007-CN-1000 | JDH4-02-007-CN-1000 | Concrete demolition works at the existing Underpass [Demolition Works ] | 26491.56 | 100% | 100% | 26491.56
JDH4-02-007-CN-1110 | JDH4-02-007-CN-1110 | Milling of the existing asphalt layer [Demolition Works ] | 25230.06 | 100% | 100% | 25230.06
JDH4-02-007-CN-1080 | JDH4-02-007-CN-1080 | Removal of the existing asphalt layers (up to base course layer) [Demolition Works ] | 37845.08 | 100% | 100% | 37845.08
JDH4-02-007-CN-1170 | JDH4-02-007-CN-1170 | Re-use and compaction of the existing aggregate base course layer | 37845.08 | 100% | 100% | 37845.08
Demolition in TSE network | Demolition in TSE network |  | 92720.45 |  | 100% | 92720.45
JDH4-02-007-CN-1480 | JDH4-02-007-CN-1480 | Pipe with diameter 63 mm pipe [Demolition Works ] | 1892.25 | 100% | 100% | 1892.25
JDH4-02-007-CN-1560 | JDH4-02-007-CN-1560 | Pipe with diameter 200 mm pipe [Demolition Works ] | 47937.11 | 100% | 100% | 47937.11
JDH4-02-007-CN-1610 | JDH4-02-007-CN-1610 | Wash out valve with chamber; on 200 mm dia pipeline Depth 1.5 - 4.0m [Demolition Works ] | 20184.04 | 100% | 100% | 20184.04
JDH4-02-007-CN-1620 | JDH4-02-007-CN-1620 | Gate valves on 200 mm pipeline [Demolition Works ] | 3784.51 | 100% | 100% | 3784.51
JDH4-02-007-CN-1590 | JDH4-02-007-CN-1590 | Pipe with diameter 250 mm pipe [Demolition Works ] | 18922.54 | 100% | 100% | 18922.54
Demolition in Storm water network | Demolition in Storm water network |  | 56073.8 |  | 100% | 56073.8
JDH4-02-007-CN-1670 | JDH4-02-007-CN-1670 | Manhole [Demolition Works ] | 8830.52 | 100% | 100% | 8830.52
JDH4-02-007-CN-1690 | JDH4-02-007-CN-1690 | Pipe with diameter 600 mm pipe [Demolition Works ] | 14128.83 | 100% | 100% | 14128.83
JDH4-02-007-CN-1700 | JDH4-02-007-CN-1700 | Pipe with diameter 800 mm pipe [Demolition Works ] | 14191.91 | 100% | 100% | 14191.91
JDH4-02-007-CN-1680 | JDH4-02-007-CN-1680 | Baffle box with dimentions 3.04x7.80m [Demolition Works ] | 18922.54 | 100% | 100% | 18922.54
Demolition in Sewerage network | Demolition in Sewerage network |  | 93225.07 |  | 100% | 93225.07
JDH4-02-007-CN-1630 | JDH4-02-007-CN-1630 | Pipe with diameter 200 mm pipe with depth 2.50 - 3.50m [Demolition Works ] | 26491.56 | 100% | 100% | 26491.56
JDH4-02-007-CN-1640 | JDH4-02-007-CN-1640 | Pipe with diameter 250 mm pipe with depth 3.50 - 4.50m [Demolition Works ] | 38349.69 | 100% | 100% | 38349.69
JDH4-02-007-CN-1650 | JDH4-02-007-CN-1650 | Manhole with depth 1.50m - 2.50m [Demolition Works ] | 12615.03 | 100% | 100% | 12615.03
JDH4-02-007-CN-1660 | JDH4-02-007-CN-1660 | Manhole with depth 4.50m - 5.50m [Demolition Works ] | 15768.79 | 100% | 100% | 15768.79
Demolition in Potable water network | Demolition in Potable water network |  | 46990.99 |  | 100% | 46990.99
JDH4-02-007-CN-1340 | JDH4-02-007-CN-1340 | Single house connection dia 63 mm [Demolition Works ] | 15768.79 | 100% | 100% | 15768.79
JDH4-02-007-CN-1400 | JDH4-02-007-CN-1400 | Pipe with diameter 200 mm [Demolition Works ] | 15453.41 | 100% | 100% | 15453.41
JDH4-02-007-CN-1430 | JDH4-02-007-CN-1430 | Wash out valve with chamber; on 200 mm dia pipeline [Demolition Works ] | 15768.79 | 100% | 100% | 15768.79
Demolition in Electrical works | Demolition in Electrical works |  | 89194.45 |  | 100% | 89194.45
JDH4-02-007-CN-1250 | JDH4-02-007-CN-1250 | Demolishing of existing Lighting Pole [Demolition Works ](Completed) | 17002.05 | 100% | 100% | 17002.05
JDH4-02-007-CN-3020 | JDH4-02-007-CN-3020 | Relocating of existing Lighting Pole [Road 02 ](Completed) | 14036.17 | 100% | 100% | 14036.17
JDH4-02-007-CN-3020R | JDH4-02-007-CN-3020R | Relocating of existing Lighting Pole [Road 02 ] | 27536.54 | 100% | 100% | 27536.54
JDH4-02-007-CN-1250R | JDH4-02-007-CN-1250R | Demolishing of existing Lighting Pole [Demolition Works ] | 3812.75 | 100% | 100% | 3812.75
JDH4-02-007-CN-3040 | JDH4-02-007-CN-3040 | Relocating of existing Lighting Pole [Road 04-R ] | 12615.03 | 100% | 100% | 12615.03
JDH4-02-007-CN-3030 | JDH4-02-007-CN-3030 | Relocating of existing Lighting Pole [Road 08 ] | 4730.64 | 100% | 100% | 4730.64
JDH4-02-007-CN-3050 | JDH4-02-007-CN-3050 | Relocating of existing Lighting Pole [Road 10 ] | 9461.27 | 100% | 100% | 9461.27
Plots | Plots |  | 4337407.52 |  | 100% | 4337407.52
Excavation | Excavation |  | 282577.06 |  | 100% | 282577.06
JDH4-02-007-CN-1760 | JDH4-02-007-CN-1760 | Plots excavation [Plots ] | 282577.06 | 100% | 100% | 282577.06
Backfilling | Backfilling |  | 4054830.46 |  | 100% | 4054830.46
JDH4-02-007-CN-1820 | JDH4-02-007-CN-1820 | Plots backfilling Stage 1 [Plots ] | 1013707.62 | 100% | 100% | 1013707.62
JDH4-02-007-CN-1830 | JDH4-02-007-CN-1830 | Plots backfilling Stage 2 [Plots ](Completed) | 709608.44 | 100% | 100% | 709608.44
JDH4-02-007-CN-1840 | JDH4-02-007-CN-1840 | Plots backfilling Stage 3 [Plots ](Completed) | 202739.5 | 100% | 100% | 202739.5
JDH4-02-007-CN-1830R | JDH4-02-007-CN-1830R | Plots backfilling Stage 2 [Plots ] | 304109.26 | 100% | 100% | 304109.26
JDH4-02-007-CN-1840R | JDH4-02-007-CN-1840R | Plots backfilling Stage 3 [Plots ] | 810958.02 | 100% | 100% | 810958.02
JDH4-02-007-CN-1850 | JDH4-02-007-CN-1850 | Plots backfilling Stage 4 [Plots ] | 1013707.62 | 100% | 100% | 1013707.62
Roads | Roads |  | 21997203.9 |  | 99.76% | 21943757.22
Road 04-R | Road 04-R |  | 5772635.72 |  | 100% | 5772635.72
Box Culvert | Box Culvert |  | 499735.96 |  | 100% | 499735.96
JDH4-02-007-CN-5580 | JDH4-02-007-CN-5580 | Excavation For Box Culvert [Road 04-R ] | 47552.35 | 100% | 100% | 47552.35
JDH4-02-007-CN-5590 | JDH4-02-007-CN-5590 | Backfilling For Box Culvert [Road 04-R ] | 30578.83 | 100% | 100% | 30578.83
JDH4-02-007-CN-5600 | JDH4-02-007-CN-5600 | Plain Concrete for box culvert [Road 04-R ] | 19679.44 | 100% | 100% | 19679.44
JDH4-02-007-CN-5610 | JDH4-02-007-CN-5610 | Steel Reinforcement for box culverts [Road 04-R ](Completed) | 33891.12 | 100% | 100% | 33891.12
JDH4-02-007-CN-5610R | JDH4-02-007-CN-5610R | Steel Reinforcement for box culverts [Road 04-R ] | 135564.48 | 100% | 100% | 135564.48
JDH4-02-007-CN-5620 | JDH4-02-007-CN-5620 | Reinforced Concrete for box culvert [Road 04-R ] | 232469.74 | 100% | 100% | 232469.74
Road Works + Roundabout | Road Works + Roundabout |  | 3655865.47 |  | 100% | 3655865.47
Eartworks & Site grading | Eartworks & Site grading |  | 1552916.51 |  | 100% | 1552916.51
JDH4-02-007-CN-1810 | JDH4-02-007-CN-1810 | Road backfilling [Road 04-R ](Completed) | 551521.49 | 100% | 100% | 551521.49
JDH4-02-007-CN-1750 | JDH4-02-007-CN-1750 | Road excavation [Road 04-R ](Completed) | 14012.87 | 100% | 100% | 14012.87
JDH4-02-007-CN-1810R | JDH4-02-007-CN-1810R | Road backfilling [Road 04-R ] | 827282.24 | 100% | 100% | 827282.24
JDH4-02-007-CN-1750R | JDH4-02-007-CN-1750R | Road excavation [Road 04-R ] | 21019.3 | 100% | 100% | 21019.3
JDH4-02-007-CN-1930 | JDH4-02-007-CN-1930 | Subgrade [Road 04-R ] | 139080.6 | 100% | 100% | 139080.6
Asphalt Works | Asphalt Works |  | 931597.75 |  | 100% | 931597.75
JDH4-02-007-CN-1990 | JDH4-02-007-CN-1990 | Aggregate base course [Road 04-R ] | 141644.69 | 100% | 100% | 141644.69
JDH4-02-007-CN-2040 | JDH4-02-007-CN-2040 | Prime Coat (MC1) [Road 04-R ] | 78995.31 | 100% | 100% | 78995.31
JDH4-02-007-CN-2090 | JDH4-02-007-CN-2090 | Bituminous base course [Road 04-R ] | 710957.75 | 100% | 100% | 710957.75
Finishing Works | Finishing Works |  | 1171351.21 |  | 100% | 1171351.21
Asphalt Wearing Course | Asphalt Wearing Course |  | 418188.18 |  | 100% | 418188.18
JDH4-02-007-CN-2140 | JDH4-02-007-CN-2140 | Tack Coat (RC2) [Road 04-R ] | 41818.82 | 100% | 100% | 41818.82
JDH4-02-007-CN-2190 | JDH4-02-007-CN-2190 | Bituminous concrete wearing course [Road 04-R ] | 376369.36 | 100% | 100% | 376369.36
Precast Concrete Curb | Precast Concrete Curb |  | 260761.75 |  | 100% | 260761.75
JDH4-02-007-CN-2240 | JDH4-02-007-CN-2240 | Installation of Precast Concrete curb [Road 04-R ] | 260761.75 | 100% | 100% | 260761.75
Precast Interlocking block pavers | Precast Interlocking block pavers |  | 247979.91 |  | 100% | 247979.91
JDH4-02-007-CN-2290 | JDH4-02-007-CN-2290 | Installation of Interlocking block pavers for sidewalk/footpath [Road 04-R ] | 247979.91 | 100% | 100% | 247979.91
Pavement Markings | Pavement Markings |  | 70108.71 |  | 100% | 70108.71
JDH4-02-007-CN-2340 | JDH4-02-007-CN-2340 | Pavement markings [Road 04-R ] | 70108.71 | 100% | 100% | 70108.71
Traffic Signage | Traffic Signage |  | 119121.91 |  | 100% | 119121.91
JDH4-02-007-CN-2390 | JDH4-02-007-CN-2390 | Installation of Traffic Signs [Road 04-R ] | 119121.91 | 100% | 100% | 119121.91
Guardrail | Guardrail |  | 55190.75 |  | 100% | 55190.75
JDH4-02-007-CN-2400 | JDH4-02-007-CN-2400 | Installation of Guard rails [Road 04-R ] | 55190.75 | 100% | 100% | 55190.75
Storm Water Drainage | Storm Water Drainage |  | 616227.34 |  | 100% | 616227.34
Pipe Works | Pipe Works |  | 372950.21 |  | 100% | 372950.21
JDH4-02-007-CN-5370 | JDH4-02-007-CN-5370 | Excavation and Compaction (FDT) [Road 04-R ](Completed) | 13055.44 | 100% | 100% | 13055.44
JDH4-02-007-CN-5420 | JDH4-02-007-CN-5420 | Sand Bedding [Road 04-R ](Completed) | 6527.73 | 100% | 100% | 6527.73
JDH4-02-007-CN-5470 | JDH4-02-007-CN-5470 | Installation of GRP Pipe [Road 04-R ](Completed) | 91388.14 | 100% | 100% | 91388.14
JDH4-02-007-CN-5520 | JDH4-02-007-CN-5520 | Sand Cover & Warning Tape [Road 04-R ] | 18629.79 | 100% | 100% | 18629.79
JDH4-02-007-CN-5570 | JDH4-02-007-CN-5570 | Backfilling & Compaction [Road 04-R ] | 37259.53 | 100% | 100% | 37259.53
JDH4-02-007-CN-5370R | JDH4-02-007-CN-5370R | Excavation and Compaction (FDT) [Road 04-R ] | 24245.82 | 100% | 100% | 24245.82
JDH4-02-007-CN-5420R | JDH4-02-007-CN-5420R | Sand Bedding [Road 04-R ] | 12122.92 | 100% | 100% | 12122.92
JDH4-02-007-CN-5470R | JDH4-02-007-CN-5470R | Installation of GRP Pipe [Road 04-R ] | 169720.83 | 100% | 100% | 169720.83
Pipe Encasement | Pipe Encasement |  | 13406.24 |  | 100% | 13406.24
JDH4-02-007-CN-5840 | JDH4-02-007-CN-5840 | Pipe Encasement Works [Road 04-R ] | 13406.24 | 100% | 100% | 13406.24
Manholes | Manholes |  | 130842.92 |  | 100% | 130842.92
JDH4-02-007-CN-5670 | JDH4-02-007-CN-5670 | Installation of Precast Manhole Ring [Road 04-R ] | 130842.92 | 100% | 100% | 130842.92
Precast Acces Openinig | Precast Acces Openinig |  | 7569.02 |  | 100% | 7569.02
JDH4-02-007-CN-5720 | JDH4-02-007-CN-5720 | Installation of Precast Access Opening [Road 04-R ] | 7569.02 | 100% | 100% | 7569.02
Catch Basins | Catch Basins |  | 40998.84 |  | 100% | 40998.84
JDH4-02-007-CN-5760 | JDH4-02-007-CN-5760 | Construction of Catch basins [Road 04-R ] | 40998.84 | 100% | 100% | 40998.84
Concrete Outfalls | Concrete Outfalls |  | 50460.11 |  | 100% | 50460.11
JDH4-02-007-CN-5790 | JDH4-02-007-CN-5790 | Construction of Concrete outfall structure [Road 04-R ] | 50460.11 | 100% | 100% | 50460.11
Sewerage Network | Sewerage Network |  | 233847.07 |  | 100% | 233847.07
Pipe Works | Pipe Works |  | 151982.41 |  | 100% | 151982.41
JDH4-02-007-CN-4820 | JDH4-02-007-CN-4820 | Excavation & Compaction (FDT) [Road 04-R ](Completed) | 759.81 | 100% | 100% | 759.81
JDH4-02-007-CN-4820R | JDH4-02-007-CN-4820R | Excavation & Compaction (FDT) [Road 04-R ] | 14436.45 | 100% | 100% | 14436.45
JDH4-02-007-CN-4890 | JDH4-02-007-CN-4890 | Sand Bedding [Road 04-R ] | 7599.22 | 100% | 100% | 7599.22
JDH4-02-007-CN-4960 | JDH4-02-007-CN-4960 | Installation of GRP Pipe [Road 04-R ] | 75992.31 | 100% | 100% | 75992.31
JDH4-02-007-CN-5030 | JDH4-02-007-CN-5030 | Gravity Test [Road 04-R ] | 30396.93 | 100% | 100% | 30396.93
JDH4-02-007-CN-5100 | JDH4-02-007-CN-5100 | Sand Cover & Warning Tape [Road 04-R ] | 7599.22 | 100% | 100% | 7599.22
JDH4-02-007-CN-5170 | JDH4-02-007-CN-5170 | Backfilling & Compaction [Road 04-R ] | 15198.47 | 100% | 100% | 15198.47
Pipe Encasement | Pipe Encasement |  | 760.54 |  | 100% | 760.54
JDH4-02-007-CN-5310 | JDH4-02-007-CN-5310 | Pipe Encasement Works [Road 04-R ] | 760.54 | 100% | 100% | 760.54
Manholes | Manholes |  | 81104.12 |  | 100% | 81104.12
JDH4-02-007-CN-5240 | JDH4-02-007-CN-5240 | Installation of Manholes [Road 04-R ] | 81104.12 | 100% | 100% | 81104.12
TSE Network | TSE Network |  | 186231.54 |  | 100% | 186231.54
Pipe Works | Pipe Works |  | 160003.08 |  | 100% | 160003.08
JDH4-02-007-CN-4040 | JDH4-02-007-CN-4040 | Excavation and Compaction (FDT) [Road 04-R ] | 15169.19 | 100% | 100% | 15169.19
JDH4-02-007-CN-4110 | JDH4-02-007-CN-4110 | Sand Bedding [Road 04-R ] | 7584.62 | 100% | 100% | 7584.62
JDH4-02-007-CN-4180 | JDH4-02-007-CN-4180 | Installation of HDPE Pipe [Road 04-R ] | 75846 | 100% | 100% | 75846
JDH4-02-007-CN-4250 | JDH4-02-007-CN-4250 | Initial Pressure Test [Road 04-R ] | 30338.38 | 100% | 100% | 30338.38
JDH4-02-007-CN-4320 | JDH4-02-007-CN-4320 | Sand Cover & Warning [Road 04-R ] | 7584.62 | 100% | 100% | 7584.62
JDH4-02-007-CN-4390 | JDH4-02-007-CN-4390 | Backfilling & Compaction [Road 04-R ] | 15169.19 | 100% | 100% | 15169.19
JDH4-02-007-CN-4700 | JDH4-02-007-CN-4700 | Point of Connection [Road 04-R ] | 8311.08 | 100% | 100% | 8311.08
Pipe Encasement | Pipe Encasement |  | 7554.9 |  | 100% | 7554.9
JDH4-02-007-CN-4460 | JDH4-02-007-CN-4460 | Encasement for Pipes [Road 04-R ] | 7554.9 | 100% | 100% | 7554.9
Valves | Valves |  | 18673.56 |  | 100% | 18673.56
JDH4-02-007-CN-4530 | JDH4-02-007-CN-4530 | Installation of Gate Valves [Road 04-R ] | 18673.56 | 100% | 100% | 18673.56
Potable Network | Potable Network |  | 193744.83 |  | 100% | 193744.83
Pipe Works | Pipe Works |  | 124027.28 |  | 100% | 124027.28
JDH4-02-007-CN-3360 | JDH4-02-007-CN-3360 | Excavation and Compaction (FDT) [Road 04-R ] | 12402.74 | 100% | 100% | 12402.74
JDH4-02-007-CN-3430 | JDH4-02-007-CN-3430 | Sand Bedding [Road 04-R ] | 6201.37 | 100% | 100% | 6201.37
JDH4-02-007-CN-3500 | JDH4-02-007-CN-3500 | Installation of HDPE Pipe [Road 04-R ] | 62013.62 | 100% | 100% | 62013.62
JDH4-02-007-CN-3570 | JDH4-02-007-CN-3570 | Initial Pressure Test [Road 04-R ] | 24805.44 | 100% | 100% | 24805.44
JDH4-02-007-CN-3640 | JDH4-02-007-CN-3640 | Sand Cover & Warning Tape [Road 04-R ] | 6201.37 | 100% | 100% | 6201.37
JDH4-02-007-CN-3710 | JDH4-02-007-CN-3710 | Backfilling [Road 04-R ] | 12402.74 | 100% | 100% | 12402.74
Pipe Encasement | Pipe Encasement |  | 9796.16 |  | 100% | 9796.16
JDH4-02-007-CN-3780 | JDH4-02-007-CN-3780 | Encasement for Pipes [Road 04-R ] | 9796.16 | 100% | 100% | 9796.16
Valves | Valves |  | 15768.79 |  | 100% | 15768.79
JDH4-02-007-CN-3850 | JDH4-02-007-CN-3850 | Installation of Gate Valves [Road 04-R ] | 15768.79 | 100% | 100% | 15768.79
Fire Hydrant | Fire Hydrant |  | 44152.6 |  | 100% | 44152.6
JDH4-02-007-CN-3940 | JDH4-02-007-CN-3940 | Installation of 3-outlet fire hydrant [Road 04-R ] | 44152.6 | 100% | 100% | 44152.6
Electrical Works | Electrical Works |  | 386983.51 |  | 100% | 386983.51
Street Lighting | Street Lighting |  | 173158.79 |  | 100% | 173158.79
JDH4-02-007-CN-2830 | JDH4-02-007-CN-2830 | Installation of Road Crossing Ducts [Road 04-R ] | 17941.62 | 100% | 100% | 17941.62
JDH4-02-007-CN-2820 | JDH4-02-007-CN-2820 | Excavation for Low Voltage Cable [Road 04-R ] | 9991.1 | 100% | 100% | 9991.1
JDH4-02-007-CN-2880 | JDH4-02-007-CN-2880 | Installation of Low Voltage Cables [Road 04-R ] | 50825.95 | 100% | 100% | 50825.95
JDH4-02-007-CN-2920 | JDH4-02-007-CN-2920 | Installation of Lighting Poles [Road 04-R ] | 73193.61 | 100% | 100% | 73193.61
JDH4-02-007-CN-2960 | JDH4-02-007-CN-2960 | Installation of Lighting Luminaires [Road 04-R ] | 17422 | 100% | 100% | 17422
JDH4-02-007-CN-2990 | JDH4-02-007-CN-2990 | Installation of Earthing System [Road 04-R ] | 3784.51 | 100% | 100% | 3784.51
Telecommunication | Telecommunication |  | 213824.72 |  | 100% | 213824.72
JDH4-02-007-CN-3110 | JDH4-02-007-CN-3110 | Installation Road Crossing R/F 6 way 50mm HDPE Pipe [Road 04-R ] | 182034.85 | 100% | 100% | 182034.85
JDH4-02-007-CN-3180 | JDH4-02-007-CN-3180 | Installation Road Crossing Un R/F 6 way 50mm HDPE Pipe [Road 04-R ] | 3406.06 | 100% | 100% | 3406.06
JDH4-02-007-CN-3290 | JDH4-02-007-CN-3290 | Installation of Manholes [Road 04-R ] | 28383.81 | 100% | 100% | 28383.81
Road 08 | Road 08 |  | 5696664.36 |  | 100% | 5696664.36
Road Works + Roundabout | Road Works + Roundabout |  | 3190850.42 |  | 100% | 3190850.42
Eartworks & Site grading | Eartworks & Site grading |  | 1378559.54 |  | 100% | 1378559.54
JDH4-02-007-CN-1710 | JDH4-02-007-CN-1710 | Road excavation [Road 08 ](Completed) | 21754.74 | 100% | 100% | 21754.74
JDH4-02-007-CN-1770 | JDH4-02-007-CN-1770 | Road backfilling [Road 08 ](Completed) | 673400.08 | 100% | 100% | 673400.08
JDH4-02-007-CN-1770R | JDH4-02-007-CN-1770R | Road backfilling [Road 08 ] | 550963.7 | 100% | 100% | 550963.7
JDH4-02-007-CN-1710R | JDH4-02-007-CN-1710R | Road excavation [Road 08 ] | 9323.46 | 100% | 100% | 9323.46
JDH4-02-007-CN-1890 | JDH4-02-007-CN-1890 | Subgrade [Road 08 ] | 123117.55 | 100% | 100% | 123117.55
Asphalt Works | Asphalt Works |  | 825025.99 |  | 100% | 825025.99
JDH4-02-007-CN-1950 | JDH4-02-007-CN-1950 | Aggregate base course [Road 08 ] | 125409.15 | 100% | 100% | 125409.15
JDH4-02-007-CN-2000 | JDH4-02-007-CN-2000 | Prime Coat (MC1) [Road 08 ] | 70000.79 | 100% | 100% | 70000.79
JDH4-02-007-CN-2050 | JDH4-02-007-CN-2050 | Bituminous base course [Road 08 ] | 629616.05 | 100% | 100% | 629616.05
Finishing Works | Finishing Works |  | 987264.89 |  | 100% | 987264.89
Asphalt Wearing Course | Asphalt Wearing Course |  | 370629.53 |  | 100% | 370629.53
JDH4-02-007-CN-2100 | JDH4-02-007-CN-2100 | Tack Coat (RC2) [Road 08 ] | 36898.96 | 100% | 100% | 36898.96
JDH4-02-007-CN-2150 | JDH4-02-007-CN-2150 | Bituminous concrete wearing course [Road 08 ] | 333730.57 | 100% | 100% | 333730.57
Precast Concrete Curb | Precast Concrete Curb |  | 231115.34 |  | 100% | 231115.34
JDH4-02-007-CN-2200 | JDH4-02-007-CN-2200 | Installation of Precast Concrete curb [Road 08 ] | 231115.34 | 100% | 100% | 231115.34
Precast Interlocking block pavers | Precast Interlocking block pavers |  | 219785.33 |  | 100% | 219785.33
JDH4-02-007-CN-2250 | JDH4-02-007-CN-2250 | Installation of Interlocking block pavers for sidewalk/footpath [Road 08 ] | 219785.33 | 100% | 100% | 219785.33
Pavement Markings | Pavement Markings |  | 62150.42 |  | 100% | 62150.42
JDH4-02-007-CN-2300 | JDH4-02-007-CN-2300 | Pavement markings [Road 08 ] | 62150.42 | 100% | 100% | 62150.42
Traffic Signage | Traffic Signage |  | 103584.27 |  | 100% | 103584.27
JDH4-02-007-CN-2350 | JDH4-02-007-CN-2350 | Installation of Traffic Signs [Road 08 ] | 103584.27 | 100% | 100% | 103584.27
Storm Water Drainage | Storm Water Drainage |  | 873781.35 |  | 100% | 873781.35
Pipe Works | Pipe Works |  | 547596.42 |  | 100% | 547596.42
JDH4-02-007-CN-5330 | JDH4-02-007-CN-5330 | Excavation and Compaction (FDT) [Road 08 ](Completed) | 8213.94 | 100% | 100% | 8213.94
JDH4-02-007-CN-5380 | JDH4-02-007-CN-5380 | Sand Bedding [Road 08 ](Completed) | 4106.98 | 100% | 100% | 4106.98
JDH4-02-007-CN-5430 | JDH4-02-007-CN-5430 | Installation of GRP Pipe [Road 08 ](Completed) | 57497.63 | 100% | 100% | 57497.63
JDH4-02-007-CN-5480 | JDH4-02-007-CN-5480 | Sand Cover & Warning Tape [Road 08 ](Completed) | 4106.98 | 100% | 100% | 4106.98
JDH4-02-007-CN-5530 | JDH4-02-007-CN-5530 | Backfilling & Compaction [Road 08 ](Completed) | 8213.94 | 100% | 100% | 8213.94
JDH4-02-007-CN-5330R | JDH4-02-007-CN-5330R | Excavation and Compaction (FDT) [Road 08 ] | 46545.67 | 100% | 100% | 46545.67
JDH4-02-007-CN-5380R | JDH4-02-007-CN-5380R | Sand Bedding [Road 08 ] | 23272.86 | 100% | 100% | 23272.86
JDH4-02-007-CN-5430R | JDH4-02-007-CN-5430R | Installation of GRP Pipe [Road 08 ] | 325819.88 | 100% | 100% | 325819.88
JDH4-02-007-CN-5530R | JDH4-02-007-CN-5530R | Backfilling & Compaction [Road 08 ] | 46545.67 | 100% | 100% | 46545.67
JDH4-02-007-CN-5480R | JDH4-02-007-CN-5480R | Sand Cover & Warning Tape [Road 08 ] | 23272.86 | 100% | 100% | 23272.86
Pipe Encasement | Pipe Encasement |  | 20926.82 |  | 100% | 20926.82
JDH4-02-007-CN-5800 | JDH4-02-007-CN-5800 | Pipe Encasement Works [Road 08 ] | 20926.82 | 100% | 100% | 20926.82
Manholes | Manholes |  | 224206.55 |  | 100% | 224206.55
JDH4-02-007-CN-5630 | JDH4-02-007-CN-5630 | Installation of Precast Manhole Ring [Road 08 ] | 224206.55 | 100% | 100% | 224206.55
Precast Acces Openinig | Precast Acces Openinig |  | 11353.53 |  | 100% | 11353.53
JDH4-02-007-CN-5680 | JDH4-02-007-CN-5680 | Installation of Precast Access Opening [Road 08 ] | 11353.53 | 100% | 100% | 11353.53
Catch Basins | Catch Basins |  | 69698.03 |  | 100% | 69698.03
JDH4-02-007-CN-5730 | JDH4-02-007-CN-5730 | Construction of Catch basins [Road 08 ] | 69698.03 | 100% | 100% | 69698.03
Sewerage Network | Sewerage Network |  | 558310.64 |  | 100% | 558310.64
Pipe Works | Pipe Works |  | 329545.92 |  | 100% | 329545.92
JDH4-02-007-CN-4780 | JDH4-02-007-CN-4780 | Excavation & Compaction (FDT) [Road 08 ] | 32954.6 | 100% | 100% | 32954.6
JDH4-02-007-CN-4850 | JDH4-02-007-CN-4850 | Sand Bedding [Road 08 ] | 16477.28 | 100% | 100% | 16477.28
JDH4-02-007-CN-4920 | JDH4-02-007-CN-4920 | Installation of GRP Pipe [Road 08 ] | 164772.96 | 100% | 100% | 164772.96
JDH4-02-007-CN-4990 | JDH4-02-007-CN-4990 | Gravity Test [Road 08 ] | 65909.2 | 100% | 100% | 65909.2
JDH4-02-007-CN-5060 | JDH4-02-007-CN-5060 | Sand Cover & Warning Tape [Road 08 ] | 16477.28 | 100% | 100% | 16477.28
JDH4-02-007-CN-5130 | JDH4-02-007-CN-5130 | Backfilling & Compaction [Road 08 ] | 32954.6 | 100% | 100% | 32954.6
Pipe Encasement | Pipe Encasement |  | 1673.19 |  | 100% | 1673.19
JDH4-02-007-CN-5270 | JDH4-02-007-CN-5270 | Pipe Encasement Works [Road 08 ] | 1673.19 | 100% | 100% | 1673.19
Manholes | Manholes |  | 227091.53 |  | 100% | 227091.53
JDH4-02-007-CN-5200 | JDH4-02-007-CN-5200 | Installation of Manholes [Road 08 ] | 227091.53 | 100% | 100% | 227091.53
TSE Network | TSE Network |  | 229231.81 |  | 100% | 229231.81
Pipe Works | Pipe Works |  | 195413.82 |  | 100% | 195413.82
JDH4-02-007-CN-4000 | JDH4-02-007-CN-4000 | Excavation and Compaction (FDT) [Road 08 ] | 18710.26 | 100% | 100% | 18710.26
JDH4-02-007-CN-4070 | JDH4-02-007-CN-4070 | Sand Bedding [Road 08 ] | 9355.16 | 100% | 100% | 9355.16
JDH4-02-007-CN-4140 | JDH4-02-007-CN-4140 | Installation of HDPE Pipe [Road 08 ] | 93551.37 | 100% | 100% | 93551.37
JDH4-02-007-CN-4210 | JDH4-02-007-CN-4210 | Initial Pressure Test [Road 08 ] | 37420.53 | 100% | 100% | 37420.53
JDH4-02-007-CN-4280 | JDH4-02-007-CN-4280 | Sand Cover & Warning [Road 08 ] | 9355.16 | 100% | 100% | 9355.16
JDH4-02-007-CN-4350 | JDH4-02-007-CN-4350 | Backfilling & Compaction [Road 08 ] | 18710.26 | 100% | 100% | 18710.26
JDH4-02-007-CN-4660 | JDH4-02-007-CN-4660 | Point of Connection [Road 08 ] | 8311.08 | 100% | 100% | 8311.08
Pipe Encasement | Pipe Encasement |  | 9368.07 |  | 100% | 9368.07
JDH4-02-007-CN-4420 | JDH4-02-007-CN-4420 | Encasement for Pipes [Road 08 ] | 9368.07 | 100% | 100% | 9368.07
Valves | Valves |  | 11204.14 |  | 100% | 11204.14
JDH4-02-007-CN-4490 | JDH4-02-007-CN-4490 | Installation of Gate Valves [Road 08 ] | 11204.14 | 100% | 100% | 11204.14
Risers | Risers |  | 13245.78 |  | 100% | 13245.78
JDH4-02-007-CN-4730 | JDH4-02-007-CN-4730 | Installation of Irrigation Riser with [Road 08 ] | 13245.78 | 100% | 100% | 13245.78
Potable Network | Potable Network |  | 199289.73 |  | 100% | 199289.73
Pipe Works | Pipe Works |  | 125752.87 |  | 100% | 125752.87
JDH4-02-007-CN-3320 | JDH4-02-007-CN-3320 | Excavation and Compaction (FDT) [Road 08 ] | 12575.3 | 100% | 100% | 12575.3
JDH4-02-007-CN-3390 | JDH4-02-007-CN-3390 | Sand Bedding [Road 08 ] | 6287.65 | 100% | 100% | 6287.65
JDH4-02-007-CN-3460 | JDH4-02-007-CN-3460 | Installation of HDPE Pipe [Road 08 ] | 62876.41 | 100% | 100% | 62876.41
JDH4-02-007-CN-3530 | JDH4-02-007-CN-3530 | Initial Pressure Test [Road 08 ] | 25150.56 | 100% | 100% | 25150.56
JDH4-02-007-CN-3600 | JDH4-02-007-CN-3600 | Sand Cover & Warning Tape [Road 08 ] | 6287.65 | 100% | 100% | 6287.65
JDH4-02-007-CN-3670 | JDH4-02-007-CN-3670 | Backfilling [Road 08 ] | 12575.3 | 100% | 100% | 12575.3
Pipe Encasement | Pipe Encasement |  | 9936.1 |  | 100% | 9936.1
JDH4-02-007-CN-3740 | JDH4-02-007-CN-3740 | Encasement for Pipes [Road 08 ] | 9936.1 | 100% | 100% | 9936.1
Valves | Valves |  | 13140.65 |  | 100% | 13140.65
JDH4-02-007-CN-3810 | JDH4-02-007-CN-3810 | Installation of Gate Valves [Road 08 ] | 13140.65 | 100% | 100% | 13140.65
Fire Hydrant | Fire Hydrant |  | 50460.11 |  | 100% | 50460.11
JDH4-02-007-CN-3900 | JDH4-02-007-CN-3900 | Installation of 3-outlet fire hydrant [Road 08 ] | 50460.11 | 100% | 100% | 50460.11
Electrical Works | Electrical Works |  | 645200.42 |  | 100% | 645200.42
LV Cables | LV Cables |  | 195304.1 |  | 100% | 195304.1
Low Voltage Cable | Low Voltage Cable |  | 195304.1 |  | 100% | 195304.1
JDH4-02-007-CN-2740 | JDH4-02-007-CN-2740 | Installation of Ring Main Unit (RMU) 3-way, 13.8kV [Road 08 ] | 63075.14 | 100% | 100% | 63075.14
JDH4-02-007-CN-2595 | JDH4-02-007-CN-2595 | Excavation for Low Voltage Cable [Road 08 ] | 10823.69 | 100% | 100% | 10823.69
JDH4-02-007-CN-2600 | JDH4-02-007-CN-2600 | Installation of Low Voltage Cables [Road 08 ] | 29946.31 | 100% | 100% | 29946.31
JDH4-02-007-CN-2730 | JDH4-02-007-CN-2730 | Installation of Unit Substation , 13.8/0.4 kV, 500kVA with RMU [Road 08 ] | 75690.17 | 100% | 100% | 75690.17
JDH4-02-007-CN-2710 | JDH4-02-007-CN-2710 | Installation of Low Voltage Distribution Panel (Main: 100A, MCCB, 5-50A, MCCB) [Road 08 ] | 15768.79 | 100% | 100% | 15768.79
Street Lighting | Street Lighting |  | 175355.47 |  | 100% | 175355.47
JDH4-02-007-CN-2760 | JDH4-02-007-CN-2760 | Installation of Road Crossing Ducts [Road 08 ] | 17695.84 | 100% | 100% | 17695.84
JDH4-02-007-CN-2890 | JDH4-02-007-CN-2890 | Installation of Lighting Poles [Road 08 ] | 79467.35 | 100% | 100% | 79467.35
JDH4-02-007-CN-2750 | JDH4-02-007-CN-2750 | Excavation for Low Voltage Cable [Road 08 ] | 8325.92 | 100% | 100% | 8325.92
JDH4-02-007-CN-2930 | JDH4-02-007-CN-2930 | Installation of Lighting Luminaires [Road 08 ] | 19910.85 | 100% | 100% | 19910.85
JDH4-02-007-CN-2840 | JDH4-02-007-CN-2840 | Installation of Low Voltage Cables [Road 08 ] | 42386.49 | 100% | 100% | 42386.49
JDH4-02-007-CN-2970 | JDH4-02-007-CN-2970 | Installation of Earthing System [Road 08 ] | 7569.02 | 100% | 100% | 7569.02
Telecommunication | Telecommunication |  | 274540.85 |  | 100% | 274540.85
JDH4-02-007-CN-3070 | JDH4-02-007-CN-3070 | Installation Road Crossing R/F 6 way 50mm HDPE Pipe [Road 08 ] | 126781.03 | 100% | 100% | 126781.03
JDH4-02-007-CN-3140 | JDH4-02-007-CN-3140 | Installation Road Crossing Un R/F 6 way 50mm HDPE Pipe [Road 08 ] | 3973.73 | 100% | 100% | 3973.73
JDH4-02-007-CN-3250 | JDH4-02-007-CN-3250 | Installation of Manholes [Road 08 ] | 45414.1 | 100% | 100% | 45414.1
JDH4-02-007-CN-3200 | JDH4-02-007-CN-3200 | Installation of 2 x 32 mm diameter HDPE ducts [Road 08 ] | 98371.99 | 100% | 100% | 98371.99
Road 07-N | Road 07-N |  | 5511432.43 |  | 100% | 5511432.43
Road Works | Road Works |  | 3118311.38 |  | 100% | 3118311.38
Eartworks & Site grading | Eartworks & Site grading |  | 1345959.82 |  | 100% | 1345959.82
JDH4-02-007-CN-1730 | JDH4-02-007-CN-1730 | Road excavation [Road 07-N ](Completed) | 13629.33 | 100% | 100% | 13629.33
JDH4-02-007-CN-1790 | JDH4-02-007-CN-1790 | Road backfilling [Road 07-N ](Completed) | 418403.53 | 100% | 100% | 418403.53
JDH4-02-007-CN-1790R | JDH4-02-007-CN-1790R | Road backfilling [Road 07-N ] | 777035.12 | 100% | 100% | 777035.12
JDH4-02-007-CN-1730R | JDH4-02-007-CN-1730R | Road excavation [Road 07-N ] | 16658.08 | 100% | 100% | 16658.08
JDH4-02-007-CN-1910 | JDH4-02-007-CN-1910 | Subgrade [Road 07-N ] | 120233.76 | 100% | 100% | 120233.76
Asphalt Works | Asphalt Works |  | 805652.45 |  | 100% | 805652.45
JDH4-02-007-CN-1970 | JDH4-02-007-CN-1970 | Aggregate base course [Road 07-N ] | 122460.38 | 100% | 100% | 122460.38
JDH4-02-007-CN-2020 | JDH4-02-007-CN-2020 | Prime Coat (MC1) [Road 07-N ] | 68436.53 | 100% | 100% | 68436.53
JDH4-02-007-CN-2070 | JDH4-02-007-CN-2070 | Bituminous base course [Road 07-N ] | 614755.54 | 100% | 100% | 614755.54
Finishing Works | Finishing Works |  | 966699.11 |  | 100% | 966699.11
Asphalt Wearing Course | Asphalt Wearing Course |  | 362429.75 |  | 100% | 362429.75
JDH4-02-007-CN-2120 | JDH4-02-007-CN-2120 | Tack Coat (RC2) [Road 07-N ] | 36078.98 | 100% | 100% | 36078.98
JDH4-02-007-CN-2170 | JDH4-02-007-CN-2170 | Bituminous concrete wearing course [Road 07-N ] | 326350.77 | 100% | 100% | 326350.77
Precast Concrete Curb | Precast Concrete Curb |  | 225534.37 |  | 100% | 225534.37
JDH4-02-007-CN-2220 | JDH4-02-007-CN-2220 | Installation of Precast Concrete curb [Road 07-N ] | 225534.37 | 100% | 100% | 225534.37
Precast Interlocking block pavers | Precast Interlocking block pavers |  | 214487.01 |  | 100% | 214487.01
JDH4-02-007-CN-2270 | JDH4-02-007-CN-2270 | Installation of Interlocking block pavers for sidewalk/footpath [Road 07-N ] | 214487.01 | 100% | 100% | 214487.01
Pavement Markings | Pavement Markings |  | 60663.71 |  | 100% | 60663.71
JDH4-02-007-CN-2320 | JDH4-02-007-CN-2320 | Pavement markings [Road 07-N ] | 60663.71 | 100% | 100% | 60663.71
Traffic Signage | Traffic Signage |  | 103584.27 |  | 100% | 103584.27
JDH4-02-007-CN-2370 | JDH4-02-007-CN-2370 | Installation of Traffic Signs [Road 07-N ] | 103584.27 | 100% | 100% | 103584.27
Storm Water Drainage | Storm Water Drainage |  | 936796.6 |  | 100% | 936796.6
Pipe Works | Pipe Works |  | 649331.81 |  | 100% | 649331.81
JDH4-02-007-CN-5350 | JDH4-02-007-CN-5350 | Excavation and Compaction (FDT) [Road 07-N ] | 64933.15 | 100% | 100% | 64933.15
JDH4-02-007-CN-5400 | JDH4-02-007-CN-5400 | Sand Bedding [Road 07-N ] | 32466.61 | 100% | 100% | 32466.61
JDH4-02-007-CN-5450 | JDH4-02-007-CN-5450 | Installation of GRP Pipe [Road 07-N ] | 454532.29 | 100% | 100% | 454532.29
JDH4-02-007-CN-5500 | JDH4-02-007-CN-5500 | Sand Cover & Warning Tape [Road 07-N ] | 32466.61 | 100% | 100% | 32466.61
JDH4-02-007-CN-5550 | JDH4-02-007-CN-5550 | Backfilling & Compaction [Road 07-N ] | 64933.15 | 100% | 100% | 64933.15
Pipe Encasement | Pipe Encasement |  | 24850.59 |  | 100% | 24850.59
JDH4-02-007-CN-5820 | JDH4-02-007-CN-5820 | Pipe Encasement Works [Road 07-N ] | 24850.59 | 100% | 100% | 24850.59
Manholes | Manholes |  | 130787.16 |  | 100% | 130787.16
JDH4-02-007-CN-5650 | JDH4-02-007-CN-5650 | Installation of Precast Manhole Ring [Road 07-N ] | 130787.16 | 100% | 100% | 130787.16
Precast Acces Openinig | Precast Acces Openinig |  | 7569.02 |  | 100% | 7569.02
JDH4-02-007-CN-5700 | JDH4-02-007-CN-5700 | Installation of Precast Access Opening [Road 07-N ] | 7569.02 | 100% | 100% | 7569.02
Catch Basins | Catch Basins |  | 73797.91 |  | 100% | 73797.91
JDH4-02-007-CN-5740 | JDH4-02-007-CN-5740 | Construction of Catch basins [Road 07-N ] | 73797.91 | 100% | 100% | 73797.91
Concrete Outfalls | Concrete Outfalls |  | 50460.11 |  | 100% | 50460.11
JDH4-02-007-CN-5770 | JDH4-02-007-CN-5770 | Construction of Concrete outfall structure [Road 07-N ] | 50460.11 | 100% | 100% | 50460.11
Sewerage Network | Sewerage Network |  | 489984.35 |  | 100% | 489984.35
Pipe Works | Pipe Works |  | 326102.92 |  | 100% | 326102.92
JDH4-02-007-CN-4800 | JDH4-02-007-CN-4800 | Excavation & Compaction (FDT) [Road 07-N ] | 32610.3 | 100% | 100% | 32610.3
JDH4-02-007-CN-4870 | JDH4-02-007-CN-4870 | Sand Bedding [Road 07-N ] | 16305.13 | 100% | 100% | 16305.13
JDH4-02-007-CN-4940 | JDH4-02-007-CN-4940 | Installation of GRP Pipe [Road 07-N ] | 163051.46 | 100% | 100% | 163051.46
JDH4-02-007-CN-5010 | JDH4-02-007-CN-5010 | Gravity Test [Road 07-N ] | 65220.6 | 100% | 100% | 65220.6
JDH4-02-007-CN-5080 | JDH4-02-007-CN-5080 | Sand Cover & Warning Tape [Road 07-N ] | 16305.13 | 100% | 100% | 16305.13
JDH4-02-007-CN-5150 | JDH4-02-007-CN-5150 | Backfilling & Compaction [Road 07-N ] | 32610.3 | 100% | 100% | 32610.3
Pipe Encasement | Pipe Encasement |  | 1673.19 |  | 100% | 1673.19
JDH4-02-007-CN-5290 | JDH4-02-007-CN-5290 | Pipe Encasement Works [Road 07-N ] | 1673.19 | 100% | 100% | 1673.19
Manholes | Manholes |  | 162208.24 |  | 100% | 162208.24
JDH4-02-007-CN-5220 | JDH4-02-007-CN-5220 | Installation of Manholes [Road 07-N ] | 162208.24 | 100% | 100% | 162208.24
TSE Network | TSE Network |  | 244612.82 |  | 100% | 244612.82
Pipe Works | Pipe Works |  | 214076.25 |  | 100% | 214076.25
JDH4-02-007-CN-4020 | JDH4-02-007-CN-4020 | Excavation and Compaction (FDT) [Road 07-N ] | 20576.51 | 100% | 100% | 20576.51
JDH4-02-007-CN-4090 | JDH4-02-007-CN-4090 | Sand Bedding [Road 07-N ] | 10288.28 | 100% | 100% | 10288.28
JDH4-02-007-CN-4160 | JDH4-02-007-CN-4160 | Installation of HDPE Pipe [Road 07-N ] | 102882.58 | 100% | 100% | 102882.58
JDH4-02-007-CN-4230 | JDH4-02-007-CN-4230 | Initial Pressure Test [Road 07-N ] | 41153.01 | 100% | 100% | 41153.01
JDH4-02-007-CN-4370 | JDH4-02-007-CN-4370 | Backfilling & Compaction [Road 07-N ] | 20576.51 | 100% | 100% | 20576.51
JDH4-02-007-CN-4300 | JDH4-02-007-CN-4300 | Sand Cover & Warning [Road 07-N ] | 10288.28 | 100% | 100% | 10288.28
JDH4-02-007-CN-4680 | JDH4-02-007-CN-4680 | Point of Connection [Road 07-N ] | 8311.08 | 100% | 100% | 8311.08
Pipe Encasement | Pipe Encasement |  | 9821.37 |  | 100% | 9821.37
JDH4-02-007-CN-4440 | JDH4-02-007-CN-4440 | Encasement for Pipes [Road 07-N ] | 9821.37 | 100% | 100% | 9821.37
Valves | Valves |  | 7469.42 |  | 100% | 7469.42
JDH4-02-007-CN-4510 | JDH4-02-007-CN-4510 | Installation of Gate Valves [Road 07-N ] | 7469.42 | 100% | 100% | 7469.42
Risers | Risers |  | 13245.78 |  | 100% | 13245.78
JDH4-02-007-CN-4750 | JDH4-02-007-CN-4750 | Installation of Irrigation Riser with [Road 07-N ] | 13245.78 | 100% | 100% | 13245.78
Potable Network | Potable Network |  | 167864.18 |  | 100% | 167864.18
Pipe Works | Pipe Works |  | 98143.31 |  | 100% | 98143.31
JDH4-02-007-CN-3340 | JDH4-02-007-CN-3340 | Excavation and Compaction (FDT) [Road 07-N ] | 9814.34 | 100% | 100% | 9814.34
JDH4-02-007-CN-3410 | JDH4-02-007-CN-3410 | Sand Bedding [Road 07-N ] | 4907.17 | 100% | 100% | 4907.17
JDH4-02-007-CN-3480 | JDH4-02-007-CN-3480 | Installation of HDPE Pipe [Road 07-N ] | 49071.64 | 100% | 100% | 49071.64
JDH4-02-007-CN-3550 | JDH4-02-007-CN-3550 | Initial Pressure Test [Road 07-N ] | 19628.65 | 100% | 100% | 19628.65
JDH4-02-007-CN-3620 | JDH4-02-007-CN-3620 | Sand Cover & Warning Tape [Road 07-N ] | 4907.17 | 100% | 100% | 4907.17
JDH4-02-007-CN-3690 | JDH4-02-007-CN-3690 | Backfilling [Road 07-N ] | 9814.34 | 100% | 100% | 9814.34
Pipe Encasement | Pipe Encasement |  | 7696.98 |  | 100% | 7696.98
JDH4-02-007-CN-3760 | JDH4-02-007-CN-3760 | Encasement for Pipes [Road 07-N ] | 7696.98 | 100% | 100% | 7696.98
Valves | Valves |  | 5256.26 |  | 100% | 5256.26
JDH4-02-007-CN-3830 | JDH4-02-007-CN-3830 | Installation of Gate Valves [Road 07-N ] | 5256.26 | 100% | 100% | 5256.26
Fire Hydrant | Fire Hydrant |  | 56767.63 |  | 100% | 56767.63
JDH4-02-007-CN-3920 | JDH4-02-007-CN-3920 | Installation of 3-outlet fire hydrant [Road 07-N ] | 56767.63 | 100% | 100% | 56767.63
Electrical Works | Electrical Works |  | 553863.1 |  | 100% | 553863.1
LV Cables | LV Cables |  | 35076.36 |  | 100% | 35076.36
Low Voltage Cable | Low Voltage Cable |  | 35076.36 |  | 100% | 35076.36
JDH4-02-007-CN-2630 | JDH4-02-007-CN-2630 | Excavation for Low Voltage Cable [Road 07-N ] | 9385.58 | 100% | 100% | 9385.58
JDH4-02-007-CN-2640 | JDH4-02-007-CN-2640 | Installation of Low Voltage Cables [Road 07-N ] | 25690.78 | 100% | 100% | 25690.78
Street Lighting | Street Lighting |  | 267583.69 |  | 100% | 267583.69
JDH4-02-007-CN-2790 | JDH4-02-007-CN-2790 | Installation of Road Crossing Ducts [Road 07-N ] | 17204.29 | 100% | 100% | 17204.29
JDH4-02-007-CN-2940 | JDH4-02-007-CN-2940 | Installation of Lighting Luminaires [Road 07-N ] | 22897.48 | 100% | 100% | 22897.48
JDH4-02-007-CN-2900 | JDH4-02-007-CN-2900 | Installation of Lighting Poles [Road 07-N ] | 96197.32 | 100% | 100% | 96197.32
JDH4-02-007-CN-2780 | JDH4-02-007-CN-2780 | Excavation for Low Voltage Cable [Road 07-N ] | 17282.59 | 100% | 100% | 17282.59
JDH4-02-007-CN-2860 | JDH4-02-007-CN-2860 | Installation of Low Voltage Cables [Road 07-N ] | 88141.2 | 100% | 100% | 88141.2
JDH4-02-007-CN-3000 | JDH4-02-007-CN-3000 | Installation of Street Lighting Feeder pillars [Road 07-N ] | 22076.3 | 100% | 100% | 22076.3
JDH4-02-007-CN-3010 | JDH4-02-007-CN-3010 | Installation of Earthing System [Road 07-N ] | 3784.51 | 100% | 100% | 3784.51
Telecommunication | Telecommunication |  | 251203.05 |  | 100% | 251203.05
JDH4-02-007-CN-3090 | JDH4-02-007-CN-3090 | Installation Road Crossing R/F 6 way 50mm HDPE Pipe [Road 07-N ] | 145325.12 | 100% | 100% | 145325.12
JDH4-02-007-CN-3160 | JDH4-02-007-CN-3160 | Installation Road Crossing Un R/F 6 way 50mm HDPE Pipe [Road 07-N ] | 3973.73 | 100% | 100% | 3973.73
JDH4-02-007-CN-3270 | JDH4-02-007-CN-3270 | Installation of Manholes [Road 07-N ] | 39737.34 | 100% | 100% | 39737.34
JDH4-02-007-CN-3210 | JDH4-02-007-CN-3210 | Installation of 2 x 32 mm diameter HDPE ducts [Road 07-N ] | 62166.86 | 100% | 100% | 62166.86
Road 01 | Road 01 |  | 3400633.43 |  | 98.43% | 3347186.75
Road Works (Roundabout) | Road Works (Roundabout) |  | 826699 |  | 93.53% | 773252.32
Eartworks & Site grading | Eartworks & Site grading |  | 357790.57 |  | 100% | 357790.57
JDH4-02-007-CN-1720 | JDH4-02-007-CN-1720 | Road excavation [Road 01 ] | 8053.45 | 100% | 100% | 8053.45
JDH4-02-007-CN-1780 | JDH4-02-007-CN-1780 | Road backfilling [Road 01 ] | 317788.32 | 100% | 100% | 317788.32
JDH4-02-007-CN-1900 | JDH4-02-007-CN-1900 | Subgrade [Road 01 ] | 31948.8 | 100% | 100% | 31948.8
Asphalt Works | Asphalt Works |  | 213995.02 |  | 100% | 213995.02
JDH4-02-007-CN-1960 | JDH4-02-007-CN-1960 | Aggregate base course [Road 01 ] | 32540.46 | 100% | 100% | 32540.46
JDH4-02-007-CN-2010 | JDH4-02-007-CN-2010 | Prime Coat (MC1) [Road 01 ] | 17989.03 | 100% | 100% | 17989.03
JDH4-02-007-CN-2060 | JDH4-02-007-CN-2060 | Bituminous base course [Road 01 ] | 163465.53 | 100% | 100% | 163465.53
Finishing Works | Finishing Works |  | 254913.41 |  | 79.03% | 201466.73
Asphalt Wearing Course | Asphalt Wearing Course |  | 95937.28 |  | 100% | 95937.28
JDH4-02-007-CN-2110 | JDH4-02-007-CN-2110 | Tack Coat (RC2) [Road 01 ] | 9429.73 | 100% | 100% | 9429.73
JDH4-02-007-CN-2160 | JDH4-02-007-CN-2160 | Bituminous concrete wearing course [Road 01 ] | 86507.55 | 100% | 100% | 86507.55
Precast Concrete Curb | Precast Concrete Curb |  | 59926.12 |  | 100% | 59926.12
JDH4-02-007-CN-2210 | JDH4-02-007-CN-2210 | Installation of Precast Concrete curb [Road 01 ] | 59926.12 | 100% | 100% | 59926.12
Precast Interlocking block pavers | Precast Interlocking block pavers |  | 57004.16 |  | 80% | 45603.33
JDH4-02-007-CN-2260 | JDH4-02-007-CN-2260 | Installation of Interlocking block pavers for sidewalk/footpath [Road 01 ] | 57004.16 | 80% | 80% | 45603.33
Pavement Markings | Pavement Markings |  | 16149.78 |  | 0% | 0
JDH4-02-007-CN-2310 | JDH4-02-007-CN-2310 | Pavement markings [Road 01 ] | 16149.78 | 0% | 0% | 0
Traffic Signage | Traffic Signage |  | 25896.07 |  | 0% | 0
JDH4-02-007-CN-2360 | JDH4-02-007-CN-2360 | Installation of Traffic Signs [Road 01 ] | 25896.07 | 0% | 0% | 0
Storm Water Drainage | Storm Water Drainage |  | 131305.17 |  | 100% | 131305.17
Pipe Works | Pipe Works |  | 26247.15 |  | 100% | 26247.15
JDH4-02-007-CN-5340 | JDH4-02-007-CN-5340 | Excavation and Compaction (FDT) [Road 01 ] | 2624.71 | 100% | 100% | 2624.71
JDH4-02-007-CN-5390 | JDH4-02-007-CN-5390 | Sand Bedding [Road 01 ] | 1312.36 | 100% | 100% | 1312.36
JDH4-02-007-CN-5440 | JDH4-02-007-CN-5440 | Installation of GRP Pipe [Road 01 ] | 18373.01 | 100% | 100% | 18373.01
JDH4-02-007-CN-5490 | JDH4-02-007-CN-5490 | Sand Cover & Warning Tape [Road 01 ] | 1312.36 | 100% | 100% | 1312.36
JDH4-02-007-CN-5540 | JDH4-02-007-CN-5540 | Backfilling & Compaction [Road 01 ] | 2624.71 | 100% | 100% | 2624.71
Pipe Encasement | Pipe Encasement |  | 1307.93 |  | 100% | 1307.93
JDH4-02-007-CN-5810 | JDH4-02-007-CN-5810 | Pipe Encasement Works [Road 01 ] | 1307.93 | 100% | 100% | 1307.93
Manholes | Manholes |  | 74735.52 |  | 100% | 74735.52
JDH4-02-007-CN-5640 | JDH4-02-007-CN-5640 | Installation of Precast Manhole Ring [Road 01 ] | 74735.52 | 100% | 100% | 74735.52
Precast Acces Openinig | Precast Acces Openinig |  | 3784.51 |  | 100% | 3784.51
JDH4-02-007-CN-5690 | JDH4-02-007-CN-5690 | Installation of Precast Access Opening [Road 01 ] | 3784.51 | 100% | 100% | 3784.51
Concrete Outfalls | Concrete Outfalls |  | 25230.06 |  | 100% | 25230.06
JDH4-02-007-CN-5780 | JDH4-02-007-CN-5780 | Construction of Concrete outfall structure [Road 01 ] | 25230.06 | 100% | 100% | 25230.06
Sewerage Network | Sewerage Network |  | 134037.33 |  | 100% | 134037.33
Pipe Works | Pipe Works |  | 52628.99 |  | 100% | 52628.99
JDH4-02-007-CN-4790 | JDH4-02-007-CN-4790 | Excavation & Compaction (FDT) [Road 01 ] | 5262.9 | 100% | 100% | 5262.9
JDH4-02-007-CN-4860 | JDH4-02-007-CN-4860 | Sand Bedding [Road 01 ] | 2631.45 | 100% | 100% | 2631.45
JDH4-02-007-CN-4930 | JDH4-02-007-CN-4930 | Installation of GRP Pipe [Road 01 ] | 26314.49 | 100% | 100% | 26314.49
JDH4-02-007-CN-5000 | JDH4-02-007-CN-5000 | Gravity Test [Road 01 ] | 10525.8 | 100% | 100% | 10525.8
JDH4-02-007-CN-5070 | JDH4-02-007-CN-5070 | Sand Cover & Warning Tape [Road 01 ] | 2631.45 | 100% | 100% | 2631.45
JDH4-02-007-CN-5140 | JDH4-02-007-CN-5140 | Backfilling & Compaction [Road 01 ] | 5262.9 | 100% | 100% | 5262.9
Pipe Encasement | Pipe Encasement |  | 304.22 |  | 100% | 304.22
JDH4-02-007-CN-5280 | JDH4-02-007-CN-5280 | Pipe Encasement Works [Road 01 ] | 304.22 | 100% | 100% | 304.22
Manholes | Manholes |  | 81104.12 |  | 100% | 81104.12
JDH4-02-007-CN-5210 | JDH4-02-007-CN-5210 | Installation of Manholes [Road 01 ] | 81104.12 | 100% | 100% | 81104.12
TSE Network | TSE Network |  | 315346.48 |  | 100% | 315346.48
Pipe Works | Pipe Works |  | 199841.72 |  | 100% | 199841.72
JDH4-02-007-CN-4010 | JDH4-02-007-CN-4010 | Excavation and Compaction (FDT) [Road 01 ](Completed) | 4579.9 | 100% | 100% | 4579.9
JDH4-02-007-CN-4150 | JDH4-02-007-CN-4150 | Installation of HDPE Pipe [Road 01 ](Completed) | 22899.5 | 100% | 100% | 22899.5
JDH4-02-007-CN-4080 | JDH4-02-007-CN-4080 | Sand Bedding [Road 01 ](Completed) | 2289.96 | 100% | 100% | 2289.96
JDH4-02-007-CN-4290 | JDH4-02-007-CN-4290 | Sand Cover & Warning [Road 01 ](Completed) | 2106.76 | 100% | 100% | 2106.76
JDH4-02-007-CN-4010R | JDH4-02-007-CN-4010R | Excavation and Compaction (FDT) [Road 01 ] | 13739.69 | 100% | 100% | 13739.69
JDH4-02-007-CN-4080R | JDH4-02-007-CN-4080R | Sand Bedding [Road 01 ] | 6869.87 | 100% | 100% | 6869.87
JDH4-02-007-CN-4150R | JDH4-02-007-CN-4150R | Installation of HDPE Pipe [Road 01 ] | 68698.5 | 100% | 100% | 68698.5
JDH4-02-007-CN-4220 | JDH4-02-007-CN-4220 | Initial Pressure Test [Road 01 ] | 36654.89 | 100% | 100% | 36654.89
JDH4-02-007-CN-4360 | JDH4-02-007-CN-4360 | Backfilling & Compaction [Road 01 ] | 18327.45 | 100% | 100% | 18327.45
JDH4-02-007-CN-4290R | JDH4-02-007-CN-4290R | Sand Cover & Warning [Road 01 ] | 7053.06 | 100% | 100% | 7053.06
JDH4-02-007-CN-4670 | JDH4-02-007-CN-4670 | Point of Connection [Road 01 ] | 16622.15 | 100% | 100% | 16622.15
Pipe Encasement | Pipe Encasement |  | 9065.88 |  | 100% | 9065.88
JDH4-02-007-CN-4430 | JDH4-02-007-CN-4430 | Encasement for Pipes [Road 01 ] | 9065.88 | 100% | 100% | 9065.88
Valves | Valves |  | 93193.1 |  | 100% | 93193.1
JDH4-02-007-CN-4500 | JDH4-02-007-CN-4500 | Installation of Gate Valves [Road 01 ] | 11204.14 | 100% | 100% | 11204.14
JDH4-02-007-CN-4550 | JDH4-02-007-CN-4550 | Installation of Butterfly Valves [Road 01 ] | 44152.6 | 100% | 100% | 44152.6
JDH4-02-007-CN-4560 | JDH4-02-007-CN-4560 | Installation of Washout Valves [Road 01 ] | 23329.08 | 100% | 100% | 23329.08
JDH4-02-007-CN-4580 | JDH4-02-007-CN-4580 | Installation of Air Valves [Road 01 ] | 14507.28 | 100% | 100% | 14507.28
Risers | Risers |  | 13245.78 |  | 100% | 13245.78
JDH4-02-007-CN-4740 | JDH4-02-007-CN-4740 | Installation of Irrigation Riser with [Road 01 ] | 13245.78 | 100% | 100% | 13245.78
Potable Network | Potable Network |  | 1242732.96 |  | 100% | 1242732.96
Pipe Works | Pipe Works |  | 176873.66 |  | 100% | 176873.66
JDH4-02-007-CN-3330 | JDH4-02-007-CN-3330 | Excavation and Compaction (FDT) [Road 01 ] | 17687.38 | 100% | 100% | 17687.38
JDH4-02-007-CN-3470 | JDH4-02-007-CN-3470 | Installation of HDPE Pipe [Road 01 ] | 88436.81 | 100% | 100% | 88436.81
JDH4-02-007-CN-3540 | JDH4-02-007-CN-3540 | Initial Pressure Test [Road 01 ] | 35374.71 | 100% | 100% | 35374.71
JDH4-02-007-CN-3610 | JDH4-02-007-CN-3610 | Sand Cover & Warning Tape [Road 01 ] | 8843.69 | 100% | 100% | 8843.69
JDH4-02-007-CN-3680 | JDH4-02-007-CN-3680 | Backfilling [Road 01 ] | 17687.38 | 100% | 100% | 17687.38
JDH4-02-007-CN-3400 | JDH4-02-007-CN-3400 | Sand Bedding [Road 01 ] | 8843.69 | 100% | 100% | 8843.69
Pipe Encasement | Pipe Encasement |  | 13294.79 |  | 100% | 13294.79
JDH4-02-007-CN-3750 | JDH4-02-007-CN-3750 | Encasement for Pipes [Road 01 ] | 13294.79 | 100% | 100% | 13294.79
Valves | Valves |  | 141183.18 |  | 100% | 141183.18
JDH4-02-007-CN-3820 | JDH4-02-007-CN-3820 | Installation of Gate Valves [Road 01 ] | 13140.65 | 100% | 100% | 13140.65
JDH4-02-007-CN-3870 | JDH4-02-007-CN-3870 | Installation of Butterfly valves [Road 01 ] | 37845.08 | 100% | 100% | 37845.08
JDH4-02-007-CN-3880 | JDH4-02-007-CN-3880 | Installation of Washout valves [Road 01 ] | 29645.31 | 100% | 100% | 29645.31
JDH4-02-007-CN-3890 | JDH4-02-007-CN-3890 | Installation of Air valves [Road 01 ] | 60552.14 | 100% | 100% | 60552.14
Fire Hydrant | Fire Hydrant |  | 75690.17 |  | 100% | 75690.17
JDH4-02-007-CN-3910 | JDH4-02-007-CN-3910 | Installation of 3-outlet fire hydrant [Road 01 ] | 75690.17 | 100% | 100% | 75690.17
Valve Chambers | Valve Chambers |  | 829383.65 |  | 100% | 829383.65
JDH4-02-007-CN-3950 | JDH4-02-007-CN-3950 | Construction of Valve Chambers [Road 01 ] | 104035.14 | 100% | 100% | 104035.14
JDH4-02-007-CN-3960 | JDH4-02-007-CN-3960 | Construction of Wash out Chambers [Road 01 ] | 261848.64 | 100% | 100% | 261848.64
JDH4-02-007-CN-3970 | JDH4-02-007-CN-3970 | Construction of Air Valve Chambers [Road 01 ] | 274274.46 | 100% | 100% | 274274.46
JDH4-02-007-CN-4600 | JDH4-02-007-CN-4600 | Construction of Valve Chambers [Road 01 ] | 75690.16 | 100% | 100% | 75690.16
JDH4-02-007-CN-4630 | JDH4-02-007-CN-4630 | Construction of Air Valve Chambers [Road 01 ] | 75690.17 | 100% | 100% | 75690.17
JDH4-02-007-CN-4610 | JDH4-02-007-CN-4610 | Construction of Wash Out Valve Chambers [Road 01 ] | 37845.08 | 100% | 100% | 37845.08
Road Crossings | Road Crossings |  | 6307.51 |  | 100% | 6307.51
JDH4-02-007-CN-3980 | JDH4-02-007-CN-3980 | Installation of HDPE road croosing [Road 01 ] | 6307.51 | 100% | 100% | 6307.51
Electrical Works | Electrical Works |  | 360707.74 |  | 100% | 360707.74
LV Cables | LV Cables |  | 71867.75 |  | 100% | 71867.75
Low Voltage Cable | Low Voltage Cable |  | 71867.75 |  | 100% | 71867.75
JDH4-02-007-CN-2610 | JDH4-02-007-CN-2610 | Excavation for Low Voltage Cable [Road 01 ] | 19225.3 | 100% | 100% | 19225.3
JDH4-02-007-CN-2620 | JDH4-02-007-CN-2620 | Installation of Low Voltage Cables [Road 01 ] | 52642.45 | 100% | 100% | 52642.45
Street Lighting | Street Lighting |  | 20045.28 |  | 100% | 20045.28
JDH4-02-007-CN-2770 | JDH4-02-007-CN-2770 | Excavation for Low Voltage Cable [Road 01 ] | 3279.91 | 100% | 100% | 3279.91
JDH4-02-007-CN-2850 | JDH4-02-007-CN-2850 | Installation of Low Voltage Cables [Road 01 ] | 16765.37 | 100% | 100% | 16765.37
Telecommunication | Telecommunication |  | 268794.71 |  | 100% | 268794.71
JDH4-02-007-CN-3150 | JDH4-02-007-CN-3150 | Installation Road Crossing Un R/F 6 way 50mm HDPE Pipe [Road 01 ] | 5392.92 | 100% | 100% | 5392.92
JDH4-02-007-CN-3260 | JDH4-02-007-CN-3260 | Installation of Manholes [Road 01 ] | 56767.63 | 100% | 100% | 56767.63
JDH4-02-007-CN-3080 | JDH4-02-007-CN-3080 | Installation Road Crossing R/F 6 way 50mm HDPE Pipe [Road 01 ] | 206634.16 | 100% | 100% | 206634.16
Open Drain Channel | Open Drain Channel |  | 389804.76 |  | 100% | 389804.76
JDH4-02-007-CN-5850 | JDH4-02-007-CN-5850 | Channel excavation [Road 01 ](Completed) | 65850.6 | 100% | 100% | 65850.6
JDH4-02-007-CN-5860 | JDH4-02-007-CN-5860 | Backfill of the existing channel [Road 01 ](Completed) | 30276.07 | 100% | 100% | 30276.07
JDH4-02-007-CN-5870 | JDH4-02-007-CN-5870 | Compaction [Road 01 ] | 18922.54 | 100% | 100% | 18922.54
JDH4-02-007-CN-5850R | JDH4-02-007-CN-5850R | Channel excavation [Road 01 ] | 98775.9 | 100% | 100% | 98775.9
JDH4-02-007-CN-5860R | JDH4-02-007-CN-5860R | Backfill of the existing channel [Road 01 ] | 20184.04 | 100% | 100% | 20184.04
JDH4-02-007-CN-5880 | JDH4-02-007-CN-5880 | Finished grouted riprap for side ditches [Road 01 ] | 155795.6 | 100% | 100% | 155795.6
Road 02 | Road 02 |  | 658204 |  | 100% | 658204
Under Pass | Under Pass |  | 112526.05 |  | 100% | 112526.05
JDH4-02-007-CN-1940 | JDH4-02-007-CN-1940 | Compacted structural backfill for closing the underpass [Road 02 ] | 16651.84 | 100% | 100% | 16651.84
JDH4-02-007-CN-2410 | JDH4-02-007-CN-2410 | RC wall and the foundation at face of underpass [Road 02 ] | 95874.21 | 100% | 100% | 95874.21
Sewerage Network | Sewerage Network |  | 89801.58 |  | 100% | 89801.58
Pipe Works | Pipe Works |  | 57055.71 |  | 100% | 57055.71
JDH4-02-007-CN-4770 | JDH4-02-007-CN-4770 | Excavation & Compaction (FDT) [Road 02 ] | 5705.57 | 100% | 100% | 5705.57
JDH4-02-007-CN-5050 | JDH4-02-007-CN-5050 | Sand Cover & Warning Tape [Road 02 ] | 2852.78 | 100% | 100% | 2852.78
JDH4-02-007-CN-4840 | JDH4-02-007-CN-4840 | Sand Bedding [Road 02 ] | 2852.78 | 100% | 100% | 2852.78
JDH4-02-007-CN-4910 | JDH4-02-007-CN-4910 | Installation of GRP Pipe [Road 02 ] | 28527.86 | 100% | 100% | 28527.86
JDH4-02-007-CN-4980 | JDH4-02-007-CN-4980 | Gravity Test [Road 02 ] | 11411.15 | 100% | 100% | 11411.15
JDH4-02-007-CN-5120 | JDH4-02-007-CN-5120 | Backfilling & Compaction [Road 02 ] | 5705.57 | 100% | 100% | 5705.57
Pipe Encasement | Pipe Encasement |  | 304.22 |  | 100% | 304.22
JDH4-02-007-CN-5260 | JDH4-02-007-CN-5260 | Pipe Encasement Works [Road 02 ] | 304.22 | 100% | 100% | 304.22
Manholes | Manholes |  | 32441.65 |  | 100% | 32441.65
JDH4-02-007-CN-5190 | JDH4-02-007-CN-5190 | Installation of Manholes [Road 02 ] | 32441.65 | 100% | 100% | 32441.65
TSE Network | TSE Network |  | 145569.49 |  | 100% | 145569.49
Pipe Works | Pipe Works |  | 112992.76 |  | 100% | 112992.76
JDH4-02-007-CN-3990 | JDH4-02-007-CN-3990 | Excavation and Compaction (FDT) [Road 02 ](Completed) | 5754.78 | 100% | 100% | 5754.78
JDH4-02-007-CN-4060 | JDH4-02-007-CN-4060 | Sand Bedding [Road 02 ](Completed) | 2877.4 | 100% | 100% | 2877.4
JDH4-02-007-CN-4130 | JDH4-02-007-CN-4130 | Installation of HDPE Pipe [Road 02 ](Completed) | 23542.29 | 100% | 100% | 23542.29
JDH4-02-007-CN-4270 | JDH4-02-007-CN-4270 | Sand Cover & Warning [Road 02 ](Completed) | 2354.23 | 100% | 100% | 2354.23
JDH4-02-007-CN-3990R | JDH4-02-007-CN-3990R | Excavation and Compaction (FDT) [Road 02 ] | 4708.46 | 100% | 100% | 4708.46
JDH4-02-007-CN-4060R | JDH4-02-007-CN-4060R | Sand Bedding [Road 02 ] | 2354.23 | 100% | 100% | 2354.23
JDH4-02-007-CN-4130R | JDH4-02-007-CN-4130R | Installation of HDPE Pipe [Road 02 ] | 28773.91 | 100% | 100% | 28773.91
JDH4-02-007-CN-4200 | JDH4-02-007-CN-4200 | Initial Pressure Test [Road 02 ] | 20959.32 | 100% | 100% | 20959.32
JDH4-02-007-CN-4270R | JDH4-02-007-CN-4270R | Sand Cover & Warning [Road 02 ] | 2877.4 | 100% | 100% | 2877.4
JDH4-02-007-CN-4340 | JDH4-02-007-CN-4340 | Backfilling & Compaction [Road 02 ] | 10479.66 | 100% | 100% | 10479.66
JDH4-02-007-CN-4650 | JDH4-02-007-CN-4650 | Point of Connection [Road 02 ] | 8311.08 | 100% | 100% | 8311.08
Pipe Encasement | Pipe Encasement |  | 5288.43 |  | 100% | 5288.43
JDH4-02-007-CN-4410 | JDH4-02-007-CN-4410 | Encasement for Pipes [Road 02 ] | 5288.43 | 100% | 100% | 5288.43
Valves | Valves |  | 18457.78 |  | 100% | 18457.78
JDH4-02-007-CN-4480 | JDH4-02-007-CN-4480 | Installation of Gate Valves [Road 02 ] | 11204.14 | 100% | 100% | 11204.14
JDH4-02-007-CN-4570 | JDH4-02-007-CN-4570 | Installation of Air Valves [Road 02 ] | 7253.64 | 100% | 100% | 7253.64
Risers | Risers |  | 8830.52 |  | 100% | 8830.52
JDH4-02-007-CN-4720 | JDH4-02-007-CN-4720 | Installation of Irrigation Riser with [Road 02 ] | 8830.52 | 100% | 100% | 8830.52
Potable Network | Potable Network |  | 139057.87 |  | 100% | 139057.87
Pipe Works | Pipe Works |  | 84122.85 |  | 100% | 84122.85
JDH4-02-007-CN-3310 | JDH4-02-007-CN-3310 | Excavation and Compaction (FDT) [Road 02 ] | 8412.29 | 100% | 100% | 8412.29
JDH4-02-007-CN-3380 | JDH4-02-007-CN-3380 | Sand Bedding [Road 02 ] | 4206.15 | 100% | 100% | 4206.15
JDH4-02-007-CN-3450 | JDH4-02-007-CN-3450 | Installation of HDPE Pipe [Road 02 ] | 42061.41 | 100% | 100% | 42061.41
JDH4-02-007-CN-3520 | JDH4-02-007-CN-3520 | Initial Pressure Test [Road 02 ] | 16824.56 | 100% | 100% | 16824.56
JDH4-02-007-CN-3590 | JDH4-02-007-CN-3590 | Sand Cover & Warning Tape [Road 02 ] | 4206.15 | 100% | 100% | 4206.15
JDH4-02-007-CN-3660 | JDH4-02-007-CN-3660 | Backfilling [Road 02 ] | 8412.29 | 100% | 100% | 8412.29
Pipe Encasement | Pipe Encasement |  | 6577.42 |  | 100% | 6577.42
JDH4-02-007-CN-3730 | JDH4-02-007-CN-3730 | Encasement for Pipes [Road 02 ] | 6577.42 | 100% | 100% | 6577.42
Valves | Valves |  | 10512.52 |  | 100% | 10512.52
JDH4-02-007-CN-3800 | JDH4-02-007-CN-3800 | Installation of Gate Valves [Road 02 ] | 10512.52 | 100% | 100% | 10512.52
Valve Chambers | Valve Chambers |  | 37845.08 |  | 100% | 37845.08
JDH4-02-007-CN-4620 | JDH4-02-007-CN-4620 | Construction of Air Valve Chambers [Road 02 ] | 37845.08 | 100% | 100% | 37845.08
Electrical Works | Electrical Works |  | 171249.01 |  | 100% | 171249.01
Telecommunication | Telecommunication |  | 171249.01 |  | 100% | 171249.01
JDH4-02-007-CN-3130 | JDH4-02-007-CN-3130 | Installation Road Crossing Un R/F 6 way 50mm HDPE Pipe [Road 02 ] | 3973.73 | 100% | 100% | 3973.73
JDH4-02-007-CN-3240 | JDH4-02-007-CN-3240 | Installation of Manholes [Road 02 ] | 34060.58 | 100% | 100% | 34060.58
JDH4-02-007-CN-3060 | JDH4-02-007-CN-3060 | Installation Road Crossing R/F 6 way 50mm HDPE Pipe [Road 02 ] | 133214.7 | 100% | 100% | 133214.7
Road 10 | Road 10 |  | 908137.39 |  | 100% | 908137.39
Sewerage Network | Sewerage Network |  | 419517.38 |  | 100% | 419517.38
Pipe Works | Pipe Works |  | 288229.72 |  | 100% | 288229.72
JDH4-02-007-CN-4830 | JDH4-02-007-CN-4830 | Excavation & Compaction (FDT) [Road 10 ] | 28822.98 | 100% | 100% | 28822.98
JDH4-02-007-CN-4900 | JDH4-02-007-CN-4900 | Sand Bedding [Road 10 ] | 14411.47 | 100% | 100% | 14411.47
JDH4-02-007-CN-4970 | JDH4-02-007-CN-4970 | Installation of GRP Pipe [Road 10 ] | 144114.86 | 100% | 100% | 144114.86
JDH4-02-007-CN-5040 | JDH4-02-007-CN-5040 | Gravity Test [Road 10 ] | 57645.96 | 100% | 100% | 57645.96
JDH4-02-007-CN-5110 | JDH4-02-007-CN-5110 | Sand Cover & Warning Tape [Road 10 ] | 14411.47 | 100% | 100% | 14411.47
JDH4-02-007-CN-5180 | JDH4-02-007-CN-5180 | Backfilling & Compaction [Road 10 ] | 28822.98 | 100% | 100% | 28822.98
Pipe Encasement | Pipe Encasement |  | 1521.08 |  | 100% | 1521.08
JDH4-02-007-CN-5320 | JDH4-02-007-CN-5320 | Pipe Encasement Works [Road 10 ] | 1521.08 | 100% | 100% | 1521.08
Manholes | Manholes |  | 129766.58 |  | 100% | 129766.58
JDH4-02-007-CN-5250 | JDH4-02-007-CN-5250 | Installation of Manholes [Road 10 ] | 129766.58 | 100% | 100% | 129766.58
TSE Network | TSE Network |  | 221839.87 |  | 100% | 221839.87
Pipe Works | Pipe Works |  | 201483.45 |  | 100% | 201483.45
JDH4-02-007-CN-4050 | JDH4-02-007-CN-4050 | Excavation and Compaction (FDT) [Road 10 ] | 18901.67 | 100% | 100% | 18901.67
JDH4-02-007-CN-4120 | JDH4-02-007-CN-4120 | Sand Bedding [Road 10 ] | 9450.86 | 100% | 100% | 9450.86
JDH4-02-007-CN-4190 | JDH4-02-007-CN-4190 | Installation of HDPE Pipe [Road 10 ] | 94508.42 | 100% | 100% | 94508.42
JDH4-02-007-CN-4260 | JDH4-02-007-CN-4260 | Initial Pressure Test [Road 10 ] | 37803.35 | 100% | 100% | 37803.35
JDH4-02-007-CN-4710 | JDH4-02-007-CN-4710 | Point of Connection [Road 10 ] | 12466.62 | 100% | 100% | 12466.62
JDH4-02-007-CN-4330 | JDH4-02-007-CN-4330 | Sand Cover & Warning [Road 10 ] | 9450.86 | 100% | 100% | 9450.86
JDH4-02-007-CN-4400 | JDH4-02-007-CN-4400 | Backfilling & Compaction [Road 10 ] | 18901.67 | 100% | 100% | 18901.67
Pipe Encasement | Pipe Encasement |  | 9368.07 |  | 100% | 9368.07
JDH4-02-007-CN-4470 | JDH4-02-007-CN-4470 | Encasement for Pipes [Road 10 ] | 9368.07 | 100% | 100% | 9368.07
Valves | Valves |  | 10988.35 |  | 100% | 10988.35
JDH4-02-007-CN-4540 | JDH4-02-007-CN-4540 | Installation of Gate Valves [Road 10 ] | 3734.71 | 100% | 100% | 3734.71
JDH4-02-007-CN-4590 | JDH4-02-007-CN-4590 | Installation of Air Valves [Road 10 ] | 7253.64 | 100% | 100% | 7253.64
Potable Network | Potable Network |  | 62644.01 |  | 100% | 62644.01
Pipe Works | Pipe Works |  | 20491.46 |  | 100% | 20491.46
JDH4-02-007-CN-3370 | JDH4-02-007-CN-3370 | Excavation and Compaction (FDT) [Road 10 ] | 2049.15 | 100% | 100% | 2049.15
JDH4-02-007-CN-3440 | JDH4-02-007-CN-3440 | Sand Bedding [Road 10 ] | 1024.57 | 100% | 100% | 1024.57
JDH4-02-007-CN-3510 | JDH4-02-007-CN-3510 | Installation of HDPE Pipe [Road 10 ] | 10245.73 | 100% | 100% | 10245.73
JDH4-02-007-CN-3580 | JDH4-02-007-CN-3580 | Initial Pressure Test [Road 10 ] | 4098.29 | 100% | 100% | 4098.29
JDH4-02-007-CN-3650 | JDH4-02-007-CN-3650 | Sand Cover & Warning Tape [Road 10 ] | 1024.57 | 100% | 100% | 1024.57
JDH4-02-007-CN-3720 | JDH4-02-007-CN-3720 | Backfilling [Road 10 ] | 2049.15 | 100% | 100% | 2049.15
Pipe Encasement | Pipe Encasement |  | 1679.34 |  | 100% | 1679.34
JDH4-02-007-CN-3790 | JDH4-02-007-CN-3790 | Encasement for Pipes [Road 10 ] | 1679.34 | 100% | 100% | 1679.34
Valves | Valves |  | 2628.13 |  | 100% | 2628.13
JDH4-02-007-CN-3860 | JDH4-02-007-CN-3860 | Installation of Gate Valves [Road 10 ] | 2628.13 | 100% | 100% | 2628.13
Valve Chambers | Valve Chambers |  | 37845.08 |  | 100% | 37845.08
JDH4-02-007-CN-4640 | JDH4-02-007-CN-4640 | Construction of Air Valve Chambers [Road 10 ] | 37845.08 | 100% | 100% | 37845.08
Electrical Works | Electrical Works |  | 204136.13 |  | 100% | 204136.13
MV & LV Cables | MV & LV Cables |  | 36633.78 |  | 100% | 36633.78
Low Voltage Cable | Low Voltage Cable |  | 36633.78 |  | 100% | 36633.78
JDH4-02-007-CN-2670 | JDH4-02-007-CN-2670 | Excavation for Low Voltage Cable [Road 10 ] | 9839.72 | 100% | 100% | 9839.72
JDH4-02-007-CN-2680 | JDH4-02-007-CN-2680 | Installation of Low Voltage Cables [Road 10 ] | 26794.06 | 100% | 100% | 26794.06
Telecommunication | Telecommunication |  | 167502.35 |  | 100% | 167502.35
JDH4-02-007-CN-3120 | JDH4-02-007-CN-3120 | Installation Road Crossing R/F 6 way 50mm HDPE Pipe [Road 10 ] | 76068.62 | 100% | 100% | 76068.62
JDH4-02-007-CN-3190 | JDH4-02-007-CN-3190 | Installation Road Crossing Un R/F 6 way 50mm HDPE Pipe [Road 10 ] | 3406.06 | 100% | 100% | 3406.06
JDH4-02-007-CN-3230 | JDH4-02-007-CN-3230 | Installation of 2 x 32 mm diameter HDPE ducts [Road 10 ] | 70997.38 | 100% | 100% | 70997.38
JDH4-02-007-CN-3300 | JDH4-02-007-CN-3300 | Installation of Manholes [Road 10 ] | 17030.29 | 100% | 100% | 17030.29
Out of Zone | Out of Zone |  | 49496.57 |  | 100% | 49496.57
Electrical Works | Electrical Works |  | 49496.57 |  | 100% | 49496.57
LV Cables | LV Cables |  | 49496.57 |  | 100% | 49496.57
Low Voltage Cable | Low Voltage Cable |  | 49496.57 |  | 100% | 49496.57
JDH4-02-007-CN-2690 | JDH4-02-007-CN-2690 | Excavation for Low Voltage Cable [Out of Zone ] | 13245.78 | 100% | 100% | 13245.78
JDH4-02-007-CN-2700 | JDH4-02-007-CN-2700 | Installation of Low Voltage Cables [Out of Zone ] | 36250.79 | 100% | 100% | 36250.79
Sewage Lift Station | Sewage Lift Station |  | 3049343.44 |  | 60.53% | 1845852.34
Site Works | Site Works |  | 10249.72 |  | 100% | 10249.72
JDH4-02-007-CN-5910 | JDH4-02-007-CN-5910 | Excavation [Sewage Lift Station ] | 3942.2 | 100% | 100% | 3942.2
JDH4-02-007-CN-5930 | JDH4-02-007-CN-5930 | Install gravel beddings [Sewage Lift Station ] | 4730.64 | 100% | 100% | 4730.64
JDH4-02-007-CN-5920 | JDH4-02-007-CN-5920 | Backfilling [Sewage Lift Station ] | 1576.88 | 100% | 100% | 1576.88
Concrete Works | Concrete Works |  | 67679.63 |  | 100% | 67679.63
JDH4-02-007-CN-1010 | JDH4-02-007-CN-1010 | Lean concrete under the foundations [Sewage Lift Station ] | 2081.48 | 100% | 100% | 2081.48
JDH4-02-007-CN-1020 | JDH4-02-007-CN-1020 | Footings For Sewage Lift Station [Sewage Lift Station ] | 25230.06 | 100% | 100% | 25230.06
JDH4-02-007-CN-1030 | JDH4-02-007-CN-1030 | Cast concrete for trench Including Mastic sealant [Sewage Lift Station ] | 40368.09 | 100% | 100% | 40368.09
Thermal & Moisture Protection | Thermal & Moisture Protection |  | 7001.35 |  | 100% | 7001.35
JDH4-02-007-CN-1050 | JDH4-02-007-CN-1050 | Install 250 micron polyethylene sheet under slab on grade and footings [Sewage Lift Station ] | 2270.71 | 100% | 100% | 2270.71
JDH4-02-007-CN-1060 | JDH4-02-007-CN-1060 | Applying 2 Coats of Bituminous Paint [Sewage Lift Station ] | 4730.64 | 100% | 100% | 4730.64
Metals | Metals |  | 10092.02 |  | 100% | 10092.02
JDH4-02-007-CN-1040 | JDH4-02-007-CN-1040 | Install Stainless steel [Sewage Lift Station ] | 10092.02 | 100% | 100% | 10092.02
Mechanical Works | Mechanical Works |  | 1705863.69 |  | 67.66% | 1154271.59
Pipes & Fittings | Pipes & Fittings |  | 256712.33 |  | 100% | 256712.33
JDH4-02-007-CN-1090 | JDH4-02-007-CN-1090 | Installation of Pipes & Fittings [Sewage Lift Station ] | 30587.94 | 100% | 100% | 30587.94
JDH4-02-007-CN-1100 | JDH4-02-007-CN-1100 | Installation of Gate Valves [Sewage Lift Station ] | 29014.56 | 100% | 100% | 29014.56
JDH4-02-007-CN-1120 | JDH4-02-007-CN-1120 | Installation of Dismantling Joints [Sewage Lift Station ] | 13876.54 | 100% | 100% | 13876.54
JDH4-02-007-CN-1130 | JDH4-02-007-CN-1130 | Installation of Non Return Valve DN250 [Sewage Lift Station ] | 9461.27 | 100% | 100% | 9461.27
JDH4-02-007-CN-1140 | JDH4-02-007-CN-1140 | Installation of Air Valve DN60 [Sewage Lift Station ] | 11353.53 | 100% | 100% | 11353.53
JDH4-02-007-CN-1160 | JDH4-02-007-CN-1160 | Installation of Odors scrubbing system [Sewage Lift Station ] | 157687.85 | 100% | 100% | 157687.85
JDH4-02-007-CN-1150 | JDH4-02-007-CN-1150 | Installation of Bauer Coupling DN150 [Sewage Lift Station ] | 4730.64 | 100% | 100% | 4730.64
Control Equipment | Control Equipment |  | 118265.89 |  | 100% | 118265.89
JDH4-02-007-CN-1200 | JDH4-02-007-CN-1200 | Installation of Screening Container [Sewage Lift Station ] | 9461.27 | 100% | 100% | 9461.27
JDH4-02-007-CN-1190 | JDH4-02-007-CN-1190 | Installation of Air Vents [Sewage Lift Station ] | 4730.64 | 100% | 100% | 4730.64
JDH4-02-007-CN-1180 | JDH4-02-007-CN-1180 | Installation of Manually operated davit crane (portable) [Sewage Lift Station ] | 94612.71 | 100% | 100% | 94612.71
JDH4-02-007-CN-1210 | JDH4-02-007-CN-1210 | Installation of Baffle Plates [Sewage Lift Station ] | 9461.27 | 100% | 100% | 9461.27
Interface Works | Interface Works |  | 63075.14 |  | 100% | 63075.14
JDH4-02-007-CN-1220 | JDH4-02-007-CN-1220 | Interfacing Works [Sewage Lift Station ] | 63075.14 | 100% | 100% | 63075.14
Anti Water Hammer Equipment | Anti Water Hammer Equipment |  | 883051.97 |  | 60% | 529831.18
JDH4-02-007-CN-1230 | JDH4-02-007-CN-1230 | Installation of Anti-Water Hammer Equipment [Sewage Lift Station ] | 883051.97 | 60% | 60% | 529831.18
Air Conditioning & Ventilation | Air Conditioning & Ventilation |  | 18922.54 |  | 100% | 18922.54
JDH4-02-007-CN-1240 | JDH4-02-007-CN-1240 | Installation of Air Conditioning [Sewage Lift Station ] | 18922.54 | 100% | 100% | 18922.54
Fuel System | Fuel System |  | 75690.17 |  | 100% | 75690.17
JDH4-02-007-CN-1260 | JDH4-02-007-CN-1260 | Installation of Bulk Fuel storage tank, 2500 Liter (7 Days of storage) [Sewage Lift Station ] | 18922.54 | 100% | 100% | 18922.54
JDH4-02-007-CN-1270 | JDH4-02-007-CN-1270 | Installation of Fuel pump set , 1 duty and 1 standby, Capacity 100 L/h, Head 1 Bar [Sewage Lift Station ] | 47306.36 | 100% | 100% | 47306.36
JDH4-02-007-CN-1280 | JDH4-02-007-CN-1280 | Pipes and Fitting Works [Sewage Lift Station ] | 9461.27 | 100% | 100% | 9461.27
Fire Fighting | Fire Fighting |  | 56767.63 |  | 100% | 56767.63
JDH4-02-007-CN-1290 | JDH4-02-007-CN-1290 | Installation of Fire fighting for electrical room which has a volume of about 62 m3 [Sewage Lift Station ] | 47306.36 | 100% | 100% | 47306.36
JDH4-02-007-CN-1300 | JDH4-02-007-CN-1300 | Installation of Foam type - wheeled type 20 Gallon capacity-ref. FE-01 [Sewage Lift Station ] | 9461.27 | 100% | 100% | 9461.27
Pumps | Pumps |  | 233378.02 |  | 15% | 35006.7
JDH4-02-007-CN-1070 | JDH4-02-007-CN-1070 | Installation of Submersible pump [Sewage Lift Station ] | 233378.02 | 15% | 15% | 35006.7
Electrical Works | Electrical Works |  | 1230213.92 |  | 47.01% | 578314.93
Main Distribution Board | Main Distribution Board |  | 104073.98 |  | 50% | 52036.99
JDH4-02-007-CN-1310 | JDH4-02-007-CN-1310 | Installation of Main Distribution Board/MCC Panel [Sewage Lift Station ] | 75690.17 | 50% | 50% | 37845.09
JDH4-02-007-CN-1320 | JDH4-02-007-CN-1320 | Installation of Panel Board [Sewage Lift Station ] | 28383.81 | 50% | 50% | 14191.91
Local Control Panel | Local Control Panel |  | 107227.74 |  | 50% | 53613.87
JDH4-02-007-CN-1330 | JDH4-02-007-CN-1330 | Installation of MCP-LP-01 [Sewage Lift Station ] | 25230.06 | 50% | 50% | 12615.03
JDH4-02-007-CN-1350 | JDH4-02-007-CN-1350 | Installation of MCP-LP-02 [Sewage Lift Station ] | 25230.06 | 50% | 50% | 12615.03
JDH4-02-007-CN-1360 | JDH4-02-007-CN-1360 | Installation of OD-CP [Sewage Lift Station ] | 28383.81 | 50% | 50% | 14191.91
JDH4-02-007-CN-1370 | JDH4-02-007-CN-1370 | Installation of FP-CP [Sewage Lift Station ] | 28383.81 | 50% | 50% | 14191.91
Diesel Generator | Diesel Generator |  | 75690.17 |  | 100% | 75690.17
JDH4-02-007-CN-1380 | JDH4-02-007-CN-1380 | Installation of Standby Diesel Generator [Sewage Lift Station ] | 75690.17 | 100% | 100% | 75690.17
Power Factor Correction Capacitor Bank | Power Factor Correction Capacitor Bank |  | 22076.3 |  | 50% | 11038.15
JDH4-02-007-CN-1390 | JDH4-02-007-CN-1390 | Installation of Power Factor Correction Capacitor Bank [Sewage Lift Station ] | 22076.3 | 50% | 50% | 11038.15
Low-Voltage Electrical Power Conductors and Cables | Low-Voltage Electrical Power Conductors and Cables |  | 17535.2 |  | 30% | 5260.56
JDH4-02-007-CN-1410 | JDH4-02-007-CN-1410 | Installation of Low Voltage Cables [Sewage Lift Station ] | 17535.2 | 30% | 30% | 5260.56
Wiring Devices | Wiring Devices |  | 5044.14 |  | 100% | 5044.14
JDH4-02-007-CN-1420 | JDH4-02-007-CN-1420 | Installation of Wiring Devices [Sewage Lift Station ] | 5044.14 | 100% | 100% | 5044.14
Enclosed Switches and Circuit Breakers | Enclosed Switches and Circuit Breakers |  | 8830.52 |  | 0% | 0
JDH4-02-007-CN-1440 | JDH4-02-007-CN-1440 | Installation of Enclosed Switches and Circuit Breakers [Sewage Lift Station ] | 8830.52 | 0% | 0% | 0
Lighting | Lighting |  | 16399.53 |  | 100% | 16399.53
JDH4-02-007-CN-1450 | JDH4-02-007-CN-1450 | Installation of Lightings [Sewage Lift Station ] | 16399.53 | 100% | 100% | 16399.53
Grounding and Bonding for Electrical Systems | Grounding and Bonding for Electrical Systems |  | 18607.15 |  | 0% | 0
JDH4-02-007-CN-1460 | JDH4-02-007-CN-1460 | Installation of Grounding Links [Sewage Lift Station ] | 18607.15 | 0% | 0% | 0
Electrical Manholes | Electrical Manholes |  | 10723.17 |  | 100% | 10723.17
JDH4-02-007-CN-1470 | JDH4-02-007-CN-1470 | Installation of Electrical Manholes [Sewage Lift Station ] | 10723.17 | 100% | 100% | 10723.17
ICT (Data& telephone System) | ICT (Data& telephone System) |  | 44152.59 |  | 25% | 11038.15
JDH4-02-007-CN-1490 | JDH4-02-007-CN-1490 | Installation of IDF Cabinet 9U (for data &Telephone) [Sewage Lift Station ] | 22076.3 | 50% | 50% | 11038.15
JDH4-02-007-CN-1500 | JDH4-02-007-CN-1500 | Installationof Single data/Telephone outlet [Sewage Lift Station ] | 1261.5 | 0% | 0% | 0
JDH4-02-007-CN-1510 | JDH4-02-007-CN-1510 | Installation of Data Switch (24 Port) [Sewage Lift Station ] | 18922.54 | 0% | 0% | 0
JDH4-02-007-CN-1520 | JDH4-02-007-CN-1520 | Installation of Fiber optic cable (12 Core single mode). [Sewage Lift Station ] | 1892.25 | 0% | 0% | 0
Security System (CCTV System) | Security System (CCTV System) |  | 198686.69 |  | 100% | 198686.69
JDH4-02-007-CN-1530 | JDH4-02-007-CN-1530 | Installation of 5.0 Megapixel, Fixed bullet IP CCTV camera [Sewage Lift Station ] | 198686.69 | 100% | 100% | 198686.69
Duct Bank and Handhole For Telecom Network | Duct Bank and Handhole For Telecom Network |  | 8199.77 |  | 100% | 8199.77
JDH4-02-007-CN-1540 | JDH4-02-007-CN-1540 | Installation of 2 x 50mm HDPE ducts Bank [Sewage Lift Station ] | 5046.01 | 100% | 100% | 5046.01
JDH4-02-007-CN-1550 | JDH4-02-007-CN-1550 | Installation of Handholes (800x800x800 mm) [Sewage Lift Station ] | 3153.76 | 100% | 100% | 3153.76
Programmable Logic Controllers | Programmable Logic Controllers |  | 252300.56 |  | 30% | 75690.17
JDH4-02-007-CN-1570 | JDH4-02-007-CN-1570 | Installation of Programmable Logic Controller [Sewage Lift Station ] | 252300.56 | 30% | 30% | 75690.17
Process Control Wiring | Process Control Wiring |  | 157687.85 |  | 0% | 0
JDH4-02-007-CN-1580 | JDH4-02-007-CN-1580 | Installation of Process Control Wiring [Sewage Lift Station ] | 157687.85 | 0% | 0% | 0
Instrumentation for Process Systems | Instrumentation for Process Systems |  | 182978.56 |  | 30% | 54893.57
JDH4-02-007-CN-1600 | JDH4-02-007-CN-1600 | Installation of Process System [Sewage Lift Station ] | 182978.56 | 30% | 30% | 54893.57
Fence Work | Fence Work |  | 18243.11 |  | 100% | 18243.11
JDH4-02-007-CN-5890 | JDH4-02-007-CN-5890 | Installation of Chain Link Fence [Sewage Lift Station ] | 11984.28 | 100% | 100% | 11984.28
JDH4-02-007-CN-5900 | JDH4-02-007-CN-5900 | Installation of Pedestrian Gate [Sewage Lift Station ] | 6258.83 | 100% | 100% | 6258.83
MV Cable Works | MV Cable Works |  | 888341.63 |  | 100% | 888341.63
Medium Voltage Cable Road 8 | Medium Voltage Cable Road 8 |  | 165937.27 |  | 100% | 165937.27
JDH4-02-007-CN-2480 | JDH4-02-007-CN-2480 | Installation of Duct banks [Road 08 ] | 31916.02 | 100% | 100% | 31916.02
JDH4-02-007-CN-2420 | JDH4-02-007-CN-2420 | Excavation for Trench [Road 08 ] | 7545 | 100% | 100% | 7545
JDH4-02-007-CN-2540 | JDH4-02-007-CN-2540 | Installation of Medium Voltage Cables [Road 08 ] | 126476.25 | 100% | 100% | 126476.25
Medium Voltage Cable Road 7 | Medium Voltage Cable Road 7 |  | 130128.34 |  | 100% | 130128.34
JDH4-02-007-CN-2500 | JDH4-02-007-CN-2500 | Installation of Duct banks [Road 07-N ] | 13876.53 | 100% | 100% | 13876.53
JDH4-02-007-CN-2440 | JDH4-02-007-CN-2440 | Excavation for Trench [Road 07-N ] | 6530.33 | 100% | 100% | 6530.33
JDH4-02-007-CN-2560 | JDH4-02-007-CN-2560 | Installation of Medium Voltage Cables [Road 07-N ] | 109721.48 | 100% | 100% | 109721.48
Medium Voltage Cable Road 1 | Medium Voltage Cable Road 1 |  | 264999.32 |  | 100% | 264999.32
JDH4-02-007-CN-2430 | JDH4-02-007-CN-2430 | Excavation for Trench [Road 01 ] | 13372.86 | 100% | 100% | 13372.86
JDH4-02-007-CN-2490 | JDH4-02-007-CN-2490 | Installation of Duct banks [Road 01 ] | 27290.51 | 100% | 100% | 27290.51
JDH4-02-007-CN-2550 | JDH4-02-007-CN-2550 | Installation of Medium Voltage Cables [Road 01 ] | 224335.95 | 100% | 100% | 224335.95
Medium Voltage Cable Road 10 | Medium Voltage Cable Road 10 |  | 130978.55 |  | 100% | 130978.55
JDH4-02-007-CN-2460 | JDH4-02-007-CN-2460 | Excavation for Trench [Road 10 ] | 6816.52 | 100% | 100% | 6816.52
JDH4-02-007-CN-2520 | JDH4-02-007-CN-2520 | Installation of Duct banks [Road 10 ] | 9251.02 | 100% | 100% | 9251.02
JDH4-02-007-CN-2580 | JDH4-02-007-CN-2580 | Installation of Medium Voltage Cables [Road 10 ] | 114911.01 | 100% | 100% | 114911.01
Medium Voltage Cable Out of Zone | Medium Voltage Cable Out of Zone |  | 196298.15 |  | 100% | 196298.15
JDH4-02-007-CN-2470 | JDH4-02-007-CN-2470 | Excavation for Trench [Out of Zone ] | 9236.12 | 100% | 100% | 9236.12
JDH4-02-007-CN-2530 | JDH4-02-007-CN-2530 | Installation of Duct banks [Out of Zone ] | 33303.68 | 100% | 100% | 33303.68
JDH4-02-007-CN-2590 | JDH4-02-007-CN-2590 | Installation of Medium Voltage Cables [Out of Zone ] | 153758.35 | 100% | 100% | 153758.35
Plot Backfilling 2 | Plot Backfilling 2 |  | 3041122.86 |  | 81.67% | 2483583.67
JDH4-02-007-CN-1860 | JDH4-02-007-CN-1860 | Plots backfilling Stage 5 [Plots ] | 1013707.62 | 100% | 100% | 1013707.62
JDH4-02-007-CN-1870 | JDH4-02-007-CN-1870 | Plots backfilling Stage 6 [Plots ] | 1013707.62 | 85% | 85% | 861651.48
JDH4-02-007-CN-1880 | JDH4-02-007-CN-1880 | Plots backfilling Stage 7 [Plots ] | 1013707.62 | 60% | 60% | 608224.57
Additional Works | Additional Works |  | 4574877.19 |  | 92.5% | 4231761.4
JDH4-02-007-CN-1740 | JDH4-02-007-CN-1740 | Earth Work | 1143719.3 | 100% | 100% | 1143719.3
JDH4-02-007-CN-5940 | JDH4-02-007-CN-5940 | Utilities Work | 1143719.3 | 100% | 100% | 1143719.3
JDH4-02-007-CN-5960 | JDH4-02-007-CN-5960 | Road Work | 1143719.3 | 85% | 85% | 972161.4
JDH4-02-007-CN-5950 | JDH4-02-007-CN-5950 | Electrical Works | 1143719.3 | 85% | 85% | 972161.4
Testing & Commissioning | Testing & Commissioning |  | 5730434.78 |  | 70.71% | 4052236.02
JDH4-02-007-TC-1020 | JDH4-02-007-TC-1020 | Test for Sanitary Sewerage | 818633.54 | 100% | 100% | 818633.54
JDH4-02-007-TC-1000 | JDH4-02-007-TC-1000 | Test for Potable Water Network | 818633.54 | 100% | 100% | 818633.54
JDH4-02-007-TC-1060 | JDH4-02-007-TC-1060 | Test for Road Works | 818633.54 | 55% | 55% | 450248.45
JDH4-02-007-TC-1030 | JDH4-02-007-TC-1030 | Test for Stormwater Utilities | 818633.54 | 100% | 100% | 818633.54
JDH4-02-007-TC-1010 | JDH4-02-007-TC-1010 | Test for TSE Network | 818633.54 | 100% | 100% | 818633.54
JDH4-02-007-TC-1050 | JDH4-02-007-TC-1050 | Test for Sewage Lift Station | 818633.54 | 20% | 20% | 163726.71
JDH4-02-007-TC-1040 | JDH4-02-007-TC-1040 | Test for Electrical Network | 818633.54 | 20% | 20% | 163726.71
Project Hand Over & Close-out | Project Hand Over & Close-out |  | 0 |  | 0% | 0
As-Built DWGs | As-Built DWGs |  | 0 |  | 0% | 0
As-Built DWGs Submittal | As-Built DWGs Submittal |  | 0 |  | 0% | 0
JDH4-02-007-AB-1020 | JDH4-02-007-AB-1020 | As-Built DWGs Submittal for Sanitary Sewerage | 0 | 100% | 100% | 0
JDH4-02-007-AB-1030 | JDH4-02-007-AB-1030 | As-Built DWGs Submittal for Stormwater Utilities | 0 | 100% | 100% | 0
JDH4-02-007-AB-1010 | JDH4-02-007-AB-1010 | As-Built DWGs Submittal for TSE Network | 0 | 100% | 100% | 0
JDH4-02-007-AB-1000 | JDH4-02-007-AB-1000 | As-Built DWGs Submittal for Potable Water Network | 0 | 100% | 100% | 0
JDH4-02-007-AB-1040 | JDH4-02-007-AB-1040 | As-Built DWGs Submittal for Electrical Network | 0 | 0% | 0% | 0
JDH4-02-007-AB-1060 | JDH4-02-007-AB-1060 | As-Built DWGs Submittal for Road Works | 0 | 0% | 0% | 0
JDH4-02-007-AB-1050 | JDH4-02-007-AB-1050 | As-Built DWGs Submittal for Sewage Lift Station | 0 | 0% | 0% | 0
As-Built DWGs Approval | As-Built DWGs Approval |  | 0 |  | 0% | 0
JDH4-02-007-AB-1090 | JDH4-02-007-AB-1090 | As- Built DWGs Approval for Sanitary Sewerage | 0 | 100% | 100% | 0
JDH4-02-007-AB-1080 | JDH4-02-007-AB-1080 | As- Built DWGs Approval for TSE Network | 0 | 100% | 100% | 0
JDH4-02-007-AB-1070 | JDH4-02-007-AB-1070 | As- Built DWGs Approval for Potable Water Network | 0 | 100% | 100% | 0
JDH4-02-007-AB-1100 | JDH4-02-007-AB-1100 | As- Built DWGs Approval for Stormwater Utilities | 0 | 100% | 100% | 0
JDH4-02-007-AB-1110 | JDH4-02-007-AB-1110 | As- Built DWGs Approval for Electrical Network | 0 | 0% | 0% | 0
JDH4-02-007-AB-1130 | JDH4-02-007-AB-1130 | As- Built DWGs Approval for Road Works | 0 | 0% | 0% | 0
JDH4-02-007-AB-1120 | JDH4-02-007-AB-1120 | As- Built DWGs Approval for Sewage Lift Station | 0 | 0% | 0% | 0
Demobilization | Demobilization |  | 0 |  | 0% | 0
JDH4-02-007-DM-1000 | JDH4-02-007-DM-1000 | Demobilization of Manpower | 0 | 0% | 0% | 0
JDH4-02-007-DM-1010 | JDH4-02-007-DM-1010 | Removal of Equipment from Site | 0 | 0% | 0% | 0
JDH4-02-007-DM-1020 | JDH4-02-007-DM-1020 | Site Clean Up | 0 | 0% | 0% | 0
JDH4-02-007-DM-1030 | JDH4-02-007-DM-1030 | Removal of Site Offices and Structures | 0 | 0% | 0% | 0
JDH4-02-007-DM-1040 | JDH4-02-007-DM-1040 | Restoration of Ground Surfaces | 0 | 0% | 0% | 0

## Previous week
Activity ID | Activity ID | Activity Name | Budgeted Total Cost | Activity % Complete | Performance % Complete | Earned Value Cost
Infrastructure Development for Madinah Industrial city Phase 1-A | JDH4-02-007-R-UP-Land Development of Jeddah Oasis- 06 Oct 2026 |  | 57304347.86 |  | 91.11% | 52209223.82
Key Milestones | Key Milestones |  | 0 |  | 0% | 0
General Milestone | General Milestone |  | 0 |  | 0% | 0
JDH4-02-007-MS-1000 | JDH4-02-007-MS-1000 | Project Commencement Date | 0 | 100% | 100% | 0
JDH4-02-007-MS-1010 | JDH4-02-007-MS-1010 | Project Completion Date | 0 | 0% | 0% | 0
Contractual Milestone | Contractual Milestone |  | 0 |  | 0% | 0
Engineering & Mobilization | Engineering & Mobilization |  | 0 |  | 0% | 0
JDH4-02-007-MS-1020 | JDH4-02-007-MS-1020 | Completion of Mobilization | 0 | 100% | 100% | 0
JDH4-02-007-MS-1030 | JDH4-02-007-MS-1030 | Submission of the Work Plan (Baseline Programme) | 0 | 100% | 100% | 0
JDH4-02-007-MS-1040 | JDH4-02-007-MS-1040 | Submission and Approval of Drawings and Materials | 0 | 100% | 100% | 0
Construction | Construction |  | 0 |  | 0% | 0
JDH4-02-007-MS-1060 | JDH4-02-007-MS-1060 | Completion of Sewerage networks | 0 | 100% | 100% | 0
JDH4-02-007-MS-1090 | JDH4-02-007-MS-1090 | Completion of TSE Network | 0 | 100% | 100% | 0
JDH4-02-007-MS-1080 | JDH4-02-007-MS-1080 | Completion of Potable Water Network | 0 | 100% | 100% | 0
JDH4-02-007-MS-1050 | JDH4-02-007-MS-1050 | Completion of Earthworks & Site Grading For Plots | 0 | 0% | 0% | 0
JDH4-02-007-MS-1070 | JDH4-02-007-MS-1070 | Completion of Road Works | 0 | 0% | 0% | 0
JDH4-02-007-MS-1100 | JDH4-02-007-MS-1100 | Completion of Electrical Networks | 0 | 0% | 0% | 0
JDH4-02-007-MS-1110 | JDH4-02-007-MS-1110 | Completion of Entire Project | 0 | 0% | 0% | 0
Monitoring & Controlling Milestone | Monitoring & Controlling Milestone |  | 0 |  | 0% | 0
JDH4-02-007-MS-1120 | JDH4-02-007-MS-1120 | Approval of Electrical Network Shop DWGs By SEC | 0 | 100% | 100% | 0
JDH4-02-007-MS-1130 | JDH4-02-007-MS-1130 | Approval of Electrical Network Materials By SEC | 0 | 100% | 100% | 0
Mobilization | Mobilization |  | 0 |  | 0% | 0
Site Facilities & Offices | Site Facilities & Offices |  | 0 |  | 0% | 0
JDH4-02-007-MB-1000 | JDH4-02-007-MB-1000 | Site Layout Plan | 0 | 100% | 100% | 0
JDH4-02-007-MB-1010 | JDH4-02-007-MB-1010 | Clear & Grub for Offices & Access Road | 0 | 100% | 100% | 0
JDH4-02-007-MB-1020 | JDH4-02-007-MB-1020 | Construct Site Access Roads | 0 | 100% | 100% | 0
JDH4-02-007-MB-1040 | JDH4-02-007-MB-1040 | Construct Site Offices & Storage | 0 | 100% | 100% | 0
JDH4-02-007-MB-1030 | JDH4-02-007-MB-1030 | Construct Temporary Fence | 0 | 100% | 100% | 0
JDH4-02-007-MB-1060 | JDH4-02-007-MB-1060 | Install Site Facilities | 0 | 100% | 100% | 0
JDH4-02-007-MB-1070 | JDH4-02-007-MB-1070 | Electrical Works & Connections | 0 | 100% | 100% | 0
JDH4-02-007-MB-1090 | JDH4-02-007-MB-1090 | Mobilization of Equipment | 0 | 100% | 100% | 0
JDH4-02-007-MB-1100 | JDH4-02-007-MB-1100 | Mobilization of Manpower | 0 | 100% | 100% | 0
JDH4-02-007-MB-1050 | JDH4-02-007-MB-1050 | Install Project Signs | 0 | 100% | 100% | 0
JDH4-02-007-MB-1080 | JDH4-02-007-MB-1080 | Construct Parking Sheds | 0 | 100% | 100% | 0
Topographic Survey | Topographic Survey |  | 0 |  | 0% | 0
JDH4-02-007-TP-1000 | JDH4-02-007-TP-1000 | Site Survey Works | 0 | 100% | 100% | 0
Permit's and Authority Approvals | Permit's and Authority Approvals |  | 0 |  | 0% | 0
JDH4-02-007-PA-1000 | JDH4-02-007-PA-1000 | Excavation & Backfilling Permit Permit | 0 | 100% | 100% | 0
JDH4-02-007-PA-1010 | JDH4-02-007-PA-1010 | Saudi Electricity Company Permit | 0 | 100% | 100% | 0
Preliminary Submittals | Preliminary Submittals |  | 0 |  | 0% | 0
Preparation and Submittal by Contractor's | Preparation and Submittal by Contractor's |  | 0 |  | 0% | 0
JDH4-02-007-PS-1000 | JDH4-02-007-PS-1000 | Preparation and Submittal of Detailed Work Order Programme (baseline schedule) | 0 | 100% | 100% | 0
JDH4-02-007-PS-1020 | JDH4-02-007-PS-1020 | Preparation and Submittal of Quality Management Plan | 0 | 100% | 100% | 0
JDH4-02-007-PS-1030 | JDH4-02-007-PS-1030 | Preparation and Submittal of Safety Management Plan | 0 | 100% | 100% | 0
JDH4-02-007-PS-1040 | JDH4-02-007-PS-1040 | Preparation and Submittal of Organization Chart | 0 | 100% | 100% | 0
JDH4-02-007-PS-1050 | JDH4-02-007-PS-1050 | Preparation and Submittal of Communication Plan | 0 | 100% | 100% | 0
JDH4-02-007-PS-1010 | JDH4-02-007-PS-1010 | Preparation and Submittal of Project Execution Plan | 0 | 100% | 100% | 0
Approval by the Employer's | Approval by the Employer's |  | 0 |  | 0% | 0
JDH4-02-007-PS-1100 | JDH4-02-007-PS-1100 | Approval of Organization Chart | 0 | 100% | 100% | 0
JDH4-02-007-PS-1110 | JDH4-02-007-PS-1110 | Approval of Comminumcation Plan | 0 | 100% | 100% | 0
JDH4-02-007-PS-1060 | JDH4-02-007-PS-1060 | Approval of Detailed Work Order Programme (baseline schedule) | 0 | 100% | 100% | 0
JDH4-02-007-PS-1090 | JDH4-02-007-PS-1090 | Approval of Safety Management Plan | 0 | 100% | 100% | 0
JDH4-02-007-PS-1080 | JDH4-02-007-PS-1080 | Approval of Quality Management Plan | 0 | 100% | 100% | 0
JDH4-02-007-PS-1070 | JDH4-02-007-PS-1070 | Approval of Project Execution Plan | 0 | 100% | 100% | 0
Engineering | Engineering |  | 1719130.43 |  | 100% | 1719130.43
Shop Drawings | Shop Drawings |  | 0 |  | 0% | 0
Shop Drawings Submittal | Shop Drawings Submittal |  | 0 |  | 0% | 0
Shop Drawings Submittal for Road Works | Shop Drawings Submittal for Road Works |  | 0 |  | 0% | 0
JDH4-02-007-EN-1040 | JDH4-02-007-EN-1040 | Shop DWG Submittal for Topographic Survey | 0 | 100% | 100% | 0
JDH4-02-007-EN-1050 | JDH4-02-007-EN-1050 | Shop DWG Submittal for Road Layout Plan | 0 | 100% | 100% | 0
JDH4-02-007-EN-1070 | JDH4-02-007-EN-1070 | Shop DWG Submittal for Road Setting Out | 0 | 100% | 100% | 0
JDH4-02-007-EN-1080 | JDH4-02-007-EN-1080 | Shop DWG Submittal for Road Profiles | 0 | 100% | 100% | 0
JDH4-02-007-EN-1090 | JDH4-02-007-EN-1090 | Shop DWG Submittal for Grading Layout Plan | 0 | 100% | 100% | 0
JDH4-02-007-EN-1100 | JDH4-02-007-EN-1100 | Shop DWG Submittal for Curb Setting Out Points | 0 | 100% | 100% | 0
JDH4-02-007-EN-1120 | JDH4-02-007-EN-1120 | Shop DWG Submittal for Standards Details | 0 | 100% | 100% | 0
JDH4-02-007-EN-1060 | JDH4-02-007-EN-1060 | Shop DWG Submittal for Typical Cross Section | 0 | 100% | 100% | 0
JDH4-02-007-EN-1110 | JDH4-02-007-EN-1110 | Shop DWG Submittal for Signing & Marking Layout Plan | 0 | 100% | 100% | 0
Shop Drawings Submittal for Stormwater Network | Shop Drawings Submittal for Stormwater Network |  | 0 |  | 0% | 0
JDH4-02-007-EN-1250 | JDH4-02-007-EN-1250 | Shop DWG Submittal for Stormwater Plans | 0 | 100% | 100% | 0
JDH4-02-007-EN-1260 | JDH4-02-007-EN-1260 | Shop DWG Submittal for Stormwater Profiles | 0 | 100% | 100% | 0
JDH4-02-007-EN-1270 | JDH4-02-007-EN-1270 | Shop DWG Submittal for Stormwater Standard Details | 0 | 100% | 100% | 0
Shop Drawings Submittal for Sanitary Sewerage | Shop Drawings Submittal for Sanitary Sewerage |  | 0 |  | 0% | 0
JDH4-02-007-EN-1220 | JDH4-02-007-EN-1220 | Shop DWG Submittal for Sanitary Sewerage Plans | 0 | 100% | 100% | 0
JDH4-02-007-EN-1230 | JDH4-02-007-EN-1230 | Shop DWG Submittal for Sanitary Sewerage Profiles | 0 | 100% | 100% | 0
JDH4-02-007-EN-1240 | JDH4-02-007-EN-1240 | Shop DWG Submittal for Sanitary Sewerage Standard Details | 0 | 100% | 100% | 0
Shop Drawings Submittal for TSE Network | Shop Drawings Submittal for TSE Network |  | 0 |  | 0% | 0
JDH4-02-007-EN-1190 | JDH4-02-007-EN-1190 | Shop DWG Submittal for TSE Network Plans | 0 | 100% | 100% | 0
JDH4-02-007-EN-1200 | JDH4-02-007-EN-1200 | Shop DWG Submittal for TSE Profiles | 0 | 100% | 100% | 0
JDH4-02-007-EN-1210 | JDH4-02-007-EN-1210 | Shop DWG Submittal for TSE Standard Details | 0 | 100% | 100% | 0
Shop Drawings Submittal for Potable Water Network | Shop Drawings Submittal for Potable Water Network |  | 0 |  | 0% | 0
JDH4-02-007-EN-1160 | JDH4-02-007-EN-1160 | Shop DWG Submittal for Potable Water Plans | 0 | 100% | 100% | 0
JDH4-02-007-EN-1170 | JDH4-02-007-EN-1170 | Shop DWG Submittal for Potable Water Profiles | 0 | 100% | 100% | 0
JDH4-02-007-EN-1180 | JDH4-02-007-EN-1180 | Shop DWG Submittal for Potable Water Standard Details | 0 | 100% | 100% | 0
Shop Drawings Submittal for Electrical Network | Shop Drawings Submittal for Electrical Network |  | 0 |  | 0% | 0
JDH4-02-007-EN-1140 | JDH4-02-007-EN-1140 | Shop DWG Submittal for Street Lighting | 0 | 100% | 100% | 0
JDH4-02-007-EN-1150 | JDH4-02-007-EN-1150 | Shop DWG Submittal for Low Voltage Network | 0 | 100% | 100% | 0
JDH4-02-007-EN-1130 | JDH4-02-007-EN-1130 | Shop DWG Submittal for Medium Voltage Network | 0 | 100% | 100% | 0
Shop Drawings Submittal for Telecommunications | Shop Drawings Submittal for Telecommunications |  | 0 |  | 0% | 0
JDH4-02-007-EN-1600 | JDH4-02-007-EN-1600 | Shop DWG Submittal for Telecommunications Works | 0 | 100% | 100% | 0
Shop Drawings Submittal for Earthing System | Shop Drawings Submittal for Earthing System |  | 0 |  | 0% | 0
JDH4-02-007-EN-1610 | JDH4-02-007-EN-1610 | Shop DWG Submittal for Earthing System | 0 | 100% | 100% | 0
Shop Drawings Submittal for Road Lighting | Shop Drawings Submittal for Road Lighting |  | 0 |  | 0% | 0
JDH4-02-007-EN-1000 | JDH4-02-007-EN-1000 | Shop DWG Submittal for Street Lighting General Arrangement | 0 | 100% | 100% | 0
JDH4-02-007-EN-1010 | JDH4-02-007-EN-1010 | Shop DWG Submittal for Street Lighting Network Layout | 0 | 100% | 100% | 0
JDH4-02-007-EN-1020 | JDH4-02-007-EN-1020 | Shop DWG Submittal for Street Lighting Details | 0 | 100% | 100% | 0
JDH4-02-007-EN-1030 | JDH4-02-007-EN-1030 | Shop DWG Submittal for Street Lighting Single Line Diagram | 0 | 100% | 100% | 0
Shop Drawings Submittal for Sewage Lift Station | Shop Drawings Submittal for Sewage Lift Station |  | 0 |  | 0% | 0
JDH4-02-007-EN-1280 | JDH4-02-007-EN-1280 | Shop DWG Submittal for the Sewage Lift Station - Civil Works | 0 | 100% | 100% | 0
JDH4-02-007-EN-1290 | JDH4-02-007-EN-1290 | Shop DWG Submittal for the Sewage Lift Station - Mechanical Works | 0 | 100% | 100% | 0
JDH4-02-007-EN-1310 | JDH4-02-007-EN-1310 | Shop DWG Submittal for the Sewage Lift Station - Finishing Works | 0 | 100% | 100% | 0
JDH4-02-007-EN-1300 | JDH4-02-007-EN-1300 | Shop DWG Submittal for the Sewage Lift Station - Electrical Works | 0 | 100% | 100% | 0
Shop Drawings Approval | Shop Drawings Approval |  | 0 |  | 0% | 0
Shop Drawings Approval for Road Works | Shop Drawings Approval for Road Works |  | 0 |  | 0% | 0
JDH4-02-007-EN-1320 | JDH4-02-007-EN-1320 | Shop DWG Approval for Topographic Survey | 0 | 100% | 100% | 0
JDH4-02-007-EN-1330 | JDH4-02-007-EN-1330 | Shop DWG Approval for Road Layout Plan | 0 | 100% | 100% | 0
JDH4-02-007-EN-1340 | JDH4-02-007-EN-1340 | Shop DWG Approval for Typical Cross Section | 0 | 100% | 100% | 0
JDH4-02-007-EN-1350 | JDH4-02-007-EN-1350 | Shop DWG Approval for Road Setting Out | 0 | 100% | 100% | 0
JDH4-02-007-EN-1360 | JDH4-02-007-EN-1360 | Shop DWG Approval for Road Profiles | 0 | 100% | 100% | 0
JDH4-02-007-EN-1370 | JDH4-02-007-EN-1370 | Shop DWG Approval for Grading Layout Plan | 0 | 100% | 100% | 0
JDH4-02-007-EN-1380 | JDH4-02-007-EN-1380 | Shop DWG Approval for Curb Setting Out Points | 0 | 100% | 100% | 0
JDH4-02-007-EN-1400 | JDH4-02-007-EN-1400 | Shop DWG Approval for Standards Details | 0 | 100% | 100% | 0
JDH4-02-007-EN-1390 | JDH4-02-007-EN-1390 | Shop DWG Approval for Signing & Marking Layout Plan | 0 | 100% | 100% | 0
Shop Drawings Approval for Storm Network | Shop Drawings Approval for Storm Network |  | 0 |  | 0% | 0
JDH4-02-007-EN-1530 | JDH4-02-007-EN-1530 | Shop DWG Approval for Stormwater Plans | 0 | 100% | 100% | 0
JDH4-02-007-EN-1540 | JDH4-02-007-EN-1540 | Shop DWG Approval for Stormwater Profiles | 0 | 100% | 100% | 0
JDH4-02-007-EN-1550 | JDH4-02-007-EN-1550 | Shop DWG Approval for Stormwater Standard Details | 0 | 100% | 100% | 0
Shop Drawings Approval for Sanitary Sewerage | Shop Drawings Approval for Sanitary Sewerage |  | 0 |  | 0% | 0
JDH4-02-007-EN-1500 | JDH4-02-007-EN-1500 | Shop DWG Approval for Sanitary Sewerage Plans | 0 | 100% | 100% | 0
JDH4-02-007-EN-1510 | JDH4-02-007-EN-1510 | Shop DWG Approval for Sanitary Sewerage Profiles | 0 | 100% | 100% | 0
JDH4-02-007-EN-1520 | JDH4-02-007-EN-1520 | Shop DWG Approval for Sanitary Sewerage Standard Details | 0 | 100% | 100% | 0
Shop Drawings Approval for TSE Network | Shop Drawings Approval for TSE Network |  | 0 |  | 0% | 0
JDH4-02-007-EN-1470 | JDH4-02-007-EN-1470 | Shop DWG Approval for TSE Network Plans | 0 | 100% | 100% | 0
JDH4-02-007-EN-1480 | JDH4-02-007-EN-1480 | Shop DWG Approval for TSE Profiles | 0 | 100% | 100% | 0
JDH4-02-007-EN-1490 | JDH4-02-007-EN-1490 | Shop DWG Approval for TSE Standard Details | 0 | 100% | 100% | 0
Shop Drawings Approval for Potable Water Network | Shop Drawings Approval for Potable Water Network |  | 0 |  | 0% | 0
JDH4-02-007-EN-1440 | JDH4-02-007-EN-1440 | Shop DWG Approval for Potable Water Plans | 0 | 100% | 100% | 0
JDH4-02-007-EN-1450 | JDH4-02-007-EN-1450 | Shop DWG Approval for Potable Water Profiles | 0 | 100% | 100% | 0
JDH4-02-007-EN-1460 | JDH4-02-007-EN-1460 | Shop DWG Approval for Potable Water Standard Details | 0 | 100% | 100% | 0
Shop Drawings Approval for Electrical Network | Shop Drawings Approval for Electrical Network |  | 0 |  | 0% | 0
JDH4-02-007-EN-1420 | JDH4-02-007-EN-1420 | Shop DWG Approval for Street Lighting by By SEC | 0 | 100% | 100% | 0
JDH4-02-007-EN-1430 | JDH4-02-007-EN-1430 | Shop DWG Approval for Low Voltage Network By SEC | 0 | 100% | 100% | 0
JDH4-02-007-EN-1410 | JDH4-02-007-EN-1410 | Shop DWG Approval for Medium Voltage Network By SEC | 0 | 100% | 100% | 0
Shop Drawings Approval for Telecommunications | Shop Drawings Approval for Telecommunications |  | 0 |  | 0% | 0
JDH4-02-007-EN-1620 | JDH4-02-007-EN-1620 | Shop DWG Approval for Telecommunications Works | 0 | 100% | 100% | 0
Shop Drawings Approval for Earthing System | Shop Drawings Approval for Earthing System |  | 0 |  | 0% | 0
JDH4-02-007-EN-1630 | JDH4-02-007-EN-1630 | Shop DWG Approval for Earthing System By SEC | 0 | 100% | 100% | 0
Shop Drawings Approval for Road Lighting | Shop Drawings Approval for Road Lighting |  | 0 |  | 0% | 0
JDH4-02-007-EN-1640 | JDH4-02-007-EN-1640 | Shop DWG Approval for Street Lighting General Arrangement By SEC | 0 | 100% | 100% | 0
JDH4-02-007-EN-1650 | JDH4-02-007-EN-1650 | Shop DWG Approval for Street Lighting Network Layout By SEC | 0 | 100% | 100% | 0
JDH4-02-007-EN-1660 | JDH4-02-007-EN-1660 | Shop DWG Approval for Street Lighting Details By SEC | 0 | 100% | 100% | 0
JDH4-02-007-EN-1670 | JDH4-02-007-EN-1670 | Shop DWG Approval for Street Lighting Single Line Diagram By SEC | 0 | 100% | 100% | 0
Shop Drawings Approval for Sewage Lift Station | Shop Drawings Approval for Sewage Lift Station |  | 0 |  | 0% | 0
JDH4-02-007-EN-1680 | JDH4-02-007-EN-1680 | Shop DWG Approval for the Sewage Lift Station - Civil Works | 0 | 100% | 100% | 0
JDH4-02-007-EN-1690 | JDH4-02-007-EN-1690 | Shop DWG Approval for the Sewage Lift Station - Mechanical Works | 0 | 100% | 100% | 0
JDH4-02-007-EN-1710 | JDH4-02-007-EN-1710 | Shop DWG Approval for the Sewage Lift Station - Finishing Works | 0 | 100% | 100% | 0
JDH4-02-007-EN-1700 | JDH4-02-007-EN-1700 | Shop DWG Approval for the Sewage Lift Station - Electrical Works | 0 | 100% | 100% | 0
Method Statements | Method Statements |  | 0 |  | 0% | 0
Method Statements Submittal | Method Statements Submittal |  | 0 |  | 0% | 0
JDH4-02-007-EN-1560 | JDH4-02-007-EN-1560 | Preparation & Submission of Method Statement for Earthworks | 0 | 100% | 100% | 0
JDH4-02-007-EN-1570 | JDH4-02-007-EN-1570 | Preparation & Submission of Method Statement for Concrete Works | 0 | 100% | 100% | 0
JDH4-02-007-EN-1580 | JDH4-02-007-EN-1580 | Preparation & Submission of Method Statement for Waterproofing Works | 0 | 100% | 100% | 0
JDH4-02-007-EN-1590 | JDH4-02-007-EN-1590 | Preparation & Submission of Method Statement for Asphalt | 0 | 100% | 100% | 0
Method Statements Approval | Method Statements Approval |  | 0 |  | 0% | 0
JDH4-02-007-EN-1720 | JDH4-02-007-EN-1720 | Approval of Method Statement for Earthworks | 0 | 100% | 100% | 0
JDH4-02-007-EN-1730 | JDH4-02-007-EN-1730 | Approval of Method Statement for Concrete Works | 0 | 100% | 100% | 0
JDH4-02-007-EN-1740 | JDH4-02-007-EN-1740 | Approval of Method Statement for Waterproofing Works | 0 | 100% | 100% | 0
JDH4-02-007-EN-1750 | JDH4-02-007-EN-1750 | Approval of Method Statement for Asphalt | 0 | 100% | 100% | 0
Method Statements Staging Time | Method Statements Staging Time |  | 0 |  | 0% | 0
JDH4-02-007-EN-1760 | JDH4-02-007-EN-1760 | Staging Time of Method Statement for Earthworks | 0 | 100% | 100% | 0
JDH4-02-007-EN-1770 | JDH4-02-007-EN-1770 | Staging Time of Method Statement for Concrete Works | 0 | 100% | 100% | 0
JDH4-02-007-EN-1780 | JDH4-02-007-EN-1780 | Staging Time of Method Statement for Waterproofing Works | 0 | 100% | 100% | 0
JDH4-02-007-EN-1790 | JDH4-02-007-EN-1790 | Staging Time of Method Statement for Asphalt | 0 | 100% | 100% | 0
Pre-qualification and Material | Pre-qualification and Material |  | 1719130.43 |  | 100% | 1719130.43
Pre-qualification | Pre-qualification |  | 0 |  | 0% | 0
Road Works - Civil | Road Works - Civil |  | 0 |  | 0% | 0
Steel Reinforcement | Steel Reinforcement |  | 0 |  | 0% | 0
JDH4-02-007-SB-1580 | JDH4-02-007-SB-1580 | Pre-Qualification Submittal for Steel Reinforcement | 0 | 100% | 100% | 0
JDH4-02-007-SB-1590 | JDH4-02-007-SB-1590 | Pre-Qualification Approval for Steel Reinforcement | 0 | 100% | 100% | 0
Ready Mixed Concrete | Ready Mixed Concrete |  | 0 |  | 0% | 0
JDH4-02-007-SB-1600 | JDH4-02-007-SB-1600 | Pre-Qualification Submittal for Ready Mixed Concrete | 0 | 100% | 100% | 0
JDH4-02-007-SB-1610 | JDH4-02-007-SB-1610 | Pre-Qualification Approval for Ready Mixed Concrete | 0 | 100% | 100% | 0
Water Proofing | Water Proofing |  | 0 |  | 0% | 0
JDH4-02-007-SB-1620 | JDH4-02-007-SB-1620 | Pre-Qualification Submittal for Water Proofing | 0 | 100% | 100% | 0
JDH4-02-007-SB-1630 | JDH4-02-007-SB-1630 | Pre-Qualification Approval for Water Proofing | 0 | 100% | 100% | 0
Aggregate Base Course | Aggregate Base Course |  | 0 |  | 0% | 0
JDH4-02-007-SB-1000 | JDH4-02-007-SB-1000 | Pre-Qualification Submittal for Aggregate Base Cource | 0 | 100% | 100% | 0
JDH4-02-007-SB-1010 | JDH4-02-007-SB-1010 | Pre-Qualification Approval for Aggregate Base Cource | 0 | 100% | 100% | 0
Bituminous Base & Wearing Course | Bituminous Base & Wearing Course |  | 0 |  | 0% | 0
JDH4-02-007-SB-1020 | JDH4-02-007-SB-1020 | Pre-Qualification Submittal for Bituminous Base & Wearing Cource | 0 | 100% | 100% | 0
JDH4-02-007-SB-1030 | JDH4-02-007-SB-1030 | Pre-Qualification Approval for Bituminous & Wearing Cource | 0 | 100% | 100% | 0
Precast Concrete Kerb | Precast Concrete Kerb |  | 0 |  | 0% | 0
JDH4-02-007-SB-1050 | JDH4-02-007-SB-1050 | Pre-Qualification Approval for Precast Concrete Kerb | 0 | 100% | 100% | 0
JDH4-02-007-SB-1040 | JDH4-02-007-SB-1040 | Pre-Qualification Submittal for Precast Concrete Kerb | 0 | 100% | 100% | 0
Interlocking Block Pavers | Interlocking Block Pavers |  | 0 |  | 0% | 0
JDH4-02-007-SB-1070 | JDH4-02-007-SB-1070 | Pre-Qualification Approval for Interlocking Block Pavers | 0 | 100% | 100% | 0
JDH4-02-007-SB-1060 | JDH4-02-007-SB-1060 | Pre-Qualification Submittal for Interlocking Block Pavers | 0 | 100% | 100% | 0
Pavement Markings | Pavement Markings |  | 0 |  | 0% | 0
JDH4-02-007-SB-1080 | JDH4-02-007-SB-1080 | Pre-Qualification Submittal for Pavement Markings | 0 | 100% | 100% | 0
JDH4-02-007-SB-1090 | JDH4-02-007-SB-1090 | Pre-Qualification Approval for Pavement Markings | 0 | 100% | 100% | 0
Traffic Signs | Traffic Signs |  | 0 |  | 0% | 0
JDH4-02-007-SB-1100 | JDH4-02-007-SB-1100 | Pre-Qualification Submittal for Traffic Signs | 0 | 100% | 100% | 0
JDH4-02-007-SB-1110 | JDH4-02-007-SB-1110 | Pre-Qualification Approval for Traffic Signs | 0 | 100% | 100% | 0
Storm Network | Storm Network |  | 0 |  | 0% | 0
GRP Pipes | GRP Pipes |  | 0 |  | 0% | 0
JDH4-02-007-SB-1260 | JDH4-02-007-SB-1260 | Pre-Qualification Submittal for GRP Pipe | 0 | 100% | 100% | 0
JDH4-02-007-SB-1270 | JDH4-02-007-SB-1270 | Pre-Qualification Approval for GRP Pipe | 0 | 100% | 100% | 0
Catch Basin | Catch Basin |  | 0 |  | 0% | 0
JDH4-02-007-SB-1640 | JDH4-02-007-SB-1640 | Pre-Qualification Submittal for Catch Basin | 0 | 100% | 100% | 0
JDH4-02-007-SB-1650 | JDH4-02-007-SB-1650 | Pre-Qualification Approval for Catch Basin | 0 | 100% | 100% | 0
Inlet Manholes | Inlet Manholes |  | 0 |  | 0% | 0
JDH4-02-007-SB-1280 | JDH4-02-007-SB-1280 | Pre-Qualification Submittal for Inlet Manholes | 0 | 100% | 100% | 0
JDH4-02-007-SB-1290 | JDH4-02-007-SB-1290 | Pre-Qualification Approval for Inlet Manholes | 0 | 100% | 100% | 0
Sanitary Sewerage | Sanitary Sewerage |  | 0 |  | 0% | 0
GRP Pipes | GRP Pipes |  | 0 |  | 0% | 0
JDH4-02-007-SB-1220 | JDH4-02-007-SB-1220 | Pre-Qualification Submittal for GRP Pipe | 0 | 100% | 100% | 0
JDH4-02-007-SB-1230 | JDH4-02-007-SB-1230 | Pre-Qualification Approval for GRP Pipe | 0 | 100% | 100% | 0
Manholes | Manholes |  | 0 |  | 0% | 0
JDH4-02-007-SB-1240 | JDH4-02-007-SB-1240 | Pre-Qualification Submittal for Manholes | 0 | 100% | 100% | 0
JDH4-02-007-SB-1250 | JDH4-02-007-SB-1250 | Pre-Qualification Approval for Manholes | 0 | 100% | 100% | 0
TSE Network | TSE Network |  | 0 |  | 0% | 0
HDPE Pipe (PN 16) | HDPE Pipe (PN 16) |  | 0 |  | 0% | 0
JDH4-02-007-SB-1200 | JDH4-02-007-SB-1200 | Pre-Qualification Submittal for HDPE Pipe (PN 16) | 0 | 100% | 100% | 0
JDH4-02-007-SB-1210 | JDH4-02-007-SB-1210 | Pre-Qualification Approval for HDPE Pipe (PN 16) | 0 | 100% | 100% | 0
Valves / Chambers | Valves / Chambers |  | 0 |  | 0% | 0
JDH4-02-007-SB-1440 | JDH4-02-007-SB-1440 | Pre-Qualification Submittal for Valves / Chambers | 0 | 100% | 100% | 0
JDH4-02-007-SB-1450 | JDH4-02-007-SB-1450 | Pre-Qualification Approval for Valves / Chambers | 0 | 100% | 100% | 0
Risers | Risers |  | 0 |  | 0% | 0
JDH4-02-007-SB-1460 | JDH4-02-007-SB-1460 | Pre-Qualification Submittal for Risers | 0 | 100% | 100% | 0
JDH4-02-007-SB-1470 | JDH4-02-007-SB-1470 | Pre-Qualification Approval for Risers | 0 | 100% | 100% | 0
Potable Water Network | Potable Water Network |  | 0 |  | 0% | 0
HDPE Pipe (PN 16) | HDPE Pipe (PN 16) |  | 0 |  | 0% | 0
JDH4-02-007-SB-1180 | JDH4-02-007-SB-1180 | Pre-Qualification Submittal for HDPE Pipe (PN 16) | 0 | 100% | 100% | 0
JDH4-02-007-SB-1190 | JDH4-02-007-SB-1190 | Pre-Qualification Approval for HDPE Pipe (PN 16) | 0 | 100% | 100% | 0
Valves / Chambers | Valves / Chambers |  | 0 |  | 0% | 0
JDH4-02-007-SB-1420 | JDH4-02-007-SB-1420 | Pre-Qualification Submittal for Valves / Chambers | 0 | 100% | 100% | 0
JDH4-02-007-SB-1430 | JDH4-02-007-SB-1430 | Pre-Qualification Approval for Valves / Chambers | 0 | 100% | 100% | 0
Fire Hydrant | Fire Hydrant |  | 0 |  | 0% | 0
JDH4-02-007-SB-1660 | JDH4-02-007-SB-1660 | Pre-Qualification Submittal for Fire Hydrant | 0 | 100% | 100% | 0
JDH4-02-007-SB-1670 | JDH4-02-007-SB-1670 | Pre-Qualification Approval for Fire Hydrant | 0 | 100% | 100% | 0
Electrical Network | Electrical Network |  | 0 |  | 0% | 0
Pipe for the Duct | Pipe for the Duct |  | 0 |  | 0% | 0
JDH4-02-007-SB-1120 | JDH4-02-007-SB-1120 | Pre-Qualification Submittal for Pipe for the Duct | 0 | 100% | 100% | 0
JDH4-02-007-SB-1130 | JDH4-02-007-SB-1130 | Pre-Qualification Approval for Pipe for the Duct | 0 | 100% | 100% | 0
Low Voltage Cables | Low Voltage Cables |  | 0 |  | 0% | 0
JDH4-02-007-SB-1320 | JDH4-02-007-SB-1320 | Pre-Qualification Submittal for Low Voltage Cables | 0 | 100% | 100% | 0
JDH4-02-007-SB-1330 | JDH4-02-007-SB-1330 | Pre-Qualification Approval for Low Voltage Cables | 0 | 100% | 100% | 0
Earthing System | Earthing System |  | 0 |  | 0% | 0
JDH4-02-007-SB-1160 | JDH4-02-007-SB-1160 | Pre-Qualification Submittal for Earthing System | 0 | 100% | 100% | 0
JDH4-02-007-SB-1170 | JDH4-02-007-SB-1170 | Pre-Qualification Approval for Earthing System | 0 | 100% | 100% | 0
Medium Voltage Cable | Medium Voltage Cable |  | 0 |  | 0% | 0
JDH4-02-007-SB-1300 | JDH4-02-007-SB-1300 | Pre-Qualification Submittal for Medium Voltage Cable | 0 | 100% | 100% | 0
JDH4-02-007-SB-1310 | JDH4-02-007-SB-1310 | Pre-Qualification Approval for Medium Voltage Cable | 0 | 100% | 100% | 0
Low Voltage Distribution Panel | Low Voltage Distribution Panel |  | 0 |  | 0% | 0
JDH4-02-007-SB-1140 | JDH4-02-007-SB-1140 | Pre-Qualification Submittal for Low Voltage Distribution Panel | 0 | 100% | 100% | 0
JDH4-02-007-SB-1150 | JDH4-02-007-SB-1150 | Pre-Qualification Approval for Low Voltage Distribution Panel | 0 | 100% | 100% | 0
Unit Sub Station | Unit Sub Station |  | 0 |  | 0% | 0
JDH4-02-007-SB-1380 | JDH4-02-007-SB-1380 | Pre-Qualification Submittal for Unit Sub Station | 0 | 100% | 100% | 0
JDH4-02-007-SB-1390 | JDH4-02-007-SB-1390 | Pre-Qualification Approval for Unit Sub Station | 0 | 100% | 100% | 0
Ring Main Unit (RMU) | Ring Main Unit (RMU) |  | 0 |  | 0% | 0
JDH4-02-007-SB-1400 | JDH4-02-007-SB-1400 | Pre-Qualification Submittal for Ring main Unit (RMU) | 0 | 100% | 100% | 0
JDH4-02-007-SB-1410 | JDH4-02-007-SB-1410 | Pre-Qualification Approval for Ring main Unit (RMU) | 0 | 100% | 100% | 0
Lighting poles | Lighting poles |  | 0 |  | 0% | 0
JDH4-02-007-SB-1340 | JDH4-02-007-SB-1340 | Pre-Qualification Submittal for Lighting poles | 0 | 100% | 100% | 0
JDH4-02-007-SB-1350 | JDH4-02-007-SB-1350 | Pre-Qualification Approval for Lighting poles | 0 | 100% | 100% | 0
Lighting panels/Feeder Pillers | Lighting panels/Feeder Pillers |  | 0 |  | 0% | 0
JDH4-02-007-SB-1520 | JDH4-02-007-SB-1520 | Pre-Qualification Submittal for Lighting panels/Feeder Pillers | 0 | 100% | 100% | 0
JDH4-02-007-SB-1530 | JDH4-02-007-SB-1530 | Pre-Qualification Approval for Lighting panels/Feeder Pillers | 0 | 100% | 100% | 0
Street Lighting Luminaire | Street Lighting Luminaire |  | 0 |  | 0% | 0
JDH4-02-007-SB-1360 | JDH4-02-007-SB-1360 | Pre-Qualification Submittal for Street Lighting Luminaire | 0 | 100% | 100% | 0
JDH4-02-007-SB-1370 | JDH4-02-007-SB-1370 | Pre-Qualification Approval for Street Lighting Luminaire | 0 | 100% | 100% | 0
Telecommunications | Telecommunications |  | 0 |  | 0% | 0
Pipe for the Duct | Pipe for the Duct |  | 0 |  | 0% | 0
JDH4-02-007-SB-1550 | JDH4-02-007-SB-1550 | Pre-Qualification Approval for Pipe for the Duct | 0 | 100% | 100% | 0
JDH4-02-007-SB-1540 | JDH4-02-007-SB-1540 | Pre-Qualification Submittal for Pipe for the Duct | 0 | 100% | 100% | 0
Sewage Lift Station | Sewage Lift Station |  | 0 |  | 0% | 0
Thermal & Moisture Protection | Thermal & Moisture Protection |  | 0 |  | 0% | 0
JDH4-02-007-SB-1490 | JDH4-02-007-SB-1490 | Pre-Qualification Submittal for Thermal & Moisture Protection | 0 | 100% | 100% | 0
JDH4-02-007-SB-1510 | JDH4-02-007-SB-1510 | Pre-Qualification Approval for Thermal & Moisture Protection | 0 | 100% | 100% | 0
Metals | Metals |  | 0 |  | 0% | 0
JDH4-02-007-SB-1480 | JDH4-02-007-SB-1480 | Pre-Qualification Submittal for Metal | 0 | 100% | 100% | 0
JDH4-02-007-SB-1500 | JDH4-02-007-SB-1500 | Pre-Qualification Approval for Metal | 0 | 100% | 100% | 0
Pumps | Pumps |  | 0 |  | 0% | 0
JDH4-02-007-SB-1560 | JDH4-02-007-SB-1560 | Pre-Qualification Submittal for pumps | 0 | 100% | 100% | 0
JDH4-02-007-SB-1570 | JDH4-02-007-SB-1570 | Pre-Qualification Approval for pumps | 0 | 100% | 100% | 0
Pipes,Fittings & Valves | Pipes,Fittings & Valves |  | 0 |  | 0% | 0
JDH4-02-007-SB-1680 | JDH4-02-007-SB-1680 | Pre-Qualification Submittal for Pipes,Fittings & Valves | 0 | 100% | 100% | 0
JDH4-02-007-SB-1700 | JDH4-02-007-SB-1700 | Pre-Qualification Approval for Pipes,Fittings & Valves | 0 | 100% | 100% | 0
Odours scrubbing system | Odours scrubbing system |  | 0 |  | 0% | 0
JDH4-02-007-SB-1690 | JDH4-02-007-SB-1690 | Pre-Qualification Submittal for Odours Scrubbing System | 0 | 100% | 100% | 0
JDH4-02-007-SB-1710 | JDH4-02-007-SB-1710 | Pre-Qualification Approval for Odours Scrubbing System | 0 | 100% | 100% | 0
Crane | Crane |  | 0 |  | 0% | 0
JDH4-02-007-SB-1720 | JDH4-02-007-SB-1720 | Pre-Qualification Submittal for Crane | 0 | 100% | 100% | 0
JDH4-02-007-SB-1730 | JDH4-02-007-SB-1730 | Pre-Qualification Approval for Crane | 0 | 100% | 100% | 0
Air Vents | Air Vents |  | 0 |  | 0% | 0
JDH4-02-007-SB-1800 | JDH4-02-007-SB-1800 | Pre-Qualification Submittal for Air Vents | 0 | 100% | 100% | 0
JDH4-02-007-SB-1820 | JDH4-02-007-SB-1820 | Pre-Qualification Approval for Air Vents | 0 | 100% | 100% | 0
Screening Container | Screening Container |  | 0 |  | 0% | 0
JDH4-02-007-SB-1740 | JDH4-02-007-SB-1740 | Pre-Qualification Submittal for Screening Container | 0 | 100% | 100% | 0
JDH4-02-007-SB-1760 | JDH4-02-007-SB-1760 | Pre-Qualification Approval for Screening Container | 0 | 100% | 100% | 0
Baffle Plates | Baffle Plates |  | 0 |  | 0% | 0
JDH4-02-007-SB-1810 | JDH4-02-007-SB-1810 | Pre-Qualification Submittal for Baffle plates | 0 | 100% | 100% | 0
JDH4-02-007-SB-1830 | JDH4-02-007-SB-1830 | Pre-Qualification Approval for Baffle plates | 0 | 100% | 100% | 0
Anti-Water Hammer Equipment | Anti-Water Hammer Equipment |  | 0 |  | 0% | 0
JDH4-02-007-SB-1840 | JDH4-02-007-SB-1840 | Pre-Qualification Submittal for Anti-Water Hammer Equipment | 0 | 100% | 100% | 0
JDH4-02-007-SB-1850 | JDH4-02-007-SB-1850 | Pre-Qualification Approval for Anti-Water Hammer Equipment | 0 | 100% | 100% | 0
Air Conditioning and Ventilation | Air Conditioning and Ventilation |  | 0 |  | 0% | 0
JDH4-02-007-SB-1750 | JDH4-02-007-SB-1750 | Pre-Qualification Submittal for Air Conditioning and Ventilation | 0 | 100% | 100% | 0
JDH4-02-007-SB-1770 | JDH4-02-007-SB-1770 | Pre-Qualification Approval for Air Conditioning and Ventilation | 0 | 100% | 100% | 0
Fuel System | Fuel System |  | 0 |  | 0% | 0
JDH4-02-007-SB-1780 | JDH4-02-007-SB-1780 | Pre-Qualification Submittal for Fuel System | 0 | 100% | 100% | 0
JDH4-02-007-SB-1790 | JDH4-02-007-SB-1790 | Pre-Qualification Approval for Fuel System | 0 | 100% | 100% | 0
Fire Fighting System | Fire Fighting System |  | 0 |  | 0% | 0
JDH4-02-007-SB-1920 | JDH4-02-007-SB-1920 | Pre-Qualification Submittal for Fire Fighting System | 0 | 100% | 100% | 0
JDH4-02-007-SB-1930 | JDH4-02-007-SB-1930 | Pre-Qualification Approval for Fire Fighting System | 0 | 100% | 100% | 0
Main Distribution Board /MCC panels | Main Distribution Board /MCC panels |  | 0 |  | 0% | 0
JDH4-02-007-SB-1860 | JDH4-02-007-SB-1860 | Pre-Qualification Submittal for Main Distribution Board/MCC Panels | 0 | 100% | 100% | 0
JDH4-02-007-SB-1870 | JDH4-02-007-SB-1870 | Pre-Qualification Approval for Main Distribution Board/MCC Panels | 0 | 100% | 100% | 0
Final Panel boards | Final Panel boards |  | 0 |  | 0% | 0
JDH4-02-007-SB-1880 | JDH4-02-007-SB-1880 | Pre-Qualification Submittal for Final Panel Boards | 0 | 100% | 100% | 0
JDH4-02-007-SB-1890 | JDH4-02-007-SB-1890 | Pre-Qualification Approval for Final Panel Boards | 0 | 100% | 100% | 0
Local Control Panel/ Monitoring Control Panel | Local Control Panel/ Monitoring Control Panel |  | 0 |  | 0% | 0
JDH4-02-007-SB-1900 | JDH4-02-007-SB-1900 | Pre-Qualification Submittal for Local Control Panel / Monitoring Control Panel | 0 | 100% | 100% | 0
JDH4-02-007-SB-1910 | JDH4-02-007-SB-1910 | Pre-Qualification Approval for Local Control Panel / Monitoring Control Panel | 0 | 100% | 100% | 0
Engine Generators | Engine Generators |  | 0 |  | 0% | 0
JDH4-02-007-SB-2060 | JDH4-02-007-SB-2060 | Pre-Qualification Submittal for Engine Generators | 0 | 100% | 100% | 0
JDH4-02-007-SB-2070 | JDH4-02-007-SB-2070 | Pre-Qualification Approval for Engine Generators | 0 | 100% | 100% | 0
Standby Diesel Generator | Standby Diesel Generator |  | 0 |  | 0% | 0
JDH4-02-007-SB-2040 | JDH4-02-007-SB-2040 | Pre-Qualification Submittal for Standby Diesel Generator | 0 | 100% | 100% | 0
JDH4-02-007-SB-2050 | JDH4-02-007-SB-2050 | Pre-Qualification Approval for Standby Diesel Generator | 0 | 100% | 100% | 0
Power Factor Correction Capacitor Bank | Power Factor Correction Capacitor Bank |  | 0 |  | 0% | 0
JDH4-02-007-SB-2000 | JDH4-02-007-SB-2000 | Pre-Qualification Submittal for Power Factor correction Capacitor Bank | 0 | 100% | 100% | 0
JDH4-02-007-SB-2010 | JDH4-02-007-SB-2010 | Pre-Qualification Approval for Power Factor correction Capacitor Bank | 0 | 100% | 100% | 0
Low-Voltage Electrical Power Conductors and Cables | Low-Voltage Electrical Power Conductors and Cables |  | 0 |  | 0% | 0
JDH4-02-007-SB-2020 | JDH4-02-007-SB-2020 | Pre-Qualification Submittal for Low Voltage Electrical Power Conductors & Cables | 0 | 100% | 100% | 0
JDH4-02-007-SB-2030 | JDH4-02-007-SB-2030 | Pre-Qualification Approval for Low Voltage Electrical Power Conductors & Cables | 0 | 100% | 100% | 0
Low Voltage Feeder Cable | Low Voltage Feeder Cable |  | 0 |  | 0% | 0
JDH4-02-007-SB-1980 | JDH4-02-007-SB-1980 | Pre-Qualification Submittal for Low Voltage Feeder Cable | 0 | 100% | 100% | 0
JDH4-02-007-SB-1990 | JDH4-02-007-SB-1990 | Pre-Qualification Approval for Low Voltage Feeder Cable | 0 | 100% | 100% | 0
Wiring Devices | Wiring Devices |  | 0 |  | 0% | 0
JDH4-02-007-SB-1940 | JDH4-02-007-SB-1940 | Pre-Qualification Submittal for Wiring Devices | 0 | 100% | 100% | 0
JDH4-02-007-SB-1950 | JDH4-02-007-SB-1950 | Pre-Qualification Approval for Wiring Devices | 0 | 100% | 100% | 0
Enclosed Switches and Circuit Breakers | Enclosed Switches and Circuit Breakers |  | 0 |  | 0% | 0
JDH4-02-007-SB-1960 | JDH4-02-007-SB-1960 | Pre-Qualification Submittal for Enclosed Switches and Circuit Breakers | 0 | 100% | 100% | 0
JDH4-02-007-SB-1970 | JDH4-02-007-SB-1970 | Pre-Qualification Approval for Enclosed Switches and Circuit Breakers | 0 | 100% | 100% | 0
Raceways for Electrical Systems | Raceways for Electrical Systems |  | 0 |  | 0% | 0
JDH4-02-007-SB-2100 | JDH4-02-007-SB-2100 | Pre-Qualification Submittal for Raceways for Electrical System | 0 | 100% | 100% | 0
JDH4-02-007-SB-2110 | JDH4-02-007-SB-2110 | Pre-Qualification Approval for Raceways for Electrical System | 0 | 100% | 100% | 0
Electrical Manholes | Electrical Manholes |  | 0 |  | 0% | 0
JDH4-02-007-SB-2140 | JDH4-02-007-SB-2140 | Pre-Qualification Submittal for Electrical Manholes | 0 | 100% | 100% | 0
JDH4-02-007-SB-2150 | JDH4-02-007-SB-2150 | Pre-Qualification Approval for Electrical Manholes | 0 | 100% | 100% | 0
Security System (CCTV System) | Security System (CCTV System) |  | 0 |  | 0% | 0
JDH4-02-007-SB-2080 | JDH4-02-007-SB-2080 | Pre-Qualification Submittal for Security System (CCTV System) | 0 | 100% | 100% | 0
JDH4-02-007-SB-2090 | JDH4-02-007-SB-2090 | Pre-Qualification Approval for Security System (CCTV System) | 0 | 100% | 100% | 0
ICT (Data& telephone System) | ICT (Data& telephone System) |  | 0 |  | 0% | 0
JDH4-02-007-SB-2120 | JDH4-02-007-SB-2120 | Pre-Qualification Submittal for ICT (Data & Telephone System) | 0 | 100% | 100% | 0
JDH4-02-007-SB-2130 | JDH4-02-007-SB-2130 | Pre-Qualification Approval for ICT (Data & Telephone System) | 0 | 100% | 100% | 0
Programmable Logic Controllers | Programmable Logic Controllers |  | 0 |  | 0% | 0
JDH4-02-007-SB-2200 | JDH4-02-007-SB-2200 | Pre-Qualification Submittal for Programmable Logic Controllers | 0 | 100% | 100% | 0
JDH4-02-007-SB-2210 | JDH4-02-007-SB-2210 | Pre-Qualification Approval for Programmable Logic Controllers | 0 | 100% | 100% | 0
Process Control Wiring | Process Control Wiring |  | 0 |  | 0% | 0
JDH4-02-007-SB-2180 | JDH4-02-007-SB-2180 | Pre-Qualification Submittal for Process Control Wiring | 0 | 100% | 100% | 0
JDH4-02-007-SB-2190 | JDH4-02-007-SB-2190 | Pre-Qualification Approval for Process Control Wiring | 0 | 100% | 100% | 0
Instrumentation for Process Systems | Instrumentation for Process Systems |  | 0 |  | 0% | 0
JDH4-02-007-SB-2160 | JDH4-02-007-SB-2160 | Pre-Qualification Submittal for Instrumentation Control Wiring | 0 | 100% | 100% | 0
JDH4-02-007-SB-2170 | JDH4-02-007-SB-2170 | Pre-Qualification Approval for Instrumentation Control Wiring | 0 | 100% | 100% | 0
Material Submittal & Approval | Material Submittal & Approval |  | 1719130.43 |  | 100% | 1719130.43
Road Works - Civil | Road Works - Civil |  | 253642.23 |  | 100% | 253642.23
Steel Reinforcement | Steel Reinforcement |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1590 | JDH4-02-007-MA-1590 | Material Approval for Steel Reinforcement | 28182.47 | 100% | 100% | 28182.47
JDH4-02-007-MA-1580 | JDH4-02-007-MA-1580 | Material Submittal for Steel Reinforcement | 0 | 100% | 100% | 0
Ready Mixed Concrete | Ready Mixed Concrete |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1610 | JDH4-02-007-MA-1610 | Material Approval for Ready Mixed Concrete | 28182.47 | 100% | 100% | 28182.47
JDH4-02-007-MA-1600 | JDH4-02-007-MA-1600 | Material Submittal for Ready Mixed Concrete | 0 | 100% | 100% | 0
Water Proofing | Water Proofing |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1630 | JDH4-02-007-MA-1630 | Material Approval for Water Proofing | 28182.47 | 100% | 100% | 28182.47
JDH4-02-007-MA-1620 | JDH4-02-007-MA-1620 | Material Submittal for Water Proofing | 0 | 100% | 100% | 0
Aggregate Base Course | Aggregate Base Course |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1010 | JDH4-02-007-MA-1010 | Material Approval for Aggregate Base Cource | 28182.47 | 100% | 100% | 28182.47
JDH4-02-007-MA-1000 | JDH4-02-007-MA-1000 | Material Submittal for Aggregate Base Cource | 0 | 100% | 100% | 0
Bituminous Base & Wearing Course | Bituminous Base & Wearing Course |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1030 | JDH4-02-007-MA-1030 | Material Approval for Bituminous & Wearing Cource | 28182.47 | 100% | 100% | 28182.47
JDH4-02-007-MA-1020 | JDH4-02-007-MA-1020 | Material Submittal for Bituminous Base & Wearing Cource | 0 | 100% | 100% | 0
Precast Concrete Kerb | Precast Concrete Kerb |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1040 | JDH4-02-007-MA-1040 | Material Submittal for Precast Concrete Kerb | 0 | 100% | 100% | 0
JDH4-02-007-MA-1050 | JDH4-02-007-MA-1050 | Material Approval for Precast Concrete Kerb | 28182.47 | 100% | 100% | 28182.47
Interlocking Block Pavers | Interlocking Block Pavers |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1060 | JDH4-02-007-MA-1060 | Material Submittal for Interlocking Block Pavers | 0 | 100% | 100% | 0
JDH4-02-007-MA-1070 | JDH4-02-007-MA-1070 | Material Approval for Interlocking Block Pavers | 28182.47 | 100% | 100% | 28182.47
Pavement Markings | Pavement Markings |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1080 | JDH4-02-007-MA-1080 | Material Submittal for Pavement Markings | 0 | 100% | 100% | 0
JDH4-02-007-MA-1090 | JDH4-02-007-MA-1090 | Material Approval for Pavement Markings | 28182.47 | 100% | 100% | 28182.47
Traffic Signs | Traffic Signs |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1100 | JDH4-02-007-MA-1100 | Material Submittal for Traffic Signs | 0 | 100% | 100% | 0
JDH4-02-007-MA-1110 | JDH4-02-007-MA-1110 | Material Approval for Traffic Signs | 28182.47 | 100% | 100% | 28182.47
Storm Network | Storm Network |  | 84547.41 |  | 100% | 84547.41
GRP Pipes | GRP Pipes |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1270 | JDH4-02-007-MA-1270 | Material Approval for GRP Pipe | 28182.47 | 100% | 100% | 28182.47
JDH4-02-007-MA-1250 | JDH4-02-007-MA-1250 | Material Submittal for GRP Pipe | 0 | 100% | 100% | 0
Catch Basin | Catch Basin |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1650 | JDH4-02-007-MA-1650 | Material Approval for Catch Basin | 28182.47 | 100% | 100% | 28182.47
JDH4-02-007-MA-1640 | JDH4-02-007-MA-1640 | Material Submittal for Catch Basin | 0 | 100% | 100% | 0
Inlet Manholes | Inlet Manholes |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1290 | JDH4-02-007-MA-1290 | Material Approval for Inlet Manholes | 28182.47 | 100% | 100% | 28182.47
JDH4-02-007-MA-1280 | JDH4-02-007-MA-1280 | Material Submittal for Inlet Manholes | 0 | 100% | 100% | 0
Sanitary Sewerage | Sanitary Sewerage |  | 56364.94 |  | 100% | 56364.94
GRP Pipes | GRP Pipes |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1230 | JDH4-02-007-MA-1230 | Material Approval for GRP Pipe | 28182.47 | 100% | 100% | 28182.47
JDH4-02-007-MA-1220 | JDH4-02-007-MA-1220 | Material Submittal for GRP Pipe | 0 | 100% | 100% | 0
Manholes | Manholes |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1260 | JDH4-02-007-MA-1260 | Material Approval for Manholes | 28182.47 | 100% | 100% | 28182.47
JDH4-02-007-MA-1240 | JDH4-02-007-MA-1240 | Material Submittal for Manholes | 0 | 100% | 100% | 0
TSE Network | TSE Network |  | 84547.41 |  | 100% | 84547.41
HDPE Pipe (PN 16) | HDPE Pipe (PN 16) |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1200 | JDH4-02-007-MA-1200 | Material Submittal for HDPE Pipe (PN 16) | 0 | 100% | 100% | 0
JDH4-02-007-MA-1210 | JDH4-02-007-MA-1210 | Material Approval for HDPE Pipe (PN 16) | 28182.47 | 100% | 100% | 28182.47
Valves / Chambers | Valves / Chambers |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1440 | JDH4-02-007-MA-1440 | Material Submittal for Valves / Chambers | 0 | 100% | 100% | 0
JDH4-02-007-MA-1450 | JDH4-02-007-MA-1450 | Material Approval for Valves / Chambers | 28182.47 | 100% | 100% | 28182.47
Risers | Risers |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1460 | JDH4-02-007-MA-1460 | Material Submittal for Risers | 0 | 100% | 100% | 0
JDH4-02-007-MA-1470 | JDH4-02-007-MA-1470 | Material Approval for Risers | 28182.47 | 100% | 100% | 28182.47
Potable Water Network | Potable Water Network |  | 84547.41 |  | 100% | 84547.41
HDPE Pipe (PN 16) | HDPE Pipe (PN 16) |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1180 | JDH4-02-007-MA-1180 | Material Submittal for HDPE Pipe (PN 16) | 0 | 100% | 100% | 0
JDH4-02-007-MA-1190 | JDH4-02-007-MA-1190 | Material Approval for HDPE Pipe (PN 16) | 28182.47 | 100% | 100% | 28182.47
Valves / Chambers | Valves / Chambers |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1420 | JDH4-02-007-MA-1420 | Material Submittal for Valves / Chambers | 0 | 100% | 100% | 0
JDH4-02-007-MA-1430 | JDH4-02-007-MA-1430 | Material Approval for Valves / Chambers | 28182.47 | 100% | 100% | 28182.47
Fire Hydrant | Fire Hydrant |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1660 | JDH4-02-007-MA-1660 | Material Submittal for Fire Hydrant | 0 | 100% | 100% | 0
JDH4-02-007-MA-1670 | JDH4-02-007-MA-1670 | Material Approval for Fire Hydrant | 28182.47 | 100% | 100% | 28182.47
Electrical Network | Electrical Network |  | 281824.7 |  | 100% | 281824.7
Pipe for the Duct | Pipe for the Duct |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1120 | JDH4-02-007-MA-1120 | Material Submittal for Pipe for the Duct | 0 | 100% | 100% | 0
JDH4-02-007-MA-1130 | JDH4-02-007-MA-1130 | Material Approval for Pipe for the Duct By SEC | 28182.47 | 100% | 100% | 28182.47
Low Voltage Cables | Low Voltage Cables |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1330 | JDH4-02-007-MA-1330 | Material Approval for Low Voltage Cables By SEC | 28182.47 | 100% | 100% | 28182.47
JDH4-02-007-MA-1320 | JDH4-02-007-MA-1320 | Material Submittal for Low Voltage Cables | 0 | 100% | 100% | 0
Earthing System | Earthing System |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1160 | JDH4-02-007-MA-1160 | Material Submittal for Earthing System | 0 | 100% | 100% | 0
JDH4-02-007-MA-1170 | JDH4-02-007-MA-1170 | Material Approval for Earthing System By SEC | 28182.47 | 100% | 100% | 28182.47
Medium Voltage Cable | Medium Voltage Cable |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1300 | JDH4-02-007-MA-1300 | Material Submittal for Medium Voltage Cable | 0 | 100% | 100% | 0
JDH4-02-007-MA-1310 | JDH4-02-007-MA-1310 | Material Approval for Medium Voltage Cable By SEC | 28182.47 | 100% | 100% | 28182.47
Low Voltage Distribution Panel | Low Voltage Distribution Panel |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1140 | JDH4-02-007-MA-1140 | Material Submittal for Low Voltage Distribution Panel | 0 | 100% | 100% | 0
JDH4-02-007-MA-1150 | JDH4-02-007-MA-1150 | Material Approval for Low Voltage Distribution Panel By SEC | 28182.47 | 100% | 100% | 28182.47
Unit Sub Station | Unit Sub Station |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1380 | JDH4-02-007-MA-1380 | Material Submittal for Unit Sub Station | 0 | 100% | 100% | 0
JDH4-02-007-MA-1390 | JDH4-02-007-MA-1390 | Material Approval for Unit Sub Station By SEC | 28182.47 | 100% | 100% | 28182.47
Ring Main Unit (RMU) | Ring Main Unit (RMU) |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1400 | JDH4-02-007-MA-1400 | Material Submittal for Ring main Unit (RMU) | 0 | 100% | 100% | 0
JDH4-02-007-MA-1410 | JDH4-02-007-MA-1410 | Material Approval for Ring main Unit (RMU) By SEC | 28182.47 | 100% | 100% | 28182.47
Lighting poles | Lighting poles |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1340 | JDH4-02-007-MA-1340 | Material Submittal for Lighting poles | 0 | 100% | 100% | 0
JDH4-02-007-MA-1350 | JDH4-02-007-MA-1350 | Material Approval for Lighting poles By SEC | 28182.47 | 100% | 100% | 28182.47
Lighting panels/Feeder Pillers | Lighting panels/Feeder Pillers |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1515 | JDH4-02-007-MA-1515 | Material Submittal for Lighting panels/Feeder Pillers By SEC | 0 | 100% | 100% | 0
JDH4-02-007-MA-1520 | JDH4-02-007-MA-1520 | Material Approval for Lighting panels/Feeder Pillers | 28182.47 | 100% | 100% | 28182.47
Street Lighting Luminaire | Street Lighting Luminaire |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1360 | JDH4-02-007-MA-1360 | Material Submittal for Street Lighting Luminaire | 0 | 100% | 100% | 0
JDH4-02-007-MA-1370 | JDH4-02-007-MA-1370 | Material Approval for Street Lighting Luminaire By SEC | 28182.47 | 100% | 100% | 28182.47
Telecommunications | Telecommunications |  | 28182.47 |  | 100% | 28182.47
Pipe for the Duct | Pipe for the Duct |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1550 | JDH4-02-007-MA-1550 | Material Approval for Pipe for the Duct | 28182.47 | 100% | 100% | 28182.47
JDH4-02-007-MA-1540 | JDH4-02-007-MA-1540 | Material Submittal for Pipe for the Duct | 0 | 100% | 100% | 0
Sewage Lift Station | Sewage Lift Station |  | 845473.86 |  | 100% | 845473.86
Thermal & Moisture Protection | Thermal & Moisture Protection |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1490 | JDH4-02-007-MA-1490 | Material Submittal for Thermal & Moisture Protection | 0 | 100% | 100% | 0
JDH4-02-007-MA-1510 | JDH4-02-007-MA-1510 | Material Approval for Thermal & Moisture Protection | 28182.47 | 100% | 100% | 28182.47
Metals | Metals |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1480 | JDH4-02-007-MA-1480 | Material Submittal for Metal | 0 | 100% | 100% | 0
JDH4-02-007-MA-1500 | JDH4-02-007-MA-1500 | Material Approval for Metal | 28182.47 | 100% | 100% | 28182.47
Pumps | Pumps |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1560 | JDH4-02-007-MA-1560 | Material Submittal for pumps | 0 | 100% | 100% | 0
JDH4-02-007-MA-1570 | JDH4-02-007-MA-1570 | Material Approval for pumps | 28182.47 | 100% | 100% | 28182.47
Pipes,Fittings & Valves | Pipes,Fittings & Valves |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1680 | JDH4-02-007-MA-1680 | Material Submittal for Pipes,Fittings & Valves | 0 | 100% | 100% | 0
JDH4-02-007-MA-1700 | JDH4-02-007-MA-1700 | Material Approval for Pipes,Fittings & Valves | 28182.47 | 100% | 100% | 28182.47
Odours scrubbing system | Odours scrubbing system |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1690 | JDH4-02-007-MA-1690 | Material Submittal for Odours Scrubbing System | 0 | 100% | 100% | 0
JDH4-02-007-MA-1710 | JDH4-02-007-MA-1710 | Material Approval for Odours Scrubbing System | 28182.47 | 100% | 100% | 28182.47
Crane | Crane |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1720 | JDH4-02-007-MA-1720 | Material Submittal for Crane | 0 | 100% | 100% | 0
JDH4-02-007-MA-1730 | JDH4-02-007-MA-1730 | Material Approval for Crane | 28182.47 | 100% | 100% | 28182.47
Air Vents | Air Vents |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1800 | JDH4-02-007-MA-1800 | Material Submittal for Air Vents | 0 | 100% | 100% | 0
JDH4-02-007-MA-1820 | JDH4-02-007-MA-1820 | Material Approval for Air Vents | 28182.47 | 100% | 100% | 28182.47
Screening Container | Screening Container |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1740 | JDH4-02-007-MA-1740 | Material Submittal for Screening Container | 0 | 100% | 100% | 0
JDH4-02-007-MA-1760 | JDH4-02-007-MA-1760 | Material Approval for Screening Container | 28182.47 | 100% | 100% | 28182.47
Baffle Plates | Baffle Plates |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1810 | JDH4-02-007-MA-1810 | Material Submittal for Baffle plates | 0 | 100% | 100% | 0
JDH4-02-007-MA-1830 | JDH4-02-007-MA-1830 | Material Approval for Baffle plates | 28182.47 | 100% | 100% | 28182.47
Anti-Water Hammer Equipment | Anti-Water Hammer Equipment |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1840 | JDH4-02-007-MA-1840 | Material Submittal for Anti-Water Hammer Equipment | 0 | 100% | 100% | 0
JDH4-02-007-MA-1850 | JDH4-02-007-MA-1850 | Material Approval for Anti-Water Hammer Equipment | 28182.47 | 100% | 100% | 28182.47
Air Conditioning and Ventilation | Air Conditioning and Ventilation |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1750 | JDH4-02-007-MA-1750 | Material Submittal for Air Conditioning and Ventilation | 0 | 100% | 100% | 0
JDH4-02-007-MA-1770 | JDH4-02-007-MA-1770 | Material Approval for Air Conditioning and Ventilation | 28182.47 | 100% | 100% | 28182.47
Fuel System | Fuel System |  | 28182.23 |  | 100% | 28182.23
JDH4-02-007-MA-1780 | JDH4-02-007-MA-1780 | Material Submittal for Fuel System | 0 | 100% | 100% | 0
JDH4-02-007-MA-1790 | JDH4-02-007-MA-1790 | Material Approval for Fuel System(Completed) | 14091.23 | 100% | 100% | 14091.23
JDH4-02-007-MA-1790R | JDH4-02-007-MA-1790R | Material Approval for Fuel System | 14091 | 100% | 100% | 14091
Fire Fighting System | Fire Fighting System |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1920 | JDH4-02-007-MA-1920 | Material Submittal for Fire Fighting System | 0 | 100% | 100% | 0
JDH4-02-007-MA-1930 | JDH4-02-007-MA-1930 | Material Approval for Fire Fighting System | 28182.47 | 100% | 100% | 28182.47
Main Distribution Board /MCC panels | Main Distribution Board /MCC panels |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1860 | JDH4-02-007-MA-1860 | Material Submittal for Main Distribution Board/MCC Panels | 0 | 100% | 100% | 0
JDH4-02-007-MA-1870 | JDH4-02-007-MA-1870 | Material Approval for Main Distribution Board/MCC Panels | 28182.47 | 100% | 100% | 28182.47
Final Panel boards | Final Panel boards |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1880 | JDH4-02-007-MA-1880 | Material Submittal for Final Panel Boards | 0 | 100% | 100% | 0
JDH4-02-007-MA-1890 | JDH4-02-007-MA-1890 | Material Approval for Final Panel Boards | 28182.47 | 100% | 100% | 28182.47
Local Control Panel/ Monitoring Control Panel | Local Control Panel/ Monitoring Control Panel |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1900 | JDH4-02-007-MA-1900 | Material Submittal for Local Control Panel / Monitoring Control Panel | 0 | 100% | 100% | 0
JDH4-02-007-MA-1910 | JDH4-02-007-MA-1910 | Material Approval for Local Control Panel / Monitoring Control Panel | 28182.47 | 100% | 100% | 28182.47
Engine Generators | Engine Generators |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-2060 | JDH4-02-007-MA-2060 | Material Submittal for Engine Generators | 0 | 100% | 100% | 0
JDH4-02-007-MA-2070 | JDH4-02-007-MA-2070 | Material Approval for Engine Generators | 28182.47 | 100% | 100% | 28182.47
Standby Diesel Generator | Standby Diesel Generator |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-2040 | JDH4-02-007-MA-2040 | Material Submittal for Standby Diesel Generator | 0 | 100% | 100% | 0
JDH4-02-007-MA-2050 | JDH4-02-007-MA-2050 | Material Approval for Standby Diesel Generator | 28182.47 | 100% | 100% | 28182.47
Power Factor Correction Capacitor Bank | Power Factor Correction Capacitor Bank |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-2000 | JDH4-02-007-MA-2000 | Material Submittal for Power Factor correction Capacitor Bank | 0 | 100% | 100% | 0
JDH4-02-007-MA-2010 | JDH4-02-007-MA-2010 | Material Approval for Power Factor correction Capacitor Bank | 28182.47 | 100% | 100% | 28182.47
Low-Voltage Electrical Power Conductors and Cables | Low-Voltage Electrical Power Conductors and Cables |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-2020 | JDH4-02-007-MA-2020 | Material Submittal for Low Voltage Electrical Power Conductors & Cables | 0 | 100% | 100% | 0
JDH4-02-007-MA-2030 | JDH4-02-007-MA-2030 | Material Approval for Low Voltage Electrical Power Conductors & Cables | 28182.47 | 100% | 100% | 28182.47
Low Voltage Feeder Cable | Low Voltage Feeder Cable |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1980 | JDH4-02-007-MA-1980 | Material Submittal for Low Voltage Feeder Cable | 0 | 100% | 100% | 0
JDH4-02-007-MA-1990 | JDH4-02-007-MA-1990 | Material Approval for Low Voltage Feeder Cable | 28182.47 | 100% | 100% | 28182.47
Wiring Devices | Wiring Devices |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1940 | JDH4-02-007-MA-1940 | Material Submittal for Wiring Devices | 0 | 100% | 100% | 0
JDH4-02-007-MA-1950 | JDH4-02-007-MA-1950 | Material Approval for Wiring Devices | 28182.47 | 100% | 100% | 28182.47
Enclosed Switches and Circuit Breakers | Enclosed Switches and Circuit Breakers |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-1960 | JDH4-02-007-MA-1960 | Material Submittal for Enclosed Switches and Circuit Breakers | 0 | 100% | 100% | 0
JDH4-02-007-MA-1970 | JDH4-02-007-MA-1970 | Material Approval for Enclosed Switches and Circuit Breakers | 28182.47 | 100% | 100% | 28182.47
Raceways for Electrical Systems | Raceways for Electrical Systems |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-2100 | JDH4-02-007-MA-2100 | Material Submittal for Raceways for Electrical System | 0 | 100% | 100% | 0
JDH4-02-007-MA-2110 | JDH4-02-007-MA-2110 | Material Approval for Raceways for Electrical System | 28182.47 | 100% | 100% | 28182.47
Electrical Manholes | Electrical Manholes |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-2140 | JDH4-02-007-MA-2140 | Material Submittal for Electrical Manholes | 0 | 100% | 100% | 0
JDH4-02-007-MA-2150 | JDH4-02-007-MA-2150 | Material Approval for Electrical Manholes | 28182.47 | 100% | 100% | 28182.47
Security System (CCTV System) | Security System (CCTV System) |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-2080 | JDH4-02-007-MA-2080 | Material Submittal for Security System (CCTV System) | 0 | 100% | 100% | 0
JDH4-02-007-MA-2090 | JDH4-02-007-MA-2090 | Material Approval for Security System (CCTV System) | 28182.47 | 100% | 100% | 28182.47
ICT (Data& telephone System) | ICT (Data& telephone System) |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-2120 | JDH4-02-007-MA-2120 | Material Submittal for ICT (Data & Telephone System) | 0 | 100% | 100% | 0
JDH4-02-007-MA-2130 | JDH4-02-007-MA-2130 | Material Approval for ICT (Data & Telephone System) | 28182.47 | 100% | 100% | 28182.47
Programmable Logic Controllers | Programmable Logic Controllers |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-2200 | JDH4-02-007-MA-2200 | Material Submittal for Programmable Logic Controllers | 0 | 100% | 100% | 0
JDH4-02-007-MA-2210 | JDH4-02-007-MA-2210 | Material Approval for Programmable Logic Controllers | 28182.47 | 100% | 100% | 28182.47
Process Control Wiring | Process Control Wiring |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-2180 | JDH4-02-007-MA-2180 | Material Submittal for Process Control Wiring | 0 | 100% | 100% | 0
JDH4-02-007-MA-2190 | JDH4-02-007-MA-2190 | Material Approval for Process Control Wiring | 28182.47 | 100% | 100% | 28182.47
Instrumentation for Process Systems | Instrumentation for Process Systems |  | 28182.47 |  | 100% | 28182.47
JDH4-02-007-MA-2160 | JDH4-02-007-MA-2160 | Material Submittal for Instrumentation Control Wiring | 0 | 100% | 100% | 0
JDH4-02-007-MA-2170 | JDH4-02-007-MA-2170 | Material Approval for Instrumentation Control Wiring | 28182.47 | 100% | 100% | 28182.47
Procurement | Procurement |  | 11460869.58 |  | 100% | 11460869.58
Short Lead Item | Short Lead Item |  | 5193206.43 |  | 100% | 5193206.43
Road Works - Civil | Road Works - Civil |  | 1611684.79 |  | 100% | 1611684.79
Steel Reinforcement | Steel Reinforcement |  | 179076.06 |  | 100% | 179076.06
JDH4-02-007-PR-1300 | JDH4-02-007-PR-1300 | PO for Steel Reinforcement | 0 | 100% | 100% | 0
JDH4-02-007-PR-1310 | JDH4-02-007-PR-1310 | Material Fabrication for Steel Reinforcement | 0 | 100% | 100% | 0
JDH4-02-007-PR-1319 | JDH4-02-007-PR-1319 | Material Delivery for Steel Reinforcement - Stage 1(Completed) | 35815.22 | 100% | 100% | 35815.22
JDH4-02-007-PR-1319R | JDH4-02-007-PR-1319R | Material Delivery for Steel Reinforcement - Stage 1 | 53722.79 | 100% | 100% | 53722.79
JDH4-02-007-PR-1320 | JDH4-02-007-PR-1320 | Material Delivery for Steel Reinforcement - Stage 2 | 89538.05 | 100% | 100% | 89538.05
Ready Mixed Concrete | Ready Mixed Concrete |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1330 | JDH4-02-007-PR-1330 | PO for Ready Mixed Concrete | 0 | 100% | 100% | 0
JDH4-02-007-PR-1340 | JDH4-02-007-PR-1340 | Material Delivery for Ready Mixed Concrete | 179076.09 | 100% | 100% | 179076.09
Water Proofing | Water Proofing |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1350 | JDH4-02-007-PR-1350 | PO for Water Proofing | 0 | 100% | 100% | 0
JDH4-02-007-PR-1360 | JDH4-02-007-PR-1360 | Material Fabrication for Water Proofing | 0 | 100% | 100% | 0
JDH4-02-007-PR-1370 | JDH4-02-007-PR-1370 | Material Delivery for Water Proofing | 179076.09 | 100% | 100% | 179076.09
Aggregate Base Course | Aggregate Base Course |  | 179076.1 |  | 100% | 179076.1
JDH4-02-007-PR-1380 | JDH4-02-007-PR-1380 | PO for Aggregate Base Course | 0 | 100% | 100% | 0
JDH4-02-007-PR-1389 | JDH4-02-007-PR-1389 | Material Delivery for Aggregate Base Course - Stage 1 | 89538.05 | 100% | 100% | 89538.05
JDH4-02-007-PR-1390 | JDH4-02-007-PR-1390 | Material Delivery for Aggregate Base Course - Stage 2 | 89538.05 | 100% | 100% | 89538.05
Bituminous Base & Wearing Course | Bituminous Base & Wearing Course |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1400 | JDH4-02-007-PR-1400 | PO for Bituminous Base & Wearing Cource | 0 | 100% | 100% | 0
JDH4-02-007-PR-1410 | JDH4-02-007-PR-1410 | Material Delivery to the Site | 179076.09 | 100% | 100% | 179076.09
Precast Concrete Kerb | Precast Concrete Kerb |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1420 | JDH4-02-007-PR-1420 | PO for Precast Concrete Kerb | 0 | 100% | 100% | 0
JDH4-02-007-PR-1430 | JDH4-02-007-PR-1430 | Material Fabrication for Precast Concrete Kerb | 0 | 100% | 100% | 0
JDH4-02-007-PR-1440 | JDH4-02-007-PR-1440 | Material Delivery for Precast Concrete Kerb | 179076.09 | 100% | 100% | 179076.09
Interlocking Block Pavers | Interlocking Block Pavers |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1450 | JDH4-02-007-PR-1450 | PO for Interlocking Block Pavers | 0 | 100% | 100% | 0
JDH4-02-007-PR-1460 | JDH4-02-007-PR-1460 | Material Fabrication for Interlocking Block Pavers | 0 | 100% | 100% | 0
JDH4-02-007-PR-1470 | JDH4-02-007-PR-1470 | Material Delivery for Interlocking Block Pavers | 179076.09 | 100% | 100% | 179076.09
Pavement Markings | Pavement Markings |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1480 | JDH4-02-007-PR-1480 | PO for Pavement Markings | 0 | 100% | 100% | 0
JDH4-02-007-PR-1500 | JDH4-02-007-PR-1500 | Material Delivery for Pavement Markings | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-1490 | JDH4-02-007-PR-1490 | Material Fabrication for Pavement Markings | 0 | 100% | 100% | 0
Traffic Signs | Traffic Signs |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1510 | JDH4-02-007-PR-1510 | PO for Traffic Signs | 0 | 100% | 100% | 0
JDH4-02-007-PR-1520 | JDH4-02-007-PR-1520 | Material Fabrication for Traffic Signs | 0 | 100% | 100% | 0
JDH4-02-007-PR-1530 | JDH4-02-007-PR-1530 | Material Delivery for Traffic Signs | 179076.09 | 100% | 100% | 179076.09
Stormwater Utilities | Stormwater Utilities |  | 716304.35 |  | 100% | 716304.35
Catch Basins | Catch Basins |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1720 | JDH4-02-007-PR-1720 | PO for Catch Basins | 0 | 100% | 100% | 0
JDH4-02-007-PR-1729 | JDH4-02-007-PR-1729 | Material Fabrication for Catch Basins - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1740 | JDH4-02-007-PR-1740 | Material Delivery for Catch Basins(Completed) | 53722.83 | 100% | 100% | 53722.83
JDH4-02-007-PR-1740R | JDH4-02-007-PR-1740R | Material Delivery for Catch Basins | 125353.26 | 100% | 100% | 125353.26
JDH4-02-007-PR-1729R | JDH4-02-007-PR-1729R | Material Fabrication for Catch Basins - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1730 | JDH4-02-007-PR-1730 | Material Fabrication for Catch Basins - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1830 | JDH4-02-007-PR-1830 | Staging Time for Catch Basins | 0 | 100% | 100% | 0
GRP Pipes | GRP Pipes |  | 358152.18 |  | 100% | 358152.18
JDH4-02-007-PR-1660 | JDH4-02-007-PR-1660 | PO for GRP Pipes | 0 | 100% | 100% | 0
JDH4-02-007-PR-1670 | JDH4-02-007-PR-1670 | Material Fabrication for GRP Pipes | 0 | 100% | 100% | 0
JDH4-02-007-PR-1680 | JDH4-02-007-PR-1680 | Material Delivery for GRP Pipes(Completed) | 196983.7 | 100% | 100% | 196983.7
JDH4-02-007-PR-1670R | JDH4-02-007-PR-1670R | Material Fabrication for GRP Pipes | 0 | 100% | 100% | 0
JDH4-02-007-PR-1680R | JDH4-02-007-PR-1680R | Material Delivery for GRP Pipes | 161168.48 | 100% | 100% | 161168.48
Inlet Manholes | Inlet Manholes |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1690 | JDH4-02-007-PR-1690 | PO for Inlet Manholes | 0 | 100% | 100% | 0
JDH4-02-007-PR-1700 | JDH4-02-007-PR-1700 | Material Fabrication for Inlet Manholes | 0 | 100% | 100% | 0
JDH4-02-007-PR-1710 | JDH4-02-007-PR-1710 | Material Delivery for Inlet Manholes(Completed) | 71630.44 | 100% | 100% | 71630.44
JDH4-02-007-PR-1700R | JDH4-02-007-PR-1700R | Material Fabrication for Inlet Manholes | 0 | 100% | 100% | 0
JDH4-02-007-PR-1710R | JDH4-02-007-PR-1710R | Material Delivery for Inlet Manholes | 107445.65 | 100% | 100% | 107445.65
Sanitary Sewerage | Sanitary Sewerage |  | 716304.35 |  | 100% | 716304.35
GRP Pipes | GRP Pipes |  | 358152.18 |  | 100% | 358152.18
JDH4-02-007-PR-1600 | JDH4-02-007-PR-1600 | PO for GRP Pipes | 0 | 100% | 100% | 0
JDH4-02-007-PR-1610 | JDH4-02-007-PR-1610 | Material Fabrication for GRP Pipes | 0 | 100% | 100% | 0
JDH4-02-007-PR-1620 | JDH4-02-007-PR-1620 | Material Delivery for GRP Pipes(Completed) | 17907.61 | 100% | 100% | 17907.61
JDH4-02-007-PR-1610R | JDH4-02-007-PR-1610R | Material Fabrication for GRP Pipes | 0 | 100% | 100% | 0
JDH4-02-007-PR-1620R | JDH4-02-007-PR-1620R | Material Delivery for GRP Pipes | 340244.57 | 100% | 100% | 340244.57
Manholes | Manholes |  | 358152.17 |  | 100% | 358152.17
JDH4-02-007-PR-1630 | JDH4-02-007-PR-1630 | PO for Manholes | 0 | 100% | 100% | 0
JDH4-02-007-PR-1638 | JDH4-02-007-PR-1638 | Material Fabrication for Manholes - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1650 | JDH4-02-007-PR-1650 | Material Delivery for Manholes(Completed) | 161168.48 | 100% | 100% | 161168.48
JDH4-02-007-PR-1650R | JDH4-02-007-PR-1650R | Material Delivery for Manholes | 196983.69 | 100% | 100% | 196983.69
JDH4-02-007-PR-1639 | JDH4-02-007-PR-1639 | Material Fabrication for Manholes - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1640 | JDH4-02-007-PR-1640 | Material Fabrication for Manholes - Stage 3 | 0 | 100% | 100% | 0
TSE Network | TSE Network |  | 179076.09 |  | 100% | 179076.09
HDPE Pipe (PN 16) | HDPE Pipe (PN 16) |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1570 | JDH4-02-007-PR-1570 | PO for HDPE Pipe (PN 16) | 0 | 100% | 100% | 0
JDH4-02-007-PR-1580 | JDH4-02-007-PR-1580 | Material Fabrication for HDPE Pipe (PN 16) | 0 | 100% | 100% | 0
JDH4-02-007-PR-1590 | JDH4-02-007-PR-1590 | Material Delivery for HDPE Pipe (PN 16)(Completed) | 164750 | 100% | 100% | 164750
JDH4-02-007-PR-1580R | JDH4-02-007-PR-1580R | Material Fabrication for HDPE Pipe (PN 16) | 0 | 100% | 100% | 0
JDH4-02-007-PR-1590R | JDH4-02-007-PR-1590R | Material Delivery for HDPE Pipe (PN 16) | 14326.09 | 100% | 100% | 14326.09
Potable Water Network | Potable Water Network |  | 179076.09 |  | 100% | 179076.09
HDPE Pipe (PN 16) | HDPE Pipe (PN 16) |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1540 | JDH4-02-007-PR-1540 | PO for HDPE Pipe (PN 16) | 0 | 100% | 100% | 0
JDH4-02-007-PR-1550 | JDH4-02-007-PR-1550 | Material Fabrication for HDPE Pipe (PN 16) | 0 | 100% | 100% | 0
JDH4-02-007-PR-1560 | JDH4-02-007-PR-1560 | Material Delivery for HDPE Pipe (PN 16)(Completed) | 148633.15 | 100% | 100% | 148633.15
JDH4-02-007-PR-1550R | JDH4-02-007-PR-1550R | Material Fabrication for HDPE Pipe (PN 16) | 0 | 100% | 100% | 0
JDH4-02-007-PR-1560R | JDH4-02-007-PR-1560R | Material Delivery for HDPE Pipe (PN 16) | 30442.94 | 100% | 100% | 30442.94
Electrical Network | Electrical Network |  | 358152.04 |  | 100% | 358152.04
Pipe for the Duct | Pipe for the Duct |  | 179075.95 |  | 100% | 179075.95
JDH4-02-007-PR-1190 | JDH4-02-007-PR-1190 | PO for Pipe for Duct | 0 | 100% | 100% | 0
JDH4-02-007-PR-1210 | JDH4-02-007-PR-1210 | Material Fabrication for Pipe for Duct | 0 | 100% | 100% | 0
JDH4-02-007-PR-1230 | JDH4-02-007-PR-1230 | Material Delivery for Pipe for Duct | 179075.95 | 100% | 100% | 179075.95
Earthing System | Earthing System |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1180 | JDH4-02-007-PR-1180 | PO for Earthing System | 0 | 100% | 100% | 0
JDH4-02-007-PR-1200 | JDH4-02-007-PR-1200 | Material Fabrication for Earthing System | 0 | 100% | 100% | 0
JDH4-02-007-PR-1220 | JDH4-02-007-PR-1220 | Material Delivery for Earthing System | 179076.09 | 100% | 100% | 179076.09
Telecommunications | Telecommunications |  | 179076.09 |  | 100% | 179076.09
Pipe for the Duct | Pipe for the Duct |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2260 | JDH4-02-007-PR-2260 | PO for Pipe for Duct | 0 | 100% | 100% | 0
JDH4-02-007-PR-2270 | JDH4-02-007-PR-2270 | Material Fabrication for Pipe for Duct | 0 | 100% | 100% | 0
JDH4-02-007-PR-2280 | JDH4-02-007-PR-2280 | Material Delivery for Pipe for Duct(Completed) | 71630.44 | 100% | 100% | 71630.44
JDH4-02-007-PR-2270R | JDH4-02-007-PR-2270R | Material Fabrication for Pipe for Duct | 0 | 100% | 100% | 0
JDH4-02-007-PR-2280R | JDH4-02-007-PR-2280R | Material Delivery for Pipe for Duct | 107445.65 | 100% | 100% | 107445.65
Sewage Lift Station | Sewage Lift Station |  | 1253532.63 |  | 100% | 1253532.63
Thermal & Moisture Protection | Thermal & Moisture Protection |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2350 | JDH4-02-007-PR-2350 | PO for Thermal & Moisture Protection | 0 | 100% | 100% | 0
JDH4-02-007-PR-2358 | JDH4-02-007-PR-2358 | Material Fabrication for Thermal & Moisture Protection - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2359 | JDH4-02-007-PR-2359 | Material Fabrication for Thermal & Moisture Protection - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2360 | JDH4-02-007-PR-2360 | Material Fabrication for Thermal & Moisture Protection - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2369 | JDH4-02-007-PR-2369 | Material Delivery for Thermal & Moisture Protection - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2370 | JDH4-02-007-PR-2370 | Material Delivery for Thermal & Moisture Protection - Stage 2 | 179076.09 | 100% | 100% | 179076.09
Metals | Metals |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1840 | JDH4-02-007-PR-1840 | PO for Metal | 0 | 100% | 100% | 0
JDH4-02-007-PR-1848 | JDH4-02-007-PR-1848 | Material Fabrication for Metal - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1849 | JDH4-02-007-PR-1849 | Material Fabrication for Metal - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1850 | JDH4-02-007-PR-1850 | Material Fabrication for Metal - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1860 | JDH4-02-007-PR-1860 | Material Delivery for Metal - Stage 2 | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-1859 | JDH4-02-007-PR-1859 | Material Delivery for Metal - Stage 1 | 0 | 100% | 100% | 0
Pipes | Pipes |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2290 | JDH4-02-007-PR-2290 | PO for Pipes | 0 | 100% | 100% | 0
JDH4-02-007-PR-2300 | JDH4-02-007-PR-2300 | Material Fabrication for Pipes | 0 | 100% | 100% | 0
JDH4-02-007-PR-2310 | JDH4-02-007-PR-2310 | Material Delivery for Pipes | 179076.09 | 100% | 100% | 179076.09
Air Conditioning and Ventilation | Air Conditioning and Ventilation |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2380 | JDH4-02-007-PR-2380 | PO for Air Conditioning and Ventilation | 0 | 100% | 100% | 0
JDH4-02-007-PR-2390 | JDH4-02-007-PR-2390 | Material Fabrication for Air Conditioning and Ventilation | 0 | 100% | 100% | 0
JDH4-02-007-PR-2400 | JDH4-02-007-PR-2400 | Material Delivery for Air Conditioning and Ventilation | 179076.09 | 100% | 100% | 179076.09
Fuel System | Fuel System |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1870 | JDH4-02-007-PR-1870 | PO forFabrication for Fuel System | 0 | 100% | 100% | 0
JDH4-02-007-PR-1880 | JDH4-02-007-PR-1880 | Material Fabrication for Fuel System | 0 | 100% | 100% | 0
JDH4-02-007-PR-1890 | JDH4-02-007-PR-1890 | Material Delivery for Fuel System | 179076.09 | 100% | 100% | 179076.09
Fire Fighting System | Fire Fighting System |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2320 | JDH4-02-007-PR-2320 | PO for Fire Fighting System | 0 | 100% | 100% | 0
JDH4-02-007-PR-2330 | JDH4-02-007-PR-2330 | Material Fabrication for Fire Fighting System | 0 | 100% | 100% | 0
JDH4-02-007-PR-2340 | JDH4-02-007-PR-2340 | Material Delivery for Fire Fighting System | 179076.09 | 100% | 100% | 179076.09
Security System (CCTV System) | Security System (CCTV System) |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2410 | JDH4-02-007-PR-2410 | PO for Security System (CCTV System) | 0 | 100% | 100% | 0
JDH4-02-007-PR-2420 | JDH4-02-007-PR-2420 | Material Fabrication for Security System (CCTV System) | 0 | 100% | 100% | 0
JDH4-02-007-PR-2430 | JDH4-02-007-PR-2430 | Material Delivery for Security System (CCTV System) | 179076.09 | 100% | 100% | 179076.09
Long Lead Item | Long Lead Item |  | 6267663.15 |  | 100% | 6267663.15
TSE Network | TSE Network |  | 358152.18 |  | 100% | 358152.18
Valves / Chambers | Valves / Chambers |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1270 | JDH4-02-007-PR-1270 | PO for Valves / Chambers | 0 | 100% | 100% | 0
JDH4-02-007-PR-1277 | JDH4-02-007-PR-1277 | Material Fabrication for Valves / Chambers - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1278 | JDH4-02-007-PR-1278 | Material Fabrication for Valves / Chambers - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1279 | JDH4-02-007-PR-1279 | Material Fabrication for Valves / Chambers - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1280 | JDH4-02-007-PR-1280 | Material Fabrication for Valves / Chambers - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1290 | JDH4-02-007-PR-1290 | Material Delivery for Valves / Chambers | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-1820 | JDH4-02-007-PR-1820 | Staging Time for Valves / Chambers | 0 | 100% | 100% | 0
Risers | Risers |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1900 | JDH4-02-007-PR-1900 | PO for Risers | 0 | 100% | 100% | 0
JDH4-02-007-PR-1907 | JDH4-02-007-PR-1907 | Material Fabrication for Risers - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1908 | JDH4-02-007-PR-1908 | Material Fabrication for Risers - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1909 | JDH4-02-007-PR-1909 | Material Fabrication for Risers - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1910 | JDH4-02-007-PR-1910 | Material Fabrication for Risers - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1920 | JDH4-02-007-PR-1920 | Material Delivery for Risers | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-1930 | JDH4-02-007-PR-1930 | Staging Time for Risers | 0 | 100% | 100% | 0
Potable Water Network | Potable Water Network |  | 358152.18 |  | 100% | 358152.18
Valves / Chambers | Valves / Chambers |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1240 | JDH4-02-007-PR-1240 | PO for Valves / Chambers | 0 | 100% | 100% | 0
JDH4-02-007-PR-1249 | JDH4-02-007-PR-1249 | Material Fabrication for Valves / Chambers - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1248 | JDH4-02-007-PR-1248 | Material Fabrication for Valves / Chambers - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1250 | JDH4-02-007-PR-1250 | Material Fabrication for Valves / Chambers - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1260 | JDH4-02-007-PR-1260 | Material Delivery for Valves / Chambers | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-1810 | JDH4-02-007-PR-1810 | Staging Time for Valves / Chambers | 0 | 100% | 100% | 0
Fire Hydrants | Fire Hydrants |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2440 | JDH4-02-007-PR-2440 | PO for Fire Hydrant | 0 | 100% | 100% | 0
JDH4-02-007-PR-2447 | JDH4-02-007-PR-2447 | Material Fabrication for Fire Hydrant - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2448 | JDH4-02-007-PR-2448 | Material Fabrication for Fire Hydrant - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2449 | JDH4-02-007-PR-2449 | Material Fabrication for Fire Hydrant - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2450 | JDH4-02-007-PR-2450 | Material Fabrication for Fire Hydrant - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2460 | JDH4-02-007-PR-2460 | Material Delivery for Fire Hydrant | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2470 | JDH4-02-007-PR-2470 | Staging Time for Fire Hydrant | 0 | 100% | 100% | 0
Electrical Network | Electrical Network |  | 1432608.72 |  | 100% | 1432608.72
Medium Voltage Cable | Medium Voltage Cable |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1000 | JDH4-02-007-PR-1000 | PO for Medium Voltage Cable | 0 | 100% | 100% | 0
JDH4-02-007-PR-1060 | JDH4-02-007-PR-1060 | Material Fabrication for Medium Voltage Cable - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1059 | JDH4-02-007-PR-1059 | Material Fabrication for Medium Voltage Cable - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1120 | JDH4-02-007-PR-1120 | Material Delivery for Medium Voltage Cable | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-1750 | JDH4-02-007-PR-1750 | Staging Time for Medium Voltage Cable | 0 | 100% | 100% | 0
Unit Sub Station | Unit Sub Station |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1010 | JDH4-02-007-PR-1010 | PO for Unit Sub-station | 0 | 100% | 100% | 0
JDH4-02-007-PR-1067 | JDH4-02-007-PR-1067 | Material Fabrication for Unit Sub-station - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1068 | JDH4-02-007-PR-1068 | Material Fabrication for Unit Sub-station - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1069 | JDH4-02-007-PR-1069 | Material Fabrication for Unit Sub-station - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1070 | JDH4-02-007-PR-1070 | Material Fabrication for Unit Sub-station - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1130 | JDH4-02-007-PR-1130 | Material Delivery for Unit Sub-station | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-1760 | JDH4-02-007-PR-1760 | Staging Time for Unit Sub-station | 0 | 100% | 100% | 0
Low Voltage Cables | Low Voltage Cables |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1020 | JDH4-02-007-PR-1020 | PO for Low Voltage Cables | 0 | 100% | 100% | 0
JDH4-02-007-PR-1078 | JDH4-02-007-PR-1078 | Material Fabrication for Low Voltage Cables - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1079 | JDH4-02-007-PR-1079 | Material Fabrication for Low Voltage Cables - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1080 | JDH4-02-007-PR-1080 | Material Fabrication for Low Voltage Cables - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1140 | JDH4-02-007-PR-1140 | Material Delivery for Low Voltage Cables | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-1770 | JDH4-02-007-PR-1770 | Staging Time for Low Voltage Cables | 0 | 100% | 100% | 0
Ring Main Unit | Ring Main Unit |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1940 | JDH4-02-007-PR-1940 | PO for Ring Main Unit | 0 | 100% | 100% | 0
JDH4-02-007-PR-1948 | JDH4-02-007-PR-1948 | Material Fabrication for Ring Main Unit - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1949 | JDH4-02-007-PR-1949 | Material Fabrication for Ring Main Unit - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1950 | JDH4-02-007-PR-1950 | Material Fabrication for Ring Main Unit - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1960 | JDH4-02-007-PR-1960 | Material Delivery for Ring Main Unit | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-1970 | JDH4-02-007-PR-1970 | Staging Time for Ring Main Unit | 0 | 100% | 100% | 0
Lighting poles | Lighting poles |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1030 | JDH4-02-007-PR-1030 | PO for Lighting poles | 0 | 100% | 100% | 0
JDH4-02-007-PR-1088 | JDH4-02-007-PR-1088 | Material Fabrication for Lighting poles - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1090 | JDH4-02-007-PR-1090 | Material Fabrication for Lighting poles - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1089 | JDH4-02-007-PR-1089 | Material Fabrication for Lighting poles - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1150 | JDH4-02-007-PR-1150 | Material Delivery for Lighting poles | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-1780 | JDH4-02-007-PR-1780 | Staging Time for Lighting poles | 0 | 100% | 100% | 0
Street Lighting Luminaire | Street Lighting Luminaire |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1040 | JDH4-02-007-PR-1040 | PO for Street Lighting Luminaire | 0 | 100% | 100% | 0
JDH4-02-007-PR-1098 | JDH4-02-007-PR-1098 | Material Fabrication for Street Lighting Luminaire - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1099 | JDH4-02-007-PR-1099 | Material Fabrication for Street Lighting Luminaire - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1100 | JDH4-02-007-PR-1100 | Material Fabrication for Street Lighting Luminaire - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1160 | JDH4-02-007-PR-1160 | Material Delivery for Street Lighting Luminaire | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-1790 | JDH4-02-007-PR-1790 | Staging Time for Street Lighting Luminaire | 0 | 100% | 100% | 0
Lighting panels/Feeder Pillers | Lighting panels/Feeder Pillers |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1050 | JDH4-02-007-PR-1050 | PO for Lighting Panels/Feeder Pillers | 0 | 100% | 100% | 0
JDH4-02-007-PR-1108 | JDH4-02-007-PR-1108 | Material Fabrication for Lighting Panels/Feeder Pillers - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1110 | JDH4-02-007-PR-1110 | Material Fabrication for Lighting Panels/Feeder Pillers - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1170 | JDH4-02-007-PR-1170 | Material Delivery for Lighting Panels/Feeder Pillers | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-1109 | JDH4-02-007-PR-1109 | Material Fabrication for Lighting Panels/Feeder Pillers - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-1800 | JDH4-02-007-PR-1800 | Staging Time for Lighting Panels/Feeder Pillers | 0 | 100% | 100% | 0
Low Voltage Distribution Panels | Low Voltage Distribution Panels |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2480 | JDH4-02-007-PR-2480 | PO for Low Voltage Distribution Panels | 0 | 100% | 100% | 0
JDH4-02-007-PR-2488 | JDH4-02-007-PR-2488 | Material Fabrication for Low Voltage Distribution Panels - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2489 | JDH4-02-007-PR-2489 | Material Fabrication for Low Voltage Distribution Panels - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2490 | JDH4-02-007-PR-2490 | Material Fabrication for Low Voltage Distribution Panels - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2500 | JDH4-02-007-PR-2500 | Material Delivery for Low Voltage Distribution Panels | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2510 | JDH4-02-007-PR-2510 | Staging Time for Low Voltage Distribution Panels | 0 | 100% | 100% | 0
Sewage Lift Station | Sewage Lift Station |  | 4118750.07 |  | 100% | 4118750.07
Odours scrubbing system | Odours scrubbing system |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1990 | JDH4-02-007-PR-1990 | PO for Odours scrubbing system | 0 | 100% | 100% | 0
JDH4-02-007-PR-2037 | JDH4-02-007-PR-2037 | Material Fabrication for Odours scrubbing system - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2038 | JDH4-02-007-PR-2038 | Material Fabrication for Odours scrubbing system - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2039 | JDH4-02-007-PR-2039 | Material Fabrication for Odours scrubbing system - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2040 | JDH4-02-007-PR-2040 | Material Fabrication for Odours scrubbing system - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2090 | JDH4-02-007-PR-2090 | Material Delivery for Odours scrubbing system | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2140 | JDH4-02-007-PR-2140 | Staging Time for Odours scrubbing system | 0 | 100% | 100% | 0
Crane | Crane |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2180 | JDH4-02-007-PR-2180 | PO for Crane | 0 | 100% | 100% | 0
JDH4-02-007-PR-2187 | JDH4-02-007-PR-2187 | Material Fabrication for Crane - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2188 | JDH4-02-007-PR-2188 | Material Fabrication for Crane - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2189 | JDH4-02-007-PR-2189 | Material Fabrication for Crane - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2190 | JDH4-02-007-PR-2190 | Material Fabrication for Crane - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2200 | JDH4-02-007-PR-2200 | Material Delivery for Crane | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2210 | JDH4-02-007-PR-2210 | Staging Time for Crane | 0 | 100% | 100% | 0
Air Vents | Air Vents |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2000 | JDH4-02-007-PR-2000 | PO for Air Vents | 0 | 100% | 100% | 0
JDH4-02-007-PR-2045 | JDH4-02-007-PR-2045 | Material Fabrication for Air Vents - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2046 | JDH4-02-007-PR-2046 | Material Fabrication for Air Vents - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2047 | JDH4-02-007-PR-2047 | Material Fabrication for Air Vents - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2048 | JDH4-02-007-PR-2048 | Material Fabrication for Air Vents - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2049 | JDH4-02-007-PR-2049 | Material Fabrication for Air Vents - Stage 5 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2050 | JDH4-02-007-PR-2050 | Material Fabrication for Air Vents - Stage 6 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2100 | JDH4-02-007-PR-2100 | Material Delivery for Air Vents | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2150 | JDH4-02-007-PR-2150 | Staging Time for Air Vents | 0 | 100% | 100% | 0
Screening Container | Screening Container |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2220 | JDH4-02-007-PR-2220 | PO for Screening Container | 0 | 100% | 100% | 0
JDH4-02-007-PR-2225 | JDH4-02-007-PR-2225 | Material Fabrication for Screening Container - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2226 | JDH4-02-007-PR-2226 | Material Fabrication for Screening Container - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2227 | JDH4-02-007-PR-2227 | Material Fabrication for Screening Container - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2230 | JDH4-02-007-PR-2230 | Material Fabrication for Screening Container - Stage 6 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2229 | JDH4-02-007-PR-2229 | Material Fabrication for Screening Container - Stage 5 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2228 | JDH4-02-007-PR-2228 | Material Fabrication for Screening Container - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2240 | JDH4-02-007-PR-2240 | Material Delivery for Screening Container | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2250 | JDH4-02-007-PR-2250 | Staging Time for Screening Container | 0 | 100% | 100% | 0
Baffle Plates | Baffle Plates |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2010 | JDH4-02-007-PR-2010 | PO for Baffle Plates | 0 | 100% | 100% | 0
JDH4-02-007-PR-2057 | JDH4-02-007-PR-2057 | Material Fabrication for Baffle Plates - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2058 | JDH4-02-007-PR-2058 | Material Fabrication for Baffle Plates - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2059 | JDH4-02-007-PR-2059 | Material Fabrication for Baffle Plates - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2060 | JDH4-02-007-PR-2060 | Material Fabrication for Baffle Plates - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2110 | JDH4-02-007-PR-2110 | Material Delivery for Baffle Plates | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2160 | JDH4-02-007-PR-2160 | Staging Time for Baffle Plates | 0 | 100% | 100% | 0
Anti-Water Hammer Equipment | Anti-Water Hammer Equipment |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2020 | JDH4-02-007-PR-2020 | PO for Anti-Water Hammer Equipment | 0 | 100% | 100% | 0
JDH4-02-007-PR-2120 | JDH4-02-007-PR-2120 | Material Delivery for Anti-Water Hammer Equipment | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2067 | JDH4-02-007-PR-2067 | Material Fabrication for Anti-Water Hammer Equipment - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2066 | JDH4-02-007-PR-2066 | Material Fabrication for Anti-Water Hammer Equipment - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2065 | JDH4-02-007-PR-2065 | Material Fabrication for Anti-Water Hammer Equipment - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2070 | JDH4-02-007-PR-2070 | Material Fabrication for Anti-Water Hammer Equipment - Stage 6 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2069 | JDH4-02-007-PR-2069 | Material Fabrication for Anti-Water Hammer Equipment - Stage 5 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2068 | JDH4-02-007-PR-2068 | Material Fabrication for Anti-Water Hammer Equipment - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2170 | JDH4-02-007-PR-2170 | Staging Time for Anti-Water Hammer Equipment | 0 | 100% | 100% | 0
Pumps | Pumps |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-1980 | JDH4-02-007-PR-1980 | PO for Pumps | 0 | 100% | 100% | 0
JDH4-02-007-PR-2026 | JDH4-02-007-PR-2026 | Material Fabrication for Pumps - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2027 | JDH4-02-007-PR-2027 | Material Fabrication for Pumps - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2028 | JDH4-02-007-PR-2028 | Material Fabrication for Pumps - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2029 | JDH4-02-007-PR-2029 | Material Fabrication for Pumps - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2030 | JDH4-02-007-PR-2030 | Material Fabrication for Pumps - Stage 5 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2080 | JDH4-02-007-PR-2080 | Material Delivery for Pumps | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2130 | JDH4-02-007-PR-2130 | Staging Time for Pumps | 0 | 100% | 100% | 0
Main Distribution Board /MCC panels | Main Distribution Board /MCC panels |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2530 | JDH4-02-007-PR-2530 | PO for Main Distribution Board / MCC panels | 0 | 100% | 100% | 0
JDH4-02-007-PR-2567 | JDH4-02-007-PR-2567 | Material Fabrication for Main Distribution Board / MCC panels - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2568 | JDH4-02-007-PR-2568 | Material Fabrication for Main Distribution Board / MCC panels - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2570 | JDH4-02-007-PR-2570 | Material Fabrication for Main Distribution Board / MCC panels - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2569 | JDH4-02-007-PR-2569 | Material Fabrication for Main Distribution Board / MCC panels - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2610 | JDH4-02-007-PR-2610 | Material Delivery for Main Distribution Board / MCC panels | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2650 | JDH4-02-007-PR-2650 | Staging Time for Main Distribution Board / MCC panels | 0 | 100% | 100% | 0
Final Panel boards | Final Panel boards |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2680 | JDH4-02-007-PR-2680 | PO for Final Panel Boards | 0 | 100% | 100% | 0
JDH4-02-007-PR-2687 | JDH4-02-007-PR-2687 | Material Fabrication for Final Panel Boards - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2688 | JDH4-02-007-PR-2688 | Material Fabrication for Final Panel Boards - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2690 | JDH4-02-007-PR-2690 | Material Fabrication for Final Panel Boards - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2689 | JDH4-02-007-PR-2689 | Material Fabrication for Final Panel Boards - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2700 | JDH4-02-007-PR-2700 | Material Delivery for Final Panel Boards | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2710 | JDH4-02-007-PR-2710 | Staging Time for Final Panel Boards | 0 | 100% | 100% | 0
Local Control Panel/ Monitoring Control Panel | Local Control Panel/ Monitoring Control Panel |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2540 | JDH4-02-007-PR-2540 | PO for Local Control Panel/ Monitoring Control Panel | 0 | 100% | 100% | 0
JDH4-02-007-PR-2576 | JDH4-02-007-PR-2576 | Material Fabrication for Local Control Panel/ Monitoring Control Panel - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2577 | JDH4-02-007-PR-2577 | Material Fabrication for Local Control Panel/ Monitoring Control Panel - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2578 | JDH4-02-007-PR-2578 | Material Fabrication for Local Control Panel/ Monitoring Control Panel - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2580 | JDH4-02-007-PR-2580 | Material Fabrication for Local Control Panel/ Monitoring Control Panel - Stage 5 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2579 | JDH4-02-007-PR-2579 | Material Fabrication for Local Control Panel/ Monitoring Control Panel - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2620 | JDH4-02-007-PR-2620 | Material Delivery for Local Control Panel/ Monitoring Control Panel | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2660 | JDH4-02-007-PR-2660 | Staging Time for Local Control Panel/ Monitoring Control Panel | 0 | 100% | 100% | 0
Engine Generators | Engine Generators |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2720 | JDH4-02-007-PR-2720 | PO for Engine Generators | 0 | 100% | 100% | 0
JDH4-02-007-PR-2726 | JDH4-02-007-PR-2726 | Material Fabrication for Engine Generators - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2727 | JDH4-02-007-PR-2727 | Material Fabrication for Engine Generators - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2728 | JDH4-02-007-PR-2728 | Material Fabrication for Engine Generators - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2729 | JDH4-02-007-PR-2729 | Material Fabrication for Engine Generators - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2730 | JDH4-02-007-PR-2730 | Material Fabrication for Engine Generators - Stage 5 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2740 | JDH4-02-007-PR-2740 | Material Delivery for Engine Generators | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2750 | JDH4-02-007-PR-2750 | Staging Time for Engine Generators | 0 | 100% | 100% | 0
Standby Diesel Generator | Standby Diesel Generator |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2550 | JDH4-02-007-PR-2550 | PO for Standby Diesel Generator | 0 | 100% | 100% | 0
JDH4-02-007-PR-2587 | JDH4-02-007-PR-2587 | Material Fabrication for Standby Diesel Generator - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2588 | JDH4-02-007-PR-2588 | Material Fabrication for Standby Diesel Generator - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2589 | JDH4-02-007-PR-2589 | Material Fabrication for Standby Diesel Generator - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2590 | JDH4-02-007-PR-2590 | Material Fabrication for Standby Diesel Generator - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2630 | JDH4-02-007-PR-2630 | Material Delivery for Standby Diesel Generator | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2670 | JDH4-02-007-PR-2670 | Staging Time for Standby Diesel Generator | 0 | 100% | 100% | 0
Power Factor Correction Capacitor Bank | Power Factor Correction Capacitor Bank |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2760 | JDH4-02-007-PR-2760 | PO for Power Factor Correction Capacitor Bank | 0 | 100% | 100% | 0
JDH4-02-007-PR-2795 | JDH4-02-007-PR-2795 | Material Fabrication for Power Factor Correction Capacitor Bank - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2796 | JDH4-02-007-PR-2796 | Material Fabrication for Power Factor Correction Capacitor Bank - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2797 | JDH4-02-007-PR-2797 | Material Fabrication for Power Factor Correction Capacitor Bank - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2798 | JDH4-02-007-PR-2798 | Material Fabrication for Power Factor Correction Capacitor Bank - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2800 | JDH4-02-007-PR-2800 | Material Fabrication for Power Factor Correction Capacitor Bank - Stage 6 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2799 | JDH4-02-007-PR-2799 | Material Fabrication for Power Factor Correction Capacitor Bank - Stage 5 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2840 | JDH4-02-007-PR-2840 | Material Delivery for Power Factor Correction Capacitor Bank | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2880 | JDH4-02-007-PR-2880 | Staging Time for Power Factor Correction Capacitor Bank | 0 | 100% | 100% | 0
Low-Voltage Electrical Power Conductors and Cables | Low-Voltage Electrical Power Conductors and Cables |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2770 | JDH4-02-007-PR-2770 | PO for Low-Voltage Electrical Power Conductors and Cables | 0 | 100% | 100% | 0
JDH4-02-007-PR-2807 | JDH4-02-007-PR-2807 | Material Fabrication for Low-Voltage Electrical Power Conductors and Cables - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2808 | JDH4-02-007-PR-2808 | Material Fabrication for Low-Voltage Electrical Power Conductors and Cables - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2809 | JDH4-02-007-PR-2809 | Material Fabrication for Low-Voltage Electrical Power Conductors and Cables - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2810 | JDH4-02-007-PR-2810 | Material Fabrication for Low-Voltage Electrical Power Conductors and Cables - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2850 | JDH4-02-007-PR-2850 | Material Delivery for Low-Voltage Electrical Power Conductors and Cables | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2890 | JDH4-02-007-PR-2890 | Staging Time for Low-Voltage Electrical Power Conductors and Cables | 0 | 100% | 100% | 0
Low Voltage Feeder Cable | Low Voltage Feeder Cable |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2920 | JDH4-02-007-PR-2920 | PO for Low Voltage Feeder Cable | 0 | 100% | 100% | 0
JDH4-02-007-PR-2927 | JDH4-02-007-PR-2927 | Material Fabrication for Low Voltage Feeder Cable - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2928 | JDH4-02-007-PR-2928 | Material Fabrication for Low Voltage Feeder Cable - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2929 | JDH4-02-007-PR-2929 | Material Fabrication for Low Voltage Feeder Cable - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2930 | JDH4-02-007-PR-2930 | Material Fabrication for Low Voltage Feeder Cable - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2940 | JDH4-02-007-PR-2940 | Material Delivery for Low Voltage Feeder Cable | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2950 | JDH4-02-007-PR-2950 | Staging Time for Low Voltage Feeder Cable | 0 | 100% | 100% | 0
Wiring Devices | Wiring Devices |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2780 | JDH4-02-007-PR-2780 | PO for Wiring Devices | 0 | 100% | 100% | 0
JDH4-02-007-PR-2815 | JDH4-02-007-PR-2815 | Material Fabrication for Wiring Devices - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2816 | JDH4-02-007-PR-2816 | Material Fabrication for Wiring Devices - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2817 | JDH4-02-007-PR-2817 | Material Fabrication for Wiring Devices - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2818 | JDH4-02-007-PR-2818 | Material Fabrication for Wiring Devices - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2819 | JDH4-02-007-PR-2819 | Material Fabrication for Wiring Devices - Stage 5 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2820 | JDH4-02-007-PR-2820 | Material Fabrication for Wiring Devices - Stage 6 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2860 | JDH4-02-007-PR-2860 | Material Delivery for Wiring Devices | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2900 | JDH4-02-007-PR-2900 | Staging Time for Wiring Devices | 0 | 100% | 100% | 0
Enclosed Switches and Circuit Breakers | Enclosed Switches and Circuit Breakers |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2960 | JDH4-02-007-PR-2960 | PO for Enclosed Switches and Circuit Breakers | 0 | 100% | 100% | 0
JDH4-02-007-PR-2965 | JDH4-02-007-PR-2965 | Material Fabrication for Enclosed Switches and Circuit Breakers - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2966 | JDH4-02-007-PR-2966 | Material Fabrication for Enclosed Switches and Circuit Breakers - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2967 | JDH4-02-007-PR-2967 | Material Fabrication for Enclosed Switches and Circuit Breakers - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2970 | JDH4-02-007-PR-2970 | Material Fabrication for Enclosed Switches and Circuit Breakers - Stage 6 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2969 | JDH4-02-007-PR-2969 | Material Fabrication for Enclosed Switches and Circuit Breakers - Stage 5 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2968 | JDH4-02-007-PR-2968 | Material Fabrication for Enclosed Switches and Circuit Breakers - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2980 | JDH4-02-007-PR-2980 | Material Delivery for Enclosed Switches and Circuit Breakers | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2990 | JDH4-02-007-PR-2990 | Staging Time for Enclosed Switches and Circuit Breakers | 0 | 100% | 100% | 0
Raceways for Electrical Systems | Raceways for Electrical Systems |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2790 | JDH4-02-007-PR-2790 | PO for Raceways for Electrical Systems | 0 | 100% | 100% | 0
JDH4-02-007-PR-2827 | JDH4-02-007-PR-2827 | Material Fabrication for Raceways for Electrical Systems - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2828 | JDH4-02-007-PR-2828 | Material Fabrication for Raceways for Electrical Systems - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2829 | JDH4-02-007-PR-2829 | Material Fabrication for Raceways for Electrical Systems - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2830 | JDH4-02-007-PR-2830 | Material Fabrication for Raceways for Electrical Systems - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2870 | JDH4-02-007-PR-2870 | Material Delivery for Raceways for Electrical Systems | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2910 | JDH4-02-007-PR-2910 | Staging Time for Raceways for Electrical Systems | 0 | 100% | 100% | 0
Electrical Manholes | Electrical Manholes |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-2520 | JDH4-02-007-PR-2520 | PO for Electrical Manholes | 0 | 100% | 100% | 0
JDH4-02-007-PR-2555 | JDH4-02-007-PR-2555 | Material Fabrication for Electrical Manholes - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2557 | JDH4-02-007-PR-2557 | Material Fabrication for Electrical Manholes - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2556 | JDH4-02-007-PR-2556 | Material Fabrication for Electrical Manholes - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2558 | JDH4-02-007-PR-2558 | Material Fabrication for Electrical Manholes - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2559 | JDH4-02-007-PR-2559 | Material Fabrication for Electrical Manholes - Stage 5 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2560 | JDH4-02-007-PR-2560 | Material Fabrication for Electrical Manholes - Stage 6 | 0 | 100% | 100% | 0
JDH4-02-007-PR-2600 | JDH4-02-007-PR-2600 | Material Delivery for Electrical Manholes | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-2640 | JDH4-02-007-PR-2640 | Staging Time for Electrical Manholes | 0 | 100% | 100% | 0
ICT (Data& telephone System) | ICT (Data& telephone System) |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-3040 | JDH4-02-007-PR-3040 | PO for ICT (Data& telephone System) | 0 | 100% | 100% | 0
JDH4-02-007-PR-3055 | JDH4-02-007-PR-3055 | Material Fabrication for ICT (Data& telephone System) - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3056 | JDH4-02-007-PR-3056 | Material Fabrication for ICT (Data& telephone System) - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3057 | JDH4-02-007-PR-3057 | Material Fabrication for ICT (Data& telephone System) - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3058 | JDH4-02-007-PR-3058 | Material Fabrication for ICT (Data& telephone System) - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3059 | JDH4-02-007-PR-3059 | Material Fabrication for ICT (Data& telephone System) - Stage 5 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3060 | JDH4-02-007-PR-3060 | Material Fabrication for ICT (Data& telephone System) - Stage 6 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3080 | JDH4-02-007-PR-3080 | Material Delivery for ICT (Data& telephone System) | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-3100 | JDH4-02-007-PR-3100 | Staging Time for ICT (Data& telephone System) | 0 | 100% | 100% | 0
Programmable Logic Controllers | Programmable Logic Controllers |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-3120 | JDH4-02-007-PR-3120 | PO for Programmable Logic Controllers | 0 | 100% | 100% | 0
JDH4-02-007-PR-3125 | JDH4-02-007-PR-3125 | Material Fabrication for Programmable Logic Controllers - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3126 | JDH4-02-007-PR-3126 | Material Fabrication for Programmable Logic Controllers - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3127 | JDH4-02-007-PR-3127 | Material Fabrication for Programmable Logic Controllers - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3130 | JDH4-02-007-PR-3130 | Material Fabrication for Programmable Logic Controllers - Stage 6 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3129 | JDH4-02-007-PR-3129 | Material Fabrication for Programmable Logic Controllers - Stage 5 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3128 | JDH4-02-007-PR-3128 | Material Fabrication for Programmable Logic Controllers - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3140 | JDH4-02-007-PR-3140 | Material Delivery for Programmable Logic Controllers | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-3150 | JDH4-02-007-PR-3150 | Staging Time for Programmable Logic Controllers | 0 | 100% | 100% | 0
Process Control Wiring | Process Control Wiring |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-3050 | JDH4-02-007-PR-3050 | PO for Process Control Wiring | 0 | 100% | 100% | 0
JDH4-02-007-PR-3067 | JDH4-02-007-PR-3067 | Material Fabrication for Process Control Wiring - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3068 | JDH4-02-007-PR-3068 | Material Fabrication for Process Control Wiring - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3069 | JDH4-02-007-PR-3069 | Material Fabrication for Process Control Wiring - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3070 | JDH4-02-007-PR-3070 | Material Fabrication for Process Control Wiring - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3090 | JDH4-02-007-PR-3090 | Material Delivery for Process Control Wiring | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-3110 | JDH4-02-007-PR-3110 | Staging Time for Process Control Wiring | 0 | 100% | 100% | 0
Instrumentation for Process Systems | Instrumentation for Process Systems |  | 179076.09 |  | 100% | 179076.09
JDH4-02-007-PR-3000 | JDH4-02-007-PR-3000 | PO for Instrumentation for Process Systems | 0 | 100% | 100% | 0
JDH4-02-007-PR-3005 | JDH4-02-007-PR-3005 | Material Fabrication for Instrumentation for Process Systems - Stage 1 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3006 | JDH4-02-007-PR-3006 | Material Fabrication for Instrumentation for Process Systems - Stage 2 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3007 | JDH4-02-007-PR-3007 | Material Fabrication for Instrumentation for Process Systems - Stage 3 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3010 | JDH4-02-007-PR-3010 | Material Fabrication for Instrumentation for Process Systems - Stage 6 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3009 | JDH4-02-007-PR-3009 | Material Fabrication for Instrumentation for Process Systems - Stage 5 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3008 | JDH4-02-007-PR-3008 | Material Fabrication for Instrumentation for Process Systems - Stage 4 | 0 | 100% | 100% | 0
JDH4-02-007-PR-3020 | JDH4-02-007-PR-3020 | Material Delivery for Instrumentation for Process Systems | 179076.09 | 100% | 100% | 179076.09
JDH4-02-007-PR-3030 | JDH4-02-007-PR-3030 | Staging Time for Instrumentation for Process Systems | 0 | 100% | 100% | 0
Construction | Construction |  | 38393913.07 |  | 91.53% | 35140714.49
Demolition Works | Demolition Works |  | 505616.54 |  | 100% | 505616.54
Demolition in Road network | Demolition in Road network |  | 127411.78 |  | 100% | 127411.78
JDH4-02-007-CN-1000 | JDH4-02-007-CN-1000 | Concrete demolition works at the existing Underpass [Demolition Works ] | 26491.56 | 100% | 100% | 26491.56
JDH4-02-007-CN-1110 | JDH4-02-007-CN-1110 | Milling of the existing asphalt layer [Demolition Works ] | 25230.06 | 100% | 100% | 25230.06
JDH4-02-007-CN-1080 | JDH4-02-007-CN-1080 | Removal of the existing asphalt layers (up to base course layer) [Demolition Works ] | 37845.08 | 100% | 100% | 37845.08
JDH4-02-007-CN-1170 | JDH4-02-007-CN-1170 | Re-use and compaction of the existing aggregate base course layer | 37845.08 | 100% | 100% | 37845.08
Demolition in TSE network | Demolition in TSE network |  | 92720.45 |  | 100% | 92720.45
JDH4-02-007-CN-1480 | JDH4-02-007-CN-1480 | Pipe with diameter 63 mm pipe [Demolition Works ] | 1892.25 | 100% | 100% | 1892.25
JDH4-02-007-CN-1560 | JDH4-02-007-CN-1560 | Pipe with diameter 200 mm pipe [Demolition Works ] | 47937.11 | 100% | 100% | 47937.11
JDH4-02-007-CN-1610 | JDH4-02-007-CN-1610 | Wash out valve with chamber; on 200 mm dia pipeline Depth 1.5 - 4.0m [Demolition Works ] | 20184.04 | 100% | 100% | 20184.04
JDH4-02-007-CN-1620 | JDH4-02-007-CN-1620 | Gate valves on 200 mm pipeline [Demolition Works ] | 3784.51 | 100% | 100% | 3784.51
JDH4-02-007-CN-1590 | JDH4-02-007-CN-1590 | Pipe with diameter 250 mm pipe [Demolition Works ] | 18922.54 | 100% | 100% | 18922.54
Demolition in Storm water network | Demolition in Storm water network |  | 56073.8 |  | 100% | 56073.8
JDH4-02-007-CN-1670 | JDH4-02-007-CN-1670 | Manhole [Demolition Works ] | 8830.52 | 100% | 100% | 8830.52
JDH4-02-007-CN-1690 | JDH4-02-007-CN-1690 | Pipe with diameter 600 mm pipe [Demolition Works ] | 14128.83 | 100% | 100% | 14128.83
JDH4-02-007-CN-1700 | JDH4-02-007-CN-1700 | Pipe with diameter 800 mm pipe [Demolition Works ] | 14191.91 | 100% | 100% | 14191.91
JDH4-02-007-CN-1680 | JDH4-02-007-CN-1680 | Baffle box with dimentions 3.04x7.80m [Demolition Works ] | 18922.54 | 100% | 100% | 18922.54
Demolition in Sewerage network | Demolition in Sewerage network |  | 93225.07 |  | 100% | 93225.07
JDH4-02-007-CN-1630 | JDH4-02-007-CN-1630 | Pipe with diameter 200 mm pipe with depth 2.50 - 3.50m [Demolition Works ] | 26491.56 | 100% | 100% | 26491.56
JDH4-02-007-CN-1640 | JDH4-02-007-CN-1640 | Pipe with diameter 250 mm pipe with depth 3.50 - 4.50m [Demolition Works ] | 38349.69 | 100% | 100% | 38349.69
JDH4-02-007-CN-1650 | JDH4-02-007-CN-1650 | Manhole with depth 1.50m - 2.50m [Demolition Works ] | 12615.03 | 100% | 100% | 12615.03
JDH4-02-007-CN-1660 | JDH4-02-007-CN-1660 | Manhole with depth 4.50m - 5.50m [Demolition Works ] | 15768.79 | 100% | 100% | 15768.79
Demolition in Potable water network | Demolition in Potable water network |  | 46990.99 |  | 100% | 46990.99
JDH4-02-007-CN-1340 | JDH4-02-007-CN-1340 | Single house connection dia 63 mm [Demolition Works ] | 15768.79 | 100% | 100% | 15768.79
JDH4-02-007-CN-1400 | JDH4-02-007-CN-1400 | Pipe with diameter 200 mm [Demolition Works ] | 15453.41 | 100% | 100% | 15453.41
JDH4-02-007-CN-1430 | JDH4-02-007-CN-1430 | Wash out valve with chamber; on 200 mm dia pipeline [Demolition Works ] | 15768.79 | 100% | 100% | 15768.79
Demolition in Electrical works | Demolition in Electrical works |  | 89194.45 |  | 100% | 89194.45
JDH4-02-007-CN-1250 | JDH4-02-007-CN-1250 | Demolishing of existing Lighting Pole [Demolition Works ](Completed) | 17002.05 | 100% | 100% | 17002.05
JDH4-02-007-CN-3020 | JDH4-02-007-CN-3020 | Relocating of existing Lighting Pole [Road 02 ](Completed) | 14036.17 | 100% | 100% | 14036.17
JDH4-02-007-CN-3020R | JDH4-02-007-CN-3020R | Relocating of existing Lighting Pole [Road 02 ] | 27536.54 | 100% | 100% | 27536.54
JDH4-02-007-CN-1250R | JDH4-02-007-CN-1250R | Demolishing of existing Lighting Pole [Demolition Works ] | 3812.75 | 100% | 100% | 3812.75
JDH4-02-007-CN-3040 | JDH4-02-007-CN-3040 | Relocating of existing Lighting Pole [Road 04-R ] | 12615.03 | 100% | 100% | 12615.03
JDH4-02-007-CN-3030 | JDH4-02-007-CN-3030 | Relocating of existing Lighting Pole [Road 08 ] | 4730.64 | 100% | 100% | 4730.64
JDH4-02-007-CN-3050 | JDH4-02-007-CN-3050 | Relocating of existing Lighting Pole [Road 10 ] | 9461.27 | 100% | 100% | 9461.27
Plots | Plots |  | 4337407.52 |  | 100% | 4337407.52
Excavation | Excavation |  | 282577.06 |  | 100% | 282577.06
JDH4-02-007-CN-1760 | JDH4-02-007-CN-1760 | Plots excavation [Plots ] | 282577.06 | 100% | 100% | 282577.06
Backfilling | Backfilling |  | 4054830.46 |  | 100% | 4054830.46
JDH4-02-007-CN-1820 | JDH4-02-007-CN-1820 | Plots backfilling Stage 1 [Plots ] | 1013707.62 | 100% | 100% | 1013707.62
JDH4-02-007-CN-1830 | JDH4-02-007-CN-1830 | Plots backfilling Stage 2 [Plots ](Completed) | 709608.44 | 100% | 100% | 709608.44
JDH4-02-007-CN-1840 | JDH4-02-007-CN-1840 | Plots backfilling Stage 3 [Plots ](Completed) | 202739.5 | 100% | 100% | 202739.5
JDH4-02-007-CN-1830R | JDH4-02-007-CN-1830R | Plots backfilling Stage 2 [Plots ] | 304109.26 | 100% | 100% | 304109.26
JDH4-02-007-CN-1840R | JDH4-02-007-CN-1840R | Plots backfilling Stage 3 [Plots ] | 810958.02 | 100% | 100% | 810958.02
JDH4-02-007-CN-1850 | JDH4-02-007-CN-1850 | Plots backfilling Stage 4 [Plots ] | 1013707.62 | 100% | 100% | 1013707.62
Roads | Roads |  | 21997203.9 |  | 98.67% | 21705656.71
Road 04-R | Road 04-R |  | 5772635.72 |  | 100% | 5772635.72
Box Culvert | Box Culvert |  | 499735.96 |  | 100% | 499735.96
JDH4-02-007-CN-5580 | JDH4-02-007-CN-5580 | Excavation For Box Culvert [Road 04-R ] | 47552.35 | 100% | 100% | 47552.35
JDH4-02-007-CN-5590 | JDH4-02-007-CN-5590 | Backfilling For Box Culvert [Road 04-R ] | 30578.83 | 100% | 100% | 30578.83
JDH4-02-007-CN-5600 | JDH4-02-007-CN-5600 | Plain Concrete for box culvert [Road 04-R ] | 19679.44 | 100% | 100% | 19679.44
JDH4-02-007-CN-5610 | JDH4-02-007-CN-5610 | Steel Reinforcement for box culverts [Road 04-R ](Completed) | 33891.12 | 100% | 100% | 33891.12
JDH4-02-007-CN-5610R | JDH4-02-007-CN-5610R | Steel Reinforcement for box culverts [Road 04-R ] | 135564.48 | 100% | 100% | 135564.48
JDH4-02-007-CN-5620 | JDH4-02-007-CN-5620 | Reinforced Concrete for box culvert [Road 04-R ] | 232469.74 | 100% | 100% | 232469.74
Road Works + Roundabout | Road Works + Roundabout |  | 3655865.47 |  | 100% | 3655865.47
Eartworks & Site grading | Eartworks & Site grading |  | 1552916.51 |  | 100% | 1552916.51
JDH4-02-007-CN-1810 | JDH4-02-007-CN-1810 | Road backfilling [Road 04-R ](Completed) | 551521.49 | 100% | 100% | 551521.49
JDH4-02-007-CN-1750 | JDH4-02-007-CN-1750 | Road excavation [Road 04-R ](Completed) | 14012.87 | 100% | 100% | 14012.87
JDH4-02-007-CN-1810R | JDH4-02-007-CN-1810R | Road backfilling [Road 04-R ] | 827282.24 | 100% | 100% | 827282.24
JDH4-02-007-CN-1750R | JDH4-02-007-CN-1750R | Road excavation [Road 04-R ] | 21019.3 | 100% | 100% | 21019.3
JDH4-02-007-CN-1930 | JDH4-02-007-CN-1930 | Subgrade [Road 04-R ] | 139080.6 | 100% | 100% | 139080.6
Asphalt Works | Asphalt Works |  | 931597.75 |  | 100% | 931597.75
JDH4-02-007-CN-1990 | JDH4-02-007-CN-1990 | Aggregate base course [Road 04-R ] | 141644.69 | 100% | 100% | 141644.69
JDH4-02-007-CN-2040 | JDH4-02-007-CN-2040 | Prime Coat (MC1) [Road 04-R ] | 78995.31 | 100% | 100% | 78995.31
JDH4-02-007-CN-2090 | JDH4-02-007-CN-2090 | Bituminous base course [Road 04-R ] | 710957.75 | 100% | 100% | 710957.75
Finishing Works | Finishing Works |  | 1171351.21 |  | 100% | 1171351.21
Asphalt Wearing Course | Asphalt Wearing Course |  | 418188.18 |  | 100% | 418188.18
JDH4-02-007-CN-2140 | JDH4-02-007-CN-2140 | Tack Coat (RC2) [Road 04-R ] | 41818.82 | 100% | 100% | 41818.82
JDH4-02-007-CN-2190 | JDH4-02-007-CN-2190 | Bituminous concrete wearing course [Road 04-R ] | 376369.36 | 100% | 100% | 376369.36
Precast Concrete Curb | Precast Concrete Curb |  | 260761.75 |  | 100% | 260761.75
JDH4-02-007-CN-2240 | JDH4-02-007-CN-2240 | Installation of Precast Concrete curb [Road 04-R ] | 260761.75 | 100% | 100% | 260761.75
Precast Interlocking block pavers | Precast Interlocking block pavers |  | 247979.91 |  | 100% | 247979.91
JDH4-02-007-CN-2290 | JDH4-02-007-CN-2290 | Installation of Interlocking block pavers for sidewalk/footpath [Road 04-R ] | 247979.91 | 100% | 100% | 247979.91
Pavement Markings | Pavement Markings |  | 70108.71 |  | 100% | 70108.71
JDH4-02-007-CN-2340 | JDH4-02-007-CN-2340 | Pavement markings [Road 04-R ] | 70108.71 | 100% | 100% | 70108.71
Traffic Signage | Traffic Signage |  | 119121.91 |  | 100% | 119121.91
JDH4-02-007-CN-2390 | JDH4-02-007-CN-2390 | Installation of Traffic Signs [Road 04-R ] | 119121.91 | 100% | 100% | 119121.91
Guardrail | Guardrail |  | 55190.75 |  | 100% | 55190.75
JDH4-02-007-CN-2400 | JDH4-02-007-CN-2400 | Installation of Guard rails [Road 04-R ] | 55190.75 | 100% | 100% | 55190.75
Storm Water Drainage | Storm Water Drainage |  | 616227.34 |  | 100% | 616227.34
Pipe Works | Pipe Works |  | 372950.21 |  | 100% | 372950.21
JDH4-02-007-CN-5370 | JDH4-02-007-CN-5370 | Excavation and Compaction (FDT) [Road 04-R ](Completed) | 13055.44 | 100% | 100% | 13055.44
JDH4-02-007-CN-5420 | JDH4-02-007-CN-5420 | Sand Bedding [Road 04-R ](Completed) | 6527.73 | 100% | 100% | 6527.73
JDH4-02-007-CN-5470 | JDH4-02-007-CN-5470 | Installation of GRP Pipe [Road 04-R ](Completed) | 91388.14 | 100% | 100% | 91388.14
JDH4-02-007-CN-5520 | JDH4-02-007-CN-5520 | Sand Cover & Warning Tape [Road 04-R ] | 18629.79 | 100% | 100% | 18629.79
JDH4-02-007-CN-5570 | JDH4-02-007-CN-5570 | Backfilling & Compaction [Road 04-R ] | 37259.53 | 100% | 100% | 37259.53
JDH4-02-007-CN-5370R | JDH4-02-007-CN-5370R | Excavation and Compaction (FDT) [Road 04-R ] | 24245.82 | 100% | 100% | 24245.82
JDH4-02-007-CN-5420R | JDH4-02-007-CN-5420R | Sand Bedding [Road 04-R ] | 12122.92 | 100% | 100% | 12122.92
JDH4-02-007-CN-5470R | JDH4-02-007-CN-5470R | Installation of GRP Pipe [Road 04-R ] | 169720.83 | 100% | 100% | 169720.83
Pipe Encasement | Pipe Encasement |  | 13406.24 |  | 100% | 13406.24
JDH4-02-007-CN-5840 | JDH4-02-007-CN-5840 | Pipe Encasement Works [Road 04-R ] | 13406.24 | 100% | 100% | 13406.24
Manholes | Manholes |  | 130842.92 |  | 100% | 130842.92
JDH4-02-007-CN-5670 | JDH4-02-007-CN-5670 | Installation of Precast Manhole Ring [Road 04-R ] | 130842.92 | 100% | 100% | 130842.92
Precast Acces Openinig | Precast Acces Openinig |  | 7569.02 |  | 100% | 7569.02
JDH4-02-007-CN-5720 | JDH4-02-007-CN-5720 | Installation of Precast Access Opening [Road 04-R ] | 7569.02 | 100% | 100% | 7569.02
Catch Basins | Catch Basins |  | 40998.84 |  | 100% | 40998.84
JDH4-02-007-CN-5760 | JDH4-02-007-CN-5760 | Construction of Catch basins [Road 04-R ] | 40998.84 | 100% | 100% | 40998.84
Concrete Outfalls | Concrete Outfalls |  | 50460.11 |  | 100% | 50460.11
JDH4-02-007-CN-5790 | JDH4-02-007-CN-5790 | Construction of Concrete outfall structure [Road 04-R ] | 50460.11 | 100% | 100% | 50460.11
Sewerage Network | Sewerage Network |  | 233847.07 |  | 100% | 233847.07
Pipe Works | Pipe Works |  | 151982.41 |  | 100% | 151982.41
JDH4-02-007-CN-4820 | JDH4-02-007-CN-4820 | Excavation & Compaction (FDT) [Road 04-R ](Completed) | 759.81 | 100% | 100% | 759.81
JDH4-02-007-CN-4820R | JDH4-02-007-CN-4820R | Excavation & Compaction (FDT) [Road 04-R ] | 14436.45 | 100% | 100% | 14436.45
JDH4-02-007-CN-4890 | JDH4-02-007-CN-4890 | Sand Bedding [Road 04-R ] | 7599.22 | 100% | 100% | 7599.22
JDH4-02-007-CN-4960 | JDH4-02-007-CN-4960 | Installation of GRP Pipe [Road 04-R ] | 75992.31 | 100% | 100% | 75992.31
JDH4-02-007-CN-5030 | JDH4-02-007-CN-5030 | Gravity Test [Road 04-R ] | 30396.93 | 100% | 100% | 30396.93
JDH4-02-007-CN-5100 | JDH4-02-007-CN-5100 | Sand Cover & Warning Tape [Road 04-R ] | 7599.22 | 100% | 100% | 7599.22
JDH4-02-007-CN-5170 | JDH4-02-007-CN-5170 | Backfilling & Compaction [Road 04-R ] | 15198.47 | 100% | 100% | 15198.47
Pipe Encasement | Pipe Encasement |  | 760.54 |  | 100% | 760.54
JDH4-02-007-CN-5310 | JDH4-02-007-CN-5310 | Pipe Encasement Works [Road 04-R ] | 760.54 | 100% | 100% | 760.54
Manholes | Manholes |  | 81104.12 |  | 100% | 81104.12
JDH4-02-007-CN-5240 | JDH4-02-007-CN-5240 | Installation of Manholes [Road 04-R ] | 81104.12 | 100% | 100% | 81104.12
TSE Network | TSE Network |  | 186231.54 |  | 100% | 186231.54
Pipe Works | Pipe Works |  | 160003.08 |  | 100% | 160003.08
JDH4-02-007-CN-4040 | JDH4-02-007-CN-4040 | Excavation and Compaction (FDT) [Road 04-R ] | 15169.19 | 100% | 100% | 15169.19
JDH4-02-007-CN-4110 | JDH4-02-007-CN-4110 | Sand Bedding [Road 04-R ] | 7584.62 | 100% | 100% | 7584.62
JDH4-02-007-CN-4180 | JDH4-02-007-CN-4180 | Installation of HDPE Pipe [Road 04-R ] | 75846 | 100% | 100% | 75846
JDH4-02-007-CN-4250 | JDH4-02-007-CN-4250 | Initial Pressure Test [Road 04-R ] | 30338.38 | 100% | 100% | 30338.38
JDH4-02-007-CN-4320 | JDH4-02-007-CN-4320 | Sand Cover & Warning [Road 04-R ] | 7584.62 | 100% | 100% | 7584.62
JDH4-02-007-CN-4390 | JDH4-02-007-CN-4390 | Backfilling & Compaction [Road 04-R ] | 15169.19 | 100% | 100% | 15169.19
JDH4-02-007-CN-4700 | JDH4-02-007-CN-4700 | Point of Connection [Road 04-R ] | 8311.08 | 100% | 100% | 8311.08
Pipe Encasement | Pipe Encasement |  | 7554.9 |  | 100% | 7554.9
JDH4-02-007-CN-4460 | JDH4-02-007-CN-4460 | Encasement for Pipes [Road 04-R ] | 7554.9 | 100% | 100% | 7554.9
Valves | Valves |  | 18673.56 |  | 100% | 18673.56
JDH4-02-007-CN-4530 | JDH4-02-007-CN-4530 | Installation of Gate Valves [Road 04-R ] | 18673.56 | 100% | 100% | 18673.56
Potable Network | Potable Network |  | 193744.83 |  | 100% | 193744.83
Pipe Works | Pipe Works |  | 124027.28 |  | 100% | 124027.28
JDH4-02-007-CN-3360 | JDH4-02-007-CN-3360 | Excavation and Compaction (FDT) [Road 04-R ] | 12402.74 | 100% | 100% | 12402.74
JDH4-02-007-CN-3430 | JDH4-02-007-CN-3430 | Sand Bedding [Road 04-R ] | 6201.37 | 100% | 100% | 6201.37
JDH4-02-007-CN-3500 | JDH4-02-007-CN-3500 | Installation of HDPE Pipe [Road 04-R ] | 62013.62 | 100% | 100% | 62013.62
JDH4-02-007-CN-3570 | JDH4-02-007-CN-3570 | Initial Pressure Test [Road 04-R ] | 24805.44 | 100% | 100% | 24805.44
JDH4-02-007-CN-3640 | JDH4-02-007-CN-3640 | Sand Cover & Warning Tape [Road 04-R ] | 6201.37 | 100% | 100% | 6201.37
JDH4-02-007-CN-3710 | JDH4-02-007-CN-3710 | Backfilling [Road 04-R ] | 12402.74 | 100% | 100% | 12402.74
Pipe Encasement | Pipe Encasement |  | 9796.16 |  | 100% | 9796.16
JDH4-02-007-CN-3780 | JDH4-02-007-CN-3780 | Encasement for Pipes [Road 04-R ] | 9796.16 | 100% | 100% | 9796.16
Valves | Valves |  | 15768.79 |  | 100% | 15768.79
JDH4-02-007-CN-3850 | JDH4-02-007-CN-3850 | Installation of Gate Valves [Road 04-R ] | 15768.79 | 100% | 100% | 15768.79
Fire Hydrant | Fire Hydrant |  | 44152.6 |  | 100% | 44152.6
JDH4-02-007-CN-3940 | JDH4-02-007-CN-3940 | Installation of 3-outlet fire hydrant [Road 04-R ] | 44152.6 | 100% | 100% | 44152.6
Electrical Works | Electrical Works |  | 386983.51 |  | 100% | 386983.51
Street Lighting | Street Lighting |  | 173158.79 |  | 100% | 173158.79
JDH4-02-007-CN-2830 | JDH4-02-007-CN-2830 | Installation of Road Crossing Ducts [Road 04-R ] | 17941.62 | 100% | 100% | 17941.62
JDH4-02-007-CN-2820 | JDH4-02-007-CN-2820 | Excavation for Low Voltage Cable [Road 04-R ] | 9991.1 | 100% | 100% | 9991.1
JDH4-02-007-CN-2880 | JDH4-02-007-CN-2880 | Installation of Low Voltage Cables [Road 04-R ] | 50825.95 | 100% | 100% | 50825.95
JDH4-02-007-CN-2920 | JDH4-02-007-CN-2920 | Installation of Lighting Poles [Road 04-R ] | 73193.61 | 100% | 100% | 73193.61
JDH4-02-007-CN-2960 | JDH4-02-007-CN-2960 | Installation of Lighting Luminaires [Road 04-R ] | 17422 | 100% | 100% | 17422
JDH4-02-007-CN-2990 | JDH4-02-007-CN-2990 | Installation of Earthing System [Road 04-R ] | 3784.51 | 100% | 100% | 3784.51
Telecommunication | Telecommunication |  | 213824.72 |  | 100% | 213824.72
JDH4-02-007-CN-3110 | JDH4-02-007-CN-3110 | Installation Road Crossing R/F 6 way 50mm HDPE Pipe [Road 04-R ] | 182034.85 | 100% | 100% | 182034.85
JDH4-02-007-CN-3180 | JDH4-02-007-CN-3180 | Installation Road Crossing Un R/F 6 way 50mm HDPE Pipe [Road 04-R ] | 3406.06 | 100% | 100% | 3406.06
JDH4-02-007-CN-3290 | JDH4-02-007-CN-3290 | Installation of Manholes [Road 04-R ] | 28383.81 | 100% | 100% | 28383.81
Road 08 | Road 08 |  | 5696664.36 |  | 100% | 5696664.36
Road Works + Roundabout | Road Works + Roundabout |  | 3190850.42 |  | 100% | 3190850.42
Eartworks & Site grading | Eartworks & Site grading |  | 1378559.54 |  | 100% | 1378559.54
JDH4-02-007-CN-1710 | JDH4-02-007-CN-1710 | Road excavation [Road 08 ](Completed) | 21754.74 | 100% | 100% | 21754.74
JDH4-02-007-CN-1770 | JDH4-02-007-CN-1770 | Road backfilling [Road 08 ](Completed) | 673400.08 | 100% | 100% | 673400.08
JDH4-02-007-CN-1770R | JDH4-02-007-CN-1770R | Road backfilling [Road 08 ] | 550963.7 | 100% | 100% | 550963.7
JDH4-02-007-CN-1710R | JDH4-02-007-CN-1710R | Road excavation [Road 08 ] | 9323.46 | 100% | 100% | 9323.46
JDH4-02-007-CN-1890 | JDH4-02-007-CN-1890 | Subgrade [Road 08 ] | 123117.55 | 100% | 100% | 123117.55
Asphalt Works | Asphalt Works |  | 825025.99 |  | 100% | 825025.99
JDH4-02-007-CN-1950 | JDH4-02-007-CN-1950 | Aggregate base course [Road 08 ] | 125409.15 | 100% | 100% | 125409.15
JDH4-02-007-CN-2000 | JDH4-02-007-CN-2000 | Prime Coat (MC1) [Road 08 ] | 70000.79 | 100% | 100% | 70000.79
JDH4-02-007-CN-2050 | JDH4-02-007-CN-2050 | Bituminous base course [Road 08 ] | 629616.05 | 100% | 100% | 629616.05
Finishing Works | Finishing Works |  | 987264.89 |  | 100% | 987264.89
Asphalt Wearing Course | Asphalt Wearing Course |  | 370629.53 |  | 100% | 370629.53
JDH4-02-007-CN-2100 | JDH4-02-007-CN-2100 | Tack Coat (RC2) [Road 08 ] | 36898.96 | 100% | 100% | 36898.96
JDH4-02-007-CN-2150 | JDH4-02-007-CN-2150 | Bituminous concrete wearing course [Road 08 ] | 333730.57 | 100% | 100% | 333730.57
Precast Concrete Curb | Precast Concrete Curb |  | 231115.34 |  | 100% | 231115.34
JDH4-02-007-CN-2200 | JDH4-02-007-CN-2200 | Installation of Precast Concrete curb [Road 08 ] | 231115.34 | 100% | 100% | 231115.34
Precast Interlocking block pavers | Precast Interlocking block pavers |  | 219785.33 |  | 100% | 219785.33
JDH4-02-007-CN-2250 | JDH4-02-007-CN-2250 | Installation of Interlocking block pavers for sidewalk/footpath [Road 08 ] | 219785.33 | 100% | 100% | 219785.33
Pavement Markings | Pavement Markings |  | 62150.42 |  | 100% | 62150.42
JDH4-02-007-CN-2300 | JDH4-02-007-CN-2300 | Pavement markings [Road 08 ] | 62150.42 | 100% | 100% | 62150.42
Traffic Signage | Traffic Signage |  | 103584.27 |  | 100% | 103584.27
JDH4-02-007-CN-2350 | JDH4-02-007-CN-2350 | Installation of Traffic Signs [Road 08 ] | 103584.27 | 100% | 100% | 103584.27
Storm Water Drainage | Storm Water Drainage |  | 873781.35 |  | 100% | 873781.35
Pipe Works | Pipe Works |  | 547596.42 |  | 100% | 547596.42
JDH4-02-007-CN-5330 | JDH4-02-007-CN-5330 | Excavation and Compaction (FDT) [Road 08 ](Completed) | 8213.94 | 100% | 100% | 8213.94
JDH4-02-007-CN-5380 | JDH4-02-007-CN-5380 | Sand Bedding [Road 08 ](Completed) | 4106.98 | 100% | 100% | 4106.98
JDH4-02-007-CN-5430 | JDH4-02-007-CN-5430 | Installation of GRP Pipe [Road 08 ](Completed) | 57497.63 | 100% | 100% | 57497.63
JDH4-02-007-CN-5480 | JDH4-02-007-CN-5480 | Sand Cover & Warning Tape [Road 08 ](Completed) | 4106.98 | 100% | 100% | 4106.98
JDH4-02-007-CN-5530 | JDH4-02-007-CN-5530 | Backfilling & Compaction [Road 08 ](Completed) | 8213.94 | 100% | 100% | 8213.94
JDH4-02-007-CN-5330R | JDH4-02-007-CN-5330R | Excavation and Compaction (FDT) [Road 08 ] | 46545.67 | 100% | 100% | 46545.67
JDH4-02-007-CN-5380R | JDH4-02-007-CN-5380R | Sand Bedding [Road 08 ] | 23272.86 | 100% | 100% | 23272.86
JDH4-02-007-CN-5430R | JDH4-02-007-CN-5430R | Installation of GRP Pipe [Road 08 ] | 325819.88 | 100% | 100% | 325819.88
JDH4-02-007-CN-5530R | JDH4-02-007-CN-5530R | Backfilling & Compaction [Road 08 ] | 46545.67 | 100% | 100% | 46545.67
JDH4-02-007-CN-5480R | JDH4-02-007-CN-5480R | Sand Cover & Warning Tape [Road 08 ] | 23272.86 | 100% | 100% | 23272.86
Pipe Encasement | Pipe Encasement |  | 20926.82 |  | 100% | 20926.82
JDH4-02-007-CN-5800 | JDH4-02-007-CN-5800 | Pipe Encasement Works [Road 08 ] | 20926.82 | 100% | 100% | 20926.82
Manholes | Manholes |  | 224206.55 |  | 100% | 224206.55
JDH4-02-007-CN-5630 | JDH4-02-007-CN-5630 | Installation of Precast Manhole Ring [Road 08 ] | 224206.55 | 100% | 100% | 224206.55
Precast Acces Openinig | Precast Acces Openinig |  | 11353.53 |  | 100% | 11353.53
JDH4-02-007-CN-5680 | JDH4-02-007-CN-5680 | Installation of Precast Access Opening [Road 08 ] | 11353.53 | 100% | 100% | 11353.53
Catch Basins | Catch Basins |  | 69698.03 |  | 100% | 69698.03
JDH4-02-007-CN-5730 | JDH4-02-007-CN-5730 | Construction of Catch basins [Road 08 ] | 69698.03 | 100% | 100% | 69698.03
Sewerage Network | Sewerage Network |  | 558310.64 |  | 100% | 558310.64
Pipe Works | Pipe Works |  | 329545.92 |  | 100% | 329545.92
JDH4-02-007-CN-4780 | JDH4-02-007-CN-4780 | Excavation & Compaction (FDT) [Road 08 ] | 32954.6 | 100% | 100% | 32954.6
JDH4-02-007-CN-4850 | JDH4-02-007-CN-4850 | Sand Bedding [Road 08 ] | 16477.28 | 100% | 100% | 16477.28
JDH4-02-007-CN-4920 | JDH4-02-007-CN-4920 | Installation of GRP Pipe [Road 08 ] | 164772.96 | 100% | 100% | 164772.96
JDH4-02-007-CN-4990 | JDH4-02-007-CN-4990 | Gravity Test [Road 08 ] | 65909.2 | 100% | 100% | 65909.2
JDH4-02-007-CN-5060 | JDH4-02-007-CN-5060 | Sand Cover & Warning Tape [Road 08 ] | 16477.28 | 100% | 100% | 16477.28
JDH4-02-007-CN-5130 | JDH4-02-007-CN-5130 | Backfilling & Compaction [Road 08 ] | 32954.6 | 100% | 100% | 32954.6
Pipe Encasement | Pipe Encasement |  | 1673.19 |  | 100% | 1673.19
JDH4-02-007-CN-5270 | JDH4-02-007-CN-5270 | Pipe Encasement Works [Road 08 ] | 1673.19 | 100% | 100% | 1673.19
Manholes | Manholes |  | 227091.53 |  | 100% | 227091.53
JDH4-02-007-CN-5200 | JDH4-02-007-CN-5200 | Installation of Manholes [Road 08 ] | 227091.53 | 100% | 100% | 227091.53
TSE Network | TSE Network |  | 229231.81 |  | 100% | 229231.81
Pipe Works | Pipe Works |  | 195413.82 |  | 100% | 195413.82
JDH4-02-007-CN-4000 | JDH4-02-007-CN-4000 | Excavation and Compaction (FDT) [Road 08 ] | 18710.26 | 100% | 100% | 18710.26
JDH4-02-007-CN-4070 | JDH4-02-007-CN-4070 | Sand Bedding [Road 08 ] | 9355.16 | 100% | 100% | 9355.16
JDH4-02-007-CN-4140 | JDH4-02-007-CN-4140 | Installation of HDPE Pipe [Road 08 ] | 93551.37 | 100% | 100% | 93551.37
JDH4-02-007-CN-4210 | JDH4-02-007-CN-4210 | Initial Pressure Test [Road 08 ] | 37420.53 | 100% | 100% | 37420.53
JDH4-02-007-CN-4280 | JDH4-02-007-CN-4280 | Sand Cover & Warning [Road 08 ] | 9355.16 | 100% | 100% | 9355.16
JDH4-02-007-CN-4350 | JDH4-02-007-CN-4350 | Backfilling & Compaction [Road 08 ] | 18710.26 | 100% | 100% | 18710.26
JDH4-02-007-CN-4660 | JDH4-02-007-CN-4660 | Point of Connection [Road 08 ] | 8311.08 | 100% | 100% | 8311.08
Pipe Encasement | Pipe Encasement |  | 9368.07 |  | 100% | 9368.07
JDH4-02-007-CN-4420 | JDH4-02-007-CN-4420 | Encasement for Pipes [Road 08 ] | 9368.07 | 100% | 100% | 9368.07
Valves | Valves |  | 11204.14 |  | 100% | 11204.14
JDH4-02-007-CN-4490 | JDH4-02-007-CN-4490 | Installation of Gate Valves [Road 08 ] | 11204.14 | 100% | 100% | 11204.14
Risers | Risers |  | 13245.78 |  | 100% | 13245.78
JDH4-02-007-CN-4730 | JDH4-02-007-CN-4730 | Installation of Irrigation Riser with [Road 08 ] | 13245.78 | 100% | 100% | 13245.78
Potable Network | Potable Network |  | 199289.73 |  | 100% | 199289.73
Pipe Works | Pipe Works |  | 125752.87 |  | 100% | 125752.87
JDH4-02-007-CN-3320 | JDH4-02-007-CN-3320 | Excavation and Compaction (FDT) [Road 08 ] | 12575.3 | 100% | 100% | 12575.3
JDH4-02-007-CN-3390 | JDH4-02-007-CN-3390 | Sand Bedding [Road 08 ] | 6287.65 | 100% | 100% | 6287.65
JDH4-02-007-CN-3460 | JDH4-02-007-CN-3460 | Installation of HDPE Pipe [Road 08 ] | 62876.41 | 100% | 100% | 62876.41
JDH4-02-007-CN-3530 | JDH4-02-007-CN-3530 | Initial Pressure Test [Road 08 ] | 25150.56 | 100% | 100% | 25150.56
JDH4-02-007-CN-3600 | JDH4-02-007-CN-3600 | Sand Cover & Warning Tape [Road 08 ] | 6287.65 | 100% | 100% | 6287.65
JDH4-02-007-CN-3670 | JDH4-02-007-CN-3670 | Backfilling [Road 08 ] | 12575.3 | 100% | 100% | 12575.3
Pipe Encasement | Pipe Encasement |  | 9936.1 |  | 100% | 9936.1
JDH4-02-007-CN-3740 | JDH4-02-007-CN-3740 | Encasement for Pipes [Road 08 ] | 9936.1 | 100% | 100% | 9936.1
Valves | Valves |  | 13140.65 |  | 100% | 13140.65
JDH4-02-007-CN-3810 | JDH4-02-007-CN-3810 | Installation of Gate Valves [Road 08 ] | 13140.65 | 100% | 100% | 13140.65
Fire Hydrant | Fire Hydrant |  | 50460.11 |  | 100% | 50460.11
JDH4-02-007-CN-3900 | JDH4-02-007-CN-3900 | Installation of 3-outlet fire hydrant [Road 08 ] | 50460.11 | 100% | 100% | 50460.11
Electrical Works | Electrical Works |  | 645200.42 |  | 100% | 645200.42
LV Cables | LV Cables |  | 195304.1 |  | 100% | 195304.1
Low Voltage Cable | Low Voltage Cable |  | 195304.1 |  | 100% | 195304.1
JDH4-02-007-CN-2740 | JDH4-02-007-CN-2740 | Installation of Ring Main Unit (RMU) 3-way, 13.8kV [Road 08 ] | 63075.14 | 100% | 100% | 63075.14
JDH4-02-007-CN-2595 | JDH4-02-007-CN-2595 | Excavation for Low Voltage Cable [Road 08 ] | 10823.69 | 100% | 100% | 10823.69
JDH4-02-007-CN-2600 | JDH4-02-007-CN-2600 | Installation of Low Voltage Cables [Road 08 ] | 29946.31 | 100% | 100% | 29946.31
JDH4-02-007-CN-2730 | JDH4-02-007-CN-2730 | Installation of Unit Substation , 13.8/0.4 kV, 500kVA with RMU [Road 08 ] | 75690.17 | 100% | 100% | 75690.17
JDH4-02-007-CN-2710 | JDH4-02-007-CN-2710 | Installation of Low Voltage Distribution Panel (Main: 100A, MCCB, 5-50A, MCCB) [Road 08 ] | 15768.79 | 100% | 100% | 15768.79
Street Lighting | Street Lighting |  | 175355.47 |  | 100% | 175355.47
JDH4-02-007-CN-2760 | JDH4-02-007-CN-2760 | Installation of Road Crossing Ducts [Road 08 ] | 17695.84 | 100% | 100% | 17695.84
JDH4-02-007-CN-2890 | JDH4-02-007-CN-2890 | Installation of Lighting Poles [Road 08 ] | 79467.35 | 100% | 100% | 79467.35
JDH4-02-007-CN-2750 | JDH4-02-007-CN-2750 | Excavation for Low Voltage Cable [Road 08 ] | 8325.92 | 100% | 100% | 8325.92
JDH4-02-007-CN-2930 | JDH4-02-007-CN-2930 | Installation of Lighting Luminaires [Road 08 ] | 19910.85 | 100% | 100% | 19910.85
JDH4-02-007-CN-2840 | JDH4-02-007-CN-2840 | Installation of Low Voltage Cables [Road 08 ] | 42386.49 | 100% | 100% | 42386.49
JDH4-02-007-CN-2970 | JDH4-02-007-CN-2970 | Installation of Earthing System [Road 08 ] | 7569.02 | 100% | 100% | 7569.02
Telecommunication | Telecommunication |  | 274540.85 |  | 100% | 274540.85
JDH4-02-007-CN-3070 | JDH4-02-007-CN-3070 | Installation Road Crossing R/F 6 way 50mm HDPE Pipe [Road 08 ] | 126781.03 | 100% | 100% | 126781.03
JDH4-02-007-CN-3140 | JDH4-02-007-CN-3140 | Installation Road Crossing Un R/F 6 way 50mm HDPE Pipe [Road 08 ] | 3973.73 | 100% | 100% | 3973.73
JDH4-02-007-CN-3250 | JDH4-02-007-CN-3250 | Installation of Manholes [Road 08 ] | 45414.1 | 100% | 100% | 45414.1
JDH4-02-007-CN-3200 | JDH4-02-007-CN-3200 | Installation of 2 x 32 mm diameter HDPE ducts [Road 08 ] | 98371.99 | 100% | 100% | 98371.99
Road 07-N | Road 07-N |  | 5511432.43 |  | 100% | 5511432.43
Road Works | Road Works |  | 3118311.38 |  | 100% | 3118311.38
Eartworks & Site grading | Eartworks & Site grading |  | 1345959.82 |  | 100% | 1345959.82
JDH4-02-007-CN-1730 | JDH4-02-007-CN-1730 | Road excavation [Road 07-N ](Completed) | 13629.33 | 100% | 100% | 13629.33
JDH4-02-007-CN-1790 | JDH4-02-007-CN-1790 | Road backfilling [Road 07-N ](Completed) | 418403.53 | 100% | 100% | 418403.53
JDH4-02-007-CN-1790R | JDH4-02-007-CN-1790R | Road backfilling [Road 07-N ] | 777035.12 | 100% | 100% | 777035.12
JDH4-02-007-CN-1730R | JDH4-02-007-CN-1730R | Road excavation [Road 07-N ] | 16658.08 | 100% | 100% | 16658.08
JDH4-02-007-CN-1910 | JDH4-02-007-CN-1910 | Subgrade [Road 07-N ] | 120233.76 | 100% | 100% | 120233.76
Asphalt Works | Asphalt Works |  | 805652.45 |  | 100% | 805652.45
JDH4-02-007-CN-1970 | JDH4-02-007-CN-1970 | Aggregate base course [Road 07-N ] | 122460.38 | 100% | 100% | 122460.38
JDH4-02-007-CN-2020 | JDH4-02-007-CN-2020 | Prime Coat (MC1) [Road 07-N ] | 68436.53 | 100% | 100% | 68436.53
JDH4-02-007-CN-2070 | JDH4-02-007-CN-2070 | Bituminous base course [Road 07-N ] | 614755.54 | 100% | 100% | 614755.54
Finishing Works | Finishing Works |  | 966699.11 |  | 100% | 966699.11
Asphalt Wearing Course | Asphalt Wearing Course |  | 362429.75 |  | 100% | 362429.75
JDH4-02-007-CN-2120 | JDH4-02-007-CN-2120 | Tack Coat (RC2) [Road 07-N ] | 36078.98 | 100% | 100% | 36078.98
JDH4-02-007-CN-2170 | JDH4-02-007-CN-2170 | Bituminous concrete wearing course [Road 07-N ] | 326350.77 | 100% | 100% | 326350.77
Precast Concrete Curb | Precast Concrete Curb |  | 225534.37 |  | 100% | 225534.37
JDH4-02-007-CN-2220 | JDH4-02-007-CN-2220 | Installation of Precast Concrete curb [Road 07-N ] | 225534.37 | 100% | 100% | 225534.37
Precast Interlocking block pavers | Precast Interlocking block pavers |  | 214487.01 |  | 100% | 214487.01
JDH4-02-007-CN-2270 | JDH4-02-007-CN-2270 | Installation of Interlocking block pavers for sidewalk/footpath [Road 07-N ] | 214487.01 | 100% | 100% | 214487.01
Pavement Markings | Pavement Markings |  | 60663.71 |  | 100% | 60663.71
JDH4-02-007-CN-2320 | JDH4-02-007-CN-2320 | Pavement markings [Road 07-N ] | 60663.71 | 100% | 100% | 60663.71
Traffic Signage | Traffic Signage |  | 103584.27 |  | 100% | 103584.27
JDH4-02-007-CN-2370 | JDH4-02-007-CN-2370 | Installation of Traffic Signs [Road 07-N ] | 103584.27 | 100% | 100% | 103584.27
Storm Water Drainage | Storm Water Drainage |  | 936796.6 |  | 100% | 936796.6
Pipe Works | Pipe Works |  | 649331.81 |  | 100% | 649331.81
JDH4-02-007-CN-5350 | JDH4-02-007-CN-5350 | Excavation and Compaction (FDT) [Road 07-N ] | 64933.15 | 100% | 100% | 64933.15
JDH4-02-007-CN-5400 | JDH4-02-007-CN-5400 | Sand Bedding [Road 07-N ] | 32466.61 | 100% | 100% | 32466.61
JDH4-02-007-CN-5450 | JDH4-02-007-CN-5450 | Installation of GRP Pipe [Road 07-N ] | 454532.29 | 100% | 100% | 454532.29
JDH4-02-007-CN-5500 | JDH4-02-007-CN-5500 | Sand Cover & Warning Tape [Road 07-N ] | 32466.61 | 100% | 100% | 32466.61
JDH4-02-007-CN-5550 | JDH4-02-007-CN-5550 | Backfilling & Compaction [Road 07-N ] | 64933.15 | 100% | 100% | 64933.15
Pipe Encasement | Pipe Encasement |  | 24850.59 |  | 100% | 24850.59
JDH4-02-007-CN-5820 | JDH4-02-007-CN-5820 | Pipe Encasement Works [Road 07-N ] | 24850.59 | 100% | 100% | 24850.59
Manholes | Manholes |  | 130787.16 |  | 100% | 130787.16
JDH4-02-007-CN-5650 | JDH4-02-007-CN-5650 | Installation of Precast Manhole Ring [Road 07-N ] | 130787.16 | 100% | 100% | 130787.16
Precast Acces Openinig | Precast Acces Openinig |  | 7569.02 |  | 100% | 7569.02
JDH4-02-007-CN-5700 | JDH4-02-007-CN-5700 | Installation of Precast Access Opening [Road 07-N ] | 7569.02 | 100% | 100% | 7569.02
Catch Basins | Catch Basins |  | 73797.91 |  | 100% | 73797.91
JDH4-02-007-CN-5740 | JDH4-02-007-CN-5740 | Construction of Catch basins [Road 07-N ] | 73797.91 | 100% | 100% | 73797.91
Concrete Outfalls | Concrete Outfalls |  | 50460.11 |  | 100% | 50460.11
JDH4-02-007-CN-5770 | JDH4-02-007-CN-5770 | Construction of Concrete outfall structure [Road 07-N ] | 50460.11 | 100% | 100% | 50460.11
Sewerage Network | Sewerage Network |  | 489984.35 |  | 100% | 489984.35
Pipe Works | Pipe Works |  | 326102.92 |  | 100% | 326102.92
JDH4-02-007-CN-4800 | JDH4-02-007-CN-4800 | Excavation & Compaction (FDT) [Road 07-N ] | 32610.3 | 100% | 100% | 32610.3
JDH4-02-007-CN-4870 | JDH4-02-007-CN-4870 | Sand Bedding [Road 07-N ] | 16305.13 | 100% | 100% | 16305.13
JDH4-02-007-CN-4940 | JDH4-02-007-CN-4940 | Installation of GRP Pipe [Road 07-N ] | 163051.46 | 100% | 100% | 163051.46
JDH4-02-007-CN-5010 | JDH4-02-007-CN-5010 | Gravity Test [Road 07-N ] | 65220.6 | 100% | 100% | 65220.6
JDH4-02-007-CN-5080 | JDH4-02-007-CN-5080 | Sand Cover & Warning Tape [Road 07-N ] | 16305.13 | 100% | 100% | 16305.13
JDH4-02-007-CN-5150 | JDH4-02-007-CN-5150 | Backfilling & Compaction [Road 07-N ] | 32610.3 | 100% | 100% | 32610.3
Pipe Encasement | Pipe Encasement |  | 1673.19 |  | 100% | 1673.19
JDH4-02-007-CN-5290 | JDH4-02-007-CN-5290 | Pipe Encasement Works [Road 07-N ] | 1673.19 | 100% | 100% | 1673.19
Manholes | Manholes |  | 162208.24 |  | 100% | 162208.24
JDH4-02-007-CN-5220 | JDH4-02-007-CN-5220 | Installation of Manholes [Road 07-N ] | 162208.24 | 100% | 100% | 162208.24
TSE Network | TSE Network |  | 244612.82 |  | 100% | 244612.82
Pipe Works | Pipe Works |  | 214076.25 |  | 100% | 214076.25
JDH4-02-007-CN-4020 | JDH4-02-007-CN-4020 | Excavation and Compaction (FDT) [Road 07-N ] | 20576.51 | 100% | 100% | 20576.51
JDH4-02-007-CN-4090 | JDH4-02-007-CN-4090 | Sand Bedding [Road 07-N ] | 10288.28 | 100% | 100% | 10288.28
JDH4-02-007-CN-4160 | JDH4-02-007-CN-4160 | Installation of HDPE Pipe [Road 07-N ] | 102882.58 | 100% | 100% | 102882.58
JDH4-02-007-CN-4230 | JDH4-02-007-CN-4230 | Initial Pressure Test [Road 07-N ] | 41153.01 | 100% | 100% | 41153.01
JDH4-02-007-CN-4370 | JDH4-02-007-CN-4370 | Backfilling & Compaction [Road 07-N ] | 20576.51 | 100% | 100% | 20576.51
JDH4-02-007-CN-4300 | JDH4-02-007-CN-4300 | Sand Cover & Warning [Road 07-N ] | 10288.28 | 100% | 100% | 10288.28
JDH4-02-007-CN-4680 | JDH4-02-007-CN-4680 | Point of Connection [Road 07-N ] | 8311.08 | 100% | 100% | 8311.08
Pipe Encasement | Pipe Encasement |  | 9821.37 |  | 100% | 9821.37
JDH4-02-007-CN-4440 | JDH4-02-007-CN-4440 | Encasement for Pipes [Road 07-N ] | 9821.37 | 100% | 100% | 9821.37
Valves | Valves |  | 7469.42 |  | 100% | 7469.42
JDH4-02-007-CN-4510 | JDH4-02-007-CN-4510 | Installation of Gate Valves [Road 07-N ] | 7469.42 | 100% | 100% | 7469.42
Risers | Risers |  | 13245.78 |  | 100% | 13245.78
JDH4-02-007-CN-4750 | JDH4-02-007-CN-4750 | Installation of Irrigation Riser with [Road 07-N ] | 13245.78 | 100% | 100% | 13245.78
Potable Network | Potable Network |  | 167864.18 |  | 100% | 167864.18
Pipe Works | Pipe Works |  | 98143.31 |  | 100% | 98143.31
JDH4-02-007-CN-3340 | JDH4-02-007-CN-3340 | Excavation and Compaction (FDT) [Road 07-N ] | 9814.34 | 100% | 100% | 9814.34
JDH4-02-007-CN-3410 | JDH4-02-007-CN-3410 | Sand Bedding [Road 07-N ] | 4907.17 | 100% | 100% | 4907.17
JDH4-02-007-CN-3480 | JDH4-02-007-CN-3480 | Installation of HDPE Pipe [Road 07-N ] | 49071.64 | 100% | 100% | 49071.64
JDH4-02-007-CN-3550 | JDH4-02-007-CN-3550 | Initial Pressure Test [Road 07-N ] | 19628.65 | 100% | 100% | 19628.65
JDH4-02-007-CN-3620 | JDH4-02-007-CN-3620 | Sand Cover & Warning Tape [Road 07-N ] | 4907.17 | 100% | 100% | 4907.17
JDH4-02-007-CN-3690 | JDH4-02-007-CN-3690 | Backfilling [Road 07-N ] | 9814.34 | 100% | 100% | 9814.34
Pipe Encasement | Pipe Encasement |  | 7696.98 |  | 100% | 7696.98
JDH4-02-007-CN-3760 | JDH4-02-007-CN-3760 | Encasement for Pipes [Road 07-N ] | 7696.98 | 100% | 100% | 7696.98
Valves | Valves |  | 5256.26 |  | 100% | 5256.26
JDH4-02-007-CN-3830 | JDH4-02-007-CN-3830 | Installation of Gate Valves [Road 07-N ] | 5256.26 | 100% | 100% | 5256.26
Fire Hydrant | Fire Hydrant |  | 56767.63 |  | 100% | 56767.63
JDH4-02-007-CN-3920 | JDH4-02-007-CN-3920 | Installation of 3-outlet fire hydrant [Road 07-N ] | 56767.63 | 100% | 100% | 56767.63
Electrical Works | Electrical Works |  | 553863.1 |  | 100% | 553863.1
LV Cables | LV Cables |  | 35076.36 |  | 100% | 35076.36
Low Voltage Cable | Low Voltage Cable |  | 35076.36 |  | 100% | 35076.36
JDH4-02-007-CN-2630 | JDH4-02-007-CN-2630 | Excavation for Low Voltage Cable [Road 07-N ] | 9385.58 | 100% | 100% | 9385.58
JDH4-02-007-CN-2640 | JDH4-02-007-CN-2640 | Installation of Low Voltage Cables [Road 07-N ] | 25690.78 | 100% | 100% | 25690.78
Street Lighting | Street Lighting |  | 267583.69 |  | 100% | 267583.69
JDH4-02-007-CN-2790 | JDH4-02-007-CN-2790 | Installation of Road Crossing Ducts [Road 07-N ] | 17204.29 | 100% | 100% | 17204.29
JDH4-02-007-CN-2940 | JDH4-02-007-CN-2940 | Installation of Lighting Luminaires [Road 07-N ] | 22897.48 | 100% | 100% | 22897.48
JDH4-02-007-CN-2900 | JDH4-02-007-CN-2900 | Installation of Lighting Poles [Road 07-N ] | 96197.32 | 100% | 100% | 96197.32
JDH4-02-007-CN-2780 | JDH4-02-007-CN-2780 | Excavation for Low Voltage Cable [Road 07-N ] | 17282.59 | 100% | 100% | 17282.59
JDH4-02-007-CN-2860 | JDH4-02-007-CN-2860 | Installation of Low Voltage Cables [Road 07-N ] | 88141.2 | 100% | 100% | 88141.2
JDH4-02-007-CN-3000 | JDH4-02-007-CN-3000 | Installation of Street Lighting Feeder pillars [Road 07-N ] | 22076.3 | 100% | 100% | 22076.3
JDH4-02-007-CN-3010 | JDH4-02-007-CN-3010 | Installation of Earthing System [Road 07-N ] | 3784.51 | 100% | 100% | 3784.51
Telecommunication | Telecommunication |  | 251203.05 |  | 100% | 251203.05
JDH4-02-007-CN-3090 | JDH4-02-007-CN-3090 | Installation Road Crossing R/F 6 way 50mm HDPE Pipe [Road 07-N ] | 145325.12 | 100% | 100% | 145325.12
JDH4-02-007-CN-3160 | JDH4-02-007-CN-3160 | Installation Road Crossing Un R/F 6 way 50mm HDPE Pipe [Road 07-N ] | 3973.73 | 100% | 100% | 3973.73
JDH4-02-007-CN-3270 | JDH4-02-007-CN-3270 | Installation of Manholes [Road 07-N ] | 39737.34 | 100% | 100% | 39737.34
JDH4-02-007-CN-3210 | JDH4-02-007-CN-3210 | Installation of 2 x 32 mm diameter HDPE ducts [Road 07-N ] | 62166.86 | 100% | 100% | 62166.86
Road 01 | Road 01 |  | 3400633.43 |  | 92.5% | 3145720.02
Road Works (Roundabout) | Road Works (Roundabout) |  | 826699 |  | 69.16% | 571785.59
Eartworks & Site grading | Eartworks & Site grading |  | 357790.57 |  | 100% | 357790.57
JDH4-02-007-CN-1720 | JDH4-02-007-CN-1720 | Road excavation [Road 01 ] | 8053.45 | 100% | 100% | 8053.45
JDH4-02-007-CN-1780 | JDH4-02-007-CN-1780 | Road backfilling [Road 01 ] | 317788.32 | 100% | 100% | 317788.32
JDH4-02-007-CN-1900 | JDH4-02-007-CN-1900 | Subgrade [Road 01 ] | 31948.8 | 100% | 100% | 31948.8
Asphalt Works | Asphalt Works |  | 213995.02 |  | 100% | 213995.02
JDH4-02-007-CN-1960 | JDH4-02-007-CN-1960 | Aggregate base course [Road 01 ] | 32540.46 | 100% | 100% | 32540.46
JDH4-02-007-CN-2010 | JDH4-02-007-CN-2010 | Prime Coat (MC1) [Road 01 ] | 17989.03 | 100% | 100% | 17989.03
JDH4-02-007-CN-2060 | JDH4-02-007-CN-2060 | Bituminous base course [Road 01 ] | 163465.53 | 100% | 100% | 163465.53
Finishing Works | Finishing Works |  | 254913.41 |  | 0% | 0
Asphalt Wearing Course | Asphalt Wearing Course |  | 95937.28 |  | 0% | 0
JDH4-02-007-CN-2110 | JDH4-02-007-CN-2110 | Tack Coat (RC2) [Road 01 ] | 9429.73 | 0% | 0% | 0
JDH4-02-007-CN-2160 | JDH4-02-007-CN-2160 | Bituminous concrete wearing course [Road 01 ] | 86507.55 | 0% | 0% | 0
Precast Concrete Curb | Precast Concrete Curb |  | 59926.12 |  | 0% | 0
JDH4-02-007-CN-2210 | JDH4-02-007-CN-2210 | Installation of Precast Concrete curb [Road 01 ] | 59926.12 | 0% | 0% | 0
Precast Interlocking block pavers | Precast Interlocking block pavers |  | 57004.16 |  | 0% | 0
JDH4-02-007-CN-2260 | JDH4-02-007-CN-2260 | Installation of Interlocking block pavers for sidewalk/footpath [Road 01 ] | 57004.16 | 0% | 0% | 0
Pavement Markings | Pavement Markings |  | 16149.78 |  | 0% | 0
JDH4-02-007-CN-2310 | JDH4-02-007-CN-2310 | Pavement markings [Road 01 ] | 16149.78 | 0% | 0% | 0
Traffic Signage | Traffic Signage |  | 25896.07 |  | 0% | 0
JDH4-02-007-CN-2360 | JDH4-02-007-CN-2360 | Installation of Traffic Signs [Road 01 ] | 25896.07 | 0% | 0% | 0
Storm Water Drainage | Storm Water Drainage |  | 131305.17 |  | 100% | 131305.17
Pipe Works | Pipe Works |  | 26247.15 |  | 100% | 26247.15
JDH4-02-007-CN-5340 | JDH4-02-007-CN-5340 | Excavation and Compaction (FDT) [Road 01 ] | 2624.71 | 100% | 100% | 2624.71
JDH4-02-007-CN-5390 | JDH4-02-007-CN-5390 | Sand Bedding [Road 01 ] | 1312.36 | 100% | 100% | 1312.36
JDH4-02-007-CN-5440 | JDH4-02-007-CN-5440 | Installation of GRP Pipe [Road 01 ] | 18373.01 | 100% | 100% | 18373.01
JDH4-02-007-CN-5490 | JDH4-02-007-CN-5490 | Sand Cover & Warning Tape [Road 01 ] | 1312.36 | 100% | 100% | 1312.36
JDH4-02-007-CN-5540 | JDH4-02-007-CN-5540 | Backfilling & Compaction [Road 01 ] | 2624.71 | 100% | 100% | 2624.71
Pipe Encasement | Pipe Encasement |  | 1307.93 |  | 100% | 1307.93
JDH4-02-007-CN-5810 | JDH4-02-007-CN-5810 | Pipe Encasement Works [Road 01 ] | 1307.93 | 100% | 100% | 1307.93
Manholes | Manholes |  | 74735.52 |  | 100% | 74735.52
JDH4-02-007-CN-5640 | JDH4-02-007-CN-5640 | Installation of Precast Manhole Ring [Road 01 ] | 74735.52 | 100% | 100% | 74735.52
Precast Acces Openinig | Precast Acces Openinig |  | 3784.51 |  | 100% | 3784.51
JDH4-02-007-CN-5690 | JDH4-02-007-CN-5690 | Installation of Precast Access Opening [Road 01 ] | 3784.51 | 100% | 100% | 3784.51
Concrete Outfalls | Concrete Outfalls |  | 25230.06 |  | 100% | 25230.06
JDH4-02-007-CN-5780 | JDH4-02-007-CN-5780 | Construction of Concrete outfall structure [Road 01 ] | 25230.06 | 100% | 100% | 25230.06
Sewerage Network | Sewerage Network |  | 134037.33 |  | 100% | 134037.33
Pipe Works | Pipe Works |  | 52628.99 |  | 100% | 52628.99
JDH4-02-007-CN-4790 | JDH4-02-007-CN-4790 | Excavation & Compaction (FDT) [Road 01 ] | 5262.9 | 100% | 100% | 5262.9
JDH4-02-007-CN-4860 | JDH4-02-007-CN-4860 | Sand Bedding [Road 01 ] | 2631.45 | 100% | 100% | 2631.45
JDH4-02-007-CN-4930 | JDH4-02-007-CN-4930 | Installation of GRP Pipe [Road 01 ] | 26314.49 | 100% | 100% | 26314.49
JDH4-02-007-CN-5000 | JDH4-02-007-CN-5000 | Gravity Test [Road 01 ] | 10525.8 | 100% | 100% | 10525.8
JDH4-02-007-CN-5070 | JDH4-02-007-CN-5070 | Sand Cover & Warning Tape [Road 01 ] | 2631.45 | 100% | 100% | 2631.45
JDH4-02-007-CN-5140 | JDH4-02-007-CN-5140 | Backfilling & Compaction [Road 01 ] | 5262.9 | 100% | 100% | 5262.9
Pipe Encasement | Pipe Encasement |  | 304.22 |  | 100% | 304.22
JDH4-02-007-CN-5280 | JDH4-02-007-CN-5280 | Pipe Encasement Works [Road 01 ] | 304.22 | 100% | 100% | 304.22
Manholes | Manholes |  | 81104.12 |  | 100% | 81104.12
JDH4-02-007-CN-5210 | JDH4-02-007-CN-5210 | Installation of Manholes [Road 01 ] | 81104.12 | 100% | 100% | 81104.12
TSE Network | TSE Network |  | 315346.48 |  | 100% | 315346.48
Pipe Works | Pipe Works |  | 199841.72 |  | 100% | 199841.72
JDH4-02-007-CN-4010 | JDH4-02-007-CN-4010 | Excavation and Compaction (FDT) [Road 01 ](Completed) | 4579.9 | 100% | 100% | 4579.9
JDH4-02-007-CN-4150 | JDH4-02-007-CN-4150 | Installation of HDPE Pipe [Road 01 ](Completed) | 22899.5 | 100% | 100% | 22899.5
JDH4-02-007-CN-4080 | JDH4-02-007-CN-4080 | Sand Bedding [Road 01 ](Completed) | 2289.96 | 100% | 100% | 2289.96
JDH4-02-007-CN-4290 | JDH4-02-007-CN-4290 | Sand Cover & Warning [Road 01 ](Completed) | 2106.76 | 100% | 100% | 2106.76
JDH4-02-007-CN-4010R | JDH4-02-007-CN-4010R | Excavation and Compaction (FDT) [Road 01 ] | 13739.69 | 100% | 100% | 13739.69
JDH4-02-007-CN-4080R | JDH4-02-007-CN-4080R | Sand Bedding [Road 01 ] | 6869.87 | 100% | 100% | 6869.87
JDH4-02-007-CN-4150R | JDH4-02-007-CN-4150R | Installation of HDPE Pipe [Road 01 ] | 68698.5 | 100% | 100% | 68698.5
JDH4-02-007-CN-4220 | JDH4-02-007-CN-4220 | Initial Pressure Test [Road 01 ] | 36654.89 | 100% | 100% | 36654.89
JDH4-02-007-CN-4360 | JDH4-02-007-CN-4360 | Backfilling & Compaction [Road 01 ] | 18327.45 | 100% | 100% | 18327.45
JDH4-02-007-CN-4290R | JDH4-02-007-CN-4290R | Sand Cover & Warning [Road 01 ] | 7053.06 | 100% | 100% | 7053.06
JDH4-02-007-CN-4670 | JDH4-02-007-CN-4670 | Point of Connection [Road 01 ] | 16622.15 | 100% | 100% | 16622.15
Pipe Encasement | Pipe Encasement |  | 9065.88 |  | 100% | 9065.88
JDH4-02-007-CN-4430 | JDH4-02-007-CN-4430 | Encasement for Pipes [Road 01 ] | 9065.88 | 100% | 100% | 9065.88
Valves | Valves |  | 93193.1 |  | 100% | 93193.1
JDH4-02-007-CN-4500 | JDH4-02-007-CN-4500 | Installation of Gate Valves [Road 01 ] | 11204.14 | 100% | 100% | 11204.14
JDH4-02-007-CN-4550 | JDH4-02-007-CN-4550 | Installation of Butterfly Valves [Road 01 ] | 44152.6 | 100% | 100% | 44152.6
JDH4-02-007-CN-4560 | JDH4-02-007-CN-4560 | Installation of Washout Valves [Road 01 ] | 23329.08 | 100% | 100% | 23329.08
JDH4-02-007-CN-4580 | JDH4-02-007-CN-4580 | Installation of Air Valves [Road 01 ] | 14507.28 | 100% | 100% | 14507.28
Risers | Risers |  | 13245.78 |  | 100% | 13245.78
JDH4-02-007-CN-4740 | JDH4-02-007-CN-4740 | Installation of Irrigation Riser with [Road 01 ] | 13245.78 | 100% | 100% | 13245.78
Potable Network | Potable Network |  | 1242732.96 |  | 100% | 1242732.96
Pipe Works | Pipe Works |  | 176873.66 |  | 100% | 176873.66
JDH4-02-007-CN-3330 | JDH4-02-007-CN-3330 | Excavation and Compaction (FDT) [Road 01 ] | 17687.38 | 100% | 100% | 17687.38
JDH4-02-007-CN-3470 | JDH4-02-007-CN-3470 | Installation of HDPE Pipe [Road 01 ] | 88436.81 | 100% | 100% | 88436.81
JDH4-02-007-CN-3540 | JDH4-02-007-CN-3540 | Initial Pressure Test [Road 01 ] | 35374.71 | 100% | 100% | 35374.71
JDH4-02-007-CN-3610 | JDH4-02-007-CN-3610 | Sand Cover & Warning Tape [Road 01 ] | 8843.69 | 100% | 100% | 8843.69
JDH4-02-007-CN-3680 | JDH4-02-007-CN-3680 | Backfilling [Road 01 ] | 17687.38 | 100% | 100% | 17687.38
JDH4-02-007-CN-3400 | JDH4-02-007-CN-3400 | Sand Bedding [Road 01 ] | 8843.69 | 100% | 100% | 8843.69
Pipe Encasement | Pipe Encasement |  | 13294.79 |  | 100% | 13294.79
JDH4-02-007-CN-3750 | JDH4-02-007-CN-3750 | Encasement for Pipes [Road 01 ] | 13294.79 | 100% | 100% | 13294.79
Valves | Valves |  | 141183.18 |  | 100% | 141183.18
JDH4-02-007-CN-3820 | JDH4-02-007-CN-3820 | Installation of Gate Valves [Road 01 ] | 13140.65 | 100% | 100% | 13140.65
JDH4-02-007-CN-3870 | JDH4-02-007-CN-3870 | Installation of Butterfly valves [Road 01 ] | 37845.08 | 100% | 100% | 37845.08
JDH4-02-007-CN-3880 | JDH4-02-007-CN-3880 | Installation of Washout valves [Road 01 ] | 29645.31 | 100% | 100% | 29645.31
JDH4-02-007-CN-3890 | JDH4-02-007-CN-3890 | Installation of Air valves [Road 01 ] | 60552.14 | 100% | 100% | 60552.14
Fire Hydrant | Fire Hydrant |  | 75690.17 |  | 100% | 75690.17
JDH4-02-007-CN-3910 | JDH4-02-007-CN-3910 | Installation of 3-outlet fire hydrant [Road 01 ] | 75690.17 | 100% | 100% | 75690.17
Valve Chambers | Valve Chambers |  | 829383.65 |  | 100% | 829383.65
JDH4-02-007-CN-3950 | JDH4-02-007-CN-3950 | Construction of Valve Chambers [Road 01 ] | 104035.14 | 100% | 100% | 104035.14
JDH4-02-007-CN-3960 | JDH4-02-007-CN-3960 | Construction of Wash out Chambers [Road 01 ] | 261848.64 | 100% | 100% | 261848.64
JDH4-02-007-CN-3970 | JDH4-02-007-CN-3970 | Construction of Air Valve Chambers [Road 01 ] | 274274.46 | 100% | 100% | 274274.46
JDH4-02-007-CN-4600 | JDH4-02-007-CN-4600 | Construction of Valve Chambers [Road 01 ] | 75690.16 | 100% | 100% | 75690.16
JDH4-02-007-CN-4630 | JDH4-02-007-CN-4630 | Construction of Air Valve Chambers [Road 01 ] | 75690.17 | 100% | 100% | 75690.17
JDH4-02-007-CN-4610 | JDH4-02-007-CN-4610 | Construction of Wash Out Valve Chambers [Road 01 ] | 37845.08 | 100% | 100% | 37845.08
Road Crossings | Road Crossings |  | 6307.51 |  | 100% | 6307.51
JDH4-02-007-CN-3980 | JDH4-02-007-CN-3980 | Installation of HDPE road croosing [Road 01 ] | 6307.51 | 100% | 100% | 6307.51
Electrical Works | Electrical Works |  | 360707.74 |  | 100% | 360707.74
LV Cables | LV Cables |  | 71867.75 |  | 100% | 71867.75
Low Voltage Cable | Low Voltage Cable |  | 71867.75 |  | 100% | 71867.75
JDH4-02-007-CN-2610 | JDH4-02-007-CN-2610 | Excavation for Low Voltage Cable [Road 01 ] | 19225.3 | 100% | 100% | 19225.3
JDH4-02-007-CN-2620 | JDH4-02-007-CN-2620 | Installation of Low Voltage Cables [Road 01 ] | 52642.45 | 100% | 100% | 52642.45
Street Lighting | Street Lighting |  | 20045.28 |  | 100% | 20045.28
JDH4-02-007-CN-2770 | JDH4-02-007-CN-2770 | Excavation for Low Voltage Cable [Road 01 ] | 3279.91 | 100% | 100% | 3279.91
JDH4-02-007-CN-2850 | JDH4-02-007-CN-2850 | Installation of Low Voltage Cables [Road 01 ] | 16765.37 | 100% | 100% | 16765.37
Telecommunication | Telecommunication |  | 268794.71 |  | 100% | 268794.71
JDH4-02-007-CN-3150 | JDH4-02-007-CN-3150 | Installation Road Crossing Un R/F 6 way 50mm HDPE Pipe [Road 01 ] | 5392.92 | 100% | 100% | 5392.92
JDH4-02-007-CN-3260 | JDH4-02-007-CN-3260 | Installation of Manholes [Road 01 ] | 56767.63 | 100% | 100% | 56767.63
JDH4-02-007-CN-3080 | JDH4-02-007-CN-3080 | Installation Road Crossing R/F 6 way 50mm HDPE Pipe [Road 01 ] | 206634.16 | 100% | 100% | 206634.16
Open Drain Channel | Open Drain Channel |  | 389804.76 |  | 100% | 389804.76
JDH4-02-007-CN-5850 | JDH4-02-007-CN-5850 | Channel excavation [Road 01 ](Completed) | 65850.6 | 100% | 100% | 65850.6
JDH4-02-007-CN-5860 | JDH4-02-007-CN-5860 | Backfill of the existing channel [Road 01 ](Completed) | 30276.07 | 100% | 100% | 30276.07
JDH4-02-007-CN-5870 | JDH4-02-007-CN-5870 | Compaction [Road 01 ] | 18922.54 | 100% | 100% | 18922.54
JDH4-02-007-CN-5850R | JDH4-02-007-CN-5850R | Channel excavation [Road 01 ] | 98775.9 | 100% | 100% | 98775.9
JDH4-02-007-CN-5860R | JDH4-02-007-CN-5860R | Backfill of the existing channel [Road 01 ] | 20184.04 | 100% | 100% | 20184.04
JDH4-02-007-CN-5880 | JDH4-02-007-CN-5880 | Finished grouted riprap for side ditches [Road 01 ] | 155795.6 | 100% | 100% | 155795.6
Road 02 | Road 02 |  | 658204 |  | 100% | 658204
Under Pass | Under Pass |  | 112526.05 |  | 100% | 112526.05
JDH4-02-007-CN-1940 | JDH4-02-007-CN-1940 | Compacted structural backfill for closing the underpass [Road 02 ] | 16651.84 | 100% | 100% | 16651.84
JDH4-02-007-CN-2410 | JDH4-02-007-CN-2410 | RC wall and the foundation at face of underpass [Road 02 ] | 95874.21 | 100% | 100% | 95874.21
Sewerage Network | Sewerage Network |  | 89801.58 |  | 100% | 89801.58
Pipe Works | Pipe Works |  | 57055.71 |  | 100% | 57055.71
JDH4-02-007-CN-4770 | JDH4-02-007-CN-4770 | Excavation & Compaction (FDT) [Road 02 ] | 5705.57 | 100% | 100% | 5705.57
JDH4-02-007-CN-5050 | JDH4-02-007-CN-5050 | Sand Cover & Warning Tape [Road 02 ] | 2852.78 | 100% | 100% | 2852.78
JDH4-02-007-CN-4840 | JDH4-02-007-CN-4840 | Sand Bedding [Road 02 ] | 2852.78 | 100% | 100% | 2852.78
JDH4-02-007-CN-4910 | JDH4-02-007-CN-4910 | Installation of GRP Pipe [Road 02 ] | 28527.86 | 100% | 100% | 28527.86
JDH4-02-007-CN-4980 | JDH4-02-007-CN-4980 | Gravity Test [Road 02 ] | 11411.15 | 100% | 100% | 11411.15
JDH4-02-007-CN-5120 | JDH4-02-007-CN-5120 | Backfilling & Compaction [Road 02 ] | 5705.57 | 100% | 100% | 5705.57
Pipe Encasement | Pipe Encasement |  | 304.22 |  | 100% | 304.22
JDH4-02-007-CN-5260 | JDH4-02-007-CN-5260 | Pipe Encasement Works [Road 02 ] | 304.22 | 100% | 100% | 304.22
Manholes | Manholes |  | 32441.65 |  | 100% | 32441.65
JDH4-02-007-CN-5190 | JDH4-02-007-CN-5190 | Installation of Manholes [Road 02 ] | 32441.65 | 100% | 100% | 32441.65
TSE Network | TSE Network |  | 145569.49 |  | 100% | 145569.49
Pipe Works | Pipe Works |  | 112992.76 |  | 100% | 112992.76
JDH4-02-007-CN-3990 | JDH4-02-007-CN-3990 | Excavation and Compaction (FDT) [Road 02 ](Completed) | 5754.78 | 100% | 100% | 5754.78
JDH4-02-007-CN-4060 | JDH4-02-007-CN-4060 | Sand Bedding [Road 02 ](Completed) | 2877.4 | 100% | 100% | 2877.4
JDH4-02-007-CN-4130 | JDH4-02-007-CN-4130 | Installation of HDPE Pipe [Road 02 ](Completed) | 23542.29 | 100% | 100% | 23542.29
JDH4-02-007-CN-4270 | JDH4-02-007-CN-4270 | Sand Cover & Warning [Road 02 ](Completed) | 2354.23 | 100% | 100% | 2354.23
JDH4-02-007-CN-3990R | JDH4-02-007-CN-3990R | Excavation and Compaction (FDT) [Road 02 ] | 4708.46 | 100% | 100% | 4708.46
JDH4-02-007-CN-4060R | JDH4-02-007-CN-4060R | Sand Bedding [Road 02 ] | 2354.23 | 100% | 100% | 2354.23
JDH4-02-007-CN-4130R | JDH4-02-007-CN-4130R | Installation of HDPE Pipe [Road 02 ] | 28773.91 | 100% | 100% | 28773.91
JDH4-02-007-CN-4200 | JDH4-02-007-CN-4200 | Initial Pressure Test [Road 02 ] | 20959.32 | 100% | 100% | 20959.32
JDH4-02-007-CN-4270R | JDH4-02-007-CN-4270R | Sand Cover & Warning [Road 02 ] | 2877.4 | 100% | 100% | 2877.4
JDH4-02-007-CN-4340 | JDH4-02-007-CN-4340 | Backfilling & Compaction [Road 02 ] | 10479.66 | 100% | 100% | 10479.66
JDH4-02-007-CN-4650 | JDH4-02-007-CN-4650 | Point of Connection [Road 02 ] | 8311.08 | 100% | 100% | 8311.08
Pipe Encasement | Pipe Encasement |  | 5288.43 |  | 100% | 5288.43
JDH4-02-007-CN-4410 | JDH4-02-007-CN-4410 | Encasement for Pipes [Road 02 ] | 5288.43 | 100% | 100% | 5288.43
Valves | Valves |  | 18457.78 |  | 100% | 18457.78
JDH4-02-007-CN-4480 | JDH4-02-007-CN-4480 | Installation of Gate Valves [Road 02 ] | 11204.14 | 100% | 100% | 11204.14
JDH4-02-007-CN-4570 | JDH4-02-007-CN-4570 | Installation of Air Valves [Road 02 ] | 7253.64 | 100% | 100% | 7253.64
Risers | Risers |  | 8830.52 |  | 100% | 8830.52
JDH4-02-007-CN-4720 | JDH4-02-007-CN-4720 | Installation of Irrigation Riser with [Road 02 ] | 8830.52 | 100% | 100% | 8830.52
Potable Network | Potable Network |  | 139057.87 |  | 100% | 139057.87
Pipe Works | Pipe Works |  | 84122.85 |  | 100% | 84122.85
JDH4-02-007-CN-3310 | JDH4-02-007-CN-3310 | Excavation and Compaction (FDT) [Road 02 ] | 8412.29 | 100% | 100% | 8412.29
JDH4-02-007-CN-3380 | JDH4-02-007-CN-3380 | Sand Bedding [Road 02 ] | 4206.15 | 100% | 100% | 4206.15
JDH4-02-007-CN-3450 | JDH4-02-007-CN-3450 | Installation of HDPE Pipe [Road 02 ] | 42061.41 | 100% | 100% | 42061.41
JDH4-02-007-CN-3520 | JDH4-02-007-CN-3520 | Initial Pressure Test [Road 02 ] | 16824.56 | 100% | 100% | 16824.56
JDH4-02-007-CN-3590 | JDH4-02-007-CN-3590 | Sand Cover & Warning Tape [Road 02 ] | 4206.15 | 100% | 100% | 4206.15
JDH4-02-007-CN-3660 | JDH4-02-007-CN-3660 | Backfilling [Road 02 ] | 8412.29 | 100% | 100% | 8412.29
Pipe Encasement | Pipe Encasement |  | 6577.42 |  | 100% | 6577.42
JDH4-02-007-CN-3730 | JDH4-02-007-CN-3730 | Encasement for Pipes [Road 02 ] | 6577.42 | 100% | 100% | 6577.42
Valves | Valves |  | 10512.52 |  | 100% | 10512.52
JDH4-02-007-CN-3800 | JDH4-02-007-CN-3800 | Installation of Gate Valves [Road 02 ] | 10512.52 | 100% | 100% | 10512.52
Valve Chambers | Valve Chambers |  | 37845.08 |  | 100% | 37845.08
JDH4-02-007-CN-4620 | JDH4-02-007-CN-4620 | Construction of Air Valve Chambers [Road 02 ] | 37845.08 | 100% | 100% | 37845.08
Electrical Works | Electrical Works |  | 171249.01 |  | 100% | 171249.01
Telecommunication | Telecommunication |  | 171249.01 |  | 100% | 171249.01
JDH4-02-007-CN-3130 | JDH4-02-007-CN-3130 | Installation Road Crossing Un R/F 6 way 50mm HDPE Pipe [Road 02 ] | 3973.73 | 100% | 100% | 3973.73
JDH4-02-007-CN-3240 | JDH4-02-007-CN-3240 | Installation of Manholes [Road 02 ] | 34060.58 | 100% | 100% | 34060.58
JDH4-02-007-CN-3060 | JDH4-02-007-CN-3060 | Installation Road Crossing R/F 6 way 50mm HDPE Pipe [Road 02 ] | 133214.7 | 100% | 100% | 133214.7
Road 10 | Road 10 |  | 908137.39 |  | 95.97% | 871503.61
Sewerage Network | Sewerage Network |  | 419517.38 |  | 100% | 419517.38
Pipe Works | Pipe Works |  | 288229.72 |  | 100% | 288229.72
JDH4-02-007-CN-4830 | JDH4-02-007-CN-4830 | Excavation & Compaction (FDT) [Road 10 ] | 28822.98 | 100% | 100% | 28822.98
JDH4-02-007-CN-4900 | JDH4-02-007-CN-4900 | Sand Bedding [Road 10 ] | 14411.47 | 100% | 100% | 14411.47
JDH4-02-007-CN-4970 | JDH4-02-007-CN-4970 | Installation of GRP Pipe [Road 10 ] | 144114.86 | 100% | 100% | 144114.86
JDH4-02-007-CN-5040 | JDH4-02-007-CN-5040 | Gravity Test [Road 10 ] | 57645.96 | 100% | 100% | 57645.96
JDH4-02-007-CN-5110 | JDH4-02-007-CN-5110 | Sand Cover & Warning Tape [Road 10 ] | 14411.47 | 100% | 100% | 14411.47
JDH4-02-007-CN-5180 | JDH4-02-007-CN-5180 | Backfilling & Compaction [Road 10 ] | 28822.98 | 100% | 100% | 28822.98
Pipe Encasement | Pipe Encasement |  | 1521.08 |  | 100% | 1521.08
JDH4-02-007-CN-5320 | JDH4-02-007-CN-5320 | Pipe Encasement Works [Road 10 ] | 1521.08 | 100% | 100% | 1521.08
Manholes | Manholes |  | 129766.58 |  | 100% | 129766.58
JDH4-02-007-CN-5250 | JDH4-02-007-CN-5250 | Installation of Manholes [Road 10 ] | 129766.58 | 100% | 100% | 129766.58
TSE Network | TSE Network |  | 221839.87 |  | 100% | 221839.87
Pipe Works | Pipe Works |  | 201483.45 |  | 100% | 201483.45
JDH4-02-007-CN-4050 | JDH4-02-007-CN-4050 | Excavation and Compaction (FDT) [Road 10 ] | 18901.67 | 100% | 100% | 18901.67
JDH4-02-007-CN-4120 | JDH4-02-007-CN-4120 | Sand Bedding [Road 10 ] | 9450.86 | 100% | 100% | 9450.86
JDH4-02-007-CN-4190 | JDH4-02-007-CN-4190 | Installation of HDPE Pipe [Road 10 ] | 94508.42 | 100% | 100% | 94508.42
JDH4-02-007-CN-4260 | JDH4-02-007-CN-4260 | Initial Pressure Test [Road 10 ] | 37803.35 | 100% | 100% | 37803.35
JDH4-02-007-CN-4710 | JDH4-02-007-CN-4710 | Point of Connection [Road 10 ] | 12466.62 | 100% | 100% | 12466.62
JDH4-02-007-CN-4330 | JDH4-02-007-CN-4330 | Sand Cover & Warning [Road 10 ] | 9450.86 | 100% | 100% | 9450.86
JDH4-02-007-CN-4400 | JDH4-02-007-CN-4400 | Backfilling & Compaction [Road 10 ] | 18901.67 | 100% | 100% | 18901.67
Pipe Encasement | Pipe Encasement |  | 9368.07 |  | 100% | 9368.07
JDH4-02-007-CN-4470 | JDH4-02-007-CN-4470 | Encasement for Pipes [Road 10 ] | 9368.07 | 100% | 100% | 9368.07
Valves | Valves |  | 10988.35 |  | 100% | 10988.35
JDH4-02-007-CN-4540 | JDH4-02-007-CN-4540 | Installation of Gate Valves [Road 10 ] | 3734.71 | 100% | 100% | 3734.71
JDH4-02-007-CN-4590 | JDH4-02-007-CN-4590 | Installation of Air Valves [Road 10 ] | 7253.64 | 100% | 100% | 7253.64
Potable Network | Potable Network |  | 62644.01 |  | 100% | 62644.01
Pipe Works | Pipe Works |  | 20491.46 |  | 100% | 20491.46
JDH4-02-007-CN-3370 | JDH4-02-007-CN-3370 | Excavation and Compaction (FDT) [Road 10 ] | 2049.15 | 100% | 100% | 2049.15
JDH4-02-007-CN-3440 | JDH4-02-007-CN-3440 | Sand Bedding [Road 10 ] | 1024.57 | 100% | 100% | 1024.57
JDH4-02-007-CN-3510 | JDH4-02-007-CN-3510 | Installation of HDPE Pipe [Road 10 ] | 10245.73 | 100% | 100% | 10245.73
JDH4-02-007-CN-3580 | JDH4-02-007-CN-3580 | Initial Pressure Test [Road 10 ] | 4098.29 | 100% | 100% | 4098.29
JDH4-02-007-CN-3650 | JDH4-02-007-CN-3650 | Sand Cover & Warning Tape [Road 10 ] | 1024.57 | 100% | 100% | 1024.57
JDH4-02-007-CN-3720 | JDH4-02-007-CN-3720 | Backfilling [Road 10 ] | 2049.15 | 100% | 100% | 2049.15
Pipe Encasement | Pipe Encasement |  | 1679.34 |  | 100% | 1679.34
JDH4-02-007-CN-3790 | JDH4-02-007-CN-3790 | Encasement for Pipes [Road 10 ] | 1679.34 | 100% | 100% | 1679.34
Valves | Valves |  | 2628.13 |  | 100% | 2628.13
JDH4-02-007-CN-3860 | JDH4-02-007-CN-3860 | Installation of Gate Valves [Road 10 ] | 2628.13 | 100% | 100% | 2628.13
Valve Chambers | Valve Chambers |  | 37845.08 |  | 100% | 37845.08
JDH4-02-007-CN-4640 | JDH4-02-007-CN-4640 | Construction of Air Valve Chambers [Road 10 ] | 37845.08 | 100% | 100% | 37845.08
Electrical Works | Electrical Works |  | 204136.13 |  | 82.05% | 167502.35
MV & LV Cables | MV & LV Cables |  | 36633.78 |  | 0% | 0
Low Voltage Cable | Low Voltage Cable |  | 36633.78 |  | 0% | 0
JDH4-02-007-CN-2670 | JDH4-02-007-CN-2670 | Excavation for Low Voltage Cable [Road 10 ] | 9839.72 | 0% | 0% | 0
JDH4-02-007-CN-2680 | JDH4-02-007-CN-2680 | Installation of Low Voltage Cables [Road 10 ] | 26794.06 | 0% | 0% | 0
Telecommunication | Telecommunication |  | 167502.35 |  | 100% | 167502.35
JDH4-02-007-CN-3120 | JDH4-02-007-CN-3120 | Installation Road Crossing R/F 6 way 50mm HDPE Pipe [Road 10 ] | 76068.62 | 100% | 100% | 76068.62
JDH4-02-007-CN-3190 | JDH4-02-007-CN-3190 | Installation Road Crossing Un R/F 6 way 50mm HDPE Pipe [Road 10 ] | 3406.06 | 100% | 100% | 3406.06
JDH4-02-007-CN-3230 | JDH4-02-007-CN-3230 | Installation of 2 x 32 mm diameter HDPE ducts [Road 10 ] | 70997.38 | 100% | 100% | 70997.38
JDH4-02-007-CN-3300 | JDH4-02-007-CN-3300 | Installation of Manholes [Road 10 ] | 17030.29 | 100% | 100% | 17030.29
Out of Zone | Out of Zone |  | 49496.57 |  | 100% | 49496.57
Electrical Works | Electrical Works |  | 49496.57 |  | 100% | 49496.57
LV Cables | LV Cables |  | 49496.57 |  | 100% | 49496.57
Low Voltage Cable | Low Voltage Cable |  | 49496.57 |  | 100% | 49496.57
JDH4-02-007-CN-2690 | JDH4-02-007-CN-2690 | Excavation for Low Voltage Cable [Out of Zone ] | 13245.78 | 100% | 100% | 13245.78
JDH4-02-007-CN-2700 | JDH4-02-007-CN-2700 | Installation of Low Voltage Cables [Out of Zone ] | 36250.79 | 100% | 100% | 36250.79
Sewage Lift Station | Sewage Lift Station |  | 3049343.44 |  | 39.92% | 1217218.95
Site Works | Site Works |  | 10249.72 |  | 100% | 10249.72
JDH4-02-007-CN-5910 | JDH4-02-007-CN-5910 | Excavation [Sewage Lift Station ] | 3942.2 | 100% | 100% | 3942.2
JDH4-02-007-CN-5930 | JDH4-02-007-CN-5930 | Install gravel beddings [Sewage Lift Station ] | 4730.64 | 100% | 100% | 4730.64
JDH4-02-007-CN-5920 | JDH4-02-007-CN-5920 | Backfilling [Sewage Lift Station ] | 1576.88 | 100% | 100% | 1576.88
Concrete Works | Concrete Works |  | 67679.63 |  | 100% | 67679.63
JDH4-02-007-CN-1010 | JDH4-02-007-CN-1010 | Lean concrete under the foundations [Sewage Lift Station ] | 2081.48 | 100% | 100% | 2081.48
JDH4-02-007-CN-1020 | JDH4-02-007-CN-1020 | Footings For Sewage Lift Station [Sewage Lift Station ] | 25230.06 | 100% | 100% | 25230.06
JDH4-02-007-CN-1030 | JDH4-02-007-CN-1030 | Cast concrete for trench Including Mastic sealant [Sewage Lift Station ] | 40368.09 | 100% | 100% | 40368.09
Thermal & Moisture Protection | Thermal & Moisture Protection |  | 7001.35 |  | 100% | 7001.35
JDH4-02-007-CN-1050 | JDH4-02-007-CN-1050 | Install 250 micron polyethylene sheet under slab on grade and footings [Sewage Lift Station ] | 2270.71 | 100% | 100% | 2270.71
JDH4-02-007-CN-1060 | JDH4-02-007-CN-1060 | Applying 2 Coats of Bituminous Paint [Sewage Lift Station ] | 4730.64 | 100% | 100% | 4730.64
Metals | Metals |  | 10092.02 |  | 100% | 10092.02
JDH4-02-007-CN-1040 | JDH4-02-007-CN-1040 | Install Stainless steel [Sewage Lift Station ] | 10092.02 | 100% | 100% | 10092.02
Mechanical Works | Mechanical Works |  | 1705863.69 |  | 43.26% | 737975.66
Pipes & Fittings | Pipes & Fittings |  | 256712.33 |  | 100% | 256712.33
JDH4-02-007-CN-1090 | JDH4-02-007-CN-1090 | Installation of Pipes & Fittings [Sewage Lift Station ] | 30587.94 | 100% | 100% | 30587.94
JDH4-02-007-CN-1100 | JDH4-02-007-CN-1100 | Installation of Gate Valves [Sewage Lift Station ] | 29014.56 | 100% | 100% | 29014.56
JDH4-02-007-CN-1120 | JDH4-02-007-CN-1120 | Installation of Dismantling Joints [Sewage Lift Station ] | 13876.54 | 100% | 100% | 13876.54
JDH4-02-007-CN-1130 | JDH4-02-007-CN-1130 | Installation of Non Return Valve DN250 [Sewage Lift Station ] | 9461.27 | 100% | 100% | 9461.27
JDH4-02-007-CN-1140 | JDH4-02-007-CN-1140 | Installation of Air Valve DN60 [Sewage Lift Station ] | 11353.53 | 100% | 100% | 11353.53
JDH4-02-007-CN-1160 | JDH4-02-007-CN-1160 | Installation of Odors scrubbing system [Sewage Lift Station ] | 157687.85 | 100% | 100% | 157687.85
JDH4-02-007-CN-1150 | JDH4-02-007-CN-1150 | Installation of Bauer Coupling DN150 [Sewage Lift Station ] | 4730.64 | 100% | 100% | 4730.64
Control Equipment | Control Equipment |  | 118265.89 |  | 100% | 118265.89
JDH4-02-007-CN-1200 | JDH4-02-007-CN-1200 | Installation of Screening Container [Sewage Lift Station ] | 9461.27 | 100% | 100% | 9461.27
JDH4-02-007-CN-1190 | JDH4-02-007-CN-1190 | Installation of Air Vents [Sewage Lift Station ] | 4730.64 | 100% | 100% | 4730.64
JDH4-02-007-CN-1180 | JDH4-02-007-CN-1180 | Installation of Manually operated davit crane (portable) [Sewage Lift Station ] | 94612.71 | 100% | 100% | 94612.71
JDH4-02-007-CN-1210 | JDH4-02-007-CN-1210 | Installation of Baffle Plates [Sewage Lift Station ] | 9461.27 | 100% | 100% | 9461.27
Interface Works | Interface Works |  | 63075.14 |  | 0% | 0
JDH4-02-007-CN-1220 | JDH4-02-007-CN-1220 | Interfacing Works [Sewage Lift Station ] | 63075.14 | 0% | 0% | 0
Anti Water Hammer Equipment | Anti Water Hammer Equipment |  | 883051.97 |  | 20% | 176610.39
JDH4-02-007-CN-1230 | JDH4-02-007-CN-1230 | Installation of Anti-Water Hammer Equipment [Sewage Lift Station ] | 883051.97 | 20% | 20% | 176610.39
Air Conditioning & Ventilation | Air Conditioning & Ventilation |  | 18922.54 |  | 100% | 18922.54
JDH4-02-007-CN-1240 | JDH4-02-007-CN-1240 | Installation of Air Conditioning [Sewage Lift Station ] | 18922.54 | 100% | 100% | 18922.54
Fuel System | Fuel System |  | 75690.17 |  | 100% | 75690.17
JDH4-02-007-CN-1260 | JDH4-02-007-CN-1260 | Installation of Bulk Fuel storage tank, 2500 Liter (7 Days of storage) [Sewage Lift Station ] | 18922.54 | 100% | 100% | 18922.54
JDH4-02-007-CN-1270 | JDH4-02-007-CN-1270 | Installation of Fuel pump set , 1 duty and 1 standby, Capacity 100 L/h, Head 1 Bar [Sewage Lift Station ] | 47306.36 | 100% | 100% | 47306.36
JDH4-02-007-CN-1280 | JDH4-02-007-CN-1280 | Pipes and Fitting Works [Sewage Lift Station ] | 9461.27 | 100% | 100% | 9461.27
Fire Fighting | Fire Fighting |  | 56767.63 |  | 100% | 56767.63
JDH4-02-007-CN-1290 | JDH4-02-007-CN-1290 | Installation of Fire fighting for electrical room which has a volume of about 62 m3 [Sewage Lift Station ] | 47306.36 | 100% | 100% | 47306.36
JDH4-02-007-CN-1300 | JDH4-02-007-CN-1300 | Installation of Foam type - wheeled type 20 Gallon capacity-ref. FE-01 [Sewage Lift Station ] | 9461.27 | 100% | 100% | 9461.27
Pumps | Pumps |  | 233378.02 |  | 15% | 35006.7
JDH4-02-007-CN-1070 | JDH4-02-007-CN-1070 | Installation of Submersible pump [Sewage Lift Station ] | 233378.02 | 15% | 15% | 35006.7
Electrical Works | Electrical Works |  | 1230213.92 |  | 29.75% | 365977.47
Main Distribution Board | Main Distribution Board |  | 104073.98 |  | 0% | 0
JDH4-02-007-CN-1310 | JDH4-02-007-CN-1310 | Installation of Main Distribution Board/MCC Panel [Sewage Lift Station ] | 75690.17 | 0% | 0% | 0
JDH4-02-007-CN-1320 | JDH4-02-007-CN-1320 | Installation of Panel Board [Sewage Lift Station ] | 28383.81 | 0% | 0% | 0
Local Control Panel | Local Control Panel |  | 107227.74 |  | 0% | 0
JDH4-02-007-CN-1330 | JDH4-02-007-CN-1330 | Installation of MCP-LP-01 [Sewage Lift Station ] | 25230.06 | 0% | 0% | 0
JDH4-02-007-CN-1350 | JDH4-02-007-CN-1350 | Installation of MCP-LP-02 [Sewage Lift Station ] | 25230.06 | 0% | 0% | 0
JDH4-02-007-CN-1360 | JDH4-02-007-CN-1360 | Installation of OD-CP [Sewage Lift Station ] | 28383.81 | 0% | 0% | 0
JDH4-02-007-CN-1370 | JDH4-02-007-CN-1370 | Installation of FP-CP [Sewage Lift Station ] | 28383.81 | 0% | 0% | 0
Diesel Generator | Diesel Generator |  | 75690.17 |  | 100% | 75690.17
JDH4-02-007-CN-1380 | JDH4-02-007-CN-1380 | Installation of Standby Diesel Generator [Sewage Lift Station ] | 75690.17 | 100% | 100% | 75690.17
Power Factor Correction Capacitor Bank | Power Factor Correction Capacitor Bank |  | 22076.3 |  | 0% | 0
JDH4-02-007-CN-1390 | JDH4-02-007-CN-1390 | Installation of Power Factor Correction Capacitor Bank [Sewage Lift Station ] | 22076.3 | 0% | 0% | 0
Low-Voltage Electrical Power Conductors and Cables | Low-Voltage Electrical Power Conductors and Cables |  | 17535.2 |  | 0% | 0
JDH4-02-007-CN-1410 | JDH4-02-007-CN-1410 | Installation of Low Voltage Cables [Sewage Lift Station ] | 17535.2 | 0% | 0% | 0
Wiring Devices | Wiring Devices |  | 5044.14 |  | 100% | 5044.14
JDH4-02-007-CN-1420 | JDH4-02-007-CN-1420 | Installation of Wiring Devices [Sewage Lift Station ] | 5044.14 | 100% | 100% | 5044.14
Enclosed Switches and Circuit Breakers | Enclosed Switches and Circuit Breakers |  | 8830.52 |  | 0% | 0
JDH4-02-007-CN-1440 | JDH4-02-007-CN-1440 | Installation of Enclosed Switches and Circuit Breakers [Sewage Lift Station ] | 8830.52 | 0% | 0% | 0
Lighting | Lighting |  | 16399.53 |  | 100% | 16399.53
JDH4-02-007-CN-1450 | JDH4-02-007-CN-1450 | Installation of Lightings [Sewage Lift Station ] | 16399.53 | 100% | 100% | 16399.53
Grounding and Bonding for Electrical Systems | Grounding and Bonding for Electrical Systems |  | 18607.15 |  | 0% | 0
JDH4-02-007-CN-1460 | JDH4-02-007-CN-1460 | Installation of Grounding Links [Sewage Lift Station ] | 18607.15 | 0% | 0% | 0
Electrical Manholes | Electrical Manholes |  | 10723.17 |  | 100% | 10723.17
JDH4-02-007-CN-1470 | JDH4-02-007-CN-1470 | Installation of Electrical Manholes [Sewage Lift Station ] | 10723.17 | 100% | 100% | 10723.17
ICT (Data& telephone System) | ICT (Data& telephone System) |  | 44152.59 |  | 0% | 0
JDH4-02-007-CN-1490 | JDH4-02-007-CN-1490 | Installation of IDF Cabinet 9U (for data &Telephone) [Sewage Lift Station ] | 22076.3 | 0% | 0% | 0
JDH4-02-007-CN-1500 | JDH4-02-007-CN-1500 | Installationof Single data/Telephone outlet [Sewage Lift Station ] | 1261.5 | 0% | 0% | 0
JDH4-02-007-CN-1510 | JDH4-02-007-CN-1510 | Installation of Data Switch (24 Port) [Sewage Lift Station ] | 18922.54 | 0% | 0% | 0
JDH4-02-007-CN-1520 | JDH4-02-007-CN-1520 | Installation of Fiber optic cable (12 Core single mode). [Sewage Lift Station ] | 1892.25 | 0% | 0% | 0
Security System (CCTV System) | Security System (CCTV System) |  | 198686.69 |  | 100% | 198686.69
JDH4-02-007-CN-1530 | JDH4-02-007-CN-1530 | Installation of 5.0 Megapixel, Fixed bullet IP CCTV camera [Sewage Lift Station ] | 198686.69 | 100% | 100% | 198686.69
Duct Bank and Handhole For Telecom Network | Duct Bank and Handhole For Telecom Network |  | 8199.77 |  | 100% | 8199.77
JDH4-02-007-CN-1540 | JDH4-02-007-CN-1540 | Installation of 2 x 50mm HDPE ducts Bank [Sewage Lift Station ] | 5046.01 | 100% | 100% | 5046.01
JDH4-02-007-CN-1550 | JDH4-02-007-CN-1550 | Installation of Handholes (800x800x800 mm) [Sewage Lift Station ] | 3153.76 | 100% | 100% | 3153.76
Programmable Logic Controllers | Programmable Logic Controllers |  | 252300.56 |  | 0% | 0
JDH4-02-007-CN-1570 | JDH4-02-007-CN-1570 | Installation of Programmable Logic Controller [Sewage Lift Station ] | 252300.56 | 0% | 0% | 0
Process Control Wiring | Process Control Wiring |  | 157687.85 |  | 0% | 0
JDH4-02-007-CN-1580 | JDH4-02-007-CN-1580 | Installation of Process Control Wiring [Sewage Lift Station ] | 157687.85 | 0% | 0% | 0
Instrumentation for Process Systems | Instrumentation for Process Systems |  | 182978.56 |  | 28% | 51234
JDH4-02-007-CN-1600 | JDH4-02-007-CN-1600 | Installation of Process System [Sewage Lift Station ] | 182978.56 | 28% | 28% | 51234
Fence Work | Fence Work |  | 18243.11 |  | 100% | 18243.11
JDH4-02-007-CN-5890 | JDH4-02-007-CN-5890 | Installation of Chain Link Fence [Sewage Lift Station ] | 11984.28 | 100% | 100% | 11984.28
JDH4-02-007-CN-5900 | JDH4-02-007-CN-5900 | Installation of Pedestrian Gate [Sewage Lift Station ] | 6258.83 | 100% | 100% | 6258.83
MV Cable Works | MV Cable Works |  | 888341.63 |  | 97.79% | 868711.82
Medium Voltage Cable Road 8 | Medium Voltage Cable Road 8 |  | 165937.27 |  | 100% | 165937.27
JDH4-02-007-CN-2480 | JDH4-02-007-CN-2480 | Installation of Duct banks [Road 08 ] | 31916.02 | 100% | 100% | 31916.02
JDH4-02-007-CN-2420 | JDH4-02-007-CN-2420 | Excavation for Trench [Road 08 ] | 7545 | 100% | 100% | 7545
JDH4-02-007-CN-2540 | JDH4-02-007-CN-2540 | Installation of Medium Voltage Cables [Road 08 ] | 126476.25 | 100% | 100% | 126476.25
Medium Voltage Cable Road 7 | Medium Voltage Cable Road 7 |  | 130128.34 |  | 100% | 130128.34
JDH4-02-007-CN-2500 | JDH4-02-007-CN-2500 | Installation of Duct banks [Road 07-N ] | 13876.53 | 100% | 100% | 13876.53
JDH4-02-007-CN-2440 | JDH4-02-007-CN-2440 | Excavation for Trench [Road 07-N ] | 6530.33 | 100% | 100% | 6530.33
JDH4-02-007-CN-2560 | JDH4-02-007-CN-2560 | Installation of Medium Voltage Cables [Road 07-N ] | 109721.48 | 100% | 100% | 109721.48
Medium Voltage Cable Road 1 | Medium Voltage Cable Road 1 |  | 264999.32 |  | 100% | 264999.32
JDH4-02-007-CN-2430 | JDH4-02-007-CN-2430 | Excavation for Trench [Road 01 ] | 13372.86 | 100% | 100% | 13372.86
JDH4-02-007-CN-2490 | JDH4-02-007-CN-2490 | Installation of Duct banks [Road 01 ] | 27290.51 | 100% | 100% | 27290.51
JDH4-02-007-CN-2550 | JDH4-02-007-CN-2550 | Installation of Medium Voltage Cables [Road 01 ] | 224335.95 | 100% | 100% | 224335.95
Medium Voltage Cable Road 10 | Medium Voltage Cable Road 10 |  | 130978.55 |  | 100% | 130978.55
JDH4-02-007-CN-2460 | JDH4-02-007-CN-2460 | Excavation for Trench [Road 10 ] | 6816.52 | 100% | 100% | 6816.52
JDH4-02-007-CN-2520 | JDH4-02-007-CN-2520 | Installation of Duct banks [Road 10 ] | 9251.02 | 100% | 100% | 9251.02
JDH4-02-007-CN-2580 | JDH4-02-007-CN-2580 | Installation of Medium Voltage Cables [Road 10 ] | 114911.01 | 100% | 100% | 114911.01
Medium Voltage Cable Out of Zone | Medium Voltage Cable Out of Zone |  | 196298.15 |  | 90% | 176668.34
JDH4-02-007-CN-2470 | JDH4-02-007-CN-2470 | Excavation for Trench [Out of Zone ] | 9236.12 | 90% | 90% | 8312.51
JDH4-02-007-CN-2530 | JDH4-02-007-CN-2530 | Installation of Duct banks [Out of Zone ] | 33303.68 | 90% | 90% | 29973.31
JDH4-02-007-CN-2590 | JDH4-02-007-CN-2590 | Installation of Medium Voltage Cables [Out of Zone ] | 153758.35 | 90% | 90% | 138382.52
Plot Backfilling 2 | Plot Backfilling 2 |  | 3041122.86 |  | 76.67% | 2331527.53
JDH4-02-007-CN-1860 | JDH4-02-007-CN-1860 | Plots backfilling Stage 5 [Plots ] | 1013707.62 | 100% | 100% | 1013707.62
JDH4-02-007-CN-1870 | JDH4-02-007-CN-1870 | Plots backfilling Stage 6 [Plots ] | 1013707.62 | 70% | 70% | 709595.33
JDH4-02-007-CN-1880 | JDH4-02-007-CN-1880 | Plots backfilling Stage 7 [Plots ] | 1013707.62 | 60% | 60% | 608224.57
Additional Works | Additional Works |  | 4574877.19 |  | 91.25% | 4174575.44
JDH4-02-007-CN-1740 | JDH4-02-007-CN-1740 | Earth Work | 1143719.3 | 100% | 100% | 1143719.3
JDH4-02-007-CN-5940 | JDH4-02-007-CN-5940 | Utilities Work | 1143719.3 | 100% | 100% | 1143719.3
JDH4-02-007-CN-5960 | JDH4-02-007-CN-5960 | Road Work | 1143719.3 | 85% | 85% | 972161.4
JDH4-02-007-CN-5950 | JDH4-02-007-CN-5950 | Electrical Works | 1143719.3 | 80% | 80% | 914975.44
Testing & Commissioning | Testing & Commissioning |  | 5730434.78 |  | 67.86% | 3888509.32
JDH4-02-007-TC-1020 | JDH4-02-007-TC-1020 | Test for Sanitary Sewerage | 818633.54 | 100% | 100% | 818633.54
JDH4-02-007-TC-1000 | JDH4-02-007-TC-1000 | Test for Potable Water Network | 818633.54 | 100% | 100% | 818633.54
JDH4-02-007-TC-1060 | JDH4-02-007-TC-1060 | Test for Road Works | 818633.54 | 40% | 40% | 327453.42
JDH4-02-007-TC-1030 | JDH4-02-007-TC-1030 | Test for Stormwater Utilities | 818633.54 | 100% | 100% | 818633.54
JDH4-02-007-TC-1010 | JDH4-02-007-TC-1010 | Test for TSE Network | 818633.54 | 100% | 100% | 818633.54
JDH4-02-007-TC-1050 | JDH4-02-007-TC-1050 | Test for Sewage Lift Station | 818633.54 | 15% | 15% | 122795.03
JDH4-02-007-TC-1040 | JDH4-02-007-TC-1040 | Test for Electrical Network | 818633.54 | 20% | 20% | 163726.71
Project Hand Over & Close-out | Project Hand Over & Close-out |  | 0 |  | 0% | 0
As-Built DWGs | As-Built DWGs |  | 0 |  | 0% | 0
As-Built DWGs Submittal | As-Built DWGs Submittal |  | 0 |  | 0% | 0
JDH4-02-007-AB-1020 | JDH4-02-007-AB-1020 | As-Built DWGs Submittal for Sanitary Sewerage | 0 | 100% | 100% | 0
JDH4-02-007-AB-1030 | JDH4-02-007-AB-1030 | As-Built DWGs Submittal for Stormwater Utilities | 0 | 100% | 100% | 0
JDH4-02-007-AB-1010 | JDH4-02-007-AB-1010 | As-Built DWGs Submittal for TSE Network | 0 | 100% | 100% | 0
JDH4-02-007-AB-1000 | JDH4-02-007-AB-1000 | As-Built DWGs Submittal for Potable Water Network | 0 | 100% | 100% | 0
JDH4-02-007-AB-1040 | JDH4-02-007-AB-1040 | As-Built DWGs Submittal for Electrical Network | 0 | 0% | 0% | 0
JDH4-02-007-AB-1060 | JDH4-02-007-AB-1060 | As-Built DWGs Submittal for Road Works | 0 | 0% | 0% | 0
JDH4-02-007-AB-1050 | JDH4-02-007-AB-1050 | As-Built DWGs Submittal for Sewage Lift Station | 0 | 0% | 0% | 0
As-Built DWGs Approval | As-Built DWGs Approval |  | 0 |  | 0% | 0
JDH4-02-007-AB-1090 | JDH4-02-007-AB-1090 | As- Built DWGs Approval for Sanitary Sewerage | 0 | 100% | 100% | 0
JDH4-02-007-AB-1080 | JDH4-02-007-AB-1080 | As- Built DWGs Approval for TSE Network | 0 | 100% | 100% | 0
JDH4-02-007-AB-1070 | JDH4-02-007-AB-1070 | As- Built DWGs Approval for Potable Water Network | 0 | 100% | 100% | 0
JDH4-02-007-AB-1100 | JDH4-02-007-AB-1100 | As- Built DWGs Approval for Stormwater Utilities | 0 | 100% | 100% | 0
JDH4-02-007-AB-1110 | JDH4-02-007-AB-1110 | As- Built DWGs Approval for Electrical Network | 0 | 0% | 0% | 0
JDH4-02-007-AB-1130 | JDH4-02-007-AB-1130 | As- Built DWGs Approval for Road Works | 0 | 0% | 0% | 0
JDH4-02-007-AB-1120 | JDH4-02-007-AB-1120 | As- Built DWGs Approval for Sewage Lift Station | 0 | 0% | 0% | 0
Demobilization | Demobilization |  | 0 |  | 0% | 0
JDH4-02-007-DM-1000 | JDH4-02-007-DM-1000 | Demobilization of Manpower | 0 | 0% | 0% | 0
JDH4-02-007-DM-1010 | JDH4-02-007-DM-1010 | Removal of Equipment from Site | 0 | 0% | 0% | 0
JDH4-02-007-DM-1020 | JDH4-02-007-DM-1020 | Site Clean Up | 0 | 0% | 0% | 0
JDH4-02-007-DM-1030 | JDH4-02-007-DM-1030 | Removal of Site Offices and Structures | 0 | 0% | 0% | 0
JDH4-02-007-DM-1040 | JDH4-02-007-DM-1040 | Restoration of Ground Surfaces | 0 | 0% | 0% | 0