## Procurement
Sr. NO. | Project ID | ACT # in P6 | Item Description | Discipline | (Long \Short) Lead Items | BOQ. No. | Unit | Quantity | Proc. Qty | Required P.O Date | Date of Pur. Order Issued | Purchase Order No. | Supplier | Supplier Phone | Method of Shipping | Required on Job | E.D.A. to Site | A.D.A. to Site | Lead Time | Approval Status | The Impact (BOQ Cost) | Completion Rate | Remarks
1 | JHD4-02-007 | JDH4-02-007-PR-1740 | Catch Basins | Mech. | Long Lead Items | B6.33 05 39.01 | nr | 32 | 32 | 2025-12-30 | 2026-01-21 | P119134 | T. Nagadi Factory | 0500195198 | Land | 2026-03-22 | 2026-03-22 | 2026-01-25 | 4 | Approved | 367153.8025 | 100% | Completed
2 | JHD4-02-007 | JDH4-02-007-PR-1680 | GRP Pipes | Mech. | Long Lead Items | B5.33 31&B6.33 42 | m | 5420 | 5420 | 2025-12-29 | 2025-12-28 | Po117310,P117449 | T. Nagadi Factory | 0500195198 | Land | 2026-02-07 | 2026-02-07 | 2025-12-28 | 0 | Approved | 5596610.14 | 100% | Completed
3 | JHD4-02-007 | JDH4-02-007-PR-1710 | Manholes | Mech. | Long Lead Items | B5.33 05 | nr | 87 | 87 | 1900-12-08 | 2026-01-01 | P117657 | T. Nagadi Factory | 0500195198 | Land | 2026-02-14 | 2026-02-14 | 2026-01-10 | 9 | Approved | 2882628.0628 | 100% | Completed
4 | JHD4-02-007 | JDH4-02-007-PR-1590 | HDPE For Network | Mech. | Long Lead Items | B3.33 14 &B4.33 31 | m | 8969 | 8969 | 2025-12-29 | 2025-12-30 | P117525 | NEPROPLAST | 0557128534 | Land | 2026-02-02 | 2026-02-02 | 2025-12-31 | 1 | Approved | 2950231.4306 | 100% | Completed
5 | JHD4-02-007 | JDH4-02-007-PR-1230 | UPVC | Mech. | Long Lead Items | B2.33 &B7.16 | 3 | 361 | 361 | 2026-01-04 |  |  | Al-Munif | 0507775269 | Land | 2026-02-15 | 2026-02-15 |  |  | Approved | 301442.6861 | 100% | Completed
6 | JHD4-02-007 | JDH4-02-007-PR-2280 | HDPE For Telcom | Elec. | Long Lead Items | B2.33 71 | m | 45580 | 45580 | 2026-01-22 |  |  |  |  | Land | 2026-03-08 | 2026-03-08 |  |  | Approved | 2151144.7149 | 100% | Completed
7 | JHD4-02-007 | JDH4-02-007-PR-2320 | Fire Fighting System | Mech. | Long Lead Items | B7.15.17.1.1 | Lot | 1 | 1 | 2026-01-18 |  |  |  |  | Land | 2026-03-05 | 2026-03-05 |  |  | Approved | 70606.5005 | 100% | Completed
8 | JHD4-02-007 | JDH4-02-007-PR-2410 | CCTV System | Elec. | Long Lead Items | B7.16.15.1 | nr | 7 | 7 | 2026-01-22 |  |  |  |  | Land | 2026-03-04 | 2026-03-04 |  |  | Approved | 296547.3021 | 100% | Completed
9 | JHD4-02-007 | JDH4-02-007-PR-1290 | Valves | Mech. | Long Lead Items | B3&B4&B7 | nr | 68 | 68 | 2026-01-01 | 2026-02-10 | P120734 | T-Nagadi | 0500195198 | Land | 2026-05-06 | 2026-05-06 |  |  | Approved | 626985.7243 | 100% | Completed
10 | JHD4-02-007 | JDH4-02-007-PR-2460 | Fire Hydrant | Mech. | Long Lead Items | B3.33 14 19.11 | nr | 30 | 30 | 2025-12-29 |  |  |  |  | Land | 2026-04-29 | 2026-04-29 |  |  | Approved | 423639.0029 | 100% | Completed
11 | JHD4-02-007 | JDH4-02-007-PR-1120 | Medium Voltage Cable | Mech. | Long Lead Items | B2.26.05.13.16.01 | m | 13117 | 13117 | 2026-01-22 |  |  |  |  | Land | 2026-04-15 | 2026-04-15 |  |  | Approved | 1166457.0449 | 100% | Completed
12 | JHD4-02-007 | JDH4-02-007-PR-1130 | Unit Sub-station | Elec. | Long Lead Items | B2.26 11 16.01 | Unit | 1 | 1 | 2026-01-22 |  |  |  |  | Sea | 2026-06-13 | 2026-06-13 |  |  | Approved | 112970.4008 | 100% | Completed
13 | JHD4-02-007 | JDH4-02-007-PR-1140 | Low Voltage Cables | Elec. | Long Lead Items | B2.26 05 &B7.16 | m | 13117 | 13117 | 2026-01-08 |  |  |  |  | Land | 2026-04-02 | 2026-04-02 |  |  | Approved | 690832.8292 | 100% | Completed
14 | JHD4-02-007 | JDH4-02-007-PR-1960 | Ring Main Unit (RMU) | Elec. | Long Lead Items | B2.26 11 16.02 | Unit | 3 | 3 | 2026-01-22 |  |  |  |  | Sea | 2026-04-29 | 2026-04-29 |  |  | Approved | 94142.0007 | 100% | Completed
15 | JHD4-02-007 | JDH4-02-007-PR-1150 | Lighting poles | Elec. | Long Lead Items | B2.26 56 | Unit | 258 | 258 | 2026-01-22 |  |  |  |  | Land | 2026-04-13 | 2026-04-13 |  |  | Approved | 527101.0617 | 100% | Completed
16 | JHD4-02-007 | JDH4-02-007-PR-1160 | Street Lighting Luminaire | Elec. | Long Lead Items | B2.26.56.19 | Unit | 258 | 258 | 2026-01-22 |  |  |  |  | Land | 2026-05-03 | 2026-05-03 |  |  | Approved | 124173.2989 | 100% | Completed
17 | JHD4-02-007 | JDH4-02-007-PR-1170 | Feeder Pillers | Elec. | Long Lead Items | B2.33 71 16.01 | Unit | 1 | 1 | 2026-01-18 |  |  |  |  | Sea | 2026-04-25 | 2026-04-25 |  |  | Approved | 32949.7002 | 100% | Completed
18 | JHD4-02-007 | JDH4-02-007-PR-2500 | Distribution Panels | Elec. | Long Lead Items | B7.16.2.1 | Item/set | 1 | 1 | 2026-01-22 |  |  |  |  | Sea | 2026-04-16 | 2026-04-16 |  |  | Approved | 42363.9003 | 100% | Completed
19 | JHD4-02-007 | JDH4-02-007-PR-2090 | Odours Control system | Mech. | Long Lead Items | B7.15.8.1 | Set | 1 | 1 | 2026-01-08 |  |  |  |  | Sea | 2026-05-24 | 2026-05-24 |  |  | Approved | 235355.0016 | 100% | Completed
20 | JHD4-02-007 | JDH4-02-007-PR-2200 | Crane | Mech. | Long Lead Items | B7.15.9.1 | nr | 1 | 1 | 2026-01-24 |  |  |  |  | Sea | 2026-06-04 | 2026-06-04 |  |  | Approved | 141213.001 | 100% | Completed
21 | JHD4-02-007 | JDH4-02-007-PR-2100 | Air Vents | Mech. | Long Lead Items | B7.15.10.3 | Lot | 1 | 1 | 2026-01-18 |  |  |  |  | Land | 2026-08-02 | 2026-08-02 |  |  | Approved | 2353.55 | 100% | Completed
22 | JHD4-02-007 | JDH4-02-007-PR-2240 | Screening Container | Mech. | Long Lead Items | B7.15.12.1 | nr | 1 | 1 | 2026-01-18 |  |  |  |  | Land | 2026-08-02 | 2026-08-02 |  |  | Approved | 14121.3001 | 100% | Completed
23 | JHD4-02-007 | JDH4-02-007-PR-2110 | Baffle Plates | Mech. | Long Lead Items | B7.15.13.1 | nr | 1 | 1 | 2026-01-18 | 2026-02-02 | P120012 | International Center of Fiberglass |  | Land | 2026-06-23 | 2026-06-23 |  |  | Approved | 14121.3001 | 100% | Completed
24 | JHD4-02-007 | JDH4-02-007-PR-2120 | Anti-Water Hammer Equipment | Mech. | Long Lead Items | B7.15.14.2.1 | Lot | 1 | 1 | 2026-01-18 |  |  |  |  | Sea | 2026-08-03 | 2026-08-03 |  |  | Approved | 1317988.0091 | 100% | Completed
25 | JHD4-02-007 | JDH4-02-007-PR-2080 | Pumps | Mech. | Long Lead Items | B7.15.1.1 | nr | 2 | 2 | 2026-01-18 | 2026-01-27 | P119594 | ZAMIL Trading | 0507972833 | Sea | 2026-08-08 | 2026-09-15 |  |  | Approved | 348325.4024 | 100% | under‑manufacturing
26 | JHD4-02-007 | JDH4-02-007-PR-2610 | MCCB (VFD) | Mech. | Long Lead Items | B7.16.1.1 | Item/set | 1 | 1 | 2026-01-18 |  |  |  |  | Sea | 2026-05-24 | 2026-09-15 |  |  | Approved | 112970.4008 | 100% | under‑manufacturing
27 | JHD4-02-007 | JDH4-02-007-PR-2620 | Local Control Panel/ Monitoring Control Panel | Elec. | Long Lead Items | B7.16.1.1&B7.16.14.1.1&B7.16.17.1 | item | 3 | 3 | 2026-01-18 |  |  |  |  | Sea | 2026-07-28 | 2026-09-15 |  |  | Approved | 522488.1036 | 100% | under‑manufacturing
28 | JHD4-02-007 | JDH4-02-007-PR-2630 | Generator | Elec. | Long Lead Items | B7.16.4.1 | Item/set | 1 | 1 | 2026-01-18 |  |  |  |  | Sea | 2026-06-23 | 2026-06-23 |  |  | Approved | 112970.4008 | 100% | under‑manufacturing
29 | JHD4-02-007 | JDH4-02-007-PR-2840 | Power Factor Correction Capacitor Bank | Elec. | Long Lead Items | B7.16.5.1 | Item/set | 1 | 1 | 2026-01-22 |  |  |  |  | Land | 2026-08-17 | 2026-08-17 |  |  | Approved | 32949.7002 | 100% | under‑manufacturing
30 | JHD4-02-007 | JDH4-02-007-PR-2980 | Enclosed Switches and Circuit Breakers | Elec. | Long Lead Items | 16.9 | nr | 7 | 4 | 2026-01-22 |  |  |  |  | Land | 2026-08-06 | 2026-08-06 |  |  | Approved | 7531.3601 | 57.14% | On Progress
31 | JHD4-02-007 | JDH4-02-007-PR-3080 | ICT (Data& telephone System) | Elec. | Long Lead Items | B7.16.15.1 | nr | 7 | 7 | 2026-01-22 |  |  |  |  | Land | 2026-08-06 | 2026-08-06 |  |  | Approved | 296547.3021 | 100% | Completed
32 | JHD4-02-007 | JDH4-02-007-PR-3140 | PLC | Elec. | Long Lead Items | B7.16.17.1 | item | 1 | 1 | 2026-01-22 |  |  |  |  | Sea | 2026-08-06 | 2026-09-15 |  |  | Approved | 376568.0026 | 100% | under‑manufacturing
33 | JHD4-02-007 | JDH4-02-007-PR-3020 | Instrumentation for Process Systems | Elec. | Long Lead Items | 16.19 | item | 18 | 18 | 2026-01-22 |  |  |  |  | Land | 2026-08-17 | 2026-09-15 |  |  | Approved | 273011.8019 | 100% | under‑manufacturing
34 | JHD4-02-007 | JDH4-02-007-PR-3021 | flow meter | Mech. | Long Lead Items | B7.15.1.2 | item | 1 | 1 | 2026-01-22 |  |  |  |  | Sea | 2026-08-17 | 2026-09-15 |  |  | Approved | 14121.3001 | 100% | under‑manufacturing
35 | JHD4-02-007 | JDH4-02-007-PR-3022 | ATS | Elec. | Long Lead Items | B7.16.1.1 | nr | 1 | 1 | 2026-01-22 |  |  |  |  | Sea | 2026-08-17 | 2026-09-15 |  |  | Approved | 112970.4008 | 100% | under‑manufacturing
36 | JHD4-02-007 | JDH4-02-007-PR-3023 | IDF Cabinet 9U (for data &Telephone) | Elec. | Long Lead Items | B7.16.14.1.1 | Item/set | 1 | 1 | 2026-01-22 |  |  |  |  | Sea | 2026-08-17 | 2026-08-17 |  |  | Approved | 32949.7002 | 100% | Completed