## الأعماال المنفذه خلال الاسبوع
# | القطاع | Project ID | اسم المشروع | مدير المشروع | المقاول | بداية المشروع | نهاية المشروع التعاقدية | نهاية المشروع المتوقعة/ الالتزام | قيمة المشروع | Planned (%) AS PER BASELINE حتى الاسبوع الحالي | Planned (%) AS PER Crashed Plan حتى الاسبوع الحالي | Actual (%) حتى الاسبوع السابق | Actual (%) حتى الاسبوع الحالي | Actual (%) خلال الاسبوع | الأعمال التي تمت خلال هذا الاسبوع | أسباب التأخير في حالة وجود تأخير | تحديات المشروع | استشاري المشروع | رقم استشاري المشروع | Email | مهندس تخطيط المشروع | رقم مهندس تخطيط المشروع | Email
1 | القطاع الأوسط | JHD4-02-007 | تطوير أراضي واحة جدة | عبد الله الشنيفي | شركة الانجاز للتجارة والمقاولات | 2025-11-24 | 2026-05-23 | 2026-11-23 | 57304347.86 | 58.61% | 86.21% | 91.11% | 93.31% | 2.2% | Road Marking Work at R8,R7S MCC Panel Work at Lift Station Diesl Pump Work at Lift Station Rockfilling Work for Plots 5 & 6 Sign Board Installation at R3 & R7S MC1 Work at Tent Road ABC work at Tent Wearing Course at R1 & R10 MV Cable Laying at RS & Out Zone SL Work at R1 & R7S PLC Installation at Lift Station Panel Board Work at Lift Station TL Work at R7S & R1 Pump Installation Work at Lift Station RMU Termination Work Checker Plate Installation at Lift Station
3 | القطاع الأوسط
4 | القطاع الأوسط
5 | القطاع الأوسط | [16 empty] | باسم الطيب | 0542536776 | Bassem.Altayeb@jasarapmc.com