## DB (hidden)
MODON - Weekly Progress Report - Construction Projects
| Contract General Information | [7 empty] | Key Dates | [10 empty] | Cost Summary (SR) | [8 empty] | Performance Summary | [11 empty] | Shop Drawings |  |  |  | Material Approval |  |  | Procurement Summary | [6 empty] | Quality Reports | [15 empty] | Key Submittals Approval Status | [9 empty] | Invoices Summary | [13 empty] | Resources at Site | [6 empty] | Safety Statistics | [63 empty] | Primavera P6 Schedule Status | [7 empty] | Weekly Prgoress Photos
Data Date | Project Name | Project ID | Contractor | Consultant | Stage | Status | Modon PM | Project Scope | Contract Award | Contract Sign | Site Handover | Original Completion | Contract Award (Hijri) | Contract Sign (Hijri) | Site Handover (Hijri) | Original Completion (Hijri) | Revised Completion | Committed Completion | Forecast Completion | Original Contract Value | Revised Contract Value | Estimate At Completion Value | Potential Changes | O&M Value (if any) | Submitted Invoices (Gross Value) | Penalities | FIR Value (Todate) | Original Plan Value | Plan Value | Earn Value | Phys. Plan Value | Phys. Earn Value | Quality Score | Safety Score | Weekly PV (SAR) | Weekly EV (SAR) | Weekly PV % | Weekly PV % | Weekly Phys PV% | Weekly Phys PV% | Total SD Planned | SD Remaining | SD Pending | Total SD Submittals | Planned Materials Approv | Material Pending Approval | Materila Total Submittals | Total Materials | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Material on Site | Remaining Materials | Material Delivery Completion (Date) | NCR Issued | NCR Closed | NCR Pending | NCR Avg. Closing (Days) | SIR Issued | SIR Closed | SIR Pending | SIR Avg. Closing (Days) | MIR Issued | MIR Closed | MIR Pending | MIR Avg. Closing (Days) | FIR Issued | FIR Closed | FIR Pending | FIR Avg. Closing (Days) | 1 Quality Plan Approval | 2 Quality Plan Last Up | 3 Safety Plan Approval | 4 Safety Plan Last Up | 5 Construction Plan Approval | 6 Baseline Approval | 7 No of Approved Version of Schedule | 8 Last Approved Schedule | 9 BOQ Approval Date | 10 No of Approved Version of BOQ | Total Submitted Invoices | PM Approved Invoices | No of Paid Invoices | No of Pending Invoices | Advance Payment % | Retention % | Deduction / Penalties % | Submitted Invoices (SAR) | PM Approved Invoices (SAR) | Paid Invoices (SAR) | Last Submitted Period | Advance Payment (SAR) | Retention (SAR) | Deduction / Penalties (SAR) | Planned Head Count | Actual Head Count | Saudi Staff | Labor Planned | Labor Actual | Equipment Planned | Equipment Actual | This Week Total Hours Worked | This Week Safe Hours Worked | This Week LTI | This Week MTC (Healed w/o Disability) | This Week MTC (Healed w/ Disability) | This Week Near Miss | This Week First Aid Cases | This Week Fatality | This Week Fire Incident Cases | This Week Vehicle Incident | This Week Property Damages | This Week Induction Training | This Week No.of Internal Training | This Week No.of Internal Audit | This Week No. of Toolbox Talks | This Week Safety Awards/Incentives | This Month Total Hours Worked | This Month Safe Hours Worked | This Month LTI | This Month MTC (Healed w/o Disability) | This Month MTC (Healed w/ Disability) | This Month Near Miss | This Month First Aid Cases | This Month Fatality | This Month Fire Incident Cases | This Month Vehicle Incident | This Month Property Damages | This Month Induction Training | This Month No.of Internal Training | This Month No.of Internal Audit | This Month No. of Toolbox Talks | This Month Safety Awards/Incentives | YTD Total Hours Worked | YTD Safe Hours Worked | YTD LTI | YTD MTC (Healed w/o Disability) | YTD MTC (Healed w/ Disability) | YTD Near Miss | YTD First Aid Cases | YTD Fatality | YTD Fire Incident Cases | YTD Vehicle Incident | YTD Property Damages | YTD Induction Training | YTD No.of Internal Training | YTD No.of Internal Audit | YTD No. of Toolbox Talks | YTD Safety Awards/Incentives | Cum Total Hours Worked | Cum Safe Hours Worked | Cum LTI | Cum MTC (Healed w/o Disability) | Cum MTC (Healed w/ Disability) | Cum Near Miss | Cum First Aid Cases | Cum Fatality | Cum Fire Incident Cases | Cum Vehicle Incident | Cum Property Damages | Cum Induction Training | Cum No.of Internal Training | Cum No.of Internal Audit | Cum No. of Toolbox Talks | Cum Safety Awards/Incentives | Total Act. | Not Started | In Progress | Completed | Critical Path Act.Last Week | Critical Path Act.This Week | Failed start Last Week | Failed start This Week | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-20 | Development of Infrastructure for phase 1 of the Logistics area at the 2nd Industrial City in Dammam | DAM2-02-009 | Shibh Aljazira Contracting Company | Egis | Construction | Active | Muhammad H Al-Essa | The project consists of the wet networks mainlines (Sewerage, Storm, Potable, Firefighting & TSE) including the force main line, in addition to the dry networks (Medium Voltage, Low Voltage, Street Lighting & Telecommunication) road crossings & main line connections, scope also included supply, install, testing & commissioning for the potable water pump station and the sewage lift station and implementation of guard rooms and applying all the road earth layers till the asphalt wearing coarse for the project scope area internal roads & finishing the landscape | 2025-06-30 | 2025-07-14 | 2025-07-30 | 2027-01-29 | 2025-06-30 | 2025-07-14 | 2025-07-30 | 2027-01-29 | 2027-01-29 | 2027-01-29 | 2027-02-14 | 198906162.61 | 198906162.61 | 198906162.61 | 0 | 0 | 62889673.529 | -104500 | 84260706.8929 | 70.66% | 70.66% | 54.47% | 71.09% | 57.9% | 0.93 | 0.92857 | 9003095.08 | 2935329.41 | 4.526% | 1.476% | 5.533% | 2.071% | 1774 | 0 | 0 | 1774 | 155 | 7 | 152 | 48 | 48 | 42 | 0 | 25 | 23 | 2026-11-09 | 4 | 3 | 1 | 0 | 52 | 42 | 10 | 0 | 116 | 113 | 3 | 0 | 4699 | 4481 | 218 | 0 | 2024-02-24 | 2024-02-24 | 2024-02-28 | 2024-02-28 | 2024-02-26 | 2024-03-10 | 1 | 2024-03-10 | 0 | 1 | 7 | 0 | 0 | 0 | 0 | 0 | 0.00052537 | 62889673.529 | 0 | 0 | 2026-09-15 | 0 | 0 | -104500 | 35 | 57 | 4 | 360 | 483 | 150 | 326 | 34740 | 34740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 (6) | 0 | 3(355) | 0 | 104220 | 104220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 3 (11) | 1 | 3(648) | 0 | 809664 | 809664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114(571) | 6(29) | 4 | (43(3442) | 1 | 874722 | 874722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148(895) | 14(104) | 4 | 56(8671) | 2 | 4851 | 1938 | 431 | 2482 | 45 | 45 | 993 | 1047 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0

## Weekly Progress Report
MODON - Weekly Progress Report - Construction Projects | [30 empty] | Data Date | 2026-10-20
Contract General Information | [5 empty] | Key Dates | [5 empty] | Cost Summary (SR) | [7 empty] | Performance Summary | [5 empty] | Project Scope
Project Name | Development of Infrastructure for phase 1 of the Logistics area at the 2nd Industrial City in Dammam |  |  |  |  | Contract Award | 2025-06-30 | Contract Award (Hijri) | 2025-06-30 | Revised Completion | 2027-01-29 | Original Contract Value |  | 198906162.61 |  | O&M Value (if any) |  | 0 | EAC | Plan Value | 70.66% | Phys. Plan Value | 71.09% | Quality Score | 93% | The project consists of the wet networks mainlines (Sewerage, Storm, Potable, Firefighting & TSE) including the force main line, in addition to the dry networks (Medium Voltage, Low Voltage, Street Lighting & Telecommunication) road crossings & main line connections, scope also included supply, install, testing & commissioning for the potable water pump station and the sewage lift station and implementation of guard rooms and applying all the road earth layers till the asphalt wearing coarse for the project scope area internal roads & finishing the landscape
Project ID | DAM2-02-009 |  | Stage | Construction |  | Contract Sign | 2025-07-14 | Contract Sign (Hijri) | 2025-07-14 | Committed Completion | 2027-01-29 | Revised Contract Value |  | 198906162.61 | EAC | Submitted Invoices (Gross Value) |  | 62889673.529 |  | Earn Value | 54.47% | Phys. Earn Value | 57.9% |  | ¢¢¢¢¢ ¢¢¢¢£
Contractor | Shibh Aljazira Contracting Company |  | Status | Active |  | Site Handover | 2025-07-30 | Site Handover (Hijri) | 2025-07-30 | Forecast Completion | 2027-02-14 | Estimate At Completion Value |  | 198906162.61 | #REF! | Penalities |  | -104500 |  | Variance | -16.19% | Variance | -13.19% | Safety Score | 92.86%
Consultant | Egis |  | Modon PM | Muhammad H Al-Essa |  | Original Completion | 2027-01-29 | Original Completion (Hijri) | 2027-01-29 | Variance | -16 | Potential Changes |  | 0 |  | FIR Value (Todate) |  | 84260706.8929 |  | FIR % | 42.36% | Invoiced % | 31.62% |  | ¢¢¢¢¢ ¢¢¢¢£
Progress Overview
Earned Value Progress (SAR) | [13 empty] | Physical Progress (Effort) | [11 empty] | Earned Value Progress (%)
WBS |  | BOQ Value (SAR) | % Wt. | Weekly (SAR) |  | To Date (SAR) | [7 empty] | Budgeted | % Wt. | Weekly Physical Progress |  |  |  | To Date Physical Progress
|  |  |  | Planned | Earned | Original Plan | Revised Planned | Earned | Original Plan % | Revised Planned % | Earned % | Variance | SPI | (Manhours) |  | Planned | Earned | Plan % | Earned % | Planned | Earned | Plan % | Earned % | Variance | SPI
Demolishing & Site Clearing |  | 457401.18 | 0.23% | 0 | 0 | 457401.18 | 457401.18 | 457401.18 | 100% | 100% | 100% | 0% | 1 | 3437.41 | 0.3735% | 0 | 0 | 0% | 0% | 3437.41 | 3437.41 | 100% | 100% | 0% | 1
Earthworks & Site Grading |  | 31040591.65 | 15.61% | 0 | 0 | 31040591.65 | 31040591.65 | 29924053.16 | 100% | 100% | 96.4% | -3.597% | 0.96403 | 22808.8 | 2.479% | 0 | 0 | 0% | 0% | 22808.8 | 21945.45 | 100% | 96.21% | -3.785% | 0.96215
Sewerage Network |  | 5111121.83 | 2.57% | 22221.96 | 19950.12 | 5091236.27 | 5091236.27 | 4581972.17 | 99.61% | 99.61% | 89.65% | -9.964% | 0.89997 | 74260.44 | 8.07% | 1004.45 | 217.98 | 1.353% | 0.2935% | 63844.93 | 61523.35 | 85.97% | 82.85% | -3.126% | 0.96364
Storm Water Network |  | 21808728.44 | 10.96% | 373528.76 | 544011.74 | 20893008.47 | 20893008.47 | 18936432.18 | 95.8% | 95.8% | 86.83% | -8.972% | 0.90635 | 143781.21 | 15.62% | 2050.16 | 5276.51 | 1.426% | 3.67% | 126434.17 | 118557.55 | 87.94% | 82.46% | -5.478% | 0.9377
Potable Water Network |  | 1954044.36 | 0.9824% | 247588.8 | 0 | 1829021.1 | 1829021.1 | 1060337.72 | 93.6% | 93.6% | 54.26% | -39.34% | 0.57973 | 57934.51 | 6.296% | 2338.75 | 0 | 4.037% | 0% | 45314.91 | 34572.01 | 78.22% | 59.67% | -18.54% | 0.76293
Fire Fighting Network |  | 4678456.73 | 2.352% | 222667.04 | 0 | 4154735.3 | 4154735.3 | 3069245.61 | 88.81% | 65.6% | 65.6% | 0% | 1 | 63346.29 | 6.884% | 1054.05 | 0 | 1.664% | 0% | 46946.75 | 35344.31 | 74.11% | 55.8% | -18.32% | 0.75286
TSE Network |  | 2995733.64 | 1.506% | 7624.54 | 4798.13 | 2890249.63 | 2890249.63 | 691639.78 | 96.48% | 23.09% | 23.09% | 0% | 1 | 48137.98 | 5.231% | 2756.68 | 280.57 | 5.727% | 0.5828% | 30407.13 | 21771.81 | 63.17% | 45.23% | -17.94% | 0.71601
Potable Water Pump Station |  | 11076181.82 | 5.569% | 871038.9 | 0 | 7778556.94 | 7778556.94 | 1734353.19 | 70.23% | 70.23% | 15.66% | -54.57% | 0.22297 | 71778.26 | 7.8% | 3916.8 | 0 | 5.457% | 0% | 55212.98 | 48814.42 | 76.92% | 68.01% | -8.914% | 0.88411
Sewerage Lift Station |  | 4985124.69 | 2.506% | 407169.42 | 57598.58 | 798505.73 | 798505.73 | 115223.71 | 16.02% | 16.02% | 2.311% | -13.71% | 0.1443 | 70758.97 | 7.689% | 4814.7 | 272.87 | 6.804% | 0.3856% | 59468.75 | 49496.9 | 84.04% | 69.95% | -14.09% | 0.83232
Medium Voltage Network |  | 5452229.25 | 2.741% | 269033.47 | 406639.88 | 4451469.67 | 4451469.67 | 1895375.67 | 81.64% | 34.76% | 34.76% | 0% | 1 | 34290.88 | 3.726% | 3548.97 | 2139.67 | 10.35% | 6.24% | 23559.75 | 16079.61 | 68.71% | 46.89% | -21.81% | 0.6825
Low Voltage Network |  | 1876943.13 | 0.9436% | 391820.55 | 108822.6 | 1463373.35 | 1463373.35 | 125449.44 | 77.97% | 6.684% | 6.684% | 0% | 1 | 31587.58 | 3.433% | 2909.49 | 4155.36 | 9.211% | 13.16% | 18110.79 | 11200.92 | 57.34% | 35.46% | -21.88% | 0.61847
Street Lighting Network |  | 8486130.58 | 4.266% | 551969.82 | 1341942.58 | 3936228.49 | 3936228.49 | 2858226.78 | 46.38% | 33.68% | 33.68% | 0% | 1 | 76760.06 | 8.341% | 3939.88 | 5046.15 | 5.133% | 6.574% | 37091.48 | 25724.17 | 48.32% | 33.51% | -14.81% | 0.69353
Telecommunication Network |  | 4454965.57 | 2.24% | 551193.35 | 114597.64 | 3054463.68 | 3054463.68 | 1079952.36 | 68.56% | 68.56% | 24.24% | -44.32% | 0.35357 | 62092.94 | 6.748% | 6921.42 | 1356.84 | 11.15% | 2.185% | 36756.61 | 16818.91 | 59.2% | 27.09% | -32.11% | 0.45758
Road Works |  | 79068381.04 | 39.75% | 4694358.02 | 336968.14 | 52058577.55 | 52058577.55 | 41659930.91 | 65.84% | 65.84% | 52.69% | -13.15% | 0.80025 | 80303.58 | 8.726% | 10540.52 | 314.34 | 13.13% | 0.3914% | 46630.85 | 27615.16 | 58.07% | 34.39% | -23.68% | 0.59221
Landscape |  | 14727629.51 | 7.404% | 343486.94 | 0 | 485726.4 | 485726.4 | 98475.6 | 3.298% | 3.298% | 0.6686% | -2.629% | 0.20274 | 44855.31 | 4.874% | 2273.25 | 0 | 5.068% | 0% | 8856.02 | 14158.54 | 19.74% | 31.56% | 11.82% | 1.5987
Guard Rooms |  | 539598.47 | 0.2713% | 49393.51 | 0 | 155239.2 | 155239.2 | 49342.79 | 28.77% | 28.77% | 9.144% | -19.63% | 0.31785 | 34095.79 | 3.705% | 2848.95 | 0 | 8.356% | 0% | 29294.65 | 25734.12 | 85.92% | 75.48% | -10.44% | 0.87846
Provisional Sum |  | 192900.72 | 0.09698% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | 0% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
| Total | 198906162.61 | 100% | 9003095.08 | 2935329.41 | 140538384.61 | 140538384.61 | 108337412.25 | 70.66% | 70.66% | 54.47% | -16.19% | 0.77087 | 920230.01 | 100% | 50918.07 | 19060.29 | 5.533% | 2.071% | 654175.98 | 532794.64 | 71.09% | 57.9% | -13.19% | 0.81445
Construction Milestones
[26 empty] | Item No. | Milestones |  | Original (Baseline) | Latest Plan | Forecast | Status | Days Change
[26 empty] | 1 | Award Date |  | 2025-06-30 | 2025-06-30 | 2025-06-30 | A | 0
[26 empty] | 2 | Contract Sign Date |  | 2025-07-14 | 2025-07-14 | 2025-07-14 | A | 0
[26 empty] | 3 | Site Handover Date |  | 2025-07-30 | 2025-07-30 | 2025-07-30 | A | 0
[26 empty] | 4 | Complete Mobilization |  | 2025-08-30 | 2025-08-30 | 2025-08-30 | A | 0
[26 empty] | 7 | Complete Earthworks |  | 2026-09-15 | 2026-09-15 | 2026-08-25 | F | 21
[26 empty] | 8 | Complete all Wet Networks |  | 2026-11-22 | 2026-11-22 | 2026-12-17 | F | -25
[26 empty] | 9 | Complete Electrical Works |  | 2026-11-24 | 2026-11-24 | 2026-12-21 | F | -27
[26 empty] | 10 | Complete all Works including Testing & Commissioning, Cleanup, Closeout Documentation and Ready for Initial Handover |  | 2027-01-14 | 2027-01-14 | 2027-02-14 | F | -31
[26 empty] | 11 | Complete Demobilization |  | 2027-01-25 | 2027-01-25 | 2027-02-24 | F | -30
[26 empty] | 12 | Project Handover |  | 2027-01-29 | 2027-01-29 | 2027-03-01 | F | -31
Performance overview
Submittals Status | [10 empty] | Quality | [10 empty] | Safety
Shop Drawings | [10 empty] | Quality Reports | [10 empty] | Safety Statistics | [7 empty] | Proactive Vs Reactive Actions Taken
Item Per WBS |  | Total | Total Submitted Drawings |  |  |  |  | Remaining | Pending | Total Submittals | Quality Reports |  | Issued | Closed | Pending | Avg. Closing (Days) | Pending |  |  |  |  | Category | Item |  | This Week |  | This Month | Year to Date | Cumulative
|  |  | A | B | C | D | Processed | [9 empty] | 0-10 Days | 11-20 Days | 21-30 Days | 31-60 Days | > 60 Days
CVL |  | 1063 | 8 | 1055 | 0 | 0 | 1063 | 0 | 0 | 1063 | [11 empty] | General | Total Hours Worked |  | 34740 |  | 104220 | 809664 | 874722 |  |  | Proactive | 6
Mech |  | 212 | 0 | 212 | 0 | 0 | 212 | 0 | 0 | 212 | Non Conformance (NCR) |  | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | Safe Hours Worked |  | 34740 |  | 104220 | 809664 | 874722 |  |  | Reactive | 0
Elec |  | 41 | 0 | 41 | 0 | 0 | 41 | 0 | 0 | 41 | Site Instruction (SIR) |  | 52 | 42 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | Reactive | LTI |  | 0 |  | 0 | 0 | 0
Landscape & Arch |  | 458 | 0 | 458 | 0 | 0 | 458 | 0 | 0 | 458 | Material Inspection (MIR) |  | 116 | 113 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  | MTC (Healed w/o Disability) |  | 0 |  | 0 | 0 | 0
[11 empty] | Field Inspection (FIR) |  | 4699 | 4481 | 218 | 0 | 0 | 0 | 0 | 0 | 0 |  | MTC (Healed w/ Disability) |  | 0 |  | 0 | 0 | 0
TOTAL |  | 1774 | 8 | 1766 | 0 | 0 | 1774 | 0 | 0 | 1774 | Key Submittals Approval Status | [11 empty] | Near Miss |  | 0 |  | 0 | 0 | 0
Material Approval | [10 empty] | 1 Quality Plan Approval |  |  | 2024-02-24 |  | 6 Baseline Approval |  |  |  | 2024-03-10 |  |  | First Aid Cases |  | 0 |  | 0 | 0 | 0 | Total Hours Worked Vs Safe Hours Worked
Item Per WBS |  | Total | Total Submitted Material |  |  |  |  | Remaining to approve | Pending | Total Submittals | 2 Quality Plan Last Up |  |  | 2024-02-24 |  | 7 No of Approved Version of Schedule |  |  |  | 1 |  |  | Fatality |  | 0 |  | 0 | 0 | 0
|  |  | A | B | C | D | Processed | with Designer |  |  | 3 Safety Plan Approval |  |  | 2024-02-28 |  | 8 Last Approved Schedule |  |  |  | 2024-03-10 |  |  | Fire Incident Cases |  | 0 |  | 0 | 0 | 0
Civil & Roads |  | 77 | 2 | 74 | 3 | 1 | 76 | 1 | 4 | 84 | 4 Safety Plan Last Up |  |  | 2024-02-28 |  | 9 BOQ Approval Date |  |  |  | 0 |  |  | Vehicle Incident |  | 0 |  | 0 | 0 | 0
Electrical |  | 30 | 0 | 22 | 0 | 0 | 22 | 8 | 0 | 22 | 5 Construction Plan Approval |  |  | 2024-02-26 |  | 10 No of Approved Version of BOQ |  |  |  | 1 |  |  | Property Damages |  | 0 |  | 0 | 0 | 0
Mechanical |  | 48 | 0 | 41 | 0 | 2 | 41 | 7 | 3 | 46 | Invoices Summary | [10 empty] | Proactive | Induction Training |  | 7 |  | 69 | 114(571) | 148(895)
[11 empty] | Total Submitted Invoices |  | 7 | Submitted Invoices (SAR) |  |  | 62889673.529 |  | Contract Value (SR) | 198906162.61 |  |  | No.of Internal Training |  | 1 (6) |  | 3 (11) | 6(29) | 14(104)
[11 empty] | PM Approved Invoices |  | 0 | PM Approved Invoices (SAR) |  |  | 0 |  | Planned Value (SR) | 140538384.61 |  |  | No.of Internal Audit |  | 0 |  | 1 | 4 | 4
TOTAL |  | 155 | 2 | 137 | 3 | 3 | 139 | 16 | 7 | 152 | No of Paid Invoices |  | 0 | Paid Invoices (SAR) |  |  | 0 |  | Earned Value (SR) | 108337412.25 |  |  | No. of Toolbox Talks |  | 3(355) |  | 3(648) | (43(3442) | 56(8671)
Procurement Summary | [10 empty] | No of Pending Invoices |  | 0 | Last Submitted Period |  |  | 2026-09-15 |  | Submitted (SAR) | 62889673.529 |  |  | Safety Awards/Incentives |  | 0 |  | 0 | 1 | 2
Item Per WBS |  | Total Materials | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Material on Site | Remaining Materials | Material Delivery Completion (Date) |  |  | Advance Payment % |  | 0% | Advance Payment (SAR) |  |  | 0 |  | PM Approved (SAR) | 0 |  | Latest Contract Change Order Log
|  |  | A | B | C | D | Processed |  |  |  | Retention % |  | 0% | Retention (SAR) |  |  | 0 |  | Total Paid (SAR) | 0
Civil & Roads |  | 77 | 77 | 76 | 1 | 55 | 22 | 2026-11-09 |  |  | Deduction / Penalties % |  | 0.05254% | Deduction / Penalties (SAR) |  |  | -104500 |  |  |  |  | CCO No. | Date Added | Description of Change |  |  |  |  | Status | Cost | Sch Impact (Months) | Date Approved | Duration
Electrical |  | 30 | 30 | 22 | 0 | 17 | 13 | 2026-09-27 |  |  | Resources at Site
Mechanical |  | 48 | 48 | 42 | 0 | 25 | 23 | 2026-09-28 |  |  | Head Count - Non Manual |  |  |  | Head Count - Manual |  |  |  | Total Head Count |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
[11 empty] | Planned | Actual | Next Month Forecast | Saudi Staff | Planned | Actual | Next Month Forecast | Saudi Staff | Total Plan | Total Actual | Variance
[11 empty] | 35 | 57 | 117 | 4 | 360 | 483 | 560 | 0 | 395 | 540 | 145
TOTAL |  | 48 | 48 | 42 | 0 | 25 | 23 | 2026-11-09 |  |  | Manpower Breakdown by Trade | [6 empty] | Major Equipment
Primavera P6 Schedule Status | [10 empty] | Key Trade | Planned | Actual |  |  |  |  | Type | Planned | Actual | Idle
Project Activities Overview | [10 empty] | General Labor | 120 | 119 |  |  |  |  | Excavator | 22 | 23 | 0
Schedule Statistics |  |  |  |  | Active Schedule Activities | [5 empty] | Carpenter | 15 | 68 |  |  |  |  | Loader | 8 | 13 | 0 | Major Quantity Trackers
Total Act. | Not Started | In Progress | Completed | % | Active | Ahead | On | Behind | Flag | 0 | Plumber | 16 | 33 |  |  |  |  | W.Tanker | 14 | 18 | 0 | BOQ N0. | Item Description |  |  |  |  | Total Qty | Measu Unit | Plan to Date | Act to Date | Remaining | Variance
4851 | 1938 | 431 | 2482 | 51.16% | 431 | 10 | 1639 | 202 | 1447 |  | Operator | 125 | 237 |  |  |  |  | Dumper | 28 | 163 | 0 | B1.1.31 23 19.01 | Surface Dewatering |  |  |  |  | 1 | Unit | 1 | 1 | 0 | 0
Critical Path Activities |  |  | Free Float Management (Total) |  |  |  | Failed Start Activities |  |  |  | Surveyor | 14 | 9 |  |  |  |  | Dozer | 8 | 10 | 0 | B1.1.31 23 16.01 | All Excavation |  |  |  |  | 853395 | m³ | 853395 | 825820.73 | 27574.27 | -27574.27
|  |  | Greater Than 14 Days |  | Less Than 14 Days | [5 empty] | Others | 70 | 17 |  |  |  |  | Grader | 8 | 8 | 0 | B1.1.31 23 23.01 | All Backfilling |  |  |  |  | 1481028.01 | m³ | 1481028.01 | 1356040.32 | 124987.69 | -124987.69
Last Week | This Week | Diff | Last Week | This Week | Last Week | This Week | Last Week | This Week | Flag | 0 | [7 empty] | Other | 62 | 91 | 0 | B1.2.32 11 26.01 | Asphalt (Base+Wearing) |  |  |  |  | 64334 | m³ | 55840.97 | 25855.83 | 38478.17 | -29985.14
45 | 45 | 0 | 490 | 527 | 2019 | 1840 | 993 | 1047 | -54 |  | Total | 360 | 483 |  |  |  |  | Total | 150 | 326 | 0 | 33 31 00 | Sew. Pipes |  |  |  |  | 7567.08 | Lm | 2.01 | 6773.83 | 793.25 | 6771.82
Weekly Prgoress Photos | [15 empty] | Top Issues and Risks
Road & Plots Works |  |  |  |  | Wet Utilities |  |  | Pump & Lift Station |  |  | Dry Utilities |  |  |  |  | Top 5 Issues
[16 empty] | Issue No | Date Identified | Issue Description |  |  |  | Responsible | Action Taken |  |  | Mitigation |  |  |  |  | Current Status | Expected/Actual Closure | Duration Elapsed
[16 empty] | 1 | 2026-04-01 | قلة عدد العمالة والمعدات و توقف مقاول الباطن |  |  |  | Contractor | جاري اسناد جزء من المشروع لمقاول آخر و جاري توفير عمالة من الشركة لاستكمال الاعمال المتبقية حيث ان عدد العمالة الحالي 304 والمعدات 184 معدة والمضخات الى 30 مضخة نزح ,و وجوب استمرار زيادة العمالة والمعدات لتحقيق مستهدفات مدن | [7 empty] | Open | 2026-05-01 | 202
[16 empty] | 2 | 2026-06-01 | تأخر أعمال العبارة بالطريق الشرياني |  |  |  | Contractor | جاري الانتهاء من الحدادة ل 16 فواصل وصب قاعدة لعدد 03 فاصل تم حفر 14 و جاري 03 فواصل أخرى | [7 empty] | Open | 2026-07-01 | 141
[16 empty] | 3 | 2026-06-01 | ضرورة الانتهاء من تنفيذ الشبكات لتحقيق جاهزية الموقع وبدء أعمال الطرق |  |  |  | Other | تم استبعاد مقاول الباطن يوناسكو و سحب اعتماده لعدم وفاءه بمستهدفات مدن و على المقاول العمل بشكل مباشر على الشبكات او تقديم مقاول باطن للاعتماد | [7 empty] | Open | 2026-07-01 | 141
[16 empty] | 4 | [6 empty] | 0
[16 empty] | 5 | [6 empty] | 0
Formulas:
Earned = MAX(I80:[Earned, row above])
8,984,239

## General Information
Weekly Progress Report - Construction Projects |  |  | Data Date | 2026-10-20 | 2026-10-27
Contract General Information
Project Name | Development of Infrastructure for phase 1 of the Logistics area at the 2nd Industrial City in Dammam
Project ID | DAM2-02-009
Contractor | Shibh Aljazira Contracting Company
Consultant | Egis
Stage | Construction
Status | Active
Modon PM | Muhammad H Al-Essa
Key Dates
Contract Award Date | 2025-06-30
Contract Sign Date | 2025-07-14
Site Handover Date | 2025-07-30
Original Completion | 2027-01-29
Contract Award Date (Hijri) | 2025-06-30
Contract Sign Date (Hijri) | 2025-07-14
Site Handover Date (Hijri) | 2025-07-30
Original Completion (Hijri) | 2027-01-29
Revised Completion Date | 2027-01-29
Committed Completion Date | 2027-01-29
Forecast Completion | 2027-02-14
Variance | -16
Key Project Submittals | Submission Date | Days taken to approve orginal plan from site handover date
Quality Plan submission | 2024-02-22 | -524
Quality Plan approval | 2024-02-24
Quality Plan Last Update | 2024-02-24
Safety Plan submission | 2024-02-23 | -523
Safety Plan approval | 2024-02-28
Safety Plan Last Update | 2024-02-28
Risk Management Plan submission | 2024-02-23 | -523
Risk Management Plan approval | 2024-02-28
Risk Management Plan Last Update | 2024-02-28
Baseline Schedule submission | 2024-02-12 | -534
Baseline Schedule approval | 2024-03-10
No of Schedule Versions | 1
Last Recovery Schedule Approval Date | 2024-03-10
BOQ submission |  | -46416
BOQ approval
No of Approved Version of BOQ | 1
Construction Plan submission | 2024-02-24 | -522
Construction Plan Approval | 2024-02-26
Note on D25: AlNuaim, Abdulaziz: As per contract requirments submission of Plans should be 30 days after site handover

## Progress
Project Scope Statement | The project consists of the wet networks mainlines (Sewerage, Storm, Potable, Firefighting & TSE) including the force main line, in addition to the dry networks (Medium Voltage, Low Voltage, Street Lighting & Telecommunication) road crossings & main line connections, scope also included supply, install, testing & commissioning for the potable water pump station and the sewage lift station and implementation of guard rooms and applying all the road earth layers till the asphalt wearing coarse for the project scope area internal roads & finishing the landscape | [13 empty] | Data Date | 2026-10-20
Earned Value Progress (SAR) | [8 empty] | Physical Progress (Effort)
WBS |  | BOQ Value (SAR) | % Wt. | Weekly (SAR) |  |  | To Date (SAR) |  | Budgeted | % Wt. | Weekly Physical Progress |  | To Date Physical Progress
|  |  |  | Planned | Earned | Original Plan | Planned | Earned | (Manhours) |  | Planned | Earned | Planned | Earned
Demolishing & Site Clearing |  | 457401.18 | 0.23% | 0 | 0 | 457401.18 | 457401.18 | 457401.18 | 3437.41 | 0.3735% | 0 | 0 | 3437.41 | 3437.41
Earthworks & Site Grading |  | 31040591.65 | 15.61% | 0 | 0 | 31040591.65 | 31040591.65 | 29924053.16 | 22808.8 | 2.479% | 0 | 0 | 22808.8 | 21945.45
Sewerage Network |  | 5111121.83 | 2.57% | 22221.96 | 19950.12 | 5091236.27 | 5091236.27 | 4581972.17 | 74260.44 | 8.07% | 1004.45 | 217.98 | 63844.93 | 61523.35
Engineering |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 568.6 | 0.06179% | 0 | 0 | 568.6 | 568.6
Procurement |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 10403.33 | 1.131% | 0 | 0 | 10403.33 | 10403.33
Construction |  | 5111121.83 | 2.57% | 22221.96 | 19950.12 | 5091236.27 | 5091236.27 | 4581972.17 | 53551.26 | 5.819% | 1004.44 | 217.98 | 52872.99 | 44059.92
Testing & Commissioning |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 9737.25 | 1.058% | 0 | 0 | 0 | 6491.5
Storm Water Network |  | 21808728.44 | 10.96% | 373528.76 | 544011.74 | 20893008.47 | 20893008.47 | 18936432.18 | 143781.21 | 15.62% | 2050.16 | 5276.51 | 126434.17 | 118557.55
Engineering |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 984.12 | 0.1069% | 0 | 0 | 984.12 | 984.12
Procurement |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 14474.2 | 1.573% | 0 | 0 | 14474.2 | 14474.2
Construction |  | 21808728.44 | 10.96% | 373528.76 | 544011.74 | 20893008.47 | 20893008.47 | 18936432.18 | 118164.9 | 12.84% | 2050.16 | 5276.51 | 110975.85 | 96607.73
Testing & Commissioning |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 10157.99 | 1.104% | 0 | 0 | 0 | 6491.5
Potable Water Network |  | 1954044.36 | 0.9824% | 247588.8 | 0 | 1829021.1 | 1829021.1 | 1060337.72 | 57934.51 | 6.296% | 2338.75 | 0 | 45314.91 | 34572.01
Engineering |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 583.28 | 0.06338% | 0 | 0 | 583.28 | 583.28
Procurement |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 12873.59 | 1.399% | 0 | 0 | 12873.59 | 12664.83
Construction |  | 1954044.36 | 0.9824% | 247588.8 | 0 | 1829021.1 | 1829021.1 | 1060337.72 | 34379.75 | 3.736% | 2338.74 | 0 | 31858.03 | 21323.9
Testing & Commissioning |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 10097.89 | 1.097% | 0 | 0 | 0 | 0
Fire Fighting Network |  | 4678456.73 | 2.352% | 222667.04 | 0 | 4154735.3 | 4154735.3 | 3069245.61 | 63346.29 | 6.884% | 1054.05 | 0 | 46946.75 | 35344.31
Engineering |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 481.12 | 0.05228% | 0 | 0 | 481.12 | 481.12
Procurement |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 13221.63 | 1.437% | 0 | 0 | 13221.63 | 13221.63
Construction |  | 4678456.73 | 2.352% | 222667.04 | 0 | 4154735.3 | 4154735.3 | 3069245.61 | 39485.54 | 4.291% | 1054.04 | 0 | 33243.99 | 21641.56
Testing & Commissioning |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 10157.99 | 1.104% | 0 | 0 | 0 | 0
TSE Network |  | 2995733.64 | 1.506% | 7624.54 | 4798.13 | 2890249.63 | 2890249.63 | 691639.78 | 48137.98 | 5.231% | 2756.68 | 280.57 | 30407.13 | 21771.81
Engineering |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 1075.88 | 0.1169% | 0 | 0 | 1075.88 | 1075.88
Procurement |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 15761.57 | 1.713% | 2154.03 | 0 | 11248.32 | 14327.72
Construction |  | 2995733.64 | 1.506% | 7624.54 | 4798.13 | 2890249.63 | 2890249.63 | 691639.78 | 21142.54 | 2.298% | 602.65 | 280.57 | 18082.93 | 6368.22
Testing & Commissioning |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 10157.99 | 1.104% | 0 | 0 | 0 | 0
Potable Water Pump Station |  | 11076181.82 | 5.569% | 871038.9 | 0 | 7778556.94 | 7778556.94 | 1734353.19 | 71778.26 | 7.8% | 3916.8 | 0 | 55212.98 | 48814.42
Engineering |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 5518 | 0.5996% | 0 | 0 | 5518 | 5474.26
Procurement |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 44188.07 | 4.802% | 2635.63 | 0 | 42867.65 | 41576.45
Construction |  | 11076181.82 | 5.569% | 871038.9 | 0 | 7778556.94 | 7778556.94 | 1734353.19 | 14498.77 | 1.576% | 1281.17 | 0 | 6827.33 | 1763.71
Testing & Commissioning |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 7573.41 | 0.823% | 0 | 0 | 0 | 0
Sewerage Lift Station |  | 4985124.69 | 2.506% | 407169.42 | 57598.58 | 798505.73 | 798505.73 | 115223.71 | 70758.97 | 7.689% | 4814.7 | 272.87 | 59468.75 | 49496.9
Engineering |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 7363.85 | 0.8002% | 0 | 0 | 7363.85 | 7363.85
Procurement |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 46623.63 | 5.067% | 3091.75 | 0 | 46542.45 | 41175.54
Construction |  | 4985124.69 | 2.506% | 407169.42 | 57598.58 | 798505.73 | 798505.73 | 115223.71 | 9198.08 | 0.9995% | 1722.96 | 272.86 | 5562.46 | 957.51
Testing & Commissioning |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 7573.41 | 0.823% | 0 | 0 | 0 | 0
Medium Voltage Network |  | 5452229.25 | 2.741% | 269033.47 | 406639.88 | 4451469.67 | 4451469.67 | 1895375.67 | 34290.88 | 3.726% | 3548.97 | 2139.67 | 23559.75 | 16079.61
Engineering |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 415.52 | 0.04515% | 0 | 0 | 415.52 | 415.52
Procurement |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 11655.91 | 1.267% | 103.82 | 0 | 11638.6 | 11467.1
Construction |  | 5452229.25 | 2.741% | 269033.47 | 406639.88 | 4451469.67 | 4451469.67 | 1895375.67 | 16449.24 | 1.788% | 3445.15 | 2139.66 | 11505.63 | 4196.99
Testing & Commissioning |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 5770.22 | 0.627% | 0 | 0 | 0 | 0
Low Voltage Network |  | 1876943.13 | 0.9436% | 391820.55 | 108822.6 | 1463373.35 | 1463373.35 | 125449.44 | 31587.58 | 3.433% | 2909.49 | 4155.36 | 18110.79 | 11200.92
Engineering |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 328.04 | 0.03565% | 0 | 0 | 328.04 | 328.04
Procurement |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 5984.53 | 0.6503% | 0 | 0 | 5984.53 | 5859.94
Construction |  | 1876943.13 | 0.9436% | 391820.55 | 108822.6 | 1463373.35 | 1463373.35 | 125449.44 | 19264.37 | 2.093% | 2909.49 | 4155.37 | 11798.22 | 5012.95
Testing & Commissioning |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 6010.65 | 0.6532% | 0 | 0 | 0 | 0
Street Lighting Network |  | 8486130.58 | 4.266% | 551969.82 | 1341942.58 | 3936228.49 | 3936228.49 | 2858226.78 | 76760.06 | 8.341% | 3939.88 | 5046.15 | 37091.48 | 25724.17
Engineering |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 430.1 | 0.04674% | 0 | 0 | 430.1 | 430.1
Procurement |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 15657.19 | 1.701% | 55.67 | 0 | 15657.19 | 15162.79
Construction |  | 8486130.58 | 4.266% | 551969.82 | 1341942.58 | 3936228.49 | 3936228.49 | 2858226.78 | 51656.8 | 5.613% | 3884.2 | 5046.15 | 21004.19 | 10131.28
Testing & Commissioning |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 9015.97 | 0.9798% | 0 | 0 | 0 | 0
Telecommunication Network |  | 4454965.57 | 2.24% | 551193.35 | 114597.64 | 3054463.68 | 3054463.68 | 1079952.36 | 62092.94 | 6.748% | 6921.42 | 1356.84 | 36756.61 | 16818.91
Engineering |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 306.17 | 0.03327% | 0 | 0 | 306.17 | 306.17
Procurement |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 5427.83 | 0.5898% | 0 | 0 | 5427.83 | 5427.83
Construction |  | 4454965.57 | 2.24% | 551193.35 | 114597.64 | 3054463.68 | 3054463.68 | 1079952.36 | 50588.72 | 5.497% | 6921.42 | 1356.85 | 31022.61 | 11084.92
Testing & Commissioning |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 5770.22 | 0.627% | 0 | 0 | 0 | 0
Road Works |  | 79068381.04 | 39.75% | 4694358.02 | 336968.14 | 52058577.55 | 52058577.55 | 41659930.91 | 80303.58 | 8.726% | 10540.52 | 314.34 | 46630.85 | 27615.16
Engineering |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 1297.71 | 0.141% | 0 | 0 | 1297.71 | 1297.71
Procurement |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 16700.9 | 1.815% | 2469.05 | 0 | 12469.27 | 13806.06
Construction |  | 79068381.04 | 39.75% | 4694358.02 | 336968.14 | 52058577.55 | 52058577.55 | 41659930.91 | 62304.97 | 6.771% | 8071.46 | 314.35 | 32863.86 | 12511.39
Landscape |  | 14727629.51 | 7.404% | 343486.94 | 0 | 485726.4 | 485726.4 | 98475.6 | 44855.31 | 4.874% | 2273.25 | 0 | 8856.02 | 14158.54
Engineering |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 2792.71 | 0.3035% | 0 | 0 | 2792.71 | 2792.71
Procurement |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 12873.69 | 1.399% | 313.15 | 0 | 3415.59 | 11076.59
Construction |  | 14727629.51 | 7.404% | 343486.94 | 0 | 485726.4 | 485726.4 | 98475.6 | 29188.91 | 3.172% | 1960.1 | 0 | 2647.72 | 289.24
Guard Rooms |  | 539598.47 | 0.2713% | 49393.51 | 0 | 155239.2 | 155239.2 | 49342.79 | 34095.79 | 3.705% | 2848.95 | 0 | 29294.65 | 25734.12
Engineering |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 5461.9 | 0.5935% | 0 | 0 | 5461.9 | 4762.08
Procurement |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 22615.94 | 2.458% | 2412.37 | 0 | 21050.22 | 19701.96
Construction |  | 539598.47 | 0.2713% | 49393.51 | 0 | 155239.2 | 155239.2 | 49342.79 | 6017.94 | 0.654% | 436.59 | 0 | 2782.53 | 1270.07
Provisional Sum |  | 192900.72 | 0.09698% | 0 | 0 | 0 | 0 | 0
Closeout |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0
| Total | 198906162.61 | 99.9% | 9003095.08 | 2935329.41 | 140538384.61 | 140538384.61 | 108337412.25 | 920230.01 | 100% | 50918.07 | 19060.29 | 654175.98 | 532794.64
|  |  |  | 4.526% | 1.476% | 70.66% | 70.66% | 54.47% |  |  | 5.533% | 2.071% | 71.09% | 57.9%
OK
`

## Weekly Photos
Date | 2026-10-20
Road & Plots Works |  |  | Dry Utilities
Wet Utilities |  | Pump & Lift Station |  | Box Culvert

## FIR Summary
Project Name |  | Development of Infrastructure for phase 1 of the Logistics area at the 2nd Industrial City in Dammam | [5 empty] | Total FIR Amount
Project ID |  | DAM2-02-009 | DAM2-02-009 | Project Budget | 198906162.61 |  |  | 84260706.8929
Date Pariod |  | Start Date | 2026-10-14 | To | Data Date | 2026-10-20
BOQ Item # | BOQ Description | FIR # | Date | FIR Description | Unit Rate | Current Pariod Quantity | Total (SR) | Comments
42.36%
B1.1.02 41 00.01 | Removal of curbstone | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0049-00 | 2025-12-07 | FIR for Removal of Existing curb stone as per attached as built Drawing DATA.Zone-1& 2.part 02. as highlighted in attached drawing | 7.902 | 1423.44 | 11248.0229
B1.1.02 41 00.01 | Removal of curbstone | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0060-00 | 2025-12-14 | FIR for Removal of Existing curb stone (Double) as per attached as built Drawing DATA.Zone-1& 2 | 7.902 | 2838.3 | 22428.2466
B1.1.02 41 00.01 | Removal of curbstone | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0679-00 | 2026-10-12 | FIR for Removal of Existing Service Road curb stone as per attached as built Drawing DATA. @ Service Road - Zone-1 | 7.902 | 1426.958 | 11275.8221
B1.1.02 41 00.03 | Removal of concrete protection | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0036-00 | 2025-12-02 | FIR for Removal of Existing curb stone as per attached as built Drawing DATA.Zone-1& 2.part 01. as highlighted in attached drawing | 28.974 | 3059.48 | 88645.3735
B1.1.31 23 16.01 | Excavation (all types of soil) | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0013-01 | 2025-11-23 | FIR for the PLOTS NO 4 - Replacement 50 cm | 14.926 | 27560.913 | 411374.1874
B1.1.31 23 16.01 | Excavation (all types of soil) | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0015-00 | 2025-11-23 | FIR for the PLOT No 5 -Replacement 50 cm | 14.926 | 11444.048 | 170813.8604
B1.1.31 23 16.01 | Excavation (all types of soil) | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0017-00 | 2025-11-26 | FIR for the cutting of Plot # 04 up to the depth from top of adjoining side Asphalt Road - 0.8 @ Zone-1 | 14.926 | 16997.485 | 253704.4611
B1.1.31 23 16.01 | Excavation (all types of soil) | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0018-01 | 2025-12-01 | FIR for the cutting of Plot # 05 (PGL-0.8) @ Zone-1 | 14.926 | 9500.5 | 141804.463
B1.1.31 23 16.01 | Excavation (all types of soil) | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0019-01 | 2025-12-01 | FIR for replacement cutting for Part-1 of Plot # 01 as per attached Level Sheet (NGL-VAR) @ Zone-1 | 14.926 | 249.457 | 3723.3952
B1.1.31 23 16.01 | Excavation (all types of soil) | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0020-01 | 2025-12-01 | FIR for replacement cutting of Part-01 Of Plot # 02 for fill Area as per attached Level Sheet (NGL- VAR) @ Zone-4 | 14.926 | 1548.02 | 23105.7465
B1.1.31 23 16.01 | Excavation (all types of soil) | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0021-01 | 2025-12-01 | FIR for replacement cutting for Part-01 OF Plot # 03 for fill area as per attached Level Sheet (NGL- VAR) @ Zone-4 | 14.926 | 883.95 | 13193.8377
B1.1.31 23 16.01 | Excavation (all types of soil) | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0026-01 | 2025-12-01 | cutting (PGL- 0.8) for Part-01 of Plot # 01 as per attached Level Sheet @ Zone-4 | 14.926 | 23527.23 | 351167.435
B1.1.31 23 16.01 | Excavation (all types of soil) | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0027-01 | 2025-12-01 | Survey FIR for cutting (PGL - 0.8) for Part-01 Of Plot # 02 as per attached Level Sheet @ Zone-4 | 14.926 | 7677.069 | 114587.9319
B1.1.31 23 16.01 | Excavation (all types of soil) | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0028-01 | 2025-12-01 | FIR for cutting ( PGL-0.8 ) for Part-01 OF Plot # 03 as per attached Level Sheet @ Zone-4 | 14.926 | 23805.69 | 355323.7289
B1.1.31 23 16.01 | Excavation (all types of soil) | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0043-00 | 2025-12-10 | FIR for replacement cutting for Part-02 OF Plot # 02 for fill area as per attached Level Sheet (NGL- 0.5) @ Zone-4 | 14.926 | 9781.38 | 145996.8779
B1.1.31 23 16.01 | Excavation (all types of soil) | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0044-00 | 2025-12-13 | Survey FIR for Fill area REPLACMENT CUT -Variable from NGL in Plot 7 Part 1 | 14.926 | 9354.77 | 139629.297
B1.1.31 23 16.01 | Excavation (all types of soil) | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0045-00 | 2025-12-13 | Survey FIR for Fill area REPLACMENT CUT –(Variable) from NGL in Plot 7 Part 2 | 14.926 | 6427.74 | 95940.4472
B1.1.31 23 16.01 | Excavation (all types of soil) | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0058-00 | 2025-12-15 | Inspection for survey work in Cut area NGL-PGL-0.80 plot 7-part 1 | 14.926 | 1516.58 | 22636.4731
B1.1.31 23 16.01 | Excavation (all types of soil) | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0059-00 | 2025-12-15 | Inspection for survey work in Cut area NGL-PGL-0.80 plot 4-part 2 | 14.926 | 9620.92 | 143601.8519
B1.1.31 23 16.01 | Excavation (all types of soil) | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0060-00 | 2025-12-15 | Inspection for survey work in Cut area NGL-PGL-0.80 plot 7-part 2 | 14.926 | 39545.05 | 590249.4163
B1.1.31 23 16.01 | Excavation (all types of soil) | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0084-00 | 2025-12-29 | Inspection for Survey works for Fill area REPLACMENT CUT -0.50 m from NGL, plot 7 (part 3). | 14.926 | 10453.44 | 156028.0454
B1.1.31 23 16.01 | Excavation (all types of soil) | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0085-00 | 2025-12-29 | FIR for (Replacement cut – Variable) @ (Plot-3, Part-2) zone-4 | 14.926 | 9594.09 | 143201.3873
B1.1.31 23 16.01 | Excavation (all types of soil) | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0086-00 | 2025-12-30 | FIR OF Replacement cut for fill Area (NGL– Variable) @ Plot-2 (Part-3) zone-4 | 14.926 | 4872.491 | 72726.8007
B1.1.31 23 16.01 | Excavation (all types of soil) | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0093-00 | 2026-01-18 | Survey FIR for Cut Area from NGL to PGL – 0.80 meter for plot 7, (part 3). | 14.926 | 27752.2 | 414229.3372
B1.1.31 23 16.01 | Excavation (all types of soil) | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0094-00 | 2026-01-19 | FIR for cutting (PGL - 0.8) for Part-02 Of Plot # 03 as per attached Level Sheet @ Zone-4 | 14.926 | 37281.47 | 556463.2212
B1.1.31 23 16.01 | Excavation (all types of soil) | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0120-00 | 2026-02-02 | Inspection for Survey works for Fill area Replacement Cut -0.50 m from NGL Plot 7 (Part-4) | 14.926 | 12084.67 | 180375.7844
B1.1.31 23 16.01 | Excavation (all types of soil) | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0143-00 | 2026-02-12 | FIR OF Replacement cut (NGL-Variable) for fill Area Plot 6 (Part-1). | 14.926 | 9353.67 | 139612.8784
B1.1.31 23 16.01 | Excavation (all types of soil) |  | 2026-06-23 | As-built Qty for IPC-5 | 14.926 | 27104.1656 | 404556.7751
B1.1.31 23 16.01 | Excavation (all types of soil) |  | 2026-07-12 | As-built Qty for IPC-6 | 14.926 | 16859.7154 | 251648.1127
B1.1.31 23 19.01 | Surface Dewatering | DAM2-02-09-SAJ-TS9-1-CVL-FIR-0001 | 2025-12-15 | FIR for 35 % DONE External surface Dewatering from Zone-04 to outside. | 2897400 | 0.345 | 999603
B1.1.31 23 19.01 | Surface Dewatering | DAM2-02-09-SAJ-TS9-1-CVL-FIR-0002 | 2026-01-25 | FIR for 35 % DONE External surface Dewatering from Zone-04 to outside. | 2897400 | 0.355 | 1028577
B1.1.31 23 19.01 | Surface Dewatering | DAM2-02-09-SAJ-TS9-1-CVL-FIR-0003 | 2026-06-10 | FIR for 30 % DONE External surface Dewatering | 2897400 | 0.3 | 869220
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0022-00 | 2025-11-27 | Survey and compaction testing for (30cm) fill of layer- 01 @ Plot 4 | 28.096 | 18402.62 | 517040.0115
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0023-00 | 2025-11-27 | Survey and compaction testing for (30cm) fill of layer- 01 @ Plot 5 | 28.096 | 7868.85 | 221083.2096
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0029-01 | 2025-12-01 | Survey and compaction testing for (30cm) fill of layer- 03 @ Plot 4 | 28.096 | 105 | 2950.08
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0032-00 | 2025-12-03 | Survey and compaction testing for (30cm) fill of layer- 04 @ Plot 5 | 28.096 | 1133.61 | 31849.9066
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0033-00 | 2025-12-04 | Survey and compaction testing for (30cm) fill of layer- 05 @ Plot 5 | 28.096 | 694.79 | 19520.8198
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0034-00 | 2025-12-03 | Survey and compaction testing for (30cm) fill of layer- 04 @ Plot 4 | 28.096 | 994.59 | 27944.0006
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0035-00 | 2025-12-03 | Survey and compaction testing for (30cm) fill of layer- 05 @ Plot 4 | 28.096 | 853.98 | 23993.4221
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0036-00 | 2025-12-04 | Survey and compaction testing for (30cm) fill of layer- 06 @ Plot 4 | 28.096 | 791.39 | 22234.8934
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0037-00 | 2025-12-06 | Survey and compaction testing for (30cm) fill of layer- 07 @ Plot 4 | 28.096 | 1480.64 | 41600.0614
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0038-00 | 2025-12-07 | Survey and compaction testing for (30cm) fill of layer- 08 @ Plot 4 | 28.096 | 2991.73 | 84055.6461
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0039-00 | 2025-12-08 | Survey and compaction testing for (30cm) fill of layer- 09 @ Plot 4 | 28.096 | 3726.79 | 104707.8918
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0040-00 | 2025-12-09 | Survey and compaction testing for (30cm) fill of layer- 10 @ Plot 4 | 28.096 | 4626.39 | 129983.0534
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0041-00 | 2025-12-09 | Survey and compaction testing for (30cm) fill of layer- 11 @ Plot 4 | 28.096 | 5494.15 | 154363.6384
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0042-00 | 2025-12-10 | Survey and compaction testing for (30cm) fill of layer- 06 @ Plot 5 | 28.096 | 841.07 | 23630.7027
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0046-00 | 2025-12-13 | Survey and compaction testing FIR for (30cm) fill layer- 01 at Part-1 of Plot # 01, Zone-04 | 28.096 | 12.48 | 350.6381
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0047-00 | 2025-12-13 | Survey and compaction testing for (30cm) fill of layer- 12 @ Plot 4 | 28.096 | 7635.36 | 214523.0746
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0049-00 | 2025-12-14 | Survey and compaction testing FIR for (30cm) fill layer- 01 at Part-1 of Plot # 01, Zone-04 | 28.096 | 15 | 421.44
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0050-00 | 2025-12-15 | Survey and compaction testing for (30cm) fill of layer- 13 @ Plot 4 | 28.096 | 8183.13 | 229913.2205
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0051-00 | 2025-12-15 | Inspection for survey works and compaction testing for the 14th fill layer (30 cm) at Plot 4 | 28.096 | 9293.79 | 261118.3238
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0053-00 | 2025-12-15 | Inspection for survey works and compaction testing for the 2nd fill layer (30 cm) at Plot 7 (Part 1)-1 | 28.096 | 72.51 | 2037.241
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0057-00 | 2025-12-15 | Inspection for survey works and compaction testing for the 2nd fill layer (30 cm) at Plot 2 Part-1 & 2 | 28.096 | 406.98 | 11434.5101
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0061-00 | 2025-12-16 | Inspection for Survey and compaction testing for 15th layer fill (30cm) at Plot 4 | 28.096 | 10763.37 | 302407.6435
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0062-00 | 2025-12-16 | Inspection for the Survey and compaction testing for 3rd layer (30cm) fill at Plot 7 (Part 1)-1 | 28.096 | 45 | 1264.32
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0063-00 | 2025-12-16 | Inspection for Survey and compaction testing for 4th layer (30cm) fill at Plot 7 (Part 1)-1 | 28.096 | 45 | 1264.32
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0067-00 | 2025-12-17 | Inspection for Survey and compaction testing for 5th layer (30cm) fill at Plot 7 (Part 1)-1 | 28.096 | 105.75 | 2971.152
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0068-00 | 2025-12-17 | Survey and compaction testing for (30cm) fill of layer- 16 @ Plot 4 | 28.096 | 11925.04 | 335045.9238
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0069-00 | 2025-12-17 | Survey and compaction testing FIR for (30cm) fill layer- 03 at Part-1 of Plot # 01, Zone-04 | 28.096 | 59.5 | 1671.712
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0070-00 | 2025-12-17 | Survey and compaction testing FIR for (30cm) fill layer-3 at (Part-1 & 2) of Plot # 02, Zone-04 | 28.096 | 1337.23 | 37570.8141
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0071-00 | 2025-12-17 | Survey and compaction testing FIR for (30cm) fill layer- 03 at Part-1 of Plot # 03, Zone-04 | 28.096 | 7123.176 | 200132.7529
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0072-00 | 2025-12-18 | Survey and compaction testing FIR for (30cm) fill layer- 04 at Part-1 of Plot # 01, Zone-04 | 28.096 | 239.23 | 6721.4061
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0073-00 | 2025-12-18 | Survey and compaction testing FIR for (30cm) fill layer- 04 at Part-1 of Plot # 03, Zone-04 | 28.096 | 59.76 | 1679.017
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0074-00 | 2025-12-18 | Inspection for Survey and compaction testing for 6th layer (30cm) fill at Plot 7 (Part 1)-1 | 28.096 | 60 | 1685.76
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0075-00 | 2025-12-18 | Inspection for Survey and compaction testing for 17th layer (30cm) fill at Plot 4 | 28.096 | 15910.52 | 447021.9699
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0076-00 | 2025-12-18 | Survey and compaction testing FIR for (30cm) fill layer-4 at (Part-1 & 2) of Plot # 02, Zone-04 | 28.096 | 2863.89 | 80463.8534
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0077-00 | 2025-12-20 | Survey and compaction testing FIR for (30cm) fill layer- 05 at Part-1 of Plot # 03, Zone-04 | 28.096 | 144.24 | 4052.567
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0078-00 | 2025-12-20 | Survey and compaction testing FIR for (30cm) fill layer-5 at (Part-1 & 2) of Plot # 02, Zone-04 | 28.096 | 3512.53 | 98688.0429
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0079-00 | 2025-12-20 | Survey and compaction testing FIR for (30cm) fill layer- 05 at Part-1 of Plot # 01, Zone-04 | 28.096 | 305.8 | 8591.7568
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0081-00 | 2025-12-22 | Survey and compaction testing FIR for (30cm) fill layer- 02 @ Plot 7, Part1 | 28.096 | 235.4 | 6613.7984
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0083-00 | 2025-12-25 | Inspection for survey works and compaction testing for plot 7, part1-1 the 7th fill layer (30 cm). | 28.096 | 366.17 | 10287.9123
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0087-00 | 2026-01-11 | Inspection for Survey and compaction testing for 8th layer (30cm) fill at Plot 7 (Part 1)-1. | 28.096 | 1093.7 | 30728.5952
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0088-00 | 2026-01-13 | Inspection for Survey and compaction testing 4th layer of (30cm) FIR for (30cm) fill at Plot 7, Part(1-2) | 28.096 | 692.92 | 19468.2803
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0089-00 | 2026-01-15 | Inspection for survey works and compaction testing 5th fill layer (30 cm) for plot 7, part1-2 | 28.096 | 1534.42 | 43111.0643
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0090-00 | 2026-01-17 | Inspection for survey works and compaction testing for plot 7, part 1- 2, the 6th fill layer (30 cm). | 28.096 | 2200.83 | 61834.5197
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0091-00 | 2026-01-18 | Inspection for survey works and compaction testing for the 6th fill layer (30 cm) at Plot 2 Part-1 & 2 | 28.096 | 4271.99 | 120025.831
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0095-00 | 2026-01-19 | Inspection for survey works and compaction testing for the 7th fill layer (30 cm) at Plot 2 Part-1 & 2 | 28.096 | 5365.52 | 150749.6499
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0096-00 | 2026-01-20 | Inspection for survey works and compaction testing for the 8th fill layer (30 cm) at Plot 2 Part-1 & 2 | 28.096 | 5460.35 | 153413.9936
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0097-00 | 2026-01-20 | Inspection for survey works and compaction testing for , plot 7-(part 2 & 3 )- layer 1 . | 28.096 | 651.36 | 18300.6106
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0098-00 | 2026-01-20 | Inspection for survey works and compaction fill layer 2 testing for plot 7-(part 2 & 3 ) | 28.096 | 2621.21 | 73645.5162
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0099-00 | 2026-01-21 | Inspection for survey works and compaction Fill Layer 9 testing for plot 2, (Part-1 & Part-2) | 28.096 | 5718.96 | 160679.9002
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0100-00 | 2026-01-21 | Inspection for survey works and compaction layer 3 testing for plot 7- (part 2 & 3) | 28.096 | 4707.53 | 132262.7629
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0101-00 | 2026-01-21 | Inspection for survey works and compaction layer 1 testing for plot 3 (part 2) | 28.096 | 90.66 | 2547.1834
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0102-00 | 2026-01-21 | Inspection for survey works and compaction layer 2 testing for plot 3 (part 2) | 28.096 | 1108.46 | 31143.2922
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0104-00 | 2026-01-22 | Inspection for survey works and compaction testing for plot 2, (Part-1 & Part-2) Fill Layer 10 | 28.096 | 5423.78 | 152386.5229
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0105-00 | 2026-01-22 | Inspection for survey works and compaction testing for plot 7-( part 2 & 3 )-layer 4. | 28.096 | 5740.95 | 161297.7312
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0106-00 | 2026-01-22 | Inspection for survey works and compaction testing for plot 3 (part 2) LAYER 3. | 28.096 | 2150.36 | 60416.5146
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0107-00 | 2026-01-24 | Inspection for survey works and compaction testing for plot 7-(part 2 & 3 )-layer 5. | 28.096 | 7447.69 | 209250.2982
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0108-00 | 2026-01-24 | Inspection for survey works and compaction testing for plot 2, (Part-1 & Part-2) Fill Layer 11 | 28.096 | 6588.56 | 185112.1818
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0109-00 | 2026-01-25 | Inspection for survey works and compaction testing for plot 2, (Part-1 & Part-2) Fill Layer-12 | 28.096 | 6299.62 | 176994.1235
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0110-00 | 2026-01-26 | Inspection for survey works and compaction testing Fill layer 13 for plot 2, (Part-1 & Part-2) | 28.096 | 7602.16 | 213590.2874
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0111-00 | 2026-01-26 | Inspection for survey works and compaction testing for plot 7-(part 2 & 3 )-layer 6. | 28.096 | 7670.54 | 215511.4918
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0112-00 | 2026-01-27 | Inspection for survey works and compaction testing for plot 7-(part 2 & 3)- layer 7 | 28.096 | 8037.28 | 225815.4189
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0113-00 | 2026-01-28 | Inspection for survey works and compaction testing for plot 7-(part 2 & 3)-layer 8. | 28.096 | 9846.99 | 276661.031
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0114-00 | 2026-01-29 | Inspection for survey works and compaction testing for plot 7-(part 2 & 3)-layer 9. | 28.096 | 12059.2 | 338815.2832
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0115-00 | 2026-01-31 | Inspection for survey works and compaction testing for plot 3, (part 2) LAYER 4. | 28.096 | 2800.7 | 78688.4672
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0116-00 | 2026-02-01 | Inspection for survey works and compaction testing, Fill layer 1 for plot 2 (Part-3) | 28.096 | 14.47 | 406.5491
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0117-00 | 2026-02-01 | Inspection for survey works and compaction testing for plot 3,(Part-2) Fill Layer 5 | 28.096 | 3491.88 | 98107.8605
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0118-00 | 2026-02-02 | Inspection for Survey work and Compaction for testing Fill layer 2 Plot 2 (Part-3 ) | 28.096 | 279.03 | 7839.6269
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0119-00 | 2026-02-02 | Inspection for Survey work and Compaction testing for plot 3, (part 2) LAYER 6. | 28.096 | 3964.73 | 111393.0541
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0121-00 | 2026-02-03 | Inspection for Survey work and Compaction testing for Plot 2 (Part-3) Fill Layer 3 | 28.096 | 428.81 | 12047.8458
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0122-00 | 2026-02-03 | Inspection for Survey work and Compaction testing for plot 3, (part 2) LAYER 7 | 28.096 | 4951.69 | 139122.6822
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0124-00 | 2026-02-03 | Inspection for Survey work and Compaction testing for Plot 7 (Part-4) Fill 2 | 28.096 | 472.53 | 13276.2029
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0125-00 | 2026-02-04 | Inspection for Survey work and Compaction testing for Plot 3 (Part-2) Fill layer 8 | 28.096 | 4771.79 | 134068.2118
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0126-00 | 2026-02-04 | Inspection for Survey work and Compaction testing for Plot 2 (Part-3) Fill layer 4 | 28.096 | 1032.11 | 28998.1626
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0127-00 | 2026-02-04 | Inspection for Survey work and Compaction testing for Plot 7 (Part-4) Fill layer 3 | 28.096 | 1561.86 | 43882.0186
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0128-00 | 2026-02-05 | Inspection for Survey work and Compaction testing for Fill Layer 9 for plot 3, (part 2) | 28.096 | 7460.574 | 209612.2871
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0129-00 | 2026-02-05 | Inspection for Survey work and Compaction testing Fill Layer 5 Plot 2 (Part-3 ) | 28.096 | 1290.31 | 36252.5498
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0130-00 | 2026-02-05 | Inspection for Survey work and Compaction testing for Plot 7 (Part-4) Fill 4 | 28.096 | 2618.1 | 73558.1376
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0131-00 | 2026-02-07 | Inspection for Survey work and Compaction testing for Plot 2 (Part-3 ) Fill Layer 6 | 28.096 | 1540.71 | 43287.7882
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0132-00 | 2026-02-07 | Inspection for Survey work and Compaction testing for Plot 7 (Part-4) Fill 5 | 28.096 | 3274.86 | 92010.4666
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0133-00 | 2026-02-08 | Inspection for Survey work and Compaction testing for Plot 2 (Part-3 ) Fill Layer 7 | 28.096 | 2003.61 | 56293.4266
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0134-00 | 2026-02-08 | Inspection for Survey work and Compaction testing for Plot 7 (Part-4) Fill 6 | 28.096 | 4345.32 | 122086.1107
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0135-00 | 2026-02-09 | Inspection for Survey work and Compaction testing for Plot 2 (Part-3 ) Fill Layer 8 | 28.096 | 2251.66 | 63262.6394
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0136-00 | 2026-02-09 | Inspection for Survey work and Compaction testing for Plot 7 (Part-4) Fill 7 | 28.096 | 5993.45 | 168391.9712
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0137-00 | 2026-02-10 | Inspection for Survey work and Compaction testing for Plot 7 (Part-4) Fill 8 | 28.096 | 6131.04 | 172257.6998
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0138-00 | 2026-02-10 | Inspection for Survey work and Compaction testing for Plot 2 (Part-3) Fill Layer 9 | 28.096 | 2255.4 | 63367.7184
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0139-00 | 2026-02-11 | Inspection for Survey work and Compaction testing For Plot 2 (Part-3 ) Fill Layer 10 | 28.096 | 2426.1 | 68163.7056
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0140-00 | 2026-02-11 | Inspection for Survey work and Compaction testing For Plot 7 (Part-4) Fill 9 | 28.096 | 6546.92 | 183942.2643
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0141-00 | 2026-02-12 | Inspection for Survey work and Compaction testing for Plot 2 (Part-3) Fill Layer 11 | 28.096 | 5030.83 | 141346.1997
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0142-00 | 2026-02-12 | Inspection for Survey work and Compaction testing For Plot 7 (Part-4) Fill 10 | 28.096 | 6535.93 | 183633.4893
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0144-00 | 2026-02-14 | Inspection for Survey work and Compaction testing For Plot 7 (Part-4) Fill 11 | 28.096 | 8440.69 | 237149.6262
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0146-00 | 2026-04-01 | Inspection for survey works and compaction testing for 7th Fill layer (30 cm), at Plot 5. | 28.096 | 987.34 | 27740.3046
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0147-00 | 2026-04-02 | Inspection for survey works and compaction testing for 8th Fill layer (30 cm), at Plot 5. | 28.096 | 6290.35 | 176733.6736
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0148-00 | 2026-04-04 | Inspection for survey works and compaction testing for 9th Fill layer (30 cm), at Plot 5. | 28.096 | 6566.67 | 184497.1603
B1.1.31 23 23.01 | Engineering backfiling | DAM2-02-09-SAJ-TS9-1-SUR-FIR-0149-00 | 2026-04-04 | Inspection for Survey and compaction testing for 9th layer (30cm) fill at Plot 7 (Part 1)-1. | 28.096 | 1462.85 | 41100.2336
B1.1.31 23 23.01 | Engineering backfiling |  |  | As-built qty for IPC-3 | 28.096 | 78368.706 | 2201847.1638
B1.1.31 23 23.01 | Engineering backfiling |  | 2026-06-23 | As-built qty for IPC-5 | 28.096 | 2791.2944 | 78424.2087
B1.1.31 23 23.01 | Engineering backfiling |  | 2026-07-12 | As-built qty for IPC-6 | 28.096 | 80724.2586 | 2268028.7684
B1.1.31 23 23.01 | Engineering backfiling |  | 2026-09-15 | As-built qty for IPC-7 | 28.096 | 100264.761 | 2817038.7251
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0001-00 | 2025-12-20 | FIR for Verification of Level Sheet (RD-1): From Station 00+10.00 to Station 00+830.00 Cutting up to PGL – 0.62 (CUT) | 14.926 | 23909.28 | 356869.9133
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0002-00 | 2025-12-20 | Survey FIR for Verification of LEVEL SHEET (RD-2) - From Station 01+577.52 To Station 02+217.52, Cutting up PGL – 0.62 (CUT) | 14.926 | 16839.92 | 251352.6459
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0003-00 | 2025-12-16 | Survey FIR for Verification of LEVEL SHEET (RD-2) - From Station 01+577.52 To Station 02+217.52, REPLACEMENT CUT ( 50cm) | 14.926 | 13115.5 | 195761.953
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0014-00 | 2025-12-23 | FIR for the 50cm Replacement cutting@ Asphalt Plot A, zone-1 | 14.926 | 12111.67 | 180778.7864
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0019-00 | 2025-12-24 | FIR for Replacement cut (NGL -50 cm) in filling Area at Asphalt Plot C, Zone-3 | 14.926 | 3350 | 50002.1
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0020-00 | 2025-12-26 | FIR for the cutting ( NGL to PGL-1M ) in cutting area at Asphalt Plot C, zone-3 | 14.926 | 21847.34 | 326093.3968
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0026-00 | 2025-12-01 | Survey FIR for Fill area REPLACMENT CUT -0.50 m from NGL in Plot D | 14.926 | 10121.35 | 151071.2701
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0030-01 | 2025-12-02 | Survey FIR for Cut Area from NGL to PGL – 1 meter in Plot D | 14.926 | 9393.8 | 140211.8588
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0037-00 | 2025-12-02 | Survey FIR for fill Area replacment cut - 0.50 m from NGL in Plot D | 14.926 | 7790.17 | 116276.0774
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0055-00 | 2025-12-13 | Survey FIR for Fill area REPLACMENT CUT -0.50 m from NGL in Road 2 (Station 00+000 to 00+420) | 14.926 | 6115.11 | 91274.1319
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0056-00 | 2025-12-13 | Survey FIR for Fill Area Replacement Cut -050 m from NGL in Plot D part 3 | 14.926 | 5598.41 | 83561.8677
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0061-00 | 2025-12-14 | Survey FIR for Cut Area from NGL to PGL – 1 meter in Plot D Part 3 | 14.926 | 11386.78 | 169959.0783
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0062-00 | 2025-12-14 | Survey FIR for Fill Area Replacement Cut -050 m from NGL in Plot D part 4 | 14.926 | 3604.66 | 53803.1552
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0063-00 | 2025-12-14 | Survey FIR for Cut Area from NGL to PGL – 1 meter in Plot D Part 4 | 14.926 | 40487.76 | 604320.3058
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0077-00 | 2025-12-27 | FIR for (Replacement cut – 0.50 m) @ Asphalt Plot B, zone-2 | 14.926 | 3421.67 | 51071.8464
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0078-00 | 2025-12-28 | FIR for (PGL – 01m) @ Asphalt Plot B, zone-2 | 14.926 | 18201.183 | 271670.8575
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0082-00 | 2025-12-29 | Inspection for Survey work for Fill area REPLACMENT CUT -0.50 m from NGL RD04 (0+020 to 0+325) | 14.926 | 1415.35 | 21125.5141
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0086-00 | 2025-12-30 | Inspection for Survey work for Fill area REPLACMENT CUT -0.50 m from NGLfor RD02 (0+532.73 to 0+960), | 14.926 | 2821 | 42106.246
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0088-00 | 2025-12-31 | Inspection for Survey work for Fill area REPLACMENT CUT -0.50 m from NGL for RD02 - (2+217.52 to 2+538.62) | 14.926 | 2498.39 | 37290.9691
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0091-00 | 2026-01-05 | Survey FIR for Cut (PGL – 0.92m), From Station 0+020 To Station 0+325 @ RD-4, Zone-04 | 14.926 | 4180.42 | 62396.9489
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0093-01 | 2026-01-08 | Inspection for Survey work for Fill area REPLACMENT CUT -0.50 m from NGL for Road 03 - Station (0+020-0+070) | 14.926 | 426.453 | 6365.2375
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0094-01 | 2026-01-11 | Inspection for Survey work for Fill area REPLACMENT CUT -0.50 m from NGL for Road 03 – Station (0+180-0+220). | 14.926 | 416.293 | 6213.5893
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0095-01 | 2026-01-11 | Inspection for Survey work for Fill area REPLACMENT CUT -0.50 m from NGL for Road 03 – Station (0+300-0+325) | 14.926 | 271.33 | 4049.8716
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0096-01 | 2026-01-11 | Survey FIR for Cut Area from NGL to PGL – 1 meter in Road 03- Station (0+220-0+290). | 14.926 | 2046.655 | 30548.3725
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0097-01 | 2026-01-11 | Survey FIR for replacement cut (NGL -0.50cm) at Road-4 ((0+020 to 0+160)&(0+300 to 325) | 14.926 | 1415.35 | 21125.5141
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0098-01 | 2026-01-11 | Survey FIR for Cut Area from NGL to PGL – 1 meter in Custom RD 6 (0+000 to 0+060) & (0+140 to 0+270) & (0+300 to 0+340) | 14.926 | 2406.05 | 35912.7023
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0099-01 | 2026-01-11 | Survey FIR for replacement cut (NGL -0.50cm) at Customs RD 5 (0+024.38 To 0+090) & (0+170 to 0+184.50) | 14.926 | 289.38 | 4319.2859
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0100-01 | 2026-01-11 | Survey FIR for Cut Area from NGL to PGL – 1 meter in Custom RD 5 (0+100 to 0+170) | 14.926 | 1103.03 | 16463.8258
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0110-00 | 2026-01-12 | Survey FIR for Cut Area from NGL to PGL – 1 meter for Road 02- (2+327.52 to 2+437.52) | 14.926 | 1896.36 | 28305.0694
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0117-00 | 2026-01-14 | Survey FIR for Cut Area from NGL to PGL – 1 meter for Road 02- (0+080 To 0+280.0 & 0+420.00 to 00+532.73) | 14.926 | 9709.32 | 144921.3103
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0118-00 | 2026-01-14 | Inspection for Survey work for Fill area REPLACMENT CUT -0.50 m from NGL for Road 02 - (0+080 & 00+270.00 to 00+420.00), | 14.926 | 1964.37 | 29320.1866
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0126-00 | 2026-01-15 | Inspection for Survey work for Fill area REPLACMENT CUT -0.50 m from NGL for Road 02 (01+530.00 To 1+577.52) | 14.926 | 548.78 | 8191.0903
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0127-00 | 2026-01-15 | Survey FIR for Cut Area from NGL to PGL – 0.92 meter for Road 02- (1+470 To Station 1+530 & 1+570) | 14.926 | 775.61 | 11576.7549
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0137-00 | 2026-01-18 | Survey FIR for Cut Area from NGL to PGL – 0.92 meter for Road 02- (2+327.52 to 2+437.52) | 14.926 | 1896.36 | 28305.0694
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0138-00 | 2026-01-18 | Survey FIR for Cut Area from NGL to PGL – 0.92 meter for Road 02- (0+532.73 to 0+960) | 14.926 | 4001.6 | 59727.8816
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0139-00 | 2026-01-18 | Survey FIR for Cut Area from NGL to PGL – 0.92 meter for Road 03- (0+070-0+180) | 14.926 | 2046.655 | 30548.3725
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0155-00 | 2026-01-25 | Survey FIR for Cut Area from NGL to PGL – 1 meter in Entrance Road 01- Station (0+107.63 To 00+177.63 & 00+227.63 to 00+267.63). | 14.926 | 889.02 | 13269.5125
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0156-00 | 2026-01-25 | Inspection for Survey work for Fill area Replacement Cut - 0.50 m from NGL for Entrance Road 01 From Station (0+017.629 To 00+097.63 & 00+187.63 To 00+312.341) | 14.926 | 743.7 | 11100.4662
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0170-00 | 2026-02-01 | Survey FIR for Cut Area from NGL to PGL – 0.92 meter for Road 02- Station (0+960). | 14.926 | 47.47 | 708.5372
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0171-00 | 2026-02-01 | Inspection for Survey work for Fill area REPLACMENT CUT - 0.50 m from NGL for Road 02 From Station (0+970.0 To 1+100). | 14.926 | 1341.94 | 20029.7964
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0176-00 | 2026-02-04 | Inspection for Survey work for Fill area REPLACMENT CUT - 0.50 m from NGL for Entrance Road 2 From Station (0+000 To 00+100.00 & 00+150.00 To 0+281.717). | 14.926 | 1625.3 | 24259.2278
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0184-00 | 2026-02-08 | Inspection for Survey work for Fill area REPLACMENT CUT - 0.50 m from NGL for Road 5 From Station (0+017.144 To 0+072.510). | 14.926 | 471.54 | 7038.206
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0199-00 | 2026-02-10 | Inspection for Survey work for Fill area REPLACMENT CUT - 0.50 m from NGL for Asphalt Plot (Intersection 1). | 14.926 | 1632.57 | 24367.7398
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0200-00 | 2026-02-10 | Survey FIR for Cut Area from NGL to PGL – 1 meter at Asphalt Plot (Intersection 1). | 14.926 | 789.02 | 11776.9125
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0214-00 | 2026-02-15 | Inspection for Survey work for Fill area REPLACMENT CUT - 0.50 m from NGL for Customs RD 4 Station 00+015.99 To 00+125.99 & 00+205.99 To 00+215.99. | 14.926 | 534.88 | 7983.6189
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0215-00 | 2026-02-15 | Survey FIR for Cut Area from NGL to PGL – 1 meter at Customs RD 4 From Station 0+15.99 To 00+055.99 & 00+125.99 To 00+195.99. | 14.926 | 751.86 | 11222.2624
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0224-00 | 2026-02-18 | Inspection for Survey work for Fill area REPLACMENT CUT - 0.50 m from NGL for Commercial RD 1 Station 0+026.42 TO 0+199.39. | 14.926 | 702.8 | 10489.9928
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0229-00 | 2026-02-21 | Inspection for Survey work for REPLACMENT CUT of Fill area - 0.50 m from NGL for Customs RD 2 Station (00+000 to 00+290.00 & 00+370.00 to 00+440.00 to 00+540.00 to 00+690.00). | 14.926 | 1777.96 | 26537.831
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0232-00 | 2026-02-24 | Survey FIR for Cut Area from NGL to PGL – 1 meter at Entrance Road 2 Station (00+110.00 To 00+230.00). | 14.926 | 2232.52 | 33322.5935
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0238-00 | 2026-03-05 | Inspection for Survey work for Fill area Replacement Cut - 0.50 m from NGL for Customs Road 06 From Station (0+270 to 0+290) & (0+330 to 0+466.413) | 14.926 | 609.1 | 9091.4266
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0240-00 | 2026-03-05 | Survey FIR for Cut Area from NGL to PGL – 1 meter at Customs RD 2 Station (00+120.00 to 00+360.00 & 00+440.00 to 00+540.00 & 00+690.00 to 00+714.546 ) | 14.926 | 1832.74 | 27355.4772
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0248-00 | 2026-03-08 | Inspection for Survey work for Fill area Replacement Cut - 0.50 m from NGL for Management RD 2 Station (0+042.939 to 0+142.975). | 14.926 | 476.73 | 7115.672
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0249-00 | 2026-03-08 | Survey FIR for Cut Area from NGL to PGL – 0.92 meter at Management RD 2 Station (0+012.939 to 0+042.939). | 14.926 | 397.64 | 5935.1746
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0261-00 | 2026-03-11 | Inspection for Survey work for Fill area Replacement Cut - 0.50 m from NGL for Custom RD 1 Station (00+100.00 to 00+260.00 & 00+370 to 00+430 & 00+520 to 00+810). | 14.926 | 1777.43 | 26529.9202
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0262-00 | 2026-03-11 | Survey FIR for Cut Area from NGL to PGL – 1 meter at Customs RD 1 Station (00+050 to 00+100 & 00+270 to 00+360 & 00+420 to 00+660). | 14.926 | 2839.7 | 42385.3622
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0265-00 | 2026-03-12 | Inspection for Survey work for Fill area Replacement Cut - 0.50 m from NGL for Management RD 1 (0+118.698 to 0+195.792). | 14.926 | 1367.42 | 20410.1109
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0266-00 | 2026-03-12 | Survey FIR for Cut Area from NGL to PGL – 1 meter at Management RD 1 (0+18.698 to 0+118.698). | 14.926 | 1521.34 | 22707.5208
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0283-00 | 2026-03-28 | Inspection for Survey work for Fill area Replacement Cut - 0.50 m from NGL for Roundabout Station (0+000 to 0+006.005 & 0+066.466 to 0+084.80). | 14.926 | 244.88 | 3655.0789
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0284-00 | 2026-03-28 | Survey FIR for Cut Area from NGL to PGL – 1 meter at Roundabout, Station (0+010 to 0+058.255). | 14.926 | 2422.43 | 36157.1902
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) |  | 2026-06-23 | As-built qty for IPC-5 | 14.926 | 31005.83 | 462793.0186
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) |  | 2026-07-12 | As-built qty for IPC-6 | 14.926 | 60180.305 | 898251.2324
B1.2.31 23 16.01 | Roadway Excavation for cuttings (all types of soil) |  | 2026-09-15 | As-built qty for IPC-7 | 14.926 | 11582.7739 | 172884.484
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0004-00 | 2025-12-16 | FIR for Verification of Level Sheet (RD-1): From Station 00+20.00 to Station 00+830.00 FILL (30cm). LAYER #1 | 27.218 | 9284.22 | 252697.9
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0005-00 | 2025-12-18 | Survey FIR for fill placement of LAYER- 01 From Station 01+577.52 To Station 02+217.52@ RD-2, ZONE-04(level sheet is attached) | 27.218 | 5684.67 | 154725.3481
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0007-00 | 2025-12-19 | Survey FIR for fill placement(30cm) of layer- 02 From Station 00+20.00 to Station 00+830.00@ RD-1, ZONE-01 (level sheet is attached) | 27.218 | 4280.45 | 116505.2881
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0009-00 | 2025-12-20 | Survey FIR for fill placement of LAYER- 02 From Station 01+577.52 To Station 02+217.52@ RD-2, ZONE-04 (level sheet is attached) | 27.218 | 4280.45 | 116505.2881
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0012-00 | 2025-12-23 | Survey FIR for fill placement(30cm) of layer- 03 From Station 00+20.00 to Station 00+830.00 @ RD-1, ZONE-01 | 27.218 | 7650.73 | 208237.5691
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0013-00 | 2025-12-23 | Survey FIR for fill placement of LAYER- 03 From Station 01+577.52 To Station 02+217.52@ RD-2, ZONE-04 | 27.218 | 3727.118 | 101444.6977
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0017-00 | 2025-12-24 | Survey FIR for fill placement of LAYER- 01 @ Asphalt Plot A, Zone-01 | 27.218 | 7102.5 | 193315.845
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0021-00 | 2025-12-26 | Survey FIR for fill placement(30cm) of layer- 04 From Station 00+20.00 to Station 00+830.00 @ RD-1, ZONE-01 | 27.218 | 6046.08 | 164562.2054
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0022-00 | 2025-12-26 | Survey FIR for fill placement of LAYER- 04 From Station 01+577.52 To Station 02+217.52@ RD-2, ZONE-04 | 27.218 | 2856.19 | 77739.7794
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0027-00 | 2025-12-27 | Survey and Compaction FIR for fill placement (30 cm) of LAYER-01 @ Asphalt Plot C, Zone-03 | 27.218 | 1933.44 | 52624.3699
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0028-00 | 2025-12-29 | Survey and Compaction FIR for fill placement (30 cm) of LAYER-02 @ Asphalt Plot C, Zone-03 | 27.218 | 1564.77 | 42589.9099
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0029-00 | 2025-12-29 | Survey and Compaction FIR for fill placement (30 cm) of LAYER-03 @ Asphalt Plot A, Zone-01 | 27.218 | 6944.55 | 189016.7619
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0031-01 | 2025-12-01 | Survey and Compaction FIR for fill placement (30 cm) of LAYER-03 @ Asphalt Plot C, Zone-03 | 27.218 | 561.51 | 15283.1792
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0033-00 | 2025-12-01 | Survey and Compaction FIR for fill placement (30 cm) of LAYER-05 @ Asphalt Plot A, Zone-01 | 27.218 | 3624.391 | 98648.6742
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0034-00 | 2025-12-02 | Survey and Compaction FIR for fill placement (30 cm) of LAYER-04 @ Asphalt Plot C, Zone-03 | 27.218 | 798.02 | 21720.5084
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0038-00 | 2025-12-02 | Survey and Compaction FIR for fill placement (30 cm) of LAYER-04 @ Asphalt Plot C, Zone-03 part 02. as highlighted in attached drawing | 27.218 | 798.02 | 21720.5084
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0039-00 | 2025-12-02 | Survey and Compaction FIR for fill placement (30 cm) of LAYER- 06 @ Asphalt Plot A, Zone-01 | 27.218 | 4138.663 | 112646.1295
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0041-00 | 2025-12-03 | Survey and Compaction FIR for fill placement (30 cm) of LAYER-05 @ Asphalt Plot C, Zone-03 | 27.218 | 1074.46 | 29244.6523
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0042-00 | 2025-12-03 | Inspection for survey works and compaction testing for the 7th fill layer (30 cm) from Station 00+20.00 to Station 00+830.00 at Road-01, as indicated in the highlighted area. | 27.218 | 1718.72 | 46780.121
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0043-00 | 2025-12-03 | Inspection for survey works and compaction testing for the 7th fill layer (30 cm) from Station 01+577.52 to Station 02+217.52 at Road-02, as indicated in the highlighted area. | 27.218 | 550.62 | 14986.7752
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0044-00 | 2025-12-04 | Survey and Compaction FIR for fill placement (30 cm) of LAYER-06 @ Asphalt Plot C, Zone-03 | 27.218 | 2654.51 | 72250.4532
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0045-00 | 2025-12-04 | Inspection for survey works and compaction testing for the 8th fill layer (30 cm) from Station 00+20.00 to Station 00+830.00 at Road-01, as indicated in the highlighted area. | 27.218 | 1890.6 | 51458.3508
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0046-00 | 2025-12-04 | Inspection for survey works and compaction testing for the 8th fill layer (30 cm) from Station 01+577.52 to Station 02+217.52 at Road-02, as indicated in the highlighted area. | 27.218 | 596.5 | 16235.537
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0047-00 | 2025-12-07 | Inspection for survey works and compaction testing for the 9th fill layer (30 cm) from Station 01+577.52 to Station 02+217.52 at Road-02, as indicated in the highlighted area. | 27.218 | 642.39 | 17484.571
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0050-00 | 2025-12-07 | Inspection for survey works and compaction testing for the 10th fill layer (30 cm) from Station 01+577.52 to Station 02+217.52 at Road-02, as indicated in the highlighted area. | 27.218 | 688.27 | 18733.3329
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0051-00 | 2025-12-08 | Inspection for survey works and compaction testing for the 11th fill layer (30 cm) from Station 01+577.52 to Station 02+217.52 at Road-02, as indicated in the highlighted area. | 27.218 | 734.16 | 19982.3669
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0052-00 | 2025-12-09 | Inspection for survey works and compaction testing for the 12th fill layer (30 cm) from Station 01+577.52 to Station 02+217.52 at Road-02, as indicated in the highlighted area. | 27.218 | 780.04 | 21231.1287
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0053-00 | 2025-12-10 | Inspection for survey works and compaction testing for the 13th fill layer (30 cm) from Station 01+577.52 to Station 02+217.52 at Road-02, as indicated in the highlighted area. | 27.218 | 825.92 | 22479.8906
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0054-00 | 2025-12-11 | Inspection for survey works and compaction testing for the 14th fill layer (30 cm) from Station 01+577.52 to Station 02+217.52 at Road-02, as indicated in the highlighted area. | 27.218 | 871.81 | 23728.9246
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0057-00 | 2025-12-13 | Survey and Compaction FIR for fill placement (30 cm) of LAYER- 07 @ Asphalt Plot A, Zone-01 | 27.218 | 4530.49 | 123310.8768
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0058-00 | 2025-12-13 | Survey and Compaction FIR for fill placement (30 cm) of LAYER-07 @ Asphalt Plot C, Zone-03 | 27.218 | 1196.25 | 32559.5325
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0059-00 | 2025-12-14 | Survey and Compaction FIR for fill placement (30 cm) of LAYER- 08 @ Asphalt Plot A, Zone-01 | 27.218 | 4726.4 | 128643.1552
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0064-00 | 2025-12-14 | Inspection for survey works and compaction testing for the 15th fill layer (30 cm) from Station 01+577.52 to Station 02+217.52 at Road-02, as indicated in the highlighted area. | 27.218 | 917.69 | 24977.6864
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0065-00 | 2025-12-15 | Inspection for survey works and compaction testing for the 16th fill layer (30 cm) from Station 01+577.52 to Station 02+217.52 at Road-02, as indicated in the highlighted area. | 27.218 | 963.58 | 26226.7204
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0066-00 | 2025-12-16 | Inspection for survey works and compaction testing for the 17th fill layer (30 cm) from Station 01+577.52 to Station 02+217.52 at Road-02, as indicated in the highlighted area. | 27.218 | 1009.46 | 27475.4823
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0067-00 | 2025-12-17 | Inspection for survey works and compaction testing for the 18th fill layer (30 cm) from Station 01+577.52 to Station 02+217.52 at Road-02, as indicated in the highlighted area. | 27.218 | 1055.35 | 28724.5163
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0068-00 | 2025-12-18 | Inspection for survey works and compaction testing for the 19th fill layer (30 cm) from Station 01+577.52 to Station 02+217.52 at Road-02, as indicated in the highlighted area. | 27.218 | 1101.23 | 29973.2781
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0071-00 | 2025-12-23 | Inspection for survey works and compaction testing for plot D, the 3rd fill layer (30 cm). | 27.218 | 159.48 | 4340.7266
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0073-00 | 2025-12-24 | Inspection for survey works and compaction testing for plot D, the 5th fill layer (30 cm). | 27.218 | 5943.79 | 161778.0762
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0076-00 | 2025-12-27 | Inspection for survey works and compaction testing for plot D, the 8th fill layer (30 cm). | 27.218 | 22071.02 | 600729.0224
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0079-00 | 2025-12-28 | Inspection for survey works and compaction testing for plot D, the 9th fill layer (30 cm). | 27.218 | 28862.476 | 785578.8718
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0081-00 | 2025-12-29 | Survey and Compaction FIR for fill Layer-02 (30 cm) @ Asphalt Plot B, Zone-02 | 27.218 | 83.72 | 2278.691
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0083-01 | 2026-01-07 | Inspection for survey works and compaction testing for plot D, the 10th fill layer (30 cm). | 27.218 | 29809.19 | 811346.5334
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0084-00 | 2025-12-30 | Survey and Compaction FIR for fill Layer-03 (30 cm) @ Asphalt Plot B, Zone-02 | 27.218 | 268.42 | 7305.8556
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0085-01 | 2026-01-07 | Survey and Compaction FIR for fill Layer-04 (30 cm) @ Asphalt Plot B, Zone-02 | 27.218 | 438.62 | 11938.3592
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0087-01 | 2026-01-07 | Survey and Compaction FIR for fill Layer-05 (30 cm) @ Asphalt Plot B, Zone-02 | 27.218 | 1019.78 | 27756.372
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0089-00 | 2026-01-03 | Inspection for survey works and compaction testing for 20th layer of Road 02 (1+577.52 to 2+217.52 | 27.218 | 1147.12 | 31222.3122
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0090-00 | 2026-01-04 | Survey and Compaction FIR for fill Layer-06(30 cm) @ Asphalt Plot B, Zone-02 | 27.218 | 1611.13 | 43851.7363
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0092-00 | 2026-01-06 | Survey and Compaction FIR for fill Layer-07 (30 cm) @ Asphalt Plot B, Zone-02 | 27.218 | 2385.1 | 64917.6518
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0102-01 | 2026-01-11 | Inspection for survey works and compaction testing for the 2nd fill layer (30 cm) for Road 04 - From Station( 0+050 To Station 0+070) & (0+100 To Station 0+130) | 27.218 | 158.4 | 4311.3312
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0103-00 | 2026-01-08 | Survey and Compaction FIR for fill Layer-08 (30 cm) @ Asphalt Plot B, Zone-02 | 27.218 | 2397.54 | 65256.2437
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0104-00 | 2026-01-11 | Inspection for survey works and compaction testing for 3rd layer (30 cm) fill at Road 04 –From Station 0+040 To Station 0+130 | 27.218 | 397.97 | 10831.9475
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0106-00 | 2026-01-11 | Inspection for survey works and compaction testing for 2nd layer (30 cm ) fill at Road 02 - From Station 02+247.52 & 02+297.52 &02+307.52&02+317.52 | 27.218 | 18.51 | 503.8052
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0109-00 | 2026-01-12 | Inspection for survey works and compaction testing for 4th layer at Road 04 | 27.218 | 797.64 | 21710.1655
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0111-00 | 2026-01-12 | Inspection for survey works and compaction testing for 3rd layer (30cm) Fill at Road 02 –(2+247.52.52 &2+457.52&02+267.52&02+297.52 to 2+457) | 27.218 | 129.27 | 3518.4709
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0112-00 | 2026-01-12 | Inspection for survey works and compaction testing for 4th layer at Road 02 (2+247.52 To 2+357 & 2+447 to 2+538.62) | 27.218 | 592.81 | 16135.1026
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0113-00 | 2026-01-13 | Inspection for survey works and compaction testing for 5th layer (30cm) fill at Road 04.Station (0+020 to 0+140 & 0+300 to 0+320 | 27.218 | 1140.36 | 31038.3185
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0114-00 | 2026-01-13 | Inspection for survey works and compaction testing for 5th layer (30cm) Fill at Road 02 (2+237.52 To 02+357.52 & 02+437.52 to 02+538.62) | 27.218 | 798.19 | 21725.1354
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0115-00 | 2026-01-14 | Inspection for survey works and compaction testing 6th layer fill at Road 04 | 27.218 | 1497.8 | 40767.1204
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0116-00 | 2026-01-14 | Inspection for survey and compaction testing of 6th layer (30cm) for Road 02 (2+217.52 To02+357.52 &02+437.52 to 02+538.62) | 27.218 | 1558.01 | 42405.9162
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0119-00 | 2026-01-14 | Inspection for survey works and compaction testing for 1st layer (30cm) Fill at Road 03, Station (0+20 To 0+040 & 0+200) | 27.218 | 10.01 | 272.4522
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0120-00 | 2026-01-14 | Inspection for survey works and compaction testing for 2nd layer 30 cm Fill at Road 03. Station (0+20 To 0+070 & 0+200) | 27.218 | 271.82 | 7398.3968
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0121-00 | 2026-01-15 | Inspection for survey works and compaction testing 7th layer fill at Road 04- From Station (0+020 To 0+150 & 0+300 to 0+320) | 27.218 | 1855.46 | 50501.9103
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0122-00 | 2026-01-15 | Inspection for survey works and compaction testing for 7th layer Road 02 (2+217.52 To 02+367.52 & 02+407.52 to02+538.62) | 27.218 | 2410.08 | 65597.5574
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0123-00 | 2026-01-15 | Inspection for survey works and compaction testing for 1st layer 30 cm fill Road 02 – Stations (0+330 To 00+410.00) | 27.218 | 339.92 | 9251.9426
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0124-00 | 2026-01-15 | Inspection for survey works and compaction testing 2nd layer 30 cm Fill for Road 02 – Stations (0+080 & 00+320.00 TO00+410.00) | 27.218 | 532.69 | 14498.7564
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0125-00 | 2026-01-15 | Inspection for survey works and compaction testing 3rd layer 30 cm Fill for Road 03 Station (0+20 To 0+080.0 & 00+190.00 TO 00+325.00) | 27.218 | 461.19 | 12552.6694
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0128-00 | 2026-01-17 | Inspection for survey works and compaction testing 8th layer 30 cm Fill for Road 04-From Station 0+020 To 00+150.00 & 00+300.00 TO 00+320.00 | 27.218 | 2482.83 | 67577.6669
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0129-00 | 2026-01-17 | Inspection for survey works and compaction testing 8th Fill layer 30 cm for Road 02 - From Station( 2+217.52 To 02+367.52 & 02+407.52 to 02+538.62) | 27.218 | 2842.38 | 77363.8988
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0130-00 | 2026-01-17 | Inspection for survey works and compaction testing 4rd layer 30 cm Fill for Road 03 Station (0+20 To 0+080.0 & 00+190.00 TO 00+325.00) ) | 27.218 | 842.56 | 22932.7981
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0131-00 | 2026-01-17 | Inspection for survey works and compaction testing of 1ST FILL Layer (30 cm) for Road 02 (01+540.00 To 1+577.52) | 27.218 | 213.95 | 5823.2911
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0132-00 | 2026-01-18 | Inspection for survey works and compaction testing of 2nd FILL Layer (30 cm) for Road 02 (01+530.0 To Station 1+577.52) | 27.218 | 303.88 | 8271.0058
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0133-00 | 2026-01-18 | Inspection for survey works and compaction testing for 5th layer (30cm) Fill for Road 03-Station (0+20 To 0+240 & 0+300 TO 0+325) | 27.218 | 1129.01 | 30729.3942
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0134-00 | 2026-01-18 | Inspection for survey works and compaction testing 9th layer 30 cm Fill for Road 04-From Station (0+020 To 00+160.00 & 00+300.00 TO 00+325.00) | 27.218 | 2708.38 | 73716.6868
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0135-00 | 2026-01-18 | Inspection for survey works and compaction testing 9th Fill layer 30 cm for Road 02(2+217.52 To2+538.62) | 27.218 | 3868.58 | 105295.0104
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0136-00 | 2026-01-18 | Inspection for survey works and compaction testing 3rd layer 30 cm Fill for Road 02– (0+080 & (00+290.00 TO 00+420.00). | 27.218 | 1029.58 | 28023.1084
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0140-00 | 2026-01-19 | Inspection for survey works and compaction testing 10th layer 30 cm Fill for Road 04-From Station 0+020 To 0+160 & 00+300.00 to 00+325.00 | 27.218 | 2290.75 | 62349.6335
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0141-00 | 2026-01-19 | Inspection for survey works and compaction testing 10th layer 30 cm Fill for Road 02 (2+217.52 To2+538.62) | 27.218 | 3578.99 | 97412.9498
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0142-00 | 2026-01-19 | Inspection for survey works and compaction testing for 4th layer 30 cm Fill Road 02 – (0+080 & 00+270.00 TO 00+420.00), | 27.218 | 1418.2 | 38600.5676
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0143-00 | 2026-01-19 | Inspection for survey works and compaction testing for 6th layer 30 cm Fill Road 03 - Station (0+20 To 00+090.00 & 00+180.00 TO 00+325.00) | 27.218 | 1187.65 | 32325.4577
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0144-00 | 2026-01-19 | Inspection for survey works and compaction testing of 3rd FILL Layer (30 cm) for Road 02 Station (01+530.0 To 1+577.52) | 27.218 | 293.88 | 7998.8258
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0145-00 | 2026-01-20 | Inspection for survey works and compaction testing for 5th layer of 30cm Fill Road 02 – (0+080 & 00+270.00 TO 00+420.00), | 27.218 | 1498.81 | 40794.6106
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0146-00 | 2026-01-21 | Inspection for survey works and compaction testing for 1st layer of 30 cm Fill RD02 (00+873.00 To00+893.00) | 27.218 | 32.06 | 872.6091
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0147-00 | 2026-01-21 | Inspection for survey works and compaction testing for 2nd layer of 30 cm RD02 From Station 00+603 To Station 00+913 | 27.218 | 245.19 | 6673.5814
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0148-00 | 2026-01-21 | Inspection for survey works and compaction testing for top of embankment (30 cm) fill capping layer A-2-4 at Road 02 Station (1+577.52 to 2+217.52).Part 1 | 27.218 | 1878.68 | 51133.9122
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0149-00 | 2026-01-22 | Inspection for survey works and compaction testing for top of embankment (30 cm) fill capping layer A-2-4 at Road 02 Station (2+217.52 to 2+538.62) Part 1 | 27.218 | 934.065 | 25423.3812
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0150-00 | 2026-01-22 | Inspection for survey works and compaction testing for 3rd Fill layer (30 cm) at Road 02 Station (0+573 To 0+683 & 0+813.00 TO 0+913) | 27.218 | 940.17 | 25589.5471
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0151-00 | 2026-01-24 | Inspection for survey works and compaction testing for 4th Fill layer (30 cm) at Road 02 Station (0+573 To 0+683 & 0+803 TO 0+923). | 27.218 | 1461.84 | 39788.3611
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0152-00 | 2026-01-24 | Inspection for survey works and compaction testing for top of embankment (30 cm) fill capping layer A-2-4 at Road 02 Station (0+080 to 0+532.73). | 27.218 | 1223.1 | 33290.3358
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0153-00 | 2026-01-25 | Inspection for survey works and compaction testing for (30 cm) fill, bottom of sub grade layer A-2-4 at Road 03 Station (0+20 To 0+325) Part 1. | 27.218 | 871.635 | 23724.1614
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0154-00 | 2026-01-25 | Inspection for survey works and compaction testing for 5th Fill layer (30 cm) at Road 02 Station (0+563 To 0+683 & 0+803 TO 0+933). | 27.218 | 2428.42 | 66096.7356
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0157-00 | 2026-01-26 | Inspection for survey works and compaction testing for 6th Fill layer (30 cm) at Road 02 Station (0+563 to 0+933). | 27.218 | 2981.4 | 81147.7452
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0160-00 | 2026-01-27 | Inspection for survey works and compaction testing for (30 cm) fill, bottom of sub grade layer A-2-4 at Road 04 Station (0+020 To 0+325). | 27.218 | 871.645 | 23724.4336
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0161-00 | 2026-01-27 | Inspection for survey works and compaction testing for 7th Fill layer (30 cm) at Road 02 Station (0+553 To 0+943). | 27.218 | 4068.76 | 110743.5097
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0162-00 | 2026-01-27 | Inspection for survey works and compaction testing for 3rd Fill layer (30 cm) at Entrance RD 1 Station (00+037.63 TO 00+077.63 & 00+207.63). | 27.218 | 12.55 | 341.5859
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0163-00 | 2026-01-27 | Inspection for survey works and compaction testing for 4th Fill layer (30 cm) at Entrance RD 1 Station (00+037.63 TO 00+077.63 & 00+207.63 & 0+287.63 TO 312.341). | 27.218 | 62.39 | 1698.131
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0164-00 | 2026-01-28 | Inspection for survey works and compaction testing for 8th Fill layer (30 cm), bottom of A-2-4 at Road 02 Station (0+553 To 0+943). | 27.218 | 3816.42 | 103875.3196
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0165-00 | 2026-01-28 | Inspection for survey works and compaction testing for 5th Fill layer (30 cm) at Entrance RD 1 Station (0+017.629 To 00+077.63 & 00+197.63 TO 00+217.63 & 00+277.63 TO 00+312.341). | 27.218 | 194.91 | 5305.0604
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0166-00 | 2026-01-28 | Inspection for survey works and compaction testing for 6th Fill layer (30 cm) at Entrance RD 1 Station (0+017.629 To 00+087.63 & 00+197.63 To 0+312.341). | 27.218 | 293.92 | 7999.9146
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0167-00 | 2026-01-29 | Inspection for survey works and compaction testing for (30 cm) fill, bottom of sub grade layer A-2-4 at Road 02 Station (0+532.73 To 0+960). | 27.218 | 1260.815 | 34316.8627
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0168-00 | 2026-01-29 | Inspection for survey works and compaction testing for 7th Fill layer (30 cm) at Entrance RD 1 Station (0+017.629 To Station 0+312.341). | 27.218 | 500.67 | 13627.2361
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0169-00 | 2026-01-31 | Inspection for survey works and compaction testing for 8th Fill layer (30 cm), bottom of A-2-4 at Entrance RD 1 Station (0+017.629 To Station 0+312.341). | 27.218 | 456.3 | 12419.5734
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0172-00 | 2026-02-02 | Inspection for survey works and compaction testing for 1st Fill layer (30 cm) at Road 02 Station (01+040.00 To 01+048.28). | 27.218 | 9.51 | 258.8432
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0173-00 | 2026-02-02 | Inspection for survey works and compaction testing for 2nd Fill layer (30 cm) at Road 02 Station (01+010.0 To 01+070.85). | 27.218 | 314.33 | 8555.4339
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0174-00 | 2026-02-03 | Inspection for survey works and compaction testing for 3rd Fill layer (30 cm) at Road 02 Station (00+980.00 To 01+070.85). | 27.218 | 442.82 | 12052.6748
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0175-00 | 2026-02-04 | Inspection for survey works and compaction testing for 4th Fill layer (30 cm) at Road 02 Station (00+970.00 To 01+080.00). | 27.218 | 984.08 | 26784.6894
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0177-00 | 2026-02-05 | Inspection for survey works and compaction testing for 5th Fill layer (30 cm) at Road 02 Station (00+970.00 To 01+080.00). | 27.218 | 1047.72 | 28516.843
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0178-00 | 2026-02-05 | Inspection for survey works and compaction testing for 1st Fill layer (30 cm) at Entrance Road 2 Station (00+270.00 To 0+281.717). | 27.218 | 46.9 | 1276.5242
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0179-00 | 2026-02-05 | Inspection for survey works and compaction testing for 2nd Fill layer (30 cm) at Entrance Road 2 Station (00+260.00 To 0+281.717). | 27.218 | 185.8 | 5057.1044
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0180-00 | 2026-02-07 | Inspection for survey works and compaction testing for 6th Fill layer (30 cm) at Road 02 Station (00+970.00 To 01+100.00). | 27.218 | 1716.84 | 46728.9511
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0181-00 | 2026-02-07 | Inspection for survey works and compaction testing for 3rd Fill layer (30 cm) at Entrance Road 2 Station (00+030.00 to 00+060.00 & 00+250.00 to 0+281.717). | 27.218 | 398.97 | 10859.1655
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0182-00 | 2026-02-08 | Inspection for survey works and compaction testing for 7th Fill layer (30 cm) at Road 02 Station (00+970.00 To 01+100.00). | 27.218 | 1876.09 | 51063.4176
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0183-00 | 2026-02-08 | Inspection for survey works and compaction testing for 4th Fill layer (30 cm) at Entrance Road 2 Station (0+000 To 00+070.00 & 00+240.00 TO 0+281.717). | 27.218 | 780.88 | 21253.9918
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0185-00 | 2026-02-08 | Inspection for survey works and compaction testing for 9th Fill layer (30 cm) at Road 01 Station (0+110 & 00+150 To 260 & 0+430 to 00+830.00). | 27.218 | 2062.47 | 56136.3085
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0186-00 | 2026-02-09 | Inspection for survey works and compaction testing for 8th Fill layer (30 cm) at Road 02 Station (00+960.00 To 01+100.00). | 27.218 | 2621.67 | 71356.6141
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0187-00 | 2026-02-09 | Inspection for survey works and compaction testing for 5th Fill layer (30 cm) at Entrance Road 2 Station (0+000 To 00+150.00 & 00+240.00 To 0+281.717). | 27.218 | 1033.23 | 28122.4541
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0189-00 | 2026-02-09 | Inspection for survey works and compaction testing for 2nd Fill layer (30 cm) at Road 5 Station (00+017.144 To 00+057.14). | 27.218 | 139.78 | 3804.532
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0191-00 | 2026-02-09 | Inspection for survey works and compaction testing for 2nd Fill layer (30 cm) at Custom Road 5 Station (00+060.00 To 00+070.00). | 27.218 | 4.52 | 123.0254
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0192-00 | 2026-02-09 | Inspection for survey works and compaction testing for 10th Fill layer (30 cm) at Road 01 Station (0+110 & 00+150 To 260 & 0+430 To 00+830.00). | 27.218 | 2234.34 | 60814.2661
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0193-00 | 2026-02-10 | Inspection for survey works and compaction testing for 9th Fill layer (30 cm), bottom of A-2-4 at Road 02 Station (00+960.00 To 01+100.00). | 27.218 | 2251.67 | 61285.9541
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0194-00 | 2026-02-10 | Inspection for survey works and compaction testing for 6th Fill layer (30 cm) at Entrance Road 2 Station (0+000 To 00+160.00 & 00+200.00 To 0+281.717). | 27.218 | 1737.53 | 47292.0915
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0195-00 | 2026-02-10 | Inspection for survey works and compaction testing for 3rd Fill layer (30 cm) at Road 5 Station (00+017.144 To 00+072.051). | 27.218 | 236.52 | 6437.6014
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0196-00 | 2026-02-10 | Inspection for survey works and compaction testing for 4th Fill layer (30 cm) at Road 5 Station (00+017.144 To 00+072.051). | 27.218 | 236.52 | 6437.6014
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0197-00 | 2026-02-10 | Inspection for survey works and compaction testing for 3rd Fill layer (30 cm) at Custom Road 5 Station (00+024.38 To 00+090.00 & 00+184.50). | 27.218 | 40.42 | 1100.1516
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0198-00 | 2026-02-10 | Inspection for survey works and compaction testing for 4th Fill layer (30 cm) at Custom Road 5 Station (00+024.38 To 00+090.00 & 00+184.50). | 27.218 | 81.12 | 2207.9242
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0201-00 | 2026-02-11 | Inspection for survey works and compaction testing for 5th Fill layer (30 cm) at Road 5 Station (00+017.144 To 00+072.051). | 27.218 | 576.05 | 15678.9289
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0202-00 | 2026-02-11 | Inspection for survey works and compaction testing for 5th Fill layer (30 cm) at Custom Road 5 Station (0+024.38 To 00+100.00 & 0+184.50). | 27.218 | 141.02 | 3838.2824
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0204-00 | 2026-02-11 | Inspection for survey works and compaction testing for 2nd Fill layer (30 cm) at Asphalt Plot (Intersection 1). | 27.218 | 59.24 | 1612.3943
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0205-00 | 2026-02-12 | Inspection for survey works and compaction testing for 11th Fill layer (30 cm) at Road 01 Station (00+40.00 To 00+50.00 & 00+110.00 To 00+270.00 & 00+400.00 To 00+830.00). | 27.218 | 2406.22 | 65492.496
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0206-00 | 2026-02-12 | Inspection for survey works and compaction testing for 6th Fill layer (30 cm) at Road 5 Station (00+017.144 To 00+072.051). | 27.218 | 696.12 | 18946.9942
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0207-00 | 2026-02-12 | Inspection for survey works and compaction testing for 3rd Fill layer (30 cm) at Asphalt Plot (Intersection 1). | 27.218 | 509.01 | 13854.2342
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0208-00 | 2026-02-14 | Inspection for survey works and compaction testing for 7th Fill layer (30 cm) at Road 5 Station (00+017.144 To 00+072.051). | 27.218 | 862.11 | 23464.91
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0209-00 | 2026-02-14 | Inspection for survey works and compaction testing for 4th Fill layer (30 cm) at Asphalt Plot (Intersection 1). | 27.218 | 793.05 | 21585.2349
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0210-00 | 2026-02-14 | Inspection for survey works and compaction testing for 12th Fill layer (30 cm) at Road 01 Station (00+20.00 To 00+50.00 & 00+110.00 To 00+270.00 & 00+380.00 To 00+270.00). | 27.218 | 2578.09 | 70170.4536
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0211-00 | 2026-02-15 | Inspection for survey works and compaction testing for 13th Fill layer (30 cm), bottom of A-2-4 at Road 01 Station (00+20.00 to 00+050 & 00+110 to 270 & 00+380 TO 830). | 27.218 | 2749.96 | 74848.4113
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0212-00 | 2026-02-15 | Inspection for survey works and compaction testing for 8th Fill layer (30 cm) at Road 5 Station (00+017.144 To 00+072.051). | 27.218 | 982.19 | 26733.2474
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0213-00 | 2026-02-15 | Inspection for survey works and compaction testing for 5th Fill layer (30 cm) at Asphalt Plot (Intersection 1). | 27.218 | 1448.62 | 39428.5392
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0216-00 | 2026-02-16 | Inspection for survey works and compaction testing for 9th Fill layer (30 cm) at Road 5 Station (00+017.144 To 00+072.051). | 27.218 | 1148.17 | 31250.8911
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0217-00 | 2026-02-16 | Inspection for survey works and compaction testing for 6th Fill layer (30 cm) at Asphalt Plot (Intersection 1). | 27.218 | 1775.57 | 48327.4643
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0219-00 | 2026-02-16 | Inspection for survey works and compaction testing for 2nd Fill layer (30 cm) at Customs Road 4 Station (00+075.99 To 00+105.99 & 00+215.99). | 27.218 | 57.08 | 1553.6034
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0220-00 | 2026-02-17 | Inspection for survey works and compaction testing for 10th Fill layer (30 cm), bottom of A-2-4 at Road 5 Station (00+017.144 To 00+072.051). | 27.218 | 1107.08 | 30132.5034
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0221-00 | 2026-02-17 | Inspection for survey works and compaction testing for 7th Fill layer (30 cm), bottom of A-2-4 at Asphalt Plot (Intersection 1). | 27.218 | 1972.14 | 53677.7065
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0222-00 | 2026-02-17 | Inspection for survey works and compaction testing for 3rd Fill layer (30 cm) at Customs Road 4 Station (00+065.99 To 00+115.99 & 00+215.99). | 27.218 | 110.05 | 2995.3409
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0223-00 | 2026-02-18 | Inspection for survey works and compaction testing for 4th Fill layer (30 cm) at Customs Road 4 Station (0+015.987 to 0+221.945). | 27.218 | 252.08 | 6861.1134
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0225-00 | 2026-02-19 | Inspection for survey works and compaction testing for 5th Fill layer (30 cm) at Customs Road 4 From Station (00+025.99 To 00+125.99 & 00+205.99 TO 00+215.99) | 27.218 | 415.18 | 11300.3692
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0226-00 | 2026-02-19 | Inspection for survey works and compaction testing for 1st Fill layer (30 cm) at Commercial RD 1 (0+026.413 to 0+199.390) | 27.218 | 222.45 | 6054.6441
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0227-00 | 2026-02-21 | Inspection for survey works and compaction testing for 6th Fill layer (30 cm), bottom of A-2-4 at Customs Road 4 From Station (00+015.99 To 00+125.99 & 00+205.99 to 00+215.99). | 27.218 | 409.49 | 11145.4988
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0228-00 | 2026-02-21 | Inspection for survey works and compaction testing for 2nd Fill layer (30 cm) at Commercial RD 1 (0+026.413 to 0+199.390). | 27.218 | 328.79 | 8949.0062
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0230-01 | 2026-03-08 | Inspection for survey works and compaction testing for (30 cm) fill, bottom of sub grade layer A-2-4 at Road 01 Station (00+320.00 To 00+830.00). | 27.218 | 5892.52 | 160382.6094
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0231-00 | 2026-02-24 | Inspection for survey works and compaction testing for (30 cm) fill, bottom of sub grade layer A-2-4 at Road 02 Station (0+960 To 1+100). | 27.218 | 412.98 | 11240.4896
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0233-00 | 2026-02-24 | Inspection for survey works and compaction testing for 6th Fill layer (30 cm), bottom of A-2-4 at Customs Road 5 Station (0+24.38 To 00+100.00 & 0+184.50). | 27.218 | 138.92 | 3781.1246
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0234-00 | 2026-02-25 | Inspection for survey works and compaction testing for (30 cm) fill, bottom of sub grade layer A-2-4 at Road 5 Station (00+017.144 To 00+072.051). | 27.218 | 282.92 | 7700.5166
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0235-00 | 2026-02-28 | Inspection for survey works and compaction testing for (30 cm) fill, bottom of sub grade layer A-2-4 at Plot D (Part-1). | 27.218 | 5232.92 | 142429.6166
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0236-00 | 2026-03-01 | Inspection for survey works and compaction testing for (30 cm) fill, bottom of sub grade layer A-2-4 at Customs Road 5 Station (0+24.38 To 0+184.50). | 27.218 | 348.46 | 9484.3843
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0237-00 | 2026-03-03 | Inspection for survey works and compaction testing for 7th Fill layer (30 cm), bottom of A-2-4 at Entrance Road 2 Station (0+000 To 00+160.00 & 00+200.00 To 0+281.717). | 27.218 | 1422.06 | 38705.6291
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0239-00 | 2026-03-05 | Inspection for survey works and compaction testing for (30 cm) fill, bottom of sub grade layer A-2-4 at Entrance Road 01 Station (0+017.629 to 0+312.341). | 27.218 | 335.97 | 9144.4315
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0241-00 | 2026-03-05 | Inspection for survey works and compaction testing for 1st Fill layer (30 cm), at Customs RD 2 Station (00+030.00 to 00+040.00). | 27.218 | 20.62 | 561.2352
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0242-00 | 2026-03-07 | Inspection for survey works and compaction testing for 2nd Fill layer (30 cm), at Customs RD 2 Station (00+000 to 00+050.00 & 00+240.00 TO 00+250.00 & 00+430.00). | 27.218 | 134.11 | 3650.206
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0244-00 | 2026-03-07 | Inspection for survey works and compaction testing for 1st Fill layer (30 cm), at Customs RD 6 Station (0+430 to 0+440). | 27.218 | 12.09 | 329.0656
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0245-00 | 2026-03-07 | Inspection for survey works and compaction testing for 2nd Fill layer (30 cm), at Customs RD 6 Station (0+430 to 0+460). | 27.218 | 53.39 | 1453.169
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0246-00 | 2026-03-08 | Inspection for survey works and compaction testing for 3rd Fill layer (30 cm), at Customs RD 6 Station (00+070.00 to 00+080 & 00+400 to 00+466.413). | 27.218 | 175.2 | 4768.5936
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0247-00 | 2026-03-08 | Inspection for survey works and compaction testing for 4th Fill layer (30 cm), at Customs RD 6 Station (00+070.00 to 00+090 & 00+400 to 00+466.413). | 27.218 | 255.82 | 6962.9088
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0250-00 | 2026-03-08 | Inspection for survey works and compaction testing for 3rd Fill layer (30 cm), at Customs RD 2 Station (00+000 to 00+250.00 & 00+400.00 to 00+620.00 ). | 27.218 | 459.34 | 12502.3161
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0251-00 | 2026-03-08 | Inspection for survey works and compaction testing for 9th Fill layer (30 cm), at Asphalt Plot A, Zone 1. | 27.218 | 4922.31 | 133975.4336
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0252-00 | 2026-03-09 | Inspection for survey works and compaction testing for 5th Fill layer (30 cm), at Customs RD 6 Station (00+070.00 to 00+466.413). | 27.218 | 445.43 | 12123.7137
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0254-00 | 2026-03-09 | Inspection for survey works and compaction testing for 2nd Fill layer (30 cm), at Management RD 2 Station (0+102.939 to 0+142.975). | 27.218 | 108.93 | 2964.8567
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0255-00 | 2026-03-10 | Inspection for survey works and compaction testing for top of embankment (30 cm) fill capping layer at Entrance RD 2 Station (0+000 To 00+281.717). | 27.218 | 817.89 | 22261.33
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0256-00 | 2026-03-10 | Inspection for survey works and compaction testing for 6th Fill layer (30 cm), at Customs RD 6 Station (00+070 To 00+100 & 00+330 to 00+466.413). | 27.218 | 606.21 | 16499.8238
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0257-00 | 2026-03-10 | Inspection for survey works and compaction testing for 3rd Fill layer (30 cm), at Management RD 2 Station (0+092.939 to 0+142.975). | 27.218 | 168.23 | 4578.8841
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0258-00 | 2026-03-11 | Inspection for survey works and compaction testing for top of embankment (30 cm) fill capping layer at Asphalt Plot (Intersection 1). | 27.218 | 557.845 | 15183.4252
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0259-00 | 2026-03-11 | Inspection for survey works and compaction testing for 7th Fill layer (30 cm), at Customs RD 6 Station (0+000 & 00+070 to 00+130 & 00+270 to 00+466.413). | 27.218 | 975.64 | 26554.9695
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0260-00 | 2026-03-11 | Inspection for survey works and compaction testing for 4th Fill layer (30 cm), at Management RD 2 Station (0+072.939 to 0+142.975). | 27.218 | 362.38 | 9863.2588
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0263-00 | 2026-03-12 | Inspection for survey works and compaction testing for 1st Fill layer (30 cm), at Customs RD 1 Station (00+570.00 to 00+580.00). | 27.218 | 0.81 | 22.0466
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0264-00 | 2026-03-12 | Inspection for survey works and compaction testing for 2nd Fill layer (30 cm), at Customs RD 1 Station (00+570 to 00+00+580 & 00+780). | 27.218 | 13.12 | 357.1002
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0267-00 | 2026-03-12 | Inspection for survey works and compaction testing for 4th Fill layer (30 cm), at Customs RD 2 Station (00+000 to 00+250.00 & 00+400.00 to 00+620.00). | 27.218 | 855.44 | 23283.3659
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0268-00 | 2026-03-12 | Inspection for survey works and compaction testing for 8th Fill layer (30 cm), bottom of Capping Layer at Customs RD 6 Station (00+070 to 00+120 to 00+290 & 00+330 to 00+466.413). | 27.218 | 754.3 | 20530.5374
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0269-00 | 2026-03-12 | Inspection for survey works and compaction testing for 5th Fill layer (30 cm), at Management RD 2 Station (0+072.939 to 0+142.975). | 27.218 | 432.4 | 11769.0632
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0270-00 | 2026-03-14 | Inspection for survey works and compaction testing for 5th Fill layer (30 cm), at Customs RD 2 Station (00+000 to 00+290 & 00+380 to 00+440 & 00+550 to 00+680). | 27.218 | 1148.74 | 31266.4053
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0271-00 | 2026-03-14 | Inspection for survey works and compaction testing for 6th Fill layer (30 cm), at Management RD 2 Station (0+062.940 to 0+142.975). | 27.218 | 727.21 | 19793.2018
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0272-00 | 2026-03-14 | Inspection for survey works and compaction testing for 3rd Fill layer (30 cm), at Customs RD 1 Station (00+110 to 00+220 & 00+570 to 00+580 & 00+770 to 00+800). | 27.218 | 30.94 | 842.1249
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0273-00 | 2026-03-14 | Inspection for survey works and compaction testing for 1st Fill layer (30 cm), at Management RD 1 Station (0+168.699 to 0+178.698). | 27.218 | 30.98 | 843.2136
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0274-00 | 2026-03-15 | Inspection for survey works and compaction testing for 6th Fill layer (30 cm), at Customs RD 2 Station (00+000 to 00+290 & 00+370 to 00+440 & 00+540 to 00+690). | 27.218 | 1789.73 | 48712.8711
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0275-00 | 2026-03-15 | Inspection for survey works and compaction testing for 7th Fill layer (30 cm), at Management RD 2 Station (0+042.939 to 0+142.975). | 27.218 | 809.7 | 22038.4146
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0276-00 | 2026-03-15 | Inspection for survey works and compaction testing for 4th Fill layer (30 cm), at Customs RD 1 Station (00+110.00 to 00+240.00 & 00+370.00 to 00+380.00 & 00+560.00 to 00+580.00 & 00+680.00 to 00+810.00). | 27.218 | 110.68 | 3012.4882
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0277-00 | 2026-03-15 | Inspection for survey works and compaction testing for 2nd Fill layer (30 cm), at Management RD 1 Station (0+168.699 to 0+178.698). | 27.218 | 22.2 | 604.2396
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0278-00 | 2026-03-16 | Inspection for survey works and compaction testing for 8th Fill layer (30 cm), bottom of Capping Layer at Management RD 2 Station (0+042.939to 0+142.975). | 27.218 | 886.16 | 24119.5029
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0279-00 | 2026-03-16 | Inspection for survey works and compaction testing for 5th Fill layer (30 cm), at Customs RD 1 Station (00+110.00 to 00+240.00 & 00+370.00 to 00+400.00 & 00+560.00 to 00+810.00). | 27.218 | 352.24 | 9587.2683
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0280-00 | 2026-03-16 | Inspection for survey works and compaction testing for 3rd Fill layer (30 cm), at Management RD 1 Station (0+138.698 to 0+188.698). | 27.218 | 278.6 | 7582.9348
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0281-00 | 2026-03-17 | Inspection for survey works and compaction testing for 4th Fill layer (30 cm), at Management RD 1 Station (0+118.698 to 0+195.792). | 27.218 | 406.42 | 11061.9396
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0282-00 | 2026-03-24 | Inspection for survey works and compaction testing for 6th Fill layer (30 cm), at Customs RD 1 Station (00+100.00 to 00+250.00 & 00+370.00 to 00+400.00 & 00+520.00 to 00+810.00). | 27.218 | 690.81 | 18802.4666
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0287-00 | 2026-03-30 | Inspection for survey works and compaction testing for 10th Fill layer (30 cm), at Asphalt Plot A, Zone 1. | 27.218 | 5387.61 | 146639.969
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0288-00 | 2026-03-30 | Inspection for survey works and compaction testing for 7th Fill layer (30 cm), at Customs RD 1 Station (00+100.00 to 00+260.00 & 00+370.00 to 00+430.00 & 00+520.00 to 00+810.00). | 27.218 | 1138.6 | 30990.4148
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0289-00 | 2026-03-30 | Inspection for survey works and compaction testing for top of embankment (30 cm) fill capping layer at Road 01 Station (00+10.00 to 00+320.00). | 27.218 | 5892.52 | 160382.6094
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0290-00 | 2026-03-30 | Inspection for survey works and compaction testing for 8th Fill layer (30 cm), bottom of capping layer at Customs RD 1 Station (00+100.00 to 00+260.00 & 00+370.00 to 00+430.00 & 00+520.00 to 00+810.00). | 27.218 | 1131.59 | 30799.6166
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0291-00 | 2026-03-31 | Inspection for survey works and compaction testing for 3rd Fill layer (30 cm), at Roundabout, Station (0+000 & 0+080). | 27.218 | 19.52 | 531.2954
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0292-00 | 2026-03-31 | Inspection for survey works and compaction testing for 4th Fill layer (30 cm), at Roundabout, Station (0+000 & 0+080). | 27.218 | 9.369 | 255.0054
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0293-00 | 2026-04-01 | Inspection for survey works and compaction testing for 5th Fill layer (30 cm), at Roundabout, Station (0+000 & 0+075.289 to 0+080.000). | 27.218 | 23.25 | 632.8185
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0294-00 | 2026-04-01 | Inspection for survey works and compaction testing for 11th Fill layer (30 cm), at Asphalt Plot A, Zone 1. | 27.218 | 5235.256 | 142493.1978
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0295-00 | 2026-04-02 | Inspection for survey works and compaction testing for 12th Fill layer (30 cm), at Asphalt Plot A, Zone 1. | 27.218 | 1461.002 | 39765.5524
B1.2.31 23 23.01 | Embankment backfiling | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0296-00 | 2026-04-02 | Inspection for survey works and compaction testing for 6th Fill layer (30 cm), at Roundabout, Station (0+000 to 0+006.005 & 0+066.466 TO 0+084.099). | 27.218 | 247.15 | 6726.9287
B1.2.31 23 23.01 | Embankment backfiling |  | 2026-06-23 | As-built qty for IPC-5 | 27.218 | 50358.14 | 1370647.8545
B1.2.31 23 23.01 | Embankment backfiling |  | 2026-09-15 | As-built qty for IPC-7 | 27.218 | 101932.326 | 2774394.0477
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0315-00 | 2026-05-05 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Asphalt Plot A, Zone 1. | 29.852 | 7267.05 | 216935.9766
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0343-00 | 2026-05-21 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Arterial Road from Station 0+220 to 0+550. | 29.852 | 1159.949 | 34626.7975
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0348-00 | 2026-06-01 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Asphalt Plot D (Part 1). | 29.852 | 3418.685 | 102054.5846
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0356-00 | 2026-06-08 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Asphalt Plot D (Part 2). | 29.852 | 2795.595 | 83454.1019
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0362-00 | 2026-06-10 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Arterial Road from Station 0+550 to 0+710. | 29.852 | 474.147 | 14154.2362
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0371-00 | 2026-06-14 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Asphalt Plot D (Part 3). | 29.852 | 2098.494 | 62644.2429
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0390-00 | 2026-06-20 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Asphalt Plot D (Part 4). | 29.852 | 2204.553 | 65810.3162
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0422-00 | 2026-06-24 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Arterial Road from Station 0+026 to 0+200 (R/S). | 29.852 | 732.657 | 21871.2768
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0458-00 | 2026-07-04 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Asphalt Plot D (Part 5). | 29.852 | 1580.091 | 47168.8765
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0521-00 | 2026-07-12 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Asphalt Plot C (Part 1). | 29.852 | 1475.268 | 44039.7003
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0543-00 | 2026-07-15 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Asphalt Plot C (Part 2). | 29.852 | 3232.218 | 96488.1717
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0544-00 | 2026-07-15 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Asphalt Plot C (Part 3). | 29.852 | 1336.413 | 39894.6009
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0566-00 | 2026-07-25 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Asphalt Plot C (Part 4). | 29.852 | 212.562 | 6345.4008
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0578-00 | 2026-08-03 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Road 01 Station ( 0+054 TO 0+801) | 29.852 | 2119.936 | 63284.3295
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0582-00 | 2026-08-09 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Road 01 Station ( 0+400 TO 0+740) | 29.852 | 2091.646 | 62439.8164
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0585-00 | 2026-08-15 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Arterial Road Left Side Station (0+055 to 0+256). | 29.852 | 662.817 | 19786.4131
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0587-00 | 2026-08-17 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Arterial Road Right Side Station (0+200 to 0+550). | 29.852 | 315.219 | 9409.9176
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0588-00 | 2026-08-17 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Asphalt Plot B (Part 1). | 29.852 | 1276.013 | 38091.5401
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0590-00 | 2026-08-18 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Asphalt Plot B (Part 2). | 29.852 | 1175.371 | 35087.1751
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0591-00 | 2026-08-19 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Asphalt Plot D (Part 6). | 29.852 | 285.947 | 8536.0898
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0593-00 | 2026-08-22 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Asphalt Plot B (Part 3). | 29.852 | 2369.95 | 70747.7474
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0594-00 | 2026-08-22 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Arterial Road Left Side Station (0+260 to 0+500). | 29.852 | 576.025 | 17195.4983
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0602-00 | 2026-08-29 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Asphalt Plot D (Part 7). | 29.852 | 3832.201 | 114398.8643
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0604-00 | 2026-08-30 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Asphalt Plot D (Part 8). | 29.852 | 1122.072 | 33496.0933
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0617-00 | 2026-09-09 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Asphalt Plot D (Part 9). | 29.852 | 2753.245 | 82189.8697
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0642-00 | 2026-09-26 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Asphalt Plot D (Part 10). | 29.852 | 1152.987 | 34418.9679
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0644-00 | 2026-09-26 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Asphalt Plot D (Part 11). | 29.852 | 2697.341 | 80521.0235
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0649-00 | 2026-09-28 | Inspection for survey works and compaction testing of the Subgrade 1st layer (15 cm) at Arterial Deceleration lane Station (0+000 to -0+473). | 29.852 | 502.335 | 14995.7044
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0653-00 | 2026-10-03 | Inspection for survey works and compaction testing of the Subgrade (30 cm) at Road 2 Station (1+200 to 1+600). | 29.852 | 2484.348 | 74162.7565
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0654-00 | 2026-10-03 | Inspection for survey works and compaction testing of the Subgrade (30 cm) at Road 2 Station (0+592 to 1+200). | 29.852 | 3255.845 | 97193.4849
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0656-01 | 2026-10-07 | Inspection for survey works and compaction testing of the Subgrade (30 cm) at Road 4 Station (0+007 to 0+340). | 29.852 | 1975.568 | 58974.6559
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0661-00 | 2026-10-17 | Inspection for survey works and compaction testing of the Subgrade (30 cm) at Road 3 Station (0+020 to 0+325). | 29.852 | 1743.267 | 52040.0065
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0671 | 2026-10-11 | Inspection for survey works and compaction testing of the Subgrade (30 cm) at Road 2 Station (0+080 to 0+592). | 29.852 | 2735.068 | 81647.2499
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0672 | 2026-10-11 | Inspection for survey works and compaction testing of the Subgrade (30 cm) at Road 2 Station (1+600 to 2+217.52). | 29.852 | 3221.627 | 96172.0092
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0673 | 2026-10-11 | Inspection for survey works and compaction testing of the Subgrade (30 cm) at Road 2 Station (2+217.52 to 2+554.225). | 29.852 | 1997.959 | 59643.0721
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0684 | 2026-10-14 | Inspection for survey works and compaction testing of the Subgrade 2nd layer (15 cm) at Arterial Deceleration lane Station (0+000 to -0+473). | 29.852 | 502.335 | 14995.7044
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0685 | 2026-10-17 | Inspection for survey works and compaction testing of the Subgrade (30 cm) at Road 2 Station (0+532.73 to 0+600). | 29.852 | 313.733 | 9365.5575
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0686 | 2026-10-17 | Inspection for survey works and compaction testing of the Subgrade layer (30 cm) at Asphalt Plot D (Part 17). | 29.852 | 2226.92 | 66478.0158
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0687 | 2026-10-18 | Inspection for survey works and compaction testing of the Subgrade 1st layer (15 cm) at Arterial Road Exit 1, Station (0+056.48 to 0+555.81). | 29.852 | 265.463 | 7924.6015
B1.2.32 11 13.01 | Subgrade | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0689 | 2026-10-19 | Inspection for survey works and compaction testing of the Subgrade 2nd layer (15 cm) at Arterial Road Exit 1, Station (0+056.48 to 0+555.81). | 29.852 | 265.463 | 7924.6015
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0328-00 | 2026-05-13 | Inspection for survey works and compaction testing of the Aggregate Base Course layer (20 cm) at Asphalt Plot A (Part 1). | 86.922 | 1227.0558 | 106658.1442
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0329-00 | 2026-05-14 | Inspection for survey works and compaction testing of the Aggregate Base Course layer (20 cm) at Asphalt Plot A (Part 2). | 86.922 | 671.6894 | 58384.586
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0333-00 | 2026-05-17 | Inspection for survey works and compaction testing of the Aggregate Base Course layer (20 cm) at Asphalt Plot A (Part 3). | 86.922 | 1266.529 | 110089.2337
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0339-00 | 2026-05-20 | Inspection for survey works and compaction testing of the Aggregate Base Course layer (20 cm) at Asphalt Plot A (Part 4). | 86.922 | 737.8956 | 64139.3613
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0346-00 | 2026-05-23 | Inspection for survey works and compaction testing of the Aggregate Base Course layer (20 cm) at Arterial Road, Station (0+200 to 0+550). | 86.922 | 773.2992 | 67216.7131
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0355-00 | 2026-06-08 | Inspection for survey works and compaction testing of the Aggregate Base Course layer (20 cm) at Asphalt Plot D (Part 1). | 86.922 | 1140 | 99091.08
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0357-00 | 2026-06-09 | Inspection for survey works and compaction testing of the Aggregate Base Course layer (20 cm) at Asphalt Plot D (Part 2). | 86.922 | 1140 | 99091.08
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0405-00 | 2026-06-23 | Inspection for survey works and compaction testing of the Aggregate Base Course layer (20 cm) at Asphalt Plot D (Part 3). | 86.922 | 1800 | 156459.6
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0435-00 | 2026-06-28 | Inspection for survey works and compaction testing of the Aggregate Base Course layer (20 cm) at Asphalt Plot D (Part 4). | 86.922 | 1266.554 | 110091.4068
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0445-00 | 2026-06-30 | Inspection for survey works and compaction testing of the Aggregate Base Course layer (20 cm) at Arterial Road (R/S), Station (0+037 to 0+200). | 86.922 | 457.534 | 39769.7703
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0495-00 | 2026-07-09 | Inspection for survey works and compaction testing of Aggregate Base Course layer (20 cm) at Asphalt Plot D (Part 5). | 86.922 | 942.65 | 81937.0233
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0537-00 | 2026-07-14 | Inspection for survey works and compaction testing of Aggregate Base Course layer (20 cm) at Asphalt Plot D (Part 6). | 86.922 | 365.102 | 31735.396
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0554-00 | 2026-07-18 | Inspection for survey works and compaction testing of Aggregate Base Course layer (20 cm) at Asphalt Plot C (Part 1). | 86.922 | 1077.588 | 93666.1041
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0568-00 | 2026-07-26 | Inspection for survey works and compaction testing of Aggregate Base Course layer (20 cm) at Asphalt Plot C (Part 2). | 86.922 | 2020.404 | 175617.5565
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0589-00 | 2026-08-18 | Inspection for survey works and compaction testing of Aggregate Base Course layer (20 cm) at Arterial Road Right Side Station (0+200 to 0+550). | 86.922 | 210.146 | 18266.3106
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0596-00 | 2026-08-24 | Inspection for survey works and compaction testing of Aggregate Base Course layer (20 cm) at Asphalt Plot B (Part 1). | 86.922 | 1612.756 | 140183.977
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0598-00 | 2026-08-25 | Inspection for survey works and compaction testing of Aggregate Base Course layer (20 cm) at Asphalt Plot D (Part 7). | 86.922 | 1419.274 | 123366.1346
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0603-00 | 2026-08-29 | Inspection for survey works and compaction testing of Aggregate Base Course layer (20 cm) at Asphalt Plot B (Part 2). | 86.922 | 1347.566 | 117133.1319
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0607-00 | 2026-09-02 | Inspection for survey works and compaction testing of Aggregate Base Course layer (20 cm) at Asphalt Plot D (Part 8). | 86.922 | 1345.391 | 116944.0765
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0615 | 2026-09-08 | Inspection for survey works and compaction testing of Aggregate Base Course layer (20 cm) at Asphalt Plot D (Part 9). | 86.922 | 1519.132 | 132045.9917
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0621-01 | 2026-10-17 | Inspection for survey works and compaction testing of Aggregate Base Course layer (20 cm) at Road 1 (0+054 to 0+400) PART 1 | 86.922 | 1413.291 | 122846.0803
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0622-01 | 2026-10-17 | Inspection for survey works and compaction testing of Aggregate Base Course layer (20 cm) at Road 1 (0+400 to 0+740) PART 2 | 86.922 | 1394.431 | 121206.7314
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0635 | 2026-09-20 | Inspection for survey works and compaction testing of Aggregate Base Course layer (20 cm) at Asphalt Plot D (Part 10). | 86.922 | 1150.953 | 100043.1367
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0640 | 2026-09-24 | Inspection for survey works and compaction testing of Aggregate Base Course layer (20 cm) at Asphalt Plot D (Part 11). | 86.922 | 566.379 | 49230.7954
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0645 | 2026-09-27 | Inspection for survey works and compaction testing of Aggregate Base Course layer (20 cm) at Asphalt Plot D (Part 12). | 86.922 | 768.658 | 66813.2907
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0646 | 2026-09-27 | Inspection for survey works and compaction testing of Aggregate Base Course layer (20 cm) at Asphalt Plot D (Part 13). | 86.922 | 1519.387 | 132068.1568
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0647 | 2026-09-27 | Inspection for survey works and compaction testing of Aggregate Base Course layer (20 cm) at Asphalt Plot D (Part 14). | 86.922 | 30.126 | 2618.6122
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0650-01 | 2026-10-19 | Inspection for survey works and compaction testing of the Aggregate Base Course layer (20 cm) at Arterial Road (R/S), Station (0+055 to 0+310). | 86.922 | 499.262 | 43396.8516
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0663 | 2026-10-19 | Inspection for survey works and compaction testing of Aggregate Base Course layer (20 cm) at Asphalt Plot D (Part 15). | 86.922 | 920.397 | 80002.748
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0667 | 2026-10-19 | Inspection for survey works and compaction testing of Aggregate Base Course layer (20 cm) at Road 3. | 86.922 | 1162.178 | 101018.8361
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0674 | 2026-10-19 | Inspection for survey works and compaction testing of Aggregate Base Course layer (20 cm) at Road 4 Station (0+007.764 to 0+337.398). | 86.922 | 1317.046 | 114480.2724
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0676 | 2026-10-19 | Inspection for survey works and compaction testing of the Aggregate Base Course layer (20 cm) at Arterial Road (L/S), Station (0+315 to 0+515) Part 1. | 86.922 | 299.179 | 26005.237
B1.2.32 11 23.01 | Aggregate base course | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0688 | 2026-10-19 | Inspection for survey works and compaction testing of Aggregate Base Course layer (20 cm) at Road 2 Station (0+592.231 to 1+561.148). | 86.922 | 3570.786 | 310379.8607
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0347-00 | 2026-05-31 | Inspection for Placement of 1st layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Asphalt Plot A as per attached survey data. | 549.628 | 1308.2752 | 719064.7091
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0361-00 | 2026-06-10 | Inspection for Placement of 2nd layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Asphalt Plot A as per attached survey data (Total thickness of Asphalt Bituminous Base course is 15 cm). | 549.628 | 1196.8972 | 657848.2417
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0363-00 | 2026-06-11 | Inspection for Placement of 1st layer (10 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Arterial Road, Station (0+220 to 0+550) as per attached survey data (Total thickness of Asphalt Bituminous Base course is 20 cm). | 549.628 | 259.882 | 142838.4239
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0403-00 | 2026-06-22 | Inspection for Placement of 1st layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Asphalt Plot D Part:1 as per attached survey data. | 549.628 | 781.875 | 429740.3925
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0411-00 | 2026-06-22 | Inspection for Placement of 2nd layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Asphalt Plot D (Part 1) as per attached survey data (Total thickness of Asphalt Bituminous Base course is 15 cm). | 549.628 | 377.757 | 207625.8244
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0448-00 | 2026-07-04 | Inspection for Placement of 1st layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Asphalt Plot D (Part 2) as per attached survey data. | 549.628 | 617.4862 | 339387.7326
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0452-00 | 2026-07-09 | Inspection for Placement of 2nd layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Asphalt Plot D (Part 2) as per attached survey data (Total thickness of Asphalt Bituminous Base course is 15 cm). | 549.628 | 1002.7095 | 551117.2171
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0504-00 | 2026-07-09 | Inspection for Placement of 1st layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Asphalt Plot D Part:3 as per attached survey data. | 549.628 | 267.6712 | 147119.6138
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0505-00 | 2026-07-09 | Inspection for Placement of 1st layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Asphalt Plot D Part:4 as per attached survey data. | 549.628 | 133.704 | 73487.4621
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0509-00 | 2026-07-11 | Inspection for Placement of 2nd layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Asphalt Plot D Part:3 as per attached survey data. | 549.628 | 267.6712 | 147119.6138
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0545-00 | 2026-07-15 | Inspection for Placement of 1st layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Asphalt Plot D Part: 5 as per attached survey data. | 549.628 | 136.9133 | 75251.3558
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0559-00 | 2026-07-19 | Inspection for Placement of 2nd layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Asphalt Plot D Part: 4 as per attached survey data. | 549.628 | 268.881 | 147784.5263
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0565-00 | 2026-07-25 | Inspection for Placement of 1st layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Arterial Road Right Side Station (0+036 to 0+220) as per attached survey data. | 549.628 | 221.196 | 121575.5151
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0570-00 | 2026-07-27 | Inspection for Placement of 1st layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Asphalt Plot D Part: 6 as per attached survey data. | 549.628 | 348.894 | 191761.9114
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0572-00 | 2026-07-28 | Inspection for Placement of 1st layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Asphalt Plot C Part: 1 as per attached survey data. | 549.628 | 415.413 | 228322.6164
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0574-00 | 2026-07-28 | Inspection for Placement of 2nd layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Asphalt Plot D Part: 5 as per attached survey data. | 549.628 | 348.894 | 191761.9114
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0576-00 | 2026-07-29 | Inspection for Placement of 2nd layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Asphalt Plot C Part: 1 as per attached survey data. | 549.628 | 415.413 | 228322.6164
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0579-00 | 2026-08-04 | Inspection for Placement of 1st layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Asphalt Plot C Part: 2 as per attached survey data. | 549.628 | 605.318 | 332699.7217
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0582-00 | 2026-08-10 | Inspection for Placement of 2nd layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Asphalt Plot C Part: 2 as per attached survey data. | 549.628 | 576.873 | 317065.5532
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0605-00 | 2026-08-31 | Inspection for Placement of 1st layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Asphalt Plot B Part: 1 as per attached survey data. | 549.628 | 659.739 | 362611.0271
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0608-00 | 2026-09-02 | Inspection for Placement of 1st layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Asphalt Plot B Part: 2 as per attached survey data. | 549.628 | 360.052 | 197894.6607
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0609-01 | 2026-10-18 | Inspection for Placement of 1st layer (10 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Arterial Road Right Side Station (0+076 to 0+550) as per attached survey data. (Part 2) | 549.628 | 239.484 | 131627.112
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0614-00 | 2026-09-08 | Inspection for Placement of 2nd layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Asphalt Plot B Part: 1 as per attached survey data. | 549.628 | 1019.791 | 560505.6877
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0624-01 | 2026-10-07 | Inspection for Placement of 2nd layer (10 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Arterial Road Right Side Station (0+080.94 to 0+528.16) as per attached survey data. | 549.628 | 628.516 | 345449.992
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0625 | 2026-09-14 | Inspection for Placement of 1st layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Asphalt Plot D Part: 7 as per attached survey data. | 549.628 | 712.116 | 391398.8928
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0627 | 2026-09-14 | Inspection for Placement of 2nd layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Asphalt Plot D Part: 6 as per attached survey data. | 549.628 | 721.401 | 396502.1888
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0631 | 2026-09-16 | Inspection for Placement of 1st layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Asphalt Plot D Part: 8 as per attached survey data. | 549.628 | 714.05 | 392461.8734
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0633 | 2026-09-16 | Inspection for Placement of 2nd layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Asphalt Plot D Part: 7 as per attached survey data. | 549.628 | 714.05 | 392461.8734
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0636 | 2026-10-19 | Inspection for Placement of 1st layer (7 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Road 1 station (0+054 to 0+740) as per attached survey data. | 549.628 | 982.702 | 540120.5349
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0658 | 2026-10-05 | Survey Inspection for Placement of 1st layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Asphalt Plot D Part: 9 as per attached survey data. | 549.628 | 1521.558 | 836290.8804
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0660 | 2026-10-07 | Survey Inspection for Placement of 2nd layer (7.5 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Asphalt Plot D Part: 8 as per attached survey data. | 549.628 | 1061.869 | 583632.9347
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0678 | 2026-10-12 | Survey Inspection for Placement of 1st layer (7 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Road 3 (Station 0+020 to 0+325) as per attached survey data. | 549.628 | 406.762 | 223567.7845
B1.2.32 11 26.01 | Bituminous base course(Grading I - Class A), including Prime Coat (MC1) and tack coat (RC2) | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0682 | 2026-10-19 | Inspection for Placement of 1st layer (10 cm) of Asphalt Bituminous Base course (Grading I – Class A) at Left Arterial Road (Part 1) Station (0+055 to 0+500) as per attached survey data. | 549.628 | 398.89 | 219241.1129
B1.2.32 16.13.01 | Curb Stone, Type K1 | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0638 | 2026-09-22 | Survey FIR for installation of Curb Stones (Type K1) at Right Arterial Road (Part 1) B/S Station (0+090 to 0+520). | 75.508 | 857.59 | 64754.9057
B1.2.32 16.13.01 | Curb Stone, Type K1 | DAM2-02-09-SAJ-TS9-1-ROD-FIR-0680 | 2026-10-12 | Survey FIR for installation of Curb Stones (Type K1) at Road 1 R/S (Station 0+210 to 0+630). | 75.508 | 426.336 | 32191.7787
B2.31 23 00.01 | Excavation for Trench size 40cm wide and 80cm deep (for 1 cable) | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0162 | 2026-10-06 | FIR for Excavation and Sand Bedding Placement for Medium Voltage Cable, at Road (RD-02),@. Zone-3 & 4 Substation No. SS-20 to SS-6 SS-6 to SS-22 | 22.828 | 460.8 | 10519.1424
B2.31 23 00.02 | Excavation for Trench size 60cm wide and 80cm deep ( for 2 cables) | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0160 | 2026-10-06 | FIR for Excavation and Sand Bedding Placement for Medium Voltage Cable, at Road (RD-01),@. Zone-1 Substation No. SS-11 to SS-7 SS-11 to SS-8 SS-7 to SS-9 SS-8 to SS-15 SS-9 to SS-22 | 22.828 | 396.96 | 9061.8029
B2.33 71 00.02 | Duct bank for MV cables UPVC(4x150mm) | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0164 | 2026-10-06 | FIR for Concrete Pouring of Medium Voltage Cable, Duct Bank UPVC (4xØ150mm), at Road (RD-01)Sta. 0+370.47,@. Zone-1 # “MV-DUCT BANK-01” | 550.506 | 20.5 | 11285.373
B2.33 71 49.23.01 | Cable 13.8 kV 3Cx 500 mm² Al XLPE,/LLDPE / Unarmored | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0161 | 2026-10-06 | FIR for Medium Voltage Cable Laying (Cable 13.8 kV 3Cx 500 mm² Al XLPE,/LLDPE) Including Backfill, at Road (RD-01),@. Zone-1 Substation No. SS-11 to SS-7 SS-11 to SS-8 SS-7 to SS-9 SS-8 to SS-15 SS-9 to SS-22 | 343.298 | 1711 | 587382.878
B2.33 71 49.23.01 | Cable 13.8 kV 3Cx 500 mm² Al XLPE,/LLDPE / Unarmored | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0163 | 2026-10-06 | FIR for Medium Voltage Cable Laying (Cable 13.8 kV 3Cx 500 mm² Al XLPE,/LLDPE), Including Backfill, at Road (RD-02),@. Zone-3 & 4 Substation No. SS-20 to SS-6 SS-6 to SS-22 | 343.298 | 1440 | 494349.12
B2.33 71 00 01 01 | Duct bank for LV cables UPVC (2x110mm) | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0005 | 2026-05-09 | FIR for Concrete Pouring of Duct bank for LV cables UPVC (2xØ110mm), at Road (RD-01).@ Sta. 0+821.55, # “LV-Duct Bank-02” | 275.692 | 14 | 3859.688
B2.33 71 00 01 01 | Duct bank for LV cables UPVC (2x110mm) | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0110 | 2026-09-27 | FIR for Concrete Pouring of Duct bank for LV cables UPVC (2xØ110mm), at Road (RD-02) ,Sta.1+292.80, @Zone-4 1) “LV-Duct Bank-05” | 275.692 | 20.5 | 5651.686
B2.33 71 00 01 01 | Duct bank for LV cables UPVC (2x110mm) | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0125 | 2026-09-27 | FIR for Concrete Pouring of Duct bank for LV cables UPVC (2xØ110mm), at Road (RD-04). ),Sta.0+331.50, @Zone-4 1) “LV-Duct Bank-09” | 275.692 | 35 | 9649.22
B2.33 71 00 01 01 | Duct bank for LV cables UPVC (2x110mm) | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0146 | 2026-09-30 | FIR for Concrete Pouring of Duct bank for LV cables UPVC (6xØ110mm), at Road (RD-02), Sta.0+110.45, @Zone-3 1) “LV-Duct Bank-03 (a)” | 568.944 | 4.4 | 2503.3536
B2.33 71 00 01 01 | Duct bank for LV cables UPVC (2x110mm) | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0159 | 2026-10-05 | FIR for Concrete Pouring of Duct bank for LV cables UPVC (2xØ110mm), at Road (RD-02), Sta.2+538.50, @Zone-4 1) “LV-Duct Bank-06” | 568.944 | 25.5 | 14508.072
B2.33 71 00 01 01 | Duct bank for LV cables UPVC (2x110mm) | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0222 | 2026-10-14 | FIR for Concrete Pouring of Duct bank for LV cables UPVC (4xØ110mm), at Road (RD-02), Sta.0+058.20, @Zone-3 1) “LV-Duct Bank-11” | 568.944 | 15.95 | 9074.6568
B2.33 71 00 01 01 | Duct bank for LV cables UPVC (2x110mm) | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0239 | 2026-10-15 | FIR for Concrete Pouring of Duct bank for LV cables UPVC (2xØ110mm), at Road (RD-05), Sta.0+114.40, @Zone-3 1) “LV-Duct Bank-27” | 568.944 | 7.75 | 4409.316
B2.33 71 00 01 02 | Duct bank for LV cables UPVC (4x110mm) | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0047 | 2026-09-10 | FIR for Concrete Pouring of Duct bank for LV cables UPVC (4xØ110mm), at Road (RD-03).@ Sta. 0+016.9 & 0+331.55,Zone-4 1) “LV-Duct Bank-07” (L=27.50m) 2) “LV-Duct Bank-08” (L=35.00m) | 421.44 | 62.5 | 26340
B2.33 71 00 01 02 | Duct bank for LV cables UPVC (4x110mm) | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0126 | 2026-09-27 | FIR for Concrete Pouring of Duct bank for LV cables UPVC (4xØ110mm), at Road (RD-04). ), Sta. 0+016.9 @Zone-4 1) “LV-Duct Bank-10” | 421.44 | 27.5 | 11589.6
B2.33 71 00 01 03 | Duct bank for LV cables UPVC (6xØ110mm) | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0113 | 2026-09-27 | FIR for Concrete Pouring of Duct bank for LV cables UPVC (6xØ110mm), at Road (RD-02). ) ,Sta.1+209.60, @Zone-4 1) “LV-Duct Bank-04” | 568.944 | 17.5 | 9956.52
B2.33 71 00 01 03 | Duct bank for LV cables UPVC (6xØ110mm) | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0140 | 2026-09-29 | FIR for Concrete Pouring of Duct bank for LV cables UPVC (6xØ110mm), at Road (RD-02). ) ,Sta. 0+127.40, @Zone-3 1) “LV-Duct Bank-03” | 568.944 | 21 | 11947.824
B2.33 71 00 01 01 | Cable, Copper 4x10mm2/ CU/XLPE/SWA/PVC + 1x10mm2 CU/PVC | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0067 | 2026-09-17 | Survey for Excavation for Cable Trench and Sand Bedding at Road (Arterial RD) Right Side. Sta. 0+052.2 to 0+509.6. @Zone-3 Pole Number :- FP-23-2 to FP-23-2/6/1R = 12m FP-23-2/6/1R to FP-23-2/6/2Y = 34.2m FP-23-2/6/2Y to FP-23-2/6/3B = 34.2m FP-23-2/6/3B to FP-23-2/6/4R = 34.2m FP-23-2/6/4R to FP-23-2/6/5Y = 34.2m FP-23-2/6/5Y to FP-23-2/6/6B = 34.2m FP-23-2/6/6B to FP-23-2/6/7R = 34.2m FP-23-2/6/7R to FP-23-2/6/8Y = 34.2m FP-23-2/6/8Y to FP-23-2/6/9B = 34.2m FP-23-2/6/9B to FP-23-2/6/10R = 34.2m FP-23-2/6/10R to FP-23-2/6/11Y = 34.2m FP-23-2/6/11Y to FP-23-2/6/12B = 34.2m FP-23-2 to FP-23-2/5/1R = 37.5m FP-23-2/5/1R to FP-23-2/5/2Y = 34.2m FP-23-2/5/2Y to FP-23-2/5/3B = 34.2m FP-23-2/5/3B to FP-23-2/5/4R = 34.2m | 62.338 | 52.83 | 3293.3165
B2.33 71 00 01 01 | Cable, Copper 4x10mm2/ CU/XLPE/SWA/PVC + 1x10mm2 CU/PVC | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0069 | 2026-09-19 | FIR for Cable (4x10mm2) Installation for Street Lighting Pole at Road (Arterial RD) Right Side. Sta. 0+052.2 to 0+509.6. @Zone-3 Pole Number :- FP-23-2 to FP-23-2/6/1R = 12m FP-23-2/6/1R to FP-23-2/6/2Y = 34.2m FP-23-2/6/2Y to FP-23-2/6/3B = 34.2m FP-23-2/6/3B to FP-23-2/6/4R = 34.2m FP-23-2/6/4R to FP-23-2/6/5Y = 34.2m FP-23-2/6/5Y to FP-23-2/6/6B = 34.2m FP-23-2/6/6B to FP-23-2/6/7R = 34.2m FP-23-2/6/7R to FP-23-2/6/8Y = 34.2m FP-23-2/6/8Y to FP-23-2/6/9B = 34.2m FP-23-2/6/9B to FP-23-2/6/10R = 34.2m FP-23-2/6/10R to FP-23-2/6/11Y = 34.2m FP-23-2/6/11Y to FP-23-2/6/12B = 34.2m FP-23-2 to FP-23-2/5/1R = 37.5m FP-23-2/5/1R to FP-23-2/5/2Y = 34.2m FP-23-2/5/2Y to FP-23-2/5/3B = 34.2m FP-23-2/5/3B to FP-23-2/5/4R = 34.2m | 62.338 | 316.98 | 19759.8992
B2.33 71 00 01 01 | Cable, Copper 4x10mm2/ CU/XLPE/SWA/PVC + 1x10mm2 CU/PVC | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0162 | 2026-10-06 | Survey and Compaction FIR for Backfill and Warning Tape Installation for Street Lighting Cable, Layer-2, at Road (Arterial RD) Right Side. Sta. 0+052.2 to 0+509.6. @Zone-3 Pole Number :- FP-23-2 to FP-23-2/6/1R = 12m FP-23-2/6/1R to FP-23-2/6/2Y = 34.2m FP-23-2/6/2Y to FP-23-2/6/3B = 34.2m FP-23-2/6/3B to FP-23-2/6/4R = 34.2m FP-23-2/6/4R to FP-23-2/6/5Y = 34.2m FP-23-2/6/5Y to FP-23-2/6/6B = 34.2m FP-23-2/6/6B to FP-23-2/6/7R = 34.2m FP-23-2/6/7R to FP-23-2/6/8Y = 34.2m FP-23-2/6/8Y to FP-23-2/6/9B = 34.2m FP-23-2/6/9B to FP-23-2/6/10R = 34.2m FP-23-2/6/10R to FP-23-2/6/11Y = 34.2m FP-23-2/6/11Y to FP-23-2/6/12B = 34.2m FP-23-2 to FP-23-2/5/1R = 37.5m FP-23-2/5/1R to FP-23-2/5/2Y = 34.2m FP-23-2/5/2Y to FP-23-2/5/3B = 34.2m FP-23-2/5/3B to FP-23-2/5/4R = 34.2m | 62.338 | 105.66 | 6586.6331
B2.33 71 00 01 01 | Cable, Copper 4x10mm2/ CU/XLPE/SWA/PVC + 1x10mm2 CU/PVC | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0200 | 2026-10-12 | FIR for Cable (4x10mm2) Installation for Street Lighting Pole, at Road (RD-01) Right Side. Sta. 0+040 to 0+808.8, @Zone-1 Pole Number :- FP-22-2/4/2Y to FP-22-2/4/3B 33.70m FP-22-2/4/3B to FP-22-2/4/4R 33.70m FP-22-2/4/4R to FP-22-2/4/5Y 28.70m FP-22-2/4/5Y to FP-22-2/4/6B 29.70m FP-22-2/4/6B to FP-22-2/4/7R 33.70m FP-22-2/4/7R to FP-22-2/4/8Y 33.70m FP-22-2/4/8Y to FP-22-2/4/9B 33.70m FP-22-2/4/9B to FP-22-2/4/10R 33.70m FP-22-2/4/10R to FP-22-2/4/11Y 33.70m FP-22-2/4/11Y to FP-22-2/4/12B 33.70m FP-22-2/4/12B to FP-22-2/4/13R 33.70m FP-22-2/4/13R to FP-22-2/4/14Y 33.70m FP-22-2/4/14Y to FP-22-2/4/15B 33.70m FP-22-2/4/15B to FP-22-2/4/16R 33.70m FP-22-2/4/16R to FP-22-2/4/17Y 33.70m FP-22-2/4/17Y to FP-22-2/4/18B 33.70m FP-22-2/4/18B to FP-22-2/4/19R 33.70m FP-22-2/4/19R to FP-22-2/4/20Y 33.70m FP-22-2/4/20Y to FP-22-2/4/21B 33.70m FP-22-2/4/21B to FP-22-2/4/22R 32.20m FP-22-2/4/22R to FP-22-2/4/23Y 35.20m FP-22-2/4/23Y to FP-22-2/4/24B 33.70m FP-22-2/4/24B to FP-22-2/4/25R 33.70m FP-22-2/4/25R to FP-22-2/4/26Y 33.70m FP-22-2/4/26Y to FP-22-2/4/27B 34.20m FP-22-2/4/27B to FP-22-2/4/28R 36.70m FP-22-2/4/28R to FP-22-2/4/29Y 33.70m FP-22-2/4/29Y to FP-22-2/4/30B 33.20m | 62.338 | 93.75 | 5844.1875
B2.33 71 00 01 01 | Cable, Copper 4x10mm2/ CU/XLPE/SWA/PVC + 1x10mm2 CU/PVC | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0205 | 2026-10-12 | FIR for Cable (4x10mm2) Installation for Street Lighting Pole, at Road (RD-01) Right Side. Sta. 0+040 to 0+808.8, @Zone-1 Pole Number :- FP-22-2/4/2Y to FP-22-2/4/3B 33.70m FP-22-2/4/3B to FP-22-2/4/4R 33.70m FP-22-2/4/4R to FP-22-2/4/5Y 28.70m FP-22-2/4/5Y to FP-22-2/4/6B 29.70m FP-22-2/4/6B to FP-22-2/4/7R 33.70m FP-22-2/4/7R to FP-22-2/4/8Y 33.70m FP-22-2/4/8Y to FP-22-2/4/9B 33.70m FP-22-2/4/9B to FP-22-2/4/10R 33.70m FP-22-2/4/10R to FP-22-2/4/11Y 33.70m FP-22-2/4/11Y to FP-22-2/4/12B 33.70m FP-22-2/4/12B to FP-22-2/4/13R 33.70m FP-22-2/4/13R to FP-22-2/4/14Y 33.70m FP-22-2/4/14Y to FP-22-2/4/15B 33.70m FP-22-2/4/15B to FP-22-2/4/16R 33.70m FP-22-2/4/16R to FP-22-2/4/17Y 33.70m FP-22-2/4/17Y to FP-22-2/4/18B 33.70m FP-22-2/4/18B to FP-22-2/4/19R 33.70m FP-22-2/4/19R to FP-22-2/4/20Y 33.70m FP-22-2/4/20Y to FP-22-2/4/21B 33.70m FP-22-2/4/21B to FP-22-2/4/22R 32.20m FP-22-2/4/22R to FP-22-2/4/23Y 35.20m FP-22-2/4/23Y to FP-22-2/4/24B 33.70m FP-22-2/4/24B to FP-22-2/4/25R 33.70m FP-22-2/4/25R to FP-22-2/4/26Y 33.70m FP-22-2/4/26Y to FP-22-2/4/27B 34.20m FP-22-2/4/27B to FP-22-2/4/28R 36.70m FP-22-2/4/28R to FP-22-2/4/29Y 33.70m FP-22-2/4/29Y to FP-22-2/4/30B 33.20m | 62.338 | 562.47 | 35063.2549
B2.33 71 00 01 01 | Cable, Copper 4x10mm2/ CU/XLPE/SWA/PVC + 1x10mm2 CU/PVC | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0209 | 2026-10-13 | Survey and Compaction FIR for Backfill above the Street Lighting Cable, Layer-1, at Road (RD-01) Right Side. Sta. 0+040 to 0+808.8, @Zone-1 Pole Number :- FP-22-2/4/2Y to FP-22-2/4/3B 33.70m FP-22-2/4/3B to FP-22-2/4/4R 33.70m FP-22-2/4/4R to FP-22-2/4/5Y 28.70m FP-22-2/4/5Y to FP-22-2/4/6B 29.70m FP-22-2/4/6B to FP-22-2/4/7R 33.70m FP-22-2/4/7R to FP-22-2/4/8Y 33.70m FP-22-2/4/8Y to FP-22-2/4/9B 33.70m FP-22-2/4/9B to FP-22-2/4/10R 33.70m FP-22-2/4/10R to FP-22-2/4/11Y 33.70m FP-22-2/4/11Y to FP-22-2/4/12B 33.70m FP-22-2/4/12B to FP-22-2/4/13R 33.70m FP-22-2/4/13R to FP-22-2/4/14Y 33.70m FP-22-2/4/14Y to FP-22-2/4/15B 33.70m FP-22-2/4/15B to FP-22-2/4/16R 33.70m FP-22-2/4/16R to FP-22-2/4/17Y 33.70m FP-22-2/4/17Y to FP-22-2/4/18B 33.70m FP-22-2/4/18B to FP-22-2/4/19R 33.70m FP-22-2/4/19R to FP-22-2/4/20Y 33.70m FP-22-2/4/20Y to FP-22-2/4/21B 33.70m FP-22-2/4/21B to FP-22-2/4/22R 32.20m FP-22-2/4/22R to FP-22-2/4/23Y 35.20m FP-22-2/4/23Y to FP-22-2/4/24B 33.70m FP-22-2/4/24B to FP-22-2/4/25R 33.70m FP-22-2/4/25R to FP-22-2/4/26Y 33.70m FP-22-2/4/26Y to FP-22-2/4/27B 34.20m FP-22-2/4/27B to FP-22-2/4/28R 36.70m FP-22-2/4/28R to FP-22-2/4/29Y 33.70m FP-22-2/4/29Y to FP-22-2/4/30B 33.20m | 62.338 | 187.49 | 11687.7516
B2.33 71 00 01 01 | Cable, Copper 4x10mm2/ CU/XLPE/SWA/PVC + 1x10mm2 CU/PVC | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0223 | 2026-10-14 | Survey for Excavation for Street Lighting, Cable Trench and Sand Bedding, at Road (RD-01) Left Side. Sta. 0+0330.30 to 0+808.8, @Zone-1 Pole Number :- FP-22-2/3/22R to FP-22-2/3/23Y 33.70m FP-22-2/3/23Y to FP-22-2/3/24B 33.70m FP-22-2/3/24B to FP-22-2/3/25R 33.70m FP-22-2/3/25R to FP-22-2/3/26Y 33.70m FP-22-2/3/26Y to FP-22-2/3/27B 33.70m FP-22-2/3/27B to FP-22-2/32/8R 33.70m FP-22-2/3/28R to FP-22-2/3/29Y 33.70m FP-22-2/3/29Y to FP-22-2/3/30B 33.70m FP-22-2/3/30B to FP-22-2/3/31R 32.20m FP-22-2/3/31R to FP-22-2/3/32Y 35.20m FP-22-2/3/32Y to FP-22-2/3/33B 33.70m FP-22-2/3/33B to FP-22-2/3/34R 30.70m FP-22-2/3/34R to FP-22-2/3/35Y 33.70m FP-22-2/3/35Y to FP-22-2/3/36B 33.70m FP-22-2/3/36B to FP-22-2/3/37R 34.45m | 62.338 | 50.33 | 3137.4715
B2.33 71 00 01 01 | Cable, Copper 4x10mm2/ CU/XLPE/SWA/PVC + 1x10mm2 CU/PVC | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0224 | 2026-10-14 | FIR for Cable (4x10mm2)+(1x10mm2) Installation for Street Lighting Pole, at Road (RD-01) Left Side. Sta. 0+030.30 to 0+808.8, @Zone-1 Pole Number :- FP-22-2/3/22R to FP-22-2/3/23Y 33.70m FP-22-2/3/23Y to FP-22-2/3/24B 33.70m FP-22-2/3/24B to FP-22-2/3/25R 33.70m FP-22-2/3/25R to FP-22-2/3/26Y 33.70m FP-22-2/3/26Y to FP-22-2/3/27B 33.70m FP-22-2/3/27B to FP-22-2/32/8R 33.70m FP-22-2/3/28R to FP-22-2/3/29Y 33.70m FP-22-2/3/29Y to FP-22-2/3/30B 33.70m FP-22-2/3/30B to FP-22-2/3/31R 32.20m FP-22-2/3/31R to FP-22-2/3/32Y 35.20m FP-22-2/3/32Y to FP-22-2/3/33B 33.70m FP-22-2/3/33B to FP-22-2/3/34R 30.70m FP-22-2/3/34R to FP-22-2/3/35Y 33.70m FP-22-2/3/35Y to FP-22-2/3/36B 33.70m FP-22-2/3/36B to FP-22-2/3/37R 34.45m | 62.338 | 301.95 | 18822.9591
B2.33 71 00 01 01 | Cable, Copper 4x10mm2/ CU/XLPE/SWA/PVC + 1x10mm2 CU/PVC | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0232 | 2026-10-15 | Survey and Compaction FIR for Backfill above the Street Lighting Cable, Layer-1, at Road (RD-01) Left Side. Sta. 0+0330.30 to 0+808.8, @Zone-1 Pole Number :- FP-22-2/3/22R to FP-22-2/3/23Y 33.70m FP-22-2/3/23Y to FP-22-2/3/24B 33.70m FP-22-2/3/24B to FP-22-2/3/25R 33.70m FP-22-2/3/25R to FP-22-2/3/26Y 33.70m FP-22-2/3/26Y to FP-22-2/3/27B 33.70m FP-22-2/3/27B to FP-22-2/32/8R 33.70m FP-22-2/3/28R to FP-22-2/3/29Y 33.70m FP-22-2/3/29Y to FP-22-2/3/30B 33.70m FP-22-2/3/30B to FP-22-2/3/31R 32.20m FP-22-2/3/31R to FP-22-2/3/32Y 35.20m FP-22-2/3/32Y to FP-22-2/3/33B 33.70m FP-22-2/3/33B to FP-22-2/3/34R 30.70m FP-22-2/3/34R to FP-22-2/3/35Y 33.70m FP-22-2/3/35Y to FP-22-2/3/36B 33.70m FP-22-2/3/36B to FP-22-2/3/37R 34.45m | 62.338 | 100.65 | 6274.3197
B2.33 71 00 01 01 | Cable, Copper 4x10mm2/ CU/XLPE/SWA/PVC + 1x10mm2 CU/PVC | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0247 | 2026-10-17 | Survey for Excavation for Street Lighting, Cable Trench and Sand Bedding, at Road (Arterial RD) Left Side. Sta. 0+0052.20 to 0+509.60, @Zone-3 Pole Number :- FP-23-2/1 to FP-23-2/1/1R = 13.7m FP-23-2/1/1R to FP-23-2/1/2Y = 34.2m FP-23-2/1/2Y to FP-23-2/1/3B = 34.2m FP-23-2/1/3B to FP-23-2/1/4R = 34.2m FP-23-2/1/4R to FP-23-2/1/5Y = 34.2m FP-23-2/1/5Y to FP-23-2/1/6B = 34.2m FP-23-2/1/6B to FP-23-2/1/7R = 34.2m FP-23-2/1/7R to FP-23-2/1/8Y = 34.2m FP-23-2/1/8Y to FP-23-2/1/9B = 34.2m FP-23-2/1/9B to FP-23-2/1/10R = 34.2m FP-23-2/1/10R to FP-23-2/1/11Y = 34.2m FP-23-2/1/11Y to FP-23-2/1/12B = 34.2m FP-23-2/4 to FP-23-2/4/1R = 38.9m FP-23-2/4/1R to FP-23-2/4/2Y = 34.2m FP-23-2/4/2Y to FP-23-2/4/3B = 34.2m FP-23-2/4/3B to FP-23-2/4/4R = 34.2m | 62.338 | 53.14 | 3312.6413
B2.33 71 00 01 01 | Cable, Copper 4x10mm2/ CU/XLPE/SWA/PVC + 1x10mm2 CU/PVC | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0248 | 2026-10-17 | FIR for Cable (4x10mm2)+(1x10mm2) Installation for Street Lighting Pole, at Road (Arterial RD) Left Side. Sta. 0+0052.20 to 0+509.60, @Zone-3 Pole Number :- FP-23-2/1 to FP-23-2/1/1R = 13.7m FP-23-2/1/1R to FP-23-2/1/2Y = 34.2m FP-23-2/1/2Y to FP-23-2/1/3B = 34.2m FP-23-2/1/3B to FP-23-2/1/4R = 34.2m FP-23-2/1/4R to FP-23-2/1/5Y = 34.2m FP-23-2/1/5Y to FP-23-2/1/6B = 34.2m FP-23-2/1/6B to FP-23-2/1/7R = 34.2m FP-23-2/1/7R to FP-23-2/1/8Y = 34.2m FP-23-2/1/8Y to FP-23-2/1/9B = 34.2m FP-23-2/1/9B to FP-23-2/1/10R = 34.2m FP-23-2/1/10R to FP-23-2/1/11Y = 34.2m FP-23-2/1/11Y to FP-23-2/1/12B = 34.2m FP-23-2/4 to FP-23-2/4/1R = 38.9m FP-23-2/4/1R to FP-23-2/4/2Y = 34.2m FP-23-2/4/2Y to FP-23-2/4/3B = 34.2m FP-23-2/4/3B to FP-23-2/4/4R = 34.2m | 62.338 | 318.84 | 19875.8479
B2.33 71 00 01 01 | Cable, Copper 4x10mm2/ CU/XLPE/SWA/PVC + 1x10mm2 CU/PVC | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0257 | 2026-10-18 | Survey and Compaction FIR for Backfill above the Street Lighting Cable, Layer-1, at Road (Arterial RD) Left Side. Sta. 0+0052.20 to 0+509.60, @Zone-3 Pole Number :- FP-23-2/1 to FP-23-2/1/1R = 13.7m FP-23-2/1/1R to FP-23-2/1/2Y = 34.2m FP-23-2/1/2Y to FP-23-2/1/3B = 34.2m FP-23-2/1/3B to FP-23-2/1/4R = 34.2m FP-23-2/1/4R to FP-23-2/1/5Y = 34.2m FP-23-2/1/5Y to FP-23-2/1/6B = 34.2m FP-23-2/1/6B to FP-23-2/1/7R = 34.2m FP-23-2/1/7R to FP-23-2/1/8Y = 34.2m FP-23-2/1/8Y to FP-23-2/1/9B = 34.2m FP-23-2/1/9B to FP-23-2/1/10R = 34.2m FP-23-2/1/10R to FP-23-2/1/11Y = 34.2m FP-23-2/1/11Y to FP-23-2/1/12B = 34.2m FP-23-2/4 to FP-23-2/4/1R = 38.9m FP-23-2/4/1R to FP-23-2/4/2Y = 34.2m FP-23-2/4/2Y to FP-23-2/4/3B = 34.2m FP-23-2/4/3B to FP-23-2/4/4R = 34.2m | 62.338 | 106.28 | 6625.2826
B2.33 71 00 01 01 | Cable, Copper 4x10mm2/ CU/XLPE/SWA/PVC + 1x10mm2 CU/PVC | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0266 | 2026-10-19 | Survey for Excavation for Street Lighting, Cable Trench and Sand Bedding, at Road (RD-03) Right Side. Sta. 0+056.00 to 0+296.00, @Zone-4 Pole Number :- FP-21-1/6/8Y to FP-21-1/6/9B = 32.7m FP-21-1/6/9B to FP-21-1/6/10R = 33.7m FP-21-1/6/10R to FP-21-1/6/11Y = 33.7m FP-21-1/6/11Y to FP-21-1/6/12B = 34.7m FP-21-1/6/12B to FP-21-1/6/13R = 32.7m FP-21-1/6/13R to FP-21-1/6/14Y = 33.7m FP-21-1/6/14Y to FP-21-1/6/15B = 34.7m FP-21-1/6/15B to FP-21-1/6/16R = 33.7m | 62.338 | 26.96 | 1680.6325
B2.33 71 00 01 01 | Cable, Copper 4x10mm2/ CU/XLPE/SWA/PVC + 1x10mm2 CU/PVC | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0267 | 2026-10-19 | FIR for Cable (4x10mm2)+(1x10mm2) Installation for Street Lighting Pole, at Road (RD-03) Right Side, Sta. 0+056.00 to 0+296.00, @Zone-4 Pole Number :- FP-21-1/6/8Y to FP-21-1/6/9B = 32.7m FP-21-1/6/9B to FP-21-1/6/10R = 33.7m FP-21-1/6/10R to FP-21-1/6/11Y = 33.7m FP-21-1/6/11Y to FP-21-1/6/12B = 34.7m FP-21-1/6/12B to FP-21-1/6/13R = 32.7m FP-21-1/6/13R to FP-21-1/6/14Y = 33.7m FP-21-1/6/14Y to FP-21-1/6/15B = 34.7m FP-21-1/6/15B to FP-21-1/6/16R = 33.7m | 62.338 | 161.76 | 10083.7949
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0007 | 2026-08-29 | FIR for Survey of Excavation , Compation and Gravel Bedding Placement for Lighting Pole Foundation at Road (RD - 01). Pole Number :- 1) FP-22-2/4/2Y 8) FP-22-2/4/10R 2) FP-22-2/4/3B 9) FP-22-2/4/11Y 3) FP-22-2/4/4R 10) FP-22-2/4/12B 4) FP-22-2/4/5Y 11) FP-22-2/4/13R 5) FP-22-2/4/6B 6) FP-22-2/4/7R 7) FP-22-2/4/8Y | 8923.992 | 0.55 | 4908.1956
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0008 | 2026-08-29 | FIR for Survey of Excavation , Compation and Gravel Bedding Placement for Lighting Pole Foundation at Road (RD - 01). Pole Number :- 1) FP-22-2/4/14Y 8) FP-22-2/4/21B 2) FP-22-2/4/15B 9) FP-22-2/4/22R 3) FP-22-2/4/16R 10) FP-22-2/4/23Y 4) FP-22-2/4/17Y 11) FP-22-2/4/24B 5) FP-22-2/4/18B 12) FP-22-2/4/25R 6) FP-22-2/4/19R 13) FP-22-2/4/26Y 7) FP-22-2/4/20Y 14) FP-22-2/4/27B | 8923.992 | 0.7 | 6246.7944
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0011 | 2026-08-30 | FIR for Survey of Concrete Foundation Installation for Lighting Pole at Road (RD - 01). @Zone-1 Pole Number :- 1) FP-22-2/4/2Y 8) FP-22-2/4/10R 2) FP-22-2/4/3B 9) FP-22-2/4/11Y 3) FP-22-2/4/4R 10) FP-22-2/4/12B 4) FP-22-2/4/5Y 11) FP-22-2/4/13R 5) FP-22-2/4/6B 6) FP-22-2/4/7R 7) FP-22-2/4/8Y | 8923.992 | 1.65 | 14724.5868
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0012 | 2026-08-30 | FIR for Survey of Concrete Foundation Installation for Lighting Pole at Road (RD - 01). @Zone-1 Pole Number :- 1) FP-22-2/4/14Y 8) FP-22-2/4/21B 2) FP-22-2/4/15B 9) FP-22-2/4/22R 3) FP-22-2/4/16R 10) FP-22-2/4/23Y 4) FP-22-2/4/17Y 11) FP-22-2/4/24B 5) FP-22-2/4/18B 12) FP-22-2/4/25R 6) FP-22-2/4/19R 13) FP-22-2/4/26Y 7) FP-22-2/4/20Y 14) FP-22-2/4/27B | 8923.992 | 2.1 | 18740.3832
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0027 | 2026-09-03 | Survey for Excavation and Gravel Bedding Placement for Lighting Pole Foundation at Road (RD-01). Zone-1 Pole Number: - 1) FP-22-2/3/13R 8) FP-22-2/3/21B 2) FP-22-2/3/15B 9) FP-22-2/3/22R 3) FP-22-2/3/16R 10) FP-22-2/3/23Y 4) FP-22-2/3/17Y 11) FP-22-2/3/24B 5) FP-22-2/3/18B 12) FP-22-2/3/25R 6) FP-22-2/3/19R 13) FP-22-2/3/26Y 7) FP-22-2/3/20Y 14) FP-22-2/3/27B | 8923.992 | 0.7 | 6246.7944
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0028 | 2026-09-03 | Survey for Excavation and Gravel Bedding Placement for Lighting Pole Foundation at Road (RD-01). Zone-1 Pole Number: - 1) FP-22-2/3/28R 8) FP-22-2/3/35Y 2) FP-22-2/3/29Y 9) FP-22-2/3/36B 3) FP-22-2/3/30B 10) FP-22-2/3/37R 4) FP-22-2/3/31R 11) FP-22-2/4/9B 5) FP-22-2/3/32Y 12) FP-22-2/4/28R 6) FP-22-2/3/33B 13) FP-22-2/4/29Y 7) FP-22-2/3/34R 14) FP-22-2/4/30B | 8923.992 | 0.7 | 6246.7944
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0030 | 2026-09-07 | FIR for Survey of Concrete Foundation Installation for Lighting Pole at Road (RD-01) Left Side. Zone-1 Pole Number: - 1) FP-22-2/3/13R 8) FP-22-2/3/21B 2) FP-22-2/3/15B 9) FP-22-2/3/22R 3) FP-22-2/3/16R 10) FP-22-2/3/23Y 4) FP-22-2/3/17Y 11) FP-22-2/3/24B 5) FP-22-2/3/18B 12) FP-22-2/3/25R 6) FP-22-2/3/19R 13) FP-22-2/3/26Y 7) FP-22-2/3/20Y 14) FP-22-2/3/27B | 8923.992 | 2.1 | 18740.3832
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0031 | 2026-09-07 | FIR for Survey of Concrete Foundation Installation for Lighting Pole at Road (RD-01) Right & Left Side. Zone-1 Pole Number: - 1) FP-22-2/3/28R 8) FP-22-2/3/35Y 2) FP-22-2/3/29Y 9) FP-22-2/3/36B 3) FP-22-2/3/30B 10) FP-22-2/3/37R 4) FP-22-2/3/31R 11) FP-22-2/4/9B 5) FP-22-2/3/32Y 12) FP-22-2/4/28R 6) FP-22-2/3/33B 13) FP-22-2/4/29Y 7) FP-22-2/3/34R 14) FP-22-2/4/30B | 8923.992 | 2.1 | 18740.3832
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0032 | 2026-09-07 | FIR for Assembly & Survey for the Installation of Lighting Pole with arm, including the power Distribution box, at Road (RD - 01) Right Side. @Zone -1 Pole Number :- 1) FP-22-2/4/2Y 8) FP-22-2/4/10R 2) FP-22-2/4/3B 9) FP-22-2/4/11Y 3) FP-22-2/4/4R 10) FP-22-2/4/12B 4) FP-22-2/4/5Y 11) FP-22-2/4/13R 5) FP-22-2/4/6B 6) FP-22-2/4/7R 7) FP-22-2/4/8Y | 8923.992 | 7.15 | 63806.5428
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0033 | 2026-09-07 | FIR for Assembly & Survey for the Installation of Lighting Pole with arm, including the power Distribution box, at Road (RD - 01) Right Side. @Zone-1 Pole Number :- 1) FP-22-2/4/14Y 8) FP-22-2/4/21B 2) FP-22-2/4/15B 9) FP-22-2/4/22R 3) FP-22-2/4/16R 10) FP-22-2/4/23Y 4) FP-22-2/4/17Y 11) FP-22-2/4/24B 5) FP-22-2/4/18B 12) FP-22-2/4/25R 6) FP-22-2/4/19R 13) FP-22-2/4/26Y 7) FP-22-2/4/20Y 14) FP-22-2/4/27B | 8923.992 | 9.1 | 81208.3272
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0043 | 2026-09-08 | FIR for Assembly & Survey for the Installation of Lighting Pole with arm, including the power Distribution box, at Road (RD-01) Left Side. Zone-1 Pole Number: - 1) FP-22-2/3/13R 8) FP-22-2/3/21B 2) FP-22-2/3/15B 9) FP-22-2/3/22R 3) FP-22-2/3/16R 10) FP-22-2/3/23Y 4) FP-22-2/3/17Y 11) FP-22-2/3/24B 5) FP-22-2/3/18B 12) FP-22-2/3/25R 6) FP-22-2/3/19R 13) FP-22-2/3/26Y 7) FP-22-2/3/20Y 14) FP-22-2/3/27B | 8923.992 | 9.1 | 81208.3272
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0044 | 2026-09-08 | FIR for Assembly & Survey for the Installation of Lighting Pole with arm, including the power Distribution box, at Road (RD-01) Right & Left Side. Zone-1 Pole Number: - 1) FP-22-2/3/28R 8) FP-22-2/3/35Y 2) FP-22-2/3/29Y 9) FP-22-2/3/36B 3) FP-22-2/3/30B 10) FP-22-2/3/37R 4) FP-22-2/3/31R 11) FP-22-2/4/9B 5) FP-22-2/3/32Y 12) FP-22-2/4/28R 6) FP-22-2/3/33B 13) FP-22-2/4/29Y 7) FP-22-2/3/34R 14) FP-22-2/4/30B | 8923.992 | 9.1 | 81208.3272
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0050 | 2026-09-12 | Survey and Compaction FIR for Backfill around the Electrical Pole concrete Foundation, Layer-Final at Road (RD - 01)Right Side.@Zone-1 Pole Number :- 1) FP-22-2/4/2Y 8) FP-22-2/4/10R 2) FP-22-2/4/3B 9) FP-22-2/4/11Y 3) FP-22-2/4/4R 10) FP-22-2/4/12B 4) FP-22-2/4/5Y 11) FP-22-2/4/13R 5) FP-22-2/4/6B 6) FP-22-2/4/7R 7) FP-22-2/4/8Y | 8923.992 | 0.55 | 4908.1956
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0051 | 2026-09-12 | Survey and Compaction FIR for Backfill around the Electrical Pole concrete Foundation, Layer-Final at Road (RD - 01)Right Side. @Zone-1 Pole Number :- 1) FP-22-2/4/14Y 8) FP-22-2/4/21B 2) FP-22-2/4/15B 9) FP-22-2/4/22R 3) FP-22-2/4/16R 10) FP-22-2/4/23Y 4) FP-22-2/4/17Y 11) FP-22-2/4/24B 5) FP-22-2/4/18B 12) FP-22-2/4/25R 6) FP-22-2/4/19R 13) FP-22-2/4/26Y 7) FP-22-2/4/20Y 14) FP-22-2/4/27B | 8923.992 | 0.7 | 6246.7944
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0052 | 2026-09-12 | Survey and Compaction FIR for Backfill around the Electrical Pole concrete Foundation, Layer-Final at Road (RD-01) Left Side. Zone-1 Pole Number: - 1) FP-22-2/3/13R 8) FP-22-2/3/21B 2) FP-22-2/3/15B 9) FP-22-2/3/22R 3) FP-22-2/3/16R 10) FP-22-2/3/23Y 4) FP-22-2/3/17Y 11) FP-22-2/3/24B 5) FP-22-2/3/18B 12) FP-22-2/3/25R 6) FP-22-2/3/19R 13) FP-22-2/3/26Y 7) FP-22-2/3/20Y 14) FP-22-2/3/27B | 8923.992 | 0.7 | 6246.7944
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0053 | 2026-09-12 | Survey and Compaction FIR for Backfill around the Electrical Pole concrete Foundation, Layer-Final at Road (RD-01) Right & Left Side. Zone-1 Pole Number: - 1) FP-22-2/3/28R 8) FP-22-2/3/35Y 2) FP-22-2/3/29Y 9) FP-22-2/3/36B 3) FP-22-2/3/30B 10) FP-22-2/3/37R 4) FP-22-2/3/31R 11) FP-22-2/4/9B 5) FP-22-2/3/32Y 12) FP-22-2/4/28R 6) FP-22-2/3/33B 13) FP-22-2/4/29Y 7) FP-22-2/3/34R 14) FP-22-2/4/30B | 8923.992 | 0.7 | 6246.7944
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0056 | 2026-09-13 | Survey for Excavation and Gravel Bedding Placement for Lighting Pole Foundation at Road (RD-01)Left Side. Zone-1 Pole Number: - 1) FP-22-2/3/14Y | 8923.992 | 0.05 | 446.1996
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0062 | 2026-09-16 | Survey for Excavation and Gravel Bedding Placement for Lighting Pole Foundation at Road (RD-03). Zone-1 Pole Number: - 1) FP-21-1/5/1R 10) FP-21-1/6/8Y 2) FP-21-1/5/2Y 11) FP-21-1/6/9B 3) FP-21-1/5/3B 12) FP-21-1/6/10R 4) FP-21-1/5/4R 13) FP-21-1/6/11Y 5) FP-21-1/5/5Y 14) FP-21-1/6/12B 6) FP-21-1/5/6B 15) FP-21-1/6/13R 7) FP-21-1/5/7R 16) FP-21-1/6/14Y 8) FP-21-1/5/8Y 17) FP-21-1/6/15B 9) FP-21-1/5/9B 18) FP-21-1/6/16R | 8923.992 | 0.9 | 8031.5928
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0068 | 2026-09-17 | FIR for Survey of Concrete Foundation Installation for Lighting Pole at Road (RD-03). Zone-1 Pole Number: - 1) FP-21-1/5/1R 10) FP-21-1/6/8Y 2) FP-21-1/5/2Y 11) FP-21-1/6/9B 3) FP-21-1/5/3B 12) FP-21-1/6/10R 4) FP-21-1/5/4R 13) FP-21-1/6/11Y 5) FP-21-1/5/5Y 14) FP-21-1/6/12B 6) FP-21-1/5/6B 15) FP-21-1/6/13R 7) FP-21-1/5/7R 16) FP-21-1/6/14Y 8) FP-21-1/5/8Y 17) FP-21-1/6/15B 9) FP-21-1/5/9B 18) FP-21-1/6/16R | 8923.992 | 2.7 | 24094.7784
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0093 | 2026-09-24 | FIR for Assembly and Installation of Street Lighting Pole 10 meter height with 1 arm, including the power Distribution box, at Road (RD-03). Zone-4 Pole Number: - 1) FP-21-1/5/1R 10) FP-21-1/6/8Y 2) FP-21-1/5/2Y 11) FP-21-1/6/9B 3) FP-21-1/5/3B 12) FP-21-1/6/10R 4) FP-21-1/5/4R 13) FP-21-1/6/11Y 5) FP-21-1/5/5Y 14) FP-21-1/6/12B 6) FP-21-1/5/6B 15) FP-21-1/6/13R 7) FP-21-1/5/7R 16) FP-21-1/6/14Y 8) FP-21-1/5/8Y 17) FP-21-1/6/15B 9) FP-21-1/5/9B 18) FP-21-1/6/16R | 8923.992 | 11.7 | 104410.7064
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0099 | 2026-09-26 | Survey for Excavation and Gravel Bedding Placement for Lighting Pole Foundation at Road (RD-03). Zone-4 Pole Number: - 1) FP-21-1/4/1R 2) FP-21-1/6/7R | 8923.992 | 0.1 | 892.3992
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0101 | 2026-09-26 | Survey for Excavation and Gravel Bedding Placement for Lighting Pole Foundation at Road (RD-02),Left Side. Zone-4 Pole Number: - 1) FP-22-1/3/14Y 10) FP-21-1/6/6B 2) FP-22-1/3/15B 11) FP-21-1/6/5Y 3) FP-21-1/4/8Y 12) FP-21-1/6/4R 4) FP-21-1/4/7R 13) FP-21-1/6/3B 5) FP-21-1/4/6B 14) FP-21-1/6/2Y 6) FP-21-1/4/5Y 15) FP-21-1/6/1R 7) FP-21-1/4/4R 16) FP-21-1/1/1R 8) FP-21-1/4/3B 9) FP-21-1/4/2Y | 8923.992 | 0.8 | 7139.1936
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0114 | 2026-09-27 | FIR for Survey of Concrete Foundation Installation for Lighting Pole, at Road (RD-03). Zone-4 Pole Number: - 1) FP-21-1/4/1R 2) FP-21-1/6/7R | 8923.992 | 1.3 | 11601.1896
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0115 | 2026-09-27 | FIR for Survey of Concrete Foundation Installation for Lighting Pole, at Road (RD-02),Left Side. Zone-4 Pole Number: - 1) FP-22-1/3/14Y 10) FP-21-1/6/6B 2) FP-22-1/3/15B 11) FP-21-1/6/5Y 3) FP-21-1/4/8Y 12) FP-21-1/6/4R 4) FP-21-1/4/7R 13) FP-21-1/6/3B 5) FP-21-1/4/6B 14) FP-21-1/6/2Y 6) FP-21-1/4/5Y 15) FP-21-1/6/1R 7) FP-21-1/4/4R 16) FP-21-1/1/1R 8) FP-21-1/4/3B 9) FP-21-1/4/2Y | 8923.992 | 10.4 | 92809.5168
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0120 | 2026-09-27 | Survey and Compaction FIR for Backfill around the Electrical Pole concrete Foundation, Layer-Final at Road (RD-03). Zone-4 Pole Number: - 1) FP-21-1/5/1R 10) FP-21-1/6/8Y 2) FP-21-1/5/2Y 11) FP-21-1/6/9B 3) FP-21-1/5/3B 12) FP-21-1/6/10R 4) FP-21-1/5/4R 13) FP-21-1/6/11Y 5) FP-21-1/5/5Y 14) FP-21-1/6/12B 6) FP-21-1/5/6B 15) FP-21-1/6/13R 7) FP-21-1/5/7R 16) FP-21-1/6/14Y 8) FP-21-1/5/8Y 17) FP-21-1/6/15B 9) FP-21-1/5/9B 18) FP-21-1/6/16R | 8923.992 | 0.9 | 8031.5928
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0131 | 2026-09-28 | FIR for Assembly and Installation of Street Lighting Pole 10 meter height with 1 arm, including the power Distribution box, at Road (RD-03). Zone-4 Pole Number: - 1) FP-21-1/4/1R 2) FP-21-1/6/7R | 8923.992 | 1.3 | 11601.1896
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0132 | 2026-09-28 | FIR for Assembly and Installation of Street Lighting Pole 10 meter height with 1 arm, including the power Distribution box, at Road (RD-02),Left Side. Zone-4 Pole Number: - 1) FP-22-1/3/14Y 10) FP-21-1/6/6B 2) FP-22-1/3/15B 11) FP-21-1/6/5Y 3) FP-21-1/4/8Y 12) FP-21-1/6/4R 4) FP-21-1/4/7R 13) FP-21-1/6/3B 5) FP-21-1/4/6B 14) FP-21-1/6/2Y 6) FP-21-1/4/5Y 15) FP-21-1/6/1R 7) FP-21-1/4/4R 16) FP-21-1/1/1R 8) FP-21-1/4/3B 9) FP-21-1/4/2Y | 8923.992 | 10.4 | 92809.5168
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0133 | 2026-09-29 | Survey and Compaction FIR for Backfill around the Electrical Pole concrete Foundation, Layer-final, at Road (RD-03). Zone-4 Pole Number: - 1) FP-21-1/4/1R 2) FP-21-1/6/7R | 8923.992 | 0.1 | 892.3992
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0134 | 2026-09-29 | Survey and Compaction FIR for Backfill around the Electrical Pole concrete Foundation, Layer-Final, at Road (RD-02),Left Side. Zone-4 Pole Number: - 1) FP-22-1/3/14Y 10) FP-21-1/6/6B 2) FP-22-1/3/15B 11) FP-21-1/6/5Y 3) FP-21-1/4/8Y 12) FP-21-1/6/4R 4) FP-21-1/4/7R 13) FP-21-1/6/3B 5) FP-21-1/4/6B 14) FP-21-1/6/2Y 6) FP-21-1/4/5Y 15) FP-21-1/6/1R 7) FP-21-1/4/4R 16) FP-21-1/1/1R 8) FP-21-1/4/3B 9) FP-21-1/4/2Y | 8923.992 | 0.8 | 7139.1936
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0135 | 2026-09-29 | FIR for Survey of Concrete Foundation Installation for Lighting Pole, at Road (RD-01), Left Side.@ Zone-1 Pole Number: - 1) FP-22-2/3/14Y | 8923.992 | 0.15 | 1338.5988
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0143 | 2026-09-30 | FIR for Assembly and Installation of Street Lighting Pole 10 meter height with 1 arm, including the power Distribution box, at Road (RD-01), Left Side.@ Zone-1 Pole Number: - 1) FP-22-2/3/14Y | 8923.992 | 0.65 | 5800.5948
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0147 | 2026-10-01 | Survey and Compaction FIR for Backfill around the Electrical Pole concrete Foundation, Layer-Final, at Road (RD-01), Left Side.@ Zone-1 Pole Number: - 1) FP-22-2/3/14Y | 8923.992 | 0.05 | 446.1996
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0148 | 2026-10-01 | Survey for Excavation and Gravel Bedding Placement for Lighting Pole Foundation at Road (RD-02),Right Side. Zone-4 Pole Number: - 1) FP-21-1/2/1R 14) FP-21-1/3/13R 2) FP-21-1/3/1R 15) FP-21-1/3/14Y 3) FP-21-1/3/2Y 16) FP-21-1/3/15B 4) FP-21-1/3/3B 17) FP-21-1/3/16R 5) FP-21-1/3/4R 18) FP-21-1/3/17Y 6) FP-21-1/3/5Y 19) FP-21-1/3/18B 7) FP-21-1/3/6B 20) FP-21-1/3/19R 8) FP-21-1/3/7R 21) FP-21-1/3/20Y 9) FP-21-1/3/8Y 22) FP-21-1/3/21B 10) FP-21-1/3/9B 23) FP-21-1/3/22R 11) FP-21-1/3/10R 24) FP-21-1/3/23Y 12) FP-21-1/3/11Y 25) FP-21-1/3/24B 13) FP-21-1/3/12B | 8923.992 | 1.25 | 11154.99
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0150 | 2026-10-03 | Survey for Excavation and Gravel Bedding Placement for Lighting Pole Foundation at Road (RD-02),Right Side. Zone-4 Pole Number: - 1) FP-21-1/2/1R 14) FP-21-1/3/13R 2) FP-21-1/3/1R 15) FP-21-1/3/14Y 3) FP-21-1/3/2Y 16) FP-21-1/3/15B 4) FP-21-1/3/3B 17) FP-21-1/3/16R 5) FP-21-1/3/4R 18) FP-21-1/3/17Y 6) FP-21-1/3/5Y 19) FP-21-1/3/18B 7) FP-21-1/3/6B 20) FP-21-1/3/19R 8) FP-21-1/3/7R 21) FP-21-1/3/20Y 9) FP-21-1/3/8Y 22) FP-21-1/3/21B 10) FP-21-1/3/9B 23) FP-21-1/3/22R 11) FP-21-1/3/10R 24) FP-21-1/3/23Y 12) FP-21-1/3/11Y 25) FP-21-1/3/24B 13) FP-21-1/3/12B | 8923.992 | 1.25 | 11154.99
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0153 | 2026-10-04 | FIR for Assembly and Installation of Street Lighting Pole 10 meter height with 1 arm, including the power Distribution box, at Road (RD-02),Right Side. Zone-4 Pole Number: - 1) FP-21-1/3/2Y 11) FP-21-1/3/13R 2) FP-21-1/3/3B 12) FP-21-1/3/14Y 3) FP-21-1/3/4R 13) FP-21-1/3/15B 4) FP-21-1/3/6B 5) FP-21-1/3/7R 6) FP-21-1/3/8Y 7) FP-21-1/3/9B 8) FP-21-1/3/10R 9) FP-21-1/3/11Y 10) FP-21-1/3/12B | 8923.992 | 8.45 | 75407.7324
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0156 | 2026-10-05 | Survey for Excavation and Gravel Bedding Placement for Lighting Pole Foundation at Road (RD-04),@. Zone-4 Pole Number: - 1) FP-21-1/4/9B 11) FP-22-1/2/9B 2) FP-21-1/4/10R 12) FP-22-1/2/10R 3) FP-21-1/4/11Y 13) FP-22-1/2/11Y 4) FP-21-1/4/12B 14) FP-22-1/2/12B 5) FP-21-1/4/13R 15) FP-22-1/2/13R 6) FP-21-1/4/14Y 16) FP-22-1/2/14Y 7) FP-21-1/4/15B 17) FP-22-1/2/15B 8) FP-21-1/4/16R 18) FP-22-1/2/16R 9) FP-21-1/4/17Y 19) FP-22-1/2/17Y 10) FP-21-1/4/18B 20) FP-22-1/2/18B | 8923.992 | 1 | 8923.992
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0158 | 2026-10-06 | FIR for Survey of Concrete Foundation Installation for Lighting Pole, at Road (RD-02),Right Side. Zone-4 Pole Number: - 1) FP-21-1/3/5Y 2) FP-21-1/3/16R 3) FP-21-1/3/17Y 4) FP-21-1/3/18B 5) FP-21-1/3/19R 6) FP-21-1/3/20Y | 8923.992 | 0.9 | 8031.5928
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0164 | 2026-10-06 | FIR for Survey of Concrete Foundation Installation for Lighting Pole, at Road (RD-04),@. Zone-4 Pole Number: - 1) FP-21-1/4/9B 11) FP-22-1/2/9B 2) FP-21-1/4/10R 12) FP-22-1/2/10R 3) FP-21-1/4/11Y 13) FP-22-1/2/11Y 4) FP-21-1/4/12B 14) FP-22-1/2/12B 5) FP-21-1/4/13R 15) FP-22-1/2/13R 6) FP-21-1/4/14Y 16) FP-22-1/2/14Y 7) FP-21-1/4/15B 17) FP-22-1/2/15B 8) FP-21-1/4/16R 18) FP-22-1/2/16R 9) FP-21-1/4/17Y 19) FP-22-1/2/17Y 10) FP-21-1/4/18B 20) FP-22-1/2/18B | 8923.992 | 3 | 26771.976
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0176 | 2026-10-08 | FIR for Assembly and Installation of Street Lighting Pole 10 meter height with 1 arm, including the power Distribution box, at Road (RD-02),Right Side. Zone-4 Pole Number: - 1) FP-21-1/3/5Y 2) FP-21-1/3/16R 3) FP-21-1/3/17Y 4) FP-21-1/3/18B 5) FP-21-1/3/19R 6) FP-21-1/3/20Y | 8923.992 | 3.9 | 34803.5688
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0172 | 2026-10-08 | FIR for Assembly and Installation of Street Lighting Pole 10 meter height with 1 arm, including the power Distribution box, at Road (RD-04),@. Zone-4 Pole Number: - 1) FP-21-1/4/9B 11) FP-22-1/2/9B 2) FP-21-1/4/10R 12) FP-22-1/2/10R 3) FP-21-1/4/11Y 13) FP-22-1/2/11Y 4) FP-21-1/4/12B 14) FP-22-1/2/12B 5) FP-21-1/4/13R 15) FP-22-1/2/13R 6) FP-21-1/4/14Y 16) FP-22-1/2/14Y 7) FP-21-1/4/15B 17) FP-22-1/2/15B 8) FP-21-1/4/16R 18) FP-22-1/2/16R 9) FP-21-1/4/17Y 19) FP-22-1/2/17Y 10) FP-21-1/4/18B 20) FP-22-1/2/18B | 8923.992 | 13 | 116011.896
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0173 | 2026-10-08 | Survey for Excavation and Gravel Bedding Placement for Lighting Pole Foundation at Road (RD-02),Right & Left Side. @ Zone-4 Pole Number: - 1) FP-21-1/2/2Y 12) FP-21-1/1/2Y 2) FP-21-1/2/3B 13) FP-21-1/1/3B 3) FP-21-1/2/4R 14) FP-21-1/1/4R 4) FP-21-1/2/5Y 15) FP-21-1/1/5Y 5) FP-21-1/2/6B 16) FP-21-1/1/6B 6) FP-21-1/2/7R 17) FP-21-1/1/7R 7) FP-21-1/2/8Y 18) FP-21-1/1/8Y 8) FP-21-1/2/9B 9) FP-21-1/2/10R 10) FP-21-1/2/11Y 11) FP-21-1/2/12B | 8923.992 | 0.9 | 8031.5928
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0175 | 2026-10-10 | FIR for Survey of Concrete Foundation Installation for Lighting Pole, at Road (RD-02),Right Side. @Zone-4 Pole Number: - 1) FP-21-1/2/1R 2) FP-21-1/3/1R 3) FP-21-1/3/21B 4) FP-21-1/3/22R 5) FP-21-1/3/23Y 6) FP-21-1/3/24B | 8923.992 | 0.9 | 8031.5928
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0182 | 2026-10-10 | Survey and Compaction FIR for Backfill around the Electrical Pole concrete Foundation, Layer-5, at Road (RD-02),Right Side. Zone-4 Pole Number: - 1) FP-21-1/3/2Y 11) FP-21-1/3/13R 2) FP-21-1/3/3B 12) FP-21-1/3/14Y 3) FP-21-1/3/4R 13) FP-21-1/3/15B 4) FP-21-1/3/6B 5) FP-21-1/3/7R 6) FP-21-1/3/8Y 7) FP-21-1/3/9B 8) FP-21-1/3/10R 9) FP-21-1/3/11Y 10) FP-21-1/3/12B | 8923.992 | 0.65 | 5800.5948
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0190 | 2026-10-11 | FIR for Survey of Concrete Foundation Installation for Lighting Pole, at Road (RD-02),Right & Left Side. @ Zone-4 Pole Number: - 1) FP-21-1/2/2Y 12) FP-21-1/1/2Y 2) FP-21-1/2/3B 13) FP-21-1/1/3B 3) FP-21-1/2/4R 14) FP-21-1/1/4R 4) FP-21-1/2/5Y 15) FP-21-1/1/5Y 5) FP-21-1/2/6B 16) FP-21-1/1/6B 6) FP-21-1/2/7R 17) FP-21-1/1/7R 7) FP-21-1/2/8Y 18) FP-21-1/1/8Y 8) FP-21-1/2/9B 9) FP-21-1/2/10R 10) FP-21-1/2/11Y 11) FP-21-1/2/12B | 8923.992 | 2.7 | 24094.7784
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0193 | 2026-10-11 | FIR for Assembly and Installation of Street Lighting Pole 10 meter height with 1 arm, including the power Distribution box, at Road (RD-02),Right Side. @Zone-4 Pole Number: - 1) FP-21-1/2/1R 2) FP-21-1/3/1R 3) FP-21-1/3/21B 4) FP-21-1/3/22R 5) FP-21-1/3/23Y 6) FP-21-1/3/24B | 8923.992 | 3.9 | 34803.5688
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0194 | 2026-10-11 | Survey and Compaction FIR for Backfill around the Electrical Pole concrete Foundation, Layer-5, at Road (RD-02),Right Side. Zone-4 Pole Number: - 1) FP-21-1/3/5Y 2) FP-21-1/3/16R 3) FP-21-1/3/17Y 4) FP-21-1/3/18B 5) FP-21-1/3/19R 6) FP-21-1/3/20Y | 8923.992 | 0.3 | 2677.1976
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0195 | 2026-10-11 | Survey and Compaction FIR for Backfill around the Electrical Pole concrete Foundation, Layer-5, at Road (RD-04),@. Zone-4 Pole Number: - 1) FP-21-1/4/9B 11) FP-22-1/2/9B 2) FP-21-1/4/10R 12) FP-22-1/2/10R 3) FP-21-1/4/11Y 13) FP-22-1/2/11Y 4) FP-21-1/4/12B 14) FP-22-1/2/12B 5) FP-21-1/4/13R 15) FP-22-1/2/13R 6) FP-21-1/4/14Y 16) FP-22-1/2/14Y 7) FP-21-1/4/15B 17) FP-22-1/2/15B 8) FP-21-1/4/16R 18) FP-22-1/2/16R 9) FP-21-1/4/17Y 19) FP-22-1/2/17Y 10) FP-21-1/4/18B 20) FP-22-1/2/18B | 8923.992 | 1 | 8923.992
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0196 | 2026-10-11 | Survey for Excavation and Gravel Bedding Placement for Lighting Pole Foundation at Road (RD-02),Left Side. @ Zone-4 Pole Number: - 1) FP-22-1/2/1R 12) FP-22-1/3/4R 2) FP-22-1/2/2Y 13) FP-22-1/3/5Y 3) FP-22-1/2/3B 14) FP-22-1/3/6B 4) FP-22-1/2/4R 15) FP-22-1/3/7R 5) FP-22-1/2/5Y 16) FP-22-1/3/8Y 6) FP-22-1/2/6B 17) FP-22-1/3/9B 7) FP-22-1/2/7R 18) FP-22-1/3/10R 8) FP-22-1/2/8Y 19) FP-22-1/3/11Y 9) FP-22-1/3/1R 20) FP-22-1/3/12B 10) FP-22-1/3/2Y 21) FP-22-1/3/13R 11) FP-22-1/3/3B | 8923.992 | 1.05 | 9370.1916
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0197 | 2026-10-11 | Survey for Excavation and Gravel Bedding Placement for Lighting Pole Foundation, Road (RD-02),Right Side. @ Zone-4 Pole Number: - 1) FP-22-1/1/1R 13) FP-22-1/4/1R 2) FP-22-1/1/2Y 14) FP-23-1/1/21B 3) FP-22-1/1/3B 15) FP-23-1/1/22R 4) FP-22-1/1/4R 16) FP-23-1/1/23Y 5) FP-22-1/1/5Y 17) FP-23-1/1/24B 6) FP-22-1/1/6B 18) FP-23-1/1/25R 7) FP-22-1/1/7R 8) FP-22-1/1/8Y 9) FP-22-1/1/9B 10) FP-22-1/1/10R 11) FP-22-1/1/11Y 12) FP-22-1/1/12B | 8923.992 | 0.9 | 8031.5928
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0203 | 2026-10-12 | FIR for Assembly and Installation of Street Lighting Pole 10 meter height with 1 arm, including the power Distribution box, at Road (RD-02),Right & Left Side. @ Zone-4 Pole Number: - 1) FP-21-1/2/2Y 12) FP-21-1/1/2Y 2) FP-21-1/2/3B 13) FP-21-1/1/3B 3) FP-21-1/2/4R 14) FP-21-1/1/4R 4) FP-21-1/2/5Y 15) FP-21-1/1/5Y 5) FP-21-1/2/6B 16) FP-21-1/1/6B 6) FP-21-1/2/7R 17) FP-21-1/1/7R 7) FP-21-1/2/8Y 18) FP-21-1/1/8Y 8) FP-21-1/2/9B 9) FP-21-1/2/10R 10) FP-21-1/2/11Y 11) FP-21-1/2/12B | 8923.992 | 11.7 | 104410.7064
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0204 | 2026-10-12 | Survey and Compaction FIR for Backfill around the Electrical Pole concrete Foundation, Layer-5 at Road (RD-02),Right Side. @Zone-4 Pole Number: - 1) FP-21-1/2/1R 2) FP-21-1/3/1R 3) FP-21-1/3/21B 4) FP-21-1/3/22R 5) FP-21-1/3/23Y 6) FP-21-1/3/24B | 8923.992 | 0.3 | 2677.1976
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0207 | 2026-10-13 | Survey and Compaction FIR for Backfill around the Electrical Pole concrete Foundation, Layer-5 at Road (RD-02),Right & Left Side. @ Zone-4 Pole Number: - 1) FP-21-1/2/2Y 12) FP-21-1/1/2Y 2) FP-21-1/2/3B 13) FP-21-1/1/3B 3) FP-21-1/2/4R 14) FP-21-1/1/4R 4) FP-21-1/2/5Y 15) FP-21-1/1/5Y 5) FP-21-1/2/6B 16) FP-21-1/1/6B 6) FP-21-1/2/7R 17) FP-21-1/1/7R 7) FP-21-1/2/8Y 18) FP-21-1/1/8Y 8) FP-21-1/2/9B 9) FP-21-1/2/10R 10) FP-21-1/2/11Y 11) FP-21-1/2/12B | 8923.992 | 0.9 | 8031.5928
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0212 | 2026-10-14 | FIR for Survey of Concrete Foundation Installation for Lighting Pole, at Road (RD-02), Left Side. @ Zone-4 Pole Number: - 1) FP-22-1/3/1R 11) FP-22-1/3/11Y 2) FP-22-1/3/2Y 12) FP-22-1/3/12B 3) FP-22-1/3/3B 13) FP-22-1/3/13R 4) FP-22-1/3/4R 5) FP-22-1/3/5Y 6) FP-22-1/3/6B 7) FP-22-1/3/7R 8) FP-22-1/3/8Y 9) FP-22-1/3/9B 10) FP-22-1/3/10R | 8923.992 | 1.95 | 17401.7844
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0215 | 2026-10-14 | Survey for Excavation and Gravel Bedding Placement for Lighting Pole Foundation at Road (RD-02),Right Side. @ Zone-4 Pole Number: - 1) FP-23-1/2/3B 9) FP-23-1/2/11Y 2) FP-23-1/2/4R 10) FP-23-1/2/12B 3) FP-23-1/2/5Y 11) FP-23-1/2/13R 4) FP-23-1/2/6B 12) FP-23-1/2/14Y 5) FP-23-1/2/7R 13) FP-23-1/2/15B 6) FP-23-1/2/8Y 14) FP-23-1/2/16R 7) FP-23-1/2/9B 15) FP-23-1/2/17Y 8) FP-23-1/2/10R 16) FP-23-1/2/18B 17) FP-23-1/3/25R | 8923.992 | 0.85 | 7585.3932
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0216 | 2026-10-14 | Survey for Excavation and Gravel Bedding Placement for Lighting Pole Foundation at Road (RD-02),Left Side. @ Zone-4 Pole Number: - 1) FP-23-1/1/5Y 9) FP-23-1/1/13R 2) FP-23-1/1/6B 10) FP-23-1/1/14Y 3) FP-23-1/1/7R 11) FP-23-1/1/15B 4) FP-23-1/1/8Y 12) FP-23-1/1/16R 5) FP-23-1/1/9B 13) FP-23-1/1/17Y 6) FP-23-1/1/10R 14) FP-23-1/1/18B 7) FP-23-1/1/11Y 15) FP-23-1/1/19R 8) FP-23-1/1/12B 16) FP-23-1/1/20Y | 8923.992 | 0.8 | 7139.1936
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0230 | 2026-10-15 | FIR for Assembly and Installation of Street Lighting Pole 10 meter height with 1 arm, including the power Distribution box, at Road (RD-02), Left Side. @ Zone-4 Pole Number: - 1) FP-22-1/3/1R 11) FP-22-1/3/11Y 2) FP-22-1/3/2Y 12) FP-22-1/3/12B 3) FP-22-1/3/3B 13) FP-22-1/3/13R 4) FP-22-1/3/4R 5) FP-22-1/3/5Y 6) FP-22-1/3/6B 7) FP-22-1/3/7R 8) FP-22-1/3/8Y 9) FP-22-1/3/9B 10) FP-22-1/3/10R | 8923.992 | 8.45 | 75407.7324
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0240 | 2026-10-17 | Survey for Excavation and Gravel Bedding Placement for Lighting Pole Foundation at Road (RD-02),Right & Left Side. @ Zone-4 Pole Number: - 1) FP-21-1/1/9B 14) FP-22-1/1/13R 2) FP-21-1/1/10R 15) FP-22-1/1/14Y 3) FP-21-1/1/11Y 16) FP-22-1/1/15B 4) FP-21-1/1/12B 17) FP-22-1/1/16R 5) FP-21-1/1/13R 18) FP-22-1/1/17Y 6) FP-21-1/1/14Y 19) FP-22-1/1/18B 7) FP-21-1/5/11Y 20) FP-22-1/1/19R 8) FP-21-1/5/12B 21) FP-22-1/1/20Y 9) FP-21-1/5/13R 22) FP-22-1/1/21B 10) FP-21-1/5/14Y 23) FP-22-1/1/22R 11) FP-21-1/5/15B 24) FP-22-1/1/23Y 12) FP-21-1/5/16R 25) FP-22-1/1/24B 13) FP-21-1/5/17Y 26) FP-21-1/2/13R | 8923.992 | 1.3 | 11601.1896
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0241 | 2026-10-17 | Survey and Compaction FIR for Backfill around the Electrical Pole concrete Foundation, Layer-5, at Road (RD-02), Left Side. @ Zone-4 Pole Number: - 1) FP-22-1/3/1R 11) FP-22-1/3/11Y 2) FP-22-1/3/2Y 12) FP-22-1/3/12B 3) FP-22-1/3/3B 13) FP-22-1/3/13R 4) FP-22-1/3/4R 5) FP-22-1/3/5Y 6) FP-22-1/3/6B 7) FP-22-1/3/7R 8) FP-22-1/3/8Y 9) FP-22-1/3/9B 10) FP-22-1/3/10R | 8923.992 | 0.65 | 5800.5948
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0243 | 2026-10-17 | FIR for Survey of Concrete Foundation Installation for Lighting Pole, at Road (RD-02),Right Side. @ Zone-4 Pole Number: - 1) FP-23-1/2/3B 9) FP-23-1/2/11Y 2) FP-23-1/2/4R 10) FP-23-1/2/12B 3) FP-23-1/2/5Y 11) FP-23-1/2/13R 4) FP-23-1/2/6B 12) FP-23-1/2/14Y 5) FP-23-1/2/7R 13) FP-23-1/2/15B 6) FP-23-1/2/8Y 14) FP-23-1/2/16R 7) FP-23-1/2/9B 15) FP-23-1/2/17Y 8) FP-23-1/2/10R 16) FP-23-1/2/18B 17) FP-23-1/3/25R | 8923.992 | 2.55 | 22756.1796
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0251 | 2026-10-18 | FIR for Survey of Concrete Foundation Installation for Lighting Pole, at Road (RD-02),Right Side. @ Zone-4 Pole Number: - 1) FP-22-1/1/13R 9) FP-22-1/1/21B 2) FP-22-1/1/14Y 10) FP-22-1/1/22R 3) FP-22-1/1/15B 11) FP-22-1/1/23Y 4) FP-22-1/1/16R 12) FP-22-1/1/24B 5) FP-22-1/1/17Y 13) FP-21-1/2/13R 6) FP-22-1/1/18B 7) FP-22-1/1/19R 8) FP-22-1/1/20Y | 8923.992 | 1.95 | 17401.7844
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0259 | 2026-10-19 | Survey and Compaction FIR for Backfill around the Electrical Pole concrete Foundation, Layer-5, at Road (RD-02),Right Side. @ Zone-4 Pole Number: - 1) FP-23-1/2/3B 9) FP-23-1/2/11Y 2) FP-23-1/2/4R 10) FP-23-1/2/12B 3) FP-23-1/2/5Y 11) FP-23-1/2/13R 4) FP-23-1/2/6B 12) FP-23-1/2/14Y 5) FP-23-1/2/7R 13) FP-23-1/2/15B 6) FP-23-1/2/8Y 14) FP-23-1/2/16R 7) FP-23-1/2/9B 15) FP-23-1/2/17Y 8) FP-23-1/2/10R 16) FP-23-1/2/18B 17) FP-23-1/3/25R | 8923.992 | 0.85 | 7585.3932
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0260 | 2026-10-19 | FIR for Assembly and Installation of Street Lighting Pole 10 meter height with 1 arm, including the power Distribution box, at Road (RD-02),Right Side. @ Zone-3 Pole Number: - 1) FP-23-1/2/3B 9) FP-23-1/2/11Y 2) FP-23-1/2/4R 10) FP-23-1/2/12B 3) FP-23-1/2/5Y 11) FP-23-1/2/13R 4) FP-23-1/2/6B 12) FP-23-1/2/14Y 5) FP-23-1/2/7R 13) FP-23-1/2/15B 6) FP-23-1/2/8Y 14) FP-23-1/2/16R 7) FP-23-1/2/9B 15) FP-23-1/2/17Y 8) FP-23-1/2/10R 16) FP-23-1/2/18B 17) FP-23-1/3/25R | 8923.992 | 11.05 | 98610.1116
B2.33 71 16.02 | Lighting poles with 1 arm, height of ( 10) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0263 | 2026-10-19 | FIR for Survey of Concrete Foundation Installation for Lighting Pole, at Road (RD-02),Right & Left Side. @ Zone-3 & 4 Pole Number: - 1) FP-22-1/2/1R 12) FP-23-1/1/16R 2) FP-22-1/2/2Y 13) FP-23-1/1/17Y 3) FP-22-1/2/3B 14) FP-23-1/1/18B 4) FP-22-1/2/4R 15) FP-23-1/1/19R 5) FP-22-1/2/5Y 16) FP-22-1/1/9B 6) FP-22-1/2/6B 17) FP-22-1/1/10R 7) FP-22-1/2/7R 18) FP-22-1/1/11Y 8) FP-22-1/2/8Y 19) FP-22-1/1/12B 9) FP-23-1/1/13R 10) FP-23-1/1/14Y 11) FP-23-1/1/15B | 8923.992 | 2.85 | 25433.3772
B2.33 71 16.03 | Lighting poles with 1 arm, height of ( 12 ) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0006 | 2026-08-29 | Survey for Excavation and Gravel Bedding Placement for Lighting Pole Foundation at Road (Arterial RD). Zone-3 Pole Number: - 1) FP-23-2/6/13R 9) FP-23-2/6/5Y 2) FP-23-2/6/12B 10) FP-23-2/6/4R 3) FP-23-2/6/11Y 11) FP-23-2/6/3B 4) FP-23-2/6/10R 12) FP-23-2/6/2Y 5) FP-23-2/6/9B 13) FP-23-2/6/1R 6) FP-23-2/6/8Y 14) FP-23-2/5/1R 7) FP-23-2/6/7R 15) FP-23-2/5/2Y 8) FP-23-2/6/6B 16) FP-23-2/5/3B 17) FP-23-2/5/4R | 10372.692 | 0.85 | 8816.7882
B2.33 71 16.03 | Lighting poles with 1 arm, height of ( 12 ) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0014 | 2026-08-30 | FIR for Survey of Installation of Electrical Pole concrete Foundation at Road (Arterial RD). Zone-3 Pole Number :- 1) FP-23-2/6/12B 9) FP-23-2/6/4R 2) FP-23-2/6/11Y 10) FP-23-2/6/3B 3) FP-23-2/6/10R 11) FP-23-2/6/2Y 4) FP-23-2/6/9B 12) FP-23-2/6/1R 5) FP-23-2/6/8Y 13) FP-23-2/5/1R 6) FP-23-2/6/7R 14) FP-23-2/5/2Y 7) FP-23-2/6/6B 15) FP-23-2/5/3B 8) FP-23-2/6/5Y 16) FP-23-2/5/4R | 10372.692 | 2.4 | 24894.4608
B2.33 71 16.03 | Lighting poles with 1 arm, height of ( 12 ) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0049 | 2026-09-12 | Survey and Compaction FIR for Backfill around the Electrical Pole concrete Foundation, Layer-Final at Road (Arterial RD).Right Side.@ Zone-3 Pole Number :- 1) FP-23-2/6/12B 9) FP-23-2/6/4R 2) FP-23-2/6/11Y 10) FP-23-2/6/3B 3) FP-23-2/6/10R 11) FP-23-2/6/2Y 4) FP-23-2/6/9B 12) FP-23-2/6/1R 5) FP-23-2/6/8Y 13) FP-23-2/5/1R 6) FP-23-2/6/7R 14) FP-23-2/5/2Y 7) FP-23-2/6/6B 15) FP-23-2/5/3B 8) FP-23-2/6/5Y 16) FP-23-2/5/4R | 10372.692 | 0.8 | 8298.1536
B2.33 71 16.03 | Lighting poles with 1 arm, height of ( 12 ) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0054 | 2026-09-12 | Survey for Excavation and Gravel Bedding Placement for Lighting Pole Foundation at Road (Arterial RD)Left Side. Zone-3 Pole Number: - 1) FP-23-2/1/12B 9) FP-23-2/1/4R 2) FP-23-2/1/11Y 10) FP-23-2/1/3B 3) FP-23-2/1/10R 11) FP-23-2/1/2Y 4) FP-23-2/1/9B 12) FP-23-2/1/1R 5) FP-23-2/1/8Y 13) FP-23-2/4/1R 6) FP-23-2/1/7R 14) FP-23-2/4/2Y 7) FP-23-2/1/6B 15) FP-23-2/4/3B 8) FP-23-2/1/5Y 16) FP-23-2/4/4R | 10372.692 | 0.8 | 8298.1536
B2.33 71 16.03 | Lighting poles with 1 arm, height of ( 12 ) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0058 | 2026-09-14 | FIR for Assembly and Installation of Street Lighting Pole 12 meter height with 1 arm, including the power Distribution box at Road (Arterial RD) Right Side. Zone-3 Pole Number :- 1) FP-23-2/6/12B 9) FP-23-2/6/4R 2) FP-23-2/6/11Y 10) FP-23-2/6/3B 3) FP-23-2/6/10R 11) FP-23-2/6/2Y 4) FP-23-2/6/9B 12) FP-23-2/6/1R 5) FP-23-2/6/8Y 13) FP-23-2/5/1R 6) FP-23-2/6/7R 14) FP-23-2/5/2Y 7) FP-23-2/6/6B 15) FP-23-2/5/3B 8) FP-23-2/6/5Y 16) FP-23-2/5/4R | 10372.692 | 10.4 | 107875.9968
B2.33 71 16.03 | Lighting poles with 1 arm, height of ( 12 ) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0077 | 2026-09-19 | FIR for Survey of Installation of Electrical Pole concrete Foundation at Road (Arterial RD)Left Side. Zone-3 Pole Number: - 1) FP-23-2/1/11Y 09) FP-23-2/1/3B 2) FP-23-2/1/10R 10) FP-23-2/1/2Y 3) FP-23-2/1/9B 11) FP-23-2/1/1R 4) FP-23-2/1/8Y 12) FP-23-2/4/1R 5) FP-23-2/1/7R 13) FP-23-2/4/2Y 6) FP-23-2/1/6B 14) FP-23-2/4/3B 7) FP-23-2/1/5Y 15) FP-23-2/4/4R 8) FP-23-2/1/4R | 10372.692 | 2.25 | 23338.557
B2.33 71 16.03 | Lighting poles with 1 arm, height of ( 12 ) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0082 | 2026-09-20 | FIR for Assembly and Installation of Street Lighting Pole 12 meter height with 1 arm, including the power Distribution box at Road (Arterial RD)Left Side. Zone-3 Pole Number: - 1) FP-23-2/1/11Y 09) FP-23-2/1/3B 2) FP-23-2/1/10R 10) FP-23-2/1/2Y 3) FP-23-2/1/9B 11) FP-23-2/1/1R 4) FP-23-2/1/8Y 12) FP-23-2/4/1R 5) FP-23-2/1/7R 13) FP-23-2/4/2Y 6) FP-23-2/1/6B 14) FP-23-2/4/3B 7) FP-23-2/1/5Y 15) FP-23-2/4/4R 8) FP-23-2/1/4R | 10372.692 | 9.75 | 101133.747
B2.33 71 16.03 | Lighting poles with 1 arm, height of ( 12 ) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0085 | 2026-09-21 | FIR for Survey of Installation of Electrical Pole concrete Foundation at Road (Arterial RD)Left Side. Zone-3 Pole Number: - 1) FP-23-2/1/12B | 10372.692 | 0.15 | 1555.9038
B2.33 71 16.03 | Lighting poles with 1 arm, height of ( 12 ) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0087 | 2026-09-22 | Survey and Compaction FIR for Backfill around the Electrical Pole concrete Foundation, Layer-Final at Road (Arterial RD)Left Side. Zone-3 Pole Number: - 1) FP-23-2/1/11Y 09) FP-23-2/1/3B 2) FP-23-2/1/10R 10) FP-23-2/1/2Y 3) FP-23-2/1/9B 11) FP-23-2/1/1R 4) FP-23-2/1/8Y 12) FP-23-2/4/1R 5) FP-23-2/1/7R 13) FP-23-2/4/2Y 6) FP-23-2/1/6B 14) FP-23-2/4/3B 7) FP-23-2/1/5Y 15) FP-23-2/4/4R 8) FP-23-2/1/4R | 10372.692 | 0.75 | 7779.519
B2.33 71 16.03 | Lighting poles with 1 arm, height of ( 12 ) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0092 | 2026-09-24 | FIR for Assembly and Installation of Street Lighting Pole 12 meter height with 1 arm, including the power Distribution box at Road (Arterial RD)Left Side. Zone-3 Pole Number: - 1) FP-23-2/1/12B | 10372.692 | 0.65 | 6742.2498
B2.33 71 16.03 | Lighting poles with 1 arm, height of ( 12 ) meters, including the power distribution box, cables , and RCC foundation. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0098 | 2026-09-26 | Survey and Compaction FIR for Backfill around the Electrical Pole concrete Foundation, Layer-Final at Road (Arterial RD)Left Side. Zone-3 Pole Number: - 1) FP-23-2/1/12B | 10372.692 | 0.05 | 518.6346
B2.26.56.19.01 | Street Lighting( LED), Lamp Lumen: 14560, Luminare Lumen:12700 , complete with control gear and lamp, (80) WATT. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0073 | 2026-09-19 | FIR for the Installation of Street Lighting LED Luminar 80 Watt on Pole 10 meter height ,1 arm at Road (RD-01) Right Side. Zone-1 Pole Number :- 1) FP-22-2/4/2Y 8) FP-22-2/4/10R 2) FP-22-2/4/3B 9) FP-22-2/4/11Y 3) FP-22-2/4/4R 10) FP-22-2/4/12B 4) FP-22-2/4/5Y 11) FP-22-2/4/13R 5) FP-22-2/4/6B 6) FP-22-2/4/7R 7) FP-22-2/4/8Y | 927.168 | 5.5 | 5099.424
B2.26.56.19.01 | Street Lighting( LED), Lamp Lumen: 14560, Luminare Lumen:12700 , complete with control gear and lamp, (80) WATT. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0074 | 2026-09-19 | FIR for the Installation of Street Lighting LED Luminar 80 Watt on Pole 10 meter height ,1 arm at Road (RD-01) Right Side. Zone-1 Pole Number :- 1) FP-22-2/4/14Y 8) FP-22-2/4/21B 2) FP-22-2/4/15B 9) FP-22-2/4/22R 3) FP-22-2/4/16R 10) FP-22-2/4/23Y 4) FP-22-2/4/17Y 11) FP-22-2/4/24B 5) FP-22-2/4/18B 12) FP-22-2/4/25R 6) FP-22-2/4/19R 13) FP-22-2/4/26Y 7) FP-22-2/4/20Y 14) FP-22-2/4/27B | 927.168 | 7 | 6490.176
B2.26.56.19.01 | Street Lighting( LED), Lamp Lumen: 14560, Luminare Lumen:12700 , complete with control gear and lamp, (80) WATT. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0075 | 2026-09-19 | FIR for the Installation of Street Lighting LED Luminar 80 Watt on Pole 10 meter height ,1 arm at Road (RD-01) Left Side. Zone-1 Pole Number :- 1) FP-22-2/3/13R 7) FP-22-2/3/21B 2) FP-22-2/3/16R 8) FP-22-2/3/22R 3) FP-22-2/3/17Y 9) FP-22-2/3/23Y 4) FP-22-2/3/18B 10) FP-22-2/3/24B 5) FP-22-2/3/19R 11) FP-22-2/3/25R 6) FP-22-2/3/20Y 12) FP-22-2/3/26Y 13) FP-22-2/3/27B | 927.168 | 6.5 | 6026.592
B2.26.56.19.01 | Street Lighting( LED), Lamp Lumen: 14560, Luminare Lumen:12700 , complete with control gear and lamp, (80) WATT. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0076 | 2026-09-19 | FIR for the Installation of Street Lighting LED Luminar 80 Watt on Pole 10 meter height ,1 arm at Road (RD-01) Left Side. Zone-1 Pole Number :- 1) FP-22-2/3/28R 8) FP-22-2/3/36B 2) FP-22-2/3/29Y 9) FP-22-2/3/37R 3) FP-22-2/3/30B 10) FP-22-2/4/9B 4) FP-22-2/3/31R 11) FP-22-2/4/28R 5) FP-22-2/3/32Y 12) FP-22-2/4/29Y 6) FP-22-2/3/33B 13) FP-22-2/4/30B 7) FP-22-2/3/34R | 927.168 | 6.5 | 6026.592
B2.26.56.19.01 | Street Lighting( LED), Lamp Lumen: 14560, Luminare Lumen:12700 , complete with control gear and lamp, (80) WATT. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0211 | 2026-10-14 | FIR for the Installation of Street Lighting LED Luminar 80 Watt on Pole 10 meter height ,1 arm, at Road (RD-02) Right Side. @Zone-4 Pole Number :- 1) FP-21-1/2/1R 20) FP-21-1/3/11Y 2) FP-21-1/2/2Y 21) FP-21-1/3/12B 3) FP-21-1/2/3B 22) FP-21-1/3/13R 4) FP-21-1/2/4R 23) FP-21-1/3/14Y 5) FP-21-1/2/5Y 24) FP-21-1/3/15B 6) FP-21-1/2/6B 25) FP-21-1/3/16R 7) FP-21-1/2/7R 26) FP-21-1/3/17Y 8) FP-21-1/2/8Y 27) FP-21-1/3/18B 9) FP-21-1/3/9B 28) FP-21-1/3/19R 10) FP-21-1/3/1R 29) FP-21-1/3/20Y 11) FP-21-1/3/2Y 30) FP-21-1/3/21B 12) FP-21-1/3/3B 31) FP-21-1/3/22R 13) FP-21-1/3/4R 32) FP-21-1/3/23Y 14) FP-21-1/3/5Y 33) FP-21-1/3/24B 15) FP-21-1/3/6B 16) FP-21-1/3/7R 17) FP-21-1/3/8Y 18) FP-21-1/3/9B 19) FP-21-1/3/10R | 927.168 | 16.5 | 15298.272
B2.26.56.19.01 | Street Lighting( LED), Lamp Lumen: 14560, Luminare Lumen:12700 , complete with control gear and lamp, (80) WATT. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0242 | 2026-10-17 | FIR for the Installation of Street Lighting LED Luminar 80 Watt on Pole 10 meter height ,1 arm, at Road (RD-02) Left Side. @Zone-4 Pole Number :- 1) FP-22-1/3/10R 17) FP-21-1/1/3B 2) FP-22-1/3/11Y 18) FP-21-1/1/4R 3) FP-22-1/3/12B 19) FP-21-1/1/5Y 4) FP-22-1/3/13R 20) FP-21-1/1/6B 5) FP-22-1/3/14Y 21) FP-21-1/1/7R 6) FP-21-1/4/3B 22) FP-21-1/1/8Y 7) FP-21-1/4/4R 23) FP-22-1/3/1R 8) FP-21-1/4/5Y 24) FP-22-1/3/2Y 9) FP-21-1/4/6B 25) FP-22-1/3/3B 10) FP-21-1/4/7R 26) FP-22-1/3/4R 11) FP-21-1/6/2Y 27) FP-22-1/3/5Y 12) FP-21-1/6/3B 28) FP-22-1/3/6B 13) FP-21-1/6/4R 29) FP-22-1/3/7R 14) FP-21-1/6/5Y 15) FP-21-1/1/1R 16) FP-21-1/1/2Y | 927.168 | 14.5 | 13443.936
B2.26.56.19.01 | Street Lighting( LED), Lamp Lumen: 14560, Luminare Lumen:12700 , complete with control gear and lamp, (80) WATT. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0246 | 2026-10-17 | FIR for the Installation of Street Lighting LED Luminar 140 Watt on Pole 12 meter height ,1 arm, at Road (RD-03). Zone-4 Pole Number: - 1) FP-21-1/5/1R 10) FP-21-1/6/8Y 2) FP-21-1/5/2Y 11) FP-21-1/6/9B 3) FP-21-1/5/3B 12) FP-21-1/6/10R 4) FP-21-1/5/4R 13) FP-21-1/6/11Y 5) FP-21-1/5/5Y 14) FP-21-1/6/12B 6) FP-21-1/5/6B 15) FP-21-1/6/13R 7) FP-21-1/5/7R 16) FP-21-1/6/14Y 8) FP-21-1/5/8Y 17) FP-21-1/6/15B 9) FP-21-1/5/9B 18) FP-21-1/6/16R | 927.168 | 9 | 8344.512
B2.26.56.19.02 | Street Lighting( LED), Lamp Lumen: 24286, Luminare Lumen:20914, complete with control gear and lamp, (140) WATT. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0070 | 2026-09-19 | FIR for the Installation of Street Lighting LED Luminar 140 Watt on Pole 12 meter height ,1 arm at Road (Arterial RD) Right Side. Zone-3 Pole Number :- 1) FP-23-2/6/12B 9) FP-23-2/6/4R 2) FP-23-2/6/11Y 10) FP-23-2/6/3B 3) FP-23-2/6/10R 11) FP-23-2/6/2Y 4) FP-23-2/6/9B 12) FP-23-2/6/1R 5) FP-23-2/6/8Y 13) FP-23-2/5/1R 6) FP-23-2/6/7R 14) FP-23-2/5/2Y 7) FP-23-2/6/6B 15) FP-23-2/5/3B 8) FP-23-2/6/5Y 16) FP-23-2/5/4R | 1065.892 | 8 | 8527.136
B2.26.56.19.02 | Street Lighting( LED), Lamp Lumen: 24286, Luminare Lumen:20914, complete with control gear and lamp, (140) WATT. | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0201 | 2026-10-12 | FIR for the Installation of Street Lighting LED Luminar 140 Watt on Pole 12 meter height ,1 arm at Road (Arterial RD)Left Side. Zone-3 Pole Number: - 1) FP-23-2/1/12B 2) FP-23-2/1/11Y 10) FP-23-2/1/3B 3) FP-23-2/1/10R 11) FP-23-2/1/2Y 4) FP-23-2/1/9B 12) FP-23-2/1/1R 5) FP-23-2/1/8Y 13) FP-23-2/4/1R 6) FP-23-2/1/7R 14) FP-23-2/4/2Y 7) FP-23-2/1/6B 15) FP-23-2/4/3B 8) FP-23-2/1/5Y 16) FP-23-2/4/4R 9) FP-23-2/1/4R | 1065.892 | 8 | 8527.136
B2.33 71 00 02 01 | Road Crossing Duct for Street Lighting cables UPVC (2xØ110mm) | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0217 | 2026-10-14 | FIR for Concrete Pouringof Duct bank for Street Lighting UPVC (2xØ110mm), at Road (RD-05). )Sta. 0+043.60 @ Zone-3 1) “ST-Duct Bank-08” | 275.692 | 16.56 | 4565.4595
B2.33 71 00 02 01 | Road Crossing Duct for Street Lighting cables UPVC (2xØ110mm) | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0236 | 2026-10-15 | FIR for Concrete Pouringof Duct bank for Street Lighting UPVC (2xØ110mm), at Road (RD-05). )Sta. 0+100.00 @ Zone-3 1) “ST-Duct Bank-09” | 275.692 | 9.35 | 2577.7202
B2.33 71 00 02 02 | Road Crossing Duct for Street Lighting cables UPVC (4xØ110mm) | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0066 | 2026-09-16 | FIR for Concrete Pouring of Duct bank for Street Lighting UPVC (4xØ110mm), at Road (RD-03). ).@ Sta. 0+050 .Zone-4 1) “ST-Duct Bank-7” | 421.44 | 16.15 | 6806.256
B2.33 71 00 02 02 | Road Crossing Duct for Street Lighting cables UPVC (4xØ110mm) | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0096 | 2026-09-24 | FIR for Concrete Pouring of Duct bank for Street Lighting UPVC (4xØ110mm), at Road (Arterial RD). )Sta. 0+390.30 @ Zone-3 1) “ST-Duct Bank-53” (Part – 1) | 421.44 | 18.3 | 7712.352
B2.33 71 00 02 02 | Road Crossing Duct for Street Lighting cables UPVC (4xØ110mm) | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0109 | 2026-09-27 | FIR for Concrete Pouring of Duct bank for Street Lighting UPVC (4xØ110mm), at Road (RD-02) . )Sta. 1+303.40 @ Zone-4 1) “ST-Duct Bank-05” | 421.44 | 17.45 | 7354.128
B2.33 71 00 02 02 | Road Crossing Duct for Street Lighting cables UPVC (4xØ110mm) | DAM2-02-09-SAJ-TS9-1-ELE-FIR-0171 | 2026-10-07 | FIR for Concrete Pouring of Duct bank for Street Lighting UPVC (4xØ110mm), at Road (RD-02). )Sta. 2+289.50 @ Zone-4 1) “ST-Duct Bank-06” | 421.44 | 15.8 | 6658.752
B2.1.33 81 26.01.01 | (6*50mm) HDPE ducts . | DAM2-02-09-SAJ-TS9-1-TEL-FIR-0031 | 2026-10-03 | FIR for Laying ducts (6*50mm) HDPE, at Road (RD-01)Left Side,@ Zone-1 MH-27 to (MH-24)3/4 = 55m (MH-24)1/2 to (MH-23)3/4 = 41m (MH-23)1/2 to (MH-21)5/6 = 80m (MH-21)1/2 to MH-09 = 51m MH-09 to MH-08 = 115m | 281.838 | 342 | 96388.596
B2.1.33 81 26.01.02 | (6*50mm+2*32mm) HDPE ducts . | DAM2-02-09-SAJ-TS9-1-TEL-FIR-0032 | 2026-10-03 | FIR for Laying ducts (6*50mm+2*32mm) HDPE, at Road (RD-01)Left Side.@ Zone-1 MH-24 to (MH-24)3/4 = 40m MH-24 to (MH-24)1/2 = 45m MH-23 to (MH-23)3/4 = 67m MH-23 to (MH-23)1/2 = 45m MH-21 to (MH-21)5/6 = 75m MH-21(3/4) to (MH-21)1/2 = 20m | 438.122 | 292 | 127931.624
B2.1.33 81 26.01.03 | (6*50mm+4*32mm) HDPE ducts . | DAM2-02-09-SAJ-TS9-1-TEL-FIR-0033 | 2026-10-03 | FIR for Laying ducts (6*50mm+4*32mm) HDPE, at Road (RD-01)Left Side.@ Zone-1 MH-21 to (MH-21)3/4 = 55m | 496.07 | 55 | 27283.85
B2.1.33 81 26.01.04 | (2*32mm) HDPE ducts . | DAM2-02-09-SAJ-TS9-1-TEL-FIR-0014 | 2026-07-18 | Survey for Ducts Installation FIR for HDPE DUCT @ MH-75 (3/4 to 1/2), Located along with Customs Road-2, ZONE-03. Dia 32mm | 156.284 | 26 | 4063.384
B2.1.33 81 26.01.05 | (4*32mm) HDPE ducts . | DAM2-02-09-SAJ-TS9-1-TEL-FIR-0013 | 2026-07-18 | Survey for Ducts Installation FIR for HDPE DUCT @ MH-75 to 3/4, Located along with Customs Road-2, ZONE-03. Dia 32mm | 214.232 | 30 | 6426.96
B2.1.33 81 26.02.01 | Manhole Type 1 | DAM2-02-09-SAJ-TS9-1-TEL-FIR-0034 | 2026-10-05 | FIR for Survey for Concrete Foundation Installation of Telecom Monhole (Type 1), at Road (RD-01),Left Side. @Zone-1 Manhole Number: - 1) MH - 09 3) MH - 23 2) MH - 21 4) MH - 24 | 7069.656 | 4 | 28278.624
B2.1.33 81 26.02.01 | Manhole Type 1 | DAM2-02-09-SAJ-TS9-1-TEL-FIR-0062 | 2026-10-18 | FIR for Survey for Concrete Foundation Installation of Telecom Monhole (Type 1), at Road (RD-01),Right Side. @Zone-1 Manhole Number: - 1) MH – 10 3) MH – 20 2) MH – 22 4) MH – 25 | 7069.656 | 4 | 28278.624
B2.1.33 81 26.02.02 | Manhole Type 2 | DAM2-02-09-SAJ-TS9-1-TEL-FIR-0010 | 2026-07-15 | Survey Excavation and Compaction Test FIR for MH-75, Located along with Customs Road-2, ZONE-03 | 6322.478 | 0.05 | 316.1239
B2.1.33 81 26.02.02 | Manhole Type 2 | DAM2-02-09-SAJ-TS9-1-TEL-FIR-0035 | 2026-10-05 | FIR for Survey for Concrete Foundation Installation of Telecom Monhole (Type 2), at Road (RD-01) Left Side. @Zone-1 Manhole Number: - 1) MH - 08 2) MH - 27 | 6322.478 | 2 | 12644.956
B2.1.33 81 26.02.02 | Manhole Type 2 | DAM2-02-09-SAJ-TS9-1-TEL-FIR-0063 | 2026-10-18 | FIR for Survey for Concrete Foundation Installation of Telecom Monhole (Type 2), at Road (RD-01),Right Side. @Zone-1 Manhole Number: - 1) MH – 06 2) MH – 07 3) MH – 28 | 6322.478 | 3 | 18967.434
B2.1.33 81 26.02.02 | Manhole Type 2 | DAM2-02-09-SAJ-TS9-1-TEL-FIR-0064 | 2026-10-19 | FIR for Survey for Concrete Foundation Installation of Telecom Monhole (Type 2), at Road (RD-05) Right & Left Side. @Zone-3 Manhole Number: - 1) 1) MH – 36 2) MH – 37 | 6322.478 | 2 | 12644.956
B2.1.33 81 26.03.01 | Road crossing ductus, (6x50) HDPE | DAM2-02-09-SAJ-TS9-1-TEL-FIR-0005 | 2026-05-09 | FIR for Concrete Pouring of Road crossing ducts, (6*50mm) HDPE at Road (RD-01). @ Sta. 0+807.25- # “TL-Duct Bank-03” | 311.69 | 20 | 6233.8
B2.1.33 81 26.03.01 | Road crossing ductus, (6x50) HDPE | DAM2-02-09-SAJ-TS9-1-TEL-FIR-0007 | 2026-05-09 | FIR for Concrete Pouring of Road crossing ducts, (6*50mm) HDPE at Road (RD-01). @ Sta. 0+044- # “TL-Duct Bank-02” | 311.69 | 20 | 6233.8
B2.1.33 81 26.03.01 | Road crossing ductus, (6x50) HDPE | DAM2-02-09-SAJ-TS9-1-TEL-FIR-0017 | 2026-09-20 | FIR for Concrete Pouring of Road crossing ducts, (6*50mm) HDPE at Road (RD-03). @ Sta. 0+055.35- # “TL-Duct Bank-08” | 311.69 | 16 | 4987.04
B2.1.33 81 26.03.01 | Road crossing ductus, (6x50) HDPE | DAM2-02-09-SAJ-TS9-1-TEL-FIR-0030 | 2026-10-01 | FIR for Concrete Pouring of Road crossing ducts, (6*50mm) HDPE at Road (RD-02). @ Sta. 2+500- # “TL-Duct Bank-07” | 311.69 | 16 | 4987.04
B2.1.33 81 26.03.01 | Road crossing ductus, (6x50) HDPE | DAM2-02-09-SAJ-TS9-1-TEL-FIR-0038 | 2026-10-07 | FIR for Concrete Pouring of Road crossing ducts, (6*50mm) HDPE, at Road (RD-02) Sta. 1+636.6, @Zone–4 # “TL-Duct Bank- 06” | 311.69 | 16 | 4987.04
B2.1.33 81 26.03.01 | Road crossing ductus, (6x50) HDPE | DAM2-02-09-SAJ-TS9-1-TEL-FIR-0055 | 2026-10-14 | FIR for Concrete Pouring of Road crossing ducts, (6*50mm) HDPE, at Road (RD-02) Sta. 0+049.9, @Zone–3 # “TL-Duct Bank- 09” | 311.69 | 16.5 | 5142.885
B2.1.33 81 26.03.03 | Road crossing ductus, (2x32) HDPE | DAM2-02-09-SAJ-TS9-1-TEL-FIR-0006 | 2026-05-09 | FIR for Concrete Pouring of Road crossing ducts, (2*32mm) HDPE, at Road (RD-01). @ Sta. 0+025 & 0+822.43- # “TL-Duct Bank-01 & 04” | 163.308 | 26.4 | 4311.3312
B2.1.33 81 26.03.03 | Road crossing ductus, (2x32) HDPE | DAM2-02-09-SAJ-TS9-1-TEL-FIR-0027 | 2026-09-29 | FIR for Concrete Pouring of Road crossing ducts, (2*32mm) HDPE, at Road (RD-02) Sta. 0+104.64, @Zone–3 # “TL-Duct Bank- 05” | 163.308 | 8.2 | 1339.1256
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0001 | 2026-04-05 | Survey Excavation and Compaction Testing FIR for Potable Water Network Plan Part 04 and Part 05 RD-01 from Station 0+216.00 TO 0+862.771 @ZONE-01 | 143.992 | 64.68 | 9313.4026
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0002 | 2026-04-05 | Survey FIR for Sand Bedding of Potable Water Network Plan Part 04 and Part 05 at RD-01 from Station 0+216.00 TO 0+862.771 @ZONE-01 | 143.992 | 32.34 | 4656.7013
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0004 | 2026-04-07 | Mechanical FIR for Installation and Laying of HDPE Pipe of Potable Water Network Plan Part 04 and Part 05 at RD-01 from Station 0+216.00 TO 0+862.771 @ ZONE-01 | 143.992 | 420.4 | 60534.2368
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0005 | 2026-04-07 | Survey Excavation and Compaction Testing FIR for Potable Water Network Plan Part 04 and Part 05 at RD-02 from Station 1+093.98 TO 1+480 & 1+540 TO 1+566 @ZONE-04 | 143.992 | 41.2 | 5932.4704
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0006 | 2026-04-07 | Survey FIR for Sand Bedding of Potable Water Network Plan Part 04 and Part 05 at RD-02 from Station 1+093.98 TO 1+480 & 1+540 TO 1+566 @ ZONE-04 | 143.992 | 20.6 | 2966.2352
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0009 | 2026-04-09 | Survey Excavation and Compaction Testing FIR for Potable Water Network Plan Part 05 at RD-01 from Station 0+138.00 TO 0+186.00 @ZONE-01 | 143.992 | 4.8 | 691.1616
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0010 | 2026-04-09 | Survey FIR for Sand Bedding of Potable Water Network Plan Part 05 at RD-01 from Station 0+138.00 TO 0+186.00 @ZONE-01 | 143.992 | 2.4 | 345.5808
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0011 | 2026-04-14 | Survey Excavation and Compaction Testing FIR for Potable Water Network Plan Part 03 at RD-02 from Station 0+480.00 TO 0+809.99 @ZONE-03 | 143.992 | 33 | 4751.736
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0012 | 2026-04-14 | Survey FIR for Sand Bedding of Potable Water Network Plan Part 03 at RD-02 from Station 0+480.00 TO 0+809.99 @ZONE-03 | 143.992 | 16.5 | 2375.868
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0015 | 2026-04-16 | Mechanical FIR for Installation and Laying of HDPE Pipe of Potable Water Network Plan Part 04 and Part 05 at RD-02 from Station 1+093.98 TO 1+480 @ZONE-04 | 143.992 | 250.91 | 36129.0327
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0017 | 2026-04-16 | Survey Excavation and Compaction Testing FIR for Potable Water Network Plan Part 05 at RD-01 from Station 0+186.00 TO 0+216.00 @ZONE-01 | 143.992 | 3 | 431.976
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0018 | 2026-04-16 | Survey FIR for Sand Bedding of Potable Water Network Plan Part 05 at RD-01 from Station 0+186.00 TO 0+216.00 @ZONE-01 | 143.992 | 1.5 | 215.988
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0021 | 2026-04-16 | Survey Excavation and Compaction Testing FIR for Potable Water Network Plan Part 05 at RD-01 from Station 0+000.25 TO 0+100.00 @ZONE-01 | 143.992 | 9.98 | 1437.0402
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0022 | 2026-04-16 | Survey FIR for Sand Bedding of Potable Water Network Plan Part 05 at RD-01 from Station 0+000.25 TO 0+100.00 @ZONE-01 | 143.992 | 4.99 | 718.5201
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0027 | 2026-04-18 | Mechanical FIR for Installation and Laying of HDPE Pipe of Potable Water Network Plan Part 05 at RD-02 from Station 1+540 TO 1+566 @ZONE-04 | 143.992 | 16.9 | 2433.4648
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0031 | 2026-04-25 | Survey Excavation and Compaction Testing FIR for Potable Water Network Plan Part 03 at RD-02 from Station 0+174.00 TO 0+480.00 @ZONE-03 | 143.992 | 30.6 | 4406.1552
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0032-01 | 2026-09-08 | Survey FIR for Sand Bedding of Potable Water Network Plan Part 03 at RD-02 from Station 0+174.00 TO 0+480.00 @ ZONE-03 | 143.992 | 15.3 | 2203.0776
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0033 | 2026-04-25 | Survey Excavation and Compaction Testing FIR for Potable Water Network Plan Part 03 and Part 07 at Entrance RD-01 from Station 0+654.972 TO 0+840 & 0+980 TO 1+006.738@ ZONE-02 | 143.992 | 21.18 | 3049.7506
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0034 | 2026-04-25 | Survey FIR for Sand Bedding of Potable Water Network Plan Part 03 and Part 07 at RD-02 from Station 0+654.972 TO 0+840 & 0+980 TO 1+006.738 @ZONE-02 | 143.992 | 10.59 | 1524.8753
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0038 | 2026-04-26 | Mechanical FIR for Installation and Laying of HDPE Pipe of Potable Water Network Plan Part 03 at RD-02 from Station 0+480.00 TO 0+809.99 @ZONE-03 | 143.992 | 214.49 | 30884.8441
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0040 | 2026-04-29 | Mechanical FIR for Installation and Laying of HDPE Pipe of Potable Water Network Plan Part 03 at RD-02 from Station 0+174.00 TO 0+480.00 @ZONE-03 | 143.992 | 198.9 | 28640.0088
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0043 | 2026-04-30 | Mechanical FIR for Installation and Laying of HDPE Pipeline of Potable Water Network Plan Part 03 and Part 07 at Entrances RD-01 from Station 0+654.972 TO 0+840 & 0+980 TO 1+006.738 @ZONE-02 | 143.992 | 137.65 | 19820.4988
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0007 | 2026-04-07 | Survey Excavation and Compaction Testing FIR for Potable Water Network Plan Part 04 and Part 05 at RD-02 from Station 1+480 TO 1+540 @ZONE-04 | 143.992 | 6 | 863.952
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0008 | 2026-04-07 | Survey FIR for Sand Bedding of Potable Water Network Plan Part 04 and Part 05 at RD-02 from Station 1+480 TO 1+540 @ ZONE-04 | 143.992 | 3 | 431.976
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0016 | 2026-04-16 | Mechanical FIR for Installation and Laying of HDPE Pipe of Potable Water Network Plan Part 04 and Part 05 at RD-02 from Station 1+480 TO 1+494 @ZONE-04 | 143.992 | 9.1 | 1310.3272
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0023 | 2026-04-16 | Survey Excavation and Compaction Testing FIR for Potable Water Network Plan Part 05 at RD-01 from Station 0+100.00 TO 0+138.00 @ZONE-01 | 143.992 | 3.8 | 547.1696
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0024 | 2026-04-16 | Survey FIR for Sand Bedding of Potable Water Network Plan Part 05 at RD-01 from Station 0+100.00 TO 0+138.00 @ZONE-01 | 143.992 | 1.9 | 273.5848
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0026 | 2026-04-18 | Mechanical FIR for Installation and Laying of HDPE Pipe of Potable Water Network Plan Part 05 at RD-02 from Station 1+494 TO 1+540 @ZONE-04 | 143.992 | 29.9 | 4305.3608
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0035 | 2026-04-25 | Survey Excavation and Compaction Testing FIR for Potable Water Network Plan Part 03 and Part 07 at Entrance RD-01 from Station 0+840 TO 0+980 @ ZONE-02 | 143.992 | 14 | 2015.888
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0036 | 2026-04-25 | Survey FIR for Sand Bedding of Potable Water Network Plan Part 03 and Part 07 at RD-02 from Station 0+840 TO 0+980 @ZONE-02 | 143.992 | 7 | 1007.944
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0044 | 2026-04-30 | Mechanical FIR for Installation and Laying of HDPE Pipeline of Potable Water Network Plan Part 03 and Part 07 at Entrances RD-01 from Station 0+840 TO 0+980 @ZONE-02 | 143.992 | 91 | 13103.272
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0053 | 2026-06-04 | Mechanical FIR for Installation and Laying of HDPE Pipeline of Potable Water Network Plan Part 05 at RD-01 from Station 0+000.25 TO 0+216.00 @ZONE-01 | 143.992 | 140.24 | 20193.4381
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0055 | 2026-06-30 | Survey Excavation and Compaction Testing FIR for Potable Water Network Plan Part 04 and Part 05 at RD-02 from Station 1+566 TO 1+794.00, @ZONE-04 | 143.992 | 22.8 | 3283.0176
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0056-01 | 2026-09-08 | Survey Sand Bedding and Compaction Testing FIR for Potable Water Network Plan Part 04 and Part 05 at RD-02 from Station 1+566 TO 1+794.00, @ZONE-04 | 143.992 | 11.4 | 1641.5088
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0057 | 2026-06-30 | Survey Excavation and Compaction Testing FIR for Potable Water Network Plan Part 04 and Part 05 at RD-02 from Station 0+996.00 TO 1+093.98, @ZONE-04 | 143.992 | 9.8 | 1411.1216
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0058-01 | 2026-09-08 | Survey Sand Bedding and Compaction Testing FIR for Potable Water Network Plan Part 04 and Part 05 at RD-02 from Station 0+996.00 TO 1+093.98, @ZONE-04 | 143.992 | 4.9 | 705.5608
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0061 | 2026-07-02 | Mechanical FIR for Installation and Laying off HDPE Pipe Line for Potable Water Network Plan Part 04 and Part 05 at RD-02 from Station 1+566 TO 1+794.00, @ZONE-04 | 143.992 | 148.2 | 21339.6144
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0062 | 2026-07-02 | Mechanical FIR for Installation and Laying off HDPE Pipe Line for Potable Water Network Plan Part 04 and Part 05 at RD-02 from Station 0+996.00 TO 1+093.98, @ZONE-04 | 143.992 | 63.69 | 9170.8505
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0067 | 2026-08-06 | Survey FIR for Sand Covering and Compaction Testing above the HDPE Pipeline of Potable Water Network Plan 05 at RD-01 from Station 0+000.25 To 0+216.00, @ Zone-01 | 143.992 | 10.79 | 1553.6737
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0068 | 2026-08-06 | Survey FIR for Sand Covering and Compaction Testing above the HDPE Pipeline of Potable Water Network Plan Part-03 at RD-02 from Station 0+480.00 To 0+809.99, @ Zone-03 | 143.992 | 16.5 | 2375.868
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0069 | 2026-08-06 | Survey FIR for Sand Covering and Compaction Testing above the HDPE Pipeline of Potable Water Network Plan Part-04 and Part-05 at RD-02 from Station 1+093.98.00 To 1+794.00, @ Zone-04 | 143.992 | 35 | 5039.72
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0070 | 2026-08-12 | Survey Excavation and Compaction Testing FIR for Potable Water Network Plan at RD-02 from Station 0+031 TO 0+255.00 @ZONE-04 | 143.992 | 22.4 | 3225.4208
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0071 | 2026-08-12 | Survey Sand Bedding and Compaction Testing FIR for Potable Water Network Plan at RD-02 from Station 0+031 TO 0+255.00 @ZONE-04 | 143.992 | 11.2 | 1612.7104
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0072 | 2026-08-13 | Survey and mechanical FIR for Installation and Laying off HDPE Pipe Line for Potable Water Network Plan at RD-02 from Station 0+031 TO 0+255.00 @ZONE-04 | 143.992 | 145.6 | 20965.2352
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0073 | 2026-08-15 | Survey Excavation and Compaction Testing FIR for Potable Water Network Plan Part 04 and Part 05 at RD-02 from Station 0+756.00 TO 0+996.00, @ZONE-04 | 143.992 | 24 | 3455.808
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0074 | 2026-08-15 | Survey Sand Bedding and Compaction Testing FIR for Potable Water Network Plan Part 04 and Part 05 at RD-02 from Station 0+756.00 TO 0+996.00, @ZONE-04 | 143.992 | 12 | 1727.904
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0075 | 2026-08-16 | Survey and Mechanical FIR for Installation and Laying of HDPE Pipeline of Potable Water Network Plan Part 04 and Part 05 at RD-02 from Station 0+756.00 TO 0+996.00, @ZONE-04 | 143.992 | 156 | 22462.752
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0076 | 2026-08-17 | Survey Excavation and Compaction Testing FIR for Potable Water Network Plan Part 04 and Part 05 at RD-03 LINE#5 from Station 0+045.00 TO 0+340.00, @ZONE-04 | 143.992 | 29.5 | 4247.764
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0077 | 2026-08-17 | Survey Fir for Sand Bedding and Compaction Testing for Potable Water Network Plan at RD-03 line#5 from Station 0+045.00 TO 0+340.00, @ZONE-04 | 143.992 | 14.75 | 2123.882
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0078 | 2026-08-18 | Survey and Mechanical FIR for Installation and Laying of HDPE Pipeline of Potable Water Network Plan at RD-03 line#5 from Station 0+045.00 TO 0+340.00, @ZONE-04 | 143.992 | 191.75 | 27610.466
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0079 | 2026-08-22 | Survey Excavation and Compaction Testing FIR for Potable Water Network Plan at RD-02 from Station 0+255 TO 0+515 | 143.992 | 26 | 3743.792
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0080 | 2026-08-22 | Survey Fir for Sand Bedding and Compaction Testing for Potable Water Network Plan at RD-02 from Station 0+255 TO 0+515 | 143.992 | 13 | 1871.896
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0081 | 2026-08-23 | Survey and Mechanical FIR for Installation and Laying of HDPE Pipeline of Potable Water Network Plan at RD-02 from Station 0+255 TO 0+515 | 143.992 | 169 | 24334.648
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0082 | 2026-08-30 | Survey Fir for Excavation and Compaction Testing FIR for Potable Water Network Plan at RD-04 Line-06 from Station 0+030 TO 0+330 | 143.992 | 30 | 4319.76
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0083 | 2026-08-30 | Survey Fir for Sand bedding and Compaction Testing FIR for Potable Water Network Plan at RD-04 Line-06 from Station 0+030 TO 0+330 | 143.992 | 15 | 2159.88
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0084 | 2026-08-30 | Survey Fir for Excavation and Compaction Testing FIR for Potable Water Network Plan at RD-02 from Station 0+515 TO 0+756@Zone:4 | 143.992 | 24.1 | 3470.2072
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0085 | 2026-08-30 | Survey Fir for Sand Bedding and Compaction Testing FIR for Potable Water Network Plan at RD-02 from Station 0+515 TO 0+756 @Zone:4 | 143.992 | 12.05 | 1735.1036
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0086 | 2026-08-31 | Survey and Mechanical Fir for Installation and laying for Potable Water Network at RD-04 Line-06 from Station 0+030 TO 0+330 @ Zone:4 | 143.992 | 195 | 28078.44
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0087 | 2026-08-31 | Survey and Mechanical Fir for Installation and laying for Potable Water Network at RD-02 from Station 0+515 TO 0+756 @Zone:4 | 143.992 | 156.65 | 22556.3468
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0101 | 2026-10-14 | Survey Fir for Excavation and Compaction Testing FIR for Potable Water Network at RD-03 Line-05 from Station 0+0.025 TO 0+045.000 & 0+340.000 to 0+360.00 & 0+360 to 0+371.259 | 143.992 | 7.62 | 1097.219
B3.33 14 13.01.01 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-POT-FIR-0102 | 2026-10-14 | Survey Fir for Excavation and Compaction Testing FIR for Potable Water Network at RD-04 Line-06 from Station 0+0.025 TO 0+030 & 0+330 to 0+360 & 0+360 to 0+372 | 143.992 | 7.2 | 1036.7424
B3.33 14 13.02.01 | Plots and Buildings Crossing Connections diameter 110 mm | DAM2-02-09-SAJ-TS9-1-POT-FIR-0019 | 2026-04-16 | Survey Excavation and Compaction Testing FIR for Potable Water Network Branch Line from HDPE Fitting-134 TO HDPE Fitting-158, HDPE Fitting-135 To HDPE Fitting-159 and HDPE Fitting-121 TO HDPE Fitting-160, Plan Part 05 at RD-01 @ZONE-01 | 447.78 | 0.3 | 134.334
B3.33 14 13.02.01 | Plots and Buildings Crossing Connections diameter 110 mm | DAM2-02-09-SAJ-TS9-1-POT-FIR-0020-01 | 2026-04-21 | Survey FIR for Sand Bedding of Potable Water Network Branch Line from HDPE Fitting-134 TO HDPE Fitting-158, HDPE Fitting-135 To HDPE Fitting-159 and HDPE Fitting-121 TO HDPE Fitting-160, Plan Part 05 at RD-01 @ZONE-01 | 447.78 | 0.15 | 67.167
B3.33 14 13.02.01 | Plots and Buildings Crossing Connections diameter 110 mm | DAM2-02-09-SAJ-TS9-1-POT-FIR-0029-00 | 2026-04-21 | Survey Excavation and Compaction Testing FIR for Potable Water Network Branch Line from HDPE Fitting-156 TO HDPE Fitting-157, Plan Part 04 at RD-01 @ZONE-01 | 447.78 | 0.1 | 44.778
B3.33 14 13.02.01 | Plots and Buildings Crossing Connections diameter 110 mm | DAM2-02-09-SAJ-TS9-1-POT-FIR-0047-00 | 2026-05-14 | Mechanical FIR for Installation and Laying of Potable Water Network Branch Line with Concrete Encasement from HDPE Fitting-134 TO HDPE Fitting-158 with Gate Valve - (60), HDPE Fitting-135 To HDPE Fitting-159 with Gate Valve - (61) and HDPE Fitting-121 TO HDPE Fitting-160 with Gate Valve - (62), Plan Part 05 at RD-01 @ZONE-01 | 447.78 | 1.95 | 873.171
B3.33 14 13.02.01 | Plots and Buildings Crossing Connections diameter 110 mm | DAM2-02-09-SAJ-TS9-1-POT-FIR-0048-00 | 2026-05-14 | Mechanical FIR for Installation and Laying of Potable Water Network Branch Line with Concrete Encasement from HDPE Fitting-156 TO HDPE Fitting-15 with Gate Valve - (43), Plan Part 04 at RD-01 @ZONE-01 | 447.78 | 0.65 | 291.057
B3.33 14 13.02.01 | Plots and Buildings Crossing Connections diameter 110 mm | DAM2-02-09-SAJ-TS9-1-POT-FIR-0088 | 2026-09-06 | Survey Excavation and Compaction Testing FIR for Potable Water Network Branch Line from HDPE Fitting-105 TO HDPE Fitting-165 and HDPE Fitting-114 To HDPE Fitting-166 at RD # 4 ZONE-4 | 447.78 | 0.2 | 89.556
B3.33 14 13.02.01 | Plots and Buildings Crossing Connections diameter 110 mm | DAM2-02-09-SAJ-TS9-1-POT-FIR-0089 | 2026-09-06 | Survey Fir Concrete Encasement for Potable Water Network Branch Line from HDPE Fitting-105 TO HDPE Fitting-165 and HDPE Fitting-114 To HDPE Fitting-166 at RD # 4 ZONE-4 | 447.78 | 0.1 | 44.778
B3.33 14 13.02.01 | Plots and Buildings Crossing Connections diameter 110 mm | DAM2-02-09-SAJ-TS9-1-POT-FIR-0090 | 2026-09-06 | Survey Excavation and Compaction Testing FIR for Potable Water Network Branch Line from HDPE Fitting-116 TO HDPE Fitting-167 and HDPE Fitting-115 To HDPE Fitting-168 at RD#3 ZONE :4 | 447.78 | 0.2 | 89.556
B3.33 14 13.02.01 | Plots and Buildings Crossing Connections diameter 110 mm | DAM2-02-09-SAJ-TS9-1-POT-FIR-0091 | 2026-09-06 | Survey Fir Concrete Encasement for Potable Water Network Branch Line from HDPE Fitting-116 TO HDPE Fitting-167 and HDPE Fitting-115 To HDPE Fitting-168 at RD#3 ZONE :4 | 447.78 | 0.1 | 44.778
B3.33 14 13.02.01 | Plots and Buildings Crossing Connections diameter 110 mm | DAM2-02-09-SAJ-TS9-1-POT-FIR-0092 | 2026-09-07 | Survey and Mechanical Fir installation and laying of Potable Water Network Branch Line from HDPE Fitting-105 TO HDPE Fitting-165 and HDPE Fitting-114 To HDPE Fitting-166 at RD # 4 ZONE-4 | 447.78 | 1.3 | 582.114
B3.33 14 13.02.01 | Plots and Buildings Crossing Connections diameter 110 mm | DAM2-02-09-SAJ-TS9-1-POT-FIR-0093 | 2026-09-07 | Survey and Mechanical Fir installation and laying of Potable Water Network Branch Line from HDPE Fitting-116 TO HDPE Fitting-167 and HDPE Fitting-115 To HDPE Fitting-168 at RD#3 ZONE :4 | 447.78 | 1.3 | 582.114
B3.33 14 13.02.01 | Plots and Buildings Crossing Connections diameter 110 mm | DAM2-02-09-SAJ-TS9-1-POT-FIR-0095 | 2026-09-14 | Survey Excavation and Compaction Testing FIR for Potable Water Network Branch Line from HDPE Fitting-199 TO HDPE Fitting-110 and HDPE Fitting-150 To HDPE Fitting-149 at RD#2 ZONE :4 | 447.78 | 0.2 | 89.556
B3.33 14 13.02.01 | Plots and Buildings Crossing Connections diameter 110 mm | DAM2-02-09-SAJ-TS9-1-POT-FIR-0096 | 2026-09-14 | Survey Fir concrete encasement for Potable Water Network Branch Line from HDPE Fitting-199 TO HDPE Fitting-110 and HDPE Fitting-150 To HDPE Fitting-149 at RD#2 ZONE :4 | 447.78 | 0.1 | 44.778
B3.33 14 13.02.01 | Plots and Buildings Crossing Connections diameter 110 mm | DAM2-02-09-SAJ-TS9-1-POT-FIR-0097 | 2026-09-15 | Survey and Mechanical Fir for installation and laying of Potable Water Network Branch Line from HDPE Fitting-199 TO HDPE Fitting-110 and HDPE Fitting-150 To HDPE Fitting-149 at RD#2 ZONE :4 | 447.78 | 1.3 | 582.114
B3.33 05 63.02.01 | Air valve chamber; on less than 315 mm diameter pipeline | DAM2-02-09-SAJ-TS9-1-POT-FIR-0064-00 | 2026-07-09 | Survey Excavation and Compaction Testing FIR for Air Valve Chamber - 24 of Potable Water Network @ Zone-04 | 22137.014 | 0.05 | 1106.8507
B3.33 05 63.02.01 | Air valve chamber; on less than 315 mm diameter pipeline | DAM2-02-09-SAJ-TS9-1-POT-FIR-0094-00 | 2026-09-09 | Fir for Installation of Air Valve Chamber – 24 with insulation work of Potable Water Network @ Zone-04 | 22137.014 | 0.45 | 9961.6563
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0002-00 | 2026-02-07 | Survey Excavation and Compaction Testing FIR for Fire Fighting Pipeline Line-05 RD-02 from Station 1+180 TO 1+350, @ ZONE-04 | 478.51 | 17 | 8134.67
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0004-00 | 2026-02-07 | Survey FIR for Sand Bedding for Fire Fighting Pipeline Line-05 RD-02 from Station 1+180 TO 1+350, @ ZONE-4 | 478.51 | 8.5 | 4067.335
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0005-00 | 2026-03-01 | Survey Excavation and Compaction Testing FIR for Fire Fighting Pipeline Line-05 RD-02 from Station 0+600 TO 0+720 & Station 0+760 TO 0+800, @ ZONE-01 | 478.51 | 16 | 7656.16
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0008-00 | 2026-03-08 | Survey Excavation and Compaction Testing FIR for Fire Fighting Pipeline RD-01 Line #4 from Station 0+520 to 0+540 @ ZONE-01 | 478.51 | 2 | 957.02
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0010-00 | 2026-03-10 | Survey FIR for Sand Bedding for Fire Fighting Pipeline Line #4 RD-01 from Station 0+720 to 0+863.94, @ ZONE-01 | 478.51 | 7.2 | 3445.272
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0011-00 | 2026-03-10 | Survey FIR for Sand Bedding for Fire Fighting Pipeline RD-01 Line #4 from Station 0+419.36 to 0+520 & 0+540 to 0+600, @ ZONE-01 | 478.51 | 8.03 | 3842.4353
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0013-00 | 2026-03-11 | Survey Excavation and Compaction Testing FIR for Fire Fighting Pipeline Line-05 RD-02 from Station 1+350 TO 1+440 & 1+580 TO 1+598.51, @ ZONE-04 | 478.51 | 10.85 | 5191.8335
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0015-00 | 2026-03-11 | Survey FIR for Sand Bedding for Fire Fighting Pipeline Line-05 RD-02 from Station 1+350 TO 1+440 & 1+580 TO 1+598.51, @ ZONE-04 | 478.51 | 5.43 | 2598.3093
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0020-00 | 2026-03-18 | Mechanical FIR for Installation and Laying of HDPE Pipe Line for Fire Fighting Network RD-01 Line #4 from Station 0+520 to 0+540 & 0+720 to 0+863.94 @ ZONE-01, Pipe DIA 250mm | 478.51 | 106.56 | 50990.0256
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0021-00 | 2026-03-29 | Survey Excavation and Compaction Testing FIR for Fire Fighting Pipeline Line #4 RD-01 from Station 0+207 to 0+220 @ ZONE-01, Pipe DIA 250mm | 478.51 | 1.3 | 622.063
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0023-00 | 2026-03-29 | Survey FIR for Sand Bedding of Fire Fighting Pipeline Line #4 RD-01 from Station 0+207 to 0+220 @ ZONE-01, Pipe DIA 250mm | 478.51 | 0.65 | 311.0315
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0028-00 | 2026-03-29 | Mechanical FIR for Installation and Laying of HDPE Pipe Line for Fire Fighting Pipeline Line-05 RD-02 from Station 1+180 TO 1+440, @ ZONE-4 | 478.51 | 169 | 80868.19
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0031-00 | 2026-04-02 | Mechanical FIR for Installation and Laying of HDPE Pipe Line For Fire Fighting Pipeline Line #4 RD-01 from Station 0+207 to 0+220 @ ZONE-01, Pipe DIA 250mm | 478.51 | 8.45 | 4043.4095
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0033 | 2026-04-09 | Survey Excavation and Compaction Testing FIR for Fire Fighting Pipeline Line # 4 RD-01 from Station 0+139.217 To 0+187.217 @ ZONE-01, Pipe DIA 250mm | 478.51 | 4.8 | 2296.848
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0034 | 2026-04-09 | Survey FIR for Sand Bedding of Fire Fighting Pipeline Line # 4 RD-01 from Station 0+139.217 to 0+187.217 @ ZONE-01, Pipe DIA 250mm | 478.51 | 2.4 | 1148.424
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0035 | 2026-04-14 | Survey Excavation and Compaction Testing FIR for Fire Fighting Pipeline Line #2 RD-02 from Station 0+482.877 to 0+640 & 0+740 to 0+813.477 @ ZONE-03, Pipe DIA 250mm | 478.51 | 23.06 | 11034.4406
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0037 | 2026-04-14 | Survey FIR for Sand Bedding of Fire Fighting Pipeline Line #2 RD-02 from Station 0+482.877 to 0+640 & 0+740 to 0+813.477 @ ZONE-03, Pipe DIA 250mm | 478.51 | 11.53 | 5517.2203
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0039 | 2026-04-16 | Survey Excavation and Compaction Testing FIR for Fire Fighting Pipeline Line #4 RD-01 from Station 0+187.217 TO 0+207 @ ZONE-01, Pipe DIA 250mm | 478.51 | 1.98 | 947.4498
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0040 | 2026-04-16 | Survey FIR for Sand Bedding of Fire Fighting Pipeline Line #4 RD-01 from Station 0+187.217 TO 0+207 @ ZONE-01, Pipe DIA 250mm | 478.51 | 0.99 | 473.7249
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0043 | 2026-04-16 | Survey Excavation and Compaction Testing FIR for Fire Fighting Pipeline Line #4 RD-01 from Station 0+040 TO 0+139.217 @ ZONE-01, Pipe DIA 250mm | 478.51 | 9.92 | 4746.8192
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0044 | 2026-04-16 | Survey FIR for Sand Bedding of Fire Fighting Pipeline Line #4 RD-01 from Station 0+040.00 TO 0+139.217 @ ZONE-01, Pipe DIA 250mm | 478.51 | 4.96 | 2373.4096
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0053 | 2026-04-21 | Mechanical FIR for Installation and Laying of HDPE Pipeline of Fire Fighting Pipeline Line #2 RD-02 from Station 0+482.877 to 0+640 & 0+740 to 0+813.477 @ ZONE-03, Pipe DIA 250mm | 478.51 | 149.89 | 71723.8639
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0055-01 | 2026-09-08 | Survey Excavation and Compaction Testing FIR for Fire Fighting Pipeline Line #2 RD-02 from Station 0+376.101 to 0+420.00 @ ZONE-03, Pipe DIA 250mm | 478.51 | 4.39 | 2100.6589
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0056 | 2026-04-27 | Survey FIR for Sand Bedding of Fire Fighting Pipeline Line #2 RD-02 from Station 0+376.101 to 0+420.00, @ ZONE-03, Pipe DIA 250mm | 478.51 | 2.19 | 1047.9369
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0059 | 2026-04-27 | Survey Excavation and Compaction Testing FIR for Fire Fighting Pipeline Line #1 (Commercial & Management RD1) from Station 0+653.810 To 1+006.139 @ ZONE-02, Pipe DIA 250mm | 478.51 | 35.23 | 16857.9073
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0060 | 2026-04-27 | Survey FIR for Sand Bedding of Fire Fighting Pipeline Line #1 (Entrance RD1) from Station 0+653.810 To 1+006.139 @ ZONE-02, Pipe DIA 250mm | 478.51 | 17.62 | 8431.3462
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0032-00 | 2026-04-02 | Mechanical FIR for Installation and Laying of HDPE Pipe Line for Fire Fighting Pipeline Line #4 RD-01 from Station 0+220 to 0+419.36 @ ZONE-01, Pipe DIA 250mm | 478.51 | 129.58 | 62005.3258
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0036-00 | 2026-04-14 | Survey Excavation and Compaction Testing FIR for Fire Fighting Pipeline Line #2 RD-02 from Station 0+640 to 0+740 @ ZONE-03, Pipe DIA 250mm | 478.51 | 10 | 4785.1
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0038-00 | 2026-04-14 | Survey FIR for Sand Bedding of Fire Fighting Pipeline Line #2 RD-02 from Station 0+640 to 0+740 @ ZONE-03, Pipe DIA 250mm | 478.51 | 5 | 2392.55
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0041-00 | 2026-04-16 | Survey Excavation and Compaction Testing FIR for Fire Fighting Pipeline Line #4 RD-01 from Station 0+000.650 TO 0+040 @ ZONE-01, Pipe DIA 250mm | 478.51 | 3.94 | 1885.3294
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0042-00 | 2026-04-16 | Survey FIR for Sand Bedding of Fire Fighting Pipeline Line #4 RD-01 from Station 0+000.650 TO 0+040.00 @ ZONE-01, Pipe DIA 250mm | 478.51 | 1.97 | 942.6647
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0050-00 | 2026-04-21 | Mechanical FIR for Installation and Laying of HDPE Pipe Line for Fire Fighting Pipeline-05 RD-02 from Station 1+563.46 TO 1+580, @ ZONE-04 | 478.51 | 10.75 | 5143.9825
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0054-00 | 2026-04-21 | Mechanical FIR for Installation and Laying of HDPE Pipeline of Fire Fighting Pipeline Line #2 RD-02 from Station 0+640 to 0+740 @ ZONE-03, Pipe DIA 250mm | 478.51 | 65 | 31103.15
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0057-00 | 2026-04-27 | Survey Excavation and Compaction Testing FIR for Fire Fighting Pipeline Line #2 RD-02 from Station 0+420.00 to 0+482.877.00, @ ZONE-03, Pipe DIA 250mm | 478.51 | 6.29 | 3009.8279
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0058-00 | 2026-04-27 | Survey FIR for Sand Bedding of Fire Fighting Pipeline Line #2 RD-02 from Station 0+420.00 to 0+482.877.00 @ ZONE-03, Pipe DIA 250mm | 478.51 | 3.14 | 1502.5214
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0069-00 | 2026-05-20 | Mechanical FIR for Installation and Laying of HDPE Fire Fighting Pipeline Line #1 (Entrance RD1) from Station 0+653.810 TO 1+006.139 @ ZONE-02, Pipe DIA 250mm | 478.51 | 229.01 | 109583.5751
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0075 | 2026-06-30 | Survey Excavation and Compaction Testing FIR for Fire Fighting Pipeline Line-05 RD-02 from Station 1+598.51 TO 1+822.043, @ ZONE-04 | 478.51 | 22.35 | 10694.6985
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0076-01 | 2026-09-08 | Survey Sand Bedding and Compaction Testing FIR for Fire Fighting Pipeline Line-05 RD-02 from Station 1+598.51 TO 1+822.043, @ ZONE-04 | 478.51 | 11.18 | 5349.7418
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0077 | 2026-06-30 | Survey Excavation and Compaction Testing FIR for Fire Fighting Pipeline Line-05 RD-02 from Station 0+971.055 TO 1+100.00, @ ZONE-04 | 478.51 | 12.89 | 6167.9939
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0078-01 | 2026-09-08 | Survey Sand Bedding and Compaction Testing FIR for Fire Fighting Pipeline Line-05 RD-02 from Station 0+971.055 TO 1+100.00, @ ZONE-04 | 478.51 | 6.45 | 3086.3895
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0081 | 2026-07-02 | Mechanical FIR for Installation and Laying off HDPE Pipe Line for Fire Fighting Pipeline Line-05 RD-02 from Station 1+598.51 TO 1+822.043, @ ZONE-04 | 478.51 | 145.29 | 69522.7179
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0082 | 2026-07-02 | Mechanical FIR for Installation and Laying off HDPE Pipe Line for Fire Fighting Pipeline Line-05 RD-02 from Station 0+971.055 TO 1+100.00, @ ZONE-04 | 478.51 | 83.82 | 40108.7082
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0084 | 2026-07-09 | Survey Excavation and Compaction Testing FIR for Fire Fighting Pipeline Line-08 (U-01)RD-01 from Station 0+000.650 TO 0+120.535, @ ZONE-01 and ZONE-04 | 478.51 | 11.99 | 5737.3349
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0085 | 2026-07-09 | Survey FIR for Sand Bedding and Compaction Testing for Fire Fighting Pipeline Line-08 (U-01) RD-01 from Station 0+000.650 TO 0+120.535, @ ZONE-01 and ZONE-04 | 478.51 | 5.99 | 2866.2749
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0087-01 | 2026-08-26 | Mechanical FIR for Installation and Laying of HDPE Pipeline for Fire Fighting Pipeline Line-08 (U-01) RD-01 from Station 0+000.650 TO 0+120.535, @ ZONE-01 and ZONE-04 | 478.51 | 77.93 | 37290.2843
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0088 | 2026-08-02 | Survey Excavation and Compaction Testing FIR for Fire Fighting Pipeline Line-06 RD-03 from Station 0+000.650 to 0+371.700, @ ZONE-04 | 478.51 | 37.11 | 17757.5061
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0089 | 2026-08-02 | Survey Sand Bedding and Compaction Testing FIR for Fire Fighting Pipeline Line-06 RD-03 from Station 0+000.650 to 0+371.700, @ ZONE-04 | 478.51 | 18.55 | 8876.3605
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0091-01 | 2026-08-26 | Mechanical FIR for Installation and Laying of HDPE Pipe Line for Fire Fighting Pipeline Line #4 RD-01 from Station 0+000.650 to 0+207.00 @ ZONE-01, Pipe DIA 250mm | 478.51 | 134.13 | 64182.5463
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0092 | 2026-08-06 | Survey FIR for Sand Covering and Compaction Testing of HDPE Pipe Line for Fire Fighting Pipeline Line #4 RD-01 from Station 0+000.650 to 0+207.00 @ ZONE-01, Pipe DIA 250mm | 478.51 | 10.32 | 4938.2232
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0093 | 2026-08-12 | Survey Excavation and Compaction Testing FIR for Fire Fighting Pipeline RD-02 from Station 0+033 TO 0+260, @ ZONE-04 | 478.51 | 22.7 | 10862.177
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0094 | 2026-08-12 | Survey Sand Bedding and Compaction Testing FIR for Fire Fighting Pipeline RD-02 from Station 0+033 TO 0+260, @ ZONE-04 | 478.51 | 11.35 | 5431.0885
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0095 | 2026-08-13 | Survey and Mechanical FIR for Installation and Laying off HDPE Pipe Line for Fire Fighting Pipeline RD-02 from Station 0+033 TO 0+260, @ ZONE-04 | 478.51 | 147.55 | 70604.1505
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0096 | 2026-08-13 | Survey and Mechanical FIR for Installation and Laying of HDPE Pipeline for Fire Fighting Pipeline Line-06 RD-03 from Station 0+038 to 0+335 | 478.51 | 193.05 | 92376.3555
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0097 | 2026-08-15 | Survey FIR for Excavation and Compaction Testing of HDPE Pipe Line for Fire Fighting Pipeline Line-05 RD-02 from Station 0+758.658 TO 0+971.055, @ ZONE-04 | 478.51 | 21.24 | 10163.5524
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0098 | 2026-08-15 | Survey FIR for Sand Bedding and Compaction Testing of HDPE Pipe Line for Fire Fighting Pipeline Line-05 RD-02 from Station 0+758.658 TO 0+971.055, @ ZONE-04 | 478.51 | 10.62 | 5081.7762
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0099 | 2026-08-16 | Survey and Mechanical FIR for Installation and Laying off HDPE Pipe Line for Fire Fighting Pipeline Line-05 RD-02 from Station 0+758.658 TO 0+971.055, @ ZONE-04 | 478.51 | 138.06 | 66063.0906
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0100 | 2026-08-31 | Survey FIR for Excavation and Compaction Testing of HDPE Pipe Line for Fire Fighting Pipeline RD-04 from Station 0+030 TO 0+342, @ ZONE-04 | 478.51 | 31.2 | 14929.512
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0101 | 2026-08-31 | Survey FIR for Sand bedding and Compaction Testing of HDPE Pipe Line for Fire Fighting Pipeline RD-04 from Station 0+030 TO 0+342, @ ZONE-04 | 478.51 | 15.6 | 7464.756
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0102 | 2026-09-01 | Survey and Mechanical FIR for Installation and laying of HDPE Pipe Line for Fire Fighting Pipeline RD-04 from Station 0+030 TO 0+342, @ ZONE-04 | 478.51 | 202.8 | 97041.828
B3.1. 33 14 13.01.01 | 250mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0109 | 2026-10-17 | Survey FIR for Excavation and Compaction Testing of HDPE Fire Fighting Pipeline Line #5 RD-02 from Station 1. 0+000 to 0+033 2. 0+260 to 0+420 @ ZONE-04 | 478.51 | 19.3 | 9235.243
B3.1. 33 14 13.01.02 | 250mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0001-00 | 2026-02-07 | Survey Excavation and Compaction Testing FIR for Fire Fighting Pipeline Line-05 RD-02 from Station 1+100 TO 1+180, @ ZONE-04 | 522.41 | 8 | 4179.28
B3.1. 33 14 13.01.02 | 250mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0003-00 | 2026-02-07 | Survey FIR for Sand Bedding for Fire Fighting Pipeline Line-05 RD-02 from Station 1+100 TO 1+180, @ ZONE-4 | 522.41 | 4 | 2089.64
B3.1. 33 14 13.01.02 | 250mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0006-00 | 2026-03-01 | Survey Excavation and Compaction Testing FIR for Fire Fighting Pipeline Line-05 RD-01 from Station 0+720 to 0+760 & 0+800 to 0+864, @ ZONE-01 | 522.41 | 10.4 | 5433.064
B3.1. 33 14 13.01.02 | 250mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0007-00 | 2026-03-08 | Survey Excavation and Compaction Testing FIR for Fire Fighting Pipeline RD-01 Line #4 from Station 0+419.36 to 0+520 & 0+540 to 0+600, @ ZONE-01 | 522.41 | 16.06 | 8389.9046
B3.1. 33 14 13.01.02 | 250mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0009-00 | 2026-03-10 | Survey FIR for Sand Bedding for Fire Fighting Pipeline Line #4 RD-01 from Station 0+600 TO 0+720 @ ZONE-01 | 522.41 | 6 | 3134.46
B3.1. 33 14 13.01.02 | 250mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0012-00 | 2026-03-10 | Survey FIR for Sand Bedding for Fire Fighting Pipeline RD-01 Line #4 from Station 0+520 to 0+540 @ ZONE-01 | 522.41 | 1 | 522.41
B3.1. 33 14 13.01.02 | 250mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0014-00 | 2026-03-11 | Survey Excavation and Compaction Testing FIR for Fire Fighting Pipeline Line-05 RD-02 from Station 1+440 TO 1+580, @ ZONE-04 | 522.41 | 14 | 7313.74
B3.1. 33 14 13.01.02 | 250mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0016-00 | 2026-03-11 | Survey FIR for Sand Bedding for Fire Fighting Pipeline Line-05 RD-02 from Station 1+440 TO 1+580, @ ZONE-04 | 522.41 | 7 | 3656.87
B3.1. 33 14 13.01.02 | 250mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0019-00 | 2026-03-18 | Mechanical FIR for Installation and Laying of HDPE Pipe Line for Fire Fighting Network RD-01 Line # 4 from Station 0+419.36 to 0+520, 0+540 to 0+720 @ ZONE-01, Pipe DIA 250mm | 522.41 | 182.42 | 95298.0322
B3.1. 33 14 13.01.02 | 250mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0022-00 | 2026-03-29 | Survey Excavation and Compaction Testing FIR for Fire Fighting Pipeline Line #4 RD-01 from Station 0+220 to 0+419.36 @ ZONE-01, Pipe DIA 250mm | 522.41 | 19.94 | 10416.8554
B3.1. 33 14 13.01.02 | 250mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0024-00 | 2026-03-29 | Survey FIR for Sand Bedding of Fire Fighting Pipeline Line #4 RD-01 from Station 0+220 to 0+419.36 @ ZONE-01, Pipe DIA 250mm | 522.41 | 9.97 | 5208.4277
B3.1. 33 14 13.01.02 | 250mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-FF-FIR-0027-00 | 2026-03-29 | Mechanical FIR for Installation and Laying of HDPE Pipe Line for Fire Fighting Pipeline-05 RD-02 from Station 1+100 TO 1+180 & Station 1+440 TO 1+563.46, @ ZONE-04 | 522.41 | 132.25 | 69088.7225
B3.1. 33 14 19.04 | 3-outlet fire hydrant (2 x 2.5 inch and 1 x 4.5 inch) in the form of a separate dry vacuum cylinder | DAM2-02-09-SAJ-TS9-1-FF-FIR-0074-00 | 2026-06-17 | Mechanical FIR for Assembly and Installation of Fire Hydrant Appurtenance - (85, 86, 87, 88, 89, 90, 91, 92, 93, 94 and 95) @ Line-05 RD-01 , @ Zone-01 | 11010.12 | 10 | 110101.2
B3.33 05 63.04.01 | Wash out valve chamber; on 110-400 mm diameter pipeline | DAM2-02-09-SAJ-TS9-1-FF-FIR-0063-00 | 2026-05-10 | Survey Excavation and Compaction Testing FIR for Washout Chamber - 182 @ Zone-01 | 34347.36 | 0.05 | 1717.368
B3.33 05 63.04.01 | Wash out valve chamber; on 110-400 mm diameter pipeline | DAM2-02-09-SAJ-TS9-1-FF-FIR-0103-00 | 2026-09-09 | Survey Excavation and Compaction Testing FIR for Washout Chamber – 181 & Chamber-190 @ Zone-04 | 34347.36 | 0.1 | 3434.736
B3.33 05 63.04.01 | Wash out valve chamber; on 110-400 mm diameter pipeline | DAM2-02-09-SAJ-TS9-1-FF-FIR-0105-00 | 2026-09-12 | Fir for Installation of Washout Chamber – 181 & Chamber-190 @ Zone-04 | 34347.36 | 0.9 | 30912.624
B3.2.31 23 16.01 | Excavation of Potable water pump station, Chlorination and Potable water tank | DAM2-02-09-SAJ-TS9-1-STU-FIR-0001-01 | 2026-05-04 | Inspection for survey works of excavation for bottom of replacement soil (Potable Water Pump Station, Potable Water Tank, and Chlorination Building). | 46.534 | 1960.84 | 91245.7286
B3.2.31 23 16.01 | Excavation of Potable water pump station, Chlorination and Potable water tank | DAM2-02-09-SAJ-TS9-1-STU-FIR-0002 | 2026-05-04 | Inspection for survey works of excavation for bottom of replacement soil of the potable water pump station. | 46.534 | 653.86 | 30426.7212
B3.2.31 23 23.01 | Engineering backfiling as per soil report recommendation, including compaction in layers up to the required level ,testing and all required in accordance with the specifications and the supervising Engineer | DAM2-02-09-SAJ-TS9-1-STU-FIR-0096 | 2026-07-29 | Inspection of survey works and compaction testing for the 1st layer of selected engineering fill (25 cm thick) placed as replacement soil at Footing of Potable Water Pump Station. | 33.364 | 1.463 | 48.8115
B3.2.31 23 23.01 | Engineering backfiling as per soil report recommendation, including compaction in layers up to the required level ,testing and all required in accordance with the specifications and the supervising Engineer | DAM2-02-09-SAJ-TS9-1-STU-FIR-0099 | 2026-08-02 | Inspection of survey works and compaction testing for the 2nd layer of selected engineering fill (25 cm thick) placed as replacement soil at Footing of Potable Water Pump Station. | 33.364 | 1.463 | 48.8115
B3.2.31 23 23.01 | Engineering backfiling as per soil report recommendation, including compaction in layers up to the required level ,testing and all required in accordance with the specifications and the supervising Engineer | DAM2-02-09-SAJ-TS9-1-STU-FIR-0132 | 2026-08-22 | Survey Inspection for Backfill and Compaction Testing of 1st Layer (25 cm) around the Footings of Potable Water Pump Station. | 33.364 | 11.675 | 389.5247
B3.2.31 23 23.01 | Engineering backfiling as per soil report recommendation, including compaction in layers up to the required level ,testing and all required in accordance with the specifications and the supervising Engineer | DAM2-02-09-SAJ-TS9-1-STU-FIR-0133 | 2026-08-22 | Survey Inspection for Backfill and Compaction Testing of 2nd Layer (25 cm) around the Footings of Potable Water Pump Station. | 33.364 | 11.675 | 389.5247
B3.2.31 23 23.01 | Engineering backfiling as per soil report recommendation, including compaction in layers up to the required level ,testing and all required in accordance with the specifications and the supervising Engineer | DAM2-02-09-SAJ-TS9-1-STU-FIR-0144 | 2026-08-23 | Inspection of survey works and compaction testing for the 1st layer of selected engineering fill (25 cm thick) placed as replacement soil at Potable Water Tank (Part-2) | 33.364 | 193.044 | 6440.72
B3.2.31 23 23.01 | Engineering backfiling as per soil report recommendation, including compaction in layers up to the required level ,testing and all required in accordance with the specifications and the supervising Engineer | DAM2-02-09-SAJ-TS9-1-STU-FIR-0145 | 2026-08-23 | Inspection of survey works and compaction testing for the 2nd layer of selected engineering fill (25 cm thick) placed as replacement soil at Potable Water Tank (Part-2) | 33.364 | 193.044 | 6440.72
B3.2.31 23 23.01 | Engineering backfiling as per soil report recommendation, including compaction in layers up to the required level ,testing and all required in accordance with the specifications and the supervising Engineer | DAM2-02-09-SAJ-TS9-1-STU-FIR-0154 | 2026-08-24 | Survey Inspection for Backfill and Compaction Testing of 5th Layer (25 cm) around the outsides of Footings of Potable Water Pump Station. | 33.364 | 20.64 | 688.633
B3.2.31 23 23.01 | Engineering backfiling as per soil report recommendation, including compaction in layers up to the required level ,testing and all required in accordance with the specifications and the supervising Engineer | DAM2-02-09-SAJ-TS9-1-STU-FIR-0155 | 2026-08-24 | Survey Inspection for Backfill and Compaction Testing of 6th Layer (25 cm) around the outsides of footings of Potable Water Pump Station | 33.364 | 20.64 | 688.633
B3.2.31 23 23.01 | Engineering backfiling as per soil report recommendation, including compaction in layers up to the required level ,testing and all required in accordance with the specifications and the supervising Engineer | DAM2-02-09-SAJ-TS9-1-STU-FIR-0156 | 2026-08-24 | Survey Inspection for Backfill and Compaction Testing of 5th Layer (25 cm) around the inside and outsides of Footings of Chlorination building. | 33.364 | 11.815 | 394.1957
B3.2.31 23 23.01 | Engineering backfiling as per soil report recommendation, including compaction in layers up to the required level ,testing and all required in accordance with the specifications and the supervising Engineer | DAM2-02-09-SAJ-TS9-1-STU-FIR-0157 | 2026-08-24 | Survey Inspection for Backfill and Compaction Testing of 6th Layer (25 cm) around the inside and outsides of Footings of Chlorination building. | 33.364 | 11.815 | 394.1957
B3.2.31 23 23.01 | Engineering backfiling as per soil report recommendation, including compaction in layers up to the required level ,testing and all required in accordance with the specifications and the supervising Engineer | DAM2-02-09-SAJ-TS9-1-STU-FIR-0162 | 2026-08-25 | Survey Inspection for Backfill and Compaction Testing of 7th Layer (25 cm) around the Footings of Potable Water Pump Station. | 33.364 | 20.64 | 688.633
B3.2.31 23 23.01 | Engineering backfiling as per soil report recommendation, including compaction in layers up to the required level ,testing and all required in accordance with the specifications and the supervising Engineer | DAM2-02-09-SAJ-TS9-1-STU-FIR-0163 | 2026-08-25 | Survey Inspection for Backfill and Compaction Testing of 7th Layer (25 cm) around the inside and outsides of Footings of Chlorination building. | 33.364 | 11.815 | 394.1957
B3.2.31 23 23.01 | Engineering backfiling as per soil report recommendation, including compaction in layers up to the required level ,testing and all required in accordance with the specifications and the supervising Engineer | DAM2-02-09-SAJ-TS9-1-STU-FIR-0180 | 2026-08-27 | Survey Inspection for Backfill and Compaction Testing of 3rd Layer (25 cm) inside the Potable Water Pump Station. | 33.364 | 45.83 | 1529.0721
B3.2.31 23 23.01 | Engineering backfiling as per soil report recommendation, including compaction in layers up to the required level ,testing and all required in accordance with the specifications and the supervising Engineer | DAM2-02-09-SAJ-TS9-1-STU-FIR-0182 | 2026-08-29 | Survey Inspection for Backfill and Compaction Testing of 5th Layer (25 cm) inside the Potable Water Pump Station. | 33.364 | 47.604 | 1588.2599
B3.2.32 11 23.01 | Aggregate base course below slab on grade for Potable water pump stationand chlorination chamber | DAM2-02-09-SAJ-TS9-1-STU-FIR-0239 | 2026-09-19 | Survey Inspection for Backfill and Compaction Testing of 7th Layer (Aggregate base course) (15 cm) inside the Potable Water Pump Station | 86.922 | 28.562 | 2482.6662
B3.2.32 11 23.01 | Aggregate base course below slab on grade for Potable water pump stationand chlorination chamber | DAM2-02-09-SAJ-TS9-1-STU-FIR-0288 | 2026-10-05 | Inspection for survey works and compaction testing of Aggregate Base Course (20 cm) under the Slab on Grade in the Chlorination Building. | 86.922 | 4.9 | 425.9178
B3.2.03 30 00.02 | 50 mm thickness lean concrete under slab on grade for Potable water pump station & Chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0179 | 2026-08-27 | Inspection for 50 mm plain concrete of the electrical trench and drain trench inside the potable water pump station. | 438.122 | 1.38 | 604.6084
B3.2.03 30 00.02 | 50 mm thickness lean concrete under slab on grade for Potable water pump station & Chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0196 | 2026-09-02 | Inspection for 50 mm plain concrete below the grade beams (G.B.1, G.B.2 & G.B.3) of the Chlorination Building. | 438.122 | 0.4 | 175.2488
B3.2.03 30 00.02 | 50 mm thickness lean concrete under slab on grade for Potable water pump station & Chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0281 | 2026-10-05 | Survey Inspection for 50 mm Lean concrete under slab on grade for potable water pump station. | 438.122 | 9.24 | 4048.2473
B3.2.03 30 00.02 | 50 mm thickness lean concrete under slab on grade for Potable water pump station & Chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0284 | 2026-10-05 | Survey Inspection for 50 mm plain concrete below the grade beam (G.B.1) and of the Control Room and LV Room. | 438.122 | 0.51 | 223.4422
B3.2.03 30 00.02 | 50 mm thickness lean concrete under slab on grade for Potable water pump station & Chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0285 | 2026-10-05 | Survey Inspection for 50 mm plain concrete of the electrical trench inside of Control Room and LV Room. | 438.122 | 0.17 | 74.4807
B3.2.03 30 00.02 | 50 mm thickness lean concrete under slab on grade for Potable water pump station & Chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0290 | 2026-10-05 | Survey Inspection for 50 mm plain concrete below slab on grade of the Chlorination Building. | 438.122 | 1.22 | 534.5088
B3.2.03 30 00.03 | 100 mm thickness lean concrete under foundations | DAM2-02-09-SAJ-TS9-1-STU-FIR-0017 | 2026-05-18 | Inspection for survey works of excavation for bottom of replacement soil of the potable water pump station. | 438.122 | 13.88 | 6081.1334
B3.2.03 30 00.03 | 100 mm thickness lean concrete under foundations | DAM2-02-09-SAJ-TS9-1-STU-FIR-0018 | 2026-05-18 | Inspection of 100 mm thickness lean concrete under the foundation of Chlorination Building. | 438.122 | 0.97 | 424.9783
B3.2.03 30 00.03 | 100 mm thickness lean concrete under foundations | DAM2-02-09-SAJ-TS9-1-STU-FIR-0019 | 2026-05-18 | Inspection of 100 mm thickness lean concrete under the foundation of Potable Water Tank (Pit). | 438.122 | 0.68 | 297.923
B3.2.03 30 00.03 | 100 mm thickness lean concrete under foundations | DAM2-02-09-SAJ-TS9-1-STU-FIR-0052 | 2026-06-29 | Inspection of 100 mm thickness lean concrete under the foundation of Potable Water Tank (Part 1). | 438.122 | 76.64 | 33577.6701
B3.2.03 30 00.03 | 100 mm thickness lean concrete under foundations | DAM2-02-09-SAJ-TS9-1-STU-FIR-0112 | 2026-08-13 | Survey Inspection of Placement 100 mm thickness lean concrete for Footing of Control Room and Electrical Room (Portable Water Pump Station) as per the attached highlighted approved drawings. | 438.122 | 0.77 | 337.3539
B3.2.03 30 00.03 | 100 mm thickness lean concrete under foundations | DAM2-02-09-SAJ-TS9-1-STU-FIR-0262 | 2026-09-28 | Inspection of 100 mm thickness lean concrete under the foundation of Flow meter at Potable Water Tank. | 438.122 | 1.26 | 552.0337
B3.2.03 30 00.01 | Footings for Potable water pump station & Potable water tank & chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0048 | 2026-06-25 | Inspection of Reinforced Concrete Placement for Footings of the Potable Water Pump Station. | 1077.306 | 62.65 | 67493.2209
B3.2.03 30 00.01 | Footings for Potable water pump station & Potable water tank & chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0049 | 2026-06-25 | Inspection of Reinforced Concrete Placement for Footings of the Chlorination building. | 1077.306 | 2.75 | 2962.5915
B3.2.03 30 00.01 | Footings for Potable water pump station & Potable water tank & chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0050 | 2026-06-25 | Inspection of Reinforced Concrete Placement for Footing of the Potable Water Tank (Pit). | 1077.306 | 2.3 | 2477.8038
B3.2.03 30 00.01 | Footings for Potable water pump station & Potable water tank & chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0127 | 2026-08-19 | Survey Inspection of the Formwork and Placement of Reinforced Concrete (C35 MPa) for the Footings of Control Room and LV Room. | 1077.306 | 2.34 | 2520.896
B3.2.03 30 00.01 | Footings for Potable water pump station & Potable water tank & chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0232 | 2026-09-16 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for base of the electric trench & drain trench inside the Potable water pump station. | 1077.306 | 4.34 | 4675.508
B3.2.03 30 00.01 | Footings for Potable water pump station & Potable water tank & chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0237 | 2026-09-19 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Bottom Slab of Potable Water Tank. | 1077.306 | 303.46 | 326919.2788
B3.2.03 30 00.01 | Footings for Potable water pump station & Potable water tank & chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0322 | 2026-10-13 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for base of the electric trench inside Control Room. | 1077.306 | 0.44 | 474.0146
B3.2.03 30 00.02 | Reinforced Concrete Walls and columns for Potable water pump station & Potable water tank & chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0086 | 2026-07-27 | Survey Inspection of the Placement of Reinforced Concrete (C35 MPa) for the Potable Water Tank (Pit) up to +08.27 level, as per the attached highlighted approved drawings. | 1299.44 | 4.65 | 6042.396
B3.2.03 30 00.02 | Reinforced Concrete Walls and columns for Potable water pump station & Potable water tank & chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0087 | 2026-07-27 | Survey Inspection of the Placement of Reinforced Concrete (C35 MPa) for the Potable Water Pump Station Walls and Columns up to UGF (+9.52), as per the attached highlighted approved drawings. | 1299.44 | 63.17 | 82085.6248
B3.2.03 30 00.02 | Reinforced Concrete Walls and columns for Potable water pump station & Potable water tank & chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0091 | 2026-07-28 | Survey Inspection of the Placement of Reinforced Concrete (C35 MPa) and Formwork for the Columns (up to 9.29 Level) of Chlorination Building. | 1299.44 | 0.81 | 1052.5464
B3.2.03 30 00.02 | Reinforced Concrete Walls and columns for Potable water pump station & Potable water tank & chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0201 | 2026-09-03 | Survey Inspection of the Formwork and Placement of Reinforced Concrete (C35 MPa) for the neck column (8.920) of Control Room and LV Room. | 1299.44 | 0.65 | 844.636
B3.2.03 30 00.02 | Reinforced Concrete Walls and columns for Potable water pump station & Potable water tank & chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0279 | 2026-10-05 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the walls of electric trench inside the Potable water pump station. | 1299.44 | 2.51 | 3261.5944
B3.2.03 30 00.02 | Reinforced Concrete Walls and columns for Potable water pump station & Potable water tank & chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0319 | 2026-10-13 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the walls of Drain trench inside the Potable water pump station. | 1299.44 | 0.53 | 688.7032
B3.2.03 30 00.02 | Reinforced Concrete Walls and columns for Potable water pump station & Potable water tank & chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0324 | 2026-10-13 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for Walls of the electric trench inside Control Room. | 1299.44 | 0.53 | 688.7032
B3.2.03 30 00.04 | Slab on grade and ground beams for Potable water pump station & Chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0203-01 | 2026-09-22 | Survey Inspection of the Formwork and Placement of Reinforced Concrete (C35 MPa) for the Grade Beams (G.B.1, G.B.2 & G.B.3) of the Chlorination Building. | 1107.158 | 2.43 | 2690.3939
B3.2.03 30 00.04 | Slab on grade and ground beams for Potable water pump station & Chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0318 | 2026-10-13 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Slab on Grade of the Potable water pump station. | 1107.158 | 38.05 | 42127.3619
B3.2.03 30 00.04 | Slab on grade and ground beams for Potable water pump station & Chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0320 | 2026-10-13 | Survey Inspection of the Formwork and Placement of Reinforced Concrete (C35 MPa) for the Grade Beams (G.B.1) of the Control Room and LV Room. | 1107.158 | 4.9 | 5425.0742
B3.2.03 30 00.04 | Slab on grade and ground beams for Potable water pump station & Chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0326 | 2026-10-13 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Slab on Grade of the Chlorination Building | 1107.158 | 3.68 | 4074.3414
B3.2.07 13 13.01 | Water proofing Membrane with 50mm screed protection fc' 20MPa | DAM2-02-09-SAJ-TS9-1-STU-FIR-0032-01 | 2026-07-16 | Inspection of the Waterproofing Membrane with 50 mm Screed Protection (20 MPa) at the Potable Water Pump Station. | 128.188 | 138.75 | 17786.085
B3.2.07 13 13.01 | Water proofing Membrane with 50mm screed protection fc' 20MPa | DAM2-02-09-SAJ-TS9-1-STU-FIR-0033 | 2026-06-22 | Inspection of the Waterproofing Membrane with 50 mm Screed Protection (20 MPa) at the Chlorination Building. | 128.188 | 9.68 | 1240.8598
B3.2.07 13 13.01 | Water proofing Membrane with 50mm screed protection fc' 20MPa | DAM2-02-09-SAJ-TS9-1-STU-FIR-0034 | 2026-06-22 | Inspection of the Waterproofing Membrane with 50 mm Screed Protection (20 MPa) at the Water Tank (Pit). | 128.188 | 6.8 | 871.6784
B3.2.07 13 13.01 | Water proofing Membrane with 50mm screed protection fc' 20MPa | DAM2-02-09-SAJ-TS9-1-STU-FIR-0055 | 2026-07-05 | Inspection of the Waterproofing Membrane (4mm thick) with 50 mm Screed Protection (20 MPa) at the Potable Water Tank (Part 1). | 128.188 | 773.2 | 99114.9616
B3.2.07 13 13.01 | Water proofing Membrane with 50mm screed protection fc' 20MPa | DAM2-02-09-SAJ-TS9-1-STU-FIR-0117 | 2026-08-16 | Inspection of the Waterproofing Membrane with 50 mm Screed Protection (20 MPa) over the lean concrete at the Footings of Control Room and LV Room. | 128.188 | 7.65 | 980.6382
B3.2.07 13 13.01 | Water proofing Membrane with 50mm screed protection fc' 20MPa | DAM2-02-09-SAJ-TS9-1-STU-FIR-0292 | 2026-10-05 | Inspection of the Waterproofing Membrane with 50 mm Screed Protection (20 MPa) at the Flowmeter of Potable Water Tank. | 128.188 | 12.6 | 1615.1688
B3.2.07 13 13.02 | Water proofing Membrane with protection board | DAM2-02-09-SAJ-TS9-1-STU-FIR-0056 | 2026-07-05 | Inspection of the Waterproofing Membrane (4mm thick) with Protection board over the RC Concrete Footings of the Chlorination Building. | 80.776 | 16.1 | 1300.4936
B3.2.07 13 13.02 | Water proofing Membrane with protection board | DAM2-02-09-SAJ-TS9-1-STU-FIR-0063 | 2026-07-07 | Inspection of the Waterproofing Membrane (4mm thick) with Protection board over the RC Concrete Footings of the Potable Water Pump Station. | 80.776 | 160.64 | 12975.8566
B3.2.07 13 13.02 | Water proofing Membrane with protection board | DAM2-02-09-SAJ-TS9-1-STU-FIR-0106 | 2026-08-11 | Inspection of the Waterproofing Membrane (4mm thick) with Protection board over the RC Concrete Columns of the Chlorination Building up to 9.29m Level as per attached Approved Drawing. | 80.776 | 12.6 | 1017.7776
B3.2.07 13 13.02 | Water proofing Membrane with protection board | DAM2-02-09-SAJ-TS9-1-STU-FIR-0107 | 2026-08-11 | Inspection of the Waterproofing Membrane (4mm thick) with Protection board over the RC Concrete walls and Columns of Portable water Pump Station up to 7.570m Level as per attached Approved Drawing. | 80.776 | 258.5 | 20880.596
B3.2.07 13 13.02 | Water proofing Membrane with protection board | DAM2-02-09-SAJ-TS9-1-STU-FIR-0110 | 2026-08-11 | Inspection of the Waterproofing Membrane (4mm thick) with Protection board over the RC Concrete of Portable Water Tank (Sumpit) Footing and Walls up to 7.820m Level as per attached Approved Drawing. | 80.776 | 9 | 726.984
B3.2.07 13 13.02 | Water proofing Membrane with protection board | DAM2-02-09-SAJ-TS9-1-STU-FIR-0211 | 2026-09-09 | Inspection of the Waterproofing Membrane (4mm thick) with Protection board over the RC concrete of the Footings and Columns of Control Room and LV Room. | 80.776 | 22.35 | 1805.3436
B3.2.07 14 00.01 | Water proofing Paint below slab on grade for Potable water pump station & chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0282 | 2026-09-03 | Inspection for waterproofing paint on 50mm Lean concrete below slab on grade for potable water pump station. | 40.388 | 195.13 | 7880.9104
B3.2.07 14 00.01 | Water proofing Paint below slab on grade for Potable water pump station & chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0291 | 2026-10-05 | Inspection for waterproofing paint on the 50mm plain concrete below slab on grade of the Chlorination Building. | 40.388 | 24.48 | 988.6982
B3.2.07 26 16.01 | Vapor retarders below slab on grade for Potable water pump station & chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0280 | 2026-10-05 | Inspection for vapor retarders below 50 mm Lean concrete under slab on grade for potable water pump station. | 6.146 | 195.13 | 1199.269
B3.2.07 26 16.01 | Vapor retarders below slab on grade for Potable water pump station & chlorination | DAM2-02-09-SAJ-TS9-1-STU-FIR-0289 | 2026-10-05 | Inspection for vapor retarders below 50 mm plain concrete under slab on grade of the Chlorination Building. | 6.146 | 24.48 | 150.4541
B3.2 22 13 16 .01 | uPVC pipes with diameter 110mm. | DAM2-02-09-SAJ-TS9-1-STU-FIR-1336 | 2026-09-27 | Survey and Mechanical FIR for installation of UPVC sanitary drainage pipe for potable water pump station @ Level +7.77 @ Potable water pump station | 107.116 | 64 | 6855.424
B4.33 14 13.06 | 90mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0016 | 2026-04-26 | Survey Excavation and Compaction Testing FIR for Irrigation Pipeline TSE-3 (RD-02) from Station 1+370.230 TO 1+460.00 & 1+660 TO 1+680 @ ZONE-04 | 82.532 | 10.98 | 906.2014
B4.33 14 13.06 | 90mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0017 | 2026-04-26 | Survey FIR for Sand Bedding for Irrigation Pipeline TSE-3 (RD-02) from Station 1+370.230 TO 1+460.00 & 1+660 TO 1+680 @ZONE-04 | 82.532 | 5.49 | 453.1007
B4.33 14 13.06 | 90mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0031 | 2026-05-06 | Mechanical FIR for Installation and Laying of HDPE Pipe for Irrigation Pipeline TSE-3 (RD-02) from Station 1+370.230 TO 1+460.00 & 1+660 TO 1+680 @ ZONE-04 | 82.532 | 71.35 | 5888.6582
B4.33 14 13.06 | 90mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0018 | 2026-04-26 | Survey Excavation and Compaction Testing FIR for Irrigation Pipeline TSE-3 (RD-02) from Station 1+460.00 TO 1+660 & 1+680 TO 1+872.00 @ZONE-04 | 82.532 | 39.2 | 3235.2544
B4.33 14 13.06 | 90mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0019 | 2026-04-26 | Survey FIR for Sand Bedding for Irrigation Pipeline TSE-3 (RD-02) from Station 1+460.00 TO 1+660 & 1+680 TO 1+872.00@ ZONE-04 | 82.532 | 19.6 | 1617.6272
B4.33 14 13.06 | 90mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0026 | 2026-05-06 | Survey Excavation and Compaction Testing FIR for Irrigation Pipeline TSE-3 (RD-02) from Station 1+872.00 TO 1+961.642 @ZONE-04 | 82.532 | 8.96 | 739.4867
B4.33 14 13.06 | 90mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0027 | 2026-05-06 | Survey FIR for Sand Bedding of Irrigation Pipeline TSE-3 (RD-02) from Station 1+872.00 TO 1+961.642 @ZONE-04 | 82.532 | 4.48 | 369.7434
B4.33 14 13.06 | 90mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0033 | 2026-05-06 | Mechanical FIR for Installation and Laying of HDPE Pipe for Irrigation Pipeline TSE-3 (RD-02) from Station 1+460.00 TO 1+660 & 1+680 TO 1+872.00@ ZONE-04 | 82.532 | 254.8 | 21029.1536
B4.33 14 13.06 | 90mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0040 | 2026-06-30 | Survey Excavation and Compaction Testing FIR for Irrigation Pipeline TSE-3 (RD-02) from Station 1+271.99 TO 1+370.23, @ZONE-04 | 82.532 | 9.82 | 810.4642
B4.33 14 13.06 | 90mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0041-01 | 2026-09-08 | Survey Sand Bedding and Compaction Testing FIR for Irrigation Pipeline TSE-3 (RD-02) from Station 1+271.99 TO 1+370.23, @ZONE-04 | 82.532 | 4.91 | 405.2321
B4.33 14 13.06 | 90mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0045 | 2026-07-02 | Mechanical FIR for Installation and Laying off HDPE Pipe Line for Irrigation Pipeline TSE-3 (RD-02) from Station 1+271.99 TO 1+370.23, @ZONE-04 | 82.532 | 63.86 | 5270.4935
B4.33 14 13.06 | 90mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0052 | 2026-08-09 | Survey and Mechanical FIR for Installation and Laying off HDPE Irrigation Pipeline TSE-3 (RD-02) from Station 1+872.00 TO 1+961.642 @ZONE-04 | 82.532 | 58.27 | 4809.1396
B4.33 14 13.06 | 90mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0054 | 2026-08-12 | Survey Excavation and Compaction Testing FIR for Irrigation Pipeline (RD-02) from Station 0+305 TO 0+530 @ZONE-04 | 82.532 | 22.5 | 1856.97
B4.33 14 13.06 | 90mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0055 | 2026-08-12 | Survey Fir for Sand Bedding and Compaction Testing Irrigation Pipeline TSE-3 (RD-02) from Station 0+305 TO 0+530 @ZONE-04 | 82.532 | 11.25 | 928.485
B4.33 14 13.06 | 90mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0056 | 2026-08-13 | Survey and Mechanical FIR for Installation and Laying off HDPE Pipe Line for Irrigation Pipeline TSE-3 (RD-02) from Station 0+305 TO 0+530 @ZONE-04 | 82.532 | 146.25 | 12070.305
B4.33 14 13.06 | 90mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0057 | 2026-08-15 | Survey Excavation and Compaction Testing FIR for Irrigation Pipeline TSE-3 (RD-02) from Station 1+032.00 TO 1+271.99, @ZONE-04 | 82.532 | 24 | 1980.768
B4.33 14 13.06 | 90mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0058 | 2026-08-15 | Survey Sand Bedding and Compaction Testing FIR for Irrigation Pipeline TSE-3 (RD-02) from Station 1+032.00 TO 1+271.99, @ZONE-04 | 82.532 | 12 | 990.384
B4.33 14 13.06 | 90mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0059 | 2026-08-16 | Survey and Mechanical FIR for Installation and Laying of HDPE Pipeline of Irrigation Pipeline TSE-3 (RD-02) from Station 1+032.00 TO 1+271.99, @ZONE-04 | 82.532 | 155.99 | 12874.1667
B4.33 14 13.06 | 90mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0060 | 2026-08-20 | Survey Excavation and Compaction Testing FIR for Irrigation Pipeline TSE-3 (RD-02) from Station 0+262 TO 0+305 & 0+530 TO 0+790 @ZONE-04 | 82.532 | 30.3 | 2500.7196
B4.33 14 13.06 | 90mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0061 | 2026-08-20 | Survey Fir for Sand Bedding and Compaction Testing Irrigation Pipeline TSE-3 (RD-02) Station 0+262 TO 0+305 & 0+530 TO 0+790 @ZONE-04 | 82.532 | 15.15 | 1250.3598
B4.33 14 13.06 | 90mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0062 | 2026-08-22 | Survey and Mechanical FIR for Installation and Laying of HDPE Pipeline TSE-3 of Irrigation Pipeline (RD-02) Station 0+262 TO 0+305 & 0+530 TO 0+790 @ZONE-04 | 82.532 | 196.95 | 16254.6774
B4.33 14 13.06 | 90mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0063 | 2026-09-01 | Survey Excavation and Compaction Testing FIR for Irrigation Pipeline (RD-02) from Station 0+790 TO 1+032 @ZONE-04 | 82.532 | 24.2 | 1997.2744
B4.33 14 13.06 | 90mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0064 | 2026-09-01 | Survey Sand Bedding and Compaction Testing FIR for Irrigation Pipeline (RD-02) from Station 0+790 TO 1+032 @ZONE-04 | 82.532 | 12.1 | 998.6372
B4.33 14 13.06 | 90mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0065 | 2026-09-02 | Survey and Mechanical fir for Installation and laying of Irrigation Pipeline (RD-02) from Station 0+790 TO 1+032 @ZONE-04 | 82.532 | 157.3 | 12982.2836
B4.33 14 13.07 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0001 | 2026-04-05 | Survey Excavation and Compaction Testing FIR for Irrigation Pipeline TSE-2 (RD-01) from Station 0+324.00 TO 0+776.30 @ZONE-01 | 143.992 | 45.23 | 6512.7582
B4.33 14 13.07 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0002 | 2026-04-05 | Survey FIR for Sand Bedding of Irrigation Pipeline TSE-2 (RD-01) from Station 0+324.00 TO 0+776.30 @ZONE-01 | 143.992 | 22.62 | 3257.099
B4.33 14 13.07 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0004 | 2026-04-07 | Mechanical FIR for Installation and Laying of HDPE Pipe for Irrigation Network TSE-2 (RD-01) from Station 0+324.00 TO 0+776.30 @ ZONE-01 | 143.992 | 294 | 42333.648
B4.33 14 13.07 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0007 | 2026-04-09 | Survey Excavation and Compaction Testing FIR for Irrigation Pipeline TSE-2 (RD-01) from Station 0+090.00 TO 0+160 & 0+240 TO 0+282.00 @ZONE-01 | 143.992 | 11.2 | 1612.7104
B4.33 14 13.07 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0008 | 2026-04-09 | Survey FIR for Sand Bedding of Irrigation Pipeline TSE-2 (RD-01) from Station 0+090.00 TO 0+160 & 0+240 TO 0+282.00 @ZONE-01 | 143.992 | 5.6 | 806.3552
B4.33 14 13.07 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0012 | 2026-04-11 | Mechanical FIR for Installation and Laying of HDPE Pipe for Irrigation Network TSE-2 (RD-01) from Station 0+090.00 TO 0+160 & 0+240 TO 0+282.00 @ZONE-01 | 143.992 | 72.8 | 10482.6176
B4.33 14 13.07 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0013 | 2026-04-16 | Survey Excavation and Compaction Testing FIR for Irrigation Pipeline TSE-2 (RD-01) from Station 0+282.00TO 0+324.00 @ZONE-01 | 143.992 | 4.2 | 604.7664
B4.33 14 13.07 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0014 | 2026-04-16 | Survey FIR for Sand Bedding for Irrigation Pipeline TSE-2 (RD-01) from Station 0+282.00 TO 0+324.00 @ZONE-01 | 143.992 | 2.1 | 302.3832
B4.33 14 13.07 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0028 | 2026-05-06 | Survey Excavation and Compaction Testing FIR for Irrigation Pipeline TSE-3 (RD-02) from Station 1+961.642 TO 2+015.663 @ZONE-04 | 143.992 | 5.4 | 777.5568
B4.33 14 13.07 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0029 | 2026-05-06 | Survey FIR for Sand Bedding of Irrigation Pipeline TSE-3 (RD-02) from Station 1+961.642 TO 2+015.663 @ZONE-04 | 143.992 | 2.7 | 388.7784
B4.33 14 13.07 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0005 | 2026-04-09 | Survey Excavation and Compaction Testing FIR for Irrigation Pipeline TSE-2 (RD-01) from Station 0+160 TO 0+240 @ZONE-01 | 143.992 | 8 | 1151.936
B4.33 14 13.07 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0006 | 2026-04-09 | Survey FIR for Sand Bedding of Irrigation Pipeline TSE-2 (RD-01) from Station 0+160 TO 0+240 @ZONE-01 | 143.992 | 4 | 575.968
B4.33 14 13.07 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0011 | 2026-04-11 | Mechanical FIR for Installation and Laying of HDPE Pipe for Irrigation Network TSE-2 (RD-01) from Station 0+160 TO 0+240 @ZONE-01 | 143.992 | 52 | 7487.584
B4.33 14 13.07 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0038 | 2026-06-30 | Survey Excavation and Compaction Testing FIR for Irrigation Pipeline TSE-3 (RD-02) from Station 2+015.663 TO 2+040.00, @ZONE-04 | 143.992 | 2.43 | 349.9006
B4.33 14 13.07 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0039-01 | 2026-09-08 | Survey Sand Bedding and Compaction Testing FIR for Irrigation Pipeline TSE-3 (RD-02) from Station 2+015.663 TO 2+040.00, @ZONE-04 | 143.992 | 1.22 | 175.6702
B4.33 14 13.07 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0044 | 2026-07-02 | Mechanical FIR for Installation and Laying off HDPE Pipe Line for Irrigation Pipeline TSE-3 (RD-02) from Station 2+015.663 TO 2+040.00, @ZONE-04 | 143.992 | 15.82 | 2277.9534
B4.33 14 13.07 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0051 | 2026-08-09 | Survey and Mechanical FIR for Installation and Laying off HDPE Irrigation Pipeline TSE-2 (RD-01) from Station 0+282.00TO 0+324.00 @ZONE-01 | 143.992 | 27.3 | 3930.9816
B4.33 14 13.07 | 110mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0053 | 2026-08-09 | Survey and Mechanical FIR for Installation and Laying off HDPE Irrigation Pipeline TSE-3 (RD-02) from Station 1+961.642 TO 2+015.663 @ZONE-04 | 143.992 | 35.11 | 5055.5591
B4.33 14 13.08 | 125mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0035 | 2026-05-23 | Survey and Compaction FIR for Excavation, Bedding and Pipe Installation Irrigation Pipeline TSE-1 (Entrance RD1) to close out the verification of NCR# 18 from Station 0+125.351 TO 0+450.00, @ZONE-02 | 154.528 | 48.7 | 7525.5136
B4.33 14 13.08 | 125mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-IRR-FIR-0036 | 2026-06-06 | Mechanical FIR for Installation and Laying off Irrigation Pipeline TSE-1 (Entrance RD1) from Station 0+125.351 TO 0+450.00, @ZONE-02 | 154.528 | 211.02 | 32608.4986
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0013-00 | 2025-12-17 | Survey Excavation and compaction test FIR for sewerage Pipe line from MH-B- 33/1 TO MH-B- 33/0 LINE B @ ZONE-01 (Length :30.40 m) | 226.524 | 4.38 | 992.1751
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0021-00 | 2025-12-21 | Survey Gravel Bedding FIR for sewerage Pipe line from MH-B- 33/1 TO MH-B- 33/0, LINE B @ ZONE-01 (Length: 28.60 m) | 226.524 | 1.43 | 323.9293
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0024-01 | 2025-12-25 | Survey FIR for Installation and Laying of Sewerage Pipeline plot connection for MH-B-33/1 & MH-B-33/0 Line B @ Zone-1 DIA 150mm | 226.524 | 17.16 | 3887.1518
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0035-00 | 2025-12-23 | Survey Excavation and Compaction Test FIR of the Sewerage Pipe Line from MH-B-39 TO MH-B-40, LINE B @ ZONE-01 | 226.524 | 5.83 | 1320.6349
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0036-00 | 2025-12-23 | Survey Sand Bedding FIR of Sewerage Pipe Line from MH-B39 TO MH-B-40, LINE B @ ZONE-01 | 226.524 | 1.94 | 439.4566
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0056-00 | 2026-01-04 | Mechanical FIR Installation and Laying of Sewerage Pipe line fromMH-B-40 TO MH-B-39 | 226.524 | 23.31 | 5280.2744
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0057-00 | 2026-01-04 | Mechanical FIR for initial Air Test of GRP Sewerage Pipe Line form MH-B-40 TO MH-B-39 | 226.524 | 1.94 | 439.4566
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0046-00 | 2025-12-27 | Survey Excavation and Compaction Testing FIR of Sewerage Pipe Line from MH-B-26-2 TO MH-B-26-1, LINE B @ ZONE-01 | 226.524 | 7.79 | 1764.622
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0050-00 | 2025-12-29 | Survey FIR for Geotextile & Gravel Bedding FIR for sewerage Pipe line from MH-B- 26-2 TO MH-B- 26-1, LINE B @ ZONE-01 | 226.524 | 2.6 | 588.9624
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0069-00 | 2026-01-05 | Mechanical FIR Installation and Laying of Sewerage for Pipe Line form MH-B-26-1 TO MH-B-26-2 Pipe DIA 150MM | 226.524 | 31.16 | 7058.4878
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0070-00 | 2026-01-05 | Mechanical FIR initial Air Test of Sewerage for Pipe Line form MH-B-26-1 TO MH-B-26-2 Pipe DIA 150MM | 226.524 | 2.6 | 588.9624
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0078-00 | 2026-01-07 | Survey Excavation and Compaction Testing FIR of Sewerage Pipe Line from MH-B-36-0 TO MH-B-36/1, LINE B @ ZONE-01 | 226.524 | 4.29 | 971.788
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0091-00 | 2026-01-10 | Survey Sand Bedding FIR of Sewerage Pipe Line from MH-B36/0 TO MH-B-36/1, LINE B @ ZONE-01 | 226.524 | 1.43 | 323.9293
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0096-00 | 2026-01-10 | Mechanical FIR Installation and Laying of Sewerage for Pipe Line form MH-B-36/0 TO MH-B-36/1 Pipe DIA 200MM | 226.524 | 17.16 | 3887.1518
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0097-00 | 2026-01-10 | Mechanical FIR initial Air Test of Sewerage for Pipe Line form MH-B-36/0 TO MH-B-36/1, Line B Pipe DIA 200MM | 226.524 | 1.43 | 323.9293
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0081-00 | 2026-01-08 | Mechanical FIR initial Air Test of Sewerage for Pipe Line form MH-B-33/0 TO MH-B-33/1 Pipe DIA 150MM, Line B @ ZONE-01 | 226.524 | 1.43 | 323.9293
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0090-00 | 2026-01-10 | Survey Excavation and Compaction Testing FIR of Sewerage Pipe Line from MH-B-31-0 TO MH-B-31/1, LINE B @ ZONE-01 | 226.524 | 4.29 | 971.788
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0106-00 | 2026-01-12 | Civil FIR for Backfill and Compaction Test 2nd Layer of Sewerage Network from MH-B-33/0 TO MH-B-33/1, LINE B @ZONE-01 Pipe DIA 150MM (Thickness 30cm) | 226.524 | 1.43 | 323.9293
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0107-00 | 2026-01-13 | Civil FIR for Backfill and Compaction Test 2nd Layer of Sewerage Network from MH-B-33/0 TO MH-B-33/1, LINE B @ZONE-01 Pipe DIA 150MM (Thickness 30cm) | 226.524 | 1.42 | 321.6641
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0109-00 | 2026-01-13 | Survey Sand Bedding FIR of Sewerage Pipe Line from MH-B31/0 TO MH-B-31/1, LINE B @ ZONE-01 | 226.524 | 16.98 | 3846.3775
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0122-00 | 2026-01-14 | Mechanical FIR initial Air Test of Sewerage for Pipe Line form MH-B-31/0 TO MH-B-31/1, Line B Pipe DIA 150MM | 226.524 | 1.42 | 321.6641
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0129-00 | 2026-01-15 | Survey FIR for Backfill and Compaction Testing 2ndLayer above the Sewerage Pipeline from MH-B-31/0 TO MH-B-31/1, LINE B @ ZONE-01 | 226.524 | 1.42 | 321.6641
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0130-00 | 2026-01-17 | Survey FIR for Backfill and Compaction Testing 3rd Layer above the Sewerage Pipeline from MH-B-31/0 TO MH-B-31/1, LINE B @ ZONE-01 | 226.524 | 1.42 | 321.6641
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0137-00 | 2026-01-19 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-28/0 TO MH-B-28/1, LINE B @ ZONE-01 | 226.524 | 4.23 | 958.1965
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0140-00 | 2026-01-20 | Survey FIR for Sand Bedding of Sewerage Pipeline from MH-B-28/0 TO MH-B-28/1, LINE B @ ZONE-01 | 226.524 | 1.41 | 319.3988
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0190-00 | 2026-01-29 | Mechanical FIR for Installation and Laying of Sewerage Pipeline form MH-B-28/0 TO MH-B-28/1, LINE B @ ZONE-01 Pipe DIA 150MM | 226.524 | 16.92 | 3832.7861
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0212-00 | 2026-02-01 | Mechanical FIR Initial Air Test of Sewerage Pipeline form MH-B-28/0 TO MH-B-28/1, Line B @ ZONE-01 Pipe DIA 150MM | 226.524 | 1.41 | 319.3988
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0184-00 | 2026-01-29 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-28 TO MH-A-27/0, LINE A @ ZONE-04 | 226.524 | 9.38 | 2124.7951
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0194-00 | 2026-01-31 | Survey FIR for Sand Bedding of Sewerage Pipeline from MH-A-28 TO MH-A-27, LINE A @ ZONE-04 | 226.524 | 3.13 | 709.0201
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0201-00 | 2026-01-31 | Mechanical FIR for Installation and Laying of Sewerage Pipeline form MH-A-28 TO MH-A-27/0, LINE A @ ZONE-04 Pipe DIA 150MM | 226.524 | 37.51 | 8496.9152
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0213-00 | 2026-02-01 | Mechanical FIR Initial Air Test of Sewerage Pipeline form MH-A-28 TO MH-A-27, Line A @ ZONE-04 Pipe DIA 150MM | 226.524 | 3.13 | 709.0201
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0252-00 | 2026-02-10 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-4-2-4 TO MH-B-4-2-3, LINE B @ ZONE-03 | 226.524 | 7.49 | 1696.6648
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0253-00 | 2026-02-10 | Survey FIR for Sand Bedding of Sewerage Pipeline from MH-B-4-2-4 TO MH-B-4-2-3 , LINE B @ ZONE-03 | 226.524 | 2.5 | 566.31
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0265-00 | 2026-02-14 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-B-4-2-4 TO MH-B-4-2-3, LINE B @ ZONE-01 Pipe DIA 150MM | 226.524 | 29.96 | 6786.659
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0268-00 | 2026-02-15 | Mechanical FIR Initial Air Test of Sewerage Pipeline form MH-4-2-4 TO MH-4-2-3, LINE B @ ZONE-03 Pipe DIA 150MM | 226.524 | 2.5 | 566.31
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0350-00 | 2026-03-17 | Survey FIR for Backfill and Compaction Testing 3rd Layer above the Sewerage Pipeline from MH-B-4-2-4 TO MH-B-4-2-3, @ZONE-03 | 226.524 | 4.99 | 1130.3548
B5.33 31 00.01.01 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0438-00 | 2026-04-05 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-14-5/1 TO MH-A-14-5/0, @ ZONE-04 | 226.524 | 4.38 | 992.1751
B5.33 31 00.01.01 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0439-00 | 2026-04-05 | Survey FIR for Sand Bedding of Sewerage Pipeline from MH-A-14-5/1 TO MH-A-14-5/0, @ ZONE-04 | 226.524 | 1.46 | 330.725
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0509-00 | 2026-04-19 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-2-3 TO MH-A-2-4, @ ZONE-03 | 226.524 | 1.5 | 339.786
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0513-00 | 2026-04-19 | Survey FIR for Sand Bedding of Sewerage Pipeline from MH-A-2-3 TO MH-A-2-4, @ ZONE-03 | 226.524 | 0.5 | 113.262
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0655-00 | 2026-05-05 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-2-3 TO MH-A-2-4, @ ZONE-03 | 226.524 | 5.99 | 1356.8788
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0687-00 | 2026-05-11 | Survey FIR for Backfill and Compaction Testing 2nd Layer above the Sewerage Pipeline from MH-A-2-3 TO MH-A-2-4, @ ZONE-03 | 226.524 | 0.5 | 113.262
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0718-00 | 2026-05-13 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-22-2 TO MH-B-22-1, @ ZONE-02 | 226.524 | 1.84 | 416.8042
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0729-00 | 2026-05-13 | Survey FIR for Backfill and Compaction Testing 4th Layer above the Sewerage Pipeline from MH-A-2-3 TO MH-A-2-4, @ ZONE-03 | 226.524 | 0.5 | 113.262
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0781-00 | 2026-05-20 | Survey FIR for Sand Bedding of Sewerage Pipeline from MH-B-22-2 TO MH-B-22-1, @ ZONE-02 | 226.524 | 0.61 | 138.1796
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0923-00 | 2026-06-13 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-14-5/1 TO MH-A-14-5/0, @ ZONE-04 | 226.524 | 17.52 | 3968.7005
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0939 | 2026-06-15 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-27-1 TO MH-A-27/0, @ ZONE-04 | 226.524 | 4.38 | 992.1751
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0940 | 2026-06-15 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-25-1 TO MH-A-25/0, @ ZONE-04 | 226.524 | 4.38 | 992.1751
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0942 | 2026-06-15 | Survey FIR for Sand Bedding and Compaction Testing of Sewerage Pipeline from MH-A-27-1 TO MH-A-27/0, @ ZONE-04 | 226.524 | 1.46 | 330.725
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0943 | 2026-06-15 | Survey FIR for Sand Bedding and Compaction Testing of Sewerage Pipeline from MH-A-25-1 TO MH-A-25/0, @ ZONE-04 | 226.524 | 1.46 | 330.725
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0945 | 2026-06-16 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-18-5-1 TO MH-A-18-5/0, @ ZONE-04 | 226.524 | 4.38 | 992.1751
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0946 | 2026-06-16 | Survey FIR for Sand Bedding and Compaction Testing of Sewerage Pipeline from MH-A-18-5-1 TO MH-A-18-5/0, @ ZONE-04 | 226.524 | 1.46 | 330.725
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0954 | 2026-06-16 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-25-1 TO MH-A-25/0, @ ZONE-04 | 226.524 | 17.52 | 3968.7005
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0956 | 2026-06-16 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-27-1 TO MH-A-27/0, @ ZONE-04 | 226.524 | 17.52 | 3968.7005
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0965 | 2026-06-17 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-10-6 TO MH-A-10-5/0, @ ZONE-04 | 226.524 | 8.53 | 1932.2497
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0966 | 2026-06-17 | Survey FIR for Sand Bedding and Compaction Testing of Sewerage Pipeline from MH-A-10-6 TO MH-A-10-5/0, @ ZONE-04 | 226.524 | 2.84 | 643.3282
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0970 | 2026-06-17 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-18-5-1 TO MH-A-18-5/0, @ ZONE-04 | 226.524 | 17.52 | 3968.7005
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0976 | 2026-06-18 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-10-6 TO MH-A-10-5/0, @ ZONE-04 | 226.524 | 34.13 | 7731.2641
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0996 | 2026-06-20 | Survey FIR for Backfill and Compaction Testing 2nd Layer above the Sewerage Pipeline MH-A-18-5-1 TO MH-A-18-5/0, ZONE-04 | 226.524 | 1.46 | 330.725
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0998 | 2026-06-20 | Survey FIR for Backfill and Compaction Testing 2nd Layer above the Sewerage Pipeline MH-A-14-5/1 TO MH-A-14-5/0, ZONE-04 | 226.524 | 1.46 | 330.725
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1000 | 2026-06-20 | Survey FIR for Backfill and Compaction Testing 2nd Layer above the Sewerage Pipeline from MH-A-10-6 TO MH-A-10-5/0, ZONE-04 | 226.524 | 2.84 | 643.3282
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1197 | 2026-08-17 | Survey FIR for Backfill and Compaction Testing 2nd Layer above the Sewerage Pipeline from MH-A-28 TO MH-A-27/0 @ ZONE-04 | 226.524 | 3.13 | 709.0201
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1292 | 2026-09-01 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-10-5-1 TO MH-A-10-5-0 | 226.524 | 4.38 | 992.1751
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1293 | 2026-09-01 | Survey FIR for Sand Bedding and Compaction Testing of Sewerage Pipeline from MH-A-10-5-1 TO MH-A-10-5-0 | 226.524 | 1.46 | 330.725
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1295 | 2026-09-02 | Survey and Mechanical FIR for Installation and laying of Sewerage Pipeline from MH-A-10-5-1 TO MH-A-10-5-0 | 226.524 | 17.52 | 3968.7005
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1300 | 2026-09-09 | Survey FIR for Backfill and Compaction Testing 2nd Layer above the Sewerage Pipeline from MH-B-39 TO MH-B-40 dia 150 mm MH-B-28 TO MH-B-28-1 dia 150 mm MH-B-36 TO MH-B-36-1 dia 150mm @ ZONE-01 | 226.524 | 5.55 | 1257.2082
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1302 | 2026-09-09 | Survey FIR for Backfill and Compaction Testing 3rd Layer above the Sewerage Pipeline from MH-B-26-1 TO MH-B-26-2, dia 150 mm @ ZONE-01 | 226.524 | 5.25 | 1189.251
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1307-01 | 2026-10-07 | Survey FIR for Backfill and Compaction Testing 4th Layer above the Sewerage Pipeline from MH-B-39 TO MH-B-40 dia 150 mm MH-B-28 TO MH-B-28-1 dia 150 mm MH-B-36 TO MH-B-36-1 dia 150mm @ ZONE-01 | 226.524 | 4.24 | 960.4618
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1323 | 2026-09-21 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-18-5-1 to MH-A-18-5/0, dia 150 mm ZONE-04 | 226.524 | 2.92 | 661.4501
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1331 | 2026-09-26 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-14-5 to MH-A-14-5-1, dia 150 mm MH-A-18-5/0 to MH-A-18-5-1, dia 150 mm duplicate in FIR # 1323 ZONE-04 | 226.524 | 2.92 | 661.4501
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1332 | 2026-09-26 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-B-36/0 to MH-B-36-1, dia 150 mm ZONE-01 | 226.524 | 1.46 | 330.725
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1335 | 2026-09-27 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-B-31-0 to MH-B-31-1 @ RD-1 , ZONE-01 | 226.524 | 1.41 | 319.3988
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1352 | 2026-09-28 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-27-0 to MH-A-27-1 @ RD-3 , ZONE-04 | 226.524 | 2.92 | 661.4501
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1364 | 2026-10-01 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-25-0 to MH-A-25-1 RD-02 - ZONE-04 | 226.524 | 2.92 | 661.4501
B5.33 31 00.01.01 | 150mm Diameter Depth: 0.0m - 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1425 | 2026-10-19 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-10-5 to MH-A-10-5-1 Road-2 , ZONE- 04 | 226.524 | 2.92 | 661.4501
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0365-00 | 2026-03-25 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-10-1-1 TO MH-A-10-1/0, @ ZONE-04 | 287.106 | 4.23 | 1214.4584
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0366-00 | 2026-03-25 | Survey FIR for Sand Bedding of Sewerage Pipeline from MH-A-10-1-1 TO MH-A-10-1/0, @ ZONE-04 | 287.106 | 1.41 | 404.8195
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0380-00 | 2026-03-26 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-10-1-1 TO MH-A-10-1/0 @ ZONE-04, Pipe DIA 150mm | 287.106 | 16.92 | 4857.8335
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0370-00 | 2026-03-25 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-12-2/0 TO MH-B-12-1, @ ZONE-03 | 287.106 | 6.79 | 1949.4497
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0381-00 | 2026-03-26 | Survey FIR for Sand Bedding of Sewerage Pipeline from MH-B-12-2/0 TO MH-B-12-1, @ ZONE-03Survey | 287.106 | 2.26 | 648.8596
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0383-00 | 2026-03-26 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-B-12-2/0 TO MH-B-12-1, @ ZONE-03 | 287.106 | 27.15 | 7794.9279
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0426-00 | 2026-04-04 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-14-5/0 TO MH-A-14-4, @ ZONE-04 | 287.106 | 6.79 | 1949.4497
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0428-00 | 2026-04-04 | Survey FIR for Sand Bedding of Sewerage Pipeline from MH-A-14-5/0 TO MH-A-14-4, @ ZONE-04 | 287.106 | 2.26 | 648.8596
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0436-00 | 2026-04-05 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-14-5/0 TO MH-A-14-4, @ ZONE-04 | 287.106 | 31.63 | 9081.1628
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0530-00 | 2026-04-21 | Mechanical FIR Initial Air Test of Sewerage Pipeline form MH-A-14-5/0 TO MH-A-14-4, LINE A @ ZONE-04 | 287.106 | 2.64 | 757.9598
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0440-00 | 2026-04-05 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-14-3/1 TO MH-A-14-3/0, @ ZONE-04 | 287.106 | 4.38 | 1257.5243
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0441-00 | 2026-04-05 | Survey FIR for Sand Bedding of Sewerage Pipeline from MH-A-14-3/1 TO MH-A-14-3/0, @ ZONE-04 | 287.106 | 1.46 | 419.1748
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0442-00 | 2026-04-05 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-18-5/0 TO MH-A-18-4, @ ZONE-04 | 287.106 | 7.77 | 2230.8136
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0443-00 | 2026-04-05 | Survey FIR for Sand Bedding of Sewerage Pipeline from MH-A-18-5/0 TO MH-A-18-4, @ ZONE-04 | 287.106 | 2.59 | 743.6045
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0893-00 | 2026-06-10 | Survey FIR for Backfill and Compaction Testing 4th Layer above the Sewerage Pipeline from MH-A-10-1-1 TO MH-A-10-1/0, ZONE-04 | 287.106 | 1.41 | 404.8195
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0918-00 | 2026-06-13 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-14-1-1 TO MH-A-14-1/0, @ ZONE-04 | 287.106 | 4.38 | 1257.5243
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0919-00 | 2026-06-13 | Survey FIR for Sand Bedding and Compaction Testing of Sewerage Pipeline from MH-A-14-1-1 TO MH-A-14-1/0, @ ZONE-04 | 287.106 | 1.46 | 419.1748
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0921-00 | 2026-06-13 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-14-3/1 TO MH-A-14-3/1, @ ZONE-04 | 287.106 | 17.52 | 5030.0971
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0941 | 2026-06-15 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-23-1 TO MH-A-23/0, @ ZONE-04 | 287.106 | 4.38 | 1257.5243
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0944 | 2026-06-15 | Survey FIR for Sand Bedding and Compaction Testing of Sewerage Pipeline from MH-A-23-1 TO MH-A-23/0, @ ZONE-04 | 287.106 | 1.46 | 419.1748
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0947 | 2026-06-16 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-18-3-1 TO MH-A-18-3/0, @ ZONE-04 | 287.106 | 4.38 | 1257.5243
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0948 | 2026-06-16 | Survey FIR for Sand Bedding and Compaction Testing of Sewerage Pipeline from MH-A-18-3-1 TO MH-A-18-3/0, @ ZONE-04 | 287.106 | 1.46 | 419.1748
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0950 | 2026-06-16 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-14-1-1 TO MH-A-14-1/0, @ ZONE-04 | 287.106 | 17.52 | 5030.0971
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0952 | 2026-06-16 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-23-1 TO MH-A-23/0, @ ZONE-04 | 287.106 | 17.52 | 5030.0971
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0968 | 2026-06-17 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-18-3-1 TO MH-A-18-3/0, @ ZONE-04 | 287.106 | 17.52 | 5030.0971
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0978 | 2026-06-20 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-18-5/0 TO MH-A-18-4, @ ZONE-04 | 287.106 | 31.08 | 8923.2545
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0991 | 2026-06-20 | Survey FIR for Excavation and Compaction Testing of the Sewerage Pipeline from MH-A-18-1-1 TO MH-A-18-1/0, ZONE-04 | 287.106 | 4.38 | 1257.5243
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0994 | 2026-06-20 | Survey FIR for Sand Bedding and Compaction Testing of the Sewerage Pipeline MH-A-18-1-1 TO MH-A-18-1/0, ZONE-04 | 287.106 | 1.46 | 419.1748
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1002 | 2026-06-21 | Mechanical FIR for Installation and Laying off the Sewerage Pipeline from MH-A-18-1-1 TO MH-A-18-1/0, ZONE-04 | 287.106 | 17.53 | 5032.9682
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1085 | 2026-07-19 | Survey FIR for Backfill and Compaction Testing 3rd Layer above the Sewerage Pipeline MH-A-18-5/0 TO MH-A-18-4, ZONE-04 | 287.106 | 2.59 | 743.6045
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1117 | 2026-07-25 | Survey FIR for Backfill and Compaction Testing Final Layer Prior to Capping Layer above the Sewerage Pipeline MH-A-18-5/0 TO MH-A-18-4, ZONE-04 | 287.106 | 2.59 | 743.6045
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1208 | 2026-08-18 | Survey FIR for Backfill and Compaction Testing 3rd Layer above the Sewerage Pipeline from MH-A-14-5/0 TO MH-A-14-4 @ ZONE-04 | 287.106 | 2.64 | 757.9598
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1215 | 2026-08-18 | Survey FIR for Backfill and Compaction Testing 4th Layer above the Sewerage Pipeline from MH-A-14-1-1 TO MH-A-14-1/0 @ ZONE-04 | 287.106 | 1.46 | 419.1748
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1304 | 2026-09-10 | FIR for Excavation for the Sewerage Pipeline from MH-A-10-3-1 TO MH-A-10-3/0 @ ZONE-04 | 287.106 | 4.23 | 1214.4584
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1305 | 2026-09-10 | FIR for SAND BEDDING for the Sewerage Pipeline from MH-A-10-3-1 TO MH-A-10-3/0 @ ZONE-04 | 287.106 | 1.41 | 404.8195
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1309 | 2026-09-12 | Survey and mechanical FIR for Pipe installation for the Sewerage pipe line From MH-A-10-3-1 TO MH-A-10-3/0 @ ZONE-04 | 287.106 | 16.93 | 4860.7046
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1310 | 2026-09-13 | Survey FIR for Backfill and Compaction Testing 6th Layer above the Sewerage Pipeline from MH-B-23 TO MH-B-24, dia 200 mm MH-B-29 TO MH-B-30, dia 200 mm MH-B-30 TO MH-B-31, dia 200 mm MH-B-31 TO MH-B-32, dia 200 mm @ ZONE-01 | 287.106 | 2.75 | 789.5415
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1322 | 2026-09-21 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-18-3/0 to MH-A-18-3-1, dia 150 mm ZONE-04 | 287.106 | 2.92 | 838.3495
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1334 | 2026-09-27 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-14-3 to MH-A-14-3-1 @ RD-4 , ZONE-04 | 287.106 | 2.92 | 838.3495
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1337 | 2026-09-28 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-18-1-0 to MH-A-18-1-1 @ RD-3 , ZONE-04 | 287.106 | 2.92 | 838.3495
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1363 | 2026-09-30 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-14-1 to MH-A-14-1-1 ZONE-04 | 287.106 | 2.92 | 838.3495
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1365 | 2026-10-14 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-10-1-0 to MH-A-10-1-1 RD-02 - ZONE-04 | 287.106 | 2.82 | 809.6389
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1368 | 2026-10-05 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-18-4 to MH-A-18-5 RD-03 - ZONE-01 | 287.106 | 5.18 | 1487.2091
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1369 | 2026-10-05 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-14-4 to MH-A-14-5 RD-04 - ZONE-01 | 287.106 | 2.64 | 757.9598
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1381 | 2026-10-08 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-23 to MH-A-23-1 Road-4 , ZONE- 04 | 287.106 | 2.92 | 838.3495
B5.33 31 00.01.02 | 150mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1422 | 2026-10-18 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-10-3-1 to MH-A-10-3 Road-2 , ZONE- 04 | 287.106 | 2.82 | 809.6389
B5.33 31 00.02.01 | 200mm Diameter depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0003-00 | 2025-12-10 | Excavation and Compaction FIR for sewerage Pipe line from MH-B-34 TO MH MH-B- 33, LINE 01 @ ZONE-01. | 278.326 | 4.914 | 1367.694
B5.33 31 00.02.01 | 200mm Diameter depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0006-01 | 2025-12-16 | Gravel Bedding for sewerage Pipe line from MH-B- 34 TO MH-B- 33, LINE 01 @ ZONE-01 | 278.326 | 2.457 | 683.847
B5.33 31 00.02.01 | 200mm Diameter depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0010-01 | 2025-12-22 | Pipe installation FIR for sewerage Pipe line from MH-B-34 TO MH-B- 33/0 , LINE B @ ZONE-01 length : 103.79 m -DIA 200 mm | 278.326 | 29.484 | 8206.1638
B5.33 31 00.02.01 | 200mm Diameter depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0076-00 | 2026-01-07 | Mechanical FIR initial Air Test of Sewerage for Pipe Line form MH-B-34 TO MH-B-33/0 Pipe DIA 200MM | 278.326 | 2.43 | 676.3322
B5.33 31 00.02.01 | 200mm Diameter depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0415-00 | 2026-04-02 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-4-6-6 TO MH-B-4-6-5, @ ZONE-02 | 278.326 | 7.74 | 2154.2432
B5.33 31 00.02.01 | 200mm Diameter depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0416-00 | 2026-04-02 | Survey FIR for Sand Bedding of Sewerage Pipeline from MH-B-4-6-6 TO MH-B-4-6-5, @ ZONE-02 | 278.326 | 2.58 | 718.0811
B5.33 31 00.02.01 | 200mm Diameter depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0435-00 | 2026-04-05 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-B-4-6-6 TO MH-B-4-6-5@ ZONE-02 | 278.326 | 30.97 | 8619.7562
B5.33 31 00.02.01 | 200mm Diameter depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0508-00 | 2026-04-19 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-2-2 TO MH-A-2-3, @ ZONE-03 | 278.326 | 4.7 | 1308.1322
B5.33 31 00.02.01 | 200mm Diameter depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0512-00 | 2026-04-19 | Survey FIR for Sand Bedding of Sewerage Pipeline from MH-A-2-2 TO MH-A-2-3, @ ZONE-03 | 278.326 | 1.57 | 436.9718
B5.33 31 00.02.01 | 200mm Diameter depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0654-00 | 2026-05-05 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-2-2 TO MH-A-2-3, @ ZONE-03 | 278.326 | 18.79 | 5229.7455
B5.33 31 00.02.01 | 200mm Diameter depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0719-00 | 2026-05-13 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-22-1 TO MH-B-22-0, @ ZONE-02 | 278.326 | 4.95 | 1377.7137
B5.33 31 00.02.01 | 200mm Diameter depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0722-00 | 2026-05-13 | Survey FIR for Backfill and Compaction Testing 3rd Layer above the Sewerage Pipeline from MH-A-2-2 TO MH-A-2-3, @ ZONE-03 | 278.326 | 1.56 | 434.1886
B5.33 31 00.02.01 | 200mm Diameter depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0782-00 | 2026-05-20 | Survey FIR for Sand Bedding of Sewerage Pipeline from MH-B-22-1 TO MH-B-22-0, @ ZONE-02 | 278.326 | 1.65 | 459.2379
B5.33 31 00.02.01 | 200mm Diameter depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1302 | 2026-09-09 | Survey FIR for Backfill and Compaction Testing 3rd Layer above the Sewerage Pipeline from MH-B-29 TO MH-B-30 dia 200 mm MH-B-33 TO MH-B-34 dia 200 mm @ ZONE-01 | 278.326 | 2.46 | 684.682
B5.33 31 00.02.01 | 200mm Diameter depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1307-01 | 2026-10-07 | Survey FIR for Backfill and Compaction Testing 4th Layer above the Sewerage Pipeline from MH-B-29 TO MH-B-30, dia 200 mm MH-B-33 TO MH-B-34, dia 200 mm MH-B-34 TO MH-B-35, dia 200 mm MH-B-35 TO MH-B-36, dia 200 mm MH-B-36 TO MH-B-37, dia 200 mm MH-B-37 TO MH-B-38, dia 200 mm MH-B-38 TO MH-B-39, dia 200 mm MH-B-39 TO MH-B-40 dia 150 mm MH-B-28 TO MH-B-28-1 dia 150 mm MH-B-36 TO MH-B-36-1 dia 150mm @ ZONE-01 | 278.326 | 2.46 | 684.682
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0003-00 | 2025-12-10 | Excavation and Compaction FIR for sewerage Pipe line from MH-B- 35 TO MH MH-B- 34 LINE 01 @ ZONE-01 | 338.03 | 5.465 | 1847.3339
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0006-01 | 2025-12-16 | Gravel Bedding for sewerage Pipe line from MH-B- 35 TO MH-B- 34, LINE 01 @ ZONE-01 | 338.03 | 2.733 | 923.836
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0007-00 | 2025-12-10 | Excavation and Compaction Test FIR for sewerage Pipe Line Trench from MH-B- 36/0 TO MH-B- 35, LINE B @ ZONE-01 (Length: 52.90 m) | 338.03 | 7.843 | 2651.1693
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0009-01 | 2025-12-22 | Sand Bedding FIR for sewerage Pipe line from MH-B- 35 TO MH-B- 36, LINE B @ ZONE-01 (length: 52.90 m)-DIA 200 mm | 338.03 | 2.62 | 885.6386
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0010-01 | 2025-12-22 | Pipe installation FIR for sewerage Pipe line from MH-B- 35 TO MH-B- 34 LINE B @ ZONE-01 DIA 200 mm | 338.03 | 32.79 | 11084.0037
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0011-01 | 2025-12-22 | Pipe installation FIR for sewerage Pipe line from MH-B- 35 TO MH-B- 36 LINE B @ ZONE-01 (Length: 52.90 m)-DIA 200 mm | 338.03 | 31.38 | 10607.3814
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0012-01 | 2025-12-22 | Survey Excavation & FDT FIR for sewerage Pipe line from MH-B- 33/0 TO MH-B- 32 LINE B @ ZONE-01 (Length: 72.10 m) | 338.03 | 10.73 | 3627.0619
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0018-00 | 2025-12-21 | Survey Gravel Bedding FIR for sewerage Pipe line from MH-B-33/0 TO MH-B-32 LINE B @ ZONE-01 (Length: 73.30 m) | 338.03 | 3.58 | 1210.1474
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0023-00 | 2025-12-21 | Survey FIR For Installation and Laying of Sewerage Pipe line from MH-B- 33/0 TO MH-B- 32, LINE B @ ZONE-01 | 338.03 | 42.9 | 14501.487
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0025-00 | 2025-12-21 | Survey Excavation and Compaction Test FIR for Sewerage Pipeline from MH-B-36/0 TO MH-B-37, Line B @ ZONE-01 | 338.03 | 10.89 | 3681.1467
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0031-00 | 2025-12-22 | Survey FIR for Sand Bedding of Sewerage Pipe Line from MH-B37 TO MH-B-36/0, LINE B @ ZONE-01 | 338.03 | 3.63 | 1227.0489
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0033-00 | 2025-12-23 | Survey Excavation and Compaction Test FIR of the Sewerage Pipe Line from MH-B-37 TO MH-B-39, LINE B @ ZONE-01 | 338.03 | 11.1 | 3752.133
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0034-00 | 2025-12-23 | Survey Sand Bedding FIR of Sewerage Pipe Line from MH-B37 TO MH-B-39, LINE B @ ZONE-01 | 338.03 | 3.7 | 1250.711
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0039-00 | 2025-12-23 | Mechanical FIR Installation and Laying of Sewerage Pipe line from MH-B- 36 TO MH-B- 37, LINE B @ ZONE-01 | 338.03 | 43.54 | 14717.8262
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0038-00 | 2025-12-23 | Survey Excavation and Compaction Testing FIR of Sewerage Pipe Line from MH-B-31/0 TO MH-B-30, LINE B @ ZONE-01 | 338.03 | 8.75 | 2957.7625
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0040-00 | 2025-12-24 | Survey Excavation and Compaction Testing FIR of Sewerage Pipe Line from MH-B-31/0 TO MH-B-30, LINE B @ ZONE-01 | 338.03 | 2.92 | 987.0476
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0064-00 | 2026-01-04 | Mechanical FIR Installation and Laying of Sewerage for Pipe Line form MH-B-31TO MH-B-30 Pipe DIA 200MM | 338.03 | 34.99 | 11827.6697
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0074-00 | 2026-01-06 | Mechanical FIR initial Air Test of Sewerage for Pipe Line form MH-B-31 TO MH-B-30 Pipe DIA 200MM | 338.03 | 2.92 | 987.0476
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0041-00 | 2025-12-24 | Survey Excavation and Compaction Testing FIR of Sewerage Pipe Line from MH-B-32 TO MH-B-31/0, LINE B @ ZONE-01 | 338.03 | 10.25 | 3464.8075
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0042-00 | 2025-12-24 | Survey FIR for Geotextile & Gravel Bedding FIR for sewerage Pipe line from MH-B- 32 TO MH-B- 31/0, LINE B @ ZONE-01 | 338.03 | 3.42 | 1156.0626
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0058-00 | 2026-01-04 | Mechanical FIR Installation and Laying of Sewerage Pipe line from MH-B- 39 TO MH-B-37 @ ZONE-01 | 338.03 | 44.41 | 15011.9123
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0059-00 | 2026-01-04 | Mechanical FIR for initial Air Test of GRP Sewerage Pipe Line form MH-B-39 TO MH-B-37 | 338.03 | 3.7 | 1250.711
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0063-00 | 2026-01-04 | Mechanical FIR Installation and Laying of Sewerage for Pipe Line form MH-B-32TO MH-B-31 Pipe DIA 200MM | 338.03 | 41.01 | 13862.6103
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0073-00 | 2026-01-06 | Mechanical FIR initial Air Test of of Sewerage for Pipe Line form MH-B-32 TO MH-B-31 Pipe DIA200mm | 338.03 | 3.42 | 1156.0626
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0075-00 | 2026-01-07 | Mechanical FIR initial Air Test of Sewerage for Pipe Line form MH-B-33/0 TO MH-B-32 Pipe DIA 200MM | 338.03 | 3.58 | 1210.1474
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0082-00 | 2026-01-08 | Mechanical FIR initial Air Test of Sewerage for Pipe Line form MH-B-37 TO MH-B-36/0, Line B Pipe DIA 200MM | 338.03 | 3.63 | 1227.0489
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0116-00 | 2026-01-14 | Civil FIR for Backfill and Compaction Test 3rd Layer above the Pipeline of Sewerage Network from MH-B-33/0 TO MH-B-32, LINE B @ZONE-01 Pipe DIA 200MM (Thickness 30cm) | 338.03 | 3.61 | 1220.2883
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0126-00 | 2026-01-14 | Mechanical FIR initial Air Test of Sewerage for Pipe Line form MH-B-35 TO MH-B-34, Line B Pipe DIA 200MM | 338.03 | 2.73 | 922.8219
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0136-00 | 2026-01-19 | Mechanical FIR Initial Air Test of Sewerage Pipeline form MH-B-36/0 TO MH-B-35, Line B @ ZONE-01 Pipe DIA 200MM | 338.03 | 2.65 | 895.7795
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0185-00 | 2026-01-29 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-27/0 TO MH-A-26, LINE A @ ZONE-04 | 338.03 | 6.18 | 2089.0254
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0195-00 | 2026-01-31 | Survey FIR for Sand Bedding of Sewerage Pipeline from MH-A-27/0 TO MH-A-26, LINE A @ ZONE-04 | 338.03 | 2.06 | 696.3418
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0198-00 | 2026-01-31 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-26 TO Station MH-A-25/0 FROM STATION (0+408.51 TO 0+430.51), LINE A @ ZONE-04 | 338.03 | 3.21 | 1085.0763
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0222-00 | 2026-02-03 | Mechanical FIR for Installation and Laying of Sewerage Pipeline form MH-A-27/0 TO MH-A-26, LINE A @ ZONE-04 Pipe DIA 200MM | 338.03 | 24.71 | 8352.7213
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0237-00 | 2026-02-07 | Mechanical FIR Initial Air Test of Sewerage Pipeline form MH-A-27/0 TO MH-A-26, Line A @ ZONE-04 Pipe DIA 200MM | 338.03 | 2.06 | 696.3418
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0249-00 | 2026-02-08 | Survey FIR for Sand Bedding of Sewerage Pipeline from MH-A-26 TO MH-A-25/0 FROM STATION (0+408.51 TO 0+430.51), LINE A @ ZONE-04 | 338.03 | 1.07 | 361.6921
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0254-00 | 2026-02-10 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-4-2-3 TO MH-B-4-2-2, LINE B @ ZONE-03 | 338.03 | 8.03 | 2714.3809
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0255-00 | 2026-02-10 | Survey FIR for Sand Bedding of Sewerage Pipeline from MH-B-4-2-3 TO MH-B-4-2-2 , LINE B @ ZONE-03 | 338.03 | 2.68 | 905.9204
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0266-00 | 2026-02-14 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-B-4-2-3 TO MH-B-4-2-2, LINE B @ ZONE-01 Pipe DIA 200MM | 338.03 | 32.1 | 10850.763
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0269-00 | 2026-02-15 | Mechanical FIR Initial Air Test of Sewerage Pipeline form MH-4-2-3 TO MH-4-2-2, LINE B @ ZONE-03 Pipe DIA 200MM | 338.03 | 2.68 | 905.9204
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0351-00 | 2026-03-17 | Survey FIR for Backfill and Compaction Testing 3rd Layer above the Sewerage Pipeline from MH-B-4-2-3 TO MH-B-4-2-2, LINE B @ ZONE-03 | 338.03 | 2.68 | 905.9204
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0507-00 | 2026-04-19 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-2-1 TO MH-A-2-2, @ ZONE-03 | 338.03 | 1.67 | 564.5101
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0511-00 | 2026-04-19 | Survey FIR for Sand Bedding of Sewerage Pipeline from MH-A-2-1 TO MH-A-2-2, @ ZONE-03 | 338.03 | 0.56 | 189.2968
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0653-00 | 2026-05-05 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-2-1 TO MH-A-2-2, @ ZONE-03 | 338.03 | 6.67 | 2254.6601
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0721-00 | 2026-05-13 | Survey FIR for Backfill and Compaction Testing 3rd Layer above the Sewerage Pipeline from MH-A-2-1 TO MH-A-2-2, @ ZONE-03 | 338.03 | 0.56 | 189.2968
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0283-00 | 2026-02-23 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-30 TO MH-B-29, LINE B @ ZONE-01 | 338.03 | 8.24 | 2785.3672
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0284-00 | 2026-02-23 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-B-30 TO MH-B-29, LINE B @ ZONE-01 | 338.03 | 2.75 | 929.5825
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0288-00 | 2026-02-24 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-B-30 TO MH-B-29, LINE B @ ZONE-01 Pipe DIA 200MM | 338.03 | 32.97 | 11144.8491
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0514 | 2026-04-20 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-18-4 TO MH-A-18-3/0, @ ZONE-03 | 338.03 | 8.61 | 2910.4383
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0515 | 2026-04-20 | Survey FIR for Sand Bedding of Sewerage Pipeline from MH-A-18-4 TO MH-A-18-3/0, @ ZONE-03 | 338.03 | 2.87 | 970.1461
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0527 | 2026-04-21 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-18-4 TO MH-A-18-3/0, @ ZONE-04 | 338.03 | 34.45 | 11645.1335
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0506 | 2026-04-19 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-2/0 TO MH-A-2-1, @ ZONE-03 | 338.03 | 3.96 | 1338.5988
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0510 | 2026-04-19 | Survey FIR for Sand Bedding of Sewerage Pipeline from MH-A-2/0 TO MH-A-2-1, @ ZONE-03 | 338.03 | 1.32 | 446.1996
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0652 | 2026-05-05 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-2/0 TO MH-A-2-1, @ ZONE-03 | 338.03 | 15.82 | 5347.6346
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0831 | 2026-06-01 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-20 TO MH-A-19, @ ZONE-04 | 338.03 | 8.87 | 2998.3261
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0832 | 2026-06-01 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-A-20 TO MH-A-19, @ ZONE-04 | 338.03 | 2.96 | 1000.5688
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0833 | 2026-06-01 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-21 TO MH-A-20, @ ZONE-04 | 338.03 | 9.42 | 3184.2426
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0834 | 2026-06-01 | Survey FIR for Sand Bedding and Compaction Testing of Sewerage Pipeline from MH-A-21 TO MH-A-20, @ ZONE-04 | 338.03 | 3.14 | 1061.4142
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0835 | 2026-06-01 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-22 TO MH-A-21, @ ZONE-04 | 338.03 | 5.09 | 1720.5727
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0836 | 2026-06-01 | Survey FIR for Sand Bedding and Compaction Testing of Sewerage Pipeline from MH-A-22 TO MH-A-21, @ ZONE-04 | 338.03 | 1.7 | 574.651
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0837 | 2026-06-01 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-23 TO MH-A-22, @ ZONE-04 | 338.03 | 10.32 | 3488.4696
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0838 | 2026-06-01 | Survey FIR for Sand Bedding and Compaction Testing of Sewerage Pipeline from MH-A-23 TO MH-A-22, @ ZONE-04 | 338.03 | 3.44 | 1162.8232
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0839-01 | 2026-09-07 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-24 TO MH-A-23, @ ZONE-04 | 338.03 | 6.32 | 2136.3496
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0840 | 2026-06-01 | Survey FIR for Sand Bedding and Compaction Testing of Sewerage Pipeline from MH-A-24 TO MH-A-23, @ ZONE-04 | 338.03 | 2.11 | 713.2433
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0841 | 2026-06-01 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-25/0 TO MH-A-24, @ ZONE-04 | 338.03 | 7.16 | 2420.2948
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0842 | 2026-06-01 | Survey FIR for Sand Bedding and Compaction Testing of Sewerage Pipeline from MH-A-25/0 TO MH-A-24, @ ZONE-04 | 338.03 | 2.39 | 807.8917
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0843 | 2026-06-01 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-26 TO MH-A-25/0 From Station (0+430.51 To 0+456.54), @ ZONE-04 | 338.03 | 3.81 | 1287.8943
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0844 | 2026-06-01 | Survey FIR for Sand Bedding and Compaction Testing of Sewerage Pipeline from MH-A-26 TO MH-A-25/0 From Station (0+430.51 To 0+456.54), @ ZONE-04 | 338.03 | 1.27 | 429.2981
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0850 | 2026-06-02 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-20 TO MH-A-19, @ ZONE-04 | 338.03 | 35.48 | 11993.3044
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0852 | 2026-06-02 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-21 TO MH-A-20, @ ZONE-04 | 338.03 | 37.67 | 12733.5901
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0854 | 2026-06-02 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-22 TO MH-A-21, @ ZONE-04 | 338.03 | 20.36 | 6882.2908
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0856 | 2026-06-02 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-23 TO MH-A-22, @ ZONE-04 | 338.03 | 41.26 | 13947.1178
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0858 | 2026-06-02 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-24 TO MH-A-23, @ ZONE-04 | 338.03 | 25.27 | 8542.0181
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0860 | 2026-06-02 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-25/0 TO MH-A-24, @ ZONE-04 | 338.03 | 28.62 | 9674.4186
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0862 | 2026-06-02 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-26 TO MH-A-25/0, @ ZONE-04 | 338.03 | 28.1 | 9498.643
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0924-01 | 2026-09-07 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-18-1/0 TO MH-A-18/0, @ ZONE-04 | 338.03 | 9.5 | 3211.285
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0925 | 2026-06-13 | Survey FIR for Sand Bedding and Compaction Testing of Sewerage Pipeline from MH-A-18-1/0 TO MH-A-18/0, @ ZONE-04 | 338.03 | 3.17 | 1071.5551
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0933 | 2026-06-14 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-18-2 TO MH-A-18-1/0, @ ZONE-04 | 338.03 | 7.85 | 2653.5355
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0934 | 2026-06-14 | Survey FIR for Sand Bedding and Compaction Testing of Sewerage Pipeline from MH-A-18-2 TO MH-A-18-1/0, @ ZONE-04 | 338.03 | 2.62 | 885.6386
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0935 | 2026-06-14 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-18-3/0 TO MH-A-18-2, @ ZONE-04 | 338.03 | 8.52 | 2880.0156
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0936 | 2026-06-14 | Survey FIR for Sand Bedding and Compaction Testing of Sewerage Pipeline from MH-A-18-3/0 TO MH-A-18-2, @ ZONE-04 | 338.03 | 2.84 | 960.0052
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0938 | 2026-06-14 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-18-1/0 TO MH-A-18/0, @ ZONE-04 | 338.03 | 38 | 12845.14
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0972 | 2026-06-18 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-18-3/0 TO MH-A-18-2, @ ZONE-04 | 338.03 | 34.1 | 11526.823
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0974 | 2026-06-18 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-18-2 TO MH-A-18-1/0, @ ZONE-04 | 338.03 | 31.38 | 10607.3814
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1030 | 2026-06-25 | Survey FIR for Backfill and Compaction Testing 4th Layer above the Sewerage Pipeline MH-A-18-3/0 TO MH-A-18-2, ZONE-04 | 338.03 | 2.84 | 960.0052
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1032 | 2026-06-25 | Survey FIR for Backfill and Compaction Testing 4th Layer above the Sewerage Pipeline MH-A-18-2 TO MH-A-18-1/0, ZONE-04 | 338.03 | 2.62 | 885.6386
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1034 | 2026-06-25 | Survey FIR for Backfill and Compaction Testing 4th Layer above the Sewerage Pipeline MH-A-18-1/0 TO MH-A-18/0, ZONE-04 | 338.03 | 3.17 | 1071.5551
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1082 | 2026-07-19 | Survey FIR for Backfill and Compaction Testing 4th Layer above the Sewerage Pipeline from MH-A-20 TO MH-A-19, ZONE-04 | 338.03 | 2.96 | 1000.5688
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1088 | 2026-07-19 | Survey FIR for Backfill and Compaction Testing 4th Layer above the Sewerage Pipeline MH-A-18-4 TO MH-A-18-3/0, ZONE-04 | 338.03 | 2.87 | 970.1461
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1176 | 2026-08-09 | Survey FIR for Backfill and Compaction Testing Final Layer Backfilling above the Sewerage Pipeline MH-A-18-4 TO MH-A-18-3/0, ZONE-04 | 338.03 | 2.87 | 970.1461
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1200 | 2026-08-17 | Survey FIR for Backfill and Compaction Testing 2nd Layer above the Sewerage Pipeline from MH-A-27/0 TO MH-A-26 @ ZONE-04 | 338.03 | 2.06 | 696.3418
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1201 | 2026-08-18 | Survey FIR for Backfill and Compaction Testing 3rd Layer above the Sewerage Pipe Line from MH-A-26 TO MH-A-25/0, @ ZONE-04 | 338.03 | 2.34 | 790.9902
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1286 | 2026-08-22 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from & MH-A-10-4 TO MH-A-10-5 | 338.03 | 8.38 | 2832.6914
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1287 | 2026-08-22 | Survey FIR for Sand Bedding and Compaction testing of Sewerage Pipeline from MH-A-10-4 TO MH-A-10-5 | 338.03 | 2.79 | 943.1037
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1288 | 2026-08-23 | Survey and Mechanical FIR for the Installation and Laying of Storm Pipeline from & MH-A-10-4 TO MH-A-10-5 | 338.03 | 33.52 | 11330.7656
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1300 | 2026-09-09 | Survey FIR for Backfill and Compaction Testing 2nd Layer above the Sewerage Pipeline from MH-B-34 TO MH-B-35, dia 200 mm MH-B-35 TO MH-B-36, dia 200 mm MH-B-36 TO MH-B-37, dia 200 mm MH-B-37 TO MH-B-38, dia 200 mm MH-B-38 TO MH-B-39, dia 200 mm @ ZONE-01 | 338.03 | 12.8 | 4326.784
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1302 | 2026-09-09 | Survey FIR for Backfill and Compaction Testing 3rd Layer above the Sewerage Pipeline from MH-B-29 TO MH-B-30 dia 200 mm MH-B-33 TO MH-B-34 dia 200 mm @ ZONE-01 | 338.03 | 2.75 | 929.5825
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1307-01 | 2026-10-07 | Survey FIR for Backfill and Compaction Testing 4th Layer above the Sewerage Pipeline from MH-B-29 TO MH-B-30, dia 200 mm MH-B-33 TO MH-B-34, dia 200 mm MH-B-34 TO MH-B-35, dia 200 mm MH-B-35 TO MH-B-36, dia 200 mm MH-B-36 TO MH-B-37, dia 200 mm MH-B-37 TO MH-B-38, dia 200 mm MH-B-38 TO MH-B-39, dia 200 mm | 338.03 | 12.8 | 4326.784
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1308-01 | 2026-10-07 | Survey FIR for Backfill and Compaction Testing 5th Layer above the Sewerage Pipeline from MH-B-23 TO MH-B-24, dia 200 mm MH-B-29 TO MH-B-30, dia 200 mm MH-B-30 TO MH-B-31, dia 200 mm MH-B-31 TO MH-B-32, dia 200 mm MH-B-32 TO MH-B-33, dia 200 mm MH-B-35 TO MH-B-36, dia 200 mm MH-B-36 TO MH-B-37, dia 200 mm MH-B-37 TO MH-B-38, dia 200 mm MH-B-38 TO MH-B-39 dia 200 mm @ ZONE-01 | 338.03 | 9.51 | 3214.6653
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1310-01 | 2026-10-08 | Survey FIR for Backfill and Compaction Testing 6th Layer above the Sewerage Pipeline from MH-B-23 TO MH-B-24, dia 200 mm MH-B-29 TO MH-B-30, dia 200 mm MH-B-30 TO MH-B-31, dia 200 mm MH-B-31 TO MH-B-32, dia 200 mm @ ZONE-01 | 338.03 | 2.75 | 929.5825
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1330 | 2026-09-26 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-18-3/0 to MH-A-18-4 ZONE-04 | 338.03 | 5.74 | 1940.2922
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1333 | 2026-09-28 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-18-1 to MH-A-18-2 MH-A-18-2 to MH-A-18-3 ZONE-01 | 338.03 | 10.91 | 3687.9073
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1338 | 2026-09-28 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-27/0 TO MH-A-26 ROAD 2, ZONE 4 | 338.03 | 2.06 | 696.3418
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1339 | 2026-09-28 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-26 TO MH-A-25/0 ROAD 2, ZONE 4 | 338.03 | 4.68 | 1581.9804
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1340 | 2026-09-28 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-25/0 TO MH-A-24 ROAD 2, ZONE 4 | 338.03 | 4.77 | 1612.4031
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1341 | 2026-09-28 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-18-1 TO MH-A-18-0 ROAD 3, ZONE 4 | 338.03 | 6.33 | 2139.7299
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1342 | 2026-09-28 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-21 to MH-A-22 Length=33.94x0.10=3.39m MH-B-37 to MH-B-38 Length=33.94x0.05=1.70m @ RD-1 , 2 , ZONE-04 | 338.03 | 5.09 | 1720.5727
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1344 | 2026-09-30 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-22-0 to MH-A-23-0 MH-A-23-0 to MH-A-24-0 ZONE-04 | 338.03 | 10.15 | 3431.0045
B5.33 31 00.02.02 | 200mm Diameter depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1404 | 2026-10-14 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-19 to MH-A-20 MH-A-20 to MH-A-21 Road-4 & 5 , ZONE- 04 | 338.03 | 12.19 | 4120.5857
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0044-00 | 2025-12-27 | Survey Excavation and Compaction Testing FIR of Sewerage Pipe Line from MH-B-29 TO MH-B-28/0 (From Station 1+163.28 To 1+121.28), LINE B @ ZONE-01 | 398.612 | 6.3 | 2511.2556
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0047-00 | 2025-12-28 | Survey FIR for Geotextile & Gravel Bedding FIR for sewerage Pipe line from MH-B-28 TO MH-B-29 (From Station 1+163.28 To 1+121.28), LINE B @ ZONE-01 | 398.612 | 2.1 | 837.0852
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0049-00 | 2025-12-29 | Survey Excavation and Compaction Testing FIR of Sewerage Pipe Line from MH-B-28/0 TO MH-B-27, LINE B @ ZONE-01 | 398.612 | 6.8 | 2710.5616
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0051-00 | 2025-12-30 | Survey FIR for Geotextile & Gravel Bedding FIR for sewerage Pipe line from MH-B- 28/0 TO MH-B- 27, LINE B @ ZONE-01 | 398.612 | 2.27 | 904.8492
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0065-00 | 2026-01-05 | Mechanical FIR Installation and Laying of Sewerage for Pipe Line form MH-B-29 TO MH-B-28/0 (From Station 1+163.28 To 1+121.28) Pipe DIA 200MM | 398.612 | 25.2 | 10045.0224
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0066-00 | 2026-01-05 | Mechanical FIR initial Air Test of Sewerage for Pipe Line form MH-B-29 TO MH-B-28/0 (From Station 1+163.28 To 1+121.28) Pipe DIA 200MM | 398.612 | 2.1 | 837.0852
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0067-00 | 2026-01-05 | Mechanical FIR Installation and Laying of Sewerage for Pipe Line form MH-B-28 TO MH-B-27 Pipe DIA 200MM | 398.612 | 27.19 | 10838.2603
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0068-00 | 2026-01-05 | Mechanical FIR initial Air Test of Sewerage for Pipe Line form MH-B-28 TO MH-B-27 Pipe DIA 200MM | 398.612 | 2.27 | 904.8492
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0072-00 | 2026-01-06 | Survey Excavation and Compaction Testing FIR of Sewerage Pipe Line from MH-B-26-1 TO MH-B26/0, LINE B @ ZONE-01 | 398.612 | 7.81 | 3113.1597
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0077-00 | 2026-01-07 | Survey FIR for Geotextile & Gravel Bedding for Sewerage Pipeline from MH-B- 26/1 TO MH-B- 26/0, LINE B @ ZONE-01 | 398.612 | 2.6 | 1036.3912
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0094-00 | 2026-01-10 | Mechanical FIR Installation and Laying of Sewerage for Pipe Line form MH-B-26/0 TO MH-B-26/1 Pipe DIA 200MM | 398.612 | 31.25 | 12456.625
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0099-00 | 2026-01-11 | Mechanical FIR initial Air Test of Sewerage for Pipe Line form MH-B-26/0 TO MH-B-26/1, Line B Pipe DIA 200MM | 398.612 | 2.63 | 1048.3496
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0080-00 | 2026-01-07 | Survey Excavation and Compaction Testing FIR of Sewerage Pipe Line from MH-B-27 TO MH-B-26/0, LINE B @ ZONE-01 | 398.612 | 6.94 | 2766.3673
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0086-00 | 2026-01-08 | Survey FIR for Geotextile & Gravel Bedding for Sewerage Pipeline from MH-B-27 TO MH-B-26/0, LINE B @ ZONE-01 | 398.612 | 2.31 | 920.7937
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0093-00 | 2026-01-10 | Mechanical FIR Installation and Laying of Sewerage for Pipe Line form MH-B-27 TO MH-B-26/0 Pipe DIA 200MM | 398.612 | 27.76 | 11065.4691
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0098-00 | 2026-01-11 | Mechanical FIR initial Air Test of Sewerage for Pipe Line form MH-B-27 TO MH-B-26/0, Line B Pipe DIA 200MM | 398.612 | 2.34 | 932.7521
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0293-00 | 2026-02-25 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-4-2-1 TO MH-B-4-2-0, @ ZONE-03 | 398.612 | 5.61 | 2236.2133
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0297-00 | 2026-02-28 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-B-4-2-1 TO MH-B-4-2-0, @ ZONE-03 | 398.612 | 1.87 | 745.4044
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0303-00 | 2026-03-01 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-4-2-1 TO MH-4-2-0, @ ZONE-03 Pipe DIA 200MM | 398.612 | 22.44 | 8944.8533
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0291-00 | 2026-02-25 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-4-2-2 TO MH-B-4-2-1, @ ZONE-03 | 398.612 | 8.1 | 3228.7572
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0296-00 | 2026-02-28 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-4-2-2 TO MH-4-2-1, @ ZONE-03 | 398.612 | 2.7 | 1076.2524
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0301-00 | 2026-03-01 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-B-4-2-2 TO MH-B-4-2-1, @ ZONE-03 Pipe DIA 200MM | 398.612 | 32.38 | 12907.0566
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0319-00 | 2026-03-04 | Survey Excavation and Compaction Testing FIR of Sewerage Pipe Line from MH-B-29 TO MH-B-28/0 (From Station 1+163.28 To 1+175.28), LINE B @ ZONE-01 | 398.612 | 1.47 | 585.9596
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0320-00 | 2026-03-04 | Survey FIR for Geotextile & Gravel Bedding FIR for sewerage Pipe line from MH-B-28 TO MH-B-29 (From Station 1+163.28 To 1+175.28), LINE B @ ZONE-01 | 398.612 | 0.49 | 195.3199
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0427-00 | 2026-04-04 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-14-4 TO MH-A-14-3/0, @ ZONE-04 | 398.612 | 8.52 | 3396.1742
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0429-00 | 2026-04-04 | Survey FIR for Sand Bedding of Sewerage Pipeline from MH-A-14-4 TO MH-A-14-3/0, @ ZONE-04 | 398.612 | 2.84 | 1132.0581
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0437-00 | 2026-04-05 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-14-4 TO MH-A-14-3/0, @ ZONE-04 | 398.612 | 34.07 | 13580.7108
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0531 | 2026-04-21 | Mechanical FIR Initial Air Test of Sewerage Pipeline form MH-A-14-4 TO MH-A-14-3/0, LINE A @ ZONE-04 | 398.612 | 2.84 | 1132.0581
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0538 | 2026-04-21 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-14/0 TO MH-A-14-1/0, @ ZONE-03 | 398.612 | 9.41 | 3750.9389
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0577 | 2026-04-25 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-A-14/0 TO MH-A-14-1, @ ZONE-03 | 398.612 | 3.14 | 1251.6417
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0595 | 2026-04-28 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-14/0 TO MH-A-14-1, @ ZONE-03 | 398.612 | 37.66 | 15011.7279
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0638 | 2026-05-05 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-14-1/0 and MH-A-14-2, @ ZONE-04 | 398.612 | 7.95 | 3168.9654
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0639 | 2026-05-05 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-14-2 and MH-A-14-3/0, @ ZONE-04 | 398.612 | 8.57 | 3416.1048
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0640 | 2026-05-05 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-A-14-1/0 and MH-A-14-2, @ ZONE-04 | 398.612 | 2.65 | 1056.3218
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0641 | 2026-05-05 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-A-14-2 and MH-A-14-3/0, @ ZONE-04 | 398.612 | 2.86 | 1140.0303
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0657 | 2026-05-05 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-13 TO MH-A-12, @ ZONE-04 | 398.612 | 8.86 | 3531.7023
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0658 | 2026-05-05 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-A-13 TO MH-A-12, @ ZONE-04 | 398.612 | 2.95 | 1175.9054
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0676 | 2026-05-06 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-12-1 TO MH-B-12/0, @ ZONE-03 | 398.612 | 6.79 | 2706.5755
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0677 | 2026-05-07 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-B-12-1 TO MH-B-12/0, @ ZONE-03 | 398.612 | 2.26 | 900.8631
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0703 | 2026-05-11 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-B-12-1 TO MH-B-12/0, @ ZONE-03 | 398.612 | 27.15 | 10822.3158
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0705 | 2026-05-11 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-14-1/0 TO MH-A-14-2, @ ZONE-04 | 398.612 | 31.81 | 12679.8477
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0707 | 2026-05-11 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-14-2 TO MH-A-14-3/0, @ ZONE-04 | 398.612 | 34.27 | 13660.4332
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0716 | 2026-05-13 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-14/0 TO MH-A-13, @ ZONE-04 | 398.612 | 9.24 | 3683.1749
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0717 | 2026-05-13 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-15 TO MH-A-14/0, @ ZONE-04 | 398.612 | 8.35 | 3328.4102
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0726 | 2026-05-13 | Survey FIR for Backfill and Compaction Testing 4th Layer above the Sewerage Pipeline from MH-A-2/0 TO MH-A-2-1, @ ZONE-03 | 398.612 | 1.32 | 526.1678
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0756 | 2026-05-23 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-A-15 TO MH-A-14/0, @ ZONE-04 | 398.612 | 2.78 | 1108.1414
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0757 | 2026-05-23 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-A-14/0 TO MH-A-13, @ ZONE-04 | 398.612 | 3.08 | 1227.725
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0789 | 2026-05-23 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-14/0 TO MH-A-13, @ ZONE-04 | 398.612 | 36.98 | 14740.6718
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0816 | 2026-05-24 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-16 TO MH-A-15, @ ZONE-04 | 398.612 | 8.82 | 3515.7578
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0817 | 2026-05-24 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-17 TO MH-A-16, @ ZONE-04 | 398.612 | 7.96 | 3172.9515
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0818 | 2026-05-24 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-18/0 TO MH-A-17, @ ZONE-04 | 398.612 | 8.65 | 3447.9938
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0819 | 2026-05-24 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-A-16 TO MH-A-15, @ ZONE-04 | 398.612 | 2.94 | 1171.9193
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0820 | 2026-05-24 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-A-17 TO MH-A-16, @ ZONE-04 | 398.612 | 2.65 | 1056.3218
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0821 | 2026-05-24 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-A-18/0 TO MH-A-17, @ ZONE-04 | 398.612 | 2.88 | 1148.0026
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0823 | 2026-06-01 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-16 TO MH-A-15, @ ZONE-04 | 398.612 | 35.27 | 14059.0452
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0825 | 2026-06-01 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-17 TO MH-A-16, @ ZONE-04 | 398.612 | 31.84 | 12691.8061
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0827 | 2026-06-01 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-18/0 TO MH-A-17, @ ZONE-04 | 398.612 | 34.6 | 13791.9752
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0829 | 2026-06-01 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-19 TO MH-A-18/0, @ ZONE-04 | 398.612 | 8.95 | 3567.5774
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0830 | 2026-06-01 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-A-19 TO MH-A-18/0, @ ZONE-04 | 398.612 | 2.98 | 1187.8638
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0846 | 2026-06-02 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-15 TO MH-A-14/0, @ ZONE-04 | 398.612 | 33.41 | 13317.6269
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0848 | 2026-06-02 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-19 TO MH-A-18/0, @ ZONE-04 | 398.612 | 35.78 | 14262.3374
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0881 | 2026-06-09 | Survey FIR for Backfill and Compaction Testing 5th Layer above the Sewerage Pipeline from MH-A-14/0 TO MH-A-14-1, @ ZONE-04 | 398.612 | 3.14 | 1251.6417
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0904 | 2026-06-11 | Survey FIR for Backfill and Compaction Testing 6th Layer above the Sewerage Pipeline from MH-A-13 TO MH-A-12, @ ZONE-04 | 398.612 | 2.95 | 1175.9054
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0910 | 2026-06-11 | Survey FIR for Backfill and Compaction Testing 4th Layer above the Sewerage Pipeline from MH-A-19 TO MH-A-18/0, ZONE-03 | 398.612 | 2.95 | 1175.9054
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0916 | 2026-06-11 | Survey FIR for Backfill and Compaction Testing 5th Layer above the Sewerage Pipeline from MH-A-14-1/0 TO MH-A-14-2, @ ZONE-04 | 398.612 | 2.65 | 1056.3218
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0957 | 2026-06-16 | Survey FIR for Backfill and Compaction Testing 4th Layer above the Sewerage Pipeline from MH-A-18/0 TO MH-A-17, ZONE-03 | 398.612 | 2.88 | 1148.0026
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0959 | 2026-06-16 | Survey FIR for Backfill and Compaction Testing 5th Layer above the Sewerage Pipeline from MH-A-14/0 TO MH-A-13, @ ZONE-04 | 398.612 | 3.08 | 1227.725
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0987 | 2026-06-20 | Survey FIR for Backfill and Compaction Testing 5th Layer above the Sewerage Pipeline, @ ZONE-04 1- MH-A-15 TO MH-A-14/0 2- MH-A-16 TO MH-A-15 3- MH-A-17 TO MH-A-16 | 398.612 | 8.38 | 3340.3686
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1084 | 2026-07-19 | Survey FIR for Backfill and Compaction Testing Final Layer Prior to Capping Layer above the Sewerage Pipeline from MH-A-18/0 TO MH-A-17, ZONE-04 | 398.612 | 2.88 | 1148.0026
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1191 | 2026-08-17 | Survey FIR for Backfill and Compaction Testing 4th Layer above the Sewerage Pipeline from MH-A-14-2 TO MH-A-14-3/0, @ ZONE-04 | 398.612 | 2.86 | 1140.0303
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1196 | 2026-08-17 | Survey FIR for Backfill and Compaction Testing Final Layer Backfilling above the Sewerage Pipeline from MH-A-14/0 TO MH-A-14-1, @ ZONE-04 | 398.612 | 3.14 | 1251.6417
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1211 | 2026-08-18 | Survey FIR for Backfill and Compaction Testing 4th Layer above the Sewerage Pipeline from MH-A-14-4 TO MH-A-14-3/0 @ ZONE-04 | 398.612 | 2.84 | 1132.0581
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1284 | 2026-08-22 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from & MH-A-10-3 TO MH-A-10-4 | 398.612 | 7.77 | 3097.2152
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1285 | 2026-08-22 | Survey FIR for Sand Bedding and Compaction testing of Sewerage Pipeline from MH-A-10-3 TO MH-A-10-4 | 398.612 | 2.59 | 1032.4051
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1289 | 2026-08-23 | Survey and Mechanical FIR for the Installation and Laying of Storm Pipeline from & MH-A-10-3 TO MH-A-10-4 | 398.612 | 31.08 | 12388.861
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1317-01 | 2026-10-10 | Survey FIR for Backfill and Compaction Testing 10th Layer above the Sewerage Pipeline from MH-B-26 TO MH-B-27, dia 200 mm B5.33 31 00.02.03 @ ZONE-01 | 398.612 | 2.35 | 936.7382
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1353 | 2026-09-28 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-B-27-0 to MH-B-28 @ RD-1 , ZONE-04 | 398.612 | 4.59 | 1829.6291
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1362 | 2026-09-30 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-14-0 to MH-A-14-1 ZONE-04 | 398.612 | 6.28 | 2503.2834
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1392 | 2026-10-14 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-12 to MH-A-13 MH-A-13 to MH-A-14 Road-2 , ZONE- 04 | 398.612 | 12.07 | 4811.2468
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1403 | 2026-10-14 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-17 to MH-A-18 MH-A-18 to MH-A-19 Road-2 & 3 , ZONE- 04 | 398.612 | 11.73 | 4675.7188
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1413 | 2026-10-15 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-19 TO MH-B-20 MH-B-20 TO MH-B-21 MH-B-21 TO MH-B-22 | 398.612 | 6.35 | 2531.1862
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1414 | 2026-10-15 | Survey FIR for Sand Bedding and Compaction Testing of Sewerage Pipeline from MH-B-19 TO MH-B-20 MH-B-20 TO MH-B-21 MH-B-21 TO MH-B-22 | 398.612 | 2.12 | 845.0574
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1416 | 2026-10-17 | Survey and Mechanical FIR for installation and laying of Sewerage Pipeline from MH-B-19 TO MH-B-20 MH-B-20 TO MH-B-21 MH-B-21 TO MH-B-22 | 398.612 | 25.41 | 10128.7309
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1419 | 2026-10-17 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-14 to MH-A-15 MH-A-15 to MH-A-16 MH-A-16 to MH-A-17 Road-2 , ZONE- 04 | 398.612 | 16.75 | 6676.751
B5.33 31 00.02.03 | 200mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1424 | 2026-10-18 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-10-3 to MH-A-10-4 Road-2 , ZONE- 04 | 398.612 | 5.18 | 2064.8102
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0128-00 | 2026-01-15 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipe Line from MH-B-11 TO MH-B-10, LINE B @ ZONE-03 | 459.194 | 8.26 | 3792.9424
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0134-00 | 2026-01-19 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-B-11 TO MH-B-10, LINE B @ ZONE-03 | 459.194 | 2.76 | 1267.3754
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0138-00 | 2026-01-20 | Mechanical FIR for Installation and Laying of Sewerage Pipeline form MH-B-11 TO MH-B-10, LINE B @ ZONE-03 Pipe DIA 200MM | 459.194 | 33.06 | 15180.9536
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0142-00 | 2026-01-20 | Mechanical FIR Initial Air Test of Sewerage Pipeline form MH-B-11 TO MH-B-10, Line B @ ZONE-03 Pipe DIA 200MM | 459.194 | 2.76 | 1267.3754
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0147-00 | 2026-01-21 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-26/0 TO MH-B-25 and MH-B-25 TO MH-B-24, LINE B @ ZONE-01 | 459.194 | 9.33 | 4284.28
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0149-00 | 2026-01-21 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-10 TO MH-B-09, LINE B @ ZONE-03 | 459.194 | 7.46 | 3425.5872
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0151-00 | 2026-01-22 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-B-26/0 TO MH-B-25 and MH-B-25 TO MH-B-24, LINE B @ ZONE-01 | 459.194 | 3.11 | 1428.0933
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0152-00 | 2026-01-22 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-B-10 TO MH-B-09, LINE B @ ZONE-03 | 459.194 | 2.49 | 1143.3931
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0155-00 | 2026-01-22 | Mechanical FIR for Installation and Laying of Sewerage Pipeline form MH-B-26/0 TO MH-B-25 and MH-B-25 TO MH-B-24, LINE B @ ZONE-01 Pipe DIA 200MM | 459.194 | 37.31 | 17132.5281
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0156-00 | 2026-01-22 | Mechanical FIR for Installation and Laying of Sewerage Pipeline form MH-B-10 TO MH-B-09, LINE B @ ZONE-03 Pipe DIA 200MM | 459.194 | 29.84 | 13702.349
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0158-00 | 2026-01-24 | Mechanical FIR Initial Air Test of Sewerage Pipeline form MH-B-26/0 TO MH-B-25 and MH-B-25 TO MH-B-24, Line B @ ZONE-01 Pipe DIA 200MM | 459.194 | 3.11 | 1428.0933
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0159-00 | 2026-01-24 | Mechanical FIR Initial Air Test of Sewerage Pipeline form MH-B-10 TO MH-B-09, Line B @ ZONE-03 Pipe DIA 200MM | 459.194 | 2.49 | 1143.3931
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0164-00 | 2026-01-25 | Survey FIR for Backfill and Compaction Testing 6th Layer above the Sewerage Pipeline from MH-B-11 TO MH-B-10 LINE B @ ZONE-03 | 459.194 | 2.76 | 1267.3754
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0169-00 | 2026-01-26 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-09 TO MH-B-08, LINE B @ ZONE-03 | 459.194 | 6.37 | 2925.0658
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0172-00 | 2026-01-27 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-B-09 TO MH-B-08, LINE B @ ZONE-03 | 459.194 | 2.12 | 973.4913
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0178-00 | 2026-01-28 | Mechanical FIR for Installation and Laying of Sewerage Pipeline form MH-B-09 TO MH-B-08, LINE B @ ZONE-03 Pipe DIA 200MM | 459.194 | 25.48 | 11700.2631
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0182-00 | 2026-01-28 | Mechanical FIR Initial Air Test of Sewerage Pipeline form MH-B-09 TO MH-B-08, Line B @ ZONE-03 Pipe DIA 200MM | 459.194 | 2.12 | 973.4913
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0191-00 | 2026-01-29 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-07 TO MH-B-06, LINE B @ ZONE-03 | 459.194 | 11.07 | 5083.2776
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0193-00 | 2026-01-31 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-08 TO MH-B-07, LINE B @ ZONE-03 | 459.194 | 2.76 | 1267.3754
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0196-00 | 2026-01-31 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-B-08 TO MH-B-07, LINE B @ ZONE-03 | 459.194 | 0.92 | 422.4585
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0197-00 | 2026-01-31 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-B-07 TO MH-B-06, LINE B @ ZONE-03 | 459.194 | 3.69 | 1694.4259
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0205-00 | 2026-01-31 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-24 TO MH-B-23, LINE B @ ZONE-01 | 459.194 | 8.3 | 3811.3102
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0206-00 | 2026-02-01 | Survey FIR for Backfill and Compaction Testing 7th Layer above the Sewerage Pipeline from MH-B-26/0 TO MH-B-25 and MH-B-25 TO MH-B-24, LINE B @ ZONE-01 | 459.194 | 3.11 | 1428.0933
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0207-00 | 2026-02-01 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-B-24 TO MH-B-23, LINE B @ ZONE-01 | 459.194 | 2.77 | 1271.9674
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0214-00 | 2026-02-01 | Mechanical FIR for Installation and Laying of Sewerage Pipeline form MH-B-07 TO MH-B-06, LINE B @ ZONE-03 Pipe DIA 200MM | 459.194 | 44.28 | 20333.1103
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0215-00 | 2026-02-01 | Mechanical FIR Initial Air Test of Sewerage Pipeline form MH-B-07 TO MH-B-06, Line B @ ZONE-03 Pipe DIA 200MM | 459.194 | 3.69 | 1694.4259
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0217-00 | 2026-02-01 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-06 TO MH-B-05, LINE B @ ZONE-03 | 459.194 | 11.07 | 5083.2776
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0220-00 | 2026-02-02 | Mechanical FIR for Installation and Laying of Sewerage Pipeline form MH-B-24 TO MH-B-23, LINE B @ ZONE-01 Pipe DIA 200MM | 459.194 | 33.22 | 15254.4247
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0221-00 | 2026-02-02 | Mechanical FIR Initial Air Test of Sewerage Pipeline form MH-B-24 TO MH-B-23, Line B @ ZONE-01 Pipe DIA 200MM | 459.194 | 2.77 | 1271.9674
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0223-00 | 2026-02-03 | Mechanical FIR for Installation and Laying of Sewerage Pipeline form MH-B-08 TO MH-B-07, LINE B @ ZONE-03 Pipe DIA 200MM | 459.194 | 11.03 | 5064.9098
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0224-00 | 2026-02-03 | Mechanical FIR Initial Air Test of Sewerage Pipeline form MH-B-08 TO MH-B-07, Line B @ ZONE-03 Pipe DIA 200MM | 459.194 | 0.92 | 422.4585
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0225-00 | 2026-02-04 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-B-06 TO MH-B-05, LINE B @ ZONE-03 | 459.194 | 3.69 | 1694.4259
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0227-00 | 2026-02-04 | Mechanical FIR for Installation and Laying of Sewerage Pipeline form MH-B-06 TO MH-B-05, LINE B @ ZONE-03 Pipe DIA 200MM | 459.194 | 44.28 | 20333.1103
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0231-00 | 2026-02-04 | Survey FIR for Backfill and Compaction Testing 6th Layer above the Sewerage Pipeline from MH-B-10 TO MH-B-09 LINE B @ ZONE-03 | 459.194 | 2.49 | 1143.3931
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0236-00 | 2026-02-04 | Survey FIR for Backfill and Compaction Testing 6th Layer above the Sewerage Pipeline from MH-B-09 TO MH-B-08, LINE B @ ZONE-03 | 459.194 | 2.12 | 973.4913
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0242-00 | 2026-02-07 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-05 TO MH-B-04/0, LINE B @ ZONE-03 | 459.194 | 10.21 | 4688.3707
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0243-00 | 2026-02-07 | Mechanical FIR Initial Air Test of Sewerage Pipeline form MH-B-06 TO MH-B-05, Line B @ ZONE-03 Pipe DIA 200MM | 459.194 | 3.69 | 1694.4259
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0250-00 | 2026-02-10 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-B-05 TO MH-B-04/0, LINE B @ ZONE-03 | 459.194 | 3.4 | 1561.2596
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0256-00 | 2026-02-11 | Mechanical FIR for Installation and Laying of Sewerage Pipeline form MH-B-05 TO MH-B-04/0, LINE B @ ZONE-03 Pipe DIA 200MM | 459.194 | 40.84 | 18753.483
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0261-00 | 2026-02-14 | Mechanical FIR Initial Air Test of Sewerage Pipeline form MH-B-05 TO MH-B-04/0, Line B @ ZONE-03 Pipe DIA 200MM | 459.194 | 3.4 | 1561.2596
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0276-00 | 2026-02-21 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-10/0 TO MH-A-09, LINE A @ ZONE-03 | 459.194 | 10.45 | 4798.5773
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0279-00 | 2026-02-23 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-A-10 TO MH-A-09, LINE A @ ZONE-03 | 459.194 | 3.48 | 1597.9951
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0281-00 | 2026-02-23 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-10 TO MH-A-09, LINE A @ ZONE-03 Pipe DIA 200MM | 459.194 | 41.8 | 19194.3092
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0294-00 | 2026-02-26 | Mechanical FIR Initial Air Test of Sewerage Pipeline form MH-A-10 TO MH-A-09, LINE A @ ZONE-03 Pipe DIA 200MM | 459.194 | 3.48 | 1597.9951
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0313-00 | 2026-03-03 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-4/0 TO MH-B-4-1, @ ZONE-03 | 459.194 | 7.42 | 3407.2195
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0316-00 | 2026-03-03 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-B-4/0 TO MH-B-4-1, @ ZONE-03 | 459.194 | 2.47 | 1134.2092
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0335-00 | 2026-03-05 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-B-4/0 TO MH-B-4-1, @ ZONE-03 | 459.194 | 29.68 | 13628.8779
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0345-00 | 2026-03-16 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-10/0 TO MH-A-10-1/0, @ ZONE-03 | 459.194 | 9.42 | 4325.6075
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0356-00 | 2026-03-18 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-A-10/0 TO MH-A-10-1/0, @ ZONE-03 | 459.194 | 3.14 | 1441.8692
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0358-00 | 2026-03-18 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-10/0 TO MH-A-10-1/0, @ ZONE-03 | 459.194 | 37.69 | 17307.0219
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0373-00 | 2026-03-25 | Survey FIR for Backfill and Compaction Testing 7th Layer above the Sewerage Pipeline from MH-A-10/0 TO MH-A-09, LINE A @ ZONE-03 | 459.194 | 3.48 | 1597.9951
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0384-00 | 2026-03-26 | Survey FIR for Backfill and Compaction Testing 7th Layer above the Sewerage Pipeline from MH-B-4/0 TO MH-B-4-1, @ ZONE-03 | 459.194 | 2.47 | 1134.2092
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0273-00 | 2026-02-19 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-09 TO MH-A-08, LINE A @ ZONE-03 | 459.194 | 10.33 | 4743.474
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0274-00 | 2026-02-19 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-A-09 TO MH-A-08, LINE A @ ZONE-03 | 459.194 | 3.44 | 1579.6274
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0278-00 | 2026-02-23 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-09 TO MH-A-08, LINE A @ ZONE-03 Pipe DIA 200MM | 459.194 | 41.32 | 18973.8961
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0286-00 | 2026-02-23 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-08 TO MH-A-07, LINE A @ ZONE-03 | 459.194 | 10.31 | 4734.2901
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0289-00 | 2026-02-24 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-A-08 TO MH-A-07, LINE A @ ZONE-03 | 459.194 | 3.44 | 1579.6274
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0295-00 | 2026-02-26 | Mechanical FIR Initial Air Test of Sewerage Pipeline form MH-A-09 TO MH-A-08, LINE A @ ZONE-03 Pipe DIA 200MM | 459.194 | 3.44 | 1579.6274
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0299-00 | 2026-02-28 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-08 TO MH-A-07, LINE A @ ZONE-01 Pipe DIA 200MM | 459.194 | 41.23 | 18932.5686
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0324-00 | 2026-03-04 | Mechanical FIR Initial Air Test of Sewerage Pipeline form MH-A-08 TO MH-A-07, LINE A @ ZONE-03 Pipe DIA 200MM | 459.194 | 3.44 | 1579.6274
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0535 | 2026-04-21 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-2 TO MH-B-3, @ ZONE-03 | 459.194 | 6.34 | 2911.29
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0541 | 2026-04-23 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-B-2 TO MH-B-3, @ ZONE-03 | 459.194 | 2.11 | 968.8993
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0546 | 2026-04-25 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-B-2 TO MH-B-3, @ ZONE-03 | 459.194 | 25.34 | 11635.976
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0399-00 | 2026-03-29 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-6 TO MH-A-5, @ ZONE-03 | 459.194 | 10.32 | 4738.8821
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0401-00 | 2026-03-30 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-A-6 TO MH-A-5, @ZONE-03 | 459.194 | 3.44 | 1579.6274
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0414-00 | 2026-04-02 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-6 TO MH-A-5 @ ZONE-03 | 459.194 | 41.28 | 18955.5283
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0445-00 | 2026-04-06 | Mechanical FIR Initial Air Test of Sewerage Pipeline form MH-A-6 TO MH-A-5, LINE A @ ZONE-03 | 459.194 | 3.44 | 1579.6274
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0516 | 2026-04-20 | Survey FIR for Backfill and Compaction Testing 8th Layer above the Sewerage Pipeline from MH-A-6 TO MH-A-5, LINE A @ ZONE-03 | 459.194 | 3.44 | 1579.6274
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0375-00 | 2026-03-25 | Survey FIR for Backfill and Compaction Testing 7th Layer above the Sewerage Pipeline from MH-A-09 TO MH-A-08, LINE A @ ZONE-03 | 459.194 | 3.44 | 1579.6274
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0387-00 | 2026-03-28 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-7 TO MH-A-6, @ ZONE-03 | 459.194 | 10.34 | 4748.066
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0388-00 | 2026-03-28 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-A-7 TO MH-A-6, @ ZONE-03 | 459.194 | 3.45 | 1584.2193
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0397-00 | 2026-03-29 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-7 TO MH-A-6 @ ZONE-03 | 459.194 | 41.36 | 18992.2638
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0450-00 | 2026-04-11 | Survey FIR for Backfill and Compaction Testing 8th Layer above the Sewerage Pipeline from MH-A-08 TO MH-A-07, LINE A @ ZONE-03 | 459.194 | 3.44 | 1579.6274
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0452-00 | 2026-04-11 | Survey FIR for Backfill and Compaction Testing 8th Layer above the Sewerage Pipeline from MH-A-7 TO MH-A-6, @ZONE-03 | 459.194 | 3.45 | 1584.2193
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0536-00 | 2026-04-21 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-3 TO MH-B-4/0, @ ZONE-03 | 459.194 | 1.94 | 890.8364
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0542-00 | 2026-04-23 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-B-3 TO MH-B-4/0, @ ZONE-03 | 459.194 | 0.65 | 298.4761
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0599-00 | 2026-04-28 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-B-3 TO MH-B-4, @ ZONE-03 | 459.194 | 7.75 | 3558.7535
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0630 | 2026-05-04 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-12 TO MH-A-11, @ ZONE-04 | 459.194 | 9.73 | 4467.9576
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0631 | 2026-05-04 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-11 TO MH-A-10, @ ZONE-04 | 459.194 | 9.3 | 4270.5042
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0632 | 2026-05-04 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-A-12 TO MH-A-11, @ ZONE-04 | 459.194 | 3.24 | 1487.7886
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0633 | 2026-05-04 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-A-11 TO MH-A-10/0, @ ZONE-04 | 459.194 | 3.1 | 1423.5014
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0670 | 2026-05-06 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-11 TO MH-A-10/0, @ ZONE-04 | 459.194 | 37.21 | 17086.6087
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0672 | 2026-05-06 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-12 TO MH-A-11, @ ZONE-04 | 459.194 | 38.92 | 17871.8305
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0701 | 2026-05-11 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-13 TO MH-A-12, @ ZONE-04 | 459.194 | 35.45 | 16278.4273
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0901 | 2026-06-11 | Survey FIR for Backfill and Compaction Testing 6th Layer above the Sewerage Pipeline, ZONE-03 1- MH-A-11 TO MH-A-10/0 2- MH-A-12 TO MH-A-11 | 459.194 | 6.34 | 2911.29
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1106 | 2026-07-22 | Survey FIR for Backfill and Compaction Testing 7th Layer above the Sewerage Pipeline from MH-B-2 TO MH-B-3, @ ZONE-03 | 459.194 | 2.11 | 968.8993
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1122 | 2026-07-25 | Survey FIR for Backfill and Compaction Testing Final Layer Prior to Capping Layer above the Sewerage Pipeline from MH-B-10 TO MH-B-09 and MH-B-09 To MH-B-08, LINE B @ ZONE-03 | 459.194 | 4.61 | 2116.8843
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1169 | 2026-08-09 | Survey FIR for Backfill and Compaction Testing 7th Layer above the Sewerage Pipeline from MH-B-06 TO MH-B-05 LINE B @ ZONE-03 | 459.194 | 3.69 | 1694.4259
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1170 | 2026-08-09 | Survey FIR for Backfill and Compaction Testing 7th Layer above the Sewerage Pipeline from MH-B-05 TO MH-B-04 LINE B @ ZONE-03 | 459.194 | 3.4 | 1561.2596
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1203 | 2026-08-18 | Survey FIR for Backfill and Compaction Testing Final Layer Prior to Capping Layer above the Sewerage Pipeline from MH-B-07 TO MH-B-06, ZONE-03 | 459.194 | 3.69 | 1694.4259
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1218 | 2026-08-18 | Survey FIR for Backfill and Compaction Testing Final Layer Prior to Capping Layer above the Sewerage Pipeline from MH-B-08 TO MH-B-07 LINE B @ ZONE-03 | 459.194 | 0.92 | 422.4585
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1220 | 2026-08-18 | Survey FIR for Backfill and Compaction Testing Final Layer Prior to Capping Layer above the Sewerage Pipeline from MH-B-06 TO MH-B-05 LINE B @ ZONE-03 | 459.194 | 3.69 | 1694.4259
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1227 | 2026-08-18 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-10-1 TO MH-A-10-2 & MH-A-10-2 TO MH-A-10-3 | 459.194 | 16.2 | 7438.9428
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1228 | 2026-08-18 | Survey FIR for Sand Bedding of Sewerage Pipeline from MH-A-10-1 TO MH-A-10-2 & MH-A-10-2 TO MH-A-10-3 | 459.194 | 5.4 | 2479.6476
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1229 | 2026-08-19 | Survey and Mechanical FIR for the Installation and Laying of Sewerage Pipeline from MH-A-10-1 TO MH-A-10-2 & MH-A-10-2 TO MH-A-10-3 | 459.194 | 64.79 | 29751.1793
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1308 | 2026-09-12 | Survey FIR for Backfill and Compaction Testing 5th Layer above the Sewerage Pipeline from MH-B-23 TO MH-B-24, dia 200 mm MH-B-29 TO MH-B-30, dia 200 mm MH-B-30 TO MH-B-31, dia 200 mm MH-B-31 TO MH-B-32, dia 200 mm MH-B-32 TO MH-B-33, dia 200 mm MH-B-35 TO MH-B-36, dia 200 mm MH-B-36 TO MH-B-37, dia 200 mm MH-B-37 TO MH-B-38, dia 200 mm MH-B-38 TO MH-B-39 dia 200 mm @ ZONE-01 | 459.194 | 2.77 | 1271.9674
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1318 | 2026-09-15 | Survey FIR for Backfill and Compaction Testing 11th Layer above the Sewerage Pipeline from MH-B-23 TO MH-B-24, dia 200 mm MH-B-24 TO MH-B-25, dia 200 mm MH-B-25 TO MH-B-26, dia 200 mm @ ZONE-01 | 459.194 | 5.81 | 2667.9171
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1391 | 2026-10-14 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-10 to MH-A-10-1 MH-A-10 to MH-A-11 MH-A-11 to MH-A-12 Road-2 , ZONE- 04 | 459.194 | 18.97 | 8710.9102
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1411 | 2026-10-15 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-12 TO MH-B-13 MH-B-13 TO MH-B-14 MH-B-14 TO MH-B-15 MH-B-15 TO MH-B-16 MH-B-16 TO MH-B-17 MH-B-17 TO MH-B-18 MH-B-18 TO MH-B-19 | 459.194 | 28.43 | 13054.8854
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1412 | 2026-10-15 | Survey FIR for Sand Bedding and Compaction Testing of Sewerage Pipeline from MH-B-12 TO MH-B-13 MH-B-13 TO MH-B-14 MH-B-14 TO MH-B-15 MH-B-15 TO MH-B-16 MH-B-16 TO MH-B-17 MH-B-17 TO MH-B-18 MH-B-18 TO MH-B-19 | 459.194 | 9.48 | 4353.1591
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1415 | 2026-10-17 | Survey and Mechanical FIR for installation and laying of Sewerage Pipeline from MH-B-12 TO MH-B-13 MH-B-13 TO MH-B-14 MH-B-14 TO MH-B-15 MH-B-15 TO MH-B-16 MH-B-16 TO MH-B-17 MH-B-17 TO MH-B-18 MH-B-18 TO MH-B-19 | 459.194 | 113.73 | 52224.1336
B5.33 31 00.02.04 | 200mm Diameter Depth: 3.51m -4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1423 | 2026-10-18 | Mechanical FIR for Final Air testing of GRP Sewerage Drainage PIPE from MH-A-10-1 to MH-A-10-2 MH-A-10-2 to MH-A-10-3 Road-2 , ZONE- 04 | 459.194 | 10.8 | 4959.2952
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0314-00 | 2026-03-03 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-4-1 TO MH-B-4-2, @ ZONE-03 | 518.898 | 7.42 | 3850.2232
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0315-00 | 2026-03-03 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-4-2 TO MH-B-4-3 (Station 0+101.34 to 117.94), @ ZONE-03 | 518.898 | 2.4 | 1245.3552
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0317-00 | 2026-03-03 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-B-4-1 TO MH-B-4-2, @ ZONE-03 | 518.898 | 2.47 | 1281.6781
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0318-00 | 2026-03-03 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-B-4-2 TO MH-B-4-3 ((Station 0+101.34 to 117.94), @ ZONE-03 | 518.898 | 0.8 | 415.1184
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0336-00 | 2026-03-05 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-B-4-1 TO MH-B-4-2, @ ZONE-03 | 518.898 | 29.68 | 15400.8926
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0337-00 | 2026-03-05 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-B-4-2 TO MH-B-4-3 (Station 0+101.34 to 0+117.94), @ ZONE-03 | 518.898 | 9.6 | 4981.4208
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0384-00 | 2026-03-26 | Survey FIR for Backfill and Compaction Testing 7th Layer above the Sewerage Pipeline from MH-B-4-1 TO MH-B-4-2/0 and MH-B-4-2/0 TO MH-B-4-3 ((Station 0+101.34 to 0+117.94), @ ZONE-03 | 518.898 | 3.27 | 1696.7965
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0412-00 | 2026-04-02 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-5 TO MH-A-4, @ ZONE-03 | 518.898 | 10.32 | 5355.0274
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0420-00 | 2026-04-02 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-A-5 TO MH-A-4, @ ZONE-03 | 518.898 | 3.44 | 1785.0091
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0434-00 | 2026-04-05 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-5 TO MH-A-4 @ ZONE-03 | 518.898 | 41.28 | 21420.1094
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0446-00 | 2026-04-06 | Mechanical FIR Initial Air Test of Sewerage Pipeline form MH-A-5 TO MH-A-4, LINE A @ ZONE-03 | 518.898 | 3.44 | 1785.0091
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0458-00 | 2026-04-11 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-4 TO MH-A-3, @ ZONE-03 | 518.898 | 7.25 | 3762.0105
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0464-00 | 2026-04-13 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-A-4 TO MH-A-3, @ ZONE-03 | 518.898 | 2.42 | 1255.7332
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0466-00 | 2026-04-13 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-4 TO MH-A-3, @ ZONE-03 | 518.898 | 28.99 | 15042.853
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0473-00 | 2026-04-13 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-3 TO MH-A-2/0, @ ZONE-03 | 518.898 | 7.19 | 3730.8766
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0475-00 | 2026-04-13 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-2/0 TO MH-A-1/0, @ ZONE-03 | 518.898 | 5.11 | 2651.5688
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0476-00 | 2026-04-14 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-A-3 TO MH-A-2/0, @ ZONE-03 | 518.898 | 2.39 | 1240.1662
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0477-00 | 2026-04-14 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-A-2/0 TO MH-A-1/0, @ ZONE-03 | 518.898 | 1.7 | 882.1266
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0480-00 | 2026-04-14 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-3 TO MH-A-2/0, @ ZONE-03 | 518.898 | 28.74 | 14913.1285
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0481-00 | 2026-04-14 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-2/0 TO MH-A-1/0, @ ZONE-03 | 518.898 | 20.45 | 10611.4641
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0482-00 | 2026-04-14 | Mechanical FIR Initial Air Test of Sewerage Pipeline form MH-A-4 TO MH-A-3, LINE A @ ZONE-03 | 518.898 | 2.42 | 1255.7332
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0501 | 2026-04-18 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-A-1/0 TO MH-B-1, @ ZONE-03 | 518.898 | 10.68 | 5541.8306
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0502 | 2026-04-18 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-A-1/0 TO MH-B-1, @ ZONE-03 | 518.898 | 3.56 | 1847.2769
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0505 | 2026-04-19 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-A-1/0 TO MH-B-1, @ ZONE-03 | 518.898 | 42.71 | 22162.1336
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0528 | 2026-04-21 | Mechanical FIR Initial Air Test of Sewerage Pipeline form MH-A-3 TO MH-A-2/0, LINE A @ ZONE-03 | 518.898 | 2.4 | 1245.3552
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0529 | 2026-04-21 | Mechanical FIR Initial Air Test of Sewerage Pipeline form MH-A-2/0 TO MH-A-1/0, LINE A @ ZONE-03 | 518.898 | 1.7 | 882.1266
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0532 | 2026-04-21 | Mechanical FIR Initial Air Test of Sewerage Pipeline form MH-A-1/0 TO MH-B-1, @ ZONE-03 | 518.898 | 3.56 | 1847.2769
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0534 | 2026-04-21 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline from MH-B-1 TO MH-B-2, @ ZONE-03 | 518.898 | 10.59 | 5495.1298
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0540 | 2026-04-23 | Survey FIR for Gravel Bedding with Geotextile of Sewerage Pipeline from MH-B-1 TO MH-B-2, @ ZONE-03 | 518.898 | 3.53 | 1831.7099
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0544 | 2026-04-25 | Mechanical FIR for Installation and Laying of Sewerage Pipeline from MH-B-1 TO MH-B-2, @ ZONE-03 | 518.898 | 42.38 | 21990.8972
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0568 | 2026-04-25 | Survey FIR for Backfill and Compaction Testing 8th Layer above the Sewerage Pipeline from MH-A-5 TO MH-A-4, LINE A @ ZONE-03 | 518.898 | 3.44 | 1785.0091
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0739 | 2026-05-17 | Survey FIR for Backfill and Compaction Testing 8th Layer above the Sewerage Pipeline from MH-A-4 TO MH-A-3, LINE A @ ZONE-03 | 518.898 | 2.42 | 1255.7332
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0741-01 | 2026-06-11 | Survey FIR for Backfill and Compaction Testing 8th Layer above the Sewerage Pipeline from MH-A-3 TO MH-A-2/0, LINE A @ ZONE-03 | 518.898 | 2.4 | 1245.3552
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0743-01 | 2026-06-11 | Survey FIR for Backfill and Compaction Testing 8th Layer above the Sewerage Pipeline from MH-A-2/0 TO MH-A-1/0, LINE A @ ZONE-03 | 518.898 | 1.7 | 882.1266
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0767-01 | 2026-06-11 | Survey FIR for Backfill and Compaction Testing 8th Layer above the Sewerage Pipeline from MH-A-1/0 TO MH-B-1, @ ZONE-03 | 518.898 | 3.56 | 1847.2769
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0897 | 2026-06-11 | Survey FIR for Backfill and Compaction Testing 7th Layer above the Sewerage Pipeline from MH-B-1 TO MH-B-2, @ ZONE-03 | 518.898 | 3.53 | 1831.7099
B5.33 31 00.02.05 | 200mm Diameter Depth: 4.51m -5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1175 | 2026-08-09 | Survey FIR for Backfill and Compaction Testing Final Layer above the Sewerage Pipeline from MH-B-4-1 TO MH-B-4-2/0, @ ZONE-03 | 518.898 | 2.47 | 1281.6781
B5.33 05 13.01 | MH dia 1200 mm, Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0306-00 | 2026-03-01 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manholes MH-B-40 Line B @ZONE-01 | 8981.94 | 0.05 | 449.097
B5.33 05 13.01 | MH dia 1200 mm, Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0447-00 | 2026-04-06 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manholes MH-B-31-1, and MH-B-26-2 @ ZONE-01 | 8981.94 | 0.1 | 898.194
B5.33 05 13.01 | MH dia 1200 mm, Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0554-00 | 2026-04-25 | Survey Excavation and Compaction Testing FIR for Sewerage Manholes (MH-A-2-4) DIA 1200, @ ZONE-03 | 8981.94 | 0.05 | 449.097
B5.33 05 13.01 | MH dia 1200 mm, Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0581-00 | 2026-04-26 | FIR for Installation of Manhole Base MH-B-40 of Sewerage Network, @ ZONE-01 | 8981.94 | 0.3 | 2694.582
B5.33 05 13.01 | MH dia 1200 mm, Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0584-00 | 2026-04-26 | FIR for Installation of Manhole Base MH-B-31/1 of Sewerage Network, @ ZONE-01 | 8981.94 | 0.3 | 2694.582
B5.33 05 13.01 | MH dia 1200 mm, Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0586-00 | 2026-04-26 | FIR for Installation of Manhole Base MH-B-26/2 of Sewerage Network, @ ZONE-01 | 8981.94 | 0.3 | 2694.582
B5.33 05 13.01 | MH dia 1200 mm, Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0646-00 | 2026-05-05 | FIR for Installation of Manhole Base MH-A-2-4 of Sewerage Network @ ZONE-03 | 8981.94 | 0.3 | 2694.582
B5.33 05 13.01 | MH dia 1200 mm, Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0690-00 | 2026-05-11 | Survey FIR for Backfill and Compaction Testing 3rd Layer around the Manholes of the Sewerage Pipeline @ ZONE-01 1- MH-B-40 2- MH-B-31/1 3- MH-B-26/2 | 8981.94 | 0.15 | 1347.291
B5.33 05 13.01 | MH dia 1200 mm, Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0791-00 | 2026-05-23 | Survey FIR for Backfill and Compaction Testing 4th Layer around the Manholes of the Sewerage Pipeline @ ZONE-01 1- MH-B-40 2- MH-B-31/1 3- MH-B-26/2 | 8981.94 | 0.15 | 1347.291
B5.33 05 13.01 | MH dia 1200 mm, Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1074-00 | 2026-07-11 | FIR for Installation of Flat Cover Slab for Manhole of Sewerage Network @ ZONE-01 1- MH-B-26-2 2- MH-B-31-1 3- MH-B-40 | 8981.94 | 1.05 | 9431.037
B5.33 05 13.01 | MH dia 1200 mm, Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1167-00 | 2026-08-06 | FIR for Benching, Joint Sealant, Epoxy and Finishing of Manholes up to the Flat Cover Slab for Manholes @ Zone-01 1- MH-B-31/1 | 8981.94 | 0.05 | 449.097
B5.33 05 13.01 | MH dia 1200 mm, Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1180-00 | 2026-08-13 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manholes 1:MH-A-28 | 8981.94 | 0.05 | 449.097
B5.33 05 13.01 | MH dia 1200 mm, Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1315 | 2026-09-15 | Survey FIR for Excavation and Compaction Testing of Sewerage Drainage Manhole’s MH-B-12-2-1 @ ZONE-01 | 8981.94 | 0.05 | 449.097
B5.33 05 13.01 | MH dia 1200 mm, Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1321 | 2026-09-16 | FIR for Installation of base of Sewerage Drainage Manhole’s MH-B-12-2-1 (B5 33.05.13.01) @ ZONE-01 | 8981.94 | 0.3 | 2694.582
B5.33 05 13.01 | MH dia 1200 mm, Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1379 | 2026-10-08 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manhole MH-B-4-6-7 | 8981.94 | 0.05 | 449.097
B5.33 05 13.01 | MH dia 1200 mm, Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1389 | 2026-10-10 | FIR for Installation of Sewerage Pipeline Manhole MH-B-4-6-7 | 8981.94 | 0.3 | 2694.582
B5.33 05 13.01 | MH dia 1200 mm, Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1397 | 2026-10-14 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manhole MH-A-10-6 MH-A-10-5-1 | 8981.94 | 0.1 | 898.194
B5.33 05 13.01 | MH dia 1200 mm, Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1408 | 2026-10-15 | FIR for Installation of Sewerage Pipeline Manhole MH-A-10-6 MH-A-10-5-1 | 8981.94 | 0.6 | 5389.164
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0004-00 | 2025-12-08 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manholes MH-B-40 Line B @ZONE-01 | 12732.756 | 0.15 | 1909.9134
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0008-00 | 2025-12-10 | Survey Excavation and Compaction FIR for sewerage Manholes (MH-B-36/0) DIA 1200, LINE-B @ ZONE-01 | 12732.756 | 0.05 | 636.6378
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0305-00 | 2026-03-01 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manholes MH-B-39, MH-B-38 Line B @ZONE-01 | 12732.756 | 0.1 | 1273.2756
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0444-00 | 2026-04-06 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manholes MH-B-36-1, MH-B-33-1 & MH-B-28-1 @ ZONE-01 | 12732.756 | 0.15 | 1909.9134
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0463-00 | 2026-04-11 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manholes MH-A-14-5/0, MH-A-14-5-1, MH-A-18-5/0 and MH-A-18-5-1 @ ZONE-04 | 12732.756 | 0.2 | 2546.5512
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0553-00 | 2026-04-25 | Survey Excavation and Compaction Testing FIR for Sewerage Manholes (MH-A-2-2 and MH-A-2-3) DIA 1200, @ ZONE-03 | 12732.756 | 0.1 | 1273.2756
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0582-00 | 2026-04-26 | FIR for Installation of Manhole Base MH-B-39, MH-B-38, MH-B-36/0, MH-B-35, MH-B-34, MH-B-33/0, MH-B-28/1, MH-B-33/1 and MH-B-36/1 of Sewerage Network, @ ZONE-01 | 12732.756 | 2.7 | 34378.4412
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0645-00 | 2026-05-05 | FIR for Installation of Manhole Base MH-A-2-2, MH-A-2-3 of Sewerage Network @ ZONE-03 | 12732.756 | 0.6 | 7639.6536
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0695-00 | 2026-05-11 | Survey FIR for Backfill and Compaction Testing 4th Layer around the Manholes of the Sewerage Pipeline @ ZONE-01 1- MH-B-38 2- MH-B-36/0 3- MH-B-35 4- MH-B-34 5- MH-B-28/1 | 12732.756 | 0.25 | 3183.189
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0711-00 | 2026-05-11 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manholes MH-A-14-3-1, @ ZONE-04 | 12732.756 | 0.05 | 636.6378
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0792-00 | 2026-05-23 | Survey FIR for Backfill and Compaction Testing 4th Layer around the Manholes of the Sewerage Pipeline @ ZONE-01 1- MH-B-39 2- MH-B-36/1 3- MH-B-33/0 4- MH-B-33/1 | 12732.756 | 0.2 | 2546.5512
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0804-00 | 2026-05-23 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manholes MH-A-18-3-1, @ ZONE-04 | 12732.756 | 0.05 | 636.6378
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0866-01 | 2026-06-24 | FIR for Installation of Manhole Base of Sewerage Network @ ZONE-04 1- MH-A-14-5 2- MH-A-14-3/1 3- MH-A-14-5/1 4- MH-A-18-5 5- MH-A-18-3/1 6- MH-A-18-5/1 | 12732.756 | 1.8 | 22918.9608
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0930-00 | 2026-06-13 | Survey Excavation and Compaction Testing FIR for Sewerage Manholes (MH-A-26) DIA 1200, @ ZONE-04 | 12732.756 | 0.05 | 636.6378
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1011 | 2026-06-24 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manholes @ ZONE-04 1- MH-A-27/0 2- MH-A-27-1 | 12732.756 | 0.1 | 1273.2756
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1019 | 2026-06-24 | FIR for Installation of Manhole Base of Sewerage Network @ZONE-04 1- MH-A-26 | 12732.756 | 0.3 | 3819.8268
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1039 | 2026-06-28 | FIR for Installation of Manhole Base of Sewerage Network @ZONE-04 1- MH-A-27/0 2- MH-A-27-1 | 12732.756 | 0.6 | 7639.6536
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1063 | 2026-07-06 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manholes @ ZONE-04 1- MH-A-23-1 2- MH-A-25-1 | 12732.756 | 0.1 | 1273.2756
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1073 | 2026-07-11 | FIR for Installation of Flat Cover Slab for Manhole of Sewerage Network @ ZONE-01 1- MH-B-33/0 2- MH-B-34 3- MH-B-35 4- MH-B-36/0 5- MH-B-38 6- MH-B-39 7- MH-B-28-1 8- MH-B-33-1 9- MH-B-36-1 | 12732.756 | 3.15 | 40108.1814
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1159 | 2026-08-03 | Survey FIR for Backfill and Compaction Testing 4TH Layer around the Manholes of the Sewerage Pipeline, @ Zone-03 1- MH-A-2-2 | 12732.756 | 0.05 | 636.6378
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1163 | 2026-08-06 | FIR for Benching, Joint Sealant, Epoxy and Finishing of Manholes up to the Flat Cover Slab for Manholes @ Zone-01 1- MH-B-33/0 2- MH-B-33/1 3- MH-B-34 4- MH-B-35 5- MH-B-36/0 6- MH-B-36/1 7- MH-B-38 8- MH-B-39 9- MH-28/1 | 12732.756 | 0.45 | 5729.7402
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1258 | 2026-08-20 | Survey FIR for Backfill and Compaction Testing 6th Layer of the Sewerage Pipeline Manhole, @ Zone-01 1- MH-B-39 | 12732.756 | 0.05 | 636.6378
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1260 | 2026-08-20 | Survey FIR for Backfill and Compaction Testing 7th Layer of the Sewerage Pipeline Manhole, @ Zone-01 1- MH-B-38 | 12732.756 | 0.05 | 636.6378
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1263 | 2026-08-20 | Survey FIR for Backfill and Compaction Testing 7th Layer of the Sewerage Pipeline Manhole, @ Zone-01 1- MH-B-36/0 | 12732.756 | 0.05 | 636.6378
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1264 | 2026-08-20 | Survey FIR for Backfill and Compaction Testing 5th Layer of the Sewerage Pipeline Manhole, @ Zone-01 1- MH-B-36/1 | 12732.756 | 0.05 | 636.6378
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1265 | 2026-08-20 | Survey FIR for Backfill and Compaction Testing 7th Layer of the Sewerage Pipeline Manhole, @ Zone-01 1- MH-B-35 | 12732.756 | 0.05 | 636.6378
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1276 | 2026-08-20 | Survey FIR for Backfill and Compaction Testing 5th Layer of the Sewerage Pipeline Manhole, @ Zone-01 1- MH-B-28/1 | 12732.756 | 0.05 | 636.6378
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1296 | 2026-09-03 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manhole MH-A-10-3-1 | 12732.756 | 0.05 | 636.6378
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1303 | 2026-09-12 | FIR for installation of base of manhole sewerage network MH-A-10-3-1 @ ZONE-04 | 12732.756 | 0.3 | 3819.8268
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1377 | 2026-10-08 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manhole MH-B-4-6-5 MH-B-4-6-6 | 12732.756 | 0.1 | 1273.2756
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1387 | 2026-10-10 | FIR for Installation of Sewerage Pipeline Manhole MH-B-4-6-5 MH-B-4-6-6 | 12732.756 | 0.6 | 7639.6536
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1399 | 2026-10-14 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manhole MH-A-10-5 | 12732.756 | 0.05 | 636.6378
B5.33 05 13.02 | MH dia 1200 mm, depth 1.51 - 2.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1409 | 2026-10-15 | FIR for Installation of Sewerage Pipeline Manhole MH-A-10-5 | 12732.756 | 0.3 | 3819.8268
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0304-00 | 2026-03-01 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manholes MH-B-37, Line B @ZONE-01 | 15294.76 | 0.05 | 764.738
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0459-00 | 2026-04-11 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manholes MH-B-32, MH-B-30, MH-B-29 and MH-B-26-1, @ ZONE-01 | 15294.76 | 0.2 | 3058.952
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0552-00 | 2026-04-25 | Survey Excavation and Compaction Testing FIR for Sewerage Manholes (MH-A-2-1) DIA 1200, @ ZONE-03 | 15294.76 | 0.05 | 764.738
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0583-00 | 2026-04-26 | FIR for Installation of Manhole Base MH-B-37 of Sewerage Network, @ ZONE-01 | 15294.76 | 0.3 | 4588.428
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-04587-00 | 2026-04-26 | FIR for Installation of Manhole Base MH-B-26/1 of Sewerage Network, @ ZONE-01 | 15294.76 | 0.3 | 4588.428
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0590-00 | 2026-04-26 | FIR for Installation of Manhole Base MH-B-29, MH-B-30 and MH-B-32 of Sewerage Network, @ ZONE-01 | 15294.76 | 0.9 | 13765.284
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0644-00 | 2026-05-05 | FIR for Installation of Manhole Base MH-A-2-1 of Sewerage Network @ ZONE-03 | 15294.76 | 0.3 | 4588.428
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0699-00 | 2026-05-11 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manholes MH-A-14-3/0, @ ZONE-04 | 15294.76 | 0.05 | 764.738
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0710-00 | 2026-05-11 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manholes MH-A-14-1-1 and MH-A-14-4, @ ZONE-04 | 15294.76 | 0.1 | 1529.476
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0803-00 | 2026-05-23 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manholes MH-A-18-1/0, MH-A-18-1-1, MH-A-18-2, MH-A-18-3/0 and MH-A-18-4, @ ZONE-04 | 15294.76 | 0.25 | 3823.69
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0810-00 | 2026-05-24 | Survey FIR for Backfill and Compaction Testing 5th Layer around the Manholes of the Sewerage Pipeline @ ZONE-01 1- MH-B-37 2- MH-B-32 3- MH-B-30 4- MH-B-29 5- MH-B-26/1 | 15294.76 | 0.25 | 3823.69
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0865-01 | 2026-06-24 | FIR for Installation of Manhole Base of Sewerage Network @ ZONE-04 1- MH-A-14-3 2- MH-A-14-1-1 3- MH-A-18-1 4- MH-A-18-2 5- MH-A-18-3 6- MH-A-18-4 7- MH-A-18-1/1 | 15294.76 | 2.1 | 32118.996
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0928-00 | 2026-06-13 | Survey Excavation and Compaction Testing FIR for Sewerage Manholes (MH-A-17, MH-A-18/0, MH-A-19, MH-A-20, MH-A-21, MH-A-22, MH-A-23/0, MH-A-24 and MH-A-25/0) DIA 1200, @ ZONE-04 | 15294.76 | 0.45 | 6882.642
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1018-00 | 2026-06-24 | FIR for Installation of Manhole Base of Sewerage Network @ZONE-04 1- MH-A-17 2- MH-A-18/0 3- MH-A-19 4- MH-A-20 5- MH-A-22 6- MH-A-23/0 | 15294.76 | 1.8 | 27530.568
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1066 | 2026-07-11 | FIR for Installation of Manhole Base of Sewerage Network @ZONE-04 1- MH-A-24 2- MH-A-25/0 | 15294.76 | 0.6 | 9176.856
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1072 | 2026-07-11 | FIR for Installation of Flat Cover Slab for Manhole of Sewerage Network @ ZONE-01 1- MH-B-29 2- MH-B-30 3- MH-B-32 4- MH-B-37 | 15294.76 | 1.4 | 21412.664
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1076 | 2026-07-11 | FIR for Installation of Flat Cover Slab for Manhole of Sewerage Network @ ZONE-01 1- MH-B-26-1 | 15294.76 | 0.35 | 5353.166
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1157 | 2026-08-03 | Survey FIR for Backfill and Compaction Testing 4TH Layer around the Manholes of the Sewerage Pipeline, @ Zone-03 1- MH-A-2-1 | 15294.76 | 0.05 | 764.738
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1164 | 2026-08-06 | FIR for Benching, Joint Sealant, Epoxy and Finishing of Manholes up to the Flat Cover Slab for Manholes @ Zone-01 1- MH-B-29 2- MH-30 3- MH-B-32 4- MH-B-37 | 15294.76 | 0.2 | 3058.952
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1230 | 2026-08-20 | Survey FIR for Backfill and Compaction Testing 5th Layer of the Sewerage Pipeline Manhole. @ Zone-04 1- MH-A-18 | 15294.76 | 0.05 | 764.738
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1261 | 2026-08-20 | Survey FIR for Backfill and Compaction Testing 7th Layer of the Sewerage Pipeline Manhole, @ Zone-01 1- MH-B-37 | 15294.76 | 0.05 | 764.738
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1267 | 2026-08-20 | Survey FIR for Backfill and Compaction Testing 8th Layer of the Sewerage Pipeline Manhole, @ Zone-01 1- MH-B-32 | 15294.76 | 0.05 | 764.738
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1271 | 2026-08-20 | Survey FIR for Backfill and Compaction Testing 7th Layer of the Sewerage Pipeline Manhole, @ Zone-01 1- MH-B-30 | 15294.76 | 0.05 | 764.738
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1273 | 2026-08-20 | Survey FIR for Backfill and Compaction Testing 8th Layer of the Sewerage Pipeline Manhole, @ Zone-01 1- MH-B-29 | 15294.76 | 0.05 | 764.738
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1281 | 2026-08-20 | Survey FIR for Backfill and Compaction Testing 6th Layer of the Sewerage Pipeline Manhole, @ Zone-01 1- MH-B-26/1 | 15294.76 | 0.05 | 764.738
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1290 | 2026-08-23 | Survey FIR for Backfill and Compaction Testing 5th Layer of the around Sewerage Manhole, @ Zone-01, Zone-04 1- MH-A-14-2 @ Zone-04 item # B5 33.05.13.05 2- MH-A-18-2 @ Zone-04 item # B5 33.05.13.03 3- MH-A-18-1/0 @ Zone-04 item # B5 33.05.13.03 4-MH-B-28/0 @ Zone-01 item # B5 33.05.13.06 | 15294.76 | 0.1 | 1529.476
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1375 | 2026-10-08 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manhole MH-B-4-6-1 MH-B-4-6-2 MH-B-4-6-3 MH-B-4-6-4 | 15294.76 | 0.2 | 3058.952
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1385 | 2026-10-10 | FIR for Installation of Sewerage Pipeline Manhole MH-B-4-6-1 MH-B-4-6-2 MH-B-4-6-3 MH-B-4-6-4 | 15294.76 | 1.2 | 18353.712
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1401 | 2026-10-14 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manhole MH-A-10-1-1 | 15294.76 | 0.05 | 764.738
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1410 | 2026-10-15 | FIR for Installation of Sewerage Pipeline Manhole MH-A-10-1-1 | 15294.76 | 0.3 | 4588.428
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1417 | 2026-10-17 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manhole MH-B-4-2-2 | 15294.76 | 0.05 | 764.738
B5.33 05 13.03 | MH dia 1200 mm, depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1421 | 2026-10-18 | FIR for Installation of Sewerage Pipeline Manhole MH-B-4-2-2 | 15294.76 | 0.3 | 4588.428
B5.33 05 13.04 | Manhole Internal Diameter 1200 depth 2.51-3.5m with back drop | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0460-00 | 2026-04-11 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manholes MH-B-31-0, @ ZONE-01 | 17572.292 | 0.05 | 878.6146
B5.33 05 13.04 | Manhole Internal Diameter 1200 depth 2.51-3.5m with back drop | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0591-00 | 2026-04-26 | FIR for Installation of Manhole Base MH-B-31/0 of Sewerage Network, @ ZONE-01 | 17572.292 | 0.3 | 5271.6876
B5.33 05 13.04 | Manhole Internal Diameter 1200 depth 2.51-3.5m with back drop | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0812-00 | 2026-05-24 | Survey FIR for Backfill and Compaction Testing 5th Layer around the Manholes of the Sewerage Pipeline @ ZONE-01 1- MH-B-31/0 | 17572.292 | 0.05 | 878.6146
B5.33 05 13.04 | Manhole Internal Diameter 1200 depth 2.51-3.5m with back drop | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1075 | 2026-07-11 | FIR for Installation of Flat Cover Slab for Manhole of Sewerage Network @ ZONE-01 1- MH-B-31/0 | 17572.292 | 0.35 | 6150.3022
B5.33 05 13.04 | Manhole Internal Diameter 1200 depth 2.51-3.5m with back drop | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1166 | 2026-08-06 | FIR for Benching, Joint Sealant, Epoxy and Finishing of Manholes up to the Flat Cover Slab for Manholes @ Zone-01 1- MH-B-31/0 | 17572.292 | 0.05 | 878.6146
B5.33 05 13.05 | MH dia 1200 mm, depth 3.51 - 4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0462-00 | 2026-04-11 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manholes MH-B-27 and MH-B-26-0, @ ZONE-01 | 20053.52 | 0.1 | 2005.352
B5.33 05 13.05 | MH dia 1200 mm, depth 3.51 - 4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0588-00 | 2026-04-26 | FIR for Installation of Manhole Base MH-B-26/0 and MH-B-27 of Sewerage Network, @ ZONE-01 | 20053.52 | 0.6 | 12032.112
B5.33 05 13.05 | MH dia 1200 mm, depth 3.51 - 4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0697-00 | 2026-05-11 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manholes MH-A-12 and MH-A-14-2, DIA 1200mm, @ ZONE-04 | 20053.52 | 0.1 | 2005.352
B5.33 05 13.05 | MH dia 1200 mm, depth 3.51 - 4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0709-00 | 2026-05-11 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manholes MH-A-13 and MH-A-14-1/0, @ ZONE-04 | 20053.52 | 0.1 | 2005.352
B5.33 05 13.05 | MH dia 1200 mm, depth 3.51 - 4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0864-01 | 2026-06-24 | FIR for Installation of Manhole Base of Sewerage Network @ ZONE-04 1- MH-A-12 2- MH-A-14-1 3- MH-A-14-2 | 20053.52 | 0.9 | 18048.168
B5.33 05 13.05 | MH dia 1200 mm, depth 3.51 - 4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0926-00 | 2026-06-13 | Survey Excavation and Compaction Testing FIR for Sewerage Manholes (MH-A-14/0, MH-A-15 and MH-A-16) DIA 1200, @ ZONE-04 | 20053.52 | 0.15 | 3008.028
B5.33 05 13.05 | MH dia 1200 mm, depth 3.51 - 4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1017-00 | 2026-06-24 | FIR for Installation of Manhole Base of Sewerage Network @ ZONE-04 1- MH-A-16 | 20053.52 | 0.3 | 6016.056
B5.33 05 13.05 | MH dia 1200 mm, depth 3.51 - 4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1069-01 | 2026-07-20 | FIR for Installation of Manhole Base of Sewerage Network @ZONE-04 1- MH-A-13 2- MH-A-14/0 3- MH-A-15 | 20053.52 | 0.3 | 6016.056
B5.33 05 13.05 | MH dia 1200 mm, depth 3.51 - 4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1153 | 2026-08-03 | Survey FIR for Backfill and Compaction Testing 6TH Layer around the Manholes of the Sewerage Pipeline, @ Zone-04 1- MH-A-12 | 20053.52 | 0.05 | 1002.676
B5.33 05 13.05 | MH dia 1200 mm, depth 3.51 - 4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1155 | 2026-08-03 | Survey FIR for Backfill and Compaction Testing 6TH Layer around the Manholes of the Sewerage Pipeline, @ Zone-04 1- MH-A-13 | 20053.52 | 0.05 | 1002.676
B5.33 05 13.05 | MH dia 1200 mm, depth 3.51 - 4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1235 | 2026-08-19 | Survey FIR for Backfill and Compaction Testing 6th Layer of the Sewerage Pipeline Manhole, @ Zone-04 1- MH-A-16 | 20053.52 | 0.05 | 1002.676
B5.33 05 13.05 | MH dia 1200 mm, depth 3.51 - 4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1277 | 2026-08-20 | Survey FIR for Backfill and Compaction Testing 6th Layer of the Sewerage Pipeline Manhole, @ Zone-01 1- MH-B-27 | 20053.52 | 0.05 | 1002.676
B5.33 05 13.05 | MH dia 1200 mm, depth 3.51 - 4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1290 | 2026-08-23 | Survey FIR for Backfill and Compaction Testing 5th Layer of the around Sewerage Manhole, @ Zone-01, Zone-04 1- MH-A-14-2 @ Zone-04 item # B5 33.05.13.05 2- MH-A-18-2 @ Zone-04 item # B5 33.05.13.03 3- MH-A-18-1/0 @ Zone-04 item # B5 33.05.13.03 4-MH-B-28/0 @ Zone-01 item # B5 33.05.13.06 | 20053.52 | 0.05 | 1002.676
B5.33 05 13.05 | MH dia 1200 mm, depth 3.51 - 4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1315 | 2026-09-15 | Survey FIR for Excavation and Compaction Testing of Sewerage Drainage Manhole’s MH-B-9 MH-B-10 @ ZONE-01 | 20053.52 | 0.1 | 2005.352
B5.33 05 13.05 | MH dia 1200 mm, depth 3.51 - 4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1321 | 2026-09-16 | FIR for Installation of base of Sewerage Drainage Manhole’s MH-B-9 (B5 33.05.13.05) MH-B-10 (B5 33.05.13.05) @ ZONE-01 | 20053.52 | 0.6 | 12032.112
B5.33 05 13.05 | MH dia 1200 mm, depth 3.51 - 4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1395 | 2026-09-14 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manhole MH-A-10-2 MH-A-10-4 | 20053.52 | 0.1 | 2005.352
B5.33 05 13.05 | MH dia 1200 mm, depth 3.51 - 4.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1407 | 2026-09-15 | FIR for Installation of Sewerage Pipeline Manhole MH-A-10-2 MH-A-10-4 | 20053.52 | 0.6 | 12032.112
B5.33 05 13.06 | Manhole Internal Diameter 1200 depth 3.51-4.5m with back drop | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0461-00 | 2026-04-11 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manholes MH-B-28-0, @ ZONE-01 | 20053.52 | 0.05 | 1002.676
B5.33 05 13.06 | Manhole Internal Diameter 1200 depth 3.51-4.5m with back drop | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0589-00 | 2026-04-26 | FIR for Installation of Manhole Base MH-B-28/0 of Sewerage Network, @ ZONE-01 | 20053.52 | 0.3 | 6016.056
B5.33 05 13.06 | Manhole Internal Diameter 1200 depth 3.51-4.5m with back drop | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1071 | 2026-07-11 | FIR for Installation of Flat Cover Slab for Manhole of Sewerage Network @ ZONE-01 1- MH-B-28/0 | 20053.52 | 0.35 | 7018.732
B5.33 05 13.06 | Manhole Internal Diameter 1200 depth 3.51-4.5m with back drop | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1165 | 2026-08-06 | FIR for Benching, Joint Sealant, Epoxy and Finishing of Manholes up to the Flat Cover Slab for Manholes @ Zone-01 1- MH-B-28/0 | 20053.52 | 0.05 | 1002.676
B5.33 05 13.06 | Manhole Internal Diameter 1200 depth 3.51-4.5m with back drop | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1290 | 2026-08-23 | Survey FIR for Backfill and Compaction Testing 5th Layer of the around Sewerage Manhole, @ Zone-01, Zone-04 1- MH-A-14-2 @ Zone-04 item # B5 33.05.13.05 2- MH-A-18-2 @ Zone-04 item # B5 33.05.13.03 3- MH-A-18-1/0 @ Zone-04 item # B5 33.05.13.03 4-MH-B-28/0 @ Zone-01 item # B5 33.05.13.06 | 20053.52 | 0.05 | 1002.676
B5.33 05 13.06 | Manhole Internal Diameter 1200 depth 3.51-4.5m with back drop | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1393 | 2026-10-14 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manhole MH-A-10-1 MH-A-10-3 | 20053.52 | 0.1 | 2005.352
B5.33 05 13.06 | Manhole Internal Diameter 1200 depth 3.51-4.5m with back drop | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1406 | 2026-10-15 | FIR for Installation of Sewerage Pipeline Manhole MH-A-10-1 MH-A-10-3 | 20053.52 | 0.6 | 12032.112
B5.33 05 13.07 | Manhole Internal Diameter 1200 depth 4.51-5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0549-01 | 2026-09-08 | Survey Excavation and Compaction Testing FIR for Sewerage Manholes (MH-A-5) DIA 1200, @ ZONE-03 | 30889.796 | 0.05 | 1544.4898
B5.33 05 13.07 | Manhole Internal Diameter 1200 depth 4.51-5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0555-00 | 2026-04-25 | Survey Excavation and Compaction Testing FIR for Sewerage Manholes (MH-B-1, MH-B-2 and MH-B-3) DIA 1200, @ ZONE-03 | 30889.796 | 0.15 | 4633.4694
B5.33 05 13.07 | Manhole Internal Diameter 1200 depth 4.51-5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0647-00 | 2026-05-05 | FIR for Installation of Manhole Base MH-B-1, MH-B-2 and MH-B-3 of Sewerage Network @ ZONE-03 | 30889.796 | 0.9 | 27800.8164
B5.33 05 13.07 | Manhole Internal Diameter 1200 depth 4.51-5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0698-00 | 2026-05-11 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manholes MH-A-11, @ ZONE-04 | 30889.796 | 0.05 | 1544.4898
B5.33 05 13.07 | Manhole Internal Diameter 1200 depth 4.51-5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0890-00 | 2026-06-10 | Survey Excavation and Compaction Testing FIR for Sewerage Manholes (MH-A-8 and MH-A-9) DIA 1200, @ ZONE-03 | 30889.796 | 0.1 | 3088.9796
B5.33 05 13.07 | Manhole Internal Diameter 1200 depth 4.51-5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1016-00 | 2026-06-24 | FIR for Installation of Manhole Base of Sewerage Network @ ZONE-03 1- MH-A-8 2- MH-A-9 | 30889.796 | 0.6 | 18533.8776
B5.33 05 13.07 | Manhole Internal Diameter 1200 depth 4.51-5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1020-00 | 2026-06-24 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manholes @ ZONE-04 1- MH-A-10/0 | 30889.796 | 0.05 | 1544.4898
B5.33 05 13.07 | Manhole Internal Diameter 1200 depth 4.51-5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1041-00 | 2026-06-28 | FIR for Installation of Manhole Base of Sewerage Network @ZONE-04 1- MH-A-10/0 | 30889.796 | 0.3 | 9266.9388
B5.33 05 13.07 | Manhole Internal Diameter 1200 depth 4.51-5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1042-00 | 2026-06-28 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manholes @ ZONE-03 1- MH-A-6 | 30889.796 | 0.05 | 1544.4898
B5.33 05 13.07 | Manhole Internal Diameter 1200 depth 4.51-5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1048-00 | 2026-06-29 | FIR for Installation of Manhole Base of Sewerage Network @ZONE-03 1- MH-A-6 | 30889.796 | 0.3 | 9266.9388
B5.33 05 13.07 | Manhole Internal Diameter 1200 depth 4.51-5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1068 | 2026-07-11 | FIR for Installation of Manhole Base of Sewerage Network @ZONE-04 1- MH-A-11 | 30889.796 | 0.3 | 9266.9388
B5.33 05 13.07 | Manhole Internal Diameter 1200 depth 4.51-5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1077 | 2026-07-13 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manholes @ ZONE-03 1- MH-A-7 | 30889.796 | 0.05 | 1544.4898
B5.33 05 13.07 | Manhole Internal Diameter 1200 depth 4.51-5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1080-01 | 2026-09-08 | FIR for Installation of Manhole Base of Sewerage Network @ZONE-03 1- MH-A-5 2- MH-A-7 | 30889.796 | 0.6 | 18533.8776
B5.33 05 13.07 | Manhole Internal Diameter 1200 depth 4.51-5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1315 | 2026-09-15 | Survey FIR for Excavation and Compaction Testing of Sewerage Drainage Manhole’s MH-B-7 MH-B-8 @ ZONE-01 | 30889.796 | 0.1 | 3088.9796
B5.33 05 13.07 | Manhole Internal Diameter 1200 depth 4.51-5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1321 | 2026-09-16 | FIR for Installation of base of Sewerage Drainage Manhole’s MH-B-7 (B5 33.05.13.07) MH-B-8 (B5 33.05.13.07) @ ZONE-01 | 30889.796 | 0.6 | 18533.8776
B5.33 05 13.07 | Manhole Internal Diameter 1200 depth 4.51-5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1373 | 2026-10-08 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manhole MH-B-4-6-0 | 30889.796 | 0.05 | 1544.4898
B5.33 05 13.07 | Manhole Internal Diameter 1200 depth 4.51-5.5m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1383 | 2026-10-10 | FIR for Installation of Sewerage Pipeline Manhole MH-B-4-6-0 | 30889.796 | 0.3 | 9266.9388
B5.33 05 13.08 | MH depth 4.51-5.5 m with back drop | DAM2-02-09-SAJ-TS9-1-SEW-FIR-1371 | 2026-10-08 | Survey FIR for Excavation and Compaction Testing of Sewerage Pipeline Manhole MH-B-4-3 | 35213.946 | 0.05 | 1760.6973
B5.33 05 13.09 | Manhole Internal Diameter 1200 depth 5.51-6m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0550-00 | 2026-04-25 | Survey Excavation and Compaction Testing FIR for Sewerage Manholes (MH-A-4, MH-A-3 and MH-A-1/0) DIA 1200, @ ZONE-03 | 42256.384 | 0.15 | 6338.4576
B5.33 05 13.09 | Manhole Internal Diameter 1200 depth 5.51-6m | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0642-00 | 2026-05-05 | FIR for Installation of Manhole Base MH-A-1/0, MH-A-3 and MH-A-4 of Sewerage Network @ ZONE-03 | 42256.384 | 0.9 | 38030.7456
B5.33 05 13.10 | Manhole Internal Diameter 1200 depth 5.51-6m with back drop | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0551-00 | 2026-04-25 | Survey Excavation and Compaction Testing FIR for Sewerage Manholes (MH-A-2/0) DIA 1200, @ ZONE-03 | 46482.198 | 0.05 | 2324.1099
B5.33 05 13.10 | Manhole Internal Diameter 1200 depth 5.51-6m with back drop | DAM2-02-09-SAJ-TS9-1-SEW-FIR-0643-00 | 2026-05-05 | FIR for Installation of Manhole Base MH-A-2/0 of Sewerage Network @ ZONE-03 | 46482.198 | 0.3 | 13944.6594
B5.1.31 23 16.01 | Wet Well & Screening Chamber & Control Room | DAM2-02-09-SAJ-TS9-1-STU-FIR-0264 | 2026-09-28 | Inspection for survey works of excavation and compaction testing for bottom of replacement soil of the Sewage Lift Station(Wet Well, Screening Chamber and Control Room). | 43.9 | 217.16 | 9533.324
B5.1.03 30 00.01 | 100 mm thickness lean concrete under the foundation for wet well & valve chamber & Screening chamber & Control room | DAM2-02-09-SAJ-TS9-1-STU-FIR-0301 | 2026-10-05 | Inspection of 100 mm thickness lean concrete under the foundation of Wet Well of Sewage Lift Station. | 438.122 | 2.21 | 968.2496
B5.1.03 30 00.01 | Footings for wet well & valve chamber & screening chamber & control room | DAM2-02-09-SAJ-TS9-1-STU-FIR-0311 | 2026-10-08 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the RC Raft of Sewage Lift Station (Wet Well). | 1101.012 | 10.13 | 11153.2516
B5.1.03 30 00.02 | Reinforced Concrete Walls for wet well and valve chamber & screening chamber | DAM2-02-09-SAJ-TS9-1-STU-FIR-0343 | 2026-10-19 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls of Wet Well (Sewage Lift Station). | 1390.752 | 23.92 | 33266.7878
B5.1.07 13 13.01 | Water proofing Membrane with 50mm screed protection fc' 20MPa | DAM2-02-09-SAJ-TS9-1-STU-FIR-0302 | 2026-10-05 | Inspection of the Waterproofing Membrane with 50 mm Screed Protection (20 MPa) at the the foundation of Wet Well of Sewage Lift Station | 128.188 | 22.09 | 2831.6729
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0136-00 | 2026-02-12 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-2-8 TO MH-6-2-7, @ ZONE-03 | 345.054 | 6.02 | 2077.2251
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0137-00 | 2026-02-12 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-2-7 TO MH-6-2-6, @ ZONE-03 | 345.054 | 16.65 | 5745.1491
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0138-00 | 2026-02-12 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-1-9 TO MH-6-1-8, @ ZONE-03 | 345.054 | 8 | 2760.432
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0139-00 | 2026-02-12 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-1-8 TO MH-6-1-7, @ ZONE-03 | 345.054 | 15.65 | 5400.0951
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0142-00 | 2026-02-12 | Survey FIR for Sand Bedding of Storm Pipeline from MH-6-2-8 TO MH-6-2-7, @ ZONE-03 | 345.054 | 2.01 | 693.5585
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0143-00 | 2026-02-12 | Survey FIR for Sand Bedding of Storm Pipeline from MH-6-2-7 TO MH-6-2-6, @ ZONE-03 | 345.054 | 5.55 | 1915.0497
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0144-00 | 2026-02-12 | Survey FIR for Sand Bedding of Storm Pipeline from MH-6-1-9 TO MH-6-1-8, @ ZONE-03 | 345.054 | 2.67 | 921.2942
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0145-00 | 2026-02-12 | Survey FIR for Sand Bedding of Storm Pipeline from MH-6-1-8 TO MH-6-1-7, @ ZONE-03 | 345.054 | 5.22 | 1801.1819
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0169-00 | 2026-02-15 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-2-8 TO MH-6-2-7, @ ZONE-03, Pipe DIA 400mm | 345.054 | 24.1 | 8315.8014
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0170-00 | 2026-02-15 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-2-7 TO MH-6-2-6, @ ZONE-03, Pipe DIA 400mm | 345.054 | 51.6 | 17804.7864
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0174-00 | 2026-02-16 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-1-7 TO MH-6-1-6, @ ZONE-03 | 345.054 | 2.42 | 835.0307
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0175-00 | 2026-02-16 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-1-6 TO MH-6-1-5, @ ZONE-03 | 345.054 | 1.83 | 631.4488
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0176-00 | 2026-02-16 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-1-5 TO MH-6-1-4, @ ZONE-03 | 345.054 | 2.47 | 852.2834
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0177-00 | 2026-02-16 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-1-4 TO MH-6-1-3, @ ZONE-03 | 345.054 | 1.79 | 617.6467
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0178-00 | 2026-02-16 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-2-6 TO MH-6-2-5, @ ZONE-03 | 345.054 | 2.23 | 769.4704
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0179-00 | 2026-02-16 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-2-5 TO MH-6-2-4, @ ZONE-03 | 345.054 | 1.52 | 524.4821
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0180-00 | 2026-02-16 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-2-4 TO MH-6-2-3, @ ZONE-03 | 345.054 | 1.94 | 669.4048
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0181-00 | 2026-02-16 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-2-3 TO MH-6-2-2, @ ZONE-03 | 345.054 | 1.88 | 648.7015
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0182-00 | 2026-02-16 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-6-1-7 TO MH-6-1-6, @ ZONE-03 | 345.054 | 0.81 | 279.4937
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0183-00 | 2026-02-16 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-6-1-6 TO MH-6-1-5, @ ZONE-03 | 345.054 | 0.61 | 210.4829
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0184-00 | 2026-02-16 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-6-1-5 TO MH-6-1-4, @ ZONE-03 | 345.054 | 0.82 | 282.9443
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0185-00 | 2026-02-16 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-6-1-4 TO MH-6-1-3, @ ZONE-03 | 345.054 | 0.6 | 207.0324
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0186-00 | 2026-02-16 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-6-2-6 TO MH-6-2-5, @ ZONE-03 | 345.054 | 0.74 | 255.34
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0187-00 | 2026-02-16 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-6-2-5 TO MH-6-2-4, @ ZONE-03 | 345.054 | 0.51 | 175.9775
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0188-00 | 2026-02-16 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-6-2-4 TO MH-6-2-3, @ ZONE-03 | 345.054 | 0.65 | 224.2851
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0189-00 | 2026-02-16 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-6-2-3 TO MH-6-2-2, @ ZONE-03 | 345.054 | 0.63 | 217.384
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0191-00 | 2026-02-16 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-1-9 TO MH-6-1-8, @ ZONE-03, Pipe DIA 400mm | 345.054 | 32.02 | 11048.6291
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0204-00 | 2026-02-18 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-1-8 TO MH-6-1-7, (Station 0+171.7To +0+269.7) @ ZONE-03, Pipe DIA 400mm | 345.054 | 58.8 | 20289.1752
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0213-00 | 2026-02-21 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-1-7 TO MH-6-1-6, @ ZONE-03, Pipe DIA 400mm | 345.054 | 9.67 | 3336.6722
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0214-00 | 2026-02-21 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-1-6 TO MH-6-1-5, @ ZONE-03, Pipe DIA 400mm | 345.054 | 7.33 | 2529.2458
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0215-00 | 2026-02-21 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-1-5 TO MH-6-1-4, @ ZONE-03, Pipe DIA 400mm | 345.054 | 9.88 | 3409.1335
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0216-00 | 2026-02-21 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-2-6 TO MH-6-2-5, @ ZONE-03, Pipe DIA 400mm | 345.054 | 8.92 | 3077.8817
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0217-00 | 2026-02-21 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-2-5 TO MH-6-2-4, @ ZONE-03, Pipe DIA 400mm | 345.054 | 6.08 | 2097.9283
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0218-00 | 2026-02-21 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-2-4 TO MH-6-2-3, @ ZONE-03, Pipe DIA 400mm | 345.054 | 7.75 | 2674.1685
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0224-00 | 2026-02-21 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-1-4 TO MH-6-1-3, @ ZONE-03, Pipe DIA 400mm | 345.054 | 7.15 | 2467.1361
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0284-00 | 2026-03-09 | Mechanical FIR Initial Air Test of Storm Pipeline form MH-6-2-8 TO MH-6-2-7, @ ZONE-03 Pipe DIA 400MM | 345.054 | 2.01 | 693.5585
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0285-00 | 2026-03-09 | Mechanical FIR Initial Air Test of Storm Pipeline form MH-6-1-9 TO MH-6-1-8, @ ZONE-03 Pipe DIA 400MM | 345.054 | 2.67 | 921.2942
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0286-00 | 2026-03-09 | Mechanical FIR Initial Air Test of Storm Pipeline form MH-6-1-8 TO MH-6-1-7 (Station 0+171.7To +0+269.7), @ ZONE-03 Pipe DIA 400MM | 345.054 | 4.9 | 1690.7646
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0393-00 | 2026-03-29 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-9-1-3 TO MH-6-9-1-2, @ ZONE-03 | 345.054 | 2.52 | 869.5361
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0394-00 | 2026-03-29 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-9-1-2 TO MH-6-9-1-1, @ ZONE-03 | 345.054 | 2.77 | 955.7996
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0395-00 | 2026-03-29 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-9-1-1 TO MH-6-9-1/0, @ ZONE-03 | 345.054 | 2.11 | 728.0639
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0396-00 | 2026-03-29 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-9-3 TO MH-6-9-2, @ ZONE-03 | 345.054 | 8.03 | 2770.7836
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0397-00 | 2026-03-29 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-9-2 TO MH-6-9-1/0, @ ZONE-03 | 345.054 | 2.33 | 803.9758
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0398-00 | 2026-03-29 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-6-9-1-3 TO MH-6-9-1-2, @ ZONE-03 | 345.054 | 0.84 | 289.8454
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0399-00 | 2026-03-29 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-6-9-1-2 TO MH-6-9-1-1, @ ZONE-03 | 345.054 | 0.92 | 317.4497
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0400-00 | 2026-03-29 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-6-9-1-1 TO MH-6-9-1/0, @ ZONE-03 | 345.054 | 0.7 | 241.5378
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0401-00 | 2026-03-29 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-6-9-3 TO MH-6-9-2, @ ZONE-03 | 345.054 | 2.68 | 924.7447
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0402-00 | 2026-03-29 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-6-9-2 TO MH-6-9-1/0, @ ZONE-03 | 345.054 | 0.78 | 269.1421
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0403-00 | 2026-03-29 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-8-15 TO MH-8-14, @ ZONE-02 | 345.054 | 6.71 | 2315.3123
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0404-00 | 2026-03-29 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-8-14 TO MH-8-13, @ ZONE-02 | 345.054 | 1.4 | 483.0756
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0407-00 | 2026-03-29 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-8-15 TO MH-8-14, @ ZONE-02 | 345.054 | 2.24 | 772.921
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0408-00 | 2026-03-29 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-8-14 TO MH-8-13, @ ZONE-02 | 345.054 | 0.47 | 162.1754
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0446-00 | 2026-03-31 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-9-1-3 TO MH-6-9-1-2 @ZONE-03, Pipe DIA 400mm | 345.054 | 10.07 | 3474.6938
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0447-00 | 2026-03-31 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-9-1-2 TO MH-6-9-1-1 @ZONE-03, Pipe DIA 400mm | 345.054 | 11.08 | 3823.1983
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0448-00 | 2026-03-31 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-9-1-1 TO MH-6-9-1/0 @ZONE-03, Pipe DIA 400mm | 345.054 | 8.44 | 2912.2558
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0449-00 | 2026-03-31 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-9-3 TO MH-6-9-2 @ZONE-03, Pipe DIA 400mm | 345.054 | 32.12 | 11083.1345
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0450-00 | 2026-03-31 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-9-2 TO MH-6-9-1/0 @ZONE-03, Pipe DIA 400mm | 345.054 | 9.3 | 3209.0022
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0453-00 | 2026-04-01 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-8-15 TO MH-8-14 @ZONE-02, Pipe DIA 400mm | 345.054 | 26.86 | 9268.1504
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0454-00 | 2026-04-01 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-8-14 TO MH-8-13 @ZONE-02, Pipe DIA 400mm | 345.054 | 5.58 | 1925.4013
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0482-00 | 2026-04-28 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-11-1 TO MH-6-11-2, @ ZONE-02 | 345.054 | 10.65 | 3674.8251
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0483-00 | 2026-04-28 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-6-11-1 TO MH-6-11-2, @ ZONE-02 | 345.054 | 3.55 | 1224.9417
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0486-00 | 2026-04-29 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-17-2 TO MH-17-1, @ ZONE-02 | 345.054 | 8.9 | 3070.9806
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0487-00 | 2026-04-29 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-17-2 TO MH-17-1, @ ZONE-02 | 345.054 | 2.97 | 1024.8104
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0491-00 | 2026-05-03 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-6-11-1 TO MH-6-11-2, @ ZONE-02 | 345.054 | 42.62 | 14706.2015
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0495-00 | 2026-05-03 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-17-2 TO MH-17-1, @ ZONE-02 | 345.054 | 35.6 | 12283.9224
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0002-01 | 2025-12-28 | Survey Excavation & Compaction Test FIR for Storm Pipe line from MH-28-4 TO MH-28-3 @ ZONE-01 Pipe DIA 400mm | 345.054 | 7.08 | 2442.9823
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0003-02 | 2025-12-31 | Survey Sand Bedding FIR for Storm Pipe Line from MH-28-4 TO MH-28-3 @ ZONE-01 Pipe DIA 400mm | 345.054 | 2.36 | 814.3274
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0005-01 | 2025-12-28 | Mechanical FIR for Installation and Laying of GRP Storm Pipe Line form MH-28-4 TO MH-28-3 @ ZONE-01 Pipe Dia 400mm | 345.054 | 28.33 | 9775.3798
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0080-00 | 2026-01-18 | Mechanical FIR Initial Air Test of Storm for Pipeline form MH-28-3 TO MH-28-4 @ ZONE-01 Pipe DIA 400MM | 345.054 | 2.39 | 824.6791
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0125-00 | 2026-02-09 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-21/0 TO MH-6-21/1, @ ZONE-04 | 345.054 | 7.29 | 2515.4437
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0126-00 | 2026-02-09 | Survey FIR for Sand Bedding of Storm Pipeline from MH-6-21/0 TO MH-6-21/1 @ ZONE-04 | 345.054 | 2.43 | 838.4812
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0141-00 | 2026-02-12 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-21/0 TO MH-6-21/1 @ ZONE-04, Pipe DIA 400mm | 345.054 | 29.15 | 10058.3241
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0148-00 | 2026-02-12 | Mechanical FIR Initial Air Test of Storm Pipeline form MH-6-21/0 TO MH-6-21/1, @ ZONE-04 Pipe DIA 400MM | 345.054 | 2.43 | 838.4812
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0160-00 | 2026-02-15 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-18/0 TO MH-6-18/1, @ ZONE-04 | 345.054 | 7.2 | 2484.3888
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0161-00 | 2026-02-15 | Survey FIR for Sand Bedding of Storm Pipeline from MH-6-18/0 TO MH-6-18/1, @ ZONE-04 | 345.054 | 2.4 | 828.1296
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0479-00 | 2026-04-23 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-18/0 TO MH-6-18/1, @ ZONE-04, Pipe DIA 400mm | 345.054 | 28.81 | 9941.0057
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0526 | 2026-05-18 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-14-3 TO MH-14-2, @ ZONE-02 | 345.054 | 11.47 | 3957.7694
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0527-01 | 2026-08-25 | Survey FIR for Bottom of Pipe Concrete Encasement of Storm Pipe Line from MH-14-3 TO MH-14-2, @ ZONE-02 | 345.054 | 3.82 | 1318.1063
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0540 | 2026-05-18 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-2/0 TO MH-6-2-1, @ ZONE-03 | 345.054 | 9.45 | 3260.7603
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0541 | 2026-05-18 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-6-2/0 TO MH-6-2-1, @ ZONE-03 | 345.054 | 3.15 | 1086.9201
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0542 | 2026-05-18 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-2-1 TO MH-6-2-2, @ ZONE-03 | 345.054 | 1.66 | 572.7896
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0543 | 2026-05-18 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-6-2-1 TO MH-6-2-2, @ ZONE-03 | 345.054 | 0.55 | 189.7797
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0544 | 2026-05-18 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-1/0 TO MH-6-1-1, @ ZONE-03 | 345.054 | 10.71 | 3695.5283
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0545 | 2026-05-18 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-6-1/0 TO MH-6-1-1, @ ZONE-03 | 345.054 | 3.57 | 1231.8428
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0546 | 2026-05-18 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-1-1 TO MH-6-1-2, @ ZONE-03 | 345.054 | 2.12 | 731.5145
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0547 | 2026-05-18 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-6-1-1 TO MH-6-1-2, @ ZONE-03 | 345.054 | 0.71 | 244.9883
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0548-01 | 2026-06-08 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-1-2 TO MH-6-1-3, @ ZONE-03 | 345.054 | 1.97 | 679.7564
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0549 | 2026-05-18 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-6-1-2 TO MH-6-1-3, @ ZONE-03 | 345.054 | 0.66 | 227.7356
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0563 | 2026-05-18 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-6-2/0 TO MH-6-2-1, @ ZONE-03 | 345.054 | 37.81 | 13046.4917
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0565 | 2026-05-20 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-6-2-1 TO MH-6-2-2, @ ZONE-03 | 345.054 | 6.64 | 2291.1586
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0567 | 2026-05-20 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-6-2-3 TO MH-6-2-2, @ ZONE-03 | 345.054 | 7.54 | 2601.7072
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0569 | 2026-05-20 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-6-1/0 TO MH-6-1-1, @ ZONE-03 | 345.054 | 42.85 | 14785.5639
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0571 | 2026-05-20 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-6-1-1 TO MH-6-1-2, @ ZONE-03 | 345.054 | 8.46 | 2919.1568
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0572 | 2026-05-20 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-1-6 TO MH-1-5, @ ZONE-02 | 345.054 | 12.03 | 4150.9996
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0575 | 2026-05-20 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-1-6 TO MH-1-5, @ ZONE-02 | 345.054 | 4.01 | 1383.6665
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0584 | 2026-05-21 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-1-6 TO MH-1-5, @ ZONE-02 | 345.054 | 48.11 | 16600.5479
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0615 | 2026-06-04 | Survey FIR for Sand Covering above the Storm Pipe Line from MH-1-6 TO MH-1-5, @ ZONE-02 | 345.054 | 4.01 | 1383.6665
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0639 | 2026-06-08 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-6-1-2 TO MH-6-1-3, @ ZONE-03 | 345.054 | 7.87 | 2715.575
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0856 | 2026-08-11 | Survey FIR for Sand Covering and Compaction Testing above the Storm Pipe Line from MH-6-9-1-3 TO MH-6-9-1-2, @ ZONE-03 | 345.054 | 0.84 | 289.8454
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0857 | 2026-08-11 | Survey FIR for Sand Covering and Compaction Testing above the Storm Pipe Line from MH-6-9-1-2 TO MH-6-9-1-1, @ ZONE-03 | 345.054 | 0.92 | 317.4497
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0858 | 2026-08-11 | Survey FIR for Sand Covering and Compaction Testing above the Storm Pipe Line from MH-6-9-1-1 TO MH-6-9-1/0, @ ZONE-03 | 345.054 | 0.7 | 241.5378
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0859 | 2026-08-11 | Survey FIR for Sand Covering and Compaction Testing above the Storm Pipe Line from MH-6-9-3 TO MH-6-9-2, @ ZONE-03 | 345.054 | 2.68 | 924.7447
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0861 | 2026-08-11 | Survey FIR for Sand Covering and Compaction Testing above the Storm Pipe Line from MH-6-1-9 TO MH-6-1-8, @ ZONE-03 | 345.054 | 2.67 | 921.2942
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0862 | 2026-08-12 | Survey FIR for Sand Covering and Compaction Testing above the Storm Pipe Line from MH-6-1-8 TO MH-6-1-7, (Station 0+171.7To +0+269.7) @ ZONE-03 | 345.054 | 2.9 | 1000.6566
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0863 | 2026-08-12 | Survey FIR for Sand Covering and Compaction Testing above the Storm Pipe Line from MH-6-1-7 TO MH-6-1-6, @ ZONE-03 | 345.054 | 0.81 | 279.4937
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0864 | 2026-08-12 | Survey FIR for Sand Covering and Compaction Testing above the Storm Pipe Line from MH-6-1-6 TO MH-6-1-5, @ ZONE-03 | 345.054 | 0.61 | 210.4829
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0865 | 2026-08-12 | Survey FIR for Sand Covering and Compaction Testing above the Storm Pipe Line from MH-6-1-5 TO MH-6-1-4, @ ZONE-03 | 345.054 | 0.82 | 282.9443
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0866 | 2026-08-12 | Survey FIR for Sand Covering and Compaction Testing above the Storm Pipe Line from MH-6-1-4 TO MH-6-1-3, @ ZONE-03 | 345.054 | 0.6 | 207.0324
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0867 | 2026-08-12 | Survey FIR for Sand Covering and Compaction Testing above the Storm Pipe Line from MH-6-1-2 TO MH-6-1-3, @ ZONE-03 | 345.054 | 0.66 | 227.7356
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0868 | 2026-08-12 | Survey FIR for Sand Covering and Compaction Testing above the Storm Pipe Line from MH-6-1-1 TO MH-6-1-2, @ ZONE-03 | 345.054 | 0.71 | 244.9883
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0870 | 2026-08-12 | Survey FIR for Sand Covering and Compaction Testing above the Storm Pipe Line from MH-6-18/0 TO MH-6-18/1, @ ZONE-04 | 345.054 | 2.4 | 828.1296
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0875-01 | 2026-09-21 | Survey FIR for last layer Compaction Testing the Storm Pipe Line from MH-28-4 TO MH-28-3, @ ZONE-01 | 345.054 | 2.39 | 824.6791
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0877 | 2026-08-12 | Survey FIR for Sand Covering and Compaction Testing above the Storm Pipe Line from MH-17-2 TO MH-17-1, @ ZONE-02 | 345.054 | 2.97 | 1024.8104
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0891 | 2026-08-12 | Survey FIR for Backfill and Compaction Testing 2nd Layer above the Storm Pipe Line from MH-6-1-8 TO MH-6-1-7, (Station 0+171.7To +0+269.7) @ ZONE-03 | 345.054 | 2.9 | 1000.6566
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0893 | 2026-08-12 | Survey FIR for Backfill and Compaction Testing last Layer above the Storm Pipe Line from MH-6-1-7 TO MH-6-1-6, @ ZONE-03 | 345.054 | 0.81 | 279.4937
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0894 | 2026-08-12 | Survey FIR for Backfill and Compaction Testing last Layer above the Storm Pipe Line from MH-6-1-4 TO MH-6-1-3, @ ZONE-03 | 345.054 | 0.59 | 203.5819
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0895 | 2026-08-12 | Survey FIR for Backfill and Compaction Testing last Layer above the Storm Pipe Line from MH-6-1-2 TO MH-6-1-3, @ ZONE-03 | 345.054 | 0.65 | 224.2851
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0979 | 2026-08-25 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-14-1 TO MH-14-2, @ ZONE-02 | 345.054 | 9.26 | 3195.2
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0980 | 2026-08-25 | Survey FIR for Bottom of Pipe Concrete Encasement of Storm Pipe Line from MH-14-1 TO MH-14-2, @ ZONE-02 | 345.054 | 3.09 | 1066.2169
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0981 | 2026-08-25 | Survey and Mechanical FIR for the Installation laying of Storm Pipe Line from MH-14-3 TO MH-14-2, @ ZONE-02 | 345.054 | 45.87 | 15827.627
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0986 | 2026-08-26 | Survey and Mechanical FIR for the Installation laying of Storm Pipe Line from MH-14-1 TO MH-14-2 | 345.054 | 37.02 | 12773.8991
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1154 | 2026-08-28 | Mechanical FIR for Final Air testing of GRP Strom Drainage PIPE from MH-28-3 TO MH-28-4 ROAD 1, ZONE 1 | 345.054 | 2.39 | 824.6791
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1173 | 2026-08-30 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline From MH-6-8-3 TO MH-6-8-2 & MH-6-8-4 TO MH-6-8-3 | 345.054 | 3.94 | 1359.5128
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1174 | 2026-08-30 | Survey FIR for Sand Bedding and Compaction Testing of Storm Pipeline From MH-6-8-3 TO MH-6-8-2 & MH-6-8-4 TO MH-6-8-3 | 345.054 | 1.31 | 452.0207
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1185 | 2026-10-01 | Survey and Mechanical FIR for installation and laying of Storm Pipeline From MH-6-8-3 TO MH-6-8-2 & MH-6-8-4 TO MH-6-8-3 | 345.054 | 15.74 | 5431.15
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1186 | 2026-10-01 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline From MH-6-9-1 TO MH-6-9-0 | 345.054 | 3.95 | 1362.9633
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1187 | 2026-10-01 | Survey FIR for Sand Bedding and Compaction Testing of Storm Pipeline From MH-6-9-1 TO MH-6-9-0 | 345.054 | 1.32 | 455.4713
B6.33 42 11.01 | 400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1192 | 2026-10-03 | Survey and Mechanical FIR for installation and laying of Storm Pipeline From MH-6-9-1 TO MH-6-9-0 | 345.054 | 15.8 | 5451.8532
B6.33 42 11.02 | 400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0488-00 | 2026-04-29 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-17-1 Station (0+020.7 to 0+060.7) TO MH-17-0, @ ZONE-02 | 383.686 | 6 | 2302.116
B6.33 42 11.02 | 400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0489-00 | 2026-05-03 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-17-1 Station (0+020.7 to 0+060.7) TO MH-17-0, @ ZONE-02 | 383.686 | 2 | 767.372
B6.33 42 11.02 | 400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1077 | 2026-09-15 | Survey and Mechanical FIR for installation and laying of Storm Pipe Line from MH-17-1 TO MH-17-0 station (0+020.7 to 0+060.7) @ ZONE-02 | 383.686 | 24 | 9208.464
B6.33 42 11.02 | 400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1260 | 2026-09-17 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline From MH-6-11-1 TO MH-6-11-0 | 383.686 | 8.32 | 3192.2675
B6.33 42 11.02 | 400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1261 | 2026-09-17 | Survey FIR for Sand Bedding and Compaction Testing of Storm Pipeline From MH-6-11-1 TO MH-6-11-0 | 383.686 | 2.77 | 1062.8102
B6.33 42 11.02 | 400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1280 | 2026-09-18 | Survey and Mechanical FIR for Installation and laying of Storm Pipeline From MH-6-11-1 TO MH-6-11-0 | 383.686 | 33.26 | 12761.3964
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0067-00 | 2026-01-14 | Survey FIR for Excavation and Compaction Test of Storm Pipe Line from MH-29-4 TO MH-29-3 @ ZONE-01, Pipe DIA 500mm | 496.948 | 10.25 | 5093.717
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0068-00 | 2026-01-15 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-29-4 TO MH-29-3@ ZONE-01 | 496.948 | 3.42 | 1699.5622
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0072-00 | 2026-01-17 | Mechanical FIR for Installation and Laying of Storm Pipeline form MH-29-4 TO MH-29-3 @ ZONE-01 Pipe DIA 500MM | 496.948 | 41 | 20374.868
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0074-00 | 2026-01-17 | Mechanical FIR Initial Air Test of Storm for Pipeline form MH-29-4 TO MH-29-3 @ ZONE-01 Pipe DIA 500MM | 496.948 | 3.42 | 1699.5622
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0153-00 | 2026-02-14 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-8/0 TO MH-3-8/1, @ ZONE-03 | 496.948 | 13.68 | 6798.2486
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0154-00 | 2026-02-14 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-7/0 TO MH-3-7/1, @ ZONE-03 | 496.948 | 13.8 | 6857.8824
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0156-00 | 2026-02-14 | Survey FIR for Sand Bedding of Storm Pipeline from MH-3-8/0 TO MH-3-8/1, @ ZONE-03 | 496.948 | 4.56 | 2266.0829
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0157-00 | 2026-02-14 | Survey FIR for Sand Bedding of Storm Pipeline from MH-3-7/0 TO MH-3-7/1, @ ZONE-03 | 496.948 | 4.6 | 2285.9608
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0165-00 | 2026-02-15 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-6/0 TO MH-3-6/1, @ ZONE-03 | 496.948 | 7.86 | 3906.0113
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0166-00 | 2026-02-15 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-6/1 TO MH-3-6/2, @ ZONE-03 | 496.948 | 5.87 | 2917.0848
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0168-00 | 2026-02-15 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-3-8/0 TO MH-3-8/1, @ ZONE-03, Pipe DIA 500mm | 496.948 | 54.7 | 27183.0556
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0171-00 | 2026-02-15 | Survey FIR for Sand Bedding of Storm Pipeline from MH-3-6/1 TO MH-3-6/2, @ ZONE-03 | 496.948 | 1.96 | 974.0181
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0172-00 | 2026-02-16 | Survey FIR for Sand Bedding of Storm Pipeline from MH-3-6/0 TO MH-3-6/1, @ ZONE-03 | 496.948 | 2.62 | 1302.0038
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0193-00 | 2026-02-16 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-3-7/0 TO MH-3-7/1, @ ZONE-03, Pipe DIA 500mm | 496.948 | 55.22 | 27441.4686
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0199-00 | 2026-02-18 | Mechanical FIR Initial Air Test of Storm Pipeline form MH-3-8/0 TO MH-3-8/1, @ ZONE-03 Pipe DIA 500MM | 496.948 | 4.56 | 2266.0829
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0201-00 | 2026-02-18 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-3-6/0 TO MH-3-6/1, @ ZONE-03, Pipe DIA 500mm | 496.948 | 31.44 | 15624.0451
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0202-00 | 2026-02-18 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-3-6/1 TO MH-3-6/2, @ ZONE-03, Pipe DIA 500mm | 496.948 | 23.49 | 11673.3085
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0001-03 | 2025-12-28 | Survey Excavation and Compaction Testing FIR for Storm Pipe Line Trench (MH 20-6 to MH-20-5) DIA 500MM, Pipe Co-A20/6, Length: 105.12 m) @ ZONE-01 | 496.948 | 15.5 | 7702.694
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0007-01 | 2025-12-28 | Survey Gravel Bedding FIR of Storm Pipe Line from MH-20-6 TO MH-20-5 @ ZONE-01, Pipe DIA 500mm | 496.948 | 5.17 | 2569.2212
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0029-00 | 2025-12-30 | Mechanical FIR for Installation and Laying of GRP Storm Pipe Line form MH-20-6 TO MH-20-5@ ZONE-01 Pipe Dia 500 mm | 496.948 | 61.99 | 30805.8065
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0050-00 | 2026-01-06 | Mechanical fir initial Air Test of GRP Storm Pipeline from MH-20-6 TO MH-20-5 @ Zone 01 | 496.948 | 5.17 | 2569.2212
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0060-00 | 2026-01-11 | Civil FIR for Backfill 2nd Layer and Compaction Testing of Storm Network from MH-20-6 TO MH-20-5, LINE B @ZONE-01 Pipe DIA 500MM | 496.948 | 5.2 | 2584.1296
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0331-00 | 2026-03-25 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-3-10/0 TO MH-3-10-1, @ ZONE-04 | 496.948 | 4.23 | 2102.09
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0375-00 | 2026-03-26 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-3-10/0 TO MH-3-10-1, @ ZONE-04, Pipe DIA 500mm | 496.948 | 50.72 | 25205.2026
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0405-00 | 2026-03-29 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-8-13 TO MH-8-12, @ ZONE-02 | 496.948 | 4.5 | 2236.266
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0406-00 | 2026-03-29 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-8-12 TO MH-8-11, @ ZONE-02 | 496.948 | 1.15 | 571.4902
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0409-00 | 2026-03-29 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-8-13 TO MH-8-12, @ ZONE-02 | 496.948 | 1.5 | 745.422
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0410-00 | 2026-03-29 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-8-12 TO MH-8-11, @ ZONE-02 | 496.948 | 0.38 | 188.8402
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0480-00 | 2026-04-28 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-18-2 TO MH-18-3, @ ZONE-02 | 496.948 | 11.68 | 5804.3526
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0481-00 | 2026-04-28 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-18-2 TO MH-18-3, @ ZONE-02 | 496.948 | 3.89 | 1933.1277
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0493-00 | 2026-05-04 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-18-2 TO MH-18-3, @ ZONE-02 | 496.948 | 46.7 | 23207.4716
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0512-00 | 2026-05-13 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-4-4 TO MH-4-3, @ ZONE-03 | 496.948 | 8.59 | 4268.7833
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0513-00 | 2026-05-13 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-4-3 TO MH-4-2, @ ZONE-03 | 496.948 | 1.83 | 909.4148
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0514 | 2026-05-14 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-4-2 TO MH-4-1, @ ZONE-03 | 496.948 | 2.79 | 1386.4849
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0515 | 2026-05-14 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-4-1 TO MH-4-0, @ ZONE-03 | 496.948 | 3.54 | 1759.1959
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0516 | 2026-05-14 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-4-4 TO MH-4-3, @ ZONE-03 | 496.948 | 2.86 | 1421.2713
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0517 | 2026-05-14 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-4-3 TO MH-4-2, @ ZONE-03 | 496.948 | 0.61 | 303.1383
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0518 | 2026-05-14 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-4-2 TO MH-4-1, @ ZONE-03 | 496.948 | 0.93 | 462.1616
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0519 | 2026-05-14 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-4-1 TO MH-4-0, @ ZONE-03 | 496.948 | 1.18 | 586.3986
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0531 | 2026-05-17 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-4-4 TO MH-4-3, @ ZONE-03 | 496.948 | 34.37 | 17080.1028
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0533 | 2026-05-17 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-4-3 TO MH-4-2, @ ZONE-03 | 496.948 | 7.34 | 3647.5983
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0535 | 2026-05-17 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-4-2 TO MH-4-1, @ ZONE-03 | 496.948 | 11.17 | 5550.9092
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0537 | 2026-05-17 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-4-1 TO MH-4/0 (from station 0+010.80 to 0+025.20) @ ZONE-03 | 496.948 | 8.64 | 4293.6307
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0573 | 2026-05-20 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-1-5 TO MH-1-4, @ ZONE-02 | 496.948 | 10.35 | 5143.4118
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0574 | 2026-05-20 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-1-4 TO MH-1-3, @ ZONE-02 | 496.948 | 10.3 | 5118.5644
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0576 | 2026-05-20 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-1-5 TO MH-1-4, @ ZONE-02 | 496.948 | 3.45 | 1714.4706
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0577 | 2026-05-20 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-1-4 TO MH-1-3, @ ZONE-02 | 496.948 | 3.43 | 1704.5316
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0583 | 2026-05-21 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-1-3 TO MH-1-2, @ ZONE-02 | 496.948 | 10.28 | 5108.6254
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0585 | 2026-05-21 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-1-5 TO MH-1-4, @ ZONE-02 | 496.948 | 41.39 | 20568.6777
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0586 | 2026-05-21 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-1-4 TO MH-1-3, @ ZONE-02 | 496.948 | 41.21 | 20479.2271
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0587 | 2026-05-21 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-1-3 TO MH-1-2, @ ZONE-02 | 496.948 | 3.43 | 1704.5316
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0591 | 2026-05-23 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-1-3 TO MH-1-2, @ ZONE-02 | 496.948 | 41.14 | 20444.4407
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0616 | 2026-06-04 | Survey FIR for Sand Covering above the Storm Pipe Line from MH-1-5 TO MH-1-4, @ ZONE-02 | 496.948 | 3.45 | 1714.4706
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0617 | 2026-06-04 | Survey FIR for Sand Covering above the Storm Pipe Line from MH-1-4 TO MH-1-3, @ ZONE-02 | 496.948 | 3.43 | 1704.5316
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0618 | 2026-06-04 | Survey FIR for Sand Covering above the Storm Pipe Line from MH-1-3 TO MH-1-2, @ ZONE-02 | 496.948 | 3.43 | 1704.5316
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0807 | 2026-07-11 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-1-2 TO MH-1-1, @ Arterial Road | 496.948 | 13.32 | 6619.3474
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0808 | 2026-07-11 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-1-2 TO MH-1-1, @ Arterial Road | 496.948 | 4.44 | 2206.4491
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0828 | 2026-07-21 | Mechanical FIR for the Installation and Laying of Strom Pipe Line network From MH-1-1 to MH-1-2) @ Arterial Road | 496.948 | 53.29 | 26482.3589
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0842 | 2026-08-08 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline From MH-3-21 To MH-3-20 @ ZONE-04 | 496.948 | 2.72 | 1351.6986
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0843 | 2026-08-08 | Survey FIR for Sand Bedding and Compaction testing of Storm Pipeline From MH-3-21 To MH-3-20 @ ZONE-04 | 496.948 | 0.91 | 452.2227
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0852 | 2026-08-11 | Survey FIR for Sand Covering and Compaction Testing above the Storm Pipe Line from MH-4-2 TO MH-4-1, @ ZONE-03 | 496.948 | 0.93 | 462.1616
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0853 | 2026-08-11 | Survey FIR for Sand Covering and Compaction Testing above the Storm Pipe Line from MH-4-1 TO MH-4/0 (from station 0+010.80 to 0+025.20), @ ZONE-03 | 496.948 | 0.72 | 357.8026
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0860-01 | 2026-09-21 | Survey and Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-8-12 TO MH-8-11, @ ZONE-02 | 496.948 | 4.59 | 2280.9913
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0871 | 2026-08-12 | Survey FIR for Sand Covering and Compaction Testing above the Storm Pipe Line from MH-3-8/0 TO MH-3-8/1, @ ZONE-03 | 496.948 | 4.56 | 2266.0829
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0872 | 2026-08-12 | Survey FIR for Sand Covering and Compaction Testing above the Storm Pipe Line from MH-3-7/0 TO MH-3-7/1, @ ZONE-03 | 496.948 | 4.6 | 2285.9608
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0873 | 2026-08-12 | Survey FIR for Sand Covering and Compaction Testing above the Storm Pipe Line from MH-3-6/0 TO MH-3-6/1, @ ZONE-03 | 496.948 | 2.62 | 1302.0038
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0878 | 2026-08-12 | Survey FIR for Sand Covering and Compaction Testing above the Storm Pipe Line from MH-18-2 TO MH-18-3, @ ZONE-04 | 496.948 | 3.89 | 1933.1277
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0879 | 2026-08-12 | Survey FIR for Sand Covering and Compaction Testing above the Storm Pipe Line from MH-8-12 TO MH-8-11, @ ZONE-02 | 496.948 | 0.38 | 188.8402
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0888 | 2026-08-12 | Survey FIR for Backfill and Compaction Testing last Layer above the Storm Pipe Line from MH-3-8/0 TO MH-3-8/1, @ ZONE-03 | 496.948 | 4.56 | 2266.0829
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0889 | 2026-08-12 | Survey FIR for Backfill and Compaction Testing last Layer above the Storm Pipe Line from MH-3-7/0 TO MH-3-7/1, @ ZONE-03 | 496.948 | 4.6 | 2285.9608
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0890 | 2026-08-12 | Survey FIR for Backfill and Compaction Testing last Layer above the Storm Pipe Line from MH-3-6/0 TO MH-3-6/1, @ ZONE-03 | 496.948 | 2.62 | 1302.0038
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0928 | 2026-08-16 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline From MH-8-4-2 TO MH-8-4-3 | 496.948 | 12.12 | 6023.0098
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0929 | 2026-08-16 | Survey FIR for Sand Bedding and Compaction testing of Storm Pipeline From MH-8-4-2 TO MH-8-4-3 | 496.948 | 4.04 | 2007.6699
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0975 | 2026-08-25 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline From MH-1-1 TO MH-1-0 | 496.948 | 13.61 | 6763.4623
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0976 | 2026-08-25 | Survey FIR for Sand Bedding and Compaction testing of Storm Pipeline From MH-1-1 TO MH-1-0 | 496.948 | 4.54 | 2256.1439
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0984 | 2026-08-26 | Survey and Mechanical FIR for the Installation laying of Storm Pipe Line From MH-1-1 TO MH-1-0 | 496.948 | 54.42 | 27043.9102
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0995-01 | 2026-10-06 | Survey and Mechanical FIR for installation and laying of Storm Pipeline From MH-8-4-2 TO MH-8-4-3 | 496.948 | 48.47 | 24087.0696
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-1155 | 2026-09-28 | Mechanical FIR for Final Air testing of GRP Strom Drainage PIPE from MH-20-6 TO MH-20-5 ROAD 1, ZONE 1 | 496.948 | 10.41 | 5173.2287
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-1284 | 2026-10-18 | Mechanical FIR for Final Air testing of GRP Strom Drainage PIPE from 1. MH-3-7 to MH-3-7-1 (92.03x0.10=9.20 m) 2. MH-3-8 to MH-3-8-1 (91.17x0.05=4.56 m (FIR # 0199) Road-2 & Plot-D , ZONE- 03 | 496.948 | 13.76 | 6838.0045
B6.33 42 11.03 | 500mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-1305 | 2026-10-19 | Mechanical FIR for Final Air testing of GRP Strom Drainage PIPE from 1. MH-3-6 to MH-3-6-1 Plot-D , ZONE- 03 | 496.948 | 5.24 | 2604.0075
B6.33 42 11.04 | 500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0019-00 | 2025-12-22 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-28-3 TO MH-28-2 @ ZONE-01, Pipe DIA 500mm | 578.602 | 12.13 | 7018.4423
B6.33 42 11.04 | 500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0021-01 | 2025-12-27 | Survey FIR for Gravel Bedding of Storm Pipe Line from MH-28-3 TO MH-28-2 @ Zone-01, Pipe DIA 500mm | 578.602 | 4.04 | 2337.5521
B6.33 42 11.04 | 500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0027-00 | 2025-12-28 | Mechanical FIR for Installation and Laying of GRP Storm Pipe Line form MH-28-3 TO MH-28-2@ ZONE-01 Pipe Dia 400mm | 578.602 | 48.5 | 28062.197
B6.33 42 11.04 | 500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0038-00 | 2026-01-01 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-29-2 TO MH-29-1(From station 0+040.84 to station 0+084.94) @ ZONE-01, Pipe DIA 500mm | 578.602 | 6.62 | 3830.3452
B6.33 42 11.04 | 500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0040-00 | 2026-01-03 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-29-3 TO MH-29-2 @ ZONE-01, Pipe DIA 500mm | 578.602 | 9.51 | 5502.505
B6.33 42 11.04 | 500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0042-00 | 2026-01-04 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-29-2 TO MH-29-1(From station 0+040.84 to station 0+084.94) @ ZONE-01, | 578.602 | 2.21 | 1278.7104
B6.33 42 11.04 | 500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0043-00 | 2026-01-04 | Survey FIR for Sand Bedding of Storm Pipe Line From MH-29-3 TO MH-29-2 @ ZONE-01 | 578.602 | 3.17 | 1834.1683
B6.33 42 11.04 | 500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0048-00 | 2026-01-06 | Mechanical Installation and Laying of GRP Storm Pipeline from MH-29-2 TO MH-29-1(From station 0+040.84 to station 0+084.94) @ ZONE-01, Pipe DIA 500mm | 578.602 | 26.46 | 15309.8089
B6.33 42 11.04 | 500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0049-00 | 2026-01-06 | Mechanical FIR For Installation and Laying of GRP Storm Pipeline from MH-29-3 TO MH-29-2 @ ZONE-01, Pipe DIA 500mm | 578.602 | 38.04 | 22010.0201
B6.33 42 11.04 | 500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0056-00 | 2026-01-08 | Mechanical fir initial Air Test of GRP Storm Pipeline from MH-29-2 TO MH-29-1 (From station 0+040.84 to station 0+084.94) @ ZONE-01, Pipe DIA 500mm | 578.602 | 2.21 | 1278.7104
B6.33 42 11.04 | 500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0057-00 | 2026-01-08 | Mechanical fir initial Air Test of GRP Storm Pipeline from MH-29-3 To MH-29-2 @ ZONE-01, Pipe DIA 500mm | 578.602 | 3.17 | 1834.1683
B6.33 42 11.04 | 500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0079-00 | 2026-01-18 | Mechanical FIR Initial Air Test of Storm for Pipeline form MH-28-2 TO MH-28-3 @ ZONE-01 Pipe DIA 500MM | 578.602 | 4.07 | 2354.9101
B6.33 42 11.04 | 500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0330-00 | 2026-03-25 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-10/0 TO MH-3-10-1, @ ZONE-04 | 578.602 | 12.68 | 7336.6734
B6.33 42 11.04 | 500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0876 | 2026-08-12 | Survey FIR for 2nd layer Compaction Testing the Storm Pipe Line from MH-28-3 TO MH-28-2, @ ZONE-01 | 578.602 | 4.1 | 2372.2682
B6.33 42 11.04 | 500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0896 | 2026-08-12 | Survey FIR for Backfill and Compaction Testing 2nd Layer above the Storm Pipe Line from MH-3-10/0 TO MH-3-10-1, @ ZONE-04 | 578.602 | 4.23 | 2447.4865
B6.33 42 11.04 | 500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0962 | 2026-08-22 | Survey FIR for Backfill and Compaction Testing 4th Layer above the Storm Pipe Line from MH-28-3 TO MH-28-2, @ ZONE-01 | 578.602 | 4.1 | 2372.2682
B6.33 42 11.04 | 500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1071-01 | 2026-10-05 | Survey FIR for Backfill and Compaction Testing 2nd Layer above the Storm Drainage Network Line A28 & Line A29 From MH-28 TO MH-28-1 MH-29-1 TO MH-29-2 (Station 0+040.84 to 0+084.94) MH-29-2 TO MH-29-3 @ Road 1 - ZONE-01 | 578.602 | 3.2 | 1851.5264
B6.33 42 11.04 | 500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1072-01 | 2026-10-05 | Survey FIR for Backfill and Compaction Testing 3rd Layer above the Storm Drainage Network Line A28 & Line A29 From MH-28 TO MH-28-1, MH-29-1 TO MH-29-2 (Station 0+040.84 to 0+084.94) MH-29-2 TO MH-29-3, @ Road 1 - ZONE-01 | 578.602 | 5.41 | 3130.2368
B6.33 42 11.04 | 500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1089-01 | 2026-10-05 | Survey FIR for Backfill and Compaction Testing 5th Layer above the Storm Drainage from MH-28 TO MH-28-1 MH-29-1 TO MH-29-2 (Station 0+040.84 to 0+084.94) @ Road 1 - ZONE-01 | 578.602 | 2.2 | 1272.9244
B6.33 42 11.04 | 500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1150 | 2026-09-27 | Mechanical FIR for Final Air testing of GRP Storm Drainage PIPE from MH-28-2 to MH-28-3 @ RD-1 , ZONE-01 | 578.602 | 4.1 | 2372.2682
B6.33 42 11.05 | 500mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0011-01 | 2025-12-28 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-28-1 TO MH-28-2 @ ZONE-01, Pipe DIA 500mm | 720.838 | 9.95 | 7172.3381
B6.33 42 11.05 | 500mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0013-02 | 2025-12-31 | Survey FIR for Gravel Bedding of Storm Pipe Line from MH-28-2TO MH-28-1 @ Zone-01, Pipe DIA 500mm | 720.838 | 3.32 | 2393.1822
B6.33 42 11.05 | 500mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0016-01 | 2025-12-27 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-28-0 TO MH-28-1 @ ZONE-01, Pipe DIA 500mm | 720.838 | 7.53 | 5427.9101
B6.33 42 11.05 | 500mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0018-02 | 2025-12-31 | Survey FIR for Gravel Bedding of Storm Pipe Line from MH-28-1 TO MH-28-0 @ Zone-01, Pipe DIA 500mm | 720.838 | 2.51 | 1809.3034
B6.33 42 11.05 | 500mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0037-00 | 2026-01-01 | Mechanical FIR for Installation of GRP Storm Pipe Line from MH-28-2TO MH-28-1 @ Zone-01, Pipe DIA 500mm | 720.838 | 39.81 | 28696.5608
B6.33 42 11.05 | 500mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0039-00 | 2026-01-01 | Mechanical FIR for Installation and Laying of GRP Storm Pipe Line form MH-28-1 TO MH-28/0 (From Station 0+017.42 To Station 0+051.52) @ ZONE-01 Pipe DIA 500mm | 720.838 | 20.46 | 14748.3455
B6.33 42 11.05 | 500mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0075-00 | 2026-01-17 | Mechanical FIR Initial Air Test of Storm for Pipeline form MH-28-0 TO MH-28-1 (From Station 0+017.42 To Station 0+051.52) @ ZONE-01 Pipe DIA 500MM | 720.838 | 1.71 | 1232.633
B6.33 42 11.05 | 500mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0076-00 | 2026-01-17 | Mechanical FIR Initial Air Test of Storm for Pipeline form MH-28-1 TO MH-28-2 @ ZONE-01 Pipe DIA 500MM | 720.838 | 3.35 | 2414.8073
B6.33 42 11.05 | 500mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0953-00 | 2026-08-20 | Survey FIR for Backfill and Compaction Testing 3rd Layer above the Storm Pipe Line from MH-28-2 TO MH-28-1, @ ZONE-01 | 720.838 | 3.35 | 2414.8073
B6.33 42 11.05 | 500mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1088 | 2026-09-15 | Survey FIR for Backfill and Compaction Testing 4th Layer above the Storm Drainage from MH-28 TO MH-28-1 MH-29-1 TO MH-29-2 (Station 0+040.84 to 0+084.94) @ Road 1 - ZONE-01 | 720.838 | 2.56 | 1845.3453
B6.33 42 11.05 | 500mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1100 | 2026-09-17 | Survey FIR for Backfill and Compaction Testing 7th Layer above the Storm Drainage from MH-28 TO MH-28-1 @ Road 1 - ZONE-01 | 720.838 | 2.56 | 1845.3453
B6.33 42 11.05 | 500mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1138 | 2026-10-14 | Mechanical FIR for Final Air testing of GRP Storm Drainage PIPE from MH-28-1 to MH-28-2 @ RD-1 , ZONE-01 | 720.838 | 3.33 | 2400.3905
B6.33 42 11.06 | 600mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0167-00 | 2026-02-15 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-5/0 TO MH-3-5/1, @ ZONE-03 | 717.326 | 8.28 | 5939.4593
B6.33 42 11.06 | 600mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0173-00 | 2026-02-16 | Survey FIR for Sand Bedding of Storm Pipeline from MH-3-5/0 TO MH-3-5/1, @ ZONE-03 | 717.326 | 2.76 | 1979.8198
B6.33 42 11.06 | 600mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0203-00 | 2026-02-18 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-3-5/0 TO MH-3-5/1, @ ZONE-03, Pipe DIA 600mm | 717.326 | 33.14 | 23772.1836
B6.33 42 11.07 | 600mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0332-00 | 2026-03-25 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-17-2 TO MH-3-17-1, @ ZONE-04 | 717.326 | 3.31 | 2374.3491
B6.33 42 11.07 | 600mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0334-00 | 2026-03-25 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-17-3 TO MH-3-17-2, @ ZONE-04 | 717.326 | 15.51 | 11125.7263
B6.33 42 11.07 | 600mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0335-00 | 2026-03-25 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-3-17-3 TO MH-3-17-2, @ ZONE-04 | 717.326 | 5.17 | 3708.5754
B6.33 42 11.07 | 600mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0348-00 | 2026-03-25 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-13-3 TO MH-3-13-2, @ ZONE-04 | 717.326 | 11.62 | 8335.3281
B6.33 42 11.07 | 600mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0349-00 | 2026-03-25 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-3-13-3 TO MH-3-13-2, @ ZONE-04 | 717.326 | 3.87 | 2776.0516
B6.33 42 11.07 | 600mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0373-00 | 2026-03-26 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-3-13-3 TO MH-3-13-2, @ ZONE-04, Pipe DIA 700mm | 717.326 | 46.48 | 33341.3125
B6.33 42 11.06 | 600mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0674-00 | 2026-06-18 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline MH-3-20 TO MH-3-19, @ ZONE-04 | 717.326 | 10.52 | 7546.2695
B6.33 42 11.06 | 600mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0675-00 | 2026-06-18 | Survey FIR for Sand Bedding of Storm Pipeline MH-3-20 TO MH-3-19, @ ZONE-04 | 717.326 | 3.51 | 2517.8143
B6.33 42 11.06 | 600mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0788-00 | 2026-07-05 | Mechanical FIR for Installation and Laying of Storm Pipe Line with Short Piece from MH-3-17-2 TO MH-3-17-1, @ ZONE-04 | 717.326 | 13.25 | 9504.5695
B6.33 42 11.06 | 600mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0850 | 2026-08-11 | Survey FIR for Sand Covering and Compaction Testing above the Storm Pipe Line from MH-3-13-3 TO MH-3-13-2, @ ZONE-04 | 717.326 | 3.87 | 2776.0516
B6.33 42 11.06 | 600mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0874 | 2026-08-12 | Survey FIR for Sand Covering and Compaction Testing above the Storm Pipe Line from MH-3-5/0 TO MH-3-5/1, @ ZONE-03 | 717.326 | 2.76 | 1979.8198
B6.33 42 11.06 | 600mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0941 | 2026-08-18 | Survey and Mechanical FIR for the Installation and Laying of Storm Pipeline MH-3-20 TO MH-3-19, @ ZONE-04 | 717.326 | 42.09 | 30192.2513
B6.33 42 11.06 | 600mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0944 | 2026-08-20 | Survey FIR for Backfill and Compaction Testing of the Final Backfill Layer above the Storm Pipe Line from MH-3-17-3 TO MH-3-17-2, @ ZONE-04 | 717.326 | 10.34 | 7417.1508
B6.33 42 11.06 | 600mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0996 | 2026-08-30 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline From MH-8-4-2 TO MH-8-4-1 | 717.326 | 8.37 | 6004.0186
B6.33 42 11.06 | 600mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0997 | 2026-08-30 | Survey FIR for Sand bedding and Compaction Testing of Storm Pipeline From MH-8-4-2 TO MH-8-4-1 | 717.326 | 2.79 | 2001.3395
B6.33 42 11.06 | 600mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-1075 | 2026-09-15 | Survey and Backfill Compaction Test FIR for the 1st Layer of Sand Covering above the Pipeline of the Storm Network from: MH-3-14 TO MH-3-15 dia 1100 mm MH-3-17-1 To MH-3-17-2 dia 600 mm @ Zone-04. | 717.326 | 1.1 | 789.0586
B6.33 42 11.06 | 600mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-1207 | 2026-10-05 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from MH-3-17-1 to MH-3-17-2 Road-3 , ZONE 4 | 717.326 | 2.21 | 1585.2905
B6.33 42 11.06 | 600mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-1224 | 2026-10-08 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from MH-3-17-2 to MH-3-17-3 Road-3 , ZONE 4 | 717.326 | 10.34 | 7417.1508
B6.33 42 11.06 | 600mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-1272 | 2026-10-17 | Survey FIR for Excavation and compaction testing of GRP Strom Drainage PIPE from 1. MH-8-8 to MH-8-9 2. MH-8-9 to MH-8-10 3. MH-8-10 to MH-8-11 ZONE- 02 | 717.326 | 10.59 | 7596.4823
B6.33 42 11.06 | 600mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-1273 | 2026-10-17 | Survey FIR for Sand bedding and compaction testing of GRP Strom Drainage PIPE from 1. MH-8-8 to MH-8-9 2. MH-8-9 to MH-8-10 3. MH-8-10 to MH-8-11 ZONE- 02 | 717.326 | 3.53 | 2532.1608
B6.33 42 11.06 | 600mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-1282 | 2026-10-18 | Survey and mechanical FIR for installation and laying of GRP Strom Drainage PIPE from 1. MH-8-8 to MH-8-9 2. MH-8-9 to MH-8-10 3. MH-8-10 to MH-8-11 ZONE- 02 | 717.326 | 42.38 | 30400.2759
B6.33 42 11.07 | 600mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0022-00 | 2025-12-25 | Survey Excavation and Compaction Testing FIR for Storm Pipe Line from MH-20-5 TO MH-20-4 @ Zone-01, Pipe DIA 600mm | 846.392 | 11.37 | 9623.477
B6.33 42 11.07 | 600mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0023-00 | 2025-12-25 | Survey FIR for Geotextile and Gravel Bedding of Storm Pipe Line from MH-20-5 TO MH-20-4 @ Zone-01, Pipe DIA 600mm | 846.392 | 3.79 | 3207.8257
B6.33 42 11.07 | 600mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0032-00 | 2025-12-30 | Survey FIR For Installation and Laying of GRP Storm Pipe Line from H-20-5 TO MH-20-4@ ZONE-01 Pipe Dia 600 mm | 846.392 | 45.5 | 38510.836
B6.33 42 11.07 | 600mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0051-00 | 2026-01-06 | Mechanical fir initial Air Test of GRP Storm Pipeline from MH-20-5 TO MH-20-4 @ Zone 01 | 846.392 | 3.79 | 3207.8257
B6.33 42 11.07 | 600mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0064-00 | 2026-01-14 | Civil FIR for Backfill and Compaction Test 3rd Layer above the Pipeline of Storm Network from MH-20-5 TO MH-20-4, LINE B @ZONE-01 Pipe DIA 600MM | 846.392 | 3.82 | 3233.2174
B6.33 42 11.07 | 600mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0095-00 | 2026-01-29 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-25 TO MH-6-24 @ ZONE-04, Pipe DIA 600mm | 846.392 | 11.83 | 10012.8174
B6.33 42 11.07 | 600mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0098-00 | 2026-01-31 | Survey FIR for Sand Bedding of Storm Pipeline from MH-6-25 TO MH-6-24, @ ZONE-04 | 846.392 | 3.94 | 3334.7845
B6.33 42 11.07 | 600mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0105-00 | 2026-02-02 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-25 TO MH-6-24, @ ZONE-04, Pipe DIA 600mm | 846.392 | 47.33 | 40059.7334
B6.33 42 11.07 | 600mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0110-00 | 2026-02-02 | Mechanical FIR Initial Air Test of Storm Pipeline form MH-6-25 TO MH-6-24, @ ZONE-04 Pipe DIA 600MM | 846.392 | 3.94 | 3334.7845
B6.33 42 11.07 | 600mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0117-00 | 2026-02-04 | Survey FIR for Backfill and Compaction Testing 2nd Layer above the Storm Pipeline from MH-6-25 TO MH-6-24, @ ZONE-04 | 846.392 | 3.94 | 3334.7845
B6.33 42 11.07 | 600mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0333-00 | 2026-03-25 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-3-17-2 TO MH-3-17-1, @ ZONE-04 | 846.392 | 1.1 | 931.0312
B6.33 42 11.07 | 600mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0360-00 | 2026-03-26 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-3-17-3 TO MH-3-17-2, @ ZONE-04, Pipe DIA 600mm | 846.392 | 62.02 | 52493.2318
B6.33 42 11.07 | 600mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0484-00 | 2026-04-29 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-18-1 TO MH-18-2, @ ZONE-02 | 846.392 | 11.69 | 9894.3225
B6.33 42 11.07 | 600mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0485-00 | 2026-04-29 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-18-1 TO MH-18-2, @ ZONE-02 | 846.392 | 3.9 | 3300.9288
B6.33 42 11.07 | 600mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0954-00 | 2026-08-20 | Survey FIR for Backfill and Compaction Test for 4th Layer above the Pipeline of Storm Network from MH-20-5 TO MH-20-4, LINE B @ ZONE-01 Pipe DIA 600MM | 846.392 | 3.82 | 3233.2174
B6.33 42 11.07 | 600mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1287 | 2026-10-18 | Mechanical FIR for Final Air testing of GRP Strom Drainage PIPE from 1. MH-20-4 to MH-20-5 Road-1 , ZONE- 01 | 846.392 | 3.81 | 3224.7535
B6.33 42 11.09 | 700mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0337-00 | 2026-03-25 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-17-1 TO MH-3-17-0, @ ZONE-04 | 803.37 | 7.14 | 5736.0618
B6.33 42 11.09 | 700mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0356-00 | 2026-03-26 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-3-17-1 TO MH-3-17-0, @ ZONE-04 | 803.37 | 2.38 | 1912.0206
B6.33 42 11.09 | 700mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0358-00 | 2026-03-26 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-3-17-1 TO MH-3-17-0, @ ZONE-04, Pipe DIA 700mm | 803.37 | 28.58 | 22960.3146
B6.33 42 11.09 | 700mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0458-00 | 2026-04-01 | Survey FIR for Backfill and Compaction Testing 2nd Layer above the Storm Pipeline from MH-3-17-1 TO MH-3-17-0 @ ZONE-04, Pipe DIA 700mm | 803.37 | 2.38 | 1912.0206
B6.33 42 11.09 | 700mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0672-00 | 2026-06-18 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline MH-3-19 TO MH-3-18, @ ZONE-04 | 803.37 | 15.49 | 12444.2013
B6.33 42 11.09 | 700mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0673-00 | 2026-06-18 | Survey FIR for Sand Bedding of Storm Pipeline MH-3-19 TO MH-3-18, @ ZONE-04 | 803.37 | 5.16 | 4145.3892
B6.33 42 11.09 | 700mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0715-01 | 2026-07-02 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-3-19 TO MH-3-18, @ ZONE-04 | 803.37 | 61.96 | 49776.8052
B6.33 42 11.09 | 700mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-0847 | 2026-08-09 | Survey FIR for Sand Covering and Compaction Testing above the Storm Pipe Line from MH-3-19 TO MH-3-18, @ ZONE-04 | 803.37 | 5.16 | 4145.3892
B6.33 42 11.09 | 700mm Diameter Depth less than 1.5 | DAM2-02-09-SAJ-TS9-1-STR-FIR-1206 | 2026-10-05 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from MH-3-17-0 to MH-3-17-1 Road-3 , ZONE 4 | 803.37 | 4.76 | 3824.0412
B6.33 42 11.10 | 700mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0024-00 | 2025-12-28 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-20-4 TO MH-20-3 (From Station 0+160.98 To Station 0+184.95) @ ZONE-01 | 920.144 | 3.6 | 3312.5184
B6.33 42 11.10 | 700mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0030-00 | 2025-12-30 | Survey FIR for Geotextile and Gravel Bedding of Storm Pipe MH-20-4 TO MH-20-3 (From Station 0+160.98 To Station 0+184.95) @ ZONE-01 | 920.144 | 1.2 | 1104.1728
B6.33 42 11.10 | 700mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0229-00 | 2026-02-23 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-20-4 TO MH-20-3 (From Station 0+184.95 To Station +264.5) @ ZONE-01 | 920.144 | 11.93 | 10977.3179
B6.33 42 11.10 | 700mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0232-00 | 2026-02-24 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-20-4 TO MH-20-3 (From Station 0+184.95 To Station +264.6), @ ZONE-01 | 920.144 | 3.98 | 3662.1731
B6.33 42 11.10 | 700mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0239-00 | 2026-02-28 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-20-4 TO MH-20-3, @ ZONE-01, Pipe DIA 700mm | 920.144 | 62.11 | 57150.1438
B6.33 42 11.10 | 700mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0346-00 | 2026-03-25 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-13-2 TO MH-3-13-1, @ ZONE-04 | 920.144 | 3.63 | 3340.1227
B6.33 42 11.10 | 700mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0347-00 | 2026-03-25 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-3-13-2 TO MH-3-13-1, @ ZONE-04 | 920.144 | 1.21 | 1113.3742
B6.33 42 11.10 | 700mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0371-00 | 2026-03-26 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-3-13-2 TO MH-3-13-1, @ ZONE-04, Pipe DIA 700mm | 920.144 | 14.54 | 13378.8938
B6.33 42 11.10 | 700mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0094-00 | 2026-01-29 | Survey Excavation and Compaction Test of Storm Pipe MH-20-4 TO MH-20-3 (From Station 0+160.98 To Station 0+184.95) @ ZONE-01 | 920.144 | 10.45 | 9615.5048
B6.33 42 11.10 | 700mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0097-00 | 2026-01-31 | Survey FIR for Sand Bedding of Storm Pipeline from MH-6-24 TO MH-6-23, @ ZONE-04 | 920.144 | 3.48 | 3202.1011
B6.33 42 11.10 | 700mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0106-00 | 2026-02-02 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-24 TO MH-6-23, @ ZONE-04, Pipe DIA 700mm | 920.144 | 41.79 | 38452.8178
B6.33 42 11.10 | 700mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0111-00 | 2026-02-02 | Mechanical FIR Initial Air Test of Storm Pipeline form MH-6-24 TO MH-6-23, @ ZONE-04 Pipe DIA 700MM | 920.144 | 3.48 | 3202.1011
B6.33 42 11.10 | 700mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0885 | 2026-08-12 | Survey FIR for Backfill and Compaction Testing 2nd Layer above the Storm Pipe Line from MH-20-4 TO MH-20-3, @ ZONE-01 | 920.144 | 5.18 | 4766.3459
B6.33 42 11.10 | 700mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0948 | 2026-08-20 | Survey FIR for Backfill and Compaction Testing 3rd Layer above the Storm Pipeline from MH-6-24 TO MH-6-23, @ ZONE-04 | 920.144 | 3.48 | 3202.1011
B6.33 42 11.10 | 700mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0964 | 2026-08-22 | Survey FIR for Backfill and Compaction Testing 4th Layer above the Storm Pipe Line from MH-20-4 TO MH-20-3, @ ZONE-01 | 920.144 | 5.18 | 4766.3459
B6.33 42 11.10 | 700mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1270 | 2026-10-17 | Survey FIR for Excavation and compaction testing of GRP Strom Drainage PIPE from 1. MH-8-7 to MH-8-8 ZONE- 02 | 920.144 | 1.75 | 1610.252
B6.33 42 11.10 | 700mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1271 | 2026-10-17 | Survey FIR for Sand bedding and compaction testing of GRP Strom Drainage PIPE from 1. MH-8-7 to MH-8-8 ZONE- 02 | 920.144 | 0.58 | 533.6835
B6.33 42 11.10 | 700mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1281 | 2026-10-18 | Survey and mechanical FIR for installation and laying of GRP Strom Drainage PIPE from 1. MH-8-7 to MH-8-8 ZONE- 02 | 920.144 | 7.01 | 6450.2094
B6.33 42 11.10 | 700mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1286 | 2026-10-18 | Mechanical FIR for Final Air testing of GRP Strom Drainage PIPE from 1. MH-20-3 to MH-20-4 Road-1 , ZONE- 01 | 920.144 | 10.35 | 9523.4904
B6.33 42 11.12 | 800mm Diameter Depth: less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0926 | 2026-08-16 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline From MH-8-4-1 TO MH-8-4 | 924.534 | 6.94 | 6416.266
B6.33 42 11.12 | 800mm Diameter Depth: less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0927 | 2026-08-16 | Survey FIR for Sand Bedding and Compaction testing of Storm Pipeline From MH-8-4-1 TO MH-8-4 | 924.534 | 2.31 | 2135.6735
B6.33 42 11.12 | 800mm Diameter Depth: less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1168 | 2026-09-30 | Survey and Mechanical FIR for installation and laying of Storm Pipeline From MH-8-4-1 TO MH-8-4 | 924.534 | 27.75 | 25655.8185
B6.33 42 11.12 | 800mm Diameter Depth: less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1169 | 2026-09-30 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline From MH-14-1 TO MH-14-0 | 924.534 | 10.57 | 9772.3244
B6.33 42 11.12 | 800mm Diameter Depth: less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1170 | 2026-09-30 | Survey FIR for Sand Bedding and Compaction Testing of Storm Pipeline From MH-14-1 TO MH-14-0 | 924.534 | 3.52 | 3254.3597
B6.33 42 11.12 | 800mm Diameter Depth: less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1183 | 2026-10-01 | Survey and Mechanical FIR for Installation and laying of Storm Pipeline From MH-14-1 TO MH-14-0 | 924.534 | 42.26 | 39070.8068
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0343-00 | 2026-03-25 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-13-1 TO MH-3-13-0, @ ZONE-04 | 1031.65 | 7.06 | 7283.449
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0344-00 | 2026-03-25 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-3-13-1 TO MH-3-13-0, @ ZONE-04 | 1031.65 | 2.35 | 2424.3775
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0369-00 | 2026-03-26 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-3-13-1 TO MH-3-13-0, @ ZONE-04, Pipe DIA 800mm | 1031.65 | 28.24 | 29133.796
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0025-00 | 2025-12-28 | Survey Excavation and Compaction Testing FIR for Storm Pipe Line from MH-20-3 TO MH-20-2 @ Zone-01 | 1031.65 | 5.23 | 5395.5295
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0031-00 | 2025-12-30 | Survey FIR for Geotextile and Gravel Bedding of Storm Pipe from MH-20-3 TO MH-20-2 @ ZONE-01 | 1031.65 | 1.74 | 1795.071
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0035-00 | 2025-12-31 | Mechanical FIR for Installation of GRP Storm Pipe from MH-20-3 TO MH-20-2 @ ZONE-01 | 1031.65 | 22.67 | 23387.5055
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0041-00 | 2026-01-03 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-20-2 TO MH-20-1@ ZONE-01 | 1031.65 | 10.34 | 10667.261
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0052-00 | 2026-01-08 | Survey FIR for Geotextile and Gravel Bedding of Storm Pipe from MH-20-2 TO MH-20-1 @ ZONE-01, Pipe DIA 800mm | 1031.65 | 3.45 | 3559.1925
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0055-00 | 2026-01-08 | Mechanical Installation and Laying of GRP Storm Pipeline from MH-20-2 TO MH-20-1 @ ZONE-01, Pipe DIA 800mm | 1031.65 | 41.34 | 42648.411
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0059-00 | 2026-01-11 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-20-1 TO MH-20-0 @ ZONE-01, Pipe DIA 800mm | 1031.65 | 7.41 | 7644.5265
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0070-00 | 2026-01-17 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipeline from MH-20-1 TO MH-20-0 @ ZONE-01, Pipe DIA 800mm | 1031.65 | 2.47 | 2548.1755
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0081-00 | 2026-01-19 | Mechanical FIR for Installation and Laying of Storm Pipeline form MH-20-1 TO MH-20-0, @ ZONE-01 Pipe DIA 500MM | 1031.65 | 29.65 | 30588.4225
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0083-00 | 2026-01-22 | Mechanical FIR Initial Air Test of Storm Pipeline form MH-20-3 TO MH-20-2, @ ZONE-01 Pipe DIA 800MM | 1031.65 | 1.77 | 1826.0205
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0086-00 | 2026-01-24 | Mechanical FIR Initial Air Test of Storm Pipeline form MH-20-2 TO MH-20-1, @ ZONE-01 Pipe DIA 800MM | 1031.65 | 3.48 | 3590.142
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0089-00 | 2026-01-25 | Mechanical FIR Initial Air Test of Storm Pipeline form MH-20-1 TO MH-20-0, @ ZONE-01 Pipe DIA 800MM | 1031.65 | 2.47 | 2548.1755
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0091-00 | 2026-01-27 | Survey FIR for Backfill and Compaction Testing 3rd Layer above the Storm Pipeline from MH-20-1 TO MH-20-0, LINE B @ ZONE-01 | 1031.65 | 2.47 | 2548.1755
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0092-00 | 2026-01-29 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-23 TO MH-6-22 (STATION FROM 1+300.7 to 1+351.7) @ ZONE-04, Pipe DIA 800mm | 1031.65 | 7.54 | 7778.641
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0093-00 | 2026-01-29 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-6-23 TO MH-6-22 (STATION FROM 1+300.7 to 1+351.7) @ ZONE-04, Pipe DIA 800mm | 1031.65 | 2.51 | 2589.4415
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0102-00 | 2026-02-01 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-23 (1+254.2 1+300.7) TO MH-6-22 @ ZONE-04, Pipe DIA 800mm | 1031.65 | 6.87 | 7087.4355
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0103-00 | 2026-02-01 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipeline from MH-6-23 (1+254.2 1+300.7) TO MH-6-22 @ ZONE-04 | 1031.65 | 2.29 | 2362.4785
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0108-00 | 2026-02-02 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-23 TO MH-6-22 (STATION FROM 1+300.7 to 1+351.7) @ ZONE-04, Pipe DIA 800mm | 1031.65 | 30.15 | 31104.2475
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0109-00 | 2026-02-02 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-23(1+254.2 1+300.7) TO MH-6-22 @ ZONE-04, Pipe DIA 800mm | 1031.65 | 27.49 | 28360.0585
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0118-00 | 2026-02-07 | Mechanical FIR Initial Air Test of Storm Pipeline form MH-6-23 TO MH-6-22, @ ZONE-04 Pipe DIA 800MM | 1031.65 | 4.8 | 4951.92
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0705-00 | 2026-06-24 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes MH-3-18 TO MH-3-17/0, @ ZONE-04 | 1031.65 | 13.14 | 13555.881
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0707-00 | 2026-06-24 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipeline Manholes MH-3-18 TO MH-3-17/0, @ ZONE-04 | 1031.65 | 4.38 | 4518.627
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0723-01 | 2026-07-02 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-3-18 TO MH-3-17, @ ZONE-04 | 1031.65 | 52.55 | 54213.2075
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0848 | 2026-08-11 | Survey FIR for Gravel Covering with Geotextile above the Storm Pipe Line from MH-3-18 TO MH-3-17, @ ZONE-04 | 1031.65 | 4.38 | 4518.627
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0943 | 2026-08-20 | Survey FIR for Backfill and Compaction Testing of the Final Backfill Layer above the Storm Pipe Line from MH-3-18 TO MH-3-17, @ ZONE-04. | 1031.65 | 4.38 | 4518.627
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0949 | 2026-08-20 | Survey FIR for Backfill and Compaction Testing 3rd Layer above the Storm Pipeline from MH-6-23 TO MH-6-22, @ ZONE-04 | 1031.65 | 4.8 | 4951.92
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0956 | 2026-08-22 | Survey FIR for Backfill and Compaction Testing 3rd Layer above the Storm Pipeline from MH-20-3 TO MH-20-2, LINE B @ ZONE-01 | 1031.65 | 1.78 | 1836.337
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0957 | 2026-08-22 | Survey FIR for Backfill and Compaction Testing 4th Layer above the Storm Pipeline from MH-20-3 TO MH-20-2, LINE B @ ZONE-01 | 1031.65 | 1.78 | 1836.337
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0958 | 2026-08-22 | Survey FIR for Backfill and Compaction Testing 3rd Layer above the Storm Pipeline from MH-20-2 TO MH-20-1, LINE B @ ZONE-01 | 1031.65 | 3.48 | 3590.142
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0959 | 2026-08-22 | Survey FIR for Backfill and Compaction Testing 4TH Layer above the Storm Pipeline from MH-20-2 TO MH-20-1, LINE B @ ZONE-01 | 1031.65 | 3.48 | 3590.142
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0961 | 2026-08-22 | Survey FIR for Backfill and Compaction Testing last Layer above the Storm Pipeline from MH-20-1 TO MH-20-0, LINE B @ ZONE-01 | 1031.65 | 2.49 | 2568.8085
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1018 | 2026-09-03 | Survey FIR for Backfill and Compaction Testing 4TH Layer above the Storm Pipeline from MH-6-23 TO MH-6-22, @ ZONE-04 | 1031.65 | 4.8 | 4951.92
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1257 | 2026-10-14 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from MH-3-17 to MH-3-18 Road-2 , ZONE- 04 | 1031.65 | 8.76 | 9037.254
B6.33 42 11.13 | 800mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1285 | 2026-10-14 | Mechanical FIR for Final Air testing of GRP Strom Drainage PIPE from 1. MH-20-2 to MH-20-3 Road-1 , ZONE- 01 | 1031.65 | 1.78 | 1836.337
B6.33 42 11.15 | 900mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0113-00 | 2026-02-02 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-22 (1+222.2 to 1+254.2) TO MH-6-21/0 @ ZONE-04, Pipe DIA 900mm | 1165.984 | 4.69 | 5468.465
B6.33 42 11.15 | 900mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0114-00 | 2026-02-04 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipeline from MH-6-22 (1+222.2 to 1+254.2) TO MH-6-21/0 @ ZONE-04, Pipe DIA 900mm | 1165.984 | 1.56 | 1818.935
B6.33 42 11.15 | 900mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0121-00 | 2026-02-09 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-22 (1+156.4 to 1+222.2 ) TO MH-6-21/0 @ ZONE-04, Pipe DIA 900mm | 1165.984 | 9.71 | 11321.7046
B6.33 42 11.15 | 900mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0127-00 | 2026-02-10 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipeline from MH-6-22 (1+156.4 To 1+222.2) TO MH-6-21/0 @ ZONE-04, Pipe DIA 900mm | 1165.984 | 3.24 | 3777.7882
B6.33 42 11.15 | 900mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0149-00 | 2026-02-14 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-22 TO MH-6-21/0 @ ZONE-04, Pipe DIA 900mm | 1165.984 | 57.59 | 67149.0186
B6.33 42 11.15 | 900mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0150-00 | 2026-02-14 | Mechanical FIR Initial Air Test of Storm Pipeline form MH-6-22 TO MH-6-21/0, @ ZONE-04 Pipe DIA 900MM | 1165.984 | 4.8 | 5596.7232
B6.33 42 11.15 | 900mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0221-00 | 2026-02-21 | Survey FIR for Backfill and Compaction Testing 2nd Layer above the Storm Pipeline from MH-6-22 TO MH-6-21/0, @ ZONE-04 Pipe DIA 900MM | 1165.984 | 4.8 | 5596.7232
B6.33 42 11.17 | 1000mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0124-00 | 2026-02-09 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-21/0 TO MH-6-20, @ ZONE-04 | 1181.788 | 8.91 | 10529.7311
B6.33 42 11.17 | 1000mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0129-00 | 2026-02-10 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipeline from MH-6-21/0 TO MH-6-20 @ ZONE-04, Pipe DIA 1000mm | 1181.788 | 2.97 | 3509.9104
B6.33 42 11.17 | 1000mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0135-00 | 2026-02-12 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-21/0 TO MH-6-20 @ ZONE-04, Pipe DIA 1000mm | 1181.788 | 35.63 | 42107.1064
B6.33 42 11.17 | 1000mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0147-00 | 2026-02-12 | Mechanical FIR Initial Air Test of Storm Pipeline form MH-6-21/0 TO MH-6-20, @ ZONE-04 Pipe DIA 1000MM | 1181.788 | 2.97 | 3509.9104
B6.33 42 11.17 | 1000mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0222-00 | 2026-02-21 | Survey FIR for Backfill and Compaction Testing 2nd Layer above the Storm Pipeline from MH-6-21/0 TO MH-6-20, @ ZONE-04 Pipe DIA 1000MM | 1181.788 | 2.97 | 3509.9104
B6.33 42 11.17 | 1000mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0939-00 | 2026-08-18 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline from MH-8-1 TO MH-8-2 & MH-8-2 TO MH-8-3 & MH-8-3 TO MH-8-4 | 1181.788 | 20.25 | 23931.207
B6.33 42 11.17 | 1000mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0940-00 | 2026-08-18 | Survey FIR for Sand Bedding and Compaction testing of Storm Pipeline from MH-8-1 TO MH-8-2 & MH-8-2 TO MH-8-3 & MH-8-3 TO MH-8-4 | 1181.788 | 6.75 | 7977.069
B6.33 42 11.17 | 1000mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0942-00 | 2026-08-19 | Survey and Mechanical FIR for installation and laying of Storm Pipeline from MH-8-1 TO MH-8-2 & MH-8-2 TO MH-8-3 & MH-8-3 TO MH-8-4 | 1181.788 | 81 | 95724.828
B6.33 42 11.19 | 1100mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0133-00 | 2026-02-11 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-20 TO MH-6-19, @ ZONE-04 | 1370.558 | 13.57 | 18598.4721
B6.33 42 11.19 | 1100mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0146-00 | 2026-02-12 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipeline from MH-6-20 TO MH-6-19, @ ZONE-04 | 1370.558 | 4.52 | 6194.9222
B6.33 42 11.19 | 1100mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0159-00 | 2026-02-14 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-20 TO MH-6-19, @ ZONE-04, Pipe DIA 1100mm | 1370.558 | 54.29 | 74407.5938
B6.33 42 11.19 | 1100mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0205-00 | 2026-02-19 | Mechanical FIR Initial Air Test of Storm Pipeline form MH-6-20 TO MH-6-19, @ ZONE-04 Pipe DIA 1100MM | 1370.558 | 4.52 | 6194.9222
B6.33 42 11.19 | 1100mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0363-00 | 2026-03-26 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-14 TO MH-3-13/0, @ ZONE-04 | 1370.558 | 3.7 | 5071.0646
B6.33 42 11.19 | 1100mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0364-00 | 2026-03-26 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-3-14 TO MH-3-13/0, @ ZONE-04 | 1370.558 | 1.23 | 1685.7863
B6.33 42 11.19 | 1100mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0384-00 | 2026-03-28 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-3-14 TO MH-3-13/0 @ ZONE-04, Pipe DIA 1100mm | 1370.558 | 14.81 | 20297.964
B6.33 42 11.19 | 1100mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0439-00 | 2026-03-31 | Survey FIR for Backfill and Compaction Testing 2nd Layer above the Storm Pipeline from MH-3-14 TO MH-3-13/0 @ ZONE-04, Pipe DIA 1100mm | 1370.558 | 1.23 | 1685.7863
B6.33 42 11.19 | 1100mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0339-00 | 2026-03-25 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-16 TO MH-3-15, @ ZONE-04 | 1370.558 | 10.66 | 14610.1483
B6.33 42 11.19 | 1100mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0361-00 | 2026-03-26 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-3-16 TO MH-3-15, @ ZONE-04 | 1370.558 | 3.55 | 4865.4809
B6.33 42 11.19 | 1100mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0386-00 | 2026-03-28 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-3-16 To MH-3-15 (Station 0+957.60 TO 0+905.60), @ ZONE-04, Pipe DIA 1100mm | 1370.558 | 30.6 | 41939.0748
B6.33 42 11.19 | 1100mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0706-00 | 2026-06-24 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes MH-3-17/0 TO MH-3-16, @ ZONE-04 | 1370.558 | 13.07 | 17913.1931
B6.33 42 11.19 | 1100mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0708-00 | 2026-06-24 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipeline Manholes MH-3-17/0 TO MH-3-16, @ ZONE-04 | 1370.558 | 4.36 | 5975.6329
B6.33 42 11.19 | 1100mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0720-00 | 2026-06-28 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes MH-3-15 TO MH-3-14, @ ZONE-04 | 1370.558 | 5.82 | 7976.6476
B6.33 42 11.19 | 1100mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0721-00 | 2026-06-28 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipeline Manholes MH-3-15 TO MH-3-14, @ ZONE-04 | 1370.558 | 1.94 | 2658.8825
B6.33 42 11.19 | 1100mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0752-00 | 2026-07-01 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-3-17/0 TO MH-3-16, @ ZONE-04 | 1370.558 | 52.28 | 71652.7722
B6.33 42 11.19 | 1100mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0832-00 | 2026-08-02 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-3-15 TO MH-3-14, @ ZONE-04 | 1370.558 | 23.26 | 31879.1791
B6.33 42 11.19 | 1100mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0834-01 | 2026-10-03 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-3-16 TO MH-3-15 with short pieces @ ZONE-04 | 1370.558 | 12.02 | 16474.1072
B6.33 42 11.19 | 1100mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0887 | 2026-08-12 | Survey FIR for Backfill and Compaction Testing 2nd Layer above the Storm Pipe Line from MH-6-20 TO MH-6-19, @ ZONE-04 | 1370.558 | 4.52 | 6194.9222
B6.33 42 11.19 | 1100mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0977 | 2026-08-25 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline from MH-8-1 TO MH-8-0 | 1370.558 | 10.22 | 14007.1028
B6.33 42 11.19 | 1100mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0978 | 2026-08-25 | Survey FIR for Sand Bedding and Compaction testing of Storm Pipeline from MH-8-1 TO MH-8-0 | 1370.558 | 3.41 | 4673.6028
B6.33 42 11.19 | 1100mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0985 | 2026-08-26 | Survey and Mechanical FIR for the Installation laying of Storm Pipe Line from MH-8-1 TO MH-8-0 | 1370.558 | 40.89 | 56042.1166
B6.33 42 11.19 | 1100mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1076 | 2026-09-15 | Survey and Backfill Compaction Test FIR for the 2nd Layer above the Pipeline of the Storm Network from MH-3-14 TO MH-3-15 & MH-3-15 TO MH-3-16 @ Zone-04. | 1370.558 | 5.49 | 7524.3634
B6.33 42 11.22 | 1200mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0234-00 | 2026-02-25 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-19 TO MH-6-18/0 @ ZONE-04 | 1440.798 | 11.05 | 15920.8179
B6.33 42 11.22 | 1200mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0237-00 | 2026-02-28 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-6-19 TO MH-6-18/0, @ ZONE-04 | 1440.798 | 3.68 | 5302.1366
B6.33 42 11.22 | 1200mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0246-00 | 2026-03-02 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-19 TO MH-6-18/0, @ ZONE-04, Pipe DIA 1200 | 1440.798 | 44.21 | 63697.6796
B6.33 42 11.22 | 1200mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0275-00 | 2026-03-08 | Survey FIR for Backfill and Compaction Testing 2nd Layer above the Storm Pipeline from MH-6-19 TO MH-6-18/0, @ ZONE-04 | 1440.798 | 3.68 | 5302.1366
B6.33 42 11.22 | 1200mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0236-00 | 2026-02-28 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-18/0 TO MH-6-17 @ ZONE-04 | 1440.798 | 5.39 | 7765.9012
B6.33 42 11.22 | 1200mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0242-00 | 2026-03-02 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-6-18/0 TO MH-6-17, @ ZONE-04 | 1440.798 | 1.8 | 2593.4364
B6.33 42 11.22 | 1200mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0247-00 | 2026-03-02 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-18/0 TO MH-6-17/0, @ ZONE-04, Pipe DIA 1200mm | 1440.798 | 21.56 | 31063.6049
B6.33 42 11.22 | 1200mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0951-00 | 2026-08-20 | Survey FIR for Backfill and Compaction Testing 3rd Layer above the Storm Pipeline from MH-6-18/0 TO MH-6-17, @ ZONE-04 | 1440.798 | 3.59 | 5172.4648
B6.33 42 11.22 | 1200mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0101 | 2026-09-17 | Survey and Backfill Compaction Test FIR for the 3rd Layer above the Pipeline of the Storm Network from: MH-6-18 TOMH-6-19 DIA 1200 mm @ Zone-04 | 1440.798 | 3.69 | 5316.5446
B6.33 42 11.24 | 1300mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0886 | 2026-08-12 | Survey FIR for Backfill and Compaction Testing 2nd Layer above the Storm Pipe Line from MH-3-11 TO MH-3-12, @ ZONE-04 | 1683.126 | 5.15 | 8668.0989
B6.33 42 11.24 | 1300mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0945 | 2026-08-20 | Survey FIR for Backfill and Compaction Testing 3rd Layer above the Storm Pipeline from MH-3-10/0 TO MH-3-11 @ ZONE-04, Pipe DIA 1300mm | 1683.126 | 2.96 | 4982.053
B6.33 42 11.24 | 1300mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0952 | 2026-08-20 | Survey FIR for Backfill and Compaction Testing 3rd Layer above the Storm Pipeline from MH-6-17 TO MH-6-16 @ ZONE-04, Pipe DIA 1300mm | 1683.126 | 4.12 | 6934.4791
B6.33 42 11.24 | 1300mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1017 | 2026-09-03 | Survey FIR for Backfill and Compaction Testing 4TH Layer above the Storm Pipeline from MH-6-17 TO MH-6-16 @ ZONE-04, Pipe DIA 1300mm | 1683.126 | 4.12 | 6934.4791
B6.33 42 11.25 | 1300mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0253-00 | 2026-03-03 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-10/0 TO MH-3-11, @ ZONE-04 | 1786.73 | 4.43 | 7915.2139
B6.33 42 11.25 | 1300mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0254-00 | 2026-03-03 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-11 TO MH-3-12, @ ZONE-04 | 1786.73 | 15.44 | 27587.1112
B6.33 42 11.25 | 1300mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0257-00 | 2026-03-05 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-17 TO MH-6-16, @ ZONE-04 | 1786.73 | 12.35 | 22066.1155
B6.33 42 11.25 | 1300mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0260-00 | 2026-03-07 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-6-17 TO MH-6-16, @ ZONE-04 | 1786.73 | 4.12 | 7361.3276
B6.33 42 11.25 | 1300mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0262-00 | 2026-03-07 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-3-10/0 TO MH-3-11, @ ZONE-04 | 1786.73 | 1.48 | 2644.3604
B6.33 42 11.25 | 1300mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0267-00 | 2026-03-08 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-3-11 TO MH-3-12, @ ZONE-04 | 1786.73 | 5.15 | 9201.6595
B6.33 42 11.25 | 1300mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0269-00 | 2026-03-08 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-17 TO MH-6-16, @ ZONE-03, Pipe DIA 1300mm | 1786.73 | 49.42 | 88300.1966
B6.33 42 11.25 | 1300mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0271-00 | 2026-03-08 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-3-11 TO MH-3-12, @ ZONE-03, Pipe DIA 1300mm | 1786.73 | 61.74 | 110312.7102
B6.33 42 11.25 | 1300mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0281-00 | 2026-03-09 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-3-10/0 TO MH-3-11, @ ZONE-04, Pipe DIA 1300mm | 1786.73 | 17.73 | 31678.7229
B6.33 42 11.25 | 1300mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0341-00 | 2026-03-25 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-13/0 TO MH-3-12, @ ZONE-04 | 1786.73 | 5.18 | 9255.2614
B6.33 42 11.25 | 1300mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0365-00 | 2026-03-26 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-3-13/0 TO MH-3-12, @ ZONE-04 | 1786.73 | 1.73 | 3091.0429
B6.33 42 11.25 | 1300mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0367-00 | 2026-03-26 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-3-13/0 TO MH-3-12, @ ZONE-04, Pipe DIA 1300mm | 1786.73 | 20.72 | 37021.0456
B6.33 42 11.25 | 1300mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0437-00 | 2026-03-31 | Survey FIR for Backfill and Compaction Testing 2nd Layer above the Storm Pipeline from MH-3-13/0 TO MH-3-12 @ ZONE-04, Pipe DIA 1300mm | 1786.73 | 1.73 | 3091.0429
B6.33 42 11.28 | 1400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0206-00 | 2026-02-19 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-10/0 TO MH-3-9, @ ZONE-03 | 1640.104 | 9.96 | 16335.4358
B6.33 42 11.28 | 1400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0225-00 | 2026-02-21 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-3-10/0 TO MH-3-9, @ ZONE-03 | 1640.104 | 3.32 | 5445.1453
B6.33 42 11.28 | 1400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0231-00 | 2026-02-21 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-3-10/0 TO MH-3-9, @ ZONE-03, Pipe DIA 1400mm | 1640.104 | 39.85 | 65358.1444
B6.33 42 11.28 | 1400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0304-00 | 2026-03-16 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-9/0 TO MH-6-10, @ ZONE-03 | 1640.104 | 4.3 | 7052.4472
B6.33 42 11.28 | 1400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0305-00 | 2026-03-16 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-10 TO MH-6-11/0, @ ZONE-03 | 1640.104 | 13.42 | 22010.1957
B6.33 42 11.28 | 1400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0317-00 | 2026-03-17 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-6-10 TO MH-6-9/0 @ ZONE-03 | 1640.104 | 1.43 | 2345.3487
B6.33 42 11.28 | 1400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0318-00 | 2026-03-17 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-6-10 TO MH-6-11/0, @ ZONE-03 | 1640.104 | 4.47 | 7331.2649
B6.33 42 11.28 | 1400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0355-00 | 2026-03-26 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-10 TO MH-6-9/0, @ ZONE-03, Pipe DIA 1400mm | 1640.104 | 17.21 | 28226.1898
B6.33 42 11.28 | 1400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0377-00 | 2026-03-26 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-11/0 TO MH-6-10, @ ZONE-03, Pipe DIA 1400mm | 1640.104 | 53.68 | 88040.7827
B6.33 42 11.28 | 1400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0241-00 | 2026-03-02 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-14 TO MH-6-13 @ ZONE-04 | 1744.586 | 10.28 | 17934.3441
B6.33 42 11.28 | 1400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0243-00 | 2026-03-02 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-6-14 TO MH-6-13, @ ZONE-04 | 1744.586 | 3.43 | 5983.93
B6.33 42 11.28 | 1400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0250-00 | 2026-03-03 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-14 TO MH-6-13, @ ZONE-04, Pipe DIA 1400mm | 1744.586 | 41.12 | 71737.3763
B6.33 42 11.28 | 1400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0134-00 | 2026-02-11 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-9 TO MH-3-8/0, @ ZONE-03 | 1640.104 | 12.47 | 20452.0969
B6.33 42 11.28 | 1400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0140-00 | 2026-02-12 | Survey FIR for Sand Bedding of Storm Pipeline from MH-3-9 TO MH-3-8/0, @ ZONE-03 | 1640.104 | 4.16 | 6822.8326
B6.33 42 11.28 | 1400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0200-00 | 2026-02-18 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-3-9 TO MH-3-8, @ ZONE-03, Pipe DIA 1400mm | 1640.104 | 49.88 | 81808.3875
B6.33 42 11.28 | 1400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0228-00 | 2026-02-23 | Mechanical FIR Initial Air Test of Storm Pipeline form MH-3-9 TO MH-3-8/0, @ ZONE-03 Pipe DIA 1400MM | 1640.104 | 4.16 | 6822.8326
B6.33 42 11.28 | 1400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0264-00 | 2026-03-07 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-16 TO MH-6-15, @ ZONE-04 | 1640.104 | 10.42 | 17089.8837
B6.33 42 11.28 | 1400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0266-00 | 2026-03-07 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-15 TO MH-6-14, @ ZONE-04 | 1640.104 | 2.68 | 4395.4787
B6.33 42 11.28 | 1400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0279-00 | 2026-03-09 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-6-16 TO MH-6-15, @ ZONE-04 | 1640.104 | 3.47 | 5691.1609
B6.33 42 11.28 | 1400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0280-00 | 2026-03-09 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-6-15 TO MH-6-14, @ ZONE-04 | 1640.104 | 0.89 | 1459.6926
B6.33 42 11.28 | 1400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0283-00 | 2026-03-09 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-16 TO MH-6-15, @ ZONE-04, Pipe DIA 1400mm | 1640.104 | 41.67 | 68343.1337
B6.33 42 11.28 | 1400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0292-00 | 2026-03-10 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-15 TO MH-6-14, @ ZONE-04, Pipe DIA 1400mm | 1640.104 | 10.73 | 17598.3159
B6.33 42 11.28 | 1400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0415-00 | 2026-03-29 | Survey FIR for Backfill and Compaction Testing 2nd Layer above the Storm Pipeline from MH-3-9 TO MH-3-8/0 @ ZONE-03, Pipe DIA 1400mm | 1640.104 | 4.16 | 6822.8326
B6.33 42 11.28 | 1400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0880 | 2026-08-12 | Survey FIR for Backfill and Compaction Testing 2nd Layer above the Storm Pipeline from MH-3-10/0 TO MH-3-9, @ ZONE-03, Pipe DIA 1400mm | 1640.104 | 3.32 | 5445.1453
B6.33 42 11.28 | 1400mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1101 | 2026-09-17 | Survey and Backfill Compaction Test FIR for the 3rd Layer above the Pipeline of the Storm Network from: MH-6-13 To MH-6-14 DIA 1400 mm MH-6-15 TO MH-6-16 DIA 1400 mm @ Zone-04 | 1640.104 | 13.8 | 22633.4352
B6.33 42 11.29 | 1400mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0306-00 | 2026-03-16 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-11/0 TO MH-6-12, @ ZONE-03 | 1744.586 | 10.95 | 19103.2167
B6.33 42 11.29 | 1400mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0307-00 | 2026-03-16 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-12 TO MH-6-13 (Station From 0+566.21 TO 0+624.74), @ ZONE-03 | 1744.586 | 8.63 | 15055.7772
B6.33 42 11.29 | 1400mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0319-00 | 2026-03-18 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-6-11/0 TO MH-6-12, @ ZONE-03 | 1744.586 | 3.65 | 6367.7389
B6.33 42 11.29 | 1400mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0320-00 | 2026-03-18 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-6-12 TO MH-6-13 (Station From 0+556.21 TO 0+624.74), @ ZONE-03 | 1744.586 | 2.88 | 5024.4077
B6.33 42 11.29 | 1400mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0323-00 | 2026-03-18 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-11/0 TO MH-6-12, @ ZONE-03, Pipe DIA 1400mm | 1744.586 | 43.81 | 76430.3127
B6.33 42 11.29 | 1400mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0324-00 | 2026-03-18 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-12 TO MH-6-13 (Station 0+566.21 TO 0+614.24) , @ ZONE-03, Pipe DIA 1400mm | 1744.586 | 34.52 | 60223.1087
B6.33 42 11.29 | 1400mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0946-00 | 2026-08-20 | Survey FIR for Backfill and Compaction Testing of the Final Backfill Layer above the Storm Pipeline from MH-6-12 TO MH-6-13 (Station 0+556.21 TO 0+614.24) @ ZONE-03, Pipe DIA 1400mm | 1744.586 | 5.75 | 10031.3695
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0311-00 | 2026-03-16 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-9/0 TO MH-6-8/0, @ ZONE-03 | 1831.508 | 9.74 | 17838.8879
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0313-00 | 2026-03-17 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-8/0 TO MH-6-7, @ ZONE-03 | 1831.508 | 1.06 | 1941.3985
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0314-00 | 2026-03-17 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-7 TO MH-6-6, @ ZONE-03 | 1831.508 | 2.43 | 4450.5644
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0315-00 | 2026-03-17 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-6 TO MH-6-5, @ ZONE-03 | 1831.508 | 1.14 | 2087.9191
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0316-00 | 2026-03-17 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-5 TO MH-6-4, @ ZONE-03 | 1831.508 | 14.6 | 26740.0168
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0325-00 | 2026-03-24 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-6-9/0 TO MH-6-8/0, @ ZONE-03 | 1831.508 | 3.25 | 5952.401
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0326-00 | 2026-03-24 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-6-8/0 TO MH-6-7, @ ZONE-03 | 1831.508 | 0.35 | 641.0278
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0327-00 | 2026-03-24 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-6-7 TO MH-6-6, @ ZONE-03 | 1831.508 | 0.81 | 1483.5215
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0328-00 | 2026-03-24 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-6-6 TO MH-6-5, @ ZONE-03 | 1831.508 | 0.38 | 695.973
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0379-00 | 2026-03-26 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-9/0 TO MH-6-8/0, @ ZONE-03, Pipe DIA 1500mm | 1831.508 | 38.96 | 71355.5517
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0380-00 | 2026-03-26 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-6-5 TO MH-6-4, @ ZONE-03 | 1831.508 | 4.87 | 8919.444
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0382-00 | 2026-03-26 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-5 TO MH-6-4, @ ZONE-03, Pipe DIA 1500mm | 1831.508 | 58.38 | 106923.437
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0390-00 | 2026-03-26 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-8/0 TO MH-6-7 @ZONE-03, Pipe DIA 1500mm | 1831.508 | 4.25 | 7783.909
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0391-00 | 2026-03-26 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-7 TO MH-6-6 @ZONE-03, Pipe DIA 1500mm | 1831.508 | 9.73 | 17820.5728
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0392-00 | 2026-03-26 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-6-6 TO MH-6-5 @ZONE-03, Pipe DIA 1500mm | 1831.508 | 4.57 | 8369.9916
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0470-00 | 2026-04-11 | Survey FIR for Gravel Covering with Geotextile above the Storm Pipe Line from MH-6-6 TO MH-6-5, @ ZONE-03 | 1831.508 | 0.38 | 695.973
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0471-00 | 2026-04-11 | Survey FIR for Backfill and Compaction Testing 2nd Layer above the Storm Pipeline from MH-6-5 TO MH-6-4 @ ZONE-03 | 1831.508 | 9.73 | 17820.5728
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0496-00 | 2026-05-03 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-4 TO MH-6-3, @ ZONE-03 | 1831.508 | 12.3 | 22527.5484
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0497-00 | 2026-05-03 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-6-4 TO MH-6-3, @ ZONE-03 | 1831.508 | 4.1 | 7509.1828
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0500-00 | 2026-05-06 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-6-4 TO MH-6-3, @ ZONE-03 | 1831.508 | 49.22 | 90146.8238
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0503-00 | 2026-05-12 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-4 TO MH-3-3, @ ZONE-03 | 1831.508 | 8.24 | 15091.6259
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0504-00 | 2026-05-12 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-3-4 TO MH-3-3, @ ZONE-03 | 1831.508 | 2.75 | 5036.647
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0505-00 | 2026-05-12 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-3 TO MH-3-2, @ ZONE-03 | 1831.508 | 1.42 | 2600.7414
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0506-00 | 2026-05-12 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-3-3 TO MH-3-2, @ ZONE-03 | 1831.508 | 0.47 | 860.8088
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0507-00 | 2026-05-13 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-2 TO MH-3-1, @ ZONE-03 | 1831.508 | 1.44 | 2637.3715
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0508-00 | 2026-05-13 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-3-2 TO MH-3-1, @ ZONE-03 | 1831.508 | 0.48 | 879.1238
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0509-00 | 2026-05-13 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-1 TO MH-3-0, @ ZONE-03 | 1831.508 | 5.57 | 10201.4996
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0510-00 | 2026-05-13 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-3-1 TO MH-3-0, @ ZONE-03 | 1831.508 | 1.86 | 3406.6049
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0152-00 | 2026-02-14 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-8/0 TO MH-3-7, @ ZONE-03 | 1831.508 | 14.69 | 26904.8525
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0155-00 | 2026-02-14 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipeline from MH-3-8 TO MH-3-7/0, @ ZONE-03 | 1831.508 | 4.9 | 8974.3892
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0227-00 | 2026-02-23 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-3-8/0 TO MH-3-7/0, @ ZONE-03, Pipe DIA 1500mm | 1831.508 | 58.78 | 107656.0402
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0248-00 | 2026-03-03 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-7/0 TO MH-3-6/0 @ ZONE-03 | 1831.508 | 11.84 | 21685.0547
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0255-00 | 2026-03-04 | Mechanical FIR Initial Air Test of Storm Pipeline form MH-3-8/0 TO MH-3-7/0, @ ZONE-04 Pipe DIA 1500MM | 1831.508 | 4.9 | 8974.3892
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0258-00 | 2026-03-07 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-3-7/0 TO MH-3-6/0, @ ZONE-03 | 1831.508 | 3.95 | 7234.4566
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0261-00 | 2026-03-07 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-3-7/0 TO MH-3-6/0, @ ZONE-03, Pipe DIA 1500mm | 1831.508 | 47.36 | 86740.2189
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0293-00 | 2026-03-10 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-6/0 TO MH-3-5/0, @ ZONE-03 | 1831.508 | 12.24 | 22417.6579
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0298-00 | 2026-03-12 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-3-6/0 TO MH-3-5/0, @ ZONE-03 | 1831.508 | 4.08 | 7472.5526
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0309-00 | 2026-03-16 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-3-6/0 TO MH-3-5/0, @ ZONE-03, Pipe DIA 1500mm | 1831.508 | 48.98 | 89707.2618
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0354-00 | 2026-03-25 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-3-5/0 TO MH-3-4, @ ZONE-03 | 1831.508 | 15.45 | 28296.7986
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0417-00 | 2026-03-29 | Survey FIR for Backfill and Compaction Testing 2nd Layer above the Storm Pipeline from MH-3-8/0 TO MH-3-7/0 @ ZONE-03, Pipe DIA 1500mm | 1831.508 | 4.9 | 8974.3892
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0420-00 | 2026-03-29 | Survey FIR for Backfill and Compaction Testing 2nd Layer above the Storm Pipeline from MH-3-6/0 TO MH-3-5/0 @ ZONE-03, Pipe DIA 1500mm | 1831.508 | 4.08 | 7472.5526
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0427-00 | 2026-03-30 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipe Line from MH-3-5/0 TO MH-3-4, @ ZONE-03 | 1831.508 | 5.15 | 9432.2662
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0429-00 | 2026-03-30 | Mechanical FIR for Installation and Laying of Storm Pipeline from MH-3-5/0 TO MH-3-4 @ZONE-03, Pipe DIA 1500mm | 1831.508 | 61.81 | 113205.5095
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0520 | 2026-05-14 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-3 TO MH-6-2/0, @ ZONE-03 | 1831.508 | 7.4 | 13553.1592
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0521 | 2026-05-14 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-2/0 TO MH-6-1/0, @ ZONE-03 | 1831.508 | 1.81 | 3315.0295
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0522-01 | 2026-09-08 | Survey Excavation and Compaction Test FIR for Storm Pipe Line from MH-6-1/0 TO MH-6/0, @ ZONE-03 | 1831.508 | 2.17 | 3974.3724
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0523 | 2026-05-14 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-6-3 TO MH-6-2/0, @ ZONE-03 | 1831.508 | 2.47 | 4523.8248
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0524 | 2026-05-14 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-6-2/0 TO MH-6-1/0, @ ZONE-03 | 1831.508 | 0.6 | 1098.9048
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0525 | 2026-05-14 | Survey FIR for Sand Bedding of Storm Pipe Line from MH-6-1/0 TO MH-6/0, @ ZONE-03 | 1831.508 | 0.72 | 1318.6858
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0529 | 2026-05-17 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-6-3 TO MH-6-2/0, @ ZONE-03 | 1831.508 | 29.59 | 54194.3217
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0539 | 2026-05-17 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-3-4 TO MH-3-3, @ ZONE-03 | 1831.508 | 32.95 | 60348.1886
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0559 | 2026-05-20 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-3-2 TO MH-3-1, @ ZONE-03 | 1831.508 | 5.74 | 10512.8559
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0561 | 2026-05-20 | Mechanical FIR for Installation and Laying of Storm Pipe Line from MH-3-1 TO MH-3-0 from Station (0+004.8 TO 0+039.5), @ ZONE-03 | 1831.508 | 20.82 | 38131.9966
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0854 | 2026-08-11 | Survey FIR for Sand Covering and Compaction Testing above the Storm Pipe Line from MH-6-4 TO MH-6-3, @ ZONE-03 | 1831.508 | 4.1 | 7509.1828
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0855 | 2026-08-11 | Survey FIR for Sand Covering and Compaction Testing above the Storm Pipe Line from MH-6-3 TO MH-6-2/0, @ ZONE-03 | 1831.508 | 2.47 | 4523.8248
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0883 | 2026-08-12 | Survey FIR for Backfill and Compaction Testing last Layer above the Storm Pipe Line from MH-6-4 TO MH-6-3, @ ZONE-03 | 1831.508 | 4.1 | 7509.1828
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0884 | 2026-08-12 | Survey FIR for Backfill and Compaction Testing last Layer above the Storm Pipe Line from MH-6-3 TO MH-6-2/0, @ ZONE-03 | 1831.508 | 2.47 | 4523.8248
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0947 | 2026-08-20 | Survey FIR for Backfill and Compaction Testing of the Final Backfill Layer above the Storm Pipeline from MH-6-9/0 TO MH-6-8/0, @ ZONE-03, Pipe DIA 1500mm | 1831.508 | 6.49 | 11886.4869
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1171 | 2026-09-30 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline From MH-16 TO MH-15 | 1831.508 | 13.53 | 24780.3032
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1172 | 2026-09-30 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipeline From MH-16 TO MH-15 | 1831.508 | 4.51 | 8260.1011
B6.33 42 11.32 | 1500mm Diameter Depth: 1.51m - 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1184 | 2026-10-01 | Survey and Mechanical FIR for installation and laying of Storm Pipeline From MH-16 TO MH-15 | 1831.508 | 54.14 | 99157.8431
B6.33 42 11.33 | 1500mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1188 | 2026-10-01 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline From MH-14 TO MH-13 | 1935.112 | 13.35 | 25833.7452
B6.33 42 11.33 | 1500mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1189 | 2026-10-01 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipeline From MH-14 TO MH-13 | 1935.112 | 4.45 | 8611.2484
B6.33 42 11.33 | 1500mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1193 | 2026-10-03 | Survey and Mechanical FIR for installation and laying of Storm Pipeline From MH-14 TO MH-13 | 1935.112 | 53.42 | 103373.683
B6.33 42 11.33 | 1500mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1232 | 2026-10-10 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline From MH-17 TO MH-16 | 1935.112 | 14.79 | 28620.3065
B6.33 42 11.33 | 1500mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1233 | 2026-10-10 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipeline From MH-17 TO MH-16 | 1935.112 | 4.93 | 9540.1022
B6.33 42 11.33 | 1500mm Diameter Depth: 2.51m - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1237 | 2026-10-11 | Survey and Mechanical FIR for installation and laying of Storm Pipeline From MH-17 TO MH-16 | 1935.112 | 59.14 | 114442.5237
B6.33 42 11.34 | 1500mm Diameter Depth: 3.51m - 4.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1262 | 2026-10-17 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline From MH-19 TO MH-18 | 2045.74 | 11.23 | 22973.6602
B6.33 42 11.34 | 1500mm Diameter Depth: 3.51m - 4.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1263 | 2026-10-17 | Survey FIR for Gravel Bedding with Geotextile of Storm Pipeline From MH-19 TO MH-18 | 2045.74 | 3.74 | 7651.0676
B6.33 42 11.34 | 1500mm Diameter Depth: 3.51m - 4.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1279 | 2026-10-18 | Survey And Mechanical FIR for Installation and laying of Storm Pipeline From MH-19 TO MH-18 | 2045.74 | 44.9 | 91853.726
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0287-01 | 2026-06-10 | Survey Excavation and Compaction Test FIR for UPVC Pipe Line for Catch Basin of Storm Network from CB-276 TO MH-3-8-1 and CB-303 TO MH-3-8-1, @ ZONE-03 | 601.43 | 2.78 | 1671.9754
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0288-01 | 2026-06-10 | Survey Excavation and Compaction Test FIR for UPVC Pipe Line for Catch Basin of Storm Network from CB-281 TO CB-314 and CB-314 TO MH-3-7-1, @ ZONE-03 | 601.43 | 5.18 | 3115.4074
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0289-01 | 2026-06-10 | Survey Excavation and Compaction Test FIR for UPVC Pipe Line for Catch Basin of Storm Network from CB-175 TO CB-329, CB-329 TO MH-3-6-2 and CB-339 TO MH-3-6-2, @ ZONE-03 | 601.43 | 9.45 | 5683.5135
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0290-01 | 2026-06-10 | Survey Excavation and Compaction Test FIR for UPVC Pipe Line for Catch Basin of Storm Network from CB-268 TO CB-331 and CB-331 TO MH-3-5-1, @ ZONE-03 | 601.43 | 6.71 | 4035.5953
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0294-01 | 2026-06-10 | Survey FIR of Sand Bedding for UPVC Pipe Line for Catch Basin of Storm Network from CB-276 TO MH-3-8-1 and CB-303 TO MH-3-8-1, @ ZONE-03 | 601.43 | 1.39 | 835.9877
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0295-01 | 2026-06-10 | Survey FIR of Sand Bedding for UPVC Pipe Line for Catch Basin of Storm Network from CB-281 TO CB-314 and CB-314 TO MH-3-7-1, @ ZONE-03 | 601.43 | 2.59 | 1557.7037
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0296-01 | 2026-06-10 | Survey FIR of Sand Bedding for UPVC Pipe Line for Catch Basin of Storm Network from CB-175 TO CB-329, CB-329 TO MH-3-6-2 and CB-339 TO MH-3-6-2, @ ZONE-03 | 601.43 | 4.72 | 2838.7496
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0297-01 | 2026-06-10 | Survey FIR of Sand Bedding for UPVC Pipe Line for Catch Basin of Storm Network from CB-268 TO CB-331 and CB-331 TO MH-3-5-1, @ ZONE-03 | 601.43 | 3.35 | 2014.7905
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0466-00 | 2026-09-13 | Survey Excavation and Compaction Test FIR for UPVC Pipe Line for Group of Catch Basins Network of Storm Network Connecting to Manholes (RD-01), @ ZONE-01 1- MH-28-0 (CB-9 TO MH-28-0) 2- MH-28-1 (CB-14 TO CB-14(4) and CB-14(4) TO MH-28-1) 3- MH-28-2 (CB-16 TO MH-28-2) 4- MH-28-3 (CB-24 TO CB-28, CB-28 TO MH-28-3 & CB-28 TO CB-34) 5- MH-28-4 (CB-43 TO MH-28-4) 6- MH-20-6 (CB-67 TO CB-81(1) ) 7- MH-20-5 (CB-75 TO CB-62, CB-62 TO CB-58 and CB-58 TO MH-20-5) 8- MH-20-4 (CB-71 TO CB-83) 9- MH-20-3 (CB-70 TO CB-52 and CB-52 TO MH-20-3) 10- MH-20-2 (CB-59 TO MH-20-2) 11- MH-20-1 (CB-82 TO CB-93, CB-93 TO CB-102) | 601.43 | 39.1 | 23515.913
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0467-00 | 2026-04-11 | Survey FIR for Sand Bedding of UPVC Pipe Line for Group of Catch Basins Network of Storm Network Connecting to Manholes (RD-01), @ ZONE-01 1- MH-28-0 (CB-9 TO MH-28-0) 2- MH-28-1 (CB-14 TO CB-14(4) and CB-14(4) TO MH-28-1) 3- MH-28-2 (CB-16 TO MH-28-2) 4- MH-28-3 (CB-24 TO CB-28, CB-28 TO MH-28-3 & CB-28 TO CB-34) 5- MH-28-4 (CB-43 TO MH-28-4) 6- MH-20-6 (CB-67 TO CB-81(1) 7- MH-20-5 (CB-75 TO CB-62, CB-62 TO CB-58 and CB-58 TO MH-20-5) 8- MH-20-4 (CB-71 TO CB-83) 9- MH-20-3 (CB-70 TO CB-52 and CB-52 TO MH-20-3) 10- MH-20-2 (CB-59 TO MH-20-2) 11- MH-20-1 (CB-82 TO CB-93, CB-93 TO CB-102) | 601.43 | 19.55 | 11757.9565
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0476-00 | 2026-04-14 | Mechanical FIR for Installation and Laying off UPVC Pipe Line for Group of Catch Basins Network of Storm Network Connecting to Manholes (RD-01), @ ZONE-01 1- MH-28-0 (CB-9 TO MH-28-0) 2- MH-28-1 (CB-14 TO CB-14(4) and CB-14(4) TO MH-28-1) 3- MH-28-2 (CB-16 TO MH-28-2) 4- MH-28-3 (CB-24 TO CB-28, CB-28 TO MH-28-3 & CB-28 TO CB-34) 5- MH-28-4 (CB-43 TO MH-28-4) 6- MH-20-6 (CB-67 TO CB-81(1) 7- MH-20-5 (CB-75 TO CB-62, CB-62 TO CB-58 and CB-58 TO MH-20-5) 8- MH-20-4 (CB-71 TO CB-83) 9- MH-20-3 (CB-70 TO CB-52 and CB-52 TO MH-20-3) 10- MH-20-2 (CB-59 TO MH-20-2) 11- MH-20-1 (CB-82 TO CB-93, CB-93 TO CB-102) | 601.43 | 254.12 | 152835.3916
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0593-01 | 2026-06-10 | Survey Excavation and Compaction Test FIR for UPVC Pipe Line for Catch Basin of Storm Network from CB-115 TO CB-171 and CB-171 TO MH-6-12 CB-186 TO CB-201 and CB-201 TO MH-6-11/0 CB-185 TO CB-184 and CB-184 TO MH-6-11/0 @ ZONE-03 | 601.43 | 11.89 | 7151.0027
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0594 | 2026-06-10 | Survey Sand Bedding and Compaction Test FIR for UPVC Pipe Line for Catch Basin of Storm Network from CB-115 TO CB-171 and CB-171 TO MH-6-12 CB-186 TO CB-201 and CB-201 TO MH-6-11/0 CB-185 TO CB-184 and CB-184 TO MH-6-11/0 @ ZONE-03 | 601.43 | 5.94 | 3572.4942
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0598 | 2026-06-02 | Mechanical FIR for Installation and Laying of UPVC Pipe Line for Catch Basin of Storm Network @ ZONE-03 CB-115 TO CB-171 and CB-171 TO MH-6-12 CB-186 TO CB-201 and CB-201 TO MH-6-11/0 CB-185 TO CB-184 and CB-184 TO MH-6-11/0 | 601.43 | 77.26 | 46466.4818
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0599-01 | 2026-06-10 | Survey Excavation and Compaction Test FIR for UPVC Pipe Line for Catch Basin of Storm Network @ ZONE-03 1- CB-199 TO CB-220 and CB-220 TO MH-4-4 | 601.43 | 7.05 | 4240.0815
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0600-01 | 2026-06-10 | Survey Sand Bedding and Compaction Test FIR for UPVC Pipe Line for Catch Basin of Storm Network @ ZONE-03 1- CB-199 TO CB-220 and CB-220 TO MH-4-4 | 601.43 | 3.52 | 2117.0336
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0603 | 2026-06-03 | Mechanical FIR for Installation and Laying of UPVC Pipe Line for Catch Basin of Storm Network @ ZONE-03 1- CB-199 TO CB-220 and CB-220 TO MH-4-4 | 601.43 | 45.81 | 27551.5083
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0607 | 2026-06-03 | Survey Excavation and Compaction Test FIR for UPVC Pipe Line for Catch Basin of Storm Network @ ZONE-03 1- CB-349 TO CB-358 | 601.43 | 2.67 | 1605.8181
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0608 | 2026-06-03 | Survey Sand Bedding and Compaction Test FIR for UPVC Pipe Line for Catch Basin of Storm Network @ ZONE-03 1- CB-349 TO CB-358 | 601.43 | 1.34 | 805.9162
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0611 | 2026-06-03 | Survey Excavation and Compaction Test FIR for UPVC Pipe Line for Catch Basin of Storm Network @ ZONE-03 1- CB-248 TO CB-284 and CB-284 TO MH-6-10 | 601.43 | 4.22 | 2538.0346
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0612 | 2026-06-03 | Survey Sand Bedding and Compaction Test FIR for UPVC Pipe Line for Catch Basin of Storm Network @ ZONE-03 1- CB-248 TO CB-284 and CB-284 TO MH-6-10 | 601.43 | 2.11 | 1269.0173
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0613 | 2026-06-03 | Survey Excavation and Compaction Test FIR for UPVC Pipe Line for Catch Basin of Storm Network @ ZONE-03 1- CB-231 TO CB-258 and CB-258 TO MH-6-10 | 601.43 | 4.25 | 2556.0775
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0614 | 2026-06-03 | Survey Sand Bedding and Compaction Test FIR for UPVC Pipe Line for Catch Basin of Storm Network @ ZONE-03 1- CB-231 TO CB-258 and CB-258 TO MH-6-10 | 601.43 | 2.13 | 1281.0459
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0620 | 2026-06-04 | Mechanical FIR for Installation and Laying of UPVC Pipe Line for Catch Basins of Storm Network from CB-276 TO MH-3-8-1 and CB-303 TO MH-3-8-1 @ ZONE-03, Pipe DIA 300mm | 601.43 | 18.25 | 10976.0975
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0621 | 2026-06-04 | Mechanical FIR for Installation and Laying of UPVC Pipe Line for Catch Basins of Storm Network from CB-281 TO CB-314 and CB-314 TO MH-3-7-1 @ ZONE-03, Pipe DIA 300mm | 601.43 | 33.93 | 20406.5199
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0622 | 2026-06-04 | Mechanical FIR for Installation and Laying of UPVC Pipe Line for Catch Basin of Storm Network from CB-175 TO CB-329, CB-329 TO MH-3-6-2 and CB-339 TO MH-3-6-2 @ ZONE-03, Pipe Dia 300mm | 601.43 | 61.31 | 36873.6733
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0623 | 2026-06-04 | Mechanical FIR for Installation and Laying of UPVC Pipe Line for Catch Basin of Storm Network from CB-268 TO CB-331 and CB-331 TO MH-3-5-1 @ ZONE-03, Pipe DIA 300mm | 601.43 | 44.48 | 26751.6064
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0624-01 | 2026-09-13 | Survey Excavation and Compaction Test FIR for UPVC Pipe Line for Group of Catch Basins Network of Storm Network Connecting to Manholes (RD-02), @ ZONE-04 1 - MH-6-24 (CB-30 TO CB-27 and CB-27 TO MH-6-24) 2- MH-6-23 (CB-23 TO CB-20 and CB-20 TO MH-6-23) 3- MH-6-22 (CB-25 TO CB-29 and CB-29 TO MH-6-22) 4- MH-6-21/0 (CB-63 TO MH-6-21/0) 5- MH-6-20 (CB-91 To CB-109 and CB-109 TO CB-140) 6- MH-6-19 (CB-116 TO CB-96 and CB-96 TO MH-6-19) 7- MH-6-18/0 (CB-85 TO CB-98 and CB-98 TO MH-6-18/0) 8- MH-6-17 (CB-117 TO MH-6-17) 9- MH-6-16 (CB-129 TO CB-113 and CB-113 TO CB-105) 10- MH-6-15 (CB-149 TO CB-173 and CB-173 TO MH-6-15) | 601.43 | 45.56 | 27401.1508
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0625-01 | 2026-09-13 | Survey FIR for Sand Bedding and Compaction Testing of UPVC Pipe Line for Group of Catch Basins Network of Storm Network Connecting to Manholes (RD-02), @ ZONE-04 1 - MH-6-24 (CB-30 TO CB-27 and CB-27 TO MH-6-24) 2- MH-6-23 (CB-23 TO CB-20 and CB-20 TO MH-6-23) 3- MH-6-22 (CB-25 TO CB-29 and CB-29 TO MH-6-22) 4- MH-6-21/0 (CB-63 TO MH-6-21/0) 5- MH-6-20 (CB-91 To CB-109 and CB-109 TO CB-140) 6- MH-6-19 (CB-116 TO CB-96 and CB-96 TO MH-6-19) 7- MH-6-18/0 (CB-85 TO CB-98 and CB-98 TO MH-6-18/0) 8- MH-6-17 (CB-117 TO MH-6-17) 9- MH-6-16 (CB-129 TO CB-113 and CB-113 TO CB-105) 10- MH-6-15 (CB-149 TO CB-173 and CB-173 TO MH-6-15) | 601.43 | 22.97 | 13814.8471
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0629 | 2026-06-08 | Mechanical FIR for Installation and Laying off UPVC Pipe Line for Group of Catch Basins Network of Storm Network Connecting to Manholes (RD-02), @ ZONE-04 1 MH-6-24 (CB-30 TO CB-27, CB-23 TO MH-6-24) and CB-27 TO MH-6-24) 2- MH-6-23 (CB-20 TO MH-6-23) 3- MH-6-22 (CB-25 TO CB-29 and CB-29 TO MH-6-22) 4- MH-6-21/0 (CB-63 TO MH-6-21/0) 5- MH-6-20 (CB-91 To CB-109 and CB-109 TO CB-140) 6- MH-6-19 (CB-116 TO CB-96 and CB-96 TO MH-6-19) 7- MH-6-18/0 (CB-85 TO CB-98 and CB-98 TO MH-6-18/0) 8- MH-6-17 (CB-117 TO MH-6-17) 9- MH-6-16 (CB-129 TO CB-113, CB-113 TO CB-105 and CB-105 TO MH-6-16) 10- MH-6-15 (CB-149 TO CB-173 and CB-173 TO MH-6-15) | 601.43 | 298.56 | 179562.9408
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0632 | 2026-06-08 | Survey Excavation and Compaction Test FIR for UPVC Pipe Line for Catch Basin of Storm Network @ ZONE-03 1- CB-320 TO CB-154 and CB-154 TO MH-6-8/0 | 601.43 | 4.29 | 2580.1347
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0633 | 2026-06-08 | Survey Excavation and Compaction Test FIR for UPVC Pipe Line for Catch Basin of Storm Network @ ZONE-03 1- CB-310 TO CB-306 and CB-306 TO MH-6-8-2 | 601.43 | 4.14 | 2489.9202
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0634 | 2026-06-08 | Survey Excavation and Compaction Test FIR for UPVC Pipe Line for Catch Basin of Storm Network @ ZONE-03 1- CB-333 TO CB-217 and CB-217 TO MH-6-3 | 601.43 | 5.55 | 3337.9365
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0635 | 2026-06-08 | Survey FIR for Sand Bedding and Compaction Test FIR for UPVC Pipe Line for Catch Basin of Storm Network @ ZONE-03 1- CB-333 TO CB-217 and CB-217 TO MH-6-3 | 601.43 | 2.78 | 1671.9754
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0636-01 | 2026-09-02 | Survey FIR for Sand Bedding and Compaction Test FIR for UPVC Pipe Line for Catch Basin of Storm Network @ ZONE-03 1- CB-154 TO MH-6-8/0 | 601.43 | 0.69 | 414.9867
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0637 | 2026-06-08 | Survey FIR for Sand Bedding and Compaction Test FIR for UPVC Pipe Line for Catch Basin of Storm Network @ ZONE-03 1- CB-310 TO CB-306 and CB-306 TO MH-6-8-2 | 601.43 | 2.07 | 1244.9601
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0695 | 2026-06-24 | Survey Excavation and Compaction Test FIR for UPVC Pipe Line for Catch Basin of Storm Network @ Arterial Road 1- CB-255 TO CB-279, CB-279 TO CB-151 and CB-151 TO MH-1-6 2- CB-145 TO CB-326 and CB-326 TO MH-1-5 3- CB-208 TO CB-202 and CB-202 TO MH-1-4 4- CB-348 TO CB-360 and CB-360 TO MH-1-3 5- CB-286 TO CB-301 and CB-301 TO MH-1-2 | 601.43 | 21.83 | 13129.2169
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0696-01 | 2026-07-06 | Survey FIR for Concrete Encasement at the Bottom Part of UPVC Pipe Line for Catch Basin of Storm Network @ Arterial Road 1- CB-255 TO CB-279, CB-279 TO CB-151 and CB-151 TO MH-1-6 2- CB-145 TO CB-326 and CB-326 TO MH-1-5 3- CB-208 TO CB-202 and CB-202 TO MH-1-4 4- CB-348 TO CB-360 and CB-360 TO MH-1-3 5- CB-286 TO CB-301 and CB-301 TO MH-1-2 | 601.43 | 10.91 | 6561.6013
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0806 | 2026-07-07 | Mechanical FIR for the Installation and Laying off UPVC Pipe Line with Connection of (Short Piece to Manholes) for Catch Basin of Storm Network @ Arterial Road 1- CB-255 TO CB-279, CB-279 TO CB-151 and CB-151 TO MH-1-6 2- CB-145 TO CB-326 and CB-326 TO MH-1-5 3- CB-208 TO CB-202 and CB-202 TO MH-1-4 4- CB-348 TO CB-360 and CB-360 TO MH-1-3 5- CB-286 TO CB-301 and CB-301 TO MH-1-2 | 601.43 | 141.89 | 85336.9027
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0835 | 2026-08-03 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-111 TO MH-3-17-1 CB-77 TO CB-92 & CB-92 TO MH-3-17-2 | 601.43 | 6.48 | 3897.2664
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0836 | 2026-08-03 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 MH-6-21-1 (CB-44 TO MH-6-21-1) MH-3-17-3 (CB-45 TO CB-48 & CB-57 TO MH-3-17-3) | 601.43 | 6.89 | 4143.8527
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0837 | 2026-08-03 | Survey Fir for Sand Bedding and Compaction Test for UPVC Pipe Line for Catch Basin of Storm Network, @ Zone-04 MH-6-21-1 (CB-44 TO MH-6-21-1) MH-3-17-3 (CB-45 TO CB-48 & CB-57 TO MH-3-17-3) | 601.43 | 3.45 | 2074.9335
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0840 | 2026-08-03 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-01 CB-5 to CB-3 and CB-3 to CB-2 (Mh-29-2 ) CB-88 TO CB-100 (MH-3-18) | 601.43 | 10.31 | 6200.7433
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0841 | 2026-08-04 | Survey Fir for Sand Bedding and Compaction Test for UPVC Pipe Line for Catch Basin of Storm Network, @ Zone-01 CB-5 to CB-3 and CB-3 to CB-2 (Mh-29-2 ) CB-88 TO CB-100 (MH-3-18) | 601.43 | 5.15 | 3097.3645
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0844 | 2026-08-08 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-35 TO CB-32 & CB-35 TO (MH-3-21) CB-42 TO (MH-3-20) | 601.43 | 4.25 | 2556.0775
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0845 | 2026-08-08 | Survey FIR for Sand Bedding and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-35 TO CB-32 & CB-35 TO (MH-3-21) CB-42 TO (MH-3-20) | 601.43 | 2.13 | 1281.0459
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0917 | 2026-08-13 | Survey and Mechanical FIR for the Installation and Laying off UPVC Pipe Line with for Catch Basin of Storm Network, @ Zone-04 MH-6-21-1 (CB-44 TO MH-6-21-1) MH-3-17-3 (CB-45 TO CB-48 & CB-57 TO MH-3-17-3) | 601.43 | 44.81 | 26950.0783
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0918 | 2026-08-13 | Survey Fir for Sand Bedding and Compaction Test for UPVC Pipe Line for Catch Basin of Storm Network, @ Zone-04 CB-111 TO MH-3-17-1 CB-77 TO CB-92 & CB-92 TO MH-3-17-2 | 601.43 | 3.24 | 1948.6332
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0919 | 2026-08-13 | Survey and Mechanical FIR for the Installation and Laying off UPVC Pipe Line with for Catch Basin of Storm Network, @ Zone-04 CB-111 TO MH-3-17-1 CB-77 TO CB-92 & CB-92 TO MH-3-17-2 | 601.43 | 42.15 | 25350.2745
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0920 | 2026-08-13 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-48 TO MH-3-17-3 | 601.43 | 0.21 | 126.3003
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0921 | 2026-08-13 | Survey FIR for Sand Bedding and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-48 TO MH-3-17-3 | 601.43 | 0.1 | 60.143
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0922 | 2026-08-15 | Survey and Mechanical FIR for the Installation and Laying off UPVC Pipe Line for Catch Basin of Storm Network 1: CB-88 TO CB-100 (MH-3-18) | 601.43 | 22.29 | 13405.8747
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0924 | 2026-08-16 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB_99 TO MH-3-18 & CB-100 TO MH-3-18 CB-65 Change to CB-99 | 601.43 | 1.96 | 1178.8028
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0925 | 2026-08-16 | Survey Fir for Sand Bedding and Compaction Test for UPVC Pipe Line for Catch Basin of Storm Network, @ Zone-04 CB_65 TO MH-3-18 & CB-100 TO MH-3-18 | 601.43 | 0.98 | 589.4014
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0930 | 2026-08-16 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-296 TO CB-303 (MH-3-8-1) CB 292 - TO CB 283 (MH-1-1) | 601.43 | 6.75 | 4059.6525
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0931 | 2026-08-16 | Survey FIR for Sand Bedding and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-296 TO CB-303 (MH-3-8-1) CB-292 TO CB-283 (MH-1-1) | 601.43 | 3.38 | 2032.8334
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0932 | 2026-08-17 | Survey and Mechanical FIR for the Installation and Laying off UPVC Pipe Line for Catch Basin of Storm Network, @ Zone-04 CB-100 TO MH-3-18 | 601.43 | 1.31 | 787.8733
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0933 | 2026-08-17 | Survey and Mechanical FIR for the Installation and Laying off UPVC Pipe Line for Catch Basin of Storm Network, @ Zone-04 CB-296 TO CB-303 (MH-3-8-1) CB-292 TO CB-283 (MH-1-1) | 601.43 | 43.88 | 26390.7484
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0936 | 2026-08-17 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB 283 TO (MH-1-1) | 601.43 | 2.4 | 1443.432
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0937 | 2026-08-17 | Survey Fir for Sand Bedding and Compaction Test for UPVC Pipe Line for Catch Basin of Storm Network, @ Zone-04 CB 283 TO (MH-1-1) | 601.43 | 1.2 | 721.716
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0938-01 | 2026-09-21 | Survey and Mechanical FIR for the Installation and Laying off UPVC Pipe Line for Catch Basin of Storm Network, @ Zone-04 CB 283 TO (MH-1-1) | 601.43 | 15.63 | 9400.3509
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0971-01 | 2026-09-21 | Survey and Mechanical FIR for the Installation and Laying of UPVC Pipe Line for Catch Basin of Storm Network, @ Zone-04 CB-35 TO CB-32 & CB-35 TO (MH-3-21) | 601.43 | 21.31 | 12816.4733
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0972 | 2026-08-25 | Survey and Mechanical FIR for the Installation and Laying of UPVC Pipe Line for Catch Basin of Storm Network, @ Zone-04 CB-99 TO (3-18) | 601.43 | 11.41 | 6862.3163
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0973 | 2026-08-25 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network CB-50 TO CB-54 & CB-54 TO MH-3-19 | 601.43 | 3.11 | 1870.4473
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0974 | 2026-08-25 | Survey FIR for Sand Bedding and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network CB-50 TO CB-54 & CB-54 TO MH-3-19 | 601.43 | 1.55 | 932.2165
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0983 | 2026-08-26 | Survey and Mechanical FIR for the Installation and Laying of UPVC Pipe Line for Catch Basin of Storm Network CB-50 TO CB-54 & CB-54 TO MH-3-19 | 601.43 | 20.18 | 12136.8574
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0998 | 2026-08-30 | Survey and Mechanical Fir for installation and laying of UPVC Pipe Line for Catch Basin of Storm Network, @ Zone-01 CB-3 to CB-2 (Mh-29-2) | 601.43 | 22.75 | 13682.5325
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0999 | 2026-08-30 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-65 TO MH-3-19 | 601.43 | 2.8 | 1684.004
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1000 | 2026-08-30 | Survey Fir for Concrete Encasement UPVC Pipe Line for Catch Basin of Storm Network, @ Zone-04 CB-65 TO MH-3-19 | 601.43 | 1.15 | 691.6445
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1007 | 2026-08-31 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-56 TO CB-79 & CB-79 TO MH-3-13-3 | 601.43 | 3.78 | 2273.4054
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1008 | 2026-08-31 | Survey FIR for Sand Bedding and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-56 TO CB-79 & CB-79 TO MH-3-13-3 | 601.43 | 1.89 | 1136.7027
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1009 | 2026-08-31 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-94 TO CB-118 & CB-118 TO MH-3-13-2 | 601.43 | 4.53 | 2724.4779
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1010 | 2026-08-31 | Survey FIR for Sand Bedding and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-94 TO CB-118 & CB-118 TO MH-3-13-2 | 601.43 | 2.26 | 1359.2318
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1011 | 2026-09-01 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-146 TO MH-3-13-1 | 601.43 | 0.25 | 150.3575
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1012 | 2026-09-01 | Survey FIR for Sand Bedding and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-146 TO MH-3-13-1 | 601.43 | 0.12 | 72.1716
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1015 | 2026-09-01 | Survey and Mechanical FIR for Installation and laying of UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-56 TO CB-79 & CB-79 TO MH-3-13-3 CB-94 TO CB-118 & CB-118 TO MH-3-13-2 | 601.43 | 53.96 | 32453.1628
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1016 | 2026-09-02 | Survey and Mechanical FIR for Installation and laying of UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-146 TO MH-3-13-1 | 601.43 | 1.61 | 968.3023
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1024 | 2026-09-06 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-86 TO (MH-6-18-1) CB-153 TO CB-177 & CB-177 TO MH-3-10-1 CB-204 TO MH-3-11 CB-207 TO MH-3-10-0 | 601.43 | 5.27 | 3169.5361
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1025 | 2026-09-06 | Survey FIR for Sand Bedding and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-86 TO (MH-6-18-1) CB-153 TO CB-177 & CB-177 TO MH-3-10-1 CB-204 TO MH-3-11 CB-207 TO MH-3-10-0 | 601.43 | 2.63 | 1581.7609
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1026 | 2026-09-07 | Survey and Mechanical FIR for installation and laying of UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-86 TO (MH-6-18-1) CB-153 TO CB-177 & CB-177 TO MH-3-10-1 CB-204 TO MH-3-11 CB-207 TO MH-3-10-0 | 601.43 | 34.25 | 20598.9775
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1028 | 2026-09-08 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-30 TO (MH-6-25) CB-31 TO CB-37 | 601.43 | 5.49 | 3301.8507
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1029 | 2026-09-08 | Survey FIR for Concrete Encasement for UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-30 TO (MH-6-25) | 601.43 | 1.28 | 769.8304
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1030 | 2026-09-08 | Survey FIR for Sand Bedding and compaction testing for UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-31 TO CB-37 | 601.43 | 1.47 | 884.1021
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1056 | 2026-09-09 | Survey and Mechanical FIR for Installation and laying of UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-30 TO (MH-6-25) CB-31 TO CB-37 | 601.43 | 35.69 | 21465.0367
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1062 | 2026-09-13 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-20 to MH-6-23 CB-144 TO MH-6-13 CB-158 TO CB-181 | 601.43 | 3.53 | 2123.0479
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1063 | 2026-09-13 | Survey FIR for Sand Bedding and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-20 to MH-6-23 CB-144 TO MH-6-13 CB-158 TO CB-181 | 601.43 | 1.76 | 1058.5168
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1066 | 2026-09-13 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-33 to CB-63 CB-69 TO MH-6-18-1 CB-122-1 TO MH-3-16 CB-122 TO CB-143 CB-127 TO CB-128 & CB-128 TO MH-3-15 CB-134 TO CB-143 CB-197 TO CB-200 & CB-200 TO MH-3-10-0 | 601.43 | 22.06 | 13267.5458
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1067 | 2026-09-13 | Survey FIR for Sand Bedding and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-33 to CB-63 CB-69 TO MH-6-18-1 CB-122-1 TO MH-3-16 CB-122 TO CB-143 CB-127 TO CB-128 & CB-128 TO MH-3-15 CB-134 TO CB-143 CB-197 TO CB-200 & CB-200 TO MH-3-10-0 | 601.43 | 11.03 | 6633.7729
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1068 | 2026-09-14 | Survey and Mechanical FIR for installation and laying of UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-20 to MH-6-23 CB-144 TO MH-6-13 CB-158 TO CB-181 | 601.43 | 22.94 | 13796.8042
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1070 | 2026-09-14 | Survey and Mechanical FIR for installation and laying of UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-33 to CB-63 CB-69 TO MH-6-18-1 CB-122-1 TO MH-3-16 CB-122 TO CB-143 CB-127 TO CB-128 & CB-128 TO MH-3-15 CB-134 TO CB-143 CB-197 TO CB-200 & CB-200 TO MH-3-10-0 | 601.43 | 143.42 | 86257.0906
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1086 | 2026-09-15 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-03 CB-235 to CB-362 & CB-346 TO CB-352 & CB-352 TO MH-4-3 CB-351 TO CB-361 & CB-345 TO CB-244 (MH-4-1) | 601.43 | 13.01 | 7824.6043
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1087 | 2026-09-15 | Survey FIR for Sand Bedding and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-03 CB-235 to CB-362 & CB-346 TO CB-352 & CB-352 TO MH-4-3 CB-351 TO CB-361 & CB-345 TO CB-244 (MH-4-1) | 601.43 | 6.5 | 3909.295
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1098 | 2026-09-16 | Survey and Mechanical FIR for installation and laying of UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-03 CB-235 to CB-362 & CB-346 TO CB-352 & CB-352 TO MH-4-3 CB-351 TO CB-361 & CB-345 TO CB-244 (MH-4-1) | 601.43 | 84.55 | 50850.9065
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1101 | 2026-09-21 | Survey and Mechanical Fir for Installation of UPVC Pipe Line for Catch Basin of Storm Network, @ Zone-04 CB-65 TO MH-3-19 | 601.43 | 14.93 | 8979.3499
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1104 | 2026-09-21 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-03 CB-253 to CB-357 (MH-6-2) CB-362 TO MH-4-3 | 601.43 | 2.18 | 1311.1174
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1105 | 2026-09-21 | Survey FIR for Sand Bedding and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-03 CB-253 to CB-357 (MH-6-2) CB-362 TO MH-4-3 | 601.43 | 1.09 | 655.5587
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1112 | 2026-09-22 | Survey and Mechanical FIR for installation and laying of UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-03 CB-253 to CB-357 (MH-6-2) CB-362 TO MH-4-3 | 601.43 | 14.19 | 8534.2917
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1125 | 2026-10-07 | Survey FIR for backfilling and compaction testing 2nd layer above UPVC Pipe Line for Group of Catch Basins of Storm Network Connecting to Manholes @ ZONE-01 CB-3 to CB-2 (Mh-29-2) | 601.43 | 3.5 | 2105.005
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1130 | 2026-10-07 | Survey FIR for backfilling and compaction testing of 1st layer sand covering above UPVC Pipe Line for Group of Catch Basins of Storm Network Connecting to Manholes (RD-01), @ ZONE-01 1- MH-28-0 (CB-9 TO MH-28-0) 3- MH-28-2 (CB-16 TO MH-28-2) 6- MH-20-6 (CB-67 TO CB-81(1) | 601.43 | 5.01 | 3013.1643
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1152 | 2026-10-07 | Survey FIR for backfilling and compaction testing of 3rd layer above UPVC Pipe Line for Group of Catch Basins of Storm Network Connecting to Manholes (RD-01), @ ZONE-01 1- MH-28-1 CB-14(4) TO MH-28-1) 2- MH-28-3 CB-28 TO CB-34) 3- MH-20-5 CB-62 TO CB-58 and CB-58 TO MH-20-5) 4- MH-20-3 (CB-70 TO CB-52 and CB-52 TO MH-20-3) | 601.43 | 16.74 | 10067.9382
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1157 | 2026-09-28 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone- 03 CB-142 TO MH-3-7 CB-160 TO CB-169 (MH-6-4) CB-187 TO MH-3-6 CB-323 TO CB-196 & CB-196 TO MH-3-6 CB-210 TO CB-237 (MH-3-9} CB-211 TO CB-318(2) (MH-3-5) CB-237 TO MH-3-9 CB-307 TO CB-318 (MH-3-8) CB-308 TO CB-318 (MH-3-8) CB-337 TO CB-318(2) (MH-3-5) CB-171 TO CB-6-12 CB-373 TO CB-374 (MH-1) CB-223 TO CB-234 ( MH-6-2-8) CB-336 TO CB-241 (MH-6-3 CB-242 TO CB-266 (MH-6-2-7) CB-243 TO CB-270 (MH-6-1-8) CB-372 TO MH-1-1 | 601.43 | 40.79 | 24532.3297
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1158 | 2026-09-28 | Mechanical FIR for Final Air testing of GRP Storm Drainage PIPE from MH-3-20 to MH-3-21 @ RD-2 , ZONE-04 | 601.43 | 20.39 | 12263.1577
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1160 | 2026-09-29 | Survey FIR for Sand Bedding and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone- 03 CB-142 TO MH-3-7 CB-160 TO CB-169 (MH-6-4) CB-187 TO MH-3-6 CB-323 TO CB-196 & CB-196 TO MH-3-6 CB-237 TO MH-3-9 CB-307 TO CB-318 (MH-3-8) CB-337 TO CB-318(2) (MH-3-5) CB-171 TO CB-6-12 CB-373 TO CB-374 (MH-1) CB-223 TO CB-234 ( MH-6-2-8) CB-336 TO CB-241 (MH-6-3 CB-243 TO CB-270 (MH-6-1-8) | 601.43 | 13.88 | 8347.8484
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1161 | 2026-09-29 | Survey FIR for Concrete Encasement for UPVC Pipe Line for Catch Basins of Storm Network, @ Zone- 03 CB-308 TO CB-318 (MH-3-8) CB-372 TO MH-1-1 CB-242 TO CB-266 (MH-6-2-7) CB-211 TO CB-318(2) (MH-3-5) CB-210 TO CB-237 (MH-3-9} | 601.43 | 6.51 | 3915.3093
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1162 | 2026-09-29 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone- 02 CB-132 TO CB-162 & CB-162 TO MH-6-11-1 CB-178 TO CB-194 (MH-8-14) CB-188 TO MH-6-11-0 CB-230 TO MH-6-9-1-3 | 601.43 | 8.64 | 5196.3552
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1163 | 2026-09-29 | Survey FIR for Sand Bedding and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone- 02 CB-188 TO MH-6-11-0 CB-230 TO MH-6-9-1-3 | 601.43 | 2.18 | 1311.1174
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1167 | 2026-09-29 | Survey FIR for Concrete Encasement for UPVC Pipe Line for Catch Basins of Storm Network, @ Zone- 03 CB-132 TO CB-162 & CB-162 TO MH-6-11-1 CB-178 TO CB-194 (MH-8-14) | 601.43 | 1.92 | 1154.7456
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1175 | 2026-09-30 | Survey and Mechanical FIR for installation and laying of UPVC Pipe Line for Catch Basins of Storm Network, @ Zone- 03 CB-142 TO MH-3-7 CB-160 TO CB-169 (MH-6-4) CB-187 TO MH-3-6 CB-323 TO CB-196 & CB-196 TO MH-3-6 CB-210 TO CB-237 (MH-3-9} CB-211 TO CB-318(2) (MH-3-5) CB-237 TO MH-3-9 CB-307 TO CB-318 (MH-3-8) CB-308 TO CB-318 (MH-3-8) CB-337 TO CB-318(2) (MH-3-5) CB-171 TO CB-6-12 CB-373 TO CB-374 (MH-1) CB-223 TO CB-234 ( MH-6-2-8) CB-336 TO CB-241 (MH-6-3 CB-242 TO CB-266 (MH-6-2-7) CB-243 TO CB-270 (MH-6-1-8) CB-372 TO MH-1-1 | 601.43 | 265.11 | 159445.1073
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1176 | 2026-09-30 | Survey and Mechanical FIR for installation and laying of UPVC Pipe Line for Catch Basins of Storm Network, @ Zone- 02 CB-132 TO CB-162 & CB-162 TO MH-6-11-1 CB-178 TO CB-194 (MH-8-14) CB-188 TO MH-6-11-0 CB-230 TO MH-6-9-1-3 | 601.43 | 4.32 | 2598.1776
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1179 | 2026-09-30 | Mechanical FIR for Final Air testing of GRP Strom Drainage PIPE from CB-52 TO MH-20-3 CB-52 TO CB-70 CB-83 TO MH-20-4 @Rd 1, Zone 1 | 601.43 | 6.89 | 4143.8527
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1180 | 2026-10-01 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone- 03 CB-133 TO MH-6-9-0 CB-229 TO CB-229(1) & CB-229(1) TO MH-6-8-4 CB-278 TO MH-6-9-1 CB-282 TO MH-6-9-0 CB-287 TO MH-6-8-3 CB-313 TO MH-6-8-2 | 601.43 | 5.57 | 3349.9651
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1181 | 2026-10-01 | Survey FIR for Sand Bedding and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone- 03 CB-133-MH-6-9-0 CB-287-MH-6-8-3 | 601.43 | 0.47 | 282.6721
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1182 | 2026-10-01 | Survey FIR for Concrete Encasement at Bottom part of VPVC Pipe lines between Catch basin of of Storm Network, @ Zone- 03 CB-313-MH-6-8-2 | 601.43 | 0.08 | 48.1144
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1190 | 2026-10-01 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from CB-62 to CB-58 CB-75 to CB-62 CB-67 to CB-81-1 ROAD 1, ZONE 1 | 601.43 | 10.41 | 6260.8863
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1191 | 2026-10-01 | Survey and Mechanical FIR for installation and laying of UPVC Pipe Line for Catch Basins of Storm Network, @ Zone- 03 CB-133 TO MH-6-9-0 CB-229 TO CB-229(1) & CB-229(1) TO MH-6-8-4 CB-278 TO MH-6-9-1 CB-282 TO MH-6-9-0 CB-287 TO MH-6-8-3 CB-313 TO MH-6-8-2 | 601.43 | 36.2 | 21771.766
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1194 | 2026-10-01 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from CB-255 to CB-279 CB-279 to CB-151 CB-151 to MH-1-6 CB-145 to CB-326 CB-326 to MH-1-5 Arterial Road , ZONE 2 | 601.43 | 10.23 | 6152.6289
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1195 | 2026-10-01 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from CB-208 to CB-202 CB-202 to MH-1-4 CB-348 to CB-360 CB-360 to MH-1-3 CB-286 to CB-301 CB-301 to MH-1-2 CB-292 to CB-283 CB-283 to MH-1-1 CB-372 to MH-1-1 CB-373 to CB-374 Arterial Road , ZONE 3 | 601.43 | 19.99 | 12022.5857
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1198 | 2026-10-01 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from CB-83 to CB-71 CB-43 to MH-28-4 CB-34 to CB-28 CB-28 to MH-28-3 Road-1 , ZONE 1 | 601.43 | 5.6 | 3368.008
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1199 | 2026-10-04 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from CB-45 to CB-48 CB-57 to MH-3-17-3 CB-77 to CB-92 CB-92 to MH-3-17-2 CB-111 to MH-3-17-1 Road-3 , ZONE 2 | 601.43 | 11 | 6615.73
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1200 | 2026-10-05 | Survey FIR for Sand Bedding and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone- 03 CB-229-CB-229 (1) &CB-229 (1)-MH-6-8-4 CB-278-MH-6-9-1 CB-282-MH-6-9-0 | 601.43 | 2.24 | 1347.2032
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1201 | 2026-10-05 | Survey FIR for Excavation and compaction testing of UPVC Pipe Line for Catch Basins of Storm Network, CB-76 TO CB-90 CB-90 TO MH-18-2 CB-112 TO CB-135 CB-150 TO CB-195 | 601.43 | 9.64 | 5797.7852
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1202 | 2026-10-05 | Survey FIR for Sand bedding and compaction testing for UPVC Pipe Line for Catch Basins of Storm Network, CB-76 TO CB-90 CB-90 TO MH-18-2 CB-112 TO CB-135 CB-150 TO CB-195 | 601.43 | 4.82 | 2898.8926
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1205 | 2026-10-05 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from CB-44 to MH-6-21-1 Road-3 , ZONE 1 | 601.43 | 2.38 | 1431.4034
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1209 | 2026-10-06 | Survey and Mechanical FIR for installation and laying of UPVC Pipe Line for Catch Basins of Storm Network, CB-76 TO CB-90 & CB-90 TO MH-18-2 CB-112 TO CB-135 CB-150 TO CB-195 | 601.43 | 62.68 | 37697.6324
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1211 | 2026-10-05 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network CB-114 TO CB-164 & CB-164 TO MH-14-3 CB-236 TO MH-6-9-3 CB-319 TO MH-6-1-3 | 601.43 | 4.85 | 2916.9355
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1212 | 2026-10-05 | Survey FIR for Sand Bedding and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network CB-114 TO CB-164 & CB-164 TO MH-14-3 CB-236 TO MH-6-9-3 CB-319 TO MH-6-1-3 | 601.43 | 2.42 | 1455.4606
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1213 | 2026-10-07 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from CB-30-1- to CB-27 CB-27 to MH-6-24 CB-23 to MH-6-24 CB-31 to CB-37 CB-30 to MH-6-25 Road-2 , ZONE 4 | 601.43 | 8.55 | 5142.2265
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1215 | 2026-10-07 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network CB-103 to CB-110 & CB-110 TO MH-6-11-2 CB-148 TO MH-6-2-2 CB-227 TO MH-6-2-6 CB-241 TO MH-6-3 CB-269 TO MH-6-2-4 CB-288 TO MH-6-1-5 CB-334 TO CB-347 CB-340 TO MH-6-1 CB-342 TO MH-6-1 | 601.43 | 16.85 | 10134.0955
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1216 | 2026-10-07 | Survey FIR for Sand Bedding and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network CB-103 to CB-110 & CB-110 TO MH-6-11-2 CB-148 TO MH-6-2-2 CB-227 TO MH-6-2-6 CB-241 TO MH-6-3 CB-269 TO MH-6-2-4 CB-288 TO MH-6-1-5 CB-334 TO CB-347 CB-340 TO MH-6-1 CB-342 TO MH-6-1 | 601.43 | 8.42 | 5064.0406
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1219 | 2026-10-08 | Survey And Mechanical FIR for installation and laying of UPVC Pipe Line for Catch Basins of Storm Network CB-114 TO CB-164 & CB-164 TO MH-14-3 CB-236 TO MH-6-9-3 CB-319 TO MH-6-1-3 | 601.43 | 31.52 | 18957.0736
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1220 | 2026-10-08 | Survey and Mechanical FIR for installation and laying of UPVC Pipe Line for Catch Basins of Storm Network CB-103 to CB-110 & CB-110 TO MH-6-11-2 CB-148 TO MH-6-2-2 CB-227 TO MH-6-2-6 CB-241 TO MH-6-3 CB-269 TO MH-6-2-4 CB-288 TO MH-6-1-5 CB-334 TO CB-347 CB-340 TO MH-6-1 CB-342 TO MH-6-1 | 601.43 | 109.51 | 65862.5993
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1223 | 2026-10-08 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from CB-32 to CB-35 CB-35 to MH-3-21 CB-50 to CB-54 CB-54 to MH-3-19 CB-65 to MH-3-19 Road-2 , ZONE 4 | 601.43 | 8.68 | 5220.4124
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1225 | 2026-10-08 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from CB-69 to MH-6-18-1 CB-56 to CB-79 CB-79 to MH-3-13-3 CB-94 to CB-118 CB-118 to MH-3-13-2 CB-146 to MH-3-13-1 Road-4 , ZONE-01 & 04 | 601.43 | 10.92 | 6567.6156
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1226 | 2026-10-08 | Survey and Mechanical FIR for installation and laying of UPVC Pipeline for Catch Basins of Storm Network, CB-42 TO MH-3-20 & CB-48 TO MH-3-17-3@ ZONE-04 | 601.43 | 7.66 | 4606.9538
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1227 | 2026-10-10 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from CB-88 to CB-100 CB-100 to MH-3-18 CB-134 to CB-143 CB-122 to CB-143 CB-122-1 to MH-3-16 CB-127 to CB-128 CB-128 to MH-3-15 Road-2 , ZONE- 04 | 601.43 | 12.06 | 7253.2458
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1228 | 2026-10-10 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network CB-47 to MH-6-21-1 CB-198 TO CB-318(1) CB-192 TO MH-3-13 CB-170 TO MH-3-14 CB-97 TO MH-3-17-2 @ Zone- 04 | 601.43 | 4.26 | 2562.0918
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1229 | 2026-10-10 | Survey FIR for Sand Bedding and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network CB-47 to MH-6-21-1 CB-198 TO CB-318(1) CB-192 TO MH-3-13 CB-170 TO MH-3-14 CB-97 TO MH-3-17-2 @ Zone- 04 | 601.43 | 2.13 | 1281.0459
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1235 | 2026-10-11 | Survey and Mechanical FIR for installation and laying of UPVC Pipe Line for Catch Basins of Storm Network CB-47 to MH-6-21-1 CB-198 TO CB-318(1) CB-192 TO MH-3-13 CB-170 TO MH-3-14 CB-97 TO MH-3-17-2 @ Zone- 04 | 601.43 | 27.67 | 16641.5681
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1239 | 2026-10-12 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from CB-58 to MH-20-5 CB-24 to CB-28 Road-1 , ZONE- 01 | 601.43 | 3.12 | 1876.4616
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1241 | 2026-10-12 | Survey FIR for Backfilling and compaction testing of 1st layer sand cover of UPVC Pipe Line for Catch Basins of Storm Network CB-47 to MH-6-21-1 CB-198 TO CB-318(1) CB-170 TO MH-3-14 @ Zone- 04 | 601.43 | 3.67 | 2207.2481
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1243 | 2026-10-12 | Survey FIR for Backfilling and compaction testing of 2nd layer above UPVC Pipe Line for Catch Basins of Storm Network CB-97 to MH-3-17-2 CB-192 TO MH-3-13 @ Zone- 04 | 601.43 | 0.59 | 354.8437
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1247 | 2026-10-12 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from CB-59 to MH-20-2 CB-82 to CB-93 CB-93 to CB-102 CB-16 to MH-28-2 CB-14 to CB-14(4) CB-14(4) to MH-28-1 Road-1 , ZONE- 01 | 601.43 | 12.24 | 7361.5032
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1251 | 2026-10-13 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from CB-47 to MH-6-21-1 CB-48 to MH-3-17-3 CB-42 to MH-3-20 CB-170 to MH-3-14 CB-192 to MH-3-13 CB-198 to CB-318(1) CB-210 to CB-237 CB-237 to MH-3-9 CB-99 to MH-3-18 Road-2 & 3 , ZONE- 04 | 601.43 | 10.79 | 6489.4297
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1255 | 2026-10-14 | Survey FIR for Backfilling and compaction testing of 4th layer above UPVC Pipeline for Catch Basins of Storm Network, 1. CB-48 TO MH-3-17-3 @ ZONE-04 | 601.43 | 0.21 | 126.3003
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1256 | 2026-10-14 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from 1. CB-200 to MH-3-10 2. CB-197 to CB-200 3. CB-153 to CB-177 4. CB-177 to MH-3-10-1 5. CB-144 to MH-6-13 Road-2 , ZONE- 04 | 601.43 | 9.72 | 5845.8996
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1258 | 2026-10-17 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from 1. CB-20 to MH-6-23 2. CB-25 to CB-29 3. CB-29 to MH-6-22 4. CB-33 to CB-63 5. CB-63 to MH-6-21 6. CB-91 to CB-109 7. CB-109 to CB-140 8. CB-116 to CB-96 9. CB-96 to MH-6-19 10. CB-85 to CB-98 11. CB-98 to MH-6-18 Road-2 , ZONE- 01 | 601.43 | 27.34 | 16443.0962
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1283 | 2026-10-18 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from 1. CB-307 to CB-318 2. CB-318 to CB-308 3. CB-296 to CB-303 4. CB-303 to MH-3-8-1 5. CB-276 to MH-3-8-1 6. CB-142 to MH-3-7 7. CB-281 to CB-314 8. CB-314 to MH-3-7-1 Road-2 & Plot-D , ZONE- 03 | 601.43 | 18.58 | 11174.5694
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1304 | 2026-10-19 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from 1. CB-337 to CB-3-18(2) 2. CB-211 to CB-3-18(2) 3. CB-331 to MH-3-5-1 4. CB-268 to CB-331 5. CB-323 to CB-196 6. CB-196 to MH-3-6 7. CB-187 to MH-3-6 8. CB-175 to CB-329 9. CB-329 to MH-3-6-2 10. CB-339 to MH-3-6-2 Road-2 & Plot-D , ZONE- 03 | 601.43 | 27.51 | 16545.3393
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1306 | 2026-10-19 | Survey FIR for Excavation and compaction testing of UPVC Strom Drainage PIPE from 1. CB-183 to MH-8-11 ZONE- 02 | 601.43 | 2.08 | 1250.9744
B6.33 42 11.35 | UPVC-300mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1307 | 2026-10-19 | Survey FIR for Sand bedding and compaction testing of UPVC Strom Drainage PIPE from 1. CB-183 to MH-8-11 ZONE- 02 | 601.43 | 1.04 | 625.4872
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0472-01 | 2026-09-02 | Survey Excavation and Compaction Test FIR for UPVC Pipe Line for Group of Catch Basins Network of Storm Network Connecting to Manholes (RD-01), @ ZONE-01 1- MH-20-6 (CB-81 (1) TO MH-20-6) 2- MH-20-4 (CB-83 TO MH-20-4) 3- MH-20-1 (CB-102 TO MH-20-1) | 600.552 | 0.47 | 282.2594
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0473-01 | 2026-09-02 | Survey FIR for Sand Bedding of UPVC Pipe Line for Group of Catch Basins Network of Storm Network Connecting to Manholes (RD-01), @ ZONE-01 1- MH-20-6 (CB-81 (1) TO MH-20-6) 2- MH-20-4 (CB-83 TO MH-20-4) 3- MH-20-1 (CB-102 TO MH-20-1) | 600.552 | 0.24 | 144.1325
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0477-00 | 2026-04-14 | Mechanical FIR for Installation and Laying off UPVC Pipe Line for Group of Catch Basins Network of Storm Network Connecting to Manholes (RD-01), @ ZONE-01 1- MH-20-6 (CB-81 (1) TO MH-20-6) 2- MH-20-4 (CB-83 TO MH-20-4) 3- MH-20-1 (CB-102 TO MH-20-1) | 600.552 | 3.08 | 1849.7002
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0604-00 | 2026-06-03 | Survey Excavation and Compaction Test FIR for UPVC Pipe Line for Catch Basin of Storm Network @ ZONE-03 1- CB-256 TO MH-4-3 | 600.552 | 2.27 | 1363.253
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0605-00 | 2026-06-03 | Survey Sand Bedding and Compaction Test FIR for UPVC Pipe Line for Catch Basin of Storm Network @ ZONE-03 1- CB-256 TO MH-4-3 | 600.552 | 1.14 | 684.6293
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0609-00 | 2026-06-03 | Survey Excavation and Compaction Test FIR for UPVC Pipe Line for Catch Basin of Storm Network @ ZONE-03 1- CB-358 TO MH-4-2 | 600.552 | 0.7 | 420.3864
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0610-00 | 2026-06-03 | Survey Sand Bedding and Compaction Test FIR for UPVC Pipe Line for Catch Basin of Storm Network @ ZONE-03 1- CB-358 TO MH-4-2 | 600.552 | 0.35 | 210.1932
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0626-01 | 2026-09-08 | Survey FIR for Excavation and Compaction Testing of UPVC Pipe Line for Group of Catch Basins Network of Storm Network Connecting to Manholes (RD-02), @ ZONE-04 1 - MH-6-20 (CB-140 TO MH-6-20) 2- MH-6-16 (CB-105 TO MH-6-16) | 600.552 | 0.21 | 126.1159
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0627-01 | 2026-09-08 | Survey FIR for Sand Bedding and Compaction Testing of UPVC Pipe Line for Group of Catch Basins Network of Storm Network Connecting to Manholes (RD-02), @ ZONE-04 1 - MH-6-20 (CB-140 TO MH-6-20) 2- MH-6-16 (CB-105 TO MH-6-16) | 600.552 | 0.11 | 66.0607
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0631-00 | 2026-06-08 | Mechanical FIR for Installation and Laying off UPVC Pipe Line for Group of Catch Basins Network of Storm Network Connecting to Manholes (RD-02), @ ZONE-04 1 - MH-6-20 (CB-140 TO MH-6-20) | 600.552 | 1.38 | 828.7618
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1031 | 2026-09-08 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-37 to MH-6-25 | 600.552 | 0.35 | 210.1932
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1032 | 2026-09-08 | Survey FIR for Sand Bedding and compaction testing for UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-37 to MH-6-25 | 600.552 | 0.17 | 102.0938
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1057 | 2026-09-09 | Survey and Mechanical FIR for Installation and laying for UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-37 to MH-6-25 | 600.552 | 2.24 | 1345.2365
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1064 | 2026-09-13 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-181 to MH-6-14 | 600.552 | 0.37 | 222.2042
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1065 | 2026-09-13 | Survey FIR for Sand Bedding and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-181 to MH-6-14 | 600.552 | 0.18 | 108.0994
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1069 | 2026-09-14 | Survey and Mechanical FIR for installation and laying of UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-04 CB-181 to MH-6-14 | 600.552 | 2.4 | 1441.3248
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1106 | 2026-09-21 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-03 CB-244 to MH-4-1 CB-357 TO CB-265 & CB-265 TO MH-6-2 CB-361 TO MH-4-1 | 600.552 | 4.46 | 2678.4619
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1107 | 2026-09-21 | Survey FIR for Sand Bedding and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-03 CB-244 to MH-4-1 CB-357 TO CB-265 & CB-265 TO MH-6-2 CB-361 TO MH-4-1 | 600.552 | 2.23 | 1339.231
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1113 | 2026-09-22 | Survey and Mechanical FIR for installation and laying of UPVC Pipe Line for Catch Basins of Storm Network, @ Zone-03 CB-244 to MH-4-1 CB-357 TO CB-265 & CB-265 TO MH-6-2 CB-361 TO MH-4-1 | 600.552 | 29.02 | 17428.019
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1128 | 2026-09-26 | Survey FIR for backfilling and compaction testing 2nd layer above UPVC Pipe Line for Group of Catch Basins of Storm Network Connecting to Manholes (RD-01), @ ZONE-01 1- MH-20-6 (CB-81 (1) TO MH-20-6) 2- MH-20-4 (CB-83 TO MH-20-4) 3- MH-20-1 (CB-102 TO MH-20-1) | 600.552 | 0.44 | 264.2429
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1164 | 2026-09-29 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone- 03 CB-234 TO MH-6-2-8 CB-266 TO MH-6-2-7 CB-318 TO MH-3-8 CB-355 TO MH-3-2 CB-365 (2) TO MH-3-1 CB-365 TO MH-3-3 CB-374 TO MH-1 | 600.552 | 5.41 | 3248.9863
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1165 | 2026-09-29 | Survey FIR for Sand Bedding and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network, @ Zone- 03 CB-234 TO MH-6-2-8 CB-318 TO MH-3-8 CB-355 TO MH-3-2 CB-365 (2) TO MH-3-1 CB-365 TO MH-3-3 CB-374 TO MH-1 | 600.552 | 2.68 | 1609.4794
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1166 | 2026-09-29 | Survey FIR for Concrete Encasement for UPVC Pipe Line for Catch Basins of Storm Network, @ Zone- 03 CB-266 TO MH-6-2-7 | 600.552 | 0.03 | 18.0166
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1177 | 2026-09-30 | Survey and Mechanical FIR for installation and laying of UPVC Pipe Line for Catch Basins of Storm Network, @ Zone- 03 CB-234 TO MH-6-2-8 CB-266 TO MH-6-2-7 CB-318 TO MH-3-8 CB-355 TO MH-3-2 CB-365 (2) TO MH-3-1 CB-365 TO MH-3-3 CB-374 TO MH-1 | 600.552 | 35.17 | 21121.4138
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1196 | 2026-10-03 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from CB-374 to MH-1 Arterial Road , ZONE 3 | 600.552 | 2.33 | 1399.2862
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1203 | 2026-10-05 | Survey FIR for Excavation and compaction testing of UPVC Pipe Line for Catch Basins of Storm Network, CB-135 TO MH-18-3 | 600.552 | 0.22 | 132.1214
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1204 | 2026-10-05 | Survey FIR for sand bedding and compaction testing for UPVC Pipe Line for Catch Basins of Storm Network, CB-135 TO MH-18-3 | 600.552 | 0.11 | 66.0607
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1210 | 2026-10-06 | Survey and Mechanical FIR for installation and laying of UPVC Pipe Line for Catch Basins of Storm Network, CB-135 TO MH-18-3 | 600.552 | 1.4 | 840.7728
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1214 | 2026-10-07 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from CB-37 to MH-6-25 Road-2 , ZONE 4 | 600.552 | 0.35 | 210.1932
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1217 | 2026-10-07 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network CB-270 to MH-6-1-8 CB-347 TO MH-6-1 | 600.552 | 0.2 | 120.1104
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1218 | 2026-10-07 | Survey FIR for Sand Bedding and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network CB-270 to MH-6-1-8 CB-347 TO MH-6-1 | 600.552 | 0.1 | 60.0552
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1221 | 2026-10-08 | Survey and Mechanical FIR for installation and laying of UPVC Pipe Line for Catch Basins of Storm Network CB-270 to MH-6-1-8 CB-347 TO MH-6-1 | 600.552 | 1.27 | 762.701
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1230 | 2026-10-10 | Survey FIR for Excavation and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network CB-318(1) to MH-3-12 CB-143 TO CB-3-17 @ Zone- 04 | 600.552 | 0.41 | 246.2263
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1231 | 2026-10-10 | Survey FIR for Sand Bedding and Compaction Testing UPVC Pipe Line for Catch Basins of Storm Network CB-3-18-1 to MH-3-12 CB-143 TO CB-3-17 @ Zone- 04 | 600.552 | 0.21 | 126.1159
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1236 | 2026-10-11 | Survey and Mechanical FIR for installation and laying of UPVC Pipe Line for Catch Basins of Storm Network CB-318(1) to MH-3-12 CB-143 TO CB-3-17 @ Zone- 04 | 600.552 | 2.67 | 1603.4738
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1240 | 2026-10-12 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from CB-81 (1) to MH-20-6 Road-1 , ZONE- 01 | 600.552 | 0.09 | 54.0497
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1245 | 2026-10-12 | Survey FIR for Backfilling and compaction testing of 2nd layer above UPVC Pipe Line for Catch Basins of Storm Network CB-143 to MH-3-17 @ Zone- 04 | 600.552 | 0.23 | 138.127
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1246 | 2026-10-12 | Survey FIR for Backfilling and compaction testing of 1st layer sand cover above UPVC Pipe Line for Catch Basins of Storm Network CB-3-18(1) to MH-3-12 @ Zone- 04 | 600.552 | 0.18 | 108.0994
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1248 | 2026-10-12 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from CB-102 to MH-20-1 Road-1 , ZONE- 01 | 600.552 | 0.21 | 126.1159
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1252 | 2026-10-13 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from CB-3-18(1) to MH-3-12 Road-2 , ZONE- 04 | 600.552 | 0.18 | 108.0994
B6.33 42 11.36 | UPVC-400mm Diameter Depth less than 1.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1259 | 2026-10-17 | Mechanical FIR for Final Air testing of UPVC Strom Drainage PIPE from 1. CB-140 to MH-6-20 Road-2 , ZONE- 01 | 600.552 | 0.21 | 126.1159
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0501-00 | 2026-05-09 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes MH-29-3, @ ZONE-01 | 8981.94 | 0.05 | 449.097
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0645-01 | 2026-07-07 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes MH-3-17-2 and MH-3-17-3, @ ZONE-04 | 8981.94 | 0.1 | 898.194
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0655-00 | 2026-06-15 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes MH-3-20 and MH-3-21, @ ZONE-04 | 8981.94 | 0.1 | 898.194
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0664-00 | 2026-06-16 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes, @ Arterial Road 1- MH-1-6 2- MH-1-5 3- MH-1-4 4- MH-1-3 5- MH-1-2 | 8981.94 | 0.25 | 2245.485
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0676-00 | 2026-06-18 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes, @ Zone-03 1- MH-3-5-1 2- MH-3-7-1 3- MH-3-6-1 4- MH-3-6-2 | 8981.94 | 0.2 | 1796.388
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0683-00 | 2026-06-21 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes, @ Zone-01 and Zone-03 1- MH-29-4 2- MH-3-8-1 3- MH-6-9-1 4- MH-6-9-2 5- MH-6-9-3 6- MH-6-9-1-1 7- MH-6-9-1-2 8- MH-6-9-1-3 | 8981.94 | 0.4 | 3592.776
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0692-00 | 2026-06-21 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes, @ Zone-03 1- MH-8-13 2- MH-8-14 3- MH-8-15 | 8981.94 | 0.15 | 1347.291
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0697-00 | 2026-06-24 | FIR for Installation of Manhole Base of Storm Network, @ Arterial Road 1- MH-1-6 2- MH-1-5 3- MH-1-4 4- MH-1-3 5- MH-1-2 | 8981.94 | 1.5 | 13472.91
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0698-00 | 2026-06-24 | FIR for Installation of Manhole Base of Storm Network, @ Zone-01, Zone-03 and Zone-04 1- MH-29-3 2- MH-29-4 3- MH-3-6-1 4- MH-3-6-2 5- MH-3-7-1 6- MH-3-8-1 7- MH-3-17-2 8- MH-3-17-3 | 8981.94 | 2.4 | 21556.656
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0702-00 | 2026-06-24 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes, @ Zone-03 1- MH-4-1 2- MH-4-2 3- MH-4-3 4- MH-4-4 | 8981.94 | 0.2 | 1796.388
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0709-01 | 2026-09-07 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes, @ Zone-03 1- MH-6-1-1 2- MH-6-1-2 3- MH-6-1-3 4- MH-6-1-4 5- MH-6-1-5 6- MH-6-1-6 7- MH-6-1-7 8- MH-6-2-1 9- MH-6-2-2 10- MH-6-2-3 11- MH-6-2-5 12- MH-6-2-4 13- MH-6-2-6 | 8981.94 | 0.65 | 5838.261
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0733-00 | 2026-06-25 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes, @ Zone-04 1- MH-6-21-1 | 8981.94 | 0.05 | 449.097
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0739-00 | 2026-06-29 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes, @ Zone-04 1- MH-3-10-1 | 8981.94 | 0.05 | 449.097
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0745-00 | 2026-06-30 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes, @ Zone-01 and Zone-03 1- MH-28-3 2- MH-28-4 3- MH-20-5 4- MH-6-1-8 5- MH-6-1-9 6- MH-6-2-7 7- MH-6-2-8 | 8981.94 | 0.35 | 3143.679
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0756-00 | 2026-07-01 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes, @ Zone-01 1- MH-20-6 | 8981.94 | 0.05 | 449.097
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0774-00 | 2026-07-05 | FIR for Installation of Manhole Base of Storm Network, @ Zone-03 1- MH-4-1 2- MH-4-2 3- MH-4-3 4- MH-4-4 5- MH-6-1-1 6- MH-6-1-2 7- MH-6-1-4 8- MH-6-1-5 9- MH-6-1-6 10- MH-6-2-1 11- MH-6-2-2 12- MH-6-2-3 13- MH-6-2-4 14- MH-6-2-5 15- MH-6-2-6 16- MH-3-5-1 | 8981.94 | 4.8 | 43113.312
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0795 | 2026-07-06 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes, @ Zone-04 1- MH-3-13-3 | 8981.94 | 0.05 | 449.097
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0799 | 2026-07-07 | FIR for Installation of Manhole Base of Storm Network, @ Zone-01 1- MH-20-5 2- MH-20-6 3- MH-28-3 4- MH-28-4 | 8981.94 | 1.2 | 10778.328
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0818 | 2026-07-13 | FIR for Installation of Manhole Base of Storm Network, @ Zone-03 1- MH-3-20 2- MH-3-21 3- MH-3-10-1 | 8981.94 | 0.9 | 8083.746
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0915 | 2026-08-13 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes 1:MH-6-25 | 8981.94 | 0.05 | 449.097
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0970 | 2026-08-23 | FIR for Installation of Manhole Base of Storm Network, @ Zone-04 1:MH-6-25 | 8981.94 | 0.3 | 2694.582
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1033 | 2026-09-08 | Survey FIR for Excavation and Compaction Testing of Storm Manholes, @ Zone-02 1:MH-14-2 2:MH-14-3 | 8981.94 | 0.1 | 898.194
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1039-01 | 2026-10-03 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manhole, @ Zone-02 1:MH-8-4-2 2:MH-8-4-3 | 8981.94 | 0.1 | 898.194
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1049-01 | 2026-10-03 | Fir for Installation of Manhole base for Storm Network, @ Zone-02 1:MH-14-2 2:MH-14-3 | 8981.94 | 0.6 | 5389.164
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1055-01 | 2026-10-03 | Fir for Installation of Storm Pipeline Manhole, @ Zone-02 1:MH-8-4-2 2:MH-8-4-3 | 8981.94 | 0.6 | 5389.164
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1080 | 2026-09-15 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes 1:MH-17-1 2:MH-17-2 3:MH-18-2 4:MH-18-3 | 8981.94 | 0.2 | 1796.388
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1093 | 2026-09-16 | FIR for Installation of base of Manhole Storm network 1:MH-17-1 2:MH-17-2 3:MH-18-2 4:MH-18-3 | 8981.94 | 1.2 | 10778.328
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1268 | 2026-10-17 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manhole MH-8-9 MH-8-10 MH-8-11 MH-8-12 | 8981.94 | 0.2 | 1796.388
B6.33 05 13.01 | Manhole dia 1200mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1275 | 2026-10-18 | FIR for Installation of Storm Pipeline Manhole MH-8-9 MH-8-10 MH-8-11 MH-8-12 | 8981.94 | 1.2 | 10778.328
B6.33 05 13.02 | Manhole dia 1200mm depth 2.5 to 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0689-00 | 2026-06-21 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes, @ Zone-01 1- 1- MH-29-2 | 12732.756 | 0.05 | 636.6378
B6.33 05 13.02 | Manhole dia 1200mm depth 2.5 to 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0699-00 | 2026-06-24 | FIR for Installation of Manhole Base of Storm Network, @ Zone-01 1- MH-29-2 | 12732.756 | 0.3 | 3819.8268
B6.33 05 13.02 | Manhole dia 1200mm depth 2.5 to 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0765-00 | 2026-07-02 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes, @ Zone-01 1- MH-28-2 | 12732.756 | 0.05 | 636.6378
B6.33 05 13.02 | Manhole dia 1200mm depth 2.5 to 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0812-00 | 2026-07-11 | FIR for Installation of Manhole Base of Storm Network, @ Zone-01 1- MH-28-2 | 12732.756 | 0.3 | 3819.8268
B6.33 05 13.02 | Manhole dia 1200mm depth 2.5 to 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1043 | 2026-09-08 | FIR for Installation of Manhole Base of Storm Network, @ Zone-01 1:MH-28-1 2:MH-29-1 | 12732.756 | 0.6 | 7639.6536
B6.33 05 13.02 | Manhole dia 1200mm depth 2.5 to 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1310 | 2026-10-19 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manhole MH-32 | 12732.756 | 0.05 | 636.6378
B6.33 05 13.03 | Manhole dia 1200mm depth 3.5 to 4.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0988 | 2026-08-27 | Survey FIR for Excavation and Compaction Testing of Storm Manhole MH-28-1 | 17572.292 | 0.05 | 878.6146
B6.33 05 13.03 | Manhole dia 1200mm depth 3.5 to 4.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0991 | 2026-08-29 | Survey FIR for Excavation and Compaction Testing of Storm Manhole MH-29-1 | 17572.292 | 0.05 | 878.6146
B6.33 05 13.04 | Manhole dia 1500mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0644-00 | 2026-06-14 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes MH-3-13-1 and MH-3-17-1, @ ZONE-04 | 10853.836 | 0.1 | 1085.3836
B6.33 05 13.04 | Manhole dia 1500mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0654-00 | 2026-06-15 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes MH-3-18 and MH-3-19, @ ZONE-04 | 10853.836 | 0.1 | 1085.3836
B6.33 05 13.04 | Manhole dia 1500mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0700-00 | 2026-06-24 | FIR for Installation of Manhole Base of Storm Network, @ Zone-04 1- MH-3-17-1 | 10853.836 | 0.3 | 3256.1508
B6.33 05 13.04 | Manhole dia 1500mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0730-00 | 2026-06-28 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes, @ Zone-04 1- MH-3-13-2 | 10853.836 | 0.05 | 542.6918
B6.33 05 13.04 | Manhole dia 1500mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0748-00 | 2026-06-30 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes, @ Zone-01 1- MH-20-4 | 10853.836 | 0.05 | 542.6918
B6.33 05 13.04 | Manhole dia 1500mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0801 | 2026-07-07 | FIR for Installation of Manhole Base of Storm Network, @ Zone-01 1- MH-20-4 | 10853.836 | 0.3 | 3256.1508
B6.33 05 13.04 | Manhole dia 1500mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0817 | 2026-07-13 | FIR for Installation of Manhole Base of Storm Network, @ Zone-03 1- MH-3-18 2- MH-3-19 3- MH-3-13-2 | 10853.836 | 0.9 | 9768.4524
B6.33 05 13.04 | Manhole dia 1500mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1037 | 2026-09-08 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manhole, @ Zone-02 1:MH-8-4-1 | 10853.836 | 0.05 | 542.6918
B6.33 05 13.04 | Manhole dia 1500mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1053 | 2026-09-09 | FIR for Installation of Storm Pipeline Manhole, @ Zone-02 1:MH-8-4-1 | 10853.836 | 0.3 | 3256.1508
B6.33 05 13.04 | Manhole dia 1500mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1266 | 2026-10-17 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manhole MH-8-7 MH-8-8 | 10853.836 | 0.1 | 1085.3836
B6.33 05 13.04 | Manhole dia 1500mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1276 | 2026-10-17 | FIR for Installation of Storm Pipeline Manhole MH-8-7 MH-8-8 | 10853.836 | 0.6 | 6512.3016
B6.33 05 13.04 | Manhole dia 1500mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1288 | 2026-10-18 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manhole MH-8-5 MH-8-6 | 10853.836 | 0.1 | 1085.3836
B6.33 05 13.04 | Manhole dia 1500mm depth 1.5 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1297 | 2026-10-19 | FIR for Installation of Storm Pipeline Manhole MH-8-5 MH-8-6 | 10853.836 | 0.6 | 6512.3016
B6.33 05 13.05 | Manhole dia 1500mm depth 2.51 to 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0657-00 | 2026-06-15 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes MH-6-24, @ ZONE-04 | 14483.488 | 0.05 | 724.1744
B6.33 05 13.05 | Manhole dia 1500mm depth 2.51 to 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0781-00 | 2026-07-05 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes, @ Zone-01 1- MH-20-3 | 14483.488 | 0.05 | 724.1744
B6.33 05 13.05 | Manhole dia 1500mm depth 2.51 to 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0800-00 | 2026-07-07 | FIR for Installation of Manhole Base of Storm Network, @ Zone-01 1- MH-20-3 | 14483.488 | 0.3 | 4345.0464
B6.33 05 13.05 | Manhole dia 1500mm depth 2.51 to 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0802-00 | 2026-07-07 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes, @ Zone-01 1- MH-20-2 | 14483.488 | 0.05 | 724.1744
B6.33 05 13.05 | Manhole dia 1500mm depth 2.51 to 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0813-00 | 2026-07-11 | FIR for Installation of Manhole Base of Storm Network, @ Zone-01 1- MH-20-2 | 14483.488 | 0.3 | 4345.0464
B6.33 05 13.05 | Manhole dia 1500mm depth 2.51 to 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0910-00 | 2026-08-13 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes 1:MH-6-22 | 14483.488 | 0.05 | 724.1744
B6.33 05 13.05 | Manhole dia 1500mm depth 2.51 to 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0912-00 | 2026-08-13 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes 1:MH-6-23 | 14483.488 | 0.05 | 724.1744
B6.33 05 13.05 | Manhole dia 1500mm depth 2.51 to 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0969-00 | 2026-08-23 | FIR for Installation of Manhole Base of Storm Network, @ Zone-04 1:MH-6-22 2:MH-6-23 3:MH-6-24 | 14483.488 | 0.9 | 13035.1392
B6.33 05 13.05 | Manhole dia 1500mm depth 2.51 to 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1044 | 2026-09-09 | Survey FIR for Excavation and Compaction Testing of Storm Manhole MH-20-1 | 14483.488 | 0.05 | 724.1744
B6.33 05 13.05 | Manhole dia 1500mm depth 2.51 to 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1059 | 2026-09-10 | Fir for Installation of Manhole base in Storm network @ Zone-1 MH-20-1 | 14483.488 | 0.3 | 4345.0464
B6.33 05 13.05 | Manhole dia 1500mm depth 2.51 to 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1084 | 2026-09-15 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manhole 1:MH-18-1 | 14483.488 | 0.05 | 724.1744
B6.33 05 13.05 | Manhole dia 1500mm depth 2.51 to 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1097 | 2026-10-06 | FIR for Installation of base of Manhole Storm network 1:MH-18-1 | 14483.488 | 0.3 | 4345.0464
B6.33 05 13.06 | Manhole dia 2000mm depth 1.51 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0906-00 | 2026-08-13 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes 1:MH-6-20 | 13283.262 | 0.05 | 664.1631
B6.33 05 13.06 | Manhole dia 2000mm depth 1.51 to 2.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0968-00 | 2026-08-23 | FIR for Installation of Manhole Base of Storm Network 1:MH-6-20 | 13283.262 | 0.3 | 3984.9786
B6.33 05 13.07 | Manhole dia 2000mm depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0578 | 2026-05-20 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes MH-3-6, MH-3-5, MH-3-4, MH-3-3 and MH-3-2 @ ZONE-03 | 17055.15 | 0.25 | 4263.7875
B6.33 05 13.07 | Manhole dia 2000mm depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0588 | 2026-05-21 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes MH-3-1, MH-3-7/0, MH-3-8/0, MH-3-9 and MH-3-10/0 @ ZONE-03 | 17055.15 | 0.25 | 4263.7875
B6.33 05 13.07 | Manhole dia 2000mm depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0595 | 2026-05-24 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes MH-6-2/0, MH-6-3, MH-6-4, MH-6-5, MH-6-6, MH-6-7 and MH-6-8/0 @ ZONE-03 | 17055.15 | 0.35 | 5969.3025
B6.33 05 13.07 | Manhole dia 2000mm depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0643 | 2026-06-14 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes MH-3-12, MH-3-13/0, MH-3-14, MH-3-16 and MH-3-17, @ ZONE-04 | 17055.15 | 0.25 | 4263.7875
B6.33 05 13.07 | Manhole dia 2000mm depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0656 | 2026-06-15 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes MH-3-15, @ ZONE-04 | 17055.15 | 0.05 | 852.7575
B6.33 05 13.07 | Manhole dia 2000mm depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0701 | 2026-06-24 | FIR for Installation of Manhole Base of Storm Network, @ Zone-04 1- MH-3-17/0 | 17055.15 | 0.3 | 5116.545
B6.33 05 13.07 | Manhole dia 2000mm depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0770 | 2026-07-05 | FIR for Installation of Manhole Base of Storm Network, @ Zone-03 & Zone-04 1- MH-3-2 2- MH-3-3 3- MH-3-4 4- MH-3-5 5- MH-3-7 6- MH-3-8 7- MH-3-9 8- MH-3-10/0 9- MH-3-13/0 10- MH-3-15 11- MH-3-16 | 17055.15 | 3.3 | 56281.995
B6.33 05 13.07 | Manhole dia 2000mm depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0771 | 2026-07-05 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes, @ Zone-04 1- MH-3-11 | 17055.15 | 0.05 | 852.7575
B6.33 05 13.07 | Manhole dia 2000mm depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0814 | 2026-07-11 | FIR for Installation of Manhole Base of Storm Network, @ Zone-04 1- MH-3-11 | 17055.15 | 0.3 | 5116.545
B6.33 05 13.07 | Manhole dia 2000mm depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0816 | 2026-07-13 | FIR for Installation of Manhole Base of Storm Network, @ Zone-03 1- MH-3-6 | 17055.15 | 0.3 | 5116.545
B6.33 05 13.07 | Manhole dia 2000mm depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0898 | 2026-08-13 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manhole 1:MH-6-16 | 17055.15 | 0.05 | 852.7575
B6.33 05 13.07 | Manhole dia 2000mm depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0900 | 2026-08-13 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes 1:MH-6-17 | 17055.15 | 0.05 | 852.7575
B6.33 05 13.07 | Manhole dia 2000mm depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0902 | 2026-08-13 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes 1:MH-6-18 | 17055.15 | 0.05 | 852.7575
B6.33 05 13.07 | Manhole dia 2000mm depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0904 | 2026-08-13 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes 1:MH-6-19 | 17055.15 | 0.05 | 852.7575
B6.33 05 13.07 | Manhole dia 2000mm depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0908 | 2026-08-13 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes 1:MH-6-21 | 17055.15 | 0.05 | 852.7575
B6.33 05 13.07 | Manhole dia 2000mm depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-0967 | 2026-08-23 | FIR for Installation of Manhole Base of Storm Network, @ Zone-04 1:MH-6-16 2:MH-6-17 3:MH-6-18 4:MH-6-19 5:MH-6-21 | 17055.15 | 1.5 | 25582.725
B6.33 05 13.07 | Manhole dia 2000mm depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1005 | 2026-08-31 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes, @ Zone-04 1:MH-6-13 2:MH-6-14 3:MH-6-15 | 17055.15 | 0.15 | 2558.2725
B6.33 05 13.07 | Manhole dia 2000mm depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1014 | 2026-09-01 | FIR for Installation of Manhole Base of Storm Network, @ Zone-04 1:MH-6-13 2:MH-6-14 3:MH-6-15 | 17055.15 | 0.9 | 15349.635
B6.33 05 13.07 | Manhole dia 2000mm depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1035 | 2026-09-08 | Survey FIR for Excavation and Compaction Testing of Storm Manhole, @ Zone-02 1:MH-8-4 | 17055.15 | 0.05 | 852.7575
B6.33 05 13.07 | Manhole dia 2000mm depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1051 | 2026-09-09 | FIR for Installation of Storm pipeline Manhole, @ Zone-02 1:MH-8-4 | 17055.15 | 0.3 | 5116.545
B6.33 05 13.07 | Manhole dia 2000mm depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1290 | 2026-10-18 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manhole MH-14 MH-15 | 17055.15 | 0.1 | 1705.515
B6.33 05 13.07 | Manhole dia 2000mm depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1299 | 2026-10-19 | FIR for Installation of Storm Pipeline Manhole MH-14 MH-15 | 17055.15 | 0.6 | 10233.09
B6.33 05 13.07 | Manhole dia 2000mm depth 2.51 - 3.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1302 | 2026-10-19 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manhole MH-24 MH-25 | 17055.15 | 0.1 | 1705.515
B6.33 05 13.08 | Manhole dia 2000mm depth 3.51 - 4.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1078 | 2026-09-15 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manholes 1:MH-17 | 22461.874 | 0.05 | 1123.0937
B6.33 05 13.08 | Manhole dia 2000mm depth 3.51 - 4.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1091 | 2026-09-16 | FIR for Installation of base of Manhole Storm network 1:MH-17 | 22461.874 | 0.3 | 6738.5622
B6.33 05 13.08 | Manhole dia 2000mm depth 3.51 - 4.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1300 | 2026-10-19 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manhole MH-20 MH-21 MH-22 MH-23 | 22461.874 | 0.2 | 4492.3748
B6.33 05 13.08 | Manhole dia 2000mm depth 3.51 - 4.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1312 | 2026-10-19 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manhole MH-26 MH-28 MH-29 MH-30 MH-31 | 22461.874 | 0.25 | 5615.4685
B6.33 05 13.09 | Manhole dia 2000mm depth 4.51 - 5.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1082 | 2026-09-15 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manhole 1:MH-18 | 23628.736 | 0.05 | 1181.4368
B6.33 05 13.09 | Manhole dia 2000mm depth 4.51 - 5.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1095 | 2026-09-16 | FIR for Installation of base of Manhole Storm network 1:MH-18 | 23628.736 | 0.3 | 7088.6208
B6.33 05 13.09 | Manhole dia 2000mm depth 4.51 - 5.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1264 | 2026-10-17 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manhole 1:MH-19 | 23628.736 | 0.05 | 1181.4368
B6.33 05 13.09 | Manhole dia 2000mm depth 4.51 - 5.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1278 | 2026-10-18 | FIR for Installation of Storm Pipeline Manhole 1:MH-19 | 23628.736 | 0.3 | 7088.6208
B6.33 05 13.09 | Manhole dia 2000mm depth 4.51 - 5.5m | DAM2-02-09-SAJ-TS9-1-STR-FIR-1308 | 2026-10-19 | Survey FIR for Excavation and Compaction Testing of Storm Pipeline Manhole MH-27 | 23628.736 | 0.05 | 1181.4368
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0102 | 2026-08-08 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls and Top Slab of the Box Culvert Segment 20. + FIR # 77 bottom slab | 1448.7 | 74.213 | 107512.3731
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0121 | 2026-08-17 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls and Top Slab of the Box Culvert Segment 12. | 1448.7 | 53.668 | 77748.8316
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0122 | 2026-08-17 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls and Top Slab of the Box Culvert Segment 13. | 1448.7 | 58.57 | 84850.359
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0123 | 2026-08-17 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls and Top Slab of the Box Culvert Segment 19. | 1448.7 | 74.213 | 107512.3731
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0131 | 2026-08-23 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls and Top Slab of the Box Culvert Segment 11. | 1448.7 | 58.57 | 84850.359
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0152 | 2026-08-24 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls(including chamber) and Top Slab of the Box Culvert Segment 15. | 1448.7 | 53.604 | 77656.1148
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0153 | 2026-08-24 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls(including chamber) and Top Slab of the Box Culvert Segment 18. | 1448.7 | 45.002 | 65194.3974
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0174 | 2026-08-26 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls (including chamber) and Top Slab of the Box Culvert Segment 21. | 1448.7 | 67.987 | 98492.7669
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0176 | 2026-08-26 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls and Top Slab of the Box Culvert Segment 22. | 1448.7 | 74.213 | 107512.3731
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0190 | 2026-09-02 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls and Top Slab of the Box Culvert Segment 14. | 1448.7 | 58.57 | 84850.359
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0191 | 2026-09-02 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls and Top Slab of the Box Culvert Segment 16. | 1448.7 | 58.57 | 84850.359
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0192 | 2026-09-02 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls and Top Slab of the Box Culvert Segment 17. | 1448.7 | 58.57 | 84850.359
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0205-01 | 2026-09-22 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls (including chamber) and Top Slab of the Box Culvert Segment 23. | 1448.7 | 67.976 | 98476.8312
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0207 | 2026-09-06 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls and Top Slab of the Box Culvert Segment 28,29 & 33. | 1448.7 | 235.14 | 340647.318
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0217 | 2026-09-13 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls and Top Slab of the Box Culvert Segment 25. | 1448.7 | 59.388 | 86035.3956
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0218 | 2026-09-13 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls and Top Slab of the Box Culvert Segment 27. | 1448.7 | 110.759 | 160456.5633
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0223 | 2026-09-14 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls and Top Slab of the Box Culvert Segment 24. | 1448.7 | 74.213 | 107512.3731
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0236 | 2026-09-17 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls (including chamber) and Top Slab of the Box Culvert Segment 26. | 1448.7 | 97.959 | 141913.2033
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0250 | 2026-09-21 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls and Top Slab of the Box Culvert Segment 31. | 1448.7 | 119.769 | 173509.3503
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0252 | 2026-09-24 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls and Top Slab of the Box Culvert Segment 30. | 1448.7 | 78.993 | 114437.1591
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0268 | 2026-09-29 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls and Top Slab of the Box Culvert Segment 32. | 1448.7 | 64.454 | 93374.5098
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0314 | 2026-10-11 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls and Top Slab of the Box Culvert Segment 7 & 8. | 1448.7 | 93.864 | 135980.7768
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0328 | 2026-10-13 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls and Top Slab of the Box Culvert Segment 5. | 1448.7 | 46.932 | 67990.3884
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0330 | 2026-10-13 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls and Top Slab of the Box Culvert Segment 6. | 1448.7 | 43.164 | 62531.6868
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0332 | 2026-10-13 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls and Top Slab of the Box Culvert Segment 9. | 1448.7 | 43.187 | 62565.0069
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0333 | 2026-10-13 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls and Top Slab of the Box Culvert Segment 10. | 1448.7 | 58.57 | 84850.359
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0347 | 2026-10-19 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls and Top Slab of the Box Culvert Segment 4. | 1448.7 | 46.932 | 67990.3884
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0349 | 2026-10-19 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls and Top Slab of the Box Culvert Segment 3. | 1448.7 | 28.182 | 40827.2634
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0351 | 2026-10-19 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls and Top Slab of the Box Culvert Segment 2. | 1448.7 | 27.794 | 40265.1678
B6. 33 42 13.01 | Concrete for box culvert | DAM2-02-09-SAJ-TS9-1-STU-FIR-0353 | 2026-10-19 | Survey Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Walls and Top Slab of the Box Culvert Segment 1. | 1448.7 | 25.054 | 36295.7298
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0101 | 2026-08-08 | Inspection of Steel Reinforcement (including all required embedded items) Prior to Concrete Placement for the Walls and Top slab of Box Culvert Segment 20. + FIR # 76 bottom slab | 4055.482 | 11.543 | 46812.4287
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0118 | 2026-08-17 | Inspection of Steel Reinforcement (including all required embedded items) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 12. | 4055.482 | 9.656 | 39159.7342
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0119 | 2026-08-17 | Inspection of Steel Reinforcement (including all required embedded items) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 13. | 4055.482 | 9.636 | 39078.6246
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0120 | 2026-08-17 | Inspection of Steel Reinforcement (including all required embedded items) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 19. | 4055.482 | 11.543 | 46812.4287
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0125 | 2026-08-19 | Inspection of Steel Reinforcement (including all required embedded items) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 21. | 4055.482 | 11.341 | 45993.2214
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0129 | 2026-08-22 | Inspection of Steel Reinforcement (including all required embedded items) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 11. | 4055.482 | 9.66 | 39175.9561
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0146 | 2026-08-23 | Inspection of Steel Reinforcement (including all required embedded items & chamber) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 15. | 4055.482 | 9.78 | 39662.614
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0147 | 2026-08-23 | Inspection of Steel Reinforcement (including all required embedded items & chamber) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 18. | 4055.482 | 9.85 | 39946.4977
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0175 | 2026-08-26 | Inspection of Steel Reinforcement (including all required embedded items) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 22. | 4055.482 | 11.5 | 46638.043
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0186 | 2026-09-01 | Inspection of Steel Reinforcement (including all required embedded items) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 14. | 4055.482 | 9.69 | 39297.6206
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0187 | 2026-09-01 | Inspection of Steel Reinforcement (including all required embedded items) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 16. | 4055.482 | 9.69 | 39297.6206
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0188 | 2026-09-01 | Inspection of Steel Reinforcement (including all required embedded items) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 17. | 4055.482 | 9.69 | 39297.6206
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0204 | 2026-09-06 | Inspection of Steel Reinforcement (including all required embedded items) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 23. | 4055.482 | 13.952 | 56582.0849
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0206 | 2026-09-06 | Inspection of Steel Reinforcement (including all required embedded items) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 28,29 & 33. | 4055.482 | 42.04 | 170492.4633
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0212 | 2026-09-10 | Inspection of Steel Reinforcement (including all required embedded items) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 24,25 & 26. | 4055.482 | 43.915 | 178096.492
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0216 | 2026-09-12 | Inspection of Steel Reinforcement (including all required embedded items) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 27. | 4055.482 | 19.765 | 80156.6017
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0249 | 2026-09-21 | Inspection of Steel Reinforcement (including all required embedded items) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 31. | 4055.482 | 20.949 | 84958.2924
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0251 | 2026-09-24 | Inspection of Steel Reinforcement (including all required embedded items) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 30. | 4055.482 | 15.278 | 61959.654
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0267 | 2026-09-29 | Inspection of Steel Reinforcement (including all required embedded items) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 32. | 4055.482 | 11.147 | 45206.4579
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0309 | 2026-10-08 | Inspection of Steel Reinforcement (including all required embedded items) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 10. | 4055.482 | 9.572 | 38819.0737
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0313 | 2026-10-11 | Inspection of Steel Reinforcement (including all required embedded items) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 7 & 8. | 4055.482 | 12.17 | 49355.2159
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0327 | 2026-10-13 | Inspection of Steel Reinforcement (including all required embedded items) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 5. | 4055.482 | 6.08 | 24657.3306
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0329 | 2026-10-13 | Inspection of Steel Reinforcement (including all required embedded items) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 6. | 4055.482 | 6.4 | 25955.0848
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0331 | 2026-10-13 | Inspection of Steel Reinforcement (including all required embedded items) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 9. | 4055.482 | 6.53 | 26482.2975
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0346 | 2026-10-19 | Inspection of Steel Reinforcement (including all required embedded items) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 4. | 4055.482 | 6.085 | 24677.608
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0348 | 2026-10-19 | Inspection of Steel Reinforcement (including all required embedded items) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 3. | 4055.482 | 3.983 | 16152.9848
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0350 | 2026-10-19 | Inspection of Steel Reinforcement (including all required embedded items) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 2. | 4055.482 | 4.782 | 19393.3149
B6. 33 42 13.02 | Steel Reinforcement for box culverts as per drawings and the Engineer's instructions | DAM2-02-09-SAJ-TS9-1-STU-FIR-0352 | 2026-10-19 | Inspection of Steel Reinforcement (including all required embedded items) Prior to Concrete Placement for the Walls and Top Slab of Box Culvert Segment 1. | 4055.482 | 4.451 | 18050.9504
B6.33 05 63.01 | Size 3.0 x 3.0 m, depth 1.51-2.5 m | DAM2-02-09-SAJ-TS9-1-STU-FIR-0257 | 2026-09-26 | Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Bottom Slab of the Concrete Chambers for (MH 2) in the Box Culvert Segment 30. | 19810.314 | 0.2 | 3962.0628
B6.33 05 63.02 | Size 3.0 x 1.5 m, depth 1.51-2.5 m | DAM2-02-09-SAJ-TS9-1-STU-FIR-0258 | 2026-09-26 | Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Bottom Slab of the Concrete Chambers for (MH 1) in the Box Culvert Segment 32. | 13544.906 | 0.2 | 2708.9812
B6.33 05 63.03 | Size 2.5 x 1.5 m, depth 1.51-2.5 m | DAM2-02-09-SAJ-TS9-1-STU-FIR-0256 | 2026-09-26 | Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Bottom Slab of the Concrete Chambers for (MH 3) in the Box Culvert Segment 26. | 12053.184 | 0.2 | 2410.6368
B6.33 05 63.04 | Size 2.0 x 1.5 m, depth 2.51-3.5 m | DAM2-02-09-SAJ-TS9-1-STU-FIR-0255 | 2026-09-26 | Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Bottom Slab of the Concrete Chambers for (MH 4,5,6) in the Box Culvert Segment 18,21 & 23. | 17995.488 | 0.6 | 10797.2928
B6.33 05 63.05 | Size 1.5 x 1.5 m, depth 2.51-3.5 m | DAM2-02-09-SAJ-TS9-1-STU-FIR-0254 | 2026-09-26 | Inspection of Formwork and Placement of Reinforced Concrete (C35 MPa) for the Bottom Slab of the Concrete Chambers for (MH 7,8,9) in the Box Culvert Segment 9,12 & 15. | 15717.956 | 0.6 | 9430.7736
B6.33 05 63.06 | Size 1.5 x 1.5 m, depth 3.51-4.5 m | DAM2-02-09-SAJ-TS9-1-STU-FIR-0259 | 2026-09-26 | Survey Inspection for Excavation of the Concrete Chamber for (MH 10) in the Box Culvert Segment 6. | 20151.856 | 0.05 | 1007.5928
B6.33 05 63.06 | Size 1.5 x 1.5 m, depth 3.51-4.5 m | DAM2-02-09-SAJ-TS9-1-STU-FIR-0335 | 2026-10-13 | Survey Inspection for Excavation of the Concrete Chamber for (MH 11 & 12) in the Box Culvert Segment 1 & 2. | 20151.856 | 0.1 | 2015.1856
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0550 | 2026-05-18 | Survey Excavation and Compaction Test FIR for Single Catch Basins of Storm Pipe Line, @ ZONE-01 1- MH-28/0 (CB-9) 2- MH-28-1 (CB-14 (4), CB-14) 3- MH-28-2 (CB-16) 4- MH-28-3 (CB-24, CB-34 and CB-28) 5- MH-28-4 (CB-43) 6- MH-20-6 (CB-67) 7- MH-20-5 (CB-58, CB-62 and CB-75) 8- MH-20-4 (CB-71) 9- MH-20-3 (CB-70 and CB-52) 10- MH-20-2 (CB-59) 11- MH-20-1 (CB-82 and CB-93) | 4519.944 | 2.7 | 12203.8488
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0601 | 2026-06-02 | FIR for Installation of Catch Basins Manhole for Storm Network @ Zone-01 1- CB-14 2- CB-59 3- CB-9 4- CB-75 5- CB-67 6- CB-70 7- CB-71 8- CB-16 9- CB-82 10- CB-93 11- CB-62 12- CB-34 13- CB-14(4) | 4519.944 | 6.5 | 29379.636
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0640 | 2026-06-13 | Survey FIR for Excavation and Compaction Testing of Single Catch Basin Manholes of Storm Network, @Zone-03 and Arterial Road 1- MH-4-4 (CB-199 and CB-220) 2- MH-1-5 (CB-145 and CB-326) 3- MH-1-4 (CB-202 and CB-208) 4- MH-1-3 (CB-348) 5- MH-1-2 (CB-286 and CB-301) 6- MH-1-1 (CB-292) | 4519.944 | 1.5 | 6779.916
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0649 | 2026-06-14 | Survey FIR for Excavation and Compaction Testing of Single Catch Basin Manholes of Storm Network, @Zone-04 1- MH-6-15 (CB-149 and CB-173) 2- MH-6-19 (CB-116 and CB-96) 3- MH-6-16 (CB-113 and CB-105) 4- MH-6-18/0 (CB-85 and CB-98) 5- MH-6-17 (CB-117) 6- MH-6-14 (CB-158) 7- MH-6-20 (CB-91 and CB-109) 8- MH-6-13 (CB-144) 9- MH-6-21/0 (CB-33 and CB-63) 10- MH-6-22 (CB-29) | 4519.944 | 2.4 | 10847.8656
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0653 | 2026-06-15 | Survey FIR for Excavation and Compaction Testing of Single Catch Basin Manholes of Storm Network, @Zone-04 1- MH-6-25 (CB-30) 2- MH-6-24 (CB-27 and CB-23) 3- MH-6-22 (CB-25) | 4519.944 | 0.6 | 2711.9664
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0666 | 2026-06-16 | Survey FIR for Excavation and Compaction Testing of Single Catch Basin Manholes of Storm Network, @Zone-03 1- MH-3-8-1 (CB-276, CB-303 and CB-296) 2- MH-3-7-1 (CB-281 and CB-314) 3- MH-3-6-2 (CB-175 | 4519.944 | 0.9 | 4067.9496
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0669 | 2026-06-17 | Survey FIR for Excavation and Compaction Testing of Single Catch Basin Manholes of Storm Network, @ Arterial Road 1- MH-1-1 (CB-283) 2- MH-3-6-2 (CB-329 and CB-339) | 4519.944 | 0.45 | 2033.9748
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0679 | 2026-06-18 | Survey FIR for Excavation and Compaction Testing of Single Catch Basin Manholes of Storm Network, @Zone-03 and Arterial Road 1- MH-3-5-1 (CB-331 and CB-268) 2- MH-1-6 (CB-151) | 4519.944 | 0.45 | 2033.9748
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0686 | 2026-06-21 | Survey FIR for Excavation and Compaction Testing of Single Catch Basin Manholes of Storm Network, @ Zone-03 1- CB-180 (MH-3-5-1) 2- CB-184, CB-185 and CB-224 (MH-6-11/0) 3- CB-230 (MH-6-9-1-3) 4- CB-231 and CB-248 (MH-6-10) 5- CB-278 (MH-6-9-1) | 4519.944 | 1.2 | 5423.9328
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0716 | 2026-06-27 | Survey FIR for Excavation and Compaction Testing of Single Catch Basin Manholes of Storm Network, @ Zone-01, Zone-04 and Arterial Road 1- CB-111 (MH-3-17-1) 2- CB-77, CB-92 and CB-97 (MH-3-17-2) 3- CB-45, CB-48 and CB-57 (MH-3-17-3) 4- CB-47 and CB-44 (MH-6-21-1) 5- CB-146 (MH-3-13-1) 6- CB-94 and CB-118 (MH-3-13-2) 7- CB-56 and CB-79 (MH-3-13-3) 8- CB-360 (MH-1-3) 9- CB-2 and CB-5 (MH-29-2) 10- CB-4 and CB-6 (MH-29-4) | 4519.944 | 2.85 | 12881.8404
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0719 | 2026-06-28 | FIR for Installation of Catch Basins Manhole for Storm Network @ Zone-03, Zone-04 and Arterial Road 1- CB-292 (MH-1-1) 2- CB-286 and CB-301 (MH-1-2) 3- CB-348 and CB-360 (MH-1-3) 4- CB-202 and CB-208 (MH-1-4) 5- CB-145 and CB-326 (MH-1-5) 6- CB-151 (MH-1-6) 7- CB-268 (MH-3-5-1) 8- CB-175 and CB-339 (MH-3-6-2) 9- CB-281 (MH-3-7-1) 10- CB-276 (MH-3-8-1) 11- CB-25 and CB-29 (MH-6-22) 12- CB-63 (MH-6-21/0) 13- CB-91 and CB-109 (MH-6-20) 14- CB-96 and CB-116 (MH-6-19) 15- CB-98 (MH-6-18/0) 16- CB-117 (MH-6-17) 17- CB-113 (MH-6-16) 18- CB-149 and CB-173 (MH-6-15) | 4519.944 | 13.5 | 61019.244
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0724 | 2026-06-28 | Survey FIR for Excavation and Compaction Testing of Single Catch Basin Manholes of Storm Network, @ Zone-03 1- CB-211 (MH-3-5) 2- CB-235, CB-346, CB-352 and CB-362 (MH-4-3) 3- CB-349 (MH-4-2) 4- CB-345 (MH-4-1) | 4519.944 | 1.05 | 4745.9412
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0736 | 2026-06-29 | Survey FIR for Excavation and Compaction Testing of Single Catch Basin Manholes of Storm Network, @ Zone-04 and Arterial Road 1- CB-31 (MH-6-25) 2- CB-279 and CB-255 (MH-1-6) | 4519.944 | 0.45 | 2033.9748
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0742 | 2026-06-30 | Survey FIR for Excavation and Compaction Testing of Single Catch Basin Manholes of Storm Network, @ Zone-03 and Zone-04 1- CB-177 (MH-3-10-1) 2- CB-341 and CB-335 (MH-3-4) 3- CB-42 (MH-3-20) 4- CB-35 (MH-3-21) | 4519.944 | 0.75 | 3389.958
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0753 | 2026-07-01 | Survey FIR for Excavation and Compaction Testing of Single Catch Basin Manholes of Storm Network, @ Zone-03 1- CB-333, CB-217 and CB-241 (MH-6-3) 2- CB-368 (MH-05) 3- CB-228 and CB-219 (MH-6-1-9) 4- CB-223 and CB-234 (MH-6-2-8) | 4519.944 | 1.2 | 5423.9328
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0759 | 2026-07-05 | Survey FIR for Excavation and Compaction Testing of Single Catch Basin Manholes of Storm Network, @ Zone-03 1- CB-243 and CB-252 (MH-6-1-8) 2- CB-240 (MH-6-1-7) 3- CB-288 (MH-6-1-5) 4- CB-319 (MH-6-1-3) 5- CB-227 (MH-6-2-6) 6- CB-269 (MH-6-2-4) 7- CB-148 (MH-6-2-2) 8- CB-238, CB-342 and CB-334 (MH-6-1) 9- CB-274 (MH-6-1-1) | 4519.944 | 1.8 | 8135.8992
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0775 | 2026-07-05 | Survey FIR for Excavation and Compaction Testing of Single Catch Basin Manholes of Storm Network, @ Zone-02 and Zone-04 1- CB-226 (MH-8-8) 2- CB-212 (MH-8-9) 3- CB-287 (MH-6-8-3) 4- CB-229 and CB-229-1 (MH-6-8-4) 5- CB-69 and CB-86 (MH-6-18-1) 6- CB-341-1 (MH-3-4) 7- CB-213 (MH-8-12) 8- CB-178 and CB-194 (MH-8-14) 9- CB-261 (MH-6-9-2) 10- CB-133 and CB-282 (MH-6-9/0) 11- CB-32 (MH-3-21) 12- CB-320 and CB-154 (MH-6-8/0) 13- CB-50 and CB-54 (MH-3-19) | 4519.944 | 2.85 | 12881.8404
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0784 | 2026-07-05 | FIR for Installation of Single Catch Basin Manhole of Storm Network, @ Zone-03 and Zone-04 1- CB-23 and CB-27 (MH-6-24) 2- CB-30 (MH-6-25) 3- CB-44 (MH-6-21-1) 4- CB-45, CB-48 and CB-57 (MH-3-17-3) 5- CB-77, CB-92 and CB-97 (MH-3-17-2) 6- CB-111 (MH-3-17-1) 7- CB-56 and CB-79 (MH-3-13-3) 8- CB-94 and CB-118 (MH-3-13-2) 9- CB-146 (MH-3-13-1) 10- CB-177 (MH-3-10-1) 11- CB-296 and CB-303 (MH-3-8-1) 12- CB-314 (MH-3-7-1) 13- CB-329 (MH-3-6-2) 14- CB-331 (MH-3-5-1) 15- CB-341 (MH-3-4) 16- CB-255 and CB-279 (MH-1-6) | 4519.944 | 10 | 45199.44
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0789 | 2026-07-06 | Survey FIR for Excavation and Compaction Testing of Single Catch Basin Manholes of Storm Network, @ Zone-02, Zone-03 and Zone-04 1- CB-336 (MH-6-3) 2- CB-340 (MH-6-1) 3- CB-242 (MH-6-2-7) 4- CB-183 and CB-147 (MH-8-11) 5- CB-222 (MH-8-10) 6- CB-125 and CB-165 (MH-8-13) 7- CB-126 and CB-152 (MH-8-15) 8- CB-258 and CB-284 (MH-6-10) 9- CB-210 (MH-3-9) 10- CB-156 and CB-168 (MH-8-13) 11- CB-197 and CB-200 (MH-3-10/0) 12- CB-313, CB-306 and CB-310 (MH-6-8-2) 13- CB-203 (MH-8-12) 14- CB-30-1 (MH-6-24) 15- CB-221 (MH-6-9-3) 16- CB-88, CB_65 and CB-100 (MH-3-18) | 4519.944 | 3.9 | 17627.7816
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0819 | 2026-07-14 | FIR for Installation of Single Catch Basin Manhole of Storm Network, @ Zone-03 and Zone-04 1- CB-88 and CB-100 (MH-3-18) 2- CB-50 and CB-54 (MH-3-19) 3- CB-42 (MH-3-20) 4- CB-32 (MH-3-21) 5- CB-30-1 (MH-6-24) 6- CB-69 and CB-86 (MH-6-18-1) 7- CB-341-1 (MH-3-4) 8- CB-334 and CB-342 (MH-6-1) 9- CB-274 (MH-6-1-1) 10- CB-319 (MH-6-1-3) 11- CB-288 (MH-6-1-5) 12- CB-240 (MH-6-1-7) 13- CB-243 (MH-6-1-8) 14- CB-219 (MH-6-1-9) 15- CB-223 and CB-234 (MH-6-2-8) 16- CB-242 (MH-6-2-7) 17- CB-269 (MH-6-2-4) | 4519.944 | 11 | 49719.384
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0820 | 2026-07-14 | Survey FIR for Excavation and Compaction Testing of Single Catch Basin Manholes of Storm Network, @ Zone-04 1- CB-153 (MH-3-10-1) 2- CB-134 (MH-3-17/0) 3- CB-65 (MH-3-19) | 4519.944 | 0.45 | 2033.9748
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-1024 | 2026-09-03 | Survey FIR for Excavation and Compaction Testing for Catch Basins of Storm Network, @ Zone-04 CB-127 (MH-3-15) CB-122 (MH-3-17) | 4519.944 | 0.3 | 1355.9832
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-1025 | 2026-09-06 | Survey FIR for Excavation and Compaction Testing for Catch Basins of Storm Network, @ Zone-04 CB-33 (MH-6-21) CB-105 (MH-6-16) CB-128 (MH-3-15) | 4519.944 | 0.45 | 2033.9748
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-1041 | 2026-09-08 | FIR for Installation of Catch basin Manhole of Storm Network, @ Zone-01 1:CB-52 7:CB-24 2:CB-43 8:CB-28 3:CB-58 9:CB-4 4:CB-2 5:CB-5 6:CB-6 | 4519.944 | 4.5 | 20339.748
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-1046 | 2026-09-09 | FIR for Installation of Catch Basins of Storm Network, @ Zone-04 CB-127 CB-122 | 4519.944 | 1 | 4519.944
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-1047 | 2026-09-09 | Fir for Installation of Catch Basins of Storm Network, @ Zone-04 CB-33 CB-105 CB-128 | 4519.944 | 1.5 | 6779.916
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-1109-01 | 2026-10-03 | FIR for installation of Single Catch Basin of Storm Network, @ Zone-03 1: CB-349 2: CB-362 | 4519.944 | 1 | 4519.944
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-1110 | 2026-09-21 | Survey FIR for Excavation and compaction testing for Catch Basin of Storm Network, @ Zone-03 1: CB-253 (MH-6-2) | 4519.944 | 0.15 | 677.9916
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-1115-01 | 2026-10-03 | FIR for Installation Catch Basin of Storm Network, @ Zone-03 1: CB-253 (MH-6-2) | 4519.944 | 0.5 | 2259.972
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-1134 | 2026-09-26 | Survey and Compaction Testing FIR for Around-Backfill 4th Layer for the Listed Catch Basins of the Storm Network, @ Zone-01. CB-2,CB-6,CB-9,CB-16,CB-67,CB-70,CB-71,CB-75 | 4519.944 | 0.4 | 1807.9776
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-1143 | 2026-09-27 | Survey and Compaction Testing FIR for Around-Backfill 5th Layer for the Listed Catch Basins of the Storm Network, @ Zone-01. CB-62,CB-59,CB-43,CB-34,CB-14,CB-14(4),CB-5 | 4519.944 | 0.35 | 1581.9804
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-1147 | 2026-09-27 | Survey and Compaction Testing FIR for Around-Backfill 6th Layer for Catch Basins of the Storm Network, @ Zone-01. CB-52 | 4519.944 | 0.05 | 225.9972
B6.33 05 63.07 | Single Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-1156 | 2026-09-28 | Survey and Compaction Testing FIR for Around-Backfill 7th Layer for the Listed Catch Basins of the Storm Network, @ Zone-01. CB-24 , CB-28 | 4519.944 | 0.1 | 451.9944
B6.33 05 63.08 | Double Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0551 | 2026-05-18 | Survey Excavation and Compaction Test FIR for Double Catch Basins of Storm Pipe Line, @ ZONE-01 1- MH-20-6 (CB-81 (1)) 2- MH-20-4 (CB-83) 3- MH-20-1 (CB-102) | 8808.096 | 0.45 | 3963.6432
B6.33 05 63.08 | Double Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0725 | 2026-06-28 | Survey FIR for Excavation and Compaction Testing of Double Catch Basin Manholes of Storm Network, @ Zone-01 and Zone-03 1- CB-357 and CB-265 (MH-6-2) 2- CB-256 (MH-4-3) 3- CB-358 (MH-4-2) 4- CB-244 and CB-361 (MH-4-1) 5- CB-365 (2) (MH-3-1) 6- CB-3 (MH-29-2) | 8808.096 | 1.2 | 10569.7152
B6.33 05 63.08 | Double Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0762 | 2026-07-02 | Survey FIR for Excavation and Compaction Testing of Double Catch Basin Manholes of Storm Network, @ Zone-03 1- CB-270 (MH-6-1-8) 2- CB-347 (MH-6-1) | 8808.096 | 0.3 | 2642.4288
B6.33 05 63.08 | Double Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0778 | 2026-07-05 | Survey FIR for Excavation and Compaction Testing of Double Catch Basin Manholes of Storm Network, @ Zone-04 1- 1- CB-37 (MH-6-25) | 8808.096 | 0.15 | 1321.2144
B6.33 05 63.08 | Double Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0792 | 2026-07-06 | Survey FIR for Excavation and Compaction Testing of Double Catch Basin Manholes of Storm Network, @ Zone-03 1- CB-166 (MH-6-5) | 8808.096 | 0.15 | 1321.2144
B6.33 05 63.08 | Double Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-0823-01 | 2026-09-08 | Survey FIR for Excavation and Compaction Testing of Double Catch Basin Manholes of Storm Network, @ Zone-03 1- CB-293 (MH-6-9-2) | 8808.096 | 0.15 | 1321.2144
B6.33 05 63.08 | Double Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-1042 | 2026-09-08 | FIR for Installation of Double Catch basin of Storm Network, @ Zone-01 1:CB-102 4:CB-83 2:CB-81(1) 3:CB-3 | 8808.096 | 0.6 | 5284.8576
B6.33 05 63.08 | Double Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-1108 | 2026-09-21 | FIR for installation of Double Catch Basin of Storm Network, @ Zone-03 1: CB-244 2: CB-256 3: CB-265 4: CB-357 5: CB-361 | 8808.096 | 2.5 | 22020.24
B6.33 05 63.08 | Double Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-1122 | 2026-09-26 | Survey FIR for Excavation and Compaction Testing for Double catch basins of Storm pipeline 1. MHA-20 (CB-60) 2. MHA-25 (CB-189) 3. MHA-30 (CB-21) ZONE-01 | 8808.096 | 0.45 | 3963.6432
B6.33 05 63.08 | Double Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-1141 | 2026-09-27 | Survey and Compaction Testing FIR for Around-Backfill 6th Layer for the Listed Catch Basins of the Storm Network, @ Zone-01. CB-3, CB-81(1), CB-102 | 8808.096 | 0.15 | 1321.2144
B6.33 05 63.08 | Double Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-1142 | 2026-09-27 | Survey and Compaction Testing FIR for Around-Backfill 5th Layer for Catch Basins of the Storm Network, @ Zone-01. CB-83 | 8808.096 | 0.05 | 440.4048
B6.33 05 63.08 | Double Catch basin | DAM2-02-09-SAJ-TS9-1-STR-FIR-1149 | 2026-09-27 | Survey FIR Installation of Double catch basins of Storm pipeline 1. MHA-20 (CB-60) 2. MHA-25 (CB-189) 3. MHA-30 (CB-21) ZONE-01 | 8808.096 | 1.5 | 13212.144
B8.31 23 16.01 | Excavation of guard room type 1 & 2 | DAM2-02-09-SAJ-TS9-1-STU-FIR-0003 | 2026-05-04 | Inspection for survey works of excavation for bottom of replacement soil of the Guard House. | 43.9 | 19.25 | 845.075
B8.32 11 23.01 | Aggregate base course below slab on grade for Guard room Type 1 & 2 | DAM2-02-09-SAJ-TS9-1-STU-FIR-0295 | 2026-10-05 | Inspection for survey works and compaction testing of Aggregate Base Course (20 cm) under the Slab on Grade in the Guard House. | 86.922 | 6.98 | 606.7156
B8.03 30 00.01 | 50 mm thickness lean concrete under slab on grade for Guard room Type 1 & 2 | DAM2-02-09-SAJ-TS9-1-STU-FIR-0244 | 2026-09-20 | Inspection for 50 mm plain concrete below the grade beams (G.B.1, G.B.2 & G.B.3) of the Guard house and Guard rooms. | 438.122 | 1.1 | 481.9342
B8.03 30 00.02 | 100 mm thickness lean concrete under the foundation for Guard room Type 1 & 2 | DAM2-02-09-SAJ-TS9-1-STU-FIR-0044 | 2026-06-23 | Inspection of 100 mm thickness lean concrete under the foundation of Guard House. | 438.122 | 1.6 | 700.9952
B8.03 30 00.02 | 100 mm thickness lean concrete under the foundation for Guard room Type 1 & 2 | DAM2-02-09-SAJ-TS9-1-STU-FIR-0051 | 2026-06-28 | Inspection of 100 mm thickness lean concrete under the foundation of Guard Rooms 1,2 & 3. | 438.122 | 1.73 | 757.9511
B8.03 30 00.01 | Footings for guard room type 1 & 2 | DAM2-02-09-SAJ-TS9-1-STU-FIR-0088 | 2026-07-28 | Survey Inspection of the Placement of Reinforced Concrete (C35 MPa) for the Footings of Guard House as per the attached highlighted approved drawings. | 1101.012 | 4.74 | 5218.7969
B8.03 30 00.01 | Footings for guard room type 1 & 2 | DAM2-02-09-SAJ-TS9-1-STU-FIR-0089 | 2026-07-28 | Survey Inspection of the Placement of Reinforced Concrete (C35 MPa) for the Footings of Guard Rooms 1,2 and 3 as per the attached highlighted approved drawings | 1101.012 | 4.8 | 5284.8576
B8.03 30 00.02 | Reinforced Concrete columns for guard room type 1 & 2 | DAM2-02-09-SAJ-TS9-1-STU-FIR-0093 | 2026-07-28 | Survey Inspection of the Placement of Reinforced Concrete (C35 MPa) and Formwork for the Columns (up to 9.90 Level) of Guard House. | 1448.7 | 0.75 | 1086.525
B8.03 30 00.02 | Reinforced Concrete columns for guard room type 1 & 2 | DAM2-02-09-SAJ-TS9-1-STU-FIR-0095 | 2026-07-28 | Survey Inspection of the Placement of Reinforced Concrete (C35 MPa) and Formwork for the Columns (up to Attached survey levels) of Guard Room 1,2 and 3. | 1448.7 | 1.31 | 1897.797
B8.03 30 00.04 | Slab on grade for guard room type 1 & 2 | DAM2-02-09-SAJ-TS9-1-STU-FIR-0263 | 2026-09-28 | Survey Inspection of the Formwork and Placement of Reinforced Concrete (C35 MPa) for the Grade Beams (G.B.1, G.B.2 & G.B.3) of the Guard House and Guard Rooms (1,2,3). | 788.444 | 6.95 | 5479.6858
B8.07 13 13.01 | Water proofing Membrane with 50mm screed protection fc' 20MPa for guard room type 1 & 2 | DAM2-02-09-SAJ-TS9-1-STU-FIR-0057 | 2026-07-05 | Inspection of the Waterproofing Membrane (4mm thick) with 50 mm Screed Protection (20 MPa) over the lean concrete at the Guard House. | 128.188 | 16 | 2051.008
B8.07 13 13.01 | Water proofing Membrane with 50mm screed protection fc' 20MPa for guard room type 1 & 2 | DAM2-02-09-SAJ-TS9-1-STU-FIR-0058 | 2026-07-05 | Inspection of the Waterproofing Membrane (4mm thick) with 50 mm Screed Protection (20 MPa) over the lean concrete at the Guard Rooms 1,2&3. | 128.188 | 17.28 | 2215.0886
B8.07 13 13.02 | Water proofing Membrane with protection board for guard room type 1 & 2 | DAM2-02-09-SAJ-TS9-1-STU-FIR-0108 | 2026-08-11 | Inspection of the Waterproofing Membrane (4mm thick) with Protection board over the RC Concrete Footing and Columns of Guard Rooms as per attached Approved Drawing. | 80.776 | 49.48 | 3996.7965
B8.07 13 13.02 | Water proofing Membrane with protection board for guard room type 1 & 2 | DAM2-02-09-SAJ-TS9-1-STU-FIR-0109 | 2026-08-11 | Inspection of the Waterproofing Membrane (4mm thick) with Protection board over the RC Concrete Footing and Columns of Guard House up to 9.80m Level as per Attached Approved Drawing. | 80.776 | 37.6 | 3037.1776
B8. 22 13 16 .02 | uPVC pipes with diameter 110mm. | DAM2-02-09-SAJ-TS9-1-MECH-FIR-0009 | 2026-09-29 | Mechanical FIR for installation of UPVC Ground Floor Drainage Pipe(diameter 110mm) for Guard House. | 115.018 | 6.85 | 787.8733
B8. 22 13 16 .03 | uPVC pipes with diameter 75mm. | DAM2-02-09-SAJ-TS9-1-MECH-FIR-0008 | 2026-09-29 | Mechanical FIR for installation of UPVC Ground Floor Drainage Pipe(diameter 75mm) for Guard House. | 111.506 | 1.6 | 178.4096
B8. 22 13 16 .04 | uPVC pipes with diameter 50mm. | DAM2-02-09-SAJ-TS9-1-MECH-FIR-0011 | 2026-10-14 | Mechanical FIR for installation of UPVC Ground Floor Drainage Pipe (diameter 50mm) for Guard House. | 107.994 | 4.25 | 458.9745
B8. 22 13 16 .01 | PPR pipes with diameter 32mm. | DAM2-02-09-SAJ-TS9-1-MECH-FIR-0010 | 2026-09-29 | Mechanical FIR for installation of PPR Potable Water Pipe for Guard House. | 27.218 | 1.5 | 40.827
Total Period Amount | [5 empty] | 84260706.8929

## Quality
QC OBSERVATIONS CHECKLIST
2025-11-25
Project No. |  |  | DAM2-02-009 |  |  | OBS No. |  |  |  | 46 |  |  | Inspection Day: | 2026-10-20
Project |  |  | Development of Infrastructure for phase 1 of the Logistics area at the 2nd Industrial City in Dammam | [6 empty] | Contractor: Consultant: |  |  | Shibh Aljazira Contracting Company Egis
4 |  | Excellent |  | Quality Management System is being practiced and applies to MODON System | [10 empty] | 90 - 100 |  | QC Overall Score | 93% |  |  |  |  | 0% | 100 | 0.22883
3 |  | Good |  | Evidence of compliance with plans and procedures. | [10 empty] | 80 - 89 | [7 empty] | 0 | 89 | 0.20366
2 |  | Average |  | Indication level of compliance with standards but there is room for improvement | [10 empty] | 70 - 79 | [8 empty] | 79 | 0.18078
1 |  | Improve |  | Quality and Control is NOT being managed effectively. Needs Improvement | [10 empty] | ≤ 69 | [8 empty] | 69 | 0.15789
0 |  | N/A |  | Item was not applicable or this item was not reviewed during the inspection. | [10 empty] | Zero | [8 empty] | 100 | 0.22883
No. | Topic |  |  |  |  | E (4) | G (3) | A (2) | I (1) | N/A (0) | No. | Topic |  |  | E (4) | G (3) | A (2) | I (1) | N/A (0) |  |  |  |  | 437
[6 empty] | 100% | 89% | 79% | 69% | 100% |  |  |  |  | 100% | 89% | 79% | 69% | 100% | 91.81%
1 | Control of Access to Site/Office | [5 empty] | 1 |  |  |  | 30 | QC of Excavation |  |  | 0 | 0 | 1 |  |  | 0.89 | 0.79 | [6 empty] | Item Count | Score | Distributtion
2 | Document Control Administration | [5 empty] | 1 | 0 |  |  | 31 | QC of Roads/Round about |  |  | 0 | 0 | 1 | 0 | 0 | 0.89 | 0.79 | [8 empty] | Overall | Relevant
3 | Project Documents and Progress | [5 empty] | 1 | 0 |  |  | 32 | QC of Interlock & Curbstone |  |  | 0 |  | 1 |  | 0 | 0.89 | 0.79 | 4 | 58 | counts |  | 4 | Excellent | 4 | 16 | 6.897% | 10%
4 | Contractor's Quality Plan/CM (Updated and Reviewed) | [5 empty] | 1 | 0 |  |  | 33 | Layers/Backfilling Sampling |  |  | 0 | 1 | 0 | 0 | 0 | 0.89 | 0.89 | 3 | 58 | counts |  | 3 | Good | 20 | 60 | 34.48% | 50%
5 | MS Log and Paperwork | [5 empty] | 1 | 0 |  |  | 34 | Pump Stations Units |  |  | 0 |  |  |  | 1 | 0.89 | 1 | 2 | 58 | counts |  | 2 | Average | 12 | 24 | 20.69% | 30% |  | NB: Insert 1, or 0 in the required cell only.
6 | RFI, FIR, & MIR Procedure | [5 empty] | 0 | 1 |  |  | 35 | Quality of Form Work |  |  | 0 | 0 | 0 | 1 | 0 | 0.79 | 0.69 | 1 | 58 | counts |  | 1 | Improve | 4 | 4 | 6.897% | 10%
7 | RFI, FIR, & MIR Inventory system | [5 empty] | 1 | 0 |  |  | 36 | Design Change List | [5 empty] | 0 | 1 | 0.89 | 1 | 0 | 58 | counts |  | 0 | N/A | 18 | 0 | 31.03% | -
8 | NCRs Control & Procedure | [5 empty] | 1 | 0 |  | 0 | 37 | Quality of Concrete Placing |  |  |  | 0 | 0 | 1 | 0 | 0.89 | 0.69 | [5 empty] | Total | 58 | 104 | 100% | 100%
9 | NCR Log |  |  |  |  | 0 | 1 |  |  |  | 38 | Concrete Surface Finishing |  |  | 0 | 0 | 1 |  | 0 | 0.89 | 0.79
10 | MODON Standard* |  |  |  |  | 0 | 1 |  |  |  | 39 | Pedestals/Columns/Beams Alignment |  |  | 0 |  |  |  | 1 | 0.89 | 1 | [6 empty] | Maz Score Available: | 160 | <- Excludes N/A items
11 | Project Risk Plan/Management* |  |  |  |  | 0 | 1 |  |  |  | 40 | Siporex Lifting & Unloading |  |  |  |  | 0 |  | 1 | 0.89 | 1
12 | Monthly Quality Reports* |  |  |  |  | 0 | 1 | 0 |  |  | 41 | Siporex Quality Pre-installation |  |  |  |  | 0 |  | 1 | 0.89 | 1
13 | ITP |  |  |  |  | 0 | 1 | 0 |  | 0 | 42 | Siporex Finishing Quality |  |  | 0 |  |  |  | 1 | 0.89 | 1 | [5 empty] | Total Score |  | Percentage (%)
14 | MODON Weekly Report |  |  |  |  | 1 | 0 | 0 |  |  | 43 | Roads / Parking Markings |  |  | 0 | 0 |  | 1 | 0 | 1 | 0.69 |  | 58 |  |  |  | 104 |  | 65 |  | %
15 | Design Change Official Paperwork* |  |  |  |  | 0 |  | 0 |  | 1 | 44 | QC of Finishing Outdoors |  |  | 0 | 0 |  |  | 1 | 1 | 1 | [5 empty] | Max Score Available | [6 empty] | 31
16 | Design Change was Applied* |  |  |  |  | 0 |  | 0 |  | 1 | 45 | Quality of Finishing Indoors |  |  | 0 |  |  |  | 1 | 1 | 1 | [5 empty] | 160 | [6 empty] | 32
17 | Material List |  |  |  |  | 0 |  | 1 |  |  | 46 | Stairs Quality |  |  | 0 |  |  |  | 1 | 0.79 | 1 | [12 empty] | 33
18 | Pending Material Status |  |  |  |  | 0 | 1 |  |  | 0 | 47 | Tanks Method Statement Work |  |  | 0 |  |  |  | 1 | 0.89 | 1 | [12 empty] | 34
19 | Lifting Plan* | [8 empty] | 1 | 48 | Electric Rooms |  |  | 0 |  |  |  | 1 | 1 | 1 | [12 empty] | 35
20 | DWG Log | [5 empty] | 1 | 0 |  | 0 | 49 | QC of MCC/ATS Plant Units |  |  | 0 |  |  |  | 1 | 0.89 | 1 | [12 empty] | 36
21 | Invoice Status |  |  |  |  | 1 | 0 |  |  | 0 | 50 | Qualified Subcontractor |  |  | 0 |  |  |  | 1 | 1 | 1 | [12 empty] | 37
22 | Site Handover Letter |  |  |  |  | 1 | 0 |  |  |  | 51 | Scaffold/Ladders/Slope/Bridge Compliance |  |  | 0 |  |  |  | 1 | 1 | 1 | [12 empty] | 38
23 | Material Testing Results & Certification |  |  |  |  | 0 | 0 | 0 | 1 | 0 | 52 | Protection Applied to Completed Work |  |  |  | 1 |  | 0 | 0 | 0.69 | 0.89
24 | As Build Drawings Status* | [5 empty] | 0 | 1 |  | 0 | 53 | Storage Management in/out Control |  |  |  | 0 | 1 | 0 |  | 0.79 | 0.79
25 | Calibrated Lab Tools & Equipment |  |  |  |  | 0 | 0 | 1 | 0 |  | 54 | Material Control |  |  |  | 0 |  |  | 1 | 0.79 | 1
26 | Storage Inventory System | [5 empty] | 1 | 0 | 0 |  | 55 | Manholes Storing and Quality |  |  |  | 0 | 1 | 0 | 0 | 0.89 | 0.79
27 | Logistics Plan | [5 empty] | 1 | 0 |  |  | 56 | Reinforced Steel Quality |  |  |  | 1 |  |  | 0 | 0.89 | 0.89
28 | Project Progress Planview |  |  |  |  | 1 |  | 0 | 0 |  | 57 | Safety Overview |  |  | 0 |  | 1 |  |  | 1 | 0.79
29 | Sufficient Number of QC Inspectors |  |  |  |  | 0 | 1 | 0 | 0 |  | 58 | Waste Management Control |  |  | 0 |  | 1 |  |  | 0.89 | 2
0
Score
[8 empty] | *QC % |  |  | 93%
Prepared by: | [10 empty] | Issued to PM:
*QC Observations refer only to the practices and documentation observed at time of inspection. The responsibility of the CM and Contractor is to ensure that aspects of Quality are suitably managed. *Scores are a reflection of the general site conditions based upon the findings at the time of the walk through *If Applicable

## Quality-Stat
Quality Reports
Item |  | Issued | Closed | Pending | Avg. Closing (Days) | Pending
[6 empty] | 0-10 Days | 11-20 Days | 21-30 Days | 31-60 Days | > 60 Days
Non Conforomance Report (NCR) |  | 51 | 49 | 2 | 0 | 4 | 0 | 0 | 0 | 0
Site Instruction (SI) |  | 52 | 42 | 10 | 0 | 0 | 0 | 0 | 0 | 0
Material Inspection Report (MIR) |  | 116 | 113 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Field Inspection Report (FIR) |  | 4699 | 4481 | 218 | 0 | 0 | 0 | 0 | 0 | 0
Shop Drawings
Item Per WBS |  |  | Total Planned | Total Drawings Submitted |  |  |  |  | Remaining Drawings | Pending | Total Submittals
|  |  |  | A | B | C | D | Approved | with Designer | Submittals With Consultant
CVL |  |  | 1063 | 8 | 1055 | 0 | 0 | 1063 | 0 | 0 | 1063
Mech |  |  | 212 | 0 | 212 | 0 | 0 | 212 | 0 | 0 | 212
Elec |  |  | 41 | 0 | 41 | 0 | 0 | 41 | 0 | 0 | 41
Landscape & Arch |  |  | 458 | 0 | 458 | 0 | 0 | 458 | 0 | 0 | 458
TOTAL |  |  | 1774 | 8 | 1766 | 0 | 0 | 1774 | 0 | 0 | 1774
Material Approval
Item Per WBS |  |  | Total Planned | Total Materials Submitted |  |  |  |  | Remaining to approve | Pending | Total Submittals
|  |  |  | A | B | C | D | Approved | with Designer | Submittals With Consultant
Civil & Roads |  |  | 77 | 2 | 74 | 3 | 1 | 76 | 1 | 4 | 84
Electrical |  |  | 30 | 0 | 22 | 0 | 0 | 22 | 8 | 0 | 22
Mechanical |  |  | 48 | 0 | 41 | 0 | 2 | 41 | 7 | 3 | 46
TOTAL |  |  | 155 | 2 | 137 | 3 | 3 | 139 | 16 | 7 | 152
Procurement Summary
Item Per WBS |  |  | Total Materials Planned | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Actual Material on Site | Remaining Materials | Material Delivery Completion (Date)
|  |  |  | A | B | C | D | Processed
Civil & Roads |  |  | 77 | 77 | 76 | 1 | 55 | 22 | 2026-11-09
Electrical |  |  | 30 | 30 | 22 | 0 | 17 | 13 | 2026-09-27
Mechanical |  |  | 48 | 48 | 42 | 0 | 25 | 23 | 2026-09-28
TOTAL |  |  | 155 | 155 | 140 | 1 | 97 | 58 | 2026-11-09
Consultant Quality Inspections / Observations (Weekly Basis) | [7 empty] | Overall Average | 92.87% |  | Average Closing | 1
Week Number | Date of Audit | Date Issued | Numbers Of Comments | Quality Score | Date Closed | Closure Duration |  | This Week Score | 93% |  | Average Number of Comments Per Audit | 0
Week-1 | 2025-11-25 | 2025-11-25 | 0 | 82.03%
Week-2 | 2025-12-02 | 2025-12-02 | 0 | 89.03%
Week-3 | 2025-12-09 | 2025-12-09 | 0 | 89.03%
Week-4 | 2025-12-16 | 2025-12-16 | 0 | 96.91%
Week-5 | 2025-12-23 | 2025-12-23 | 0 | 93%
Week-6 | 2025-12-30 | 2025-12-30 | 0 | 89.09%
Week-7 | 2026-01-06 | 2026-01-06 | 0 | 91%
Week-8 | 2026-01-13 | 2026-01-13 | 0 | 92%
Week-9 | 2026-01-20 | 2026-01-20 | 0 | 91%
Week-10 | 2026-01-27 | 2026-01-27 | 0 | 91%
Week-11 | 2026-02-03 | 2026-02-03 | 0 | 93%
Week-12 | 2026-02-10 | 2026-02-10 | 0 | 92%
Week-13 | 2026-02-17 | 2026-02-17 | 0 | 91%
Week-14 | 2026-02-24 | 2026-02-24 | 0 | 91.77%
Week-15 | 2026-03-03 | 2026-02-17 | 0 | 92%
Week-16 | 2026-03-10 | 2026-02-10 | 0 | 93%
Week-17 | 2026-03-17 | 2026-03-17 | 0 | 96%
Week-18 | 2026-03-31 | 2026-03-31 | 0 | 96%
Week-19 | 2026-04-07 | 2026-04-07 | 0 | 93%
Week-20 | 2026-04-14 | 2026-04-14 | 0 | 93%
Week-21 | 2026-04-21 | 2026-04-21 | 0 | 93%
Week-22 | 2026-04-28 | 2026-04-28 | 0 | 95%
Week-23 | 2026-05-05 | 2026-05-05 | 0 | 93%
Week-24 | 2026-05-12 | 2026-05-12 | 0 | 94%
Week-25 | 2026-05-19 | 2026-05-19 | 0 | 94%
Week-26 | 2026-06-02 | 2026-06-02 | 0 | 94%
Week-27 | 2026-06-09 | 2026-06-09 | 0 | 94%
Week-28 | 2026-06-16 | 2026-06-16 | 0 | 94%
Week-29 | 2026-06-23 | 2026-06-23 | 0 | 94%
Week-30 | 2026-06-30 | 2026-06-30 | 0 | 94%
Week-31 | 2026-07-07 | 2026-07-07 | 0 | 94%
Week-32 | 2026-07-14 | 2026-07-14 | 0 | 94%
Week-33 | 2026-07-21 | 2026-07-21 | 0 | 94%
Week-34 | 2026-07-28 | 2026-07-28 | 0 | 94%
Week-35 | 2026-08-04 | 2026-08-04 | 0 | 94%
Week-36 | 2026-08-11 | 2026-08-11 | 0 | 94%
Week-37 | 2026-08-18 | 2026-08-18 | 0 | 94%
Week-38 | 2026-08-25 | 2026-08-25 | 0 | 94%
Week-39 | 2026-09-01 | 2026-09-01 | 0 | 94%
Week-40 | 2026-09-08 | 2026-09-08 | 0 | 94%
Week-41 | 2026-09-15 | 2026-09-15 | 0 | 93%
Week-42 | 2026-09-22 | 2026-09-22 | 0 | 93%
Week-43 | 2026-09-29 | 2026-09-29 | 0 | 93%
Week-44 | 2026-10-06 | 2026-10-06 | 0 | 93%
Week-45 | 2026-10-13 | 2026-10-13 | 0 | 93%
Week-46 | 2026-10-20 | 2026-10-20 | 0 | 93%
Week-47
Week-48
Week-49
Week-50
Week-51
Week-52
Week-53
Week-54
Week-55
Week-56
Week-57
Week-58
Week-59
Week-60
Week-61
Week-62
Week-63
Week-64
Week-65
Week-66
Week-67
Week-68
Week-69
Week-70
Week-71
Week-72
Week-73
Week-74
Week-75
Formulas:
Remaining Drawings = MAX(J31:[Remaining Drawings, row above])

## HSE
MODON HSE Site Inspection Report
Date |  |  | 2026-10-20 |  |  |  |  | Inspected By: |  |  |  |  | Muhammad Al Rajjal
Project ID. |  |  | DAM2-02-009 |  |  |  |  | Report No. | 46 |  |  |  |  | MODON PM Name |  | Muhammad H Al-Essa
Project Name: |  |  | Development of Infrastructure for phase 1 of the Logistics area at the 2nd Industrial City in Dammam |  |  |  |  | Contractor: |  | Shibh Aljazira Contracting Company |  |  |  |  | Safety Performance |  | 80 |  |  | 92.86%
Inspections are a snapshot in time and refer only to the practices and documentation observed at the time of the Inspection. It remains the responsibility of the Consultant and Contractor to ensure that all aspects of Health & Safety are suitably managed.
1 |  | Good Practice |  |  | 2 | Need Improvement | [5 empty] | 3 | Fail (Life Threatening Activity) / Comliance with Plan & Procedures |  | N/A | Atcitty Not Applicable for this Site Inspection Report
No. | Topic | [5 empty] | Wt. | HSE Compliance |  |  | No. | Topic | [5 empty] | Wt. | HSE Compliance
1 | Access and Egress - (General access to site, segregated from vehicles, / Overhead protection, while entering into the building /Adequate lighting provided when dark or overnight work) | [5 empty] | 5% | 2 |  |  | 14 | Work at Height - (PPE/Fall Protection(Same level, above and blow) / Training / Fall restraint / competency /Safe access & egress to and from work at height / Ladders / Openings (floor/shafts/Provision of emergency rescue) | [5 empty] | 5% | N/A |  |  |  | 1 | 100 | 1
2 | Traffic Management - (Loading/unloading/sheeting/temp. routes/speed/parking/competence) | [5 empty] | 3% | 2 |  |  | 15 | Scaffolding - (Temp. Scaffolding Work-platform (All types) - qualified scaffolder / Inspection / Tagged / Safe Access/egress / PTW/Falsework & Formwork) | [5 empty] | 4% | N/A |  |  |  | 2 | 75 | 2
3 | Site Signage - (Project Notice Board & General Signage) | [5 empty] | 2% | 1 |  |  | 16 | Mobile Elevated Work platform (MEWP) - (PTW/competence requirements/conditions/inspections/tagged/training/Full-body harness) | [5 empty] | 4% | N/A |  |  |  | 3 | 0 | 3
4 | PPE Compliance - (Use, storage, stock, handling & checks - Head, Foot, Eye, Hearing) | [5 empty] | 5% | 1 |  |  | 17 | Excavation & Trenches - (PTW/Edge protection/buffer zone/Slope/Benching/Shoring/Geo-tech report/Atmospheric hazards/Acess&egress/Emergency management / MS&RA/H.E) | [5 empty] | 3% | N/A | [5 empty] | N/A
5 | Housekeeping - (Material correctly stored/Rubbish cleaned & removed daily/slips & trips hazards) | [5 empty] | 3% | 1 |  |  | 18 | Confined Space - (PTW/Training/competence/Emergency Management/MS & RA/Safe access/egress) | [5 empty] | 5% | N/A
6 | Storage of Materials - (Transporting, storage, training and use - Combustible / Flammable / Hazardous substances (COSHH) | [6 empty] | 1 |  |  | 19 | Fire Protection - (Flammable/Oxy. LPG /Combustible separated/FE's/Flashback arrestor/Sparks & slags/Smoking area/PTW/Generators/MS & RA/Emergency Management) | [6 empty] | 1 |  | Red | Serious injury or death (immediately)
7 | Site Waste Management - (Hazardous waste /Combustible waste / Human waste / Construction waste - asphalt, cable, timber, paving roof sheeting tiles, plastic & bricks) | [6 empty] | 2 |  |  | 20 | Health & Welfare - (Adequate drinking water/shaded - eating & rest area/washing & sanitary facilities/Certified FA/FA Box & Stock/adequate toilets/Ambulance) | [6 empty] | 1 |  | Yellow | Minor or near miss (3 days to comply)
8 | Health Surveillance - (Expose to excessive noise/vibration/dust/silica/CO/cement/radiation/extreme weather condition) | [5 empty] | 3% | 1 |  |  | 21 | Environmental Incident Measures - (Spill/ Leakage / Concrete wash / vehicle & eqpts. wash / waste disposal/Sewers and drains/emissions/Emergency Management/Training/site run-off water) | [5 empty] | 5% | 2 |  | Green | No issues
9 | Electrical Safety - (Electrical qualified /RCD/GFCI/Industrial Cocket/LOTO/Cable-overhung or buried/Cords in good condition/current inspection tag) | [5 empty] | 5% | 1 |  |  | 22 | HSE Communications & Meetings - (Schedule HSE Meetings/Safety Committee meetings/Alerts / Lesson learned/Safety Bulletin contains latest HSE KPI) | [5 empty] | 5% | 1
10 | Tools & Equipment - (Includes, powered, hydraulic & pneumatic/Guards in place/Properly stored/RCD Protection/Earthed/Good condition & tagged) | [5 empty] | 3% | 1 |  |  | 23 | HSE Plan & Associated Procedures - (Approved updated HSE Plan/ CEMP/HAZComm/Procedures/Standards/Project Safety Risk Register) | [5 empty] | 3% | 1 |  | 26 points > 4 minors then is it’s a serious issue
11 | Manual Handling - (Lifting/loading/pulling/pushing/twisting/awkward posture/repetitive task/frequent and prolong physical effort/Reasonable practicable use of mechanical aid) | [5 empty] | 3% | 1 |  |  | 24 | Health, Safety & Environment Incident reporting - (Review of HSE Statistics, Reporting of Unsafe Act & Conditions/ Reporting of Near Miss incident/Reporting of FA cases/Record MT cases) | [5 empty] | 3% | 1
12 | Vehicle and mobile equipment / Plant - (dumpers; excavators, cranes, piling rigs, grader, roller, loaders/condition/KSA License/certification) | [5 empty] | 5% | 1 |  |  | 25 | HSE Awareness, Training & Competence - (Policy /Objective & targets/Information, training/Climatic condition awareness/Reponses in emergency situation/ Safety Behavior Observation) | [5 empty] | 4% | 1
13 | Lifting Operations & Rigging - (Lifting Plan/Lifting devices & gears/PTW/Condition/3rd party certification/bank-man/rigger/slingers/man-basket/inspection record/tagged) | [6 empty] | 2 |  |  | 26 | Project Leadership Site Tours - (Provide evidence of proactive safety performance/Deficient discovered discussed/Positive feedback/Workers resolving safety issues) | [6 empty] | 2
Prepared by: |  |  |  | Muhammad Al Rajjal | [6 empty] | Sent to MODON PM: |  |  |  | Muhammad H Al-Essa
Safety Results
1 |  | 15 |  |  |  | 2 |  | 6 |  |  |  |  | 3 | 0
Note on C13: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Safe access / egress for people to their work area 2 - Safe access / egress for construction vehicles 3 - Access properly restricted-site fencing provided and maintained 4 - Access proper and not blocked 5 - Safe access is available for rescue operation 6 - Storage access / exit are clearly marked and unobstructed 8 - Access and egress is in good condition, hand holds, ladder etc. are sound and in place 9 - Ensure unauthorized public access is prevented 11 - Site assembled ladders or make-shift tables for access are forbidden on site. 13 - Use proper bridges, walkways or gangways to access or cross trenches or an excavation area 14 - Surrounding areas are cleared and barricaded and access restricted to all unauthorized trades while crane in operation 15 - To ensure early access to accredited medical / rehabilitation services 16 - Parking vehicles on site access roads causing obstruction 17 - All personnel will be instructed that access to firefighting equipment must remain clear at all times 18 - Access control gates to be locked out of hours 19 - Site access gates to be designed and located to, where possible, avoid clashes with external hazards / activities
Note on T13: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Personal Fall Arrest System; 1 - Is the suitable harness harnesses is provided 2 - Are shock absorbing lanyard with 2 locking snap hooks. 3 - Is anchorage point strong enough and can support 5,000 Ibs. 4 - Do inspection checklist is being implemented before use. 5 - Is the emergency plan for rescue in place Personal Fall Restraint System; 1 - The fall restraint equipment should be set and adjusted so there is no free fall over the edge. 2 - A harness or body belt may be used 3 - The anchorage point must support 4 times the intended load. Positioning System; 1 - Is a suitable harness or body belt provided 2 - Is there a not more than 2' free fall maintained 3 - Is the anchorage point capable of supporting 2 times the intended load or 3.000 Ibs, whichever is greater 4 - Is 100% tie-off (protection from falls at all times, even when moving from point to point) provided while using personal fall protection with two lanyards Fall Protection System; 1 - Suitable edge protection and work platforms are to be provided to prevent a fall occurring 2 - Where the provision of edge protection or adequate platforms cannot be provided safety nets or other soft-landing systems such as inflatable bags are to be used to minimize the consequences of a fall. 3 - If nets are used, they must be installed by a competent rigger and fitted as close under the work surface as possible. 4 - Areas below roof works are to be cordoned off and properly signed to prevent personnel being injured from falling materials 5 - If access onto the roof cannot be avoided, edge protection is to be installed 6 - Floor and wall openings are to be protected using covers of adequate strength to withstand the expected load that will be imposed and securely fixed. 7 - Penetrations in walls such as those provided for lift shafts, door openings, etc. are to be closed with suitable strength material or have fixed protective barriers around the penetration with a sign warning personnel of the danger of falling.
Note on C14: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are arrival and departure of vehicles and delivery accompany by security department? 2 - Are proper loading, unloading and securing loads, being properly controlled? 3 - Is the proper sheeting & coupling in place when transporting and disposing material to and from site? 4 - Is the parking to the designated parking lot and in reverse order? 5 - Is the designated speed limit adhered on workplace? 6 - Provision of ramps, traffic signs, cones, barriers, demarcation posts and tape, flashing lights and any other traffic control devices. 7 - Do visiting drivers are being inducted at the workplace, prior to enter on the workplace? 8 - Are visiting drivers restricted to dangerous areas, e.g. moving to and from they vehicles to washrooms, lavatory & offices etc.? 9 - Do drivers observe site rules and procedures, for delivery, loading and unloading? 10 - Are the areas wide enough for the safe movement of large vehicles (including visiting vehicles)? 11 - Does drivers are competent, hold valid local driving license and competent training? 12 - Ensure the vehicle and trailers have their brakes applied and all stabilizers properly positioned before beginning loading or unloading?
Note on T14: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Base soundness, load adequately spread (base plate jacks, base plate on firm ground). 2 - Line of standard (vertical) and ledger (horizontal) secure and plumb. 3 - Spacing of transoms on platforms, support for Scaff boards, boards are not over protruded and boards are secured. 4 - Staggering of joints vertical and horizontal. 5 - Guardrail / fall protection. (Top rail – Min.1mtr, Mid rail – 470mm from floor and Toe boards – Minimum150mm) 6 - Longitude and bracing on standards and ledgers. 7 - If close to structure, ties must be on lift below to top working platform and every 3m, load bearing couplers used or tie with certified anchor bolts (eye bolts). 8 - Clamps and tubes used are of correct fittings, size and free from defects. 9 - Tubes & fittings free from defects / deformation. 10 - Safe and proper access available to the working platform. 11 - Scaff tags signed, displayed and up to date. 12 - If close to slab edge/opening scaffold tied and secured to structure correctly.
Note on C15: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a Project Notice Board - (showing HSE Statistics / Safety alerts / lesson learned)? 2 - Is there prominent safety boards that are depicting the mandatory PPE on the workplace? 3 - Are other safety required signs are prominently installed on the workplace in relevant to their work-task, as following: > Hazardous Substances - e.g. respiratory protection Sign > Working at Height - e.g. Full body Harness Sign > Working UG - e.g. Full body Harness, SCBA, Ventilation, PTW Signage etc. > Working with Electrical - e.g. Leather Gloves, Goggles, Face shield, Electric shock proof helmet & shoes > Working with Chemicals - Signage = e.g. Impermeable gloves/clothing's, long sleeves, Goggles 4 - General Site Safety Signs: > Prohibition Sign = (e.g., ‘no access for unauthorized persons’). > Warning Signs = (e.g., ‘danger: electricity’) > Mandatory Signs = e.g., ‘eye protection must be worn’) > Emergency Escape or First Aid Sign = e.g., ‘emergency exit/escape route’) > Safety Color Signs = (e.g., yellow means ‘be careful’ or ‘take precautions’) > Illuminated Signs = (e.g., many emergency exit signs) > Acoustic Signals =( e.g., fire alarm) > Fire safety sign > Supplementary Signs = "This way"
Note on T15: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Man-Lift operators are to be competent and trained to operate the specific Man-Lift by examination and hold a current approved certificate / license from an approved and internationally recognized source (TUV, SGS etc. 1 - All Man-Lifts shall be inspected by a 3rd party on an annual basis. 2 - All Man-Lifts shall display a sticker corresponding to the 3rd party inspection certificate. 3 - The manufacturer's instruction manual must be on site for each and every type of Man-Lift in use. 4- A pre-start daily operator inspection of the equipment will be performed and documented on a daily basis as per the manufacturer's instructions. The user is responsible for ensuring this has occurred. 5 - The use of a Man-Lift as, or in lieu of, a Crane is strictly prohibited. Man-Lifts are to be used only for lifting personnel and small tools within the designed Safe Working Load. 6 - The platform is not to be loaded in excess of the designed working load; the safe working load of the platform is to be clearly displayed on both the platform, and body of the equipment. 7 - All persons inside work platforms shall wear a full-body harness attached to the designated anchor point. Personnel must stand on the floor of the working platform; standing on the handrails is strictly prohibited. Harnesses must not be attached to other structures outside of the working platform. 8 - Personnel must stay inside the working platform at all times; the platform must not be used as an access to structures. The use of staging or ladders to extend height is strictly forbidden. 9 - Securing the boom or work platform to any structure is strictly prohibited. The boom or working platform must not be rested upon on any structure, nor is the Man-Lift to be used as a jack/ prop or tie to support other structures. 10 - All Man-Lifts must be equipped with a 5kg (10lb) fire extinguisher. 11 - No man-lifts are to be operated that have had safety devices removed or disabled. Daily operator inspections are to include the testing of these devices (limit switches, alarms and hazard flashing beacons). 12 - Specific Man-Lifts are fitted with outriggers and/or stabilizers which must be used as per manufacturer's instructions. 13 - The work area surrounding the man-lift is to be cordoned off using barricades and signage if the area is used by other workers or vehicles. A full traffic management plan is required for all works involving man-lifts when working on highways. Under no circumstances is any part of a man-lift to extend or swing into a line of traffic.
Note on C16: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Does required mandatory PPE (refer specification BS, EN & ANSI) is provided, as following? > Safety helmet (see below for color scheme) > Safety glasses (shaded for outdoor work and clear inside structures and during non-daylight hours) > Safety boots (safety shoes are prohibited) > Orange hi-visibility vest 2 - Additional PPE shall be provided to a specific task 3 - Do specific PPE is provided according to their job requirement? > To work at height - Full Body harness / Fall arrest Devices / Fall Restraint Devices / V & H Lifeline etc. > To work in the confined space - Full Bodyarness, Tripod with retractable lifeline, SCBA, Masks etc. > 4 - Are the PPE stored appropriately to prevent deformation or distortion? 5 - Has self assessment being carried out for in according to the work requirements? 6 - EYEWEAR (Glasses/Goggles/Face Shields) > Eyewear cleaning supplies available. > Safety glasses in good condition and lenses free of scratches. > Goggles adjustment strap not cracked or frayed, not deformed, or lenses not > Face shields in good condition, including adjustment band, and free of scratches or 7 - HEAD PROTECTION > Hard hat bill and suspension attached as allowed by manufacturer. > is pliable, free of dents, cracks, nicks, or any damage due to impact. > Suspension maintained at 1.25 inches from inside of shell. > Suspension free of cuts or fraying, torn headband, adjustment strap workable. > Electrical hard hat matched to hazard classification. > Dated to determine whether within manufacturer’s allowable 5-year use time period. 8 - HAND PROTECTION > Available in sizes matched to employee. > Gloves free of rips tears, abrasions, or holes. > Matched to manufacturer’s specification for chemicals used onsite. > Electrical gloves matched to hazard and periodically inspected for insulating rating. > Maintained in a clean and sanitary condition, decontaminated or disposed properly. 9 - BODY PROTECTION > Available in sizes matched to employee. > Maintained in a clean and sanitary condition, decontaminated or disposed properly. > Vapor-tight fully encapsulated suits tested at required periodic intervals. > Flame-resistant clothing matched to electrical hazard and arc flash rating. > Welding gear matched to degree of hazard and free of cuts, tears or burn holes. > Flotation gear available for work near or on water and in good condition. 10 - HOT AND COLD BODY PROTECTION > Cooling gear available based on degree of heat stress hazard. > Cooling gear in operable, clean, and sanitary condition. > Cold-weather gear provided based on needs assessment. > Cold-weather gear available in sizes to match employees. > Cold-weather gear is in free of tears, rips, or holes and in maintained in a clean condition. 11 - TRAINING > Initial PPE training completed by employees. > Training conducted when new types or styles of PPE are issued. > PPE selection, use, and maintenance reviewed at daily safety briefings. 12 - Provision of impermeable clothing appropriate for the work being performed? 13 - Wearing of shorts, sleeveless shirts, loose clothing are prohibited across the MODON Projects. 14 - Clothing contaminated with grease, oils, fuels and other hazardous substances is not to be worn.
Note on T16: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a valid Excavation PTW in place? 2 - Are spoils, materials, and equipment set back at least 1.5 meters from the edge of the excavation? 3 - Are walkways and bridges over excavations structurally sound, minimum 0.5 meter in width and equipped with standard guard rails and toe boards? 4 - Are warning systems established and used when mobile equipment is operating near the edge of an excavation? 5 - Are employees prohibited from working on the faces of sloped or benched excavations above other employees? 6 - Are the exact locations of Utilities (piping, electrical, etc.) clearly marked? 7 - Are underground installations protected, supported, or removed when an excavation is open? 8 - Are ladders or other means of access and egress in place as per the PTW requirements? 9 - Are all workers within 7.6 meters of a means of access and egress to a trench? 10 - Are ALL ramps constructed of materials of uniform thickness, cleated together, equipped with no-slip surfaces? 11 - Are employees protected from cave-ins when entering or exiting excavation? 12 - Are precautions taken to protect employees from water accumulation and dewatering is being carried out? 13 - Is surface water or runoff diverted after every rainstorm or other hazard-increasing occurrence? 14 - Is the excavation classified as a confined space? If so, is their a valid confined space PTW and is the atmosphere being tested when there is a reasonable possibility of an oxygen-deficient, oxygen-enriched, combustible, toxic, or other harmful contaminant? 15 - Have materials and/or equipment chosen for shoring been based upon soils analysis, trench depth and expected loads (as per Excavation PTW)? 16 - Are shoring materials and equipment that are used for protective systems inspected and in good condition? 17 - Are damaged shoring materials and equipment immediately removed from service? 18 - Are damaged shoring materials and equipment inspected by a Registered Professional Engineer after repairs are made and before being placed back in service? 19 - Are protective systems installed without exposing employees to hazards of cave-ins, collapses, or threat of being struck by materials or equipment? 20 - Are ALL members of support systems securely fastened together to prevent failure? 21 - Are support systems provided to insure stability of adjacent structures, buildings, roadways, sidewalks, etc.? 22 - Are excavations below the level of the base or footing supported, and approved by a Registered Professional Engineer? 23 - Does back-filling progress with the removal of the support system? 24 - Is a shield system installed to prevent lateral movement? 25 - Are employees prohibited from remaining in a shield system during vertical movement?
Note on C17: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Sites are to be kept clean and tidy and free from slip, trip and fall hazards. 2 - Do all personnel trained in the importance of good housekeeping, managers, supervisors undertake regular monitoring and inspection of the workplace? 3 - Workplace are to be left clean and tidy at the end of each shift and where there is an accumulation of materials throughout the shift, at regular intervals as required to maintain a clean and safe site. 4 - Buildings under construction and nearing completion must ensure that all combustible and flammable materials are removed at the end of each shift. 5 - Nails are to be removed from timber as soon as possible, where this is not practical they are to be flattened and placed in a safe area (barrier and signs) until nails can be removed at a later time. 6 - Materials are to be stored so as they do not pose a risk to personnel stacking, removing or walking by (further guidance is given in the materials storage and handling section). 7 - All spills are to be cleaned up immediately using absorbent material. 8 - Cables/hoses/other trailing leads are to be protected, buried or secured above head height to avoid a slip trip, fall hazard. 9 - Waste is to be placed in designated containers and covered to protect against high winds, pests or risk of fire. Waste containers are to be emptied on a regular basis to prevent a build-up of material. 10 - Loose or light materials that are stored on roofs or open spaces are to be secured to prevent them from inclement weather. Location: 1 - Receptacles located inside buildings shall be kept at least 18 inches away from combustible walls and partitions. 2 - Receptacles for combustible trash that are located outside of buildings shall be placed at least 15 feet from the building or combustible material. Use: 1 - Cigarettes, cigar butts, matches, and similar potential ignition sources should never be placed in a trash receptacle. Proper receptacles for such items should be provided in areas designated for smoking. 2 - Broken glass, empty jars, scrap metal, and similar construction material should never be placed in office trash containers. A roll-off bin or other appropriate container should be used to hold construction debris. Environmental: 1 - Container storage areas shall be kept clean and free of trash. Improper disposal of food waste can attract pests and vermin. Prevention methods that do not involve the use of toxic chemicals is the preferred method of pest control. 2 - Outdoor containers should be kept covered when not in use so as to avoid attracting pests and to prevent the entry of water. Dripping or leaking trash containers may violate local storm water quality discharge regulations. 3 - Promote recycling by contracting with a waste removal company that provides reuse as part of the waste processing or by providing segregated bins for the collection of office paper, aluminum cans, plastic bottles, and toner cartridges. Rinse empty cans and bottles of sugar-based soda so as not to attract ants and other pests. 4 - Proper lighting (indoor) or during Night Shift are provided. Accurately installed. No impairement or poor visibilty is generated. No shadow due to installation of lights are presents.
Note on T17: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Permit is taken for confined space entry and all recommended precautions are in place. 2 - Operatives are trained and fit for the specified job. 3 - Confined space is well ventilated by means of mechanical ventilation. (Exhaust fan, blowers, low velocity air hose etc.). 4 - Rescue system (Tripod with hoisting device, Rescue Harness etc.) in place and sufficient trained persons are available for the rescue operation. 5 - Safe access is available for rescue operation. (Manhole size - Min. 450 mm X 407 mm or 457 mm Dia.) 6 - Atmospheric monitoring conducted and confined space is safe to enter. Percentage of gas concentration will be monitored and recorded every 4 hrs. A. Oxygen percentage. (Permissible limit – 19.5% to 23.5%) B. Flammable gas or vapors.(Permissible limit - <10% of LFL) C. Carbon Monoxide. (Permissible limit - <50ppm) D. Hydrogen sulfide.(Permissible limit - <10ppm) E. Any other toxic gas or vapors. _______________________________ 7 - Minimum two persons shall be assigned to work in the confined space. One person will remain in the entrance at all times to monitor the work 8 - All persons shall wear safety harness, which should be connected to safety line from outside at all times. 9 - All electrical equipment & leads are free from damage and guards in place. 10 - All electrical tools & equipment are connected through ELCB. 11 - Compressed gas cylinders are kept outside the confined space. 12 - supervisor / Foreman will be available at all time to monitor the work and for the rescue operation. 13 - Tool box talk conducted for the entire team and they are well aware of the risks. 14 - Proper communication system is available in between persons inside and standby person. 15 - Trained First aider with first aid kit will be available when working in the confined space. 16 - Confined space entry register is available and shift records will be maintained. -
Note on C18: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Combustible: 1 - Ensure oily rags, combustible material and other flammable substances which may ignite are not accumulated and that they are removed without delay to the designated disposal / storage area. 2 - Combustible materials shall not be stored within 20 feet (6.1 meters) of compressed gas cylinders. 3 - Safety cans used for dispensing combustible liquids shall be kept at a point of use 4 - Storage rooms for combustible liquids must have explosion-proof light fixtures 5 - No flames - hot work or smoking is be permitted in combustible liquid storage areas. Flammable: 1 - Adequate training in the use and storage of flammable liquids is in place. 2 - Storage of Flammable liquids in accordance with NFPA approved flammable storage lockers or in low value structures at least 50 feet from any other structure. 3 - Do not store other combustible materials near flammable storage areas 4 - Bulk drums of flammable liquids must be grounded and bonded to containers during dispensing 5 - Portable containers of gasoline or diesel are not to exceed 5 gallons 6 - Safety cans used for dispensing flammable liquids shall be kept at a point of use 7 - Appropriate fire extinguishers are to be mounted within 75 feet of outside areas containing flammable liquids, and within 10 feet of any inside storage area for such materials. 8 - Storage rooms for flammable liquids must have explosion-proof light fixtures 9 - No flames - hot work or smoking is be permitted in flammable or combustible liquid storage areas. 10 - Flammable liquid transfer areas are to be separated from other operations by distance or by construction having proper fire resistance. 11 - When not in use flammable liquids shall be kept in covered containers. 12 - Flammable materials are considered hazardous and as such, material safety data sheets and appropriate hazard communication training for affected employees is required 13 - Maintain high levels of housekeeping, particularly with relations to flammable materials. 14 - Where flammable materials are handled in the course of work, safe work procedures must be prepared and documented with reference made to the Material Safety Data Sheets (MSDS‘s) for the materials concerned. 15 - All people handling, working with or in control of flammable substances must be properly trained and supervised (documentation to be maintained). 16 - Lead, dust, fumes and vapor constitute a major health hazard to workers. Hazardous Substances COSHH 1 - Under COSHH the risk presented by any hazardous substance assessed using hierarchy of control, stored, transported, created or disposed and usage at the workplace; > Very toxic or toxic: Substances that, in low quantities, cause death or acute or chronic damage to health when inhaled, swallowed or absorbed via the skin > Harmful: Substances that may cause death or acute or chronic damage to health when inhaled, swallowed or absorbed via the skin > Corrosive: Substances that may, on contact with living tissues, destroy them > inhalation into the lungs, when the substance is in the form of a gas, vapor, fume, mist, aerosol or dust > absorption through the skin or eyes by contact with a substance that can penetrate unbroken skin, or is absorbed through unprotected cuts or grazes > injection by contact with contaminated sharp objects or high-pressure equipment, e.g. water jetting > ingestion by swallowing particles of a hazardous substance resulting from hand-to- mouth transfer
Note on T18: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are regular and frequent fire safety inspections carried out? 2 - Have a sufficient number of fire marshals/evacuation officers been appointed? 3 - Are water supplies adequate? 4 - Does the building or site have a written fire procedure? 5 - Is there an effective permit to work system in operation for all hot work and other fire related work? 6 - Do all doors from areas from which a large number of people may have to escape open in the direction of travel? 7 - Do all emergency exit doors (i.e. doors not in normal use) have clear instructions displayed on how to open? 8 - Are all escape routes clear and unobstructed? 9 - Are all fire exit doors correctly signed? 10 - Is all fire fighting equipment immediately visible or correctly signed? 11 - Are all flammable and explosive substances adequately signed to indicate their presence and danger? 12 - Where necessary, is there a sufficient number of emergency lights to adequately illuminate all internal escape routes, exit doors and signs? 13 - Where automatic fire detection is deemed to be necessary is there an adequate number of detectors in the critical areas? 14 - Where the means of raising the alarm is by hand-operated devices, can the operation of one device be heard throughout the entire building or site? 15 - Is there an adequate number of fire extinguishers in the building? 16 - Is there firefighting equipment other than extinguishers in the building? 17 - Are all electrical circuits and fixed electrical installations examined and tested at an acceptable frequency? 18 - Is housekeeping to an acceptable standard? 19 - Have all staff been trained in fire procedures in the last twelve months? 20 - Are all fire drills adequately recorded?
Note on C19: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - General construction waste streams generated including; > Asphalt, cable, timber, paving, roof sheeting, tiles, plastic sheeting and brickwork. > Excess concrete, spoil material from excavations. > General waste, such as putrescible food scraps and packaging from workers. > General (food) waste, construction/concrete waste, hazardous waste, paper/cardboard and waste water/sewage. 2 - Are hazardous waste identified with hazardous Waste label. 3 - Containers are properly labeled in according to their contents. 4 - Container inspections are documented in writing using the Container Inspection Checklist. 5 - Weekly inspections logged into book using the Accumulation Area Inspection Log Sheet. “NO SMOKING OR OPEN FLAME” sign posted. 6 Disposal facilities identified, evaluated using the procedures. 7 - Disposal facility accepted waste and issue approval letter. 8 - Waste transfer/dispose tracked using Waste Tracking Form. 9 - Waste streams, such as asphalt and concrete, to be recycled should be segregated and separately stored. 10 - Spill Release Contingency: 1 - Prior to beginning operations, ensure that on-site spill response capabilities (containment and personal protective equipment) are consistent with task requirements described in job hazard analysis.
Note on T19: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: HHE is required at all locations where chemical hazards exist, such as; storing, transferring and handling facilities, under routine conditions. The HHE scope shall include the physical, chemical, radiological, and biological health hazards. Physical health hazards include elevated noise and vibration exposures, repetitive motion work operations, ionizing and non-ionizing radiation exposures heat and cold stress and biological hazards include infectious disease agents. HHE shall be performed before the site mobilization; 1 - Is the adequate eating or mess area is provided and sufficient for number of workers? 2 - Are sufficient tables and Chair are provide and Kept Clean? 3 - Are FEs, signs, pest control being implemented? 4 - Is washing Area sufficient and Kept Clean? 5- Cooking Area Kept Clean? 6 - L.P.G. Cylinder stored outside, secured & upright 7 - Sufficient drinking water provided. Filters changed (as per manufacturer recommendation)? 8 - Sufficient toilets, washbasins, cleaned/disinfectant provided? 9 - Provision of First Aider 10 - Provision of Nurse 11 - Provision of First Aid Kit 12 - Provision of site clinic with required first aid equipment and items. 13 - Provision of shaded area on the workplace 14 - Provision of Ambulance or an equal arrangement in place" 15 - Smoking area is Prohibited other than designated smoking areas, clear of flammable and combustible materials? 16 - All toilets, washing, rest and eating facilities to be kept clean, hygienic and be well maintained at all times? 17 - Waste Management - Covered bins, emptied daily, close proximity, color coded etc.? 18 - Are the monitoring, including integrated air sampling, noise dosimetry and other exposure assessments, being carried out? 19 - Are the Physical, chemical, and biological stresses, being identified, results are taken with action level to prevent sickness, impaired health, significant discomfort, or inefficiency in workers? 20 - Are WEL, LEL, OEL PEL & TLV linked to control workers airborne exposure to a chemical in a concentration above which is likely to cause death or immediate or delayed permanent adverse health effects or prevent escape from such an environment, if bening implemented?
Note on C20: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Is the hierarchy of Control is beng carried out on the following and recorded; 1 - Exposure to Chemical; e.g. - Dust, Gas, Mist, Vapor 2 - Exposure to Radiation; e.g. - Pipe radiography etc. 3 - Exposure to Biological Hazard; e.g. - Bloodborne pathogens / Legionella / Leptospirosis 4 - Exposure to noise; e.g. Loss of hearing / Physical damage to hearing mechanism 5 - Heat and cold stress work; e.g. - Heat-stroke, Heat stress / Frostbite / 6 - Repetitive Motion Work; e.g. - Musculoskeletal disorder, awkward position etc. 7 - Is the risk assessment carried out on the hazardous material and covering the following; > Allowable exposure limits, > Exposure monitoring requirements, > Methods of compliance for potential over exposure conditions, > Medical surveillance program, > Hazard communication, employee training requirements, 8- Is the IH Surveillance Plan should being implemented and have rocored on the following; > Which exposure groups require IH monitoring and medical surveillance > Specific substances or agents to be monitored, > The OELs to be used to evaluate results > The statistical basis to continue or cease monitoring > Specific medical testing/protocol to be implemented 9 - Do we've program on identifies work conditions such as the following, the exposure must first be mitigated or work shall not be performed. > Oxygen concentrations less than 19.5% or greater than 23.5%, or > Atmospheres greater than 1% of the Lower Explosive Limit, or > Atmospheres that are >50% of Immediately Dangerous to Life or Health (IDLH) concentrations, or > Work with sensitizers or known human carcinogens, mutagens, or teratogens without process isolation or fully encapsulating personal protection, or > Work with highly infectious biological agents without process isolation
Note on T20: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are all dispensing areas diked or properly graded to control drainage of spilled fuel? 2 - are all workers and operatives are trained to use spill response kit? 3 - Is the procedure in place for collecting and/or containing, and disposing of spilled materials? 4 - All tanks & vessels areas are diked to contain accidental spills?. 5 - Do measures taken to prevent an accidental contaminated runoff from construction , operation, maintenance, plant and storage areas? 6 - Do measures taken to control on deposits of oils, greases and fuels, from site plant and vehicle operations, mechanical failures, spillages and discharges to ground or drains and the dispersion of unattended spills by plant / vehicle movements?. 7 - Do measures taken to control on fuels, oils and other hazardous chemicals spilled on site during re-fueling, storage or transport operations?. 8 - Do we have an Emergency Response Procedure will be followed in the event of environmental emergency such as an oil or chemical spill? 9 - Is there a procedure for concrete wash, clean and dispose to prevent ground contamination, such as; Concrete wash pits with leak proof sedimentation tanks will be provided for washing concrete mixer trucks. The design and location of such wash pits shall be agreed with the Project Manager prior to its construction on site. Concrete dumping or spillages of any kind shall not be allowed in any other location on site? 10 - Is there a procedure to used in the situation of a major spills that will have an impact on the surrounding environment will be promptly reported to the Fire Brigade? 11 - Are there a procedure of disposing off any damage/leakage drums or containers shall be removed in accordance with the local requirements? 12 - Are there a procedure of dealing with spilled contaminated soils, resulted and remediated, accordingly? 13 - Are all personnel trained in the use of spill procedure and response and the adequate spill kits are available on site?
Note on C21: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - All electrical extension cords are equipped with nonconductive plugs 2 - Cords must not be spliced or draped over nails, metal objects 3 - The use of extension cords by means of multiple outlet plugs from single outlets is prohibited 4 - All electrical service removals, alterations and equipment installations are performed by an authorized electrician 5 - Faulty electrical installation 6 - Electrical supply disruption 7 - Exposed cables 8 - Trip / fall hazards from installed cables 9 - Fire hazard Electrical overload 10 - electrocution 11 - Electrical (short circuit) - Contact with exposed conductors or a device that is incorrectly or inadvertently grounded, such as when a metal ladder comes into contact with power lines 12 - Electrical - (static discharge) 13 - Electrical Fire - Use of electrical power that results in electrical overheating or arcing to the point of combustion or ignition of flammables, or electrical component damage 14 - Improper grounding 15 - Damaged insulation 16 - Exposed electrical parts 17 - Overloaded circuits 18 - Inadequate wiring 19 - Wet conditions 20 - Overhead power lines 21 - Damaged tools and equipment
Note on T21: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a meaningful and an effective consultation and communication on health and safety matters being implemented through out the project? 2 - Is the Consultation and communication on health and safety matters in place through the following mechanisms: > Project specific induction - (prior to commencement of contracted work) > Work activity Induction (in SWMS or equivalent) - (prior to commencement any construction work) > Toolbox Meetings - (Monthly intervals or generally when there is the introduction of a new process (SWMS) or when discussing OHS issues/topics). > Subcontractor Meetings - (weekly) > Project team meetings - (weekly) > HSE Committee Meeting - (as agreed with the HSE Committee) > OHS Report - (monthly) > Project Notice Board and general signage - (as required) 3 - Is there a method of communication is to be established in the work procedures to allow constant monitoring of those persons working in the confined space? 4 - Is there a material safety data sheets and appropriate hazard communication training for affected employees is in place? 5 - Are all environmental aspects and impacts been communicated to employees? 6 - Dose the notice
Note on C22: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1- Check that all the workers are using safe hand tools/power tools and instruct them to operate and maintain the same in safe manner 2 - Ensure power tools and hand tools are checked prior to issue 3 - Damaged tools and equipment 4 - Electrical tools or electrical equipment are not to be issued for use until inspected. 5 - Electrical tools or electrical equipment are not to be issued for use until inspected. 6 - "Defective" electrical tools and equipment are to be tagged and removed from service until repaired and inspected 7 - The frequency for inspection of construction electrical tools and electrical equipment shall be monthly and inspection indicated by attached color-coded tape or color- coded tie wraps and a color coded inspection tag with Contractor‘s name, the supervisor, the inspection date, equipment number and signature of competent inspector displayed on the tag. 8 - Checking the cords for worn or cracked insulation. 9 - Checking the cords entry to plug and tool housing for frayed or worn insulation and strain relief. 10 - Checking the plug prongs for damage. 11 - Checking the plug for exposed connectors 12 - Checking the equipment housing for damage. 13 - Checking trigger locks to ensure they have been removed 14 - Checking the leads for signs of wear, poor connections at probes, etc. 15 - Checking the housing and the readout window for cracks, loose screws, etc. 16 - Check all Ground Fault Circuit Interrupters (GFCI) during the monthly inspections. 17 - Machines are free from any defects / damage. 18 - Pressure switch and safety guards in place where applicable. 19 - Leads are fitted with correct plugs & sockets and free from damages. 20 - Leads wires are free from joints, cuts and other defects. 21 - Leads are suitably rated for the electric current. 22 - Machines / Tools are equipped with properly functioning dead man switch. 23 - Tools issue and maintenance record is properly maintained. 24 - Tools are correctly stored. 25 - Discarded Tools / cords are marked and stored separately.
Note on T22: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is the Project HSE Plan presents actions, responsibilities, protocol, conformance, verification and containment activities to be undertaken by project staff and sub-contractors at all times during the construction phase of the project. 2 - Is the implementation of the HSE plan is being monitored, evaluated for accuracy and any changes made communicated to all relevant personnel. 3 - Is the HSE Plan, CEMP, Security Plan, HAZcomm., standards & procedures are updated, signed, approved and distributed, acknowledged to the construction team's responsible individuals? 4 -Is the project overall safety risk register developed, approved and being implemented?
Note on C23: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Immediate Postural and Load Factor; 1- Is the body position stable? 2 - Is the trunk of the body straight (not twisted)? 3 - Is the operation carried out by one person? 4 - Is the load kept close to the body? 5 - Can the handler avoid stretching upwards? 6 - Can the handler avoid a prolonged period in one posture? 7 - Can the handler perform the task without overreaching? 8 - Are both hands used for grasping? 9 - Are the hands less than a shoulder width apart? 10 - Is the load positioned centrally in front of the body? 11 - Is the load reasonably symmetrical? 12 - Is the load stable and easy to grasp? 13 - Can handlers move and position themselves freely? Environmental Risk Factor; 1 - Too hot? 2 - Too cold? 3 - Too bright? 4 - Too dark? 5 - Too noisy to allow effective communication? 6 - Too wet? 7 - Slippery underfoot? 8 - Does any personal protective equipment interfere with the task? Carrying; 1 - Is the load carried at knuckle height? 2 - Is the load carried at arm's length from the body? 3 - Is the load carried for more than 10 meters? Seated Work; 1 - Is the load lifted from below thigh height? 2 - Is the load lifted to above shoulder height? 3 - Is the load lifted at arm's length from the body? 4 - Does the handler have to twist significantly to the side? 5 - Is the load heavier than 5kg? Pushing and Pulling; 1 - Does the pushing and pulling take place below knuckle height? 2 - Does the pushing and pulling take place above shoulder height? 3 - Is the initial or maximum force required to push or pull the load more than 25kg? 4 - Is the continuous force required to keep the load in motion more than 10kg?
Note on T23: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a system of proper HSE reporting in place, such as; all work-related incidents including near misses, injuries, illnesses, property damage, environmental incidents, security events and motor vehicle incidents, using proper protocol followed? 2 - Is the HSE incidents, accident, near misses, unsafe acts/conditions and dangerous occurrences are being reporting in timely manner and in the approved company format? 3 - Are the workers informed, trained in reporting all near misses, unsafe acts/conditions to the appropriate authority or line of manager? 4 - Is the Weekly / Monthly HSE Statistics data, including (leading & lagging) indicators, reviewed by the senior management?
Note on C24: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: CHECKS; 1 - Plant guarding is in place and in good condition to prevent injury from parts disintegrating or failing 2 - Access and egress is in good condition, hand holds, ladder etc. are sound and in place 3 - Operator's seat and controls are in good condition and all safety devices (limiters and indicators) are labelled and fully operational. 4 - Operator's manual / instructions supplied by the manufacturer of the plant are available in the plant. 5 - Hazards with the use of the plant are identified, i.e. Safe working limits on batters, operator safety instructions etc., are displayed clearly in the cabin of the plant for operator reference. I.E. PLANT SPECIFIC RISK ASSESSMENT. 6 - Hazard controls, i.e. seat belts must be worn and hearing protection must be worn, caution/danger signs (counter weight slewing area, excavators and cranes) etc. are displayed in the cabin or on the plant in a position relevant to the hazard. 7 - Operator cabin/work platform access is clean and free of debris, loose tools, equipment, grease oil and is in an orderly condition. 8 - Plant is clean and free from oil leaks and oil build up. 9 - Plant Pre Start inspection is complete and a record of the inspection will be provided at commencement on the site. 10 - Certification of operator / proof of competency. 11 - Operational Noise Level - Statement of conforming emission level. 12 - Plant has no areas of excessive wear or damage. Mobile plant required to have; 1 - Plant is fitted with a Roll Over Protection Structure (R.O.P.S.) and operator restraint. 2 - Plant is fitted with a front horn and reversing beeper. 3 - Plant is fitted with a rotating or flashing amber beacon. Plant used to lift Material and equipment; Backhoes, excavators, cranes and loaders used as crane from designed lifting points. The Safe Working Load of the plant item is displayed on the plant as: EITHER; A Crane Chart supplied by the manufacturer specific to the plant item in the cabin of the plant for operator reference OR; The Safe Working Load of the equipment on the boom of the loader bucket and of the dipper arm of excavators - a combination of both is required for backhoes e.g. SWL 1.2ton. Personal Lifting Equipment - (Cherry Pickers, boom lift and elevated platform) 1 - Safety Working Load is displayed on work bucket / platform. 2 - Fully body harnesses and lanyards are to be provided for personnel using the equipment. 3 - Safety Instruction for the operation of the equipment is clearly displayed in the work bucket / platform. 4 - The supplier have provided training for personnel using the platform in the safe use of the equipment
Note on T24: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Do all personnel have the correct information, instruction and training according to their role and responsibilities? 2 - Is the contractor promoting awareness of company standards and regulations among their employees on a regular basis, or when it is necessary? 3 - Do all personnel have completed basic relevant awareness training, such as; Fire Awareness Training, Heat Stress awareness Training, Safety Signs and Color Code awareness Training, Environmental Awareness Training, Using Fire Extinguisher Awareness Training, Emergency reporting Awareness Training, Unsafe Act/Conditions reporting awareness training, Evacuation Procedure Awareness Training?
Note on C25: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Crane Inspected 2 - Operator certified 3 - Lift Plan approved 4 - PTW obtained 5 - lifting equipment is suitable for the use it is being put to, marked with safe working load, properly maintained and inspected, and receives a periodic thorough examination. 6 - Are all members of the lifting operations team including the Appointed Person, Crane Drivers and Slingers / Signalers / Banksmen will be competent and have such practical and theoretical knowledge and experience as is necessary to carry out their duties. 7 - Bank man is available and certified 8 - The crane operator have a practical and theoretical knowledge of lifting operations 9 - Lifting operations will be undertaken by a minimum of three competent people the crane operator, slinger / signaler (slinger and signaler can be one person) / banks man / flagman (banks man and flagmen can be one person) and Supervisor 10 - Certification of Lifting Equipment / Lifting Gear / Lifting Devices 11 - Lifting plan prepared/approved/communicated 12 - Lifting gear (Chain sling, shackle, webbing sling, lifting clamps etc.) / devices (Chain block, Winch, Monorail etc.) are checked, inspected & tagged - ( size, length, dia, width, SWL,Condition & defects. 13 - All lifting equipment / gears have valid test certificates and are in good condition.
Note on T25: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there process of SBO for leadership to identify and reinforce safe work practices/behaviors? 2 - Is there process of SBO for leadership to identify and improve on at-risk practices? 3 - Is there process of SBO for leadership to identify and improve on practices, conditions, controls, and compliance that eliminate or reduce hazards? 4 - Is there a process of SBO for leadership to make positive, corrective, cooperative, collaborative feedback/recommendations? 5 - Is there a training program for BBST, that how to identify critical safety behavior and how to provide feedback and the number of personnel trained. 6 - Is there a program for the leadership to carry out SBO once a month or twice (depends project scope of work), and record available?

## HSE-Stat
Safety Statistics
Category | Item |  | This Week | This Month | Year to Date | Cumulative
Category | Total Hours Worked |  | 34740 | 104220 | 809664 | 874722 |  |  | 64 | 64
| Safe Hours Worked |  | 34740 | 104220 | 809664 | 874722 |  |  |  | 0
Reactive | LTI |  | 0 | 0 | 0 | 0
| MTC (Healed w/o Disability) |  | 0 | 0 | 0 | 0
| MTC (Healed w/ Disability) |  | 0 | 0 | 0 | 0
| Near Miss |  | 0 | 0 | 0 | 0
| First Aid Cases |  | 0 | 0 | 0 | 0
| Fatality |  | 0 | 0 | 0 | 0
| Fire Incident Cases |  | 0 | 0 | 0 | 0
| Vehicle Incident |  | 0 | 0 | 0 | 0
| Property Damages |  | 0 | 0 | 0 | 0
Proactive | Induction Training |  | 7 | 69 | 114(571) | 148(895)
| No.of Internal Training |  | 1 (6) | 3 (11) | 6(29) | 14(104)
| No.of Internal Audit |  | 0 | 1 | 4 | 4
| No. of Toolbox Talks |  | 3(355) | 3(648) | (43(3442) | 56(8671)
| Safety Awards/Incentives |  | 0 | 0 | 1 | 2
[7 empty] | Category | Item |  | This Week | This Month | Year to Date | Cumulative
Consultant Safety Inspection (Weekly Basis) | [6 empty] | Overall Average | 92.25%
Week Number | Date of Audit | Date Issued | Numbers Of Comments | Overall Score | Date Closed | Closure Duration | This Week Score | 92.86%
Week-1 | 2025-11-25 | 2025-11-25 | 15 | 81.25%
Week-2 | 2025-12-02 | 2025-12-02 | 11 | 86.25%
Week-3 | 2025-12-09 | 2025-12-09 | 9 | 89.29%
Week-4 | 2025-12-16 | 2025-12-16 | 8 | 90.48%
Week-5 | 2025-12-23 | 2025-12-23 | 7 | 91.67%
Week-6 | 2025-12-30 | 2025-12-30 | 7 | 91.67%
Week-7 | 2026-01-06 | 2026-01-06 | 7 | 91.67%
Week-8 | 2026-01-13 | 2026-01-13 | 6 | 92.86%
Week-9 | 2026-01-20 | 2026-01-20 | 6 | 92.86%
Week-10 | 2026-01-27 | 2026-01-27 | 5 | 94.05%
Week-11 | 2026-02-03 | 2026-02-03 | 5 | 94.05%
Week-12 | 2026-02-10 | 2026-02-10 | 5 | 94.05%
Week-13 | 2026-02-17 | 2026-02-17 | 6 | 92.86%
Week-14 | 2026-02-24 | 2026-02-24 | 7 | 91.67%
Week-15 | 2026-03-03 | 2026-03-03 | 7 | 91.67%
Week-16 | 2026-03-10 | 2026-03-10 | 7 | 91.67%
Week-17 | 2026-03-17 | 2026-03-17 | 6 | 92.86%
Week-18 | 2026-03-31 | 2026-03-31 | 6 | 92.86%
Week-19 | 2026-04-07 | 2026-04-07 | 6 | 92.86%
Week-20 | 2026-04-14 | 2026-04-14 | 6 | 92.86%
Week-21 | 2026-04-21 | 2026-04-21 | 6 | 92.86%
Week-22 | 2026-04-28 | 2026-04-28 | 6 | 92.86%
Week-23 | 2026-05-05 | 2026-05-05 | 6 | 92.86%
Week-24 | 2026-05-12 | 2026-05-12 | 6 | 92.86%
Week-25 | 2026-05-19 | 2026-05-19 | 6 | 92.86%
Week-26 | 2026-06-02 | 2026-06-02 | 6 | 92.86%
Week-27 | 2026-06-09 | 2026-06-09 | 6 | 92.86%
Week-28 | 2026-06-16 | 2026-06-16 | 6 | 92.86%
Week-29 | 2026-06-23 | 2026-06-23 | 6 | 92.86%
Week-30 | 2026-06-30 | 2026-06-30 | 6 | 92.86%
Week-31 | 2026-07-07 | 2026-07-07 | 6 | 92.86%
Week-32 | 2026-07-14 | 2026-07-14 | 6 | 92.86%
Week-33 | 2026-07-21 | 2026-07-21 | 6 | 92.86%
Week-34 | 2026-07-28 | 2026-07-28 | 6 | 92.86%
Week-35 | 2026-08-04 | 2026-08-04 | 6 | 92.86%
Week-36 | 2026-08-11 | 2026-08-11 | 6 | 92.86%
Week-37 | 2026-08-18 | 2026-08-18 | 6 | 92.86%
Week-38 | 2026-08-25 | 2026-08-25 | 6 | 92.86%
Week-39 | 2026-09-01 | 2026-09-01 | 6 | 92.86%
Week-40 | 2026-09-08 | 2026-09-08 | 6 | 92.86%
Week-41 | 2026-09-15 | 2026-09-15 | 6 | 92.86%
Week-42 | 2026-09-22 | 2026-09-22 | 6 | 92.86%
Week-43 | 2026-09-29 | 2026-09-29 | 6 | 92.86%
Week-44 | 2026-10-06 | 2026-10-06 | 6 | 92.86%
Week-45 | 2026-10-13 | 2026-10-13 | 6 | 92.86%
Week-46 | 2026-10-20 | 2026-10-20 | 6 | 92.86%
Week-47
Week-48
Week-49
Week-50
Week-51
Week-52
Week-53
Week-54
Week-55
Week-56
Week-57
Week-58
Week-59
Week-60
Week-61
Week-62
Week-63
Week-64
Week-65
Week-66
Week-67
Week-68
Week-69
Week-70
Week-71
Week-72
Week-73
Week-74
Week-75

## Major Quantities
BOQ Number | Description of Item | Total Quantity | Unit of Measurement | Plan To Date | Actual To Date | Remaining Total | Variance | Variance % | Notices | Perf. %
B1.1.31 23 19.01 | Surface Dewatering | 1 | Unit | 1 | 1 | 0 | 0 | 0% |  | 100% | Actual EW | Plan EW
B1.1.31 23 16.01 | All Excavation | 853395 | m³ | 853395 | 825820.73 | 27574.27 | -27574.27 | -3.231% |  | 96.77% | 93.46% | 100%
B1.1.31 23 23.01 | All Backfilling | 1481028.01 | m³ | 1481028.01 | 1356040.32 | 124987.69 | -124987.69 | -8.439% |  | 91.56%
B1.2.32 11 26.01 | Asphalt (Base+Wearing) | 64334 | m³ | 55840.97 | 25855.83 | 38478.17 | -29985.14 | -46.61% |  | 40.19%
33 31 00 | Sew. Pipes | 7567.08 | Lm | 2.01 | 6773.83 | 793.25 | 6771.82 | 89.49% |  | 89.52%
33 05 13 | Sew. Manholes Dia. 1200mm | 135.99 | Unit | 135.99 | 131.22 | 4.77 | -4.77 | -3.508% |  | 96.49%
33 42 11 | Storm Pipes | 14821.15 | Lm | 14344.67 | 13913.95 | 907.2 | -430.72 | -2.906% |  | 93.88%
33 05 13 | Storm Manholes | 160.01 | Unit | 151.01 | 146.02 | 13.99 | -4.99 | -3.119% |  | 91.26%
33 05 63 | Catch Basins | 337.99 | Unit | 313.73 | 280.46 | 57.53 | -33.27 | -9.843% |  | 82.98%
33 14 11 | Potable Pipes | 7213.99 | Lm | 7159.48 | 5677.44 | 1536.55 | -1482.04 | -20.54% |  | 78.7%
33 14 13 | Fire Fighting Pipes | 6354.52 | Lm | 6087.41 | 5750.51 | 604.01 | -336.9 | -5.302% |  | 90.49%
33 14 13 | TSE Pipes | 57419.14 | Lm | 57419.14 | 7736.72 | 49682.42 | -49682.42 | -86.53% |  | 13.47%
B2.33 71 49.23 | MV Cables | 12559 | Lm | 11560.18 | 5124.77 | 7434.23 | -6435.41 | -51.24% |  | 40.81%
B2 33 73 00.01 | Unit Substation 13.8/0.4 K V, 500kVA | 3 | Unit | 1.76 | 0 | 3 | -1.76 | -58.67% |  | 0%
B2 33 73 00.02 | RMU, 13.8KV | 3 | Unit | 2.87 | 0 | 3 | -2.87 | -95.67% |  | 0%
B2.33 71 00 02 | LV Cables | 14369.96 | Lm | 12005.9 | 683.44 | 13686.52 | -11322.46 | -78.79% |  | 4.756%
33 71 00 01 | SL Cable | 21524.99 | Lm | 12180.33 | 3207.05 | 18317.94 | -8973.28 | -41.69% |  | 14.9%
33 71 16 | SL Poles | 564.99 | Unit | 385.87 | 247.28 | 317.71 | -138.59 | -24.53% |  | 43.77%
33 81 26.01 | Telecom Ducts | 11057.03 | Lm | 7520.29 | 2357.76 | 8699.27 | -5162.53 | -46.69% |  | 21.32%
Bill 3.2 | Pump Station | 1 | Unit | 69.68% | 26.96% | 73.04% | -42.73% | -42.73% |  | 26.96%
Bill 5.1 | Sewerage Lift Station | 1 | Unit | 83.36% | 41.1% | 58.9% | -42.26% | -42.26% |  | 41.1%

## Risk Register
Department: | [8 empty] | Status Date:
Program | [8 empty] | 2026-10-20
Project: |  |  | Development of Infrastructure for phase 1 of the Logistics area at the 2nd Industrial City in Dammam
Project No.: |  |  | DAM2-02-009
Project Location: |  |  | 2nd Industrial City in Dammam
[16 empty] | Before Treatment | [10 empty] | Post Treatment
Risk Data | [5 empty] | Category |  |  | Risk Description |  |  | Risk Control Dates |  | Risk Manageability | Risk Proximity | Most Likely |  |  | Risk Owner | Risk Response & Treatment Action |  |  |  | Treatment Control Dates |  |  | Most Likely |  |  | Treatment Status
Risk ID | Region | Section / Group | City | Project ID | Risk Status | T/O/I | Internal/External | Category | Cause / Source | Risk | Consequence / Effect | Identified | Closed |  |  | Liklihood | Impact | Risk Score |  | Risk Response Strategy | Treatment Action | Treatment Acton Description | Treatment Action Owner | Start | Due | Closed | Liklihood | Impact | Risk Score
Rsk-01 | Eastern | Eastern | 2nd Industrial City in Dammam | DAM2-01-029 | Open | Threat | Internal | Design / Planning | قلة عدد العمالة والمعدات و توقف مقاول الباطن | Slow Production | Can't Achieve MODON Goals | 2026-04-01 |  | Moderate | Overdue | Medium | Medium |  | Contractor | Terminate | Mitigate | Increase the no. of manpower & equipment - transfer from another projects | Contractor | 2026-02-10 | 2026-04-17 |  | High | High |  | Open
Rsk-02 | Eastern | Eastern | 3rd Industrial City in Dammam | DAM2-01-029 | Escalate | Issue | Internal | Resources / Finance | تأخر أعمال العبارة بالطريق الشرياني | Delay in material installation /construction | Delay in construction | 2026-06-01 |  | Moderate | Overdue | Medium | Medium |  | Contractor | Enhance/ Exploit | Mitigate | Delivery Schedule to be provided and committed with | Contractor | 2026-02-16 |  |  | High | High |  | Open
Rsk-04 | Eastern | Eastern | 6th Industrial City in Dammam | DAM2-01-029 | Open | Issue | Internal | Interface / Communication | ضرورة الانتهاء من تنفيذ الشبكات لتحقيق جاهزية الموقع وبدء أعمال الطرق | Slow work sequence, Delay in Dry Networks | Can't commit with planned dates for fulfilling box culvert | 2026-06-01 |  | Hard | Med Term | Medium | Medium |  | Contractor | Treat | Mitigate | Crashing - Increasing manpower & equipment | Contractor | 2026-03-23 |  |  | High | High |  | Open
NOTES:
Risk Status: 1.Open, 2.Closed, or 3.Realized
T/O/I: 1.Threat, 2.Opportunity, or 3.Issue
Category (select 1):
1. Political
2. Legal, Regulatory, Compliance
3. Funding, Finance, Budget
4. Management, Governance, Policies, KPI, Performance
5. Human Resources | [21 empty] | `
6. Stakeholders, Authorities, Approvals, Permits
7. Requirements, Specifications, Scope, Procurement, Contract
8. Process, Tools, Technique, Technology
9. Design, Engineering
10. Construction, Execution
11. Testing, Commissioning, Handover
12. Operation, Maintenance
Risk Description (add all 3):
1. Source/Cause
2. Event = Threat, Opportunity, or Issue
3. Consequence/Effect
Risk Response Strategy for Threats: 1.Terminate, 2.Tolerate, 3.Transfer, or 4.Treat
Risk Response Strategy for Opportunities: 1.Ignore, 2.Share, or 3.Enhance/Exploit
Treatment Action: 1.Mitigate, 2.Control, or 3.Fall Back
Treatment Status: 1.Unapproved, 2.Active, or 3.Closed
Risk Level/Score: Likelihood x Highest Impact (Safety, Cost, Schedule, Environment, Quality, or Reputation. See Risk Scoring Matrix tab)

## CCO
CONTRACT CHANGE ORDER (CCO)
CCO No. | Date Added | Description of Change | Status | SR | Sch Impact (Months) | Date Approved | Duration (days)

## Invoice Log
Weekly Progress Report - Invoice Log | [31 empty] | Y
Project Value | [8 empty] | Payment Status | [7 empty] | Invoices Summary | [9 empty] | Average Invoices durations |  |  |  |  | N
Original Contract Value |  |  | 198906162.61 |  | O&M Value |  | 0 | EAC | Advance Payment % |  | 0% |  | Advance Payment (SAR) |  | 0 |  | No of Submitted Invoices |  | 7 |  | Submitted Invoices (SAR) |  | 62889673.529 |  | Submiited Invoice Peroid | 2026-09-15 | CM / PgM Average Approval duration |  | 1 | Average Invoice Value | 8984239.0756
Revised Contract Value |  | 21100000 | 198906162.61 | EAC | Revised O&M Value |  | 0 | #REF! | Retention % |  | 0% |  | Retention (SAR) |  | 0 |  | No of Approved Invoices (CM) |  | 7 |  | Approved Invoices (CM) (SAR) |  | 62889673.529 |  |  |  | MODON PM & Accounts Average Approval duration |  | #DIV/0!
Estimate At Completion Value |  | 20900000 | 198906162.61 | #REF! | Submitted Invoices (Gross Value) |  | 62889673.529 |  | Penalties and deduction % |  | 0.05254% |  | AP Recovery (SAR) |  | 0 |  | No of Approved Invoices (PM) |  | 0 |  | Approved Invoices (PM) (SAR) |  | 0 |  | Invoice Submitted Compared to Contract Value | 31.62% | Payments Average Duration |  | #DIV/0!
Potential Changes |  | 200000 | 0 |  | Total Deduction |  | -104500 |  | Penalties and deduction (SAR) |  | -104500 |  | Retention Cumulative (SAR) |  | 0 |  | No of Paid Invoices |  | 0 |  | Paid Invoices (SAR) |  | 0 |  |  |  | Invoices Average total Duration
Invoice Reference |  |  |  | Invoice Value |  |  |  |  | Period Covered |  | CM / PgM Approval Timeline |  |  |  | Modon PM & Accounts Approval | [6 empty] | Payment Status |  |  |  |  | Total Invoice Duration | Remarks
# | Invoice No. | Doc Control reference | Submittal Rev. # | Gross Value | AP Recovery | Retention | Deduction / Penalties | Amount (net) + VAT 15% | Start Date | End Date | Date to CM / PgM | CM / PgM Approval (Yes/No) | CM / PgM Reply Date | Days Elapsed | Date to PM | PM Approval (Yes/No) | PM Reply Date | Date to Accounts | Accounts Approval (Yes/No) | Accounts Approval Date | Days Elapsed | Date Paid | Amount Paid | Paid % | Payment Period (d) | Amount Pending
1 | 1 | DAM2-02-09-SAJ-TS9-1-GEN-DSF-041 | 0 | 3437652.2 | 0 | 0 | -104500 | 3848800.03 | 2025-07-30 | 2025-11-30 | 2025-12-02 | Y | 2025-12-02 | 0
2 | 2 | DAM2-02-09-SAJ-TS9-1-GEN-DSF-045 | 0 | 5352442.12 | 0 | 0 | 0 | 6155308.438 | 2025-12-01 | 2025-12-15 | 2025-12-17 | Y | 2025-12-18 | 1
3 | 3 | DAM2-02-09-SAJ-TS9-1-GEN-DSF-049 | 0 | 10988940.12 | 0 | 0 | 0 | 12637281.138 | 2025-12-16 | 2026-01-25 | 2026-01-27 | Y | 2026-01-28 | 1
4 | 4 | DAM2-02-09-SAJ-TS9-1-GEN-DSF-056-02 | 2 | 12998014 | 0 | 0 | 0 | 14947716.1 | 2026-01-26 | 2026-03-31 | 2026-04-27 | Y | 2026-04-27 | 0
5 | 5 | DAM2-02-09-SAJ-TS9-1-GEN-DSF-067-00 | 0 | 9370944.56 | 0 | 0 | 0 | 10776586.244 | 2026-04-01 | 2026-06-23 | 2026-06-25 | Y | 2026-06-25 | 0
6 | 6 | DAM2-02-09-SAJ-TS9-1-GEN-DSF-074-00 | 0 | 8014146.053 | 0 | 0 | 0 | 9216267.961 | 2026-06-24 | 2026-07-12 | 2026-08-08 | Y | 2026-08-08 | 0
7 | 7 | DAM2-02-09-SAJ-TS9-1-GEN-DSF-084 | 0 | 12727534.476 | 0 | 0 | 0 | 14636664.6474 | 2026-07-13 | 2026-09-15 | 2026-09-30 | Y | 2026-10-05 | 5
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
|  |  | TOTAL | 62889673.529 | 0 | 0 | -104500 | 72218624.5583 | [17 empty] | 0
Formulas:
Payment Status = [End Date, row above]+1
End Date = [Payment Status]+14
CM / PgM Approval Timeline = [End Date]+2
CM / PgM Reply Date = [CM / PgM Approval Timeline]+1
CM / PgM Reply Date = [CM / PgM Approval Timeline]
Note on I3: Without O&M Cost
Note on D4: Without O&M Cost
Note on E4: Without O&M Cost

## Procurement
|  |  | DAM2-02-009 |  |  | Procurement Log - Long / Short Lead Items | [16 empty] | 2026-10-20
SR. NO. | Project ID | ACT # in P6 | Item Description | Discipline | (Long \Short) Lead Items | BOQ. No. | Unit | Quantity | Proc. Qty | Planed P.O Date | Date of Pur. Order Issued | Purchase Order No. | Supplier | Supplier Phone | Method of Shipping | Start Manufacturing Date | Required on Job | Es.D.A. to Site | Acual.D.A. to Site | Lead Time | Approval Status | Completion Rate | Remarks | Delivery Qty
1 | DAM2-01-029 | B2.337126 04 | Office KWH meter | Electrical | LL | B2.337126 04 | EA | 1 | 1 | 2026-02-01 | Not Issue | NA | Effective Power | Taha 0555590882 | Trucks | 2026-02-20 | 2026-06-04 |  | 0 |  | B | 0% |  | 0
2 | DAM2-01-029 | B2.337126 04 | Main Guard House KWH meter | Electrical | LL | B2.337126 04 | EA | 1 | 1 | 2026-02-07 | 30.11.25 | NA | Effective Power | Taha 0555590882 | Trucks | 30.11.25 | 2026-05-06 |  | 0 |  | B | 0% |  | 0
3 | DAM2-01-029 | B2.337126 04 | Guard Rooms KWH meter | Electrical | LL | B2.337126 04 | EA | 14 | 14 | 2026-01-01 | 2025-11-23 | Jc/026Dm/25 | Siemens Limited AGU | Mohmoud 0539124686 | Trucks | 2025-11-23 | 2026-06-30 |  | 0 |  | B | 0% |  | 0
4 | DAM2-01-029 | B2.337126 04 | PW Station KWH meter | Electrical | LL | B2.337126 04 | EA | 1 | 1 | 2025-10-24 | 2025-11-23 | Jc/027Dm/25 | Siemens Limited AGU | Basil Najjar 0138924503 Mahmoud Hassan 0539124686 | Trucks | 2025-11-23 | 2026-07-06 |  | 0 |  | B | 0% |  | 0
5 | DAM2-01-029 | B2.337126 04 | TSE Station KWH meter | Electrical | LL | B2.337126 04 | EA | 1 | 1 | 2026-02-07 | 2025-11-30 | DAM-251229 | Saudi Co. fo Lighting Fixtures (SACLF) | Ayman 0510546706 | Trucks | 2025-11-30 | 2026-05-09 |  | 320 |  | B | 32000% |  | 320
6 | DAM2-01-029 | B2.337126 04 | Sewage lift Station KWH meter | Electrical | LL | B2.337126 04 | EA | 1 | 1 | 2026-02-07 | 2025-11-27 | DAM-251228 | Jeddah Cable | Amjad 0561792045 | Trucks | 2025-11-27 | 2026-05-19 |  | 0 |  | B | 0% |  | 0
7 | DAM2-01-029 | B2.337100 02 | 4x300mm2/ AL/XLPE/PVC | Electrical | LL | B2.337100 02 | LM | 50 | 50 | 2026-02-07 | 2025-11-30 | DAM-251229 | SLC/Philips | Ayman 0510546706 | Trucks | 2025-11-30 | 2026-05-03 |  | 0 |  | B | 0% |  | 0
8 | DAM2-01-029 | B2.337100 02 | 4x185mm2/ AL/XLPE/PVC | Electrical | LL | B2.337100 02 | LM | 1200 | 1200 | 2026-02-15 | Not Issue | NA | SLC/Philips | Bassam Imam 0500246975 | Trucks | 2026-02-03 | 2026-05-03 |  | 0 |  | B | 0% |  | 0
9 | DAM2-01-029 | B2.337100 02 | 4x70mm2/ AL/XLPE/PVC | Electrical | LL | B2.337100 02 | LM | 3400 | 3400 | 2026-01-10 | 2025-11-27 | DAM-251228 | Jeddah Cable | Amjad 0561792045 | Trucks | 2025-11-27 | 2026-02-23 |  | 0 |  | B | 0% |  | 0
10 | DAM2-01-029 | B2.337126 01 | Low Voltage Distribution Pillars | Electrical | LL | B2.337126 01 | EA | 7 | 7 | 2026-02-20 | Not Issue | NA | Khreji ABB | Ahmad | Trucks | 2026-02-01 | 2026-02-14 |  | 0 |  | B | 0% |  | 0
11 | DAM2-01-029 | New item | Irrigattion control panel | Electrical | LL | New item | EA | 1 | 1 | 2026-01-20 | 20.12.25 | Jc/019Dm/25 | Schneider-MOTS | Muhamad Zubair 0508195967 | Trucks | 2026-01-13 | 2026-06-13 |  | 0 |  | B | 0% |  | 0
12 | DAM2-01-029 | New item | UPS 5KVA for Sewage lift station(Industrial UPS) | Electrical | LL | New item | EA | 1 | 1 | 2025-12-30 | 10.01.26 | DAM-251231 | Al-Ojaimi Factory | Hashim 0558092903 | Trucks | 2026-01-21 | 2026-03-07 |  | 0 |  | B | 0% |  | 0
13 | DAM2-01-029 | New item | DB UPS for Sewage lift station | Electrical | LL | New item | EA | 1 | 1 | 2025-12-30 | 20.12.25 | Jc/019Dm/25 | Schneider-MOTS | Muhamad Zubair 0508195967 | Trucks | 2026-01-21 | 2026-03-07 |  | 0 |  | B | 0% |  | 0
14 | DAM2-01-029 | New item | UPS 5KVA for Portable water pump station(Industrial UPS) | Electrical | LL | New item | EA | 1 | 1 | 2026-01-15 | 20.12.25 | Jc/019Dm/25 | Schneider-MOTS | Muhamad Zubair 0508195967 | Trucks | 2026-04-19 | 2026-06-18 |  | 0 |  | B | 0% |  | 0
15 | DAM2-01-029 | New item | DB UPS for Portable water pump station | Electrical | LL | New item | EA | 1 | 1 | 2025-12-30 | 10.01.26 | DAM-251231 | Al-Ojaimi Factory | Hashim 0558092903 | Trucks | 2026-01-01 | 2026-03-01 |  | 0 |  | B | 0% |  | 0
16 | DAM2-01-029 | New item | 630Amp MCCB for fire water pump no.1 | Electrical | LL | New item | EA | 2 | 2 | 2026-02-20 | 2025-12-15 | DAM-151229 | Jeddah Cable | Amjad 0561792045 | Trucks | 27.11.25 | 2026-01-30 |  | 12600 |  | B | 630000% |  | 12600
17 | DAM2-01-029 | New item | VFD for fire water Pump no.1 | Electrical | LL | New item | EA | 1 | 1 | 2026-03-03 | 2025-11-08 | Jc/020Dm/25 | SFFECO | Ahmad Gaballah 050521925 | Trucks | 2025-11-08 | 2026-06-01 |  | 0 |  | B | 0% |  | 0
18 | DAM2-01-029 | New item | 20A, 3P, 60Hz Isolator/disconnect switches IP65 | Electrical | LL | New item | EA | 1 | 1 | 2025-11-08 | 45969 | Jc/017Dm/25 | JADF | Azeem alasawey 0542110025 | Trucks | 2026-04-19 | 2026-05-04 |  | 0 |  | B | 0% |  | 0
19 | DAM2-01-029 | New item | Telecom Main Antena at guard room 1 | Electrical | LL | New item | EA | 1 | 1 | 2025-11-24 | 46042 | PO UCC-C6-046 | SPS | Rami Hamouri 055 999 4033 | Trucks | 2025-12-09 | 2026-01-08 |  | 61 |  | B | 6100% |  | 61
20 | DAM2-01-029 | New item | DC-GR Cabinet | Electrical | LL | New item | EA | 1 | 1 | 2025-11-08 | 45969 | PO UCC-C6-004 | SFFECO | Repy 0533723157 | Trucks | 2025-11-08 | 2026-01-17 |  | 0 |  | B | 0% |  | 0
21 | DAM2-01-029 | New item | Telecom Antena guard room2 | Electrical | LL | New item | EA | 3 | 3 | 2025-11-08 | 45969 | Jc/018Dm/25 | KSB | Khalid Al Shemy 58 260 9298 | Trucks | 2025-11-08 | 2026-06-13 |  | 0 |  | B | 0% |  | 0
22 | DAM2-01-029 | New item | DC-GR1-Cabinet | Electrical | LL | New item | EA | 3 | 3 | 2025-11-08 | 45969 | Jc/020Dm/25 | SFFECO | Ahmed Gaballah 0505219256 | Trucks | 2025-11-08 | 2026-06-13 |  | 0 |  | B | 0% |  | 0
23 | DAM2-01-029 | New item | Clorination -Indutrial socket outlet,1P,with grounding,Suuply & apply including cable,conduit,T&C as per IFC and Project Specs. | Electrical | LL | New item | EA | 6 | 6 | 2025-11-08 | 45969 | Jc/018Dm/25 | KSB | Khalid Al Shemy 58 260 9298 | Trucks | 2025-11-08 | 2026-06-24 |  | 0 |  | B | 0% |  | 0
24 | DAM2-01-029 | New item | Clorination-20A dissconnect switch/Isolator ,Suuply & apply including cable,conduit,T&C as per IFC and Project Specs. | Electrical | LL | New item |  | 2 | 2 | 2026-03-26 | Not Issue | NA | Power Technics | Omar 0558665562 | Trucks | 2026-04-25 | 2026-06-24 |  | 0 |  | B | 0% |  | 0
25 | DAM2-01-029 | New item | Clorination-Pendant Lights 35W Normal IP65,4200Lumens ,Suuply & apply including cable,conduit,T&C as per IFC and Project Specs. | Electrical | LL | New item | EA | 3 | 3 | 2026-04-04 | Not Issue | NA | AL SAGHEER | Ali Al Fadel 0559339753 | Trucks | 2026-05-04 | 2026-06-18 |  | 0 |  | B | 0% |  | 0
26 | DAM2-01-029 | New item | Clorination-Pendant Lights 35W Emergency IP65 with 3 Hrs kit,4200lumens,Suuply & apply including cable,conduit,T&C as per IFC and Project Specs. | Electrical | LL | New item | EA | 1 | 1 | 2026-02-18 | Not Issue | NA | Environmental System | Haytham 0565412827 | Trucks | 2026-02-20 | 2026-07-05 |  | 0 |  | B | 0% |  | 0
27 | DAM2-01-029 | New item | Wall mounted Bulk head lights 15W IP65,Suuply & apply including cable,conduit,T&C as per IFC and Project Specs. | Electrical | LL | New item | EA | 2 | 2 | 2026-02-18 | Not Issue | NA | Arabian Scope | Waheed 0555830075 | Trucks | 2026-02-02 | 2026-07-05 |  | 0 |  | B | 0% |  | 0
28 | DAM2-01-029 | New item | Clorination -Grounding system ,Suuply & apply including cable,conduit,T&C as per IFC and Project Specs. | Electrical | LL | New item | EA | 1 | 1 | 2026-02-18 | Not Issue | NA | Arabian Scope | Waheed 0555830075 | Trucks | 2026-06-05 | 2026-07-05 |  | 0 |  | B | 0% |  | 0
29 | DAM2-01-029 | New item | Clorination-4x10mm2 CU/XLPE/PVC+1CX100MM2 CU/PVCDB-CL ,Suuply & apply including cable,conduit,T&C as per IFC and Project Specs. | Electrical | LL | New item | LM | 45 | 45 | 2026-01-17 | 29.01.26 | Jc/015Dm/26 | Riyadh Crane | Ahmed Qasim 0594602092 | Trucks | 2026-02-16 | 2026-04-02 |  | 0 |  | B | 0% |  | 0
30 | DAM2-01-029 | New item | DI pipe 350 mm, Pn16 | Mechanical | LL | New item | EA | 12 | 12 | 2026-02-25 | 28.12.25 | Jc/028Dm/25 | Environmental System | Haytham 0565412827 | Trucks | 2026-03-27 | 2026-04-26 |  | 0 |  | B | 0% |  | 0
31 | DAM2-01-029 | New item | DI Pudle flange 350 mm, Pn16 | Mechanical | LL | New item | EA | 2 | 2 | 2025-10-09 | 2025-11-08 | Jc/019Dm/25 | MOTS | Muhammad zubair 0508195967 | Trucks | 2025-11-08 | 2026-06-10 |  | 0 |  | B | 0% |  | 0
32 | DAM2-01-029 | New item | DI pipe 200 mm, Pn16 | Mechanical | LL | New item | EA | 24 | 24 | 2025-11-30 | 2025-11-23 | Jc/025Dm/25 | CUMMINS | Mahmoud 0540488952 | Trucks | 2025-11-23 | 2026-06-04 |  | 0 |  | B | 0% |  | 0
33 | DAM2-01-029 | New item | DI Pudle flange,200mm, Pn16 | Mechanical | LL | New item | EA | 3 | 3 | 2025-10-24 | 2025-11-23 | Jc/027Dm/25 | Siemens Limited AGU | Basil 0507972833 | Trucks | 2025-11-23 | 2026-04-13 |  | 0 |  | B | 0% |  | 0
34 | DAM2-01-029 | New item | DI gate valve,200mm, Pn16 | Mechanical | SL | New item | EA | 2 | 2 | 2026-03-05 | Not Issue | NA | Road Technology | Soheel 597055344 | Trucks | 2026-03-15 | 2026-04-15 |  | 0 |  | B | 0% |  | 0
35 | DAM2-01-029 | New item | DI float valve,200mm, Pn16 | Mechanical | SL | New item | EA | 2 | 2 | 2026-03-10 | Not Issue | NA | AL Kamline | Hani 506668043 | Trucks | 2026-03-10 | 2026-04-20 |  | 0 |  | B | 0% |  | 0
36 | DAM2-01-029 | New item | DI Pudle flange,150 mm, Pn16 | Mechanical | SL | New item | EA | 4 | 4 | 2025-10-15 | 2025-10-01 | PO 001 | SAJCO | Ahmad 0550750285 | Trucks | 2025-10-01 | 2025-11-02 |  | 0 |  | B | 0% |  | 0
37 | DAM2-01-029 | New item | DI gate valve150mm, Pn16 | Mechanical | SL | New item | EA | 2 | 2 | 2025-10-15 | 2025-10-01 | PO 002 | SAJCO | Ahmad 0550750285 | Trucks | 2025-10-01 | 2025-11-16 |  | 0 |  | B | 0% |  | 0
38 | DAM2-01-029 | New item | DI pipe100 mm, Pn16 | Mechanical | SL | New item | EA | 12 | 12 | 2025-10-15 | 2025-10-01 | PO 003 | SAJCO | Ahmad 0550750285 | Trucks | 2025-10-01 | 2025-10-19 |  | 0 |  | B | 11041667% |  | 1325000
39 | DAM2-01-029 | New item | DI Pudle flange,100 mm, Pn16 | Mechanical | SL | New item | EA | 2 | 2 | 2025-10-20 | 2025-11-18 | PO 004 | SAJCO | Mahmoud 0504467488 | Trucks | 2026-03-10 | 2026-03-20 |  | 0 |  | B | 0% |  | 0
40 | DAM2-01-029 | New item | vent pipe galvanized 100 mm | Mechanical | SL | New item | EA | 12 | 12 | 2025-10-20 | 2025-11-18 | PO 004 | SAJCO | Mahmoud 0504467488 | Trucks | 2026-03-10 | 2026-03-20 |  | 0 |  | B | 0% |  | 0
41 | DAM2-01-029 | New item | scupper roof drain 110 mm | Mechanical | SL | New item | EA | 8 | 8 | 2026-01-15 | 31.01.26 | PO 010 | Riyadh Kingdom | Eyad 0545515566 | Trucks | 2026-02-01 | 2026-02-15 |  | 0 |  | B | 0% |  | 0
42 | DAM2-01-029 | New item | 40Amp Disconnect Switch for Crane(4P IP65) | Electrical | SL | New item | EA | 0 | 0 | 2026-01-15 | 31.01.26 | PO 010 | Riyadh Kingdom | Eyad 0545515566 | Trucks | 2026-02-01 | 2026-02-15 |  | 0 |  | B | #DIV/0! |  | 0
43 | DAM2-01-029 | New item | 40Amp Disconnect Switch for penstock(4P IP65) | Electrical | SL | New item | EA | 0 | 0 | 2026-01-15 | 05.02.26 | PO 011 | Riyadh Kingdom | Eyad 0545515566 | Trucks | 2026-04-01 | 2026-04-21 |  | 0 |  | B | #DIV/0! |  | 0
44 | DAM2-01-029 | New item | 40Amp Disconnect Switch for Order(4P IP65) Contol Unit | Electrical | SL | New item | EA | 0 | 0 | 2026-02-15 | Not Issue | NA | NEXUS | Hasan 564632788 | Trucks | 2026-03-10 | 2026-04-09 |  | 0 |  | B | #DIV/0! |  | 0
45 | DAM2-01-029 | New item | 30Amp Disconnect Switch Bar screen(4P IP65) | Electrical | SL | New item | EA | 0 | 0 | 2026-01-20 | 29.01.26 | PO 011 | SAJCO | Ahmad 0550750285 | Trucks | 2026-03-10 | 2026-04-09 |  | 0 |  | B | #DIV/0! |  | 0
46 | DAM2-01-029 | New item | 30Amp Disconnect Switch for Fuel pump control Panel(4P IP65) | Electrical | SL | New item | EA | 0 | 0 | 2025-12-30 | 2026-01-18 | PO 006 | Saudi Benaa | Muhammad Ghalib 550112470 | Trucks | 2026-01-04 | 2026-01-04 |  | 0 |  | B | #DIV/0! |  | 0
47 | DAM2-01-029 | New item | 3 KW - one Local Control Panel for two pumps(IP-65) | Electrical | SL | New item | EA | 0 | 0 | 2025-12-30 | 2026-01-15 | PO 007 | AL Faisal Al Rajhi | Mohamed Shaikh 534913166 | Trucks | 2026-01-25 | 2026-02-04 |  | 0 |  | B | #DIV/0! |  | 0
48 | DAM2-01-029 | New item | 630Amp MCCB with IP65 inclosure | Electrical | SL | New item | EA | 0 | 0 | 2025-12-27 | Not Issue | PO 012 | Riyadh Kingdom AL Manarateen | AHMED IBRAHIM 500165534 | Trucks | 2026-01-15 | 2026-01-04 |  | 0 |  | B | #DIV/0! |  | 0
49 | DAM2-01-029 | New item | 260kw-Local Control Panel for fire water pump -IP65) | Electrical | SL | New item | EA | 0 | 0 | 2025-12-27 | Not Issue | NA | Isam Kabbani | Mamoon 538477569 | Trucks | 2026-01-01 | 2026-01-04 |  | 0 |  | B | #DIV/0! |  | 0
50 | DAM2-01-029 | New item | 260KW VFD for fire water Pump( IP54) | Electrical | SL | New item | EA | 0 | 0 | 2026-02-26 | Not Issue | NA | Art International | Ahmad Khaled 54 408 2100 | Trucks | 2026-02-26 | 2026-03-28 |  | 0 |  | B | #DIV/0! |  | 0
51 | DAM2-01-029 | New item | 260 KW-Local Control Panel for fire water pump( IP65) | Electrical | SL | New item | EA | 0 | 0 | 2026-02-26 | Not Issue | NA | Art International | Ahmad Khaled 54 408 2100 | Trucks | 2026-02-26 | 2026-03-28 |  | 0 |  | B | #DIV/0! |  | 0
52 | DAM2-01-029 | New item | 40Amp MCCB for Jockey pump | Electrical | SL | New item | EA | 0 | 0 | 2026-02-10 | Not Issue | NA | Art International | Ahmad Khaled 54 408 2100 | Trucks | 2026-01-31 | 2026-03-02 |  | 0 |  | B | #DIV/0! |  | 0
53 | DAM2-01-029 | New item | 60 Amp Disconnect Switch for Jocky pump(4P IP65) | Electrical | SL | New item | EA | 0 | 0 | 2026-02-10 | Not Issue | NA | MODERN WOOD WORKS FACTORY | Wael Ahour 558338634 | Trucks | 2026-05-17 | 2026-06-16 |  | 0 |  | B | #DIV/0! |  | 0
54 | DAM2-01-029 | New item | 7 KW-Local Control Panel for Jocky pump( IP65) | Electrical | SL | New item | EA | 0 | 0 | 2026-01-25 | 29.01.26 | PO 009 | BRC | Modar Al Adwani 502787877 | Trucks | 2026-06-06 | 2026-07-21 |  | 0 |  | B | #DIV/0! |  | 0
55 | DAM2-01-029 | New item | 3KW-one Local Control Panel for two fuel pump(IP65) | Electrical | SL | New item | EA | 0 | 0 | 2026-01-25 | 28.01.26 | PO 008 | SAJCO | Ahmad Khaled 54 408 2100 | Trucks | 2026-06-06 | 2026-07-21 |  | 0 |  | B | #DIV/0! |  | 0
56 | DAM2-01-029 | New item | 30Amp disconnect switch for two fuel pumps`s control panel(4P IP65) | Electrical | SL | New item | EA | 0 | 0 | 2026-02-25 | Not Issue | NA | Art International | Ahmad Khaled 54 408 2100 | Trucks | 2026-05-02 | 2026-06-01 |  | 0 |  | B | #DIV/0! |  | 0
57 | DAM2-01-029 | New item | 30Amp Disconnect Switch for Crane(4P IP65) | Electrical | SL | New item | EA | 0 | 0 | 2026-02-01 | Not Issue | NA | Art International | Ahmad Khaled 54 408 2100 | Trucks | 2026-03-10 | 2026-04-06 |  | 0 |  | B | #DIV/0! |  | 0
58 | DAM2-01-029 | New item | 7KW-One Local Control Panel for two submersible pumps( IP65) | Electrical | SL | New item | EA | 0 | 0 | 2025-11-01 | 2025-10-10 | PO UCC-C6-031 | Alyaf | Mohamad Osam 559472880 | Trucks | 2025-11-01 | 2026-11-30 |  | 0 |  | B | #DIV/0! |  | 22200
59 | DAM2-01-029 | New item | Low Volatge cable (1x630mm2)CU/MICA/XPLE/LOSH) for fire pump no.2 | Electrical | SL | New item | LM | 0 | 0 | 2025-11-01 | 2025-11-10 | PO UCC-C6-032 | IKK | Maamoon 506362390 | Trucks | 2026-01-01 | 2026-01-04 |  | 0 |  | B | #DIV/0! |  | 6000
60 | DAM2-01-029 | New item | Low Volatge cable (1x300mm2)CU/MICA/XPLE/LOSH) for fire pump no.2 | Electrical | SL | New item | LM | 0 | 0 | 2026-01-15 | Not Issue | NA | SIKA | Saqr Esbitan 555436939 | Trucks | 2026-02-01 | 2026-02-15 |  | 0 |  | B | #DIV/0! |  | 0
61 | DAM2-01-029 | New item | Low Volatge cable 4x10mm2)CU/MICA/XPLE/LOSH) for Jocky Pump | Electrical | SL | New item | LM | 0 | 0 | 2026-02-01 | Not Issue | NA | Saudi Paint Co Ltd ( Paintco ) | Mohammad 540806806 | Trucks | 2026-03-01 | 2026-03-28 |  | 0 |  | B | #DIV/0! |  | 0
62 | DAM2-01-029 | New item | Low Volatge cable 1x10mm2)CU/MICA/XPLE/LOSH) for Jocky Pump | Electrical | SL | New item | LM | 0 | 0 | 2026-02-01 | Not Issue | NA | Saudi Paint Co Ltd ( Paintco ) | Mohammad 540806806 | Trucks | 2026-03-01 | 2026-03-28 |  | 0 |  | B | #DIV/0! |  | 0
63 | DAM2-01-029 | New item | Draw pit with heavy duty steel cover,size 1400x600x1200mm | Electrical | SL | New item | EA | 0 | 0 | 2026-02-01 | Not Issue | NA | Al Fanar | Turki Al Turki 549991949 | Trucks | 2026-04-01 | 2026-04-14 |  | 0 |  | B | #DIV/0! |  | 0
64 | DAM2-01-029 | New item | Draw pit with heavy duty steel cover,size 1400x600x600mm | Electrical | SL | New item | EA | 0 | 0 | 2026-01-15 | Not Issue | NA | NA | NA | Trucks | 2026-02-15 | 2026-03-02 |  | 0 |  | B | #DIV/0! |  | 0
65 | DAM2-01-029 | Bill:2-337100.02 | Street lighting duct bank | Electrical | SL | Bill:2-337100.02 | LM | 0 | 0 | 2026-01-20 | Not Issue | NA | NA | NA | Trucks | 2026-02-01 | 2026-03-02 |  | 0 |  | B | #DIV/0! |  | 0
66 | DAM2-01-029 | B2.33 7100.01 | LV duct bank | Electrical | SL | B2.33 7100.01 | LM | 0 | 0 | 2026-01-20 | Not Issue | NA | NA | NA | Trucks | 2026-02-01 | 2026-03-02 |  | 0 |  | B | #DIV/0! |  | 0
67 | DAM2-01-029 | B2.33 7100 | MV duct back | Electrical | SL | B2.33 7100 | LM | 0 | 0 | 2026-01-20 | Not Issue | NA | NA | NA | Trucks | 2026-02-01 | 2026-03-02 |  | 0 |  | B | #DIV/0! |  | 0
68 | DAM2-01-029 | Bill:2.1-338126.03 | Telecom duct bank | Electrical | SL | Bill:2.1-338126.03 | LM | 0 | 0 | 2026-01-10 | Not Issue | NA | DCP | Yazan 0532449865 | Trucks | 2026-03-01 | 2026-03-28 |  | 0 |  | B | #DIV/0! |  | 0
69 | DAM2-01-029 | B2.33 7100.02 | MV duct bank(4x150) | Electrical | SL | B2.33 7100.02 | LM | 100 | 100 | 2026-03-05 | Not Issue | NA | NA | NA | Trucks | 2026-05-01 | 2026-07-09 |  | 0 |  | B | 0% |  | 0
70 | DAM2-01-029 | Bill-8 | DB-MGR Panel: 32/100 Ampere, 3P, IP66,60Hz incomer MCCB . For guard room 1 | Electrical | SL | Bill-8 | EA | 1 | 1 | 2025-12-15 | 2026-12-01 | PO 005 | AHMED ALWAN GEN | Mohammad 0549358786 | Trucks | 2026-01-01 | 2026-01-04 |  | 0 |  | B | 0% |  | 0
71 | DAM2-01-029 | Bill-8 | DB-GR Panel: 32/100 Ampere, 3P, IP66,60Hz incomer MCCB .For guard room 2 | Electrical | SL | Bill-8 | EA | 3 | 3 | 2026-03-05 | Not Issue | NA | AL Khreji | Mahmoud 0555219643 | Trucks | 2026-02-05 | 2026-05-04 |  | 0 |  | B | 0% |  | 0
72 | DAM2-01-029 | Bill-8 | 4Cx 6mm2 + 1Cx6mm2 Cu/XLPE/PVC FROM KWHM to DB-MGR For guard room 1 & 2 | Electrical | SL | Bill-8 | EA | 40 | 40 | 20.10.25 | 25.01.26 | DAM-260102 | TARIQ NAGADI | Ahmed Al deeb 0539747328 | Trucks | 2026-01-30 | 2026-03-15 |  | 0 |  | B | 0% |  | 0
73 | DAM2-01-029 | Bill-8 | Conduit and accessories FROM KWHM to DB-MGR For guard room 1 & 2 | Electrical | SL | Bill-8 | EA | 40 | 40 | 2026-01-15 | 01.01.26 | DAM-251230 | KHAM Factory | Mohammad Faraj 0508042050 | Trucks | 2026-02-01 | 2026-03-19 |  | 0 |  | B | 12135% |  | 4854
74 | DAM2-01-029 | Bill-8 | ROUND RECESSED LED 11.5 WATTS, IP20, 230V, 60HZ, 1400 LUMENS, For guard room 1&2 | Electrical | SL | Bill-8 | EA | 14 | 14 | 2026-01-30 | 22.01.26 | DAM-260101 | Alwasail | BEDIER 506404317 | Trucks | 2026-03-01 | 2026-03-19 |  | 0 |  | B | 535714% |  | 75000
75 | DAM2-01-029 | Bill-8 | ROUND RECESSED LED 11.5 WATTS, IP20, 230V, 60HZ, 1400 LUMENS, with 3 hour emergency battery kit For guard room 1 | Electrical | SL | Bill-8 | EA | 2 | 2 | 2026-02-01 | Not Issue | NA | AL Khreji | Mahmoud 0555219643 | Highbed | 2026-03-15 | 2026-04-04 |  | 0 |  | B | 0% |  | 0
76 | DAM2-01-029 | Bill-8 | WALL MOUNTED BULK HEAD OUTDOOR LED 15 WATTS, IP65,230V 60 HZ, For guard room 1&2 | Electrical | SL | Bill-8 | EA | 5 | 5 | 2026-02-20 | 10.01.26 | DAM-100126 | Elsewedy | Amjad 0561792045 | Highbed | 2026-02-20 | 2026-05-05 |  | 0 |  | B | 0% |  | 0
77 | DAM2-01-029 | Bill-8 | ROUND RECESSED LED 11.5 WATTS, IP44, 230V, 60HZ, 1400 LUMENS, For guard room 1 | Electrical | SL | Bill-8 | EA | 2 | 2 | 2026-02-20 | 10.01.26 | DAM-100126 | Elsewedy | Amjad 0561792045 | Highbed | 2026-02-20 | 2026-05-05 |  | 0 |  | B | 0% |  | 0
78 | DAM2-01-029 | Bill-8 | Conduit and accessories for building lifghting circuits | Electrical | SL | Bill-8 | EA | Tech | Tech | 2025-12-25 | 20.01.26 | DAM-260103 | Global Source | Raheeb 555636521 | Trucks | 2025-11-01 | 2025-12-30 |  | 0 |  | B | #VALUE! |  | 86000
79 | DAM2-01-029 | Bill-8 | 3x2.5mm2 Cables & cable Accessories for building ligjhting circuits | Electrical | SL | Bill-8 | EA | Tech | Tech | 2026-02-20 | Not Issue | NA | FURSE | NA | Trucks | 2026-01-15 | 2026-01-30 |  | 0 |  | B | #VALUE! |  | 0
80 | DAM2-01-029 | Bill-8 | 13A SINGLE SWITCH SOCKET OUTLET, For guard room 1&2 | Electrical | SL | Bill-8 | EA | 6 | 6 | 2026-03-01 | Not Issue | NA | AL Khreji | Mahmoud 0555219643 | Trucks | 2026-04-03 | 2026-05-03 |  | 0 |  | B | 0% |  | 0
81 | DAM2-01-029 | Bill-8 | 13A DOUBLE SWITCH SOCKET OUTLET, For guard room 1&2 | Electrical | SL | Bill-8 | EA | 22 | 22 | 2026-01-10 | 25.01.26 | DAM-260102 | TARIQ NAGADI | Ahmed Al deeb 0539747328 | Trucks | 2026-01-20 | 2026-02-19 |  | 88 |  | B | 400% |  | 88
82 | DAM2-01-029 | Bill-8 | 13A SPUR OUTLET, For guard room 1&2 | Electrical | SL | Bill-8 | EA | 6 | 6 | 2026-02-01 | Not Issue | NA | NA | NA | Trucks | 2026-04-02 | 2026-05-02 |  | 0 |  | B | 0% |  | 0
83 | DAM2-01-029 | Bill-8 | 20A DOUBLE POLE SWITCH, IP65, For guard room 1 | Electrical | SL | Bill-8 | EA | 3 | 3 | 2026-03-10 | Not Issue | NA | NA | NA | Trucks | 2026-03-13 | 2026-03-28 |  | 0 |  | B | 0% |  | 0
84 | DAM2-01-029 | Bill-8 | Conduit and accessories for building wiring devices circuits | Electrical | SL | Bill-8 | EA | Tech | Tech | 2026-03-09 | Not Issue | NA | NA | NA | Trucks | 2026-04-17 | 2026-05-02 |  | 0 |  | B | #VALUE! |  | 0
85 | DAM2-01-029 | Bill-8 | 3x4mm2 Cables & cable Accessories for building wiring devices circuits | Electrical | SL | Bill-8 | EA | Tech | Tech | 2026-03-09 | Not Issue | NA | NA | NA | Trucks | 2026-03-24 | 2026-04-08 |  | 0 |  | B | #VALUE! |  | 0
86 | DAM2-01-029 | Bill-8 | Supply, install and test the following grounding and lightning system including ground wires, ground rods, inspection pits, terminations, bonding/clamping, civil works and all materials and accessories required to complete the work according to specification, drawing and standards and materials as per approved samples; all materials should be SASO certified. guard room 1&2 | Electrical | SL | Bill-8 | EA | 4 | 4 | 2026-07-04 | Not Issue | NA | NA | NA | Trucks | 2026-07-19 | 2026-08-03 |  | 0 |  | B | 0% |  | 0
87 | DAM2-01-029 | Bill-8 | 120 mm2 BCW for grounding & Lightining protection | Electrical | SL | Bill-8 | EA | 4 | 4 | 2025-10-12 | 2025-11-15 | PO UCC-C6-002 | KHAM Factory | Mohammad Faraj 0508042050 | Highbed | 2025-10-27 | 2025-11-11 |  | 0 |  | B | 61500% |  | 2460
88 | DAM2-01-029 | Bill-8 | 70mm2 BCW for grounding & Lightining protection | Electrical | SL | Bill-8 | EA | 4 | 4 | 01.03.26 | Not Issue | NA | Al Muneef | Ahmad Hasson 0550901644 | Highbed | 2026-03-15 | 2026-03-30 |  | 0 |  | B | 0% |  | 0
89 | DAM2-01-029 | Bill-8 | Rod 19mmx2.4mtrfor grounding & Lightining protection | Electrical | SL | Bill-8 | EA | 4 | 4 | 2025-10-04 | 2025-11-10 | PO UCC-C6-006 | WASAEL,UNION | BEDIER 506404317 | Highbed | 2025-10-19 | 2025-11-03 |  | 13800 |  | B | 345000% |  | 13800
90 | DAM2-01-029 | Bill-8 | Earth pit 300x300mm for grounding & Lightining protection | Electrical | SL | Bill-8 | EA | 4 | 4 | 2025-11-03 | 2025-11-08 | PO UCC-C6-003 | FUTURE PIPE | Abdul Rasheed 0553177750 | Highbed | 2025-11-18 | 2025-12-03 |  | 10516 |  | B | 262900% |  | 10516
91 | DAM2-01-029 | Bill-8 | Busbar 8way with DS link ffor grounding & Lightining protection | Electrical | SL | Bill-8 | EA | 4 | 4 | 25.11.25 | 2025-11-25 | PO UCC-C6-014 | Global Source | Raheeb 555636521 | Trucks | 2025-11-01 | 2025-11-11 |  | 86730 |  | B | 2168250% |  | 86730
92 | DAM2-01-029 | Bill-8 | 25mm2 x 3mm CU tape & Accessories for grounding & Lightining protection | Electrical | SL | Bill-8 | EA | 4 | 4 | 2026-02-16 | Not Issue | NA | SAUDI FANS | Samir 0502007277 | Trucks | 2026-03-03 | 2026-04-02 |  | 0 |  | B | 0% |  | 0
93 | DAM2-01-029 | Bill-8 | 20A, 1P, 60Hz Isolator/disconnect switches IP65 guard room 1&2 | Electrical | SL | Bill-8 | EA | 6 | 6 | 2025-11-08 | 2025-11-08 | Jc/020Dm/25 | SFFECO | Ahmad Gaballah 050521925 | Trucks | 2025-11-08 | 2026-04-08 |  | 0 |  | B | 0% |  | 0
94 | DAM2-01-029 | Bill-8 | Conduit 25 uPVC for fire Alarm system | Electrical | SL | Bill-8 | LM | Tech | Tech | 2025-11-08 | 2025-11-08 | Jc/020Dm/25 | SFFECO | Ahmad Gaballah 050521925 | Trucks | 2025-11-08 | 2026-07-05 |  | 0 |  | B | #VALUE! |  | 0
95 | DAM2-01-029 | Bill-8 | Cable 2x1.5mm2 or fire Alarm system | Electrical | SL | Bill-8 | LM | Tech | Tech | 2026-03-26 | Not Issue | NA | AL ZAMEL | Mo Rasheed 0594009672 | Trucks | 2026-04-25 | 2026-05-25 |  | 0 |  | B | #VALUE! |  | 0
96 | DAM2-01-029 | Bill-8 | smoke detectorsor fire Alarm system | Electrical | SL | Bill-8 | EA | 3 | 3 | 2026-02-13 | Not Issue | NA | NA | NA | Trucks | 2026-03-15 | 2026-04-14 |  | 0 |  | B | 0% |  | 0
97 | DAM2-01-029 | Bill-8 | Sounder indoor or fire Alarm system | Electrical | SL | Bill-8 | EA | 1 | 1 | 2026-03-17 | Not Issue | NA | NA | NA | Trucks | 2026-04-16 | 2026-05-16 |  | 0 |  | B | 0% |  | 0
98 | DAM2-01-029 | Bill-8 | FACP Panel with 2 LOOPS ADDRESABLE TYPE COMPLETE WITH BATTERY CHARGER. POWER SUPPLY UNIT. LCD PRINTER KEY BOARD AND AUTOMATIC TELEPHONE DIALER | Electrical | SL | Bill-8 | EA | 1 | 1 | 15.03.26 | Not Issue | NA | NA | NA | Trucks | 2026-03-22 | 2026-04-21 |  | 0 |  | B | 0% |  | 0
99 | DAM2-01-029 | Bill-8 | Sounder out door or fire Alarm system | Electrical | SL | Bill-8 | EA | 2 | 2 | 08.11.25 | 08.12.25 | UCC-C6-020 | TARIQ NAGADI | Ahmed Al-Deeb 539747328 | Highbed | 2025-11-17 | 2025-12-17 |  | 202 |  | B | 10100% |  | 202
100 | DAM2-01-029 | Bill-8 | Printer or fire Alarm system | Electrical | SL | Bill-8 | EA | 1 | 1 | 2026-02-15 | Not Issue | NA | UKC | Hany 0569441706 | Trucks | 2026-02-16 | 2026-03-17 |  | 0 |  | B | 0% |  | 0
101 | DAM2-01-029 | Bill-8 | Conduit & Accessories for DTA & voice system | Electrical | SL | Bill-8 | LM | Tech | Tech | 2026-02-10 | Not Issue | NA | Middle East Rinbird - Hiner | Samir 0509355864 | Trucks | 2026-02-20 | 2026-02-13 |  | 0 |  | B | #VALUE! |  | 0
102 | DAM2-01-029 | Bill-8 | CAT6 cables for DTA & voice system | Electrical | SL | Bill-8 | LM | Tech | Tech | 2026-02-10 | Not Issue | NA | Middle East Rinbird - Hiner | Samir 0509355864 | Trucks | 2026-02-20 | 2026-02-13 |  | 0 |  | B | #VALUE! |  | 0
103 | DAM2-01-029 | Bill-8 | Data Cabinet including all devices 12U for guard room 1 | Electrical | SL | Bill-8 | EA | 1 | 1 | 2026-02-10 | Not Issue | NA | Middle East Rinbird - Hiner | Samir 0509355864 | Trucks | 2026-02-20 | 2026-02-13 |  | 0 |  | B | 0% |  | 0
104 | DAM2-01-029 | Bill-8 | Data/ voice RJ45 outlet include CAT6A cable for guard room 1 | Electrical | SL | Bill-8 | EA | 14 | 14 | 2026-05-29 | Not Issue | NA | NA | NA | Trucks | 2026-06-28 | 2026-07-13 |  | 0 |  | B | 0% |  | 0
105 | DAM2-01-029 | Bill-8 | RJ45 connector include CAT6A cable for security cameras for guard room 1&2 | Electrical | SL | Bill-8 | EA | 12 | 12 | 2026-02-11 | Not Issue | NA | NA | NA | Trucks | 2026-03-13 | 2026-03-28 |  | 0 |  | B | 0% |  | 0
106 | DAM2-01-029 | Bill-8 | 50 inch screen for guard room 1 | Electrical | SL | Bill-8 | EA | 4 | 4 | 2026-03-18 | Not Issue | NA | NA | NA | Trucks | 2026-04-17 | 2026-05-02 |  | 0 |  | B | 0% |  | 0
107 | DAM2-01-029 | Bill-8 | PC workstation for guard room 1 | Mechanical | SL | Bill-8 | EA | 2 | 2 | 2026-03-18 | Not Issue | NA | NA | NA | Trucks | 2026-04-17 | 2026-05-02 |  | 0 |  | B | 0% |  | 0
108 | DAM2-01-029 | Bill-8 | DX wall mounted Split/AC For guard room type 1&2 | Mechanical | SL | Bill-8 | EA | 7 | 7 | 2026-03-29 | Not Issue | NA | NA | NA | Trucks | 2026-04-28 | 2026-05-13 |  | 0 |  | B | 0% |  | 0
|  | Bill-8 | EF-01 Exhaust axial fan air flow capacity = 50 l/s | Mechanical |  | Bill-8 | EA
|  | Bill-8 | uPVC pipes with diameter 160mm. | Mechanical |  | Bill-8 | EA
|  | Bill-8 | uPVC pipes with diameter 110mm. | Mechanical |  | Bill-8 | EA
|  | Bill-8 | uPVC pipes with diameter 75mm. | Mechanical |  | Bill-8 | EA
|  | Bill-8 | uPVC pipes with diameter 50mm. | Mechanical |  | Bill-8 | EA
|  | Bill-8 | PPR pipes with diameter 32mm. | Mechanical |  | Bill-8 | EA
|  | Bill-8 | PPR pipes with diameter 25mm. | Mechanical |  | Bill-8 | EA
|  | Bill-8 | PPR pipes with diameter 20mm. | Mechanical |  | Bill-8 | EA
|  | Bill-8 | Scupper with diameter 110mm | Mechanical |  | Bill-8 | EA
|  | Bill-8 | Clean out with diameter 110mm | Mechanical |  | Bill-8 | EA
|  | Bill-8 | Floor drain | Mechanical |  | Bill-8 | EA
|  | Bill-8 | Manhole, dimensions 600mmX600mm | Mechanical |  | Bill-8 | EA
|  | Bill-8 | Electrical Water Heater 50L capacity | Mechanical |  | Bill-8 | EA
|  | Bill-8 | Shower | Mechanical |  | Bill-8 | EA
|  | Bill-8 | Toilet | Mechanical |  | Bill-8 | EA
|  | Bill-8 | Semi pedestal sink | Mechanical |  | Bill-8 | EA
|  | Bill-8 | CO2 fire extinguishers | Mechanical |  | Bill-8 | EA
|  | Bill-8 | Powder fire extinguishers For guard room type 1&2 | Mechanical |  | Bill-8 | EA
|  | Bill-3.2 | Trench drain, dimensions 18000mmX300mmX300mm | Mechanical |  | Bill-3.2 | EA
|  | Bill-3.2 | Scupper with diameter 110mm | Mechanical |  | Bill-3.2 | EA
|  | Bill-3.2 | PPR pipes with diameter 25mm. | Mechanical |  | Bill-3.2 | LM
|  | Bill-3.2 | PPR pipes with diameter 32mm. | Mechanical |  | Bill-3.2 | LM
|  | Bill-3.2 | PPR pipes with diameter 40mm. | Mechanical |  | Bill-3.2 | LM
|  | Bill-3.2 | Hose bibb | Mechanical |  | Bill-3.2 | EA
|  | Bill-5.1 | Supply, test and commissioning for screening container constructed from steel with thickness of 4 mm for sides and cover and 6 mm for base. Dimensions of container shall be at least 80 cm x 80 cm x 80 cm.Container shall be epoxy coated (sewega water resistant) and equipped with four roller bearing wheels, safety brakes, rear swivel caster, lifting lugs, cover & cover mechanism, drain hole, manual handle, and all fittings and accessories. Price includes supply, on-site Workmanship, all necessary fittings, accessories and miscellaneous materials for connections and support, and all required components for safe operation as per the supplier recommendations, Testing & Commissioning for hand-over in fully operational conditions. All materials and painting shall be SASO certified. | Mechanical |  | Bill-5.1 | EA
|  | Bill-5.1 | Scupper with diameter 110mm | Mechanical |  | Bill-5.1 | EA
|  | Bill-3.2 | Scupper with diameter 110mm | Mechanical |  | Bill-3.2 | EA
|  | Bill-5.1 | Ø110mm UNDER GROUND pipes | Mechanical |  | Bill-5.1 | LM

## Issues
[8 empty] | 2026-10-20 | Status | Responsibility
[9 empty] | Open | Contractor
[9 empty] | Closed | Consultant
Modon
Third Party
Other
Issue Log
Issue No | Date Identified | Issue Description | Responsibility | Action Taken | Current Status | Expected/Actual Closure | Duration Elapsed
1 | 2026-04-01 | قلة عدد العمالة والمعدات و توقف مقاول الباطن | Contractor | جاري اسناد جزء من المشروع لمقاول آخر و جاري توفير عمالة من الشركة لاستكمال الاعمال المتبقية حيث ان عدد العمالة الحالي 304 والمعدات 184 معدة والمضخات الى 30 مضخة نزح ,و وجوب استمرار زيادة العمالة والمعدات لتحقيق مستهدفات مدن | Open | 2026-05-01 | 202
2 | 2026-06-01 | تأخر أعمال العبارة بالطريق الشرياني | Contractor | جاري الانتهاء من الحدادة ل 16 فواصل وصب قاعدة لعدد 03 فاصل تم حفر 14 و جاري 03 فواصل أخرى | Open | 2026-07-01 | 141
3 | 2026-06-01 | ضرورة الانتهاء من تنفيذ الشبكات لتحقيق جاهزية الموقع وبدء أعمال الطرق | Other | تم استبعاد مقاول الباطن يوناسكو و سحب اعتماده لعدم وفاءه بمستهدفات مدن و على المقاول العمل بشكل مباشر على الشبكات او تقديم مقاول باطن للاعتماد | Open | 2026-07-01 | 141
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
Formulas:
Expected/Actual Closure = [Date Identified]+30

## Manpower
Head-Count ( Non Manual)
MONTHS | 2025-07-30 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31
Plan - Monthly | 1 | 9 | 14 | 27 | 48 | 51 | 46 | 56 | 54 | 63 | 46 | 53 | 48 | 45 | 38 | 35 | 35 | 6 | 4
Planned - Cumulative | 1 | 10 | 24 | 51 | 99 | 150 | 196 | 252 | 306 | 369 | 415 | 468 | 516 | 561 | 599 | 634 | 669 | 675 | 679
Actual - Monthly | 8 | 14 | 25 | 36 | 46 | 48 | 49 | 52 | 52 | 56 | 56 | 57 | 57 | 57 | 57 | 57
Actual Cumulative | 8 | 22 | 47 | 83 | 129 | 177 | 226 | 278 | 330 | 386 | 442 | 499 | 556 | 613 | 670 | 727
Forecast - Monthly | [16 empty] | 117 | 82 | 19 | 0 | 0 | 0 | 0
Saudi Monthly - Actual | 1 | 1 | 3 | 4 | 10 | 10 | 10 | 14 | 15 | 15 | 15 | 16 | 13 | 13 | 13 | 13
Head-Count (Manual)
MONTHS | 2025-07-30 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31
Plan - Monthly | 1 | 12 | 18 | 35 | 85 | 116 | 205 | 203 | 244 | 248 | 263 | 258 | 243 | 391 | 142 | 78 | 78 | 24 | 15
Planned - Cumulative | 1 | 13 | 31 | 66 | 151 | 267 | 472 | 675 | 919 | 1167 | 1430 | 1688 | 1931 | 2322 | 2464 | 2542 | 2620 | 2644 | 2659
Actual - Monthly | 5 | 31 | 65 | 80 | 93 | 146 | 151 | 172 | 217 | 305 | 364 | 408 | 420 | 499 | 519 | 537
Actual Cumulative | 5 | 36 | 101 | 181 | 274 | 420 | 571 | 743 | 960 | 1265 | 1629 | 2037 | 2457 | 2956 | 3475 | 4012
Forecast - Monthly | [16 empty] | 560 | 324 | 155 | 0 | 0 | 0 | 0
Saudi - Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Head-Count (Non-Manual) | [24 empty] | Month | 2026-10-31 | 2026-11-30
Planned | Actual |  | Variance |  | Forecast Next Month |  | Saudi Staff
35 | 57 |  | 22 |  | 117 |  | 4
Head-Count (Manual) | [10 empty] | Man Power by Trade
Planned | Actual |  | Variance |  | Forecast Next Month |  | Saudi Staff |  |  |  | Key Trade |  | General Labor |  | Carpenter |  | Plumber |  | Operator | Steelfixer | Mason | Surveyor | Others | Total
78 | 537 |  | 459 |  | 560 |  | 0 |  |  |  | Plan |  | 120 |  | 15 |  | 16 |  | 125 | 17 | 14 | 14 | 70 | 391
[11 empty] | Actual |  | 119 |  | 68 |  | 33 |  | 237 | 44 | 10 | 9 | 17 | 537
Equipment
MONTHS | 2025-07-30 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31
Plan - Monthly | 1 | 12 | 18 | 35 | 61 | 95 | 110 | 132 | 128 | 150 | 166 | 170 | 219 | 220 | 215 | 166 | 97 | 38 | 15
Planned - Cumulative | 1 | 13 | 31 | 66 | 127 | 222 | 332 | 464 | 592 | 742 | 908 | 1078 | 1297 | 1517 | 1732 | 1898 | 1995 | 2033 | 2048
Actual - Monthly | 2 | 13 | 27 | 37 | 42 | 87 | 91 | 99 | 147 | 204 | 243 | 245 | 246 | 305 | 324 | 326
Actual Cumulative | 2 | 15 | 42 | 79 | 121 | 208 | 299 | 398 | 545 | 749 | 992 | 1237 | 1483 | 1788 | 2112 | 2438
Forecast - Monthly | [16 empty] | 285 | 128 | 129 | 129 | 110 | 77 | 23
Equipment Count
Planned | Actual |  | Idle |  | Variance |  | Forecast Next Month
166 | 326 |  |  |  | 160 |  | 285
Type | Excavator | Fork lift | Loader | Dumper | W.Tanker | Grader | Dumper |  | Dozer |  | Grader |  | Other |  | Total
Plan | 22 |  | 8 |  | 14 |  | 28 |  | 8 |  | 8 |  | 62 |  | 150
Actual | 23 |  | 13 |  | 18 |  | 163 |  | 10 |  | 8 |  | 91 |  | 326
Idle | [14 empty] | 0
Formulas:
Steelfixer = EOMONTH([Operator],1)
Mason = EOMONTH([Steelfixer],1)
Surveyor = EOMONTH([Mason],1)
Others = EOMONTH([Surveyor],1)

## Milestones
Milestones for Development of Infrastructure for phase 1 of the Logistics area at the 2nd Industrial City in Dammam
Item No. | Milestones | Original (Baseline) | Latest | Forecast |  | Days Change
| Contract Duration Current Contract Weeks : 64 of 78 | 77.7143 | 78 | 82 |  | -28 | 64 | 78
1 | Award Date | 2025-06-30 | 2025-06-30 | 2025-06-30 | A | 0
2 | Contract Sign Date | 2025-07-14 | 2025-07-14 | 2025-07-14 | A | 0
3 | Site Handover Date | 2025-07-30 | 2025-07-30 | 2025-07-30 | A | 0
4 | Complete Mobilization | 2025-08-30 | 2025-08-30 | 2025-08-30 | A | 0
5 | Complete Submittals and place order for all long-lead items. | 2026-09-24 | 2026-09-24 | 2026-10-24 | F | -30
6 | Complete delivery of all equipment and materials | 2026-12-03 | 2026-12-03 | 2026-10-24 | F | 40
7 | Complete Earthworks | 2026-09-15 | 2026-09-15 | 2026-08-25 | F | 21
8 | Complete all Wet Networks | 2026-11-22 | 2026-11-22 | 2026-12-17 | F | -25
9 | Complete Electrical Works | 2026-11-24 | 2026-11-24 | 2026-12-21 | F | -27
10 | Complete all Works including Testing & Commissioning, Cleanup, Closeout Documentation and Ready for Initial Handover | 2027-01-14 | 2027-01-14 | 2027-02-14 | F | -31
11 | Complete Demobilization | 2027-01-25 | 2027-01-25 | 2027-02-24 | F | -30
12 | Project Handover | 2027-01-29 | 2027-01-29 | 2027-03-01 | F | -31

## Schedule
Primavera P6 Schedule Status | [9 empty] | Data Date | 2026-10-20
Project Activities Overview
Schedule Statistics |  |  |  |  | Active Schedule Activities
Total Act. | Not Started | In Progress | Completed | % | Active | Ahead | On | Behind | Flag
4851 | 1938 | 431 | 2482 | 51.16% | 431 | 10 | 1639 | 202 | 1447
Critical Path Activities |  |  | Free Float Management (Total) |  |  |  | Failed Start Activities
|  |  | Greater Than 14 Days |  | Less Than 14 Days
Last Week | This Week | Diff | Last Week | This Week | Last Week | This Week | Last Week | This Week | Flag
45 | 45 | 0 | 490 | 527 | 2019 | 1840 | 993 | 1047 | -54

## EV-Chart Data
| 198906162.31 |  |  | 198906162.6 | [5 empty] | 0.85
| Baseline Plan |  |  | Revised / Recovery Plan |  |  | Earned Value |  |  | Gross Paid Value |  |  | Forecast |  |  | Actual/Fcst vs Plan
Month | Monthly | Cum | % | Monthly | Cum | % | Monthly | Cum | % | Monthly | Cum | % | Monthly | C um |  | Month | Cum
2025-07-30 |  | 0 | 0% | 579721.05 | 579721.05 | 0.2915% | 0 | 0 | 0% | 0 | 0 | 0% |  |  |  | 0 | 0 |  | Actuals thru previous month
2025-08-31 | 1746054.2 | 1746054.2 | 0.8778% | 2766044.15 | 3345765.2 | 1.682% | 0 | 0 | 0% | 0 | 0 | 0% |  |  |  | -1746054.2 | -1746054.2
2025-09-30 | 2103730.61 | 3849784.81 | 1.935% | 6811937.15 | 10157702.35 | 5.107% | 2830887.23 | 2830887.23 | 1.423% | 0 | 0 | 0% |  |  |  | 727156.62 | 727156.62
2025-10-31 | 5790018.53 | 9639803.34 | 4.846% | 11987993.41 | 22145695.76 | 11.13% | 3803813.22 | 6634700.45 | 3.336% | 0 | 0 | 0% |  |  |  | -1986205.31 | -1986205.31
2025-11-30 | 12262120.42 | 21901923.76 | 11.01% | 11446317.88 | 33592013.64 | 16.89% | 11085138.79 | 17719839.24 | 8.909% | 3437652.2 | 3437652.2 | 1.728% |  |  |  | -1176981.63 | -1176981.63 |  | Forecast current and future months
2025-12-31 | 16490469.29 | 38392393.05 | 19.3% | 10610396.52 | 44202410.16 | 22.22% | 20493922.25 | 38213761.49 | 19.21% | 5352442.12 | 8790094.32 | 4.419% |  |  |  | 4003452.96 | 4003452.96
2026-01-31 | 12394605.78 | 50786998.83 | 25.53% | 10027789.24 | 54230199.4 | 27.26% | 11705192.91 | 49918954.4 | 25.1% | 10988940.12 | 19779034.44 | 9.944% |  |  |  | -689412.87 | -689412.87
2026-02-28 | 12567500.3 | 63354499.13 | 31.85% | 6795310 | 61025509.4 | 30.68% | 12510524.53 | 62429478.93 | 31.39% | 0 | 19779034.44 | 9.944% |  |  |  | -56975.77 | -56975.77
2026-03-31 | 14157471.26 | 77511970.39 | 38.97% | 3552179.39 | 64577688.79 | 32.47% | 10442953.13 | 72872432.06 | 36.64% | 12998014 | 32777048.44 | 16.48% |  |  |  | -3714518.13 | -3714518.13
2026-04-30 | 28432891.55 | 105944861.94 | 53.26% | 4794256.99 | 69371945.78 | 34.88% | 4767643.19 | 77640075.25 | 39.03% | 0 | 32777048.44 | 16.48% |  |  |  | -23665248.36 | -23665248.36
2026-05-31 | 21535457.71 | 127480319.65 | 64.09% | 5849004.94 | 75220950.72 | 37.82% | 4100259.61 | 81740334.86 | 41.09% | 0 | 32777048.44 | 16.48% |  |  |  | -17435198.1 | -17435198.1
2026-06-30 | 9620303.88 | 137100623.53 | 68.93% | 11489123.35 | 86710074.07 | 43.59% | 7041317.44 | 88781652.3 | 50.34% | 9370944.56 | 42147993 | 21.19% |  |  |  | -2578986.44 | -2578986.44
2026-07-31 | 16928223.72 | 154028847.25 | 77.44% | 50155238.78 | 136865312.85 | 68.81% | 3707171.27 | 92488823.57 | 46.5% | 8014146.053 | 50162139.053 | 25.22% |  |  |  | -13221052.45 | -13221052.45
2026-08-31 | 9444688.8 | 163473536.05 | 82.19% | 35429818.45 | 172295131.3 | 86.62% | 3857301.42 | 96346124.99 | 53.14% | 0 | 50162139.053 | 25.22% |  |  |  | -5587387.38 | -5587387.38
2026-09-30 | 7884821.72 | 171358357.77 | 86.15% | 18032992.66 | 190328123.96 | 95.69% | 2218615.57 | 98564740.56 | 49.55% | 12727534.476 | 62889673.529 | 31.62% |  |  |  | -5666206.15 | -5666206.15
2026-10-31 | 9480512.03 | 180838869.8 | 90.92% | 8578038.64 | 198906162.6 | 100% | 9772671.69 | 108337412.25 | 54.47% | 0 | 62889673.529 |  | 9772671.69 | 108337412.25 | 54.47% | 292159.66 | 292159.66
2026-11-30 | 16074507.37 | 196913377.17 | 99% |  | 198906162.6 | 100% |  |  |  | 0 | 62889673.529 |  | 53890800.1542 | 162228212.4042 | 81.56% | -16074507.37 | -16074507.37
2026-12-31 | 1992785.14 | 198906162.31 | 100% |  | 198906162.6 | 100% |  |  |  | 0 | 62889673.529 |  | 22011615.6233 | 184239828.0275 | 92.63% | -1992785.14 | -1992785.14
2027-01-31 | 0 | 198906162.31 | 100% |  | 198906162.6 | 100% |  |  |  | 0 | 62889673.529 |  | 14666334.5725 | 198906162.6 | 100% | 0 | 0 |  |  | Extended Duration
2027-02-28 | [15 empty] | 0 | 0
2027-03-31 | [15 empty] | 0 | 0
2027-04-30 | [15 empty] | 0 | 0
2027-05-31 | [15 empty] | 0 | 0
2027-06-30 | [15 empty] | 0 | 0
2027-07-31
2027-08-31
2027-09-30
2027-10-31
2027-11-30
2027-12-31
2028-01-31
2028-02-29
UPDATE ONLY YELLOW PORTION FROM PRIMAVERA EXPORT, IF NEEDED, EXTEND YELLOW PORTION BASED ON SCHEDULE.
2986147.75
6786523.94
[5 empty] | 30033627.89 | 247.98 | [5 empty] | 30033627.89 | 0.59503 | 0 | 30033627.89
[5 empty] | 12267189.78 | 3452 | [5 empty] | 12267189.78 | 0.24304 | 0 | 12267189.78
[5 empty] | 8173625.81 | 4549.14 | [5 empty] | 8173625.81 | 0.16194 | 0 | 8173625.81
[6 empty] | 6227.72 | [6 empty] | 0 | 0 | 0
[6 empty] | 10179.24 | [6 empty] | 0 | 0 | 0
[6 empty] | 19067.53 | [6 empty] | 0 | 0 | 0
[6 empty] | 24560.14 | [6 empty] | 0 | 0 | 0
[6 empty] | 32255.25 | [6 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
50474443.48
0
0
| Activity ID | Activity Name | Original Duration | Activity Count | BL Project Start | BL Project Finish | Start | Finish | Budgeted Total Cost | Remaining Total Cost | Activity Status | Schedule % Complete | Performance % Complete | Planned Value Cost | Actual Total Cost | Earned Value Cost | Activity % Complete | Labor Units % Complete | Physical % Complete | Units % Complete | Duration % Complete | Budgeted Labor Units | Planned Value Labor Units | Performance % Complete - Labor Units | Actual Labor Units | Earned Value Labor Units | Spreadsheet Field | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01
| Total |  | 413.32 | 4851 | 2025-07-30 | 2027-01-29 | 30-Jul-25 A | 46447 | 198906162.61 | 9044174918% |  | 0.7066 | 0.5447 | 140538384.62 | 108365544.05 | 10833741225% |  | 57.91% |  | 59.39% | 77.42% | 92023000% | 65417595% | 57.9% | 532494.26 | 532794.64 | Estimate At Completion Cost |  |  | 579721.05 | 2766044.15 | 6811937.15 | 11987993.41 | 11446385.54 | 10615173.94 | 10022944.17 | 6795310 | 3497681 | 4798731.76 | 5853503.33 | 11494863.55 | 13564774.19 | 48097786.52 | 30033627.89 | 12267189.78 | 8173625.81
| Total |  | 413.32 | 4851 | 2025-07-30 | 2027-01-29 | 30-Jul-25 A | 46447 | 198906162.61 | 9044174918% |  | 0.7066 | 0.5447 | 140538384.62 | 108365544.05 | 10833741225% |  | 57.91% |  | 59.39% | 77.42% | 92023000% | 65417595% | 57.9% | 532494.26 | 532794.64 | Cum Estimate At Completion Cost |  |  | 579721.05 | 3345765.2 | 10157702.35 | 22145695.76 | 33592081.3 | 44207255.24 | 54230199.41 | 61025509.41 | 64523190.41 | 69321922.17 | 75175425.49 | 86670289.04 | 100235063.23 | 148332849.76 | 178366477.64 | 190633667.43 | 198807293.24 | 198807293.24 | 198807293.24
| Total |  | 413.32 | 4851 | 2025-07-30 | 2027-01-29 | 30-Jul-25 A | 46447 | 198906162.61 | 9044174918% |  | 0.7066 | 0.5447 | 140538384.62 | 108365544.05 | 10833741225% |  | 57.91% |  | 59.39% | 77.42% | 92023000% | 65417595% | 57.9% | 532494.26 | 532794.64 | Estimate At Completion - Labor Units |  | 138.51 | 2852.79 | 6198.57 | 8830.85 | 18495.84 | 27067.47 | 33980.82 | 31896.76 | 42004.3 | 35271.86 | 37337.9 | 37046.38 | 39378.33 | 98254.04 | 227407.24 | 139592.19 | 110659.63 | 23174.31
| Total |  | 413.32 | 4851 | 2025-07-30 | 2027-01-29 | 30-Jul-25 A | 46447 | 198906162.61 | 9044174918% |  | 0.7066 | 0.5447 | 140538384.62 | 108365544.05 | 10833741225% |  | 57.91% |  | 59.39% | 77.42% | 92023000% | 65417595% | 57.9% | 532494.26 | 532794.64 | Cum Estimate At Completion - Labor Units |  | 138.51 | 2991.3 | 9189.87 | 18020.72 | 36516.56 | 63584.03 | 97564.85 | 129461.61 | 171465.91 | 206737.78 | 244075.68 | 281122.05 | 320500.39 | 418754.43 | 646161.67 | 785753.86 | 896413.49 | 919587.81 | 919587.81 | 919587.81
Formulas:
Month = EOMONTH([Month, row above],1)

## Physical-Chart Data
| 884888 |  |  | 920230
| Baseline Plan |  |  | Revised / Recovery Plan |  |  | Earned Effort % |  |  | Forecast |  |  | Achieved/Fcst vs Plan
Week | Monthly Effort | Cum Effort | Plan Wt.% | Weekly Effort | Cum Effort | Plan Wt.% | Weekly Wt. | Cum Wt. | Achieved Wt.% | Monthly Wt. | Cum Wt. | Wt.% | Weekly Wt. | Cum Wt.
2025-07-30 | 320 | 320 | 0.03616% |  | 0 | 0% | 247.98 | 248 | 0.02803% |  |  |  | -320 | -320 |  | Actuals thru previous month
2025-08-31 | 4000 | 4320 | 0.4882% | 138.51 | 138.51 | 0.01505% | 3452 | 3700 | 0.4181% |  |  |  | -4000 | -4320
2025-09-30 | 6200 | 10520 | 1.189% | 2852.79 | 2991.3 | 0.3251% | 4549.14 | 8249 | 0.9322% |  |  |  | -6200 | -10520
2025-10-31 | 12384 | 22904 | 2.588% | 6198.57 | 9189.87 | 0.9986% | 6227.72 | 14477 | 1.636% |  |  |  | -12384 | -22904
2025-11-30 | 21904 | 44808 | 5.064% | 8830.85 | 18020.72 | 1.958% | 10179.24 | 24656 | 2.786% |  |  |  | -21904 | -44808 |  | Forecast current and future months
2025-12-31 | 53184 | 97992 | 11.07% | 18495.84 | 36516.56 | 3.968% | 19067.53 | 43724 | 4.941% |  |  |  | -53184 | -97992
2026-01-31 | 93880 | 191872 | 21.68% | 27067.47 | 63584.03 | 6.91% | 24560.14 | 68284 | 7.717% |  |  |  | -93880 | -191872
2026-02-28 | 113512 | 305384 | 34.51% | 33980.82 | 97564.85 | 10.6% | 32255.25 | 100539 | 11.36% |  |  |  | -113512 | -305384
2026-03-31 | 110000 | 415384 | 46.94% | 31896.76 | 129461.61 | 14.07% | 37655.25 | 138194 | 15.62% |  |  |  | -110000 | -415384
2026-04-30 | 128872 | 544256 | 61.51% | 42004.3 | 171465.91 | 18.63% | 62937.81 | 201132 | 22.73% |  |  |  | -128872 | -544256
2026-05-31 | 94592 | 638848 | 72.2% | 35368.79 | 206834.7 | 22.48% | 54571.77 | 255704 | 28.9% |  |  |  | -94592 | -638848
2026-06-30 | 66984 | 705832 | 79.77% | 37324.53 | 244159.23 | 26.53% | 61815.25 | 317519 | 37.27% |  |  |  | -66984 | -705832
2026-07-31 | 63176 | 769008 | 86.9% | 37033.01 | 281192.24 | 30.56% | 37627.88 | 355147 | 40.13% |  |  |  | -63176 | -769008
2026-08-31 | 46824 | 815832 | 92.2% | 39364.06 | 320556.3 | 34.83% | 38891.93 | 394039 | 42.75% |  |  |  | -46824 | -815832
2026-09-30 | 28232 | 844064 | 95.39% | 193689.92 | 514246.22 | 55.88% | 45440.35 | 439479 | 49.66% |  |  |  | -28232 | -844064
2026-10-31 | 15464 | 859528 | 97.13% | 212177.6 | 726423.82 | 78.94% | 93315.64 | 532795 | 57.9% | 93315.64 | 532795 | 57.9% | 77852 | -766212
2026-11-30 | 15504 | 875032 | 98.89% | 128409.69 | 854833.51 | 92.89% |  |  |  | 197797.1167 | 730592.1167 | 79.39% | 182293 | -583919
2026-12-31 | 6024 | 881056 | 99.57% | 65396.49 | 920230 | 100% |  |  |  | 156800.7189 | 887392.8356 | 96.43% | 150777 | -433142
2027-01-31 | 3832 | 884888 | 100% |  | 920230 | 100% |  |  |  | 32837.1644 | 920230 | 100% | 29005 | -404137 |  |  | Extended Duration
2027-02-28 | [12 empty] | 0 | -404137
2027-03-31 | [12 empty] | 0 | -404137
2027-04-30 | [12 empty] | 0 | -404137
2027-05-31 | [12 empty] | 0 | -404137
2027-06-30
2027-07-31
2027-08-31
2027-09-30
2027-10-31
2027-11-30
2027-12-31
2028-01-31
2028-02-29
UPDATE ONLY YELLOW PORTION FROM PRIMAVERA EXPORT, IF NEEDED, EXTEND YELLOW PORTION BASED ON SCHEDULE.
|  |  |  | 139592.19 |  |  |  | 139592.19 | 0.51053 | 0 | 139592.19
|  |  |  | 110659.63 |  |  |  | 110659.63 | 0.40471 | 0 | 110659.63
|  |  |  | 23174.31 |  |  |  | 23174.31 | 0.084755 | 0 | 23174.31
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
273426.13
273426.13
0
Activity ID | Activity Name | Original Duration | Activity Count | BL Project Start | BL Project Finish | Start | Finish | Budgeted Total Cost | Remaining Total Cost | Activity Status | Schedule % Complete | Performance % Complete | Planned Value Cost | Actual Total Cost | Earned Value Cost | Activity % Complete | Labor Units % Complete | Physical % Complete | Units % Complete | Duration % Complete | Budgeted Labor Units | Planned Value Labor Units | Performance % Complete - Labor Units | Actual Labor Units | Earned Value Labor Units | Spreadsheet Field | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01
Total |  | 403.32 | 4851 | 45868 | 46416 | 30-Jul-25 A | 46433 | 198906162.61 | 94879033.1 |  | 0.7233 | 0.5149 | 143859912.52 | 104023764.29 | 102415935.07 |  | 53.31% |  | 54.7% | 76.86% | 920230 | 560205.94 | 53.27% | 490238.84 | 490194.97 | Estimate At Completion Cost |  |  | 579721.05 | 2766044.15 | 6811937.15 | 11987993.41 | 11446385.54 | 10615173.94 | 10022944.17 | 6795310 | 3552179.39 | 4794240.05 | 5849011.62 | 11489135.9 | 14159879.55 | 58146865.98 | 22879437.39 | 13719735.61 | 3286802.51
Total |  | 403.32 | 4851 | 45868 | 46416 | 30-Jul-25 A | 46433 | 198906162.61 | 94879033.1 |  | 0.7233 | 0.5149 | 143859912.52 | 104023764.29 | 102415935.07 |  | 53.31% |  | 54.7% | 76.86% | 920230 | 560205.94 | 53.27% | 490238.84 | 490194.97 | Cum Estimate At Completion Cost |  |  | 579721.05 | 3345765.2 | 10157702.35 | 22145695.76 | 33592081.3 | 44207255.24 | 54230199.41 | 61025509.41 | 64577688.8 | 69371928.85 | 75220940.47 | 86710076.37 | 100869955.91 | 159016821.89 | 181896259.27 | 195615994.88 | 198902797.39 | 198902797.39
Total |  | 403.32 | 4851 | 45868 | 46416 | 30-Jul-25 A | 46433 | 198906162.61 | 94879033.1 |  | 0.7233 | 0.5149 | 143859912.52 | 104023764.29 | 102415935.07 |  | 53.31% |  | 54.7% | 76.86% | 920230 | 560205.94 | 53.27% | 490238.84 | 490194.97 | Estimate At Completion - Labor Units |  | 138.51 | 2852.79 | 6198.57 | 8830.85 | 18495.84 | 27067.47 | 33980.82 | 31896.76 | 42004.3 | 35368.79 | 37324.53 | 37033.01 | 39364.45 | 120540.98 | 241930.74 | 123371.28 | 110271.67 | 2932.08
Total |  | 403.32 | 4851 | 45868 | 46416 | 30-Jul-25 A | 46433 | 198906162.61 | 94879033.1 |  | 0.7233 | 0.5149 | 143859912.52 | 104023764.29 | 102415935.07 |  | 53.31% |  | 54.7% | 76.86% | 920230 | 560205.94 | 53.27% | 490238.84 | 490194.97 | Cum Estimate At Completion - Labor Units |  | 138.51 | 2991.3 | 9189.87 | 18020.72 | 36516.56 | 63584.03 | 97564.85 | 129461.61 | 171465.91 | 206834.7 | 244159.24 | 281192.25 | 320556.7 | 441097.69 | 683028.42 | 806399.71 | 916671.37 | 919603.45 | 919603.45
Formulas:
Week = EOMONTH([Week, row above],1)

## Testing
Testing and Commissioning
Item | Planned Start Date | Planned Finish Date | Forecast Start Date | Forecast Finish Date | Actual Start Date | Actual Finish Date | % Completed | Open Comments | Closed Comments
Zone 01 | 2026-11-19 | 2026-12-12 | 08-Sep-26 A | 2027-01-06 | 2026-09-08
Testing & Commissioning for Sewerage Network | 2026-11-19 | 2026-11-26 | 08-Sep-26 A | 2026-12-22 | 2026-09-08 |  | 90%
Testing & Commissioning for Storm Network | 2026-11-19 | 2026-11-26 | 12-Sep-26 A | 2026-12-22 | 2026-09-12 |  | 90%
Testing & Commissioning for Potable Network | 2026-11-19 | 2026-11-28 | 2026-12-14 | 2026-12-22
Testing & Commissioning for Fire Fighting Network | 2026-11-21 | 2026-11-28 | 2026-12-15 | 2026-12-22
Testing & Commissioning for TSE Network | 2026-11-21 | 2026-11-28 | 2026-12-15 | 2026-12-22
Testing & Commissioning for Medium Voltage Network | 2026-11-26 | 2026-12-01 | 2026-12-22 | 2026-12-27
Testing & Commissioning for Low Voltage Network | 2026-12-01 | 2026-12-05 | 2026-12-27 | 2026-12-30
Testing & Commissioning for Telecommunication Network | 2026-12-05 | 2026-12-12 | 2026-12-30 | 2027-01-06
Testing & Commissioning for Street Lighting Network | 2026-11-26 | 2026-12-03 | 2026-12-22 | 2026-12-29
Zone 02 | 2026-11-21 | 2026-12-15 | 2026-12-02 | 2027-01-10
Testing & Commissioning for Sewerage Network | 2026-11-26 | 2026-12-03 | 2026-12-22 | 2026-12-29
Testing & Commissioning for Storm Network | 2026-11-26 | 2026-12-05 | 2026-12-22 | 2026-12-30
Testing & Commissioning for Potable Network | 2026-11-28 | 2026-12-05 | 2026-12-22 | 2026-12-29
Testing & Commissioning for Fire Fighting Network | 2026-11-21 | 2026-11-28 | 2026-12-15 | 2026-12-22
Testing & Commissioning for TSE Network | 2026-11-28 | 2026-12-05 | 2026-12-22 | 2026-12-29
Potable Water Pump Station | 2026-11-28 | 2026-12-01 | 2026-12-02 | 2026-12-19
Testing & Commissioning for PLC System | 2026-11-28 | 2026-12-01 | 2026-12-02 | 2026-12-07
Testing & Commissioning for Instrumentation for Process Systems | 2026-11-28 | 2026-12-01 | 2026-12-02 | 2026-12-07
Testing & Commissioning for Process Control Wiring | 2026-11-28 | 2026-12-01 | 2026-12-14 | 2026-12-19
Testing & Commissioning for Medium Voltage Network | 2026-12-01 | 2026-12-06 | 2026-12-27 | 2026-12-31
Testing & Commissioning for Low Voltage Network | 2026-12-05 | 2026-12-08 | 2026-12-30 | 2027-01-03
Testing & Commissioning for Telecommunication Network | 2026-12-08 | 2026-12-15 | 2027-01-03 | 2027-01-10
Testing & Commissioning for Street Lighting Network | 2026-11-26 | 2026-12-03 | 2026-12-22 | 2026-12-29
Zone 03 | 2026-11-28 | 2026-12-15 | 12-Sep-26 A | 2027-01-10 | 2026-09-12
Testing & Commissioning for Sewerage Network | 2026-12-03 | 2026-12-10 | 13-Sep-26 A | 2026-10-21 | 2026-09-13 |  | 90%
Testing & Commissioning for Storm Network | 2026-11-28 | 2026-12-05 | 12-Sep-26 A | 2026-12-30 | 2026-09-12 |  | 90%
Testing & Commissioning for Potable Network | 2026-11-28 | 2026-12-05 | 2026-12-22 | 2026-12-29
Testing & Commissioning for Fire Fighting Network | 2026-11-28 | 2026-12-01 | 2026-12-22 | 2026-12-26
Testing & Commissioning for TSE Network | 2026-12-05 | 2026-12-13 | 2026-12-29 | 2027-01-06
Sewer Lift Station | 2026-12-02 | 2026-12-08 | 2026-12-22 | 2026-12-29
Testing & Commissioning for PLC System | 2026-12-02 | 2026-12-08 | 2026-12-22 | 2026-12-29
Testing & Commissioning for Process Control Wiring | 2026-12-02 | 2026-12-08 | 2026-12-22 | 2026-12-29
Testing & Commissioning for Instrumentation for Process Systems | 2026-12-02 | 2026-12-08 | 2026-12-22 | 2026-12-29
Testing & Commissioning for Medium Voltage Network | 2026-12-06 | 2026-12-10 | 2026-12-31 | 2027-01-05
Testing & Commissioning for Low Voltage Network | 2026-12-08 | 2026-12-12 | 2027-01-03 | 2027-01-06
Testing & Commissioning for Telecommunication Network | 2026-12-08 | 2026-12-15 | 2027-01-03 | 2027-01-10
Testing & Commissioning for Street Lighting Network | 2026-11-30 | 2026-12-03 | 2026-12-26 | 2026-12-29
Zone 04 | 2026-11-23 | 2026-12-20 | 10-Sep-26 A | 2027-01-13 | 2026-09-10
Testing & Commissioning for Sewerage Network | 2026-12-10 | 2026-12-17 | 10-Sep-26 A | 2026-12-22 | 2026-09-10 |  | 90%
Testing & Commissioning for Storm Network | 2026-11-28 | 2026-12-05 | 28-Sep-26 A | 2026-10-21 | 2026-09-28 |  | 90%
Testing & Commissioning for Potable Network | 2026-11-28 | 2026-12-05 | 2026-12-22 | 2026-12-29
Testing & Commissioning for Fire Fighting Network | 2026-11-23 | 2026-12-01 | 2026-12-17 | 2026-12-26
Testing & Commissioning for TSE Network | 2026-12-13 | 2026-12-20 | 2027-01-06 | 2027-01-13
Testing & Commissioning for Medium Voltage Network | 2026-12-10 | 2026-12-15 | 2027-01-05 | 2027-01-10
Testing & Commissioning for Low Voltage Network | 2026-12-12 | 2026-12-15 | 2027-01-06 | 2027-01-10
Testing & Commissioning for Telecommunication Network | 2026-12-08 | 2026-12-15 | 2027-01-03 | 2027-01-10
Testing & Commissioning for Street Lighting Network | 2026-11-26 | 2026-12-05 | 2026-12-22 | 2026-12-30
Total | 2026-11-19 | 2026-12-20 | 2026-12-02 | 2027-01-13 | 2026-09-08 | 0 | 90% | 0 | 0

## Conclusion ملخص سير الأعمال
تقدم سير المشروع لتطوير البنية التحتية للمرحلة الأولى بالمنطقة اللوجستية بالمدينة الصناعية الثانية بالدمام
معلومات المشروع |  |  |  |  | نطاق المشروع | [5 empty] | موقع المشروع
المقاول | شركة شبه الجزيرة للمقاولات | الاستشاري | شركة إيجيس لإدارة المشاريع |  | البند | الكمية الكلية (م.ط) | الكمية المنفذة (م.ط) | الكمية المتبقية (م.ط) | نسبة المنفذ
تاريخ استلام الموقع | 2025-07-30 | مدة التنفيذ | 18 شهرًا ميلاديًا |  | Sewerage Network | 6146.02 | 5501.7384 | 644.2816 | 89.52%
بداية العقد | من تاريخ استلام الموقع | قيمة العقد (شامل ضريبة القيمة المضافة) | 198,906,162.312 ريال |  | Strom Water Network | 14999.6 | 14081.4771 | 918.1229 | 93.88% |  |  |  | GRADING WORKS | 35878385.3 | 18.04%
نسبة الإنجاز المخطط له | 70.66% | نسبة الإنجاز الفعلي | 54.47% |  | Potable Water Network | 7217 | 5679.8089 | 1537.1911 | 78.7% |  |  |  | ROAD WORKS | 82675562.658 | 41.57%
[5 empty] | Fire Fighting Network | 6268.68 | 5672.8293 | 595.8507 | 90.49% |  |  |  | ELECTRICAL WORKS | 14832965.364 | 7.46%
ملخص جدول الكميات |  |  |  |  | TSE Network | 17678 | 2381.9538 | 15296.0462 | 13.47% |  |  |  | TELECOMMUNICATIONS | 4558897.348 | 2.29%
مكونات المشروع |  | التكلفة (غير شامل ضريبة القيمة المضافة) | النسبة الاجمالية |  | Medium Voltage Network | 12559 | 5124.77 | 7434.23 | 40.81% |  |  |  | POTABLE WATER NETWORK | 1974578.978 | 0.99%
GRADING WORKS |  | 35878385.3 | 18.04% |  | Low Voltage Network | 14370 | 683.44 | 13686.56 | 4.756% |  | تقدم أعمال layout |  | FIREFIGHTING NETWORK | 4850538.007 | 2.44%
ROAD WORKS |  | 82675562.658 | 41.57% |  | Street Lighting Network | 21525 | 3207.0515 | 18317.9485 | 14.9% |  | Sewerage Network | MV Network | POTABLE WATER PUMP STATION | 10874258.28 | 5.47%
ELECTRICAL WORKS |  | 14832965.364 | 7.46% |  | Street Lighting Poles | 565 | 247.28 | 317.72 | 43.77% |  |  |  | TSE NETWORK | 1525335.352 | 0.77%
TELECOMMUNICATIONS |  | 4558897.348 | 2.29% |  | Telecommunication Network | 11001 | 1000 | 10001 | 9.09% |  |  |  | SEWERAGE NETWORK | 5243677.644 | 2.64%
POTABLE WATER NETWORK |  | 1974578.978 | 0.99% |  | Road Works | 64334 | 36244.37 | 28089.63 | 56.34% |  |  |  | SEWAGE LIFT STATION | 4979998.44 | 2.5%
FIREFIGHTING NETWORK |  | 4850538.007 | 2.44% |  | ملخص التوريدات | [7 empty] | STORM WATER DRAINAGE NETWORK | 21853500.776 | 10.99%
POTABLE WATER PUMP STATION |  | 10874258.28 | 5.47% |  | البند | الكمية الكلية (م.ط) | الكمية الموردة (م.ط) | الكمية المتبقية (م.ط) | نسبة التوريد |  |  |  | LANDSCAPE WORK | 9113963.104 | 4.58%
TSE NETWORK |  | 1525335.352 | 0.77% |  | Sewer Pipes | 6256.86 | 6046.41 | 210.45 | 96.64% |  |  |  | GUARD ROOMS | 544501.358 | 0.27%
SEWERAGE NETWORK |  | 5243677.644 | 2.64% |  | Sewer Manholes | 136 | 136 | 0 | 100%
SEWAGE LIFT STATION |  | 4979998.44 | 2.5% |  | Storm Pipes (GRP+UPVC) | 14999.6 | 14999.6 | 0 | 100% |  | Strom Water Network | Street Lighting Network
STORM WATER DRAINAGE NETWORK |  | 21853500.776 | 10.99% |  | Storm Manholes | 163 | 163 | 0 | 100%
LANDSCAPE WORK |  | 9113963.104 | 4.58% |  | Storm Catch Basins | 338 | 338 | 0 | 100%
GUARD ROOMS |  | 544501.358 | 0.27% |  | Potable Pipes (HDPE) | 7217 | 7217 | 0 | 100%
[5 empty] | Firefighting Pipes (HDPE) | 6268.68 | 6268.68 | 0 | 100%
[5 empty] | TSE Pipes (HDPE) | 17678 | 17678 | 0 | 100%
[5 empty] | Medium Voltage Cables | 12559 | 12559 | 0 | 100%
الإجمالي |  | 198906162.609 | 100% |  | Unit Substation | 3 |  | 3 | 0% |  | Potable Water Network | LV Network
[5 empty] | RMU | 3 |  | 3 | 0%
معالم البرنامج الزمني |  |  |  |  | Low Voltage Cables | 14370 | 1000 | 13370 | 6.959%
البند |  | التاريخ حسب الجدول الزمني | ملاحظة (التاريخ الفعلي) |  | Street Lighting Cables | 21525 | 4500 | 17025 | 20.91%
انتهاء من تجهيزات الموقع |  | 2025-08-30 | 2025-08-30 |  | Street Lighting Poles | 565 | 380 | 185 | 67.26%
انتهاء من تقديم خطة العمل والبرنامج الزمنى |  | 2025-08-30 | 2025-11-12
انتهاء من تقديم واعتماد المخططات والمواد |  | 2025-09-30 | 2026-02-08
انتهاء من الأعمال الكهربائية |  | 2026-10-03 | 2027-01-16 |  | التحديات
انتهاء من أعمال شبكة مياه الشرب |  | 2026-09-24 | 2026-12-28 |  | قلة عدد العمالة والمعدات وتوقف مقاول الباطن | [5 empty] | Earth & Road Works | Telecom Network
انتهاء من أعمال شبكة الري |  | 2026-08-02 | 2026-10-27 |  | تأخر أعمال العبارة بالطريق الشرياني
انتهاء من أعمال شبكة مياه الصرف الصحي |  | 2026-04-28 | 2026-05-12 |  | ضرورة الانتهاء من تنفيذ الشبكات لتحقيق جاهزية الموقع وبدء أعمال الطرق
انتهاء من أعمال شبكة صرف مياه الامطار |  | 2026-09-05 | 2026-12-26
| Activity ID | Activity Name | Original Duration | Activity Count | BL Project Start | BL Project Finish | Start | Finish | Budgeted Total Cost | Schedule % Complete | Performance % Complete
| Sewarage Network |  | 162.86 | 304 | 2025-11-11 | 2026-04-28 | 11-Nov-25 A | 2026-05-12 | 2099532.09 | 28.83% | 3.14%
| Storm Water Drainage |  | 303.58 | 681 | 2025-12-02 | 2026-09-05 | 15-Dec-25 A | 2026-12-26 | 14030918.34 | 10.79% | 0.43%
| Potable Water Network |  | 214.4 | 188 | 2025-12-09 | 2026-07-16 | 2026-01-15 | 2026-10-11 | 787572.64 | 6.34% | 0
| TSE Network |  | 229.32 | 162 | 2026-01-10 | 2026-08-02 | 2026-01-14 | 2026-10-27 | 837624.54 | 0% | 0
| Firefighting Network |  | 214.79 | 232 | 2026-01-05 | 2026-07-16 | 2026-01-15 | 2026-10-11 | 1894922.32 | 1.42% | 0
| Potable Water Pump Station |  | 284 | 141 | 2026-06-08 | 2026-09-24 | 07-Dec-25 A | 2026-12-28 | 8451419.05 | 0% | 0
| Sewage Lift Station |  | 318 | 78 | 2026-06-14 | 2026-10-05 | 07-Dec-25 A | 2027-02-01 | 3027598.51 | 0% | 0
| Medium Voltage Network |  | 230 | 90 | 2026-01-05 | 2026-08-02 | 2026-01-14 | 2026-10-27 | 2557026.81 | 0.18% | 0
| Low Voltage Network |  | 227.64 | 95 | 2026-02-01 | 2026-07-11 | 2026-01-14 | 2026-10-25 | 1140610.58 | 0% | 0
| Street Lighting Network |  | 287 | 250 | 2026-02-05 | 2026-09-17 | 2026-01-14 | 2027-01-02 | 3337456.91 | 0% | 0
| Telecommunication Network |  | 271.35 | 252 | 2026-01-15 | 2026-10-03 | 2026-02-15 | 2027-01-16 | 1874663.34 | 0% | 0%
| Guard Rooms |  | 246.45 | 75 | 2026-04-16 | 2026-08-17 | 2026-02-23 | 2026-12-23 | 513138.2 | 0% | 0%
| Landscape Green Areas |  | 302 | 32 | 2026-07-14 | 2026-11-08 | 2026-03-01 | 2027-03-01 | 5665437.16 | 0% | 0%
| Fences & Gates |  | 284 | 66 | 2026-06-27 | 2026-10-17 | 2026-02-25 | 2027-02-06 | 3869777.74 | 0% | 0%
| Roads |  | 370 | 365 | 2026-01-28 | 2026-11-24 | 20-Nov-25 A | 2027-03-17 | 62250682.66 | 0% | 3.93%

## LOOK AHEAD
مستهدف الربع
# | القطاع | المبادرة | Project ID | اسم المشروع | مدير المشروع | المقاول | بداية المشروع | نهاية المشروع التعاقدية | مدة المشروع (أشهر) | نهاية المشروع المتوقعة/ الالتزام | قيمة المشروع | المخطط /الفعلي | Mobilization المخطط | Mobilization المنفذ | Procurement (Long Lead Items) توريد المواد طويلة الأجل (المخطط) | Procurement (Long Lead Items) توريد المواد طويلة الأجل (المنفذ) | Civil Work الأعمال المدنية (المخطط) | Civil Work الأعمال المدنية (المنفذ) | Mechnical Work أعمال الميكانيكل (المخطط) | Mechnical Work أعمال الميكانيكل (المنفذ) | Electrical Work أعمال الكهرباء (المخطط) | Electrical Work أعمال الكهرباء (المنفذ) | تأثير التأخير (إن وجد) على المبادرات في الربع | نسبة الانجاز المستهدفة بنهاية الربع | نسبة الانجاز المحققة بنهاية الربع | مجموع المبالغ المفوترة المستهدفة بنهاية الربع | مجموع المبالغ المفوترة المحققة بنهاية الربع | نهاية المشروع المتوقعة
1 | الشرقي |  | DAM2-02-009 | Development of Infrastructure for phase 1 of the Logistics area at the 2nd Industrial City in Dammam | Muhammad H Al-Essa | Shibh Aljazira Contracting Company | 2025-07-30 | 2027-01-29 | 18.2667 | 2026-11-30 | 198906162.61 | 0.544665941107213/0.706556211058965 | 100% | 100% | توريد المواد الخاصة بمحطات الضخ و الرفع توريد مواد اللاندسكيب و الهاردسكيب | تم اصدار أوامر شراء المواد و جاري التصنيع و سيتم بدء التوريد | فرد طبقات الصبجري و فرد البيزكورس و الأسفلت في جميع المناطق المتاحة سواء Roads & Plots | جاري فرد طبقات الصبجري و فرد البيزكورس و الأسفلت في جميع المناطق المتاحة سواء Roads & Plots | - أعمال حفر التقاطعات و الخط الرئيسي لشبكات الصرف الصحي و صرف الأمطار و المياه و الحريق و الري | - تم الانتهاء من حفر و تمديد الخط الرئيسي و التقاطعات لشبكات الصرف الصحي و صرف الأمطار و المياه و الحريق و الري بالمناطق 01 و 02 و 03 و 04 بشكل كبير | - أعمال حفر التقاطعات (الداكت بانك) لشبكات الجهد المتوسط و الإنارة و الاتصالات - تركيب أعمدة الإنارة | - أعمال حفر التقاطعات (الداكت بانك) لشبكات الجهد المتوسط و الإنارة و الاتصالات - جاري حفر و تركيب قواعد و أعمدة الإنارة - جاري حفر و صب دكت بانك شبكة الاتصالات |  | 100% |  | 198906162.312 | 0 | 2026-11-30
64.92%
|  | Activity ID | Activity Name | Original Duration | Activity Count | BL Project Start | BL Project Finish | Start | Finish | Budgeted Total Cost | Schedule % Complete | Performance % Complete | Planned Value Cost | Actual Total Cost | Earned Value Cost | Activity % Complete | Units % Complete | Labor Units % Complete | Physical % Complete | Duration % Complete | Budgeted Labor Units | Planned Value Labor Units | Performance % Complete - Labor Units | Actual Labor Units | Earned Value Labor Units
|  | Developing of Infrastructure - Hail Industrial City PHASE II - Eastern Side Project - RBL - UPD |  | 573 | 1346 | 2024-01-07 | 2026-01-06 | 07-Jan-24 A | 2025-12-13 | 45093675 | 55.81% | 64.93% | 25164601.71 | 29291723.47 | 29280013.57 |  | 84.99% | 83.66% |  | 56.28% | 723256 | 606392 | 83.54% | 605105.55 | 604190.47
|  | Milestones |  | 573 | 10 | 2024-01-07 | 2026-01-06 | 07-Jan-24 A | 2025-12-13 | 0 | 0% | 0% | 0 | 0 | 0 |  | 0% | 0% |  | 56.49% | 0 | 0 | 0% | 0 | 0
|  | Mobilization |  | 564 | 26 | 2024-01-07 | 2025-12-02 | 07-Jan-24 A | 2025-12-09 | 0 | 0% | 0% | 0 | 0 | 0 |  | 65.05% | 64.3% |  | 56.08% | 72168 | 47052 | 64.3% | 46406.33 | 46406.28
|  | Engineering |  | 346.5 | 102 | 2024-01-30 | 2024-11-25 | 30-Jan-24 A | 2025-04-10 | 855746.25 | 100% | 98.39% | 855746.25 | 842006.25 | 842006.25 |  | 87.33% | 87.33% |  | 87.3% | 7512 | 7512 | 87.33% | 6560 | 6560
|  | Procurement |  | 446.38 | 93 | 2024-03-02 | 2025-11-03 | 02-Mar-24 A | 2025-09-09 | 5704975 | 79.8% | 96.96% | 4552391 | 5543594.06 | 5531827.53 |  | 82.05% | 82.43% |  | 61.92% | 55636 | 47260 | 80.78% | 45858.5 | 44943.36
|  | Construction |  | 495.5 | 1094 | 2024-02-26 | 2025-11-29 | 26-Feb-24 A | 2025-11-02 | 34023586.24 | 58.07% | 67.32% | 19756464.46 | 22906123.15 | 22906179.79 |  | 87.45% | 86.51% |  | 56.61% | 585220 | 504568 | 86.51% | 506280.72 | 506280.82
|  | POND #A |  | 450.5 | 29 | 2024-02-26 | 2025-11-29 | 26-Feb-24 A | 2025-09-09 | 8763653.64 | 85.83% | 97.07% | 7521973.07 | 8506553.64 | 8506553.64 |  | 96.88% | 95.35% |  | 62.26% | 22216 | 20792 | 95.35% | 21183.2 | 21183.2
|  | Storm Water Network |  | 300.63 | 410 | 2024-03-24 | 2025-05-22 | 24-Mar-24 A | 2025-04-07 | 10220975.4 | 61.7% | 83.43% | 6306639.93 | 8527064.74 | 8527130.18 |  | 97.31% | 97.22% |  | 86.36% | 307104 | 292988 | 97.23% | 298595.93 | 298596.16
|  | Sewerage Network |  | 227.55 | 201 | 2024-05-06 | 2025-04-06 | 06-May-24 A | 2025-02-05 | 3677928.7 | 99.15% | 99.88% | 3646835.26 | 3673447.83 | 3673446.66 |  | 99.95% | 99.94% |  | 99.74% | 161712 | 160372 | 99.94% | 161611.72 | 161611.68
|  | Potable Water Network |  | 283.98 | 205 | 2024-07-27 | 2025-08-12 | 27-Jul-24 A | 2025-05-06 | 3122794.65 | 49.08% | 47.56% | 1532618.02 | 1485275.98 | 1485289.29 |  | 47.24% | 44.97% |  | 76.76% | 41076 | 23536 | 44.97% | 18472.45 | 18472.46
|  | TSE Network |  | 275 | 109 | 2024-09-09 | 2025-11-03 | 09-Sep-24 A | 2025-08-14 | 1721343 | 43.48% | 41.47% | 748398.18 | 713780.97 | 713760.01 |  | 25.71% | 24.71% |  | 46.18% | 25968 | 6880 | 24.71% | 6417.42 | 6417.32
|  | Electrical Network - Road Lighting |  | 180 | 85 | 2025-04-03 | 2025-11-26 | 2025-03-25 | 2025-11-02 | 4342534.5 | 0% | 0% | 0 | 0 | 0 |  | 0% | 0% |  | 0% | 17608 | 0 | 0% | 0 | 0
|  | Additional Work |  | 135 | 55 | 2025-05-22 | 2025-11-02 | 2025-04-07 | 2025-09-16 | 2174356.36 | 0% | 0% | 0 | 0 | 0 |  | 0% | 0% |  | 0% | 9536 | 0 | 0% | 0 | 0
|  | Testing & Commissioning |  | 30 | 10 | 2025-11-04 | 2025-12-09 | 2025-10-11 | 2025-11-15 | 4509367.5 | 0% | 0% | 0 | 0 | 0 |  | 0% | 0% |  | 0% | 1968 | 0 | 0% | 0 | 0
|  | Close-Out |  | 24.5 | 11 | 2025-12-09 | 2026-01-06 | 2025-11-15 | 2025-12-13 | 0 | 0% | 0% | 0 | 0 | 0 |  | 0% | 0% |  | 0% | 752 | 0 | 0% | 0 | 0
Formulas:
نهاية المشروع المتوقعة/ الالتزام = [نهاية المشروع التعاقدية]-60
نهاية المشروع المتوقعة = [نهاية المشروع المتوقعة/ الالتزام]

## Codes (hidden)
Status List
| Approved |  | Y
| Pending |  | N | [5 empty] | (Manhours)
| Potential | [7 empty] | (Mandays)
| Phase | Stage |  | Stage |  | Status |  | Score
[8 empty] | Low | Contractor | Active
| Launch | LOA |  | LOA |  | Active |  | Medium | CM | Expired
| Launch | Kick-off Meeting |  | Kick-off Meeting |  | On Hold |  | High | PgM | Occurred
| Launch | Site Handover |  |  |  | Terminated |  |  | Modon | Pending
| Launch | Mobilization |  | Mobilization | Initial staff and equipment in place, ready to start production | Terminated, Closed |  |  | Other
| Execution | Construction |  | Execution | Tender Documents Issued | Substantial Complete | Initial Handover done at site
| Execution | T&C |  |  | Responses to the OCS completed | Complete | Initial Handover Signed
| Execution | Initial Handover |  | Closeout | Design close-out process complete | Closed | Final Handover done at Site
Warranty Period
Final Handover
Project Status Score
Elements |  |  | Max | Score | Planned | Actual | Remarks
SPI (Physical Effort) |  |  | 100% | 81.45% | No Entry Required
SPI (Cost) |  |  | 100% | 77.09% | No Entry Required
On Schedule -Active |  |  | 100% | 382.6% | No Entry Required |  |  |  | 0.6
Manpower Availability |  |  | 100% | 134.2% | No Entry Required
Major Equipment Availability |  |  | 100% | 217.3% | No Entry Required
Billing % Compared to Planned |  |  | 100% | 0% | No Entry Required
Safety Score |  |  | 100% | 92.25% | No Entry Required
Quality Score |  |  | 100% | #REF! | No Entry Required