## Slide 1: Executive Summary
Key Accomplishments This Week | Key Focus Areas Next Week
Engineering: Shop Drawings : Air Dome Power Single Line Drawings are Submitted Curtain Wall Steel Structure Schedules, Sections & Details are Submitted Material Submittal : Material submittal for Site Lighting Poles / Street Lights for all regions are Submitted Material submittal for Membrane Water proofing for all regions are Submitted | Engineering: Shop Drawing Preparation for Air Dome Shop Drawing Preparation for Electrical Work Shop Drawing Preparation for Mechanical Work Shop Drawing Preparation for Architectural Work
Construction: Asphalt Work Lean Concrete for Irrigation Tank Plastering Work in Toilet Area Foundation Work for Septic Tank Concrete pouring works for the curbs | Construction: Irrigation Pipe installation Asphalt Work Curbstone & Interlock Tiles installation Foundation work for Air Dome & Curtain Wall