## % Summary
P030 - (MLTX-02-003) - Playgrounds Initiative at (Qassim Oasis, Hail and Tabuk Industrial City) Technical/Engineering Submittals - Summary / Percentage
ADV | [5 empty] | Egis / Modon
Document Type / Trade | Deadline for Trade | Total Number of Documents | Planned Submissions to date | Actual Submissions to date | Delayed Submissions | Approved Code ( A&B ) | Revise & Resubmit Code ( C ) | Under Review Code ( UR ) | Delayed Review (+3 >= 5 days) | Under PMC Review / For Info. / Rejected / Withdrawn / Cancelled / Recalled Code ( D)
Pre-Qualification |  | 52 | N/A | 52 | N/A | 46 | 6 | 0 | 0 | 0
|  | 100% | N/A | 100% | N/A | 88.46% | 11.54% | 0% | 0% | 0%
Material Submittal |  | 130 | N/A | 130 | N/A | 119 | 6 | 4 | 1 | 0
|  | 100% | N/A | 100% | N/A | 91.54% | 4.615% | 3.077% | 0.7692% | 0%
Method Statement |  | 22 | N/A | 22 | N/A | 22 | 0 | 0 | 0 | 0
|  | 100% | N/A | 100% | N/A | 100% | 0% | 0% | 0% | 0%
Document Submittals Technical / General |  | 172 | N/A | 172 | N/A | 136 | 13 | 10 | 13 | 0
|  | 100% | N/A | 100% | N/A | 79.07% | 7.558% | 5.814% | 7.558% | 0%
RFI |  | 33 | N/A | 33 | N/A | 29 | 3 | 0 | 1 | 0
|  | 100% | N/A | 100% | N/A | 87.88% | 9.091% | 0% | 3.03% | 0%
Design Drawings |  | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0
|  | #DIV/0! | N/A | #DIV/0! | N/A | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Shop Drawings |  | 343 | N/A | 343 | N/A | 303 | 18 | 10 | 12 | 0
|  | 100% | N/A | 100% | N/A | 88.34% | 5.248% | 2.915% | 3.499% | 0%
Material Source Approval (MSA) |  | 13 | N/A | 13 | N/A | 1 | 3 | 0 | 9 | 0
|  | 100% | N/A | 100% | N/A | 7.692% | 23.08% | 0% | 69.23% | 0%
Total |  | 765 | N/A | 765 | N/A | 656 | 49 | 24 | 36 | 0
|  | 100% | N/A | 100% | N/A | 85.75% | 6.405% | 3.137% | 4.706% | 0%

## PQA
[25 empty] | Approved = A |  | 5
[5 empty] | P030 - (MLTX-02-003) - Playgrounds Initiative at (Qassim Oasis , Hail and Tabuk Industrial City) | [19 empty] | Approved with Comments = B |  | 41
[25 empty] | Revise & Resubmit = C |  | 6
[5 empty] | Pre-Qualifications (PQA) - Submissions & Approvals | [19 empty] | Under PMC Review / For Info. / Rejected / Cancelled / Recalled = D |  | 0
[25 empty] | Under Review = UR |  | 0
[25 empty] | Delayed with ADV |  | 0
[25 empty] | Delayed with Egis |  | 0
[25 empty] | Total Number of Submittals |  | 52
[10 empty] | 1st Submittal - Rev-00 |  |  |  |  | 2nd Submittal - Rev-01 |  |  |  | 3rd Submittal - Rev-02 |  |  |  | 4th Submittal - Rev-03 |  |  |  | 2026-10-01
Transmittle # | Location Area / Floor | SI No. | Transmittal Number | Latest Rev.# | ADV Reference Number | Doc Type | Description | Discipline | Site | Actual Submission Date | Delayed | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | A | B | C | D | UR | Delayed with Egis | Remarks
|  | 1 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0001-00 | 00 | ADV-0001 | PQA | Pre-qualification of “PRO YARD AIRDOM” for supply and install of Air dome. | CVL | All | 2026-03-04 |  | 2026-03-07 | 3 Days | C | [14 empty] | 1 |  |  |  | Revise & Resubmit
|  | 2 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0002-00 | 00 | ADV-0002 | PQA | Pre-qualification by “Abdullah Abdin Ready-mix & Cement Products” | CVL | Tabuk | 2026-03-24 |  | 2026-04-18 | 25 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 3 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0003-00 | 00 | ADV-0003 | PQA | Pre-Qualification of Tabuk Engineering Laboratory for material testing | CVL | Tabuk | 2026-03-24 |  | 2026-03-26 | 2 Days | C | [14 empty] | 1 |  |  |  | Revise & Resubmit
|  | 4 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0004-00 | 00 | ADV-0004 | PQA | Pre-qualification of “Mohd Omar Jazzar Consulting Engineers Co.” for Third-Party Site and Laboratory Testing Services. | CVL | All | 2026-04-04 |  | 2026-04-06 | 2 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 5 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0005-00 | 02 | ADV-0005 | PQA | Pre-qualification of “Global Sport Gate - Doul” for Air Dome System. (Tabuk & Qasim) | CVL | Qassim & Tabuk | 2026-04-04 |  | 2026-05-02 | 28 Days | C | 2026-05-18 | 2026-05-18 | 0 Days | C | 2026-06-03 | 2026-06-04 | 1 Days | B | [5 empty] | 1 |  |  |  |  | Approved with Comments
|  | 6 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0006-00 | 00 | ADV-0006 | PQA | Pre-qualification of “MAPEI CONSTRUCTION CHEMICALS S.P.A.” for Repair and Finishing Works | CVL | All | 2026-04-09 |  | 2026-04-15 | 6 Days | C | [14 empty] | 1 |  |  |  | Revise & Resubmit
|  | 7 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0007-00 | 00 | ADV-0007 | PQA | Pre-qualification of “SACEP & Construct” for supply of Kerbstone, Interlock Paver and Wheel Stopper. | CVL | All | 2026-04-19 |  | 2026-04-21 | 2 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 8 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0008-00 | 00 | ADV-0008 | PQA | Pre-qualification of “OPAL United Factory for Concrete Products Co.” for supply of Kerbstone, Interlock Paver and Wheel Stopper. | CVL | Qassim & Hail | 2026-04-19 |  | 2026-05-03 | 14 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 9 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0009-00 | 01 | ADV-0009 | PQA | Pre-qualification of ASAS AL-MOHILEB CRUSHER for Backfilling Materials A1-a & Aggregate Base Course materials - Tabuk | CVL | Tabuk | 2026-04-20 |  | 2026-04-21 | 1 Days | C | 2026-04-25 | 2026-04-26 | 1 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 10 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0010-00 | 00 | ADV-0010 | PQA | Pre-qualification of ASAS AL-MOHILEB Concrete batch plant for concrete ready mix for Tabuk project | CVL | Tabuk | 2026-04-21 |  | 2026-05-20 | 29 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 11 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0011-00 | 00 | ADV-0011 | PQA | Pre-qualification for Company Kharsana Tabuk Crusher (Abullah Abdin Industry Factory) for cement products for Backfilling Materials A1-a & Aggregate Base Course materials | CVL | Tabuk | 2026-04-21 |  | 2026-06-07 | 47 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 12 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0012-00 | 02 | ADV-0012 | PQA | Pre-qualification of Al-Omaier Trading & contracting. Co Crusher for Backfilling Materials A1-a & Aggregate Base Course materials | CVL | Hail | 2026-04-26 |  | 2026-05-03 | 7 Days | C | 2026-05-09 | 2026-05-09 | 0 Days | C | 2026-05-11 | 2026-05-11 | 0 Days | B | [5 empty] | 1 |  |  |  |  | Approved with Comments
|  | 13 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0013-00 | 00 | ADV-0013 | PQA | Pre-qualification of “Qassim Cement” for Portland Cement to be used in site for masonry and plaster works. | CVL | All | 2026-05-04 |  | 2026-05-10 | 6 Days | A | [12 empty] | 1 | [5 empty] | Approved
|  | 14 | MLTX-02-003-ADV-TS9-1-ARC-PQA-0014-00 | 00 | ADV-0014 | PQA | Pre-qualification of “Saudi Ceramic Company” for supply of Ceramic Tiles. | ARC | All | 2026-05-05 |  | 2026-05-10 | 5 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 15 | MLTX-02-003-ADV-TS9-1-ARC-PQA-0015-00 | 00 | ADV-0015 | PQA | Pre-qualification of “Emad Elsafwah” for Supply of Marble & Granite. | ARC | All | 2026-05-05 |  | 2026-05-09 | 4 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 16 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0016-00 | 00 | ADV-0016 | PQA | Pre-qualification of Arabian Testing Evolution company Laboratory for 3rd party site and laboratory testing services | CVL | Tabuk | 2026-05-09 |  | 2026-05-16 | 7 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 17 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0017-00 | 00 | ADV-0017 | PQA | Pre-qualification of “ASAS Laboratory Company” for field and laboratory material testing (Hail). | CVL | Hail | 2026-05-11 |  | 2026-06-02 | 22 Days | C | [14 empty] | 1 |  |  |  | Revise & Resubmit
|  | 18 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0018-00 | 00 | ADV-0018 | PQA | Pre-qualification by RAWAI AL BASATIN COMPANY For Sports Fields Flooring & Landscape Construction works (Qassim, Hail and Tabuk) | CVL | All | 2026-05-12 |  | 2026-06-02 | 21 Days | A | [12 empty] | 1 | [5 empty] | Approved
|  | 19 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0019-00 | 00 | ADV-0019 | PQA | Pre-qualification by GREEN YARD COMPANY for Sports Fields Flooring & Landscape works | CVL | All | 2026-05-12 |  | 2026-06-02 | 21 Days | A | [12 empty] | 1 | [5 empty] | Approved
|  | 20 | MLTX-02-003-ADV-TS9-1-ARC-PQA-0020-00 | 00 | ADV-0020 | PQA | Pre-qualification of ASAS AL-MOHILEB Concrete batch plant for supply of Kerbstone, Interlock, Wheel Stopper and CMU Block - (Tabuk Project ) | ARC | Tabuk | 2026-05-13 |  | 2026-05-20 | 7 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 21 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0021-00 | 00 | ADV-0021 | PQA | Pre-qualification FOR Arab Company for Laboratories and Soil (ACES) 3rd Party site and laboratory testing services Tabuk project | CVL | Tabuk | 2026-05-19 |  | 2026-05-20 | 1 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 22 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0022-00 | 00 | ADV-0022 | PQA | Pre-qualification Riyadh Geo-technique & Foundations Lab as a 3rd Party site and laboratory testing services Hail project | CVL | Hail | 2026-05-19 |  | 2026-05-19 | 0 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 23 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0023-00 | 00 | ADV-0023 | PQA | Pre-qualification of “Al Jammaz Hydrotek” for sports flooring and landscape work (Qassim Oasis, Hail and Tabuk Industrial City) | CVL | All | 2026-05-25 |  | 2026-06-04 | 10 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 24 | MLTX-02-003-ADV-TS9-1-ARC-PQA-0024-00 | 00 | ADV-0024 | PQA | Pre-qualification by MALAEB ALASIMA CONTRACTING COMPANY For Sports Fields Flooring & Landscape Construction works | ARC | All | 2026-06-03 |  | 2026-06-07 | 4 Days | A | [12 empty] | 1 | [5 empty] | Approved
|  | 25 | MLTX-02-003-ADV-TS9-1-ARC-PQA-0025-00 | 00 | ADV-0025 | PQA | Pre-qualification by ARAB FARMER COMPANY For Agricultural Soil, Plants, Trees and shrubs works (Qassim-Hail-Tabuk) | ARC | All | 2026-06-03 |  | 2026-07-16 | 43 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 26 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0026-00 | 00 | ADV-0026 | PQA | Pre-qualification for Expert Future company for Asphalt Patch plant (Abdullah Abdin Factory for asphalt) for supplying asphalt - Tabuk project | CVL | Tabuk | 2026-06-04 |  | 2026-06-14 | 10 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 27 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0027-00 | 01 | ADV-0027 | PQA | Pre-qualification of “Alomaier Trading and Contracting Co.” for supply of Asphalt and Roads material. (HAIL) | CVL | Hail | 2026-06-06 |  | 2026-06-11 | 5 Days | C | 2026-06-14 | 2026-06-15 | 1 Days | A | [8 empty] | 1 | [5 empty] | Approved
|  | 28 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0028-00 | 00 | ADV-0028 | PQA | Pre-qualification Saudi Center for Insulations & Concrete repair (Seal-Tech) company for Insulations systems (water proofing-thermal insulation-Epoxies) & concrete repair | CVL | All | 2026-06-08 |  | 2026-06-13 | 5 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 29 | MLTX-02-003-ADV-TS9-1-ARC-PQA-0029-00 | 00 | ADV-0029 | PQA | Pre-qualification by Saudi Floors COMPANY For Agricultural Soil, Plants, Trees and shrubs supplying & installation works (Qassim-Hail-Tabuk) | ARC | All | 2026-06-10 |  | 2026-06-14 | 4 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 30 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0030-00 | 00 | ADV-0030 | PQA | Pre-qualification for Fugro Suhaimi Company Limited Laboratory for 3rd party site and laboratory testing services (Tabuk) | CVL | Tabuk | 2026-06-13 |  | 2026-06-14 | 1 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 31 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0031-00 | 00 | ADV-0031 | PQA | Pre-qualification Saleh Contracting Company (SMCC) for Insulations systems (water proofing-thermal insulation-Epoxies) (Qassim, Hail and Tabuk) | CVL | All | 2026-06-16 |  | 2026-06-21 | 5 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 32 | MLTX-02-003-ADV-TS9-1-ARC-PQA-0032-00 | 00 | ADV-0032 | PQA | Pre-qualification of “ALUMINUM MAZAYA” for METAL WORKS (QASSIM, HAIL and TABUK) | ARC | All | 2026-06-29 |  | 2026-07-09 | 10 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 33 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0033-00 | 01 | ADV-0033 | PQA | Pre-Qualification of (Aman Construction Chemicals Manufacture Co. “Amancrete” 11) for material of stamped concrete flooring (Qassim, Hail and Tabuk) | CVL | All | 2026-07-01 |  | 2026-07-02 | 1 Days | C | 2026-07-05 | 2026-07-08 | 3 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 34 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0034-00 | 00 | ADV-0034 | PQA | Pre-qualification of Shibh Al Jazira Contracting Co. (SAJCO) for Asphalt Road work (Qassim) | CVL | Qassim | 2026-07-01 |  | 2026-07-09 | 8 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 35 | MLTX-02-003-ADV-TS9-1-ARC-PQA-0035-00 | 00 | ADV-0035 | PQA | Pre-qualification of "Alsarif company" for site furniture (Qassim, Hail and Tabuk) | ARC | All | 2026-07-04 |  | 2026-07-05 | 1 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 36 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0036-00 | 00 | ADV-0036 | PQA | Pre-qualification of MADAR BUILDING MATERIALS CO.LTD for supplying steel welding mesh (Qassim, Hail and Tabuk) | CVL | All | 2026-07-12 |  | 2026-07-15 | 3 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 37 | MLTX-02-003-ADV-TS9-1-ARC-PQA-0037-00 | 00 | ADV-0037 | PQA | Pre-qualification of Saudi Turf LTD for Playgrounds Flooring Materials (Qassim, Hail and Tabuk) | ARC | All | 2026-07-13 |  | 2026-07-15 | 2 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 38 | MLTX-02-003-ADV-TS9-1-ELE-PQA-0038-00 | 01 | ADV-0038 | PQA | Pre-qualification of Lighting Square Factory for Lighting Poles (Qassim, Hail & Tabuk ) | ELE | All | 2026-07-15 |  | 2026-07-16 | 1 Days | C | 2026-08-10 | 2026-08-12 | 2 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 39 | MLTX-02-003-ADV-TS9-1-ARC-PQA-0039-00 | 00 | ADV-0039 | PQA | Pre-qualification of MARBLE HOUSE FACTORY for Marble, Granite and Riyadh Stone Materials (Qassim, Hail and Tabuk) | ARC | All | 2026-07-20 |  | 2026-07-27 | 7 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 40 | MLTX-02-003-ADV-TS9-1-ELE-PQA-0040-00 | 01 | ADV-0040 | PQA | Pre-qualification by ALADWAA CO Lighting Fixtures for AIR DOME (QASIM-TABUK) | ELE | Qassim & Tabuk | 2026-08-17 |  | 2026-08-23 | 6 Days | C | 2026-08-24 | 2026-08-25 | 1 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 41 | MLTX-02-003-ADV-TS9-1-ELE-PQA-0041-00 | 00 | ADV-0041 | PQA | Pre-qualification by Works and Trade CO. LTD (WATCO) for supplying Lighting Fixtures from (skying co) for AIR DOME - Qassim & Tabuk | ELE | Qassim & Tabuk | 2026-08-19 |  | 2026-08-24 | 5 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 42 | MLTX-02-003-ADV-TS9-1-ELE-PQA-0042-00 | 00 | ADV-0042 | PQA | Pre-qualification by Desert Machinery Generators CO for supplying Diesel Engine from PERKINS for AIR DOME (QASSIM-TABUK) | ELE | Qassim & Tabuk | 2026-08-19 |  | 2026-08-20 | 1 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 43 | MLTX-02-003-ADV-TS9-1-ARC-PQA-0043-00 | 00 | ADV-0043 | PQA | Pre-qualification by STEEL FORCE INDUSTIES CO for metal products for AIR DOME at (QASIM-TABUK) | ARC | Qassim & Tabuk | 2026-08-22 |  | 2026-09-06 | 15 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 44 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0044-00 | 00 | ADV-0044 | PQA | Pre-qualification by MASDAR TECHNICAL SUPPLIES CO for supplying Anchor Bolts, Nuts, Washers, Screws, etc. for AIR DOME (QASSIM-TABUK) | CVL | Qassim & Tabuk | 2026-08-26 |  | 2026-09-06 | 11 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 45 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0045-00 | 00 | ADV-0045 | PQA | Pre-qualification by Al-Arkan Steel & Industrial Ltd. Co for Steel products for AIR DOME at (QASIM-TABUK) | CVL | Qassim & Tabuk | 2026-08-31 |  | 2026-09-06 | 6 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 46 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0046-00 | 00 | ADV-0046 | PQA | Pre-qualification by MAWARED AL-TASEES CO for Steel products for AIR DOME at (QASIM-TABUK) | CVL | Qassim & Tabuk | 2026-09-03 |  | 2026-09-06 | 3 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 47 | MLTX-02-003-ADV-TS9-1-ARC-PQA-0047-00 | 00 | ADV-0047 | PQA | Pre-qualification by Sada Al-Tatweer Aluminum Factory for Curtain Wall materials Aluminum & Glazing at (QASIM-HailTABUK) | ARC | All | 2026-09-08 |  | 2026-09-12 | 4 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 48 | MLTX-02-003-ADVTS9-1-CVL-PQA-0048-00 | 00 | ADV-0048 | PQA | Pre-qualification by Maaden Internation Metal Industries Ltd. Co. for Supply & install steel structure of AIR DOME (QASSIM-TABUK) | CVL | Qassim & Tabuk | 2026-09-10 |  | 2026-09-15 | 5 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 49 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0049-00 | 00 | ADV-0049 | PQA | Pre-qualification by IZOMAKS INDUSTRIES L.LC. IZOMAKS for supplying insulation water proofing materials at (QASIM-Hail-TABUK) | CVL | All | 2026-09-21 |  | 2026-09-26 | 5 Days | C | [14 empty] | 1 |  |  |  | Revise & Resubmit
|  | 50 | MLTX-02-003-ADV-TS9-1-CVL-PQA-0050-00 | 00 | ADV-0050 | PQA | Pr-qualification by SHIEL CAPITAL ARABIA CO for Pre-Cast concrete products Furniture concrete scope at (QASIM-Hail-TABUK) | CVL | All | 2026-09-21 |  | 2026-09-30 | 9 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 51 | MLTX-02-003-ADV-TS9-1-ELE-PQA-0051-00 | 00 | ADV-0051 | PQA | Pre-qualification SOMOUD ALAMIDAH CO for lighting pols and lighting fixtures and lights at QASSIM-HAIL-TABUK | ELE | All | 2026-09-28 |  | 2026-09-28 | 0 Days | C | [14 empty] | 1 |  |  |  | Revise & Resubmit
|  | 52 | MLTX-02-003-ADV-TS9-1-ARC-PQA-0052-00 | 00 | ADV-0052 |  | Pre-qualification of HURYMALA FACTORY CO. FOR NATURAL STONE (Riyadh stone) at QASSIM-HAIL-TABUK | ARC | All | 2026-09-29 |  | 2026-09-30 | 1 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
53
Formulas:
Duration with Egis = IF([Actual Submission Date]="","",(IF([Date of Return Egis]="",TODAY()-[Actual Submission Date],[Date of Return Egis]-[Actual Submission Date])+0)) & " Days "

## MS
[29 empty] | Approved = A |  | 5
[5 empty] | P030 - (MLTX-02-003) - Playgrounds Initiative at (Qassim Oasis , Hail and Tabuk Industrial City) | [23 empty] | Approved with Comments = B |  | 114
[29 empty] | Revise & Resubmit = C |  | 6
[5 empty] | Material Submittals (MS) - Submissions & Approvals | [23 empty] | Under PMC Review / For Info. / Rejected / Cancelled / Recalled = D |  | 0
[29 empty] | Under Review = UR |  | 4
[29 empty] | Delayed with ADV |  | 0
[29 empty] | Delayed with Egis |  | 1
[29 empty] | Total Number of Submittals |  | 130
[10 empty] | 1st Submittal - Rev-00 |  |  |  |  | 2nd Submittal - Rev-01 |  |  |  | 3rd Submittal - Rev-02 |  |  |  | 4th Submittal - Rev-03 |  |  |  | 5th Submittal - Rev-04 |  |  |  | 2026-10-01
Transmittle # | Location Area / Floor | SI No. | Transmittal Number | Latest Rev.# | ADV Reference Number | Doc Type | Description | Discipline | Site | Actual Submission Date | Delayed | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | A | B | C | D | UR | Delayed with Egis | Remarks
|  | 1 | MLTX-02-003-ADV-TS9-1-CVL-MS-0001-00 | 00 | ADV-0001 | MS | Material submittal for Ready Mix Concrete, Concrete Grade: C20 MPa SRC/OPC & C35 MPa SRC/OPC. | CVL | Qassim | 2026-03-09 |  | 2026-03-09 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 2 | MLTX-02-003-ADV-TS9-1-CVL-MS-0002-00 | 00 | ADV-0002 | MS | Material submittal for Ready Mix Concrete, Concrete Grade: C20 MPa SRC/OPC & C35 MPa SRC/OPC. | CVL | Hail | 2026-03-09 |  | 2026-03-10 | 1 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 3 | MLTX-02-003-ADV-TS9-1-CVL-MS-0003-00 | 00 | ADV-0003 | MS | Material submittal for Ready Mix Concrete, Concrete Grade: C20 MPa SRC/OPC & C35 MPa SRC/OPC. | CVL | Hail | 2026-03-09 |  | 2026-03-10 | 1 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 4 | MLTX-02-003-ADV-TS9-1-CVL-MS-0004-00 | 00 | ADV-0004 | MS | Material submittal for “Hadded” Steel Reinforcing Bars ASTM A615 Grade 60 | CVL | All | 2026-03-09 |  | 2026-03-10 | 1 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 5 | MLTX-02-003-ADV-TS9-1-CVL-MS-0005-00 | 00 | ADV-0005 | MS | Material submittal of “FOSROC” concrete repair materials. 1. RENDEROC FC 2. RENDEROC HS XTRA | CVL | All | 2026-03-24 |  | 2026-04-08 | 15 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 6 | MLTX-02-003-ADV-TS9-1-CVL-MS-0006-00 | 00 | ADV-0006 | MS | Material submittal of “Sika” concrete repair materials. 1. SikaRep Fine 2. SikaRep | CVL | All | 2026-03-24 |  | 2026-04-09 | 16 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 7 | MLTX-02-003-ADV-TS9-1-CVL-MS-0007-00 | 00 | ADV-0007 | MS | Material submittal for “Biflex TC” for termite control | CVL | All | 2026-03-24 |  | 2026-04-09 | 16 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 8 | MLTX-02-003-ADV-TS9-1-CVL-MS-0008-00 | 00 | ADV-0008 | MS | Material submittal for “Al Ittefaq” Steel Reinforcing Bars ASTM A615 Grade 60 | CVL | All | 2026-03-25 |  | 2026-03-28 | 3 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 9 | MLTX-02-003-ADV-TS9-1-CVL-MS-0009-00 | 00 | ADV-0009 | MS | Material submittal of “Poliane” Polyethylene Sheet 1. 250 micron under grade slab 2. 300 micron at roof waterproofing system | CVL | All | 2026-03-25 |  | 2026-03-28 | 3 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 10 | MLTX-02-003-ADV-TS9-1-CVL-MS-0010-00 | 00 | ADV-0010 | MS | Material submittal of Readymix Concrete (Concrete Mix Design) for concrete grades: C20 SRC, C35 SRC/OPC. (TABUK) | CVL | Tabuk | 2026-04-22 |  | 2026-05-06 | 14 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 11 | MLTX-02-003-ADV-TS9-1-CVL-MS-0011-00 | 00 | ADV-0011 | MS | Material submittal for “Autoclaved Aerated Panels” | CVL | All | 2026-04-27 |  | 2026-05-04 | 7 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 12 | MLTX-02-003-ADV-TS9-1-MEC-MS-0012-00 | 00 | ADV-0012 | MS | Material submittal for AC UNITS | MEC | All | 2026-05-05 |  | 2026-05-06 | 1 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 13 | MLTX-02-003-ADV-TS9-1-MEC-MS-0013-00 | 00 | ADV-0013 | MS | Material submittal for AIR OUTLET | MEC | All | 2026-05-05 |  | 2026-05-07 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 14 | MLTX-02-003-ADV-TS9-1-MEC-MS-0014-00 | 00 | ADV-0014 | MS | Material submittal for COPPER PIPES | MEC | All | 2026-05-06 |  | 2026-05-11 | 5 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 15 | MLTX-02-003-ADV-TS9-1-MEC-MS-0015-00 | 00 | ADV-0015 | MS | Material submittal for INSULATION FOR COPPER PIPES AND PPR HOT WATER PIPES | MEC | All | 2026-05-06 |  | 2026-05-11 | 5 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 16 | MLTX-02-003-ADV-TS9-1-MEC-MS-0016-00 | 00 | ADV-0016 | MS | Material submittal for DUCT, PLENUM BOX AND VOLUME DAMPERS | MEC | All | 2026-05-06 |  | 2026-05-11 | 5 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 17 | MLTX-02-003-ADV-TS9-1-MEC-MS-0017-00 | 00 | ADV-0017 | MS | MATERIAL SUBMITAL FOR UPVC PIPES AND FITTINGS | MEC | All | 2026-05-06 |  | 2026-05-11 | 5 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 18 | MLTX-02-003-ADV-TS9-1-MEC-MS-0018-00 | 00 | ADV-0018 | MS | MATERIAL SUBMITAL FOR PPR PIPES AND FITTINGS | MEC | All | 2026-05-06 |  | 2026-05-11 | 5 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 19 | MLTX-02-003-ADV-TS9-1-MEC-MS-0019-00 | 00 | ADV-0019 | MS | MATERIAL SUBMITAL FOR HDPE PIPES AND FITTINGS | MEC | All | 2026-05-06 |  | 2026-05-11 | 5 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 20 | MLTX-02-003-ADV-TS9-1-CVL-MS-0020-00 | 00 | ADV-0020 | MS | Material submittal for Backfilling Materials Class A-1-a (Hail) | CVL | Hail | 2026-05-07 |  | 2026-05-07 | 0 Days | C | [18 empty] | 1 |  |  |  | Revise & Resubmit
|  | 21 | MLTX-02-003-ADV-TS9-1-ARC-MS-0021-00 | 00 | ADV-0021 | MS | Material submittal of “Mada Gypsum” for supply of gypsum board, metal framing and accessories. | ARC | All | 2026-05-07 |  | 2026-05-16 | 9 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 22 | MLTX-02-003-ADV-TS9-1-ARC-MS-0022-00 | 00 | ADV-0022 | MS | Submittal of Qassim Cement “Finishing Cement” for use in site masonry and plastering works. | ARC | Qassim | 2026-05-10 |  | 2026-05-11 | 1 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 23 | MLTX-02-003-ADV-TS9-1-ELE-MS-0023-00 | 00 | ADV-0023 | MS | Material submittal for “CABLE TRAY”. | ELE | All | 2026-05-10 |  | 2026-05-13 | 3 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 24 | MLTX-02-003-ADV-TS9-1-ELE-MS-0024-00 | 00 | ADV-0024 | MS | Material submittal for “ EMT PIPES ,FITTINGS AND BOXES”. | ELE | All | 2026-05-11 |  | 2026-05-13 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 25 | MLTX-02-003-ADV-TS9-1-ARC-MS-0025-00 | 00 | ADV-0025 | MS | Material Submittal for Thermal and Water Proofing Materials | ARC | All | 2026-05-10 |  | 2026-05-17 | 7 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 26 | MLTX-02-003-ADV-TS9-1-ARC-MS-0026-00 | 00 | ADV-0026 | MS | Material Submittal for Waterproofing System Materials And Thermal Proofing | ARC | All | 2026-05-10 |  | 2026-05-11 | 1 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 27 | MLTX-02-003-ADV-TS9-1-ARC-MS-0027-00 | 00 | ADV-0027 | MS | Material Submittal of “Saudi Ceramics” for supply of 300*300mm and 600*600 mm Ceramic Floor Tiles and 300*300mm Wall Ceramic Wall Tiles. | ARC | All | 2026-05-10 |  | 2026-05-11 | 1 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 28 | MLTX-02-003-ADV-TS9-1-ARC-MS-0028-00 | 00 | ADV-0028 | MS | Material submittal of “Jazeera Paints” for epoxy floor paint, Internal/External Wall Acrylic Paints and Retroreflective Thermoplastic Road Paint. | ARC | All | 2026-05-12 |  | 2026-06-02 | 21 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 29 | MLTX-02-003-ADV-TS9-1-ARC-MS-0029-00 | 00 | ADV-0029 | MS | Material submittal for Masonry Concrete Blocks | ARC | Qassim | 2026-05-12 |  | 2026-06-02 | 21 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 30 | MLTX-02-003-ADV-TS9-1-ELE-MS-0030-00 | 00 | ADV-0030 | MS | Material submittal for LOW VOLTAGE CABLES AND WIRES | ELE | All | 2026-05-12 |  | 2026-05-13 | 1 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 31 | MLTX-02-003-ADV-TS9-1-ARC-MS-0031-00 | 00 | ADV-0031 | MS | Material submittal for Masonry Concrete Blocks | ARC | Hail | 2026-05-12 |  | 2026-06-02 | 21 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 32 | MLTX-02-003-ADV-TS9-1-ARC-MS-0032-00 | 00 | ADV-0032 | MS | Material submittal for Internal-External Signages / Traffic signs | ARC | All | 2026-05-12 |  | 2026-06-02 | 21 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 33 | MLTX-02-003-ADV-TS9-1-ELE-MS-0033-00 | 00 | ADV-0033 | MS | Material Submittal for PVC CONDUIT AND FITTINGS | ELE | All | 2026-05-13 |  | 2026-05-21 | 8 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 34 | MLTX-02-003-ADV-TS9-1-ARC-MS-0034-00 | 00 | ADV-0034 | MS | Material Submittal of Interlock Pavers (Hail, Qassim and Tabuk) Manufacturer: OPAL United Factory | ARC | All | 2026-05-17 |  | 2026-05-20 | 3 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 35 | MLTX-02-003-ADV-TS9-1-MEC-MS-0035-00 | 00 | ADV-0035 | MS | Material Submittal for BOOSTER PUMP (Hail, Qassim and Tabuk) | MEC | All | 2026-05-17 |  | 2026-05-21 | 4 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 36 | MLTX-02-003-ADV-TS9-1-CVL-MS-0036-00 | 01 | ADV-0036 | MS | Request for approval of Subgrade Material (Qassim) Supplier: Al-Sayigh Crusher | CVL | Qassim | 2026-05-18 |  | 2026-05-19 | 1 Days | C | 2026-06-07 | 2026-06-09 | 2 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 37 | MLTX-02-003-ADV-TS9-1-ARC-MS-0037-00 | 00 | ADV-0037 | MS | Material submittal for Kerbstone and Wheel Stopper – (Qassim, Hail and Tabuk ) Manufacturer and Supplier: OPAL United Factory | ARC | All | 2026-05-21 |  | 2026-06-02 | 12 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 38 | MLTX-02-003-ADV-TS9-1-ARC-MS-0038-00 | 00 | ADV-0038 | MS | Material submittal for “UNITECH” Block & Plaster Accessories (Qassim, Hail and Tabuk) Manufacturer: Isam Kabbani & Partners (UNITECH) | ARC | All | 2026-05-23 |  | 2026-05-31 | 8 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 39 | MLTX-02-003-ADV-TS9-1-CVL-MS-0039-00 | 00 | ADV-0039 | MS | MATERIAL SUBMITAL FOR MIX DESIGN FOR C20 OPC/SRC AND C35 OPC/SRC (Tabuk project) Manufacturer: Asas Almohaileb for Ready Mix Concrete | CVL | Tabuk | 2026-05-23 |  | 2026-06-07 | 15 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 40 | MLTX-02-003-ADV-TS9-1-ARC-MS-0040-00 | 00 | ADV-0040 | MS | Material submittal for Interlock Pavers, Kerbstones and Wheel stopper (Tabuk Project) Manufacturer: ASAS Almohileb | ARC | Tabuk | 2026-05-23 |  | 2026-06-07 | 15 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 41 | MLTX-02-003-ADV-TS9-1-MEC-MS-0041-00 | 00 | ADV-0041 | MS | Material submittal for FIRE EXTINGUISHER (Hail, Qassim & Tabuk) | MEC | All | 2026-05-23 |  | 2026-05-23 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 42 | MLTX-02-003-ADV-TS9-1-ARC-MS-0042-00 | 00 | ADV-0042 | MS | Material submittal of Wooden and metal Doors (for Hail, Qassim and Tabuk) Manufacturer: Al-Manashy Doors Factory | ARC | All | 2026-05-23 |  | 2026-05-31 | 8 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 43 | MLTX-02-003-ADV-TS9-1-CVL-MS-0043-00 | 00 | ADV-0043 | MS | Material submittal for Autoclaved Aerated Panels (Adhesive and Grout) (Qassim, Hail and Tabuk) Manufacturer: ESPAC | CVL | All | 2026-06-01 |  | 2026-06-04 | 3 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 44 | MLTX-02-003-ADV-TS9-1-MEC-MS-0044-00 | 00 | ADV-0044 | MS | Material submittal for GRP TANK (Hail, Qassim & Tabuk) | MEC | All | 2026-06-01 |  | 2026-06-06 | 5 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 45 | MLTX-02-003-ADV-TS9-1-ARC-MS-0045-00 | 00 | ADV-0045 | MS | Material submittal for: Supplying and installation of sports flooring rubber acrylic paint (paintCo ) system (For Qassim, Hail and Tabuk) Manufacturer: RAWAI AL BASATIN | ARC | All | 2026-06-04 |  | 2026-06-17 | 13 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 46 | MLTX-02-003-ADV-TS9-1-CVL-MS-0046-00 | 00 | ADV-0046 | MS | Material submittal for: Artificial grass for Football playgrounds (For Qassim, Hail and Tabuk) Manufacturer: RAWAI AL BASATIN | CVL | All | 2026-06-04 |  | 2026-06-08 | 4 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 47 | MLTX-02-003-ADV-TS9-1-ARC-MS-0047-00 | 01 | ADV-0047 | MS | Material submittal for: Panoramic of Padel Court , Incudes : Steel Structure & Steel Accessories - Glass & Glass Accessories - LED Lights - Net and Door Accessories - Turf & Turf Accessories of playgrounds (For Qassim, Hail and Tabuk) Manufacturer: RAWAI AL BASATIN | ARC | All | 2026-06-08 |  | 2026-06-11 | 3 Days | C | 2026-06-16 | 2026-06-21 | 5 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 48 | MLTX-02-003-ADV-TS9-1-ARC-MS-0048-00 | 01 | ADV-0048 | MS | Material submittal for: Tartan Floor Rubber tiles 50*50*40 MM Blue colour of playgrounds (For Qassim, Hail and Tabuk). Manufacturer: RAWAI AL BASATIN | ARC | All | 2026-06-08 |  | 2026-06-11 | 3 Days | C | 2026-06-16 | 2026-06-21 | 5 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 49 | MLTX-02-003-ADV-TS9-1-CVL-MS-0049-00 | 02 | ADV-0049 | MS | Material Submittal for Chain link Fence & Gate Materials. (For Qassim, Hail and Tabuk) Supplier: BRC Industrial Saudia Co. | CVL | All | 2026-06-08 |  | 2026-06-11 | 3 Days | C | 2026-06-17 | 2026-06-22 | 5 Days | C | 2026-07-22 | 2026-07-30 | 8 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 50 | MLTX-02-003-ADV-TS9-1-ARC-MS-0050-00 | 00 | ADV-0050 | MS | PU PRIMER 870 - Special, polyurethane, primer PU BINDER 1118 - Polyurethane binder RECYCLED RUBBER 858 - SBR granules EPDM 856 in granulometry POLYSPORT XP 1069 - UV-resistant Manufacturer/Supplier: Al Jammaz Hydrotek | ARC | All | 2026-06-08 |  | 2026-07-09 | 31 Days | C | [18 empty] | 1 |  |  |  | Revise & Resubmit
|  | 51 | MLTX-02-003-ADV-TS9-1-ARC-MS-0051-00 | 01 | ADV-0051 | MS | Turfs for paddle flooring, Tempered glass , Steel structural (columns & mesh) , Led lighting system Manufacturer/Supplier: Al Jammaz Hydrotek | ARC | All | 2026-06-08 |  | 2026-06-11 | 3 Days | C | 2026-06-17 | 2026-06-21 | 4 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 52 | MLTX-02-003-ADV-TS9-1-ARC-MS-0052-00 | 01 | ADV-0052 | MS | Artificial Grass (Stemgrass 50) (Qassim, Hail and Tabuk) Manufacturer/Supplier: Al Jammaz Hydrotek | ARC | All | 2026-06-08 |  | 2026-06-11 | 3 Days | C | 2026-06-17 | 2026-06-21 | 4 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 53 | MLTX-02-003-ADV-TS9-1-ARC-MS-0053-00 | 01 | ADV-0053 | MS | RITIVEX R LIQUID 1102 - Acrylic primer ELASTOSPORT 853 - Acrylic ELASTOTURF 851 ELASTOMARK 818 Manufacturer/Supplier: Al Jammaz Hydrotek | ARC | All | 2026-06-08 |  | 2026-06-11 | 3 Days | C | 2026-06-17 | 2026-06-21 | 4 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 54 | MLTX-02-003-ADV-TS9-1-ARC-MS-0054-00 | 00 | ADV-0054 | MS | PU FLEX 140 - Special, polyurethane adhesive ISOPOL 854 - Shock-pad in rolls POLYSPORT STUCCO 1050 - Polyurethane, elastic POLYSPORT PU 1051 - Polyurethane POLYSPORT 1052 - UV-resistant, polyurethane (Qassim Hail and Tabuk) Manufacturer/Supplier: Al Jammaz Hydrotek | ARC | All | 2026-06-08 |  | 2026-06-13 | 5 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 55 | MLTX-02-003-ADV-TS9-1-ARC-MS-0055-00 | 00 | ADV-0055 | MS | Material submittal for Interlock Paving Tiles (Qassim and Hail) Manufacturer: OPAL United Factory | ARC | Qassim & Hail | 2026-06-08 |  | 2026-06-13 | 5 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 56 | MLTX-02-003-ADV-TS9-1-ARC-MS-0056-00 | 01 | ADV-0056 | MS | PU PRIMER 870 primer, PU BINDER 1118 - RECYCLED RUBBER 858, EPDM 856 granules, POLYSPORT XP 1069 (Qassim, Hail and Tabuk) Manufacturer/Supplier: RAWAI AL BASATIN | ARC | All | 2026-06-10 |  | 2026-06-11 | 1 Days | C | 2026-06-17 | 2026-06-21 | 4 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 57 | MLTX-02-003-ADV-TS9-1-ARC-MS-0057-00 | 01 | ADV-0057 | MS | Artificial Grass, Silica sand, SBR granules rubber (Qassim, Hail and Tabuk) Manufacturer/Supplier: MALAEB ALASIMA COMPANY | ARC | All | 2026-06-10 |  | 2026-06-11 | 1 Days | C | 2026-06-17 | 2026-06-21 | 4 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 58 | MLTX-02-003-ADV-TS9-1-CVL-MS-0058-00 | 00 | ADV-0058 | MS | WOVEN & NON WOVEN GEOTEXTILE Manufacturer: TERRAM Geosynthetics Supplier: ISSAM KABBANI | CVL | All | 2026-06-13 |  | 2026-06-16 | 3 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 59 | MLTX-02-003-ADV-TS9-1-ARC-MS-0059-00 | 00 | ADV-0059 | MS | SIKA GARD PW for wet area using water proofing Epoxy Coating (Qassim, Hail and Tabuk) Manufacturer/Supplier: Sika Saudi Arabia Limited | ARC | All | 2026-06-18 |  | 2026-06-20 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 60 | MLTX-02-003-ADV-TS9-1-CVL-MS-0060-00 | 00 | ADV-0060 | MS | Material submittal of BituTHERM (EXTRUDED POLYSTYRENE THERMAL INSULATION BOARDS) (Qassim, Hail and Tabuk) Manufacturer: Bitumat Company Ltd. | CVL | All | 2026-06-18 |  | 2026-06-20 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 61 | MLTX-02-003-ADV-TS9-1-CVL-MS-0061-00 | 00 | ADV-0061 | MS | Material submittal of Bitumat Concrete primer (Qassim, Hail and Tabuk) Manufacturer: Bitumat Company Ltd. | CVL | All | 2026-06-18 |  | 2026-06-20 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 62 | MLTX-02-003-ADV-TS9-1-CVL-MS-0062-00 | 00 | ADV-0062 | MS | Material submittal of POLYFLAME (Qassim, Hail and Tabuk) Manufacturer: Bitumat Company Ltd. | CVL | All | 2026-06-18 |  | 2026-06-20 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 63 | MLTX-02-003-ADV-TS9-1-CVL-MS-0063-00 | 00 | ADV-0063 | MS | Material submittal of BITUMAT TOPSEAL 200 (Qassim, Hail and Tabuk) Manufacturer: Bitumat Company Ltd. | CVL | All | 2026-06-18 |  | 2026-06-20 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 64 | MLTX-02-003-ADV-TS9-1-CVL-MS-0064-00 | 00 | ADV-0064 | MS | PVC Water Stop (Qassim, Hail and Tabuk) Manufacturer: ISSAM KABBANI | CVL | All | 2026-06-20 |  | 2026-06-22 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 65 | MLTX-02-003-ADV-TS9-1-ELE-MS-0065-00 | 00 | ADV-0065 | MS | Material submittal for LIGHTNING AND PROTECTION SYSTEM (Hail, Qassim and Tabuk) Manufacturer: FURSE Supplier: SAUDI ELECTRIC SUPPLY COMPANY | ELE | All | 2026-06-22 |  | 2026-06-24 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 66 | MLTX-02-003-ADV-TS9-1-ELE-MS-0066-00 | 00 | ADV-0066 | MS | Material submittal for WIRING DEVICES (Hail, Qassim and Tabuk) Manufacturer: MK ELECTRIC Supplier: SAUDI ELECTRIC SUPPLY COMPANY | ELE | All | 2026-06-22 |  | 2026-06-27 | 5 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 67 | MLTX-02-003-ADV-TS9-1-CVL-MS-0067-00 | 00 | ADV-0067 | MS | Anchor Bolts (FBN II), Super Bond-System FSB and Injection Mortar FIS SB (Qassim, Hail and Tabuk) Manufacturer: (Doul) Fischer Innovative solutions | CVL | All | 2026-06-29 |  | 2026-07-05 | 6 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 68 | MLTX-02-003-ADV-TS9-1-ARC-MS-0068-00 | 00 | ADV-0068 | MS | External Membrane PVC/PVDF Obetex 1400, AFICO BLANKET INSULATION middle layer and Internal Membrane BLOCKOUT BOP 0850 (PVC) (Qassim, Hail and Tabuk) Manufacturer: OBLEKAN Technical Fabrics | ARC | All | 2026-06-29 |  | 2026-07-05 | 6 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 69 | MLTX-02-003-ADV-TS9-1-MEC-MS-0069-00 | 00 | ADV-0069 | MS | Ventilation Units System for AIR DOME (Qassim, Hail and Tabuk) Manufacturer: (DOUL) | MEC | All | 2026-06-30 |  | 2026-07-02 | 2 Days | B | 2026-06-30 | 2026-09-15 | 77 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 70 | MLTX-02-003-ADV-TS9-1-ARC-MS-0070-00 | 01 | ADV-0070 | MS | Weber floor 440 SC Weber Floor 340 RLS (Qassim, Hail and Tabuk) Manufacturer: WEBER | ARC | All | 2026-07-01 |  | 2026-07-02 | 1 Days | C | 2026-07-05 | 2026-07-06 | 1 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 71 | MLTX-02-003-ADV-TS9-1-ELE-MS-0071-00 | 00 | ADV-0071 | MS | Material submittal for Low Current Cable (Qassim, Hail and Tabuk) Manufacturer: MESC Supplier: Taysser Services Trading | ELE | All | 2026-07-05 |  | 2026-07-07 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 72 | MLTX-02-003-ADV-TS9-1-ARC-MS-0072-00 | 01 | ADV-0072 | MS | CEMENTITOUS MATERIAL FOR STAMPED CONCRETE - Aman Crete Sealer - Aman Crete 300 Release Agent - Aman Crete 200 Color Hardner (Qassim, Hail and Tabuk) Manufacturer: Aman Construction Chemicals Manufacture Co | ARC | All | 2026-07-08 |  | 2026-07-09 | 1 Days | C | 2026-07-12 | 2026-07-15 | 3 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 73 | MLTX-02-003-ADV-TS9-1-CVL-MS-0073-00 | 00 | ADV-0073 | MS | Material Submittal for Cico-Cure AR 380 acrylic resin-based concrete curing compound (Qassim, Hail and Tabuk) Manufacturer: CIC Construction Chemicals | CVL | All | 2026-07-07 |  | 2026-07-19 | 12 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 74 | MLTX-02-003-ADV-TS9-1-ELE-MS-0074-00 | 00 | ADV-0074 | MS | Material Submittal for DISCONNECT SWITCH (Qassim, Hail and Tabuk) Manufacturer: SCHNEIDER Supplier: ICON FOR TRADING | ELE | All | 2026-07-07 |  | 2026-07-14 | 7 Days | C | [18 empty] | 1 |  |  |  | Revise & Resubmit
|  | 75 | MLTX-02-003-ADV-TS9-1-ELE-MS-0075-00 | 01 | ADV-0075 | MS | Material Submittal for LIGHTING FIXTURES (Qassim, Hail and Tabuk) Manufacturer: NOORTEK - Supplier: AL NASSER PRO | ELE | All | 2026-07-13 |  | 2026-07-15 | 2 Days | C | 2026-09-19 | 2026-09-22 | 3 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 76 | MLTX-02-003-ADV-TS9-1-ARC-MS-0076-00 | 00 | ADV-0076 | MS | Material Submittal of Standard Grade Compact Laminate Phenolic Toilet Partitions (Merino) (Qassim, Hail and Tabuk) Manufacturer: Merino Industries Ltd., India | ARC | All | 2026-07-09 |  | 2026-07-12 | 3 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 77 | MLTX-02-003-ADV-TS9-1-ELE-MS-0077-00 | 01 | ADV-0077 | MS | Electrical generator from Perkins for AIR DOME (Qassim-Tabuk) 91 KVA (73 KW) DESIEL ENGINE 1100 Series 1104A-44TG2 Manufactures by (Perkins) | ELE | Qassim & Tabuk | 2026-07-12 |  | 2026-07-12 | 0 Days | C | 2026-08-22 | 2026-08-25 | 3 Days | C | 2026-09-10 | 2026-09-12 | 2 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 78 | MLTX-02-003-ADV-TS9-1-CVL-MS-0078-00 | 00 | ADV-0078 | MS | Steel Welding Reinforcement Mesh 8mm 20*20 cm (1.5 * 4.0 meter squire) Sabic steel (HADEED) (Qassim, Hail and Tabuk) Manufacturer: Bawan Metal Industries Co | CVL | All | 2026-07-16 |  | 2026-07-18 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 79 | MLTX-02-003-ADV-TS9-1-ARC-MS-0079-00 | 00 | ADV-0079 | MS | Material Submittal for Tartan Rubber Tiles 50*50*4 cm from Saudi Turf (Qassim, Hail and Tabuk) Manufacturer: Saudi Turf Co LTD. | ARC | All | 2026-07-21 |  | 2026-08-01 | 11 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 80 | MLTX-02-003-ADV-TS9-1-CVL-MS-0080-00 | 00 | ADV-0080 | MS | Material Submittal for BITUMEN IMPREGNATED WOOD FIBER FILLERS AND PROTECTION BOARDS (Qassim, Hail and Tabuk) Manufacturer: Isam Kabbani & Partners (UNITECH) | CVL | All | 2026-07-25 |  | 2026-08-01 | 7 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 81 | MLTX-02-003-ADV-TS9-1-CVL-MS-0081-00 | 00 | ADV-0081 | MS | Material Submittal of Isolation Joint Sealant “Cico Seal PU 40” (Qassim, Hail and Tabuk) Manufacturer: CIC Construction Chemicals | CVL | All | 2026-07-26 |  | 2026-08-01 | 6 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 82 | MLTX-02-003-ADV-TS9-1-CVL-MS-0082-00 | 01 | ADV-0082 | MS | Material Submittal of Bituminous Wearing Course - B (BWC-B) (Hail) Manufacturer: Alomaier Trading and Contracting Company | CVL | Hail | 2026-07-28 |  | 2026-08-01 | 4 Days | C | 2026-08-08 | 2026-08-16 | 8 Days | B | 2026-09-16 |  | 15 Days | UR | [12 empty] | 1 |  | Under Review
|  | 83 | MLTX-02-003-ADV-TS9-1-CVL-MS-0083-00 | 01 | ADV-0083 | MS | Material Submittal of Bituminous Base Course (BBC-A) (Hail) Manufacturer: Alomaier Trading and Contracting Company | CVL | Hail | 2026-07-28 |  | 2026-08-01 | 4 Days | C | 2026-08-08 | 2026-08-16 | 8 Days | B | 2026-09-16 |  | 15 Days | UR | [12 empty] | 1 |  | Under Review
|  | 84 | MLTX-02-003-ADV-TS9-1-CVL-MS-0084-00 | 00 | ADV-0084 | MS | Material Submittal of Aggregate Base Course “Mix Design-1” (Hail) Manufacturer: Alomaier Trading and Contracting Company. | CVL | Hail | 2026-07-28 |  | 2026-08-01 | 4 Days | C | [18 empty] | 1 |  |  |  | Revise & Resubmit
|  | 85 | MLTX-02-003-ADV-TS9-1-ARC-MS-0085-00 | 00 | ADV-0085 | MS | Material Submittal of Granite and Riyadh Stone (Qassim, Hail and Tabuk) Manufacturer: Marble House Factory co. | ARC | All | 2026-07-29 |  | 2026-08-01 | 3 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 86 | MLTX-02-003-ADV-TS9-1-ARC-MS-0086-00 | 00 | ADV-0086 | MS | Material Submittal and Sample of Tartan Floor Rubber Tiles - 50*50*40 MM Blue Colour (Qassim, Hail and Tabuk) Manufacturer: Rubber Arts Company for Industry (RAWAI AL BASATIN COMPANY) | ARC | All | 2026-07-30 |  | 2026-08-10 | 11 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 87 | MLTX-02-003-ADV-TS9-1-ARC-MS-0087-00 | 00 | ADV-0087 | MS | Playgrounds Equipments 1. PlayGround Benches 2. Football Goal 3. Basket Ball Stand - MANUFACTURED BY RAWAI AL BASATIN | ARC | All | 2026-08-01 |  | 2026-08-06 | 5 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 88 | MLTX-02-003-ADV-TS9-1-ARC-MS-0088-00 | 00 | ADV-0088 | MS | Material Submittal “saveto” Premium Project Fix – cementitious mortar adhesive for fixing ceramic tile - (Qassim, Tabuk and Hail) Supplier & Manufacturer: SAVETO | ARC | All | 2026-08-05 |  | 2026-08-15 | 10 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 89 | MLTX-02-003-ADV-TS9-1-ARC-MS-0089-00 | 00 | ADV-0089 | MS | FOOTBALL COURT ARTIFICIAL GRASS with Adhesive and silica sand and SBR rubber Materials by RAWAI AL BASATIN COMPANY for all locations | ARC | All | 2026-08-06 |  | 2026-08-15 | 9 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 90 | MLTX-02-003-ADV-TS9-1-ELE-MS-0090-00 | 01 | ADV-0090 | MS | MATERIAL SUBMITAL FOR LIGHTING POLES ( HAIL-TABUK-QASSIM ) | ELE | All | 2026-08-16 |  | 2026-08-18 | 2 Days | C | 2026-09-21 | 2026-09-22 | 1 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 91 | MLTX-02-003-ADV-TS9-1-CVL-MS-0091-00 | 01 | ADV-0091 | MS | Material Submittal of Bituminous Mix Design Wearing Course Class 'C' Manufacturer: Expert Future company for Asphalt Patch Plant for the BIKE PATH, WALK PATH, FOOTBALL COURTS. (Tabuk Project) MANUFACTURED BY: Expert Future company for Asphalt Patch | CVL | Tabuk | 2026-08-16 |  | 2026-08-23 | 7 Days | C | 2026-08-25 | 2026-09-03 | 9 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 92 | MLTX-02-003-ADV-TS9-1-CVL-MS-0092-00 | 00 | ADV-0092 | MS | Bituminous Mix Design Base Course Class 'B') from Shibh Al Jazira Contracting Co. (SAJCO) for Asphalt Road work (Qassim) football courts. (Qassim Project) MANUFACTURED BY: from Shibh Al Jazira Contracting Co. (SAJCO) for Asphalt Road work | CVL | Qassim | 2026-08-16 |  | 2026-08-31 | 15 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 93 | MLTX-02-003-ADV-TS9-1-CVL-MS-0093-00 | 00 | ADV-0093 | MS | Material Submittal of Bituminous Mix Design Wearing Course Class 'C' Manufacturer: Shibh Al Jazira Contracting Co. (SAJCO) for Asphalt Road work for the BIKE PATH, WALK PATH, FOOTBALL COURTS. (Qassim Project) MANUFACTURED BY: Shibh Al Jazira Contracting for Asphalt Patch | CVL | Qassim | 2026-08-16 |  | 2026-09-01 | 16 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 94 | MLTX-02-003-ADV-TS9-1-CVL-MS-0094-00 | 01 | ADV-0094 | MS | Material Submittal of Bituminous Mix Design Base Course Class 'B' Manufacturer: Expert Future company for Asphalt Patch plant (Tabuk Project) MANUFACTURED BY : Expert Future company for Asphalt Patch | CVL | Tabuk | 2026-08-16 |  | 2026-08-23 | 7 Days | C | 2026-08-25 | 2026-09-03 | 9 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 95 | MLTX-02-003-ADV-TS9-1-CVL-MS-0095-00 | 01 | ADV-0095 | MS | Material submittal for curb stone from Adullah Abdin Factory for cement products - (Tabuk Project) (15*30*50 cm – 12.5*25.5*91.5 cm) with chamfer (10*20*40 cm – 15*30*50 cm) without chamfer MANUFACTURED BY Adullah Abdin Factory for cement products | CVL | Tabuk | 2026-08-18 |  | 2026-08-18 | 0 Days | C | 2026-08-22 | 2026-08-22 | 0 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 96 | MLTX-02-003-ADV-TS9-1-ELE-MS-0096-00 | 00 | ADV-0096 | MS | Bypass System for AIR DOME BY (DESERT MACHINRY) Company (QASSIM-TABUK) projects Manufactures by (ABB Electrical) | ELE | Qassim & Tabuk | 2026-08-18 |  | 2026-08-23 | 5 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 97 | MLTX-02-003-ADV-TS9-1-CVL-MS-0097-00 | 00 | ADV-0097 | MS | Material Submittal for Prime coat MC1 and Tack coat RC2 for ASPHALT POURING WORKS from Expert Future company for Asphalt Patch plant (Abdullah Abdin Factory for asphalt) - (Tabuk Project) MANUFACTURED BY: Expert Future company for Asphalt Patch | CVL | Tabuk | 2026-08-19 |  | 2026-09-03 | 15 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 98 | MLTX-02-003-ADV-TS9-1-CVL-MS-0098-00 | 00 | ADV-0098 | MS | Material Submittal for Prime Coat (MC1). (Qassim) Supplier: SHIBH AL JAZIRA CONTRACTING CO. | CVL | Qassim | 2026-08-19 |  | 2026-09-16 | 28 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 99 | MLTX-02-003-ADV-TS9-1-CVL-MS-0099-00 | 00 | ADV-0099 | MS | Material Submittal for Tack Coat (RC-2). (Qassim) Supplier: SHIBH AL JAZIRA CONTARCTING. CO. | CVL | Qassim | 2026-08-19 |  | 2026-09-03 | 15 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 100 | MLTX-02-003-ADV-TS9-1-MEC-MS-0100-00 | 01 | ADV-0100 | MS | Air conditioners Package unit from ALZAMIL AC for AIR DOME (Qassim-Tabuk) Model ZRT 300/360 Manufactures by (ALZAMIL AC) | MEC | Qassim & Tabuk | 2026-08-22 |  | 2026-08-27 | 5 Days | C | 2026-08-29 | 2026-09-05 | 7 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 101 | MLTX-02-003-ADV-TS9-1-MEC-MS-0101-00 | 00 | ADV-0101 | MS | Material submittal for HDPE PIPES AND FITTINGS (Hail, Qassim & Tabuk) | MEC | All | 2026-08-22 |  | 2026-08-24 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 102 | MLTX-02-003-ADV-TS9-1-ARC-MS-0102-00 | 00 | ADV-0102 | MS | Material Submittal of 6649 Paintco aliphatic pu sg enamel LOCATIONS for planning paint of football - Padel-Basketball courts (Qassim-Hail-Tabuk) MANUFACTURED BY RAWAI AL BASATIN | ARC | All | 2026-08-23 |  | 2026-09-06 | 14 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 103 | MLTX-02-003-ADV-TS9-1-ELE-MS-0103-00 | 00 | ADV-0103 | MS | Emergency Exit Light for AIR DOME (Qassim-Tabuk) PNEX123-3.5W - Manufactures by (PAN LIGHTING CO) / Global Sport Gate - Doul | ELE | Qassim & Tabuk | 2026-08-26 |  | 2026-09-01 | 6 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 104 | MLTX-02-003-ADV-TS9-1-ELE-MS-0104-00 | 00 | ADV-0104 | MS | Light fixtures for AIR DOME (Qassim-Tabuk) PNHB123-200W-6.5K Manufactures by (PAN LIGHTING CO) / Global Sport Gate - Doul | ELE | Qassim & Tabuk | 2026-08-26 |  | 2026-09-01 | 6 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 105 | MLTX-02-003-ADV-TS9-1-ELE-MS-0105-00 | 00 | ADV-0105 | MS | Material Submittal of LV Cables 95 mm2 - 25 mm2 for earthing system for AIR DOME (Qassim-Tabuk) - Manufactures by (BAHRA CABLES CO) - (Banan Thiba CO) Company | ELE | Qassim & Tabuk | 2026-08-29 |  | 2026-09-01 | 3 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 106 | MLTX-02-003-ADV-TS9-1-ELE-MS-0106-00 | 01 | ADV-0106 | MS | MATERIAL SUBMITAL FOR FOOTBALL PLAYGROUND LIGHTING SYSTEM ( HAIL-TABUK-QASSIM ) | ELE | All | 2026-08-29 |  | 2026-09-03 | 5 Days | C | 2026-09-21 | 2026-09-22 | 1 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 107 | MLTX-02-003-ADV-TS9-1-ELE-MS-0107-00 | 00 | ADV-0107 | MS | Material Submittal for Earthing system materials for AIR DOME (Qassim-Tabuk) (Furse welded powder 90 P10) – (Sack of bentonite moisture CM105)- (Rod Clamb CR705) (Inspection Box PT005) _ (Earth Rod RB 325) _ (Copper Earth Bar LK245-6SS) (Copper Cable Lug) Manufactures by (FURSE CO) | ELE | Qassim & Tabuk | 2026-08-31 |  | 2026-09-01 | 1 Days | C | 2026-09-22 | 2026-09-22 | 0 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 108 | MLTX-02-003-ADV-TS9-1-CVL-MS-0108-00 | 00 | ADV-0108 | MS | Material submittal for “Bolden Emulsion Primer”, water base damp proof coat / primer coat - (QASIM-HAIL-TABUK) Manufactures by (Isam Kabbani & Partners (UNITECH)) | CVL | All | 2026-08-31 |  | 2026-09-12 | 12 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 109 | MLTX-02-003-ADV-TS9-1-MEC-MS-0109-00 | 00 | ADV-0109 | MS | Material Submittal of FIRE HOSE CABINET materials for AIR DOME at (Qassim-Tabuk) Manufactures by (HEBA Industrial factory CO) | MEC | Qassim & Tabuk | 2026-08-31 |  | 2026-09-06 | 6 Days | C | [18 empty] | 1 |  |  |  | Revise & Resubmit
|  | 110 | MLTX-02-003-ADV-TS9-1-ELE-MS-0110-00 | 00 | ADV-0110 | MS | Material Submittal of Switch Boxes for AIR DOME (Qassim-Tabuk) Manufactures by (ALFANAR CO) | ELE | Qassim & Tabuk | 2026-09-05 |  | 2026-09-06 | 1 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 111 | MLTX-02-003-ADV-TS9-1-ELE-MS-0111-00 | 00 | ADV-0111 | MS | Material Submittal of EMT Conduits & Fittings for AIR DOME (Qassim-Tabuk) - Manufactures by (International Tube & Conduit Company Ltd.CO) | ELE | Qassim & Tabuk | 2026-09-05 |  | 2026-09-06 | 1 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 112 | MLTX-02-003-ADV-TS9-1-CVL-MS-0112-00 | 00 | ADV-0112 | MS | Material Submittal for Anchor Bolts for AIR DOME (Qassim-Tabuk) - Manufactures by (MASDAR TECHNICAL SUPPLIES CO) | CVL | Qassim & Tabuk | 2026-09-06 |  | 2026-09-12 | 6 Days | C | 2026-09-14 | 2026-09-15 | 1 Days | C | [14 empty] | 1 |  |  |  | Revise & Resubmit
|  | 113 | MLTX-02-003-ADV-TS9-1-CVL-MS-0113-00 | 00 | ADV-0113 | MS | Steel Welding Reinforcement Mesh 8mm 20*20 cm (2.0 * 5.0-meter square) Sabic steel (HADEED) Sabic steel - Manufactural by Tabuk Steel Industries Co | CVL | Tabuk | 2026-09-07 |  |  | 24 Days | UR | [21 empty] | 1 | Delayed with Egis
|  | 114 | MLTX-02-003-ADV-TS9-1-ELE-MS-0114-00 | 00 | ADV-0114 | MS | Material Submittal of UPVC Conduits & Fittings Switch & Socket Boxes for AIR DOME (Qassim-Tabuk) Manufactures by (MK CABLES MANAGEMENT CO) | ELE | Qassim & Tabuk | 2026-09-07 |  | 2026-09-09 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 115 | MLTX-02-003-ADV-TS9-1-ARC-MS-0115-00 | 00 | ADV-0115 | MS | Material Submittal of SHUTTER DOOR FOR AIR DOME (Qassim-Tabuk) REVOLVING DOORSS ACCESSIBLE DOORS EMERGENCY METAL DOORS Manufactures by (STEEL FORCE INDUSTIES CO) | ARC | Qassim & Tabuk | 2026-09-09 |  | 2026-09-13 | 4 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 116 | MLTX-02-003-ADV-TS9-1-CVL-MS-0116-00 | 00 | ADV-0116 | MS | Material Submittal of L-Profile (L-angle) for AIR DOME (Qassim-Tabuk) Manufactures by (UNITED SULB COMPANY (SAUDI SULB) L.L.C.) | CVL | Qassim & Tabuk | 2026-09-09 |  | 2026-09-13 | 4 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 117 | MLTX-02-003-ADV-TS9-1-ARC-MS-0117-00 | 00 | ADV-0117 | MS | Material submittal for Interlock tiles grey scale with black marble chips 600*300*60mm zero joint. MANUFACTURED BY: Adullah Abdin Factory for cement products (QASIM-HAIL-Tabuk) | ARC | All | 2026-09-10 |  | 2026-09-14 | 4 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 118 | MLTX-02-003-ADV-TS9-1-ELE-MS-0118-00 | 00 | ADV-0118 | MS | MATERIAL SUBMITTAL FOR MOTOR of SHUTTER DOOR OPERATIONAL FOR AIR DOME MODEL TITAN 240/76 E HS. Manufactures by (STEEL FORCE INDUSTIES CO) (Qassim-Tabuk) | ELE | Qassim & Tabuk | 2026-09-10 |  | 2026-09-20 | 10 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 119 | MLTX-02-003-ADV-TS9-1-ELE-MS-0119-00 | 00 | ADV-0119 | MS | Material Submittal of Plexo weatherproof boxes for AIR DOME (Qassim-Tabuk) Manufactures by (LEGRAND .CO) | ELE | Qassim & Tabuk | 2026-09-12 |  | 2026-09-19 | 7 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 120 | MLTX-02-003-ADV-TS9-1-CVL-MS-0120-00 | 00 | ADV-0120 | MS | Material Submittal of SIKDUR- 32 epoxy bonding/grouting adhesive for (Qassim-Hail-Tabuk). Manufactures by (Sika Saudi Arabia Limited) | CVL | All | 2026-09-14 |  | 2026-09-16 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 121 | MLTX-02-003-ADV-TS9-1-CVL-MS-0121-00 | 00 | ADV-0121 | MS | Steel structure with accessories for shutter door tunnel for AIR DOME (Qassim-Tabuk) Manufactures by (STEEL FORCE INDUSTIES CO) | CVL | Qassim & Tabuk | 2026-09-15 |  | 2026-09-15 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 122 | MLTX-02-003-ADV-TS9-1-MEC-MS-0122-00 | 00 | ADV-0122 | MS | Materials submittal for Fire Extinguishers for AIR DOME at MODEL 6 kg carbon steel co2 SP01-04-6C, MODEL 6 kg Powder Fire Extinguisher SP01-05-6P. Manufactures by (HEBA Industrial factory CO) | CVL | Qassim & Tabuk | 2026-09-15 |  | 2026-09-21 | 6 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 123 | MLTX-02-003-ADV-TS9-1-ARC-MS-0123-00 | 00 | ADV-0123 | MS | Materials submittal for Aluminium frame & Glass materials with accessories for Curtain Wall for AIR DOME. Manufactured by (SADA AL-TATWEER Aluminum Factory) | ARC | Qassim & Tabuk | 2026-09-16 |  | 2026-09-19 | 3 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 124 | MLTX-02-003-ADV-TS9-1-CVL-MS-0124-00 | 00 | ADV-0124 | MS | Material Submittal of Bituminous Mix Design BASE Course Class B (BBC-B) (Hail). Manufacturer: Alomaier Trading and Contracting Company, MANUFACTURED BY Alomaier asphalt patch plant | CVL | Hail | 2026-09-17 |  | 2026-09-20 | 3 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 125 | MLTX-02-003-ADV-TS9-1-CVL-MS-0125-00 | 00 | ADV-0125 | MS | Material Submittal of Bituminous Mix Design Wearing Course Class C (BWC-C) (Hail)Manufacturer: Alomaier Trading and Contracting Company, MANUFACTURED BY Alomaier asphalt patch plant | CVL | Hail | 2026-09-17 |  | 2026-09-19 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 126 | MLTX-02-003-ADV-TS9-1-ELE-MS-0126-00 | 00 | ADV-0126 | MS | Material Submittal of WIRES & LOW VOLTAGE CABLES for AIR DOME at (Qassim-Tabuk) Manufactured by (JEDDAH CABLES CO) | ELE | Qassim & Tabuk | 2026-09-20 |  | 2026-09-22 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 127 | MLTX-02-003-ADV-TS9-1-ELE-MS-0127-00 | 00 | ADV-0127 | MS | Material Submittal of Panel Boards for AIR DOME at (Qassim-Tabuk) Manufactures by (First Panel CO) | ELE | Qassim & Tabuk | 2026-09-20 |  | 2026-09-22 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 128 | MLTX-05-047-ADVTS9-1-ELE-MS-0128-00 | 00 | ADV-0128 | MS | Material submittal for PANEL BOARDS COMPONENTS (Hail, Qassim & Tabuk) | ELE | All | 2026-09-22 |  | 2026-09-22 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 129 | MLTX-02-003-ADV-TS9-1-CVL-MS-0129-00 |  | ADV-0129 |  | Material submittal for Membrane water proofing IZOMAX VIA from IZOMAX Industrials CO Manufactures by IZOMAX Industrials CO | CVL | All | 2026-09-26 |  |  | 5 Days | UR | [20 empty] | 1 |  | Under Review
|  | 130 | MLTX-02-003-ADV-TS9-1-ELE-MS-0130-00 |  | ADV-0130 |  | Material Submittal for Site Lighting Poles / Street lights (Qassim, Hail and Tabuk) Manufacturer: SCALF | ELE | All | 2026-10-01 |  |  | 0 Days | UR | [20 empty] | 1 |  | Under Review
131
132
Formulas:
Duration with Egis = IF([Actual Submission Date]="","",(IF([Date of Return Egis]="",TODAY()-[Actual Submission Date],[Date of Return Egis]-[Actual Submission Date])+0)) & " Days "

## MST
[21 empty] | Approved = A |  | 0
[5 empty] | P030 - (MLTX-02-003) - Playgrounds Initiative at (Qassim Oasis , Hail and Tabuk Industrial City) | [15 empty] | Approved with Comments = B |  | 22
[21 empty] | Revise & Resubmit = C |  | 0
[5 empty] | Method of Statement (MST) - Submissions & Approvals | [15 empty] | Under PMC Review / For Info. / Rejected / Cancelled / Recalled = D |  | 0
[21 empty] | Under Review = UR |  | 0
[21 empty] | Delayed with ADV |  | 0
[21 empty] | Delayed with Egis |  | 0
[21 empty] | Total Number of Submittals |  | 22
[10 empty] | 1st Submittal - Rev-00 |  |  |  |  | 2nd Submittal - Rev-01 |  |  |  | 3rd Submittal - Rev-02 |  |  |  | 2026-10-01
Transmittle # | Location Area / Floor | SI No. | Transmittal Number | Latest Rev.# | ADV Reference Number | Doc Type | Description | Discipline | Planned Submission Date | Actual Submission Date | Delayed | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | A | B | C | D | UR | Delayed with Egis | Remarks
|  | 1 | MLTX-02-003-ADV-TS9-1-CVL-MST-0001-00 | 01 | ADV-0001 | MST | Method of Statement for Excavation Works | CVL |  | 2026-03-09 |  | 2026-03-17 | 8 Days | C | 2026-03-23 | 2026-03-26 | 3 Days | B | [5 empty] | 1 |  |  |  |  | Approved with Comments
|  | 2 | MLTX-02-003-ADV-TS9-1-CVL-MST-0002-00 | 01 | ADV-0002 | MST | Method of Statement for Backfilling Works | CVL |  | 2026-03-09 |  | 2026-03-17 | 8 Days | C | 2026-03-23 | 2026-03-26 | 3 Days | B | [5 empty] | 1 |  |  |  |  | Approved with Comments
|  | 3 | MLTX-02-003-ADV-TS9-1-CVL-MST-0003-00 | 01 | ADV-0003 | MST | Method Statement for Anti-Termite Treatment | CVL |  | 2026-03-10 |  | 2026-03-11 | 1 Days | C | 2026-03-24 | 2026-04-18 | 25 Days | B | [5 empty] | 1 |  |  |  |  | Approved with Comments
|  | 4 | MLTX-02-003-ADV-TS9-1-CVL-MST-0004-00 | 00 | ADV-0004 | MST | Method Statement for Cast-In-Situ Concrete Works | CVL |  | 2026-03-29 |  | 2026-04-08 | 10 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 5 | MLTX-02-003-ADV-TS9-1-CVL-MST-0005-00 | 00 | ADV-0005 | MST | Method Statement for Substructure Bituminous Damp Proof Coating | CVL |  | 2026-04-13 |  | 2026-04-18 | 5 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 6 | MLTX-02-003-ADV-TS9-1-ARC-MST-0006-00 | 00 | ADV-0006 | MST | Method Statement for Masonry Block Works | ARC |  | 2026-04-20 |  | 2026-04-26 | 6 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 7 | MLTX-02-003-ADV-TS9-1-ARC-MST-0007-00 | 00 | ADV-0007 | MST | MST for CURBSTONE & INTERLOCK PAVING WORKS | ARC |  | 2026-04-20 |  | 2026-04-26 | 6 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 8 | MLTX-02-003-ADV-TS9-1-CVL-MST-0008-00 | 00 | ADV-0008 | MST | Method Statement for Asphalt Paving Works | CVL |  | 2026-04-28 |  | 2026-04-30 | 2 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 9 | MLTX-02-003-ADV-TS9-1-CVL-MST-0009-00 | 01 | ADV-0009 | MST | Method Statement for Installation of Precast Concrete Manholes | CVL |  | 2026-04-30 |  | 2026-04-30 | 0 Days | C | 2026-05-02 | 2026-05-07 | 5 Days | B | [5 empty] | 1 |  |  |  |  | Approved with Comments
|  | 10 | MLTX-02-003-ADV-TS9-1-ELE-MST-0010-00 | 01 | ADV-0010 | MST | Installation of LV, SMDB, DB's Switchgear | ELE |  | 2026-05-02 |  | 2026-05-03 | 1 Days | C | 2026-05-11 | 2026-05-17 | 6 Days | B | [5 empty] | 1 |  |  |  |  | Approved with Comments
|  | 11 | MLTX-02-003-ADV-TS9-1-ELE-MST-0011-00 | 01 | ADV-0011 | MST | Installation of Earthing and Lightning Protection System | ELE |  | 2026-05-02 |  | 2026-05-03 | 1 Days | C | 2026-06-03 | 2026-06-10 | 7 Days | B | [5 empty] | 1 |  |  |  |  | Approved with Comments
|  | 12 | MLTX-02-003-ADV-TS9-1-MEC-MST-0012-00 | 00 | ADV-0012 | MST | Installation of Drainage Piping Network | MEC |  | 2026-05-12 |  | 2026-05-19 | 7 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 13 | MLTX-02-003-ADV-TS9-1-CVL-MST-0013-00 | 00 | ADV-0013 | MST | Method Statement for Installation of Autoclaved Aerated Panels | CVL |  | 2026-05-19 |  | 2026-06-01 | 13 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 14 | MLTX-02-003-ADV-TS9-1-MEC-MST-0014-00 | 00 | ADV-0014 | MST | Installation of Water Supply Piping Network | MEC |  | 2026-06-02 |  | 2026-06-06 | 4 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 15 | MLTX-02-003-ADV-TS9-1-ELE-MST-0015-00 | 00 | ADV-0015 | MST | Installation of PVC conduits & Accessories | ELE |  | 2026-06-02 |  | 2026-06-08 | 6 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 16 | MLTX-02-003-ADV-TS9-1-ARC-MST-0016-00 | 00 | ADV-0016 | MST | Method Statement for Epoxy Paint for walls & floors | ARC |  | 2026-06-11 |  | 2026-06-13 | 2 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 17 | MLTX-02-003-ADV-TS9-1-CVL-MST-0017-00 | 00 | ADV-0017 | MST | Method Statement for Installation of Steel chain link fence & Gates | CVL |  | 2026-06-16 |  | 2026-06-24 | 8 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 18 | MLTX-02-003-ADV-TS9-1-CVL-MST-0018-00 | 00 | ADV-0018 | MST | Method Statement for Installation of Water Proofing Membrane | CVL |  | 2026-06-21 |  | 2026-07-03 | 12 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 19 | MLTX-02-003-ADV-TS9-1-CVL-MST-0019-00 | 01 | ADV-0019 | MST | Method Statement for Installation of woven & non-woven Geotextile | CVL |  | 2026-07-09 |  | 2026-07-18 | 9 Days | C | 2026-07-21 | 2026-07-22 | 1 Days | B | [5 empty] | 1 |  |  |  |  | Approved with Comments
|  | 20 | MLTX-02-003-ADV-TS9-1-CVL-MST-0020-00 | 00 | ADV-0020 | MST | Method Statement for Plaster Work | CVL |  | 2026-07-30 |  | 2026-08-03 | 4 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 21 | MLTX-02-003-ADV-TS9-1-ARC-MST-0021-00 | 00 | ADV-0021 | MST | Method Statement for Installation of Gypsum Board Ceiling | ARC |  | 2026-09-05 |  | 2026-09-12 | 7 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 22 | MLTX-02-003-ADV-TS9-1-ARC-MST-0022-00 | 00 | ADV-0022 | MST | Method Statement for: Method Statement for Installation of Rubber Tartan Tiles | ARC |  | 2026-09-05 |  | 2026-09-12 | 7 Days | C | 2026-09-15 |  | 16 Days | B | [5 empty] | 1 |  |  |  |  | Approved with Comments
Formulas:
Duration with Egis = IF([Actual Submission Date]="","",(IF([Date of Return Egis]="",TODAY()-[Actual Submission Date],[Date of Return Egis]-[Actual Submission Date])+0)) & " Days "

## Doc. Submittals (Tech & Gen)
[33 empty] | Approved = A |  | 12
[5 empty] | P030 - (MLTX-02-003) - Playgrounds Initiative at (Qassim Oasis , Hail and Tabuk Industrial City) | [27 empty] | Approved with Comments = B |  | 124
[33 empty] | Revise & Resubmit = C |  | 13
[5 empty] | Technical Documents Submittals (DS) - Submissions & Approvals | [27 empty] | Under PMC Review / For Info. / Rejected / Cancelled / Recalled = D |  | 0
[33 empty] | Under Review = UR |  | 10
[33 empty] | Delayed with ADV |  | 0
[33 empty] | Delayed with Egis |  | 13
[33 empty] | Total Number of Submittals |  | 172
[10 empty] | 1st Submittal - Rev-00 |  |  |  |  | 2nd Submittal - Rev-01 |  |  |  | 3rd Submittal - Rev-02 |  |  |  | 4th Submittal - Rev-03 |  |  |  | 5th Submittal - Rev-04 |  |  |  | 6th Submittal - Rev-05 |  |  |  | 2026-10-01
Transmittle # | Location Area / Floor | SI No. | Transmittal Number | Latest Rev.# | ADV Reference Number | Doc Type | Description | Discipline | Planned Submission Date | Actual Submission Date | Delayed | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | A | B | C | D | UR | Delayed with Egis | Remarks
|  | 1 | MLTX-02-003-ADV-TS9-1-PRM-PLN-0001-00 | 01 | ADV-001 | PRM | Baseline Program Schedule – Qassim, Hail & Tabuk | PLN |  | 2026-02-28 |  | 2026-03-04 | 4 Days | C | 2026-03-04 | 2026-03-05 | 1 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 2 | MLTX-02-003-ADV-TS9-1-PRM-PQP-0002-00 | 02 | ADV-002 | PRM | Project Quality Plan – Qassim, Hail & Tabuk | PQP |  | 2026-03-12 |  | 2026-03-12 | 0 Days | C | 2026-04-09 | 2026-04-14 | 5 Days | C | 2026-05-23 | 2026-06-07 | 15 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 3 | MLTX-02-003-ADV-TS9-1-PRM-ORG-0003-00 | 00 | ADV-003 | PRM | Organization Chart – Hail, Qassim & Tabuk | ORG |  | 2026-03-23 |  | 2026-03-26 | 3 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 4 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0004-00 | 01 | ADV-004 | PRM | Curriculum vitae (CV) - Abdelelaah Saad Alashry - QA/QC Manager | CUV |  | 2026-03-28 |  | 2026-03-29 | 1 Days | C | 2026-03-30 | 2026-04-01 | 2 Days | C | [18 empty] | 1 |  |  |  | Revise & Resubmit
|  | 5 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0005-00 | 01 | ADV-005 | PRM | Curriculum vitae (CV) - Aatif Hussain - HSE Engineer | CUV |  | 2026-03-29 |  | 2026-04-13 | 15 Days | B | 2026-07-11 |  | 82 Days | UR | [21 empty] | 1 | Delayed with Egis
|  | 6 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0006-00 | 01 | ADV-006 | PRM | Curriculum vitae (CV) - Jaafar Gharaibeh - Civil Senior Engineer | CUV |  | 2026-03-30 |  | 2026-03-31 | 1 Days | C | 2026-04-02 | 2026-04-04 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 7 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0007-00 | 01 | ADV-007 | PRM | Curriculum vitae (CV) - NAVEED UR REHMAN - Planning Engineer | CUV |  | 2026-03-30 |  | 2026-03-31 | 1 Days | C | 2026-04-01 | 2026-04-08 | 7 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 8 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0008-00 | 01 | ADV-008 | PRM | Curriculum vitae (CV) – Abdelsalam Ali Mohamed Ahmed – Agricultural Engineer | CUV |  | 2026-03-30 |  | 2026-03-31 | 1 Days | C | 2026-04-04 | 2026-04-04 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 9 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0009-00 | 00 | ADV-009 | PRM | Curriculum vitae (CV) – Hany Faris - Senior Electrical Engineer | CUV |  | 2026-03-30 |  | 2026-04-01 | 2 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 10 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0010-00 | 01 | ADV-010 | PRM | Curriculum vitae (CV) – Mohammad Saleem Ansari - Senior Mechanical Engineer (MEP) | CUV |  | 2026-03-30 |  | 2026-03-30 | 0 Days | C | 2026-04-02 | 2026-04-08 | 6 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 11 | MLTX-02-003-ADV-TS9-1-PRM-RPT-0011-00 | 00 | ADV-011 | PRM | GEOTECHNICAL INVESTIGATION REPORT FOR QASSIM INDUSTRIAL PROJECT (Order No.078) QASSIM, KINGDOM OF SAUDI ARABIA - Applus Arabia for Testing and Physical Analysis LTD. - QASSIM | RPT |  | 2026-03-31 | [25 empty] | 1 |  |  |  |  | For Information
|  | 12 | MLTX-02-003-ADV-TS9-1-PRM-RPT-0012-00 | 00 | ADV-012 | PRM | GEOTECHNICAL INVESTIGATION REPORT FOR THE PROPOSED STADIUMS INITIATIVE AT TABUK Industrial City District, Tabuk, The Kingdom of Saudi Arabia - Applus Arabia for Testing and Physical Analysis. - TABUK | RPT |  | 2026-03-31 | [25 empty] | 1 |  |  |  |  | For Information
|  | 13 | MLTX-02-003-ADV-TS9-1-PRM-RPT-0013-00 | 00 | ADV-013 | PRM | GEOTECHNICAL INVESTIGATION REPORT FOR THE PROPOSED PLAYGROUNDS INITIAIVE-HAIL INDUSTRIAL PROJECT (WORK ODER NO:074) MODON OASIS, HAIL, K.S.A - Appl us Arabia for Testing and Physical Analysis LTD - HAIL | RPT |  | 2026-03-31 | [25 empty] | 1 |  |  |  |  | For Information
|  | 14 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0014-00 | 00 | ADV-014 | PRM | Curriculum vitae (CV) – Ahmed Mohammed Emeish – Project Manager | CUV |  | 2026-04-02 |  | 2026-04-05 | 3 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 15 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0015-00 | 00 | ADV-015 | PRM | Curriculum vitae (CV) – Bilal Nabil Loutfi - Senior Land Surveyor Engineer | CUV |  | 2026-04-02 |  | 2026-04-08 | 6 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 16 | MLTX-02-003-ADV-TS9-1-HSE-PLN-0016-00 | 01 | ADV-016 | HSE | Health & Safety Plan - Hail | PLN |  | 2026-04-04 |  | 2026-04-19 | 15 Days | A | 2026-04-29 | 2026-06-03 | 35 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 17 | MLTX-02-003-ADV-TS9-1-HSE-PLN-0017-00 | 00 | ADV-017 | HSE | Health & Safety Plan - Tabuk | PLN |  | 2026-04-04 |  | 2026-04-06 | 2 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 18 | MLTX-02-003-ADV-TS9-1-HSE-PLN-0018-00 | 01 | ADV-018 | HSE | Health & Safety Plan - Qassim | PLN |  | 2026-04-04 |  | 2026-04-21 | 17 Days | C | 2026-04-29 | 2026-05-11 | 12 Days | C | [18 empty] | 1 |  |  |  | Revise & Resubmit
|  | 19 | MLTX-02-003-ADV-TS9-1-HSE-PLN-0019-00 | 01 | ADV-019 | HSE | ENVIRONMENTAL MANAGEMENT PLAN - Hail | PLN |  | 2026-04-04 |  | 2026-04-15 | 11 Days | A | 2026-05-12 | 2026-06-04 | 23 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 20 | MLTX-02-003-ADV-TS9-1-HSE-PLN-0020-00 | 00 | ADV-020 | HSE | ENVIRONMENTAL MANAGEMENT PLAN - Qassim | PLN |  | 2026-04-04 |  | 2026-04-19 | 15 Days | C | [22 empty] | 1 |  |  |  | Revise & Resubmit
|  | 21 | MLTX-02-003-ADV-TS9-1-HSE-PLN-0021-00 | 00 | ADV-021 | HSE | ENVIRONMENTAL MANAGEMENT PLAN - Tabuk | PLN |  | 2026-04-04 |  | 2026-04-06 | 2 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 22 | MLTX-02-003-ADV-TS9-1-HSE-PLN-0022-00 | 01 | ADV-022 | HSE | WASTE MANAGEMENT PLAN - Hail | PLN |  | 2026-04-04 |  | 2026-04-15 | 11 Days | B | 2026-07-04 | 2026-08-19 | 46 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 23 | MLTX-02-003-ADV-TS9-1-HSE-PLN-0023-00 | 00 | ADV-023 | HSE | WASTE MANAGEMENT PLAN - Qassim | PLN |  | 2026-04-04 |  | 2026-04-19 | 15 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 24 | MLTX-02-003-ADV-TS9-1-HSE-PLN-0024-00 | 00 | ADV-024 | HSE | WASTE MANAGEMENT PLAN - Tabuk | PLN |  | 2026-04-04 |  | 2026-04-06 | 2 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 25 | MLTX-02-003-ADV-TS9-1-HSE-PLN-0025-00 | 01 | ADV-025 | HSE | EMERGENCY PREPARDNESS & RESPONSE PLAN - Hail | PLN |  | 2026-04-05 |  | 2026-04-15 | 10 Days | B | 2026-07-04 | 2026-08-19 | 46 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 26 | MLTX-02-003-ADV-TS9-1-HSE-PLN-0026-00 | 00 | ADV-026 | HSE | EMERGENCY PREPARDNESS & RESPONSE PLAN – Qassim | PLN |  | 2026-04-05 |  | 2026-04-19 | 14 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 27 | MLTX-02-003-ADV-TS9-1-HSE-PLN-0027-00 | 00 | ADV-027 | HSE | SITE SECURITY MANAGEMENT PLAN - Hail | PLN |  | 2026-04-05 |  | 2026-04-22 | 17 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 28 | MLTX-02-003-ADV-TS9-1-HSE-PLN-0028-00 | 00 | ADV-028 | HSE | SITE SECURITY MANAGEMENT PLAN - Qassim | PLN |  | 2026-04-05 |  | 2026-05-04 | 29 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 29 | MLTX-02-003-ADV-TS9-1-HSE-PLN-0029-00 | 00 | ADV-029 | HSE | SITE SECURITY MANAGEMENT PLAN - Tabuk | PLN |  | 2026-04-05 |  | 2026-04-06 | 1 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 30 | MLTX-02-003-ADV-TS9-1-HSE-PRO-0030-00 | 00 | ADV-030 | HSE | PERMIT TO WORK PROCEDURE - Hail | PRO |  | 2026-04-05 |  | 2026-04-15 | 10 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 31 | MLTX-02-003-ADV-TS9-1-HSE-PRO-0031-00 | 00 | ADV-031 | HSE | PERMIT TO WORK PROCEDURE - Qassim | PRO |  | 2026-04-05 |  | 2026-04-12 | 7 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 32 | MLTX-02-003-ADV-TS9-1-HSE-PRO-0032-00 | 00 | ADV-032 | HSE | PERMIT TO WORK PROCEDURE - Tabuk | PRO |  | 2026-04-05 |  | 2026-04-06 | 1 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 33 | MLTX-02-003-ADV-TS9-1-HSE-REG-0033-00 | 00 | ADV-033 | HSE | HSE PROJECT RISK REGISTER - Hail | REG |  | 2026-04-05 |  | 2026-04-13 | 8 Days | A | [20 empty] | 1 | [5 empty] | Approved
|  | 34 | MLTX-02-003-ADV-TS9-1-HSE-REG-0034-00 | 01 | ADV-034 | HSE | HSE PROJECT RISK REGISTER - Qassim | REG |  | 2026-04-05 |  | 2026-04-12 | 7 Days | C | 2026-04-15 | 2026-04-21 | 6 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 35 | MLTX-02-003-ADV-TS9-1-HSE-REG-0035-00 | 00 | ADV-035 | HSE | HSE PROJECT RISK REGISTER - Tabuk | REG |  | 2026-04-05 |  | 2026-04-06 | 1 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 36 | MLTX-02-003-ADV-TS9-1-HSE-TRN-0036-00 | 00 | ADV-036 | HSE | Occupational Health and Safety Training Matrix (Internal) - Hail | TRN |  | 2026-04-05 |  | 2026-04-13 | 8 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 37 | MLTX-02-003-ADV-TS9-1-HSE-TRN-0037-00 | 00 | ADV-037 | HSE | Occupational Health and Safety Training Matrix (Internal) - Qassim | TRN |  | 2026-04-05 |  | 2026-04-12 | 7 Days | C | [22 empty] | 1 |  |  |  | Revise & Resubmit
|  | 38 | MLTX-02-003-ADV-TS9-1-HSE-TRN-0038-00 | 00 | ADV-038 | HSE | Occupational Health and Safety Training Matrix (Internal) - Tabuk | TRN |  | 2026-04-05 |  | 2026-04-06 | 1 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 39 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0039-00 | 00 | ADV-039 | PRM | Curriculum vitae (CV) – Mohammad Ghazan Farali – HSE Officer | CUV |  | 2026-04-06 |  | 2026-04-23 | 17 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 40 | MLTX-02-003-ADV-TS9-1-PRM-WPR-0040-00 | 00 | ADV-040 | PRM | Weekly Progress Report (WPR) – Qassim, Hail & Tabuk (Report No. # 01) | WPR |  | 2026-04-06 |  | 2026-06-18 | 73 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 41 | MLTX-02-003-ADV-TS9-1-GEN-LST-0041-00 | 00 | ADV-041 | GEN | Material List – Qassim, Hail & Tabuk | LST |  | 2026-04-07 |  | 2026-04-14 | 7 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 42 | MLTX-02-003-ADV-TS9-1-HSE-PLN-0042-00 | 00 | ADV-042 | HSE | EMERGENCY PREPARDNESS & RESPONSE PLAN – Tabuk | PLN |  | 2026-04-08 |  | 2026-04-12 | 4 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 43 | MLTX-02-003-ADV-TS9-1-PRM-WPR-0043-00 | 00 | ADV-043 | PRM | Weekly Progress Report (WPR) – Qassim, Hail & Tabuk (Report No. # 02) | WPR |  | 2026-04-13 |  | 2026-04-15 | 2 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 44 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0044-00 | 00 | ADV-044 | PRM | Curriculum vitae (CV) – CRISTITO AQUINO PULIDO - Senior Quantity Surveyor | CUV |  | 2026-04-14 |  | 2026-04-25 | 11 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 45 | MLTX-02-003-ADV-TS9-1-HSE-PLN-0045-00 | 01 | ADV-045 | HSE | TRAFFIC MANAGEMENT PLAN – HAIL | PLN |  | 2026-04-19 |  | 2026-04-29 | 10 Days | C | 2026-05-17 | 2026-06-17 | 31 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 46 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0046-00 | 00 | ADV-046 | PRM | Curriculum vitae (CV) – Ahmed EID – Electrical Engineer | CUV |  | 2026-04-20 |  | 2026-04-21 | 1 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 47 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0047-00 | 00 | ADV-047 | PRM | Curriculum vitae (CV) – Mohamed Elsayed Abdelkader – Mechanical Engineer | CUV |  | 2026-04-20 |  | 2026-04-28 | 8 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 48 | MLTX-02-003-ADV-TS9-1-PRM-WPR-0048-00 | 00 | ADV-048 | PRM | Weekly Progress Report (WPR) – Qassim, Hail & Tabuk (Report No. # 03) | WPR |  | 2026-04-20 |  | 2026-06-18 | 59 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 49 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0049-00 | 00 | ADV-049 | PRM | Curriculum vitae (CV) – Yazan Jawad AL Saleh – Civil Engineer | CUV |  | 2026-05-03 |  | 2026-05-03 | 0 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 50 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0050-00 | 01 | ADV-050 | PRM | Curriculum vitae (CV) – Abdullah Saleh Alshammeri – QA-QC Engineer | CUV |  | 2026-04-23 |  | 2026-04-28 | 5 Days | C | 2026-05-19 | 2026-05-19 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 51 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0051-00 | 00 | ADV-051 | PRM | Curriculum vitae (CV) – Majid Ouidah - Sr. Civil Engineer | CUV |  | 2026-04-23 |  | 2026-05-06 | 13 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 52 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0052-00 | 00 | ADV-052 | PRM | Curriculum vitae (CV) – Ahmed Refaat – Technical Manager | CUV |  | 2026-04-25 |  | 2026-04-26 | 1 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 53 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0053-00 | 00 | ADV-053 | PRM | Curriculum vitae (CV) – MEHRAN AKHTAR – HSE Officer | CUV |  | 2026-04-27 |  | 2026-05-10 | 13 Days | C | [22 empty] | 1 |  |  |  | Revise & Resubmit
|  | 54 | MLTX-02-003-ADV-TS9-1-PRM-WPR-0054-00 | 00 | ADV-054 | PRM | Weekly Progress Report (WPR) – Qassim, Hail & Tabuk (Report No. # 04) | WPR |  | 2026-04-27 |  | 2026-06-18 | 52 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 55 | MLTX-02-003-ADV-TS9-1-GET-REP-0055-00 | 00 | ADV-055 | GET | GEO - Technical Report for Bore holes - Tabuk Project From: Mohamed Omar Consulting Engineers Co Laboratory | REP |  | 2026-04-29 |  | 2026-06-15 | 47 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 56 | MLTX-02-003-ADV-TS9-1-GET-REP-0056-00 | 01 | ADV-056 | GET | GEO-Technical Report for Bore holes of Hail Project From: Mohamed Omar Jazzar Consulting Engineers Co Laboratory | REP |  | 2026-05-03 |  | 2026-05-05 | 2 Days | C | 2026-05-05 | 2026-05-05 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 57 | MLTX-02-003-ADV-TS9-1-PRM-CER-0057-00 | 00 | ADV-057 | PRM | Calibration Certificate of Auto Level “Leica NA 520” | CER |  | 2026-05-04 |  | 2026-05-06 | 2 Days | A | [20 empty] | 1 | [5 empty] | Approved
|  | 58 | MLTX-02-003-ADV-TS9-1-PRM-CER-0058-00 | 00 | ADV-058 | PRM | Calibration Certificate of Total Station “Leica TS 03” | CER |  | 2026-05-04 |  | 2026-05-06 | 2 Days | A | [20 empty] | 1 | [5 empty] | Approved
|  | 59 | MLTX-02-003-ADV-TS9-1-PRM-WPR-0059-00 | 00 | ADV-059 | PRM | Weekly Progress Report (WPR) – Qassim, Hail & Tabuk (Report No. # 05) | WPR |  | 2026-05-04 |  | 2026-06-18 | 45 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 60 | MLTX-02-003-ADV-TS9-1-PRM-TST-0060-00 | 00 | ADV-060 | PRM | Sub-Base Material Sample Test Reports Material Source: Alsayegh Crusher | TST |  | 2026-05-05 |  | 2026-05-06 | 1 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 61 | MLTX-02-003-ADV-TS9-1-PRM-MPR-0061-00 | 00 | ADV-061 | PRM | Monthly Progress Report (MPR) of April 2026 – Qassim, Hail & Tabuk | MPR |  | 2026-05-05 |  | 2026-06-18 | 44 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 62 | MLTX-02-003-ADV-TS9-1-PRM-TST-0062-00 | 01 | ADV-062 | PRM | Sub-base and aggregate base course sample test by Aljazzar LAB Material source Almohelib Crusher for (A1-a & Aggregate base course) for Tabuk project | TST |  | 2026-05-06 |  | 2026-05-10 | 4 Days | C | 2026-05-11 | 2026-05-16 | 5 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 63 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0063-00 | 00 | ADV-063 | PRM | Curriculum vitae (CV) – UZAIR NAWAZ – HSE Officer | CUV |  | 2026-05-10 |  | 2026-05-18 | 8 Days | C | [22 empty] | 1 |  |  |  | Revise & Resubmit
|  | 64 | MLTX-02-003-ADV-TS9-1-PRM-WPR-0064-00 | 00 | ADV-064 | PRM | Weekly Progress Report (WPR) – Qassim, Hail & Tabuk (Report No. # 06) | WPR |  | 2026-05-11 |  | 2026-06-18 | 38 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 65 | MLTX-02-003-ADV-TS9-1-GET-REP-0065-00 | 00 | ADV-065 | GET | GEO-Technical Report for Bore holes of Qasim Project From: Mohamed Omar Jazzar Consulting Engineers Co Laboratory | REP |  | 2026-05-07 |  | 2026-05-07 | 0 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 66 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0066-00 | 00 | ADV-066 | PRM | Curriculum Vitae (CV) – Syed Usama Trimzi – HSE Officer | CUV |  | 2026-05-11 |  | 2026-06-11 | 31 Days | C | [22 empty] | 1 |  |  |  | Revise & Resubmit
|  | 67 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0067-00 | 00 | ADV-067 | PRM | Curriculum Vitae (CV) – INAM ULLAH KHAN – HSE Officer | CUV |  | 2026-05-12 |  | 2026-06-07 | 26 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 68 | MLTX-02-003-ADV-TS9-1-PRM-TST-0068-00 | 00 | ADV-068 | PRM | Field Density Test Report – Qassim Field Density Test for compacted Subgrade after removal of top soil and excavation | TST |  | 2026-05-17 |  | 2026-05-19 | 2 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 69 | MLTX-02-003-ADV-TS9-1-PRM-WPR-0069-00 | 00 | ADV-069 | PRM | Weekly Progress Report (WPR) – Qassim, Hail & Tabuk (Report No. # 07) | WPR |  | 2026-05-18 |  | 2026-05-19 | 1 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 70 | MLTX-02-003-ADV-TS9-1-PRM-TST-0070-00 | 00 | ADV-070 | PRM | Sub-base and aggregate base course sample test by Aljazzar LAB Material source Alomaier Crusher for (A1-a & Aggregate base course) for Hail project | TST |  | 2026-05-20 |  | 2026-06-13 | 24 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 71 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0071-00 | 00 | ADV-071 | PRM | Curriculum vitae (CV) - Anwar Omran El Taher- Senior Civil Engineer | CUV |  | 2026-05-23 |  | 2026-06-07 | 15 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 72 | MLTX-02-003-ADV-TS9-1-PRM-TST-0072-00 | 00 | ADV-072 | PRM | Test Soil Report for Sample (Back Filling & Fill) From LAB RGF (HAIL) | TST |  | 2026-05-23 |  | 2026-06-06 | 14 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 73 | MLTX-02-003-ADV-TS9-1-PRM-WPR-0073-00 | 00 | ADV-073 | PRM | Weekly Progress Report (WPR) – Qassim, Hail & Tabuk (Report No. # 08) | WPR |  | 2026-05-25 |  | 2026-06-18 | 24 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 74 | MLTX-02-003-ADV-TS9-1-PRM-SAM-0074-00 | 00 | ADV-074 | PRM | Material Sample of “OPAL United factory” Interlock pavers (for Qassim and Hail) 1. 200mm*100mm*80 mm | SAM |  | 2026-06-01 |  | 2026-06-06 | 5 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 75 | MLTX-02-003-ADV-TS9-1-PRM-WPR-0075-00 | 00 | ADV-075 | PRM | Weekly Progress Report (WPR) – Qassim, Hail & Tabuk (Report No. # 09) | WPR |  | 2026-06-01 |  | 2026-06-18 | 17 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 76 | MLTX-02-003-ADV-TS9-1-PRM-MPR-0076-00 | 00 | ADV-076 | PRM | Monthly Progress Report (MPR) of May 2026 – Qassim, Hail & Tabuk | MPR |  | 2026-06-02 |  | 2026-06-18 | 16 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 77 | MLTX-02-003-ADV-TS9-1-PRM-CER-0077-00 | 00 | ADV-077 | PRM | Calibration Certificates (HAIL) Calibration Certificate for Auto level “Sokkia B30A” Calibration Certificate for TOTAL STATION “Sokkia IM-55” | CER |  | 2026-06-02 |  | 2026-06-02 | 0 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 78 | MLTX-02-003-ADV-TS9-1-PRM-WPR-0078-00 | 00 | ADV-078 | PRM | Weekly Progress Report (WPR) – Qassim, Hail & Tabuk (Report No. # 10) | WPR |  | 2026-06-08 |  | 2026-06-18 | 10 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 79 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0079-00 | 00 | ADV-079 | PRM | Curriculum vitae (CV) - KALEEL NAWAIR - Quantity Surveyor (QS) | CUV |  | 2026-06-08 |  | 2026-06-13 | 5 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 80 | MLTX-02-003-ADV-TS9-1-PRM-SAM-0080-00 | 00 | ADV-080 | PRM | Material Sample of “ISAM KABBANI & PARTNERS (UNITECH)” Block & Plaster Accessories (Qassim, Hail and Tabuk) | SAM |  | 2026-06-09 |  | 2026-06-11 | 2 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 81 | MLTX-02-003-ADV-TS9-1-PRM-SAM-0081-00 | 00 | ADV-081 | PRM | Material Sample of “OPAL United factory” Kerbstone (for Qassim and Hail) | SAM |  | 2026-06-09 |  | 2026-07-09 | 30 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 82 | MLTX-02-003-ADV-TS9-1-PRM-SAM-0082-00 | 00 | ADV-082 | PRM | Colour selection for approved Material Sample of “OPAL United factory” Interlock pavers (for Qassim and Hail) “200mm*100mm*80mm” | SAM |  | 2026-06-10 |  | 2026-06-11 | 1 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 83 | MLTX-02-003-ADV-TS9-1-PRM-TST-0083-00 | 01 | ADV-083 | PRM | Particle size distribution (gradation) test and Modified Proctor compaction test on existing natural ground soil. (Tabuk) | TST |  | 2026-06-11 |  | 2026-06-14 | 3 Days | C | 2026-06-15 | 2026-06-15 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 84 | MLTX-02-003-ADV-TS9-1-PRM-WPR-0084-00 | 00 | ADV-084 | PRM | Weekly Progress Report (WPR) – Qassim, Hail & Tabuk (Report No. # 11) | WPR |  | 2026-06-15 |  | 2026-06-18 | 3 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 85 | MLTX-02-003-ADV-TS9-1-PRM-TST-0085-00 | 00 | ADV-085 | PRM | Aggregate base coarse material sample test reports by Arab company for laboratories and soil (ACES) Material Source: Alsayegh Crusher ( For Qassim ) | TST |  | 2026-06-17 |  | 2026-06-21 | 4 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 86 | MLTX-02-003-ADV-TS9-1-PRM-TST-0086-00 | 00 | ADV-086 | PRM | Subgrade material sample test by Fugro Suhaimi LAB. Material source ASAS Al-Mohelib Crusher (Tabuk Project) | TST |  | 2026-06-22 |  | 2026-07-07 | 15 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 87 | MLTX-02-003-ADV-TS9-1-PRM-WPR-0087-00 | 00 | ADV-087 | PRM | Weekly Progress Report (WPR) – Qassim, Hail & Tabuk (Report No. # 12) | WPR |  | 2026-06-22 |  | 2026-07-29 | 37 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 88 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0088-00 | 00 | ADV-088 | PRM | Curriculum vitae (CV) - ADNAN SHAHZAD – HSE Officer - Hail | CUV |  | 2026-06-24 |  | 2026-06-30 | 6 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 89 | MLTX-02-003-ADV-TS9-1-PRM-SAM-0089-00 | 00 | ADV-089 | PRM | Material Sample of “Al-Jammaz HydroteK (KDF)” Basketball flooring (Qassim, Hail and Tabuk) | SAM |  | 2026-06-25 |  | 2026-07-05 | 10 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 90 | MLTX-02-003-ADV-TS9-1-PRM-SAM-0090-00 | 02 | ADV-090 | PRM | Material Sample of “RAWAI AL BASATIN COMPANY” Paddle Court Turf (Qassim, Hail and Tabuk) | SAM |  | 2026-06-25 |  | 2026-07-05 | 10 Days | C | 2026-08-17 | 2026-08-24 | 7 Days | C | 2026-09-05 | 2026-09-12 | 7 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 91 | MLTX-02-003-ADV-TS9-1-PRM-SAM-0091-00 | 00 | ADV-091 | PRM | Material Sample of “Al-Jammaz HydroteK ” Artificial Grass (Qassim, Hail and Tabuk) | SAM |  | 2026-06-25 |  | 2026-07-05 | 10 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 92 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0092-00 | 00 | ADV-092 | PRM | Curriculum vitae (CV) - NALLAJALA VINESH - HSE Officer - TABUK | CUV |  | 2026-06-27 |  | 2026-06-28 | 1 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 93 | MLTX-02-003-ADV-TS9-1-PRM-TST-0093-00 | 00 | ADV-093 | PRM | Aggregate Sub Base material sample test by Fugro Suhaimi LAB. Material source ASAS Al-Mohelib Crusher (Tabuk Project) | TST |  | 2026-06-29 |  | 2026-06-30 | 1 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 94 | MLTX-02-003-ADV-TS9-1-PRM-WPR-0094-00 | 00 | ADV-094 | PRM | Weekly Progress Report (WPR) – Qassim, Hail & Tabuk (Report No. # 13) | WPR |  | 2026-06-29 |  | 2026-07-29 | 30 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 95 | MLTX-02-003-ADV-TS9-1-PRM-TST-0095-00 | 00 | ADV-095 | PRM | Trail mix test report of C20 CRS by Arab company for laboratories and soil (ACES) LAB. Material source Al-Fozan Ready-mix & cement products (Qassim Project) | TST |  | 2026-06-30 |  | 2026-07-09 | 9 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 96 | MLTX-02-003-ADV-TS9-1-PRM-TST-0096-00 | 00 | ADV-096 | PRM | Trail mix test report of C35 SRC by Arab company for laboratories and soil (ACES) LAB. Material source Al-Fozan Ready-mix & cement products (Qassim Project) | TST |  | 2026-06-30 |  | 2026-07-09 | 9 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 97 | MLTX-02-003-ADV-TS9-1-PRM-TST-0097-00 | 00 | ADV-097 | PRM | Test for compressive strength of concrete cylinder specimen at 7 days for concrete under foundation and slab concrete (shower and locker building) Grade C20 (Qassim Project) | TST |  | 2026-06-30 |  | 2026-07-09 | 9 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 98 | MLTX-02-003-ADV-TS9-1-PRM-TST-0098-00 | 00 | ADV-098 | PRM | Natural sand material sample test reports by Arab company for laboratories and soil (ACES) Material Source: Alsayegh Crusher - QASSIM | TST |  | 2026-07-04 |  | 2026-07-12 | 8 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 99 | MLTX-02-003-ADV-TS9-1-PRM-MPR-0099-00 | 00 | ADV-099 | PRM | Monthly Progress Report (MPR) of June 2026 – Qassim, Hail & Tabuk | MPR |  | 2026-07-04 |  | 2026-07-29 | 25 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 100 | MLTX-02-003-ADV-TS9-1-PRM-SCH-0100-00 | 01 | ADV-100 | PRM | Recovery Schedule – Qassim, Hail & Tabuk | SCH |  | 2026-07-05 |  | 2026-07-08 | 3 Days | C | 2026-07-08 | 2026-07-11 | 3 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 101 | MLTX-02-003-ADV-TS9-1-PRM-WPR-0101-00 | 00 | ADV-101 | PRM | Weekly Progress Report (WPR) – Qassim, Hail & Tabuk (Report No. # 14) | WPR |  | 2026-07-06 |  | 2026-07-07 | 1 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 102 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0102-00 | 00 | ADV-102 | PRM | Curriculum vitae (CV) - MUHAMMAD RIZWAN - HSE Officer - TABUK | CUV |  | 2026-07-07 |  | 2026-07-08 | 1 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 103 | MLTX-02-003-ADV-TS9-1-PRM-TST-0103-00 | 00 | ADV-103 | PRM | Test for compressive strength of concrete cylinder specimens at 7 days for lean concrete under curb stones (Parking area) Grade C20 (Qassim Project) | TST |  | 2026-07-07 |  | 2026-07-11 | 4 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 104 | MLTX-02-003-ADV-TS9-1-PRM-CAL-0104-00 | 00 | ADV-104 | PRM | DRAINAGE CALCULATION - TABUK | CAL |  | 2026-07-07 |  |  | 86 Days | UR | [25 empty] | 1 | Delayed with Egis
|  | 105 | MLTX-02-003-ADV-TS9-1-PRM-TST-0105-00 | 00 | ADV-105 | PRM | Test for the Compressive Strength of Concrete Cylinder Specimens at 7 Days for Lean Concrete (Grade C20) in the Toilet Area. (Tabuk Project) | TST |  | 2026-07-07 |  | 2026-07-09 | 2 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 106 | MLTX-02-003-ADV-TS9-1-PRM-TST-0106-00 | 00 | ADV-106 | PRM | Test for the Compressive Strength of Concrete Cylinder Specimens at 7 Days for Concrete (Grade C35) from the Concrete Trial Mix at Fugro-Suhaimi Lab.(Tabuk Project) | TST |  | 2026-07-07 |  | 2026-07-09 | 2 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 107 | MLTX-02-003-ADV-TS9-1-PRM-TST-0107-00 | 00 | ADV-107 | PRM | Test Results for Aggregate Base Course Material from Asas Almouhaileb Crusher, Tested by Fugro-Suhaimi Laboratory (Tabuk Project) | TST |  | 2026-07-11 |  | 2026-07-12 | 1 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 108 | MLTX-02-003-ADV-TS9-1-PRM-TST-0108-00 | 00 | ADV-108 | PRM | MIX DESIGN FOR BITUMINOUS BASE COURSE CLASS " A " MIX DESIGN FOR BITUMINOUS WEARING COURSE CLASS "B" (Qassim) | TST |  | 2026-07-11 |  | 2026-07-19 | 8 Days | C | [22 empty] | 1 |  |  |  | Revise & Resubmit
|  | 109 | MLTX-02-003-ADV-TS9-1-PRM-TST-0109-00 | 00 | ADV-109 | PRM | Test for compressive strength of concrete cylinder specimens at 28 days for concrete under foundation and slab (shower and locker building) Grade C20 (Qassim Project) | TST |  | 2026-07-12 |  | 2026-07-19 | 7 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 110 | MLTX-02-003-ADV-TS9-1-PRM-WPR-0110-00 | 00 | ADV-110 | PRM | Weekly Progress Report (WPR) – Qassim, Hail & Tabuk (Report No. # 15) | WPR |  | 2026-07-13 |  | 2026-07-29 | 16 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 111 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0111-00 | 00 | ADV-111 | PRM | Curriculum vitae (CV) - Muhammad Mubashar Munir - HSE Officer - QASSIM | CUV |  | 2026-07-13 |  | 2026-08-16 | 34 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 112 | MLTX-02-003-ADV-TS9-1-PRM-TST-0112-00 | 00 | ADV-112 | PRM | Test for compressive strength of concrete cylinder specimens at 7 days for lean concrete under curb stones (Parking area) Grade C20 (Qassim Project) | TST |  | 2026-07-15 |  | 2026-07-21 | 6 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 113 | MLTX-02-003-ADV-TS9-1-PRM-TST-0113-00 | 00 | ADV-113 | PRM | Test for compressive strength of concrete cylinder specimens at 7 days for lean concrete under curb stones (Parking area) Grade C20 (Qassim Project) | TST |  | 2026-07-15 |  | 2026-07-21 | 6 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 114 | MLTX-02-003-ADV-TS9-1-PRM-TST-0114-00 | 00 | ADV-114 | PRM | Sub Grade Material Sample Test Reports by Arab Company for Laboratories and Soil (ACES) Material Source: Alsayegh Crusher (Qassim) | TST |  | 2026-07-16 |  | 2026-07-22 | 6 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 115 | MLTX-02-003-ADV-TS9-1-PRM-TST-0115-00 | 00 | ADV-115 | PRM | Trail mix test report (at 28 days) of C20 CRS by Arab company for laboratories and soil (ACES) LAB. Material source Al-Fozan Ready-mix & cement products (Qassim Project) | TST |  | 2026-07-18 |  | 2026-07-22 | 4 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 116 | MLTX-02-003-ADV-TS9-1-PRM-TST-0116-00 | 00 | ADV-116 | PRM | Trail mix test report of C35 SRC (at 28 days) by Arab company for laboratories and soil (ACES) LAB. Material source Al-Fozan Ready-mix & cement products (Qassim Project) | TST |  | 2026-07-18 |  | 2026-07-22 | 4 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 117 | MLTX-02-003-ADV-TS9-1-PRM-TST-0117-00 | 00 | ADV-117 | PRM | Test for compressive strength of concrete cylinder specimens at 7 days for concrete for foundation and slab concrete (shower and locker building) Grade C35 (Qassim Project) | TST |  | 2026-07-18 |  | 2026-07-22 | 4 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 118 | MLTX-02-003-ADV-TS9-1-PRM-TST-0118-00 | 00 | ADV-118 | PRM | Test for compressive strength of concrete cylinder specimens at 28 days for concrete for foundation and slab concrete (shower and locker building) Grade C35 (Qassim Project) | TST |  | 2026-07-18 |  | 2026-07-22 | 4 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 119 | MLTX-02-003-ADV-TS9-1-PRM-TST-0119-00 | 00 | ADV-119 | PRM | 7-Day Compressive Strength Test of Grade C35 Concrete Cylinder Specimens for the Toilet Area Slab-on-Grade, Playground Project at (Fugro-Suhaimi Laboratory) Tabuk Project | TST |  | 2026-07-18 |  | 2026-07-18 | 0 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 120 | MLTX-02-003-ADV-TS9-1-PRM-WPR-0120-00 | 00 | ADV-120 | PRM | Weekly Progress Report (WPR) – Qassim, Hail & Tabuk (Report No. # 16) | WPR |  | 2026-07-20 |  | 2026-07-22 | 2 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 121 | MLTX-02-003-ADV-TS9-1-PRM-TST-0121-00 | 00 | ADV-121 | PRM | TESTS REPORT FOR SAMPLE (BACKFILLING: SUBBASE, SUBGRADE, BASE COURSE) FROM LABOURATY RGF (HAIL) | TST |  | 2026-07-21 |  | 2026-07-26 | 5 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 122 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0122-00 | 00 | ADV-122 | PRM | Curriculum vitae (CV) - MALIK TAHREEM UL HAQ - HSE Officer - Hail | CUV |  | 2026-07-22 |  | 2026-08-02 | 11 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 123 | MLTX-02-003-ADV-TS9-1-PRM-WPR-0123-00 | 00 | ADV-123 | PRM | Weekly Progress Report (WPR) – Qassim, Hail & Tabuk (Report No. # 17) | WPR |  | 2026-07-27 |  | 2026-07-29 | 2 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 124 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0124-00 | 00 | ADV-124 | PRM | Curriculum vitae (CV) - MUHAMMATHU SASNAS NAJIMUDEEN - Quantity Surveyor (QS) | CUV |  | 2026-07-27 |  | 2026-07-28 | 1 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 125 | MLTX-02-003-ADV-TS9-1-PRM-TST-0125-00 | 00 | ADV-125 | PRM | Test for the Compressive Strength of Concrete Cylinder Specimens at 28 Days for Concrete (Grade C35) from the Concrete Trial Mix at Fugro-Suhaimi Lab (Tabuk Project) | TST |  | 2026-07-29 |  | 2026-08-04 | 6 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 126 | MLTX-02-003-ADV-TS9-1-PRM-TST-0126-00 | 00 | ADV-126 | PRM | Test for the Compressive Strength of Concrete Cylinder Specimens at 28 Days for Lean Concrete (Grade C20) in the Toilet Area (Tabuk Project) | TST |  | 2026-07-29 |  | 2026-08-13 | 15 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 127 | MLTX-02-003-ADV-TS9-1-PRM-MPR-0127-00 | 00 | ADV-127 | PRM | Monthly Progress Report (MPR) of July 2026 –Qassim, Hail & Tabuk | MPR |  | 2026-07-30 |  |  | 63 Days | UR | [25 empty] | 1 | Delayed with Egis
|  | 128 | MLTX-02-003-ADV-TS9-1-PRM-SAM-0128-00 | 00 | ADV-128 | PRM | Material Sample of “Saudi Ceramics” For Ceramic Tiles (Qassim, Hail and Tabuk) - Ceramic Tile for Walls 30*60*0.9 cm - Ceramic Tile for Floor 30*30*0.9 cm | SAM |  | 2026-07-30 |  | 2026-08-15 | 16 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 129 | MLTX-02-003-ADV-TS9-1-PRM-WPR-0129-00 | 00 | ADV-129 | PRM | Weekly Progress Report (WPR) – Qassim, Hail & Tabuk (Report No. # 18) | WPR |  | 2026-08-03 |  | 2026-08-05 | 2 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 130 | MLTX-02-003-ADV-TS9-1-PRM-TST -0130-00 | 00 | ADV-130 | PRM | Test for compressive strength of concrete cylinder specimens at 7 days for Concrete Beam and Columns (Toilet Building) Grade C35 (Tabuk Project) | TST |  | 2026-08-04 |  | 2026-08-09 | 5 Days | A | [20 empty] | 1 | [5 empty] | Approved
|  | 131 | MLTX-02-003-ADV-TS9-1-PRM-WPR-0131-00 | 00 | ADV-131 | PRM | Weekly Progress Report (WPR) – Qassim, Hail & Tabuk (Report No. # 19) | WPR |  | 2026-08-10 |  | 2026-08-12 | 2 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 132 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0132-00 | 00 | ADV-132 | PRM | Curriculum vitae (CV) – Jayasundara Mudiyanselage Kanishka Bandara – Planning Engineer | CUV |  | 2026-08-10 |  | 2026-08-19 | 9 Days | C | [22 empty] | 1 |  |  |  | Revise & Resubmit
|  | 133 | MLTX-02-003-ADV-TS9-1-PRM-TST-0133-00 | 00 | ADV-133 | PRM | Test for compressive strength of concrete cylinder specimens at 28 days for RCC Slab and Foundation (Toilet Building) Grade C35 (Tabuk Project) | TST |  | 2026-08-13 |  | 2026-08-13 | 0 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 134 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0134-00 | 00 | ADV-134 | PRM | Curriculum vitae (CV) – MO’MEN ELSAID ABO ELMAATY - QC Engineer | CUV |  | 2026-08-13 |  | 2026-08-24 | 11 Days | C | [22 empty] | 1 |  |  |  | Revise & Resubmit
|  | 135 | MLTX-02-003-ADV-TS9-1-PRM-SAM-0135-00 | 00 | ADV-135 | PRM | Material Sample of “RAWAI AL BASATIN COMPANY” Walking path and bike path surface (Blue and Red) Material (Qassim, Hail and Tabuk) | SAM |  | 2026-08-17 |  |  | 45 Days | UR | [25 empty] | 1 | Delayed with Egis
|  | 136 | MLTX-02-003-ADV-TS9-1-PRM-SAM-0136-00 | 00 | ADV-136 | PRM | Sample of “Saudi Ceramics” For Ceramic Tiles (Qassim, Hail and Tabuk) 1. Ceramic Tile for Floor 60*60*1 cm | SAM |  | 2026-08-17 |  | 2026-08-24 | 7 Days | C | [22 empty] | 1 |  |  |  | Revise & Resubmit
|  | 137 | MLTX-02-003-ADV-TS9-1-PRM-SAM-0137-00 | 01 | ADV-137 | PRM | Material Samples of “RAWAI AL BASATIN COMPANY” Artificial Grass (Qassim, Hail and Tabuk) | SAM |  | 2026-08-17 |  | 2026-08-24 | 7 Days | C | 2026-09-05 |  | 26 Days | UR | [21 empty] | 1 | Delayed with Egis
|  | 138 | MLTX-02-003-ADV-TS9-1-PRM-SAM-0138-00 | 00 | ADV-138 | PRM | Material Samples for “BRC Industrial Saudia Co.” Chain Link Fence and Gate (Qassim, Hail and Tabuk) | SAM |  | 2026-08-17 |  | 2026-08-24 | 7 Days | C | [22 empty] | 1 |  |  |  | Revise & Resubmit
|  | 139 | MLTX-02-003-ADV-TS9-1-PRM-SAM-0139-00 | 00 | ADV-139 | PRM | Material Sample of “RAWAI AL BASATIN COMPANY” Tartan Floor Rubber Tiles 50*50*40 MM Blue Color (Qassim, Hail and Tabuk) | SAM |  | 2026-08-17 |  | 2026-09-03 | 17 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 140 | MLTX-02-003-ADV-TS9-1-PRM-WPR-0140-00 | 00 | ADV-140 | PRM | Weekly Progress Report (WPR) – Qassim, Hail & Tabuk (Report No. # 20) | WPR |  | 2026-08-17 |  |  | 45 Days | UR | [25 empty] | 1 | Delayed with Egis
|  | 141 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0141-00 | 00 | ADV-141 | PRM | Curriculum vitae (CV) – AFSAR AL ATHEEP - QUANTITY SURVEYOR | CUV |  | 2026-08-19 |  | 2026-08-20 | 1 Days | C | [22 empty] | 1 |  |  |  | Revise & Resubmit
|  | 142 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0142-00 | 00 | ADV-142 | PRM | Curriculum vitae (CV) – Mohammed Ibrahim Ahmed – QAQC Engineer | CUV |  | 2026-08-22 |  | 2026-09-01 | 10 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 143 | MLTX-02-003-ADV-TS9-1-PRM-CAL-0143-00 | 00 | ADV-143 | PRM | IRRIGATION TANK DESIGN CACULATIONS - HAIL | CAL |  | 2026-08-22 |  | 2026-08-29 | 7 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 144 | MLTX-02-003-ADV-TS9-1-PRM-WPR-0144-00 | 00 | ADV-144 | PRM | Weekly Progress Report (WPR) – Qassim, Hail & Tabuk (Report No. # 21) | WPR |  | 2026-08-24 |  | 2026-08-26 | 2 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 145 | MLTX-02-003-ADV-TS9-1-PRM-WPR-0145-00 | 00 | ADV-145 | PRM | Weekly Progress Report (WPR) – Qassim, Hail & Tabuk (Report No. # 22) | WPR |  | 2026-08-31 |  |  | 31 Days | UR | [25 empty] | 1 | Delayed with Egis
|  | 146 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0146-00 | 00 | ADV-146 | PRM | Curriculum vitae (CV) – MOSAB ABDELMOUNIM EDRES - Planning Engineer | CUV |  | 2026-09-03 |  | 2026-09-13 | 10 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 147 | MLTX-02-003-ADV-TS9-1-PRM-MPR-0147-00 | 00 | ADV-147 | PRM | Monthly Progress Report (MPR) of August 2026 – Qassim, Hail & Tabuk | MPR |  | 2026-09-03 |  |  | 28 Days | UR | [25 empty] | 1 | Delayed with Egis
|  | 148 | MLTX-02-003-ADV-TS9-1-PRM-TST-0148-00 | 00 | ADV-148 | PRM | Test for compressive strength of concrete cylinder specimens at 7 days for Airdome Foundation (AIRDOME) Grade C20 (Tabuk Project) | TST |  | 2026-09-07 |  | 2026-09-08 | 1 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 149 | MLTX-02-003-ADV-TS9-1-PRM-TST-0149-00 | 00 | ADV-149 | PRM | Test for compressive strength of concrete cylinder specimens at 7 days for Airdome Foundation (AIRDOME) Grade C20 (Tabuk Project) | TST |  | 2026-09-07 |  | 2026-09-08 | 1 Days | A | [20 empty] | 1 | [5 empty] | Approved
|  | 150 | MLTX-02-003-ADV-TS9-1-PRMTST-0150-00 | 00 | ADV-150 | PRM | Test for compressive strength of concrete cylinder specimens at 7 days for Airdome Foundation Base (AIRDOME) Grade C35 (Tabuk Project) | TST |  | 2026-09-07 |  | 2026-09-20 | 13 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 151 | MLTX-02-003-ADV-TS9-1-PRM-WPR-0151-00 | 00 | ADV-151 | EPM | Weekly Progress Report (WPR) – Qassim, Hail & Tabuk (Report No. # 23) | WPR |  | 2026-09-07 |  |  | 24 Days | UR | [25 empty] | 1 | Delayed with Egis
|  | 152 | MLTX-02-003-ADV-TS9-1-PRM-CUV-0152-00 | 00 | ADV-152 | PRM | Document Submittal of Curriculum vitae (CV) – Henry Avila Requintoza – QA/QC Engineer | CUV |  | 2026-09-13 |  |  | 18 Days | UR | [25 empty] | 1 | Delayed with Egis
|  | 153 | MLTX-02-003-ADV-TS9-1-PRM-WPR-0153-00 | 00 | ADV-153 | EPM | Weekly Progress Report (WPR) – Qassim, Hail & Tabuk (Report No. # 24) | WPR |  | 2026-09-14 |  | 2026-09-16 | 2 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 154 | MLTX-02-003-ADV-TS9-1-PRM-TST-0154-00 | 00 | ADV-154 | EPM | 7-Day Compressive Strength Test Report of Grade C35 Concrete Cylinder Specimens for the Footing For GRP Tank, Playground Project at (Fugro-Suhaimi Laboratory)-Tabuk project | TST |  | 2026-09-15 |  | 2026-09-16 | 1 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 155 | MLTX-02-003-ADV-TS9-1-PRM-TST-0155-00 | 00 | ADV-155 | EPM | Trail mix test report of Bituminous base course class B by Arab company for laboratories and soil (ACES) LAB. Material source Expert Future Asphalt Patch plant (BIN ABDIN) TABUK | TST |  | 2026-09-17 |  |  | 14 Days | UR | [25 empty] | 1 | Delayed with Egis
|  | 156 | MLTX-02-003-ADV-TS9-1-PRM-TST-0156-00 | 00 | ADV-156 | EPM | Trail mix test report of Bituminous Wearing course class C by Arab company for laboratories and soil (ACES) LAB. Material source Expert Future Asphalt Patch plant (BIN ABDIN) TABUK | TST |  | 2026-09-17 |  |  | 14 Days | UR | [25 empty] | 1 | Delayed with Egis
|  | 157 | MLTX-02-003-ADV-TS9-1-PRM-TST-0157-00 | 00 | ADV-157 | EPM | Trail mix test report of Bituminous Base course class B by Arab company for laboratories and soil (ACES) LAB. Material source Shibh Al Jazira Contracting Co. (SAJCO) (QASIM) | TST |  | 2026-09-17 |  | 2026-09-19 | 2 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 158 | MLTX-02-003-ADV-TS9-1-PRM-TST-0158-00 | 00 | ADV-158 | EPM | Trail mix test report of Bituminous Wearing course class C by Arab company for laboratories and soil (ACES) LAB. Material source Expert Future Asphalt Patch plant (BIN ABDIN) TABUK | TST |  | 2026-09-17 |  | 2026-09-19 | 2 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 159 | MLTX-02-003-ADV-TS9-1-PRM-WPR-0159-00 | 00 | ADV-159 | EPM | Weekly Progress Report (WPR) – Qassim, Hail & Tabuk (Report No. # 25) | WPR |  | 2026-09-21 |  |  | 10 Days | UR | [25 empty] | 1 | Delayed with Egis
|  | 160 | MLTX-02-003-ADV-TS9-1-PRM-TST -0160-00 | 00 | ADV-160 | EPM | Test for compressive strength of concrete cylinder specimens at 28 days for Airdome Foundation Base (AIRDOME) Grade C35 | TST |  | 2026-09-27 |  | 2026-09-28 | 1 Days | A | [20 empty] | 1 | [5 empty] | Approved
|  | 161 | MLTX-02-003-ADV-TS9-1-PRM-TST -0161-00 | 00 | ADV-161 | EPM | Test for compressive strength of concrete cylinder specimens at 7 days for Lean concrete for CURTAIN WALL AND SEPTIC TANK Grade C20 | TST |  | 2026-09-27 |  | 2026-09-28 | 1 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 162 | MLTX-02-003-ADV-TS9-1-PRM-TST -0162-00 | 00 | ADV-162 | EPM | Test for compressive strength of concrete cylinder specimens at 28 days for Airdrome Foundation C-20 | TST |  | 2026-09-27 |  | 2026-09-28 | 1 Days | B | [21 empty] | 1 |  |  |  |  | Approved with Comments
|  | 163 | MLTX-02-003-ADV-TS9-1-PRM-WPR-0163-00 | 00 | ADV-163 | EPM | Weekly Progress Report (WPR) – Qassim, Hail & Tabuk (Report No. # 26) | WPR |  | 2026-09-28 |  |  | 3 Days | UR | [24 empty] | 1 |  | Under Review
|  | 164 | MLTX-02-003-ADV-TS9-1-PRM-TST-0164-00 | 00 | ADV-164 | EPM | Test for compressive strength of concrete cylinder specimen at 7 And 28 days for concrete for Football court 2 Curb stones lean Grade C20 (Qassim) | TST |  | 2026-09-30 |  |  | 1 Days | UR | [24 empty] | 1 |  | Under Review
|  | 165 | MLTX-02-003-ADV-TS9-1-PRM-TST -0165-00 | 00 | ADV-165 | EPM | Test for compressive strength of concrete cylinder specimen at 7 And 28 days for concrete Tartan area 1,2,3,4 Curbstone lean Grade C20 | TST |  | 2026-09-30 |  |  | 1 Days | UR | [24 empty] | 1 |  | Under Review
|  | 166 | MLTX-02-003-ADV-TS9-1-PRM-TST -0166-00 | 00 | ADV-166 | EPM | Test for compressive strength of concrete cylinder specimen at 7 And 28 days for concrete Tartan area 2,3 Curbstone lean Grade C20 | TST |  | 2026-09-30 |  |  | 1 Days | UR | [24 empty] | 1 |  | Under Review
|  | 167 | MLTX-02-003-ADV-TS9-1-PRM-TST -0167-00 | 00 | ADV-167 | EPM | Test for compressive strength of concrete cylinder specimen at 7 And 28 days for concrete Tartan area 11, 12 and Court 2 Curbstone lean Grade C20 | TST |  | 2026-09-30 |  |  | 1 Days | UR | [24 empty] | 1 |  | Under Review
|  | 168 | MLTX-02-003-ADV-TS9-1-PRM-TST-0168-00 | 00 | ADV-168 | EPM | Test for compressive strength of concrete cylinder specimen at 7 And 28 days for concrete Tartan area 11, 12 and Court 2 Curbstone lean | TST |  | 2026-09-30 |  |  | 1 Days | UR | [24 empty] | 1 |  | Under Review
|  | 169 | MLTX-02-003-ADV-TS9-1-PRM-TST -0169-00 | 00 | ADV-169 | EPM | Test for compressive strength of concrete cylinder specimen at 7 And 28 days for Shower and locker building Beam and column Grade C35 | TST |  | 2026-09-30 |  |  | 1 Days | UR | [24 empty] | 1 |  | Under Review
|  | 170 | MLTX-02-003-ADV-TS9-1-PRM-TST -0170-00 | 00 | ADV-170 | EPM | Test for compressive strength of concrete cylinder specimen at 7 And 28 days for concrete Hunching Tartan area (1,2,3,4) Curbstone lean Grade C20 | TST |  | 2026-09-30 |  |  | 1 Days | UR | [24 empty] | 1 |  | Under Review
|  | 171 | MLTX-02-003-ADV-TS9-1-PRM-TST -0171-00 | 00 | ADV-171 | EPM | Test for compressive strength of concrete cylinder specimen at 7 And 28 days for Tartan area ,11, 12 &football court 2 CURBSTONES LEAN Hunching Grade C2 | TST |  | 2026-09-30 |  |  | 1 Days | UR | [24 empty] | 1 |  | Under Review
|  | 172 | MLTX-02-003-ADV-TS9-1-PRM-MPR-0172-00 | 00 | ADV-172 | PRM | Monthly Progress Report (MPR) of August 2026 – Qassim, Hail & Tabuk | MPR |  | 2026-10-01 |  |  | 0 Days | UR | [24 empty] | 1 |  | Under Review
Formulas:
Duration with Egis = IF([Actual Submission Date]="","",(IF([Date of Return Egis]="",TODAY()-[Actual Submission Date],[Date of Return Egis]-[Actual Submission Date])+0)) & " Days "
Note on L19: Mail send on 29-03-2026 to PMC
Note on L20: Mail send on 29-03-2026 to PMC
Note on L21: Mail send on 29-03-2026 to PMC
Note on L22: Mail send on 29-03-2026 to PMC
Note on L23: Mail send on 29-03-2026 to PMC
Note on N100: Rceived this reply from Abdul Majeed Alfaraj on whatsapp
Note on N107: Rceived this reply from Abdul Majeed Alfaraj on whatsapp
Note on N112: Rceived this reply from Abdul Majeed Alfaraj on whatsapp
Note on N123: Rceived this reply from Abdul Majeed Alfaraj on whatsapp

## Design Dwgs (hidden)
[26 empty] | Approved = A |  | 0
[5 empty] | P030 - (MLTX-02-003) - Playgrounds Initiative at (Qassim Oasis , Hail and Tabuk Industrial City) | [20 empty] | Approved with Comments = B |  | 0
[26 empty] | Revise & Resubmit = C |  | 0
[5 empty] | Design Drawings (DD) - Submissions & Approvals | [20 empty] | Under PMC Review / For Info. / Rejected / Cancelled / Recalled = D |  | 0
[26 empty] | Under Review = UR |  | 0
[26 empty] | Delayed with ADV |  | 0
[26 empty] | Delayed with Egis |  | 0
[26 empty] | Total Number of Submittals |  | 0
[11 empty] | 1st Submittal - Rev-00 |  |  |  |  | 2nd Submittal - Rev-01 |  |  |  | 3rd Submittal - Rev-02 |  |  |  | 4rd Submittal - Rev-03 |  |  |  | 2026-10-01
Transmittle # | Location Area / Floor | SI No. | Transmittal Number | Latest Rev.# | ADV Reference Number | Doc Type | Drawing Number | Drawing Description | Discipline | Site | Actual Submission Date | Delayed | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | A | B | C | D | UR | Delayed with Egis | Remarks
1
2
3
4
5
6
7
8
9
10

## RFI
[24 empty] | Approved = A |  | 0
[5 empty] | P030 - (MLTX-02-003) - Playgrounds Initiative at (Qassim Oasis , Hail and Tabuk Industrial City) | [18 empty] | Approved with Comments = B |  | 29
[24 empty] | Revise & Resubmit = C |  | 3
[5 empty] | Request for Information (RFI) - Submissions & Approvals | [18 empty] | Under PMC Review / For Info. / Rejected / Cancelled / Recalled = D |  | 0
[24 empty] | Under Review = UR |  | 0
[24 empty] | Delayed with ADV |  | 0
[24 empty] | Delayed with Egis |  | 1
[24 empty] | Total Number of Submittals |  | 33
[9 empty] | 1st Submittal - Rev-00 |  |  |  |  | 2nd Submittal - Rev-01 |  |  |  | 3rd Submittal - Rev-02 |  |  |  | 4th Submittal - Rev-03 |  |  |  | 2026-10-01
Transmittle # | Location Area / Floor | SI No. | Transmittal Number | Latest Rev.# | ADV Reference Number | Doc Type | Description / Subject | Discipline | Actual Submission Date | Delayed | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | A | B | C | D | UR | Delayed with Egis | Remarks
|  | 1 | MLTX-02-003-ADV-TS9-1-ARC-RFI-0001-00 | 01 | ADV-0001 | RFI | New Conflict After Revised Boundary - Hail | ARC | 2026-03-04 |  | 2026-03-08 | 4 Days | B | 2026-03-31 | 2026-04-08 | 8 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 2 | MLTX-02-003-ADV-TS9-1-ARC-RFI-0002-00 | 00 | ADV-0002 | RFI | Tabuk (Conflict with Under-Construction Building) | ARC | 2026-03-04 |  | 2026-03-12 | 8 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 3 | MLTX-02-003-ADV-TS9-1-STR-RFI-0003-00 | 00 | ADV-0003 | RFI | Pump Room STR Data Missing | STR | 2026-03-07 |  | 2026-03-09 | 2 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 4 | MLTX-02-003-ADV-TS9-1-MEC-RFI-0004-00 | 00 | ADV-0004 | RFI | Septic tank dimensions | MEC | 2026-03-09 |  | 2026-03-12 | 3 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 5 | MLTX-02-003-ADV-TS9-1-LSP-RFI-0005-00 | 00 | ADV-0005 | RFI | Tree Layout and Planting Details Clarification (BOQ Item 2.3.4) – Qassim, Hail & Tabuk | LSP | 2026-03-25 |  | 2026-04-04 | 10 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 6 | MLTX-02-003-ADV-TS9-1-LSP-RFI-0006-00 | 00 | ADV-0006 | RFI | Fertilizer Requirements and Soil Treatment Clarification – Qassim, Hail & Tabuk | LSP | 2026-03-25 |  | 2026-04-02 | 8 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 7 | MLTX-02-003-ADV-TS9-1-LSP-RFI-0007-00 | 00 | ADV-0007 | RFI | Clashes between existing light poles and sign bords with design of walk/Bike path – Qassim Project | LSP | 2026-04-20 |  | 2026-04-22 | 2 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 8 | MLTX-02-003-ADV-TS9-1-LSP-RFI-0008-00 | 02 | ADV-0008 | RFI | Missing Project Details and Specifications – Qassim, Hail and Tabuk | LSP | 2026-04-20 |  | 2026-04-21 | 1 Days | B | 2026-04-27 | 2026-04-29 | 2 Days | B | 2026-06-10 | 2026-07-12 | 32 Days | B | [5 empty] | 1 |  |  |  |  | Approved with Comments
|  | 9 | MLTX-02-003-ADV-TS9-1-GEN-RFI-0009-00 | 00 | ADV-0009 | RFI | Request for As-Built Drawings – Underground Utilities (Qassim, Hail & Tabuk) | GEN | 2026-04-28 |  | 2026-05-14 | 16 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 10 | MLTX-02-003-ADV-TS9-1-ARC-RFI-0010-00 | 01 | ADV-0010 | RFI | Qassim Parking level | ARC | 2026-05-12 |  | 2026-05-13 | 1 Days | B | 2026-05-19 | 2026-05-31 | 12 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 11 | MLTX-02-003-ADV-TS9-1-LSP-RFI-0011-00 | 00 | ADV-0011 | RFI | Stamped Concrete Section Detail | LSP | 2026-05-14 |  | 2026-05-20 | 6 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 12 | MLTX-02-003-ADV-TS9-1-LSP-RFI-0012-00 | 00 | ADV-0012 | RFI | Curbstone size | LSP | 2026-05-16 |  | 2026-05-18 | 2 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 13 | MLTX-02-003-ADV-TS9-1-CVL-RFI-0013-00 | 00 | ADV-0013 | RFI | Top Soil Removal (Qassim, Hail, Tabuk) | CVL | 2026-05-21 |  | 2026-06-01 | 11 Days | C | [14 empty] | 1 |  |  |  | Revise & Resubmit
|  | 14 | MLTX-02-003-ADV-TS9-1-SVY-RFI-0014-00 | 00 | ADV-0014 | RFI | Proposal for Site Levels (Qassim) | SVY | 2026-05-23 |  | 2026-05-23 | 0 Days | C | [14 empty] | 1 |  |  |  | Revise & Resubmit
|  | 15 | MLTX-02-003-ADV-TS9-1-GEN-RFI-0015-00 | 00 | ADV-0015 | RFI | Identical Drawings (Qassim, Hail and Tabuk) | GEN | 2026-06-01 |  | 2026-06-07 | 6 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 16 | MLTX-02-003-ADV-TS9-1-LSP-RFI-0016-00 | 01 | ADV-0016 | RFI | Plant Specifications (Qassim, Hail and Tabuk) | LSP | 2026-06-09 |  | 2026-06-11 | 2 Days | C | 2026-07-02 | 2026-08-02 | 31 Days | C | [10 empty] | 1 |  |  |  | Revise & Resubmit
|  | 17 | MLTX-02-003-ADV-TS9-1-LSP-RFI-0017-00 | 01 | ADV-0017 | RFI | Tartan Details (Qassim, Hail and Tabuk) | LSP | 2026-06-09 |  | 2026-06-11 | 2 Days | C | 2026-06-13 | 2026-06-25 | 12 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 18 | MLTX-02-003-ADV-TS9-1-CVL-RFI-0018-00 | 01 | ADV-0018 | RFI | Septic Tank Location (Qassim, Hail and Tabuk) | CVL | 2026-06-09 |  | 2026-06-15 | 6 Days | B | 2026-06-16 | 2026-06-21 | 5 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 19 | MLTX-02-003-ADV-TS9-1-CVL-RFI-0019-00 | 00 | ADV-0019 | RFI | Culvert (Hail) | CVL | 2026-06-17 |  | 2026-06-18 | 1 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 20 | MLTX-02-003-ADV-TS9-1-CVL-RFI-0020-00 | 00 | ADV-0020 | RFI | Water, Irrigation & Sewer Connections (Hail) | CVL | 2026-06-22 |  | 2026-06-29 | 7 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 21 | MLTX-02-003-ADV-TS9-1-CVL-RFI-0021-00 | 00 | ADV-0021 | RFI | Water, Irrigation & Sewer Connections (Tabuk) | CVL | 2026-06-22 |  |  | 101 Days | UR | [17 empty] | 1 | Delayed with Egis
|  | 22 | MLTX-02-003-ADV-TS9-1-LSP-RFI-0022-00 | 00 | ADV-0022 | RFI | Area Surrounding Padel Court (Qassim, Tabuk) | LSP | 2026-06-23 |  | 2026-06-25 | 2 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 23 | MLTX-02-003-ADV-TS9-1-LSP-RFI-0023-00 | 00 | ADV-0023 | RFI | FINISH FLOOR AND INTERNAL ROAD LEVELS (HAIL) | LSP | 2026-06-24 |  | 2026-07-02 | 8 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 24 | MLTX-02-003-ADV-TS9-1-LSP-RFI-0024-00 | 00 | ADV-0024 | RFI | Internal Football Playground Fence (Qassim, Tabuk) | LSP | 2026-06-27 |  | 2026-07-02 | 5 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 25 | MLTX-02-003-ADV-TS9-1-SVY-RFI-0025-00 | 01 | ADV-0025 | RFI | GRP Tank Location (Hail) | SVY | 2026-07-09 |  | 2026-07-11 | 2 Days | C | 2026-07-11 | 2026-07-14 | 3 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 26 | MLTX-02-003-ADV-TS9-1-STR-RFI-0026-00 | 00 | ADV-0026 | RFI | Vapor Barrier beneath the Concrete Slab under Basketball, Padel and Tartan Areas (Qassim, Hail and Tabuk) | STR | 2026-07-09 |  | 2026-07-12 | 3 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 27 | MLTX-02-003-ADV-TS9-1-LSP-RFI-0027-00 | 00 | ADV-0027 | RFI | Interlocking Paver Thickness for Qassim Park and Project-Wide Standards (Qassim) | LSP | 2026-07-20 |  | 2026-07-23 | 3 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 28 | MLTX-02-003-ADV-TS9-1-STR-RFI-0028-00 | 01 | ADV-0028 | RFI | 2 IRRIGATION GROUND WATER TANK (INCLUDING BOOSTER PUMP EACH) (Hail and Tabuk) | STR | 2026-07-21 |  | 2026-08-02 | 12 Days | C | 2026-08-04 | 2026-08-19 | 15 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 29 | MLTX-02-003-ADV-TS9-1-LSP-RFI-0029-00 | 00 | ADV-0029 | RFI | Land scape Details (Qassim) | LSP | 2026-07-22 |  | 2026-07-30 | 8 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 30 | MLTX-02-003-ADV-TS9-1-MEC-RFI-0030-00 | 00 | ADV-0030 | RFI | Clarification on Firefighting System Requirements for Air Dome (Qassim and Tabuk) | MEC | 2026-07-25 |  | 2026-07-29 | 4 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 31 | MLTX-02-003-ADV-TS9-1-LSP-RFI-0031-00 | 00 | ADV-0031 | RFI | Asphalt Specifications Below Artificial Grass Football Court (Qassim, Hail and Tabuk) | LSP | 2026-07-27 |  | 2026-08-10 | 14 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 32 | MLTX-02-003-ADV-TS9-1-ELE-RFI-0032-00 | 00 | ADV-0032 | RFI | RELOCATING CABLE GUY BASE IN HAIL PROJECT | ELE | 2026-09-03 |  | 2026-09-14 | 11 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 33 | MLTX-02-003-ADV-TS9-1-LSP-RFI-0033-00 | 00 | ADV-0033 | RFI | UNKNOWN ELEMENT NEED TO BE IDENTIFIED | LSP | 2026-09-16 |  | 2026-09-22 | 6 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
35
36
37
38
39
40
41
Formulas:
Duration with Egis = IF([Actual Submission Date]="","",(IF([Date of Return Egis]="",TODAY()-[Actual Submission Date],[Date of Return Egis]-[Actual Submission Date])+0)) & " Days "

## Shop Dwgs
[24 empty] | Approved = A |  | 36
[5 empty] | P030 - (MLTX-02-003) - Playgrounds Initiative at (Qassim Oasis , Hail and Tabuk Industrial City) | [18 empty] | Approved with Comments = B |  | 267
[24 empty] | Revise & Resubmit = C |  | 18
[5 empty] | Shop Drawings (SDW) - Submissions & Approvals | [18 empty] | Under PMC Review / For Info. / Rejected / Cancelled / Recalled = D |  | 0
[24 empty] | Under Review = UR |  | 10
[24 empty] | Delayed with ADV |  | 0
[24 empty] | Delayed with Egis |  | 12
[24 empty] | Total Number of Submittals |  | 343
[11 empty] | 1st Submittal - Rev-00 |  |  |  |  | 2nd Submittal - Rev-01 |  |  |  | 3rd Submittal - Rev-02 |  |  |  |  | 4th Submittal - Rev-03 |  |  |  | 5th Submittal - Rev-03 |  |  | 2026-10-01
Transmittle # | Location Area / Floor | SI No. | Transmittal Number | Latest Rev.# | ADV Reference Number | Doc Type | MLTX-02-003-QSM3-ADV-TS9-1-LS-SDW-0103-00 | Drawing Description | Discipline | Site | Actual Submission Date | Delayed | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | A | B | C | D | UR | Delayed with Egis | Remarks
|  | 1 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0001-00 | 00 | ADV-0001 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-AR-SDW-0001-00 | TABUK-SITE LAYOUT | ARC | Tabuk | 2026-03-11 |  | 2026-04-11 | 31 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 2 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0001-00 | 00 | ADV-0001 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-AR-SDW-0002-00 | TABUK MOBILIZATION PLAN SITE OFFICE & LAYDOWN AREA | ARC | Tabuk | 2026-03-11 |  | 2026-04-11 | 31 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 3 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0002-00 | 01 | ADV-0002 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-AR-SDW-0001-00 | QASSIM SITE LAYOUT | ARC | Qassim | 2026-03-11 |  | 2026-03-17 | 6 Days | C | 2026-03-26 | 2026-04-13 | 18 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 4 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0002-00 | 01 | ADV-0002 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-AR-SDW-0002-00 | QASSIM MOBILIZATION PLAN SITE OFFICE & LAYDOWN AREA | ARC | Qassim | 2026-03-11 |  | 2026-03-17 | 6 Days | C | 2026-03-26 | 2026-04-13 | 18 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 5 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0003-00 | 03 | ADV-0003 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-AR-SDW-0001-00 | HAIL-SITE LAYOUT | ARC | Hail | 2026-03-11 |  | 2026-03-18 | 7 Days | C | 2026-03-28 | 2026-03-29 | 1 Days | C | 2026-03-31 | 2026-04-07 | 7 Days | C | 2026-04-08 | 2026-04-09 | 1 Days | B | [5 empty] | 1 |  |  |  |  | Approved with Comments
|  | 6 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0003-00 | 03 | ADV-0003 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-AR-SDW-0002-00 | MOBILIZATION PLAN SITE OFFICE & LAYDOWN AREA | ARC | Hail | 2026-03-11 |  | 2026-03-18 | 7 Days | C | 2026-03-28 | 2026-03-29 | 1 Days | C | 2026-03-31 | 2026-04-07 | 7 Days | C | 2026-04-08 | 2026-04-09 | 1 Days | B | [5 empty] | 1 |  |  |  |  | Approved with Comments
|  | 7 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0004-00 | 01 | ADV-0004 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-AR-SDW-0003-00 | TABUK-SIGN BOARD LAYOUT | ARC | Tabuk | 2026-03-11 |  | 2026-03-31 | 20 Days | B | 2026-05-03 | 2026-05-05 | 2 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 8 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0005-00 | 00 | ADV-0005 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-AR-SDW-0003-00 | QASSIM SIGN BOARD LAYOUT | ARC | Qassim | 2026-03-11 |  | 2026-03-31 | 20 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 9 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0006-00 | 00 | ADV-0006 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-AR-SDW-0003-00 | HAIL-SIGN BOARD LAYOUT | ARC | Hail | 2026-03-11 |  | 2026-03-17 | 6 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 10 | MLTX-02-003-ADV-TS9-1-SVY-SDW-0007-00 | 02 | ADV-0007 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-SVY-SDW-0001-00 | SITE LAYOUT - TABUK (TOPOGRAPHIC SURVEY) | SVY | Tabuk | 2026-03-24 |  | 2026-03-25 | 1 Days | C | 2026-04-12 | 2026-04-19 | 7 Days | C | 2026-04-22 | 2026-04-30 | 8 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 11 | MLTX-02-003-ADV-TS9-1-SVY-SDW-0008-00 | 00 | ADV-0008 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-SVY-SDW-0001-00 | SITE LAYOUT - QASSIM (TOPOGRAPHIC SURVEY) | SVY | Qassim | 2026-03-24 |  | 2026-04-09 | 16 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 12 | MLTX-02-003-ADV-TS9-1-SVY-SDW-0009-00 | 01 | ADV-0009 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-SVY-SDW-0001-00 | SITE LAYOUT - HAIL (TOPOGRAPHIC SURVEY) | SVY | Hail | 2026-03-24 |  | 2026-03-26 | 2 Days | C | 2026-04-06 | 2026-04-06 | 0 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 13 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0010-00 | 01 | ADV-0010 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-AR-SDW-0004-00 | Hail - Site Development Layout | ARC | Hail | 2026-03-24 |  | 2026-03-26 | 2 Days | C | 2026-04-07 | 2026-04-11 | 4 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 14 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0011-00 | 03 | ADV-0011 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-AR-SDW-0004-00 | Qassim Oasis - Site Development Layout | ARC | Qassim | 2026-03-24 |  | 2026-04-09 | 16 Days | B | 2026-04-29 | 2026-05-10 | 11 Days | C | 2026-06-04 | 2026-06-06 | 2 Days | B | 2026-07-21 | 2026-07-27 | 6 Days | C | [6 empty] | 1 |  |  |  | Revise & Resubmit
|  | 15 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0012-00 | 01 | ADV-0012 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-AR-SDW-0004-00 | Tabuk - Site Development Layout | ARC | Tabuk | 2026-03-24 |  | 2026-04-07 | 14 Days | C | 2026-04-07 | 2026-04-11 | 4 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 16 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0013-00 | 03 | ADV-0013 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-AR-SDW-0100-00 | HAIL-TOILET FLOOR LAYOUT & DETAILS | ARC | Hail | 2026-03-24 |  | 2026-03-25 | 1 Days | C | 2026-04-28 | 2026-05-07 | 9 Days | C | 2026-06-02 | 2026-06-07 | 5 Days | C | 2026-06-09 | 2026-06-16 | 7 Days | B | [5 empty] | 1 |  |  |  |  | Approved with Comments
|  | 17 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0013-00 | 03 | ADV-0013 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-AR-SDW-0101-00 | HAIL-TOILET FLOORING LAYOUT & DETAILS | ARC | Hail | 2026-03-24 |  | 2026-03-25 | 1 Days | C | 2026-04-28 | 2026-05-07 | 9 Days | C | 2026-06-02 | 2026-06-07 | 5 Days | C | 2026-06-09 | 2026-06-16 | 7 Days | B | [5 empty] | 1 |  |  |  |  | Approved with Comments
|  | 18 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0013-00 | 01 | ADV-0013 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-AR-SDW-0102-00 | HAIL-TOILET CEILING LAYOUT & DETAILS | ARC | Hail | 2026-03-24 |  | 2026-03-25 | 1 Days | C | 2026-04-28 | 2026-05-07 | 9 Days | C | [14 empty] | 1 |  |  |  | Revise & Resubmit
|  | 19 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0013-00 | 03 | ADV-0013 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-AR-SDW-0200-00 | HAIL-TOILET ELEVATIONS LAYOUT | ARC | Hail | 2026-03-24 |  | 2026-03-25 | 1 Days | C | 2026-04-28 | 2026-05-07 | 9 Days | C | 2026-06-02 | 2026-06-07 | 5 Days | C | 2026-06-09 | 2026-06-16 | 7 Days | B | [5 empty] | 1 |  |  |  |  | Approved with Comments
|  | 20 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0013-00 | 03 | ADV-0013 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-AR-SDW-0300-00 | HAIL-TOILET SECTIONS (01-02) LAYOUT | ARC | Hail | 2026-03-24 |  | 2026-03-25 | 1 Days | C | 2026-04-28 | 2026-05-07 | 9 Days | C | 2026-06-02 | 2026-06-07 | 5 Days | C | 2026-06-09 | 2026-06-16 | 7 Days | B | [5 empty] | 1 |  |  |  |  | Approved with Comments
|  | 21 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0013-00 | 03 | ADV-0013 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-AR-SDW-0301-00 | HAIL-TOILET SECTION (03) LAYOUT | ARC | Hail | 2026-03-24 |  | 2026-03-25 | 1 Days | C | 2026-04-28 | 2026-05-07 | 9 Days | C | 2026-06-02 | 2026-06-07 | 5 Days | C | 2026-06-09 | 2026-06-16 | 7 Days | B | [5 empty] | 1 |  |  |  |  | Approved with Comments
|  | 22 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0014-00 | 00 | ADV-0014 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-AR-SDW-0100-00 | QASSIM OASIS - TOILET FLOOR LAYOUT & DETAILS | ARC | Qassim | 2026-03-24 |  | 2026-04-18 | 25 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 23 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0014-00 | 00 | ADV-0014 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-AR-SDW-0101-00 | QASSIM OASIS-TOILET FLOORING LAYOUT & DETAILS | ARC | Qassim | 2026-03-24 |  | 2026-04-18 | 25 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 24 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0014-00 | 00 | ADV-0014 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-AR-SDW-0102-00 | QASSIM OASIS-TOILET CEILING LAYOUT & DETAILS | ARC | Qassim | 2026-03-24 |  | 2026-04-18 | 25 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 25 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0014-00 | 00 | ADV-0014 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-AR-SDW-0200-00 | QASSIM OASIS-TOILET ELEVATIONS LAYOUT | ARC | Qassim | 2026-03-24 |  | 2026-04-18 | 25 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 26 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0014-00 | 00 | ADV-0014 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-AR-SDW-0300-00 | QASSIM OASIS-TOILET SECTIONS (01-02) LAYOUT | ARC | Qassim | 2026-03-24 |  | 2026-04-18 | 25 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 27 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0014-00 | 00 | ADV-0014 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-AR-SDW-0301-00 | QASSIM OASIS-TOILET SECTION (03) LAYOUT | ARC | Qassim | 2026-03-24 |  | 2026-04-18 | 25 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 28 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0015-00 | 01 | ADV-0015 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-AR-SDW-0100-00 | TABUK - TOILET FLOOR LAYOUT & DETAILS | ARC | Tabuk | 2026-03-24 |  | 2026-04-09 | 16 Days | C | 2026-04-14 | 2026-04-15 | 1 Days | A | [12 empty] | 1 | [5 empty] | Approved
|  | 29 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0015-00 | 01 | ADV-0015 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-AR-SDW-0101-00 | TABUK-TOILET FLOORING LAYOUT & DETAILS | ARC | Tabuk | 2026-03-24 |  | 2026-04-09 | 16 Days | C | 2026-04-14 | 2026-04-15 | 1 Days | A | [12 empty] | 1 | [5 empty] | Approved
|  | 30 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0015-00 | 01 | ADV-0015 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-AR-SDW-0102-00 | TABUK-TOILET CEILING LAYOUT & DETAILS | ARC | Tabuk | 2026-03-24 |  | 2026-04-09 | 16 Days | C | 2026-04-14 | 2026-04-15 | 1 Days | A | [12 empty] | 1 | [5 empty] | Approved
|  | 31 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0015-00 | 01 | ADV-0015 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-AR-SDW-0200-00 | TABUK-TOILET ELEVATIONS LAYOUT | ARC | Tabuk | 2026-03-24 |  | 2026-04-09 | 16 Days | C | 2026-04-14 | 2026-04-15 | 1 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 32 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0015-00 | 01 | ADV-0015 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-AR-SDW-0300-00 | TABUK-TOILET SECTIONS (01-02) LAYOUT | ARC | Tabuk | 2026-03-24 |  | 2026-04-09 | 16 Days | C | 2026-04-14 | 2026-04-15 | 1 Days | A | [12 empty] | 1 | [5 empty] | Approved
|  | 33 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0015-00 | 01 | ADV-0015 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-AR-SDW-0301-00 | TABUK-TOILET SECTION (03) LAYOUT | ARC | Tabuk | 2026-03-24 |  | 2026-04-09 | 16 Days | C | 2026-04-14 | 2026-04-15 | 1 Days | A | [12 empty] | 1 | [5 empty] | Approved
|  | 34 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0016-00 | 01 | ADV-0016 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-AR-SDW-1001-00 | HAIL-DEMOLISHING LAYOUT | ARC | Hail | 2026-03-26 |  | 2026-03-28 | 2 Days | C | 2026-04-12 | 2026-04-15 | 3 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 35 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0017-00 | 00 | ADV-0017 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LS-SDW-0100-00 | QASSIM OASIS - PARK LAYOUT PLAN | LSP | Qassim | 2026-03-26 |  | 2026-04-18 | 23 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 36 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0017-00 | 00 | ADV-0017 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LS-SDW-0101-00 | QASSIM OASIS - PARK LAYOUT PLAN PART 1 of 3 | LSP | Qassim | 2026-03-26 |  | 2026-04-18 | 23 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 37 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0017-00 | 00 | ADV-0017 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LS-SDW-0102-00 | QASSIM OASIS - PARK LAYOUT PLAN PART 2 of 3 | LSP | Qassim | 2026-03-26 |  | 2026-04-18 | 23 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 38 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0017-00 | 00 | ADV-0017 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LS-SDW-0103-00 | QASSIM OASIS - PARK LAYOUT PLAN PART 3 of 3 | LSP | Qassim | 2026-03-26 |  | 2026-04-18 | 23 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 39 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0018-00 | 01 | ADV-0018 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LS-SDW-0401-00 | QASSIM OASIS - BIKE and WALKING LAYOUT | LSP | Qassim | 2026-03-26 |  | 2026-04-18 | 23 Days | C | 2026-06-08 | 2026-06-11 | 3 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 40 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0018-00 | 00 | ADV-0018 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LS-SDW-0402-00 | QASSIM OASIS - BIKE and WALKING LAYOUT PART 2 | LSP | Qassim | 2026-03-26 |  | 2026-04-18 | 23 Days | C | As per Engr. Khaled's instruction, this drawing has been cancelled, revision will not be submitted.
|  | 41 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0019-00 | 01 | ADV-0019 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LS-SDW-0403-00 | QASSIM OASIS - PAVING TILE LAYOUT PART 1 | LSP | Qassim | 2026-03-26 |  | 2026-04-18 | 23 Days | C | 2026-07-02 | 2026-07-12 | 10 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 42 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0019-00 | 01 | ADV-0019 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LS-SDW-0404-00 | QASSIM OASIS - PAVING TILE LAYOUT PART 2 | LSP | Qassim | 2026-03-26 |  | 2026-04-18 | 23 Days | C | 2026-07-02 | 2026-07-12 | 10 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 43 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0020-00 | 01 | ADV-0020 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LS-SDW-0405-00 | QASSIM OASIS - RUBBER SURFACE & FOOTBALL COURT LAYOUT - PART 1 of 3 | LSP | Qassim | 2026-03-26 |  | 2026-04-19 | 24 Days | C | 2026-06-29 | 2026-07-12 | 13 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 44 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0020-00 | 01 | ADV-0020 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LS-SDW-0406-00 | QASSIM OASIS - RUBBER SURFACE & FOOTBALL COURT LAYOUT - PART 2 of 3 | LSP | Qassim | 2026-03-26 |  | 2026-04-19 | 24 Days | C | 2026-06-29 | 2026-07-12 | 13 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 45 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0020-00 | 01 | ADV-0020 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LS-SDW-0407-00 | QASSIM OASIS - RUBBER SURFACE & FOOTBALL COURT LAYOUT - PART 3 of 3 | LSP | Qassim | 2026-03-26 |  | 2026-04-19 | 24 Days | C | 2026-06-29 | 2026-07-12 | 13 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 46 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0021-00 | 01 | ADV-0021 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LS-SDW-0408-00 | QASSIM OASIS - SEATING BENCH LAYOUT PART 1 | LSP | Qassim | 2026-03-26 |  | 2026-04-18 | 23 Days | C | 2026-06-30 | 2026-07-12 | 12 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 47 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0021-00 | 01 | ADV-0021 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LS-SDW-0409-00 | QASSIM OASIS - SEATING BENCH LAYOUT PART 2 | LSP | Qassim | 2026-03-26 |  | 2026-04-18 | 23 Days | C | 2026-06-30 | 2026-07-12 | 12 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 48 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0022-00 | 00 | ADV-0022 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LS-SDW-0410-00 | QASSIM OASIS - STAMPED CONCRETE LAYOUT PART 1 | LSP | Qassim | 2026-03-26 |  | 2026-04-28 | 33 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 49 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0022-00 | 00 | ADV-0022 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LS-SDW-0411-00 | QASSIM OASIS - STAMPED CONCRETE LAYOUT PART 2 | LSP | Qassim | 2026-03-26 |  | 2026-04-28 | 33 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 50 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0023-00 | 02 | ADV-0023 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-LS-SDW-0100-00 | HAIL-PARK LAYOUT PLAN | LSP | Hail | 2026-03-26 |  | 2026-03-28 | 2 Days | C | 2026-04-13 | 2026-04-19 | 6 Days | C | 2026-04-20 | 2026-04-22 | 2 Days | B | 2026-09-22 |  | 9 Days | UR | [8 empty] | 1 |  | Under Review
|  | 51 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0024-00 | 03 | ADV-0024 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-LS-SDW-0401-00 | HAIL-BIKE and WALKING LAYOUT | LSP | Hail | 2026-03-26 |  | 2026-03-28 | 2 Days | C | 2026-04-13 | 2026-04-20 | 7 Days | C | 2026-04-28 | 2026-05-04 | 6 Days | B | 2026-09-22 | 2026-09-28 | 6 Days | B | [5 empty] | 1 |  |  |  |  | Approved with Comments
|  | 52 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0025-00 | 02 | ADV-0025 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-LS-SDW-0402-00 | HAIL-PAVING TILE LAYOUT | LSP | Hail | 2026-03-26 |  | 2026-03-28 | 2 Days | C | 2026-04-13 | 2026-04-20 | 7 Days | C | 2026-04-28 | 2026-05-04 | 6 Days | B | 2026-09-22 | 2026-09-28 | 6 Days | B | [5 empty] | 1 |  |  |  |  | Approved with Comments
|  | 53 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0026-00 | 03 | ADV-0026 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-LS-SDW-0403-00 | HAIL-RUBBER SURFACE & FOOTBALL COURT LAYOUT | LSP | Hail | 2026-03-26 |  | 2026-03-28 | 2 Days | C | 2026-04-13 | 2026-04-20 | 7 Days | C | 2026-04-28 | 2026-05-04 | 6 Days | B | 2026-09-24 | 2026-09-28 | 4 Days | B | [5 empty] | 1 |  |  |  |  | Approved with Comments
|  | 54 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0027-00 | 02 | ADV-0027 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-LS-SDW-0404-00 | HAIL-SEATING BENCH LAYOUT | LSP | Hail | 2026-03-26 |  | 2026-03-28 | 2 Days | C | 2026-04-13 | 2026-04-20 | 7 Days | C | 2026-04-28 | 2026-05-04 | 6 Days | B | 2026-09-24 | 2026-09-28 | 4 Days | B | [5 empty] | 1 |  |  |  |  | Approved with Comments
|  | 55 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0028-00 | 02 | ADV-0028 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-LS-SDW-0405-00 | HAIL-STAMPED CONCRETE LAYOUT | LSP | Hail | 2026-03-26 |  | 2026-03-28 | 2 Days | C | 2026-04-13 | 2026-04-20 | 7 Days | C | 2026-04-28 | 2026-05-04 | 6 Days | B | 2026-09-24 |  | 7 Days | UR | [8 empty] | 1 |  | Under Review
|  | 56 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0029-00 | 00 | ADV-0029 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-MEC-SDW-0001-00 | GENERAL NOTES, LEGENDS, SYMBOLS & ABBREVIATIONS HVAC | MEC | Qassim | 2026-03-30 |  | 2026-04-05 | 6 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 57 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0029-00 | 00 | ADV-0029 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-MEC-SDW-0002-00 | GENERAL INSTRUMENTATION & CONTROL | MEC | Qassim | 2026-03-30 |  | 2026-04-05 | 6 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 58 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0029-00 | 00 | ADV-0029 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-MEC-SDW-0003-00 | TYPICAL GROUND FLOOR PLAN HVAC | MEC | Qassim | 2026-03-30 |  | 2026-04-05 | 6 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 59 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0029-00 | 00 | ADV-0029 | SDW | MLTX-02-003-QSM2-ADV-TS9-1-MEC-SDW-0004-00 | GENERAL MISCELLANEOUS DETAILS - HVAC | MEC | Qassim | 2026-03-30 |  | 2026-04-05 | 6 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 60 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0029-00 | 00 | ADV-0029 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-MEC-SDW-0005-00 | GENERAL MISCELLANEOUS DETAILS - HVAC | MEC | Qassim | 2026-03-30 |  | 2026-04-05 | 6 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 61 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0029-00 | 00 | ADV-0029 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-MEC-SDW-0006-00 | GENERAL MISCELLANEOUS DETAILS - HVAC | MEC | Qassim | 2026-03-30 |  | 2026-04-05 | 6 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 62 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0030-00 | 00 | ADV-0030 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-MEC-SDW-0001-00 | GENERAL NOTES, LEGENDS, SYMBOLS & ABBREVIATIONS HVAC | MEC | Tabuk | 2026-03-30 |  | 2026-04-01 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 63 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0030-00 | 00 | ADV-0030 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-MEC-SDW-0002-00 | GENERAL INSTRUMENTATION & CONTROL | MEC | Tabuk | 2026-03-30 |  | 2026-04-01 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 64 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0030-00 | 00 | ADV-0030 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-MEC-SDW-0003-00 | TYPICAL GROUND FLOOR PLAN HVAC | MEC | Tabuk | 2026-03-30 |  | 2026-04-01 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 65 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0030-00 | 00 | ADV-0030 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-MEC-SDW-0004-00 | GENERAL MISCELLANEOUS DETAILS - HVAC | MEC | Tabuk | 2026-03-30 |  | 2026-04-01 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 66 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0030-00 | 00 | ADV-0030 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-MEC-SDW-0005-00 | GENERAL MISCELLANEOUS DETAILS - HVAC | MEC | Tabuk | 2026-03-30 |  | 2026-04-01 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 67 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0030-00 | 00 | ADV-0030 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-MEC-SDW-0006-00 | GENERAL MISCELLANEOUS DETAILS - HVAC | MEC | Tabuk | 2026-03-30 |  | 2026-04-01 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 68 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0031-00 | 00 | ADV-0031 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-MEC-SDW-0001-00 | GENERAL NOTES, LEGENDS, SYMBOLS & ABBREVIATIONS HVAC | MEC | Hail | 2026-04-02 |  | 2026-04-07 | 5 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 69 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0031-00 | 00 | ADV-0031 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-MEC-SDW-0002-00 | GENERAL INSTRUMENTATION & CONTROL | MEC | Hail | 2026-04-02 |  | 2026-04-07 | 5 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 70 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0031-00 | 00 | ADV-0031 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-MEC-SDW-0003-00 | TYPICAL GROUND FLOOR PLAN HVAC | MEC | Hail | 2026-04-02 |  | 2026-04-07 | 5 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 71 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0031-00 | 00 | ADV-0031 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-MEC-SDW-0004-00 | GENERAL MISCELLANEOUS DETAILS - HVAC | MEC | Hail | 2026-04-02 |  | 2026-04-07 | 5 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 72 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0031-00 | 00 | ADV-0031 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-MEC-SDW-0005-00 | GENERAL MISCELLANEOUS DETAILS - HVAC | MEC | Hail | 2026-04-02 |  | 2026-04-07 | 5 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 73 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0031-00 | 00 | ADV-0031 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-MEC-SDW-0006-00 | GENERAL MISCELLANEOUS DETAILS - HVAC | MEC | Hail | 2026-04-02 |  | 2026-04-07 | 5 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 74 | MLTX-02-003-ADV-TS9-1-CVL-SDW-0032-00 | 00 | ADV-0032 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-CV-SDW-0001-00 | SITE LAYOUT - TABUK (BOREHOLES LOCATION) | CVL | Tabuk | 2026-04-02 |  | 2026-04-05 | 3 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 75 | MLTX-02-003-ADV-TS9-1-CVL-SDW-0033-00 | 01 | ADV-0033 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-CV-SDW-0001-00 | SITE LAYOUT - QASSIM (BOREHOLES LOCATION) | CVL | Qassim | 2026-04-02 |  | 2026-04-07 | 5 Days | B | 2026-04-13 | 2026-04-14 | 1 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 76 | MLTX-02-003-ADV-TS9-1-CVL-SDW-0034-00 | 01 | ADV-0034 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-CV-SDW-0001-00 | SITE LAYOUT - HAIL (BOREHOLES LOCATION) | CVL | Hail | 2026-04-02 |  | 2026-04-06 | 4 Days | C | 2026-04-13 | 2026-04-13 | 0 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 77 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0035-00 | 00 | ADV-0035 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-MEC-SDW-0007-00 | GENERAL NOTES, LEGENDS, SYMBOLS & ABBREVIATIONS - PLUMBING | MEC | Qassim | 2026-04-04 |  | 2026-04-07 | 3 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 78 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0035-00 | 01 | ADV-0035 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-MEC-SDW-0008-00 | GRP WATER TANK PIPING LAYOUT | MEC | Qassim | 2026-04-04 |  | 2026-04-07 | 3 Days | C | 2026-04-09 | 2026-04-13 | 4 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 79 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0035-00 | 02 | ADV-0035 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-MEC-SDW-0009-00 | TYPICAL GROUND FLOOR PLAN - PLUMBING DRAINAGE & WATER SUPPLY | MEC | Qassim | 2026-04-04 |  | 2026-04-07 | 3 Days | C | 2026-04-09 | 2026-04-13 | 4 Days | B | 2026-06-17 | 2026-06-27 | 10 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 80 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0035-00 | 00 | ADV-0035 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-MEC-SDW-0010-00 | GENERAL MISCELLANEOUS DETAILS PLUMBING | MEC | Qassim | 2026-04-04 |  | 2026-04-07 | 3 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 81 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0035-00 | 00 | ADV-0035 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-MEC-SDW-0011-00 | GENERAL MISCELLANEOUS DETAILS PLUMBING | MEC | Qassim | 2026-04-04 |  | 2026-04-07 | 3 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 82 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0036-00 | 00 | ADV-0036 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-MEC-SDW-0007-00 | GENERAL NOTES, LEGENDS, SYMBOLS & ABBREVIATIONS - PLUMBING | MEC | Hail | 2026-04-04 |  | 2026-04-07 | 3 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 83 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0036-00 | 01 | ADV-0036 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-MEC-SDW-0008-00 | GRP WATER TANK PIPING LAYOUT | MEC | Hail | 2026-04-04 |  | 2026-04-07 | 3 Days | C | 2026-04-09 | 2026-04-13 | 4 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 84 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0036-00 | 01 | ADV-0036 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-MEC-SDW-0009-00 | TYPICAL GROUND FLOOR PLAN - PLUMBING DRAINAGE & WATER SUPPLY | MEC | Hail | 2026-04-04 |  | 2026-04-07 | 3 Days | C | 2026-04-09 | 2026-04-13 | 4 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 85 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0036-00 | 00 | ADV-0036 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-MEC-SDW-0010-00 | GENERAL MISCELLANEOUS DETAILS - PLUMBING | MEC | Hail | 2026-04-04 |  | 2026-04-07 | 3 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 86 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0036-00 | 00 | ADV-0036 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-MEC-SDW-0011-00 | GENERAL MISCELLANEOUS DETAILS -PLUMBING | MEC | Hail | 2026-04-04 |  | 2026-04-07 | 3 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 87 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0037-00 | 00 | ADV-0037 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-MEC-SDW-0007-00 | GENERAL NOTES, LEGENDS, SYMBOLS & ABBREVIATIONS - PLUMBING | MEC | Tabuk | 2026-04-04 |  | 2026-04-11 | 7 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 88 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0037-00 | 00 | ADV-0037 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-MEC-SDW-0008-00 | GRP WATER TANK PIPING LAYOUT | MEC | Tabuk | 2026-04-04 |  | 2026-04-11 | 7 Days | C | [18 empty] | 1 |  |  |  | Revise & Resubmit
|  | 89 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0037-00 | 00 | ADV-0037 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-MEC-SDW-0009-00 | TYPICAL GROUND FLOOR PLAN - PLUMBING DRAINAGE & WATER SUPPLY | MEC | Tabuk | 2026-04-04 |  | 2026-04-11 | 7 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 90 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0037-00 | 00 | ADV-0037 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-MEC-SDW-0010-00 | GENERAL MISCELLANEOUS DETAILS PLUMBING | MEC | Tabuk | 2026-04-04 |  | 2026-04-11 | 7 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 91 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0037-00 | 00 | ADV-0037 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-MEC-SDW-0011-00 | GENERAL MISCELLANEOUS DETAILS PLUMBING | MEC | Tabuk | 2026-04-04 |  | 2026-04-11 | 7 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 92 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0038-00 | 01 | ADV-0038 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-LS-SDW-0407-00 | HAIL-SOFT LANDSCAPE PLANT LAYOUT & DETAILS | LSP | Hail | 2026-04-13 |  | 2026-04-20 | 7 Days | C | 2026-04-28 | 2026-05-04 | 6 Days | B | 2026-09-24 | 2026-09-28 | 4 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 93 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0039-00 | 00 | ADV-0039 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-LS-SDW-0100-00 | TABUK - PARK LAYOUT PLAN | LSP | Tabuk | 2026-04-19 |  | 2026-05-05 | 16 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 94 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0040-00 | 00 | ADV-0040 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-LS-SDW-0401-00 | TABUK - PIKE & WALKING LAYOUT | LSP | Tabuk | 2026-04-19 |  | 2026-04-25 | 6 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 95 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0041-00 | 01 | ADV-0041 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-LS-SDW-0402-00 | TABUK - PAVING TILE LAYOUT | LSP | Tabuk | 2026-04-19 |  | 2026-04-25 | 6 Days | C | 2026-06-03 | 2026-06-09 | 6 Days | A | [12 empty] | 1 | [5 empty] | Approved
|  | 96 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0042-00 | 00 | ADV-0042 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-LS-SDW-0403-00 | TABUK - RUBBER SURFACE, SPORT & FOOTBALL COURT LAYOUT | LSP | Tabuk | 2026-04-19 |  | 2026-04-25 | 6 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 97 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0043-00 | 00 | ADV-0043 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-LS-SDW-0404-00 | TABUK - SEATING BENCH LAYOUT | LSP | Tabuk | 2026-04-19 |  | 2026-04-22 | 3 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 98 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0044-00 | 00 | ADV-0044 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-LS-SDW-0405-00 | TABUK - STAMPED CONCRETE LAYOUT | LSP | Tabuk | 2026-04-19 |  | 2026-05-05 | 16 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 99 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0045-00 | 00 | ADV-0045 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-LS-SDW-0406-00 | TABUK - SOFT LANDSCAPE PLANT LAYOUT & DETAILS | LSP | Tabuk | 2026-04-19 |  | 2026-04-22 | 3 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 100 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0046-00 | 00 | ADV-0046 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-GEN-SDW-0100-00 | HAIL-AAC PANELS GROUND FLOOR PLAN LAYOUT | GEN | Hail | 2026-04-30 |  | 2026-05-11 | 11 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 101 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0046-00 | 00 | ADV-0046 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-GEN-SDW-0101-00 | HAIL-AAC GROUND FLOOR CEILING PLAN LAYOUT | GEN | Hail | 2026-04-30 |  | 2026-05-11 | 11 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 102 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0046-00 | 00 | ADV-0046 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-GEN-SDW-0102-00 | HAIL-AAC ELEVATIONS LAYOUT | GEN | Hail | 2026-04-30 |  | 2026-05-11 | 11 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 103 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0046-00 | 00 | ADV-0046 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-GEN-SDW-0103-00 | HAIL-AAC SECTION DETAILS | GEN | Hail | 2026-04-30 |  | 2026-05-11 | 11 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 104 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0046-00 | 00 | ADV-0046 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-GEN-SDW-0104-00 | HAIL-AAC PANELS TYPICAL DETAILS (VP) | GEN | Hail | 2026-04-30 |  | 2026-05-11 | 11 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 105 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0046-00 | 00 | ADV-0046 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-GEN-SDW-0105-00 | HAIL-AAC ISOMETRIC VIEW | GEN | Hail | 2026-04-30 |  | 2026-05-11 | 11 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 106 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0047-00 | 00 | ADV-0047 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-GEN-SDW-0100-00 | TABUK-AAC PANELS GROUND FLOOR PLAN LAYOUT | GEN | Tabuk | 2026-04-30 |  | 2026-05-05 | 5 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 107 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0047-00 | 00 | ADV-0047 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-GEN-SDW-0101-00 | TABUK-AAC GROUND FLOOR CEILING PLAN LAYOUT | GEN | Tabuk | 2026-04-30 |  | 2026-05-05 | 5 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 108 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0047-00 | 00 | ADV-0047 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-GEN-SDW-0102-00 | TABUK-AAC ELEVATIONS LAYOUT | GEN | Tabuk | 2026-04-30 |  | 2026-05-05 | 5 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 109 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0047-00 | 00 | ADV-0047 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-GEN-SDW-0103-00 | TABUK-AAC SECTION DETAILS | GEN | Tabuk | 2026-04-30 |  | 2026-05-05 | 5 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 110 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0047-00 | 00 | ADV-0047 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-GEN-SDW-0104-00 | TABUK-AAC PANELS TYPICAL DETAILS (VP) | GEN | Tabuk | 2026-04-30 |  | 2026-05-05 | 5 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 111 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0047-00 | 00 | ADV-0047 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-GEN-SDW-0105-00 | TABUK-AAC ISOMETRIC VIEW | GEN | Tabuk | 2026-04-30 |  | 2026-05-05 | 5 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 112 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0048-00 | 01 | ADV-0048 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-GEN-SDW-0100-00 | QASSIM-AAC PANELS GROUND FLOOR PLAN LAYOUT | GEN | Qassim | 2026-04-30 |  | 2026-05-05 | 5 Days | C | 2026-05-09 | 2026-05-09 | 0 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 113 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0048-00 | 01 | ADV-0048 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-GEN-SDW-0101-00 | QASSIM-AAC GROUND FLOOR CEILING PLAN LAYOUT | GEN | Qassim | 2026-04-30 |  | 2026-05-05 | 5 Days | C | 2026-05-09 | 2026-05-09 | 0 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 114 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0048-00 | 01 | ADV-0048 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-GEN-SDW-0102-00 | QASSIM-AAC ELEVATIONS LAYOUT | GEN | Qassim | 2026-04-30 |  | 2026-05-05 | 5 Days | C | 2026-05-09 | 2026-05-09 | 0 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 115 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0048-00 | 01 | ADV-0048 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-GEN-SDW-0103-00 | QASSIM-AAC SECTION DETAILS | GEN | Qassim | 2026-04-30 |  | 2026-05-05 | 5 Days | C | 2026-05-09 | 2026-05-09 | 0 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 116 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0048-00 | 01 | ADV-0048 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-GEN-SDW-0104-00 | QASSIM-AAC PANELS TYPICAL DETAILS (VP) | GEN | Qassim | 2026-04-30 |  | 2026-05-05 | 5 Days | C | 2026-05-09 | 2026-05-09 | 0 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 117 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0048-00 | 01 | ADV-0048 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-GEN-SDW-0105-00 | QASSIM-AAC ISOMETRIC VIEW | GEN | Qassim | 2026-04-30 |  | 2026-05-05 | 5 Days | C | 2026-05-09 | 2026-05-09 | 0 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 118 | MLTX-02-003-ADV-TS9-1-CVL-SDW-0049-00 | 01 | ADV-0049 | SDW | MTLX-02-003-TAB4-ADV-TS9-1-CV-SDW-1000-00 | TOILET @ PLAYGROUND EXCAVATION LAYOUT PLAN & SECTIONS | CVL | Tabuk | 2026-05-03 |  | 2026-05-09 | 6 Days | C | 2026-05-11 | 2026-05-25 | 14 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 119 | MLTX-02-003-ADV-TS9-1-CVL-SDW-0050-00 | 00 | ADV-0050 | SDW | MTLX-02-003-HAL1-ADV-TS9-1-CV-SDW-1000-00 | TOILET @ PLAYGROUND EXCAVATION LAYOUT PLAN & SECTIONS | CVL | Hail | 2026-05-09 |  | 2026-05-13 | 4 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 120 | MLTX-02-003-ADV-TS9-1-CVL-SDW-0051-00 | 00 | ADV-0051 | SDW | MTLX-02-003-QSM3-ADV-TS9-1-CV-SDW-1000-00 | TOILET @ PLAYGROUND EXCAVATION LAYOUT PLAN & SECTIONS | CVL | Qassim | 2026-05-09 |  | 2026-05-09 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 121 | MLTX-02-003-ADV-TS9-1-STR-SDW-0052-00 | 01 | ADV-0052 | SDW | MTLX-02-003-TAB4-ADV-TS9-1-STR-SDW-1100-00 | TOILET @ PLAYGROUND FOUNDATION LAYOUT PLAN & SECTIONS | STR | Tabuk | 2026-05-11 |  | 2026-05-25 | 14 Days | B | 2026-06-30 | 2026-06-30 | 0 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 122 | MLTX-02-003-ADV-TS9-1-STR-SDW-0053-00 | 02 | ADV-0053 | SDW | MTLX-02-003-HAL1-ADV-TS9-1-STR-SDW-1100-00 | TOILET @ PLAYGROUND FOUNDATION LAYOUT PLAN & SECTIONS | STR | Hail | 2026-05-12 |  | 2026-05-17 | 5 Days | B | 2026-09-12 | 2026-09-12 | 0 Days | C | 2026-09-13 | 2026-09-16 | 3 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 123 | MLTX-02-003-ADV-TS9-1-STR-SDW-0054-00 | 00 | ADV-0054 | SDW | MTLX-02-003-QSM3-ADV-TS9-1-STR-SDW-1100-00 | TOILET @ PLAYGROUND FOUNDATION LAYOUT PLAN & SECTIONS | STR | Qassim | 2026-05-12 |  | 2026-05-17 | 5 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 124 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0055-00 | 00 | ADV-0055 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-3001-00 | FIRE ALARM SYSTEM LAYOUT | ELE | Qassim | 2026-05-13 |  | 2026-05-21 | 8 Days | C | [18 empty] | 1 |  |  |  | Revise & Resubmit
|  | 125 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0055-00 | 00 | ADV-0055 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-3002-00 | FIRE ALARM SYSTEM SCHEMATIC DIAGRAM | ELE | Qassim | 2026-05-13 |  | 2026-05-21 | 8 Days | C | [18 empty] | 1 |  |  |  | Revise & Resubmit
|  | 126 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0055-00 | 00 | ADV-0055 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-7004-00 | TYPICAL ELECTRICAL INSTALLATION DETAILS (SHEET-04) | ELE | Qassim | 2026-05-13 |  | 2026-05-21 | 8 Days | C | [18 empty] | 1 |  |  |  | Revise & Resubmit
|  | 127 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0056-00 | 00 | ADV-0056 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-4001-00 | DATA & TELECOM SYSTEM LAYOUT | ELE | Qassim | 2026-05-13 |  | 2026-06-02 | 20 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 128 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0056-00 | 00 | ADV-0056 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-4002-00 | DATA & TELECOM SINGLE LINE DIAGRAM | ELE | Qassim | 2026-05-13 |  | 2026-06-02 | 20 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 129 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0057-00 | 00 | ADV-0057 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-2003-00 | AC POWER SYSTEM LAYOUT | ELE | Qassim | 2026-05-13 |  | 2026-05-21 | 8 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 130 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0058-00 | 00 | ADV-0058 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-1001-00 | LIGHTING SYSTEM LAYOUT | ELE | Qassim | 2026-05-14 |  | 2026-05-21 | 7 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 131 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0058-00 | 00 | ADV-0058 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-2004-00 | ROOF LIGHTING SYSTEM LAYOUT | ELE | Qassim | 2026-05-14 |  | 2026-05-21 | 7 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 132 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0058-00 | 00 | ADV-0058 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-7001-00 | TYPICAL ELECTRICAL INSTALLATION DETAILS (SHEET-01) | ELE | Qassim | 2026-05-14 |  | 2026-05-21 | 7 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 133 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0059-00 | 00 | ADV-0059 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-2001-00 | SMALL POWER SYSTEM LAYOUT | ELE | Qassim | 2026-05-13 |  | 2026-05-21 | 8 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 134 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0060-00 | 00 | ADV-0060 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-ELE-SDW-2001-00 | SMALL POWER SYSTEM LAYOUT | ELE | Hail | 2026-05-14 |  | 2026-05-21 | 7 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 135 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0061-00 | 01 | ADV-0061 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-1001-00 | LIGHTING SYSTEM LAYOUT | ELE | Tabuk | 2026-05-14 |  | 2026-05-19 | 5 Days | C | 2026-09-01 |  | 30 Days | UR | [17 empty] | 1 | Delayed with Egis
|  | 136 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0061-00 | 01 | ADV-0061 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-2004-00 | ROOF LIGHTING SYSTEM LAYOUT | ELE | Tabuk | 2026-05-14 |  | 2026-05-19 | 5 Days | C | 2026-09-01 |  | 30 Days | UR | [17 empty] | 1 | Delayed with Egis
|  | 137 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0061-00 | 01 | ADV-0061 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-7001-00 | TYPICAL ELECTRICAL INSTALLATION DETAILS (SHEET-01) | ELE | Tabuk | 2026-05-14 |  | 2026-05-19 | 5 Days | C | 2026-09-01 |  | 30 Days | UR | [17 empty] | 1 | Delayed with Egis
|  | 138 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0062-00 | 00 | ADV-0062 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-ELE-SDW-1001-00 | LIGHTING SYSTEM LAYOUT | ELE | Hail | 2026-05-14 |  | 2026-05-21 | 7 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 139 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0062-00 | 00 | ADV-0062 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-ELE-SDW-2004-00 | ROOF LIGHTING SYSTEM LAYOUT | ELE | Hail | 2026-05-14 |  | 2026-05-21 | 7 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 140 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0062-00 | 00 | ADV-0062 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-ELE-SDW-7001-00 | TYPICAL ELECTRICAL INSTALLATION DETAILS (SHEET-01) | ELE | Hail | 2026-05-14 |  | 2026-05-21 | 7 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 141 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0063-00 | 01 | ADV-0063 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-2001-00 | SMALL POWER SYSTEM LAYOUT | ELE | Tabuk | 2026-05-14 |  | 2026-05-19 | 5 Days | C | 2026-09-01 |  | 30 Days | UR | [17 empty] | 1 | Delayed with Egis
|  | 142 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0064-00 | 00 | ADV-0064 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-ELE-SDW-2003-00 | AC POWER SYSTEM LAYOUT | ELE | Hail | 2026-05-14 |  | 2026-05-21 | 7 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 143 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0065-00 | 01 | ADV-0065 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-2003-00 | AC POWER SYSTEM LAYOUT | ELE | Tabuk | 2026-05-14 |  | 2026-05-19 | 5 Days | C | 2026-09-01 |  | 30 Days | UR | [17 empty] | 1 | Delayed with Egis
|  | 144 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0066-00 | 00 | ADV-0066 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-ELE-SDW-4001-00 | DATA & TELECOM SYSTEM LAYOUT | ELE | Hail | 2026-05-14 |  | 2026-05-17 | 3 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 145 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0066-00 | 00 | ADV-0066 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-ELE-SDW-4002-00 | DATA & TELECOM SINGLE LINE DIAGRAM | ELE | Hail | 2026-05-14 |  | 2026-05-17 | 3 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 146 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0067-00 | 01 | ADV-0067 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-4001-00 | DATA & TELECOM SYSTEM LAYOUT | ELE | Tabuk | 2026-05-14 |  | 2026-05-19 | 5 Days | C | 2026-09-01 |  | 30 Days | UR | [17 empty] | 1 | Delayed with Egis
|  | 147 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0067-00 | 01 | ADV-0067 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-4002-00 | DATA & TELECOM SINGLE LINE DIAGRAM | ELE | Tabuk | 2026-05-14 |  | 2026-05-19 | 5 Days | C | 2026-09-01 |  | 30 Days | UR | [17 empty] | 1 | Delayed with Egis
|  | 148 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0068-00 | 00 | ADV-0068 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-ELE-SDW-3001-00 | FIRE ALARM SYSTEM LAYOUT | ELE | Hail | 2026-05-16 |  | 2026-05-17 | 1 Days | C | [18 empty] | 1 |  |  |  | Revise & Resubmit
|  | 149 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0068-00 | 00 | ADV-0068 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-ELE-SDW-3002-00 | FIRE ALARM SYSTEM SCHEMATIC DIAGRAM | ELE | Hail | 2026-05-16 |  | 2026-05-17 | 1 Days | C | [18 empty] | 1 |  |  |  | Revise & Resubmit
|  | 150 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0068-00 | 00 | ADV-0068 | SDW | MLTX-02-003-HAIL1-ADV-TS9-1-ELE-SDW-7004-00 | TYPICAL ELECTRICAL INSTALLATION DETAILS (SHEET-04) | ELE | Hail | 2026-05-16 |  | 2026-05-17 | 1 Days | C | [18 empty] | 1 |  |  |  | Revise & Resubmit
|  | 151 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0069-00 | 01 | ADV-0069 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-3001-00 | FIRE ALARM SYSTEM LAYOUT | ELE | Tabuk | 2026-05-16 |  | 2026-05-19 | 3 Days | C | 2026-09-01 |  | 30 Days | UR | [17 empty] | 1 | Delayed with Egis
|  | 152 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0069-00 | 01 | ADV-0069 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-3002-00 | FIRE ALARM SYSTEM SCHEMATIC DIAGRAM | ELE | Tabuk | 2026-05-16 |  | 2026-05-19 | 3 Days | C | 2026-09-01 |  | 30 Days | UR | [17 empty] | 1 | Delayed with Egis
|  | 153 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0069-00 | 01 | ADV-0069 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-7004-00 | TYPICAL ELECTRICAL INSTALLATION DETAILS (SHEET-04) | ELE | Tabuk | 2026-05-16 |  | 2026-05-19 | 3 Days | C | 2026-09-01 |  | 30 Days | UR | [17 empty] | 1 | Delayed with Egis
|  | 154 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0070-00 | 01 | ADV-0070 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-LSP-SDW-0407-00 | TABUK - CURBSTONE LAYOUT PLAN & DETAILS | LSP | Tabuk | 2026-06-03 |  | 2026-07-19 | 46 Days | B | 2026-09-16 | 2026-09-17 | 1 Days | A | [12 empty] | 1 | [5 empty] | Approved
|  | 155 | MLTX-02-003-ADV-TS9-1-CVL-SDW-0071-00 | 01 | ADV-0071 | SDW | MTLX-02-003-TAB4-ADV-TS9-1-CVL-SDW-2000-00 | GRP WATER TANK @ PLAYGROUND EXCAVATION LAYOUT PLAN & SECTIONS | CVL | Tabuk | 2026-06-04 |  | 2026-06-09 | 5 Days | C | 2026-06-28 | 2026-07-28 | 30 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 156 | MLTX-02-003-ADV-TS9-1-STR-SDW-0072-00 | 01 | ADV-0072 | SDW | MTLX-02-003-TAB4-ADV-TS9-1-STR-SDW-2100-00 | GRP WATER TANK @PLAYGROUND FOUNDATION LAYOUT PLAN & SECTIONS | STR | Tabuk | 2026-06-04 |  | 2026-06-20 | 16 Days | C | 2026-06-28 | 2026-06-29 | 1 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 157 | MLTX-02-003-ADV-TS9-1-STR-SDW-0073-00 | 00 | ADV-0073 | SDW | MTLX-02-003-QSM3-ADV-TS9-1-STR-SDW-2100-00 | GRP WATER TANK @PLAYGROUND FOUNDATION LAYOUT PLAN & SECTIONS | STR | Qassim | 2026-06-04 |  | 2026-06-11 | 7 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 158 | MLTX-02-003-ADV-TS9-1-CVL-SDW-0074-00 | 00 | ADV-0074 | SDW | MTLX-02-003-QSM3-ADV-TS9-1-CVL-SDW-2000-00 | GRP WATER TANK @ PLAYGROUND EXCAVATION LAYOUT PLAN & SECTIONS | CVL | Qassim | 2026-06-04 |  | 2026-06-11 | 7 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 159 | MLTX-02-003-ADV-TS9-1-CVL-SDW-0075-00 | 01 | ADV-0075 | SDW | MTLX-02-003-HAL1-ADV-TS9-1-CVL-SDW-2000-00 | GRP WATER TANK @ PLAYGROUND EXCAVATION LAYOUT PLAN & SECTIONS | CVL | Hail | 2026-06-04 |  | 2026-06-08 | 4 Days | C | 2026-06-09 | 2026-06-16 | 7 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 160 | MLTX-02-003-ADV-TS9-1-STR-SDW-0076-00 | 01 | ADV-0076 | SDW | MTLX-02-003-HAL1-ADV-TS9-1-STR-SDW-2100-00 | GRP WATER TANK @PLAYGROUND FOUNDATION LAYOUT PLAN & SECTIONS | STR | Hail | 2026-06-04 |  | 2026-06-08 | 4 Days | C | 2026-06-09 | 2026-06-22 | 13 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 161 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0077-00 | 01 | ADV-0077 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LSP-SDW-0407-00 | QASSIM - CURBSTONE LAYOUT PLAN & DETAILS | LSP | Qassim | 2026-06-04 |  | 2026-06-13 | 9 Days | C | 2026-06-14 | 2026-06-14 | 0 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 162 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0078-00 | 01 | ADV-0078 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-LSP-SDW-0407-00 | HAIL - CURBSTONE LAYOUT PLAN & DETAILS | LSP | Hail | 2026-06-06 |  | 2026-06-06 | 0 Days | C | 2026-06-08 | 2026-06-13 | 5 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 163 | MLTX-02-003-ADV-TS9-1-STR-SDW-0079-00 | 01 | ADV-0079 | SDW | MTLX-02-003-QSM3-ADV-TS9-1-STR-SDW-4100-00 | FOOTBALL PLAYGROUND FENCE FOOTING DETAILS- QASSIM | STR | Qassim | 2026-06-10 |  | 2026-06-13 | 3 Days | C | 2026-06-15 | 2026-06-20 | 5 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 164 | MLTX-02-003-ADV-TS9-1-STR-SDW-0079-00 | 01 | ADV-0079 | SDW | MTLX-02-003-TAB4-ADV-TS9-1-STR-SDW-4100-00 | FOOTBALL PLAYGROUND FENCE FOOTING DETAILS - TABUK | STR | Tabuk | 2026-06-10 |  | 2026-06-13 | 3 Days | C | 2026-06-15 | 2026-06-20 | 5 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 165 | MLTX-02-003-ADV-TS9-1-STR-SDW-0079-00 | 01 | ADV-0079 | SDW | MTLX-02-003-HAL1-ADV-TS9-1-STR-SDW-4100-00 | FOOTBALL PLAYGROUND FENCE FOOTING DETAILS - HAIL | STR | Hail | 2026-06-10 |  | 2026-06-13 | 3 Days | C | 2026-06-15 | 2026-06-20 | 5 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 166 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0080-00 | 01 | ADV-0080 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-GEN-SDW-0200-00 | QASSIM - TOP VIEW | GEN | Qassim | 2026-06-15 |  | 2026-06-21 | 6 Days | C | 2026-06-22 | 2026-06-25 | 3 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 167 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0080-00 | 01 | ADV-0080 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-GEN-SDW-0201-00 | QASSIM - ARCH LAYOUT | GEN | Qassim | 2026-06-15 |  | 2026-06-21 | 6 Days | C | 2026-06-22 | 2026-06-25 | 3 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 168 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0080-00 | 01 | ADV-0080 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-GEN-SDW-0202-00 | QASSIM - ELEVATIONS | GEN | Qassim | 2026-06-15 |  | 2026-06-21 | 6 Days | C | 2026-06-22 | 2026-06-25 | 3 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 169 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0080-00 | 01 | ADV-0080 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-GEN-SDW-0203-00 | QASSIM - SECTIONS | GEN | Qassim | 2026-06-15 |  | 2026-06-21 | 6 Days | C | 2026-06-22 | 2026-06-25 | 3 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 170 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0080-00 | 01 | ADV-0080 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-GEN-SDW-0204-00 | QASSIM - DOME FOUNDATION LAYOUT PLAN | GEN | Qassim | 2026-06-15 |  | 2026-06-21 | 6 Days | C | 2026-06-22 | 2026-06-25 | 3 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 171 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0080-00 | 01 | ADV-0080 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-GEN-SDW-0205-00 | QASSIM – MACHINERY FOUNDATION LAYOUT | GEN | Qassim | 2026-06-15 |  | 2026-06-21 | 6 Days | C | 2026-06-22 | 2026-06-25 | 3 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 172 | MLTX-02-003-ADV-TS9-1-IRR-SDW-0081-00 | 02 | ADV-0081 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-IRR-SDW-1000-00 | BUBBLER | IRR | Qassim | 2026-06-15 |  | 2026-06-20 | 5 Days | C | 2026-07-02 | 2026-07-14 | 12 Days | C | 2026-07-20 | 2026-08-01 | 12 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 173 | MLTX-02-003-ADV-TS9-1-IRR-SDW-0081-00 | 02 | ADV-0081 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-IRR-SDW-1001-00 | MAIN LINE | IRR | Qassim | 2026-06-15 |  | 2026-06-20 | 5 Days | C | 2026-07-02 | 2026-07-14 | 12 Days | C | 2026-07-20 | 2026-08-01 | 12 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 174 | MLTX-02-003-ADV-TS9-1-IRR-SDW-0081-00 | 02 | ADV-0081 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-IRR-SDW-1002-00 | IRRIGATION CONTROL | IRR | Qassim | 2026-06-15 |  | 2026-06-20 | 5 Days | C | 2026-07-02 | 2026-07-14 | 12 Days | C | 2026-07-20 | 2026-08-01 | 12 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 175 | MLTX-02-003-ADV-TS9-1-IRR-SDW-0081-00 | 02 | ADV-0081 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-IRR-SDW-1003-00 | POP UP SPRAY | IRR | Qassim | 2026-06-15 |  | 2026-06-20 | 5 Days | C | 2026-07-02 | 2026-07-14 | 12 Days | C | 2026-07-20 | 2026-08-01 | 12 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 176 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0082-00 | 01 | ADV-0082 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-GEN-SDW-0200-00 | TABUK - TOP VIEW | GEN | Tabuk | 2026-06-15 |  | 2026-06-21 | 6 Days | C | 2026-06-22 | 2026-06-25 | 3 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 177 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0082-00 | 01 | ADV-0082 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-GEN-SDW-0201-00 | TABUK - ARCH LAYOUT | GEN | Tabuk | 2026-06-15 |  | 2026-06-21 | 6 Days | C | 2026-06-22 | 2026-06-25 | 3 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 178 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0082-00 | 01 | ADV-0082 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-GEN-SDW-0202-00 | TABUK - ELEVATIONS | GEN | Tabuk | 2026-06-15 |  | 2026-06-21 | 6 Days | C | 2026-06-22 | 2026-06-25 | 3 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 179 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0082-00 | 01 | ADV-0082 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-GEN-SDW-0203-00 | TABUK - SECTIONS | GEN | Tabuk | 2026-06-15 |  | 2026-06-21 | 6 Days | C | 2026-06-22 | 2026-06-25 | 3 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 180 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0082-00 | 01 | ADV-0082 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-GEN-SDW-0204-00 | TABUK - DOME FOUNDATION LAYOUT PLAN | GEN | Tabuk | 2026-06-15 |  | 2026-06-21 | 6 Days | C | 2026-06-22 | 2026-06-25 | 3 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 181 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0082-00 | 01 | ADV-0082 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-GEN-SDW-0205-00 | TABUK – MACHINERY FOUNDATION LAYOUT | GEN | Tabuk | 2026-06-15 |  | 2026-06-21 | 6 Days | C | 2026-06-22 | 2026-06-25 | 3 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 182 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0083-00 | 00 | ADV-0083 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-LSP-SDW-0201-00 | PROPOSAL FOR PART 1 FINISH LEVELS PLAN - PROFILES | LSP | Hail | 2026-06-17 |  | 2026-06-20 | 3 Days | C | These Drawings have been superseded with the Transmittal No. MLTX-02-003-ADV-TS9-1-LSP-SDW-0104-00, Revision will not be submitted as per Engr Ahmed Refaat (Technical Manager)
|  | 183 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0083-00 | 00 | ADV-0083 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-LSP-SDW-0202-00 | PROPOSAL FOR PART 1 FINISH LEVELS LEVELS GRID - PROFILES | LSP | Hail | 2026-06-17 |  | 2026-06-20 | 3 Days | C
|  | 184 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0084-00 | 01 | ADV-0084 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-LSP-SDW-201-00 | GRADING PROPOSAL - TABUK | LSP | Tabuk | 2026-06-20 |  | 2026-06-22 | 2 Days | B | 2026-07-05 | 2026-08-24 | 50 Days | C | [14 empty] | 1 |  |  |  | Revise & Resubmit
|  | 185 | MLTX-02-003-ADV-TS9-1-SVY-SDW-0085-00 | 00 | ADV-0085 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-SVY-SDW-0002-00 | SITE LAYOUT - QASSIM COMMERCIAL STRIP (TOPOGRAPHIC SURVEY) | SVY | Qassim | 2026-06-21 |  | 2026-06-22 | 1 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 186 | MLTX-02-003-ADV-TS9-1-STR-SDW-0086-00 | 03 | ADV-0086 | SDW | MTLX-02-003-HAL1-ADV-TS9-1-STR-SDW-3100-00 | SEPTIC TANK Concrete Details for Foundation Plan & Walls - HAIL | STR | Hail | 2026-06-21 |  | 2026-06-22 | 1 Days | C | 2026-06-22 | 2026-06-27 | 5 Days | C | 2026-06-30 | 2026-06-30 | 0 Days | B | 2026-08-01 | 2026-08-06 | 5 Days | B | [5 empty] | 1 |  |  |  |  | Approved with Comments
|  | 187 | MLTX-02-003-ADV-TS9-1-STR-SDW-0086-00 | 03 | ADV-0086 | SDW | MTLX-02-003-HAL1-ADV-TS9-1-STR-SDW-3101-00 | SEPTIC TANK Concrete Details for Roof Slab Plan & Walls - HAIL | STR | Hail | 2026-06-21 |  | 2026-06-22 | 1 Days | C | 2026-06-22 | 2026-06-27 | 5 Days | C | 2026-06-30 | 2026-06-30 | 0 Days | B | 2026-08-01 | 2026-08-06 | 5 Days | B | [5 empty] | 1 |  |  |  |  | Approved with Comments
|  | 188 | MLTX-02-003-ADV-TS9-1-STR-SDW-0087-00 | 00 | ADV-0087 | SDW | MTLX-02-003-TAB4-ADV-TS9-1-STR-SDW-3100-00 | SEPTIC TANK Concrete Details for Foundation Plan & Walls - TABUK | STR | Tabuk | 2026-06-23 |  |  | 100 Days | UR | [21 empty] | 1 | Delayed with Egis
|  | 189 | MLTX-02-003-ADV-TS9-1-STR-SDW-0087-00 | 00 | ADV-0087 | SDW | MTLX-02-003-TAB4-ADV-TS9-1-STR-SDW-3101-00 | SEPTIC TANK Concrete Details for Roof Slab Plan & Walls - TABUK | STR | Tabuk | 2026-06-23 |  |  | 100 Days | UR | [21 empty] | 1 | Delayed with Egis
|  | 190 | MLTX-02-003-ADV-TS9-1-STR-SDW-0088-00 | 01 | ADV-0088 | SDW | MTLX-02-003-QSM3-ADV-TS9-1-STR-SDW-5100-00 | PLAYGROUND EQUIPMENTS FOOTING DETAILS - QASSIM | STR | Qassim | 2026-06-23 |  | 2026-06-27 | 4 Days | C | 2026-07-07 | 2026-07-09 | 2 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 191 | MLTX-02-003-ADV-TS9-1-STR-SDW-0088-00 | 01 | ADV-0088 | SDW | MTLX-02-003-TAB4-ADV-TS9-1-STR-SDW-5100-00 | PLAYGROUND EQUIPMENTS FOOTING DETAILS - TABUK | STR | Tabuk | 2026-06-23 |  | 2026-06-27 | 4 Days | C | 2026-07-07 | 2026-07-09 | 2 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 192 | MLTX-02-003-ADV-TS9-1-STR-SDW-0088-00 | 01 | ADV-0088 | SDW | MTLX-02-003-HAL1-ADV-TS9-1-STR-SDW-5100-00 | PLAYGROUND EQUIPMENTS FOOTING DETAILS - HAIL | STR | Hail | 2026-06-23 |  | 2026-06-27 | 4 Days | C | 2026-07-07 | 2026-07-09 | 2 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 193 | MLTX-02-003-ADV-TS9-1-STR-SDW-0089-00 | 00 | ADV-0089 | SDW | MTLX-02-003-TAB4-ADV-TS9-1-STR-SDW-3102-00 | SEPTIC TANK Reinforcement Detail for Foundation Plan & Wall Sections - TABUK | STR | Tabuk | 2026-06-25 |  | 2026-07-19 | 24 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 194 | MLTX-02-003-ADV-TS9-1-STR-SDW-0089-00 | 00 | ADV-0089 | SDW | MTLX-02-003-TAB4-ADV-TS9-1-STR-SDW-3103-00 | SEPTIC TANK Reinforcement Details for Roof Slab Plan & Walls Sections- TABUK | STR | Tabuk | 2026-06-25 |  | 2026-07-19 | 24 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 195 | MLTX-02-003-ADV-TS9-1-STR-SDW-0090-00 | 02 | ADV-0090 | SDW | MTLX-02-003-HAL1-ADV-TS9-1-STR-SDW-3102-00 | SEPTIC TANK Reinforcement Detail for Foundation Plan & Wall Sections - HAIL | STR | Hail | 2026-06-27 |  | 2026-06-30 | 3 Days | B | 2026-08-04 | 2026-08-08 | 4 Days | C | 2026-08-29 | 2026-09-02 | 4 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 196 | MLTX-02-003-ADV-TS9-1-STR-SDW-0090-00 | 02 | ADV-0090 | SDW | MTLX-02-003-HAL1-ADV-TS9-1-STR-SDW-3103-00 | SEPTIC TANK Reinforcement Details for Roof Slab Plan & Walls Sections- HAIL | STR | Hail | 2026-06-27 |  | 2026-06-30 | 3 Days | B | 2026-08-04 | 2026-08-08 | 4 Days | C | 2026-08-29 | 2026-09-02 | 4 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 197 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0091-00 | 01 | ADV-0091 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LSP-SDW-0408-00 | Qassim Oasis - SOFT LANDSCAPE PLANT LAYOUT & DETAILS _ PART 1 | LSP | Qassim | 2026-06-29 |  | 2026-07-12 | 13 Days | C | 2026-07-20 | 2026-07-29 | 9 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 198 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0091-00 | 01 | ADV-0091 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LSP-SDW-0409-00 | Qassim Oasis - SOFT LANDSCAPE PLANT LAYOUT & DETAILS _ PART 2 | LSP | Qassim | 2026-06-29 |  | 2026-07-12 | 13 Days | C | 2026-07-20 | 2026-07-29 | 9 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 199 | MLTX-02-003-ADV-TS9-1-IRR-SDW-0092-00 | 02 | ADV-0092 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-IRR-SDW-1000-00 | BUBBLER | IRR | Hail | 2026-07-01 |  | 2026-07-05 | 4 Days | C | 2026-07-08 | 2026-07-15 | 7 Days | C | 2026-07-16 | 2026-07-19 | 3 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 200 | MLTX-02-003-ADV-TS9-1-IRR-SDW-0092-00 | 02 | ADV-0092 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-IRR-SDW-1001-00 | MAIN LINE | IRR | Hail | 2026-07-01 |  | 2026-07-05 | 4 Days | C | 2026-07-08 | 2026-07-15 | 7 Days | C | 2026-07-16 | 2026-07-19 | 3 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 201 | MLTX-02-003-ADV-TS9-1-IRR-SDW-0092-00 | 02 | ADV-0092 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-IRR-SDW-1002-00 | IRRIGATION CONTROL | IRR | Hail | 2026-07-01 |  | 2026-07-05 | 4 Days | C | 2026-07-08 | 2026-07-15 | 7 Days | C | 2026-07-16 | 2026-07-19 | 3 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 202 | MLTX-02-003-ADV-TS9-1-IRR-SDW-0092-00 | 02 | ADV-0092 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-IRR-SDW-1003-00 | POP UP SPRAY | IRR | Hail | 2026-07-01 |  | 2026-07-05 | 4 Days | C | 2026-07-08 | 2026-07-15 | 7 Days | C | 2026-07-16 | 2026-07-19 | 3 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 203 | MLTX-02-003-ADV-TS9-1-IRR-SDW-0092-00 | 02 | ADV-0092 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-IRR-SDW-1004-00 | Details | IRR | Hail | 2026-07-01 |  | 2026-07-05 | 4 Days | C | 2026-07-08 | 2026-07-15 | 7 Days | C | 2026-07-16 | 2026-07-19 | 3 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 204 | MLTX-02-003-ADV-TS9-1-IRR-SDW-0093-00 | 01 | ADV-0093 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-IRR-SDW-1000-00 | BUBBLER | IRR | Tabuk | 2026-07-01 |  | 2026-07-15 | 14 Days | C | 2026-07-16 | 2026-07-23 | 7 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 205 | MLTX-02-003-ADV-TS9-1-IRR-SDW-0093-00 | 01 | ADV-0093 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-IRR-SDW-1001-00 | MAIN LINE | IRR | Tabuk | 2026-07-01 |  | 2026-07-15 | 14 Days | C | 2026-07-16 | 2026-07-23 | 7 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 206 | MLTX-02-003-ADV-TS9-1-IRR-SDW-0093-00 | 01 | ADV-0093 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-IRR-SDW-1002-00 | IRRIGATION CONTROL | IRR | Tabuk | 2026-07-01 |  | 2026-07-15 | 14 Days | C | 2026-07-16 | 2026-07-23 | 7 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 207 | MLTX-02-003-ADV-TS9-1-IRR-SDW-0093-00 | 01 | ADV-0093 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-IRR-SDW-1003-00 | POP UP SPRAY | IRR | Tabuk | 2026-07-01 |  | 2026-07-15 | 14 Days | C | 2026-07-16 | 2026-07-23 | 7 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 208 | MLTX-02-003-ADV-TS9-1-IRR-SDW-0093-00 | 01 | ADV-0093 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-IRR-SDW-1004-00 | Details | IRR | Tabuk | 2026-07-01 |  | 2026-07-15 | 14 Days | C | 2026-07-16 | 2026-07-23 | 7 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 209 | MLTX-02-003-ADV-TS9-1-STR-SDW-0094-00 | 02 | ADV-0094 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-STR-SDW-3100-00 | IDENTICAL – FOUNDATION LOCATION LAYOUT PLAN - Qassim | STR | Qassim | 2026-07-01 |  | 2026-07-04 | 3 Days | C | 2026-07-07 | 2026-07-11 | 4 Days | C | 2026-07-13 | 2026-07-15 | 2 Days | C | These Drawings have been superseded with the Transmittal No. MLTX-02-003-ADV-TS9-1-STR-SDW-0111-00, Revision will not be submitted as per Engr. Khaled Badawy (ADV)
|  | 210 | MLTX-02-003-ADV-TS9-1-STR-SDW-0094-00 | 02 | ADV-0094 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-STR-SDW-3100-00 | IDENTICAL – FOUNDATION LOCATION LAYOUT PLAN - Tabuk | STR | Tabuk | 2026-07-01 |  | 2026-07-04 | 3 Days | C | 2026-07-07 | 2026-07-11 | 4 Days | C | 2026-07-13 | 2026-07-15 | 2 Days | C
|  | 211 | MLTX-02-003-ADV-TS9-1-STR-SDW-0094-00 | 02 | ADV-0094 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-STR-SDW-3101-00 | IDENTICAL - DOME FOUNDATION LAYOUT PLAN & SECTION - Qassim | STR | Qassim | 2026-07-01 |  | 2026-07-04 | 3 Days | C | 2026-07-07 | 2026-07-11 | 4 Days | C | 2026-07-13 | 2026-07-15 | 2 Days | C
|  | 212 | MLTX-02-003-ADV-TS9-1-STR-SDW-0094-00 | 02 | ADV-0094 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-STR-SDW-3101-00 | IDENTICAL - DOME FOUNDATION LAYOUT PLAN & SECTION - Tabuk | STR | Tabuk | 2026-07-01 |  | 2026-07-04 | 3 Days | C | 2026-07-07 | 2026-07-11 | 4 Days | C | 2026-07-13 | 2026-07-15 | 2 Days | C
|  | 213 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0095-00 | 00 | ADV-0095 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-5001-00 | GROUNDING SYSTEM LAYOUT | ELE | Qassim | 2026-07-02 |  | 2026-07-20 | 18 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 214 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0095-00 | 00 | ADV-0095 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-7006-00 | TYPICAL ELECTRICAL INSTALLATION DETAILS (SHEET-06) | ELE | Qassim | 2026-07-02 |  | 2026-07-20 | 18 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 215 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0096-00 | 00 | ADV-0096 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-ELE-SDW-5001-00 | GROUNDING SYSTEM LAYOUT | ELE | Hail | 2026-07-02 |  | 2026-07-14 | 12 Days | C | [18 empty] | 1 |  |  |  | Revise & Resubmit
|  | 216 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0096-00 | 00 | ADV-0096 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-ELE-SDW-7006-00 | TYPICAL ELECTRICAL INSTALLATION DETAILS (SHEET-06) | ELE | Hail | 2026-07-02 |  | 2026-07-14 | 12 Days | C | [18 empty] | 1 |  |  |  | Revise & Resubmit
|  | 217 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0097-00 | 00 | ADV-0097 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-5001-00 | GROUNDING SYSTEM LAYOUT | ELE | Tabuk | 2026-07-02 |  | 2026-07-02 | 0 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 218 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0097-00 | 00 | ADV-0097 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-7006-00 | TYPICAL ELECTRICAL INSTALLATION DETAILS (SHEET-06) | ELE | Tabuk | 2026-07-02 |  | 2026-07-02 | 0 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 219 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0098-00 | 00 | ADV-0098 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-6001-00 | LIGHTNING PROTECTION SYSTEM LAYOUT | ELE | Qassim | 2026-07-02 |  | 2026-07-20 | 18 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 220 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0098-00 | 00 | ADV-0098 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-7007-00 | TYPICAL ELECTRICAL INSTALLATION DETAILS (SHEET-07) | ELE | Qassim | 2026-07-02 |  | 2026-07-20 | 18 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 221 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0099-00 | 00 | ADV-0099 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-ELE-SDW-6001-00 | LIGHTNING PROTECTION SYSTEM LAYOUT | ELE | Hail | 2026-07-02 |  | 2026-07-14 | 12 Days | C | [18 empty] | 1 |  |  |  | Revise & Resubmit
|  | 222 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0099-00 | 00 | ADV-0099 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-ELE-SDW-7007-00 | TYPICAL ELECTRICAL INSTALLATION DETAILS (SHEET-07) | ELE | Hail | 2026-07-02 |  | 2026-07-14 | 12 Days | C | [18 empty] | 1 |  |  |  | Revise & Resubmit
|  | 223 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0100-00 | 00 | ADV-0100 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-6001-00 | LIGHTNING PROTECTION SYSTEM LAYOUT | ELE | Tabuk | 2026-07-02 |  | 2026-07-02 | 0 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 224 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0100-00 | 00 | ADV-0100 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-7007-00 | TYPICAL ELECTRICAL INSTALLATION DETAILS (SHEET-07) | ELE | Tabuk | 2026-07-02 |  | 2026-07-02 | 0 Days | A | [16 empty] | 1 | [5 empty] | Approved
|  | 225 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0101-00 | 00 | ADV-0101 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-ELE-SDW-0203-00 | LIGHTING POLES SINGLE LINE DIAGRAM | ELE | Hail | 2026-07-02 |  | 2026-07-15 | 13 Days | C | [18 empty] | 1 |  |  |  | Revise & Resubmit
|  | 226 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0101-00 | 00 | ADV-0101 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-ELE-SDW-1000-00 | LIGHTING POLES LAYOUT | ELE | Hail | 2026-07-02 |  | 2026-07-15 | 13 Days | C | [18 empty] | 1 |  |  |  | Revise & Resubmit
|  | 227 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0102-00 | 00 | ADV-0102 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-ELE-SDW-2006-00 | PANEL SCHEDULE | ELE | Hail | 2026-07-04 |  | 2026-07-15 | 11 Days | C | [18 empty] | 1 |  |  |  | Revise & Resubmit
|  | 228 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0103-00 | 01 | ADV-0103 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-ELE-SDW-2005-00 | POWER SINGLE LINE DIAGRAM | ELE | Hail | 2026-07-04 |  | 2026-07-15 | 11 Days | C | 2026-07-22 | 2026-07-23 | 1 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 229 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0104-00 | 00 | ADV-0104 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-LSP-SDW-0201-00 | GRID FINISH LEVELS FOR HAIL PART 1 (PLAN+PROFILE+TABLE) | LSP | Hail | 2026-07-11 |  | 2026-07-14 | 3 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 230 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0104-00 | 00 | ADV-0104 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-LSP-SDW-0202-00 | GRID FINISH LEVELS FOR HAIL PART 2 (PLAN+PROFILE+TABLE) | LSP | Hail | 2026-07-11 |  | 2026-07-14 | 3 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 231 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0104-00 | 00 | ADV-0104 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-LSP-SDW-0203-00 | GRID FINISH LEVELS FOR HAIL PART 3 (PLAN+PROFILE+TABLE) | LSP | Hail | 2026-07-11 |  | 2026-07-14 | 3 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 232 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0104-00 | 00 | ADV-0104 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-LSP-SDW-0204-00 | CROSS AND PROFILE SECTIONS IN DITCH | LSP | Hail | 2026-07-11 |  | 2026-07-14 | 3 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 233 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0105-00 | 00 | ADV-0105 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-0200-00 | POWER PLAN QASIM | ELE | Qassim | 2026-07-13 |  | 2026-07-20 | 7 Days | C | These Drawings have been superseded with the Transmittal No. MLTX-02-003-ADV-TS9-1-ELE-SDW-0118-00, Revision will not be submitted as per Engr. Islam Moustafa (ADV)
|  | 234 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0105-00 | 00 | ADV-0105 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-0201-00 | POWER SINGLE LINE DIAGRAM QASSIM | ELE | Qassim | 2026-07-13 |  | 2026-07-20 | 7 Days | C
|  | 235 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0105-00 | 00 | ADV-0105 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-0202-00 | PANEL LOAD SCHEDULE MDB QASSIM | ELE | Qassim | 2026-07-13 |  | 2026-07-20 | 7 Days | C
|  | 236 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0105-00 | 00 | ADV-0105 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-0203-00 | VOLTAGE DROP QASSIM | ELE | Qassim | 2026-07-13 |  | 2026-07-20 | 7 Days | C
|  | 237 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0105-00 | 00 | ADV-0105 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-0204-00 | GENERATOR SIZE QASSIM | ELE | Qassim | 2026-07-13 |  | 2026-07-20 | 7 Days | C | These Drawings have been superseded with the Transmittal No. MLTX-02-003-ADV-TS9-1-ELE-SDW-0120-00, Revision will not be submitted as per Engr. Islam Moustafa (ADV)
|  | 238 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0105-00 | 00 | ADV-0105 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-0205-00 | ELECT CONSTRUCTION LAYOUT QASSIM | ELE | Qassim | 2026-07-13 |  | 2026-07-20 | 7 Days | C | These Drawings have been superseded with the Transmittal No. MLTX-02-003-ADV-TS9-1-ELE-SDW-0117-00, Revision will not be submitted as per Engr. Islam Moustafa (ADV)
|  | 239 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0105-00 | 00 | ADV-0105 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-0206-00 | PLC SINGLE LINE DIAGRAM QASSIM | ELE | Qassim | 2026-07-13 |  | 2026-07-20 | 7 Days | C
|  | 240 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0105-00 | 00 | ADV-0105 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-0207-00 | SLD GENERAL QASSIM | ELE | Qassim | 2026-07-13 |  | 2026-07-20 | 7 Days | C | As per Engr. Islam Moustafa 's instruction, this drawing has been cancelled, revision will not be submitted.
|  | 241 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0105-00 | 00 | ADV-0105 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-0208-00 | EARTHING CALCULATION QASSIM | ELE | Qassim | 2026-07-13 |  | 2026-07-20 | 7 Days | C | These Drawings have been superseded with the Transmittal No. MLTX-02-003-ADV-TS9-1-ELE-SDW-0116-00, Revision will not be submitted as per Engr. Islam Moustafa (ADV)
|  | 242 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0105-00 | 00 | ADV-0105 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-0209-00 | CCTV LAYOUT QASSIM | ELE | Qassim | 2026-07-13 |  | 2026-07-20 | 7 Days | C | As per Engr. Islam Moustafa 's instruction, this drawing has been cancelled, revision will not be submitted.
|  | 243 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0105-00 | 00 | ADV-0105 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-0210-00 | CCTV SYSTEM DIAGRAM QASSIM | ELE | Qassim | 2026-07-13 |  | 2026-07-20 | 7 Days | C
|  | 244 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0106-00 | 00 | ADV-0106 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-GEN-SDW-0300-00 | 2.0m WIDE x 2.10m HIGH DOUBLE LEAF GATE (BASKET BALL FIELD) ELEVATION & DETAILS | GEN | Qassim | 2026-07-13 |  | 2026-07-21 | 8 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 245 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0106-00 | 00 | ADV-0106 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-GEN-SDW-0300-00 | 2.0m WIDE x 2.10m HIGH DOUBLE LEAF GATE (BASKET BALL FIELD) ELEVATION & DETAILS | GEN | Hail | 2026-07-13 |  | 2026-07-21 | 8 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 246 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0106-00 | 00 | ADV-0106 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-GEN-SDW-0300-00 | 2.0m WIDE x 2.10m HIGH DOUBLE LEAF GATE (BASKET BALL FIELD) ELEVATION & DETAILS | GEN | Tabuk | 2026-07-13 |  | 2026-07-21 | 8 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 247 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0106-00 | 00 | ADV-0106 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-GEN-SDW-0301-00 | 4.50M High Chain Link Fence Brace System (Foot Ball Field) Elevation Details | GEN | Qassim | 2026-07-13 |  | 2026-07-21 | 8 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 248 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0106-00 | 00 | ADV-0106 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-GEN-SDW-0301-00 | 4.50M High Chain Link Fence Brace System (Foot Ball Field) Elevation Details | GEN | Hail | 2026-07-13 |  | 2026-07-21 | 8 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 249 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0106-00 | 00 | ADV-0106 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-GEN-SDW-0301-00 | 4.50M High Chain Link Fence Brace System (Foot Ball Field) Elevation Details | GEN | Tabuk | 2026-07-13 |  | 2026-07-21 | 8 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 250 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0106-00 | 00 | ADV-0106 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-GEN-SDW-0302-00 | 2.0M WIDE x 4.50M HIGH DOUBLE LEAF GATE (FOOT BALL FIELD) ELEVATION & DETAILS | GEN | Qassim | 2026-07-13 |  | 2026-07-21 | 8 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 251 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0106-00 | 00 | ADV-0106 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-GEN-SDW-0302-00 | 2.0M WIDE x 4.50M HIGH DOUBLE LEAF GATE (FOOT BALL FIELD) ELEVATION & DETAILS | GEN | Hail | 2026-07-13 |  | 2026-07-21 | 8 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 252 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0106-00 | 00 | ADV-0106 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-GEN-SDW-0302-00 | 2.0M WIDE x 4.50M HIGH DOUBLE LEAF GATE (FOOT BALL FIELD) ELEVATION & DETAILS | GEN | Tabuk | 2026-07-13 |  | 2026-07-21 | 8 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 253 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0106-00 | 00 | ADV-0106 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-GEN-SDW-0303-00 | 2.10M High Chain Link Fence Brace System (Basket Ball Field) Elevation Details | GEN | Qassim | 2026-07-13 |  | 2026-07-21 | 8 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 254 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0106-00 | 00 | ADV-0106 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-GEN-SDW-0303-00 | 2.10M High Chain Link Fence Brace System (Basket Ball Field) Elevation Details | GEN | Hail | 2026-07-13 |  | 2026-07-21 | 8 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 255 | MLTX-02-003-ADV-TS9-1-GEN-SDW-0106-00 | 00 | ADV-0106 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-GEN-SDW-0303-00 | 2.10M High Chain Link Fence Brace System (Basket Ball Field) Elevation Details | GEN | Tabuk | 2026-07-13 |  | 2026-07-21 | 8 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 256 | MLTX-02-003-ADV-TS9-1-STR-SDW-0107-00 | 00 | ADV-0107 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-STR-SDW-3102-00 | SCHEDULE AND DETAILS | STR | Qassim | 2026-07-13 |  | 2026-07-15 | 2 Days | C | These Drawings have been superseded with the Transmittal No. MLTX-02-003-ADV-TS9-1-STR-SDW-0111-00, Revision will not be submitted as per Engr. Khaled Badawy (ADV)
|  | 257 | MLTX-02-003-ADV-TS9-1-STR-SDW-0107-00 | 00 | ADV-0107 | SDW | MLTX-02-003-TAB4 -ADV-TS9-1-STR-SDW-3102-00 | SCHEDULE AND DETAILS | STR | Tabuk | 2026-07-13 |  | 2026-07-15 | 2 Days | C
|  | 258 | MLTX-02-003-ADV-TS9-1-STR-SDW-0107-00 | 00 | ADV-0107 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-STR-SDW-3103-00 | GLASS FACADE STEEL FRAMES PLAN AND ELEVATION | STR | Qassim | 2026-07-13 |  | 2026-07-15 | 2 Days | C
|  | 259 | MLTX-02-003-ADV-TS9-1-STR-SDW-0107-00 | 00 | ADV-0107 | SDW | MLTX-02-003-TAB4 -ADV-TS9-1-STR-SDW-3103-00 | GLASS FACADE STEEL FRAMES PLAN AND ELEVATION | STR | Tabuk | 2026-07-13 |  | 2026-07-15 | 2 Days | C
|  | 260 | MLTX-02-003-ADV-TS9-1-STR-SDW-0107-00 | 00 | ADV-0107 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-STR-SDW-3104-00 | STEEL COLUMN DESCRIPTION | STR | Qassim | 2026-07-13 |  | 2026-07-15 | 2 Days | C
|  | 261 | MLTX-02-003-ADV-TS9-1-STR-SDW-0107-00 | 00 | ADV-0107 | SDW | MLTX-02-003-TAB4 -ADV-TS9-1-STR-SDW-3104-00 | STEEL COLUMN DESCRIPTION | STR | Tabuk | 2026-07-13 |  | 2026-07-15 | 2 Days | C
|  | 262 | MLTX-02-003-ADV-TS9-1-STR-SDW-0107-00 | 00 | ADV-0107 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-STR-SDW-3105-00 | STRUCTURE FOUNDATION COORDINATION | STR | Qassim | 2026-07-13 |  | 2026-07-15 | 2 Days | C
|  | 263 | MLTX-02-003-ADV-TS9-1-STR-SDW-0107-00 | 00 | ADV-0107 | SDW | MLTX-02-003-TAB4 -ADV-TS9-1-STR-SDW-3105-00 | STRUCTURE FOUNDATION COORDINATION | STR | Tabuk | 2026-07-13 |  | 2026-07-15 | 2 Days | C
|  | 265 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0108-00 | 00 | ADV-0108 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-MEC-SDW-0201-00 | MECHANICAL PLAN | MEC | Qassim | 2026-07-21 |  | 2026-07-22 | 1 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 266 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0108-00 | 00 | ADV-0108 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-MEC-SDW-0202-00 | MECH DETAILS | MEC | Qassim | 2026-07-21 |  | 2026-07-22 | 1 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 268 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0109-00 | 00 | ADV-0109 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-MEC-SDW-0201-00 | MECHANICAL PLAN | MEC | Tabuk | 2026-07-21 |  | 2026-07-23 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 269 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0109-00 | 00 | ADV-0109 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-MEC-SDW-0202-00 | MECH DETAILS | MEC | Tabuk | 2026-07-21 |  | 2026-07-23 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 270 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0110-00 | 00 | ADV-0110 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-0200-00 | POWER PLAN TABUK | ELE | Tabuk | 2026-07-15 |  | 2026-07-20 | 5 Days | C | These Drawings have been superseded with the Transmittal No. MLTX-02-003-ADV-TS9-1-ELE-SDW-0114-00, Revision will not be submitted as per Engr. Islam Moustafa (ADV)
|  | 271 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0110-00 | 00 | ADV-0110 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-0201-00 | POWER SINGLE LINE DIAGRAM TABUK | ELE | Tabuk | 2026-07-15 |  | 2026-07-20 | 5 Days | C
|  | 272 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0110-00 | 00 | ADV-0110 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-0202-00 | PANEL LOAD SCHEDULE MDB TABUK | ELE | Tabuk | 2026-07-15 |  | 2026-07-20 | 5 Days | C
|  | 273 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0110-00 | 00 | ADV-0110 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-0203-00 | VOLTAGE DROP TABUK | ELE | Tabuk | 2026-07-15 |  | 2026-07-20 | 5 Days | C
|  | 274 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0110-00 | 00 | ADV-0110 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-0204-00 | GENERATOR SIZE TABUK | ELE | Tabuk | 2026-07-15 |  | 2026-07-20 | 5 Days | C | These Drawings have been superseded with the Transmittal No. MLTX-02-003-ADV-TS9-1-ELE-SDW-0121-00, Revision will not be submitted as per Engr. Islam Moustafa (ADV)
|  | 275 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0110-00 | 00 | ADV-0110 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-0205-00 | ELECT CONSTRUCTION LAYOUT TABUK | ELE | Tabuk | 2026-07-15 |  | 2026-07-20 | 5 Days | C | These Drawings have been superseded with the Transmittal No. MLTX-02-003-ADV-TS9-1-ELE-SDW-0115-00, Revision will not be submitted as per Engr. Islam Moustafa (ADV)
|  | 276 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0110-00 | 00 | ADV-0110 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-0206-00 | PLC SINGLE LINE DIAGRAM TABUK | ELE | Tabuk | 2026-07-15 |  | 2026-07-20 | 5 Days | C
|  | 277 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0110-00 | 00 | ADV-0110 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-0207-00 | SLD GENERAL TABUK | ELE | Tabuk | 2026-07-15 |  | 2026-07-20 | 5 Days | C | As per Engr. Islam Moustafa 's instruction, this drawing has been cancelled, revision will not be submitted.
|  | 278 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0110-00 | 00 | ADV-0110 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-0208-00 | EARTHING CALCULATION TABUK | ELE | Tabuk | 2026-07-15 |  | 2026-07-20 | 5 Days | C | These Drawings have been superseded with the Transmittal No. MLTX-02-003-ADV-TS9-1-ELE-SDW-0113-00, Revision will not be submitted as per Engr. Islam Moustafa (ADV)
|  | 279 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0110-00 | 00 | ADV-0110 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-0209-00 | CCTV LAYOUT TABUK | ELE | Tabuk | 2026-07-15 |  | 2026-07-20 | 5 Days | C | As per Engr. Islam Moustafa 's instruction, this drawing has been cancelled, revision will not be submitted.
|  | 280 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0110-00 | 00 | ADV-0110 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-0210-00 | CCTV SYSTEM DIAGRAM TABUK | ELE | Tabuk | 2026-07-15 |  | 2026-07-20 | 5 Days | C
|  | 281 | MLTX-02-003-ADV-TS9-1-STR-SDW-0111-00 | 03 | ADV-0111 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-STR-SDW-3100-00 | IDENTICAL – FOUNDATION LOCATION LAYOUT PLAN | STR | Qassim | 2026-07-22 |  | 2026-07-23 | 1 Days | B | 2026-08-18 | 2026-08-20 | 2 Days | C | 2026-08-24 | 2026-08-31 | 7 Days | C | 2026-09-03 | 2026-09-05 | 2 Days | C | 2026-09-10 | 2026-09-14 | 4 Days | B |  | 1 |  |  |  |  | Approved with Comments
|  | 282 | MLTX-02-003-ADV-TS9-1-STR-SDW-0111-00 | 03 | ADV-0111 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-STR-SDW-3100-00 | IDENTICAL – FOUNDATION LOCATION LAYOUT PLAN | STR | Tabuk | 2026-07-22 |  | 2026-07-23 | 1 Days | B | 2026-08-18 | 2026-08-20 | 2 Days | C | 2026-08-24 | 2026-08-31 | 7 Days | C | 2026-09-03 | 2026-09-05 | 2 Days | C | 2026-09-10 | 2026-09-14 | 4 Days | B |  | 1 |  |  |  |  | Approved with Comments
|  | 283 | MLTX-02-003-ADV-TS9-1-STR-SDW-0111-00 | 03 | ADV-0111 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-STR-SDW-3101-00 | IDENTICAL - DOME FOUNDATION LAYOUT PLAN & SECTION | STR | Qassim | 2026-07-22 |  | 2026-07-23 | 1 Days | B | 2026-08-18 | 2026-08-20 | 2 Days | C | 2026-08-24 | 2026-08-31 | 7 Days | C | 2026-09-03 | 2026-09-05 | 2 Days | C | 2026-09-10 | 2026-09-14 | 4 Days | B |  | 1 |  |  |  |  | Approved with Comments
|  | 284 | MLTX-02-003-ADV-TS9-1-STR-SDW-0111-00 | 03 | ADV-0111 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-STR-SDW-3101-00 | IDENTICAL - DOME FOUNDATION LAYOUT PLAN & SECTION | STR | Tabuk | 2026-07-22 |  | 2026-07-23 | 1 Days | B | 2026-08-18 | 2026-08-20 | 2 Days | C | 2026-08-24 | 2026-08-31 | 7 Days | C | 2026-09-03 | 2026-09-05 | 2 Days | C | 2026-09-10 | 2026-09-14 | 4 Days | B |  | 1 |  |  |  |  | Approved with Comments
|  | 285 | MLTX-02-003-ADV-TS9-1-STR-SDW-0111-00 | 03 | ADV-0111 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-STR-SDW-3102-00 | STEEL MEMBERS SCHEDULE AND DETAILS | STR | Qassim | 2026-07-22 |  | 2026-07-23 | 1 Days | B | 2026-08-18 | 2026-08-20 | 2 Days | C | 2026-08-24 | 2026-08-31 | 7 Days | C | 2026-09-03 | 2026-09-05 | 2 Days | C | 2026-09-10 | 2026-09-14 | 4 Days | B |  | 1 |  |  |  |  | Approved with Comments
|  | 286 | MLTX-02-003-ADV-TS9-1-STR-SDW-0111-00 | 03 | ADV-0111 | SDW | MLTX-02-003-TAB4 -ADV-TS9-1-STR-SDW-3102-00 | STEEL MEMBERS SCHEDULE AND DETAILS | STR | Tabuk | 2026-07-22 |  | 2026-07-23 | 1 Days | B | 2026-08-18 | 2026-08-20 | 2 Days | C | 2026-08-24 | 2026-08-31 | 7 Days | C | 2026-09-03 | 2026-09-05 | 2 Days | C | 2026-09-10 | 2026-09-14 | 4 Days | B |  | 1 |  |  |  |  | Approved with Comments
|  | 287 | MLTX-02-003-ADV-TS9-1-STR-SDW-0111-00 | 03 | ADV-0111 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-STR-SDW-3103-00 | GLASS FACADE STEEL FRAMES PLAN AND ELEVATION | STR | Qassim | 2026-07-22 |  | 2026-07-23 | 1 Days | B | 2026-08-18 | 2026-08-20 | 2 Days | C | 2026-08-24 | 2026-08-31 | 7 Days | C | 2026-09-03 | 2026-09-05 | 2 Days | C | 2026-09-10 | 2026-09-14 | 4 Days | B |  | 1 |  |  |  |  | Approved with Comments
|  | 288 | MLTX-02-003-ADV-TS9-1-STR-SDW-0111-00 | 03 | ADV-0111 | SDW | MLTX-02-003-TAB4 -ADV-TS9-1-STR-SDW-3103-00 | GLASS FACADE STEEL FRAMES PLAN AND ELEVATION | STR | Tabuk | 2026-07-22 |  | 2026-07-23 | 1 Days | B | 2026-08-18 | 2026-08-20 | 2 Days | C | 2026-08-24 | 2026-08-31 | 7 Days | C | 2026-09-03 | 2026-09-05 | 2 Days | C | 2026-09-10 | 2026-09-14 | 4 Days | B |  | 1 |  |  |  |  | Approved with Comments
|  | 289 | MLTX-02-003-ADV-TS9-1-STR-SDW-0111-00 | 03 | ADV-0111 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-STR-SDW-3104-00 | STEEL COLUMN LAYOUT PLAN | STR | Qassim | 2026-07-22 |  | 2026-07-23 | 1 Days | B | 2026-08-18 | 2026-08-20 | 2 Days | C | 2026-08-24 | 2026-08-31 | 7 Days | C | 2026-09-03 | 2026-09-05 | 2 Days | C | 2026-09-10 | 2026-09-14 | 4 Days | B |  | 1 |  |  |  |  | Approved with Comments
|  | 290 | MLTX-02-003-ADV-TS9-1-STR-SDW-0111-00 | 03 | ADV-0111 | SDW | MLTX-02-003-TAB4 -ADV-TS9-1-STR-SDW-3104-00 | STEEL COLUMN LAYOUT PLAN | STR | Tabuk | 2026-07-22 |  | 2026-07-23 | 1 Days | B | 2026-08-18 | 2026-08-20 | 2 Days | C | 2026-08-24 | 2026-08-31 | 7 Days | C | 2026-09-03 | 2026-09-05 | 2 Days | C | 2026-09-10 | 2026-09-14 | 4 Days | B |  | 1 |  |  |  |  | Approved with Comments
|  | 291 | MLTX-02-003-ADV-TS9-1-STR-SDW-0111-00 | 03 | ADV-0111 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-STR-SDW-3105-00 | CURTAIN WALL FOUNDATION COORDINATION | STR | Qassim | 2026-07-22 |  | 2026-07-23 | 1 Days | B | 2026-08-18 | 2026-08-20 | 2 Days | C | 2026-08-24 | 2026-08-31 | 7 Days | C | 2026-09-03 | 2026-09-05 | 2 Days | C | 2026-09-10 | 2026-09-14 | 4 Days | B |  | 1 |  |  |  |  | Approved with Comments
|  | 292 | MLTX-02-003-ADV-TS9-1-STR-SDW-0111-00 | 03 | ADV-0111 | SDW | MLTX-02-003-TAB4 -ADV-TS9-1-STR-SDW-3105-00 | CURTAIN WALL FOUNDATION COORDINATION | STR | Tabuk | 2026-07-22 |  | 2026-07-23 | 1 Days | B | 2026-08-18 | 2026-08-20 | 2 Days | C | 2026-08-24 | 2026-08-31 | 7 Days | C | 2026-09-03 | 2026-09-05 | 2 Days | C | 2026-09-10 | 2026-09-14 | 4 Days | B |  | 1 |  |  |  |  | Approved with Comments
|  | 293 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0112-00 | 00 | ADV-0112 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-0208-00 | PLC SINGLE LINE DIAGRAM TABUK | ELE | Tabuk | 2026-07-23 |  | 2026-07-23 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 294 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0113-00 | 00 | ADV-0113 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-0200-00 | EARTHING TABUK | ELE | Tabuk | 2026-07-23 |  | 2026-07-23 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 295 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0113-00 | 00 | ADV-0113 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-0201-00 | POWER SINGLE LINE DIAGRAM TABUK | ELE | Tabuk | 2026-07-23 |  | 2026-07-23 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 296 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0114-00 | 01 | ADV-0114 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-0202-00 | HVAC POWER PLAN TABUK | ELE | Tabuk | 2026-07-23 |  | 2026-07-25 | 2 Days | B | 2026-08-30 | 2026-09-19 | 20 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 297 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0114-00 | 01 | ADV-0114 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-0203-00 | POWER SINGLE LINE DIAGRAM TABUK | ELE | Tabuk | 2026-07-23 |  | 2026-07-25 | 2 Days | B | 2026-08-30 | 2026-09-19 | 20 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 298 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0114-00 | 01 | ADV-0114 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-0204-00 | PANEL LOAD SCHEDULE MDB TABUK | ELE | Tabuk | 2026-07-23 |  | 2026-07-25 | 2 Days | B | 2026-08-30 | 2026-09-19 | 20 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 299 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0114-00 | 01 | ADV-0114 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-0205-00 | VOLTAGE DROP CALCULATION TABUK | ELE | Tabuk | 2026-07-23 |  | 2026-07-25 | 2 Days | B | 2026-08-30 | 2026-09-19 | 20 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 300 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0115-00 | 00 | ADV-0115 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-0206-00 | ELECT CONSTRUCTION LAYOUT TABUK | ELE | Tabuk | 2026-07-23 |  | 2026-07-25 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 301 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0115-00 | 00 | ADV-0115 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-0207-00 | PLC SINGLE LINE DIAGRAM TABUK | ELE | Tabuk | 2026-07-23 |  | 2026-07-25 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 302 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0116-00 | 00 | ADV-0116 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-0200-00 | EARTHING QASSIM | ELE | Qassim | 2026-07-23 |  | 2026-07-23 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 303 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0116-00 | 00 | ADV-0116 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-0201-00 | EARTHING CALCULATION QASSIM | ELE | Qassim | 2026-07-23 |  | 2026-07-23 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 304 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0117-00 | 00 | ADV-0117 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-0206-00 | Lighting Shop Drawing QASSIM | ELE | Qassim | 2026-07-23 |  | 2026-07-23 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 305 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0117-00 | 00 | ADV-0117 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-0207-00 | PLC SINGLE LINE DIAGRAM QASSIM | ELE | Qassim | 2026-07-23 |  | 2026-07-23 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 306 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0118-00 | 01 | ADV-0118 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-0202-00 | HVAC POWER PLAN Qassim | ELE | Qassim | 2026-07-23 |  | 2026-07-23 | 0 Days | B | 2026-08-30 | 2026-09-09 | 10 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 307 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0118-00 | 01 | ADV-0118 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-0203-00 | POWER SINGLE LINE DIAGRAM Qassim | ELE | Qassim | 2026-07-23 |  | 2026-07-23 | 0 Days | B | 2026-08-30 | 2026-09-09 | 10 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 308 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0118-00 | 01 | ADV-0118 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-0204-00 | PANEL LOAD SCHEDULE MDB Qassim | ELE | Qassim | 2026-07-23 |  | 2026-07-23 | 0 Days | B | 2026-08-30 | 2026-09-09 | 10 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 309 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0118-00 | 01 | ADV-0118 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-0205-00 | VOLTAGE DROP CALCULATION Qassim | ELE | Qassim | 2026-07-23 |  | 2026-07-23 | 0 Days | B | 2026-08-30 | 2026-09-09 | 10 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 310 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0119-00 | 00 | ADV-0119 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-0208-00 | PLC SINGLE LINE DIAGRAM Qassim | ELE | Qassim | 2026-07-23 |  | 2026-07-23 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 311 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0120-00 | 00 | ADV-0120 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-0209-00 | Generator Size QASIM | ELE | Qassim | 2026-07-23 |  | 2026-07-25 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 312 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0121-00 | 00 | ADV-0121 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-0209-00 | GENERATOR SIZE TABUK | ELE | Tabuk | 2026-07-23 |  | 2026-07-25 | 2 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 313 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0122-00 | 01 | ADV-0122 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LSP-SDW-0300-00 | DETAILS OF FOOTBALL PLAYGROUND | LSP | Qassim | 2026-08-04 |  | 2026-08-18 | 14 Days | B | 2026-08-24 | 2026-09-12 | 19 Days | C | 2026-09-24 | 2026-09-27 | 3 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 314 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0122-00 | 01 | ADV-0122 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-LSP-SDW-0300-00 | DETAILS OF FOOTBALL PLAYGROUND | LSP | Hail | 2026-08-04 |  | 2026-08-18 | 14 Days | B | 2026-08-24 | 2026-09-12 | 19 Days | C | 2026-09-24 | 2026-09-27 | 3 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 315 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0122-00 | 01 | ADV-0122 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-LSP-SDW-0300-00 | DETAILS OF FOOTBALL PLAYGROUND | LSP | Tabuk | 2026-08-04 |  | 2026-08-18 | 14 Days | B | 2026-08-24 | 2026-09-12 | 19 Days | C | 2026-09-24 | 2026-09-27 | 3 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 316 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0123-00 | 00 | ADV-0123 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LSP-SDW-0302-00 | DETAILS OF RUBBER TILES & PATHS QASSIM | LSP | Qassim | 2026-08-05 |  | 2026-08-15 | 10 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 317 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0124-00 | 00 | ADV-0124 | SDW | MLTX-02-003-TAB4 -ADV-TS9-1-LSP-SDW-0302-00 | DETAILS OF RUBBER TILES & PATHS Tabuk | LSP | Tabuk | 2026-08-05 |  | 2026-08-05 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 318 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0125-00 | 00 | ADV-0125 | SDW | MLTX-02-003-HAL1- ADV-TS9-1-LSP-SDW-0302-00 | DETAILS OF RUBBER TILES & PATHS HAIL | LSP | Hail | 2026-08-05 |  | 2026-08-15 | 10 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 319 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0126-00 | 01 | ADV-0126 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LSP-SDW-0301-00 | DETAILS OF BASKETBALL COURT | LSP | Qassim | 2026-08-05 |  | 2026-08-20 | 15 Days | B | 2026-08-24 | 2026-09-09 | 16 Days | C | 2026-09-24 | 2026-09-26 | 2 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 320 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0126-00 | 01 | ADV-0126 | SDW | MLTX-02-003-TAB4 -ADV-TS9-1-LSP-SDW-0301-00 | DETAILS OF BASKETBALL COURT | LSP | Tabuk | 2026-08-05 |  | 2026-08-20 | 15 Days | B | 2026-08-24 | 2026-09-09 | 16 Days | C | 2026-09-24 | 2026-09-26 | 2 Days | B | [9 empty] | 1 |  |  |  |  | Approved with Comments
|  | 321 | MLTX-02-003-ADV-TS9-1-STR-SDW-0127-00 | 00 | ADV-0127 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-STR-SDW-6100-00 | FOUNDATION DETAIL OF 6.0 m OCTAGONAL LIGHTING POLE (150KPA) | STR | Qassim | 2026-08-18 |  | 2026-09-03 | 16 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 322 | MLTX-02-003-ADV-TS9-1-STR-SDW-0127-00 | 00 | ADV-0127 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-STR-SDW-6100-00 | FOUNDATION DETAIL OF 6.0 m OCTAGONAL LIGHTING POLE (150KPA) | STR | Hail | 2026-08-18 |  | 2026-09-03 | 16 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 323 | MLTX-02-003-ADV-TS9-1-STR-SDW-0127-00 | 00 | ADV-0127 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-STR-SDW-6100-00 | FOUNDATION DETAIL OF 6.0 m OCTAGONAL LIGHTING POLE (150KPA) | STR | Tabuk | 2026-08-18 |  | 2026-09-03 | 16 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 324 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0128-00 | 00 | ADV-0128 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LSP-SDW-0303-00 | Paddle Court Posts & Glass Details | LSP | Qassim | 2026-08-18 |  | 2026-08-31 | 13 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 325 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0128-00 | 00 | ADV-0128 | SDW | MLTX-02-003-TAB4 -ADV-TS9-1-LSP-SDW-0303-00 | Paddle Court Posts & Glass Details | LSP | Tabuk | 2026-08-18 |  | 2026-08-31 | 13 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 326 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0128-00 | 00 | ADV-0128 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LSP-SDW-0304-00 | Paddle Court Assembly Details(2) | LSP | Qassim | 2026-08-18 |  | 2026-08-31 | 13 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 327 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0128-00 | 00 | ADV-0128 | SDW | MLTX-02-003-TAB4 -ADV-TS9-1-LSP-SDW-0304-00 | Paddle Court Assembly Details(2) | LSP | Tabuk | 2026-08-18 |  | 2026-08-31 | 13 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 328 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0128-00 | 00 | ADV-0128 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LSP-SDW-0305-00 | Paddle Court Assembly Details | LSP | Qassim | 2026-08-18 |  | 2026-08-31 | 13 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 329 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0128-00 | 00 | ADV-0128 | SDW | MLTX-02-003-TAB4 -ADV-TS9-1-LSP-SDW-0305-00 | Paddle Court Assembly Details | LSP | Tabuk | 2026-08-18 |  | 2026-08-31 | 13 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 330 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0128-00 | 00 | ADV-0128 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LSP-SDW-0306-00 | Padel Court - Site Development Layout | LSP | Qassim | 2026-08-18 |  | 2026-08-31 | 13 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 331 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0128-00 | 00 | ADV-0128 | SDW | MLTX-02-003-TAB4 -ADV-TS9-1-LSP-SDW-0306-00 | Padel Court - Site Development Layout | LSP | Tabuk | 2026-08-18 |  | 2026-08-31 | 13 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 332 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0128-00 | 00 | ADV-0128 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LSP-SDW-0307-00 | Padel Court -Plan &Elevation &Side View Dimensions | LSP | Qassim | 2026-08-18 |  | 2026-08-31 | 13 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 333 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0128-00 | 00 | ADV-0128 | SDW | MLTX-02-003-TAB4 -ADV-TS9-1-LSP-SDW-0307-00 | Padel Court -Plan &Elevation &Side View Dimensions | LSP | Tabuk | 2026-08-18 |  | 2026-08-31 | 13 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 334 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0128-00 | 00 | ADV-0128 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LSP-SDW-0308-00 | Padel Court - Foundation Layout | LSP | Qassim | 2026-08-18 |  | 2026-08-31 | 13 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 335 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0128-00 | 00 | ADV-0128 | SDW | MLTX-02-003-TAB4 -ADV-TS9-1-LSP-SDW-0308-00 | Padel Court - Foundation Layout | LSP | Tabuk | 2026-08-18 |  | 2026-08-31 | 13 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 336 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0128-00 | 00 | ADV-0128 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LSP-SDW-0309-00 | Padel Court - Installation Details | LSP | Qassim | 2026-08-18 |  | 2026-08-31 | 13 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 337 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0128-00 | 00 | ADV-0128 | SDW | MLTX-02-003-TAB4 -ADV-TS9-1-LSP-SDW-0309-00 | Padel Court - Installation Details | LSP | Tabuk | 2026-08-18 |  | 2026-08-31 | 13 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 338 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0128-00 | 00 | ADV-0128 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LSP-SDW-0310-00 | Padel Court -COORDINATES | LSP | Qassim | 2026-08-18 |  | 2026-08-31 | 13 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 339 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0128-00 | 00 | ADV-0128 | SDW | MLTX-02-003-TAB4 -ADV-TS9-1-LSP-SDW-0310-00 | Padel Court -COORDINATES | LSP | Tabuk | 2026-08-18 |  | 2026-08-31 | 13 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 340 | MLTX-02-003-ADV-TS9-1-STR-SDW-0129-00 | 01 | ADV-0129 | SDW | MTLX-02-003-HAL1-ADV-TS9-1-STR-SDW-6100-00 | IRRIGATION TANK - Concrete Details for Foundation Plan & Walls | STR | Hail | 2026-08-22 |  | 2026-09-02 | 11 Days | C | 2026-10-01 |  | 0 Days | UR | [16 empty] | 1 |  | Under Review
|  | 341 | MLTX-02-003-ADV-TS9-1-STR-SDW-0129-00 | 01 | ADV-0129 | SDW | MTLX-02-003-HAL1-ADV-TS9-1-STR-SDW-6101-00 | IRRIGATION TANK PLAN - Concrete Details for Roof Slab Plan & Walls | STR | Hail | 2026-08-22 |  | 2026-09-02 | 11 Days | C | 2026-10-01 |  | 0 Days | UR | [16 empty] | 1 |  | Under Review
|  | 342 | MLTX-02-003-ADV-TS9-1-STR-SDW-0129-00 | 01 | ADV-0129 | SDW | MTLX-02-003-HAL1-ADV-TS9-1-STR-SDW-6102-00 | IRRIGATION TANK - Reinforcement Detail For Foundation Plan & Wall Sections | STR | Hail | 2026-08-22 |  | 2026-09-02 | 11 Days | C | 2026-10-01 |  | 0 Days | UR | [16 empty] | 1 |  | Under Review
|  | 343 | MLTX-02-003-ADV-TS9-1-STR-SDW-0129-00 | 01 | ADV-0129 | SDW | MTLX-02-003-HAL1-ADV-TS9-1-STR-SDW-6103-00 | IRRIGATION TANK - Reinforcement Details For Roof Slab Plan & Walls Sections | STR | Hail | 2026-08-22 |  | 2026-09-02 | 11 Days | C | 2026-10-01 |  | 0 Days | UR | [16 empty] | 1 |  | Under Review
|  | 344 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0130-00 | 00 | ADV-0130 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-LSP-SDW-3100-00 | IDENTICAL – FOUNDATION LOCATION LAYOUT PLAN | LSP | Qassim | 2026-08-22 |  | 2026-08-25 | 3 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 345 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0131-00 | 00 | ADV-0131 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-LS-SDW-0500-00 | HAIL-IRRIGATION TANK COORDINATES AND LEVELS | LSP | Hail | 2026-08-23 |  | 2026-08-29 | 6 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 346 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0132-00 | 00 | ADV-0132 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-AR-SDW-0302-00 | TOILET PLAN SECTIONAL & ELEVATIONS DETAILS LAYOUT - 1 | ARC | Hail | 2026-08-29 |  | 2026-09-13 | 15 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 347 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0132-00 | 00 | ADV-0132 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-AR-SDW-0302-00 | TOILET PLAN SECTIONAL & ELEVATIONS DETAILS LAYOUT - 1 | ARC | Qassim | 2026-08-29 |  | 2026-09-13 | 15 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 348 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0132-00 | 00 | ADV-0132 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-AR-SDW-0302-00 | TOILET PLAN SECTIONAL & ELEVATIONS DETAILS LAYOUT - 1 | ARC | Tabuk | 2026-08-29 |  | 2026-09-13 | 15 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 349 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0132-00 | 00 | ADV-0132 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-AR-SDW-0303-00 | TOILET SECTIONAL & ELEVATIONS DETAILS LAYOUT - 2 | ARC | Hail | 2026-08-29 |  | 2026-09-13 | 15 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 350 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0132-00 | 00 | ADV-0132 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-AR-SDW-0303-00 | TOILET SECTIONAL & ELEVATIONS DETAILS LAYOUT - 2 | ARC | Qassim | 2026-08-29 |  | 2026-09-13 | 15 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 351 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0132-00 | 00 | ADV-0132 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-AR-SDW-0303-00 | TOILET SECTIONAL & ELEVATIONS DETAILS LAYOUT - 2 | ARC | Tabuk | 2026-08-29 |  | 2026-09-13 | 15 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 352 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0132-00 | 00 | ADV-0132 | SDW | MLTX-02-003-HAL1-ADV-TS9-1-AR-SDW-0304-00 | TOILET SECTIONAL & ELEVATIONS DETAILS LAYOUT - 3 | ARC | Hail | 2026-08-29 |  | 2026-09-13 | 15 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 353 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0132-00 | 00 | ADV-0132 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-AR-SDW-0304-00 | TOILET SECTIONAL & ELEVATIONS DETAILS LAYOUT - 3 | ARC | Qassim | 2026-08-29 |  | 2026-09-13 | 15 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 354 | MLTX-02-003-ADV-TS9-1-ARC-SDW-0132-00 | 00 | ADV-0132 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-AR-SDW-0304-00 | TOILET SECTIONAL & ELEVATIONS DETAILS LAYOUT - 3 | ARC | Tabuk | 2026-08-29 |  | 2026-09-13 | 15 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 355 | MLTX-02-003-ADV-TS9-1-STR-SDW-0133-00 | 00 | ADV-0133 | SDW | MTLX-02-003-TAB4-ADV-TS9-1-STR-SDW-3100-00 | SEPTIC TANK - Concrete Details for – Foundation Plan & Walls | STR | Tabuk | 2026-08-30 |  | 2026-09-06 | 7 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 356 | MLTX-02-003-ADV-TS9-1-STR-SDW-0133-00 | 00 | ADV-0133 | SDW | MTLX-02-003-TAB4-ADV-TS9-1-STR-SDW-3101-00 | SEPTIC TANK PLAN - Concrete Details for – Roof Slab Plan & Walls | STR | Tabuk | 2026-08-30 |  | 2026-09-06 | 7 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 357 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0134-00 | 00 | ADV-0134 | SDW | MTLX-02-003-HAL1-ADV-TS9-1-MEC-SDW-6100-00 | IRRIGATION PUMP ROOM | MEC | Hail | 2026-09-06 |  | 2026-09-07 | 1 Days | C | 2026-09-15 | 2026-09-16 | 1 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 358 | MLTX-02-003-ADV-TS9-1-LSP-SDW-0135-00 | 00 | ADV-0135 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-LS-SDW-3100-00 | FOUNDATIONLOCATION LAYOUT PLAN LANDSCAPE | LSP | Tabuk | 2026-09-06 |  | 2026-09-12 | 6 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 359 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0136-00 | 00 | ADV-0136 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-MEC-SDW-0203-00 | AIR DOME FIRE FIGHTING | MEC | Tabuk | 2026-09-22 |  | 2026-09-24 | 2 Days | C | [18 empty] | 1 |  |  |  | Revise & Resubmit
|  | 360 | MLTX-02-003-ADV-TS9-1-MEC-SDW-0137-00 | 00 | ADV-0137 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-MEC-SDW-0203-00 | AIR DOME FIRE FIGHTING - QASSIM | MEC | Qassim | 2026-09-22 |  | 2026-09-26 | 4 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 361 | MLTX-02-003-ADV-TS9-1-STR-SDW-0138-00 | 00 | ADV-0138 | SDW | MTLX-02-003-TAB4-ADV-TS9-1-STR-SDW-3201-00 | A.D CURTAIN WALL STEEL STRUCTURE BASE PLATE LAYOUT | STR | Tabuk & Qassim | 2026-09-30 |  | 2026-09-30 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 362 | MLTX-02-003-ADV-TS9-1-STR-SDW-0138-00 | 00 | ADV-0138 | SDW | MTLX-02-003-QSM3-ADV-TS9-1-STR-SDW-3201-00 | A.D CURTAIN WALL STEEL STRUCTURE BASE PLATE LAYOUT | STR | Tabuk & Qassim | 2026-09-30 |  | 2026-09-30 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 363 | MLTX-02-003-ADV-TS9-1-STR-SDW-0138-00 | 00 | ADV-0138 | SDW | MTLX-02-003-TAB4-ADV-TS9-1-STR-SDW-3202-00 | A.D CURTAIN WALL STEEL STRUCTURE CONCRETE COLUMN LAYOUT & SECTION DETAILS | STR | Tabuk & Qassim | 2026-09-30 |  | 2026-09-30 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 364 | MLTX-02-003-ADV-TS9-1-STR-SDW-0138-00 | 00 | ADV-0138 | SDW | MTLX-02-003-QSM3-ADV-TS9-1-STR-SDW-3202-00 | A.D CURTAIN WALL STEEL STRUCTURE CONCRETE COLUMN LAYOUT & SECTION DETAILS | STR | Tabuk & Qassim | 2026-09-30 |  | 2026-09-30 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 365 | MLTX-02-003-ADV-TS9-1-STR-SDW-0138-00 | 00 | ADV-0138 | SDW | MTLX-02-003-TAB4-ADV-TS9-1-STR-SDW-3203-00 | A.D CURTAIN WALL STEEL STRUCTURE CONNECTION DETAILS | STR | Tabuk & Qassim | 2026-09-30 |  | 2026-09-30 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 366 | MLTX-02-003-ADV-TS9-1-STR-SDW-0138-00 | 00 | ADV-0138 | SDW | MTLX-02-003-QSM3-ADV-TS9-1-STR-SDW-3203-00 | A.D CURTAIN WALL STEEL STRUCTURE CONNECTION DETAILS | STR | Tabuk & Qassim | 2026-09-30 |  | 2026-09-30 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 367 | MLTX-02-003-ADV-TS9-1-STR-SDW-0138-00 | 00 | ADV-0138 | SDW | MTLX-02-003-TAB4-ADV-TS9-1-STR-SDW-3204-00 | A.D CURTAIN WALL STEEL STRUCTURE FRAMING PLAN | STR | Tabuk & Qassim | 2026-09-30 |  | 2026-09-30 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 368 | MLTX-02-003-ADV-TS9-1-STR-SDW-0138-00 | 00 | ADV-0138 | SDW | MTLX-02-003-QSM3-ADV-TS9-1-STR-SDW-3204-00 | A.D CURTAIN WALL STEEL STRUCTURE FRAMING PLAN | STR | Tabuk & Qassim | 2026-09-30 |  | 2026-09-30 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 369 | MLTX-02-003-ADV-TS9-1-STR-SDW-0138-00 | 00 | ADV-0138 | SDW | MTLX-02-003-TAB4-ADV-TS9-1-STR-SDW-3205-00 | A.D CURTAIN WALL STEEL STRUCTURE FRAMING ELEVATION | STR | Tabuk & Qassim | 2026-09-30 |  | 2026-09-30 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 370 | MLTX-02-003-ADV-TS9-1-STR-SDW-0138-00 | 00 | ADV-0138 | SDW | MTLX-02-003-QSM3-ADV-TS9-1-STR-SDW-3205-00 | A.D CURTAIN WALL STEEL STRUCTURE FRAMING ELEVATION | STR | Tabuk & Qassim | 2026-09-30 |  | 2026-09-30 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 371 | MLTX-02-003-ADV-TS9-1-STR-SDW-0138-00 | 00 | ADV-0138 | SDW | MTLX-02-003-TAB4-ADV-TS9-1-STR-SDW-3206-00 | A.D CURTAIN WALL STEEL STRUCTURE SECTIONS-1 | STR | Tabuk & Qassim | 2026-09-30 |  | 2026-09-30 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 372 | MLTX-02-003-ADV-TS9-1-STR-SDW-0138-00 | 00 | ADV-0138 | SDW | MTLX-02-003-QSM3-ADV-TS9-1-STR-SDW-3206-00 | A.D CURTAIN WALL STEEL STRUCTURE SECTIONS-1 | STR | Tabuk & Qassim | 2026-09-30 |  | 2026-09-30 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 373 | MLTX-02-003-ADV-TS9-1-STR-SDW-0138-00 | 00 | ADV-0138 | SDW | MTLX-02-003-TAB4-ADV-TS9-1-STR-SDW-3207-00 | A.D CURTAIN WALL STEEL STRUCTURE SECTIONS-2 | STR | Tabuk & Qassim | 2026-09-30 |  | 2026-09-30 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 374 | MLTX-02-003-ADV-TS9-1-STR-SDW-0138-00 | 00 | ADV-0138 | SDW | MTLX-02-003-QSM3-ADV-TS9-1-STR-SDW-3207-00 | A.D CURTAIN WALL STEEL STRUCTURE SECTIONS-2 | STR | Tabuk & Qassim | 2026-09-30 |  | 2026-09-30 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 375 | MLTX-02-003-ADV-TS9-1-STR-SDW-0138-00 | 00 | ADV-0138 | SDW | MTLX-02-003-TAB4-ADV-TS9-1-STR-SDW-3208-00 | A.D CURTAIN WALL STEEL STRUCTURE FRAMING 3D VIEW | STR | Tabuk & Qassim | 2026-09-30 |  | 2026-09-30 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 376 | MLTX-02-003-ADV-TS9-1-STR-SDW-0138-00 | 00 | ADV-0138 | SDW | MTLX-02-003-QSM3-ADV-TS9-1-STR-SDW-3208-00 | A.D CURTAIN WALL STEEL STRUCTURE FRAMING 3D VIEW | STR | Tabuk & Qassim | 2026-09-30 |  | 2026-09-30 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 377 | MLTX-02-003-ADV-TS9-1-STR-SDW-0138-00 | 00 | ADV-0138 | SDW | MTLX-02-003-TAB4-ADV-TS9-1-STR-SDW-3209-00 | A.D CURTAIN WALL STEEL STRUCTURE SCHEDULES, SECTIONS & DETAILS | STR | Tabuk & Qassim | 2026-09-30 |  | 2026-09-30 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 378 | MLTX-02-003-ADV-TS9-1-STR-SDW-0138-00 | 00 | ADV-0138 | SDW | MTLX-02-003-QSM3-ADV-TS9-1-STR-SDW-3209-00 | A.D CURTAIN WALL STEEL STRUCTURE SCHEDULES, SECTIONS & DETAILS | STR | Tabuk & Qassim | 2026-09-30 |  | 2026-09-30 | 0 Days | B | [17 empty] | 1 |  |  |  |  | Approved with Comments
|  | 379 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0139-00 | 00 | ADV-0139 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-2010-00 | POWER SINGLE LINE DIAGRAM | ELE | Qassim | 2026-10-01 |  |  | 0 Days | UR | [20 empty] | 1 |  | Under Review
|  | 380 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0140-00 | 00 | ADV-0140 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-2010-00 | POWER SINGLE LINE DIAGRAM | ELE | Tabuk | 2026-10-01 |  |  | 0 Days | UR | [20 empty] | 1 |  | Under Review
|  | 381 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0141-00 | 00 | ADV-0141 | SDW | MLTX-02-003-QSM3-ADV-TS9-1-ELE-SDW-2010-00 | AIR DOME POWER SINGLE LINE DIAGRAM | ELE | Qassim | 2026-10-01 |  |  | 0 Days | UR | [20 empty] | 1 |  | Under Review
|  | 382 | MLTX-02-003-ADV-TS9-1-ELE-SDW-0142-00 | 00 | ADV-0140 | SDW | MLTX-02-003-TAB4-ADV-TS9-1-ELE-SDW-2010-00 | AIR DOME POWER SINGLE LINE DIAGRAM | ELE | Tabuk | 2026-10-01 |  |  | 0 Days | UR | [20 empty] | 1 |  | Under Review
Formulas:
Duration with Egis = IF([Actual Submission Date]="","",(IF([Date of Return Egis]="",TODAY()-[Actual Submission Date],[Date of Return Egis]-[Actual Submission Date])+0)) & " Days "
Note on R195: Email received from Engr Ahmed Refaat: Thu 7/9/2026 3:26 PM

## MSA
[23 empty] | Approved = A |  | 0
[5 empty] | P030 - (MLTX-02-003) - Playgrounds Initiative at (Qassim Oasis , Hail and Tabuk Industrial City) | [17 empty] | Approved with Comments = B |  | 1
[23 empty] | Revise & Resubmit = C |  | 3
[5 empty] | Material Source Approval (MSA) - Submissions & Approvals | [17 empty] | Under PMC Review / For Info. / Rejected / Cancelled / Recalled = D |  | 0
[23 empty] | Under Review = UR |  | 0
[23 empty] | Delayed with ADV |  | 0
[23 empty] | Delayed with Egis |  | 9
[23 empty] | Total Number of Submittals |  | 13
[10 empty] | 1st Submittal - Rev-00 |  |  |  |  | 2nd Submittal - Rev-01 |  |  |  | 3rd Submittal - Rev-02 |  |  |  |  | 4th Submittal - Rev-03 |  |  | 2026-10-01
Transmittle # | Location Area / Floor | SI No. | Transmittal Number | Latest Rev.# | ADV Reference Number | Doc Type | Description | Discipline | Site | Actual Submission Date | Delayed | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | Actual Submission Date | Date of Return Egis | Duration with Egis | Code | A | B | C | D | UR | Delayed with Egis | Remarks
|  | 1 | MLTX-02-003-ADV-MSA-0001-00 | 00 | ADV-0001 | MSA | Material Source Approval "Al-Omaier Trading & contracting. Co" for Backfilling Materials |  | Hail | 2026-05-17 |  | 2026-06-14 | 28 Days | B | [13 empty] | 1 |  |  |  |  | Approved with Comments
|  | 2 | MLTX-02-003-ADV-MSA-0002-00 | 00 | ADV-0002 | MSA | Material Source Approval "Al-Sayigh Crusher" for A-1-a fill material |  | Qassim | 2026-05-20 |  | 2026-06-18 | 29 Days | C | [14 empty] | 1 |  |  |  | Revise & Resubmit
|  | 3 | MLTX-02-003-ADV-MSA-0003-00 | 00 | ADV-0003 | MSA | Material Source Approval "Al-Sayigh Crusher" for A-1-b fill material |  | Qassim | 2026-05-20 |  |  | 134 Days | UR | [17 empty] | 1 | Delayed with Egis
|  | 4 | MLTX-02-003-ADV-MSA-0004-00 | 00 | ADV-0004 | MSA | Material Source Approval "ASAS Al-Mohileb Crusher" A-1-a fill material |  | Tabuk | 2026-05-21 |  |  | 133 Days | UR | [17 empty] | 1 | Delayed with Egis
|  | 5 | MLTX-02-003-ADV-MSA-0005-00 | 00 | ADV-0005 | MSA | Material Source Approval "Al-Sayigh Crusher" for Aggregate Base Course Material |  | Qassim | 2026-06-21 |  |  | 102 Days | UR | [17 empty] | 1 | Delayed with Egis
|  | 6 | MLTX-02-003-ADV-MSA-0006-00 | 00 | ADV-0006 | MSA | Material Source Approval (MSA) of “ASAS Al-Mohelib Crusher” for Sub-Base Material |  | Tabuk | 2026-07-01 |  |  | 92 Days | UR | [17 empty] | 1 | Delayed with Egis
|  | 7 | MLTX-02-003-ADV-MSA-0007-00 | 00 | ADV-0007 | MSA | Material Source Approval (MSA) of “Expert Future for Asphalt Co.” for the Aggregate Base Course |  | Tabuk | 2026-07-16 |  |  | 77 Days | UR | [17 empty] | 1 | Delayed with Egis
|  | 8 | MLTX-02-003-ADV-MSA-0008-00 | 00 | ADV-0008 | MSA | Material Source Approval (MSA) of “Asas Almohaileb for Ready Mix Concrete” for Concrete Mix Design C35 OPC/SRC |  | Tabuk | 2026-07-16 |  |  | 77 Days | UR | [17 empty] | 1 | Delayed with Egis
|  | 9 | MLTX-02-003-ADV-MSA-0009-00 | 00 | ADV-0009 | MSA | Material Source Approval (MSA) of “Al- Fouzan Ready-mix & Cement Products” for Ready-mix Concrete C20 CRS, C35 CRS |  | Qassim | 2026-07-27 |  |  | 66 Days | UR | [17 empty] | 1 | Delayed with Egis
|  | 10 | MLTX-05-047-ADV-MSA-0010-00 | 00 | ADV-0010 | MSA | MSA material source approval of Bituminous base course class B from Expert future asphalt patch plant for TABUK project. |  | Tabuk | 2026-09-17 |  |  | 14 Days | UR | [17 empty] | 1 | Delayed with Egis
|  | 11 | MLTX-05-047-ADV-MSA-0011-00 | 00 | ADV-0011 | MSA | MSA materials source approval of Bituminous Wearing course class C from EPAERT FUTURE PATCH PLANT for Tabuk playgrounds project |  | Tabuk | 2026-09-17 |  | 2026-09-28 | 11 Days | C | [14 empty] | 1 |  |  |  | Revise & Resubmit
|  | 12 | MLTX-05-047-ADV-MSA-0012-00 | 00 | ADV-0012 | MSA | material source approval of Bituminous Base Course class B from SHIBH Aljazeera Asphalt patch plant for Qasim project |  | Qassim | 2026-09-19 |  |  | 12 Days | UR | [17 empty] | 1 | Delayed with Egis
|  | 13 | MLTX-05-047-ADV-MSA-0013-00 | 00 | ADV-0013 | MSA | MSA for Bituminous Wearing Course class C (BWC-C) from SHIBH ALJAZEERA asphalt patch plant for playgrounds project at QASSIM. |  | Qassim | 2026-09-19 |  | 2026-09-22 | 3 Days | C | [14 empty] | 1 |  |  |  | Revise & Resubmit
14
Formulas:
Duration with Egis = IF([Actual Submission Date]="","",(IF([Date of Return Egis]="",TODAY()-[Actual Submission Date],[Date of Return Egis]-[Actual Submission Date])+0)) & " Days "