## Dashboard (hidden)
MODON Design Department — Risk & Issue Dashboard
Open Risks | High | Medium | Low |  |  | Open Issues | Critical | High | Normal
246 | 0 | 0 | 0 |  |  | 133 | 0 | 0 | 0
Risks by category × rating | [5 empty] | Issues by category × priority
Category | High | Medium | Low | Total | Exposure (SAR M) | Category | Critical | High | Normal | Total | Exposure (SAR M)
Contractor Performance | 0 | 0 | 0 | 0 | 0 | Contractor Performance | 0 | 0 | 0 | 0 | 0
Contractual | 0 | 0 | 0 | 0 | 0 | Contractual | 0 | 0 | 0 | 0 | 0
Cost | 0 | 0 | 0 | 0 | 0 | Cost | 0 | 0 | 0 | 0 | 0
Financial | 0 | 0 | 0 | 0 | 0 | Design/Technical | 0 | 0 | 0 | 0 | 0
Reporting | 0 | 0 | 0 | 0 | 0 | Financial | 0 | 0 | 0 | 0 | 0
Resources | 0 | 0 | 0 | 0 | 0 | Interface/Utilities | 0 | 0 | 0 | 0 | 0
Schedule | 0 | 0 | 0 | 0 | 0 | Permits/Stakeholder | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | Quality/HSE | 0 | 0 | 0 | 0 | 0
[6 empty] | Schedule | 0 | 0 | 0 | 0 | 0
[6 empty] | Scope | 0 | 0 | 0 | 0 | 0
[6 empty] | Site/Technical | 0 | 0 | 0 | 0 | 0
[6 empty] | Total | 0 | 0 | 0 | 0 | 0
Risks by fund source | [5 empty] | Issues by fund source
Category | High | Medium | Low | Total |  | Category | Critical | High | Normal | Total
MODON | 0 | 0 | 0 | 0 |  | MODON | 0 | 0 | 0 | 0
MOF | 0 | 0 | 0 | 0 |  | MOF | 0 | 0 | 0 | 0
MTLS | 0 | 0 | 0 | 0 |  | MTLS | 0 | 0 | 0 | 0
Modon | 0 | 0 | 0 | 0 |  | Modon | 0 | 0 | 0 | 0
NIDLP | 0 | 0 | 0 | 0 |  | NIDLP | 0 | 0 | 0 | 0
NIS | 0 | 0 | 0 | 0 |  | NIS | 0 | 0 | 0 | 0
Other | 0 | 0 | 0 | 0 |  | Other | 0 | 0 | 0 | 0
WAS | 0 | 0 | 0 | 0 |  | WAS | 0 | 0 | 0 | 0
التجمعات الصناعية | 0 | 0 | 0 | 0 |  | التجمعات الصناعية | 0 | 0 | 0 | 0
الصندوق الصناعي | 0 | 0 | 0 | 0 |  | الصندوق الصناعي | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 |  | Total | 0 | 0 | 0 | 0
Scoring: Risk Score = Probability × Impact → High ≥15, Medium 8–14, Low <8. Issue Priority = Severity × Urgency → Critical ≥15, High 8–14, Normal <8. Impact from value: ≥100M=5, 50–100M=4, 20–50M=3, 5–20M=2, <5M=1. Counts exclude entries with Status = Closed.

## Risk Log
Risk Log
Risk ID | Parent Project ID | Contract / Project ID | Project Name | City | Region | Fund Source | Phase | PM / Owner | Contractor / Designer | Current Status | Value (SAR) | Category | Risk Title | Description | Evidence / Data | Probability (1-5) | Impact (1-5) | Score | Rating | Response | Mitigation Plan | Date Identified | Status | Target Date | Notes / Updates | Source
MKH2-02-004-01 |  | MKH2-02-004 | Road Development for the Support Services Area at the Second Industrial City in Makkah (Al-Akayshiyah) | Makkah | Western | MODON | MODON-MIC Phase II | Engr. Abdallah Aljulaifi | Al Enjaz Trading & Contracting Co. | In Progress | 33040004 | Quality/HSE | Fall into excavation pit, causing injury to workers. | Unstable soil and absence of adequate barricading. |  | 2 | 3 |  |  |  | Set up barricades around excavation areas less than 3 meters deep, provide warning signs, and assign a supervisor to monitor the area. | 2026-07-25 | In Progress | 2026-12-20
MKH2-02-004-02 |  | MKH2-02-004 | Road Development for the Support Services Area at the Second Industrial City in Makkah (Al-Akayshiyah) | Makkah | Western | MODON | MODON-MIC Phase II | Engr. Abdallah Aljulaifi | Al Enjaz Trading & Contracting Co. | In Progress | 33040004 | Quality/HSE | Vehicle accidents due to improper traffic management. | Inadequate traffic diversion measures |  | 2 | 3 |  |  |  | Implement proper traffic diversion signs, barriers, and personnel to manage traffic flow around the worksite. | 2026-07-25 | In Progress | 2027-06-03
MKH2-02-004-03 |  | MKH2-02-004 | Road Development for the Support Services Area at the Second Industrial City in Makkah (Al-Akayshiyah) | Makkah | Western | MODON | MODON-MIC Phase II | Engr. Abdallah Aljulaifi | Al Enjaz Trading & Contracting Co. | In Progress | 33040004 | Quality/HSE | Accidents or errors during operations due to operator incompetence. | Insufficient training, lack of experience, and inadequate supervision of operators. |  | 2 | 3 |  |  |  | Provide comprehensive training programs, implement competency assessments, and establish strict supervision protocols for operators. | 2026-07-25 | In Progress | 2027-06-03
MKH2-02-004-04 |  | MKH2-02-004 | Road Development for the Support Services Area at the Second Industrial City in Makkah (Al-Akayshiyah) | Makkah | Western | MODON | MODON-MIC Phase II | Engr. Abdallah Aljulaifi | Al Enjaz Trading & Contracting Co. | In Progress | 33040004 | Quality/HSE | Contamination of soil and potential harm to surrounding ecosystems. | Equipment failure, improper handling of oil, or accidental leaks during storage and transport. |  | 2 | 3 |  |  |  | Implement spill response plans, conduct regular maintenance on equipment, provide training on proper handling procedures, and install containment measures to prevent spillage. | 2026-07-25 | In Progress | 2027-06-03

## Issue Log
Issue Log
Issue ID | Parent Project ID | Contract / Project ID | Project Name | City | Region | Fund Source | Phase | PM / Owner | Contractor / Designer | Current Status | Value (SAR) | Category | Issue Title | Description | Evidence / Data | Severity (1-5) | Urgency (1-5) | Priority Score | Priority | Action Required | Date Raised | Status | Target Date | Resolution / Updates | Source

## Lists (hidden)
Status | Response | Scale | RiskCategory
Open | Avoid | 1 | Schedule
In Progress | Mitigate | 2 | Cost
Monitoring | Transfer | 3 | Financial
Closed | Accept | 4 | Scope
|  | 5 | Contractual
Resources
Contractor Performance
Reporting
Design/Technical
Permits/Stakeholder
Interface/Utilities
Quality/HSE
Site/Technical

## Rules (hidden)
Detection rules & methodology
Each entry in the logs was generated by one of these rules. Adjust thresholds here for reference; logs are static once generated.
Log | Rule | Condition (source field) | Default score | Suggested response
Issue | Schedule slippage beyond tolerance | CWAR Schedule Variance < −10% (Severity 5 if < −25%) | Sev 4–5 × Urg 4 | Recovery plan, EOT/penalty assessment
Issue | Contract flagged as delayed | CWAR "Delayed?" = 1 | Sev 4 × Urg 4 | Delay notice, revised finish
Issue | Extension of time granted | CWAR Approved Extension Of Time > 0 | Sev 3 × Urg 2 | Track vs revised finish
Issue | Contract on hold | CWAR Current Status = Hold | Sev 5 × Urg 5 | Escalate, resumption plan
Issue | Invoices pending payment | CWAR Invoices Pending Payment > 0 | Sev 3 × Urg 3 | Finance follow-up
Issue | Contract value exceeds approved budget | CWAR Current Approved Contract Value > Approved Budget | Sev 4 × Urg 3 | Budget re-approval
Issue | EAC exceeds contract value | CWAR EAC > Current Approved Contract Value | Sev 4 × Urg 3 | Validate EAC, variation
Issue | Approved change orders | CWAR Approved Change Orders (Nos.) > 0 | Sev 2 × Urg 2 | Update baseline
Issue | Guarantee / insurance expired | CWAR "Expired or Expiring in 3 Months" = منتهي الصلاحية, or Insurance Expiry < Data Date | Sev 4 × Urg 5 | Immediate renewal
Issue | Quality / Safety NCRs | CWAR NCRs Issued > 0 | Sev 3 × Urg 3 | Corrective action
Issue | Site / interface / permit / design / contractor issue | CWAR "Remarks on Schedule Status" non-empty (keyword-classified into category) | Sev 3–4 × Urg 3 | PM action owner
Issue | Ongoing project without full approval | All Projects: Status = Ongoing and حالة الاعتماد ∈ {غير معتمد, اعتماد جزئي} | Sev 3–4 × Urg 4 | Expedite approval
Risk | Progress trending behind plan | CWAR Schedule Variance between −5% and −10% | Prob 3 | Mitigate
Risk | Guarantee / insurance expiring ≤ 3 months | CWAR "Expired or Expiring" = تنتهي في ثلاثة أشهر, or Insurance Expiry within 90 days | Prob 4 | Mitigate
Risk | Insufficient time to complete | CWAR Remaining Duration < 90 days and Actual < 85% (Active) | Prob 4 | Mitigate
Risk | Manpower below plan | CWAR Actual Manpower < 70% of Plan Manpower | Prob 3 | Mitigate
Risk | Potential change orders | CWAR Potential Changes (Active) > 0 | Prob 3 | Mitigate
Risk | Baseline not approved / works suspended | CWAR "Delays by Modon or Contractor" contains baseline / stoppage keywords | Prob 3–4 | Mitigate
Risk | Mobilisation / start-up delay | CWAR Status ∈ {LOA, Open} or Actual = 0% more than 60 days after contract start | Prob 3 | Mitigate
Risk | Contractor delayed on multiple contracts | Same contractor with ≥2 active contracts at SV < −10% | Prob 4 | Mitigate
Risk | Budget not approved for next phase | All Projects: Status ∈ {Design completed, Tendered, Future} and حالة الاعتماد ∈ {غير معتمد, اعتماد جزئي} | Prob 3–4 | Mitigate
Risk | No approved budget baseline | All Projects: Status ∈ {Design completed, Future, Under design} and Approved Budget blank/0 | Prob 3 | Mitigate
Risk | Completed design awaiting tender | All Projects: Status = Design completed and no Contractor | Prob 2 | Accept / monitor
Risk | No active CWAR record | All Projects: Status = Ongoing and Parent Project ID not found in active CWAR rows | Prob 3 | Mitigate
Both | Impact scale (from value incl. VAT) | ≥100M = 5 · 50–100M = 4 · 20–50M = 3 · 5–20M = 2 · <5M = 1
Both | Scope | Active CWAR = Current Status ∈ {Active, Substantial Complete, LOA, Hold, Open}. Portfolio excludes Completed, Closed, Merged, Terminated.